## Sheet1 (2)
WBS Level | Trimmed ID | Activity Name | Start | Finish | WBS_Level
1 | CCPP Project Standard Schedule_20181012_Idea |  | 2007-03-01 | 2009-11-02
2 | Plant General |  | 2007-03-01 | 2009-11-02
3 | Key Milestones |  | 2007-03-01 | 2009-11-02
4 | Guaranteed Completion Date |  | 2007-03-01 | 2009-11-02
Activity | 1SF0500W00A01 | NTP | 2007-03-01
Activity | 1SF0500W00A02 | GTG #11 TOD |  | 30-Nov-08*
Activity | 1SF0500W00A03 | GTG #12 TOD |  | 30-Nov-08*
Activity | 2SF0500W00A04 | GTG #21 TOD |  | 2009-01-03
Activity | 2SF0500W00A05 | GTG #22 TOD |  | 2009-01-03
Activity | 3SF0500W00A06 | GTG #31 TOD |  | 2009-02-01
Activity | 3SF0500W00A07 | GTG #32 TOD |  | 2009-02-01
Activity | 1SF0500W00A08 | HRSG #11 TOD |  | 2009-03-25
Activity | 1SF0500W00A09 | HRSG #12 TOD |  | 2009-03-26
Activity | 2SF0500W00A10 | HRSG #21 TOD |  | 2009-04-27
Activity | 2SF0500W00A11 | HRSG #22 TOD |  | 2009-04-27
Activity | 3SF0500W00A12 | HRSG #31 TOD |  | 2009-05-27
Activity | 3SF0500W00A13 | HRSG #32 TOD |  | 2009-05-27
Activity | 1SF0500W00A14 | STG #10 TOD |  | 31-Aug-09*
Activity | 2SF0500W00A15 | STG #20 TOD |  | 02-Oct-09*
Activity | 3SF0500W00A16 | STG #30 TOD |  | 2009-11-02
4 | Utilities Ready by Owner/ Contractor |  | 2008-08-08 | 2008-10-18
Activity | 0SF0500W00A03 | Fuel Oil Available from Owner | 2008-08-08
Activity | 0SF0500W00A01 | Power Receiving from Owner | 16-Sep-08*
Activity | 0SF0500W00A02 | Fuel Gas Available from Owner | 18-Oct-08*
3 | Plant Engineering |  | 2007-03-01 | 2008-02-15
4 | Basic Engineering & Design |  | 2007-03-01 | 2008-02-15
Activity | 0EF1000W00A01 | Heat Balance Diagram | 2007-03-01 | 2007-07-02
Activity | 0EF1000W00A02 | Plant Plot Plan | 2007-03-01 | 2007-08-28
Activity | 0EF1000W00A05 | Single Line Diagram | 2007-03-01 | 2007-10-12
Activity | 0EF1000W00A04 | Mechanical Design Criteria | 2007-03-15 | 2007-07-24
Activity | 0EF1000W00A03 | Plant General Arrangement | 2007-03-30 | 2007-10-08
Activity | 0EF1000W00A06 | Control Room Layout | 2007-03-30 | 2007-07-03
Activity | 0EF1000W00A07 | P&ID | 2007-04-30 | 2007-11-06
Activity | 0EF1000W00A09 | DCS I/O List of Overall Plant | 2007-04-30 | 2007-12-31
Activity | 0EF1000W00A10 | Instrument Installation Detail | 2007-05-11 | 2007-09-28
Activity | 0EF1000W00A08 | Operational Philosophy of Overall Plant | 2007-06-22 | 2008-02-15
3 | General Civil Works |  | 2007-03-01 | 2007-12-14
4 | Site Preparation |  | 2007-03-01 | 2007-09-28
Activity | 0EF6010W10A01 | Soil Investigation Plan(NTP 이전 완료) | 2007-03-01 | 2007-03-29
Activity | 0EF6010W10A03 | Site Preparation Layout | 2007-03-01 | 2007-05-29
Activity | 0CF6010W10A02 | Soil Investigation Work(NTP 이전 완료) from NTP-1.5M | 2007-03-01 | 2007-03-30
Activity | 0CF6010W28A05 | Land Scape | 2007-03-01 | 2007-06-28
Activity | 0CF6010W10A04 | Site Preparation Civil Work | 2007-03-31 | 2007-09-28
4 | Piling & Soil Improvement |  | 2007-03-01 | 2007-12-14
Activity | 0EF6010W12A01 | Soil Improvement Design | 2007-03-01 | 2007-05-31
Activity | 0EF2000W14A14 | STG Area Pile Design | 2007-03-30 | 2007-07-02
Activity | 0EF1600W14A10 | HRSG Area Pile Design | 2007-04-02 | 2007-06-15
Activity | 0EF1200W14A03 | GTG Area Pile Design | 2007-04-02 | 2007-05-31
Activity | 0CF6010W12A04 | Pre-Excavation(GTG, HRSG,STG Area) Block #1 | 2007-05-15 | 2007-06-30
Activity | 0CF1200W14A07 | GTG Block #1 Area Piling Work(Incl. CCB) | 2007-06-01 | 2007-07-31
Activity | 0CF6010W12A02 | Soil Improvement Work | 2007-06-01 | 2007-07-03
Activity | 0CF6010W12A05 | Pre-Excavation(GTG, HRSG,STG Area) Block #2 | 2007-06-14 | 2007-07-31
Activity | 0CF1600W14A11 | HRSG Block #1 Area Piling Work | 2007-07-02 | 2007-09-17
Activity | 0CF1200W14A08 | GTG Block #2 Area Piling Work | 2007-07-02 | 2007-08-30
Activity | 0CF6010W12A06 | Pre-Excavation(GTG, HRSG,STG Area) Block #3 | 2007-07-14 | 2007-08-30
Activity | 0CF2000W14A15 | STG Block #1 Area Piling Work | 2007-08-01 | 2007-10-15
Activity | 0CF1200W14A09 | GTG Block #3 Area Piling Work | 2007-08-01 | 2007-09-29
Activity | 0CF1600W14A12 | HRSG Block #2 Area Piling Work | 2007-08-01 | 2007-10-17
Activity | 0CF1600W14A13 | HRSG Block #3 Area Piling Work | 2007-08-31 | 2007-11-16
Activity | 0CF2000W14A16 | STG Block #2 Area Piling Work | 2007-08-31 | 2007-11-14
Activity | 0CF2000W14A17 | STG Block #3 Area Piling Work | 2007-10-01 | 2007-12-14
2 | Plant Common |  | 2007-03-01 | 2009-03-20
3 | Fuel Gas & Oil Supply Systems |  | 2007-03-01 | 2008-09-23
4 | Fuel Gas Supply System |  | 2007-03-01 | 2008-09-23
Activity | 0EF3520W00A02 | (FGSS) FGSS Key Data | 2007-03-01 | 2007-03-30
Activity | 0EF3520W00A01 | (FGSS) P&ID & System Design | 2007-03-15 | 2007-09-20
5 | Gas Buffer |  | 2007-03-30 | 2008-09-23
Activity | 0EF3520W42A03 | (Gas Buffer) MPS Issue |  | 2007-03-30
Activity | 0PF3520W42A04P | (Gas Buffer) P.O & Procurement(incl. FG Booster Comp.&Bottles) | 2007-06-01 | 2008-04-01
Activity | 0EF3520W16A01 | (Gas Buffer) FDN Design | 2007-08-02 | 2007-12-04
Activity | 0CF3520W16A02 | (Gas Buffer) FDN Work | 2007-12-05 | 2008-02-04
Activity | 0PF3520W42A05T | (Gas Buffer) Transportation(incl. FG Booster Comp.&Bottles) | 2008-04-02 | 2008-05-16
Activity | 0CF3520W42A06 | (Gas Buffer) Installation(incl. FG Booster Comp.&Bottles) | 2008-05-17 | 2008-05-31
Activity | 0SF3520W62A07.0 | (Gas Buffer) Loop chek | 2008-06-01 | 2008-06-02
Activity | 0SF3520W62A08 | (Gas Buffer) Function Test | 2008-06-03 | 2008-06-04
Activity | 0SF3520W62A09 | (Gas Buffer) Load Test | 2008-09-22 | 2008-09-23
5 | Flare Cum Incinerator |  | 2007-03-30 | 2008-05-24
Activity | 0EF3520W42A03.2 | (Flare cum incinerator) MPS Issue |  | 2007-03-30
Activity | 0EF3520W16A01.2 | (Flare cum incinerator) FDN Design | 2007-06-01 | 2007-10-11
Activity | 0PF3520W42A04.2P | (Flare cum incinerator) P.O & Procurement | 2007-06-01 | 2008-03-03
Activity | 0CF3520W16A02.2 | (Flare cum incinerator) FDN Work | 2007-10-12 | 2007-12-08
Activity | 0PF3520W42A05.2T | (Flare cum incinerator) Transportation | 2008-03-04 | 2008-04-17
Activity | 0CF3520W42A06.2 | (Flare cum incinerator) Installation | 2008-04-18 | 2008-05-19
Activity | 0SF3520W62A07 | (Flare cum incinerator) Loop chek | 2008-05-20 | 2008-05-22
Activity | 0SF3520W62A08.2 | (Flare cum incinerator) Function Test | 2008-05-23 | 2008-05-24
5 | Condensate System |  | 2007-03-30 | 2008-05-16
Activity | 0EF3520W68A03 | (Condensate Tank) MPS Issue |  | 2007-03-30
Activity | 0EF3520W42A07 | (Condensate Pump) MPS Issue |  | 2007-03-30
Activity | 0EF3520W16A01.1 | (Condensate Tank & Pump) FDN Design | 2007-06-01 | 2007-10-11
Activity | 0PF3520W68A04P | (Condensate Tank) P.O & Procurement | 2007-06-01 | 2008-01-30
Activity | 0PF3520W42A08P | (Condensate Pump) P.O & Procurement | 2007-06-01 | 2008-01-30
Activity | 0CF3520W16A02.1 | (Condensate Tank & Pump) FDN Work | 2007-10-12 | 2007-12-08
Activity | 0PF3520W68A05T | (Condensate Tank) Transportation | 2008-01-31 | 2008-03-15
Activity | 0PF3520W42A09T | (Condensate Pump) Transportation | 2008-01-31 | 2008-03-15
Activity | 0CF3520W68A06 | (Condensate Tank) Installation | 2008-03-17 | 2008-05-16
Activity | 0CF3520W42A10.1 | (Condensate Pump) Installation | 2008-03-17 | 2008-05-16
5 | Fuel Gas Supply System LEB |  | 2007-05-15 | 2008-07-28
Activity | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | 2007-05-15
Activity | 0EF3520W16A02.1 | (FGS LEB) FDN Design | 2007-05-15 | 2007-09-13
Activity | 0EF3520W32A04.1 | (FGS LEB) Structure Design | 2007-05-15 | 2007-09-13
Activity | 0CF3520W16A03.1 | (FGS LEB) FDN Work | 2007-09-14 | 2007-11-10
Activity | 0CF3520W32A05.1 | (FGS LEB) Structure Work | 2007-11-12 | 2008-02-09
Activity | 0CF3520W74A08.1 | (FGS LEB) Installation & Test - Elec | 2008-01-11 | 2008-03-08
Activity | 0CF3520W90A09.1 | (FGS LEB) Installation & Test - I&C | 2008-01-11 | 2008-03-08
Activity | 0CF3520W36A07.1 | (FGS LEB) Installation & Test - HVAC | 2008-05-15 | 2008-07-11
Activity | 0CF3520W38A06.1 | (FGS LEB) Installation & Test - Fire Fighting Sys. | 2008-05-31 | 2008-07-28
Activity | 0CF3520W24A10.1 | (FGS LEB) Building Finish | 2008-05-31 | 2008-07-28
4 | Fuel Oil Supply System |  | 2007-03-15 | 2008-08-29
Activity | 0EF3520W00A02.2 | (FOSS) P&ID & System Design | 2007-03-15 | 2007-10-29
Activity | 0EF3520W00A01.2 | (FOSS) FO Forwarding Pump, FO Unloading Pump Key data | 2007-04-02 | 2007-04-30
Activity | 0CF3520W58A03 | (FOSS) Piping Work(Oil Farm Area) | 2008-03-03 | 2008-06-20
Activity | 0CF3520W74A04 | (FOSS) Installation & Test - Elec. | 2008-05-06 | 2008-06-20
Activity | 0CF3520W90A05 | (FOSS) Installation & Test - I&C | 2008-05-06 | 2008-06-20
Activity | 0SF3520W62A06 | (FOSS) Fuel Oil Filling DFO Tank | 2008-08-08 | 2008-08-14
Activity | 0SF3520W62A07.2 | (FOSS) Oil Flushing(Forward Line) | 2008-08-15 | 2008-08-29
5 | Fuel Oil Forward Station |  | 2007-04-30 | 2008-06-20
Activity | 0EF3520W42A03.3 | (FOFP) MPS Issue |  | 2007-04-30
Activity | 0EF3520W00A10.3 | (FO FWD Station Shelter) GA & Load Data to Civil Design | 2007-07-02
Activity | 0EF3520W16A11.3 | (FO FWD Station Shelter) FDN Design | 2007-07-02 | 2007-10-26
Activity | 0EF3520W32A13.3 | (FO FWD Station Shelter) Structure Design | 2007-07-02 | 2007-10-26
Activity | 0EF3520W16A01.3 | (FOFP) FDN Design | 2007-07-02 | 2007-10-30
Activity | 0PF3520W42A04.3P | (FOFP) P.O & Procurement | 2007-07-02 | 2008-03-28
Activity | 0CF3520W16A12.3 | (FO FWD Station Shelter) FDN Work | 2007-10-27 | 2007-12-24
Activity | 0CF3520W16A02.3 | (FOFP) FDN Work | 2007-10-31 | 2007-12-27
Activity | 0CF3520W32A14.3 | (FO FWD Station Shelter) Structure Work | 2007-12-25 | 2008-03-26
Activity | 0PF3520W42A05.3T | (FOFP) Transportation | 2008-03-29 | 2008-05-13
Activity | 0CF3520W24A15.3 | (FO FWD Station Shelter) Shelter Finish | 2008-04-29 | 2008-06-13
Activity | 0CF3520W42A06.3 | (FOFP) Installation | 2008-05-14 | 2008-06-13
Activity | 0SF3520W62A07.3 | (FOFP) Loop chek | 2008-06-14 | 2008-06-16
Activity | 0SF3520W62A08.3 | (FOFP) Function Test | 2008-06-17 | 2008-06-18
Activity | 0SF3520W62A09.3 | (FOFP) Load Test | 2008-06-19 | 2008-06-20
5 | Fuel Oil Unloading Station |  | 2007-04-30 | 2008-06-20
Activity | 0EF3520W42A03.4 | (FOUP) MPS Issue |  | 2007-04-30
Activity | 0EF3520W00A10.4 | (FO Unloading Station Shelter) GA & Load Data to Civil Design | 2007-07-02
Activity | 0EF3520W16A11.4 | (FO Unloading Station Shelter) FDN Design | 2007-07-02 | 2007-10-30
Activity | 0EF3520W32A13.4 | (FO Unloading Station Shelter) Structure Design | 2007-07-02 | 2007-10-30
Activity | 0PF3520W42A04.4P | (FOUP) P.O & Procurement | 2007-07-02 | 2008-03-28
Activity | 0EF3520W16A01.4 | (FOUP) FDN Design | 2007-07-02 | 2007-09-28
Activity | 0CF3520W16A02.4 | (FOUP) FDN Work | 2007-09-29 | 2007-11-26
Activity | 0CF3520W16A12.4 | (FO Unloading Station Shelter) FDN Work | 2007-10-31 | 2007-12-27
Activity | 0CF3520W32A14.4 | (FO Unloading Station Shelter) Structure Work | 2007-12-28 | 2008-03-29
Activity | 0PF3520W42A05.4T | (FOUP) Transportation | 2008-03-29 | 2008-05-13
Activity | 0CF3520W24A15.4 | (FO Unloading Station Shelter) Shelter Finish | 2008-04-29 | 2008-06-13
Activity | 0CF3520W42A06.4 | (FOUP) Installation | 2008-05-14 | 2008-06-13
Activity | 0SF3520W62A07.4 | (FOUP) Loop chek | 2008-06-14 | 2008-06-16
Activity | 0SF3520W62A08.4 | (FOUP) Function Test | 2008-06-17 | 2008-06-18
Activity | 0SF3520W62A09.4 | (FOUP) Load(Running) Test | 2008-06-19 | 2008-06-20
5 | Foam Station Building |  | 2007-05-01 | 2008-07-28
Activity | 0EF3520W00A01.3 | (Foam Station BLDG) GA & Load Data to Civil Design | 2007-05-01
Activity | 0EF3520W16A02.3 | (Foam Station BLDG) FDN Design | 2007-05-01 | 2007-10-01
Activity | 0EF3520W32A04.3 | (Foam Station BLDG) Structure Design | 2007-05-01 | 2007-10-01
Activity | 0CF3520W16A03.3 | (Foam Station BLDG) FDN Work | 2007-10-02 | 2007-11-28
Activity | 0CF3520W32A05.3 | (Foam Station BLDG) Structure Work | 2007-11-29 | 2008-02-29
Activity | 0CF3520W74A08.3 | (Foam Station BLDG) Installation & Test - Elec | 2008-02-01 | 2008-03-29
Activity | 0CF3520W90A09.3 | (Foam Station BLDG) Installation & Test - I&C | 2008-02-01 | 2008-03-29
Activity | 0CF3520W36A07.3 | (Foam Station BLDG) Installation & Test - HVAC | 2008-05-15 | 2008-07-12
Activity | 0CF3520W38A06.3 | (Foam Station BLDG) Installation & Test - Fire Fighting Sys. | 2008-05-31 | 2008-07-28
Activity | 0CF3520W24A10.3 | (Foam Station BLDG) Building Finish | 2008-05-31 | 2008-07-28
5 | DFO Tank & Pump |  | 2007-05-01 | 2008-08-15
Activity | 0EF3520W16A01.5 | (DFO Tank) FDN Design | 2007-05-01 | 2007-08-30
Activity | 0CF3520W16A02.5 | (DFO Tank) FDN Work | 2007-08-31 | 2007-10-27
Activity | 0CF3520W68A03 | (DFO Tank) Installation(incl. Painting & Test for only 2EA) | 2007-10-29 | 2008-03-31
Activity | 0CF3520W16A04 | (Transfer Pump) FDN Work | 2007-10-31 | 2007-12-27
Activity | 0CF3520W16A06 | (Day Tank) FDN Work | 2008-01-02 | 2008-02-28
Activity | 0CF3520W42A05 | (Transfer Pump) Installation | 2008-05-14 | 2008-06-13
Activity | 0CF3520W68A07 | (Day Tank) Installation | 2008-05-14 | 2008-06-13
Activity | 0CF3520W42A10 | (Day Tank Fill up Pump) Installation | 2008-05-14 | 2008-06-13
Activity | 0SF3520W62A08.5 | (Transfer Pump) Loop chek | 2008-06-14 | 2008-06-16
Activity | 0SF3520W62A11 | (Day Tank Fill up Pump) Loop chek | 2008-06-14 | 2008-06-16
Activity | 0SF3520W62A09.5 | (Transfer Pump) Function Test | 2008-06-17 | 2008-06-18
Activity | 0SF3520W62A12 | (Day Tank Fill up Pump) Function Test | 2008-06-17 | 2008-06-18
Activity | 0SF3520W62A13.5 | (Day Tank) Day Tank filling | 2008-08-15 | 2008-08-15
5 | Slop Oil Tank & Pump |  | 2007-04-30 | 2008-06-11
Activity | 0EF3520W42A09.6 | (SOP) MPS Issue |  | 2007-04-30
Activity | 0EF3520W42A03.6 | (SOT) MPS Issue |  | 2007-04-30
Activity | 0PF3520W42A10.6P | (SOP) P.O & Procurement | 2007-07-02 | 2008-02-28
Activity | 0PF3520W42A04.6P | (SOT) P.O & Procurement | 2007-07-02 | 2008-03-28
Activity | 0EF3520W16A07.6 | (SOP) FDN Design | 2007-08-31 | 2008-01-09
Activity | 0EF3520W16A01.6 | (SOT) FDN Design | 2007-08-31 | 2008-01-01
Activity | 0CF3520W16A02.6 | (SOT) FDN Work | 2008-01-02 | 2008-02-28
Activity | 0CF3520W16A08.6 | (SOP) FDN Work | 2008-01-10 | 2008-02-07
Activity | 0PF3520W42A11.6T | (SOP) Transportation | 2008-02-29 | 2008-04-14
Activity | 0PF3520W42A05.6T | (SOT) Transportation | 2008-03-29 | 2008-05-13
Activity | 0CF3520W42A12.6 | (SOP) Installation | 2008-04-15 | 2008-05-15
Activity | 0CF3520W42A06.6 | (SOT) Installation | 2008-05-14 | 2008-06-11
Activity | 0SF3520W62A13.6 | (SOP) Loop chek | 2008-05-16 | 2008-05-18
Activity | 0SF3520W62A14.6 | (SOP) Function Test | 2008-05-19 | 2008-05-20
5 | Fuel Oil Supply System LEB |  | 2007-05-01 | 2008-07-28
Activity | 0EF3520W00A01.4 | (FO LEB) GA & Load Data to Civil Design | 2007-05-01
Activity | 0EF3520W16A02.4 | (FO LEB) FDN Design | 2007-05-01 | 2007-08-30
Activity | 0EF3520W32A04.4 | (FO LEB) Structure Design | 2007-05-01 | 2007-08-30
Activity | 0CF3520W16A03.4 | (FO LEB) FDN Work | 2007-08-31 | 2007-10-27
Activity | 0CF3520W32A05.4 | (FO LEB) Structure Work | 2007-10-29 | 2008-02-27
Activity | 0CF3520W74A08.4 | (FO LEB) Installation & Test - Elec | 2008-01-30 | 2008-03-27
Activity | 0CF3520W90A09.4 | (FO LEB) Installation & Test - I&C | 2008-01-30 | 2008-03-27
Activity | 0CF3520W36A07.4 | (FO LEB) Installation & Test - HVAC | 2008-05-15 | 2008-06-26
Activity | 0CF3520W38A06.4 | (FO LEB) Installation & Test - Fire Fighting Sys. | 2008-05-31 | 2008-07-28
Activity | 0CF3520W24A10.4 | (FO LEB) Building Finish | 2008-05-31 | 2008-07-28
4 | Fuel Oil Metering System |  | 2007-04-30 | 2008-05-30
Activity | 0EF3520W42A01 | (FO Metering Equip) MPS Issue |  | 2007-04-30
Activity | 0PF3520W42A02P | (FO Metering Equip) P.O & Procurement | 2007-06-29 | 2008-03-17
Activity | 0PF3520W42A03T | (FO Metering Equip) Transportation | 2008-03-18 | 2008-05-01
Activity | 0CF3520W42A04 | (FO Metering Equip) Installation | 2008-05-02 | 2008-05-30
3 | Water & Air Supply System |  | 2007-03-01 | 2009-03-20
4 | Make-up Water Supply System |  | 2007-03-01 | 2008-08-11
Activity | 0EF3010W00A01.0 | (Make-up WTR Supply System) Demi WTR Supply pump Key Data | 2007-03-01 | 2007-05-01
Activity | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | 2007-03-15 | 2007-11-21
Activity | 0EF3010W16A06 | (Make-up WTR Tank) FDN Design | 2007-08-02 | 2007-10-30
Activity | 0CF3010W16A07 | (Make-up WTR Tank) FDN Work | 2007-10-31 | 2007-12-31
Activity | 0CF3010W42A08 | (Make-up WTR Tank) Installation(incl. Painting & Test) | 2008-01-01 | 2008-05-14
Activity | 0CF3010W58A03 | (Make-up WTR Supply System) Piping Work | 2008-05-19 | 2008-07-18
Activity | 0CF3010W74A04 | (Make-up WTR Supply System) Installation & Test - Elec. | 2008-05-19 | 2008-07-18
Activity | 0CF3010W90A05 | (Make-up WTR Supply System) Installation & Test - I&C | 2008-05-19 | 2008-07-18
Activity | 0CF3010W58A09 | (Make-up WTR) Piping Work BL#1(upto pump Discharge header) | 2008-06-19 | 2008-07-04
Activity | 0CF3010W58A10 | (Make-up WTR) Piping Work BL#2(upto pump Discharge header) | 2008-06-19 | 2008-07-04
Activity | 0CF3010W58A11 | (Make-up WTR) Piping Work BL#3(upto pump Discharge header) | 2008-06-19 | 2008-07-04
Activity | 0CF3010W62A12 | (Make-up WTR Tank) Water filling for Early Power (Purchase demi. WTR) | 2008-08-05 | 2008-08-07
5 | Make-up Water Pump |  | 2007-05-01 | 2008-08-11
Activity | 0EF3010W42A03 | (Make-up WTR Pump) MPS Issue |  | 2007-05-01
Activity | 0PF3010W42A04P | (Make-up WTR Pump) P.O & Procurement | 2007-08-02 | 2008-04-02
Activity | 0EF3010W16A01.0 | (Make-up WTR Pump) FDN Design | 2007-08-02 | 2007-12-11
Activity | 0EF3010W00A12 | (Make-up WTR Pump Shelter) GA & Load Data to Civil Design | 2007-09-03
Activity | 0EF3010W16A13 | (Make-up WTR Pump Shelter) FDN Design | 2007-09-03 | 2007-11-30
Activity | 0EF3010W32A15 | (Make-up WTR Pump Shelter) Structure Design | 2007-09-03 | 2008-01-01
Activity | 0CF3010W16A14 | (Make-up WTR Pump Shelter) FDN Work | 2007-12-01 | 2008-01-31
Activity | 0CF3010W16A02.0 | (Make-up WTR Pump) FDN Work | 2007-12-12 | 2008-01-26
Activity | 0CF3010W32A16 | (Make-up WTR Pump Shelter) Structure Work | 2008-02-01 | 2008-05-03
Activity | 0PF3010W42A05.0T | (Make-up WTR Pump) Transportation | 2008-04-03 | 2008-05-17
Activity | 0CF3010W24A17 | (Make-up WTR Pump Shelter) Shelter Finish | 2008-05-04 | 2008-06-25
Activity | 0CF3010W42A07.0 | (Make-up WTR Pump) Installation for Block #2 | 2008-05-19 | 2008-06-18
Activity | 0CF3010W42A08.0 | (Make-up WTR Pump) Installation for Block #3 | 2008-05-19 | 2008-06-18
Activity | 0CF3010W42A06 | (Make-up WTR Pump) Installation for Block #1 | 2008-05-19 | 2008-06-18
Activity | 0SF3010W62A09 | (Make-up WTR Pump) Loop check & Motor Solo run Test | 2008-07-19 | 2008-07-28
Activity | 0SF3010W62A10 | (Make-up WTR Pump) Function Test | 2008-07-29 | 2008-08-02
Activity | 0SF3010W62A11.0 | (Make-up WTR Pump) Operation Test | 2008-08-08 | 2008-08-11
4 | Water Treatment System |  | 2007-03-15 | 2009-02-26
Activity | 0EF3010W00A03 | (WTS) P&ID & System Design | 2007-03-15 | 2007-11-21
Activity | 0EF3010W42A04 | (WTS) MPS Issue |  | 2007-05-30
Activity | 0PF3010W42A05P | (WTS) P.O & Procurement | 2007-08-31 | 2008-09-01
Activity | 0EF3010W16A01 | (WTS) FDN Design | 2007-08-31 | 2008-01-09
Activity | 0CF3010W16A02 | (WTS) FDN Work | 2008-01-10 | 2008-04-05
Activity | 0PF3010W42A06T | (WTS) Transportation | 2008-09-02 | 2008-10-16
Activity | 0CF3010W58A08 | (WTS) Piping Work | 2008-10-17 | 2008-12-16
Activity | 0CF3010W74A09 | (WTS) Installation & Test - Elec. | 2008-10-17 | 2009-01-01
Activity | 0CF3010W90A10 | (WTS) Installation & Test - I&C | 2008-10-17 | 2009-01-01
Activity | 0CF3010W42A07 | (WTS) Installation | 2008-10-17 | 2008-12-01
Activity | 0SF3010W62A11 | (WTS) Loop chek | 2009-01-02 | 2009-01-15
Activity | 0SF3010W62A12 | (WTS) Function Test | 2009-02-01 | 2009-02-14
Activity | 0SF3010W62A13 | (WTS) Load Test(incl. Tank filling) | 2009-02-15 | 2009-02-24
Activity | 0SF3010W62A14 | (WTS) System Operation | 2009-02-25 | 2009-02-26
5 | Demi. Water Plant Building |  | 2007-08-31 | 2008-09-18
Activity | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | 2007-08-31
Activity | 0EF5534W16A02 | (DWP BLDG) FDN Design | 2007-08-31 | 2008-01-01
Activity | 0EF5534W32A04 | (DWP BLDG) Structure Design | 2007-08-31 | 2008-01-01
Activity | 0CF5534W16A03 | (DWP BLDG) FDN Work | 2008-01-02 | 2008-02-28
Activity | 0CF5534W32A05 | (DWP BLDG) Station Structure Work | 2008-02-29 | 2008-06-30
Activity | 0CF5534W74A08 | (DWP BLDG) Installation & Test - Elec | 2008-05-21 | 2008-08-05
Activity | 0CF5534W90A09 | (DWP BLDG) Installation & Test - I&C | 2008-05-21 | 2008-08-05
Activity | 0CF5534W24A10 | (DWP BLDG) Building Finish | 2008-07-01 | 2008-09-18
Activity | 0CF5534W38A06 | (DWP BLDG) Installation & Test - Fire Fighting Sys. | 2008-07-01 | 2008-08-27
Activity | 0CF5534W36A07 | (DWP BLDG) Installation & Test - HVAC | 2008-07-01 | 2008-09-15
5 | Demi. Water Plant Chemical Storage Tank |  | 2007-08-31 | 2008-10-13
Activity | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | 2007-08-31
Activity | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | 2007-08-31 | 2007-12-27
Activity | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | 2007-10-02 | 2008-01-24
Activity | 0CF3010W16A03 | (DWP Chemical Storage Tank Shelter) FDN Work | 2008-01-25 | 2008-03-22
Activity | 0CF3010W32A05 | (DWP Chemical Storage Tank Shelter) Structure Work | 2008-03-24 | 2008-06-24
Activity | 0CF3010W74A06 | (DWP Chemical Storage Tank Shelter) Installation & Test - Elec | 2008-06-25 | 2008-08-21
Activity | 0CF3010W90A07 | (DWP Chemical Storage Tank Shelter) Installation & Test - I&C | 2008-06-25 | 2008-08-21
Activity | 0CF3010W24A08 | (DWP Chemical Storage Tank Shelter) Shelter Finish | 2008-08-22 | 2008-10-13
4 | Service Water System |  | 2007-03-15 | 2009-01-11
Activity | 0EF3035W00A01.0 | (SWS) P&ID & System Design | 2007-03-15 | 2007-11-21
Activity | 0EF3035W00A02.0 | (SWS) Service Water Supply pump Key data | 2007-04-27 | 2007-05-31
Activity | 0EF3035W42A05.0 | (SWS) MPS Issue |  | 2007-05-31
Activity | 0PF3035W42A06.0P | (SWS) P.O & Procurement | 2007-08-31 | 2008-09-01
Activity | 0EF3035W16A03.0 | (SWS) FDN Design | 2007-11-01 | 2008-03-04
Activity | 0CF3035W16A04.0 | (SWS) FDN Work | 2008-03-05 | 2008-06-05
Activity | 0PF3035W42A07.0T | (SWS) Transportation | 2008-09-02 | 2008-10-16
Activity | 0CF3035W42A08.0 | (SWS) Installation (upto pump Discharge header) | 2008-10-17 | 2008-12-16
Activity | 0CF3035W74A09.0 | (SWS) Installation & Test - Elec. | 2008-12-06 | 2009-01-07
Activity | 0CF3035W90A10.0 | (SWS) Installation & Test - I&C | 2008-12-06 | 2009-01-07
Activity | 0SF3035W62A11.0 | (SWS) Loop chek | 2008-12-17 | 2008-12-18
Activity | 0SF3035W62A12.0 | (SWS) Function Test | 2009-01-08 | 2009-01-09
Activity | 0SF3035W62A13.0 | (SWS) Load Test | 2009-01-10 | 2009-01-11
4 | Waste Water Treatment System |  | 2007-04-02 | 2009-03-20
Activity | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | 2007-04-02 | 2007-12-07
Activity | 0EF4035W42A04.1 | (WWTS) MPS Issue |  | 2007-05-31
Activity | 0EF5535W00A15.1 | (WWT Shelter) GA & Load Data to Civil Design | 2007-09-03
Activity | 0EF5535W16A16.1 | (WWT Shelter) FDN Design | 2007-09-03 | 2007-11-30
Activity | 0EF5535W32A18.1 | (WWT Shelter) Structure Design | 2007-09-03 | 2008-01-01
Activity | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | 2007-09-03 | 2008-09-01
Activity | 0EF4035W16A02.1 | (WWTS) Civil Design(incl. FDN) | 2007-09-03 | 2008-02-01
Activity | 0CF5535W16A17.1 | (WWT Shelter) FDN Work | 2007-12-01 | 2008-01-31
Activity | 0CF5535W32A19.1 | (WWT Shelter) Structure Work | 2008-02-01 | 2008-05-29
Activity | 0CF4035W16A03.1 | (WWTS) Civil Work(incl. FDN) | 2008-02-02 | 2008-07-02
Activity | 0PF4035W42A06.1T | (WWTS) Transportation | 2008-09-02 | 2008-10-16
Activity | 0CF4035W58A08.1 | (WWTS) Piping Work for Chemical & Oil | 2008-10-17 | 2009-02-17
Activity | 0CF4035W42A07.1 | (WWTS) Installation(PKG Type, not central) | 2008-10-17 | 2009-01-16
Activity | 0CF5535W24A20.1 | (WWT Shelter) Shelter Finish | 2008-11-16 | 2009-01-16
Activity | 0CF4035W74A09.1 | (WWTS) Installation & Test - Elec. | 2008-11-24 | 2009-02-17
Activity | 0CF4035W90A10.1 | (WWTS) Installation & Test - I&C | 2008-11-24 | 2009-02-17
Activity | 0SF4035W62A11.1 | (WWTS) Loop chek | 2009-02-18 | 2009-02-27
Activity | 0SF4035W62A12.1 | (WWTS) Function Test | 2009-02-28 | 2009-03-14
Activity | 0SF4035W62A13.1 | (WWTS) Load(running) Test | 2009-03-15 | 2009-03-18
Activity | 0SF4035W62A14.1 | (WWTS) System Operation | 2009-03-19 | 2009-03-20
5 | Waste Water Treatment LEB |  | 2007-11-02 | 2009-01-02
Activity | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | 2007-11-02
Activity | 0EF4035W16A02.2 | (WWT LEB) FDN Design | 2007-11-02 | 2008-02-01
Activity | 0EF4035W32A04 | (WWT LEB) Structure Design | 2007-11-02 | 2008-02-01
Activity | 0CF4035W16A03.2 | (WWT LEB) FDN Work | 2008-02-02 | 2008-06-02
Activity | 0CF4035W32A05 | (WWT LEB) Structure Work | 2008-06-03 | 2008-10-02
Activity | 0CF4035W38A06 | (WWT LEB) Installation & Test - Fire Fighting Sys. | 2008-10-03 | 2008-11-29
Activity | 0CF4035W36A07 | (WWT LEB) Installation & Test - HVAC | 2008-10-03 | 2008-11-29
Activity | 0CF4035W74A08 | (WWT LEB) Installation & Test - Elec | 2008-10-03 | 2008-11-29
Activity | 0CF4035W24A10 | (WWT LEB) Building Finish | 2008-10-03 | 2009-01-02
Activity | 0CF4035W90A09 | (WWT LEB) Installation & Test - I&C | 2008-10-03 | 2008-11-29
4 | Sewage Treatment System |  | 2007-04-02 | 2009-02-15
Activity | 0EF4035W00A01 | (STS) P&ID & System Design | 2007-04-02 | 2007-12-07
Activity | 0EF4035W42A04 | (STP) MPS Issue |  | 2007-05-31
Activity | 0PF4035W42A05P | (STP) P.O & Procurement | 2007-09-03 | 2008-09-01
Activity | 0EF5535W00A15 | (STS BLDG) GA & Load Data to Civil Design | 2007-11-02
Activity | 0EF5535W32A17 | (STS BLDG) Building Design | 2007-11-02 | 2008-01-31
Activity | 0EF4035W16A02 | (STP) FDN Design | 2007-11-02 | 2008-01-31
Activity | 0CF5535W16A16 | (STS BLDG) FDN Work | 2008-02-01 | 2008-05-03
Activity | 0CF4035W16A03 | (STP) FDN Work | 2008-02-01 | 2008-05-03
Activity | 0CF5535W32A18 | (STS BLDG) Structure Work | 2008-05-05 | 2008-08-05
Activity | 0CF5535W36A20 | (STS BLDG) Installation & Test - HVAC | 2008-08-06 | 2008-10-02
Activity | 0CF5535W74A21 | (STS BLDG) Installation & Test - Elec | 2008-08-06 | 2008-10-02
Activity | 0CF5535W90A22 | (STS BLDG) Installation & Test - I&C | 2008-08-06 | 2008-10-02
Activity | 0CF5535W38A19 | (STS BLDG) Installation & Test - Fire Fighting Sys. | 2008-08-16 | 2008-10-13
Activity | 0PF4035W42A06T | (STP) Transportation | 2008-09-02 | 2008-10-16
Activity | 0CF4035W42A07 | (STP) Installation | 2008-10-17 | 2008-12-31
Activity | 0CF4035W58A08 | (STS) Piping Work | 2008-10-17 | 2009-01-16
Activity | 0CF4035W74A09 | (STS) Installation & Test - Elec. | 2008-10-17 | 2009-01-26
Activity | 0CF4035W90A10 | (STS) Installation & Test - I&C | 2008-10-17 | 2009-01-26
Activity | 0CF4035W38A11 | (STS) Installation & Test - Fire Fighting Sys. | 2008-11-01 | 2008-12-27
Activity | 0SF4035W62A12 | (STS) Loop chek | 2009-01-27 | 2009-02-05
Activity | 0SF4035W62A13 | (STS) System Function Test | 2009-02-06 | 2009-02-10
Activity | 0SF4035W62A14 | (STS) System Operation | 2009-02-11 | 2009-02-15
4 | Potable Water System |  | 2007-03-15 | 2009-01-24
Activity | 0EF3035W00A01 | (PWS) P&ID & System Design | 2007-03-15 | 2007-10-29
Activity | 0EF3035W00A02.1 | (PWS) Potable Water Supply System Key data | 2007-04-27 | 2007-05-31
Activity | 0EF3035W42A05 | (PWP) MPS Issue |  | 2007-05-31
Activity | 0PF3035W42A06P | (PWP) P.O & Procurement | 2007-09-03 | 2008-09-01
Activity | 0EF3035W16A14 | (PWT) FDN Design | 2007-11-02 | 2008-03-04
Activity | 0EF3035W16A03 | (PWP) FDN Design | 2007-12-04 | 2008-03-04
Activity | 0CF3035W16A04 | (PWP) FDN Work | 2008-03-05 | 2008-05-05
Activity | 0CF3035W16A15 | (PWT) FDN Work | 2008-03-05 | 2008-05-05
Activity | 0CF3035W68A16 | (PWT) Installation(incl. painting & Test) | 2008-05-06 | 2008-11-03
Activity | 0PF3035W42A07T | (PWP) Transportation | 2008-09-02 | 2008-10-16
Activity | 0CF3035W42A08 | (PWP) Installation (upto pump Discharge header) | 2008-10-17 | 2008-11-17
Activity | 0CF3035W74A09 | (PWS) Installation & Test - Elec. | 2008-11-15 | 2008-12-12
Activity | 0CF3035W90A10 | (PWS) Installation & Test - I&C | 2008-11-15 | 2008-12-12
Activity | 0SF3035W62A11.1 | (PWS) Loop chek | 2008-12-13 | 2008-12-22
Activity | 0SF3035W62A12.1 | (PWS) System Function Test | 2008-12-23 | 2008-12-27
Activity | 0SF3035W62A13.1 | (PWS) Load Test | 2009-01-20 | 2009-01-24
4 | Circulating Water System |  | 2007-03-15 | 2009-02-23
Activity | 0EF3025W00A01 | (CWS) P&ID & System Design | 2007-03-15 | 2007-10-29
Activity | 0EF3025W00A02 | (CWS) CWP Key data | 2007-04-13 | 2007-05-15
Activity | 0EF3025W42A03 | (CWP) MPS Issue |  | 2007-05-15
Activity | 0EF3025W22A07 | (CW Piping) MPS Issue |  | 2007-08-01
Activity | 0PF3025W42A04P | (CWP) P.O & Procurement | 2007-08-15 | 2008-08-15
Activity | 0PF3025W22A08P | (CW Piping) P.O & Procurement | 2007-10-01 | 2008-03-31
Activity | 0PF3025W22A09T | (CW Piping) Transportation | 2008-04-01 | 2008-05-15
Activity | 0CF3025W22A10 | (CW Piping) Piping Work | 2008-05-31 | 2008-11-28
Activity | 0PF3025W42A05T | (CWP) Transportation | 2008-08-16 | 2008-10-01
Activity | 0CF3025W38A11 | (CWS) Installation & Test - Fire Fighting Sys. | 2008-08-16 | 2008-10-13
Activity | 0CF3025W42A06 | (CWP) Installation | 2008-10-02 | 2008-11-28
Activity | 0CF3025W74A12 | (CWS) Installation & Test - Elec. | 2008-10-20 | 2008-12-26
Activity | 0CF3025W90A13 | (CWS) Installation & Test - I&C | 2008-10-20 | 2008-12-26
Activity | 0CF3025W62A14 | (CW Piping) Hydro Test | 2008-11-29 | 2008-12-26
Activity | 0SF3025W62A15 | (CWS) Loop chek & Motor Solo Test | 2008-12-27 | 2009-01-10
Activity | 0SF3025W62A16 | (CWS) Function Test | 2009-01-28 | 2009-02-06
Activity | 0SF3025W62A17 | (CWS) CTCS Function Test | 2009-02-07 | 2009-02-11
Activity | 0SF3025W62A18 | (CWS) Pump Operation | 2009-02-21 | 2009-02-23
4 | Chlorination System |  | 2007-03-30 | 2009-02-20
Activity | 0EF3045W00A01.0 | (Chlorination System) P&ID & System Design | 2007-03-30 | 2007-11-13
Activity | 0EF3045W42A04 | (Chlorination Plant) MPS Issue |  | 2007-05-31
Activity | 0EF3045W58A08 | (Chlorination System Piping) MPS Issue |  | 2007-07-31
Activity | 0PF3045W42A05P | (Chlorination Plant) P.O & Procurement | 2007-08-31 | 2008-09-01
Activity | 0EF3045W16A02 | (Chlorination Plant) FDN Design | 2007-08-31 | 2007-11-30
Activity | 0PF3045W58A09P | (Chlorination System Piping) Raw Material Procurement | 2007-11-01 | 2008-01-01
Activity | 0CF3045W16A03 | (Chlorination Plant) FDN Work | 2007-12-01 | 2008-03-03
Activity | 0PF3045W58A10P | (Chlorination System Piping) Manufacturing | 2008-01-02 | 2008-07-01
Activity | 0PF3045W58A11T | (Chlorination System Piping) Transportation | 2008-07-02 | 2008-08-15
Activity | 0PF3045W42A06T | (Chlorination Plant) Transportation | 2008-09-02 | 2008-10-16
Activity | 0CF3045W42A07 | (Chlorination Plant) Installation | 2008-10-17 | 2009-01-01
Activity | 0CF3045W58A12 | (Chlorination System Piping) Piping Work | 2008-10-17 | 2009-01-10
Activity | 0CF3045W74A14 | (Chlorination System) Installation & Test - Elec. | 2008-10-17 | 2009-01-10
Activity | 0CF3045W90A15 | (Chlorination System) Installation & Test - I&C | 2008-10-17 | 2009-01-10
Activity | 0CF3045W62A13 | (Chlorination System Piping) Hydro Test | 2009-01-12 | 2009-01-26
Activity | 0SF3045W62A16 | (Chlorination System) Loop check | 2009-01-27 | 2009-02-10
Activity | 0SF3045W62A17 | (Chlorination System) System Function Test | 2009-02-11 | 2009-02-15
Activity | 0SF3045W62A18 | (Chlorination System) System Operation | 2009-02-16 | 2009-02-20
5 | Chlorination Building |  | 2007-08-31 | 2008-12-27
Activity | 0EF3045W00A01 | (Chlorination BLDG) GA & Load Data to Civil Design | 2007-08-31
Activity | 0EF3045W32A03 | (Chlorination BLDG) Structure Design | 2007-08-31 | 2007-11-30
Activity | 0CF3045W16A02 | (Chlorination BLDG) FDN Work | 2007-12-01 | 2008-03-03
Activity | 0CF3045W32A04 | (Chlorination BLDG) Structure Work | 2008-03-04 | 2008-07-03
Activity | 0CF3045W74A07 | (Chlorination BLDG) Installation & Test - Elec | 2008-07-04 | 2008-08-30
Activity | 0CF3045W90A08 | (Chlorination BLDG) Installation & Test - I&C | 2008-07-04 | 2008-08-30
Activity | 0CF3045W36A06 | (Chlorination BLDG) Installation & Test - HVAC | 2008-07-31 | 2008-09-26
Activity | 0CF3045W38A05 | (Chlorination BLDG) Installation & Test - Fire Fighting Sys. | 2008-11-01 | 2008-12-27
4 | Intake Pump Structure |  | 2007-03-15 | 2009-01-27
Activity | 0EF3025W00A01.0 | (Intake Screening System) P&ID & System Design | 2007-03-15 | 2007-10-29
Activity | 0EF3025W42A02 | (Intake Screening Equipment) MPS Issue |  | 2007-04-02
Activity | 0EF3025W00A10 | (Intake Pump Station) GA & Load Data to Civil Design | 2007-04-03
Activity | 0EF3025W16A12 | (Intake Pump Station) FDN Design | 2007-06-04 | 2007-10-03
Activity | 0EF3025W42A17 | (Gantry Crane) MPS Issue |  | 2007-06-29
Activity | 0PF3025W42A03P | (Intake Screening Equipment) P.O & Procurement | 2007-07-03 | 2008-08-18
Activity | 0EF3025W16A11 | (Intake Pump Station) Structure Design | 2007-08-15 | 2007-11-12
Activity | 0PF3025W42A18P | (Gantry Crane) P.O & Procurement | 2007-09-28 | 2008-06-14
Activity | 0EF3025W12A13 | (Intake Pump Station) Excavation | 2007-10-04 | 2008-01-04
Activity | 0CF3025W16A14 | (Intake Pump Station) FDN Work | 2008-01-05 | 2008-03-06
Activity | 0CF3025W16A15 | (Intake Pump Station) Structure Work(Wall & Top Slab) | 2008-03-07 | 2008-07-12
Activity | 0PF3025W42A19T | (Gantry Crane) Transportation | 2008-06-15 | 2008-07-29
Activity | 0CF3025W12A16 | (Intake Pump Station) Backfilling | 2008-07-14 | 2008-09-12
Activity | 0CF3025W42A20 | (Gantry Crane) Equipment Installation | 2008-07-30 | 2008-09-27
Activity | 0PF3025W42A04.0T | (Intake Screening Equipment) Transportation | 2008-08-19 | 2008-10-02
Activity | 0CF3025W42A05 | (Intake System) Equipment Installation(Stop gate, screening sys.) | 2008-10-03 | 2009-01-03
Activity | 0CF3025W58A06 | (Intake System) Piping Work | 2008-10-24 | 2009-01-06
Activity | 0CF3025W74A07 | (Intake System) Installation & Test - Elec. | 2008-10-24 | 2009-01-17
Activity | 0CF3025W90A08 | (Intake System) Installation & Test - I&C | 2008-10-24 | 2009-01-17
Activity | 0SF3025W62A09 | (Intake System) Loop chek & Motor Solo Test | 2009-01-18 | 2009-01-27
4 | Compressed Air System |  | 2007-03-30 | 2008-12-03
Activity | 0EF3510W00A02 | (COMP Air System) Compressed Air Sys. Key data | 2007-03-30 | 2007-04-30
Activity | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | 2007-04-30 | 2007-12-12
Activity | 0EF3510W42A05 | (COMP Air PKG) MPS Issue |  | 2007-04-30
Activity | 0EF3510W00A17 | (COMP Air BLDG) GA & Load Data to Civil Design | 2007-08-01
Activity | 0EF3510W16A18 | (COMP Air BLDG) FDN Design | 2007-08-01 | 2007-10-31
Activity | 0EF3510W32A20 | (COMP Air BLDG) Structure Design | 2007-08-01 | 2007-10-31
Activity | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | 2007-08-01 | 2008-04-30
Activity | 0EF3510W16A03 | (COMP Air PKG) FDN Design | 2007-08-01 | 2007-12-03
Activity | 0CF3510W16A19 | (COMP Air BLDG) FDN Work | 2007-11-01 | 2007-12-31
Activity | 0CF3510W16A04 | (COMP Air PKG) FDN Work | 2007-12-04 | 2008-02-01
Activity | 0CF3510W32A21 | (COMP Air BLDG) Structure Work | 2008-01-01 | 2008-04-01
Activity | 0CF3510W36A23 | (COMP Air BLDG) Installation & Test - HVAC | 2008-04-02 | 2008-05-19
Activity | 0PF3510W42A07T | (COMP Air PKG) Transportation | 2008-05-01 | 2008-06-14
Activity | 0CF3510W24A24 | (COMP Air BLDG) Building Finish | 2008-05-21 | 2008-07-17
Activity | 0CF3510W38A22 | (COMP Air BLDG) Installation & Test - Fire Fighting Sys. | 2008-05-31 | 2008-07-17
Activity | 0CF3510W42A08 | (COMP Air PKG) Installation_Compressor, Dryer | 2008-06-16 | 2008-08-16
Activity | 0CF3510W58A09 | (COMP Air System) IA Piping Work(Upto IA header) | 2008-08-01 | 2008-09-01
Activity | 0CF3510W58A11 | (COMP Air System) SA Piping Work(Upto SA Header) | 2008-08-01 | 2008-09-01
Activity | 0CF3510W74A12 | (COMP Air System) Installation & Test - Elec. | 2008-08-13 | 2008-09-12
Activity | 0CF3510W90A13 | (COMP Air System) Installation & Test - I&C | 2008-08-13 | 2008-09-12
Activity | 0CF3510W58A10 | (COMP Air System) Piping Work for CP(incl. Air Blowing) | 2008-09-02 | 2008-12-03
Activity | 0SF3510W62A14 | (COMP Air System) Loop chek & Motor Solo Test | 2008-10-02 | 2008-10-15
Activity | 0SF3510W62A15 | (COMP Air System) System Function Test | 2008-10-16 | 2008-10-20
Activity | 0SF3510W62A16 | (COMP Air System) Load Test | 2008-10-21 | 2008-10-22
5 | Receiver Tank |  | 2007-08-01 | 2008-08-16
Activity | 0EF3510W00A01 | (COMP Air Receiver TK Shelter) GA & Load Data to Civil Design | 2007-08-01
Activity | 0EF3510W16A02 | (COMP Air Receiver TK Shelter) FDN Design | 2007-08-01 | 2007-11-12
Activity | 0EF3510W32A04 | (COMP Air Receiver TK Shelter) Structure Design | 2007-08-01 | 2007-09-13
Activity | 0CF3510W16A03 | (COMP Air Receiver TK Shelter) FDN Work | 2007-11-13 | 2008-01-09
Activity | 0CF3510W32A05 | (COMP Air Receiver TK Shelter) Structure Work | 2008-01-10 | 2008-03-28
Activity | 0CF3510W42A07 | (COMP Air Receiver TK) Installation & MECH Test | 2008-06-16 | 2008-08-16
Activity | 0CF3510W24A06 | (COMP Air Receiver TK Shelter) Shleter Finish | 2008-06-17 | 2008-08-16
3 | HVAC & Fire Fighting System |  | 2007-03-30 | 2008-10-31
4 | HVAC System |  | 2007-03-30 | 2008-07-30
Activity | 0EF5000W00A01 | (HVAC System) P&ID & System Design | 2007-03-30 | 2007-11-01
Activity | 0EF5000W36A02 | (HVAC Equipment) MPS Issue |  | 2007-05-15
Activity | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | 2007-08-15 | 2008-06-11
Activity | 0PF5000W36A04T | (HVAC Equipment) Transportation | 2008-03-29 | 2008-07-30
Activity | 0PF5000W36A05T | (HVAC Equipment) 1st Delivery on site_Transportation |  | 2008-05-14
4 | Fire Fighting System |  | 2007-03-30 | 2008-10-31
Activity | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | 2007-03-30 | 2007-11-01
Activity | 0EF4500W38A08 | (Fire Fighting System) MPS Issue |  | 2007-05-01
Activity | 0EF4500W38A02 | (Fire Fighting Equip) MPS Issue |  | 2007-05-01
Activity | 0PF4500W38A09P | (Fire Fighting System) P.O & Procurement_piping | 2007-08-01 | 2007-12-31
Activity | 0PF4500W38A03P | (Fire Fighting Equip) P.O & Procurement | 2007-08-01 | 2008-06-18
Activity | 0PF4500W38A10T | (Fire Fighting System) Transportation | 2008-01-01 | 2008-02-14
Activity | 0CF4500W38A11 | (Fire Fighting System) Piping Work(Ring Main) | 2008-02-15 | 2008-05-17
Activity | 0PF4500W38A04T | (Fire Fighting Equip) Transportation | 2008-04-16 | 2008-10-31
Activity | 0PF4500W38A05T | (Fire Fighting Equip) 1st Delivery on site_Transportation |  | 2008-05-30
Activity | 0CF4500W62A12 | (Fire Fighting System) Hydro Test | 2008-07-23 | 2008-08-07
Activity | 0PF4500W38A06T | (Fire Fighting Equip) 2nd Delivery on site_Transportation |  | 2008-08-15
Activity | 0PF4500W38A07T | (Fire Fighting Equip) 3rd Delivery on site_Transportation |  | 2008-10-31
5 | Fire Fighting Pump & Shelter |  | 2007-05-01 | 2008-07-22
Activity | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | 2007-05-01
Activity | 0EF4500W32A04 | (Fire WTR Pump Shelter) Structure Design | 2007-05-01 | 2007-08-27
Activity | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | 2007-05-31 | 2007-08-30
Activity | 0CF4500W16A03 | (Fire WTR Pump Shelter) FDN Work | 2007-08-31 | 2007-10-27
Activity | 0CF4500W32A05 | (Fire WTR Pump Shelter) Structure Work | 2007-10-29 | 2008-02-27
Activity | 0CF4500W74A07 | (Fire WTR Pump Shelter) Installation & Test - Elec | 2008-05-06 | 2008-07-02
Activity | 0CF4500W90A08 | (Fire WTR Pump Shelter) Installation & Test - I&C | 2008-05-06 | 2008-07-02
Activity | 0CF4500W24A11 | (Fire WTR Pump Shelter) Building Finish | 2008-05-20 | 2008-07-16
Activity | 0CF4500W38A09 | (Fire WTR Pump Shelter) Installation & Test - Fire Fighting Sys. | 2008-05-31 | 2008-07-16
Activity | 0CF4500W36A10 | (Fire WTR Pump Shelter) Installation & Test - HVAC | 2008-05-31 | 2008-07-16
Activity | 0CF4500W38A06.0 | (Fire WTR Pump Shelter) Installation F/F pump | 2008-05-31 | 2008-07-02
Activity | 0SF4500W62A12 | (Fire WTR Pump) Loop chek | 2008-07-17 | 2008-07-18
Activity | 0SF4500W62A13 | (Fire WTR Pump) System Function Test | 2008-07-19 | 2008-07-20
Activity | 0SF4500W62A14 | (Fire WTR Pump) Load(running) Test | 2008-07-21 | 2008-07-22
5 | Fire Fighting Building |  | 2007-08-07 | 2008-07-11
Activity | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | 2007-08-07 | 2007-11-06
Activity | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | 2007-08-07 | 2007-12-03
Activity | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | 2007-08-07
Activity | 0CF4500W16A03.1 | (Fire Fighting BLDG) FDN Work | 2007-11-07 | 2008-01-03
Activity | 0CF4500W32A05.1 | (Fire Fighting BLDG) Structure Work | 2008-01-04 | 2008-03-01
Activity | 0CF4500W74A08 | (Fire Fighting BLDG) Installation & Test - Elec | 2008-02-02 | 2008-03-31
Activity | 0CF4500W90A09 | (Fire Fighting BLDG) Installation & Test - I&C | 2008-02-02 | 2008-03-31
Activity | 0CF4500W36A07 | (Fire Fighting BLDG) Installation & Test - HVAC | 2008-05-15 | 2008-07-11
Activity | 0CF4500W24A10 | (Fire Fighting BLDG) Building Finish | 2008-05-21 | 2008-07-11
Activity | 0CF4500W38A06 | (Fire Fighting BLDG) Installation - Fire Fighting Sys. | 2008-05-31 | 2008-07-11
3 | BOP Piping for Plant Common |  | 2007-03-01 | 2008-09-30
4 | System Engineering |  | 2007-03-01 | 2008-09-30
Activity | 0EF6020W00A02 | (BOP Piping) Pipe Material Specification | 2007-03-01 | 2008-01-28
Activity | 0EF6020W00A03 | (BOP Piping) Piping Insulation Specification | 2007-04-02 | 2008-01-28
Activity | 0EF6020W00A01 | (BOP Piping) Pipe Arrangement | 2007-04-30 | 2008-09-30
Activity | 0EF6020W00A05 | (BOP Piping) Valve List | 2007-04-30 | 2008-01-03
Activity | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | 2007-05-18 | 2008-01-31
4 | Piping Material Procurement |  | 2007-04-30 | 2008-07-16
Activity | 0EF6020W58A10 | (Piping Insulation) MPS Issue |  | 2007-07-30
Activity | 0EF6020W58A01 | (Piping) MPS Issue |  | 2007-07-30
Activity | 0EF6020W46A07 | (Hanger & Support & Fitting) MPS Issue |  | 2007-07-30
Activity | 0PF6020W58A02P | (Piping) P.O & Procurement | 2007-09-14 | 2008-06-11
Activity | 0PF6020W46A08P | (Hanger & Support & Fitting) P.O & Procurement | 2007-09-14 | 2008-02-29
Activity | 0PF6020W58A11P | (Piping Insulation) P.O & Procurement | 2007-10-01 | 2008-04-30
Activity | 0PF6020W58A03T | (Piping) Transportation | 2008-01-16 | 2008-07-16
Activity | 0PF6020W46A09T | (Hanger & Support & Fitting) Transportation for Early Power | 2008-03-01 | 2008-04-15
Activity | 0PF6020W58A04T | (Piping) 1st Delivery on site_Transportation |  | 2008-03-01
Activity | 0PF6020W58A12T | (Piping Insulation) Transportation for Early Power | 2008-05-01 | 2008-06-14
Activity | 0PF6020W58A05T | (Piping) 2nd Delivery on site_Transportation |  | 2008-05-14
Activity | 0PF6020W58A06T | (Piping) 3rd Delivery on site_Transportation |  | 2008-07-16
5 | Manual Valve |  | 2007-07-30 | 2008-04-15
Activity | 0EF6050W86A01 | (Manual Valve) MPS Issue |  | 2007-07-30
Activity | 0PF6050W86A02P | (Manual Valve) P.O & Procurement | 2007-09-24 | 2008-02-29
Activity | 0PF6050W86A03.0T | (Manual Valve) Transportation for Early Power | 2008-03-01 | 2008-04-15
5 | Motor Operation Valve |  | 2007-04-30 | 2008-06-14
Activity | 0EF6050W00A01 | (MOV) MOV Key Data | 2007-04-30 | 2007-07-13
Activity | 0EF6050W86A02 | (MOV) MPS Issue |  | 2007-07-13
Activity | 0PF6050W86A03P | (MOV) P.O & Procurement | 2007-09-14 | 2008-04-30
Activity | 0PF6050W86A04T | (MOV) Transportation for Early Power | 2008-05-01 | 2008-06-14
5 | Safety Valve |  | 2007-04-30 | 2008-07-08
Activity | 0EF6050W00A01.1 | (Safety Valve) Key Data | 2007-04-30 | 2007-07-13
Activity | 0EF6050W86A02.1 | (Safety Valve) MPS Issue |  | 2007-07-13
Activity | 0PF6050W86A03.1P | (Safety Valve) P.O & Procurement | 2007-09-14 | 2008-05-23
Activity | 0PF6050W86A04.1T | (Safety Valve) Transportation for Early Power | 2008-05-24 | 2008-07-08
3 | Electrical System |  | 2007-03-01 | 2008-12-18
4 | Extra High Voltage Substation (GIS/AIS) |  | 2007-03-01 | 2008-12-18
Activity | 0PF5544W70A02P | (GIS Equip) P.O & Procurement | 2007-03-01 | 2008-01-29
Activity | 0EF5544W70A01 | (GIS Equip) MPS Issue |  | 2007-03-01
Activity | 0EF5544W00A08 | (GIS BLDG) GA & Load Data to Civil Design | 2007-03-01
Activity | 0EF5544W16A09 | (GIS BLDG) FDN Design | 2007-03-01 | 2007-06-29
Activity | 0EF5544W32A11 | (GIS BLDG) Structure Design | 2007-03-01 | 2007-06-29
Activity | 0CF5544W16A10 | (GIS BLDG) FDN Work | 2007-06-30 | 2007-08-27
Activity | 0CF5544W32A12 | (GIS BLDG) Structure Work | 2007-08-28 | 2007-11-29
Activity | 0PF5544W70A03T | (GIS Equip) Transportation | 2008-01-30 | 2008-03-14
Activity | 0CF5544W70A04 | (GIS Equip) Installation for power receiving | 2008-04-02 | 2008-08-04
Activity | 0CF5544W74A15 | (GIS BLDG) Installation & Test - Elec | 2008-04-02 | 2008-08-13
Activity | 0CF5544W90A16 | (GIS BLDG) Installation & Test - I&C | 2008-04-02 | 2008-08-13
Activity | 0CF5544W38A13 | (GIS BLDG) Installation & Test - Fire Fighting Sys. | 2008-05-31 | 2008-07-17
Activity | 0CF5544W36A14 | (GIS BLDG) Installation & Test - HVAC | 2008-05-31 | 2008-07-17
Activity | 0CF5544W24A17 | (GIS BLDG) Building Finish | 2008-06-30 | 2008-08-13
Activity | 0SF5544W62A05 | (GIS Equip) Commissioning for power receiving | 2008-08-14 | 2008-08-28
Activity | 0CF5544W70A06 | (GIS Equip) Installation for overall plant | 2008-08-29 | 2008-11-28
Activity | 0SF5544W62A07 | (GIS Equip) Commissioning for overall plant | 2008-11-29 | 2008-12-18
4 | MV Switchgears With Auxiliaries |  | 2007-03-30 | 2008-07-20
Activity | 0EF6500W70A01.2 | (MV SWGR) MPS Issue |  | 2007-03-30
Activity | 0PF6500W70A02.2P | (MV SWGR) P.O & Procurement for Early power | 2007-07-03 | 2008-03-31
Activity | 0PF6500W70A03.2T | (MV SWGR) Transportation | 2008-04-01 | 2008-05-15
Activity | 0CF6500W70A04.2 | (MV SWGR) Installation for Early power | 2008-05-16 | 2008-06-30
Activity | 0SF6500W62A05.2 | (MV SWGR) Function Test | 2008-07-01 | 2008-07-20
4 | LV Switchgears & MCC With Auxiliaries |  | 2007-03-30 | 2008-07-01
Activity | 0EF6500W70A01.3 | (LV SWGR) MPS Issue |  | 2007-03-30
Activity | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | 2007-07-03 | 2008-03-31
Activity | 0PF6500W70A03.3T | (LV SWGR) Transportation | 2008-04-01 | 2008-05-15
Activity | 0CF6500W70A04.3 | (LV SWGR) Installation for Early power | 2008-05-16 | 2008-06-21
Activity | 0SF6500W62A05.3 | (LV SWGR) Function Test | 2008-06-22 | 2008-07-01
4 | DC & UPS System |  | 2007-05-01 | 2008-06-04
Activity | 0EF6500W70A01.4 | (DC & UPS) MPS Issue |  | 2007-05-01
Activity | 0PF6500W70A02.4P | (DC & UPS) P.O & Procurement | 2007-08-08 | 2008-03-06
Activity | 0PF6500W70A03.4T | (DC & UPS) Transportation | 2008-03-07 | 2008-04-21
Activity | 0CF6500W70A04.4 | (DC & UPS) Installation(incl. DB) | 2008-04-22 | 2008-05-20
Activity | 0SF6500W62A05.4 | (DC & UPS) Function Test | 2008-05-21 | 2008-06-04
4 | Batteries |  | 2007-06-15 | 2008-06-17
Activity | 0EF6500W70A01.5 | (Battery) MPS Issue |  | 2007-06-15
Activity | 0PF6500W70A02.5P | (Battery) P.O & Procurement | 2007-09-18 | 2008-04-18
Activity | 0PF6500W70A03.5T | (Battery) Transportation | 2008-04-19 | 2008-06-03
Activity | 0CF6500W70A04.5 | (Battery) Installation | 2008-06-04 | 2008-06-10
Activity | 0SF6500W62A05.5 | (Battery) System Test(Incl. Acid Filling & Initial charging) | 2008-06-11 | 2008-06-17
4 | Power & Electrical Control Cables |  | 2007-07-02 | 2008-07-15
Activity | 0EF6040W74A01.1 | (Electrical Cable) MPS Issue |  | 2007-07-02
Activity | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | 2007-09-19 | 2008-03-25
Activity | 0PF6040W74A03.1T | (Electrical Cable) Transportation | 2008-03-26 | 2008-05-09
Activity | 0CF6040W74A04.1 | (Electrical Cable) Cable Pulling for CCB-GTG LEB(Early Power) | 2008-05-10 | 2008-05-30
Activity | 0CF6040W74A05.1 | (Electrical Cable) Cable Pulling for CCB-GIS BLDG(Early Power) | 2008-05-10 | 2008-05-20
Activity | 0CF6040W74A06.1 | (Electrical Cable) Cable Pulling for GTG LEB-GIS BLDG(Early Power) | 2008-05-31 | 2008-07-15
4 | Electrical Protection Panel |  | 2007-05-31 | 2008-06-15
Activity | 0EF6500W70A01.6 | (Electrical Protection Panel) MPS Issue |  | 2007-05-31
Activity | 0PF6500W70A02.6P | (Electrical Protection Panel) P.O & Procurement | 2007-08-30 | 2008-03-10
Activity | 0PF6500W70A03.6T | (Electrical Protection Panel) Transportation | 2008-03-11 | 2008-04-24
Activity | 0CF6500W70A04.6 | (Electrical Protection Panel) Installation | 2008-04-25 | 2008-05-26
Activity | 0SF6500W62A05.6 | (Electrical Protection Panel) Function Test | 2008-05-27 | 2008-06-05
Activity | 0SF6500W62A06.6 | (Electrical Protection Panel) Secondary & Primary Test | 2008-06-06 | 2008-06-15
4 | Lighting System |  | 2007-05-30 | 2008-06-30
Activity | 0EF6040W70A01 | (Lighting Equip) MPS Issue |  | 2007-05-30
Activity | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | 2007-08-01 | 2008-02-27
Activity | 0PF6040W70A03T | (Lighting Equip) Transportation | 2008-02-28 | 2008-04-12
Activity | 0CF6040W70A04 | (Lighting Equip) Installation | 2008-04-14 | 2008-06-30
4 | Earthing & Lightning Materials |  | 2007-05-30 | 2008-08-01
Activity | 0EF6040W80A01 | (Earthing & Lightning Material) MPS Issue |  | 2007-05-30
Activity | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | 2007-08-17 | 2007-12-18
Activity | 0PF6040W80A03T | (Earthing & Lightning Material) Transportation | 2007-12-19 | 2008-01-28
Activity | 0CF6040W80A04 | (Earthing & Lightning Material) Installation | 2008-01-29 | 2008-08-01
4 | Raceway System |  | 2007-07-02 | 2008-05-30
Activity | 0EF6040W74A01 | (Raceway) MPS Issue |  | 2007-07-02
Activity | 0PF6040W74A02P | (Raceway) P.O & Procurement | 2007-09-03 | 2008-01-31
Activity | 0PF6040W74A03T | (Raceway) Transportation | 2008-02-01 | 2008-03-17
Activity | 0CF6040W74A04 | (Raceway) Installation for CCB-GTG LEB(Early Power) | 2008-03-18 | 2008-04-17
Activity | 0CF6040W74A05 | (Raceway) Installation for CCB-GIS BLDG(Early Power) | 2008-03-18 | 2008-04-17
Activity | 0CF6040W74A06 | (Raceway) Installation for GTG LEB-GIS BLDG(Early Power) | 2008-03-18 | 2008-05-30
4 | Power Metering System |  | 2007-05-01 | 2008-05-29
Activity | 0EF6500W70A01.7 | (Power Metering Equip) MPS Issue |  | 2007-05-01
Activity | 0PF6500W70A02.7P | (Power Metering Equip) P.O & Procurement | 2007-07-13 | 2008-02-12
Activity | 0PF6500W70A03.7T | (Power Metering Equip) Transportation | 2008-02-13 | 2008-03-28
Activity | 0CF6500W70A04.7 | (Power Metering Equip) Installation | 2008-03-29 | 2008-04-29
Activity | 0SF6500W62A05.7 | (Power Metering Equip) Function Test | 2008-04-30 | 2008-05-29
4 | Power Receiving |  | 2008-08-01 | 2008-09-15
Activity | 0SF6500W62A01 | (Power Receiving) Interface signal Test | 2008-08-01 | 2008-08-02
Activity | 0SF6500W62A02 | (Power Receiving) Interlock Test between power plant & LCC | 2008-08-03 | 2008-08-06
Activity | 0SF6500W62A03 | (Power Receiving) Overall Interlock & Intertrip Test | 2008-09-02 | 2008-09-04
Activity | 0SF6500W62A04 | (Power Receiving) Protection Secondary & Primary Test | 2008-09-05 | 2008-09-11
Activity | 0SF6500W62A05.1 | (Power Receiving) Back Charging of Transformer | 2008-09-12 | 2008-09-12
Activity | 0SF6500W62A06.1 | (Power Receiving) Permit power receiving from LCC | 2008-09-13 | 2008-09-15
3 | Instrument & Control Systems |  | 2007-04-30 | 2008-12-15
4 | DCS |  | 2007-04-30 | 2008-12-15
Activity | 0EF7000W86A01.1 | (DCS) MPS Issue |  | 2007-04-30
Activity | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | 2007-06-15 | 2008-04-16
Activity | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | 2007-08-01 | 2008-10-31
Activity | 0PF7000W86A03.1T | (DCS) Transportation for Early power | 2008-04-17 | 2008-05-31
Activity | 0CF7000W86A04 | (DCS) Installation for Early power | 2008-06-02 | 2008-06-16
Activity | 0SF7000W62A07 | (DCS) Loop Check | 2008-06-17 | 2008-07-01
Activity | 0SF7000W62A08 | (DCS) Start up | 2008-07-02 | 2008-07-11
Activity | 0SF7000W62A09 | (DCS) Electrical signal Test for Power Receiving | 2008-07-24 | 2008-07-28
Activity | 0PF7000W86A06T | (DCS) Transportation for Combined power | 2008-11-01 | 2008-12-15
4 | Control Valves |  | 2007-06-28 | 2008-09-30
Activity | 0EF7000W86A01 | (Control Valve) MPS Issue |  | 2007-06-28
Activity | 0PF7000W86A02P | (Control Valve) P.O & Procurement for Early power | 2007-10-01 | 2008-08-15
Activity | 0PF7000W86A04T | (Control Valve) 1st Delivery(On site) |  | 2008-05-15
Activity | 0PF7000W86A03T | (Control Valve) Transportation | 2008-08-16 | 2008-09-30
3 | Common Equipment & Infrastructure |  | 2007-03-01 | 2009-02-24
4 | Mechanical & Electrical/I&C Workshop (MEWS) |  | 2007-08-28 | 2009-02-24
Activity | 0EF5560W42A21 | (M&E WORKSHOP EQUIP) MPS Issue |  | 2007-08-28
Activity | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | 2007-11-29
Activity | 0EF5560W16A02 | (M&E WORKSHOP BLDG) FDN Design | 2007-11-29 | 2008-04-09
Activity | 0EF5560W32A04 | (M&E WORKSHOP BLDG) Structure Design | 2007-11-29 | 2008-04-09
Activity | 0PF5560W42A22P | (M&E WORKSHOP EQUIP) P.O & Procurement | 2007-11-29 | 2008-06-13
Activity | 0EF5560W00A11 | (M&E WORKSHOP LEB) GA & Load Data to Civil Design | 2007-12-05
Activity | 0EF5560W16A12 | (M&E WORKSHOP LEB) FDN Design | 2007-12-05 | 2008-04-07
Activity | 0EF5560W32A14 | (M&E WORKSHOP LEB) Structure Design | 2007-12-05 | 2008-04-07
Activity | 0CF5560W16A13 | (M&E WORKSHOP LEB) FDN Work | 2008-04-08 | 2008-06-04
Activity | 0CF5560W16A03 | (M&E WORKSHOP BLDG) FDN Work | 2008-04-10 | 2008-06-06
Activity | 0CF5560W32A15 | (M&E WORKSHOP LEB) Structure Work(R.C) | 2008-06-05 | 2008-10-04
Activity | 0CF5560W32A05 | (M&E WORKSHOP BLDG) Structure Work(R.C) | 2008-06-07 | 2008-10-07
Activity | 0PF5560W42A23T | (M&E WORKSHOP EQUIP) Transportation | 2008-06-14 | 2008-07-29
Activity | 0CF5560W36A17 | (M&E WORKSHOP LEB) Installation & Test - HVAC | 2008-10-06 | 2008-12-01
Activity | 0CF5560W74A18 | (M&E WORKSHOP LEB) Installation & Test - Elec | 2008-10-06 | 2008-12-01
Activity | 0CF5560W24A20 | (M&E WORKSHOP LEB) Building Finish | 2008-10-06 | 2008-12-01
Activity | 0CF5560W90A19 | (M&E WORKSHOP LEB) Installation & Test - I&C | 2008-10-06 | 2008-12-01
Activity | 0CF5560W36A07 | (M&E WORKSHOP BLDG) Installation & Test - HVAC | 2008-10-08 | 2008-12-03
Activity | 0CF5560W74A08 | (M&E WORKSHOP BLDG) Installation & Test - Elec | 2008-10-08 | 2008-12-03
Activity | 0CF5560W90A09 | (M&E WORKSHOP BLDG) Installation & Test - I&C | 2008-10-08 | 2008-12-03
Activity | 0CF5560W42A24 | (M&E WORKSHOP EQUIP) Installation | 2008-10-29 | 2008-12-27
Activity | 0CF5560W38A06 | (M&E WORKSHOP BLDG) Installation & Test - Fire Fighting Sys. | 2008-11-01 | 2008-12-27
Activity | 0CF5560W38A16 | (M&E WORKSHOP LEB) Installation & Test - Fire Fighting Sys. | 2008-11-01 | 2008-12-27
Activity | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | 2008-12-29 | 2009-02-24
4 | Warehouse |  | 2007-12-05 | 2008-12-01
Activity | 0EF5565W32A04 | (Warehouse) Structure Design | 2007-12-05 | 2008-04-07
Activity | 0EF5565W00A01 | (Warehouse) GA & Load Data to Civil Design | 2007-12-05
Activity | 0EF5565W16A02 | (Warehouse) FDN Design | 2007-12-05 | 2008-04-07
Activity | 0CF5565W16A03 | (Warehouse) FDN Work | 2008-04-08 | 2008-06-04
Activity | 0CF5565W32A05 | (Warehouse) Structure Work(R.C) | 2008-06-05 | 2008-10-04
Activity | 0CF5565W38A06 | (Warehouse) Installation & Test - Fire Fighting Sys. | 2008-10-06 | 2008-12-01
Activity | 0CF5565W36A07 | (Warehouse) Installation & Test - HVAC | 2008-10-06 | 2008-12-01
Activity | 0CF5565W74A08 | (Warehouse) Installation & Test - Elec | 2008-10-06 | 2008-12-01
Activity | 0CF5565W24A10 | (Warehouse) Building Finish | 2008-10-06 | 2008-12-01
Activity | 0CF5565W90A09 | (Warehouse) Installation & Test - I&C | 2008-10-06 | 2008-12-01
4 | Administration Building |  | 2007-03-30 | 2008-07-29
Activity | 0EF5566W00A01 | (ADMIN BLDG) GA & Load Data to Civil Design | 2007-03-30
Activity | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | 2007-03-30 | 2007-10-01
Activity | 0EF5566W32A04 | (ADMIN BLDG) Structure Design | 2007-03-30 | 2007-10-01
Activity | 0CF5566W16A03 | (ADMIN BLDG) FDN Work | 2007-10-02 | 2007-11-28
Activity | 0CF5566W32A05 | (ADMIN BLDG) Structure Work | 2007-11-29 | 2008-03-31
Activity | 0CF5566W74A08 | (ADMIN BLDG) Installation & Test - Elec | 2008-04-01 | 2008-07-01
Activity | 0CF5566W90A09 | (ADMIN BLDG) Installation & Test - I&C | 2008-04-01 | 2008-07-01
Activity | 0CF5566W24A10 | (ADMIN BLDG) Building Finish | 2008-04-30 | 2008-07-29
Activity | 0CF5566W36A07 | (ADMIN BLDG) Installation & Test - HVAC | 2008-05-15 | 2008-07-12
Activity | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | 2008-05-31 | 2008-07-29
4 | Fence & Gates |  | 2007-08-31 | 2008-09-01
Activity | 0EF5570W16A01 | (Gate House) FDN Design | 2007-08-31 | 2007-11-30
Activity | 0EF5570W32A03 | (Gate House) Structure Design | 2007-08-31 | 2007-11-30
Activity | 0EF5570W16A10 | (Fence & Gate) FDN Design | 2007-08-31 | 2007-12-12
Activity | 0CF5570W16A02 | (Gate House) FDN Work | 2007-12-01 | 2008-01-31
Activity | 0CF5570W16A11 | (Fence & Gate) FDN Work | 2007-12-13 | 2008-03-14
Activity | 0CF5570W32A04 | (Gate House) Structure Work | 2008-02-01 | 2008-05-03
Activity | 0CF5570W38A05 | (Gate House) Installation & Test - Fire Fighting Sys. | 2008-05-05 | 2008-07-01
Activity | 0CF5570W36A06 | (Gate House) Installation & Test - HVAC | 2008-05-05 | 2008-07-01
Activity | 0CF5570W74A07 | (Gate House) Installation & Test - Elec | 2008-05-05 | 2008-06-04
Activity | 0CF5570W90A08 | (Gate House) Installation & Test - I&C | 2008-05-05 | 2008-06-04
Activity | 0CF5570W16A12 | (Fence & Gate) Installation | 2008-05-08 | 2008-09-01
Activity | 0CF5570W24A09 | (Gate House) Building Finish | 2008-07-02 | 2008-09-01
4 | Road & Parking Places |  | 2007-11-01 | 2008-09-25
Activity | 0EF5570W16A01.1 | (Convered Parking Place shelter) FDN Design | 2007-11-01 | 2008-02-15
Activity | 0EF5570W32A03.1 | (Convered Parking Place shelter) Structure Design | 2007-11-01 | 2008-02-15
Activity | 0EF5570W30A05 | (Road & Parking Place) FDN Design | 2007-11-01 | 2008-02-12
Activity | 0CF5570W30A06 | (Road & Parking Place) FDN Work | 2008-02-13 | 2008-04-10
Activity | 0CF5570W16A02.1 | (Convered Parking Place shelter) FDN Work | 2008-02-16 | 2008-04-14
Activity | 0CF5570W30A07 | (Road & Parking Place) Civil Work | 2008-04-11 | 2008-09-25
Activity | 0CF5570W32A04.1 | (Convered Parking Place shelter) Structure Work | 2008-04-15 | 2008-06-11
4 | Central Control Building |  | 2007-04-02 | 2008-07-31
Activity | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | 2007-04-02
Activity | 0EF5510W16A02 | (CCR BLDG) FDN Design | 2007-04-02 | 2007-08-30
Activity | 0EF5510W32A04 | (CCR BLDG) Structure Design | 2007-04-02 | 2007-09-14
Activity | 0EF5510W24A05 | (CCR BLDG) Finish Design | 2007-05-31 | 2008-01-31
Activity | 0CF5510W16A03 | (CCR BLDG) FDN Work | 2007-09-01 | 2007-11-01
Activity | 0CF5510W32A04 | (CCR BLDG) Structure Work | 2007-11-02 | 2008-05-15
Activity | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | 2008-03-18 | 2008-07-31
Activity | 0CF5510W74A08 | (CCR BLDG) Installation & Test - Elec for Power Receiving | 2008-04-22 | 2008-07-09
Activity | 0CF5510W90A09 | (CCR BLDG) Installation & Test - I&C for Power Receiving | 2008-04-22 | 2008-07-09
Activity | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | 2008-05-15 | 2008-07-30
Activity | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | 2008-05-31 | 2008-07-31
4 | Pipe Rack |  | 2007-06-29 | 2008-04-15
Activity | 0EF5550W00A01 | (Pipe Rack) GA & Load Data to Civil Design | 2007-06-29
Activity | 0EF5550W16A03 | (Pipe Rack) FDN Design | 2007-06-29 | 2007-10-26
Activity | 0EF5550W46A02 | (Pipe Rack) Design | 2007-06-29 | 2007-11-26
Activity | 0CF5550W16A04 | (Pipe Rack) FDN Work for Early Power | 2007-10-27 | 2008-02-15
Activity | 0CF5550W46A05 | (Pipe Rack) Pipe Rack Installation for Early Power | 2007-12-13 | 2008-04-15
4 | Blackstart Diesel Generator |  | 2007-03-01 | 2008-09-06
Activity | 0EF3530W00A01 | (BSDG) Key Data | 2007-03-01 | 2007-04-30
Activity | 0EF3530W42A04 | (BSDG) MPS Issue |  | 2007-04-30
Activity | 0EF3530W00A13 | (BSDG BLDG) GA & Load Data to Civil Design | 2007-05-01
Activity | 0EF3530W16A14 | (BSDG BLDG) FDN Design | 2007-07-09 | 2007-10-08
Activity | 0EF3530W32A16 | (BSDG BLDG) Structure Design | 2007-07-09 | 2007-11-07
Activity | 0PF3530W42A05P | (BSDG) P.O & Procurement | 2007-08-01 | 2008-05-30
Activity | 0CF3530W16A15 | (BSDG BLDG) FDN Work | 2007-10-09 | 2007-12-08
Activity | 0CF3530W32A17 | (BSDG BLDG) Structure Work | 2007-12-10 | 2008-03-07
Activity | 0EF3530W16A02 | (BSDG) FDN Design | 2008-01-09 | 2008-04-09
Activity | 0CF3530W36A19 | (BSDG BLDG) Installation & Test - HVAC | 2008-03-08 | 2008-04-24
Activity | 0CF3530W74A20 | (BSDG BLDG) Installation & Test - Elec | 2008-03-08 | 2008-06-05
Activity | 0CF3530W90A21 | (BSDG BLDG) Installation & Test - I&C | 2008-03-08 | 2008-06-05
Activity | 0CF3530W16A03 | (BSDG) FDN Work | 2008-04-10 | 2008-06-06
Activity | 0CF3530W24A22 | (BSDG BLDG) Building Finish | 2008-05-05 | 2008-08-05
Activity | 0CF3530W38A18 | (BSDG BLDG) Installation & Test - Fire Fighting Sys. Sys | 2008-05-31 | 2008-07-17
Activity | 0PF3530W42A06T | (BSDG) Transportation | 2008-05-31 | 2008-07-15
Activity | 0CF3530W42A07 | (BSDG) Installation | 2008-07-16 | 2008-08-05
Activity | 0SF3530W62A08 | (BSDG) Loop chek | 2008-08-06 | 2008-08-15
Activity | 0SF3530W62A09 | (BSDG) Function Test | 2008-08-16 | 2008-08-22
Activity | 0SF3530W62A10 | (BSDG) Initial start up | 2008-08-23 | 2008-08-27
Activity | 0SF3530W62A11 | (BSDG) Synchronization | 2008-08-28 | 2008-09-01
Activity | 0SF3530W62A12 | (BSDG) Load Operation | 2008-09-02 | 2008-09-06
4 | Common Emergency Diesel Generator |  | 2007-03-01 | 2008-09-06
Activity | 0EF3530W00A01.1 | (Common EDG) Key data | 2007-03-01 | 2007-04-30
Activity | 0EF3530W42A04.1 | (Common EDG) MPS Issue |  | 2007-04-30
Activity | 0EF3530W00A13.1 | (Common EDG BLDG) GA & Load Data to Civil Design | 2007-05-01
Activity | 0EF3530W16A14.1 | (Common EDG BLDG) FDN Design | 2007-07-27 | 2007-10-24
Activity | 0EF3530W32A16.1 | (Common EDG BLDG) Structure Design | 2007-07-27 | 2007-11-27
Activity | 0PF3530W42A05.1P | (Common EDG) P.O & Procurement | 2007-07-27 | 2008-05-27
Activity | 0EF3530W16A02.1 | (Common EDG) FDN Design | 2007-07-27 | 2007-10-24
Activity | 0CF3530W16A15.1 | (Common EDG BLDG) FDN Work | 2007-10-25 | 2007-12-21
Activity | 0CF3530W16A03.1 | (Common EDG) FDN Work | 2007-10-25 | 2007-12-21
Activity | 0CF3530W32A17.1 | (Common EDG BLDG) Structure Work | 2007-12-22 | 2008-03-24
Activity | 0CF3530W38A18.1 | (Common EDG BLDG) Installation - Fire Fighting Sys. | 2008-03-25 | 2008-05-09
Activity | 0CF3530W74A20.1 | (Common EDG BLDG) Installation & Test - Elec | 2008-03-25 | 2008-05-09
Activity | 0CF3530W24A22.1 | (Common EDG BLDG) Building Finish | 2008-03-25 | 2008-06-25
Activity | 0CF3530W90A21.1 | (Common EDG BLDG) Installation & Test - I&C | 2008-03-25 | 2008-05-09
Activity | 0CF3530W36A19.1 | (Common EDG BLDG) Installation & Test - HVAC | 2008-05-15 | 2008-06-30
Activity | 0PF3530W42A06.1T | (Common EDG) Transportation | 2008-05-28 | 2008-07-11
Activity | 0CF3530W42A07.1 | (Common EDG) Installation | 2008-07-12 | 2008-08-13
Activity | 0SF3530W62A08.1 | (Common EDG) Loop chek | 2008-08-14 | 2008-08-20
Activity | 0SF3530W62A09.1 | (Common EDG) System Function Test | 2008-08-21 | 2008-08-28
Activity | 0SF3530W62A10.1 | (Common EDG) Initial Start up | 2008-08-29 | 2008-08-30
Activity | 0SF3530W62A11.1 | (Common EDG) Synchronization | 2008-08-31 | 2008-09-01
Activity | 0SF3530W62A12.1 | (Common EDG) Load Operation | 2008-09-02 | 2008-09-06
4 | Crane & Hoist |  | 2007-04-30 | 2008-09-17
Activity | 0EF6030W42A01 | (Crane & Hoist) MPS Issue |  | 2007-04-30
Activity | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | 2007-08-01 | 2008-05-06
Activity | 0CF5544W42A11 | (Crane & Hoist) Crane Erection for GIS Building | 2008-02-15 | 2008-04-01
Activity | 0PF6030W42A04T | (Crane & Hoist) 1st Delivery |  | 2008-02-15
Activity | 0PF6030W42A03T | (Crane & Hoist) Transportation | 2008-02-15 | 2008-07-01
Activity | 0CF3530W42A09 | (Crane & Hoist) Crane Erection for BSDG Building | 2008-03-08 | 2008-04-08
Activity | 0PF6030W42A05T | (Crane & Hoist) 2nd Delivery |  | 2008-04-15
Activity | 0CF3530W42A08 | (Crane & Hoist) Crane Erection for Common EDG Building | 2008-04-16 | 2008-05-16
Activity | 0CF3510W42A10 | (Crane & Hoist) Crane Erection for Air Compressor Building | 2008-04-16 | 2008-05-16
Activity | 0CF3530W42A12 | (Crane & Hoist) Crane Erection for Block EDG Building | 2008-04-16 | 2008-05-16
Activity | 0CF2010W42A07 | (Crane & Hoist) Crane Erection for STG Building | 2008-07-17 | 2008-09-17
Activity | 0CF1210W42A06 | (Crane & Hoist) Crane Erection for GTG Building | 2008-07-21 | 2008-08-18
4 | H2 Generation Plant |  | 2007-03-01 | 2008-12-30
Activity | 0EF3515W00A01 | (H2) P&ID & System Design | 2007-03-01 | 2007-06-29
Activity | 0EF3515W00A02 | (H2) Key data | 2007-04-27 | 2007-07-13
Activity | 0EF3515W42A07 | (H2) MPS Issue |  | 2007-07-13
Activity | 0PF3515W42A08P | (H2) P.O & Procurement | 2007-09-24 | 2008-07-23
Activity | 0EF3515W32A03 | (H2) Building Design | 2007-10-24 | 2008-01-23
Activity | 0EF3515W16A05 | (H2 Equipment) FDN Design | 2007-10-24 | 2008-01-21
Activity | 0CF3515W16A06 | (H2 Equipment) FDN Work | 2008-01-22 | 2008-04-20
Activity | 0CF3515W32A04 | (H2) Building Work | 2008-01-24 | 2008-07-23
Activity | 0PF3515W42A09T | (H2) Transportation | 2008-07-24 | 2008-09-06
Activity | 0CF3515W42A10 | (H2 Equipment) Installation | 2008-09-08 | 2008-11-07
Activity | 0CF3515W74A11 | (H2) Installation & Test - Elec. | 2008-10-07 | 2008-12-05
Activity | 0CF3515W90A12 | (H2) Installation & Test - I&C | 2008-10-07 | 2008-12-05
Activity | 0SF3515W62A13 | (H2) Loop check | 2008-12-06 | 2008-12-20
Activity | 0SF3515W62A14 | (H2) System Function Test | 2008-12-21 | 2008-12-25
Activity | 0SF3515W62A15 | (H2) System Operation | 2008-12-26 | 2008-12-30
4 | Laboratory |  | 2007-12-30 | 2008-12-10
Activity | 0EF3040W42A03 | (Lab) MPS Issue |  | 2007-12-30
Activity | 0PF3040W42A04P | (Lab) P.O & Procurement | 2008-03-31 | 2008-10-20
Activity | 0EF3040W16A01 | (Lab) FDN Design | 2008-03-31 | 2008-06-30
Activity | 0CF3040W16A02 | (Lab) FDN Work | 2008-07-01 | 2008-08-30
Activity | 0PF3040W42A05T | (Lab) Transportation | 2008-10-21 | 2008-12-04
Activity | 0CF3040W42A06 | (Lab) Installation | 2008-12-05 | 2008-12-10
2 | Power Plant Block #1 |  | 2007-03-01 | 2009-08-31
3 | Block #1 Early Power Block Common |  | 2007-03-01 | 2009-01-18
4 | Fuel Gas Supply System |  | 2007-03-01 | 2008-09-28
Activity | 1CF3520W16A01 | (FGSS #11) FDN Work(Misc. Equipment) | 2007-11-29 | 2008-02-29
Activity | 1CF3520W16A08 | (FGSS #12) FDN Work(Misc. Equipment) | 2007-11-29 | 2008-02-29
Activity | 1CF3520W58A03 | (FGSS #11) Piping Work(incl. Air leak Test & Blowing)_Gas Farm Area | 2008-05-20 | 2008-08-02
Activity | 1CF3520W58A10 | (FGSS #12) Piping Work(incl. Air leak Test & Blowing)_Gas Farm Area | 2008-05-20 | 2008-08-02
Activity | 1CF3520W86A02 | (FGSS #11) ESD Valve Skid installation | 2008-05-20 | 2008-05-30
Activity | 1CF3520W86A09 | (FGSS #12) ESD Valve Skid installation | 2008-05-20 | 2008-05-30
Activity | 1CF3520W74A04 | (FGSS #11) Installation & Test - Elec. | 2008-06-04 | 2008-08-02
Activity | 1CF3520W90A05 | (FGSS #11) Installation & Test - I&C | 2008-06-04 | 2008-08-02
Activity | 1CF3520W74A11 | (FGSS #12) Installation & Test - Elec. | 2008-06-04 | 2008-08-02
Activity | 1CF3520W90A12 | (FGSS #12) Installation & Test - I&C | 2008-06-04 | 2008-08-02
Activity | 1SF3520W62A06 | (FGSS #11) Fuel Gas Receiving | 2008-09-21 | 2008-09-21
Activity | 1SF3520W62A13 | (FGSS #12) Fuel Gas Receiving | 2008-09-21 | 2008-09-21
Activity | 1SF3520W62A07.2 | (FGSS #11) Metering System Calibration with supplier | 2008-09-24 | 2008-09-28
Activity | 1SF3520W62A14 | (FGSS #12) Metering System Calibration with supplier | 2008-09-24 | 2008-09-28
5 | Gas Pressure Reducing System |  | 2007-03-30 | 2008-08-05
Activity | 1EF3520W42A03 | (GPRS) MPS Issue |  | 2007-03-30
Activity | 1EF3520W00A28 | (GT/HRSG GPRS Shelter) GA & Load Data to Civil Design | 2007-06-01
Activity | 1EF3520W16A29 | (GT/HRSG GPRS Shelter) FDN Design | 2007-06-01 | 2007-10-04
Activity | 1EF3520W32A31 | (GT/HRSG GPRS Shelter) Structure Design | 2007-06-01 | 2007-10-04
Activity | 1PF3520W42A04P | (GPRS) P.O & Procurement for GT | 2007-06-01 | 2008-03-31
Activity | 1PF3520W42A14P | (GPRS) P.O & Procurement for HRSG | 2007-07-03 | 2008-04-30
Activity | 1EF3520W16A12 | (GPRS) FDN Design for HRSG | 2007-07-03 | 2007-11-09
Activity | 1EF3520W16A01 | (GPRS) FDN Design for GT | 2007-08-02 | 2007-10-16
Activity | 1CF3520W16A02 | (GPRS) FDN Work for GT | 2007-10-17 | 2007-12-13
Activity | 1CF3520W16A30 | (GT/HRSG GPRS Shelter) FDN Work | 2007-11-10 | 2008-01-10
Activity | 1CF3520W16A13 | (GPRS) FDN Work for HRSG | 2007-11-10 | 2008-01-07
Activity | 1CF3520W32A32 | (GT/HRSG GPRS Shelter) Structure Work | 2008-01-11 | 2008-04-12
Activity | 1PF3520W42A05T | (GPRS) Transportation for GT | 2008-04-01 | 2008-05-15
Activity | 1PF3520W42A15T | (GPRS) Transportation for HRSG | 2008-05-01 | 2008-06-14
Activity | 1CF3520W42A06 | (GPRS #11) Installation for GT | 2008-05-16 | 2008-07-31
Activity | 1CF3520W42A09 | (GPRS #12) Installation for GT | 2008-05-16 | 2008-07-31
Activity | 1CF3520W42A22 | (GPRS #11 for Fuel Change over) Installation | 2008-05-16 | 2008-06-26
Activity | 1CF3520W42A25 | (GPRS #12 for Fuel Change over) Installation | 2008-05-16 | 2008-06-26
Activity | 1CF3520W24A33 | (GT/HRSG GPRS Shelter) Shelter Finish | 2008-06-09 | 2008-07-31
Activity | 1CF3520W42A16 | (GPRS #11) Installation for HRSG | 2008-06-16 | 2008-07-26
Activity | 1CF3520W42A19 | (GPRS #12) Installation for HRSG | 2008-06-16 | 2008-07-26
Activity | 1SF3520W62A23 | (GPRS #11 for Fuel Change over) Loop chek & Motor Solo Test | 2008-06-27 | 2008-06-29
Activity | 1SF3520W62A26 | (GPRS #12 for Fuel Change over) Loop chek & Motor Solo Test | 2008-06-27 | 2008-06-29
Activity | 1SF3520W62A24 | (GPRS #11 for Fuel Change over) Function Test | 2008-06-30 | 2008-07-01
Activity | 1SF3520W62A27 | (GPRS #12 for Fuel Change over) Function Test | 2008-06-30 | 2008-07-01
Activity | 1SF3520W62A17 | (GPRS #11) Loop chek & Motor Solo Test for HRSG | 2008-07-27 | 2008-07-29
Activity | 1SF3520W62A20 | (GPRS #12) Loop chek & Motor Solo Test for HRSG | 2008-07-27 | 2008-07-29
Activity | 1SF3520W62A18 | (GPRS #11) Function Test for HRSG | 2008-07-30 | 2008-08-01
Activity | 1SF3520W62A21 | (GPRS #12) Function Test for HRSG | 2008-07-30 | 2008-08-01
Activity | 1SF3520W62A07 | (GPRS #11) Loop check for GT | 2008-08-01 | 2008-08-03
Activity | 1SF3520W62A10 | (GPRS #12) Loop check for GT | 2008-08-01 | 2008-08-03
Activity | 1SF3520W62A08 | (GPRS #11) Function Test for GT | 2008-08-04 | 2008-08-05
Activity | 1SF3520W62A11 | (GPRS #12) Function Test for GT | 2008-08-04 | 2008-08-05
5 | Fuel Gas Filter & Metering System |  | 2007-03-30 | 2008-06-20
Activity | 1EF3520W42A01.3 | (Filtering/Metering Station) MPS Issue |  | 2007-03-30
Activity | 1EF3520W00A10 | (Filtering/Metering Station Shelter) GA & Load Data to Civil Design | 2007-06-01
Activity | 1EF3520W16A11 | (Filtering/Metering Station Shelter) FDN Design | 2007-06-01 | 2007-10-12
Activity | 1EF3520W32A13 | (Filtering/Metering Station Shelter) Structure Design | 2007-06-01 | 2007-10-12
Activity | 1PF3520W42A02.3P | (Filtering/Metering Station) P.O & Procurement | 2007-07-03 | 2008-04-01
Activity | 1CF3520W16A12 | (Filtering/Metering Station Shelter) FDN Work | 2007-10-13 | 2007-12-10
Activity | 1CF3520W32A14 | (Filtering/Metering Station Shelter) Structure Work | 2007-12-11 | 2008-02-09
Activity | 1PF3520W42A03.3T | (Filtering/Metering Station) Transportation | 2008-04-02 | 2008-05-16
Activity | 1CF3520W42A04.3 | (Filtering/Metering Station #11) Installation | 2008-05-17 | 2008-05-31
Activity | 1CF3520W42A07.3 | (Filtering/Metering Station #12) Installation | 2008-05-17 | 2008-05-31
Activity | 1CF3520W24A15 | (Filtering/Metering Station Shelter) Shelter Finish | 2008-06-01 | 2008-06-20
Activity | 1SF3520W62A05.3 | (Filtering/Metering Station #11) Loop chek | 2008-06-01 | 2008-06-03
Activity | 1SF3520W62A08.3 | (Filtering/Metering Station #12) Loop chek | 2008-06-01 | 2008-06-03
Activity | 1SF3520W62A06.3 | (Filtering/Metering Station #11) Function Test | 2008-06-04 | 2008-06-05
Activity | 1SF3520W62A09.3 | (Filtering/Metering Station #12) Function Test | 2008-06-04 | 2008-06-05
5 | Gas Heater |  | 2007-03-30 | 2008-06-25
Activity | 1EF3520W42A06.2 | (Gas HTR) MPS Issue |  | 2007-03-30
Activity | 1EF3520W32A03.2 | (Gas HTR) Structure Design | 2007-07-03 | 2007-10-01
Activity | 1PF3520W42A07.2P | (Gas HTR) P.O & Procurement | 2007-07-03 | 2008-04-01
Activity | 1EF3520W16A01.2 | (Gas HTR) FDN Design | 2007-07-03 | 2007-10-01
Activity | 1CF3520W16A02.2 | (Gas HTR) FDN Work | 2007-10-02 | 2007-11-28
Activity | 1CF3520W32A04.2 | (Gas HTR) Structure Work | 2007-11-29 | 2008-01-29
Activity | 1PF3520W42A08.2T | (Gas HTR) Transportation | 2008-04-02 | 2008-05-16
Activity | 1CF3520W24A05.2 | (Gas HTR) Shelter Finish | 2008-05-17 | 2008-06-25
Activity | 1CF3520W42A09.2 | (Gas HTR #11) Installation | 2008-05-17 | 2008-06-02
Activity | 1CF3520W42A12.2 | (Gas HTR #12) Installation | 2008-05-17 | 2008-06-02
Activity | 1SF3520W62A10.2 | (Gas HTR #11) Loop chek | 2008-06-03 | 2008-06-05
Activity | 1SF3520W62A13.2 | (Gas HTR #12) Loop chek | 2008-06-03 | 2008-06-05
Activity | 1SF3520W62A11.2 | (Gas HTR #11) Function Test | 2008-06-06 | 2008-06-08
Activity | 1SF3520W62A14.2 | (Gas HTR #12) Function Test | 2008-06-06 | 2008-06-08
5 | Gas Compressor |  | 2007-03-01 | 2008-09-23
Activity | 1EF3520W00A03.1 | (Gas COMP PKG) FGC Key Data | 2007-03-01 | 2007-03-01
Activity | 1EF3520W42A04.1 | (Gas COMP PKG) MPS Issue(실제 NTP-1.5M) |  | 2007-03-01
Activity | 1PF3520W42A05.1P | (Gas COMP PKG) P.O & Procurement | 2007-03-15 | 2008-04-14
Activity | 1EF3520W00A25.1 | (Gas COMP House) GA & Load Data to Civil Design | 2007-03-30
Activity | 1EF3520W16A26.1 | (Gas COMP House) FDN Design | 2007-05-01 | 2007-10-01
Activity | 1EF3520W32A28 | (Gas COMP House) Structure Design | 2007-05-01 | 2007-10-01
Activity | 1EF3520W16A01.1 | (Gas COMP PKG) FDN Design | 2007-08-02 | 2007-11-01
Activity | 1CF3520W16A27.1 | (Gas COMP House) FDN Work | 2007-10-02 | 2007-11-28
Activity | 1CF3520W16A02.1 | (Gas COMP PKG) FDN Work | 2007-11-02 | 2008-01-31
Activity | 1CF3520W32A29 | (Gas COMP House) Structure Work | 2007-11-29 | 2008-02-12
Activity | 1PF3520W42A06.1T | (Gas COMP PKG)Transportation | 2008-04-15 | 2008-05-29
Activity | 1CF3520W42A07.1 | (Gas COMP PKG #11) Installation_Gas Compressor | 2008-05-30 | 2008-07-01
Activity | 1CF3520W42A16.1 | (Gas COMP PKG #12) Installation_Gas Compressor | 2008-05-30 | 2008-07-01
Activity | 1CF3520W42A11.1 | (Gas COMP PKG #11) Installation_Lube oil Sys.(incl. Flushing) | 2008-05-30 | 2008-07-01
Activity | 1CF3520W42A08.1 | (Gas COMP PKG #11) Installation_Air Compressor | 2008-05-30 | 2008-07-01
Activity | 1CF3520W42A09.1 | (Gas COMP PKG #11) Installation_Air Ventilation | 2008-05-30 | 2008-07-01
Activity | 1CF3520W42A20.1 | (Gas COMP PKG #12) Installation_Lube oil Sys.(incl. Flushing) | 2008-05-30 | 2008-07-01
Activity | 1CF3520W42A17.1 | (Gas COMP PKG #12) Installation_Air Compressor | 2008-05-30 | 2008-07-01
Activity | 1CF3520W42A18.1 | (Gas COMP PKG #12) Installation_Air Ventilation | 2008-05-30 | 2008-07-01
Activity | 1CF3520W24A30 | (Gas COMP House) Shelter finish | 2008-07-02 | 2008-08-10
Activity | 1CF3520W42A12.1 | (Gas COMP PKG #11) Installation_N2 Generation Sys. | 2008-07-02 | 2008-08-02
Activity | 1CF3520W42A10.1 | (Gas COMP PKG #11) Installation_Seal Gas Sys. | 2008-07-02 | 2008-08-02
Activity | 1CF3520W42A21.1 | (Gas COMP PKG #12) Installation_N2 Generation Sys. | 2008-07-02 | 2008-08-02
Activity | 1CF3520W42A19.1 | (Gas COMP PKG #12) Installation_Seal Gas Sys. | 2008-07-02 | 2008-08-02
Activity | 1SF3520W62A13.1 | (Gas COMP PKG #11) Loop chek | 2008-08-03 | 2008-08-12
Activity | 1SF3520W62A22.1 | (Gas COMP PKG #12) Loop chek | 2008-08-03 | 2008-08-12
Activity | 1SF3520W62A14.1 | (Gas COMP PKG #11) Function Test | 2008-09-16 | 2008-09-20
Activity | 1SF3520W62A23.1 | (Gas COMP PKG #12) Function Test | 2008-09-16 | 2008-09-20
Activity | 1SF3520W62A15.1 | (Gas COMP PKG #11) Running Test | 2008-09-22 | 2008-09-23
Activity | 1SF3520W62A24.1 | (Gas COMP PKG #12) Running Test | 2008-09-22 | 2008-09-23
5 | Gas cooler |  | 2008-05-30 | 2008-06-30
Activity | 1CF3520W42A01.1 | (Gas Cooler #11) Installation(incl. fan) | 2008-05-30 | 2008-06-20
Activity | 1CF3520W42A05.1 | (Gas Cooler #12) Installation(incl. fan) | 2008-05-30 | 2008-06-20
Activity | 1SF3520W62A02.1 | (Gas Cooler #11) Loop chek | 2008-06-21 | 2008-06-25
Activity | 1SF3520W62A06.1 | (Gas Cooler #12) Loop chek | 2008-06-21 | 2008-06-25
Activity | 1SF3520W62A03.1 | (Gas Cooler #11) Function Test | 2008-06-26 | 2008-06-28
Activity | 1SF3520W62A07.1 | (Gas Cooler #12) Function Test | 2008-06-26 | 2008-06-28
Activity | 1SF3520W62A04.1 | (Gas Cooler #11) Running Test | 2008-06-29 | 2008-06-30
Activity | 1SF3520W62A08.1 | (Gas Cooler #12) Running Test | 2008-06-29 | 2008-06-30
4 | N2 Gas System |  | 2007-04-02 | 2008-08-09
Activity | 1EF3515W00A01 | (N2 Gas System) P&ID & System Design | 2007-04-02 | 2007-08-27
Activity | 1EF3515W00A02 | (N2 Gas System) Key data | 2007-04-27 | 2007-07-31
Activity | 1EF3515W42A03 | (N2 Gas Equip) MPS Issue |  | 2007-07-31
Activity | 1PF3515W42A04P | (N2 Gas Equip) P.O & Procurement for FGSS(Local PROC.) | 2007-11-01 | 2008-05-30
Activity | 1EF3515W00A06 | (N2 Gas Station Shelter) GA & Load Data to Civil Design | 2007-12-03
Activity | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | 2007-12-03 | 2008-03-03
Activity | 1CF3515W16A07 | (N2 Gas Station Shelter) FDN Work | 2008-03-04 | 2008-04-30
Activity | 1CF3515W32A09 | (N2 Gas Station Shelter) Shelter Work | 2008-05-01 | 2008-08-09
Activity | 1CF3515W42A05 | (N2 Gas Equip) Installation for FGSS | 2008-05-31 | 2008-07-01
4 | Electrical System |  | 2007-03-01 | 2009-01-18
5 | Generator Circuit Breaker (GCB) |  | 2007-03-01 | 2009-01-04
Activity | 1EF6500W86A01 | (GT GCB) MPS Issue |  | 2007-03-01
Activity | 1PF6500W86A02P | (GT GCB) P.O & Procurement | 2007-05-31 | 2008-03-31
Activity | 1EF6500W86A06 | (ST GCB) MPS Issue |  | 2007-07-02
Activity | 1PF6500W86A07P | (ST GCB) P.O & Procurement | 2007-10-02 | 2008-07-30
Activity | 1PF6500W86A03T | (GT GCB) Transportation | 2008-04-01 | 2008-05-15
Activity | 1CF6500W86A04 | (GT GCB) Installation | 2008-05-16 | 2008-06-16
Activity | 1SF6500W62A05 | (GT GCB) Function Test | 2008-06-17 | 2008-07-01
Activity | 1PF6500W86A08T | (ST GCB) Transportation | 2008-07-31 | 2008-09-13
Activity | 1CF6500W86A09 | (ST GCB) Installation | 2008-11-21 | 2008-12-20
Activity | 1SF6500W62A10 | (ST GCB) Function Test | 2008-12-21 | 2009-01-04
5 | Extra High Voltage Cable |  | 2007-05-01 | 2008-07-23
Activity | 1EF6040W74A05 | (EHV Cable) MPS Issue |  | 2007-05-01
Activity | 1PF6040W74A06P | (EHV Cable) P.O & Procurement | 2007-08-02 | 2008-02-29
Activity | 1EF6040W16A02 | (Cable tunnel) FDN Design | 2007-08-02 | 2007-11-01
Activity | 1EF6040W16A01 | (Cable tunnel) Cable tunnel Design | 2007-08-02 | 2007-11-30
Activity | 1CF6040W16A03 | (Cable tunnel) Civil Work | 2007-11-02 | 2008-04-01
Activity | 1PF6040W74A07T | (EHV Cable) Transportation | 2008-03-01 | 2008-04-15
Activity | 1CF6040W74A08 | (EHV Cable) Cable Electrical Work | 2008-04-16 | 2008-07-01
Activity | 1CF6040W38A04 | (Cable tunnel) F/F Work & Test | 2008-05-31 | 2008-07-16
Activity | 1CF6040W62A09 | (EHV Cable) Function Test | 2008-07-02 | 2008-07-06
Activity | 1CF6040W74A10 | (EHV Cable) Connection with GIS & TR | 2008-07-17 | 2008-07-23
5 | Isolated Phase Busduct (IPB) |  | 2007-05-01 | 2008-09-01
Activity | 1EF6500W74A01 | (IPB) MPS Issue |  | 2007-05-01
Activity | 1PF6500W74A02P | (IPB) P.O & Procurement | 2007-08-02 | 2008-05-01
Activity | 1PF6500W74A03T | (IPB) Transportation | 2008-05-02 | 2008-06-16
Activity | 1CF6500W74A04 | (IPB) Installation form TR to GCB(incl. Support) | 2008-06-17 | 2008-08-18
Activity | 1CF6500W62A05 | (IPB) Insulation Test & Hi potential Test | 2008-08-19 | 2008-08-25
Activity | 1CF6500W74A06 | (IPB) IPB connection with TR & GCB | 2008-08-26 | 2008-09-01
5 | Power Transformer |  | 2007-03-01 | 2009-01-18
Activity | 1EF6500W70A03 | (GTG TR) MPS Issue(실제 NTP-1M) |  | 2007-03-01
Activity | 1PF6500W70A04P | (GTG TR) P.O & Procurement | 2007-04-02 | 2008-04-15
Activity | 1EF6500W70A11 | (STG TR) MPS Issue |  | 2007-05-01
Activity | 1PF6500W70A12P | (STG TR) P.O & Procurement | 2007-08-02 | 2008-07-30
Activity | 1EF6500W16A01 | (GTG TR) FDN Design | 2007-08-02 | 2007-11-30
Activity | 1CF6500W16A02 | (GTG TR) FDN & Firewall Work | 2007-12-01 | 2008-04-01
Activity | 1EF6500W16A09 | (STG TR) FDN Design | 2008-02-06 | 2008-07-04
Activity | 1PF6500W70A05T | (GTG TR) Transportation | 2008-04-16 | 2008-05-30
Activity | 1CF6500W70A06 | (GTG TR) Installation | 2008-05-31 | 2008-07-16
Activity | 1CF6500W16A10 | (STG TR) FDN & Firewall Work | 2008-07-05 | 2008-11-04
Activity | 1CF6500W38A07 | (GTG TR) F/F Install & test | 2008-07-17 | 2008-07-30
Activity | 1SF6500W62A08 | (GTG TR) Function Test | 2008-07-17 | 2008-07-23
Activity | 1PF6500W70A13T | (STG TR) Transportation | 2008-07-31 | 2008-09-13
Activity | 1CF6500W70A14 | (STG TR) Installation | 2008-11-05 | 2008-12-19
Activity | 1CF6500W38A15 | (STG TR) F/F test | 2008-12-20 | 2008-12-26
Activity | 1SF6500W62A16 | (STG TR) Function Test | 2009-01-05 | 2009-01-18
5 | Auxiliary Transformer |  | 2007-03-01 | 2008-07-16
Activity | 1EF6500W70A03.1 | (GTG UAT) MPS Issue(실제 NTP-1M) |  | 2007-03-01
Activity | 1PF6500W70A04.1P | (GTG UAT) P.O & Procurement | 2007-03-30 | 2008-03-17
Activity | 1EF6500W00A09 | (GTG #11 & UAT Shelter) GA & Load Data to Civil Design | 2007-05-31
Activity | 1EF6500W16A01.1 | (GTG UAT) FDN Design | 2007-05-31 | 2007-10-01
Activity | 1EF6500W16A10 | (GTG #11 & UAT Shelter) FDN Design | 2007-07-02 | 2007-10-01
Activity | 1EF6500W32A12 | (GTG #11& UAT Shelter) Structure Design | 2007-07-02 | 2007-10-01
Activity | 1CF6500W16A02.1 | (GTG UAT) FDN Work & Firewall Work | 2007-10-02 | 2008-01-29
Activity | 1CF6500W16A11 | (GTG #11 & UAT Shelter) FDN Work | 2007-10-02 | 2007-11-28
Activity | 1CF6500W32A13 | (GTG #11 & UAT Shelter) Structure Work | 2007-11-29 | 2008-02-29
Activity | 1PF6500W70A05.1T | (GTG UAT) Transportation | 2008-03-18 | 2008-05-01
Activity | 1CF6500W70A06.1 | (GTG UAT) Installation | 2008-05-02 | 2008-06-17
Activity | 1CF6500W38A14 | (GTG #11 & UAT Shelter) Installation & Test - Fire Fighting Sys. | 2008-05-31 | 2008-07-16
Activity | 1CF6500W74A15 | (GTG #11 & UAT Shelter) Installation & Test - Elec | 2008-05-31 | 2008-07-16
Activity | 1CF6500W90A16 | (GTG #11 & UAT Shelter) Installation & Test - I&C | 2008-05-31 | 2008-07-16
Activity | 1SF6500W62A08.1 | (GTG UAT) Function Test | 2008-06-18 | 2008-06-21
Activity | 1CF6500W38A07.1 | (GTG UAT) F/F Install & test | 2008-06-18 | 2008-07-03
5 | Emergency Diesel Generator |  | 2007-04-17 | 2008-08-15
Activity | 1EF3530W00A04 | (Block #1 EDG) Key data | 2007-04-17 | 2007-05-31
Activity | 1EF3530W42A05 | (Block #1 EDG) MPS Issue |  | 2007-05-01
Activity | 1EF3530W00A01 | (Block #1 EDG) GA & Load Data to Civil Design | 2007-08-01
Activity | 1EF3530W16A14 | (Block #1 EDG BLDG) FDN Design | 2007-08-01 | 2007-10-29
Activity | 1EF3530W32A16 | (Block #1 EDG BLDG) Structure Design | 2007-08-01 | 2007-11-29
Activity | 1PF3530W42A06P | (Block #1 EDG) P.O & Procurement | 2007-08-01 | 2008-05-30
Activity | 1EF3530W16A02 | (Block #1 EDG) FDN Design | 2007-08-01 | 2007-10-29
Activity | 1CF3530W16A15 | (Block #1 EDG BLDG) FDN Work | 2007-10-30 | 2007-12-29
Activity | 1CF3530W16A03 | (Block #1 EDG) FDN Work | 2007-10-30 | 2007-12-29
Activity | 1CF3530W32A17 | (Block #1 EDG BLDG) Structure Work | 2007-12-31 | 2008-04-01
Activity | 1CF3530W38A18 | (Block #1 EDG BLDG) Installation - Fire Fighting Sys. | 2008-04-02 | 2008-05-17
Activity | 1CF3530W36A19 | (Block #1 EDG BLDG) Installation & Test - HVAC | 2008-04-02 | 2008-05-17
Activity | 1CF3530W74A20 | (Block #1 EDG BLDG) Installation & Test - Elec | 2008-04-02 | 2008-05-17
Activity | 1CF3530W24A22 | (Block #1 EDG BLDG) Building Finish | 2008-04-02 | 2008-06-13
Activity | 1CF3530W90A21 | (Block #1 EDG BLDG) Installation & Test - I&C | 2008-04-02 | 2008-05-17
Activity | 1PF3530W42A07T | (Block #1 EDG) Transportation | 2008-05-31 | 2008-07-15
Activity | 1CF3530W42A08 | (Block #1 EDG) Installation | 2008-07-16 | 2008-08-05
Activity | 1SF3530W62A09 | (Block #1 EDG) Loop chek | 2008-08-06 | 2008-08-07
Activity | 1SF3530W62A10 | (Block #1 EDG) Function Test | 2008-08-08 | 2008-08-09
Activity | 1SF3530W62A11 | (Block #1 EDG) System Operation | 2008-08-10 | 2008-08-11
Activity | 1SF3530W62A12 | (Block #1 EDG) Synchronization | 2008-08-12 | 2008-08-13
Activity | 1SF3530W62A13 | (Block #1 EDG) Load Operation | 2008-08-14 | 2008-08-15
3 | Block #1 Combined Power Block Common |  | 2007-03-01 | 2009-03-15
4 | Closed Cooling Water System for Block #1 |  | 2007-03-01 | 2008-10-31
Activity | 1EF3030W00A12 | (CCWS) CCW H/EX key data | 2007-03-01 | 2007-05-31
Activity | 1EF3030W00A19 | (CCWP) Key data | 2007-03-01 | 2007-05-31
Activity | 1EF3030W68A03 | (EXP Head Tank) MPS Issue |  | 2007-05-31
Activity | 1EF3030W42A20 | (CCWP) MPS Issue |  | 2007-05-31
Activity | 1EF3030W42A13 | (CCW H/EX) MPS Issue |  | 2007-05-31
Activity | 1PF3030W68A04P | (EXP Head Tank) P.O & Procurement | 2007-09-03 | 2008-07-30
Activity | 1PF3030W42A21P | (CCWP) P.O & Procurement | 2007-09-03 | 2008-07-02
Activity | 1EF3030W16A17 | (CCWP) FDN Design | 2007-09-03 | 2008-01-30
Activity | 1PF3030W42A14P | (CCW H/EX) P.O & Procurement | 2007-09-03 | 2008-07-16
Activity | 1EF3030W16A10 | (CCW H/EX) FDN Design | 2007-09-03 | 2008-01-30
Activity | 1EF3030W16A01 | (EXP Head Tank) FDN Design | 2007-11-02 | 2008-04-01
Activity | 1CF3030W16A18 | (CCWP) FDN Work | 2008-01-31 | 2008-03-28
Activity | 1CF3030W16A11 | (CCW H/EX) FDN Work | 2008-01-31 | 2008-04-26
Activity | 1CF3030W16A02 | (EXP Head Tank) FDN Work | 2008-04-02 | 2008-04-30
Activity | 1CF3030W58A07 | (CCWS) Piping Work | 2008-06-16 | 2008-09-16
Activity | 1PF3030W42A22T | (CCWP) Transportation | 2008-07-03 | 2008-08-16
Activity | 1PF3030W42A15T | (CCW H/EX) Transportation | 2008-07-17 | 2008-08-30
Activity | 1PF3030W68A05T | (EXP Head Tank) Transportation | 2008-07-31 | 2008-09-13
Activity | 1CF3030W42A23 | (CCWP) Installation | 2008-08-18 | 2008-09-01
Activity | 1CF3030W74A08 | (CCWS) Installation & Test - Elec. | 2008-08-19 | 2008-10-18
Activity | 1CF3030W90A09 | (CCWS) Installation & Test - I&C | 2008-08-19 | 2008-10-18
Activity | 1CF3030W68A06 | (EXP Head Tank) Installation | 2008-09-15 | 2008-10-13
Activity | 1CF3030W42A16 | (CCW H/EX) Installation | 2008-09-17 | 2008-10-18
Activity | 1SF3030W62A24 | (CCWS) Loop chek | 2008-10-19 | 2008-10-23
Activity | 1SF3030W62A25 | (CCWS) System Function Test | 2008-10-24 | 2008-10-28
Activity | 1SF3030W62A26 | (CCWS) Pump Operation | 2008-10-29 | 2008-10-31
5 | Temporary Cooling Tower |  | 2007-10-31 | 2008-10-01
Activity | 1EF3030W42A01 | (Temp. Cooling Tower) MPS Issue |  | 2007-10-31
Activity | 1PF3030W42A02P | (Temp. Cooling Tower) P.O & Procurement | 2008-02-21 | 2008-06-19
Activity | 1PF3030W42A03T | (Temp. Cooling Tower)Transportation | 2008-06-20 | 2008-08-04
Activity | 1CF3030W42A04 | (Temp. Cooling Tower) Installation | 2008-08-05 | 2008-09-05
Activity | 1CF3030W58A05 | (Temp. Cooling Tower) Temp. pipe install | 2008-09-17 | 2008-10-01
4 | Clean & Dirty Oil System |  | 2007-04-02 | 2009-01-31
Activity | 1EF3546W00A02 | (Clean & Dirty Oil System) P&ID & System Design | 2007-04-02 | 2007-10-31
Activity | 1EF3546W00A01 | (Clean & Dirty Oil System) Key data | 2007-04-27 | 2007-07-31
Activity | 1EF3546W42A11 | (Dirty Oil Tank) MPS Issue |  | 2007-07-31
Activity | 1EF3546W42A05 | (Clean Oil Tank) MPS Issue |  | 2007-08-01
Activity | 1EF3546W42A17 | (Clean & Dirty LOP) MPS Issue |  | 2007-08-01
Activity | 1PF3546W42A18P | (Clean & Dirty LOP) P.O & Procurement | 2007-10-31 | 2008-10-01
Activity | 1EF3546W16A15 | (Clean & Dirty LOP) FDN Design | 2007-10-31 | 2008-03-31
Activity | 1PF3546W42A06P | (Clean Oil Tank) P.O & Procurement | 2007-11-01 | 2008-10-01
Activity | 1EF3546W16A03 | (Clean Oil Tank) FDN Design | 2007-11-01 | 2008-03-31
Activity | 1PF3546W42A12P | (Dirty Oil Tank) P.O & Procurement | 2007-11-01 | 2008-10-01
Activity | 1EF3546W16A09 | (Dirty Oil Tank) FDN Design | 2007-11-01 | 2008-03-31
Activity | 1CF3546W16A04 | (Clean Oil Tank) FDN Work | 2008-04-01 | 2008-05-31
Activity | 1CF3546W16A10 | (Dirty Oil Tank) FDN Work | 2008-04-01 | 2008-05-31
Activity | 1CF3546W16A16 | (Clean & Dirty LOP) FDN Work | 2008-04-01 | 2008-05-31
Activity | 1PF3546W42A07T | (Clean Oil Tank) Transportation | 2008-10-02 | 2008-11-15
Activity | 1PF3546W42A13T | (Dirty Oil Tank) Transportation | 2008-10-02 | 2008-11-15
Activity | 1PF3546W42A19T | (Clean & Dirty LOP) Transportation | 2008-10-02 | 2008-11-15
Activity | 1CF3546W42A08 | (Clean Oil Tank) Installation | 2008-11-17 | 2009-01-15
Activity | 1CF3546W42A14 | (Dirty Oil Tank) Installation | 2008-11-17 | 2009-01-16
Activity | 1CF3546W42A20 | (Clean & Dirty LOP) Installation & Test | 2008-11-17 | 2008-12-16
Activity | 1CF3546W58A21 | (Clean & Dirty Oil System) Piping Work | 2008-11-17 | 2009-01-31
Activity | 1CF3546W74A22 | (Clean & Dirty Oil System) Installation & Test - Elec. | 2009-01-01 | 2009-01-31
Activity | 1CF3546W90A23 | (Clean & Dirty Oil System) Installation & Test - I&C | 2009-01-01 | 2009-01-31
4 | Feed Water System |  | 2007-04-02 | 2009-01-21
Activity | 1EF3015W00A01 | (FWS) BFP Key data | 2007-04-02 | 2007-05-31
Activity | 1EF3015W00A02 | (FWS) P&ID & System Design | 2007-04-02 | 2007-11-14
Activity | 1EF3015W42A05 | (FWP) MPS Issue |  | 2007-06-01
Activity | 1PF3015W42A06P | (FWP) P.O & Procurement | 2007-08-30 | 2008-08-29
Activity | 1EF3015W58A13 | (FW PIPING) MPS Issue |  | 2007-08-31
Activity | 1EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | 2007-10-31
Activity | 1EF3015W32A10 | (FWP Shelter) FDN & Shelter Design | 2007-10-31 | 2008-01-30
Activity | 1EF3015W16A03 | (FWP) FDN Design | 2007-10-31 | 2008-01-30
Activity | 1PF3015W58A14P | (FW PIPING) P.O & Procurement | 2007-11-02 | 2008-06-30
Activity | 1CF3015W16A11 | (FWP Shelter) FDN Work | 2008-01-31 | 2008-04-01
Activity | 1CF3015W16A04 | (FWP) FDN Work | 2008-01-31 | 2008-04-30
Activity | 1CF3015W32A12 | (FWP Shelter) Shelter Structure Work | 2008-04-02 | 2008-06-30
Activity | 1PF3015W58A15T | (FW PIPING) Transportation | 2008-07-01 | 2008-08-14
Activity | 1CF3015W58A16 | (FW PIPING) Piping Work (incl. Insulation) | 2008-08-15 | 2008-11-15
Activity | 1PF3015W42A07T | (FWP) Transportation | 2008-08-30 | 2008-10-14
Activity | 1CF3015W74A18 | (FWS) Installation & Test - Elec. | 2008-10-15 | 2008-12-15
Activity | 1CF3015W90A19 | (FWS) Installation & Test - I&C | 2008-10-15 | 2008-12-15
Activity | 1CF3015W42A08 | (FWP) Installation | 2008-10-15 | 2008-11-27
Activity | 1CF3015W62A17 | (FW PIPING) Hydro Test | 2008-11-17 | 2008-12-13
Activity | 1SF3015W62A20 | (FWS) Loop check | 2008-12-16 | 2009-01-04
Activity | 1SF3015W62A21 | (FWS) System Function Test | 2009-01-05 | 2009-01-18
Activity | 1SF3015W62A22 | (FWS) Pump Operation | 2009-01-19 | 2009-01-21
4 | Chemical Dosing System |  | 2007-04-02 | 2009-01-25
Activity | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | 2007-04-02 | 2007-11-14
Activity | 1EF3045W42A02 | (Chemical Dosing Equip) MPS Issue |  | 2007-07-02
Activity | 1EF3045W00A06 | (Chemical Dosing BLDG) GA & Load Data to Civil Design | 2007-09-26
Activity | 1EF3045W16A07 | (Chemical Dosing BLDG) FDN Design | 2007-09-26 | 2008-01-23
Activity | 1EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | 2007-09-26 | 2008-01-23
Activity | 1PF3045W42A03P | (Chemical Dosing Equip) P.O & Procurement | 2007-09-26 | 2008-07-24
Activity | 1CF3045W16A08 | (Chemical Dosing BLDG) FDN Work | 2008-01-24 | 2008-03-25
Activity | 1CF3045W32A10 | (Chemical Dosing BLDG) Structure Work | 2008-03-26 | 2008-07-25
Activity | 1PF3045W42A04T | (Chemical Dosing Equip) Transportation | 2008-07-25 | 2008-09-08
Activity | 1CF3045W58A16 | (Chemical Dosing System) Piping Work | 2008-09-09 | 2008-12-09
Activity | 1CF3045W42A05 | (Chemical Dosing Equip) Installation | 2008-09-09 | 2008-11-10
Activity | 1CF3045W74A17 | (Chemical Dosing System) Installation & Test - Elec. | 2008-10-04 | 2008-12-04
Activity | 1CF3045W90A18 | (Chemical Dosing System) Installation & Test - I&C | 2008-10-04 | 2008-12-04
Activity | 1CF3045W38A11 | (Chemical Dosing BLDG) Installation & Test - Fire Fighting Sys. | 2008-11-01 | 2008-12-27
Activity | 1CF3045W36A12 | (Chemical Dosing BLDG) Installation & Test - HVAC | 2008-11-01 | 2008-12-27
Activity | 1CF3045W74A13 | (Chemical Dosing BLDG) Installation & Test - Elec | 2008-11-01 | 2008-12-27
Activity | 1CF3045W24A15 | (Chemical Dosing BLDG) Building Finish | 2008-11-01 | 2008-12-27
Activity | 1CF3045W90A14 | (Chemical Dosing BLDG) Installation & Test - I&C | 2008-11-01 | 2008-12-27
Activity | 1SF3045W62A19 | (Chemical Dosing System) Loop chek | 2008-12-28 | 2009-01-11
Activity | 1SF3045W62A20 | (Chemical Dosing System) System Function Test | 2009-01-12 | 2009-01-18
Activity | 1SF3045W62A21 | (Chemical Dosing System) System Operation | 2009-01-19 | 2009-01-25
4 | Sampling System |  | 2007-04-02 | 2009-02-04
Activity | 1EF3040W00A01 | (Sampling System) P&ID & System Design | 2007-04-02 | 2007-08-31
Activity | 1EF3040W42A04 | (Sampling Equip) MPS Issue |  | 2007-07-02
Activity | 1PF3040W42A05P | (Sampling Equip) P.O & Procurement | 2007-10-01 | 2008-07-30
Activity | 1EF3040W16A02 | (Sampling Equip) FDN Design | 2008-01-01 | 2008-04-02
Activity | 1CF3040W16A03 | (Sampling Equip) FDN Work | 2008-04-03 | 2008-05-30
Activity | 1PF3040W42A06T | (Sampling Equip) Transportation | 2008-07-31 | 2008-09-15
Activity | 1CF3040W42A07 | (Sampling Equip) Installation | 2008-09-16 | 2008-10-16
Activity | 1CF3040W58A08 | (Sampling System) Piping Work | 2008-10-17 | 2009-01-10
Activity | 1CF3040W74A09 | (Sampling System) Installation & Test - Elec. | 2008-12-11 | 2009-01-10
Activity | 1CF3040W90A10 | (Sampling System) Installation & Test - I&C | 2008-12-11 | 2009-01-10
Activity | 1SF3040W62A11 | (Sampling System) Loop chek | 2009-01-11 | 2009-01-20
Activity | 1SF3040W62A12 | (Sampling System) Chiller Function Test | 2009-01-21 | 2009-01-25
Activity | 1SF3040W62A13 | (Sampling System) Sampling System Function Test | 2009-01-26 | 2009-01-30
Activity | 1SF3040W62A14 | (Sampling System) System Service | 2009-01-31 | 2009-02-04
4 | Condensate System |  | 2007-03-01 | 2009-01-22
5 | Condenser |  | 2007-03-01 | 2009-01-22
Activity | 1EF3020W00A15 | (COND) Condenser Design Data | 2007-03-01 | 2007-04-12
Activity | 1EF3020W00A16 | (COND) Utility Consumption Data | 2007-03-01 | 2007-04-26
Activity | 1EF3020W00A01 | (COND System) P&ID & System Design | 2007-04-02 | 2007-11-30
Activity | 1EF3020W00A02 | (COND System) Key data | 2007-04-13 | 2007-05-31
Activity | 1EF3020W42A11 | (COND Flash Box) MPS Issue |  | 2007-07-02
Activity | 1EF3020W42A19 | (COND) MPS Issue |  | 2007-07-02
Activity | 1EF3020W42A05 | (COND Air EXT Equip) MPS Issue |  | 2007-07-02
Activity | 1PF3020W42A12P | (COND Flash Box) P.O & Procurement | 2007-10-03 | 2008-07-01
Activity | 1EF3020W16A17 | (COND) FDN Design | 2007-10-03 | 2008-01-30
Activity | 1PF3020W42A20P | (COND) P.O & Procurement | 2007-10-03 | 2008-07-30
Activity | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | 2007-10-03 | 2008-08-12
Activity | 1EF3020W16A09 | (COND Flash Box) FDN Design | 2008-01-02 | 2008-03-31
Activity | 1CF3020W16A18 | (COND) FDN Work | 2008-01-31 | 2008-05-02
Activity | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | 2008-03-01 | 2008-05-29
Activity | 1CF3020W16A10 | (COND Flash Box) FDN Work | 2008-04-01 | 2008-05-30
Activity | 1CF3020W16A04 | (COND Air EXT Equip) FDN Work | 2008-05-30 | 2008-07-28
Activity | 1PF3020W42A13T | (COND Flash Box) Transportation | 2008-07-02 | 2008-08-15
Activity | 1PF3020W42A21T | (COND) Transportation | 2008-07-31 | 2008-09-13
Activity | 1PF3020W42A07T | (COND Air EXT Equip) Transportation | 2008-08-13 | 2008-09-26
Activity | 1CF3020W42A14 | (COND Flash Box) Installation | 2008-08-16 | 2008-09-13
Activity | 1CF3020W42A22 | (COND) Installation | 2008-09-15 | 2008-12-15
Activity | 1CF3020W58A23 | (COND System) Piping Work(incl. Insulation) | 2008-09-23 | 2008-12-23
Activity | 1CF3020W74A24 | (COND System) Installation & Test - Elec. | 2008-09-23 | 2008-12-17
Activity | 1CF3020W90A25 | (COND System) Installation & Test - I&C | 2008-09-23 | 2008-12-17
Activity | 1CF3020W42A08 | (COND Air EXT Equip) Installation | 2008-09-27 | 2008-11-10
Activity | 1SF3020W62A26 | (COND System) Loop check | 2008-12-24 | 2009-01-07
Activity | 1SF3020W62A27 | (COND System) System Function Test | 2009-01-08 | 2009-01-17
Activity | 1SF3020W62A28 | (COND System) Pump Operation | 2009-01-18 | 2009-01-22
5 | Condenser Tube Cleaning System |  | 2007-07-30 | 2008-11-29
Activity | 1EF3020W42A01 | (CTCS) MPS Issue |  | 2007-07-30
Activity | 1PF3020W42A02P | (CTCS) P.O & Procurement | 2007-10-31 | 2008-09-01
Activity | 1PF3020W42A03T | (CTCS) Transportation | 2008-09-02 | 2008-10-16
Activity | 1CF3020W42A04 | (CTCS) Installation | 2008-10-17 | 2008-11-29
5 | Condensate Extraction Pump |  | 2007-05-31 | 2008-12-11
Activity | 1EF3020W42A03 | (CEP) MPS Issue |  | 2007-05-31
Activity | 1PF3020W42A04P | (CEP) P.O & Procurement | 2007-09-07 | 2008-08-07
Activity | 1EF3020W16A01 | (CEP) FDN Design | 2007-10-09 | 2008-01-04
Activity | 1CF3020W16A02 | (CEP) FDN Work | 2008-01-05 | 2008-05-07
Activity | 1PF3020W42A05T | (CEP) Transportation | 2008-08-08 | 2008-09-22
Activity | 1CF3020W42A06 | (CEP) Installation | 2008-09-23 | 2008-12-11
4 | Auxiliary Cooling Water System |  | 2007-04-02 | 2009-03-15
Activity | 1EF3030W00A01 | (ACWS) P&ID & System Design | 2007-04-02 | 2007-10-05
Activity | 1EF3030W00A02 | (ACWS) ACWP Key data | 2007-04-13 | 2007-07-02
Activity | 1EF3030W42A03 | (ACW PUMP) MPS Issue |  | 2007-07-02
Activity | 1EF3030W58A09 | (ACW Piping) MPS Issue |  | 2007-07-02
Activity | 1PF3030W42A04P | (ACW PUMP) P.O & Procurement | 2007-10-03 | 2008-09-30
Activity | 1PF3030W58A10P | (ACW Piping) P.O & Procurement | 2007-10-03 | 2008-07-01
Activity | 1PF3030W58A11T | (ACW Piping) Transportation | 2008-07-02 | 2008-08-15
Activity | 1CF3030W58A12 | (ACW Piping) Piping Work | 2008-09-08 | 2008-12-09
Activity | 1PF3030W42A05T | (ACW PUMP) Transportation | 2008-10-01 | 2008-11-14
Activity | 1CF3030W42A06 | (ACW PUMP) Installation | 2008-11-15 | 2008-12-09
Activity | 1CF3030W62A13 | (ACW Piping) Hydro Test | 2008-12-10 | 2009-01-07
Activity | 1CF3030W74A07 | (ACW PUMP) Installation - Elec | 2008-12-10 | 2008-12-31
Activity | 1CF3030W90A08 | (ACW PUMP) Installation - I&C | 2008-12-10 | 2008-12-31
Activity | 1SF3030W62A14 | (ACWS) Loop check | 2009-02-24 | 2009-03-05
Activity | 1SF3030W62A15 | (ACWS) System Function Test | 2009-03-06 | 2009-03-10
Activity | 1SF3030W62A16 | (ACWS) Pump Operation | 2009-03-11 | 2009-03-15
4 | Steam System |  | 2007-03-30 | 2009-01-22
Activity | 1EF2510W00A02 | (Steam System) Silencer Key data | 2007-03-30 | 2007-07-13
Activity | 1EF2510W00A01 | (Steam System) P&ID | 2007-04-02 | 2007-11-14
Activity | 1EF2510W42A03 | (Silencer) MPS Issue |  | 2007-07-13
Activity | 1EF2510W58A07 | (Steam PIPING) MPS Issue |  | 2007-07-30
Activity | 1PF2510W58A08P | (Steam PIPING) P.O & Procurement | 2007-10-01 | 2008-05-01
Activity | 1PF2510W42A04P | (Silencer) P.O & Procurement | 2007-10-15 | 2008-07-15
Activity | 1PF2510W58A09T | (Steam PIPING) Transportation | 2008-05-02 | 2008-06-16
Activity | 1CF2510W58A10 | (Steam PIPING) Piping Work | 2008-06-17 | 2008-11-18
Activity | 1PF2510W42A05T | (Silencer) Transportation | 2008-07-16 | 2008-08-29
Activity | 1CF2510W74A12 | (Steam System) Installation & Test - Elec. | 2008-08-30 | 2008-11-25
Activity | 1CF2510W90A13 | (Steam System) Installation & Test - I&C | 2008-08-30 | 2008-11-25
Activity | 1CF2510W42A06 | (Silencer) Installation | 2008-08-30 | 2008-09-27
Activity | 1CF2510W62A11 | (Steam PIPING) Hydro Test | 2008-11-19 | 2008-12-18
Activity | 1SF2510W62A14 | (Steam System) Loop chek | 2008-12-19 | 2009-01-07
Activity | 1SF2510W62A15 | (Steam System) System Function Test | 2009-01-08 | 2009-01-17
Activity | 1SF2510W62A16 | (Steam System) System Service | 2009-01-18 | 2009-01-22
4 | Bypass System |  | 2007-03-21 | 2008-12-14
Activity | 1EF2510W00A02.1 | (Bypass System) Bypass Valve, PRDS key data | 2007-03-21 | 2007-05-17
Activity | 1EF2510W00A01.1 | (Bypass System) P&ID & System Design | 2007-04-02 | 2007-11-01
Activity | 1EF2510W42A03.1 | (Bypass Valve) MPS Issue |  | 2007-05-18
Activity | 1PF2510W42A04.1P | (Bypass Valve) P.O & Procurement | 2007-08-20 | 2008-06-13
Activity | 1PF2510W42A05.1T | (Bypass Valve) Transportation | 2008-06-14 | 2008-07-29
Activity | 1CF2510W58A07.1 | (Bypass System) Piping Work | 2008-07-30 | 2008-10-29
Activity | 1CF2510W90A10.1 | (Bypass System) Installation & Test - I&C | 2008-07-30 | 2008-09-29
Activity | 1CF2510W74A09.1 | (Bypass System) Installation & Test - Elec. | 2008-07-30 | 2008-09-29
Activity | 1CF2510W42A06.1 | (Bypass Valve) Installation | 2008-07-30 | 2008-09-29
Activity | 1CF2510W62A08.1 | (Bypass System) Hydro Test | 2008-10-30 | 2008-11-15
Activity | 1SF2510W62A11.1 | (Bypass System) Loop check | 2008-11-16 | 2008-11-29
Activity | 1SF2510W62A12.1 | (Bypass System) System Function Test | 2008-11-30 | 2008-12-09
Activity | 1SF2510W62A13.1 | (Bypass System) System Service | 2008-12-10 | 2008-12-14
4 | Clean Drain System |  | 2007-03-15 | 2009-03-11
Activity | 1EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | 2007-03-15 | 2008-01-15
Activity | 1EF3020W00A02.1 | (Clean Drain System) Clean drain pump Key data | 2007-04-02 | 2007-07-02
Activity | 1EF3020W42A05.1 | (Clean Drain Flash Vessel) MPS Issue |  | 2007-07-02
Activity | 1EF3020W42A17.1 | (Clean Drain Pump) MPS Issue |  | 2007-07-02
Activity | 1EF3020W42A11.1 | (Clean Drain Tank) MPS Issue |  | 2007-07-02
Activity | 1PF3020W42A12.1P | (Clean Drain Tank) P.O & Procurement | 2007-10-01 | 2008-09-01
Activity | 1PF3020W42A06.1P | (Clean Drain Flash Vessel) P.O & Procurement | 2007-10-03 | 2008-04-02
Activity | 1EF3020W16A03.1 | (Clean Drain Flash Vessel) FDN Design | 2007-10-03 | 2008-02-29
Activity | 1EF3020W16A15.1 | (Clean Drain Pump) FDN Design | 2007-10-03 | 2008-02-29
Activity | 1PF3020W42A18.1P | (Clean Drain Pump) P.O & Procurement | 2007-10-03 | 2008-07-17
Activity | 1EF3020W16A09.1 | (Clean Drain Tank) FDN Design | 2007-12-06 | 2008-05-05
Activity | 1CF3020W16A04.1 | (Clean Drain Flash Vessel) FDN Work | 2008-03-01 | 2008-04-28
Activity | 1CF3020W16A16.1 | (Clean Drain Pump) FDN Work | 2008-03-01 | 2008-05-01
Activity | 1PF3020W42A07.1T | (Clean Drain Flash Vessel) Transportation | 2008-04-03 | 2008-05-17
Activity | 1CF3020W16A10.1 | (Clean Drain Tank) FDN Work | 2008-05-06 | 2008-07-02
Activity | 1CF3020W42A08.1 | (Clean Drain Flash Vessel) Installation | 2008-05-19 | 2008-06-16
Activity | 1PF3020W42A19.1T | (Clean Drain Pump) Transportation | 2008-07-18 | 2008-09-01
Activity | 1CF3020W42A20.1 | (Clean Drain Pump) Installation | 2008-09-02 | 2008-09-30
Activity | 1PF3020W42A13.1T | (Clean Drain Tank) Transportation | 2008-09-02 | 2008-10-16
Activity | 1CF3020W58A21.1 | (Clean Drain System) Piping Work | 2008-10-17 | 2009-01-16
Activity | 1CF3020W42A14.1 | (Clean Drain Tank) Installation | 2008-10-17 | 2008-11-14
Activity | 1CF3020W74A23.1 | (Clean Drain System) Installation & Test - Elec. | 2008-12-17 | 2009-01-16
Activity | 1CF3020W90A24.1 | (Clean Drain System) Installation & Test - I&C | 2008-12-17 | 2009-01-16
Activity | 1CF3020W62A22.1 | (Clean Drain System) Hydro Test | 2009-01-17 | 2009-02-14
Activity | 1SF3020W62A25.1 | (Clean Drain System) Loop chek | 2009-02-15 | 2009-03-06
Activity | 1SF3020W62A26.1 | (Clean Drain System) System Function Test | 2009-03-07 | 2009-03-09
Activity | 1SF3020W62A27.1 | (Clean Drain System) System Service | 2009-03-10 | 2009-03-11
3 | BOP Piping for Block #1 Common |  | 2007-03-01 | 2009-01-31
4 | Gas Supply System (GTG) |  | 2008-05-20 | 2008-07-19
Activity | 1CF3520W58A01 | (Gas Supply System) Piping Work(Yard area) | 2008-05-20 | 2008-07-19
4 | Oil Supply System (GTG) |  | 2008-03-03 | 2008-05-19
Activity | 1CF3520W58A01.1 | (Oil Supply System) Piping Work(Yard area) | 2008-03-03 | 2008-05-02
Activity | 1CF3520W62A02.1 | (Oil Supply System) Hydro Test | 2008-05-03 | 2008-05-19
4 | Make Up Wate Supply System (STG) |  | 2008-05-19 | 2008-08-04
Activity | 1CF3010W58A01 | (Make Up WTR Supply System) Piping Work(Block #1) | 2008-05-19 | 2008-07-18
Activity | 1CF3010W62A02 | (Make Up WTR Supply System) Hydro Test | 2008-07-19 | 2008-08-04
4 | Water Treatment Sytstem (BOP) |  | 2008-10-17 | 2009-01-01
Activity | 1CF3010W58A01.1 | (Water Treatment System) Piping Work(Block #1) | 2008-10-17 | 2008-12-16
Activity | 1CF3010W62A02.1 | (Water Treatment System) Hydro Test | 2008-12-17 | 2009-01-01
4 | Service Water System (BOP) |  | 2008-10-17 | 2009-01-01
Activity | 1CF3035W58A01 | (SWS) Piping Work(Block #1) | 2008-10-17 | 2008-12-16
Activity | 1CF3035W62A02 | (SWS) Hydro Test | 2008-12-17 | 2009-01-01
4 | Potable Water System (BOP) |  | 2008-11-04 | 2009-01-19
Activity | 1CF3035W58A01.1 | (PWS) Piping Work(Block #1) | 2008-11-04 | 2009-01-02
Activity | 1CF3035W62A02.1 | (PWS) Hydro Test | 2009-01-03 | 2009-01-19
4 | Compressed Air System (BOP) |  | 2008-09-02 | 2008-12-31
Activity | 1CF3510W58A01 | (COMP Air System) Piping Work(incl. Air blowing)_Block #1 | 2008-09-02 | 2008-12-31
4 | Waste Water Treatment System (BOP) |  | 2008-10-17 | 2009-01-31
Activity | 1CF4035W58A01 | (WWTS) Piping Work(Blcok #1) | 2008-10-17 | 2009-01-15
Activity | 1CF4035W62A02 | (WWTS) Hydro Test | 2009-01-16 | 2009-01-31
4 | Sewage Water System (BOP) |  | 2008-10-17 | 2009-01-31
Activity | 1CF4035W58A01.1 | (STS) Piping Work(Block #1) | 2008-10-17 | 2009-01-15
Activity | 1CF4035W62A02.1 | (STS) Hydro Test | 2009-01-16 | 2009-01-31
4 | U/G Line |  | 2008-10-17 | 2009-01-16
Activity | 1CF4035W22A01 | (STRS) Piping Work(Block #1) | 2008-10-17 | 2009-01-10
Activity | 1CF4035W22A02 | (SWS) Piping Work(Block #1) | 2008-10-17 | 2009-01-16
4 | Pipe Rack |  | 2007-03-01 | 2008-05-31
Activity | 1EF5550W00A01 | (PipeRack) Pipe Rack Key Data | 2007-03-01 | 2007-03-29
Activity | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | 2007-03-30
Activity | 1EF5550W46A07 | (PipeRack) MPS Issue |  | 2007-03-30
Activity | 1EF5550W20A05 | (PipeRack) Structure Design | 2007-05-30 | 2007-08-31
Activity | 1EF5550W16A03 | (PipeRack) FDN Design | 2007-05-30 | 2007-08-31
Activity | 1PF5550W46A08P | (PipeRack) P.O & Procurement | 2007-06-28 | 2008-01-02
Activity | 1CF5550W16A04 | (PipeRack) FDN Work Block #1 Area | 2007-09-01 | 2008-01-01
Activity | 1PF5550W46A09T | (PipeRack) Trasnportation | 2008-01-03 | 2008-02-16
Activity | 1CF5550W46A06 | (PipeRack) Structure Work for Block #1 Area | 2008-02-18 | 2008-05-31
3 | Gas Turbine & Generator #11 & #12 |  | 2007-03-01 | 2008-11-29
4 | GTG Common |  | 2007-03-01 | 2008-08-18
Activity | 1EF1210W00A06 | (GTG Common BLDG) GA & Load Data to Civil Design | 2007-03-01
Activity | 1EF1210W16A07 | (GTG Common BLDG) FDN Design | 2007-03-01 | 2007-08-01
Activity | 1EF1210W20A09 | (GTG Common BLDG) Structure Design | 2007-03-01 | 2007-08-31
Activity | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | 2007-03-01 | 2007-03-30
Activity | 1EF1200W00A02 | (GTG #11/#12) Instrument, Service Air, Aux steam Data | 2007-03-01 | 2007-03-29
Activity | 1EF1200W00A03 | (GTG #11/#12) Utility Consumption Data | 2007-03-01 | 2007-04-26
Activity | 1EF1200W00A04 | (GTG #11/#12) Emergency Load Data | 2007-03-01 | 2007-04-26
Activity | 1EF1200W00A05 | (GTG #11/#12) Black Start Load Data | 2007-03-01 | 2007-04-26
Activity | 1CF1210W16A08 | (GTG Common BLDG) FDN Work | 2007-09-01 | 2007-12-31
Activity | 1PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | 2007-09-03 | 2008-01-15
Activity | 1CF1210W20A10 | (GTG Common BLDG) Structure Work(S/S, Cladding, Roof) | 2008-01-16 | 2008-05-19
Activity | 1CF1210W36A12 | (GTG Common BLDG) Installation & Test - HVAC | 2008-05-15 | 2008-07-11
Activity | 1CF1210W74A13 | (GTG Common BLDG) Installation & Test - Elec | 2008-05-20 | 2008-07-16
Activity | 1CF1210W90A14 | (GTG Common BLDG) Installation & Test - I&C | 2008-05-20 | 2008-07-16
Activity | 1CF1210W38A11 | (GTG Common BLDG) Installation & Test - Fire Fighting Sys. | 2008-05-31 | 2008-07-28
Activity | 1CF1210W24A15 | (GTG Common BLDG) Building Finish | 2008-06-27 | 2008-08-18
4 | GTG #11 LEB |  | 2007-05-31 | 2008-08-04
Activity | 1EF1200W00A01.1 | (GTG #11 LEB) GA & Load Data to Civil Design | 2007-05-31
Activity | 1EF1200W16A02 | (GTG #11 LEB) FDN Design | 2007-08-01 | 2007-11-27
Activity | 1EF1200W32A04 | (GTG #11 LEB) Structure Design | 2007-08-01 | 2007-11-27
Activity | 1CF1200W16A03 | (GTG #11 LEB) FDN Work | 2007-11-28 | 2008-01-24
Activity | 1CF1200W32A05 | (GTG #11 LEB) Structure Work | 2008-01-25 | 2008-04-26
Activity | 1CF1200W36A07 | (GTG #11 LEB) Installation & Test - HVAC | 2008-05-15 | 2008-06-30
Activity | 1CF1200W24A10 | (GTG #11 LEB) Building Finish | 2008-05-27 | 2008-08-04
Activity | 1CF1200W38A06 | (GTG #11 LEB) Installation & Test - Fire Fighting Sys. | 2008-05-31 | 2008-07-04
Activity | 1CF1200W74A08 | (GTG #11 LEB) Installation & Test - Elec | 2008-06-04 | 2008-08-04
Activity | 1CF1200W90A09 | (GTG #11 LEB) Installation & Test - I&C | 2008-06-04 | 2008-08-04
4 | GTG #11 |  | 2007-03-01 | 2008-11-27
5 | GTG #11 Main body |  | 2007-03-01 | 2008-07-31
Activity | 1PF1213W42A08P | (GEN #11) P.O & Procurement | 2007-03-01 | 2008-01-31
Activity | 1EF1213W16A06 | (GEN #11) FDN Design | 2007-03-01 | 2007-07-31
Activity | 1PF1213W42A03P | (GT #11) P.O & Procurement | 2007-03-01 | 2008-01-31
Activity | 1EF1213W16A01 | (GT #11) FDN Design | 2007-03-01 | 2007-05-31
Activity | 1CF1213W16A07 | (GEN #11) FDN Work | 2007-08-01 | 2007-12-15
Activity | 1CF1213W16A02 | (GT #11) FDN Work | 2007-08-01 | 2007-12-15
Activity | 1PF1213W42A09T | (GEN #11) Transportation | 2008-02-01 | 2008-03-17
Activity | 1PF1213W42A04T | (GT #11) Transportation | 2008-02-01 | 2008-03-15
Activity | 1CF1213W42A05 | (GT #11) Installation(On FDN~Final Alignment) | 2008-03-17 | 2008-07-30
Activity | 1CF1213W42A10 | (GEN #11) Installation | 2008-04-01 | 2008-07-31
Activity | 1CF1213W52A11 | (GTG #11) Insulation | 2008-06-16 | 2008-06-30
5 | GTG #11 Electrical System |  | 2007-03-01 | 2008-09-26
Activity | 1PF1255W70A01P | (GTG#11 Electrical) P.O & Procurement | 2007-03-01 | 2008-03-31
Activity | 1PF1255W70A02T | (GTG#11 Electrical) Transportation | 2008-04-01 | 2008-05-15
Activity | 1CF1255W70A03 | (GTG#11 Electrical) Installation- PCC | 2008-08-01 | 2008-09-15
Activity | 1CF1255W70A04 | (GTG#11 Electrical) Installation- MCC | 2008-08-01 | 2008-09-15
Activity | 1CF1255W70A05 | (GTG#11 Electrical) Installation- Protection Sys. | 2008-08-01 | 2008-09-15
Activity | 1CF1255W70A07 | (GTG#11 Electrical) Installation- SEE&SFC Sys. | 2008-08-01 | 2008-09-15
Activity | 1CF1255W70A08 | (GTG#11 Electrical) Installation- DC&UPS Sys. | 2008-08-01 | 2008-09-15
Activity | 1CF1255W74A09 | (GTG#11 Electrical) Cable work | 2008-08-01 | 2008-09-15
Activity | 1CF1255W86A06 | (GTG#11 Electrical) Installation- GT control Sys. | 2008-08-04 | 2008-09-15
Activity | 1CF1255W62A10 | (GTG#11 Electrical) Electrical Function Test | 2008-09-16 | 2008-09-20
Activity | 1CF1255W62A11 | (GTG#11 Electrical) Loop Test | 2008-09-22 | 2008-09-26
5 | GTG #11 Starting System(Turning Device) |  | 2007-03-01 | 2008-05-27
Activity | 1PF1265W42A01P | (Turning Gear) P.O & Procurement | 2007-03-01 | 2008-02-29
Activity | 1PF1265W42A02T | (Turning Gear) Transportation | 2008-03-01 | 2008-04-15
Activity | 1CF1265W42A03 | (Turning Gear) Installation | 2008-04-16 | 2008-04-23
Activity | 1CF1265W74A04 | (Turning Gear) Installation- Elec. | 2008-04-24 | 2008-05-01
Activity | 1CF1265W90A05 | (Turning Gear) Installation- I&C | 2008-04-24 | 2008-05-01
Activity | 1SF1265W62A06 | (Turning Gear) Loop check | 2008-05-02 | 2008-05-06
Activity | 1SF1265W62A07.0 | (Turning Gear) Function Test | 2008-05-25 | 2008-05-27
5 | GTG #11 Air Intake System |  | 2007-03-01 | 2008-06-16
Activity | 1PF1230W20A02P | (Air Intake) P.O & Procurement_Steel Sturucture | 2007-03-01 | 2008-01-31
Activity | 1PF1230W64A05P | (Air Intake) P.O & Procurement_Inlet Duct | 2007-03-01 | 2008-01-31
Activity | 1PF1230W64A08P | (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2007-03-01 | 2008-01-31
Activity | 1CF1230W16A01 | (Air Intake) FDN Work_Steel Sturucture | 2007-10-01 | 2007-11-30
Activity | 1PF1230W20A03T | (Air Intake) Transportation_Steel Sturucture | 2008-02-01 | 2008-03-17
Activity | 1PF1230W64A06T | (Air Intake) Transportation_Inlet Duct | 2008-02-01 | 2008-03-17
Activity | 1PF1230W64A09T | (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-02-01 | 2008-03-17
Activity | 1CF1230W20A04 | (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | 2008-03-18 | 2008-04-18
Activity | 1CF1230W64A07 | (Air Intake) Installation_Inlet Duct | 2008-04-19 | 2008-04-26
Activity | 1CF1230W64A10 | (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-04-28 | 2008-05-21
Activity | 1CF1230W74A11 | (Air Intake) Installation- Elec. | 2008-05-22 | 2008-06-04
Activity | 1CF1230W90A12 | (Air Intake) Installation- I&C | 2008-05-22 | 2008-06-04
Activity | 1SF1230W62A13 | (Air Intake) Loop chek | 2008-06-05 | 2008-06-07
Activity | 1SF1230W62A14 | (Air Intake) Function Test | 2008-06-11 | 2008-06-13
Activity | 1SF1230W62A15 | (Air Intake) Load(Running) Test | 2008-06-14 | 2008-06-16
5 | GTG #11 Air and Flue Gas System |  | 2007-03-01 | 2008-05-19
Activity | 1PF1265W64A01P | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | 2007-03-01 | 2008-01-31
Activity | 1PF1265W64A02T | (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | 2008-02-01 | 2008-03-17
Activity | 1CF1265W64A03 | (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | 2008-03-18 | 2008-04-17
Activity | 1CF1265W64A04 | (Air&Flue Gas System) Duct work | 2008-04-18 | 2008-05-02
Activity | 1CF1265W74A05 | (Air&Flue Gas System) Installation- Elec. | 2008-05-03 | 2008-05-16
Activity | 1CF1265W90A06 | (Air&Flue Gas System) Installation- I&C | 2008-05-03 | 2008-05-16
Activity | 1SF1265W62A07 | (Air&Flue Gas System) Loop chek | 2008-05-14 | 2008-05-16
Activity | 1SF1265W62A08 | (Air&Flue Gas System) Function Test | 2008-05-17 | 2008-05-19
5 | GTG #11 Lube Oil System |  | 2007-03-01 | 2008-05-24
Activity | 1PF1250W42A02P | (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | 2007-03-01 | 2008-01-30
Activity | 1PF1250W42A06P | (Lube Oil System) P.O & Procurement_Lube oil functional Module | 2007-03-01 | 2008-01-30
Activity | 1PF1250W42A10P | (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | 2007-03-01 | 2008-01-30
Activity | 1CF1250W16A01 | (Lube Oil System) FDN Work_Lube Oil Supply Module | 2007-10-01 | 2007-11-30
Activity | 1CF1250W16A05 | (Lube Oil System) FDN Work_Lube oil functional Module | 2007-10-01 | 2007-11-30
Activity | 1CF1250W16A09 | (Lube Oil System) FDN Work_Lube oil Mist Separator | 2007-10-01 | 2007-11-30
Activity | 1PF1250W42A03T | (Lube Oil System) Transportation_Lube Oil Supply Module | 2008-01-31 | 2008-03-15
Activity | 1PF1250W42A07T | (Lube Oil System) Transportation_Lube oil functional Module | 2008-01-31 | 2008-03-15
Activity | 1PF1250W42A11T | (Lube Oil System) Transportation_Lube oil Mist Separator | 2008-01-31 | 2008-03-15
Activity | 1CF1250W42A04 | (Lube Oil System) Installation_Lube Oil Supply Module | 2008-03-17 | 2008-04-01
Activity | 1CF1250W42A08 | (Lube Oil System) Installation_Lube oil functional Module | 2008-03-17 | 2008-04-01
Activity | 1CF1250W42A12 | (Lube Oil System) Installation_Lube oil Mist Separator | 2008-03-17 | 2008-03-24
Activity | 1CF1250W58A13 | (Lube Oil System) Piping work | 2008-04-02 | 2008-05-02
Activity | 1CF1250W62A16 | (GTG #11) Lube Oil Flushing | 2008-05-02 | 2008-05-19
Activity | 1CF1250W74A14 | (Lube Oil System) Installation- Elec. | 2008-05-03 | 2008-05-16
Activity | 1CF1250W90A15 | (Lube Oil System) Installation- I&C | 2008-05-03 | 2008-05-16
Activity | 1SF1250W62A17 | (Lube Oil System) Loop chek | 2008-05-17 | 2008-05-19
Activity | 1SF1250W62A18 | (Lube Oil System) Function Test | 2008-05-20 | 2008-05-22
Activity | 1SF1250W62A19 | (Lube Oil System) Load Test | 2008-05-23 | 2008-05-24
5 | GTG#11 Generator Seal Oil System |  | 2007-03-01 | 2008-05-21
Activity | 1PF1250W42A02.1P | (GEN Seal Oil Sys.) P.O & Procurement | 2007-03-01 | 2008-01-30
Activity | 1CF1250W16A01.1 | (GEN Seal Oil Sys.) FDN Work | 2007-10-01 | 2007-12-26
Activity | 1PF1250W42A03.1T | (GEN Seal Oil Sys.) Transportation | 2008-01-31 | 2008-03-15
Activity | 1CF1250W42A04.1 | (GEN Seal Oil Sys.) Installation | 2008-03-17 | 2008-03-31
Activity | 1CF1250W58A05.1 | (GEN Seal Oil Sys.) Piping Work | 2008-04-01 | 2008-05-01
Activity | 1CF1250W74A06.1 | (GEN Seal Oil Sys.) Installation- Elec. | 2008-05-02 | 2008-05-15
Activity | 1CF1250W90A07.1 | (GEN Seal Oil Sys.) Installation- I&C | 2008-05-02 | 2008-05-15
Activity | 1SF1250W62A08.1 | (GEN Seal Oil Sys.) Oil Flushing | 2008-05-02 | 2008-05-06
Activity | 1SF1250W62A09.1 | (GEN Seal Oil Sys.) Loop chek | 2008-05-16 | 2008-05-18
Activity | 1SF1250W62A10.1 | (GEN Seal Oil Sys.) Function Test | 2008-05-19 | 2008-05-21
5 | GTG #11 Fuel Gas Supply System |  | 2007-03-01 | 2008-09-24
Activity | 1PF1265W42A13P | (TCA Cooler) P.O & Procurement | 2007-03-01 | 2008-02-29
Activity | 1PF1265W42A03P | (Gas Final Filter & Metering Skid) P.O & Procurement | 2007-03-01 | 2008-01-30
Activity | 1EF1265W16A01 | (Gas Final Filter & Metering Skid) FDN Design | 2007-03-01 | 2007-08-31
Activity | 1CF1265W16A02 | (Gas Final Filter & Metering Skid) FDN Work | 2007-09-01 | 2007-11-27
Activity | 1CF1265W16A12 | (TCA Cooler) FDN Work | 2007-10-01 | 2007-11-30
Activity | 1PF1265W42A04T | (Gas Final Filter & Metering Skid) Transportation | 2008-01-31 | 2008-03-15
Activity | 1PF1265W42A14T | (TCA Cooler) Transportation | 2008-03-01 | 2008-04-15
Activity | 1CF1265W42A05 | (Gas Final Filter & Metering Skid) Installation | 2008-03-17 | 2008-04-17
Activity | 1CF1265W42A15 | (TCA Cooler) Installation | 2008-04-16 | 2008-05-16
Activity | 1CF1265W58A06 | (FGSS) Piping Work(incl. Airblowing Test)_Power block Area | 2008-05-20 | 2008-07-04
Activity | 1CF1265W74A07 | (FGSS) Installation- Elec. | 2008-07-05 | 2008-07-18
Activity | 1CF1265W90A08 | (FGSS) Installation- I&C | 2008-07-05 | 2008-07-18
Activity | 1SF1265W62A09 | (FGSS) Loop chek | 2008-08-03 | 2008-08-12
Activity | 1SF1265W62A10.0 | (FGSS) Function Test | 2008-08-13 | 2008-08-17
Activity | 1SF1265W62A11.0 | (FGSS) Gas Receiving upto GT Final Control Valve | 2008-09-22 | 2008-09-24
5 | GTG #11 Washing & Drain System |  | 2007-03-01 | 2008-08-14
Activity | 1PF1265W42A02.0P | (Washing & Drain system Skid) P.O & Procurement | 2007-03-01 | 2008-02-29
Activity | 1CF1265W16A01 | (Washing & Drain system Skid) FDN Work | 2007-10-01 | 2007-11-30
Activity | 1PF1265W42A03.0T | (Washing & Drain system Skid) Transportation | 2008-03-01 | 2008-04-15
Activity | 1CF1265W42A04 | (Washing & Drain system Skid) Installation | 2008-04-16 | 2008-05-02
Activity | 1CF1265W58A05 | (Washing & Drain system Skid) Piping work | 2008-05-03 | 2008-06-03
Activity | 1CF1265W62A08 | (Washing & Drain system Skid) Flushing | 2008-06-04 | 2008-06-06
Activity | 1CF1265W74A06 | (Washing & Drain system Skid) Installation- Elec. | 2008-06-04 | 2008-06-17
Activity | 1CF1265W90A07 | (Washing & Drain system Skid) Installation- I&C | 2008-06-04 | 2008-06-17
Activity | 1SF1265W62A09.0 | (Washing & Drain system Skid) Loop chek | 2008-06-18 | 2008-06-22
Activity | 1SF1265W62A10 | (Washing & Drain system Skid) Function Test | 2008-06-23 | 2008-06-25
Activity | 1SF1265W62A11 | (Washing & Drain system Skid) Load(Running) Test | 2008-08-12 | 2008-08-14
5 | GTG #11 Fuel Oil Injection System |  | 2007-03-01 | 2008-09-02
Activity | 1PF1265W42A02.00P | (Fuel oil injection System) P.O & Procurement | 2007-03-01 | 2008-02-29
Activity | 1PF1265W42A09P | (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | 2007-03-01 | 2008-01-31
Activity | 1PF1265W42A16P | (Water injection System) P.O & Procurement | 2007-03-01 | 2008-01-31
Activity | 1CF1265W16A01.0 | (Fuel oil injection System) FDN Work | 2007-10-01 | 2007-11-30
Activity | 1CF1265W16A08 | (Fuel oil injection Pump & actuator) FDN Work | 2007-10-01 | 2007-11-30
Activity | 1CF1265W16A15 | (Water injection System) FDN Work | 2007-10-01 | 2007-11-30
Activity | 1PF1265W42A10T | (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | 2008-02-01 | 2008-03-17
Activity | 1PF1265W42A17T | (Water injection System) Transportation | 2008-02-01 | 2008-03-17
Activity | 1PF1265W42A03.00T | (Fuel oil injection System) Transportation | 2008-03-01 | 2008-04-15
Activity | 1CF1265W42A11 | (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | 2008-03-18 | 2008-04-01
Activity | 1CF1265W42A18 | (Water injection System) Installation | 2008-03-18 | 2008-04-01
Activity | 1CF1265W58A19 | (Water injection System) Piping work | 2008-04-02 | 2008-04-16
Activity | 1CF1265W42A04.0 | (Fuel oil injection System) Installation | 2008-04-16 | 2008-04-30
Activity | 1CF1265W74A20 | (Water injection System) Installation- Elec. | 2008-04-17 | 2008-04-30
Activity | 1CF1265W90A21 | (Water injection System) Installation- I&C | 2008-04-17 | 2008-04-30
Activity | 1SF1265W62A22 | (Water injection System) Loop chek | 2008-05-01 | 2008-05-05
Activity | 1CF1265W58A05.0 | (Fuel oil injection System) Piping work | 2008-05-05 | 2008-05-19
Activity | 1SF1265W62A23 | (Water injection System) Function Test | 2008-05-06 | 2008-05-08
Activity | 1CF1265W74A06.0 | (Fuel oil injection System) Installation- Elec. | 2008-05-20 | 2008-06-02
Activity | 1CF1265W90A07.0 | (Fuel oil injection System) Installation- I&C | 2008-05-20 | 2008-06-02
Activity | 1SF1265W62A12 | (Fuel oil injection System) Loop chek | 2008-06-03 | 2008-06-05
Activity | 1SF1265W62A24 | (Water injection System) Load Test | 2008-08-12 | 2008-08-13
Activity | 1SF1265W62A13 | (Fuel oil injection System) Function Test | 2008-08-15 | 2008-08-19
Activity | 1SF1265W62A14 | (Fuel oil injection System) Flushing | 2008-08-30 | 2008-09-02
5 | GTG #11 Vibration Monitoring System (VMS) |  | 2007-05-30 | 2008-08-12
Activity | 1EF1260W86A01 | (VMS) MPS Issue for GT |  | 2007-05-30
Activity | 1PF1260W86A02P | (VMS) P.O & Procurement for GT | 2007-08-31 | 2008-05-01
Activity | 1PF1260W86A03T | (VMS) Transportation for GT | 2008-05-02 | 2008-06-16
Activity | 1CF1260W86A04 | (VMS) Installation for GT | 2008-07-31 | 2008-08-07
Activity | 1SF1260W62A05 | (VMS) Function Test for GT | 2008-08-08 | 2008-08-12
5 | GTG #11 Closed Cooling Water System |  | 2007-03-01 | 2008-08-12
Activity | 1EF1225W00A01 | (CCWS) CCW H/EX key data | 2007-03-01 | 2007-05-01
Activity | 1EF1225W00A08 | (CCWP) Key data for GT | 2007-03-01 | 2007-05-01
Activity | 1EF1225W42A17 | (EXP Head Tank) MPS Issue |  | 2007-05-01
Activity | 1EF1225W00A11 | (CCWP) MPS Issue for GT |  | 2007-05-01
Activity | 1EF1225W42A04 | (CCW H/EX) MPS Issue_Fin fan cooler |  | 2007-05-01
Activity | 1PF1225W42A18P | (EXP Head Tank) P.O & Procurement | 2007-07-03 | 2008-03-31
Activity | 1EF1225W16A15 | (EXP Head Tank) FDN Design | 2007-07-03 | 2007-11-29
Activity | 1PF1225W42A12P | (CCWP) P.O & Procurement for GT | 2007-07-03 | 2008-03-31
Activity | 1EF1225W16A09 | (CCWP) FDN Design | 2007-07-03 | 2007-11-29
Activity | 1PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | 2007-07-03 | 2008-03-31
Activity | 1EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | 2007-07-03 | 2007-11-29
Activity | 1CF1225W16A16 | (EXP Head Tank) FDN Work | 2007-11-30 | 2007-12-28
Activity | 1CF1225W16A10 | (CCWP) FDN Work | 2007-11-30 | 2008-01-26
Activity | 1CF1225W16A03 | (CCW H/EX) FDN Work_Fin fan cooler | 2007-11-30 | 2008-02-25
Activity | 1PF1225W42A19T | (EXP Head Tank) Transportation | 2008-04-01 | 2008-05-15
Activity | 1PF1225W42A13T | (CCWP) Transportation for GT | 2008-04-01 | 2008-05-15
Activity | 1PF1225W42A06T | (CCW H/EX) Transportation_Fin fan cooler | 2008-04-01 | 2008-05-15
Activity | 1CF1225W58A21 | (CCWS) Piping Work | 2008-04-26 | 2008-06-30
Activity | 1CF1225W42A20 | (EXP Head Tank) Installation | 2008-05-16 | 2008-06-13
Activity | 1CF1225W42A14 | (CCWP) Installation | 2008-05-16 | 2008-05-30
Activity | 1CF1225W42A07 | (CCW H/EX) Installation_Fin fan cooler | 2008-05-16 | 2008-06-30
Activity | 1CF1225W74A22 | (CCWS) Installation & Test - Elec. | 2008-05-30 | 2008-06-30
Activity | 1CF1225W90A23 | (CCWS) Installation & Test - I&C | 2008-05-30 | 2008-06-30
Activity | 1SF1225W62A24 | (CCWS) Loop chek | 2008-07-01 | 2008-07-10
Activity | 1SF1225W62A25 | (CCWS) Function Test | 2008-07-11 | 2008-07-15
Activity | 1SF1225W62A26 | (CCWS) Flushing | 2008-08-08 | 2008-08-12
5 | GTG #11 Fire fighting System |  | 2007-03-01 | 2008-07-04
Activity | 1PF1265W38A01P | (F/F GTG#11) P.O & Procurement_CO2 FF System | 2007-03-01 | 2008-03-14
Activity | 1PF1265W38A04P | (F/F GTG#11) P.O & Procurement_Clean Agent FF System | 2007-03-01 | 2008-03-14
Activity | 1PF1265W38A02T | (F/F GTG#11) Transportation_CO2 FF System | 2008-03-15 | 2008-04-29
Activity | 1PF1265W38A05T | (F/F GTG#11) Transportation_Clean Agent FF System | 2008-03-15 | 2008-04-29
Activity | 1CF1265W38A03 | (F/F GTG#11) Installation_CO2 FF System | 2008-04-30 | 2008-05-14
Activity | 1CF1265W38A06 | (F/F GTG#11) Installation_Clean Agent FF System | 2008-04-30 | 2008-05-14
Activity | 1CF1265W38A07 | (F/F GTG#11) Piping work | 2008-05-15 | 2008-06-07
Activity | 1SF1265W62A08.2 | (F/F GTG#11) Loop chek | 2008-06-08 | 2008-06-14
Activity | 1SF1265W62A09.2 | (F/F GTG#11) Function Test(incl. Alarm Test) | 2008-06-15 | 2008-06-24
Activity | 1SF1265W62A10.2 | (F/F GTG#11) CO2 Discharge Test | 2008-06-25 | 2008-07-04
5 | GTG #11 Auxiliary System |  | 2007-03-01 | 2008-06-10
Activity | 1PF1265W42A02.3P | (Purge Air System) P.O & Procurement | 2007-03-01 | 2008-01-31
Activity | 1PF1265W42A12P | (Control Oil) P.O & Procurement | 2007-03-01 | 2008-01-31
Activity | 1CF1265W16A01.3 | (Purge Air System) FDN Work | 2007-10-01 | 2007-11-30
Activity | 1CF1265W16A11 | (Control Oil) FDN Work | 2007-10-01 | 2007-11-30
Activity | 1PF1265W42A03.3T | (Purge Air System) Transportation | 2008-02-01 | 2008-03-17
Activity | 1PF1265W42A13.0T | (Control Oil)Transportation | 2008-02-01 | 2008-03-17
Activity | 1CF1265W42A04.3 | (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | 2008-03-18 | 2008-04-01
Activity | 1CF1265W42A14 | (Control Oil) Installation | 2008-03-18 | 2008-04-01
Activity | 1CF1265W58A05.3 | (Purge Air System) Piping work | 2008-04-02 | 2008-04-16
Activity | 1CF1265W58A15 | (Control Oil) Piping work | 2008-04-02 | 2008-05-02
Activity | 1CF1265W74A06.3 | (Purge Air System) Installation- Elec. | 2008-04-17 | 2008-04-30
Activity | 1CF1265W90A07.3 | (Purge Air System) Installation- I&C | 2008-04-17 | 2008-04-30
Activity | 1SF1265W62A08.3 | (Purge Air System) Loop chek | 2008-05-01 | 2008-05-03
Activity | 1CF1265W74A16 | (Control Oil) Installation- Elec. | 2008-05-03 | 2008-05-16
Activity | 1CF1265W90A17 | (Control Oil) Installation- I&C | 2008-05-03 | 2008-05-16
Activity | 1SF1265W62A09.3 | (Purge Air System) Function Test | 2008-05-04 | 2008-05-06
Activity | 1SF1265W62A10.3 | (Purge Air System) Load Test | 2008-05-07 | 2008-05-09
Activity | 1SF1265W62A18 | (Control Oil) Loop chek | 2008-05-17 | 2008-05-21
Activity | 1SF1265W62A19 | (Control Oil) Function Test | 2008-05-22 | 2008-05-31
Activity | 1SF1265W62A20 | (Control Oil) Flushing | 2008-06-01 | 2008-06-10
5 | GTG #11 Commissioning |  | 2008-09-29 | 2008-11-27
Activity | 1SF9011W62A01 | (GTG #11) Fuel Gas System Final Function Test | 2008-09-29 | 2008-10-01
Activity | 1SF9011W62A02 | (GTG #11) Turning Gear Operation | 2008-10-02 | 2008-10-03
Activity | 1SF9011W62A03 | (GTG #11) Initial Firing with FSNL | 2008-10-04 | 2008-10-21
Activity | 1SF9012W62A04 | (GTG #11) TBN & GEN Protection Test | 2008-10-22 | 2008-10-23
Activity | 1SF9012W62A05 | (GTG #11) 1st Synchronization | 2008-10-24 | 2008-10-24
Activity | 1SF9012W62A06 | (GTG #11) Optimization with Fuel Gas | 2008-10-25 | 2008-10-30
Activity | 1SF9012W62A07 | (GTG #11) Fuel Oil System Final Function Test | 2008-10-31 | 2008-10-31
Activity | 1SF9012W62A08 | (GTG #11) Optimization with Fuel Oil | 2008-10-31 | 2008-10-31
Activity | 1SF9012W62A09 | (GTG #11) Black start Test with GT | 2008-10-31 | 2008-10-31
Activity | 1SF9012W62A10 | (GTG #11) Trial Run Test | 2008-11-01 | 2008-11-01
Activity | 1SF9013W62A11 | (GTG #11) Reliability Test | 2008-11-02 | 2008-11-16
Activity | 1SF9013W62A12 | (GTG #11) Performance Test (Fuel Gas & Fuel Oil) | 2008-11-17 | 2008-11-26
Activity | 1SF9012W62A13 | (GTG #11) Fuel Change-Over Test | 2008-11-27 | 2008-11-27
4 | GTG #12 |  | 2007-03-01 | 2008-11-29
5 | GTG #12 Main body |  | 2007-03-01 | 2008-08-15
Activity | 1PF1213W42A08.1P | (Gen #12) P.O & Procurement | 2007-03-01 | 2008-01-31
Activity | 1EF1213W16A06.1 | (Gen #12) FDN Design | 2007-03-01 | 2007-07-31
Activity | 1PF1213W42A03.1P | (GT #12) P.O & Procurement | 2007-03-01 | 2008-02-29
Activity | 1EF1213W16A01.1 | (GT #12) FDN Design | 2007-03-01 | 2007-07-31
Activity | 1CF1213W16A07.1 | (Gen #12) FDN Work | 2007-08-01 | 2007-12-15
Activity | 1CF1213W16A02.1 | (GT #12) FDN Work | 2007-08-01 | 2007-12-15
Activity | 1PF1213W42A09.1T | (Gen #12) Transportation | 2008-02-01 | 2008-03-17
Activity | 1PF1213W42A04.1T | (GT #12) Transportation | 2008-03-01 | 2008-04-14
Activity | 1CF1213W42A10.1 | (Gen #12) Installation | 2008-03-18 | 2008-07-18
Activity | 1CF1213W42A05.1 | (GT #12) Installation(On FDN~Final Alignment) | 2008-04-15 | 2008-08-15
Activity | 1CF1213W52A11.1 | (GT #12) Insulation | 2008-06-16 | 2008-06-30
5 | GTG #12 Electrical System |  | 2007-03-01 | 2008-09-26
Activity | 1PF1255W70A01.1P | (GTG#12 Electrical) P.O & Procurement | 2007-03-01 | 2008-03-31
Activity | 1PF1255W70A02.1T | (GTG#12 Electrical) Transportation | 2008-04-01 | 2008-05-15
Activity | 1CF1255W70A03.1 | (GTG#12 Electrical) Installation- PCC | 2008-08-01 | 2008-09-15
Activity | 1CF1255W70A04.1 | (GTG#12 Electrical) Installation- MCC | 2008-08-01 | 2008-09-15
Activity | 1CF1255W70A05.1 | (GTG#12 Electrical) Installation- Protection Sys. | 2008-08-01 | 2008-09-15
Activity | 1CF1255W70A07.1 | (GTG#12 Electrical) Installation- SEE&SFC Sys. | 2008-08-01 | 2008-09-15
Activity | 1CF1255W70A08.1 | (GTG#12 Electrical) Installation- DC&UPS Sys. | 2008-08-01 | 2008-09-15
Activity | 1CF1255W74A09.1 | (GTG#12 Electrical) Cable work | 2008-08-01 | 2008-09-15
Activity | 1CF1255W86A06.1 | (GTG#12 Electrical) Installation- GT control Sys. | 2008-08-04 | 2008-09-15
Activity | 1CF1255W62A10.1 | (GTG#12 Electrical) Electrical Function Test | 2008-09-16 | 2008-09-20
Activity | 1CF1255W62A11.1 | (GTG#12 Electrical) Loop Test | 2008-09-22 | 2008-09-26
5 | GTG #12 Starting System(Turning Device) |  | 2007-03-01 | 2008-05-28
Activity | 1PF1265W42A01.1P | (Turning Gear) P.O & Procurement | 2007-03-01 | 2008-02-29
Activity | 1PF1265W42A02.1T | (Turning Gear) Transportation | 2008-03-01 | 2008-04-15
Activity | 1CF1265W42A03.1 | (Turning Gear) Installation | 2008-04-16 | 2008-04-23
Activity | 1CF1265W74A04.1 | (Turning Gear) Installation- Elec. | 2008-04-24 | 2008-05-01
Activity | 1CF1265W90A05.1 | (Turning Gear) Installation- I&C | 2008-04-24 | 2008-05-01
Activity | 1SF1265W62A06.1 | (Turning Gear) Loop check | 2008-05-02 | 2008-05-06
Activity | 1SF1265W62A07.1 | (Turning Gear) Function Test | 2008-05-26 | 2008-05-28
5 | GTG #12 Air Intake System |  | 2007-03-01 | 2008-06-16
Activity | 1PF1230W20A02.1P | (Air Intake) P.O & Procurement_Steel Sturucture | 2007-03-01 | 2008-01-31
Activity | 1PF1230W64A05.1P | (Air Intake) P.O & Procurement_Inlet Duct | 2007-03-01 | 2008-01-31
Activity | 1PF1230W64A08.1P | (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2007-03-01 | 2008-01-31
Activity | 1CF1230W16A01.1 | (Air Intake) FDN Work_Steel Sturucture | 2007-10-01 | 2007-11-30
Activity | 1PF1230W20A03.1T | (Air Intake) Transportation_Steel Sturucture | 2008-02-01 | 2008-03-17
Activity | 1PF1230W64A06.1T | (Air Intake) Transportation_Inlet Duct | 2008-02-01 | 2008-03-17
Activity | 1PF1230W64A09.1T | (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-02-01 | 2008-03-17
Activity | 1CF1230W20A04.1 | (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | 2008-04-01 | 2008-04-17
Activity | 1CF1230W64A07.1 | (Air Intake) Installation_Inlet Duct | 2008-04-18 | 2008-04-25
Activity | 1CF1230W64A10.1 | (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-04-26 | 2008-05-20
Activity | 1CF1230W74A11.1 | (Air Intake) Installation- Elec. | 2008-05-21 | 2008-06-03
Activity | 1CF1230W90A12.1 | (Air Intake) Installation- I&C | 2008-05-21 | 2008-06-03
Activity | 1SF1230W62A13.1 | (Air Intake) Loop chek | 2008-06-04 | 2008-06-06
Activity | 1SF1230W62A14.1 | (Air Intake) Function Test | 2008-06-11 | 2008-06-13
Activity | 1SF1230W62A15.1 | (Air Intake) Load(Running) Test | 2008-06-14 | 2008-06-16
5 | GTG #12 Air and Flue Gas System |  | 2007-03-01 | 2008-05-19
Activity | 1PF1265W64A01.1P | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | 2007-03-01 | 2008-01-31
Activity | 1PF1265W64A02.1T | (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | 2008-02-01 | 2008-03-17
Activity | 1CF1265W64A03.1 | (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | 2008-03-18 | 2008-04-17
Activity | 1CF1265W64A04.1 | (Air&Flue Gas System) Duct work | 2008-04-18 | 2008-05-02
Activity | 1CF1265W74A06.1 | (Air&Flue Gas System) Installation- Elec. | 2008-05-03 | 2008-05-16
Activity | 1CF1265W90A07.1 | (Air&Flue Gas System) Installation- I&C | 2008-05-03 | 2008-05-16
Activity | 1SF1265W62A05.1 | (Air&Flue Gas System) Loop chek | 2008-05-14 | 2008-05-16
Activity | 1SF1265W62A08.1 | (Air&Flue Gas System) Function Test | 2008-05-17 | 2008-05-19
5 | GTG #12 Lube Oil System |  | 2007-03-01 | 2008-05-25
Activity | 1PF1250W42A10.2P | (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | 2007-03-01 | 2008-01-31
Activity | 1PF1250W42A02.2P | (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | 2007-03-01 | 2008-01-31
Activity | 1PF1250W42A06.2P | (Lube Oil System) P.O & Procurement_Lube oil functional Module | 2007-03-01 | 2008-01-31
Activity | 1CF1250W16A05.2 | (Lube Oil System) FDN Work_Lube oil functional Module | 2007-10-01 | 2007-11-30
Activity | 1CF1250W16A09.2 | (Lube Oil System) FDN Work_Lube oil Mist Separator | 2007-10-01 | 2007-11-30
Activity | 1CF1250W16A01.2 | (Lube Oil System) FDN Work_Lube Oil Supply Module | 2007-10-01 | 2007-11-30
Activity | 1PF1250W42A07.2T | (Lube Oil System) Transportation_Lube oil functional Module | 2008-02-01 | 2008-03-17
Activity | 1PF1250W42A11.2T | (Lube Oil System) Transportation_Lube oil Mist Separator | 2008-02-01 | 2008-03-17
Activity | 1PF1250W42A03.2T | (Lube Oil System) Transportation_Lube Oil Supply Module | 2008-02-01 | 2008-03-17
Activity | 1CF1250W42A08.2 | (Lube Oil System) Installation_Lube oil functional Module | 2008-03-18 | 2008-04-02
Activity | 1CF1250W42A12.2 | (Lube Oil System) Installation_Lube oil Mist Separator | 2008-03-18 | 2008-03-25
Activity | 1CF1250W42A04.2 | (Lube Oil System) Installation_Lube Oil Supply Module | 2008-03-18 | 2008-04-02
Activity | 1CF1250W58A13.2 | (Lube Oil System) Piping work | 2008-04-03 | 2008-05-03
Activity | 1CF1250W62A16.2 | (GTG #12) Lube Oil Flushing | 2008-05-03 | 2008-05-20
Activity | 1CF1250W74A14.2 | (Lube Oil System) Installation- Elec. | 2008-05-05 | 2008-05-17
Activity | 1CF1250W90A15.2 | (Lube Oil System) Installation- I&C | 2008-05-05 | 2008-05-17
Activity | 1SF1250W62A17.2 | (Lube Oil System) Loop chek | 2008-05-18 | 2008-05-20
Activity | 1SF1250W62A18.2 | (Lube Oil System) Function Test | 2008-05-21 | 2008-05-23
Activity | 1SF1250W62A19.2 | (Lube Oil System) Load Test | 2008-05-24 | 2008-05-25
5 | GTG #12 Generator Seal Oil System |  | 2007-03-01 | 2008-05-22
Activity | 1PF1250W42A02.3P | (GEN Seal Oil Sys.) P.O & Procurement | 2007-03-01 | 2008-01-31
Activity | 1CF1250W16A01.3 | (GEN Seal Oil Sys.) FDN Work | 2007-10-01 | 2007-12-26
Activity | 1PF1250W42A03.3T | (GEN Seal Oil Sys.) Transportation | 2008-02-01 | 2008-03-17
Activity | 1CF1250W42A04.3 | (GEN Seal Oil Sys.) Installation | 2008-03-18 | 2008-04-01
Activity | 1CF1250W58A05.3 | (GEN Seal Oil Sys.) Piping Work | 2008-04-02 | 2008-05-02
Activity | 1CF1250W74A07.3 | (GEN Seal Oil Sys.) Installation- Elec. | 2008-05-03 | 2008-05-16
Activity | 1CF1250W90A08.3 | (GEN Seal Oil Sys.) Installation- I&C | 2008-05-03 | 2008-05-16
Activity | 1SF1250W62A06.3 | (GEN Seal Oil Sys.) Oil Flushing | 2008-05-03 | 2008-05-07
Activity | 1SF1250W62A09.3 | (GEN Seal Oil Sys.) Loop chek | 2008-05-17 | 2008-05-19
Activity | 1SF1250W62A10.3 | (GEN Seal Oil Sys.) Function Test | 2008-05-20 | 2008-05-22
5 | GTG #12 Fuel Gas Supply System |  | 2007-03-01 | 2008-09-24
Activity | 1PF1265W42A13.4P | (TCA Cooler) P.O & Procurement | 2007-03-01 | 2008-02-29
Activity | 1PF1265W42A03.4P | (Gas Final Filter & Metering Skid) P.O & Procurement | 2007-03-01 | 2008-01-31
Activity | 1EF1265W16A01.4 | (Gas Final Filter & Metering Skid) FDN Design | 2007-03-01 | 2007-08-31
Activity | 1CF1265W16A02.4 | (Gas Final Filter & Metering Skid) FDN Work | 2007-09-01 | 2007-11-27
Activity | 1CF1265W16A12.4 | (TCA Cooler) FDN Work | 2007-10-01 | 2007-11-30
Activity | 1PF1265W42A04.4T | (Gas Final Filter & Metering Skid) Transportation | 2008-02-01 | 2008-03-17
Activity | 1PF1265W42A14.4T | (TCA Cooler) Transportation | 2008-03-01 | 2008-04-15
Activity | 1CF1265W42A05.4 | (Gas Final Filter & Metering Skid) Installation | 2008-03-18 | 2008-04-01
Activity | 1CF1265W42A15.4 | (TCA Cooler) Installation | 2008-04-16 | 2008-04-30
Activity | 1CF1265W58A06.4 | (FGSS) Piping Work(incl. Airblowing Test)_Power Block Area | 2008-05-20 | 2008-06-19
Activity | 1CF1265W74A07.4 | (FGSS) Installation- Elec. | 2008-06-20 | 2008-07-03
Activity | 1CF1265W90A08.4 | (FGSS) Installation- I&C | 2008-06-20 | 2008-07-03
Activity | 1SF1265W62A09.4 | (FGSS) Loop chek | 2008-08-03 | 2008-08-12
Activity | 1SF1265W62A10.4 | (FGSS) Function Test | 2008-08-13 | 2008-08-17
Activity | 1SF1265W62A11.4 | (FGSS) Gas Receiving upto GT Final Control Valve | 2008-09-22 | 2008-09-24
5 | GTG #12 Washing & Drain System |  | 2007-03-01 | 2008-08-14
Activity | 1PF1265W42A02.5P | (Washing & Drain system Skid) P.O & Procurement | 2007-03-01 | 2008-02-29
Activity | 1CF1265W16A01.5 | (Washing & Drain system Skid) FDN Work | 2007-10-01 | 2007-11-30
Activity | 1PF1265W42A03.5T | (Washing & Drain system Skid) Transportation | 2008-03-01 | 2008-04-15
Activity | 1CF1265W42A04.5 | (Washing & Drain system Skid) Installation | 2008-04-16 | 2008-05-02
Activity | 1CF1265W58A05.5 | (Washing & Drain system Skid) Piping work | 2008-05-03 | 2008-06-03
Activity | 1CF1265W74A07.5 | (Washing & Drain system Skid) Installation- Elec. | 2008-06-04 | 2008-06-17
Activity | 1CF1265W90A08.5 | (Washing & Drain system Skid) Installation- I&C | 2008-06-04 | 2008-06-17
Activity | 1CF1265W62A06.5 | (Washing & Drain system Skid) Flushing | 2008-06-04 | 2008-06-06
Activity | 1SF1265W62A09.5 | (Washing & Drain system Skid) Loop chek | 2008-06-18 | 2008-06-22
Activity | 1SF1265W62A10.5 | (Washing & Drain system Skid) Function Test | 2008-06-23 | 2008-06-25
Activity | 1SF1265W62A11.5 | (Washing & Drain system Skid) Load(Running) Test | 2008-08-12 | 2008-08-14
5 | GTG #12 Fuel Oil Injection System |  | 2007-03-01 | 2008-09-02
Activity | 1PF1265W42A02.6P | (Fuel oil injection System) P.O & Procurement | 2007-03-01 | 2008-02-29
Activity | 1PF1265W42A12.6P | (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | 2007-03-01 | 2008-01-31
Activity | 1PF1265W42A15.6P | (Water injection System) P.O & Procurement | 2007-03-01 | 2008-01-31
Activity | 1CF1265W16A01.6 | (Fuel oil injection System) FDN Work | 2007-10-01 | 2007-11-30
Activity | 1CF1265W16A11.6 | (Fuel oil injection Pump & actuator) FDN Work | 2007-10-01 | 2007-11-30
Activity | 1CF1265W16A15.6 | (Water injection System) FDN Work | 2007-10-01 | 2007-11-30
Activity | 1PF1265W42A13.6T | (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | 2008-02-01 | 2008-03-17
Activity | 1PF1265W42A16.6T | (Water injection System) Transportation | 2008-02-01 | 2008-03-17
Activity | 1PF1265W42A03.6T | (Fuel oil injection System) Transportation | 2008-03-01 | 2008-04-15
Activity | 1CF1265W42A14.6 | (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | 2008-03-18 | 2008-04-01
Activity | 1CF1265W42A17.6 | (Water injection System) Installation | 2008-03-18 | 2008-04-01
Activity | 1CF1265W58A18.6 | (Water injection System) Piping work | 2008-04-02 | 2008-04-16
Activity | 1CF1265W42A04.6 | (Fuel oil injection System) Installation | 2008-04-16 | 2008-04-30
Activity | 1CF1265W74A19.6 | (Water injection System) Installation- Elec. | 2008-04-17 | 2008-04-30
Activity | 1CF1265W90A20.6 | (Water injection System) Installation- I&C | 2008-04-17 | 2008-04-30
Activity | 1SF1265W62A21.6 | (Water injection System) Loop chek | 2008-05-01 | 2008-05-05
Activity | 1CF1265W58A05.6 | (Fuel oil injection System) Piping work | 2008-05-05 | 2008-05-19
Activity | 1SF1265W62A22.6 | (Water injection System) Function Test | 2008-05-06 | 2008-05-08
Activity | 1CF1265W74A06.6 | (Fuel oil injection System) Installation- Elec. | 2008-05-20 | 2008-06-02
Activity | 1CF1265W90A07.6 | (Fuel oil injection System) Installation- I&C | 2008-05-20 | 2008-06-02
Activity | 1SF1265W62A08.6 | (Fuel oil injection System) Loop chek | 2008-06-03 | 2008-06-05
Activity | 1SF1265W62A23.6 | (Water injection System) Load Test | 2008-08-12 | 2008-08-13
Activity | 1SF1265W62A09.6 | (Fuel oil injection System) Function Test | 2008-08-15 | 2008-08-19
Activity | 1SF1265W62A10.6 | (Fuel oil injection System) Flushing | 2008-08-30 | 2008-09-02
5 | GTG #12 Vibration Monitoring System (VMS) |  | 2007-05-30 | 2008-08-28
Activity | 1EF1260W86A01.1 | (VMS) MPS Issue for GT |  | 2007-05-30
Activity | 1PF1260W86A02.1P | (VMS) P.O & Procurement for GT | 2007-08-31 | 2008-05-01
Activity | 1PF1260W86A03.1T | (VMS) Transportation for GT | 2008-05-02 | 2008-06-16
Activity | 1CF1260W86A04.1 | (VMS) Installation for GT | 2008-08-16 | 2008-08-23
Activity | 1SF1260W62A05.1 | (VMS) Function Test for GT | 2008-08-24 | 2008-08-28
5 | GTG #12 Closed Cooling Water System |  | 2007-03-01 | 2008-08-12
Activity | 1EF1225W00A01.1 | (CCWS) CCW H/EX key data | 2007-03-01 | 2007-05-01
Activity | 1EF1225W00A02.1 | (CCWP) Key data for GT | 2007-03-01 | 2007-05-01
Activity | 1EF1225W42A11.1 | (EXP Head Tank) MPS Issue |  | 2007-05-01
Activity | 1EF1225W42A05.1 | (CCWP) MPS Issue for GT |  | 2007-05-01
Activity | 1EF1225W42A17.1 | (CCW H/EX) MPS Issue_Fin fan cooler |  | 2007-05-01
Activity | 1PF1225W42A12.1P | (EXP Head Tank) P.O & Procurement | 2007-07-03 | 2008-03-31
Activity | 1EF1225W16A09.1 | (EXP Head Tank) FDN Design | 2007-07-03 | 2007-11-29
Activity | 1PF1225W42A06.1P | (CCWP) P.O & Procurement for GT | 2007-07-03 | 2008-03-31
Activity | 1EF1225W16A03.1 | (CCWP) FDN Design | 2007-07-03 | 2007-11-29
Activity | 1PF1225W42A18.1P | (CCW H/EX) P.O & Procurement_Fin fan cooler | 2007-07-03 | 2008-03-31
Activity | 1EF1225W16A15.1 | (CCW H/EX) FDN Design_Fin fan cooler | 2007-07-03 | 2007-11-29
Activity | 1CF1225W16A10.1 | (EXP Head Tank) FDN Work | 2007-11-30 | 2007-12-28
Activity | 1CF1225W16A04.1 | (CCWP) FDN Work | 2007-11-30 | 2008-01-26
Activity | 1CF1225W16A16.1 | (CCW H/EX) FDN Work_Fin fan cooler | 2007-11-30 | 2008-02-25
Activity | 1PF1225W42A13.1T | (EXP Head Tank) Transportation | 2008-04-01 | 2008-05-15
Activity | 1PF1225W42A07.1T | (CCWP) Transportation for GT | 2008-04-01 | 2008-05-15
Activity | 1PF1225W42A19.1T | (CCW H/EX) Transportation_Fin fan cooler | 2008-04-01 | 2008-05-15
Activity | 1CF1225W58A21.1 | (CCWS) Piping Work | 2008-05-09 | 2008-06-30
Activity | 1CF1225W42A14.1 | (EXP Head Tank) Installation | 2008-05-16 | 2008-06-13
Activity | 1CF1225W42A08.1 | (CCWP) Installation | 2008-05-16 | 2008-05-30
Activity | 1CF1225W42A20.1 | (CCW H/EX) Installation_Fin fan cooler | 2008-05-16 | 2008-06-30
Activity | 1CF1225W74A22.1 | (CCWS) Installation & Test - Elec. | 2008-05-30 | 2008-06-30
Activity | 1CF1225W90A23.1 | (CCWS) Installation & Test - I&C | 2008-05-30 | 2008-06-30
Activity | 1SF1225W62A24.1 | (CCWS) Loop chek | 2008-07-01 | 2008-07-10
Activity | 1SF1225W62A25.1 | (CCWS) Function Test | 2008-07-11 | 2008-07-15
Activity | 1SF1225W62A26.1 | (CCWS) Flushing | 2008-08-08 | 2008-08-12
5 | GTG #12 Fire fighting System |  | 2007-03-01 | 2008-07-04
Activity | 1PF1265W38A01.7P | (F/F GTG#12) P.O & Procurement_CO2 FF System | 2007-03-01 | 2008-03-14
Activity | 1PF1265W38A04.7P | (F/F GTG#12) P.O & Procurement_Clean Agent FF System | 2007-03-01 | 2008-03-14
Activity | 1PF1265W38A02.7T | (F/F GTG#12) Transportation_CO2 FF System | 2008-03-15 | 2008-04-29
Activity | 1PF1265W38A05.7T | (F/F GTG#12) Transportation_Clean Agent FF System | 2008-03-15 | 2008-04-29
Activity | 1CF1265W38A03.7 | (F/F GTG#12) Installation_CO2 FF System | 2008-04-30 | 2008-05-14
Activity | 1CF1265W38A06.7 | (F/F GTG#12) Installation_Clean Agent FF System | 2008-04-30 | 2008-05-14
Activity | 1CF1265W38A07.7 | (F/F GTG#12) Piping work | 2008-05-15 | 2008-06-07
Activity | 1SF1265W62A08.7 | (F/F GTG#12) Loop chek | 2008-06-08 | 2008-06-14
Activity | 1SF1265W62A09.7 | (F/F GTG#12) Function Test(incl. Alarm Test) | 2008-06-15 | 2008-06-24
Activity | 1SF1265W62A10.7 | (F/F GTG#12) CO2 Discharge Test | 2008-06-25 | 2008-07-04
5 | GTG #12 Auxiliary System |  | 2007-03-01 | 2008-06-10
Activity | 1PF1265W42A02.8P | (Purge Air System) P.O & Procurement | 2007-03-01 | 2008-01-31
Activity | 1PF1265W42A12.8P | (Control Oil) P.O & Procurement | 2007-03-01 | 2008-01-31
Activity | 1CF1265W16A01.8 | (Purge Air System) FDN Work | 2007-10-01 | 2007-11-30
Activity | 1CF1265W16A11.8 | (Control Oil) FDN Work | 2007-10-01 | 2007-11-30
Activity | 1PF1265W42A03.8T | (Purge Air System) Transportation | 2008-02-01 | 2008-03-17
Activity | 1PF1265W42A13.8T | (Control Oil)Transportation | 2008-02-01 | 2008-03-17
Activity | 1CF1265W42A04.8 | (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | 2008-03-18 | 2008-04-01
Activity | 1CF1265W42A14.8 | (Control Oil) Installation | 2008-03-18 | 2008-04-01
Activity | 1CF1265W16A05.8 | (Purge Air System) Piping work | 2008-04-02 | 2008-04-16
Activity | 1CF1265W16A15.8 | (Control Oil) Piping work | 2008-04-02 | 2008-05-02
Activity | 1CF1265W74A06.8 | (Purge Air System) Installation- Elec. | 2008-04-17 | 2008-04-30
Activity | 1CF1265W90A07.8 | (Purge Air System) Installation- I&C | 2008-04-17 | 2008-04-30
Activity | 1SF1265W62A08.8 | (Purge Air System) Loop chek | 2008-05-01 | 2008-05-03
Activity | 1CF1265W74A16.8 | (Control Oil) Installation- Elec. | 2008-05-03 | 2008-05-16
Activity | 1CF1265W90A17.8 | (Control Oil) Installation- I&C | 2008-05-03 | 2008-05-16
Activity | 1SF1265W62A09.8 | (Purge Air System) Function Test | 2008-05-04 | 2008-05-06
Activity | 1SF1265W62A10.8 | (Purge Air System) Load Test | 2008-05-07 | 2008-05-09
Activity | 1SF1265W62A18.8 | (Control Oil) Loop chek | 2008-05-17 | 2008-05-21
Activity | 1SF1265W62A19.8 | (Control Oil) Function Test | 2008-05-22 | 2008-05-31
Activity | 1SF1265W62A20.8 | (Control Oil) Flushing | 2008-06-01 | 2008-06-10
5 | GTG #12 Commissioning |  | 2008-09-29 | 2008-11-29
Activity | 1SF9011W62A01.1 | (GTG #12) Fuel Gas System Final Function Test | 2008-09-29 | 2008-10-01
Activity | 1SF9011W62A02.1 | (GTG #12) Turning Gear Operation | 2008-10-02 | 2008-10-03
Activity | 1SF9011W62A03.1 | (GTG #12) Initial Firing with FSNL | 2008-10-04 | 2008-10-04
Activity | 1SF9012W62A04.1 | (GTG #12) TBN & GEN Protection Test | 2008-10-05 | 2008-10-12
Activity | 1SF9012W62A05.1 | (GTG #12) 1st Synchronization | 2008-10-13 | 2008-10-14
Activity | 1SF9012W62A06.1 | (GTG #12) Optimization with Fuel Gas | 2008-10-15 | 2008-10-20
Activity | 1SF9012W62A09.1 | (GTG #12) Black start Test with GT | 2008-10-21 | 2008-10-21
Activity | 1SF9012W62A07.1 | (GTG #12) Fuel Oil System Final Function Test | 2008-10-21 | 2008-10-21
Activity | 1SF9012W62A08.1 | (GTG #12) Optimization with Fuel Oil | 2008-10-21 | 2008-10-21
Activity | 1SF9012W62A10.1 | (GTG #12) Trial Run Test | 2008-10-22 | 2008-10-22
Activity | 1SF9013W62A11.1 | (GTG #12) Reliability Test | 2008-10-23 | 2008-11-06
Activity | 1SF9013W62A12.1 | (GTG #12) Performance Test (Fuel Gas & Fuel Oil) | 2008-11-07 | 2008-11-16
Activity | 1SF9012W62A13.1 | (GTG #12) Fuel Change-Over Test | 2008-11-17 | 2008-11-29
3 | HRSG #11 & #12 |  | 2007-03-01 | 2009-03-26
4 | HRSG Common |  | 2007-03-01 | 2008-03-05
Activity | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | 2007-03-01 | 2007-03-30
Activity | 1EF1600W00A03 | (HRSG #11/#12) Instrument, Service Air Data | 2007-03-01 | 2007-03-29
Activity | 1EF1600W00A04 | (HRSG #11/#12) Utility Consumption Data | 2007-03-01 | 2007-04-26
Activity | 1EF1600W00A05 | (HRSG #11/#12) Emergency Load Data | 2007-03-01 | 2007-04-16
Activity | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | 2007-03-19 | 2008-03-05
4 | HRSG #11 |  | 2007-04-17 | 2009-03-25
5 | HRSG LEB |  | 2007-06-15 | 2008-12-15
Activity | 1EF1600W74A05 | (HRSG #11 LEB) MPS Issue - Elec |  | 2007-06-15
Activity | 1EF1600W90A09 | (HRSG #11 LEB) MPS Issue - I&C |  | 2007-06-15
Activity | 1EF1600W00A01 | (HRSG #11 LEB) GA & Load Data to Civil Design | 2007-06-20
Activity | 1EF1600W32A02 | (HRSG #11 LEB) Building Design | 2007-06-20 | 2007-11-20
Activity | 1PF1600W74A06P | (HRSG #11 LEB) P.O & Procurement - Elec | 2007-09-15 | 2008-07-10
Activity | 1PF1600W90A10P | (HRSG #11 LEB) P.O & Procurement - I&C | 2007-09-15 | 2008-07-10
Activity | 1CF1600W16A03 | (HRSG #11 LEB) FDN Work | 2008-01-01 | 2008-02-27
Activity | 1CF1600W32A04 | (HRSG #11 LEB) Structure Work | 2008-02-28 | 2008-05-24
Activity | 1PF1600W74A07T | (HRSG #11 LEB) Transportataion - Elec | 2008-07-11 | 2008-08-24
Activity | 1PF1600W90A11T | (HRSG #11 LEB) Transportataion - I&C | 2008-07-11 | 2008-08-24
Activity | 1CF1600W36A14 | (HRSG #11 LEB) Installation & Test - HVAC | 2008-07-31 | 2008-09-13
Activity | 1CF1600W74A08 | (HRSG #11 LEB) Installation & Test - Elec | 2008-10-20 | 2008-12-15
Activity | 1CF1600W90A12 | (HRSG #11 LEB) Installation & Test - I&C | 2008-10-20 | 2008-12-15
Activity | 1CF1600W38A13 | (HRSG #11 LEB) Installation & Test - Fire Fighting Sys. | 2008-11-01 | 2008-12-15
5 | Steel Structure & Casing |  | 2007-04-18 | 2008-07-15
Activity | 1EF1610W20A01 | (HRSG #11 S/Structure & Casing) Design | 2007-04-18 | 2007-11-14
Activity | 1EF1610W20A02 | (HRSG #11 S/Structure & Casing) MPS Issue |  | 2007-05-15
Activity | 1PF1610W20A03P | (HRSG #11 S/Structure & Casing) P.O & Procurement | 2007-06-14 | 2008-01-01
Activity | 1PF1610W20A04T | (HRSG #11 S/Structure & Casing) Transportation | 2008-01-02 | 2008-02-15
Activity | 1CF1610W20A05 | (HRSG #11 S/Structure & Casing) S/Structure Installation | 2008-03-17 | 2008-05-16
Activity | 1CF1610W20A06 | (HRSG #11 S/Structure & Casing) Casing Installation | 2008-05-17 | 2008-07-15
5 | Duct |  | 2007-04-17 | 2009-01-02
Activity | 1EF1615W64A04 | (HRSG #11 Duct) Design | 2007-04-17 | 2007-10-18
Activity | 1EF1615W64A13 | (HRSG #11 EXP Joint & Bellows) MPS Issue |  | 2007-04-25
Activity | 1EF1615W64A09 | (HRSG #11 Damper) MPS Issue |  | 2007-04-25
Activity | 1EF1615W00A01 | (HRSG #11 Duct) GA & Load Data to Civil Design | 2007-04-30
Activity | 1EF1615W64A05 | (HRSG #11 Duct) MPS Issue |  | 2007-05-15
Activity | 1PF1615W64A14P | (HRSG #11 EXP Joint & Bellows) P.O & Procurement | 2007-06-13 | 2008-03-31
Activity | 1PF1615W64A10P | (HRSG #11 Damper) P.O & Procurement | 2007-06-13 | 2008-02-29
Activity | 1PF1615W64A06P | (HRSG #11 Duct) P.O & Procurement | 2007-06-14 | 2008-01-31
Activity | 1EF1615W16A02 | (HRSG #11 Duct) FDN Design | 2007-08-02 | 2007-12-13
Activity | 1CF1615W16A03 | (HRSG #11 Duct) FDN Work | 2007-12-14 | 2008-03-15
Activity | 1PF1615W64A07T | (HRSG #11 Duct) Transportation | 2008-02-01 | 2008-03-17
Activity | 1PF1615W64A11T | (HRSG #11 Damper) Transportation | 2008-03-01 | 2008-04-15
Activity | 1PF1615W64A15T | (HRSG #11 EXP Joint & Bellows) Transportation | 2008-04-01 | 2008-05-15
Activity | 1CF1615W64A12 | (HRSG #11 Damper) Installation | 2008-04-16 | 2008-06-16
Activity | 1CF1615W64A17 | (HRSG #11) Installation_Diverter Damper | 2008-05-03 | 2008-05-27
Activity | 1CF1615W64A20 | (HRSG #11) Installation_Guillotine Damper | 2008-05-28 | 2008-06-20
Activity | 1CF1615W86A18 | (HRSG #11) Installation_Diverter Damper Control Unit | 2008-05-28 | 2008-06-07
Activity | 1CF1615W62A19 | (HRSG #11) Diverter Damper Control Unit Flushing | 2008-06-09 | 2008-06-25
Activity | 1SF1615W62A21 | (HRSG #11) Diverter Damper Function Test for GT #11 | 2008-08-05 | 2008-08-08
Activity | 1SF1615W62A22 | (HRSG #11) Guillotine Damper Function Test for GT #11 | 2008-08-05 | 2008-08-08
Activity | 1CF1615W64A08 | (HRSG #11 Duct) Duct Installation | 2008-09-16 | 2008-12-16
Activity | 1CF1615W64A16 | (HRSG #11 EXP Joint & Bellows) Installation | 2008-11-19 | 2009-01-02
5 | Module |  | 2007-06-01 | 2008-09-15
Activity | 1EF1610W42A01 | (HRSG #11 Module) MPS Issue |  | 2007-06-01
Activity | 1PF1610W42A02P | (HRSG #11 Module) P.O & Procurement | 2007-07-03 | 2008-03-03
Activity | 1PF1610W42A03T | (HRSG #11 Module) Transportation | 2008-03-04 | 2008-04-17
Activity | 1CF1610W42A04 | (HRSG #11 Module) Installation | 2008-07-16 | 2008-09-15
5 | Drum |  | 2007-04-17 | 2008-10-14
Activity | 1EF1645W42A01 | (HRSG #11 Drum) Design | 2007-04-17 | 2007-11-07
Activity | 1EF1645W42A02 | (HRSG #11 Drum) MPS Issue | 2007-05-15
Activity | 1PF1645W42A03P | (HRSG #11 Drum) P.O & Procurement | 2007-06-13 | 2008-04-30
Activity | 1PF1645W42A04T | (HRSG #11 Drum) Transportation | 2008-05-01 | 2008-06-14
Activity | 1CF1645W42A05 | (HRSG #11 Drum) Installation | 2008-09-16 | 2008-10-14
5 | Bypass Stack |  | 2007-04-17 | 2008-07-02
Activity | 1EF1625W42A04 | (HRSG #11 Bypass Stack) Design | 2007-04-17 | 2007-10-29
Activity | 1EF1625W42A09 | (HRSG #11 Bypass Stack Silencer) MPS Issue |  | 2007-04-25
Activity | 1EF1625W42A05 | (HRSG #11 Bypass Stack) MPS Issue |  | 2007-05-15
Activity | 1EF1625W00A01 | (HRSG #11 Bypass Stack) GA & Load Data to Civil Design | 2007-05-31
Activity | 1PF1625W42A10P | (HRSG #11 Bypass Stack Silencer) P.O & Procurement | 2007-06-13 | 2008-03-31
Activity | 1PF1625W42A06P | (HRSG #11 Bypass Stack) P.O & Procurement | 2007-07-03 | 2008-01-30
Activity | 1EF1625W16A02 | (HRSG #11 Bypass Stack) FDN Design | 2007-09-04 | 2008-01-11
Activity | 1CF1625W16A03 | (HRSG #11 Bypass Stack) FDN Work | 2008-01-11 | 2008-03-31
Activity | 1PF1625W42A07T | (HRSG #11 Bypass Stack) Transportation | 2008-01-31 | 2008-03-15
Activity | 1CF1625W42A08 | (HRSG #11 Bypass Stack) Installation | 2008-03-31 | 2008-07-02
Activity | 1PF1625W42A11T | (HRSG #11 Bypass Stack Silencer) Transportation | 2008-04-01 | 2008-05-15
Activity | 1CF1625W42A12 | (HRSG #11 Bypass Stack Silencer) Installation | 2008-05-31 | 2008-06-30
5 | Main Stack |  | 2007-04-17 | 2009-02-18
Activity | 1EF1625W42A05.0 | (HRSG #11 Main Stack) MPS Issue |  | 2007-04-17
Activity | 1EF1625W42A01 | (HRSG #11 Main Stack) Design | 2007-04-17 | 2007-10-29
Activity | 1EF1625W42A09.0 | (HRSG #11 Main Stack Silencer) MPS Issue |  | 2007-04-25
Activity | 1PF1625W42A06.0P | (HRSG #11 Main Stack) P.O & Procurement | 2007-06-04 | 2008-01-31
Activity | 1EF1625W00A02 | (HRSG #11 Main Stack) GA & Load Data to Civil Design | 2007-06-05
Activity | 1PF1625W42A10.0P | (HRSG #11 Main Stack Silencer) P.O & Procurement | 2007-07-27 | 2008-05-14
Activity | 1EF1625W16A03 | (HRSG #11 Main Stack) FDN Design | 2007-09-07 | 2008-01-16
Activity | 1CF1625W16A04 | (HRSG #11 Main Stack) FDN Work | 2008-01-16 | 2008-04-18
Activity | 1PF1625W42A07.0T | (HRSG #11 Main Stack) Transportation | 2008-02-01 | 2008-03-17
Activity | 1PF1625W42A11.0T | (HRSG #11 Main Stack Silencer) Transportation | 2008-05-15 | 2008-06-28
Activity | 1CF1625W42A08.0 | (HRSG #11 Main Stack) Installation | 2008-11-13 | 2009-02-10
Activity | 1CF1625W42A12.0 | (HRSG #11 Main Stack Silencer) Installation | 2009-01-21 | 2009-02-18
5 | Piping Work |  | 2007-11-21 | 2009-02-18
Activity | 1EF1650W52A01 | (HRSG #11 Insulation) MPS Issue |  | 2007-11-21
Activity | 1PF1650W52A02P | (HRSG #11 Insulation) P.O & Procurement | 2008-01-09 | 2008-09-30
Activity | 1CF1640W58A05 | (HRSG #11) Piping Work | 2008-09-30 | 2008-12-31
Activity | 1PF1650W52A03T | (HRSG #11 Insulation) Transportation | 2008-10-01 | 2008-11-14
Activity | 1CF1640W62A06 | (HRSG #11) Hydro Test | 2009-01-01 | 2009-01-24
Activity | 1CF1650W52A04 | (HRSG #11 Insulation) Installation | 2009-01-15 | 2009-02-18
Activity | 1CF1640W60A07 | (HRSG #11) Acid Cleaning | 2009-01-26 | 2009-02-17
5 | CEMS |  | 2007-05-31 | 2008-08-10
Activity | 1EF1660W86A03 | (CEMS) MPS Issue |  | 2007-05-31
Activity | 1PF1660W86A04P | (CEMS) P.O & Procurement | 2007-08-29 | 2008-03-31
Activity | 1EF1660W16A01 | (CEMS) FDN Design | 2007-10-30 | 2008-01-25
Activity | 1CF1660W16A02 | (CEMS) FDN Work | 2008-01-26 | 2008-03-24
Activity | 1PF1660W86A05T | (CEMS) Transportation | 2008-04-01 | 2008-05-15
Activity | 1CF1660W86A06 | (CEMS) Installation(incl. Elec, I&C) | 2008-05-16 | 2008-05-31
Activity | 1CF1660W62A07 | (CEMS) Loop Test | 2008-06-02 | 2008-06-06
Activity | 1SF1615W62A08 | (HRSG #11) CEMS Function Test for GT #11(Bypass stack) | 2008-08-05 | 2008-08-10
5 | Auxiliary System |  | 2007-06-15 | 2009-01-28
Activity | 1EF1660W70A05 | (HRSG #11 ELEC Vendor Equip) MPS Issue |  | 2007-06-15
Activity | 1EF1660W86A10 | (HRSG #11 I&C Vendor Equip) MPS Issue |  | 2007-06-15
Activity | 1EF1665W42A01 | (HRSG #11 MECH Vendor Equip) MPS Issue |  | 2007-06-28
Activity | 1PF1665W42A02P | (HRSG #11 MECH Vendor Equip) P.O & Procurement | 2007-09-10 | 2008-08-01
Activity | 1PF1660W70A06P | (HRSG #11 ELEC Vendor Equip) P.O & Procurement | 2007-10-02 | 2008-08-04
Activity | 1PF1660W86A11P | (HRSG #11 I&C Vendor Equip) P.O & Procurement | 2007-10-02 | 2008-08-04
Activity | 1PF1665W42A03T | (HRSG #11 MECH Vendor Equip) Transportation | 2008-08-02 | 2008-09-16
Activity | 1PF1660W70A07T | (HRSG #11 ELEC Vendor Equip) Transportation | 2008-08-05 | 2008-09-18
Activity | 1PF1660W86A12T | (HRSG #11 I&C Vendor Equip) Transportation | 2008-08-05 | 2008-09-18
Activity | 1CF1665W42A04 | (HRSG #11 MECH Vendor Equip) Installation | 2008-09-17 | 2008-12-30
Activity | 1CF1660W70A08 | (HRSG #11 ELEC Vendor Equip) Installation | 2008-09-19 | 2009-01-12
Activity | 1CF1660W86A13 | (HRSG #11 I&C Vendor Equip) Installation | 2008-09-19 | 2009-01-12
Activity | 1CF1655W74A09 | (HRSG #11) Installation & Test - Elec. | 2008-10-29 | 2009-01-28
Activity | 1CF1660W90A14 | (HRSG #11) Installation & Test - I&C | 2008-10-29 | 2009-01-28
5 | Commissioning |  | 2009-02-19 | 2009-03-25
Activity | 1SF1600W62A01 | (HRSG #11) Cold Commissioning for HRSG #11 | 2009-02-19 | 2009-03-10
Activity | 1SF1600W62A02 | (HRSG #11) Function Test for HRSG #11 | 2009-03-11 | 2009-03-25
4 | HRSG #12 |  | 2007-04-17 | 2009-03-26
5 | HRSG LEB |  | 2007-06-15 | 2008-12-15
Activity | 1EF1600W74A05.1 | (HRSG #12 LEB) MPS Issue - Elec |  | 2007-06-15
Activity | 1EF1600W90A09.1 | (HRSG #12 LEB) MPS Issue - I&C |  | 2007-06-15
Activity | 1EF1600W00A01.1 | (HRSG #12 LEB) GA & Load Data to Civil Design | 2007-06-20
Activity | 1EF1600W32A02.1 | (HRSG #12 LEB) Building Design | 2007-06-20 | 2007-11-20
Activity | 1PF1600W74A06.1P | (HRSG #12 LEB) P.O & Procurement - Elec | 2007-09-15 | 2008-07-10
Activity | 1PF1600W90A10.1P | (HRSG #12 LEB) P.O & Procurement - I&C | 2007-09-15 | 2008-07-10
Activity | 1CF1600W16A03.1 | (HRSG #12 LEB)FDN Work | 2008-01-01 | 2008-02-27
Activity | 1CF1600W32A04.1 | (HRSG #12 LEB)Structure Work | 2008-02-28 | 2008-05-24
Activity | 1PF1600W74A07.1T | (HRSG #12 LEB) Transportataion - Elec | 2008-07-11 | 2008-08-24
Activity | 1PF1600W90A11.1T | (HRSG #12 LEB) Transportataion - I&C | 2008-07-11 | 2008-08-24
Activity | 1CF1600W36A13.1 | (HRSG #12 LEB) Installation & Test - HVAC | 2008-07-31 | 2008-09-13
Activity | 1CF1600W74A08.1 | (HRSG #12 LEB) Installation & Test - Elec | 2008-10-20 | 2008-12-15
Activity | 1CF1600W90A12.1 | (HRSG #12 LEB) Installation & Test - I&C | 2008-10-20 | 2008-12-15
Activity | 1CF1600W38A14.1 | (HRSG #12 LEB) Installation & Test - Fire Fighting Sys. | 2008-11-01 | 2008-12-15
5 | Steel Structure & Casing |  | 2007-04-18 | 2008-07-16
Activity | 1EF1610W20A01.1 | (HRSG #12 S/Structure & Casing) Design | 2007-04-18 | 2007-11-14
Activity | 1EF1610W20A02.1 | (HRSG #12 S/Structure & Casing) MPS Issue |  | 2007-05-15
Activity | 1PF1610W20A03.1P | (HRSG #12 S/Structure & Casing) P.O & Procurement | 2007-06-14 | 2008-01-31
Activity | 1PF1610W20A04.1T | (HRSG #12 S/Structure & Casing) Transportation | 2008-02-01 | 2008-03-17
Activity | 1CF1610W20A05.1 | (HRSG #12 S/Structure & Casing) S/Structure Installation | 2008-03-18 | 2008-05-17
Activity | 1CF1610W20A06.1 | (HRSG #12 S/Structure & Casing) Casing Installation | 2008-05-18 | 2008-07-16
5 | Duct |  | 2007-04-17 | 2009-01-03
Activity | 1EF1615W64A01.1 | (HRSG #12 Duct) Design | 2007-04-17 | 2007-10-18
Activity | 1EF1665W64A13.1 | (HRSG #12 EXP Joint & Bellows) MPS Issue |  | 2007-04-25
Activity | 1EF1615W64A09.1 | (HRSG #12 Damper) MPS Issue |  | 2007-04-25
Activity | 1EF1615W00A02.1 | (HRSG #12 Duct) GA & Load Data to Civil Design | 2007-04-30
Activity | 1EF1615W64A05.1 | (HRSG #12 Duct) MPS Issue |  | 2007-05-15
Activity | 1PF1665W64A14.1P | (HRSG #12 EXP Joint & Bellows) P.O & Procurement | 2007-06-13 | 2008-03-31
Activity | 1PF1615W64A10.1P | (HRSG #12 Damper) P.O & Procurement | 2007-06-13 | 2008-02-29
Activity | 1PF1615W64A06.1P | (HRSG #12 Duct) P.O & Procurement | 2007-06-14 | 2008-01-31
Activity | 1EF1615W16A03.1 | (HRSG #12 Duct) FDN Design | 2007-08-02 | 2007-12-13
Activity | 1CF1615W16A04.1 | (HRSG #12 Duct) FDN Work | 2007-12-14 | 2008-03-15
Activity | 1PF1615W64A07.1T | (HRSG #12 Duct) Transportation | 2008-02-01 | 2008-03-17
Activity | 1PF1615W64A11.1T | (HRSG #12 Damper) Transportation | 2008-03-01 | 2008-04-15
Activity | 1PF1665W64A15.1T | (HRSG #12 EXP Joint & Bellows) Transportation | 2008-04-01 | 2008-05-15
Activity | 1CF1615W64A12.1 | (HRSG #12 Damper) Installation | 2008-04-16 | 2008-06-16
Activity | 1CF1615W64A17.1 | (HRSG #12) Installation_Diverter Damper | 2008-05-03 | 2008-05-27
Activity | 1CF1615W64A18.1 | (HRSG #12) Installation_Guillotine Damper | 2008-05-28 | 2008-06-20
Activity | 1CF1615W86A19.1 | (HRSG #12) Installation_Diverter Damper Control Unit | 2008-05-28 | 2008-06-07
Activity | 1CF1615W62A20.1 | (HRSG #12) Diverter Damper Control Unit Flushing | 2008-06-09 | 2008-06-25
Activity | 1SF1615W62A21.1 | (HRSG #12) Diverter Damper Function Test for GT #12 | 2008-08-05 | 2008-08-08
Activity | 1SF1615W62A22.1 | (HRSG #12) Guillotine Damper Function Test for GT #12 | 2008-08-05 | 2008-08-08
Activity | 1CF1615W64A08.1 | (HRSG #12 Duct) Duct Installation | 2008-09-17 | 2008-12-17
Activity | 1CF1665W64A16.1 | (HRSG #12 EXP Joint & Bellows) Installation | 2008-11-20 | 2009-01-03
5 | Module |  | 2007-06-01 | 2008-09-16
Activity | 1EF1610W42A01.1 | (HRSG #12 Module) MPS Issue |  | 2007-06-01
Activity | 1PF1610W42A02.1P | (HRSG #12 Module) P.O & Procurement | 2007-07-03 | 2008-03-03
Activity | 1PF1610W42A03.1T | (HRSG #12 Module) Transportation | 2008-03-04 | 2008-04-17
Activity | 1CF1610W42A04.1 | (HRSG #12 Module) Installation | 2008-07-17 | 2008-09-16
5 | Drum |  | 2007-04-17 | 2008-10-15
Activity | 1EF1645W42A01.1 | (HRSG #12 Drum) Design | 2007-04-17 | 2007-11-07
Activity | 1EF1645W42A02.1 | (HRSG #12 Drum) MPS Issue | 2007-05-15
Activity | 1PF1645W42A03.1P | (HRSG #12 Drum) P.O & Procurement | 2007-06-13 | 2008-04-30
Activity | 1PF1645W42A04.1T | (HRSG #12 Drum) Transportation | 2008-05-01 | 2008-06-14
Activity | 1CF1645W42A05.1 | (HRSG #12 Drum) Installation | 2008-09-17 | 2008-10-15
5 | Bypass Stack |  | 2007-04-17 | 2008-07-02
Activity | 1EF1625W42A01.1 | (HRSG #12 Bypass Stack) Design | 2007-04-17 | 2007-10-29
Activity | 1EF1625W42A09.1 | (HRSG #12 Bypass Stack Silencer) MPS Issue |  | 2007-04-25
Activity | 1EF1625W42A05.1 | (HRSG #12 Bypass Stack) MPS Issue |  | 2007-05-15
Activity | 1EF1625W00A02.1 | (HRSG #12 Bypass Stack) GA & Load Data to Civil Design | 2007-05-31
Activity | 1PF1625W42A10.1P | (HRSG #12 Bypass Stack Silencer) P.O & Procurement | 2007-06-13 | 2008-03-31
Activity | 1PF1625W42A06.1P | (HRSG #12 Bypass Stack) P.O & Procurement | 2007-07-03 | 2008-01-30
Activity | 1EF1625W16A03.1 | (HRSG #12 Bypass Stack) FDN Design | 2007-09-04 | 2008-01-11
Activity | 1CF1625W16A04.1 | (HRSG #12 Bypass Stack) FDN Work | 2008-01-11 | 2008-03-31
Activity | 1PF1625W42A07.1T | (HRSG #12 Bypass Stack) Transportation | 2008-01-31 | 2008-03-15
Activity | 1CF1625W42A08.1 | (HRSG #12 Bypass Stack) Installation | 2008-03-31 | 2008-07-02
Activity | 1PF1625W42A11.1T | (HRSG #12 Bypass Stack Silencer) Transportation | 2008-04-01 | 2008-05-15
Activity | 1CF1625W42A12.1 | (HRSG #12 Bypass Stack Silencer) Installation | 2008-05-31 | 2008-06-30
5 | Main Stack |  | 2007-04-17 | 2009-02-19
Activity | 1EF1625W42A05.2 | (HRSG #12 Main Stack) MPS Issue |  | 2007-04-17
Activity | 1EF1625W42A01.2 | (HRSG #12 Main Stack) Design | 2007-04-17 | 2007-10-29
Activity | 1EF1625W42A09.2 | (HRSG #12 Main Stack Silencer) MPS Issue |  | 2007-04-25
Activity | 1EF1625W00A02.2 | (HRSG #12 Main Stack) GA & Load Data to Civil Design | 2007-06-05
Activity | 1PF1625W42A10.2P | (HRSG #12 Main Stack Silencer) P.O & Procurement | 2007-06-13 | 2008-03-31
Activity | 1PF1625W42A06.2P | (HRSG #12 Main Stack) P.O & Procurement | 2007-07-18 | 2008-03-17
Activity | 1EF1625W16A03.2 | (HRSG #12 Main Stack) FDN Design | 2007-09-07 | 2008-01-16
Activity | 1CF1625W16A04.2 | (HRSG #12 Main Stack) FDN Work | 2008-01-16 | 2008-04-18
Activity | 1PF1625W42A07.2T | (HRSG #12 Main Stack) Transportation | 2008-03-18 | 2008-05-01
Activity | 1PF1625W42A11.2T | (HRSG #12 Main Stack Silencer) Transportation | 2008-04-01 | 2008-05-15
Activity | 1CF1625W42A08.2 | (HRSG #12 Main Stack) Installation | 2008-11-14 | 2009-01-09
Activity | 1CF1625W42A12.2 | (HRSG #12 Main Stack Silencer) Installation | 2009-01-22 | 2009-02-19
5 | Piping Work |  | 2007-11-21 | 2009-02-06
Activity | 1EF1650W52A01.1 | (HRSG #12 Insulation) MPS Issue |  | 2007-11-21
Activity | 1PF1650W52A02.1P | (HRSG #12 Insulation) P.O & Procurement | 2008-01-09 | 2008-09-30
Activity | 1CF1640W58A05.1 | (HRSG #12) Piping Work | 2008-10-01 | 2008-12-19
Activity | 1PF1650W52A03.1T | (HRSG #12 Insulation) Transportation | 2008-10-01 | 2008-11-14
Activity | 1CF1640W62A06.1 | (HRSG #12) Hydro Test | 2008-12-20 | 2009-01-13
Activity | 1CF1650W52A04.1 | (HRSG #12 Insulation) Installation | 2009-01-03 | 2009-02-06
Activity | 1CF1640W60A07.1 | (HRSG #12)Acid Cleaning | 2009-01-14 | 2009-02-05
5 | CEMS |  | 2007-05-31 | 2008-08-10
Activity | 1EF1660W86A03.1 | (CEMS) MPS Issue |  | 2007-05-31
Activity | 1PF1660W86A04.1P | (CEMS) P.O & Procurement | 2007-08-29 | 2008-04-29
Activity | 1EF1660W16A01.1 | (CEMS) FDN Design | 2007-10-30 | 2008-01-25
Activity | 1CF1660W16A02.1 | (CEMS) FDN Work | 2008-01-26 | 2008-03-24
Activity | 1PF1660W86A05.1T | (CEMS) Transportation | 2008-04-30 | 2008-06-13
Activity | 1CF1660W86A06.1 | (CEMS) Installation(incl. Elec, I&C) | 2008-06-14 | 2008-06-30
Activity | 1CF1660W86A07.1 | (CEMS) Loop Test | 2008-07-01 | 2008-07-05
Activity | 1SF1660W62A08.1 | (HRSG #12) CEMS Function Test for GT #11(Bypass stack) | 2008-08-05 | 2008-08-10
5 | Auxiliary System |  | 2007-06-15 | 2009-01-29
Activity | 1EF1660W70A01.1 | (HRSG #12 ELEC Vendor Equip) MPS Issue |  | 2007-06-15
Activity | 1EF1660W86A06.1 | (HRSG #12 I&C Vendor Equip) MPS Issue |  | 2007-06-15
Activity | 1EF1665W42A11.1 | (HRSG #12 MECH Vendor Equip) MPS Issue |  | 2007-06-28
Activity | 1PF1665W42A12.1P | (HRSG #12 MECH Vendor Equip) P.O & Procurement | 2007-09-10 | 2008-08-01
Activity | 1PF1660W70A02.1P | (HRSG #12 ELEC Vendor Equip) P.O & Procurement | 2007-10-02 | 2008-08-04
Activity | 1PF1660W86A07.1P | (HRSG #12 I&C Vendor Equip) P.O & Procurement | 2007-10-02 | 2008-08-04
Activity | 1PF1665W42A13.1T | (HRSG #12 MECH Vendor Equip) Transportation | 2008-08-02 | 2008-09-16
Activity | 1PF1660W70A03.1T | (HRSG #12 ELEC Vendor Equip) Transportation | 2008-08-05 | 2008-09-18
Activity | 1PF1660W86A08.1T | (HRSG #12 I&C Vendor Equip) Transportation | 2008-08-05 | 2008-09-18
Activity | 1CF1665W42A14.1 | (HRSG #12 MECH Vendor Equip) Installation | 2008-09-17 | 2008-12-30
Activity | 1CF1660W70A04.1 | (HRSG #12 ELEC Vendor Equip) Installation | 2008-09-19 | 2009-01-12
Activity | 1CF1660W86A09.1 | (HRSG #12 I&C Vendor Equip) Installation | 2008-09-19 | 2009-01-12
Activity | 1CF1655W74A05.1 | (HRSG #12) Installation & Test - Elec. | 2008-10-30 | 2009-01-29
Activity | 1CF1660W90A10.1 | (HRSG #12) Installation & Test - I&C | 2008-10-30 | 2009-01-29
5 | Commissioning |  | 2009-02-20 | 2009-03-26
Activity | 1SF1600W62A01.1 | (HRSG #12) Cold Commissioning for HRSG #11 | 2009-02-20 | 2009-03-11
Activity | 1SF1600W62A02.1 | (HRSG #12) Function Test for HRSG #12 | 2009-03-12 | 2009-03-26
3 | Steam Turbine & Generator #10 |  | 2007-03-01 | 2009-03-30
4 | STG Building |  | 2007-03-01 | 2009-01-12
Activity | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | 2007-03-01
Activity | 1EF2010W20A02 | (STG #10 BLDG) Buliding Design | 2007-03-01 | 2007-09-18
Activity | 1PF2010W20A04P | (STG #10 BLDG) P.O & Procurement - Structure Work(S/S) | 2007-09-19 | 2008-01-31
Activity | 1CF2010W16A03 | (STG #10 BLDG) FDN Work | 2007-11-02 | 2008-03-03
Activity | 1PF2010W20A05T | (STG #10 BLDG) Transportation - Structure Work(S/S) | 2008-02-01 | 2008-03-16
Activity | 1CF2010W20A06 | (STG #10 BLDG) Structure Work(S/S) | 2008-03-17 | 2008-07-16
Activity | 1CF2010W20A07 | (STG #10 BLDG) Cladding Work | 2008-05-26 | 2008-10-11
Activity | 1CF2010W20A08 | (STG #10 BLDG) Roof Work | 2008-08-05 | 2008-11-06
Activity | 1CF2010W36A10 | (STG #10 BLDG) Installation & Test - HVAC | 2008-10-13 | 2008-12-08
Activity | 1CF2010W74A11 | (STG #10 BLDG) Installation & Test - Elec | 2008-10-13 | 2009-01-12
Activity | 1CF2010W90A12 | (STG #10 BLDG) Installation & Test - I&C | 2008-10-13 | 2009-01-12
Activity | 1CF2010W38A09 | (STG #10 BLDG) Installation & Test - Fire Fighting Sys. | 2008-11-01 | 2008-12-27
4 | STG Unit Step-up Transformer |  | 2007-03-30 | 2008-10-08
Activity | 1EF6500W70A06 | (STG #10 & UST Shelter) MPS Issue - Main TR |  | 2007-03-30
Activity | 1PF6500W70A07P | (STG #10 & UST Shelter) P.O & Procurement - Main TR | 2007-06-29 | 2008-06-22
Activity | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | 2007-11-28
Activity | 1EF6500W16A02 | (STG #10 & UST Shelter) FDN & Firewall Design | 2007-11-28 | 2008-03-10
Activity | 1EF6500W32A04 | (STG #10 & UST Shelter) Structure Design | 2007-11-28 | 2008-03-10
Activity | 1CF6500W16A03 | (STG #10 & UST Shelter) FDN Work | 2008-03-11 | 2008-06-09
Activity | 1CF6500W16A05 | (STG #10 & UST Shelter) Firewall Work | 2008-06-10 | 2008-08-09
Activity | 1PF6500W70A08T | (STG #10 & UST Shelter) Transportation - Main TR | 2008-06-23 | 2008-08-06
Activity | 1CF6500W70A09 | (STG #10 & UST Shelter) Installation - Main TR | 2008-08-10 | 2008-10-08
4 | Steam Turbine |  | 2007-03-01 | 2009-03-18
Activity | 1EF2020W00A01 | (ST #10) ST Process Data | 2007-03-01 | 2007-03-30
Activity | 1EF2020W00A02 | (ST #10) ST Aux' Steam Consumption Data | 2007-03-01 | 2007-03-29
Activity | 1EF2020W00A03 | (ST #10) Instrument, Service Air Data | 2007-03-01 | 2007-03-29
Activity | 1EF2020W00A04 | (ST #10) Utility Consumption Data | 2007-03-01 | 2007-04-26
Activity | 1EF2020W00A05 | (ST #10) Emergency Load Data | 2007-03-01 | 2007-04-16
Activity | 1EF2020W42A09 | (ST #10) MPS Issue |  | 2007-03-01
Activity | 1PF2020W42A10P | (ST #10) P.O & Procurement | 2007-03-01 | 2008-09-01
Activity | 1EF2020W16A06 | (ST #10) FDN Design | 2007-07-03 | 2007-11-01
Activity | 1CF2020W16A07 | (ST #10) FDN Work | 2007-11-02 | 2008-03-03
Activity | 1CF2020W16A08 | (ST #10) Pedestal & Top Slab Work | 2008-03-04 | 2008-08-29
Activity | 1PF2020W42A11T | (ST #10) Transportation | 2008-09-02 | 2008-10-16
Activity | 1CF2020W42A12 | (ST #10) Installation | 2008-10-17 | 2009-03-18
4 | ST Generator |  | 2007-03-01 | 2009-02-17
Activity | 1EF2040W42A01 | (STG #10) MPS Issue |  | 2007-03-01
Activity | 1PF2040W42A02P | (STG #10) P.O & Procurement | 2007-03-01 | 2008-09-01
Activity | 1PF2040W42A03T | (STG #10) Transportation | 2008-09-02 | 2008-10-16
Activity | 1CF2040W42A04 | (STG #10) Installation | 2008-10-17 | 2009-02-17
4 | STG Auxiliary Equipment |  | 2007-03-01 | 2009-01-08
Activity | 1EF2070W42A03 | (STG #10 Aux. Equip) MPS Issue |  | 2007-03-01
Activity | 1PF2070W42A04P | (STG #10 Aux. Equip) P.O & Procurement | 2007-04-30 | 2008-07-31
Activity | 1EF2070W16A01 | (STG #10 Aux. Equip) FDN Design | 2007-12-24 | 2008-05-21
Activity | 1CF2070W16A02 | (STG #10 Aux. Equip) FDN Work | 2008-05-22 | 2008-08-16
Activity | 1PF2070W42A05T | (STG #10 Aux. Equip) Transportation | 2008-08-01 | 2008-09-15
Activity | 1CF2070W42A06 | (STG #10 Aux. Equip) Installation | 2008-09-16 | 2009-01-08
4 | Piping & Etc. |  | 2008-08-11 | 2009-02-11
Activity | 1CF2035W58A01 | (ST #10) Piping Work | 2008-08-11 | 2009-01-10
Activity | 1CF2060W74A03 | (ST #10) Installation & Test - Elec. | 2008-11-18 | 2009-02-05
Activity | 1CF2065W90A04 | (ST #10) Installation & Test - I&C | 2008-11-18 | 2009-02-05
Activity | 1CF2035W62A02 | (ST #10) Hydro Test | 2009-01-12 | 2009-02-11
4 | Lube Oil System |  | 2007-05-01 | 2009-02-25
Activity | 1EF2030W42A03 | (Lube Oil Sys.) MPS Issue |  | 2007-05-01
Activity | 1PF2030W42A04P | (Lube Oil Sys.) P.O & Procurement | 2007-07-31 | 2008-07-30
Activity | 1EF2030W16A01 | (Lube Oil Sys.) FDN Design | 2007-10-23 | 2008-01-22
Activity | 1CF2030W16A02 | (Lube Oil Sys.) FDN Work | 2008-01-23 | 2008-05-23
Activity | 1PF2030W42A05T | (Lube Oil Sys.) Transportation | 2008-07-31 | 2008-09-13
Activity | 1CF2030W42A06 | (Lube Oil Sys.) Equipment Installation | 2008-09-15 | 2008-10-30
Activity | 1CF2030W58A07 | (Lube Oil Sys.) Pipe Installation | 2008-10-31 | 2009-01-15
Activity | 1CF2030W62A08 | (Lube Oil Sys.) Lube oil flushing | 2009-01-16 | 2009-02-13
Activity | 1CF2030W58A09 | (Lube Oil Sys.) Remove Temp. Pipe | 2009-02-14 | 2009-02-25
4 | Test & Commissioning |  | 2009-02-27 | 2009-03-30
Activity | 1SF2000W62A02 | (ST #10) Pre-Commissioning | 2009-02-27 | 2009-03-28
Activity | 1SF2000W62A01 | (ST #10) Aux. Equipment Function Test | 2009-03-09 | 2009-03-28
Activity | 1SF2000W62A03 | (ST #10) Turnning Gear Operation | 2009-03-29 | 2009-03-30
3 | Block #1 Commisssioning |  | 2009-03-31 | 2009-08-31
Activity | 1SF9035W62A01 | (Comm'g) Steam Blowing | 2009-03-31 | 2009-04-19
Activity | 1CF9035W62A02 | (Comm'g) Temporary Piping Restoration | 2009-04-20 | 2009-04-29
Activity | 1SF9035W62A03 | (Comm'g) Bypass Operation | 2009-04-30 | 2009-05-06
Activity | 1SF9035W62A04 | (Comm'g) Safety & Interlock Test | 2009-05-02 | 2009-05-06
Activity | 1SF9035W62A05 | (Comm'g) Steam Admission | 2009-05-07 | 2009-05-08
Activity | 1SF9040W62A06 | (Comm'g) TBN & GEN. Test | 2009-05-09 | 2009-05-21
Activity | 1SF9040W62A07 | (Comm'g) Synchronization Test | 2009-05-22 | 2009-05-22
Activity | 1SF9040W62A08 | (Comm'g) Optimaization Test | 2009-05-23 | 2009-06-09
Activity | 1SF9040W62A09 | (Comm'g) Fuel Change-Over(Gas to Oil) and Optimaization | 2009-06-10 | 2009-06-10
Activity | 1SF9040W62A10 | (Comm'g) Outage Period | 2009-06-10 | 2009-06-16
Activity | 1SF9040W62A11 | (Comm'g) APS & Stability Guarantee Test | 2009-06-17 | 2009-07-18
Activity | 1SF9040W62A12 | (Comm'g) Trial Run Test | 2009-07-19 | 2009-07-20
Activity | 1SF9041W62A14 | (Comm'g) Reliability Test | 2009-07-21 | 2009-08-19
Activity | 1SF9040W62A13 | (Comm'g) Initial Operation Test | 2009-07-21 | 2009-07-21
Activity | 1SF9042W62A15 | (Comm'g) Performance Test (Fuel Gas & Fuel Oil) | 2009-08-20 | 2009-08-31
2 | Power Plant Block #2 |  | 2007-03-01 | 2009-10-02
3 | Block #2 Early Power Block Common |  | 2007-03-02 | 2009-02-18
4 | Fuel Gas Supply System |  | 2007-03-02 | 2008-09-28
Activity | 2CF3520W16A01 | (FGSS #21) FDN Work(Misc. Equipment) | 2008-01-01 | 2008-04-02
Activity | 2CF3520W16A08 | (FGSS #22) FDN Work(Misc. Equipment) | 2008-01-01 | 2008-04-02
Activity | 2CF3520W58A03 | (FGSS #21) Piping Work(incl. Air leak Test & Blowing)_Gas Farm Area | 2008-06-19 | 2008-09-02
Activity | 2CF3520W58A10 | (FGSS #22) Piping Work(incl. Air leak Test & Blowing)_Gas Farm Area | 2008-06-19 | 2008-09-02
Activity | 2CF3520W86A02 | (FGSS #21) ESD Valve Skid installation | 2008-06-19 | 2008-06-30
Activity | 2CF3520W86A09 | (FGSS #22) ESD Valve Skid installation | 2008-06-19 | 2008-06-30
Activity | 2CF3520W74A04 | (FGSS #21) Installation & Test - Elec. | 2008-07-04 | 2008-09-02
Activity | 2CF3520W90A05 | (FGSS #21) Installation & Test - I&C | 2008-07-04 | 2008-09-02
Activity | 2CF3520W74A11 | (FGSS #22) Installation & Test - Elec. | 2008-07-04 | 2008-09-02
Activity | 2CF3520W90A12 | (FGSS #22) Installation & Test - I&C | 2008-07-04 | 2008-09-02
Activity | 2SF3520W62A06 | (FGSS #21) Fuel Gas Receiving | 2008-09-21 | 2008-09-21
Activity | 2SF3520W62A13 | (FGSS #22) Fuel Gas Receiving | 2008-09-21 | 2008-09-21
Activity | 2SF3520W62A07.2 | (FGSS #21) Metering System Calibration with supplier | 2008-09-24 | 2008-09-28
Activity | 2SF3520W62A14 | (FGSS #22) Metering System Calibration with supplier | 2008-09-24 | 2008-09-28
5 | Gas Pressure Reducing System |  | 2007-06-01 | 2008-09-04
Activity | 2EF3520W00A28 | (GT/HRSG GPRS Shelter) GA & Load Data to Civil Design | 2007-06-01
Activity | 2EF3520W16A29 | (GT/HRSG GPRS Shelter) FDN Design | 2007-06-01 | 2007-10-04
Activity | 2EF3520W32A31 | (GT/HRSG GPRS Shelter) Structure Design | 2007-06-01 | 2007-10-04
Activity | 2PF3520W42A04P | (GPRS) P.O & Procurement for GT | 2007-06-01 | 2008-04-30
Activity | 2PF3520W42A14P | (GPRS) P.O & Procurement for HRSG | 2007-07-03 | 2008-05-30
Activity | 2EF3520W16A12 | (GPRS) FDN Design for HRSG | 2007-07-03 | 2007-11-09
Activity | 2EF3520W16A01 | (GPRS) FDN Design for GT | 2007-08-02 | 2007-10-16
Activity | 2CF3520W16A02 | (GPRS) FDN Work for GT | 2007-11-02 | 2007-12-29
Activity | 2CF3520W16A13 | (GPRS) FDN Work for HRSG | 2007-11-27 | 2008-01-23
Activity | 2CF3520W16A30 | (GT/HRSG GPRS Shelter) FDN Work | 2007-12-13 | 2008-02-12
Activity | 2CF3520W32A32 | (GT/HRSG GPRS Shelter) Structure Work | 2008-02-13 | 2008-05-15
Activity | 2PF3520W42A05T | (GPRS) Transportation for GT | 2008-05-01 | 2008-06-14
Activity | 2PF3520W42A15T | (GPRS) Transportation for HRSG | 2008-05-31 | 2008-07-15
Activity | 2CF3520W42A06 | (GPRS #21) Installation for GT | 2008-06-16 | 2008-08-30
Activity | 2CF3520W42A09 | (GPRS #22) Installation for GT | 2008-06-16 | 2008-08-30
Activity | 2CF3520W42A22 | (GPRS #21 for Fuel Change over) Installation | 2008-06-16 | 2008-07-26
Activity | 2CF3520W42A25 | (GPRS #22 for Fuel Change over) Installation | 2008-06-16 | 2008-07-26
Activity | 2CF3520W24A33 | (GT/HRSG GPRS Shelter) Shelter Finish | 2008-07-09 | 2008-08-30
Activity | 2CF3520W42A16 | (GPRS #21) Installation for HRSG | 2008-07-16 | 2008-08-26
Activity | 2CF3520W42A19 | (GPRS #22) Installation for HRSG | 2008-07-16 | 2008-08-26
Activity | 2SF3520W62A23 | (GPRS #21 for Fuel Change over) Loop chek & Motor Solo Test | 2008-07-27 | 2008-07-29
Activity | 2SF3520W62A26 | (GPRS #22 for Fuel Change over) Loop chek & Motor Solo Test | 2008-07-27 | 2008-07-29
Activity | 2SF3520W62A24 | (GPRS #21 for Fuel Change over) Function Test | 2008-07-30 | 2008-07-31
Activity | 2SF3520W62A27 | (GPRS #22 for Fuel Change over) Function Test | 2008-07-30 | 2008-07-31
Activity | 2SF3520W62A17 | (GPRS #21) Loop chek & Motor Solo Test for HRSG | 2008-08-27 | 2008-08-29
Activity | 2SF3520W62A20 | (GPRS #22) Loop chek & Motor Solo Test for HRSG | 2008-08-27 | 2008-08-29
Activity | 2SF3520W62A18 | (GPRS #21) Function Test for HRSG | 2008-08-30 | 2008-09-01
Activity | 2SF3520W62A21 | (GPRS #22) Function Test for HRSG | 2008-08-30 | 2008-09-01
Activity | 2SF3520W62A07 | (GPRS #21) Loop check for GT | 2008-08-31 | 2008-09-02
Activity | 2SF3520W62A10 | (GPRS #22) Loop check for GT | 2008-08-31 | 2008-09-02
Activity | 2SF3520W62A08 | (GPRS #21) Function Test for GT | 2008-09-03 | 2008-09-04
Activity | 2SF3520W62A11 | (GPRS #22) Function Test for GT | 2008-09-03 | 2008-09-04
5 | Fuel Gas Filter & Metering System |  | 2007-06-01 | 2008-08-07
Activity | 2EF3520W00A10 | (Filtering/Metering Station Shelter) GA & Load Data to Civil Design | 2007-06-01
Activity | 2EF3520W16A11 | (Filtering/Metering Station Shelter) FDN Design | 2007-06-01 | 2007-10-12
Activity | 2EF3520W32A13 | (Filtering/Metering Station Shelter) Structure Design | 2007-06-01 | 2007-10-12
Activity | 2PF3520W42A02.3P | (Filtering/Metering Station) P.O & Procurement | 2007-07-03 | 2008-05-19
Activity | 2CF3520W16A12 | (Filtering/Metering Station Shelter) FDN Work | 2007-11-15 | 2008-01-11
Activity | 2CF3520W32A14 | (Filtering/Metering Station Shelter) Structure Work | 2008-01-12 | 2008-03-13
Activity | 2PF3520W42A03.3T | (Filtering/Metering Station) Transportation | 2008-05-20 | 2008-07-03
Activity | 2CF3520W42A04.3 | (Filtering/Metering Station #21) Installation | 2008-07-04 | 2008-07-18
Activity | 2CF3520W42A07.3 | (Filtering/Metering Station #22) Installation | 2008-07-04 | 2008-07-18
Activity | 2CF3520W24A15 | (Filtering/Metering Station Shelter) Shelter Finish | 2008-07-19 | 2008-08-07
Activity | 2SF3520W62A05.3 | (Filtering/Metering Station #21) Loop chek | 2008-07-19 | 2008-07-21
Activity | 2SF3520W62A08.3 | (Filtering/Metering Station #22) Loop chek | 2008-07-19 | 2008-07-21
Activity | 2SF3520W62A06.3 | (Filtering/Metering Station #21) Function Test | 2008-07-22 | 2008-07-23
Activity | 2SF3520W62A09.3 | (Filtering/Metering Station #22) Function Test | 2008-07-22 | 2008-07-23
5 | Gas Heater |  | 2007-07-03 | 2008-08-26
Activity | 2EF3520W16A01.2 | (Gas HTR) FDN Design | 2007-07-03 | 2007-10-01
Activity | 2EF3520W32A03.2 | (Gas HTR) Structure Design | 2007-07-03 | 2007-10-01
Activity | 2PF3520W42A07.2P | (Gas HTR) P.O & Procurement | 2007-07-03 | 2008-06-02
Activity | 2CF3520W16A02.2 | (Gas HTR) FDN Work | 2007-10-02 | 2007-11-28
Activity | 2CF3520W32A04.2 | (Gas HTR) Structure Work | 2007-11-29 | 2008-01-29
Activity | 2PF3520W42A08.2T | (Gas HTR) Transportation | 2008-06-03 | 2008-07-17
Activity | 2CF3520W24A05.2 | (Gas HTR) Shelter Finish | 2008-07-18 | 2008-08-26
Activity | 2CF3520W42A09.2 | (Gas HTR #21) Installation | 2008-07-18 | 2008-08-02
Activity | 2CF3520W42A12.2 | (Gas HTR #22) Installation | 2008-07-18 | 2008-08-02
Activity | 2SF3520W62A10.2 | (Gas HTR #21) Loop chek | 2008-08-03 | 2008-08-05
Activity | 2SF3520W62A13.2 | (Gas HTR #22) Loop chek | 2008-08-03 | 2008-08-05
Activity | 2SF3520W62A11.2 | (Gas HTR #21) Function Test | 2008-08-06 | 2008-08-08
Activity | 2SF3520W62A14.2 | (Gas HTR #22) Function Test | 2008-08-06 | 2008-08-08
5 | Gas Compressor |  | 2007-03-02 | 2008-09-23
Activity | 2EF3520W00A25.1 | (Gas COMP House) GA & Load Data to Civil Design | 2007-03-02
Activity | 2PF3520W42A05.1P | (Gas COMP PKG) P.O & Procurement | 2007-03-15 | 2008-05-14
Activity | 2EF3520W16A26.1 | (Gas COMP House) FDN Design | 2007-04-03 | 2007-09-03
Activity | 2EF3520W32A28.1 | (Gas COMP House) Structure Design | 2007-04-03 | 2007-09-03
Activity | 2EF3520W16A01.1 | (Gas COMP PKG) FDN Design | 2007-08-02 | 2007-11-01
Activity | 2CF3520W16A02.1 | (Gas COMP PKG) FDN Work | 2007-11-02 | 2008-01-31
Activity | 2CF3520W16A27.1 | (Gas COMP House) FDN Work | 2007-11-03 | 2007-12-31
Activity | 2CF3520W32A29.1 | (Gas COMP House) Structure Work | 2008-01-01 | 2008-03-15
Activity | 2PF3520W42A06.1T | (Gas COMP PKG)Transportation | 2008-05-15 | 2008-06-28
Activity | 2CF3520W42A07.1 | (Gas COMP PKG #21) Installation_Gas Compressor | 2008-06-30 | 2008-07-31
Activity | 2CF3520W42A16.1 | (Gas COMP PKG #22) Installation_Gas Compressor | 2008-06-30 | 2008-07-31
Activity | 2CF3520W42A11.1 | (Gas COMP PKG #21) Installation_Lube oil Sys.(incl. Flushing) | 2008-06-30 | 2008-07-31
Activity | 2CF3520W42A08.1 | (Gas COMP PKG #21) Installation_Air Compressor | 2008-06-30 | 2008-07-31
Activity | 2CF3520W42A09.1 | (Gas COMP PKG #21) Installation_Air Ventilation | 2008-06-30 | 2008-07-31
Activity | 2CF3520W42A20.1 | (Gas COMP PKG #22) Installation_Lube oil Sys.(incl. Flushing) | 2008-06-30 | 2008-07-31
Activity | 2CF3520W42A17.1 | (Gas COMP PKG #22) Installation_Air Compressor | 2008-06-30 | 2008-07-31
Activity | 2CF3520W42A18.1 | (Gas COMP PKG #22) Installation_Air Ventilation | 2008-06-30 | 2008-07-31
Activity | 2CF3520W24A30.1 | (Gas COMP House) Shelter finish | 2008-08-01 | 2008-09-09
Activity | 2CF3520W42A12.1 | (Gas COMP PKG #21) Installation_N2 Generation Sys. | 2008-08-01 | 2008-09-02
Activity | 2CF3520W42A10.1 | (Gas COMP PKG #21) Installation_Seal Gas Sys. | 2008-08-01 | 2008-09-02
Activity | 2CF3520W42A21.1 | (Gas COMP PKG #22) Installation_N2 Generation Sys. | 2008-08-01 | 2008-09-02
Activity | 2CF3520W42A19.1 | (Gas COMP PKG #22) Installation_Seal Gas Sys. | 2008-08-01 | 2008-09-02
Activity | 2SF3520W62A13.1 | (Gas COMP PKG #21) Loop chek | 2008-09-03 | 2008-09-12
Activity | 2SF3520W62A22.1 | (Gas COMP PKG #22) Loop chek | 2008-09-03 | 2008-09-12
Activity | 2SF3520W62A14.1 | (Gas COMP PKG #21) Function Test | 2008-09-16 | 2008-09-20
Activity | 2SF3520W62A23.1 | (Gas COMP PKG #22) Function Test | 2008-09-16 | 2008-09-20
Activity | 2SF3520W62A15.1 | (Gas COMP PKG #21) Running Test | 2008-09-22 | 2008-09-23
Activity | 2SF3520W62A24.1 | (Gas COMP PKG #22) Running Test | 2008-09-22 | 2008-09-23
5 | Gas cooler |  | 2008-06-30 | 2008-07-31
Activity | 2CF3520W42A01.1 | (Gas Cooler #21) Installation(incl. fan) | 2008-06-30 | 2008-07-21
Activity | 2CF3520W42A05.1 | (Gas Cooler #22) Installation(incl. fan) | 2008-06-30 | 2008-07-21
Activity | 2SF3520W62A02.1 | (Gas Cooler #21) Loop chek | 2008-07-22 | 2008-07-26
Activity | 2SF3520W62A06.1 | (Gas Cooler #22) Loop chek | 2008-07-22 | 2008-07-26
Activity | 2SF3520W62A03.1 | (Gas Cooler #21) Function Test | 2008-07-27 | 2008-07-29
Activity | 2SF3520W62A07.1 | (Gas Cooler #22) Function Test | 2008-07-27 | 2008-07-29
Activity | 2SF3520W62A04.1 | (Gas Cooler #21) Running Test | 2008-07-30 | 2008-07-31
Activity | 2SF3520W62A08.1 | (Gas Cooler #22) Running Test | 2008-07-30 | 2008-07-31
4 | N2 Gas System |  | 2007-11-01 | 2008-09-11
Activity | 2PF3515W42A04P | (N2 Gas Equip) P.O & Procurement for FGSS(Local PROC.) | 2007-11-01 | 2008-05-30
Activity | 2EF3515W00A06 | (N2 Gas Station Shelter) GA & Load Data to Civil Design | 2007-12-03
Activity | 2EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | 2007-12-03 | 2008-03-03
Activity | 2CF3515W16A07 | (N2 Gas Station Shelter) FDN Work | 2008-04-05 | 2008-06-02
Activity | 2CF3515W42A05 | (N2 Gas Equip) Installation for FGSS | 2008-05-31 | 2008-07-01
Activity | 2CF3515W32A09 | (N2 Gas Station Shelter) Shelter Work | 2008-06-03 | 2008-09-11
4 | Electrical System |  | 2007-03-30 | 2009-02-18
5 | Generator Circuit Breaker (GCB) |  | 2007-05-31 | 2009-02-04
Activity | 2PF6500W86A02P | (GT GCB) P.O & Procurement | 2007-05-31 | 2008-05-01
Activity | 2PF6500W86A07P | (ST GCB) P.O & Procurement | 2007-10-02 | 2008-08-29
Activity | 2PF6500W86A03T | (GT GCB) Transportation | 2008-05-02 | 2008-06-16
Activity | 2CF6500W86A04 | (GT GCB) Installation | 2008-06-17 | 2008-07-17
Activity | 2SF6500W62A05 | (GT GCB) Function Test | 2008-07-18 | 2008-08-01
Activity | 2PF6500W86A08T | (ST GCB) Transportation | 2008-08-30 | 2008-10-14
Activity | 2CF6500W86A09 | (ST GCB) Installation | 2008-12-20 | 2009-01-20
Activity | 2SF6500W62A10 | (ST GCB) Function Test | 2009-01-21 | 2009-02-04
5 | Extra High Voltage Cable |  | 2007-08-02 | 2008-08-22
Activity | 2PF6040W74A06P | (EHV Cable) P.O & Procurement | 2007-08-02 | 2008-04-01
Activity | 2EF6040W16A02 | (Cable tunnel) FDN Design | 2007-08-02 | 2007-11-01
Activity | 2EF6040W16A01 | (Cable tunnel) Cable tunnel Design | 2007-08-02 | 2008-01-01
Activity | 2CF6040W16A03 | (Cable tunnel) Civil Work | 2007-11-02 | 2008-04-01
Activity | 2PF6040W74A07T | (EHV Cable) Transportation | 2008-04-02 | 2008-05-16
Activity | 2CF6040W74A08 | (EHV Cable) Cable Electrical Work | 2008-05-17 | 2008-08-01
Activity | 2CF6040W38A04 | (Cable tunnel) F/F Work & Test | 2008-05-31 | 2008-07-16
Activity | 2CF6040W62A09 | (EHV Cable) Function Test | 2008-08-02 | 2008-08-06
Activity | 2CF6040W74A10 | (EHV Cable) Connection with GIS & TR | 2008-08-16 | 2008-08-22
5 | Isolated Phase Busduct (IPB) |  | 2007-08-02 | 2008-09-12
Activity | 2PF6500W74A02P | (IPB) P.O & Procurement | 2007-08-02 | 2008-04-15
Activity | 2PF6500W74A03T | (IPB) Transportation | 2008-04-16 | 2008-05-30
Activity | 2CF6500W74A04 | (IPB) Installation form TR to GCB(incl. Support) | 2008-05-31 | 2008-08-01
Activity | 2CF6500W62A05 | (IPB) Insulation Test & Hi potential Test | 2008-08-02 | 2008-08-08
Activity | 2CF6500W74A06 | (IPB) IPB connection with TR & GCB | 2008-09-06 | 2008-09-12
5 | Power Transformer |  | 2007-04-02 | 2009-02-18
Activity | 2PF6500W70A04P | (GTG TR) P.O & Procurement | 2007-04-02 | 2008-05-15
Activity | 2PF6500W70A12P | (STG TR) P.O & Procurement | 2007-08-02 | 2008-08-29
Activity | 2EF6500W16A01 | (GTG TR) FDN Design | 2007-08-02 | 2007-11-30
Activity | 2CF6500W16A02 | (GTG TR) FDN & Firewall Work | 2007-12-01 | 2008-04-01
Activity | 2EF6500W16A09 | (STG TR) FDN Design | 2008-02-06 | 2008-07-04
Activity | 2PF6500W70A05T | (GTG TR) Transportation | 2008-05-16 | 2008-06-30
Activity | 2CF6500W70A06 | (GTG TR) Installation | 2008-07-01 | 2008-08-15
Activity | 2CF6500W16A10 | (STG TR) FDN & Firewall Work | 2008-07-05 | 2008-11-04
Activity | 2CF6500W38A07 | (GTG TR) F/F Install & test | 2008-08-16 | 2008-08-29
Activity | 2PF6500W70A13T | (STG TR) Transportation | 2008-08-30 | 2008-10-14
Activity | 2SF6500W62A08 | (GTG TR) Function Test | 2008-08-30 | 2008-09-05
Activity | 2CF6500W70A14 | (STG TR) Installation | 2008-11-05 | 2008-12-19
Activity | 2CF6500W38A15 | (STG TR) F/F test | 2008-12-20 | 2008-12-26
Activity | 2SF6500W62A16 | (STG TR) Function Test | 2009-02-05 | 2009-02-18
5 | Auxiliary Transformer |  | 2007-03-30 | 2008-08-06
Activity | 2PF6500W70A04.1P | (GTG UAT) P.O & Procurement | 2007-03-30 | 2008-04-16
Activity | 2EF6500W16A01.1 | (GTG UAT) FDN Design | 2007-05-01 | 2007-08-30
Activity | 2EF6500W00A09 | (GTG #21 & UAT Shelter) GA & Load Data to Civil Design | 2007-05-31
Activity | 2EF6500W16A10 | (GTG #21 & UAT Shelter) FDN Design | 2007-07-02 | 2007-10-11
Activity | 2EF6500W32A12 | (GTG #21 & UAT Shelter) Structure Design | 2007-07-02 | 2007-10-11
Activity | 2CF6500W16A02.1 | (GTG UAT) FDN Work & Firewall Work | 2007-11-02 | 2008-02-29
Activity | 2CF6500W16A11 | (GTG #21 & UAT Shelter) FDN Work | 2007-11-02 | 2007-12-29
Activity | 2CF6500W32A13 | (GTG #21 & UAT Shelter) Structure Work | 2007-12-31 | 2008-04-01
Activity | 2PF6500W70A05.1T | (GTG UAT) Transportation | 2008-04-17 | 2008-05-31
Activity | 2CF6500W90A16 | (GTG #21 & UAT Shelter) Installation & Test - I&C | 2008-05-31 | 2008-07-16
Activity | 2CF6500W38A14 | (GTG #21 & UAT Shelter) Installation & Test - Fire Fighting Sys. | 2008-05-31 | 2008-07-16
Activity | 2CF6500W74A15 | (GTG #21 & UAT Shelter) Installation & Test - Elec | 2008-05-31 | 2008-07-16
Activity | 2CF6500W70A06.1 | (GTG UAT) Installation | 2008-06-02 | 2008-07-17
Activity | 2CF6500W38A07.1 | (GTG UAT) F/F Install & test | 2008-07-18 | 2008-08-02
Activity | 2SF6500W62A08.1 | (GTG UAT) Function Test | 2008-08-03 | 2008-08-06
5 | Emergency Diesel Generator |  | 2007-08-01 | 2008-09-15
Activity | 2EF3530W00A01 | (Block #2 EDG) GA & Load Data to Civil Design | 2007-08-01
Activity | 2EF3530W16A14 | (Block #2 EDG BLDG) FDN Design | 2007-08-01 | 2007-10-29
Activity | 2EF3530W32A16 | (Block #2 EDG BLDG) Structure Design | 2007-08-01 | 2007-11-29
Activity | 2PF3530W42A06P | (Block #2 EDG) P.O & Procurement | 2007-08-01 | 2008-07-01
Activity | 2EF3530W16A02 | (Block #2 EDG) FDN Design | 2007-08-01 | 2007-10-29
Activity | 2CF3530W16A15 | (Block #2 EDG BLDG) FDN Work | 2007-11-30 | 2008-01-30
Activity | 2CF3530W16A03 | (Block #2 EDG) FDN Work | 2007-11-30 | 2008-01-30
Activity | 2CF3530W32A17 | (Block #2 EDG BLDG) Structure Work | 2008-01-31 | 2008-05-02
Activity | 2CF3530W90A21 | (Block #2 EDG BLDG) Installation & Test - I&C | 2008-05-03 | 2008-06-18
Activity | 2CF3530W38A18 | (Block #2 EDG BLDG) Installation - Fire Fighting Sys. | 2008-05-03 | 2008-06-18
Activity | 2CF3530W36A19 | (Block #2 EDG BLDG) Installation & Test - HVAC | 2008-05-03 | 2008-06-18
Activity | 2CF3530W74A20 | (Block #2 EDG BLDG) Installation & Test - Elec | 2008-05-03 | 2008-06-18
Activity | 2CF3530W24A22 | (Block #2 EDG BLDG) Building Finish | 2008-05-03 | 2008-07-15
Activity | 2PF3530W42A07T | (Block #2 EDG) Transportation | 2008-07-02 | 2008-08-15
Activity | 2CF3530W42A08 | (Block #2 EDG) Installation | 2008-08-16 | 2008-09-05
Activity | 2SF3530W62A09 | (Block #2 EDG) Loop chek | 2008-09-06 | 2008-09-07
Activity | 2SF3530W62A10 | (Block #2 EDG) Function Test | 2008-09-08 | 2008-09-09
Activity | 2SF3530W62A11 | (Block #2 EDG) System Operation | 2008-09-10 | 2008-09-11
Activity | 2SF3530W62A12 | (Block #2 EDG) Synchronization | 2008-09-12 | 2008-09-13
Activity | 2SF3530W62A13 | (Block #2 EDG) Load Operation | 2008-09-14 | 2008-09-15
3 | Block #2 Combined Power Block Common |  | 2007-03-01 | 2009-04-11
4 | Closed Cooling Water System for Block #2 |  | 2007-09-03 | 2008-11-25
Activity | 2PF3030W68A04P | (EXP Head Tank) P.O & Procurement | 2007-09-03 | 2008-08-29
Activity | 2PF3030W42A21P | (CCWP) P.O & Procurement | 2007-09-03 | 2008-08-01
Activity | 2EF3030W16A17 | (CCWP) FDN Design | 2007-09-03 | 2008-01-30
Activity | 2PF3030W42A14P | (CCW H/EX) P.O & Procurement | 2007-09-03 | 2008-08-15
Activity | 2EF3030W16A10 | (CCW H/EX) FDN Design | 2007-09-03 | 2008-01-30
Activity | 2EF3030W16A01 | (EXP Head Tank) FDN Design | 2007-11-02 | 2008-04-01
Activity | 2CF3030W16A18 | (CCWP) FDN Work | 2008-03-03 | 2008-04-29
Activity | 2CF3030W16A11 | (CCW H/EX) FDN Work | 2008-03-03 | 2008-05-28
Activity | 2CF3030W16A02 | (EXP Head Tank) FDN Work | 2008-05-03 | 2008-05-31
Activity | 2CF3030W58A07 | (CCWS) Piping Work | 2008-07-01 | 2008-10-01
Activity | 2PF3030W42A22T | (CCWP) Transportation | 2008-08-02 | 2008-09-16
Activity | 2PF3030W42A15T | (CCW H/EX) Transportation | 2008-08-16 | 2008-09-30
Activity | 2PF3030W68A05T | (EXP Head Tank) Transportation | 2008-08-30 | 2008-10-14
Activity | 2CF3030W74A08 | (CCWS) Installation & Test - Elec. | 2008-09-12 | 2008-11-12
Activity | 2CF3030W90A09 | (CCWS) Installation & Test - I&C | 2008-09-12 | 2008-11-12
Activity | 2CF3030W42A23 | (CCWP) Installation | 2008-09-17 | 2008-10-01
Activity | 2CF3030W42A16 | (CCW H/EX) Installation | 2008-10-02 | 2008-11-03
Activity | 2CF3030W68A06 | (EXP Head Tank) Installation | 2008-10-15 | 2008-11-12
Activity | 2SF3030W62A24 | (CCWS) Loop chek | 2008-11-13 | 2008-11-17
Activity | 2SF3030W62A25 | (CCWS) System Function Test | 2008-11-18 | 2008-11-22
Activity | 2SF3030W62A26 | (CCWS) Pump Operation | 2008-11-23 | 2008-11-25
4 | Clean & Dirty Oil System |  | 2007-10-31 | 2009-03-03
Activity | 2PF3546W42A18P | (Clean & Dirty LOP) P.O & Procurement | 2007-10-31 | 2008-10-31
Activity | 2EF3546W16A15 | (Clean & Dirty LOP) FDN Design | 2007-10-31 | 2008-03-31
Activity | 2PF3546W42A06P | (Clean Oil Tank) P.O & Procurement | 2007-11-01 | 2008-10-31
Activity | 2EF3546W16A03 | (Clean Oil Tank) FDN Design | 2007-11-01 | 2008-03-31
Activity | 2PF3546W42A12P | (Dirty Oil Tank) P.O & Procurement | 2007-11-01 | 2008-10-31
Activity | 2EF3546W16A09 | (Dirty Oil Tank) FDN Design | 2007-11-01 | 2008-03-31
Activity | 2CF3546W16A04 | (Clean Oil Tank) FDN Work | 2008-05-02 | 2008-07-02
Activity | 2CF3546W16A10 | (Dirty Oil Tank) FDN Work | 2008-05-02 | 2008-07-02
Activity | 2CF3546W16A16 | (Clean & Dirty LOP) FDN Work | 2008-05-02 | 2008-07-02
Activity | 2PF3546W42A07T | (Clean Oil Tank) Transportation | 2008-11-01 | 2008-12-15
Activity | 2PF3546W42A13T | (Dirty Oil Tank) Transportation | 2008-11-01 | 2008-12-15
Activity | 2PF3546W42A19T | (Clean & Dirty LOP) Transportation | 2008-11-01 | 2008-12-15
Activity | 2CF3546W42A08 | (Clean Oil Tank) Installation | 2008-12-16 | 2009-02-14
Activity | 2CF3546W42A14 | (Dirty Oil Tank) Installation | 2008-12-16 | 2009-02-16
Activity | 2CF3546W42A20 | (Clean & Dirty LOP) Installation & Test | 2008-12-16 | 2009-01-15
Activity | 2CF3546W58A21 | (Clean & Dirty Oil System) Piping Work | 2008-12-16 | 2009-03-03
Activity | 2CF3546W74A22 | (Clean & Dirty Oil System) Installation & Test - Elec. | 2009-01-31 | 2009-03-03
Activity | 2CF3546W90A23 | (Clean & Dirty Oil System) Installation & Test - I&C | 2009-01-31 | 2009-03-03
4 | Feed Water System |  | 2007-08-30 | 2009-02-21
Activity | 2PF3015W42A06P | (FWP) P.O & Procurement | 2007-08-30 | 2008-09-30
Activity | 2EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | 2007-10-31
Activity | 2EF3015W32A10 | (FWP Shelter) FDN & Shelter Design | 2007-10-31 | 2008-01-30
Activity | 2EF3015W16A03 | (FWP) FDN Design | 2007-10-31 | 2008-01-30
Activity | 2PF3015W58A14P | (FW PIPING) P.O & Procurement | 2007-11-02 | 2008-07-30
Activity | 2CF3015W16A11 | (FWP Shelter) FDN Work | 2008-01-31 | 2008-04-01
Activity | 2CF3015W16A04 | (FWP) FDN Work | 2008-03-03 | 2008-05-31
Activity | 2CF3015W32A12 | (FWP Shelter) Shelter Structure Work | 2008-04-02 | 2008-06-30
Activity | 2PF3015W58A15T | (FW PIPING) Transportation | 2008-07-31 | 2008-09-13
Activity | 2CF3015W58A16 | (FW PIPING) Piping Work (incl. Insulation) | 2008-09-15 | 2008-12-15
Activity | 2PF3015W42A07T | (FWP) Transportation | 2008-10-01 | 2008-11-14
Activity | 2CF3015W74A18 | (FWS) Installation & Test - Elec. | 2008-11-15 | 2009-01-15
Activity | 2CF3015W90A19 | (FWS) Installation & Test - I&C | 2008-11-15 | 2009-01-15
Activity | 2CF3015W42A08 | (FWP) Installation | 2008-11-15 | 2008-12-27
Activity | 2CF3015W62A17 | (FW PIPING) Hydro Test | 2008-12-16 | 2009-01-13
Activity | 2SF3015W62A20 | (FWS) Loop check | 2009-01-16 | 2009-02-04
Activity | 2SF3015W62A21 | (FWS) System Function Test | 2009-02-05 | 2009-02-18
Activity | 2SF3015W62A22 | (FWS) Pump Operation | 2009-02-19 | 2009-02-21
4 | Chemical Dosing System |  | 2007-09-26 | 2009-02-07
Activity | 2EF3045W00A06 | (Chemical Dosing BLDG) GA & Load Data to Civil Design | 2007-09-26
Activity | 2EF3045W16A07 | (Chemical Dosing BLDG) FDN Design | 2007-09-26 | 2008-01-23
Activity | 2EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | 2007-09-26 | 2008-01-23
Activity | 2PF3045W42A03P | (Chemical Dosing Equip) P.O & Procurement | 2007-09-26 | 2008-08-25
Activity | 2CF3045W16A08 | (Chemical Dosing BLDG) FDN Work | 2008-01-24 | 2008-03-25
Activity | 2CF3045W32A10 | (Chemical Dosing BLDG) Structure Work | 2008-03-26 | 2008-07-25
Activity | 2PF3045W42A04T | (Chemical Dosing Equip) Transportation | 2008-08-26 | 2008-10-09
Activity | 2CF3045W58A16 | (Chemical Dosing System) Piping Work | 2008-10-10 | 2009-01-09
Activity | 2CF3045W42A05 | (Chemical Dosing Equip) Installation | 2008-10-10 | 2008-12-10
Activity | 2CF3045W38A11 | (Chemical Dosing BLDG) Installation & Test - Fire Fighting Sys. | 2008-11-01 | 2008-12-27
Activity | 2CF3045W36A12 | (Chemical Dosing BLDG) Installation & Test - HVAC | 2008-11-01 | 2008-12-27
Activity | 2CF3045W74A13 | (Chemical Dosing BLDG) Installation & Test - Elec | 2008-11-01 | 2008-12-27
Activity | 2CF3045W24A15 | (Chemical Dosing BLDG) Building Finish | 2008-11-01 | 2008-12-27
Activity | 2CF3045W90A14 | (Chemical Dosing BLDG) Installation & Test - I&C | 2008-11-01 | 2008-12-27
Activity | 2CF3045W74A17 | (Chemical Dosing System) Installation & Test - Elec. | 2008-11-05 | 2009-01-05
Activity | 2CF3045W90A18 | (Chemical Dosing System) Installation & Test - I&C | 2008-11-05 | 2009-01-05
Activity | 2SF3045W62A19 | (Chemical Dosing System) Loop chek | 2009-01-10 | 2009-01-24
Activity | 2SF3045W62A20 | (Chemical Dosing System) System Function Test | 2009-01-25 | 2009-01-31
Activity | 2SF3045W62A21 | (Chemical Dosing System) System Operation | 2009-02-01 | 2009-02-07
4 | Sampling System |  | 2007-10-01 | 2009-03-07
Activity | 2PF3040W42A05P | (Sampling Equip) P.O & Procurement | 2007-10-01 | 2008-08-29
Activity | 2EF3040W16A02 | (Sampling Equip) FDN Design | 2008-01-01 | 2008-04-02
Activity | 2CF3040W16A03 | (Sampling Equip) FDN Work | 2008-04-03 | 2008-05-30
Activity | 2PF3040W42A06T | (Sampling Equip) Transportation | 2008-08-30 | 2008-10-15
Activity | 2CF3040W42A07 | (Sampling Equip) Installation | 2008-10-16 | 2008-11-15
Activity | 2CF3040W58A08 | (Sampling System) Piping Work | 2008-11-17 | 2009-02-10
Activity | 2CF3040W74A09 | (Sampling System) Installation & Test - Elec. | 2009-01-10 | 2009-02-10
Activity | 2CF3040W90A10 | (Sampling System) Installation & Test - I&C | 2009-01-10 | 2009-02-10
Activity | 2SF3040W62A11 | (Sampling System) Loop chek | 2009-02-11 | 2009-02-20
Activity | 2SF3040W62A12 | (Sampling System) Chiller Function Test | 2009-02-21 | 2009-02-25
Activity | 2SF3040W62A13 | (Sampling System) Sampling System Function Test | 2009-02-26 | 2009-03-02
Activity | 2SF3040W62A14 | (Sampling System) System Service | 2009-03-03 | 2009-03-07
4 | Condensate System |  | 2007-03-01 | 2009-02-22
5 | Condenser |  | 2007-03-01 | 2009-02-22
Activity | 2EF3020W00A15 | (COND) Condenser Design Data | 2007-03-01 | 2007-04-12
Activity | 2PF3020W42A12P | (COND Flash Box) P.O & Procurement | 2007-10-03 | 2008-07-31
Activity | 2EF3020W16A17 | (COND) FDN Design | 2007-10-03 | 2008-01-30
Activity | 2PF3020W42A20P | (COND) P.O & Procurement | 2007-10-03 | 2008-08-29
Activity | 2PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | 2007-10-03 | 2008-09-11
Activity | 2EF3020W16A09 | (COND Flash Box) FDN Design | 2008-01-02 | 2008-03-31
Activity | 2CF3020W16A18 | (COND) FDN Work | 2008-01-31 | 2008-05-02
Activity | 2EF3020W16A03 | (COND Air EXT Equip) FDN Design | 2008-03-01 | 2008-05-29
Activity | 2CF3020W16A10 | (COND Flash Box) FDN Work | 2008-04-01 | 2008-05-30
Activity | 2CF3020W16A04 | (COND Air EXT Equip) FDN Work | 2008-05-30 | 2008-07-28
Activity | 2PF3020W42A13T | (COND Flash Box) Transportation | 2008-08-01 | 2008-09-15
Activity | 2PF3020W42A21T | (COND) Transportation | 2008-08-30 | 2008-10-14
Activity | 2PF3020W42A07T | (COND Air EXT Equip) Transportation | 2008-09-12 | 2008-10-27
Activity | 2CF3020W42A14 | (COND Flash Box) Installation | 2008-09-16 | 2008-10-14
Activity | 2CF3020W42A22 | (COND) Installation | 2008-10-15 | 2009-01-14
Activity | 2CF3020W58A23 | (COND System) Piping Work(incl. Insulation) | 2008-10-24 | 2009-01-23
Activity | 2CF3020W74A24 | (COND System) Installation & Test - Elec. | 2008-10-24 | 2009-01-17
Activity | 2CF3020W90A25 | (COND System) Installation & Test - I&C | 2008-10-24 | 2009-01-17
Activity | 2CF3020W42A08 | (COND Air EXT Equip) Installation | 2008-10-28 | 2008-12-09
Activity | 2SF3020W62A26 | (COND System) Loop check | 2009-01-24 | 2009-02-07
Activity | 2SF3020W62A27 | (COND System) System Function Test | 2009-02-08 | 2009-02-17
Activity | 2SF3020W62A28 | (COND System) Pump Operation | 2009-02-18 | 2009-02-22
5 | Condenser Tube Cleaning System |  | 2007-10-31 | 2008-12-29
Activity | 2PF3020W42A02P | (CTCS) P.O & Procurement | 2007-10-31 | 2008-10-01
Activity | 2PF3020W42A03T | (CTCS) Transportation | 2008-10-02 | 2008-11-15
Activity | 2CF3020W42A04 | (CTCS) Installation | 2008-11-17 | 2008-12-29
5 | Condensate Extraction Pump |  | 2007-09-07 | 2009-01-12
Activity | 2PF3020W42A04P | (CEP) P.O & Procurement | 2007-09-07 | 2008-09-08
Activity | 2EF3020W16A01 | (CEP) FDN Design | 2007-10-09 | 2008-01-04
Activity | 2CF3020W16A02 | (CEP) FDN Work | 2008-01-05 | 2008-05-07
Activity | 2PF3020W42A05T | (CEP) Transportation | 2008-09-09 | 2008-10-23
Activity | 2CF3020W42A06 | (CEP) Installation | 2008-10-24 | 2009-01-12
4 | Auxiliary Cooling Water System |  | 2007-10-03 | 2009-03-15
Activity | 2PF3030W42A04P | (ACW PUMP) P.O & Procurement | 2007-10-03 | 2008-10-30
Activity | 2PF3030W58A10P | (ACW Piping) P.O & Procurement | 2007-10-03 | 2008-07-31
Activity | 2PF3030W58A11T | (ACW Piping) Transportation | 2008-08-01 | 2008-09-15
Activity | 2CF3030W58A12 | (ACW Piping) Piping Work | 2008-10-08 | 2009-01-08
Activity | 2PF3030W42A05T | (ACW PUMP) Transportation | 2008-10-31 | 2008-12-13
Activity | 2CF3030W42A06 | (ACW PUMP) Installation | 2008-12-15 | 2009-01-08
Activity | 2CF3030W62A13 | (ACW Piping) Hydro Test | 2009-01-09 | 2009-02-06
Activity | 2CF3030W90A08 | (ACW PUMP) Installation - I&C | 2009-01-09 | 2009-01-30
Activity | 2CF3030W74A07 | (ACW PUMP) Installation - Elec | 2009-01-09 | 2009-01-30
Activity | 2SF3030W62A14 | (ACWS) Loop check | 2009-02-24 | 2009-03-05
Activity | 2SF3030W62A15 | (ACWS) System Function Test | 2009-03-06 | 2009-03-10
Activity | 2SF3030W62A16 | (ACWS) Pump Operation | 2009-03-11 | 2009-03-15
4 | Steam System |  | 2007-04-02 | 2009-02-23
Activity | 2EF2510W00A01 | (Steam System) P&ID | 2007-04-02 | 2007-11-14
Activity | 2PF2510W58A08P | (Steam PIPING) P.O & Procurement | 2007-10-01 | 2008-06-02
Activity | 2PF2510W42A04P | (Silencer) P.O & Procurement | 2007-10-15 | 2008-08-14
Activity | 2PF2510W58A09T | (Steam PIPING) Transportation | 2008-06-03 | 2008-07-17
Activity | 2CF2510W58A10 | (Steam PIPING) Piping Work | 2008-07-18 | 2008-12-18
Activity | 2PF2510W42A05T | (Silencer) Transportation | 2008-08-15 | 2008-09-29
Activity | 2CF2510W74A12 | (Steam System) Installation & Test - Elec. | 2008-09-30 | 2008-12-24
Activity | 2CF2510W90A13 | (Steam System) Installation & Test - I&C | 2008-09-30 | 2008-12-24
Activity | 2CF2510W42A06 | (Silencer) Installation | 2008-09-30 | 2008-10-28
Activity | 2CF2510W62A11 | (Steam PIPING) Hydro Test | 2008-12-19 | 2009-01-19
Activity | 2SF2510W62A14 | (Steam System) Loop chek | 2009-01-20 | 2009-02-08
Activity | 2SF2510W62A15 | (Steam System) System Function Test | 2009-02-09 | 2009-02-18
Activity | 2SF2510W62A16 | (Steam System) System Service | 2009-02-19 | 2009-02-23
4 | Bypass System |  | 2007-04-02 | 2009-01-29
Activity | 2EF2510W00A01.1 | (Bypass System) P&ID & System Design | 2007-04-02 | 2007-11-01
Activity | 2PF2510W42A04.1P | (Bypass Valve) P.O & Procurement | 2007-08-20 | 2008-07-15
Activity | 2PF2510W42A05.1T | (Bypass Valve) Transportation | 2008-07-31 | 2008-09-13
Activity | 2CF2510W58A07.1 | (Bypass System) Piping Work | 2008-09-15 | 2008-12-13
Activity | 2CF2510W90A10.1 | (Bypass System) Installation & Test - I&C | 2008-09-15 | 2008-11-14
Activity | 2CF2510W74A09.1 | (Bypass System) Installation & Test - Elec. | 2008-09-15 | 2008-11-14
Activity | 2CF2510W42A06.1 | (Bypass Valve) Installation | 2008-09-15 | 2008-11-14
Activity | 2CF2510W62A08.1 | (Bypass System) Hydro Test | 2008-12-15 | 2008-12-31
Activity | 2SF2510W62A11.1 | (Bypass System) Loop check | 2009-01-01 | 2009-01-14
Activity | 2SF2510W62A12.1 | (Bypass System) System Function Test | 2009-01-15 | 2009-01-24
Activity | 2SF2510W62A13.1 | (Bypass System) System Service | 2009-01-25 | 2009-01-29
4 | Clean Drain System |  | 2007-03-15 | 2009-04-11
Activity | 2EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | 2007-03-15 | 2008-01-15
Activity | 2PF3020W42A12.1P | (Clean Drain Tank) P.O & Procurement | 2007-10-01 | 2008-10-01
Activity | 2PF3020W42A06.1P | (Clean Drain Flash Vessel) P.O & Procurement | 2007-10-03 | 2008-05-02
Activity | 2EF3020W16A03.1 | (Clean Drain Flash Vessel) FDN Design | 2007-10-03 | 2008-02-29
Activity | 2EF3020W16A15.1 | (Clean Drain Pump) FDN Design | 2007-10-03 | 2008-02-29
Activity | 2PF3020W42A18.1P | (Clean Drain Pump) P.O & Procurement | 2007-10-03 | 2008-08-18
Activity | 2EF3020W16A09.1 | (Clean Drain Tank) FDN Design | 2007-12-06 | 2008-05-05
Activity | 2CF3020W16A04.1 | (Clean Drain Flash Vessel) FDN Work | 2008-03-01 | 2008-04-28
Activity | 2CF3020W16A16.1 | (Clean Drain Pump) FDN Work | 2008-03-01 | 2008-05-01
Activity | 2PF3020W42A07.1T | (Clean Drain Flash Vessel) Transportation | 2008-05-03 | 2008-06-17
Activity | 2CF3020W16A10.1 | (Clean Drain Tank) FDN Work | 2008-05-06 | 2008-07-02
Activity | 2CF3020W42A08.1 | (Clean Drain Flash Vessel) Installation | 2008-06-18 | 2008-07-16
Activity | 2PF3020W42A19.1T | (Clean Drain Pump) Transportation | 2008-08-19 | 2008-10-02
Activity | 2PF3020W42A13.1T | (Clean Drain Tank) Transportation | 2008-10-02 | 2008-11-15
Activity | 2CF3020W42A20.1 | (Clean Drain Pump) Installation | 2008-10-03 | 2008-10-31
Activity | 2CF3020W58A21.1 | (Clean Drain System) Piping Work | 2008-11-17 | 2009-02-16
Activity | 2CF3020W42A14.1 | (Clean Drain Tank) Installation | 2008-11-17 | 2008-12-13
Activity | 2CF3020W74A23.1 | (Clean Drain System) Installation & Test - Elec. | 2009-01-16 | 2009-02-16
Activity | 2CF3020W90A24.1 | (Clean Drain System) Installation & Test - I&C | 2009-01-16 | 2009-02-16
Activity | 2CF3020W62A22.1 | (Clean Drain System) Hydro Test | 2009-02-17 | 2009-03-17
Activity | 2SF3020W62A25.1 | (Clean Drain System) Loop chek | 2009-03-18 | 2009-04-06
Activity | 2SF3020W62A26.1 | (Clean Drain System) System Function Test | 2009-04-07 | 2009-04-09
Activity | 2SF3020W62A27.1 | (Clean Drain System) System Service | 2009-04-10 | 2009-04-11
3 | BOP Piping for Block #2 Common |  | 2007-03-01 | 2009-01-31
4 | Gas Supply System (GTG) |  | 2008-06-19 | 2008-08-19
Activity | 2CF3520W58A01 | (Gas Supply System) Piping Work(Yard area) | 2008-06-19 | 2008-08-19
4 | Oil Supply System (GTG) |  | 2008-03-03 | 2008-05-19
Activity | 2CF3520W58A01.1 | (Oil Supply System) Piping Work(Yard area) | 2008-03-03 | 2008-05-02
Activity | 2CF3520W62A02 | (Oil Supply System) Hydro Test | 2008-05-03 | 2008-05-19
4 | Make Up Wate Supply System (STG) |  | 2008-05-19 | 2008-08-04
Activity | 2CF3010W58A01 | (Make Up WTR Supply System) Piping Work(Block #2) | 2008-05-19 | 2008-07-18
Activity | 2CF3010W62A02 | (Make Up WTR Supply System) Hydro Test(Block #2) | 2008-07-19 | 2008-08-04
4 | Water Treatment Sytstem (BOP) |  | 2008-10-17 | 2009-01-01
Activity | 2CF3010W58A01.1 | (Water Treatment System) Piping Work(Block #2) | 2008-10-17 | 2008-12-16
Activity | 2CF3010W62A02.1 | (Water Treatment System) Hydro Test(Block #2) | 2008-12-17 | 2009-01-01
4 | Service Water System (BOP) |  | 2008-10-17 | 2009-01-01
Activity | 2CF3035W58A01 | (SWS) Piping Work(Block #2) | 2008-10-17 | 2008-12-16
Activity | 2CF3035W62A02 | (SWS) Hydro Test(Block #2) | 2008-12-17 | 2009-01-01
4 | Potable Water System (BOP) |  | 2008-11-04 | 2009-01-19
Activity | 2CF3035W58A01.1 | (PWS) Piping Work(Block #2) | 2008-11-04 | 2009-01-02
Activity | 2CF3035W62A02.1 | (PWS) Hydro Test(Block #2) | 2009-01-03 | 2009-01-19
4 | Compressed Air System (BOP) |  | 2008-09-02 | 2008-12-31
Activity | 2CF3510W58A01 | (COMP Air System) Piping Work(incl. Air blowing)_(Block #2) | 2008-09-02 | 2008-12-31
4 | Waste Water Treatment System (BOP) |  | 2008-10-17 | 2009-01-31
Activity | 2CF4035W58A01 | (WWTS) Piping Work(Block #2) | 2008-10-17 | 2009-01-15
Activity | 2CF4035W62A02 | (WWTS) Hydro Test(Block #2) | 2009-01-16 | 2009-01-31
4 | Sewage Water System (BOP) |  | 2008-10-17 | 2009-01-31
Activity | 2CF4035W58A01.1 | (STS) Piping Work(Block #2) | 2008-10-17 | 2009-01-15
Activity | 2CF4035W62A02.1 | (STS) Hydro Test(Block #2) | 2009-01-16 | 2009-01-31
4 | U/G Line |  | 2008-10-17 | 2009-01-16
Activity | 2CF4035W22A01 | (STRS) Piping Work(Block #2) | 2008-10-17 | 2009-01-10
Activity | 2CF4035W22A02 | (SWS) Piping Work(Block #2) | 2008-10-17 | 2009-01-16
4 | Pipe Rack |  | 2007-03-01 | 2008-06-30
Activity | 2EF5550W00A01 | (PipeRack) Pipe Rack Key Data | 2007-03-01 | 2007-03-29
Activity | 2EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | 2007-03-30
Activity | 2EF5550W16A03 | (PipeRack) FDN Design | 2007-05-30 | 2007-08-31
Activity | 2EF5550W20A05 | (PipeRack) Structure Design | 2007-05-30 | 2007-08-31
Activity | 2PF5550W46A08P | (PipeRack) P.O & Procurement | 2007-06-28 | 2008-02-01
Activity | 2CF5550W16A04 | (PipeRack) FDN Work Block #1 Area | 2007-09-01 | 2008-01-01
Activity | 2PF5550W46A09T | (PipeRack) Trasnportation | 2008-02-02 | 2008-03-17
Activity | 2CF5550W46A06 | (PipeRack) Structure Work for Block #1 Area | 2008-03-18 | 2008-06-30
3 | Gas Turbine & Generator #21 & #22 |  | 2007-03-01 | 2009-01-03
4 | GTG Common |  | 2007-03-01 | 2008-08-18
Activity | 2EF1210W00A06 | (GTG Common BLDG) GA & Load Data to Civil Design | 2007-03-01
Activity | 2EF1210W16A07 | (GTG Common BLDG) FDN Design | 2007-03-01 | 2007-08-01
Activity | 2EF1210W20A09 | (GTG Common BLDG) Structure Design | 2007-03-01 | 2007-08-31
Activity | 2EF1200W00A01 | (GTG #21/#22) GTG Process Data (FG, FO, CCW) | 2007-03-01 | 2007-03-30
Activity | 2EF1200W00A02 | (GTG #21/#22) Instrument, Service Air, Aux steam Data | 2007-03-01 | 2007-03-29
Activity | 2EF1200W00A03 | (GTG #21/#22) Utility Consumption Data | 2007-03-01 | 2007-04-26
Activity | 2EF1200W00A04 | (GTG #21/#22) Emergency Load Data | 2007-03-01 | 2007-04-26
Activity | 2EF1200W00A05 | (GTG #21/#22) Black Start Load Data | 2007-03-01 | 2007-04-26
Activity | 2PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | 2007-09-03 | 2008-02-14
Activity | 2CF1210W16A08 | (GTG Common BLDG) FDN Work | 2007-10-02 | 2008-01-30
Activity | 2CF1210W20A10 | (GTG Common BLDG) Structure Work(S/S, Cladding, Roof) | 2008-02-15 | 2008-06-18
Activity | 2CF1210W36A12 | (GTG Common BLDG) Installation & Test - HVAC | 2008-05-15 | 2008-07-11
Activity | 2CF1210W38A11 | (GTG Common BLDG) Installation & Test - Fire Fighting Sys. | 2008-05-31 | 2008-07-28
Activity | 2CF1210W90A14 | (GTG Common BLDG) Installation & Test - I&C | 2008-06-19 | 2008-08-15
Activity | 2CF1210W74A13 | (GTG Common BLDG) Installation & Test - Elec | 2008-06-19 | 2008-08-15
Activity | 2CF1210W24A15 | (GTG Common BLDG) Building Finish | 2008-06-27 | 2008-08-18
4 | GTG #21 LEB |  | 2007-05-31 | 2008-08-04
Activity | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | 2007-05-31
Activity | 2EF1200W16A02 | (GTG #21 LEB) FDN Design | 2007-08-01 | 2007-11-27
Activity | 2EF1200W32A04 | (GTG #21 LEB) Structure Design | 2007-08-01 | 2007-11-27
Activity | 2CF1200W16A03 | (GTG #21 LEB) FDN Work | 2007-11-28 | 2008-01-24
Activity | 2CF1200W32A05 | (GTG #21 LEB) Structure Work | 2008-01-25 | 2008-04-26
Activity | 2CF1200W36A07 | (GTG #21 LEB) Installation & Test - HVAC | 2008-05-15 | 2008-06-30
Activity | 2CF1200W24A10 | (GTG #21 LEB) Building Finish | 2008-05-27 | 2008-08-04
Activity | 2CF1200W38A06 | (GTG #21 LEB) Installation & Test - Fire Fighting Sys. | 2008-05-31 | 2008-07-04
Activity | 2CF1200W90A09 | (GTG #21 LEB) Installation & Test - I&C | 2008-06-04 | 2008-08-04
Activity | 2CF1200W74A08 | (GTG #21 LEB) Installation & Test - Elec | 2008-06-04 | 2008-08-04
4 | GTG #21 |  | 2007-03-30 | 2009-01-03
5 | GTG #21 Main body |  | 2007-03-30 | 2008-09-12
Activity | 2PF1213W42A08P | (GEN #21) P.O & Procurement | 2007-03-30 | 2008-02-29
Activity | 2EF1213W16A06 | (GEN #21) FDN Design | 2007-03-30 | 2007-08-29
Activity | 2PF1213W42A03P | (GT #21) P.O & Procurement | 2007-03-30 | 2008-02-29
Activity | 2EF1213W16A01 | (GT #21) FDN Design | 2007-03-30 | 2007-06-29
Activity | 2CF1213W16A07 | (GEN #21) FDN Work | 2007-08-31 | 2008-01-15
Activity | 2CF1213W16A02 | (GT #21) FDN Work | 2007-08-31 | 2008-01-15
Activity | 2PF1213W42A09T | (GEN #21) Transportation | 2008-03-01 | 2008-04-15
Activity | 2PF1213W42A04T | (GT #21) Transportation | 2008-03-01 | 2008-04-14
Activity | 2CF1213W42A05 | (GT #21) Installation(On FDN~Final Alignment) | 2008-04-15 | 2008-08-28
Activity | 2CF1213W42A10 | (GEN #21) Installation | 2008-05-14 | 2008-09-12
Activity | 2CF1213W52A11 | (GEN #21) Insulation | 2008-06-18 | 2008-07-02
5 | GTG #21 Electrical System |  | 2007-03-30 | 2008-09-26
Activity | 2PF1255W70A01P | (GTG#21 Electrical) P.O & Procurement | 2007-03-30 | 2008-04-29
Activity | 2PF1255W70A02T | (GTG#21 Electrical) Transportation | 2008-04-30 | 2008-06-13
Activity | 2CF1255W70A03 | (GTG#21 Electrical) Installation- PCC | 2008-08-01 | 2008-09-15
Activity | 2CF1255W70A04 | (GTG#21 Electrical) Installation- MCC | 2008-08-01 | 2008-09-15
Activity | 2CF1255W70A05 | (GTG#21 Electrical) Installation- Protection Sys. | 2008-08-01 | 2008-09-15
Activity | 2CF1255W70A07 | (GTG#21 Electrical) Installation- SEE&SFC Sys. | 2008-08-01 | 2008-09-15
Activity | 2CF1255W70A08 | (GTG#21 Electrical) Installation- DC&UPS Sys. | 2008-08-01 | 2008-09-15
Activity | 2CF1255W74A09 | (GTG#21 Electrical) Cable work | 2008-08-01 | 2008-09-15
Activity | 2CF1255W86A06 | (GTG#21 Electrical) Installation- GT control Sys. | 2008-08-04 | 2008-09-15
Activity | 2CF1255W62A10 | (GTG#21 Electrical) Electrical Function Test | 2008-09-16 | 2008-09-20
Activity | 2CF1255W62A11 | (GTG#21 Electrical) Loop Test | 2008-09-22 | 2008-09-26
5 | GTG #21 Starting System(Turning Device) |  | 2007-03-30 | 2008-06-25
Activity | 2PF1265W42A01P | (Turning Gear) P.O & Procurement | 2007-03-30 | 2008-03-31
Activity | 2PF1265W42A02T | (Turning Gear) Transportation | 2008-04-01 | 2008-05-15
Activity | 2CF1265W42A03 | (Turning Gear) Installation | 2008-05-16 | 2008-05-23
Activity | 2CF1265W74A04 | (Turning Gear) Installation- Elec. | 2008-05-24 | 2008-05-31
Activity | 2CF1265W90A05 | (Turning Gear) Installation- I&C | 2008-05-24 | 2008-05-31
Activity | 2SF1265W62A06 | (Turning Gear) Loop check | 2008-06-01 | 2008-06-05
Activity | 2SF1265W62A07.0 | (Turning Gear) Function Test | 2008-06-23 | 2008-06-25
5 | GTG #21 Air and Flue Gas System |  | 2007-03-30 | 2008-06-17
Activity | 2PF1265W64A01P | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | 2007-03-30 | 2008-02-29
Activity | 2PF1265W64A02T | (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | 2008-03-01 | 2008-04-15
Activity | 2CF1265W64A03 | (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | 2008-04-16 | 2008-05-16
Activity | 2CF1265W64A04 | (Air&Flue Gas System) Duct work | 2008-05-17 | 2008-05-31
Activity | 2CF1265W74A05 | (Air&Flue Gas System) Installation- Elec. | 2008-06-02 | 2008-06-14
Activity | 2CF1265W90A06 | (Air&Flue Gas System) Installation- I&C | 2008-06-02 | 2008-06-14
Activity | 2SF1265W62A07 | (Air&Flue Gas System) Loop chek | 2008-06-12 | 2008-06-14
Activity | 2SF1265W62A08 | (Air&Flue Gas System) Function Test | 2008-06-15 | 2008-06-17
5 | GTG #21 Air Intake System |  | 2007-03-30 | 2008-07-15
Activity | 2PF1230W20A02P | (Air Intake) P.O & Procurement_Steel Sturucture | 2007-03-30 | 2008-02-29
Activity | 2PF1230W64A05P | (Air Intake) P.O & Procurement_Inlet Duct | 2007-03-30 | 2008-02-29
Activity | 2PF1230W64A08P | (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2007-03-30 | 2008-02-29
Activity | 2CF1230W16A01 | (Air Intake) FDN Work_Steel Sturucture | 2007-10-31 | 2007-12-31
Activity | 2PF1230W20A03T | (Air Intake) Transportation_Steel Sturucture | 2008-03-01 | 2008-04-15
Activity | 2PF1230W64A06T | (Air Intake) Transportation_Inlet Duct | 2008-03-01 | 2008-04-15
Activity | 2PF1230W64A09T | (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-03-01 | 2008-04-15
Activity | 2CF1230W20A04 | (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | 2008-04-16 | 2008-05-17
Activity | 2CF1230W64A07 | (Air Intake) Installation_Inlet Duct | 2008-05-19 | 2008-05-26
Activity | 2CF1230W64A10 | (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-05-27 | 2008-06-19
Activity | 2CF1230W74A11 | (Air Intake) Installation- Elec. | 2008-06-20 | 2008-07-03
Activity | 2CF1230W90A12 | (Air Intake) Installation- I&C | 2008-06-20 | 2008-07-03
Activity | 2SF1230W62A13 | (Air Intake) Loop chek | 2008-07-04 | 2008-07-06
Activity | 2SF1230W62A14 | (Air Intake) Function Test | 2008-07-10 | 2008-07-12
Activity | 2SF1230W62A15 | (Air Intake) Load(Running) Test | 2008-07-13 | 2008-07-15
5 | GTG #21 Lube Oil System |  | 2007-03-30 | 2008-06-22
Activity | 2PF1250W42A02P | (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | 2007-03-30 | 2008-02-28
Activity | 2PF1250W42A06P | (Lube Oil System) P.O & Procurement_Lube oil functional Module | 2007-03-30 | 2008-02-28
Activity | 2PF1250W42A10P | (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | 2007-03-30 | 2008-02-28
Activity | 2CF1250W16A01 | (Lube Oil System) FDN Work_Lube Oil Supply Module | 2007-10-31 | 2007-12-31
Activity | 2CF1250W16A05 | (Lube Oil System) FDN Work_Lube oil functional Module | 2007-10-31 | 2007-12-31
Activity | 2CF1250W16A09 | (Lube Oil System) FDN Work_Lube oil Mist Separator | 2007-10-31 | 2007-12-31
Activity | 2PF1250W42A03T | (Lube Oil System) Transportation_Lube Oil Supply Module | 2008-02-29 | 2008-04-14
Activity | 2PF1250W42A07T | (Lube Oil System) Transportation_Lube oil functional Module | 2008-02-29 | 2008-04-14
Activity | 2PF1250W42A11T | (Lube Oil System) Transportation_Lube oil Mist Separator | 2008-02-29 | 2008-04-14
Activity | 2CF1250W42A04 | (Lube Oil System) Installation_Lube Oil Supply Module | 2008-04-15 | 2008-04-30
Activity | 2CF1250W42A08 | (Lube Oil System) Installation_Lube oil functional Module | 2008-04-15 | 2008-04-30
Activity | 2CF1250W42A12 | (Lube Oil System) Installation_Lube oil Mist Separator | 2008-04-15 | 2008-04-22
Activity | 2CF1250W58A13 | (Lube Oil System) Piping work | 2008-05-01 | 2008-05-31
Activity | 2CF1250W62A16 | (GTG #11) Lube Oil Flushing | 2008-05-31 | 2008-06-17
Activity | 2CF1250W74A14 | (Lube Oil System) Installation- Elec. | 2008-06-02 | 2008-06-14
Activity | 2CF1250W90A15 | (Lube Oil System) Installation- I&C | 2008-06-02 | 2008-06-14
Activity | 2SF1250W62A17 | (Lube Oil System) Loop chek | 2008-06-15 | 2008-06-17
Activity | 2SF1250W62A18 | (Lube Oil System) Function Test | 2008-06-18 | 2008-06-20
Activity | 2SF1250W62A19 | (Lube Oil System) Load Test | 2008-06-21 | 2008-06-22
5 | GTG #21 Generator Seal Oil System |  | 2007-03-30 | 2008-06-19
Activity | 2PF1250W42A02.1P | (GEN Seal Oil Sys.) P.O & Procurement | 2007-03-30 | 2008-02-28
Activity | 2CF1250W16A01.1 | (GEN Seal Oil Sys.) FDN Work | 2007-10-31 | 2008-01-25
Activity | 2PF1250W42A03.1T | (GEN Seal Oil Sys.) Transportation | 2008-02-29 | 2008-04-14
Activity | 2CF1250W42A04.1 | (GEN Seal Oil Sys.) Installation | 2008-04-15 | 2008-04-29
Activity | 2CF1250W58A05.1 | (GEN Seal Oil Sys.) Piping Work | 2008-04-30 | 2008-05-30
Activity | 2CF1250W74A06.1 | (GEN Seal Oil Sys.) Installation- Elec. | 2008-05-31 | 2008-06-13
Activity | 2CF1250W90A07.1 | (GEN Seal Oil Sys.) Installation- I&C | 2008-05-31 | 2008-06-13
Activity | 2SF1250W62A08.1 | (GEN Seal Oil Sys.) Oil Flushing | 2008-05-31 | 2008-06-04
Activity | 2SF1250W62A09.1 | (GEN Seal Oil Sys.) Loop chek | 2008-06-14 | 2008-06-16
Activity | 2SF1250W62A10.1 | (GEN Seal Oil Sys.) Function Test | 2008-06-17 | 2008-06-19
5 | GTG #21 Fuel Gas Supply System |  | 2007-03-30 | 2008-09-24
Activity | 2PF1265W42A03P | (Gas Final Filter & Metering Skid) P.O & Procurement | 2007-03-30 | 2008-02-28
Activity | 2EF1265W16A01 | (Gas Final Filter & Metering Skid) FDN Design | 2007-03-30 | 2007-10-01
Activity | 2PF1265W42A13P | (TCA Cooler) P.O & Procurement | 2007-03-30 | 2008-03-31
Activity | 2CF1265W16A02 | (Gas Final Filter & Metering Skid) FDN Work | 2007-10-02 | 2007-12-27
Activity | 2CF1265W16A12 | (TCA Cooler) FDN Work | 2007-10-31 | 2007-12-31
Activity | 2PF1265W42A04T | (Gas Final Filter & Metering Skid) Transportation | 2008-02-29 | 2008-04-14
Activity | 2PF1265W42A14T | (TCA Cooler) Transportation | 2008-04-01 | 2008-05-15
Activity | 2CF1265W42A05 | (Gas Final Filter & Metering Skid) Installation | 2008-04-15 | 2008-05-16
Activity | 2CF1265W42A15 | (TCA Cooler) Installation | 2008-05-16 | 2008-06-16
Activity | 2CF1265W58A06 | (FGSS) Piping Work(incl. Airblowing Test)_Power block Area | 2008-06-19 | 2008-08-04
Activity | 2CF1265W74A07 | (FGSS) Installation- Elec. | 2008-08-05 | 2008-08-18
Activity | 2CF1265W90A08 | (FGSS) Installation- I&C | 2008-08-05 | 2008-08-18
Activity | 2SF1265W62A09 | (FGSS) Loop chek | 2008-09-03 | 2008-09-12
Activity | 2SF1265W62A10.0 | (FGSS) Function Test | 2008-09-13 | 2008-09-17
Activity | 2SF1265W62A11.0 | (FGSS) Gas Receiving upto GT Final Control Valve | 2008-09-22 | 2008-09-24
5 | GTG #21 Washing & Drain System |  | 2007-03-30 | 2008-08-14
Activity | 2PF1265W42A02.0P | (Washing & Drain system Skid) P.O & Procurement | 2007-03-30 | 2008-03-31
Activity | 2CF1265W16A01 | (Washing & Drain system Skid) FDN Work | 2007-10-31 | 2007-12-31
Activity | 2PF1265W42A03.0T | (Washing & Drain system Skid) Transportation | 2008-04-01 | 2008-05-15
Activity | 2CF1265W42A04 | (Washing & Drain system Skid) Installation | 2008-05-16 | 2008-06-02
Activity | 2CF1265W58A05 | (Washing & Drain system Skid) Piping work | 2008-06-03 | 2008-07-03
Activity | 2CF1265W74A06 | (Washing & Drain system Skid) Installation- Elec. | 2008-07-04 | 2008-07-17
Activity | 2CF1265W90A07 | (Washing & Drain system Skid) Installation- I&C | 2008-07-04 | 2008-07-17
Activity | 2CF1265W62A08 | (Washing & Drain system Skid) Flushing | 2008-07-04 | 2008-07-07
Activity | 2SF1265W62A09.0 | (Washing & Drain system Skid) Loop chek | 2008-07-18 | 2008-07-22
Activity | 2SF1265W62A10 | (Washing & Drain system Skid) Function Test | 2008-07-23 | 2008-07-25
Activity | 2SF1265W62A11 | (Washing & Drain system Skid) Load(Running) Test | 2008-08-12 | 2008-08-14
5 | GTG #21 Fuel Oil Injection System |  | 2007-03-30 | 2008-09-02
Activity | 2PF1265W42A02.2P | (Fuel oil injection System) P.O & Procurement | 2007-03-30 | 2008-03-31
Activity | 2PF1265W42A09P | (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | 2007-03-30 | 2008-02-29
Activity | 2PF1265W42A16P | (Water injection System) P.O & Procurement | 2007-03-30 | 2008-02-29
Activity | 2CF1265W16A01.0 | (Fuel oil injection System) FDN Work | 2007-10-31 | 2007-12-31
Activity | 2CF1265W16A08 | (Fuel oil injection Pump & actuator) FDN Work | 2007-10-31 | 2007-12-31
Activity | 2CF1265W16A15 | (Water injection System) FDN Work | 2007-10-31 | 2007-12-31
Activity | 2PF1265W42A10T | (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | 2008-03-01 | 2008-04-15
Activity | 2PF1265W42A17T | (Water injection System) Transportation | 2008-03-01 | 2008-04-15
Activity | 2PF1265W42A03.2T | (Fuel oil injection System) Transportation | 2008-04-01 | 2008-05-15
Activity | 2CF1265W42A11 | (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | 2008-04-16 | 2008-04-30
Activity | 2CF1265W42A18 | (Water injection System) Installation | 2008-04-16 | 2008-04-30
Activity | 2CF1265W58A19 | (Water injection System) Piping work | 2008-05-01 | 2008-05-15
Activity | 2CF1265W42A04.0 | (Fuel oil injection System) Installation | 2008-05-16 | 2008-05-30
Activity | 2CF1265W74A20 | (Water injection System) Installation- Elec. | 2008-05-16 | 2008-05-29
Activity | 2CF1265W90A21 | (Water injection System) Installation- I&C | 2008-05-16 | 2008-05-29
Activity | 2SF1265W62A22 | (Water injection System) Loop chek | 2008-05-30 | 2008-06-03
Activity | 2CF1265W58A05.0 | (Fuel oil injection System) Piping work | 2008-05-31 | 2008-06-14
Activity | 2SF1265W62A23 | (Water injection System) Function Test | 2008-06-04 | 2008-06-06
Activity | 2CF1265W74A06.0 | (Fuel oil injection System) Installation- Elec. | 2008-06-16 | 2008-06-28
Activity | 2CF1265W90A07.0 | (Fuel oil injection System) Installation- I&C | 2008-06-16 | 2008-06-28
Activity | 2SF1265W62A12 | (Fuel oil injection System) Loop chek | 2008-06-29 | 2008-07-01
Activity | 2SF1265W62A24 | (Water injection System) Load Test | 2008-08-12 | 2008-08-13
Activity | 2SF1265W62A13 | (Fuel oil injection System) Function Test | 2008-08-15 | 2008-08-19
Activity | 2SF1265W62A14 | (Fuel oil injection System) Flushing | 2008-08-30 | 2008-09-02
5 | GTG #21 Vibration Monitoring System (VMS) |  | 2007-08-31 | 2008-09-10
Activity | 2PF1260W86A02P | (VMS) P.O & Procurement for GT | 2007-08-31 | 2008-06-02
Activity | 2PF1260W86A03T | (VMS) Transportation for GT | 2008-06-03 | 2008-07-17
Activity | 2CF1260W86A04 | (VMS) Installation for GT | 2008-08-29 | 2008-09-05
Activity | 2SF1260W62A05 | (VMS) Function Test for GT | 2008-09-06 | 2008-09-10
5 | GTG #21 Closed Cooling Water System |  | 2007-03-30 | 2008-08-19
Activity | 2EF1225W00A01 | (CCWS) CCW H/EX key data | 2007-03-30 | 2007-05-30
Activity | 2PF1225W42A18P | (EXP Head Tank) P.O & Procurement | 2007-07-03 | 2008-04-30
Activity | 2EF1225W16A15 | (EXP Head Tank) FDN Design | 2007-07-03 | 2007-11-29
Activity | 2PF1225W42A12P | (CCWP) P.O & Procurement for GT | 2007-07-03 | 2008-04-30
Activity | 2EF1225W16A09 | (CCWP) FDN Design | 2007-07-03 | 2007-11-29
Activity | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | 2007-07-03 | 2008-04-30
Activity | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | 2007-07-03 | 2007-11-29
Activity | 2CF1225W16A10 | (CCWP) FDN Work | 2007-11-30 | 2008-01-26
Activity | 2CF1225W16A03 | (CCW H/EX) FDN Work_Fin fan cooler | 2007-11-30 | 2008-02-25
Activity | 2CF1225W16A16 | (EXP Head Tank) FDN Work | 2008-01-01 | 2008-01-29
Activity | 2PF1225W42A19T | (EXP Head Tank) Transportation | 2008-05-01 | 2008-06-14
Activity | 2PF1225W42A13T | (CCWP) Transportation for GT | 2008-05-01 | 2008-06-14
Activity | 2PF1225W42A06T | (CCW H/EX) Transportation_Fin fan cooler | 2008-05-01 | 2008-06-14
Activity | 2CF1225W58A21 | (CCWS) Piping Work | 2008-05-27 | 2008-07-30
Activity | 2CF1225W42A20 | (EXP Head Tank) Installation | 2008-06-16 | 2008-07-14
Activity | 2CF1225W42A14 | (CCWP) Installation | 2008-06-16 | 2008-06-30
Activity | 2CF1225W42A07 | (CCW H/EX) Installation_Fin fan cooler | 2008-06-16 | 2008-07-30
Activity | 2CF1225W74A22 | (CCWS) Installation & Test - Elec. | 2008-06-30 | 2008-07-30
Activity | 2CF1225W90A23 | (CCWS) Installation & Test - I&C | 2008-06-30 | 2008-07-30
Activity | 2SF1225W62A24 | (CCWS) Loop chek | 2008-07-31 | 2008-08-09
Activity | 2SF1225W62A25 | (CCWS) Function Test | 2008-08-10 | 2008-08-14
Activity | 2SF1225W62A26 | (CCWS) Flushing | 2008-08-15 | 2008-08-19
5 | GTG #21 Fire fighting System |  | 2007-03-30 | 2008-08-04
Activity | 2PF1265W38A01P | (F/F GTG#21) P.O & Procurement_CO2 FF System | 2007-03-30 | 2008-04-14
Activity | 2PF1265W38A04P | (F/F GTG#21)P.O & Procurement_Clean Agent FF System | 2007-03-30 | 2008-04-14
Activity | 2PF1265W38A02T | (F/F GTG#21) Transportation_CO2 FF System | 2008-04-15 | 2008-05-29
Activity | 2PF1265W38A05T | (F/F GTG#21) Transportation_Clean Agent FF System | 2008-04-15 | 2008-05-29
Activity | 2CF1265W38A03 | (F/F GTG#21) Installation_CO2 FF System | 2008-05-30 | 2008-06-13
Activity | 2CF1265W38A06 | (F/F GTG#21) Installation_Clean Agent FF System | 2008-05-30 | 2008-06-13
Activity | 2CF1265W38A07 | (F/F GTG#21) Piping work | 2008-06-14 | 2008-07-08
Activity | 2SF1265W62A08.2 | (F/F GTG#21) Loop chek | 2008-07-09 | 2008-07-15
Activity | 2SF1265W62A09.2 | (F/F GTG#21) Function Test(incl. Alarm Test) | 2008-07-16 | 2008-07-25
Activity | 2SF1265W62A10.2 | (F/F GTG#21) CO2 Discharge Test | 2008-07-26 | 2008-08-04
5 | GTG #21 Auxiliary System |  | 2007-03-30 | 2008-07-09
Activity | 2PF1265W42A02.3P | (Purge Air System) P.O & Procurement | 2007-03-30 | 2008-02-29
Activity | 2PF1265W42A12P | (Control Oil) P.O & Procurement | 2007-03-30 | 2008-02-29
Activity | 2CF1265W16A01.3 | (Purge Air System) FDN Work | 2007-10-31 | 2007-12-31
Activity | 2CF1265W16A11 | (Control Oil) FDN Work | 2007-10-31 | 2007-12-31
Activity | 2PF1265W42A03.3T | (Purge Air System) Transportation | 2008-03-01 | 2008-04-15
Activity | 2PF1265W42A13.0T | (Control Oil)Transportation | 2008-03-01 | 2008-04-15
Activity | 2CF1265W42A04.3 | (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | 2008-04-16 | 2008-04-30
Activity | 2CF1265W42A14 | (Control Oil) Installation | 2008-04-16 | 2008-04-30
Activity | 2CF1265W58A05.3 | (Purge Air System) Piping work | 2008-05-01 | 2008-05-15
Activity | 2CF1265W58A15 | (Control Oil) Piping work | 2008-05-01 | 2008-05-31
Activity | 2CF1265W74A06.3 | (Purge Air System) Installation- Elec. | 2008-05-16 | 2008-05-29
Activity | 2CF1265W90A07.3 | (Purge Air System) Installation- I&C | 2008-05-16 | 2008-05-29
Activity | 2SF1265W62A08.3 | (Purge Air System) Loop chek | 2008-05-30 | 2008-06-01
Activity | 2SF1265W62A09.3 | (Purge Air System) Function Test | 2008-06-02 | 2008-06-04
Activity | 2CF1265W74A16 | (Control Oil) Installation- Elec. | 2008-06-02 | 2008-06-14
Activity | 2CF1265W90A17 | (Control Oil) Installation- I&C | 2008-06-02 | 2008-06-14
Activity | 2SF1265W62A10.3 | (Purge Air System) Load Test | 2008-06-05 | 2008-06-07
Activity | 2SF1265W62A18 | (Control Oil) Loop chek | 2008-06-15 | 2008-06-19
Activity | 2SF1265W62A19 | (Control Oil) Function Test | 2008-06-20 | 2008-06-29
Activity | 2SF1265W62A20 | (Control Oil) Flushing | 2008-06-30 | 2008-07-09
5 | GTG #21 Commissioning |  | 2008-09-29 | 2009-01-03
Activity | 2SF9011W62A01 | (GTG #21) Fuel Gas System Final Function Test | 2008-09-29 | 2008-10-01
Activity | 2SF9011W62A02 | (GTG #21) Turning Gear Operation | 2008-10-02 | 2008-10-03
Activity | 2SF9011W62A03 | (GTG #21) Initial Firing with FSNL | 2008-10-04 | 2008-10-04
Activity | 2SF9012W62A04 | (GTG #21) TBN & GEN Protection Test | 2008-10-05 | 2008-10-06
Activity | 2SF9012W62A05 | (GTG #21) 1st Synchronization | 2008-10-07 | 2008-10-08
Activity | 2SF9012W62A06 | (GTG #21) Optimization with Fuel Gas | 2008-10-09 | 2008-10-23
Activity | 2SF9012W62A07 | (GTG #21) Fuel Oil System Final Function Test | 2008-10-24 | 2008-11-02
Activity | 2SF9012W62A08 | (GTG #21) Optimization with Fuel Oil | 2008-11-03 | 2008-12-02
Activity | 2SF9012W62A09 | (GTG #21) Black start Test with GT | 2008-12-03 | 2008-12-03
Activity | 2SF9012W62A13 | (GTG #21) Fuel Change-Over Test | 2008-12-03 | 2008-12-15
Activity | 2SF9012W62A10 | (GTG #21) Trial Run Test | 2008-12-04 | 2008-12-04
Activity | 2SF9013W62A11 | (GTG #21) Reliability Test | 2008-12-05 | 2008-12-19
Activity | 2SF9013W62A12 | (GTG #21) Performance Test (Fuel Gas & Fuel Oil) | 2008-12-20 | 2009-01-03
4 | GTG #22 |  | 2007-03-30 | 2009-01-03
5 | GTG #22 Main body |  | 2007-03-30 | 2008-09-15
Activity | 2PF1213W42A08.1P | (Gen #22) P.O & Procurement | 2007-03-30 | 2008-02-29
Activity | 2EF1213W16A06.1 | (Gen #22) FDN Design | 2007-03-30 | 2007-08-29
Activity | 2PF1213W42A03.1P | (GT #22) P.O & Procurement | 2007-03-30 | 2008-03-31
Activity | 2EF1213W16A01.1 | (GT #22) FDN Design | 2007-03-30 | 2007-08-29
Activity | 2CF1213W16A07.1 | (Gen #22) FDN Work | 2007-08-30 | 2008-01-14
Activity | 2CF1213W16A02.1 | (GT #22) FDN Work | 2007-08-30 | 2008-01-14
Activity | 2PF1213W42A09.1T | (Gen #22) Transportation | 2008-03-01 | 2008-04-15
Activity | 2PF1213W42A04.1T | (GT #22) Transportation | 2008-04-01 | 2008-05-14
Activity | 2CF1213W42A10.1 | (Gen #22) Installation | 2008-04-16 | 2008-08-16
Activity | 2CF1213W42A05.1 | (GT #22) Installation(On FDN~Final Alignment) | 2008-05-15 | 2008-09-15
Activity | 2CF1213W52A11.1 | (GT #22) Insulation | 2008-06-19 | 2008-07-03
5 | GTG #22 Electrical System |  | 2007-03-30 | 2008-09-26
Activity | 2PF1255W70A01.1P | (GTG#22 Electrical) P.O & Procurement | 2007-03-30 | 2008-04-29
Activity | 2PF1255W70A02.1T | (GTG#22 Electrical) Transportation | 2008-04-30 | 2008-06-13
Activity | 2CF1255W70A03.1 | (GTG#22 Electrical) Installation- PCC | 2008-08-01 | 2008-09-15
Activity | 2CF1255W70A04.1 | (GTG#22 Electrical) Installation- MCC | 2008-08-01 | 2008-09-15
Activity | 2CF1255W70A05.1 | (GTG#22 Electrical) Installation- Protection Sys. | 2008-08-01 | 2008-09-15
Activity | 2CF1255W70A07.1 | (GTG#22 Electrical) Installation- SEE&SFC Sys. | 2008-08-01 | 2008-09-15
Activity | 2CF1255W70A08.1 | (GTG#22 Electrical) Installation- DC&UPS Sys. | 2008-08-01 | 2008-09-15
Activity | 2CF1255W74A09.1 | (GTG#22 Electrical) Cable work | 2008-08-01 | 2008-09-15
Activity | 2CF1255W86A06.1 | (GTG#22 Electrical) Installation- GT control Sys. | 2008-08-04 | 2008-09-15
Activity | 2CF1255W62A10.1 | (GTG#22 Electrical) Electrical Function Test | 2008-09-16 | 2008-09-20
Activity | 2CF1255W62A11.1 | (GTG#22 Electrical) Loop Test | 2008-09-22 | 2008-09-26
5 | GTG #22 Starting System(Turning Device) |  | 2007-03-30 | 2008-06-27
Activity | 2PF1265W42A01.1P | (Turning Gear) P.O & Procurement | 2007-03-30 | 2008-03-31
Activity | 2PF1265W42A02.1T | (Turning Gear) Transportation | 2008-04-01 | 2008-05-15
Activity | 2CF1265W42A03.1 | (Turning Gear) Installation | 2008-05-16 | 2008-05-23
Activity | 2CF1265W74A04.1 | (Turning Gear) Installation- Elec. | 2008-05-24 | 2008-05-31
Activity | 2CF1265W90A05.1 | (Turning Gear) Installation- I&C | 2008-05-24 | 2008-05-31
Activity | 2SF1265W62A06.1 | (Turning Gear) Loop check | 2008-06-01 | 2008-06-05
Activity | 2SF1265W62A07.1 | (Turning Gear) Function Test | 2008-06-25 | 2008-06-27
5 | GTG #22 Air Intake System |  | 2007-03-30 | 2008-07-15
Activity | 2PF1230W20A02.1P | (Air Intake) P.O & Procurement_Steel Sturucture | 2007-03-30 | 2008-02-29
Activity | 2PF1230W64A05.1P | (Air Intake) P.O & Procurement_Inlet Duct | 2007-03-30 | 2008-02-29
Activity | 2PF1230W64A08.1P | (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2007-03-30 | 2008-02-29
Activity | 2CF1230W16A01.1 | (Air Intake) FDN Work_Steel Sturucture | 2007-10-30 | 2007-12-29
Activity | 2PF1230W20A03.1T | (Air Intake) Transportation_Steel Sturucture | 2008-03-01 | 2008-04-15
Activity | 2PF1230W64A06.1T | (Air Intake) Transportation_Inlet Duct | 2008-03-01 | 2008-04-15
Activity | 2PF1230W64A09.1T | (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-03-01 | 2008-04-15
Activity | 2CF1230W20A04.1 | (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | 2008-05-01 | 2008-05-17
Activity | 2CF1230W64A07.1 | (Air Intake) Installation_Inlet Duct | 2008-05-19 | 2008-05-26
Activity | 2CF1230W64A10.1 | (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-05-27 | 2008-06-19
Activity | 2CF1230W74A11.1 | (Air Intake) Installation- Elec. | 2008-06-20 | 2008-07-03
Activity | 2CF1230W90A12.1 | (Air Intake) Installation- I&C | 2008-06-20 | 2008-07-03
Activity | 2SF1230W62A13.1 | (Air Intake) Loop chek | 2008-07-04 | 2008-07-06
Activity | 2SF1230W62A14.1 | (Air Intake) Function Test | 2008-07-10 | 2008-07-12
Activity | 2SF1230W62A15.1 | (Air Intake) Load(Running) Test | 2008-07-13 | 2008-07-15
5 | GTG #22 Air and Flue Gas System |  | 2007-03-30 | 2008-06-17
Activity | 2PF1265W64A01.1P | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | 2007-03-30 | 2008-02-29
Activity | 2PF1265W64A02.1T | (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | 2008-03-01 | 2008-04-15
Activity | 2CF1265W64A03.1 | (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | 2008-04-16 | 2008-05-16
Activity | 2CF1265W64A04.1 | (Air&Flue Gas System) Duct work | 2008-05-17 | 2008-05-31
Activity | 2CF1265W74A06.1 | (Air&Flue Gas System) Installation- Elec. | 2008-06-02 | 2008-06-14
Activity | 2CF1265W90A07.1 | (Air&Flue Gas System) Installation- I&C | 2008-06-02 | 2008-06-14
Activity | 2SF1265W62A05.1 | (Air&Flue Gas System) Loop chek | 2008-06-12 | 2008-06-14
Activity | 2SF1265W62A08.1 | (Air&Flue Gas System) Function Test | 2008-06-15 | 2008-06-17
5 | GTG #22 Lube Oil System |  | 2007-03-30 | 2008-06-24
Activity | 2PF1250W42A02.2P | (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | 2007-03-30 | 2008-02-29
Activity | 2PF1250W42A06.2P | (Lube Oil System) P.O & Procurement_Lube oil functional Module | 2007-03-30 | 2008-02-29
Activity | 2PF1250W42A10.2P | (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | 2007-03-30 | 2008-02-29
Activity | 2CF1250W16A01.2 | (Lube Oil System) FDN Work_Lube Oil Supply Module | 2007-10-30 | 2007-12-29
Activity | 2CF1250W16A05.2 | (Lube Oil System) FDN Work_Lube oil functional Module | 2007-10-30 | 2007-12-29
Activity | 2CF1250W16A09.2 | (Lube Oil System) FDN Work_Lube oil Mist Separator | 2007-10-30 | 2007-12-29
Activity | 2PF1250W42A03.2T | (Lube Oil System) Transportation_Lube Oil Supply Module | 2008-03-01 | 2008-04-15
Activity | 2PF1250W42A07.2T | (Lube Oil System) Transportation_Lube oil functional Module | 2008-03-01 | 2008-04-15
Activity | 2PF1250W42A11.2T | (Lube Oil System) Transportation_Lube oil Mist Separator | 2008-03-01 | 2008-04-15
Activity | 2CF1250W42A04.2 | (Lube Oil System) Installation_Lube Oil Supply Module | 2008-04-16 | 2008-05-01
Activity | 2CF1250W42A08.2 | (Lube Oil System) Installation_Lube oil functional Module | 2008-04-16 | 2008-05-01
Activity | 2CF1250W42A12.2 | (Lube Oil System) Installation_Lube oil Mist Separator | 2008-04-16 | 2008-04-23
Activity | 2CF1250W58A13.2 | (Lube Oil System) Piping work | 2008-05-02 | 2008-06-02
Activity | 2CF1250W62A16.2 | (GTG #22) Lube Oil Flushing | 2008-06-02 | 2008-06-18
Activity | 2CF1250W74A14.2 | (Lube Oil System) Installation- Elec. | 2008-06-03 | 2008-06-16
Activity | 2CF1250W90A15.2 | (Lube Oil System) Installation- I&C | 2008-06-03 | 2008-06-16
Activity | 2SF1250W62A17.2 | (Lube Oil System) Loop chek | 2008-06-17 | 2008-06-19
Activity | 2SF1250W62A18.2 | (Lube Oil System) Function Test | 2008-06-20 | 2008-06-22
Activity | 2SF1250W62A19.2 | (Lube Oil System) Load Test | 2008-06-23 | 2008-06-24
5 | GTG #22 Generator Seal Oil System |  | 2007-03-30 | 2008-06-20
Activity | 2PF1250W42A02.3P | (GEN Seal Oil Sys.) P.O & Procurement | 2007-03-30 | 2008-02-29
Activity | 2CF1250W16A01.3 | (GEN Seal Oil Sys.) FDN Work | 2007-10-30 | 2008-01-24
Activity | 2PF1250W42A03.3T | (GEN Seal Oil Sys.) Transportation | 2008-03-01 | 2008-04-15
Activity | 2CF1250W42A04.3 | (GEN Seal Oil Sys.) Installation | 2008-04-16 | 2008-04-30
Activity | 2CF1250W58A05.3 | (GEN Seal Oil Sys.) Piping Work | 2008-05-01 | 2008-05-31
Activity | 2CF1250W74A07.3 | (GEN Seal Oil Sys.) Installation- Elec. | 2008-06-02 | 2008-06-14
Activity | 2CF1250W90A08.3 | (GEN Seal Oil Sys.) Installation- I&C | 2008-06-02 | 2008-06-14
Activity | 2SF1250W62A06.3 | (GEN Seal Oil Sys.) Oil Flushing | 2008-06-02 | 2008-06-06
Activity | 2SF1250W62A09.3 | (GEN Seal Oil Sys.) Loop chek | 2008-06-15 | 2008-06-17
Activity | 2SF1250W62A10.3 | (GEN Seal Oil Sys.) Function Test | 2008-06-18 | 2008-06-20
5 | GTG #22 Fuel Gas Supply System |  | 2007-03-30 | 2008-09-24
Activity | 2PF1265W42A03.4P | (Gas Final Filter & Metering Skid) P.O & Procurement | 2007-03-30 | 2008-02-29
Activity | 2EF1265W16A01.4 | (Gas Final Filter & Metering Skid) FDN Design | 2007-03-30 | 2007-10-01
Activity | 2PF1265W42A13.4P | (TCA Cooler) P.O & Procurement | 2007-03-30 | 2008-03-31
Activity | 2CF1265W16A02.4 | (Gas Final Filter & Metering Skid) FDN Work | 2007-10-02 | 2007-12-27
Activity | 2CF1265W16A12.4 | (TCA Cooler) FDN Work | 2007-10-30 | 2007-12-29
Activity | 2PF1265W42A04.4T | (Gas Final Filter & Metering Skid) Transportation | 2008-03-01 | 2008-04-15
Activity | 2PF1265W42A14.4T | (TCA Cooler) Transportation | 2008-04-01 | 2008-05-15
Activity | 2CF1265W42A05.4 | (Gas Final Filter & Metering Skid) Installation | 2008-04-16 | 2008-04-30
Activity | 2CF1265W42A15.4 | (TCA Cooler) Installation | 2008-05-16 | 2008-05-30
Activity | 2CF1265W58A06.4 | (FGSS) Piping Work(incl. Airblowing Test)_Power Block Area | 2008-06-19 | 2008-07-19
Activity | 2CF1265W74A07.4 | (FGSS) Installation- Elec. | 2008-07-21 | 2008-08-02
Activity | 2CF1265W90A08.4 | (FGSS) Installation- I&C | 2008-07-21 | 2008-08-02
Activity | 2SF1265W62A09.4 | (FGSS) Loop chek | 2008-09-03 | 2008-09-12
Activity | 2SF1265W62A10.4 | (FGSS) Function Test | 2008-09-13 | 2008-09-17
Activity | 2SF1265W62A11.4 | (FGSS) Gas Receiving upto GT Final Control Valve | 2008-09-22 | 2008-09-24
5 | GTG #22 Washing & Drain System |  | 2007-03-30 | 2008-08-14
Activity | 2PF1265W42A02.5P | (Washing & Drain system Skid) P.O & Procurement | 2007-03-30 | 2008-03-31
Activity | 2CF1265W16A01.1 | (Washing & Drain system Skid) FDN Work | 2007-10-30 | 2007-12-29
Activity | 2PF1265W42A03.5T | (Washing & Drain system Skid) Transportation | 2008-04-01 | 2008-05-15
Activity | 2CF1265W42A04.1 | (Washing & Drain system Skid) Installation | 2008-05-16 | 2008-06-02
Activity | 2CF1265W58A05.1 | (Washing & Drain system Skid) Piping work | 2008-06-03 | 2008-07-03
Activity | 2CF1265W74A07.5 | (Washing & Drain system Skid) Installation- Elec. | 2008-07-04 | 2008-07-17
Activity | 2CF1265W90A08.5 | (Washing & Drain system Skid) Installation- I&C | 2008-07-04 | 2008-07-17
Activity | 2CF1265W62A06.1 | (Washing & Drain system Skid) Flushing | 2008-07-04 | 2008-07-07
Activity | 2SF1265W62A09.5 | (Washing & Drain system Skid) Loop chek | 2008-07-18 | 2008-07-22
Activity | 2SF1265W62A10.1 | (Washing & Drain system Skid) Function Test | 2008-07-23 | 2008-07-25
Activity | 2SF1265W62A11.1 | (Washing & Drain system Skid) Load(Running) Test | 2008-08-12 | 2008-08-14
5 | GTG #22 Fuel Oil Injection System |  | 2007-03-30 | 2008-09-02
Activity | 2PF1265W42A02.6P | (Fuel oil injection System) P.O & Procurement | 2007-03-30 | 2008-03-31
Activity | 2PF1265W42A12.1P | (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | 2007-03-30 | 2008-02-29
Activity | 2PF1265W42A15.1P | (Water injection System) P.O & Procurement | 2007-03-30 | 2008-02-29
Activity | 2CF1265W16A01.6 | (Fuel oil injection System) FDN Work | 2007-10-30 | 2007-12-29
Activity | 2CF1265W16A11.1 | (Fuel oil injection Pump & actuator) FDN Work | 2007-10-30 | 2007-12-29
Activity | 2CF1265W16A15.1 | (Water injection System) FDN Work | 2007-10-30 | 2007-12-29
Activity | 2PF1265W42A13.1T | (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | 2008-03-01 | 2008-04-15
Activity | 2PF1265W42A16.1T | (Water injection System) Transportation | 2008-03-01 | 2008-04-15
Activity | 2PF1265W42A03.6T | (Fuel oil injection System) Transportation | 2008-04-01 | 2008-05-15
Activity | 2CF1265W42A14.1 | (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | 2008-04-16 | 2008-04-30
Activity | 2CF1265W42A17.1 | (Water injection System) Installation | 2008-04-16 | 2008-04-30
Activity | 2CF1265W58A18.1 | (Water injection System) Piping work | 2008-05-01 | 2008-05-15
Activity | 2CF1265W42A04.6 | (Fuel oil injection System) Installation | 2008-05-16 | 2008-05-30
Activity | 2CF1265W74A19.1 | (Water injection System) Installation- Elec. | 2008-05-16 | 2008-05-29
Activity | 2CF1265W90A20.1 | (Water injection System) Installation- I&C | 2008-05-16 | 2008-05-29
Activity | 2SF1265W62A21.1 | (Water injection System) Loop chek | 2008-05-30 | 2008-06-03
Activity | 2CF1265W58A05.6 | (Fuel oil injection System) Piping work | 2008-05-31 | 2008-06-14
Activity | 2SF1265W62A22.1 | (Water injection System) Function Test | 2008-06-04 | 2008-06-06
Activity | 2CF1265W74A06.6 | (Fuel oil injection System) Installation- Elec. | 2008-06-16 | 2008-06-28
Activity | 2CF1265W90A07.6 | (Fuel oil injection System) Installation- I&C | 2008-06-16 | 2008-06-28
Activity | 2SF1265W62A08.6 | (Fuel oil injection System) Loop chek | 2008-06-29 | 2008-07-01
Activity | 2SF1265W62A23.1 | (Water injection System) Load Test | 2008-08-12 | 2008-08-13
Activity | 2SF1265W62A09.6 | (Fuel oil injection System) Function Test | 2008-08-15 | 2008-08-19
Activity | 2SF1265W62A10.6 | (Fuel oil injection System) Flushing | 2008-08-30 | 2008-09-02
5 | GTG #22 Vibration Monitoring System (VMS) |  | 2007-08-31 | 2008-09-28
Activity | 2PF1260W86A02.1P | (VMS) P.O & Procurement for GT | 2007-08-31 | 2008-06-02
Activity | 2PF1260W86A03.1T | (VMS) Transportation for GT | 2008-06-03 | 2008-07-17
Activity | 2CF1260W86A04.1 | (VMS) Installation for GT | 2008-09-16 | 2008-09-23
Activity | 2SF1260W62A05.1 | (VMS) Function Test for GT | 2008-09-24 | 2008-09-28
5 | GTG #22 Closed Cooling Water System |  | 2007-03-30 | 2008-08-19
Activity | 2EF1225W00A01.1 | (CCWS) CCW H/EX key data | 2007-03-30 | 2007-05-30
Activity | 2PF1225W42A12.1P | (EXP Head Tank) P.O & Procurement | 2007-07-03 | 2008-04-30
Activity | 2EF1225W16A09.1 | (EXP Head Tank) FDN Design | 2007-07-03 | 2007-11-29
Activity | 2PF1225W42A06.1P | (CCWP) P.O & Procurement for GT | 2007-07-03 | 2008-04-30
Activity | 2EF1225W16A03.1 | (CCWP) FDN Design | 2007-07-03 | 2007-11-29
Activity | 2PF1225W42A18.1P | (CCW H/EX) P.O & Procurement_Fin fan cooler | 2007-07-03 | 2008-04-30
Activity | 2EF1225W16A15.1 | (CCW H/EX) FDN Design_Fin fan cooler | 2007-07-03 | 2007-11-29
Activity | 2CF1225W16A04.1 | (CCWP) FDN Work | 2007-11-30 | 2008-01-26
Activity | 2CF1225W16A16.1 | (CCW H/EX) FDN Work_Fin fan cooler | 2007-11-30 | 2008-02-25
Activity | 2CF1225W16A10.1 | (EXP Head Tank) FDN Work | 2008-01-01 | 2008-01-29
Activity | 2PF1225W42A13.1T | (EXP Head Tank) Transportation | 2008-05-01 | 2008-06-14
Activity | 2PF1225W42A07.1T | (CCWP) Transportation for GT | 2008-05-01 | 2008-06-14
Activity | 2PF1225W42A19.1T | (CCW H/EX) Transportation_Fin fan cooler | 2008-05-01 | 2008-06-14
Activity | 2CF1225W58A21.1 | (CCWS) Piping Work | 2008-06-09 | 2008-07-30
Activity | 2CF1225W42A14.1 | (EXP Head Tank) Installation | 2008-06-16 | 2008-07-14
Activity | 2CF1225W42A08.1 | (CCWP) Installation | 2008-06-16 | 2008-06-30
Activity | 2CF1225W42A20.1 | (CCW H/EX) Installation_Fin fan cooler | 2008-06-16 | 2008-07-30
Activity | 2CF1225W74A22.1 | (CCWS) Installation & Test - Elec. | 2008-06-30 | 2008-07-30
Activity | 2CF1225W90A23.1 | (CCWS) Installation & Test - I&C | 2008-06-30 | 2008-07-30
Activity | 2SF1225W62A24.1 | (CCWS) Loop chek | 2008-07-31 | 2008-08-09
Activity | 2SF1225W62A25.1 | (CCWS) Function Test | 2008-08-10 | 2008-08-14
Activity | 2SF1225W62A26.1 | (CCWS) Flushing | 2008-08-15 | 2008-08-19
5 | GTG #22 Fire fighting System |  | 2007-03-30 | 2008-08-04
Activity | 2PF1265W38A01.1P | (F/F GTG#22) P.O & Procurement_CO2 FF System | 2007-03-30 | 2008-04-14
Activity | 2PF1265W38A04.1P | (F/F GTG#22) P.O & Procurement_Clean Agent FF System | 2007-03-30 | 2008-04-14
Activity | 2PF1265W38A02.1T | (F/F GTG#22) Transportation_CO2 FF System | 2008-04-15 | 2008-05-29
Activity | 2PF1265W38A05.1T | (F/F GTG#22) Transportation_Clean Agent FF System | 2008-04-15 | 2008-05-29
Activity | 2CF1265W38A03.1 | (F/F GTG#22) Installation_CO2 FF System | 2008-05-30 | 2008-06-13
Activity | 2CF1265W38A06.1 | (F/F GTG#22) Installation_Clean Agent FF System | 2008-05-30 | 2008-06-13
Activity | 2CF1265W38A07.1 | (F/F GTG#22) Piping work | 2008-06-14 | 2008-07-08
Activity | 2SF1265W62A08.7 | (F/F GTG#22) Loop chek | 2008-07-09 | 2008-07-15
Activity | 2SF1265W62A09.7 | (F/F GTG#22) Function Test(incl. Alarm Test) | 2008-07-16 | 2008-07-25
Activity | 2SF1265W62A10.7 | (F/F GTG#22) CO2 Discharge Test | 2008-07-26 | 2008-08-04
5 | GTG #22 Auxiliary System |  | 2007-03-30 | 2008-07-09
Activity | 2PF1265W42A02.8P | (Purge Air System) P.O & Procurement | 2007-03-30 | 2008-02-29
Activity | 2PF1265W42A12.8P | (Control Oil) P.O & Procurement | 2007-03-30 | 2008-02-29
Activity | 2CF1265W16A01.8 | (Purge Air System) FDN Work | 2007-10-30 | 2007-12-29
Activity | 2CF1265W16A11.8 | (Control Oil) FDN Work | 2007-10-30 | 2007-12-29
Activity | 2PF1265W42A03.8T | (Purge Air System) Transportation | 2008-03-01 | 2008-04-15
Activity | 2PF1265W42A13.8T | (Control Oil)Transportation | 2008-03-01 | 2008-04-15
Activity | 2CF1265W42A04.8 | (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | 2008-04-16 | 2008-04-30
Activity | 2CF1265W42A14.8 | (Control Oil) Installation | 2008-04-16 | 2008-04-30
Activity | 2CF1265W16A05.8 | (Purge Air System) Piping work | 2008-05-01 | 2008-05-15
Activity | 2CF1265W16A15.8 | (Control Oil) Piping work | 2008-05-01 | 2008-05-31
Activity | 2CF1265W74A06.8 | (Purge Air System) Installation- Elec. | 2008-05-16 | 2008-05-29
Activity | 2CF1265W90A07.8 | (Purge Air System) Installation- I&C | 2008-05-16 | 2008-05-29
Activity | 2SF1265W62A08.8 | (Purge Air System) Loop chek | 2008-05-30 | 2008-06-01
Activity | 2SF1265W62A09.8 | (Purge Air System) Function Test | 2008-06-02 | 2008-06-04
Activity | 2CF1265W74A16.8 | (Control Oil) Installation- Elec. | 2008-06-02 | 2008-06-14
Activity | 2CF1265W90A17.8 | (Control Oil) Installation- I&C | 2008-06-02 | 2008-06-14
Activity | 2SF1265W62A10.8 | (Purge Air System) Load Test | 2008-06-05 | 2008-06-07
Activity | 2SF1265W62A18.8 | (Control Oil) Loop chek | 2008-06-15 | 2008-06-19
Activity | 2SF1265W62A19.8 | (Control Oil) Function Test | 2008-06-20 | 2008-06-29
Activity | 2SF1265W62A20.8 | (Control Oil) Flushing | 2008-06-30 | 2008-07-09
5 | GTG #22 Commissioning |  | 2008-09-29 | 2009-01-03
Activity | 2SF9011W62A01.1 | (GTG #22) Fuel Gas System Final Function Test | 2008-09-29 | 2008-10-01
Activity | 2SF9011W62A02.1 | (GTG #22) Turning Gear Operation | 2008-10-02 | 2008-10-03
Activity | 2SF9011W62A03.1 | (GTG #22) Initial Firing with FSNL | 2008-10-04 | 2008-10-04
Activity | 2SF9012W62A04.1 | (GTG #22) TBN & GEN Protection Test | 2008-10-05 | 2008-10-06
Activity | 2SF9012W62A05.1 | (GTG #22) 1st Synchronization | 2008-10-07 | 2008-10-08
Activity | 2SF9012W62A06.1 | (GTG #22) Optimization with Fuel Gas | 2008-10-09 | 2008-10-23
Activity | 2SF9012W62A07.1 | (GTG #22) Fuel Oil System Final Function Test | 2008-10-24 | 2008-11-02
Activity | 2SF9012W62A08.1 | (GTG #22) Optimization with Fuel Oil | 2008-11-03 | 2008-12-02
Activity | 2SF9012W62A13.1 | (GTG #22) Fuel Change-Over Test | 2008-12-03 | 2008-12-15
Activity | 2SF9012W62A09.1 | (GTG #22) Black start Test with GT | 2008-12-03 | 2008-12-03
Activity | 2SF9012W62A10.1 | (GTG #22) Trial Run Test | 2008-12-04 | 2008-12-04
Activity | 2SF9013W62A11.1 | (GTG #22) Reliability Test | 2008-12-05 | 2008-12-19
Activity | 2SF9013W62A12.1 | (GTG #22) Performance Test (Fuel Gas & Fuel Oil) | 2008-12-20 | 2009-01-03
3 | HRSG #21 & #22 |  | 2007-03-01 | 2009-04-27
4 | HRSG Common |  | 2007-03-01 | 2008-04-04
Activity | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | 2007-03-01 | 2007-03-30
Activity | 2EF1600W00A03 | (HRSG #21/#22) Instrument, Service Air Data | 2007-03-01 | 2007-03-29
Activity | 2EF1600W00A04 | (HRSG #21/#22) Utility Consumption Data | 2007-03-01 | 2007-04-26
Activity | 2EF1600W00A05 | (HRSG #21/#22) Emergency Load Data | 2007-03-01 | 2007-04-16
Activity | 2EF1600W00A01.0 | (HRSG #21/#22) P&ID & System Design | 2007-04-18 | 2008-04-04
4 | HRSG #21 |  | 2007-05-17 | 2009-04-27
5 | HRSG LEB |  | 2007-06-20 | 2008-12-15
Activity | 2EF1600W00A01 | (HRSG #21 LEB) GA & Load Data to Civil Design | 2007-06-20
Activity | 2EF1600W32A02 | (HRSG #21 LEB) Building Design | 2007-06-20 | 2007-11-20
Activity | 2PF1600W90A10P | (HRSG #21 LEB) P.O & Procurement - I&C | 2007-09-15 | 2008-08-01
Activity | 2PF1600W74A06P | (HRSG #21 LEB) P.O & Procurement - Elec | 2007-09-15 | 2008-08-01
Activity | 2CF1600W16A03 | (HRSG #21 LEB) FDN Work | 2008-02-01 | 2008-03-29
Activity | 2CF1600W32A04 | (HRSG #21 LEB) Structure Work | 2008-03-31 | 2008-06-25
Activity | 2CF1600W36A14 | (HRSG #21 LEB) Installation & Test - HVAC | 2008-07-31 | 2008-09-13
Activity | 2PF1600W90A11T | (HRSG #21 LEB) Transportataion - I&C | 2008-08-02 | 2008-09-15
Activity | 2PF1600W74A07T | (HRSG #21 LEB) Transportataion - Elec | 2008-08-02 | 2008-09-15
Activity | 2CF1600W90A12 | (HRSG #21 LEB) Installation & Test - I&C | 2008-10-20 | 2008-12-15
Activity | 2CF1600W74A08 | (HRSG #21 LEB) Installation & Test - Elec | 2008-10-20 | 2008-12-15
Activity | 2CF1600W38A13 | (HRSG #21 LEB) Installation & Test - Fire Fighting Sys. | 2008-11-01 | 2008-12-15
5 | Steel Structure & Casing |  | 2007-05-18 | 2008-08-17
Activity | 2EF1610W20A01 | (HRSG #21 S/Structure & Casing) Design | 2007-05-18 | 2007-12-14
Activity | 2PF1610W20A03P | (HRSG #21 S/Structure & Casing) P.O & Procurement | 2007-06-14 | 2008-03-03
Activity | 2PF1610W20A04T | (HRSG #21 S/Structure & Casing) Transportation | 2008-03-04 | 2008-04-17
Activity | 2CF1610W20A05 | (HRSG #21 S/Structure & Casing) S/Structure Installation | 2008-04-18 | 2008-06-18
Activity | 2CF1610W20A06 | (HRSG #21 S/Structure & Casing) Casing Installation | 2008-06-19 | 2008-08-17
5 | Duct |  | 2007-05-17 | 2009-02-04
Activity | 2EF1615W64A04 | (HRSG #21 Duct) Design | 2007-05-17 | 2007-11-19
Activity | 2EF1615W00A01 | (HRSG #21 Duct) GA & Load Data to Civil Design | 2007-05-30
Activity | 2PF1615W64A14P | (HRSG #21 EXP Joint & Bellows) P.O & Procurement | 2007-06-13 | 2008-04-30
Activity | 2PF1615W64A10P | (HRSG #21 Damper) P.O & Procurement | 2007-06-13 | 2008-04-01
Activity | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | 2007-06-14 | 2008-03-03
Activity | 2EF1615W16A02 | (HRSG #21 Duct) FDN Design | 2007-09-03 | 2008-01-14
Activity | 2CF1615W16A03 | (HRSG #21 Duct) FDN Work | 2008-01-15 | 2008-04-16
Activity | 2PF1615W64A07T | (HRSG #21 Duct) Transportation | 2008-03-04 | 2008-04-17
Activity | 2PF1615W64A11T | (HRSG #21 Damper) Transportation | 2008-04-02 | 2008-05-16
Activity | 2PF1615W64A15T | (HRSG #21 EXP Joint & Bellows) Transportation | 2008-05-01 | 2008-06-14
Activity | 2CF1615W64A12 | (HRSG #21 Damper) Installation | 2008-05-17 | 2008-07-17
Activity | 2CF1615W64A17 | (HRSG #21) Installation_Diverter Damper | 2008-06-02 | 2008-06-25
Activity | 2CF1615W64A20 | (HRSG #21) Installation_Guillotine Damper | 2008-06-26 | 2008-07-19
Activity | 2CF1615W86A18 | (HRSG #21) Installation_Diverter Damper Control Unit | 2008-06-26 | 2008-07-07
Activity | 2CF1615W62A19 | (HRSG #21) Diverter Damper Control Unit Flushing | 2008-07-08 | 2008-07-24
Activity | 2SF1615W62A21 | (HRSG #21) Diverter Damper Function Test for GT #21 | 2008-08-05 | 2008-08-08
Activity | 2SF1615W62A22 | (HRSG #21) Guillotine Damper Function Test for GT #21 | 2008-08-05 | 2008-08-08
Activity | 2CF1615W64A08 | (HRSG #21 Duct) Duct Installation | 2008-10-18 | 2009-01-17
Activity | 2CF1615W64A16 | (HRSG #21 EXP Joint & Bellows) Installation | 2008-12-20 | 2009-02-04
5 | Module |  | 2007-07-03 | 2008-10-17
Activity | 2PF1610W42A02P | (HRSG #21 Module) P.O & Procurement | 2007-07-03 | 2008-04-02
Activity | 2PF1610W42A03T | (HRSG #21 Module) Transportation | 2008-04-03 | 2008-05-17
Activity | 2CF1610W42A04 | (HRSG #21 Module) Installation | 2008-08-18 | 2008-10-17
5 | Drum |  | 2007-05-17 | 2008-11-15
Activity | 2EF1645W42A01 | (HRSG #21 Drum) Design | 2007-05-17 | 2007-12-07
Activity | 2PF1645W42A03P | (HRSG #21 Drum) P.O & Procurement | 2007-06-13 | 2008-05-30
Activity | 2PF1645W42A04T | (HRSG #21 Drum) Transportation | 2008-05-31 | 2008-07-15
Activity | 2CF1645W42A05 | (HRSG #21 Drum) Installation | 2008-10-18 | 2008-11-15
5 | Bypass Stack |  | 2007-05-17 | 2008-08-02
Activity | 2EF1625W42A04 | (HRSG #21 Bypass Stack) Design | 2007-05-17 | 2007-11-28
Activity | 2PF1625W42A10P | (HRSG #21 Bypass Stack Silencer) P.O & Procurement | 2007-06-13 | 2008-04-30
Activity | 2EF1625W00A01 | (HRSG #21 Bypass Stack) GA & Load Data to Civil Design | 2007-07-02
Activity | 2PF1625W42A06P | (HRSG #21 Bypass Stack) P.O & Procurement | 2007-07-03 | 2008-02-29
Activity | 2EF1625W16A02 | (HRSG #21 Bypass Stack) FDN Design | 2007-10-04 | 2008-02-12
Activity | 2CF1625W16A03 | (HRSG #21 Bypass Stack) FDN Work | 2008-02-12 | 2008-05-01
Activity | 2PF1625W42A07T | (HRSG #21 Bypass Stack) Transportation | 2008-03-01 | 2008-04-15
Activity | 2PF1625W42A11T | (HRSG #21 Bypass Stack Silencer) Transportation | 2008-05-01 | 2008-06-14
Activity | 2CF1625W42A08 | (HRSG #21 Bypass Stack) Installation | 2008-05-01 | 2008-08-02
Activity | 2CF1625W42A12 | (HRSG #21 Bypass Stack Silencer) Installation | 2008-07-02 | 2008-07-31
5 | Main Stack |  | 2007-05-17 | 2009-03-23
Activity | 2EF1625W42A01 | (HRSG #21 Main Stack) Design | 2007-05-17 | 2007-11-28
Activity | 2PF1625W42A06.0P | (HRSG #21 Main Stack) P.O & Procurement | 2007-06-04 | 2008-03-03
Activity | 2EF1625W00A02 | (HRSG #21 Main Stack) GA & Load Data to Civil Design | 2007-07-05
Activity | 2PF1625W42A10.0P | (HRSG #21 Main Stack Silencer) P.O & Procurement | 2007-07-27 | 2008-06-13
Activity | 2EF1625W16A03 | (HRSG #21 Main Stack) FDN Design | 2007-10-09 | 2008-02-15
Activity | 2CF1625W16A04 | (HRSG #21 Main Stack) FDN Work | 2008-02-15 | 2008-05-19
Activity | 2PF1625W42A07.0T | (HRSG #21 Main Stack) Transportation | 2008-03-04 | 2008-04-17
Activity | 2PF1625W42A11.0T | (HRSG #21 Main Stack Silencer) Transportation | 2008-06-14 | 2008-07-29
Activity | 2CF1625W42A08.0 | (HRSG #21 Main Stack) Installation | 2008-12-15 | 2009-03-14
Activity | 2CF1625W42A12.0 | (HRSG #21 Main Stack Silencer) Installation | 2009-02-23 | 2009-03-23
5 | Piping Work |  | 2008-01-09 | 2009-03-23
Activity | 2PF1650W52A02P | (HRSG #21 Insulation) P.O & Procurement | 2008-01-09 | 2008-10-30
Activity | 2PF1650W52A03T | (HRSG #21 Insulation) Transportation | 2008-10-31 | 2008-12-13
Activity | 2CF1640W58A05 | (HRSG #21) Piping Work | 2008-11-01 | 2009-02-02
Activity | 2CF1640W62A06 | (HRSG #21 Hydro Test | 2009-02-03 | 2009-02-26
Activity | 2CF1650W52A04 | (HRSG #21 Insulation) Installation | 2009-02-17 | 2009-03-23
Activity | 2CF1640W60A07 | (HRSG #21) Acid Cleaning | 2009-02-27 | 2009-03-21
5 | CEMS |  | 2007-08-29 | 2008-08-10
Activity | 2PF1660W86A04P | (CEMS) P.O & Procurement | 2007-08-29 | 2008-04-30
Activity | 2EF1660W16A01 | (CEMS) FDN Design | 2007-10-30 | 2008-01-25
Activity | 2CF1660W16A02 | (CEMS) FDN Work | 2008-01-26 | 2008-03-24
Activity | 2PF1660W86A05T | (CEMS) Transportation | 2008-05-01 | 2008-06-14
Activity | 2CF1660W86A06 | (CEMS) Installation(incl. Elec, I&C) | 2008-06-16 | 2008-07-01
Activity | 2CF1660W62A07 | (CEMS) Loop Test | 2008-07-02 | 2008-07-07
Activity | 2SF1615W62A08 | (HRSG #21) CEMS Function Test for GT #21(Bypass stack) | 2008-08-05 | 2008-08-10
5 | Auxiliary System |  | 2007-09-10 | 2009-03-02
Activity | 2PF1665W42A02P | (HRSG #21 MECH Vendor Equip) P.O & Procurement | 2007-09-10 | 2008-09-02
Activity | 2PF1660W86A11P | (HRSG #21 I&C Vendor Equip) P.O & Procurement | 2007-10-02 | 2008-09-03
Activity | 2PF1660W70A06P | (HRSG #21 ELEC Vendor Equip) P.O & Procurement | 2007-10-02 | 2008-09-03
Activity | 2PF1665W42A03T | (HRSG #21 MECH Vendor Equip) Transportation | 2008-09-03 | 2008-10-17
Activity | 2PF1660W86A12T | (HRSG #21 I&C Vendor Equip) Transportation | 2008-09-04 | 2008-10-18
Activity | 2PF1660W70A07T | (HRSG #21 ELEC Vendor Equip) Transportation | 2008-09-04 | 2008-10-18
Activity | 2CF1665W42A04 | (HRSG #21 MECH Vendor Equip) Installation | 2008-10-18 | 2009-01-30
Activity | 2CF1660W86A13 | (HRSG #21 I&C Vendor Equip) Installation | 2008-10-20 | 2009-02-11
Activity | 2CF1660W70A08 | (HRSG #21 ELEC Vendor Equip) Installation | 2008-10-20 | 2009-02-11
Activity | 2CF1655W74A09 | (HRSG #21) Installation & Test - Elec. | 2008-11-30 | 2009-03-02
Activity | 2CF1660W90A14 | (HRSG #21) Installation & Test - I&C | 2008-11-30 | 2009-03-02
5 | Commissioning |  | 2009-03-24 | 2009-04-27
Activity | 2SF1600W62A01 | (HRSG #21) Cold Commissioning for HRSG #21 | 2009-03-24 | 2009-04-12
Activity | 2SF1600W62A02 | (HRSG #21) Function Test for HRSG #21 | 2009-04-13 | 2009-04-27
4 | HRSG #22 |  | 2007-05-17 | 2009-04-27
5 | HRSG LEB |  | 2007-06-20 | 2008-12-15
Activity | 2EF1600W00A01.1 | (HRSG #22 LEB) GA & Load Data to Civil Design | 2007-06-20
Activity | 2EF1600W32A02.1 | (HRSG #22 LEB) Building Design | 2007-06-20 | 2007-11-20
Activity | 2PF1600W90A10.1P | (HRSG #22 LEB) P.O & Procurement - I&C | 2007-09-15 | 2008-08-01
Activity | 2PF1600W74A06.1P | (HRSG #22 LEB) P.O & Procurement - Elec | 2007-09-15 | 2008-08-01
Activity | 2CF1600W16A03.1 | (HRSG #22 LEB)FDN Work | 2008-02-01 | 2008-03-29
Activity | 2CF1600W32A04.1 | (HRSG #22 LEB)Structure Work | 2008-03-31 | 2008-06-25
Activity | 2CF1600W36A13.1 | (HRSG #22 LEB) Installation & Test - HVAC | 2008-07-31 | 2008-09-13
Activity | 2PF1600W90A11.1T | (HRSG #22 LEB) Transportataion - I&C | 2008-08-02 | 2008-09-15
Activity | 2PF1600W74A07.1T | (HRSG #22 LEB) Transportataion - Elec | 2008-08-02 | 2008-09-15
Activity | 2CF1600W90A12.1 | (HRSG #22 LEB) Installation & Test - I&C | 2008-10-20 | 2008-12-15
Activity | 2CF1600W74A08.1 | (HRSG #22 LEB) Installation & Test - Elec | 2008-10-20 | 2008-12-15
Activity | 2CF1600W38A14.1 | (HRSG #22 LEB) Installation & Test - Fire Fighting Sys. | 2008-11-01 | 2008-12-15
5 | Steel Structure & Casing |  | 2007-05-18 | 2008-08-17
Activity | 2EF1610W20A01.1 | (HRSG #22 S/Structure & Casing) Design | 2007-05-18 | 2007-12-14
Activity | 2PF1610W20A03.1P | (HRSG #22 S/Structure & Casing) P.O & Procurement | 2007-06-14 | 2008-03-03
Activity | 2PF1610W20A04.1T | (HRSG #22 S/Structure & Casing) Transportation | 2008-03-04 | 2008-04-17
Activity | 2CF1610W20A05.1 | (HRSG #22 S/Structure & Casing) S/Structure Installation | 2008-04-18 | 2008-06-18
Activity | 2CF1610W20A06.1 | (HRSG #22 S/Structure & Casing) Casing Installation | 2008-06-19 | 2008-08-17
5 | Duct |  | 2007-05-17 | 2009-02-04
Activity | 2EF1615W64A01.1 | (HRSG #22 Duct) Design | 2007-05-17 | 2007-11-19
Activity | 2EF1615W00A02.1 | (HRSG #22 Duct) GA & Load Data to Civil Design | 2007-05-30
Activity | 2PF1665W64A14.1P | (HRSG #22 EXP Joint & Bellows) P.O & Procurement | 2007-06-13 | 2008-04-30
Activity | 2PF1615W64A10.1P | (HRSG #22 Damper) P.O & Procurement | 2007-06-13 | 2008-04-01
Activity | 2PF1615W64A06.1P | (HRSG #22 Duct) P.O & Procurement | 2007-06-14 | 2008-03-03
Activity | 2EF1615W16A03.1 | (HRSG #22 Duct) FDN Design | 2007-09-03 | 2008-01-14
Activity | 2CF1615W16A04.1 | (HRSG #22 Duct) FDN Work | 2008-01-15 | 2008-04-16
Activity | 2PF1615W64A07.1T | (HRSG #22 Duct) Transportation | 2008-03-04 | 2008-04-17
Activity | 2PF1615W64A11.1T | (HRSG #22 Damper) Transportation | 2008-04-02 | 2008-05-16
Activity | 2PF1665W64A15.1T | (HRSG #22 EXP Joint & Bellows) Transportation | 2008-05-01 | 2008-06-14
Activity | 2CF1615W64A12.1 | (HRSG #22 Damper) Installation | 2008-05-17 | 2008-07-17
Activity | 2CF1615W64A17.1 | (HRSG #22) Installation_Diverter Damper | 2008-06-02 | 2008-06-25
Activity | 2CF1615W64A18.1 | (HRSG #22) Installation_Guillotine Damper | 2008-06-26 | 2008-07-19
Activity | 2CF1615W86A19.1 | (HRSG #22) Installation_Diverter Damper Control Unit | 2008-06-26 | 2008-07-07
Activity | 2CF1615W62A20.1 | (HRSG #22) Diverter Damper Control Unit Flushing | 2008-07-08 | 2008-07-24
Activity | 2SF1615W62A21.1 | (HRSG #22) Diverter Damper Function Test for GT #22 | 2008-08-05 | 2008-08-08
Activity | 2SF1615W62A22.1 | (HRSG #22) Guillotine Damper Function Test for GT #22 | 2008-08-05 | 2008-08-08
Activity | 2CF1615W64A08.1 | (HRSG #22 Duct) Duct Installation | 2008-10-18 | 2009-01-17
Activity | 2CF1665W64A16.1 | (HRSG #22 EXP Joint & Bellows) Installation | 2008-12-20 | 2009-02-04
5 | Module |  | 2007-07-03 | 2008-10-17
Activity | 2PF1610W42A02.1P | (HRSG #22 Module) P.O & Procurement | 2007-07-03 | 2008-04-02
Activity | 2PF1610W42A03.1T | (HRSG #22 Module) Transportation | 2008-04-03 | 2008-05-17
Activity | 2CF1610W42A04.1 | (HRSG #22 Module) Installation | 2008-08-18 | 2008-10-17
5 | Drum |  | 2007-05-17 | 2008-11-15
Activity | 2EF1645W42A01.1 | (HRSG #22 Drum) Design | 2007-05-17 | 2007-12-07
Activity | 2PF1645W42A03.1P | (HRSG #22 Drum) P.O & Procurement | 2007-06-13 | 2008-05-30
Activity | 2PF1645W42A04.1T | (HRSG #22 Drum) Transportation | 2008-05-31 | 2008-07-15
Activity | 2CF1645W42A05.1 | (HRSG #22 Drum) Installation | 2008-10-18 | 2008-11-15
5 | Bypass Stack |  | 2007-05-17 | 2008-08-02
Activity | 2EF1625W42A01.1 | (HRSG #22 Bypass Stack) Design | 2007-05-17 | 2007-11-28
Activity | 2PF1625W42A10.1P | (HRSG #22 Bypass Stack Silencer) P.O & Procurement | 2007-06-13 | 2008-04-30
Activity | 2EF1625W00A02.1 | (HRSG #22 Bypass Stack) GA & Load Data to Civil Design | 2007-07-02
Activity | 2PF1625W42A06.1P | (HRSG #22 Bypass Stack) P.O & Procurement | 2007-07-03 | 2008-02-29
Activity | 2EF1625W16A03.1 | (HRSG #22 Bypass Stack) FDN Design | 2007-10-04 | 2008-02-12
Activity | 2CF1625W16A04.1 | (HRSG #22 Bypass Stack) FDN Work | 2008-02-12 | 2008-05-01
Activity | 2PF1625W42A07.1T | (HRSG #22 Bypass Stack) Transportation | 2008-03-01 | 2008-04-15
Activity | 2PF1625W42A11.1T | (HRSG #22 Bypass Stack Silencer) Transportation | 2008-05-01 | 2008-06-14
Activity | 2CF1625W42A08.1 | (HRSG #22 Bypass Stack) Installation | 2008-05-01 | 2008-08-02
Activity | 2CF1625W42A12.1 | (HRSG #22 Bypass Stack Silencer) Installation | 2008-07-02 | 2008-07-31
5 | Main Stack |  | 2007-05-17 | 2009-03-23
Activity | 2EF1625W42A01.2 | (HRSG #22 Main Stack) Design | 2007-05-17 | 2007-11-28
Activity | 2PF1625W42A10.2P | (HRSG #22 Main Stack Silencer) P.O & Procurement | 2007-06-13 | 2008-04-30
Activity | 2EF1625W00A02.2 | (HRSG #22 Main Stack) GA & Load Data to Civil Design | 2007-07-05
Activity | 2PF1625W42A06.2P | (HRSG #22 Main Stack) P.O & Procurement | 2007-07-18 | 2008-04-16
Activity | 2EF1625W16A03.2 | (HRSG #22 Main Stack) FDN Design | 2007-10-09 | 2008-02-15
Activity | 2CF1625W16A04.2 | (HRSG #22 Main Stack) FDN Work | 2008-02-15 | 2008-05-19
Activity | 2PF1625W42A07.2T | (HRSG #22 Main Stack) Transportation | 2008-04-17 | 2008-05-31
Activity | 2PF1625W42A11.2T | (HRSG #22 Main Stack Silencer) Transportation | 2008-05-01 | 2008-06-14
Activity | 2CF1625W42A08.2 | (HRSG #22 Main Stack) Installation | 2008-12-15 | 2009-02-10
Activity | 2CF1625W42A12.2 | (HRSG #22 Main Stack Silencer) Installation | 2009-02-23 | 2009-03-23
5 | Piping Work |  | 2008-01-09 | 2009-03-19
Activity | 2PF1650W52A02.1P | (HRSG #22 Insulation) P.O & Procurement | 2008-01-09 | 2008-10-30
Activity | 2PF1650W52A03.1T | (HRSG #22 Insulation) Transportation | 2008-10-31 | 2008-12-13
Activity | 2CF1640W58A05.1 | (HRSG #22) Piping Work | 2008-11-01 | 2009-01-20
Activity | 2CF1640W62A06.1 | (HRSG #22) Hydro Test | 2009-01-30 | 2009-02-23
Activity | 2CF1650W52A04.1 | (HRSG #22 Insulation) Installation | 2009-02-13 | 2009-03-19
Activity | 2CF1640W60A07.1 | (HRSG #22) Acid Cleaning | 2009-02-24 | 2009-03-18
5 | CEMS |  | 2007-08-29 | 2008-08-11
Activity | 2PF1660W86A04.1P | (CEMS) P.O & Procurement | 2007-08-29 | 2008-05-29
Activity | 2EF1660W16A01.1 | (CEMS) FDN Design | 2007-10-30 | 2008-01-25
Activity | 2CF1660W16A02.1 | (CEMS) FDN Work | 2008-01-26 | 2008-03-24
Activity | 2PF1660W86A05.1T | (CEMS) Transportation | 2008-05-30 | 2008-07-14
Activity | 2CF1660W86A06.1 | (CEMS) Installation(incl. Elec, I&C) | 2008-07-15 | 2008-07-30
Activity | 2CF1660W86A07.1 | (CEMS) Loop Test | 2008-07-31 | 2008-08-05
Activity | 2SF1660W62A08.1 | (HRSG #22) CEMS Function Test for GT #11(Bypass stack) | 2008-08-06 | 2008-08-11
5 | Auxiliary System |  | 2007-09-10 | 2009-03-02
Activity | 2PF1665W42A12.1P | (HRSG #22 MECH Vendor Equip) P.O & Procurement | 2007-09-10 | 2008-09-02
Activity | 2PF1660W86A07.1P | (HRSG #22 I&C Vendor Equip) P.O & Procurement | 2007-10-02 | 2008-09-03
Activity | 2PF1660W70A02.1P | (HRSG #22 ELEC Vendor Equip) P.O & Procurement | 2007-10-02 | 2008-09-03
Activity | 2PF1665W42A13.1T | (HRSG #22 MECH Vendor Equip) Transportation | 2008-09-03 | 2008-10-17
Activity | 2PF1660W86A08.1T | (HRSG #22 I&C Vendor Equip) Transportation | 2008-09-04 | 2008-10-18
Activity | 2PF1660W70A03.1T | (HRSG #22 ELEC Vendor Equip) Transportation | 2008-09-04 | 2008-10-18
Activity | 2CF1665W42A14.1 | (HRSG #22 MECH Vendor Equip) Installation | 2008-10-18 | 2009-01-30
Activity | 2CF1660W86A09.1 | (HRSG #22 I&C Vendor Equip) Installation | 2008-10-20 | 2009-02-11
Activity | 2CF1660W70A04.1 | (HRSG #22 ELEC Vendor Equip) Installation | 2008-10-20 | 2009-02-11
Activity | 2CF1655W74A05.1 | (HRSG #22) Installation & Test - Elec. | 2008-11-30 | 2009-03-02
Activity | 2CF1660W90A10.1 | (HRSG #22) Installation & Test - I&C | 2008-11-30 | 2009-03-02
5 | Commissioning |  | 2009-03-24 | 2009-04-27
Activity | 2SF1600W62A01.1 | (HRSG #22)Cold Commissioning for HRSG #21 | 2009-03-24 | 2009-04-12
Activity | 2SF1600W62A02.1 | (HRSG #22) Function Test for HRSG #22 | 2009-04-13 | 2009-04-27
3 | Steam Turbine & Generator #20 |  | 2007-03-01 | 2009-04-29
4 | STG Building |  | 2007-03-01 | 2009-01-12
Activity | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | 2007-03-01
Activity | 2EF2010W20A02 | (STG #20 BLDG) Buliding Design | 2007-03-01 | 2007-09-18
Activity | 2PF2010W20A04P | (STG #20 BLDG) P.O & Procurement - Structure Work(S/S) | 2007-09-19 | 2008-01-31
Activity | 2CF2010W16A03 | (STG #20 BLDG) FDN Work | 2007-11-15 | 2008-03-15
Activity | 2PF2010W20A05T | (STG #20 BLDG) Transportation - Structure Work(S/S) | 2008-02-01 | 2008-03-16
Activity | 2CF2010W20A06 | (STG #20 BLDG) Structure Work(S/S) | 2008-03-17 | 2008-07-16
Activity | 2CF2010W20A07 | (STG #20 BLDG) Cladding Work | 2008-05-26 | 2008-10-11
Activity | 2CF2010W20A08 | (STG #20 BLDG) Roof Work | 2008-08-05 | 2008-11-06
Activity | 2CF2010W90A12 | (STG #20 BLDG) Installation & Test - I&C | 2008-10-13 | 2009-01-12
Activity | 2CF2010W36A10 | (STG #20 BLDG) Installation & Test - HVAC | 2008-10-13 | 2008-12-08
Activity | 2CF2010W74A11 | (STG #20 BLDG) Installation & Test - Elec | 2008-10-13 | 2009-01-12
Activity | 2CF2010W38A09 | (STG #20 BLDG) Installation & Test - Fire Fighting Sys. | 2008-11-01 | 2008-12-27
4 | STG Unit Step-up Transformer |  | 2007-06-29 | 2008-10-27
Activity | 2PF6500W70A07P | (STG #20 & UST Shelter) P.O & Procurement - Main TR | 2007-06-29 | 2008-07-14
Activity | 2EF6500W00A01 | (STG #20 & UST Shelter) GA & Load Data to Civil Design | 2007-11-28
Activity | 2EF6500W16A02 | (STG #20 & UST Shelter) FDN & Firewall Design | 2007-11-28 | 2008-03-10
Activity | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | 2007-11-28 | 2008-03-10
Activity | 2CF6500W16A03 | (STG #20 & UST Shelter) FDN Work | 2008-03-11 | 2008-06-09
Activity | 2CF6500W16A05 | (STG #20 & UST Shelter) Firewall Work | 2008-06-10 | 2008-08-09
Activity | 2PF6500W70A08T | (STG #20 & UST Shelter) Transportation - Main TR | 2008-07-15 | 2008-08-28
Activity | 2CF6500W70A09 | (STG #20 & UST Shelter) Installation - Main TR | 2008-08-29 | 2008-10-27
4 | Steam Turbine |  | 2007-03-01 | 2009-04-17
Activity | 2PF2020W42A10P | (ST #20) P.O & Procurement | 2007-03-01 | 2008-10-01
Activity | 2EF2020W00A01 | (ST #20) ST Process Data | 2007-03-01 | 2007-03-30
Activity | 2EF2020W00A03 | (ST #20) Instrument, Service Air Data | 2007-03-01 | 2007-03-29
Activity | 2EF2020W00A04 | (ST #20) Utility Consumption Data | 2007-03-01 | 2007-04-26
Activity | 2EF2020W00A05 | (ST #20) Emergency Load Data | 2007-03-01 | 2007-04-16
Activity | 2EF2020W00A02 | (ST #20) ST Aux' Steam Consumption Data | 2007-03-01 | 2007-03-29
Activity | 2EF2020W16A06 | (ST #20) FDN Design | 2007-07-03 | 2007-11-01
Activity | 2CF2020W16A07 | (ST #20) FDN Work | 2007-11-15 | 2008-03-15
Activity | 2CF2020W16A08 | (ST #20) Pedestal & Top Slab Work | 2008-03-17 | 2008-09-11
Activity | 2PF2020W42A11T | (ST #20) Transportation | 2008-10-02 | 2008-11-15
Activity | 2CF2020W42A12 | (ST #20) Installation | 2008-11-17 | 2009-04-17
4 | ST Generator |  | 2007-03-01 | 2009-03-19
Activity | 2PF2040W42A02P | (STG #20) P.O & Procurement | 2007-03-01 | 2008-10-01
Activity | 2PF2040W42A03T | (STG #20) Transportation | 2008-10-02 | 2008-11-15
Activity | 2CF2040W42A04 | (STG #20) Installation | 2008-11-17 | 2009-03-19
4 | STG Auxiliary Equipment |  | 2007-04-30 | 2009-02-09
Activity | 2PF2070W42A04P | (STG #20 Aux. Equip) P.O & Procurement | 2007-04-30 | 2008-09-01
Activity | 2EF2070W16A01 | (STG #20 Aux. Equip) FDN Design | 2007-12-24 | 2008-05-21
Activity | 2CF2070W16A02 | (STG #20 Aux. Equip) FDN Work | 2008-05-22 | 2008-08-16
Activity | 2PF2070W42A05T | (STG #20 Aux. Equip) Transportation | 2008-09-02 | 2008-10-16
Activity | 2CF2070W42A06 | (STG #20 Aux. Equip) Installation | 2008-10-17 | 2009-02-09
4 | Piping & Etc. |  | 2008-08-11 | 2009-03-07
Activity | 2CF2035W58A01 | (ST #20) Piping Work | 2008-08-11 | 2009-01-10
Activity | 2CF2060W74A03 | (ST #20) Installation & Test - Elec. | 2008-12-17 | 2009-03-07
Activity | 2CF2065W90A04 | (ST #20) Installation & Test - I&C | 2008-12-17 | 2009-03-07
Activity | 2CF2035W62A02 | (ST #20) Hydro Test | 2009-01-12 | 2009-02-11
4 | Lube Oil System |  | 2007-07-31 | 2009-03-27
Activity | 2PF2030W42A04P | (Lube Oil Sys.) P.O & Procurement | 2007-07-31 | 2008-08-29
Activity | 2EF2030W16A01 | (Lube Oil Sys.) FDN Design | 2007-10-23 | 2008-01-22
Activity | 2CF2030W16A02 | (Lube Oil Sys.) FDN Work | 2008-01-23 | 2008-05-23
Activity | 2PF2030W42A05T | (Lube Oil Sys.) Transportation | 2008-08-30 | 2008-10-14
Activity | 2CF2030W42A06 | (Lube Oil Sys.) Equipment Installation | 2008-10-15 | 2008-11-29
Activity | 2CF2030W58A07 | (Lube Oil Sys.) Pipe Installation | 2008-11-30 | 2009-02-14
Activity | 2CF2030W62A08 | (Lube Oil Sys.) Lube oil flushing | 2009-02-16 | 2009-03-16
Activity | 2CF2030W58A09 | (Lube Oil Sys.) Remove Temp. Pipe | 2009-03-17 | 2009-03-27
4 | Test & Commissioning |  | 2009-03-29 | 2009-04-29
Activity | 2SF2000W62A02 | (ST #20) Pre-Commissioning | 2009-03-29 | 2009-04-27
Activity | 2SF2000W62A01 | (ST #20) Aux. Equipment Function Test | 2009-04-08 | 2009-04-27
Activity | 2SF2000W62A03 | (ST #20) Turnning Gear Operation | 2009-04-28 | 2009-04-29
3 | Block #2 Commisssioning |  | 2009-04-30 | 2009-10-02
Activity | 2SF9035W62A01 | (Comm'g) Steam Blowing | 2009-04-30 | 2009-05-19
Activity | 2CF9035W62A02 | (Comm'g) Temporary Piping Restoration | 2009-05-20 | 2009-05-29
Activity | 2SF9035W62A03 | (Comm'g) Bypass Operation | 2009-05-30 | 2009-06-05
Activity | 2SF9035W62A04 | (Comm'g) Safety & Interlock Test | 2009-06-01 | 2009-06-05
Activity | 2SF9035W62A05 | (Comm'g) Steam Admission | 2009-06-06 | 2009-06-07
Activity | 2SF9040W62A06 | (Comm'g) TBN & GEN. Test | 2009-06-08 | 2009-06-20
Activity | 2SF9040W62A07 | (Comm'g) Synchronization Test | 2009-06-21 | 2009-06-21
Activity | 2SF9040W62A08 | (Comm'g) Optimaization Test | 2009-06-22 | 2009-07-09
Activity | 2SF9040W62A09 | (Comm'g) Fuel Change-Over(Gas to Oil) and Optimaization | 2009-07-10 | 2009-07-10
Activity | 2SF9040W62A10 | (Comm'g) Outage Period | 2009-07-10 | 2009-07-16
Activity | 2SF9040W62A11 | (Comm'g) APS & Stability Guarantee Test | 2009-07-17 | 2009-08-19
Activity | 2SF9040W62A12 | (Comm'g) Trial Run Test | 2009-08-20 | 2009-08-21
Activity | 2SF9041W62A14 | (Comm'g) Reliability Test | 2009-08-22 | 2009-09-20
Activity | 2SF9040W62A13 | (Comm'g) Initial Operation Test | 2009-08-22 | 2009-08-22
Activity | 2SF9042W62A15 | (Comm'g) Performance Test (Fuel Gas & Fuel Oil) | 2009-09-21 | 2009-10-02
2 | Power Plant Block #3 |  | 2007-03-01 | 2009-11-02
3 | Block #3 Early Power Block Common |  | 2007-03-15 | 2009-03-20
4 | Fuel Gas Supply System |  | 2007-03-15 | 2008-10-25
Activity | 3CF3520W16A01 | (FGSS #31) FDN Work(Misc. Equipment) | 2007-11-29 | 2008-02-29
Activity | 3CF3520W16A08 | (FGSS #32) FDN Work(Misc. Equipment) | 2007-11-29 | 2008-02-29
Activity | 3CF3520W58A10 | (FGSS #32) Piping Work(incl. Air leak Test & Blowing) | 2008-07-19 | 2008-10-02
Activity | 3CF3520W86A02 | (FGSS #31) ESD Valve Skid installation | 2008-07-19 | 2008-07-30
Activity | 3CF3520W86A09 | (FGSS #32) ESD Valve Skid installation | 2008-07-19 | 2008-07-30
Activity | 3CF3520W58A03 | (FGSS #31) Piping Work(incl. Air leak Test & Blowing)_Gas Farm Area | 2008-07-19 | 2008-10-02
Activity | 3CF3520W74A11 | (FGSS #32) Installation & Test - Elec. | 2008-08-04 | 2008-10-02
Activity | 3CF3520W90A12 | (FGSS #32) Installation & Test - I&C | 2008-08-04 | 2008-10-02
Activity | 3CF3520W74A04 | (FGSS #31) Installation & Test - Elec. | 2008-08-04 | 2008-10-02
Activity | 3CF3520W90A05 | (FGSS #31) Installation & Test - I&C | 2008-08-04 | 2008-10-02
Activity | 3SF3520W62A13 | (FGSS #32) Fuel Gas Receiving | 2008-10-18 | 2008-10-18
Activity | 3SF3520W62A06 | (FGSS #31)Fuel Gas Receiving | 2008-10-18 | 2008-10-18
Activity | 3SF3520W62A14 | (FGSS #32) Metering System Calibration with supplier | 2008-10-21 | 2008-10-25
Activity | 3SF3520W62A07.2 | (FGSS #31) Metering System Calibration with supplier | 2008-10-21 | 2008-10-25
5 | Gas Pressure Reducing System |  | 2007-06-01 | 2008-10-05
Activity | 3EF3520W00A28 | (GT/HRSG GPRS Shelter) GA & Load Data to Civil Design | 2007-06-01
Activity | 3EF3520W16A29 | (GT/HRSG GPRS Shelter) FDN Design | 2007-06-01 | 2007-10-04
Activity | 3EF3520W32A31 | (GT/HRSG GPRS Shelter) Structure Design | 2007-06-01 | 2007-10-04
Activity | 3PF3520W42A04P | (GPRS) P.O & Procurement for GT | 2007-06-01 | 2008-05-30
Activity | 3PF3520W42A14P | (GPRS) P.O & Procurement for HRSG | 2007-07-03 | 2008-07-01
Activity | 3EF3520W16A12 | (GPRS) FDN Design for HRSG | 2007-07-03 | 2007-11-09
Activity | 3EF3520W16A01 | (GPRS) FDN Design for GT | 2007-08-02 | 2007-10-16
Activity | 3CF3520W16A02 | (GPRS) FDN Work for GT | 2007-10-17 | 2007-12-13
Activity | 3CF3520W16A30 | (GT/HRSG GPRS Shelter) FDN Work | 2007-11-10 | 2008-01-10
Activity | 3CF3520W16A13 | (GPRS) FDN Work for HRSG | 2007-11-10 | 2008-01-07
Activity | 3CF3520W32A32 | (GT/HRSG GPRS Shelter) Structure Work | 2008-01-11 | 2008-04-12
Activity | 3PF3520W42A05T | (GPRS) Transportation for GT | 2008-05-31 | 2008-07-15
Activity | 3PF3520W42A15T | (GPRS) Transportation for HRSG | 2008-07-02 | 2008-08-15
Activity | 3CF3520W42A06 | (GPRS #31) Installation for GT | 2008-07-16 | 2008-09-30
Activity | 3CF3520W42A09 | (GPRS #32) Installation for GT | 2008-07-16 | 2008-09-30
Activity | 3CF3520W42A22 | (GPRS #31 for Fuel Change over) Installation | 2008-07-16 | 2008-08-26
Activity | 3CF3520W42A25 | (GPRS #32 for Fuel Change over) Installation | 2008-07-16 | 2008-08-26
Activity | 3CF3520W24A33 | (GT/HRSG GPRS Shelter) Shelter Finish | 2008-08-09 | 2008-09-30
Activity | 3CF3520W42A16 | (GPRS #31) Installation for HRSG | 2008-08-16 | 2008-09-26
Activity | 3CF3520W42A19 | (GPRS #32) Installation for HRSG | 2008-08-16 | 2008-09-26
Activity | 3SF3520W62A23 | (GPRS #31 for Fuel Change over) Loop chek & Motor Solo Test | 2008-08-27 | 2008-08-29
Activity | 3SF3520W62A26 | (GPRS #32 for Fuel Change over) Loop chek & Motor Solo Test | 2008-08-27 | 2008-08-29
Activity | 3SF3520W62A24 | (GPRS #31 for Fuel Change over) Function Test | 2008-08-30 | 2008-08-31
Activity | 3SF3520W62A27 | (GPRS #32 for Fuel Change over) Function Test | 2008-08-30 | 2008-08-31
Activity | 3SF3520W62A17 | (GPRS #31) Loop chek & Motor Solo Test for HRSG | 2008-09-27 | 2008-09-29
Activity | 3SF3520W62A20 | (GPRS #32) Loop chek & Motor Solo Test for HRSG | 2008-09-27 | 2008-09-29
Activity | 3SF3520W62A18 | (GPRS #31) Function Test for HRSG | 2008-09-30 | 2008-10-02
Activity | 3SF3520W62A21 | (GPRS #32) Function Test for HRSG | 2008-09-30 | 2008-10-02
Activity | 3SF3520W62A07 | (GPRS #31) Loop check for GT | 2008-10-01 | 2008-10-03
Activity | 3SF3520W62A10 | (GPRS #32) Loop check for GT | 2008-10-01 | 2008-10-03
Activity | 3SF3520W62A08 | (GPRS #31) Function Test for GT | 2008-10-04 | 2008-10-05
Activity | 3SF3520W62A11 | (GPRS #32) Function Test for GT | 2008-10-04 | 2008-10-05
5 | Fuel Gas Filter & Metering System |  | 2007-06-01 | 2008-08-21
Activity | 3EF3520W00A10 | (Filtering/Metering Station Shelter) GA & Load Data to Civil Design | 2007-06-01
Activity | 3EF3520W16A11 | (Filtering/Metering Station Shelter) FDN Design | 2007-06-01 | 2007-10-12
Activity | 3EF3520W32A13 | (Filtering/Metering Station Shelter) Structure Design | 2007-06-01 | 2007-10-12
Activity | 3PF3520W42A02.3P | (Filtering/Metering Station) P.O & Procurement | 2007-07-03 | 2008-06-02
Activity | 3CF3520W16A12 | (Filtering/Metering Station Shelter) FDN Work | 2007-10-13 | 2007-12-10
Activity | 3CF3520W32A14 | (Filtering/Metering Station Shelter) Structure Work | 2007-12-11 | 2008-02-09
Activity | 3PF3520W42A03.3T | (Filtering/Metering Station) Transportation | 2008-06-03 | 2008-07-17
Activity | 3CF3520W42A07.3 | (Filtering/Metering Station #32) Installation | 2008-07-18 | 2008-08-01
Activity | 3CF3520W42A04.3 | (Filtering/Metering Station #31) Installation | 2008-07-18 | 2008-08-01
Activity | 3SF3520W62A08.3 | (Filtering/Metering Station #32) Loop chek | 2008-08-02 | 2008-08-04
Activity | 3CF3520W24A15 | (Filtering/Metering Station Shelter) Shelter Finish | 2008-08-02 | 2008-08-21
Activity | 3SF3520W62A05.3 | (Filtering/Metering Station #31) Loop chek | 2008-08-02 | 2008-08-04
Activity | 3SF3520W62A09.3 | (Filtering/Metering Station #32) Function Test | 2008-08-05 | 2008-08-06
Activity | 3SF3520W62A06.3 | (Filtering/Metering Station #31) Function Test | 2008-08-05 | 2008-08-06
5 | Gas Heater |  | 2007-07-03 | 2008-08-26
Activity | 3EF3520W16A01.2 | (Gas HTR) FDN Design | 2007-07-03 | 2007-10-01
Activity | 3EF3520W32A03.2 | (Gas HTR) Structure Design | 2007-07-03 | 2007-10-01
Activity | 3PF3520W42A07.2P | (Gas HTR) P.O & Procurement | 2007-07-03 | 2008-06-02
Activity | 3CF3520W16A02.2 | (Gas HTR) FDN Work | 2007-10-02 | 2007-11-28
Activity | 3CF3520W32A04.2 | (Gas HTR) Structure Work | 2007-11-29 | 2008-01-29
Activity | 3PF3520W42A08.2T | (Gas HTR) Transportation | 2008-06-03 | 2008-07-17
Activity | 3CF3520W24A05.2 | (Gas HTR) Shelter Finish | 2008-07-18 | 2008-08-26
Activity | 3CF3520W42A09.2 | (Gas HTR #31) Installation | 2008-07-18 | 2008-08-02
Activity | 3CF3520W42A12.2 | (Gas HTR #32) Installation | 2008-07-18 | 2008-08-02
Activity | 3SF3520W62A10.2 | (Gas HTR #31) Loop chek | 2008-08-03 | 2008-08-05
Activity | 3SF3520W62A13.2 | (Gas HTR #32) Loop chek | 2008-08-03 | 2008-08-05
Activity | 3SF3520W62A11.2 | (Gas HTR #31) Function Test | 2008-08-06 | 2008-08-08
Activity | 3SF3520W62A14.2 | (Gas HTR #32) Function Test | 2008-08-06 | 2008-08-08
5 | Gas Compressor |  | 2007-03-15 | 2008-10-20
Activity | 3PF3520W42A05.1P | (Gas COMP PKG) P.O & Procurement | 2007-03-15 | 2008-06-13
Activity | 3EF3520W00A25.1 | (Gas COMP House) GA & Load Data to Civil Design | 2007-03-30
Activity | 3EF3520W16A26.1 | (Gas COMP House) FDN Design | 2007-05-01 | 2007-10-01
Activity | 3EF3520W32A28.1 | (Gas COMP House) Structure Design | 2007-05-01 | 2007-10-01
Activity | 3EF3520W16A01.1 | (Gas COMP PKG) FDN Design | 2007-08-02 | 2007-11-01
Activity | 3CF3520W16A27.1 | (Gas COMP House) FDN Work | 2007-10-02 | 2007-11-28
Activity | 3CF3520W16A02.1 | (Gas COMP PKG) FDN Work | 2007-11-02 | 2008-01-31
Activity | 3CF3520W32A29.1 | (Gas COMP House) Structure Work | 2007-11-29 | 2008-02-12
Activity | 3PF3520W42A06.1T | (Gas COMP PKG)Transportation | 2008-06-14 | 2008-07-29
Activity | 3CF3520W42A20.1 | (Gas COMP PKG #32) Installation_Lube oil Sys.(incl. Flushing) | 2008-07-30 | 2008-08-30
Activity | 3CF3520W42A17.1 | (Gas COMP PKG #32) Installation_Air Compressor | 2008-07-30 | 2008-08-30
Activity | 3CF3520W42A18.1 | (Gas COMP PKG #32) Installation_Air Ventilation | 2008-07-30 | 2008-08-30
Activity | 3CF3520W42A07.1 | (Gas COMP PKG #31) Installation_Gas Compressor | 2008-07-30 | 2008-08-30
Activity | 3CF3520W42A16.1 | (Gas COMP PKG #32) Installation_Gas Compressor | 2008-07-30 | 2008-08-30
Activity | 3CF3520W42A11.1 | (Gas COMP PKG #31) Installation_Lube oil Sys.(incl. Flushing) | 2008-07-30 | 2008-08-30
Activity | 3CF3520W42A08.1 | (Gas COMP PKG #31) Installation_Air Compressor | 2008-07-30 | 2008-08-30
Activity | 3CF3520W42A09.1 | (Gas COMP PKG #31) Installation_Air Ventilation | 2008-07-30 | 2008-08-30
Activity | 3CF3520W42A21.1 | (Gas COMP PKG #32) Installation_N2 Generation Sys. | 2008-09-01 | 2008-10-02
Activity | 3CF3520W42A19.1 | (Gas COMP PKG #32) Installation_Seal Gas Sys. | 2008-09-01 | 2008-10-02
Activity | 3CF3520W24A30.1 | (Gas COMP House) Shelter finish | 2008-09-01 | 2008-10-10
Activity | 3CF3520W42A12.1 | (Gas COMP PKG #31) Installation_N2 Generation Sys. | 2008-09-01 | 2008-10-02
Activity | 3CF3520W42A10.1 | (Gas COMP PKG #31) Installation_Seal Gas Sys. | 2008-09-01 | 2008-10-02
Activity | 3SF3520W62A13.1 | (Gas COMP PKG #31) Loop chek | 2008-10-03 | 2008-10-12
Activity | 3SF3520W62A22.1 | (Gas COMP PKG #32) Loop chek | 2008-10-03 | 2008-10-12
Activity | 3SF3520W62A14.1 | (Gas COMP PKG #31) Function Test | 2008-10-13 | 2008-10-17
Activity | 3SF3520W62A23.1 | (Gas COMP PKG #32) Function Test | 2008-10-13 | 2008-10-17
Activity | 3SF3520W62A15.1 | (Gas COMP PKG #31) Running Test | 2008-10-19 | 2008-10-20
Activity | 3SF3520W62A24.1 | (Gas COMP PKG #32) Running Test | 2008-10-19 | 2008-10-20
5 | Gas cooler |  | 2008-07-30 | 2008-08-30
Activity | 3CF3520W42A01.1 | (Gas Cooler #11) Installation(incl. fan) | 2008-07-30 | 2008-08-20
Activity | 3CF3520W42A05.1 | (Gas Cooler #32) Installation(incl. fan) | 2008-07-30 | 2008-08-20
Activity | 3SF3520W62A02.1 | (Gas Cooler #31) Loop chek | 2008-08-21 | 2008-08-25
Activity | 3SF3520W62A06.1 | (Gas Cooler #32) Loop chek | 2008-08-21 | 2008-08-25
Activity | 3SF3520W62A03.1 | (Gas Cooler #31) Function Test | 2008-08-26 | 2008-08-28
Activity | 3SF3520W62A07.1 | (Gas Cooler #32) Function Test | 2008-08-26 | 2008-08-28
Activity | 3SF3520W62A04.1 | (Gas Cooler #31) Running Test | 2008-08-29 | 2008-08-30
Activity | 3SF3520W62A08.1 | (Gas Cooler #32) Running Test | 2008-08-29 | 2008-08-30
4 | N2 Gas System |  | 2007-11-01 | 2008-08-09
Activity | 3PF3515W42A04P | (N2 Gas Equip) P.O & Procurement for FGSS(Local PROC.) | 2007-11-01 | 2008-07-01
Activity | 3EF3515W00A06 | (N2 Gas Station Shelter) GA & Load Data to Civil Design | 2007-12-03
Activity | 3EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | 2007-12-03 | 2008-03-03
Activity | 3CF3515W16A07 | (N2 Gas Station Shelter) FDN Work | 2008-03-04 | 2008-04-30
Activity | 3CF3515W32A09 | (N2 Gas Station Shelter) Shelter Work | 2008-05-01 | 2008-08-09
Activity | 3CF3515W42A05 | (N2 Gas Equip) Installation for FGSS | 2008-07-02 | 2008-08-01
4 | Electrical System |  | 2007-03-30 | 2009-03-20
5 | Generator Circuit Breaker (GCB) |  | 2007-05-31 | 2009-03-06
Activity | 3PF6500W86A02P | (GT GCB) P.O & Procurement | 2007-05-31 | 2008-05-30
Activity | 3PF6500W86A07P | (ST GCB) P.O & Procurement | 2007-10-02 | 2008-09-30
Activity | 3PF6500W86A03T | (GT GCB) Transportation | 2008-05-31 | 2008-07-15
Activity | 3CF6500W86A04 | (GT GCB) Installation | 2008-07-16 | 2008-08-15
Activity | 3SF6500W62A05 | (GT GCB) Function Test | 2008-08-16 | 2008-08-30
Activity | 3PF6500W86A08T | (ST GCB) Transportation | 2008-10-01 | 2008-11-14
Activity | 3CF6500W86A09 | (ST GCB) Installation | 2009-01-20 | 2009-02-19
Activity | 3SF6500W62A10 | (ST GCB) Function Test | 2009-02-20 | 2009-03-06
5 | Extra High Voltage Cable |  | 2007-08-02 | 2008-09-23
Activity | 3PF6040W74A06P | (EHV Cable) P.O & Procurement | 2007-08-02 | 2008-05-01
Activity | 3EF6040W16A02 | (Cable tunnel) FDN Design | 2007-08-02 | 2007-11-01
Activity | 3EF6040W16A01 | (Cable tunnel) Cable tunnel Design | 2007-08-02 | 2007-11-30
Activity | 3CF6040W16A03 | (Cable tunnel) Civil Work | 2007-11-02 | 2008-04-01
Activity | 3PF6040W74A07T | (EHV Cable) Transportation | 2008-05-02 | 2008-06-16
Activity | 3CF6040W38A04 | (Cable tunnel) F/F Work & Test | 2008-05-31 | 2008-07-16
Activity | 3CF6040W74A08 | (EHV Cable) Cable Electrical Work | 2008-06-17 | 2008-09-01
Activity | 3CF6040W62A09 | (EHV Cable) Function Test | 2008-09-02 | 2008-09-06
Activity | 3CF6040W74A10 | (EHV Cable) Connection with GIS & TR | 2008-09-17 | 2008-09-23
5 | Isolated Phase Busduct (IPB) |  | 2007-08-02 | 2008-10-27
Activity | 3PF6500W74A02P | (IPB) P.O & Procurement | 2007-08-02 | 2008-05-15
Activity | 3PF6500W74A03T | (IPB) Transportation | 2008-05-16 | 2008-06-30
Activity | 3CF6500W74A04 | (IPB) Installation form TR to GCB(incl. Support) | 2008-07-01 | 2008-09-01
Activity | 3CF6500W62A05 | (IPB) Insulation Test & Hi potential Test | 2008-09-02 | 2008-09-08
Activity | 3CF6500W74A06 | (IPB) IPB connection with TR & GCB | 2008-10-21 | 2008-10-27
5 | Power Transformer |  | 2007-04-02 | 2009-03-20
Activity | 3PF6500W70A04P | (GTG TR) P.O & Procurement | 2007-04-02 | 2008-06-16
Activity | 3PF6500W70A12P | (STG TR) P.O & Procurement | 2007-08-02 | 2008-09-30
Activity | 3EF6500W16A01 | (GTG TR) FDN Design | 2007-08-02 | 2007-11-30
Activity | 3CF6500W16A02 | (GTG TR) FDN & Firewall Work | 2007-12-01 | 2008-04-01
Activity | 3EF6500W16A09 | (STG TR) FDN Design | 2008-02-06 | 2008-07-04
Activity | 3PF6500W70A05T | (GTG TR) Transportation | 2008-06-17 | 2008-07-31
Activity | 3CF6500W16A10 | (STG TR) FDN & Firewall Work | 2008-07-05 | 2008-11-04
Activity | 3CF6500W70A06 | (GTG TR) Installation | 2008-08-01 | 2008-09-16
Activity | 3CF6500W38A07 | (GTG TR) F/F Install & test | 2008-09-17 | 2008-09-30
Activity | 3PF6500W70A13T | (STG TR) Transportation | 2008-10-01 | 2008-11-14
Activity | 3SF6500W62A08 | (GTG TR) Function Test | 2008-10-01 | 2008-10-07
Activity | 3CF6500W70A14 | (STG TR) Installation | 2008-11-15 | 2008-12-30
Activity | 3CF6500W38A15 | (STG TR) F/F test | 2008-12-31 | 2009-01-06
Activity | 3SF6500W62A16 | (STG TR) Function Test | 2009-03-07 | 2009-03-20
5 | Auxiliary Transformer |  | 2007-03-30 | 2008-10-20
Activity | 3PF6500W70A04.1P | (GTG UAT) P.O & Procurement | 2007-03-30 | 2008-05-16
Activity | 3EF6500W16A01.1 | (GTG UAT) FDN Design | 2007-05-01 | 2007-08-30
Activity | 3EF6500W00A09 | (GTG #31 & UAT Shelter) GA & Load Data to Civil Design | 2007-05-31
Activity | 3EF6500W16A10 | (GTG #31 & UAT Shelter) FDN Design | 2007-07-02 | 2007-10-11
Activity | 3EF6500W32A12 | (GTG #31 & UAT Shelter) Structure Design | 2007-07-02 | 2007-10-11
Activity | 3CF6500W16A02.1 | (GTG UAT) FDN Work & Firewall Work | 2007-12-04 | 2008-04-01
Activity | 3CF6500W16A11 | (GTG #31 & UAT Shelter) FDN Work | 2008-04-02 | 2008-05-29
Activity | 3PF6500W70A05.1T | (GTG UAT) Transportation | 2008-05-17 | 2008-07-01
Activity | 3CF6500W32A13 | (GTG #31 & UAT Shelter) Structure Work | 2008-05-30 | 2008-08-30
Activity | 3CF6500W70A06.1 | (GTG UAT) Installation | 2008-07-02 | 2008-08-16
Activity | 3CF6500W38A07.1 | (GTG UAT) F/F Install & test | 2008-08-18 | 2008-09-02
Activity | 3CF6500W38A14 | (GTG #31 & UAT Shelter) Installation & Test - Fire Fighting Sys. | 2008-09-01 | 2008-10-16
Activity | 3CF6500W74A15 | (GTG #31 & UAT Shelter) Installation & Test - Elec | 2008-09-01 | 2008-10-16
Activity | 3CF6500W90A16 | (GTG #31 & UAT Shelter) Installation & Test - I&C | 2008-09-01 | 2008-10-16
Activity | 3SF6500W62A08.1 | (GTG UAT) Function Test | 2008-10-17 | 2008-10-20
5 | Emergency Diesel Generator |  | 2007-08-01 | 2008-10-16
Activity | 3EF3530W00A01 | (Block #3 EDG) GA & Load Data to Civil Design | 2007-08-01
Activity | 3EF3530W16A14 | (Block #3 EDG BLDG) FDN Design | 2007-08-01 | 2007-10-29
Activity | 3EF3530W32A16 | (Block #3 EDG BLDG) Structure Design | 2007-08-01 | 2007-11-29
Activity | 3PF3530W42A06P | (Block #3 EDG) P.O & Procurement | 2007-08-01 | 2008-07-31
Activity | 3EF3530W16A02 | (Block #3 EDG) FDN Design | 2007-08-01 | 2007-10-29
Activity | 3CF3530W16A15 | (Block #3 EDG BLDG) FDN Work | 2008-01-01 | 2008-03-01
Activity | 3CF3530W16A03 | (Block #3 EDG) FDN Work | 2008-01-01 | 2008-03-01
Activity | 3CF3530W32A17 | (Block #3 EDG BLDG) Structure Work | 2008-03-03 | 2008-06-03
Activity | 3CF3530W90A21 | (Block #3 EDG BLDG) Installation & Test - I&C | 2008-06-04 | 2008-07-19
Activity | 3CF3530W38A18 | (Block #3 EDG BLDG) Installation - Fire Fighting Sys. | 2008-06-04 | 2008-07-19
Activity | 3CF3530W36A19 | (Block #3 EDG BLDG) Installation & Test - HVAC | 2008-06-04 | 2008-07-19
Activity | 3CF3530W74A20 | (Block #3 EDG BLDG) Installation & Test - Elec | 2008-06-04 | 2008-07-19
Activity | 3CF3530W24A22 | (Block #3 EDG BLDG) Building Finish | 2008-06-04 | 2008-08-15
Activity | 3PF3530W42A07T | (Block #3 EDG) Transportation | 2008-08-01 | 2008-09-15
Activity | 3CF3530W42A08 | (Block #3 EDG) Installation | 2008-09-16 | 2008-10-06
Activity | 3SF3530W62A09 | (Block #3 EDG) Loop chek | 2008-10-07 | 2008-10-08
Activity | 3SF3530W62A10 | (Block #3 EDG) Function Test | 2008-10-09 | 2008-10-10
Activity | 3SF3530W62A11 | (Block #3 EDG) System Operation | 2008-10-11 | 2008-10-12
Activity | 3SF3530W62A12 | (Block #3 EDG) Synchronization | 2008-10-13 | 2008-10-14
Activity | 3SF3530W62A13 | (Block #3 EDG) Load Operation | 2008-10-15 | 2008-10-16
3 | Block #3 Combined Power Block Common |  | 2007-03-01 | 2009-05-11
4 | Closed Cooling Water System for Block #3 |  | 2007-09-03 | 2008-12-25
Activity | 3PF3030W68A04P | (EXP Head Tank) P.O & Procurement | 2007-09-03 | 2008-09-30
Activity | 3PF3030W42A21P | (CCWP) P.O & Procurement | 2007-09-03 | 2008-09-02
Activity | 3EF3030W16A17 | (CCWP) FDN Design | 2007-09-03 | 2008-01-30
Activity | 3PF3030W42A14P | (CCW H/EX) P.O & Procurement | 2007-09-03 | 2008-09-16
Activity | 3EF3030W16A10 | (CCW H/EX) FDN Design | 2007-09-03 | 2008-01-30
Activity | 3EF3030W16A01 | (EXP Head Tank) FDN Design | 2007-11-02 | 2008-04-01
Activity | 3CF3030W16A18 | (CCWP) FDN Work | 2008-04-03 | 2008-05-30
Activity | 3CF3030W16A11 | (CCW H/EX) FDN Work | 2008-04-03 | 2008-06-28
Activity | 3CF3030W16A02 | (EXP Head Tank) FDN Work | 2008-06-04 | 2008-07-02
Activity | 3CF3030W58A07 | (CCWS) Piping Work | 2008-08-01 | 2008-11-01
Activity | 3PF3030W42A22T | (CCWP) Transportation | 2008-09-03 | 2008-10-17
Activity | 3PF3030W42A15T | (CCW H/EX) Transportation | 2008-09-17 | 2008-10-31
Activity | 3PF3030W68A05T | (EXP Head Tank) Transportation | 2008-10-01 | 2008-11-14
Activity | 3CF3030W74A08 | (CCWS) Installation & Test - Elec. | 2008-10-14 | 2008-12-12
Activity | 3CF3030W90A09 | (CCWS) Installation & Test - I&C | 2008-10-14 | 2008-12-12
Activity | 3CF3030W42A23 | (CCWP) Installation | 2008-10-18 | 2008-11-01
Activity | 3CF3030W42A16 | (CCW H/EX) Installation | 2008-11-03 | 2008-12-03
Activity | 3CF3030W68A06 | (EXP Head Tank) Installation | 2008-11-15 | 2008-12-12
Activity | 3SF3030W62A24 | (CCWS) Loop chek | 2008-12-13 | 2008-12-17
Activity | 3SF3030W62A25 | (CCWS) System Function Test | 2008-12-18 | 2008-12-22
Activity | 3SF3030W62A26 | (CCWS) Pump Operation | 2008-12-23 | 2008-12-25
4 | Clean & Dirty Oil System |  | 2007-10-31 | 2009-04-04
Activity | 3PF3546W42A18P | (Clean & Dirty LOP) P.O & Procurement | 2007-10-31 | 2008-12-02
Activity | 3EF3546W16A15 | (Clean & Dirty LOP) FDN Design | 2007-10-31 | 2008-03-31
Activity | 3PF3546W42A06P | (Clean Oil Tank) P.O & Procurement | 2007-11-01 | 2008-12-02
Activity | 3EF3546W16A03 | (Clean Oil Tank) FDN Design | 2007-11-01 | 2008-03-31
Activity | 3PF3546W42A12P | (Dirty Oil Tank) P.O & Procurement | 2007-11-01 | 2008-12-02
Activity | 3EF3546W16A09 | (Dirty Oil Tank) FDN Design | 2007-11-01 | 2008-03-31
Activity | 3CF3546W16A04 | (Clean Oil Tank) FDN Work | 2008-06-03 | 2008-08-02
Activity | 3CF3546W16A10 | (Dirty Oil Tank) FDN Work | 2008-06-03 | 2008-08-02
Activity | 3CF3546W16A16 | (Clean & Dirty LOP) FDN Work | 2008-06-03 | 2008-08-02
Activity | 3PF3546W42A07T | (Clean Oil Tank) Transportation | 2008-12-03 | 2009-01-16
Activity | 3PF3546W42A13T | (Dirty Oil Tank) Transportation | 2008-12-03 | 2009-01-16
Activity | 3PF3546W42A19T | (Clean & Dirty LOP) Transportation | 2008-12-03 | 2009-01-16
Activity | 3CF3546W42A08 | (Clean Oil Tank) Installation | 2009-01-17 | 2009-03-19
Activity | 3CF3546W42A14 | (Dirty Oil Tank) Installation | 2009-01-17 | 2009-03-20
Activity | 3CF3546W42A20 | (Clean & Dirty LOP) Installation & Test | 2009-01-17 | 2009-02-17
Activity | 3CF3546W58A21 | (Clean & Dirty Oil System) Piping Work | 2009-01-17 | 2009-04-04
Activity | 3CF3546W74A22 | (Clean & Dirty Oil System) Installation & Test - Elec. | 2009-03-05 | 2009-04-04
Activity | 3CF3546W90A23 | (Clean & Dirty Oil System) Installation & Test - I&C | 2009-03-05 | 2009-04-04
4 | Feed Water System |  | 2007-08-30 | 2009-03-23
Activity | 3PF3015W42A06P | (FWP) P.O & Procurement | 2007-08-30 | 2008-10-30
Activity | 3EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | 2007-10-31
Activity | 3EF3015W32A10 | (FWP Shelter) FDN & Shelter Design | 2007-10-31 | 2008-01-30
Activity | 3EF3015W16A03 | (FWP) FDN Design | 2007-10-31 | 2008-01-30
Activity | 3PF3015W58A14P | (FW PIPING) P.O & Procurement | 2007-11-02 | 2008-08-29
Activity | 3CF3015W16A11 | (FWP Shelter) FDN Work | 2008-01-31 | 2008-04-01
Activity | 3CF3015W32A12 | (FWP Shelter) Shelter Structure Work | 2008-04-02 | 2008-06-30
Activity | 3CF3015W16A04 | (FWP) FDN Work | 2008-04-03 | 2008-07-02
Activity | 3PF3015W58A15 | (FW PIPING) Transportation | 2008-08-30 | 2008-10-14
Activity | 3CF3015W58A16 | (FW PIPING) Piping Work (incl. Insulation) | 2008-10-15 | 2009-01-14
Activity | 3PF3015W42A07 | (FWP) Transportation | 2008-10-31 | 2008-12-13
Activity | 3CF3015W74A18 | (FWS) Installation & Test - Elec. | 2008-12-15 | 2009-02-14
Activity | 3CF3015W90A19 | (FWS) Installation & Test - I&C | 2008-12-15 | 2009-02-14
Activity | 3CF3015W42A08 | (FWP) Installation | 2008-12-15 | 2009-01-27
Activity | 3CF3015W62A17 | (FW PIPING) Hydro Test | 2009-01-15 | 2009-02-12
Activity | 3SF3015W62A20 | (FWS) Loop check | 2009-02-15 | 2009-03-06
Activity | 3SF3015W62A21 | (FWS) System Function Test | 2009-03-07 | 2009-03-20
Activity | 3SF3015W62A22 | (FWS) Pump Operation | 2009-03-21 | 2009-03-23
4 | Chemical Dosing System |  | 2007-09-26 | 2009-03-10
Activity | 3EF3045W00A06 | (Chemical Dosing BLDG) GA & Load Data to Civil Design | 2007-09-26
Activity | 3EF3045W16A07 | (Chemical Dosing BLDG) FDN Design | 2007-09-26 | 2008-01-23
Activity | 3EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | 2007-09-26 | 2008-01-23
Activity | 3PF3045W42A03P | (Chemical Dosing Equip) P.O & Procurement | 2007-09-26 | 2008-09-24
Activity | 3CF3045W16A08 | (Chemical Dosing BLDG) FDN Work | 2008-01-24 | 2008-03-25
Activity | 3CF3045W32A10 | (Chemical Dosing BLDG) Structure Work | 2008-03-26 | 2008-07-25
Activity | 3PF3045W42A04 | (Chemical Dosing Equip) Transportation | 2008-09-25 | 2008-11-08
Activity | 3CF3045W38A11 | (Chemical Dosing BLDG) Installation & Test - Fire Fighting Sys. | 2008-11-01 | 2008-12-27
Activity | 3CF3045W36A12 | (Chemical Dosing BLDG) Installation & Test - HVAC | 2008-11-01 | 2008-12-27
Activity | 3CF3045W74A13 | (Chemical Dosing BLDG) Installation & Test - Elec | 2008-11-01 | 2008-12-27
Activity | 3CF3045W24A15 | (Chemical Dosing BLDG) Building Finish | 2008-11-01 | 2008-12-27
Activity | 3CF3045W90A14 | (Chemical Dosing BLDG) Installation & Test - I&C | 2008-11-01 | 2008-12-27
Activity | 3CF3045W58A16 | (Chemical Dosing System) Piping Work | 2008-11-10 | 2009-02-09
Activity | 3CF3045W42A05 | (Chemical Dosing Equip) Installation | 2008-11-10 | 2009-01-09
Activity | 3CF3045W74A17 | (Chemical Dosing System) Installation & Test - Elec. | 2008-12-04 | 2009-02-04
Activity | 3CF3045W90A18 | (Chemical Dosing System) Installation & Test - I&C | 2008-12-04 | 2009-02-04
Activity | 3SF3045W62A19 | (Chemical Dosing System) Loop chek | 2009-02-10 | 2009-02-24
Activity | 3SF3045W62A20 | (Chemical Dosing System) System Function Test | 2009-02-25 | 2009-03-03
Activity | 3SF3045W62A21 | (Chemical Dosing System) System Operation | 2009-03-04 | 2009-03-10
4 | Sampling System |  | 2007-10-01 | 2009-04-07
Activity | 3PF3040W42A05P | (Sampling Equip) P.O & Procurement | 2007-10-01 | 2008-09-30
Activity | 3EF3040W16A02 | (Sampling Equip) FDN Design | 2008-01-01 | 2008-04-02
Activity | 3CF3040W16A03 | (Sampling Equip) FDN Work | 2008-04-03 | 2008-05-30
Activity | 3PF3040W42A06 | (Sampling Equip) Transportation | 2008-10-01 | 2008-11-15
Activity | 3CF3040W42A07 | (Sampling Equip) Installation | 2008-11-17 | 2008-12-16
Activity | 3CF3040W58A08 | (Sampling System) Piping Work | 2008-12-17 | 2009-03-13
Activity | 3CF3040W74A09 | (Sampling System) Installation & Test - Elec. | 2009-02-11 | 2009-03-13
Activity | 3CF3040W90A10 | (Sampling System) Installation & Test - I&C | 2009-02-11 | 2009-03-13
Activity | 3SF3040W62A11 | (Sampling System) Loop chek | 2009-03-14 | 2009-03-23
Activity | 3SF3040W62A12 | (Sampling System) Chiller Function Test | 2009-03-24 | 2009-03-28
Activity | 3SF3040W62A13 | (Sampling System) Sampling System Function Test | 2009-03-29 | 2009-04-02
Activity | 3SF3040W62A14 | (Sampling System) System Service | 2009-04-03 | 2009-04-07
4 | Condensate System |  | 2007-03-01 | 2009-03-25
5 | Condenser |  | 2007-03-01 | 2009-03-25
Activity | 3EF3020W00A15 | (COND) Condenser Design Data | 2007-03-01 | 2007-04-12
Activity | 3PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | 2007-10-03 | 2008-10-13
Activity | 3PF3020W42A12P | (COND Flash Box) P.O & Procurement | 2007-10-03 | 2008-09-01
Activity | 3EF3020W16A17 | (COND) FDN Design | 2007-10-03 | 2008-01-30
Activity | 3PF3020W42A20P | (COND) P.O & Procurement | 2007-10-03 | 2008-09-30
Activity | 3EF3020W16A09 | (COND Flash Box) FDN Design | 2008-01-02 | 2008-03-31
Activity | 3CF3020W16A18 | (COND) FDN Work | 2008-01-31 | 2008-05-02
Activity | 3EF3020W16A03 | (COND Air EXT Equip) FDN Design | 2008-03-01 | 2008-05-29
Activity | 3CF3020W16A10 | (COND Flash Box) FDN Work | 2008-04-01 | 2008-05-30
Activity | 3CF3020W16A04 | (COND Air EXT Equip) FDN Work | 2008-05-30 | 2008-07-28
Activity | 3PF3020W42A13T | (COND Flash Box) Transportation | 2008-09-02 | 2008-10-16
Activity | 3PF3020W42A21T | (COND) Transportation | 2008-10-01 | 2008-11-14
Activity | 3PF3020W42A07T | (COND Air EXT Equip) Transportation | 2008-10-14 | 2008-11-27
Activity | 3CF3020W42A14 | (COND Flash Box) Installation | 2008-10-17 | 2008-11-14
Activity | 3CF3020W42A22 | (COND) Installation | 2008-11-15 | 2009-02-14
Activity | 3CF3020W58A23 | (COND System) Piping Work(incl. Insulation) | 2008-11-24 | 2009-02-23
Activity | 3CF3020W74A24 | (COND System) Installation & Test - Elec. | 2008-11-24 | 2009-02-17
Activity | 3CF3020W90A25 | (COND System) Installation & Test - I&C | 2008-11-24 | 2009-02-17
Activity | 3CF3020W42A08 | (COND Air EXT Equip) Installation | 2008-11-28 | 2009-01-09
Activity | 3SF3020W62A26 | (COND System) Loop check | 2009-02-24 | 2009-03-10
Activity | 3SF3020W62A27 | (COND System) System Function Test | 2009-03-11 | 2009-03-20
Activity | 3SF3020W62A28 | (COND System) Pump Operation | 2009-03-21 | 2009-03-25
5 | Condenser Tube Cleaning System |  | 2007-10-31 | 2009-01-28
Activity | 3PF3020W42A02P | (CTCS) P.O & Procurement | 2007-10-31 | 2008-10-31
Activity | 3PF3020W42A03T | (CTCS) Transportation | 2008-11-01 | 2008-12-15
Activity | 3CF3020W42A04 | (CTCS) Installation | 2008-12-16 | 2009-01-28
5 | Condensate Extraction Pump |  | 2007-09-07 | 2009-02-11
Activity | 3PF3020W42A04P | (CEP) P.O & Procurement | 2007-09-07 | 2008-10-08
Activity | 3EF3020W16A01 | (CEP) FDN Design | 2007-10-09 | 2008-01-04
Activity | 3CF3020W16A02 | (CEP) FDN Work | 2008-01-05 | 2008-05-07
Activity | 3PF3020W42A05T | (CEP) Transportation | 2008-10-09 | 2008-11-22
Activity | 3CF3020W42A06 | (CEP) Installation | 2008-11-24 | 2009-02-11
4 | Auxiliary Cooling Water System |  | 2007-10-03 | 2009-03-31
Activity | 3PF3030W42A04P | (ACW PUMP) P.O & Procurement | 2007-10-03 | 2008-12-01
Activity | 3PF3030W58A10P | (ACW Piping) P.O & Procurement | 2007-10-03 | 2008-09-01
Activity | 3PF3030W58A11T | (ACW Piping) Transportation | 2008-09-02 | 2008-10-16
Activity | 3CF3030W58A12 | (ACW Piping) Piping Work | 2008-11-10 | 2009-02-10
Activity | 3PF3030W42A05T | (ACW PUMP) Transportation | 2008-12-02 | 2009-01-15
Activity | 3CF3030W42A06 | (ACW PUMP) Installation | 2009-01-16 | 2009-02-10
Activity | 3CF3030W74A07 | (ACW PUMP) Installation - Elec | 2009-02-11 | 2009-03-04
Activity | 3CF3030W90A08 | (ACW PUMP) Installation - I&C | 2009-02-11 | 2009-03-04
Activity | 3CF3030W62A13 | (ACW Piping) Hydro Test | 2009-02-11 | 2009-03-11
Activity | 3SF3030W62A14 | (ACWS) Loop check | 2009-03-12 | 2009-03-21
Activity | 3SF3030W62A15 | (ACWS) System Function Test | 2009-03-22 | 2009-03-26
Activity | 3SF3030W62A16 | (ACWS) Pump Operation | 2009-03-27 | 2009-03-31
4 | Steam System |  | 2007-04-02 | 2009-03-25
Activity | 3EF2510W00A01 | (Steam System) P&ID | 2007-04-02 | 2007-11-14
Activity | 3PF2510W58A08P | (Steam PIPING) P.O & Procurement | 2007-10-01 | 2008-07-02
Activity | 3PF2510W42A04P | (Silencer) P.O & Procurement | 2007-10-15 | 2008-09-15
Activity | 3PF2510W58A09T | (Steam PIPING) Transportation | 2008-07-03 | 2008-08-16
Activity | 3CF2510W58A10 | (Steam PIPING) Piping Work | 2008-08-18 | 2009-01-17
Activity | 3PF2510W42A05T | (Silencer) Transportation | 2008-09-16 | 2008-10-30
Activity | 3CF2510W74A12 | (Steam System) Installation & Test - Elec. | 2008-10-31 | 2009-01-24
Activity | 3CF2510W90A13 | (Steam System) Installation & Test - I&C | 2008-10-31 | 2009-01-24
Activity | 3CF2510W42A06 | (Silencer) Installation | 2008-10-31 | 2008-11-28
Activity | 3CF2510W62A11 | (Steam PIPING) Hydro Test | 2009-01-19 | 2009-02-18
Activity | 3SF2510W62A14 | (Steam System) Loop chek | 2009-02-19 | 2009-03-10
Activity | 3SF2510W62A15 | (Steam System) System Function Test | 2009-03-11 | 2009-03-20
Activity | 3SF2510W62A16 | (Steam System) System Service | 2009-03-21 | 2009-03-25
4 | Bypass System |  | 2007-04-02 | 2009-02-28
Activity | 3EF2510W00A01.1 | (Bypass System) P&ID & System Design | 2007-04-02 | 2007-11-01
Activity | 3PF2510W42A04.1P | (Bypass Valve) P.O & Procurement | 2007-08-20 | 2008-08-14
Activity | 3PF2510W42A05.1T | (Bypass Valve) Transportation | 2008-08-30 | 2008-10-14
Activity | 3CF2510W58A07.1 | (Bypass System) Piping Work | 2008-10-15 | 2009-01-13
Activity | 3CF2510W90A10.1 | (Bypass System) Installation & Test - I&C | 2008-10-15 | 2008-12-13
Activity | 3CF2510W74A09.1 | (Bypass System) Installation & Test - Elec. | 2008-10-15 | 2008-12-13
Activity | 3CF2510W42A06.1 | (Bypass Valve) Installation | 2008-10-15 | 2008-12-13
Activity | 3CF2510W62A08.1 | (Bypass System) Hydro Test | 2009-01-14 | 2009-01-30
Activity | 3SF2510W62A11.1 | (Bypass System) Loop check | 2009-01-31 | 2009-02-13
Activity | 3SF2510W62A12.1 | (Bypass System) System Function Test | 2009-02-14 | 2009-02-23
Activity | 3SF2510W62A13.1 | (Bypass System) System Service | 2009-02-24 | 2009-02-28
4 | Clean Drain System |  | 2007-03-15 | 2009-05-11
Activity | 3EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | 2007-03-15 | 2008-01-15
Activity | 3PF3020W42A12.1P | (Clean Drain Tank) P.O & Procurement | 2007-10-01 | 2008-10-31
Activity | 3PF3020W42A06.1P | (Clean Drain Flash Vessel) P.O & Procurement | 2007-10-03 | 2008-06-03
Activity | 3EF3020W16A03.1 | (Clean Drain Flash Vessel) FDN Design | 2007-10-03 | 2008-02-29
Activity | 3EF3020W16A15.1 | (Clean Drain Pump) FDN Design | 2007-10-03 | 2008-02-29
Activity | 3PF3020W42A18.1P | (Clean Drain Pump) P.O & Procurement | 2007-10-03 | 2008-09-17
Activity | 3EF3020W16A09.1 | (Clean Drain Tank) FDN Design | 2007-12-06 | 2008-05-05
Activity | 3CF3020W16A04.1 | (Clean Drain Flash Vessel) FDN Work | 2008-03-01 | 2008-04-28
Activity | 3CF3020W16A16.1 | (Clean Drain Pump) FDN Work | 2008-03-01 | 2008-05-01
Activity | 3CF3020W16A10.1 | (Clean Drain Tank) FDN Work | 2008-05-06 | 2008-07-02
Activity | 3PF3020W42A07.1T | (Clean Drain Flash Vessel) Transportation | 2008-06-04 | 2008-07-18
Activity | 3CF3020W42A08.1 | (Clean Drain Flash Vessel) Installation | 2008-07-19 | 2008-08-16
Activity | 3PF3020W42A19.1T | (Clean Drain Pump) Transportation | 2008-09-18 | 2008-11-01
Activity | 3PF3020W42A13.1T | (Clean Drain Tank) Transportation | 2008-11-01 | 2008-12-15
Activity | 3CF3020W42A20.1 | (Clean Drain Pump) Installation | 2008-11-03 | 2008-11-30
Activity | 3CF3020W58A21.1 | (Clean Drain System) Piping Work | 2008-12-16 | 2009-03-18
Activity | 3CF3020W42A14.1 | (Clean Drain Tank) Installation | 2008-12-16 | 2009-01-13
Activity | 3CF3020W74A23.1 | (Clean Drain System) Installation & Test - Elec. | 2009-02-16 | 2009-03-18
Activity | 3CF3020W90A24.1 | (Clean Drain System) Installation & Test - I&C | 2009-02-16 | 2009-03-18
Activity | 3CF3020W62A22.1 | (Clean Drain System) Hydro Test | 2009-03-19 | 2009-04-16
Activity | 3SF3020W62A25.1 | (Clean Drain System) Loop chek | 2009-04-17 | 2009-05-06
Activity | 3SF3020W62A26.1 | (Clean Drain System) System Function Test | 2009-05-07 | 2009-05-09
Activity | 3SF3020W62A27.1 | (Clean Drain System) System Service | 2009-05-10 | 2009-05-11
3 | BOP Piping for Block #3 Common |  | 2007-03-01 | 2009-01-31
4 | Gas Supply System (GTG) |  | 2008-07-19 | 2008-09-18
Activity | 3CF3520W58A01 | (Gas Supply System) Piping Work(Yard area) | 2008-07-19 | 2008-09-18
4 | Oil Supply System (GTG) |  | 2008-03-03 | 2008-05-19
Activity | 3CF3520W58A01.1 | (Oil Supply System) Piping Work(Yard area) | 2008-03-03 | 2008-05-02
Activity | 3CF3520W62A02 | (Oil Supply System) Hydro Test | 2008-05-03 | 2008-05-19
4 | Make Up Wate Supply System (STG) |  | 2008-05-19 | 2008-08-04
Activity | 3CF3010W58A01 | (Make Up WTR Supply System) Piping Work(Block #3) | 2008-05-19 | 2008-07-18
Activity | 3CF3010W62A02 | (Make Up WTR Supply System) Hydro Test(Block #3) | 2008-07-19 | 2008-08-04
4 | Water Treatment Sytstem (BOP) |  | 2008-10-17 | 2009-01-01
Activity | 3CF3010W58A01.1 | (Water Treatment System) Piping Work(Block #3) | 2008-10-17 | 2008-12-16
Activity | 3CF3010W62A02.1 | (Water Treatment System) Hydro Test(Block #3) | 2008-12-17 | 2009-01-01
4 | Service Water System (BOP) |  | 2008-10-17 | 2009-01-01
Activity | 3CF3035W58A01 | (SWS) Piping Work(Block #3) | 2008-10-17 | 2008-12-16
Activity | 3CF3035W62A02 | (SWS) Hydro Test(Block #3) | 2008-12-17 | 2009-01-01
4 | Potable Water System (BOP) |  | 2008-11-04 | 2009-01-19
Activity | 3CF3035W58A01.1 | (PWS) Piping Work(Block #3) | 2008-11-04 | 2009-01-02
Activity | 3CF3035W62A02.1 | (PWS) Hydro Test(Block #3) | 2009-01-03 | 2009-01-19
4 | Compressed Air System (BOP) |  | 2008-09-02 | 2008-12-31
Activity | 3CF3510W58A01 | (COMP Air System) Piping Work(incl. Air blowing)_(Block #3) | 2008-09-02 | 2008-12-31
4 | Waste Water Treatment System (BOP) |  | 2008-10-17 | 2009-01-31
Activity | 3CF4035W58A01.1 | (WWTS) Piping Work(Block #3) | 2008-10-17 | 2009-01-15
Activity | 3CF4035W62A02.1 | (WWTS) Hydro Test(Block #3) | 2009-01-16 | 2009-01-31
4 | Sewage Water System (BOP) |  | 2008-10-17 | 2009-01-31
Activity | 3CF4035W58A01 | (STS) Piping Work(Block #3) | 2008-10-17 | 2009-01-15
Activity | 3CF4035W62A02 | (STS) Hydro Test(Block #3) | 2009-01-16 | 2009-01-31
4 | U/G Line |  | 2008-10-17 | 2009-01-16
Activity | 3CF4035W22A01 | (STRS) Piping Work(Block #3) | 2008-10-17 | 2009-01-10
Activity | 3CF4035W22A02 | (SWS) Piping Work(Block #3) | 2008-10-17 | 2009-01-16
4 | Pipe Rack |  | 2007-03-01 | 2008-08-01
Activity | 3EF5550W00A01 | (PipeRack) Pipe Rack Key Data | 2007-03-01 | 2007-03-29
Activity | 3EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | 2007-03-30
Activity | 3EF5550W20A05 | (PipeRack) Structure Design | 2007-05-30 | 2007-08-31
Activity | 3EF5550W16A03 | (PipeRack) FDN Design | 2007-05-30 | 2007-08-31
Activity | 3PF5550W46A08P | (PipeRack) P.O & Procurement | 2007-06-28 | 2008-03-04
Activity | 3CF5550W16A04 | (PipeRack) FDN Work Block #1 Area | 2007-09-01 | 2008-01-01
Activity | 3PF5550W46A09T | (PipeRack) Trasnportation | 2008-03-05 | 2008-04-18
Activity | 3CF5550W46A06 | (PipeRack) Structure Work for Block #1 Area | 2008-04-19 | 2008-08-01
3 | Gas Turbine & Generator #31 & #32 |  | 2007-03-01 | 2009-02-01
4 | GTG Common |  | 2007-03-01 | 2008-09-16
Activity | 3EF1200W00A01 | (GTG #31/#32) GTG Process Data (FG, FO, CCW) | 2007-03-01 | 2007-03-30
Activity | 3EF1200W00A02 | (GTG #31/#32) Instrument, Service Air, Aux steam Data | 2007-03-01 | 2007-03-29
Activity | 3EF1200W00A03 | (GTG #31/#32) Utility Consumption Data | 2007-03-01 | 2007-04-26
Activity | 3EF1200W00A04 | (GTG #31/#32) Emergency Load Data | 2007-03-01 | 2007-04-26
Activity | 3EF1200W00A05 | (GTG #31/#32) Black Start Load Data | 2007-03-01 | 2007-04-26
Activity | 3EF1210W00A06 | (GTG Common BLDG) GA & Load Data to Civil Design | 2007-03-01
Activity | 3EF1210W16A07 | (GTG Common BLDG) FDN Design | 2007-03-01 | 2007-08-01
Activity | 3EF1210W20A09 | (GTG Common BLDG) Structure Design | 2007-03-01 | 2007-08-31
Activity | 3PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | 2007-09-03 | 2008-03-17
Activity | 3CF1210W16A08 | (GTG Common BLDG) FDN Work | 2007-11-01 | 2008-02-29
Activity | 3CF1210W20A10 | (GTG Common BLDG) Structure Work(S/S, Cladding, Roof) | 2008-03-18 | 2008-07-19
Activity | 3CF1210W36A12 | (GTG Common BLDG) Installation & Test - HVAC | 2008-05-15 | 2008-07-11
Activity | 3CF1210W38A11 | (GTG Common BLDG) Installation & Test - Fire Fighting Sys. | 2008-05-31 | 2008-07-28
Activity | 3CF1210W90A14 | (GTG Common BLDG) Installation & Test - I&C | 2008-07-21 | 2008-09-16
Activity | 3CF1210W74A13 | (GTG Common BLDG) Installation & Test - Elec | 2008-07-21 | 2008-09-16
Activity | 3CF1210W24A15 | (GTG Common BLDG) Building Finish | 2008-07-26 | 2008-09-16
4 | GTG #31 LEB |  | 2007-05-31 | 2008-08-04
Activity | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | 2007-05-31
Activity | 3EF1200W16A02 | (GTG #31 LEB) FDN Design | 2007-08-01 | 2007-11-27
Activity | 3EF1200W32A04 | (GTG #31 LEB) Structure Design | 2007-08-01 | 2007-11-27
Activity | 3CF1200W16A03 | (GTG #31 LEB) FDN Work | 2007-11-28 | 2008-01-24
Activity | 3CF1200W32A05 | (GTG #31 LEB) Structure Work | 2008-01-25 | 2008-04-26
Activity | 3CF1200W36A07 | (GTG #31 LEB) Installation & Test - HVAC | 2008-05-15 | 2008-06-30
Activity | 3CF1200W24A10 | (GTG #31 LEB) Building Finish | 2008-05-27 | 2008-08-04
Activity | 3CF1200W38A06 | (GTG #31 LEB) Installation & Test - Fire Fighting Sys. | 2008-05-31 | 2008-07-04
Activity | 3CF1200W90A09 | (GTG #31 LEB) Installation & Test - I&C | 2008-06-04 | 2008-08-04
Activity | 3CF1200W74A08 | (GTG #31 LEB) Installation & Test - Elec | 2008-06-04 | 2008-08-04
4 | GTG #31 |  | 2007-04-30 | 2009-02-01
5 | GTG #31 Main body |  | 2007-04-30 | 2008-10-27
Activity | 3PF1213W42A08P | (GEN #31) P.O & Procurement | 2007-04-30 | 2008-03-31
Activity | 3EF1213W16A06 | (GEN #31) FDN Design | 2007-04-30 | 2007-09-27
Activity | 3PF1213W42A03P | (GT #31) P.O & Procurement | 2007-04-30 | 2008-03-31
Activity | 3EF1213W16A01 | (GT #31) FDN Design | 2007-04-30 | 2007-07-30
Activity | 3CF1213W16A07 | (GEN #31) FDN Work | 2007-10-01 | 2008-02-14
Activity | 3CF1213W16A02 | (GT #31) FDN Work | 2007-10-01 | 2008-02-14
Activity | 3PF1213W42A09T | (GEN #31) Transportation | 2008-04-01 | 2008-05-15
Activity | 3PF1213W42A04T | (GT #31) Transportation | 2008-04-01 | 2008-05-14
Activity | 3CF1213W42A05 | (GT #31) Installation(On FDN~Final Alignment) | 2008-05-15 | 2008-09-27
Activity | 3CF1213W42A10 | (GEN #31) Installation | 2008-06-27 | 2008-10-27
Activity | 3CF1213W52A11 | (GEN #31) Insulation | 2008-07-17 | 2008-07-31
5 | GTG #31 Electrical System |  | 2007-04-30 | 2008-09-26
Activity | 3PF1255W70A01P | (GTG#31 Electrical) P.O & Procurement | 2007-04-30 | 2008-05-28
Activity | 3PF1255W70A02T | (GTG#31 Electrical) Transportation | 2008-05-29 | 2008-07-12
Activity | 3CF1255W70A03 | (GTG#31 Electrical) Installation- PCC | 2008-08-01 | 2008-09-15
Activity | 3CF1255W70A04 | (GTG#31 Electrical) Installation- MCC | 2008-08-01 | 2008-09-15
Activity | 3CF1255W70A05 | (GTG#31 Electrical) Installation- Protection Sys. | 2008-08-01 | 2008-09-15
Activity | 3CF1255W70A07 | (GTG#31 Electrical) Installation- SEE&SFC Sys. | 2008-08-01 | 2008-09-15
Activity | 3CF1255W70A08 | (GTG#31 Electrical) Installation- DC&UPS Sys. | 2008-08-01 | 2008-09-15
Activity | 3CF1255W74A09 | (GTG#31 Electrical) Cable work | 2008-08-01 | 2008-09-15
Activity | 3CF1255W86A06 | (GTG#31 Electrical) Installation- GT control Sys. | 2008-08-04 | 2008-09-15
Activity | 3CF1255W62A10 | (GTG#31 Electrical) Electrical Function Test | 2008-09-16 | 2008-09-20
Activity | 3CF1255W62A11 | (GTG#31 Electrical) Loop Test | 2008-09-22 | 2008-09-26
5 | GTG #31 Starting System(Turning Device) |  | 2007-04-30 | 2008-07-25
Activity | 3PF1265W42A01P | (Turning Gear) P.O & Procurement | 2007-04-30 | 2008-04-29
Activity | 3PF1265W42A02T | (Turning Gear) Transportation | 2008-04-30 | 2008-06-13
Activity | 3CF1265W42A03 | (Turning Gear) Installation | 2008-06-14 | 2008-06-21
Activity | 3CF1265W74A04 | (Turning Gear) Installation- Elec. | 2008-06-23 | 2008-06-30
Activity | 3CF1265W90A05 | (Turning Gear) Installation- I&C | 2008-06-23 | 2008-06-30
Activity | 3SF1265W62A06 | (Turning Gear) Loop check | 2008-07-01 | 2008-07-05
Activity | 3SF1265W62A07.0 | (Turning Gear) Function Test | 2008-07-23 | 2008-07-25
5 | GTG #31 Air Intake System |  | 2007-04-30 | 2008-08-15
Activity | 3PF1230W20A02P | (Air Intake) P.O & Procurement_Steel Sturucture | 2007-04-30 | 2008-03-31
Activity | 3PF1230W64A05P | (Air Intake) P.O & Procurement_Inlet Duct | 2007-04-30 | 2008-03-31
Activity | 3PF1230W64A08P | (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2007-04-30 | 2008-03-31
Activity | 3CF1230W16A01 | (Air Intake) FDN Work_Steel Sturucture | 2007-11-30 | 2008-01-30
Activity | 3PF1230W20A03T | (Air Intake) Transportation_Steel Sturucture | 2008-04-01 | 2008-05-15
Activity | 3PF1230W64A06T | (Air Intake) Transportation_Inlet Duct | 2008-04-01 | 2008-05-15
Activity | 3PF1230W64A09T | (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-04-01 | 2008-05-15
Activity | 3CF1230W20A04 | (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | 2008-05-16 | 2008-06-17
Activity | 3CF1230W64A07 | (Air Intake) Installation_Inlet Duct | 2008-06-18 | 2008-06-25
Activity | 3CF1230W64A10 | (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-06-26 | 2008-07-19
Activity | 3CF1230W74A11 | (Air Intake) Installation- Elec. | 2008-07-21 | 2008-08-02
Activity | 3CF1230W90A12 | (Air Intake) Installation- I&C | 2008-07-21 | 2008-08-02
Activity | 3SF1230W62A13 | (Air Intake) Loop chek | 2008-08-03 | 2008-08-05
Activity | 3SF1230W62A14 | (Air Intake) Function Test | 2008-08-10 | 2008-08-12
Activity | 3SF1230W62A15 | (Air Intake) Load(Running) Test | 2008-08-13 | 2008-08-15
5 | GTG #31 Air and Flue Gas System |  | 2007-04-30 | 2008-07-18
Activity | 3PF1265W64A01P | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | 2007-04-30 | 2008-03-31
Activity | 3PF1265W64A02T | (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | 2008-04-01 | 2008-05-15
Activity | 3CF1265W64A03 | (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | 2008-05-16 | 2008-06-16
Activity | 3CF1265W64A04 | (Air&Flue Gas System) Duct work | 2008-06-17 | 2008-07-01
Activity | 3CF1265W74A05 | (Air&Flue Gas System) Installation- Elec. | 2008-07-02 | 2008-07-15
Activity | 3CF1265W90A06 | (Air&Flue Gas System) Installation- I&C | 2008-07-02 | 2008-07-15
Activity | 3SF1265W62A07 | (Air&Flue Gas System) Loop chek | 2008-07-13 | 2008-07-15
Activity | 3SF1265W62A08 | (Air&Flue Gas System) Function Test | 2008-07-16 | 2008-07-18
5 | GTG #31 Lube Oil System |  | 2007-04-30 | 2008-07-22
Activity | 3PF1250W42A02P | (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | 2007-04-30 | 2008-03-28
Activity | 3PF1250W42A06P | (Lube Oil System) P.O & Procurement_Lube oil functional Module | 2007-04-30 | 2008-03-28
Activity | 3PF1250W42A10P | (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | 2007-04-30 | 2008-03-28
Activity | 3CF1250W16A01 | (Lube Oil System) FDN Work_Lube Oil Supply Module | 2007-11-30 | 2008-01-30
Activity | 3CF1250W16A05 | (Lube Oil System) FDN Work_Lube oil functional Module | 2007-11-30 | 2008-01-30
Activity | 3CF1250W16A09 | (Lube Oil System) FDN Work_Lube oil Mist Separator | 2007-11-30 | 2008-01-30
Activity | 3PF1250W42A03T | (Lube Oil System) Transportation_Lube Oil Supply Module | 2008-03-29 | 2008-05-13
Activity | 3PF1250W42A07T | (Lube Oil System) Transportation_Lube oil functional Module | 2008-03-29 | 2008-05-13
Activity | 3PF1250W42A11T | (Lube Oil System) Transportation_Lube oil Mist Separator | 2008-03-29 | 2008-05-13
Activity | 3CF1250W42A04 | (Lube Oil System) Installation_Lube Oil Supply Module | 2008-05-14 | 2008-05-29
Activity | 3CF1250W42A08 | (Lube Oil System) Installation_Lube oil functional Module | 2008-05-14 | 2008-05-29
Activity | 3CF1250W42A12 | (Lube Oil System) Installation_Lube oil Mist Separator | 2008-05-14 | 2008-05-21
Activity | 3CF1250W58A13 | (Lube Oil System) Piping work | 2008-05-30 | 2008-06-30
Activity | 3CF1250W62A16 | (GTG #11) Lube Oil Flushing | 2008-06-30 | 2008-07-16
Activity | 3CF1250W74A14 | (Lube Oil System) Installation- Elec. | 2008-07-01 | 2008-07-14
Activity | 3CF1250W90A15 | (Lube Oil System) Installation- I&C | 2008-07-01 | 2008-07-14
Activity | 3SF1250W62A17 | (Lube Oil System) Loop chek | 2008-07-15 | 2008-07-17
Activity | 3SF1250W62A18 | (Lube Oil System) Function Test | 2008-07-18 | 2008-07-20
Activity | 3SF1250W62A19 | (Lube Oil System) Load Test | 2008-07-21 | 2008-07-22
5 | GTG #31 Generator Seal Oil System |  | 2007-04-30 | 2008-07-18
Activity | 3PF1250W42A02.0P | (GEN Seal Oil Sys.) P.O & Procurement | 2007-04-30 | 2008-03-28
Activity | 3CF1250W16A01.0 | (GEN Seal Oil Sys.) FDN Work | 2007-11-30 | 2008-02-25
Activity | 3PF1250W42A03.0T | (GEN Seal Oil Sys.) Transportation | 2008-03-29 | 2008-05-13
Activity | 3CF1250W42A04.0 | (GEN Seal Oil Sys.) Installation | 2008-05-14 | 2008-05-28
Activity | 3CF1250W58A05 | (GEN Seal Oil Sys.) Piping Work | 2008-05-29 | 2008-06-28
Activity | 3CF1250W74A06 | (GEN Seal Oil Sys.) Installation- Elec. | 2008-06-30 | 2008-07-12
Activity | 3CF1250W90A07 | (GEN Seal Oil Sys.) Installation- I&C | 2008-06-30 | 2008-07-12
Activity | 3SF1250W62A08 | (GEN Seal Oil Sys.) Oil Flushing | 2008-06-30 | 2008-07-04
Activity | 3SF1250W62A09 | (GEN Seal Oil Sys.) Loop chek | 2008-07-13 | 2008-07-15
Activity | 3SF1250W62A10 | (GEN Seal Oil Sys.) Function Test | 2008-07-16 | 2008-07-18
5 | GTG #31 Fuel Gas Supply System |  | 2007-04-30 | 2008-10-21
Activity | 3PF1265W42A03P | (Gas Final Filter & Metering Skid) P.O & Procurement | 2007-04-30 | 2008-03-28
Activity | 3EF1265W16A01 | (Gas Final Filter & Metering Skid) FDN Design | 2007-04-30 | 2007-10-30
Activity | 3PF1265W42A13P | (TCA Cooler) P.O & Procurement | 2007-04-30 | 2008-04-29
Activity | 3CF1265W16A02 | (Gas Final Filter & Metering Skid) FDN Work | 2007-10-31 | 2008-01-25
Activity | 3CF1265W16A12 | (TCA Cooler) FDN Work | 2007-11-30 | 2008-01-30
Activity | 3PF1265W42A04T | (Gas Final Filter & Metering Skid) Transportation | 2008-03-29 | 2008-05-13
Activity | 3PF1265W42A14T | (TCA Cooler) Transportation | 2008-04-30 | 2008-06-13
Activity | 3CF1265W42A05 | (Gas Final Filter & Metering Skid) Installation | 2008-05-14 | 2008-06-14
Activity | 3CF1265W42A15 | (TCA Cooler) Installation | 2008-06-14 | 2008-07-15
Activity | 3CF1265W58A06 | (FGSS) Piping Work(incl. Airblowing Test)_Power block Area | 2008-07-19 | 2008-09-03
Activity | 3CF1265W74A07 | (FGSS) Installation- Elec. | 2008-09-04 | 2008-09-17
Activity | 3CF1265W90A08 | (FGSS) Installation- I&C | 2008-09-04 | 2008-09-17
Activity | 3SF1265W62A09 | (FGSS) Loop chek | 2008-10-03 | 2008-10-12
Activity | 3SF1265W62A10.7 | (FGSS) Function Test | 2008-10-13 | 2008-10-17
Activity | 3SF1265W62A11.7 | (FGSS) Gas Receiving upto GT Final Control Valve | 2008-10-19 | 2008-10-21
5 | GTG #31 Washing & Drain System |  | 2007-04-30 | 2008-08-26
Activity | 3PF1265W42A02.0P | (Washing & Drain system Skid) P.O & Procurement | 2007-04-30 | 2008-04-29
Activity | 3CF1265W16A01 | (Washing & Drain system Skid) FDN Work | 2007-11-30 | 2008-01-30
Activity | 3PF1265W42A03.0T | (Washing & Drain system Skid) Transportation | 2008-04-30 | 2008-06-13
Activity | 3CF1265W42A04 | (Washing & Drain system Skid) Installation | 2008-06-14 | 2008-07-01
Activity | 3CF1265W58A05 | (Washing & Drain system Skid) Piping work | 2008-07-02 | 2008-08-01
Activity | 3CF1265W74A06 | (Washing & Drain system Skid) Installation- Elec. | 2008-08-02 | 2008-08-15
Activity | 3CF1265W90A07 | (Washing & Drain system Skid) Installation- I&C | 2008-08-02 | 2008-08-15
Activity | 3CF1265W62A08 | (Washing & Drain system Skid) Flushing | 2008-08-02 | 2008-08-05
Activity | 3SF1265W62A09.0 | (Washing & Drain system Skid) Loop chek | 2008-08-16 | 2008-08-20
Activity | 3SF1265W62A10 | (Washing & Drain system Skid) Function Test | 2008-08-21 | 2008-08-23
Activity | 3SF1265W62A11 | (Washing & Drain system Skid) Load(Running) Test | 2008-08-24 | 2008-08-26
5 | GTG #31 Fuel Oil Injection System |  | 2007-04-30 | 2008-09-02
Activity | 3PF1265W42A02.8P | (Fuel oil injection System) P.O & Procurement | 2007-04-30 | 2008-04-29
Activity | 3PF1265W42A09P | (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | 2007-04-30 | 2008-03-31
Activity | 3PF1265W42A16P | (Water injection System) P.O & Procurement | 2007-04-30 | 2008-03-31
Activity | 3CF1265W16A01.8 | (Fuel oil injection System) FDN Work | 2007-11-30 | 2008-01-30
Activity | 3CF1265W16A08 | (Fuel oil injection Pump & actuator) FDN Work | 2007-11-30 | 2008-01-30
Activity | 3CF1265W16A15 | (Water injection System) FDN Work | 2007-11-30 | 2008-01-30
Activity | 3PF1265W42A10T | (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | 2008-04-01 | 2008-05-15
Activity | 3PF1265W42A17T | (Water injection System) Transportation | 2008-04-01 | 2008-05-15
Activity | 3PF1265W42A03.8T | (Fuel oil injection System) Transportation | 2008-04-30 | 2008-06-13
Activity | 3CF1265W42A11 | (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | 2008-05-16 | 2008-05-30
Activity | 3CF1265W42A18 | (Water injection System) Installation | 2008-05-16 | 2008-05-30
Activity | 3CF1265W58A19 | (Water injection System) Piping work | 2008-05-31 | 2008-06-14
Activity | 3CF1265W42A04.8 | (Fuel oil injection System) Installation | 2008-06-14 | 2008-06-28
Activity | 3CF1265W74A20 | (Water injection System) Installation- Elec. | 2008-06-16 | 2008-06-28
Activity | 3CF1265W90A21 | (Water injection System) Installation- I&C | 2008-06-16 | 2008-06-28
Activity | 3SF1265W62A22 | (Water injection System) Loop chek | 2008-06-29 | 2008-07-03
Activity | 3CF1265W58A05.8 | (Fuel oil injection System) Piping work | 2008-06-30 | 2008-07-14
Activity | 3SF1265W62A23 | (Water injection System) Function Test | 2008-07-04 | 2008-07-06
Activity | 3CF1265W74A06.8 | (Fuel oil injection System) Installation- Elec. | 2008-07-15 | 2008-07-28
Activity | 3CF1265W90A07.8 | (Fuel oil injection System) Installation- I&C | 2008-07-15 | 2008-07-28
Activity | 3SF1265W62A12 | (Fuel oil injection System) Loop chek | 2008-07-29 | 2008-07-31
Activity | 3SF1265W62A24 | (Water injection System) Load Test | 2008-08-12 | 2008-08-13
Activity | 3SF1265W62A13 | (Fuel oil injection System) Function Test | 2008-08-15 | 2008-08-19
Activity | 3SF1265W62A14 | (Fuel oil injection System) Flushing | 2008-08-30 | 2008-09-02
5 | GTG #31 Vibration Monitoring System (VMS) |  | 2007-08-31 | 2008-10-11
Activity | 3PF1260W86A02P | (VMS) P.O & Procurement for GT | 2007-08-31 | 2008-07-02
Activity | 3PF1260W86A03T | (VMS) Transportation for GT | 2008-07-03 | 2008-08-16
Activity | 3CF1260W86A04 | (VMS) Installation for GT | 2008-09-29 | 2008-10-06
Activity | 3SF1260W62A05 | (VMS) Function Test for GT | 2008-10-07 | 2008-10-11
5 | GTG #31 Closed Cooling Water System |  | 2007-04-30 | 2008-09-18
Activity | 3EF1225W00A01 | (CCWS) CCW H/EX key data | 2007-04-30 | 2007-06-28
Activity | 3PF1225W42A18P | (EXP Head Tank) P.O & Procurement | 2007-07-03 | 2008-05-30
Activity | 3EF1225W16A15 | (EXP Head Tank) FDN Design | 2007-07-03 | 2007-11-29
Activity | 3PF1225W42A12P | (CCWP) P.O & Procurement for GT | 2007-07-03 | 2008-05-30
Activity | 3EF1225W16A09 | (CCWP) FDN Design | 2007-07-03 | 2007-11-29
Activity | 3PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | 2007-07-03 | 2008-05-30
Activity | 3EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | 2007-07-03 | 2007-11-29
Activity | 3CF1225W16A10 | (CCWP) FDN Work | 2007-11-30 | 2008-01-26
Activity | 3CF1225W16A03 | (CCW H/EX) FDN Work_Fin fan cooler | 2007-11-30 | 2008-02-25
Activity | 3CF1225W16A16 | (EXP Head Tank) FDN Work | 2008-02-01 | 2008-02-29
Activity | 3PF1225W42A19T | (EXP Head Tank) Transportation | 2008-05-31 | 2008-07-15
Activity | 3PF1225W42A13T | (CCWP) Transportation for GT | 2008-05-31 | 2008-07-15
Activity | 3PF1225W42A06T | (CCW H/EX) Transportation_Fin fan cooler | 2008-05-31 | 2008-07-15
Activity | 3CF1225W58A21 | (CCWS) Piping Work | 2008-06-26 | 2008-08-29
Activity | 3CF1225W42A20 | (EXP Head Tank) Installation | 2008-07-16 | 2008-08-13
Activity | 3CF1225W42A14 | (CCWP) Installation | 2008-07-16 | 2008-07-30
Activity | 3CF1225W42A07 | (CCW H/EX) Installation_Fin fan cooler | 2008-07-16 | 2008-08-29
Activity | 3CF1225W74A22 | (CCWS) Installation & Test - Elec. | 2008-07-30 | 2008-08-29
Activity | 3CF1225W90A23 | (CCWS) Installation & Test - I&C | 2008-07-30 | 2008-08-29
Activity | 3SF1225W62A24 | (CCWS) Loop chek | 2008-08-30 | 2008-09-08
Activity | 3SF1225W62A25 | (CCWS) Function Test | 2008-09-09 | 2008-09-13
Activity | 3SF1225W62A26 | (CCWS) Flushing | 2008-09-14 | 2008-09-18
5 | GTG #31 Fire fighting System |  | 2007-04-30 | 2008-09-02
Activity | 3PF1265W38A01P | (F/F GTG#31) P.O & Procurement_CO2 FF System | 2007-04-30 | 2008-05-13
Activity | 3PF1265W38A04P | (F/F GTG#31)P.O & Procurement_Clean Agent FF System | 2007-04-30 | 2008-05-13
Activity | 3PF1265W38A02T | (F/F GTG#31) Transportation_CO2 FF System | 2008-05-14 | 2008-06-27
Activity | 3PF1265W38A05T | (F/F GTG#31) Transportation_Clean Agent FF System | 2008-05-14 | 2008-06-27
Activity | 3CF1265W38A03 | (F/F GTG#31) Installation_CO2 FF System | 2008-06-28 | 2008-07-12
Activity | 3CF1265W38A06 | (F/F GTG#31) Installation_Clean Agent FF System | 2008-06-28 | 2008-07-12
Activity | 3CF1265W38A07 | (F/F GTG#31) Piping work | 2008-07-14 | 2008-08-06
Activity | 3SF1265W62A08.0 | (F/F GTG#31) Loop chek | 2008-08-07 | 2008-08-13
Activity | 3SF1265W62A09.00 | (F/F GTG#31) Function Test(incl. Alarm Test) | 2008-08-14 | 2008-08-23
Activity | 3SF1265W62A10.0 | (F/F GTG#31) CO2 Discharge Test | 2008-08-24 | 2008-09-02
5 | GTG #31 Auxiliary System |  | 2007-04-30 | 2008-08-09
Activity | 3PF1265W42A02.5P | (Purge Air System) P.O & Procurement | 2007-04-30 | 2008-03-31
Activity | 3PF1265W42A12P | (Control Oil) P.O & Procurement | 2007-04-30 | 2008-03-31
Activity | 3CF1265W16A01.5 | (Purge Air System) FDN Work | 2007-11-30 | 2008-01-30
Activity | 3CF1265W16A11 | (Control Oil) FDN Work | 2007-11-30 | 2008-01-30
Activity | 3PF1265W42A03.5T | (Purge Air System) Transportation | 2008-04-01 | 2008-05-15
Activity | 3PF1265W42A13.0T | (Control Oil)Transportation | 2008-04-01 | 2008-05-15
Activity | 3CF1265W42A04.5 | (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | 2008-05-16 | 2008-05-30
Activity | 3CF1265W42A14 | (Control Oil) Installation | 2008-05-16 | 2008-05-30
Activity | 3CF1265W58A05.5 | (Purge Air System) Piping work | 2008-05-31 | 2008-06-14
Activity | 3CF1265W58A15 | (Control Oil) Piping work | 2008-05-31 | 2008-07-01
Activity | 3CF1265W74A06.5 | (Purge Air System) Installation- Elec. | 2008-06-16 | 2008-06-28
Activity | 3CF1265W90A07.5 | (Purge Air System) Installation- I&C | 2008-06-16 | 2008-06-28
Activity | 3SF1265W62A08.5 | (Purge Air System) Loop chek | 2008-06-29 | 2008-07-01
Activity | 3SF1265W62A09.5 | (Purge Air System) Function Test | 2008-07-02 | 2008-07-04
Activity | 3CF1265W74A16 | (Control Oil) Installation- Elec. | 2008-07-02 | 2008-07-15
Activity | 3CF1265W90A17 | (Control Oil) Installation- I&C | 2008-07-02 | 2008-07-15
Activity | 3SF1265W62A10.5 | (Purge Air System) Load Test | 2008-07-05 | 2008-07-07
Activity | 3SF1265W62A18 | (Control Oil) Loop chek | 2008-07-16 | 2008-07-20
Activity | 3SF1265W62A19 | (Control Oil) Function Test | 2008-07-21 | 2008-07-30
Activity | 3SF1265W62A20 | (Control Oil) Flushing | 2008-07-31 | 2008-08-09
5 | GTG #31 Commissioning |  | 2008-10-28 | 2009-02-01
Activity | 3SF9011W62A01 | (GTG #31) Fuel Gas System Final Function Test | 2008-10-28 | 2008-10-30
Activity | 3SF9011W62A02 | (GTG #31) Turning Gear Operation | 2008-10-31 | 2008-11-01
Activity | 3SF9011W62A03 | (GTG #31) Initial Firing with FSNL | 2008-11-02 | 2008-11-02
Activity | 3SF9012W62A04 | (GTG #31) TBN & GEN Protection Test | 2008-11-03 | 2008-11-04
Activity | 3SF9012W62A05 | (GTG #31) 1st Synchronization | 2008-11-05 | 2008-11-06
Activity | 3SF9012W62A06 | (GTG #31) Optimization with Fuel Gas | 2008-11-07 | 2008-11-21
Activity | 3SF9012W62A07 | (GTG #31) Fuel Oil System Final Function Test | 2008-11-22 | 2008-12-01
Activity | 3SF9012W62A08 | (GTG #31) Optimization with Fuel Oil | 2008-12-02 | 2008-12-31
Activity | 3SF9012W62A09 | (GTG #31) Black start Test with GT | 2009-01-01 | 2009-01-01
Activity | 3SF9012W62A13 | (GTG #31) Fuel Change-Over Test | 2009-01-01 | 2009-01-13
Activity | 3SF9012W62A10 | (GTG #31) Trial Run Test | 2009-01-02 | 2009-01-02
Activity | 3SF9013W62A11 | (GTG #31) Reliability Test | 2009-01-03 | 2009-01-17
Activity | 3SF9013W62A12 | (GTG #31) Performance Test (Fuel Gas & Fuel Oil) | 2009-01-18 | 2009-02-01
4 | GTG #32 |  | 2007-04-30 | 2009-02-01
5 | GTG #32 Main body |  | 2007-04-30 | 2008-10-14
Activity | 3PF1213W42A08.1P | (Gen #32) P.O & Procurement | 2007-04-30 | 2008-03-31
Activity | 3EF1213W16A06.1 | (Gen #32) FDN Design | 2007-04-30 | 2007-09-27
Activity | 3PF1213W42A03.1P | (GT #32) P.O & Procurement | 2007-04-30 | 2008-04-29
Activity | 3EF1213W16A01.1 | (GT #32) FDN Design | 2007-04-30 | 2007-09-27
Activity | 3CF1213W16A07.1 | (Gen #32) FDN Work | 2007-09-28 | 2008-02-12
Activity | 3CF1213W16A02.1 | (GT #32) FDN Work | 2007-09-28 | 2008-02-12
Activity | 3PF1213W42A09.1T | (Gen #32) Transportation | 2008-04-01 | 2008-05-15
Activity | 3PF1213W42A04.1T | (GT #32) Transportation | 2008-04-30 | 2008-06-12
Activity | 3CF1213W42A10.1 | (Gen #32) Installation | 2008-05-16 | 2008-09-16
Activity | 3CF1213W42A05.1 | (GT #32) Installation(On FDN~Final Alignment) | 2008-06-13 | 2008-10-14
Activity | 3CF1213W52A11.1 | (GT #32) Insulation | 2008-07-19 | 2008-08-02
5 | GTG #32 Electrical System |  | 2007-04-30 | 2008-09-26
Activity | 3PF1255W70A01.1P | (GTG#32 Electrical) P.O & Procurement | 2007-04-30 | 2008-05-28
Activity | 3PF1255W70A02.1T | (GTG#32 Electrical) Transportation | 2008-05-29 | 2008-07-12
Activity | 3CF1255W70A03.1 | (GTG#32 Electrical) Installation- PCC | 2008-08-01 | 2008-09-15
Activity | 3CF1255W70A04.1 | (GTG#32 Electrical) Installation- MCC | 2008-08-01 | 2008-09-15
Activity | 3CF1255W70A05.1 | (GTG#32 Electrical) Installation- Protection Sys. | 2008-08-01 | 2008-09-15
Activity | 3CF1255W70A07.1 | (GTG#32 Electrical) Installation- SEE&SFC Sys. | 2008-08-01 | 2008-09-15
Activity | 3CF1255W70A08.1 | (GTG#32 Electrical) Installation- DC&UPS Sys. | 2008-08-01 | 2008-09-15
Activity | 3CF1255W74A09.1 | (GTG#32 Electrical) Cable work | 2008-08-01 | 2008-09-15
Activity | 3CF1255W86A06.1 | (GTG#32 Electrical) Installation- GT control Sys. | 2008-08-04 | 2008-09-15
Activity | 3CF1255W62A10.1 | (GTG#32 Electrical) Electrical Function Test | 2008-09-16 | 2008-09-20
Activity | 3CF1255W62A11.1 | (GTG#32 Electrical) Loop Test | 2008-09-22 | 2008-09-26
5 | GTG #32 Starting System(Turning Device) |  | 2007-04-30 | 2008-07-27
Activity | 3PF1265W42A01.1P | (Turning Gear) P.O & Procurement | 2007-04-30 | 2008-04-29
Activity | 3PF1265W42A02.1T | (Turning Gear) Transportation | 2008-04-30 | 2008-06-13
Activity | 3CF1265W42A03.1 | (Turning Gear) Installation | 2008-06-14 | 2008-06-21
Activity | 3CF1265W74A04.1 | (Turning Gear) Installation- Elec. | 2008-06-23 | 2008-06-30
Activity | 3CF1265W90A05.1 | (Turning Gear) Installation- I&C | 2008-06-23 | 2008-06-30
Activity | 3SF1265W62A06.1 | (Turning Gear) Loop check | 2008-07-01 | 2008-07-05
Activity | 3SF1265W62A07.1 | (Turning Gear) Function Test | 2008-07-25 | 2008-07-27
5 | GTG #32 Air Intake System |  | 2007-04-30 | 2008-08-15
Activity | 3PF1230W20A02.1P | (Air Intake) P.O & Procurement_Steel Sturucture | 2007-04-30 | 2008-03-31
Activity | 3PF1230W64A05.1P | (Air Intake) P.O & Procurement_Inlet Duct | 2007-04-30 | 2008-03-31
Activity | 3PF1230W64A08.1P | (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2007-04-30 | 2008-03-31
Activity | 3CF1230W16A01.1 | (Air Intake) FDN Work_Steel Sturucture | 2007-11-28 | 2008-01-28
Activity | 3PF1230W20A03.1T | (Air Intake) Transportation_Steel Sturucture | 2008-04-01 | 2008-05-15
Activity | 3PF1230W64A06.1T | (Air Intake) Transportation_Inlet Duct | 2008-04-01 | 2008-05-15
Activity | 3PF1230W64A09.1T | (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-04-01 | 2008-05-15
Activity | 3CF1230W20A04.1 | (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | 2008-06-02 | 2008-06-18
Activity | 3CF1230W64A07.1 | (Air Intake) Installation_Inlet Duct | 2008-06-19 | 2008-06-26
Activity | 3CF1230W64A10.1 | (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-06-27 | 2008-07-21
Activity | 3CF1230W74A11.1 | (Air Intake) Installation- Elec. | 2008-07-22 | 2008-08-04
Activity | 3CF1230W90A12.1 | (Air Intake) Installation- I&C | 2008-07-22 | 2008-08-04
Activity | 3SF1230W62A13.1 | (Air Intake) Loop chek | 2008-08-05 | 2008-08-07
Activity | 3SF1230W62A14.1 | (Air Intake) Function Test | 2008-08-10 | 2008-08-12
Activity | 3SF1230W62A15.1 | (Air Intake) Load(Running) Test | 2008-08-13 | 2008-08-15
5 | GTG #32 Air and Flue Gas System |  | 2007-04-30 | 2008-07-18
Activity | 3PF1265W64A01.1P | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | 2007-04-30 | 2008-03-31
Activity | 3PF1265W64A02.1T | (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | 2008-04-01 | 2008-05-15
Activity | 3CF1265W64A03.1 | (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | 2008-05-16 | 2008-06-16
Activity | 3CF1265W64A04.1 | (Air&Flue Gas System) Duct work | 2008-06-17 | 2008-07-01
Activity | 3CF1265W74A06.1 | (Air&Flue Gas System) Installation- Elec. | 2008-07-02 | 2008-07-15
Activity | 3CF1265W90A07.1 | (Air&Flue Gas System) Installation- I&C | 2008-07-02 | 2008-07-15
Activity | 3SF1265W62A05.1 | (Air&Flue Gas System) Loop chek | 2008-07-13 | 2008-07-15
Activity | 3SF1265W62A08.1 | (Air&Flue Gas System) Function Test | 2008-07-16 | 2008-07-18
5 | GTG #32 Lube Oil System |  | 2007-04-30 | 2008-07-24
Activity | 3PF1250W42A02.1P | (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | 2007-04-30 | 2008-03-31
Activity | 3PF1250W42A06.1P | (Lube Oil System) P.O & Procurement_Lube oil functional Module | 2007-04-30 | 2008-03-31
Activity | 3PF1250W42A10.1P | (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | 2007-04-30 | 2008-03-31
Activity | 3CF1250W16A01.1 | (Lube Oil System) FDN Work_Lube Oil Supply Module | 2007-11-28 | 2008-01-28
Activity | 3CF1250W16A05.1 | (Lube Oil System) FDN Work_Lube oil functional Module | 2007-11-28 | 2008-01-28
Activity | 3CF1250W16A09.1 | (Lube Oil System) FDN Work_Lube oil Mist Separator | 2007-11-28 | 2008-01-28
Activity | 3PF1250W42A03.1T | (Lube Oil System) Transportation_Lube Oil Supply Module | 2008-04-01 | 2008-05-15
Activity | 3PF1250W42A07.1T | (Lube Oil System) Transportation_Lube oil functional Module | 2008-04-01 | 2008-05-15
Activity | 3PF1250W42A11.1T | (Lube Oil System) Transportation_Lube oil Mist Separator | 2008-04-01 | 2008-05-15
Activity | 3CF1250W42A04.1 | (Lube Oil System) Installation_Lube Oil Supply Module | 2008-05-16 | 2008-05-31
Activity | 3CF1250W42A08.1 | (Lube Oil System) Installation_Lube oil functional Module | 2008-05-16 | 2008-05-31
Activity | 3CF1250W42A12.1 | (Lube Oil System) Installation_Lube oil Mist Separator | 2008-05-16 | 2008-05-23
Activity | 3CF1250W58A13.1 | (Lube Oil System) Piping work | 2008-06-02 | 2008-07-02
Activity | 3CF1250W62A16.1 | (GTG #32) Lube Oil Flushing | 2008-07-02 | 2008-07-18
Activity | 3CF1250W74A14.1 | (Lube Oil System) Installation- Elec. | 2008-07-03 | 2008-07-16
Activity | 3CF1250W90A15.1 | (Lube Oil System) Installation- I&C | 2008-07-03 | 2008-07-16
Activity | 3SF1250W62A17.1 | (Lube Oil System) Loop chek | 2008-07-17 | 2008-07-19
Activity | 3SF1250W62A18.1 | (Lube Oil System) Function Test | 2008-07-20 | 2008-07-22
Activity | 3SF1250W62A19.1 | (Lube Oil System) Load Test | 2008-07-23 | 2008-07-24
5 | GTG #32 Generator Seal Oil System |  | 2007-04-30 | 2008-07-21
Activity | 3PF1250W42A02.2P | (GEN Seal Oil Sys.) P.O & Procurement | 2007-04-30 | 2008-03-31
Activity | 3CF1250W16A01.2 | (GEN Seal Oil Sys.) FDN Work | 2007-11-28 | 2008-02-22
Activity | 3PF1250W42A03.2T | (GEN Seal Oil Sys.) Transportation | 2008-04-01 | 2008-05-15
Activity | 3CF1250W42A04.2 | (GEN Seal Oil Sys.) Installation | 2008-05-16 | 2008-05-30
Activity | 3CF1250W58A05.2 | (GEN Seal Oil Sys.) Piping Work | 2008-05-31 | 2008-07-01
Activity | 3CF1250W74A07.2 | (GEN Seal Oil Sys.) Installation- Elec. | 2008-07-02 | 2008-07-15
Activity | 3CF1250W90A08.2 | (GEN Seal Oil Sys.) Installation- I&C | 2008-07-02 | 2008-07-15
Activity | 3SF1250W62A06.2 | (GEN Seal Oil Sys.) Oil Flushing | 2008-07-02 | 2008-07-06
Activity | 3SF1250W62A09.2 | (GEN Seal Oil Sys.) Loop chek | 2008-07-16 | 2008-07-18
Activity | 3SF1250W62A10.2 | (GEN Seal Oil Sys.) Function Test | 2008-07-19 | 2008-07-21
5 | GTG #32 Fuel Gas Supply System |  | 2007-04-30 | 2008-10-21
Activity | 3PF1265W42A03.1P | (Gas Final Filter & Metering Skid) P.O & Procurement | 2007-04-30 | 2008-03-31
Activity | 3EF1265W16A01.1 | (Gas Final Filter & Metering Skid) FDN Design | 2007-04-30 | 2007-10-30
Activity | 3PF1265W42A13.4P | (TCA Cooler) P.O & Procurement | 2007-04-30 | 2008-04-29
Activity | 3CF1265W16A02.1 | (Gas Final Filter & Metering Skid) FDN Work | 2007-10-31 | 2008-01-25
Activity | 3CF1265W16A12.1 | (TCA Cooler) FDN Work | 2007-11-28 | 2008-01-28
Activity | 3PF1265W42A04.1T | (Gas Final Filter & Metering Skid) Transportation | 2008-04-01 | 2008-05-15
Activity | 3PF1265W42A14.1T | (TCA Cooler) Transportation | 2008-04-30 | 2008-06-13
Activity | 3CF1265W42A05.1 | (Gas Final Filter & Metering Skid) Installation | 2008-05-16 | 2008-05-30
Activity | 3CF1265W42A15.1 | (TCA Cooler) Installation | 2008-06-14 | 2008-06-28
Activity | 3CF1265W58A06.1 | (FGSS) Piping Work(incl. Airblowing Test)_Power Block Area | 2008-07-19 | 2008-08-19
Activity | 3CF1265W74A07.1 | (FGSS) Installation- Elec. | 2008-08-20 | 2008-09-02
Activity | 3CF1265W90A08.1 | (FGSS) Installation- I&C | 2008-08-20 | 2008-09-02
Activity | 3SF1265W62A09.1 | (FGSS) Loop chek | 2008-10-03 | 2008-10-12
Activity | 3SF1265W62A10.4 | (FGSS) Function Test | 2008-10-13 | 2008-10-17
Activity | 3SF1265W62A11.4 | (FGSS) Gas Receiving upto GT Final Control Valve | 2008-10-19 | 2008-10-21
5 | GTG #32 Washing & Drain System |  | 2007-04-30 | 2008-08-26
Activity | 3PF1265W42A02.2P | (Washing & Drain system Skid) P.O & Procurement | 2007-04-30 | 2008-04-29
Activity | 3CF1265W16A01.2 | (Washing & Drain system Skid) FDN Work | 2007-11-28 | 2008-01-28
Activity | 3PF1265W42A03.2T | (Washing & Drain system Skid) Transportation | 2008-04-30 | 2008-06-13
Activity | 3CF1265W42A04.2 | (Washing & Drain system Skid) Installation | 2008-06-14 | 2008-07-01
Activity | 3CF1265W58A05.2 | (Washing & Drain system Skid) Piping work | 2008-07-02 | 2008-08-01
Activity | 3CF1265W74A07.2 | (Washing & Drain system Skid) Installation- Elec. | 2008-08-02 | 2008-08-15
Activity | 3CF1265W90A08.2 | (Washing & Drain system Skid) Installation- I&C | 2008-08-02 | 2008-08-15
Activity | 3CF1265W62A06.2 | (Washing & Drain system Skid) Flushing | 2008-08-02 | 2008-08-05
Activity | 3SF1265W62A09.2 | (Washing & Drain system Skid) Loop chek | 2008-08-16 | 2008-08-20
Activity | 3SF1265W62A10.2 | (Washing & Drain system Skid) Function Test | 2008-08-21 | 2008-08-23
Activity | 3SF1265W62A11.2 | (Washing & Drain system Skid) Load(Running) Test | 2008-08-24 | 2008-08-26
5 | GTG #32 Fuel Oil Injection System |  | 2007-04-30 | 2008-09-02
Activity | 3PF1265W42A02.3P | (Fuel oil injection System) P.O & Procurement | 2007-04-30 | 2008-04-29
Activity | 3PF1265W42A12.1P | (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | 2007-04-30 | 2008-03-31
Activity | 3PF1265W42A15.1P | (Water injection System) P.O & Procurement | 2007-04-30 | 2008-03-31
Activity | 3CF1265W16A01.3 | (Fuel oil injection System) FDN Work | 2007-11-28 | 2008-01-28
Activity | 3CF1265W16A11.1 | (Fuel oil injection Pump & actuator) FDN Work | 2007-11-28 | 2008-01-28
Activity | 3CF1265W16A15.1 | (Water injection System) FDN Work | 2007-11-28 | 2008-01-28
Activity | 3PF1265W42A13.1T | (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | 2008-04-01 | 2008-05-15
Activity | 3PF1265W42A16.1T | (Water injection System) Transportation | 2008-04-01 | 2008-05-15
Activity | 3PF1265W42A03.3T | (Fuel oil injection System) Transportation | 2008-04-30 | 2008-06-13
Activity | 3CF1265W42A14.1 | (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | 2008-05-16 | 2008-05-30
Activity | 3CF1265W42A17.1 | (Water injection System) Installation | 2008-05-16 | 2008-05-30
Activity | 3CF1265W58A18.1 | (Water injection System) Piping work | 2008-05-31 | 2008-06-14
Activity | 3CF1265W42A04.3 | (Fuel oil injection System) Installation | 2008-06-14 | 2008-06-28
Activity | 3CF1265W74A19.1 | (Water injection System) Installation- Elec. | 2008-06-16 | 2008-06-28
Activity | 3CF1265W90A20.1 | (Water injection System) Installation- I&C | 2008-06-16 | 2008-06-28
Activity | 3SF1265W62A21.1 | (Water injection System) Loop chek | 2008-06-29 | 2008-07-03
Activity | 3CF1265W58A05.3 | (Fuel oil injection System) Piping work | 2008-06-30 | 2008-07-14
Activity | 3SF1265W62A22.1 | (Water injection System) Function Test | 2008-07-04 | 2008-07-06
Activity | 3CF1265W74A06.3 | (Fuel oil injection System) Installation- Elec. | 2008-07-15 | 2008-07-28
Activity | 3CF1265W90A07.3 | (Fuel oil injection System) Installation- I&C | 2008-07-15 | 2008-07-28
Activity | 3SF1265W62A08.3 | (Fuel oil injection System) Loop chek | 2008-07-29 | 2008-07-31
Activity | 3SF1265W62A23.1 | (Water injection System) Load Test | 2008-08-12 | 2008-08-13
Activity | 3SF1265W62A09.3 | (Fuel oil injection System) Function Test | 2008-08-15 | 2008-08-19
Activity | 3SF1265W62A10.3 | (Fuel oil injection System) Flushing | 2008-08-30 | 2008-09-02
5 | GTG #32 Vibration Monitoring System (VMS) |  | 2007-08-31 | 2008-10-27
Activity | 3PF1260W86A02.1P | (VMS) P.O & Procurement for GT | 2007-08-31 | 2008-07-30
Activity | 3PF1260W86A03.1T | (VMS) Transportation for GT | 2008-07-31 | 2008-09-13
Activity | 3CF1260W86A04.1 | (VMS) Installation for GT | 2008-10-15 | 2008-10-22
Activity | 3SF1260W62A05.1 | (VMS) Function Test for GT | 2008-10-23 | 2008-10-27
5 | GTG #32 Closed Cooling Water System |  | 2007-04-30 | 2008-09-18
Activity | 3EF1225W00A01.1 | (CCWS) CCW H/EX key data | 2007-04-30 | 2007-06-28
Activity | 3PF1225W42A12.1P | (EXP Head Tank) P.O & Procurement | 2007-07-03 | 2008-05-30
Activity | 3EF1225W16A09.1 | (EXP Head Tank) FDN Design | 2007-07-03 | 2007-11-29
Activity | 3PF1225W42A06.1P | (CCWP) P.O & Procurement for GT | 2007-07-03 | 2008-05-30
Activity | 3EF1225W16A03.1 | (CCWP) FDN Design | 2007-07-03 | 2007-11-29
Activity | 3PF1225W42A18.1P | (CCW H/EX) P.O & Procurement_Fin fan cooler | 2007-07-03 | 2008-05-30
Activity | 3EF1225W16A15.1 | (CCW H/EX) FDN Design_Fin fan cooler | 2007-07-03 | 2007-11-29
Activity | 3CF1225W16A04.1 | (CCWP) FDN Work | 2007-11-30 | 2008-01-26
Activity | 3CF1225W16A16.1 | (CCW H/EX) FDN Work_Fin fan cooler | 2007-11-30 | 2008-02-25
Activity | 3CF1225W16A10.1 | (EXP Head Tank) FDN Work | 2008-02-01 | 2008-02-29
Activity | 3PF1225W42A13.1T | (EXP Head Tank) Transportation | 2008-05-31 | 2008-07-15
Activity | 3PF1225W42A07.1T | (CCWP) Transportation for GT | 2008-05-31 | 2008-07-15
Activity | 3PF1225W42A19.1T | (CCW H/EX) Transportation_Fin fan cooler | 2008-05-31 | 2008-07-15
Activity | 3CF1225W58A21.1 | (CCWS) Piping Work | 2008-07-09 | 2008-08-29
Activity | 3CF1225W42A14.1 | (EXP Head Tank) Installation | 2008-07-16 | 2008-08-13
Activity | 3CF1225W42A08.1 | (CCWP) Installation | 2008-07-16 | 2008-07-30
Activity | 3CF1225W42A20.1 | (CCW H/EX) Installation_Fin fan cooler | 2008-07-16 | 2008-08-29
Activity | 3CF1225W74A22.1 | (CCWS) Installation & Test - Elec. | 2008-07-30 | 2008-08-29
Activity | 3CF1225W90A23.1 | (CCWS) Installation & Test - I&C | 2008-07-30 | 2008-08-29
Activity | 3SF1225W62A24.1 | (CCWS) Loop chek | 2008-08-30 | 2008-09-08
Activity | 3SF1225W62A25.1 | (CCWS) Function Test | 2008-09-09 | 2008-09-13
Activity | 3SF1225W62A26.1 | (CCWS) Flushing | 2008-09-14 | 2008-09-18
5 | GTG #32 Fire fighting System |  | 2007-04-30 | 2008-09-02
Activity | 3PF1265W38A01.2P | (F/F GTG#32) P.O & Procurement_CO2 FF System | 2007-04-30 | 2008-05-13
Activity | 3PF1265W38A04.2P | (F/F GTG#32) P.O & Procurement_Clean Agent FF System | 2007-04-30 | 2008-05-13
Activity | 3PF1265W38A02.2T | (F/F GTG#32) Transportation_CO2 FF System | 2008-05-14 | 2008-06-27
Activity | 3PF1265W38A05.2T | (F/F GTG#32)Transportation_Clean Agent FF System | 2008-05-14 | 2008-06-27
Activity | 3CF1265W38A03.2 | (F/F GTG#32) Installation_CO2 FF System | 2008-06-28 | 2008-07-12
Activity | 3CF1265W38A06.2 | (F/F GTG#32) Installation_Clean Agent FF System | 2008-06-28 | 2008-07-12
Activity | 3CF1265W38A07.2 | (F/F GTG#32) Piping work | 2008-07-14 | 2008-08-06
Activity | 3SF1265W62A08.2 | (F/F GTG#32) Loop chek | 2008-08-07 | 2008-08-13
Activity | 3SF1265W62A09.20 | (F/F GTG#32) Function Test(incl. Alarm Test) | 2008-08-14 | 2008-08-23
Activity | 3SF1265W62A10.20 | (F/F GTG#32) CO2 Discharge Test | 2008-08-24 | 2008-09-02
5 | GTG #32 Auxiliary System |  | 2007-04-30 | 2008-08-09
Activity | 3PF1265W42A02.6P | (Purge Air System) P.O & Procurement | 2007-04-30 | 2008-03-31
Activity | 3PF1265W42A12.6P | (Control Oil) P.O & Procurement | 2007-04-30 | 2008-03-31
Activity | 3CF1265W16A01.6 | (Purge Air System) FDN Work | 2007-11-28 | 2008-01-28
Activity | 3CF1265W16A11.6 | (Control Oil) FDN Work | 2007-11-28 | 2008-01-28
Activity | 3PF1265W42A03.6T | (Purge Air System) Transportation | 2008-04-01 | 2008-05-15
Activity | 3PF1265W42A13.6T | (Control Oil)Transportation | 2008-04-01 | 2008-05-15
Activity | 3CF1265W42A04.6 | (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | 2008-05-16 | 2008-05-30
Activity | 3CF1265W42A14.6 | (Control Oil) Installation | 2008-05-16 | 2008-05-30
Activity | 3CF1265W16A05.6 | (Purge Air System) Piping work | 2008-05-31 | 2008-06-14
Activity | 3CF1265W16A15.6 | (Control Oil) Piping work | 2008-05-31 | 2008-07-01
Activity | 3CF1265W74A06.6 | (Purge Air System) Installation- Elec. | 2008-06-16 | 2008-06-28
Activity | 3CF1265W90A07.6 | (Purge Air System) Installation- I&C | 2008-06-16 | 2008-06-28
Activity | 3SF1265W62A08.6 | (Purge Air System) Loop chek | 2008-06-29 | 2008-07-01
Activity | 3SF1265W62A09.6 | (Purge Air System) Function Test | 2008-07-02 | 2008-07-04
Activity | 3CF1265W74A16.6 | (Control Oil) Installation- Elec. | 2008-07-02 | 2008-07-15
Activity | 3CF1265W90A17.6 | (Control Oil) Installation- I&C | 2008-07-02 | 2008-07-15
Activity | 3SF1265W62A10.6 | (Purge Air System) Load Test | 2008-07-05 | 2008-07-07
Activity | 3SF1265W62A18.6 | (Control Oil) Loop chek | 2008-07-16 | 2008-07-20
Activity | 3SF1265W62A19.6 | (Control Oil) Function Test | 2008-07-21 | 2008-07-30
Activity | 3SF1265W62A20.6 | (Control Oil) Flushing | 2008-07-31 | 2008-08-09
5 | GTG #32 Commissioning |  | 2008-10-28 | 2009-02-01
Activity | 3SF9011W62A01.1 | (GTG #32) Fuel Gas System Final Function Test | 2008-10-28 | 2008-10-30
Activity | 3SF9011W62A02.1 | (GTG #32) Turning Gear Operation | 2008-10-31 | 2008-11-01
Activity | 3SF9011W62A03.1 | (GTG #32) Initial Firing with FSNL | 2008-11-02 | 2008-11-02
Activity | 3SF9012W62A04.1 | (GTG #32) TBN & GEN Protection Test | 2008-11-03 | 2008-11-04
Activity | 3SF9012W62A05.1 | (GTG #32) 1st Synchronization | 2008-11-05 | 2008-11-06
Activity | 3SF9012W62A06.1 | (GTG #32) Optimization with Fuel Gas | 2008-11-07 | 2008-11-21
Activity | 3SF9012W62A07.1 | (GTG #32) Fuel Oil System Final Function Test | 2008-11-22 | 2008-12-01
Activity | 3SF9012W62A08.1 | (GTG #32) Optimization with Fuel Oil | 2008-12-02 | 2008-12-31
Activity | 3SF9012W62A13.1 | (GTG #32) Fuel Change-Over Test | 2009-01-01 | 2009-01-13
Activity | 3SF9012W62A09.1 | (GTG #32) Black start Test with GT | 2009-01-01 | 2009-01-01
Activity | 3SF9012W62A10.1 | (GTG #32) Trial Run Test | 2009-01-02 | 2009-01-02
Activity | 3SF9013W62A11.1 | (GTG #32) Reliability Test | 2009-01-03 | 2009-01-17
Activity | 3SF9013W62A12.1 | (GTG #32) Performance Test (Fuel Gas & Fuel Oil) | 2009-01-18 | 2009-02-01
3 | HRSG #31 & #32 |  | 2007-03-01 | 2009-05-27
4 | HRSG Common |  | 2007-03-01 | 2008-05-06
Activity | 3EF1600W00A02 | (HRSG #31/#32) HRSG Process, GA Data | 2007-03-01 | 2007-03-30
Activity | 3EF1600W00A03 | (HRSG #31/#32) Instrument, Service Air Data | 2007-03-01 | 2007-03-29
Activity | 3EF1600W00A04 | (HRSG #31/#32) Utility Consumption Data | 2007-03-01 | 2007-04-26
Activity | 3EF1600W00A05 | (HRSG #31/#32) Emergency Load Data | 2007-03-01 | 2007-04-16
Activity | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | 2007-05-18 | 2008-05-06
4 | HRSG #31 |  | 2007-06-04 | 2009-05-27
5 | HRSG LEB |  | 2007-06-20 | 2008-12-15
Activity | 3EF1600W00A01 | (HRSG #31 LEB) GA & Load Data to Civil Design | 2007-06-20
Activity | 3EF1600W32A02 | (HRSG #31 LEB) Building Design | 2007-06-20 | 2007-11-20
Activity | 3PF1600W90A10P | (HRSG #31 LEB) P.O & Procurement - I&C | 2007-09-15 | 2008-08-23
Activity | 3PF1600W74A06P | (HRSG #31 LEB) P.O & Procurement - Elec | 2007-09-15 | 2008-08-23
Activity | 3CF1600W16A03 | (HRSG #31 LEB) FDN Work | 2008-03-03 | 2008-04-29
Activity | 3CF1600W32A04 | (HRSG #31 LEB) Structure Work | 2008-04-30 | 2008-07-25
Activity | 3CF1600W36A14 | (HRSG #31 LEB) Installation & Test - HVAC | 2008-07-31 | 2008-09-13
Activity | 3PF1600W90A11T | (HRSG #31 LEB) Transportataion - I&C | 2008-08-24 | 2008-10-07
Activity | 3PF1600W74A07T | (HRSG #31 LEB) Transportataion - Elec | 2008-08-24 | 2008-10-07
Activity | 3CF1600W90A12 | (HRSG #31 LEB) Installation & Test - I&C | 2008-10-20 | 2008-12-15
Activity | 3CF1600W74A08 | (HRSG #31 LEB) Installation & Test - Elec | 2008-10-20 | 2008-12-15
Activity | 3CF1600W38A13 | (HRSG #31 LEB) Installation & Test - Fire Fighting Sys. | 2008-11-01 | 2008-12-15
5 | Steel Structure & Casing |  | 2007-06-14 | 2008-09-16
Activity | 3PF1610W20A03P | (HRSG #31 S/Structure & Casing) P.O & Procurement | 2007-06-14 | 2008-04-02
Activity | 3EF1610W20A01 | (HRSG #31 S/Structure & Casing) Design | 2007-06-19 | 2008-01-15
Activity | 3PF1610W20A04T | (HRSG #31 S/Structure & Casing) Transportation | 2008-04-03 | 2008-05-17
Activity | 3CF1610W20A05 | (HRSG #31 S/Structure & Casing) S/Structure Installation | 2008-05-19 | 2008-07-18
Activity | 3CF1610W20A06 | (HRSG #31 S/Structure & Casing) Casing Installation | 2008-07-19 | 2008-09-16
5 | Duct |  | 2007-06-13 | 2009-03-06
Activity | 3PF1615W64A14P | (HRSG #31 EXP Joint & Bellows) P.O & Procurement | 2007-06-13 | 2008-05-30
Activity | 3PF1615W64A10P | (HRSG #31 Damper) P.O & Procurement | 2007-06-13 | 2008-05-01
Activity | 3PF1615W64A06P | (HRSG #31 Duct) P.O & Procurement | 2007-06-14 | 2008-04-02
Activity | 3EF1615W64A04 | (HRSG #31 Duct) Design | 2007-06-18 | 2007-12-19
Activity | 3EF1615W00A01 | (HRSG #31 Duct) GA & Load Data to Civil Design | 2007-06-29
Activity | 3EF1615W16A02 | (HRSG #31 Duct) FDN Design | 2007-10-03 | 2008-02-13
Activity | 3CF1615W16A03 | (HRSG #31 Duct) FDN Work | 2008-02-14 | 2008-05-16
Activity | 3PF1615W64A07T | (HRSG #31 Duct) Transportation | 2008-04-03 | 2008-05-17
Activity | 3PF1615W64A11T | (HRSG #31(HRSG #11 Damper) Transportation | 2008-05-02 | 2008-06-16
Activity | 3PF1615W64A15T | (HRSG #31 EXP Joint & Bellows) Transportation | 2008-05-31 | 2008-07-15
Activity | 3CF1615W64A12 | (HRSG #31 Damper) Installation | 2008-06-17 | 2008-08-16
Activity | 3CF1615W64A17 | (HRSG #31) Installation_Diverter Damper | 2008-07-02 | 2008-07-25
Activity | 3CF1615W64A20 | (HRSG #31) Installation_Guillotine Damper | 2008-07-26 | 2008-08-19
Activity | 3CF1615W86A18 | (HRSG #31) Installation_Diverter Damper Control Unit | 2008-07-26 | 2008-08-06
Activity | 3CF1615W62A19 | (HRSG #31) Diverter Damper Control Unit Flushing | 2008-08-07 | 2008-08-23
Activity | 3SF1615W62A21 | (HRSG #31) Diverter Damper Function Test for GT #31 | 2008-09-02 | 2008-09-06
Activity | 3SF1615W62A22 | (HRSG #31) Guillotine Damper Function Test for GT #31 | 2008-09-02 | 2008-09-06
Activity | 3CF1615W64A08 | (HRSG #31 Duct) Duct Installation | 2008-11-18 | 2009-02-17
Activity | 3CF1615W64A16 | (HRSG #31 EXP Joint & Bellows) Installation | 2009-01-20 | 2009-03-06
5 | Module |  | 2007-07-03 | 2008-11-17
Activity | 3PF1610W42A02P | (HRSG #31 Module) P.O & Procurement | 2007-07-03 | 2008-05-02
Activity | 3PF1610W42A03T | (HRSG #31 Module) Transportation | 2008-05-03 | 2008-06-17
Activity | 3CF1610W42A04 | (HRSG #31 Module) Installation | 2008-09-17 | 2008-11-17
5 | Drum |  | 2007-06-13 | 2008-12-15
Activity | 3PF1645W42A03P | (HRSG #31 Drum) P.O & Procurement | 2007-06-13 | 2008-07-01
Activity | 3EF1645W42A01 | (HRSG #31 Drum) Design | 2007-06-18 | 2008-01-08
Activity | 3PF1645W42A04T | (HRSG #31 Drum) Transportation | 2008-07-02 | 2008-08-15
Activity | 3CF1645W42A05 | (HRSG #31 Drum) Installation | 2008-11-18 | 2008-12-15
5 | Bypass Stack |  | 2007-06-13 | 2008-09-02
Activity | 3PF1625W42A10P | (HRSG #31Bypass Stack Silencer) P.O & Procurement | 2007-06-13 | 2008-05-30
Activity | 3EF1625W42A04 | (HRSG #31 Bypass Stack) Design | 2007-06-18 | 2007-12-28
Activity | 3PF1625W42A06P | (HRSG #31 Bypass Stack) P.O & Procurement | 2007-07-03 | 2008-04-01
Activity | 3EF1625W00A01 | (HRSG #31 Bypass Stack) GA & Load Data to Civil Design | 2007-08-01
Activity | 3EF1625W16A02 | (HRSG #31 Bypass Stack) FDN Design | 2007-11-05 | 2008-03-13
Activity | 3CF1625W16A03 | (HRSG #31 Bypass Stack) FDN Work | 2008-03-13 | 2008-05-31
Activity | 3PF1625W42A07T | (HRSG #31 Bypass Stack) Transportation | 2008-04-02 | 2008-05-16
Activity | 3PF1625W42A11T | (HRSG #31 Bypass Stack Silencer) Transportation | 2008-05-31 | 2008-07-15
Activity | 3CF1625W42A08 | (HRSG #31 Bypass Stack) Installation | 2008-05-31 | 2008-09-02
Activity | 3CF1625W42A12 | (HRSG #31 Bypass Stack Silencer) Installation | 2008-08-01 | 2008-08-30
5 | Main Stack |  | 2007-06-04 | 2009-04-22
Activity | 3PF1625W42A06.0P | (HRSG #31 Main Stack) P.O & Procurement | 2007-06-04 | 2008-04-02
Activity | 3EF1625W42A01 | (HRSG #31 Main Stack) Design | 2007-06-18 | 2007-12-28
Activity | 3PF1625W42A10.0P | (HRSG #31 Main Stack Silencer) P.O & Procurement | 2007-07-27 | 2008-07-15
Activity | 3EF1625W00A02 | (HRSG #31 Main Stack) GA & Load Data to Civil Design | 2007-08-06
Activity | 3EF1625W16A03 | (HRSG #31 Main Stack) FDN Design | 2007-11-08 | 2008-03-18
Activity | 3CF1625W16A04 | (HRSG #31Main Stack) FDN Work | 2008-03-18 | 2008-06-19
Activity | 3PF1625W42A07.0T | (HRSG #31 Main Stack) Transportation | 2008-04-03 | 2008-05-17
Activity | 3PF1625W42A11.0T | (HRSG #31 Main Stack Silencer) Transportation | 2008-07-16 | 2008-08-29
Activity | 3CF1625W42A08.0 | (HRSG #31 Main Stack) Installation | 2009-01-14 | 2009-04-14
Activity | 3CF1625W42A12.0 | (HRSG #31 Main Stack Silencer) Installation | 2009-03-25 | 2009-04-22
5 | Piping Work |  | 2008-01-09 | 2009-04-22
Activity | 3PF1650W52A02P | (HRSG #31 Insulation) P.O & Procurement | 2008-01-09 | 2008-12-01
Activity | 3CF1640W58A05 | (HRSG #31) Piping Work | 2008-12-01 | 2009-03-04
Activity | 3PF1650W52A03T | (HRSG #31 Insulation) Transportation | 2008-12-02 | 2009-01-15
Activity | 3CF1640W62A06 | (HRSG #31) Hydro Test | 2009-03-05 | 2009-03-28
Activity | 3CF1650W52A04 | (HRSG #31 Insulation) Installation | 2009-03-19 | 2009-04-22
Activity | 3CF1640W60A07 | (HRSG #31) Acid Cleaning | 2009-03-30 | 2009-04-21
5 | CEMS |  | 2007-08-29 | 2008-09-08
Activity | 3PF1660W86A04P | (CEMS) P.O & Procurement | 2007-08-29 | 2008-05-30
Activity | 3EF1660W16A01 | (CEMS) FDN Design | 2007-10-30 | 2008-01-25
Activity | 3CF1660W16A02 | (CEMS) FDN Work | 2008-01-26 | 2008-03-24
Activity | 3PF1660W86A05T | (CEMS) Transportation | 2008-05-31 | 2008-07-15
Activity | 3CF1660W86A06 | (CEMS) Installation(incl. Elec, I&C) | 2008-07-16 | 2008-07-31
Activity | 3CF1660W62A07 | (CEMS) Loop Test | 2008-08-01 | 2008-08-06
Activity | 3SF1615W62A08 | (HRSG #31) CEMS Function Test for GT #31(Bypass stack) | 2008-09-02 | 2008-09-08
5 | Auxiliary System |  | 2007-09-10 | 2009-04-01
Activity | 3PF1665W42A02P | (HRSG #31 MECH Vendor Equip) P.O & Procurement | 2007-09-10 | 2008-10-02
Activity | 3PF1655W86A11P | (HRSG #31 I&C Vendor Equip) P.O & Procurement | 2007-10-02 | 2008-10-03
Activity | 3PF1655W70A06P | (HRSG #31 ELEC Vendor Equip) P.O & Procurement | 2007-10-02 | 2008-10-03
Activity | 3PF1665W42A03T | (HRSG #31 MECH Vendor Equip) Transportation | 2008-10-03 | 2008-11-17
Activity | 3PF1655W86A12T | (HRSG #31 I&C Vendor Equip) Transportation | 2008-10-04 | 2008-11-18
Activity | 3PF1655W70A07T | (HRSG #31 ELEC Vendor Equip) Transportation | 2008-10-04 | 2008-11-18
Activity | 3CF1665W42A04 | (HRSG #31 MECH Vendor Equip) Installation | 2008-11-18 | 2009-03-02
Activity | 3CF1655W86A13 | (HRSG #31 I&C Vendor Equip) Installation | 2008-11-19 | 2009-03-13
Activity | 3CF1655W70A08 | (HRSG #31 ELEC Vendor Equip) Installation | 2008-11-19 | 2009-03-13
Activity | 3CF1655W74A09 | (HRSG #31) Installation & Test - Elec. | 2008-12-30 | 2009-04-01
Activity | 3CF1660W90A14 | (HRSG #31) Installation & Test - I&C | 2008-12-30 | 2009-04-01
5 | Commissioning |  | 2009-04-23 | 2009-05-27
Activity | 3SF1600W62A01 | (HRSG #31) Cold Commissioning for HRSG #31 | 2009-04-23 | 2009-05-12
Activity | 3SF1600W62A02 | (HRSG #31) Function Test for HRSG #31 | 2009-05-13 | 2009-05-27
4 | HRSG #32 |  | 2007-06-13 | 2009-05-27
5 | HRSG LEB |  | 2007-06-20 | 2008-12-15
Activity | 3EF1600W00A01.1 | (HRSG #32 LEB) GA & Load Data to Civil Design | 2007-06-20
Activity | 3EF1600W32A02.1 | (HRSG #32 LEB) Building Design | 2007-06-20 | 2007-11-20
Activity | 3PF1600W90A10.1P | (HRSG #32 LEB) P.O & Procurement - I&C | 2007-09-15 | 2008-08-23
Activity | 3PF1600W74A06.1P | (HRSG #32 LEB) P.O & Procurement - Elec | 2007-09-15 | 2008-08-23
Activity | 3CF1600W16A03.1 | (HRSG #32 LEB)FDN Work | 2008-03-03 | 2008-04-29
Activity | 3CF1600W32A04.1 | (HRSG #32 LEB)Structure Work | 2008-04-30 | 2008-07-25
Activity | 3CF1600W36A13.1 | (HRSG #32 LEB) Installation & Test - HVAC | 2008-07-31 | 2008-09-13
Activity | 3PF1600W90A11.1T | (HRSG #32 LEB) Transportataion - I&C | 2008-08-24 | 2008-10-07
Activity | 3PF1600W74A07.1T | (HRSG #32 LEB) Transportataion - Elec | 2008-08-24 | 2008-10-07
Activity | 3CF1600W90A12.1 | (HRSG #32 LEB) Installation & Test - I&C | 2008-10-20 | 2008-12-15
Activity | 3CF1600W74A08.1 | (HRSG #32 LEB) Installation & Test - Elec | 2008-10-20 | 2008-12-15
Activity | 3CF1600W38A14.1 | (HRSG #32 LEB) Installation & Test - Fire Fighting Sys. | 2008-11-01 | 2008-12-15
5 | Steel Structure & Casing |  | 2007-06-14 | 2008-09-16
Activity | 3PF1610W20A03.1 | (HRSG #32 S/Structure & Casing) P.O & Procurement | 2007-06-14 | 2008-04-02
Activity | 3EF1610W20A01.1 | (HRSG #32 S/Structure & Casing) Design | 2007-06-19 | 2008-01-15
Activity | 3PF1610W20A04.1T | (HRSG #32 S/Structure & Casing) Transportation | 2008-04-03 | 2008-05-17
Activity | 3CF1610W20A05.1 | (HRSG #32 S/Structure & Casing) S/Structure Installation | 2008-05-19 | 2008-07-18
Activity | 3CF1610W20A06.1 | (HRSG #32 S/Structure & Casing) Casing Installation | 2008-07-19 | 2008-09-16
5 | Duct |  | 2007-06-13 | 2009-03-06
Activity | 3PF1665W64A14.1P | (HRSG #32 EXP Joint & Bellows) P.O & Procurement | 2007-06-13 | 2008-05-30
Activity | 3PF1615W64A10.1P | (HRSG #32 Damper) P.O & Procurement | 2007-06-13 | 2008-05-01
Activity | 3PF1615W64A06.1P | (HRSG #32 Duct) P.O & Procurement | 2007-06-14 | 2008-04-02
Activity | 3EF1615W64A01.1 | (HRSG #32 Duct) Design | 2007-06-18 | 2007-12-19
Activity | 3EF1615W00A02.1 | (HRSG #32 Duct) GA & Load Data to Civil Design | 2007-06-29
Activity | 3EF1615W16A03.1 | (HRSG #32 Duct) FDN Design | 2007-10-03 | 2008-02-13
Activity | 3CF1615W16A04.1 | (HRSG #32 Duct) FDN Work | 2008-02-14 | 2008-05-16
Activity | 3PF1615W64A07.1T | (HRSG #32 Duct) Transportation | 2008-04-03 | 2008-05-17
Activity | 3PF1615W64A11.1T | (HRSG #32 Damper) Transportation | 2008-05-02 | 2008-06-16
Activity | 3PF1665W64A15.1T | (HRSG #32 EXP Joint & Bellows) Transportation | 2008-05-31 | 2008-07-15
Activity | 3CF1615W64A12.1 | (HRSG #32 Damper) Installation | 2008-06-17 | 2008-08-16
Activity | 3CF1615W64A17.1 | (HRSG #32) Installation_Diverter Damper | 2008-07-02 | 2008-07-25
Activity | 3CF1615W64A18.1 | (HRSG #32) Installation_Guillotine Damper | 2008-07-26 | 2008-08-19
Activity | 3CF1615W86A19.1 | (HRSG #32) Installation_Diverter Damper Control Unit | 2008-07-26 | 2008-08-06
Activity | 3CF1615W62A20.1 | (HRSG #32) Diverter Damper Control Unit Flushing | 2008-08-07 | 2008-08-23
Activity | 3SF1615W62A21.1 | (HRSG #32) Diverter Damper Function Test for GT #32 | 2008-09-02 | 2008-09-06
Activity | 3SF1615W62A22.1 | (HRSG #32) Guillotine Damper Function Test for GT #32 | 2008-09-02 | 2008-09-06
Activity | 3CF1615W64A08.1 | (HRSG #32 Duct) Duct Installation | 2008-11-18 | 2009-02-17
Activity | 3CF1665W64A16.1 | (HRSG #32 EXP Joint & Bellows) Installation | 2009-01-20 | 2009-03-06
5 | Module |  | 2007-07-03 | 2008-11-17
Activity | 3PF1610W42A02.1P | (HRSG #32 Module) P.O & Procurement | 2007-07-03 | 2008-05-02
Activity | 3PF1610W42A03.1T | (HRSG #32 Module) Transportation | 2008-05-03 | 2008-06-17
Activity | 3CF1610W42A04.1 | (HRSG #32 Module) Installation | 2008-09-17 | 2008-11-17
5 | Drum |  | 2007-06-13 | 2008-12-15
Activity | 3PF1645W42A03.1P | (HRSG #32 Drum) P.O & Procurement | 2007-06-13 | 2008-07-01
Activity | 3EF1645W42A01.1 | (HRSG #32 Drum) Design | 2007-06-18 | 2008-01-08
Activity | 3PF1645W42A04.1T | (HRSG #32 Drum) Transportation | 2008-07-02 | 2008-08-15
Activity | 3CF1645W42A05.1 | (HRSG #32 Drum) Installation | 2008-11-18 | 2008-12-15
5 | Bypass Stack |  | 2007-06-13 | 2008-09-02
Activity | 3PF1625W42A10.1P | (HRSG #32 Bypass Stack Silencer) P.O & Procurement | 2007-06-13 | 2008-05-30
Activity | 3EF1625W42A01.1 | (HRSG #32 Bypass Stack) Design | 2007-06-18 | 2007-12-28
Activity | 3PF1625W42A06.1P | (HRSG #32 Bypass Stack) P.O & Procurement | 2007-07-03 | 2008-04-01
Activity | 3EF1625W00A02.1 | (HRSG #32 Bypass Stack) GA & Load Data to Civil Design | 2007-08-01
Activity | 3EF1625W16A03.1 | (HRSG #32 Bypass Stack) FDN Design | 2007-11-05 | 2008-03-13
Activity | 3CF1625W16A04.1 | (HRSG #32 Bypass Stack) FDN Work | 2008-03-13 | 2008-05-31
Activity | 3PF1625W42A07.1T | (HRSG #32 Bypass Stack) Transportation | 2008-04-02 | 2008-05-16
Activity | 3PF1625W42A11.1T | (HRSG #32 Bypass Stack Silencer) Transportation | 2008-05-31 | 2008-07-15
Activity | 3CF1625W42A08.1 | (HRSG #32 Bypass Stack) Installation | 2008-05-31 | 2008-09-02
Activity | 3CF1625W42A12.1 | (HRSG #32 Bypass Stack Silencer) Installation | 2008-08-01 | 2008-08-30
5 | Main Stack |  | 2007-06-13 | 2009-04-22
Activity | 3PF1625W42A10.2P | (HRSG #32 Main Stack Silencer) P.O & Procurement | 2007-06-13 | 2008-05-30
Activity | 3EF1625W42A01.2 | (HRSG #32 Main Stack) Design | 2007-06-18 | 2007-12-28
Activity | 3PF1625W42A06.2P | (HRSG #32 Main Stack) P.O & Procurement | 2007-07-18 | 2008-05-16
Activity | 3EF1625W00A02.2 | (HRSG #32 Main Stack) GA & Load Data to Civil Design | 2007-08-06
Activity | 3EF1625W16A03.2 | (HRSG #32 Main Stack) FDN Design | 2007-11-08 | 2008-03-18
Activity | 3CF1625W16A04.2 | (HRSG #32 Main Stack) FDN Work | 2008-03-18 | 2008-06-19
Activity | 3PF1625W42A07.2T | (HRSG #32 Main Stack) Transportation | 2008-05-17 | 2008-07-01
Activity | 3PF1625W42A11.2T | (HRSG #32 Main Stack Silencer) Transportation | 2008-05-31 | 2008-07-15
Activity | 3CF1625W42A08.2 | (HRSG #32 Main Stack) Installation | 2009-01-14 | 2009-03-12
Activity | 3CF1625W42A12.2 | (HRSG #32 Main Stack Silencer) Installation | 2009-03-25 | 2009-04-22
5 | Piping Work |  | 2008-01-09 | 2009-04-18
Activity | 3PF1650W52A02.1P | (HRSG #32 Insulation) P.O & Procurement | 2008-01-09 | 2008-12-01
Activity | 3CF1640W58A05.1 | (HRSG #32) Piping Work | 2008-12-01 | 2009-02-19
Activity | 3PF1650W52A03.1T | (HRSG #32 Insulation) Transportation | 2008-12-02 | 2009-01-15
Activity | 3CF1640W62A06.1 | (HRSG #32) Hydro Test | 2009-03-02 | 2009-03-25
Activity | 3CF1650W52A04.1 | (HRSG #32 Insulation) Installation | 2009-03-16 | 2009-04-18
Activity | 3CF1640W60A07.1 | (HRSG #32) Acid Cleaning | 2009-03-26 | 2009-04-17
5 | CEMS |  | 2007-08-29 | 2008-09-11
Activity | 3PF1660W86A04.1P | (CEMS) P.O & Procurement | 2007-08-29 | 2008-06-30
Activity | 3EF1660W16A01.1 | (CEMS) FDN Design | 2007-10-30 | 2008-01-25
Activity | 3CF1660W16A02.1 | (CEMS) FDN Work | 2008-01-26 | 2008-03-24
Activity | 3PF1660W86A05.1T | (CEMS) Transportation | 2008-07-01 | 2008-08-14
Activity | 3CF1660W86A06.1 | (CEMS) Installation(incl. Elec, I&C) | 2008-08-15 | 2008-08-30
Activity | 3CF1660W86A07.1 | (CEMS) Loop Test | 2008-09-01 | 2008-09-05
Activity | 3SF1660W62A08.1 | (HRSG #32) CEMS Function Test for GT #11(Bypass stack) | 2008-09-06 | 2008-09-11
5 | Auxiliary System |  | 2007-09-10 | 2009-04-01
Activity | 3PF1665W42A12.1P | (HRSG #32 MECH Vendor Equip) P.O & Procurement | 2007-09-10 | 2008-10-02
Activity | 3PF1655W86A07.1P | (HRSG #32 I&C Vendor Equip) P.O & Procurement | 2007-10-02 | 2008-10-03
Activity | 3PF1655W70A02.1P | (HRSG #32 ELEC Vendor Equip) P.O & Procurement | 2007-10-02 | 2008-10-03
Activity | 3PF1665W42A13.1T | (HRSG #32 MECH Vendor Equip) Transportation | 2008-10-03 | 2008-11-17
Activity | 3PF1655W86A08.1T | (HRSG #32 I&C Vendor Equip) Transportation | 2008-10-04 | 2008-11-18
Activity | 3PF1655W70A03.1T | (HRSG #32 ELEC Vendor Equip) Transportation | 2008-10-04 | 2008-11-18
Activity | 3CF1665W42A14.1 | (HRSG #32 MECH Vendor Equip) Installation | 2008-11-18 | 2009-03-02
Activity | 3CF1655W86A09.1 | (HRSG #32 I&C Vendor Equip) Installation | 2008-11-19 | 2009-03-13
Activity | 3CF1655W70A04.1 | (HRSG #32 ELEC Vendor Equip) Installation | 2008-11-19 | 2009-03-13
Activity | 3CF1655W74A05.1 | (HRSG #32) Installation & Test - Elec. | 2008-12-30 | 2009-04-01
Activity | 3CF1660W90A10.1 | (HRSG #32) Installation & Test - I&C | 2008-12-30 | 2009-04-01
5 | Commissioning |  | 2009-04-23 | 2009-05-27
Activity | 3SF1600W62A01.1 | (HRSG #32)Cold Commissioning for HRSG #32 | 2009-04-23 | 2009-05-12
Activity | 3SF1600W62A02.1 | (HRSG #32) Function Test for HRSG #32 | 2009-05-13 | 2009-05-27
3 | Steam Turbine & Generator #30 |  | 2007-03-01 | 2009-05-30
4 | STG Building |  | 2007-03-01 | 2009-02-11
Activity | 3EF2010W00A01 | (STG #30 BLDG) GA & Load Data to Civil Design | 2007-03-01
Activity | 3EF2010W20A02 | (STG #30 BLDG) Buliding Design | 2007-03-01 | 2007-09-18
Activity | 3PF2010W20A04P | (STG #30 BLDG) P.O & Procurement - Structure Work(S/S) | 2007-09-19 | 2008-01-31
Activity | 3CF2010W16A03 | (STG #30 BLDG) FDN Work | 2007-12-15 | 2008-04-15
Activity | 3PF2010W20A05T | (STG #30 BLDG) Transportation - Structure Work(S/S) | 2008-02-01 | 2008-03-16
Activity | 3CF2010W20A06 | (STG #30 BLDG) Structure Work(S/S) | 2008-04-16 | 2008-08-15
Activity | 3CF2010W20A07 | (STG #30 BLDG) Cladding Work | 2008-06-25 | 2008-11-11
Activity | 3CF2010W20A08 | (STG #30 BLDG) Roof Work | 2008-09-04 | 2008-12-05
Activity | 3CF2010W38A09 | (STG #30 BLDG) Installation & Test - Fire Fighting Sys. | 2008-11-01 | 2008-12-27
Activity | 3CF2010W90A12 | (STG #30 BLDG) Installation & Test - I&C | 2008-11-12 | 2009-02-11
Activity | 3CF2010W36A10 | (STG #30 BLDG) Installation & Test - HVAC | 2008-11-12 | 2009-01-07
Activity | 3CF2010W74A11 | (STG #30 BLDG) Installation & Test - Elec | 2008-11-12 | 2009-02-11
4 | STG Unit Step-up Transformer |  | 2007-06-29 | 2008-11-18
Activity | 3PF6500W70A07P | (STG #30 & UST Shelter) P.O & Procurement - Main TR | 2007-06-29 | 2008-08-05
Activity | 3EF6500W00A01 | (STG #30 & UST Shelter) GA & Load Data to Civil Design | 2007-11-28
Activity | 3EF6500W16A02 | (STG #30 & UST Shelter) FDN & Firewall Design | 2007-11-28 | 2008-03-10
Activity | 3EF6500W32A04 | (STG #30 & UST Shelter) Structure Design | 2007-11-28 | 2008-03-10
Activity | 3CF6500W16A03 | (STG #30 & UST Shelter) FDN Work | 2008-03-11 | 2008-06-09
Activity | 3CF6500W16A05 | (STG #30 & UST Shelter) Firewall Work | 2008-06-10 | 2008-08-09
Activity | 3PF6500W70A08T | (STG #30 & UST Shelter) Transportation - Main TR | 2008-08-06 | 2008-09-19
Activity | 3CF6500W70A09 | (STG #30 & UST Shelter) Installation - Main TR | 2008-09-20 | 2008-11-18
4 | Steam Turbine |  | 2007-03-01 | 2009-05-18
Activity | 3EF2020W00A01 | (ST #30) ST Process Data | 2007-03-01 | 2007-03-30
Activity | 3EF2020W00A02 | (ST #30) ST Aux' Steam Consumption Data | 2007-03-01 | 2007-03-29
Activity | 3EF2020W00A03 | (ST #30) Instrument, Service Air Data | 2007-03-01 | 2007-03-29
Activity | 3EF2020W00A04 | (ST #30) Utility Consumption Data | 2007-03-01 | 2007-04-26
Activity | 3EF2020W00A05 | (ST #30) Emergency Load Data | 2007-03-01 | 2007-04-16
Activity | 3PF2020W42A10P | (ST #30) P.O & Procurement | 2007-03-01 | 2008-10-31
Activity | 3EF2020W16A06 | (ST #30) FDN Design | 2007-07-03 | 2007-11-01
Activity | 3CF2020W16A07 | (ST #30) FDN Work | 2007-12-15 | 2008-04-15
Activity | 3CF2020W16A08 | (ST #30) Pedestal & Top Slab Work | 2008-04-16 | 2008-10-11
Activity | 3PF2020W42A11T | (ST #30) Transportation | 2008-11-01 | 2008-12-15
Activity | 3CF2020W42A12 | (ST #30) Installation | 2008-12-16 | 2009-05-18
4 | ST Generator |  | 2007-03-01 | 2009-04-18
Activity | 3PF2040W42A02P | (STG #30) P.O & Procurement | 2007-03-01 | 2008-10-31
Activity | 3PF2040W42A03T | (STG #30) Transportation | 2008-11-01 | 2008-12-15
Activity | 3CF2040W42A04 | (STG #30) Installation | 2008-12-16 | 2009-04-18
4 | STG Auxiliary Equipment |  | 2007-04-30 | 2009-03-11
Activity | 3PF2070W42A04P | (STG #30 Aux. Equip) P.O & Procurement | 2007-04-30 | 2008-10-01
Activity | 3EF2070W16A01 | (STG #30 Aux. Equip) FDN Design | 2007-12-24 | 2008-05-21
Activity | 3CF2070W16A02 | (STG #30 Aux. Equip) FDN Work | 2008-05-22 | 2008-08-16
Activity | 3PF2070W42A05T | (STG #30 Aux. Equip) Transportation | 2008-10-02 | 2008-11-15
Activity | 3CF2070W42A06 | (STG #30 Aux. Equip) Installation | 2008-11-17 | 2009-03-11
4 | Piping & Etc. |  | 2008-08-16 | 2009-04-07
Activity | 3CF2035W58A01 | (ST #30) Piping Work | 2008-08-16 | 2009-01-16
Activity | 3CF2060W74A03 | (ST #30) Installation & Test - Elec. | 2009-01-16 | 2009-04-07
Activity | 3CF2065W90A04 | (ST #30) Installation & Test - I&C | 2009-01-16 | 2009-04-07
Activity | 3CF2035W62A02 | (ST #30) Hydro Test | 2009-01-17 | 2009-02-17
4 | Lube Oil System |  | 2007-07-31 | 2009-04-28
Activity | 3PF2030W42A04P | (Lube Oil Sys.) P.O & Procurement | 2007-07-31 | 2008-09-30
Activity | 3EF2030W16A01 | (Lube Oil Sys.) FDN Design | 2007-10-23 | 2008-01-22
Activity | 3CF2030W16A02 | (Lube Oil Sys.) FDN Work | 2008-01-23 | 2008-05-23
Activity | 3PF2030W42A05T | (Lube Oil Sys.) Transportation | 2008-10-01 | 2008-11-14
Activity | 3CF2030W42A06 | (Lube Oil Sys.) Equipment Installation | 2008-11-15 | 2008-12-30
Activity | 3CF2030W58A07 | (Lube Oil Sys.) Pipe Installation | 2008-12-31 | 2009-03-18
Activity | 3CF2030W62A08 | (Lube Oil Sys.) Lube oil flushing | 2009-03-19 | 2009-04-16
Activity | 3CF2030W58A09 | (Lube Oil Sys.) Remove Temp. Pipe | 2009-04-17 | 2009-04-28
4 | Test & Commissioning |  | 2009-04-29 | 2009-05-30
Activity | 3SF2000W62A02 | (ST #30) Pre-Commissioning | 2009-04-29 | 2009-05-28
Activity | 3SF2000W62A01 | (ST #30) Aux. Equipment Function Test | 2009-05-09 | 2009-05-28
Activity | 3SF2000W62A03 | (ST #30) Turnning Gear Operation | 2009-05-29 | 2009-05-30
3 | Block #3 Commisssioning |  | 2009-05-31 | 2009-11-02
Activity | 3SF9035W62A01 | (Comm'g) Steam Blowing | 2009-05-31 | 2009-06-19
Activity | 3CF9035W62A02 | (Comm'g) Temporary Piping Restoration | 2009-06-20 | 2009-06-29
Activity | 3SF9035W62A03 | (Comm'g) Bypass Operation | 2009-06-30 | 2009-07-06
Activity | 3SF9035W62A04 | (Comm'g) Safety & Interlock Test | 2009-07-02 | 2009-07-06
Activity | 3SF9035W62A05 | (Comm'g) Steam Admission | 2009-07-07 | 2009-07-08
Activity | 3SF9040W62A06 | (Comm'g) TBN & GEN. Test | 2009-07-09 | 2009-07-21
Activity | 3SF9040W62A07 | (Comm'g) Synchronization Test | 2009-07-22 | 2009-07-22
Activity | 3SF9040W62A08 | (Comm'g) Optimaization Test | 2009-07-23 | 2009-08-09
Activity | 3SF9040W62A09 | (Comm'g) Fuel Change-Over(Gas to Oil) and Optimaization | 2009-08-10 | 2009-08-10
Activity | 3SF9040W62A10 | (Comm'g) Outage Period | 2009-08-10 | 2009-08-16
Activity | 3SF9040W62A11 | (Comm'g) APS & Stability Guarantee Test | 2009-08-17 | 2009-09-19
Activity | 3SF9040W62A12 | (Comm'g) Trial Run Test | 2009-09-20 | 2009-09-21
Activity | 3SF9041W62A14 | (Comm'g) Reliability Test | 2009-09-22 | 2009-10-21
Activity | 3SF9040W62A13 | (Comm'g) Initial Operation Test | 2009-09-22 | 2009-09-22
Activity | 3SF9042W62A15 | (Comm'g) Performance Test (Fuel Gas & Fuel Oil) | 2009-10-22 | 2009-11-02