## Generated Schedule
source_file | document_no | title | deliverable | equipment | system | building | itb_sources | rule_query | matched_rule | submission_type | matched_activity_id | matched_activity_name | matched_activity_wbs_path | matched_activity_start_date | matched_activity_finish_date | fa_earliest | fa_recommended | fa_latest | fc_earliest | fc_recommended | fc_latest | date_range_status | date_range_confidence | ntp_shift_days
Fadhili_MDL.xlsx | T16182-DA01-P0ZEN-020001 | DOCUMENT IDENTIFICATION | [7 empty] | FA | 0EF1000W00A10 | Instrument Installation Detail | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-05-11 | 2007-09-28 |  |  |  | 2024-03-01 | 2024-03-12 | 2024-04-11 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-DA01-P0ZEN-020002 | EQUIPMENT AND SYSTEM IDENTIFICATION | [7 empty] | FA | 0CF5560W42A24 | (M&E WORKSHOP EQUIP) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-10-29 | 2008-12-27 |  |  |  | 2025-08-01 | 2025-08-31 | 2025-09-30 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-VA08-P0ZEN-020003 | CONTRACTORS ADMIN PLAN | PLAN |  |  |  |  | Plan |  | FA | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DP00-P0ZEN-020004 | PAINTING SPECIFICATION | SPECIFICATION |  |  |  |  | Technical Specification |  | FA | 0PF6020W58A11P | (Piping Insulation) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-10-01 | 2008-04-30 | 2024-10-15 | 2024-11-14 | 2024-12-14 | 2024-12-29 | 2025-01-13 | 2025-01-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DP00-P0ZEN-020005 | PACKING SPECIFICATION | SPECIFICATION |  |  |  |  | Technical Specification |  | FA | 0PF6020W58A11P | (Piping Insulation) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-10-01 | 2008-04-30 | 2024-10-15 | 2024-11-14 | 2024-12-14 | 2024-12-29 | 2025-01-13 | 2025-01-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DP00-P0ZEN-020006 | NAME AND TAG PLATE | [7 empty] | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-DP00-P0ZEN-020007 | ABBREVIATION LIST | LIST |  |  |  |  | LIST |  | FA | 0PF3040W42A04P | (Lab) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Laboratory | 2008-03-31 | 2008-10-20 | 2025-04-29 | 2025-05-29 | 2025-06-28 | 2025-07-13 | 2025-07-28 | 2025-08-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0ZEN-020008 | LABELING LAYOUT FOR WATER STORAGE TANKS | LAYOUT | TANKS |  |  |  | Layout Drawing for TANKS | Substation | SKIP | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P0ZEN-020009 | TYPICAL DANGER SIGN DRAWING | DRAWING |  |  |  |  | DRAWING |  | FA | 0PF6500W70A02.6P | (Electrical Protection Panel) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2007-08-30 | 2008-03-10 | 2024-10-11 | 2024-11-10 | 2024-12-10 | 2024-12-25 | 2025-01-09 | 2025-01-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA07-P0ZEN-020010 | UNDERGROUND PIPE MARKER DETAIL | DETAIL |  | PIPE |  |  | Detail Drawing for PIPE |  | FI | 1PF5550W46A08P | (PipeRack) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-06-28 | 2008-01-02 | 2024-08-23 | 2024-09-22 | 2024-10-22 | 2024-11-06 | 2024-11-21 | 2024-12-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-BV02-P0ZEN-020020 | MAINTAINABILITY STUDY | STUDY |  |  |  |  | STUDY |  | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-BV02-P0ZEN-020030 | CORROSION AND MATERIAL STUDY | STUDY |  |  |  |  | STUDY |  | FA | 0EF6040W80A01 | (Earthing & Lightning Material) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials |  | 2007-05-30 | [6 empty] | missing_date |  | 6210
Fadhili_MDL.xlsx | T16182-BV02-P0ZEN-020040 | FIRE STUDY | STUDY |  |  |  |  | STUDY |  | FA | 0CF4500W24A10 | (Fire Fighting BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2008-05-21 | 2008-07-11 |  |  |  | 2025-02-21 | 2025-03-23 | 2025-04-22 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-BV02-P0ZEN-050001 | BUILDING RISK ASSESSMENT |  |  |  | BUILDING |  | for BUILDING |  | FA | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 | 2026-10-10 | 2026-11-09 | 2026-12-09 | 2026-12-24 | 2027-01-08 | 2027-01-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UC07-P0ZEN-100001 | SITE PLAN | PLAN |  |  |  |  | Plan |  | FA | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UC07-P0ZEN-100002 | OVERALL PLOT PLAN WITH ESF AREA | PLAN |  |  |  |  | Plan |  | FA | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UC07-P0ZEN-100003 | OVERALL PLOT PLAN | PLAN |  |  |  |  | Plan |  | FA | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0MB-100004 | PLANT GENERAL ARRANGEMENT FOR GTG & HRSG AREA UNIT 1&2 (PLAN VIEW) | General Arrangement | Gas Turbine Generator & Heat Recovery Steam Generator |  |  |  | General Arrangement Drawing for Gas Turbine Generator & Heat Recovery Steam Generator |  | FA | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0MB-100005 | PLANT GENERAL ARRANGEMENT FOR GTG & HRSG AREA UNIT 3&4&5 (PLAN VIEW) | General Arrangement | Gas Turbine Generator & Heat Recovery Steam Generator |  |  |  | General Arrangement Drawing for Gas Turbine Generator & Heat Recovery Steam Generator |  | FA | 3EF1600W00A02 | (HRSG #31/#32) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0MB-100006 | PLANT GENERAL ARRANGEMENT FOR GTG & HRSG AREA (SECTION A - A) | General Arrangement | Gas Turbine Generator & Heat Recovery Steam Generator |  |  |  | General Arrangement Drawing for Gas Turbine Generator & Heat Recovery Steam Generator |  | FA | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0MB-100007 | PLANT GENERAL ARRANGEMENT FOR GTG & HRSG AREA (SECTION B - B) | GENERAL ARRANGEMENT | Gas Turbine Generator & Heat Recovery Steam Generator |  |  |  | General Arrangement Drawing for Gas Turbine Generator & Heat Recovery Steam Generator |  | FA | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0UMA-100008 | PLANT GENERAL ARRANGEMENT FOR STG AREA (PLAN VIEW) | GENERAL ARRANGEMENT | Steam Turbine & Generator |  |  |  | General Arrangement Drawing for STG |  | FA | 0EF1000W00A03 | Plant General Arrangement | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-10-08 | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0UMA-100009 | PLANT GENERAL ARRANGEMENT FOR STG AREA (SECTION A - A) | GENERAL ARRANGEMENT | Steam Turbine & Generator |  |  |  | General Arrangement Drawing for STG |  | FA | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0UMA-100010 | PLANT GENERAL ARRANGEMENT FOR STG AREA (SECTION B - B) | GENERAL ARRANGEMENT | Steam Turbine & Generator |  |  |  | General Arrangement Drawing for STG |  | FA | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG05-P0ZEN-110001 | HEAT BALANCE DIAGRAMS | DIAGRAMS |  |  |  |  | DIAGRAMS |  | FA | 1PF1650W52A02P | (HRSG #11 Insulation) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Piping Work | 2008-01-09 | 2008-09-30 | 2025-07-22 | 2025-08-21 | 2025-09-20 | 2025-10-05 | 2025-10-20 | 2025-11-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0ZEN-110002 | P&I DIAGRAM FOR SYMBOL AND LEGEND | P&I DIAGRAM |  |  |  |  | P&ID |  | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LBA-110003 | P&I DIAGRAM FOR HP STEAM SYSTEM | P&I DIAGRAM |  | HP STEAM SYSTEM |  |  | P&ID for HP STEAM SYSTEM | Water Treatment System | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LBC-110004 | P&I DIAGRAM FOR IP STEAM SYSTEM | P&I DIAGRAM |  | IP STEAM SYSTEM |  |  | P&ID for IP STEAM SYSTEM | Water Treatment System | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LBG-110005 | P&I DIAGRAM FOR LP STEAM SYSTEM | P&I DIAGRAM |  | LP STEAM SYSTEM |  |  | P&ID for LP STEAM SYSTEM | Water Treatment System | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LBS-110006 | P&I DIAGRAM FOR PROCESS STEAM SYSTEM | P&I DIAGRAM |  | PROCESS STEAM SYSTEM |  |  | P&ID for PROCESS STEAM SYSTEM | Water Treatment System | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P6LCM-110007 | P&I DIAGRAM FOR STEAM DRAIN SYSTEM | P&I DIAGRAM |  | STEAM DRAIN SYSTEM |  |  | P&ID for STEAM DRAIN SYSTEM | Sampling System | FA | 1EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | 2007-03-15 | 2008-01-15 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P6LCA-110008 | P&I DIAGRAM FOR CONDENSATE SYSTEM | P&I DIAGRAM |  | CONDENSATE SYSTEM |  |  | P&ID for CONDENSATE SYSTEM | Water Treatment System | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LAA-110009 | P&I DIAGRAM FOR FEEDWATER SYSTEM | P&I DIAGRAM |  | FEEDWATER SYSTEM |  |  | P&ID for FEEDWATER SYSTEM | Water Treatment System | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0PGB-110010 | P&I DIAGRAM FOR CLOSED COOLING WATER SYSTEM | P&I DIAGRAM |  | CLOSED COOLING WATER SYSTEM |  |  | P&ID for CLOSED COOLING WATER SYSTEM | Water Treatment System | FA | 1PF3030W42A14P | (CCW H/EX) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-09-03 | 2008-07-16 | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0GHC-110011 | P&I DIAGRAM FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | P&I DIAGRAM |  | DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM |  |  | P&ID for DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | Water Treatment System | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0QJA-110012 | P&I DIAGRAM FOR NITROGEN GAS SYSTEM | P&I DIAGRAM |  | NITROGEN GAS SYSTEM |  |  | P&ID for NITROGEN GAS SYSTEM | Water Treatment System | FA | 1EF3515W00A01 | (N2 Gas System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-04-02 | 2007-08-27 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P1MBH-110013 | GTG - P&I DIAGRAM FOR GT ROTOR COOLING AIR COOLER SYSTEM | P&I DIAGRAM | Gas Turbine Generator |  |  |  | P&ID for GTG |  | FA | 1PF1265W42A13P | (TCA Cooler) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Gas Supply System | 2007-03-01 | 2008-02-29 | 2024-08-12 | 2024-09-11 | 2024-10-11 | 2024-10-26 | 2024-11-10 | 2024-11-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P1EKC-110014 | P&I DIAGRAM FOR GT PERFORMANCE HEATER SYSTEM | P&I DIAGRAM |  | GT PERFORMANCE HEATER SYSTEM |  |  | P&ID for GT PERFORMANCE HEATER SYSTEM |  | FA | 1PF3520W42A07.2P | (Gas HTR) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Heater | 2007-07-03 | 2008-04-01 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0LA-110031 | PROCESS FLOW DIAGRAM FOR STEAM/CONDENSATE/FW SYSTEM | PROCESS FLOW DIAGRAM |  |  |  |  | PROCESS FLOW DIAGRAM | FireFighting | FA | 1PF3015W58A14P | (FW PIPING) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-11-02 | 2008-06-30 | 2024-11-16 | 2024-12-21 | 2025-01-25 | 2025-01-11 | 2025-02-15 | 2025-03-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0PG-110032 | PROCESS FLOW DIAGRAM FOR CCW SYSTEM | PROCESS FLOW DIAGRAM |  |  |  |  | PROCESS FLOW DIAGRAM | FireFighting | FA | 1PF3030W42A14P | (CCW H/EX) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-09-03 | 2008-07-16 | 2024-09-17 | 2024-10-22 | 2024-11-26 | 2024-11-12 | 2024-12-17 | 2025-01-21 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0GHC-110033 | PROCESS FLOW DIAGRAM FOR DM WATER SYSTEM | PROCESS FLOW DIAGRAM |  | DM WATER SYSTEM |  |  | PROCESS FLOW DIAGRAM for DM WATER SYSTEM | Water Treatment System | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0LB-110035 | DESIGN CRITERIA FOR STEAM AND BYPASS SYSTEM | DESIGN CRITERIA |  | STEAM AND BYPASS SYSTEM |  |  | DESIGN CRITERIA for STEAM AND BYPASS SYSTEM | Intake Screening System | FA | 1EF2510W00A01.1 | (Bypass System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Bypass System | 2007-04-02 | 2007-11-01 | 2024-04-16 | 2024-05-16 | 2024-06-15 | 2024-06-30 | 2024-07-15 | 2024-07-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0LC-110036 | DESIGN CRITERIA FOR CONDENSATE SYSTEM | DESIGN CRITERIA |  | CONDENSATE SYSTEM |  |  | DESIGN CRITERIA for CONDENSATE SYSTEM | Water Treatment System | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0LA-110037 | DESIGN CRITERIA FOR FEEDWATER SYSTEM | DESIGN CRITERIA |  | FEEDWATER SYSTEM |  |  | DESIGN CRITERIA for FEEDWATER SYSTEM | Water Treatment System | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0PGB-110038 | DESIGN CRITERIA FOR CLOSED COOLING WATER SYSTEM | DESIGN CRITERIA |  | CLOSED COOLING WATER SYSTEM |  |  | DESIGN CRITERIA for CLOSED COOLING WATER SYSTEM | Water Treatment System | FA | 1EF3030W16A17 | (CCWP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-09-03 | 2008-01-30 | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0GHC-110039 | DESIGN CRITERIA FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | DESIGN CRITERIA |  | DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM |  |  | DESIGN CRITERIA for DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | Water Treatment System | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | 2024-11-01 | 2024-12-01 | 2024-12-31 | 2025-01-15 | 2025-01-30 | 2025-02-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0LB-110040 | SYSTEM DESCRIPTION FOR STEAM AND BYPASS SYSTEM | SYSTEM DESCRIPTION |  | STEAM AND BYPASS SYSTEM |  |  | System Description for STEAM AND BYPASS SYSTEM | Sampling System | FA | 1EF2510W00A01.1 | (Bypass System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Bypass System | 2007-04-02 | 2007-11-01 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0LC-110041 | SYSTEM DESCRIPTION FOR CONDENSATE SYSTEM | SYSTEM DESCRIPTION |  | CONDENSATE SYSTEM |  |  | System Description for CONDENSATE SYSTEM |  | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | 2024-07-14 | 2024-08-13 | 2024-09-12 | 2024-09-27 | 2024-10-12 | 2024-10-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0LA-110042 | SYSTEM DESCRIPTION FOR FEEDWATER SYSTEM | SYSTEM DESCRIPTION |  | FEEDWATER SYSTEM |  |  | System Description for FEEDWATER SYSTEM | Water Treatment System | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0PGB-110043 | SYSTEM DESCRIPTION FOR CLOSED COOLING WATER SYSTEM | SYSTEM DESCRIPTION |  | CLOSED COOLING WATER SYSTEM |  |  | System Description for CLOSED COOLING WATER SYSTEM | Water Treatment System | FA | 1SF3030W62A26 | (CCWS) Pump Operation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2008-10-29 | 2008-10-31 | 2025-11-29 | 2025-12-29 | 2026-01-28 | 2026-02-12 | 2026-02-27 | 2026-03-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0GHC-110044 | SYSTEM DESCRIPTION FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | SYSTEM DESCRIPTION |  | DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM |  |  | System Description for DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | Water Treatment System | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | 2024-11-01 | 2024-12-01 | 2024-12-31 | 2025-01-15 | 2025-01-30 | 2025-02-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0LB-110045 | PRESSURE LOSS CALCULATIONS FOR MAIN STEAM SYSTEM | CALCULATIONS |  | MAIN STEAM SYSTEM |  |  | CALCULATIONS for MAIN STEAM SYSTEM | Sampling System | FI | 1PF1625W42A06.0P | (HRSG #11 Main Stack) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | 2007-06-04 | 2008-01-31 | 2024-07-04 | 2024-08-03 | 2024-09-02 | 2024-09-17 | 2024-10-02 | 2024-10-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0LC-110046 | SIZING CALCULATION FOR CONDENSATE EXTRACTION PUMP | SIZING CALCULATION | Condensate Extraction Pump |  |  |  | Calculation sheet for CEP |  | FA | 1CF3020W42A06 | (CEP) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2008-09-23 | 2008-12-11 |  |  |  | 2025-06-26 | 2025-07-26 | 2025-08-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0LC-110047 | SIZING CALCULATION FOR FGP CONDENSATE PUMP | SIZING CALCULATION | Fuel Gas Package CONDENSATE PUMP |  |  |  | Calculation sheet for Fuel Gas Package CONDENSATE PUMP | Fuel Gas System | FA | 0PF3520W42A08P | (Condensate Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-10-19 | 2024-11-16 | 2024-12-14 | 2024-12-07 | 2025-01-04 | 2025-02-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0LA-110048 | SIZING CALCULATION FOR HRSG FEEDWATER PUMP | SIZING CALCULATION | Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | Calculation sheet for Heat Recovery Steam Generator FEEDWATER PUMP |  | FA | 1PF1610W42A02P | (HRSG #11 Module) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Module | 2007-07-03 | 2008-03-03 | 2024-12-14 | 2025-01-13 | 2025-02-12 | 2025-02-27 | 2025-03-14 | 2025-03-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0LA-110049 | SIZING CALCULATION FOR FGP FEEDWATER PUMP | SIZING CALCULATION | Fuel Gas Package FEEDWATER PUMP |  |  |  | Calculation sheet for Fuel Gas Package FEEDWATER PUMP | Fuel Gas System | FA | 0PF3520W42A08P | (Condensate Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-10-19 | 2024-11-16 | 2024-12-14 | 2024-12-07 | 2025-01-04 | 2025-02-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0PGB-110050 | SIZING CALCULATION FOR CLOSED COOLING WATER SYSTEM | SIZING CALCULATION |  | CLOSED COOLING WATER SYSTEM |  |  | Calculation sheet for CLOSED COOLING WATER SYSTEM | Water Treatment System | FA | 1PF3030W42A14P | (CCW H/EX) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-09-03 | 2008-07-16 | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0GHC-110051 | SIZING CALCULATION FOR CYCLE MAKEUP WATER PUMP AND DM WATER SUPPLY PUMP | SIZING CALCULATION | CYCLE MAKEUP WATER PUMP AND DM WATER SUPPLY PUMP |  |  |  | Calculation sheet for CYCLE MAKEUP WATER PUMP AND DM WATER SUPPLY PUMP | Water Treatment System | FA | 0PF3010W42A04P | (Make-up WTR Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System > Make-up Water Pump | 2007-08-02 | 2008-04-02 | 2024-09-01 | 2024-10-01 | 2024-10-31 | 2024-11-15 | 2024-11-30 | 2024-12-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0QJA-110052 | SIZING CALCULATION FOR NITROGEN GAS SYSTEM | SIZING CALCULATION |  | NITROGEN GAS SYSTEM |  |  | Calculation sheet for NITROGEN GAS SYSTEM | Fuel Gas System | FA | 1PF3515W42A04P | (N2 Gas Equip) P.O & Procurement for FGSS(Local PROC.) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-11-01 | 2008-05-30 | 2025-03-21 | 2025-04-18 | 2025-05-16 | 2025-05-09 | 2025-06-06 | 2025-07-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0MJ-110053 | BSEDG - CALCULATION | CALCULATION | BSEDG |  |  |  | Calculation sheet for BSEDG | FloW element | FA | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | 2024-08-15 | 2024-09-14 | 2024-10-14 | 2024-10-29 | 2024-11-13 | 2024-11-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0LA-110061 | HRSG/FGP FEEDWATER PUMP NPSH TRANSIENT ANALYSIS | ANALYSIS | HRSG/FGP FEEDWATER PUMP |  |  |  | ANALYSIS for HRSG/FGP FEEDWATER PUMP |  | FA | 0PF3520W42A08P | (Condensate Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-11-12 | 2024-12-12 | 2025-01-11 | 2025-01-26 | 2025-02-10 | 2025-02-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LF-110101 | DATA SHEET FOR SAFETY RELIEF VALVE AND RUPTURE DISC FOR BOP SYSTEMS | DATA SHEET | SAFETY RELIEF VALVE AND RUPTURE DISC | BOP SYSTEMS |  |  | Data Sheet for SAFETY RELIEF VALVE AND RUPTURE DISC | BYPASS VALVE & PRDS | FA | 0EF6050W00A01.1 | (Safety Valve) Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-04-30 | 2007-07-13 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0LF-110102 | OUTLINE DRAWING FOR SAFETY RELIEF VALVE AND RUPTURE DISC FOR BOP SYSTEMS | OUTLINE DRAWING | SAFETY RELIEF VALVE AND RUPTURE DISC | BOP SYSTEMS |  |  | Outline Drawing for SAFETY RELIEF VALVE AND RUPTURE DISC |  | FA | 0PF6050W86A03.1P | (Safety Valve) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-09-14 | 2008-05-23 | 2025-05-21 | 2025-06-20 | 2025-07-20 | 2025-08-04 | 2025-08-19 | 2025-09-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MAN-110153 | DATA SHEET FOR BYPASS AND PRDS | DATA SHEET | BYPASS AND PRDS |  |  |  | Data Sheet for BYPASS AND PRDS | BYPASS VALVE & PRDS | FA | 1EF2510W00A02.1 | (Bypass System) Bypass Valve, PRDS key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Bypass System | 2007-03-21 | 2007-05-17 | 2024-04-18 | 2024-05-18 | 2024-06-17 | 2024-07-02 | 2024-07-17 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0MAN-110154 | OUTLINE DRAWING FOR BYPASS AND PRDS | OUTLINE DRAWING | BYPASS AND PRDS |  |  |  | Outline Drawing for BYPASS AND PRDS | BYPASS VALVE & PRDS | FA | 1EF2510W00A02.1 | (Bypass System) Bypass Valve, PRDS key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Bypass System | 2007-03-21 | 2007-05-17 | 2024-04-18 | 2024-05-18 | 2024-06-17 | 2024-07-02 | 2024-07-17 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YR01-P0ZEN-110201 | STEAM BLOWING - OUT PROCEDURE | PROCEDURE |  |  |  |  | PROCEDURE |  | FA | 1SF9035W62A01 | (Comm'g) Steam Blowing | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | 2009-03-31 | 2009-04-19 | 2027-03-31 | 2027-04-21 | 2027-05-12 | 2027-06-05 | 2027-06-20 | 2027-07-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LBG-110251 | DATA SHEET FOR SILENCER | DATA SHEET | SILENCER |  |  |  | Data Sheet for SILENCER | Silencer | FA | 1EF2510W00A02 | (Steam System) Silencer Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-03-30 | 2007-07-13 | 2024-06-08 | 2024-07-08 | 2024-08-07 | 2024-08-22 | 2024-09-06 | 2024-09-21 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0LBG-110252 | OUTLINE DRAWING FOR SILENCER | OUTLINE DRAWING | SILENCER |  |  |  | Outline Drawing for SILENCER | Silencer | FA | 1PF2510W42A04P | (Silencer) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-10-15 | 2008-07-15 | 2025-02-04 | 2025-03-06 | 2025-04-05 | 2025-04-20 | 2025-05-05 | 2025-05-20 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCP-110301 | DATA SHEET FOR CONDENSATE PLATE TYPE HEAT EXCHANGER | DATA SHEET | CONDENSATE PLATE TYPE HEAT EXCHANGER |  |  |  | Data Sheet for CONDENSATE PLATE TYPE HEAT EXCHANGER | PLATE TYPE HEAT EXCHANGNER | FA | 1EF3020W00A15 | (COND) Condenser Design Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-03-01 | 2007-04-12 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LCP-110302 | OUTLINE DRAWING FOR CONDENSATE PLATE TYPE HEAT EXCHANGER | OUTLINE DRAWING | CONDENSATE PLATE TYPE HEAT EXCHANGER |  |  |  | Outline Drawing for CONDENSATE PLATE TYPE HEAT EXCHANGER | PLATE TYPE HEAT EXCHANGNER | FI | 1PF3020W42A20P | (COND) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-07-30 | 2025-02-06 | 2025-03-08 | 2025-04-07 | 2025-04-22 | 2025-05-07 | 2025-05-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0PGB-110401 | GENERAL ARRANGEMENT DRAWING FOR CLOSED COOLING WATER PUMP | GENERAL ARRANGEMENT DRAWING | CLOSED COOLING WATER PUMP |  |  |  | GENERAL ARRANGEMENT DRAWING for CLOSED COOLING WATER PUMP |  | FA | 1PF1225W42A12P | (CCWP) P.O & Procurement for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | 2007-07-03 | 2008-03-31 | 2024-08-14 | 2024-09-13 | 2024-10-13 | 2024-10-28 | 2024-11-12 | 2024-11-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL22-P0PGB-110402 | NAMEPLATE DRAWING FOR CLOSED COOLING WATER PUMP | NAMEPLATE DRAWING | CLOSED COOLING WATER PUMP |  |  |  | NAMEPLATE DRAWING for CLOSED COOLING WATER PUMP |  | FA | 1PF3030W42A21P | (CCWP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-09-03 | 2008-07-02 | 2024-10-01 | 2024-10-31 | 2024-11-30 | 2024-12-15 | 2024-12-30 | 2025-01-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0PGB-110403 | DATA SHEET FOR CLOSED COOLING WATER PUMP | DATA SHEET | CLOSED COOLING WATER PUMP |  |  |  | Data Sheet for CLOSED COOLING WATER PUMP | FireFighting | FA | 1PF1225W42A12P | (CCWP) P.O & Procurement for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | 2007-07-03 | 2008-03-31 | 2024-10-09 | 2024-11-13 | 2024-12-18 | 2024-12-04 | 2025-01-08 | 2025-02-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0PGB-110404 | OUTLINE DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | OUTLINE DRAWING | CLOSED COOLING WATER PUMP MOTOR |  |  |  | Outline Drawing for CLOSED COOLING WATER PUMP MOTOR |  | FA | 3PF1225W42A12P | (CCWP) P.O & Procurement for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | 2007-07-03 | 2008-05-30 | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0PGB-110405 | MAIN TERMINAL BOX DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | DRAWING | CLOSED COOLING WATER PUMP MOTOR |  |  |  | DRAWING for CLOSED COOLING WATER PUMP MOTOR |  | FA | 1PF3030W42A21P | (CCWP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-09-03 | 2008-07-02 | 2024-10-01 | 2024-10-31 | 2024-11-30 | 2024-12-15 | 2024-12-30 | 2025-01-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL22-P0PGB-110406 | NAMEPLATE DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | NAMEPLATE DRAWING | CLOSED COOLING WATER PUMP MOTOR |  |  |  | NAMEPLATE DRAWING for CLOSED COOLING WATER PUMP MOTOR |  | FI | 1PF3030W42A21P | (CCWP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-09-03 | 2008-07-02 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0PGB-110407 | DATA SHEET FOR CLOSED COOLING WATER PUMP MOTOR | DATA SHEET | CLOSED COOLING WATER PUMP MOTOR |  |  |  | Data Sheet for CLOSED COOLING WATER PUMP MOTOR | Cooling ToWer | FA | 1PF1225W42A12P | (CCWP) P.O & Procurement for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | 2007-07-03 | 2008-03-31 | 2024-08-28 | 2024-09-27 | 2024-10-27 | 2024-11-11 | 2024-11-26 | 2024-12-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0QJA-110500 | SYSTEM DESCRIPTION FOR NITROGEN GAS SYSTEM | SYSTEM DESCRIPTION |  | NITROGEN GAS SYSTEM |  |  | System Description for NITROGEN GAS SYSTEM | N2 Gas System | FA | 1EF3515W00A01 | (N2 Gas System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-04-02 | 2007-08-27 | 2024-04-16 | 2024-05-16 | 2024-06-15 | 2024-06-30 | 2024-07-15 | 2024-07-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0QJA-110501 | EQUIPMENT ASSEMBLY AND DETAIL DRAWING FOR NITROGEN GAS SYSTEM | EQUIPMENT ASSEMBLY AND DETAIL DRAWING |  | NITROGEN GAS SYSTEM |  |  | EQUIPMENT ASSEMBLY AND DETAIL DRAWING for NITROGEN GAS SYSTEM | N2 Gas System | FA | 1PF3515W42A04P | (N2 Gas Equip) P.O & Procurement for FGSS(Local PROC.) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-11-01 | 2008-05-30 | 2025-03-21 | 2025-04-20 | 2025-05-20 | 2025-06-04 | 2025-06-19 | 2025-07-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0QJA-110502 | GENERAL ARRANGEMENT DRAWING FOR NITROGEN GAS SYSTEM | GENERAL ARRANGEMENT DRAWING |  | NITROGEN GAS SYSTEM |  |  | GENERAL ARRANGEMENT DRAWING for NITROGEN GAS SYSTEM | N2 Gas System | FA | 1EF3515W00A06 | (N2 Gas Station Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 |  | 2025-01-28 | 2025-02-27 | 2025-03-29 | 2025-04-13 | 2025-04-28 | 2025-05-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0QJA-110503 | DATA SHEET FOR NITROGEN GAS SYSTEM | DATA SHEET |  | NITROGEN GAS SYSTEM |  |  | Data Sheet for NITROGEN GAS SYSTEM | N2 Gas System | FA | 1EF3515W00A02 | (N2 Gas System) Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-04-27 | 2007-07-31 | 2024-09-14 | 2024-10-14 | 2024-11-13 | 2024-11-28 | 2024-12-13 | 2024-12-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MJ-110504 | BSEDG - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | Blackstart Diesel Generator |  |  |  | GENERAL ARRANGEMENT DRAWING for Blackstart Diesel Generator |  | FA | 0EF3530W00A13 | (BSDG BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2007-05-01 |  | 2024-06-12 | 2024-07-12 | 2024-08-11 | 2024-08-26 | 2024-09-10 | 2024-09-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0MJ-110505 | BSEDG - P&I DIAGRAM | P&I DIAGRAM | Blackstart Diesel Generator |  |  |  | P&ID for Blackstart Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | FA | 0PF3530W42A05P | (BSDG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2007-08-01 | 2008-05-30 | 2024-08-29 | 2024-09-28 | 2024-10-28 | 2024-11-12 | 2024-11-27 | 2024-12-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0MJ-110506 | BSEDG - OUTLINE DRAWING | OUTLINE DRAWING | Blackstart Diesel Generator |  |  |  | Outline Drawing for Blackstart Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | FA | 0PF3530W42A05P | (BSDG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2007-08-01 | 2008-05-30 | 2024-08-29 | 2024-09-28 | 2024-10-28 | 2024-11-12 | 2024-11-27 | 2024-12-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0MJ-110507 | BSEDG - SINGLE LINE DIAGRAM | SINGLE LINE DIAGRAM | Blackstart Diesel Generator |  |  |  | Single Line Diagram for Blackstart Diesel Generator |  | SKIP | 0PF3530W42A05P | (BSDG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2007-08-01 | 2008-05-30 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MJ-110508 | BSEDG - DATA SHEET | DATA SHEET | Blackstart Diesel Generator |  |  |  | Data Sheet for Blackstart Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | FA | 0EF3530W00A01 | (BSDG) Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2007-03-01 | 2007-04-30 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG01-P0MJ-110509 | BSEDG - PIPING ISOMETRIC DRAWING | PIPING ISOMETRIC DRAWING | Blackstart Diesel Generator | PIPING |  |  | PIPING ISOMETRIC DRAWING for Blackstart Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-05 | 2024-11-04 | 2024-12-04 | 2024-12-19 | 2025-01-03 | 2025-01-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0MJ-110510 | BSEDG - SYSTEM DESCRIPTION | SYSTEM DESCRIPTION | Blackstart Diesel Generator |  |  |  | System Description for Blackstart Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | FA | 0EF3530W16A02 | (BSDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2008-01-09 | 2008-04-09 | 2025-03-06 | 2025-04-05 | 2025-05-05 | 2025-05-20 | 2025-06-04 | 2025-06-19 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0MJ-110511 | BSEDG - CONTROL LOGIC DIAGRAM | CONTROL LOGIC DIAGRAM | Blackstart Diesel Generator | control system |  |  | CONTROL LOGIC DIAGRAM for Blackstart Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | FA | 0PF3530W42A05P | (BSDG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2007-08-01 | 2008-05-30 | 2024-12-19 | 2025-01-18 | 2025-02-17 | 2025-03-04 | 2025-03-19 | 2025-04-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0MJ-110512 | BSEDG - EMBEDDED CONDUIT LAYOUT | EMBEDDED CONDUIT LAYOUT | Blackstart Diesel Generator |  |  |  | EMBEDDED CONDUIT LAYOUT for Blackstart Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | FA | 0PF3530W42A05P | (BSDG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2007-08-01 | 2008-05-30 | 2024-08-29 | 2024-09-28 | 2024-10-28 | 2024-11-12 | 2024-11-27 | 2024-12-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YM02-P0MJ-110561 | BSEDG - CONTROL PANEL OUTLINE DRAWING | OUTLINE DRAWING | Blackstart Diesel Generator |  |  |  | Outline Drawing for Blackstart Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | FA | 0PF3530W42A05P | (BSDG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2007-08-01 | 2008-05-30 | 2024-08-29 | 2024-09-28 | 2024-10-28 | 2024-11-12 | 2024-11-27 | 2024-12-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG11-P0MJ-110564 | BSEDG - SCHEMATIC DIAGRAM | SCHEMATIC DIAGRAM | Blackstart Diesel Generator |  |  |  | SCHEMATIC DIAGRAM for Blackstart Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | FA | 0PF3530W42A05P | (BSDG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2007-08-01 | 2008-05-30 | 2024-10-10 | 2024-11-09 | 2024-12-09 | 2024-12-24 | 2025-01-08 | 2025-01-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0MJ-110568 | BSEDG - PROTECTION RELAY SETTING REPORT | REPORT | Blackstart Diesel Generator |  |  |  | REPORT for Blackstart Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | FA | 0PF3530W42A05P | (BSDG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2007-08-01 | 2008-05-30 | 2024-08-29 | 2024-09-28 | 2024-10-28 | 2024-11-12 | 2024-11-27 | 2024-12-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YM02-P0MJ-110578 | BSEDG – MV SWGR DRAWING | DRAWING | Blackstart Diesel Generator |  |  |  | DRAWING for Blackstart Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | FA | 0PF3530W42A05P | (BSDG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2007-08-01 | 2008-05-30 | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LF-110601 | VALVE LIST & DATA SHEET FOR MOV (G&G) | LIST & DATA SHEET | MOV (G&G) |  |  |  | LIST & DATA SHEET for MOV (G&G) |  | FA | 0EF6050W00A01 | (MOV) MOV Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Motor Operation Valve | 2007-04-30 | 2007-07-13 | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0LF-110602 | OUTLINE DRAWING FOR MOV (G&G) | OUTLINE DRAWING | MOV (G&G) |  |  |  | Outline Drawing for MOV (G&G) |  | FA | 0EF6050W00A01 | (MOV) MOV Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Motor Operation Valve | 2007-04-30 | 2007-07-13 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LF-110603 | VALVE LIST & DATA SHEET FOR MOV (BUTTERFLY) | LIST & DATA SHEET | MOV (BUTTERFLY) |  |  |  | LIST & DATA SHEET for MOV (BUTTERFLY) |  | FA | 0EF6050W00A01 | (MOV) MOV Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Motor Operation Valve | 2007-04-30 | 2007-07-13 | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0LF-110604 | OUTLINE DRAWING FOR MOV (BUTTERFLY) | OUTLINE DRAWING | MOV (BUTTERFLY) |  |  |  | Outline Drawing for MOV (BUTTERFLY) |  | FA | 0EF6050W00A01 | (MOV) MOV Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Motor Operation Valve | 2007-04-30 | 2007-07-13 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CN00-P0ZEN-110701 | OPERATION PHILOSOPHY OF OVERALL PLANT | PHILOSOPHY |  | Plant Operating Philosophy |  |  | PHILOSOPHY for Plant Operating Philosophy | VFD | FA | 0EF1000W00A08 | Operational Philosophy of Overall Plant | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-06-22 | 2008-02-15 | 2024-07-20 | 2024-08-19 | 2024-09-18 | 2024-10-03 | 2024-10-18 | 2024-11-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CN00-P0ZEN-110702 | PLANT START-UP AND SHUT-DOWN PROCEDURE | PROCEDURE |  |  |  |  | PROCEDURE |  | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | 2025-09-13 | 2025-10-04 | 2025-10-25 | 2025-11-18 | 2025-12-03 | 2025-12-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CN00-P0ZEN-110703 | HAZARD AND OPERABILITY STUDY | STUDY |  |  |  |  | STUDY |  | FA | 0CF3515W90A12 | (H2) Installation & Test - I&C | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2008-10-07 | 2008-12-05 |  |  |  | 2025-07-10 | 2025-08-09 | 2025-09-08 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-CN00-P0ZEN-110704 | SAFETY INTEGRITY LEVEL STUDY | STUDY |  |  |  |  | STUDY |  | FA | 1SF9035W62A04 | (Comm'g) Safety & Interlock Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | 2009-05-02 | 2009-05-06 |  |  |  | 2026-02-02 | 2026-03-04 | 2026-04-03 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-CN00-P0ZEN-110705 | HAZARDOUS AREA CLASSIFICATION REPORT | REPORT |  |  |  |  | REPORT |  | FA | 0EF1600W14A10 | HRSG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-04-02 | 2007-06-15 | 2024-03-01 | 2024-03-01 | 2024-03-19 | 2024-04-03 | 2024-04-18 | 2024-05-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CN00-P0ZEN-110706 | HAZOP AND SIL STUDY PROCEDURE | STUDY PROCEDURE |  |  |  |  | STUDY PROCEDURE |  | FA | 0PF6050W86A03.1P | (Safety Valve) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-09-14 | 2008-05-23 | 2025-02-01 | 2025-03-03 | 2025-04-02 | 2025-04-17 | 2025-05-02 | 2025-05-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0GKB-120001 | P&I DIAGRAM FOR POTABLE WATER STORAGE AND SUPPLY SYSTEM | P&I DIAGRAM |  | POTABLE WATER STORAGE AND SUPPLY SYSTEM |  |  | P&ID for POTABLE WATER STORAGE AND SUPPLY SYSTEM | Water Treatment System | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0GKC-120002 | P&I DIAGRAM FOR POTABLE WATER DISTRIBUTION SYSTEM | P&I DIAGRAM |  | POTABLE WATER DISTRIBUTION SYSTEM |  |  | P&ID for POTABLE WATER DISTRIBUTION SYSTEM | Water Treatment System | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SCA-120004 | P&I DIAGRAM FOR COMPRESSED AIR SYSTEM | P&I DIAGRAM |  | COMPRESSED AIR SYSTEM |  |  | P&ID for COMPRESSED AIR SYSTEM |  | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | 2024-10-25 | 2024-11-24 | 2024-12-24 | 2025-01-08 | 2025-01-23 | 2025-02-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SCA-120005 | P&I DIAGRAM FOR INSTRUMENT AIR SYSTEM | P&I DIAGRAM |  | INSTRUMENT AIR SYSTEM |  |  | P&ID for INSTRUMENT AIR SYSTEM |  | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | 2024-10-25 | 2024-11-24 | 2024-12-24 | 2025-01-08 | 2025-01-23 | 2025-02-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SCA-120006 | P&I DIAGRAM FOR SERVICE AIR SYSTEM | P&I DIAGRAM |  | SERVICE AIR SYSTEM |  |  | P&ID for SERVICE AIR SYSTEM |  | FA | 0EF3035W00A01.0 | (SWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-03-15 | 2007-11-21 | 2024-09-09 | 2024-10-09 | 2024-11-08 | 2024-11-23 | 2024-12-08 | 2024-12-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0EK-120007 | P&I DIAGRAM FOR FUEL GAS SYSTEM | P&I DIAGRAM |  | Fuel Gas System |  |  | P&ID for Fuel Gas System | Fuel Gas Compressor | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0GM-120008 | P&I DIAGRAM FOR WASTE WATER TRANSFER SYSTEM | P&I DIAGRAM |  | WASTE WATER TRANSFER SYSTEM |  |  | P&ID for WASTE WATER TRANSFER SYSTEM | Water Treatment System | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0GKS-120012 | DESIGN CRITERIA FOR POTABLE WATER SYSTEM | DESIGN CRITERIA |  | POTABLE WATER SYSTEM |  |  | DESIGN CRITERIA for POTABLE WATER SYSTEM | Water Treatment System | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0GKS-120013 | SIZING CALCULATION - POTABLE WATER DISTRIBUTION PUMP | SIZING CALCULATION | POTABLE WATER DISTRIBUTION PUMP |  |  |  | Calculation sheet for POTABLE WATER DISTRIBUTION PUMP | Water Treatment System | FA | 0CF3035W42A08 | (PWP) Installation (upto pump Discharge header) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2008-10-17 | 2008-11-17 | 2025-11-17 | 2025-12-17 | 2026-01-16 | 2026-01-31 | 2026-02-15 | 2026-03-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SCA-120014 | PROCESS FLOW DIAGRAM FOR COMPRESSED AIR SYSTEM | PROCESS FLOW DIAGRAM |  | COMPRESSED AIR SYSTEM |  |  | PROCESS FLOW DIAGRAM for COMPRESSED AIR SYSTEM |  | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | 2024-07-25 | 2024-08-24 | 2024-09-23 | 2024-10-08 | 2024-10-23 | 2024-11-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0SCA-120015 | SYSTEM DESCRIPTION FOR COMPRESSED AIR SYSTEM | SYSTEM DESCRIPTION |  | COMPRESSED AIR SYSTEM |  |  | System Description for COMPRESSED AIR SYSTEM | Air Compressor | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0SCA-120016 | DESIGN CRITERIA FOR COMPRESSED AIR SYSTEM | DESIGN CRITERIA |  | COMPRESSED AIR SYSTEM |  |  | DESIGN CRITERIA for COMPRESSED AIR SYSTEM |  | FA | 0EF3510W16A18 | (COMP Air BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2007-10-31 | 2025-01-06 | 2025-02-05 | 2025-03-07 | 2025-03-22 | 2025-04-06 | 2025-04-21 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SCA-120017 | SIZING CALCULATION - COMPRESSED AIR SYSTEM | SIZING CALCULATION |  | COMPRESSED AIR SYSTEM |  |  | Calculation sheet for COMPRESSED AIR SYSTEM | Water Treatment System | FA | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | 2024-08-31 | 2024-09-30 | 2024-10-30 | 2024-11-14 | 2024-11-29 | 2024-12-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0EKG-120018 | PROCESS FLOW DIAGRAM FOR FUEL GAS SYSTEM | PROCESS FLOW DIAGRAM |  | Fuel Gas System |  |  | PROCESS FLOW DIAGRAM for Fuel Gas System | Fuel Gas System | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | 2024-03-29 | 2024-05-03 | 2024-06-07 | 2024-05-24 | 2024-06-28 | 2024-08-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0EKG-120019 | SYSTEM DESCRIPTION FOR FUEL GAS SYSTEM | SYSTEM DESCRIPTION |  | Fuel Gas System |  |  | System Description for Fuel Gas System | Fuel Gas System | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | 2024-03-29 | 2024-05-03 | 2024-06-07 | 2024-05-24 | 2024-06-28 | 2024-08-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0EKG-120020 | DESIGN CRITERIA FOR FUEL GAS SYSTEM | DESIGN CRITERIA |  | Fuel Gas System |  |  | DESIGN CRITERIA for Fuel Gas System | Fuel Gas System | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-03-29 | 2024-05-03 | 2024-06-07 | 2024-05-24 | 2024-06-28 | 2024-08-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0EKG-120021 | SIZING CALCULATION - FUEL GAS SYSTEM | SIZING CALCULATION |  | FUEL GAS SYSTEM |  |  | Calculation sheet for FUEL GAS SYSTEM | Fuel Gas System | FA | 0PF3520W42A04P | (Gas Buffer) P.O & Procurement(incl. FG Booster Comp.&Bottles) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Gas Buffer | 2007-06-01 | 2008-04-01 | 2024-10-19 | 2024-11-16 | 2024-12-14 | 2024-12-07 | 2025-01-04 | 2025-02-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0GM-120022 | SYSTEM DESCRIPTION FOR WASTE WATER TRANSFER SYSTEM | SYSTEM DESCRIPTION |  | WASTE WATER TRANSFER SYSTEM |  |  | System Description for WASTE WATER TRANSFER SYSTEM | Water Treatment System | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0GM-120023 | DESIGN CRITERIA FOR WASTE WATER TRANSFER SYSTEM | DESIGN CRITERIA |  | WASTE WATER TRANSFER SYSTEM |  |  | DESIGN CRITERIA for WASTE WATER TRANSFER SYSTEM | Water Treatment System | FA | 0EF4035W16A02.1 | (WWTS) Civil Design(incl. FDN) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-02-01 | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0ZEN-120050 | WATER BALANCE DIAGRAM | Diagram |  | Water Balance Diagram |  |  | Diagram for Water Balance Diagram | Water Treatment System | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0GKS-120051 | SYSTEM DESCRIPTION FOR POTABLE WATER SYSTEM | SYSTEM DESCRIPTION |  | POTABLE WATER SYSTEM |  |  | System Description for POTABLE WATER SYSTEM | Water Treatment System | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MBA-121001 | GTG - EQUIPMENT ARRANGEMENT | EQUIPMENT ARRANGEMENT | Gas Turbine Generator |  |  |  | EQUIPMENT ARRANGEMENT for GTG | Mechanical Workshop Equipment | FA | 1PF2070W42A04P | (STG #10 Aux. Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Auxiliary Equipment | 2007-04-30 | 2008-07-31 | 2024-05-30 | 2024-06-29 | 2024-07-29 | 2024-08-13 | 2024-08-28 | 2024-09-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL25-P0MBA-121002 | GTG - GT EXHAUST MECHANICAL INTERFACE REQUIREMENTS | REQUIREMENTS | Gas Turbine Generator | EXHAUST SYSTEM |  |  | REQUIREMENTS for GTG |  | FA | 1PF1265W64A01.1P | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Air and Flue Gas System | 2007-03-01 | 2008-01-31 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0MBA-121003 | GTG - P&I DIAGRAM | P&I DIAGRAM | Gas Turbine Generator |  |  |  | P&ID for GTG |  | FA | 1PF1213W42A03P | (GT #11) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | 2007-03-01 | 2008-01-31 | 2024-08-12 | 2024-09-11 | 2024-10-11 | 2024-10-26 | 2024-11-10 | 2024-11-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0MBA-121004 | GTG - ROTOR COOLING AIR SYSTEM REQUIREMENTS | REQUIREMENTS | Gas Turbine Generator | cooling system |  |  | REQUIREMENTS for GTG |  | FA | 1PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | 2007-07-03 | 2008-03-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0MBA-121005 | GTG - GOVERNOR AND TURBINE MODEL | MODEL | Gas Turbine Generator |  |  |  | MODEL for GTG |  | FA | 2PF1213W42A03P | (GT #21) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | 2007-03-30 | 2008-02-29 | 2024-07-26 | 2024-08-25 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0MBA-121006 | GTG - GENERATOR, EXCITATION SYSTEM, AND POWER SYSTEM STABILIZER MODEL | MODEL | Gas Turbine Generator |  |  |  | MODEL for GTG |  | FA | 1PF1255W70A01.1P | (GTG#12 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Electrical System | 2007-03-01 | 2008-03-31 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB00-P0MBA-121007 | GTG - AUXILIARY EQUIPMENT FOUNDATION INTERFACE DRAWINGS | DRAWINGS | Gas Turbine Generator |  |  |  | DRAWINGS for GTG |  | FA | 1PF2070W42A04P | (STG #10 Aux. Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Auxiliary Equipment | 2007-04-30 | 2008-07-31 | 2024-08-26 | 2024-09-25 | 2024-10-25 | 2024-11-09 | 2024-11-24 | 2024-12-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0MBA-121008 | GTG - CUSTOMER PIPING CONNECTIONS PHYSICAL AND PROCESS DATA | DATA | Gas Turbine Generator | Piping |  |  | DATA for GTG |  | FA | 3EF1200W00A01 | (GTG #31/#32) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | 2007-03-01 | 2007-03-30 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0MBA-121009 | GTG - INLET FILTER AND DUCT SUPPLIER DRAWINGS | DRAWINGS | Gas Turbine Generator | AIR INTAKE SYSTEM |  |  | DRAWINGS for GTG |  | FA | 1PF1230W64A08.1P | (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Air Intake System | 2007-03-01 | 2008-01-31 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DM02-P0MBA-121010 | GTG_STG-PAC INSTRUCTION BOOK VOLUME I (GAS TURBINE AND AUXILIARIES | INSTRUCTION BOOK | Gas Turbine Generator |  |  |  | INSTRUCTION BOOK for GTG |  | FA | 1PF2070W42A04P | (STG #10 Aux. Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Auxiliary Equipment | 2007-04-30 | 2008-07-31 | 2024-08-26 | 2024-09-25 | 2024-10-25 | 2024-11-09 | 2024-11-24 | 2024-12-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0MBA-121011 | GTG - SYSTEM DESCRIPTION | SYSTEM DESCRIPTION | Gas Turbine Generator |  |  |  | System Description for GTG |  | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | 2024-08-20 | 2024-09-19 | 2024-10-19 | 2024-11-03 | 2024-11-18 | 2024-12-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0MBA-121012 | GTG - GENERATOR/MEDIUM VOLTAGE SINGLE LINE DIAGRAM | Single Line Diagram | Gas Turbine Generator |  |  |  | Single Line Diagram for GTG |  | SKIP | 3PF1255W70A01.1P | (GTG#32 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Electrical System | 2007-04-30 | 2008-05-28 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MBA-121013 | GTG - GENERATOR CAPABILITY CURVES AND DATA | DATA | Gas Turbine Generator |  |  |  | DATA for GTG |  | FA | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-30 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL25-P0MBA-121014 | GTG - GENERATOR ISOPHASE BUS INTERFACE | INTERFACE | Gas Turbine Generator |  |  |  | INTERFACE for GTG |  | FA | 1PF1255W70A01.1P | (GTG#12 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Electrical System | 2007-03-01 | 2008-03-31 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0MBA-121015 | GTG - DESIGN REQUIREMENTS FOR VT & SURGE, BAB36 | REQUIREMENTS | Gas Turbine Generator |  |  |  | REQUIREMENTS for GTG |  | FA | 3PF1213W42A03P | (GT #31) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | 2007-04-30 | 2008-03-31 | 2024-08-26 | 2024-09-25 | 2024-10-25 | 2024-11-09 | 2024-11-24 | 2024-12-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL06-P0MBA-121016 | GTG - ELECTRICAL LOAD LIST | LOAD LIST | Gas Turbine Generator |  |  |  | LOAD LIST for GTG |  | SKIP | 1PF1255W70A01.1P | (GTG#12 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Electrical System | 2007-03-01 | 2008-03-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU05-P0MBA-121017 | GTG - THREE - LINE SCHEMATICS | THREE - LINE SCHEMATICS | Gas Turbine Generator |  |  |  | THREE - LINE SCHEMATICS for GTG |  | FA | 3PF1255W70A02T | (GTG#31 Electrical) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Electrical System | 2008-05-29 | 2008-07-12 |  |  |  | 2025-03-01 | 2025-03-31 | 2025-04-30 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0MBA-121018 | GTG - MCC & 125VDC SINGLE LINE DIAGRAM | SINGLE LINE DIAGRAM | Gas Turbine Generator |  |  |  | Single Line Diagram for GTG |  | SKIP | 1PF1255W70A01P | (GTG#11 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | 2007-03-01 | 2008-03-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0MBA-121019 | GTG - CUSTOMER ELECTRICAL CONNECTIONS |  | Gas Turbine Generator |  |  |  | for GTG |  | FA | 1PF1255W70A01P | (GTG#11 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | 2007-03-01 | 2008-03-31 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0MBA-121020 | GTG - ELECTRICAL SCHEMATICS | SCHEMATICS | Gas Turbine Generator |  |  |  | SCHEMATICS for GTG |  | FA | 1PF1255W70A01P | (GTG#11 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | 2007-03-01 | 2008-03-31 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0MBA-121021 | GTG - ABOVE - GRADE FIELD CONDUIT PLAN | PLAN | Gas Turbine Generator |  |  |  | Plan for GTG |  | FA | 1CF1255W70A03.1 | (GTG#12 Electrical) Installation- PCC | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Electrical System | 2008-08-01 | 2008-09-15 |  |  |  | 2025-05-04 | 2025-06-03 | 2025-07-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0MBA-121022 | GTG - CABLE AND CONDUIT LIST | LIST | Gas Turbine Generator |  |  |  | LIST for GTG |  | FA | 2PF1255W70A01P | (GTG#21 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Electrical System | 2007-03-30 | 2008-04-29 | 2024-07-26 | 2024-08-25 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MBA-121023 | GTG_ELECTRICAL PROTECTION AND OPERATION SETTINGS |  | Gas Turbine Generator |  |  |  | for GTG |  | FA | 1CF1255W70A05 | (GTG#11 Electrical) Installation- Protection Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | 2008-08-01 | 2008-09-15 | 2025-11-28 | 2025-12-28 | 2026-01-27 | 2026-02-11 | 2026-02-26 | 2026-03-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL25-P0MBA-121024 | GTG - DCS SIGNAL INTERFACE INFORMATION |  | Gas Turbine Generator |  |  |  | for GTG |  | FA | 0SF7000W62A09 | (DCS) Electrical signal Test for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2008-07-24 | 2008-07-28 | 2025-11-20 | 2025-12-20 | 2026-01-19 | 2026-02-03 | 2026-02-18 | 2026-03-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0MBA-121025 | GTG - INSTRUMENT, VALVE AND CONTROL SETTINGS LIST | LIST | Gas Turbine Generator |  |  |  | LIST for GTG |  | FA | 1PF1265W42A12.8P | (Control Oil) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Auxiliary System | 2007-03-01 | 2008-01-31 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS01-P0MBA-121026 | GTG - CONTROL PHILOSOPHY | PHILOSOPHY | Gas Turbine Generator | control system |  |  | PHILOSOPHY for GTG |  | FA | 1PF1265W42A12P | (Control Oil) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | 2007-03-01 | 2008-01-31 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS01-P0MBA-121027 | GTG - CONTROL SYSTEM DESCRIPTION | DESCRIPTION | Gas Turbine Generator | control system |  |  | DESCRIPTION for GTG |  | FA | 1PF1265W42A12P | (Control Oil) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | 2007-03-01 | 2008-01-31 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0MBA-121028 | GTG - CONTROL SYSTEM INPUT/OUTPUT DATABASE (I/O DATABASE) | DATABASE | Gas Turbine Generator | control system |  |  | DATABASE for GTG |  | FA | 1PF1265W42A12P | (Control Oil) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | 2007-03-01 | 2008-01-31 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0MBA-121029 | GTG - POWER SUPPLY DISTRIBUTION DRAWING | DRAWING | Gas Turbine Generator |  |  |  | DRAWING for GTG |  | FA | 1PF1265W42A13P | (TCA Cooler) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Gas Supply System | 2007-03-01 | 2008-02-29 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MBA-121030 | GTG - DATA SHEETS FOR I&C EQUIPMENT | DATA SHEETS | Gas Turbine Generator | Instrumentation & Control |  |  | DATA SHEETS for GTG |  | FA | 1PF1265W42A12P | (Control Oil) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | 2007-03-01 | 2008-01-31 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0MBA-121031 | GTG - CABINET / PANEL TERMINAL BLOCK DETAILS |  | Gas Turbine Generator |  |  |  | for GTG |  | FA | 3PF1255W70A01P | (GTG#31 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Electrical System | 2007-04-30 | 2008-05-28 | 2024-08-26 | 2024-09-25 | 2024-10-25 | 2024-11-09 | 2024-11-24 | 2024-12-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD05-P0MBA-121032 | GTG - HMI GRAPHIC | HMI GRAPHIC | Gas Turbine Generator |  |  |  | HMI GRAPHIC for GTG |  | FA | 1PF1255W70A01P | (GTG#11 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | 2007-03-01 | 2008-03-31 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS01-P0MBA-121033 | GTG - CONTROL SYSTEM OVERVIEW | OVERVIEW | Gas Turbine Generator | control system |  |  | OVERVIEW for GTG |  | FA | 1CF1255W86A06 | (GTG#11 Electrical) Installation- GT control Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | 2008-08-04 | 2008-09-15 | 2025-12-01 | 2025-12-31 | 2026-01-30 | 2026-02-14 | 2026-03-01 | 2026-03-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS01-P0MBA-121034 | GTG - FOUNDATION DESIGN BASIS DOCUMENT | DOCUMENT | Gas Turbine Generator |  |  |  | DOCUMENT for GTG |  | FA | 1PF1213W42A03P | (GT #11) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | 2007-03-01 | 2008-01-31 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS01-P0MBA-121035 | GTG - POWER BLOCK FOUNDATION GENERAL NOTES |  | Gas Turbine Generator |  |  |  | for GTG |  | FA | 1PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-09-03 | 2008-01-15 | 2024-12-30 | 2025-01-29 | 2025-02-28 | 2025-03-15 | 2025-03-30 | 2025-04-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YQ03-P0CY-121036 | GTG – ELECTRICAL PACKAGE COMMUNICATION LAYOUT DRAWING | LAYOUT DRAWING | Gas Turbine Generator | Communication System & Security System |  |  | Layout Drawing for GTG | Substation | SKIP | 1PF1255W70A01.1P | (GTG#12 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Electrical System | 2007-03-01 | 2008-03-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0MBA-121037 | GTG - PSS STUDY REPORT_DRAFT | STUDY REPORT_DRAFT | Gas Turbine Generator |  |  |  | STUDY REPORT_DRAFT for GTG |  | FA | 1PF1255W70A01P | (GTG#11 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | 2007-03-01 | 2008-03-31 | 2024-07-09 | 2024-08-08 | 2024-09-07 | 2024-09-22 | 2024-10-07 | 2024-10-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DM02-P0MBA-121038 | GTG_STG-PAC INSTRUCTION BOOK VOLUME II (GENERATOR AND AUXILIARIES) | INSTRUCTION BOOK | Gas Turbine Generator, Steam Turbine & Generator |  |  |  | INSTRUCTION BOOK for Gas Turbine Generator, Steam Turbine & Generator |  | FA | 1PF2070W42A04P | (STG #10 Aux. Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Auxiliary Equipment | 2007-04-30 | 2008-07-31 | 2024-08-26 | 2024-09-25 | 2024-10-25 | 2024-11-09 | 2024-11-24 | 2024-12-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VN01-P0MBA-121044 | GTG - ACCESS PLATFORM LAYOUT | LAYOUT | Gas Turbine Generator |  |  |  | Layout Drawing for GTG | Substation | SKIP | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-CQ02-P0MBA-121051 | GTG_GAS TURBINE AND AUXILIARIES INSTALLATION MANUAL | INSTALLATION MANUAL | Gas Turbine Generator |  |  |  | INSTALLATION MANUAL for GTG |  | FI | 3CF1265W90A06 | (Air&Flue Gas System) Installation- I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Air and Flue Gas System | 2008-07-02 | 2008-07-15 | 2025-02-22 | 2025-03-24 | 2025-04-23 | 2025-05-08 | 2025-05-23 | 2025-06-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CQ02-P0MBA-121073 | GTG_GAS TURBINE AND AUXILIARIES COMMISSIOINING MANUAL | COMMISSIOINING MANUAL | Gas Turbine Generator |  |  |  | COMMISSIOINING MANUAL for GTG |  | FI | 3PF1213W42A04T | (GT #31) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | 2008-04-01 | 2008-05-14 | 2024-12-22 | 2025-01-21 | 2025-02-20 | 2025-03-07 | 2025-03-22 | 2025-04-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CQ02-P0MBA-121076 | GTG_INSTALLATION MANUAL | INSTALLATION MANUAL | Gas Turbine Generator |  |  |  | INSTALLATION MANUAL for GTG |  | FI | 3CF1213W42A10 | (GEN #31) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | 2008-06-27 | 2008-10-27 | 2025-06-06 | 2025-07-06 | 2025-08-05 | 2025-08-20 | 2025-09-04 | 2025-09-19 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CQ02-P0MBA-121077 | GTG_GENERATOR REMOVAL PROCEDURE | PROCEDURE | Gas Turbine Generator |  |  |  | PROCEDURE for GTG |  | FA | 1PF1213W42A03P | (GT #11) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | 2007-03-01 | 2008-01-31 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CQ02-P0MBA-121099 | GTG ERECTION DRAWING PACKAGE | DRAWING PACKAGE | Gas Turbine Generator |  |  |  | DRAWING PACKAGE for GTG |  | FA | 3PF1255W70A01P | (GTG#31 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Electrical System | 2007-04-30 | 2008-05-28 | 2024-08-26 | 2024-09-25 | 2024-10-25 | 2024-11-09 | 2024-11-24 | 2024-12-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0GM-121100 | GTG – DRAIN INTERFACE FLOW DIAGRAM | FLOW DIAGRAM | Gas Turbine Generator | Drain System |  |  | FLOW DIAGRAM for GTG |  | FA | 1PF1265W42A02.0P | (Washing & Drain system Skid) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Washing & Drain System | 2007-03-01 | 2008-02-29 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MBA-121555 | GTG_CONDUIT LAYOUT DRAWING | LAYOUT DRAWING | Gas Turbine Generator |  |  |  | Layout Drawing for GTG | Substation | SKIP | 1PF1213W42A03P | (GT #11) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | 2007-03-01 | 2008-01-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MBA-121677 | GTG_GAS TURBINE GENERATOR COMMISSIOINING MANUAL | COMMISSIOINING MANUAL | Gas Turbine Generator |  |  |  | COMMISSIOINING MANUAL for GTG |  | FI | 1PF1213W42A04.1T | (GT #12) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Main body | 2008-03-01 | 2008-04-14 | 2024-11-22 | 2024-12-22 | 2025-01-21 | 2025-02-05 | 2025-02-20 | 2025-03-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0MBA-121678 | GTG_I&C SCHEMATICS | SCHEMATICS | Gas Turbine Generator | Instrumentation & Control |  |  | SCHEMATICS for GTG |  | FA | 1PF1265W42A12P | (Control Oil) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | 2007-03-01 | 2008-01-31 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MBA-121824 | GTG_FIRE PROTECTION SYSTEM DRAWING | DRAWING | Gas Turbine Generator | Fire Fighting System |  |  | DRAWING for GTG |  | FA | 1PF1265W38A01.7P | (F/F GTG#12) P.O & Procurement_CO2 FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fire fighting System | 2007-03-01 | 2008-03-14 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MBA-121971 | GTG – SFC / SEE CIRCUIT DIAGRAM | CIRCUIT DIAGRAM | Gas Turbine Generator |  |  |  | CIRCUIT DIAGRAM for GTG |  | FA | 1PF6500W86A02P | (GT GCB) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Generator Circuit Breaker (GCB) | 2007-05-31 | 2008-03-31 | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CQ02-P0LB-122001 | HRSG - INSTALLATION AND INSTRUCTION MANUAL | INSTALLATION AND INSTRUCTION MANUAL | Heat Recovery Steam Generator |  |  |  | INSTALLATION AND INSTRUCTION MANUAL for HRSG |  | FI | 1PF1600W90A11.1T | (HRSG #12 LEB) Transportataion - I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | 2008-07-11 | 2008-08-24 | 2025-04-03 | 2025-05-03 | 2025-06-02 | 2025-06-17 | 2025-07-02 | 2025-07-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DF04-P0LB-122003 | HRSG - STRESS ANALYSIS ISOMETRIC DRAWING FOR CRITICAL PIPING | DRAWING | Heat Recovery Steam Generator | Piping |  |  | DRAWING for HRSG |  | FA | 1PF1650W52A02.1P | (HRSG #12 Insulation) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Piping Work | 2008-01-09 | 2008-09-30 | 2025-09-21 | 2025-10-21 | 2025-11-20 | 2025-12-05 | 2025-12-20 | 2026-01-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DF04-P0LB-122004 | HRSG - CFD REPORT FOR INLET DUCT | REPORT | Heat Recovery Steam Generator |  |  |  | REPORT for HRSG |  | FA | 1PF1615W64A06P | (HRSG #11 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | 2007-06-14 | 2008-01-31 | 2024-11-10 | 2024-12-10 | 2025-01-09 | 2025-01-24 | 2025-02-08 | 2025-02-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DF04-P0LB-122005 | HRSG - CFD REPORT FOR DUCT BURNER SYSTEM | REPORT | Heat Recovery Steam Generator |  |  |  | REPORT for HRSG |  | FA | 1PF1615W64A06.1P | (HRSG #12 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | 2007-06-14 | 2008-01-31 | 2024-11-10 | 2024-12-10 | 2025-01-09 | 2025-01-24 | 2025-02-08 | 2025-02-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122006 | HRSG - SPEC. & DRAWING FOR HOIST | DRAWING | Heat Recovery Steam Generator |  |  |  | DRAWING for HRSG |  | FA | 1PF1600W74A06.1P | (HRSG #12 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | 2007-09-15 | 2008-07-10 | 2025-05-28 | 2025-06-27 | 2025-07-27 | 2025-08-11 | 2025-08-26 | 2025-09-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122007 | HRSG - GENERAL ARRANGEMENT | GENERAL ARRANGEMENT | Heat Recovery Steam Generator |  |  |  | General Arrangement Drawing for HRSG |  | FA | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122008 | HRSG - ARRANGEMENT OF CASING & FIELD ERECTION | ARRANGEMENT | Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG |  | FA | 1PF1610W20A03P | (HRSG #11 S/Structure & Casing) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Steel Structure & Casing | 2007-06-14 | 2008-01-01 | 2024-09-09 | 2024-10-09 | 2024-11-08 | 2024-11-23 | 2024-12-08 | 2024-12-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122009 | HRSG - ARRANGEMENT OF INLET DUCT | ARRANGEMENT | Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG |  | FA | 1PF1615W64A06.1P | (HRSG #12 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | 2007-06-14 | 2008-01-31 | 2024-09-09 | 2024-10-09 | 2024-11-08 | 2024-11-23 | 2024-12-08 | 2024-12-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122010 | HRSG - ARRANGEMENT OF MAIN STACK& FIELD ERECTION | ARRANGEMENT | Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG |  | FA | 1PF1625W42A06.0P | (HRSG #11 Main Stack) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | 2007-06-04 | 2008-01-31 | 2024-08-30 | 2024-09-29 | 2024-10-29 | 2024-11-13 | 2024-11-28 | 2024-12-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122011 | HRSG - GENERAL ARRANGEMENT FOR DUCT BURNER SYSTEM | GENERAL ARRANGEMENT | Heat Recovery Steam Generator |  |  |  | General Arrangement Drawing for HRSG |  | FA | 3EF1615W00A01 | (HRSG #31 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2007-06-29 |  | 2024-09-24 | 2024-10-24 | 2024-11-23 | 2024-12-08 | 2024-12-23 | 2025-01-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122012 | HRSG - DETAIL ARRANGEMENT FOR DUCT BURNER SYSTEM | DETAIL ARRANGEMENT | Heat Recovery Steam Generator |  |  |  | DETAIL ARRANGEMENT for HRSG |  | FA | 1PF1615W64A06.1P | (HRSG #12 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | 2007-06-14 | 2008-01-31 | 2024-09-09 | 2024-10-09 | 2024-11-08 | 2024-11-23 | 2024-12-08 | 2024-12-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122013 | HRSG - FUEL GAS SKID ARRANGEMENT FOR DUCT BURNER SYSTEM | ARRANGEMENT | Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG |  | FA | 3PF1615W64A06.1P | (HRSG #32 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Duct | 2007-06-14 | 2008-04-02 | 2024-09-09 | 2024-10-09 | 2024-11-08 | 2024-11-23 | 2024-12-08 | 2024-12-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122014 | HRSG - COOLING AIR SKID ARRANGEMENT FOR DUCT BURNER SYSTEM | ARRANGEMENT | Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG |  | FA | 1PF1615W64A06.1P | (HRSG #12 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | 2007-06-14 | 2008-01-31 | 2024-09-09 | 2024-10-09 | 2024-11-08 | 2024-11-23 | 2024-12-08 | 2024-12-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VN03-P0LB-122015 | HRSG - ARRANGEMENT FOR PLATFORM STRUCTURE | ARRANGEMENT | Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG |  | FA | 1PF1610W20A03P | (HRSG #11 S/Structure & Casing) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Steel Structure & Casing | 2007-06-14 | 2008-01-01 | 2024-09-09 | 2024-10-09 | 2024-11-08 | 2024-11-23 | 2024-12-08 | 2024-12-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0LB-122016 | HRSG - COLUMN LOCATION FOR STEEL STRUCTURE AND STACK |  | Heat Recovery Steam Generator |  |  |  | for HRSG |  | FA | 1PF1610W20A03.1P | (HRSG #12 S/Structure & Casing) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Steel Structure & Casing | 2007-06-14 | 2008-01-31 | 2024-11-25 | 2024-12-25 | 2025-01-24 | 2025-02-08 | 2025-02-23 | 2025-03-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0LB-122017 | HRSG - FOUNDATION LOAD TABLE FOR STEEL STRUCTURE AND STACK | FOUNDATION LOAD TABLE | Heat Recovery Steam Generator |  |  |  | FOUNDATION LOAD TABLE for HRSG |  | FA | 2EF1625W00A02 | (HRSG #21 Main Stack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Main Stack | 2007-07-05 |  |  |  |  | 2024-04-06 | 2024-05-06 | 2024-06-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0LB-122018 | HRSG - BASE PLATE AND ANCHOR BOLTS DETAIL FOR STEEL STRUCTURE |  | Heat Recovery Steam Generator |  |  |  | for HRSG |  | FA | 1PF1610W20A03P | (HRSG #11 S/Structure & Casing) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Steel Structure & Casing | 2007-06-14 | 2008-01-01 | 2024-11-25 | 2024-12-25 | 2025-01-24 | 2025-02-08 | 2025-02-23 | 2025-03-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0LB-122019 | HRSG - ANCHOR BOLT & TEMPLATE DETAIL FOR STACK |  | Heat Recovery Steam Generator |  |  |  | for HRSG |  | FA | 1PF1625W42A06.0P | (HRSG #11 Main Stack) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | 2007-06-04 | 2008-01-31 | 2024-11-15 | 2024-12-15 | 2025-01-14 | 2025-01-29 | 2025-02-13 | 2025-02-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0LB-122020 | HRSG - FOUNDATION LOADING & LOCATION DRAWING FOR BLOWDOWN TANK | FOUNDATION LOADING & LOCATION DRAWING | Heat Recovery Steam Generator |  |  |  | FOUNDATION LOADING & LOCATION DRAWING for HRSG |  | FA | 1EF1625W16A03.2 | (HRSG #12 Main Stack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Main Stack | 2007-09-07 | 2008-01-16 | 2024-12-19 | 2025-01-18 | 2025-02-17 | 2025-03-04 | 2025-03-19 | 2025-04-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG01-P0LB-122021 | HRSG - LARGE BORE PIPING ARRANGEMENT | ARRANGEMENT | Heat Recovery Steam Generator | Piping |  |  | ARRANGEMENT for HRSG |  | FA | 1PF1650W52A02.1P | (HRSG #12 Insulation) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Piping Work | 2008-01-09 | 2008-09-30 | 2025-04-06 | 2025-05-06 | 2025-06-05 | 2025-06-20 | 2025-07-05 | 2025-07-20 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LB-122022 | HRSG - P&I DIAGRAM | P&I DIAGRAM | Heat Recovery Steam Generator |  |  |  | P&ID for HRSG |  | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | 2024-08-30 | 2024-09-29 | 2024-10-29 | 2024-11-13 | 2024-11-28 | 2024-12-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LB-122023 | HRSG - P&I DIAGRAM FOR HRSG DUCT BURNER SYSTEM | P&I DIAGRAM | Heat Recovery Steam Generator |  |  |  | P&ID for HRSG |  | FA | 1PF1615W64A06.1P | (HRSG #12 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | 2007-06-14 | 2008-01-31 | 2024-11-25 | 2024-12-25 | 2025-01-24 | 2025-02-08 | 2025-02-23 | 2025-03-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LB-122024 | HRSG - PIPE SUPPORT DRAWING FOR EXTERNAL PIPING | PIPE SUPPORT DRAWING | Heat Recovery Steam Generator | Piping |  |  | PIPE SUPPORT DRAWING for HRSG |  | FA | 3PF1650W52A02.1P | (HRSG #32 Insulation) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Piping Work | 2008-01-09 | 2008-12-01 | 2025-09-21 | 2025-10-21 | 2025-11-20 | 2025-12-05 | 2025-12-20 | 2026-01-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LB-122025 | HRSG - TYPICAL SUPPORT DRAWING FOR SMALL BORE PIPING | TYPICAL SUPPORT DRAWING | Heat Recovery Steam Generator | Piping |  |  | TYPICAL SUPPORT DRAWING for HRSG |  | FA | 3PF1650W52A02.1P | (HRSG #32 Insulation) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Piping Work | 2008-01-09 | 2008-12-01 | 2025-11-21 | 2025-12-21 | 2026-01-20 | 2026-02-04 | 2026-02-19 | 2026-03-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LB-122026 | HRSG - PIPE SUPPORT DRAWINGS | PIPE SUPPORT DRAWINGS | Heat Recovery Steam Generator |  |  |  | PIPE SUPPORT DRAWINGS for HRSG |  | FA | 3EF1600W00A02 | (HRSG #31/#32) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-03-01 | 2007-03-30 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LB-122027 | HRSG - LARGE BORE ERECTION ISOMETRIC DRAWING FOR EXTERNAL PIPING | ISOMETRIC DRAWING | Heat Recovery Steam Generator | Piping |  |  | Isometric Drawing for HRSG |  | FA | 1PF1650W52A02P | (HRSG #11 Insulation) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Piping Work | 2008-01-09 | 2008-09-30 | 2025-09-21 | 2025-10-21 | 2025-11-20 | 2025-12-05 | 2025-12-20 | 2026-01-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LB-122028 | HRSG - SMALL BORE ERECTION ISOMETRIC DRAWING FOR EXTERNAL PIPING | ISOMETRIC DRAWING | Heat Recovery Steam Generator | Piping |  |  | Isometric Drawing for HRSG |  | FA | 1PF1650W52A02P | (HRSG #11 Insulation) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Piping Work | 2008-01-09 | 2008-09-30 | 2025-09-21 | 2025-10-21 | 2025-11-20 | 2025-12-05 | 2025-12-20 | 2026-01-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LB-122029 | HRSG - VENT & DRAIN LINE (MODULE /FIELD WELD) |  | Heat Recovery Steam Generator | Drain System |  |  | for HRSG |  | FA | 3PF1610W42A02.1P | (HRSG #32 Module) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Module | 2007-07-03 | 2008-05-02 | 2024-12-14 | 2025-01-13 | 2025-02-12 | 2025-02-27 | 2025-03-14 | 2025-03-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XL00-P0LB-122030 | HRSG - LINE LIST | LINE LIST | Heat Recovery Steam Generator |  |  |  | LINE LIST for HRSG |  | FA | 2PF1600W74A06.1P | (HRSG #22 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > HRSG LEB | 2007-09-15 | 2008-08-01 | 2025-02-11 | 2025-03-13 | 2025-04-12 | 2025-04-27 | 2025-05-12 | 2025-05-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XL00-P0LB-122031 | HRSG - LINE LIST FOR DUCT BURNER SYSTEM | LINE LIST | Heat Recovery Steam Generator |  |  |  | LINE LIST for HRSG |  | FA | 1PF1615W64A06.1P | (HRSG #12 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | 2007-06-14 | 2008-01-31 | 2024-11-10 | 2024-12-10 | 2025-01-09 | 2025-01-24 | 2025-02-08 | 2025-02-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0LB-122032 | HRSG - MANUAL VALVE LIST | LIST | Heat Recovery Steam Generator |  |  |  | LIST for HRSG |  | FA | 1PF1615W64A10P | (HRSG #11 Damper) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | 2007-06-13 | 2008-02-29 | 2024-11-09 | 2024-12-09 | 2025-01-08 | 2025-01-23 | 2025-02-07 | 2025-02-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0LB-122033 | HRSG - MOV & CV LIST | LIST | Heat Recovery Steam Generator |  |  |  | LIST for HRSG |  | FA | 2PF1600W74A06P | (HRSG #21 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | 2007-09-15 | 2008-08-01 | 2025-02-11 | 2025-03-13 | 2025-04-12 | 2025-04-27 | 2025-05-12 | 2025-05-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0LB-122034 | HRSG - VALVE LIST FOR DUCT BURNER SYSTEM | LIST | Heat Recovery Steam Generator |  |  |  | LIST for HRSG |  | FA | 1PF1615W64A06.1P | (HRSG #12 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | 2007-06-14 | 2008-01-31 | 2024-11-10 | 2024-12-10 | 2025-01-09 | 2025-01-24 | 2025-02-08 | 2025-02-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0LB-122035 | HRSG - SYSTEM DESCRIPTION | SYSTEM DESCRIPTION | Heat Recovery Steam Generator |  |  |  | System Description for HRSG |  | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | 2024-06-30 | 2024-07-30 | 2024-08-29 | 2024-09-13 | 2024-09-28 | 2024-10-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0LB-122036 | HRSG - SYSTEM DESCRIPTION FOR HRSG DUCT BURNER SYSTEM | SYSTEM DESCRIPTION | Heat Recovery Steam Generator |  |  |  | System Description for HRSG |  | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | 2024-06-30 | 2024-07-30 | 2024-08-29 | 2024-09-13 | 2024-09-28 | 2024-10-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0LB-122037 | HRSG - BLOWDOWN SYSTEM SUMMARY | SUMMARY | Heat Recovery Steam Generator |  |  |  | SUMMARY for HRSG |  | FA | 1PF1665W42A02P | (HRSG #11 MECH Vendor Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | 2007-09-10 | 2008-08-01 | 2024-12-06 | 2025-01-05 | 2025-02-04 | 2025-02-19 | 2025-03-06 | 2025-03-21 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XV00-P0LB-122038 | HRSG - BMS PANEL PART LIST FOR DUCT BURNER SYSTEM | LIST | Heat Recovery Steam Generator |  |  |  | LIST for HRSG |  | FA | 1PF1615W64A06.1P | (HRSG #12 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | 2007-06-14 | 2008-01-31 | 2024-11-10 | 2024-12-10 | 2025-01-09 | 2025-01-24 | 2025-02-08 | 2025-02-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XV00-P0LB-122039 | HRSG - EQUIPMENT LIST | LIST | Heat Recovery Steam Generator |  |  |  | LIST for HRSG |  | FA | 1PF1665W42A02P | (HRSG #11 MECH Vendor Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | 2007-09-10 | 2008-08-01 | 2025-02-06 | 2025-03-08 | 2025-04-07 | 2025-04-22 | 2025-05-07 | 2025-05-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CN00-P0LB-122040 | HRSG - HAZARDOUS AREA CLASSIFICATION SPECIFICATION & DRAWING FOR DUCT BURNER SYSTEM | SPECIFICATION & DRAWING | Heat Recovery Steam Generator |  |  |  | SPECIFICATION & DRAWING for HRSG |  | FA | 1PF1615W64A06.1P | (HRSG #12 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | 2007-06-14 | 2008-01-31 | 2025-01-13 | 2025-02-12 | 2025-03-14 | 2025-03-29 | 2025-04-13 | 2025-04-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0LB-122041 | HRSG - TECHNICAL SPECIFICATION FOR AC & DC DISTRIBUTION BOARD | TECHNICAL SPECIFICATION | Heat Recovery Steam Generator |  |  |  | Technical Specification for HRSG |  | FA | 3PF1600W74A06P | (HRSG #31 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | 2007-09-15 | 2008-08-23 | 2025-02-26 | 2025-03-28 | 2025-04-27 | 2025-05-12 | 2025-05-27 | 2025-06-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122042 | HRSG - COOLING AIR FAN & MOTOR DATASHEET FOR DUCT BURNER SYSTEM | DATASHEET | Heat Recovery Steam Generator |  |  |  | Data Sheet for HRSG |  | FA | 1PF1615W64A06.1P | (HRSG #12 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | 2007-06-14 | 2008-01-31 | 2025-03-04 | 2025-04-03 | 2025-05-03 | 2025-05-18 | 2025-06-02 | 2025-06-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122044 | HRSG - BMS SHELTER LAYOUT FOR DUCT BURNER SYSTEM | LAYOUT | Heat Recovery Steam Generator |  |  |  | Layout Drawing for HRSG |  | FA | 2EF1615W00A01 | (HRSG #21 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-05-30 |  | 2025-02-09 | 2025-03-11 | 2025-04-10 | 2025-04-25 | 2025-05-10 | 2025-05-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0LB-122045 | HRSG - TECHNICAL SPECIFICATION FOR EARTHING & LIGHTNING PROTECTION SYSTEM | TECHNICAL SPECIFICATION | Heat Recovery Steam Generator | Earthing & Lightning Protection System |  |  | Technical Specification for HRSG |  | FA | 0EF6040W80A01 | (Earthing & Lightning Material) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials |  | 2007-05-30 | [6 empty] | missing_date |  | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0LB-122046 | HRSG - TECHNICAL SPECIFICATION FOR COMMUNICATION SYSTEM | TECHNICAL SPECIFICATION | Heat Recovery Steam Generator | Communication System & Security System |  |  | Technical Specification for HRSG |  | FA | 1PF1665W42A12.1P | (HRSG #12 MECH Vendor Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Auxiliary System | 2007-09-10 | 2008-08-01 | 2025-02-21 | 2025-03-23 | 2025-04-22 | 2025-05-07 | 2025-05-22 | 2025-06-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0LB-122047 | HRSG - CABLE CONNECTION DIAGRAM | CABLE CONNECTION DIAGRAM | Heat Recovery Steam Generator |  |  |  | CABLE CONNECTION DIAGRAM for HRSG |  | FA | 3PF1600W74A06.1P | (HRSG #32 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > HRSG LEB | 2007-09-15 | 2008-08-23 | 2025-03-28 | 2025-04-27 | 2025-05-27 | 2025-06-11 | 2025-06-26 | 2025-07-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0LB-122048 | HRSG - PRESSURE PART ARRANGEMENT | ARRANGEMENT | Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG |  | FA | 3EF1600W00A02 | (HRSG #31/#32) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122049 | HRSG - SPEC. & DRAWING FOR STEAM DRUM | SPEC. & DRAWING | Heat Recovery Steam Generator |  |  |  | SPEC. & DRAWING for HRSG |  | FA | 1PF1645W42A03.1P | (HRSG #12 Drum) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Drum | 2007-06-13 | 2008-04-30 | 2024-11-24 | 2024-12-24 | 2025-01-23 | 2025-02-07 | 2025-02-22 | 2025-03-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122050 | HRSG - SPEC. & DRAWING FOR BLOWDOWN PUMP | SPEC. & DRAWING | Heat Recovery Steam Generator |  |  |  | SPEC. & DRAWING for HRSG |  | FA | 3PF1615W64A14P | (HRSG #31 EXP Joint & Bellows) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2007-06-13 | 2008-05-30 | 2024-11-24 | 2024-12-24 | 2025-01-23 | 2025-02-07 | 2025-02-22 | 2025-03-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122051 | HRSG - SPEC. & DRAWING FOR SAFETY & RELIEF VALVE | SPEC. & DRAWING | Heat Recovery Steam Generator |  |  |  | SPEC. & DRAWING for HRSG |  | FA | 3PF1650W52A02.1P | (HRSG #32 Insulation) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Piping Work | 2008-01-09 | 2008-12-01 | 2025-06-22 | 2025-07-22 | 2025-08-21 | 2025-09-05 | 2025-09-20 | 2025-10-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122052 | HRSG - SPEC. & DRAWING FOR STACK DAMPER | SPEC. & DRAWING | Heat Recovery Steam Generator |  |  |  | SPEC. & DRAWING for HRSG |  | FA | 3PF1615W64A10.1P | (HRSG #32 Damper) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Duct | 2007-06-13 | 2008-05-01 | 2024-11-24 | 2024-12-24 | 2025-01-23 | 2025-02-07 | 2025-02-22 | 2025-03-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122053 | HRSG - SPEC. & DRAWING FOR VENT SILENCER | SPEC. & DRAWING | Heat Recovery Steam Generator |  |  |  | SPEC. & DRAWING for HRSG |  | FA | 1PF1625W42A10.2P | (HRSG #12 Main Stack Silencer) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Main Stack | 2007-06-13 | 2008-03-31 | 2024-11-24 | 2024-12-24 | 2025-01-23 | 2025-02-07 | 2025-02-22 | 2025-03-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122054 | HRSG - SPEC. & DRAWING FOR DEAERATOR & STORAGE TANK | SPEC. & DRAWING | Heat Recovery Steam Generator |  |  |  | SPEC. & DRAWING for HRSG |  | FA | 3PF1600W74A06.1P | (HRSG #32 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > HRSG LEB | 2007-09-15 | 2008-08-23 | 2025-02-26 | 2025-03-28 | 2025-04-27 | 2025-05-12 | 2025-05-27 | 2025-06-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122055 | HRSG - EQUIPMENT OUTLINE DRAWING FOR BLOWDOWN TANK | EQUIPMENT OUTLINE DRAWING | Heat Recovery Steam Generator |  |  |  | EQUIPMENT OUTLINE DRAWING for HRSG |  | FA | 1PF1665W42A02P | (HRSG #11 MECH Vendor Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | 2007-09-10 | 2008-08-01 | 2025-03-23 | 2025-04-22 | 2025-05-22 | 2025-06-06 | 2025-06-21 | 2025-07-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122056 | HRSG - POWER DISTRIBUTION PANEL DRAWINGS | DRAWINGS | Heat Recovery Steam Generator |  |  |  | DRAWINGS for HRSG |  | FA | 1PF1600W74A06P | (HRSG #11 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | 2007-09-15 | 2008-07-10 | 2025-01-27 | 2025-02-26 | 2025-03-28 | 2025-04-12 | 2025-04-27 | 2025-05-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122057 | HRSG - HEADER AND SUPPORT DRAWING FOR DUCT BURNER SYSTEM | DRAWING | Heat Recovery Steam Generator |  |  |  | DRAWING for HRSG |  | FA | 1PF1615W64A06.1P | (HRSG #12 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | 2007-06-14 | 2008-01-31 | 2025-02-24 | 2025-03-26 | 2025-04-25 | 2025-05-10 | 2025-05-25 | 2025-06-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122058 | HRSG - BMS PANEL LAYOUT FOR DUCT BURNER SYSTEM | LAYOUT | Heat Recovery Steam Generator |  |  |  | Layout Drawing for HRSG |  | FA | 2EF1615W00A01 | (HRSG #21 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-05-30 |  | 2025-02-09 | 2025-03-11 | 2025-04-10 | 2025-04-25 | 2025-05-10 | 2025-05-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD05-P0LB-122059 | HRSG - HMI SCREEN LAYOUT FOR DUCT BURNER SYSTEM | LAYOUT | Heat Recovery Steam Generator |  |  |  | Layout Drawing for HRSG |  | FA | 2EF1615W00A01 | (HRSG #21 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-05-30 |  | 2025-02-09 | 2025-03-11 | 2025-04-10 | 2025-04-25 | 2025-05-10 | 2025-05-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122060 | HRSG - JUNCTION BOX DATASHEET FOR DUCT BURNER SYSTEM | DATASHEET | Heat Recovery Steam Generator |  |  |  | Data Sheet for HRSG |  | FA | 1PF1615W64A06.1P | (HRSG #12 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | 2007-06-14 | 2008-01-31 | 2025-03-04 | 2025-04-03 | 2025-05-03 | 2025-05-18 | 2025-06-02 | 2025-06-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0LB-122061 | HRSG - FLAME SCANNER & IGNITION BURNER SPECIFICATION FOR DUCT BURNER SYSTEM | SPECIFICATION | Heat Recovery Steam Generator |  |  |  | Technical Specification for HRSG |  | FA | 1PF1615W64A06.1P | (HRSG #12 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | 2007-06-14 | 2008-01-31 | 2024-11-25 | 2024-12-25 | 2025-01-24 | 2025-02-08 | 2025-02-23 | 2025-03-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122062 | HRSG - ARRANGEMENT OF STACK SILENCER | ARRANGEMENT | Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG |  | FA | 1PF1625W42A10.0P | (HRSG #11 Main Stack Silencer) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | 2007-07-27 | 2008-05-14 | 2024-10-22 | 2024-11-21 | 2024-12-21 | 2025-01-05 | 2025-01-20 | 2025-02-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0LB-122063 | HRSG - CONDUIT LAYOUT DRAWING | LAYOUT DRAWING | Heat Recovery Steam Generator |  |  |  | Layout Drawing for HRSG |  | FA | 1PF1600W74A06.1P | (HRSG #12 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | 2007-09-15 | 2008-07-10 | 2025-05-28 | 2025-06-27 | 2025-07-27 | 2025-08-11 | 2025-08-26 | 2025-09-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0LB-122064 | HRSG - CABLE TRAY & RACEWAY LAYOUT DIAGRAM | LAYOUT DIAGRAM | Heat Recovery Steam Generator |  |  |  | LAYOUT DIAGRAM for HRSG |  | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | 2024-06-14 | 2024-07-14 | 2024-08-13 | 2024-08-28 | 2024-09-12 | 2024-09-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0LB-122065 | HRSG - GROUNDING AND LIGHTNING PLAN DIAGRAMS | PLAN DIAGRAMS | Heat Recovery Steam Generator |  |  |  | PLAN DIAGRAMS for HRSG |  | FA | 1PF1600W90A10.1P | (HRSG #12 LEB) P.O & Procurement - I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | 2007-09-15 | 2008-07-10 | 2025-03-28 | 2025-04-27 | 2025-05-27 | 2025-06-11 | 2025-06-26 | 2025-07-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0LB-122066 | HRSG - CONTROL LOGIC DIAGRAM | DIAGRAM | Heat Recovery Steam Generator |  |  |  | Diagram for HRSG |  | FA | 1PF1600W90A10.1P | (HRSG #12 LEB) P.O & Procurement - I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | 2007-09-15 | 2008-07-10 | 2024-12-11 | 2025-01-10 | 2025-02-09 | 2025-02-24 | 2025-03-11 | 2025-03-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0LB-122067 | HRSG - CONTROL LOOP DIAGRAM | DIAGRAM | Heat Recovery Steam Generator |  |  |  | Diagram for HRSG |  | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | 2024-06-14 | 2024-07-14 | 2024-08-13 | 2024-08-28 | 2024-09-12 | 2024-09-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0LB-122068 | HRSG - LOGIC DIAGRAM FOR DUCT BURNER SYSTEM | LOGIC DIAGRAM | Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | LOGIC DIAGRAM for HRSG |  | FA | 1PF1615W64A06P | (HRSG #11 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | 2007-06-14 | 2008-01-31 | 2024-12-25 | 2025-01-24 | 2025-02-23 | 2025-03-10 | 2025-03-25 | 2025-04-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YM03-P0LB-122069 | HRSG - INSTRUMENT LOCATION | INSTRUMENT LOCATION | Heat Recovery Steam Generator |  |  |  | INSTRUMENT LOCATION for HRSG |  | FA | 1PF1600W90A10P | (HRSG #11 LEB) P.O & Procurement - I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | 2007-09-15 | 2008-07-10 | 2025-06-13 | 2025-07-13 | 2025-08-12 | 2025-08-27 | 2025-09-11 | 2025-09-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0LB-122070 | HRSG - BMS SYSTEM CONFIGURATION FOR DUCT BURNER SYSTEM | SYSTEM CONFIGURATION | Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | SYSTEM CONFIGURATION for HRSG |  | FA | 1PF1615W64A06.1P | (HRSG #12 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | 2007-06-14 | 2008-01-31 | 2024-11-25 | 2024-12-25 | 2025-01-24 | 2025-02-08 | 2025-02-23 | 2025-03-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0LB-122071 | HRSG - LINK ASSEMBLY DRAWING | ASSEMBLY DRAWING | Heat Recovery Steam Generator |  |  |  | ASSEMBLY DRAWING for HRSG |  | FA | 1PF1600W74A06.1P | (HRSG #12 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | 2007-09-15 | 2008-07-10 | 2025-06-29 | 2025-07-29 | 2025-08-28 | 2025-09-12 | 2025-09-27 | 2025-10-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0LB-122072 | HRSG - INSTRUMENT INSTALLATION DETAIL DRAWINGS | DRAWINGS | Heat Recovery Steam Generator | INSTRUMENT INSTALLATION MATERIAL |  |  | DRAWINGS for HRSG |  | FA | 1PF1600W90A10P | (HRSG #11 LEB) P.O & Procurement - I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | 2007-09-15 | 2008-07-10 | 2025-01-27 | 2025-02-26 | 2025-03-28 | 2025-04-12 | 2025-04-27 | 2025-05-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0LB-122073 | HRSG - SPECIALTY DRAWING FOR EXTERNAL PIPING | DRAWING | Heat Recovery Steam Generator | Piping |  |  | DRAWING for HRSG |  | FA | 3PF1650W52A02.1P | (HRSG #32 Insulation) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Piping Work | 2008-01-09 | 2008-12-01 | 2025-09-21 | 2025-10-21 | 2025-11-20 | 2025-12-05 | 2025-12-20 | 2026-01-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK01-P0LB-122074 | HRSG - MANUAL VALVE ASSEMBLY DRAWING FOR EXTERNAL PIPING | ASSEMBLY DRAWING | Heat Recovery Steam Generator | Piping |  |  | ASSEMBLY DRAWING for HRSG |  | FA | 3PF1650W52A02.1P | (HRSG #32 Insulation) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Piping Work | 2008-01-09 | 2008-12-01 | 2025-10-23 | 2025-11-22 | 2025-12-22 | 2026-01-06 | 2026-01-21 | 2026-02-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0LB-122075 | HRSG - INSTRUMENT LIST | LIST | Heat Recovery Steam Generator |  |  |  | LIST for HRSG |  | FA | 1PF1600W90A10P | (HRSG #11 LEB) P.O & Procurement - I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | 2007-09-15 | 2008-07-10 | 2025-02-11 | 2025-03-13 | 2025-04-12 | 2025-04-27 | 2025-05-12 | 2025-05-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0LB-122076 | HRSG - INSTRUMENT LIST FOR DUCT BURNER SYSTEM | LIST | Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | LIST for HRSG |  | FA | 1PF1615W64A06P | (HRSG #11 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | 2007-06-14 | 2008-01-31 | 2024-11-10 | 2024-12-10 | 2025-01-09 | 2025-01-24 | 2025-02-08 | 2025-02-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0LB-122077 | HRSG - ALARM AND TRIP SETTING LIST FOR DUCT BURNER SYSTEM | LIST | Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | LIST for HRSG |  | FA | 1PF1615W64A06.1P | (HRSG #12 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | 2007-06-14 | 2008-01-31 | 2024-11-10 | 2024-12-10 | 2025-01-09 | 2025-01-24 | 2025-02-08 | 2025-02-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0LB-122078 | HRSG - CABLE SCHEDULE | SCHEDULE | Heat Recovery Steam Generator |  |  |  | Schedule for HRSG |  | FA | 1PF1600W74A06P | (HRSG #11 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | 2007-09-15 | 2008-07-10 | 2025-03-28 | 2025-04-27 | 2025-05-27 | 2025-06-11 | 2025-06-26 | 2025-07-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0LB-122079 | HRSG - LIGHTING PLAN DIAGRAMS | PLAN DIAGRAMS | Heat Recovery Steam Generator | Lighting |  |  | PLAN DIAGRAMS for HRSG |  | FA | 1PF1600W74A06P | (HRSG #11 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | 2007-09-15 | 2008-07-10 | 2025-03-28 | 2025-04-27 | 2025-05-27 | 2025-06-11 | 2025-06-26 | 2025-07-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0LB-122080 | HRSG - COMMUNICATION BLOCK DIAGRAM | BLOCK DIAGRAM | Heat Recovery Steam Generator | Communication System & Security System |  |  | BLOCK DIAGRAM for HRSG |  | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | 2025-01-28 | 2025-02-27 | 2025-03-29 | 2025-04-13 | 2025-04-28 | 2025-05-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-US02-P0LB-122081 | HRSG - COMMUNICATION LAYOUT DRAWING | LAYOUT DRAWING | Heat Recovery Steam Generator | Communication System & Security System |  |  | Layout Drawing for HRSG |  | FA | 1PF1665W42A12.1P | (HRSG #12 MECH Vendor Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Auxiliary System | 2007-09-10 | 2008-08-01 | 2025-05-23 | 2025-06-22 | 2025-07-22 | 2025-08-06 | 2025-08-21 | 2025-09-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YR01-P0LB-122082 | HRSG - CHEMICAL CLEANING PROCEDURE | PROCEDURE | Heat Recovery Steam Generator |  |  |  | PROCEDURE for HRSG |  | FA | 1CF1640W60A07 | (HRSG #11) Acid Cleaning | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Piping Work | 2009-01-26 | 2009-02-17 | 2026-07-10 | 2026-08-09 | 2026-09-08 | 2026-09-23 | 2026-10-08 | 2026-10-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL08-P0LB-122083 | HRSG - PRESERVATION AND STORAGE PROCEDURE | PROCEDURE | Heat Recovery Steam Generator |  |  |  | PROCEDURE for HRSG |  | FA | 1PF1600W90A10.1P | (HRSG #12 LEB) P.O & Procurement - I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | 2007-09-15 | 2008-07-10 | 2025-02-26 | 2025-03-28 | 2025-04-27 | 2025-05-12 | 2025-05-27 | 2025-06-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0LB-122084 | HRSG - PANEL ELECTRIC SCHEME FOR DUCT BURNER SYSTEM | ELECTRIC SCHEME | Heat Recovery Steam Generator | DUCT BURNER SYSTEM |  |  | ELECTRIC SCHEME for HRSG |  | FA | 1PF1615W64A06.1P | (HRSG #12 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | 2007-06-14 | 2008-01-31 | 2024-11-25 | 2024-12-25 | 2025-01-24 | 2025-02-08 | 2025-02-23 | 2025-03-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0LB-122085 | HRSG - WIRING & SCHEMATIC DIAGRAM | WIRING & SCHEMATIC DIAGRAM | Heat Recovery Steam Generator |  |  |  | WIRING & SCHEMATIC DIAGRAM for HRSG |  | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | 2024-11-28 | 2024-12-28 | 2025-01-27 | 2025-02-11 | 2025-02-26 | 2025-03-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YQ03-P0LB-122086 | HRSG - DATA & BOM OF INSULATION FOR BLOWDOWN TANK | DATA & BOM | Heat Recovery Steam Generator |  |  |  | DATA & BOM for HRSG |  | FA | 1PF1650W52A02P | (HRSG #11 Insulation) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Piping Work | 2008-01-09 | 2008-09-30 | 2025-11-22 | 2025-12-22 | 2026-01-21 | 2026-02-05 | 2026-02-20 | 2026-03-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YQ03-P0LB-122087 | HRSG - DATA & BOM OF INSULATION FOR INTERNAL PIPING | DATA & BOM | Heat Recovery Steam Generator | Piping |  |  | DATA & BOM for HRSG |  | FA | 1PF1650W52A02P | (HRSG #11 Insulation) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Piping Work | 2008-01-09 | 2008-09-30 | 2025-11-22 | 2025-12-22 | 2026-01-21 | 2026-02-05 | 2026-02-20 | 2026-03-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YQ03-P0LB-122088 | HRSG - PERFORMANCE AND OPERATIONAL DATA | DATA | Heat Recovery Steam Generator |  |  |  | DATA for HRSG |  | FA | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-11-27 | 2024-12-27 | 2025-01-26 | 2025-02-10 | 2025-02-25 | 2025-03-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VN02-P0LB-122089 | HRSG - MOV DATASHEET & DRAWINGS | DATASHEET & DRAWINGS | Heat Recovery Steam Generator |  |  |  | DATASHEET & DRAWINGS for HRSG |  | FA | 1PF1615W64A06.1P | (HRSG #12 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | 2007-06-14 | 2008-01-31 | 2025-02-24 | 2025-03-26 | 2025-04-25 | 2025-05-10 | 2025-05-25 | 2025-06-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VN02-P0LB-122090 | HRSG - CV DATASHEET & DRAWINGS | DATASHEET & DRAWINGS | Heat Recovery Steam Generator |  |  |  | DATASHEET & DRAWINGS for HRSG |  | FA | 1PF1615W64A06.1P | (HRSG #12 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | 2007-06-14 | 2008-01-31 | 2025-02-24 | 2025-03-26 | 2025-04-25 | 2025-05-10 | 2025-05-25 | 2025-06-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0LB-122091 | HRSG - DESH. DATASHEET & DRAWINGS | DATASHEET & DRAWINGS | Heat Recovery Steam Generator |  |  |  | DATASHEET & DRAWINGS for HRSG |  | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | 2025-02-24 | 2025-03-26 | 2025-04-25 | 2025-05-10 | 2025-05-25 | 2025-06-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0LB-122092 | HRSG - AIRCRAFT WARNING LIGHT DATASHEET & LAYOUT DIAGRAM | DATASHEET & LAYOUT DIAGRAM | Heat Recovery Steam Generator |  |  |  | DATASHEET & LAYOUT DIAGRAM for HRSG |  | FA | 1PF1600W74A06.1P | (HRSG #12 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | 2007-09-15 | 2008-07-10 | 2025-03-28 | 2025-04-27 | 2025-05-27 | 2025-06-11 | 2025-06-26 | 2025-07-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122093 | HRSG - CEMS DATASHEET & DRAWINGS | DATASHEET & DRAWINGS | Heat Recovery Steam Generator |  |  |  | DATASHEET & DRAWINGS for HRSG |  | FA | 1PF1660W86A04P | (CEMS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > CEMS | 2007-08-29 | 2008-03-31 | 2025-05-11 | 2025-06-10 | 2025-07-10 | 2025-07-25 | 2025-08-09 | 2025-08-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT02-P0LB-122094 | HRSG - LOCAL INSTRUMENT DATASHEET & DRAWINGS | DATASHEET & DRAWINGS | Heat Recovery Steam Generator |  |  |  | DATASHEET & DRAWINGS for HRSG |  | FA | 1PF1600W90A10.1P | (HRSG #12 LEB) P.O & Procurement - I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | 2007-09-15 | 2008-07-10 | 2025-05-28 | 2025-06-27 | 2025-07-27 | 2025-08-11 | 2025-08-26 | 2025-09-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122095 | HRSG - TRANSMITTER DATASHEET & DRAWINGS | DATASHEET & DRAWINGS | Heat Recovery Steam Generator |  |  |  | DATASHEET & DRAWINGS for HRSG |  | FA | 1PF1615W64A06.1P | (HRSG #12 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | 2007-06-14 | 2008-01-31 | 2025-02-24 | 2025-03-26 | 2025-04-25 | 2025-05-10 | 2025-05-25 | 2025-06-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122096 | HRSG - DRUM LEVEL GAUGE DATASHEET & DRAWINGS | DATASHEET & DRAWINGS | Heat Recovery Steam Generator |  |  |  | DATASHEET & DRAWINGS for HRSG |  | FA | 1PF1645W42A03.1P | (HRSG #12 Drum) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Drum | 2007-06-13 | 2008-04-30 | 2025-02-23 | 2025-03-25 | 2025-04-24 | 2025-05-09 | 2025-05-24 | 2025-06-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122097 | HRSG - FLOW ELEMENT DATASHEET & DRAWINGS | DATASHEET & DRAWINGS | Heat Recovery Steam Generator |  |  |  | DATASHEET & DRAWINGS for HRSG |  | FA | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-06-14 | 2008-03-03 | 2025-02-24 | 2025-03-26 | 2025-04-25 | 2025-05-10 | 2025-05-25 | 2025-06-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122098 | HRSG - REMOTE DRUM LEVEL INDICATOR DATASHEET & DRAWINGS | DATASHEET & DRAWINGS | Heat Recovery Steam Generator |  |  |  | DATASHEET & DRAWINGS for HRSG |  | FA | 1PF1645W42A03.1P | (HRSG #12 Drum) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Drum | 2007-06-13 | 2008-04-30 | 2025-02-23 | 2025-03-25 | 2025-04-24 | 2025-05-09 | 2025-05-24 | 2025-06-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122099 | HRSG - TECHNICAL SPECIFICATION FOR LIGHTING & SMALL POWER SYSTEM | TECHNICAL SPECIFICATION | Heat Recovery Steam Generator | Lighting & Small Power System |  |  | Technical Specification for HRSG |  | FA | 0EF6040W70A01 | (Lighting Equip) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System |  | 2007-05-30 | [6 empty] | missing_date |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122100 | HRSG - ELECTRICAL SINGLE LINE DIAGRAMS | SINGLE LINE DIAGRAMS | Heat Recovery Steam Generator |  |  |  | SINGLE LINE DIAGRAMS for HRSG |  | FA | 3PF1600W74A06.1P | (HRSG #32 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > HRSG LEB | 2007-09-15 | 2008-08-23 | 2025-01-23 | 2025-02-22 | 2025-03-24 | 2025-04-08 | 2025-04-23 | 2025-05-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122101 | HRSG - ILLUMINATION CALCULATION | CALCULATION | Heat Recovery Steam Generator |  |  |  | Calculation sheet for HRSG |  | FA | 1PF1600W74A06P | (HRSG #11 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | 2007-09-15 | 2008-07-10 | 2025-02-26 | 2025-03-28 | 2025-04-27 | 2025-05-12 | 2025-05-27 | 2025-06-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122102 | HRSG - I/O LIST FOR BMS AND CEMS | LIST | Heat Recovery Steam Generator |  |  |  | LIST for HRSG |  | FA | 1PF1600W90A10P | (HRSG #11 LEB) P.O & Procurement - I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | 2007-09-15 | 2008-07-10 | 2025-02-11 | 2025-03-13 | 2025-04-12 | 2025-04-27 | 2025-05-12 | 2025-05-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122103 | HRSG - ARRANGEMENT OF PARTITION PLATE & GAS BAFFLE | ARRANGEMENT | Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG |  | FA | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT02-P0LB-122104 | HRSG - PIPING MATERIAL CLASSIFICATION | CLASSIFICATION | Heat Recovery Steam Generator | Piping |  |  | CLASSIFICATION for HRSG |  | FA | 1PF1650W52A02P | (HRSG #11 Insulation) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Piping Work | 2008-01-09 | 2008-09-30 | 2025-07-22 | 2025-08-21 | 2025-09-20 | 2025-10-05 | 2025-10-20 | 2025-11-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122105 | HRSG - INSTRUMENT SPECIFICATION & DATASHEET FOR DUCT BURNER SYSTEM | SPECIFICATION & DATASHEET | Heat Recovery Steam Generator |  |  |  | SPECIFICATION & DATASHEET for HRSG |  | FA | 1PF1615W64A06.1P | (HRSG #12 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | 2007-06-14 | 2008-01-31 | 2025-01-13 | 2025-02-12 | 2025-03-14 | 2025-03-29 | 2025-04-13 | 2025-04-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122106 | HRSG - SHUT OFF AND CONTROL VALVE DATASHEET FOR DUCT BURNER SYSTEM | DATASHEET | Heat Recovery Steam Generator |  |  |  | Data Sheet for HRSG |  | FA | 3PF1615W64A10P | (HRSG #31 Damper) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2007-06-13 | 2008-05-01 | 2025-03-03 | 2025-04-02 | 2025-05-02 | 2025-05-17 | 2025-06-01 | 2025-06-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0LB-122107 | HRSG - INTERCONNECTION WIRING DIAGRAM FOR DUCT BURNER SYSTEM | INTERCONNECTION WIRING DIAGRAM | Heat Recovery Steam Generator |  |  |  | INTERCONNECTION WIRING DIAGRAM for HRSG |  | FA | 1PF1615W64A06.1P | (HRSG #12 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | 2007-06-14 | 2008-01-31 | 2024-12-25 | 2025-01-24 | 2025-02-23 | 2025-03-10 | 2025-03-25 | 2025-04-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LB-122108 | HRSG - BMS SPECIFICATION FOR DUCT BURNER SYSTEM | SPECIFICATION | Heat Recovery Steam Generator |  |  |  | Technical Specification for HRSG |  | FA | 1PF1615W64A06.1P | (HRSG #12 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | 2007-06-14 | 2008-01-31 | 2024-11-25 | 2024-12-25 | 2025-01-24 | 2025-02-08 | 2025-02-23 | 2025-03-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LB-122109 | HRSG - UNDERGROUND EARTHING CABLE LAYOUT DRAWING | LAYOUT DRAWING | Heat Recovery Steam Generator | Earthing & Lightning Protection System |  |  | Layout Drawing for HRSG |  | FA | 1PF1600W74A06P | (HRSG #11 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | 2007-09-15 | 2008-07-10 | 2025-05-28 | 2025-06-27 | 2025-07-27 | 2025-08-11 | 2025-08-26 | 2025-09-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0LB-122110 | HRSG - STRENGTH CALCULATION REPORT FOR STEEL STRUCTURE | CALCULATION REPORT | Heat Recovery Steam Generator |  |  |  | CALCULATION REPORT for HRSG |  | FA | 1PF1610W20A03P | (HRSG #11 S/Structure & Casing) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Steel Structure & Casing | 2007-06-14 | 2008-01-01 | 2025-02-24 | 2025-03-26 | 2025-04-25 | 2025-05-10 | 2025-05-25 | 2025-06-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UE00-P0LB-122111 | HRSG – PERPENDICULAR BAFFLE AND TIE PLATE ASSY DRAWINGS | DRAWINGS | Heat Recovery Steam Generator |  |  |  | DRAWINGS for HRSG |  | FA | 3PF1600W90A10.1P | (HRSG #32 LEB) P.O & Procurement - I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > HRSG LEB | 2007-09-15 | 2008-08-23 | 2025-01-27 | 2025-02-26 | 2025-03-28 | 2025-04-12 | 2025-04-27 | 2025-05-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0GM-122112 | HRSG – DRAIN FLOW DIAGRAM | FLOW DIAGRAM | Heat Recovery Steam Generator | Drain System |  |  | FLOW DIAGRAM for HRSG |  | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | 2024-08-13 | 2024-09-12 | 2024-10-12 | 2024-10-27 | 2024-11-11 | 2024-11-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MAG-123001 | ACC - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | Air Cooled Condenser |  |  |  | GENERAL ARRANGEMENT DRAWING for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2024-12-21 | 2025-01-20 | 2025-02-19 | 2025-03-06 | 2025-03-21 | 2025-04-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0MAG-123002 | ACC - P&I DIAGRAM | P&I DIAGRAM | Air Cooled Condenser |  |  |  | P&ID for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-03-16 | 2025-04-15 | 2025-05-15 | 2025-05-30 | 2025-06-14 | 2025-06-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0MAG-123004 | ACC - PERFORMANCE CURVE | PERFORMANCE CURVE | Air Cooled Condenser |  |  |  | PERFORMANCE CURVE for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-01-20 | 2025-02-19 | 2025-03-21 | 2025-04-05 | 2025-04-20 | 2025-05-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0MAG-123005 | ACC - EQUIPMENT LIST | EQUIPMENT LIST | Air Cooled Condenser |  |  |  | EQUIPMENT LIST for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-01-10 | 2025-02-09 | 2025-03-11 | 2025-03-26 | 2025-04-10 | 2025-04-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VN02-P0MAG-123006 | ACC - FAN SPECIFICATION | SPECIFICATION | Air Cooled Condenser |  |  |  | Technical Specification for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-03-21 | 2025-04-20 | 2025-05-20 | 2025-06-04 | 2025-06-19 | 2025-07-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0MAG-123007 | ACC - CONDENSATE COLLECTING TANK OUTLINE DRAWING | OUTLINE DRAWING | Air Cooled Condenser |  |  |  | Outline Drawing for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-04-20 | 2025-05-20 | 2025-06-19 | 2025-07-04 | 2025-07-19 | 2025-08-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XK00-P0MAG-123008 | ACC - GEARBOX DATASHEET | DATASHEET | Air Cooled Condenser |  |  |  | Data Sheet for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2024-12-12 | 2025-01-11 | 2025-02-10 | 2025-02-25 | 2025-03-12 | 2025-03-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XK00-P0MAG-123009 | ACC - FAN MOTOR DATA SHEET | DATA SHEET | Air Cooled Condenser |  |  |  | Data Sheet for ACC |  | FA | 3EF3020W00A15 | (COND) Condenser Design Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condenser | 2007-03-01 | 2007-04-12 | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0MAG-123010 | ACC - CONDENSATE DRAIN PUMP SPECIFICATION | SPECIFICATION | Air Cooled Condenser |  |  |  | Technical Specification for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-03-21 | 2025-04-20 | 2025-05-20 | 2025-06-04 | 2025-06-19 | 2025-07-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DH02-P0MAG-123011 | ACC - SJAE DATASHEET | DATASHEET | Air Cooled Condenser |  |  |  | Data Sheet for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2024-12-12 | 2025-01-11 | 2025-02-10 | 2025-02-25 | 2025-03-12 | 2025-03-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MAJ-123012 | ACC - CLEANING WATER PUMP DATASHEET | DATASHEET | Air Cooled Condenser |  |  |  | Data Sheet for ACC |  | FA | 1PF3020W42A02P | (CTCS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser Tube Cleaning System | 2007-10-31 | 2008-09-01 | 2025-01-09 | 2025-02-08 | 2025-03-10 | 2025-03-25 | 2025-04-09 | 2025-04-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XR00-P0MAG-123013 | ACC - ELECTRICAL LIFTING HOIST DATASHEET | DATASHEET | Air Cooled Condenser |  |  |  | Data Sheet for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2024-12-12 | 2025-01-11 | 2025-02-10 | 2025-02-25 | 2025-03-12 | 2025-03-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MAG-123014 | ACC - MANUAL VALVE LIST | LIST | Air Cooled Condenser |  |  |  | LIST for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-02-17 | 2025-03-19 | 2025-04-18 | 2025-05-03 | 2025-05-18 | 2025-06-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0MAG-123015 | ACC - MANUAL VALVE OUTLINE DRAWING | OUTLINE DRAWING | Air Cooled Condenser |  |  |  | Outline Drawing for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-04-20 | 2025-05-20 | 2025-06-19 | 2025-07-04 | 2025-07-19 | 2025-08-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0MAG-123016 | ACC - PIPING ARRANGEMENT DRAWING | ARRANGEMENT DRAWING | Air Cooled Condenser | Piping |  |  | General Arrangement Drawing for ACC |  | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | 2024-06-17 | 2024-07-17 | 2024-08-16 | 2024-08-31 | 2024-09-15 | 2024-09-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0MAG-123017 | ACC - PIPING ISOMETRIC DRAWING | ISOMETRIC DRAWING | Air Cooled Condenser | Piping |  |  | Isometric Drawing for ACC |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-12-03 | 2025-01-02 | 2025-02-01 | 2025-02-16 | 2025-03-03 | 2025-03-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0MAG-123019 | ACC - LINE LIST | LINE LIST | Air Cooled Condenser |  |  |  | LINE LIST for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-02-17 | 2025-03-19 | 2025-04-18 | 2025-05-03 | 2025-05-18 | 2025-06-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0MAG-123020 | ACC - STEEL STRUCTURE SPECIFICATION | SPECIFICATION | Air Cooled Condenser |  |  |  | Technical Specification for ACC |  | FA | 1PF1610W20A03.1P | (HRSG #12 S/Structure & Casing) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Steel Structure & Casing | 2007-06-14 | 2008-01-31 | 2024-11-30 | 2024-12-30 | 2025-01-29 | 2025-02-13 | 2025-02-28 | 2025-03-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XL00-P0MAG-123021 | ACC - FOUNDATION DRAWINGS / CIVIL LOADING DATA | DRAWINGS | Air Cooled Condenser |  |  |  | DRAWINGS for ACC |  | FA | 0EF3510W00A17 | (COMP Air BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 |  | 2024-10-19 | 2024-11-18 | 2024-12-18 | 2025-01-02 | 2025-01-17 | 2025-02-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VN02-P0MAG-123022 | ACC - EMBEDDED MATERIAL SPECIFICATION | SPECIFICATION | Air Cooled Condenser |  |  |  | Technical Specification for ACC |  | FA | 1EF3020W42A05 | (COND Air EXT Equip) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser |  | 2007-07-02 | [6 empty] | missing_date |  | 6210
Fadhili_MDL.xlsx | T16182-XB00-P0MAG-123023 | ACC - ELECTRICAL LOAD LIST | LOAD LIST | Air Cooled Condenser | Electrical System |  |  | LOAD LIST for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-01-20 | 2025-02-19 | 2025-03-21 | 2025-04-05 | 2025-04-20 | 2025-05-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YM01-P0MAG-123025 | ACC - MOTOR THERMAL LIMIT CURVE | CURVE | Air Cooled Condenser |  |  |  | CURVE for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-01-20 | 2025-02-19 | 2025-03-21 | 2025-04-05 | 2025-04-20 | 2025-05-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0MAG-123026 | ACC - SPEED - TORQUE & CURRENT CURVE | CURVE | Air Cooled Condenser |  |  |  | CURVE for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-01-20 | 2025-02-19 | 2025-03-21 | 2025-04-05 | 2025-04-20 | 2025-05-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XK00-P0MAG-123027 | ACC - FUNCTIONAL DESCRIPTION | FUNCTIONAL DESCRIPTION | Air Cooled Condenser |  |  |  | FUNCTIONAL DESCRIPTION for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-02-20 | 2025-03-22 | 2025-04-21 | 2025-05-06 | 2025-05-21 | 2025-06-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YM02-P0MAG-123029 | ACC - CONTROL LOGIC & LOOP DIAGRAM | CONTROL LOGIC & LOOP DIAGRAM | Air Cooled Condenser | control system |  |  | CONTROL LOGIC & LOOP DIAGRAM for ACC |  | FA | 3SF1265W62A18 | (Control Oil) Loop chek | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Auxiliary System | 2008-07-16 | 2008-07-20 | 2026-02-01 | 2026-03-03 | 2026-04-02 | 2026-04-17 | 2026-05-02 | 2026-05-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YR04-P0MAG-123030 | ACC - I&C WIRING DIAGRAMS | WIRING DIAGRAMS | Air Cooled Condenser | Instrumentation & Control |  |  | WIRING DIAGRAMS for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-07-19 | 2025-08-18 | 2025-09-17 | 2025-10-02 | 2025-10-17 | 2025-11-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0MAG-123031 | ACC - INSTRUMENT LIST | LIST | Air Cooled Condenser | Instrument |  |  | LIST for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-02-17 | 2025-03-19 | 2025-04-18 | 2025-05-03 | 2025-05-18 | 2025-06-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0MAG-123032 | ACC - INSTRUMENT DATASHEET | DATASHEET | Air Cooled Condenser | Instrument |  |  | Data Sheet for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2024-12-12 | 2025-01-11 | 2025-02-10 | 2025-02-25 | 2025-03-12 | 2025-03-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YV02-P0MAG-123033 | ACC - INSTRUMENT DRAWING | DRAWING | Air Cooled Condenser | Instrument |  |  | DRAWING for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-04-20 | 2025-05-20 | 2025-06-19 | 2025-07-04 | 2025-07-19 | 2025-08-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0MAG-123034 | ACC - INSTRUMENT CALIBRATION SHEET | CALIBRATION SHEET | Air Cooled Condenser | Instrument |  |  | CALIBRATION SHEET for ACC |  | FA | 1SF3520W62A14 | (FGSS #12) Metering System Calibration with supplier | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System | 2008-09-24 | 2008-09-28 | 2025-11-20 | 2025-12-20 | 2026-01-19 | 2026-02-03 | 2026-02-18 | 2026-03-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT02-P0MAG-123035 | ACC - INSTRUMENTATION HOOK - UP DRAWING | HOOK - UP DRAWING | Air Cooled Condenser | Instrument |  |  | HOOK - UP DRAWING for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-04-20 | 2025-05-20 | 2025-06-19 | 2025-07-04 | 2025-07-19 | 2025-08-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MAG-123036 | ACC-MOTORISED VALVE SPECIFICATION | SPECIFICATION | Air Cooled Condenser |  |  |  | Technical Specification for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-03-21 | 2025-04-20 | 2025-05-20 | 2025-06-04 | 2025-06-19 | 2025-07-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0MAG-123037 | ACC - I&C JB OUTLINE AND LAYOUT DRAWING | DRAWING | Air Cooled Condenser | Instrumentation & Control |  |  | DRAWING for ACC |  | FA | 1CF3020W90A25 | (COND System) Installation & Test - I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-09-23 | 2008-12-17 | 2026-04-11 | 2026-05-11 | 2026-06-10 | 2026-06-25 | 2026-07-10 | 2026-07-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MAG-123038 | ACC - TERMINAL POINT LIST | LIST | Air Cooled Condenser |  |  |  | LIST for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-02-17 | 2025-03-19 | 2025-04-18 | 2025-05-03 | 2025-05-18 | 2025-06-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MAG-123039 | ACC - UTILITY CONSUMPTION LIST | LIST | Air Cooled Condenser |  |  |  | LIST for ACC |  | FA | 1EF3020W00A16 | (COND) Utility Consumption Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-03-01 | 2007-04-26 | 2024-07-16 | 2024-08-15 | 2024-09-14 | 2024-09-29 | 2024-10-14 | 2024-10-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VN01-P0MAG-123045 | ACC ERECTION DRAWING | DRAWING | Air Cooled Condenser |  |  |  | DRAWING for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-04-20 | 2025-05-20 | 2025-06-19 | 2025-07-04 | 2025-07-19 | 2025-08-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VN01-P0MAG-123046 | ACC REFERENCE DRAWING | DRAWING | Air Cooled Condenser |  |  |  | DRAWING for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-04-20 | 2025-05-20 | 2025-06-19 | 2025-07-04 | 2025-07-19 | 2025-08-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VN01-P0MAG-123047 | ACC ERECTION MANUAL | MANUAL | Air Cooled Condenser |  |  |  | MANUAL for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-02-20 | 2025-03-22 | 2025-04-21 | 2025-05-06 | 2025-05-21 | 2025-06-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XA00-P0MAG-123048 | ACC - HOLDING EJECTOR DRAWING | DRAWING | Air Cooled Condenser |  |  |  | DRAWING for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-04-20 | 2025-05-20 | 2025-06-19 | 2025-07-04 | 2025-07-19 | 2025-08-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XA00-P0MAG-123049 | ACC - HOGGING EJECTOR DRAWING | DRAWING | Air Cooled Condenser |  |  |  | DRAWING for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-04-20 | 2025-05-20 | 2025-06-19 | 2025-07-04 | 2025-07-19 | 2025-08-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VN01-P0MAG-123050 | ACC - WINDWALL DRAWING | DRAWING | Air Cooled Condenser |  |  |  | DRAWING for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-04-20 | 2025-05-20 | 2025-06-19 | 2025-07-04 | 2025-07-19 | 2025-08-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MAG-123051 | ACC CABLE TRAY LAYOUT DRAWING | LAYOUT DRAWING | Air Cooled Condenser |  |  |  | Layout Drawing for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-05-20 | 2025-06-19 | 2025-07-19 | 2025-08-03 | 2025-08-18 | 2025-09-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-123052 | ACC_LIGHTING & SMALL POWER LAYOUT DRAWING | LAYOUT DRAWING | Air Cooled Condenser | Lighting & Small Power System |  |  | Layout Drawing for ACC |  | FA | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | 2025-03-18 | 2025-04-17 | 2025-05-17 | 2025-06-01 | 2025-06-16 | 2025-07-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DS00-P0MAG-123053 | ACC – CLEANING PROCEDURE | PROCEDURE | Air Cooled Condenser |  |  |  | PROCEDURE for ACC |  | FA | 1PF3020W42A02P | (CTCS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser Tube Cleaning System | 2007-10-31 | 2008-09-01 | 2025-03-20 | 2025-04-19 | 2025-05-19 | 2025-06-03 | 2025-06-18 | 2025-07-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MAG-123054 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR AIR COOLED CONDENSER | DRAWING | Balance of Plant |  |  |  | DRAWING for BOP |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-06-29 | 2024-07-29 | 2024-08-28 | 2024-09-12 | 2024-09-27 | 2024-10-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VN01-P0MAG-123055 | WINDWALL LOGO FOR AIR COOLED CONDENSER |  | Air Cooled Condenser |  |  |  | for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2024-12-21 | 2025-01-20 | 2025-02-19 | 2025-03-06 | 2025-03-21 | 2025-04-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG01-P0EKG-124001 | FGS - FUEL GAS SYSTEM GENERAL LAYOUT DRAWING | DRAWING |  | Fuel Gas System |  |  | DRAWING for Fuel Gas System | Fuel Gas System | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | 2024-09-04 | 2024-10-30 | 2024-12-25 | 2024-11-20 | 2025-01-15 | 2025-03-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0EKG-124002 | FGS - P&I DIAGRAM | Piping & Instrumentation Drawing |  | Fuel Gas System |  |  | P&ID for Fuel Gas System | Fuel Gas Compressor | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0EKG-124003 | FGS - GAS FILTER & SEPARATOR ASSEMBLY DRAWING | ASSEMBLY DRAWING |  | Fuel Gas System |  |  | ASSEMBLY DRAWING for Fuel Gas System | Fuel Gas System | FA | 1PF1265W42A03P | (Gas Final Filter & Metering Skid) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Gas Supply System | 2007-03-01 | 2008-01-30 | 2024-03-29 | 2024-06-28 | 2024-09-27 | 2024-07-19 | 2024-10-18 | 2025-01-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0EKG-124004 | FGS - GAS HEATER ASSEMBLY DRAWING | ASSEMBLY DRAWING |  | Fuel Gas System |  |  | ASSEMBLY DRAWING for Fuel Gas System | Fuel Gas System | FA | 1PF3520W42A07.2P | (Gas HTR) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Heater | 2007-07-03 | 2008-04-01 | 2024-07-31 | 2024-10-30 | 2025-01-29 | 2024-11-20 | 2025-02-19 | 2025-05-21 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0EKG-124005 | FGS - MAIN GAS PRESSURE REDUCING STATION ASSEMBLY DRAWING | ASSEMBLY DRAWING |  | Fuel Gas System |  |  | ASSEMBLY DRAWING for Fuel Gas System | Fuel Gas System | FA | 1PF3520W42A04P | (GPRS) P.O & Procurement for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-06-01 | 2008-03-31 | 2024-06-29 | 2024-09-28 | 2024-12-28 | 2024-10-19 | 2025-01-18 | 2025-04-19 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0EKG-124006 | FGS - 2ND GAS PRESSURE REDUCING STATION ASSEMBLY DRAWING | ASSEMBLY DRAWING |  | Fuel Gas System |  |  | ASSEMBLY DRAWING for Fuel Gas System | Fuel Gas System | FA | 2PF3520W42A04P | (GPRS) P.O & Procurement for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-06-01 | 2008-04-30 | 2024-06-29 | 2024-09-28 | 2024-12-28 | 2024-10-19 | 2025-01-18 | 2025-04-19 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0EKG-124007 | FGS - COLD VENT STACK ASSEMBLY DRAWING | ASSEMBLY DRAWING |  | Fuel Gas System |  |  | ASSEMBLY DRAWING for Fuel Gas System | Fuel Gas System | FA | 0PF3520W42A04.2P | (Flare cum incinerator) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Flare Cum Incinerator | 2007-06-01 | 2008-03-03 | 2024-06-29 | 2024-09-28 | 2024-12-28 | 2024-10-19 | 2025-01-18 | 2025-04-19 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0EKG-124008 | FGS - CONDENSATE COLLECTING TANK & CONDENSATE PUMP ASSEMBLY DRAWING | ASSEMBLY DRAWING |  | Fuel Gas System |  |  | ASSEMBLY DRAWING for Fuel Gas System | Fuel Gas System | FA | 0PF3520W68A04P | (Condensate Tank) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-06-29 | 2024-09-28 | 2024-12-28 | 2024-10-19 | 2025-01-18 | 2025-04-19 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0EKG-124009 | FGS - PANEL LAYOUT FOR LOCAL ELECTRICAL ROOM FOR FUEL GAS SUPPLY SYSTEM |  |  | Fuel Gas Supply System | LOCAL ELECTRICAL ROOM |  | for Fuel Gas Supply System | Fuel Gas System | FA | 0EF3520W16A02.1 | (FGS LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 | 2007-09-13 | 2024-05-29 | 2024-07-03 | 2024-08-07 | 2024-07-24 | 2024-08-28 | 2024-10-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0EKG-124010 | FGS - GAS CHROMATOGRAPH OUTLINE DRAWING | OUTLINE DRAWING |  | Fuel Gas System |  |  | Outline Drawing for Fuel Gas System | Fuel Gas System | FA | 0PF3520W42A04P | (Gas Buffer) P.O & Procurement(incl. FG Booster Comp.&Bottles) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Gas Buffer | 2007-06-01 | 2008-04-01 | 2024-06-29 | 2024-09-28 | 2024-12-28 | 2024-10-19 | 2025-01-18 | 2025-04-19 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0EKG-124011 | FGS - ESD VALVE ASSEMBLY DRAWING | ASSEMBLY DRAWING |  | Fuel Gas System |  |  | ASSEMBLY DRAWING for Fuel Gas System | Fuel Gas System | FA | 1CF3520W86A02 | (FGSS #11) ESD Valve Skid installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System | 2008-05-20 | 2008-05-30 | 2025-06-18 | 2025-09-17 | 2025-12-17 | 2025-10-08 | 2026-01-07 | 2026-04-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0EKG-124012 | FGS - CABLE ROUTE LAYOUT FOR FUEL GAS SUPPLY SYSTEM | LAYOUT |  | Fuel Gas Supply System |  |  | Layout Drawing for Fuel Gas Supply System | Fuel Gas System | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | 2024-09-04 | 2024-10-30 | 2024-12-25 | 2024-11-20 | 2025-01-15 | 2025-03-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0EKG-124013 | FGS - FOUDATION & LOADS FOR FUEL GAS SUPPLY SYSTEM |  |  | Fuel Gas Supply System |  |  | for Fuel Gas Supply System | Fuel Gas System | FA | 0EF3520W16A02.1 | (FGS LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 | 2007-09-13 | 2024-05-29 | 2024-07-03 | 2024-08-07 | 2024-07-24 | 2024-08-28 | 2024-10-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0EKG-124014 | FGS - CONTROL LOOP, LOGIC DIAGRAM FOR FUEL GAS SUPPLY SYSTEM | LOGIC DIAGRAM |  | Fuel Gas Supply System |  |  | LOGIC DIAGRAM for Fuel Gas Supply System | Fuel Gas System | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | 2024-06-07 | 2024-07-19 | 2024-08-30 | 2024-08-09 | 2024-09-20 | 2024-11-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0EKG-124015 | FGS - CABLE BLOCK DIAGRAM FOR FUEL GAS SUPPLY SYSTEM | BLOCK DIAGRAM |  | Fuel Gas Supply System |  |  | BLOCK DIAGRAM for Fuel Gas Supply System | Fuel Gas System | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | 2024-03-29 | 2024-05-03 | 2024-06-07 | 2024-05-24 | 2024-06-28 | 2024-08-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0EKG-124016 | FGS - TERMINAL BOX DRAWING FOR FUEL GAS SUPPLY SYSTEM | DRAWING |  | Fuel Gas Supply System |  |  | DRAWING for Fuel Gas Supply System | Fuel Gas System | FA | 0EF3520W16A02.1 | (FGS LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 | 2007-09-13 | 2024-09-04 | 2024-10-30 | 2024-12-25 | 2024-11-20 | 2025-01-15 | 2025-03-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0EKG-124017 | FGS - SINGLE LINE DIAGRAM FOR FUEL GAS SUPPLY SYSTEM | SINGLE LINE DIAGRAM |  | Fuel Gas Supply System |  |  | Single Line Diagram for Fuel Gas Supply System | Fuel Gas System | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | 2024-05-10 | 2024-06-21 | 2024-08-02 | 2024-07-12 | 2024-08-23 | 2024-10-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0EKG-124018 | FGS - MEASUREMENT LIST FOR FUEL GAS SUPPLY SYSTEM | LIST |  | Fuel Gas Supply System |  |  | LIST for Fuel Gas Supply System | Fuel Gas System | FI | 0EF3520W16A02.1 | (FGS LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 | 2007-09-13 | 2024-06-17 | 2024-07-17 | 2024-08-16 | 2024-08-31 | 2024-09-15 | 2024-09-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-BX03-P0EKG-124020 | FGS - WIRING DIAGRAM FOR FUEL GAS SUPPLY SYSTEM | WIRING DIAGRAM |  | Fuel Gas Supply System |  |  | WIRING DIAGRAM for Fuel Gas Supply System | Fuel Gas System | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | 2024-06-07 | 2024-07-19 | 2024-08-30 | 2024-08-09 | 2024-09-20 | 2024-11-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0EKG-124021 | FGS - VALVE LIST | LIST |  | Fuel Gas System |  |  | LIST for Fuel Gas System | Fuel Gas System | FI | 0EF6020W00A05 | (BOP Piping) Valve List | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-04-30 | 2008-01-03 | 2024-07-23 | 2024-09-03 | 2024-10-15 | 2024-09-24 | 2024-11-05 | 2024-12-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YV02-P0EKG-124022 | FGS - VALVE DATA SHEET | DATA SHEET |  | Fuel Gas System |  |  | Data Sheet for Fuel Gas System | Fuel Gas System | FA | 0EF6050W00A01.1 | (Safety Valve) Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-04-30 | 2007-07-13 | 2024-07-09 | 2024-08-27 | 2024-10-15 | 2024-09-17 | 2024-11-05 | 2024-12-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0EKG-124023 | FGS - BUFFER TANK OUTLINE DRAWING | OUTLINE DRAWING |  | Fuel Gas System |  |  | Outline Drawing for Fuel Gas System | Fuel Gas System | FA | 0PF3520W42A04P | (Gas Buffer) P.O & Procurement(incl. FG Booster Comp.&Bottles) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Gas Buffer | 2007-06-01 | 2008-04-01 | 2024-06-29 | 2024-09-28 | 2024-12-28 | 2024-10-19 | 2025-01-18 | 2025-04-19 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124024 | FGS - BOOSTER COMPRESSOR OUTLINE DRAWING | OUTLINE DRAWING |  | Fuel Gas System |  |  | Outline Drawing for Fuel Gas System | Fuel Gas System | FA | 0PF3520W42A04P | (Gas Buffer) P.O & Procurement(incl. FG Booster Comp.&Bottles) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Gas Buffer | 2007-06-01 | 2008-04-01 | 2024-06-29 | 2024-09-28 | 2024-12-28 | 2024-10-19 | 2025-01-18 | 2025-04-19 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0EKG-124025 | FGS - GAS HEATER DATA SHEET | DATA SHEET |  | Fuel Gas System |  |  | Data Sheet for Fuel Gas System | Fuel Gas System | FA | 1PF3520W42A07.2P | (Gas HTR) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Heater | 2007-07-03 | 2008-04-01 | 2024-09-11 | 2024-10-30 | 2024-12-18 | 2024-11-20 | 2025-01-08 | 2025-02-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0EKG-124026 | FGS - MAIN GAS PRESSURE REDUCING STATION DATA SHEET | DATA SHEET |  | Fuel Gas System |  |  | Data Sheet for Fuel Gas System | Fuel Gas System | FA | 1PF3520W42A04P | (GPRS) P.O & Procurement for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-06-01 | 2008-03-31 | 2024-08-10 | 2024-09-28 | 2024-11-16 | 2024-10-19 | 2024-12-07 | 2025-01-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124027 | FGS - 2ND GAS PRESSURE REDUCING STATION DATA SHEET | DATA SHEET |  | Fuel Gas System |  |  | Data Sheet for Fuel Gas System | Fuel Gas System | FA | 2PF3520W42A04P | (GPRS) P.O & Procurement for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-06-01 | 2008-04-30 | 2024-08-10 | 2024-09-28 | 2024-11-16 | 2024-10-19 | 2024-12-07 | 2025-01-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124028 | FGS - COLD VENT STACK DATA SHEET | DATA SHEET |  | Fuel Gas System |  |  | Data Sheet for Fuel Gas System | Fuel Gas System | FA | 0EF3520W00A02 | (FGSS) FGSS Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-01 | 2007-03-30 | 2024-05-10 | 2024-06-28 | 2024-08-16 | 2024-07-19 | 2024-09-06 | 2024-10-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124029 | FGS - CONDENSATE COLLECTING TANK & CONDENSATE PUMP DATA SHEET | DATA SHEET |  | Fuel Gas System |  |  | Data Sheet for Fuel Gas System | Fuel Gas System | FA | 0EF3520W16A01.1 | (Condensate Tank & Pump) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2007-10-11 | 2024-08-10 | 2024-09-28 | 2024-11-16 | 2024-10-19 | 2024-12-07 | 2025-01-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124030 | FGS - GAS CHROMATOGRAPH DATA SHEET | DATA SHEET |  | Fuel Gas System |  |  | Data Sheet for Fuel Gas System | Fuel Gas System | FA | 0EF3520W00A02 | (FGSS) FGSS Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-01 | 2007-03-30 | 2024-05-10 | 2024-06-28 | 2024-08-16 | 2024-07-19 | 2024-09-06 | 2024-10-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124031 | FGS - ESD VALVE DATA SHEET | DATA SHEET |  | Fuel Gas System |  |  | Data Sheet for Fuel Gas System | Fuel Gas System | FA | 1CF3520W86A02 | (FGSS #11) ESD Valve Skid installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System | 2008-05-20 | 2008-05-30 | 2025-07-30 | 2025-09-17 | 2025-11-05 | 2025-10-08 | 2025-11-26 | 2026-01-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124032 | FGS - BOOSTER COMPRESSOR DATA SHEET | DATA SHEET |  | Fuel Gas System |  |  | Data Sheet for Fuel Gas System | Fuel Gas System | FA | 0PF3520W42A04P | (Gas Buffer) P.O & Procurement(incl. FG Booster Comp.&Bottles) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Gas Buffer | 2007-06-01 | 2008-04-01 | 2024-08-10 | 2024-09-28 | 2024-11-16 | 2024-10-19 | 2024-12-07 | 2025-01-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124033 | FGS - BUFFER TANK DATA SHEET | DATA SHEET |  | Fuel Gas System |  |  | Data Sheet for Fuel Gas System | Fuel Gas System | FA | 0PF3520W42A04P | (Gas Buffer) P.O & Procurement(incl. FG Booster Comp.&Bottles) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Gas Buffer | 2007-06-01 | 2008-04-01 | 2024-08-10 | 2024-09-28 | 2024-11-16 | 2024-10-19 | 2024-12-07 | 2025-01-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CH01-P0EKG-124039 | INSTALLATION & ERECTION MANUAL | INSTALLATION & ERECTION MANUAL |  |  |  |  | INSTALLATION & ERECTION MANUAL |  | FI | 0PF6050W86A03.0T | (Manual Valve) Transportation for Early Power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Manual Valve | 2008-03-01 | 2008-04-15 | 2024-11-23 | 2024-12-23 | 2025-01-22 | 2025-02-06 | 2025-02-21 | 2025-03-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124040 | FGS_DATASHEET AND OUTLINE DRAWING FOR GTG INLET STRAINERS | DATASHEET AND OUTLINE DRAWING | Gas Turbine Generator | Fuel Gas System |  |  | DATASHEET AND OUTLINE DRAWING for GTG |  | FA | 1PF1265W64A01.1P | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Air and Flue Gas System | 2007-03-01 | 2008-01-31 | 2024-05-24 | 2024-06-23 | 2024-07-23 | 2024-08-07 | 2024-08-22 | 2024-09-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS02-P0EKG-124048 | CABLE CONNECTION DIAGRAM | DIAGRAM |  |  |  |  | Diagram |  | FA | 1PF6040W74A06P | (EHV Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2008-02-29 | 2024-09-27 | 2024-10-27 | 2024-11-26 | 2024-12-11 | 2024-12-26 | 2025-01-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UB01-P0EKG-124075 | FGS - FUNCTIONAL DESCRIPTION | FUNCTIONAL DESCRIPTION |  | Fuel Gas System |  |  | FUNCTIONAL DESCRIPTION for Fuel Gas System | Fuel Gas System | FA | 2PF1250W42A06P | (Lube Oil System) P.O & Procurement_Lube oil functional Module | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Lube Oil System | 2007-03-30 | 2008-02-28 | 2024-06-08 | 2024-07-06 | 2024-08-03 | 2024-07-27 | 2024-08-24 | 2024-09-21 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0EKG-124077 | FGS – ISO DRAWING | ISO DRAWING |  | Fuel Gas System |  |  | ISO DRAWING for Fuel Gas System | Fuel Gas System | FA | 1PF1265W42A02.6P | (Fuel oil injection System) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Oil Injection System | 2007-03-01 | 2008-02-29 | 2024-07-19 | 2024-09-13 | 2024-11-08 | 2024-10-04 | 2024-11-29 | 2025-01-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL30-P0EKG-124078 | FGS – SALES GAS CONTROL VALVE STATION DOCUMENT & DRAWING | DOCUMENT & DRAWING |  | Fuel Gas System |  |  | DOCUMENT & DRAWING for Fuel Gas System | Fuel Gas System | FA | 1SF1265W62A11.0 | (FGSS) Gas Receiving upto GT Final Control Valve | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Gas Supply System | 2008-09-22 | 2008-09-24 | 2025-10-21 | 2026-01-20 | 2026-04-21 | 2026-02-10 | 2026-05-12 | 2026-08-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0EKG-124079 | FGS – DUPLEX STRAINER INSTRUMENT DATA & DRAWING | DATA & DRAWING |  | Fuel Gas System |  |  | DATA & DRAWING for Fuel Gas System | Fuel Gas System | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | 2024-06-12 | 2024-09-11 | 2024-12-11 | 2024-10-02 | 2025-01-01 | 2025-04-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DN04-P0EKG-124161 | INSULATION PROCEDURE FOR FGSS AREA AND HEATER SKIDS | PROCEDURE |  | Fuel Gas Supply System |  |  | PROCEDURE for Fuel Gas Supply System | Fuel Gas System | FA | 1PF3520W42A07.2P | (Gas HTR) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Heater | 2007-07-03 | 2008-04-01 | 2024-11-20 | 2024-12-18 | 2025-01-15 | 2025-01-08 | 2025-02-05 | 2025-03-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0EKG-124180 | FGS - 120V TR PANEL FOR GAS CHROMATOGRAPH |  |  | Fuel Gas System |  |  | for Fuel Gas System | Fuel Gas System | FA | 1PF3520W42A04P | (GPRS) P.O & Procurement for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-06-01 | 2008-03-31 | 2024-06-15 | 2024-07-20 | 2024-08-24 | 2024-08-10 | 2024-09-14 | 2024-10-19 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XV00-P8ZEN-125001 | RESERVE BOILER - SUPPLY/EQUIPMENT LIST | LIST | RESERVE BOILER |  |  |  | LIST for RESERVE BOILER | Boiler Feed Pump | FI | 1PF1665W42A02P | (HRSG #11 MECH Vendor Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | 2007-09-10 | 2008-08-01 | 2024-12-03 | 2025-01-02 | 2025-02-01 | 2025-02-16 | 2025-03-03 | 2025-03-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P8QHA-125002 | RESERVE BOILER - SYSTEM DESCRIPTION | SYSTEM DESCRIPTION | RESERVE BOILER |  |  |  | System Description for RESERVE BOILER |  | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | 2024-06-26 | 2024-07-26 | 2024-08-25 | 2024-09-09 | 2024-09-24 | 2024-10-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P8ZEN-125012 | RESERVE BOILER - BOILER PREDICTED PERFORMANCE DATA & CURVE | DATA & CURVE | RESERVE BOILER |  |  |  | DATA & CURVE for RESERVE BOILER | Boiler Feed Pump | FA | 0EF6050W00A01.1 | (Safety Valve) Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-04-30 | 2007-07-13 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P8ZEN-125014 | RESERVE BOILER - BOILER START - UP CURVE | CURVE | RESERVE BOILER |  |  |  | CURVE for RESERVE BOILER |  | FA | 0PF6050W86A03.1P | (Safety Valve) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-09-14 | 2008-05-23 | 2024-12-26 | 2025-01-25 | 2025-02-24 | 2025-03-11 | 2025-03-26 | 2025-04-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CQ02-P8ZEN-125019 | RESERVE BOILER_ERECTION MANUAL | ERECTION MANUAL | RESERVE BOILER |  |  |  | ERECTION MANUAL for RESERVE BOILER |  | FI | 0PF6050W86A03.0T | (Manual Valve) Transportation for Early Power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Manual Valve | 2008-03-01 | 2008-04-15 | 2024-11-23 | 2024-12-23 | 2025-01-22 | 2025-02-06 | 2025-02-21 | 2025-03-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CC00-P8QHA-125101 | RESERVE BOILER - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | RESERVE BOILER |  |  |  | GENERAL ARRANGEMENT DRAWING for RESERVE BOILER |  | FA | 0EF1000W00A03 | Plant General Arrangement | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-10-08 | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CC08-P8QHB-125151 | RESERVE BOILER - FOUNDATION LOADING DATA FOR STEEL STRUCTURE & STACK | DATA | RESERVE BOILER |  |  |  | DATA for RESERVE BOILER | Boiler Feed Pump | FI | 1EF1625W00A02 | (HRSG #11 Main Stack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | 2007-06-05 |  | 2024-09-25 | 2024-10-25 | 2024-11-24 | 2024-12-09 | 2024-12-24 | 2025-01-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XT00-P8QHB-125152 | RESERVE BOILER - ANCHOR BOLT ARRANGEMENT DRAWING FOR STEEL STRUCTURE | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | FA | 1PF1610W20A03P | (HRSG #11 S/Structure & Casing) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Steel Structure & Casing | 2007-06-14 | 2008-01-01 | 2024-11-25 | 2024-12-25 | 2025-01-24 | 2025-02-08 | 2025-02-23 | 2025-03-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XT00-P8QHB-125153 | RESERVE BOILER - ANCHOR BOLT ARRANGEMENT DRAWING FOR STACK | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | FA | 1PF1625W42A06.0P | (HRSG #11 Main Stack) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | 2007-06-04 | 2008-01-31 | 2024-11-15 | 2024-12-15 | 2025-01-14 | 2025-01-29 | 2025-02-13 | 2025-02-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CC05-P8QHB-125161 | RESERVE BOILER - DESIGN CRITERIA FOR STEEL STRUCTURE | DESIGN CRITERIA | RESERVE BOILER |  |  |  | DESIGN CRITERIA for RESERVE BOILER | Water Treatment System | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CC05-P8QHB-125162 | RESERVE BOILER - CONNECTION DETAIL DRAWING FOR STEEL STRUCTURE | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | FA | 1PF1610W20A03P | (HRSG #11 S/Structure & Casing) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Steel Structure & Casing | 2007-06-14 | 2008-01-01 | 2024-11-25 | 2024-12-25 | 2025-01-24 | 2025-02-08 | 2025-02-23 | 2025-03-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CC02-P8QHB-125164 | RESERVE BOILER - ARRANGEMENT DRAWING FOR STEEL STRUCTURE | ARRANGEMENT DRAWING | RESERVE BOILER |  |  |  | General Arrangement Drawing for RESERVE BOILER |  | FA | 1PF1610W20A03P | (HRSG #11 S/Structure & Casing) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Steel Structure & Casing | 2007-06-14 | 2008-01-01 | 2024-07-26 | 2024-08-25 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CC02-P8QHB-125172 | RESERVE BOILER - ARRANGEMENT DRAWING FOR STACK | ARRANGEMENT DRAWING | RESERVE BOILER |  |  |  | General Arrangement Drawing for RESERVE BOILER |  | FA | 1EF1625W00A02 | (HRSG #11 Main Stack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | 2007-06-05 |  | 2024-07-17 | 2024-08-16 | 2024-09-15 | 2024-09-30 | 2024-10-15 | 2024-10-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD07-P8QHA-125201 | RESERVE BOILER - PRESSURE PART ARRANGEMENT OF BOILER DRAWING | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | FA | 1PF3520W42A14P | (GPRS) P.O & Procurement for HRSG | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-07-03 | 2008-04-30 | 2024-12-14 | 2025-01-13 | 2025-02-12 | 2025-02-27 | 2025-03-14 | 2025-03-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK10-P8QHA-125202 | RESERVE BOILER - DESUPERHEATER DRAWING | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | FA | 0PF6050W86A03.1P | (Safety Valve) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-09-14 | 2008-05-23 | 2025-02-25 | 2025-03-27 | 2025-04-26 | 2025-05-11 | 2025-05-26 | 2025-06-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK10-P8QHA-125207 | RESERVE BOILER - ECONOMIZER DRAWING | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | FA | 0PF6050W86A03.1P | (Safety Valve) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-09-14 | 2008-05-23 | 2025-02-25 | 2025-03-27 | 2025-04-26 | 2025-05-11 | 2025-05-26 | 2025-06-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CC08-P8QHA-125300 | RESERVE BOILER - FOUNDATION LOADING DATA FOR BOILER PROPER | DATA | RESERVE BOILER |  |  |  | DATA for RESERVE BOILER | Boiler Feed Pump | FI | 1EF3015W00A01 | (FWS) BFP Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-05-31 | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UC02-P8QHA-125303 | RESERVE BOILER - REFRACTORY LINING PROCEDURE FOR BOILER PROPER | PROCEDURE | RESERVE BOILER |  |  |  | PROCEDURE for RESERVE BOILER | Boiler Feed Pump | FA | 0PF6050W86A04.1T | (Safety Valve) Transportation for Early Power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2008-05-24 | 2008-07-08 | 2025-04-12 | 2025-05-12 | 2025-06-11 | 2025-06-26 | 2025-07-11 | 2025-07-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UC02-P8QHA-125304 | RESERVE BOILER - INSULATION SPECIFICATION & DRAWING FOR BOILER PROPER | SPECIFICATION & DRAWING | RESERVE BOILER |  |  |  | SPECIFICATION & DRAWING for RESERVE BOILER | Boiler Feed Pump | FI | 1PF1650W52A02P | (HRSG #11 Insulation) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Piping Work | 2008-01-09 | 2008-09-30 | 2025-04-17 | 2025-05-17 | 2025-06-16 | 2025-07-01 | 2025-07-16 | 2025-07-31 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK10-P8QHA-125308 | RESERVE BOILER - NAME PLATE DRAWING OF BOILER PROPER | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | FA | 1PF2510W58A08P | (Steam PIPING) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-10-01 | 2008-05-01 | 2025-03-14 | 2025-04-13 | 2025-05-13 | 2025-05-28 | 2025-06-12 | 2025-06-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125310 | RESERVE BOILER - NAME PLATE DRAWING OF VALVE | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | FA | 0PF6050W86A03.1P | (Safety Valve) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-09-14 | 2008-05-23 | 2025-02-25 | 2025-03-27 | 2025-04-26 | 2025-05-11 | 2025-05-26 | 2025-06-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH02-P8QHL-125400 | RESERVE BOILER - GAS & AIR DUCT ARRANGEMENT DRAWING | ARRANGEMENT DRAWING | RESERVE BOILER |  |  |  | General Arrangement Drawing for RESERVE BOILER |  | FA | 3EF1615W00A01 | (HRSG #31 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2007-06-29 |  | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XA00-P8QHL-125401 | RESERVE BOILER - DAMPER DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | FA | 1PF1615W64A10P | (HRSG #11 Damper) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | 2007-06-13 | 2008-02-29 | 2024-11-24 | 2024-12-24 | 2025-01-23 | 2025-02-07 | 2025-02-22 | 2025-03-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XA00-P8QHL-125402 | RESERVE BOILER - EXPANSION JOINT DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | FA | 1PF1615W64A14P | (HRSG #11 EXP Joint & Bellows) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | 2007-06-13 | 2008-03-31 | 2024-11-24 | 2024-12-24 | 2025-01-23 | 2025-02-07 | 2025-02-22 | 2025-03-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK08-P8QHL-125403 | RESERVE BOILER - INSULATION SPECIFICATION & DRAWING FOR DUCT | SPECIFICATION & DRAWING | RESERVE BOILER |  |  |  | SPECIFICATION & DRAWING for RESERVE BOILER | Boiler Feed Pump | FI | 1PF1650W52A02P | (HRSG #11 Insulation) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Piping Work | 2008-01-09 | 2008-09-30 | 2025-04-17 | 2025-05-17 | 2025-06-16 | 2025-07-01 | 2025-07-16 | 2025-07-31 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DE00-P8ZEN-125502 | RESERVE BOILER - PMS (PIPE MATERIAL SPECIFICATION) | PMS (PIPE MATERIAL SPECIFICATION) | RESERVE BOILER |  |  |  | PMS (PIPE MATERIAL SPECIFICATION) for RESERVE BOILER | FinFan Cooler | FA | 0EF6020W00A02 | (BOP Piping) Pipe Material Specification | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-03-01 | 2008-01-28 | 2024-05-30 | 2024-06-29 | 2024-07-29 | 2024-08-13 | 2024-08-28 | 2024-09-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XN00-P8ZEN-125503 | RESERVE BOILER - LINE LIST | LINE LIST | RESERVE BOILER |  |  |  | LINE LIST for RESERVE BOILER |  | FA | 0EF6020W00A05 | (BOP Piping) Valve List | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-04-30 | 2008-01-03 | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XN00-P8ZEN-125504 | RESERVE BOILER - VALVE LIST | VALVE LIST | RESERVE BOILER |  |  |  | VALVE LIST for RESERVE BOILER |  | FA | 0EF6020W00A05 | (BOP Piping) Valve List | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-04-30 | 2008-01-03 | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XV00-P8ZEN-125505 | RESERVE BOILER - PIPING SPECIALITY DRAWING & LIST | DRAWING & LIST | RESERVE BOILER | PIPING |  |  | DRAWING & LIST for RESERVE BOILER |  | FA | 0EF6020W00A05 | (BOP Piping) Valve List | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-04-30 | 2008-01-03 | 2025-03-12 | 2025-04-11 | 2025-05-11 | 2025-05-26 | 2025-06-10 | 2025-06-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125506 | RESERVE BOILER - MANUAL VALVE DRAWING | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | FA | 0PF6050W86A02P | (Manual Valve) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Manual Valve | 2007-09-24 | 2008-02-29 | 2025-03-07 | 2025-04-06 | 2025-05-06 | 2025-05-21 | 2025-06-05 | 2025-06-20 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P8ZEN-125507 | RESERVE BOILER - PIPING & PIPING SUPPORT PLAN DRAWING | DRAWING | RESERVE BOILER | PIPING |  |  | DRAWING for RESERVE BOILER |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XK00-P8ZEN-125509 | RESERVE BOILER - PIPING SUPPORT DETAIL DRAWING FOR SMALL BORE PIPING. | DRAWING | RESERVE BOILER | PIPING |  |  | DRAWING for RESERVE BOILER |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL30-P8ZEN-125514 | RESERVE BOILER - CONTROL VALVE DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | FA | 0PF7000W86A02P | (Control Valve) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > Control Valves | 2007-10-01 | 2008-08-15 | 2025-03-14 | 2025-04-13 | 2025-05-13 | 2025-05-28 | 2025-06-12 | 2025-06-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125520 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(DEAERATOR SYSTEM) | DRAWING | RESERVE BOILER | DEAERATOR SYSTEM |  |  | DRAWING for RESERVE BOILER |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125521 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(FEEDWATER PUMP SYSTEM) | DRAWING | RESERVE BOILER | FEEDWATER PUMP SYSTEM |  |  | DRAWING for RESERVE BOILER |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125522 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(BOILER WATER SYSTEM) | DRAWING | RESERVE BOILER | BOILER WATER SYSTEM |  |  | DRAWING for RESERVE BOILER |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125523 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(BOILER STEAM SYSTEM) | DRAWING | RESERVE BOILER | BOILER STEAM SYSTEM |  |  | DRAWING for RESERVE BOILER |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125524 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(BURNER SYSTEM) | DRAWING | RESERVE BOILER | BURNER SYSTEM |  |  | DRAWING for RESERVE BOILER |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125525 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(BLOWDOWN SYSTEM) | DRAWING | RESERVE BOILER | BLOWDOWN SYSTEM |  |  | DRAWING for RESERVE BOILER |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125526 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(CLOSED COOLING WATER & SERVICE WATER SYSTEM) | DRAWING | RESERVE BOILER | CLOSED COOLING WATER & SERVICE WATER SYSTEM |  |  | DRAWING for RESERVE BOILER |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125527 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(SERVICE AIR & SEALING AIR SYSTEM) | DRAWING | RESERVE BOILER | SERVICE AIR & SEALING AIR SYSTEM |  |  | DRAWING for RESERVE BOILER |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XK00-P8ZEN-125530 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(DEAERATOR SYSTEM) | DRAWING | RESERVE BOILER | DEAERATOR SYSTEM |  |  | DRAWING for RESERVE BOILER |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XK00-P8ZEN-125531 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(FEEDWATER PUMP SYSTEM) | DRAWING | RESERVE BOILER | FEEDWATER PUMP SYSTEM |  |  | DRAWING for RESERVE BOILER |  | FA | 1EF3015W00A01 | (FWS) BFP Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-05-31 | 2024-09-13 | 2024-10-13 | 2024-11-12 | 2024-11-27 | 2024-12-12 | 2024-12-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XK00-P8ZEN-125532 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(BOILER WATER SYSTEM) | DRAWING | RESERVE BOILER | BOILER WATER SYSTEM |  |  | DRAWING for RESERVE BOILER |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XK00-P8ZEN-125533 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(BOILER STEAM SYSTEM) | DRAWING | RESERVE BOILER | BOILER STEAM SYSTEM |  |  | DRAWING for RESERVE BOILER |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XK00-P8ZEN-125534 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(BURNER SYSTEM) | DRAWING | RESERVE BOILER | BURNER SYSTEM |  |  | DRAWING for RESERVE BOILER |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XK00-P8ZEN-125535 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(BLOWDOWN SYSTEM) | DRAWING | RESERVE BOILER | BLOWDOWN SYSTEM |  |  | DRAWING for RESERVE BOILER |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XK00-P8ZEN-125536 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(CLOSED COOLING WATER & SERVICE WATER SYSTEM) | DRAWING | RESERVE BOILER | CLOSED COOLING WATER & SERVICE WATER SYSTEM |  |  | DRAWING for RESERVE BOILER |  | FA | 1CF3030W58A07 | (CCWS) Piping Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2008-06-16 | 2008-09-16 | 2025-11-28 | 2025-12-28 | 2026-01-27 | 2026-02-11 | 2026-02-26 | 2026-03-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XK00-P8ZEN-125537 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(SERVICE AIR & SEALING AIR SYSTEM) | DRAWING | RESERVE BOILER | SERVICE AIR & SEALING AIR SYSTEM |  |  | DRAWING for RESERVE BOILER |  | FA | 0EF3035W00A01.0 | (SWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-03-15 | 2007-11-21 | 2024-08-26 | 2024-09-25 | 2024-10-25 | 2024-11-09 | 2024-11-24 | 2024-12-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125540 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(DEAERATOR SYSTEM) | DRAWING | RESERVE BOILER | DEAERATOR SYSTEM |  |  | DRAWING for RESERVE BOILER |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125541 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(FEEDWATER PUMP SYSTEM) | DRAWING | RESERVE BOILER | FEEDWATER PUMP SYSTEM |  |  | DRAWING for RESERVE BOILER |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125542 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(BOILER WATER SYSTEM) | DRAWING | RESERVE BOILER | BOILER WATER SYSTEM |  |  | DRAWING for RESERVE BOILER |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125543 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(BOILER STEAM SYSTEM) | DRAWING | RESERVE BOILER | BOILER STEAM SYSTEM |  |  | DRAWING for RESERVE BOILER |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125544 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(COMBUSTION AIR & FLUE GAS SYSTEM) | DRAWING | RESERVE BOILER | COMBUSTION AIR & FLUE GAS SYSTEM |  |  | DRAWING for RESERVE BOILER |  | FA | 3PF1265W64A01P | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Air and Flue Gas System | 2007-04-30 | 2008-03-31 | 2024-10-11 | 2024-11-10 | 2024-12-10 | 2024-12-25 | 2025-01-09 | 2025-01-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125545 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(BURNER SYSTEM) | DRAWING | RESERVE BOILER | BURNER SYSTEM |  |  | DRAWING for RESERVE BOILER |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125546 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(BLOWDOWN SYSTEM) | DRAWING | RESERVE BOILER | BLOWDOWN SYSTEM |  |  | DRAWING for RESERVE BOILER |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125547 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(CHEMICAL DOSING SYSTEM) | DRAWING | RESERVE BOILER | CHEMICAL DOSING SYSTEM |  |  | DRAWING for RESERVE BOILER |  | FA | 1PF3045W42A03P | (Chemical Dosing Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-07-24 | 2025-03-09 | 2025-04-08 | 2025-05-08 | 2025-05-23 | 2025-06-07 | 2025-06-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125548 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(CLOSED COOLING WATER & SERVICE WATER SYSTEM) | DRAWING | RESERVE BOILER | CLOSED COOLING WATER & SERVICE WATER SYSTEM |  |  | DRAWING for RESERVE BOILER |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125549 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(INSTRUMENT AIR SYSTEM) | DRAWING | RESERVE BOILER | INSTRUMENT AIR SYSTEM |  |  | DRAWING for RESERVE BOILER |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125550 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(SERVICE AIR & SEALING AIR SYSTEM) | DRAWING | RESERVE BOILER | SERVICE AIR & SEALING AIR SYSTEM |  |  | DRAWING for RESERVE BOILER |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P8ZEN-125570 | RESERVE BOILER_ FUEL SKID DETAIL DRAWING | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | FA | 0PF3520W68A04P | (Condensate Tank) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-11-12 | 2024-12-12 | 2025-01-11 | 2025-01-26 | 2025-02-10 | 2025-02-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG05-P8ZEN-125571 | RESERVE BOILER - HEAT & MASS BLANCE DIAGRAM | DIAGRAM | RESERVE BOILER |  |  |  | Diagram for RESERVE BOILER |  | FA | 0EF1000W00A01 | Heat Balance Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-07-02 | 2024-11-11 | 2024-12-11 | 2025-01-10 | 2025-01-25 | 2025-02-09 | 2025-02-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125582 | RESERVE BOILER - P&ID OF DEAERATOR SYSTEM | Piping & Instrumentation Drawing | RESERVE BOILER | DEAERATOR SYSTEM |  |  | P&ID for RESERVE BOILER | Boiler Feed Pump | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125583 | RESERVE BOILER - P&ID OF FEEDWATER PUMP SYSTEM | Piping & Instrumentation Drawing | RESERVE BOILER | FEEDWATER PUMP SYSTEM |  |  | P&ID for RESERVE BOILER | Boiler Feed Pump | FA | 1EF3015W00A01 | (FWS) BFP Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-05-31 | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125584 | RESERVE BOILER - P&ID OF BOILER WATER SYSTEM | Piping & Instrumentation Drawing | RESERVE BOILER | BOILER WATER SYSTEM |  |  | P&ID for RESERVE BOILER | Boiler Feed Pump | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125585 | RESERVE BOILER - P&ID OF BOILER STEAM SYSTEM | Piping & Instrumentation Drawing | RESERVE BOILER | BOILER STEAM SYSTEM |  |  | P&ID for RESERVE BOILER | Boiler Feed Pump | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125586 | RESERVE BOILER - P&ID OF COMBUSTION AIR & FLUE GAS SYSTEM | Piping & Instrumentation Drawing | RESERVE BOILER | COMBUSTION AIR & FLUE GAS SYSTEM |  |  | P&ID for RESERVE BOILER | Boiler Feed Pump | FA | 2PF1265W64A01P | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Air and Flue Gas System | 2007-03-30 | 2008-02-29 | 2024-04-27 | 2024-05-27 | 2024-06-26 | 2024-07-11 | 2024-07-26 | 2024-08-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125587 | RESERVE BOILER - P&ID OF BURNER & FUEL GAS SYSTEM | Piping & Instrumentation Drawing | RESERVE BOILER | BURNER & Fuel Gas System |  |  | P&ID for RESERVE BOILER | Boiler Feed Pump | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125588 | RESERVE BOILER - P&ID OF BLOWDOWN SYSTEM | Piping & Instrumentation Drawing | RESERVE BOILER | BLOWDOWN SYSTEM |  |  | P&ID for RESERVE BOILER | Boiler Feed Pump | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125589 | RESERVE BOILER - P&ID OF SAMPLING SYSTEM | Piping & Instrumentation Drawing | RESERVE BOILER | SAMPLING SYSTEM |  |  | P&ID for RESERVE BOILER | Boiler Feed Pump | FA | 1EF3040W00A01 | (Sampling System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2007-04-02 | 2007-08-31 | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125590 | RESERVE BOILER - P&ID OF CHEMICAL DOSING SYSTEM | Piping & Instrumentation Drawing | RESERVE BOILER | CHEMICAL DOSING SYSTEM |  |  | P&ID for RESERVE BOILER | Boiler Feed Pump | FA | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125591 | RESERVE BOILER - P&ID OF CLOSED COOLING WATER & SERVICE WATER SYSTEM | Piping & Instrumentation Drawing | RESERVE BOILER | CLOSED COOLING WATER & SERVICE WATER SYSTEM |  |  | P&ID for RESERVE BOILER | Boiler Feed Pump | FA | 0EF3035W00A01.0 | (SWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-03-15 | 2007-11-21 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125592 | RESERVE BOILER - P&ID OF INSTRUMENT AIR SYSTEM | Piping & Instrumentation Drawing | RESERVE BOILER | INSTRUMENT AIR SYSTEM |  |  | P&ID for RESERVE BOILER | Boiler Feed Pump | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P8ZEN-125593 | RESERVE BOILER - P&ID OF SERVICE AIR & SEALING AIR SYSTEM | Piping & Instrumentation Drawing | RESERVE BOILER | SERVICE AIR & SEALING AIR SYSTEM |  |  | P&ID for RESERVE BOILER | Boiler Feed Pump | FA | 0EF3035W00A01.0 | (SWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-03-15 | 2007-11-21 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YR01-P8ZEN-125597 | METHODS STATEMENTS OF STEAM FLUSHING FOR RESERVE BOILER |  | RESERVE BOILER |  |  |  | for RESERVE BOILER | Boiler Feed Pump | FI | 0PF6050W86A03.1P | (Safety Valve) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-09-14 | 2008-05-23 | 2024-12-07 | 2025-01-06 | 2025-02-05 | 2025-02-20 | 2025-03-07 | 2025-03-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125601 | RESERVE BOILER - F.D FAN DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | FA | 1PF1265W38A01P | (F/F GTG#11) P.O & Procurement_CO2 FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fire fighting System | 2007-03-01 | 2008-03-14 | 2024-08-12 | 2024-09-11 | 2024-10-11 | 2024-10-26 | 2024-11-10 | 2024-11-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125602 | RESERVE BOILER - BURNER DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | FA | 0PF6050W86A03.1P | (Safety Valve) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-09-14 | 2008-05-23 | 2025-02-25 | 2025-03-27 | 2025-04-26 | 2025-05-11 | 2025-05-26 | 2025-06-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125604 | RESERVE BOILER - BFP DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | 2025-02-25 | 2025-03-27 | 2025-04-26 | 2025-05-11 | 2025-05-26 | 2025-06-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125605 | RESERVE BOILER - DEAERATOR WITH STORAGE TANK DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | FA | 0PF3520W68A04P | (Condensate Tank) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-11-12 | 2024-12-12 | 2025-01-11 | 2025-01-26 | 2025-02-10 | 2025-02-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125606 | RESERVE BOILER - SILENCER DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | FA | 1PF2510W42A04P | (Silencer) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-10-15 | 2008-07-15 | 2025-03-28 | 2025-04-27 | 2025-05-27 | 2025-06-11 | 2025-06-26 | 2025-07-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125607 | RESERVE BOILER - SAMPLING SYSTEM DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER | SAMPLING SYSTEM |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | FA | 1PF3040W42A05P | (Sampling Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2007-10-01 | 2008-07-30 | 2025-03-14 | 2025-04-13 | 2025-05-13 | 2025-05-28 | 2025-06-12 | 2025-06-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125608 | RESERVE BOILER - CHEMICAL DOSING SYSTEM DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER | CHEMICAL DOSING SYSTEM |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | FA | 1PF3045W42A03P | (Chemical Dosing Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-07-24 | 2025-03-09 | 2025-04-08 | 2025-05-08 | 2025-05-23 | 2025-06-07 | 2025-06-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125609 | RESERVE BOILER - MONORAIL HOIST DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2025-01-12 | 2025-02-11 | 2025-03-13 | 2025-03-28 | 2025-04-12 | 2025-04-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125610 | RESERVE BOILER - SRV DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | FA | 0PF6050W86A03.1P | (Safety Valve) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-09-14 | 2008-05-23 | 2025-02-25 | 2025-03-27 | 2025-04-26 | 2025-05-11 | 2025-05-26 | 2025-06-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125611 | RESERVE BOILER - BLOWDOWN TANK DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | FA | 0PF3520W68A04P | (Condensate Tank) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-11-12 | 2024-12-12 | 2025-01-11 | 2025-01-26 | 2025-02-10 | 2025-02-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8ZEN-125612 | RESERVE BOILER - LEVEL GAUGE DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | FA | 0PF6050W86A03.1P | (Safety Valve) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-09-14 | 2008-05-23 | 2025-02-25 | 2025-03-27 | 2025-04-26 | 2025-05-11 | 2025-05-26 | 2025-06-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CC08-P8ZEN-125614 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR F.D FAN | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | FA | 1EF3015W00A01 | (FWS) BFP Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-05-31 | 2024-09-13 | 2024-10-13 | 2024-11-12 | 2024-11-27 | 2024-12-12 | 2024-12-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CC08-P8ZEN-125615 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR BOILER FEED WATER PUMP | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | FA | 1EF3015W00A01 | (FWS) BFP Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-05-31 | 2024-09-13 | 2024-10-13 | 2024-11-12 | 2024-11-27 | 2024-12-12 | 2024-12-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CC08-P8ZEN-125616 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR FUEL SKID | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | FA | 0PF3520W68A04P | (Condensate Tank) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-11-12 | 2024-12-12 | 2025-01-11 | 2025-01-26 | 2025-02-10 | 2025-02-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CC08-P8ZEN-125617 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR SAMPLING SYSTEM | DRAWING | RESERVE BOILER | Sampling system |  |  | DRAWING for RESERVE BOILER |  | FA | 1EF3040W16A02 | (Sampling Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2008-01-01 | 2008-04-02 | 2025-06-14 | 2025-07-14 | 2025-08-13 | 2025-08-28 | 2025-09-12 | 2025-09-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CC08-P8ZEN-125618 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR CHEMICAL DOSING SYSTEM | DRAWING | RESERVE BOILER | Chemical dosing system |  |  | DRAWING for RESERVE BOILER |  | FA | 1EF3045W00A06 | (Chemical Dosing BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 |  | 2025-03-09 | 2025-04-08 | 2025-05-08 | 2025-05-23 | 2025-06-07 | 2025-06-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CC08-P8ZEN-125619 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR BLOW DOWN TANK | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | FA | 0PF3520W68A04P | (Condensate Tank) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-11-12 | 2024-12-12 | 2025-01-11 | 2025-01-26 | 2025-02-10 | 2025-02-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CC08-P8ZEN-125620 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR ELECTRICAL & CONTROL ROOM | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | FA | 1PF1600W90A10P | (HRSG #11 LEB) P.O & Procurement - I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | 2007-09-15 | 2008-07-10 | 2025-02-26 | 2025-03-28 | 2025-04-27 | 2025-05-12 | 2025-05-27 | 2025-06-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P8SGK-125650 | RESERVE BOILER_ FM GAS SYSTEM CALCULATION & DOCUMENT | CALCULATION & DOCUMENT | RESERVE BOILER | FM GAS SYSTEM |  |  | CALCULATION & DOCUMENT for RESERVE BOILER |  | FA | 0PF3520W42A04P | (Gas Buffer) P.O & Procurement(incl. FG Booster Comp.&Bottles) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Gas Buffer | 2007-06-01 | 2008-04-01 | 2024-09-05 | 2024-10-05 | 2024-11-04 | 2024-11-19 | 2024-12-04 | 2024-12-19 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS01-P8ZEN-125700 | RESERVE BOILER - OPERATION PHILOSOPHY | OPERATION PHILOSOPHY | RESERVE BOILER |  |  |  | OPERATION PHILOSOPHY for RESERVE BOILER | VFD | FA | 0EF1000W00A08 | Operational Philosophy of Overall Plant | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-06-22 | 2008-02-15 | 2024-07-20 | 2024-08-19 | 2024-09-18 | 2024-10-03 | 2024-10-18 | 2024-11-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF02-P8ZEN-125701 | RESERVE BOILER - CONTROL SYSTEM CONFIGURATION | CONFIGURATION | RESERVE BOILER | control system |  |  | CONFIGURATION for RESERVE BOILER |  | FA | 0PF7000W86A02P | (Control Valve) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > Control Valves | 2007-10-01 | 2008-08-15 | 2025-04-13 | 2025-05-13 | 2025-06-12 | 2025-06-27 | 2025-07-12 | 2025-07-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125702 | RESERVE BOILER - BMS SPECIFICATION | SPECIFICATION | RESERVE BOILER |  |  |  | Technical Specification for RESERVE BOILER |  | FA | 0EF6050W86A02.1 | (Safety Valve) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve |  | 2007-07-13 | [6 empty] | missing_date |  | 6210
Fadhili_MDL.xlsx | T16182-YL01-P8ZEN-125703 | RESERVE BOILER - BMS I/O LIST | I/O LIST | RESERVE BOILER |  |  |  | I/O LIST for RESERVE BOILER |  | FA | 0EF6020W00A05 | (BOP Piping) Valve List | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-04-30 | 2008-01-03 | 2024-10-11 | 2024-11-10 | 2024-12-10 | 2024-12-25 | 2025-01-09 | 2025-01-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL01-P8ZEN-125704 | RESERVE BOILER - BCS I/O LIST | I/O LIST | RESERVE BOILER |  |  |  | I/O LIST for RESERVE BOILER |  | FA | 0EF1000W00A09 | DCS I/O List of Overall Plant | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-12-31 | 2024-10-11 | 2024-11-10 | 2024-12-10 | 2024-12-25 | 2025-01-09 | 2025-01-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL01-P8ZEN-125705 | RESERVE BOILER - VMS I/O LIST | I/O LIST | RESERVE BOILER |  |  |  | I/O LIST for RESERVE BOILER |  | FA | 0EF6020W00A05 | (BOP Piping) Valve List | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-04-30 | 2008-01-03 | 2024-10-11 | 2024-11-10 | 2024-12-10 | 2024-12-25 | 2025-01-09 | 2025-01-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL01-P8ZEN-125706 | RESERVE BOILER - DATALINK I/O LIST | I/O LIST | RESERVE BOILER |  |  |  | I/O LIST for RESERVE BOILER |  | FA | 0EF1000W00A09 | DCS I/O List of Overall Plant | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-12-31 | 2024-10-11 | 2024-11-10 | 2024-12-10 | 2024-12-25 | 2025-01-09 | 2025-01-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL00-P8ZEN-125707 | RESERVE BOILER - INSTRUMENT LIST | LIST | RESERVE BOILER | Instrument |  |  | LIST for RESERVE BOILER | Boiler Feed Pump | FI | 0EF6020W00A05 | (BOP Piping) Valve List | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-04-30 | 2008-01-03 | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL00-P8ZEN-125708 | RESERVE BOILER - ALARM AND TRIP SETTING LIST | LIST | RESERVE BOILER |  |  |  | LIST for RESERVE BOILER | Boiler Feed Pump | FI | 0EF6020W00A05 | (BOP Piping) Valve List | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-04-30 | 2008-01-03 | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P8ZEN-125709 | RESERVE BOILER - CONTROL LOGIC DIAGRAM | CONTROL LOGIC DIAGRAM | RESERVE BOILER |  |  |  | CONTROL LOGIC DIAGRAM for RESERVE BOILER |  | FA | 1PF1265W42A12P | (Control Oil) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | 2007-03-01 | 2008-01-31 | 2024-09-11 | 2024-10-11 | 2024-11-10 | 2024-11-25 | 2024-12-10 | 2024-12-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P8ZEN-125710 | RESERVE BOILER - CONTROL LOOP DIAGRAM | CONTROL LOOP DIAGRAM | RESERVE BOILER |  |  |  | CONTROL LOOP DIAGRAM for RESERVE BOILER |  | FA | 0PF7000W86A02P | (Control Valve) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > Control Valves | 2007-10-01 | 2008-08-15 | 2025-04-13 | 2025-05-13 | 2025-06-12 | 2025-06-27 | 2025-07-12 | 2025-07-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P8ZEN-125711 | RESERVE BOILER - BMS LOGIC DIAGRAM | LOGIC DIAGRAM | RESERVE BOILER |  |  |  | LOGIC DIAGRAM for RESERVE BOILER |  | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125713 | RESERVE BOILER - MOV DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | FA | 0PF6050W86A03P | (MOV) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Motor Operation Valve | 2007-09-14 | 2008-04-30 | 2025-02-25 | 2025-03-27 | 2025-04-26 | 2025-05-11 | 2025-05-26 | 2025-06-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125714 | RESERVE BOILER - TRANSMITTER SPECIFICATION | SPECIFICATION | RESERVE BOILER | INSTRUMENT(Transmitter/gauge) |  |  | Technical Specification for RESERVE BOILER |  | FA | 0EF6050W86A02.1 | (Safety Valve) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve |  | 2007-07-13 | [6 empty] | missing_date |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125715 | RESERVE BOILER - LOCAL GAUGE SPECIFICATION | SPECIFICATION |  |  |  |  | Technical Specification |  | FA | 1PF1600W90A10P | (HRSG #11 LEB) P.O & Procurement - I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | 2007-09-15 | 2008-07-10 | 2024-09-29 | 2024-10-29 | 2024-11-28 | 2024-12-13 | 2024-12-28 | 2025-01-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125716 | RESERVE BOILER - TEMP. ELEMENT SPECIFICATION | SPECIFICATION |  |  |  |  | Technical Specification |  | FA | 1EF3030W42A01 | (Temp. Cooling Tower) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 > Temporary Cooling Tower |  | 2007-10-31 | [6 empty] | missing_date |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125717 | RESERVE BOILER - FLOW ELEMENT SPECIFICATION | SPECIFICATION |  |  |  |  | Technical Specification |  | FA | 0EF6050W86A02.1 | (Safety Valve) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve |  | 2007-07-13 | [6 empty] | missing_date |  | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125718 | RESERVE BOILER - REMOTE DRUM LEVEL INDICATOR SPECIFICATION | SPECIFICATION |  |  |  |  | Technical Specification |  | FA | 1PF1645W42A03P | (HRSG #11 Drum) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Drum | 2007-06-13 | 2008-04-30 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125719 | RESERVE BOILER - AIR OPERATED VALVE DOCUMENT & DRAWING | DOCUMENT & DRAWING |  |  |  |  | DOCUMENT & DRAWING |  | FA | 0EF6050W00A01.1 | (Safety Valve) Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-04-30 | 2007-07-13 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-31 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P8ZEN-125720 | RESERVE BOILER - INSTRUMENT INSTALLATION DETAIL DRAWING | DRAWING |  |  |  |  | DRAWING |  | FA | 0EF1000W00A10 | Instrument Installation Detail | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-05-11 | 2007-09-28 | 2024-06-22 | 2024-07-22 | 2024-08-21 | 2024-09-05 | 2024-09-20 | 2024-10-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YM03-P8ZEN-125721 | RESERVE BOILER - INSTRUMENT LOCATION DRAWING | DRAWING |  |  |  |  | DRAWING |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-06-29 | 2024-07-29 | 2024-08-28 | 2024-09-12 | 2024-09-27 | 2024-10-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P8ZEN-125722 | RESERVE BOILER - TRANSMITTER CALIBRATION SHEET | CALIBRATION SHEET |  |  |  |  | CALIBRATION SHEET |  | FA | 1SF3520W62A14 | (FGSS #12) Metering System Calibration with supplier | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System | 2008-09-24 | 2008-09-28 | 2025-11-20 | 2025-12-20 | 2026-01-19 | 2026-02-03 | 2026-02-18 | 2026-03-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P8ZEN-125723 | RESERVE BOILER - FLOW ELEMENT CALIBRATION SHEET | CALIBRATION SHEET |  |  |  |  | CALIBRATION SHEET |  | FA | 1SF3520W62A14 | (FGSS #12) Metering System Calibration with supplier | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System | 2008-09-24 | 2008-09-28 | 2025-11-20 | 2025-12-20 | 2026-01-19 | 2026-02-03 | 2026-02-18 | 2026-03-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P8ZEN-125724 | RESERVE BOILER - MONITOR SCREEN DIAGRAM | DIAGRAM |  |  |  |  | Diagram |  | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125725 | RESERVE BOILER - GAS LEAK DETECTION SYSTEM DOCUMENT & DRAWING | DOCUMENT & DRAWING |  | GAS LEAK DETECTION SYSTEM |  |  | DOCUMENT & DRAWING for GAS LEAK DETECTION SYSTEM | Fuel Gas System | FA | 1PF3520W42A04P | (GPRS) P.O & Procurement for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-06-01 | 2008-03-31 | 2024-06-29 | 2024-09-28 | 2024-12-28 | 2024-10-19 | 2025-01-18 | 2025-04-19 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125726 | RESERVE BOILER - O2 ANALYZER DOCUMENT & DRAWING | DOCUMENT & DRAWING |  |  |  |  | DOCUMENT & DRAWING |  | FA | 0EF3520W00A02.2 | (FOSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System | 2007-03-15 | 2007-10-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-YT02-P8ZEN-125727 | RESERVE BOILER - CEMS DOCUMENT & DRAWING | DOCUMENT & DRAWING |  |  |  |  | DOCUMENT & DRAWING |  | FA | 1EF1660W16A01 | (CEMS) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > CEMS | 2007-10-30 | 2008-01-25 |  |  |  | 2024-08-01 | 2024-08-31 | 2024-09-30 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P8ZEN-125728 | RESERVE BOILER - CONTROL ROOM & ELECTRICAL ROOM ARRANGEMENT DRAWING | ARRANGEMENT DRAWING |  |  | CONTROL ROOM & ELECTRICAL ROOM |  | General Arrangement Drawing for CONTROL ROOM & ELECTRICAL ROOM |  | FA | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XF00-P8ZEN-125729 | RESERVE BOILER - JUNCTION BOX DRAWING | DRAWING |  |  |  |  | DRAWING |  | FA | 1PF3020W42A12P | (COND Flash Box) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-07-01 | 2024-11-14 | 2024-12-14 | 2025-01-13 | 2025-01-28 | 2025-02-12 | 2025-02-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL16-P8ZEN-125731 | RESERVE BOILER - I&C CABLE SCHEDULE | SCHEDULE |  | Instrumentation & Control |  |  | Schedule for Instrumentation & Control |  | SKIP | 1PF1660W86A11P | (HRSG #11 I&C Vendor Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | 2007-10-02 | 2008-08-04 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P8ZEN-125732 | RESERVE BOILER - I&C CABLE CONNECTION DIAGRAM | DIAGRAM |  | Instrumentation & Control |  |  | Diagram for Instrumentation & Control | FireFighting | FA | 1PF1660W86A11P | (HRSG #11 I&C Vendor Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | 2007-10-02 | 2008-08-04 | 2025-02-19 | 2025-03-06 | 2025-03-21 | 2025-03-27 | 2025-04-11 | 2025-04-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125734 | RESERVE BOILER - BCS SPECIFICATION | SPECIFICATION |  |  |  |  | Technical Specification |  | FA | 0EF6050W86A02.1 | (Safety Valve) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve |  | 2007-07-13 | [6 empty] | missing_date |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P8ZEN-125735 | RESERVE BOILER - HAZARDOUS AREA CLASSFICATION | [7 empty] | FA | 0PF6050W86A03.1P | (Safety Valve) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-09-14 | 2008-05-23 | 2024-12-25 | 2025-01-24 | 2025-02-23 | 2025-03-10 | 2025-03-25 | 2025-04-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125737 | RESERVE BOILER _ VMS SPECIFICATION | SPECIFICATION |  |  |  |  | Technical Specification |  | FA | 0EF6050W86A01 | (Manual Valve) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Manual Valve |  | 2007-07-30 | [6 empty] | missing_date |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125749 | RESERVE BOILER - MOTOR LIST | MOTOR LIST | RESERVE BOILER |  |  |  | MOTOR LIST for RESERVE BOILER |  | FA | 0PF6050W86A03P | (MOV) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Motor Operation Valve | 2007-09-14 | 2008-04-30 | 2025-01-22 | 2025-02-21 | 2025-03-23 | 2025-04-07 | 2025-04-22 | 2025-05-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P8ZEN-125750 | RESERVE BOILER - POWER DISTRIBUTION PANEL DRAWING | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | FA | 1PF2510W58A08P | (Steam PIPING) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-10-01 | 2008-05-01 | 2025-03-14 | 2025-04-13 | 2025-05-13 | 2025-05-28 | 2025-06-12 | 2025-06-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P8ZEN-125751 | RESERVE BOILER - RACEWAY PLAN DRAWING | PLAN DRAWING | RESERVE BOILER |  |  |  | PLAN DRAWING for RESERVE BOILER |  | FA | 0PF6040W74A02P | (Raceway) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Raceway System | 2007-09-03 | 2008-01-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P8ZEN-125752 | RESERVE BOILER - RACEWAY DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER |  |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | FA | 0PF6040W74A02P | (Raceway) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Raceway System | 2007-09-03 | 2008-01-31 | 2025-02-14 | 2025-03-16 | 2025-04-15 | 2025-04-30 | 2025-05-15 | 2025-05-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125754 | RESERVE BOILER - TECHNICAL SPECIFICATION FOR MCC | TECHNICAL SPECIFICATION | RESERVE BOILER |  |  |  | Technical Specification for RESERVE BOILER |  | FA | 0EF6050W86A02.1 | (Safety Valve) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve |  | 2007-07-13 | [6 empty] | missing_date |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P8ZEN-125755 | RESERVE BOILER - MCC SINGLE LINE DIAGRAM | SINGLE LINE DIAGRAM | RESERVE BOILER | Motor Control Center |  |  | Single Line Diagram for RESERVE BOILER |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P8ZEN-125756 | RESERVE BOILER - MCC SCHEMATIC DIAGRAM | SCHEMATIC DIAGRAM | RESERVE BOILER | Motor Control Center |  |  | SCHEMATIC DIAGRAM for RESERVE BOILER |  | FA | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2007-07-03 | 2008-03-31 | 2024-08-28 | 2024-09-27 | 2024-10-27 | 2024-11-11 | 2024-11-26 | 2024-12-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125757 | RESERVE BOILER - TECHNICAL SPECIFICATION FOR CABLE | TECHNICAL SPECIFICATION | RESERVE BOILER |  |  |  | Technical Specification for RESERVE BOILER |  | FA | 0EF6050W86A02.1 | (Safety Valve) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve |  | 2007-07-13 | [6 empty] | missing_date |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125758 | RESERVE BOILER - TECHNICAL SPECIFICATION FOR CABLING ACCESSORIES | TECHNICAL SPECIFICATION | RESERVE BOILER |  |  |  | Technical Specification for RESERVE BOILER |  | FA | 0EF6050W86A02.1 | (Safety Valve) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve |  | 2007-07-13 | [6 empty] | missing_date |  | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125759 | RESERVE BOILER - TECHNICAL SPECIFICATION FOR FIRE STOP MATERIALS | TECHNICAL SPECIFICATION | RESERVE BOILER |  |  |  | Technical Specification for RESERVE BOILER |  | FA | 0EF4500W38A02 | (Fire Fighting Equip) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System |  | 2007-05-01 | [6 empty] | missing_date |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P8ZEN-125760 | RESERVE BOILER - POWER CABLE SCHEDULE | SCHEDULE | RESERVE BOILER |  |  |  | Schedule for RESERVE BOILER |  | FI | 1EF6040W16A02 | (Cable tunnel) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-01 | 2024-07-03 | 2024-08-02 | 2024-09-01 | 2024-09-16 | 2024-10-01 | 2024-10-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB03-P8ZEN-125761 | RESERVE BOILER - POWER CABLE CONNECTION DIAGRAM | CONNECTION DIAGRAM | RESERVE BOILER |  |  |  | CONNECTION DIAGRAM for RESERVE BOILER | FireFighting | FA | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | 2025-02-06 | 2025-03-06 | 2025-04-03 | 2025-03-27 | 2025-04-24 | 2025-05-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P8ZEN-125762 | RESERVE BOILER - EMBEDDED CONDUIT LAYOUT DRAWING | LAYOUT DRAWING | RESERVE BOILER |  |  |  | Layout Drawing for RESERVE BOILER |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2025-01-28 | 2025-02-27 | 2025-03-29 | 2025-04-13 | 2025-04-28 | 2025-05-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125763 | RESERVE BOILER - TECHNICAL SPECIFICATION FOR LIGHTING SYSTEM | TECHNICAL SPECIFICATION | RESERVE BOILER | LIGHTING SYSTEM |  |  | Technical Specification for RESERVE BOILER |  | FA | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | 2025-01-12 | 2025-02-11 | 2025-03-13 | 2025-03-28 | 2025-04-12 | 2025-04-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P8ZEN-125764 | RESERVE BOILER - ILLUMINATION CALCULATION | CALCULATION | RESERVE BOILER |  |  |  | Calculation sheet for RESERVE BOILER | Water Treatment System | FA | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | 2024-08-31 | 2024-09-30 | 2024-10-30 | 2024-11-14 | 2024-11-29 | 2024-12-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P8ZEN-125765 | RESERVE BOILER - LIGHTING LAYOUT DRAWING | LAYOUT DRAWING | RESERVE BOILER | LIGHTING |  |  | Layout Drawing for RESERVE BOILER |  | FA | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | 2025-04-13 | 2025-05-13 | 2025-06-12 | 2025-06-27 | 2025-07-12 | 2025-07-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DP00-P8ZEN-125766 | RESERVE BOILER - AIRCRAFT WARNING LIGHT DRAWING | DRAWING | RESERVE BOILER |  |  |  | DRAWING for RESERVE BOILER |  | FA | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | 2025-01-12 | 2025-02-11 | 2025-03-13 | 2025-03-28 | 2025-04-12 | 2025-04-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE03-P8ZEN-125767 | RESERVE BOILER - EARTHING DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER | Earthing & Lightning Protection System |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | FA | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | 2025-01-28 | 2025-02-27 | 2025-03-29 | 2025-04-13 | 2025-04-28 | 2025-05-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE01-P8ZEN-125768 | RESERVE BOILER - LIGHTNING PROTECTION DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER | Lightning Protection System |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | FA | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | 2025-01-28 | 2025-02-27 | 2025-03-29 | 2025-04-13 | 2025-04-28 | 2025-05-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YQ03-P8ZEN-125769 | RESERVE BOILER - COMMUNICATION SYSTEM DOCUMENT & DRAWING | DOCUMENT & DRAWING | RESERVE BOILER | Communication System & Security System |  |  | DOCUMENT & DRAWING for RESERVE BOILER |  | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | 2025-01-12 | 2025-02-11 | 2025-03-13 | 2025-03-28 | 2025-04-12 | 2025-04-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LAC-126001 | HRSG FEEDWATER PUMP - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | GENERAL ARRANGEMENT DRAWING for Heat Recovery Steam Generator FEEDWATER PUMP |  | FA | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LAC-126003 | HRSG FEEDWATER PUMP - P&I DIAGRAM | P&I DIAGRAM | Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | P&ID for Heat Recovery Steam Generator FEEDWATER PUMP |  | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | 2024-08-30 | 2024-09-29 | 2024-10-29 | 2024-11-13 | 2024-11-28 | 2024-12-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LAC-126004 | HRSG FEEDWATER PUMP - DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | DATA SHEET AND CHARACTERISTIC CURVE | Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | DATA SHEET AND CHARACTERISTIC CURVE for Heat Recovery Steam Generator FEEDWATER PUMP |  | FA | 3EF1600W00A02 | (HRSG #31/#32) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LAC-126005 | HRSG FEEDWATER PUMP - DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | DATA SHEET AND CHARACTERISTIC CURVE | Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | DATA SHEET AND CHARACTERISTIC CURVE for Heat Recovery Steam Generator FEEDWATER PUMP |  | FA | 3EF1600W00A02 | (HRSG #31/#32) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK01-P0LAC-126006 | HRSG FEEDWATER PUMP - SECTIONAL DRAWING FOR PUMP | SECTIONAL DRAWING | Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | SECTIONAL DRAWING for Heat Recovery Steam Generator FEEDWATER PUMP |  | FA | 1PF1600W74A06.1P | (HRSG #12 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | 2007-09-15 | 2008-07-10 | 2024-11-10 | 2024-12-10 | 2025-01-09 | 2025-01-24 | 2025-02-08 | 2025-02-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LAC-126007 | HRSG FEEDWATER PUMP - NAME PLATE DRAWING | NAME PLATE DRAWING | Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | NAME PLATE DRAWING for Heat Recovery Steam Generator FEEDWATER PUMP |  | FA | 3PF1615W64A06P | (HRSG #31 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2007-06-14 | 2008-04-02 | 2024-12-25 | 2025-01-24 | 2025-02-23 | 2025-03-10 | 2025-03-25 | 2025-04-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LAC-126009 | HRSG FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR SUCTION STRAINER | OUTLINE DRAWING AND DATA SHEET | Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | OUTLINE DRAWING AND DATA SHEET for Heat Recovery Steam Generator FEEDWATER PUMP |  | FA | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LAC-126010 | HRSG FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR MECHANICA SEAL | OUTLINE DRAWING AND DATA SHEET | Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | OUTLINE DRAWING AND DATA SHEET for Heat Recovery Steam Generator FEEDWATER PUMP |  | FA | 3EF1600W00A02 | (HRSG #31/#32) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT02-P0LAC-126011 | HRSG FEEDWATER PUMP - LIST AND DATA SHEET FOR INSTRUMENT | LIST AND DATA SHEET | Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | LIST AND DATA SHEET for Heat Recovery Steam Generator FEEDWATER PUMP |  | FA | 1PF1660W86A07.1P | (HRSG #12 I&C Vendor Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Auxiliary System | 2007-10-02 | 2008-08-04 | 2025-06-22 | 2025-07-22 | 2025-08-21 | 2025-09-05 | 2025-09-20 | 2025-10-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DM01-P0LAC-126012 | HRSG FEEDWATER PUMP - INSTALLATION MANUAL | INSTALLATION MANUAL | Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | INSTALLATION MANUAL for Heat Recovery Steam Generator FEEDWATER PUMP | Boiler Feed Pump | FI | 3CF1600W38A13 | (HRSG #31 LEB) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | 2008-11-01 | 2008-12-15 | 2025-07-25 | 2025-08-24 | 2025-09-23 | 2025-10-08 | 2025-10-23 | 2025-11-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LAC-126016 | HRSG FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR LUBE OIL UNIT | OUTLINE DRAWING AND DATA SHEET | Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | OUTLINE DRAWING AND DATA SHEET for Heat Recovery Steam Generator FEEDWATER PUMP |  | FA | 3EF1600W00A02 | (HRSG #31/#32) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LAC-126019 | HRSG FEEDWATER PUMP - EMERGENCY PUSH BUTTON DRAWING | DRAWING | Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | DRAWING for Heat Recovery Steam Generator FEEDWATER PUMP |  | FA | 1PF1600W74A06P | (HRSG #11 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | 2007-09-15 | 2008-07-10 | 2025-02-26 | 2025-03-28 | 2025-04-27 | 2025-05-12 | 2025-05-27 | 2025-06-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0LAC-126027 | HRSG FEEDWATER PUMP - FLEXIBLE COUPLING DATA SHEET & DRAWING | DATA SHEET & DRAWING | Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | DATA SHEET & DRAWING for Heat Recovery Steam Generator FEEDWATER PUMP |  | FA | 3EF1600W00A02 | (HRSG #31/#32) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-08-12 | 2024-09-11 | 2024-10-11 | 2024-10-26 | 2024-11-10 | 2024-11-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LAC-126051 | FGP FEEDWATER PUMP - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | Fuel Gas Package FEEDWATER PUMP |  |  |  | GENERAL ARRANGEMENT DRAWING for Fuel Gas Package FEEDWATER PUMP |  | FA | 1EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-10-31 |  | 2024-12-12 | 2025-01-11 | 2025-02-10 | 2025-02-25 | 2025-03-12 | 2025-03-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LAC-126053 | FGP FEEDWATER PUMP - P&I DIAGRAM | P&I DIAGRAM | Fuel Gas Package FEEDWATER PUMP |  |  |  | P&ID for Fuel Gas Package FEEDWATER PUMP | Fuel Gas Compressor | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LAC-126054 | FGP FEEDWATER PUMP - DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | DATA SHEET AND CHARACTERISTIC CURVE | Fuel Gas Package FEEDWATER PUMP |  |  |  | DATA SHEET AND CHARACTERISTIC CURVE for Fuel Gas Package FEEDWATER PUMP |  | FA | 0EF3520W00A01.2 | (FOSS) FO Forwarding Pump, FO Unloading Pump Key data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System | 2007-04-02 | 2007-04-30 | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LAC-126055 | FGP FEEDWATER PUMP - DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | DATA SHEET AND CHARACTERISTIC CURVE | Fuel Gas Package FEEDWATER PUMP |  |  |  | DATA SHEET AND CHARACTERISTIC CURVE for Fuel Gas Package FEEDWATER PUMP |  | FA | 0PF3520W42A08P | (Condensate Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-06-29 | 2024-07-29 | 2024-08-28 | 2024-09-12 | 2024-09-27 | 2024-10-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK01-P0LAC-126056 | FGP FEEDWATER PUMP - SECTIONAL DRAWING FOR PUMP | SECTIONAL DRAWING | Fuel Gas Package FEEDWATER PUMP |  |  |  | SECTIONAL DRAWING for Fuel Gas Package FEEDWATER PUMP |  | FA | 0PF3520W42A08P | (Condensate Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-07-27 | 2024-08-26 | 2024-09-25 | 2024-10-10 | 2024-10-25 | 2024-11-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LAC-126057 | FGP FEEDWATER PUMP - NAME PLATE DRAWING | NAME PLATE DRAWING | Fuel Gas Package FEEDWATER PUMP |  |  |  | NAME PLATE DRAWING for Fuel Gas Package FEEDWATER PUMP |  | FI | 0PF3520W42A08P | (Condensate Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-10-19 | 2024-11-18 | 2024-12-18 | 2025-01-02 | 2025-01-17 | 2025-02-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LAC-126059 | FGP FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR SUCTION STRAINER | OUTLINE DRAWING AND DATA SHEET | Fuel Gas Package FEEDWATER PUMP |  |  |  | OUTLINE DRAWING AND DATA SHEET for Fuel Gas Package FEEDWATER PUMP |  | FA | 0PF3520W42A08P | (Condensate Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-06-29 | 2024-07-29 | 2024-08-28 | 2024-09-12 | 2024-09-27 | 2024-10-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LAC-126060 | FGP FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR MECHANICA SEAL | OUTLINE DRAWING AND DATA SHEET | Fuel Gas Package FEEDWATER PUMP |  |  |  | OUTLINE DRAWING AND DATA SHEET for Fuel Gas Package FEEDWATER PUMP |  | FA | 0PF3520W42A08P | (Condensate Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-06-29 | 2024-07-29 | 2024-08-28 | 2024-09-12 | 2024-09-27 | 2024-10-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT02-P0LAC-126061 | FGP FEEDWATER PUMP - LIST AND DATA SHEET FOR INSTRUMENT | LIST AND DATA SHEET | Fuel Gas Package FEEDWATER PUMP | Instrumentation & Control |  |  | LIST AND DATA SHEET for Fuel Gas Package FEEDWATER PUMP | FireFighting | FA | 0PF3520W42A08P | (Condensate Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-09-07 | 2024-10-12 | 2024-11-16 | 2024-11-02 | 2024-12-07 | 2025-01-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DM01-P0LAC-126062 | FGP FEEDWATER PUMP - INSTALLATION MANUAL | INSTALLATION MANUAL | Fuel Gas Package FEEDWATER PUMP |  |  |  | INSTALLATION MANUAL for Fuel Gas Package FEEDWATER PUMP | Fuel Gas Compressor | FI | 0CF3520W42A05 | (Transfer Pump) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > DFO Tank & Pump | 2008-05-14 | 2008-06-13 | 2025-01-21 | 2025-02-20 | 2025-03-22 | 2025-04-06 | 2025-04-21 | 2025-05-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LAC-126066 | FGP FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR LUBE OIL UNIT | OUTLINE DRAWING AND DATA SHEET | Fuel Gas Package FEEDWATER PUMP | LUBE OIL SYSTEM |  |  | OUTLINE DRAWING AND DATA SHEET for Fuel Gas Package FEEDWATER PUMP |  | FA | 1PF1250W42A06P | (Lube Oil System) P.O & Procurement_Lube oil functional Module | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Lube Oil System | 2007-03-01 | 2008-01-30 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LAC-126069 | FGP FEEDWATER PUMP - EMERGENCY PUSH BUTTON DRAWING | DRAWING | Fuel Gas Package FEEDWATER PUMP |  |  |  | DRAWING for Fuel Gas Package FEEDWATER PUMP |  | FA | 1PF1265W42A09P | (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | 2007-03-01 | 2008-01-31 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0LAC-126077 | FGP FEEDWATER PUMP - FLEXIBLE COUPLING DATA SHEET & DRAWING | DATA SHEET & DRAWING | Fuel Gas Package FEEDWATER PUMP |  |  |  | DATA SHEET & DRAWING for Fuel Gas Package FEEDWATER PUMP | Fuel Gas Compressor | FA | 1EF3015W00A01 | (FWS) BFP Key data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-04-02 | 2007-05-31 | [6 empty] | generated |  | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0LAC-126301 | HRSG FEEDWATER PUMP - I&C JUNCTION BOX DRAWING | DRAWING | Heat Recovery Steam Generator FEEDWATER PUMP | Instrumentation & Control |  |  | DRAWING for Heat Recovery Steam Generator FEEDWATER PUMP |  | FA | 1PF1600W90A10P | (HRSG #11 LEB) P.O & Procurement - I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | 2007-09-15 | 2008-07-10 | 2025-02-26 | 2025-03-28 | 2025-04-27 | 2025-05-12 | 2025-05-27 | 2025-06-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS02-P0LAC-126302 | HRSG FEEDWATER PUMP - CABLE INTERCONNECTION WIRING DIAGRAM | WIRING DIAGRAM | Heat Recovery Steam Generator FEEDWATER PUMP |  |  |  | WIRING DIAGRAM for Heat Recovery Steam Generator FEEDWATER PUMP |  | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | 2024-09-29 | 2024-10-29 | 2024-11-28 | 2024-12-13 | 2024-12-28 | 2025-01-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0LAC-126351 | FGP FEEDWATER PUMP - I&C JUNCTION BOX DRAWING | DRAWING | Fuel Gas Package FEEDWATER PUMP | Instrumentation & Control |  |  | DRAWING for Fuel Gas Package FEEDWATER PUMP |  | FA | 1PF1265W42A09P | (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | 2007-03-01 | 2008-01-31 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS02-P0LAC-126352 | FGP FEEDWATER PUMP - CABLE INTERCONNECTION WIRING DIAGRAM | WIRING DIAGRAM | Fuel Gas Package FEEDWATER PUMP |  |  |  | WIRING DIAGRAM for Fuel Gas Package FEEDWATER PUMP | Fuel Gas System | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | 2024-06-07 | 2024-07-19 | 2024-08-30 | 2024-08-09 | 2024-09-20 | 2024-11-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0PCA-126501 | FIN FAN COOLER - SYSTEM DESCRIPTION | SYSTEM DESCRIPTION | Fin Fan Cooler |  |  |  | System Description for Fin Fan Cooler | FinFan Cooler | FI | 1CF1225W42A07 | (CCW H/EX) Installation_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | 2008-05-16 | 2008-06-30 | 2025-06-16 | 2025-07-16 | 2025-08-15 | 2025-08-30 | 2025-09-14 | 2025-09-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0PCA-126502 | FIN FAN COOLER - P&I DIAGRAM | P&I DIAGRAM | Fin Fan Cooler |  |  |  | P&ID for Fin Fan Cooler | CPP FIN FAN COOLER | FA | 1CF1225W42A07 | (CCW H/EX) Installation_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | 2008-05-16 | 2008-06-30 |  |  |  | 2025-02-16 | 2025-03-18 | 2025-04-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0PCA-126503 | FIN FAN COOLER - GENERAL ARRANGEMENT & PLOT PLAN DRAWING | GENERAL ARRANGEMENT & PLOT PLAN DRAWING | Fin Fan Cooler |  |  |  | GENERAL ARRANGEMENT & PLOT PLAN DRAWING for Fin Fan Cooler | FinFan Cooler | FA | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | 2024-08-02 | 2024-09-01 | 2024-10-01 | 2024-10-16 | 2024-10-31 | 2024-11-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0PCA-126504 | FIN FAN COOLER - PERFORMANCE CURVE | PERFORMANCE CURVE | Fin Fan Cooler |  |  |  | PERFORMANCE CURVE for Fin Fan Cooler | FinFan Cooler | FI | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | 2024-08-02 | 2024-09-01 | 2024-10-01 | 2024-10-16 | 2024-10-31 | 2024-11-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL25-P0PCA-126505 | FIN FAN COOLER - TERMINAL POINT LIST & DRAWING | LIST & DRAWING | Fin Fan Cooler |  |  |  | LIST & DRAWING for Fin Fan Cooler | FinFan Cooler | FI | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | 2024-08-02 | 2024-09-01 | 2024-10-01 | 2024-10-16 | 2024-10-31 | 2024-11-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XV00-P0PCA-126506 | FIN FAN COOLER - EQUIPMENT LIST | EQUIPMENT LIST | Fin Fan Cooler |  |  |  | EQUIPMENT LIST for Fin Fan Cooler | FinFan Cooler | FI | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | 2024-08-02 | 2024-09-01 | 2024-10-01 | 2024-10-16 | 2024-10-31 | 2024-11-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0PCA-126507 | FIN FAN COOLER - VALVE LIST | VALVE LIST | Fin Fan Cooler |  |  |  | VALVE LIST for Fin Fan Cooler |  | FA | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | 2024-09-25 | 2024-10-25 | 2024-11-24 | 2024-12-09 | 2024-12-24 | 2025-01-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XK00-P0PCA-126508 | FIN FAN COOLER - BELT PULLEY DATA SHEET | DATA SHEET | Fin Fan Cooler |  |  |  | Data Sheet for Fin Fan Cooler | FinFan Cooler | FA | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | 2024-08-02 | 2024-09-01 | 2024-10-01 | 2024-10-16 | 2024-10-31 | 2024-11-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0PCA-126509 | FIN FAN COOLER - FAN MOTOR DATA SHEET | DATA SHEET | Fin Fan Cooler |  |  |  | Data Sheet for Fin Fan Cooler | FinFan Cooler | FA | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | 2024-08-02 | 2024-09-01 | 2024-10-01 | 2024-10-16 | 2024-10-31 | 2024-11-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0PCA-126512 | FIN FAN COOLER - FAN OUTLINE DRAWING (WITH MOTOR) | OUTLINE DRAWING | Fin Fan Cooler |  |  |  | Outline Drawing for Fin Fan Cooler |  | FA | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | 2025-01-18 | 2025-02-17 | 2025-03-19 | 2025-04-03 | 2025-04-18 | 2025-05-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0PCA-126513 | FIN FAN COOLER - VALVE OUTLINE DRAWING | OUTLINE DRAWING | FIN FAN COOLER |  |  |  | Outline Drawing for FIN FAN COOLER |  | FA | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | 2025-01-18 | 2025-02-17 | 2025-03-19 | 2025-04-03 | 2025-04-18 | 2025-05-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0PCA-126514 | FIN FAN COOLER - PIPING ARRANGEMENT DRAWING | ARRANGEMENT DRAWING | FIN FAN COOLER | Piping |  |  | General Arrangement Drawing for FIN FAN COOLER |  | FA | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | 2024-08-14 | 2024-09-13 | 2024-10-13 | 2024-10-28 | 2024-11-12 | 2024-11-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0PCA-126515 | FIN FAN COOLER - PIPING ISOMETRIC DRAWRING | ISOMETRIC DRAWRING | FIN FAN COOLER | Piping |  |  | ISOMETRIC DRAWRING for FIN FAN COOLER | CCW FIN FAN COOLER | FA | 1CF1225W42A07 | (CCW H/EX) Installation_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | 2008-05-16 | 2008-06-30 |  |  |  | 2025-02-16 | 2025-03-18 | 2025-04-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0PCA-126516 | FIN FAN COOLER - PIPE MATERIAL SPECIFICATION | MATERIAL SPECIFICATION | FIN FAN COOLER | Piping |  |  | MATERIAL SPECIFICATION for FIN FAN COOLER | FinFan Cooler | FA | 1EF1225W42A17.1 | (CCW H/EX) MPS Issue_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System |  | 2007-05-01 | [6 empty] | missing_date |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0PCA-126517 | FIN FAN COOLER - PIPE LINE LIST | LINE LIST | FIN FAN COOLER |  |  |  | LINE LIST for FIN FAN COOLER | FinFan Cooler | FI | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | 2024-10-01 | 2024-10-31 | 2024-11-30 | 2024-12-15 | 2024-12-30 | 2025-01-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0PCA-126519 | FIN FAN COOLER - CONTROL DESCRIPTION (PHILOSOPHY) | CONTROL DESCRIPTION (PHILOSOPHY) | FIN FAN COOLER | control system |  |  | CONTROL DESCRIPTION (PHILOSOPHY) for FIN FAN COOLER | FinFan Cooler | FA | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | 2024-10-01 | 2024-10-31 | 2024-11-30 | 2024-12-15 | 2024-12-30 | 2025-01-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0PCA-126522 | FIN FAN COOLER - LOGIC / FUNCTIONAL LOOP DIAGRAMS | LOGIC / FUNCTIONAL LOOP DIAGRAMS | FIN FAN COOLER |  |  |  | LOGIC / FUNCTIONAL LOOP DIAGRAMS for FIN FAN COOLER | FinFan Cooler | FA | 1PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | 2007-07-03 | 2008-03-31 | 2024-10-01 | 2024-10-31 | 2024-11-30 | 2024-12-15 | 2024-12-30 | 2025-01-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0PCA-126523 | FIN FAN COOLER - INSTRUMENT LIST | LIST | FIN FAN COOLER | Instrument |  |  | LIST for FIN FAN COOLER | FinFan Cooler | FI | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | 2024-09-01 | 2024-10-01 | 2024-10-31 | 2024-11-15 | 2024-11-30 | 2024-12-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0PCA-126524 | FIN FAN COOLER - INSTRUMENT CATALOG | CATALOG | FIN FAN COOLER | Instrument |  |  | CATALOG for FIN FAN COOLER | FinFan Cooler | FA | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | 2024-09-01 | 2024-10-01 | 2024-10-31 | 2024-11-15 | 2024-11-30 | 2024-12-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0PCA-126525 | FIN FAN COOLER - INSTRUMENT INSTALLATION DETAIL DRAWING | INSTALLATION DETAIL DRAWING | FIN FAN COOLER | Instrument |  |  | INSTALLATION DETAIL DRAWING for FIN FAN COOLER | FinFan Cooler | FA | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | 2024-10-01 | 2024-10-31 | 2024-11-30 | 2024-12-15 | 2024-12-30 | 2025-01-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0PCA-126526 | FIN FAN COOLER - INSTRUMENT DATA SHEET | DATA SHEET | FIN FAN COOLER | Instrument |  |  | Data Sheet for FIN FAN COOLER | FinFan Cooler | FA | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | 2024-08-02 | 2024-09-01 | 2024-10-01 | 2024-10-16 | 2024-10-31 | 2024-11-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0PCA-126527 | FIN FAN COOLER - DRIVE LIST (MOVS, MOTORS, CONTROL VALVES, SOLENOID VALVES, ETC..) | LIST | FIN FAN COOLER |  |  |  | LIST for FIN FAN COOLER | FinFan Cooler | FI | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | 2024-09-01 | 2024-10-01 | 2024-10-31 | 2024-11-15 | 2024-11-30 | 2024-12-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT02-P0PCA-126529 | FIN FAN COOLER - RACEWAY DRAWING | DRAWING | FIN FAN COOLER |  |  |  | DRAWING for FIN FAN COOLER | FinFan Cooler | FA | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | 2024-11-30 | 2024-12-30 | 2025-01-29 | 2025-02-13 | 2025-02-28 | 2025-03-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0PCA-126530 | JUNCTION BOX OUTLINE AND LAYOUT DRAWING | DRAWING |  |  |  |  | DRAWING |  | FA | 1PF3020W42A12P | (COND Flash Box) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-07-01 | 2024-11-14 | 2024-12-14 | 2025-01-13 | 2025-01-28 | 2025-02-12 | 2025-02-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0PCA-126533 | FIN FAN COOLER - WIRING DIAGRAMS FOR JUNCTION BOXES | WIRING DIAGRAMS | FIN FAN COOLER |  |  |  | WIRING DIAGRAMS for FIN FAN COOLER | FinFan Cooler | FA | 1PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | 2007-07-03 | 2008-03-31 | 2024-10-01 | 2024-10-31 | 2024-11-30 | 2024-12-15 | 2024-12-30 | 2025-01-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XK00-P0PCA-126538 | FIN FAN COOLER - FOUNDATION DRAWINGS / CIVIL LOADING DATA WITH EMBEDDED MATERIAL DRAWING (INCLUDE AUXILIARY EQUIPMENT) | DRAWINGS / DRAWING | FIN FAN COOLER |  |  |  | DRAWINGS / DRAWING for FIN FAN COOLER | FinFan Cooler | FA | 1PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | 2007-07-03 | 2008-03-31 | 2024-11-30 | 2024-12-30 | 2025-01-29 | 2025-02-13 | 2025-02-28 | 2025-03-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XK00-P0PCA-126539 | FIN FAN COOLER - STEEL STRUCTURE CALCULATION | CALCULATION | FIN FAN COOLER |  |  |  | Calculation sheet for FIN FAN COOLER | CCW FIN FAN COOLER | FA | 1CF1225W42A07 | (CCW H/EX) Installation_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | 2008-05-16 | 2008-06-30 |  |  |  | 2025-02-16 | 2025-03-18 | 2025-04-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0PCA-126540 | FIN FAN COOLER – DETAIL DRAWING FOR CLEANING COMPRESSOR | DETAIL DRAWING | FIN FAN COOLER |  |  |  | Detail Drawing for FIN FAN COOLER | FinFan Cooler | FA | 1PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | 2007-07-03 | 2008-03-31 | 2024-10-01 | 2024-10-31 | 2024-11-30 | 2024-12-15 | 2024-12-30 | 2025-01-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LCB-127001 | FGP COP - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | Fuel Gas Package COP |  |  |  | GENERAL ARRANGEMENT DRAWING for Fuel Gas Package COP |  | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | 2024-06-26 | 2024-07-26 | 2024-08-25 | 2024-09-09 | 2024-09-24 | 2024-10-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LCB-127002 | FGP COP - P&I DIAGRAM | Piping & Instrumentation Drawing | Fuel Gas Package COP |  |  |  | P&ID for Fuel Gas Package COP | Fuel Gas Compressor | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCB-127003 | FGP COP - DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET & CHARACTERISTIC CURVE | Fuel Gas Package |  |  |  | DATA SHEET & CHARACTERISTIC CURVE for FGP |  | FA | 1EF3520W00A03.1 | (Gas COMP PKG) FGC Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-03-01 | 2007-03-01 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0LCB-127004 | FGP COP - PUMP SECTIONAL DRAWING | DRAWING | Fuel Gas Package |  |  |  | DRAWING for FGP |  | FA | 0PF3520W42A08P | (Condensate Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCB-127005 | FGP COP - MECHANICAL SEAL SPECIFICATION | SPECIFICATION | Fuel Gas Package |  |  |  | Technical Specification for FGP |  | FA | 1PF1250W42A02.3P | (GEN Seal Oil Sys.) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Generator Seal Oil System | 2007-03-01 | 2008-01-31 | 2024-08-12 | 2024-09-11 | 2024-10-11 | 2024-10-26 | 2024-11-10 | 2024-11-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCB-127006 | FGP COP - COUPLING SPECIFICATION | SPECIFICATION | Fuel Gas Package |  |  |  | Technical Specification for FGP |  | FA | 1PF3520W42A05.1P | (Gas COMP PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-03-15 | 2008-04-14 | 2024-08-26 | 2024-09-25 | 2024-10-25 | 2024-11-09 | 2024-11-24 | 2024-12-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCB-127007 | FGP COP - SUCTION STRAINER SPECIFICATION | SPECIFICATION | Fuel Gas Package |  |  |  | Technical Specification for FGP |  | FA | 1PF3520W42A05.1P | (Gas COMP PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-03-15 | 2008-04-14 | 2024-08-26 | 2024-09-25 | 2024-10-25 | 2024-11-09 | 2024-11-24 | 2024-12-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LCB-127009 | FGP COP - FOUNDATION DRAWINGS | DRAWINGS | Fuel Gas Package |  |  |  | DRAWINGS for FGP |  | FA | 1PF3520W42A05.1P | (Gas COMP PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-03-15 | 2008-04-14 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YM01-P0LCB-127010 | FGP COP - MOTOR DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET & CHARACTERISTIC CURVE | Fuel Gas Package |  |  |  | DATA SHEET & CHARACTERISTIC CURVE for FGP |  | FA | 1EF3520W00A03.1 | (Gas COMP PKG) FGC Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-03-01 | 2007-03-01 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0LCB-127011 | FGP COP - EMERGENCY PUSH BUTTON DRAWING | DRAWING | Fuel Gas Package |  |  |  | DRAWING for FGP |  | FA | 1PF3520W42A05.1P | (Gas COMP PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-03-15 | 2008-04-14 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0LCB-127013 | FGP COP - INSTRUMENT LIST AND DATA SHEET | LIST AND DATA SHEET | Fuel Gas Package |  |  |  | LIST AND DATA SHEET for FGP |  | FA | 1EF3520W00A03.1 | (Gas COMP PKG) FGC Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-03-01 | 2007-03-01 | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0LCB-127015 | FGP COP - INSTRUMENTATION HOOK - UP DRAWING | HOOK - UP DRAWING | Fuel Gas Package |  |  |  | HOOK - UP DRAWING for FGP |  | FI | 1PF3520W42A05.1P | (Gas COMP PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-03-15 | 2008-04-14 | 2024-07-05 | 2024-08-04 | 2024-09-03 | 2024-09-18 | 2024-10-03 | 2024-10-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCB-127016 | FGP COP - VMS SPECIFICATION | SPECIFICATION | Fuel Gas Package |  |  |  | Technical Specification for FGP |  | FA | 1PF3520W42A05.1P | (Gas COMP PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-03-15 | 2008-04-14 | 2024-08-26 | 2024-09-25 | 2024-10-25 | 2024-11-09 | 2024-11-24 | 2024-12-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL22-P0LCB-127018 | FGP COP - NAME PLATE DRAWING | DRAWING | Fuel Gas Package |  |  |  | DRAWING for FGP |  | FA | 1PF3520W42A05.1P | (Gas COMP PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-03-15 | 2008-04-14 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LCB-127031 | CEP - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | Condensate Extraction Pump |  |  |  | GENERAL ARRANGEMENT DRAWING for CEP |  | FA | 1PF3020W42A04P | (CEP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-09-07 | 2008-08-07 | 2024-10-19 | 2024-11-18 | 2024-12-18 | 2025-01-02 | 2025-01-17 | 2025-02-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LCB-127032 | CEP - P&I DIAGRAM | P&I DIAGRAM | Condensate Extraction Pump |  |  |  | P&ID for CEP |  | FA | 1PF3020W42A04P | (CEP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-09-07 | 2008-08-07 | 2024-10-05 | 2024-11-04 | 2024-12-04 | 2024-12-19 | 2025-01-03 | 2025-01-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCB-127033 | CEP - DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET & CHARACTERISTIC CURVE | Condensate Extraction Pump |  |  |  | DATA SHEET & CHARACTERISTIC CURVE for CEP |  | FA | 1PF3020W42A04P | (CEP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-09-07 | 2008-08-07 | 2024-10-05 | 2024-11-04 | 2024-12-04 | 2024-12-19 | 2025-01-03 | 2025-01-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0LCB-127034 | CEP - PUMP SECTIONAL DRAWING | DRAWING | Condensate Extraction Pump |  |  |  | DRAWING for CEP |  | FA | 1CF3020W42A06 | (CEP) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2008-09-23 | 2008-12-11 |  |  |  | 2025-06-26 | 2025-07-26 | 2025-08-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCB-127035 | CEP - MECHANICAL SEAL SPECIFICATION | SPECIFICATION | Condensate Extraction Pump |  |  |  | Technical Specification for CEP |  | FA | 1PF3020W42A04P | (CEP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-09-07 | 2008-08-07 | 2025-02-18 | 2025-03-20 | 2025-04-19 | 2025-05-04 | 2025-05-19 | 2025-06-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCB-127036 | CEP - COUPLING SPECIFICATION | SPECIFICATION | Condensate Extraction Pump |  |  |  | Technical Specification for CEP |  | FA | 1PF3020W42A04P | (CEP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-09-07 | 2008-08-07 | 2025-02-18 | 2025-03-20 | 2025-04-19 | 2025-05-04 | 2025-05-19 | 2025-06-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LCB-127037 | CEP - SUCTION STRAINER SPECIFICATION | SPECIFICATION | Condensate Extraction Pump |  |  |  | Technical Specification for CEP |  | FA | 1PF3020W42A04P | (CEP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-09-07 | 2008-08-07 | 2025-02-18 | 2025-03-20 | 2025-04-19 | 2025-05-04 | 2025-05-19 | 2025-06-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LCB-127038 | CEP - FOUNDATION DRAWINGS | DRAWINGS | Condensate Extraction Pump |  |  |  | DRAWINGS for CEP |  | FA | 1EF3020W16A01 | (CEP) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-10-09 | 2008-01-04 |  |  |  | 2024-07-11 | 2024-08-10 | 2024-09-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YM01-P0LCB-127039 | CEP - MOTOR DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET | Condensate Extraction Pump |  |  |  | Data Sheet for CEP |  | FA | 1PF3020W42A04P | (CEP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-09-07 | 2008-08-07 | 2024-11-16 | 2024-12-16 | 2025-01-15 | 2025-01-30 | 2025-02-14 | 2025-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0LCB-127040 | CEP - INSTRUMENT LIST AND DATA SHEET | LIST AND DATA SHEET | Condensate Extraction Pump |  |  |  | LIST AND DATA SHEET for CEP |  | FA | 1PF3020W42A04P | (CEP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-09-07 | 2008-08-07 | 2024-11-16 | 2024-12-16 | 2025-01-15 | 2025-01-30 | 2025-02-14 | 2025-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0LCB-127041 | CEP - INSTRUMENTATION HOOK - UP DRAWING | HOOK - UP DRAWING | Condensate Extraction Pump | Instrumentation & Control |  |  | HOOK - UP DRAWING for CEP |  | FI | 1PF3020W42A04P | (CEP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-09-07 | 2008-08-07 | 2024-12-28 | 2025-01-27 | 2025-02-26 | 2025-03-13 | 2025-03-28 | 2025-04-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL22-P0LCB-127042 | CEP - NAME PLATE DRAWING | DRAWING | Condensate Extraction Pump |  |  |  | DRAWING for CEP |  | FA | 1CF3020W42A06 | (CEP) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2008-09-23 | 2008-12-11 |  |  |  | 2025-06-26 | 2025-07-26 | 2025-08-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LCB-127501 | AIR COMPRESSOR - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | AIR COMPRESSOR |  |  |  | GENERAL ARRANGEMENT DRAWING for AIR COMPRESSOR |  | FA | 0EF3510W00A17 | (COMP Air BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 |  | 2024-09-12 | 2024-10-12 | 2024-11-11 | 2024-11-26 | 2024-12-11 | 2024-12-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SCA-127502 | AIR COMPRESSOR - P&I DIAGRAM | P&I DIAGRAM | AIR COMPRESSOR |  |  |  | P&ID for AIR COMPRESSOR | Fuel Gas Compressor | FA | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | 2024-08-29 | 2024-09-28 | 2024-10-28 | 2024-11-12 | 2024-11-27 | 2024-12-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0SCA-127503 | AIR COMPRESSOR - AIR COMPRESSOR SPECIFICATION | SPECIFICATION | AIR COMPRESSOR |  |  |  | Technical Specification for AIR COMPRESSOR | Air Compressor | FA | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | 2024-08-15 | 2024-09-14 | 2024-10-14 | 2024-10-29 | 2024-11-13 | 2024-11-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0SCA-127504 | AIR COMPRESSOR - AIR DRYER SPECIFICATION | SPECIFICATION | AIR COMPRESSOR |  |  |  | Technical Specification for AIR COMPRESSOR | Air Compressor | FA | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | 2024-08-15 | 2024-09-14 | 2024-10-14 | 2024-10-29 | 2024-11-13 | 2024-11-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0SCA-127505 | AIR COMPRESSOR - AIR RECEIVER SPECIFICATION | SPECIFICATION | AIR COMPRESSOR |  |  |  | Technical Specification for AIR COMPRESSOR | Air Compressor | FA | 0EF3510W16A02 | (COMP Air Receiver TK Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-11-12 | 2024-08-15 | 2024-09-14 | 2024-10-14 | 2024-10-29 | 2024-11-13 | 2024-11-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0SCA-127506 | AIR COMPRESSOR - AIR FILTER SPECIFICATION | SPECIFICATION | AIR COMPRESSOR |  |  |  | Technical Specification for AIR COMPRESSOR | Air Compressor | FA | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | 2024-08-15 | 2024-09-14 | 2024-10-14 | 2024-10-29 | 2024-11-13 | 2024-11-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB00-P0SCA-127509 | AIR COMPRESSOR - FOUNDATION DRAWINGS | DRAWINGS | AIR COMPRESSOR |  |  |  | DRAWINGS for AIR COMPRESSOR | Air Compressor | FA | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | 2024-10-24 | 2024-11-23 | 2024-12-23 | 2025-01-07 | 2025-01-22 | 2025-02-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0SCA-127510 | AIR COMPRESSOR - SINGLE LINE DIAGRAM | SINGLE LINE DIAGRAM | AIR COMPRESSOR |  |  |  | Single Line Diagram for AIR COMPRESSOR | Air Compressor | FA | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YV02-P0SCA-127511 | AIR COMPRESSOR - SCHEMATIC & WIRING DIAGRAM | SCHEMATIC & WIRING DIAGRAM | AIR COMPRESSOR |  |  |  | SCHEMATIC & WIRING DIAGRAM for AIR COMPRESSOR | Air Compressor | FA | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | 2024-10-24 | 2024-11-23 | 2024-12-23 | 2025-01-07 | 2025-01-22 | 2025-02-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF02-P0SCA-127514 | AIR COMPRESSOR - CONTROL DESCRIPTION (PHILOSOPHY) | CONTROL DESCRIPTION (PHILOSOPHY) | AIR COMPRESSOR |  |  |  | CONTROL DESCRIPTION (PHILOSOPHY) for AIR COMPRESSOR | Air Compressor | FA | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | 2024-10-24 | 2024-11-23 | 2024-12-23 | 2025-01-07 | 2025-01-22 | 2025-02-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD05-P0SCA-127515 | AIR COMPRESSOR - PLC HMI GRAPHICS | GRAPHICS | AIR COMPRESSOR |  |  |  | GRAPHICS for AIR COMPRESSOR | Air Compressor | FA | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | 2024-12-19 | 2025-01-18 | 2025-02-17 | 2025-03-04 | 2025-03-19 | 2025-04-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0SCA-127516 | AIR COMPRESSOR - PLC HARDWIRED IO LIST | LIST | AIR COMPRESSOR |  |  |  | LIST for AIR COMPRESSOR | Air Compressor | FI | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0SCA-127517 | AIR COMPRESSOR - DATALINK INTERFACE IO LIST | LIST | AIR COMPRESSOR |  |  |  | LIST for AIR COMPRESSOR | Air Compressor | FI | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0SCA-127518 | AIR COMPRESSOR - CONTROL LOGIC & LOOP DIAGRAM | CONTROL LOGIC & LOOP DIAGRAM | AIR COMPRESSOR |  |  |  | CONTROL LOGIC & LOOP DIAGRAM for AIR COMPRESSOR | Air Compressor | FA | 1SF3520W62A13.1 | (Gas COMP PKG #11) Loop chek | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2008-08-03 | 2008-08-12 | 2025-10-27 | 2025-11-26 | 2025-12-26 | 2026-01-10 | 2026-01-25 | 2026-02-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0SCA-127520 | AIR COMPRESSOR - INSTRUMENT LIST | LIST | AIR COMPRESSOR |  |  |  | LIST for AIR COMPRESSOR | Air Compressor | FI | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0SCA-127521 | AIR COMPRESSOR - INSTRUMENT SPECIFICATION | SPECIFICATION | AIR COMPRESSOR |  |  |  | Technical Specification for AIR COMPRESSOR | Air Compressor | FA | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | 2024-08-15 | 2024-09-14 | 2024-10-14 | 2024-10-29 | 2024-11-13 | 2024-11-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0SCA-127522 | AIR COMPRESSOR - INSTRUMENTATION HOOK - UP DRAWING | HOOK - UP DRAWING | AIR COMPRESSOR | Instrumentation & Control |  |  | HOOK - UP DRAWING for AIR COMPRESSOR |  | FI | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | 2024-11-21 | 2024-12-21 | 2025-01-20 | 2025-02-04 | 2025-02-19 | 2025-03-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0SCA-127523 | AIR COMPRESSOR - PLC PANEL DRAWING | DRAWING | AIR COMPRESSOR |  |  |  | DRAWING for AIR COMPRESSOR | Air Compressor | FA | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | 2024-11-21 | 2024-12-21 | 2025-01-20 | 2025-02-04 | 2025-02-19 | 2025-03-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XF00-P0SCA-127524 | AIR COMPRESSOR - NAME PLATE DRAWING | DRAWING | AIR COMPRESSOR |  |  |  | DRAWING for AIR COMPRESSOR | Air Compressor | FA | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | 2024-11-21 | 2024-12-21 | 2025-01-20 | 2025-02-04 | 2025-02-19 | 2025-03-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0SCA-127525 | AIR COMPRESSOR - VALVE LIST | LIST | AIR COMPRESSOR |  |  |  | LIST for AIR COMPRESSOR | Air Compressor | FI | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SCA-127526 | AIR COMPRESSOR - VALVE SPECIFICATION | SPECIFICATION | AIR COMPRESSOR |  |  |  | Technical Specification for AIR COMPRESSOR | Air Compressor | FA | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | 2024-08-15 | 2024-09-14 | 2024-10-14 | 2024-10-29 | 2024-11-13 | 2024-11-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD16-P0SCA-127546 | AIR COMPRESSOR - EMBEDDED CONDUIT LAYOUT FOR CONTROL CABLES (FROM MCP TO EQUIPMENT) |  | AIR COMPRESSOR |  |  |  | for AIR COMPRESSOR | Air Compressor | FA | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | 2024-12-19 | 2025-01-18 | 2025-02-17 | 2025-03-04 | 2025-03-19 | 2025-04-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YV02-P0SCA-127548 | AIR COMPRESSOR – I&C CABLE INTERCONNECTION WIRING DIAGRAM | WIRING DIAGRAM | AIR COMPRESSOR | Instrumentation & Control |  |  | WIRING DIAGRAM for AIR COMPRESSOR | Air Compressor | FA | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | 2024-10-24 | 2024-11-23 | 2024-12-23 | 2025-01-07 | 2025-01-22 | 2025-02-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LCB-127555 | AIR COMPRESSOR - AIR CHILLER - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | AIR COMPRESSOR, AIR CHILLER |  |  |  | GENERAL ARRANGEMENT DRAWING for AIR COMPRESSOR, AIR CHILLER |  | FA | 0EF3510W00A17 | (COMP Air BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 |  | 2024-09-12 | 2024-10-12 | 2024-11-11 | 2024-11-26 | 2024-12-11 | 2024-12-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0SCA-127556 | AIR COMPRESSOR - AIR CHILLER - DATA SHEET | DATA SHEET | AIR COMPRESSOR, AIR CHILLER |  |  |  | Data Sheet for AIR COMPRESSOR, AIR CHILLER | Air Compressor | FA | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SCA-127557 | AIR COMPRESSOR - AIR CHILLER - P&I DIAGRAM | P&I DIAGRAM | AIR COMPRESSOR, AIR CHILLER |  |  |  | P&ID for AIR COMPRESSOR, AIR CHILLER | Fuel Gas Compressor | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMM-128001 | CRANE - GA DRAWING FOR STEAM TURBINE BUILDING CRANE | GENERAL ARRANGEMENT DRAWING | Crane & Hoist |  | Steam Turbine Building |  | GENERAL ARRANGEMENT DRAWING for Crane & Hoist |  | FA | 0CF2010W42A07 | (Crane & Hoist) Crane Erection for STG Building | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2008-07-17 | 2008-09-17 | 2025-08-29 | 2025-09-28 | 2025-10-28 | 2025-11-12 | 2025-11-27 | 2025-12-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMS-128002 | CRANE - GA DRAWING FOR WORKSHOP CRANE | GENERAL ARRANGEMENT DRAWING | Crane & Hoist |  | Workshop Building |  | GENERAL ARRANGEMENT DRAWING for Crane & Hoist |  | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2024-09-12 | 2024-10-12 | 2024-11-11 | 2024-11-26 | 2024-12-11 | 2024-12-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMM-128004 | CRANE - DATA SHEETS FOR STEAM TURBINE BUILDING CRANE | DATA SHEETS | Crane & Hoist |  | Steam Turbine Building |  | DATA SHEETS for Crane & Hoist | Crane,hoist | FI | 0CF2010W42A07 | (Crane & Hoist) Crane Erection for STG Building | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2008-07-17 | 2008-09-17 | 2025-08-08 | 2025-09-07 | 2025-10-07 | 2025-10-22 | 2025-11-06 | 2025-11-21 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMS-128005 | CRANE - DATA SHEETS FOR WORKSHOP CRANE | DATA SHEETS | Crane & Hoist |  | Workshop Building |  | DATA SHEETS for Crane & Hoist | Crane,hoist | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2024-08-22 | 2024-09-21 | 2024-10-21 | 2024-11-05 | 2024-11-20 | 2024-12-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMM-128007 | CRANE - MECHNICAL DETAIL FOR STEAM TURBINE BUILDING CRANE |  | Crane & Hoist |  | Steam Turbine Building |  | for Crane & Hoist | Crane,hoist | FI | 0CF2010W42A07 | (Crane & Hoist) Crane Erection for STG Building | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2008-07-17 | 2008-09-17 | 2025-04-27 | 2025-05-27 | 2025-06-26 | 2025-07-11 | 2025-07-26 | 2025-08-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMS-128008 | CRANE - MECHNICAL DETAIL FOR WORKSHOP CRANE |  | Crane & Hoist |  | Workshop Building |  | for Crane & Hoist | Crane,hoist | FI | 0PF6030W42A04T | (Crane & Hoist) 1st Delivery | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist |  | 2008-02-15 | 2024-09-24 | 2024-10-24 | 2024-11-23 | 2024-12-08 | 2024-12-23 | 2025-01-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SMM-128010 | CRANE - ELECTRICAL DETAIL FOR STEAM TURBINE BUILDING CRANE |  | Crane & Hoist |  | Steam Turbine Building |  | for Crane & Hoist | Crane,hoist | FI | 0CF2010W42A07 | (Crane & Hoist) Crane Erection for STG Building | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2008-07-17 | 2008-09-17 | 2025-04-27 | 2025-05-27 | 2025-06-26 | 2025-07-11 | 2025-07-26 | 2025-08-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SMS-128011 | CRANE - ELECTRICAL DETAIL FOR WORKSHOP CRANE |  | Crane & Hoist |  | Workshop Building |  | for Crane & Hoist | Crane,hoist | FI | 0PF6030W42A04T | (Crane & Hoist) 1st Delivery | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist |  | 2008-02-15 | 2024-09-24 | 2024-10-24 | 2024-11-23 | 2024-12-08 | 2024-12-23 | 2025-01-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SML-128013 | CRANE - GA DRAWING FOR DEAERATOR SUPPORT STRUCTURE CRANE | GENERAL ARRANGEMENT DRAWING | Crane & Hoist |  |  |  | GENERAL ARRANGEMENT DRAWING for Crane & Hoist |  | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2024-09-12 | 2024-10-12 | 2024-11-11 | 2024-11-26 | 2024-12-11 | 2024-12-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMQ-128014 | HOIST - GA DRAWING FOR FF PUMP HOUSE HOIST | GENERAL ARRANGEMENT DRAWING | Hoist |  | Fire Pump House |  | GENERAL ARRANGEMENT DRAWING for Hoist |  | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2024-09-12 | 2024-10-12 | 2024-11-11 | 2024-11-26 | 2024-12-11 | 2024-12-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMU-128015 | HOIST - GA DRAWING FOR AIR COMPRSSOR HOUSE HOIST | GA DRAWING | HOIST |  |  |  | General Arrangement Drawing for HOIST |  | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2024-09-12 | 2024-10-12 | 2024-11-11 | 2024-11-26 | 2024-12-11 | 2024-12-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMG-128016 | HOIST - GA DRAWING FOR DM WATER TREATMENT HOIST | GA DRAWING | HOIST |  |  |  | General Arrangement Drawing for HOIST |  | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2024-09-12 | 2024-10-12 | 2024-11-11 | 2024-11-26 | 2024-12-11 | 2024-12-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMU-128017 | HOIST - GA DRAWING FOR CHAIN BLOCK | GA DRAWING | HOIST |  |  |  | General Arrangement Drawing for HOIST |  | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2024-09-12 | 2024-10-12 | 2024-11-11 | 2024-11-26 | 2024-12-11 | 2024-12-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SML-128018 | CRANE - DATA SHEETS FOR DEAERATOR SUPPORT STRUCTURE CRANE | DATA SHEETS | CRANE |  |  |  | DATA SHEETS for CRANE | Crane,hoist | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2024-08-22 | 2024-09-21 | 2024-10-21 | 2024-11-05 | 2024-11-20 | 2024-12-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMQ-128019 | HOIST - DATA SHEETS FOR FF PUMP HOUSE HOIST | DATA SHEETS | HOIST |  |  |  | DATA SHEETS for HOIST | Crane,hoist | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2024-08-22 | 2024-09-21 | 2024-10-21 | 2024-11-05 | 2024-11-20 | 2024-12-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMU-128020 | HOIST - DATA SHEETS FOR AIR COMPRSSOR HOUSE HOIST | DATA SHEETS | HOIST |  |  |  | DATA SHEETS for HOIST | Crane,hoist | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2024-08-22 | 2024-09-21 | 2024-10-21 | 2024-11-05 | 2024-11-20 | 2024-12-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMG-128021 | HOIST - DATA SHEETS FOR DM WATER TREATMENT HOIST | DATA SHEETS | HOIST |  |  |  | DATA SHEETS for HOIST | Crane,hoist | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2024-08-22 | 2024-09-21 | 2024-10-21 | 2024-11-05 | 2024-11-20 | 2024-12-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMU-128022 | HOIST - DATA SHEETS FOR CHAIN BLOCK | DATA SHEETS | HOIST |  |  |  | DATA SHEETS for HOIST | Crane,hoist | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2024-08-22 | 2024-09-21 | 2024-10-21 | 2024-11-05 | 2024-11-20 | 2024-12-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SML-128023 | CRANE - MECHNICAL DETAIL FOR DEAERATOR SUPPORT STRUCTURE CRANE | MECHNICAL DETAIL | CRANE |  |  |  | MECHNICAL DETAIL for CRANE | Crane,hoist | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2024-08-15 | 2024-09-14 | 2024-10-14 | 2024-10-29 | 2024-11-13 | 2024-11-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMQ-128024 | HOIST - MECHANICAL DETAIL FOR FF PUMP HOUSE HOIST | MECHANICAL DETAIL | HOIST |  |  |  | MECHANICAL DETAIL for HOIST |  | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2025-04-13 | 2025-05-13 | 2025-06-12 | 2025-06-27 | 2025-07-12 | 2025-07-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMU-128025 | HOIST - MECHANICAL DETAIL FOR AIR COMPRSSOR HOUSE HOIST | MECHANICAL DETAIL | HOIST |  |  |  | MECHANICAL DETAIL for HOIST |  | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2025-04-13 | 2025-05-13 | 2025-06-12 | 2025-06-27 | 2025-07-12 | 2025-07-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMG-128026 | HOIST - MECHANICAL DETAIL FOR DM WATER TREATMENT HOIST | MECHANICAL DETAIL | HOIST |  |  |  | MECHANICAL DETAIL for HOIST |  | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2025-04-13 | 2025-05-13 | 2025-06-12 | 2025-06-27 | 2025-07-12 | 2025-07-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SML-128027 | CRANE - ELECTRICAL DETAIL FOR DEAERATOR SUPPORT STRUCTURE CRANE | ELECTRICAL DETAIL | CRANE |  |  |  | ELECTRICAL DETAIL for CRANE | Crane,hoist | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2024-08-22 | 2024-09-21 | 2024-10-21 | 2024-11-05 | 2024-11-20 | 2024-12-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMC-128028 | HOIST - GA DRAWING FOR CENTRAL CONTROL BUILDING HOIST | GA DRAWING | HOIST |  | CENTRAL CONTROL BUILDING |  | General Arrangement Drawing for HOIST |  | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2024-09-12 | 2024-10-12 | 2024-11-11 | 2024-11-26 | 2024-12-11 | 2024-12-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMS-128029 | HOIST - GA DRAWING FOR WAREHOUSE HOIST | GA DRAWING | HOIST |  |  |  | General Arrangement Drawing for HOIST |  | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2024-09-12 | 2024-10-12 | 2024-11-11 | 2024-11-26 | 2024-12-11 | 2024-12-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMG-128030 | HOIST - GA DRAWING FOR WASTE WATER TREATMENT HOIST | GA DRAWING | HOIST |  |  |  | General Arrangement Drawing for HOIST |  | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2024-09-12 | 2024-10-12 | 2024-11-11 | 2024-11-26 | 2024-12-11 | 2024-12-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMM-128031 | HOIST - GA DRAWING FOR CPP HOIST | GA DRAWING | HOIST |  |  |  | General Arrangement Drawing for HOIST |  | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2024-09-12 | 2024-10-12 | 2024-11-11 | 2024-11-26 | 2024-12-11 | 2024-12-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMU-128032 | JIB CRANE - GA DRAWING FOR AIR COOLED CONDENSER JIB CRANE | GA DRAWING | JIB CRANE |  |  |  | General Arrangement Drawing for JIB CRANE |  | FA | 0CF3510W42A10 | (Crane & Hoist) Crane Erection for Air Compressor Building | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2008-04-16 | 2008-05-16 | 2025-05-29 | 2025-06-28 | 2025-07-28 | 2025-08-12 | 2025-08-27 | 2025-09-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMC-128033 | HOIST - DATA SHEETS FOR CENTRAL CONTROL BUILDING HOIST | DATA SHEETS | HOIST |  | CENTRAL CONTROL BUILDING |  | DATA SHEETS for HOIST | Crane,hoist | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2024-08-22 | 2024-09-21 | 2024-10-21 | 2024-11-05 | 2024-11-20 | 2024-12-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMS-128034 | HOIST - DATA SHEETS FOR WAREHOUSE HOIST | DATA SHEETS | HOIST |  |  |  | DATA SHEETS for HOIST | Crane,hoist | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2024-08-22 | 2024-09-21 | 2024-10-21 | 2024-11-05 | 2024-11-20 | 2024-12-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMG-128035 | HOIST - DATA SHEETS FOR WASTE WATER TREATMENT HOIST | DATA SHEETS | HOIST |  |  |  | DATA SHEETS for HOIST | Crane,hoist | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2024-08-22 | 2024-09-21 | 2024-10-21 | 2024-11-05 | 2024-11-20 | 2024-12-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMM-128036 | HOIST - DATA SHEETS FOR CPP HOIST | DATA SHEETS | HOIST |  |  |  | DATA SHEETS for HOIST | Crane,hoist | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2024-08-22 | 2024-09-21 | 2024-10-21 | 2024-11-05 | 2024-11-20 | 2024-12-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SMU-128037 | JIB CRANE - DATA SHEETS FOR AIR COOLED CONDENSER JIB CRANE | DATA SHEETS | JIB CRANE |  |  |  | DATA SHEETS for JIB CRANE | Crane,hoist | FI | 0CF3510W42A10 | (Crane & Hoist) Crane Erection for Air Compressor Building | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2008-04-16 | 2008-05-16 | 2025-05-08 | 2025-06-07 | 2025-07-07 | 2025-07-22 | 2025-08-06 | 2025-08-21 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMC-128038 | HOIST - MECHANICAL DETAIL FOR CENTRAL CONTROL BUILDING HOIST | DETAIL | HOIST |  | CENTRAL CONTROL BUILDING |  | Detail Drawing for HOIST |  | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2025-04-13 | 2025-05-13 | 2025-06-12 | 2025-06-27 | 2025-07-12 | 2025-07-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMS-128039 | HOIST - MECHANICAL DETAIL FOR WAREHOUSE HOIST | DETAIL | HOIST |  | WAREHOUSE |  | Detail Drawing for HOIST |  | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2025-04-13 | 2025-05-13 | 2025-06-12 | 2025-06-27 | 2025-07-12 | 2025-07-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMG-128040 | HOIST - MECHANICAL DETAIL FOR WASTE WATER TREATMENT HOIST | DETAIL | HOIST |  |  |  | Detail Drawing for HOIST |  | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2025-04-13 | 2025-05-13 | 2025-06-12 | 2025-06-27 | 2025-07-12 | 2025-07-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMM-128041 | HOIST - MECHANICAL DETAIL FOR CPP HOIST | DETAIL | HOIST |  |  |  | Detail Drawing for HOIST |  | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2025-04-13 | 2025-05-13 | 2025-06-12 | 2025-06-27 | 2025-07-12 | 2025-07-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SMU-128042 | JIB CRANE - MECHANICAL DETAIL FOR AIR COOLED CONDENSER JIB CRANE | DETAIL | JIB CRANE |  |  |  | Detail Drawing for JIB CRANE |  | FI | 0CF3510W42A10 | (Crane & Hoist) Crane Erection for Air Compressor Building | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2008-04-16 | 2008-05-16 | 2025-06-12 | 2025-07-12 | 2025-08-11 | 2025-08-26 | 2025-09-10 | 2025-09-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SMC-128043 | HOIST - ELECTRICAL DETAIL FOR CENTRAL CONTROL BUILDING HOIST | DETAIL | HOIST |  | CENTRAL CONTROL BUILDING |  | Detail Drawing for HOIST |  | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2025-04-13 | 2025-05-13 | 2025-06-12 | 2025-06-27 | 2025-07-12 | 2025-07-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SMS-128044 | HOIST - ELECTRICAL DETAIL FOR WAREHOUSE HOIST | DETAIL | HOIST |  | WAREHOUSE |  | Detail Drawing for HOIST |  | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2025-04-13 | 2025-05-13 | 2025-06-12 | 2025-06-27 | 2025-07-12 | 2025-07-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SMQ-128045 | HOIST - ELECTRICAL DETAIL FOR FF PUMP HOUSE HOIST | DETAIL | HOIST |  |  |  | Detail Drawing for HOIST |  | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2025-04-13 | 2025-05-13 | 2025-06-12 | 2025-06-27 | 2025-07-12 | 2025-07-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SMU-128046 | HOIST - ELECTRICAL DETAIL FOR AIR COMPRSSOR HOUSE HOIST | DETAIL | HOIST |  |  |  | Detail Drawing for HOIST |  | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2025-04-13 | 2025-05-13 | 2025-06-12 | 2025-06-27 | 2025-07-12 | 2025-07-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SMG-128047 | HOIST - ELECTRICAL DETAIL FOR DM WATER TREATMENT HOIST | DETAIL | HOIST |  |  |  | Detail Drawing for HOIST |  | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2025-04-13 | 2025-05-13 | 2025-06-12 | 2025-06-27 | 2025-07-12 | 2025-07-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SMG-128048 | HOIST - ELECTRICAL DETAIL FOR WASTE WATER TREATMENT HOIST | DETAIL | HOIST |  |  |  | Detail Drawing for HOIST |  | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2025-04-13 | 2025-05-13 | 2025-06-12 | 2025-06-27 | 2025-07-12 | 2025-07-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS18-P0SMM-128049 | HOIST - ELECTRICAL DETAIL FOR CPP HOIST | DETAIL | HOIST |  |  |  | Detail Drawing for HOIST |  | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2025-04-13 | 2025-05-13 | 2025-06-12 | 2025-06-27 | 2025-07-12 | 2025-07-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMG-128051 | JIB CRANE - GA DRAWING FOR ATM. FLESH TANK DRAIN PUMP JIB CRANE | GENERAL ARRANGEMENT DRAWING | JIB CRANE |  |  |  | GENERAL ARRANGEMENT DRAWING for JIB CRANE |  | FA | 0PF3025W42A18P | (Gantry Crane) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-09-28 | 2008-06-14 | 2024-11-09 | 2024-12-09 | 2025-01-08 | 2025-01-23 | 2025-02-07 | 2025-02-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMG-128052 | JIB CRANE - DATA SHEETS FOR ATM. FLESH TANK DRAIN PUMP JIB CRANE | DATA SHEETS | JIB CRANE |  |  |  | DATA SHEETS for JIB CRANE | Crane,hoist | FI | 0PF3025W42A18P | (Gantry Crane) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-09-28 | 2008-06-14 | 2024-10-19 | 2024-11-18 | 2024-12-18 | 2025-01-02 | 2025-01-17 | 2025-02-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMG-128053 | JIB CRANE - MECHANICAL DETAIL FOR ATM. FLESH TANK DRAIN PUMP JIB CRANE | DETAIL | JIB CRANE |  |  |  | Detail Drawing for JIB CRANE |  | FI | 0PF3025W42A18P | (Gantry Crane) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-09-28 | 2008-06-14 | 2024-11-23 | 2024-12-23 | 2025-01-22 | 2025-02-06 | 2025-02-21 | 2025-03-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMS-128060 | PORTABLE GANTRY - GA DRAWING | GENERAL ARRANGEMENT DRAWING | PORTABLE GANTRY |  |  |  | GENERAL ARRANGEMENT DRAWING for PORTABLE GANTRY |  | FA | 0PF3025W42A18P | (Gantry Crane) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-09-28 | 2008-06-14 | 2024-11-09 | 2024-12-09 | 2025-01-08 | 2025-01-23 | 2025-02-07 | 2025-02-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMU-128070 | HOIST - GA DRAWING FOR ST GSUT | GENERAL ARRANGEMENT DRAWING | HOIST |  |  |  | GENERAL ARRANGEMENT DRAWING for HOIST |  | FA | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2024-09-12 | 2024-10-12 | 2024-11-11 | 2024-11-26 | 2024-12-11 | 2024-12-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMM-128101 | CRANE - NAME PLATE DRAWING FOR STEAM TURBINE BUILDING CRANE | DRAWING | CRANE |  | STEAM TURBINE BUILDING |  | DRAWING for CRANE | Crane,hoist | FI | 0CF2010W42A07 | (Crane & Hoist) Crane Erection for STG Building | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2008-07-17 | 2008-09-17 | 2025-08-29 | 2025-09-28 | 2025-10-28 | 2025-11-12 | 2025-11-27 | 2025-12-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SMS-128102 | CRANE - NAME PLATE DRAWING FOR WORKSHOP CRANE | DRAWING | CRANE |  | WORKSHOP |  | DRAWING for CRANE | Crane,hoist | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2024-09-12 | 2024-10-12 | 2024-11-11 | 2024-11-26 | 2024-12-11 | 2024-12-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SML-128103 | CRANE - NAME PLATE DRAWING FOR DEAERATOR SUPPORT STRUCTURE CRANE | DRAWING | CRANE |  |  |  | DRAWING for CRANE | Crane,hoist | FI | 0PF6030W42A02P | (Crane & Hoist) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2007-08-01 | 2008-05-06 | 2024-09-12 | 2024-10-12 | 2024-11-11 | 2024-11-26 | 2024-12-11 | 2024-12-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0GM-128501 | SUMP PUMP - PUMP OUTLINE DRAWING | DRAWING | SUMP PUMP |  |  |  | DRAWING for SUMP PUMP |  | FA | 0PF3010W42A04P | (Make-up WTR Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System > Make-up Water Pump | 2007-08-02 | 2008-04-02 | 2024-08-30 | 2024-09-29 | 2024-10-29 | 2024-11-13 | 2024-11-28 | 2024-12-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0GM-128502 | SUMP PUMP - DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET & CHARACTERISTIC CURVE | SUMP PUMP |  |  |  | DATA SHEET & CHARACTERISTIC CURVE for SUMP PUMP |  | FA | 0EF3025W00A10 | (Intake Pump Station) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-04-03 |  | 2024-05-01 | 2024-05-31 | 2024-06-30 | 2024-07-15 | 2024-07-30 | 2024-08-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0GM-128503 | SUMP PUMP - PUMP SECTIONAL DRAWING | DRAWING | SUMP PUMP |  |  |  | DRAWING for SUMP PUMP |  | FA | 0PF3010W42A04P | (Make-up WTR Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System > Make-up Water Pump | 2007-08-02 | 2008-04-02 | 2024-08-30 | 2024-09-29 | 2024-10-29 | 2024-11-13 | 2024-11-28 | 2024-12-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XK00-P0GM-128504 | SUMP PUMP - MECHANICAL SEAL SPECIFICATION | SPECIFICATION | SUMP PUMP |  |  |  | Technical Specification for SUMP PUMP |  | FA | 0PF3010W42A04P | (Make-up WTR Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System > Make-up Water Pump | 2007-08-02 | 2008-04-02 | 2025-01-13 | 2025-02-12 | 2025-03-14 | 2025-03-29 | 2025-04-13 | 2025-04-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XK00-P0GM-128505 | SUMP PUMP - COUPLING SPECIFICATION | SPECIFICATION | SUMP PUMP |  |  |  | Technical Specification for SUMP PUMP |  | FA | 0PF3010W42A04P | (Make-up WTR Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System > Make-up Water Pump | 2007-08-02 | 2008-04-02 | 2025-01-13 | 2025-02-12 | 2025-03-14 | 2025-03-29 | 2025-04-13 | 2025-04-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB00-P0GM-128506 | SUMP PUMP - FOUNDATION DRAWINGS | DRAWINGS | SUMP PUMP |  |  |  | DRAWINGS for SUMP PUMP |  | FA | 0PF3010W42A04P | (Make-up WTR Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System > Make-up Water Pump | 2007-08-02 | 2008-04-02 | 2024-08-30 | 2024-09-29 | 2024-10-29 | 2024-11-13 | 2024-11-28 | 2024-12-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0GM-128507 | SUMP PUMP - MOTOR SPECIFICATION | SPECIFICATION | SUMP PUMP |  |  |  | Technical Specification for SUMP PUMP |  | FA | 0PF3010W42A04P | (Make-up WTR Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System > Make-up Water Pump | 2007-08-02 | 2008-04-02 | 2025-01-13 | 2025-02-12 | 2025-03-14 | 2025-03-29 | 2025-04-13 | 2025-04-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0GM-128508 | SUMP PUMP - INSTRUMENT SPECIFICATION | SPECIFICATION | SUMP PUMP |  |  |  | Technical Specification for SUMP PUMP |  | FA | 0PF3010W42A04P | (Make-up WTR Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System > Make-up Water Pump | 2007-08-02 | 2008-04-02 | 2025-01-13 | 2025-02-12 | 2025-03-14 | 2025-03-29 | 2025-04-13 | 2025-04-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0GM-128509 | SUMP PUMP - INSTRUMENTATION HOOK - UP DRAWING | HOOK - UP DRAWING | SUMP PUMP |  |  |  | HOOK - UP DRAWING for SUMP PUMP | SumpPump | FI | 0PF3010W42A04P | (Make-up WTR Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System > Make-up Water Pump | 2007-08-02 | 2008-04-02 | 2024-11-22 | 2024-12-22 | 2025-01-21 | 2025-02-05 | 2025-02-20 | 2025-03-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XF00-P0GM-128510 | SUMP PUMP - NAME PLATE DRAWING | DRAWING | SUMP PUMP |  |  |  | DRAWING for SUMP PUMP |  | FA | 0PF3010W42A04P | (Make-up WTR Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System > Make-up Water Pump | 2007-08-02 | 2008-04-02 | 2024-08-30 | 2024-09-29 | 2024-10-29 | 2024-11-13 | 2024-11-28 | 2024-12-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0GM-128511 | SUMP PUMP - SCHEMATIC AND WIRING DIAGRAM WITH CONTROL PANEL LAYOUT DRAWING FOR WASTE WATER TRANSFER SYSTEM | DIAGRAM WITH CONTROL PANEL LAYOUT DRAWING | SUMP PUMP | Waste Water Transfer System |  |  | DIAGRAM WITH CONTROL PANEL LAYOUT DRAWING for SUMP PUMP |  | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0GM-128512 | SUMP PUMP - INSTRUMENT LIST | INSTRUMENT LIST | SUMP PUMP |  |  |  | INSTRUMENT LIST for SUMP PUMP |  | FA | 0PF3010W42A04P | (Make-up WTR Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System > Make-up Water Pump | 2007-08-02 | 2008-04-02 | 2025-02-11 | 2025-03-13 | 2025-04-12 | 2025-04-27 | 2025-05-12 | 2025-05-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0GHC-129001 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING |  |  |  |  | GENERAL ARRANGEMENT DRAWING |  | FA | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  | 2024-10-12 | 2024-11-11 | 2024-12-11 | 2024-12-26 | 2025-01-10 | 2025-01-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0GHC-129002 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET & CHARACTERISTIC CURVE |  |  |  |  | DATA SHEET & CHARACTERISTIC CURVE |  | FA | 0EF3035W00A02.0 | (SWS) Service Water Supply pump Key data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-04-27 | 2007-05-31 | 2024-05-25 | 2024-06-24 | 2024-07-24 | 2024-08-08 | 2024-08-23 | 2024-09-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0GHC-129003 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - PUMP SECTIONAL DRAWING | DRAWING |  |  |  |  | DRAWING |  | FA | 3PF3030W42A04P | (ACW PUMP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Auxiliary Cooling Water System | 2007-10-03 | 2008-12-01 | 2024-11-14 | 2024-12-14 | 2025-01-13 | 2025-01-28 | 2025-02-12 | 2025-02-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0GHC-129004 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - MECHANICAL SEAL SPECIFICATION | SPECIFICATION |  |  |  |  | Technical Specification |  | FA | 3PF3030W42A04P | (ACW PUMP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Auxiliary Cooling Water System | 2007-10-03 | 2008-12-01 | 2024-10-17 | 2024-11-16 | 2024-12-16 | 2024-12-31 | 2025-01-15 | 2025-01-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YM01-P0GHC-129008 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - MOTOR DATA SHEET & CHARACTERISTIC CURVE | MOTOR DATA SHEET & CHARACTERISTIC CURVE |  |  |  |  | MOTOR DATA SHEET & CHARACTERISTIC CURVE |  | FA | 0EF3035W00A02.0 | (SWS) Service Water Supply pump Key data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-04-27 | 2007-05-31 | 2024-05-25 | 2024-06-24 | 2024-07-24 | 2024-08-08 | 2024-08-23 | 2024-09-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0GHC-129011 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - INSTRUMENT LIST AND DATA SHEET | INSTRUMENT LIST AND DATA SHEET | PUMPS |  |  |  | INSTRUMENT LIST AND DATA SHEET for PUMPS |  | FI | 3PF3030W42A04P | (ACW PUMP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Auxiliary Cooling Water System | 2007-10-03 | 2008-12-01 | 2024-12-26 | 2025-01-25 | 2025-02-24 | 2025-03-11 | 2025-03-26 | 2025-04-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0GHC-129013 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - INSTRUMENTATION HOOK - UP DRAWING | INSTRUMENTATION HOOK - UP DRAWING |  |  |  |  | INSTRUMENTATION HOOK - UP DRAWING |  | FI | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | 2024-07-05 | 2024-08-04 | 2024-09-03 | 2024-09-18 | 2024-10-03 | 2024-10-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL22-P0GHC-129014 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - NAME PLATE DRAWING | NAME PLATE DRAWING |  |  |  |  | NAME PLATE DRAWING |  | FI | 3PF3030W42A04P | (ACW PUMP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Auxiliary Cooling Water System | 2007-10-03 | 2008-12-01 | 2025-02-20 | 2025-03-22 | 2025-04-21 | 2025-05-06 | 2025-05-21 | 2025-06-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0GHC-129031 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | Fuel Gas Package |  |  |  | GENERAL ARRANGEMENT DRAWING for FGP |  | FA | 2EF3520W00A28 | (GT/HRSG GPRS Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-06-01 |  | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0GHC-129032 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET & CHARACTERISTIC CURVE | Fuel Gas Package |  |  |  | DATA SHEET & CHARACTERISTIC CURVE for FGP |  | FA | 1EF3520W00A03.1 | (Gas COMP PKG) FGC Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-03-01 | 2007-03-01 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0GHC-129033 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - PUMP SECTIONAL DRAWING | PUMP SECTIONAL DRAWING | Fuel Gas Package |  |  |  | PUMP SECTIONAL DRAWING for FGP |  | FA | 0PF3520W42A08P | (Condensate Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-07-27 | 2024-08-26 | 2024-09-25 | 2024-10-10 | 2024-10-25 | 2024-11-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0GHC-129034 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - MECHANICAL SEAL SPECIFICATION | MECHANICAL SEAL SPECIFICATION | Fuel Gas Package |  |  |  | MECHANICAL SEAL SPECIFICATION for FGP |  | FA | 2CF3520W42A10.1 | (Gas COMP PKG #21) Installation_Seal Gas Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2008-08-01 | 2008-09-02 |  |  |  | 2025-05-04 | 2025-06-03 | 2025-07-03 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-YM01-P0GHC-129035 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - MOTOR DATA SHEET & CHARACTERISTIC CURVE | MOTOR DATA SHEET & CHARACTERISTIC CURVE | Fuel Gas Package |  |  |  | MOTOR DATA SHEET & CHARACTERISTIC CURVE for FGP |  | FA | 2PF3520W42A05.1P | (Gas COMP PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-03-15 | 2008-05-14 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0GHC-129036 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - INSTRUMENT LIST AND DATA SHEET | INSTRUMENT LIST AND DATA SHEET | Fuel Gas Package |  |  |  | INSTRUMENT LIST AND DATA SHEET for FGP |  | FI | 2EF1200W00A02 | (GTG #21/#22) Instrument, Service Air, Aux steam Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-03-01 | 2007-03-29 | 2024-05-24 | 2024-06-23 | 2024-07-23 | 2024-08-07 | 2024-08-22 | 2024-09-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0GHC-129037 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - INSTRUMENTATION HOOK - UP DRAWING | INSTRUMENTATION HOOK - UP DRAWING |  |  |  |  | INSTRUMENTATION HOOK - UP DRAWING |  | FI | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | 2024-07-05 | 2024-08-04 | 2024-09-03 | 2024-09-18 | 2024-10-03 | 2024-10-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL22-P0GHC-129038 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - NAME PLATE DRAWING | NAME PLATE DRAWING |  |  |  |  | NAME PLATE DRAWING |  | FI | 2PF3020W42A18.1P | (Clean Drain Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | 2007-10-03 | 2008-08-18 | 2025-02-20 | 2025-03-22 | 2025-04-21 | 2025-05-06 | 2025-05-21 | 2025-06-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0GHC-129050 | CHILLED WATER DISTRIBUTION PUMP - DATA SHEET & CHARACTERISTIC CURVE | DATA SHEET & CHARACTERISTIC CURVE | Pump |  |  |  | DATA SHEET & CHARACTERISTIC CURVE for Pump |  | FA | 0EF3035W00A02.0 | (SWS) Service Water Supply pump Key data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-04-27 | 2007-05-31 | 2024-05-25 | 2024-06-24 | 2024-07-24 | 2024-08-08 | 2024-08-23 | 2024-09-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0GHC-129051 | CHILLED WATER DISTRIBUTION PUMP - GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | Pump |  |  |  | GENERAL ARRANGEMENT DRAWING for Pump |  | FA | 1PF3030W42A04P | (ACW PUMP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | 2007-10-03 | 2008-09-30 | 2024-11-14 | 2024-12-14 | 2025-01-13 | 2025-01-28 | 2025-02-12 | 2025-02-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0GHC-129053 | CHILLED WATER DISTRIBUTION PUMP - PUMP SECTIONAL DRAWING | PUMP SECTIONAL DRAWING | Pump |  |  |  | PUMP SECTIONAL DRAWING for Pump |  | FA | 1PF3030W42A04P | (ACW PUMP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | 2007-10-03 | 2008-09-30 | 2024-11-28 | 2024-12-28 | 2025-01-27 | 2025-02-11 | 2025-02-26 | 2025-03-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0GHC-129055 | CHILLED WATER DISTRIBUTION PUMP - MECHANICAL SEAL SPECIFICATION | MECHANICAL SEAL SPECIFICATION | Pump |  |  |  | MECHANICAL SEAL SPECIFICATION for Pump |  | FA | 0EF3010W42A03 | (Make-up WTR Pump) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System > Make-up Water Pump |  | 2007-05-01 | [6 empty] | missing_date |  | 6210
Fadhili_MDL.xlsx | T16182-YL22-P0GHC-129056 | CHILLED WATER DISTRIBUTION PUMP - NAME PLATE DRAWING | NAME PLATE DRAWING | Pump |  |  |  | NAME PLATE DRAWING for Pump |  | FI | 1PF3030W42A04P | (ACW PUMP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | 2007-10-03 | 2008-09-30 | 2025-02-20 | 2025-03-22 | 2025-04-21 | 2025-05-06 | 2025-05-21 | 2025-06-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YM01-P0GHC-129060 | CHILLED WATER DISTRIBUTION PUMP - MOTOR DATA SHEET & CHARACTERISTIC CURVE | MOTOR DATA SHEET & CHARACTERISTIC CURVE | Pump |  |  |  | MOTOR DATA SHEET & CHARACTERISTIC CURVE for Pump |  | FA | 0EF3035W00A02.0 | (SWS) Service Water Supply pump Key data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-04-27 | 2007-05-31 | 2024-05-25 | 2024-06-24 | 2024-07-24 | 2024-08-08 | 2024-08-23 | 2024-09-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0GHC-129063 | CHILLED WATER DISTRIBUTION PUMP - INSTRUMENT LIST AND DATA SHEET | INSTRUMENT LIST AND DATA SHEET | Pump |  |  |  | INSTRUMENT LIST AND DATA SHEET for Pump |  | FI | 0EF3025W00A10 | (Intake Pump Station) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-04-03 |  | 2024-06-26 | 2024-07-26 | 2024-08-25 | 2024-09-09 | 2024-09-24 | 2024-10-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0GHC-129064 | CHILLED WATER DISTRIBUTION PUMP - INSTRUMENTATION HOOK - UP DRAWING | INSTRUMENTATION HOOK - UP DRAWING |  |  |  |  | INSTRUMENTATION HOOK - UP DRAWING |  | FI | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | 2024-07-05 | 2024-08-04 | 2024-09-03 | 2024-09-18 | 2024-10-03 | 2024-10-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0GCF-130001 | SYSTEM DESCRIPTION FOR WATER TREATMENT PLANT | SYSTEM DESCRIPTION | Water Treatment Plant |  |  |  | System Description for Water Treatment Plant | Water Treatment System | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0GCF-130002 | GENERAL ARRANGEMENT DRAWING FOR WATER TREATMENT PLANT | GENERAL ARRANGEMENT DRAWING | Water Treatment Plant |  |  |  | GENERAL ARRANGEMENT DRAWING for Water Treatment Plant | Water Treatment System | FA | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 |  | 2024-12-02 | 2025-01-01 | 2025-01-31 | 2025-02-15 | 2025-03-02 | 2025-03-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0GCF-130003 | PROCESS FLOW DIAGRAM FOR WATER TREATMENT PLANT | PROCESS FLOW DIAGRAM | Water Treatment Plant |  |  |  | PROCESS FLOW DIAGRAM for Water Treatment Plant | Water Treatment System | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0GCF-130004 | PIPING & INSTRUMENT DIAGRAM FOR WATER TREATMENT PLANT | PIPING & INSTRUMENT DIAGRAM | Water Treatment Plant |  |  |  | PIPING & INSTRUMENT DIAGRAM for Water Treatment Plant | Water Treatment System | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0GCF-130005 | CALCULATION SHEET FOR WATER TREATMENT PLANT | CALCULATION SHEET | Water Treatment Plant |  |  |  | CALCULATION SHEET for Water Treatment Plant | Water Treatment System | FA | 0PF3010W42A05P | (WTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-08-31 | 2008-09-01 | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0GCF-130006 | MCC ARRANGEMENT DRAWING FOR WATER AND WASTE WATER TREATMENT PLANT | DRAWING | Motor Control Center |  |  |  | DRAWING for Motor Control Center |  | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0GCF-130007 | CONTROL PANEL ARRANGEMENT DRAWING FOR WATER AND WASTE WATER TREATMENT PLANT | DRAWING | CONTROL PANEL |  |  |  | DRAWING for CONTROL PANEL |  | FA | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 |  |  |  |  | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0GCF-130008 | VALVE LIST FOR WATER TREATMENT PLANT | VALVE LIST | Water Treatment Plant |  |  |  | VALVE LIST for Water Treatment Plant | Water Treatment System | FI | 0EF6020W00A05 | (BOP Piping) Valve List | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-04-30 | 2008-01-03 | 2024-07-29 | 2024-08-28 | 2024-09-27 | 2024-10-12 | 2024-10-27 | 2024-11-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0GCF-130009 | INSTRUMENT LIST FOR WATER TREATMENT PLANT | INSTRUMENT LIST | Water Treatment Plant |  |  |  | INSTRUMENT LIST for Water Treatment Plant | Water Treatment System | FI | 0PF3010W42A05P | (WTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-08-31 | 2008-09-01 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0GCF-130010 | SINGLE LINE DIAGRAM FOR WATER AND WASTE WATER TREATMENT PLANT | SINGLE LINE DIAGRAM | Water and Waste Water Treatment Plant |  |  |  | Single Line Diagram for Water and Waste Water Treatment Plant | Water Treatment System | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | 2024-06-01 | 2024-07-01 | 2024-07-31 | 2024-08-15 | 2024-08-30 | 2024-09-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF02-P0GCF-130011 | CONTROL CONFIGURATION DIAGRAM FOR WATER AND WASTE WATER TREATMENT PLANT | CONTROL CONFIGURATION DIAGRAM | Water and Waste Water Treatment Plant |  |  |  | CONTROL CONFIGURATION DIAGRAM for Water and Waste Water Treatment Plant | Water Treatment System | FI | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0GCF-130012 | EQUIPMENT ASSEMBLY DRAWING FOR WATER TREATMENT PLANT | EQUIPMENT ASSEMBLY DRAWING | Water Treatment Plant |  |  |  | EQUIPMENT ASSEMBLY DRAWING for Water Treatment Plant | Water Treatment System | FI | 0PF3010W42A05P | (WTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-08-31 | 2008-09-01 | 2024-10-30 | 2024-11-29 | 2024-12-29 | 2025-01-13 | 2025-01-28 | 2025-02-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0GCF-130013 | PIPING ARRANGEMENT DRAWING FOR WATER TREATMENT PLANT | DRAWING | Water Treatment Plant | PIPING |  |  | DRAWING for Water Treatment Plant | Water Treatment System | FI | 1CF3010W58A01.1 | (Water Treatment System) Piping Work(Block #1) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Water Treatment Sytstem (BOP) | 2008-10-17 | 2008-12-16 | 2026-03-17 | 2026-04-16 | 2026-05-16 | 2026-05-31 | 2026-06-15 | 2026-06-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0GCF-130014 | TEHCNICAL DATA SHEET FOR WATER TREATMENT PLANT | TEHCNICAL DATA SHEET | Water Treatment Plant |  |  |  | TEHCNICAL DATA SHEET for Water Treatment Plant | Water Treatment System | FI | 0PF3010W42A05P | (WTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-08-31 | 2008-09-01 | 2024-10-30 | 2024-11-29 | 2024-12-29 | 2025-01-13 | 2025-01-28 | 2025-02-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0GCF-130015 | CABLE TRAY LAYOUT DRAWING FOR WATER AND WASTE WATER TREATMENT PLANT | LAYOUT DRAWING | CABLE TRAY |  |  |  | Layout Drawing for CABLE TRAY | Substation | SKIP | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0GCF-130016 | HOOK - UP DRAWING FOR WATER AND WASTE WATER TREATMENT PLANT | HOOK - UP DRAWING | Water and Waste Water Treatment Plant |  |  |  | HOOK - UP DRAWING for Water and Waste Water Treatment Plant | Water Treatment System | FI | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-09-01 | 2025-01-01 | 2025-01-31 | 2025-03-02 | 2025-03-17 | 2025-04-01 | 2025-04-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0GCF-130017 | SCHEMATIC AND WIRING DIAGRAM FOR WATER AND WASTE WATER TREATMENT PLANT | SCHEMATIC AND WIRING DIAGRAM | Water and Waste Water Treatment Plant |  |  |  | SCHEMATIC AND WIRING DIAGRAM for Water and Waste Water Treatment Plant | Water Treatment System | FI | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0GCF-130018 | CONTROL LOOP & LOGIC DIAGRAM FOR WATER AND WASTE WATER TREATMENT PLANT | CONTROL LOOP & LOGIC DIAGRAM | Water and Waste Water Treatment Plant |  |  |  | CONTROL LOOP & LOGIC DIAGRAM for Water and Waste Water Treatment Plant | Water Treatment System | FI | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0GCF-130019 | SLEEVE AND WALL OPENING FOR WATER AND WASTE WATER TREATMENT PLANT |  | Water and Waste Water Treatment Plant |  |  |  | for Water and Waste Water Treatment Plant | WASTE WATER TREATMENT PLANT | FA | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 |  |  |  | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0GCF-130035 | PLC IO LIST FOR WATER AND WASTE WATER TREATMENT PLANT | LIST | Water and Waste Water Treatment Plant |  |  |  | LIST for Water and Waste Water Treatment Plant |  | FA | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-09-01 | 2024-12-14 | 2025-01-13 | 2025-02-12 | 2025-02-27 | 2025-03-14 | 2025-03-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0GCF-130042 | FOUNDATION AND LOADING DATA FOR WATER AND WASTE WATER TREATMENT PLANT | FOUNDATION AND LOADING DATA | Water and Waste Water Treatment Plant |  |  |  | Foundation and Loading Data for Water and Waste Water Treatment Plant | Water Treatment System | FA | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 |  | 2025-01-01 | 2025-01-31 | 2025-03-02 | 2025-03-17 | 2025-04-01 | 2025-04-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0GCF-130055 | PIPING MATERIAL CLASSIFICATION FOR WATER AND WASTE WATER TREATMENT PLANT |  |  | Water and Waste Water Treatment Plant |  |  | for Water and Waste Water Treatment Plant | WASTE WATER TREATMENT PLANT | FA | 0CF4035W58A08.1 | (WWTS) Piping Work for Chemical & Oil | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2008-10-17 | 2009-02-17 |  |  |  | 2025-07-20 | 2025-08-19 | 2025-09-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0GNR-130101 | SYSTEM DESCRIPTION FOR WASTE WATER TREATMENT PLANT | SYSTEM DESCRIPTION |  | Waste Water Treatment Plant |  |  | System Description for Waste Water Treatment Plant | Water Treatment System | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0GNR-130102 | PROCESS FLOW DIAGRAM FOR WASTE WATER TREATMENT PLANT | PROCESS FLOW DIAGRAM |  | Waste Water Treatment Plant |  |  | PROCESS FLOW DIAGRAM for Waste Water Treatment Plant | WASTE WATER TREATMENT PLANT | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0GNR-130103 | PIPING & INSTRUMENT DIAGRAM FOR WASTE WATER TREATMENT PLANT | PIPING & INSTRUMENT DIAGRAM |  | Waste Water Treatment Plant |  |  | PIPING & INSTRUMENT DIAGRAM for Waste Water Treatment Plant | WASTE WATER TREATMENT PLANT | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0GNR-130104 | CALCULATION SHEET FOR WASTE WATER TREATMENT PLANT | CALCULATION SHEET |  | Waste Water Treatment Plant |  |  | CALCULATION SHEET for Waste Water Treatment Plant | Water Treatment System | FA | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-09-01 | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0GNR-130105 | VALVE LIST FOR WASTE WATER TREATMENT PLANT | VALVE LIST |  | Waste Water Treatment Plant |  |  | VALVE LIST for Waste Water Treatment Plant |  | FA | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-09-01 | 2024-12-14 | 2025-01-13 | 2025-02-12 | 2025-02-27 | 2025-03-14 | 2025-03-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0GNR-130106 | INSTRUMENT LIST FOR WASTE WATER TREATMENT PLANT | INSTRUMENT LIST |  | Waste Water Treatment Plant |  |  | INSTRUMENT LIST for Waste Water Treatment Plant |  | FA | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-09-01 | 2024-12-14 | 2025-01-13 | 2025-02-12 | 2025-02-27 | 2025-03-14 | 2025-03-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0GNR-130107 | EQUIPMENT ASSEMBLY DRAWING FOR WASTE WATER TREATMENT PLANT | ASSEMBLY DRAWING |  | Waste Water Treatment Plant |  |  | ASSEMBLY DRAWING for Waste Water Treatment Plant | WASTE WATER TREATMENT PLANT | FA | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 |  |  |  | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0GNR-130108 | TEHCNICAL DATA SHEET FOR WASTE WATER TREATMENT PLANT | TEHCNICAL DATA SHEET |  | Waste Water Treatment Plant |  |  | TEHCNICAL DATA SHEET for Waste Water Treatment Plant | WASTE WATER TREATMENT PLANT | FA | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 |  |  |  |  | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0LD-130201 | SYSTEM DESCRIPTION FOR CONDENSATE POLISHING PLANT | SYSTEM DESCRIPTION |  |  |  |  | System Description |  | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | 2024-05-02 | 2024-05-17 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | generated | 0.60 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LD-130202 | GENERAL ARRANGEMENT DRAWING FOR CONDENSATE POLISHING PLANT | GENERAL ARRANGEMENT DRAWING |  |  |  |  | GENERAL ARRANGEMENT DRAWING |  | FA | 0EF1000W00A03 | Plant General Arrangement | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-10-08 | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0LD-130203 | PROCESS FLOW DIAGRAM FOR CONDENSATE POLISHING PLANT | PROCESS FLOW DIAGRAM |  |  |  |  | PROCESS FLOW DIAGRAM | FireFighting | FA | 0PF3520W42A08P | (Condensate Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-06-15 | 2024-07-20 | 2024-08-24 | 2024-08-10 | 2024-09-14 | 2024-10-19 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0LD-130204 | PIPING & INSTRUMENT DIAGRAM FOR CONDENSATE POLISHING PLANT | PIPING & INSTRUMENT DIAGRAM |  |  |  |  | PIPING & INSTRUMENT DIAGRAM |  | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0LD-130205 | CALCULATION SHEET FOR CONDENSATE POLISHING PLANT | CALCULATION SHEET |  |  |  |  | CALCULATION SHEET |  | FA | 0PF3520W68A04P | (Condensate Tank) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-10-19 | 2024-11-18 | 2024-12-18 | 2025-01-02 | 2025-01-17 | 2025-02-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0LD-130206 | MCC ARRANGEMENT DRAWING FOR CONDENSATE POLISHING PLANT | ARRANGEMENT DRAWING | Motor Control Center |  |  |  | General Arrangement Drawing for Motor Control Center |  | FA | 0EF1000W00A03 | Plant General Arrangement | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-10-08 | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0LD-130207 | CONTROL PANEL ARRANGEMENT DRAWING FOR CONDENSATE POLISHING PLANT | ARRANGEMENT DRAWING |  |  |  |  | General Arrangement Drawing |  | FA | 0EF1000W00A03 | Plant General Arrangement | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-10-08 | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0LD-130208 | VALVE LIST FOR CONDENSATE POLISHING PLANT | VALVE LIST |  |  |  |  | VALVE LIST |  | FA | 0EF6020W00A05 | (BOP Piping) Valve List | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-04-30 | 2008-01-03 | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0LD-130209 | INSTRUMENT LIST FOR CONDENSATE POLISHING PLANT | INSTRUMENT LIST |  |  |  |  | INSTRUMENT LIST |  | FA | 0PF3520W42A08P | (Condensate Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-12-11 | 2025-01-10 | 2025-02-09 | 2025-02-24 | 2025-03-11 | 2025-03-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0LD-130210 | SINGLE LINE DIAGRAM FOR CONDENSATE POLISHING PLANT | SINGLE LINE DIAGRAM |  |  |  |  | Single Line Diagram |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YF02-P0LD-130211 | CONTROL CONFIGURATION DIAGRAM FOR CONDENSATE POLISHING PLANT | CONTROL CONFIGURATION DIAGRAM |  |  |  |  | CONTROL CONFIGURATION DIAGRAM |  | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0LD-130212 | EQUIPMENT ASSEMBLY DRAWING FOR CONDENSATE POLISHING PLANT | EQUIPMENT ASSEMBLY DRAWING |  |  |  |  | EQUIPMENT ASSEMBLY DRAWING |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-01-23 | 2025-02-22 | 2025-03-24 | 2025-04-08 | 2025-04-23 | 2025-05-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LD-130213 | PIPING ARRANGEMENT DRAWING FOR CONDENSATE POLISHING PLANT | ARRANGEMENT DRAWING |  | PIPING |  |  | General Arrangement Drawing for PIPING |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-06-29 | 2024-07-29 | 2024-08-28 | 2024-09-12 | 2024-09-27 | 2024-10-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0LD-130214 | TECHNICAL DATA SHEET FOR CONDENSATE POLISHING PLANT | TECHNICAL DATA SHEET |  |  |  |  | TECHNICAL DATA SHEET |  | FA | 0PF3520W68A04P | (Condensate Tank) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0LD-130215 | CABLE TRAY LAYOUT DRAWING FOR CONDENSATE POLISHING PLANT | LAYOUT DRAWING | Cable Tray |  |  |  | Layout Drawing for Cable Tray | Substation | SKIP | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0LD-130216 | HOOK - UP DRAWING FOR CONDENSATE POLISHING PLANT | HOOK - UP DRAWING |  |  |  |  | HOOK - UP DRAWING |  | FI | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-09-07 | 2024-10-07 | 2024-11-06 | 2024-11-21 | 2024-12-06 | 2024-12-21 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0LD-130217 | SCHEMATIC & WIRING DIAGRAM FOR CONDENSATE POLISHING PLANT | SCHEMATIC & WIRING DIAGRAM |  |  |  |  | SCHEMATIC & WIRING DIAGRAM |  | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0LD-130218 | CONTROL LOOP & LOGIC DIAGRAM FOR CONDENSATE POLISHING PLANT | CONTROL LOOP & LOGIC DIAGRAM |  |  |  |  | CONTROL LOOP & LOGIC DIAGRAM |  | FA | 1SF1265W62A18 | (Control Oil) Loop chek | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | 2008-05-17 | 2008-05-21 | 2025-07-13 | 2025-08-12 | 2025-09-11 | 2025-09-26 | 2025-10-11 | 2025-10-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0LD-130219 | PIPING MATERIAL SPECIFICATION FOR CONDENSATE POLISHING PLANT | MATERIAL SPECIFICATION |  | PIPING |  |  | MATERIAL SPECIFICATION for PIPING | FireFighting | FA | 0EF6020W58A01 | (Piping) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement |  | 2007-07-30 | [6 empty] | missing_date |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0LD-130220 | FOUNDATION AND LOADING DATA FOR CONDENSATE POLISHING PLANT | [6 empty] | Water Treatment System | FA | 0PF3520W68A04P | (Condensate Tank) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YM03-P0LD-130221 | INSTRUMENT LOCATION DRAWING FOR CONDENSATE POLISHING PLANT | LOCATION DRAWING |  | INSTRUMENT |  |  | LOCATION DRAWING for INSTRUMENT |  | FA | 0EF1000W00A10 | Instrument Installation Detail | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-05-11 | 2007-09-28 | 2024-07-06 | 2024-08-05 | 2024-09-04 | 2024-09-19 | 2024-10-04 | 2024-10-19 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0QC-130301 | SYSTEM DESCRIPTION FOR CHEMICAL DOSING SYSTEM | SYSTEM DESCRIPTION |  | CHEMICAL DOSING SYSTEM |  |  | System Description for CHEMICAL DOSING SYSTEM | Chemical Dosing System | FA | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0QC-130302 | GENERAL ARRANGEMENT DRAWING FOR CHEMICAL DOSING SYSTEM | GENERAL ARRANGEMENT DRAWING |  | CHEMICAL DOSING SYSTEM |  |  | GENERAL ARRANGEMENT DRAWING for CHEMICAL DOSING SYSTEM | Chemical Dosing System | FA | 1EF3045W00A06 | (Chemical Dosing BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 |  | 2024-10-26 | 2024-11-25 | 2024-12-25 | 2025-01-09 | 2025-01-24 | 2025-02-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0QC-130303 | PIPING & INSTRUMENT DIAGRAM FOR CHEMICAL DOSING SYSTEM | PIPING & INSTRUMENT DIAGRAM |  | CHEMICAL DOSING SYSTEM |  |  | PIPING & INSTRUMENT DIAGRAM for CHEMICAL DOSING SYSTEM | Chemical Dosing System | FI | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0QC-130304 | CALCULATION SHEET FOR CHEMICAL DOSING SYSTEM | CALCULATION SHEET |  | CHEMICAL DOSING SYSTEM |  |  | CALCULATION SHEET for CHEMICAL DOSING SYSTEM | Chemical Dosing System | FA | 1PF3045W42A03P | (Chemical Dosing Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-07-24 | 2024-10-26 | 2024-11-25 | 2024-12-25 | 2025-01-09 | 2025-01-24 | 2025-02-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0QC-130305 | INSTRUMENT LIST FOR CHEMICAL DOSING SYSTEM | INSTRUMENT LIST |  | CHEMICAL DOSING SYSTEM |  |  | INSTRUMENT LIST for CHEMICAL DOSING SYSTEM | Chemical Dosing System | FA | 1PF3045W42A03P | (Chemical Dosing Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-07-24 | 2024-11-25 | 2024-12-25 | 2025-01-24 | 2025-02-08 | 2025-02-23 | 2025-03-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0QC-130306 | CONTROL PANEL ARRANGEMENT DRAWING FOR CHEMICAL DOSING SYSTEM | ARRANGEMENT DRAWING |  | CHEMICAL DOSING SYSTEM |  |  | General Arrangement Drawing for CHEMICAL DOSING SYSTEM | Chemical Dosing System | FA | 1PF3045W42A03P | (Chemical Dosing Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-07-24 | 2024-10-26 | 2024-11-25 | 2024-12-25 | 2025-01-09 | 2025-01-24 | 2025-02-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0QC-130307 | TECHNICAL DATA SHEET FOR CHEMICAL DOSING SYSTEM | TECHNICAL DATA SHEET |  | CHEMICAL DOSING SYSTEM |  |  | TECHNICAL DATA SHEET for CHEMICAL DOSING SYSTEM | Chemical Dosing System | FA | 1PF3045W42A03P | (Chemical Dosing Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-07-24 | 2024-12-25 | 2025-01-24 | 2025-02-23 | 2025-03-10 | 2025-03-25 | 2025-04-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0QC-130308 | SCHEMATIC & WIRING DIAGRAM FOR CHEMICAL DOSING SYSTEM | SCHEMATIC & WIRING DIAGRAM |  | CHEMICAL DOSING SYSTEM |  |  | SCHEMATIC & WIRING DIAGRAM for CHEMICAL DOSING SYSTEM | Chemical Dosing System | FI | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0QC-130309 | CONTROL LOOP & LOGIC DIAGRAM FOR CHEMICAL DOSING SYSTEM | CONTROL LOOP & LOGIC DIAGRAM |  | CHEMICAL DOSING SYSTEM |  |  | CONTROL LOOP & LOGIC DIAGRAM for CHEMICAL DOSING SYSTEM | Chemical Dosing System | FA | 1SF3045W62A19 | (Chemical Dosing System) Loop chek | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2008-12-28 | 2009-01-11 | 2026-04-28 | 2026-05-28 | 2026-06-27 | 2026-07-12 | 2026-07-27 | 2026-08-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0QU-130401 | SYSTEM DESCRIPTION FOR SAMPLING SYSTEM | SYSTEM DESCRIPTION |  | SAMPLING SYSTEM |  |  | System Description for SAMPLING SYSTEM | Sampling System | FI | 1EF3040W00A01 | (Sampling System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2007-04-02 | 2007-08-31 | 2024-04-03 | 2024-05-03 | 2024-06-02 | 2024-06-17 | 2024-07-02 | 2024-07-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0QU-130402 | GENERAL ARRANGEMENT DRAWING FOR SAMPLING SYSTEM | GENERAL ARRANGEMENT DRAWING |  | SAMPLING SYSTEM |  |  | GENERAL ARRANGEMENT DRAWING for SAMPLING SYSTEM |  | FA | 1PF3040W42A05P | (Sampling Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2007-10-01 | 2008-07-30 | 2024-11-12 | 2024-12-12 | 2025-01-11 | 2025-01-26 | 2025-02-10 | 2025-02-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0QU-130403 | PIPING & INSTRUMENT DIAGRAM FOR SAMPLING SYSTEM | PIPING & INSTRUMENT DIAGRAM |  | SAMPLING SYSTEM |  |  | PIPING & INSTRUMENT DIAGRAM for SAMPLING SYSTEM | Sampling System | FI | 1EF3040W00A01 | (Sampling System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2007-04-02 | 2007-08-31 | 2024-07-01 | 2024-07-31 | 2024-08-30 | 2024-09-14 | 2024-09-29 | 2024-10-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0QU-130404 | INSTRUMENT LIST FOR SAMPLING SYSTEM | INSTRUMENT LIST |  | SAMPLING SYSTEM |  |  | INSTRUMENT LIST for SAMPLING SYSTEM |  | FA | 1PF3040W42A05P | (Sampling Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2007-10-01 | 2008-07-30 | 2025-04-12 | 2025-05-12 | 2025-06-11 | 2025-06-26 | 2025-07-11 | 2025-07-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0QU-130405 | TECHNICAL DATA SHEET FOR SAMPLING SYSTEM | TECHNICAL DATA SHEET |  | SAMPLING SYSTEM |  |  | TECHNICAL DATA SHEET for SAMPLING SYSTEM | Sampling System | FA | 1SF3040W62A13 | (Sampling System) Sampling System Function Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2009-01-26 | 2009-01-30 | 2026-03-28 | 2026-04-27 | 2026-05-27 | 2026-06-11 | 2026-06-26 | 2026-07-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0QU-130406 | SCHEMATIC & WIRING DIAGRAM FOR SAMPLING SYSTEM | SCHEMATIC & WIRING DIAGRAM |  | SAMPLING SYSTEM |  |  | SCHEMATIC & WIRING DIAGRAM for SAMPLING SYSTEM | Sampling System | FI | 1EF3040W00A01 | (Sampling System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2007-04-02 | 2007-08-31 | 2024-07-01 | 2024-07-31 | 2024-08-30 | 2024-09-14 | 2024-09-29 | 2024-10-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0QU-130407 | CONTROL LOOP & LOGIC DIAGRAM FOR SAMPLING SYSTEM | CONTROL LOOP & LOGIC DIAGRAM |  | SAMPLING SYSTEM |  |  | CONTROL LOOP & LOGIC DIAGRAM for SAMPLING SYSTEM |  | FA | 1SF3040W62A11 | (Sampling System) Loop chek | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2009-01-11 | 2009-01-20 | 2026-03-09 | 2026-04-08 | 2026-05-08 | 2026-05-23 | 2026-06-07 | 2026-06-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0STG-130501 | EQUIPMENT SPECIFICATION FOR CHEMICAL LABORATORY | EQUIPMENT SPECIFICATION | Chemical Laboratory Equipment |  |  |  | EQUIPMENT SPECIFICATION for Chemical Laboratory Equipment | Chemical Laboratory Equipment | FA | 0PF3040W42A04P | (Lab) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Laboratory | 2008-03-31 | 2008-10-20 | 2025-05-01 | 2025-05-31 | 2025-06-30 | 2025-07-15 | 2025-07-30 | 2025-08-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0STG-130502 | ARRANGEMENT DRAWING FOR CHEMICAL LABORATORY EQUIPMENT | ARRANGEMENT DRAWING | Chemical Laboratory Equipment |  |  |  | General Arrangement Drawing for Chemical Laboratory Equipment | Chemical Laboratory Equipment | FA | 0PF3040W42A04P | (Lab) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Laboratory | 2008-03-31 | 2008-10-20 | 2025-05-01 | 2025-05-31 | 2025-06-30 | 2025-07-15 | 2025-07-30 | 2025-08-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XL00-P0STG-130503 | EQUIPMENT LIST FOR CHEMICAL LABORATORY | EQUIPMENT LIST |  |  |  |  | EQUIPMENT LIST |  | FI | 0PF3040W42A04P | (Lab) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Laboratory | 2008-03-31 | 2008-10-20 | 2025-06-24 | 2025-07-24 | 2025-08-23 | 2025-09-07 | 2025-09-22 | 2025-10-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0GK-130601 | GENERAL ARRANGEMENT DRAWING FOR POTABLE WATER CHILLER | GENERAL ARRANGEMENT DRAWING |  |  |  |  | GENERAL ARRANGEMENT DRAWING |  | FA | 0PF3035W42A06P | (PWP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-09-03 | 2008-09-01 | 2024-10-15 | 2024-11-14 | 2024-12-14 | 2024-12-29 | 2025-01-13 | 2025-01-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS01-P0GK-130602 | ELECTRICAL DRAWING FOR POTABLE WATER CHILLER | ELECTRICAL DRAWING |  |  |  |  | ELECTRICAL DRAWING |  | FA | 0CF3035W74A09 | (PWS) Installation & Test - Elec. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2008-11-15 | 2008-12-12 |  |  |  | 2025-08-18 | 2025-09-17 | 2025-10-17 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0SAA-133301 | DESIGN CRITERIA FOR HVAC SYSTEM | DESIGN CRITERIA |  | HVAC SYSTEM |  |  | DESIGN CRITERIA for HVAC SYSTEM | Water Treatment System | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK09-P0SAA-133302 | STANDARD DRAIWNG FOR HVAC SYSTEM | STANDARD DRAIWNG |  | HVAC SYSTEM |  |  | STANDARD DRAIWNG for HVAC SYSTEM |  | FI | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 | 2025-02-28 | 2025-03-30 | 2025-04-29 | 2025-05-14 | 2025-05-29 | 2025-06-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAH-133401 | LOAD CALCULATION OF HVAC SYSTEM FOR STEAM TURBINE BUILDING | LOAD CALCULATION |  | HVAC SYSTEM | STEAM TURBINE BUILDING |  | LOAD CALCULATION for HVAC SYSTEM | Water Treatment System | FA | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 | 2024-09-14 | 2024-10-14 | 2024-11-13 | 2024-11-28 | 2024-12-13 | 2024-12-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAH-133402 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR STEAM TURBINE BUILDING | AIR FLOW DIAGRAM |  | HVAC SYSTEM | STEAM TURBINE BUILDING |  | AIR FLOW DIAGRAM for HVAC SYSTEM |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAH-133403 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR STEAM TURBINE BUILDING | EQUIPMENT SCHEDULE |  | HVAC SYSEM | STEAM TURBINE BUILDING |  | EQUIPMENT SCHEDULE for HVAC SYSEM | SECURITY BUILDING | FI | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  |  |  | 2024-12-30 | 2025-01-29 | 2025-02-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAH-133404 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSEM FOR STEAM TURBINE BUILDING | PLAN |  | HVAC SYSEM | STEAM TURBINE BUILDING |  | Plan for HVAC SYSEM |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAC-133501 | LOAD CALCULATION OF HVAC SYSTEM FOR CENTRAL CONTROL BUILDING | LOAD CALCULATION |  | HVAC SYSTEM | CENTRAL CONTROL BUILDING |  | LOAD CALCULATION for HVAC SYSTEM | Water Treatment System | FA | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 | 2025-06-15 | 2025-07-15 | 2025-08-14 | 2025-08-29 | 2025-09-13 | 2025-09-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAC-133502 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR CENTRAL CONTROL BUILDING | AIR FLOW DIAGRAM |  | HVAC SYSTEM | CENTRAL CONTROL BUILDING |  | AIR FLOW DIAGRAM for HVAC SYSTEM |  | FA | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  |  |  | 2025-02-15 | 2025-03-17 | 2025-04-16 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAC-133503 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR CENTRAL CONTROL BUILDING | EQUIPMENT SCHEDULE |  | HVAC SYSEM | CENTRAL CONTROL BUILDING |  | EQUIPMENT SCHEDULE for HVAC SYSEM | SECURITY BUILDING | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  |  |  | 2025-02-15 | 2025-03-17 | 2025-04-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAC-133504 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR CENTRAL CONTROL BUILDING | PLAN |  | Heating, Ventilating and Air - Conditioning System | CENTRAL CONTROL BUILDING |  | Plan for Heating, Ventilating and Air - Conditioning System |  | FA | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  |  |  | 2025-02-15 | 2025-03-17 | 2025-04-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAK-133601 | LOAD CALCULATION OF HVAC SYSTEM FOR WATER TREATMENT BUILDING | LOAD CALCULATION |  | Heating, Ventilating and Air - Conditioning System | WATER TREATMENT BUILDING |  | LOAD CALCULATION for Heating, Ventilating and Air - Conditioning System |  | FA | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  |  |  | 2024-12-30 | 2025-01-29 | 2025-02-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAK-133602 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR WATER TREATMENT BUILDING | AIR FLOW DIAGRAM |  | Heating, Ventilating and Air - Conditioning System | WATER TREATMENT BUILDING |  | AIR FLOW DIAGRAM for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAK-133603 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR WATER TREATMENT BUILDING | EQUIPMENT SCHEDULE |  | Heating, Ventilating and Air - Conditioning System | WATER TREATMENT BUILDING |  | EQUIPMENT SCHEDULE for Heating, Ventilating and Air - Conditioning System | SECURITY BUILDING | FI | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  |  |  | 2024-12-30 | 2025-01-29 | 2025-02-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAK-133604 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR WATER TREATMENT BUILDING | PLAN |  | Heating, Ventilating and Air - Conditioning System | WATER TREATMENT BUILDING |  | Plan for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAJ-133701 | LOAD CALCULATION OF HVAC SYSTEM FOR FGS ELECTRICAL BUILDING | LOAD CALCULATION |  | Heating, Ventilating and Air - Conditioning System | FGS ELECTRICAL BUILDING |  | LOAD CALCULATION for Heating, Ventilating and Air - Conditioning System |  | FA | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  |  |  | 2024-12-30 | 2025-01-29 | 2025-02-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAJ-133702 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR FGS ELECTRICAL BUILDING | AIR FLOW DIAGRAM |  | Heating, Ventilating and Air - Conditioning System | FGS ELECTRICAL BUILDING |  | AIR FLOW DIAGRAM for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAJ-133703 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR FGS ELECTRICAL BUILDING | EQUIPMENT SCHEDULE |  | Heating, Ventilating and Air - Conditioning System | FGS ELECTRICAL BUILDING |  | EQUIPMENT SCHEDULE for Heating, Ventilating and Air - Conditioning System | SECURITY BUILDING | FI | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  |  |  | 2024-12-30 | 2025-01-29 | 2025-02-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAJ-133704 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR FGS ELECTRICAL BUILDING | PLAN |  | Heating, Ventilating and Air - Conditioning System | FGS ELECTRICAL BUILDING |  | Plan for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAI-133801 | LOAD CALCULATION OF HVAC SYSTEM FOR GTG #1/2 LEB | LOAD CALCULATION |  | Heating, Ventilating and Air - Conditioning System | GTG #1/2 Local Electrical Building |  | LOAD CALCULATION for Heating, Ventilating and Air - Conditioning System |  | FA | 1CF1200W36A07 | (GTG #11 LEB) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 LEB | 2008-05-15 | 2008-06-30 |  |  |  | 2025-02-15 | 2025-03-17 | 2025-04-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAI-133802 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR GTG #1/2 LEB | AIR FLOW DIAGRAM |  | Heating, Ventilating and Air - Conditioning System | GTG #1/2 Local Electrical Building |  | AIR FLOW DIAGRAM for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAI-133803 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR GTG #1/2 LEB | EQUIPMENT SCHEDULE |  | Heating, Ventilating and Air - Conditioning System | GTG #1/2 Local Electrical Building |  | EQUIPMENT SCHEDULE for Heating, Ventilating and Air - Conditioning System | SECURITY BUILDING | FI | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  |  |  | 2024-12-30 | 2025-01-29 | 2025-02-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAI-133804 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR GTG #1/2 LEB | PLAN |  | Heating, Ventilating and Air - Conditioning System | GTG #1/2 Local Electrical Building |  | Plan for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAI-133901 | LOAD CALCULATION OF HVAC SYSTEM FOR GTG #3/4/5 LEB | LOAD CALCULATION |  | Heating, Ventilating and Air - Conditioning System | GTG #3/4/5 Local Electrical Building |  | LOAD CALCULATION for Heating, Ventilating and Air - Conditioning System |  | FA | 3CF1200W36A07 | (GTG #31 LEB) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2008-05-15 | 2008-06-30 |  |  |  | 2025-02-15 | 2025-03-17 | 2025-04-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAI-133902 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR GTG #3/4/5 LEB | AIR FLOW DIAGRAM |  | Heating, Ventilating and Air - Conditioning System | GTG #3/4/5 Local Electrical Building |  | AIR FLOW DIAGRAM for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAI-133903 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR GTG #3/4/5 LEB | EQUIPMENT SCHEDULE |  | Heating, Ventilating and Air - Conditioning System | GTG #3/4/5 Local Electrical Building |  | EQUIPMENT SCHEDULE for Heating, Ventilating and Air - Conditioning System | SECURITY BUILDING | FI | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  |  |  | 2024-12-30 | 2025-01-29 | 2025-02-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAI-133904 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR GTG #3/4/5 LEB | PLAN |  | Heating, Ventilating and Air - Conditioning System | GTG #3/4/5 Local Electrical Building |  | Plan for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAL-134001 | LOAD CALCULATION OF HVAC SYSTEM FOR ADMIN & SOCIAL BUILDING | LOAD CALCULATION |  | Heating, Ventilating and Air - Conditioning System | ADMIN & SOCIAL BUILDING |  | LOAD CALCULATION for Heating, Ventilating and Air - Conditioning System |  | FA | 0CF5566W36A07 | (ADMIN BLDG) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-15 | 2008-07-12 |  |  |  | 2025-02-15 | 2025-03-17 | 2025-04-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAL-134002 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR ADMIN & SOCIAL BUILDING | AIR FLOW DIAGRAM |  | Heating, Ventilating and Air - Conditioning System | ADMIN & SOCIAL BUILDING |  | AIR FLOW DIAGRAM for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAL-134003 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR ADMIN & SOCIAL BUILDING | EQUIPMENT SCHEDULE |  | Heating, Ventilating and Air - Conditioning System | ADMIN & SOCIAL BUILDING |  | EQUIPMENT SCHEDULE for Heating, Ventilating and Air - Conditioning System | SECURITY BUILDING | FI | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  |  |  | 2024-12-30 | 2025-01-29 | 2025-02-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAL-134004 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR ADMIN & SOCIAL BUILDING | PLAN |  | Heating, Ventilating and Air - Conditioning System SYSTEM |  |  | Plan for Heating, Ventilating and Air - Conditioning System SYSTEM |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAR-134101 | LOAD CALCULATION OF HVAC SYSTEM FOR ST #1 LEB | CALCULATION |  | Heating, Ventilating and Air - Conditioning System SYSTEM | ST #1 Local Electrical Building |  | Calculation sheet for Heating, Ventilating and Air - Conditioning System SYSTEM | Water Treatment System | FA | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 | 2024-09-14 | 2024-10-14 | 2024-11-13 | 2024-11-28 | 2024-12-13 | 2024-12-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAR-134102 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR ST #1 LEB | AIR FLOW DIAGRAM |  | Heating, Ventilating and Air - Conditioning System SYSTEM | ST #1 Local Electrical Building |  | AIR FLOW DIAGRAM for Heating, Ventilating and Air - Conditioning System SYSTEM |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAR-134103 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR ST#1 LEB | EQUIPMENT SCHEDULE |  | Heating, Ventilating and Air - Conditioning System SYSEM | ST#1 Local Electrical Building |  | EQUIPMENT SCHEDULE for Heating, Ventilating and Air - Conditioning System SYSEM | SECURITY BUILDING | FI | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  |  |  | 2024-12-30 | 2025-01-29 | 2025-02-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAR-134104 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR ST #1 LEB | PLAN |  | Heating, Ventilating and Air - Conditioning System SYSTEM | ST #1 Local Electrical Building |  | Plan for Heating, Ventilating and Air - Conditioning System SYSTEM |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAR-134201 | LOAD CALCULATION OF HVAC SYSTEM FOR ST #2 LEB | CALCULATION |  | Heating, Ventilating and Air - Conditioning System SYSTEM | ST #2 Local Electrical Building |  | Calculation sheet for Heating, Ventilating and Air - Conditioning System SYSTEM | Water Treatment System | FA | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 | 2024-09-14 | 2024-10-14 | 2024-11-13 | 2024-11-28 | 2024-12-13 | 2024-12-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAR-134202 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR ST #2 LEB | AIR FLOW DIAGRAM |  | Heating, Ventilating and Air - Conditioning System SYSTEM | ST #2 Local Electrical Building |  | AIR FLOW DIAGRAM for Heating, Ventilating and Air - Conditioning System SYSTEM |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAR-134203 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR ST#2 LEB | EQUIPMENT SCHEDULE |  | Heating, Ventilating and Air - Conditioning System SYSEM | ST#2 Local Electrical Building |  | EQUIPMENT SCHEDULE for Heating, Ventilating and Air - Conditioning System SYSEM | SECURITY BUILDING | FI | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  |  |  | 2024-12-30 | 2025-01-29 | 2025-02-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAR-134204 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR ST #2 LEB | PLAN |  | Heating, Ventilating and Air - Conditioning System SYSTEM | ST #2 Local Electrical Building |  | Plan for Heating, Ventilating and Air - Conditioning System SYSTEM |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAE-134301 | LOAD CALCULATION OF HVAC SYSTEM FOR MAIN GATE HOUSE | CALCULATION |  | Heating, Ventilating and Air - Conditioning System SYSTEM | MAIN GATE HOUSE |  | Calculation sheet for Heating, Ventilating and Air - Conditioning System SYSTEM | Water Treatment System | FA | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 | 2024-09-14 | 2024-10-14 | 2024-11-13 | 2024-11-28 | 2024-12-13 | 2024-12-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAE-134302 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR MAIN GATE HOUSE | AIR FLOW DIAGRAM |  | Heating, Ventilating and Air - Conditioning System SYSTEM | MAIN GATE HOUSE |  | AIR FLOW DIAGRAM for Heating, Ventilating and Air - Conditioning System SYSTEM |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAE-134303 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR MAIN GATE HOUSE | EQUIPMENT SCHEDULE |  | Heating, Ventilating and Air - Conditioning System SYSEM | MAIN GATE HOUSE |  | EQUIPMENT SCHEDULE for Heating, Ventilating and Air - Conditioning System SYSEM | SECURITY BUILDING | FI | 0CF5570W36A06 | (Gate House) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-05 | 2008-07-01 |  |  |  | 2025-02-05 | 2025-03-07 | 2025-04-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAE-134304 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR MAIN GATE HOUSE | PLAN |  | Heating, Ventilating and Air - Conditioning System SYSTEM | MAIN GATE HOUSE |  | Plan for Heating, Ventilating and Air - Conditioning System SYSTEM |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAN-134401 | LOAD CALCULATION OF HVAC SYSTEM FOR SUPPORT BUILDING | CALCULATION |  | Heating, Ventilating and Air - Conditioning System SYSTEM | SUPPORT BUILDING |  | Calculation sheet for Heating, Ventilating and Air - Conditioning System SYSTEM | Water Treatment System | FA | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 | 2024-09-14 | 2024-10-14 | 2024-11-13 | 2024-11-28 | 2024-12-13 | 2024-12-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAN-134402 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR SUPPORT BUILDING | AIR FLOW DIAGRAM |  | Heating, Ventilating and Air - Conditioning System SYSTEM | SUPPORT BUILDING |  | AIR FLOW DIAGRAM for Heating, Ventilating and Air - Conditioning System SYSTEM |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAN-134403 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR SUPPORT BUILDING | EQUIPMENT SCHEDULE |  | Heating, Ventilating and Air - Conditioning System SYSEM | SUPPORT BUILDING |  | EQUIPMENT SCHEDULE for Heating, Ventilating and Air - Conditioning System SYSEM | SECURITY BUILDING | FI | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  |  |  | 2024-12-30 | 2025-01-29 | 2025-02-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAN-134404 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR SUPPORT BUILDING | PLAN |  | Heating, Ventilating and Air - Conditioning System SYSTEM | SUPPORT BUILDING |  | Plan for Heating, Ventilating and Air - Conditioning System SYSTEM |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAD-134501 | LOAD CALCULATION OF HVAC SYSTEM FOR SECURITY BUILDING | CALCULATION |  | Heating, Ventilating and Air - Conditioning System SYSTEM | SECURITY BUILDING |  | Calculation sheet for Heating, Ventilating and Air - Conditioning System SYSTEM | Water Treatment System | FA | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 | 2024-09-14 | 2024-10-14 | 2024-11-13 | 2024-11-28 | 2024-12-13 | 2024-12-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAD-134502 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR SECURITY BUILDING | AIR FLOW DIAGRAM |  | Heating, Ventilating and Air - Conditioning System SYSTEM | SECURITY BUILDING |  | AIR FLOW DIAGRAM for Heating, Ventilating and Air - Conditioning System SYSTEM |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAD-134503 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR SECURITY BUILDING | EQUIPMENT SCHEDULE |  | Heating, Ventilating and Air - Conditioning System SYSEM | SECURITY BUILDING |  | EQUIPMENT SCHEDULE for Heating, Ventilating and Air - Conditioning System SYSEM | SECURITY BUILDING | FI | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  |  |  | 2024-12-30 | 2025-01-29 | 2025-02-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAD-134504 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR SECURITY BUILDING | PLAN |  | Heating, Ventilating and Air - Conditioning System | SECURITY BUILDING |  | Plan for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAE-134601 | LOAD CALCULATION OF HVAC SYSTEM FOR SEARCH FACILITY & VISITORS CENTRE | LOAD CALCULATION |  | Heating, Ventilating and Air - Conditioning System | SEARCH FACILITY & VISITORS CENTRE |  | LOAD CALCULATION for Heating, Ventilating and Air - Conditioning System |  | FA | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  |  |  | 2024-12-30 | 2025-01-29 | 2025-02-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAE-134602 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR SEARCH FACILITY & VISITORS CENTRE | AIR FLOW DIAGRAM |  | Heating, Ventilating and Air - Conditioning System | SEARCH FACILITY & VISITORS CENTRE |  | AIR FLOW DIAGRAM for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAE-134603 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR SEARCH FACILITY & VISITORS CENTRE |  |  |  | SEARCH FACILITY & VISITORS CENTRE |  | for SEARCH FACILITY & VISITORS CENTRE | Search Facility & Visitor Center | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  |  |  | 2025-02-15 | 2025-03-17 | 2025-04-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAE-134604 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR SEARCH FACILITY & VISITORS CENTRE | PLAN |  | Heating, Ventilating and Air - Conditioning System | SEARCH FACILITY & VISITORS CENTRE |  | Plan for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAF-134701 | LOAD CALCULATION OF HVAC SYSTEM FOR FIRE BRIGADE | LOAD CALCULATION |  | Heating, Ventilating and Air - Conditioning System | FIRE BRIGADE |  | LOAD CALCULATION for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAF-134702 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR FIRE BRIGADE | AIR FLOW DIAGRAM |  | Heating, Ventilating and Air - Conditioning System | FIRE BRIGADE |  | AIR FLOW DIAGRAM for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAF-134703 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR FIRE BRIGADE |  |  |  | FIRE BRIGADE |  | for FIRE BRIGADE | FIRE BRIGADE | FI | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  |  |  | 2024-12-30 | 2025-01-29 | 2025-02-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAF-134704 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR FIRE BRIGADE | PLAN |  | Heating, Ventilating and Air - Conditioning System | FIRE BRIGADE |  | Plan for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAB-134801 | LOAD CALCULATION OF HVAC SYSTEM FOR WORKSHOP & STORAGE BUILDING | LOAD CALCULATION |  | Heating, Ventilating and Air - Conditioning System |  |  | LOAD CALCULATION for Heating, Ventilating and Air - Conditioning System |  | FA | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  |  |  | 2024-12-30 | 2025-01-29 | 2025-02-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAB-134802 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR WORKSHOP & STORAGE BUILDING | AIR FLOW DIAGRAM |  | Heating, Ventilating and Air - Conditioning System |  |  | AIR FLOW DIAGRAM for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAB-134803 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR WORKSHOP & STORAGE BUILDING | [6 empty] | WORKSHOP & STORAGE BUILDING | FI | 0CF5560W36A07 | (M&E WORKSHOP BLDG) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-10-08 | 2008-12-03 |  |  |  | 2025-07-11 | 2025-08-10 | 2025-09-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAB-134804 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR WORKSHOP & STORAGE BUILDING |  |  | Heating, Ventilating and Air - Conditioning System |  |  | for Heating, Ventilating and Air - Conditioning System | Air Compressor | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | [6 empty] | generated |  | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAG-134901 | LOAD CALCULATION OF HVAC SYSTEM FOR FIRE WATER PUMP HOUSE | LOAD CALCULATION |  | Heating, Ventilating and Air - Conditioning System | Fire Pump House |  | LOAD CALCULATION for Heating, Ventilating and Air - Conditioning System |  | FA | 0SF4500W62A14 | (Fire WTR Pump) Load(running) Test | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2008-07-21 | 2008-07-22 |  |  |  | 2025-04-23 | 2025-05-23 | 2025-06-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAG-134902 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR FIRE WATER PUMP HOUSE | AIR FLOW DIAGRAM |  | Heating, Ventilating and Air - Conditioning System | Fire Pump House |  | AIR FLOW DIAGRAM for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAG-134903 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR FIRE WATER PUMP HOUSE |  |  |  | Fire Pump House |  | for Fire Pump House |  | FA | 0CF4500W36A10 | (Fire WTR Pump Shelter) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2008-05-31 | 2008-07-16 | 2026-11-23 | 2026-12-23 | 2027-01-22 | 2027-02-06 | 2027-02-21 | 2027-03-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAG-134904 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR FIRE WATER PUMP HOUSE | PLAN |  | Heating, Ventilating and Air - Conditioning System | Fire Pump House |  | Plan for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAM-135001 | LOAD CALCULATION OF HVAC SYSTEM FOR CPP & CPP REGEN BUILDING | LOAD CALCULATION |  | Heating, Ventilating and Air - Conditioning System |  |  | LOAD CALCULATION for Heating, Ventilating and Air - Conditioning System |  | FA | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 |  |  |  | 2024-12-30 | 2025-01-29 | 2025-02-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAM-135002 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR CPP & CPP REGEN BUILDING | AIR FLOW DIAGRAM |  | Heating, Ventilating and Air - Conditioning System |  |  | AIR FLOW DIAGRAM for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAM-135003 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR CPP & CPP REGEN BUILDING | [6 empty] | CPP Regeneration Building | FI | 0CF5510W36A07 | (CCR BLDG) Installation & Test - HVAC for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-15 | 2008-07-30 |  |  |  | 2025-02-15 | 2025-03-17 | 2025-04-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAM-135004 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR CPP & CPP REGEN BUILDING | Plan |  | Heating, Ventilating and Air - Conditioning System |  |  | Plan for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAV-135101 | LOAD CALCULATION OF HVAC SYSTEM FOR SHELTER FOR WASTE WATER TREATMENT W/ OILY WATER SEPARATOR | Calculation |  | Heating, Ventilating and Air - Conditioning System |  |  | Calculation sheet for Heating, Ventilating and Air - Conditioning System | Water Treatment System | FA | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 | 2024-09-14 | 2024-10-14 | 2024-11-13 | 2024-11-28 | 2024-12-13 | 2024-12-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAV-135102 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR SHELTER FOR WASTE WATER TREATMENT W/ OILY WATER SEPARATOR | Diagram |  | Heating, Ventilating and Air - Conditioning System |  |  | Diagram for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | 2024-06-24 | 2024-07-24 | 2024-08-23 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAV-135103 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR SHELTER FOR WASTE WATER TREATMENT W/ OILY WATER SEPARATOR | Schedule |  | Heating, Ventilating and Air - Conditioning System |  |  | Schedule for Heating, Ventilating and Air - Conditioning System | Air Compressor | FA | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 | [6 empty] | generated |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAV-135104 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR SHELTER FOR WASTE WATER TREATMENT W/ OILY WATER SEPARATOR | Plan |  | Heating, Ventilating and Air - Conditioning System |  |  | Plan for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAQ-135201 | LOAD CALCULATION OF HVAC SYSTEM FOR AUX. LEB | Calculation |  | Heating, Ventilating and Air - Conditioning System | Auxiliary Local Electrical Building |  | Calculation sheet for Heating, Ventilating and Air - Conditioning System | Water Treatment System | FA | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 | 2024-09-14 | 2024-10-14 | 2024-11-13 | 2024-11-28 | 2024-12-13 | 2024-12-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAQ-135202 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR AUX. LEB | Diagram |  | Heating, Ventilating and Air - Conditioning System | Auxiliary Local Electrical Building |  | Diagram for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | 2024-06-24 | 2024-07-24 | 2024-08-23 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAQ-135203 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR AUX. LEB | Schedule |  | Heating, Ventilating and Air - Conditioning System | Auxiliary Local Electrical Building |  | Schedule for Heating, Ventilating and Air - Conditioning System | Air Compressor | FA | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 | [6 empty] | generated |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAQ-135204 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR AUX. LEB | Plan |  | Heating, Ventilating and Air - Conditioning System | Auxiliary Local Electrical Building |  | Plan for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAE-135301 | LOAD CALCULATION OF HVAC SYSTEM FOR PLANT ACCESS GATE HOUSE | Calculation |  | Heating, Ventilating and Air - Conditioning System |  |  | Calculation sheet for Heating, Ventilating and Air - Conditioning System | Water Treatment System | FA | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 | 2024-09-14 | 2024-10-14 | 2024-11-13 | 2024-11-28 | 2024-12-13 | 2024-12-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAE-135302 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR PLANT ACCESS GATE HOUSE | Diagram |  | Heating, Ventilating and Air - Conditioning System |  |  | Diagram for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | 2024-06-24 | 2024-07-24 | 2024-08-23 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAE-135303 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR PLANT ACCESS GATE HOUSE | Schedule |  | Heating, Ventilating and Air - Conditioning System |  |  | Schedule for Heating, Ventilating and Air - Conditioning System | Air Compressor | FA | 0CF5570W36A06 | (Gate House) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-05 | 2008-07-01 | [6 empty] | generated |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAE-135304 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR PLANT ACCESS GATE HOUSE | Plan |  | Heating, Ventilating and Air - Conditioning System |  |  | Plan for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAE-135401 | LOAD CALCULATION OF HVAC SYSTEM FOR PIC GATE HOUSE | Calculation |  | Heating, Ventilating and Air - Conditioning System |  |  | Calculation sheet for Heating, Ventilating and Air - Conditioning System | Water Treatment System | FA | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 | 2024-09-14 | 2024-10-14 | 2024-11-13 | 2024-11-28 | 2024-12-13 | 2024-12-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG07-P0SAE-135402 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR PIC GATE HOUSE | Diagram |  | Heating, Ventilating and Air - Conditioning System |  |  | Diagram for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | 2024-06-24 | 2024-07-24 | 2024-08-23 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW03-P0SAE-135403 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR PIC GATE HOUSE | Schedule |  | Heating, Ventilating and Air - Conditioning System |  |  | Schedule for Heating, Ventilating and Air - Conditioning System | Air Compressor | FA | 0CF5570W36A06 | (Gate House) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-05 | 2008-07-01 | [6 empty] | generated |  | 6210
Fadhili_MDL.xlsx | T16182-XH02-P0SAE-135404 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR PIC GATE HOUSE | Plan |  | Heating, Ventilating and Air - Conditioning System |  |  | Plan for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SAA-136001 | VENDOR PRINT FOR HVAC EQUIPMENT-1 | VENDOR PRINT |  | Heating, Ventilating and Air - Conditioning System |  |  | VENDOR PRINT for Heating, Ventilating and Air - Conditioning System | Air Compressor | FA | 0PF5000W36A05T | (HVAC Equipment) 1st Delivery on site_Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System |  | 2008-05-14 | [6 empty] | missing_date |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SAA-136002 | VENDOR PRINT FOR HVAC EQUIPMENT-2 | VENDOR PRINT |  | Heating, Ventilating and Air - Conditioning System |  |  | VENDOR PRINT for Heating, Ventilating and Air - Conditioning System | Air Compressor | FA | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 | [6 empty] | generated |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SAA-136003 | VENDOR PRINT FOR HVAC EQUIPMENT-3 | VENDOR PRINT |  | Heating, Ventilating and Air - Conditioning System |  |  | VENDOR PRINT for Heating, Ventilating and Air - Conditioning System | Air Compressor | FA | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 | [6 empty] | generated |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SAA-136004 | VENDOR PRINT FOR HVAC EQUIPMENT-4 | PRINT | HVAC EQUIPMENT |  |  |  | PRINT for HVAC EQUIPMENT |  | FA | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 | 2025-02-25 | 2025-03-27 | 2025-04-26 | 2025-05-11 | 2025-05-26 | 2025-06-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SAA-136005 | VENDOR PRINT FOR HVAC EQUIPMENT-5 | PRINT | HVAC EQUIPMENT |  |  |  | PRINT for HVAC EQUIPMENT |  | FA | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 | 2025-02-25 | 2025-03-27 | 2025-04-26 | 2025-05-11 | 2025-05-26 | 2025-06-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0SG-136601 | FIRE FIGHTING SYSTEM CONCEPTUAL DESIGN | CONCEPTUAL DESIGN |  | FIRE FIGHTING SYSTEM |  |  | CONCEPTUAL DESIGN for FIRE FIGHTING SYSTEM |  | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XS00-P0SG-136602 | FIRE RISK EVALUATION | EVALUATION |  |  |  |  | EVALUATION |  | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-136603 | FIRE SERVICE RING MAIN SYSTEM - P&ID | Piping & Instrumentation Drawing |  | FIRE SERVICE RING MAIN SYSTEM |  |  | P&ID for FIRE SERVICE RING MAIN SYSTEM | Water Treatment System | FA | 0CF4500W38A11 | (Fire Fighting System) Piping Work(Ring Main) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2008-02-15 | 2008-05-17 | 2025-03-17 | 2025-04-16 | 2025-05-16 | 2025-05-31 | 2025-06-15 | 2025-06-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-136604 | FIRE SERVICE RING MAIN SYSTEM - PIPE LAYOUT AND DETAIL DRAWING | LAYOUT AND DETAIL DRAWING |  | FIRE SERVICE RING MAIN SYSTEM |  |  | LAYOUT AND DETAIL DRAWING for FIRE SERVICE RING MAIN SYSTEM |  | FI | 0CF4500W38A11 | (Fire Fighting System) Piping Work(Ring Main) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2008-02-15 | 2008-05-17 | 2025-04-12 | 2025-05-12 | 2025-06-11 | 2025-06-26 | 2025-07-11 | 2025-07-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGA-136605 | FIRE SERVICE RING MAIN SYSTEM - HYDRAULIC CALCULATION | HYDRAULIC CALCULATION |  | FIRE SERVICE RING MAIN SYSTEM |  |  | HYDRAULIC CALCULATION for FIRE SERVICE RING MAIN SYSTEM | FIRE BRIGADE | FI | 0CF4500W38A11 | (Fire Fighting System) Piping Work(Ring Main) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2008-02-15 | 2008-05-17 |  |  |  | 2024-11-17 | 2024-12-17 | 2025-01-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0CYE-136606 | FIRE DETECTION AND ALARM SYSTEM - BLOCK DIAGRAM | BLOCK DIAGRAM |  | FIRE DETECTION AND ALARM SYSTEM |  |  | BLOCK DIAGRAM for FIRE DETECTION AND ALARM SYSTEM | Cathodic | SKIP | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-136607 | FIRE DETECTION AND ALARM SYSTEM - NETWORK SINGLE LINE DIAGRAM | SINGLE LINE DIAGRAM |  | FIRE DETECTION AND ALARM SYSTEM |  |  | Single Line Diagram for FIRE DETECTION AND ALARM SYSTEM |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SGA-136609 | FIRE FIGHTING PUMP SYSTEM - DATASHEET | DATASHEET |  | FIRE FIGHTING PUMP SYSTEM |  |  | Data Sheet for FIRE FIGHTING PUMP SYSTEM | FireFighting | FA | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  | 2024-08-07 | 2024-09-11 | 2024-10-16 | 2024-10-02 | 2024-11-06 | 2024-12-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SGA-136610 | OUTDOOR HYDRANT SYSTEM - DATASHEET | DATASHEET |  | OUTDOOR HYDRANT SYSTEM |  |  | Data Sheet for OUTDOOR HYDRANT SYSTEM |  | FA | 0PF4500W38A09P | (Fire Fighting System) P.O & Procurement_piping | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-08-01 | 2007-12-31 | 2024-10-10 | 2024-11-09 | 2024-12-09 | 2024-12-24 | 2025-01-08 | 2025-01-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SGA-136611 | STAND PIPE SYSTEM - DATASHEET | DATASHEET |  | STAND PIPE SYSTEM |  |  | Data Sheet for STAND PIPE SYSTEM |  | FA | 0EF5550W00A01 | (Pipe Rack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Pipe Rack | 2007-06-29 |  | 2024-09-07 | 2024-10-07 | 2024-11-06 | 2024-11-21 | 2024-12-06 | 2024-12-21 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SGE-136612 | SPRINKLER SYSTEM - DATASHEET | DATASHEET |  | SPRINKLER SYSTEM |  |  | Data Sheet for SPRINKLER SYSTEM |  | FA | 0PF3045W42A05P | (Chlorination Plant) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Chlorination System | 2007-08-31 | 2008-09-01 | 2024-11-09 | 2024-12-09 | 2025-01-08 | 2025-01-23 | 2025-02-07 | 2025-02-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SGC-136613 | WATER SPRAY SYSTEM - DATASHEET | DATASHEET |  | WATER SPRAY SYSTEM |  |  | Data Sheet for WATER SPRAY SYSTEM | Water Treatment System | FI | 0PF3035W42A06.0P | (SWS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-08-31 | 2008-09-01 | 2024-10-30 | 2024-11-29 | 2024-12-29 | 2025-01-13 | 2025-01-28 | 2025-02-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SGK-136614 | CLEAN AGENT SYSTEM - DATASHEET | DATASHEET |  | CLEAN AGENT SYSTEM |  |  | Data Sheet for CLEAN AGENT SYSTEM |  | FA | 1PF1265W38A04.7P | (F/F GTG#12) P.O & Procurement_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fire fighting System | 2007-03-01 | 2008-03-14 | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SGZ-136615 | FIRE EXTINGUISHER SYSTEM - DATASHEET | DATASHEET |  | FIRE EXTINGUISHER SYSTEM |  |  | Data Sheet for FIRE EXTINGUISHER SYSTEM |  | FA | 0PF4500W38A03P | (Fire Fighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-08-01 | 2008-06-18 | 2024-10-10 | 2024-11-09 | 2024-12-09 | 2024-12-24 | 2025-01-08 | 2025-01-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0SGX-136616 | PIPE AND BULK MATERIAL - DATASHEET | DATASHEET |  |  |  |  | Data Sheet |  | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | 2024-11-23 | 2024-12-23 | 2025-01-22 | 2025-02-06 | 2025-02-21 | 2025-03-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0CYE-136617 | FIRE DETECTION AND ALARM SYSTEM - DATASHEET | DATASHEET |  | FIRE DETECTION AND ALARM SYSTEM |  |  | Data Sheet for FIRE DETECTION AND ALARM SYSTEM |  | FA | 1SF1265W62A09.7 | (F/F GTG#12) Function Test(incl. Alarm Test) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fire fighting System | 2008-06-15 | 2008-06-24 |  |  |  | 2025-03-18 | 2025-04-17 | 2025-05-17 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0CYE-136618 | CABLE AND BULK MATERIAL - DATASHEET | DATASHEET |  |  |  |  | Data Sheet |  | FA | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | 2024-11-28 | 2024-12-28 | 2025-01-27 | 2025-02-11 | 2025-02-26 | 2025-03-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0SG-136620 | FIRE FIGHTING, DETECTION AND ALARM SYSTEM_TEST & COMMISSIONING PROCEDURE FOR ESOD | PROCEDURE |  | FIRE FIGHTING, DETECTION AND ALARM SYSTEM |  |  | PROCEDURE for FIRE FIGHTING, DETECTION AND ALARM SYSTEM |  | FA | 0CF4500W90A09 | (Fire Fighting BLDG) Installation & Test - I&C | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2008-02-02 | 2008-03-31 |  |  |  | 2024-11-04 | 2024-12-04 | 2025-01-03 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0SG-136621 | PIPING MATERIAL SPECIFICATION FOR FIRE FIGHTING SYSTEM | PIPING MATERIAL SPECIFICATION |  | FIRE FIGHTING SYSTEM |  |  | PIPING MATERIAL SPECIFICATION for FIRE FIGHTING SYSTEM | FireFighting | FA | 0PF4500W38A09P | (Fire Fighting System) P.O & Procurement_piping | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-08-01 | 2007-12-31 | 2024-08-29 | 2024-09-26 | 2024-10-24 | 2024-10-17 | 2024-11-14 | 2024-12-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0SGA-136622 | ISOMETRIC DRAWING FOR FIRE SERVICE RING MAIN SYSTEM | ISOMETRIC DRAWING |  | FIRE SERVICE RING MAIN SYSTEM |  |  | Isometric Drawing for FIRE SERVICE RING MAIN SYSTEM | Water Treatment System | FI | 0CF4500W38A11 | (Fire Fighting System) Piping Work(Ring Main) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2008-02-15 | 2008-05-17 | 2025-07-15 | 2025-08-14 | 2025-09-13 | 2025-09-28 | 2025-10-13 | 2025-10-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0SG-136623 | FIRE FIGHTING, DETECTION AND ALARM SYSTEM_TEST & COMMISSIONING PROCEDURE FOR NON ESOD | PROCEDURE |  | FIRE FIGHTING, DETECTION AND ALARM SYSTEM |  |  | PROCEDURE for FIRE FIGHTING, DETECTION AND ALARM SYSTEM |  | FA | 0CF4500W90A09 | (Fire Fighting BLDG) Installation & Test - I&C | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2008-02-02 | 2008-03-31 |  |  |  | 2024-11-04 | 2024-12-04 | 2025-01-03 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-136624 | FIRE DETECTION AND ALARM SYSTEM LAYOUT FOR YARD AREA | LAYOUT |  | FIRE DETECTION AND ALARM SYSTEM |  |  | Layout Drawing for FIRE DETECTION AND ALARM SYSTEM | Substation | SKIP | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-136631 | PORTABLE EXTINGUISHER ARRANGEMENT FOR SUPPORT BUILDING | ARRANGEMENT |  |  | SUPPORT BUILDING |  | ARRANGEMENT for SUPPORT BUILDING |  | FA | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | 2026-02-28 | 2026-03-30 | 2026-04-29 | 2026-05-14 | 2026-05-29 | 2026-06-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-136641 | FIRE ALARM SYSTEM LAYOUT FOR SUPPORT BUILDING | LAYOUT |  | FIRE ALARM SYSTEM | SUPPORT BUILDING |  | Layout Drawing for FIRE ALARM SYSTEM | Substation | SKIP | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-136642 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR SUPPORT BUILDING | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | SUPPORT BUILDING |  | Single Line Diagram for FIRE ALARM SYSTEM |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-136701 | P&ID OF STAND PIPE SYSTEM FOR CENTRAL CONTROL BUILDING | Piping & Instrumentation Drawing |  | STAND PIPE SYSTEM | CENTRAL CONTROL BUILDING |  | P&ID for STAND PIPE SYSTEM | Water Treatment System | FA | 3PF5550W46A08P | (PipeRack) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-06-28 | 2008-03-04 | 2024-07-28 | 2024-08-27 | 2024-09-26 | 2024-10-11 | 2024-10-26 | 2024-11-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-136702 | P&ID OF SPRINKLER SYSTEM FOR CENTRAL CONTROL BUILDING | Piping & Instrumentation Drawing |  | SPRINKLER SYSTEM | CENTRAL CONTROL BUILDING |  | P&ID for SPRINKLER SYSTEM | Water Treatment System | FA | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 | 2025-07-01 | 2025-07-31 | 2025-08-30 | 2025-09-14 | 2025-09-29 | 2025-10-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-136703 | P&ID OF CLEAN AGENT SYSTEM FOR CENTRAL CONTROL BUILDING | Piping & Instrumentation Drawing |  | CLEAN AGENT SYSTEM | CENTRAL CONTROL BUILDING |  | P&ID for CLEAN AGENT SYSTEM | Water Treatment System | FA | 1PF1265W38A04.7P | (F/F GTG#12) P.O & Procurement_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fire fighting System | 2007-03-01 | 2008-03-14 | 2024-03-31 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-136711 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR CENTRAL CONTROL BUILDING | PIPE LAYOUT AND DETAIL |  | STAND PIPE SYSTEM | CENTRAL CONTROL BUILDING |  | PIPE LAYOUT AND DETAIL for STAND PIPE SYSTEM | PIPE RACK | FI | 3EF5550W20A05 | (PipeRack) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-05-30 | 2007-08-31 |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGE-136712 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR CENTRAL CONTROL BUILDING | PIPE LAYOUT AND DETAIL |  | SPRINKLER SYSTEM | CENTRAL CONTROL BUILDING |  | PIPE LAYOUT AND DETAIL for SPRINKLER SYSTEM | PIPE RACK | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-136713 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR CENTRAL CONTROL BUILDING | PIPE LAYOUT AND DETAIL |  | CLEAN AGENT SYSTEM | CENTRAL CONTROL BUILDING |  | PIPE LAYOUT AND DETAIL for CLEAN AGENT SYSTEM | PIPE RACK | FI | 2CF1265W38A06 | (F/F GTG#21) Installation_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fire fighting System | 2008-05-30 | 2008-06-13 |  |  |  | 2025-03-02 | 2025-04-01 | 2025-05-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGE-136722 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR CENTRAL CONTROL BUILDING | CALCULATION |  | SPRINKLER SYSTEM | CENTRAL CONTROL BUILDING |  | Calculation sheet for SPRINKLER SYSTEM | Water Treatment System | FA | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 | 2025-07-01 | 2025-07-31 | 2025-08-30 | 2025-09-14 | 2025-09-29 | 2025-10-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-136723 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR CENTRAL CONTROL BUILDING | CALCULATION |  | CLEAN AGENT SYSTEM | CENTRAL CONTROL BUILDING |  | Calculation sheet for CLEAN AGENT SYSTEM | Water Treatment System | FA | 2PF1265W38A04P | (F/F GTG#21)P.O & Procurement_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fire fighting System | 2007-03-30 | 2008-04-14 | 2024-04-29 | 2024-05-29 | 2024-06-28 | 2024-07-13 | 2024-07-28 | 2024-08-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-136731 | PORTABLE EXTINGUISHER ARRANGEMENT FOR CENTRAL CONTROL BUILDING | ARRANGEMENT |  |  | CENTRAL CONTROL BUILDING |  | ARRANGEMENT for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-136741 | FIRE ALARM SYSTEM LAYOUT FOR CENTRAL CONTROL BUILDING | LAYOUT |  | FIRE ALARM SYSTEM | CENTRAL CONTROL BUILDING |  | Layout Drawing for FIRE ALARM SYSTEM | Substation | SKIP | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-136742 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR CENTRAL CONTROL BUILDING | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | CENTRAL CONTROL BUILDING |  | Single Line Diagram for FIRE ALARM SYSTEM |  | SKIP | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-136743 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR CENTRAL CONTROL BUILDING | CALCULATION |  | FIRE ALARM SYSTEM | CENTRAL CONTROL BUILDING |  | Calculation sheet for FIRE ALARM SYSTEM | FIRE BRIGADE | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  |  |  | 2025-03-03 | 2025-04-02 | 2025-05-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-136744 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR CENTRAL CONTROL BUILDING | CAUSE & EFFECT MATRIX |  | FIRE ALARM SYSTEM | CENTRAL CONTROL BUILDING |  | CAUSE & EFFECT MATRIX for FIRE ALARM SYSTEM |  | FA | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 | 2025-11-27 | 2025-12-27 | 2026-01-26 | 2026-02-10 | 2026-02-25 | 2026-03-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-136801 | P&ID OF STAND PIPE SYSTEM FOR GTG #1,2 LEB | Piping & Instrumentation Drawing |  | STAND PIPE SYSTEM | Gas Turbine Generator #1,2 Local Electrical Building |  | P&ID for STAND PIPE SYSTEM | Water Treatment System | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-136802 | P&ID OF SPRINKLER SYSTEM FOR GTG #1,2 LEB | Piping & Instrumentation Drawing |  | SPRINKLER SYSTEM | Gas Turbine Generator #1,2 Local Electrical Building |  | P&ID for SPRINKLER SYSTEM | Water Treatment System | FA | 0EF3045W00A01.0 | (Chlorination System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Chlorination System | 2007-03-30 | 2007-11-13 | 2024-04-29 | 2024-05-29 | 2024-06-28 | 2024-07-13 | 2024-07-28 | 2024-08-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-136803 | P&ID OF CLEAN AGENT SYSTEM FOR GTG #1,2 LEB | Piping & Instrumentation Drawing |  | CLEAN AGENT SYSTEM | Gas Turbine Generator #1,2 Local Electrical Building |  | P&ID for CLEAN AGENT SYSTEM | Water Treatment System | FA | 1PF1265W38A04.7P | (F/F GTG#12) P.O & Procurement_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fire fighting System | 2007-03-01 | 2008-03-14 | 2024-03-31 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-136811 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR GTG #1,2 LEB | PIPE LAYOUT AND DETAIL |  | STAND PIPE SYSTEM | Gas Turbine Generator #1,2 Local Electrical Building |  | PIPE LAYOUT AND DETAIL for STAND PIPE SYSTEM | PIPE RACK | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGE-136812 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR GTG #1,2 LEB | PIPE LAYOUT AND DETAIL |  | SPRINKLER SYSTEM | Gas Turbine Generator #1,2 Local Electrical Building |  | PIPE LAYOUT AND DETAIL for SPRINKLER SYSTEM | PIPE RACK | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-136813 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR GTG #1,2 LEB | PIPE LAYOUT AND DETAIL |  | CLEAN AGENT SYSTEM | Gas Turbine Generator #1,2 Local Electrical Building |  | PIPE LAYOUT AND DETAIL for CLEAN AGENT SYSTEM | PIPE RACK | FI | 2CF1265W38A06.1 | (F/F GTG#22) Installation_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fire fighting System | 2008-05-30 | 2008-06-13 |  |  |  | 2025-03-02 | 2025-04-01 | 2025-05-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGE-136822 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR GTG #1,2 LEB | HYDRAULIC CALCULATION |  | SPRINKLER SYSTEM | Gas Turbine Generator #1,2 Local Electrical Building |  | HYDRAULIC CALCULATION for SPRINKLER SYSTEM | Water Treatment System | FA | 2PF1265W38A04.1P | (F/F GTG#22) P.O & Procurement_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fire fighting System | 2007-03-30 | 2008-04-14 | 2024-04-29 | 2024-05-29 | 2024-06-28 | 2024-07-13 | 2024-07-28 | 2024-08-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-136823 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR GTG #1,2 LEB | FLOW CALCULATION |  | CLEAN AGENT SYSTEM | Gas Turbine Generator #1,2 Local Electrical Building |  | FLOW CALCULATION for CLEAN AGENT SYSTEM | Water Treatment System | FA | 2PF1265W38A04P | (F/F GTG#21)P.O & Procurement_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fire fighting System | 2007-03-30 | 2008-04-14 | 2024-04-29 | 2024-05-29 | 2024-06-28 | 2024-07-13 | 2024-07-28 | 2024-08-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-136831 | PORTABLE EXTINGUISHER ARRANGEMENT FOR GTG #1,2 LEB | ARRANGEMENT |  |  | Gas Turbine Generator #1,2 Local Electrical Building |  | ARRANGEMENT for Gas Turbine Generator #1,2 Local Electrical Building |  | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | 2024-08-20 | 2024-09-19 | 2024-10-19 | 2024-11-03 | 2024-11-18 | 2024-12-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-136841 | FIRE ALARM SYSTEM LAYOUT FOR GTG #1,2 LEB | LAYOUT |  | FIRE ALARM SYSTEM | Gas Turbine Generator #1,2 Local Electrical Building |  | Layout Drawing for FIRE ALARM SYSTEM | Substation | SKIP | 2CF1200W38A06 | (GTG #21 LEB) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2008-05-31 | 2008-07-04 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-136842 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GTG #1,2 LEB | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | Gas Turbine Generator #1,2 Local Electrical Building |  | Single Line Diagram for FIRE ALARM SYSTEM |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-136843 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR GTG #1,2 LEB | CALCULATION |  | FIRE ALARM SYSTEM | Gas Turbine Generator #1,2 Local Electrical Building |  | Calculation sheet for FIRE ALARM SYSTEM | FIRE BRIGADE | FI | 2CF1200W38A06 | (GTG #21 LEB) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2008-05-31 | 2008-07-04 |  |  |  | 2025-03-03 | 2025-04-02 | 2025-05-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-136844 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR GTG #1,2 LEB | CAUSE & EFFECT MATRIX |  | FIRE ALARM SYSTEM | Gas Turbine Generator #1,2 Local Electrical Building |  | CAUSE & EFFECT MATRIX for FIRE ALARM SYSTEM |  | FA | 1SF1265W62A09.7 | (F/F GTG#12) Function Test(incl. Alarm Test) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fire fighting System | 2008-06-15 | 2008-06-24 | 2025-12-12 | 2026-01-11 | 2026-02-10 | 2026-02-25 | 2026-03-12 | 2026-03-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-136901 | P&ID OF STAND PIPE SYSTEM FOR GTG #3,4,5 LEB | Piping & Instrumentation Drawing |  | STAND PIPE SYSTEM | Gas Turbine Generator #3,4,5 Local Electrical Building |  | P&ID for STAND PIPE SYSTEM | Water Treatment System | FA | 3EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-136902 | P&ID OF SPRINKLER SYSTEM FOR GTG #3,4,5 LEB | Piping & Instrumentation Drawing |  | SPRINKLER SYSTEM | Gas Turbine Generator #3,4,5 Local Electrical Building |  | P&ID for SPRINKLER SYSTEM | Water Treatment System | FA | 0EF3045W00A01.0 | (Chlorination System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Chlorination System | 2007-03-30 | 2007-11-13 | 2024-04-29 | 2024-05-29 | 2024-06-28 | 2024-07-13 | 2024-07-28 | 2024-08-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-136903 | P&ID OF CLEAN AGENT SYSTEM FOR GTG #3,4,5 LEB | Piping & Instrumentation Drawing |  | CLEAN AGENT SYSTEM | Gas Turbine Generator #3,4,5 Local Electrical Building |  | P&ID for CLEAN AGENT SYSTEM | Water Treatment System | FA | 3PF1265W38A04.2P | (F/F GTG#32) P.O & Procurement_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fire fighting System | 2007-04-30 | 2008-05-13 | 2024-05-30 | 2024-06-29 | 2024-07-29 | 2024-08-13 | 2024-08-28 | 2024-09-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-136911 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR GTG #3,4,5 LEB | PIPE LAYOUT AND DETAIL |  | STAND PIPE SYSTEM | Gas Turbine Generator #3,4,5 Local Electrical Building |  | PIPE LAYOUT AND DETAIL for STAND PIPE SYSTEM | PIPE RACK | FI | 3EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-05-30 | 2007-08-31 |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGE-136912 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR GTG #3,4,5 LEB | PIPE LAYOUT AND DETAIL |  | SPRINKLER SYSTEM | Gas Turbine Generator #3,4,5 Local Electrical Building |  | PIPE LAYOUT AND DETAIL for SPRINKLER SYSTEM | PIPE RACK | FI | 3EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-05-30 | 2007-08-31 |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-136913 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR GTG #3,4,5 LEB | PIPE LAYOUT AND DETAIL |  | CLEAN AGENT SYSTEM | Gas Turbine Generator #3,4,5 Local Electrical Building |  | PIPE LAYOUT AND DETAIL for CLEAN AGENT SYSTEM | PIPE RACK | FI | 3CF1265W38A06.2 | (F/F GTG#32) Installation_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fire fighting System | 2008-06-28 | 2008-07-12 |  |  |  | 2025-03-31 | 2025-04-30 | 2025-05-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGE-136922 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR GTG #3,4,5 LEB | HYDRAULIC CALCULATION |  | SPRINKLER SYSTEM | Gas Turbine Generator #3,4,5 Local Electrical Building |  | HYDRAULIC CALCULATION for SPRINKLER SYSTEM | Water Treatment System | FA | 3PF1265W38A04P | (F/F GTG#31)P.O & Procurement_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fire fighting System | 2007-04-30 | 2008-05-13 | 2024-05-30 | 2024-06-29 | 2024-07-29 | 2024-08-13 | 2024-08-28 | 2024-09-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-136923 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR GTG #3,4,5 LEB | Calculation | Gas Turbine Generator |  | Local Electrical Building |  | Calculation sheet for GTG |  | FI | 3CF1265W38A06 | (F/F GTG#31) Installation_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fire fighting System | 2008-06-28 | 2008-07-12 |  |  |  | 2025-03-31 | 2025-04-30 | 2025-05-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-136931 | PORTABLE EXTINGUISHER ARRANGEMENT FOR GTG #3,4,5 LEB | Arrangement | Gas Turbine Generator |  | Local Electrical Building |  | Arrangement for GTG |  | FA | 3PF1213W42A03.1P | (GT #32) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Main body | 2007-04-30 | 2008-04-29 | 2024-08-26 | 2024-09-25 | 2024-10-25 | 2024-11-09 | 2024-11-24 | 2024-12-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-136941 | FIRE ALARM SYSTEM LAYOUT FOR GTG #3,4,5 LEB | Layout | Gas Turbine Generator | FIRE ALARM SYSTEM | Local Electrical Building |  | Layout Drawing for GTG | Substation | SKIP | 3CF1200W38A06 | (GTG #31 LEB) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2008-05-31 | 2008-07-04 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-136942 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GTG #3,4,5 LEB | Single Line Diagram | Gas Turbine Generator | FIRE ALARM SYSTEM | Local Electrical Building |  | Single Line Diagram for GTG |  | SKIP | 3PF1265W38A04.2P | (F/F GTG#32) P.O & Procurement_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fire fighting System | 2007-04-30 | 2008-05-13 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-136943 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR GTG #3,4,5 LEB | Calculation | Gas Turbine Generator | FIRE ALARM SYSTEM | Local Electrical Building |  | Calculation sheet for GTG |  | FI | 3CF1200W38A06 | (GTG #31 LEB) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2008-05-31 | 2008-07-04 |  |  |  | 2025-03-03 | 2025-04-02 | 2025-05-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-136944 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR GTG #3,4,5 LEB | CAUSE & EFFECT MATRIX | Gas Turbine Generator | FIRE ALARM SYSTEM | Local Electrical Building |  | CAUSE & EFFECT MATRIX for GTG |  | FA | 3SF1265W62A09.20 | (F/F GTG#32) Function Test(incl. Alarm Test) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fire fighting System | 2008-08-14 | 2008-08-23 | 2026-02-10 | 2026-03-12 | 2026-04-11 | 2026-04-26 | 2026-05-11 | 2026-05-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-137001 | P&ID OF WATER SPRAY SYSTEM FOR GTG GSU TRANSFORMER | Piping & Instrumentation Drawing | Gas Turbine Generator | WATER SPRAY SYSTEM |  |  | P&ID for GTG |  | FA | 1PF1265W42A16P | (Water injection System) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | 2007-03-01 | 2008-01-31 | 2024-08-12 | 2024-09-11 | 2024-10-11 | 2024-10-26 | 2024-11-10 | 2024-11-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-137011 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GTG GSU TRANSFORMER | PIPE LAYOUT AND DETAIL | Gas Turbine Generator | WATER SPRAY SYSTEM |  |  | PIPE LAYOUT AND DETAIL for GTG | PIPE RACK | FI | 1CF1265W58A18.6 | (Water injection System) Piping work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Oil Injection System | 2008-04-02 | 2008-04-16 |  |  |  | 2025-01-03 | 2025-02-02 | 2025-03-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-137021 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GTG GSU TRANSFORMER | Calculation | Gas Turbine Generator | WATER SPRAY SYSTEM |  |  | Calculation sheet for GTG |  | FI | 1PF1265W42A16.6T | (Water injection System) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Oil Injection System | 2008-02-01 | 2008-03-17 |  |  |  | 2024-11-03 | 2024-12-03 | 2025-01-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137031 | PORTABLE EXTINGUISHER ARRANGEMENT FOR GTG GSU TRANSFORMER | Arrangement | Gas Turbine Generator |  |  |  | Arrangement for GTG |  | FA | 1PF1213W42A03.1P | (GT #12) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Main body | 2007-03-01 | 2008-02-29 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-137041 | FIRE ALARM SYSTEM LAYOUT FOR GTG GSU TRANSFORMER | Layout | Gas Turbine Generator | FIRE ALARM SYSTEM |  |  | Layout Drawing for GTG | Substation | SKIP | 1PF1265W38A02.7T | (F/F GTG#12) Transportation_CO2 FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fire fighting System | 2008-03-15 | 2008-04-29 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-137042 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GTG GSU TRANSFORMER | Single Line Diagram | Gas Turbine Generator | FIRE ALARM SYSTEM |  |  | Single Line Diagram for GTG |  | SKIP | 3PF1265W38A04.2P | (F/F GTG#32) P.O & Procurement_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fire fighting System | 2007-04-30 | 2008-05-13 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-137101 | P&ID OF WATER SPRAY SYSTEM FOR GTG UNIT AUX. TRANSFORMER | Piping & Instrumentation Drawing | Gas Turbine Generator | WATER SPRAY SYSTEM |  |  | P&ID for GTG |  | FA | 1PF1265W42A16P | (Water injection System) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | 2007-03-01 | 2008-01-31 | 2024-08-12 | 2024-09-11 | 2024-10-11 | 2024-10-26 | 2024-11-10 | 2024-11-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-137111 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GTG UNIT AUX. TRANSFORMER | PIPE LAYOUT AND DETAIL | Gas Turbine Generator | WATER SPRAY SYSTEM |  |  | PIPE LAYOUT AND DETAIL for GTG | PIPE RACK | FI | 1CF1265W90A20.6 | (Water injection System) Installation- I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Oil Injection System | 2008-04-17 | 2008-04-30 |  |  |  | 2025-01-18 | 2025-02-17 | 2025-03-19 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-137121 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GTG UNIT AUX. TRANSFORMER | Calculation | Gas Turbine Generator | WATER SPRAY SYSTEM |  |  | Calculation sheet for GTG |  | FI | 1EF1225W00A02.1 | (CCWP) Key data for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System | 2007-03-01 | 2007-05-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137131 | PORTABLE EXTINGUISHER ARRANGEMENT FOR GTG UNIT AUX. TRANSFORMER | Arrangement | Gas Turbine Generator |  |  |  | Arrangement for GTG |  | FA | 1PF6500W70A04.1P | (GTG UAT) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-03-30 | 2008-03-17 | 2024-07-26 | 2024-08-25 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-137141 | FIRE ALARM SYSTEM LAYOUT FOR GTG UNIT AUX. TRANSFORMER | Layout | Gas Turbine Generator | FIRE ALARM SYSTEM |  |  | Layout Drawing for GTG | Substation | SKIP | 1CF6500W38A14 | (GTG #11 & UAT Shelter) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2008-05-31 | 2008-07-16 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-137142 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GTG UNIT AUX. TRANSFORMER | Single Line Diagram | Gas Turbine Generator | FIRE ALARM SYSTEM |  |  | Single Line Diagram for GTG |  | SKIP | 1PF1265W38A04.7P | (F/F GTG#12) P.O & Procurement_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fire fighting System | 2007-03-01 | 2008-03-14 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-137201 | P&ID OF WATER SPRAY SYSTEM FOR STG GSU TRANSFORMER | Piping & Instrumentation Drawing | Steam Turbine & Generator | WATER SPRAY SYSTEM |  |  | P&ID for STG |  | FA | 0EF3035W00A01.0 | (SWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-03-15 | 2007-11-21 | 2024-09-09 | 2024-10-09 | 2024-11-08 | 2024-11-23 | 2024-12-08 | 2024-12-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-137211 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR STG GSU TRANSFORMER | PIPE LAYOUT AND DETAIL | Steam Turbine & Generator | WATER SPRAY SYSTEM |  |  | PIPE LAYOUT AND DETAIL for STG | PIPE RACK | FI | 1EF6500W32A04 | (STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 |  |  |  | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-137221 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR STG GSU TRANSFORMER | CALCULATION | Steam Turbine & Generator | Water Spray System |  |  | Calculation sheet for STG |  | FI | 1EF6500W32A04 | (STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 |  |  |  | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137231 | PORTABLE EXTINGUISHER ARRANGEMENT FOR STG GSU TRANSFORMER | ARRANGEMENT | Steam Turbine & Generator |  |  |  | ARRANGEMENT for STG |  | FA | 1PF6500W70A07P | (STG #10 & UST Shelter) P.O & Procurement - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-06-29 | 2008-06-22 | 2025-01-02 | 2025-02-01 | 2025-03-03 | 2025-03-18 | 2025-04-02 | 2025-04-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-137241 | FIRE ALARM SYSTEM LAYOUT FOR STG GSU TRANSFORMER | LAYOUT | Steam Turbine & Generator | FIRE ALARM SYSTEM |  |  | Layout Drawing for STG | Substation | SKIP | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-137242 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR STG GSU TRANSFORMER | SINGLE LINE DIAGRAM | Steam Turbine & Generator | FIRE ALARM SYSTEM |  |  | Single Line Diagram for STG |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-137301 | P&ID OF STAND PIPE SYSTEM FOR FIRE WATER PUMP HOUSE | Piping & Instrumentation Drawing |  |  | FIRE WATER PUMP HOUSE |  | P&ID for FIRE WATER PUMP HOUSE | Fire Water Pump House | FI | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-137302 | P&ID OF SPRINKLER SYSTEM FOR FIRE WATER PUMP HOUSE | Piping & Instrumentation Drawing |  |  | FIRE WATER PUMP HOUSE |  | P&ID for FIRE WATER PUMP HOUSE | Fire Water Pump House | FI | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-137303 | P&ID OF FIRE WATER PUMP FOR FIRE WATER PUMP HOUSE | Piping & Instrumentation Drawing | FIRE WATER PUMP |  | FIRE WATER PUMP HOUSE |  | P&ID for FIRE WATER PUMP | Water Treatment System | FA | 0SF4500W62A12 | (Fire WTR Pump) Loop chek | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2008-07-17 | 2008-07-18 | 2025-08-17 | 2025-09-16 | 2025-10-16 | 2025-10-31 | 2025-11-15 | 2025-11-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-137311 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR FIRE WATER PUMP HOUSE | PIPE LAYOUT AND DETAIL |  |  | FIRE WATER PUMP HOUSE |  | PIPE LAYOUT AND DETAIL for FIRE WATER PUMP HOUSE | Fire Water Pump House | FI | 1EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-05-30 | 2007-08-31 |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGE-137312 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR FIRE WATER PUMP HOUSE | PIPE LAYOUT AND DETAIL |  |  | FIRE WATER PUMP HOUSE |  | PIPE LAYOUT AND DETAIL for FIRE WATER PUMP HOUSE | Fire Water Pump House | FI | 0SF4500W62A12 | (Fire WTR Pump) Loop chek | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2008-07-17 | 2008-07-18 |  |  |  | 2025-04-19 | 2025-05-19 | 2025-06-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGE-137322 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR FIRE WATER PUMP HOUSE | CALCULATION |  |  | FIRE WATER PUMP HOUSE |  | Calculation sheet for FIRE WATER PUMP HOUSE | Fire Water Pump House | FI | 0SF4500W62A12 | (Fire WTR Pump) Loop chek | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2008-07-17 | 2008-07-18 |  |  |  | 2025-04-19 | 2025-05-19 | 2025-06-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137331 | FIRE WATER PUMP ARRANGEMENT FOR FIRE WATER PUMP HOUSE | ARRANGEMENT | FIRE WATER PUMP |  | FIRE WATER PUMP HOUSE |  | ARRANGEMENT for FIRE WATER PUMP | Fire Water Pump House | FI | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  |  |  |  | 2024-03-01 | 2024-03-02 | 2024-04-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137332 | PORTABLE EXTINGUISHER ARRANGEMENT FOR FIRE WATER PUMP HOUSE | ARRANGEMENT |  |  | FIRE WATER PUMP HOUSE |  | ARRANGEMENT for FIRE WATER PUMP HOUSE | Fire Water Pump House | FI | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  |  |  |  | 2024-03-01 | 2024-03-02 | 2024-04-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-137341 | FIRE ALARM SYSTEM LAYOUT FOR FIRE WATER PUMP HOUSE | LAYOUT |  | FIRE ALARM SYSTEM | FIRE WATER PUMP HOUSE |  | Layout Drawing for FIRE ALARM SYSTEM | Substation | SKIP | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-137342 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR FIRE WATER PUMP HOUSE | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | FIRE WATER PUMP HOUSE |  | Single Line Diagram for FIRE ALARM SYSTEM |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-137401 | P&ID OF WATER SPRAY SYSTEM FOR BURNER FOR RESERVE BOILER | Piping & Instrumentation Drawing |  | Water Spray System |  |  | P&ID for Water Spray System | Water Treatment System | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-137411 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR BURNER FOR RESERVE BOILER | PIPE LAYOUT AND DETAIL |  |  |  |  | PIPE LAYOUT AND DETAIL | PIPE RACK | FI | 0EF6020W00A01 | (BOP Piping) Pipe Arrangement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-04-30 | 2008-09-30 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-31 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-137421 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR BURNER FOR RESERVE BOILER | CALCULATION |  | Water Spray System |  |  | Calculation sheet for Water Spray System | Water Treatment System | FA | 2PF1265W42A15.1P | (Water injection System) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Oil Injection System | 2007-03-30 | 2008-02-29 | 2024-04-29 | 2024-05-29 | 2024-06-28 | 2024-07-13 | 2024-07-28 | 2024-08-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137431 | PORTABLE EXTINGUISHER ARRANGEMENT FOR RESERVE BOILER | ARRANGEMENT |  |  |  |  | ARRANGEMENT |  | FA | 0PF6050W86A03.1P | (Safety Valve) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-09-14 | 2008-05-23 | 2024-10-14 | 2024-10-29 | 2024-11-13 | 2024-12-13 | 2024-12-28 | 2025-01-12 | generated | 0.60 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-137441 | FIRE ALARM SYSTEM LAYOUT FOR RESERVE BOILER | LAYOUT |  | FIRE ALARM SYSTEM |  |  | Layout Drawing for FIRE ALARM SYSTEM | Substation | SKIP | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-137442 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR RESERVE BOILER | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM |  |  | Single Line Diagram for FIRE ALARM SYSTEM |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-137603 | P&ID OF CLEAN AGENT SYSTEM FOR FGS ELECTRICAL BUILDING | Piping & Instrumentation Drawing |  | CLEAN AGENT SYSTEM | FGS ELECTRICAL BUILDING |  | P&ID for CLEAN AGENT SYSTEM | Water Treatment System | FA | 1PF1265W38A04.7P | (F/F GTG#12) P.O & Procurement_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fire fighting System | 2007-03-01 | 2008-03-14 | 2024-03-31 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-137613 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR FGS ELECTRICAL BUILDING | PIPE LAYOUT AND DETAIL |  | CLEAN AGENT SYSTEM | FGS ELECTRICAL BUILDING |  | PIPE LAYOUT AND DETAIL for CLEAN AGENT SYSTEM | PIPE RACK | FI | 1CF1265W38A06 | (F/F GTG#11) Installation_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fire fighting System | 2008-04-30 | 2008-05-14 |  |  |  | 2025-01-31 | 2025-03-02 | 2025-04-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-137623 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR FGS ELECTRICAL BUILDING | FLOW CALCULATION |  | CLEAN AGENT SYSTEM | FGS ELECTRICAL BUILDING |  | FLOW CALCULATION for CLEAN AGENT SYSTEM | Water Treatment System | FA | 1PF1265W38A04.7P | (F/F GTG#12) P.O & Procurement_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fire fighting System | 2007-03-01 | 2008-03-14 | 2024-03-31 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137631 | PORTABLE EXTINGUISHER ARRANGEMENT FOR FGS ELECTRICAL BUILDING | ARRANGEMENT |  |  | FGS ELECTRICAL BUILDING |  | ARRANGEMENT for FGS ELECTRICAL BUILDING | Electrical Building | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-137641 | FIRE ALARM SYSTEM LAYOUT FOR FGS ELECTRICAL BUILDING | LAYOUT |  | FIRE ALARM SYSTEM | FGS ELECTRICAL BUILDING |  | Layout Drawing for FIRE ALARM SYSTEM | Substation | SKIP | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-137642 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR FGS ELECTRICAL BUILDING | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | FGS ELECTRICAL BUILDING |  | Single Line Diagram for FIRE ALARM SYSTEM |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-137643 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR FGS ELECTRICAL BUILDING | CALCULATION |  | FIRE ALARM SYSTEM | FGS ELECTRICAL BUILDING |  | Calculation sheet for FIRE ALARM SYSTEM | FIRE BRIGADE | FI | 1SF1265W62A09.7 | (F/F GTG#12) Function Test(incl. Alarm Test) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fire fighting System | 2008-06-15 | 2008-06-24 |  |  |  | 2025-03-18 | 2025-04-17 | 2025-05-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-137644 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR FGS ELECTRICAL BUILDING | CAUSE & EFFECT MATRIX |  | FIRE ALARM SYSTEM | FGS ELECTRICAL BUILDING |  | CAUSE & EFFECT MATRIX for FIRE ALARM SYSTEM |  | FA | 1SF1265W62A09.2 | (F/F GTG#11) Function Test(incl. Alarm Test) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fire fighting System | 2008-06-15 | 2008-06-24 | 2025-12-12 | 2026-01-11 | 2026-02-10 | 2026-02-25 | 2026-03-12 | 2026-03-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-137701 | P&ID OF STAND PIPE SYSTEM FOR AIR COMPRESSOR SHELTER | Piping & Instrumentation Drawing |  | STAND PIPE SYSTEM | AIR COMPRESSOR SHELTER |  | P&ID for STAND PIPE SYSTEM | Water Treatment System | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | 2024-05-30 | 2024-06-29 | 2024-07-29 | 2024-08-13 | 2024-08-28 | 2024-09-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-137711 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR AIR COMPRESSOR SHELTER | PIPE LAYOUT AND DETAIL |  | STAND PIPE SYSTEM | AIR COMPRESSOR SHELTER |  | PIPE LAYOUT AND DETAIL for STAND PIPE SYSTEM | PIPE RACK | FI | 0EF3510W16A02 | (COMP Air Receiver TK Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-11-12 |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137731 | PORTABLE EXTINGUISHER ARRANGEMENT FOR AIR COMPRESSOR SHELTER | ARRANGEMENT | Air Compressor |  | AIR COMPRESSOR SHELTER |  | ARRANGEMENT for Air Compressor | Air Compressor | FA | 0EF3510W00A01 | (COMP Air Receiver TK Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 |  | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-137741 | FIRE ALARM SYSTEM LAYOUT FOR AIR COMPRESSOR SHELTER | LAYOUT |  | FIRE ALARM SYSTEM | AIR COMPRESSOR SHELTER |  | Layout Drawing for FIRE ALARM SYSTEM | Substation | SKIP | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-137742 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR AIR COMPRESSOR SHELTER | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | AIR COMPRESSOR SHELTER |  | Single Line Diagram for FIRE ALARM SYSTEM |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-137801 | P&ID OF STAND PIPE SYSTEM FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | Piping & Instrumentation Drawing |  | STAND PIPE SYSTEM | WWT & BULK CHEMICAL STORAGE TANK SHELTER |  | P&ID for STAND PIPE SYSTEM | Water Treatment System | FA | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-137811 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | PIPE LAYOUT AND DETAIL |  | STAND PIPE SYSTEM | WWT & BULK CHEMICAL STORAGE TANK SHELTER |  | PIPE LAYOUT AND DETAIL for STAND PIPE SYSTEM | PIPE RACK | FI | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137831 | PORTABLE EXTINGUISHER ARRANGEMENT FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | ARRANGEMENT | Tank |  | WWT & BULK CHEMICAL STORAGE TANK SHELTER |  | ARRANGEMENT for Tank |  | FA | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  | 2024-11-18 | 2024-12-18 | 2025-01-17 | 2025-02-01 | 2025-02-16 | 2025-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-137841 | FIRE ALARM SYSTEM LAYOUT FORSHELTER FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | LAYOUT |  | FIRE ALARM SYSTEM | WWT & BULK CHEMICAL STORAGE TANK SHELTER |  | Layout Drawing for FIRE ALARM SYSTEM | Substation | SKIP | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-137842 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | WWT & BULK CHEMICAL STORAGE TANK SHELTER |  | Single Line Diagram for FIRE ALARM SYSTEM |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-137901 | P&ID OF STAND PIPE SYSTEM FOR WATER TREATMENT BUILDING | Piping & Instrumentation Drawing |  | STAND PIPE SYSTEM | WATER TREATMENT BUILDING |  | P&ID for STAND PIPE SYSTEM | Water Treatment System | FA | 0EF4035W00A01 | (STS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-04-02 | 2007-12-07 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-137902 | P&ID OF CLEAN AGENT SYSTEM FOR WATER TREATMENT BUILDING | Piping & Instrumentation Drawing |  | CLEAN AGENT SYSTEM | WATER TREATMENT BUILDING |  | P&ID for CLEAN AGENT SYSTEM | Water Treatment System | FA | 2EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | 2007-03-15 | 2008-01-15 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-137903 | P&ID OF SPRINKLER SYSTEM FOR WATER TREATMENT BUILDING | Piping & Instrumentation Drawing |  | SPRINKLER SYSTEM | WATER TREATMENT BUILDING |  | P&ID for SPRINKLER SYSTEM | Water Treatment System | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-137911 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR WATER TREATMENT BUILDING | PIPE LAYOUT AND DETAIL |  | STAND PIPE SYSTEM | WATER TREATMENT BUILDING |  | PIPE LAYOUT AND DETAIL for STAND PIPE SYSTEM | PIPE RACK | FI | 3EF5550W20A05 | (PipeRack) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-05-30 | 2007-08-31 |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-137912 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR WATER TREATMENT BUILDING | PIPE LAYOUT AND DETAIL |  | CLEAN AGENT SYSTEM | WATER TREATMENT BUILDING |  | PIPE LAYOUT AND DETAIL for CLEAN AGENT SYSTEM | PIPE RACK | FI | 2CF1265W38A06 | (F/F GTG#21) Installation_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fire fighting System | 2008-05-30 | 2008-06-13 |  |  |  | 2025-03-02 | 2025-04-01 | 2025-05-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGE-137913 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR WATER TREATMENT BUILDING | PIPE LAYOUT AND DETAIL |  | SPRINKLER SYSTEM | WATER TREATMENT BUILDING |  | PIPE LAYOUT AND DETAIL for SPRINKLER SYSTEM | PIPE RACK | FI | 1EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-05-30 | 2007-08-31 |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-137922 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR WATER TREATMENT BUILDING | FLOW CALCULATION |  | CLEAN AGENT SYSTEM | WATER TREATMENT BUILDING |  | FLOW CALCULATION for CLEAN AGENT SYSTEM | Water Treatment System | FA | 1PF1265W38A04.7P | (F/F GTG#12) P.O & Procurement_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fire fighting System | 2007-03-01 | 2008-03-14 | 2024-03-31 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGE-137923 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR WATER TREATMENT BUILDING | HYDRAULIC CALCULATION |  | SPRINKLER SYSTEM | WATER TREATMENT BUILDING |  | HYDRAULIC CALCULATION for SPRINKLER SYSTEM | Water Treatment System | FA | 1CF3010W62A02.1 | (Water Treatment System) Hydro Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Water Treatment Sytstem (BOP) | 2008-12-17 | 2009-01-01 | 2026-01-17 | 2026-02-16 | 2026-03-18 | 2026-04-02 | 2026-04-17 | 2026-05-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-137931 | PORTABLE EXTINGUISHER ARRANGEMENT FOR WATER TREATMENT BUILDING | ARRANGEMENT |  |  | WATER TREATMENT BUILDING |  | ARRANGEMENT for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-137941 | FIRE ALARM SYSTEM LAYOUT FOR WATER TREATMENT BUILDING | LAYOUT |  | FIRE ALARM SYSTEM | WATER TREATMENT BUILDING |  | Layout Drawing for FIRE ALARM SYSTEM | Substation | SKIP | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-137942 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR WATER TREATMENT BUILDING | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | WATER TREATMENT BUILDING |  | Single Line Diagram for FIRE ALARM SYSTEM |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-137943 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR WATER TREATMENT BUILDING | BATTERY CALCULATION |  | FIRE ALARM SYSTEM | WATER TREATMENT BUILDING |  | BATTERY CALCULATION for FIRE ALARM SYSTEM | FIRE BRIGADE | FI | 0CF6500W70A04.5 | (Battery) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Batteries | 2008-06-04 | 2008-06-10 |  |  |  | 2025-03-07 | 2025-04-06 | 2025-05-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-137944 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR WATER TREATMENT BUILDING | CAUSE & EFFECT MATRIX |  | FIRE ALARM SYSTEM | WATER TREATMENT BUILDING |  | CAUSE & EFFECT MATRIX for FIRE ALARM SYSTEM |  | FA | 0CF5535W38A19 | (STS BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2008-08-16 | 2008-10-13 | 2026-02-12 | 2026-03-14 | 2026-04-13 | 2026-04-28 | 2026-05-13 | 2026-05-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-138001 | P&ID OF STANDPIPE SYSTEM FOR N2 GAS STORAGE SHELTER | Piping & Instrumentation Drawing |  | STANDPIPE SYSTEM | Nitrogen GAS STORAGE SHELTER |  | P&ID for STANDPIPE SYSTEM | Water Treatment System | FA | 1EF3515W00A01 | (N2 Gas System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-04-02 | 2007-08-27 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-138011 | PIPE LAYOUT AND DETAIL OF STANDPIPE SYSTEM FOR N2 GAS STORAGE SHELTER | PIPE LAYOUT AND DETAIL |  | STANDPIPE SYSTEM | Nitrogen GAS STORAGE SHELTER |  | PIPE LAYOUT AND DETAIL for STANDPIPE SYSTEM | PIPE RACK | FI | 2EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 |  |  |  | 2024-09-04 | 2024-10-04 | 2024-11-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138031 | PORTABLE EXTINGUISHER ARRANGEMENT FOR N2 GAS STORAGE SHELTER | ARRANGEMENT |  |  | Nitrogen GAS STORAGE SHELTER |  | ARRANGEMENT for Nitrogen GAS STORAGE SHELTER | Gas Storage Shelter | FI | 1EF3515W00A06 | (N2 Gas Station Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 |  |  |  |  | 2024-09-04 | 2024-10-04 | 2024-11-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138041 | FIRE ALARM SYSTEM LAYOUT FOR N2 GAS STORAGE SHELTER | LAYOUT |  | FIRE ALARM SYSTEM | Nitrogen GAS STORAGE SHELTER |  | Layout Drawing for FIRE ALARM SYSTEM | Substation | SKIP | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138042 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR N2 GAS STORAGE SHELTER | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | Nitrogen GAS STORAGE SHELTER |  | Single Line Diagram for FIRE ALARM SYSTEM |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-138101 | P&ID OF WATER SPRAY SYSTEM FOR BURNER FOR HRSG | Piping & Instrumentation Drawing | Heat Recovery Steam Generator |  |  |  | P&ID for HRSG |  | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | 2024-08-30 | 2024-09-29 | 2024-10-29 | 2024-11-13 | 2024-11-28 | 2024-12-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-138102 | P&ID OF WATER SPRAY SYSTEM FOR GTG LUBE OIL UNIT | Piping & Instrumentation Drawing | Gas Turbine Generator | LUBE OIL SYSTEM |  |  | P&ID for GTG |  | FA | 1PF1250W42A06P | (Lube Oil System) P.O & Procurement_Lube oil functional Module | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Lube Oil System | 2007-03-01 | 2008-01-30 | 2024-08-12 | 2024-09-11 | 2024-10-11 | 2024-10-26 | 2024-11-10 | 2024-11-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-138111 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR BURNER FOR HRSG | PIPE LAYOUT AND DETAIL | Heat Recovery Steam Generator |  |  |  | PIPE LAYOUT AND DETAIL for HRSG |  | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-138112 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GTG LUBE OIL UNIT | PIPE LAYOUT AND DETAIL | Gas Turbine Generator | LUBE OIL SYSTEM |  |  | PIPE LAYOUT AND DETAIL for GTG | PIPE RACK | FI | 1CF2030W58A07 | (Lube Oil Sys.) Pipe Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Lube Oil System | 2008-10-31 | 2009-01-15 |  |  |  | 2025-08-03 | 2025-09-02 | 2025-10-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-138121 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR BURNER FOR HRSG | CALCULATION | Heat Recovery Steam Generator |  |  |  | Calculation sheet for HRSG |  | FA | 1PF1665W42A12.1P | (HRSG #12 MECH Vendor Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Auxiliary System | 2007-09-10 | 2008-08-01 | 2025-02-21 | 2025-03-23 | 2025-04-22 | 2025-05-07 | 2025-05-22 | 2025-06-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-138122 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GTG LUBE OIL UNIT | CALCULATION | Gas Turbine Generator | LUBE OIL SYSTEM |  |  | Calculation sheet for GTG |  | FI | 1CF1250W42A08 | (Lube Oil System) Installation_Lube oil functional Module | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Lube Oil System | 2008-03-17 | 2008-04-01 |  |  |  | 2024-12-18 | 2025-01-17 | 2025-02-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138131 | PORTABLE EXTINGUISHER ARRANGEMENT FOR HRSG | ARRANGEMENT | Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG |  | FA | 3EF1600W00A02 | (HRSG #31/#32) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138141 | FIRE ALARM SYSTEM LAYOUT FOR HRSG | LAYOUT | Heat Recovery Steam Generator |  |  |  | Layout Drawing for HRSG |  | FA | 1CF1600W38A14.1 | (HRSG #12 LEB) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | 2008-11-01 | 2008-12-15 | 2026-07-15 | 2026-08-14 | 2026-09-13 | 2026-09-28 | 2026-10-13 | 2026-10-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138142 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR HRSG | SINGLE LINE DIAGRAM | Heat Recovery Steam Generator |  |  |  | Single Line Diagram for HRSG |  | SKIP | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138143 | FIRE ALARM SYSTEM LAYOUT FOR GTG LUBE OIL UNIT | LAYOUT | Gas Turbine Generator |  |  |  | Layout Drawing for GTG | Substation | SKIP | 1CF1250W42A08 | (Lube Oil System) Installation_Lube oil functional Module | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Lube Oil System | 2008-03-17 | 2008-04-01 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138144 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GTG LUBE OIL UNIT | SINGLE LINE DIAGRAM | Gas Turbine Generator |  |  |  | Single Line Diagram for GTG |  | SKIP | 1PF1250W42A02P | (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Lube Oil System | 2007-03-01 | 2008-01-30 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-138201 | P&ID OF WATER SPRAY SYSTEM FOR BSDG DIESEL OIL DAY TANK | Piping & Instrumentation Drawing | Blackstart Diesel Generator,Tank |  |  |  | P&ID for Blackstart Diesel Generator,Tank | Emergency Diesel Generator/Blackstart Diesel Generator | FA | 0PF3530W42A05P | (BSDG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2007-08-01 | 2008-05-30 | 2024-08-29 | 2024-09-28 | 2024-10-28 | 2024-11-12 | 2024-11-27 | 2024-12-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-138211 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR BSDG DIESEL OIL DAY TANK | PIPE LAYOUT AND DETAIL | Blackstart Diesel Generator,Tank |  |  |  | PIPE LAYOUT AND DETAIL for Blackstart Diesel Generator,Tank | Emergency Diesel Generator/Blackstart Diesel Generator | FA | 0PF3530W42A05P | (BSDG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2007-08-01 | 2008-05-30 | 2024-12-19 | 2025-01-18 | 2025-02-17 | 2025-03-04 | 2025-03-19 | 2025-04-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-138221 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR BSDG DIESEL OIL DAY TANK | CALCULATION | Blackstart Diesel Generator,Tank |  |  |  | Calculation sheet for Blackstart Diesel Generator,Tank | Emergency Diesel Generator/Blackstart Diesel Generator | FA | 0SF3520W62A13.5 | (Day Tank) Day Tank filling | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > DFO Tank & Pump | 2008-08-15 | 2008-08-15 | 2025-09-13 | 2025-10-13 | 2025-11-12 | 2025-11-27 | 2025-12-12 | 2025-12-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138231 | PORTABLE EXTINGUISHER ARRANGEMENT FOR BSDG DIESEL OIL DAY TANK | ARRANGEMENT | Blackstart Diesel Generator,Tank |  |  |  | ARRANGEMENT for Blackstart Diesel Generator,Tank | Emergency Diesel Generator/Blackstart Diesel Generator | FA | 0EF3530W00A13 | (BSDG BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2007-05-01 |  | 2024-08-21 | 2024-09-20 | 2024-10-20 | 2024-11-04 | 2024-11-19 | 2024-12-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138241 | FIRE ALARM SYSTEM LAYOUT FOR BSDG DIESEL OIL DAY TANK | LAYOUT | Blackstart Diesel Generator,Tank |  |  |  | Layout Drawing for Blackstart Diesel Generator,Tank | Emergency Diesel Generator/Blackstart Diesel Generator | FA | 0CF3530W38A18 | (BSDG BLDG) Installation & Test - Fire Fighting Sys. Sys | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2008-05-31 | 2008-07-17 | 2025-07-27 | 2025-08-26 | 2025-09-25 | 2025-10-10 | 2025-10-25 | 2025-11-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138242 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR BSDG DIESEL OIL DAY TANK | SINGLE LINE DIAGRAM | Blackstart Diesel Generator,Tank |  |  |  | Single Line Diagram for Blackstart Diesel Generator,Tank |  | SKIP | 0CF3530W38A18 | (BSDG BLDG) Installation & Test - Fire Fighting Sys. Sys | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2008-05-31 | 2008-07-17 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-138301 | P&ID OF WATER SPRAY SYSTEM FOR GAS COMPRESSOR IN GPRS AREA | Piping & Instrumentation Drawing | Compressor |  |  |  | P&ID for Compressor | Fuel Gas Compressor | FA | 1PF3520W42A05.1P | (Gas COMP PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-03-15 | 2008-04-14 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-138311 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GAS COMPRESSOR IN GPRS AREA | PIPE LAYOUT AND DETAIL | Compressor |  |  |  | PIPE LAYOUT AND DETAIL for Compressor | Air Compressor | FA | 1PF3520W42A05.1P | (Gas COMP PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | 2007-03-15 | 2008-04-14 | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-138321 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GAS COMPRESSOR IN GPRS AREA | CALCULATION | Compressor |  |  |  | Calculation sheet for Compressor | AIR COMPRESSOR | FI | 0CF3510W42A08 | (COMP Air PKG) Installation_Compressor, Dryer | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2008-06-16 | 2008-08-16 |  |  |  | 2025-03-19 | 2025-04-18 | 2025-05-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138331 | PORTABLE EXTINGUISHER ARRANGEMENT FOR GPRS AREA | ARRANGEMENT |  |  |  |  | ARRANGEMENT |  | FA | 1PF3520W42A04P | (GPRS) P.O & Procurement for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-06-01 | 2008-03-31 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-30 | 2024-09-14 | 2024-09-29 | generated | 0.60 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138341 | FIRE ALARM SYSTEM LAYOUT FOR GPRS AREA | LAYOUT |  |  |  |  | Layout Drawing | Substation | SKIP | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138342 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GPRS AREA | SINGLE LINE DIAGRAM |  |  |  |  | Single Line Diagram |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-138401 | P&ID of Standpipe system for H2, CO2 Gas Storage Shelter | Piping & Instrumentation Drawing |  |  |  |  | P&ID |  | FA | 0EF3515W00A01 | (H2) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-03-01 | 2007-06-29 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-138411 | Pipe layout and detail of Standpipe system for H2, CO2 Gas Storage Shelter | layout and detail |  | Standpipe system | H2, CO2 Gas Storage Shelter |  | layout and detail for Standpipe system | Water Treatment System | FI | 0CF3010W24A08 | (DWP Chemical Storage Tank Shelter) Shelter Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2008-08-22 | 2008-10-13 | 2025-10-22 | 2025-11-21 | 2025-12-21 | 2026-01-05 | 2026-01-20 | 2026-02-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138431 | PORTABLE EXTINGUISHER ARRANGEMENT FOR H2, CO2 GAS STORAGE SHELTER | PORTABLE EXTINGUISHER ARRANGEMENT |  |  | H2, CO2 GAS STORAGE SHELTER |  | PORTABLE EXTINGUISHER ARRANGEMENT for H2, CO2 GAS STORAGE SHELTER | Gas Storage Shelter | FI | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138441 | FIRE ALARM SYSTEM LAYOUT FOR H2, CO2 GAS STORAGE SHELTER | LAYOUT |  | FIRE ALARM SYSTEM | H2, CO2 GAS STORAGE SHELTER |  | Layout Drawing for FIRE ALARM SYSTEM | Substation | SKIP | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138442 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR H2, CO2 GAS STORAGE SHELTER | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | H2, CO2 GAS STORAGE SHELTER |  | Single Line Diagram for FIRE ALARM SYSTEM |  | SKIP | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-138502 | P&ID OF CLEAN AGENT SYSTEM FOR AUX. LEB | Piping & Instrumentation Drawing |  | CLEAN AGENT SYSTEM | Auxiliary Local Electrical Building |  | P&ID for CLEAN AGENT SYSTEM | Water Treatment System | FA | 1PF1265W38A04P | (F/F GTG#11) P.O & Procurement_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fire fighting System | 2007-03-01 | 2008-03-14 | 2024-03-31 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-138512 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR AUX. LEB | LAYOUT AND DETAIL |  | CLEAN AGENT SYSTEM | Auxiliary Local Electrical Building |  | LAYOUT AND DETAIL for CLEAN AGENT SYSTEM |  | FA | 1CF1265W38A06 | (F/F GTG#11) Installation_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fire fighting System | 2008-04-30 | 2008-05-14 |  |  |  | 2025-01-31 | 2025-03-02 | 2025-04-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-138522 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR AUX. LEB | FLOW CALCULATION |  | CLEAN AGENT SYSTEM | Auxiliary Local Electrical Building |  | FLOW CALCULATION for CLEAN AGENT SYSTEM | Water Treatment System | FA | 2PF1265W38A04P | (F/F GTG#21)P.O & Procurement_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fire fighting System | 2007-03-30 | 2008-04-14 | 2024-04-29 | 2024-05-29 | 2024-06-28 | 2024-07-13 | 2024-07-28 | 2024-08-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138531 | PORTABLE EXTINGUISHER ARRANGEMENT FOR AUX. LEB | PORTABLE EXTINGUISHER ARRANGEMENT |  |  | Auxiliary Local Electrical Building |  | PORTABLE EXTINGUISHER ARRANGEMENT for Auxiliary Local Electrical Building |  | FA | 0EF3520W00A01.4 | (FO LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > Fuel Oil Supply System LEB | 2007-05-01 |  | 2025-06-25 | 2025-07-25 | 2025-08-24 | 2025-09-08 | 2025-09-23 | 2025-10-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138541 | FIRE ALARM SYSTEM LAYOUT FOR AUX. LEB | LAYOUT |  | FIRE ALARM SYSTEM | Auxiliary Local Electrical Building |  | Layout Drawing for FIRE ALARM SYSTEM | Substation | SKIP | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138542 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR AUX. LEB | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | Auxiliary Local Electrical Building |  | Single Line Diagram for FIRE ALARM SYSTEM |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-138601 | P&ID OF STAND PIPE SYSTEM FOR ST BUILDING | Piping & Instrumentation Drawing |  | STAND PIPE SYSTEM | Steam Turbine Building |  | P&ID for STAND PIPE SYSTEM | Water Treatment System | FA | 1PF5550W46A08P | (PipeRack) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-06-28 | 2008-01-02 | 2024-07-28 | 2024-08-27 | 2024-09-26 | 2024-10-11 | 2024-10-26 | 2024-11-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-138602 | P&ID OF SPRINKLER SYSTEM FOR ST BUILDING | Piping & Instrumentation Drawing |  | SPRINKLER SYSTEM | Steam Turbine Building |  | P&ID for SPRINKLER SYSTEM | Water Treatment System | FA | 0EF3010W00A02 | (Make-up WTR Supply System) P&ID & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-15 | 2007-11-21 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-138603 | P&ID OF PRE - ACTION SPRINKLER SYSTEM FOR ST BUILDING | Piping & Instrumentation Drawing |  | PRE - ACTION SPRINKLER SYSTEM | Steam Turbine Building |  | P&ID for PRE - ACTION SPRINKLER SYSTEM | Water Treatment System | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | 2024-04-29 | 2024-05-29 | 2024-06-28 | 2024-07-13 | 2024-07-28 | 2024-08-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-138604 | P&ID OF WATER SPRAY SYSTEM FOR GENERATOR LUBE OIL UNIT FOR ST BUILDING | Piping & Instrumentation Drawing |  | WATER SPRAY SYSTEM | Steam Turbine Building |  | P&ID for WATER SPRAY SYSTEM | Water Treatment System | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-138606 | P&ID OF WATER SPRAY SYSTEM FOR GENERATOR HYDROGEN SEAL OIL UNITS FOR ST BUILDING | Piping & Instrumentation Drawing |  | WATER SPRAY SYSTEM | Steam Turbine Building |  | P&ID for WATER SPRAY SYSTEM | Water Treatment System | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-138608 | P&ID of Clean agent system for Excitation Panel Room for ST Building | Piping & Instrumentation Drawing |  | Clean agent system | ST Building |  | P&ID for Clean agent system | Water Treatment System | FA | 1PF1265W38A04.7P | (F/F GTG#12) P.O & Procurement_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fire fighting System | 2007-03-01 | 2008-03-14 | 2024-03-31 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-138611 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR ST BUILDING | LAYOUT AND DETAIL |  | STAND PIPE SYSTEM | Steam Turbine Building |  | LAYOUT AND DETAIL for STAND PIPE SYSTEM | PIPE RACK | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGE-138612 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR ST BUILDING | LAYOUT AND DETAIL |  | SPRINKLER SYSTEM | Steam Turbine Building |  | LAYOUT AND DETAIL for SPRINKLER SYSTEM |  | FA | 0CF4500W24A10 | (Fire Fighting BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2008-05-21 | 2008-07-11 |  |  |  | 2025-02-21 | 2025-03-23 | 2025-04-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGE-138613 | PIPE LAYOUT AND DETAIL OF PRE - ACTION SPRINKLER SYSTEM FOR ST BUILDING | LAYOUT AND DETAIL |  | PRE - ACTION SPRINKLER SYSTEM | Steam Turbine Building |  | LAYOUT AND DETAIL for PRE - ACTION SPRINKLER SYSTEM |  | FA | 0CF4500W24A10 | (Fire Fighting BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2008-05-21 | 2008-07-11 |  |  |  | 2025-02-21 | 2025-03-23 | 2025-04-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-138614 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GENERATOR LUBE OIL UNIT FOR ST BUILDING | LAYOUT AND DETAIL |  | WATER SPRAY SYSTEM | Steam Turbine Building |  | LAYOUT AND DETAIL for WATER SPRAY SYSTEM |  | FA | 1CF2030W58A07 | (Lube Oil Sys.) Pipe Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Lube Oil System | 2008-10-31 | 2009-01-15 |  |  |  | 2025-08-03 | 2025-09-02 | 2025-10-02 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-138616 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GENERATOR HYDROGEN SEAL OIL UNITS FOR ST BUILDING | LAYOUT AND DETAIL |  | WATER SPRAY SYSTEM | ST BUILDING |  | LAYOUT AND DETAIL for WATER SPRAY SYSTEM |  | FA | 1CF1250W58A05.3 | (GEN Seal Oil Sys.) Piping Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Generator Seal Oil System | 2008-04-02 | 2008-05-02 |  |  |  | 2025-01-03 | 2025-02-02 | 2025-03-04 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-138618 | Pipe Layout and detail of Clean agent system for Excitation Panel Room for ST Building | Layout and detail |  |  | ST Building |  | Layout and detail for ST Building | ST BUILDING | FI | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGE-138622 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR ST BUILDING | CALCULATION |  |  | ST BUILDING |  | Calculation sheet for ST BUILDING | ST BUILDING | FI | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 |  |  |  | 2025-03-03 | 2025-04-02 | 2025-05-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGE-138623 | HYDRAULIC CALCULATION OF PRE - ACTION SPRINKLER SYSTEM FOR ST BUILDING | CALCULATION |  |  | ST BUILDING |  | Calculation sheet for ST BUILDING | ST BUILDING | FI | 0CF4500W24A10 | (Fire Fighting BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2008-05-21 | 2008-07-11 |  |  |  | 2025-02-21 | 2025-03-23 | 2025-04-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-138624 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GENERATOR LUBE OIL FOR ST BUILDING | CALCULATION |  | WATER SPRAY SYSTEM | ST BUILDING |  | Calculation sheet for WATER SPRAY SYSTEM | Water Treatment System | FA | 1PF2030W42A04P | (Lube Oil Sys.) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Lube Oil System | 2007-07-31 | 2008-07-30 | 2024-08-30 | 2024-09-29 | 2024-10-29 | 2024-11-13 | 2024-11-28 | 2024-12-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-138626 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GENERATOR HYDROGEN SEAL OIL UNITS FOR ST BUILDING | CALCULATION |  | WATER SPRAY SYSTEM | ST BUILDING |  | Calculation sheet for WATER SPRAY SYSTEM | Water Treatment System | FA | 1PF1250W42A02.3P | (GEN Seal Oil Sys.) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Generator Seal Oil System | 2007-03-01 | 2008-01-31 | 2024-03-31 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-138628 | Flow calculation of Clean Agent system for Excitation Panel Room for ST Building | calculation |  |  | ST Building |  | Calculation sheet for ST Building | ST BUILDING | FI | 2CF1265W38A06 | (F/F GTG#21) Installation_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fire fighting System | 2008-05-30 | 2008-06-13 |  |  |  | 2025-03-02 | 2025-04-01 | 2025-05-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138631 | PORTABLE EXTINGUISHER ARRANGEMENT FOR ST BUILDING | ARRANGEMENT |  |  | ST BUILDING |  | ARRANGEMENT for ST BUILDING | ST BUILDING | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138641 | FIRE ALARM SYSTEM LAYOUT FOR ST BUILDING | LAYOUT |  | FIRE ALARM SYSTEM | ST BUILDING |  | Layout Drawing for FIRE ALARM SYSTEM | Substation | SKIP | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138642 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR ST BUILDING | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | ST BUILDING |  | Single Line Diagram for FIRE ALARM SYSTEM |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-138643 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR ST BUILDING | CALCULATION |  | FIRE ALARM SYSTEM | ST BUILDING |  | Calculation sheet for FIRE ALARM SYSTEM | FIRE BRIGADE | FI | 0CF4500W24A10 | (Fire Fighting BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2008-05-21 | 2008-07-11 |  |  |  | 2025-02-21 | 2025-03-23 | 2025-04-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-138644 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR ST BUILDING | CAUSE & EFFECT MATRIX |  | FIRE ALARM SYSTEM | ST BUILDING |  | CAUSE & EFFECT MATRIX for FIRE ALARM SYSTEM |  | FA | 3PF1265W38A04P | (F/F GTG#31)P.O & Procurement_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fire fighting System | 2007-04-30 | 2008-05-13 | 2024-10-26 | 2024-11-25 | 2024-12-25 | 2025-01-09 | 2025-01-24 | 2025-02-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-138702 | P&ID OF CLEAN AGENT SYSTEM FOR ST#1 LEB | Piping & Instrumentation Drawing |  |  | ST#1 Local Electrical Building |  | P&ID for ST#1 Local Electrical Building | ST BUILDING | FI | 1EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | 2007-03-15 | 2008-01-15 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-138712 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR ST#1 LEB | LAYOUT AND DETAIL |  |  | ST#1 Local Electrical Building |  | LAYOUT AND DETAIL for ST#1 Local Electrical Building | ST BUILDING | FI | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-138722 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR ST#1 LEB | CALCULATION |  |  | ST#1 Local Electrical Building |  | Calculation sheet for ST#1 Local Electrical Building | Electrical Building | FI | 1CF1265W38A06 | (F/F GTG#11) Installation_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fire fighting System | 2008-04-30 | 2008-05-14 |  |  |  | 2025-01-31 | 2025-03-02 | 2025-04-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138731 | PORTABLE EXTINGUISHER ARRANGEMENT FOR ST#1 LEB | ARRANGEMENT |  |  | ST#1 Local Electrical Building |  | ARRANGEMENT for ST#1 Local Electrical Building | ST BUILDING | FI | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  |  |  |  | 2024-03-01 | 2024-03-16 | 2024-04-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138741 | FIRE ALARM SYSTEM LAYOUT FOR ST#1 LEB | LAYOUT |  | FIRE ALARM SYSTEM | ST#1 Local Electrical Building |  | Layout Drawing for FIRE ALARM SYSTEM | Substation | SKIP | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138742 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR ST#1 LEB | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | ST#1 Local Electrical Building |  | Single Line Diagram for FIRE ALARM SYSTEM |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-138743 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR ST#1 LEB | CALCULATION |  | FIRE ALARM SYSTEM | ST#1 Local Electrical Building |  | Calculation sheet for FIRE ALARM SYSTEM | FIRE BRIGADE | FI | 1CF1200W38A06 | (GTG #11 LEB) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 LEB | 2008-05-31 | 2008-07-04 |  |  |  | 2025-03-03 | 2025-04-02 | 2025-05-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-138744 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR ST#1 LEB | CAUSE & EFFECT MATRIX |  | FIRE ALARM SYSTEM | ST#1 Local Electrical Building |  | CAUSE & EFFECT MATRIX for FIRE ALARM SYSTEM |  | FA | 1PF1265W38A04P | (F/F GTG#11) P.O & Procurement_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fire fighting System | 2007-03-01 | 2008-03-14 | 2024-08-27 | 2024-09-26 | 2024-10-26 | 2024-11-10 | 2024-11-25 | 2024-12-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-138802 | P&ID OF CLEAN AGENT SYSTEM FOR ST#2 LEB | Piping & Instrumentation Drawing |  | CLEAN AGENT SYSTEM | Steam Turbine#2 Local Electrical Building |  | P&ID for CLEAN AGENT SYSTEM | Water Treatment System | FA | 2PF1265W38A04P | (F/F GTG#21)P.O & Procurement_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fire fighting System | 2007-03-30 | 2008-04-14 | 2024-04-29 | 2024-05-29 | 2024-06-28 | 2024-07-13 | 2024-07-28 | 2024-08-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-138812 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR ST#2 LEB | PIPE LAYOUT AND DETAIL |  | CLEAN AGENT SYSTEM | Steam Turbine#2 Local Electrical Building |  | PIPE LAYOUT AND DETAIL for CLEAN AGENT SYSTEM | PIPE RACK | FI | 2CF1265W38A06 | (F/F GTG#21) Installation_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fire fighting System | 2008-05-30 | 2008-06-13 |  |  |  | 2025-03-02 | 2025-04-01 | 2025-05-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-138822 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR ST#2 LEB | FLOW CALCULATION |  | CLEAN AGENT SYSTEM | Steam Turbine#2 Local Electrical Building |  | FLOW CALCULATION for CLEAN AGENT SYSTEM | Water Treatment System | FA | 2PF1265W38A04P | (F/F GTG#21)P.O & Procurement_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fire fighting System | 2007-03-30 | 2008-04-14 | 2024-04-29 | 2024-05-29 | 2024-06-28 | 2024-07-13 | 2024-07-28 | 2024-08-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138831 | PORTABLE EXTINGUISHER ARRANGEMENT FOR ST#2 LEB | ARRANGEMENT |  |  | Steam Turbine#2 Local Electrical Building |  | ARRANGEMENT for Steam Turbine#2 Local Electrical Building |  | FA | 2EF1600W00A01 | (HRSG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | 2007-06-20 |  | 2025-08-14 | 2025-09-13 | 2025-10-13 | 2025-10-28 | 2025-11-12 | 2025-11-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138841 | FIRE ALARM SYSTEM LAYOUT FOR ST#2 LEB | LAYOUT |  | FIRE ALARM SYSTEM | Steam Turbine#2 Local Electrical Building |  | Layout Drawing for FIRE ALARM SYSTEM | Substation | SKIP | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138842 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR ST#2 LEB | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | Steam Turbine#2 Local Electrical Building |  | Single Line Diagram for FIRE ALARM SYSTEM |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-138843 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR ST#2 LEB | BATTERY CALCULATION |  | FIRE ALARM SYSTEM | Steam Turbine#2 Local Electrical Building |  | BATTERY CALCULATION for FIRE ALARM SYSTEM | FIRE BRIGADE | FI | 2CF1200W38A06 | (GTG #21 LEB) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2008-05-31 | 2008-07-04 |  |  |  | 2025-03-03 | 2025-04-02 | 2025-05-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-138844 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR ST#2 LEB | CAUSE & EFFECT MATRIX |  | FIRE ALARM SYSTEM | Steam Turbine#2 Local Electrical Building |  | CAUSE & EFFECT MATRIX for FIRE ALARM SYSTEM |  | FA | 3SF1265W62A09.20 | (F/F GTG#32) Function Test(incl. Alarm Test) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fire fighting System | 2008-08-14 | 2008-08-23 | 2026-02-10 | 2026-03-12 | 2026-04-11 | 2026-04-26 | 2026-05-11 | 2026-05-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-138901 | P&ID OF STAND PIPE SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | Piping & Instrumentation Drawing |  | STAND PIPE SYSTEM |  |  | P&ID for STAND PIPE SYSTEM | Water Treatment System | FA | 1PF5550W46A08P | (PipeRack) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-06-28 | 2008-01-02 | 2024-07-28 | 2024-08-27 | 2024-09-26 | 2024-10-11 | 2024-10-26 | 2024-11-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-138902 | P&ID OF WATER SPRAY SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | Piping & Instrumentation Drawing |  | WATER SPRAY SYSTEM |  |  | P&ID for WATER SPRAY SYSTEM | Water Treatment System | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-138911 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | PIPE LAYOUT AND DETAIL |  | STAND PIPE SYSTEM |  |  | PIPE LAYOUT AND DETAIL for STAND PIPE SYSTEM | PIPE RACK | FI | 3EF5550W20A05 | (PipeRack) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-05-30 | 2007-08-31 |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-138912 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | PIPE LAYOUT AND DETAIL |  | WATER SPRAY SYSTEM |  |  | PIPE LAYOUT AND DETAIL for WATER SPRAY SYSTEM | Water Treatment System | FI | 1EF5550W20A05 | (PipeRack) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | 2024-09-27 | 2024-10-27 | 2024-11-26 | 2024-12-11 | 2024-12-26 | 2025-01-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-138922 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | HYDRAULIC CALCULATION |  | WATER SPRAY SYSTEM |  |  | HYDRAULIC CALCULATION for WATER SPRAY SYSTEM | Water Treatment System | FA | 0PF3035W42A06.0P | (SWS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-08-31 | 2008-09-01 | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-138931 | PORTABLE EXTINGUISHER ARRANGEMENT FOR DEAERATOR SUPPORT STRUCTURE | ARRANGEMENT |  |  |  |  | ARRANGEMENT |  | FA | 2PF1610W20A03P | (HRSG #21 S/Structure & Casing) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Steel Structure & Casing | 2007-06-14 | 2008-03-03 | 2024-07-14 | 2024-07-29 | 2024-08-13 | 2024-09-12 | 2024-09-27 | 2024-10-12 | generated | 0.60 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-138941 | FIRE ALARM SYSTEM LAYOUT FOR DEAERATOR SUPPORT STRUCTURE | LAYOUT |  | FIRE ALARM SYSTEM |  |  | Layout Drawing for FIRE ALARM SYSTEM | Substation | SKIP | 0EF4500W32A04.1 | (Fire Fighting BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-12-03 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-138942 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM |  |  | Single Line Diagram for FIRE ALARM SYSTEM |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-139001 | P&ID OF STAND PIPE SYSTEM FOR ADMINISTRATION & SOCIAL BUILDING | Piping & Instrumentation Drawing |  | STAND PIPE SYSTEM | ADMINISTRATION & SOCIAL BUILDING |  | P&ID for STAND PIPE SYSTEM | Water Treatment System | FA | 1PF5550W46A08P | (PipeRack) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-06-28 | 2008-01-02 | 2024-07-28 | 2024-08-27 | 2024-09-26 | 2024-10-11 | 2024-10-26 | 2024-11-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-139002 | P&ID of Clean Agent system for Administration & Social Building | Piping & Instrumentation Drawing |  | Clean Agent system | Administration & Social Building |  | P&ID for Clean Agent system | Water Treatment System | FA | 1PF1265W38A04.7P | (F/F GTG#12) P.O & Procurement_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fire fighting System | 2007-03-01 | 2008-03-14 | 2024-03-31 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-139011 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR ADMINISTRATION & SOCIAL BUILDING | PIPE LAYOUT AND DETAIL |  | STAND PIPE SYSTEM | ADMINISTRATION & SOCIAL BUILDING |  | PIPE LAYOUT AND DETAIL for STAND PIPE SYSTEM | PIPE RACK | FI | 2EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-03-30 |  |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-139012 | Pipe Layout and detail of Clean Agent system for Administration & Social Building | Pipe Layout and detail |  | Clean Agent system | Administration & Social Building |  | Pipe Layout and detail for Clean Agent system | Water Treatment System | FI | 1PF1265W38A04.7P | (F/F GTG#12) P.O & Procurement_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fire fighting System | 2007-03-01 | 2008-03-14 | 2024-06-29 | 2024-07-29 | 2024-08-28 | 2024-09-12 | 2024-09-27 | 2024-10-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-139023 | Flow calculation of Clean Agent system for Administration & Social Building | Flow calculation |  |  | Administration & Social Building |  | Flow calculation for Administration & Social Building |  | FA | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 | 2026-10-24 | 2026-11-23 | 2026-12-23 | 2027-01-07 | 2027-01-22 | 2027-02-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139031 | PORTABLE EXTINGUISHER ARRANGEMENT FOR ADMINISTRATION & SOCIAL BUILDING | ARRANGEMENT |  |  | ADMINISTRATION & SOCIAL BUILDING |  | ARRANGEMENT for ADMINISTRATION & SOCIAL BUILDING |  | FA | 0EF5566W00A01 | (ADMIN BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 |  | 2025-08-22 | 2025-09-21 | 2025-10-21 | 2025-11-05 | 2025-11-20 | 2025-12-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139041 | FIRE ALARM SYSTEM LAYOUT FOR ADMINISTRATION & SOCIAL BUILDING | LAYOUT |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Layout Drawing for ADMINISTRATION & SOCIAL BUILDING |  | FA | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 | 2026-10-24 | 2026-11-23 | 2026-12-23 | 2027-01-07 | 2027-01-22 | 2027-02-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139042 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR ADMINISTRATION & SOCIAL BUILDING | SINGLE LINE DIAGRAM |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Single Line Diagram for ADMINISTRATION & SOCIAL BUILDING |  | FA | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | 2025-07-24 | 2025-08-23 | 2025-09-22 | 2025-10-07 | 2025-10-22 | 2025-11-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-139043 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR ADMINISTRATION & SOCIAL BUILDING | BATTERY CALCULATION |  |  | ADMINISTRATION & SOCIAL BUILDING |  | BATTERY CALCULATION for ADMINISTRATION & SOCIAL BUILDING |  | FA | 0CF6500W70A04.5 | (Battery) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Batteries | 2008-06-04 | 2008-06-10 | 2026-10-28 | 2026-11-27 | 2026-12-27 | 2027-01-11 | 2027-01-26 | 2027-02-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-139044 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR ADMINISTRATION & SOCIAL BUILDING | CAUSE & EFFECT MATRIX |  |  | ADMINISTRATION & SOCIAL BUILDING |  | CAUSE & EFFECT MATRIX for ADMINISTRATION & SOCIAL BUILDING |  | FA | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 | 2026-10-24 | 2026-11-23 | 2026-12-23 | 2027-01-07 | 2027-01-22 | 2027-02-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-139101 | P&ID OF STAND PIPE SYSTEM FOR SECURITY BUILDING | Piping & Instrumentation Drawing |  |  | SECURITY BUILDING |  | P&ID for SECURITY BUILDING |  | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | 2025-08-23 | 2025-09-22 | 2025-10-22 | 2025-11-06 | 2025-11-21 | 2025-12-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-139103 | P&ID OF CLEAN AGENT SYSTEM FOR SECURITY BUILDING | Piping & Instrumentation Drawing |  |  | SECURITY BUILDING |  | P&ID for SECURITY BUILDING |  | FA | 1EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | 2007-03-15 | 2008-01-15 | 2025-07-08 | 2025-08-07 | 2025-09-06 | 2025-09-21 | 2025-10-06 | 2025-10-21 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-139111 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR SECURITY BUILDING | PIPE LAYOUT AND DETAIL |  |  | SECURITY BUILDING |  | PIPE LAYOUT AND DETAIL for SECURITY BUILDING |  | FA | 3EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-05-30 | 2007-08-31 | 2025-09-22 | 2025-10-22 | 2025-11-21 | 2025-12-06 | 2025-12-21 | 2026-01-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-139113 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR SECURITY BUILDING | PIPE LAYOUT AND DETAIL |  |  | SECURITY BUILDING |  | PIPE LAYOUT AND DETAIL for SECURITY BUILDING |  | FA | 1CF1265W38A06.7 | (F/F GTG#12) Installation_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fire fighting System | 2008-04-30 | 2008-05-14 | 2026-08-24 | 2026-09-23 | 2026-10-23 | 2026-11-07 | 2026-11-22 | 2026-12-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-139123 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR SECURITY BUILDING | FLOW CALCULATION |  |  | SECURITY BUILDING |  | FLOW CALCULATION for SECURITY BUILDING | SECURITY BUILDING | FI | 2CF1265W38A06 | (F/F GTG#21) Installation_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fire fighting System | 2008-05-30 | 2008-06-13 |  |  |  | 2025-03-02 | 2025-04-01 | 2025-05-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139131 | PORTABLE EXTINGUISHER ARRANGEMENT FOR SECURITY BUILDING | ARRANGEMENT |  |  | SECURITY BUILDING |  | ARRANGEMENT for SECURITY BUILDING |  | FA | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | 2025-11-30 | 2025-12-30 | 2026-01-29 | 2026-02-13 | 2026-02-28 | 2026-03-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139141 | FIRE ALARM SYSTEM LAYOUT FOR SECURITY BUILDING | LAYOUT |  |  | SECURITY BUILDING |  | Layout Drawing for SECURITY BUILDING |  | FA | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  | 2025-11-30 | 2025-12-30 | 2026-01-29 | 2026-02-13 | 2026-02-28 | 2026-03-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139142 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR SECURITY BUILDING | SINGLE LINE DIAGRAM |  |  | SECURITY BUILDING |  | Single Line Diagram for SECURITY BUILDING |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-139143 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR SECURITY BUILDING | BATTERY CALCULATION |  |  | SECURITY BUILDING |  | BATTERY CALCULATION for SECURITY BUILDING | SECURITY BUILDING | FI | 0CF6500W70A04.5 | (Battery) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Batteries | 2008-06-04 | 2008-06-10 |  |  |  | 2025-03-07 | 2025-04-06 | 2025-05-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-139144 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR SECURITY BUILDING | CAUSE & EFFECT MATRIX |  |  | SECURITY BUILDING |  | CAUSE & EFFECT MATRIX for SECURITY BUILDING |  | FA | 0CF5510W38A06 | (CCR BLDG) Installation & Test - Fire Fighting Sys. for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-05-31 | 2008-07-31 | 2026-09-24 | 2026-10-24 | 2026-11-23 | 2026-12-08 | 2026-12-23 | 2027-01-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139231 | PORTABLE EXTINGUISHER ARRANGEMENT FOR MAIN GATE HOUSE | ARRANGEMENT |  |  | MAIN GATE HOUSE |  | ARRANGEMENT for MAIN GATE HOUSE | MAIN GATE | FI | 0EF5570W16A01 | (Gate House) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139241 | FIRE ALARM SYSTEM LAYOUT FOR MAIN GATE HOUSE | LAYOUT |  |  | MAIN GATE HOUSE |  | Layout Drawing for MAIN GATE HOUSE | MAIN GATE | FI | 0CF5570W38A05 | (Gate House) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-05 | 2008-07-01 |  |  |  | 2025-02-05 | 2025-03-07 | 2025-04-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139242 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR MAIN GATE HOUSE | SINGLE LINE DIAGRAM |  |  | MAIN GATE HOUSE |  | Single Line Diagram for MAIN GATE HOUSE |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-139301 | P&ID OF STAND PIPE SYSTEM FOR X-RAY SEARCHING ROOM | Piping & Instrumentation Drawing |  |  |  |  | P&ID |  | FA | 1PF5550W46A08P | (PipeRack) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-06-28 | 2008-01-02 | 2024-07-26 | 2024-08-25 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-139311 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR X-RAY SEARCHING ROOM | PIPE LAYOUT AND DETAIL |  |  | X-RAY SEARCHING ROOM |  | PIPE LAYOUT AND DETAIL for X-RAY SEARCHING ROOM | PIPE RACK | FI | 2EF5550W00A01 | (PipeRack) Pipe Rack Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-03-01 | 2007-03-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139331 | PORTABLE EXTINGUISHER ARRANGEMENT FOR X-RAY SEARCHING ROOM | ARRANGEMENT |  |  | X-RAY SEARCHING ROOM |  | ARRANGEMENT for X-RAY SEARCHING ROOM |  | FA | 0PF4500W38A03P | (Fire Fighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-08-01 | 2008-06-18 | 2024-12-12 | 2025-01-11 | 2025-02-10 | 2025-02-25 | 2025-03-12 | 2025-03-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139341 | FIRE ALARM SYSTEM LAYOUT FOR X-RAY SEARCHING ROOM | LAYOUT |  | FIRE ALARM SYSTEM | X-RAY SEARCHING ROOM |  | Layout Drawing for FIRE ALARM SYSTEM | Substation | SKIP | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139342 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR X-RAY SEARCHING ROOM | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | X-RAY SEARCHING ROOM |  | Single Line Diagram for FIRE ALARM SYSTEM |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-139401 | P&ID OF STAND PIPE SYSTEM FOR FIRE BRIGADE BUILDING | Piping & Instrumentation Drawing |  |  | FIRE BRIGADE BUILDING |  | P&ID for FIRE BRIGADE BUILDING | FIRE BRIGADE | FI | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-139411 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR FIRE BRIGADE BUILDING | PIPE LAYOUT AND DETAIL |  |  | FIRE BRIGADE BUILDING |  | PIPE LAYOUT AND DETAIL for FIRE BRIGADE BUILDING | FIRE BRIGADE | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139431 | PORTABLE EXTINGUISHER ARRANGEMENT FOR FIRE BRIGADE BUILDING | ARRANGEMENT |  |  | FIRE BRIGADE BUILDING |  | ARRANGEMENT for FIRE BRIGADE BUILDING | FIRE BRIGADE | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139441 | FIRE ALARM SYSTEM LAYOUT FOR FIRE BRIGADE BUILDING | LAYOUT |  | FIRE ALARM SYSTEM | FIRE BRIGADE BUILDING |  | Layout Drawing for FIRE ALARM SYSTEM | Substation | SKIP | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139442 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR FIRE BRIGADE BUILDING | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | FIRE BRIGADE BUILDING |  | Single Line Diagram for FIRE ALARM SYSTEM |  | SKIP | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-139443 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR FIRE BRIGADE BUILDING | CALCULATION |  | FIRE ALARM SYSTEM | FIRE BRIGADE BUILDING |  | Calculation sheet for FIRE ALARM SYSTEM | FIRE BRIGADE | FI | 0CF4500W24A10 | (Fire Fighting BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2008-05-21 | 2008-07-11 |  |  |  | 2025-02-21 | 2025-03-23 | 2025-04-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-139444 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR FIRE BRIGADE BUILDING | MATRIX |  | FIRE ALARM SYSTEM | FIRE BRIGADE BUILDING |  | MATRIX for FIRE ALARM SYSTEM |  | FA | 0CF4500W24A10 | (Fire Fighting BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2008-05-21 | 2008-07-11 |  |  |  | 2025-02-21 | 2025-03-23 | 2025-04-22 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-139501 | P&ID OF STAND PIPE SYSTEM FOR WORKSHOP & STORAGE BUILDING | Piping & Instrumentation Drawing |  |  | WORKSHOP & STORAGE BUILDING |  | P&ID for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-31 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-139502 | P&ID OF SPRINKLER SYSTEM FOR WORKSHOP & STORAGE BUILDING | Piping & Instrumentation Drawing |  |  | WORKSHOP & STORAGE BUILDING |  | P&ID for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 0EF3045W00A01.0 | (Chlorination System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Chlorination System | 2007-03-30 | 2007-11-13 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-139511 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR WORKSHOP & STORAGE BUILDING | PIPE LAYOUT AND DETAIL |  |  | WORKSHOP & STORAGE BUILDING |  | PIPE LAYOUT AND DETAIL for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGE-139512 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR WORKSHOP & STORAGE BUILDING | PIPE LAYOUT AND DETAIL |  |  | WORKSHOP & STORAGE BUILDING |  | PIPE LAYOUT AND DETAIL for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGE-139522 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR WORKSHOP & STORAGE BUILDING | CALCULATION |  |  | WORKSHOP & STORAGE BUILDING |  | Calculation sheet for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 0CF5560W38A06 | (M&E WORKSHOP BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-11-01 | 2008-12-27 |  |  |  | 2025-08-04 | 2025-09-03 | 2025-10-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139531 | PORTABLE EXTINGUISHER ARRANGEMENT FOR WORKSHOP & STORAGE BUILDING | ARRANGEMENT |  |  | WORKSHOP & STORAGE BUILDING |  | ARRANGEMENT for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139541 | FIRE ALARM SYSTEM LAYOUT FOR MAINTENANCE AND WORKSHOP & STORAGE BUILDING | LAYOUT |  | FIRE ALARM SYSTEM | MAINTENANCE AND WORKSHOP & STORAGE BUILDING |  | Layout Drawing for FIRE ALARM SYSTEM | Substation | SKIP | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139542 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR WORKSHOP & STORAGE BUILDING | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | WORKSHOP & STORAGE BUILDING |  | Single Line Diagram for FIRE ALARM SYSTEM |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0CYE-139543 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR WORKSHOP & STORAGE BUILDING | CALCULATION |  | FIRE ALARM SYSTEM | WORKSHOP & STORAGE BUILDING |  | Calculation sheet for FIRE ALARM SYSTEM | FIRE BRIGADE | FI | 0CF5560W38A06 | (M&E WORKSHOP BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-11-01 | 2008-12-27 |  |  |  | 2025-08-04 | 2025-09-03 | 2025-10-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0CYE-139544 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR WORKSHOP & STORAGE BUILDING | MATRIX |  | FIRE ALARM SYSTEM | WORKSHOP & STORAGE BUILDING |  | MATRIX for FIRE ALARM SYSTEM |  | FA | 0CF5560W38A06 | (M&E WORKSHOP BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-11-01 | 2008-12-27 |  |  |  | 2025-08-04 | 2025-09-03 | 2025-10-03 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGA-139601 | P&ID OF STAND PIPE SYSTEM FOR CPP BUILDING | Piping & Instrumentation Drawing |  | STAND PIPE SYSTEM | CPP BUILDING |  | P&ID for STAND PIPE SYSTEM | Water Treatment System | FA | 2PF5550W46A08P | (PipeRack) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-06-28 | 2008-02-01 | 2024-07-28 | 2024-08-27 | 2024-09-26 | 2024-10-11 | 2024-10-26 | 2024-11-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGK-139602 | P&ID OF CLEAN AGENT SYSTEM FOR CPP BUILDING | Piping & Instrumentation Drawing |  | CLEAN AGENT SYSTEM | CPP BUILDING |  | P&ID for CLEAN AGENT SYSTEM | Water Treatment System | FA | 2PF1265W38A04P | (F/F GTG#21)P.O & Procurement_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fire fighting System | 2007-03-30 | 2008-04-14 | 2024-04-29 | 2024-05-29 | 2024-06-28 | 2024-07-13 | 2024-07-28 | 2024-08-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGE-139603 | P&ID OF SPRINKLER SYSTEM FOR CPP BUILDING | Piping & Instrumentation Drawing |  | SPRINKLER SYSTEM | CPP BUILDING |  | P&ID for SPRINKLER SYSTEM | Water Treatment System | FA | 0EF3045W00A01.0 | (Chlorination System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Chlorination System | 2007-03-30 | 2007-11-13 | 2024-04-29 | 2024-05-29 | 2024-06-28 | 2024-07-13 | 2024-07-28 | 2024-08-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGA-139611 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR CPP BUILDING | PIPE LAYOUT AND DETAIL |  | STAND PIPE SYSTEM | CPP BUILDING |  | PIPE LAYOUT AND DETAIL for STAND PIPE SYSTEM | PIPE RACK | FI | 2EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-03-30 |  |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGK-139612 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR CPP BUILDING | PIPE LAYOUT AND DETAIL |  | CLEAN AGENT SYSTEM | CPP BUILDING |  | PIPE LAYOUT AND DETAIL for CLEAN AGENT SYSTEM | PIPE RACK | FI | 1CF1265W38A06 | (F/F GTG#11) Installation_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fire fighting System | 2008-04-30 | 2008-05-14 |  |  |  | 2025-01-31 | 2025-03-02 | 2025-04-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGE-139613 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR CPP BUILDING | PIPE LAYOUT AND DETAIL |  | SPRINKLER SYSTEM | CPP BUILDING |  | PIPE LAYOUT AND DETAIL for SPRINKLER SYSTEM | PIPE RACK | FI | 0EF6020W00A01 | (BOP Piping) Pipe Arrangement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-04-30 | 2008-09-30 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-31 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGK-139622 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR CPP BUILDING | FLOW CALCULATION |  | CLEAN AGENT SYSTEM | CPP BUILDING |  | FLOW CALCULATION for CLEAN AGENT SYSTEM | Water Treatment System | FA | 2PF1265W38A04P | (F/F GTG#21)P.O & Procurement_Clean Agent FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fire fighting System | 2007-03-30 | 2008-04-14 | 2024-04-29 | 2024-05-29 | 2024-06-28 | 2024-07-13 | 2024-07-28 | 2024-08-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGE-139623 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR CPP BUILDING | HYDRAULIC CALCULATION |  | SPRINKLER SYSTEM | CPP BUILDING |  | HYDRAULIC CALCULATION for SPRINKLER SYSTEM | Water Treatment System | FA | 0PF4500W38A09P | (Fire Fighting System) P.O & Procurement_piping | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-08-01 | 2007-12-31 | 2024-08-31 | 2024-09-30 | 2024-10-30 | 2024-11-14 | 2024-11-29 | 2024-12-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139631 | PORTABLE EXTINGUISHER ARRANGEMENT FOR CPP BUILDING | PORTABLE EXTINGUISHER ARRANGEMENT |  |  | CPP BUILDING |  | PORTABLE EXTINGUISHER ARRANGEMENT for CPP BUILDING | CPP Regeneration Building | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139641 | FIRE ALARM SYSTEM LAYOUT FOR CPP BUILDING | LAYOUT |  | FIRE ALARM SYSTEM | CPP BUILDING |  | Layout Drawing for FIRE ALARM SYSTEM | Substation | SKIP | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139642 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR CPP BUILDING | SINGLE LINE DIAGRAM |  | FIRE ALARM SYSTEM | CPP BUILDING |  | Single Line Diagram for FIRE ALARM SYSTEM |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139731 | PORTABLE EXTINGUISHER ARRANGEMENT FOR CHEMICAL DOSING SHELTER FOR STG & HRSG | PORTABLE EXTINGUISHER ARRANGEMENT | Steam Turbine & Generator, Heat Recovery Steam Generator |  | CHEMICAL DOSING SHELTER |  | PORTABLE EXTINGUISHER ARRANGEMENT for Steam Turbine & Generator, Heat Recovery Steam Generator |  | FA | 3EF1600W00A02 | (HRSG #31/#32) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139741 | FIRE ALARM SYSTEM LAYOUT FOR CHEMICAL DOSING SHELTER FOR STG & HRSG | LAYOUT | Steam Turbine & Generator, Heat Recovery Steam Generator | FIRE ALARM SYSTEM | CHEMICAL DOSING SHELTER |  | Layout Drawing for Steam Turbine & Generator, Heat Recovery Steam Generator | STEAM TURBINE GENERATOR | FA | 1CF1600W38A14.1 | (HRSG #12 LEB) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | 2008-11-01 | 2008-12-15 |  |  |  | 2025-08-04 | 2025-09-03 | 2025-10-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139742 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR CHEMICAL DOSING SHELTER FOR STG & HRSG | SINGLE LINE DIAGRAM | Steam Turbine & Generator, Heat Recovery Steam Generator | FIRE ALARM SYSTEM | CHEMICAL DOSING SHELTER |  | Single Line Diagram for Steam Turbine & Generator, Heat Recovery Steam Generator |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139831 | PORTABLE EXTINGUISHER ARRANGEMENT FOR CHEMICAL DOSING SHELTER FOR HRSG | PORTABLE EXTINGUISHER ARRANGEMENT | Heat Recovery Steam Generator |  | CHEMICAL DOSING SHELTER |  | PORTABLE EXTINGUISHER ARRANGEMENT for HRSG |  | FA | 3EF1600W00A02 | (HRSG #31/#32) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139841 | FIRE ALARM SYSTEM LAYOUT FOR CHEMICAL DOSING SHELTER FOR HRSG | LAYOUT | Heat Recovery Steam Generator | FIRE ALARM SYSTEM | CHEMICAL DOSING SHELTER |  | Layout Drawing for HRSG |  | FA | 1CF1600W38A14.1 | (HRSG #12 LEB) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | 2008-11-01 | 2008-12-15 | 2026-07-15 | 2026-08-14 | 2026-09-13 | 2026-09-28 | 2026-10-13 | 2026-10-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139842 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR CHEMICAL DOSING SHELTER FOR HRSG | SINGLE LINE DIAGRAM | Heat Recovery Steam Generator | FIRE ALARM SYSTEM | CHEMICAL DOSING SHELTER |  | Single Line Diagram for HRSG |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0SGC-139901 | P&ID OF WATER SPRAY SYSTEM FOR STG EXCITATION TRANSFORMER | Piping & Instrumentation Drawing | Steam Turbine & Generator EXCITATION TRANSFORMER | WATER SPRAY SYSTEM |  |  | P&ID for Steam Turbine & Generator EXCITATION TRANSFORMER | STEAM TURBINE GENERATOR | FA | 0EF3010W00A03 | (WTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-03-15 | 2007-11-21 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0SGC-139911 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR STG EXCITATION TRANSFORMER | PIPE LAYOUT AND DETAIL | Steam Turbine & Generator EXCITATION TRANSFORMER | WATER SPRAY SYSTEM |  |  | PIPE LAYOUT AND DETAIL for Steam Turbine & Generator EXCITATION TRANSFORMER | STEAM TURBINE GENERATOR | FA | 1CF6500W38A15 | (STG TR) F/F test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-12-20 | 2008-12-26 |  |  |  | 2025-09-22 | 2025-10-22 | 2025-11-21 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0SGC-139921 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR STG EXCITATION TRANSFORMER | CALCULATION | Steam Turbine & Generator EXCITATION TRANSFORMER | WATER SPRAY SYSTEM |  |  | Calculation sheet for Steam Turbine & Generator EXCITATION TRANSFORMER | STEAM TURBINE GENERATOR | FA | 1CF6500W38A15 | (STG TR) F/F test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-12-20 | 2008-12-26 |  |  |  | 2025-11-21 | 2025-10-22 | 2025-09-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0SGZ-139931 | PORTABLE EXTINGUISHER ARRANGEMENT FOR STG EXCITATION TRANSFORMER | ARRANGEMENT | Steam Turbine & Generator EXCITATION TRANSFORMER |  |  |  | ARRANGEMENT for Steam Turbine & Generator EXCITATION TRANSFORMER | STEAM TURBINE GENERATOR | FA | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  |  |  |  | 2024-10-29 | 2024-09-29 | 2024-08-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CYE-139941 | FIRE ALARM SYSTEM LAYOUT FOR STG EXCITATION TRANSFORMER | LAYOUT | Steam Turbine & Generator EXCITATION TRANSFORMER | FIRE ALARM SYSTEM |  |  | Layout Drawing for Steam Turbine & Generator EXCITATION TRANSFORMER | STEAM TURBINE GENERATOR | FA | 1CF6500W38A15 | (STG TR) F/F test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-12-20 | 2008-12-26 |  |  |  | 2025-09-22 | 2025-10-22 | 2025-11-21 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYE-139942 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR STG EXCITATION TRANSFORMER | SINGLE LINE DIAGRAM | Steam Turbine & Generator EXCITATION TRANSFORMER | FIRE ALARM SYSTEM |  |  | Single Line Diagram for Steam Turbine & Generator EXCITATION TRANSFORMER |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-140001 | PIPING MATERIAL SPECIFICATION | MATERIAL SPECIFICATION |  | PIPING |  |  | MATERIAL SPECIFICATION for PIPING | FireFighting | FA | 0EF6020W58A01 | (Piping) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement |  | 2007-07-30 | [6 empty] | missing_date |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-140002 | PIPING INSULATION SPECIFICATION | SPECIFICATION |  | PIPING |  |  | Technical Specification for PIPING | FireFighting | FA | 0EF6020W00A03 | (BOP Piping) Piping Insulation Specification | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-04-02 | 2008-01-28 | 2024-04-30 | 2024-05-28 | 2024-06-25 | 2024-06-18 | 2024-07-16 | 2024-08-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0ZEN-140003 | MANUAL VALVE LIST | LIST |  |  |  |  | LIST |  | FA | 0PF6050W86A02P | (Manual Valve) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Manual Valve | 2007-09-24 | 2008-02-29 | 2024-10-22 | 2024-11-21 | 2024-12-21 | 2025-01-05 | 2025-01-20 | 2025-02-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XL00-P0ZEN-140004 | PIPING SPECIALTY LIST | LIST |  | PIPING |  |  | LIST for PIPING |  | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | 2026-04-09 | 2026-05-09 | 2026-06-08 | 2026-06-23 | 2026-07-08 | 2026-07-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XL00-P0ZEN-140005 | PIPING LINE LIST | LIST |  | PIPING |  |  | LIST for PIPING |  | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | 2026-04-09 | 2026-05-09 | 2026-06-08 | 2026-06-23 | 2026-07-08 | 2026-07-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XL00-P0ZEN-140006 | PIPING TERMINAL POINT LIST BETWEEN FCHPP AND FGP | LIST | Fuel Conditioning & Heating Preparation Package AND Fuel Gas Package | PIPING |  |  | LIST for Fuel Conditioning & Heating Preparation Package AND Fuel Gas Package | Fuel Gas System | FI | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | 2024-06-07 | 2024-07-19 | 2024-08-30 | 2024-08-09 | 2024-09-20 | 2024-11-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-BP00-P0LBA-140011 | STRESS ANALYSIS REPORT FOR HP STEAM SYSTEM | ANALYSIS REPORT |  | High Pressure STEAM SYSTEM |  |  | ANALYSIS REPORT for High Pressure STEAM SYSTEM |  | FA | 1PF3520W42A14P | (GPRS) P.O & Procurement for HRSG | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-07-03 | 2008-04-30 | 2024-10-23 | 2024-11-22 | 2024-12-22 | 2025-01-06 | 2025-01-21 | 2025-02-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-BP00-P0LBC-140012 | STRESS ANALYSIS REPORT FOR IP STEAM SYSTEM | ANALYSIS REPORT |  | Intermediate Pressure STEAM SYSTEM |  |  | ANALYSIS REPORT for Intermediate Pressure STEAM SYSTEM |  | FA | 1PF2510W58A08P | (Steam PIPING) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-10-01 | 2008-05-01 | 2025-01-21 | 2025-02-20 | 2025-03-22 | 2025-04-06 | 2025-04-21 | 2025-05-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-BP00-P0LBS-140013 | STRESS ANALYSIS REPORT FOR PROCESS STEAM SYSTEM | ANALYSIS REPORT |  | PROCESS STEAM SYSTEM |  |  | ANALYSIS REPORT for PROCESS STEAM SYSTEM |  | FA | 1PF2510W58A08P | (Steam PIPING) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-10-01 | 2008-05-01 | 2025-01-21 | 2025-02-20 | 2025-03-22 | 2025-04-06 | 2025-04-21 | 2025-05-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-BP00-P0LAB-140014 | STRESS ANALYSIS REPORT FOR FEED WATER SYSTEM | ANALYSIS REPORT |  | FEED WATER SYSTEM |  |  | ANALYSIS REPORT for FEED WATER SYSTEM | Boiler Feed Pump | FI | 1PF3015W42A06P | (FWP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-08-30 | 2008-08-29 | 2024-12-20 | 2025-01-19 | 2025-02-18 | 2025-03-05 | 2025-03-20 | 2025-04-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-BP00-P0EKG-140015 | STRESS ANALYSIS REPORT FOR FUEL SYSTEM | ANALYSIS REPORT |  | FUEL SYSTEM |  |  | ANALYSIS REPORT for FUEL SYSTEM |  | FA | 0PF3520W42A04.3P | (FOFP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > Fuel Oil Forward Station | 2007-07-02 | 2008-03-28 | 2024-10-22 | 2024-11-21 | 2024-12-21 | 2025-01-05 | 2025-01-20 | 2025-02-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-BP00-P0LBG-140016 | STRESS ANALYSIS REPORT FOR LP STEAM SYSTEM | ANALYSIS REPORT |  | Low Pressure STEAM SYSTEM |  |  | ANALYSIS REPORT for Low Pressure STEAM SYSTEM |  | FA | 1PF3520W42A14P | (GPRS) P.O & Procurement for HRSG | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-07-03 | 2008-04-30 | 2024-10-23 | 2024-11-22 | 2024-12-22 | 2025-01-06 | 2025-01-21 | 2025-02-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-BP00-P0LCA-140017 | STRESS ANALYSIS REPORT FOR CONDENSATE SYSTEM | ANALYSIS REPORT |  | CONDENSATE SYSTEM |  |  | ANALYSIS REPORT for CONDENSATE SYSTEM |  | FA | 0PF3520W68A04P | (Condensate Tank) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-09-21 | 2024-10-21 | 2024-11-20 | 2024-12-05 | 2024-12-20 | 2025-01-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ZEN-140020 | KEY PLAN DRAWING | PLAN DRAWING |  |  |  |  | PLAN DRAWING |  | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | 2024-11-09 | 2024-12-09 | 2025-01-08 | 2025-01-23 | 2025-02-07 | 2025-02-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P6UMA-140021 | PIPING ARRANGEMENT DRAWING FOR ST BLDG #1 GROUND FLOOR | ARRANGEMENT DRAWING |  | PIPING | Steam Turbine Building #1 GROUND FLOOR |  | General Arrangement Drawing for PIPING |  | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P6UMA-140022 | PIPING ARRANGEMENT DRAWING FOR ST BLDG #1 OPERATING FLOOR | ARRANGEMENT DRAWING |  | PIPING | Steam Turbine Building #1 OPERATING FLOOR |  | General Arrangement Drawing for PIPING |  | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P7UMA-140023 | PIPING ARRANGEMENT DRAWING FOR ST BLDG #2 GROUND FLOOR | ARRANGEMENT DRAWING |  | Piping | Steam Turbine Building #2 |  | General Arrangement Drawing for Piping |  | FA | 2EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-03-30 |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P7UMA-140024 | PIPING ARRANGEMENT DRAWING FOR ST BLDG #2 OPERATING FLOOR | ARRANGEMENT DRAWING |  | Piping | Steam Turbine Building #2 |  | General Arrangement Drawing for Piping |  | FA | 2EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-03-30 |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P6UMA-140025 | PIPING ARRANGEMENT DRAWING FOR AIR COOLED CONDENSER #1 AREA | ARRANGEMENT DRAWING | AIR COOLED CONDENSER #1 | Piping |  |  | General Arrangement Drawing for AIR COOLED CONDENSER #1 |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2024-11-14 | 2024-12-14 | 2025-01-13 | 2025-01-28 | 2025-02-12 | 2025-02-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P7UMA-140026 | PIPING ARRANGEMENT DRAWING FOR AIR COOLED CONDENSER #2 & H2 CO2 N2 STORAGE SHELTER AREA | ARRANGEMENT DRAWING | AIR COOLED CONDENSER #2 | Piping | H2 CO2 N2 STORAGE SHELTER |  | General Arrangement Drawing for AIR COOLED CONDENSER #2 |  | FA | 2PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-09-11 | 2024-11-14 | 2024-12-14 | 2025-01-13 | 2025-01-28 | 2025-02-12 | 2025-02-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULY-140027 | PIPING ARRANGEMENT DRAWING FOR ST BLDG PIPE RACK AREA | ARRANGEMENT DRAWING |  | Piping | ST BLDG PIPE RACK |  | General Arrangement Drawing for Piping |  | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULY-140028 | PIPING ARRANGEMENT DRAWING FOR TO ST BLDG #1 MAIN PIPE RACK AREA | ARRANGEMENT DRAWING |  | Piping | ST BLDG #1 MAIN PIPE RACK |  | General Arrangement Drawing for Piping |  | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULY-140029 | PIPING ARRANGEMENT DRAWING FOR TO ST BLDG #2 MAIN PIPE RACK AREA | ARRANGEMENT DRAWING |  | Piping | ST BLDG #2 MAIN PIPE RACK |  | General Arrangement Drawing for Piping |  | FA | 2EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-03-30 |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULY-140030 | PIPING ARRANGEMENT DRAWING FOR TO MAIN FCP GATE HOUSE AREA | ARRANGEMENT DRAWING |  | Piping | GATE HOUSE |  | General Arrangement Drawing for Piping |  | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ZEN-140031 | PIPING ARRANGEMENT DRAWING FOR TO ESF AREA | ARRANGEMENT DRAWING |  | Piping |  |  | General Arrangement Drawing for Piping |  | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P1UHA-140032 | PIPING ARRANGEMENT DRAWING FOR HRSG #1 AREA EL +0 | ARRANGEMENT DRAWING | Heat Recovery Steam Generator #1 | Piping |  |  | General Arrangement Drawing for Heat Recovery Steam Generator #1 |  | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | 2024-06-14 | 2024-07-14 | 2024-08-13 | 2024-08-28 | 2024-09-12 | 2024-09-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P1UHA-140034 | PIPING ARRANGEMENT DRAWING FOR HRSG #1 AREA EL +106,000 | ARRANGEMENT DRAWING | Heat Recovery Steam Generator #1 | Piping |  |  | General Arrangement Drawing for Heat Recovery Steam Generator #1 |  | FA | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P1UHA-140036 | PIPING ARRANGEMENT DRAWING FOR HRSG #1 AREA EL +108,000 & ABOVE | ARRANGEMENT DRAWING | Heat Recovery Steam Generator #1 | Piping |  |  | General Arrangement Drawing for Heat Recovery Steam Generator #1 |  | FA | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P2UHA-140037 | PIPING ARRANGEMENT DRAWING FOR HRSG #2 AREA EL +0 | ARRANGEMENT DRAWING | Heat Recovery Steam Generator #2 | Piping |  |  | General Arrangement Drawing for Heat Recovery Steam Generator #2 |  | FA | 2EF1600W00A01.0 | (HRSG #21/#22) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | 2007-04-18 | 2008-04-04 | 2024-07-14 | 2024-08-13 | 2024-09-12 | 2024-09-27 | 2024-10-12 | 2024-10-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P2UHA-140038 | PIPING ARRANGEMENT DRAWING FOR HRSG #2 AREA EL +106,000 | ARRANGEMENT DRAWING | Heat Recovery Steam Generator #2 | Piping |  |  | General Arrangement Drawing for Heat Recovery Steam Generator #2 |  | FA | 2EF1625W00A02.2 | (HRSG #22 Main Stack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Main Stack | 2007-07-05 |  | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P2UHA-140039 | PIPING ARRANGEMENT DRAWING FOR HRSG #2 AREA EL +108,000 & ABOVE | ARRANGEMENT DRAWING | Heat Recovery Steam Generator #2 | Piping |  |  | General Arrangement Drawing for Heat Recovery Steam Generator #2 |  | FA | 2EF1625W00A02.2 | (HRSG #22 Main Stack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Main Stack | 2007-07-05 |  | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P3UHA-140040 | PIPING ARRANGEMENT DRAWING FOR HRSG #3 AREA EL +0 | ARRANGEMENT DRAWING | Heat Recovery Steam Generator #3 | Piping |  |  | General Arrangement Drawing for Heat Recovery Steam Generator #3 |  | FA | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-05-18 | 2008-05-06 | 2024-08-13 | 2024-09-12 | 2024-10-12 | 2024-10-27 | 2024-11-11 | 2024-11-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P3UHA-140041 | PIPING ARRANGEMENT DRAWING FOR HRSG #3 AREA EL +106,000 | ARRANGEMENT DRAWING | Heat Recovery Steam Generator #3 | Piping |  |  | General Arrangement Drawing for Heat Recovery Steam Generator #3 |  | FA | 3EF1600W00A02 | (HRSG #31/#32) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P3UHA-140042 | PIPING ARRANGEMENT DRAWING FOR HRSG #3 AREA EL +108,000 & ABOVE | ARRANGEMENT DRAWING | Heat Recovery Steam Generator #3 | Piping |  |  | General Arrangement Drawing for Heat Recovery Steam Generator #3 |  | FA | 3EF1600W00A02 | (HRSG #31/#32) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P4UHA-140043 | PIPING ARRANGEMENT DRAWING FOR HRSG #4 AREA EL +0 | ARRANGEMENT DRAWING | Heat Recovery Steam Generator #4 | Piping |  |  | General Arrangement Drawing for Heat Recovery Steam Generator #4 |  | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | 2024-06-14 | 2024-07-14 | 2024-08-13 | 2024-08-28 | 2024-09-12 | 2024-09-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P4UHA-140044 | PIPING ARRANGEMENT DRAWING FOR HRSG #4 AREA EL +106,000 | ARRANGEMENT DRAWING | Heat Recovery Steam Generator #4 | Piping |  |  | General Arrangement Drawing for Heat Recovery Steam Generator #4 |  | FA | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P4UHA-140045 | PIPING ARRANGEMENT DRAWING FOR HRSG #4 AREA EL +108,000 & ABOVE | ARRANGEMENT DRAWING | Heat Recovery Steam Generator #4 | Piping |  |  | General Arrangement Drawing for Heat Recovery Steam Generator #4 |  | FA | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P5UHA-140046 | PIPING ARRANGEMENT DRAWING FOR HRSG #5 AREA EL +0 | ARRANGEMENT DRAWING | Heat Recovery Steam Generator #5 | Piping |  |  | General Arrangement Drawing for Heat Recovery Steam Generator #5 |  | FA | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-19 | 2008-03-05 | 2024-06-14 | 2024-07-14 | 2024-08-13 | 2024-08-28 | 2024-09-12 | 2024-09-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P5UHA-140047 | PIPING ARRANGEMENT DRAWING FOR HRSG #5 AREA EL +106,000 | ARRANGEMENT DRAWING | Heat Recovery Steam Generator #5 | Piping |  |  | General Arrangement Drawing for Heat Recovery Steam Generator #5 |  | FA | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P5UHA-140048 | PIPING ARRANGEMENT DRAWING FOR HRSG #5 AREA EL +108,000 & ABOVE | ARRANGEMENT DRAWING | Heat Recovery Steam Generator #5 | Piping |  |  | General Arrangement Drawing for Heat Recovery Steam Generator #5 |  | FA | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P1MBA-140049 | PIPING ARRANGEMENT DRAWING FOR GT #1 AREA | ARRANGEMENT DRAWING | GT #1 | Piping |  |  | General Arrangement Drawing for GT #1 |  | FA | 1CF3520W58A01 | (Gas Supply System) Piping Work(Yard area) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Gas Supply System (GTG) | 2008-05-20 | 2008-07-19 | 2025-07-02 | 2025-08-01 | 2025-08-31 | 2025-09-15 | 2025-09-30 | 2025-10-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P2MBA-140050 | PIPING ARRANGEMENT DRAWING FOR GT #2 AREA | ARRANGEMENT DRAWING | GT #2 | Piping |  |  | General Arrangement Drawing for GT #2 |  | FA | 2CF3520W58A01 | (Gas Supply System) Piping Work(Yard area) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Gas Supply System (GTG) | 2008-06-19 | 2008-08-19 | 2025-08-01 | 2025-08-31 | 2025-09-30 | 2025-10-15 | 2025-10-30 | 2025-11-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P3MBA-140051 | PIPING ARRANGEMENT DRAWING FOR GT #3 AREA | ARRANGEMENT DRAWING | GT #3 | Piping |  |  | General Arrangement Drawing for GT #3 |  | FA | 3CF3520W58A01 | (Gas Supply System) Piping Work(Yard area) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Gas Supply System (GTG) | 2008-07-19 | 2008-09-18 | 2025-08-31 | 2025-09-30 | 2025-10-30 | 2025-11-14 | 2025-11-29 | 2025-12-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P4MBA-140052 | PIPING ARRANGEMENT DRAWING FOR GT #4 AREA | ARRANGEMENT DRAWING | GT #4 | Piping |  |  | General Arrangement Drawing for GT #4 |  | FA | 1CF1265W58A06.4 | (FGSS) Piping Work(incl. Airblowing Test)_Power Block Area | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Gas Supply System | 2008-05-20 | 2008-06-19 | 2025-07-02 | 2025-08-01 | 2025-08-31 | 2025-09-15 | 2025-09-30 | 2025-10-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P5MBA-140053 | PIPING ARRANGEMENT DRAWING FOR GT #5 AREA | ARRANGEMENT DRAWING | GT #5 | Piping |  |  | General Arrangement Drawing for GT #5 |  | FA | 1CF3520W58A01 | (Gas Supply System) Piping Work(Yard area) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Gas Supply System (GTG) | 2008-05-20 | 2008-07-19 | 2025-07-02 | 2025-08-01 | 2025-08-31 | 2025-09-15 | 2025-09-30 | 2025-10-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULA-140054 | PIPING ARRANGEMENT DRAWING FOR BFP SHELTER AREA EL. +0 | ARRANGEMENT DRAWING | BFP | Piping |  |  | General Arrangement Drawing for BFP |  | FA | 0EF4500W00A01.0 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 |  | 2024-06-12 | 2024-07-12 | 2024-08-11 | 2024-08-26 | 2024-09-10 | 2024-09-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULA-140055 | PIPING ARRANGEMENT DRAWING FOR BFP SHELTER AREA EL. +111,500 | ARRANGEMENT DRAWING | BFP | Piping |  |  | General Arrangement Drawing for BFP |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-06-29 | 2024-07-29 | 2024-08-28 | 2024-09-12 | 2024-09-27 | 2024-10-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULA-140056 | PIPING ARRANGEMENT DRAWING FOR BFP SHELTER AREA EL. +114,500 | ARRANGEMENT DRAWING | BFP | Piping |  |  | General Arrangement Drawing for BFP |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-06-29 | 2024-07-29 | 2024-08-28 | 2024-09-12 | 2024-09-27 | 2024-10-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULA-140057 | PIPING ARRANGEMENT DRAWING FOR DEAERATOR AREA | ARRANGEMENT DRAWING |  | Piping |  |  | General Arrangement Drawing for Piping |  | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULY-140058 | PIPING ARRANGEMENT DRAWING FOR MAIN PIPE RACK AREA 1 | ARRANGEMENT DRAWING |  | Piping | MAIN PIPE RACK |  | General Arrangement Drawing for Piping |  | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULY-140059 | PIPING ARRANGEMENT DRAWING FOR MAIN PIPE RACK AREA 2 | ARRANGEMENT DRAWING |  | Piping | MAIN PIPE RACK |  | General Arrangement Drawing for Piping |  | FA | 2EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-03-30 |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULY-140060 | PIPING ARRANGEMENT DRAWING FOR MAIN PIPE RACK AREA 3 | ARRANGEMENT DRAWING |  | Piping | MAIN PIPE RACK |  | General Arrangement Drawing for Piping |  | FA | 3EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-03-30 |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ULY-140061 | PIPING ARRANGEMENT DRAWING FOR MAIN PIPE RACK AREA 4 | ARRANGEMENT DRAWING |  | Piping | MAIN PIPE RACK |  | General Arrangement Drawing for Piping |  | FA | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-30 |  | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ZEN-140062 | PIPING ARRANGEMENT DRAWING FOR CCW FIN FAN COOLER AREA | ARRANGEMENT DRAWING | Fin Fan Cooler | Piping |  |  | General Arrangement Drawing for Fin Fan Cooler |  | FA | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2008-04-30 | 2024-08-14 | 2024-09-13 | 2024-10-13 | 2024-10-28 | 2024-11-12 | 2024-11-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UTF-140063 | PIPING ARRANGEMENT DRAWING FOR AIR COMPRESSOR AREA | ARRANGEMENT DRAWING | Air Compressor | Piping |  |  | General Arrangement Drawing for Air Compressor |  | FA | 0EF3510W00A17 | (COMP Air BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 |  | 2024-09-12 | 2024-10-12 | 2024-11-11 | 2024-11-26 | 2024-12-11 | 2024-12-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0GRK-140064 | PIPING ARRANGEMENT DRAWING FOR WATER TREATMENT BLDG AREA | ARRANGEMENT DRAWING | Water Treatment Plant | Piping |  |  | General Arrangement Drawing for Water Treatment Plant | Water Treatment System | FA | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UGD-140065 | PIPING ARRANGEMENT DRAWING FOR DEMI & POTABLE WATER TANK AREA | PIPING ARRANGEMENT DRAWING | Tank | Piping |  |  | PIPING ARRANGEMENT DRAWING for Tank |  | FA | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  | 2024-11-23 | 2024-12-23 | 2025-01-22 | 2025-02-06 | 2025-02-21 | 2025-03-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UGA-140066 | PIPING ARRANGEMENT DRAWING FOR POTABLE & FIRE WATER TANK A/B AREA | PIPING ARRANGEMENT DRAWING | Tank | Piping |  |  | PIPING ARRANGEMENT DRAWING for Tank |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UGA-140067 | PIPING ARRANGEMENT DRAWING FOR POTABLE & FIRE WATER TANK C AREA | PIPING ARRANGEMENT DRAWING | Tank | Piping |  |  | PIPING ARRANGEMENT DRAWING for Tank |  | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | 2024-06-07 | 2024-07-07 | 2024-08-06 | 2024-08-21 | 2024-09-05 | 2024-09-20 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UCB-140068 | PIPING ARRANGEMENT DRAWING FOR CCB AREA | PIPING ARRANGEMENT DRAWING |  | Piping | CCB |  | PIPING ARRANGEMENT DRAWING for Piping |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LCA-140069 | PIPING ARRANGEMENT DRAWING FOR CONDENSATE TANK C AREA | PIPING ARRANGEMENT DRAWING | Tank | Piping |  |  | PIPING ARRANGEMENT DRAWING for Tank |  | FA | 0PF3520W68A04P | (Condensate Tank) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-08-24 | 2024-09-23 | 2024-10-23 | 2024-11-07 | 2024-11-22 | 2024-12-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LCA-140070 | PIPING ARRANGEMENT DRAWING FOR CONDENSATE TANK A/B AREA | PIPING ARRANGEMENT DRAWING | Tank | Piping |  |  | PIPING ARRANGEMENT DRAWING for Tank |  | FA | 0PF3520W68A04P | (Condensate Tank) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-08-24 | 2024-09-23 | 2024-10-23 | 2024-11-07 | 2024-11-22 | 2024-12-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LDK-140071 | PIPING ARRANGEMENT DRAWING FOR CPP BLDG AREA 1 | PIPING ARRANGEMENT DRAWING |  | Piping | CPP BLDG |  | PIPING ARRANGEMENT DRAWING for Piping |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LDK-140072 | PIPING ARRANGEMENT DRAWING FOR CPP BLDG AREA 2 | PIPING ARRANGEMENT DRAWING |  | Piping | CPP BLDG |  | PIPING ARRANGEMENT DRAWING for Piping |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0EKG-140073 | PIPING ARRANGEMENT DRAWING FOR GPRS AREA | PIPING ARRANGEMENT DRAWING |  | Piping |  |  | PIPING ARRANGEMENT DRAWING for Piping |  | FA | 1CF3520W58A01 | (Gas Supply System) Piping Work(Yard area) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Gas Supply System (GTG) | 2008-05-20 | 2008-07-19 | 2025-08-13 | 2025-09-12 | 2025-10-12 | 2025-10-27 | 2025-11-11 | 2025-11-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UYE-140074 | PIPING ARRANGEMENT DRAWING FOR MAIN GATE HOUSE AREA | PIPING ARRANGEMENT DRAWING |  | Piping | Gate House |  | PIPING ARRANGEMENT DRAWING for Piping |  | FA | 1CF3520W58A01 | (Gas Supply System) Piping Work(Yard area) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Gas Supply System (GTG) | 2008-05-20 | 2008-07-19 | 2025-08-13 | 2025-09-12 | 2025-10-12 | 2025-10-27 | 2025-11-11 | 2025-11-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UYF-140075 | PIPING ARRANGEMENT DRAWING FOR SECURITY BUILDING AREA | PIPING ARRANGEMENT DRAWING |  | Piping | Security |  | PIPING ARRANGEMENT DRAWING for Piping |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UYC-140076 | PIPING ARRANGEMENT DRAWING FOR MAIN ADMIN BUILDING AREA | PIPING ARRANGEMENT DRAWING |  | Piping | Administration Building |  | PIPING ARRANGEMENT DRAWING for Piping |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UST-140077 | PIPING ARRANGEMENT DRAWING FOR MAINTENANCE & WORKSHOP BUILDING AREA | PIPING ARRANGEMENT DRAWING |  | Piping | Workshop Building |  | PIPING ARRANGEMENT DRAWING for Piping |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0UYP-140078 | PIPING ARRANGEMENT DRAWING FOR FIRE BRIGATE AREA | PIPING ARRANGEMENT DRAWING |  | Piping | fire brigade Building |  | PIPING ARRANGEMENT DRAWING for Piping |  | FA | 0PF4500W38A09P | (Fire Fighting System) P.O & Procurement_piping | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-08-01 | 2007-12-31 | 2024-10-24 | 2024-11-23 | 2024-12-23 | 2025-01-07 | 2025-01-22 | 2025-02-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P7UBA-140079 | PIPING ARRANGEMENT DRAWING FOR STG ELECTRICAL BUILDING #2 AREA | PIPING ARRANGEMENT DRAWING | Steam Turbine & Generator | Piping | Electrical Building |  | PIPING ARRANGEMENT DRAWING for STG |  | FA | 2PF2010W20A04P | (STG #20 BLDG) P.O & Procurement - Structure Work(S/S) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-09-19 | 2008-01-31 | 2024-12-12 | 2025-01-11 | 2025-02-10 | 2025-02-25 | 2025-03-12 | 2025-03-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P6UBA-140080 | PIPING ARRANGEMENT DRAWING FOR STG ELECTRICAL BUILDING #1 & SWAS CONTAINER AREA | PIPING ARRANGEMENT DRAWING | Steam Turbine & Generator | Piping | Electrical Building |  | PIPING ARRANGEMENT DRAWING for STG |  | FA | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 |  | 2024-05-24 | 2024-06-23 | 2024-07-23 | 2024-08-07 | 2024-08-22 | 2024-09-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ZEN-140081 | PIPING ARRANGEMENT DRAWING FOR FGP TP AREA | PIPING ARRANGEMENT DRAWING | Fuel Gas Package | Piping |  |  | PIPING ARRANGEMENT DRAWING for FGP |  | FA | 1CF3520W58A01 | (Gas Supply System) Piping Work(Yard area) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Gas Supply System (GTG) | 2008-05-20 | 2008-07-19 | 2025-08-13 | 2025-09-12 | 2025-10-12 | 2025-10-27 | 2025-11-11 | 2025-11-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ZEN-140082 | PIPING ARRANGEMENT DRAWING FOR YARD AREA TO FGP TP | PIPING ARRANGEMENT DRAWING | Fuel Gas Package | Piping |  |  | PIPING ARRANGEMENT DRAWING for FGP |  | FA | 1CF3520W58A01 | (Gas Supply System) Piping Work(Yard area) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Gas Supply System (GTG) | 2008-05-20 | 2008-07-19 | 2025-08-13 | 2025-09-12 | 2025-10-12 | 2025-10-27 | 2025-11-11 | 2025-11-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0ZEN-140083 | PIPING ARRANGEMENT DRAWING FOR CONDENSATE TANK A & YARD AREA | PIPING ARRANGEMENT DRAWING | Tank | Piping |  |  | PIPING ARRANGEMENT DRAWING for Tank |  | FA | 1CF3520W58A01 | (Gas Supply System) Piping Work(Yard area) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Gas Supply System (GTG) | 2008-05-20 | 2008-07-19 | 2025-08-13 | 2025-09-12 | 2025-10-12 | 2025-10-27 | 2025-11-11 | 2025-11-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0ZEN-140100 | FABRICATION STANDARD DRAWING | DRAWING |  |  |  |  | DRAWING |  | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | 2024-10-26 | 2024-11-25 | 2024-12-25 | 2025-01-09 | 2025-01-24 | 2025-02-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LBA-140101 | FABRICATION ISOMETRIC DRAWING FOR HP STEAM SYSTEM | ISOMETRIC DRAWING |  | HP STEAM SYSTEM |  |  | Isometric Drawing for HP STEAM SYSTEM | Water Treatment System | FI | 1PF2510W58A08P | (Steam PIPING) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-10-01 | 2008-05-01 | 2025-02-28 | 2025-03-30 | 2025-04-29 | 2025-05-14 | 2025-05-29 | 2025-06-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LBC-140102 | FABRICATION ISOMETRIC DRAWING FOR IP STEAM SYSTEM | ISOMETRIC DRAWING |  | IP STEAM SYSTEM |  |  | Isometric Drawing for IP STEAM SYSTEM | Water Treatment System | FI | 1PF2510W58A08P | (Steam PIPING) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-10-01 | 2008-05-01 | 2025-02-28 | 2025-03-30 | 2025-04-29 | 2025-05-14 | 2025-05-29 | 2025-06-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LBG-140103 | FABRICATION ISOMETRIC DRAWING FOR LP STEAM SYSTEM | ISOMETRIC DRAWING |  | LP STEAM SYSTEM |  |  | Isometric Drawing for LP STEAM SYSTEM | Water Treatment System | FI | 1PF2510W58A08P | (Steam PIPING) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-10-01 | 2008-05-01 | 2025-02-28 | 2025-03-30 | 2025-04-29 | 2025-05-14 | 2025-05-29 | 2025-06-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LBG-140104 | FABRICATION ISOMETRIC DRAWING FOR PROCESS STEAM SYSTEM | ISOMETRIC DRAWING |  | PROCESS STEAM SYSTEM |  |  | Isometric Drawing for PROCESS STEAM SYSTEM | Water Treatment System | FI | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-15 | 2024-11-14 | 2024-12-14 | 2024-12-29 | 2025-01-13 | 2025-01-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LCM-140105 | FABRICATION ISOMETRIC DRAWING FOR STEAM DRAIN SYSTEM | ISOMETRIC DRAWING |  | STEAM DRAIN SYSTEM |  |  | Isometric Drawing for STEAM DRAIN SYSTEM | Water Treatment System | FI | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-15 | 2024-11-14 | 2024-12-14 | 2024-12-29 | 2025-01-13 | 2025-01-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LCA-140106 | FABRICATION ISOMETRIC DRAWING FOR CONDENSATE SYSTEM | ISOMETRIC DRAWING |  | CONDENSATE SYSTEM |  |  | Isometric Drawing for CONDENSATE SYSTEM | Water Treatment System | FI | 0PF3520W68A04P | (Condensate Tank) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LAB-140108 | FABRICATION ISOMETRIC DRAWING FOR FEED WATER SYSTEM | ISOMETRIC DRAWING |  | FEED WATER SYSTEM |  |  | Isometric Drawing for FEED WATER SYSTEM | Water Treatment System | FI | 1PF3015W42A06P | (FWP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-08-30 | 2008-08-29 | 2025-01-27 | 2025-02-26 | 2025-03-28 | 2025-04-12 | 2025-04-27 | 2025-05-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0PGB-140109 | FABRICATION ISOMETRIC DRAWING FOR CLOSED COOLING WATER SYSTEM | ISOMETRIC DRAWING |  | CLOSED COOLING WATER SYSTEM |  |  | Isometric Drawing for CLOSED COOLING WATER SYSTEM | Water Treatment System | FI | 1PF3030W42A14P | (CCW H/EX) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-09-03 | 2008-07-16 | 2025-01-31 | 2025-03-02 | 2025-04-01 | 2025-04-16 | 2025-05-01 | 2025-05-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0SCA-140110 | FABRICATION ISOMETRIC DRAWING FOR SERVICE AIR SYSTEM | ISOMETRIC DRAWING |  | SERVICE AIR SYSTEM |  |  | Isometric Drawing for SERVICE AIR SYSTEM | Water Treatment System | FI | 0EF3035W00A01.0 | (SWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2007-03-15 | 2007-11-21 | 2024-08-12 | 2024-09-11 | 2024-10-11 | 2024-10-26 | 2024-11-10 | 2024-11-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0GKB-140112 | FABRICATION ISOMETRIC DRAWING FOR POTABLE WATER SYSTEM | ISOMETRIC DRAWING |  | POTABLE WATER SYSTEM |  |  | Isometric Drawing for POTABLE WATER SYSTEM | Water Treatment System | FI | 0PF3035W42A06P | (PWP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-09-03 | 2008-09-01 | 2025-01-31 | 2025-03-02 | 2025-04-01 | 2025-04-16 | 2025-05-01 | 2025-05-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0GHC-140113 | FABRICATION ISOMETRIC DRAWING FOR DEMI WATER SYSTEM | ISOMETRIC DRAWING |  | DEMI WATER SYSTEM |  |  | Isometric Drawing for DEMI WATER SYSTEM | Water Treatment System | FI | 0EF3010W00A01.0 | (Make-up WTR Supply System) Demi WTR Supply pump Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-01 | 2007-05-01 | 2024-07-29 | 2024-08-28 | 2024-09-27 | 2024-10-12 | 2024-10-27 | 2024-11-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0PDA-140114 | FABRICATION ISOMETRIC DRAWING FOR TREATED EFFLUENT COLLECTION AND TRANSFER SYSTEM | ISOMETRIC DRAWING |  | TREATED EFFLUENT COLLECTION AND TRANSFER SYSTEM |  |  | Isometric Drawing for TREATED EFFLUENT COLLECTION AND TRANSFER SYSTEM | Water Treatment System | FI | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-15 | 2024-11-14 | 2024-12-14 | 2024-12-29 | 2025-01-13 | 2025-01-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0MBH-140116 | FABRICATION ISOMETRIC DRAWING FOR GT ROTOR COOLING AIR COOLING SYSTEM | ISOMETRIC DRAWING |  | GT ROTOR COOLING AIR COOLING SYSTEM |  |  | Isometric Drawing for GT ROTOR COOLING AIR COOLING SYSTEM | Water Treatment System | FI | 3PF1225W42A12P | (CCWP) P.O & Procurement for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | 2007-07-03 | 2008-05-30 | 2024-11-30 | 2024-12-30 | 2025-01-29 | 2025-02-13 | 2025-02-28 | 2025-03-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0EKC-140117 | FABRICATION ISOMETRIC DRAWING FOR GT PERFORMANCE HEATER SYSTEM | ISOMETRIC DRAWING |  | GT PERFORMANCE HEATER SYSTEM |  |  | Isometric Drawing for GT PERFORMANCE HEATER SYSTEM | Water Treatment System | FI | 1PF3520W42A07.2P | (Gas HTR) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Heater | 2007-07-03 | 2008-04-01 | 2024-11-30 | 2024-12-30 | 2025-01-29 | 2025-02-13 | 2025-02-28 | 2025-03-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0EKG-140118 | FABRICATION ISOMETRIC DRAWING FOR FUEL GAS SYSTEM | ISOMETRIC DRAWING |  | Fuel Gas System |  |  | Isometric Drawing for Fuel Gas System | Fuel Gas System | FA | 1PF3520W42A04P | (GPRS) P.O & Procurement for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-06-01 | 2008-03-31 | 2024-09-21 | 2024-11-16 | 2025-01-11 | 2024-12-07 | 2025-02-01 | 2025-03-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0ZEN-140119 | FABRICATION ISOMETRIC DRAWING FOR TG MISCELLANEOUS SYSTEM | ISOMETRIC DRAWING |  | TG MISCELLANEOUS SYSTEM |  |  | Isometric Drawing for TG MISCELLANEOUS SYSTEM | Water Treatment System | FI | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-15 | 2024-11-14 | 2024-12-14 | 2024-12-29 | 2025-01-13 | 2025-01-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0ZEN-140120 | ISOMETRIC DRAWING FOR TG MISCELLANEOUS SMALL BORE SYSTEM | ISOMETRIC DRAWING |  | TG MISCELLANEOUS SMALL BORE SYSTEM |  |  | Isometric Drawing for TG MISCELLANEOUS SMALL BORE SYSTEM | Water Treatment System | FI | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-15 | 2024-11-14 | 2024-12-14 | 2024-12-29 | 2025-01-13 | 2025-01-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0GM-140121 | FABRICATION ISOMETRIC DRAWING FOR WASTE WATER SYSTEM | ISOMETRIC DRAWING |  | WASTE WATER SYSTEM |  |  | Isometric Drawing for WASTE WATER SYSTEM | Water Treatment System | FI | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-09-01 | 2025-01-31 | 2025-03-02 | 2025-04-01 | 2025-04-16 | 2025-05-01 | 2025-05-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LBA-140201 | ISOMETRIC DRAWING FOR HP STEAM SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | HP STEAM SYSTEM |  |  | Isometric Drawing for HP STEAM SYSTEM | Water Treatment System | FI | 1PF2510W58A08P | (Steam PIPING) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-10-01 | 2008-05-01 | 2025-02-28 | 2025-03-30 | 2025-04-29 | 2025-05-14 | 2025-05-29 | 2025-06-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LBC-140202 | ISOMETRIC DRAWING FOR IP STEAM SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | IP STEAM SYSTEM |  |  | Isometric Drawing for IP STEAM SYSTEM | Water Treatment System | FI | 1PF2510W58A08P | (Steam PIPING) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-10-01 | 2008-05-01 | 2025-02-28 | 2025-03-30 | 2025-04-29 | 2025-05-14 | 2025-05-29 | 2025-06-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LBG-140203 | ISOMETRIC DRAWING FOR LP STEAM SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | LP STEAM SYSTEM |  |  | Isometric Drawing for LP STEAM SYSTEM | Water Treatment System | FI | 1PF2510W58A08P | (Steam PIPING) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-10-01 | 2008-05-01 | 2025-02-28 | 2025-03-30 | 2025-04-29 | 2025-05-14 | 2025-05-29 | 2025-06-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LBG-140204 | ISOMETRIC DRAWING FOR PROCESS STEAM SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | PROCESS STEAM SYSTEM |  |  | Isometric Drawing for PROCESS STEAM SYSTEM | Water Treatment System | FI | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-15 | 2024-11-14 | 2024-12-14 | 2024-12-29 | 2025-01-13 | 2025-01-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LCM-140205 | ISOMETRIC DRAWING FOR STEAM DRAIN SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | STEAM DRAIN SYSTEM |  |  | Isometric Drawing for STEAM DRAIN SYSTEM | Water Treatment System | FI | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-15 | 2024-11-14 | 2024-12-14 | 2024-12-29 | 2025-01-13 | 2025-01-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LCA-140206 | ISOMETRIC DRAWING FOR CONDENSATE SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | CONDENSATE SYSTEM |  |  | Isometric Drawing for CONDENSATE SYSTEM | Water Treatment System | FI | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-15 | 2024-11-14 | 2024-12-14 | 2024-12-29 | 2025-01-13 | 2025-01-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0LAB-140208 | ISOMETRIC DRAWING FOR FEED WATER SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | FEED WATER SYSTEM |  |  | Isometric Drawing for FEED WATER SYSTEM | Water Treatment System | FI | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-15 | 2024-11-14 | 2024-12-14 | 2024-12-29 | 2025-01-13 | 2025-01-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0PGB-140209 | ISOMETRIC DRAWING FOR CLOSED COOLING WATER SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | CLOSED COOLING WATER SYSTEM |  |  | Isometric Drawing for CLOSED COOLING WATER SYSTEM | Water Treatment System | FI | 1PF3030W42A14P | (CCW H/EX) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-09-03 | 2008-07-16 | 2025-01-31 | 2025-03-02 | 2025-04-01 | 2025-04-16 | 2025-05-01 | 2025-05-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0SCA-140210 | ISOMETRIC DRAWING FOR SERVICE AIR SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | SERVICE AIR SYSTEM |  |  | Isometric Drawing for SERVICE AIR SYSTEM | Water Treatment System | FI | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-15 | 2024-11-14 | 2024-12-14 | 2024-12-29 | 2025-01-13 | 2025-01-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0QFB-140211 | ISOMETRIC DRAWING FOR INSTRUMENT AIR SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | INSTRUMENT AIR SYSTEM |  |  | Isometric Drawing for INSTRUMENT AIR SYSTEM |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0GKB-140212 | ISOMETRIC DRAWING FOR POTABLE WATER SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | POTABLE WATER SYSTEM |  |  | Isometric Drawing for POTABLE WATER SYSTEM | Water Treatment System | FI | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | 2024-08-12 | 2024-09-11 | 2024-10-11 | 2024-10-26 | 2024-11-10 | 2024-11-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0GHC-140213 | ISOMETRIC DRAWING FOR DEMI WATER SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | DEMI WATER SYSTEM |  |  | Isometric Drawing for DEMI WATER SYSTEM | Water Treatment System | FI | 0EF3010W00A01.0 | (Make-up WTR Supply System) Demi WTR Supply pump Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-03-01 | 2007-05-01 | 2024-07-29 | 2024-08-28 | 2024-09-27 | 2024-10-12 | 2024-10-27 | 2024-11-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0GKB-140215 | ISOMETRIC DRAWING FOR UNDERGROUND PIPING SYSTEM | ISOMETRIC DRAWING |  | UNDERGROUND PIPING SYSTEM |  |  | Isometric Drawing for UNDERGROUND PIPING SYSTEM | Water Treatment System | FI | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-10-15 | 2024-11-14 | 2024-12-14 | 2024-12-29 | 2025-01-13 | 2025-01-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0MBH-140216 | ISOMETRIC DRAWING FOR GT ROTOR COOLING AIR COOLING SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | GT ROTOR COOLING AIR COOLING SYSTEM |  |  | Isometric Drawing for GT ROTOR COOLING AIR COOLING SYSTEM | Water Treatment System | FI | 3PF1225W42A12P | (CCWP) P.O & Procurement for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | 2007-07-03 | 2008-05-30 | 2024-11-30 | 2024-12-30 | 2025-01-29 | 2025-02-13 | 2025-02-28 | 2025-03-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0EKC-140217 | ISOMETRIC DRAWING FOR GT PERFORMANCE HEATER SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | GT PERFORMANCE HEATER SYSTEM |  |  | Isometric Drawing for GT PERFORMANCE HEATER SYSTEM | Water Treatment System | FI | 1PF3520W42A07.2P | (Gas HTR) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Heater | 2007-07-03 | 2008-04-01 | 2024-11-30 | 2024-12-30 | 2025-01-29 | 2025-02-13 | 2025-02-28 | 2025-03-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0QUB-140219 | ISOMETRIC DRAWING FOR SAMPLING SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | SAMPLING SYSTEM |  |  | Isometric Drawing for SAMPLING SYSTEM | Water Treatment System | FI | 1EF3040W00A01 | (Sampling System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | 2007-04-02 | 2007-08-31 | 2024-08-30 | 2024-09-29 | 2024-10-29 | 2024-11-13 | 2024-11-28 | 2024-12-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0QCA-140221 | ISOMETRIC DRAWING FOR CHEMICAL DOSING SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | CHEMICAL DOSING SYSTEM |  |  | Isometric Drawing for CHEMICAL DOSING SYSTEM | Water Treatment System | FI | 1PF3045W42A03P | (Chemical Dosing Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-07-24 | 2025-02-23 | 2025-03-25 | 2025-04-24 | 2025-05-09 | 2025-05-24 | 2025-06-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0QJA-140223 | ISOMETRIC DRAWING FOR N2 GAS SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | Nitrogen GAS SYSTEM |  |  | Isometric Drawing for Nitrogen GAS SYSTEM | Water Treatment System | FI | 1PF3515W42A04P | (N2 Gas Equip) P.O & Procurement for FGSS(Local PROC.) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-11-01 | 2008-05-30 | 2025-03-31 | 2025-04-30 | 2025-05-30 | 2025-06-14 | 2025-06-29 | 2025-07-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P0GM-140224 | ISOMETRIC DRAWING FOR WASTE WATER SYSTEM SMALL BORE | ISOMETRIC DRAWING |  | WASTE WATER SYSTEM |  |  | Isometric Drawing for WASTE WATER SYSTEM | Water Treatment System | FI | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-09-01 | 2025-01-31 | 2025-03-02 | 2025-04-01 | 2025-04-16 | 2025-05-01 | 2025-05-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0LF-140301 | MANUAL BUTTERFLY VALVE OUTLINE DRAWINGS | OUTLINE DRAWINGS |  |  |  |  | OUTLINE DRAWINGS |  | FA | 0PF6050W86A02P | (Manual Valve) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Manual Valve | 2007-09-24 | 2008-02-29 | 2024-10-22 | 2024-11-21 | 2024-12-21 | 2025-01-05 | 2025-01-20 | 2025-02-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0LF-140302 | MANUAL LOW PRESSURE CASTING VALVE OUTLINE DRAWINGS | OUTLINE DRAWINGS |  |  |  |  | OUTLINE DRAWINGS |  | FA | 0PF6050W86A02P | (Manual Valve) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Manual Valve | 2007-09-24 | 2008-02-29 | 2024-10-22 | 2024-11-21 | 2024-12-21 | 2025-01-05 | 2025-01-20 | 2025-02-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0LF-140303 | MANUAL HIGH PRESSURE CASTING VALVE OUTLINE DRAWINGS | OUTLINE DRAWINGS |  |  |  |  | OUTLINE DRAWINGS |  | FA | 0PF6050W86A02P | (Manual Valve) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Manual Valve | 2007-09-24 | 2008-02-29 | 2024-10-22 | 2024-11-21 | 2024-12-21 | 2025-01-05 | 2025-01-20 | 2025-02-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0LF-140304 | MANUAL FORGING VALVE OUTLINE DRAWINGS | DRAWINGS | valve |  |  |  | DRAWINGS for valve | CONTROL VALVE | FA | 0PF6050W86A02P | (Manual Valve) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Manual Valve | 2007-09-24 | 2008-02-29 | 2024-10-22 | 2024-11-21 | 2024-12-21 | 2025-01-05 | 2025-01-20 | 2025-02-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140401 | PIPING SUPPORT DETAIL DRAWING FOR HP STEAM SYSTEM | DRAWING |  | Steam System(High Pressure) |  |  | DRAWING for Steam System(High Pressure) | Water Treatment System | FI | 1PF2510W58A08P | (Steam PIPING) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-10-01 | 2008-05-01 | 2025-02-28 | 2025-03-30 | 2025-04-29 | 2025-05-14 | 2025-05-29 | 2025-06-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140402 | PIPING SUPPORT DETAIL DRAWING FOR IP STEAM SYSTEM | DRAWING |  | Intermediate Pressure |  |  | DRAWING for Intermediate Pressure |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-06-15 | 2024-07-15 | 2024-08-14 | 2024-08-29 | 2024-09-13 | 2024-09-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140403 | PIPING SUPPORT DETAIL DRAWING FOR LP STEAM SYSTEM | DRAWING |  | Steam System(Low Pressure) |  |  | DRAWING for Steam System(Low Pressure) | Water Treatment System | FI | 1PF2510W58A08P | (Steam PIPING) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-10-01 | 2008-05-01 | 2025-02-28 | 2025-03-30 | 2025-04-29 | 2025-05-14 | 2025-05-29 | 2025-06-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140404 | PIPING SUPPORT DETAIL DRAWING FOR PROCESS STEAM SYSTEM | DRAWING |  | Steam System |  |  | DRAWING for Steam System | Water Treatment System | FI | 1PF2510W58A08P | (Steam PIPING) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-10-01 | 2008-05-01 | 2025-02-28 | 2025-03-30 | 2025-04-29 | 2025-05-14 | 2025-05-29 | 2025-06-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140405 | PIPING SUPPORT DETAIL DRAWING FOR STEAM DRAIN SYSTEM | DRAWING |  | Drain System |  |  | DRAWING for Drain System | Water Treatment System | FI | 1PF3020W42A12.1P | (Clean Drain Tank) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | 2007-10-01 | 2008-09-01 | 2025-02-28 | 2025-03-30 | 2025-04-29 | 2025-05-14 | 2025-05-29 | 2025-06-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140406 | PIPING SUPPORT DETAIL DRAWING FOR CONDENSATE SYSTEM | DRAWING |  | Condensate System |  |  | DRAWING for Condensate System | Water Treatment System | FI | 0PF3520W42A08P | (Condensate Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140407 | PIPING SUPPORT DETAIL DRAWING FOR FEEDWATER SYSTEM | DRAWING |  | Feed Water System |  |  | DRAWING for Feed Water System | Water Treatment System | FI | 1PF3015W58A14P | (FW PIPING) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | 2007-11-02 | 2008-06-30 | 2025-04-01 | 2025-05-01 | 2025-05-31 | 2025-06-15 | 2025-06-30 | 2025-07-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140408 | PIPING SUPPORT DETAIL DRAWING FOR CLOSED COOLING WATER SYSTEM | DRAWING |  | Water System(Closed Cooling Water) |  |  | DRAWING for Water System(Closed Cooling Water) | Water Treatment System | FI | 1PF3030W42A14P | (CCW H/EX) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-09-03 | 2008-07-16 | 2025-01-31 | 2025-03-02 | 2025-04-01 | 2025-04-16 | 2025-05-01 | 2025-05-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140410 | PIPING SUPPORT DETAIL DRAWING FOR SERVICE AIR SYSTEM | DRAWING |  | Compressed air System |  |  | DRAWING for Compressed air System | Air Compressor | FA | 0CF3510W58A10 | (COMP Air System) Piping Work for CP(incl. Air Blowing) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2008-09-02 | 2008-12-03 | [6 empty] | generated |  | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140411 | PIPING SUPPORT DETAIL DRAWING FOR POTABLE WATER SYSTEM | DRAWING |  | Potable Water System |  |  | DRAWING for Potable Water System | Water Treatment System | FI | 0PF3035W42A06P | (PWP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-09-03 | 2008-09-01 | 2025-01-31 | 2025-03-02 | 2025-04-01 | 2025-04-16 | 2025-05-01 | 2025-05-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140412 | PIPING SUPPORT DETAIL DRAWING FOR DEMI. WATER SYSTEM | DRAWING |  | Water System |  |  | DRAWING for Water System | Water Treatment System | FI | 0CF3010W62A12 | (Make-up WTR Tank) Water filling for Early Power (Purchase demi. WTR) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2008-08-05 | 2008-08-07 | 2026-01-03 | 2026-02-02 | 2026-03-04 | 2026-03-19 | 2026-04-03 | 2026-04-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140415 | PIPING SUPPORT DETAIL DRAWING FOR GT ROTOR COOLING AIR COOLING SYSTEM | DRAWING | GT | AIR INTAKE SYSTEM |  |  | DRAWING for GT |  | FA | 3PF1230W20A02P | (Air Intake) P.O & Procurement_Steel Sturucture | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Air Intake System | 2007-04-30 | 2008-03-31 | 2024-07-22 | 2024-08-21 | 2024-09-20 | 2024-10-05 | 2024-10-20 | 2024-11-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140416 | PIPING SUPPORT DETAIL DRAWING FOR GT PERFORMANCE HEATER SYSTEM | DRAWING | GT | Performance Heater |  |  | DRAWING for GT |  | FA | 1PF3520W42A07.2P | (Gas HTR) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Heater | 2007-07-03 | 2008-04-01 | 2024-09-24 | 2024-10-24 | 2024-11-23 | 2024-12-08 | 2024-12-23 | 2025-01-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140417 | PIPING SUPPORT DETAIL DRAWING FOR FUEL GAS SYSTEM | DRAWING |  | Fuel Gas System |  |  | DRAWING for Fuel Gas System | Fuel Gas System | FA | 1PF3520W42A04P | (GPRS) P.O & Procurement for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2007-06-01 | 2008-03-31 | 2024-09-21 | 2024-11-16 | 2025-01-11 | 2024-12-07 | 2025-02-01 | 2025-03-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140418 | PIPING SUPPORT DETAIL DRAWING FOR STEAM BLOWING | DRAWING |  |  |  |  | DRAWING |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-06-29 | 2024-07-29 | 2024-08-28 | 2024-09-12 | 2024-09-27 | 2024-10-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140419 | PIPING SUPPORT DETAIL DRAWING FOR TREATED EFFLUENT COLLECTION AND TRANSFER SYSTEM | DRAWING |  |  |  |  | DRAWING |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-06-29 | 2024-07-29 | 2024-08-28 | 2024-09-12 | 2024-09-27 | 2024-10-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140420 | PIPING SUPPORT TYPICAL DRAWING FOR SB PIPING ESOD AREA | DRAWING |  | Piping |  |  | DRAWING for Piping |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140421 | PIPING SUPPORT DETAIL DRAWING FOR WASTE WATER SYSTEM | DRAWING |  |  |  |  | DRAWING |  | FA | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-09-01 | 2024-10-15 | 2024-11-14 | 2024-12-14 | 2024-12-29 | 2025-01-13 | 2025-01-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140422 | PIPING SUPPORT DETAIL DRAWING FOR TG MISCELLANEOUS SYSTEM | DRAWING |  |  |  |  | DRAWING |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-06-29 | 2024-07-29 | 2024-08-28 | 2024-09-12 | 2024-09-27 | 2024-10-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P0LF-140423 | PIPING SUPPORT TYPICAL DRAWING FOR SB PIPING NON ESOD AREA | DRAWING |  | PIPING |  |  | DRAWING for PIPING |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YR02-P0ZEN-150001 | DESIGN CRITERIA FOR ELECTRICAL SYSTEM | DESIGN CRITERIA |  | ELECTRICAL SYSTEM |  |  | DESIGN CRITERIA for ELECTRICAL SYSTEM | Water Treatment System | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL06-P0ZEN-150101 | ELECTRICAL LOAD LIST | LIST |  | ELECTRICAL |  |  | LIST for ELECTRICAL |  | FI | 0PF6500W70A02.6P | (Electrical Protection Panel) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2007-08-30 | 2008-03-10 | 2024-09-27 | 2024-10-27 | 2024-11-26 | 2024-12-11 | 2024-12-26 | 2025-01-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0ZEN-150201 | SYMBOL & LEGEND FOR ELECTRICAL SYSTEM |  |  | ELECTRICAL SYSTEM |  |  | for ELECTRICAL SYSTEM |  | FA | 0PF6500W70A03.6T | (Electrical Protection Panel) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2008-03-11 | 2008-04-24 |  |  |  | 2024-12-12 | 2025-01-11 | 2025-02-10 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0ZEN-150202 | KEY SINGLE LINE DIAGRAM | SINGLE LINE DIAGRAM |  |  |  |  | Single Line Diagram |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0ZEN-150211 | PROTECTION AND METERING SINGLE LINE DIAGRAM FOR GTG UNIT | SINGLE LINE DIAGRAM | Gas Turbine Generator |  |  |  | Single Line Diagram for GTG |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0ZEN-150212 | PROTECTION AND METERING SINGLE LINE DIAGRAM FOR STG UNIT | SINGLE LINE DIAGRAM | Steam Turbine & Generator |  |  |  | Single Line Diagram for STG |  | SKIP | 1PF6500W70A07P | (STG #10 & UST Shelter) P.O & Procurement - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-06-29 | 2008-06-22 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU05-P0ZEN-150221 | PHASING DIAGRAM | DIAGRAM |  |  |  |  | Diagram |  | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | 2024-11-09 | 2024-12-09 | 2025-01-08 | 2025-01-23 | 2025-02-07 | 2025-02-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150301 | SHORT CIRCUIT STUDY | SHORT CIRCUIT STUDY |  |  |  |  | SHORT CIRCUIT STUDY |  | FA | 1SF6500W62A10 | (ST GCB) Function Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Generator Circuit Breaker (GCB) | 2008-12-21 | 2009-01-04 |  |  |  | 2025-09-23 | 2025-10-23 | 2025-11-22 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150302 | LOAD FLOW & LARGE MOTOR STARTING STUDY | LOAD FLOW & LARGE MOTOR STARTING STUDY |  |  |  |  | LOAD FLOW & LARGE MOTOR STARTING STUDY |  | FA | 0SF3025W62A15 | (CWS) Loop chek & Motor Solo Test | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Circulating Water System | 2008-12-27 | 2009-01-10 |  |  |  | 2025-09-29 | 2025-10-29 | 2025-11-28 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150303 | CT PT CALCULATION STUDY REPORT FOR HV EQUIPMENT | CALCULATION STUDY REPORT |  |  |  |  | CALCULATION STUDY REPORT |  | FA | 0PF6500W70A02.7P | (Power Metering Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power Metering System | 2007-07-13 | 2008-02-12 | 2024-11-20 | 2024-12-20 | 2025-01-19 | 2025-02-03 | 2025-02-18 | 2025-03-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150304 | HARMONIC STUDY REPORT | HARMONIC STUDY REPORT |  |  |  |  | HARMONIC STUDY REPORT |  | FA | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | 2024-12-25 | 2025-01-24 | 2025-02-23 | 2025-03-10 | 2025-03-25 | 2025-04-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150305 | INSULATION STUDY REPORT | INSULATION STUDY REPORT |  |  |  |  | INSULATION STUDY REPORT | Substation | SKIP | 0PF6020W58A11P | (Piping Insulation) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-10-01 | 2008-04-30 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150306 | TAP RATIO STUDY REPORT | TAP RATIO STUDY REPORT |  |  |  |  | TAP RATIO STUDY REPORT |  | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | 2025-01-22 | 2025-02-21 | 2025-03-23 | 2025-04-07 | 2025-04-22 | 2025-05-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150311 | PROTECTION RELAY COORDINATION STUDY - GSUT / UAT / OVERALL PROTECTION FOR GTG UNIT | STUDY | Generator Step-Up Transformer / UNIT AUXILIARY TRANSFORMER | PROTECTION SYSTEM |  |  | STUDY for Generator Step-Up Transformer / UNIT AUXILIARY TRANSFORMER |  | FA | 1SF6500W62A08.1 | (GTG UAT) Function Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2008-06-18 | 2008-06-21 |  |  |  | 2025-03-21 | 2025-04-20 | 2025-05-20 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150312 | PROTECTION RELAY COORDINATION STUDY - MV SWITCHGEAR | STUDY | MV Switchgear | PROTECTION SYSTEM |  |  | STUDY for MV Switchgear | Substation | SKIP | 0PF6500W70A02.2P | (MV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > MV Switchgears With Auxiliaries | 2007-07-03 | 2008-03-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150313 | PROTECTION RELAY COORDINATION STUDY - LV SWITCHGEAR | STUDY | LV Switchgear | PROTECTION SYSTEM |  |  | STUDY for LV Switchgear | Substation | SKIP | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2007-07-03 | 2008-03-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-150314 | PROTECTION RELAY COORDINATION STUDY - GSUT / OVERALL PROTECTION FOR STG UNIT | STUDY | Generator Step-Up Transformer | PROTECTION SYSTEM |  |  | STUDY for Generator Step-Up Transformer |  | FA | 1EF6500W32A04 | (STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 |  |  |  | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0BA-150401 | ELECTRICAL CONTROL LOGIC DIAGRAM - GSUT / UAT / OVERALL PROTECTION FOR GTG UNIT | DIAGRAM | Generator Step-Up Transformer / UNIT AUXILIARY TRANSFORMER | control system |  |  | Diagram for Generator Step-Up Transformer / UNIT AUXILIARY TRANSFORMER | Transformer | FA | 1PF6500W70A04.1P | (GTG UAT) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-03-30 | 2008-03-17 | 2024-05-25 | 2024-06-24 | 2024-07-24 | 2024-08-08 | 2024-08-23 | 2024-09-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0BB-150402 | ELECTRICAL CONTROL LOGIC DIAGRAM - MV SWITCHGEAR | DIAGRAM | MV Switchgear | control system |  |  | Diagram for MV Switchgear | Substation | SKIP | 0PF6500W70A02.2P | (MV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > MV Switchgears With Auxiliaries | 2007-07-03 | 2008-03-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0BB-150403 | ELECTRICAL CONTROL LOGIC DIAGRAM - LV SWITCHGEAR | LOGIC DIAGRAM | LV SWITCHGEAR |  |  |  | LOGIC DIAGRAM for LV SWITCHGEAR |  | FA | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2007-07-03 | 2008-03-31 | 2024-08-28 | 2024-09-27 | 2024-10-27 | 2024-11-11 | 2024-11-26 | 2024-12-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0BA-150404 | ELECTRICAL CONTROL LOGIC DIAGRAM - GSUT / OVERALL PROTECTION FOR STG UNIT | LOGIC DIAGRAM | Generator Step-Up Transformer |  |  |  | LOGIC DIAGRAM for Generator Step-Up Transformer | Transformer | FA | 1PF6500W70A07P | (STG #10 & UST Shelter) P.O & Procurement - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-06-29 | 2008-06-22 | 2024-08-24 | 2024-09-23 | 2024-10-23 | 2024-11-07 | 2024-11-22 | 2024-12-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0UCA-150501 | ELECTRICAL ROOM LAYOUT DRAWING - CENTRAL CONTROL BUILDING | LAYOUT DRAWING |  |  | CENTRAL CONTROL BUILDING |  | Layout Drawing for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0UBA-150502 | ELECTRICAL ROOM LAYOUT DRAWING - GTG #1,2 LEB | LAYOUT DRAWING |  |  | GTG #1,2 Local Electrical Building |  | Layout Drawing for GTG #1,2 Local Electrical Building |  | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | 2025-07-25 | 2025-08-24 | 2025-09-23 | 2025-10-08 | 2025-10-23 | 2025-11-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0UBA-150503 | ELECTRICAL ROOM LAYOUT DRAWING - GTG #3,4,5 LEB | LAYOUT DRAWING |  |  | GTG #3,4,5 Local Electrical Building |  | Layout Drawing for GTG #3,4,5 Local Electrical Building |  | FA | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | 2025-05-24 | 2025-06-23 | 2025-07-23 | 2025-08-07 | 2025-08-22 | 2025-09-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0UBA-150504 | ELECTRICAL ROOM LAYOUT DRAWING - STG #1 LEB | LAYOUT DRAWING |  |  | STG #1 Local Electrical Building |  | Layout Drawing for STG #1 Local Electrical Building |  | FA | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | 2025-05-24 | 2025-06-23 | 2025-07-23 | 2025-08-07 | 2025-08-22 | 2025-09-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0UBA-150505 | ELECTRICAL ROOM LAYOUT DRAWING - STG #2 LEB | LAYOUT DRAWING |  |  | STG #2 Local Electrical Building |  | Layout Drawing for STG #2 Local Electrical Building |  | FA | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | 2025-05-24 | 2025-06-23 | 2025-07-23 | 2025-08-07 | 2025-08-22 | 2025-09-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0UBA-150506 | ELECTRICAL ROOM LAYOUT DRAWING - WATER TREATMENT PLANT BUILDING | LAYOUT DRAWING |  |  | WATER TREATMENT PLANT BUILDING |  | Layout Drawing for WATER TREATMENT PLANT BUILDING | WATER TREATMENT BUILDING | FI | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0UBA-150508 | ELECTRICAL ROOM LAYOUT DRAWING –AUX. LEB | LAYOUT DRAWING |  |  | Auxiliary Local Electrical Building |  | Layout Drawing for Auxiliary Local Electrical Building |  | FA | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | 2025-05-24 | 2025-06-23 | 2025-07-23 | 2025-08-07 | 2025-08-22 | 2025-09-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0BAT-150601 | SIZING CALCULATION - GENERATOR STEP - UP TRANSFORMER | SIZING CALCULATION | GENERATOR STEP - UP TRANSFORMER |  |  |  | Calculation sheet for GENERATOR STEP - UP TRANSFORMER |  | FA | 1EF6500W32A04 | (STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 |  |  |  | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BAT-150611 | TECHNICAL SPECIFICATION - GENERATOR STEP - UP TRANSFORMER | TECHNICAL SPECIFICATION | GENERATOR STEP - UP TRANSFORMER |  |  |  | Technical Specification for GENERATOR STEP - UP TRANSFORMER | Transformer | FA | 1PF6500W70A07P | (STG #10 & UST Shelter) P.O & Procurement - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-06-29 | 2008-06-22 | 2024-07-27 | 2024-08-26 | 2024-09-25 | 2024-10-10 | 2024-10-25 | 2024-11-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAT-150621 | OUTLINE DRAWING - GENERATOR STEP - UP TRANSFORMER (GTG) | OUTLINE DRAWING | GENERATOR STEP - UP TRANSFORMER (Gas Turbine Generator) |  |  |  | Outline Drawing for GENERATOR STEP - UP TRANSFORMER (Gas Turbine Generator) |  | FA | 1PF6500W70A07P | (STG #10 & UST Shelter) P.O & Procurement - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-06-29 | 2008-06-22 | 2024-10-25 | 2024-11-24 | 2024-12-24 | 2025-01-08 | 2025-01-23 | 2025-02-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAT-150626 | OUTLINE DRAWING - GENERATOR STEP - UP TRANSFORMER (STG) | OUTLINE DRAWING | GENERATOR STEP - UP TRANSFORMER (Steam Turbine & Generator) |  |  |  | Outline Drawing for GENERATOR STEP - UP TRANSFORMER (Steam Turbine & Generator) |  | FA | 1PF6500W70A07P | (STG #10 & UST Shelter) P.O & Procurement - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-06-29 | 2008-06-22 | 2024-10-25 | 2024-11-24 | 2024-12-24 | 2025-01-08 | 2025-01-23 | 2025-02-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BAT-150631 | SCHEMATIC DIAGRAM - GENERATOR STEP - UP TRANSFORMER | SCHEMATIC DIAGRAM | GENERATOR STEP - UP TRANSFORMER |  |  |  | SCHEMATIC DIAGRAM for GENERATOR STEP - UP TRANSFORMER | Transformer | FA | 1PF6500W70A07P | (STG #10 & UST Shelter) P.O & Procurement - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-06-29 | 2008-06-22 | 2024-08-24 | 2024-09-23 | 2024-10-23 | 2024-11-07 | 2024-11-22 | 2024-12-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BAT-150636 | SCHEMATIC DIAGRAM - GENERATOR STEP - UP TRANSFORMER (STG) | SCHEMATIC DIAGRAM | GENERATOR STEP - UP TRANSFORMER (Steam Turbine & Generator) |  |  |  | SCHEMATIC DIAGRAM for GENERATOR STEP - UP TRANSFORMER (Steam Turbine & Generator) | Transformer | FA | 1PF6500W70A07P | (STG #10 & UST Shelter) P.O & Procurement - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-06-29 | 2008-06-22 | 2024-08-24 | 2024-09-23 | 2024-10-23 | 2024-11-07 | 2024-11-22 | 2024-12-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0BBT-150651 | SIZING CALCULATION - UNIT AUXILIARY TRANSFORMER | SIZING CALCULATION | UNIT AUXILIARY TRANSFORMER |  |  |  | Calculation sheet for UNIT AUXILIARY TRANSFORMER | Water Treatment System | FA | 1PF6500W70A04.1P | (GTG UAT) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-03-30 | 2008-03-17 | 2024-04-29 | 2024-05-29 | 2024-06-28 | 2024-07-13 | 2024-07-28 | 2024-08-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BBT-150661 | TECHNICAL SPECIFICATION - UNIT AUXILIARY TRANSFORMER | TECHNICAL SPECIFICATION | UNIT AUXILIARY TRANSFORMER |  |  |  | Technical Specification for UNIT AUXILIARY TRANSFORMER | Transformer | FA | 1PF6500W70A04.1P | (GTG UAT) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-03-30 | 2008-03-17 | 2024-04-27 | 2024-05-27 | 2024-06-26 | 2024-07-11 | 2024-07-26 | 2024-08-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BBT-150671 | OUTLINE DRAWING - UNIT AUXILIARY TRANSFORMER | OUTLINE DRAWING | UNIT AUXILIARY TRANSFORMER |  |  |  | Outline Drawing for UNIT AUXILIARY TRANSFORMER | Transformer | FA | 1PF6500W70A04.1P | (GTG UAT) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-03-30 | 2008-03-17 | 2024-05-11 | 2024-06-10 | 2024-07-10 | 2024-07-25 | 2024-08-09 | 2024-08-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BBT-150681 | SCHEMATIC DIAGRAM - UNIT AUXILIARY TRANSFORMER | SCHEMATIC DIAGRAM | UNIT AUXILIARY TRANSFORMER |  |  |  | SCHEMATIC DIAGRAM for UNIT AUXILIARY TRANSFORMER | Transformer | FA | 1PF6500W70A04.1P | (GTG UAT) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-03-30 | 2008-03-17 | 2024-05-25 | 2024-06-24 | 2024-07-24 | 2024-08-08 | 2024-08-23 | 2024-09-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0BAA-150701 | SIZING CALCULATION - GENERATOR CIRCUIT BREAKER / ISOLATED PHASE BUSDUCT | SIZING CALCULATION | GENERATOR CIRCUIT BREAKER / ISOLATED PHASE BUSDUCT |  |  |  | Calculation sheet for GENERATOR CIRCUIT BREAKER / ISOLATED PHASE BUSDUCT | GENERATOR CIRCUIT BREAKER | FI | 1CF6500W74A04 | (IPB) Installation form TR to GCB(incl. Support) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2008-06-17 | 2008-08-18 | 2025-10-16 | 2025-11-15 | 2025-12-15 | 2025-12-30 | 2026-01-14 | 2026-01-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BAC-150711 | TECHNICAL SPECIFICATION - GENERATOR CIRCUIT BREAKER | TECHNICAL SPECIFICATION | Generator Circuit Breaker |  |  |  | Technical Specification for Generator Circuit Breaker | GENERATOR CIRCUIT BREAKER | FA | 1PF6500W86A02P | (GT GCB) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Generator Circuit Breaker (GCB) | 2007-05-31 | 2008-03-31 | 2024-09-28 | 2024-10-28 | 2024-11-27 | 2024-12-12 | 2024-12-27 | 2025-01-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAC-150721 | OUTLINE DRAWING - GENERATOR CIRCUIT BREAKER | OUTLINE DRAWING | Generator Circuit Breaker |  |  |  | Outline Drawing for Generator Circuit Breaker | GENERATOR CIRCUIT BREAKER | FA | 1PF6500W86A02P | (GT GCB) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Generator Circuit Breaker (GCB) | 2007-05-31 | 2008-03-31 | 2024-11-27 | 2024-12-27 | 2025-01-26 | 2025-02-10 | 2025-02-25 | 2025-03-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BAC-150731 | SCHEMATIC DIAGRAM - GENERATOR CIRCUIT BREAKER | SCHEMATIC DIAGRAM | Generator Circuit Breaker |  |  |  | SCHEMATIC DIAGRAM for Generator Circuit Breaker | GENERATOR CIRCUIT BREAKER | FA | 1PF6500W86A02P | (GT GCB) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Generator Circuit Breaker (GCB) | 2007-05-31 | 2008-03-31 | 2025-01-26 | 2025-02-25 | 2025-03-27 | 2025-04-11 | 2025-04-26 | 2025-05-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BAA-150751 | TECHNICAL SPECIFICATION - ISOLATED PHASE BUSDUCT FOR GTG UNIT | TECHNICAL SPECIFICATION | ISOLATED PHASE BUSDUCT |  |  |  | Technical Specification for ISOLATED PHASE BUSDUCT | Isolated Phase Bus | FA | 1PF6500W74A02P | (IPB) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2007-08-02 | 2008-05-01 | 2024-11-30 | 2024-12-30 | 2025-01-29 | 2025-02-13 | 2025-02-28 | 2025-03-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BAA-150752 | TECHNICAL SPECIFICATION - ISOLATED PHASE BUSDUCT FOR STG UNIT | TECHNICAL SPECIFICATION | ISOLATED PHASE BUSDUCT |  |  |  | Technical Specification for ISOLATED PHASE BUSDUCT | Isolated Phase Bus | FA | 1PF6500W74A02P | (IPB) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2007-08-02 | 2008-05-01 | 2024-11-30 | 2024-12-30 | 2025-01-29 | 2025-02-13 | 2025-02-28 | 2025-03-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150761 | GENERAL ARRANGEMENT DRAWING - ISOLATED PHASE BUSDUCT FOR GTG UNIT | GENERAL ARRANGEMENT DRAWING | ISOLATED PHASE BUSDUCT |  |  |  | GENERAL ARRANGEMENT DRAWING for ISOLATED PHASE BUSDUCT | Isolated Phase Bus | FA | 1PF6500W74A02P | (IPB) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2007-08-02 | 2008-05-01 | 2025-01-29 | 2025-02-28 | 2025-03-30 | 2025-04-14 | 2025-04-29 | 2025-05-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150762 | GENERAL ARRANGEMENT DRAWING - ISOLATED PHASE BUSDUCT FOR STG UNIT | GENERAL ARRANGEMENT DRAWING | ISOLATED PHASE BUSDUCT |  |  |  | GENERAL ARRANGEMENT DRAWING for ISOLATED PHASE BUSDUCT | Isolated Phase Bus | FA | 1PF6500W74A02P | (IPB) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2007-08-02 | 2008-05-01 | 2025-01-29 | 2025-02-28 | 2025-03-30 | 2025-04-14 | 2025-04-29 | 2025-05-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150766 | CONNECTION DRAWING - ISOLATED PHASE BUSDUCT FOR GTG UNIT | CONNECTION DRAWING | ISOLATED PHASE BUSDUCT |  |  |  | CONNECTION DRAWING for ISOLATED PHASE BUSDUCT | Isolated Phase Bus | FA | 1CF6500W74A06 | (IPB) IPB connection with TR & GCB | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2008-08-26 | 2008-09-01 | 2026-02-23 | 2026-03-25 | 2026-04-24 | 2026-05-09 | 2026-05-24 | 2026-06-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150767 | CONNECTION DRAWING - ISOLATED PHASE BUSDUCT FOR STG UNIT | CONNECTION DRAWING | ISOLATED PHASE BUSDUCT |  |  |  | CONNECTION DRAWING for ISOLATED PHASE BUSDUCT | Isolated Phase Bus | FA | 1CF6500W74A06 | (IPB) IPB connection with TR & GCB | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2008-08-26 | 2008-09-01 | 2026-02-23 | 2026-03-25 | 2026-04-24 | 2026-05-09 | 2026-05-24 | 2026-06-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150771 | PRESSURIZATION PANEL DRAWING - ISOLATED PHASE BUSDUCT FOR GTG UNIT | PRESSURIZATION PANEL DRAWING | ISOLATED PHASE BUSDUCT |  |  |  | PRESSURIZATION PANEL DRAWING for ISOLATED PHASE BUSDUCT | Isolated Phase Bus | FA | 1PF6500W74A02P | (IPB) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2007-08-02 | 2008-05-01 | 2025-03-30 | 2025-04-29 | 2025-05-29 | 2025-06-13 | 2025-06-28 | 2025-07-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150772 | PRESSURIZATION PANEL DRAWING - ISOLATED PHASE BUSDUCT FOR STG UNIT | PRESSURIZATION PANEL DRAWING | ISOLATED PHASE BUSDUCT |  |  |  | PRESSURIZATION PANEL DRAWING for ISOLATED PHASE BUSDUCT | Isolated Phase Bus | FA | 1PF6500W74A02P | (IPB) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2007-08-02 | 2008-05-01 | 2025-03-30 | 2025-04-29 | 2025-05-29 | 2025-06-13 | 2025-06-28 | 2025-07-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150776 | DETAIL DRAWING - ISOLATED PHASE BUSDUCT FOR GTG UNIT | DETAIL DRAWING | ISOLATED PHASE BUSDUCT |  |  |  | Detail Drawing for ISOLATED PHASE BUSDUCT | Isolated Phase Bus | FA | 1PF6500W74A02P | (IPB) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2007-08-02 | 2008-05-01 | 2025-01-29 | 2025-02-28 | 2025-03-30 | 2025-04-14 | 2025-04-29 | 2025-05-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150777 | DETAIL DRAWING - ISOLATED PHASE BUSDUCT FOR STG UNIT | DETAIL DRAWING | ISOLATED PHASE BUSDUCT |  |  |  | Detail Drawing for ISOLATED PHASE BUSDUCT | Isolated Phase Bus | FA | 1PF6500W74A02P | (IPB) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2007-08-02 | 2008-05-01 | 2025-01-29 | 2025-02-28 | 2025-03-30 | 2025-04-14 | 2025-04-29 | 2025-05-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150781 | STEEL SUPPORT STRUCTURE DRAWING - ISOLATED PHASE BUSDUCT FOR GTG UNIT | DRAWING | ISOLATED PHASE BUSDUCT |  |  |  | DRAWING for ISOLATED PHASE BUSDUCT | Isolated Phase Bus | FA | 1PF6500W74A02P | (IPB) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2007-08-02 | 2008-05-01 | 2025-01-29 | 2025-02-28 | 2025-03-30 | 2025-04-14 | 2025-04-29 | 2025-05-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BAA-150782 | STEEL SUPPORT STRUCTURE DRAWING - ISOLATED PHASE BUSDUCT FOR STG UNIT | DRAWING | ISOLATED PHASE BUSDUCT |  |  |  | DRAWING for ISOLATED PHASE BUSDUCT | Isolated Phase Bus | FA | 1PF6500W74A02P | (IPB) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2007-08-02 | 2008-05-01 | 2025-01-29 | 2025-02-28 | 2025-03-30 | 2025-04-14 | 2025-04-29 | 2025-05-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BB-150801 | TECHNICAL SPECIFICATION - MV SWITCHGEAR | TECHNICAL SPECIFICATION | MV Switchgear |  |  |  | Technical Specification for MV Switchgear | Substation | SKIP | 0EF6500W70A01.2 | (MV SWGR) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > MV Switchgears With Auxiliaries |  | 2007-03-30 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BB-150811 | SINGLE LINE DIAGRAM – 13.8kV GTG SWITCHGEAR #1 | SINGLE LINE DIAGRAM | Switchgear |  |  |  | Single Line Diagram for Switchgear |  | SKIP | 0PF5544W70A02P | (GIS Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 | 2008-01-29 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BB-150812 | SINGLE LINE DIAGRAM – 13.8kV GTG SWITCHGEAR #2 | SINGLE LINE DIAGRAM | Switchgear |  |  |  | Single Line Diagram for Switchgear |  | SKIP | 0PF5544W70A02P | (GIS Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 | 2008-01-29 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BB-150813 | SINGLE LINE DIAGRAM – 13.8kV GTG SWITCHGEAR #3 | SINGLE LINE DIAGRAM | Switchgear |  |  |  | Single Line Diagram for Switchgear |  | SKIP | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2007-07-03 | 2008-03-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BB-150814 | SINGLE LINE DIAGRAM – 13.8kV GTG SWITCHGEAR #4 | SINGLE LINE DIAGRAM | Switchgear |  |  |  | Single Line Diagram for Switchgear |  | SKIP | 0PF5544W70A02P | (GIS Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 | 2008-01-29 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BB-150815 | SINGLE LINE DIAGRAM – 13.8kV GTG SWITCHGEAR #5 | SINGLE LINE DIAGRAM | Gas Turbine Generator SWITCHGEAR #5 |  |  |  | Single Line Diagram for Gas Turbine Generator SWITCHGEAR #5 |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BB-150816 | SINGLE LINE DIAGRAM – 13.8kV COMMON SWITCHGEAR | SINGLE LINE DIAGRAM | COMMON SWITCHGEAR |  |  |  | Single Line Diagram for COMMON SWITCHGEAR |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BB-150821 | OUTLINE DRAWING - MV SWITCHGEAR | OUTLINE DRAWING | MV SWITCHGEAR |  |  |  | Outline Drawing for MV SWITCHGEAR | Substation | SKIP | 0PF6500W70A02.2P | (MV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > MV Switchgears With Auxiliaries | 2007-07-03 | 2008-03-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BB-150831 | WIRING DIAGRAM - MV SWITCHGEAR | WIRING DIAGRAM | MV SWITCHGEAR |  |  |  | WIRING DIAGRAM for MV SWITCHGEAR |  | FA | 0PF6500W70A02.2P | (MV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > MV Switchgears With Auxiliaries | 2007-07-03 | 2008-03-31 | 2024-09-25 | 2024-10-25 | 2024-11-24 | 2024-12-09 | 2024-12-24 | 2025-01-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BB-150836 | DRAWINGS - HTS | DRAWINGS |  |  |  |  | DRAWINGS |  | FA | 2PF1615W64A06.1P | (HRSG #22 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Duct | 2007-06-14 | 2008-03-03 |  |  |  | 2024-03-16 | 2024-04-15 | 2024-05-15 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BF-150901 | TECHNICAL SPECIFICATION - LV SWITCHGEAR | TECHNICAL SPECIFICATION | LV SWITCHGEAR |  |  |  | Technical Specification for LV SWITCHGEAR | Substation | SKIP | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2007-07-03 | 2008-03-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BF-150902 | TECHNICAL SPECIFICATION - 13.8/0.48kV MOLD TRANSFORMER | TECHNICAL SPECIFICATION | MOLD TRANSFORMER |  |  |  | Technical Specification for MOLD TRANSFORMER | Transformer | FA | 1PF6500W70A04P | (GTG TR) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-04-02 | 2008-04-15 | 2024-04-30 | 2024-05-30 | 2024-06-29 | 2024-07-14 | 2024-07-29 | 2024-08-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BF-150903 | TECHNICAL SPECIFICATION - 480V NON SEGREGATED PHASE BUS DUCT | TECHNICAL SPECIFICATION | Non-Segregated Phase Bus Duct |  |  |  | Technical Specification for Non-Segregated Phase Bus Duct | Isolated Phase Bus | FA | 1PF6500W74A02P | (IPB) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2007-08-02 | 2008-05-01 | 2024-11-30 | 2024-12-30 | 2025-01-29 | 2025-02-13 | 2025-02-28 | 2025-03-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BFA-150911 | SINGLE LINE DIAGRAM - 480V GTG/HRSG SWITCHGEAR | SINGLE LINE DIAGRAM | Gas Turbine Generator/Heat Recovery Steam Generator SWITCHGEAR |  |  |  | Single Line Diagram for Gas Turbine Generator/Heat Recovery Steam Generator SWITCHGEAR |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BFA-150912 | SINGLE LINE DIAGRAM - 480V STG/ACC SWITCHGEAR | SINGLE LINE DIAGRAM | Steam Turbine & Generator/Air Cooled Condenser SWITCHGEAR |  |  |  | Single Line Diagram for Steam Turbine & Generator/Air Cooled Condenser SWITCHGEAR |  | SKIP | 1PF2070W42A04P | (STG #10 Aux. Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Auxiliary Equipment | 2007-04-30 | 2008-07-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BFA-150913 | SINGLE LINE DIAGRAM - 480V COMMON SWITCHGEAR | SINGLE LINE DIAGRAM | COMMON SWITCHGEAR |  |  |  | Single Line Diagram for COMMON SWITCHGEAR |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BFA-150914 | SINGLE LINE DIAGRAM - 480V WT SWITCHGEAR | SINGLE LINE DIAGRAM | WT SWITCHGEAR |  |  |  | Single Line Diagram for WT SWITCHGEAR |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BFA-150915 | SINGLE LINE DIAGRAM - 480V FIRE BRIGADE SWITCHGEAR | SINGLE LINE DIAGRAM | FIRE BRIGADE SWITCHGEAR |  |  |  | Single Line Diagram for FIRE BRIGADE SWITCHGEAR |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BFA-150916 | SINGLE LINE DIAGRAM - 480V BLOCK#1 ESSENTIAL SWITCHGEAR | SINGLE LINE DIAGRAM | BLOCK#1 ESSENTIAL SWITCHGEAR |  |  |  | Single Line Diagram for BLOCK#1 ESSENTIAL SWITCHGEAR |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BFA-150917 | SINGLE LINE DIAGRAM - 480V BLOCK#2 ESSENTIAL SWITCHGEAR | SINGLE LINE DIAGRAM | BLOCK#2 ESSENTIAL SWITCHGEAR |  |  |  | Single Line Diagram for BLOCK#2 ESSENTIAL SWITCHGEAR |  | SKIP | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2007-07-03 | 2008-03-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BFA-150918 | SINGLE LINE DIAGRAM - 480V COMMON ESSENTIAL SWITCHGEAR | SINGLE LINE DIAGRAM | COMMON ESSENTIAL SWITCHGEAR |  |  |  | Single Line Diagram for COMMON ESSENTIAL SWITCHGEAR |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150931 | OUTLINE DRAWING - 480V GTG/HRSG SWITCHGEAR | OUTLINE DRAWING | Gas Turbine Generator/Heat Recovery Steam Generator SWITCHGEAR |  |  |  | Outline Drawing for Gas Turbine Generator/Heat Recovery Steam Generator SWITCHGEAR |  | FA | 3PF1600W74A06.1P | (HRSG #32 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > HRSG LEB | 2007-09-15 | 2008-08-23 | 2025-01-11 | 2025-02-10 | 2025-03-12 | 2025-03-27 | 2025-04-11 | 2025-04-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150932 | OUTLINE DRAWING - 480V STG/ACC SWITCHGEAR | OUTLINE DRAWING | Steam Turbine & Generator/Air Cooled Condenser SWITCHGEAR |  |  |  | Outline Drawing for Steam Turbine & Generator/Air Cooled Condenser SWITCHGEAR |  | FA | 1PF2070W42A04P | (STG #10 Aux. Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Auxiliary Equipment | 2007-04-30 | 2008-07-31 | 2024-12-15 | 2025-01-14 | 2025-02-13 | 2025-02-28 | 2025-03-15 | 2025-03-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150933 | OUTLINE DRAWING - 480V COMMON SWITCHGEAR | OUTLINE DRAWING | COMMON SWITCHGEAR |  |  |  | Outline Drawing for COMMON SWITCHGEAR | Substation | SKIP | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2007-07-03 | 2008-03-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150934 | OUTLINE DRAWING - 480V WT SWITCHGEAR | OUTLINE DRAWING | WT SWITCHGEAR |  |  |  | Outline Drawing for WT SWITCHGEAR |  | FA | 0PF6500W70A02.2P | (MV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > MV Switchgears With Auxiliaries | 2007-07-03 | 2008-03-31 | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150935 | OUTLINE DRAWING - 480V FIRE BRIGADE SWITCHGEAR | OUTLINE DRAWING | SWITCHGEAR |  |  |  | Outline Drawing for SWITCHGEAR | Substation | SKIP | 0PF5544W70A02P | (GIS Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 | 2008-01-29 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150936 | OUTLINE DRAWING - 480V BLOCK#1 ESSENTIAL SWITCHGEAR | OUTLINE DRAWING | SWITCHGEAR |  |  |  | Outline Drawing for SWITCHGEAR | Substation | SKIP | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2007-07-03 | 2008-03-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150937 | OUTLINE DRAWING - 480V BLOCK#2 ESSENTIAL SWITCHGEAR | OUTLINE DRAWING | SWITCHGEAR |  |  |  | Outline Drawing for SWITCHGEAR | Substation | SKIP | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2007-07-03 | 2008-03-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150938 | OUTLINE DRAWING - 480V COMMON ESSENTIAL SWITCHGEAR | OUTLINE DRAWING | SWITCHGEAR |  |  |  | Outline Drawing for SWITCHGEAR | Substation | SKIP | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2007-07-03 | 2008-03-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150939 | OUTLINE DRAWING - 13.8/0.48kV MOLD TRANSFORMER | OUTLINE DRAWING | TRANSFORMER |  |  |  | Outline Drawing for TRANSFORMER | Transformer | FA | 1PF6500W70A04P | (GTG TR) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-04-02 | 2008-04-15 | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BF-150940 | OUTLINE DRAWING - 480V NON SEGREGATED PHASE BUS DUCT | OUTLINE DRAWING | Non-Segregated Phase Bus Duct |  |  |  | Outline Drawing for Non-Segregated Phase Bus Duct | Isolated Phase Bus | FA | 1PF6500W74A02P | (IPB) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2007-08-02 | 2008-05-01 | 2025-01-29 | 2025-02-28 | 2025-03-30 | 2025-04-14 | 2025-04-29 | 2025-05-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BFA-150951 | WIRING DIAGRAM - 480V GTG/HRSG SWITCHGEAR | WIRING DIAGRAM | SWITCHGEAR |  |  |  | WIRING DIAGRAM for SWITCHGEAR |  | FA | 0PF6500W70A02.2P | (MV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > MV Switchgears With Auxiliaries | 2007-07-03 | 2008-03-31 | 2024-09-25 | 2024-10-25 | 2024-11-24 | 2024-12-09 | 2024-12-24 | 2025-01-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BFA-150952 | WIRING DIAGRAM - 480V STG/ACC SWITCHGEAR | WIRING DIAGRAM | SWITCHGEAR |  |  |  | WIRING DIAGRAM for SWITCHGEAR |  | FA | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2007-07-03 | 2008-03-31 | 2024-09-25 | 2024-10-25 | 2024-11-24 | 2024-12-09 | 2024-12-24 | 2025-01-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BFA-150953 | WIRING DIAGRAM - 480V COMMON SWITCHGEAR | WIRING DIAGRAM | SWITCHGEAR |  |  |  | WIRING DIAGRAM for SWITCHGEAR |  | FA | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2007-07-03 | 2008-03-31 | 2024-09-25 | 2024-10-25 | 2024-11-24 | 2024-12-09 | 2024-12-24 | 2025-01-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BFA-150954 | WIRING DIAGRAM - 480V WT SWITCHGEAR | WIRING DIAGRAM | SWITCHGEAR |  |  |  | WIRING DIAGRAM for SWITCHGEAR |  | FA | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2007-07-03 | 2008-03-31 | 2024-09-25 | 2024-10-25 | 2024-11-24 | 2024-12-09 | 2024-12-24 | 2025-01-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BFA-150955 | WIRING DIAGRAM - 480V FIRE BRIGADE SWITCHGEAR | WIRING DIAGRAM | SWITCHGEAR |  |  |  | WIRING DIAGRAM for SWITCHGEAR |  | FA | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2007-07-03 | 2008-03-31 | 2024-09-25 | 2024-10-25 | 2024-11-24 | 2024-12-09 | 2024-12-24 | 2025-01-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BFA-150956 | WIRING DIAGRAM - 480V BLOCK#1 ESSENTIAL SWITCHGEAR | WIRING DIAGRAM | SWITCHGEAR |  |  |  | WIRING DIAGRAM for SWITCHGEAR |  | FA | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2007-07-03 | 2008-03-31 | 2024-09-25 | 2024-10-25 | 2024-11-24 | 2024-12-09 | 2024-12-24 | 2025-01-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BFA-150957 | WIRING DIAGRAM - 480V BLOCK#2 ESSENTIAL SWITCHGEAR | WIRING DIAGRAM | SWITCHGEAR |  |  |  | WIRING DIAGRAM for SWITCHGEAR |  | FA | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2007-07-03 | 2008-03-31 | 2024-09-25 | 2024-10-25 | 2024-11-24 | 2024-12-09 | 2024-12-24 | 2025-01-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BFA-150958 | WIRING DIAGRAM - 480V COMMON ESSENTIAL SWITCHGEAR | WIRING DIAGRAM | SWITCHGEAR |  |  |  | WIRING DIAGRAM for SWITCHGEAR |  | FA | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2007-07-03 | 2008-03-31 | 2024-09-25 | 2024-10-25 | 2024-11-24 | 2024-12-09 | 2024-12-24 | 2025-01-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0BT-151001 | SIZING CALCULATION - DC & AC UPS SYSTEM | SIZING CALCULATION |  | DC & AC UPS SYSTEM |  |  | Calculation sheet for DC & AC UPS SYSTEM | Substation | SKIP | 0PF6500W70A02.4P | (DC & UPS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > DC & UPS System | 2007-08-08 | 2008-03-06 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0BT-151011 | TECHNICAL SPECIFICATION - DC & AC UPS SYSTEM | TECHNICAL SPECIFICATION |  | DC & AC UPS SYSTEM |  |  | Technical Specification for DC & AC UPS SYSTEM |  | FA | 0PF6500W70A02.4P | (DC & UPS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > DC & UPS System | 2007-08-08 | 2008-03-06 | 2025-02-17 | 2025-03-19 | 2025-04-18 | 2025-05-03 | 2025-05-18 | 2025-06-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BT-151021 | SINGLE LINE DIAGRAM - BLOCK #1 DC & AC UPS SYSTEM | SINGLE LINE DIAGRAM |  | BLOCK #1 DC & AC UPS SYSTEM |  |  | Single Line Diagram for BLOCK #1 DC & AC UPS SYSTEM |  | SKIP | 0PF6500W70A02.4P | (DC & UPS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > DC & UPS System | 2007-08-08 | 2008-03-06 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BT-151026 | SINGLE LINE DIAGRAM - BLOCK #2 DC & AC UPS SYSTEM | SINGLE LINE DIAGRAM |  | BLOCK #2 DC & AC UPS SYSTEM |  |  | Single Line Diagram for BLOCK #2 DC & AC UPS SYSTEM |  | SKIP | 0PF6500W70A02.4P | (DC & UPS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > DC & UPS System | 2007-08-08 | 2008-03-06 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0BT-151031 | SINGLE LINE DIAGRAM - COMMON DC & UPS SYSTEM | SINGLE LINE DIAGRAM |  | COMMON DC & UPS SYSTEM |  |  | Single Line Diagram for COMMON DC & UPS SYSTEM |  | SKIP | 0PF6500W70A02.4P | (DC & UPS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > DC & UPS System | 2007-08-08 | 2008-03-06 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BT-151041 | OUTLINE DRAWING - BLOCK #1 DC & AC UPS SYSTEM | OUTLINE DRAWING |  | BLOCK #1 DC & AC UPS SYSTEM |  |  | Outline Drawing for BLOCK #1 DC & AC UPS SYSTEM | Substation | SKIP | 0PF6500W70A02.4P | (DC & UPS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > DC & UPS System | 2007-08-08 | 2008-03-06 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BT-151046 | OUTLINE DRAWING - BLOCK #2 DC & AC UPS SYSTEM | OUTLINE DRAWING |  | Direct Current & Uninterruptible Power Supply SYSTEM |  |  | Outline Drawing for Direct Current & Uninterruptible Power Supply SYSTEM | Lighting&small PoWer System | SKIP | 0PF6500W70A02.4P | (DC & UPS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > DC & UPS System | 2007-08-08 | 2008-03-06 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0BT-151051 | OUTLINE DRAWING - COMMON DC & AC UPS SYSTEM | OUTLINE DRAWING |  | Direct Current & Uninterruptible Power Supply SYSTEM |  |  | Outline Drawing for Direct Current & Uninterruptible Power Supply SYSTEM | Lighting&small PoWer System | SKIP | 0PF6500W70A02.4P | (DC & UPS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > DC & UPS System | 2007-08-08 | 2008-03-06 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BT-151061 | SCHEMATIC DIAGRAM - BLOCK #1 DC & AC UPS SYSTEM | SCHEMATIC DIAGRAM |  | Direct Current & Uninterruptible Power Supply SYSTEM |  |  | SCHEMATIC DIAGRAM for Direct Current & Uninterruptible Power Supply SYSTEM | Lighting&small PoWer System | SKIP | 0PF6500W70A02.4P | (DC & UPS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > DC & UPS System | 2007-08-08 | 2008-03-06 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BT-151066 | SCHEMATIC DIAGRAM - BLOCK #2 DC & AC UPS SYSTEM | SCHEMATIC DIAGRAM |  | Direct Current & Uninterruptible Power Supply SYSTEM |  |  | SCHEMATIC DIAGRAM for Direct Current & Uninterruptible Power Supply SYSTEM | Lighting&small PoWer System | SKIP | 0PF6500W70A02.4P | (DC & UPS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > DC & UPS System | 2007-08-08 | 2008-03-06 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0BT-151071 | SCHEMATIC DIAGRAM - COMMON DC & AC UPS SYSTEM | SCHEMATIC DIAGRAM |  | Direct Current & Uninterruptible Power Supply SYSTEM |  |  | SCHEMATIC DIAGRAM for Direct Current & Uninterruptible Power Supply SYSTEM | Lighting&small PoWer System | SKIP | 0PF6500W70A02.4P | (DC & UPS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > DC & UPS System | 2007-08-08 | 2008-03-06 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0CHB-151101 | TECHNICAL SPECIFICATION - PROTECTION RELAY PANEL | TECHNICAL SPECIFICATION |  |  |  |  | Technical Specification |  | FA | 0PF6500W70A02.6P | (Electrical Protection Panel) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2007-08-30 | 2008-03-10 | 2024-09-13 | 2024-10-13 | 2024-11-12 | 2024-11-27 | 2024-12-12 | 2024-12-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CHB-151111 | OUTLINE DRAWING - PROTECTION RELAY PANEL & FMS FOR GTG UNIT | OUTLINE DRAWING | Gas Turbine Generator | Fault Monitoring System |  |  | Outline Drawing for GTG |  | FA | 3PF1260W86A02P | (VMS) P.O & Procurement for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Vibration Monitoring System (VMS) | 2007-08-31 | 2008-07-02 | 2024-09-28 | 2024-10-28 | 2024-11-27 | 2024-12-12 | 2024-12-27 | 2025-01-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CHB-151112 | OUTLINE DRAWING - PROTECTION RELAY PANEL & FMS FOR STG UNIT | OUTLINE DRAWING | Steam Turbine & Generator | Fault Monitoring System |  |  | Outline Drawing for STG |  | FA | 1PF6500W70A07P | (STG #10 & UST Shelter) P.O & Procurement - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-06-29 | 2008-06-22 | 2024-07-27 | 2024-08-26 | 2024-09-25 | 2024-10-10 | 2024-10-25 | 2024-11-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0CHB-151121 | WIRING DIAGRAM - PROTECTION RELAY PANEL & FMS FOR GTG UNIT | WIRING DIAGRAM | Gas Turbine Generator | Fault Monitoring System |  |  | WIRING DIAGRAM for GTG |  | FA | 1PF1260W86A02P | (VMS) P.O & Procurement for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Vibration Monitoring System (VMS) | 2007-08-31 | 2008-05-01 | 2024-11-23 | 2024-12-23 | 2025-01-22 | 2025-02-06 | 2025-02-21 | 2025-03-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0CHB-151122 | WIRING DIAGRAM - PROTECTION RELAY PANEL & FMS FOR STG UNIT | WIRING DIAGRAM | Steam Turbine & Generator | Fault Monitoring System |  |  | WIRING DIAGRAM for STG |  | FA | 2PF6500W70A07P | (STG #20 & UST Shelter) P.O & Procurement - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-06-29 | 2008-07-14 | 2024-09-21 | 2024-10-21 | 2024-11-20 | 2024-12-05 | 2024-12-20 | 2025-01-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CHB-151131 | CONFIGURATION DIAGRM - FAULT MONITORING SYSTEM | DIAGRAM |  | Fault Monitoring System |  |  | Diagram for Fault Monitoring System | Substation | SKIP | 2PF1260W86A02P | (VMS) P.O & Procurement for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Vibration Monitoring System (VMS) | 2007-08-31 | 2008-06-02 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0CFA-151161 | TECHNICAL SPECIFICATION - METERING PANEL | TECHNICAL SPECIFICATION |  |  |  |  | Technical Specification |  | FA | 0PF6500W70A02.6P | (Electrical Protection Panel) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2007-08-30 | 2008-03-10 | 2024-09-13 | 2024-10-13 | 2024-11-12 | 2024-11-27 | 2024-12-12 | 2024-12-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CFA-151171 | OUTLINE DRAWING - METERING PANEL | OUTLINE DRAWING |  |  |  |  | Outline Drawing |  | FA | 0PF6500W70A02.7P | (Power Metering Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power Metering System | 2007-07-13 | 2008-02-12 | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YU03-P0CFA-151181 | WIRING DIAGRAM - METERING PANEL | WIRING DIAGRAM |  |  |  |  | WIRING DIAGRAM |  | FA | 0PF6500W70A02.6P | (Electrical Protection Panel) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2007-08-30 | 2008-03-10 | 2025-06-15 | 2025-07-15 | 2025-08-14 | 2025-08-29 | 2025-09-13 | 2025-09-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YQ02-P0ZEN-152001 | TYPICAL INSTALLATION DRAWING - RACEWAY | TYPICAL INSTALLATION DRAWING |  |  |  |  | TYPICAL INSTALLATION DRAWING |  | FA | 0CF6040W74A05 | (Raceway) Installation for CCB-GIS BLDG(Early Power) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Raceway System | 2008-03-18 | 2008-04-17 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0ZEN-152002 | TECHNICAL SPECIFICATION - CABLE TRAY AND ACCESSORIES | TECHNICAL SPECIFICATION |  |  |  |  | Technical Specification |  | FA | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD16-P0ZEN-152003 | MAIN CABLE ROUTE PLAN | PLAN |  |  |  |  | Plan |  | FA | 1EF6040W16A01 | (Cable tunnel) Cable tunnel Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-30 |  |  |  | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152004 | 380KV CABLE ROUTE PLAN | PLAN |  |  |  |  | Plan |  | FA | 1EF6040W16A01 | (Cable tunnel) Cable tunnel Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-30 |  |  |  | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152005 | CABLE TRAY LAYOUT FOR CENTRAL CONTROL BUILDING | LAYOUT | Cable Tray |  | CENTRAL CONTROL BUILDING |  | Layout Drawing for Cable Tray | Substation | SKIP | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152006 | CABLE TRAY LAYOUT FOR GTG #1,2 LEB | LAYOUT | Cable Tray |  | Local Electrical Building |  | Layout Drawing for Cable Tray | Substation | SKIP | 0CF6040W74A06.1 | (Electrical Cable) Cable Pulling for GTG LEB-GIS BLDG(Early Power) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2008-05-31 | 2008-07-15 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152007 | CABLE TRAY LAYOUT FOR GTG #3,4,5 LEB | CABLE TRAY LAYOUT | Gas Turbine Generator |  | Local Electrical Building |  | CABLE TRAY LAYOUT for GTG | Cable Tray | SKIP | 3CF1255W74A09 | (GTG#31 Electrical) Cable work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Electrical System | 2008-08-01 | 2008-09-15 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152008 | CABLE TRAY LAYOUT FOR ST #1 LEB | CABLE TRAY LAYOUT | Steam Turbine |  | Local Electrical Building |  | CABLE TRAY LAYOUT for STG | Cable Tray | SKIP | 1EF6040W16A01 | (Cable tunnel) Cable tunnel Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-30 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152009 | CABLE TRAY LAYOUT FOR ST #2 LEB | CABLE TRAY LAYOUT | Steam Turbine |  | Local Electrical Building |  | CABLE TRAY LAYOUT for STG | Cable Tray | SKIP | 2EF6040W16A02 | (Cable tunnel) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-01 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152010 | CABLE TRAY LAYOUT FOR ST BUILDING | CABLE TRAY LAYOUT |  |  | ST Building |  | CABLE TRAY LAYOUT for ST Building | ST BUILDING | FI | 3EF6040W16A01 | (Cable tunnel) Cable tunnel Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-30 |  |  |  | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152011 | CABLE TRAY LAYOUT FOR WATER TREATMENT BUILDING | CABLE TRAY LAYOUT |  |  | WATER TREATMENT BUILDING |  | CABLE TRAY LAYOUT for WATER TREATMENT BUILDING | Water Treatment System | FI | 0PF3010W42A05P | (WTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-08-31 | 2008-09-01 | 2024-12-29 | 2025-01-28 | 2025-02-27 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152012 | CABLE TRAY LAYOUT FOR FGS ELECTRICAL BUILDING | CABLE TRAY LAYOUT |  | Fuel Gas System | ELECTRICAL BUILDING |  | CABLE TRAY LAYOUT for Fuel Gas System | Fuel Gas System | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | 2024-08-07 | 2024-09-18 | 2024-10-30 | 2024-10-09 | 2024-11-20 | 2025-01-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152013 | CABLE TRAY LAYOUT FOR WORKSHOP & STORAGE BUILDING | CABLE TRAY LAYOUT |  |  | WORKSHOP & STORAGE BUILDING |  | CABLE TRAY LAYOUT for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 0CF6040W74A05.1 | (Electrical Cable) Cable Pulling for CCB-GIS BLDG(Early Power) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2008-05-10 | 2008-05-20 |  |  |  | 2025-02-10 | 2025-03-12 | 2025-04-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152014 | CABLE TRAY LAYOUT FOR ADMINISTRATION & SOCIAL BUILDING | CABLE TRAY LAYOUT |  |  | ADMINISTRATION & SOCIAL BUILDING |  | CABLE TRAY LAYOUT for ADMINISTRATION & SOCIAL BUILDING |  | FA | 0CF6040W74A05.1 | (Electrical Cable) Cable Pulling for CCB-GIS BLDG(Early Power) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2008-05-10 | 2008-05-20 | 2026-10-03 | 2026-11-02 | 2026-12-02 | 2026-12-17 | 2027-01-01 | 2027-01-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152015 | CABLE TRAY LAYOUT FOR PIPE RACK | CABLE TRAY LAYOUT |  |  | PIPE RACK |  | CABLE TRAY LAYOUT for PIPE RACK | PIPE RACK | FI | 0CF5550W46A05 | (Pipe Rack) Pipe Rack Installation for Early Power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Pipe Rack | 2007-12-13 | 2008-04-15 |  |  |  | 2024-09-14 | 2024-10-14 | 2024-11-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152016 | CABLE TRAY LAYOUT FOR AUX LEB | CABLE TRAY LAYOUT |  |  | Auxiliary Local Electrical Building |  | CABLE TRAY LAYOUT for Auxiliary Local Electrical Building | Cable Tray | SKIP | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152017 | CABLE TRAY LAYOUT FOR GTG PCC #1,2,3,4,5 | CABLE TRAY LAYOUT | Gas Turbine Generator |  |  |  | CABLE TRAY LAYOUT for GTG | Cable Tray | SKIP | 3CF1255W74A09.1 | (GTG#32 Electrical) Cable work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Electrical System | 2008-08-01 | 2008-09-15 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152018 | CABLE TRAY LAYOUT FOR TANK SLEEPER AREA | CABLE TRAY LAYOUT | Tank |  |  |  | CABLE TRAY LAYOUT for Tank | Cable Tray | SKIP | 2EF6040W16A01 | (Cable tunnel) Cable tunnel Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2008-01-01 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152019 | CABLE TRAY LAYOUT FOR DEAERATOR SUPPORT STRUCTURE | CABLE TRAY LAYOUT |  |  |  |  | CABLE TRAY LAYOUT | Cable Tray | SKIP | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD04-P0ZEN-152020 | CABLE TRAY LAYOUT FOR SECURITY BUILDING | CABLE TRAY LAYOUT |  |  | SECURITY BUILDING |  | CABLE TRAY LAYOUT for SECURITY BUILDING | Cable Tray | SKIP | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-152052 | CONTROL CABLE CONNECTION DIAGRAM | CABLE CONNECTION DIAGRAM |  |  |  |  | CABLE CONNECTION DIAGRAM | Substation | SKIP | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152201 | TYPICAL INSTALLATION DRAWING - LIGHTING AND SMALL POWER | DRAWING |  | Lighting & Small Power System |  |  | DRAWING for Lighting & Small Power System | Lighting&small PoWer System | SKIP | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0ZEN-152202 | TECHNICAL SPECIFICATION - LIGHTING AND SMALL POWER | TECHNICAL SPECIFICATION |  | Lighting & Small Power System |  |  | Technical Specification for Lighting & Small Power System | Lighting&small PoWer System | SKIP | 0EF6040W70A01 | (Lighting Equip) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System |  | 2007-05-30 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152203 | ILLUMINATION CALCULATION - CENTRAL CONTROL BUILDING | ILLUMINATION CALCULATION |  |  | CENTRAL CONTROL BUILDING |  | ILLUMINATION CALCULATION for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152204 | ILLUMINATION CALCULATION - GTG #1,2 LEB | ILLUMINATION CALCULATION | Gas Turbine Generator |  | Local Electrical Building |  | ILLUMINATION CALCULATION for GTG |  | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152205 | ILLUMINATION CALCULATION - GTG #3,4,5 LEB | ILLUMINATION CALCULATION | Gas Turbine Generator |  | Local Electrical Building |  | ILLUMINATION CALCULATION for GTG |  | FI | 3EF1200W16A02 | (GTG #31 LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152206 | ILLUMINATION CALCULATION - ST #1 LEB | CALCULATION |  |  | ST #1 Local Electrical Building |  | Calculation sheet for ST #1 Local Electrical Building | Electrical Building | FI | 1EF1200W00A01.1 | (GTG #11 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 LEB | 2007-05-31 |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152207 | ILLUMINATION CALCULATION - ST #2 LEB | CALCULATION |  |  | ST #2 Local Electrical Building |  | Calculation sheet for ST #2 Local Electrical Building | Electrical Building | FI | 2CF1200W74A08 | (GTG #21 LEB) Installation & Test - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2008-06-04 | 2008-08-04 |  |  |  | 2025-03-07 | 2025-04-06 | 2025-05-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152208 | ILLUMINATION CALCULATION - ST BUILDING | CALCULATION |  |  | ST BUILDING |  | Calculation sheet for ST BUILDING | ST BUILDING | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152209 | ILLUMINATION CALCULATION - FGS ELECTRICAL BUILDING | CALCULATION |  |  | FGS ELECTRICAL BUILDING |  | Calculation sheet for FGS ELECTRICAL BUILDING | Electrical Building | FI | 0CF6040W74A06.1 | (Electrical Cable) Cable Pulling for GTG LEB-GIS BLDG(Early Power) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2008-05-31 | 2008-07-15 |  |  |  | 2025-03-03 | 2025-04-02 | 2025-05-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152210 | ILLUMINATION CALCULATION - ADMINISTRATION | CALCULATION |  |  | ADMINISTRATION |  | Calculation sheet for ADMINISTRATION | ADMINISTRATION & SOCIAL BUILDING | FI | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152211 | ILLUMINATION CALCULATION - SECURITY BUILDING | CALCULATION |  |  | SECURITY BUILDING |  | Calculation sheet for SECURITY BUILDING | SECURITY BUILDING | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152212 | ILLUMINATION CALCULATION - MAIN GATE HOUSE | CALCULATION |  |  | MAIN GATE HOUSE |  | Calculation sheet for MAIN GATE HOUSE | MAIN GATE | FI | 0EF5570W16A01 | (Gate House) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152213 | ILLUMINATION CALCULATION - SUPPORT BUILDING | CALCULATION |  |  | SUPPORT BUILDING |  | Calculation sheet for SUPPORT BUILDING | SUPPORT BUILDING | FI | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152214 | ILLUMINATION CALCULATION - X-RAY SEARCHING ROOM | CALCULATION |  |  | X-RAY SEARCHING ROOM |  | Calculation sheet for X-RAY SEARCHING ROOM | Water Treatment System | FA | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | 2024-04-29 | 2024-05-29 | 2024-06-28 | 2024-07-13 | 2024-07-28 | 2024-08-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152215 | ILLUMINATION CALCULATION - MAIN GATE HOUSE SUNSHADE | CALCULATION |  |  | MAIN GATE HOUSE |  | Calculation sheet for MAIN GATE HOUSE | MAIN GATE | FI | 0EF5570W32A03 | (Gate House) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152216 | ILLUMINATION CALCULATION - FIRE BRIGADE & AUX. LEB | CALCULATION |  |  | FIRE BRIGADE & Auxiliary Local Electrical Building |  | Calculation sheet for FIRE BRIGADE & Auxiliary Local Electrical Building | FIRE BRIGADE | FI | 3CF1200W38A06 | (GTG #31 LEB) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2008-05-31 | 2008-07-04 |  |  |  | 2025-03-03 | 2025-04-02 | 2025-05-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152217 | ILLUMINATION CALCULATION - WORKSHOP & STORAGE BUILDING | CALCULATION |  |  | WORKSHOP & STORAGE BUILDING |  | Calculation sheet for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 0CF5560W24A20 | (M&E WORKSHOP LEB) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-10-06 | 2008-12-01 |  |  |  | 2025-07-09 | 2025-08-08 | 2025-09-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152218 | ILLUMINATION CALCULATION - H2, CO2, N2 STORAGE SHELTER | CALCULATION |  |  | H2, CO2, N2 STORAGE SHELTER |  | Calculation sheet for H2, CO2, N2 STORAGE SHELTER | Gas Storage Shelter | FI | 2EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 |  |  |  | 2024-09-04 | 2024-10-04 | 2024-11-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152219 | ILLUMINATION CALCULATION - AIR COMPRESSOR SHELTER | CALCULATION | AIR COMPRESSOR |  | AIR COMPRESSOR SHELTER |  | Calculation sheet for AIR COMPRESSOR | AIR COMPRESSOR | FI | 0EF3510W16A02 | (COMP Air Receiver TK Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-11-12 |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152220 | ILLUMINATION CALCULATION - DEAERATOR SUPPORT STRUCTURE | CALCULATION |  |  |  |  | Calculation sheet |  | FA | 3PF1610W20A03P | (HRSG #31 S/Structure & Casing) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Steel Structure & Casing | 2007-06-14 | 2008-04-02 | 2024-11-01 | 2024-12-01 | 2024-12-31 | 2025-01-15 | 2025-01-30 | 2025-02-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152221 | ILLUMINATION CALCULATION - FIRE WATER PUMP HOUSE | CALCULATION |  |  | FIRE WATER PUMP HOUSE |  | Calculation sheet for FIRE WATER PUMP HOUSE | Fire Water Pump House | FI | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152222 | ILLUMINATION CALCULATION - WWT & BULK CHEMICAL STORAGE TANK SHELTER | CALCULATION | Tank |  | WWT & BULK CHEMICAL STORAGE TANK SHELTER |  | Calculation sheet for Tank | Water Treatment System | FA | 0CF3010W24A08 | (DWP Chemical Storage Tank Shelter) Shelter Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2008-08-22 | 2008-10-13 | 2025-09-22 | 2025-10-22 | 2025-11-21 | 2025-12-06 | 2025-12-21 | 2026-01-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152223 | ILLUMINATION CALCULATION - WATER TREATMENT BUILDING | CALCULATION |  |  | WATER TREATMENT BUILDING |  | Calculation sheet for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0CF5534W24A10 | (DWP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2008-07-01 | 2008-09-18 |  |  |  | 2025-04-03 | 2025-05-03 | 2025-06-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152224 | ILLUMINATION CALCULATION - CPP & CPP REGENERATION BUILDING | CALCULATION |  |  | CPP & CPP REGENERATION BUILDING |  | Calculation sheet for CPP & CPP REGENERATION BUILDING | CPP Regeneration Building | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152225 | ILLUMINATION CALCULATION - CHEMICAL DOSING SHELTER FOR STG & HRSG | CALCULATION | Steam Turbine & Generator, Heat Recovery Steam Generator | Chemical dosing system |  |  | Calculation sheet for Steam Turbine & Generator, Heat Recovery Steam Generator |  | FA | 1PF3045W42A03P | (Chemical Dosing Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-07-24 | 2025-03-09 | 2025-04-08 | 2025-05-08 | 2025-05-23 | 2025-06-07 | 2025-06-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152226 | ILLUMINATION CALCULATION - CHEMICAL DOSING SHELTER FOR HRSG | CALCULATION | Heat Recovery Steam Generator | Chemical dosing system |  |  | Calculation sheet for HRSG |  | FA | 1PF3045W42A03P | (Chemical Dosing Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-07-24 | 2025-03-09 | 2025-04-08 | 2025-05-08 | 2025-05-23 | 2025-06-07 | 2025-06-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152229 | ILLUMINATION CALCULATION - YARD | CALCULATION |  |  |  |  | Calculation sheet |  | FA | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | 2024-12-19 | 2025-01-18 | 2025-02-17 | 2025-03-04 | 2025-03-19 | 2025-04-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152230 | ILLUMINATION CALCULATION – TANK AREA | CALCULATION | Tank |  |  |  | Calculation sheet for Tank | Water Treatment System | FA | 0PF3520W68A04P | (Condensate Tank) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-07-01 | 2024-07-31 | 2024-08-30 | 2024-09-14 | 2024-09-29 | 2024-10-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152231 | ILLUMINATION CALCULATION – GTG #1, 2 TRANSFORMER AREA | CALCULATION | Gas Turbine Generator |  |  |  | Calculation sheet for GTG |  | FI | 2EF6500W00A09 | (GTG #21 & UAT Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152232 | ILLUMINATION CALCULATION – GTG #3, 4, 5 TRANSFORMER AREA | CALCULATION | Gas Turbine Generator |  |  |  | Calculation sheet for GTG |  | FI | 3CF6500W70A06 | (GTG TR) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Power Transformer | 2008-08-01 | 2008-09-16 |  |  |  | 2025-05-04 | 2025-06-03 | 2025-07-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152233 | ILLUMINATION CALCULATION – STG #1, 2 TRANSFORMER AREA | CALCULATION | Steam Turbine & Generator |  |  |  | Calculation sheet for STG |  | FI | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 |  |  |  | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152234 | ILLUMINATION CALCULATION – FUEL GAS SYSTEM AREA | CALCULATION |  | Fuel Gas System |  |  | Calculation sheet for Fuel Gas System | Fuel Gas System | FA | 0PF3520W42A04.2P | (Flare cum incinerator) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Flare Cum Incinerator | 2007-06-01 | 2008-03-03 | 2024-10-19 | 2024-11-16 | 2024-12-14 | 2024-12-07 | 2025-01-04 | 2025-02-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152301 | LIGHTING & SMALL POWER LAYOUT DRAWING - CENTRAL CONTROL BUILDING | LAYOUT DRAWING |  | Lighting & Small Power System | CENTRAL CONTROL BUILDING |  | Layout Drawing for Lighting & Small Power System | Substation | SKIP | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152302 | LIGHTING & SMALL POWER LAYOUT DRAWING - GTG #1,2 LEB | LAYOUT DRAWING |  | Lighting & Small Power System | Local Electrical Building |  | Layout Drawing for Lighting & Small Power System | Substation | SKIP | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152303 | LIGHTING & SMALL POWER LAYOUT DRAWING - GTG #3,4,5 LEB | LAYOUT DRAWING |  | Lighting & Small Power System | Local Electrical Building |  | Layout Drawing for Lighting & Small Power System | Substation | SKIP | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152304 | LIGHTING & SMALL POWER LAYOUT DRAWING - ST #1 LEB | LAYOUT DRAWING |  | Lighting & Small Power System | Local Electrical Building |  | Layout Drawing for Lighting & Small Power System | Substation | SKIP | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152305 | LIGHTING & SMALL POWER LAYOUT DRAWING - ST #2 LEB | LAYOUT DRAWING |  | Lighting & Small Power System | Local Electrical Building |  | Layout Drawing for Lighting & Small Power System | Substation | SKIP | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152306 | LIGHTING & SMALL POWER LAYOUT DRAWING - ST BUILDING | LAYOUT DRAWING |  | Lighting & Small Power System | ST Building |  | Layout Drawing for Lighting & Small Power System | Substation | SKIP | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152307 | LIGHTING & SMALL POWER LAYOUT DRAWING - FGS ELECTRICAL BUILDING | LAYOUT DRAWING |  | Lighting & Small Power System | ELECTRICAL BUILDING |  | Layout Drawing for Lighting & Small Power System | Substation | SKIP | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152308 | LIGHTING & SMALL POWER LAYOUT DRAWING - ADMINISTRATION | LAYOUT DRAWING |  | Lighting & Small Power System | Administration Building |  | Layout Drawing for Lighting & Small Power System | Substation | SKIP | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152309 | LIGHTING & SMALL POWER LAYOUT DRAWING - SECURITY BUILDING | LAYOUT DRAWING |  | Lighting & Small Power System | SECURITY BUILDING |  | Layout Drawing for Lighting & Small Power System | Substation | SKIP | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152310 | LIGHTING & SMALL POWER LAYOUT DRAWING - MAIN GATE HOUSE | LAYOUT DRAWING |  | Lighting & Small Power System | Gate House |  | Layout Drawing for Lighting & Small Power System | Substation | SKIP | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152311 | LIGHTING & SMALL POWER LAYOUT DRAWING - SUPPORT BUILDING | LAYOUT DRAWING |  | Lighting & Small Power System | Support Building |  | Layout Drawing for Lighting & Small Power System | Substation | SKIP | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152312 | LIGHTING & SMALL POWER LAYOUT DRAWING - X-RAY SEARCHING ROOM | LAYOUT DRAWING |  | Lighting & Small Power System | Room |  | Layout Drawing for Lighting & Small Power System | Substation | SKIP | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152313 | LIGHTING & SMALL POWER LAYOUT DRAWING - MAIN GATE HOUSE SUNSHADE | LAYOUT DRAWING |  | Lighting & Small Power System | Gate House |  | Layout Drawing for Lighting & Small Power System | Substation | SKIP | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152314 | LIGHTING & SMALL POWER LAYOUT DRAWING - FIRE BRIGADE & AUX. LEB | LAYOUT DRAWING |  | LIGHTING & SMALL POWER | FIRE BRIGADE & Auxiliary Local Electrical Building |  | Layout Drawing for LIGHTING & SMALL POWER | Substation | SKIP | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152315 | LIGHTING & SMALL POWER LAYOUT DRAWING - WORKSHOP & STORAGE BUILDING | LAYOUT DRAWING |  | LIGHTING & SMALL POWER | WORKSHOP & STORAGE BUILDING |  | Layout Drawing for LIGHTING & SMALL POWER | Substation | SKIP | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152316 | LIGHTING & SMALL POWER LAYOUT DRAWING - H2, CO2, N2 STORAGE SHELTER | LAYOUT DRAWING |  | LIGHTING & SMALL POWER | H2, CO2, N2 STORAGE SHELTER |  | Layout Drawing for LIGHTING & SMALL POWER | Substation | SKIP | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152317 | LIGHTING & SMALL POWER LAYOUT DRAWING - AIR COMPRESSOR SHELTER | LAYOUT DRAWING | Air Compressor | LIGHTING & SMALL POWER | AIR COMPRESSOR SHELTER |  | Layout Drawing for Air Compressor | Air Compressor | FA | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152318 | LIGHTING & SMALL POWER LAYOUT DRAWING - DEAERATOR SUPPORT STRUCTURE | LAYOUT DRAWING |  | LIGHTING & SMALL POWER |  |  | Layout Drawing for LIGHTING & SMALL POWER | Substation | SKIP | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152319 | LIGHTING & SMALL POWER LAYOUT DRAWING - FIRE WATER PUMP HOUSE | LAYOUT DRAWING |  | LIGHTING & SMALL POWER | FIRE WATER PUMP HOUSE |  | Layout Drawing for LIGHTING & SMALL POWER | Substation | SKIP | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152320 | LIGHTING & SMALL POWER LAYOUT DRAWING - WWT & BULK CHEMICAL STORAGE TANK SHELTER | LAYOUT DRAWING | Tank | LIGHTING & SMALL POWER | WWT & BULK CHEMICAL STORAGE TANK SHELTER |  | Layout Drawing for Tank | shop Tank | FA | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 | 2024-09-14 | 2024-10-14 | 2024-11-13 | 2024-11-28 | 2024-12-13 | 2024-12-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152321 | LIGHTING & SMALL POWER LAYOUT DRAWING - WATER TREATMENT BUILDING | LAYOUT DRAWING |  | LIGHTING & SMALL POWER | WATER TREATMENT BUILDING |  | Layout Drawing for LIGHTING & SMALL POWER | Substation | SKIP | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152322 | LIGHTING & SMALL POWER LAYOUT DRAWING - CPP & CPP REGENERATION BUILDING | LAYOUT DRAWING |  | LIGHTING & SMALL POWER | CPP & CPP REGENERATION BUILDING |  | Layout Drawing for LIGHTING & SMALL POWER | Substation | SKIP | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152323 | LIGHTING & SMALL POWER LAYOUT DRAWING - CHEMICAL DOSING SHELTER FOR STG & HRSG | LAYOUT DRAWING | Steam Turbine & Generator, Heat Recovery Steam Generator | LIGHTING & SMALL POWER | CHEMICAL DOSING SHELTER |  | Layout Drawing for Steam Turbine & Generator, Heat Recovery Steam Generator | STEAM TURBINE GENERATOR | FA | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 |  |  |  | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152324 | LIGHTING & SMALL POWER LAYOUT DRAWING - CHEMICAL DOSING SHELTER FOR HRSG | LAYOUT DRAWING | Heat Recovery Steam Generator | LIGHTING & SMALL POWER | CHEMICAL DOSING SHELTER |  | Layout Drawing for HRSG |  | FA | 1PF1600W74A06.1P | (HRSG #12 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | 2007-09-15 | 2008-07-10 | 2025-05-28 | 2025-06-27 | 2025-07-27 | 2025-08-11 | 2025-08-26 | 2025-09-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152327 | LIGHTING & SMALL POWER LAYOUT DRAWING - YARD | LAYOUT DRAWING |  | LIGHTING & SMALL POWER |  |  | Layout Drawing for LIGHTING & SMALL POWER | Substation | SKIP | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152328 | LIGHTING & SMALL POWER LAYOUT DRAWING – TANK AREA | LAYOUT DRAWING | Tank | LIGHTING & SMALL POWER |  |  | Layout Drawing for Tank | shop Tank | FA | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | 2024-08-15 | 2024-09-14 | 2024-10-14 | 2024-10-29 | 2024-11-13 | 2024-11-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152329 | LIGHTING & SMALL POWER LAYOUT DRAWING – GTG #1, 2 TRANSFORMER AREA | LAYOUT DRAWING | Gas Turbine Generator | LIGHTING & SMALL POWER |  |  | Layout Drawing for GTG | Substation | SKIP | 1PF6500W70A04P | (GTG TR) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-04-02 | 2008-04-15 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152330 | LIGHTING & SMALL POWER LAYOUT DRAWING – GTG #3, 4, 5 TRANSFORMER AREA | LAYOUT DRAWING | Gas Turbine Generator | LIGHTING & SMALL POWER |  |  | Layout Drawing for GTG | Substation | SKIP | 3PF6500W70A04P | (GTG TR) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Power Transformer | 2007-04-02 | 2008-06-16 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152331 | LIGHTING & SMALL POWER LAYOUT DRAWING – STG #1, 2 TRANSFORMER AREA | LAYOUT DRAWING | Steam Turbine & Generator | LIGHTING & SMALL POWER |  |  | Layout Drawing for STG | Substation | SKIP | 1PF6500W70A07P | (STG #10 & UST Shelter) P.O & Procurement - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-06-29 | 2008-06-22 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152332 | LIGHTING & SMALL POWER LAYOUT DRAWING – FUEL GAS SYSTEM AREA | LAYOUT DRAWING |  | Fuel Gas System |  |  | Layout Drawing for Fuel Gas System | Fuel Gas System | FA | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | 2024-11-21 | 2025-01-16 | 2025-03-13 | 2025-02-06 | 2025-04-03 | 2025-05-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YQ01-P0ZEN-152333 | LIGHTING & SMALL POWER LAYOUT DRAWING – WELDING SHED AND CONTAINER AT OPEN STORAGE AREA | LAYOUT DRAWING |  | LIGHTING & SMALL POWER |  |  | Layout Drawing for LIGHTING & SMALL POWER | Substation | SKIP | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152401 | LIGHTING PANEL BOARD SCHEDULE - CENTRAL CONTROL BUILDING | SCHEDULE |  | LIGHTING | CENTRAL CONTROL BUILDING |  | Schedule for LIGHTING |  | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 | 2024-03-03 | 2024-04-02 | 2024-05-02 | 2024-05-17 | 2024-06-01 | 2024-06-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152402 | LIGHTING PANEL BOARD SCHEDULE - GTG #1,2 LEB | SCHEDULE | Gas Turbine Generator | LIGHTING | Local Electrical Building |  | Schedule for GTG |  | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152403 | LIGHTING PANEL BOARD SCHEDULE - GTG #3,4,5 LEB | SCHEDULE | Gas Turbine Generator |  | Local Electrical Building |  | Schedule for GTG |  | FA | 3EF1200W32A04 | (GTG #31 LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152404 | LIGHTING PANEL BOARD SCHEDULE - ST #1 LEB | SCHEDULE | Steam Turbine |  | Local Electrical Building |  | Schedule for STG |  | FA | 1PF2020W42A10P | (ST #10) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2008-09-01 | 2024-09-04 | 2024-10-04 | 2024-11-03 | 2024-11-18 | 2024-12-03 | 2024-12-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152405 | LIGHTING PANEL BOARD SCHEDULE - ST #2 LEB | SCHEDULE | Steam Turbine |  | Local Electrical Building |  | Schedule for STG |  | FA | 2PF2020W42A10P | (ST #20) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-03-01 | 2008-10-01 | 2024-09-04 | 2024-10-04 | 2024-11-03 | 2024-11-18 | 2024-12-03 | 2024-12-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152406 | LIGHTING PANEL BOARD SCHEDULE - ST BUILDING | SCHEDULE |  |  | ST BUILDING |  | Schedule for ST BUILDING | ST BUILDING | FI | 0PF6040W70A03T | (Lighting Equip) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-02-28 | 2008-04-12 | 2025-07-28 | 2025-08-27 | 2025-09-26 | 2025-10-11 | 2025-10-26 | 2025-11-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152407 | LIGHTING PANEL BOARD SCHEDULE - FGS ELECTRICAL BUILDING | SCHEDULE |  | Fuel Gas System | ELECTRICAL BUILDING |  | Schedule for Fuel Gas System | Fuel Gas System | FA | 0CF3520W24A10.1 | (FGS LEB) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2008-05-31 | 2008-07-28 | 2025-06-15 | 2025-07-20 | 2025-08-24 | 2025-08-10 | 2025-09-14 | 2025-10-19 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152408 | LIGHTING PANEL BOARD SCHEDULE - ADMINISTRATION | SCHEDULE |  |  |  |  | Schedule |  | FI | 0CF6040W70A04 | (Lighting Equip) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-04-14 | 2008-06-30 | 2025-03-16 | 2025-04-15 | 2025-05-15 | 2025-05-30 | 2025-06-14 | 2025-06-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152409 | LIGHTING PANEL BOARD SCHEDULE - SECURITY BUILDING | SCHEDULE |  |  | SECURITY BUILDING |  | Schedule for SECURITY BUILDING |  | FA | 0PF6040W70A03T | (Lighting Equip) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-02-28 | 2008-04-12 | 2026-06-23 | 2026-07-23 | 2026-08-22 | 2026-09-06 | 2026-09-21 | 2026-10-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152411 | LIGHTING PANEL BOARD SCHEDULE - SUPPORT BUILDING | SCHEDULE |  |  | SUPPORT BUILDING |  | Schedule for SUPPORT BUILDING |  | FA | 0PF6040W70A03T | (Lighting Equip) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-02-28 | 2008-04-12 | 2026-09-21 | 2026-10-21 | 2026-11-20 | 2026-12-05 | 2026-12-20 | 2027-01-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152414 | LIGHTING PANEL BOARD SCHEDULE - FIRE BRIGADE & AUX. LEB | SCHEDULE |  |  | FIRE BRIGADE & Auxiliary Local Electrical Building |  | Schedule for FIRE BRIGADE & Auxiliary Local Electrical Building | FIRE BRIGADE | FI | 0CF6040W70A04 | (Lighting Equip) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-04-14 | 2008-06-30 |  |  |  | 2025-01-15 | 2025-02-14 | 2025-03-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152415 | LIGHTING PANEL BOARD SCHEDULE - WORKSHOP & STORAGE BUILDING | SCHEDULE |  |  | WORKSHOP & STORAGE BUILDING |  | Schedule for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 0CF6040W70A04 | (Lighting Equip) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-04-14 | 2008-06-30 |  |  |  | 2025-01-15 | 2025-02-14 | 2025-03-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152418 | LIGHTING PANEL BOARD SCHEDULE - DEAERATOR SUPPORT STRUCTURE | SCHEDULE |  |  |  |  | Schedule |  | FI | 0CF6040W70A04 | (Lighting Equip) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-04-14 | 2008-06-30 | 2025-03-16 | 2025-04-15 | 2025-05-15 | 2025-05-30 | 2025-06-14 | 2025-06-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152419 | LIGHTING PANEL BOARD SCHEDULE - FIRE WATER PUMP HOUSE | SCHEDULE |  |  | FIRE WATER PUMP HOUSE |  | Schedule for FIRE WATER PUMP HOUSE | Fire Water Pump House | FI | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152421 | LIGHTING PANEL BOARD SCHEDULE - WATER TREATMENT BUILDING | SCHEDULE |  |  | WATER TREATMENT BUILDING |  | Schedule for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0CF6040W70A04 | (Lighting Equip) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-04-14 | 2008-06-30 |  |  |  | 2025-01-15 | 2025-02-14 | 2025-03-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152422 | LIGHTING PANEL BOARD SCHEDULE - CPP & CPP REGENERATION BUILDING | SCHEDULE |  |  |  |  | Schedule |  | FI | 0CF6040W70A04 | (Lighting Equip) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-04-14 | 2008-06-30 | 2025-03-16 | 2025-04-15 | 2025-05-15 | 2025-05-30 | 2025-06-14 | 2025-06-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152427 | LIGHTING PANEL BOARD SCHEDULE - YARD | SCHEDULE |  |  |  |  | Schedule |  | FI | 0PF6040W70A03T | (Lighting Equip) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-02-28 | 2008-04-12 | 2025-01-29 | 2025-02-28 | 2025-03-30 | 2025-04-14 | 2025-04-29 | 2025-05-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB11-P0ZEN-152428 | LIGHTING PANEL BOARD SCHEDULE – TANK AREA | SCHEDULE |  |  |  |  | Schedule |  | FI | 0PF6040W70A03T | (Lighting Equip) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-02-28 | 2008-04-12 | 2025-01-29 | 2025-02-28 | 2025-03-30 | 2025-04-14 | 2025-04-29 | 2025-05-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE04-P0BAU-152501 | TYPICAL INSTALLATION DRAWING - EARTHING AND LIGHTNING PROTECTION | DRAWING |  | Earthing & Lightning Protection System |  |  | DRAWING for Earthing & Lightning Protection System | Earthing & Lightning Protection | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0BAU-152502 | TECHNICAL SPECIFICATION - EARTHING AND LIGHTNING PROTECTION SYSTEM | TECHNICAL SPECIFICATION |  | Earthing & Lightning Protection System |  |  | Technical Specification for Earthing & Lightning Protection System | Earthing & Lightning Protection | SKIP | 0EF6040W80A01 | (Earthing & Lightning Material) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials |  | 2007-05-30 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0BAU-152503 | MAIN EARTHING GRID CALCULATION | CALCULATION |  |  |  |  | Calculation sheet |  | FA | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | 2025-01-04 | 2025-02-03 | 2025-03-05 | 2025-03-20 | 2025-04-04 | 2025-04-19 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152504 | EARTHING LAYOUT DRAWING - MAIN GRID | LAYOUT DRAWING |  |  |  |  | Layout Drawing | Substation | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152505 | EARTHING LAYOUT DRAWING - CENTRAL CONTROL BUILDING | LAYOUT DRAWING |  | Earthing & Lightning Protection System | CENTRAL CONTROL BUILDING |  | Layout Drawing for Earthing & Lightning Protection System | Substation | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152506 | EARTHING LAYOUT DRAWING - GTG #1,2 LEB | LAYOUT DRAWING | Gas Turbine Generator | Earthing & Lightning Protection System | GTG #1,2 Local Electrical Building |  | Layout Drawing for GTG | Substation | SKIP | 0CF6040W80A04 | (Earthing & Lightning Material) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2008-01-29 | 2008-08-01 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152507 | EARTHING LAYOUT DRAWING - GTG #3,4,5 LEB | LAYOUT DRAWING | Gas Turbine Generator | Earthing & Lightning Protection System | GTG #3,4,5 Local Electrical Building |  | Layout Drawing for GTG | Substation | SKIP | 0CF6040W80A04 | (Earthing & Lightning Material) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2008-01-29 | 2008-08-01 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P6BAU-152508 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - ST #1 LEB | LAYOUT DRAWING | Steam Turbine | Earthing & Lightning Protection System | ST #1 Local Electrical Building |  | Layout Drawing for STG | Substation | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P7BAU-152509 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - ST #2 LEB | LAYOUT DRAWING | Steam Turbine | Earthing & Lightning Protection System | ST #2 Local Electrical Building |  | Layout Drawing for STG | Substation | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152510 | EARTHING LAYOUT DRAWING - ST BUILDING | LAYOUT DRAWING |  | Earthing & Lightning Protection System | ST BUILDING |  | Layout Drawing for Earthing & Lightning Protection System | Substation | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152511 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - FGS ELECTRICAL BUILDING | LAYOUT DRAWING |  | Earthing & Lightning Protection System | Fuel Gas System ELECTRICAL BUILDING |  | Layout Drawing for Earthing & Lightning Protection System | Substation | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152512 | EARTHING LAYOUT DRAWING - ADMINISTRATION & SOCIAL BUILDING | LAYOUT DRAWING |  | Earthing & Lightning Protection System | ADMINISTRATION & SOCIAL BUILDING |  | Layout Drawing for Earthing & Lightning Protection System | Substation | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152513 | EARTHING LAYOUT DRAWING - SECURITY BUILDING | LAYOUT DRAWING |  | Earthing & Lightning Protection System | SECURITY BUILDING |  | Layout Drawing for Earthing & Lightning Protection System | Substation | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152514 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - GATE HOUSE | LAYOUT DRAWING |  | Earthing & Lightning Protection System | GATE HOUSE |  | Layout Drawing for Earthing & Lightning Protection System | Substation | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152515 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - SUPPORT BUILDING | LAYOUT DRAWING |  | Earthing & Lightning Protection System | SUPPORT BUILDING |  | Layout Drawing for Earthing & Lightning Protection System | Substation | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152516 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - SEARCH FACILITY AND VISITORS CENTRE | LAYOUT DRAWING |  | Earthing & Lightning Protection System | SEARCH FACILITY AND VISITORS CENTRE |  | Layout Drawing for Earthing & Lightning Protection System | Substation | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152517 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - FIRE BRIGADE | LAYOUT DRAWING |  | Earthing & Lightning Protection System | FIRE BRIGADE |  | Layout Drawing for Earthing & Lightning Protection System | Substation | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152518 | EARTHING LAYOUT DRAWING - WORKSHOP & STORAGE BUILDING | LAYOUT DRAWING |  | Earthing & Lightning Protection System | WORKSHOP & STORAGE BUILDING |  | Layout Drawing for Earthing & Lightning Protection System | Substation | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152519 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - N2 STORAGE SHELTER | LAYOUT DRAWING |  | Earthing & Lightning Protection System | N2 STORAGE SHELTER |  | Layout Drawing for Earthing & Lightning Protection System | Substation | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152520 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - AIR COMPRESSOR SHELTER | LAYOUT DRAWING | Air Compressor | Earthing & Lightning Protection System | AIR COMPRESSOR SHELTER |  | Layout Drawing for Air Compressor | Air Compressor | FA | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | 2024-10-12 | 2024-11-11 | 2024-12-11 | 2024-12-26 | 2025-01-10 | 2025-01-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152521 | EARTHING LAYOUT DRAWING - DEAERATOR SUPPORT STRUCTURE | LAYOUT DRAWING |  | Earthing & Lightning Protection System |  |  | Layout Drawing for Earthing & Lightning Protection System | Substation | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152522 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - FIRE WATER PUMP HOUSE | LAYOUT DRAWING |  | Earthing & Lightning Protection System | FIRE WATER PUMP HOUSE |  | Layout Drawing for Earthing & Lightning Protection System | Substation | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152523 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - WWT & BULK CHEMICAL STORAGE TANK SHELTER | LAYOUT DRAWING | Tank | Earthing & Lightning Protection System | WWT & BULK CHEMICAL STORAGE TANK SHELTER |  | Layout Drawing for Tank | shop Tank | FA | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | 2024-08-31 | 2024-09-30 | 2024-10-30 | 2024-11-14 | 2024-11-29 | 2024-12-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152524 | EARTHING LAYOUT DRAWING - WATER TREATMENT BUILDING | LAYOUT DRAWING |  | Earthing & Lightning Protection System | WATER TREATMENT BUILDING |  | Layout Drawing for Earthing & Lightning Protection System | Substation | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152525 | EARTHING LAYOUT DRAWING - CPP & CPP REGENERATION BUILDING | LAYOUT DRAWING |  |  | CPP & CPP REGENERATION BUILDING |  | Layout Drawing for CPP & CPP REGENERATION BUILDING | CPP Regeneration Building | FI | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152526 | EARTHING LAYOUT DRAWING - PIPE RACK FOR HRSG | LAYOUT DRAWING | Heat Recovery Steam Generator |  | PIPE RACK |  | Layout Drawing for HRSG |  | FA | 1PF1600W74A06.1P | (HRSG #12 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | 2007-09-15 | 2008-07-10 | 2025-05-28 | 2025-06-27 | 2025-07-27 | 2025-08-11 | 2025-08-26 | 2025-09-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152527 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - AUX. LEB | LAYOUT DRAWING |  | EARTHING & LIGHTNING PROTECTION | Auxiliary Local Electrical Building |  | Layout Drawing for EARTHING & LIGHTNING PROTECTION | Substation | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152528 | EARTHING LAYOUT DRAWING - TANK AREA | LAYOUT DRAWING | Tank |  |  |  | Layout Drawing for Tank | shop Tank | FA | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | 2024-08-31 | 2024-09-30 | 2024-10-30 | 2024-11-14 | 2024-11-29 | 2024-12-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152529 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - GTG & TR #1,2 AREA | LAYOUT DRAWING | Gas Turbine Generator | EARTHING & LIGHTNING PROTECTION |  |  | Layout Drawing for GTG | Substation | SKIP | 2CF1255W70A05.1 | (GTG#22 Electrical) Installation- Protection Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Electrical System | 2008-08-01 | 2008-09-15 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152530 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - GTG & TR #3,4,5 AREA | LAYOUT DRAWING | Gas Turbine Generator | EARTHING & LIGHTNING PROTECTION |  |  | Layout Drawing for GTG | Substation | SKIP | 3CF1255W70A05 | (GTG#31 Electrical) Installation- Protection Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Electrical System | 2008-08-01 | 2008-09-15 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152531 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - STG TR AREA | LAYOUT DRAWING | Steam Turbine & Generator | EARTHING & LIGHTNING PROTECTION |  |  | Layout Drawing for STG | Substation | SKIP | 1PF6500W70A07P | (STG #10 & UST Shelter) P.O & Procurement - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-06-29 | 2008-06-22 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152532 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - AIR COOLED CONDENSER-1 | LAYOUT DRAWING | AIR COOLED CONDENSER-1 | EARTHING & LIGHTNING PROTECTION |  |  | Layout Drawing for AIR COOLED CONDENSER-1 | CONDENSER | FA | 0PF6040W80A03T | (Earthing & Lightning Material) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-12-19 | 2008-01-28 |  |  |  | 2024-09-20 | 2024-10-20 | 2024-11-19 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152533 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - AIR COOLED CONDENSER-2 | LAYOUT DRAWING | AIR COOLED CONDENSER-2 | EARTHING & LIGHTNING PROTECTION |  |  | Layout Drawing for AIR COOLED CONDENSER-2 | CONDENSER | FA | 0PF6040W80A03T | (Earthing & Lightning Material) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-12-19 | 2008-01-28 |  |  |  | 2024-09-20 | 2024-10-20 | 2024-11-19 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152534 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - FIN FAN COOLER & CCW PUMP AREA | LAYOUT DRAWING | Fin Fan Cooler & Closed Cooling Water Pump | EARTHING & LIGHTNING PROTECTION |  |  | Layout Drawing for Fin Fan Cooler & Closed Cooling Water Pump | CCW FIN FAN COOLER | FA | 1EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | 2007-07-03 | 2007-11-29 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152535 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - FGS AREA |  |  | Fuel Gas System |  |  | for Fuel Gas System | Fuel Gas System | FA | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | 2024-08-31 | 2024-10-05 | 2024-11-09 | 2024-10-26 | 2024-11-30 | 2025-01-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152536 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - BLACK START DIESEL GENERATOR AREA | LAYOUT DRAWING | Blackstart Diesel Generator | EARTHING & LIGHTNING PROTECTION |  |  | Layout Drawing for Blackstart Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | FA | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | 2024-10-12 | 2024-11-11 | 2024-12-11 | 2024-12-26 | 2025-01-10 | 2025-01-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152537 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - H2, CO2 STORAGE SHELTER | LAYOUT DRAWING |  | EARTHING & LIGHTNING PROTECTION | H2/CO2 Shelter |  | Layout Drawing for EARTHING & LIGHTNING PROTECTION | Substation | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152538 | EARTHING LAYOUT DRAWING - 380kV EHV CABLE INSULATION JOINT AREA | LAYOUT DRAWING |  |  |  |  | Layout Drawing | Substation | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152539 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - CHEMICAL DOSING SYSTEM | LAYOUT DRAWING |  | Chemical dosing system |  |  | Layout Drawing for Chemical dosing system | Chemical Dosing System | FA | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE03-P0BAU-152540 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - PRELIMINARY INSPECTION CHECK POINT (PIC) | LAYOUT DRAWING |  |  |  |  | Layout Drawing | Substation | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152600 | LIGHTNING PROTECTION LAYOUT DRAWING - OVERALL AREA | LAYOUT DRAWING |  | LIGHTNING PROTECTION |  |  | Layout Drawing for LIGHTNING PROTECTION | Substation | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152601 | LIGHTNING PROTECTION LAYOUT DRAWING - CENTRAL CONTROL BUILDING | LAYOUT DRAWING |  | LIGHTNING PROTECTION | CENTRAL CONTROL BUILDING |  | Layout Drawing for LIGHTNING PROTECTION | Substation | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152602 | LIGHTNING PROTECTION LAYOUT DRAWING - GTG #1,2 LEB | LAYOUT DRAWING | Gas Turbine Generator | LIGHTNING PROTECTION | Local Electrical Building |  | Layout Drawing for GTG | Substation | SKIP | 2CF1255W70A05.1 | (GTG#22 Electrical) Installation- Protection Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Electrical System | 2008-08-01 | 2008-09-15 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152603 | LIGHTNING PROTECTION LAYOUT DRAWING - GTG #3,4,5 LEB | LAYOUT DRAWING | Gas Turbine Generator | LIGHTNING PROTECTION | Local Electrical Building |  | Layout Drawing for GTG | Substation | SKIP | 3CF1255W70A05 | (GTG#31 Electrical) Installation- Protection Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Electrical System | 2008-08-01 | 2008-09-15 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152606 | LIGHTNING PROTECTION LAYOUT DRAWING - ST BUILDING | LAYOUT DRAWING |  | Lightning Protection System | ST Building |  | Layout Drawing for Lightning Protection System | Substation | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152608 | LIGHTNING PROTECTION LAYOUT DRAWING - ADMINISTRATION & SOCIAL BUILDING | LAYOUT DRAWING |  | Lightning Protection System | ADMINISTRATION & SOCIAL BUILDING |  | Layout Drawing for Lightning Protection System | Substation | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152609 | LIGHTNING PROTECTION LAYOUT DRAWING - SECURITY BUILDING | LAYOUT DRAWING |  | Lightning Protection System | SECURITY BUILDING |  | Layout Drawing for Lightning Protection System | Substation | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152614 | LIGHTNING PROTECTION LAYOUT DRAWING - WORKSHOP & STORAGE BUILDING | LAYOUT DRAWING |  | Lightning Protection System | WORKSHOP & STORAGE BUILDING |  | Layout Drawing for Lightning Protection System | Substation | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152620 | LIGHTNING PROTECTION LAYOUT DRAWING - WATER TREATMENT BUILDING | LAYOUT DRAWING |  | Lightning Protection System | WATER TREATMENT BUILDING |  | Layout Drawing for Lightning Protection System | Substation | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE01-P0BAU-152621 | LIGHTNING PROTECTION LAYOUT DRAWING - CPP & CPP REGENERATION BUILDING | LAYOUT DRAWING |  | Lightning Protection System | CPP & CPP REGENERATION BUILDING |  | Layout Drawing for Lightning Protection System | Substation | SKIP | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0ZEN-152701 | TECHNICAL SPECIFICATION - PVC CONDUIT AND ACCESSORIES | TECHNICAL SPECIFICATION |  |  |  |  | Technical Specification |  | FA | 0EF6020W58A10 | (Piping Insulation) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement |  | 2007-07-30 | [6 empty] | missing_date |  | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0ZEN-152702 | TECHNICAL SPECIFICATION - STEEL CONDUIT AND ACCESSORIES | TECHNICAL SPECIFICATION |  |  |  |  | Technical Specification |  | FA | 3PF1610W20A03.1 | (HRSG #32 S/Structure & Casing) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Steel Structure & Casing | 2007-06-14 | 2008-04-02 | 2024-06-28 | 2024-07-28 | 2024-08-27 | 2024-09-11 | 2024-09-26 | 2024-10-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152705 | EMBEDDED CONDUIT LAYOUT FOR ST #1 LEB | LAYOUT |  |  | ST #1 Local Electrical Building |  | Layout Drawing for ST #1 Local Electrical Building | ST BUILDING | FI | 1EF1200W00A01.1 | (GTG #11 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 LEB | 2007-05-31 |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152706 | EMBEDDED CONDUIT LAYOUT FOR ST #2 LEB | LAYOUT |  |  | ST #2 Local Electrical Building |  | Layout Drawing for ST #2 Local Electrical Building | ST BUILDING | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152707 | EMBEDDED CONDUIT LAYOUT FOR ST BUILDING | LAYOUT |  |  | ST BUILDING |  | Layout Drawing for ST BUILDING | ST BUILDING | FI | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152708 | EMBEDDED CONDUIT LAYOUT FOR FGS ELECTRICAL BUILDING | LAYOUT |  |  | Fuel Gas System ELECTRICAL BUILDING |  | Layout Drawing for Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | 2024-08-07 | 2024-09-18 | 2024-10-30 | 2024-10-09 | 2024-11-20 | 2025-01-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152709 | EMBEDDED CONDUIT LAYOUT FOR ADMINISTRATION & SOCIAL BUILDING | LAYOUT |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Layout Drawing for ADMINISTRATION & SOCIAL BUILDING |  | FA | 0EF5566W00A01 | (ADMIN BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 |  | 2025-08-22 | 2025-09-21 | 2025-10-21 | 2025-11-05 | 2025-11-20 | 2025-12-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152710 | EMBEDDED CONDUIT LAYOUT FOR SECURITY BUILDING | LAYOUT |  |  | SECURITY BUILDING |  | Layout Drawing for SECURITY BUILDING |  | FA | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | 2025-07-23 | 2025-08-22 | 2025-09-21 | 2025-10-06 | 2025-10-21 | 2025-11-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152711 | EMBEDDED CONDUIT LAYOUT FOR MAIN GATE HOUSE AREA | LAYOUT |  |  | MAIN GATE HOUSE AREA |  | Layout Drawing for MAIN GATE HOUSE AREA | MAIN GATE | FI | 0EF5570W32A03 | (Gate House) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152715 | EMBEDDED CONDUIT LAYOUT FOR FIRE BRIGADE | LAYOUT |  |  | FIRE BRIGADE |  | Layout Drawing for FIRE BRIGADE | FIRE BRIGADE | FI | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152716 | EMBEDDED CONDUIT LAYOUT FOR WORKSHOP & STORAGE BUILDING | LAYOUT |  |  | WORKSHOP & STORAGE BUILDING |  | Layout Drawing for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 0EF5560W00A01 | (M&E WORKSHOP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 |  |  |  |  | 2024-08-31 | 2024-09-30 | 2024-10-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152717 | EMBEDDED CONDUIT LAYOUT FOR H2, CO2, N2 STORAGE SHELTER | LAYOUT |  |  | H2, CO2, Nitrogen STORAGE SHELTER |  | Layout Drawing for H2, CO2, Nitrogen STORAGE SHELTER | Gas Storage Shelter | FI | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152718 | EMBEDDED CONDUIT LAYOUT FOR AIR COMPRESSOR SHELTER | LAYOUT |  |  | AIR COMPRESSOR SHELTER |  | Layout Drawing for AIR COMPRESSOR SHELTER | AIR COMPRESSOR | FI | 0EF3510W00A01 | (COMP Air Receiver TK Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 |  |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152719 | EMBEDDED CONDUIT LAYOUT FOR DEAERATOR SUPPORT STRUCTURE | LAYOUT |  |  |  |  | Layout Drawing | Substation | SKIP | 3EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-03-30 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152720 | EMBEDDED CONDUIT LAYOUT FOR FIRE WATER PUMP HOUSE & FIN FAN COOLER(CPP) | LAYOUT | Fire Fighting Pump, Fin Fan Cooler(CPP) |  | Fire Pump House |  | Layout Drawing for Fire Fighting Pump, Fin Fan Cooler(CPP) | CPP FIN FAN COOLER | FA | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152721 | EMBEDDED CONDUIT LAYOUT FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | LAYOUT |  |  |  |  | Layout Drawing | Substation | SKIP | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152722 | EMBEDDED CONDUIT LAYOUT FOR WATER TREATMENT BUILDING | LAYOUT |  |  | WT Building |  | Layout Drawing for WT Building | Substation | SKIP | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152724 | EMBEDDED CONDUIT LAYOUT FOR CHEMICAL DOSING SHELTER FOR STG & HRSG | LAYOUT | Steam Turbine & Generator, Heat Recovery Steam Generator | Chemical dosing system |  |  | Layout Drawing for Steam Turbine & Generator, Heat Recovery Steam Generator | STEAM TURBINE GENERATOR | FA | 1EF3045W00A06 | (Chemical Dosing BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 |  |  |  |  | 2024-06-28 | 2024-07-28 | 2024-08-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152725 | EMBEDDED CONDUIT LAYOUT FOR CHEMICAL DOSING SHELTER FOR HRSG | LAYOUT | Heat Recovery Steam Generator | Chemical dosing system |  |  | Layout Drawing for HRSG |  | FA | 1EF3045W00A06 | (Chemical Dosing BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 |  | 2025-06-08 | 2025-07-08 | 2025-08-07 | 2025-08-22 | 2025-09-06 | 2025-09-21 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152726 | EMBEDDED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #1 | LAYOUT | Gas Turbine Generator |  |  |  | Layout Drawing for GTG | Substation | SKIP | 1EF6500W00A09 | (GTG #11 & UAT Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152727 | EMBEDDED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #2 | LAYOUT | Gas Turbine Generator |  |  |  | Layout Drawing for GTG | Substation | SKIP | 2EF6500W00A09 | (GTG #21 & UAT Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152728 | EMBEDDED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #3 | LAYOUT | Gas Turbine Generator |  |  |  | Layout Drawing for GTG | Substation | SKIP | 3EF6500W00A09 | (GTG #31 & UAT Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152729 | EMBEDDED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #4 | LAYOUT | Gas Turbine Generator |  |  |  | Layout Drawing for GTG | Substation | SKIP | 1EF6500W00A09 | (GTG #11 & UAT Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152730 | EMBEDDED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #5 | LAYOUT | Gas Turbine Generator |  |  |  | Layout Drawing for GTG | Substation | SKIP | 1EF6500W00A09 | (GTG #11 & UAT Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152731 | EMBEDDED CONDUIT LAYOUT FOR POTABLE STORAGE WATER TANK & FIRE WATER TANK AREA | LAYOUT | Tank |  |  |  | Layout Drawing for Tank | shop Tank | FA | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  | 2024-09-14 | 2024-10-14 | 2024-11-13 | 2024-11-28 | 2024-12-13 | 2024-12-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152732 | EMBEDDED CONDUIT LAYOUT FOR DEMI WATER STORAGE TANK AREA | LAYOUT | Tank |  |  |  | Layout Drawing for Tank | shop Tank | FA | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  | 2024-09-14 | 2024-10-14 | 2024-11-13 | 2024-11-28 | 2024-12-13 | 2024-12-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152733 | EMBEDDED CONDUIT LAYOUT FOR CONDENSATE STORAGE TANK AREA | LAYOUT | Tank |  |  |  | Layout Drawing for Tank | shop Tank | FA | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  | 2024-09-14 | 2024-10-14 | 2024-11-13 | 2024-11-28 | 2024-12-13 | 2024-12-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152735 | EMBEDDED CONDUIT LAYOUT FOR FIN FAN COOLER(CCW) & CCW PUMP AREA | LAYOUT | Fin Fan Cooler(CCW), Closed Cooling Water Pump |  |  |  | Layout Drawing for Fin Fan Cooler(CCW), Closed Cooling Water Pump | CCW FIN FAN COOLER | FA | 1EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | 2007-07-03 | 2007-11-29 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152736 | EMBEDDED CONDUIT LAYOUT FOR STG TRANSFORMER AREA #1,#2 | LAYOUT | Steam Turbine & Generator |  |  |  | Layout Drawing for STG | Substation | SKIP | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152750 | ELECTRICAL DUCT BANK LAYOUT DRAWING CENTRAL CONTROL BUILDING AREA | LAYOUT DRAWING |  |  | CENTRAL CONTROL BUILDING |  | Layout Drawing for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152751 | ELECTRICAL DUCT BANK LAYOUT GTG #1 AREA | LAYOUT | Gas Turbine Generator |  |  |  | Layout Drawing for GTG | Substation | SKIP | 1EF1200W00A01.1 | (GTG #11 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 LEB | 2007-05-31 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152752 | ELECTRICAL DUCT BANK LAYOUT GTG #2 AREA | LAYOUT | Gas Turbine Generator |  |  |  | Layout Drawing for GTG | Substation | SKIP | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152753 | ELECTRICAL DUCT BANK LAYOUT GTG #3,#4 AREA | LAYOUT | Gas Turbine Generator |  |  |  | Layout Drawing for GTG | Substation | SKIP | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152754 | ELECTRICAL DUCT BANK LAYOUT GTG #5 AREA | LAYOUT | Gas Turbine Generator |  |  |  | Layout Drawing for GTG | Substation | SKIP | 1EF1200W00A01.1 | (GTG #11 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 LEB | 2007-05-31 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152755 | ELECTRICAL DUCT BANK LAYOUT HRSG #1 AREA | LAYOUT | Heat Recovery Steam Generator |  |  |  | Layout Drawing for HRSG |  | FA | 1EF1615W00A01 | (HRSG #11 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | 2007-04-30 |  | 2025-01-10 | 2025-02-09 | 2025-03-11 | 2025-03-26 | 2025-04-10 | 2025-04-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152756 | ELECTRICAL DUCT BANK LAYOUT HRSG #2 AREA | LAYOUT | Heat Recovery Steam Generator |  |  |  | Layout Drawing for HRSG |  | FA | 2EF1615W00A01 | (HRSG #21 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-05-30 |  | 2025-02-09 | 2025-03-11 | 2025-04-10 | 2025-04-25 | 2025-05-10 | 2025-05-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152757 | ELECTRICAL DUCT BANK LAYOUT HRSG #3,#4 AREA | LAYOUT | Heat Recovery Steam Generator |  |  |  | Layout Drawing for HRSG |  | FA | 3EF1615W00A01 | (HRSG #31 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2007-06-29 |  | 2025-03-11 | 2025-04-10 | 2025-05-10 | 2025-05-25 | 2025-06-09 | 2025-06-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152758 | ELECTRICAL DUCT BANK LAYOUT HRSG #5 AREA | LAYOUT | Heat Recovery Steam Generator |  |  |  | Layout Drawing for HRSG |  | FA | 2EF1615W00A01 | (HRSG #21 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-05-30 |  | 2025-02-09 | 2025-03-11 | 2025-04-10 | 2025-04-25 | 2025-05-10 | 2025-05-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152759 | ELECTRICAL DUCT BANK LAYOUT AIR COMPRESSOR & ACC AREA | LAYOUT | Air Compressor & Air Cooled Condenser |  |  |  | Layout Drawing for Air Compressor & Air Cooled Condenser | CONDENSER | FA | 0EF3510W00A17 | (COMP Air BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 |  |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152760 | ELECTRICAL DUCT BANK LAYOUT ST #1 LEB | LAYOUT | Steam Turbine |  | Local Electrical Building |  | Layout Drawing for STG | Substation | SKIP | 1EF1600W00A01 | (HRSG #11 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | 2007-06-20 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152761 | ELECTRICAL DUCT BANK LAYOUT ST #2 LEB | LAYOUT | Steam Turbine |  | Local Electrical Building |  | Layout Drawing for STG | Substation | SKIP | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152762 | ELECTRICAL DUCT BANK LAYOUT TANK AREA | LAYOUT | Tank |  |  |  | Layout Drawing for Tank | shop Tank | FA | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  | 2024-09-14 | 2024-10-14 | 2024-11-13 | 2024-11-28 | 2024-12-13 | 2024-12-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152763 | ELECTRICAL DUCT BANK LAYOUT WATER TREATMENT BUILDING AREA | LAYOUT |  |  | WATER TREATMENT BUILDING |  | Layout Drawing for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 |  |  |  |  | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152764 | ELECTRICAL DUCT BANK LAYOUT CPP REGEN BUILDING AREA | LAYOUT |  |  | CPP REGEN BUILDING |  | Layout Drawing for CPP REGEN BUILDING | CPP Regeneration Building | FI | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152765 | ELECTRICAL DUCT BANK LAYOUT FGS & RESERVE BOILER AREA | LAYOUT |  | Fuel Gas System |  |  | Layout Drawing for Fuel Gas System | Fuel Gas System | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | 2024-09-04 | 2024-10-30 | 2024-12-25 | 2024-11-20 | 2025-01-15 | 2025-03-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152766 | ELECTRICAL DUCT BANK LAYOUT ADMINISTRATION & SOCIAL BUILDING AREA | LAYOUT |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Layout Drawing for ADMINISTRATION & SOCIAL BUILDING |  | FA | 0EF5566W00A01 | (ADMIN BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 |  | 2025-08-22 | 2025-09-21 | 2025-10-21 | 2025-11-05 | 2025-11-20 | 2025-12-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152767 | ELECTRICAL DUCT BANK LAYOUT SECURITY BUILDING AREA | LAYOUT |  |  | SECURITY BUILDING |  | Layout Drawing for SECURITY BUILDING |  | FA | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | 2025-07-23 | 2025-08-22 | 2025-09-21 | 2025-10-06 | 2025-10-21 | 2025-11-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152768 | ELECTRICAL DUCT BANK LAYOUT MAIN GATE HOUSE AREA | LAYOUT |  |  | MAIN GATE HOUSE |  | Layout Drawing for MAIN GATE HOUSE | MAIN GATE | FI | 0EF5570W32A03 | (Gate House) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152769 | ELECTRICAL DUCT BANK LAYOUT EHV CABLE AREA - 1 | LAYOUT |  |  |  |  | Layout Drawing | Substation | SKIP | 1CF6040W74A08 | (EHV Cable) Cable Electrical Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2008-04-16 | 2008-07-01 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152770 | ELECTRICAL DUCT BANK LAYOUT EHV CABLE AREA - 2 | LAYOUT |  |  |  |  | Layout Drawing | Substation | SKIP | 2CF6040W74A08 | (EHV Cable) Cable Electrical Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2008-05-17 | 2008-08-01 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152771 | ELECTRICAL DUCT BANK LAYOUT EHV CABLE AREA - 3 | LAYOUT |  |  |  |  | Layout Drawing | Substation | SKIP | 3CF6040W74A08 | (EHV Cable) Cable Electrical Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2008-06-17 | 2008-09-01 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152791 | RACEWAY DRAWING FOR HCIS – MAIN GATE HOUSE | RACEWAY DRAWING |  |  | MAIN GATE HOUSE |  | RACEWAY DRAWING for MAIN GATE HOUSE | MAIN GATE | FI | 0CF6040W74A05 | (Raceway) Installation for CCB-GIS BLDG(Early Power) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Raceway System | 2008-03-18 | 2008-04-17 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152792 | RACEWAY DRAWING FOR HCIS – PLANT ACCESS GATE HOUSE | RACEWAY DRAWING |  |  | PLANT ACCESS GATE HOUSE |  | RACEWAY DRAWING for PLANT ACCESS GATE HOUSE |  | FA | 0CF6040W74A05 | (Raceway) Installation for CCB-GIS BLDG(Early Power) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Raceway System | 2008-03-18 | 2008-04-17 | 2025-05-14 | 2025-06-13 | 2025-07-13 | 2025-07-28 | 2025-08-12 | 2025-08-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152793 | RACEWAY DRAWING FOR HCIS – SEARCH FACILITY & VISITOR CENTRE | RACEWAY DRAWING |  |  | SEARCH FACILITY & VISITOR CENTRE |  | RACEWAY DRAWING for SEARCH FACILITY & VISITOR CENTRE |  | FA | 0PF6040W74A02P | (Raceway) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Raceway System | 2007-09-03 | 2008-01-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152794 | RACEWAY DRAWING FOR HCIS – SUPPORT BUILDING | RACEWAY DRAWING |  |  | SUPPORT BUILDING |  | RACEWAY DRAWING for SUPPORT BUILDING |  | FA | 0PF6040W74A02P | (Raceway) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Raceway System | 2007-09-03 | 2008-01-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0ZEN-152795 | RACEWAY DRAWING FOR HCIS – PRELIMINARY INSPECTION CHECKPOINT | RACEWAY DRAWING |  |  |  |  | RACEWAY DRAWING |  | FA | 0PF6040W74A02P | (Raceway) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Raceway System | 2007-09-03 | 2008-01-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YR02-P0ZEN-152801 | SIZING CALCULATION - MV/LV POWER CABLES | SIZING CALCULATION | MV/LV POWER CABLES |  |  |  | Calculation sheet for MV/LV POWER CABLES | FloW element | FA | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ZEN-152810 | SIZING CALCULATION - 380KV EHV CABLE AND ACCESSOIRES | SIZING CALCULATION | 380KV EHV CABLE AND ACCESSOIRES |  |  |  | Calculation sheet for 380KV EHV CABLE AND ACCESSOIRES | Substation | SKIP | 1PF6040W74A06P | (EHV Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2008-02-29 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0ZEN-152820 | TECHNICAL SPECIFICATION - 380KV EHV CABLE AND ACCESSORIES | TECHNICAL SPECIFICATION | 380KV EHV CABLE AND ACCESSORIES |  |  |  | Technical Specification for 380KV EHV CABLE AND ACCESSORIES |  | FA | 1PF6040W74A06P | (EHV Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2008-02-29 | 2024-09-27 | 2024-10-27 | 2024-11-26 | 2024-12-11 | 2024-12-26 | 2025-01-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0ZEN-152822 | OUTLINE & SCHEMATIC DRAWING - 380KV EHV CABLE AND ACCESSOIRES | OUTLINE & SCHEMATIC DRAWING | 380KV EHV CABLE AND ACCESSOIRES |  |  |  | OUTLINE & SCHEMATIC DRAWING for 380KV EHV CABLE AND ACCESSOIRES |  | FA | 1CF6040W74A08 | (EHV Cable) Cable Electrical Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2008-04-16 | 2008-07-01 |  |  |  | 2025-01-17 | 2025-02-16 | 2025-03-18 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0ZEN-152823 | INSTALLATION DRAWING - 380KV EHV CABLE AND ACCESSOIRES | INSTALLATION DRAWING | 380KV EHV CABLE AND ACCESSOIRES |  |  |  | INSTALLATION DRAWING for 380KV EHV CABLE AND ACCESSOIRES |  | FA | 1PF6040W74A06P | (EHV Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2008-02-29 | 2024-09-27 | 2024-10-27 | 2024-11-26 | 2024-12-11 | 2024-12-26 | 2025-01-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0ZEN-152830 | TECHNICAL SPECIFICATION - POWER & CONTROL & F/O CABLE | TECHNICAL SPECIFICATION | POWER & CONTROL & Fiber Optic Cable |  |  |  | Technical Specification for POWER & CONTROL & Fiber Optic Cable |  | FA | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | 2024-11-14 | 2024-12-14 | 2025-01-13 | 2025-01-28 | 2025-02-12 | 2025-02-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0ZEN-152840 | TECHNICAL SPECIFICATION - CABLING ACCESSORIES | TECHNICAL SPECIFICATION | CABLING ACCESSORIES |  |  |  | Technical Specification for CABLING ACCESSORIES |  | FA | 0EF6020W46A07 | (Hanger & Support & Fitting) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement |  | 2007-07-30 | [6 empty] | missing_date |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-152850 | POWER CABLE SCHEDULE | SCHEDULE | POWER CABLE |  |  |  | Schedule for POWER CABLE |  | FA | 1PF6040W74A06P | (EHV Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2008-02-29 | 2025-02-12 | 2025-03-14 | 2025-04-13 | 2025-04-28 | 2025-05-13 | 2025-05-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-152860 | CONTROL CABLE SCHEDULE | SCHEDULE | CONTROL CABLE |  |  |  | Schedule for CONTROL CABLE |  | FA | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | 2025-05-06 | 2025-06-05 | 2025-07-05 | 2025-07-20 | 2025-08-04 | 2025-08-19 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0ZEN-152870 | TECHNICAL SPECIFICATION - FIRE STOP MATERIAL | TECHNICAL SPECIFICATION |  |  |  |  | Technical Specification |  | FA | 0EF4500W38A08 | (Fire Fighting System) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System |  | 2007-05-01 | [6 empty] | missing_date |  | 6210
Fadhili_MDL.xlsx | T16182-DE00-P0CY-154001 | TECHNICAL SPECIFICATION - COMMUNICATION SYSTEM | TECHNICAL SPECIFICATION |  | COMMUNICATION SYSTEM |  |  | Technical Specification for COMMUNICATION SYSTEM | Communication System & Security | SKIP | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYA-154011 | CONFIGURATION DIAGRAM - OFFICE TELEPHONE & LAN SYSTEM | CONFIGURATION DIAGRAM |  |  |  |  | CONFIGURATION DIAGRAM |  | FA | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0CYM-154013 | CONFIGURATION DIAGRAM - PUBLIC ADDRESS SYSTEM (SIREN SYSTEM) | CONFIGURATION DIAGRAM |  |  |  |  | CONFIGURATION DIAGRAM |  | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-YQ03-P0CY-154021 | TYPICAL INSTALLATION DRAWING - COMMUNICATION SYSTEM | INSTALLATION DRAWING |  | COMMUNICATION SYSTEM |  |  | INSTALLATION DRAWING for COMMUNICATION SYSTEM |  | FA | 0PF6040W74A02P | (Raceway) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Raceway System | 2007-09-03 | 2008-01-31 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154031 | COMMUNICATION LAYOUT DRAWING - CENTRAL CONTROL BUILDING | LAYOUT DRAWING |  |  | CENTRAL CONTROL BUILDING |  | Layout Drawing for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154032 | COMMUNICATION LAYOUT DRAWING - GTG #1,2 LEB | LAYOUT DRAWING |  |  | GTG #1,2 LEB |  | Layout Drawing for GTG #1,2 LEB |  | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154033 | COMMUNICATION LAYOUT DRAWING - GTG #3,4,5 LEB | LAYOUT DRAWING |  |  | GTG #3,4,5 LEB |  | Layout Drawing for GTG #3,4,5 LEB |  | FI | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154034 | COMMUNICATION LAYOUT DRAWING - ST #1 LEB | LAYOUT DRAWING |  |  | Steam Turbine #1 LEB |  | Layout Drawing for Steam Turbine #1 LEB | STEAM TURBINE GENERATOR | FA | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154035 | COMMUNICATION LAYOUT DRAWING - ST #2 LEB | LAYOUT DRAWING |  | Communication System & Security System | Steam Turbine #2 Local Electrical Building |  | Layout Drawing for Communication System & Security System | Communication System & Security | SKIP | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154036 | COMMUNICATION LAYOUT DRAWING - ST BUILDING | LAYOUT DRAWING |  | Communication System & Security System | ST BUILDING |  | Layout Drawing for Communication System & Security System | Communication System & Security | SKIP | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154037 | COMMUNICATION LAYOUT DRAWING - FGS ELECTRICAL BUILDING | LAYOUT DRAWING |  | Communication System & Security System | Fuel Gas System ELECTRICAL BUILDING |  | Layout Drawing for Communication System & Security System | Communication System & Security | SKIP | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154038 | COMMUNICATION LAYOUT DRAWING - ADMINISTRATION & SOCIAL BUILDING | LAYOUT DRAWING |  | Communication System & Security System | ADMINISTRATION & SOCIAL BUILDING |  | Layout Drawing for Communication System & Security System | Communication System & Security | SKIP | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154039 | COMMUNICATION LAYOUT DRAWING - SECURITY BUILDING | LAYOUT DRAWING |  | Communication System & Security System | SECURITY BUILDING |  | Layout Drawing for Communication System & Security System | Communication System & Security | SKIP | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154040 | COMMUNICATION LAYOUT DRAWING – MAIN GATE & PLANT ACCESS GATE HOUSE | LAYOUT DRAWING |  | Communication System & Security System | MAIN GATE & PLANT ACCESS GATE HOUSE |  | Layout Drawing for Communication System & Security System | Communication System & Security | SKIP | 0EF5570W32A03 | (Gate House) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154041 | COMMUNICATION LAYOUT DRAWING - SUPPORT BUILDING | LAYOUT DRAWING |  | Communication System & Security System | SUPPORT BUILDING |  | Layout Drawing for Communication System & Security System | Communication System & Security | SKIP | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154042 | COMMUNICATION LAYOUT DRAWING - X-RAY SEARCHING ROOM | LAYOUT DRAWING |  | Communication System & Security System | X-RAY SEARCHING ROOM |  | Layout Drawing for Communication System & Security System | Communication System & Security | SKIP | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154044 | COMMUNICATION LAYOUT DRAWING - FIRE BRIGADE & AUX. LEB | LAYOUT DRAWING |  | Communication System & Security System | FIRE BRIGADE & Auxiliary Local Electrical Building |  | Layout Drawing for Communication System & Security System | Communication System & Security | SKIP | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154045 | COMMUNICATION LAYOUT DRAWING - WORKSHOP & STORAGE BUILDING | LAYOUT DRAWING |  | Communication System & Security System | WORKSHOP & STORAGE BUILDING |  | Layout Drawing for Communication System & Security System | Communication System & Security | SKIP | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154049 | COMMUNICATION LAYOUT DRAWING - FIRE WATER PUMP HOUSE | LAYOUT DRAWING |  | Communication System & Security System | FIRE WATER PUMP HOUSE |  | Layout Drawing for Communication System & Security System | Communication System & Security | SKIP | 0PF4500W38A09P | (Fire Fighting System) P.O & Procurement_piping | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-08-01 | 2007-12-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154051 | COMMUNICATION LAYOUT DRAWING - WATER TREATMENT BUILDING | LAYOUT DRAWING |  | Communication System & Security System | WATER TREATMENT BUILDING |  | Layout Drawing for Communication System & Security System | Communication System & Security | SKIP | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154052 | COMMUNICATION LAYOUT DRAWING - CPP & CPP REGENERATION BUILDING | LAYOUT DRAWING |  | Communication System & Security System | CPP & CPP REGENERATION BUILDING |  | Layout Drawing for Communication System & Security System | Communication System & Security | SKIP | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YQ08-P0CY-154053 | COMMUNICATION LAYOUT DRAWING – PIPE RACK | LAYOUT DRAWING |  | Communication System & Security System | PIPE RACK |  | Layout Drawing for Communication System & Security System | Communication System & Security | SKIP | 1PF5550W46A08P | (PipeRack) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-06-28 | 2008-01-02 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0ASS-155001 | RELAY SETTING CALCULATION OF 380kV SYNCHRONIZING SYSTEM | CALCULATION |  | SYNCHRONIZING SYSTEM |  |  | Calculation sheet for SYNCHRONIZING SYSTEM | Water Treatment System | FA | 0PF6500W70A02.7P | (Power Metering Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power Metering System | 2007-07-13 | 2008-02-12 | 2024-08-12 | 2024-09-11 | 2024-10-11 | 2024-10-26 | 2024-11-10 | 2024-11-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ASR-155011 | RELAY SETTING CALCULATION FOR GTG1 & GTG2 CABLE PROTECTION | CALCULATION | Gas Turbine Generator1 & Gas Turbine Generator2 |  |  |  | Calculation sheet for Gas Turbine Generator1 & Gas Turbine Generator2 |  | FA | 2SF9012W62A04 | (GTG #21) TBN & GEN Protection Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Commissioning | 2008-10-05 | 2008-10-06 | 2026-10-16 | 2026-11-15 | 2026-12-15 | 2026-12-30 | 2027-01-14 | 2027-01-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ASR-155012 | RELAY SETTING CALCULATION FOR GTG #3, 4, 5 CABLE PROTECTION | CALCULATION | Gas Turbine Generator #3, 4, 5 |  |  |  | Calculation sheet for Gas Turbine Generator #3, 4, 5 |  | FI | 3CF1255W70A05 | (GTG#31 Electrical) Installation- Protection Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Electrical System | 2008-08-01 | 2008-09-15 |  |  |  | 2025-05-04 | 2025-06-03 | 2025-07-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ASR-155013 | RELAY SETTING CALCULATION FOR STG #1, 2 CABLE PROTECTION | CALCULATION | Steam Turbine & Generator #1, 2 |  |  |  | Calculation sheet for Steam Turbine & Generator #1, 2 | STEAM TURBINE GENERATOR | FA | 2CF1255W70A05.1 | (GTG#22 Electrical) Installation- Protection Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Electrical System | 2008-08-01 | 2008-09-15 |  |  |  | 2025-07-03 | 2025-06-03 | 2025-05-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0ASR-155014 | RELAY SETTING CALCULATION FOR 13.8kV CABLE PROTECTION – COGEN TO ESF | CALCULATION |  |  |  |  | Calculation sheet |  | FA | 0PF6500W70A02.6P | (Electrical Protection Panel) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2007-08-30 | 2008-03-10 | 2025-01-17 | 2025-02-16 | 2025-03-18 | 2025-04-02 | 2025-04-17 | 2025-05-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0ZEN-161001 | DESIGN CRITERIA FOR GENERAL I&C SYSTEM | DESIGN CRITERIA |  | GENERAL Instrumentation & Control SYSTEM |  |  | DESIGN CRITERIA for GENERAL Instrumentation & Control SYSTEM | Chemical Dosing System | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0ZEN-161011 | MASTER CLOCK CONCEPT DIAGRAM | DIAGRAM |  |  |  |  | Diagram |  | FA | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CJD-161021 | PLANT START - UP & SHUTDOWN SEQUENCE DIAGRAM – SYMBOL & LEGEND | DIAGRAM |  |  |  |  | Diagram |  | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CJD-161022 | PLANT START - UP & SHUTDOWN SEQUENCE DIAGRAM FOR START - UP | DIAGRAM |  |  |  |  | Diagram |  | FA | 0SF3530W62A10 | (BSDG) Initial start up | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2008-08-23 | 2008-08-27 | 2025-10-19 | 2025-11-18 | 2025-12-18 | 2026-01-02 | 2026-01-17 | 2026-02-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CJD-161025 | PLANT START - UP & SHUTDOWN SEQUENCE DIAGRAM FOR SHUTDOWN | DIAGRAM |  |  |  |  | Diagram |  | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | 2024-11-09 | 2024-12-09 | 2025-01-08 | 2025-01-23 | 2025-02-07 | 2025-02-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF02-P0ZEN-161031 | PLANT CONTROL SYSTEM CONFIGURATION DIAGRAM | DIAGRAM |  | PLANT CONTROL SYSTEM |  |  | Diagram for PLANT CONTROL SYSTEM |  | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | 2024-10-23 | 2024-11-22 | 2024-12-22 | 2025-01-06 | 2025-01-21 | 2025-02-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CJA-161041 | PLANT MASTER CONTROL DIAGRAM | DIAGRAM |  |  |  |  | Diagram |  | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF01-P0BYA-161051 | PLANT PROTECTION & INTERLOCK DIAGRAM | DIAGRAM |  | PLANT PROTECTION SYSTEM |  |  | Diagram for PLANT PROTECTION SYSTEM |  | FA | 0PF6500W70A02.6P | (Electrical Protection Panel) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2007-08-30 | 2008-03-10 | 2024-11-21 | 2024-12-21 | 2025-01-20 | 2025-02-04 | 2025-02-19 | 2025-03-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0CBA-161101 | DCS I/O DATABASE | DATABASE | DCS |  |  |  | DATABASE for DCS |  | FA | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | 2025-06-14 | 2025-07-05 | 2025-07-26 | 2025-08-19 | 2025-09-03 | 2025-09-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF02-P0CRV-161102 | DCS - LAN CONFIGURATION DIAGRAM | DIAGRAM | DCS |  |  |  | Diagram for DCS |  | FA | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | 2025-06-14 | 2025-07-05 | 2025-07-26 | 2025-08-19 | 2025-09-03 | 2025-09-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CRN-161103 | DCS - FUNCTIONAL DESIGN SPECIFICATION FOR HARDWARE | FUNCTIONAL DESIGN SPECIFICATION | DCS |  |  |  | FUNCTIONAL DESIGN SPECIFICATION for DCS |  | FA | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CRN-161104 | DCS - FUNCTIONAL DESIGN SPECIFICATION FOR SOFTWARE | FUNCTIONAL DESIGN SPECIFICATION | DCS |  |  |  | FUNCTIONAL DESIGN SPECIFICATION for DCS |  | FA | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CRN-161105 | DCS - FUNCTIONAL DESIGN SPECIFICATION FOR HMI GRAPHIC | FUNCTIONAL DESIGN SPECIFICATION | DCS |  |  |  | FUNCTIONAL DESIGN SPECIFICATION for DCS |  | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | 2024-11-16 | 2024-12-16 | 2025-01-15 | 2025-01-30 | 2025-02-14 | 2025-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YR04-P0CUQ-161111 | DCS POWER DISTRIBUTION CONCEPT DIAGRAM | DIAGRAM | DCS |  |  |  | Diagram for DCS |  | FA | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | 2025-06-14 | 2025-07-05 | 2025-07-26 | 2025-08-19 | 2025-09-03 | 2025-09-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CUQ-161112 | DCS - POWER DISTRIBUTION DRAWING | DRAWING | DCS |  |  |  | DRAWING for DCS |  | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | 2025-03-19 | 2025-04-18 | 2025-05-18 | 2025-06-02 | 2025-06-17 | 2025-07-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CRN-161113 | DCS - IO & MODULE ALLOCATION |  | DCS |  |  |  | for DCS |  | FA | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | 2025-06-14 | 2025-07-05 | 2025-07-26 | 2025-08-19 | 2025-09-03 | 2025-09-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0CRN-161114 | DCS - INTERNAL CABLE CONNECTION DIAGRAM | DIAGRAM | DCS |  |  |  | Diagram for DCS |  | FA | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | 2025-06-14 | 2025-07-05 | 2025-07-26 | 2025-08-19 | 2025-09-03 | 2025-09-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0CRN-161115 | DCS - CABLE LIST | CABLE LIST | DCS |  |  |  | CABLE LIST for DCS |  | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | 2025-07-31 | 2025-08-21 | 2025-09-11 | 2025-10-05 | 2025-10-20 | 2025-11-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD05-P0CRN-161116 | DCS - HMI GRAPHIC DISPLAY DIAGRAM | DIAGRAM | DCS |  |  |  | Diagram for DCS |  | FA | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | 2025-06-14 | 2025-07-05 | 2025-07-26 | 2025-08-19 | 2025-09-03 | 2025-09-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0CRN-161117 | 3RD PARTY DATA - LINK INTERFACE SIGNAL DATABASE | DATABASE |  |  |  |  | DATABASE |  | FA | 0SF6500W62A01 | (Power Receiving) Interface signal Test | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power Receiving | 2008-08-01 | 2008-08-02 |  |  |  | 2025-05-04 | 2025-06-03 | 2025-07-03 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-YR04-P0CUQ-161118 | I&C GROUNDING CONCEPT DIAGRAM | DIAGRAM |  | Instrumentation & Control Grounding System |  |  | Diagram for Instrumentation & Control Grounding System | Substation | SKIP | 0CF5510W90A09 | (CCR BLDG) Installation & Test - I&C for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-04-22 | 2008-07-09 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CUQ-161119 | DCS - GROUNDING DRAWING | DRAWING | DCS | Grounding System |  |  | DRAWING for DCS |  | FA | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | 2025-01-31 | 2025-03-02 | 2025-04-01 | 2025-04-16 | 2025-05-01 | 2025-05-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CWQ-161121 | DCS - PERFORMANCE MONITORING SYSTEM |  | DCS |  |  |  | for DCS |  | FA | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | 2025-06-14 | 2025-07-05 | 2025-07-26 | 2025-08-19 | 2025-09-03 | 2025-09-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CWQ-161122 | DCS - PLANT INFORMATION HISTORIAN |  | DCS |  |  |  | for DCS |  | FA | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | 2025-06-14 | 2025-07-05 | 2025-07-26 | 2025-08-19 | 2025-09-03 | 2025-09-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CWQ-161123 | DCS - FIELD INSTRUMENT MONITORING SYSTEM |  | DCS |  |  |  | for DCS |  | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | 2025-07-31 | 2025-08-21 | 2025-09-11 | 2025-10-05 | 2025-10-20 | 2025-11-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CWQ-161132 | DCS - TECHNICAL SPECIFICATION FOR TIME SYNCHRONIZATION | TECHNICAL SPECIFICATION | DCS |  |  |  | Technical Specification for DCS |  | FA | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CWQ-161133 | DCS - TECHNICAL SPECIFICATION FOR EMERGENCY PUSH BUTTON | TECHNICAL SPECIFICATION | DCS |  |  |  | Technical Specification for DCS |  | FA | 0EF7000W86A01.1 | (DCS) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS |  | 2007-04-30 | [6 empty] | missing_date |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CWQ-161134 | TECHNICAL SPECIFICATION & DATA SHEET FOR SETTLEMENT SYSTEM | TECHNICAL SPECIFICATION & DATA SHEET |  | Plant Settlement System |  |  | TECHNICAL SPECIFICATION & DATA SHEET for Plant Settlement System |  | FA | 0EF6020W46A07 | (Hanger & Support & Fitting) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement |  | 2007-07-30 | [6 empty] | missing_date |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CWQ-161135 | DCS - TECHNICAL SPECIFICATION FOR LARGE SCREEN DISPLAY | TECHNICAL SPECIFICATION | DCS |  |  |  | Technical Specification for DCS |  | FA | 0EF7000W86A01.1 | (DCS) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS |  | 2007-04-30 | [6 empty] | missing_date |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0CWQ-161141 | DCS - OUTLINE & DETAIL DRAWING FOR DCS SYSTEM CABINET | OUTLINE & DETAIL DRAWING | DCS |  |  |  | OUTLINE & DETAIL DRAWING for DCS |  | FA | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | 2025-01-31 | 2025-03-02 | 2025-04-01 | 2025-04-16 | 2025-05-01 | 2025-05-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0CWQ-161142 | DCS - OUTLINE & DETAIL DRAWING FOR LAN/SERVER CABINET | OUTLINE & DETAIL DRAWING | DCS |  |  |  | OUTLINE & DETAIL DRAWING for DCS |  | FA | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | 2025-01-31 | 2025-03-02 | 2025-04-01 | 2025-04-16 | 2025-05-01 | 2025-05-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0CWQ-161143 | DCS - OUTLINE & DETAIL DRAWING FOR MARSHALLING CABINET | OUTLINE & DETAIL DRAWING | DCS |  |  |  | OUTLINE & DETAIL DRAWING for DCS |  | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | 2025-03-19 | 2025-04-18 | 2025-05-18 | 2025-06-02 | 2025-06-17 | 2025-07-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0CWQ-161146 | DCS - OUTLINE & DETAIL DRAWING FOR DCS CONSOLE & DESK | OUTLINE & DETAIL DRAWING | DCS |  |  |  | OUTLINE & DETAIL DRAWING for DCS |  | FA | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | 2025-01-31 | 2025-03-02 | 2025-04-01 | 2025-04-16 | 2025-05-01 | 2025-05-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0CWQ-161147 | DCS - OUTLINE & DETAIL DRAWING FOR DCS POWER DISTRIBUTION CABINET | OUTLINE & DETAIL DRAWING | DCS |  |  |  | OUTLINE & DETAIL DRAWING for DCS |  | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | 2025-03-19 | 2025-04-18 | 2025-05-18 | 2025-06-02 | 2025-06-17 | 2025-07-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0CWQ-161148 | DCS - OUTLINE & DETAIL DRAWING FOR DCS GROUNDING BOX | OUTLINE & DETAIL DRAWING | DCS |  |  |  | OUTLINE & DETAIL DRAWING for DCS |  | FA | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | 2025-01-31 | 2025-03-02 | 2025-04-01 | 2025-04-16 | 2025-05-01 | 2025-05-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0CRT-161149 | DCS - TECHNICAL SPECIFICATION FOR FIELDBUS MOV | TECHNICAL SPECIFICATION | DCS |  |  |  | Technical Specification for DCS |  | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | 2024-11-16 | 2024-12-16 | 2025-01-15 | 2025-01-30 | 2025-02-14 | 2025-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YR01-P0CRU-161150 | INTEGRATED SAT(SITE ACCEPTANCE TEST) PROCEDURE FOR DCS | PROCEDURE | DCS |  |  |  | PROCEDURE for DCS |  | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | 2025-07-31 | 2025-08-21 | 2025-09-11 | 2025-10-05 | 2025-10-20 | 2025-11-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161201 | CONTROL LOGIC DIAGRAM - SYMBOL & LEGEND | CONTROL LOGIC DIAGRAM |  |  |  |  | CONTROL LOGIC DIAGRAM |  | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | 2025-02-16 | 2025-03-18 | 2025-04-17 | 2025-05-02 | 2025-05-17 | 2025-06-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161202 | CONTROL LOGIC DIAGRAM - TYPICAL FUNCTION | CONTROL LOGIC DIAGRAM |  |  |  |  | CONTROL LOGIC DIAGRAM |  | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | 2025-02-16 | 2025-03-18 | 2025-04-17 | 2025-05-02 | 2025-05-17 | 2025-06-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161203 | CONTROL LOGIC DIAGRAM FOR HP STEAM SYSTEM | CONTROL LOGIC DIAGRAM |  | Steam System(High Pressure) |  |  | CONTROL LOGIC DIAGRAM for Steam System(High Pressure) |  | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | 2024-10-13 | 2024-11-12 | 2024-12-12 | 2024-12-27 | 2025-01-11 | 2025-01-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161204 | CONTROL LOGIC DIAGRAM FOR IP STEAM SYSTEM | CONTROL LOGIC DIAGRAM |  | Intermediate Pressure Steam System |  |  | CONTROL LOGIC DIAGRAM for Intermediate Pressure Steam System |  | FA | 3EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | 2024-10-13 | 2024-11-12 | 2024-12-12 | 2024-12-27 | 2025-01-11 | 2025-01-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161205 | CONTROL LOGIC DIAGRAM FOR LP STEAM SYSTEM | CONTROL LOGIC DIAGRAM |  | LP STEAM SYSTEM |  |  | CONTROL LOGIC DIAGRAM for LP STEAM SYSTEM |  | FA | 3EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | 2024-10-13 | 2024-11-12 | 2024-12-12 | 2024-12-27 | 2025-01-11 | 2025-01-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161206 | CONTROL LOGIC DIAGRAM FOR PROCESS STEAM SYSTEM | CONTROL LOGIC DIAGRAM |  | PROCESS STEAM SYSTEM |  |  | CONTROL LOGIC DIAGRAM for PROCESS STEAM SYSTEM |  | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | 2024-10-13 | 2024-11-12 | 2024-12-12 | 2024-12-27 | 2025-01-11 | 2025-01-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161207 | CONTROL LOGIC DIAGRAM FOR STEAM DRAIN SYSTEM | CONTROL LOGIC DIAGRAM |  | STEAM DRAIN SYSTEM |  |  | CONTROL LOGIC DIAGRAM for STEAM DRAIN SYSTEM |  | FA | 1EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | 2007-03-15 | 2008-01-15 | 2024-09-25 | 2024-10-25 | 2024-11-24 | 2024-12-09 | 2024-12-24 | 2025-01-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161208 | CONTROL LOGIC DIAGRAM FOR CONDENSATE SYSTEM | CONTROL LOGIC DIAGRAM |  | CONDENSATE SYSTEM |  |  | CONTROL LOGIC DIAGRAM for CONDENSATE SYSTEM |  | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | 2024-10-13 | 2024-11-12 | 2024-12-12 | 2024-12-27 | 2025-01-11 | 2025-01-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161209 | CONTROL LOGIC DIAGRAM FOR FEEDWATER SYSTEM | CONTROL LOGIC DIAGRAM |  | FEEDWATER SYSTEM |  |  | CONTROL LOGIC DIAGRAM for FEEDWATER SYSTEM |  | FA | 0PF7000W86A02P | (Control Valve) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > Control Valves | 2007-10-01 | 2008-08-15 | 2025-04-13 | 2025-05-13 | 2025-06-12 | 2025-06-27 | 2025-07-12 | 2025-07-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161210 | CONTROL LOGIC DIAGRAM FOR CLOSED COOLING WATER SYSTEM | CONTROL LOGIC DIAGRAM |  | CLOSED COOLING WATER SYSTEM |  |  | CONTROL LOGIC DIAGRAM for CLOSED COOLING WATER SYSTEM |  | FA | 1PF3030W42A14P | (CCW H/EX) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-09-03 | 2008-07-16 | 2025-03-16 | 2025-04-15 | 2025-05-15 | 2025-05-30 | 2025-06-14 | 2025-06-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161211 | CONTROL LOGIC DIAGRAM FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | CONTROL LOGIC DIAGRAM |  | DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM |  |  | CONTROL LOGIC DIAGRAM for DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | Water Treatment System | FI | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161212 | CONTROL LOGIC DIAGRAM FOR GT ROTOR COOLING AIR SYSTEM | CONTROL LOGIC DIAGRAM |  | GT ROTOR COOLING AIR SYSTEM |  |  | CONTROL LOGIC DIAGRAM for GT ROTOR COOLING AIR SYSTEM |  | FA | 1PF1265W42A13.4P | (TCA Cooler) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Gas Supply System | 2007-03-01 | 2008-02-29 | 2024-05-23 | 2024-06-22 | 2024-07-22 | 2024-08-06 | 2024-08-21 | 2024-09-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161213 | CONTROL LOGIC DIAGRAM FOR GT PERFORMANCE HEATER SYSTEM | CONTROL LOGIC DIAGRAM |  | GT PERFORMANCE HEATER SYSTEM |  |  | CONTROL LOGIC DIAGRAM for GT PERFORMANCE HEATER SYSTEM |  | FA | 1PF3520W42A07.2P | (Gas HTR) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Heater | 2007-07-03 | 2008-04-01 | 2024-09-24 | 2024-10-24 | 2024-11-23 | 2024-12-08 | 2024-12-23 | 2025-01-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161214 | CONTROL LOGIC DIAGRAM FOR POTABLE WATER SYSTEM | CONTROL LOGIC DIAGRAM |  | POTABLE WATER SYSTEM |  |  | CONTROL LOGIC DIAGRAM for POTABLE WATER SYSTEM | FireFighting | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161216 | CONTROL LOGIC DIAGRAM FOR COMPRESSED AIR SYSTEM | CONTROL LOGIC DIAGRAM |  | COMPRESSED AIR SYSTEM |  |  | CONTROL LOGIC DIAGRAM for COMPRESSED AIR SYSTEM | Air Compressor | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161220 | CONTROL LOGIC DIAGRAM FOR ELECTRICAL SYSTEM | CONTROL LOGIC DIAGRAM |  | ELECTRICAL SYSTEM |  |  | CONTROL LOGIC DIAGRAM for ELECTRICAL SYSTEM |  | FA | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | 2024-12-11 | 2025-01-10 | 2025-02-09 | 2025-02-24 | 2025-03-11 | 2025-03-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161221 | CONTROL LOGIC DIAGRAM FOR INTERFACE WITH OTHER CONTROL SYSTEM | CONTROL LOGIC DIAGRAM |  |  |  |  | CONTROL LOGIC DIAGRAM |  | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | 2025-02-16 | 2025-03-18 | 2025-04-17 | 2025-05-02 | 2025-05-17 | 2025-06-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CBA-161222 | CONTROL LOGIC DIAGRAM FOR MISCELLANEOUS SYSTEM | CONTROL LOGIC DIAGRAM |  |  |  |  | CONTROL LOGIC DIAGRAM |  | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | 2025-02-16 | 2025-03-18 | 2025-04-17 | 2025-05-02 | 2025-05-17 | 2025-06-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161301 | CONTROL LOOP DIAGRAM - SYMBOL & LEGEND | CONTROL LOOP DIAGRAM |  |  |  |  | CONTROL LOOP DIAGRAM | FireFighting | FA | 0PF7000W86A02P | (Control Valve) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > Control Valves | 2007-10-01 | 2008-08-15 | 2025-02-18 | 2025-03-05 | 2025-03-20 | 2025-03-26 | 2025-04-10 | 2025-04-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161302 | CONTROL LOOP DIAGRAM - TYPICAL FUNCTION | CONTROL LOOP DIAGRAM |  |  |  |  | CONTROL LOOP DIAGRAM | FireFighting | FA | 0PF7000W86A02P | (Control Valve) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > Control Valves | 2007-10-01 | 2008-08-15 | 2025-02-18 | 2025-03-05 | 2025-03-20 | 2025-03-26 | 2025-04-10 | 2025-04-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161303 | CONTROL LOOP DIAGRAM FOR HP STEAM SYSTEM | CONTROL LOOP DIAGRAM |  | HP STEAM SYSTEM |  |  | CONTROL LOOP DIAGRAM for HP STEAM SYSTEM |  | FA | 1EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | 2024-10-13 | 2024-11-12 | 2024-12-12 | 2024-12-27 | 2025-01-11 | 2025-01-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161304 | CONTROL LOOP DIAGRAM FOR IP STEAM SYSTEM | CONTROL LOOP DIAGRAM |  | IP STEAM SYSTEM |  |  | CONTROL LOOP DIAGRAM for IP STEAM SYSTEM |  | FA | 0PF7000W86A02P | (Control Valve) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > Control Valves | 2007-10-01 | 2008-08-15 | 2025-04-13 | 2025-05-13 | 2025-06-12 | 2025-06-27 | 2025-07-12 | 2025-07-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161305 | CONTROL LOOP DIAGRAM FOR LP STEAM SYSTEM | CONTROL LOOP DIAGRAM |  | LP STEAM SYSTEM |  |  | CONTROL LOOP DIAGRAM for LP STEAM SYSTEM |  | FA | 3EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | 2024-10-13 | 2024-11-12 | 2024-12-12 | 2024-12-27 | 2025-01-11 | 2025-01-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161306 | CONTROL LOOP DIAGRAM FOR PROCESS STEAM SYSTEM | CONTROL LOOP DIAGRAM |  | PROCESS STEAM SYSTEM |  |  | CONTROL LOOP DIAGRAM for PROCESS STEAM SYSTEM |  | FA | 3EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | 2024-10-13 | 2024-11-12 | 2024-12-12 | 2024-12-27 | 2025-01-11 | 2025-01-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161307 | CONTROL LOOP DIAGRAM FOR STEAM DRAIN SYSTEM | CONTROL LOOP DIAGRAM |  | STEAM DRAIN SYSTEM |  |  | CONTROL LOOP DIAGRAM for STEAM DRAIN SYSTEM |  | FA | 1EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | 2007-03-15 | 2008-01-15 | 2024-09-25 | 2024-10-25 | 2024-11-24 | 2024-12-09 | 2024-12-24 | 2025-01-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161308 | CONTROL LOOP DIAGRAM FOR CONDENSATE SYSTEM | CONTROL LOOP DIAGRAM |  | CONDENSATE SYSTEM |  |  | CONTROL LOOP DIAGRAM for CONDENSATE SYSTEM |  | FA | 1EF3020W00A01 | (COND System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-04-02 | 2007-11-30 | 2024-10-13 | 2024-11-12 | 2024-12-12 | 2024-12-27 | 2025-01-11 | 2025-01-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161309 | CONTROL LOOP DIAGRAM FOR FEEDWATER SYSTEM | CONTROL LOOP DIAGRAM |  | FEEDWATER SYSTEM |  |  | CONTROL LOOP DIAGRAM for FEEDWATER SYSTEM | FireFighting | FA | 0PF7000W86A02P | (Control Valve) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > Control Valves | 2007-10-01 | 2008-08-15 | 2025-02-18 | 2025-03-05 | 2025-03-20 | 2025-03-26 | 2025-04-10 | 2025-04-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161310 | CONTROL LOOP DIAGRAM FOR CLOSED COOLING WATER SYSTEM | CONTROL LOOP DIAGRAM |  | CLOSED COOLING WATER SYSTEM |  |  | CONTROL LOOP DIAGRAM for CLOSED COOLING WATER SYSTEM | FireFighting | FA | 1SF3030W62A24 | (CCWS) Loop chek | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2008-10-19 | 2008-10-23 | 2026-03-09 | 2026-03-24 | 2026-04-08 | 2026-04-14 | 2026-04-29 | 2026-05-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161311 | CONTROL LOOP DIAGRAM FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | CONTROL LOOP DIAGRAM |  | DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM |  |  | CONTROL LOOP DIAGRAM for DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | Water Treatment System | FI | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161312 | CONTROL LOOP DIAGRAM FOR GT ROTOR COOLING AIR SYSTEM | CONTROL LOOP DIAGRAM |  | GT ROTOR COOLING AIR SYSTEM |  |  | CONTROL LOOP DIAGRAM for GT ROTOR COOLING AIR SYSTEM |  | FA | 3SF1265W62A18 | (Control Oil) Loop chek | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Auxiliary System | 2008-07-16 | 2008-07-20 | 2025-10-11 | 2025-11-10 | 2025-12-10 | 2025-12-25 | 2026-01-09 | 2026-01-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161313 | CONTROL LOOP DIAGRAM FOR GT PERFORMANCE HEATER SYSTEM | CONTROL LOOP DIAGRAM |  | GT PERFORMANCE HEATER SYSTEM |  |  | CONTROL LOOP DIAGRAM for GT PERFORMANCE HEATER SYSTEM |  | FA | 3SF3520W62A13.2 | (Gas HTR #32) Loop chek | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Heater | 2008-08-03 | 2008-08-05 | 2026-02-14 | 2026-03-16 | 2026-04-15 | 2026-04-30 | 2026-05-15 | 2026-05-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161314 | CONTROL LOOP DIAGRAM FOR POTABLE WATER SYSTEM | CONTROL LOOP DIAGRAM |  | POTABLE WATER SYSTEM |  |  | CONTROL LOOP DIAGRAM for POTABLE WATER SYSTEM | FireFighting | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | 2024-08-02 | 2024-08-17 | 2024-09-01 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161316 | CONTROL LOOP DIAGRAM FOR COMPRESSED AIR SYSTEM | CONTROL LOOP DIAGRAM |  | COMPRESSED AIR SYSTEM |  |  | CONTROL LOOP DIAGRAM for COMPRESSED AIR SYSTEM | Air Compressor | FA | 0EF3510W00A01.0 | (COMP Air System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-04-30 | 2007-12-12 | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161320 | CONTROL LOOP DIAGRAM FOR ELECTRICAL SYSTEM | CONTROL LOOP DIAGRAM |  | ELECTRICAL SYSTEM |  |  | CONTROL LOOP DIAGRAM for ELECTRICAL SYSTEM | FireFighting | FA | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | 2025-02-06 | 2025-02-21 | 2025-03-08 | 2025-03-14 | 2025-03-29 | 2025-04-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161321 | CONTROL LOOP DIAGRAM FOR INTERFACE WITH OTHER CONTROL SYSTEM | CONTROL LOOP DIAGRAM |  | control system |  |  | CONTROL LOOP DIAGRAM for control system | FireFighting | FA | 0SF7000W62A07 | (DCS) Loop Check | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2008-06-17 | 2008-07-01 | 2025-11-05 | 2025-11-20 | 2025-12-05 | 2025-12-11 | 2025-12-26 | 2026-01-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0CGA-161322 | CONTROL LOOP DIAGRAM FOR MISCELLANEOUS SYSTEM | CONTROL LOOP DIAGRAM |  |  |  |  | CONTROL LOOP DIAGRAM | FireFighting | FA | 0SF7000W62A07 | (DCS) Loop Check | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2008-06-17 | 2008-07-01 | 2025-11-05 | 2025-11-20 | 2025-12-05 | 2025-12-11 | 2025-12-26 | 2026-01-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CWQ-161401 | I&C EQUIPMENT LAYOUT DRAWING FOR CENTRAL CONTROL ROOM | LAYOUT DRAWING |  | Instrumentation & Control |  |  | Layout Drawing for Instrumentation & Control |  | FI | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | 2024-07-20 | 2024-08-19 | 2024-09-18 | 2024-10-03 | 2024-10-18 | 2024-11-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CWQ-161402 | I&C EQUIPMENT LAYOUT DRAWING FOR CENTRAL ELECTRONIC ROOM | LAYOUT DRAWING |  | Instrumentation & Control |  |  | Layout Drawing for Instrumentation & Control |  | FI | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | 2024-07-20 | 2024-08-19 | 2024-09-18 | 2024-10-03 | 2024-10-18 | 2024-11-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CWQ-161403 | I&C EQUIPMENT LAYOUT DRAWING FOR COMPUTER ROOM | LAYOUT DRAWING |  | Instrumentation & Control |  |  | Layout Drawing for Instrumentation & Control |  | FI | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | 2024-07-20 | 2024-08-19 | 2024-09-18 | 2024-10-03 | 2024-10-18 | 2024-11-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CWQ-161404 | I&C EQUIPMENT LAYOUT DRAWING FOR IT & COMMUNICATION ROOM | LAYOUT DRAWING |  | Instrumentation & Control |  |  | Layout Drawing for Instrumentation & Control |  | FI | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | 2024-07-20 | 2024-08-19 | 2024-09-18 | 2024-10-03 | 2024-10-18 | 2024-11-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CWQ-161405 | I&C EQUIPMENT LAYOUT DRAWING FOR GTG #1,2 LEB LOCAL ELECTRICAL & ELECTRONIC ROOM | LAYOUT DRAWING | Gas Turbine Generator | Instrumentation & Control | Local Electrical Building LOCAL ELECTRICAL & ELECTRONIC ROOM |  | Layout Drawing for GTG | Substation | SKIP | 2CF1200W90A09 | (GTG #21 LEB) Installation & Test - I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2008-06-04 | 2008-08-04 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CWQ-161406 | I&C EQUIPMENT LAYOUT DRAWING FOR GTG #3,4,5 LEB LOCAL ELECTRICAL & ELECTRONIC ROOM | LAYOUT DRAWING | Gas Turbine Generator | Instrumentation & Control | Local Electrical Building LOCAL ELECTRICAL & ELECTRONIC ROOM |  | Layout Drawing for GTG | Substation | SKIP | 3CF1200W90A09 | (GTG #31 LEB) Installation & Test - I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2008-06-04 | 2008-08-04 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CWQ-161407 | I&C EQUIPMENT LAYOUT DRAWING FOR ST #1 LEB LOCAL ELECTRICAL & ELECTRONIC ROOM | LAYOUT DRAWING | Steam Turbine | Instrumentation & Control | Local Electrical Building LOCAL ELECTRICAL & ELECTRONIC ROOM |  | Layout Drawing for STG | Substation | SKIP | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CWQ-161408 | I&C EQUIPMENT LAYOUT DRAWING FOR ST #2 LEB LOCAL ELECTRICAL & ELECTRONIC ROOM | LAYOUT DRAWING | Steam Turbine | Instrumentation & Control | Local Electrical Building LOCAL ELECTRICAL & ELECTRONIC ROOM |  | Layout Drawing for STG | Substation | SKIP | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0CWQ-161409 | I&C EQUIPMENT LAYOUT DRAWING FOR FGS ELECTRICAL BUILDING LOCAL ELECTRONIC ROOM | LAYOUT DRAWING |  | Fuel Gas System | ELECTRICAL BUILDING LOCAL ELECTRONIC ROOM |  | Layout Drawing for Fuel Gas System | Fuel Gas System | FA | 0CF3520W90A09.1 | (FGS LEB) Installation & Test - I&C | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2008-01-11 | 2008-03-08 | 2025-05-03 | 2025-06-28 | 2025-08-23 | 2025-07-19 | 2025-09-13 | 2025-11-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL00-P0ZEN-163101 | FIELD INSTRUMENT LIST FOR BOP | LIST |  |  |  |  | LIST |  | FA | 0EF6020W00A05 | (BOP Piping) Valve List | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-04-30 | 2008-01-03 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-163102 | TECHNICAL SPECIFICATION & DATA SHEET FOR LOCAL INSTRUMENT - BOP | TECHNICAL SPECIFICATION & DATA SHEET |  |  |  |  | TECHNICAL SPECIFICATION & DATA SHEET |  | FA | 0EF6020W00A02 | (BOP Piping) Pipe Material Specification | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-03-01 | 2008-01-28 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-163103 | TECHNICAL SPECIFICATION & DATA SHEET FOR PROCESS TRANSMITTER - BOP | TECHNICAL SPECIFICATION & DATA SHEET |  |  |  |  | TECHNICAL SPECIFICATION & DATA SHEET |  | FA | 0EF6020W00A02 | (BOP Piping) Pipe Material Specification | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-03-01 | 2008-01-28 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-163104 | TECHNICAL SPECIFICATION & DATA SHEET FOR FLOW ELEMENT - BOP | TECHNICAL SPECIFICATION & DATA SHEET | Flow element |  |  |  | TECHNICAL SPECIFICATION & DATA SHEET for Flow element | FloW element | FA | 0EF6020W00A02 | (BOP Piping) Pipe Material Specification | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-03-01 | 2008-01-28 | 2024-03-15 | 2024-04-14 | 2024-05-14 | 2024-05-29 | 2024-06-13 | 2024-06-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-163201 | TECHNICAL SPECIFICATION & DATA SHEET FOR CONTROL VALVE - BOP | TECHNICAL SPECIFICATION & DATA SHEET | CONTROL VALVE |  |  |  | TECHNICAL SPECIFICATION & DATA SHEET for CONTROL VALVE | CONTROL VALVE | FA | 0PF7000W86A02P | (Control Valve) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > Control Valves | 2007-10-01 | 2008-08-15 | 2024-10-15 | 2024-11-14 | 2024-12-14 | 2024-12-29 | 2025-01-13 | 2025-01-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0EKU-163202 | TECHNICAL SPECIFICATION & DATA SHEET FOR GAS METERING SYSTEM | TECHNICAL SPECIFICATION & DATA SHEET |  | Gas Metering System |  |  | TECHNICAL SPECIFICATION & DATA SHEET for Gas Metering System | Process Metering | FA | 0PF3520W42A02P | (FO Metering Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Metering System | 2007-06-29 | 2008-03-17 | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0UCL-163203 | TECHNICAL SPECIFICATION & DATA SHEET FOR STEAM/WATER METERING SYSTEM | TECHNICAL SPECIFICATION & DATA SHEET |  |  |  |  | TECHNICAL SPECIFICATION & DATA SHEET |  | FA | 0PF6500W70A02.7P | (Power Metering Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power Metering System | 2007-07-13 | 2008-02-12 | 2024-08-10 | 2024-09-09 | 2024-10-09 | 2024-10-24 | 2024-11-08 | 2024-11-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-163204 | TECHNICAL SPECIFICATION & DATA SHEET FOR WEATHER STATION | TECHNICAL SPECIFICATION & DATA SHEET |  |  |  |  | TECHNICAL SPECIFICATION & DATA SHEET |  | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | 2024-08-29 | 2024-09-28 | 2024-10-28 | 2024-11-12 | 2024-11-27 | 2024-12-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163301 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM - INDEX | DIAGRAM | DCS |  |  |  | Diagram for DCS |  | FA | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | 2025-06-14 | 2025-07-05 | 2025-07-26 | 2025-08-19 | 2025-09-03 | 2025-09-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163302 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MV SWGR INCOMER | ELEMENTARY WIRING DIAGRAM | DCS |  |  |  | ELEMENTARY WIRING DIAGRAM for DCS |  | FA | 0PF6500W70A02.2P | (MV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > MV Switchgears With Auxiliaries | 2007-07-03 | 2008-03-31 | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163303 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MV SWGR MOTOR FEEDER | ELEMENTARY WIRING DIAGRAM | DCS |  |  |  | ELEMENTARY WIRING DIAGRAM for DCS |  | FA | 0PF6500W70A02.2P | (MV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > MV Switchgears With Auxiliaries | 2007-07-03 | 2008-03-31 | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163304 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MV SWGR TR FEEDER | ELEMENTARY WIRING DIAGRAM | DCS |  |  |  | ELEMENTARY WIRING DIAGRAM for DCS |  | FA | 0PF6500W70A02.2P | (MV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > MV Switchgears With Auxiliaries | 2007-07-03 | 2008-03-31 | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163305 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MV SWGR BUS TIE | ELEMENTARY WIRING DIAGRAM | DCS |  |  |  | ELEMENTARY WIRING DIAGRAM for DCS |  | FA | 0PF6500W70A02.2P | (MV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > MV Switchgears With Auxiliaries | 2007-07-03 | 2008-03-31 | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163306 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MV SWGR UNIT/COMMON TIE | ELEMENTARY WIRING DIAGRAM | DCS |  |  |  | ELEMENTARY WIRING DIAGRAM for DCS |  | FA | 0PF6500W70A02.2P | (MV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > MV Switchgears With Auxiliaries | 2007-07-03 | 2008-03-31 | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163307 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR PT PANEL | ELEMENTARY WIRING DIAGRAM | DCS |  |  |  | ELEMENTARY WIRING DIAGRAM for DCS |  | FA | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163308 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR INCOMER | ELEMENTARY WIRING DIAGRAM | DCS |  |  |  | ELEMENTARY WIRING DIAGRAM for DCS |  | FA | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2007-07-03 | 2008-03-31 | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163309 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR MOTOR FEEDER (ACB) | ELEMENTARY WIRING DIAGRAM | DCS |  |  |  | ELEMENTARY WIRING DIAGRAM for DCS |  | FA | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2007-07-03 | 2008-03-31 | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163310 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR MOTOR FEEDER (MCCB) | ELEMENTARY WIRING DIAGRAM | DCS |  |  |  | ELEMENTARY WIRING DIAGRAM for DCS |  | FA | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2007-07-03 | 2008-03-31 | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163311 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR NON MOTOR FEEDER (ACB) | ELEMENTARY WIRING DIAGRAM | DCS |  |  |  | ELEMENTARY WIRING DIAGRAM for DCS |  | FA | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2007-07-03 | 2008-03-31 | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163312 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR NON MOTOR FEEDER (MCCB EHS) | DIAGRAM | DCS |  |  |  | Diagram for DCS |  | FA | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2007-07-03 | 2008-03-31 | 2025-07-02 | 2025-07-23 | 2025-08-13 | 2025-09-06 | 2025-09-21 | 2025-10-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163313 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR BUS TIE | DIAGRAM | DCS |  |  |  | Diagram for DCS |  | FA | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2007-07-03 | 2008-03-31 | 2025-07-02 | 2025-07-23 | 2025-08-13 | 2025-09-06 | 2025-09-21 | 2025-10-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163314 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR ANALOG INPUT | DIAGRAM | DCS |  |  |  | Diagram for DCS |  | FA | 0EF1000W00A09 | DCS I/O List of Overall Plant | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-12-31 | 2025-04-29 | 2025-05-20 | 2025-06-10 | 2025-07-04 | 2025-07-19 | 2025-08-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163315 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR ANALOG OUTPUT | DIAGRAM | DCS |  |  |  | Diagram for DCS |  | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | 2025-07-31 | 2025-08-21 | 2025-09-11 | 2025-10-05 | 2025-10-20 | 2025-11-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163316 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR BINARY INPUT | DIAGRAM | DCS |  |  |  | Diagram for DCS |  | FA | 0EF1000W00A09 | DCS I/O List of Overall Plant | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-12-31 | 2025-04-29 | 2025-05-20 | 2025-06-10 | 2025-07-04 | 2025-07-19 | 2025-08-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163317 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR BINARY OUTPUT | DIAGRAM | DCS |  |  |  | Diagram for DCS |  | FA | 0PF7000W86A02.1P | (DCS) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-06-15 | 2008-04-16 | 2025-06-14 | 2025-07-05 | 2025-07-26 | 2025-08-19 | 2025-09-03 | 2025-09-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163318 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR PNEUMATIC CONTROL VALVE - MODULATING | DIAGRAM | CONTROL VALVE |  |  |  | Diagram for CONTROL VALVE | CONTROL VALVE | FI | 0PF7000W86A04T | (Control Valve) 1st Delivery(On site) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > Control Valves |  | 2008-05-15 | 2025-02-17 | 2025-03-19 | 2025-04-18 | 2025-05-03 | 2025-05-18 | 2025-06-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163319 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR PNEUMATIC SHUT - OFF VALVE (SOLENOID VALVE) | DIAGRAM | valve |  |  |  | Diagram for valve | Motor Operated Valve | FI | 0PF6050W86A03.1P | (Safety Valve) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Safety Valve | 2007-09-14 | 2008-05-23 | 2024-11-09 | 2024-12-09 | 2025-01-08 | 2025-01-23 | 2025-02-07 | 2025-02-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163320 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MOTOR OPERATED VALVE - INTERNAL MCC | DIAGRAM | MOV |  |  |  | Diagram for MOV |  | FA | 0EF6050W86A02 | (MOV) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Motor Operation Valve |  | 2007-07-13 | [6 empty] | missing_date |  | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0ZEN-163321 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MOTOR OPERATED VALVE - FIELDBUS | DIAGRAM | MOV |  |  |  | Diagram for MOV |  | FA | 0PF6050W86A03P | (MOV) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Motor Operation Valve | 2007-09-14 | 2008-04-30 | 2024-11-09 | 2024-12-09 | 2025-01-08 | 2025-01-23 | 2025-02-07 | 2025-02-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-163331 | TECHNICAL SPECIFICATION & DATA SHEET FOR VIBRATION MONITORING SYSTEM | TECHNICAL SPECIFICATION & DATA SHEET |  | Vibration measurement system |  |  | TECHNICAL SPECIFICATION & DATA SHEET for Vibration measurement system |  | FA | 1PF1260W86A02.1P | (VMS) P.O & Procurement for GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Vibration Monitoring System (VMS) | 2007-08-31 | 2008-05-01 | 2024-09-28 | 2024-10-28 | 2024-11-27 | 2024-12-12 | 2024-12-27 | 2025-01-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF02-P0SAY-163401 | CONTROL SYSTEM CONFIGURATION DIAGRAM FOR HVAC | CONFIGURATION DIAGRAM |  | Heating, Ventilating and Air - Conditioning System |  |  | CONFIGURATION DIAGRAM for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | 2024-09-10 | 2024-10-10 | 2024-11-09 | 2024-11-24 | 2024-12-09 | 2024-12-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL01-P0SAY-163402 | I/O LIST FOR HVAC | LIST |  | Heating, Ventilating and Air - Conditioning System |  |  | LIST for Heating, Ventilating and Air - Conditioning System | Air Compressor | FI | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 | 2024-10-10 | 2024-11-09 | 2024-12-09 | 2024-12-24 | 2025-01-08 | 2025-01-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0SAY-163403 | TECHNICAL SPECIFICATION & DATA SHEET FOR FIELD INSTRUMENT - HVAC | TECHNICAL SPECIFICATION & DATA SHEET |  | Heating, Ventilating and Air - Conditioning System |  |  | TECHNICAL SPECIFICATION & DATA SHEET for Heating, Ventilating and Air - Conditioning System |  | FA | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 | 2024-08-29 | 2024-09-28 | 2024-10-28 | 2024-11-12 | 2024-11-27 | 2024-12-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0SAY-163404 | INSTRUMENT INSTALLATION DETAIL DRAWING FOR HVAC | DRAWING |  | Heating, Ventilating and Air - Conditioning System |  |  | DRAWING for Heating, Ventilating and Air - Conditioning System |  | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | 2024-08-17 | 2024-09-16 | 2024-10-16 | 2024-10-31 | 2024-11-15 | 2024-11-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0SAY-163405 | CONTROL LOGIC & LOOP DIAGRAM FOR HVAC | DIAGRAM |  | Heating, Ventilating and Air - Conditioning System |  |  | Diagram for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | 2024-06-24 | 2024-07-24 | 2024-08-23 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0SAY-163406 | I&C CABLE SCHEDULE FOR HVAC | SCHEDULE |  | Heating, Ventilating and Air - Conditioning System |  |  | Schedule for Heating, Ventilating and Air - Conditioning System | Air Compressor | FA | 0PF5000W36A04T | (HVAC Equipment) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2008-03-29 | 2008-07-30 | [6 empty] | generated |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0SAY-163407 | I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR HVAC | DIAGRAM |  | Heating, Ventilating and Air - Conditioning System |  |  | Diagram for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | 2024-06-24 | 2024-07-24 | 2024-08-23 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163408 | HVAC I&C CABLE RACEWAY DRAWING FOR CCB | DRAWING |  | Heating, Ventilating and Air - Conditioning System | CCB |  | DRAWING for Heating, Ventilating and Air - Conditioning System |  | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | 2024-08-17 | 2024-09-16 | 2024-10-16 | 2024-10-31 | 2024-11-15 | 2024-11-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163409 | HVAC I&C CABLE RACEWAY DRAWING FOR STEAM TURBINE BUILDING | DRAWING |  | Heating, Ventilating and Air - Conditioning System | STEAM TURBINE BUILDING |  | DRAWING for Heating, Ventilating and Air - Conditioning System |  | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | 2024-08-17 | 2024-09-16 | 2024-10-16 | 2024-10-31 | 2024-11-15 | 2024-11-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163411 | HVAC I&C CABLE RACEWAY DRAWING FOR STG ELECTRICAL BUILDING FOR #1 | DRAWING | Steam Turbine & Generator | Heating, Ventilating and Air - Conditioning System | ELECTRICAL BUILDING |  | DRAWING for STG |  | FA | 1CF2010W36A10 | (STG #10 BLDG) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2008-10-13 | 2008-12-08 | 2026-04-19 | 2026-05-19 | 2026-06-18 | 2026-07-03 | 2026-07-18 | 2026-08-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163412 | HVAC I&C CABLE RACEWAY DRAWING FOR STG ELECTRICAL BUILDING FOR #2 | DRAWING | Steam Turbine & Generator | Heating, Ventilating and Air - Conditioning System | ELECTRICAL BUILDING |  | DRAWING for STG |  | FA | 2CF2010W36A10 | (STG #20 BLDG) Installation & Test - HVAC | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2008-10-13 | 2008-12-08 | 2026-04-19 | 2026-05-19 | 2026-06-18 | 2026-07-03 | 2026-07-18 | 2026-08-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163413 | HVAC I&C CABLE RACEWAY DRAWING FOR GTG ELECTRICAL BUILDING FOR #1,2 | DRAWING | Gas Turbine Generator | Heating, Ventilating and Air - Conditioning System | ELECTRICAL BUILDING |  | DRAWING for GTG |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | 2024-07-26 | 2024-08-25 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163414 | HVAC I&C CABLE RACEWAY DRAWING FOR GTG ELECTRICAL BUILDING FOR #3, 4, 5 | DRAWING | Gas Turbine Generator | Heating, Ventilating and Air - Conditioning System | ELECTRICAL BUILDING |  | DRAWING for GTG |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | 2024-07-26 | 2024-08-25 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163415 | HVAC I&C CABLE RACEWAY DRAWING FOR MAIN ADMINISTRATION BUILDING /W SOCIAL FACILITIES BUILDING | DRAWING |  | Heating, Ventilating and Air - Conditioning System | MAIN ADMINISTRATION BUILDING /W SOCIAL FACILITIES BUILDING |  | DRAWING for Heating, Ventilating and Air - Conditioning System |  | FI | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 | 2025-01-02 | 2025-02-01 | 2025-03-03 | 2025-03-18 | 2025-04-02 | 2025-04-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163416 | HVAC I&C CABLE RACEWAY DRAWING FOR SECURITY BUILDING | DRAWING |  | Heating, Ventilating and Air - Conditioning System | SECURITY BUILDING |  | DRAWING for Heating, Ventilating and Air - Conditioning System |  | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | 2024-08-17 | 2024-09-16 | 2024-10-16 | 2024-10-31 | 2024-11-15 | 2024-11-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163417 | HVAC I&C CABLE RACEWAY DRAWING FOR FIRE BRIGADE & AUX LEB | DRAWING |  | Heating, Ventilating and Air - Conditioning System | FIRE BRIGADE & AUX. LEB |  | DRAWING for Heating, Ventilating and Air - Conditioning System |  | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | 2024-08-17 | 2024-09-16 | 2024-10-16 | 2024-10-31 | 2024-11-15 | 2024-11-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163418 | HVAC I&C CABLE RACEWAY DRAWING FOR MAINTENANCE AND WORKSHOP BUILDING /W WAREHOUSE | DRAWING |  | Heating, Ventilating and Air - Conditioning System | MAINTENANCE AND WORKSHOP BUILDING /W WAREHOUSE |  | DRAWING for Heating, Ventilating and Air - Conditioning System |  | FI | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 | 2025-01-02 | 2025-02-01 | 2025-03-03 | 2025-03-18 | 2025-04-02 | 2025-04-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163419 | HVAC I&C CABLE RACEWAY DRAWING FOR FGS ELECTRICAL BUILDING | DRAWING |  | Heating, Ventilating and Air - Conditioning System | FGS ELECTRICAL BUILDING |  | DRAWING for Heating, Ventilating and Air - Conditioning System |  | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | 2024-08-17 | 2024-09-16 | 2024-10-16 | 2024-10-31 | 2024-11-15 | 2024-11-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163420 | HVAC I&C CABLE RACEWAY DRAWING FOR FIRE WATER PUMP HOUSE | DRAWING |  | Heating, Ventilating and Air - Conditioning System | FIRE WATER PUMP HOUSE |  | DRAWING for Heating, Ventilating and Air - Conditioning System |  | FI | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 | 2025-01-02 | 2025-02-01 | 2025-03-03 | 2025-03-18 | 2025-04-02 | 2025-04-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163421 | HVAC I&C CABLE RACEWAY DRAWING FOR WATER TREATMENT BUILDING /W MAIN LABORATORY | DRAWING |  | Heating, Ventilating and Air - Conditioning System | WATER TREATMENT BUILDING /W MAIN LABORATORY |  | DRAWING for Heating, Ventilating and Air - Conditioning System |  | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | 2024-08-17 | 2024-09-16 | 2024-10-16 | 2024-10-31 | 2024-11-15 | 2024-11-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163422 | HVAC I&C CABLE RACEWAY DRAWING FOR CPP BUILDING | DRAWING |  | Heating, Ventilating and Air - Conditioning System | CPP BUILDING |  | DRAWING for Heating, Ventilating and Air - Conditioning System |  | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | 2024-08-17 | 2024-09-16 | 2024-10-16 | 2024-10-31 | 2024-11-15 | 2024-11-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0SAY-163423 | CONTROL PANEL OUTLINE & DETAIL DRAWING FOR HVAC | DRAWING |  | Heating, Ventilating and Air - Conditioning System |  |  | DRAWING for Heating, Ventilating and Air - Conditioning System |  | FI | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | 2024-08-17 | 2024-09-16 | 2024-10-16 | 2024-10-31 | 2024-11-15 | 2024-11-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD05-P0SAY-163424 | HMI GRAPHIC DISPLAY DIAGRAM FOR HVAC | DIAGRAM |  | Heating, Ventilating and Air - Conditioning System |  |  | Diagram for Heating, Ventilating and Air - Conditioning System |  | FA | 0EF5000W00A01 | (HVAC System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-03-30 | 2007-11-01 | 2024-06-24 | 2024-07-24 | 2024-08-23 | 2024-09-07 | 2024-09-22 | 2024-10-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0SAY-163425 | TECHNICAL SPECIFICATION - HVAC CONTROL SYSTEM | TECHNICAL SPECIFICATION |  | HVAC CONTROL SYSTEM |  |  | Technical Specification for HVAC CONTROL SYSTEM |  | FA | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 | 2025-01-26 | 2025-02-25 | 2025-03-27 | 2025-04-11 | 2025-04-26 | 2025-05-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0SAC-163426 | HVAC I&C CABLE RACEWAY DRAWING FOR MAIN GATE HOUSE AREA | DRAWING |  | Heating, Ventilating and Air - Conditioning System | MAIN GATE HOUSE AREA |  | DRAWING for Heating, Ventilating and Air - Conditioning System |  | FI | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > HVAC System | 2007-08-15 | 2008-06-11 | 2025-01-02 | 2025-02-01 | 2025-03-03 | 2025-03-18 | 2025-04-02 | 2025-04-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XW01-P0ZEN-165001 | DESIGN CRITERIA FOR I&C CABLE | DESIGN CRITERIA |  |  |  |  | DESIGN CRITERIA |  | FI | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-03-01 | 2024-03-15 | 2024-04-14 | 2024-04-29 | 2024-05-14 | 2024-05-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL02-P0ZEN-165011 | I&C CABLE PRINCIPLE DIAGRAM | PRINCIPLE DIAGRAM |  |  |  |  | PRINCIPLE DIAGRAM |  | FA | 1EF6040W16A01 | (Cable tunnel) Cable tunnel Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2007-11-30 |  |  |  | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165301 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - CONTROL VALVE | DRAWINGS | CONTROL VALVE |  |  |  | DRAWINGS for CONTROL VALVE | CONTROL VALVE | FA | 0PF7000W86A02P | (Control Valve) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > Control Valves | 2007-10-01 | 2008-08-15 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165302 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - MOV | DRAWINGS | MOV |  |  |  | DRAWINGS for MOV |  | FA | 0PF6050W86A03P | (MOV) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement > Motor Operation Valve | 2007-09-14 | 2008-04-30 | 2025-05-27 | 2025-06-26 | 2025-07-26 | 2025-08-10 | 2025-08-25 | 2025-09-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165303 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - INSTRUMENT RACK AND JUNCTION BOX | CABLE INSTALLATION DRAWINGS | Instrument Rack, Junction Box | Instrumentation & Control |  |  | CABLE INSTALLATION DRAWINGS for Instrument Rack, Junction Box |  | FA | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | 2024-11-14 | 2024-12-14 | 2025-01-13 | 2025-01-28 | 2025-02-12 | 2025-02-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165304 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - FIELD INSTRUMENT | CABLE INSTALLATION DRAWINGS |  | Instrumentation & Control |  |  | CABLE INSTALLATION DRAWINGS for Instrumentation & Control |  | FA | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | 2025-01-31 | 2025-03-02 | 2025-04-01 | 2025-04-16 | 2025-05-01 | 2025-05-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165305 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - CONDUIT SUPPORT | CABLE INSTALLATION DRAWINGS |  | Instrumentation & Control |  |  | CABLE INSTALLATION DRAWINGS for Instrumentation & Control |  | FA | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | 2025-01-31 | 2025-03-02 | 2025-04-01 | 2025-04-16 | 2025-05-01 | 2025-05-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165311 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS - GENERAL NOTE | DETAIL DRAWINGS | Balance of Plant | INSTRUMENT INSTALLATION MATERIAL |  |  | DETAIL DRAWINGS for BOP |  | FA | 0EF1000W00A10 | Instrument Installation Detail | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-05-11 | 2007-09-28 | 2024-09-22 | 2024-10-22 | 2024-11-21 | 2024-12-06 | 2024-12-21 | 2025-01-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165312 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS - SYMBOL & LEGEND | DETAIL DRAWINGS | Balance of Plant | INSTRUMENT INSTALLATION MATERIAL |  |  | DETAIL DRAWINGS for BOP |  | FA | 0EF1000W00A10 | Instrument Installation Detail | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-05-11 | 2007-09-28 | 2024-09-22 | 2024-10-22 | 2024-11-21 | 2024-12-06 | 2024-12-21 | 2025-01-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165313 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS - MATERIAL LISTS | DETAIL DRAWINGS | Balance of Plant | INSTRUMENT INSTALLATION MATERIAL |  |  | DETAIL DRAWINGS for BOP |  | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | 2025-01-26 | 2025-02-25 | 2025-03-27 | 2025-04-11 | 2025-04-26 | 2025-05-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165314 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR FLOW TRANSMITTER | DETAIL DRAWINGS | Balance of Plant | INSTRUMENT INSTALLATION MATERIAL |  |  | DETAIL DRAWINGS for BOP |  | FA | 0EF1000W00A10 | Instrument Installation Detail | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-05-11 | 2007-09-28 | 2024-09-22 | 2024-10-22 | 2024-11-21 | 2024-12-06 | 2024-12-21 | 2025-01-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165315 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR LEVEL TRANSMITTER | DETAIL DRAWINGS | Balance of Plant | INSTRUMENT INSTALLATION MATERIAL |  |  | DETAIL DRAWINGS for BOP |  | FA | 0EF1000W00A10 | Instrument Installation Detail | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-05-11 | 2007-09-28 | 2024-09-22 | 2024-10-22 | 2024-11-21 | 2024-12-06 | 2024-12-21 | 2025-01-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165316 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR PRESSURE TRANSMITTER | DETAIL DRAWINGS | Balance of Plant | INSTRUMENT INSTALLATION MATERIAL |  |  | DETAIL DRAWINGS for BOP |  | FA | 0EF1000W00A10 | Instrument Installation Detail | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-05-11 | 2007-09-28 | 2024-09-22 | 2024-10-22 | 2024-11-21 | 2024-12-06 | 2024-12-21 | 2025-01-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165317 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR DIFF. PRESSURE TRANSMITTER | DETAIL DRAWINGS | Balance of Plant | INSTRUMENT INSTALLATION MATERIAL |  |  | DETAIL DRAWINGS for BOP |  | FA | 0EF1000W00A10 | Instrument Installation Detail | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-05-11 | 2007-09-28 | 2024-09-22 | 2024-10-22 | 2024-11-21 | 2024-12-06 | 2024-12-21 | 2025-01-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165318 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR PRESSURE GAUGE | DETAIL DRAWINGS | Balance of Plant | INSTRUMENT INSTALLATION MATERIAL |  |  | DETAIL DRAWINGS for BOP |  | FA | 0EF1000W00A10 | Instrument Installation Detail | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-05-11 | 2007-09-28 | 2024-09-22 | 2024-10-22 | 2024-11-21 | 2024-12-06 | 2024-12-21 | 2025-01-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165319 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR TEMPERATURE TRANSMITTER (RTD/TC) | DETAIL DRAWINGS | Balance of Plant | INSTRUMENT INSTALLATION MATERIAL |  |  | DETAIL DRAWINGS for BOP |  | FA | 0EF1000W00A10 | Instrument Installation Detail | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-05-11 | 2007-09-28 | 2024-09-22 | 2024-10-22 | 2024-11-21 | 2024-12-06 | 2024-12-21 | 2025-01-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165320 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR TEMPERATURE GAUGE | DETAIL DRAWINGS | Balance of Plant | INSTRUMENT INSTALLATION MATERIAL |  |  | DETAIL DRAWINGS for BOP |  | FA | 0EF1000W00A10 | Instrument Installation Detail | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-05-11 | 2007-09-28 | 2024-09-22 | 2024-10-22 | 2024-11-21 | 2024-12-06 | 2024-12-21 | 2025-01-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165321 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR TEST WELL | DETAIL DRAWINGS | Balance of Plant | INSTRUMENT INSTALLATION MATERIAL |  |  | DETAIL DRAWINGS for BOP |  | FA | 0EF1000W00A10 | Instrument Installation Detail | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-05-11 | 2007-09-28 | 2024-09-22 | 2024-10-22 | 2024-11-21 | 2024-12-06 | 2024-12-21 | 2025-01-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165322 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR PNEUMATIC CONTROL VALVES | DETAIL DRAWINGS | Balance of Plant, CONTROL VALVE | INSTRUMENT INSTALLATION MATERIAL |  |  | DETAIL DRAWINGS for Balance of Plant, CONTROL VALVE | CONTROL VALVE | FA | 0PF7000W86A02P | (Control Valve) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > Control Valves | 2007-10-01 | 2008-08-15 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK00-P0ZEN-165323 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR STANCHION & RACK | DETAIL DRAWINGS | Balance of Plant, Instrument Rack | INSTRUMENT INSTALLATION MATERIAL |  |  | DETAIL DRAWINGS for Balance of Plant, Instrument Rack |  | FA | 1PF5550W46A08P | (PipeRack) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-06-28 | 2008-01-02 | 2024-11-09 | 2024-12-09 | 2025-01-08 | 2025-01-23 | 2025-02-07 | 2025-02-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165501 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR CENTRAL CONTROL BUILDING | LAYOUT AND DRAWING | Balance of Plant |  | CENTRAL CONTROL BUILDING |  | LAYOUT AND DRAWING for BOP | Substation | SKIP | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165502 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR GTG #1,2 LEB | LAYOUT AND DRAWING | Balance of Plant, Gas Turbine Generator |  | Local Electrical Building |  | LAYOUT AND DRAWING for Balance of Plant, Gas Turbine Generator |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-08-28 | 2024-09-27 | 2024-10-27 | 2024-11-11 | 2024-11-26 | 2024-12-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165503 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR GTG #3,4,5 LEB | LAYOUT AND DRAWING | Balance of Plant, Gas Turbine Generator |  | Local Electrical Building |  | LAYOUT AND DRAWING for Balance of Plant, Gas Turbine Generator |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-08-28 | 2024-09-27 | 2024-10-27 | 2024-11-11 | 2024-11-26 | 2024-12-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165504 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR ST #1 LEB | LAYOUT AND DRAWING | Balance of Plant, Steam Turbine |  | Local Electrical Building |  | LAYOUT AND DRAWING for Balance of Plant, Steam Turbine | STEAM TURBINE GENERATOR | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 |  |  |  | 2024-03-01 | 2024-03-19 | 2024-04-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165505 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR ST #2 LEB | LAYOUT AND INSTRUMENT LOCATION DRAWING | Balance of Plant |  | Local Electrical Building |  | LAYOUT AND INSTRUMENT LOCATION DRAWING for BOP |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165506 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR ST BUILDING | LAYOUT AND INSTRUMENT LOCATION DRAWING | Balance of Plant |  | ST Building |  | LAYOUT AND INSTRUMENT LOCATION DRAWING for BOP |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165507 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR FGS ELECTRICAL BUILDING | LAYOUT AND INSTRUMENT LOCATION DRAWING | Balance of Plant | Fuel Gas System | ELECTRICAL BUILDING |  | LAYOUT AND INSTRUMENT LOCATION DRAWING for BOP |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165508 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR ADMINISTRATION & SOCIAL BUILDING | LAYOUT AND INSTRUMENT LOCATION DRAWING | Balance of Plant |  | ADMINISTRATION & SOCIAL BUILDING |  | LAYOUT AND INSTRUMENT LOCATION DRAWING for BOP |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165509 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR SECURITY BUILDING | LAYOUT AND INSTRUMENT LOCATION DRAWING | Balance of Plant |  | SECURITY BUILDING |  | LAYOUT AND INSTRUMENT LOCATION DRAWING for BOP |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165510 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR MAIN GATE HOUSE AREA | LAYOUT AND INSTRUMENT LOCATION DRAWING | Balance of Plant |  | GATE House |  | LAYOUT AND INSTRUMENT LOCATION DRAWING for BOP |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165514 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR FIRE BRIGADE | LAYOUT AND INSTRUMENT LOCATION DRAWING | Balance of Plant |  | FIRE BRIGADE |  | LAYOUT AND INSTRUMENT LOCATION DRAWING for BOP |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165515 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR WORKSHOP & STORAGE BUILDING | LAYOUT AND INSTRUMENT LOCATION DRAWING | Balance of Plant |  | WORKSHOP & STORAGE BUILDING |  | LAYOUT AND INSTRUMENT LOCATION DRAWING for BOP |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165516 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR H2, CO2, N2 STORAGE SHELTER | LAYOUT AND INSTRUMENT LOCATION DRAWING | Balance of Plant |  | H2, CO2, N2 STORAGE SHELTER |  | LAYOUT AND INSTRUMENT LOCATION DRAWING for BOP |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165517 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR AIR COMPRESSOR SHELTER | LAYOUT AND INSTRUMENT LOCATION DRAWING | Balance of Plant |  | AIR COMPRESSOR SHELTER |  | LAYOUT AND INSTRUMENT LOCATION DRAWING for BOP |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165518 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR DEAERATOR SUPPORT STRUCTURE | LAYOUT AND INSTRUMENT LOCATION DRAWING | Balance of Plant |  |  |  | LAYOUT AND INSTRUMENT LOCATION DRAWING for BOP |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165519 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR FIRE WATER PUMP HOUSE & FIN FAN COOLER (CPP) | LAYOUT AND INSTRUMENT LOCATION DRAWING | Balance of Plant |  | Fire Pump House |  | LAYOUT AND INSTRUMENT LOCATION DRAWING for BOP |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165520 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | LAYOUT AND INSTRUMENT LOCATION DRAWING | Balance of Plant |  | WWT/WT Shelter |  | LAYOUT AND INSTRUMENT LOCATION DRAWING for BOP |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165521 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR WATER TREATMENT BUILDING | LAYOUT AND INSTRUMENT LOCATION DRAWING | Balance of Plant |  | WATER TREATMENT BUILDING |  | LAYOUT AND INSTRUMENT LOCATION DRAWING for BOP |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165522 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR CPP & CPP REGENERATION BUILDING | LAYOUT AND INSTRUMENT LOCATION DRAWING | Balance of Plant |  |  |  | LAYOUT AND INSTRUMENT LOCATION DRAWING for BOP |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165523 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR CHEMICAL DOSING SHELTER FOR STG & HRSG | LAYOUT AND INSTRUMENT LOCATION DRAWING | Balance of Plant |  |  |  | LAYOUT AND INSTRUMENT LOCATION DRAWING for BOP |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165524 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR CHEMICAL DOSING SHELTER FOR HRSG | LAYOUT AND INSTRUMENT LOCATION DRAWING | Balance of Plant |  |  |  | LAYOUT AND INSTRUMENT LOCATION DRAWING for BOP |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-07-13 | 2024-08-12 | 2024-09-11 | 2024-09-26 | 2024-10-11 | 2024-10-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165525 | BOP EXPOSED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #1 | LAYOUT | Balance of Plant |  |  |  | Layout Drawing for BOP | Substation | SKIP | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165526 | BOP EXPOSED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #2 | LAYOUT | Balance of Plant |  |  |  | Layout Drawing for BOP | Substation | SKIP | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165527 | BOP EXPOSED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #3 | LAYOUT | Balance of Plant |  |  |  | Layout Drawing for BOP | Substation | SKIP | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165528 | BOP EXPOSED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #4 | LAYOUT | Balance of Plant |  |  |  | Layout Drawing for BOP | Substation | SKIP | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165529 | BOP EXPOSED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #5 | LAYOUT | Balance of Plant |  |  |  | Layout Drawing for BOP | Substation | SKIP | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165531 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM - GENERAL INFORMATION | WIRING DIAGRAM | Balance of Plant | Instrumentation & Control |  |  | WIRING DIAGRAM for BOP |  | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | 2024-12-07 | 2025-01-06 | 2025-02-05 | 2025-02-20 | 2025-03-07 | 2025-03-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165532 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR HP STEAM SYSTEM | WIRING DIAGRAM | Balance of Plant | Instrumentation & Control |  |  | WIRING DIAGRAM for BOP |  | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | 2024-12-07 | 2025-01-06 | 2025-02-05 | 2025-02-20 | 2025-03-07 | 2025-03-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165533 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR IP STEAM SYSTEM | WIRING DIAGRAM | Balance of Plant | Instrumentation & Control |  |  | WIRING DIAGRAM for BOP |  | FA | 0EF6020W00A01 | (BOP Piping) Pipe Arrangement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-04-30 | 2008-09-30 | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165534 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR LP STEAM SYSTEM | WIRING DIAGRAM | Balance of Plant | Instrumentation & Control |  |  | WIRING DIAGRAM for BOP |  | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | 2024-12-07 | 2025-01-06 | 2025-02-05 | 2025-02-20 | 2025-03-07 | 2025-03-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165535 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR PROCESS STEAM SYSTEM | WIRING DIAGRAM | Balance of Plant | Instrumentation & Control |  |  | WIRING DIAGRAM for BOP |  | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | 2024-12-07 | 2025-01-06 | 2025-02-05 | 2025-02-20 | 2025-03-07 | 2025-03-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165536 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR STEAM DRAIN SYSTEM | WIRING DIAGRAM | Balance of Plant | Instrumentation & Control |  |  | WIRING DIAGRAM for BOP |  | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | 2024-12-07 | 2025-01-06 | 2025-02-05 | 2025-02-20 | 2025-03-07 | 2025-03-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165537 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR CONDENSATE SYSTEM | WIRING DIAGRAM | Balance of Plant | Instrumentation & Control |  |  | WIRING DIAGRAM for BOP |  | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | 2024-12-07 | 2025-01-06 | 2025-02-05 | 2025-02-20 | 2025-03-07 | 2025-03-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165538 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR FEEDWATER SYSTEM | WIRING DIAGRAM | Balance of Plant | Instrumentation & Control |  |  | WIRING DIAGRAM for BOP |  | FA | 0EF6020W00A01 | (BOP Piping) Pipe Arrangement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-04-30 | 2008-09-30 | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165539 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR CLOSED COOLING WATER SYSTEM | WIRING DIAGRAM | Balance of Plant | Instrumentation & Control |  |  | WIRING DIAGRAM for BOP |  | FA | 1PF3030W42A21P | (CCWP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-09-03 | 2008-07-02 | 2024-11-26 | 2024-12-26 | 2025-01-25 | 2025-02-09 | 2025-02-24 | 2025-03-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165540 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | WIRING DIAGRAM | Balance of Plant | Instrumentation & Control |  |  | WIRING DIAGRAM for BOP |  | FA | 0CF5534W90A09 | (DWP BLDG) Installation & Test - I&C | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2008-05-21 | 2008-08-05 | 2025-08-14 | 2025-09-13 | 2025-10-13 | 2025-10-28 | 2025-11-12 | 2025-11-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165541 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR GT ROTOR COOLING AIR SYSTEM | WIRING DIAGRAM | Balance of Plant | Instrumentation & Control |  |  | WIRING DIAGRAM for BOP |  | FA | 0EF6020W00A01 | (BOP Piping) Pipe Arrangement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-04-30 | 2008-09-30 | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165542 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR GT PERFORMANCE HEATER SYSTEM | WIRING DIAGRAM | Balance of Plant | Instrumentation & Control |  |  | WIRING DIAGRAM for BOP |  | FA | 0EF6020W00A01 | (BOP Piping) Pipe Arrangement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-04-30 | 2008-09-30 | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165543 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR POTABLE WATER STORAGE AND SUPPLY SYSTEM | WIRING DIAGRAM | Balance of Plant | Instrumentation & Control |  |  | WIRING DIAGRAM for BOP |  | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | 2024-06-07 | 2024-07-07 | 2024-08-06 | 2024-08-21 | 2024-09-05 | 2024-09-20 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165544 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR POTABLE WATER DISTRIBUTION SYSTEM | WIRING DIAGRAM | Balance of Plant | Instrumentation & Control |  |  | WIRING DIAGRAM for BOP |  | FA | 1CF3035W58A01.1 | (PWS) Piping Work(Block #1) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Potable Water System (BOP) | 2008-11-04 | 2009-01-02 | 2026-01-28 | 2026-02-27 | 2026-03-29 | 2026-04-13 | 2026-04-28 | 2026-05-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165545 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR COMPRESSED AIR SYSTEM | WIRING DIAGRAM | Balance of Plant | Instrumentation & Control |  |  | WIRING DIAGRAM for BOP |  | FA | 1CF3510W58A01 | (COMP Air System) Piping Work(incl. Air blowing)_Block #1 | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Compressed Air System (BOP) | 2008-09-02 | 2008-12-31 | 2025-11-26 | 2025-12-26 | 2026-01-25 | 2026-02-09 | 2026-02-24 | 2026-03-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165546 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR FUEL GAS SYSTEM | WIRING DIAGRAM | Balance of Plant | Instrumentation & Control |  |  | WIRING DIAGRAM for BOP |  | FA | 0EF6020W00A01 | (BOP Piping) Pipe Arrangement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-04-30 | 2008-09-30 | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165547 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR ELECTRICAL SYSTEM | WIRING DIAGRAM | Balance of Plant | Instrumentation & Control |  |  | WIRING DIAGRAM for BOP |  | FA | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | 2024-12-12 | 2025-01-11 | 2025-02-10 | 2025-02-25 | 2025-03-12 | 2025-03-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YB03-P0ZEN-165548 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR INTERFACE WITH OTHER CONTROL SYSTEM | WIRING DIAGRAM | Balance of Plant | Instrumentation & Control |  |  | WIRING DIAGRAM for BOP |  | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | 2024-12-07 | 2025-01-06 | 2025-02-05 | 2025-02-20 | 2025-03-07 | 2025-03-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165551 | BOP - I&C CABLE SCHEDULE - GENERAL INFORMATION | CABLE SCHEDULE | Balance of Plant | Instrumentation & Control |  |  | CABLE SCHEDULE for BOP | Substation | SKIP | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165552 | BOP - I&C CABLE SCHEDULE FOR HP STEAM SYSTEM | CABLE SCHEDULE | Balance of Plant | HP STEAM SYSTEM |  |  | CABLE SCHEDULE for BOP | Substation | SKIP | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165553 | BOP - I&C CABLE SCHEDULE FOR IP STEAM SYSTEM | CABLE SCHEDULE | Balance of Plant | IP STEAM SYSTEM |  |  | CABLE SCHEDULE for BOP | Substation | SKIP | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165554 | BOP - I&C CABLE SCHEDULE FOR LP STEAM SYSTEM | CABLE SCHEDULE | Balance of Plant | LP STEAM SYSTEM |  |  | CABLE SCHEDULE for BOP | Substation | SKIP | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165555 | BOP - I&C CABLE SCHEDULE FOR PROCESS STEAM SYSTEM | CABLE SCHEDULE | Balance of Plant | PROCESS STEAM SYSTEM |  |  | CABLE SCHEDULE for BOP | Substation | SKIP | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165556 | BOP - I&C CABLE SCHEDULE FOR STEAM DRAIN SYSTEM | CABLE SCHEDULE | Balance of Plant | STEAM DRAIN SYSTEM |  |  | CABLE SCHEDULE for BOP | Substation | SKIP | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165557 | BOP - I&C CABLE SCHEDULE FOR CONDENSATE SYSTEM | CABLE SCHEDULE | Balance of Plant | CONDENSATE SYSTEM |  |  | CABLE SCHEDULE for BOP | Substation | SKIP | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165558 | BOP - I&C CABLE SCHEDULE FOR FEEDWATER SYSTEM | CABLE SCHEDULE | Balance of Plant | FEEDWATER SYSTEM |  |  | CABLE SCHEDULE for BOP | Substation | SKIP | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165559 | BOP - I&C CABLE SCHEDULE FOR CLOSED COOLING WATER SYSTEM | CABLE SCHEDULE | Balance of Plant | CLOSED COOLING WATER SYSTEM |  |  | CABLE SCHEDULE for BOP | Substation | SKIP | 1PF3030W42A21P | (CCWP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-09-03 | 2008-07-02 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165560 | BOP - I&C CABLE SCHEDULE FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | CABLE SCHEDULE | Balance of Plant | DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM |  |  | CABLE SCHEDULE for BOP | Substation | SKIP | 0CF5534W90A09 | (DWP BLDG) Installation & Test - I&C | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2008-05-21 | 2008-08-05 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165561 | BOP - I&C CABLE SCHEDULE FOR GT ROTOR COOLING AIR SYSTEM | CABLE SCHEDULE | Balance of Plant | GT ROTOR COOLING AIR SYSTEM |  |  | CABLE SCHEDULE for BOP | Substation | SKIP | 1CF3510W58A01 | (COMP Air System) Piping Work(incl. Air blowing)_Block #1 | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Compressed Air System (BOP) | 2008-09-02 | 2008-12-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165562 | BOP - I&C CABLE SCHEDULE FOR GT PERFORMANCE HEATER SYSTEM | CABLE SCHEDULE | Balance of Plant | GT PERFORMANCE HEATER SYSTEM |  |  | CABLE SCHEDULE for BOP | Substation | SKIP | 1PF3520W42A07.2P | (Gas HTR) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Heater | 2007-07-03 | 2008-04-01 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165563 | BOP - I&C CABLE SCHEDULE FOR POTABLE WATER STORAGE AND SUPPLY SYSTEM | CABLE SCHEDULE | Balance of Plant | POTABLE WATER STORAGE AND SUPPLY SYSTEM |  |  | CABLE SCHEDULE for BOP | Substation | SKIP | 1CF3035W62A02.1 | (PWS) Hydro Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Potable Water System (BOP) | 2009-01-03 | 2009-01-19 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165564 | BOP - I&C CABLE SCHEDULE FOR POTABLE WATER DISTRIBUTION SYSTEM | CABLE SCHEDULE | Balance of Plant | POTABLE WATER DISTRIBUTION SYSTEM |  |  | CABLE SCHEDULE for BOP | Substation | SKIP | 1CF3035W62A02.1 | (PWS) Hydro Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Potable Water System (BOP) | 2009-01-03 | 2009-01-19 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165565 | BOP - I&C CABLE SCHEDULE FOR COMPRESSED AIR SYSTEM | CABLE SCHEDULE | Balance of Plant | COMPRESSED AIR SYSTEM |  |  | CABLE SCHEDULE for BOP | Substation | SKIP | 1CF3510W58A01 | (COMP Air System) Piping Work(incl. Air blowing)_Block #1 | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Compressed Air System (BOP) | 2008-09-02 | 2008-12-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165566 | BOP - I&C CABLE SCHEDULE FOR FUEL GAS SYSTEM | CABLE SCHEDULE | Balance of Plant | Fuel Gas System |  |  | CABLE SCHEDULE for BOP | Substation | SKIP | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165567 | BOP - I&C CABLE SCHEDULE FOR ELECTRICAL SYSTEM | CABLE SCHEDULE | Balance of Plant | Electrical System |  |  | CABLE SCHEDULE for BOP | Substation | SKIP | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YL16-P0ZEN-165568 | BOP - I&C CABLE SCHEDULE FOR INTERFACE WITH OTHER CONTROL SYSTEM | CABLE SCHEDULE | Balance of Plant | INTERFACE WITH OTHER CONTROL SYSTEM |  |  | CABLE SCHEDULE for BOP | Substation | SKIP | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165571 | BOP EXPOSED CONDUIT LAYOUT FOR POTABLE STORAGE WATER TANK & FIRE WATER TANK AREA | EXPOSED CONDUIT LAYOUT | Balance of Plant |  |  |  | EXPOSED CONDUIT LAYOUT for BOP |  | FA | 2CF3035W58A01.1 | (PWS) Piping Work(Block #2) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Potable Water System (BOP) | 2008-11-04 | 2009-01-02 |  |  |  | 2025-08-07 | 2025-09-06 | 2025-10-06 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165572 | BOP EXPOSED CONDUIT LAYOUT FOR DEMI WATER STORAGE TANK AREA | EXPOSED CONDUIT LAYOUT | Balance of Plant |  |  |  | EXPOSED CONDUIT LAYOUT for BOP |  | FA | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165573 | BOP EXPOSED CONDUIT LAYOUT FOR CONDENSATE STORAGE TANK AREA | LAYOUT | Balance of Plant |  |  |  | Layout Drawing for BOP | Substation | SKIP | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165575 | BOP EXPOSED CONDUIT LAYOUT FOR FIN FAN COOLER(CCW) & CCW PUMP AREA | LAYOUT | Balance of Plant |  |  |  | Layout Drawing for BOP | Substation | SKIP | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165576 | BOP EXPOSED CONDUIT LAYOUT FOR STG TRANSFORMER AREA #1,#2 | LAYOUT | Balance of Plant |  |  |  | Layout Drawing for BOP | Substation | SKIP | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD02-P0ZEN-165577 | BOP EXPOSED CONDUIT LAYOUT FOR PIPE RACK AREA | LAYOUT | Balance of Plant |  | PIPE RACK |  | Layout Drawing for BOP | Substation | SKIP | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-165701 | TECHNICAL SPECIFICATION FOR I&C CABLE | TECHNICAL SPECIFICATION |  | Instrumentation & Control Cable |  |  | Technical Specification for Instrumentation & Control Cable |  | FA | 0PF6040W74A02.1P | (Electrical Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power & Electrical Control Cables | 2007-09-19 | 2008-03-25 | 2025-04-01 | 2025-05-01 | 2025-05-31 | 2025-06-15 | 2025-06-30 | 2025-07-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-165711 | TECHNICAL SPECIFICATION FOR JUNCTION BOX & RACK | TECHNICAL SPECIFICATION |  | JUNCTION BOX & Transmitter rack |  |  | Technical Specification for JUNCTION BOX & Transmitter rack | LOCAL BOX | FA | 1PF5550W46A08P | (PipeRack) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-06-28 | 2008-01-02 | 2024-07-12 | 2024-08-11 | 2024-09-10 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0ZEN-165731 | TECHNICAL SPECIFICATION FOR INSTRUMENT INSTALLATION MATERIALS | TECHNICAL SPECIFICATION |  | INSTRUMENT INSTALLATION MATERIALS |  |  | Technical Specification for INSTRUMENT INSTALLATION MATERIALS | INSTRUMENT INSTALLATION MATERIA | FA | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | 2024-08-31 | 2024-09-30 | 2024-10-30 | 2024-11-14 | 2024-11-29 | 2024-12-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YR02-P0ZEN-165900 | DESCRIPTION OF SETTLEMENT SYSTEM | DESCRIPTION |  | Plant Settlement System |  |  | DESCRIPTION for Plant Settlement System |  | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | 2024-11-09 | 2024-12-09 | 2025-01-08 | 2025-01-23 | 2025-02-07 | 2025-02-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0ZEN-167001 | CYBER SECURITY PLAN | PLAN |  |  |  |  | Plan |  | FA | 0EF6010W10A01 | Soil Investigation Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-03-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-BF05-P0ZEN-170101 | SOIL INVESTIGATION REPORT | REPORT |  |  |  |  | REPORT |  | FA | 0EF6010W10A01 | Soil Investigation Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-03-29 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-03-17 | 2024-04-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-BF05-P0ZEN-170102 | TOPOGRAPHIC SURVEY REPORT | REPORT |  |  |  |  | REPORT |  | FA | 0EF6010W10A01 | Soil Investigation Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-03-29 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-03-17 | 2024-04-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0ZEN-170103 | PILE CAPACITY CALCULATION | CALCULATION |  |  |  |  | Calculation sheet |  | FA | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 | 2024-08-17 | 2024-09-16 | 2024-10-16 | 2024-10-31 | 2024-11-15 | 2024-11-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0ZEN-170104 | WORKING PILE DETAIL | DETAIL |  |  |  |  | Detail Drawing |  | FI | 0EF1200W14A03 | GTG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-04-02 | 2007-05-31 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-BF05-P0ZEN-170105 | REPORT FOR PILE LOAD TEST OF BORED CAST - IN - PLACE PILE | REPORT |  |  |  |  | REPORT |  | FA | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 | 2024-03-01 | 2024-03-01 | 2024-03-16 | 2024-03-31 | 2024-04-15 | 2024-04-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UMX-171001 | GTG FOUNDATION - PILE CALCULATION SHEET | CALCULATION SHEET | Gas Turbine Generator |  |  |  | CALCULATION SHEET for GTG |  | FI | 0EF1200W14A03 | GTG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-04-02 | 2007-05-31 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171002 | GTG FOUNDATION - PILE ARRANGEMENT DRAWING | ARRANGEMENT DRAWING | Gas Turbine Generator |  |  |  | General Arrangement Drawing for GTG |  | FA | 3EF1210W00A06 | (GTG Common BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | 2007-03-01 |  | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UMX-171004 | GTG FOUNDATION - DESIGN REPORT | REPORT | Gas Turbine Generator |  |  |  | REPORT for GTG |  | FA | 1EF1213W16A01 | (GT #11) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | 2007-03-01 | 2007-05-31 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171005 | GT FDN GENERAL NOTES FORMWORK DWG | Drawing | GT |  |  |  | Drawing for GT |  | FA | 3PF1213W42A03P | (GT #31) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | 2007-04-30 | 2008-03-31 | 2024-07-22 | 2024-08-21 | 2024-09-20 | 2024-10-05 | 2024-10-20 | 2024-11-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171006 | GT FDN TOP PLAN VIEW INSERT PLATE ARRANGEMENT AND DETAILS FORMWORK DWG, PART 1/6 | Drawing | GT |  |  |  | Drawing for GT |  | FA | 1PF1213W42A03.1P | (GT #12) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Main body | 2007-03-01 | 2008-02-29 | 2024-05-23 | 2024-06-22 | 2024-07-22 | 2024-08-06 | 2024-08-21 | 2024-09-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171007 | GT FDN TOP PLAN VIEW ANCHOR BOLT ARRANGEMENT AND DETAILS FORMWORK DRAWING, PART 2/6 | DRAWING | GT |  |  |  | DRAWING for GT |  | FA | 2PF1213W42A03.1P | (GT #22) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Main body | 2007-03-30 | 2008-03-31 | 2024-06-21 | 2024-07-21 | 2024-08-20 | 2024-09-04 | 2024-09-19 | 2024-10-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171008 | GT FDN TOP PLAN VIEW EXPANSION BOLT ARRGMNT AND DETAIL FORMWORK DWG, 3/6 | Drawing |  |  |  |  | Drawing |  | FA | 3PF1225W42A18P | (EXP Head Tank) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | 2007-07-03 | 2008-05-30 | 2024-08-14 | 2024-09-13 | 2024-10-13 | 2024-10-28 | 2024-11-12 | 2024-11-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171009 | GT FDN VIEWS & SECTIONS FORMWORK DWG, PART 4/6 | Drawing |  |  |  |  | Drawing |  | FA | 3PF1213W42A03P | (GT #31) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | 2007-04-30 | 2008-03-31 | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171010 | GT FDN ANCHOR BOLT DETAILS FORMWORK DWG, PART 5/6 | Drawing |  |  |  |  | Drawing |  | FA | 0PF6040W80A02P | (Earthing & Lightning Material) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Earthing & Lightning Materials | 2007-08-17 | 2007-12-18 | 2024-09-28 | 2024-10-28 | 2024-11-27 | 2024-12-12 | 2024-12-27 | 2025-01-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171011 | GT FDN TOP PLAN VIEW SCHEDULE OF EMBEDDED PARTS FORMWORK DRAWING, PART 6/6 | Drawing |  |  |  |  | Drawing |  | FA | 2PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-09-03 | 2008-02-14 | 2024-10-15 | 2024-11-14 | 2024-12-14 | 2024-12-29 | 2025-01-13 | 2025-01-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171012 | GT FDN BOTTOM LONGITUDINAL & LATERAL REINFORCEMENT REINFORCEMENT DRAWING BASEMAT, PART 1/9 | Drawing |  |  |  |  | Drawing |  | FA | 1PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-09-03 | 2008-01-15 | 2024-10-15 | 2024-11-14 | 2024-12-14 | 2024-12-29 | 2025-01-13 | 2025-01-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171013 | GT FDN TOP LOGITUDINAL & LATERAL REINFORCEMENT DWG BASEMAT, PART 2/9 | Drawing |  |  |  |  | Drawing |  | FA | 2PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-09-03 | 2008-02-14 | 2024-10-15 | 2024-11-14 | 2024-12-14 | 2024-12-29 | 2025-01-13 | 2025-01-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171014 | GT FDN BOTTOM & TOP (3rd + 4th LAYER) LATERAL & LONGITUDINAL REINFORCEMENT, PART 3/9 | Drawing |  |  |  |  | Drawing |  | FA | 3PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | 2007-09-03 | 2008-03-17 | 2024-10-15 | 2024-11-14 | 2024-12-14 | 2024-12-29 | 2025-01-13 | 2025-01-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171015 | GT FDN CONNECTION AND SIDE FACE REINFORCEMENT PLAN AT +0.152M & 1.099M LEVEL REINFORCEMENT DRAWING BASEMAT, PART 4/9 | Drawing |  |  |  |  | Drawing |  | FA | 1PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-09-03 | 2008-01-15 | 2024-10-15 | 2024-11-14 | 2024-12-14 | 2024-12-29 | 2025-01-13 | 2025-01-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171016 | GT FDN SPACER REBARS AND DETAILS REINFORCEMENT DRAWING BASEMAT, PART 5/9 | Drawing |  |  |  |  | Drawing |  | FA | 3PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | 2007-09-03 | 2008-03-17 | 2024-10-15 | 2024-11-14 | 2024-12-14 | 2024-12-29 | 2025-01-13 | 2025-01-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171017 | GT FDN SECTION 1-1 AND DETAILS REINFORCEMENT DRAWING BASEMAT, PART 6/9 | Drawing |  |  |  |  | Drawing |  | FA | 1PF1213W42A03P | (GT #11) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | 2007-03-01 | 2008-01-31 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171018 | GT FDN REINFORCEMENT SECTION 2-2 AND 3-3 REINFORCEMENT DRAWING BASEMAT, PART 7/9 | Drawing |  |  |  |  | Drawing |  | FA | 3PF1213W42A03.1P | (GT #32) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Main body | 2007-04-30 | 2008-04-29 | 2024-06-11 | 2024-07-11 | 2024-08-10 | 2024-08-25 | 2024-09-09 | 2024-09-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171019 | GT FDN REINFORCEMENT DETAILS SECTION 4-4 AND 5-5 REINFORCEMENT DRAWING BASEMAT, PART 8/9 | Drawing |  |  |  |  | Drawing |  | FA | 2PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-09-03 | 2008-02-14 | 2024-10-15 | 2024-11-14 | 2024-12-14 | 2024-12-29 | 2025-01-13 | 2025-01-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171020 | GT FDN REINFORCEMENT PLAN & SECTIONS FOR COMPRESSION SUPPORT, TURNING GEAR PEDESTAL AND MOUNTING PAD PEDESTAL REINFORCEMENT DRAWING BASEMAT, PART 9/9 | Drawing |  |  |  |  | Drawing |  | FA | 0PF6020W46A08P | (Hanger & Support & Fitting) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-02-29 | 2024-10-26 | 2024-11-25 | 2024-12-25 | 2025-01-09 | 2025-01-24 | 2025-02-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171021 | GT FDN REINFORCEMENT PLAN AT +1.099M LEVEL AND SPACER & SIDE FACE REBARS GENERATOR DECK REINFORCEMENT, PART 1/2 | Drawing |  |  |  |  | Drawing |  | FA | 1PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-09-03 | 2008-01-15 | 2024-10-15 | 2024-11-14 | 2024-12-14 | 2024-12-29 | 2025-01-13 | 2025-01-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171022 | GT FDN SECTIONS & DETAILS GENERATOR DECK REINFORCEMENT, PART 2/2 | Drawing |  |  |  |  | Drawing |  | FA | 2PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-09-03 | 2008-02-14 | 2024-10-15 | 2024-11-14 | 2024-12-14 | 2024-12-29 | 2025-01-13 | 2025-01-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171023 | GTG FOUNDATION BAR BENDING SCHEDULE | Schedule | Gas Turbine Generator |  |  |  | Schedule for GTG |  | FA | 1EF1210W16A07 | (GTG Common BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-08-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171024 | GT FDN BENDING SCHEDULES - GENERATOR DECK | Schedule |  |  |  |  | Schedule |  | FI | 2EF1213W16A01 | (GT #21) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | 2007-03-30 | 2007-06-29 | 2024-03-01 | 2024-03-30 | 2024-04-29 | 2024-05-14 | 2024-05-29 | 2024-06-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UMX-171051 | GTG AUXILIARY FOUNDATION - DESIGN REPORT | DESIGN REPORT | Gas Turbine Generator |  |  |  | DESIGN REPORT for GTG |  | FA | 1EF1213W16A01 | (GT #11) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | 2007-03-01 | 2007-05-31 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171052 | GTG AUXILIARY FOUNDATION - GENERAL ARRANGEMENT | GENERAL ARRANGEMENT | Gas Turbine Generator |  |  |  | General Arrangement Drawing for GTG |  | FA | 1EF6500W00A09 | (GTG #11 & UAT Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 |  | 2024-07-12 | 2024-08-11 | 2024-09-10 | 2024-09-25 | 2024-10-10 | 2024-10-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171053 | FOUNDATION FOR SFC & SEE TRANSFORMER PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | Drawing |  |  |  |  | Drawing |  | FA | 1PF6500W70A04P | (GTG TR) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-04-02 | 2008-04-15 | 2024-05-14 | 2024-06-13 | 2024-07-13 | 2024-07-28 | 2024-08-12 | 2024-08-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171054 | FOUNDATION FOR EXHAUST TRANSITION DUCT & COMPRESSOR BLEED PIPE SUPPORT PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | DRAWING | DUCT |  |  |  | DRAWING for DUCT |  | FA | 1PF1615W64A06P | (HRSG #11 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | 2007-06-14 | 2008-01-31 | 2024-10-25 | 2024-11-24 | 2024-12-24 | 2025-01-08 | 2025-01-23 | 2025-02-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171055 | FOUNDATION FOR WOBBE METER CABINET, GT ENCLOSURE RIGHT SIDE EXHAUST END EXTERIOR PLATFORM & AIR COMPRESSOR SKID(DAIS) PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | DRAWING |  |  |  |  | DRAWING |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-06-29 | 2024-07-29 | 2024-08-28 | 2024-09-12 | 2024-09-27 | 2024-10-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171056 | FOUNDATION FOR SEE/ SFC PACKAGE FOUNDATION INTERFACE-SEE ONLY PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | DRAWING |  |  |  |  | DRAWING |  | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | 2024-10-26 | 2024-11-25 | 2024-12-25 | 2025-01-09 | 2025-01-24 | 2025-02-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171057 | FOUNDATION FOR SEE/ SFC PACKAGE SEE WITH SFC NORMAL START PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | DRAWING |  |  |  |  | DRAWING |  | FA | 0PF4500W38A09P | (Fire Fighting System) P.O & Procurement_piping | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-08-01 | 2007-12-31 | 2024-09-12 | 2024-10-12 | 2024-11-11 | 2024-11-26 | 2024-12-11 | 2024-12-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171058 | FOUNDATION FOR CONTROL OIL SKID, AIR BACKUP COMPRESSOR, FILTER HOUSE, GENERATOR AIR FILTER, LUBE OIL PACKAGE, ELECTRICAL PACKAGE & GTE RS INLET END EXT. PLATFORM PLAN, SECTIONS AND DETAILS FORMWORK DRAWING | DRAWING |  |  |  |  | DRAWING |  | FA | 0EF3510W16A03 | (COMP Air PKG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2007-12-03 | 2024-09-12 | 2024-10-12 | 2024-11-11 | 2024-11-26 | 2024-12-11 | 2024-12-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171059 | FOUNDATION FOR CONTROL OIL SKID, AIR BACKUP COMPRESSOR, FILTER HOUSE, GENERATOR AIR FILTER, LUBE OIL PACKAGE, ELECTRICAL PACKAGE & GTE RS INLET END EXT. PLATFORM PLAN, SECTIONS AND DETAILS REINFORCEMENT DRAWING | DRAWING |  |  |  |  | DRAWING |  | FA | 1PF1250W42A02P | (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Lube Oil System | 2007-03-01 | 2008-01-30 | 2024-04-12 | 2024-05-12 | 2024-06-11 | 2024-06-26 | 2024-07-11 | 2024-07-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UMX-171060 | FOUNDATION FOR CONTROL OIL SKID, AIR BACKUP COMPRESSOR, FILTER HOUSE, GENERATOR AIR FILTER, LUBE OIL PACKAGE, ELECTRICAL PACKAGE & GTE RS INLET END EXT. PLATFORM BAR BENDING SCHEDULE | Schedule |  |  |  |  | Schedule |  | FI | 0CF3510W16A04 | (COMP Air PKG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-12-04 | 2008-02-01 | 2024-11-04 | 2024-12-04 | 2025-01-03 | 2025-01-18 | 2025-02-02 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171061 | FOUNDATION FOR ROTOR AIR COOLER(KETTLE BOILER) & ROTOR COOLING AIR PIPE SUPPORTS PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | DRAWING |  |  |  |  | DRAWING |  | FA | 1PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | 2007-07-03 | 2008-03-31 | 2024-08-14 | 2024-09-13 | 2024-10-13 | 2024-10-28 | 2024-11-12 | 2024-11-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171062 | FOUNDATION FOR SFC CROSSOVER SWITCH & FIRE PROTECTION SKID PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | DRAWING |  |  |  |  | DRAWING |  | FA | 0PF4500W38A09P | (Fire Fighting System) P.O & Procurement_piping | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-08-01 | 2007-12-31 | 2024-09-12 | 2024-10-12 | 2024-11-11 | 2024-11-26 | 2024-12-11 | 2024-12-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UMX-171063 | FOUNDATION FOR PULSE AIR COMPRESSIOR SKID PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | DRAWING |  |  |  |  | DRAWING |  | FA | 0PF3510W42A06P | (COMP Air PKG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-08-01 | 2008-04-30 | 2024-09-12 | 2024-10-12 | 2024-11-11 | 2024-11-26 | 2024-12-11 | 2024-12-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0MPA-171101 | CALCULATION OF STEAM TURBINE GENERATOR FOUNDATION PILE DESIGN | CALCULATION | Steam Turbine & Generator |  |  |  | Calculation sheet for STG |  | FI | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0MPA-171102 | CALCULATION OF STEAM TURBINE GENERATOR FOUNDATION DYNAMIC ANALYSIS | CALCULATION | Steam Turbine & Generator |  |  |  | Calculation sheet for STG |  | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0MPA-171103 | CALCULATION OF STEAM TURBINE GENERATOR FOUNDATION R.C DESIGN | CALCULATION | Steam Turbine & Generator |  |  |  | Calculation sheet for STG |  | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0MPA-171104 | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | LAYOUT | Steam Turbine & Generator |  |  |  | Layout Drawing for STG | Substation | SKIP | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0MPA-171105 | STEAM TURBINE GENERATOR FOUNDATION PILE ARRANGEMENT | ARRANGEMENT | Steam Turbine & Generator |  |  |  | ARRANGEMENT for STG |  | FA | 1PF2040W42A02P | (STG #10) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > ST Generator | 2007-03-01 | 2008-09-01 | 2024-09-04 | 2024-10-04 | 2024-11-03 | 2024-11-18 | 2024-12-03 | 2024-12-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0MPA-171106 | STEAM TURBINE GENERATOR FOUNDATION PLAN AND SECTION | PLAN AND SECTION | Steam Turbine & Generator |  |  |  | PLAN AND SECTION for STG |  | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0MPA-171113 | STEAM TURBINE GENERATOR FOUNDATION ANCHOR BOLTS AND EMBEDMENT |  | Steam Turbine & Generator |  |  |  | for STG |  | FA | 1PF2020W42A10P | (ST #10) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2008-09-01 | 2024-09-04 | 2024-10-04 | 2024-11-03 | 2024-11-18 | 2024-12-03 | 2024-12-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0MPA-171117 | STEAM TURBINE GENERATOR FOUNDATION R.C DETAIL | DETAIL | Steam Turbine & Generator |  |  |  | Detail Drawing for STG |  | FI | 1PF2020W42A10P | (ST #10) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2008-09-01 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0ULX-171201 | CALCULATION OF CCW FIN FAN COOLER FOUNDATION | CALCULATION |  | Closed Cooling Water |  |  | Calculation sheet for Closed Cooling Water | Water Treatment System | FA | 3EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | 2024-08-02 | 2024-09-01 | 2024-10-01 | 2024-10-16 | 2024-10-31 | 2024-11-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-171202 | CCW FIN FAN COOLER FOUNDATION LAYOUT | LAYOUT |  | Closed Cooling Water |  |  | Layout Drawing for Closed Cooling Water | Cooling ToWer | FA | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 | 2024-11-20 | 2024-12-20 | 2025-01-19 | 2025-02-03 | 2025-02-18 | 2025-03-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-171203 | CCW FIN FAN COOLER FOUNDATION PLAN AND SECTION | PLAN AND SECTION | Fin Fan Cooler |  |  |  | PLAN AND SECTION for Fin Fan Cooler | CCW FIN FAN COOLER | FA | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0ULX-171221 | CALCULATION OF CPP FIN FAN COOLER FOUNDATION | CALCULATION | Fin Fan Cooler |  |  |  | Calculation sheet for Fin Fan Cooler | CCW FIN FAN COOLER | FA | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-171222 | CPP FIN FAN COOLER FOUNDATION LAYOUT | LAYOUT | Fin Fan Cooler |  |  |  | Layout Drawing for Fin Fan Cooler | CCW FIN FAN COOLER | FA | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-171223 | CPP FIN FAN COOLER FOUNDATION PLAN AND SECTION | PLAN AND SECTION | Fin Fan Cooler |  |  |  | PLAN AND SECTION for Fin Fan Cooler | CCW FIN FAN COOLER | FA | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | 2007-07-03 | 2007-11-29 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0ULC-171301 | CALCULATION OF AIR COOLED CONDENSER FOUNDATION | CALCULATION | Air Cooled Condenser |  |  |  | Calculation sheet for ACC |  | FA | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2025-06-09 | 2025-07-09 | 2025-08-08 | 2025-08-23 | 2025-09-07 | 2025-09-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULC-171302 | AIR COOLED CONDENSER FOUNDATION LAYOUT | LAYOUT | Air Cooled Condenser |  |  |  | Layout Drawing for ACC |  | FA | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-03-01 | 2008-05-29 | 2025-10-17 | 2025-11-16 | 2025-12-16 | 2025-12-31 | 2026-01-15 | 2026-01-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULC-171303 | AIR COOLED CONDENSER FOUNDATION PLAN AND SECTION | PLAN AND SECTION | Air Cooled Condenser |  |  |  | PLAN AND SECTION for ACC |  | FA | 1CF3020W16A04 | (COND Air EXT Equip) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2008-05-30 | 2008-07-28 |  |  |  | 2025-03-02 | 2025-04-01 | 2025-05-01 | generated | 0.60 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0ULC-171308 | AIR COOLED CONDENSER FOUNDATION R.C DETAIL | DETAIL | Air Cooled Condenser |  |  |  | Detail Drawing for ACC |  | FI | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2024-11-28 | 2024-12-28 | 2025-01-27 | 2025-02-11 | 2025-02-26 | 2025-03-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0ULC-171309 | AIR COOLED CONDENSER DRAIN WATER PUMP PIT DETAIL | DETAIL | Air Cooled Condenser |  |  |  | Detail Drawing for ACC |  | FI | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-12 | 2024-11-28 | 2024-12-28 | 2025-01-27 | 2025-02-11 | 2025-02-26 | 2025-03-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UNX-171401 | CALCULATION OF PIPE SLEEPER FOUNDATION | CALCULATION |  |  |  |  | Calculation sheet |  | FA | 0EF5550W16A03 | (Pipe Rack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Pipe Rack | 2007-06-29 | 2007-10-26 | 2024-11-16 | 2024-12-16 | 2025-01-15 | 2025-01-30 | 2025-02-14 | 2025-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UNX-171402 | PIPE SLEEPER FOUNDATION OVERALL LAYOUT | LAYOUT |  |  |  |  | Layout Drawing | Substation | SKIP | 0EF5550W00A01 | (Pipe Rack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Pipe Rack | 2007-06-29 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UNX-171403 | PIPE SLEEPER FOUNDATION LAYOUT | LAYOUT |  |  |  |  | Layout Drawing | Substation | SKIP | 0EF5550W00A01 | (Pipe Rack) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Pipe Rack | 2007-06-29 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UNX-171410 | PIPE SLEEPER FOUNDATION PLAN AND SECTION | PLAN AND SECTION |  |  |  |  | PLAN AND SECTION |  | FA | 0EF5550W16A03 | (Pipe Rack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Pipe Rack | 2007-06-29 | 2007-10-26 |  |  |  | 2024-03-31 | 2024-04-30 | 2024-05-30 | generated | 0.60 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UEG-171501 | FGS AREA FOUNDATION CALCULATION | CALCULATION |  | Fuel Gas System |  |  | Calculation sheet for Fuel Gas System | Fuel Gas System | FA | 0EF3520W16A02.1 | (FGS LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 | 2007-09-13 | 2024-10-02 | 2024-10-30 | 2024-11-27 | 2024-11-20 | 2024-12-18 | 2025-01-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UEG-171502 | FGS AREA LAYOUT | LAYOUT |  | Fuel Gas System |  |  | Layout Drawing for Fuel Gas System | Fuel Gas System | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | 2024-09-04 | 2024-10-30 | 2024-12-25 | 2024-11-20 | 2025-01-15 | 2025-03-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UEG-171504 | FGS AREA PLAN AND SECTION | PLAN AND SECTION |  | Fuel Gas System |  |  | PLAN AND SECTION for Fuel Gas System | Fuel Gas System | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  |  |  |  | 2024-03-01 | 2024-03-16 | 2024-04-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0ULX-171601 | CALCULATION OF GT PERFORMANCE HEATER FOUNDATION | CALCULATION | GT |  |  |  | Calculation sheet for GT |  | FA | 1CF1213W16A02.1 | (GT #12) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Main body | 2007-08-01 | 2007-12-15 |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-171602 | GT PERFORMANCE HEATER FOUNDATION LAYOUT | LAYOUT | GT |  |  |  | Layout Drawing for GT |  | FA | 2EF1213W16A01 | (GT #21) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | 2007-03-30 | 2007-06-29 | 2025-06-20 | 2025-07-20 | 2025-08-19 | 2025-09-03 | 2025-09-18 | 2025-10-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-171603 | GT PERFORMANCE HEATER FOUNDATION PLAN AND SECTION | PLAN AND SECTION | GT |  |  |  | PLAN AND SECTION for GT |  | FA | 2EF3520W16A01.2 | (Gas HTR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Heater | 2007-07-03 | 2007-10-01 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0ULX-171604 | GT PERFORMANCE HEATER FOUNDATION R.C DETAIL | DETAIL | GT |  |  |  | Detail Drawing for GT |  | FI | 1PF3520W42A07.2P | (Gas HTR) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Heater | 2007-07-03 | 2008-04-01 | 2024-08-28 | 2024-09-27 | 2024-10-27 | 2024-11-11 | 2024-11-26 | 2024-12-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UEM-171701 | CALCULATION OF WASTE WATER TREATMENT PLANT | CALCULATION | Waste Water Treatment Plant |  |  |  | Calculation sheet for Waste Water Treatment Plant | Water Treatment System | FA | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-09-01 | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UEM-171702 | WASTE WATER TREATMENT PLANT PLAN AND SECTION | PLAN AND SECTION | Waste Water Treatment Plant |  |  |  | PLAN AND SECTION for Waste Water Treatment Plant | WASTE WATER TREATMENT PLANT | FA | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UEM-171708 | WASTE WATER TREATMENT PLANT EMBEDMENT DETAIL | DETAIL | Waste Water Treatment Plant |  |  |  | Detail Drawing for Waste Water Treatment Plant | WASTE WATER TREATMENT PLANT | FA | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 |  |  |  | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UEM-171711 | WASTE WATER TREATMENT R.C DETAIL | DETAIL |  |  |  |  | Detail Drawing |  | FI | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-09-01 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UHA-171801 | CALCULATION OF HRSG FOUNDATION PILING | CALCULATION | Heat Recovery Steam Generator |  |  |  | Calculation sheet for HRSG |  | FA | 1PF1625W42A06.0P | (HRSG #11 Main Stack) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | 2007-06-04 | 2008-01-31 | 2024-11-15 | 2024-12-15 | 2025-01-14 | 2025-01-29 | 2025-02-13 | 2025-02-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UHA-171802 | CALCULATION OF HRSG FOUNDATION | CALCULATION | Heat Recovery Steam Generator |  |  |  | Calculation sheet for HRSG |  | FA | 1PF1625W42A06.0P | (HRSG #11 Main Stack) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | 2007-06-04 | 2008-01-31 | 2024-11-15 | 2024-12-15 | 2025-01-14 | 2025-01-29 | 2025-02-13 | 2025-02-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UHA-171803 | HRSG FOUNDATION ARRANGEMENT | ARRANGEMENT | Heat Recovery Steam Generator |  |  |  | ARRANGEMENT for HRSG |  | FA | 3EF1600W00A02 | (HRSG #31/#32) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UHA-171804 | HRSG FOUNDATION PILE ARRANGEMENT PLAN | ARRANGEMENT PLAN | Heat Recovery Steam Generator |  |  |  | ARRANGEMENT PLAN for HRSG |  | FA | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UHA-171805 | HRSG FOUNDATION LAYOUT | LAYOUT | Heat Recovery Steam Generator |  |  |  | Layout Drawing for HRSG |  | FA | 2EF1600W00A01 | (HRSG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | 2007-06-20 |  | 2025-03-02 | 2025-04-01 | 2025-05-01 | 2025-05-16 | 2025-05-31 | 2025-06-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UHA-171806 | HRSG FOUNDATION PLAN SECTION & DETAIL | PLAN SECTION & DETAIL | Heat Recovery Steam Generator |  |  |  | PLAN SECTION & DETAIL for HRSG |  | FA | 1CF1600W16A03 | (HRSG #11 LEB) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | 2008-01-01 | 2008-02-27 |  |  |  | 2024-10-03 | 2024-11-02 | 2024-12-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UHA-171807 | HRSG FOUNDATION REBAR DETAIL | REBAR DETAIL | Heat Recovery Steam Generator |  |  |  | REBAR DETAIL for HRSG |  | FA | 2CF1600W16A03 | (HRSG #21 LEB) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | 2008-02-01 | 2008-03-29 |  |  |  | 2024-11-03 | 2024-12-03 | 2025-01-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UHA-171815 | HRSG MISC. FOUNDATION PLAN | PLAN | Heat Recovery Steam Generator |  |  |  | Plan for HRSG |  | FA | 1PF1610W42A02P | (HRSG #11 Module) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Module | 2007-07-03 | 2008-03-03 | 2025-01-13 | 2025-02-12 | 2025-03-14 | 2025-03-29 | 2025-04-13 | 2025-04-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UHA-171816 | HRSG MISC. FOUNDATION DETAILS | DETAILS | Heat Recovery Steam Generator |  |  |  | DETAILS for HRSG |  | FA | 1CF1600W16A03 | (HRSG #11 LEB) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | 2008-01-01 | 2008-02-27 |  |  |  | 2024-10-03 | 2024-11-02 | 2024-12-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UHA-171819 | CALCULATION OF HRSG MISC. FOUNDATION | CALCULATION | Heat Recovery Steam Generator |  |  |  | Calculation sheet for HRSG |  | FA | 1PF1625W42A06.0P | (HRSG #11 Main Stack) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | 2007-06-04 | 2008-01-31 | 2024-11-15 | 2024-12-15 | 2025-01-14 | 2025-01-29 | 2025-02-13 | 2025-02-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P8UTH-172001 | CALCULATION OF RESERVE BOILER FOUNDATION | CALCULATION |  |  |  |  | Calculation sheet |  | FA | 1PF2510W58A08P | (Steam PIPING) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-10-01 | 2008-05-01 | 2025-02-18 | 2025-03-20 | 2025-04-19 | 2025-05-04 | 2025-05-19 | 2025-06-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P8UTH-172003 | RESERVE BOILER FOUNDATION LAYOUT | LAYOUT |  |  |  |  | Layout Drawing | Substation | SKIP | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P8UTH-172004 | RESERVE BOILER FOUNDATION SECTION & DETAIL | SECTION & DETAIL |  |  |  |  | SECTION & DETAIL |  | FA | 1EF3020W16A17 | (COND) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-01-30 |  |  |  | 2024-07-05 | 2024-08-04 | 2024-09-03 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P8UTH-172005 | RESERVE BOILER FOUNDATION REBAR DETAIL | REBAR DETAIL |  |  |  |  | REBAR DETAIL |  | FA | 0CF5510W16A03 | (CCR BLDG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-09-01 | 2007-11-01 |  |  |  | 2024-06-03 | 2024-07-03 | 2024-08-02 | generated | 0.60 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P8UTH-172007 | RESERVE BOILER GRADE SLAB PLAN & SECTION | PLAN & SECTION |  |  |  |  | PLAN & SECTION |  | FA | 3CF2020W16A08 | (ST #30) Pedestal & Top Slab Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Steam Turbine | 2008-04-16 | 2008-10-11 |  |  |  | 2025-01-17 | 2025-02-16 | 2025-03-18 | generated | 0.60 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P8UTH-172008 | RESERVE BOILER GRADE SLAB REBAR DETAIL | REBAR DETAIL |  |  |  |  | REBAR DETAIL |  | FA | 1CF2020W16A08 | (ST #10) Pedestal & Top Slab Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2008-03-04 | 2008-08-29 |  |  |  | 2024-12-05 | 2025-01-04 | 2025-02-03 | generated | 0.60 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P8UTH-172011 | CALCULATION OF FD FAN AND MISC. FOUNDATION | CALCULATION |  |  |  |  | Calculation sheet |  | FA | 1CF3520W16A01 | (FGSS #11) FDN Work(Misc. Equipment) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System | 2007-11-29 | 2008-02-29 | 2025-04-18 | 2025-05-18 | 2025-06-17 | 2025-07-02 | 2025-07-17 | 2025-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P8UTH-172012 | RESERVE BOILER FD FAN FOUNDATION | [7 empty] | FA | 1EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | 2007-07-03 | 2007-11-29 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P8UTH-172013 | RESERVE BOILER MISC. FOUNDATION | [7 empty] | FA | 1CF3520W16A01 | (FGSS #11) FDN Work(Misc. Equipment) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System | 2007-11-29 | 2008-02-29 |  |  |  | 2024-08-31 | 2024-09-30 | 2024-10-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UAG-172100 | TRANSFORMER FOUNDATION ARRANGEMENT PLAN | ARRANGEMENT PLAN | Power Transformer |  |  |  | ARRANGEMENT PLAN for Power Transformer |  | FA | 1EF6500W16A01 | (GTG TR) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2007-11-30 |  |  |  | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UAG-172101 | CALCULATION OF STG STEP - UP AND EXCITATION TRANSFORMER FOUNDATION | CALCULATION | Steam Turbine & Generator |  |  |  | Calculation sheet for STG |  | FI | 1CF6500W16A03 | (STG #10 & UST Shelter) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2008-03-11 | 2008-06-09 |  |  |  | 2024-12-12 | 2025-01-11 | 2025-02-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UAG-172102 | STG STEP UP AND EXCITATION TRANSFORMER PLAN & SECTION | PLAN & SECTION | Steam Turbine & Generator |  |  |  | PLAN & SECTION for STG |  | FI | 1EF6500W32A04 | (STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 |  |  |  | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UAG-172108 | STG STEP UP AND EXCITATION TRANSFORMER GRATING & GRATING SUPPORT ARRANGEMENT PLAN & SECTION | ARRANGEMENT PLAN & SECTION | Steam Turbine & Generator |  |  |  | ARRANGEMENT PLAN & SECTION for STG |  | FA | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  |  |  |  | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UAG-172109 | STG STEP UP AND EXCITATION TRANSFORMER RE-BAR DETAIL |  | Steam Turbine & Generator |  |  |  | for STG |  | FA | 1PF6500W70A07P | (STG #10 & UST Shelter) P.O & Procurement - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-06-29 | 2008-06-22 | 2025-01-02 | 2025-02-01 | 2025-03-03 | 2025-03-18 | 2025-04-02 | 2025-04-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UAG-172151 | CALCULATION OF GTG STEP UP & UNIT AUX. TRANSFORMER FOUNDATION | CALCULATION | Gas Turbine Generator |  |  |  | Calculation sheet for GTG |  | FI | 1EF6500W16A01.1 | (GTG UAT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 | 2007-10-01 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UAG-172162 | GTG STEP UP & UNIT AUX. TRANSFORMER FOUNDATION PLAN & SECTION | PLAN & SECTION | Gas Turbine Generator |  |  |  | PLAN & SECTION for GTG |  | FI | 1CF6500W16A03 | (STG #10 & UST Shelter) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2008-03-11 | 2008-06-09 |  |  |  | 2024-12-12 | 2025-01-11 | 2025-02-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UAG-172168 | GTG STEP UP & UNIT AUX. TRANSFORMER GRATING & GRATING SUPPORT ARRANGEMENT PLAN & SECTION | ARRANGEMENT PLAN & SECTION | Gas Turbine Generator |  |  |  | ARRANGEMENT PLAN & SECTION for GTG |  | FI | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  |  |  |  | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UAG-172170 | GTG STEP UP & UNIT AUX. TRANSFORMER RE-BAR DETAIL |  | Gas Turbine Generator |  |  |  | for GTG |  | FA | 1PF6500W70A07P | (STG #10 & UST Shelter) P.O & Procurement - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-06-29 | 2008-06-22 | 2024-10-25 | 2024-11-24 | 2024-12-24 | 2025-01-08 | 2025-01-23 | 2025-02-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UBN-172201 | CALCULATION OF BSDG FOUNDATION | CALCULATION | Blackstart Diesel Generator |  |  |  | Calculation sheet for Blackstart Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | FA | 0EF3530W16A14 | (BSDG BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2007-07-09 | 2007-10-08 | 2024-08-06 | 2024-09-05 | 2024-10-05 | 2024-10-20 | 2024-11-04 | 2024-11-19 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UBN-172202 | BSDG FOUNDATION PLAN & SECTION | PLAN & SECTION | Blackstart Diesel Generator |  |  |  | PLAN & SECTION for Blackstart Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | FA | 0EF3530W16A14 | (BSDG BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2007-07-09 | 2007-10-08 | 2024-08-06 | 2024-09-05 | 2024-10-05 | 2024-10-20 | 2024-11-04 | 2024-11-19 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UBN-172203 | BSDG FOUNDATION R.C DETAIL |  | Blackstart Diesel Generator |  |  |  | for Blackstart Diesel Generator | Emergency Diesel Generator/Blackstart Diesel Generator | FA | 0EF3530W16A02 | (BSDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2008-01-09 | 2008-04-09 | 2025-02-06 | 2025-03-08 | 2025-04-07 | 2025-04-22 | 2025-05-07 | 2025-05-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0BAA-172401 | CALCULATION OF IPB FOUNDATION | CALCULATION | IPB |  |  |  | Calculation sheet for IPB |  | FA | 1CF6500W74A06 | (IPB) IPB connection with TR & GCB | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2008-08-26 | 2008-09-01 |  |  |  | 2025-05-29 | 2025-06-28 | 2025-07-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0BAA-172402 | IPB FOUNDATION PLAN & SECTION | PLAN & SECTION | IPB |  |  |  | PLAN & SECTION for IPB |  | FA | 2CF6500W74A06 | (IPB) IPB connection with TR & GCB | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2008-09-06 | 2008-09-12 |  |  |  | 2025-06-09 | 2025-07-09 | 2025-08-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0BAA-172403 | IPB FOUNDATION R.C DETAIL |  | IPB |  |  |  | for IPB |  | FA | 1CF6500W74A06 | (IPB) IPB connection with TR & GCB | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2008-08-26 | 2008-09-01 |  |  |  | 2025-05-29 | 2025-06-28 | 2025-07-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0ULC-172501 | CALCULATION OF CONDENSATE WATER TANK FOUNDATION | CALCULATION | Tank |  |  |  | Calculation sheet for Tank | Water Treatment System | FA | 0PF3520W68A04P | (Condensate Tank) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-07-01 | 2024-07-31 | 2024-08-30 | 2024-09-14 | 2024-09-29 | 2024-10-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULC-172502 | CONDENSATE WATER TANK FOUNDATION PLAN & SECTION | PLAN & SECTION | Tank |  |  |  | PLAN & SECTION for Tank |  | FA | 0CF3520W16A02.1 | (Condensate Tank & Pump) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-10-12 | 2007-12-08 |  |  |  | 2024-07-14 | 2024-08-13 | 2024-09-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0ULC-172503 | CONDENSATE WATER TANK FOUNDATION REBAR DETAIL | DETAIL | Tank |  |  |  | Detail Drawing for Tank |  | FI | 0PF3520W68A04P | (Condensate Tank) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-07-27 | 2024-08-26 | 2024-09-25 | 2024-10-10 | 2024-10-25 | 2024-11-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UGF-172521 | CALCULATION OF POTABLE & FIRE FIGHTING WATER TANK FOUNDATION | CALCULATION | Tank | Fire Fighting |  |  | Calculation sheet for Tank | Water Treatment System | FA | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 | 2024-06-30 | 2024-07-30 | 2024-08-29 | 2024-09-13 | 2024-09-28 | 2024-10-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UGF-172522 | POTABLE & FIRE FIGHTING WATER TANK FOUNDATION PLAN & SECTION | PLAN & SECTION | Tank | Fire Fighting |  |  | PLAN & SECTION for Tank |  | FA | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UGF-172523 | POTABLE & FIRE FIGHTING WATER TANK FOUNDATION REBAR DETAIL | DETAIL | Tank | Fire Fighting |  |  | Detail Drawing for Tank |  | FI | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 | 2024-07-26 | 2024-08-25 | 2024-09-24 | 2024-10-09 | 2024-10-24 | 2024-11-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UGD-172541 | CALCULATION OF DEMINERALIZED WATER TANK FOUNDATION | CALCULATION | Tank |  |  |  | Calculation sheet for Tank | Water Treatment System | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | 2024-11-01 | 2024-12-01 | 2024-12-31 | 2025-01-15 | 2025-01-30 | 2025-02-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UGD-172542 | DEMINERALIZED WATER TANK FOUNDATION PLAN & SECTION | PLAN & SECTION | Tank |  |  |  | PLAN & SECTION for Tank |  | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 |  |  |  | 2024-07-04 | 2024-08-03 | 2024-09-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UGD-172543 | DEMINERALIZED WATER TANK FOUNDATION REBAR DETAIL | DETAIL | Tank |  |  |  | Detail Drawing for Tank |  | FI | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | 2024-11-27 | 2024-12-27 | 2025-01-26 | 2025-02-10 | 2025-02-25 | 2025-03-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UGG-172561 | CALCULATION OF POTABLE WATER TANK FOUNDATION | CALCULATION | Tank |  |  |  | Calculation sheet for Tank | Water Treatment System | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | 2024-11-01 | 2024-12-01 | 2024-12-31 | 2025-01-15 | 2025-01-30 | 2025-02-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UGG-172562 | POTABLE WATER TANK FOUNDATION PLAN & SECTION | PLAN & SECTION | Tank |  |  |  | PLAN & SECTION for Tank |  | FA | 0EF3010W16A06 | (Make-up WTR Tank) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System | 2007-08-02 | 2007-10-30 |  |  |  | 2024-05-04 | 2024-06-03 | 2024-07-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UGG-172563 | POTABLE WATER TANK FOUNDATION REBAR DETAIL | DETAIL | Tank |  |  |  | Detail Drawing for Tank |  | FI | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | 2024-11-27 | 2024-12-27 | 2025-01-26 | 2025-02-10 | 2025-02-25 | 2025-03-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0ULX-172581 | CALCULATION OF GENERAL SERVICE PUMP FOUNDATION | CALCULATION | Pump |  |  |  | Calculation sheet for Pump | Water Treatment System | FA | 0PF3010W42A04P | (Make-up WTR Pump) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Make-up Water Supply System > Make-up Water Pump | 2007-08-02 | 2008-04-02 | 2024-09-01 | 2024-10-01 | 2024-10-31 | 2024-11-15 | 2024-11-30 | 2024-12-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-172582 | GENERAL SERVICE PUMP FOUNDATIONS LAYOUT | LAYOUT | Pump |  |  |  | Layout Drawing for Pump |  | FA | 0EF3025W00A10 | (Intake Pump Station) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-04-03 |  | 2024-05-01 | 2024-05-31 | 2024-06-30 | 2024-07-15 | 2024-07-30 | 2024-08-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-172583 | GENERAL SERVICE PUMP FOUNDATIONS DETAILS (1) |  | Pump |  |  |  | for Pump |  | FA | 1PF3020W42A04P | (CEP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-09-07 | 2008-08-07 | 2024-10-05 | 2024-11-04 | 2024-12-04 | 2024-12-19 | 2025-01-03 | 2025-01-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-172584 | GENERAL SERVICE PUMP FOUNDATIONS DETAILS (2) |  | Pump |  |  |  | for Pump |  | FA | 2PF3020W42A04P | (CEP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condensate Extraction Pump | 2007-09-07 | 2008-09-08 | 2024-10-05 | 2024-11-04 | 2024-12-04 | 2024-12-19 | 2025-01-03 | 2025-01-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0ULX-172585 | GENERAL SERVICE PUMP FOUNDATIONS DETAILS (3) |  | Pump |  |  |  | for Pump |  | FA | 3PF3030W42A04P | (ACW PUMP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Auxiliary Cooling Water System | 2007-10-03 | 2008-12-01 | 2024-10-31 | 2024-11-30 | 2024-12-30 | 2025-01-14 | 2025-01-29 | 2025-02-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UAZ-172601 | CALCULATION OF EHV CABLE TRENCH & DIRECT BURIED CABLE | CALCULATION |  |  |  |  | Calculation sheet |  | FA | 1PF6040W74A06P | (EHV Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2008-02-29 | 2024-12-20 | 2025-01-19 | 2025-02-18 | 2025-03-05 | 2025-03-20 | 2025-04-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UAZ-172602 | EHV CABLE TRENCH & DIRECT BURIED CABLE OVERALL LAYOUT | LAYOUT |  |  |  |  | Layout Drawing | Substation | SKIP | 1PF6040W74A07T | (EHV Cable) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2008-03-01 | 2008-04-15 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UAZ-172603 | EHV CABLE TRENCH & DIRECT BURIED CABLE LAYOUT | LAYOUT |  |  |  |  | Layout Drawing | Substation | SKIP | 1CF6040W74A08 | (EHV Cable) Cable Electrical Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2008-04-16 | 2008-07-01 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UAZ-172608 | EHV CABLE TRENCH & DIRECT BURIED CABLE PLAN & SECTION | PLAN & SECTION |  |  |  |  | PLAN & SECTION |  | FA | 2CF6040W74A08 | (EHV Cable) Cable Electrical Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2008-05-17 | 2008-08-01 |  |  |  | 2025-02-17 | 2025-03-19 | 2025-04-18 | generated | 0.60 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UAZ-172613 | EHV CABLE TRENCH & DIRECT BURIED CABLE DETAIL | DETAIL |  |  |  |  | Detail Drawing |  | FI | 1PF6040W74A06P | (EHV Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2008-02-29 | 2024-09-27 | 2024-10-27 | 2024-11-26 | 2024-12-11 | 2024-12-26 | 2025-01-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UZT-172701 | CALCULATION OF ELECTRICAL DUCT BANK MANHOLE | CALCULATION |  |  |  |  | Calculation sheet |  | FA | 1PF1615W64A06P | (HRSG #11 Duct) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | 2007-06-14 | 2008-01-31 | 2024-11-01 | 2024-12-01 | 2024-12-31 | 2025-01-15 | 2025-01-30 | 2025-02-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZT-172702 | ELECTRICAL DUCT BANK OVERALL LAYOUT | OVERALL LAYOUT |  |  |  |  | OVERALL LAYOUT |  | FA | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZT-172703 | ELECTRICAL DUCT BANK LAYOUT | LAYOUT |  |  |  |  | Layout Drawing | Substation | SKIP | 2EF1615W00A01 | (HRSG #21 Duct) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2007-05-30 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZT-172704 | ELECTRICAL DUCT BANK TYPICAL SECTION & R.C DETAILS | [7 empty] | FA | 2CF1615W64A08 | (HRSG #21 Duct) Duct Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | 2008-10-18 | 2009-01-17 |  |  |  | 2025-07-21 | 2025-08-20 | 2025-09-19 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZT-172713 | ELECTRICAL DUCT BANK MANHOLE SCHEDULE | SCHEDULE |  |  |  |  | Schedule |  | FI | 3CF1615W64A08 | (HRSG #31 Duct) Duct Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2008-11-18 | 2009-02-17 | 2025-10-20 | 2025-11-19 | 2025-12-19 | 2026-01-03 | 2026-01-18 | 2026-02-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZT-172716 | ELECTRICAL DUCT BANK MANHOLE PLAN, SECTION & R.C DETAILS | [7 empty] | FA | 3CF1615W64A08 | (HRSG #31 Duct) Duct Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2008-11-18 | 2009-02-17 |  |  |  | 2025-08-21 | 2025-09-20 | 2025-10-20 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0GUC-172801 | CALCULATION OF STORMWATER POND | CALCULATION |  |  |  |  | Calculation sheet |  | FA | 0PF4035W42A05P | (STP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-09-03 | 2008-09-01 | 2025-01-21 | 2025-02-20 | 2025-03-22 | 2025-04-06 | 2025-04-21 | 2025-05-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0GUC-172802 | CLEAN STORM WATER PONDS OVERALL LAYOUT | OVERALL LAYOUT |  |  |  |  | OVERALL LAYOUT |  | FA | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0GUC-172803 | CLEAN STORM WATER PONDS PLAN AND SECTION | [7 empty] | FA | 2EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | 2007-03-15 | 2008-01-15 |  |  |  | 2024-10-11 | 2024-11-10 | 2024-12-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0GUC-172804 | STORMWATER POND DETAIL | DETAIL |  |  |  |  | Detail Drawing |  | FI | 0PF4035W42A05P | (STP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-09-03 | 2008-09-01 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UZA-172901 | CALCULATION OF ROAD AND PAVING | CALCULATION |  |  |  |  | Calculation sheet |  | FA | 0CF5570W30A07 | (Road & Parking Place) Civil Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Road & Parking Places | 2008-04-11 | 2008-09-25 | 2025-08-30 | 2025-09-29 | 2025-10-29 | 2025-11-13 | 2025-11-28 | 2025-12-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZA-172902 | ROAD AND PAVING OVERALL LAYOUT | OVERALL LAYOUT |  |  |  |  | OVERALL LAYOUT |  | FA | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZA-172903 | ROAD AND PAVING LAYOUT | LAYOUT |  |  |  |  | Layout Drawing | Substation | SKIP | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZA-172904 | ROAD AND PAVING - GRAVEL PAVEMENT PLAN & SECTION | [7 empty] | FA | 0EF5570W30A05 | (Road & Parking Place) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Road & Parking Places | 2007-11-01 | 2008-02-12 |  |  |  | 2024-08-03 | 2024-09-02 | 2024-10-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZA-172908 | ROAD AND PAVING DETAIL | DETAIL |  |  |  |  | Detail Drawing |  | FI | 0EF5570W30A05 | (Road & Parking Place) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Road & Parking Places | 2007-11-01 | 2008-02-12 | 2024-12-27 | 2025-01-26 | 2025-02-25 | 2025-03-12 | 2025-03-27 | 2025-04-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZA-172911 | ROAD MARKING AND SIGN BOARD LAYOUT | LAYOUT |  |  |  |  | Layout Drawing | Substation | SKIP | 0EF5570W30A05 | (Road & Parking Place) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Road & Parking Places | 2007-11-01 | 2008-02-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZA-172912 | ROAD MARKING AND SIGN BOARD DETAIL | DETAIL |  |  |  |  | Detail Drawing |  | FI | 0EF5570W30A05 | (Road & Parking Place) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Road & Parking Places | 2007-11-01 | 2008-02-12 | 2024-12-27 | 2025-01-26 | 2025-02-25 | 2025-03-12 | 2025-03-27 | 2025-04-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0UZT-173001 | CALCULATION OF LIGHTING POLE FOUNDATION | CALCULATION |  |  |  |  | Calculation sheet |  | FA | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | 2024-12-19 | 2025-01-18 | 2025-02-17 | 2025-03-04 | 2025-03-19 | 2025-04-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZT-173002 | LIGHTING POLE FOUNDATION OVERALL LAYOUT | OVERALL LAYOUT |  |  |  |  | OVERALL LAYOUT |  | FA | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZT-173003 | LIGHTING POLE FOUNDATION LAYOUT | LAYOUT |  |  |  |  | Layout Drawing | Substation | SKIP | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZT-173008 | LIGHTING POLE FOUNDATION PLAN & DETAIL | PLAN & DETAIL |  | Lighting |  |  | PLAN & DETAIL for Lighting |  | FA | 0PF6040W70A03T | (Lighting Equip) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2008-02-28 | 2008-04-12 |  |  |  | 2024-11-30 | 2024-12-30 | 2025-01-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UGF-173101 | FIREFIGHTING & POTABLE WATER PIPE CIVIL WORKS OVERALL LAYOUT | OVERALL LAYOUT |  | Fire Fighting |  |  | OVERALL LAYOUT for Fire Fighting | Fire Fighting System | FA | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UGF-173102 | FIREFIGHTING & POTABLE WATER PIPE CIVIL WORKS LAYOUT | LAYOUT |  | Fire Fighting |  |  | Layout Drawing for Fire Fighting | Fire Fighting System | FA | 0EF4500W00A01.1 | (Fire Fighting BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 |  |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UGF-173107 | FIREFIGHTING & POTABLE WATER PIPE CIVIL WORKS |  |  | Fire Fighting |  |  | for Fire Fighting |  | FA | 0CF4500W38A09 | (Fire WTR Pump Shelter) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2008-05-31 | 2008-07-16 | 2026-11-23 | 2026-12-23 | 2027-01-22 | 2027-02-06 | 2027-02-21 | 2027-03-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZJ-173202 | FENCE AND GATE OVERALL LAYOUT | OVERALL LAYOUT |  |  |  |  | OVERALL LAYOUT |  | FA | 0EF5570W16A10 | (Fence & Gate) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-12-12 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZJ-173208 | FENCE AND GATE PLAN AND DETAIL | PLAN AND DETAIL |  |  |  |  | PLAN AND DETAIL |  | FA | 0EF5570W16A10 | (Fence & Gate) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-12-12 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZJ-173209 | INTERNAL FENCE AND GATE PLAN AND DETAIL | PLAN AND DETAIL |  |  |  |  | PLAN AND DETAIL |  | FA | 0EF5570W16A10 | (Fence & Gate) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-12-12 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0GUB-173301 | CALCULATION OF STORMWATER DRAINAGE | CALCULATION |  |  |  |  | Calculation sheet |  | FA | 0PF4035W42A05P | (STP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-09-03 | 2008-09-01 | 2025-01-21 | 2025-02-20 | 2025-03-22 | 2025-04-06 | 2025-04-21 | 2025-05-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0GUB-173302 | STORMWATER DRAINAGE OVERALL LAYOUT | OVERALL LAYOUT |  |  |  |  | OVERALL LAYOUT |  | FA | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0GUB-173303 | STORMWATER DRAINAGE LAYOUT | LAYOUT |  |  |  |  | Layout Drawing | Substation | SKIP | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0GUB-173313 | STORMWATER DRAINAGE STRUCTURAL DETAIL | DETAIL |  |  |  |  | Detail Drawing |  | FI | 0PF4035W42A05P | (STP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-09-03 | 2008-09-01 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0GQB-173401 | CALCULATION OF WASTE WATER DRAINAGE OVERALL LAYOUT | CALCULATION |  |  |  |  | Calculation sheet |  | FA | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-09-01 | 2025-01-21 | 2025-02-20 | 2025-03-22 | 2025-04-06 | 2025-04-21 | 2025-05-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UT01-P0GQB-173402 | WASTE WATER DRAINAGE OVERALL LAYOUT | OVERALL LAYOUT |  |  |  |  | OVERALL LAYOUT |  | FA | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 |  |  |  | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UT01-P0GQB-173403 | WASTE WATER DRAINAGE LAYOUT | LAYOUT |  |  |  |  | Layout Drawing | Substation | SKIP | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-UT01-P0GQB-173413 | WASTE WATER DRAINAGE MANHOLE SCHEDULE | SCHEDULE |  |  |  |  | Schedule |  | FI | 0CF4035W16A03.2 | (WWT LEB) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2008-02-02 | 2008-06-02 | 2025-01-03 | 2025-02-02 | 2025-03-04 | 2025-03-19 | 2025-04-03 | 2025-04-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0GQB-173417 | WASTE WATER DRAINAGE STRUCTURE MANHOLE RE-BAR DETAIL | DETAIL |  |  |  |  | Detail Drawing |  | FI | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-09-01 | 2024-10-29 | 2024-11-28 | 2024-12-28 | 2025-01-12 | 2025-01-27 | 2025-02-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZK-173501 | LANDSCAPE LAYOUT | LAYOUT |  |  |  |  | Layout Drawing | Substation | SKIP | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZK-173502 | LANDSCAPING CROSS SECTION & DETAIL | & DETAIL |  |  |  |  | & DETAIL |  | FA | 0CF6010W28A05 | Land Scape | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-06-28 | 2024-03-31 | 2024-04-30 | 2024-05-30 | 2024-06-14 | 2024-06-29 | 2024-07-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZK-173503 | WATER TANK SECTION & DETAIL | SECTION & DETAIL |  |  |  |  | SECTION & DETAIL |  | FA | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZK-173504 | PAVILION PLAN & DETAIL | PLAN & DETAIL |  |  |  |  | PLAN & DETAIL |  | FA | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZK-173505 | PUMP ROOM PLAN AND DETAIL | PLAN AND DETAIL |  |  |  |  | PLAN AND DETAIL |  | FA | 0EF4500W32A04 | (Fire WTR Pump Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 | 2007-08-27 |  |  |  | 2024-03-01 | 2024-03-02 | 2024-04-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0GKC-173601 | CALCULATION OF CHILLED WATER STORAGE TANK FOUNDATION | CALCULATION | CHILLED WATER STORAGE TANK |  |  |  | Calculation sheet for CHILLED WATER STORAGE TANK | Water Treatment System | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | 2024-11-01 | 2024-12-01 | 2024-12-31 | 2025-01-15 | 2025-01-30 | 2025-02-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0GKC-173602 | CHILLED WATER STORAGE TANK FOUNDATION DETAIL | DETAIL | CHILLED WATER STORAGE TANK |  |  |  | Detail Drawing for CHILLED WATER STORAGE TANK |  | FI | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | 2024-11-27 | 2024-12-27 | 2025-01-26 | 2025-02-10 | 2025-02-25 | 2025-03-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0GKC-173702 | POTABLE WATER CHILLER FOUNDATION DETAIL | DETAIL |  |  |  |  | Detail Drawing |  | FI | 0EF3035W16A14 | (PWT) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-11-02 | 2008-03-04 | 2024-12-28 | 2025-01-27 | 2025-02-26 | 2025-03-13 | 2025-03-28 | 2025-04-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE04-P0GHC-173801 | CALCULATION OF ATM FLASH TANK & DRAIN PUMP PIT | CALCULATION | flash Tank | Drain System |  |  | Calculation sheet for flash Tank |  | FA | 1EF3020W16A03.1 | (Clean Drain Flash Vessel) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | 2007-10-03 | 2008-02-29 |  |  |  | 2024-07-05 | 2024-08-04 | 2024-09-03 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0GHC-173802 | ATM FLASH TANK & DRAIN PUMP PIT DETAIL | DETAIL | flash Tank | Drain System |  |  | Detail Drawing for flash Tank |  | FA | 1PF3020W42A06.1P | (Clean Drain Flash Vessel) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | 2007-10-03 | 2008-04-02 | 2025-04-20 | 2025-05-20 | 2025-06-19 | 2025-07-04 | 2025-07-19 | 2025-08-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB02-P0UZJ-173902 | POWER PLANT DIESEL GENERATOR FOUNDATION PLAN | PLAN | EDG |  |  |  | Plan for EDG |  | FA | 0EF3530W16A14.1 | (Common EDG BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Common Emergency Diesel Generator | 2007-07-27 | 2007-10-24 |  |  |  | 2024-04-28 | 2024-05-28 | 2024-06-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VK02-P0UZJ-173903 | POWER PLANT DIESEL GENERATOR FOUNDATION REINF. DETAIL | DETAIL | EDG |  |  |  | Detail Drawing for EDG |  | FI | 1PF3530W42A06P | (Block #1 EDG) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Emergency Diesel Generator | 2007-08-01 | 2008-05-30 | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180001 | STANDARD DRAWING - GENERAL NOTES, ABBREVIATION, LEGEND & SIMBOLS | STANDARD DRAWING |  |  |  |  | STANDARD DRAWING |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 |  |  |  | 2024-03-01 | 2024-03-19 | 2024-04-18 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180002 | STANDARD DRAWING - INTERIOR FINISH DETAILS | STANDARD DRAWING |  |  |  |  | STANDARD DRAWING |  | FA | 0CF5565W24A10 | (Warehouse) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Warehouse | 2008-10-06 | 2008-12-01 |  |  |  | 2025-07-09 | 2025-08-08 | 2025-09-07 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180006 | STANDARD DRAWING - CLADDING JOINT DETAILS | STANDARD DRAWING |  |  |  |  | STANDARD DRAWING |  | FA | 3CF2010W20A07 | (STG #30 BLDG) Cladding Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2008-06-25 | 2008-11-11 |  |  |  | 2025-03-28 | 2025-04-27 | 2025-05-27 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180008 | STANDARD DRAWING - MISC. ARCHITECTURAL DETAILS | STANDARD DRAWING |  |  |  |  | STANDARD DRAWING |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 |  |  |  | 2024-03-01 | 2024-03-19 | 2024-04-18 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180019 | STANDARD DRAWING - DOOR SCHEDULE | SCHEDULE |  |  |  |  | Schedule |  | FI | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-15 | 2024-04-30 | 2024-05-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180020 | STANDARD DRAWING - DOOR DETAILS | DETAILS |  |  |  |  | DETAILS |  | FI | 0EF5570W16A10 | (Fence & Gate) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-12-12 | 2024-08-01 | 2024-08-31 | 2024-09-30 | 2024-10-15 | 2024-10-30 | 2024-11-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180024 | STANDARD DRAWING - WINDOW SCHEDULE | SCHEDULE |  |  |  |  | Schedule |  | FI | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-15 | 2024-04-30 | 2024-05-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180025 | STANDARD DRAWING - WINDOW DETAILS | DETAILS |  |  |  |  | DETAILS |  | FI | 0EF1000W00A10 | Instrument Installation Detail | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-05-11 | 2007-09-28 | 2024-04-11 | 2024-05-11 | 2024-06-10 | 2024-06-25 | 2024-07-10 | 2024-07-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180030 | STANDARD DRAWING - RE - BAR STANDARD | STANDARD DRAWING |  |  |  |  | STANDARD DRAWING |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 |  |  |  | 2024-03-01 | 2024-03-19 | 2024-04-18 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180033 | STANDARD DRAWING - GENERAL NOTES, MATERIALS, CONNECTIONS & MEMBER SIZE DESIGNATION | STANDARD DRAWING |  |  |  |  | STANDARD DRAWING |  | FA | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180034 | STANDARD DRAWING - ABBREVIATIONS & WELDING | STANDARD DRAWING |  |  |  |  | STANDARD DRAWING |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 |  |  |  | 2024-03-01 | 2024-03-19 | 2024-04-18 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180035 | STANDARD DRAWING - MOMENT CONNECTION DETAILS | STANDARD DRAWING |  |  |  |  | STANDARD DRAWING |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 |  |  |  | 2024-03-01 | 2024-03-19 | 2024-04-18 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180036 | STANDARD DRAWING - SHEAR CONNECTION DETAILS | DRAWING |  |  |  |  | DRAWING |  | FA | 0PF6020W46A08P | (Hanger & Support & Fitting) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-02-29 | 2024-10-26 | 2024-11-25 | 2024-12-25 | 2025-01-09 | 2025-01-24 | 2025-02-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180037 | STANDARD DRAWING - TYPICAL VERTICAL & HORIZONTAL BRACING CONNECTION DETAILS | DRAWING |  |  |  |  | DRAWING |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-06-29 | 2024-07-29 | 2024-08-28 | 2024-09-12 | 2024-09-27 | 2024-10-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180038 | STANDARD DRAWING - TYPICAL STAIR & HANDRAIL DETAILS | DRAWING |  |  |  |  | DRAWING |  | FA | 0PF6040W74A02P | (Raceway) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Raceway System | 2007-09-03 | 2008-01-31 | 2024-10-15 | 2024-11-14 | 2024-12-14 | 2024-12-29 | 2025-01-13 | 2025-01-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180039 | STANDARD DRAWING - TYPICAL STAIR STRINGER CONNECTION DETAILS | DRAWING |  |  |  |  | DRAWING |  | FA | 0PF6020W46A08P | (Hanger & Support & Fitting) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-02-29 | 2024-10-26 | 2024-11-25 | 2024-12-25 | 2025-01-09 | 2025-01-24 | 2025-02-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180040 | STANDARD DRAWING - GIRTH & PURLIN CONNECTION DETAILS | DRAWING |  |  |  |  | DRAWING |  | FA | 0PF6020W46A08P | (Hanger & Support & Fitting) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-02-29 | 2024-10-26 | 2024-11-25 | 2024-12-25 | 2025-01-09 | 2025-01-24 | 2025-02-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180041 | STANDARD DRAWING - TYPICAL GRATING AND CHK'D PLATE DETAILS | DRAWING |  |  |  |  | DRAWING |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2024-06-29 | 2024-07-29 | 2024-08-28 | 2024-09-12 | 2024-09-27 | 2024-10-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180042 | STANDARD DRAWING - LADDER DETAILS | DRAWING |  |  |  |  | DRAWING |  | FA | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | 2024-09-12 | 2024-10-12 | 2024-11-11 | 2024-11-26 | 2024-12-11 | 2024-12-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180043 | STANDARD DRAWING - PLUMBING STANDARD SYMBOL & ABBREVIATION | DRAWING |  |  |  |  | DRAWING |  | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | 2024-10-26 | 2024-11-25 | 2024-12-25 | 2025-01-09 | 2025-01-24 | 2025-02-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CC05-P0ZEN-180044 | STANDARD DRAWING - PLUMBING STANDARD GENERAL DETAILS | DRAWING |  |  |  |  | DRAWING |  | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | 2024-10-26 | 2024-11-25 | 2024-12-25 | 2025-01-09 | 2025-01-24 | 2025-02-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UMA-180401 | ST BUILDING - GROUND FLOOR PLAN | PLAN |  |  | Steam Turbine Building |  | Plan for Steam Turbine Building |  | FA | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UMA-180402 | ST BUILDING - ROOF PLAN | PLAN |  |  | Steam Turbine Building |  | Plan for Steam Turbine Building |  | FA | 2CF2010W20A08 | (STG #20 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2008-08-05 | 2008-11-06 |  |  |  | 2025-05-08 | 2025-06-07 | 2025-07-07 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UMA-180403 | ST BUILDING - ELEVATION | ELEVATION |  |  | Steam Turbine Building |  | Elevation Drawing for Steam Turbine Building | ST BUILDING | FI | 1EF2010W20A02 | (STG #10 BLDG) Buliding Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 | 2007-09-18 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UMA-180404 | ST BUILDING - SECTION | SECTION |  |  | Steam Turbine Building |  | SECTION for Steam Turbine Building | ST BUILDING | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UMA-180405 | ST BUILDING - INTERIOR FINISH SCHEDULE | SCHEDULE |  |  | Steam Turbine Building |  | Schedule for Steam Turbine Building |  | FA | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UMA-180406 | ST BUILDING - DOOR SCHEDULE | SCHEDULE |  |  | Steam Turbine Building |  | Schedule for Steam Turbine Building |  | FA | 0CF4500W24A10 | (Fire Fighting BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2008-05-21 | 2008-07-11 |  |  |  | 2025-02-21 | 2025-03-23 | 2025-04-22 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UMA-180408 | ST BUILDING - WALL SECTION | SECTION |  |  | Steam Turbine Building |  | SECTION for Steam Turbine Building | ST BUILDING | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UMA-180451 | ST BUILDING - PILE ARRANGEMENT | ARRANGEMENT |  |  | Steam Turbine Building |  | ARRANGEMENT for Steam Turbine Building |  | FA | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UMA-180452 | ST BUILDING - FOUNDATION LOCATION PLAN | PLAN |  |  | Steam Turbine Building |  | Plan for Steam Turbine Building |  | FA | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UMA-180454 | ST BUILDING - PILE CAP & FOUNDATION REINFORCEMENT DETAIL |  |  |  | Steam Turbine Building |  | for Steam Turbine Building |  | FA | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180458 | ST BUILDING - COLUMN LOCATION PLAN | PLAN |  |  | Steam Turbine Building |  | Plan for Steam Turbine Building |  | FA | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180459 | ST BUILDING - BASE PLATE DETAIL |  |  |  | ST BUILDING |  | for ST BUILDING | ST BUILDING | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180460 | ST BUILDING - CRANE GIRDER FRAMING PLAN | PLAN |  |  | ST BUILDING |  | Plan for ST BUILDING | ST BUILDING | FI | 0CF2010W42A07 | (Crane & Hoist) Crane Erection for STG Building | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2008-07-17 | 2008-09-17 |  |  |  | 2025-04-19 | 2025-05-19 | 2025-06-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180462 | ST BUILDING - ROOF FRAMING PLAN | PLAN |  |  | ST BUILDING |  | Plan for ST BUILDING | ST BUILDING | FI | 2CF2010W20A08 | (STG #20 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2008-08-05 | 2008-11-06 |  |  |  | 2025-05-08 | 2025-06-07 | 2025-07-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180463 | ST BUILDING - FRAMING ELEVATION |  |  |  | ST BUILDING |  | for ST BUILDING | ST BUILDING | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180464 | ST BUILDING - GIRT NORTH - SOUTH ELEVATION |  |  |  | ST BUILDING |  | for ST BUILDING | ST BUILDING | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180465 | ST BUILDING - GIRT EAST - WEST ELEVATION |  |  |  | ST BUILDING |  | for ST BUILDING | ST BUILDING | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180466 | ST BUILDING - MISC. PLATFORM PLAN & SECTION | PLAN & SECTION |  |  | ST BUILDING |  | PLAN & SECTION for ST BUILDING | ST BUILDING | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180467 | ST BUILDING - STAIR PLAN, ELEVATION & DETAIL | PLAN, ELEVATION & DETAIL |  |  | ST BUILDING |  | PLAN, ELEVATION & DETAIL for ST BUILDING | ST BUILDING | FI | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180468 | ST BUILDING – MAIN TRUSS DETAIL |  |  |  | ST BUILDING |  | for ST BUILDING | ST BUILDING | FI | 2EF1625W16A03 | (HRSG #21 Main Stack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Main Stack | 2007-10-09 | 2008-02-15 |  |  |  | 2024-07-11 | 2024-08-10 | 2024-09-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180469 | ST BUILDING - ROOF WALKWAY FRAMING PLAN | PLAN |  |  | ST BUILDING |  | Plan for ST BUILDING | ST BUILDING | FI | 2CF2010W20A08 | (STG #20 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2008-08-05 | 2008-11-06 |  |  |  | 2025-05-08 | 2025-06-07 | 2025-07-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180471 | ST BUILDING - ROOF PURLIN PLAN | PLAN |  |  | ST BUILDING |  | Plan for ST BUILDING | ST BUILDING | FI | 3CF2010W20A08 | (STG #30 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2008-09-04 | 2008-12-05 |  |  |  | 2025-06-07 | 2025-07-07 | 2025-08-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UMA-180481 | ST BUILDING - EQUIPMENT DRAIN PLAN | PLAN |  |  | ST BUILDING |  | Plan for ST BUILDING | ST BUILDING | FI | 1EF3020W16A09.1 | (Clean Drain Tank) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | 2007-12-06 | 2008-05-05 |  |  |  | 2024-09-07 | 2024-10-07 | 2024-11-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UMA-180482 | ST BUILDING - EQUIPMENT DRAIN PLAN (ISO) |  |  |  | ST BUILDING |  | for ST BUILDING | ST BUILDING | FI | 2EF3020W16A09.1 | (Clean Drain Tank) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | 2007-12-06 | 2008-05-05 |  |  |  | 2024-09-07 | 2024-10-07 | 2024-11-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UMA-180490 | ST BUILDING - DESIGN CALCULATION FOR FOUNDATION | DESIGN CALCULATION |  |  | ST BUILDING |  | DESIGN CALCULATION for ST BUILDING | ST BUILDING | FI | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UMA-180491 | ST BUILDING - DESIGN CALCULATION FOR BASE PLATE, COLUMN, BEAM & ROOF TRUSS | DESIGN CALCULATION |  |  | ST BUILDING |  | DESIGN CALCULATION for ST BUILDING | ST BUILDING | FI | 0EF5566W32A04 | (ADMIN BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UMA-180492 | ST BUILDING - DESIGN CALCULATION FOR CRANE GIRDER, PURLIN & SIDE GIRT | DESIGN CALCULATION |  |  | ST BUILDING |  | DESIGN CALCULATION for ST BUILDING | ST BUILDING | FI | 0CF5544W42A11 | (Crane & Hoist) Crane Erection for GIS Building | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2008-02-15 | 2008-04-01 |  |  |  | 2024-11-17 | 2024-12-17 | 2025-01-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0BAT-180500 | ROOF FOR GTG TR - CALCULATION | CALCULATION | Gas Turbine Generator |  |  |  | Calculation sheet for GTG |  | FI | 1CF1210W20A10 | (GTG Common BLDG) Structure Work(S/S, Cladding, Roof) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2008-01-16 | 2008-05-19 |  |  |  | 2024-10-18 | 2024-11-17 | 2024-12-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMA-180500 | ST BUILDING_MISC. PLATFORM PLAN & SECTION | PLAN & SECTION |  |  | ST BUILDING |  | PLAN & SECTION for ST BUILDING | ST BUILDING | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P1BAT-180511 | ROOF FOR GTG #1 TR - PLAN, SECTION, ELEVATION | PLAN, SECTION, ELEVATION | Gas Turbine Generator |  |  |  | PLAN, SECTION, ELEVATION for GTG |  | FI | 1CF1210W20A10 | (GTG Common BLDG) Structure Work(S/S, Cladding, Roof) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2008-01-16 | 2008-05-19 |  |  |  | 2024-10-18 | 2024-11-17 | 2024-12-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P1BAT-180512 | ROOF FOR GTG #1 TR - COLUMN ARRAGEMENT, ROOF FRAMING PLAN, BASEPLATE DETAILS |  | Gas Turbine Generator |  |  |  | for GTG |  | FA | 1CF1210W20A10 | (GTG Common BLDG) Structure Work(S/S, Cladding, Roof) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2008-01-16 | 2008-05-19 | 2025-05-14 | 2025-06-13 | 2025-07-13 | 2025-07-28 | 2025-08-12 | 2025-08-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P1BAT-180513 | ROOF FOR GTG #1 TR - ROOF FRAMING ELEVATION, CONNECTION DETAILS |  | Gas Turbine Generator #1 TR |  |  |  | for Gas Turbine Generator #1 TR |  | FA | 1CF1210W20A10 | (GTG Common BLDG) Structure Work(S/S, Cladding, Roof) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2008-01-16 | 2008-05-19 | 2025-05-14 | 2025-06-13 | 2025-07-13 | 2025-07-28 | 2025-08-12 | 2025-08-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UCB-180600 | CENTRAL CONTROL BUILDING - CALCULATION | CALCULATION |  |  | CENTRAL CONTROL BUILDING |  | Calculation sheet for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180601 | CENTRAL CONTROL BUILDING - GROUND FLOOR PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180602 | CENTRAL CONTROL BUILDING - 1ST FLOOR PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180603 | CENTRAL CONTROL BUILDING - 2ND FLOOR PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180604 | CENTRAL CONTROL BUILDING - ROOF PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180605 | CENTRAL CONTROL BUILDING - SIDE WALL ELEVATION | ELEVATION |  |  | CENTRAL CONTROL BUILDING |  | Elevation Drawing for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180606 | CENTRAL CONTROL BUILDING - MAIN SECTION | SECTION |  |  | CENTRAL CONTROL BUILDING |  | SECTION for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180607 | CENTRAL CONTROL BUILDING - INTERIOR FINISH SCHEDULE | SCHEDULE |  |  | CENTRAL CONTROL BUILDING |  | Schedule for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180608 | CENTRAL CONTROL BUILDING - DOOR & WINDOW SCHEDULE | SCHEDULE |  |  | CENTRAL CONTROL BUILDING |  | Schedule for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180609 | CENTRAL CONTROL BUILDING - STAIRCASE#1 ENLARGED PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180610 | CENTRAL CONTROL BUILDING - STAIRCASE#2 ENLARGED PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180611 | CENTRAL CONTROL BUILDING - ENLARGED TOILET PLAN & ELEVATION | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180612 | CENTRAL CONTROL BUILDING - WALL OPENING ELEVATION | ELEVATION |  |  | CENTRAL CONTROL BUILDING |  | Elevation Drawing for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180613 | CENTRAL CONTROL BUILDING - CEILING PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UCB-180614 | CENTRAL CONTROL BUILDING - MISC. DETAIL |  |  |  | CENTRAL CONTROL BUILDING |  | for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180651 | CENTRAL CONTROL BUILDING - FDN & COLUMN ARRANGEMENT PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180652 | CENTRAL CONTROL BUILDING - GROUND FLOOR FRAMING PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180653 | CENTRAL CONTROL BUILDING - 1ST FLOOR FRAMING PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180654 | CENTRAL CONTROL BUILDING - 2ND FLOOR FRAMING PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180655 | CENTRAL CONTROL BUILDING - ROOF FRAMING PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180656 | CENTRAL CONTROL BUILDING - LINE FRAMING ELEVATION | ELEVATION |  |  | CENTRAL CONTROL BUILDING |  | Elevation Drawing for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180657 | CENTRAL CONTROL BUILDING - ROW FRAMING ELEVATION | ELEVATION |  |  | CENTRAL CONTROL BUILDING |  | Elevation Drawing for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180658 | CENTRAL CONTROL BUILDING - STAIRCASE#1 FRAMING PLAN & ELEVATION | PLAN & ELEVATION |  |  | CENTRAL CONTROL BUILDING |  | PLAN & ELEVATION for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180659 | CENTRAL CONTROL BUILDING - STAIRCASE#2 FRAMING PLAN & ELEVATION | PLAN & ELEVATION |  |  | CENTRAL CONTROL BUILDING |  | PLAN & ELEVATION for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180660 | CENTRAL CONTROL BUILDING - 1ST FLOOR OPENING PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UCB-180661 | CENTRAL CONTROL BUILDING - 2ND FLOOR OPENING PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UCB-180664 | CENTRAL CONTROL BUILDING - FOUNDATION RE - BAR DETAIL |  |  |  | CENTRAL CONTROL BUILDING |  | for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UCB-180665 | CENTRAL CONTROL BUILDING - COLUMN RE - BAR SCHEDULE | SCHEDULE |  |  | CENTRAL CONTROL BUILDING |  | Schedule for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UCB-180666 | CENTRAL CONTROL BUILDING - BEAM & GIRDER RE - BAR SCHEDULE | SCHEDULE |  |  | CENTRAL CONTROL BUILDING |  | Schedule for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UCB-180667 | CENTRAL CONTROL BUILDING - SLAB & MISC. RE - BAR SCHEDULE | SCHEDULE |  |  | CENTRAL CONTROL BUILDING |  | Schedule for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UCB-180668 | CENTRAL CONTROL BUILDING - STRUCTURAL MISC. DETAIL | DETAIL |  |  | CENTRAL CONTROL BUILDING |  | Detail Drawing for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 |  |  |  | 2024-07-01 | 2024-07-31 | 2024-08-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UCB-180681 | CENTRAL CONTROL BUILDING - PLUMBING EQUIPMENT SCHEDULE | SCHEDULE |  |  | CENTRAL CONTROL BUILDING |  | Schedule for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UCB-180682 | CENTRAL CONTROL BUILDING - PLUMBING SCHEMATIC DIAGRAM | DIAGRAM |  |  | CENTRAL CONTROL BUILDING |  | Diagram for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UCB-180683 | CENTRAL CONTROL BUILDING - GROUND FLOOR PLUMBING PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UCB-180684 | CENTRAL CONTROL BUILDING - 1ST FLOOR PLUMBING PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UCB-180685 | CENTRAL CONTROL BUILDING - 2ND FLOOR PLUMBING PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UCB-180686 | CENTRAL CONTROL BUILDING - ROOF PLUMBING PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UCB-180687 | CENTRAL CONTROL BUILDING - ENLARGED TOILET & SHOWER PLUMBING PLAN | PLAN |  |  | CENTRAL CONTROL BUILDING |  | Plan for CENTRAL CONTROL BUILDING | CENTRAL CONTROL BUILDING | FI | 0EF5510W32A04 | (CCR BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-09-14 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UBA-181000 | ST #1 LEB - CALCULATION | CALCULATION |  |  | Steam Turbine #1 Local Electrical Building |  | Calculation sheet for Steam Turbine #1 Local Electrical Building | Electrical Building | FI | 1EF1200W00A01.1 | (GTG #11 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 LEB | 2007-05-31 |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181001 | ST #1 LEB - GROUND FLOOR PLAN & INTERIOR FINISH SCHEDULE(INCL. DOOR & WINDOW) | Plan | Steam Turbine |  | Local Electrical Building |  | Plan for STG |  | FA | 1CF1200W24A10 | (GTG #11 LEB) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 LEB | 2008-05-27 | 2008-08-04 |  |  |  | 2025-02-27 | 2025-03-29 | 2025-04-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181002 | ST #1 LEB - ROOF PLAN | Plan | Steam Turbine |  | Local Electrical Building |  | Plan for STG |  | FA | 1CF2010W20A08 | (STG #10 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2008-08-05 | 2008-11-06 |  |  |  | 2025-05-08 | 2025-06-07 | 2025-07-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181003 | ST #1 LEB - SIDE WALL ELEVATION | ELEVATION | Steam Turbine |  | Local Electrical Building |  | Elevation Drawing for STG |  | FI | 1EF2020W00A02 | (ST #10) ST Aux' Steam Consumption Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181004 | ST #1 LEB - MAIN SECTION | SECTION | Steam Turbine |  | Local Electrical Building |  | SECTION for STG |  | FA | 1PF2020W42A10P | (ST #10) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2008-09-01 | 2024-09-04 | 2024-10-04 | 2024-11-03 | 2024-11-18 | 2024-12-03 | 2024-12-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181005 | ST #1 LEB - ARCHITECTURAL MISC. DETAIL | DETAIL | Steam Turbine |  | Local Electrical Building |  | Detail Drawing for STG |  | FI | 1PF2020W42A10P | (ST #10) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2008-09-01 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181051 | ST #1 LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | Plan | Steam Turbine |  | Local Electrical Building |  | Plan for STG |  | FA | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181052 | ST #1 LEB - GROUND FLOOR FRAMING PLAN | Plan | Steam Turbine |  | Local Electrical Building |  | Plan for STG |  | FA | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181053 | ST #1 LEB - ROOF FLOOR FRAMING PLAN | Plan | Steam Turbine |  | Local Electrical Building |  | Plan for STG |  | FA | 1CF2010W20A08 | (STG #10 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2008-08-05 | 2008-11-06 |  |  |  | 2025-05-08 | 2025-06-07 | 2025-07-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181054 | ST #1 LEB - LINE & ROW FRAMING ELEVATION | ELEVATION | Steam Turbine |  | Local Electrical Building |  | Elevation Drawing for STG |  | FI | 1EF2020W16A06 | (ST #10) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-07-03 | 2007-11-01 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181055 | ST #1 LEB - FOUNDATION, SLAB & MISC. DETAIL RE - BAR DETAIL | DETAIL | Steam Turbine |  | Local Electrical Building |  | Detail Drawing for STG |  | FI | 1CF2020W16A08 | (ST #10) Pedestal & Top Slab Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2008-03-04 | 2008-08-29 | 2025-04-30 | 2025-05-30 | 2025-06-29 | 2025-07-14 | 2025-07-29 | 2025-08-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181056 | ST #1 LEB - COLUMN, BEAM & GIRDER RE - BAR SCHEDULE | SCHEDULE | Steam Turbine |  | Local Electrical Building |  | Schedule for STG |  | FA | 1PF2020W42A10P | (ST #10) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2008-09-01 | 2024-09-04 | 2024-10-04 | 2024-11-03 | 2024-11-18 | 2024-12-03 | 2024-12-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UBA-181100 | ST #2 LEB - CALCULATION | CALCULATION | Steam Turbine |  | Local Electrical Building |  | Calculation sheet for STG |  | FI | 2EF2020W00A02 | (ST #20) ST Aux' Steam Consumption Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-03-01 | 2007-03-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181101 | ST #2 LEB - GROUND FLOOR PLAN & INTERIOR FINISH SCHEDULE(INCL. DOOR & WINDOW) | Plan | Steam Turbine |  | Local Electrical Building |  | Plan for STG |  | FA | 2CF1200W24A10 | (GTG #21 LEB) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2008-05-27 | 2008-08-04 |  |  |  | 2025-02-27 | 2025-03-29 | 2025-04-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181102 | ST #2 LEB - ROOF PLAN | Plan | Steam Turbine |  | Local Electrical Building |  | Plan for STG |  | FA | 2CF2010W20A08 | (STG #20 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2008-08-05 | 2008-11-06 |  |  |  | 2025-05-08 | 2025-06-07 | 2025-07-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181103 | ST #2 LEB - SIDE WALL ELEVATION | ELEVATION | Steam Turbine |  | Local Electrical Building |  | Elevation Drawing for STG |  | FI | 2EF2020W16A06 | (ST #20) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-07-03 | 2007-11-01 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181104 | ST #2 LEB - MAIN SECTION | SECTION | Steam Turbine |  | Local Electrical Building |  | SECTION for STG |  | FA | 2PF2020W42A10P | (ST #20) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-03-01 | 2008-10-01 | 2024-09-04 | 2024-10-04 | 2024-11-03 | 2024-11-18 | 2024-12-03 | 2024-12-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181105 | ST #2 LEB - ARCHITECTURAL MISC. DETAIL | DETAIL | Steam Turbine |  | Local Electrical Building |  | Detail Drawing for STG |  | FI | 1PF2020W42A10P | (ST #10) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2008-09-01 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181151 | ST #2 LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | Plan | Steam Turbine |  | Local Electrical Building |  | Plan for STG |  | FA | 2EF2020W16A06 | (ST #20) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-07-03 | 2007-11-01 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181152 | ST #2 LEB - GROUND FLOOR FRAMING PLAN | Plan | Steam Turbine |  | Local Electrical Building |  | Plan for STG |  | FA | 2EF2020W16A06 | (ST #20) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-07-03 | 2007-11-01 |  |  |  | 2024-04-04 | 2024-05-04 | 2024-06-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181153 | ST #2 LEB - ROOF FLOOR FRAMING PLAN | Plan | Steam Turbine |  | Local Electrical Building |  | Plan for STG |  | FA | 2CF2010W20A08 | (STG #20 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2008-08-05 | 2008-11-06 |  |  |  | 2025-05-08 | 2025-06-07 | 2025-07-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181154 | ST #2 LEB - LINE & ROW FRAMING ELEVATION | ELEVATION |  |  | Steam Turbine #2 Local Electrical Building |  | Elevation Drawing for Steam Turbine #2 Local Electrical Building | ST BUILDING | FI | 2EF1200W32A04 | (GTG #21 LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-08-01 | 2007-11-27 |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181155 | ST #2 LEB - FOUNDATION, SLAB & MISC. DETAIL RE - BAR DETAIL | DETAIL |  |  | Steam Turbine #2 Local Electrical Building |  | Detail Drawing for Steam Turbine #2 Local Electrical Building | STEAM TURBINE GENERATOR | FA | 2CF1600W16A03.1 | (HRSG #22 LEB)FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > HRSG LEB | 2008-02-01 | 2008-03-29 |  |  |  | 2024-11-03 | 2024-12-03 | 2025-01-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181156 | ST #2 LEB - COLUMN, BEAM & GIRDER RE - BAR SCHEDULE | SCHEDULE |  |  | Steam Turbine #2 Local Electrical Building |  | Schedule for Steam Turbine #2 Local Electrical Building |  | FA | 2EF1200W32A04 | (GTG #21 LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-08-01 | 2007-11-27 | 2025-09-25 | 2025-10-25 | 2025-11-24 | 2025-12-09 | 2025-12-24 | 2026-01-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UBA-181200 | GTG #1,2 LEB - CALCULATION | CALCULATION |  |  | Gas Turbine Generator #1,2 Local Electrical Building |  | Calculation sheet for Gas Turbine Generator #1,2 Local Electrical Building | Electrical Building | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181201 | GTG #1,2 LEB - BASEMENT FLOOR PLAN | PLAN |  |  | Gas Turbine Generator #1,2 Local Electrical Building |  | Plan for Gas Turbine Generator #1,2 Local Electrical Building |  | FA | 2PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-09-03 | 2008-02-14 | 2024-12-30 | 2025-01-29 | 2025-02-28 | 2025-03-15 | 2025-03-30 | 2025-04-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181202 | GTG #1,2 LEB - GROUND FLOOR PLAN | PLAN |  |  | Gas Turbine Generator #1,2 Local Electrical Building |  | Plan for Gas Turbine Generator #1,2 Local Electrical Building |  | FA | 2PF1600W74A06P | (HRSG #21 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | 2007-09-15 | 2008-08-01 | 2025-01-11 | 2025-02-10 | 2025-03-12 | 2025-03-27 | 2025-04-11 | 2025-04-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181203 | GTG #1,2 LEB - ROOF PLAN | PLAN |  |  | Gas Turbine Generator #1,2 Local Electrical Building |  | Plan for Gas Turbine Generator #1,2 Local Electrical Building |  | FA | 2PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-09-03 | 2008-02-14 | 2024-12-30 | 2025-01-29 | 2025-02-28 | 2025-03-15 | 2025-03-30 | 2025-04-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181204 | GTG #1,2 LEB - SIDE WALL ELEVATION | ELEVATION |  |  | Gas Turbine Generator #1,2 Local Electrical Building |  | Elevation Drawing for Gas Turbine Generator #1,2 Local Electrical Building |  | FA | 2PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-09-03 | 2008-02-14 | 2024-12-14 | 2025-01-13 | 2025-02-12 | 2025-02-27 | 2025-03-14 | 2025-03-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181205 | GTG #1,2 LEB - MAIN SECTION | SECTION |  |  | Gas Turbine Generator #1,2 Local Electrical Building |  | SECTION for Gas Turbine Generator #1,2 Local Electrical Building | Electrical Building | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181206 | GTG #1,2 LEB - INTERIOR FINISH SCHEDULE (INCL. DOOR & WINDOW) | SCHEDULE |  |  | Gas Turbine Generator #1,2 Local Electrical Building |  | Schedule for Gas Turbine Generator #1,2 Local Electrical Building |  | FA | 2CF1200W24A10 | (GTG #21 LEB) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2008-05-27 | 2008-08-04 | 2025-09-23 | 2025-10-23 | 2025-11-22 | 2025-12-07 | 2025-12-22 | 2026-01-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181207 | GTG #1,2 LEB - STAIR PLAN & SECTION | PLAN & SECTION |  |  | Gas Turbine Generator #1,2 Local Electrical Building |  | PLAN & SECTION for Gas Turbine Generator #1,2 Local Electrical Building | STEAM TURBINE GENERATOR | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181208 | GTG #1,2 LEB - ARCHITECTURAL MISC. DETAIL | DETAIL |  |  | Gas Turbine Generator #1,2 Local Electrical Building |  | Detail Drawing for Gas Turbine Generator #1,2 Local Electrical Building |  | FA | 2PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-09-03 | 2008-02-14 | 2024-12-14 | 2025-01-13 | 2025-02-12 | 2025-02-27 | 2025-03-14 | 2025-03-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181251 | GTG #1,2 LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | PLAN |  |  | Gas Turbine Generator #1,2 Local Electrical Building |  | Plan for Gas Turbine Generator #1,2 Local Electrical Building |  | FA | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  | 2024-09-26 | 2024-10-26 | 2024-11-25 | 2024-12-10 | 2024-12-25 | 2025-01-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181252 | GTG #1,2 LEB - GROUND FLOOR FRAMING PLAN | PLAN |  |  | Gas Turbine Generator #1,2 Local Electrical Building |  | Plan for Gas Turbine Generator #1,2 Local Electrical Building |  | FA | 2PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-09-03 | 2008-02-14 | 2024-12-30 | 2025-01-29 | 2025-02-28 | 2025-03-15 | 2025-03-30 | 2025-04-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181253 | GTG #1,2 LEB - ROOF FRAMING PLAN | PLAN |  |  | Gas Turbine Generator #1,2 Local Electrical Building |  | Plan for Gas Turbine Generator #1,2 Local Electrical Building |  | FA | 2PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-09-03 | 2008-02-14 | 2024-12-30 | 2025-01-29 | 2025-02-28 | 2025-03-15 | 2025-03-30 | 2025-04-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181254 | GTG #1,2 LEB - LINE & ROW FRAMING ELEVATION | ELEVATION |  |  | Gas Turbine Generator #1,2 Local Electrical Building |  | Elevation Drawing for Gas Turbine Generator #1,2 Local Electrical Building |  | FA | 2PF1600W74A06P | (HRSG #21 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | 2007-09-15 | 2008-08-01 | 2024-12-26 | 2025-01-25 | 2025-02-24 | 2025-03-11 | 2025-03-26 | 2025-04-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181255 | GTG #1,2 LEB - STAIR FRAMING PLAN & ELEVATION | PLAN & ELEVATION |  |  | Gas Turbine Generator #1,2 Local Electrical Building |  | PLAN & ELEVATION for Gas Turbine Generator #1,2 Local Electrical Building | ST BUILDING | FI | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | 2007-05-31 |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181256 | GTG #1,2 LEB - GROUND FLOOR OPENING PLAN | PLAN |  |  | Gas Turbine Generator #1,2 Local Electrical Building |  | Plan for Gas Turbine Generator #1,2 Local Electrical Building |  | FA | 2PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-09-03 | 2008-02-14 | 2024-12-30 | 2025-01-29 | 2025-02-28 | 2025-03-15 | 2025-03-30 | 2025-04-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181257 | GTG #1,2 LEB - FOUNDATION RE - BAR DETAIL | DETAIL |  |  | Gas Turbine Generator #1,2 Local Electrical Building |  | Detail Drawing for Gas Turbine Generator #1,2 Local Electrical Building |  | FA | 2PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-09-03 | 2008-02-14 | 2024-12-14 | 2025-01-13 | 2025-02-12 | 2025-02-27 | 2025-03-14 | 2025-03-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181258 | GTG #1,2 LEB - COLUMN RE - BAR SCHEDULE | SCHEDULE |  |  | Gas Turbine Generator #1,2 Local Electrical Building |  | Schedule for Gas Turbine Generator #1,2 Local Electrical Building |  | FA | 2PF1600W74A06.1P | (HRSG #22 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > HRSG LEB | 2007-09-15 | 2008-08-01 | 2025-01-11 | 2025-02-10 | 2025-03-12 | 2025-03-27 | 2025-04-11 | 2025-04-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181259 | GTG #1,2 LEB - BEAM & GIRDER RE - BAR SCHEDULE | SCHEDULE |  |  | Gas Turbine Generator #1,2 Local Electrical Building |  | Schedule for Gas Turbine Generator #1,2 Local Electrical Building |  | FA | 2PF1600W74A06P | (HRSG #21 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | 2007-09-15 | 2008-08-01 | 2025-01-11 | 2025-02-10 | 2025-03-12 | 2025-03-27 | 2025-04-11 | 2025-04-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181260 | GTG #1,2 LEB - SLAB & MISC. DETAIL RE - BAR DETAIL | DETAIL |  |  | Gas Turbine Generator #1,2 Local Electrical Building |  | Detail Drawing for Gas Turbine Generator #1,2 Local Electrical Building |  | FA | 2PF1600W74A06.1P | (HRSG #22 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > HRSG LEB | 2007-09-15 | 2008-08-01 | 2024-12-26 | 2025-01-25 | 2025-02-24 | 2025-03-11 | 2025-03-26 | 2025-04-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UBA-181281 | GTG #1,2 LEB - PLUMBING EQUIPMENT SCHEDULE | SCHEDULE |  |  | Gas Turbine Generator #1,2 Local Electrical Building |  | Schedule for Gas Turbine Generator #1,2 Local Electrical Building |  | FA | 2PF1600W74A06P | (HRSG #21 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | 2007-09-15 | 2008-08-01 | 2025-01-11 | 2025-02-10 | 2025-03-12 | 2025-03-27 | 2025-04-11 | 2025-04-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UBA-181282 | GTG #1,2 LEB - PLUMBING SCHEMATIC DIAGRAM | DIAGRAM |  |  | Gas Turbine Generator #1,2 Local Electrical Building |  | Diagram for Gas Turbine Generator #1,2 Local Electrical Building |  | FA | 2PF1600W90A10.1P | (HRSG #22 LEB) P.O & Procurement - I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > HRSG LEB | 2007-09-15 | 2008-08-01 | 2025-02-27 | 2025-03-29 | 2025-04-28 | 2025-05-13 | 2025-05-28 | 2025-06-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UBA-181284 | GTG #1,2 LEB - GROUND FLOOR PLUMBING PLAN | PLAN |  |  | Gas Turbine Generator #1,2 Local Electrical Building |  | Plan for Gas Turbine Generator #1,2 Local Electrical Building |  | FA | 2PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-09-03 | 2008-02-14 | 2024-12-30 | 2025-01-29 | 2025-02-28 | 2025-03-15 | 2025-03-30 | 2025-04-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UBA-181300 | GTG #3,4,5 LEB - CALCULATION | CALCULATION |  |  | Gas Turbine Generator #3,4,5 Local Electrical Building |  | Calculation sheet for Gas Turbine Generator #3,4,5 Local Electrical Building | Electrical Building | FI | 3CF1200W32A05 | (GTG #31 LEB) Structure Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2008-01-25 | 2008-04-26 |  |  |  | 2024-10-27 | 2024-11-26 | 2024-12-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181301 | GTG #3,4,5 LEB - BASEMENT FLOOR PLAN | PLAN |  |  | Gas Turbine Generator #3,4,5 Local Electrical Building |  | Plan for Gas Turbine Generator #3,4,5 Local Electrical Building |  | FA | 3CF1200W16A03 | (GTG #31 LEB) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-11-28 | 2008-01-24 | 2026-01-22 | 2026-02-21 | 2026-03-23 | 2026-04-07 | 2026-04-22 | 2026-05-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181302 | GTG #3,4,5 LEB - GROUND FLOOR PLAN | PLAN |  |  | Gas Turbine Generator #3,4,5 Local Electrical Building |  | Plan for Gas Turbine Generator #3,4,5 Local Electrical Building |  | FA | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | 2025-07-25 | 2025-08-24 | 2025-09-23 | 2025-10-08 | 2025-10-23 | 2025-11-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181303 | GTG #3,4,5 LEB - ROOF PLAN | PLAN |  |  | Gas Turbine Generator #3,4,5 Local Electrical Building |  | Plan for Gas Turbine Generator #3,4,5 Local Electrical Building |  | FA | 3CF1210W20A10 | (GTG Common BLDG) Structure Work(S/S, Cladding, Roof) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | 2008-03-18 | 2008-07-19 | 2026-05-13 | 2026-06-12 | 2026-07-12 | 2026-07-27 | 2026-08-11 | 2026-08-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181304 | GTG #3,4,5 LEB - SIDE WALL ELEVATION | ELEVATION |  |  | Gas Turbine Generator #3,4,5 Local Electrical Building |  | Elevation Drawing for Gas Turbine Generator #3,4,5 Local Electrical Building | ST BUILDING | FI | 3EF1200W32A04 | (GTG #31 LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181305 | GTG #3,4,5 LEB - MAIN SECTION | SECTION |  |  | Gas Turbine Generator #3,4,5 Local Electrical Building |  | SECTION for Gas Turbine Generator #3,4,5 Local Electrical Building | Electrical Building | FI | 3CF1200W32A05 | (GTG #31 LEB) Structure Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2008-01-25 | 2008-04-26 |  |  |  | 2024-10-27 | 2024-11-26 | 2024-12-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181306 | GTG #3,4,5 LEB - INTERIOR FINISH SCHEDULE (INCL. DOOR & WINDOW) | SCHEDULE |  |  | Gas Turbine Generator #3,4,5 Local Electrical Building |  | Schedule for Gas Turbine Generator #3,4,5 Local Electrical Building |  | FA | 3CF1200W24A10 | (GTG #31 LEB) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2008-05-27 | 2008-08-04 | 2025-09-23 | 2025-10-23 | 2025-11-22 | 2025-12-07 | 2025-12-22 | 2026-01-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-181307 | GTG #3,4,5 LEB - STAIR PLAN & SECTION | PLAN & SECTION |  |  | Gas Turbine Generator #3,4,5 Local Electrical Building |  | PLAN & SECTION for Gas Turbine Generator #3,4,5 Local Electrical Building | STEAM TURBINE GENERATOR | FA | 3EF1200W32A04 | (GTG #31 LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181351 | GTG #3,4,5 LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | PLAN |  |  | Gas Turbine Generator #3,4,5 Local Electrical Building |  | Plan for Gas Turbine Generator #3,4,5 Local Electrical Building |  | FA | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | 2025-07-25 | 2025-08-24 | 2025-09-23 | 2025-10-08 | 2025-10-23 | 2025-11-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181352 | GTG #3,4,5 LEB - GROUND FLOOR FRAMING PLAN | PLAN |  |  | Gas Turbine Generator #3,4,5 Local Electrical Building |  | Plan for Gas Turbine Generator #3,4,5 Local Electrical Building |  | FA | 3CF1200W16A03 | (GTG #31 LEB) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-11-28 | 2008-01-24 | 2026-01-22 | 2026-02-21 | 2026-03-23 | 2026-04-07 | 2026-04-22 | 2026-05-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181353 | GTG #3,4,5 LEB - ROOF FRAMING PLAN | PLAN |  |  | Gas Turbine Generator #3,4,5 Local Electrical Building |  | Plan for Gas Turbine Generator #3,4,5 Local Electrical Building |  | FA | 3CF1210W20A10 | (GTG Common BLDG) Structure Work(S/S, Cladding, Roof) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | 2008-03-18 | 2008-07-19 | 2026-05-13 | 2026-06-12 | 2026-07-12 | 2026-07-27 | 2026-08-11 | 2026-08-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181354 | GTG #3,4,5 LEB - LINE & ROW FRAMING ELEVATION | ELEVATION |  |  | Gas Turbine Generator #3,4,5 Local Electrical Building |  | Elevation Drawing for Gas Turbine Generator #3,4,5 Local Electrical Building | ST BUILDING | FI | 3EF1200W32A04 | (GTG #31 LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181355 | GTG #3,4,5 LEB - STAIR FRAMING PLAN & ELEVATION | PLAN & ELEVATION |  |  | Gas Turbine Generator #3,4,5 Local Electrical Building |  | PLAN & ELEVATION for Gas Turbine Generator #3,4,5 Local Electrical Building | ST BUILDING | FI | 3EF1200W32A04 | (GTG #31 LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-181356 | GTG #3,4,5 LEB - GROUND FLOOR OPENING PLAN | PLAN |  |  | Gas Turbine Generator #3,4,5 Local Electrical Building |  | Plan for Gas Turbine Generator #3,4,5 Local Electrical Building |  | FA | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-05-31 |  | 2025-07-25 | 2025-08-24 | 2025-09-23 | 2025-10-08 | 2025-10-23 | 2025-11-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181357 | GTG #3,4,5 LEB - FOUNDATION RE - BAR DETAIL | DETAIL |  |  | Gas Turbine Generator #3,4,5 Local Electrical Building |  | Detail Drawing for Gas Turbine Generator #3,4,5 Local Electrical Building |  | FA | 3PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | 2007-09-03 | 2008-03-17 | 2024-12-14 | 2025-01-13 | 2025-02-12 | 2025-02-27 | 2025-03-14 | 2025-03-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181358 | GTG #3,4,5 LEB - COLUMN RE - BAR SCHEDULE | SCHEDULE | Gas Turbine Generator |  | Local Electrical Building |  | Schedule for GTG |  | FA | 3EF1200W32A04 | (GTG #31 LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2007-08-01 | 2007-11-27 |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181359 | GTG #3,4,5 LEB - BEAM & GIRDER RE - BAR SCHEDULE | SCHEDULE | Gas Turbine Generator |  | Local Electrical Building |  | Schedule for GTG |  | FA | 3CF1200W32A05 | (GTG #31 LEB) Structure Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | 2008-01-25 | 2008-04-26 |  |  |  | 2024-10-27 | 2024-11-26 | 2024-12-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-181360 | GTG #3,4,5 LEB - SLAB & MISC. DETAIL RE - BAR DETAIL | DETAIL | Gas Turbine Generator |  | Local Electrical Building |  | Detail Drawing for GTG |  | FI | 3PF1213W42A03.1P | (GT #32) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Main body | 2007-04-30 | 2008-04-29 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UBA-181381 | GTG#3,4,5LEB - PLUMBING EQUIPMENT SCHEDULE | SCHEDULE | Gas Turbine Generator |  | Local Electrical Building |  | Schedule for GTG |  | FA | 3CF1265W38A07 | (F/F GTG#31) Piping work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fire fighting System | 2008-07-14 | 2008-08-06 |  |  |  | 2025-04-16 | 2025-05-16 | 2025-06-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UBA-181382 | GTG#3,4,5LEB - PLUMBING SCHEMATIC DIAGRAM | DIAGRAM | Gas Turbine Generator |  | Local Electrical Building |  | Diagram for GTG |  | FA | 3PF1213W42A03P | (GT #31) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | 2007-04-30 | 2008-03-31 | 2024-08-26 | 2024-09-25 | 2024-10-25 | 2024-11-09 | 2024-11-24 | 2024-12-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UBA-181384 | GTG#3,4,5LEB - GROUND FLOOR PLUMBING PLAN | PLAN | Gas Turbine Generator |  | Local Electrical Building |  | Plan for GTG |  | FA | 3EF1210W16A07 | (GTG Common BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | 2007-03-01 | 2007-08-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0BAT-181800 | ROOF FOR STG TR - CALCULATION | CALCULATION |  |  |  |  | Calculation sheet |  | FA | 1PF6500W70A07P | (STG #10 & UST Shelter) P.O & Procurement - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-06-29 | 2008-06-22 | 2024-11-16 | 2024-12-16 | 2025-01-15 | 2025-01-30 | 2025-02-14 | 2025-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P6BAT-181811 | ROOF FOR STG TR - PLAN, SECTION, ELEVATION | PLAN, SECTION, ELEVATION |  |  |  |  | PLAN, SECTION, ELEVATION |  | FA | 1CF2010W20A08 | (STG #10 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2008-08-05 | 2008-11-06 |  |  |  | 2025-05-08 | 2025-06-07 | 2025-07-07 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P6BAT-181812 | ROOF FOR STG TR - COLUMN ARRAGEMENT, ROOF FRAMING PLAN, BASEPLATE DETAILS | [7 empty] | FI | 1CF2010W20A08 | (STG #10 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2008-08-05 | 2008-11-06 |  |  |  | 2025-05-08 | 2025-06-07 | 2025-07-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P6BAT-181813 | ROOF FOR STG TR - ROOF FRAMING ELEVATION, CONNECTION DETAILS | [7 empty] | FI | 1CF2010W20A08 | (STG #10 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2008-08-05 | 2008-11-06 |  |  |  | 2025-05-08 | 2025-06-07 | 2025-07-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UGD-181900 | WATER TREATMENT BUILDING - CALCULATION | CALCULATION |  |  | WATER TREATMENT BUILDING |  | Calculation sheet for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0CF5534W24A10 | (DWP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2008-07-01 | 2008-09-18 |  |  |  | 2025-04-03 | 2025-05-03 | 2025-06-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181901 | WATER TREATMENT BUILDING - GROUND FLOOR PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 |  |  |  | 2025-01-31 | 2025-03-02 | 2025-04-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181902 | WATER TREATMENT BUILDING - 1ST FLOOR PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0CF5534W24A10 | (DWP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2008-07-01 | 2008-09-18 |  |  |  | 2025-09-30 | 2025-10-30 | 2025-11-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181903 | WATER TREATMENT BUILDING - ROOF FLOOR PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0CF5534W24A10 | (DWP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2008-07-01 | 2008-09-18 |  |  |  | 2025-09-30 | 2025-10-30 | 2025-11-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181904 | WATER TREATMENT BUILDING - ELEVATION | ELEVATION |  |  | WATER TREATMENT BUILDING |  | Elevation Drawing for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 |  |  |  |  | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181905 | WATER TREATMENT BUILDING - SECTION | SECTION |  |  | WATER TREATMENT BUILDING |  | SECTION for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 |  |  |  | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181906 | WATER TREATMENT BUILDING - INTERIOR FINISH & DOOR SCHEDULE | SCHEDULE |  |  | WATER TREATMENT BUILDING |  | Schedule for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0CF5534W24A10 | (DWP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2008-07-01 | 2008-09-18 |  |  |  | 2025-04-03 | 2025-05-03 | 2025-06-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181908 | WATER TREATMENT BUILDING - WALL SECTION DETAIL | DETAIL |  |  | WATER TREATMENT BUILDING |  | Detail Drawing for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 |  |  |  | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181909 | WATER TREATMENT BUILDING - TOILET ENLARGED PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 |  |  |  | 2025-01-31 | 2025-03-02 | 2025-04-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181910 | WATER TREATMENT BUILDING - WALL OPENING PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0CF5534W24A10 | (DWP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2008-07-01 | 2008-09-18 |  |  |  | 2025-09-30 | 2025-10-30 | 2025-11-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181911 | WATER TREATMENT BUILDING - CEILING PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 |  |  |  | 2025-01-31 | 2025-03-02 | 2025-04-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181912 | WATER TREATMENT BUILDING - STAIR ENLARGED PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0EF5535W32A17 | (STS BLDG) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 | 2008-01-31 |  |  |  | 2025-01-31 | 2025-03-02 | 2025-04-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181913 | WATER TREATMENT BUILDING - STAIR ENLARGED SECTION | SECTION |  |  | WATER TREATMENT BUILDING |  | SECTION for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0EF5535W32A17 | (STS BLDG) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 | 2008-01-31 |  |  |  | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-181914 | WATER TREATMENT BUILDING - ARCHITECTURAL MISC. |  |  |  | WATER TREATMENT BUILDING |  | for WATER TREATMENT BUILDING |  | FA | 0CF5534W24A10 | (DWP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2008-07-01 | 2008-09-18 | 2026-12-24 | 2027-01-23 | 2027-02-22 | 2027-03-09 | 2027-03-24 | 2027-04-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UGD-181951 | WATER TREATMENT BUILDING - FOUNDATION & COLUMN ARRANGEMENT PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  |  |  |  | 2024-11-29 | 2024-12-29 | 2025-01-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UGD-181952 | WATER TREATMENT BUILDING - GROUND FLOOR FRAMING |  |  |  | WATER TREATMENT BUILDING |  | for WATER TREATMENT BUILDING |  | FA | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | 2026-02-22 | 2026-03-24 | 2026-04-23 | 2026-05-08 | 2026-05-23 | 2026-06-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UGD-181953 | WATER TREATMENT BUILDING - 1ST FLOOR FRAMING PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0CF5534W24A10 | (DWP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2008-07-01 | 2008-09-18 |  |  |  | 2025-09-30 | 2025-10-30 | 2025-11-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UGD-181954 | WATER TREATMENT BUILDING - ROOF FLOOR FRAMING PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0CF5534W24A10 | (DWP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2008-07-01 | 2008-09-18 |  |  |  | 2025-09-30 | 2025-10-30 | 2025-11-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UGD-181955 | WATER TREATMENT BUILDING - FRAMING ELEVATION | ELEVATION |  |  | WATER TREATMENT BUILDING |  | Elevation Drawing for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UGD-181956 | WATER TREATMENT BUILDING - STAIR FRAMING PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0EF5535W32A17 | (STS BLDG) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 | 2008-01-31 |  |  |  | 2025-01-31 | 2025-03-02 | 2025-04-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UGD-181957 | WATER TREATMENT BUILDING - STAIR FRAMING SECTION | SECTION |  |  | WATER TREATMENT BUILDING |  | SECTION for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0EF5535W32A17 | (STS BLDG) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 | 2008-01-31 |  |  |  | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UGD-181958 | WATER TREATMENT BUILDING - FOUNDATION REBAR DETAIL | DETAIL |  |  | WATER TREATMENT BUILDING |  | Detail Drawing for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UGD-181959 | WATER TREATMENT BUILDING - COLUMN REBAR DETAIL | DETAIL |  |  | WATER TREATMENT BUILDING |  | Detail Drawing for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0EF5534W32A04 | (DWP BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UGD-181960 | WATER TREATMENT BUILDING - GIRDER & BEAM REBAR SCHEDULE | SCHEDULE |  |  | WATER TREATMENT BUILDING |  | Schedule for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0CF5534W24A10 | (DWP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2008-07-01 | 2008-09-18 |  |  |  | 2025-04-03 | 2025-05-03 | 2025-06-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UGD-181961 | WATER TREATMENT BUILDING - SLAB REBAR DETAIL | DETAIL |  |  | WATER TREATMENT BUILDING |  | Detail Drawing for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 |  |  |  | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UGD-181962 | WATER TREATMENT BUILDING - EQUIPMENT FOUNDTAION ARRANGEMENT PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0EF5534W00A01 | (DWP BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 |  |  |  |  | 2024-11-29 | 2024-12-29 | 2025-01-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UGD-181963 | WATER TREATMENT BUILDING - EMBEDDED PLATE & SLEEVE PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 |  |  |  | 2025-01-31 | 2025-03-02 | 2025-04-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UGD-181964 | WATER TREATMENT BUILDING - MISC. REBAR DETAIL | DETAIL |  |  | WATER TREATMENT BUILDING |  | Detail Drawing for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 |  |  |  | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UGD-181965 | WATER TREATMENT BUILDING - ROOF COLUMN LOCATION PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0CF5534W24A10 | (DWP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2008-07-01 | 2008-09-18 |  |  |  | 2025-09-30 | 2025-10-30 | 2025-11-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UGD-181966 | WATER TREATMENT BUILDING - ENLARGED ROOF FRAMING PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0EF5534W32A04 | (DWP BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 |  |  |  | 2024-11-29 | 2024-12-29 | 2025-01-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UGD-181967 | WATER TREATMENT BUILDING - GIRT LINE & ROW ELEVATION | ELEVATION |  |  | WATER TREATMENT BUILDING |  | Elevation Drawing for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 |  |  |  |  | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UGD-181968 | WATER TREATMENT BUILDING - STEEL CONNECTION DETAIL | DETAIL |  |  | WATER TREATMENT BUILDING |  | Detail Drawing for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 |  |  |  | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UGD-181981 | WATER TREATMENT BUILDING - PLUMBING EQUIPMENT SCHEDULE | SCHEDULE |  |  | WATER TREATMENT BUILDING |  | Schedule for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0EF5535W32A17 | (STS BLDG) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 | 2008-01-31 |  |  |  | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UGD-181982 | WATER TREATMENT BUILDING - PLUMBING SCHEMATIC DIAGRAM | SCHEMATIC DIAGRAM |  |  | WATER TREATMENT BUILDING |  | SCHEMATIC DIAGRAM for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UGD-181983 | WATER TREATMENT BUILDING - GROUND FLOOR PLUMBING PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 |  |  |  |  | 2025-01-31 | 2025-03-02 | 2025-04-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UGD-181984 | WATER TREATMENT BUILDING - 1ST FLOOR PLUMBING PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0CF5534W24A10 | (DWP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2008-07-01 | 2008-09-18 |  |  |  | 2025-09-30 | 2025-10-30 | 2025-11-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UGD-181985 | WATER TREATMENT BUILDING - ROOF PLUMBING PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0CF5534W24A10 | (DWP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2008-07-01 | 2008-09-18 |  |  |  | 2025-09-30 | 2025-10-30 | 2025-11-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UGD-181986 | WATER TREATMENT BUILDING - ENLARGED PLUMBING PLAN | PLAN |  |  | WATER TREATMENT BUILDING |  | Plan for WATER TREATMENT BUILDING | WATER TREATMENT BUILDING | FI | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 |  |  |  |  | 2025-01-31 | 2025-03-02 | 2025-04-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UST-182000 | WORKSHOP & STORAGE BUILDING - CALCULATION | CALCULATION |  |  | WORKSHOP & STORAGE BUILDING |  | Calculation sheet for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  |  | 2025-10-01 | 2025-10-31 | 2025-11-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UST-182001 | WORKSHOP & STORAGE BUILDING - GROUND FLOOR PLAN | PLAN |  |  | WORKSHOP & STORAGE BUILDING |  | Plan for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 0CF5560W24A20 | (M&E WORKSHOP LEB) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-10-06 | 2008-12-01 |  |  |  | 2025-07-09 | 2025-08-08 | 2025-09-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UST-182002 | WORKSHOP & STORAGE BUILDING - ROOF PLAN | PLAN |  |  | WORKSHOP & STORAGE BUILDING |  | Plan for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 1CF2010W20A08 | (STG #10 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2008-08-05 | 2008-11-06 |  |  |  | 2025-05-08 | 2025-06-07 | 2025-07-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UST-182003 | WORKSHOP & STORAGE BUILDING - ELEVATION | ELEVATION |  |  | WORKSHOP & STORAGE BUILDING |  | Elevation Drawing for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  |  | 2025-10-01 | 2025-10-31 | 2025-11-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UST-182004 | WORKSHOP & STORAGE BUILDING - SECTION | SECTION |  |  | WORKSHOP & STORAGE BUILDING |  | SECTION for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  |  | 2025-10-01 | 2025-10-31 | 2025-11-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UST-182005 | WORKSHOP & STORAGE BUILDING - INTERIOR FINISH, DOOR & WINDOW SCHEDULE | SCHEDULE |  |  | WORKSHOP & STORAGE BUILDING |  | Schedule for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 0CF5560W24A20 | (M&E WORKSHOP LEB) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-10-06 | 2008-12-01 |  |  |  | 2025-07-09 | 2025-08-08 | 2025-09-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UST-182006 | WORKSHOP & STORAGE BUILDING - ENLARGED PLAN, CEILING PLAN | PLAN |  |  | WORKSHOP & STORAGE BUILDING |  | Plan for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 0CF5560W24A20 | (M&E WORKSHOP LEB) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-10-06 | 2008-12-01 |  |  |  | 2025-07-09 | 2025-08-08 | 2025-09-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UST-182051 | WORKSHOP & STORAGE BUILDING - FOUNDATION PLAN | PLAN |  |  | WORKSHOP & STORAGE BUILDING |  | Plan for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 0CF5560W16A03 | (M&E WORKSHOP BLDG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-04-10 | 2008-06-06 |  |  |  | 2025-01-11 | 2025-02-10 | 2025-03-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UST-182052 | WORKSHOP & STORAGE BUILDING - COLUMN LOCATION PLAN | PLAN |  |  | WORKSHOP & STORAGE BUILDING |  | Plan for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  |  | 2025-10-01 | 2025-10-31 | 2025-11-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UST-182053 | WORKSHOP & STORAGE BUILDING - GROUND FLOOR FRAMING PLAN | PLAN |  |  | WORKSHOP & STORAGE BUILDING |  | Plan for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  |  | 2025-10-01 | 2025-10-31 | 2025-11-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UST-182054 | WORKSHOP & STORAGE BUILDING - ROOF FRAMING PLAN | PLAN |  |  | WORKSHOP & STORAGE BUILDING |  | Plan for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 2CF2010W20A08 | (STG #20 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2008-08-05 | 2008-11-06 |  |  |  | 2025-05-08 | 2025-06-07 | 2025-07-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UST-182055 | WORKSHOP & STORAGE BUILDING - STEEL ROOF FRAMING PLAN | PLAN |  |  | WORKSHOP & STORAGE BUILDING |  | Plan for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 2CF2010W20A08 | (STG #20 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2008-08-05 | 2008-11-06 |  |  |  | 2025-05-08 | 2025-06-07 | 2025-07-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UST-182056 | WORKSHOP & STORAGE BUILDING - FRAMING ELEVATION |  |  |  | WORKSHOP & STORAGE BUILDING |  | for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  |  | 2025-10-01 | 2025-10-31 | 2025-11-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UST-182058 | WORKSHOP & STORAGE BUILDING - FOUNDATION DETAIL |  |  |  | WORKSHOP & STORAGE BUILDING |  | for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 0CF5560W16A03 | (M&E WORKSHOP BLDG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-04-10 | 2008-06-06 |  |  |  | 2025-01-11 | 2025-02-10 | 2025-03-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UST-182059 | WORKSHOP & STORAGE BUILDING - RC COLUMN DETAIL |  |  |  | WORKSHOP & STORAGE BUILDING |  | for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  |  | 2025-10-01 | 2025-10-31 | 2025-11-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UST-182060 | WORKSHOP & STORAGE BUILDING - SLAB DETAIL |  |  |  | WORKSHOP & STORAGE BUILDING |  | for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  |  | 2025-10-01 | 2025-10-31 | 2025-11-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UST-182061 | WORKSHOP & STORAGE BUILDING - CRANE GIRDER & MISC. DETAIL |  |  |  | WORKSHOP & STORAGE BUILDING |  | for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 0CF5544W42A11 | (Crane & Hoist) Crane Erection for GIS Building | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Crane & Hoist | 2008-02-15 | 2008-04-01 |  |  |  | 2024-11-17 | 2024-12-17 | 2025-01-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UST-182062 | WORKSHOP & STORAGE BUILDING - STEEL COLUMN & BASE PLATE DETAIL |  |  |  | WORKSHOP & STORAGE BUILDING |  | for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 0EF5560W32A04 | (M&E WORKSHOP BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-11-29 | 2008-04-09 |  |  |  | 2024-08-31 | 2024-09-30 | 2024-10-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UST-182063 | WORKSHOP & STORAGE BUILDING - CONNECTION DETAIL |  |  |  | WORKSHOP & STORAGE BUILDING |  | for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  |  | 2025-10-01 | 2025-10-31 | 2025-11-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UST-182081 | WORKSHOP & STORAGE BUILDING - PLUMBING EQUIPMENT SCHEDULE | SCHEDULE |  |  | WORKSHOP & STORAGE BUILDING |  | Schedule for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 0CF5560W24A20 | (M&E WORKSHOP LEB) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-10-06 | 2008-12-01 |  |  |  | 2025-07-09 | 2025-08-08 | 2025-09-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UST-182082 | WORKSHOP & STORAGE BUILDING - PLUMBING SCHEMATIC DIAGRAM | DIAGRAM |  |  | WORKSHOP & STORAGE BUILDING |  | Diagram for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 0CF5560W24A20 | (M&E WORKSHOP LEB) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-10-06 | 2008-12-01 |  |  |  | 2025-07-09 | 2025-08-08 | 2025-09-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UST-182083 | WORKSHOP & STORAGE BUILDING - GROUND FLOOR PLUMBING PLAN | PLAN |  |  | WORKSHOP & STORAGE BUILDING |  | Plan for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  |  | 2025-10-01 | 2025-10-31 | 2025-11-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UST-182084 | WORKSHOP & STORAGE BUILDING - ROOF PLUMBING PLAN | PLAN |  |  | WORKSHOP & STORAGE BUILDING |  | Plan for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  |  | 2025-10-01 | 2025-10-31 | 2025-11-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UST-182085 | WORKSHOP & STORAGE BUILDING - ENLARGED PLUMBING PLAN | PLAN |  |  | WORKSHOP & STORAGE BUILDING |  | Plan for WORKSHOP & STORAGE BUILDING | WORKSHOP & STORAGE BUILDING | FI | 0CF5560W24A10 | (M&E WORKSHOP BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2008-12-29 | 2009-02-24 |  |  |  | 2025-10-01 | 2025-10-31 | 2025-11-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0ULA-182151 | DEAERATOR SUPPORT STRUCTURE - PILE & FOUNDATION PLAN | PLAN |  |  |  |  | Plan |  | FA | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULA-182152 | DEAERATOR SUPPORT STRUCTURE - COLUMN LOCATION PLAN | PLAN |  |  |  |  | Plan |  | FA | 3CF1610W20A05.1 | (HRSG #32 S/Structure & Casing) S/Structure Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Steel Structure & Casing | 2008-05-19 | 2008-07-18 |  |  |  | 2025-02-19 | 2025-03-21 | 2025-04-20 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULA-182153 | DEAERATOR SUPPORT STRUCTURE - GROUND FLOOR FRAMING PLAN | PLAN |  |  |  |  | Plan |  | FA | 1CF1230W20A04 | (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air Intake System | 2008-03-18 | 2008-04-18 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULA-182154 | DEAERATOR SUPPORT STRUCTURE - DEAERATOR FLOOR FRAMING PLAN | PLAN |  |  |  |  | Plan |  | FA | 3EF1610W20A01 | (HRSG #31 S/Structure & Casing) Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Steel Structure & Casing | 2007-06-19 | 2008-01-15 |  |  |  | 2024-03-21 | 2024-04-20 | 2024-05-20 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULA-182155 | DEAERATOR SUPPORT STRUCTURE - FRAMING ELEVATION | [7 empty] | FI | 3CF1610W20A05.1 | (HRSG #32 S/Structure & Casing) S/Structure Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Steel Structure & Casing | 2008-05-19 | 2008-07-18 |  |  |  | 2025-02-19 | 2025-03-21 | 2025-04-20 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULA-182157 | DEAERATOR SUPPORT STRUCTURE - FOUNDATION DETAIL | [7 empty] | FI | 3EF1610W20A01 | (HRSG #31 S/Structure & Casing) Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Steel Structure & Casing | 2007-06-19 | 2008-01-15 |  |  |  | 2024-03-21 | 2024-04-20 | 2024-05-20 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULA-182160 | DEAERATOR SUPPORT STRUCTURE - BASE PLATE DETAIL | [7 empty] | FI | 3EF1610W20A01 | (HRSG #31 S/Structure & Casing) Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Steel Structure & Casing | 2007-06-19 | 2008-01-15 |  |  |  | 2024-03-21 | 2024-04-20 | 2024-05-20 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0ULA-182190 | DEAERATOR SUPPORT STRUCTURE - PILE & FOUNDATION CALCULATION | CALCULATION |  |  |  |  | Calculation sheet |  | FA | 0EF2000W14A14 | STG Area Pile Design | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Piling & Soil Improvement | 2007-03-30 | 2007-07-02 | 2024-08-17 | 2024-09-16 | 2024-10-16 | 2024-10-31 | 2024-11-15 | 2024-11-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0ULA-182191 | DEAERATOR SUPPORT STRUCTURE - SUPERSTRUCTURE CALCULATION | CALCULATION |  |  |  |  | Calculation sheet |  | FA | 3PF1610W20A03P | (HRSG #31 S/Structure & Casing) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Steel Structure & Casing | 2007-06-14 | 2008-04-02 | 2024-11-01 | 2024-12-01 | 2024-12-31 | 2025-01-15 | 2025-01-30 | 2025-02-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0USG-182700 | FIRE WATER PUMP HOUSE - CALCULATION | CALCULATION |  |  | FIRE WATER PUMP HOUSE |  | Calculation sheet for FIRE WATER PUMP HOUSE | Fire Water Pump House | FI | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0USG-182701 | FIRE WATER PUMP HOUSE - GROUND FLOOR PLAN, INTERIOR FINISH SCHEDULE | PLAN, SCHEDULE |  |  | FIRE WATER PUMP HOUSE |  | PLAN, SCHEDULE for FIRE WATER PUMP HOUSE | Fire Water Pump House | FI | 0CF4500W24A11 | (Fire WTR Pump Shelter) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2008-05-20 | 2008-07-16 |  |  |  | 2025-02-20 | 2025-03-22 | 2025-04-21 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0USG-182702 | FIRE WATER PUMP HOUSE - ROOF PLAN | PLAN |  |  | FIRE WATER PUMP HOUSE |  | Plan for FIRE WATER PUMP HOUSE | Fire Water Pump House | FI | 0EF4500W32A04 | (Fire WTR Pump Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 | 2007-08-27 |  |  |  | 2024-03-01 | 2024-03-02 | 2024-04-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0USG-182703 | FIRE WATER PUMP HOUSE - ELEVATION | ELEVATION |  |  | FIRE WATER PUMP HOUSE |  | Elevation Drawing for FIRE WATER PUMP HOUSE | Fire Water Pump House | FI | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0USG-182704 | FIRE WATER PUMP HOUSE - MAIN SECTION | SECTION |  |  | FIRE WATER PUMP HOUSE |  | SECTION for FIRE WATER PUMP HOUSE | Fire Water Pump House | FI | 0EF4500W32A04 | (Fire WTR Pump Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-01 | 2007-08-27 |  |  |  | 2024-03-01 | 2024-03-02 | 2024-04-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0USG-182751 | FIRE WATER PUMP HOUSE - FOUNDATION, COLUMN ARRAGEMENT PLAN | PLAN |  |  | FIRE WATER PUMP HOUSE |  | Plan for FIRE WATER PUMP HOUSE | Fire Water Pump House | FI | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0USG-182752 | FIRE WATER PUMP HOUSE - GROUND FLOOR FRAMING PLAN, ROOF FRAMING PLAN | PLAN |  |  | FIRE WATER PUMP HOUSE |  | Plan for FIRE WATER PUMP HOUSE | Fire Water Pump House | FI | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0USG-182753 | FIRE WATER PUMP HOUSE - FRAMING ELEVATION | ELEVATION |  |  | FIRE WATER PUMP HOUSE |  | Elevation Drawing for FIRE WATER PUMP HOUSE | Fire Water Pump House | FI | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0USG-182754 | FIRE WATER PUMP HOUSE - FOUNDATION REBAR SCHEDULE, SLAB REBAR DETAIL | SCHEDULE, DETAIL |  |  | FIRE WATER PUMP HOUSE |  | SCHEDULE, DETAIL for FIRE WATER PUMP HOUSE | Fire Water Pump House | FI | 0CF4500W16A03 | (Fire WTR Pump Shelter) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-08-31 | 2007-10-27 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0USG-182755 | FIRE WATER PUMP HOUSE - COLUMN, GIRDER, BEAM SHEDULE | SHEDULE |  |  | FIRE WATER PUMP HOUSE |  | SHEDULE for FIRE WATER PUMP HOUSE | Fire Water Pump House | FI | 0EF4500W16A02 | (Fire WTR Pump Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Pump & Shelter | 2007-05-31 | 2007-08-30 |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UTF-182800 | AIR COMPRESSOR SHELTER - CALCULATION SHEET | CALCULATION SHEET |  |  | AIR COMPRESSOR SHELTER |  | CALCULATION SHEET for AIR COMPRESSOR SHELTER | AIR COMPRESSOR | FI | 0EF3510W32A04 | (COMP Air Receiver TK Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-09-13 |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UTF-182801 | AIR COMPRESSOR SHELTER - GROUND FLOOR PLAN | PLAN |  |  | AIR COMPRESSOR SHELTER |  | Plan for AIR COMPRESSOR SHELTER | AIR COMPRESSOR | FI | 0EF3510W16A02 | (COMP Air Receiver TK Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-11-12 |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UTF-182802 | AIR COMPRESSOR SHELTER - ROOF PLAN | PLAN |  |  | AIR COMPRESSOR SHELTER |  | Plan for AIR COMPRESSOR SHELTER | AIR COMPRESSOR | FI | 0EF3510W32A04 | (COMP Air Receiver TK Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-09-13 |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UTF-182803 | AIR COMPRESSOR SHELTER - SIDE ELEVATION | ELEVATION |  |  | AIR COMPRESSOR SHELTER |  | Elevation Drawing for AIR COMPRESSOR SHELTER | AIR COMPRESSOR | FI | 0EF3510W16A02 | (COMP Air Receiver TK Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-11-12 |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UTF-182804 | AIR COMPRESSOR SHELTER - MAIN SECTION | SECTION |  |  | AIR COMPRESSOR SHELTER |  | SECTION for AIR COMPRESSOR SHELTER | AIR COMPRESSOR | FI | 0EF3510W32A04 | (COMP Air Receiver TK Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-09-13 |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UTF-182851 | AIR COMPRESSOR SHELTER - FOUNDATION ARRANGEMENT PLAN | PLAN |  |  | AIR COMPRESSOR SHELTER |  | Plan for AIR COMPRESSOR SHELTER | AIR COMPRESSOR | FI | 0CF3510W16A03 | (COMP Air Receiver TK Shelter) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-11-13 | 2008-01-09 |  |  |  | 2024-08-15 | 2024-09-14 | 2024-10-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UTF-182852 | AIR COMPRESSOR SHELTER - COLUMN ARRANGEMENT PLAN | PLAN |  |  | AIR COMPRESSOR SHELTER |  | Plan for AIR COMPRESSOR SHELTER | AIR COMPRESSOR | FI | 0EF3510W00A01 | (COMP Air Receiver TK Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 |  |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UTF-182853 | AIR COMPRESSOR SHELTER - GROUND FLOOR FRAMING PLAN | PLAN |  |  | AIR COMPRESSOR SHELTER |  | Plan for AIR COMPRESSOR SHELTER | AIR COMPRESSOR | FI | 0EF3510W16A02 | (COMP Air Receiver TK Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-11-12 |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UTF-182854 | AIR COMPRESSOR SHELTER - ROOF FRAMING PLAN | PLAN |  |  | AIR COMPRESSOR SHELTER |  | Plan for AIR COMPRESSOR SHELTER | AIR COMPRESSOR | FI | 0EF3510W32A04 | (COMP Air Receiver TK Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-09-13 |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UTF-182855 | AIR COMPRESSOR SHELTER - LINE FRAMING ELEVATION | ELEVATION |  |  | AIR COMPRESSOR SHELTER |  | Elevation Drawing for AIR COMPRESSOR SHELTER | AIR COMPRESSOR | FI | 0EF3510W16A02 | (COMP Air Receiver TK Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-11-12 |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UTF-182856 | AIR COMPRESSOR SHELTER - ROW FRAMING ELEVATION | ELEVATION |  |  | AIR COMPRESSOR SHELTER |  | Elevation Drawing for AIR COMPRESSOR SHELTER | AIR COMPRESSOR | FI | 0EF3510W16A02 | (COMP Air Receiver TK Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-11-12 |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UTF-182857 | AIR COMPRESSOR SHELTER - REBAR DETAIL | REBAR DETAIL |  |  | AIR COMPRESSOR SHELTER |  | REBAR DETAIL for AIR COMPRESSOR SHELTER | AIR COMPRESSOR | FI | 0EF3510W32A04 | (COMP Air Receiver TK Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System > Receiver Tank | 2007-08-01 | 2007-09-13 |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UYC-182900 | ADMINISTRATION & SOCIAL BUILDING - CALCULATION SHEET | CALCULATION SHEET |  |  | ADMINISTRATION & SOCIAL BUILDING |  | CALCULATION SHEET for ADMINISTRATION & SOCIAL BUILDING | ADMINISTRATION & SOCIAL BUILDING | FI | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYC-182901 | ADMINISTRATION & SOCIAL BUILDING - GROUND FLOOR PLAN | PLAN |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Plan for ADMINISTRATION & SOCIAL BUILDING |  | FA | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | 2025-08-22 | 2025-09-21 | 2025-10-21 | 2025-11-05 | 2025-11-20 | 2025-12-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYC-182902 | ADMINISTRATION & SOCIAL BUILDING - ROOF PLAN | PLAN |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Plan for ADMINISTRATION & SOCIAL BUILDING |  | FA | 0EF5566W32A04 | (ADMIN BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | 2025-08-22 | 2025-09-21 | 2025-10-21 | 2025-11-05 | 2025-11-20 | 2025-12-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYC-182903 | ADMINISTRATION & SOCIAL BUILDING - SIDE ELEVATION | ELEVATION |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Elevation Drawing for ADMINISTRATION & SOCIAL BUILDING |  | FA | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | 2025-08-22 | 2025-09-21 | 2025-10-21 | 2025-11-05 | 2025-11-20 | 2025-12-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYC-182904 | ADMINISTRATION & SOCIAL BUILDING - MAIN SECTION | SECTION |  |  | ADMINISTRATION & SOCIAL BUILDING |  | SECTION for ADMINISTRATION & SOCIAL BUILDING |  | FA | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | 2025-08-22 | 2025-09-21 | 2025-10-21 | 2025-11-05 | 2025-11-20 | 2025-12-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYC-182905 | ADMINISTRATION & SOCIAL BUILDING - INTERIOR FINISH & DOOR / WINDOW SCHEDULE | SCHEDULE |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Schedule for ADMINISTRATION & SOCIAL BUILDING |  | FA | 0CF5566W24A10 | (ADMIN BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-04-30 | 2008-07-29 | 2026-09-23 | 2026-10-23 | 2026-11-22 | 2026-12-07 | 2026-12-22 | 2027-01-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYC-182906 | ADMINISTRATION & SOCIAL BUILDING - WALL SECTION | SECTION |  |  | ADMINISTRATION & SOCIAL BUILDING |  | SECTION for ADMINISTRATION & SOCIAL BUILDING |  | FA | 0CF5566W32A05 | (ADMIN BLDG) Structure Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-11-29 | 2008-03-31 | 2026-04-23 | 2026-05-23 | 2026-06-22 | 2026-07-07 | 2026-07-22 | 2026-08-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYC-182907 | ADMINISTRATION & SOCIAL BUILDING - ENLARGED REST ROOM PLAN & ELEVATION | PLAN & ELEVATION |  |  | ADMINISTRATION & SOCIAL BUILDING |  | PLAN & ELEVATION for ADMINISTRATION & SOCIAL BUILDING |  | FA | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | 2025-08-22 | 2025-09-21 | 2025-10-21 | 2025-11-05 | 2025-11-20 | 2025-12-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYC-182908 | ADMINISTRATION & SOCIAL BUILDING - CEILING PLAN | PLAN |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Plan for ADMINISTRATION & SOCIAL BUILDING |  | FA | 0EF5566W32A04 | (ADMIN BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | 2025-08-22 | 2025-09-21 | 2025-10-21 | 2025-11-05 | 2025-11-20 | 2025-12-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYC-182951 | ADMINISTRATION & SOCIAL BUILDING - FOUNDATION & COLUMN ARRANGEMENT PLAN | PLAN |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Plan for ADMINISTRATION & SOCIAL BUILDING |  | FA | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | 2025-08-22 | 2025-09-21 | 2025-10-21 | 2025-11-05 | 2025-11-20 | 2025-12-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYC-182952 | ADMINISTRATION & SOCIAL BUILDING - GROUND FLOOR FRAMING PLAN | PLAN |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Plan for ADMINISTRATION & SOCIAL BUILDING |  | FA | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | 2025-08-22 | 2025-09-21 | 2025-10-21 | 2025-11-05 | 2025-11-20 | 2025-12-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYC-182953 | ADMINISTRATION & SOCIAL BUILDING - ROOF FRAMING PLAN | PLAN |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Plan for ADMINISTRATION & SOCIAL BUILDING |  | FA | 0EF5566W32A04 | (ADMIN BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | 2025-08-22 | 2025-09-21 | 2025-10-21 | 2025-11-05 | 2025-11-20 | 2025-12-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYC-182954 | ADMINISTRATION & SOCIAL BUILDING - LINE FRAMING ELEVATION | ELEVATION |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Elevation Drawing for ADMINISTRATION & SOCIAL BUILDING |  | FA | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | 2025-08-22 | 2025-09-21 | 2025-10-21 | 2025-11-05 | 2025-11-20 | 2025-12-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYC-182955 | ADMINISTRATION & SOCIAL BUILDING - ROW FRAMING ELEVATION | ELEVATION |  |  | ADMINISTRATION & SOCIAL BUILDING |  | Elevation Drawing for ADMINISTRATION & SOCIAL BUILDING |  | FA | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | 2025-08-22 | 2025-09-21 | 2025-10-21 | 2025-11-05 | 2025-11-20 | 2025-12-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYC-182956 | ADMINISTRATION & SOCIAL BUILDING - FOUNDATION & COLUMN REBAR DETAIL | REBAR DETAIL |  |  | ADMINISTRATION & SOCIAL BUILDING |  | REBAR DETAIL for ADMINISTRATION & SOCIAL BUILDING |  | FA | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | 2025-08-22 | 2025-09-21 | 2025-10-21 | 2025-11-05 | 2025-11-20 | 2025-12-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYC-182957 | ADMINISTRATION & SOCIAL BUILDING - BEAM & GIRDER REBAR DETAIL | REBAR DETAIL |  |  | ADMINISTRATION & SOCIAL BUILDING |  | REBAR DETAIL for ADMINISTRATION & SOCIAL BUILDING |  | FA | 0EF5566W32A04 | (ADMIN BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | 2025-08-22 | 2025-09-21 | 2025-10-21 | 2025-11-05 | 2025-11-20 | 2025-12-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYC-182958 | ADMINISTRATION & SOCIAL BUILDING - SLAB & MISC REBAR DETAIL | REBAR DETAIL |  |  | ADMINISTRATION & SOCIAL BUILDING |  | REBAR DETAIL for ADMINISTRATION & SOCIAL BUILDING |  | FA | 0EF5566W32A04 | (ADMIN BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | 2025-08-22 | 2025-09-21 | 2025-10-21 | 2025-11-05 | 2025-11-20 | 2025-12-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYC-182981 | ADMINISTRATION & SOCIAL BUILDING - PLUMBING EQUIPMENT SCHEDULE | SCHEDULE |  |  |  |  | Schedule |  | FI | 0CF5566W24A10 | (ADMIN BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-04-30 | 2008-07-29 | 2025-04-01 | 2025-05-01 | 2025-05-31 | 2025-06-15 | 2025-06-30 | 2025-07-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYC-182982 | ADMINISTRATION & SOCIAL BUILDING - PLUMBING SCHEMATIC DIAGRAM | DIAGRAM |  |  |  |  | Diagram |  | FA | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | 2024-05-25 | 2024-06-24 | 2024-07-24 | 2024-08-08 | 2024-08-23 | 2024-09-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYC-182983 | ADMINISTRATION & SOCIAL BUILDING - GROUND FLOOR PLUMBING PLAN | PLAN |  |  |  |  | Plan |  | FA | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYC-182984 | ADMINISTRATION & SOCIAL BUILDING - ROOF PLUMBING PLAN | PLAN |  |  |  |  | Plan |  | FA | 0EF5566W32A04 | (ADMIN BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYC-182985 | ADMINISTRATION & SOCIAL BUILDING - ENLARGED PLUMBING PLAN | PLAN |  |  |  |  | Plan |  | FA | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UYA-183100 | SECURITY BUILDING - CALCULATION | CALCULATION |  |  |  |  | Calculation sheet |  | FA | 3PF2010W20A04P | (STG #30 BLDG) P.O & Procurement - Structure Work(S/S) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2007-09-19 | 2008-01-31 | 2025-02-06 | 2025-03-08 | 2025-04-07 | 2025-04-22 | 2025-05-07 | 2025-05-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYA-183101 | SECURITY BUILDING - GROUND FLOOR PLAN | PLAN |  |  |  |  | Plan |  | FA | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYA-183102 | SECURITY BUILDING - ROOF PLAN | PLAN |  |  |  |  | Plan |  | FA | 1CF2010W20A08 | (STG #10 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2008-08-05 | 2008-11-06 |  |  |  | 2025-05-08 | 2025-06-07 | 2025-07-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYA-183103 | SECURITY BUILDING - SIDE WALL ELEVATION | [6 empty] | SECURITY BUILDING | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYA-183104 | SECURITY BUILDING - MAIN SECTION | [6 empty] | SECURITY BUILDING | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYA-183105 | SECURITY BUILDING - INTERIOR FINISH SCHEDULE | SCHEDULE |  |  |  |  | Schedule |  | FI | 0CF5566W24A10 | (ADMIN BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-04-30 | 2008-07-29 | 2025-04-01 | 2025-05-01 | 2025-05-31 | 2025-06-15 | 2025-06-30 | 2025-07-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYA-183151 | SECURITY BUILDING - FOUNDATION & COLUMN LOCATION PLAN | PLAN |  |  |  |  | Plan |  | FA | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYA-183152 | SECURITY BUILDING - GROUND FLOOR FRAMING PLAN | PLAN |  |  |  |  | Plan |  | FA | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYA-183153 | SECURITY BUILDING - ROOF FLOOR FRAMING PLAN | PLAN |  |  |  |  | Plan |  | FA | 2CF2010W20A08 | (STG #20 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2008-08-05 | 2008-11-06 |  |  |  | 2025-05-08 | 2025-06-07 | 2025-07-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYA-183154 | SECURITY BUILDING - FRAMING ELEVATION | [6 empty] | SECURITY BUILDING | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYA-183155 | SECURITY BUILDING - RE - BAR DETAIL | [6 empty] | SECURITY BUILDING | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYA-183181 | SECURITY BUILDING - PLUMBING EQUIPMENT SCHEDULE | SCHEDULE |  |  |  |  | Schedule |  | FI | 0CF5566W38A06 | (ADMIN BLDG) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2008-05-31 | 2008-07-29 | 2025-05-02 | 2025-06-01 | 2025-07-01 | 2025-07-16 | 2025-07-31 | 2025-08-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYA-183182 | SECURITY BUILDING - PLUMBING SCHEMATIC DIAGRAM | DIAGRAM |  |  |  |  | Diagram |  | FA | 0EF3035W00A01 | (PWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2007-03-15 | 2007-10-29 | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYA-183183 | SECURITY BUILDING - PLUMBING PLAN | PLAN |  |  |  |  | Plan |  | FA | 0CF4500W24A10 | (Fire Fighting BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2008-05-21 | 2008-07-11 |  |  |  | 2025-02-21 | 2025-03-23 | 2025-04-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UYP-183200 | FIRE BRIGADE - CALCULATION | CALCULATION |  |  |  |  | Calculation sheet |  | FA | 0PF4500W38A03P | (Fire Fighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-08-01 | 2008-06-18 | 2024-12-19 | 2025-01-18 | 2025-02-17 | 2025-03-04 | 2025-03-19 | 2025-04-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYP-183201 | FIRE BRIGADE - GROUND FLOOR PLAN, INTERIOR FINISH SCHEDULE | PLAN, SCHEDULE |  |  |  |  | PLAN, SCHEDULE |  | FI | 0CF4500W24A10 | (Fire Fighting BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2008-05-21 | 2008-07-11 | 2025-04-22 | 2025-05-22 | 2025-06-21 | 2025-07-06 | 2025-07-21 | 2025-08-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYP-183202 | FIRE BRIGADE - ROOF PLAN | ROOF PLAN |  |  |  |  | ROOF PLAN |  | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.60 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYP-183203 | FIRE BRIGADE - ELEVATION | ELEVATION |  |  |  |  | Elevation Drawing |  | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.60 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYP-183204 | FIRE BRIGADE - MAIN SECTION | MAIN SECTION |  |  |  |  | MAIN SECTION |  | FI | 0CF4500W38A11 | (Fire Fighting System) Piping Work(Ring Main) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2008-02-15 | 2008-05-17 |  |  |  | 2024-11-17 | 2024-12-17 | 2025-01-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYP-183205 | FIRE BRIGADE - ENLARGED PLAN, CEILING PLAN | PLAN |  |  |  |  | Plan |  | FA | 0CF4500W24A10 | (Fire Fighting BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2008-05-21 | 2008-07-11 |  |  |  | 2025-02-21 | 2025-03-23 | 2025-04-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYP-183251 | FIRE BRIGADE - FOUNDATION, COLUMN ARRAGEMENT PLAN | PLAN |  |  |  |  | Plan |  | FA | 0CF4500W16A03.1 | (Fire Fighting BLDG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-11-07 | 2008-01-03 |  |  |  | 2024-08-09 | 2024-09-08 | 2024-10-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYP-183252 | FIRE BRIGADE - GROUND FLOOR FRAMING PLAN | GROUND FLOOR FRAMING PLAN |  |  |  |  | GROUND FLOOR FRAMING PLAN |  | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.60 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYP-183253 | FIRE BRIGADE - ROOF FRAMING PLAN | ROOF FRAMING PLAN |  |  |  |  | ROOF FRAMING PLAN |  | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.60 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYP-183254 | FIRE BRIGADE - FRAMING ELEVATION | FRAMING ELEVATION |  |  |  |  | FRAMING ELEVATION | ST BUILDING | FI | 0CF4500W24A10 | (Fire Fighting BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2008-05-21 | 2008-07-11 |  |  |  | 2025-02-21 | 2025-03-23 | 2025-04-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYP-183255 | FIRE BRIGADE - MISC. STRUCTURAL DETAIL | MISC. STRUCTURAL DETAIL |  |  |  |  | MISC. STRUCTURAL DETAIL | FIRE BRIGADE | FI | 0CF4500W24A10 | (Fire Fighting BLDG) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2008-05-21 | 2008-07-11 |  |  |  | 2025-02-21 | 2025-03-23 | 2025-04-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYP-183256 | FIRE BRIGADE - FOUNDATION, SLAB REBAR SCHEDULE | SCHEDULE |  |  |  |  | Schedule |  | FI | 0CF4500W16A03.1 | (Fire Fighting BLDG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-11-07 | 2008-01-03 | 2024-10-08 | 2024-11-07 | 2024-12-07 | 2024-12-22 | 2025-01-06 | 2025-01-21 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYP-183257 | FIRE BRIGADE - COLUMN, GIRDER, BEAM SHEDULE | [6 empty] | FIRE BRIGADE | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYP-183281 | FIRE BRIGADE - PLUMBING EQUIPMENT SCHEDULE | SCHEDULE |  |  |  |  | Schedule |  | FI | 0PF4500W38A04T | (Fire Fighting Equip) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2008-04-16 | 2008-10-31 | 2025-03-18 | 2025-04-17 | 2025-05-17 | 2025-06-01 | 2025-06-16 | 2025-07-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYP-183282 | FIRE BRIGADE - PLUMBING SCHEMATIC DIAGRAM | PLUMBING SCHEMATIC DIAGRAM |  |  |  |  | PLUMBING SCHEMATIC DIAGRAM |  | FA | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System | 2007-03-30 | 2007-11-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYP-183283 | FIRE BRIGADE - GROUND FLOOR PLUMBING PLAN | GROUND FLOOR PLUMBING PLAN |  |  |  |  | GROUND FLOOR PLUMBING PLAN |  | FA | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  |  |  | 2024-05-09 | 2024-06-08 | 2024-07-08 | generated | 0.60 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYP-183284 | FIRE BRIGADE - ROOF PLUMBING PLAN | ROOF PLUMBING PLAN |  |  |  |  | ROOF PLUMBING PLAN | FIRE BRIGADE | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  |  |  | 2024-07-08 | 2024-08-07 | 2024-09-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYP-183285 | FIRE BRIGADE - ENLARGED PLUMBING PLAN | ENLARGED PLUMBING PLAN |  |  |  |  | ENLARGED PLUMBING PLAN | FIRE BRIGADE | FI | 0EF4500W16A02.1 | (Fire Fighting BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > HVAC & Fire Fighting System > Fire Fighting System > Fire Fighting Building | 2007-08-07 | 2007-11-06 |  |  |  | 2024-07-08 | 2024-08-07 | 2024-09-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UYE-183300 | MAIN GATE HOUSE - CALCULATION | CALCULATION |  |  |  |  | Calculation sheet |  | FA | 0EF5570W32A03 | (Gate House) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 | 2025-01-18 | 2025-02-17 | 2025-03-19 | 2025-04-03 | 2025-04-18 | 2025-05-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYE-183301 | MAIN GATE HOUSE - GROUND FLOOR , ROOF PLAN, INTERIOR FINISH, DOOR & WINDOW SCHEDULES | PLAN, SCHEDULES |  |  |  |  | PLAN, SCHEDULES |  | FA | 0CF5570W24A09 | (Gate House) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-07-02 | 2008-09-01 |  |  |  | 2025-04-04 | 2025-05-04 | 2025-06-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYE-183302 | MAIN GATE HOUSE - ELEVATIONS | ELEVATIONS |  |  |  |  | ELEVATIONS | SUPPORT BUILDING | FI | 0EF5570W16A01 | (Gate House) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYE-183303 | MAIN GATE HOUSE - SECTIONS & DETAILS |  |  |  | MAIN GATE HOUSE |  | for MAIN GATE HOUSE | MAIN GATE | FI | 0EF5570W16A01 | (Gate House) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYE-183351 | MAIN GATE HOUSE - FOUNDATION ARRANGEMENT, GROUND FLOOR FRAMING PLAN | PLAN |  |  | MAIN GATE HOUSE |  | Plan for MAIN GATE HOUSE | MAIN GATE | FI | 0EF5570W16A01 | (Gate House) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYE-183352 | MAIN GATE HOUSE - ROOF FRAMING PLAN | PLAN |  |  | MAIN GATE HOUSE |  | Plan for MAIN GATE HOUSE | MAIN GATE | FI | 0EF5570W32A03 | (Gate House) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYE-183353 | MAIN GATE HOUSE - FRAMING ELEVATION | ELEVATION |  |  | MAIN GATE HOUSE |  | Elevation Drawing for MAIN GATE HOUSE | MAIN GATE | FI | 0EF5570W16A01 | (Gate House) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYE-183354 | MAIN GATE HOUSE - COLUMN, GIRDER & BEAM RE - BAR DETAIL |  |  |  | MAIN GATE HOUSE |  | for MAIN GATE HOUSE | MAIN GATE | FI | 0EF5570W16A01 | (Gate House) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYE-183355 | MAIN GATE HOUSE - FOUNDATION, SLAB & MISC. RE - BAR DEDAIL |  |  |  | MAIN GATE HOUSE |  | for MAIN GATE HOUSE | MAIN GATE | FI | 0EF5570W16A01 | (Gate House) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UTX-183361 | MAIN GATE HOUSE SUNSHADE - GROUND FLOOR, ROOF PLAN & ELEVATION |  |  |  | MAIN GATE HOUSE |  | for MAIN GATE HOUSE | MAIN GATE | FI | 0EF5570W16A01 | (Gate House) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UTX-183371 | MAIN GATE HOUSE SUNSHADE - ROOF FRAMING PLAN (TOP CHORD) |  |  |  | MAIN GATE HOUSE |  | for MAIN GATE HOUSE | MAIN GATE | FI | 0EF5570W16A01 | (Gate House) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UTX-183372 | MAIN GATE HOUSE SUNSHADE - ROOF FRAMING PLAN (BOTTOM CHORD) |  |  |  | MAIN GATE HOUSE |  | for MAIN GATE HOUSE | MAIN GATE | FI | 0EF5570W16A01 | (Gate House) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UTX-183373 | MAIN GATE HOUSE SUNSHADE - FRAMING ELEVATION | ELEVATION |  |  | MAIN GATE HOUSE |  | Elevation Drawing for MAIN GATE HOUSE | MAIN GATE | FI | 0EF5570W16A01 | (Gate House) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UTX-183375 | MAIN GATE HOUSE SUNSHADE - BASE PLATE & CONNECTION DETAIL |  |  |  | MAIN GATE HOUSE |  | for MAIN GATE HOUSE | MAIN GATE | FI | 0EF5570W16A01 | (Gate House) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UTX-183377 | MAIN GATE HOUSE SUNSHADE - FOUNDATION RE - BAR DETAIL |  |  |  | MAIN GATE HOUSE |  | for MAIN GATE HOUSE | MAIN GATE | FI | 0EF5570W16A01 | (Gate House) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UTX-183390 | MAIN GATE HOUSE SUNSHADE - CALCULATION | CALCULATION |  |  | MAIN GATE HOUSE |  | Calculation sheet for MAIN GATE HOUSE | MAIN GATE | FI | 0EF5570W16A01 | (Gate House) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2007-08-31 | 2007-11-30 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UYB-183500 | SUPPORT BUILDING - CALCULATION | CALCULATION |  |  | SUPPORT BUILDING |  | Calculation sheet for SUPPORT BUILDING | SUPPORT BUILDING | FI | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYB-183501 | SUPPORT BUILDING - GROUND FLOOR PLAN, ROOF PLAN, ELEVATIONS & MAIN SECTION |  |  |  | SUPPORT BUILDING |  | for SUPPORT BUILDING |  | FA | 3CF2010W20A08 | (STG #30 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2008-09-04 | 2008-12-05 | 2027-03-29 | 2027-04-28 | 2027-05-28 | 2027-06-12 | 2027-06-27 | 2027-07-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYB-183502 | SUPPORT BUILDING - TOILET PLAN & ELEVATION |  |  |  | SUPPORT BUILDING |  | for SUPPORT BUILDING |  | FA | 0EF5566W32A04 | (ADMIN BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | 2025-10-21 | 2025-11-20 | 2025-12-20 | 2026-01-04 | 2026-01-19 | 2026-02-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYB-183551 | SUPPORT BUILDING - FOUNDATION DETAILS, GROUND FLOOR PLAN, ROOF FRAMING PLAN | PLAN |  |  | SUPPORT BUILDING |  | Plan for SUPPORT BUILDING |  | FA | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 | 2025-10-21 | 2025-11-20 | 2025-12-20 | 2026-01-04 | 2026-01-19 | 2026-02-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYB-183552 | SUPPORT BUILDING - FRAMING ELEVATIONS | ELEVATIONS |  |  | SUPPORT BUILDING |  | ELEVATIONS for SUPPORT BUILDING | SUPPORT BUILDING | FI | 0EF5566W32A04 | (ADMIN BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYB-183553 | SUPPORT BUILDING - COLUMN, GIRDER & BEAM RE - BAR DETAIL |  |  |  | SUPPORT BUILDING |  | for SUPPORT BUILDING |  | FA | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 | 2026-10-10 | 2026-11-09 | 2026-12-09 | 2026-12-24 | 2027-01-08 | 2027-01-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYB-183554 | SUPPORT BUILDING - FOUNDATION, SLAB & MISC. RE - BAR DEDAIL |  |  |  | SUPPORT BUILDING |  | for SUPPORT BUILDING |  | FA | 0CF5510W16A03 | (CCR BLDG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-09-01 | 2007-11-01 | 2026-03-25 | 2026-04-24 | 2026-05-24 | 2026-06-08 | 2026-06-23 | 2026-07-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYB-183581 | SUPPORT BUILDING - PLUMBING EQUIPMENT SCHEDULE & PLUMBING SCHEMATIC DIAGRAM | EQUIPMENT SCHEDULE & PLUMBING SCHEMATIC DIAGRAM |  |  | SUPPORT BUILDING |  | EQUIPMENT SCHEDULE & PLUMBING SCHEMATIC DIAGRAM for SUPPORT BUILDING | SUPPORT BUILDING | FI | 0EF5566W16A02 | (ADMIN BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Administration Building | 2007-03-30 | 2007-10-01 |  |  |  | 2024-03-01 | 2024-03-30 | 2024-04-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYB-183582 | SUPPORT BUILDING - PLUMBING PLAN | PLAN |  |  | SUPPORT BUILDING |  | Plan for SUPPORT BUILDING |  | FA | 0EF5535W32A17 | (STS BLDG) Building Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-11-02 | 2008-01-31 | 2026-05-26 | 2026-06-25 | 2026-07-25 | 2026-08-09 | 2026-08-24 | 2026-09-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UYF-183600 | SEARCH FACILITY & VISITORS CENTRE - CALCULATION | CALCULATION |  |  | SEARCH FACILITY & VISITORS CENTRE |  | Calculation sheet for SEARCH FACILITY & VISITORS CENTRE | Search Facility & Visitor Center | FI | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYF-183601 | SEARCH FACILITY & VISITORS CENTRE - GROUND FLOOR PLAN | PLAN |  |  | SEARCH FACILITY & VISITORS CENTRE |  | Plan for SEARCH FACILITY & VISITORS CENTRE | Search Facility & Visitor Center | FI | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYF-183602 | SEARCH FACILITY & VISITORS CENTRE - ROOF PLAN | PLAN |  |  | SEARCH FACILITY & VISITORS CENTRE |  | Plan for SEARCH FACILITY & VISITORS CENTRE | Search Facility & Visitor Center | FI | 3CF2010W20A08 | (STG #30 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | 2008-09-04 | 2008-12-05 |  |  |  | 2025-06-07 | 2025-07-07 | 2025-08-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYF-183603 | SEARCH FACILITY & VISITORS CENTRE - ELEVATION | ELEVATION |  |  | SEARCH FACILITY & VISITORS CENTRE |  | Elevation Drawing for SEARCH FACILITY & VISITORS CENTRE | Search Facility & Visitor Center | FI | 0EF6010W10A03 | Site Preparation Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > General Civil Works > Site Preparation | 2007-03-01 | 2007-05-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UYF-183604 | SEARCH FACILITY & VISITORS CENTRE - MAIN SECTION | SECTION |  |  | SEARCH FACILITY & VISITORS CENTRE |  | SECTION for SEARCH FACILITY & VISITORS CENTRE | Search Facility & Visitor Center | FI | 2EF1625W42A01 | (HRSG #21 Main Stack) Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Main Stack | 2007-05-17 | 2007-11-28 |  |  |  | 2024-03-01 | 2024-03-18 | 2024-04-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYF-183651 | SEARCH FACILITY & VISITORS CENTRE - FOUNDATION & COLUMN ARRANGEMENT PLAN | PLAN |  |  | SEARCH FACILITY & VISITORS CENTRE |  | Plan for SEARCH FACILITY & VISITORS CENTRE | Search Facility & Visitor Center | FI | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYF-183652 | SEARCH FACILITY & VISITORS CENTRE - GROUND FLOOR & ROOF FRAMING PLAN | PLAN |  |  | SEARCH FACILITY & VISITORS CENTRE |  | Plan for SEARCH FACILITY & VISITORS CENTRE | Search Facility & Visitor Center | FI | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UYF-183653 | SEARCH FACILITY & VISITORS CENTRE - FRAMING ELEVATION | ELEVATION |  |  | SEARCH FACILITY & VISITORS CENTRE |  | Elevation Drawing for SEARCH FACILITY & VISITORS CENTRE | Search Facility & Visitor Center | FI | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UYF-183654 | SEARCH FACILITY & VISITORS CENTRE - REBAR SCHEDULE & DETAIL | SCHEDULE & DETAIL |  |  | SEARCH FACILITY & VISITORS CENTRE |  | SCHEDULE & DETAIL for SEARCH FACILITY & VISITORS CENTRE | Search Facility & Visitor Center | FI | 0CF5570W16A12 | (Fence & Gate) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Fence & Gates | 2008-05-08 | 2008-09-01 |  |  |  | 2025-02-08 | 2025-03-10 | 2025-04-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYF-183681 | SEARCH FACILITY & VISITORS CENTRE - PLUMBING EQUIPMENT SCHEDULE & PLUMBING SCHEMATIC DIAGRAM | EQUIPMENT SCHEDULE & PLUMBING SCHEMATIC DIAGRAM |  |  | SEARCH FACILITY & VISITORS CENTRE |  | EQUIPMENT SCHEDULE & PLUMBING SCHEMATIC DIAGRAM for SEARCH FACILITY & VISITORS CENTRE | Search Facility & Visitor Center | FI | 0EF4035W00A01 | (STS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Sewage Treatment System | 2007-04-02 | 2007-12-07 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA05-P0UYF-183682 | SEARCH FACILITY & VISITORS CENTRE - PLUMBING PLAN | PLAN |  |  | SEARCH FACILITY & VISITORS CENTRE |  | Plan for SEARCH FACILITY & VISITORS CENTRE | Search Facility & Visitor Center | FI | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0ULD-183900 | CPP & CPP REGEN BUILDING - CALCULATION | CALCULATION |  |  | CPP & CPP REGEN BUILDING |  | Calculation sheet for CPP & CPP REGEN BUILDING | CPP Regeneration Building | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0ULD-183902 | CPP & CPP REGEN BUILDING - GROUND FLOOR PLAN | PLAN |  |  | CPP & CPP REGEN BUILDING |  | Plan for CPP & CPP REGEN BUILDING | CPP Regeneration Building | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0ULD-183903 | CPP & CPP REGEN BUILDING - ROOF FLOOR PLAN | PLAN |  |  | CPP & CPP REGEN BUILDING |  | Plan for CPP & CPP REGEN BUILDING | CPP Regeneration Building | FI | 2CF2010W20A08 | (STG #20 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2008-08-05 | 2008-11-06 |  |  |  | 2025-05-08 | 2025-06-07 | 2025-07-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0ULD-183904 | CPP & CPP REGEN BUILDING - ELEVATION | ELEVATION |  |  | CPP & CPP REGEN BUILDING |  | Elevation Drawing for CPP & CPP REGEN BUILDING | CPP Regeneration Building | FI | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 |  |  |  | 2024-03-01 | 2024-03-19 | 2024-04-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0ULD-183905 | CPP & CPP REGEN BUILDING - SECTION | SECTION |  |  | CPP & CPP REGEN BUILDING |  | SECTION for CPP & CPP REGEN BUILDING | CPP Regeneration Building | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0ULD-183906 | CPP & CPP REGEN BUILDING - INTERIOR FINISH, DOOR & WINDOW SCHEDULE | SCHEDULE |  |  | CPP & CPP REGEN BUILDING |  | Schedule for CPP & CPP REGEN BUILDING | CPP Regeneration Building | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0ULD-183908 | CPP & CPP REGEN BUILDING - WALL SECTION DETAIL | SECTION DETAIL |  |  | CPP & CPP REGEN BUILDING |  | SECTION DETAIL for CPP & CPP REGEN BUILDING | CPP Regeneration Building | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0ULD-183909 | CPP & CPP REGEN BUILDING - WALL OPENING PLAN | PLAN |  |  | CPP & CPP REGEN BUILDING |  | Plan for CPP & CPP REGEN BUILDING | CPP Regeneration Building | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0ULD-183910 | CPP & CPP REGEN BUILDING - ARCHITECTURAL MISC. DETAIL |  |  |  | CPP & CPP REGEN BUILDING |  | for CPP & CPP REGEN BUILDING | CPP Regeneration Building | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0ULD-183951 | CPP & CPP REGEN BUILDING - FOUNDATION & COLUMN ARRANGEMENT PLAN | PLAN |  |  | CPP & CPP REGEN BUILDING |  | Plan for CPP & CPP REGEN BUILDING | CPP Regeneration Building | FI | 0EF5510W00A01 | (CCR BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 |  |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0ULD-183952 | CPP & CPP REGEN BUILDING - GROUND FLOOR FRAMING PLAN | PLAN |  |  | CPP & CPP REGEN BUILDING |  | Plan for CPP & CPP REGEN BUILDING | CPP Regeneration Building | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0ULD-183953 | CPP & CPP REGEN BUILDING - ROOF FLOOR FRAMING PLAN | PLAN |  |  | CPP & CPP REGEN BUILDING |  | Plan for CPP & CPP REGEN BUILDING | CPP Regeneration Building | FI | 2CF2010W20A08 | (STG #20 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2008-08-05 | 2008-11-06 |  |  |  | 2025-05-08 | 2025-06-07 | 2025-07-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0ULD-183954 | CPP & CPP REGEN BUILDING - FRAMING ELEVATION |  |  |  | CPP & CPP REGEN BUILDING |  | for CPP & CPP REGEN BUILDING | CPP Regeneration Building | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0ULD-183955 | CPP & CPP REGEN BUILDING - FOUNDATION REBAR DETAIL |  |  |  | CPP & CPP REGEN BUILDING |  | for CPP & CPP REGEN BUILDING | CPP Regeneration Building | FI | 0CF5510W16A03 | (CCR BLDG) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-09-01 | 2007-11-01 |  |  |  | 2024-06-03 | 2024-07-03 | 2024-08-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0ULD-183956 | CPP & CPP REGEN BUILDING - COLUMN REBAR DETAIL |  |  |  | CPP & CPP REGEN BUILDING |  | for CPP & CPP REGEN BUILDING | CPP Regeneration Building | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0ULD-183957 | CPP & CPP REGEN BUILDING - GIRDER & BEAM REBAR SCHEDULE | SCHEDULE |  |  | CPP & CPP REGEN BUILDING |  | Schedule for CPP & CPP REGEN BUILDING | CPP Regeneration Building | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0ULD-183958 | CPP & CPP REGEN BUILDING - SLAB REBAR DETAIL |  |  |  | CPP & CPP REGEN BUILDING |  | for CPP & CPP REGEN BUILDING | CPP Regeneration Building | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0ULD-183959 | CPP & CPP REGEN BUILDING - EQUIPMENT FOUNDTAION REBAR DETAIL |  |  |  | CPP & CPP REGEN BUILDING |  | for CPP & CPP REGEN BUILDING | CPP Regeneration Building | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0ULD-183960 | CPP & CPP REGEN BUILDING - EMBEDDED PLATE & SLEEVE PLAN | PLAN |  |  | CPP & CPP REGEN BUILDING |  | Plan for CPP & CPP REGEN BUILDING | CPP Regeneration Building | FI | 0EF5510W16A02 | (CCR BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2007-04-02 | 2007-08-30 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0ULD-183961 | CPP & CPP REGEN BUILDING - MISC. REBAR DETAIL |  |  |  | CPP & CPP REGEN BUILDING |  | for CPP & CPP REGEN BUILDING | CPP Regeneration Building | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULD-183962 | CPP & CPP REGEN BUILDING - ROOF COLUMN LOCATION PLAN | PLAN |  |  | CPP & CPP REGEN BUILDING |  | Plan for CPP & CPP REGEN BUILDING | CPP Regeneration Building | FI | 2CF2010W20A08 | (STG #20 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2008-08-05 | 2008-11-06 |  |  |  | 2025-05-08 | 2025-06-07 | 2025-07-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULD-183963 | CPP & CPP REGEN BUILDING - ENLARGED ROOF FRAMING PLAN | PLAN |  |  | CPP & CPP REGEN BUILDING |  | Plan for CPP & CPP REGEN BUILDING | CPP Regeneration Building | FI | 2CF2010W20A08 | (STG #20 BLDG) Roof Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2008-08-05 | 2008-11-06 |  |  |  | 2025-05-08 | 2025-06-07 | 2025-07-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULD-183964 | CPP & CPP REGEN BUILDING - GIRT LINE & ROW ELEVATION |  |  |  | CPP & CPP REGEN BUILDING |  | for CPP & CPP REGEN BUILDING | CPP Regeneration Building | FI | 0CF5510W24A10 | (CCR BLDG) Building Finish for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Central Control Building | 2008-03-18 | 2008-07-31 |  |  |  | 2024-12-19 | 2025-01-18 | 2025-02-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0ULD-183965 | CPP & CPP REGEN BUILDING - STEEL CONNECTION DETAIL |  |  |  | CPP & CPP REGEN BUILDING |  | for CPP & CPP REGEN BUILDING | CPP Regeneration Building | FI | 2PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | 2007-09-03 | 2008-02-14 |  |  |  | 2024-06-05 | 2024-07-05 | 2024-08-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0USR-184700 | WWT & BULK CHEMICAL STORAGE TANK SHELTER - CALCULATION | CALCULATION |  |  | WWT & BULK CHEMICAL STORAGE TANK SHELTER |  | Calculation sheet for WWT & BULK CHEMICAL STORAGE TANK SHELTER |  | FI | 0CF3010W24A08 | (DWP Chemical Storage Tank Shelter) Shelter Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2008-08-22 | 2008-10-13 |  |  |  | 2025-05-25 | 2025-06-24 | 2025-07-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0USR-184701 | WWT & BULK CHEMICAL STORAGE TANK SHELTER - GROUND & ROOF FLOOR PLAN | PLAN |  |  | WWT & BULK CHEMICAL STORAGE TANK SHELTER |  | Plan for WWT & BULK CHEMICAL STORAGE TANK SHELTER |  | FI | 0CF3010W24A08 | (DWP Chemical Storage Tank Shelter) Shelter Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2008-08-22 | 2008-10-13 |  |  |  | 2025-05-25 | 2025-06-24 | 2025-07-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0USR-184702 | WWT & BULK CHEMICAL STORAGE TANK SHELTER - ELEVATIONS & SECTIONS |  |  |  | WWT & BULK CHEMICAL STORAGE TANK SHELTER |  | for WWT & BULK CHEMICAL STORAGE TANK SHELTER |  | FI | 0CF3010W24A08 | (DWP Chemical Storage Tank Shelter) Shelter Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2008-08-22 | 2008-10-13 |  |  |  | 2025-05-25 | 2025-06-24 | 2025-07-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0USR-184751 | WWT & BULK CHEMICAL STORAGE TANK SHELTER - STEEL COLUMN LOCATION & ROOF PLAN | PLAN | Tank |  | WWT & BULK CHEMICAL STORAGE TANK SHELTER |  | Plan for Tank |  | FA | 0CF3010W24A08 | (DWP Chemical Storage Tank Shelter) Shelter Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2008-08-22 | 2008-10-13 |  |  |  | 2025-05-25 | 2025-06-24 | 2025-07-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0USR-184752 | WWT & BULK CHEMICAL STORAGE TANK SHELTER - STEEL FRAMING ELEVATIONS | ELEVATIONS |  |  | WWT & BULK CHEMICAL STORAGE TANK SHELTER |  | ELEVATIONS for WWT & BULK CHEMICAL STORAGE TANK SHELTER |  | FI | 0CF3010W24A08 | (DWP Chemical Storage Tank Shelter) Shelter Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2008-08-22 | 2008-10-13 |  |  |  | 2025-05-25 | 2025-06-24 | 2025-07-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0QJA-184800 | N2 STORAGE SHELTER - CALCULATION | CALCULATION |  |  | N2 STORAGE SHELTER |  | Calculation sheet for N2 STORAGE SHELTER | Gas Storage Shelter | FI | 1EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 |  |  |  | 2024-09-04 | 2024-10-04 | 2024-11-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0QJA-184801 | N2 STORAGE SHELTER - GROUND FLOOR PLAN, ROOF PLAN | PLAN |  |  | N2 STORAGE SHELTER |  | Plan for N2 STORAGE SHELTER | Gas Storage Shelter | FI | 2EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 |  |  |  | 2024-09-04 | 2024-10-04 | 2024-11-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0QJA-184802 | N2 STORAGE SHELTER - ELEVATION | ELEVATION |  |  | N2 STORAGE SHELTER |  | Elevation Drawing for N2 STORAGE SHELTER | Gas Storage Shelter | FI | 2EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 |  |  |  | 2024-09-04 | 2024-10-04 | 2024-11-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0QJA-184803 | N2 STORAGE SHELTER - MAIN SECTION | SECTION |  |  | N2 STORAGE SHELTER |  | SECTION for N2 STORAGE SHELTER | Gas Storage Shelter | FI | 0CF3010W24A08 | (DWP Chemical Storage Tank Shelter) Shelter Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2008-08-22 | 2008-10-13 |  |  |  | 2025-05-25 | 2025-06-24 | 2025-07-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0QJA-184851 | N2 STORAGE SHELTER - FOUNDATION, COLUMN ARRAGEMENT PLAN | PLAN |  |  | N2 STORAGE SHELTER |  | Plan for N2 STORAGE SHELTER | Gas Storage Shelter | FI | 2CF3515W16A07 | (N2 Gas Station Shelter) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > N2 Gas System | 2008-04-05 | 2008-06-02 |  |  |  | 2025-01-06 | 2025-02-05 | 2025-03-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0QJA-184852 | N2 STORAGE SHELTER - GROUND FLOOR FRAMING PLAN, ROOF FRAMING PLAN | PLAN |  |  | N2 STORAGE SHELTER |  | Plan for N2 STORAGE SHELTER | Gas Storage Shelter | FI | 2EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 |  |  |  | 2024-09-04 | 2024-10-04 | 2024-11-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0QJA-184853 | N2 STORAGE SHELTER - FRAMING ELEVATION | ELEVATION |  |  | N2 STORAGE SHELTER |  | Elevation Drawing for N2 STORAGE SHELTER | Gas Storage Shelter | FI | 2EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 |  |  |  | 2024-09-04 | 2024-10-04 | 2024-11-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0QJA-184854 | N2 STORAGE SHELTER - REBAR DETAIL | REBAR DETAIL |  |  | N2 STORAGE SHELTER |  | REBAR DETAIL for N2 STORAGE SHELTER | Gas Storage Shelter | FI | 2EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 |  |  |  | 2024-09-04 | 2024-10-04 | 2024-11-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UTG-184900 | H2, CO2 STORAGE SHELTER - CALCULATION | CALCULATION |  |  | H2, CO2 STORAGE SHELTER |  | Calculation sheet for H2, CO2 STORAGE SHELTER | Gas Storage Shelter | FI | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UTG-184901 | H2, CO2 STORAGE SHELTER - GROUND FLOOR PLAN, ROOF PLAN | PLAN |  |  | H2, CO2 STORAGE SHELTER |  | Plan for H2, CO2 STORAGE SHELTER | Gas Storage Shelter | FI | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UTG-184902 | H2, CO2 STORAGE SHELTER - ELEVATION | ELEVATION |  |  | H2, CO2 STORAGE SHELTER |  | Elevation Drawing for H2, CO2 STORAGE SHELTER | Gas Storage Shelter | FI | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UTG-184903 | H2, CO2 STORAGE SHELTER - MAIN SECTION | SECTION |  |  | H2, CO2 STORAGE SHELTER |  | SECTION for H2, CO2 STORAGE SHELTER | Gas Storage Shelter | FI | 0CF3010W24A08 | (DWP Chemical Storage Tank Shelter) Shelter Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2008-08-22 | 2008-10-13 |  |  |  | 2025-05-25 | 2025-06-24 | 2025-07-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UTG-184951 | H2, CO2 STORAGE SHELTER - FOUNDATION, COLUMN ARRAGEMENT PLAN | PLAN |  |  | H2, CO2 STORAGE SHELTER |  | Plan for H2, CO2 STORAGE SHELTER | Gas Storage Shelter | FI | 0EF3515W16A05 | (H2 Equipment) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-10-24 | 2008-01-21 |  |  |  | 2024-07-26 | 2024-08-25 | 2024-09-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UTG-184952 | H2, CO2 STORAGE SHELTER - GROUND FLOOR FRAMING PLAN, ROOF FRAMING PLAN | PLAN |  |  | H2, CO2 STORAGE SHELTER |  | Plan for H2, CO2 STORAGE SHELTER | Gas Storage Shelter | FI | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UTG-184953 | H2, CO2 STORAGE SHELTER - FRAMING ELEVATION | ELEVATION |  |  | H2, CO2 STORAGE SHELTER |  | Elevation Drawing for H2, CO2 STORAGE SHELTER | Gas Storage Shelter | FI | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UTG-184954 | H2, CO2 STORAGE SHELTER - REBAR DETAIL | REBAR DETAIL |  |  | H2, CO2 STORAGE SHELTER |  | REBAR DETAIL for H2, CO2 STORAGE SHELTER | Gas Storage Shelter | FI | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  |  |  |  | 2024-06-02 | 2024-07-02 | 2024-08-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185151 | PIPE RACK #1 - FOUNDATION PLAN | PLAN |  |  | PIPE RACK #1 |  | Plan for PIPE RACK #1 | PIPE RACK | FI | 0EF5550W16A03 | (Pipe Rack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Pipe Rack | 2007-06-29 | 2007-10-26 |  |  |  | 2024-03-31 | 2024-04-30 | 2024-05-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185152 | PIPE RACK #1 - COLUMN LOCATION PLAN & BASE PLATE DETAIL | DETAIL |  |  | PIPE RACK #1 |  | Detail Drawing for PIPE RACK #1 | PIPE RACK | FI | 0EF5550W16A03 | (Pipe Rack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Pipe Rack | 2007-06-29 | 2007-10-26 |  |  |  | 2024-03-31 | 2024-04-30 | 2024-05-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185153 | PIPE RACK #1 - FRAMING PLAN | PLAN |  |  | PIPE RACK |  | Plan for PIPE RACK | PIPE RACK | FI | 1EF5550W00A01 | (PipeRack) Pipe Rack Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-01 | 2007-03-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185154 | PIPE RACK #1 - ELEVATION | ELEVATION |  |  | PIPE RACK |  | Elevation Drawing for PIPE RACK | PIPE RACK | FI | 1EF5550W00A01 | (PipeRack) Pipe Rack Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-01 | 2007-03-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185155 | PIPE RACK #1 - FOUNDATION & PEDETAL DETAIL | DETAIL |  |  | PIPE RACK |  | Detail Drawing for PIPE RACK | PIPE RACK | FI | 0EF5550W16A03 | (Pipe Rack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Pipe Rack | 2007-06-29 | 2007-10-26 |  |  |  | 2024-03-31 | 2024-04-30 | 2024-05-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185160 | PIPE RACK #2 - FOUNDATION PLAN | PLAN |  |  | PIPE RACK |  | Plan for PIPE RACK | PIPE RACK | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185161 | PIPE RACK #2 - COLUMN LOCATION PLAN | PLAN |  |  | PIPE RACK |  | Plan for PIPE RACK | PIPE RACK | FI | 2EF5550W00A01 | (PipeRack) Pipe Rack Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-03-01 | 2007-03-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185162 | PIPE RACK #2 - FRAMING PLAN - 1 | PLAN |  |  | PIPE RACK |  | Plan for PIPE RACK | PIPE RACK | FI | 2EF5550W00A01 | (PipeRack) Pipe Rack Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-03-01 | 2007-03-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185163 | PIPE RACK #2 - FRAMING PLAN - 2 | PLAN |  |  | PIPE RACK |  | Plan for PIPE RACK | PIPE RACK | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185164 | PIPE RACK #2 - LINE ELEVATION | ELEVATION |  |  | PIPE RACK |  | Elevation Drawing for PIPE RACK | PIPE RACK | FI | 2EF5550W00A01 | (PipeRack) Pipe Rack Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-03-01 | 2007-03-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185165 | PIPE RACK #2 - ROW ELEVATION | ELEVATION |  |  | PIPE RACK |  | Elevation Drawing for PIPE RACK | PIPE RACK | FI | 2EF5550W00A01 | (PipeRack) Pipe Rack Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-03-01 | 2007-03-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185166 | PIPE RACK #2 - FOUNDATION DETAIL | DETAIL |  |  | PIPE RACK |  | Detail Drawing for PIPE RACK | PIPE RACK | FI | 0EF5550W16A03 | (Pipe Rack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Pipe Rack | 2007-06-29 | 2007-10-26 |  |  |  | 2024-03-31 | 2024-04-30 | 2024-05-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185167 | PIPE RACK #2 - PEDETAL DETAIL | DETAIL |  |  | PIPE RACK |  | Detail Drawing for PIPE RACK | PIPE RACK | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185168 | PIPE RACK #2 - BASE PLATE DETAIL | DETAIL |  |  | PIPE RACK |  | Detail Drawing for PIPE RACK | PIPE RACK | FI | 2EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-05-30 | 2007-08-31 |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185169 | PIPE RACK #3 - FOUNDATION PLAN | PLAN |  |  | PIPE RACK |  | Plan for PIPE RACK | PIPE RACK | FI | 3EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-05-30 | 2007-08-31 |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185170 | PIPE RACK #3 - COLUMN LOCATION PLAN | PLAN |  |  | PIPE RACK |  | Plan for PIPE RACK | PIPE RACK | FI | 3EF5550W00A01 | (PipeRack) Pipe Rack Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-03-01 | 2007-03-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185171 | PIPE RACK #3 - FRAMING PLAN - 1 | PLAN |  |  | PIPE RACK |  | Plan for PIPE RACK | PIPE RACK | FI | 3EF5550W00A01 | (PipeRack) Pipe Rack Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-03-01 | 2007-03-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185172 | PIPE RACK #3 - FRAMING PLAN - 2 | PLAN |  |  | PIPE RACK |  | Plan for PIPE RACK | PIPE RACK | FI | 3EF5550W00A01 | (PipeRack) Pipe Rack Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-03-01 | 2007-03-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185173 | PIPE RACK #3 - LINE ELEVATION | ELEVATION |  |  | PIPE RACK |  | Elevation Drawing for PIPE RACK | PIPE RACK | FI | 3EF5550W00A01 | (PipeRack) Pipe Rack Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-03-01 | 2007-03-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185174 | PIPE RACK #3 - ROW SECTION | SECTION |  |  | PIPE RACK |  | SECTION for PIPE RACK | PIPE RACK | FI | 3EF5550W00A01 | (PipeRack) Pipe Rack Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-03-01 | 2007-03-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185175 | PIPE RACK #3 - FOUNDATION DETAIL | DETAIL |  |  | PIPE RACK |  | Detail Drawing for PIPE RACK | PIPE RACK | FI | 3EF5550W16A03 | (PipeRack) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-05-30 | 2007-08-31 |  |  |  | 2024-03-01 | 2024-03-31 | 2024-04-30 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185176 | PIPE RACK #3 - PEDETAL & TIE GIRDER DETAIL | DETAIL |  |  | PIPE RACK |  | Detail Drawing for PIPE RACK | PIPE RACK | FI | 3EF5550W00A01 | (PipeRack) Pipe Rack Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-03-01 | 2007-03-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185177 | PIPE RACK #3 - BASE PLATE DETAIL | DETAIL |  |  | PIPE RACK #3 |  | Detail Drawing for PIPE RACK #3 | PIPE RACK | FI | 3EF5550W00A01 | (PipeRack) Pipe Rack Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-03-01 | 2007-03-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0UMY-185178 | PIPE RACK - MISC DETAIL | DETAIL |  |  | PIPE RACK |  | Detail Drawing for PIPE RACK | PIPE RACK | FI | 2EF5550W00A01 | (PipeRack) Pipe Rack Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-03-01 | 2007-03-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UMY-185190 | PIPE RACK #1 - CALCULATION | CALCULATION |  |  | PIPE RACK #1 |  | Calculation sheet for PIPE RACK #1 | PIPE RACK | FI | 1EF5550W00A01 | (PipeRack) Pipe Rack Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | 2007-03-01 | 2007-03-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UMY-185191 | PIPE RACK #2 - CALCULATION | CALCULATION |  |  | PIPE RACK #2 |  | Calculation sheet for PIPE RACK #2 | PIPE RACK | FI | 2EF5550W00A01 | (PipeRack) Pipe Rack Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | 2007-03-01 | 2007-03-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UMY-185192 | PIPE RACK #3 - CALCULATION | CALCULATION |  |  | PIPE RACK #3 |  | Calculation sheet for PIPE RACK #3 | PIPE RACK | FI | 3EF5550W00A01 | (PipeRack) Pipe Rack Key Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | 2007-03-01 | 2007-03-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0GEN-185701 | CHEMICAL DOSING SHELTER FOR HRSG - GROUND FLOOR PLAN, ROOF PLAN | PLAN | Heat Recovery Steam Generator | CHEMICAL DOSING | CHEMICAL DOSING SHELTER |  | Plan for HRSG |  | FA | 1PF3045W42A03P | (Chemical Dosing Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-07-24 | 2025-04-08 | 2025-05-08 | 2025-06-07 | 2025-06-22 | 2025-07-07 | 2025-07-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0GEN-185751 | CHEMICAL DOSING SHELTER FOR HRSG - GROUND FLOOR FRAMING PLAN | PLAN | Heat Recovery Steam Generator | CHEMICAL DOSING | CHEMICAL DOSING SHELTER |  | Plan for HRSG |  | FA | 1EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-01-23 | 2025-04-08 | 2025-05-08 | 2025-06-07 | 2025-06-22 | 2025-07-07 | 2025-07-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0GEN-185800 | CHEMICAL DOSING SHELTER FOR STG & HRSG - CALCULATION | CALCULATION | Steam Turbine & Generator & Heat Recovery Steam Generator | CHEMICAL DOSING | CHEMICAL DOSING SHELTER |  | Calculation sheet for Steam Turbine & Generator & Heat Recovery Steam Generator |  | FA | 1PF3045W42A03P | (Chemical Dosing Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-07-24 | 2025-03-09 | 2025-04-08 | 2025-05-08 | 2025-05-23 | 2025-06-07 | 2025-06-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0GEN-185801 | CHEMICAL DOSING SHELTER FOR STG & HRSG - GROUND FLOOR PLAN, ROOF PLAN | PLAN | Steam Turbine & Generator & Heat Recovery Steam Generator | CHEMICAL DOSING | CHEMICAL DOSING SHELTER |  | Plan for Steam Turbine & Generator & Heat Recovery Steam Generator |  | FA | 1PF3045W42A03P | (Chemical Dosing Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-07-24 | 2025-04-08 | 2025-05-08 | 2025-06-07 | 2025-06-22 | 2025-07-07 | 2025-07-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0GEN-185802 | CHEMICAL DOSING SHELTER FOR STG & HRSG - ELEVATION | ELEVATION | Steam Turbine & Generator & Heat Recovery Steam Generator | CHEMICAL DOSING | CHEMICAL DOSING SHELTER |  | Elevation Drawing for Steam Turbine & Generator & Heat Recovery Steam Generator |  | FA | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | 2024-09-13 | 2024-10-13 | 2024-11-12 | 2024-11-27 | 2024-12-12 | 2024-12-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0GEN-185803 | CHEMICAL DOSING SHELTER FOR STG & HRSG - MAIN SECTION | SECTION | Steam Turbine & Generator & Heat Recovery Steam Generator | CHEMICAL DOSING | CHEMICAL DOSING SHELTER |  | SECTION for Steam Turbine & Generator & Heat Recovery Steam Generator | STEAM TURBINE GENERATOR | FA | 1EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-01-23 |  |  |  | 2024-06-28 | 2024-07-28 | 2024-08-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0GEN-185851 | CHEMICAL DOSING SHELTER FOR STG & HRSG - GROUND FLOOR FRAMING PLAN | PLAN | Steam Turbine & Generator & Heat Recovery Steam Generator | CHEMICAL DOSING | CHEMICAL DOSING SHELTER |  | Plan for Steam Turbine & Generator & Heat Recovery Steam Generator |  | FA | 1EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-01-23 | 2025-04-08 | 2025-05-08 | 2025-06-07 | 2025-06-22 | 2025-07-07 | 2025-07-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0GEN-185852 | CHEMICAL DOSING SHELTER FOR STG & HRSG - GROUND FLOOR FRAMING PLAN, ROOF FRAMING PLAN | PLAN | Steam Turbine & Generator & Heat Recovery Steam Generator | CHEMICAL DOSING | CHEMICAL DOSING SHELTER |  | Plan for Steam Turbine & Generator & Heat Recovery Steam Generator |  | FA | 1EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-01-23 | 2025-04-08 | 2025-05-08 | 2025-06-07 | 2025-06-22 | 2025-07-07 | 2025-07-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0GEN-185853 | CHEMICAL DOSING SHELTER FOR STG & HRSG - FRAMING ELEVATION | ELEVATION | Steam Turbine & Generator & Heat Recovery Steam Generator | CHEMICAL DOSING | CHEMICAL DOSING SHELTER |  | Elevation Drawing for Steam Turbine & Generator & Heat Recovery Steam Generator |  | FA | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-04-02 | 2007-11-14 | 2024-09-13 | 2024-10-13 | 2024-11-12 | 2024-11-27 | 2024-12-12 | 2024-12-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0GEN-185854 | CHEMICAL DOSING SHELTER FOR STG & HRSG - REBAR DETAIL | DETAIL | Steam Turbine & Generator & Heat Recovery Steam Generator | CHEMICAL DOSING | CHEMICAL DOSING SHELTER |  | Detail Drawing for Steam Turbine & Generator & Heat Recovery Steam Generator | STEAM TURBINE GENERATOR | FA | 1EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-01-23 |  |  |  | 2024-06-28 | 2024-07-28 | 2024-08-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UBA-186100 | FGS ELECTRICAL BUILDING - CALCULATION | CALCULATION |  | Fuel Gas System | Fuel Gas System ELECTRICAL BUILDING |  | Calculation sheet for Fuel Gas System | Fuel Gas System | FA | 0CF3520W24A10.1 | (FGS LEB) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2008-05-31 | 2008-07-28 | 2025-10-19 | 2025-11-16 | 2025-12-14 | 2025-12-07 | 2026-01-04 | 2026-02-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-186101 | FGS ELECTRICAL BUILDING - GROUND FLOOR, ROOF PLAN & INTERIOR FINISH SCHEDULE(INCL. DOOR & WINDOW) | PLAN & INTERIOR FINISH SCHEDULE |  | Fuel Gas System | Fuel Gas System ELECTRICAL BUILDING |  | PLAN & INTERIOR FINISH SCHEDULE for Fuel Gas System |  | FA | 0CF3520W24A10.1 | (FGS LEB) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2008-05-31 | 2008-07-28 |  |  |  | 2025-03-03 | 2025-04-02 | 2025-05-02 | generated | 0.60 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-186103 | FGS ELECTRICAL BUILDING - SIDE WALL ELEVATION | ELEVATION |  | Fuel Gas System | Fuel Gas System ELECTRICAL BUILDING |  | Elevation Drawing for Fuel Gas System | Fuel Gas System | FA | 0CF3520W24A10.1 | (FGS LEB) Building Finish | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2008-05-31 | 2008-07-28 | 2025-09-21 | 2025-11-16 | 2026-01-11 | 2025-12-07 | 2026-02-01 | 2026-03-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-186104 | FGS ELECTRICAL BUILDING - MAIN SECTION | SECTION |  | Fuel Gas System | Fuel Gas System ELECTRICAL BUILDING |  | SECTION for Fuel Gas System | Fuel Gas System | FA | 0CF3520W74A08.1 | (FGS LEB) Installation & Test - Elec | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2008-01-11 | 2008-03-08 | 2025-01-25 | 2025-03-01 | 2025-04-05 | 2025-03-22 | 2025-04-26 | 2025-05-31 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-186151 | FGS ELECTRICAL BUILDING - FOUNDATION & COLUMN ARRANGEMENT PLAN | PLAN |  | Fuel Gas System | Fuel Gas System ELECTRICAL BUILDING |  | Plan for Fuel Gas System | Fuel Gas System | FA | 0EF3520W00A01.1 | (FGS LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-05-15 |  | 2024-05-29 | 2024-07-03 | 2024-08-07 | 2024-07-24 | 2024-08-28 | 2024-10-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-186152 | FGS ELECTRICAL BUILDING - GROUND FLOOR & ROOF FRAMING PLAN | PLAN |  |  | Fuel Gas System ELECTRICAL BUILDING |  | Plan for Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | FA | 2PF2010W20A04P | (STG #20 BLDG) P.O & Procurement - Structure Work(S/S) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | 2007-09-19 | 2008-01-31 | 2024-10-03 | 2024-11-07 | 2024-12-12 | 2024-11-28 | 2025-01-02 | 2025-02-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-186154 | FGS ELECTRICAL BUILDING - LINE & ROW FRAMING ELEVATION | ELEVATION |  |  | Fuel Gas System ELECTRICAL BUILDING |  | Elevation Drawing for Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | FA | 1PF1600W74A06P | (HRSG #11 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | 2007-09-15 | 2008-07-10 | 2024-12-08 | 2025-01-19 | 2025-03-02 | 2025-02-09 | 2025-03-23 | 2025-05-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-186155 | FGS ELECTRICAL BUILDING - FOUNDATION, SLAB & MISC. DETAIL RE - BAR DETAIL | DETAIL |  |  | Fuel Gas System ELECTRICAL BUILDING |  | Detail Drawing for Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | FA | 0CF3520W16A03.1 | (FGS LEB) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Fuel Gas Supply System LEB | 2007-09-14 | 2007-11-10 | 2024-12-07 | 2025-01-18 | 2025-03-01 | 2025-02-08 | 2025-03-22 | 2025-05-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-186156 | FGS ELECTRICAL BUILDING - COLUMN, BEAM & GIRDER RE - BAR SCHEDULE | SCHEDULE |  |  | Fuel Gas System ELECTRICAL BUILDING |  | Schedule for Fuel Gas System ELECTRICAL BUILDING | Fuel Gas System | FA | 2PF1600W74A06P | (HRSG #21 LEB) P.O & Procurement - Elec | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | 2007-09-15 | 2008-08-01 | 2024-09-29 | 2024-11-03 | 2024-12-08 | 2024-11-24 | 2024-12-29 | 2025-02-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UGD-186600 | NAOCL DOSING SKID SHELTER - CALCULATION | CALCULATION |  |  | NAOCL DOSING SKID SHELTER |  | Calculation sheet for NAOCL DOSING SKID SHELTER |  | FI | 1EF3045W16A07 | (Chemical Dosing BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-01-23 |  |  |  | 2024-06-28 | 2024-07-28 | 2024-08-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-186601 | NAOCL DOSING SKID SHELTER - GROUND & ROOF FLOOR PLAN | PLAN |  |  | NAOCL DOSING SKID SHELTER |  | Plan for NAOCL DOSING SKID SHELTER |  | FI | 3EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > N2 Gas System | 2007-12-03 | 2008-03-03 |  |  |  | 2024-09-04 | 2024-10-04 | 2024-11-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UGD-186602 | NAOCL DOSING SKID SHELTER - ELEVATION & SECTION | ELEVATION & SECTION |  |  | NAOCL DOSING SKID SHELTER |  | ELEVATION & SECTION for NAOCL DOSING SKID SHELTER |  | FI | 1EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-01-23 |  |  |  | 2024-06-28 | 2024-07-28 | 2024-08-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UGD-186651 | NAOCL DOSING SKID SHELTER - FND, GROUND, ROOF FRAMING PLAN & FRAMING ELEVATION | ELEVATION |  |  | NAOCL DOSING SKID SHELTER |  | Elevation Drawing for NAOCL DOSING SKID SHELTER |  | FI | 1EF3045W16A07 | (Chemical Dosing BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-01-23 |  |  |  | 2024-06-28 | 2024-07-28 | 2024-08-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UGD-186652 | NAOCL DOSING SKID SHELTER - REBAR DETAIL | DETAIL |  |  | NAOCL DOSING SKID SHELTER |  | Detail Drawing for NAOCL DOSING SKID SHELTER |  | FI | 1EF3045W16A07 | (Chemical Dosing BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | 2007-09-26 | 2008-01-23 |  |  |  | 2024-06-28 | 2024-07-28 | 2024-08-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA06-P0UBA-186800 | AUX. LEB - CALCULATION | CALCULATION |  |  | Auxiliary Local Electrical Building |  | Calculation sheet for Auxiliary Local Electrical Building | Electrical Building | FI | 1EF2020W00A02 | (ST #10) ST Aux' Steam Consumption Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2007-03-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-186801 | AUX. LEB - GROUND FLOOR PLAN & ROOF PLAN | PLAN |  |  | Auxiliary Local Electrical Building |  | Plan for Auxiliary Local Electrical Building |  | FA | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 | 2025-04-25 | 2025-05-25 | 2025-06-24 | 2025-07-09 | 2025-07-24 | 2025-08-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-186802 | AUX. LEB - SIDE WALL ELEVATION | ELEVATION |  |  | Auxiliary Local Electrical Building |  | Elevation Drawing for Auxiliary Local Electrical Building | ST BUILDING | FI | 0EF4035W32A04 | (WWT LEB) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 |  |  |  | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA00-P0UBA-186803 | AUX. LEB - MAIN SECTION | SECTION |  |  | Auxiliary Local Electrical Building |  | SECTION for Auxiliary Local Electrical Building |  | FA | 0CF3520W38A06.4 | (FO LEB) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > Fuel Oil Supply System LEB | 2008-05-31 | 2008-07-28 | 2026-07-26 | 2026-08-25 | 2026-09-24 | 2026-10-09 | 2026-10-24 | 2026-11-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-186851 | AUX. LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | PLAN |  |  | Auxiliary Local Electrical Building |  | Plan for Auxiliary Local Electrical Building |  | FA | 0EF3520W00A01.4 | (FO LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > Fuel Oil Supply System LEB | 2007-05-01 |  | 2025-06-25 | 2025-07-25 | 2025-08-24 | 2025-09-08 | 2025-09-23 | 2025-10-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-186852 | AUX. LEB - GROUND FLOOR FRAMING PLAN & ROOF FRAMING PLAN | PLAN |  |  | Auxiliary Local Electrical Building |  | Plan for Auxiliary Local Electrical Building |  | FA | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 | 2025-04-25 | 2025-05-25 | 2025-06-24 | 2025-07-09 | 2025-07-24 | 2025-08-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA01-P0UBA-186853 | AUX. LEB - LINE & ROW FRAMING ELEVATION | ELEVATION |  |  | Auxiliary Local Electrical Building |  | Elevation Drawing for Auxiliary Local Electrical Building | ST BUILDING | FI | 1EF1200W16A02 | (GTG #11 LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 LEB | 2007-08-01 | 2007-11-27 |  |  |  | 2024-05-03 | 2024-06-02 | 2024-07-02 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-186854 | AUX. LEB - FOUNDATION, SLAB & MISC. DETAIL RE - BAR DETAIL | DETAIL |  |  | Auxiliary Local Electrical Building |  | Detail Drawing for Auxiliary Local Electrical Building |  | FA | 1CF1200W16A03 | (GTG #11 LEB) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 LEB | 2007-11-28 | 2008-01-24 | 2026-01-22 | 2026-02-21 | 2026-03-23 | 2026-04-07 | 2026-04-22 | 2026-05-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA02-P0UBA-186855 | AUX. LEB - COLUMN, BEAM & GIRDER RE - BAR SCHEDULE | SCHEDULE |  |  | Auxiliary Local Electrical Building |  | Schedule for Auxiliary Local Electrical Building |  | FA | 2CF1600W32A04 | (HRSG #21 LEB) Structure Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | 2008-03-31 | 2008-06-25 | 2026-05-26 | 2026-06-25 | 2026-07-25 | 2026-08-09 | 2026-08-24 | 2026-09-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA07-P0ZEN-189000 | DESIGN CRITERIA FOR CIVIL AND BUILDING STRUCTURES | DESIGN CRITERIA |  |  |  |  | DESIGN CRITERIA |  | FI | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-03-01 | 2024-03-15 | 2024-04-14 | 2024-04-29 | 2024-05-14 | 2024-05-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0HBD-189001 | YARD PLATFORM | PLATFORM |  |  |  |  | PLATFORM |  | FA | 1CF3520W58A01 | (Gas Supply System) Piping Work(Yard area) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Gas Supply System (GTG) | 2008-05-20 | 2008-07-19 |  |  |  | 2025-02-20 | 2025-03-22 | 2025-04-21 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-CA03-P0HBD-189002 | PEECC PLATFORM | [7 empty] | FA | 0EF1000W00A07 | P&ID | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-11-06 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-31 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-VL00-P0MPA-220001 | CIVIL - STG FOUNDATION - SHAPE UNIT P6 |  | Steam Turbine & Generator |  |  |  | for STG |  | FA | 1PF6500W70A07P | (STG #10 & UST Shelter) P.O & Procurement - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-06-29 | 2008-06-22 | 2025-01-02 | 2025-02-01 | 2025-03-03 | 2025-03-18 | 2025-04-02 | 2025-04-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VL00-P7MPA-220002 | CIVIL - STG FOUNDATION - SHAPE - UNIT P7 |  | Steam Turbine & Generator |  |  |  | for STG |  | FA | 1PF6500W70A07P | (STG #10 & UST Shelter) P.O & Procurement - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-06-29 | 2008-06-22 | 2025-01-02 | 2025-02-01 | 2025-03-03 | 2025-03-18 | 2025-04-02 | 2025-04-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UF00-P0MAA-220003 | ST FOUNDATION LOAD - PLAN | PLAN | Steam Turbine |  |  |  | Plan for STG |  | FA | 1CF2020W16A07 | (ST #10) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-11-02 | 2008-03-03 |  |  |  | 2024-08-04 | 2024-09-03 | 2024-10-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XM00-P0MAA-220015 | LAYDOWN PLAN - UNIT P6 & P7 | PLAN |  |  |  |  | Plan |  | FA | 0EF1000W00A02 | Plant Plot Plan | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-08-28 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CA07-P0MPA-220023 | STG FOUNDATION - DESIGN CRITERIA - UNIT P6 & P7 | DESIGN CRITERIA | Steam Turbine & Generator |  |  |  | DESIGN CRITERIA for STG |  | FA | 1EF6500W16A02 | (STG #10 & UST Shelter) FDN & Firewall Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 | 2025-06-03 | 2025-07-03 | 2025-08-02 | 2025-08-17 | 2025-09-01 | 2025-09-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P6MAA-220025 | P&I DIAGRAM STEAM TURBINE SYSTEM - UNIT P6 | P&I DIAGRAM |  | STEAM TURBINE SYSTEM |  |  | P&ID for STEAM TURBINE SYSTEM | Water Treatment System | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P7MAA-220026 | P&I DIAGRAM STEAM TURBINE SYSTEM - UNIT P7 | P&I DIAGRAM |  | STEAM TURBINE SYSTEM |  |  | P&ID for STEAM TURBINE SYSTEM | Water Treatment System | FA | 2EF2510W00A01 | (Steam System) P&ID | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | 2007-04-02 | 2007-11-14 | 2024-05-02 | 2024-06-01 | 2024-07-01 | 2024-07-16 | 2024-07-31 | 2024-08-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P6MAA-220027 | P&I DIAGRAM HPH - UNIT P6 | P&I DIAGRAM |  | HPH |  |  | P&ID for HPH |  | FA | 0EF3515W00A01 | (H2) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-03-01 | 2007-06-29 | 2024-08-12 | 2024-09-11 | 2024-10-11 | 2024-10-26 | 2024-11-10 | 2024-11-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P7MAA-220028 | P&I DIAGRAMS HPH - UNIT P7 | P&I DIAGRAMS |  | HPH |  |  | P&I DIAGRAMS for HPH |  | FA | 1PF1600W90A10P | (HRSG #11 LEB) P.O & Procurement - I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | 2007-09-15 | 2008-07-10 | 2024-12-11 | 2025-01-10 | 2025-02-09 | 2025-02-24 | 2025-03-11 | 2025-03-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P6MAA-220029 | P&I DIAGRAM LUBRICATION OIL - UNIT P6 | P&I DIAGRAM |  | LUBRICATION OIL |  |  | P&ID for LUBRICATION OIL |  | FA | 1EF3546W00A02 | (Clean & Dirty Oil System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean & Dirty Oil System | 2007-04-02 | 2007-10-31 | 2024-09-13 | 2024-10-13 | 2024-11-12 | 2024-11-27 | 2024-12-12 | 2024-12-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P7MAA-220030 | P&I DIAGRAM LUBRICATION OIL - UNIT P7 | P&I DIAGRAM |  | LUBRICATION OIL |  |  | P&ID for LUBRICATION OIL |  | FA | 1PF2030W42A04P | (Lube Oil Sys.) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Lube Oil System | 2007-07-31 | 2008-07-30 | 2025-01-11 | 2025-02-10 | 2025-03-12 | 2025-03-27 | 2025-04-11 | 2025-04-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-VE01-P6MAA-220047 | ALLOWABLE LOADINGS AND DISPLACEMENTS | [7 empty] | FA | 0EF3520W00A10.4 | (FO Unloading Station Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > Fuel Oil Unloading Station | 2007-07-02 |  |  |  |  | 2024-04-03 | 2024-05-03 | 2024-06-02 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-YR00-P6MAA-220073 | CONTROL SYSTEM ARCHITECTURE |  |  | control system |  |  | for control system |  | FI | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | 2024-12-19 | 2025-01-18 | 2025-02-17 | 2025-03-04 | 2025-03-19 | 2025-04-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG01-P6MAA-220089 | DETAIL DRAWINGS - PIPING, COMPONENTS AND BOM - UNIT P6 | DETAIL DRAWINGS |  | PIPING |  |  | DETAIL DRAWINGS for PIPING |  | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | 2025-01-26 | 2025-02-25 | 2025-03-27 | 2025-04-11 | 2025-04-26 | 2025-05-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG01-P7MAA-220090 | DETAIL DRAWINGS - PIPING, COMPONENTS AND BOM - UNIT P7 | DETAIL DRAWINGS |  | PIPING |  |  | DETAIL DRAWINGS for PIPING |  | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | 2025-01-26 | 2025-02-25 | 2025-03-27 | 2025-04-11 | 2025-04-26 | 2025-05-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XS01-P6MAA-220093 | CONTROL SYSTEM FUNCTIONS PHILOSOPHY | PHILOSOPHY |  | CONTROL SYSTEM |  |  | PHILOSOPHY for CONTROL SYSTEM | Fuel Gas System | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | 2024-10-24 | 2024-12-05 | 2025-01-16 | 2024-12-26 | 2025-02-06 | 2025-03-20 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL13-P6MAA-220095 | SIGNAL TRANSFER LIST BETWEEN TCS AND DCS (HW) | LIST | TCS | DCS |  |  | LIST for TCS |  | FA | 0SF7000W62A09 | (DCS) Electrical signal Test for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2008-07-24 | 2008-07-28 | 2026-01-05 | 2026-02-04 | 2026-03-06 | 2026-03-21 | 2026-04-05 | 2026-04-20 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF00-P6MAA-220097 | LOGIC DIAGRAMS FOR ST | LOGIC DIAGRAMS | Steam Turbine |  |  |  | LOGIC DIAGRAMS for STG |  | FA | 1PF2020W42A10P | (ST #10) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2008-09-01 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YL13-P6MAA-220143 | SIGNAL TRANSFER LIST BETWEEN TCS AND DCS (SW) - UNIT 1+2 | LIST | TCS | DCS |  |  | LIST for TCS |  | FA | 0SF7000W62A09 | (DCS) Electrical signal Test for Power Receiving | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2008-07-24 | 2008-07-28 | 2026-01-05 | 2026-02-04 | 2026-03-06 | 2026-03-21 | 2026-04-05 | 2026-04-20 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CM01-P6MAA-220205 | DRAWINGS, PART LISTS OF TURBINE – UNIT P6 | DRAWINGS, PART LISTS |  |  |  |  | DRAWINGS, PART LISTS |  | FA | 1EF6500W32A04 | (STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 |  |  |  | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-CM01-P7MAA-220206 | DRAWINGS, PART LISTS OF TURBINE – UNIT P7 | DRAWINGS, PART LISTS |  |  |  |  | DRAWINGS, PART LISTS |  | FA | 1EF6500W32A04 | (STG #10 & UST Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 | 2008-03-10 |  |  |  | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-YL08-P6MAA-220207 | TRIPS & ALARMS SETTINGS UNIT P6+P7 | [7 empty] | FA | 2CF6500W38A14 | (GTG #21 & UAT Shelter) Installation & Test - Fire Fighting Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2008-05-31 | 2008-07-16 |  |  |  | 2025-03-03 | 2025-04-02 | 2025-05-02 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-YF02-P6CJJ-220275 | CONTROL SYSTEM HARDWARE SPECIFICATION – UNIT P6 | SPECIFICATION |  | control system |  |  | Technical Specification for control system |  | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | 2024-11-11 | 2024-12-11 | 2025-01-10 | 2025-01-25 | 2025-02-09 | 2025-02-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YF02-P7CJJ-220276 | CONTROL SYSTEM HARDWARE SPECIFICATION – UNIT P7 | SPECIFICATION |  | control system |  |  | Technical Specification for control system |  | FA | 0PF7000W86A05P | (DCS) P.O & Procurement for Combined power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > DCS | 2007-08-01 | 2008-10-31 | 2024-11-11 | 2024-12-11 | 2025-01-10 | 2025-01-25 | 2025-02-09 | 2025-02-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YV02-P6CJJ-220277 | HMI DESIGN – UNIT P6 | [7 empty] | FA | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-YV02-P7CJJ-220278 | HMI DESIGN – UNIT P7 | [7 empty] | FA | 2EF6500W00A09 | (GTG #21 & UAT Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 |  |  |  |  | 2024-03-02 | 2024-04-01 | 2024-05-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-YT02-P6CJJ-220293 | INSTRUMENTATION DATA SHEETS - UNIT P6 | DATA SHEETS |  | INSTRUMENTATION |  |  | DATA SHEETS for INSTRUMENTATION |  | FA | 2EF2020W00A03 | (ST #20) Instrument, Service Air Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-03-01 | 2007-03-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-YT02-P7CJJ-220294 | INSTRUMENTATION DATA SHEETS - UNIT P7 | DATA SHEETS |  | INSTRUMENTATION |  |  | DATA SHEETS for INSTRUMENTATION |  | FA | 0EF5560W00A11 | (M&E WORKSHOP LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Mechanical & Electrical/I&C Workshop (MEWS) | 2007-12-05 |  |  |  |  | 2024-09-06 | 2024-10-06 | 2024-11-05 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P6MAA-220383 | ISOMETRIC DRAWINGS OF PIPELINES - SMALL BORE PIPING P6 | ISOMETRIC DRAWINGS |  | Piping |  |  | ISOMETRIC DRAWINGS for Piping |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2025-01-28 | 2025-02-27 | 2025-03-29 | 2025-04-13 | 2025-04-28 | 2025-05-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P7MAA-220384 | ISOMETRIC DRAWINGS OF PIPELINES - SMALL BORE PIPING P7 | ISOMETRIC DRAWINGS |  | Piping |  |  | ISOMETRIC DRAWINGS for Piping |  | FA | 0EF6020W00A04 | (BOP Piping) Piping Isometric Drawing | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-05-18 | 2008-01-31 | 2025-01-28 | 2025-02-27 | 2025-03-29 | 2025-04-13 | 2025-04-28 | 2025-05-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MAA-220801 | STEAM TURBINE OUTLINE DRAWING | Outline Drawing | Steam Turbine |  |  |  | Outline Drawing for STG |  | FA | 1PF2020W42A10P | (ST #10) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | 2007-03-01 | 2008-09-01 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB00-P6MKA-250001 | ST GENERATOR UNIT#P6 FOUNDATION ARRANGEMENT DRAWING | ARRANGEMENT DRAWING | Steam Turbine & Generator |  |  |  | General Arrangement Drawing for STG |  | FA | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | 2025-01-09 | 2025-02-08 | 2025-03-10 | 2025-03-25 | 2025-04-09 | 2025-04-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XB00-P7MKA-250002 | ST GENERATOR UNIT#P7 FOUNDATION ARRANGEMENT DRAWING | ARRANGEMENT DRAWING | Steam Turbine & Generator |  |  |  | General Arrangement Drawing for STG |  | FA | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  | 2025-01-09 | 2025-02-08 | 2025-03-10 | 2025-03-25 | 2025-04-09 | 2025-04-24 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UF00-P6MKA-250003 | ST GENERATOR FOUNDATION LOADING |  | Steam Turbine & Generator |  |  |  | for STG |  | FA | 1PF2040W42A02P | (STG #10) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > ST Generator | 2007-03-01 | 2008-09-01 | 2024-09-04 | 2024-10-04 | 2024-11-03 | 2024-11-18 | 2024-12-03 | 2024-12-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKA-250004 | GENERATOR PIPING CONNECTION |  | Generator | Piping |  |  | for Generator |  | FA | 1PF2510W58A08P | (Steam PIPING) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | 2007-10-01 | 2008-05-01 | 2025-01-27 | 2025-02-26 | 2025-03-28 | 2025-04-12 | 2025-04-27 | 2025-05-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKA-250005 | GENERATOR STATOR HANDLING AND SHIPPING DIMENSION |  | Generator |  |  |  | for Generator |  | FA | 1PF2040W42A02P | (STG #10) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > ST Generator | 2007-03-01 | 2008-09-01 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKA-250006 | HANDLING DIMENSION FOR GENERATOR ROTOR |  | Generator |  |  |  | for Generator |  | FA | 3PF1213W42A08P | (GEN #31) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | 2007-04-30 | 2008-03-31 | 2024-08-26 | 2024-09-25 | 2024-10-25 | 2024-11-09 | 2024-11-24 | 2024-12-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0MKA-250007 | BRUSH HOLDER RIGGING ASSEMBLY | ASSEMBLY |  |  |  |  | ASSEMBLY |  | FA | 3PF1615W64A10P | (HRSG #31 Damper) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | 2007-06-13 | 2008-05-01 | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P6MKA-250008 | ST GENERATOR UNIT HYDROGEN COOLER OUTLINE | OUTLINE | Steam Turbine & Generator |  |  |  | OUTLINE for STG |  | FA | 1PF6500W70A07P | (STG #10 & UST Shelter) P.O & Procurement - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-06-29 | 2008-06-22 | 2025-06-10 | 2025-07-10 | 2025-08-09 | 2025-08-24 | 2025-09-08 | 2025-09-23 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MKA-250009 | GENERATOR DATA SHEET | DATA SHEET | GENERATOR |  |  |  | Data Sheet for GENERATOR |  | FA | 0EF3530W00A01 | (BSDG) Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Blackstart Diesel Generator | 2007-03-01 | 2007-04-30 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UC02-P0MKA-250010 | GENERATOR ELECTRICAL CONNECTION OUTLINE WITH PACKAGE WIRING AND TERMINAL | OUTLINE | GENERATOR |  |  |  | OUTLINE for GENERATOR |  | FA | 3PF1255W70A01P | (GTG#31 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Electrical System | 2007-04-30 | 2008-05-28 | 2024-08-26 | 2024-09-25 | 2024-10-25 | 2024-11-09 | 2024-11-24 | 2024-12-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UC02-P6MKA-250011 | GENERATOR ELECTRICAL FOUNDATION CONDUITS LAYOUT (UNIT#P6) | LAYOUT | GENERATOR |  |  |  | Layout Drawing for GENERATOR | Substation | SKIP | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-UC02-P7MKA-250012 | GENERATOR ELECTRICAL FOUNDATION CONDUITS LAYOUT (UNIT#P7) | LAYOUT | GENERATOR |  |  |  | Layout Drawing for GENERATOR | Substation | SKIP | 0EF1000W00A06 | Control Room Layout | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-30 | 2007-07-03 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-UC02-P0MKA-250013 | CURRENT TRANSFORMER ASSEMBLY | ASSEMBLY | Current Transformer |  |  |  | ASSEMBLY for Current Transformer |  | FA | 1CF6500W70A06 | (GTG TR) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2008-05-31 | 2008-07-16 |  |  |  | 2025-03-03 | 2025-04-02 | 2025-05-02 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-UC02-P0MKA-250014 | STATOR WINDING DIAGRAM | DIAGRAM |  |  |  |  | Diagram |  | FA | 1PF2040W42A02P | (STG #10) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > ST Generator | 2007-03-01 | 2008-09-01 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-UC02-P0MKA-250015 | FIELD CLEARANCE DIAGRAM | DIAGRAM |  |  |  |  | Diagram |  | FA | 0PF6500W70A02.6P | (Electrical Protection Panel) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2007-08-30 | 2008-03-10 | 2024-10-25 | 2024-11-24 | 2024-12-24 | 2025-01-08 | 2025-01-23 | 2025-02-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKA-250016 | ST GENERATOR MECHANICAL OUTLINE | OUTLINE | Steam Turbine & Generator |  |  |  | OUTLINE for STG |  | FA | 1PF2040W42A02P | (STG #10) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > ST Generator | 2007-03-01 | 2008-09-01 | 2025-02-10 | 2025-03-12 | 2025-04-11 | 2025-04-26 | 2025-05-11 | 2025-05-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKA-250017 | STG SOLE PLATE LAYOUT | LAYOUT | Steam Turbine & Generator |  |  |  | Layout Drawing for STG | Substation | SKIP | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKA-250018 | STG FLOOR PLATE LAYOUT | LAYOUT | Steam Turbine & Generator |  |  |  | Layout Drawing for STG | Substation | SKIP | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | 2007-03-01 | [7 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-DM02-P0MKA-250019 | SUGGESTIONS FOR GROUTING STG WITH FLOWABLE GROUT |  | Steam Turbine & Generator |  |  |  | for STG |  | FA | 1PF2070W42A04P | (STG #10 Aux. Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Auxiliary Equipment | 2007-04-30 | 2008-07-31 | 2024-11-03 | 2024-12-03 | 2025-01-02 | 2025-01-17 | 2025-02-01 | 2025-02-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKA-250020 | ST GENERATOR TERMINAL BOX ASSEMBLY | ASSEMBLY | Steam Turbine & Generator |  |  |  | ASSEMBLY for STG |  | FA | 1PF2040W42A02P | (STG #10) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > ST Generator | 2007-03-01 | 2008-09-01 | 2024-09-04 | 2024-10-04 | 2024-11-03 | 2024-11-18 | 2024-12-03 | 2024-12-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DM02-P0MKA-250021 | ROTOR ASSEMBLY DISASSEMBLY NOTE | ASSEMBLY DISASSEMBLY NOTE |  |  |  |  | ASSEMBLY DISASSEMBLY NOTE |  | FA | 3CF1265W42A03.1 | (Turning Gear) Installation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Starting System(Turning Device) | 2008-06-14 | 2008-06-21 |  |  |  | 2025-03-17 | 2025-04-16 | 2025-05-16 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-UC02-P0MKA-250022 | ROTOR ASSEMBLY DISASSEMBLY DIAGRAM | ASSEMBLY DISASSEMBLY DIAGRAM |  |  |  |  | ASSEMBLY DISASSEMBLY DIAGRAM |  | FA | 1EF3546W00A02 | (Clean & Dirty Oil System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean & Dirty Oil System | 2007-04-02 | 2007-10-31 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-03 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKA-250023 | ST GENERATOR END SHIELD ASSY CE |  | Steam Turbine & Generator |  |  |  | for STG |  | FA | 1PF2040W42A02P | (STG #10) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > ST Generator | 2007-03-01 | 2008-09-01 | 2024-09-04 | 2024-10-04 | 2024-11-03 | 2024-11-18 | 2024-12-03 | 2024-12-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKA-250024 | ST GENERATOR END SHIELD ASSY TE |  | Steam Turbine & Generator |  |  |  | for STG |  | FA | 1PF2040W42A02P | (STG #10) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > ST Generator | 2007-03-01 | 2008-09-01 | 2024-09-04 | 2024-10-04 | 2024-11-03 | 2024-11-18 | 2024-12-03 | 2024-12-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKW-260001 | SEAL OIL DRAIN ENLARGEMENT OUTLINE | OUTLINE |  |  |  |  | OUTLINE |  | FA | 1PF1250W42A02.1P | (GEN Seal Oil Sys.) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG#11 Generator Seal Oil System | 2007-03-01 | 2008-01-30 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKW-260002 | BEARING OIL DRAIN ENLARGEMENT OUTLINE | OUTLINE |  |  |  |  | OUTLINE |  | FA | 3PF1250W42A06P | (Lube Oil System) P.O & Procurement_Lube oil functional Module | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Lube Oil System | 2007-04-30 | 2008-03-28 | 2024-08-26 | 2024-09-25 | 2024-10-25 | 2024-11-09 | 2024-11-24 | 2024-12-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P6MKA-260003 | ST GENERATOR UNIT#P6 AUX SYSTEM PIPING ISO | Isometric Drawing | Steam Turbine & Generator | AUX SYSTEM PIPING |  |  | Isometric Drawing for STG | Water Treatment System | FI | 1PF2070W42A04P | (STG #10 Aux. Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Auxiliary Equipment | 2007-04-30 | 2008-07-31 | 2024-09-27 | 2024-10-27 | 2024-11-26 | 2024-12-11 | 2024-12-26 | 2025-01-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P6MKA-260004 | ST GENERATOR UNIT#P6 AUX SYSTEM PIPING ARRANGEMENT | ARRANGEMENT | Steam Turbine & Generator | AUX SYSTEM PIPING |  |  | ARRANGEMENT for STG |  | FA | 1PF2070W42A04P | (STG #10 Aux. Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Auxiliary Equipment | 2007-04-30 | 2008-07-31 | 2024-11-03 | 2024-12-03 | 2025-01-02 | 2025-01-17 | 2025-02-01 | 2025-02-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XK00-P6MKA-260005 | ST GENERATOR UNIT#P6 AUX SYSTEM HANGER & SUPPORT |  | Steam Turbine | AUX SYSTEM |  |  | for STG |  | FA | 1PF2070W42A04P | (STG #10 Aux. Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Auxiliary Equipment | 2007-04-30 | 2008-07-31 | 2024-11-03 | 2024-12-03 | 2025-01-02 | 2025-01-17 | 2025-02-01 | 2025-02-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XJ00-P7MKA-260006 | ST GENERATOR UNIT#P7 AUX SYSTEM PIPING ISO | Isometric Drawing | Steam Turbine | AUX SYSTEM PIPING |  |  | Isometric Drawing for STG | Water Treatment System | FI | 1PF2070W42A04P | (STG #10 Aux. Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Auxiliary Equipment | 2007-04-30 | 2008-07-31 | 2024-09-27 | 2024-10-27 | 2024-11-26 | 2024-12-11 | 2024-12-26 | 2025-01-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XH01-P7MKA-260007 | ST GENERATOR UNIT#P7 AUX SYSTEM PIPING ARRANGEMENT | Arrangement | Steam Turbine | AUX SYSTEM PIPING |  |  | Arrangement for STG |  | FA | 1PF2070W42A04P | (STG #10 Aux. Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Auxiliary Equipment | 2007-04-30 | 2008-07-31 | 2024-11-03 | 2024-12-03 | 2025-01-02 | 2025-01-17 | 2025-02-01 | 2025-02-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XK00-P7MKA-260008 | ST GENERATOR UNIT#P7 AUX SYSTEM HANGER & SUPPORT |  | Steam Turbine | AUX SYSTEM |  |  | for STG |  | FA | 1PF2070W42A04P | (STG #10 Aux. Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Auxiliary Equipment | 2007-04-30 | 2008-07-31 | 2024-11-03 | 2024-12-03 | 2025-01-02 | 2025-01-17 | 2025-02-01 | 2025-02-16 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKW-260011 | H2 SEAL OIL UNIT OUTLINE | Outline Drawing |  |  |  |  | Outline Drawing |  | FA | 3PF1250W42A02.2P | (GEN Seal Oil Sys.) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Generator Seal Oil System | 2007-04-30 | 2008-03-31 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKW-260012 | FLOAT TRAP OUTLINE | Outline Drawing |  |  |  |  | Outline Drawing |  | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | 2024-10-12 | 2024-11-11 | 2024-12-11 | 2024-12-26 | 2025-01-10 | 2025-01-25 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKW-260013 | LIQUID LEVEL DETECTOR OUTLINE | Outline Drawing |  |  |  |  | Outline Drawing |  | FA | 0PF3520W42A02P | (FO Metering Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Metering System | 2007-06-29 | 2008-03-17 | 2024-07-27 | 2024-08-26 | 2024-09-25 | 2024-10-10 | 2024-10-25 | 2024-11-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKG-260014 | GAS CONTROL VALVE STATION OUTLINE | Outline Drawing |  | GAS CONTROL SYSTEM |  |  | Outline Drawing for GAS CONTROL SYSTEM |  | FI | 0PF7000W86A02P | (Control Valve) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > Control Valves | 2007-10-01 | 2008-08-15 | 2025-02-18 | 2025-03-20 | 2025-04-19 | 2025-05-04 | 2025-05-19 | 2025-06-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKG-260015 | H2 BOTTLE MANIFOLD OUTLINE | Outline Drawing |  |  |  |  | Outline Drawing |  | FA | 0EF3515W00A01 | (H2) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-03-01 | 2007-06-29 | 2024-03-29 | 2024-04-28 | 2024-05-28 | 2024-06-12 | 2024-06-27 | 2024-07-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKG-260016 | CO2 BOTTLE MANIFOLD OUTLINE | Outline Drawing |  |  |  |  | Outline Drawing |  | FA | 3PF1265W38A01P | (F/F GTG#31) P.O & Procurement_CO2 FF System | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fire fighting System | 2007-04-30 | 2008-05-13 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKG-260017 | H2 CONTROL CABINET OUTLINE | Outline Drawing |  |  |  |  | Outline Drawing |  | FA | 2PF1265W42A12P | (Control Oil) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Auxiliary System | 2007-03-30 | 2008-02-29 | 2024-04-27 | 2024-05-27 | 2024-06-26 | 2024-07-11 | 2024-07-26 | 2024-08-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YD00-P0MKG-260018 | H2 GAS DRYER OUTLINE | Outline Drawing |  |  |  |  | Outline Drawing |  | FA | 1PF3520W42A07.2P | (Gas HTR) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Heater | 2007-07-03 | 2008-04-01 | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MKA-260019 | GENERATOR AUX SYSTEM MOTOR & PUMP DATA SHEET | DATA SHEET | GENERATOR | AUX SYSTEM |  |  | Data Sheet for GENERATOR |  | FA | 3EF2020W00A02 | (ST #30) ST Aux' Steam Consumption Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Steam Turbine | 2007-03-01 | 2007-03-29 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT01-P0MKA-260020 | GENERATOR AUX SYSTEM INSTRUMENT DATA SHEET | DATA SHEET | GENERATOR | AUX SYSTEM |  |  | Data Sheet for GENERATOR |  | FA | 1EF1200W00A02 | (GTG #11/#12) Instrument, Service Air, Aux steam Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-03-29 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YV02-P0MKW-260021 | H2 SEAL OIL SYSTEM - WIRING DIAGRAMS | Wiring Drawing |  | H2 SEAL OIL SYSTEM |  |  | Wiring Drawing for H2 SEAL OIL SYSTEM |  | FA | 1PF1250W42A02.3P | (GEN Seal Oil Sys.) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Generator Seal Oil System | 2007-03-01 | 2008-01-31 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YV02-P0MKG-260022 | GAS CONTROL SYSTEM - WIRING DIAGRAMS | Wiring Drawing |  | GAS CONTROL SYSTEM |  |  | Wiring Drawing for GAS CONTROL SYSTEM |  | FI | 3PF1265W42A12P | (Control Oil) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Auxiliary System | 2007-04-30 | 2008-03-31 | 2024-09-17 | 2024-10-17 | 2024-11-16 | 2024-12-01 | 2024-12-16 | 2024-12-31 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CY03-P0MKW-260031 | H2 SEAL OIL SYSTEM - SYSTEM DESCRIPTION | Description |  | H2 SEAL OIL SYSTEM |  |  | Description for H2 SEAL OIL SYSTEM | H2, CO2 Supply System | FA | 2PF1250W42A02.3P | (GEN Seal Oil Sys.) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Generator Seal Oil System | 2007-03-30 | 2008-02-29 | 2024-05-29 | 2024-06-28 | 2024-07-28 | 2024-08-12 | 2024-08-27 | 2024-09-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CY03-P0MKG-260032 | GAS CONTROL SYSTEM - SYSTEM DESCRIPTION | Description |  | GAS CONTROL SYSTEM |  |  | Description for GAS CONTROL SYSTEM | Fuel Gas System | FA | 1PF1265W42A12.8P | (Control Oil) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Auxiliary System | 2007-03-01 | 2008-01-31 | 2024-03-15 | 2024-04-19 | 2024-05-24 | 2024-05-10 | 2024-06-14 | 2024-07-19 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0MKW-260033 | H2 SEAL OIL SYTSEM P&ID | Piping & Instrumentation Drawing |  | H2 SEAL OIL SYTSEM |  |  | P&ID for H2 SEAL OIL SYTSEM |  | FA | 1PF1250W42A02.3P | (GEN Seal Oil Sys.) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Generator Seal Oil System | 2007-03-01 | 2008-01-31 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XG02-P0MKG-260034 | GAS CONTROL SYSTEM P&ID | Piping & Instrumentation Drawing |  | GAS CONTROL SYSTEM |  |  | P&ID for GAS CONTROL SYSTEM | Water Treatment System | FA | 3PF1265W42A12P | (Control Oil) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Auxiliary System | 2007-04-30 | 2008-03-31 | 2024-05-30 | 2024-06-29 | 2024-07-29 | 2024-08-13 | 2024-08-28 | 2024-09-12 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XL00-P0MKA-260035 | LINE LIST FOR ST GENERATOR | LINE LIST |  |  |  |  | LINE LIST |  | FA | 1PF2040W42A02P | (STG #10) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > ST Generator | 2007-03-01 | 2008-09-01 | 2024-07-28 | 2024-08-27 | 2024-09-26 | 2024-10-11 | 2024-10-26 | 2024-11-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-XN00-P0MKA-260036 | VALVE LIST FOR ST GENERATOR | VALVE LIST |  |  |  |  | VALVE LIST |  | FA | 0EF6020W00A05 | (BOP Piping) Valve List | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > System Engineering | 2007-04-30 | 2008-01-03 | 2024-07-23 | 2024-08-22 | 2024-09-21 | 2024-10-06 | 2024-10-21 | 2024-11-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS00-P0CJN-290001 | ELECTRICAL DIAGRAM STATIC EXCITATION SYSTEM FOR ST | DIAGRAM |  | STATIC EXCITATION SYSTEM |  |  | Diagram for STATIC EXCITATION SYSTEM | Substation | SKIP | 1CF1255W70A07.1 | (GTG#12 Electrical) Installation- SEE&SFC Sys. | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Electrical System | 2008-08-01 | 2008-09-15 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0CJN-290002 | EXCITER PANEL OUTLINE DRAWING FOR ST | OUTLINE DRAWING |  |  |  |  | Outline Drawing |  | FA | 0PF6500W70A02.6P | (Electrical Protection Panel) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2007-08-30 | 2008-03-10 | 2024-09-27 | 2024-10-27 | 2024-11-26 | 2024-12-11 | 2024-12-26 | 2025-01-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-BV02-P0CJN-290003 | PSS STUDY REPORT FOR ST | STUDY REPORT |  |  |  |  | STUDY REPORT |  | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | 2025-01-22 | 2025-02-21 | 2025-03-23 | 2025-04-07 | 2025-04-22 | 2025-05-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YR05-P0CJN-290004 | DRAWINGS OF EXCITATION TRANSFORMER FOR ST | DRAWINGS |  |  |  |  | DRAWINGS |  | FA | 0SF6500W62A05.1 | (Power Receiving) Back Charging of Transformer | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power Receiving | 2008-09-12 | 2008-09-12 |  |  |  | 2025-06-15 | 2025-07-15 | 2025-08-14 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-YE00-P0CJN-290005 | AC/DC POWER CABLE/RACEWAY LAYOUT | LAYOUT |  |  |  |  | Layout Drawing | Substation | SKIP | 0PF6040W74A03T | (Raceway) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Raceway System | 2008-02-01 | 2008-03-17 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YU02-P0MKY-290006 | SINGLE LINE DIAGRAMS INCLUDING GENERATOR CONTROL & PROTECTION | SINGLE LINE DIAGRAMS |  |  |  |  | SINGLE LINE DIAGRAMS |  | SKIP | 0EF1000W00A05 | Single Line Diagram | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-01 | 2007-10-12 | [6 empty] | skip |  | 6210
Fadhili_MDL.xlsx | T16182-YF00-P0MKY-290007 | LOGIC DIAGRAMS OF GENERATOR CONTROL PANEL FOR STG | LOGIC DIAGRAMS |  |  |  |  | LOGIC DIAGRAMS |  | FA | 1PF2040W42A02P | (STG #10) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > ST Generator | 2007-03-01 | 2008-09-01 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS01-P0MKY-290008 | SCHEMATIC DIAGRAMS FOR GENERATOR PROTECTION RELAY FOR STG | SCHEMATIC DIAGRAMS |  |  |  |  | SCHEMATIC DIAGRAMS |  | FA | 0PF6500W70A02.6P | (Electrical Protection Panel) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2007-08-30 | 2008-03-10 | 2024-10-25 | 2024-11-24 | 2024-12-24 | 2025-01-08 | 2025-01-23 | 2025-02-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS01-P0MKY-290009 | SCHEMATIC DIAGRAMS FOR GENERATOR CONTROL PANEL | SCHEMATIC DIAGRAMS |  |  |  |  | SCHEMATIC DIAGRAMS |  | FA | 0PF6500W70A02.6P | (Electrical Protection Panel) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2007-08-30 | 2008-03-10 | 2024-10-25 | 2024-11-24 | 2024-12-24 | 2025-01-08 | 2025-01-23 | 2025-02-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0MKY-290010 | PROTECTION RELAY SETTING DATA AND CALCULATION FOR STG | CALCULATION | Steam Turbine & Generator |  |  |  | Calculation sheet for STG |  | FI | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-11-28 |  |  |  |  | 2024-08-30 | 2024-09-29 | 2024-10-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS01-P0MKY-290011 | SCHEMATIC DIAGRAMS FOR EMERGENCY SEAL OIL DC MOTOR STARTER PANEL | SCHEMATIC DIAGRAMS |  |  |  |  | SCHEMATIC DIAGRAMS |  | FA | 1PF1250W42A02.3P | (GEN Seal Oil Sys.) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Generator Seal Oil System | 2007-03-01 | 2008-01-31 | 2024-04-26 | 2024-05-26 | 2024-06-25 | 2024-07-10 | 2024-07-25 | 2024-08-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS01-P0MKY-290012 | SCHEMATIC DIAGRAMS FOR NGR AND NGTR PANEL FOR STG | SCHEMATIC DIAGRAMS | Steam Turbine & Generator |  |  |  | SCHEMATIC DIAGRAMS for STG |  | FA | 1PF2070W42A04P | (STG #10 Aux. Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Auxiliary Equipment | 2007-04-30 | 2008-07-31 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YS01-P0MKY-290013 | SCHEMATIC DIAGRAMS FOR PT/SA PANEL FOR STG | SCHEMATIC DIAGRAMS | Steam Turbine & Generator |  |  |  | SCHEMATIC DIAGRAMS for STG |  | FA | 1PF2070W42A04P | (STG #10 Aux. Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Auxiliary Equipment | 2007-04-30 | 2008-07-31 | 2024-06-25 | 2024-07-25 | 2024-08-24 | 2024-09-08 | 2024-09-23 | 2024-10-08 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YR02-P0CJN-290014 | TECHNICAL SPECIFICATION OF EXCITATION SYSTEM FOR ST | TECHNICAL SPECIFICATION |  | EXCITATION SYSTEM |  |  | Technical Specification for EXCITATION SYSTEM |  | FA | 1PF6500W86A07P | (ST GCB) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Generator Circuit Breaker (GCB) | 2007-10-02 | 2008-07-30 | 2025-03-15 | 2025-04-14 | 2025-05-14 | 2025-05-29 | 2025-06-13 | 2025-06-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0LCP-410001 | OUTLINE DRAWING FOR CONDENSATE STORAGE TANK | OUTLINE DRAWING | Tank |  |  |  | Outline Drawing for Tank | shop Tank | FA | 0PF3520W68A04P | (Condensate Tank) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-06-15 | 2024-07-15 | 2024-08-14 | 2024-08-29 | 2024-09-13 | 2024-09-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0LCP-410002 | STRENGTH CALCULATION FOR CONDENSATE STORAGE TANK | STRENGTH CALCULATION | Tank |  |  |  | STRENGTH CALCULATION for Tank | shop Tank | FA | 0PF3520W68A04P | (Condensate Tank) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System | 2007-06-01 | 2008-01-30 | 2024-07-01 | 2024-07-31 | 2024-08-30 | 2024-09-14 | 2024-09-29 | 2024-10-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0GHC-410011 | OUTLINE DRAWING FOR DEMINERALIZED WATER STORAGE TANK | OUTLINE DRAWING | Tank |  |  |  | Outline Drawing for Tank | shop Tank | FA | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 | 2024-09-14 | 2024-10-14 | 2024-11-13 | 2024-11-28 | 2024-12-13 | 2024-12-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0GHC-410012 | STRENGTH CALCULATION FOR DEMINERALIZED WATER STORAGE TANK | STRENGTH CALCULATION | Tank |  |  |  | STRENGTH CALCULATION for Tank | shop Tank | FA | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0GKB-410021 | OUTLINE DRAWING FOR POTABLE & FIRE FIGHTING WATER STORAGE TANK | OUTLINE DRAWING | TANK |  |  |  | Outline Drawing for TANK | shop Tank | FA | 1PF3030W68A04P | (EXP Head Tank) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-09-03 | 2008-07-30 | 2024-09-17 | 2024-10-17 | 2024-11-16 | 2024-12-01 | 2024-12-16 | 2024-12-31 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0GKB-410022 | STRENGTH CALCULATION FOR POTABLE & FIRE FIGHTING WATER STORAGE TANK | STRENGTH CALCULATION | TANK |  |  |  | STRENGTH CALCULATION for TANK | shop Tank | FA | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK10-P0GKB-410031 | OUTLINE DRAWING FOR POTABLE WATER STORAGE TANK | OUTLINE DRAWING | TANK |  |  |  | Outline Drawing for TANK | shop Tank | FA | 0EF3010W00A01 | (DWP Chemical Storage Tank Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 |  | 2024-09-14 | 2024-10-14 | 2024-11-13 | 2024-11-28 | 2024-12-13 | 2024-12-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YT10-P0GKB-410032 | STRENGTH CALCULATION FOR POTABLE WATER STORAGE TANK | STRENGTH CALCULATION | TANK |  |  |  | STRENGTH CALCULATION for TANK | shop Tank | FA | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0PUR-411001 | CATHODIC PROTECTION SYSTEM TECHNICAL SPECIFICATION FOR CONDENSATE STORAGE TANK | TECHNICAL SPECIFICATION | Tank | Cathodic protection system |  |  | Technical Specification for Tank |  | FA | 0EF3520W68A03 | (Condensate Tank) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System > Condensate System |  | 2007-03-30 | [6 empty] | missing_date |  | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0PUR-411011 | CATHODIC PROTECTION SYSTEM TECHNICAL SPECIFICATION FOR DEMINERALIZED WATER STORAGE TANK | TECHNICAL SPECIFICATION | Tank | Cathodic protection system |  |  | Technical Specification for Tank |  | FA | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 | 2025-02-11 | 2025-03-13 | 2025-04-12 | 2025-04-27 | 2025-05-12 | 2025-05-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0PUR-411021 | CATHODIC PROTECTION SYSTEM TECHNICAL SPECIFICATION FOR POTABLE & FIRE FIGHTING WATER STORAGE TANK | TECHNICAL SPECIFICATION | TANK | Cathodic protection system |  |  | Technical Specification for TANK |  | FA | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 | 2025-02-11 | 2025-03-13 | 2025-04-12 | 2025-04-27 | 2025-05-12 | 2025-05-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-CV03-P0PUR-411031 | CATHODIC PROTECTION SYSTEM TECHNICAL SPECIFICATION FOR POTABLE WATER STORAGE TANK | TECHNICAL SPECIFICATION | TANK | Cathodic protection system |  |  | Technical Specification for TANK |  | FA | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 | 2025-02-11 | 2025-03-13 | 2025-04-12 | 2025-04-27 | 2025-05-12 | 2025-05-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0PGB-420010 | OUTLINE DRAWING FOR CCW EXPANSION HEAD TANK | OUTLINE DRAWING | Tank |  |  |  | Outline Drawing for Tank | shop Tank | FA | 1PF3030W68A04P | (EXP Head Tank) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-09-03 | 2008-07-30 | 2024-09-17 | 2024-10-17 | 2024-11-16 | 2024-12-01 | 2024-12-16 | 2024-12-31 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0PGB-420020 | OUTLINE DRAWING FOR CCW CHEMICAL ADDITIVE TANK | OUTLINE DRAWING | Tank |  |  |  | Outline Drawing for Tank | shop Tank | FA | 0EF3010W32A04 | (DWP Chemical Storage Tank Shelter) Structure Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-08-31 | 2007-12-27 | 2024-09-14 | 2024-10-14 | 2024-11-13 | 2024-11-28 | 2024-12-13 | 2024-12-28 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0LCM-420030 | OUTLINE DRAWING FOR ATMOSPHERIC FLASH TANK | OUTLINE DRAWING | flash Tank |  |  |  | Outline Drawing for flash Tank |  | FA | 1PF3020W42A12P | (COND Flash Box) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-07-01 | 2025-04-20 | 2025-05-20 | 2025-06-19 | 2025-07-04 | 2025-07-19 | 2025-08-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0LCM-420040 | OUTLINE DRAWING FOR VACUUM FLASH TANK | OUTLINE DRAWING | flash Tank |  |  |  | Outline Drawing for flash Tank |  | FA | 1PF3020W42A12P | (COND Flash Box) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-07-01 | 2025-04-20 | 2025-05-20 | 2025-06-19 | 2025-07-04 | 2025-07-19 | 2025-08-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0GKC-420050 | OUTLINE DRAWING FOR CHILLED WATER STORAGE TANK | OUTLINE DRAWING | TANK |  |  |  | Outline Drawing for TANK | shop Tank | FA | 1PF3030W68A04P | (EXP Head Tank) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-09-03 | 2008-07-30 | 2024-09-17 | 2024-10-17 | 2024-11-16 | 2024-12-01 | 2024-12-16 | 2024-12-31 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-YK08-P0GKC-420051 | INSULATION DETAIL DRAWING FOR CHILLED WATER STORAGE TANK | DRAWING | TANK |  |  |  | DRAWING for TANK | shop Tank | FA | 1PF3030W68A04P | (EXP Head Tank) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2007-09-03 | 2008-07-30 | 2024-09-17 | 2024-10-17 | 2024-11-16 | 2024-12-01 | 2024-12-16 | 2024-12-31 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755001 | SAT Procedure for Isolated Phase Busbar (IPB) | SAT Procedure | Isolated Phase Busbar |  |  |  | SAT Procedure for Isolated Phase Busbar | Isolated Phase Bus | FI | 1PF6500W74A03T | (IPB) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2008-05-02 | 2008-06-16 | 2025-01-24 | 2025-02-23 | 2025-03-25 | 2025-04-09 | 2025-04-24 | 2025-05-09 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755002 | SAT Procedure for GSUT | SAT Procedure | Generator Step-Up Transformer |  |  |  | SAT Procedure for Generator Step-Up Transformer | Transformer | FI | 1PF6500W70A08T | (STG #10 & UST Shelter) Transportation - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2008-06-23 | 2008-08-06 | 2025-03-16 | 2025-04-15 | 2025-05-15 | 2025-05-30 | 2025-06-14 | 2025-06-29 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755003 | SAT Procedure for 380kv EHV Cable and Accessories | SAT Procedure |  |  |  |  | SAT Procedure |  | FA | 1PF6040W74A06P | (EHV Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2008-02-29 | 2025-08-01 | 2025-08-22 | 2025-09-12 | 2025-10-06 | 2025-10-21 | 2025-11-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755004 | SAT Procedure for Non Segregated Phase Busduct (NSPBD) | SAT Procedure | Non Segregated Phase Bus Duct |  |  |  | SAT Procedure for Non Segregated Phase Bus Duct |  | FA | 1PF6500W74A02P | (IPB) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | 2007-08-02 | 2008-05-01 | 2025-08-01 | 2025-08-22 | 2025-09-12 | 2025-10-06 | 2025-10-21 | 2025-11-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755005 | SAT Procedure for Unit Auxillary Transformer (UAT) | SAT Procedure | UNIT AUXILIARY TRANSFORMER |  |  |  | SAT Procedure for UNIT AUXILIARY TRANSFORMER |  | FA | 2PF6500W70A04.1P | (GTG UAT) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-03-30 | 2008-04-16 | 2025-03-29 | 2025-04-19 | 2025-05-10 | 2025-06-03 | 2025-06-18 | 2025-07-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755006 | SAT Procedure for Protection Relay Panel, GSUT HV Side Energy Metering Panel | SAT Procedure |  |  |  |  | SAT Procedure |  | FA | 0PF6500W70A02.6P | (Electrical Protection Panel) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2007-08-30 | 2008-03-10 | 2025-08-29 | 2025-09-19 | 2025-10-10 | 2025-11-03 | 2025-11-18 | 2025-12-03 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755007 | SAT Procedure for AC-UPS System | SAT Procedure |  | AC-UPS System |  |  | SAT Procedure for AC-UPS System |  | FA | 0PF6500W70A02.4P | (DC & UPS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > DC & UPS System | 2007-08-08 | 2008-03-06 | 2025-08-07 | 2025-08-28 | 2025-09-18 | 2025-10-12 | 2025-10-27 | 2025-11-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755008 | SAT Procedure for DC Battery Charger System | SAT Procedure |  | DC Battery Charger System |  |  | SAT Procedure for DC Battery Charger System |  | FA | 0PF6500W70A02.5P | (Battery) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Batteries | 2007-09-18 | 2008-04-18 | 2025-09-17 | 2025-10-08 | 2025-10-29 | 2025-11-22 | 2025-12-07 | 2025-12-22 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755009 | SAT Procedure for Generator Circuit Breaker (GCB) | SAT Procedure | Generator Circuit Breaker (GCB) |  |  |  | SAT Procedure for Generator Circuit Breaker (GCB) | GENERATOR CIRCUIT BREAKER | FI | 1PF6500W86A03T | (GT GCB) Transportation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Generator Circuit Breaker (GCB) | 2008-04-01 | 2008-05-15 | 2024-12-23 | 2025-01-22 | 2025-02-21 | 2025-03-08 | 2025-03-23 | 2025-04-07 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755010 | SAT Procedure for LV Cable | SAT Procedure | LV Cable |  |  |  | SAT Procedure for LV Cable |  | FA | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2007-07-03 | 2008-03-31 | 2025-07-02 | 2025-07-23 | 2025-08-13 | 2025-09-06 | 2025-09-21 | 2025-10-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755011 | SAT Procedure for MV Cable | SAT Procedure | MV Cable |  |  |  | SAT Procedure for MV Cable |  | FA | 1PF6040W74A06P | (EHV Cable) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Extra High Voltage Cable | 2007-08-02 | 2008-02-29 | 2025-08-01 | 2025-08-22 | 2025-09-12 | 2025-10-06 | 2025-10-21 | 2025-11-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755012 | SAT Procedure for 480V Motor Control Center | SAT Procedure | 480V Motor Control Center |  |  |  | SAT Procedure for 480V Motor Control Center |  | FA | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2007-07-03 | 2008-03-31 | 2025-01-12 | 2025-02-11 | 2025-03-13 | 2025-03-28 | 2025-04-12 | 2025-04-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755013 | SAT Procedure for 13.8 kV MV Switch Gear | SAT Procedure | 13.8 kV MV Switch Gear |  |  |  | SAT Procedure for 13.8 kV MV Switch Gear |  | FA | 0PF6500W70A02.2P | (MV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > MV Switchgears With Auxiliaries | 2007-07-03 | 2008-03-31 | 2025-07-02 | 2025-07-23 | 2025-08-13 | 2025-09-06 | 2025-09-21 | 2025-10-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755014 | SAT Procedure for LV Switchgear | SAT Procedure | LV Switchgear |  |  |  | SAT Procedure for LV Switchgear |  | FA | 0PF6500W70A02.3P | (LV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > LV Switchgears & MCC With Auxiliaries | 2007-07-03 | 2008-03-31 | 2025-07-02 | 2025-07-23 | 2025-08-13 | 2025-09-06 | 2025-09-21 | 2025-10-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755015 | SAT Procedure for Lighting Distribution Board (LDB) | SAT Procedure |  |  |  |  | SAT Procedure |  | FA | 0PF6040W70A02P | (Lighting Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Lighting System | 2007-08-01 | 2008-02-27 | 2025-07-31 | 2025-08-21 | 2025-09-11 | 2025-10-05 | 2025-10-20 | 2025-11-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755016 | SAT Procedure for Mold / Dry Transformer | SAT Procedure |  |  |  |  | SAT Procedure |  | FA | 1PF6500W70A04P | (GTG TR) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-04-02 | 2008-04-15 | 2025-04-01 | 2025-04-22 | 2025-05-13 | 2025-06-06 | 2025-06-21 | 2025-07-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755017 | SAT Procedure for MV & LV Motors | SAT Procedure |  |  |  |  | SAT Procedure |  | FA | 0PF6500W70A02.2P | (MV SWGR) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > MV Switchgears With Auxiliaries | 2007-07-03 | 2008-03-31 | 2025-07-02 | 2025-07-23 | 2025-08-13 | 2025-09-06 | 2025-09-21 | 2025-10-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755019 | SAT Procedure for STG Excitation Transformer (Oil Type) | SAT Procedure |  |  |  |  | SAT Procedure |  | FA | 3PF6500W70A12P | (STG TR) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Power Transformer | 2007-08-02 | 2008-09-30 | 2025-08-01 | 2025-08-22 | 2025-09-12 | 2025-10-06 | 2025-10-21 | 2025-11-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755020 | SAT Procedure for Neutral Grounding Transformer (NGTR) Neutral Grounding Resistor (NGR) | SAT Procedure |  |  |  |  | SAT Procedure |  | FA | 1PF6500W70A04P | (GTG TR) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Power Transformer | 2007-04-02 | 2008-04-15 | 2025-04-01 | 2025-04-22 | 2025-05-13 | 2025-06-06 | 2025-06-21 | 2025-07-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755021 | SAT Procedure for Ground, Step & touch Voltage | SAT Procedure |  |  |  |  | SAT Procedure |  | FA | 0PF5544W70A02P | (GIS Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 | 2008-01-29 | 2025-02-28 | 2025-03-21 | 2025-04-11 | 2025-05-05 | 2025-05-20 | 2025-06-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755022 | Site Acceptance Test Procedure for Generator & Exc. TR Protection Relay, Control Panel | Site Acceptance Test Procedure |  |  |  |  | Site Acceptance Test Procedure |  | FA | 0SF6500W62A05.6 | (Electrical Protection Panel) Function Test | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2008-05-27 | 2008-06-05 |  |  |  | 2025-02-27 | 2025-03-29 | 2025-04-28 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-DD09-P0ZEN-755023 | Site Acceptance Test Procedure for HCIS Security System | Site Acceptance Test Procedure |  | HCIS Security System |  |  | Site Acceptance Test Procedure for HCIS Security System |  | FA | 1SF3030W62A25 | (CCWS) System Function Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | 2008-10-24 | 2008-10-28 |  |  |  | 2025-07-27 | 2025-08-26 | 2025-09-25 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-DN05-P8MB-810006 | GAS TURBINE FUEL CHANGE-OVER TEST | TEST |  |  |  |  | TEST |  | FA | 1SF9012W62A13 | (GTG #11) Fuel Change-Over Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Commissioning | 2008-11-27 | 2008-11-27 | 2025-12-26 | 2026-01-25 | 2026-02-24 | 2026-03-11 | 2026-03-26 | 2026-04-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DN05-P8ZEN-810030 | PLANT EMERGENCY FUEL CHANGE-OVER TEST | TEST |  |  |  |  | TEST |  | FA | 1SF3520W62A24 | (GPRS #11 for Fuel Change over) Function Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | 2008-06-30 | 2008-07-01 | 2025-07-29 | 2025-08-28 | 2025-09-27 | 2025-10-12 | 2025-10-27 | 2025-11-11 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860001 | GT LOAD REJECTION TEST | TEST |  |  |  |  | TEST |  | FA | 3PF1213W42A03.1P | (GT #32) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Main body | 2007-04-30 | 2008-04-29 | 2024-05-28 | 2024-06-27 | 2024-07-27 | 2024-08-11 | 2024-08-26 | 2024-09-10 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860002 | TRIAL RUN TEST OF THE PLANT | TRIAL RUN TEST |  |  |  |  | TRIAL RUN TEST |  | FA | 1SF9040W62A12 | (Comm'g) Trial Run Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | 2009-07-19 | 2009-07-20 |  |  |  | 2026-04-21 | 2026-05-21 | 2026-06-20 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860003 | ST LOAD REJECTION TEST | Test |  |  |  |  | Test | FireFighting | FA | 0SF3035W62A13.1 | (PWS) Load Test | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2009-01-20 | 2009-01-24 | 2026-02-11 | 2026-03-14 | 2026-04-15 | 2026-04-04 | 2026-05-05 | 2026-06-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860004 | ACTIVE POWER RESPONSE AND VOLTAGE CONTROL RESPONSE TEST | Test |  |  |  |  | Test | FireFighting | FA | 0PF7000W86A02P | (Control Valve) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > Control Valves | 2007-10-01 | 2008-08-15 | 2024-10-22 | 2024-11-22 | 2024-12-24 | 2024-12-13 | 2025-01-13 | 2025-02-14 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860006 | ISLAND MODE TEST | Test |  |  |  |  | Test | FireFighting | FA | 0PF3040W42A04P | (Lab) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Laboratory | 2008-03-31 | 2008-10-20 | 2025-04-22 | 2025-05-23 | 2025-06-24 | 2025-06-13 | 2025-07-14 | 2025-08-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860007 | LOAD SWING TEST | Test |  |  |  |  | Test | FireFighting | FA | 0SF3035W62A13.0 | (SWS) Load Test | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Service Water System | 2009-01-10 | 2009-01-11 | 2026-02-01 | 2026-03-04 | 2026-04-05 | 2026-03-25 | 2026-04-25 | 2026-05-27 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860008 | LDC Integration | [7 empty] | FA | 0EF1000W00A09 | DCS I/O List of Overall Plant | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-04-30 | 2007-12-31 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-31 | generated | 0.30 | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860009 | STARTUP TIME TEST (COLD/WARM/HOT) | Test |  |  |  |  | Test | FireFighting | FA | 0PF3040W42A04P | (Lab) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Laboratory | 2008-03-31 | 2008-10-20 | 2025-04-22 | 2025-05-23 | 2025-06-24 | 2025-06-13 | 2025-07-14 | 2025-08-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860010 | MINIMUM LOAD TEST | Test |  |  |  |  | Test | FireFighting | FA | 0SF3035W62A13.1 | (PWS) Load Test | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Potable Water System | 2009-01-20 | 2009-01-24 | 2026-02-11 | 2026-03-14 | 2026-04-15 | 2026-04-04 | 2026-05-05 | 2026-06-06 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860011 | AGC |  |  | AGC |  |  | for AGC |  | FA | 0PF3040W42A04P | (Lab) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Laboratory | 2008-03-31 | 2008-10-20 | 2026-06-22 | 2026-07-22 | 2026-08-21 | 2026-09-05 | 2026-09-20 | 2026-10-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860012 | PERFORMANCE TEST PROCEDURE FOR THERMAL PERFORMANCE | PERFORMANCE TEST PROCEDURE |  |  |  |  | PERFORMANCE TEST PROCEDURE | FireFighting | FA | 1SF9042W62A15 | (Comm'g) Performance Test (Fuel Gas & Fuel Oil) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | 2009-08-20 | 2009-08-31 | 2026-09-11 | 2026-10-12 | 2026-11-13 | 2026-11-02 | 2026-12-03 | 2027-01-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860013 | RELIABILITY TEST | Test |  |  |  |  | Test | FireFighting | FA | 1SF9041W62A14 | (Comm'g) Reliability Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | 2009-07-21 | 2009-08-19 | 2026-08-12 | 2026-09-12 | 2026-10-14 | 2026-10-03 | 2026-11-03 | 2026-12-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860014 | NET DEPENDABLE CAPACITY TEST | Test |  |  |  |  | Test | FireFighting | FA | 0PF3040W42A04P | (Lab) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Laboratory | 2008-03-31 | 2008-10-20 | 2025-04-22 | 2025-05-23 | 2025-06-24 | 2025-06-13 | 2025-07-14 | 2025-08-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860015 | REACTIVE POWER TEST | Test |  |  |  |  | Test | FireFighting | FA | 0PF6500W70A02.7P | (Power Metering Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power Metering System | 2007-07-13 | 2008-02-12 | 2024-08-03 | 2024-09-03 | 2024-10-05 | 2024-09-24 | 2024-10-25 | 2024-11-26 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860016 | PRIMARY RESPONSE TEST | Test |  |  |  |  | Test | FireFighting | FA | 0PF3040W42A04P | (Lab) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Laboratory | 2008-03-31 | 2008-10-20 | 2025-04-22 | 2025-05-23 | 2025-06-24 | 2025-06-13 | 2025-07-14 | 2025-08-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860017 | BLACK START-UP TEST | Test |  |  |  |  | Test | FireFighting | FA | 1SF9012W62A09 | (GTG #11) Black start Test with GT | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Commissioning | 2008-10-31 | 2008-10-31 | 2025-11-22 | 2025-12-23 | 2026-01-24 | 2026-01-13 | 2026-02-13 | 2026-03-17 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860018 | PSS TEST | Test |  |  |  |  | Test | FireFighting | FA | 0PF3040W42A04P | (Lab) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > Laboratory | 2008-03-31 | 2008-10-20 | 2025-04-22 | 2025-05-23 | 2025-06-24 | 2025-06-13 | 2025-07-14 | 2025-08-15 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860019 | RESERVE BOILER THERMAL PERFORMANCE TEST PROCEDURE | TEST PROCEDURE | RESERVE BOILER |  |  |  | TEST PROCEDURE for RESERVE BOILER | FireFighting | FA | 1SF9042W62A15 | (Comm'g) Performance Test (Fuel Gas & Fuel Oil) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | 2009-08-20 | 2009-08-31 | 2026-09-11 | 2026-10-12 | 2026-11-13 | 2026-11-02 | 2026-12-03 | 2027-01-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860020 | PERFORMANCE TEST PROCEDURE FOR NOISE EMISSION | PERFORMANCE TEST PROCEDURE |  |  |  |  | PERFORMANCE TEST PROCEDURE | FireFighting | FA | 1SF9042W62A15 | (Comm'g) Performance Test (Fuel Gas & Fuel Oil) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | 2009-08-20 | 2009-08-31 | 2026-09-11 | 2026-10-12 | 2026-11-13 | 2026-11-02 | 2026-12-03 | 2027-01-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860021 | PERFORMANCE TEST PROCEDURE FOR AIR EMISSION | PERFORMANCE TEST PROCEDURE |  |  |  |  | PERFORMANCE TEST PROCEDURE | FireFighting | FA | 1SF9042W62A15 | (Comm'g) Performance Test (Fuel Gas & Fuel Oil) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | 2009-08-20 | 2009-08-31 | 2026-09-11 | 2026-10-12 | 2026-11-13 | 2026-11-02 | 2026-12-03 | 2027-01-04 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860022 | SUPPLEMENTARY FIRING FOR HRSG |  | Heat Recovery Steam Generator |  |  |  | for HRSG |  | FA | 1PF1650W52A02.1P | (HRSG #12 Insulation) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Piping Work | 2008-01-09 | 2008-09-30 | 2025-06-22 | 2025-07-22 | 2025-08-21 | 2025-09-05 | 2025-09-20 | 2025-10-05 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860027 | REACTIVE POWER TEST OF STG | Test | Steam Turbine & Generator |  |  |  | Test for STG |  | FA | 1PF2040W42A02P | (STG #10) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > ST Generator | 2007-03-01 | 2008-09-01 | 2024-09-04 | 2024-10-04 | 2024-11-03 | 2024-11-18 | 2024-12-03 | 2024-12-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860028 | PSS TEST OF STG | TEST | Steam Turbine & Generator |  |  |  | TEST for STG |  | FA | 1PF2040W42A02P | (STG #10) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > ST Generator | 2007-03-01 | 2008-09-01 | 2024-09-04 | 2024-10-04 | 2024-11-03 | 2024-11-18 | 2024-12-03 | 2024-12-18 | generated | 0.90 | 6210
Fadhili_MDL.xlsx | T16182-DN05-P0ZEN-860029 | SECONDARY RESPONSE TEST | TEST |  |  |  |  | TEST |  | FA | 0SF6500W62A04 | (Power Receiving) Protection Secondary & Primary Test | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power Receiving | 2008-09-05 | 2008-09-11 | 2025-10-04 | 2025-11-03 | 2025-12-03 | 2025-12-18 | 2026-01-02 | 2026-01-17 | generated | 0.90 | 6210