ANNEX 1

Work Scope

- 1A:	Design/Engineering

This section of Work Scope shall include the entire design of the Project, including Front End Engineering Design and detailed design and all other processes required by Good Engineering Practice.

The Design/Engineeringshall include the following:

- obtaining approvals and opinions of relevant government agencies and services required for the Design/Engineering including technical conditions (Технические условия на подключение к источникам инженерного и коммунального обеспечения in Russian) for connection to utilities sources as required by legislation of the Republic of Kazakhstan and Architectural and planning assignment for the design of the Project from local authority of Architecture and Urban Planning;

- development of the Detailed Documentation Issued for Construction works under EPCM’s scope(topographical survey, geological studies etc) required by legislation of the Republic of Kazakhstan in order to develop Detailed Documentation Issued for Construction;

- adaptation and obtainment of positive resolution (approval) of State Expertise for the Detailed Documentation Issued for Construction;

- submitting and obtaining approval for the Detailed Documentation Issued for Construction from authorized state body for architecture, urban planning and construction;

- author supervision of construction works to be performed by the Construction contractor in accordance with legislation of the Republic of Kazakhstan (providing with field engineering service (site works));

- providing with a bill of quantities for the Construction Contractor’s Materials for inclusion into the Construction Contract such as:

- Material balance

- Equipment list with the installation drawings and all the details for structureand footers(dimensions, weight etc).

- Line list with all the details for tie-in points.

- Electrical user list with the details of the loads and in-rush current

- Single line drawings

- Instrument list including the fire protection and gas/smoke detection

- Automation system structure

- BoQ’s for all bulk material including the construction job

- providing to the Construction Contractor such further information as the Construction Contractor reasonably requires in order to understand and follow the Contractor’s design.

- preparing the Information and Contractor’s Materials Delivery Schedule and agreeing the same with the Construction Contractor

- any other works and services related to or required for performance of the above under EPCM’s Scope in accordance with requirements of legislation of the Republic of Kazakhstan.

All Design/Engineering shall comply with the legislation of the Republic of Kazakhstan including all and any technical or construction rules and regulations.

- 1B:	Contractor’s Materials Supply (including procurement management)

- The Contractor’s Materials Supply shall include the following:

- Manufacture or procurement of the Contractor’s Materials in accordance with the Contractor’s design and Contractor’s Documents, including all appropriate inspection, shop testing and QA/QC;

- packing and loading, transporting, inspecting and testing Contractor’s Materials before delivering to the Construction Contractor at the Delivery Point including any temporary works to public highways or facilities required to facilitate transport of Contractor’s Materials to the Delivery Point including any reinstatement, fees, compensation, etc. for any disturbances. Arrangement of any permits required for transportation of Contractor’s Materials;

- verification that Contractor’s Materials meet the Procurement procedure provided by Contractor and approved by Company and are suitable for incorporation to the Project;

- supplying two(2) years operational spares required in respect of the Equipment, the Process Unit and the Contractor’s Materials prior to the date of Final Acceptance (including for Precommissioning, Commissioning, Functional Tests and Performance Tests, as applicable);

- providing consumables to fill and use during start up and initial operation. Handling and screening facilities, if required for operations, shall be provided by Contractor;

- providing lubricants, greases and, in general, all consumables and spares, excluding feed stocks and permanent plant utilities, required up to the Final Acceptance, plus, for consumables, for a further twelve (12) months operation of the Process Unit;

- training of the Company personnel for start-up, maintenance and operation of the Process Unit;

- preparation of appropriate forms and applications (in the Company’s name where necessary) and take all actions necessary for customs clearance and to obtain permissions to enable the importation of the Contractor’s Materials into the Republic of Kazakhstan;

- obtaining the necessary permits in government authorities and agencies, necessary for the organization and delivery of materials and equipment (if applicable);

- any other procurement services related to or required for performance of the above in accordance with requirements of legislation of the Republic of Kazakhstan.

Materials Supply shall comply with the legislation of the Republic of Kazakhstan including all and any technical or construction rules and regulations.

- 1C:	Construction Management (including pre-commissioning, commissioning, start-up and performance testing)

People required on Site: Site Construction Manager, Engineer for each discipline, Health and Safety Manager, Site Manager or Construction Inspector, Quality Manager, Project Controls Manager, Administration Manager, Materials Control Manager, Completion Manager or Completion Engineer (later on, 6 month before Mechanical Completion), Safety Inspector, Local Environmental Engineer, Material Control Supervisor (material and logistics), Field office for engineering (Project Engineers and discipline engineers, i.e. electrical, civil, mechanical, piping, structural, instrument, DCS, etc.).

Contractor, refering to the above mentioned Company requirement will submit the site organization chart for Company approval before kick-off meeting.

The Construction Management (including pre-commissioning, commissioning, start-up and performance testing) shall include the following:

- preparing the Project Time Schedule and agreeing the same with the Company

- technical inspection in accordance with requirements of legislation of the Republic of Kazakhstan;

- supervision and reporting of all construction works performed by Construction Contractor under the Construction Contract starting from the beginning of construction activities till the mechanical completion in order to detect any defects and inconsistencies of Construction Work to the Detailed Documentation Issued for Construction and to verify the Construction Contractor’s compliance with his obligations;

- off-site inspection of manufacturing for large items of Construction Contractor’s Materials;

- acting as and fulfilling the functions of client’s representative and engineer under the Construction Contract

- reviewing and commenting upon all programmes, drawings, specifications and details which the Construction Contractor prepares pursuant to the Construction Contract, checking compliance between such documentation and the Project Time Schedule and Contractor’s Documents, and approving, rejecting or commenting upon the same as appropriate;

- Managing payment provisions under the Construction Contract, in order to value work done to date and provide recommendations to the Company as to milestone payment amounts and any deductions to be made (whether for poor performance or otherwise)

- providing of pre-commissioning and commissioning works together with the Company and Construction contractor;

- supervision of installation of the Equipment;

- selection, evaluation, prequalification, preparation and providing to the Company a list of experienced and professional potential Construction Contractors those are able to perform construction works, reviewing and evaluating and advising the Company upon the prospective Construction Contractors’ tender returns (including reviewing pricing, contract sum analysis, risk profiles and any technical submissions) and providing such technical support as the Company requires in order to negotiate and conclude the Construction Contract;

- providing full-time site attendance during the course of execution of works on Site, and attend all meetings in connection with the progress of design and/or works;

- advising the Company concerning drawings and samples submitted to the Company by the Construction Contractor;

- conducting such negotiations as may be appropriate with the Construction Contractor and making the appropriate recommendations to the Company;

- advising the Company upon the performance and discharge of its duties and obligations under the terms of the Construction Contract, including in relation to any certifications required under the Construction Contract.  Advising the Company of any action that it is necessary for the Company to take in connection with the Construction Contract;

- manage the defects rectification process under the Construction Contract, including rectification of Punch List Items;

- provide all operation and maintenance manuals to the Company as required for the continued operation and maintenance of the Project

- supporting the Company in responding to, and if appropriate defending, any claim raised by the Construction Contractor.

Construction management shall comply with the legislation of the Republic of Kazakhstan including all and any technical or construction rules and regulations.

Design/Engineering, Materials Supply and Construction management must be carried out in such a way that they allow the Construction contractor to comply promptly with the construction and installation work and meet the objectives of the Project.

All other works, services and activities that must be performed by the Contractor in accordance with the contract, including those that are ancillary or related to the above.

- Work Scope`s List

- The following Work Scope`s List  sets out, as between the Company, the Contractor and the Construction Contractor, the responsibility of each for providing Materials.  Where any materials are required for the Project which are not set out in such Work Scope`s List , they shall be the responsibility of the Contractor to provide; unless such materials are generally provided by Construction Contractor.

| Section 1D Scope of Work List of Annex 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CODE | DESC'N. | BREAKDOWN |  | REQD | ENG'G | MTO |  | SUPPLY/PROCURE |  |  |  | INSTALLATION |  |  |
|  |  |  |  | (Y/N) | ENTITY | ENTITY |  | EPCM | CC | CLIENT |  | EPCM | CC | CLIENT |
| 1 | CIVIL |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | PILING |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | CAST IN-SITU |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | PREFAB |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | CASINGS REQUIRED |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | REINFORCEMENT FULL LENGTH |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | STAKING OUT |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | PILE TEST |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  | CIVIL |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | SOIL INVESTIGATION |  | Y | EPCM | EPCM |  | X |  |  |  | X |  |  |
|  |  | SITE PREPARATION |  | if Req | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | - CONTAMINATED SOIL |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | - PRELOADING |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | - BATH TUBBING |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | DIKES |  | If. Req | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | TANKPADS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | DEWATERING |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | WINTERIZATION |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | SHEETPILING: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - TEMPORARY |  | Y | CC | CC |  |  | X |  |  |  | X |  |
|  |  | - PERMANENT |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | PILE HEAD CUTTING |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | EXCAVATION |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | BACKFILL |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | IMPORTED FILL |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | OFFSITE DISPOSAL OF EXCESS EXCAVATED MATERIAL |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | ROCK BLASTING |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | ROCK GRINDING |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | BLINDING |  | if Req | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | REINFORCED CONCRETE: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - SUBSTRUCTURES |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | - SUPERSTRUCTURES |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | - SLEEPERS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | - PITS/BASINS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | JOINT FILLERS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | GROUT: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - SAND/CEMENT |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | - NON SHRINK |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | EMBEDDED STEEL |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | EQUIPMENT TEMPLATES |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | ANCHOR BOLTS (FOR EQUIPMENTS) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | SLIDING PLATES |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | CONCRETE FINISHING: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - BITUMEN |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | - EPOXY |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | - TITLNG |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | CULVERTS: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - CONCRETE |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | - BRICKWORK |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | DITCHES (CONCRETE PAVED) |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | PERMANENT PLANT ROADS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | TEMPORARY ROADS DURING CONSTRUCTION |  | Y | CC | CC |  |  | X |  |  |  | X |  |
|  |  | PERMANENT FENCING |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | TEMPORARY FENCING DURING CONSTRUCTION |  | Y | CC | CC |  |  | X |  |  |  | X |  |
|  |  | GATES |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | ROAD BARRIERS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | U/G PIPING (EXCEPT FIRE FIGHTING SYSTEM) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | MANHOLES/BOXES |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
| 2 | EQUIPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | AIR COOLED CONDENSERS AND AUX |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | BLOWERS AND FANS (IF REQUIRED) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | START UP BOILER |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | CAPITAL SPARES |  | Y | EPCM | EPCM |  |  |  | X |  |  |  | X |
|  |  | COMPRESSORS AND DRIVERS |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | COOLING TOWERS |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | CRANES (PERMANENT) FOR GTG & STG |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | CYCLONES |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | DESOLVING AND SUSPENSION EQUIPMENT |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | DRILLING EQUIPMENT |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | DRUMS AND PROCESS TANKS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | DRYERS AND ACCUMULATORS |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | ELEVATORS AND CONVEYORS |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | ENVIRONMENTAL EQUIPMENT |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | FILTERS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | FIRED HEATERS AND ACCESSORIES |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | FLAME ARRESTORS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | GAS TURBINES WITH AUX |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | HEAT EXCHANGERS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | HRSG's AND AUX |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | LOADING, UNLOADING AND RECLAIMING EQUIPMENT |  | If Req. | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | MAINTENANCE EQUIPMENT (HOIST IN EPCM'S SCOPE) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | MISCELLANEOUS MECHANICAL EQUIMPENT |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | SAFETY EQUIPMENT (EYE WASH & SAFETY SHOWER) |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | OTHER PRESSURE VESSELS (IN EPCM'S SCOPE) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | PACKAGE UNITS (if any) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | POWER GENERATORS AND AUX |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | PUMPS AND DRIVERS (IN EPCM'S SCOPE) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | REFRIGERATION EQUIPMENT |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | SILENCERS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | SKID MOUNTED EQUIPMENT |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | STEAM TURBINES AND AUX |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | BULLETS |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | STACKS AND VENTS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | STRAINERS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | TANKS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | TOWERS |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | VACUUM EQUIPMENT |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | WEIGHING EQUIPMENT AND SCALES |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | WELLHEAD EQUIPMENT |  | N |  |  |  |  |  |  |  |  |  |  |
| 3 | PIPING |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ABOVE GROUND PIPING |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - CS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - SS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - ALLOY |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - CEMENT LINED |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | - PLASTIC/OTHER |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  | BELOW GROUND PIPING |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - CS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - SS |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | - ALLOY |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | - CEMENT LINED |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | - PLASTIC/OTHER |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - FIELD COAT AND WRAP MATERIALS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  | OTHERS |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | VALVES |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | BOLTS, NUTS, GASKETS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | PIPE SUPPORTS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | SPRING SUPPORTS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | HYDROTEST MATERIALS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | BELLOWS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | HYDRANTS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | FIRE MONITORS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | PREFABRICATION |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | LIFE FIGHTING EQUIPMENT |  | N |  |  |  |  |  |  |  |  |  |  |
| 4 | BUILDINGS - OUT OF THE EQUIPMENT ENCLOSURE |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | BUILDING TYPE |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | NON BLASTPROOF / RESISTANT |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | BLASTPROOF / RESISTANT |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | BUILDING MATERIALS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | ARCHITECTURAL MATERIALS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | FIREFIGHTING SYSTEM: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - SPRINKLER SYSTEM |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | - HOSE REELS, etc |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | - INERT GAS SYSTEM |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | ELECTRICAL SYSTEMS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | PLUMBING SYSTEMS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | HVAC/DUCTING SYSTEMS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | FIXTURES AND FITTINGS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | FURNITURE AND EQUIPMENT |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | ACCESS PLATFORM TO SUBSTATION |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
| 4 | PROCESS EQUIPMENT ENCLOSURES |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | BUILDING TYPE |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | NON BLASTPROOF / RESISTANT |  | N |  |  |  |  |  |  |  |  | X |  |
|  |  | BLASTPROOF / RESISTANT |  | N |  |  |  |  |  |  |  |  | X |  |
|  |  | BUILDING MATERIALS |  | N |  |  |  |  |  |  |  |  | X |  |
|  |  | ARCHITECTURAL MATERIALS |  | N |  |  |  |  |  |  |  |  | X |  |
|  |  | FIREFIGHTING SYSTEM(Detection and Fire extuinguishing system as per local RoK regulations and manufacturer standrds: |  | Y | EPCM | EPCM |  | X |  |  |  |  |  |  |
|  |  | - SPRINKLER SYSTEM |  | N |  |  |  |  |  |  |  |  | X |  |
|  |  | - HOSE REELS, etc |  | N |  |  |  |  |  |  |  |  | X |  |
|  |  | - INERT GAS SYSTEM |  | N |  |  |  |  |  |  |  |  | X |  |
|  |  | ELECTRICAL SYSTEMS (per local RoK and manufacturer standards) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | PLUMBING SYSTEMS |  | If Req. | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | HVAC/DUCTING SYSTEMS (per local RoK and manufacturer standards) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | FIXTURES AND FITTINGS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | FURNITURE AND EQUIPMENT |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | ACCESS PLATFORM |  | Y | EPCM | EPCM |  | X |  |  |  |  |  |  |
| 5 | STRUCTURAL STEEL - PROCESS AREA |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | PIPERACKS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | PIPESUOOPRTS (T-POSTS) |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | STRUCTURES: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - ONSHORE |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - COMPRESSOR BUILDINGS |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | - SHEDS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | - OFFSHORE: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - PRIMARY STEEL |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | - SECONDARY STEEL |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | - TERTIARY STEEL |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | PLATFORMS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | LADDERS: |  |  |  |  |  | X |  |  |  |  |  |  |
|  |  | WITHOUT CAGE |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | WITH CAGE |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | SUPPORTS/MOUNTINGS/BRACING |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | CONNECTIONS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | BOLTS/NUTS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | HANDRAILS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | GRATING |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | CHECKER PLATE |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | STAIRTREADS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | SAFETY BARS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | CORRUGATED ROOFING |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | CORRUGATED SIDING |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | TRANSLUCENT SHEETING |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | STEEL PLATES |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | DAVITS |  | If Req. | EPCM | EPCM |  | X |  |  |  |  |  |  |
|  |  | HOISTS/TROLLEY |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | ELEVATORS |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | CONVEYING EQUIPMENT: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - BELT CONVEYORS |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | - BUCKET CONVEYORS |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | - SCREW CONVEYORS |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | FIREWALLS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
| 5 | STRUCTURAL STEEL - OUTSIDE PROCESS AREA |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | PIPERACKS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | PIPESUOOPRTS (T-POSTS) |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | STRUCTURES: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - ONSHORE |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - COMPRESSOR BUILDINGS |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | - SHEDS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | - OFFSHORE: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - PRIMARY STEEL |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | - SECONDARY STEEL |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | - TERTIARY STEEL |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | PLATFORMS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | LADDERS: |  |  |  |  |  |  | X |  |  |  |  |  |
|  |  | WITHOUT CAGE |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | WITH CAGE |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | SUPPORTS/MOUNTINGS/BRACING |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | CONNECTIONS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | BOLTS/NUTS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | HANDRAILS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | GRATING |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | CHECKER PLATE |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | STAIRTREADS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | SAFETY BARS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | CORRUGATED ROOFING |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | CORRUGATED SIDING |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | TRANSLUCENT SHEETING |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | STEEL PLATES |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | DAVITS |  | If Req. | EPCM | EPCM |  |  | X |  |  |  |  |  |
|  |  | HOISTS/TROLLEY |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | ELEVATORS |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | CONVEYING EQUIPMENT: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - BELT CONVEYORS |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | - BUCKET CONVEYORS |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | - SCREW CONVEYORS |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | FIREWALLS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
| 6 | INSTRUMENTS |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | FLOW INSTRUMENTS (As per Requisition List) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | LEVEL INSTRUMENTS (As per Requisition List) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | PRESSURE Instruments (As per Requisition List) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | TEMPERATURE INSTRUMENTS (As per Requisition List) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | CONTROL VALVES (As per Requisition List) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | SAFETY RELIEF decices (As per Requisition List) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | ANALYZERS (As per Requisition List) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | FIRE & GAS SYSTEM (As per Requisition List) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | FIRE & GAS INSTRUMENTS (As per Requisition List) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | METERING STATION (As per Requisition List) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | COMMUNICATION SYSTEMS (As per Requisition List) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | MACHINE MONITORING SYSTEM |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  | MISCELLANEOUS |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | CONVERTORS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | SOLENOID VALVES |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | PROTECTION HOUSINGS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | SUNSHADES |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | LOCAL PANELS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | PROXIMITY SWITCHES |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | MANUAL LOADING STATIONS |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | WEIGHING SYSTEMS |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | TANK BLANKETING |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | SPEED TRANSMITTERS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | CORROSION PROBES |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | FLAME DETECTION FOR HEATERS |  | if Req | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | TRANSMITTER OUTPUT GAUGES (EL) |  | Y | EPCM | EPCM |  | X |  |  |  |  |  |  |
|  | INSTALLATION MATERIAL |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | JUNCTION BOXES |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | CABLE: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - INSTRUMENT SINGLE |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - INSTRUMENT MULTICORE |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - T/C EXTENSION |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - DATA HIGHWAY |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - COAX |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - FIBRE OPTIC |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | FIRE PROTECTION |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | DATA HIGHWAY COUPLERS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | NUCLEAR CELLS |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | MAIN CABLE TRAYS/LADDERS (from DCS to JB) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | SECONDARY TRAY (from field to JB) |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | CONDUIT: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - OPEN SYSTEM |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | - CLOSED SYSTEM |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | MULTICABLE TRANSIT BLOCKS |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | INSTRUMENT SUPPORTS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | PROCESS PIPE HOOK-UP (TUBING, AIRFILTERS, MANIFOLDS, UNIONS, COUPLINGS, BALL VALVES, ETC) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | MANIFOLD BLOCKS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | AIR PIPING HOOK-UP (TUBING, FITTINGS, AIRFILTERS, VALVES< UNIONS, TEES, ETC) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | AIRFILTER REGULATORS |  | Y | EPCM | EPCM |  | X |  |  |  |  |  |  |
|  |  | SUB-AIR HEADER PIPING HOOK-UP |  | Y | EPCM | EPCM |  | X |  |  |  |  |  |  |
|  |  | STEAM TRACING CONNECTION |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | CONDENSATE TRAPS |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | OTHER INSTALLATION MATERIAL |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  | CONTROL ROOM EQUIPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | DIGITAL CONTROL SYSTEM (As per Requisition List) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
| 7 | INSULATION |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | EQUIPMENT |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | PIPING (process area) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | INSTRUMENTATION (process area) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | PIPING (outside of process area) |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | INSTRUMENTATION I(outside of process area) |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
| 8 | FIREPROOFING |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | EQUIPMENT |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | STRUCTURAL STEEL |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | INSTRUMENTATION |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | ELECTRICAL |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
| 9 | ELECTRICAL |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | HIGH VOLTAGE FEEDERS |  |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  | TRANSFORMERS (As per Requisition List) |  |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | TYPE: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - POWER |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - SMALL POWER AND LIGHTING |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - EARTHING RESISTORS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  | GIS/MV SWITCHGEAR (As per Requisition List) |  |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | TYPE: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - HIGH VOLTAGE (110 kV) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - MEDIUM VOLTAGE (10 kV) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  | LV SWITCHGEAR / MCC (As per Requisition List) |  |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  | BUS DUCT SYSTEM |  |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  | MOTORS |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | TYPE: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - MEDIUM VOLTAGE |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - LOW VOLTAGE |  | Y | EPCM | Cb7I |  | X |  |  |  |  | X |  |
|  | DISTRIBUTION PANELS (As per Requisition List) |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | TYPE: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - SMALL POWER DISTRIBUTION PANELS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - LIGHTING PANELS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - EMERGENCY LIGHTING PANELS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - RECEPTACLE PANELS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - HEAT TRACING PANELS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - INSTRUMENT DISTRIBUTION PANELS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  | UPS-SYSTEMS (As per Requisition List) |  |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | TYPE: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - STATIC; COMPONENTS AND BATTERIES |  |  |  |  |  |  |  |  |  |  |  |  |
|  | DC SYSTEMS |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | TYPE: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - BATTERY CHARGERS AND BATTERIES |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  | MISCELLANEOUS PANELS |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | TYPE: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - INTERPOSING RELAY PANELS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - RELAY CABINETS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - MARSHALLING CABINETS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - ANNUNCIATOR PANELS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - VARIABLE SPEED DRIVE PANELS (IF REQUIRED) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - CAPACITOR BANKS |  | If Req. | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  | POWER INSTALLATION MATERIAL |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | PUSH BUTTONS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | MOTOR CONTROL STNS.(WITH AMMETER) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | MOTOR CONTROL STNS.(W/O AMMETER) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | SAFETY SWITCHES |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | JUNCTION BOXES |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | WELDING OUTLETS/PLUGS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | CABLE TRAYS/LADDERS (MAIN) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | CABLE TRAYS/LADDERS (SUB) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | CABLE TRENCHES/TILES/TAPE |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | CABLE TRANSIT BLOCKS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | CABLE GLANDS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | CABLE CLEATS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | PROTECTION CONDUIT: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - OPEN SYSTEM |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - CLOSED SYSTEM |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | HOOK-UP MATERIAL: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - CONTROL STATION |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - WELDING OUTLET |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - MOTOR JUNCTION BOX |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - PROTECTION CONDUIT |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - OTHER INSTALLATION MATERIALS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  | CABLES AND CABLE CONNECTION |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | TYPE: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - HIGH VOLTAGE |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - MEDIUM VOLTAGE |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - LOW VOLTAGE |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - POWER |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - CONTROL |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - LIGHTING |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - HEAT TRACING |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - OVERHEAD POWER LINES |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | CABLE TERMINAL LUGS (HV CABLE TERMINATION EXCEPT DOWNSTREAM TERMINALS OF THE HV FEEDERS RELATED TO THE GRID CONNECTION AND IPC USERS) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | CABLE SPLICE KITS (HV CABLE TERMINATION EXCEPT DOWNSTREAM TERMINALS OF THE HV FEEDERS RELATED TO THE GRID CONNECTION AND IPC USERS) |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  | LIGHTING SYSTEMS- PROCESS AREA (EXCEPT BUILDING) |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | LIGHTING FIXTURES: |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - INCANDESCENT |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - FLUORESCENT |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - HIGH PRESSURE SODIUM |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - MERCURY VAPOUR |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - EMERGENCY |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - PORTABLE |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | SWITCHES |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | JUNCTION BOXES |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | SOCKET OUTLETS/PLUGS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | 42V RECEPTACLE TRANSFORMER |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | CONTROL BOX GEAR |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | PHOTOELECTRIC CELL |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | HOOK-UP MATERIALS: |  |  |  |  |  |  |  |  |  |  | X |  |
|  |  | - MOUNTING MATERIALS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - POLES |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  | LIGHTING SYSTEMS NON PROCESS AREA |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | LIGHTING FIXTURES: |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | - INCANDESCENT |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - FLUORESCENT |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - HIGH PRESSURE SODIUM |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - MERCURY VAPOUR |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - EMERGENCY |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - PORTABLE |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | SWITCHES |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | JUNCTION BOXES |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | SOCKET OUTLETS/PLUGS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | 42V RECEPTACLE TRANSFORMER |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | CONTROL BOX GEAR |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | PHOTOELECTRIC CELL |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | HOOK-UP MATERIALS: |  |  |  |  |  |  |  |  |  |  | X |  |
|  |  | - MOUNTING MATERIALS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | - POLES |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  | EARTHING/LIGHTNING PROTECTION - WITHIN PROCESS AREA EXCEPT BUILDINGS AND STEEL STRUCTURES |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | EARTHING MATERIALS: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - CABLES/WIRES |  | Y | EPCM | EPCM |  |  |  |  |  |  | X |  |
|  |  | - RODS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - CONNECTORS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - BUSBARS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - HOOK-UP MATERIALS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - SURGE DIVERTERS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - COMPRESSION TOOLS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - CADWELD MOULDS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | FENCE EARTHING |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | LOADING STATION EARTHING |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | LIGHTNING MATERIALS: |  |  |  |  |  | X |  |  |  |  |  |  |
|  |  | - WIRE/STRIP |  | Y | EPCM | EPCM |  |  |  |  |  |  | X |  |
|  |  | - BUILDING |  | Y | EPCM | EPCM |  |  |  |  |  |  | X |  |
|  | EARTHING/LIGHTNING PROTECTION- OUTSIDE PROCESS AREA |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | EARTHING MATERIALS: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - MAIN EARTHING GRID |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | - CABLES/WIRES |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | - RODS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | - CONNECTORS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | - BUSBARS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | - HOOK-UP MATERIALS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | - SURGE DIVERTERS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | - COMPRESSION TOOLS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | - CADWELD MOULDS |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | FENCE EARTHING |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | LOADING STATION EARTHING |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | LIGHTNING MATERIALS: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - WIRE/STRIP |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | - BUILDING |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  | HEAT TRACING/WINTERIZATION |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | TRACER CABLE |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | CUBICLES |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | CONDUCTOR |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | TUBING |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | TERMINATION BOXES |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | COLD JOINT BOXES |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | COLD END BOXES |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | RTD ASSEMBLIES |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | OTHER INSTALLATION MATERIALS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  | PERMANENT CATHODIC PROTECTION (FOR UG CARBON PIPES) |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | TRANSFORMER RECTIFIER |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | SI-FE ANODE |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | Mg ALLOY ANODE |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | ZN REF CELL |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | DISTRIBUTION BOX |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | ANODE JUNCTION BOXES |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | ANODE CABLE |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | HDR CABLE |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | OTHER MATERIALS |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  | MISCELLANEOUS MATERIALS/SYSTEMS |  |  |  |  |  |  |  |  |  |  |  | X |  |
|  |  | OTHER INSTALLATION MATERIALS |  | Y | EPCM | EPCM |  |  | X |  |  |  |  |  |
| 10 | PAINTING & TSA |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | EQUIPMENT |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | PIPING |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | ARCHITECTURAL |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | STRUCTURAL STEEL (HDG) |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | SPLASH ZONE |  | N |  |  |  |  |  |  |  |  |  |  |
| 11 | SHIPPING |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | VENDORS SHOP TO PORT OF EXPORT |  | Y | EPCM | EPCM |  | X |  |  |  |  |  |  |
|  |  | PORT OF EXPORT TO PORT OF IMPORT |  | Y | EPCM | EPCM |  | X |  |  |  |  |  |  |
|  |  | PORT OF IMPORT TO SITE |  | Y | EPCM | EPCM |  | X |  |  |  |  |  |  |
|  |  | HEAVY LIFT CONTRACT |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
| 12 | GENERAL |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | VENDOR REPRESENTATIVES |  | Y | EPCM | EPCM |  | X |  |  |  | X |  |  |
|  |  | LABOUR (INCLUDING EPCm STAFF) CAMP: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - SET UP |  | Y | CC | CC |  |  | X |  |  |  | X |  |
|  |  | - CATERING |  | Y | CC | CC |  |  | X |  |  |  | X |  |
|  |  | - MAINTENANCE |  | Y | CC | CC |  |  | X |  |  |  | X |  |
|  |  | - REMOVAL |  | Y | CC | CC |  |  | X |  |  |  | X |  |
|  |  | LAYDOWN YARD |  | Y | CC | CC |  |  | X |  |  |  | X |  |
|  |  | TEMPORARY SITE BUILDINGS AND SITE FACILITIES |  | Y | CC | CC |  |  | X |  |  |  | X |  |
|  |  | SPARE PARTS: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - FOR CONSTRUCTION |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | - CAPITAL SPARES |  | Y | EPCM | EPCM |  |  |  | X |  |  |  | X |
|  |  | - 2 YEARS OPERATIONAL SPARES |  | Y | EPCM | EPCM |  |  |  | X |  |  |  | X |
|  |  | - COMMISSIONING AND START-UP SPARES |  | Y | EPCM | EPCM |  | X |  |  |  |  | X |  |
|  |  | CHEMICALS FIRST FILLING |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | PRE-COMMISSIONING (Transformers oil filtration,cable IR test, etc) |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | CHEMICAL CLEANING |  | Y | EPCM | EPCM |  |  | X |  |  |  | X |  |
|  |  | STEAM BLOWING |  | Y | EPCM | CC |  |  | X |  |  |  | X |  |
|  |  | COMMISSIONING, START-UP |  | Y | EPCM | EPCM |  | Note 1 |  | X |  |  | X |  |
|  |  | TRAINING |  | Y | EPCM | EPCM |  | X |  |  |  |  |  |  |
|  |  | Note 1: Under EPCM Instruction |  |  |  |  |  |  |  |  |  |  |  |  |
| 13 | SERVICES |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | HOME OFFICE SERVICES |  | Y | EPCM | EPCM |  | X |  |  |  |  |  |  |
|  |  | CONSTRUCTION MANAGEMENT |  | Y | EPCM | EPCM |  | X |  |  |  |  |  |  |
|  |  | FIELD INDIRECTS |  | Y | EPCM | EPCM |  | X |  |  |  |  |  |  |
|  |  | TRANSLATION (RUSSIAN) FOR ENGIEERING WORKS |  | Y | EPCM | EPCM |  | X |  |  |  |  |  |  |
|  |  | AUTHOR SUPERVISION |  | Y | EPCM | EPCM |  | X |  |  |  |  |  |  |
|  |  | TRAVELING (FOR EPCm) |  | Y | EPCM | EPCM |  | X |  |  |  |  |  |  |
|  |  | ASSIGNMENTS - LOCAL ENGINEERING COMPANY |  | Y | EPCM | EPCM |  | X |  |  |  |  |  |  |
|  |  | ASSIGNMENTS - CONSTRUCTION MANAGEMENT |  | Y | EPCM | EPCM |  | X |  |  |  |  |  |  |
| 14 | FINANCIAL COST |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | INSURANCES (AS REQUIRED): |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - THIRD PARTLY LIABILITY |  | Y | EPCM | EPCM |  | X |  |  |  |  |  |  |
|  |  | - FREIGHT INSURANCE |  | Y | EPCM | EPCM |  | X |  |  |  |  |  |  |
|  |  | - OTHER INSURANCES |  | Y | EPCM | EPCM |  | X |  |  |  |  |  |  |
|  |  | CURRENCY PROTECTION |  | N |  |  |  |  |  |  |  |  |  |  |
|  |  | BANK GUARANTEES |  | Y | EPCM | EPCM |  | X |  |  |  |  |  |  |
|  |  | DUTIES & TAXES |  | Y | EPCM | EPCM |  | X |  |  |  |  |  |  |
|  |  | OTHER FINANCIAL COST (IF REQUIRED) |  | Y | EPCM | EPCM |  | X |  |  |  |  |  |  |
| 15 | (POTENTIAL) COST SAVINGS |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | AGREED SCOPE ITEMS |  | Y | EPCM | EPCM |  | X | X | X |  |  |  |  |
|  |  | OPEN SCOPE ITEMS |  | Y | EPCM | EPCM |  | X | X | X |  |  |  |  |
| EPCM/EPCm : DOOSAN |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

- 1E: Office Facilities

1. Contractor shall provide the following services and facilities for Company team members resident at Contractor’s Home Offices within its lump sum price.

1. These services and facilities are in addition to daily cleaning, maintenance, consumables, stationery and utilities which are to be provided at such offices.  All offices, office areas, conference rooms and secretarial stations shall include the necessary computer wires/cables including modems and connection to Contractor’s local area network.

2. All facilities described below are to be situated within a separate lockable area adjacent to Contractor’s team.

Contractor Home Office

Contractor shall provide the following:

1.  One suitable executive lockable offices for Company Project Director/Manager, furnished with a minimum of desk with chair, table, meeting table and chairs, 2 five-drawer filing cabinets, international telephone (speaker telephone).  Access to design office network, e-mail, internet, plotters, and laser printers shall be provided.

2.  A partitioned office area to accommodate up to 8 Company staff, each with desk, chair, lockable drawers/cupboards, telephone. Access to design office network, e-mail, internet, plotters and laser printers shall be provided.

3.  A fully equipped, furnished and dedicated conference room of minimum capacity to seat 10 people comfortably, complete with an agreed conference telephone and computer network connection to the design office network, e-mail, internet, projector, plotters and laser printers.

4.  Access to Contractor’s facilities such as employee cafeterias, rest rooms, toilets, and recreation areas, which are normally available to Contractor’s personnel, shall be made available to Company and its representatives.

5.  All necessary software necessary to review contractor documentation in original format as well as to review 3D model.  One computer shall be loaded with Primavera P6e/c and a suitable Risk Analysis program for use with P6 e/c shall be available. Other specialist software (RAM, 3D model review, etc.) shall be provided as required.

6.  Contractor shall provide the following printers for Company use: 1 high volume printer, 1 low volume printer and a colour laser printer.

7.  Contractor shall provide access to Company, to Contractor’s high quality large format colour plotter.

8.  Contractor shall provide suitable data connectivity, allowing Company’s team to access the Contractor’s design office network and document management system (read-only), as well as the internet and Wide Area Network (WAN) connectivity to Company’s own networking environment.  Data connectivity shall be at a level equivalent to international standards.  The minimum acceptable requirement will be of T1 or greater bandwidth capacity.

9.   All office accommodation will be fully furnished with quality furnishings and have access to dedicated and secure facsimile machine, reproduction facilities, routine office supplies, and networked, secure personal computers with associated technical support as required by Company.

10.  The cost of provision of international telephone lines and local telephone charges shall be included in the lump sum price. All international telephone calls made by Company personnel shall be reimbursed at cost to Contractor.

11.  Contractor shall provide the dedicated clerical and secretarial support for Company use in the Home Office for the duration of the engineering and procurement activities.  The secretarial personnel shall be fluent in the English language as well as the language of the Contractor, and be highly skilled in the use of computers and conventional office software including the latest version of the Microsoft Office Professional suite of software.

12.   Contractor  shall provide all services necessary to assist Company whenever requested in the following:

- Renting fully furnished houses or flats of excellent standard preferably within the vicinity of Home Office, where the design shall be conducted, and payment of utilities and similar expenses.

- Locating and registering the Company team and their dependents in the applicable medical centres.

- Locating schools in the vicinity of Company’s team accommodation for admission of dependents, including the payment of fees, registration, etc.

- Opening bank accounts for the Company’s team, if required.

- Visas and/or work permits, addressing tax issues and the like, to the extent required by Company.

- Travel arrangements including flight, hotel and rental car bookings.

- The agreed costs of the above services shall be reimbursed at actual cost to Contractor.

13.  The services and facilities in this section shall be provided by the Contractor for the entire duration of the stay of Company team in Contractor’s Home Office. The duration and the termination of those services and facilities shall be entirely at Company’s discretion.

| Doosan and KNEP Consortium represented by the Consortium Leader Doosan Heavy Industries Construction Co., Ltd |  | “Karabatan Utility Solutions” LLP |  |
| --- | --- | --- | --- |
| Signature: |  | Signature: |  |
| Name: | Jin Wook Eom | Name: | Stjepan Skufca |
| Title: | General Manager | Title: | General Director |