## Document for Owner
Scope | Team Code | Owner | Document No | Serial | Title | Pur | First Plan | Final Plan | DT Date(EM) | DT Date | DT No | DT Pur. | DT Rev. | Com. Date | Com. No | Com. Pur. | Com. Rev. | Com. Status | Discipline | PKG Code
DHI | 배관기술 | 황계증 | MRT-UC07-P0ZEN-100001 | 1 | [Overall Arrange]_PLOT PLAN | FA | 2017-06-30 | 2018-09-28 | 2023-03-02 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | 2020-11-04 | 134/T/MRT/REC/XI/2020 | FC | 6 | A | MECHANICAL | PLOT PLAN
DHI | 배관기술 | 황계증 | MRT-UC08-P0ZEN-100002 | 2 | GENERAL ARRANGEMENT FOR POWER BLOCK | FA | 2017-07-28 | 2018-09-28 | 2023-03-02 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | 2020-11-04 | 134/T/MRT/REC/XI/2020 | FC | 5 | A | MECHANICAL | PLOT PLAN
DHI | 배관기술 | 황계증 | MRT-UC08-P0ZEN-100003 | 3 | GENERAL ARRANGEMENT FOR POWER BLOCK GENERAL SECTION G-G | FA | 2017-07-28 | 2018-07-30 | 2023-03-02 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | 2020-11-04 | 134/T/MRT/REC/XI/2020 | FC | 5 | A | MECHANICAL | PLOT PLAN
DHI | 배관기술 | 황계증 | MRT-UE00-P2ZEN-100004 | 4 | [Steam Turbine Building_GA (For Block 2)]_GENERAL ARRANGEMENT GROUND FLOOR PLAN | FA | 2017-07-28 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220033 | AB | Z0 | 2020-11-13 | 137/T/MRT/REC/XI/2020 | FC | 7 | A | MECHANICAL | PLOT PLAN
DHI | 배관기술 | 황계증 | MRT-UE00-P2ZEN-100005 | 5 | [Steam Turbine Building_GA (For Block 2)]_GENERAL ARRANGEMENT MEZZANINE FLOOR PLAN | FA | 2017-07-28 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220033 | AB | Z0 | 2020-11-13 | 137/T/MRT/REC/XI/2020 | FC | 7 | A | MECHANICAL | PLOT PLAN
DHI | 배관기술 | 황계증 | MRT-UE00-P2ZEN-100006 | 6 | [Steam Turbine Building_GA (For Block 2)]_GENERAL ARRANGEMENT OPERATING FLOOR PLAN | FA | 2017-07-28 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220033 | AB | Z0 | 2020-11-13 | 137/T/MRT/REC/XI/2020 | FC | 7 | A | MECHANICAL | PLOT PLAN
DHI | 배관기술 | 황계증 | MRT-UE00-P2ZEN-100007 | 7 | [Steam Turbine Building_GA (For Block 2)]_GENERAL ARRANGEMENT BASEMENT PLAN | FA | 2017-07-28 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220033 | AB | Z0 | 2020-11-13 | 137/T/MRT/REC/XI/2020 | FC | 7 | A | MECHANICAL | PLOT PLAN
DHI | 배관기술 | 황계증 | MRT-UE00-P2ZEN-100008 | 8 | [Steam Turbine Building_GA (For Block 2)]_GENERAL ARRANGEMENT SECTION A-A | FA | 2017-07-28 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220033 | AB | Z0 | 2020-11-13 | 137/T/MRT/REC/XI/2020 | FC | 6 | A | MECHANICAL | PLOT PLAN
DHI | 배관기술 | 황계증 | MRT-UE00-P2ZEN-100009 | 9 | [Steam Turbine Building_GA (For Block 2)]_GENERAL ARRANGEMENT SECTION B-B | FA | 2017-07-28 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220033 | AB | Z0 | 2020-11-13 | 137/T/MRT/REC/XI/2020 | FC | 6 | A | MECHANICAL | PLOT PLAN
DHI | 배관기술 | 황계증 | MRT-UE00-P3ZEN-100010 | 10 | [Steam Turbine Building_GA (For BLOCK 3&4)]_GENERAL ARRANGEMENT GROUND FLOOR PLAN | FA | 2017-07-28 | 2018-07-30 | 2023-03-02 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | 2024-03-26 | MTW-AS-C-LT-24.5107.0 | AB | Z0 | A | MECHANICAL | PLOT PLAN
DHI | 배관기술 | 황계증 | MRT-UE00-P3ZEN-100011 | 11 | [Steam Turbine Building_GA (For BLOCK 3&4)]_GENERAL ARRANGEMENT MEZZANINE FLOOR PLAN | FA | 2017-07-28 | 2018-07-30 | 2023-03-02 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | 2024-03-26 | MTW-AS-C-LT-24.5107.0 | AB | Z0 | A | MECHANICAL | PLOT PLAN
DHI | 배관기술 | 황계증 | MRT-UE00-P3ZEN-100012 | 12 | [Steam Turbine Building_GA (For BLOCK 3&4)]_GENERAL ARRANGEMENT OPERATING FLOOR PLAN | FA | 2017-07-28 | 2018-07-30 | 2023-03-02 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | 2024-03-26 | MTW-AS-C-LT-24.5107.0 | AB | Z0 | A | MECHANICAL | PLOT PLAN
DHI | 배관기술 | 황계증 | MRT-UE00-P3ZEN-100013 | 13 | [Steam Turbine Building_GA (For BLOCK 3&4)]_GENERAL ARRANGEMENT BASEMENT PLAN | FA | 2017-07-28 | 2018-05-30 | 2023-03-02 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | 2024-03-26 | MTW-AS-C-LT-24.5107.0 | AB | Z0 | A | MECHANICAL | PLOT PLAN
DHI | 배관기술 | 황계증 | MRT-UE00-P3ZEN-100014 | 14 | [Steam Turbine Building_GA (For BLOCK 3&4)]_GENERAL ARRANGEMENT SECTION C-C | FA | 2017-07-28 | 2018-07-30 | 2023-03-02 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | 2024-03-26 | MTW-AS-C-LT-24.5107.0 | AB | Z0 | A | MECHANICAL | PLOT PLAN
DHI | 배관기술 | 황계증 | MRT-UE00-P3ZEN-100015 | 15 | [Steam Turbine Building_GA (For BLOCK 3&4)]_GENERAL ARRANGEMENT SECTION D-D | FA | 2017-07-28 | 2018-07-30 | 2023-03-02 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | 2024-03-26 | MTW-AS-C-LT-24.5107.0 | AB | Z0 | A | MECHANICAL | PLOT PLAN
DHI | 배관기술 | 황계증 | MRT-UE00-P2ZEN-100016 | 16 | [Steam Turbine Building_GA (For Block 2)]_GENERAL ARRANGEMENT ROOF FLOOR PLAN | FA | 2018-02-16 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220033 | AB | Z0 | 2020-11-13 | 137/T/MRT/REC/XI/2020 | FC | 5 | A | MECHANICAL | PLOT PLAN
DHI | 배관기술 | 황계증 | MRT-UE00-P3ZEN-100017 | 17 | [Steam Turbine Building_GA (For BLOCK 3&4)]_GENERAL ARRANGEMENT ROOF FLOOR PLAN | FA | 2018-02-16 | 2018-07-30 | 2023-03-02 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | 2024-03-26 | MTW-AS-C-LT-24.5107.0 | AB | Z0 | A | MECHANICAL | PLOT PLAN
DHI | EM | 김태환 | MRT-DA01-P0ZEN-020001 | 18 | DOCUMENT IDENTIFICATION | FI | 2017-05-30 |  | 2020-11-04 | 2020-11-04 | MRT-DS-REC-TT-200082-FC | FC | 2 | 2020-11-05 | 200082-FC STAMPED | FC | 2 | A | SUPPORT | GENERAL
DHI | EM | 김태환 | MRT-DA01-P0ZEN-020002 | 19 | EQUIPMENT AND SYSTEM IDENTIFICATION | FI | 2017-05-30 |  | 2017-08-21 | 2017-08-22 | MRT-DS-PLNE-TT-170016 | FI | 1 | 2017-09-15 | 15.018/E04/PLNE/IX/2017 | FI | 1 | I | SUPPORT | GENERAL
DHI | EM | 장준태 | MRT-XV00-P0ZEN-020003 | 20 | EQUIPMENT LIST | FI | 2018-03-30 |  | 2020-08-24 | 2020-08-24 | MRT-DS-REC-TT-200067-FC | FC | 2 | 2020-08-24 | 200067-FC STAMPED | FC | 2 | A | SUPPORT | GENERAL
DHI | EM | 장준태 | MRT-YK08-P0ZEN-020004 | 21 | TYPICAL NAMEPLATE DRAWING | FA | 2018-08-31 | 2018-11-30 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170100-FC | FC | 2 | 2018-09-21 | 170100-FC STAMPED | FC | 2 | A | SUPPORT | GENERAL
DHI | EM | 장준태 | MRT-BV02-P0ZEN-020005 | 22 | FLUE GAS DISPERSION STUDY | FI | 2017-11-24 |  | 2018-01-05 | 2018-01-11 | MRT-DS-PLNE-TT-180002 | FI | 1 | 2018-01-18 | 17.009/E04/PLNE/I/2018 | FI | 1 | A | SUPPORT | GENERAL
DHI | EM | 장준태 | MRT-DA05-P0ZEN-020006 | 23 | ABBREVIATION LIST | FI | 2017-11-30 |  | 2017-11-24 | 2017-12-05 | MRT-DS-PLNE-TT-170103 | FI | 0 | 2017-12-18 | 18.016/E04/PLNE/XII/2017 | FI | 0 | I | SUPPORT | GENERAL
DHI | EM | 장준태 | MRT-YT01-P0QJA-110001 | 24 | Gas Cylinder (N2, CO2) Calculation | FA | 2019-04-26 | 2019-07-26 | 2019-05-07 | 2019-05-16 | MRT-DS-REC-TT-190114-FC | FC | 0 | 2019-05-16 | 190114-FC STAMPED | FC | 0 | A | MECHANICAL | N2 GAS SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XG05-P0ZEN-110001 | 25 | [Plant Overall]_HEAT BALANCE DIAGRAMS | FA | 2017-05-31 | 2017-07-13 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170104-FC | FC | 3 | 2018-09-22 | 170104-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XG02-P0ZEN-110002 | 26 | [Symbol & Legend]_P&I DIAGRAM | FA | 2017-07-07 | 2017-11-07 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170070-FC | FC | 2 | 2018-09-21 | 170070-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XG02-P0GHC-110002 | 27 | [Make-up Water System]_P&I DIAGRAM | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2019-09-19 | 190191-FC STAMPED | FC | 7 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XG02-P0LBG-110004 | 28 | [Aux Steam system (For Common)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2019-09-19 | 190191-FC STAMPED | FC | 6 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XG02-P0PA-110002 | 29 | [Cooling Water system (For Common)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2019-09-19 | 190187-FC STAMPED | FC | 6 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XG02-P2LA-110006 | 30 | [Feedwater system (For Block 2)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2019-09-19 | 190191-FC STAMPED | FC | 7 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XG02-P2LBA-110003 | 31 | [Steam and Bypass system (For Block 2)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2020-09-28 | 118-T-MRT-REC-IX-2020 | FC | 8 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XG02-P2LBG-110004 | 32 | [AUX Steam system (For Block 2)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-11-07 | 2024-06-11 | 2024-06-11 | MRT-DS-REC-TT-240014 | AB | Z1 | 2024-09-30 | MTW-AS-C-LT-24.5780.0 | AB | Z1 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XG02-P2LC-110007 | 33 | [Condensate system (For Block 2)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2019-09-19 | 190191-FC STAMPED | FC | 7 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XG02-P2LCM-110005 | 34 | [Steam Drain System((For Block 2]_P&I DIAGRAM | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2019-09-19 | 190191-FC STAMPED | FC | 7 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XG02-P2PA-110002 | 35 | [Cooling Water system (For Block 2)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2019-09-19 | 190187-FC STAMPED | FC | 7 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XG02-P2PA-110008 | 36 | [Aux Cooling Water system (For Block 2)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2020-12-04 | 140/T/MRT/REC/XII/2020 | FC | 6 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XG02-P2PG-110009 | 37 | [Closed cooling water system (For Block 2)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2020-12-04 | 140/T/MRT/REC/XII/2020 | FC | 6 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XG02-P3LA-110006 | 38 | [Feedwater system (For Block 3, 4)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-12-09 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4969.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XG02-P3LBA-110003 | 39 | [Steam and Bypass system (For Block 3, 4)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-12-09 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4969.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XG02-P3LBG-110004 | 40 | [Aux Steam system (For Block 3, 4)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-12-09 | 2024-06-11 | 2024-06-11 | MRT-DS-REC-TT-240014 | AB | Z1 | 2024-06-25 | MTW-AS-C-LT-24.5422.0 | AB | Z1 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XG02-P3LC-110007 | 41 | [Condensate system (For Block 3, 4)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-12-09 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4969.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XG02-P3LCM-110005 | 42 | [Steam Drain System((For Block 3,4]_P&I DIAGRAM | FA | 2017-07-07 | 2017-12-09 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4969.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XG02-P3PA-110002 | 43 | [Cooling Water system (For Block 3, 4)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-12-09 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4969.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XG02-P3PA-110008 | 44 | [Aux Cooling Water system (For Block 3, 4)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-12-09 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4969.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XG02-P3PG-110009 | 45 | [Closed cooling water system (For Block 3, 4)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-12-09 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4969.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XG07-P2LBA-110300 | 46 | [Steam, Feedwater & condensate system (For Block 2)]_PROCESS FLOW DIAGRAM | FA | 2017-10-19 | 2018-01-17 | 2018-07-27 | 2018-08-01 | MRT-DS-REC-TT-180049-FC | FC | 2 | 2018-08-13 | 180049-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XG07-P3LBA-110300 | 47 | [Steam, Feedwater & condensate system (For Block 3, 4)]_PROCESS FLOW DIAGRAM | FA | 2017-10-19 | 2018-01-17 | 2018-07-27 | 2018-08-01 | MRT-DS-REC-TT-180049-FC | FC | 2 | 2018-08-13 | 180049-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XG07-P2PA-110002 | 48 | [Cooling Water System (For Block 2)]_PROCESS FLOW DIAGRAM | FA | 2017-10-19 | 2018-01-17 | 2018-07-27 | 2018-08-01 | MRT-DS-REC-TT-180049-FC | FC | 2 | 2018-08-13 | 180049-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XG07-P3PA-110002 | 49 | [Cooling Water System (For Block 3, 4)]_PROCESS FLOW DIAGRAM | FA | 2017-10-19 | 2018-01-17 | 2018-07-27 | 2018-08-01 | MRT-DS-REC-TT-180049-FC | FC | 2 | 2018-08-13 | 180049-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XG07-P2PA-110304 | 50 | [Aux & Closed Cooling Water System (For Block 2)]_PROCESS FLOW DIAGRAM | FA | 2017-10-19 | 2018-01-17 | 2018-07-27 | 2018-08-01 | MRT-DS-REC-TT-180049-FC | FC | 2 | 2018-08-13 | 180049-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XG07-P3PA-110304 | 51 | [Aux & Closed Cooling Water System (For Block 3, 4)]_PROCESS FLOW DIAGRAM | FA | 2017-10-19 | 2018-01-17 | 2018-07-27 | 2018-09-10 | MRT-DS-REC-TT-180147-FC | FC | 3 | 2018-09-14 | 180147-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XS00-P2LBA-110400 | 52 | [Steam and Bypass system (For Block 2)]_SYSTEM DESCRIPTION | FA | 2017-07-13 | 2017-11-10 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170123-FC | FC | 3 | 2018-09-22 | 170123-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XS00-P3LBA-110400 | 53 | [Steam and Bypass system (For Block 3, 4)]_SYSTEM DESCRIPTION | FA | 2017-07-13 | 2017-12-15 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170123-FC | FC | 3 | 2018-09-22 | 170123-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XS00-P2LBG-110401 | 54 | [Aux Steam System(For Block 2)]_SYSTEM DESCRIPTION | FA | 2017-07-13 | 2017-11-10 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170123-FC | FC | 3 | 2018-09-22 | 170123-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XS00-P3LBG-110401 | 55 | [Aux Steam System(For Block 3, 4)]_SYSTEM DESCRIPTION | FA | 2017-07-13 | 2017-12-15 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170123-FC | FC | 3 | 2018-09-22 | 170123-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XS00-P2LA-110402 | 56 | [Feedwater system (For Block 2)]_SYSTEM DESCRIPTION | FA | 2017-07-13 | 2017-11-10 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170123-FC | FC | 3 | 2018-09-22 | 170123-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XS00-P3LA-110402 | 57 | [Feedwater system (For Block 3, 4)]_SYSTEM DESCRIPTION | FA | 2017-07-13 | 2017-12-15 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170123-FC | FC | 3 | 2018-09-22 | 170123-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XS00-P2LC-110403 | 58 | [Condensate system (For Block 2)]_SYSTEM DESCRIPTION | FA | 2017-07-13 | 2017-11-10 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170123-FC | FC | 3 | 2018-09-22 | 170123-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XS00-P3LC-110403 | 59 | [Condensate system (For Block 3, 4)]_SYSTEM DESCRIPTION | FA | 2017-07-13 | 2017-12-15 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170123-FC | FC | 3 | 2018-09-22 | 170123-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XS00-P0GHC-110044 | 60 | [Make-up Water System]_SYSTEM DESCRIPTION | FA | 2017-10-25 | 2018-01-26 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170123-FC | FC | 2 | 2018-09-22 | 170123-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XS00-P2PA-110400 | 61 | [Cooling Water System (For Block 2)]_SYSTEM DESCRIPTION | FA | 2017-07-13 | 2017-11-10 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170123-FC | FC | 2 | 2018-09-22 | 170123-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XS00-P3PA-110400 | 62 | [Cooling Water System (For Block 3, 4)]_SYSTEM DESCRIPTION | FA | 2017-07-13 | 2017-12-15 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170123-FC | FC | 2 | 2018-09-22 | 170123-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XS00-P2PA-110404 | 63 | [Aux Cooling Water System (For Block 2)]_SYSTEM DESCRIPTION | FA | 2017-07-13 | 2017-11-10 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170096-FC | FC | 2 | 2018-09-22 | 170096-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XS00-P3PA-110404 | 64 | [Aux Cooling Water System (For Block 3, 4)]_SYSTEM DESCRIPTION | FA | 2017-07-13 | 2017-12-15 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170096-FC | FC | 2 | 2018-09-22 | 170096-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XS00-P2PG-110405 | 65 | [Closed cooling water system (For Block 2)]_SYSTEM DESCRIPTION | FA | 2017-07-13 | 2017-11-10 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170096-FC | FC | 2 | 2018-09-22 | 170096-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XS00-P3PG-110405 | 66 | [Closed cooling water system (For Block 3, 4)]_SYSTEM DESCRIPTION | FA | 2017-07-13 | 2017-12-15 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170096-FC | FC | 2 | 2018-09-22 | 170096-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XW03-P2LA-110500 | 67 | [HP&LP Feed Water Pump_Design (For Block 2)]_sizing Calculation | FA | 2017-07-11 | 2017-11-24 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170127-FC | FC | 2 | 2018-09-22 | 170127-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XW03-P3LA-110500 | 68 | [HP&LP Feed Water Pump_Design (For Block 3, 4)]_sizing Calculation | FA | 2017-07-11 | 2017-12-10 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170127-FC | FC | 2 | 2018-09-22 | 170127-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XW03-P2LC-110501 | 69 | [Condensate Extraction Pump_Design (For Block 2)]_sizing Calculation | FA | 2017-07-11 | 2017-11-24 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170127-FC | FC | 2 | 2018-09-22 | 170127-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XW03-P3LC-110501 | 70 | [Condensate Extraction Pump_Design (For Block 3, 4)]_sizing Calculation | FA | 2017-07-11 | 2017-12-10 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170127-FC | FC | 2 | 2018-09-22 | 170127-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XW03-P0GHC-110051 | 71 | [Make-up Water Pump_Design]_SIZING CALCULATION | FA | 2017-10-25 | 2018-01-26 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170127-FC | FC | 2 | 2018-09-22 | 170127-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XW03-P2PAC-113500 | 72 | [Circulating Water Pump(DHI)_Design (For Block 2)]_sizing Calculation | FA | 2017-07-11 | 2017-11-24 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170127-FC | FC | 2 | 2018-09-22 | 170127-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XW03-P3PAC-113500 | 73 | [Circulating Water Pump(DHI)_Design (For Block 3, 4)]_sizing Calculation | FA | 2017-07-11 | 2017-12-10 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170127-FC | FC | 2 | 2018-09-22 | 170127-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-XW03-P0MJ-110511 | 74 | [Diesel Generator_Design]_sizing Calculation | FA | 2017-08-14 | 2017-11-14 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-180036-FC | FC | 3 | 2018-09-21 | 180036-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-CN00-P2ZEN-110100 | 75 | [Plant Overall]_OPERATION PHILOSOPHY OF OVERALL PLANT (For Block 2) | FA | 2018-04-23 | 2018-08-31 | 2018-07-27 | 2018-09-17 | MRT-DS-REC-TT-180494-FC | FC | 1 | 2018-09-22 | 180494-FC STAMPED | FC | 1 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-CN00-P3ZEN-110100 | 76 | [Plant Overall]_OPERATION PHILOSOPHY OF OVERALL PLANT (For Block 3, 4) | FA | 2018-05-23 | 2018-08-31 | 2018-07-27 | 2018-08-15 | MRT-DS-REC-TT-180603-FC | FC | 2 | 2018-09-01 | 180603-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-CN00-P2ZEN-110102 | 77 | [Plant Overall]_PLANT START-UP AND SHUT-DOWN PROCEDURE (For Block 2) | FA | 2018-11-14 | 2019-02-14 | 2018-12-21 | 2018-12-26 | MRT-DS-REC-TT-180917-FC | FC | 0 | 2018-12-27 | 180917-FC STAMPED | FC | 0 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-CN00-P3ZEN-110102 | 78 | [Plant Overall]_PLANT START-UP AND SHUT-DOWN PROCEDURE (For Block 3,4) | FA | 2018-08-12 | 2018-12-10 | 2018-12-21 | 2018-12-26 | MRT-DS-REC-TT-180917-FC | FC | 2 | 2018-12-27 | 180917-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-YR01-P2ZEN-110103 | 79 | [Plant Overall]_STEAM BLOWING - OUT PROCEDURE (For Block 2) | FA | 2019-02-28 | 2019-06-21 | 2021-04-28 | 2021-04-28 | MRT-DS-REC-TT-210030 | FC | 2 | 2021-05-24 | 016/SER.00.01/LE/2021 | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-YR01-P3ZEN-110103 | 80 | [Plant Overall]_STEAM BLOWING - OUT PROCEDURE (For Block 3, 4) | FA | 2019-02-28 | 2019-06-21 | 2021-04-28 | 2021-04-28 | MRT-DS-REC-TT-210030 | FC | 2 | 2021-05-24 | 016/SER.00.01/LE/2021 | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-YK08-P2LB-111101 | 81 | [Bypass Valve & PRDS (For Block 2)]_OUTLINE DRAWING FOR BYPASS AND PRDS | FA | 2018-02-03 | 2018-05-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-09-15 | 180429-FC STAMPED | FC | 1 | A | MECHANICAL | BYPASS PRDS
DHI | 프로세스기술 | 김광희 | MRT-YK08-P3LB-111101 | 82 | [Bypass Valve & PRDS (For Block 3, 4)]_OUTLINE DRAWING FOR BYPASS AND PRDS | FA | 2018-02-03 | 2018-07-05 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6017.0 | AB | Z0 | A | MECHANICAL | BYPASS PRDS
DHI | 프로세스기술 | 김광희 | MRT-YT01-P2LB-111102 | 83 | [Bypass Valve & PRDS (For Block 2)]_DATA SHEET FOR BYPASS AND PRDS | FA | 2018-02-03 | 2018-05-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-09-15 | 180429-FC STAMPED | FC | 1 | A | MECHANICAL | BYPASS PRDS
DHI | 프로세스기술 | 김광희 | MRT-YT01-P3LB-111102 | 84 | [Bypass Valve & PRDS (For Block 3, 4)]_DATA SHEET FOR BYPASS AND PRDS | FA | 2018-02-03 | 2018-07-05 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6017.0 | AB | Z0 | A | MECHANICAL | BYPASS PRDS
DHI | 프로세스기술 | 김광희 | MRT-YK09-P2LB-111103 | 85 | [Bypass Valve & PRDS (For Block 2)]_Sectional drawing | FI | 2018-02-03 | 2018-05-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-09-15 | 180429-FC STAMPED | FC | 1 | A | MECHANICAL | BYPASS PRDS
DHI | 프로세스기술 | 김광희 | MRT-YK09-P3LB-111103 | 86 | [Bypass Valve & PRDS (For Block 3, 4)]_Sectional drawing | FI | 2018-02-03 | 2018-07-05 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6017.0 | AB | Z0 | A | MECHANICAL | BYPASS PRDS
DHI | 프로세스기술 | 김광희 | MRT-YL22-P2LB-111104 | 87 | [Bypass Valve & PRDS (For Block 2)]_Name Plate Drawing | FA | 2018-06-04 | 2018-09-04 | 2018-07-27 | 2018-08-29 | MRT-DS-REC-TT-180457-FC | FC | 0 | 2018-10-09 | 180457-FC STAMPED | FC | 0 | A | MECHANICAL | BYPASS PRDS
DHI | 프로세스기술 | 김광희 | MRT-YL22-P3LB-111104 | 88 | [Bypass Valve & PRDS (For Block 3, 4)]_Name Plate Drawing | FA | 2018-06-04 | 2018-09-04 | 2018-07-27 | 2018-08-29 | MRT-DS-REC-TT-180457-FC | FC | 0 | 2018-10-09 | 180457-FC STAMPED | FC | 0 | A | MECHANICAL | BYPASS PRDS
DHI | 프로세스기술 | 김광희 | MRT-YU04-P2LB-111105 | 89 | [Bypass Valve & PRDS (For Block 2)]_Pneumatic Diagram | FI | 2018-11-15 | 2019-02-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2019-01-12 | 180888-FC STAMPED | FC | 0 | A | I&C | BYPASS PRDS
DHI | 프로세스기술 | 김광희 | MRT-YU04-P3LB-111105 | 90 | [Bypass Valve & PRDS (For Block 3, 4)]_Pneumatic Diagram | FI | 2018-11-15 | 2019-02-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-02-19 | MTW-AS-C-LT-24.4911.0 | AB | Z0 | A | I&C | BYPASS PRDS
DHI | 프로세스기술 | 김광희 | MRT-YV02-P2LB-111106 | 91 | [Bypass Valve & PRDS (For Block 2)]_Wiring Diagram | FI | 2018-11-15 | 2019-02-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2019-01-12 | 180888-FC STAMPED | FC | 0 | A | ELECTRICAL | BYPASS PRDS
DHI | 프로세스기술 | 김광희 | MRT-YV02-P3LB-111106 | 92 | [Bypass Valve & PRDS (For Block 3, 4)]_Wiring Diagram | FI | 2018-11-15 | 2019-02-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-02-19 | MTW-AS-C-LT-24.4911.0 | AB | Z0 | A | ELECTRICAL | BYPASS PRDS
DHI | 프로세스기술 | 김광희 | MRT-DC04-P2LB-1111301 | 93 | [Bypass Valve & PRDS (For Block 2)]_O&M Manual | FI | 2018-11-30 | 2019-02-28 | 2019-01-14 | 2019-01-14 | MRT-DS-REC-TT-180940-FC | FC | 0 | 2019-01-15 | 180940-FC STAMPED | FC | 0 | A | SUPPORT | BYPASS PRDS
DHI | 프로세스기술 | 김광희 | MRT-DC04-P3LB-1111301 | 94 | [Bypass Valve & PRDS (For Block 3, 4)]_O&M Manual | FI | 2018-11-30 | 2019-02-28 | 2019-01-14 | 2019-01-14 | MRT-DS-REC-TT-180940-FC | FC | 0 | 2019-01-15 | 180940-FC STAMPED | FC | 0 | A | SUPPORT | BYPASS PRDS
DHI | 프로세스기술 | 김광희 | MRT-YD00-P2PAB-113251 | 95 | [ASCS (For Block 2)]_GENERAL ARRANGEMENT DRAWING FOR AUTO SELF-CLEANING STRAINER | FA | 2018-03-09 | 2018-07-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-12-10 | 180814-FC STAMPED | FC | 4 | A | MECHANICAL | CCW ASCS
DHI | 프로세스기술 | 김광희 | MRT-YD00-P3PAB-113251 | 96 | [ASCS (For Block 3, 4)]_GENERAL ARRANGEMENT DRAWING FOR AUTO SELF-CLEANING STRAINER | FA | 2018-03-09 | 2018-07-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4980.0 | AB | Z0 | A | MECHANICAL | CCW ASCS
DHI | 프로세스기술 | 김광희 | MRT-YT01-P2PAB-113252 | 97 | [ASCS (For Block 2)]_DATA SHEET FOR AUTO SELF-CLEANING STRAINER | FA | 2018-03-09 | 2018-07-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-09-28 | 180576-FC STAMPED | FC | 3 | A | MECHANICAL | CCW ASCS
DHI | 프로세스기술 | 김광희 | MRT-YT01-P3PAB-113252 | 98 | [ASCS (For Block 3, 4)]_DATA SHEET FOR AUTO SELF-CLEANING STRAINER | FA | 2018-03-09 | 2018-07-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4980.0 | AB | Z0 | A | MECHANICAL | CCW ASCS
DHI | 프로세스기술 | 김광희 | MRT-XG02-P2PAB-113253 | 99 | [ASCS (For Block 2)]_P&I DIAGRAM FOR AUTO SELF-CLEANING STRAINER | FA | 2018-03-09 | 2018-07-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-12-10 | 180814-FC STAMPED | FC | 4 | A | MECHANICAL | CCW ASCS
DHI | 프로세스기술 | 김광희 | MRT-XG02-P3PAB-113253 | 100 | [ASCS (For Block 3, 4)]_P&I DIAGRAM FOR AUTO SELF-CLEANING STRAINER | FA | 2018-03-09 | 2018-07-15 | 2024-10-23 | 2024-10-23 | MRT-DS-REC-TT-240019 | AB | Z1 | 2024-11-08 | MTW-AS-C-LT-24.5927.0 | AB | Z1 | A | MECHANICAL | CCW ASCS
DHI | 프로세스기술 | 김광희 | MRT-YD00-P2PAB-113263 | 101 | [ASCS (For Block 2)]_CONTROL PANEL OUTLINE AND WIRING DRAWING FOR AUTO SELF-CLEANING STRAINER | FI | 2018-11-07 | 2019-02-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-12-17 | 180868-FC STAMPED | FC | 0 | A | I&C | CCW ASCS
DHI | 프로세스기술 | 김광희 | MRT-YD00-P3PAB-113263 | 102 | [ASCS (For Block 3, 4)]_CONTROL PANEL OUTLINE AND WIRING DRAWING FOR AUTO SELF-CLEANING STRAINER | FI | 2018-11-07 | 2019-02-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-07-01 | MTW-AS-C-LT-24.5459.0 | AB | Z0 | A | I&C | CCW ASCS
DHI | 프로세스기술 | 김광희 | MRT-CQ02-P2PAB-113267 | 103 | [ASCS (For Block 2)]_OPERATION & MAINTENANCE MANUAL | FI | 2018-11-07 | 2019-02-07 | 2018-12-10 | 2018-12-11 | MRT-DS-REC-TT-180868-FC | FC | 0 | 2018-12-17 | 180868-FC STAMPED | FC | 0 | A | SUPPORT | CCW ASCS
DHI | 프로세스기술 | 김광희 | MRT-CQ02-P3PAB-113267 | 104 | [ASCS (For Block 3, 4)]_OPERATION & MAINTENANCE MANUAL | FI | 2018-11-07 | 2019-02-07 | 2018-12-10 | 2018-12-11 | MRT-DS-REC-TT-180868-FC | FC | 0 | 2018-12-17 | 180868-FC STAMPED | FC | 0 | A | SUPPORT | CCW ASCS
DHI | 프로세스기술 | 김광희 | MRT-YT01-P2PGB-113200 | 105 | [CCW Heat Exchanger (For Block 2)]_DATA SHEET FOR PLATE TYPE HEAT EXCHANGER | FA | 2018-02-01 | 2018-05-04 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-08-13 | 180212-FC STAMPED | FC | 2 | A | MECHANICAL | CCW HX
DHI | 프로세스기술 | 김광희 | MRT-YT01-P3PGB-113200 | 106 | [CCW Heat Exchanger (For Block 3, 4)]_DATA SHEET FOR PLATE TYPE HEAT EXCHANGER | FA | 2018-02-01 | 2018-07-03 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4980.0 | AB | Z0 | A | MECHANICAL | CCW HX
DHI | 프로세스기술 | 김광희 | MRT-YD00-P2PGB-113201 | 107 | [CCW Heat Exchanger (For Block 2)]_OUTLINE DRAWING FOR PLATE TYPE HEAT EXCHANGER | FI | 2018-02-01 | 2018-05-04 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-08-29 | 180385-FC STAMPED | FC | 3 | A | MECHANICAL | CCW HX
DHI | 프로세스기술 | 김광희 | MRT-YD00-P3PGB-113201 | 108 | [CCW Heat Exchanger (For Block 3, 4)]_OUTLINE DRAWING FOR PLATE TYPE HEAT EXCHANGER | FI | 2018-02-01 | 2018-07-03 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4980.0 | AB | Z0 | A | MECHANICAL | CCW HX
DHI | 프로세스기술 | 김광희 | MRT-CQ02-P2PGB-113203 | 109 | [CCW Heat Exchanger (For Block 2)]_Installation & O&M MANUAL | FI | 2018-11-07 | 2019-02-07 | 2018-12-10 | 2018-12-11 | MRT-DS-REC-TT-180868-FC | FC | 0 | 2018-12-17 | 180868-FC STAMPED | FC | 0 | A | SUPPORT | CCW HX
DHI | 프로세스기술 | 김광희 | MRT-CQ02-P3PGB-113203 | 110 | [CCW Heat Exchanger (For Block 3, 4)]_Installation & O&M MANUAL | FI | 2018-11-07 | 2019-02-07 | 2018-12-10 | 2018-12-11 | MRT-DS-REC-TT-180868-FC | FC | 0 | 2018-12-17 | 180868-FC STAMPED | FC | 0 | A | SUPPORT | CCW HX
DHI | 프로세스기술 | 김광희 | MRT-YD00-P2PGB-113101 | 111 | [CCWP (For Block 2)]_GENERAL ARRANGEMENT DRAWING FOR CLOSED COOLING WATER PUMP | FA | 2018-02-04 | 2018-05-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-09-28 | 180577-FC STAMPED | FC | 2 | A | MECHANICAL | CCWP
DHI | 프로세스기술 | 김광희 | MRT-YD00-P3PGB-113101 | 112 | [CCWP (For Block 3, 4)]_GENERAL ARRANGEMENT DRAWING FOR CLOSED COOLING WATER PUMP | FA | 2018-02-04 | 2018-07-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4980.0 | AB | Z0 | A | MECHANICAL | CCWP
DHI | 프로세스기술 | 김광희 | MRT-YT01-P2PGB-113102 | 113 | [CCWP (For Block 2)]_DATA SHEET FOR CLOSED COOLING WATER PUMP | FA | 2018-02-04 | 2018-05-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-09-03 | 180252-FC STAMPED | FC | 1 | A | MECHANICAL | CCWP
DHI | 프로세스기술 | 김광희 | MRT-YT01-P3PGB-113102 | 114 | [CCWP (For Block 3, 4)]_DATA SHEET FOR CLOSED COOLING WATER PUMP | FA | 2018-02-04 | 2018-07-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4980.0 | AB | Z0 | A | MECHANICAL | CCWP
DHI | 프로세스기술 | 김광희 | MRT-YK10-P2PGB-113103 | 115 | [CCWP (For Block 2)]_Pump Sectional Drawing | FI | 2018-03-06 | 2018-06-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-08-25 | 180386-FC STAMPED | FC | 1 | A | MECHANICAL | CCWP
DHI | 프로세스기술 | 김광희 | MRT-YK10-P3PGB-113103 | 116 | [CCWP (For Block 3, 4)]_Pump Sectional Drawing | FI | 2018-03-06 | 2018-08-05 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4980.0 | AB | Z0 | A | MECHANICAL | CCWP
DHI | 프로세스기술 | 김광희 | MRT-YT01-P2PGB-113104 | 117 | [CCWP (For Block 2)]_DATA SHEET FOR CLOSED COOLING WATER PUMP MOTOR | FA | 2018-03-06 | 2018-06-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-10-23 | 180787-FC STAMPED | FC | 3 | A | ELECTRICAL | CCWP
DHI | 프로세스기술 | 김광희 | MRT-YT01-P3PGB-113104 | 118 | [CCWP (For Block 3, 4)]_DATA SHEET FOR CLOSED COOLING WATER PUMP MOTOR | FA | 2018-03-06 | 2018-08-05 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4980.0 | AB | Z0 | A | ELECTRICAL | CCWP
DHI | 프로세스기술 | 김광희 | MRT-YD00-P2PGB-113105 | 119 | [CCWP (For Block 2)]_OUTLINE DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | FA | 2018-03-06 | 2018-06-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-10-23 | 180787-FC STAMPED | FC | 3 | A | ELECTRICAL | CCWP
DHI | 프로세스기술 | 김광희 | MRT-YD00-P3PGB-113105 | 120 | [CCWP (For Block 3, 4)]_OUTLINE DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | FA | 2018-03-06 | 2018-08-05 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4980.0 | AB | Z0 | A | ELECTRICAL | CCWP
DHI | 프로세스기술 | 김광희 | MRT-YD00-P2PGB-113107 | 121 | [CCWP (For Block 2)]_MAIN TERNINAL BOX DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | FI | 2018-10-31 | 2019-01-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2019-01-31 | 180889-FC STAMPED | FC | 1 | A | ELECTRICAL | CCWP
DHI | 프로세스기술 | 김광희 | MRT-YD00-P3PGB-113107 | 122 | [CCWP (For Block 3, 4)]_MAIN TERNINAL BOX DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | FI | 2018-10-31 | 2019-01-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-07-01 | MTW-AS-C-LT-24.5459.0 | AB | Z0 | A | ELECTRICAL | CCWP
DHI | 프로세스기술 | 김광희 | MRT-XW03-P2PGB-113110 | 123 | [CCWP (For Block 2)]_SIZING CALCULATION FOR CLOSED COOLING WATER PUMP | FA | 2017-08-01 | 2017-11-01 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170127-FC | FC | 2 | 2018-09-22 | 170127-FC STAMPED | FC | 2 | A | MECHANICAL | CCWP
DHI | 프로세스기술 | 김광희 | MRT-XW03-P3PGB-113110 | 124 | [CCWP (For Block 3, 4)]_SIZING CALCULATION FOR CLOSED COOLING WATER PUMP | FA | 2017-08-01 | 2017-12-31 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170127-FC | FC | 2 | 2018-09-22 | 170127-FC STAMPED | FC | 2 | A | MECHANICAL | CCWP
DHI | 프로세스기술 | 김광희 | MRT-CQ02-P2PGB-113116 | 125 | [CCWP (For Block 2)]_INSTALLATION MANUAL | FI | 2018-10-31 | 2019-01-31 | 2018-11-12 | 2018-12-03 | MRT-DS-REC-TT-180851-FC | FC | 0 | 2018-12-07 | 180851-FC STAMPED | FC | 0 | A | SUPPORT | CCWP
DHI | 프로세스기술 | 김광희 | MRT-CQ02-P3PGB-113116 | 126 | [CCWP (For Block 3, 4)]_INSTALLATION MANUAL | FI | 2018-10-31 | 2019-01-31 | 2018-11-12 | 2018-12-03 | MRT-DS-REC-TT-180851-FC | FC | 0 | 2018-12-07 | 180851-FC STAMPED | FC | 0 | A | SUPPORT | CCWP
DHI | 프로세스기술 | 김광희 | MRT-CQ02-P2PGB-113117 | 127 | [CCWP (For Block 2)]_OPERATION & MAINTENANCE MANUAL | FI | 2018-10-31 | 2019-01-31 | 2018-11-12 | 2018-12-03 | MRT-DS-REC-TT-180851-FC | FC | 0 | 2018-12-07 | 180851-FC STAMPED | FC | 0 | A | SUPPORT | CCWP
DHI | 프로세스기술 | 김광희 | MRT-CQ02-P3PGB-113117 | 128 | [CCWP (For Block 3, 4)]_OPERATION & MAINTENANCE MANUAL | FI | 2018-10-31 | 2019-01-31 | 2018-11-12 | 2018-12-03 | MRT-DS-REC-TT-180851-FC | FC | 0 | 2018-12-07 | 180851-FC STAMPED | FC | 0 | A | SUPPORT | CCWP
DHI | 프로세스기술 | 김광희 | MRT-CQ02-P2PGB-113118 | 129 | [CCWP (For Block 2)]_COMMISSIONING MANUAL | FI | 2018-10-31 | 2019-01-31 | 2018-11-12 | 2018-12-03 | MRT-DS-REC-TT-180851-FC | FC | 0 | 2021-01-14 | 001/SER.00.01/LE/2021 | FC | 0 | I | SUPPORT | CCWP
DHI | 프로세스기술 | 김광희 | MRT-CQ02-P3PGB-113118 | 130 | [CCWP (For Block 3, 4)]_COMMISSIONING MANUAL | FI | 2018-10-31 | 2019-01-31 | 2018-11-12 | 2018-12-03 | MRT-DS-REC-TT-180851-FC | FC | 0 | 2021-01-14 | 001/SER.00.01/LE/2021 | FC | 0 | I | SUPPORT | CCWP
DHI | 프로세스기술 | 김광희 | MRT-YD00-P2ZEN-113300 | 133 | [MOV (Gate & Globe)(DHI) (For Block 2)]_OUTLINE DRAWING FOR MOV (G&G) | FA | 2018-06-20 | 2018-09-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-10-22 | 180618-FC STAMPED | FC | 2 | A | MECHANICAL | MOV
DHI | 프로세스기술 | 김광희 | MRT-YD00-P3ZEN-113300 | 134 | [MOV (Gate & Globe)(DHI) (For Block 3, 4)]_OUTLINE DRAWING FOR MOV (G&G) | FA | 2018-06-20 | 2018-11-19 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-07-01 | MTW-AS-C-LT-24.5459.0 | AB | Z0 | A | MECHANICAL | MOV
DHI | 프로세스기술 | 김광희 | MRT-YT01-P2ZEN-113301 | 135 | [MOV (Gate & Globe)(DHI) (For Block 2)]_DATA SHEET FOR MOV (G&G) | FA | 2018-06-20 | 2018-09-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-09-12 | 180619-FC STAMPED | FC | 2 | A | MECHANICAL | MOV
DHI | 프로세스기술 | 김광희 | MRT-YT01-P3ZEN-113301 | 136 | [MOV (Gate & Globe)(DHI) (For Block 3, 4)]_DATA SHEET FOR MOV (G&G) | FA | 2018-06-20 | 2018-11-19 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-07-01 | MTW-AS-C-LT-24.5459.0 | AB | Z0 | A | MECHANICAL | MOV
DHI | 프로세스기술 | 김광희 | MRT-CT00-P2ZEN-113300 | 137 | [MOV (GATE & GLOBE)(DHI) (For Block 2)]_OPERATION & MAINTENANCE MANUAL | FI | 2018-11-15 | 2019-02-15 | 2018-12-04 | 2018-12-04 | MRT-DS-REC-TT-180859-FC | FC | 0 | 2018-12-12 | 180859-FC STAMPED | FC | 0 | A | SUPPORT | MOV
DHI | 프로세스기술 | 김광희 | MRT-CT00-P3ZEN-113300 | 138 | [MOV (GATE & GLOBE)(DHI) (For Block 3, 4)]_OPERATION & MAINTENANCE MANUAL | FI | 2018-11-15 | 2019-02-15 | 2018-12-04 | 2018-12-04 | MRT-DS-REC-TT-180859-FC | FC | 0 | 2018-12-12 | 180859-FC STAMPED | FC | 0 | A | SUPPORT | MOV
DHI | 프로세스기술 | 김광희 | MRT-YD00-P2ZEN-113400 | 139 | [MOV (Butterfly)(DHI) (For Block 2)]_OUTLINE DRAWING FOR MOV (BUTTERFLY) | FA | 2018-06-20 | 2018-09-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-10-16 | 180736-FC STAMPED | FC | 2 | A | MECHANICAL | MOV
DHI | 프로세스기술 | 김광희 | MRT-YD00-P3ZEN-113400 | 140 | [MOV (Butterfly)(DHI) (For Block 3, 4)]_OUTLINE DRAWING FOR MOV (BUTTERFLY) | FA | 2018-06-20 | 2018-11-19 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-07-01 | MTW-AS-C-LT-24.5459.0 | AB | Z0 | A | MECHANICAL | MOV
DHI | 프로세스기술 | 김광희 | MRT-YT01-P2ZEN-113401 | 141 | [MOV (Butterfly)(DHI) (For Block 2)]_DATA SHEET FOR MOV (BUTTERFLY) | FA | 2018-06-20 | 2018-09-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-10-16 | 180736-FC STAMPED | FC | 2 | A | MECHANICAL | MOV
DHI | 프로세스기술 | 김광희 | MRT-YT01-P3ZEN-113401 | 142 | [MOV (Butterfly)(DHI) (For Block 3, 4)]_DATA SHEET FOR MOV (BUTTERFLY) | FA | 2018-06-20 | 2018-11-19 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-07-01 | MTW-AS-C-LT-24.5459.0 | AB | Z0 | A | MECHANICAL | MOV
DHI | 프로세스기술 | 김광희 | MRT-CT00-P2ZEN-113400 | 143 | [MOV (Butterfly)(DHI) (For Block 2)]_OPERATION & MAINTENANCE MANUAL | FI | 2018-11-15 | 2019-02-15 | 2018-12-04 | 2018-12-04 | MRT-DS-REC-TT-180860-FC | FC | 0 | 2018-12-12 | 180860-FC STAMPED | FC | 0 | A | SUPPORT | MOV
DHI | 프로세스기술 | 김광희 | MRT-CT00-P3ZEN-113400 | 144 | [MOV (Butterfly)(DHI) (For Block 3, 4)]_OPERATION & MAINTENANCE MANUAL | FI | 2018-11-15 | 2019-02-15 | 2018-12-04 | 2018-12-04 | MRT-DS-REC-TT-180860-FC | FC | 0 | 2018-12-12 | 180860-FC STAMPED | FC | 0 | A | SUPPORT | MOV
DHI | 프로세스기술 | 김광희 | MRT-XG02-P0QJA-110010 | 145 | [N2 Gas system]_P&ID | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2020-12-04 | 140/T/MRT/REC/XII/2020 | FC | 5 | A | MECHANICAL | N2 GAS SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-YD00-P0QJA-111101 | 146 | [N2 Gas System]_General Arrangement Drawing | FA | 2018-06-26 | 2018-09-26 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-10-05 | 180544-FC STAMPED | FC | 0 | A | MECHANICAL | N2 GAS SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-YD00-P0QJA-111601 | 147 | [N2 Gas system] O&M Manual | FI | 2018-11-02 | 2019-02-08 | 2018-11-29 | 2018-12-07 | MRT-DS-REC-TT-180862-FC | FC | 0 | 2018-12-11 | 180862-FC STAMPED | FC | 0 | A | SUPPORT | N2 GAS SYSTEM
DHI | 프로세스기술 | 김광희 | MRT-YD00-P2ZEN-113500 | 148 | [COMBINED NONRETURN VALVE(DHI) (For Block 2)]_OUTLINE DRAWING FOR C-NRV | FA | 2018-06-20 | 2018-09-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-10-31 | 180737-FC STAMPED | FC | 2 | A | MECHANICAL | NRV
DHI | 프로세스기술 | 김광희 | MRT-YD00-P3ZEN-113500 | 149 | [COMBINED NONRETURN VALVE(DHI) (For Block 3, 4)]_OUTLINE DRAWING FOR C-NRV | FA | 2018-06-20 | 2018-09-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-06-24 | MTW-AS-C-LT-24.5412.0 | AB | Z0 | A | MECHANICAL | NRV
DHI | 프로세스기술 | 김광희 | MRT-YT01-P2ZEN-113501 | 150 | [COMBINED NONRETURN VALVE(DHI) (For Block 2)]_DATA SHEET FOR C-NRV | FA | 2018-06-20 | 2018-09-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-10-31 | 180737-FC STAMPED | FC | 2 | A | MECHANICAL | NRV
DHI | 프로세스기술 | 김광희 | MRT-YT01-P3ZEN-113501 | 151 | [COMBINED NONRETURN VALVE(DHI) (For Block 3, 4)]_DATA SHEET FOR C-NRV | FA | 2018-06-20 | 2018-09-20 | 2024-10-23 | 2024-10-23 | MRT-DS-REC-TT-240019 | AB | Z1 | 2024-11-08 | MTW-AS-C-LT-24.5927.0 | AB | Z1 | A | MECHANICAL | NRV
DHI | 프로세스기술 | 김광희 | MRT-CT00-P2ZEN-113500 | 152 | [COMBINED NONRETURN VALVE(DHI) (For Block 2)]_OPERATION & MAINTENANCE MANUAL | FI | 2018-11-15 | 2019-02-15 | 2018-11-29 | 2018-12-07 | MRT-DS-REC-TT-180861-FC | FC | 0 | 2018-12-13 | 180861-FC STAMPED | FC | 0 | A | SUPPORT | NRV
DHI | 프로세스기술 | 김광희 | MRT-CT00-P3ZEN-113500 | 153 | [COMBINED NONRETURN VALVE(DHI) (For Block 3, 4)]_OPERATION & MAINTENANCE MANUAL | FI | 2018-11-15 | 2019-02-15 | 2018-11-29 | 2018-12-07 | MRT-DS-REC-TT-180861-FC | FC | 0 | 2018-12-13 | 180861-FC STAMPED | FC | 0 | A | SUPPORT | NRV
DHI | 프로세스기술 | 김광희 | MRT-YK08-P2LBG-111300 | 154 | [Silencer (For Block 2)]_OUTLINE DRAWING FOR Silencer | FI | 2018-06-20 | 2018-09-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2020-03-02 | 200023-FC STAMPED | FC | 3 | I | MECHANICAL | SILENCER
DHI | 프로세스기술 | 김광희 | MRT-YK08-P3LBG-111300 | 155 | [Silencer (For Block 3, 4)]_OUTLINE DRAWING FOR Silencer | FI | 2018-06-20 | 2018-11-19 | 2024-10-23 | 2024-10-23 | MRT-DS-REC-TT-240019 | AB | Z1 | 2024-11-08 | MTW-AS-C-LT-24.5927.0 | AB | Z1 | A | MECHANICAL | SILENCER
DHI | 프로세스기술 | 김광희 | MRT-YT01-P2LBG-111301 | 156 | [Silencer (For Block 2)]_DATA SHEET FOR Silencer | FA | 2018-06-20 | 2018-09-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-10-05 | 180536-FC STAMPED | FC | 1 | A | MECHANICAL | SILENCER
DHI | 프로세스기술 | 김광희 | MRT-YT01-P3LBG-111301 | 157 | [Silencer (For Block 3, 4)]_DATA SHEET FOR Silencer | FA | 2018-06-20 | 2018-11-19 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-06-24 | MTW-AS-C-LT-24.5412.0 | AB | Z0 | A | MECHANICAL | SILENCER
DHI | 프로세스기술 | 김광희 | MRT-YK08-P2ZEN-111200 | 158 | [Safety Relief Valve(DHI) (For Block 2)]_OUTLINE DRAWING FOR SAFETY AND RELIEF VALVE | FI | 2018-06-20 | 2018-09-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-08-25 | 180370-FC STAMPED | FC | 1 | A | MECHANICAL | SRV
DHI | 프로세스기술 | 김광희 | MRT-YK08-P3ZEN-111200 | 159 | [Safety Relief Valve(DHI) (For Block 3, 4)]_OUTLINE DRAWING FOR SAFETY AND RELIEF VALVE | FI | 2018-06-20 | 2018-11-19 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-06-24 | MTW-AS-C-LT-24.5412.0 | AB | Z0 | A | MECHANICAL | SRV
DHI | 프로세스기술 | 김광희 | MRT-YT01-P2ZEN-111201 | 160 | [Safety Relief Valve(DHI) (For Block 2)]_DATA SHEET FOR SAFETY AND RELIEF VALVE | FA | 2018-06-20 | 2018-09-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-08-25 | 180370-FC STAMPED | FC | 1 | A | MECHANICAL | SRV
DHI | 프로세스기술 | 김광희 | MRT-YT01-P3ZEN-111201 | 161 | [Safety Relief Valve(DHI) (For Block 3, 4)]_DATA SHEET FOR SAFETY AND RELIEF VALVE | FA | 2018-06-20 | 2018-11-19 | 2024-11-11 | 2024-11-11 | MRT-DS-REC-TT-240025 | AB | Z2 | 2024-11-21 | MTW-AS-C-LT-24.5975.0 | AB | Z2 | A | MECHANICAL | SRV
DHI | 플랜트기술 | 류두현 | MRT-XG02-P2SCA-120004 | 162 | [Compressed air system (DHI for Block 2)]_P&I DIAGRAM FOR COMPRESSED AIR SYSTEM | FA | 2017-07-07 | 2017-11-05 | 2024-11-19 | 2024-11-19 | MRT-DS-REC-TT-240036 | AB | Z1 | 2024-11-29 | MTW-AS-C-LT-24.6005.0 | AB | Z1 | A | MECHANICAL | BOP SYSTEM
DHI | 플랜트기술 | 류두현 | MRT-XG02-P3SCA-120004 | 163 | [Compressed air system (DHI for Block 3, 4)]_P&I DIAGRAM FOR COMPRESSED AIR SYSTEM | FA | 2017-07-07 | 2017-12-04 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220029 | AB | Z0 | 2024-11-18 | MTW-AS-C-LT-23.4183.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM
DHI | 플랜트기술 | 류두현 | MRT-XG02-P2SCA-120005 | 164 | [Compressed air system (DHI for Block 2)]_P&I DIAGRAM FOR INSTRUMENT AIR SYSTEM | FA | 2017-07-07 | 2017-11-05 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220029 | AB | Z0 | 2024-11-18 | MTW-AS-C-LT-23.4183.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM
DHI | 플랜트기술 | 류두현 | MRT-XG02-P3SCA-120005 | 165 | [Compressed air system (DHI for Block 3, 4)]_P&I DIAGRAM FOR INSTRUMENT AIR SYSTEM | FA | 2017-07-07 | 2017-12-04 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220029 | AB | Z0 | 2024-11-18 | MTW-AS-C-LT-23.4183.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM
DHI | 플랜트기술 | 류두현 | MRT-XG02-P2SCA-120006 | 166 | [Compressed air system (DHI for Block 2)]_P&I DIAGRAM FOR SERVICE AIR SYSTEM | FA | 2017-07-07 | 2017-11-05 | 2025-02-07 | 2025-02-07 | MRT-DS-REC-TT-250006 | AB | Z3 | 2025-02-17 | MTW-AS-C-LT-25.6202.0 | AB | Z3 | A | MECHANICAL | BOP SYSTEM
DHI | 플랜트기술 | 류두현 | MRT-XG02-P3SCA-120006 | 167 | [Compressed air system (DHI for Block 3, 4)]_P&I DIAGRAM FOR SERVICE AIR SYSTEM | FA | 2017-07-07 | 2017-12-04 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220029 | AB | Z0 | 2024-11-18 | MTW-AS-C-LT-23.4183.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM
DHI | 플랜트기술 | 류두현 | MRT-XS00-P2SCA-120015 | 168 | [Compressed air system (DHI for Block 2)]_SYSTEM DESCRIPTION FOR COMPRESSED AIR SYSTEM | FA | 2017-07-07 | 2017-11-05 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170090-FC | FC | 2 | 2018-09-22 | 170090-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 플랜트기술 | 류두현 | MRT-XS00-P3SCA-120015 | 169 | [Compressed air system (DHI for Block 3,4)]_SYSTEM DESCRIPTION FOR COMPRESSED AIR SYSTEM | FA | 2017-07-07 | 2017-12-05 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170090-FC | FC | 2 | 2018-09-22 | 170090-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 플랜트기술 | 류두현 | MRT-XW03-P2SCA-120017 | 170 | [Compressed air system (DHI for Block 2)]_SIZING CALCULATION_COMPRESSED AIR SYSTEM | FA | 2017-08-07 | 2017-11-05 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170111-FC | FC | 2 | 2018-09-22 | 170111-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 플랜트기술 | 류두현 | MRT-XW03-P3SCA-120017 | 171 | [Compressed air system (DHI for Block 3, 4)]_SIZING CALCULATION_COMPRESSED AIR SYSTEM | FA | 2017-08-07 | 2018-01-04 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170111-FC | FC | 2 | 2018-09-22 | 170111-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 플랜트기술 | 오광일 | MRT-XS00-P2MAV-120053 | 172 | [Clean & Dirty Oil Storage System(For Block 2)]_System Description | FA | 2017-07-07 | 2017-11-07 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-180032-FC | FC | 3 | 2018-09-24 | 180032-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM
DHI | 플랜트기술 | 오광일 | MRT-XS00-P3MAV-120053 | 173 | [Clean & Dirty Oil Storage System(For Block 3,4)]_System Description | FA | 2017-07-07 | 2017-12-07 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-180032-FC | FC | 3 | 2018-09-24 | 180032-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM
DHI | 플랜트기술 | 오광일 | MRT-XG02-P2MAV-120054 | 174 | [Clean & Dirty Oil Storage System(For Block 2)]_P&ID | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220029 | AB | Z0 | 2024-11-18 | MTW-AS-C-LT-23.4183.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM
DHI | 플랜트기술 | 오광일 | MRT-XG02-P3MAV-120054 | 175 | [Clean & Dirty Oil Storage System(For Block 3,4)]_P&ID | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220029 | AB | Z0 | 2024-11-18 | MTW-AS-C-LT-23.4183.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM
DHI | 플랜트기술 | 이태훈 | MRT-XG02-P0GHD-120001 | 176 | [Service water distribution system]_P&ID | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220029 | AB | Z0 | 2024-11-18 | MTW-AS-C-LT-23.4183.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM
DHI | 플랜트기술 | 이태훈 | MRT-XG02-P0GKC-120001 | 177 | [Potable water distribution system]_P&ID | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220029 | AB | Z0 | 2024-11-18 | MTW-AS-C-LT-23.4183.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM
DHI | 플랜트기술 | 이태훈 | MRT-XS00-P0GHD-120001 | 178 | [Service water distribution system]_system description | FA | 2017-07-07 | 2017-11-07 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170089-FC | FC | 2 | 2018-10-02 | 170089-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 플랜트기술 | 이태훈 | MRT-XS00-P0GKC-120001 | 179 | [Potable water distribution system]_system description | FA | 2017-07-07 | 2017-11-07 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170089-FC | FC | 2 | 2018-10-02 | 170089-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 플랜트기술 | 오광일 | MRT-XW03-P2MAV-120001 | 180 | [General Service Pump (oil) DHI for Block 2_Design]_sizing Calculation | FA | 2018-02-28 | 2018-05-29 | 2018-07-27 | 2018-08-27 | MRT-DS-REC-TT-180329-FC | FC | 1 | 2018-09-06 | 180329-FC STAMPED | FC | 1 | A | MECHANICAL | BOP SYSTEM
DHI | 플랜트기술 | 오광일 | MRT-XW03-P3MAV-130001 | 181 | [General Service Pump (oil) DHI for Block 3, 4_Design]_sizing Calculation | FA | 2018-02-28 | 2018-07-29 | 2018-07-27 | 2018-08-27 | MRT-DS-REC-TT-180329-FC | FC | 1 | 2018-09-06 | 180329-FC STAMPED | FC | 1 | A | MECHANICAL | BOP SYSTEM
DHI | 플랜트기술 | 이태훈 | MRT-XW03-P3GHD-120001 | 182 | [Service Water Pump (DHI for Block 3,4)]_SIZING CALCULATION | FA | 2017-11-30 | 2018-02-28 | 2018-07-27 | 2018-08-01 | MRT-DS-REC-TT-180149-FC | FC | 2 | 2018-08-13 | 180149-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM
DHI | 플랜트기술 | 이태훈 | MRT-XK00-P2GM-128508 | 183 | [Sump Pump (DHI for Block 2)]_SUMP PUMP_Sizing Calculation | FA | 2017-11-24 | 2018-03-24 | 2018-07-27 | 2018-08-29 | MRT-DS-REC-TT-180547-FC | FC | 3 | 2018-10-23 | 180547-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM
DHI | 플랜트기술 | 이태훈 | MRT-XK00-P3GM-128508 | 184 | [Sump Pump (DHI for Block 3, 4)]_SUMP PUMP_Sizing Calculation | FA | 2017-11-24 | 2018-03-24 | 2018-07-27 | 2018-08-29 | MRT-DS-REC-TT-180547-FC | FC | 3 | 2018-10-23 | 180547-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM
DHI | 플랜트기술 | 이태훈 | MRT-XG07-P0ZEN-120050 | 185 | [Plant Overall]_WATER BALANCE DIAGRAM | FA | 2017-06-09 | 2017-09-07 | 2018-09-14 | 2018-10-10 | MRT-DS-REC-TT-180733-FC | FC | 4 | 2018-10-16 | 180733-FC STAMPED | FC | 4 | A | MECHANICAL | BOP SYSTEM
DHI | 플랜트기술 | 오슬기 | MRT-YQ03-P2LB-122088 | 186 | [HRSG(For Block 2)]_HRSG_PERFORMANCE AND OPERATIONAL DATA | FA | 2017-11-01 | 2018-01-30 | 2018-07-27 | 2018-08-27 | MRT-DS-REC-TT-180320-FC | FC | 3 | 2018-09-10 | 180320-FC STAMPED | FC | 3 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YQ03-P3LB-122088 | 187 | [HRSG(For Block 3, 4)]_HRSG_PERFORMANCE AND OPERATIONAL DATA | FA | 2017-11-01 | 2018-01-30 | 2018-07-27 | 2018-08-27 | MRT-DS-REC-TT-180320-FC | FC | 2 | 2018-09-10 | 180320-FC STAMPED | FC | 2 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XG02-P2LB-122022 | 188 | [HRSG(For Block 2)]_HRSG_P&I DIAGRAM | FA | 2017-11-01 | 2018-01-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XG02-P3LB-122022 | 189 | [HRSG(for Block 3, 4)]_HRSG_P&I DIAGRAM | FA | 2017-11-01 | 2018-01-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XS00-P2LB-122035 | 190 | [HRSG(For Block 2)]_HRSG_SYSTEM DESCRIPTION | FA | 2018-01-01 | 2018-04-01 | 2018-07-27 | 2018-09-19 | MRT-DS-REC-TT-180160-FC | FC | 2 | 2018-09-28 | 180160-FC STAMPED | FC | 2 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XS00-P3LB-122035 | 191 | [HRSG(for Block 3, 4)]_HRSG_SYSTEM DESCRIPTION | FA | 2018-01-01 | 2018-04-01 | 2018-07-27 | 2018-08-20 | MRT-DS-REC-TT-180262-FC | FC | 2 | 2018-09-10 | 180262-FC STAMPED | FC | 2 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XS00-P2LB-122037 | 192 | [HRSG(For Block 2)]_HRSG_BLOWDOWN SYSTEM SUMMARY | FI | 2017-12-01 |  | 2018-07-28 | 2018-07-28 | MRT-DS-REC-TT-180687 | FI | 2 | 2018-08-03 | 685/T/MRT/REC/VIII/2018 | FI | 2 | I | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XS00-P3LB-122037 | 193 | [HRSG(For Block 3, 4)]_HRSG_BLOWDOWN SYSTEM SUMMARY | FI | 2017-12-01 |  | 2018-07-28 | 2018-07-28 | MRT-DS-REC-TT-180687 | FI | 1 | 2018-08-03 | 685/T/MRT/REC/VIII/2018 | FI | 1 | I | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-UE00-P2LB-122007 | 194 | [HRSG(For Block 2)]_HRSG_GENERAL ARRANGEMENT | FA | 2017-11-01 | 2018-01-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-UE00-P3LB-122007 | 195 | [HRSG(For Block 3, 4)]_HRSG_GENERAL ARRANGEMENT | FA | 2017-11-01 | 2018-01-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XV00-P2LB-122039 | 196 | [HRSG(For Block 2)]_HRSG_EQUIPMENT LIST | FI | 2018-03-01 |  | 2018-08-16 | 2018-08-16 | MRT-DS-REC-TT-180705 | FI | 1 | 2018-08-28 | 752/T/MRT/REC/VIII/2018 | FI | 1 | I | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XV00-P3LB-122039 | 197 | [HRSG(For Block 3, 4)]_HRSG_EQUIPMENT LIST | FI | 2018-03-01 |  | 2018-08-16 | 2018-08-16 | MRT-DS-REC-TT-180705 | FI | 1 | 2018-08-28 | 752/T/MRT/REC/VIII/2018 | FI | 1 | I | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-UE00-P2LB-122008 | 198 | [HRSG(For Block 2)]_HRSG_ARRANGEMENT OF CASING & FIELD ERECTION | FI | 2017-11-01 | 2018-01-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-UE00-P3LB-122008 | 199 | [HRSG(for Block 3, 4)]_HRSG_ARRANGEMENT OF CASING & FIELD ERECTION | FI | 2017-11-01 | 2018-01-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-UE00-P2LB-122010 | 200 | [HRSG(For Block 2)]_HRSG_ARRANGEMENT OF MAIN STACK & FIELD ERECTION | FI | 2017-11-01 | 2018-01-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-UE00-P3LB-122010 | 201 | [HRSG(for Block 3, 4)]_HRSG_ARRANGEMENT OF MAIN STACK & FIELD ERECTION | FI | 2017-11-01 | 2018-01-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-VN03-P2LB-122015 | 202 | [HRSG(For Block 2)]_HRSG_ARRANGEMENT FOR PLATFORM STRUCTURE | FI | 2018-02-01 | 2018-05-02 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-VN03-P3LB-122015 | 203 | [HRSG(For Block 3, 4)]_HRSG_ARRANGEMENT FOR PLATFORM STRUCTURE | FI | 2018-02-01 | 2018-05-02 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XB02-P2LB-122022 | 204 | [HRSG(for Block 2, 3 & 4)]_HRSG_PRESSURE PARTS DESIGN REPORT | FI | 2018-03-20 |  | 2018-11-07 | 2018-11-07 | MRT-DS-REC-TT-180863 | FI | 1 | 2019-01-02 | 1169/T/MRT/REC/XII/2018 | FI | 1 | I | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YB03-P2LB-122048 | 205 | [HRSG(For Block 2)]_HRSG_PRESSURE PART ARRANGEMENT | FI | 2017-12-01 | 2018-03-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YB03-P3LB-122048 | 206 | [HRSG(for Block 3, 4)]_HRSG_PRESSURE PART ARRANGEMENT | FI | 2017-12-01 | 2018-03-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P2LB-122049 | 207 | [HRSG(For Block 2)]_HRSG_SPEC. & DRAWING FOR STEAM DRUM | FI | 2018-04-01 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P3LB-122049 | 208 | [HRSG(for Block 3, 4)]_HRSG_SPEC. & DRAWING FOR STEAM DRUM | FI | 2018-04-01 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P2LB-122050 | 209 | [HRSG(For Block 2)]_HRSG_SPEC. & DRAWING FOR BLOWDOWN PUMP | FA | 2018-03-01 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P3LB-122050 | 210 | [HRSG(For Block 3, 4)]_HRSG_SPEC. & DRAWING FOR BLOWDOWN PUMP | FA | 2018-03-01 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YT01-P2LB-122051 | 211 | [HRSG(For Block 2)]_HRSG_SPEC. & DRAWING FOR SAFETY & RELIEF VALVE | FA | 2018-03-01 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YT01-P3LB-122051 | 212 | [HRSG(For Block 3, 4)]_HRSG_SPEC. & DRAWING FOR SAFETY & RELIEF VALVE | FA | 2018-03-01 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P2LB-122052 | 213 | [HRSG(For Block 2)]_HRSG_SPEC. & DRAWING FOR STACK DAMPER | FA | 2018-03-01 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P3LB-122052 | 214 | [HRSG(For Block 3, 4)]_HRSG_SPEC. & DRAWING FOR STACK DAMPER | FA | 2018-03-01 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P2LB-122053 | 215 | [HRSG(For Block 2)]_HRSG_SPEC. & DRAWING FOR SILENCER | FA | 2018-03-01 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P3LB-122053 | 216 | [HRSG(For Block 3, 4)]_HRSG_SPEC. & DRAWING FOR SILENCER | FA | 2018-03-01 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P2LB-122055 | 217 | [HRSG(For Block 2)]_HRSG_EQUIPMENT OUTLINE DRAWING FOR BLOWDOWN TANK | FI | 2018-03-01 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P3LB-122055 | 218 | [HRSG(For Block 3, 4)]_HRSG_EQUIPMENT OUTLINE DRAWING FOR BLOWDOWN TANK | FI | 2018-03-01 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YB03-P2LB-122113 | 219 | [HRSG(for Block 2, 3&4)]_ HRSG_PRESSURE PART DETAIL FOR INSTALLATION | FI | 2018-10-24 | 2018-11-24 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P2LB-122120 | 220 | [HRSG(for Block 2, 3&4)]_HRSG_CASING EXPANSION JOINT DRAWINGS FOR INSTALLATION | FI | 2018-11-22 | 2019-01-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-DP00-P2LB-122106 | 221 | [HRSG(For Block 2)]_HRSG_DIVERTER & GUILLOTINE DAMPER DOCUMENT PACKAGE | FA | 2017-12-15 | 2018-02-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-DP00-P3LB-122106 | 222 | [HRSG(For Block 3, 4)]_HRSG_DIVERTER & GUILLOTINE DAMPER DOCUMENT PACKAGE | FA | 2017-12-15 | 2018-02-01 | 2024-11-14 | 2024-11-14 | MRT-DS-REC-TT-240028 | AB | Z1 | 2024-11-26 | MTW-AS-C-LT-24.5992.0 | AB | Z1 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-DP00-P2LB-122117 | 223 | [HRSG(for Block 2, 3&4)]_HRSG_DIVERTER DAMPER DRAWINGS FOR INSTALLATION | FI | 2018-11-12 | 2019-01-11 | 2018-11-09 | 2018-11-12 | MRT-DS-REC-TT-180869-FC | FC | 0 | 2018-11-13 | 180869-FC STAMPED | FC | 0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P2LB-122107 | 224 | [HRSG(For Block 2)]_HRSG_SPEC. & DRAWING FOR RECIRCULATION PUMP | FA | 2018-01-31 | 2018-04-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P3LB-122107 | 225 | [HRSG(For Block 3, 4)]_HRSG_SPEC. & DRAWING FOR RECIRCULATION PUMP | FA | 2018-01-31 | 2018-04-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P2LB-122114 | 226 | [HRSG(for Block 2)]_HRSG_SPEC. & DRAWING FOR SUMP PUMP | FA | 2018-10-30 | 2018-11-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P3LB-122114 | 227 | [HRSG(for Block 3, 4)]_HRSG_SPEC. & DRAWING FOR SUMP PUMP | FA | 2018-10-30 | 2018-11-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YK08-P2LB-122115 | 228 | [HRSG(for Block 2)]_HRSG_NAMEPLATE DRAWING | FI | 2018-11-07 | 2019-03-07 | 2019-05-24 | 2019-05-27 | MRT-DS-REC-TT-180857-FC | FC | 0 | 2019-05-29 | 180857-FC STAMPED | FC | 0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YK08-P3LB-122115 | 229 | [HRSG(for Block 3, 4)]_HRSG_ NAMEPLATE DRAWING | FI | 2018-11-07 | 2019-03-07 | 2019-05-24 | 2019-05-27 | MRT-DS-REC-TT-180857-FC | FC | 0 | 2019-05-29 | 180857-FC STAMPED | FC | 0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-DP00-P2LB-122122 | 230 | [HRSG(for Block 2)]_HRSG_ELEVATOR DOCUMENT PACKAGE | FA | 2019-03-11 | 2019-06-14 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-DP00-P3LB-122122 | 231 | [HRSG(for Block 3, 4)]_HRSG_ELEVATOR DOCUMENT PACKAGE | FA | 2019-03-11 | 2019-06-14 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-07-12 | MTW-AS-C-LT-24.5520.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-DP00-P2LB-122123 | 232 | [HRSG(for Block 2)]_HRSG_HOIST DOCUMENT PACKAGE | FI | 2019-04-03 | 2019-06-03 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-DP00-P3LB-122123 | 233 | [HRSG(for Block 3, 4)]_HRSG_HOIST DOCUMENT PACKAGE | FI | 2019-04-03 | 2019-06-03 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-07-12 | MTW-AS-C-LT-24.5520.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YT02-P2LB-122104 | 234 | [HRSG(For Block 2)]_HRSG_PIPING MATERIAL CLASSIFICATION | FI | 2018-02-01 |  | 2018-11-16 | 2018-11-16 | MRT-DS-REC-TT-180885 | FI | 1 | 2018-12-20 | 1148/T/MRT/REC/XII/2018 | FI | 1 | I | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YT02-P3LB-122104 | 235 | [HRSG(for Block 3, 4)]_HRSG_PIPING MATERIAL CLASSIFICATION | FI | 2018-02-01 |  | 2018-11-16 | 2018-11-16 | MRT-DS-REC-TT-180885 | FI | 1 | 2018-12-20 | 1148/T/MRT/REC/XII/2018 | FI | 1 | I | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XG01-P2LB-122021 | 236 | [HRSG(For Block 2)]_HRSG_PIPING ARRANGEMENT | FI | 2018-06-01 | 2018-08-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XG01-P3LB-122021 | 237 | [HRSG(For Block 3, 4)]_HRSG_PIPING ARRANGEMENT | FI | 2018-06-01 | 2018-08-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YK01-P2LB-122074 | 238 | [HRSG(For Block 2)]_HRSG_MANUAL VALVE ASSEMBLY DRAWING FOR EXTERNAL PIPING | FI | 2018-06-01 | 2018-08-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YK01-P3LB-122074 | 239 | [HRSG(For Block 3, 4)]_HRSG_MANUAL VALVE ASSEMBLY DRAWING FOR EXTERNAL PIPING | FI | 2018-06-01 | 2018-08-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XL00-P2LB-122030 | 240 | [HRSG(For Block 2)]_HRSG_LINE LIST | FA | 2018-01-01 | 2018-04-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XL00-P3LB-122030 | 241 | [HRSG(For Block 3, 4)]_HRSG_LINE LIST | FA | 2018-01-01 | 2018-04-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XN00-P2LB-122032 | 242 | [HRSG(For Block 2)]_HRSG_VALVE LIST | FI | 2018-01-01 | 2018-05-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XN00-P3LB-122032 | 243 | [HRSG(For Block 3, 4)]_HRSG_VALVE LIST | FI | 2018-01-01 | 2018-05-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XJ00-P2LB-122027 | 244 | [HRSG(For Block 2)]_HRSG_LARGE BORE ERECTION ISOMETRIC DRAWING FOR EXTERNAL PIPING | FI | 2018-06-01 | 2018-08-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XJ00-P3LB-122027 | 245 | [HRSG(For Block 3, 4)]_HRSG_LARGE BORE ERECTION ISOMETRIC DRAWING FOR EXTERNAL PIPING | FI | 2018-06-01 | 2018-08-30 | 2024-03-12 | 2024-03-12 | MRT-DS-REC-TT-240007 | AB | Z1 | 2024-03-20 | MTW-AS-C-LT-24.5077.0 | AB | Z1 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XJ00-P2LB-122028 | 246 | [HRSG(For Block 2)]_HRSG_SMALL BORE ERECTION ISOMETRIC DRAWING FOR EXTERNAL PIPING | FI | 2018-02-01 | 2018-07-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XJ00-P3LB-122028 | 247 | [HRSG(For Block 3, 4)]_HRSG_SMALL BORE ERECTION ISOMETRIC DRAWING FOR EXTERNAL PIPING | FI | 2018-02-01 | 2018-07-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XH01-P2LB-122026 | 248 | [HRSG(For Block 2)]_HRSG_PIPE SUPPORT DRAWINGS | FI | 2018-06-30 | 2018-08-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XH01-P3LB-122026 | 249 | [HRSG(For Block 3, 4)]_HRSG_PIPE SUPPORT DRAWINGS | FI | 2018-06-30 | 2018-08-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XH01-P2LB-122025 | 250 | [HRSG(For Block 2)]_HRSG_TYPICAL SUPPORT DRAWING FOR SMALL BORE PIPING | FI | 2018-06-30 | 2018-08-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XH01-P3LB-122025 | 251 | [HRSG(For Block 3, 4)]_HRSG_TYPICAL SUPPORT DRAWING FOR SMALL BORE PIPING | FI | 2018-06-30 | 2018-08-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XH01-P2LB-122112 | 252 | [HRSG(for Block 2)]_HRSG_PIPE SUPPORT DRAWINGS FOR INSTALLATION | FI | 2018-10-19 | 2018-11-19 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XH01-P3LB-122112 | 253 | [HRSG(for Block 3, 4)]_HRSG_PIPE SUPPORT DRAWINGS FOR INSTALLATION | FI | 2018-10-19 | 2018-11-19 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YQ03-P2LB-122086 | 254 | [HRSG(For Block 2)]_HRSG_DATA & BOM OF INSULATION | FI | 2018-03-01 | 2018-06-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YQ03-P3LB-122086 | 255 | [HRSG(For Block 3, 4)]_HRSG_DATA & BOM OF INSULATION | FI | 2018-03-01 | 2018-06-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YT01-P2LB-122100 | 256 | [HRSG(For Block 2)]_HRSG_ELECTRICAL SINGLE LINE DIAGRAMS | FI | 2018-02-01 | 2018-06-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | ELECTRICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YT01-P3LB-122100 | 257 | [HRSG(for Block 3, 4)]_HRSG_ELECTRICAL SINGLE LINE DIAGRAMS | FI | 2018-02-01 | 2018-06-01 | 2024-11-14 | 2024-11-14 | MRT-DS-REC-TT-240028 | AB | Z0 | 2024-11-21 | MTW-AS-C-LT-24.5978.0 | AB | Z0 | A | ELECTRICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P2LB-122109 | 258 | [HRSG(for Block 2)]_HRSG_ELECTRICAL USER LOCATION | FI | 2018-04-06 | 2018-08-04 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | ELECTRICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P3LB-122109 | 259 | [HRSG(for Block 3, 4)]_HRSG_ELECTRICAL USER LOCATION | FI | 2018-04-06 | 2018-08-04 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-07-12 | MTW-AS-C-LT-24.5520.0 | AB | Z0 | A | ELECTRICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P2LB-122056 | 260 | [HRSG(For Block 2)]_HRSG_POWER DISTRIBUTION PANEL DRAWINGS | FA | 2018-05-01 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | ELECTRICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P3LB-122056 | 261 | [HRSG(For Block 3, 4)]_HRSG_POWER DISTRIBUTION PANEL DRAWINGS | FA | 2018-05-01 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-07-12 | MTW-AS-C-LT-24.5520.0 | AB | Z0 | A | ELECTRICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YQ01-P2LB-122085 | 262 | [HRSG(For Block 2)]_HRSG_WIRING & SCHEMATIC DIAGRAM | FI | 2018-04-01 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | ELECTRICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YQ01-P3LB-122085 | 263 | [HRSG(For Block 3, 4)]_HRSG_WIRING & SCHEMATIC DIAGRAM | FI | 2018-04-01 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-07-12 | MTW-AS-C-LT-24.5520.0 | AB | Z0 | A | ELECTRICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YE00-P2LB-122116 | 264 | [HRSG(for Block 2)]_HRSG_LIGHTING SYSTEM | FA | 2018-11-07 | 2018-12-21 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | ELECTRICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YE00-P3LB-122116 | 265 | [HRSG(for Block 3, 4)]_HRSG_LIGHTING SYSTEM | FA | 2018-11-07 | 2018-12-21 | 2024-11-14 | 2024-11-14 | MRT-DS-REC-TT-240028 | AB | Z0 | 2024-11-21 | MTW-AS-C-LT-24.5978.0 | AB | Z0 | A | ELECTRICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YS00-P2LB-122092 | 266 | [HRSG(For Block 2)]_HRSG_AIRCRAFT WARNING LIGHT DATASHEET & LAYOUT DIAGRAM | FA | 2018-04-01 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | ELECTRICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YS00-P3LB-122092 | 267 | [HRSG(For Block 3, 4)]_HRSG_AIRCRAFT WARNING LIGHT DATASHEET & LAYOUT DIAGRAM | FA | 2018-04-01 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-07-12 | MTW-AS-C-LT-24.5520.0 | AB | Z0 | A | ELECTRICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XW01-P2LB-122043 | 268 | [HRSG(For Block 2)]_HRSG_TECHNICAL SPECIFICATION FOR CABLING ACCESSORIES | FA | 2018-05-10 | 2018-07-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | ELECTRICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XW01-P3LB-122043 | 269 | [HRSG(For Block 3, 4)]_HRSG_TECHNICAL SPECIFICATION FOR CABLING ACCESSORIES | FA | 2018-06-01 | 2018-07-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-07-12 | MTW-AS-C-LT-24.5520.0 | AB | Z0 | A | ELECTRICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YL16-P2LB-122078 | 270 | [HRSG(For Block 2)]_HRSG_CABLE SCHEDULE | FA | 2018-04-01 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | ELECTRICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YL16-P3LB-122078 | 271 | [HRSG(For Block 3, 4)]_HRSG_CABLE SCHEDULE | FA | 2018-04-01 | 2018-06-30 | 2024-11-14 | 2024-11-14 | MRT-DS-REC-TT-240028 | AB | Z0 | 2024-11-21 | MTW-AS-C-LT-24.5978.0 | AB | Z0 | A | ELECTRICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YD02-P2LB-122063 | 272 | [HRSG(For Block 2)]_HRSG_CONDUIT LAYOUT DRAWING | FI | 2018-06-10 | 2018-07-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | ELECTRICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YD02-P3LB-122063 | 273 | [HRSG(For Block 3, 4)]_HRSG_CONDUIT LAYOUT DRAWING | FI | 2018-06-10 | 2018-07-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-12-06 | MTW-AS-C-LT-23.4676.0 | AB | Z0 | A | ELECTRICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YD02-P2LB-122064 | 274 | [HRSG(For Block 2)]_HRSG_CABLE TRAY & RACEWAY LAYOUT DIAGRAM | FI | 2018-06-10 | 2018-07-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | ELECTRICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YD02-P3LB-122064 | 275 | [HRSG(For Block 3, 4)]_HRSG_CABLE TRAY & RACEWAY LAYOUT DIAGRAM | FI | 2018-06-10 | 2018-07-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-12-06 | MTW-AS-C-LT-23.4676.0 | AB | Z0 | A | ELECTRICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YD02-P2LB-122065 | 276 | [HRSG(For Block 2)]_HRSG_GROUNDING AND LIGHTNING PLAN DIAGRAMS | FI | 2018-05-10 | 2018-07-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | ELECTRICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YD02-P3LB-122065 | 277 | [HRSG(For Block 3, 4)]_HRSG_GROUNDING AND LIGHTNING PLAN DIAGRAMS | FI | 2018-06-10 | 2018-07-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-08-09 | MTW-AS-C-LT-24.5626.0 | AB | Z0 | A | ELECTRICAL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XS01-P2LB-122111 | 278 | [HRSG(For Block 2, 3&4)]_HRSG_CONTROL AND AUTOMATION DESCRIPTION | FI | 2018-10-12 |  | 2019-01-24 | 2019-01-24 | MRT-DS-REC-TT-190018 | FI | 1 | 2019-03-29 | 187/T/MRT/REC/III/2019 | FI | 1 | I | I&C | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-VN02-P2LB-122089 | 279 | [HRSG(For Block 2)]_HRSG_MOV DATASHEET & DRAWINGS | FA | 2018-03-01 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | I&C | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-VN02-P3LB-122089 | 280 | [HRSG(For Block 3, 4)]_HRSG_MOV DATASHEET & DRAWINGS | FA | 2018-03-01 | 2018-05-30 | 2024-10-17 | 2024-10-17 | MRT-DS-REC-TT-240015 | AB | Z2 | 2024-12-05 | MTW-AS-C-LT-24.6039.0 | AB | Z2 | A | I&C | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-VN02-P2LB-122090 | 281 | [HRSG(For Block 2)]_HRSG_CV DATASHEET & DRAWINGS | FA | 2018-03-01 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | I&C | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-VN02-P3LB-122090 | 282 | [HRSG(For Block 3, 4)]_HRSG_CV DATASHEET & DRAWINGS | FA | 2018-03-01 | 2018-05-30 | 2024-02-23 | 2024-02-23 | MRT-DS-REC-TT-240004 | AB | Z2 | 2024-04-02 | MTW-AS-C-LT-24.5134.0 | AB | Z2 | A | I&C | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YT01-P2LB-122093 | 283 | [HRSG(For Block 2)]_HRSG_CEMS DATASHEET & DRAWINGS | FA | 2018-05-10 | 2018-07-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | I&C | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YT01-P3LB-122093 | 284 | [HRSG(For Block 3, 4)]_HRSG_CEMS DATASHEET & DRAWINGS | FA | 2018-06-20 | 2018-07-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2025-02-20 | MTW-AS-C-LT-25.6214.0 | AB | Z0 | A | I&C | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YF00-P2LB-122066 | 285 | [HRSG(For Block 2)]_HRSG_CONTROL AND AUTOMATION DIAGRAM | FA | 2018-02-01 | 2018-07-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | I&C | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YF00-P3LB-122066 | 286 | [HRSG(For Block 3, 4)]_HRSG_CONTROL AND AUTOMATION DIAGRAM | FA | 2018-09-20 | 2018-11-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2025-02-20 | MTW-AS-C-LT-25.6214.0 | AB | Z0 | A | I&C | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YL00-P2LB-122075 | 287 | [HRSG(For Block 2, 3&4)]_HRSG_INSTRUMENT LIST | FI | 2018-01-01 | 2018-05-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | I&C | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YT02-P2LB-122094 | 288 | [HRSG(For Block 2)]_HRSG_LOCAL INSTRUMENT DATASHEET & DRAWINGS | FI | 2018-04-01 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | I&C | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YT02-P3LB-122094 | 289 | [HRSG(For Block 3, 4)]_HRSG_LOCAL INSTRUMENT DATASHEET & DRAWINGS | FI | 2018-04-01 | 2018-06-30 | 2024-03-05 | 2024-03-05 | MRT-DS-REC-TT-240006 | AB | Z1 | 2024-03-28 | MTW-AS-C-LT-24.5129.0 | AB | Z1 | A | I&C | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YT01-P2LB-122095 | 290 | [HRSG(For Block 2)]_HRSG_TRANSMITTER DATASHEET & DRAWINGS | FI | 2018-04-01 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | I&C | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YT01-P3LB-122095 | 291 | [HRSG(For Block 3, 4)]_HRSG_TRANSMITTER DATASHEET & DRAWINGS | FI | 2018-04-01 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6018.0 | AB | Z0 | A | I&C | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YT01-P2LB-122096 | 292 | [HRSG(For Block 2)]_HRSG_DRUM LEVEL GAUGE DATASHEET & DRAWINGS | FI | 2018-04-01 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | I&C | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YT01-P3LB-122096 | 293 | [HRSG(For Block 3, 4)]_HRSG_DRUM LEVEL GAUGE DATASHEET & DRAWINGS | FI | 2018-04-01 | 2018-06-30 | 2024-03-05 | 2024-03-05 | MRT-DS-REC-TT-240006 | AB | Z1 | 2024-03-28 | MTW-AS-C-LT-24.5129.0 | AB | Z1 | A | I&C | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YT01-P2LB-122097 | 294 | [HRSG(For Block 2)]_HRSG_FLOW ELEMENT DATASHEET & DRAWINGS | FI | 2018-04-01 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | I&C | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YT01-P3LB-122097 | 295 | [HRSG(For Block 3, 4)]_HRSG_FLOW ELEMENT DATASHEET & DRAWINGS | FI | 2018-04-01 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | I&C | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P2LB-122108 | 296 | [HRSG(For Block 2)]_HRSG_I&C LOCAL PANEL DRAWINGS | FA | 2018-03-05 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | I&C | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P3LB-122108 | 297 | [HRSG(For Block 3, 4)]_HRSG_I&C LOCAL PANEL DRAWINGS | FA | 2018-03-05 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | I&C | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YM03-P2LB-122069 | 298 | [HRSG(For Block 2)]_HRSG_INSTRUMENT LOCATION | FA | 2018-03-01 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | I&C | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YM03-P3LB-122069 | 299 | [HRSG(For Block 3, 4)]_HRSG_INSTRUMENT LOCATION | FA | 2018-03-01 | 2018-05-30 | 2024-03-05 | 2024-03-05 | MRT-DS-REC-TT-240006 | AB | Z1 | 2024-03-28 | MTW-AS-C-LT-24.5129.0 | AB | Z1 | A | I&C | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YK00-P2LB-122072 | 300 | [HRSG(For Block 2)]_HRSG_INSTRUMENT INSTALLATION DETAIL DRAWINGS | FA | 2018-03-01 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | I&C | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YK00-P3LB-122072 | 301 | [HRSG(For Block 3, 4)]_HRSG_INSTRUMENT INSTALLATION DETAIL DRAWINGS | FA | 2018-03-01 | 2018-05-30 | 2024-02-23 | 2024-02-23 | MRT-DS-REC-TT-240004 | AB | Z2 | 2024-04-02 | MTW-AS-C-LT-24.5134.0 | AB | Z2 | A | I&C | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YK00-P2LB-122076 | 302 | [HRSG(for Block 2)]_HRSG_HOOK UP DRAWING | FI | 2018-05-30 | 2018-10-19 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | I&C | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YK00-P3LB-122076 | 303 | [HRSG(for Block 3, 4)]_HRSG_HOOK UP DRAWING | FI | 2018-06-30 | 2018-11-23 | 2024-12-09 | 2024-12-09 | MRT-DS-REC-TT-240043 | AB | Z3 | 2024-12-16 | MTW-AS-C-LT-24.6072.0 | AB | Z3 | A | I&C | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XB02-P2LB-122021 | 304 | [HRSG(For Block 2, 3&4)]_HRSG_MAIN FRAMES DESIGN REPORT | FA | 2017-12-04 | 2018-04-30 | 2018-10-01 | 2018-11-23 | MRT-DS-REC-TT-180774-FC | FC | 3 | 2018-12-03 | 180774-FC STAMPED | FC | 3 | A | CIVIL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XB02-P2LB-122016 | 305 | [HRSG(For Block 2)]_HRSG_COLUMN LOCATION FOR STEEL STRUCTURE AND STACK (WITH PLAN VIEW) | FA | 2017-11-01 | 2018-01-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | CIVIL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XB02-P3LB-122016 | 306 | [HRSG(for Block 3, 4)]_HRSG_COLUMN LOCATION FOR STEEL STRUCTURE AND STACK (WITH PLAN VIEW) | FA | 2017-11-01 | 2018-01-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-03-20 | MTW-AS-C-LT-24.5076.0 | AB | Z0 | A | CIVIL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XB02-P2LB-122017 | 307 | [HRSG(For Block 2)]_HRSG_FOUNDATION LOAD TABLE FOR STEEL STRUCTURE AND STACK | FA | 2017-11-01 | 2018-01-30 | 2018-07-27 | 2018-08-20 | MRT-DS-REC-TT-180257-FC | FC | 3 | 2018-09-03 | 180257-FC STAMPED | FC | 3 | A | CIVIL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XB02-P3LB-122017 | 308 | [HRSG(for Block 3, 4)]_HRSG_FOUNDATION LOAD TABLE FOR STEEL STRUCTURE AND STACK | FA | 2017-11-01 | 2018-01-30 | 2018-07-27 | 2018-08-20 | MRT-DS-REC-TT-180257-FC | FC | 2 | 2018-09-03 | 180257-FC STAMPED | FC | 2 | A | CIVIL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XB02-P2LB-122018 | 309 | [HRSG(For Block 2)]_HRSG_BASE PLATE AND ANCHOR BOLTS DETAIL FOR STEEL STRUCTURE | FA | 2017-11-01 | 2018-01-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | CIVIL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-XB02-P3LB-122018 | 310 | [HRSG(For Block 3, 4)]_HRSG_BASE PLATE AND ANCHOR BOLTS DETAIL FOR STEEL STRUCTURE | FA | 2017-11-01 | 2018-01-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-03-20 | MTW-AS-C-LT-24.5076.0 | AB | Z0 | A | CIVIL | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-UC02-P2LB-122121 | 311 | [HRSG(for Block 2, 3&4)]_HRSG_ERECTION MANUAL FOR INSTALLATION | FI | 2018-11-27 | 2019-01-30 | 2019-08-20 | 2019-08-20 | MRT-DS-REC-TT-190180-FC | FC | 1 | 2019-08-20 | 190180-FC STAMPED | FC | 1 | A | SUPPORT | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YR01-P2LB-122082 | 312 | [HRSG(For Block 2, 3&4)]_HRSG_CHEMICAL CLEANING PROCEDURE | FI | 2018-07-06 | 2018-11-03 | 2019-05-24 | 2019-06-14 | MRT-DS-REC-TT-180595-FC | FC | 0 | 2019-06-14 | 180595-FC STAMPED | FC | 0 | A | SUPPORT | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-YL08-P2LB-122083 | 313 | [HRSG(For Block 2, 3&4)]_HRSG_CONSERVATION PROCEDURE | FI | 2018-06-01 | 2018-09-29 | 2019-05-24 | 2019-06-17 | MRT-DS-REC-TT-180487-FC | FC | 0 | 2019-06-17 | 180487-FC STAMPED | FC | 0 | A | SUPPORT | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-DN05-P2LB-122119 | 314 | [HRSG(for Block 2, 3&4)]_HRSG_COMMISSIONING MANUAL | FA | 2018-11-30 | 2019-02-28 | 2022-12-12 | 2022-12-12 | MRT-DS-REC-TT-220026 | FC | 0 | 2023-01-11 | DEEMED APPROVAL | FC | 0 | A | SUPPORT | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-DN05-P2LB-122110 | 315 | [HRSG(For Block 2, 3&4)]_COMMISSIONING PROCEDURE FOR DIVERTER DAMPER, GUILLOTTINE | FA | 2018-07-09 | 2018-10-09 | 2018-07-27 | 2018-09-24 | MRT-DS-REC-TT-180561-FC | FC | 0 | 2021-01-14 | 001/SER.00.01/LE/2021 | FC | 0 | A | SUPPORT | HRSG
DHI | 플랜트기술 | 오슬기 | MRT-CQ02-P2LB-122118 | 316 | [HRSG(for Block 2, 3&4)]_HRSG_OPERATION & MAINTENANCE MANUAL | FI | 2018-11-30 | 2019-02-28 | 2019-08-23 | 2019-08-24 | MRT-DS-REC-TT-190185-FC | FC | 1 | 2019-08-26 | 190185-FC STAMPED | FC | 1 | A | SUPPORT | HRSG
DHI | 플랜트기술 | 류두현 | MRT-XG02-P2SCA-127502 | 317 | [Air compressor (DHI for Block 2)]_P&I DIAGRAM FOR AIR COMPRESSOR PACKAGE | FA | 2018-01-21 | 2018-04-21 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3689.0 | AB | Z0 | A | MECHANICAL | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-XG02-P3SCA-127502 | 318 | [Air compressor (DHI for Block 3, 4)]_P&I DIAGRAM FOR AIR COMPRESSOR PACKAGE | FA | 2018-01-21 | 2018-06-20 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2018-10-23 | 180711-FC STAMPED | FC | 2 | A | MECHANICAL | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-YD00-P2LCB-127501 | 319 | [Air compressor (DHI for Block 2)]_AIR COMPRESSOR_GENERAL ARRANGEMENT DRAWING FOR AIR COMPRESSORS PACKAGE | FA | 2018-03-21 | 2018-06-19 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3689.0 | AB | Z0 | A | MECHANICAL | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-YD00-P3LCB-127501 | 320 | [Air compressor (DHI for Block 3, 4)]_AIR COMPRESSOR_GENERAL ARRANGEMENT DRAWING FOR AIR COMPRESSORS PACKAGE | FA | 2018-03-21 | 2018-08-18 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2018-10-22 | 180638-FC STAMPED | FC | 2 | A | MECHANICAL | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-XW01-P2SCA-127503 | 321 | [Air compressor (DHI for Block 2)]_EQUIPMENT SPECIFICATION FOR COMPRESSED AIR SYSTEM | FA | 2018-01-21 | 2018-04-21 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3689.0 | AB | Z0 | A | MECHANICAL | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-XW01-P3SCA-127503 | 322 | [Air compressor (DHI for Block 3, 4)]_EQUIPMENT SPECIFICATION FOR COMPRESSED AIR SYSTEM | FA | 2018-01-21 | 2018-06-20 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2018-10-10 | 180474-FC STAMPED | FC | 2 | A | MECHANICAL | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-XF00-P2SCA-127524 | 323 | [Air compressor (DHI for Block 2)]_AIR COMPRESSOR_NAME PLATE DRAWING | FI | 2018-05-21 | 2018-08-19 | 2018-08-29 | 2018-10-02 | MRT-DS-REC-TT-180710-FC | FC | 1 | 2018-10-22 | 180710-FC STAMPED | FC | 1 | A | MECHANICAL | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-XF00-P3SCA-127524 | 324 | [Air compressor (DHI for Block 3, 4)]_AIR COMPRESSOR_NAME PLATE DRAWING | FI | 2018-05-21 | 2018-10-18 | 2018-08-29 | 2018-10-02 | MRT-DS-REC-TT-180710-FC | FC | 1 | 2018-10-22 | 180710-FC STAMPED | FC | 1 | A | MECHANICAL | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-YF02-P2SCA-127514 | 325 | [Air compressor (DHI for Block 2)]_AIR COMPRESSOR_CONTROL DESCRIPTION (PHILOSOPHY) | FA | 2018-02-20 | 2018-05-21 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180209-FC | FC | 1 | 2018-08-13 | 180209-FC STAMPED | FC | 1 | A | MECHANICAL | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-YF02-P3SCA-127514 | 326 | [Air compressor (DHI for Block 3, 4)]_AIR COMPRESSOR_CONTROL DESCRIPTION (PHILOSOPHY) | FA | 2018-02-20 | 2018-07-20 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180209-FC | FC | 1 | 2018-08-13 | 180209-FC STAMPED | FC | 1 | A | MECHANICAL | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-XW01-P2SCA-127504 | 327 | [Air compressor (DHI for Block 2)]_AIR COMPRESSOR_MOTOR SPECIFICATION | FA | 2018-03-21 | 2018-05-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3689.0 | AB | Z0 | A | ELECTRICAL | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-XW01-P3SCA-127504 | 328 | [Air compressor (DHI for Block 3, 4)]_AIR COMPRESSOR_MOTOR SPECIFICATION | FA | 2018-03-21 | 2018-05-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2018-11-29 | 180699-FC STAMPED | FC | 2 | A | ELECTRICAL | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-YU02-P2SCA-127510 | 329 | [Air compressor (DHI for Block 2)]_AIR COMPRESSOR_SINGLE LINE DIAGRAM | FA | 2018-03-21 | 2018-06-19 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3689.0 | AB | Z0 | A | ELECTRICAL | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-YU02-P3SCA-127510 | 330 | [Air compressor (DHI for Block 3, 4)]_AIR COMPRESSOR_SINGLE LINE DIAGRAM | FA | 2018-03-21 | 2018-08-18 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2024-07-16 | MTW-AS-C-LT-24.5526.0 | AB | Z0 | A | ELECTRICAL | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-YS01-P2SCA-127511 | 331 | [Air compressor (DHI for Block 2)]_AIR COMPRESSOR_SCHEMATIC DIAGRAM FOR AIR COMPRESSOR PACKAGE | FI | 2018-04-21 | 2018-07-20 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3689.0 | AB | Z0 | A | ELECTRICAL | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-YS01-P3SCA-127511 | 332 | [Air compressor (DHI for Block 3, 4)]_AIR COMPRESSOR_SCHEMATIC DIAGRAM FOR AIR COMPRESSOR PACKAGE | FI | 2018-04-21 | 2018-09-18 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2024-07-16 | MTW-AS-C-LT-24.5526.0 | AB | Z0 | A | ELECTRICAL | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-YV02-P2SCA-127532 | 333 | [Air compressor (DHI for Block 2)]_AIR COMPRESSOR_INTERCONNECTION WIRING DIAGRAM | FI | 2018-09-19 | 2018-11-19 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3689.0 | AB | Z0 | A | ELECTRICAL | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-YV02-P3SCA-127532 | 334 | [Air compressor (DHI for Block 3, 4)]_AIR COMPRESSOR_INTERCONNECTION WIRING DIAGRAM | FI | 2018-09-19 | 2018-11-19 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2024-07-16 | MTW-AS-C-LT-24.5526.0 | AB | Z0 | A | ELECTRICAL | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-YD16-P2SCA-127531 | 335 | [Air compressor (DHI for Block 2)]_AIR COMPRESSOR_EMBEDDED CONDUIT DRAWING | FA | 2018-04-13 | 2018-06-13 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3689.0 | AB | Z0 | A | ELECTRICAL | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-YD16-P3SCA-127531 | 336 | [Air compressor (DHI for Block 3, 4)]_AIR COMPRESSOR_EMBEDDED CONDUIT DRAWING | FA | 2018-04-13 | 2018-06-13 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2024-07-16 | MTW-AS-C-LT-24.5526.0 | AB | Z0 | A | ELECTRICAL | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-YR05-P2SCA-127523 | 337 | [Air compressor (DHI for Block 2)]_AIR COMPRESSOR_PLC PANEL & EQUIPMENT LCP DRAWING | FA | 2018-05-21 | 2018-08-19 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3689.0 | AB | Z0 | A | I&C | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-YR05-P3SCA-127523 | 338 | [Air compressor (DHI for Block 3, 4)]_AIR COMPRESSOR_PLC PANEL & EQUIPMENT LCP DRAWING | FA | 2018-05-21 | 2018-10-18 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5825.0 | AB | Z0 | A | I&C | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-YD05-P2SCA-127515 | 339 | [Air compressor (DHI for Block 2)]_AIR COMPRESSOR_PLC HMI GRAPHICS | FA | 2018-05-11 | 2018-07-20 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3689.0 | AB | Z0 | A | I&C | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-YD05-P3SCA-127515 | 340 | [Air compressor (DHI for Block 3, 4)]_AIR COMPRESSOR_PLC HMI GRAPHICS | FA | 2018-05-11 | 2018-09-18 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2024-07-16 | MTW-AS-C-LT-24.5526.0 | AB | Z0 | A | I&C | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-YF00-P2SCA-127518 | 341 | [Air compressor (DHI for Block 2)]_AIR COMPRESSOR_CONTROL LOGIC & LOOP DIAGRAM | FA | 2018-05-25 | 2018-07-20 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3689.0 | AB | Z0 | A | I&C | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-YF00-P3SCA-127518 | 342 | [Air compressor (DHI for Block 3, 4)]_AIR COMPRESSOR_CONTROL LOGIC & LOOP DIAGRAM | FA | 2018-05-25 | 2018-09-18 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5825.0 | AB | Z0 | A | I&C | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-YL00-P2SCA-127520 | 343 | [Air compressor (DHI for Block 2)]_AIR COMPRESSOR_INSTRUMENT LIST AND DATA SHEET | FI | 2018-05-21 | 2018-08-19 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3689.0 | AB | Z0 | A | I&C | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-YL00-P3SCA-127520 | 344 | [Air compressor (DHI for Block 3, 4)]_AIR COMPRESSOR_INSTRUMENT LIST AND DATA SHEET | FI | 2018-05-21 | 2018-10-18 | 2024-11-18 | 2024-11-18 | MRT-DS-REC-TT-240030 | AB | Z1 | 2024-12-04 | MTW-AS-C-LT-24.6031.0 | AB | Z1 | A | I&C | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-YK00-P2SCA-127521 | 345 | [Air compressor (DHI for Block 2)]_HOOK UP DRAWING | FI | 2018-05-18 | 2018-07-18 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3689.0 | AB | Z0 | A | I&C | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-YK00-P3SCA-127521 | 346 | [Air compressor (DHI for Block 3, 4)]_HOOK UP DRAWING | FI | 2018-05-18 | 2018-07-18 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5825.0 | AB | Z0 | A | I&C | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-XB00-P2SCA-127509 | 347 | [Air compressor (DHI for Block 2)]_AIR COMPRESSOR_FOUNDATION DRAWINGS | FI | 2018-04-07 | 2018-07-06 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3689.0 | AB | Z0 | A | CIVIL | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-XB00-P3SCA-127509 | 348 | [Air compressor (DHI for Block 3, 4)]_AIR COMPRESSOR_FOUNDATION DRAWINGS | FI | 2018-04-07 | 2018-09-04 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2024-03-20 | MTW-AS-C-LT-24.5075.0 | AB | Z0 | A | CIVIL | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-CQ02-P2SCA-127529 | 349 | [Air compressor (DHI for Block 2)]_AIR COMPRESSOR_O & M MANUAL | FI | 2018-07-24 | 2018-10-22 | 2018-08-06 | 2018-11-19 | MRT-DS-REC-TT-180632-FC | FC | 0 | 2018-11-28 | 180632-FC STAMPED | FC | 0 | A | SUPPORT | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-CQ02-P3SCA-127529 | 350 | [Air compressor (DHI for Block 3, 4)]_AIR COMPRESSOR_O & M MANUAL | FI | 2018-07-24 | 2018-12-21 | 2018-08-06 | 2018-11-19 | MRT-DS-REC-TT-180632-FC | FC | 0 | 2018-11-28 | 180632-FC STAMPED | FC | 0 | A | SUPPORT | AIR COMPRESSOR
DHI | 플랜트기술 | 류두현 | MRT-XG02-P2LAC-126003 | 351 | [HP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_P&I DIAGRAM | FA | 2018-01-09 | 2018-06-08 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-12-17 | 180906-FC STAMPED | FC | 3 | A | MECHANICAL | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-XG02-P3LAC-126003 | 352 | [HP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_P&I DIAGRAM | FA | 2018-01-09 | 2018-06-08 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-03-21 | MTW-AS-C-LT-24.5086.0 | AB | Z0 | A | MECHANICAL | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-YD00-P2LAC-126001 | 353 | [HP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_GENERAL ARRANGEMENT DRAWING | FA | 2018-01-09 | 2018-04-09 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-09-10 | 180327-FC STAMPED | FC | 1 | A | MECHANICAL | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-YD00-P3LAC-126001 | 354 | [HP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_GENERAL ARRANGEMENT DRAWING | FA | 2018-01-09 | 2018-06-08 | 2024-11-18 | 2024-11-18 | MRT-DS-REC-TT-240031 | AB | Z1 | 2024-11-22 | MTW-AS-C-LT-24.5983.0 | AB | Z1 | A | MECHANICAL | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-YT01-P2LAC-126004 | 355 | [HP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | FA | 2018-01-09 | 2018-04-09 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-09-10 | 180327-FC STAMPED | FC | 1 | A | MECHANICAL | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-YT01-P3LAC-126004 | 356 | [HP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | FA | 2018-01-09 | 2018-06-08 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-03-21 | MTW-AS-C-LT-24.5086.0 | AB | Z0 | A | MECHANICAL | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-YT01-P2LAC-126005 | 357 | [HP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | FA | 2018-02-10 | 2018-05-11 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-10-23 | 180712-FC STAMPED | FC | 4 | A | ELECTRICAL | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-YT01-P3LAC-126005 | 358 | [HP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | FA | 2018-02-10 | 2018-07-10 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-03-21 | MTW-AS-C-LT-24.5086.0 | AB | Z0 | A | ELECTRICAL | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-YK01-P2LAC-126006 | 359 | [HP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_SECTIONAL DRAWING FOR PUMP | FI | 2018-02-10 | 2018-05-11 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-08-29 | 180380-FC STAMPED | FC | 1 | A | MECHANICAL | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-YK01-P3LAC-126006 | 360 | [HP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_SECTIONAL DRAWING FOR PUMP | FI | 2018-02-10 | 2018-07-10 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-03-21 | MTW-AS-C-LT-24.5086.0 | AB | Z0 | A | MECHANICAL | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-YT02-P2LAC-126011 | 361 | [HP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_LIST AND DATA SHEET FOR INSTRUMENT | FI | 2018-05-27 | 2018-08-25 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-11-29 | 180748-FC STAMPED | FC | 3 | A | I&C | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-YT02-P3LAC-126011 | 362 | [HP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_LIST AND DATA SHEET FOR INSTRUMENT | FI | 2018-05-27 | 2018-10-24 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5834.0 | AB | Z0 | A | I&C | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-XK00-P2LAC-126013 | 363 | [HP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_FLEXIBLE COUPLING DRAWING | FI | 2018-06-30 | 2018-10-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2019-05-29 | 180556-FC STAMPED | FC | 0 | A | MECHANICAL | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-XK00-P3LAC-126013 | 364 | [HP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_FLEXIBLE COUPLING DRAWING | FI | 2018-06-30 | 2018-10-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-03-21 | MTW-AS-C-LT-24.5086.0 | AB | Z0 | A | MECHANICAL | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-XK00-P2LAC-126014 | 365 | [HP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_DATA AND OUTLINE DRAWING FOR LUBE OIL UNIT | FA | 2018-05-31 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-11-05 | 180657-FC STMAPED | FC | 1 | A | MECHANICAL | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-XK00-P3LAC-126014 | 366 | [HP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_DATA AND OUTLINE DRAWING FOR LUBE OIL UNIT | FA | 2018-05-31 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-03-21 | MTW-AS-C-LT-24.5086.0 | AB | Z0 | A | MECHANICAL | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-YD00-P2LAC-126016 | 367 | [HP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_MECHANICAL SEAL OUTLINE DRAWING & DATA SHEET | FI | 2018-06-30 | 2018-10-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2019-06-14 | 180422-FC STAMPED | FC | 0 | A | MECHANICAL | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-YD00-P3LAC-126016 | 368 | [HP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_MECHANICAL SEAL OUTLINE DRAWING & DATA SHEET | FI | 2018-06-30 | 2018-10-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-03-21 | MTW-AS-C-LT-24.5086.0 | AB | Z0 | A | MECHANICAL | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-YD00-P2LAC-126017 | 369 | [HP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_SUCTION STRAINER DRAWING & DATA SHEET | FA | 2018-05-31 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-10-31 | 180676-FC STAMPED | FC | 1 | A | MECHANICAL | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-YD00-P3LAC-126017 | 370 | [HP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_SUCTION STRAINER DRAWING & DATA SHEET | FA | 2018-05-31 | 2018-08-31 | 2024-04-09 | 2024-04-09 | MRT-DS-REC-TT-240009 | AB | Z1 | 2024-05-20 | MTW-AS-C-LT-24.5267.0 | AB | Z1 | A | MECHANICAL | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-YD00-P2LAC-126007 | 371 | [HP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_NAME PLATE DRAWING | FI | 2018-05-27 | 2018-08-25 | 2018-07-27 | 2018-08-13 | MRT-DS-REC-TT-180378-FC | FC | 1 | 2018-08-31 | 180378-FC STAMPED | FC | 1 | A | MECHANICAL | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-YD00-P3LAC-126007 | 372 | [HP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_NAME PLATE DRAWING | FI | 2018-03-25 | 2018-08-22 | 2018-07-27 | 2018-08-13 | MRT-DS-REC-TT-180378-FC | FC | 1 | 2018-08-31 | 180378-FC STAMPED | FC | 1 | A | MECHANICAL | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-YD00-P2LAC-126049 | 373 | [HP Feed Water pump (DHI for Block 2)]_I&C JUNCTION BOX OUTLINE & INTERNAL LAYOUT DRAWING | FI | 2018-06-15 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2019-02-18 | 190008-FC STAMPED | FC | 3 | A | I&C | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-YD00-P3LAC-126049 | 374 | [HP Feed Water pump (DHI for Block 3,4)]_I&C JUNCTION BOX OUTLINE & INTERNAL LAYOUT DRAWING | FI | 2018-06-15 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5834.0 | AB | Z0 | A | I&C | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-YD00-P2LAC-126050 | 375 | [HP Feed Water pump (DHI for Block 2)]_CABLE INTERCONNECTION WIRING DIAGRAM | FI | 2018-06-15 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2019-02-18 | 190008-FC STAMPED | FC | 3 | A | ELECTRICAL | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-YD00-P3LAC-126050 | 376 | [HP Feed Water pump (DHI for Block 3,4)]_CABLE INTERCONNECTION WIRING DIAGRAM | FI | 2018-06-15 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-07-16 | MTW-AS-C-LT-24.5527.0 | AB | Z0 | A | ELECTRICAL | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-XB00-P2LAC-126022 | 377 | [HP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_FOUNDATION DRAWING | FI | 2018-02-28 | 2018-06-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-08-31 | 180396-FC STAMPED | FC | 1 | A | CIVIL | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-XB00-P3LAC-126022 | 378 | [HP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_FOUNDATION DRAWING | FI | 2018-02-28 | 2018-06-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-03-20 | MTW-AS-C-LT-24.5073.0 | AB | Z0 | A | CIVIL | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-CH01-P2LAC-126037 | 379 | [HP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_ERECTION MANUAL | FI | 2018-12-18 | 2019-02-15 | 2018-11-28 | 2018-11-29 | MRT-DS-REC-TT-180907-FC | FC | 0 | 2018-12-06 | 180907-FC STAMPED | FC | 0 | A | SUPPORT | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-CH01-P3LAC-126037 | 380 | [HP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_ERECTION MANUAL | FI | 2018-12-18 | 2019-02-15 | 2018-11-28 | 2018-11-29 | MRT-DS-REC-TT-180907-FC | FC | 0 | 2018-12-06 | 180907-FC STAMPED | FC | 0 | A | SUPPORT | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-CQ02-P2LAC-126038 | 381 | [HP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_O&M MANUAL | FI | 2019-03-30 | 2019-05-30 | 2018-12-19 | 2018-12-19 | MRT-DS-REC-TT-180911-FC | FC | 0 | 2018-12-22 | 180911-FC STAMPED | FC | 0 | A | SUPPORT | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-CQ02-P3LAC-126038 | 382 | [HP Feed Water pump (DHI for Block 3,4)]_FEEDWATER PUMP_O&M MANUAL | FI | 2019-03-30 | 2019-05-30 | 2018-12-19 | 2018-12-19 | MRT-DS-REC-TT-180911-FC | FC | 0 | 2018-12-22 | 180911-FC STAMPED | FC | 0 | A | SUPPORT | BFP HP
DHI | 플랜트기술 | 류두현 | MRT-XG02-P2LAC-126053 | 383 | [LP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_P&I DIAGRAM | FA | 2018-01-09 | 2018-06-08 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-12-17 | 180906-FC STAMPED | FC | 3 | A | MECHANICAL | BFP LP
DHI | 플랜트기술 | 류두현 | MRT-XG02-P3LAC-126053 | 384 | [LP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_P&I DIAGRAM | FA | 2018-01-09 | 2018-06-08 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-05-17 | MTW-AS-C-LT-24.5260.0 | AB | Z0 | A | MECHANICAL | BFP LP
DHI | 플랜트기술 | 류두현 | MRT-YD00-P2LAC-126051 | 385 | [LP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_GENERAL ARRANGEMENT DRAWING | FA | 2018-01-09 | 2018-04-09 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-09-10 | 180327-FC STAMPED | FC | 1 | A | MECHANICAL | BFP LP
DHI | 플랜트기술 | 류두현 | MRT-YD00-P3LAC-126051 | 386 | [LP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_GENERAL ARRANGEMENT DRAWING | FA | 2018-01-09 | 2018-06-08 | 2024-04-09 | 2024-04-09 | MRT-DS-REC-TT-240009 | AB | Z1 | 2024-05-20 | MTW-AS-C-LT-24.5267.0 | AB | Z1 | A | MECHANICAL | BFP LP
DHI | 플랜트기술 | 류두현 | MRT-YT01-P2LAC-126054 | 387 | [LP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | FA | 2018-01-09 | 2018-04-09 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-09-10 | 180327-FC STAMPED | FC | 1 | A | MECHANICAL | BFP LP
DHI | 플랜트기술 | 류두현 | MRT-YT01-P3LAC-126054 | 388 | [LP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | FA | 2018-01-09 | 2018-06-08 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-03-21 | MTW-AS-C-LT-24.5086.0 | AB | Z0 | A | MECHANICAL | BFP LP
DHI | 플랜트기술 | 류두현 | MRT-YT01-P2LAC-126055 | 389 | [LP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | FA | 2018-02-10 | 2018-05-11 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-10-23 | 180712-FC STAMPED | FC | 2 | A | ELECTRICAL | BFP LP
DHI | 플랜트기술 | 류두현 | MRT-YT01-P3LAC-126055 | 390 | [LP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | FA | 2018-02-10 | 2018-07-10 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-03-21 | MTW-AS-C-LT-24.5086.0 | AB | Z0 | A | ELECTRICAL | BFP LP
DHI | 플랜트기술 | 류두현 | MRT-YK01-P2LAC-126056 | 391 | [LP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_SECTIONAL DRAWING FOR PUMP | FI | 2018-02-10 | 2018-05-11 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-08-29 | 180380-FC STAMPED | FC | 1 | A | MECHANICAL | BFP LP
DHI | 플랜트기술 | 류두현 | MRT-YK01-P3LAC-126056 | 392 | [LP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_SECTIONAL DRAWING FOR PUMP | FI | 2018-02-10 | 2018-07-10 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-03-21 | MTW-AS-C-LT-24.5086.0 | AB | Z0 | A | MECHANICAL | BFP LP
DHI | 플랜트기술 | 류두현 | MRT-YD00-P2LAC-126057 | 393 | [LP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_NAME PLATE DRAWING | FI | 2018-05-27 | 2018-08-25 | 2018-07-27 | 2018-08-13 | MRT-DS-REC-TT-180378-FC | FC | 1 | 2018-08-31 | 180378-FC STAMPED | FC | 1 | A | MECHANICAL | BFP LP
DHI | 플랜트기술 | 류두현 | MRT-YD00-P3LAC-126057 | 394 | [LP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_NAME PLATE DRAWING | FI | 2018-03-25 | 2018-08-22 | 2018-07-27 | 2018-08-13 | MRT-DS-REC-TT-180378-FC | FC | 1 | 2018-08-31 | 180378-FC STAMPED | FC | 1 | A | MECHANICAL | BFP LP
DHI | 플랜트기술 | 류두현 | MRT-YT02-P2LAC-126061 | 395 | [LP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_LIST AND DATA SHEET FOR INSTRUMENT | FI | 2018-05-27 | 2018-08-25 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-11-29 | 180748-FC STAMPED | FC | 3 | A | I&C | BFP LP
DHI | 플랜트기술 | 류두현 | MRT-YT02-P3LAC-126061 | 396 | [LP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_LIST AND DATA SHEET FOR INSTRUMENT | FI | 2018-05-27 | 2018-10-24 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5834.0 | AB | Z0 | A | I&C | BFP LP
DHI | 플랜트기술 | 류두현 | MRT-XK00-P2LAC-126063 | 397 | [LP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_FLEXIBLE COUPLING DRAWING | FI | 2018-06-30 | 2018-10-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2019-05-29 | 180556-FC STAMPED | FC | 0 | A | MECHANICAL | BFP LP
DHI | 플랜트기술 | 류두현 | MRT-XK00-P3LAC-126063 | 398 | [LP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_FLEXIBLE COUPLING DRAWING | FI | 2018-06-30 | 2018-10-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-03-21 | MTW-AS-C-LT-24.5086.0 | AB | Z0 | A | MECHANICAL | BFP LP
DHI | 플랜트기술 | 류두현 | MRT-YD00-P2LAC-126064 | 399 | [LP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_MECHANICAL SEAL OUTLINE DRAWING & DATA SHEET | FI | 2018-06-30 | 2018-10-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2019-06-14 | 180422-FC STAMPED | FC | 0 | A | MECHANICAL | BFP LP
DHI | 플랜트기술 | 류두현 | MRT-YD00-P3LAC-126064 | 400 | [LP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_MECHANICAL SEAL OUTLINE DRAWING & DATA SHEET | FI | 2018-06-30 | 2018-10-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-03-21 | MTW-AS-C-LT-24.5086.0 | AB | Z0 | A | MECHANICAL | BFP LP
DHI | 플랜트기술 | 류두현 | MRT-YD00-P2LAC-126065 | 401 | [LP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_SUCTION STRAINER DRAWING & DATA SHEET | FA | 2018-05-31 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-10-31 | 180676-FC STAMPED | FC | 1 | A | MECHANICAL | BFP LP
DHI | 플랜트기술 | 류두현 | MRT-YD00-P3LAC-126065 | 402 | [LP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_SUCTION STRAINER & DATA SHEET | FA | 2018-05-31 | 2018-08-31 | 2024-11-25 | 2024-11-25 | MRT-DS-REC-TT-240040 | AB | Z1 | 2024-12-03 | MTW-AS-C-LT-24.6028.0 | AB | Z1 | A | MECHANICAL | BFP LP
DHI | 플랜트기술 | 류두현 | MRT-YD00-P2LAC-126096 | 403 | [LP Feed Water pump (DHI for Block 2)]_I&C JUNCTION BOX OUTLINE & INTERNAL LAYOUT DRAWING | FI | 2018-06-15 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-12-08 | 180867-FC STAMPED | FC | 2 | A | I&C | BFP LP
DHI | 플랜트기술 | 류두현 | MRT-YD00-P3LAC-126096 | 404 | [LP Feed Water pump (DHI for Block 3,4)]_I&C JUNCTION BOX OUTLINE & INTERNAL LAYOUT DRAWING | FI | 2018-06-15 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5834.0 | AB | Z0 | A | I&C | BFP LP
DHI | 플랜트기술 | 류두현 | MRT-YD00-P2LAC-126097 | 405 | [LP Feed Water pump (DHI for Block 2)]_CABLE INTERCONNECTION WIRING DAIGRAM | FI | 2018-06-15 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-12-08 | 180867-FC STAMPED | FC | 2 | A | ELECTRICAL | BFP LP
DHI | 플랜트기술 | 류두현 | MRT-YD00-P3LAC-126097 | 406 | [LP Feed Water pump (DHI for Block 3,4)]_CABLE INTERCONNECTION WIRING DAIGRAM | FI | 2018-06-15 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-07-16 | MTW-AS-C-LT-24.5527.0 | AB | Z0 | A | ELECTRICAL | BFP LP
DHI | 플랜트기술 | 류두현 | MRT-XB00-P2LAC-126070 | 407 | [LP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_FOUNDATION DRAWING | FI | 2018-02-28 | 2018-06-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-08-31 | 180396-FC STAMPED | FC | 1 | A | CIVIL | BFP LP
DHI | 플랜트기술 | 류두현 | MRT-XB00-P3LAC-126070 | 408 | [LP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_FOUNDATION DRAWING | FI | 2018-02-28 | 2018-06-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-03-20 | MTW-AS-C-LT-24.5073.0 | AB | Z0 | A | CIVIL | BFP LP
DHI | 플랜트기술 | 류두현 | MRT-CH01-P2LAC-126085 | 409 | [LP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_ERECTION MANUAL | FI | 2018-12-18 | 2019-02-15 | 2018-11-28 | 2018-11-29 | MRT-DS-REC-TT-180907-FC | FC | 0 | 2018-12-06 | 180907-FC STAMPED | FC | 0 | A | SUPPORT | BFP LP
DHI | 플랜트기술 | 류두현 | MRT-CH01-P3LAC-126085 | 410 | [LP Feed Water pump (DHI for Block 3,4)]_FEEDWATER PUMP_ERECTION MANUAL | FI | 2018-12-18 | 2019-02-15 | 2018-11-28 | 2018-11-29 | MRT-DS-REC-TT-180907-FC | FC | 0 | 2018-12-06 | 180907-FC STAMPED | FC | 0 | A | SUPPORT | BFP LP
DHI | 플랜트기술 | 류두현 | MRT-CQ02-P2LAC-126086 | 411 | [LP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_O&M MANUAL | FI | 2019-03-30 | 2019-05-30 | 2018-12-19 | 2018-12-19 | MRT-DS-REC-TT-180911-FC | FC | 0 | 2018-12-22 | 180911-FC STAMPED | FC | 0 | A | SUPPORT | BFP LP
DHI | 플랜트기술 | 류두현 | MRT-CQ02-P3LAC-126086 | 412 | [LP Feed Water pump (DHI for Block 3,4)]_FEEDWATER PUMP_O&M MANUAL | FI | 2019-03-30 | 2019-05-30 | 2018-12-19 | 2018-12-19 | MRT-DS-REC-TT-180911-FC | FC | 0 | 2018-12-22 | 180911-FC STAMPED | FC | 0 | A | SUPPORT | BFP LP
DHI | 플랜트기술 | 이태훈 | MRT-YD00-P2LCB-127031 | 413 | [Condensate Extraction pump (DHI for Block 2)]_CEP_GENERAL ARRANGEMENT DRAWING | FA | 2018-03-10 | 2018-06-08 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-01-05 | 180923-FC STAMPED | FC | 2 | A | MECHANICAL | CEP
DHI | 플랜트기술 | 이태훈 | MRT-XG02-P2LCB-127032 | 413 | [Condensate Extraction pump (DHI for Block 2)]_CEP_P&I DIAGRAM | FA | 2018-03-10 | 2018-06-08 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2020-01-10 | 190244-FC STAMPED | FC | 4 | A | MECHANICAL | CEP
DHI | 플랜트기술 | 이태훈 | MRT-XG02-P3LCB-127032 | 413 | [Condensate Extraction pump (DHI for Block 3, 4)]_CEP_P&I DIAGRAM | FA | 2018-03-10 | 2018-08-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | CEP
DHI | 플랜트기술 | 이태훈 | MRT-YD00-P3LCB-127031 | 414 | [Condensate Extraction pump (DHI for Block 3, 4)]_CEP_GENERAL ARRANGEMENT DRAWING | FA | 2018-03-10 | 2018-08-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | CEP
DHI | 플랜트기술 | 이태훈 | MRT-YT01-P2LCB-127033 | 415 | [Condensate Extraction pump (DHI for Block 2)]_CEP_DATA SHEET & CHARACTERISTIC CURVE | FA | 2018-03-10 | 2018-06-08 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2018-12-17 | 180874-FC STAMPED | FC | 3 | A | MECHANICAL | CEP
DHI | 플랜트기술 | 이태훈 | MRT-YT01-P3LCB-127033 | 416 | [Condensate Extraction pump (DHI for Block 3, 4)]_CEP_DATA SHEET & CHARACTERISTIC CURVE | FA | 2018-03-10 | 2018-08-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | CEP
DHI | 플랜트기술 | 이태훈 | MRT-YK09-P2LCB-127034 | 417 | [Condensate Extraction pump (DHI for Block 2)]_CEP_PUMP SECTIONAL DRAWING | FI | 2018-05-28 | 2018-08-26 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-01-05 | 180923-FC STAMPED | FC | 1 | A | MECHANICAL | CEP
DHI | 플랜트기술 | 이태훈 | MRT-YK09-P3LCB-127034 | 418 | [Condensate Extraction pump (DHI for Block 3, 4)]_CEP_PUMP SECTIONAL DRAWING | FI | 2018-05-28 | 2018-10-25 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | CEP
DHI | 플랜트기술 | 이태훈 | MRT-YT01-P2LCB-127035 | 419 | [Condensate Extraction pump (DHI for Block 2)]_CEP_MECHANICAL SEAL SPECIFICATION | FI | 2018-05-28 | 2018-08-26 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2018-09-13 | 180470-FC STAMPED | FC | 0 | A | MECHANICAL | CEP
DHI | 플랜트기술 | 이태훈 | MRT-YT01-P3LCB-127035 | 420 | [Condensate Extraction pump (DHI for Block 3, 4)]_CEP_MECHANICAL SEAL SPECIFICATION | FI | 2018-05-28 | 2018-10-25 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | CEP
DHI | 플랜트기술 | 이태훈 | MRT-YT01-P2LCB-127036 | 421 | [Condensate Extraction pump (DHI for Block 2)]_CEP_COUPLING SPECIFICATION | FA | 2018-07-28 | 2018-10-26 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2018-11-29 | 180684-FC STAMPED | FC | 0 | A | MECHANICAL | CEP
DHI | 플랜트기술 | 이태훈 | MRT-YT01-P3LCB-127036 | 422 | [Condensate Extraction pump (DHI for Block 3, 4)]_CEP_COUPLING SPECIFICATION | FA | 2018-07-28 | 2018-12-25 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | CEP
DHI | 플랜트기술 | 이태훈 | MRT-YT01-P2LCB-127037 | 423 | [Condensate Extraction pump (DHI for Block 2)]_CEP_SUCTION STRAINER SPECIFICATION | FA | 2018-07-28 | 2018-10-26 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2018-10-06 | 180668-FC STAMPED | FC | 0 | A | MECHANICAL | CEP
DHI | 플랜트기술 | 이태훈 | MRT-YT01-P3LCB-127037 | 424 | [Condensate Extraction pump (DHI for Block 3, 4)]_CEP_SUCTION STRAINER SPECIFICATION | FA | 2018-07-28 | 2018-12-25 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | CEP
DHI | 플랜트기술 | 이태훈 | MRT-YL22-P2LCB-127042 | 425 | [Condensate Extraction pump (DHI for Block 2)]_CEP_NAME PLATE DRAWING | FI | 2018-07-28 | 2018-10-26 | 2019-01-02 | 2019-01-03 | MRT-DS-REC-TT-180923-FC | FC | 1 | 2019-01-05 | 180923-FC STAMPED | FC | 1 | A | MECHANICAL | CEP
DHI | 플랜트기술 | 이태훈 | MRT-YL22-P3LCB-127042 | 426 | [Condensate Extraction pump (DHI for Block 3, 4)]_CEP_NAME PLATE DRAWING | FI | 2018-07-28 | 2018-12-25 | 2019-01-02 | 2019-01-03 | MRT-DS-REC-TT-180923-FC | FC | 1 | 2019-01-05 | 180923-FC STAMPED | FC | 1 | A | MECHANICAL | CEP
DHI | 플랜트기술 | 이태훈 | MRT-YM01-P2LCB-127039 | 427 | [Condensate Extraction pump (DHI for Block 2)]_CEP_MOTOR DATA SHEET & CHARACTERISTIC CURVE | FA | 2018-07-28 | 2018-10-26 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2020-09-01 | 200070-FC STAMPED | FC | 3 | A | ELECTRICAL | CEP
DHI | 플랜트기술 | 이태훈 | MRT-YM01-P3LCB-127039 | 428 | [Condensate Extraction pump (DHI for Block 3, 4)]_CEP_MOTOR DATA SHEET & CHARACTERISTIC CURVE | FA | 2018-07-28 | 2018-12-25 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | ELECTRICAL | CEP
DHI | 플랜트기술 | 이태훈 | MRT-YL00-P2LCB-127040 | 429 | [Condensate Extraction pump (DHI for Block 2)]_CEP_INSTRUMENT LIST AND DATA SHEET | FI | 2018-07-28 | 2018-10-26 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2018-11-29 | 180684-FC STAMPED | FC | 0 | A | I&C | CEP
DHI | 플랜트기술 | 이태훈 | MRT-YL00-P3LCB-127040 | 430 | [Condensate Extraction pump (DHI for Block 3, 4)]_CEP_INSTRUMENT LIST AND DATA SHEET | FI | 2018-07-28 | 2018-12-25 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-08-12 | MTW-AS-C-LT-24.5630.0 | AB | Z0 | A | I&C | CEP
DHI | 플랜트기술 | 이태훈 | MRT-CQ02-P2LCB-127043 | 431 | [Condensate Extraction pump (DHI for Block 2)]_CEP_O&M MANUAL | FI | 2018-07-30 | 2018-10-28 | 2018-08-06 | 2018-09-27 | MRT-DS-REC-TT-180637-FC | FC | 0 | 2018-10-05 | 180637-FC STAMPED | FC | 0 | A | SUPPORT | CEP
DHI | 플랜트기술 | 이태훈 | MRT-CQ02-P3LCB-127043 | 432 | [Condensate Extraction pump (DHI for Block 3, 4)]_CEP_O&M MANUAL | FI | 2018-07-30 | 2018-12-27 | 2018-08-06 | 2018-09-27 | MRT-DS-REC-TT-180637-FC | FC | 0 | 2018-10-05 | 180637-FC STAMPED | FC | 0 | A | SUPPORT | CEP
DHI | 플랜트기술 | 이태훈 | MRT-YD00-P2GHC-129001 | 433 | [General Service Pump (DHI for Block 2)]_GSP_GENERAL ARRANGEMENT DRAWING | FA | 2018-02-28 | 2018-05-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2018-09-13 | 180460-FC STAMPED | FC | 3 | A | MECHANICAL | GSP
DHI | 플랜트기술 | 이태훈 | MRT-YD00-P3GHC-129001 | 434 | [General Service Pump (DHI for Block 3, 4)]_GSP_GENERAL ARRANGEMENT DRAWING | FA | 2018-02-28 | 2018-07-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | GSP
DHI | 플랜트기술 | 이태훈 | MRT-YT01-P2GHC-129002 | 435 | [General Service Pump (DHI for Block 2)]_GSP_DATA SHEET & CHARACTERISTIC CURVE | FA | 2018-02-28 | 2018-05-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2018-08-23 | 180427-FC STAMPED | FC | 2 | A | MECHANICAL | GSP
DHI | 플랜트기술 | 이태훈 | MRT-YT01-P3GHC-129002 | 436 | [General Service Pump (DHI for Block 3, 4)]_GSP_DATA SHEET & CHARACTERISTIC CURVE | FA | 2018-02-28 | 2018-07-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | GSP
DHI | 플랜트기술 | 이태훈 | MRT-YK09-P2GHC-129003 | 437 | [General Service Pump (DHI for Block 2)]_GSP_PUMP SECTIONAL DRAWING | FI | 2018-03-15 | 2018-07-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-05-29 | 180190-FC STAMPED | FC | 0 | A | MECHANICAL | GSP
DHI | 플랜트기술 | 이태훈 | MRT-YK09-P3GHC-129003 | 438 | [General Service Pump (DHI for Block 3, 4)]_GSP_PUMP SECTIONAL DRAWING | FI | 2018-03-15 | 2018-07-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | GSP
DHI | 플랜트기술 | 이태훈 | MRT-YT01-P2GHC-129004 | 439 | [General Service Pump (DHI for Block 2)]_GSP_MECHANICAL SEAL SPECIFICATION | FI | 2018-03-31 | 2018-07-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-05-29 | 180277-FC STAMPED | FC | 0 | A | MECHANICAL | GSP
DHI | 플랜트기술 | 이태훈 | MRT-YT01-P3GHC-129004 | 440 | [General Service Pump (DHI for Block 3, 4)]_GSP_MECHANICAL SEAL SPECIFICATION | FI | 2018-03-31 | 2018-07-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | GSP
DHI | 플랜트기술 | 이태훈 | MRT-YL22-P2GHC-129014 | 441 | [General Service Pump (DHI for Block 2)]_GSP_NAME PLATE DRAWING | FI | 2018-05-31 | 2018-09-28 | 2019-05-24 | 2019-05-28 | MRT-DS-REC-TT-180502-FC | FC | 0 | 2019-06-11 | 180502-FC STAMPED | FC | 0 | A | MECHANICAL | GSP
DHI | 플랜트기술 | 이태훈 | MRT-YL22-P3GHC-129014 | 442 | [General Service Pump (DHI for Block 3, 4)]_GSP_NAME PLATE DRAWING | FI | 2018-05-31 | 2018-09-28 | 2019-05-24 | 2019-05-28 | MRT-DS-REC-TT-180502-FC | FC | 0 | 2019-06-11 | 180502-FC STAMPED | FC | 0 | A | MECHANICAL | GSP
DHI | 플랜트기술 | 이태훈 | MRT-YM01-P2GHC-129008 | 443 | [General Service Pump (DHI for Block 2)]_GSP_MOTOR DATA SHEET & CHARACTERISTIC CURVE | FA | 2018-03-31 | 2018-06-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2018-09-27 | 180428-FC STAMPED | FC | 2 | A | ELECTRICAL | GSP
DHI | 플랜트기술 | 이태훈 | MRT-YM01-P3GHC-129008 | 444 | [General Service Pump (DHI for Block 3, 4)]_GSP_MOTOR DATA SHEET & CHARACTERISTIC CURVE | FA | 2018-03-31 | 2018-08-28 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | ELECTRICAL | GSP
DHI | 플랜트기술 | 이태훈 | MRT-YL00-P2GHC-129011 | 445 | [General Service Pump (DHI for Block 2)]_GSP_INSTRUMENT LIST AND DATA SHEET | FI | 2018-04-30 | 2018-08-28 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-05-29 | 180382-FC STAMPED | FC | 0 | A | I&C | GSP
DHI | 플랜트기술 | 이태훈 | MRT-YL00-P3GHC-129011 | 446 | [General Service Pump (DHI for Block 3, 4)]_GSP_INSTRUMENT LIST AND DATA SHEET | FI | 2018-04-30 | 2018-08-28 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240018 | AB | Z1 | 2024-12-03 | MTW-AS-C-LT-24.6022.0 | AB | Z1 | A | I&C | GSP
DHI | 플랜트기술 | 이태훈 | MRT-CQ02-P2GHC-129016 | 447 | [General Service Pump (DHI for Block 2)]_GSP_O&M MANUAL | FI | 2018-07-15 | 2018-10-13 | 2018-07-27 | 2018-09-27 | MRT-DS-REC-TT-180587-FC | FC | 0 | 2018-10-05 | 180587-FC STAMPED | FC | 0 | A | SUPPORT | GSP
DHI | 플랜트기술 | 이태훈 | MRT-CQ02-P3GHC-129016 | 448 | [General Service Pump (DHI for Block 3, 4)]_GSP_O&M MANUAL | FI | 2018-07-15 | 2018-12-12 | 2018-07-27 | 2018-09-27 | MRT-DS-REC-TT-180587-FC | FC | 0 | 2018-10-05 | 180587-FC STAMPED | FC | 0 | A | SUPPORT | GSP
DHI | 플랜트기술 | 이태훈 | MRT-XK00-P2GM-128507 | 449 | [Sump Pump (DHI for Block 2)]_SUMP PUMP_P&ID | FA | 2017-11-16 | 2018-03-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-09-11 | 489/T/MRT/REC/IX/2019 | FC | 4 | A | MECHANICAL | SUMP PUMP
DHI | 플랜트기술 | 이태훈 | MRT-XK00-P3GM-128507 | 450 | [Sump Pump (DHI for Block 3, 4)]_SUMP PUMP_P&ID | FA | 2017-11-16 | 2018-03-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | SUMP PUMP
DHI | 플랜트기술 | 이태훈 | MRT-YD00-P2GM-128501 | 451 | [Sump Pump (DHI for Block 2)]_SUMP PUMP_PUMP OUTLINE DRAWING | FA | 2018-03-10 | 2018-06-08 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-01-12 | 180943-FC STAMPED | FC | 2 | A | MECHANICAL | SUMP PUMP
DHI | 플랜트기술 | 이태훈 | MRT-YD00-P3GM-128501 | 452 | [Sump Pump (DHI for Block 3, 4)]_SUMP PUMP_PUMP OUTLINE DRAWING | FA | 2018-03-10 | 2018-08-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | SUMP PUMP
DHI | 플랜트기술 | 이태훈 | MRT-YT01-P2GM-128502 | 453 | [Sump Pump (DHI for Block 2)]_SUMP PUMP_DATA SHEET & CHARACTERISTIC CURVE | FA | 2018-03-26 | 2018-06-24 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-01-12 | 180943-FC STAMPED | FC | 2 | A | MECHANICAL | SUMP PUMP
DHI | 플랜트기술 | 이태훈 | MRT-YT01-P3GM-128502 | 454 | [Sump Pump (DHI for Block 3, 4)]_SUMP PUMP_DATA SHEET & CHARACTERISTIC CURVE | FA | 2018-03-26 | 2018-08-23 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | SUMP PUMP
DHI | 플랜트기술 | 이태훈 | MRT-YD00-P2GM-128503 | 455 | [Sump Pump (DHI for Block 2)]_SUMP PUMP_PUMP SECTIONAL DRAWING | FI | 2018-04-26 | 2018-07-25 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2018-10-26 | 180656-FC STAMPED | FC | 1 | A | MECHANICAL | SUMP PUMP
DHI | 플랜트기술 | 이태훈 | MRT-YD00-P3GM-128503 | 456 | [Sump Pump (DHI for Block 3, 4)]_SUMP PUMP_PUMP SECTIONAL DRAWING | FI | 2018-04-26 | 2018-09-23 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | SUMP PUMP
DHI | 플랜트기술 | 이태훈 | MRT-XK00-P2GM-128504 | 457 | [Sump Pump (DHI for Block 2)]_SUMP PUMP_MECHANICAL SEAL SPECIFICATION | FI | 2018-05-15 | 2018-08-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2018-08-25 | 180395-FC STAMPED | FC | 0 | A | MECHANICAL | SUMP PUMP
DHI | 플랜트기술 | 이태훈 | MRT-XK00-P3GM-128504 | 458 | [Sump Pump (DHI for Block 3, 4)]_SUMP PUMP_MECHANICAL SEAL SPECIFICATION | FI | 2018-05-15 | 2018-10-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | SUMP PUMP
DHI | 플랜트기술 | 이태훈 | MRT-XK00-P2GM-128505 | 459 | [Sump Pump (DHI for Block 2)]_SUMP PUMP_COUPLING SPECIFICATION | FA | 2018-04-16 | 2018-07-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2018-10-26 | 180656-FC STAMPED | FC | 1 | A | MECHANICAL | SUMP PUMP
DHI | 플랜트기술 | 이태훈 | MRT-XK00-P3GM-128505 | 460 | [Sump Pump (DHI for Block 3, 4)]_SUMP PUMP_COUPLING SPECIFICATION | FA | 2018-04-16 | 2018-09-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | SUMP PUMP
DHI | 플랜트기술 | 이태훈 | MRT-XF00-P2GM-128510 | 461 | [Sump Pump (DHI for Block 2)]_SUMP PUMP_NAME PLATE DRAWING | FI | 2018-05-26 | 2018-09-23 | 2019-05-24 | 2019-05-27 | MRT-DS-REC-TT-180442-FC | FC | 0 | 2019-05-29 | 180442-FC STAMPED | FC | 0 | A | MECHANICAL | SUMP PUMP
DHI | 플랜트기술 | 이태훈 | MRT-XF00-P3GM-128510 | 462 | [Sump Pump (DHI for Block 3, 4)]_SUMP PUMP_NAME PLATE DRAWING | FI | 2018-05-26 | 2018-09-23 | 2019-05-24 | 2019-05-27 | MRT-DS-REC-TT-180442-FC | FC | 0 | 2019-12-06 | 180442-FC STAMPED | FC | 0 | A | MECHANICAL | SUMP PUMP
DHI | 플랜트기술 | 이태훈 | MRT-XW01-P2GM-128507 | 463 | [Sump Pump (DHI for Block 2)]_SUMP PUMP_MOTOR SPECIFICATION | FA | 2018-05-26 | 2018-08-24 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-01-12 | 180943-FC STAMPED | FC | 2 | A | ELECTRICAL | SUMP PUMP
DHI | 플랜트기술 | 이태훈 | MRT-XW01-P3GM-128507 | 464 | [Sump Pump (DHI for Block 3, 4)]_SUMP PUMP_MOTOR SPECIFICATION | FA | 2018-05-26 | 2018-10-23 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | ELECTRICAL | SUMP PUMP
DHI | 플랜트기술 | 이태훈 | MRT-YR05-P2GM-128511 | 465 | [Sump Pump (DHI for Block 2)]_SUMP PUMP_SCHEMATIC AND WIRING DIAGRAM WITH CONTROL PANEL LAYOUT DRAWING | FI | 2018-05-26 | 2018-08-24 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-01-12 | 180943-FC STAMPED | FC | 2 | A | ELECTRICAL | SUMP PUMP
DHI | 플랜트기술 | 이태훈 | MRT-YR05-P3GM-128511 | 466 | [Sump Pump (DHI for Block 3, 4)]_SUMP PUMP_SCHEMATIC AND WIRING DIAGRAM WITH CONTROL PANEL LAYOUT DRAWING | FI | 2018-05-26 | 2018-10-23 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240018 | AB | Z1 | 2024-12-03 | MTW-AS-C-LT-24.6022.0 | AB | Z1 | A | ELECTRICAL | SUMP PUMP
DHI | 플랜트기술 | 이태훈 | MRT-YL00-P2GM-128512 | 467 | [Sump Pump (DHI for Block 2)]_SUMP PUMP_INSTRUMENT LIST AND DATA SHEET | FI | 2018-05-26 | 2018-08-24 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-08-12 | 190176-FC STAMPED | FC | 3 | A | I&C | SUMP PUMP
DHI | 플랜트기술 | 이태훈 | MRT-YL00-P3GM-128512 | 468 | [Sump Pump (DHI for Block 3, 4)]_SUMP PUMP_INSTRUMENT LIST AND DATA SHEET | FI | 2018-05-26 | 2018-10-23 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240018 | AB | Z1 | 2024-12-03 | MTW-AS-C-LT-24.6022.0 | AB | Z1 | A | I&C | SUMP PUMP
DHI | 플랜트기술 | 이태훈 | MRT-XB00-P2GM-128506 | 469 | [Sump Pump (DHI for Block 2)]_SUMP PUMP_FOUNDATION DRAWINGS | FI | 2018-05-26 | 2018-08-24 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-04-29 | 190118-FC STAMPED | FC | 2 | A | CIVIL | SUMP PUMP
DHI | 플랜트기술 | 이태훈 | MRT-XB00-P3GM-128506 | 470 | [Sump Pump (DHI for Block 3, 4)]_SUMP PUMP_FOUNDATION DRAWINGS | FI | 2018-05-26 | 2018-10-23 | 2024-11-15 | 2024-11-15 | MRT-DS-REC-TT-240029 | AB | Z0 | 2025-02-20 | MTW-AS-C-LT-25.6213.0 | AB | Z0 | A | CIVIL | SUMP PUMP
DHI | 플랜트기술 | 이태훈 | MRT-CQ02-P2GM-128515 | 471 | [Sump Pump (DHI for Block 2)]_SUMP PUMP_O&M MANUAL | FI | 2018-08-10 | 2019-01-31 | 2018-11-14 | 2018-12-03 | MRT-DS-REC-TT-180839-FC | FC | 1 | 2018-12-08 | 180839-FC STAMPED | FC | 1 | A | SUPPORT | SUMP PUMP
DHI | 플랜트기술 | 이태훈 | MRT-CQ02-P3GM-128515 | 472 | [Sump Pump (DHI for Block 3, 4)]_SUMP PUMP_O&M MANUAL | FI | 2018-08-10 | 2019-01-31 | 2018-11-14 | 2018-12-03 | MRT-DS-REC-TT-180839-FC | FC | 1 | 2018-12-08 | 180839-FC STAMPED | FC | 1 | A | SUPPORT | SUMP PUMP
DHI | 플랜트기술 | 안성훈 | MRT-YD00-P0SMM-128001 | 473 | [Crane & Hoist(DHI)]_CRANE_GA DRAWING FOR STEAM TURBINE BUILDING CRANE | FA | 2018-01-05 | 2018-04-05 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-12-23 | 190223-FC STAMPED | FC | 4 | A | MECHANICAL | CRANE
DHI | 플랜트기술 | 안성훈 | MRT-YT01-P0SMM-128004 | 474 | [Crane & Hoist(DHI)]_CRANE_DATA SHEETS FOR STEAM TURBINE BUILDING CRANE | FA | 2018-01-05 | 2018-04-05 | 2018-07-27 | 2018-08-27 | MRT-DS-REC-TT-180446-FC | FC | 3 | 2018-09-12 | 180446-FC STAMPED | FC | 3 | A | MECHANICAL | CRANE
DHI | 플랜트기술 | 안성훈 | MRT-YK09-P0SMM-128007 | 475 | [Crane & Hoist(DHI)]_CRANE_MECHNICAL DETAIL FOR STEAM TURBINE BUILDING CRANE | FA | 2018-03-26 | 2018-06-24 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2020-01-02 | 190232-FC STAMPED | FC | 4 | A | MECHANICAL | CRANE
DHI | 플랜트기술 | 안성훈 | MRT-YK08-P0SMM-128001 | 476 | [Crane & Hoist(DHI)]_CRANE_NAMEPLATE DRAWING FOR STEAM TURBINE BUILDING CRANE | FI | 2018-03-20 | 2018-07-18 | 2019-05-24 | 2019-05-27 | MRT-DS-REC-TT-180232-FC | FC | 0 | 2019-05-29 | 180232-FC STAMPED | FC | 0 | A | MECHANICAL | CRANE
DHI | 플랜트기술 | 안성훈 | MRT-YS18-P0SMM-128010 | 477 | [Crane & Hoist(DHI)]_CRANE_ELECTRICAL DETAIL FOR STEAM TURBINE BUILDING CRANE | FI | 2018-03-26 | 2018-07-24 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2020-01-10 | 190242-FC STAMPED | FC | 2 | A | ELECTRICAL | CRANE
DHI | 플랜트기술 | 안성훈 | MRT-DM02-P0SMM-128001 | 478 | [Crane & Hoist(DHI)]_CRANE_INSTALLATION & ERECTION MANUAL FOR STEAM TURBINE BUILDING CRANE | FI | 2018-11-06 | 2019-01-06 | 2018-11-22 | 2018-11-22 | MRT-DS-REC-TT-180848-FC | FC | 0 | 2018-12-13 | 180848-FC STAMPED | FC | 0 | A | SUPPORT | CRANE
DHI | 플랜트기술 | 안성훈 | MRT-CT00-P0SMM-128001 | 479 | [Crane & Hoist(DHI)]_CRANE_OPERATION & MAINTENANCE MANUAL FOR STEAM TURBINE BUILDING CRANE | FI | 2018-11-06 | 2019-01-06 | 2018-11-22 | 2018-11-22 | MRT-DS-REC-TT-180848-FC | FC | 0 | 2018-12-13 | 180848-FC STAMPED | FC | 0 | A | SUPPORT | CRANE
DHI | 플랜트기술 | 박대영 | MRT-YD00-P2SM-128020 | 480 | [Crane & Hoist(DHI)]_HOIST_GA DRAWING (FOR BLOCK 2) | FI | 2018-04-30 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2018-12-07 | 180838-FC STAMPED | FC | 2 | A | MECHANICAL | HOIST
DHI | 플랜트기술 | 박대영 | MRT-YD00-P3SM-128020 | 481 | [Crane & Hoist(DHI)]_HOIST_GA DRAWING (FOR BLOCK 3, 4) | FI | 2018-04-30 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | HOIST
DHI | 플랜트기술 | 박대영 | MRT-YK09-P2SM-128040 | 482 | [Crane & Hoist(DHI)]_HOIST_MECHANICAL DETAIL (FOR BLOCK 2) | FI | 2018-04-30 | 2019-03-18 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-03-18 | 180841-FC STAMPED | FC | 1 | A | MECHANICAL | HOIST
DHI | 플랜트기술 | 박대영 | MRT-YK09-P3SM-128040 | 483 | [Crane & Hoist(DHI)]_HOIST_MECHANICAL DETAIL (FOR BLOCK 3, 4) | FI | 2018-04-30 | 2019-03-18 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | HOIST
DHI | 플랜트기술 | 박대영 | MRT-YT01-P2SM-128030 | 484 | [Crane & Hoist(DHI)]_HOIST_DATA SHEET (FOR BLOCK 2) | FI | 2018-04-30 | 2019-03-18 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-03-18 | 180420-FC STAMPED | FC | 0 | A | MECHANICAL | HOIST
DHI | 플랜트기술 | 박대영 | MRT-YT01-P3SM-128030 | 485 | [Crane & Hoist(DHI)]_HOIST_DATA SHEET (FOR BLOCK 3, 4) | FI | 2018-04-30 | 2019-03-18 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | HOIST
DHI | 플랜트기술 | 박대영 | MRT-YS18-P2SM-128050 | 486 | [Crane & Hoist(DHI)]_HOIST_ELECTRICAL DETAIL (FOR BLOCK 2) | FI | 2018-04-30 | 2019-03-18 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-03-18 | 180420-FC STAMPED | FC | 0 | A | ELECTRICAL | HOIST
DHI | 플랜트기술 | 박대영 | MRT-YS18-P3SM-128050 | 487 | [Crane & Hoist(DHI)]_HOIST_ELECTRICAL DETAIL (FOR BLOCK 3, 4) | FI | 2018-04-30 | 2019-03-18 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-07-12 | MTW-AS-C-LT-24.5518.0 | AB | Z0 | A | ELECTRICAL | HOIST
DHI | 플랜트기술 | 박대영 | MRT-CQ02-P2SM-128060 | 488 | [Crane & Hoist(DHI)]_HOIST_ O&M Manual (FOR BLOCK 2) | FI | 2018-11-30 | 2019-01-31 | 2018-12-24 | 2018-12-26 | MRT-DS-REC-TT-180918-FC | FC | 0 | 2018-12-27 | 180918-FC STAMPED | FC | 0 | A | SUPPORT | HOIST
DHI | 플랜트기술 | 박대영 | MRT-CQ02-P3SM-128060 | 489 | [Crane & Hoist(DHI)]_HOIST_ O&M Manual (FOR BLOCK 3, 4) | FI | 2018-11-30 | 2019-01-31 | 2018-12-24 | 2018-12-26 | MRT-DS-REC-TT-180918-FC | FC | 0 | 2018-12-27 | 180918-FC STAMPED | FC | 0 | A | SUPPORT | HOIST
DHI | 기계기술 | 김희정 | MRT-XG02-P2QC-130001 | 490 | [Chemical Dosing System For Block 2]_P&ID | FA | 2018-02-01 | 2018-05-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2018-10-23 | 180749-FC STMAPED | FC | 3 | A | MECHANICAL | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-XG02-P3QC-130001 | 491 | [Chemical Dosing system For Block 3, 4]_P&ID | FA | 2018-02-01 | 2018-05-16 | 2024-05-20 | 2024-05-20 | MRT-DS-REC-TT-240012 | AB | Z1 | 2024-06-08 | MTW-AS-C-LT-24.5327.0 | AB | Z1 | A | MECHANICAL | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-XA00-P2QC-130002 | 492 | [Chemical Dosing System For Block 2]_GENERAL ARRANGEMENT DRAWING | FA | 2018-02-01 | 2018-05-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2018-10-20 | 180760-FC STAMPED | FC | 3 | A | MECHANICAL | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-XA00-P3QC-130002 | 493 | [Chemical Dosing system For Block 3, 4]_GENERAL ARRANGEMENT DRAWING | FA | 2018-02-01 | 2018-05-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2018-10-20 | 180760-FC STAMPED | FC | 3 | A | MECHANICAL | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-XS00-P2QC-130003 | 494 | [Chemical Dosing System For Block 2]_SYSTEM DESCRIPTION | FA | 2018-02-01 | 2018-05-16 | 2018-07-27 | 2018-08-29 | MRT-DS-REC-TT-180463-FC | FC | 2 | 2018-09-13 | 180463-FC STAMPED | FC | 2 | A | MECHANICAL | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-XS00-P3QC-130003 | 495 | [Chemical Dosing system For Block 3, 4]_SYSTEM DESCRIPTION | FA | 2018-02-01 | 2018-05-16 | 2018-07-27 | 2018-08-29 | MRT-DS-REC-TT-180463-FC | FC | 2 | 2018-09-13 | 180463-FC STAMPED | FC | 2 | A | MECHANICAL | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-CC07-P2QC-130004 | 496 | [Chemical Dosing System For Block 2]_CALCULATION SHEET | FA | 2018-02-01 | 2018-05-16 | 2018-07-27 | 2018-08-29 | MRT-DS-REC-TT-180463-FC | FC | 2 | 2018-09-13 | 180463-FC STAMPED | FC | 2 | A | MECHANICAL | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-CC07-P3QC-130004 | 497 | [Chemical Dosing system For Block 3, 4]_CALCULATION SHEET | FA | 2018-02-01 | 2018-05-16 | 2018-07-27 | 2018-08-29 | MRT-DS-REC-TT-180463-FC | FC | 2 | 2018-09-13 | 180463-FC STAMPED | FC | 2 | A | MECHANICAL | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YD00-P2QC-130005 | 498 | [Chemical Dosing System For Block 2]_CONTROL PANEL ARRANGEMENT DRAWING | FI | 2018-03-01 | 2018-06-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2018-10-16 | 180750-FC STAMPED | FC | 3 | A | I&C | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YD00-P3QC-130005 | 499 | [Chemical Dosing system For Block 3, 4]_CONTROL PANEL ARRANGEMENT DRAWING | FI | 2018-03-01 | 2018-06-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5936.0 | AB | Z0 | A | I&C | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YF02-P2QC-130006 | 500 | [Chemical Dosing System For Block 2]_CONTROL CONFIGURATION DIAGRAM | FA | 2018-03-01 | 2018-06-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2018-12-10 | 180831-FC STAMPED | FC | 4 | A | I&C | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YF02-P3QC-130006 | 501 | [Chemical Dosing system For Block 3, 4]_CONTROL CONFIGURATION DIAGRAM | FA | 2018-03-01 | 2018-06-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6021.0 | AB | Z0 | A | I&C | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YL00-P2QC-130007 | 502 | [Chemical Dosing System For Block 2]_INSTRUMENT LIST | FI | 2018-03-01 | 2018-06-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-06-11 | 180694-FC STAMPED | FC | 2 | A | I&C | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YL00-P3QC-130007 | 503 | [Chemical Dosing system For Block 3, 4]_INSTRUMENT LIST | FI | 2018-03-01 | 2018-06-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6021.0 | AB | Z0 | A | I&C | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-XN00-P2QC-130008 | 504 | [Chemical Dosing System For Block 2]_VALVE LIST | FI | 2018-03-01 | 2018-06-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-05-29 | 180519-FC STAMPED | FC | 1 | A | MECHANICAL | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-XN00-P3QC-130008 | 505 | [Chemical Dosing system For Block 3, 4]_VALVE LIST | FI | 2018-03-01 | 2018-06-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-05-29 | 180519-FC STAMPED | FC | 1 | A | MECHANICAL | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-XB02-P2QC-130009 | 506 | [Chemical Dosing System For Block 2]_FOUNDATION AND LOADING DATA | FI | 2018-04-01 | 2018-07-14 | 2018-09-18 | 2018-10-10 | MRT-DS-REC-TT-180752-FC | FC | 2 | 2018-10-16 | 180752-FC STAMPED | FC | 2 | A | CIVIL | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-XB02-P3QC-130009 | 507 | [Chemical Dosing system For Block 3, 4]_FOUNDATION AND LOADING DATA | FI | 2018-04-01 | 2018-07-14 | 2018-09-18 | 2018-10-10 | MRT-DS-REC-TT-180752-FC | FC | 2 | 2018-10-16 | 180752-FC STAMPED | FC | 2 | A | CIVIL | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YK10-P2QC-130010 | 508 | [Chemical Dosing System For Block 2]_EQUIPMENT ASSEMBLY DRAWING | FI | 2018-04-01 | 2018-07-14 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2018-10-23 | 180698-FC STAMPED | FC | 2 | A | MECHANICAL | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YK10-P3QC-130010 | 509 | [Chemical Dosing system For Block 3, 4]_EQUIPMENT ASSEMBLY DRAWING | FI | 2018-04-01 | 2018-07-14 | 2025-01-21 | 2025-01-21 | MRT-DS-REC-TT-250005 | AB | Z2 | 2025-01-24 | MTW-AS-C-LT-25.6148.0 | AB | Z2 | A | MECHANICAL | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-XH01-P2QC-130011 | 510 | [Chemical Dosing System For Block 2]_PIPING ARRANGEMENT DRAWING | FI | 2018-04-01 | 2018-07-14 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-06-11 | 180761-FC STAMPED | FC | 2 | A | MECHANICAL | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-XH01-P3QC-130011 | 511 | [Chemical Dosing system For Block 3, 4]_PIPING ARRANGEMENT DRAWING | FI | 2018-04-01 | 2018-07-14 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-05-17 | MTW-AS-C-LT-24.5261.0 | AB | Z0 | A | MECHANICAL | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YT01-P2QC-130012 | 512 | [Chemical Dosing System For Block 2]_TECHNICAL DATASHEET | FI | 2018-04-01 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-06-17 | 180697-FC STAMPED | FC | 1 | A | MECHANICAL | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YT01-P3QC-130012 | 513 | [Chemical Dosing system For Block 3, 4]_TECHNICAL DATASHEET | FI | 2018-04-01 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-06-17 | 180697-FC STAMPED | FC | 1 | A | MECHANICAL | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YT01-P2QC-130013 | 514 | [Chemical Dosing System For Block 2]_MOTOR DATA SHEET | FI | 2018-04-01 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-05-29 | 180563-FC STAMPED | FC | 1 | A | ELECTRICAL | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YT01-P3QC-130013 | 515 | [Chemical Dosing system For Block 3, 4]_MOTOR DATA SHEET | FI | 2018-04-01 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-05-29 | 180563-FC STAMPED | FC | 1 | A | ELECTRICAL | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YT01-P2QC-130014 | 516 | [Chemical Dosing System For Block 2]_PUMP DATA SHEET | FI | 2018-04-01 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-05-29 | 180511-FC STAMPED | FC | 1 | A | MECHANICAL | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YT01-P3QC-130014 | 517 | [Chemical Dosing system For Block 3, 4]_PUMP DATA SHEET | FI | 2018-04-01 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-10-31 | MRT-YT01-P3QC-130014 | AB | Z0 | A | MECHANICAL | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YT01-P2QC-130016 | 518 | [Chemical Dosing System For Block 2]_INSTRUMENT DATA SHEET | FI | 2018-04-01 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-06-14 | 180695-FC STAMPED | FC | 2 | A | I&C | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YT01-P3QC-130016 | 519 | [Chemical Dosing system For Block 3, 4]_INSTRUMENT DATA SHEET | FI | 2018-04-01 | 2018-07-30 | 2025-01-21 | 2025-01-21 | MRT-DS-REC-TT-250005 | AB | Z1 | 2025-02-12 | MTW-AS-C-LT-25.6191.0 | AB | Z1 | A | I&C | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YV02-P2QC-130017 | 520 | [Chemical Dosing System For Block 2]_INTERCONNECTION WIRING DIAGRAM | FI | 2018-05-01 | 2018-08-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2018-10-22 | 180615-FC STAMPED | FC | 2 | A | I&C | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YV02-P3QC-130017 | 521 | [Chemical Dosing system For Block 3, 4]_INTERCONNECTION WIRING DIAGRAM | FI | 2018-05-01 | 2018-08-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5936.0 | AB | Z0 | A | I&C | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YL22-P2QC-130018 | 522 | [Chemical Dosing System For Block 2]_NAME PLATE DRAWING | FI | 2018-05-01 | 2018-08-29 | 2019-05-24 | 2019-06-17 | MRT-DS-REC-TT-180753-FC | FC | 1 | 2018-10-17 | 921/T/MRT/REC/X/2018 | FI | 1 | I | MECHANICAL | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YL22-P3QC-130018 | 523 | [Chemical Dosing system For Block 3, 4]_NAME PLATE DRAWING | FI | 2018-05-01 | 2018-08-29 | 2019-05-24 | 2019-06-17 | MRT-DS-REC-TT-180753-FC | FC | 1 | 2018-10-17 | 921/T/MRT/REC/X/2018 | FI | 1 | I | MECHANICAL | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YF00-P2QC-130019 | 524 | [Chemical Dosing System For Block 2]_CONTROL LOOP & LOGIC DIAGRAM | FI | 2018-05-01 | 2018-08-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-06-14 | 180520-FC STAMPED | FC | 1 | A | I&C | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YF00-P3QC-130019 | 525 | [Chemical Dosing system For Block 3, 4]_CONTROL LOOP & LOGIC DIAGRAM | FI | 2018-05-01 | 2018-08-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6021.0 | AB | Z0 | A | I&C | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YS01-P2QC-130020 | 526 | [Chemical Dosing System For Block 2]_SCHEMATIC DIAGRAM | FI | 2018-05-01 | 2018-08-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-06-19 | 180811-FC STAMPED | FC | 2 | A | ELECTRICAL | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YS01-P3QC-130020 | 527 | [Chemical Dosing system For Block 3, 4]_SCHEMATIC DIAGRAM | FI | 2018-05-01 | 2018-08-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6021.0 | AB | Z0 | A | ELECTRICAL | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YE00-P2QC-130021 | 528 | [Chemical Dosing System For Block 2]_CABLE TRAY LAYOUT DRAWING | FI | 2018-05-01 | 2018-08-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2018-10-26 | 180754-FC STAMPED | FC | 3 | A | ELECTRICAL | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YE00-P3QC-130021 | 529 | [Chemical Dosing system For Block 3, 4]_CABLE TRAY LAYOUT DRAWING | FI | 2018-05-01 | 2018-08-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5936.0 | AB | Z0 | A | ELECTRICAL | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YK00-P2QC-130022 | 530 | [Chemical Dosing System For Block 2]_HOOK UP DRAWING | FI | 2018-05-01 | 2018-08-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2018-10-23 | 180762-FC STAMPED | FC | 3 | A | I&C | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YK00-P3QC-130022 | 531 | [Chemical Dosing system For Block 3, 4]_HOOK UP DRAWING | FI | 2018-05-01 | 2018-08-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6021.0 | AB | Z0 | A | I&C | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YT01-P2QC-130033 | 532 | [Chemical Dosing System For Block 2]_PLC DATA SHEET | FI | 2018-04-01 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-06-14 | 180509-FC STAMPED | FC | 1 | A | I&C | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YT01-P3QC-130033 | 533 | [Chemical Dosing system For Block 3, 4]_PLC DATA SHEET | FI | 2018-04-01 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6021.0 | AB | Z0 | A | I&C | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YL01-P2QC-130034 | 534 | [Chemical Dosing System For Block 2]_PLC IO LIST | FI | 2018-05-01 | 2018-08-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-05-28 | 180891-FC STAMPED | FC | 3 | A | I&C | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YL01-P3QC-130034 | 535 | [Chemical Dosing system For Block 3, 4]_PLC IO LIST | FI | 2018-05-01 | 2018-08-29 | 2025-01-21 | 2025-01-21 | MRT-DS-REC-TT-250005 | AB | Z1 | 2025-02-12 | MTW-AS-C-LT-25.6191.0 | AB | Z1 | A | I&C | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YD05-P2QC-130035 | 536 | [Chemical Dosing System For Block 2]_HMI GRAPHICS | FI | 2018-05-01 | 2018-08-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-06-19 | 180904-FC STAMPED | FC | 3 | A | I&C | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YD05-P3QC-130035 | 537 | [Chemical Dosing system For Block 3, 4]_HMI GRAPHICS | FI | 2018-05-01 | 2018-08-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5936.0 | AB | Z0 | A | I&C | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-CQ02-P2QC-130036 | 538 | [Chemical Dosing System For Block 2]_Installation & Erection Manual | FI | 2018-11-30 | 2019-02-28 | 2018-12-19 | 2018-12-19 | MRT-DS-REC-TT-180925-FC | FC | 0 | 2018-12-22 | 180925-FC STAMPED | FC | 0 | A | SUPPORT | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-CQ02-P3QC-130036 | 539 | [Chemical Dosing System For Block 3,4]_Installation & Erection Manual | FI | 2018-11-30 | 2019-02-28 | 2018-12-19 | 2018-12-19 | MRT-DS-REC-TT-180925-FC | FC | 0 | 2018-12-22 | 180925-FC STAMPED | FC | 0 | A | SUPPORT | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-DN05-P2QC-130001 | 540 | [Chemical Dosing System For Block 2]_Commissioning Manual | FA | 2018-11-30 | 2019-02-28 | 2019-01-02 | 2019-01-03 | MRT-DS-REC-TT-180924-FC | FC | 0 | 2021-01-14 | 001/SER.00.01/LE/2021 | FC | 0 | A | SUPPORT | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-DN05-P3QC-130001 | 541 | [Chemical dosing system For Block 3, 4]_Commissioning Manual | FA | 2018-11-30 | 2019-02-28 | 2019-01-02 | 2019-01-03 | MRT-DS-REC-TT-180924-FC | FC | 0 | 2021-01-14 | 001/SER.00.01/LE/2021 | FC | 0 | A | SUPPORT | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-CQ02-P2QC-130023 | 542 | [Chemical Dosing System For Block 2]_O&M MANUAL | FI | 2018-06-29 | 2018-11-30 | 2018-11-15 | 2018-12-04 | MRT-DS-REC-TT-180581-FC | FC | 0 | 2018-12-11 | 180581-FC STAMPED | FC | 0 | A | SUPPORT | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-CQ02-P3QC-130023 | 543 | [Chemical Dosing system For Block 3, 4]_O&M MANUAL | FI | 2018-06-29 | 2018-11-30 | 2018-11-15 | 2018-12-04 | MRT-DS-REC-TT-180581-FC | FC | 0 | 2018-12-11 | 180581-FC STAMPED | FC | 0 | A | SUPPORT | CHEMICAL DOSING SYSTEM
DHI | 기계기술 | 김희정 | MRT-XG02-P2QU-130024 | 544 | [Sampling System_For Block 2]_P&ID | FA | 2018-01-31 | 2018-05-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2018-09-13 | 180449-FC STAMPED | FC | 2 | A | MECHANICAL | SAMPLING SYSTEM
DHI | 기계기술 | 김희정 | MRT-XG02-P3QU-130024 | 545 | [Sampling System_For Block 3,4]_P&ID | FA | 2018-01-31 | 2018-05-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-05-17 | MTW-AS-C-LT-24.5261.0 | AB | Z0 | A | MECHANICAL | SAMPLING SYSTEM
DHI | 기계기술 | 김희정 | MRT-XA00-P2QU-130025 | 546 | [Sampling System_For Block 2]_GENERAL ARRANGEMENT DRAWING | FA | 2018-01-31 | 2018-05-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2018-12-17 | 180870-FC STAMPED | FC | 6 | A | MECHANICAL | SAMPLING SYSTEM
DHI | 기계기술 | 김희정 | MRT-XA00-P3QU-130025 | 547 | [Sampling System_For Block 3,4]_GENERAL ARRANGEMENT DRAWING | FA | 2018-01-31 | 2018-05-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2018-12-07 | 180842-FC STAMPED | FC | 5 | A | MECHANICAL | SAMPLING SYSTEM
DHI | 기계기술 | 김희정 | MRT-XS00-P2QU-130026 | 548 | [Sampling System_For Block 2]_SYSTEM DESCRIPTION | FA | 2018-01-31 | 2018-05-15 | 2018-11-07 | 2018-12-03 | MRT-DS-REC-TT-180832-FC | FC | 3 | 2018-12-07 | 180832-FC STAMPED | FC | 3 | A | MECHANICAL | SAMPLING SYSTEM
DHI | 기계기술 | 김희정 | MRT-XS00-P3QU-130026 | 549 | [Sampling System_For Block 3,4]_SYSTEM DESCRIPTION | FA | 2018-01-31 | 2018-05-15 | 2018-11-07 | 2018-12-03 | MRT-DS-REC-TT-180832-FC | FC | 3 | 2018-12-07 | 180832-FC STAMPED | FC | 3 | A | MECHANICAL | SAMPLING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YF02-P2QU-130027 | 550 | [Sampling System_For Block 2]_CONTROL CONFIGURATION DIAGRAM | FA | 2018-02-28 | 2018-06-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2018-09-21 | 180499-FC STAMPED | FC | 2 | A | I&C | SAMPLING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YF02-P3QU-130027 | 551 | [Sampling System_For Block 3,4]_CONTROL CONFIGURATION DIAGRAM | FA | 2018-02-28 | 2018-06-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6021.0 | AB | Z0 | A | I&C | SAMPLING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YL00-P2QU-130028 | 552 | [Sampling System_For Block 2]_INSTRUMENT LIST | FI | 2018-02-28 | 2018-06-28 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-05-29 | 180424-FC STAMPED | FC | 1 | A | I&C | SAMPLING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YL00-P3QU-130028 | 553 | [Sampling System_For Block 3,4]_INSTRUMENT LIST | FI | 2018-02-28 | 2018-06-28 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6021.0 | AB | Z0 | A | I&C | SAMPLING SYSTEM
DHI | 기계기술 | 김희정 | MRT-XN00-P2QU-130029 | 554 | [Sampling System_For Block 2]_VALVE LIST | FI | 2018-02-28 | 2018-06-28 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-05-29 | 180152-FC STAMPED | FC | 0 | A | MECHANICAL | SAMPLING SYSTEM
DHI | 기계기술 | 김희정 | MRT-XN00-P3QU-130029 | 555 | [Sampling System_For Block 3,4]_VALVE LIST | FI | 2018-02-28 | 2018-06-28 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-05-29 | 180152-FC STAMPED | FC | 0 | A | MECHANICAL | SAMPLING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YT01-P2QU-130030 | 556 | [Sampling System_For Block 2]_TECHNICAL DATASHEET | FI | 2018-03-31 | 2018-07-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-05-29 | 180423-FC STAMPED | FC | 1 | A | MECHANICAL | SAMPLING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YT01-P3QU-130030 | 557 | [Sampling System_For Block 3,4]_TECHNICAL DATASHEET | FI | 2018-03-31 | 2018-07-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-05-29 | 180293-FC STAMPED | FC | 0 | A | MECHANICAL | SAMPLING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YT01-P2QU-130031 | 558 | [Sampling System_For Block 2]_INSTRUMENT DATA SHEET | FI | 2018-03-31 | 2018-07-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-06-19 | 180757-FC STAMPED | FC | 3 | A | I&C | SAMPLING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YT01-P3QU-130031 | 559 | [Sampling System_For Block 3,4]_INSTRUMENT DATA SHEET | FI | 2018-03-31 | 2018-07-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6021.0 | AB | Z0 | A | I&C | SAMPLING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YV02-P2QU-130032 | 560 | [Sampling System_For Block 2]_INTERCONNECTION WIRING DIAGRAM | FI | 2018-03-31 | 2018-07-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2018-10-05 | 180612-FC STAMPED | FC | 2 | A | ELECTRICAL | SAMPLING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YV02-P3QU-130032 | 561 | [Sampling System_For Block 3,4]_INTERCONNECTION WIRING DIAGRAM | FI | 2018-03-31 | 2018-07-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6021.0 | AB | Z0 | A | ELECTRICAL | SAMPLING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YF00-P2QU-130033 | 562 | [Sampling System_For Block 2]_CONTROL LOOP & LOGIC DIAGRAM | FI | 2018-03-31 | 2018-07-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-06-19 | 180757-FC STAMPED | FC | 3 | A | I&C | SAMPLING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YF00-P3QU-130033 | 563 | [Sampling System_For Block 3,4]_CONTROL LOOP & LOGIC DIAGRAM | FI | 2018-03-31 | 2018-07-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6021.0 | AB | Z0 | A | I&C | SAMPLING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YS01-P2QU-130034 | 564 | [Sampling System_For Block 2]_SCHEMATIC DIAGRAM | FI | 2018-03-31 | 2018-07-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-06-19 | 180715-FC STAMPED | FC | 3 | A | ELECTRICAL | SAMPLING SYSTEM
DHI | 기계기술 | 김희정 | MRT-YS01-P3QU-130034 | 565 | [Sampling System_For Block 3,4]_SCHEMATIC DIAGRAM | FI | 2018-03-31 | 2018-07-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6021.0 | AB | Z0 | A | ELECTRICAL | SAMPLING SYSTEM
DHI | 기계기술 | 김희정 | MRT-CQ02-P2QU-130036 | 566 | [Sampling System For Block 2]_Installation & Erection Manual | FI | 2018-11-23 | 2019-02-23 | 2018-11-26 | 2018-11-26 | MRT-DS-REC-TT-180901-FC | FC | 0 | 2018-12-03 | 180901-FC STAMPED | FC | 0 | A | SUPPORT | SAMPLING SYSTEM
DHI | 기계기술 | 김희정 | MRT-CQ02-P3QU-130036 | 567 | [Sampling System For Block 3,4]_Installation & Erection Manual | FI | 2018-11-23 | 2019-02-23 | 2018-11-26 | 2018-11-26 | MRT-DS-REC-TT-180901-FC | FC | 0 | 2018-12-03 | 180901-FC STAMPED | FC | 0 | A | SUPPORT | SAMPLING SYSTEM
DHI | 기계기술 | 김희정 | MRT-DN05-P2QU-130001 | 568 | [Sampling System For Block 2]_Commissioning Manual | FA | 2018-11-23 | 2019-02-23 | 2021-02-09 | 2021-02-09 | MRT-DS-REC-TT-210003 | FC | 1 | 2021-03-11 | DEEMED APPROVAL | FC | 1 | A | SUPPORT | SAMPLING SYSTEM
DHI | 기계기술 | 김희정 | MRT-DN05-P3QU-130001 | 569 | [Sampling system For Block 3, 4]_Commissioning Manual | FA | 2018-11-23 | 2019-02-23 | 2021-02-09 | 2021-02-09 | MRT-DS-REC-TT-210003 | FC | 1 | 2021-03-11 | DEEMED APPROVAL | FC | 1 | A | SUPPORT | SAMPLING SYSTEM
DHI | 기계기술 | 김희정 | MRT-CQ02-P2QU-130035 | 570 | [Sampling System_For Block 2]_O&M MANUAL | FI | 2018-04-30 | 2018-11-30 | 2018-11-15 | 2018-12-03 | MRT-DS-REC-TT-180373-FC | FC | 0 | 2018-12-07 | 180373-FC STAMPED | FC | 0 | A | SUPPORT | SAMPLING SYSTEM
DHI | 기계기술 | 김희정 | MRT-CQ02-P3QU-130035 | 571 | [Sampling System_For Block 3,4]_O&M MANUAL | FI | 2018-04-30 | 2018-11-30 | 2018-11-15 | 2018-12-03 | MRT-DS-REC-TT-180373-FC | FC | 0 | 2018-12-07 | 180373-FC STAMPED | FC | 0 | A | SUPPORT | SAMPLING SYSTEM
DHI | 배관기술 | 김근유 | MRT-DE00-P0ZEN-140001 | 572 | [Piping General]_Piping material specification | FA | 2017-08-31 | 2017-11-30 | 2019-01-14 | 2019-01-14 | MRT-DS-REC-TT-180939-FC | FC | 3 | 2019-01-15 | 180939-FC STAMPED | FC | 3 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-CV03-P0ZEN-140002 | 573 | [Piping General]_Piping Insulation Specification | FA | 2017-08-31 | 2017-11-30 | 2019-03-28 | 2019-03-29 | MRT-DS-REC-TT-190060-FC | FC | 3 | 2019-03-30 | 190060-FC STAMPED | FC | 3 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-DE00-P0ZEN-140002 | 574 | [Piping General]_Material Specification for GRP | FA | 2018-12-31 | 2019-01-31 | 2019-01-02 | 2019-01-03 | MRT-DS-REC-TT-180934-FC | FC | 0 | 2019-01-05 | 180934-FC STAMPED | FC | 0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-CC05-P0ZEN-140001 | 575 | [Piping General]_Product Detail Drawing for GRP | FA | 2018-12-31 | 2019-01-31 | 2019-01-02 | 2019-01-03 | MRT-DS-REC-TT-180934-FC | FC | 0 | 2019-01-05 | 180934-FC STAMPED | FC | 0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-CC07-P0ZEN-140001 | 576 | [Piping General]_Wall thickness calculation for GRP | FA | 2018-12-31 | 2019-01-31 | 2019-01-02 | 2019-01-03 | MRT-DS-REC-TT-180934-FC | FC | 0 | 2019-01-05 | 180934-FC STAMPED | FC | 0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-DL03-P0ZEN-140001 | 577 | [Piping General]_Transporting, Handling & Storage Procedure for GRP Installation | FI | 2019-02-21 | 2019-04-21 | 2019-04-12 | 2019-04-15 | MRT-DS-REC-TT-190050-FC | FC | 0 | 2019-04-15 | 190050-FC STAMPED | FC | 0 | A | SUPPORT | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-DM01-P0ZEN-140001 | 578 | [Piping General]_Installation Manual for GRP | FI | 2019-02-01 | 2019-04-01 | 2019-02-11 | 2019-02-12 | MRT-DS-REC-TT-190027-FC | FC | 0 | 2019-02-14 | 190027-FC STAMPED | FC | 0 | A | SUPPORT | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-DM01-P0ZEN-140002 | 579 | [Piping General]_Hydrotest procedure for GRP installation | FI | 2019-02-21 | 2019-04-21 | 2019-05-30 | 2019-06-14 | MRT-DS-REC-TT-190123-FC | FC | 1 | 2019-06-17 | 190123-FC STAMPED | FC | 1 | A | SUPPORT | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-DF04-P2ZEN-142001 | 580 | [Piping General]_Stress Analysis Report for HP & CRH Steam system Block #2 | FI | 2018-03-31 |  | 2018-04-03 | 2018-04-03 | MRT-DS-REC-TT-180274 | FI | 0 | 2018-04-16 | 213/T/MRT/REC/IV/2018 | FI | 0 | I | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-DF04-P2ZEN-142002 | 581 | [Piping General]_Stress Analysis Report for HRH Steam system Block #2 | FI | 2018-03-31 |  | 2018-04-03 | 2018-04-03 | MRT-DS-REC-TT-180274 | FI | 0 | 2018-04-16 | 213/T/MRT/REC/IV/2018 | FI | 0 | I | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-DF04-P2ZEN-142003 | 582 | [Piping General]_Stress Analysis Report for LP Steam system Block #2 | FI | 2018-04-30 |  | 2018-06-18 | 2018-06-18 | MRT-DS-REC-TT-180512 | FI | 1 | 2018-07-02 | 469/T/MRT/REC/VII/2018 | FI | 1 | I | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-DF04-P2ZEN-142004 | 583 | [Piping General]_Stress Analysis Report for Feed water system Block #2 | FI | 2018-04-30 |  | 2018-06-18 | 2018-06-18 | MRT-DS-REC-TT-180512 | FI | 1 | 2018-07-02 | 469/T/MRT/REC/VII/2018 | FI | 1 | I | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-DF04-P3ZEN-143001 | 584 | [Piping General]_Stress Analysis Report for HP & CRH Steam system Block #3 | FI | 2018-05-10 |  | 2018-05-29 | 2018-05-29 | MRT-DS-REC-TT-180439 | FI | 0 | 2018-06-29 | 445/T/MRT/REC/VI/2018 | FI | 0 | I | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-DF04-P3ZEN-143002 | 585 | [Piping General]_Stress Analysis Report for HRH Steam system Block #3 | FI | 2018-05-10 |  | 2018-06-05 | 2018-06-05 | MRT-DS-REC-TT-180466 | FI | 0 | 2018-06-29 | 456/T/MRT/REC/VI/2018 | FI | 0 | I | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-DF04-P3ZEN-143003 | 586 | [Piping General]_Stress Analysis Report for LP Steam system Block #3 | FI | 2018-05-10 |  | 2018-05-29 | 2018-05-29 | MRT-DS-REC-TT-180439 | FI | 0 | 2018-06-29 | 445/T/MRT/REC/VI/2018 | FI | 0 | I | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-DF04-P3ZEN-143004 | 587 | [Piping General]_Stress Analysis Report for Feed water system Block #3 | FI | 2018-05-10 |  | 2018-06-05 | 2018-06-05 | MRT-DS-REC-TT-180466 | FI | 0 | 2018-06-29 | 456/T/MRT/REC/VI/2018 | FI | 0 | I | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-DF04-P3ZEN-144001 | 588 | [Piping General]_Stress Analysis Report for HP & CRH Steam system Block #4 | FI | 2018-05-31 |  | 2018-09-19 | 2018-09-19 | MRT-DS-REC-TT-180790 | FI | 1 | 2018-11-14 | 1014/T/MRT/REC/XI/2018 | FI | 1 | I | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-DF04-P3ZEN-144002 | 589 | [Piping General]_Stress Analysis Report for HRH Steam system Block #4 | FI | 2018-05-31 |  | 2018-09-19 | 2018-09-19 | MRT-DS-REC-TT-180790 | FI | 1 | 2018-11-14 | 1014/T/MRT/REC/XI/2018 | FI | 1 | I | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-DF04-P3ZEN-144003 | 590 | [Piping General]_Stress Analysis Report for LP Steam system Block #4 | FI | 2018-05-31 |  | 2018-06-18 | 2018-06-18 | MRT-DS-REC-TT-180513 | FI | 0 | 2018-07-03 | 495/T/MRT/REC/VII/2018 | FI | 0 | I | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-DF04-P3ZEN-144004 | 591 | [Piping General]_Stress Analysis Report for Feed water system Block #4 | FI | 2018-05-31 |  | 2018-09-19 | 2018-09-19 | MRT-DS-REC-TT-180790 | FI | 1 | 2018-11-14 | 1014/T/MRT/REC/XI/2018 | FI | 1 | I | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XN00-P0ZEN-140001 | 592 | [Piping General]_Manual Valve List | FA | 2017-10-30 | 2018-02-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-01-22 | 180932-FC STAMPED | FC | 4 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XL00-P0ZEN-140001 | 593 | [Piping General]_Piping Line List | FA | 2017-10-30 | 2018-02-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2018-08-03 | 180225-FC STAMPED | FC | 3 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XL00-P0ZEN-140002 | 594 | [Piping General]_Piping Specialty List | FA | 2017-11-30 | 2018-02-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-01-22 | 180932-FC STAMPED | FC | 4 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XK00-P0ZEN-140001 | 595 | [Piping General]_Typical Installation Drawing for Pipe Support | FA | 2018-02-28 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2018-08-25 | 180355-FC STAMPED | FC | 1 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XH01-P0UZT-140001 | 596 | [Yard_Piping]_Key Plan for Piping Arrangement Drawing | FA | 2017-12-30 | 2018-03-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2018-09-05 | 180310-FC STAMPED | FC | 2 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XH01-P0UZT-140000 | 597 | [Yard_Piping]_Piping Arrangement Drawing for Yard area | FA | 2018-02-28 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-03-12 | 190031-FC STAMPED | FC | 2 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XH01-P2UMA-142000 | 598 | [Steam Turbine Building_Piping]_Piping Arrangement Drawing for Block 2 STG Building Area | FA | 2018-02-28 | 2018-05-18 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2018-08-03 | 681/T/MRT/REC/VII/2018 | FC | 1 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XH01-P3UMA-143000 | 599 | [Steam Turbine Building_Piping]_Piping Arrangement Drawing for Block 3 STG Building Area | FA | 2018-06-15 | 2018-08-14 | 2024-11-18 | 2024-11-18 | MRT-DS-REC-TT-240032 | AB | Z1 | 2024-12-03 | MTW-AS-C-LT-24.6019.0 | AB | Z1 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XH01-P3UMA-144000 | 600 | [Steam Turbine Building_Piping]_Piping Arrangement Drawing for Block 4 STG Building Area | FA | 2018-07-20 | 2018-09-18 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2024-02-29 | MTW-AS-C-LT-24.4987.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XH01-P2ULY-142000 | 601 | [Pipe Rack_Piping]_Piping Arrangement Drawing for Block 2 Piperack area | FA | 2017-12-30 | 2018-03-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-11-25 | 190216-FC STAMPED | FC | 3 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XH01-P3ULY-143000 | 602 | [Pipe Rack_Piping]_Piping Arrangement Drawing for Block 3 Piperack area | FA | 2017-12-30 | 2018-03-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2024-02-29 | MTW-AS-C-LT-24.4987.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XH01-P3ULY-144000 | 603 | [Pipe Rack_Piping]_Piping Arrangement Drawing for Block 4 Piperack area | FA | 2017-12-30 | 2018-03-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2024-02-29 | MTW-AS-C-LT-24.4987.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P2LBA-142000 | 604 | [Steam and Bypass system(For Block 2)_Piping]_Piping ISO drawing_LB | FI | 2018-04-30 |  | 2024-05-14 | 2024-05-14 | MRT-DS-REC-TT-240011 | AB | Z1 | 2024-05-20 | MTW-AS-C-LT-24.5268.0 | AB | Z1 | C | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P2LBA-145000 | 605 | [Steam and Bypass system(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2018-12-21 | 2019-03-29 | 2024-05-14 | 2024-05-14 | MRT-DS-REC-TT-240011 | AB | Z1 | 2024-05-20 | MTW-AS-C-LT-24.5268.0 | AB | Z1 | C | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P3LBA-143000 | 606 | [Steam and Bypass system(For Block 3)_Piping]_Piping ISO drawing_LB | FI | 2018-05-31 |  | 2024-05-14 | 2024-05-14 | MRT-DS-REC-TT-240011 | AB | Z1 | 2024-09-20 | MTW-AS-C-LT-24.5759.0 | AB | Z1 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3LBA-146000 | 607 | [Steam and Bypass system(For Block 3)_Piping]_Piping ISO drawing_SB | FI | 2019-01-31 | 2019-03-29 | 2024-10-18 | 2024-10-18 | MRT-DS-REC-TT-240016 | AB | Z1 | 2024-12-13 | MTW-AS-C-LT-24.6064.0 | AB | Z1 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P3LBA-144000 | 608 | [Steam and Bypass system(For Block 4)_Piping]_Piping ISO drawing_LB | FI | 2018-06-30 |  | 2024-05-14 | 2024-05-14 | MRT-DS-REC-TT-240011 | AB | Z1 | 2024-09-20 | MTW-AS-C-LT-24.5759.0 | AB | Z1 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3LBA-147000 | 609 | [Steam and Bypass system(For Block 4)_Piping]_Piping ISO drawing_SB | FI | 2019-04-15 | 2019-05-15 | 2024-10-18 | 2024-10-18 | MRT-DS-REC-TT-240016 | AB | Z1 | 2024-12-13 | MTW-AS-C-LT-24.6064.0 | AB | Z1 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P2LCM-142000 | 610 | [Steam Drain System(For Block 2)_Piping]_Piping ISO drawing_LB | FI | 2018-05-25 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2020-01-24 | 200009-FC STAMPED | FC | 2A | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P2LCM-145000 | 611 | [Steam Drain System(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2018-12-21 | 2019-03-29 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2020-12-07 | 200088-FC STAMPED | FC | 1B | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P3LCM-143000 | 612 | [Steam Drain System(For Block 3)_Piping]_Piping ISO drawing_LB | FI | 2018-06-25 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3LCM-146000 | 613 | [Steam Drain System(For Block 3)_Piping]_Piping ISO drawing_SB | FI | 2019-01-31 | 2019-03-29 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P3LCM-144000 | 614 | [Steam Drain System(For Block 4)_Piping]_Piping ISO drawing_LB | FI | 2018-08-17 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3LCM-147000 | 615 | [Steam Drain System(For Block 4)_Piping]_Piping ISO drawing_SB | FI | 2019-04-15 | 2019-05-15 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P2MAA-142000 | 616 | [ST Misc system(For Block 2)_Piping]_Piping ISO drawing_LB | FI | 2019-04-30 | 2019-05-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2020-02-19 | 200017-FC STAMPED | FC | 1 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P2MAA-145000 | 617 | [ST Misc system(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2019-03-29 | 2019-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2020-12-07 | 200088-FC STAMPED | FC | 1B | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P3MAA-143000 | 618 | [ST Misc system(For Block 3)_Piping]_Piping ISO drawing_LB | FI | 2019-04-30 | 2019-05-31 | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3MAA-146000 | 619 | [ST Misc system(For Block 3)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P3MAA-144000 | 620 | [ST Misc system(For Block 4)_Piping]_Piping ISO drawing_LB | FI | 2019-04-30 | 2019-05-31 | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3MAA-147000 | 621 | [ST Misc system(For Block 4)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P0LBG-141000 | 622 | [Aux Steam System(Common)_Piping]_Piping ISO drawing_LB | FI | 2018-08-31 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2023-11-17 | MTW-AS-C-LT-23.4620.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P0LBG-140000 | 623 | [Aux Steam System(Common)_Piping]_Piping ISO drawing_SB | FI | 2019-02-28 | 2019-03-29 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2019-12-17 | 190238-FC STAMPED | FC | 1A | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P2LBG-142000 | 624 | [Aux Steam System(For Block 2)_Piping]_Piping ISO drawing_LB | FI | 2018-05-18 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2020-01-24 | 200009-FC STAMPED | FC | 2A | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P2LBG-145000 | 625 | [Aux Steam System(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2018-12-21 | 2019-03-29 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-08-15 | 190178-FC STAMPED | FC | 1 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P3LBG-143000 | 626 | [Aux Steam System(For Block 3)_Piping]_Piping ISO drawing_LB | FI | 2018-06-18 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3LBG-146000 | 627 | [Aux Steam System(For Block 3)_Piping]_Piping ISO drawing_SB | FI | 2019-01-31 | 2019-03-29 | 2024-10-18 | 2024-10-18 | MRT-DS-REC-TT-240016 | AB | Z1 | 2024-12-13 | MTW-AS-C-LT-24.6064.0 | AB | Z1 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P3LBG-144000 | 628 | [Aux Steam System(For Block 4)_Piping]_Piping ISO drawing_LB | FI | 2018-07-18 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3LBG-147000 | 629 | [Aux Steam System(For Block 4)_Piping]_Piping ISO drawing_SB | FI | 2019-04-15 | 2019-05-15 | 2024-10-18 | 2024-10-18 | MRT-DS-REC-TT-240016 | AB | Z1 | 2024-12-13 | MTW-AS-C-LT-24.6064.0 | AB | Z1 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P2LCA-142000 | 630 | [Condensate system(For Block 2)_Piping]_Piping ISO drawing_LB | FI | 2018-05-31 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2020-01-24 | 200009-FC STAMPED | FC | 2C | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P2LCA-145000 | 631 | [Condensate system(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2018-12-21 | 2019-03-29 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2020-12-07 | 200088-FC STAMPED | FC | 2B | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P3LCA-143000 | 632 | [Condensate system(For Block 3)_Piping]_Piping ISO drawing_LB | FI | 2018-06-30 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3LCA-146000 | 633 | [Condensate system(For Block 3)_Piping]_Piping ISO drawing_SB | FI | 2019-01-31 | 2019-03-29 | 2025-01-17 | 2025-01-17 | MRT-DS-REC-TT-250004 | AB | Z0 | 2025-01-23 | MTW-AS-C-LT-25.6149.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P3LCA-144000 | 634 | [Condensate system(For Block 4)_Piping]_Piping ISO drawing_LB | FI | 2018-08-17 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3LCA-147000 | 635 | [Condensate system(For Block 4)_Piping]_Piping ISO drawing_SB | FI | 2019-04-15 | 2019-05-15 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P2LAB-142000 | 636 | [Feedwater system(For Block 2)_Piping]_Piping ISO drawing_LB | FI | 2018-05-18 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2020-01-24 | 200009-FC STAMPED | FC | 2A | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P2LAB-145000 | 637 | [Feedwater system(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2018-12-21 | 2019-03-29 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-08-15 | 190177-FC STAMPED | FC | 1 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P3LAB-143000 | 638 | [Feedwater system(For Block 3)_Piping]_Piping ISO drawing_LB | FI | 2018-06-18 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3LAB-146000 | 639 | [Feedwater system(For Block 3)_Piping]_Piping ISO drawing_SB | FI | 2019-01-31 | 2019-03-29 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P3LAB-144000 | 640 | [Feedwater system(For Block 4)_Piping]_Piping ISO drawing_LB | FI | 2018-07-18 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3LAB-147000 | 641 | [Feedwater system(For Block 4)_Piping]_Piping ISO drawing_SB | FI | 2019-04-15 | 2019-05-15 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P0GHC-140001 | 642 | [Make-up Water System_Piping]_Piping ISO drawing_LB | FI | 2018-05-30 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2023-11-17 | MTW-AS-C-LT-23.4620.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P0GHC-141000 | 643 | [Make-up Water System_Piping]_Piping ISO drawing_SB | FI | 2019-03-29 | 2019-04-30 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2021-03-26 | 210018-FC STAMPED | FC | 1D | 1 | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P2PAB-140001 | 644 | [Cooling Water System(For Block 2)_Piping]_Piping ISO drawing_LB | FI | 2018-01-31 | 2018-05-04 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-09-27 | 190198-FC STAMPED | FC | 4A | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P2PAB-145000 | 645 | [Cooling Water System(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2018-12-21 | 2019-03-29 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-09-17 | 190171-FC STAMPED | FC | 1 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3PAB-140001 | 646 | [Cooling Water System(For Block 3, 4)_Piping]_Piping ISO drawing_LB | FI | 2018-01-31 | 2018-05-04 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3PAB-146000 | 647 | [Cooling Water System(For Block 3, 4)_Piping]_Piping ISO drawing_SB | FI | 2019-01-31 | 2019-03-29 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P2PAB-142200 | 648 | [Cooling Water Miscellaneous System(For Block 2)_Piping]_Piping ISO drawing | FI | 2019-02-01 | 2019-02-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2021-03-26 | 210018-FC STAMPED | FC | 1B | 1 | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3PAB-143200 | 649 | [Cooling Water Miscellaneous System(For Block 3)_Piping]_Piping ISO drawing | FI | 2019-02-01 | 2019-02-28 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3PAB-144200 | 650 | [Cooling Water Miscellaneous System(For Block 4)_Piping]_Piping ISO drawing | FI | 2019-02-01 | 2019-02-28 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P2PAB-142100 | 651 | [Aux Cooling Water System(For Block 2)_Piping]_Piping ISO drawing_LB | FI | 2018-02-28 | 2018-05-04 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-11-15 | 190226-FC STAMPED | FC | 3B | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P2PAB-145100 | 652 | [Aux Cooling Water System(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2018-12-21 | 2019-03-29 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-09-17 | 190171-FC STAMPED | FC | 1 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3PAB-143100 | 653 | [Aux Cooling Water System(For Block 3)_Piping]_Piping ISO drawing_LB | FI | 2018-02-28 | 2018-05-04 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3PAB-146100 | 654 | [Aux Cooling Water System(For Block 3)_Piping]_Piping ISO drawing_SB | FI | 2019-01-31 | 2019-03-29 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3PAB-144100 | 655 | [Aux Cooling Water System(For Block 4)_Piping]_Piping ISO drawing_LB | FI | 2018-02-28 | 2018-05-04 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3PAB-147100 | 656 | [Aux Cooling Water System(For Block 4)_Piping]_Piping ISO drawing_SB | FI | 2019-02-28 | 2019-05-15 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P2PGB-142000 | 657 | [Closed cooling water system(For Block 2)_Piping]_Piping ISO drawing_LB | FI | 2018-05-18 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2022-11-25 | 220023-FC STAMPED | FC | 2C | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P2PGB-145000 | 658 | [Closed cooling water system(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2018-12-21 | 2019-03-29 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2020-11-19 | 200083-FC STAMPED | FC | 1B | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P3PGB-143000 | 659 | [Closed cooling water system(For Block 3)_Piping]_Piping ISO drawing_LB | FI | 2018-06-18 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3PGB-146000 | 660 | [Closed cooling water system(For Block 3)_Piping]_Piping ISO drawing_SB | FI | 2019-01-31 | 2019-03-29 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P3PGB-144000 | 661 | [Closed cooling water system(For Block 4)_Piping]_Piping ISO drawing_LB | FI | 2018-07-18 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3PGB-147000 | 662 | [Closed cooling water system(For Block 4)_Piping]_Piping ISO drawing_SB | FI | 2019-04-15 | 2019-05-15 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P2QC-145000 | 663 | [Chemical dosing system(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2021-03-26 | 210018-FC STAMPED | FC | 1B | 1 | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3QC-146000 | 664 | [Chemical dosing system(For Block 3)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3QC-147000 | 665 | [Chemical dosing system(For Block 4)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P2QU-145000 | 666 | [Sampling system(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2024-01-03 | MTW-AS-C-LT-24.4759.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3QU-146000 | 667 | [Sampling system(For Block 3)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3QU-147000 | 668 | [Sampling system(For Block 4)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P0GKB-140001 | 669 | [Potable water system_Piping]_Piping ISO drawing_LB | FI | 2018-05-30 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2023-11-17 | MTW-AS-C-LT-23.4620.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P0GKB-141000 | 670 | [Potable water system_Piping]_Piping ISO drawing_SB | FI | 2019-03-29 | 2019-04-30 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2021-07-01 | 210044-FC STAMPED | FC | 1E | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P0GHD-140001 | 671 | [Service water system_Piping]_Piping ISO drawing_LB | FI | 2018-05-30 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2023-11-17 | MTW-AS-C-LT-23.4620.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P0GHD-141000 | 672 | [Service water system_Piping]_Piping ISO drawing_SB | FI | 2019-03-29 | 2019-04-30 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2021-07-01 | 210044-FC STAMPED | FC | 1E | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P2SCA-145000 | 673 | [Compressed air system(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2019-03-29 | 2019-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-09-19 | 190196-FC STAMPED | FC | 1 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3SCA-146000 | 674 | [Compressed air system(For Block 3)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3SCA-147000 | 675 | [Compressed air system(For Block 4)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P2QFB-145000 | 676 | [Instrument air system(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2019-03-29 | 2019-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2021-03-26 | 210018-FC STAMPED | FC | 1C | 1 | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3QFB-146000 | 677 | [Instrument air system(For Block 3)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3QFB-147000 | 678 | [Instrument air system(For Block 4)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P2SCB-145000 | 679 | [Service air system(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2019-03-29 | 2019-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2021-11-23 | 210059-FC STAMP | FC | 1E | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3SCB-146000 | 680 | [Service air system(For Block 3)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3SCB-147000 | 681 | [Service air system(For Block 4)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P2MAV-145000 | 682 | [Clean & Dirty oil system(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2021-06-21 | 210042-FC STAMPED | FC | 1C | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3MAV-146000 | 683 | [Clean & Dirty oil system(For Block 3)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3MAV-147000 | 684 | [Clean & Dirty oil system(For Block 4)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P0QJA-141000 | 685 | [N2 Gas system_Piping]_Piping ISO drawing_SB | FI | 2019-03-29 | 2019-04-30 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2020-03-07 | 200027-FC STAMPED | FC | 1B | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P0EKG-141000 | 686 | [Fuel gas supply system_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2020-03-07 | 200027-FC STAMPED | FC | 1B | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P0EGD-141000 | 687 | [Fuel oil supply system_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2020-03-07 | 200027-FC STAMPED | FC | 1B | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P0MKG-141000 | 688 | [H2 Gas system_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2020-12-07 | 200088-FC STAMPED | FC | 1B | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P0GMA-140001 | 689 | [Waste Water Transfer system_Piping]_Piping ISO drawing_LB | FI | 2018-08-31 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2023-12-08 | MTW-AS-C-LT-23.4681.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P0GMA-141000 | 690 | [Waste Water Transfer system_Piping]_Piping ISO drawing_SB | FI | 2019-03-29 | 2019-04-30 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2021-03-26 | 210018-FC STAMPED | FC | 1D | 1 | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P0QCH-140000 | 691 | [Electro Chlorination_Piping]_Piping ISO drawing | FI | 2019-05-17 | 2019-06-21 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2022-04-16 | 220005-FC STAMP | FC | 1B | 1 | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P0LAA-140000 | 692 | [Aux Boiler Miscellaneous System_Piping]_Piping ISO drawing | FI | 2019-05-24 | 2019-06-30 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2020-03-07 | 200027-FC STAMPED | FC | 1B | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P2LB-142000 | 693 | [Steam Blowing(For Blcok2)_Piping]_Piping ISO drawing_LB | FI | 2019-11-15 |  | 2022-05-23 | 2022-05-23 | MRT-DS-REC-TT-220006 | FC | 1C | 2022-05-23 | 220006-FC STAMP | FC | 1C | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3LB-143000 | 694 | [Steam Blowing(For Blcok3)_Piping]_Piping ISO drawing_LB | FI | 2019-11-15 |  | 2020-04-09 |  | MRT-DS-REC-TT-200035-FC | FC | 1A | 2019-11-11 | 190224-FC STAMPED | FI | 0 | A | MECHANICAL | BOP PIPING
DHI | 배관기술 | 김근유 | MRT-XJ00-P3LB-144000 | 695 | [Steam Blowing(For Blcok4)_Piping]_Piping ISO drawing_LB | FI | 2019-11-15 |  | 2020-04-09 |  | MRT-DS-REC-TT-200035-FC | FC | 1A | 2019-11-11 | 190224-FC STAMPED | FI | 0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P2LBA-142000 | 696 | Pipe Support for Steam and Bypass System (Block 2) | FI | 2019-03-21 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2020-03-09 | 200025-FC STAMPED | FC | 3 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P3LBA-143000 | 697 | Pipe Support for Steam and Bypass System (Block 3) | FI | 2019-04-17 |  | 2024-11-18 | 2024-11-18 | MRT-DS-REC-TT-240034 | AB | Z1 | 2024-11-22 | MTW-AS-C-LT-24.5985.0 | AB | Z1 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P4LBA-144000 | 698 | Pipe Support for Steam and Bypass System (Block 4) | FI | 2019-04-17 |  | 2024-11-18 | 2024-11-18 | MRT-DS-REC-TT-240034 | AB | Z1 | 2024-11-22 | MTW-AS-C-LT-24.5985.0 | AB | Z1 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P2LCM-142000 | 699 | Pipe Support for Steam Drain System (Block 2) | FI | 2019-04-17 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2020-10-20 | 200077-FC STAMPED | FC | 3 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P3LCM-143000 | 700 | Pipe Support for Steam Drain System (Block 3) | FI | 2019-04-17 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P4LCM-144000 | 701 | Pipe Support for Steam Drain System (Block 4) | FI | 2019-04-17 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P2LCA-142000 | 702 | Pipe Support for Condensate System (Block 2) | FI | 2019-04-17 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-12-16 | 190239-FC STAMPED | FC | 2 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P3LCA-143000 | 703 | Pipe Support for Condensate System (Block 3) | FI | 2019-04-17 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P4LCA-144000 | 704 | Pipe Support for Condensate System (Block 4) | FI | 2019-04-17 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P2LAB-142000 | 705 | Pipe Support for Feedwater System (Block 2) | FI | 2019-04-17 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2020-03-09 | 200025-FC STAMPED | FC | 3 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P3LAB-143000 | 706 | Pipe Support for Feedwater System (Block 3) | FI | 2019-04-17 |  | 2024-11-18 | 2024-11-18 | MRT-DS-REC-TT-240034 | AB | Z1 | 2024-11-22 | MTW-AS-C-LT-24.5985.0 | AB | Z1 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P4LAB-144000 | 707 | Pipe Support for Feedwater System (Block 4) | FI | 2019-04-17 |  | 2024-11-18 | 2024-11-18 | MRT-DS-REC-TT-240034 | AB | Z1 | 2024-11-22 | MTW-AS-C-LT-24.5985.0 | AB | Z1 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P2LBG-142000 | 708 | Pipe Support for Aux Steam System (Block 2) | FI | 2019-04-17 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-12-16 | 190239-FC STAMPED | FC | 2 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P3LBG-143000 | 709 | Pipe Support for Aux Steam System (Block 3) | FI | 2019-04-17 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P4LBG-144000 | 710 | Pipe Support for Aux Steam System (Block 4) | FI | 2019-04-17 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P0LBG-141000 | 711 | Pipe Support for AUX Steam System_Common | FI | 2019-07-01 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2023-11-17 | MTW-AS-C-LT-23.4620.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P0GHC-140001 | 712 | Pipe Support for Make-up Water System | FI | 2019-07-01 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2023-11-17 | MTW-AS-C-LT-23.4620.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P2PAB-142000 | 713 | Pipe Support for Cooling Water System (Block 2) | FI | 2019-03-22 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2021-04-27 | 050/T/MRT/REC/IV/2021 | FC | 4 | I | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P3PAB-143000 | 714 | Pipe Support for Cooling Water System (Block 3) | FI | 2019-03-22 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P4PAB-144000 | 715 | Pipe Support for Cooling Water System (Block 4) | FI | 2019-03-22 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P2ACW-142000 | 716 | Pipe Support for Aux Cooling Water System (Block 2) | FI | 2019-04-17 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2020-03-09 | 200025-FC STAMPED | FC | 3 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P3ACW-143000 | 717 | Pipe Support for Aux Cooling Water System (Block 3) | FI | 2019-04-17 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P4ACW-144000 | 718 | Pipe Support for Aux Cooling Water System (Block 4) | FI | 2019-04-17 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P2PGB-142000 | 719 | Pipe Support for Closed Cooling Water System (Block 2) | FI | 2019-04-17 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-12-16 | 190239-FC STAMPED | FC | 2 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P3PGB-143000 | 720 | Pipe Support for Closed Cooling Water System (Block 3) | FI | 2019-04-17 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P4PGB-144000 | 721 | Pipe Support for Closed Cooling Water System (Block 4) | FI | 2019-04-17 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P0GHD-140001 | 722 | Pipe Support for Service water system | FI | 2019-07-01 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2023-11-17 | MTW-AS-C-LT-23.4620.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P0GMA-140001 | 723 | Pipe Support for Waste Water Transfer system | FI | 2019-07-01 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2023-11-17 | MTW-AS-C-LT-23.4620.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P0QCH-140001 | 724 | Pipe Support for Electro Chlorniation System (Common) | FI | 2020-03-03 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2023-11-17 | MTW-AS-C-LT-23.4620.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P2MAM-142000 | 725 | Pipe Support for Miscellinious System (Block 2) | FI | 2019-04-17 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-12-16 | 190239-FC STAMPED | FC | 2 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P3MAM-142000 | 726 | Pipe Support for Miscellinious System (Block 3) | FI | 2019-04-17 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P4MAM-142000 | 727 | Pipe Support for Miscellinious System (Block 4) | FI | 2019-04-17 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P2LB0-140001 | 728 | Pipe Support for Steam blowing (Block 2) | FI | 2020-01-17 |  | 2020-01-20 | 2020-01-22 | MRT-DS-REC-TT-200005-FC | FI | 0 | 2020-01-22 | 200005-FC STAMPED | FI | 0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P3LB0-140001 | 729 | Pipe Support for Steam blowing (Block 3) | FI | 2020-01-21 |  | 2020-01-21 | 2020-01-22 | MRT-DS-REC-TT-200006-FC | FI | 0 | 2020-01-22 | 200006-FC STAMPED | FI | 0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P4LB0-140001 | 730 | Pipe Support for Steam blowing (Block 4) | FI | 2020-01-21 |  | 2020-01-21 | 2020-01-22 | MRT-DS-REC-TT-200006-FC | FI | 0 | 2020-01-22 | 200006-FC STAMPED | FI | 0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P2LBA-141000 | 731 | Small Bore Pipe Support for Steam and Bypass System (Block 2) | FI | 2019-12-06 |  | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220053 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3771.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P3LBA-141000 | 732 | Small Bore Pipe Support for Steam and Bypass System (Block 3) | FI | 2019-12-06 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P4LBA-141100 | 733 | Small Bore Pipe Support for Steam and Bypass System (Block 4) | FI | 2019-12-06 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P2LBA-141100 | 734 | Small Bore Pipe Support for Steam Drain System (Block 2) | FI | 2019-12-06 |  | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220053 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3771.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P3LBA-141100 | 735 | Small Bore Pipe Support for Steam Drain System (Block 3) | FI | 2019-12-06 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P4LBA-141200 | 736 | Small Bore Pipe Support for Steam Drain System (Block 4) | FI | 2019-12-06 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P2LBG-141000 | 737 | Small Bore Pipe Support for Aux Steam System (Block 2) | FI | 2019-12-06 |  | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220053 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3771.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P2LCA-141000 | 738 | Small Bore Pipe Support for Condensate System (Block 2) | FI | 2019-12-06 |  | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220053 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3771.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P3LCE-141000 | 739 | Small Bore Pipe Support for Condensate System (Block 3) | FI | 2019-12-06 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P4LCE-142000 | 740 | Small Bore Pipe Support for Condensate System (Block 4) | FI | 2019-12-06 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P3LAB-141100 | 741 | Small Bore Pipe Support for Feed water System (Block 3) | FI | 2019-12-06 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P0EGD-141000 | 742 | Small Bore Pipe Support for Fuel Oil Supply System (Common) | FI | 2019-12-06 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2023-11-17 | MTW-AS-C-LT-23.4620.0 | AB | Z0 | A | MECHANICAL | BOP PIPING
DHI | 계측제어기술 | 최민석 | MRT-XW01-P0ZEN-161001 | 743 | I&C General Design Criteria | FA | 2017-11-01 | 2018-02-02 | 2018-07-27 | 2018-08-27 | MRT-DS-REC-TT-180218-FC | FC | 5 | 2018-09-03 | 180218-FC STAMPED | FC | 5 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2ZEN-161601 | 744 | Plant Master Control Diagram(For Block 2) | FA | 2018-05-11 | 2018-07-31 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3ZEN-161601 | 745 | Plant Master Control Diagram(For Block 3, 4) | FA | 2018-05-11 | 2018-07-31 | 2024-10-24 | 2024-10-24 | MRT-DS-REC-TT-240021 | AB | Z0 | 2024-12-04 | MTW-AS-C-LT-24.6034.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YU04-P0ZEN-161012 | 746 | Plant Control Block Diagram(For Block 2, 3 & 4) | FA | 2017-11-24 | 2018-03-23 | 2018-07-27 | 2018-08-21 | MRT-DS-REC-TT-180289-FC | FC | 4 | 2018-09-07 | 180289-FC STAMPED | FC | 4 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-MA01-P2ZEN-161011 | 747 | Plant Control System Configuration Diagram(For Block 2) | FA | 2017-12-01 | 2018-03-02 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | 2018-08-13 | 180200-FC STAMPED | FC | 3 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-MA01-P3ZEN-161011 | 748 | Plant Control System Configuration Diagram(For Block 3, 4) | FA | 2017-12-01 | 2018-03-02 | 2024-10-25 | 2024-10-25 | MRT-DS-REC-TT-240022 | AB | Z0 | 2024-12-04 | MTW-AS-C-LT-24.6033.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF01-P2ZEN-161013 | 749 | Plant Protection & Interlock Diagram(For Block 2) | FA | 2017-12-21 | 2018-03-22 | 2018-07-27 | 2018-07-30 | MRT-DS-REC-TT-180226-FC | FC | 3 | 2018-08-03 | 180226-FC STAMPED | FC | 3 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF01-P3ZEN-161013 | 750 | Plant Protection & Interlock Diagram(For Block 3, 4) | FA | 2017-12-21 | 2018-03-22 | 2018-07-27 | 2018-07-30 | MRT-DS-REC-TT-180226-FC | FC | 3 | 2018-08-03 | 180226-FC STAMPED | FC | 3 | A | I&C | BOP I&C
DHI | 계측제어기술 | 고경환 | MRT-YR05-P0ZEN-161016 | 751 | Master & Slave Clock Concept Diagram (For Block 2, 3&4) | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-20 | MRT-DS-REC-TT-180206-FC | FC | 2 | 2018-09-05 | 180206-FC STAMPED | FC | 2 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P0CJD-161401 | 752 | Plant Start-up & Shutdown Sequence Diagram - Symbol & Legend | FA | 2018-05-20 | 2018-09-21 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CJD-161402 | 753 | Plant Start-up & Shutdown Sequence Diagram for Start-up(For Block 2) | FA | 2018-05-20 | 2018-09-21 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CJD-161402 | 754 | Plant Start-up & Shutdown Sequence Diagram for Start-up(For Block 3, 4) | FA | 2018-05-20 | 2018-09-21 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CJD-161403 | 755 | Plant Start-up & Shutdown Sequence Diagram for Shutdown(For Block 2) | FA | 2018-05-20 | 2018-09-21 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CJD-161403 | 756 | Plant Start-up & Shutdown Sequence Diagram for Shutdown(For Block 3, 4) | FA | 2018-05-20 | 2018-09-21 | 2024-10-24 | 2024-10-24 | MRT-DS-REC-TT-240021 | AB | Z0 | 2024-12-04 | MTW-AS-C-LT-24.6034.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-MA02-P2ZEN-161015 | 757 | 3rd Party Data-link Interface Concept Diagram(For Block 2) | FA | 2017-11-15 | 2018-03-16 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | 2018-08-13 | 180200-FC STAMPED | FC | 2 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-MA02-P3ZEN-161015 | 758 | 3rd Party Data-link Interface Concept Diagram(For Block 3, 4) | FA | 2017-11-15 | 2018-03-16 | 2024-10-25 | 2024-10-25 | MRT-DS-REC-TT-240022 | AB | Z0 | 2024-12-04 | MTW-AS-C-LT-24.6033.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P0CBA-161201 | 759 | Control Logic Diagram - Symbol & Legend(For Block 2,3&4) | FA | 2018-01-05 | 2018-06-29 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | 2018-09-15 | 180376-FC STAMPED | FC | 1 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P0CBA-161202 | 760 | Control Logic Diagram - Typical Function(For Block 2,3&4) | FA | 2018-01-05 | 2018-06-29 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | 2019-01-22 | 180376-FC STAMPED | FC | 1 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CBA-161203 | 761 | [HP&IP&LP Steam System(For Block 2)] Control Logic Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | 2018-12-03 | 180582-FC STAMPED | FC | 2 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CBA-161203 | 762 | [HP&IP&LP Steam System(For Block 3, 4)] Control Logic Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CBA-161204 | 763 | [Aux Steam System(For Block 2)] Control Logic Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | 2018-12-03 | 180582-FC STAMPED | FC | 2 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CBA-161204 | 764 | [Aux Steam System(For Block 3, 4)] Control Logic Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CBA-161205 | 765 | [Feedwater system(For Block 2)] Control Logic Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CBA-161205 | 766 | [Feedwater system(For Block 3, 4)] Control Logic Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CBA-161206 | 767 | [Condensate system(For Block 2)] Control Logic Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CBA-161206 | 768 | [Condensate system(For Block 3, 4)] Control Logic Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CBA-161207 | 769 | [Cooling Water System(For Block 2)] Control Logic Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CBA-161207 | 770 | [Cooling Water System(For Block 3, 4)] Control Logic Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CBA-161208 | 771 | [Steam Drain System(For Block 2)] Control Logic Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CBA-161208 | 772 | [Steam Drain System(For Block 3, 4)] Control Logic Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CBA-161209 | 773 | [Closed cooling water system(For Block 2)] Control Logic Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CBA-161209 | 774 | [Closed cooling water system(For Block 3, 4)] Control Logic Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CBA-161210 | 775 | [Condensate Vacuum System(For Block 2)] Control Logic Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CBA-161210 | 776 | [Condensate Vacuum System(For Block 3, 4)] Control Logic Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CBA-161211 | 777 | [Miscellaneous System(For Block 2)] Control Logic Diagram | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CBA-161211 | 778 | [Miscellaneous System(For Block 3, 4)] Control Logic Diagram | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CBA-161212 | 779 | [Interface with GT & ST Control System(For Block 2)] Control Logic Diagram | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CBA-161212 | 780 | [Interface with GT & ST Control System(For Block 3, 4)] Control Logic Diagram | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P0CBA-161221 | 781 | [Make-up Water System] Control Logic Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | 2018-12-03 | 180582-FC STAMPED | FC | 2 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P0CBA-161222 | 782 | [Service water system] Control Logic Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P0CGA-161301 | 783 | Control Loop Diagram - Symbol & Legend(For Block 2,3&4) | FA | 2018-01-05 | 2018-06-29 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | 2018-09-15 | 180376-FC STAMPED | FC | 1 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P0CGA-161302 | 784 | Control Loop Diagram - Typical Function(For Block 2,3&4) | FA | 2018-01-05 | 2018-06-29 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | 2018-09-15 | 180376-FC STAMPED | FC | 1 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CGA-161303 | 785 | [HP&IP&LP Steam System(For Block 2)] Control Loop Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CGA-161303 | 786 | [HP&IP&LP Steam System(For Block 3, 4)] Control Loop Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CGA-161304 | 787 | [Aux Steam System(For Block 2)] Control Loop Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CGA-161304 | 788 | [Aux Steam System(For Block 3, 4)] Control Loop Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CGA-161305 | 789 | [Feedwater system(For Block 2)] Control Loop Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CGA-161305 | 790 | [Feedwater system(For Block 3, 4)] Control Loop Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CGA-161306 | 791 | [Condensate system(For Block 2)] Control Loop Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CGA-161306 | 792 | [Condensate system(For Block 3, 4)] Control Loop Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CGA-161307 | 793 | [Cooling Water System(For Block 2)] Control Loop Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CGA-161307 | 794 | [Cooling Water System(For Block 3, 4)] Control Loop Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CGA-161308 | 795 | [Steam Drain System(For Block 2)] Control Loop Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CGA-161308 | 796 | [Steam Drain System(For Block 3, 4)] Control Loop Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CGA-161309 | 797 | [Closed cooling water system(For Block 2)] Control Loop Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CGA-161309 | 798 | [Closed cooling water system(For Block 3, 4)] Control Loop Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CGA-161310 | 799 | [Condensate Vacuum System(For Block 2)] Control Loop Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CGA-161310 | 800 | [Condensate Vacuum System(For Block 3, 4)] Control Loop Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CGA-161311 | 801 | [Miscellaneous System(For Block 2)] Control Loop Diagram | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CGA-161311 | 802 | [Miscellaneous System(For Block 3, 4)] Control Loop Diagram | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CGA-161312 | 803 | [Interface with GT & ST Control System(For Block 2)] Control Loop Diagram | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CGA-161312 | 804 | [Interface with GT & ST Control System(For Block 3, 4)] Control Loop Diagram | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P0CGA-161321 | 805 | [Make-up Water System] Control Loop Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | 2018-12-03 | 180582-FC STAMPED | FC | 2 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YF00-P0CGA-161322 | 806 | [Service water system] Control Loop Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-CV03-P2ZEN-165201 | 807 | [Control Valves(DHI For Block 2)] Technical Specification & Datasheet for Control Valve - BOP | FA | 2018-03-30 | 2018-06-30 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220052 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3770.0 | AB | Z0 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-CV03-P3ZEN-165201 | 808 | [Control Valves(DHI For Block 3, 4)] Technical Specification & Datasheet for Control Valve - BOP | FA | 2018-03-30 | 2018-06-30 | 2024-11-12 | 2024-11-12 | MRT-DS-REC-TT-240026 | AB | Z0 | 2018-12-17 | 180802-FC STAMPED | FC | 4 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-GT00-P2ZEN-167001 | 809 | TECHNICAL SPECIFICATION FOR GAS TURBINE CONTROL SYSTEM (BLOCK 2 ABB MODIFICATION) | FA | 2020-02-20 | 2020-06-29 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | 2021-06-23 | DEEMED APPROVAL | FC | 1 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-GT00-P3ZEN-167001 | 810 | TECHNICAL SPECIFICATION FOR GAS TURBINE CONTROL SYSTEM (BLOCK 3,4 SIEMENS MODIFICATION) | FA | 2020-04-20 | 2020-08-28 | 2025-02-17 | 2025-02-17 | MRT-DS-REC-TT-250007 | AB | Z1 | 2025-02-13 | MTW-AS-C-LT-25.6199.0 | AB | Z0 | B | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YR00-P0ZEN-163001 | 810 | TECHNICAL SPECIFICATION FOR STG CABLE | FA | 2023-04-14 | 2023-08-11 | 2023-04-11 | 2023-04-11 | MRT-DS-REC-TT-230009 | FA | A | [5 empty] | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162101 | 811 | Typical Elementary Wiring Diagram - Index | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162102 | 812 | Typical Elementary Wiring Diagram for Motor Operated Valve (Internal MCC) | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162103 | 813 | Typical Elementary Wiring Diagram for Pneumatic Shut-off Valve (Double Coil SOV) | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162104 | 814 | Typical Elementary Wiring Diagram for Pneumatic Shut-off Valve (Single Coil SOV) | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162105 | 815 | Typical Elementary Wiring Diagram for Modulating Control Actuator | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162106 | 816 | Typical Elementary Wiring Diagram for Analog Input | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162107 | 817 | Typical Elementary Wiring Diagram for Analog Output | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162108 | 818 | Typical Elementary Wiring Diagram for Binary Input | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162109 | 819 | Typical Elementary Wiring Diagram for Binary Output | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162110 | 820 | Typical Elementary Wiring Diagram for MV SWGR BUS TIE-1 | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162111 | 821 | Typical Elementary Wiring Diagram for MV SWGR BUS TIE-2 | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162112 | 822 | Typical Elementary Wiring Diagram for MV SWGR INCOMER | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162113 | 823 | Typical Elementary Wiring Diagram for MV SWGR MOTOR FEEDER | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162114 | 824 | Typical Elementary Wiring Diagram for MV SWGR NON MOTOR FEEDER | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162115 | 825 | Typical Elementary Wiring Diagram for LV SWGR BUS TIE-1 | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162116 | 826 | Typical Elementary Wiring Diagram for LV SWGR BUS TIE-2 | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162117 | 827 | Typical Elementary Wiring Diagram for LV SWGR INCOMER | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162118 | 828 | Typical Elementary Wiring Diagram for LV SWGR MCC MOTOR FEEDER | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162119 | 829 | Typical Elementary Wiring Diagram for LV SWGR NON MOTOR FEEDER | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162120 | 830 | Typical Elementary Wiring Diagram for MCC INCOMER | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C
DHI | 계측제어기술 | 최민석 | MRT-YL01-P2ZEN-161051 | 831 | DCS IO Database(For Block 2) | FA | 2017-12-01 | 2018-05-01 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | 2018-09-28 | 180574-FC STAMPED | FC | 3 | A | I&C | DCS
DHI | 계측제어기술 | 최민석 | MRT-YL01-P3ZEN-161051 | 832 | DCS IO Database(For Block 3, 4) | FA | 2017-12-14 | 2018-05-01 | 2024-11-14 | 2024-11-14 | MRT-DS-REC-TT-240027 | AB | Z0 | 2024-12-04 | MTW-AS-C-LT-24.6032.0 | AB | Z0 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-YD06-P2ZEN-161014 | 833 | DCS Power Distribution Concept Diagram(For Block 2) | FA | 2017-11-10 | 2018-02-09 | 2018-07-27 | 2018-08-01 | MRT-DS-REC-TT-180103-FC | FC | 1 | 2018-09-05 | 180103-FC STAMPED | FC | 1 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-YD06-P3ZEN-161014 | 834 | DCS Power Distribution Concept Diagram(For Block 3, 4) | FA | 2017-11-10 | 2018-02-09 | 2018-07-27 | 2018-08-01 | MRT-DS-REC-TT-180103-FC | FC | 1 | 2018-09-05 | 180103-FC STAMPED | FC | 1 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-CV03-P0ZEN-163101 | 835 | [DCS(For Block 2,3&4)] Functional Design Specification for Graphic | FA | 2018-02-21 | 2018-05-22 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2018-10-15 | 180484-FC STAMPED | FC | 1 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-CV03-P0ZEN-163102 | 836 | [DCS(For Block 2,3&4)] Functional Design Specification for Hardware | FA | 2018-02-21 | 2018-05-22 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2018-09-29 | 180461-FC STAMPED | FC | 1 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-CV03-P0ZEN-163103 | 837 | [DCS(For Block 2,3&4)] Functional Design Specification for Software | FA | 2018-02-21 | 2018-05-22 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2018-09-29 | 180461-FC STAMPED | FC | 1 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-YE03-P2ZEN-163104 | 838 | [DCS(For Block 2)] Grounding Concept & Detail Drawing | FA | 2018-02-21 | 2018-05-22 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2020-05-15 | 085/T/MRT/REC/V/2020 | FC | 2 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-YE03-P3ZEN-163104 | 839 | [DCS(For Block 3, 4)] Grounding Concept & Detail Drawing | FA | 2018-03-23 | 2018-06-21 | 2024-11-18 | 2024-11-18 | MRT-DS-REC-TT-240035 | AB | Z1 | 2024-12-03 | MTW-AS-C-LT-24.6024.0 | AB | Z1 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-MA02-P2ZEN-163105 | 840 | [DCS(For Block 2)] LAN Configuration Diagram | FA | 2018-02-21 | 2018-05-22 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2020-05-15 | 085/T/MRT/REC/V/2020 | FC | 2 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-MA02-P3ZEN-163105 | 841 | [DCS(For Block 3, 4)] LAN Configuration Diagram | FA | 2018-03-23 | 2018-06-21 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2024-10-15 | MTW-AS-C-LT-24.5835.0 | AB | Z0 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-YD06-P2ZEN-163106 | 842 | [DCS(For Block 2)] Equipment Power Distribution Diagram | FA | 2018-02-28 | 2018-05-29 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2020-05-15 | 085/T/MRT/REC/V/2020 | FC | 2 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-YD06-P3ZEN-163106 | 843 | [DCS(For Block 3, 4)] Equipment Power Distribution Diagram | FA | 2018-03-30 | 2018-06-28 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5824.0 | AB | Z0 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-CV03-P0ZEN-163107 | 844 | [DCS(For Block 2,3&4)] Specification & Drawing for CCR Emergency Push Button | FA | 2018-03-04 | 2018-06-02 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2020-05-15 | 085/T/MRT/REC/V/2020 | FC | 2 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-CV03-P0ZEN-163108 | 845 | [DCS(For Block 2,3&4)] Technical Specification for Time Synchronization | FA | 2018-03-04 | 2018-06-02 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2020-05-15 | 085/T/MRT/REC/V/2020 | FC | 2 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-YD07-P2ZEN-163109 | 846 | [DCS(For Block 2)] IO & Module Allocation | FA | 2018-04-12 | 2018-07-11 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2020-05-15 | 085/T/MRT/REC/V/2020 | FC | 2 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-YD07-P3ZEN-163109 | 847 | [DCS(For Block 3, 4)] IO & Module Allocation | FA | 2018-05-12 | 2018-08-10 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2024-10-15 | MTW-AS-C-LT-24.5835.0 | AB | Z0 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-YR05-P2ZEN-163110 | 848 | [DCS(For Block 2)] Outline & Detail Drawing for Console, Computer, Printer Desk | FA | 2018-04-12 | 2018-07-11 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2020-12-15 | 142/T/MRT/REC/XII/2020 | FC | 3 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-YR05-P3ZEN-163110 | 849 | [DCS(For Block 3&4)] Outline & Detail Drawing for Console, Computer, Printer Desk | FA | 2018-04-12 | 2018-07-11 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2024-10-15 | MTW-AS-C-LT-24.5835.0 | AB | Z0 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-YR05-P2ZEN-163111 | 850 | [DCS(For Block 2)] Outline & Detail Drawing for Network Cabinet | FA | 2018-04-12 | 2018-07-11 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2020-05-15 | 085/T/MRT/REC/V/2020 | FC | 2 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-YR05-P3ZEN-163111 | 851 | [DCS(For Block 3&4)] Outline & Detail Drawing for Network Cabinet | FA | 2018-04-12 | 2018-07-11 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2024-10-15 | MTW-AS-C-LT-24.5835.0 | AB | Z0 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-YR05-P2ZEN-163112 | 852 | [DCS(For Block 2)] Outline & Detail Drawing for Marshalling and Relay Cabinet | FA | 2018-04-12 | 2018-07-11 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2020-05-15 | 085/T/MRT/REC/V/2020 | FC | 2 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-YR05-P3ZEN-163112 | 853 | [DCS(For Block 3&4)] Outline & Detail Drawing for Marshalling and Relay Cabinet | FA | 2018-04-12 | 2018-07-11 | 2023-05-09 | 2023-05-09 | MRT-DS-REC-TT-230010 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5833.0 | AB | Z0 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-YR05-P2ZEN-163113 | 854 | [DCS(For Block 2)] Outline & Detail Drawing for Power Distribution Cabinet | FA | 2018-04-12 | 2018-07-11 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2020-12-15 | 142/T/MRT/REC/XII/2020 | FC | 3 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-YR05-P3ZEN-163113 | 855 | [DCS(For Block 3&4)] Outline & Detail Drawing for Power Distribution Cabinet | FA | 2018-04-12 | 2018-07-11 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5824.0 | AB | Z0 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-YR05-P2ZEN-163114 | 856 | [DCS(For Block 2)] Outline & Detail Drawing for System Cabinet | FA | 2018-04-12 | 2018-07-11 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2020-05-15 | 085/T/MRT/REC/V/2020 | FC | 2 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-YR05-P3ZEN-163114 | 857 | [DCS(For Block 3&4)] Outline & Detail Drawing for System Cabinet | FA | 2018-04-12 | 2018-07-11 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2024-10-15 | MTW-AS-C-LT-24.5835.0MTW-AS-C-LT-24.5835.0 | AB | Z0 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-YR05-P0ZEN-163115 | 858 | [DCS(For Block 2, 3&4)] HMI Graphic Drawing | FA | 2018-06-08 | 2018-09-06 | 2023-05-09 | 2023-05-09 | MRT-DS-REC-TT-230010 | AB | Z0 | 2018-10-06 | 180535-FC STAMPED | FC | 0 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-YR05-P2ZEN-163116 | 859 | [DCS(For Block 2)] Internal Cable Connection Diagram | FI | 2018-06-21 | 2018-09-19 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2018-09-28 | 180553-FC STAMPED | FC | 0 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-YV02-P3ZEN-163116 | 860 | [DCS(For Block 3, 4)] Internal Cable Connection Diagram | FI | 2018-07-21 | 2018-10-19 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2024-10-15 | MTW-AS-C-LT-24.5835.0 | AB | Z0 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-CV03-P3ZEN-163118 | 861 | [DCS(For Block 3, 4)] Specification & Drawings for Large Screen Display | FA | 2018-04-03 | 2018-07-02 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2024-10-15 | MTW-AS-C-LT-24.5835.0 | AB | Z0 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-YL15-P3ZEN-163117 | 862 | [DCS(For Block 3, 4)] Cable list | FI | 2018-07-21 | 2018-10-19 | 2018-09-10 | 2018-11-21 | MRT-DS-REC-TT-180625-FC | FC | 0 | 2018-11-26 | 180625-FC STAMPED | FC | 0 | A | I&C | DCS
DHI | 계측제어기술 | 고경환 | MRT-YR05-P2ZEN-163117 | 863 | [DCS(For Block 2)] Cable List | FI | 2018-06-21 | 2018-09-19 | 2018-07-27 | 2018-09-24 | MRT-DS-REC-TT-180553-FC | FC | 0 | 2018-09-28 | 180553-FC STAMPED | FC | 0 | A | I&C | DCS
DHI | 계측제어기술 | 신동인 | MRT-YL00-P2ZEN-165101 | 864 | [Field Instrument(DHI For Block 2)] Field Instrument List for BOP | FA | 2018-03-30 | 2018-06-30 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220049 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3768.0 | AB | Z0 | A | I&C | FIELD INSTRUMENT
DHI | 계측제어기술 | 신동인 | MRT-YL00-P3ZEN-165101 | 865 | [Field Instrument(DHI For Block 3, 4)] Field Instrument List for BOP | FA | 2018-03-30 | 2018-06-30 | 2024-11-26 | 2024-11-26 | MRT-DS-REC-TT-240041 | AB | Z1 | 2024-12-03 | MTW-AS-C-LT-24.6027.0 | AB | Z1 | A | I&C | FIELD INSTRUMENT
DHI | 계측제어기술 | 신동인 | MRT-CV03-P2ZEN-165102 | 866 | [Field Instrument(DHI For Block 2)] Technical Specification & Datasheet for Process Transmitter - BOP | FA | 2018-03-30 | 2018-06-30 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220049 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3768.0 | AB | Z0 | A | I&C | FIELD INSTRUMENT
DHI | 계측제어기술 | 신동인 | MRT-CV03-P3ZEN-165102 | 867 | [Field Instrument(DHI For Block 3, 4)] Technical Specification & Datasheet for Process Transmitter - BOP | FA | 2018-03-30 | 2018-06-30 | 2024-11-26 | 2024-11-26 | MRT-DS-REC-TT-240041 | AB | Z1 | 2024-12-03 | MTW-AS-C-LT-24.6027.0 | AB | Z1 | A | I&C | FIELD INSTRUMENT
DHI | 계측제어기술 | 신동인 | MRT-CV03-P2ZEN-165103 | 868 | [Field Instrument(DHI For Block 2)] Technical Specification & Datasheet for Local Instrument - BOP | FA | 2018-03-30 | 2018-06-30 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220049 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3768.0 | AB | Z0 | A | I&C | FIELD INSTRUMENT
DHI | 계측제어기술 | 신동인 | MRT-CV03-P3ZEN-165103 | 869 | [Field Instrument(DHI For Block 3, 4)] Technical Specification & Datasheet for Local Instrument - BOP | FA | 2018-03-30 | 2018-06-30 | 2024-11-26 | 2024-11-26 | MRT-DS-REC-TT-240041 | AB | Z1 | 2024-12-03 | MTW-AS-C-LT-24.6027.0 | AB | Z1 | A | I&C | FIELD INSTRUMENT
DHI | 계측제어기술 | 신동인 | MRT-CV03-P2ZEN-165104 | 870 | [Field Instrument(DHI For Block 2)] Technical Specification & Datasheet for Flow Element - BOP | FA | 2018-03-30 | 2018-06-30 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220049 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3768.0 | AB | Z0 | A | I&C | FIELD INSTRUMENT
DHI | 계측제어기술 | 신동인 | MRT-CV03-P3ZEN-165104 | 871 | [Field Instrument(DHI For Block 3, 4)] Technical Specification & Datasheet for Flow Element - BOP | FA | 2018-03-30 | 2018-06-30 | 2024-01-08 | 2024-01-08 | MRT-DS-REC-TT-240002 | AB | Z0 | 2024-02-07 | MTW-AS-C-LT-24.4898.0 | AB | Z0 | A | I&C | FIELD INSTRUMENT
DHI | 건축기술 | 정윤철 | MRT-CA06-P0UCA-180101 | 872 | [Central control building]_Calculation Sheet | FA | 2017-10-18 | 2017-12-31 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170157-FC | FC | 2 | 2018-10-23 | 170757-FC STAMPED | FC | 2 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-XB02-P0UCA-180102 | 873 | [Central control building]_Pile Arrangement Plan | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA01-P0UCA-180103 | 874 | [Central control building]_Foundation & Column Arrangement Plan | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA02-P0UCA-180104 | 875 | [Central control building]_Foundation Re-Bar Schedule | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UCA-180105 | 876 | [Central control building]_Interior Finish Schedule | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UCA-180106 | 877 | [Central control building]_Door & Window Schedule | FA | 2017-12-01 | 2018-03-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UCA-180107 | 878 | [Central control building]_Ground & First Floor Plan | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UCA-180108 | 879 | [Central control building]_Second & Roof Floor Plan | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UCA-180112 | 880 | [Central control building]_Main Section | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UCA-180113 | 881 | [Central control building]_Side Elevation | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UCA-180114 | 882 | [Central control building]_Enlarged Staircase Plan & Section | FA | 2017-12-01 | 2018-03-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UCA-180115 | 883 | [Central control building]_Enlarged Toilet Plan & Elevation | FA | 2017-12-01 | 2018-03-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UCA-180116 | 884 | [Central control building]_Enlarged Locker, Kitchen and Ablution Room Plan & Elevation | FA | 2017-12-01 | 2018-03-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UCA-180117 | 885 | [Central control building]_Wall Section | FA | 2017-12-01 | 2018-03-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UCA-180119 | 886 | [Central control building]_Ceiling Plan | FA | 2018-04-01 | 2018-09-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UCA-180120 | 887 | [Central control building]_Architectural Misc. Detail | FA | 2018-04-01 | 2018-09-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA01-P0UCA-180122 | 888 | [Central control building]_Ground & First Floor Framing Plan | FA | 2017-12-27 | 2018-03-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA01-P0UCA-180123 | 889 | [Central control building]_Second & Roof Floor Framing Plan | FA | 2017-12-27 | 2018-03-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA01-P0UCA-180127 | 890 | [Central control building]_Line Framing Elevation | FA | 2017-12-27 | 2018-03-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA01-P0UCA-180128 | 891 | [Central control building]_Row Framing Elevation | FA | 2017-12-27 | 2018-03-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA01-P0UCA-180129 | 892 | [Central control building]_Staircase Framing Plan & Elevation | FA | 2017-12-27 | 2018-03-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UCA-180132 | 893 | [Central control building]_Panel Support Frame Layout & Detail | FA | 2018-02-01 | 2018-07-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA01-P0UCA-180133 | 894 | [Central control building]_Structual Misc. Detail | FA | 2018-02-01 | 2018-07-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA02-P0UCA-180134 | 895 | [Central control building]_Column Re-Bar Schedule | FA | 2017-12-27 | 2018-03-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA02-P0UCA-180135 | 896 | [Central control building]_Beam & Girder Re-Bar Schedule | FA | 2017-12-27 | 2018-03-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA02-P0UCA-180136 | 897 | [Central control building]_Slab & Misc. Re-Bar Schedule | FA | 2017-12-27 | 2018-03-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA05-P0UCA-180161 | 898 | [Central control building_Plumbing]_Plumbing Equipment Schedule | FA | 2017-12-01 | 2018-03-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA05-P0UCA-180162 | 899 | [Central control building_Plumbing]_Plumbing Schematic Diagram | FA | 2017-12-01 | 2018-03-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA05-P0UCA-180163 | 900 | [Central control building_Plumbing]_Plumbing Plan | FA | 2017-12-01 | 2018-03-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA05-P0UCA-180164 | 901 | [Central control building_Plumbing]_Enlarged Plumbing Plan | FA | 2017-12-01 | 2018-03-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA06-P0UMA-180001 | 902 | [Steam Turbine Building]_Calculation of Piling & Foundation | FA | 2017-10-18 | 2017-12-31 | 2018-07-27 | 2018-08-21 | MRT-DS-REC-TT-180307-FC | FC | 3 | 2018-09-10 | 180307-FC STAMPED | FC | 3 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA06-P0UMA-180002 | 903 | [Steam Turbine Building]_Calculation of Super Structure | FA | 2017-11-02 | 2018-01-16 | 2018-07-27 | 2018-11-01 | MRT-DS-REC-TT-180255-FC | FC | 4 | 2018-11-09 | 180255-FC STAMPED | FC | 4 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA06-P0UMA-180003 | 904 | [Steam Turbine Building]_Loading Data for Super Structure | FA | 2017-10-18 | 2017-12-31 | 2018-07-27 | 2018-11-01 | MRT-DS-REC-TT-180255-FC | FC | 3 | 2018-11-09 | 180255-FC STAMPED | FC | 3 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-XB02-P0UMA-180004 | 905 | [Steam Turbine Building]_Pile Arrangement Plan | FI | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA01-P0UMA-180005 | 906 | [Steam Turbine Building]_Foundation Arrangement Plan | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA01-P0UMA-180006 | 907 | [Steam Turbine Building]_Foundation Longitudinal Section | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA01-P0UMA-180007 | 908 | [Steam Turbine Building]_Foundation Rebar Detail | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180008 | 909 | [Steam Turbine Building]_Interior Finish Schedule | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180009 | 910 | [Steam Turbine Building]_Door & Window Schedule | FA | 2017-11-15 | 2018-01-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180010 | 911 | [Steam Turbine Building]_Ground & Mezzanine Floor Plan | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180011 | 912 | [Steam Turbine Building]_Operating & Roof Floor Plan | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180013 | 913 | [Steam Turbine Building]_Main Section | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180014 | 914 | [Steam Turbine Building]_Side Elevation | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180015 | 915 | [Steam Turbine Building]_Ground Floor Plan (Enlarged) | FA | 2017-11-15 | 2018-01-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180016 | 916 | [Steam Turbine Building]_Mezzanine Floor Plan (Enlarged) | FA | 2017-11-15 | 2018-01-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180017 | 917 | [Steam Turbine Building]_Operating Floor Plan (Enlarged) | FA | 2017-11-15 | 2018-01-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180019 | 918 | [Steam Turbine Building]_Roof Floor Plan (Enlarged) | FA | 2017-11-15 | 2018-01-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180021 | 919 | [Steam Turbine Building]_Wall Section | FA | 2017-11-15 | 2018-01-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180022 | 920 | [Steam Turbine Building]_Stair Plan & Section | FA | 2017-11-15 | 2018-01-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180023 | 921 | [Steam Turbine Building]_Misc. Platform Plan & Section | FA | 2018-03-01 | 2018-07-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180024 | 922 | [Steam Turbine Building]_Architectural Misc. Detail | FA | 2018-03-01 | 2018-07-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180025 | 923 | [Steam Turbine Building]_Column Arrangement Plan | FA | 2017-11-02 | 2018-01-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180026 | 924 | [Steam Turbine Building]_Column Schedule | FA | 2017-11-02 | 2018-01-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA01-P0UMA-180027 | 925 | [Steam Turbine Building]_Ground Floor Framing Plan (Enlarged) | FA | 2017-11-02 | 2018-01-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180028 | 926 | [Steam Turbine Building]_Mezzanine Floor Framing Plan (Enlarged) | FA | 2017-11-02 | 2018-01-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180029 | 927 | [Steam Turbine Building]_Operating Floor Framing Plan (Enlarged) | FA | 2017-11-02 | 2018-01-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180030 | 928 | [Steam Turbine Building]_Lower Roof Floor Framing Plan (Enlarged) | FA | 2017-11-02 | 2018-01-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180031 | 929 | [Steam Turbine Building]_Crane Floor Framing Plan (Enlarged) | FA | 2017-11-02 | 2018-01-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180032 | 930 | [Steam Turbine Building]_Roof Floor Framing Plan (Enlarged) | FA | 2017-11-02 | 2018-01-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180033 | 931 | [Steam Turbine Building]_Line Framing Elevation (Enlarged) | FA | 2017-11-02 | 2018-01-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180034 | 932 | [Steam Turbine Building]_Row Framing Elevation (Enlarged) | FA | 2017-11-02 | 2018-01-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180035 | 933 | [Steam Turbine Building]_Girt Arrangement Plan | FA | 2017-12-01 | 2018-02-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180036 | 934 | [Steam Turbine Building]_Girt Line Elevation (Enlarged) | FA | 2017-12-01 | 2018-02-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180037 | 935 | [Steam Turbine Building]_Girt Row Elevation (Enlarged) | FA | 2017-12-01 | 2018-02-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180039 | 936 | [Steam Turbine Building]_Misc. Platform Framing Plan & Elevation | FA | 2017-12-01 | 2018-02-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180040 | 937 | [Steam Turbine Building]_Stair Framing Plan & Elevation | FA | 2017-12-01 | 2018-02-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180042 | 938 | [Steam Turbine Building]_Crane Girder Detail | FA | 2017-11-02 | 2018-01-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180043 | 939 | [Steam Turbine Building]_Connection Detail | FA | 2017-11-02 | 2018-01-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA01-P0UMA-180044 | 940 | [Steam Turbine Building]_Equipment Foundation & Slab Outline Plan | FA | 2018-02-01 | 2018-05-18 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA02-P0UMA-180045 | 941 | [Steam Turbine Building]_Equipment Foundation Rebar Detail | FA | 2018-02-01 | 2018-05-18 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180046 | 942 | [Steam Turbine Building]_Structural Misc. Detail | FA | 2018-02-01 | 2018-05-18 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180047 | 943 | [Steam Turbine Building]_Floor Opening Schedule | FA | 2018-02-01 | 2018-07-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA05-P0UMA-180061 | 944 | [Steam Turbine Building_Plumbing]_Equipment drain Schematic Diagram | FA | 2017-12-15 | 2018-05-18 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 건축기술 | 정윤철 | MRT-CA05-P0UMA-180062 | 945 | [Steam Turbine Building_Plumbing]_Equipment drain Plan | FA | 2017-12-15 | 2018-05-18 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING
DHI | 토목기술 | 박찬웅 | MRT-CC07-P2UMA-170801 | 946 | [Air Receiver Tank Foundation(For Block 2)]_Calculation | FA | 2018-01-05 | 2018-08-26 | 2018-07-27 | 2018-08-13 | MRT-DS-REC-TT-180367-FC | FC | 2 | 2018-08-23 | 180367-FC STAMPED | FC | 2 | A | CIVIL | AIR TANK FDN
DHI | 토목기술 | 박찬웅 | MRT-CC07-P3UMA-170801 | 947 | [Air Receiver Tank Foundation(For Block 3, 4)]_Calculation | FA | 2018-01-05 | 2018-09-26 | 2018-07-27 | 2018-08-13 | MRT-DS-REC-TT-180367-FC | FC | 2 | 2018-08-23 | 180367-FC STAMPED | FC | 2 | A | CIVIL | AIR TANK FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170803 | 948 | [Air Receiver Tank Foundation(For Block 2)]_Plan & Section drawing | FA | 2018-01-05 | 2018-08-26 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-08-23 | 180367-FC STAMPED | FC | 2 | A | CIVIL | AIR TANK FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170803 | 949 | [Air Receiver Tank Foundation(For Block 3, 4)]_Plan & Section drawing | FA | 2018-01-05 | 2018-09-26 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2018-08-23 | 180367-FC STAMPED | FC | 2 | A | CIVIL | AIR TANK FDN
DHI | 토목기술 | 박찬웅 | MRT-VK02-P2UMA-170806 | 950 | [Air Receiver Tank Foundation(For Block 2)]_Re-bar Arrangement | FA | 2018-01-05 | 2018-08-26 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-08-23 | 180367-FC STAMPED | FC | 2 | A | CIVIL | AIR TANK FDN
DHI | 토목기술 | 박찬웅 | MRT-VK02-P3UMA-170806 | 951 | [Air Receiver Tank Foundation(For Block 3, 4)]_Re-bar Arrangement | FA | 2018-01-05 | 2018-09-26 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2018-08-23 | 180367-FC STAMPED | FC | 2 | A | CIVIL | AIR TANK FDN
DHI | 토목기술 | 박찬웅 | MRT-CC07-P2UMA-170501 | 952 | [BFP Foundation(For Block 2)]_Calculation | FA | 2017-11-02 | 2018-01-16 | 2018-07-27 | 2018-08-27 | MRT-DS-REC-TT-180364-FC | FC | 3 | 2018-09-07 | 180364-FC STAMPED | FC | 3 | A | CIVIL | BFP FDN
DHI | 토목기술 | 박찬웅 | MRT-CC07-P3UMA-170501 | 953 | [BFP Foundation(For Block 3, 4)]_Calculation | FA | 2017-11-02 | 2018-02-11 | 2018-07-27 | 2018-08-27 | MRT-DS-REC-TT-180364-FC | FC | 3 | 2018-09-07 | 180364-FC STAMPED | FC | 3 | A | CIVIL | BFP FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P0UMA-170502 | 954 | [BFP Foundation(For Block 2, 3&4)] Foundation Layout | FA | 2017-11-02 | 2018-01-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-10-15 | 180720-FC STAMPED | FC | 4 | A | CIVIL | BFP FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170503 | 955 | [BFP Foundation(For Block 2)]_Pile Arrangement Drawing | FA | 2017-11-02 | 2018-01-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-08-03 | 180219-FC STAMPED | FC | 2 | A | CIVIL | BFP FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170503 | 956 | [BFP Foundation(For Block 3, 4)]_Pile Arrangement Drawing | FA | 2017-11-02 | 2018-02-11 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2018-08-03 | 180219-FC STAMPED | FC | 2 | A | CIVIL | BFP FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170507 | 957 | [BFP Foundation(For Block 2)]_Plan drawing | FA | 2017-11-02 | 2018-08-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2020-04-06 | 200016-FC STAMPED | FC | 5 | A | CIVIL | BFP FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170507 | 958 | [BFP Foundation(For Block 3, 4)]_Plan drawing | FA | 2017-11-02 | 2018-09-20 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2020-04-06 | 200016-FC STAMPED | FC | 5 | A | CIVIL | BFP FDN
DHI | 토목기술 | 박찬웅 | MRT-VK02-P2UMA-170510 | 959 | [BFP Foundation(For Block 2)]_Re-bar Arrangement | FA | 2017-11-02 | 2018-08-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2020-04-06 | 200016-FC STAMPED | FC | 5 | A | CIVIL | BFP FDN
DHI | 토목기술 | 박찬웅 | MRT-VK02-P3UMA-170510 | 960 | [BFP Foundation(For Block 3, 4)]_Re-bar Arrangement | FA | 2017-11-02 | 2018-09-20 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2020-04-06 | 200016-FC STAMPED | FC | 5 | A | CIVIL | BFP FDN
DHI | 토목기술 | 박찬웅 | MRT-CC07-P2UMA-170601 | 961 | [CEP PIT Foundation(For Block 2)]_Calculation | FA | 2017-11-12 | 2018-01-25 | 2018-07-27 | 2018-08-15 | MRT-DS-REC-TT-180221-FC | FC | 2 | 2018-08-31 | 180221-FC STAMPED | FC | 2 | A | CIVIL | CEP FDN
DHI | 토목기술 | 박찬웅 | MRT-CC07-P3UMA-170601 | 962 | [CEP PIT Foundation(For Block 3, 4)]_Calculation | FA | 2017-11-12 | 2018-02-22 | 2018-07-27 | 2018-08-15 | MRT-DS-REC-TT-180221-FC | FC | 2 | 2018-08-31 | 180221-FC STAMPED | FC | 2 | A | CIVIL | CEP FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P0UMA-170602 | 963 | [CEP PIT FOUNDATION]_FOUNDATION LAYOUT | FA | 2018-02-12 | 2018-03-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-10-15 | 180476-FC STAMPED | FC | 2 | A | CIVIL | CEP FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170603 | 964 | [CEP PIT Foundation(For Block 2)]_Pile Arrangement Drawing | FA | 2017-11-12 | 2018-01-25 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-08-31 | 180221-FC STAMPED | FC | 2 | A | CIVIL | CEP FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170603 | 965 | [CEP PIT Foundation(For Block 3, 4)]_Pile Arrangement Drawing | FA | 2017-11-12 | 2018-02-22 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2018-08-31 | 180221-FC STAMPED | FC | 2 | A | CIVIL | CEP FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170607 | 966 | [CEP PIT Foundation(For Block 2)]_Plan drawing | FA | 2017-11-12 | 2018-03-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-04-22 | 231/T/MRT/REC/IV/2019 | FC | 5 | A | CIVIL | CEP FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170607 | 967 | [CEP PIT Foundation(For Block 3, 4)]_Plan drawing | FA | 2017-11-12 | 2018-03-06 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-04-22 | 231/T/MRT/REC/IV/2019 | FC | 5 | A | CIVIL | CEP FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170608 | 968 | [CEP PIT Foundation(For Block 2)]_Sectional drawing | FA | 2017-11-12 | 2018-03-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-04-22 | 231/T/MRT/REC/IV/2019 | FC | 5 | A | CIVIL | CEP FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170608 | 969 | [CEP PIT Foundation(For Block 3, 4)]_Sectional drawing | FA | 2017-11-12 | 2018-03-06 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-04-22 | 231/T/MRT/REC/IV/2019 | FC | 5 | A | CIVIL | CEP FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170609 | 970 | [CEP PIT Foundation(For Block 2)]_Detail drawing | FA | 2018-01-12 | 2018-03-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-08-12 | 190150-FC STAMPED | FC | 5 | A | CIVIL | CEP FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170609 | 971 | [CEP PIT Foundation(For Block 3, 4)]_Detail drawing | FA | 2018-01-12 | 2018-03-06 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2018-10-15 | 180701-FC STAMPED | FC | 4 | A | CIVIL | CEP FDN
DHI | 토목기술 | 박찬웅 | MRT-VK02-P2UMA-170610 | 972 | [CEP PIT Foundation(For Block 2)]_Re-bar Arrangement | FA | 2017-11-12 | 2018-03-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-10-15 | 180701-FC STAMPED | FC | 3 | A | CIVIL | CEP FDN
DHI | 토목기술 | 박찬웅 | MRT-VK02-P3UMA-170610 | 973 | [CEP PIT Foundation(For Block 3, 4)]_Re-bar Arrangement | FA | 2017-11-12 | 2018-03-06 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2018-10-15 | 180701-FC STAMPED | FC | 3 | A | CIVIL | CEP FDN
DHI | 토목기술 | 박찬웅 | MRT-CC07-P2UMA-170701 | 974 | [CW PIT Foundation(For Block 2)]_Calculation | FA | 2017-11-12 | 2018-01-25 | 2018-07-27 | 2018-09-14 | MRT-DS-REC-TT-180213-FC | FC | 2 | 2018-09-18 | 180213-FC STAMPED | FC | 2 | A | CIVIL | CW PIT FDN
DHI | 토목기술 | 박찬웅 | MRT-CC07-P3UMA-170701 | 975 | [CW PIT Foundation(For Block 3, 4)]_Calculation | FA | 2017-11-12 | 2018-02-22 | 2018-07-27 | 2018-09-14 | MRT-DS-REC-TT-180213-FC | FC | 2 | 2018-09-18 | 180213-FC STAMPED | FC | 2 | A | CIVIL | CW PIT FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P0UMA-170702 | 976 | [CW PIT Foundation]_Foundation Layout | FA | 2018-02-12 | 2018-03-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-09-28 | 180558-FC STAMPED | FC | 2 | A | CIVIL | CW PIT FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170703 | 977 | [CW PIT Foundation(For Block 2)]_Pile Arrangement Drawing | FA | 2017-11-12 | 2018-01-25 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-09-18 | 180213-FC STAMPED | FC | 2 | A | CIVIL | CW PIT FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170703 | 978 | [CW PIT Foundation(For Block 3, 4)]_Pile Arrangement Drawing | FA | 2017-11-12 | 2018-02-22 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2018-09-18 | 180213-FC STAMPED | FC | 2 | A | CIVIL | CW PIT FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170707 | 979 | [CW PIT Foundation(For Block 2)]_Plan drawing | FA | 2017-11-12 | 2018-03-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-04-23 | 190109-FC STAMPED | FC | 5 | A | CIVIL | CW PIT FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170707 | 980 | [CW PIT Foundation(For Block 3, 4)]_Plan drawing | FA | 2017-11-12 | 2018-03-06 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-04-23 | 190109-FC STAMPED | FC | 6 | A | CIVIL | CW PIT FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170708 | 981 | [CW PIT Foundation(For Block 2)]_Sectional drawing | FA | 2017-11-12 | 2018-03-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-04-23 | 190109-FC STAMPED | FC | 5 | A | CIVIL | CW PIT FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170708 | 982 | [CW PIT Foundation(For Block 3, 4)]_Sectional drawing | FA | 2017-11-12 | 2018-03-06 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-04-23 | 190109-FC STAMPED | FC | 6 | A | CIVIL | CW PIT FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170709 | 983 | [CW PIT Foundation(For Block 2)]_Detail drawing | FA | 2018-01-12 | 2018-03-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-04-23 | 190109-FC STAMPED | FC | 6 | A | CIVIL | CW PIT FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170709 | 984 | [CW PIT Foundation(For Block 3, 4)]_Detail drawing | FA | 2018-01-12 | 2018-03-06 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-04-23 | 190109-FC STAMPED | FC | 6 | A | CIVIL | CW PIT FDN
DHI | 토목기술 | 박찬웅 | MRT-VK02-P2UMA-170710 | 985 | [CW PIT Foundation(For Block 2)]_Re-bar Arrangement | FA | 2017-11-12 | 2018-03-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-09-28 | 180558-FC STAMPED | FC | 2 | A | CIVIL | CW PIT FDN
DHI | 토목기술 | 박찬웅 | MRT-VK02-P3UMA-170710 | 986 | [CW PIT Foundation(For Block 3, 4)]_Re-bar Arrangement | FA | 2017-11-12 | 2018-03-06 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-03-18 | 190064-FC STAMPED | FC | 4 | A | CIVIL | CW PIT FDN
DHI | 토목기술 | 박찬웅 | MRT-CC07-P2UHA-170001 | 987 | [HRSG Foundation(For Block 2)]_Pile calculation | FA | 2017-10-20 | 2017-12-30 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180202-FC | FC | 3 | 2018-09-05 | 180202-FC STAMPED | FC | 3 | A | CIVIL | HRSG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC07-P3UHA-170001 | 988 | [HRSG Foundation(For Block 3, 4)]_Pile calculation | FA | 2017-10-20 | 2018-01-30 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180202-FC | FC | 3 | 2018-09-05 | 180202-FC STAMPED | FC | 3 | A | CIVIL | HRSG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P0UHA-170002 | 989 | [HRSG Foundation]_Layout | FA | 2017-10-20 | 2017-12-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-09-05 | 180202-FC STAMPED | FC | 4 | A | CIVIL | HRSG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UHA-170003 | 990 | [HRSG Foundation(For Block 2)]_Pile Arrangement Drawing | FA | 2017-10-20 | 2017-12-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-09-05 | 180202-FC STAMPED | FC | 4 | A | CIVIL | HRSG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UHA-170003 | 991 | [HRSG Foundation(For Block 3, 4)]_Pile Arrangement Drawing | FA | 2017-10-20 | 2018-01-30 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2018-09-05 | 180202-FC STAMPED | FC | 4 | A | CIVIL | HRSG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UHA-170004 | 992 | [HRSG Foundation(For Block 2)]_Pile Schedule | FA | 2017-10-20 | 2017-12-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-09-05 | 180202-FC STAMPED | FC | 4 | A | CIVIL | HRSG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UHA-170004 | 993 | [HRSG Foundation(For Block 3, 4)]_Pile Schedule | FA | 2017-10-20 | 2018-01-30 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2018-09-05 | 180202-FC STAMPED | FC | 4 | A | CIVIL | HRSG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC07-P2UHA-170005 | 994 | [HRSG Foundation(For Block 2)]_Calculation | FA | 2017-11-05 | 2018-02-16 | 2018-07-27 | 2018-09-04 | MRT-DS-REC-TT-180333-FC | FC | 3 | 2018-09-13 | 180333-FC STAMPED | FC | 3 | A | CIVIL | HRSG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC07-P3UHA-170005 | 995 | [HRSG Foundation(For Block 3, 4)]_Calculation | FA | 2017-11-05 | 2018-03-16 | 2018-07-27 | 2018-09-04 | MRT-DS-REC-TT-180333-FC | FC | 3 | 2018-09-13 | 180333-FC STAMPED | FC | 3 | A | CIVIL | HRSG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UHA-170007 | 996 | [HRSG Foundation(For Block 2)]_Plan drawing | FA | 2017-11-05 | 2018-02-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-02-02 | 190022-FC STAMPED | FC | 3 | A | CIVIL | HRSG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UHA-170007 | 997 | [HRSG Foundation(For Block 3, 4)]_Plan drawing | FA | 2017-11-05 | 2018-03-16 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-02-02 | 190022-FC STAMPED | FC | 3 | A | CIVIL | HRSG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UHA-170008 | 998 | [HRSG Foundation(For Block 2)]_Sectional drawing | FA | 2017-11-05 | 2018-02-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-08-13 | 180203-FC STAMPED | FC | 2 | A | CIVIL | HRSG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UHA-170008 | 999 | [HRSG Foundation(For Block 3, 4)]_Sectional drawing | FA | 2017-11-05 | 2018-03-16 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2018-08-13 | 180203-FC STAMPED | FC | 2 | A | CIVIL | HRSG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UHA-170009 | 1000 | [HRSG Foundation(For Block 2)]_Detail drawing | FA | 2017-12-05 | 2018-02-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-03-11 | 190055-FC STAMPED | FC | 4 | A | CIVIL | HRSG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UHA-170009 | 1001 | [HRSG Foundation(For Block 3, 4)]_Detail drawing | FA | 2017-12-05 | 2018-03-16 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-03-11 | 190055-FC STAMPED | FC | 4 | A | CIVIL | HRSG FDN
DHI | 토목기술 | 박찬웅 | MRT-VK02-P2UHA-170010 | 1002 | [HRSG Foundation(For Block 2)]_Re-bar Arrangement | FA | 2017-11-05 | 2018-02-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-02-02 | 190022-FC STAMPED | FC | 3 | A | CIVIL | HRSG FDN
DHI | 토목기술 | 박찬웅 | MRT-VK02-P3UHA-170010 | 1003 | [HRSG Foundation(For Block 3, 4)]_Re-bar Arrangement | FA | 2017-11-05 | 2018-03-16 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-02-02 | 190022-FC STAMPED | FC | 3 | A | CIVIL | HRSG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC07-P2UHA-170101 | 1004 | [HRSG MISCELLANEOUS Foundation(For Block 2)]_Calculation | FA | 2017-10-20 | 2018-02-16 | 2018-11-01 | 2018-11-09 | MRT-DS-REC-TT-180815-FC | FC | 3 | 2018-11-09 | 180815-FC STAMPED | FC | 3 | A | CIVIL | HRSG MISC FDN
DHI | 토목기술 | 박찬웅 | MRT-CC07-P3UHA-170101 | 1005 | [HRSG MISCELLANEOUS Foundation(For Block 3, 4)]_Calculation | FA | 2017-10-20 | 2018-03-16 | 2018-11-01 | 2018-11-09 | MRT-DS-REC-TT-180815-FC | FC | 3 | 2018-11-09 | 180815-FC STAMPED | FC | 3 | A | CIVIL | HRSG MISC FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UHA-170103 | 1006 | [HRSG MISCELLANEOUS Foundation(For Block 2)]_Plan drawing | FA | 2017-10-20 | 2018-02-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-08-12 | 190159-FC STAMPED | FC | 11 | A | CIVIL | HRSG MISC FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UHA-170103 | 1007 | [HRSG MISCELLANEOUS Foundation(For Block 3, 4)]_Plan drawing | FA | 2017-10-20 | 2018-03-16 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-08-12 | 190159-FC STAMPED | FC | 11 | A | CIVIL | HRSG MISC FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UHA-170104 | 1008 | [HRSG MISCELLANEOUS Foundation(For Block 2)]_Sectional drawing | FA | 2017-10-20 | 2018-02-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-06-19 | 190142-FC STAMPED | FC | 7 | A | CIVIL | HRSG MISC FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UHA-170104 | 1009 | [HRSG MISCELLANEOUS Foundation(For Block 3, 4)]_Sectional drawing | FA | 2017-10-20 | 2018-03-16 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-06-19 | 190142-FC STAMPED | FC | 7 | A | CIVIL | HRSG MISC FDN
DHI | 토목기술 | 박찬웅 | MRT-VK02-P2UHA-170106 | 1010 | [HRSG MISCELLANEOUS Foundation(For Block 2)]_Re-bar Arrangement | FA | 2017-10-20 | 2018-02-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-04-11 | 190095-FC STMAPED | FC | 8 | A | CIVIL | HRSG MISC FDN
DHI | 토목기술 | 박찬웅 | MRT-VK02-P3UHA-170106 | 1011 | [HRSG MISCELLANEOUS Foundation(For Block 3, 4)]_Re-bar Arrangement | FA | 2017-10-20 | 2018-03-16 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-04-11 | 190095-FC STMAPED | FC | 8 | A | CIVIL | HRSG MISC FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P0UMA-171003 | 1012 | [N2 Gas System Foundation]_Plan & Section drawing | FA | 2018-10-12 | 2018-12-14 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-02-11 | 190023-FC STAMPED | FC | 1 | A | CIVIL | N2 FDN
DHI | 토목기술 | 박찬웅 | MRT-VK02-P0UMA-171006 | 1013 | [N2 Gas System Foundation]_Re-bar Arrangement | FA | 2018-10-12 | 2018-12-14 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-02-11 | 190023-FC STAMPED | FC | 1 | A | CIVIL | N2 FDN
DHI | 토목기술 | 박찬웅 | MRT-CC07-P2UEJ-170901 | 1014 | [Clean and Dirty Oil Tank Foundation(For Block 2)]_Calculation | FA | 2018-04-27 | 2018-07-27 | 2018-08-09 | 2018-10-02 | MRT-DS-REC-TT-180650-FC | FC | 1 | 2018-10-22 | 180650-FC STAMPED | FC | 1 | A | CIVIL | OIL TANK FDN
DHI | 토목기술 | 박찬웅 | MRT-CC07-P3UEJ-170901 | 1015 | [Clean and Dirty Oil Tank Foundation(For Block 3, 4)]_Calculation | FA | 2018-04-27 | 2018-07-27 | 2018-08-09 | 2018-10-02 | MRT-DS-REC-TT-180650-FC | FC | 1 | 2018-10-22 | 180650-FC STAMPED | FC | 1 | A | CIVIL | OIL TANK FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UEJ-170907 | 1016 | [Clean and Dirty Oil Tank Foundation(For Block 2)]_Plan & Section drawing | FA | 2018-04-27 | 2018-07-27 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2020-08-13 | 200059-FC STAMPED | FC | 3 | A | CIVIL | OIL TANK FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UEJ-170907 | 1017 | [Clean and Dirty Oil Tank Foundation(For Block 3, 4)]_Plan & Section drawing | FA | 2018-04-27 | 2018-07-27 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2020-08-13 | 200059-FC STAMPED | FC | 3 | A | CIVIL | OIL TANK FDN
DHI | 토목기술 | 박찬웅 | MRT-VK02-P2UEJ-170910 | 1018 | [Clean and Dirty Oil Tank Foundation(For Block 2)]_Re-bar Arrangement | FA | 2018-04-27 | 2018-07-27 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-04-23 | 190108-FC STAMPED | FC | 2 | A | CIVIL | OIL TANK FDN
DHI | 토목기술 | 박찬웅 | MRT-VK02-P3UEJ-170910 | 1019 | [Clean and Dirty Oil Tank Foundation(For Block 3, 4)]_Re-bar Arrangement | FA | 2018-04-27 | 2018-07-27 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-04-23 | 190108-FC STAMPED | FC | 2 | A | CIVIL | OIL TANK FDN
DHI | 토목기술 | 박찬웅 | MRT-CC07-P0UMA-171201 | 1020 | [Sampling System Foundation]_Calculation | FA | 2019-07-19 | 2019-09-19 | 2019-07-31 | 2019-08-02 | MRT-DS-REC-TT-190160-FC | FC | 0 | 2019-08-02 | 190160-FC STAMPED | FC | 0 | A | CIVIL | SAMPLING FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P0UMA-171203 | 1021 | [Sampling System Foundation]_Plan & Section & Rebar Drawing | FA | 2019-07-19 | 2019-09-19 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-08-27 | 190174-FC STAMPED | FC | 1 | A | CIVIL | SAMPLING FDN
DHI | 토목기술 | 박찬웅 | MRT-CC07-P2UMA-170201 | 1022 | [Steam Turbine Generator Foundation(For Block 2)]_Pile calculation | FA | 2017-10-20 | 2018-01-01 | 2018-08-09 | 2018-11-15 | MRT-DS-REC-TT-180636-FC | FC | 2 | 2018-11-24 | 180636-FC STAMPED | FC | 2 | A | CIVIL | STG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC07-P3UMA-170201 | 1023 | [Steam Turbine Generator Foundation(For Block 3, 4)]_Pile calculation | FA | 2017-10-20 | 2018-02-01 | 2018-08-09 | 2018-11-15 | MRT-DS-REC-TT-180636-FC | FC | 2 | 2018-11-24 | 180636-FC STAMPED | FC | 2 | A | CIVIL | STG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170203 | 1024 | [Steam Turbine Generator Foundation(For Block 2)]_Pile Arrangement Drawing | FA | 2017-10-20 | 2018-01-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-09-07 | 180318-FC STAMPED | FC | 2 | A | CIVIL | STG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170203 | 1025 | [Steam Turbine Generator Foundation(For Block 3, 4)]_Pile Arrangement Drawing | FA | 2017-10-20 | 2018-02-01 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2018-09-07 | 180318-FC STAMPED | FC | 2 | A | CIVIL | STG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170204 | 1026 | [Steam Turbine Generator Foundation(For Block 2)]_Pile Schedule | FA | 2017-10-20 | 2018-01-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-09-07 | 180318-FC STAMPED | FC | 2 | A | CIVIL | STG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170204 | 1027 | [Steam Turbine Generator Foundation(For Block 3, 4)]_Pile Schedule | FA | 2017-10-20 | 2018-02-01 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2018-09-07 | 180318-FC STAMPED | FC | 2 | A | CIVIL | STG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC07-P2UMA-170205 | 1028 | [Steam Turbine Generator Foundation(For Block 2)]_Calculation | FA | 2017-11-05 | 2018-02-12 | 2018-08-09 | 2018-11-15 | MRT-DS-REC-TT-180636-FC | FC | 2 | 2018-11-24 | 180636-FC STAMPED | FC | 2 | A | CIVIL | STG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC07-P3UMA-170205 | 1029 | [Steam Turbine Generator Foundation(For Block 3, 4)]_Calculation | FA | 2017-11-05 | 2018-03-12 | 2018-08-09 | 2018-11-15 | MRT-DS-REC-TT-180636-FC | FC | 2 | 2018-11-24 | 180636-FC STAMPED | FC | 2 | A | CIVIL | STG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170207 | 1030 | [Steam Turbine Generator Foundation(For Block 2)]_Plan drawing | FA | 2017-11-05 | 2018-02-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-08-27 | 190175-FC STAMPED | FC | 7 | A | CIVIL | STG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170207 | 1031 | [Steam Turbine Generator Foundation(For Block 3, 4)]_Plan drawing | FA | 2017-11-05 | 2018-03-12 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-08-27 | 190175-FC STAMPED | FC | 7 | A | CIVIL | STG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170208 | 1032 | [Steam Turbine Generator Foundation(For Block 2)]_Sectional drawing | FA | 2017-11-05 | 2018-02-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-12-22 | 180821-FC STAMPED | FC | 4 | A | CIVIL | STG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170208 | 1033 | [Steam Turbine Generator Foundation(For Block 3, 4)]_Sectional drawing | FA | 2017-11-05 | 2018-03-12 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-05-28 | 324/T/MRT/REC/V/2019 | FC | 5 | A | CIVIL | STG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170209 | 1034 | [Steam Turbine Generator Foundation(For Block 2)]_Detail drawing | FA | 2018-01-05 | 2018-03-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-04-15 | 190100-FC STAMPED | FC | 4 | A | CIVIL | STG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170209 | 1035 | [Steam Turbine Generator Foundation(For Block 3, 4)]_Detail drawing | FA | 2018-01-05 | 2018-04-12 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-04-15 | 190100-FC STAMPED | FC | 4 | A | CIVIL | STG FDN
DHI | 토목기술 | 박찬웅 | MRT-VK02-P2UMA-170210 | 1036 | [Steam Turbine Generator Foundation(For Block 2)]_Re-bar Arrangement | FA | 2017-11-05 | 2018-02-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-04-15 | 190100-FC STAMPED | FC | 4 | A | CIVIL | STG FDN
DHI | 토목기술 | 박찬웅 | MRT-VK02-P3UMA-170210 | 1037 | [Steam Turbine Generator Foundation(For Block 3, 4)]_Re-bar Arrangement | FA | 2017-11-05 | 2018-06-01 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-04-15 | 190100-FC STAMPED | FC | 4 | A | CIVIL | STG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC07-P2UMA-170211 | 1038 | [Steam Turbine Generator Foundation(For Block 2)]_Dynamic Analysis for TG Pedestal | FA | 2017-11-05 | 2018-02-12 | 2018-08-09 | 2018-11-15 | MRT-DS-REC-TT-180636-FC | FC | 2 | 2018-11-24 | 180636-FC STAMPED | FC | 2 | A | CIVIL | STG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC07-P3UMA-170211 | 1039 | [Steam Turbine Generator Foundation(For Block 3, 4)]_Dynamic Analysis for TG Pedestal | FA | 2017-11-05 | 2018-03-12 | 2018-08-09 | 2018-11-15 | MRT-DS-REC-TT-180636-FC | FC | 2 | 2018-11-24 | 180636-FC STAMPED | FC | 2 | A | CIVIL | STG FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P0UMA-171103 | 1040 | [Sump Pump Pit]_Plan & Section drawing | FA | 2018-11-12 | 2019-01-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-04-15 | 190098-FC STAMPED | FC | 2 | A | CIVIL | SUMP PIT
DHI | 토목기술 | 박찬웅 | MRT-VK02-P0UMA-171106 | 1041 | [Sump Pump Pit]_Re-bar Arrangement | FA | 2018-11-12 | 2019-01-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-12-27 | 180927-FC STAMPED | FC | 0 | A | CIVIL | SUMP PIT
DHI | 토목기술 | 박찬웅 | MRT-CC07-P2UAG-170301 | 1042 | [TR Foundation(For Block 2)]_Calculation | FA | 2018-07-13 | 2018-09-08 | 2018-08-09 | 2018-08-28 | MRT-DS-REC-TT-180660-FC | FC | 1 | 2018-09-13 | 180660-FC STAMPED | FC | 1 | A | CIVIL | TR FDN
DHI | 토목기술 | 박찬웅 | MRT-CC07-P3UAG-170301 | 1043 | [TR Foundation(For Block 3, 4)]_Calculation | FA | 2018-07-13 | 2018-09-08 | 2018-08-09 | 2018-08-28 | MRT-DS-REC-TT-180660-FC | FC | 1 | 2018-09-13 | 180660-FC STAMPED | FC | 1 | A | CIVIL | TR FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UAG-170303 | 1044 | [TR Foundation(For Block 2)]_Pile Arrangement Drawing | FA | 2018-07-13 | 2018-09-08 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-09-13 | 180660-FC STAMPED | FC | 1 | A | CIVIL | TR FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UAG-170303 | 1045 | [TR Foundation(For Block 3, 4)]_Pile Arrangement Drawing | FA | 2018-07-13 | 2018-09-08 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2018-09-13 | 180660-FC STAMPED | FC | 1 | A | CIVIL | TR FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UAG-170307 | 1046 | [TR Foundation(For Block 2)]_Plan drawing | FA | 2018-07-13 | 2018-09-08 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-11-25 | 190220-FC STAMPED | FC | 4 | A | CIVIL | TR FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UAG-170307 | 1047 | [TR Foundation(For Block 3, 4)]_Plan drawing | FA | 2018-07-13 | 2018-09-08 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-11-25 | 190220-FC STAMPED | FC | 3 | A | CIVIL | TR FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UAG-170308 | 1048 | [TR Foundation(For Block 2)]_Sectional drawing | FA | 2018-07-13 | 2018-09-08 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-11-25 | 190220-FC STAMPED | FC | 5 | A | CIVIL | TR FDN
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UAG-170308 | 1049 | [TR Foundation(For Block 3, 4)]_Sectional drawing | FA | 2018-07-13 | 2018-09-08 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-11-25 | 190220-FC STAMPED | FC | 4 | A | CIVIL | TR FDN
DHI | 토목기술 | 박찬웅 | MRT-VK02-P2UAG-170310 | 1050 | [TR Foundation(For Block 2)]_Re-bar Arrangement | FA | 2018-07-13 | 2018-09-08 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-03-30 | 190081-FC STAMPED | FC | 2 | A | CIVIL | TR FDN
DHI | 토목기술 | 박찬웅 | MRT-VK02-P3UAG-170310 | 1051 | [TR Foundation(For Block 3, 4)]_Re-bar Arrangement | FA | 2018-07-13 | 2018-09-08 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2018-12-12 | 180890-FC STAMPED | FC | 1 | A | CIVIL | TR FDN
DHI | TG_SKODA | 백운홍 | MRT-XA00-P2MAA-220014 | 1052 | [STEAM TURBINE] GENERAL ARRANGEMENT DRAWING - LAYOUT +3.10MM (BLOCK #2) | FA | 2017-11-26 | 2018-01-12 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-07-12 | 190139-FC STAMPED | FC | 4 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XA00-P2MAA-220015 | 1053 | [STEAM TURBINE] GENERAL ARRANGEMENT DRAWING - LAYOUT +9.10MM (BLOCK #2) | FA | 2017-11-26 | 2018-01-12 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-07-12 | 190139-FC STAMPED | FC | 4 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XA00-P2MAA-220016 | 1054 | [STEAM TURBINE] GENERAL ARRANGEMENT DRAWING - LAYOUT +14.60MM (BLOCK #2) | FA | 2017-11-26 | 2018-01-12 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-07-12 | 190139-FC STAMPED | FC | 4 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XA00-P2MAA-220017 | 1055 | [STEAM TURBINE] GENERAL ARRANGEMENT DRAWING - LAYOUT LONGGITUDINAL SECTION AA (BLOCK #2) | FA | 2017-11-26 | 2018-01-12 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-07-12 | 190139-FC STAMPED | FC | 4 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XA00-P2MAA-220018 | 1056 | [STEAM TURBINE] GENERAL ARRANGEMENT DRAWING - LAYOUT LONGGITUDINAL SECTION BB (BLOCK #2) | FA | 2017-11-26 | 2018-01-12 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-07-12 | 190139-FC STAMPED | FC | 4 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XA00-P2MAA-220020 | 1057 | [STEAM TURBINE] TURBINE CROSS SECTION 1-1 (BLOCK #2) | FA | 2017-11-26 | 2018-01-12 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-07-12 | 190139-FC STAMPED | FC | 4 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XA00-P2MAA-220021 | 1058 | [STEAM TURBINE] TURBINE CROSS SECTION 2-2 (BLOCK #2) | FA | 2017-11-26 | 2018-01-12 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-07-12 | 190139-FC STAMPED | FC | 4 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XA00-P2MAA-220022 | 1059 | [STEAM TURBINE] TURBINE CROSS SECTION 3-3 (BLOCK #2) | FA | 2017-11-26 | 2018-01-12 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-07-12 | 190139-FC STAMPED | FC | 4 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XA00-P3MAA-220014 | 1060 | [STEAM TURBINE] GENERAL ARRANGEMENT DRAWING - LAYOUT +3.10MM (BLOCK #3,4) | FA | 2017-12-24 | 2018-01-28 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XA00-P3MAA-220015 | 1061 | [STEAM TURBINE] GENERAL ARRANGEMENT DRAWING - LAYOUT +9.10MM (BLOCK #3,4) | FA | 2017-12-24 | 2018-01-28 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XA00-P3MAA-220016 | 1062 | [STEAM TURBINE] GENERAL ARRANGEMENT DRAWING - LAYOUT +14.60MM (BLOCK #3,4) | FA | 2017-12-24 | 2018-01-28 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XA00-P3MAA-220017 | 1063 | [STEAM TURBINE] GENERAL ARRANGEMENT DRAWING - LAYOUT LONGGITUDINAL SECTION AA (BLOCK #3,4) | FA | 2017-12-24 | 2018-01-28 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XA00-P3MAA-220018 | 1064 | [STEAM TURBINE] GENERAL ARRANGEMENT DRAWING - LAYOUT LONGGITUDINAL SECTION BB (BLOCK #3,4) | FA | 2017-12-24 | 2018-01-28 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XA00-P3MAA-220019 | 1065 | [STEAM TURBINE] GENERAL ARRANGEMENT DRAWING - LAYOUT LONGGITUDINAL SECTION CC (BLOCK #3,4) | FA | 2017-12-24 | 2018-01-28 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XA00-P3MAA-220020 | 1066 | [STEAM TURBINE] TURBINE CROSS SECTION 1-1 (BLOCK #3,4) | FA | 2017-12-24 | 2018-01-28 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XA00-P3MAA-220021 | 1067 | [STEAM TURBINE] TURBINE CROSS SECTION 2-2 (BLOCK #3,4) | FA | 2017-12-24 | 2018-01-28 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XA00-P3MAA-220022 | 1068 | [STEAM TURBINE] TURBINE CROSS SECTION 3-3 (BLOCK #3,4) | FA | 2017-12-24 | 2018-01-28 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XG02-P2MAA-220005 | 1069 | [STEAM TURBINE] P&I DIAGRAM STEAM-WATER (BLOCK #2) | FA | 2017-12-03 | 2018-04-22 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-11-01 | 190208-FC STAMPED | FC | 3 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XG02-P3MAA-220005 | 1070 | [STEAM TURBINE] P&I DIAGRAM STEAM-WATER (BLOCK #3, 4) | FA | 2017-12-03 | 2018-04-22 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XG02-P2MAV-220006 | 1071 | [STEAM TURBINE] P&I DIAGRAM LUBRICATION OIL (BLOCK #2) | FA | 2017-12-03 | 2018-04-22 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2018-12-03 | 180797-FC STAMPED | FC | 2 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XG02-P3MAV-220006 | 1072 | [STEAM TURBINE] P&I DIAGRAM LUBRICATION OIL (BLOCK #3,4) | FA | 2017-12-03 | 2018-04-22 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XG02-P2MAX-220007 | 1073 | [STEAM TURBINE] P&I DIAGRAM HPH (BLOCK #2) | FA | 2017-12-03 | 2018-04-22 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2018-10-23 | 180788-FC STAMPED | FC | 1 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XG02-P3MAX-220007 | 1074 | [STEAM TURBINE] P&I DIAGRAM HPH (BLOCK #3,4) | FA | 2017-12-03 | 2018-04-22 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XK00-P2MAA-220207 | 1075 | [STEAM TURBINE] DRAWINGS AND PARTS LISTS OF TURBINE (BLOCK #2) | FI | 2019-04-18 |  | 2019-06-26 | 2019-07-01 | MRT-DS-REC-TT-190117-FC | FC | 0 | 2019-07-01 | 190117-FC STAMPED | FC | 0 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XK00-P3MAA-220207 | 1076 | [STEAM TURBINE] DRAWINGS AND PARTS LISTS OF TURBINE (BLOCK #3,4) | FI | 2019-03-14 |  | 2020-05-08 | 2020-06-10 | MRT-DS-REC-TT-200041-FC | FC | 1 | 2020-06-10 | 200041-FC STAMPED | FC | 1 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XR00-P2MAA-220040 | 1077 | [STEAM TURBINE] LIST OF EQUIPMENTS (BLOCK #2) | FI | 2018-10-25 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-03-18 | 180843-FC STAMPED | FC | 0 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XR00-P3MAA-220040 | 1078 | [STEAM TURBINE] LIST OF EQUIPMENTS (BLOCK #3,4) | FI | 2018-11-07 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XR00-P2MAV-220041 | 1079 | [STEAM TURBINE] LIST OF OIL SYSTEM EQUIPMENTS (BLOCK #2) | FI | 2018-10-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-03-18 | 180816-FC STAMPED | FC | 0 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XR00-P3MAV-220041 | 1080 | [STEAM TURBINE] LIST OF OIL SYSTEM EQUIPMENTS (BLOCK #3,4) | FI | 2019-03-14 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XN00-P2MAV-220039 | 1081 | [STEAM TURBINE] LIST OF VALVES - OIL SYSTEM (BLOCK #2) | FI | 2019-02-18 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-03-12 | 190037-FC STAMPED | FC | 0 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XN00-P3MAV-220039 | 1082 | [STEAM TURBINE] LIST OF VALVES - OIL SYSTEM (BLOCK #3,4) | FI | 2019-02-18 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XN00-P2MAA-220038 | 1083 | [STEAM TURBINE] LIST OF VALVES - STEAM AND WATER (BLOCK #2) | FI | 2019-02-18 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2021-08-27 | 210048-FC STAMPED | FC | 1 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XN00-P3MAA-220038 | 1084 | [STEAM TURBINE] LIST OF VALVES - STEAM AND WATER (BLOCK #3,4) | FI | 2019-02-18 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XM00-P2MAA-220012 | 1085 | [STEAM TURBINE] STEAM TURBINE LAYDOWN PLAN (BLOCK #2) | FI | 2017-12-03 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-10-18 | 190211-FC STAMPED | FC | 1 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XM00-P3MAA-220012 | 1086 | [STEAM TURBINE] STEAM TURBINE LAYDOWN PLAN (BLOCK #3, 4) | FI | 2017-12-03 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YV02-P3MAK-230077 | 1087 | [STEAM TURBINE] FREQUENCY CONVERTER FOR TURNING GEAR (BLOCK #3,4) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XV00-P2MAA-220036 | 1088 | [STEAM TURBINE] PIPING LINE LIST - STEAM-WATER (BLOCK #2) | FA | 2018-01-10 | 2018-04-10 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2018-10-16 | 180621-FC STAMPED | FC | 3 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XV00-P3MAA-220036 | 1089 | [STEAM TURBINE] PIPING LINE LIST - STEAM-WATER (BLOCK #3, 4) | FA | 2018-01-10 | 2018-04-10 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XV00-P2MAV-220037 | 1090 | [STEAM TURBINE] PIPING LINE LIST - LUBRICATION OIL (BLOCK #2) | FA | 2018-01-10 | 2018-04-10 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-12-04 | 141/T/MRT/REC/XII/2020 | FC | 4 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XV00-P3MAV-220037 | 1091 | [STEAM TURBINE] PIPING LINE LIST - LUBRICATION OIL (BLOCK #3, 4) | FA | 2018-01-10 | 2018-04-10 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YD00-P2MAA-220214 | 1092 | [STEAM TURBINE] ISOMETRIC DRAWINGS OF PIPELINES FOR SMALL BORE PIPING (BLOCK #2) | FI | 2020-02-25 | 2020-04-25 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-02-25 | 200019-FC STAMPED | FI | 0 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YD00-P3MAA-220214 | 1093 | [STEAM TURBINE] ISOMETRIC DRAWINGS OF PIPELINES FOR SMALL BORE PIPING (BLOCK #3,4) | FI | 2019-09-01 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-VE01-P2MAA-220044 | 1094 | [STEAM TURBINE] ALLOWABLE FORCES AND MOMENTS (BLOCK #2) | FI | 2018-01-28 |  | 2019-04-08 | 2019-04-08 | MRT-DS-REC-TT-190067 | FI | 1 | 2019-04-10 | 211/T/MRT/REC/IV/2019 | FI | 1 | I | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-VE01-P3MAA-220044 | 1095 | [STEAM TURBINE] ALLOWABLE FORCES AND MOMENTS (BLOCK #3, 4) | FI | 2018-01-28 |  | 2019-04-08 | 2019-04-08 | MRT-DS-REC-TT-190067 | FI | 1 | 2019-04-10 | 211/T/MRT/REC/IV/2019 | FI | 1 | I | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XG01-P2MAA-220045 | 1096 | [STEAM TURBINE] DETAIL DRAWINGS - PIPING, COMPONENTS AND BOM (BLOCK #2) | FI | 2018-07-08 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-06-29 | 200052-FC STAMPED | FC | 3 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XG01-P3MAA-220045 | 1097 | [STEAM TURBINE] DETAIL DRAWINGS - PIPING, COMPONENTS AND BOM (BLOCK #3, 4) | FI | 2018-07-08 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XT00-P2MAA-220208 | 1098 | [STEAM TURBINE] FOUNDATION BOLT ASSEMBLY AND PART LIST (BLOCK #2) FOR INSTALLATION | FI | 2019-01-10 |  | 2019-01-11 | 2019-01-11 | MRT-DS-REC-TT-190009-FC | FC | 0 | 2019-01-12 | 190009-FC STAMPED | FC | 0 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XT00-P3MAA-220208 | 1099 | [STEAM TURBINE] FOUNDATION BOLT ASSEMBLY AND PART LIST (BLOCK #3,4) FOR INSTALLATION | FI | 2019-01-10 |  | 2019-01-11 | 2019-01-11 | MRT-DS-REC-TT-190009-FC | FC | 0 | 2019-01-12 | 190009-FC STAMPED | FC | 0 | A | MECHANICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YV02-P2MAK-230077 | 1100 | [STEAM TURBINE] STARTER FOR TURNING GEAR (BLOCK #2) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-04-08 | 190032-FC STAMPED | FC | 0 | A | ELECTRICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YV02-P2MAV-230078 | 1101 | [STEAM TURBINE] DC MOTOR STARTER (BLOCK #2) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-04-08 | 190032-FC STAMPED | FC | 0 | A | ELECTRICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YV02-P3MAV-230078 | 1102 | [STEAM TURBINE] DC MOTOR STARTER (BLOCK #3,4) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-07-18 | MTW-AS-C-LT-24.5541.0 | AB | Z0 | A | ELECTRICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YL15-P2CJJ-240072 | 1103 | [STEAM TURBINE] CABLE LIST (BLOCK #2) | FA | 2019-02-20 | 2019-04-20 | 2019-04-01 | 2019-04-12 | MRT-DS-REC-TT-190042-FC | FC | 0 | 2019-04-12 | 190042-FC STAMPED | FC | 0 | A | ELECTRICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YL15-P3CJJ-240072 | 1104 | [STEAM TURBINE] CABLE LIST (BLOCK #3,4) | FA | 2019-02-20 | 2019-04-20 | 2019-04-01 | 2019-04-12 | MRT-DS-REC-TT-190042-FC | FC | 0 | 2019-04-12 | 190042-FC STAMPED | FC | 0 | A | ELECTRICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YL15-P2CJJ-240122 | 1105 | [STEAM TURBINE] CABLE LIST FOR FIELD INSTALLATION (BLOCK #2) | FI | 2020-07-09 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-07-09 | 200058-FC STAMPED | FI | 0 | A | ELECTRICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YL15-P3CJJ-240114 | 1106 | [STEAM TURBINE] CABLE LIST FOR FIELD INSTALLATION (BLOCK #3,4) | FI | 2019-02-20 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | ELECTRICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YL15-P2MAD-240171 | 1107 | [STEAM TURBINE] VIBRATION MONITORING SYSTEM - CABLE LIST (BLOCK #2) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-04-08 | 190032-FC STAMPED | FC | 0 | A | ELECTRICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YL15-P3MAD-240181 | 1108 | [STEAM TURBINE] VIBRATION MONITORING SYSTEM - CABLE LIST (BLOCK #3,4) | FI | 2019-02-20 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | ELECTRICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YV02-P2CJJ-240121 | 1109 | [STEAM TURBINE] WIRING DIAGRAMS, LOOP DIAGRAMS (BLOCK #2) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-03-07 | 200022-FC STAMPED | FC | 2 | A | ELECTRICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YV02-P3CJJ-240113 | 1110 | [STEAM TURBINE] WIRING DIAGRAMS, LOOP DIAGRAMS (BLOCK #3,4) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | ELECTRICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YV02-P2MAX-220095 | 1111 | [STEAM TURBINE] WIRING DIAGRAMS, HIGH-PRESSURE HYDRAULIC (BLOCK #2) | FI | 2020-04-08 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-04-08 | 200033-FC STAMPED | FI | 0 | A | ELECTRICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YV02-P3MAX-220144 | 1112 | [STEAM TURBINE] WIRING DIAGRAMS, HIGH-PRESSURE HYDRAULIC (BLOCK #3,4) | FI | 2020-04-29 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | ELECTRICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YD05-P3MAA-240157 | 1113 | [STEAM TURBINE] WIRING DIAGRAMS, LOOP DIAGRAMS for Synchr. System of Turning gear (BLOCK #3,4) | FI | 2020-08-14 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | ELECTRICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YV02-P2MAD-240170 | 1114 | [STEAM TURBINE] VIBRATION MONITORING SYSTEM - WIRING DIAGRAMS (BLOCK #2) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-04-08 | 190032-FC STAMPED | FC | 0 | A | ELECTRICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YV02-P3MAD-240180 | 1115 | [STEAM TURBINE] VIBRATION MONITORING SYSTEM - WIRING DIAGRAMS (BLOCK #3,4) | FI | 2019-04-04 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-07-18 | MTW-AS-C-LT-24.5541.0 | AB | Z0 | A | ELECTRICAL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XS01-P2CJJ-240060 | 1116 | [STEAM TURBINE] CONTROL SYSTEM FUNCTIONS PHILOSOPHY (BLOCK #2) | FI | 2018-03-11 |  | 2019-02-22 | 2019-02-22 | MRT-DS-REC-TT-190053 | FI | 1 | 2019-03-27 | 164/T/MRT/REC/III/2019 | FI | 1 | I | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XS01-P3CJJ-240060 | 1117 | [STEAM TURBINE] CONTROL SYSTEM FUNCTIONS PHILOSOPHY (BLOCK #3, 4) | FI | 2018-03-11 |  | 2019-03-14 | 2019-03-14 | MRT-DS-REC-TT-190077 | FI | 1 | 2019-04-04 | 194/T/MRT/REC/IV/2019 | FI | 1 | I | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XR00-P2MAA-220086 | 1118 | [STEAM TURBINE] FUNCTIONAL DESCRIPTION (BLOCK #2) | FI | 2019-02-20 |  | 2019-04-01 | 2019-04-12 | MRT-DS-REC-TT-190042-FC | FC | 0 | 2019-04-12 | 190042-FC STAMPED | FC | 0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XR00-P3MAA-220082 | 1119 | [STEAM TURBINE] FUNCTIONAL DESCRIPTION (BLOCK #3,4) | FI | 2019-02-12 |  | 2019-04-01 | 2019-04-08 | MRT-DS-REC-TT-190032-FC | FC | 0 | 2019-04-08 | 190032-FC STAMPED | FC | 0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YF00-P2CJJ-240064 | 1120 | [STEAM TURBINE] LOGIC DIAGRAMS (BLOCK #2) | FI | 2018-07-15 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-07-09 | 377/T/MRT/REC/VII/2019 | FI | 1 | I | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YF00-P3CJJ-240064 | 1121 | [STEAM TURBINE] LOGIC DIAGRAMS (BLOCK #3, 4) | FI | 2018-07-15 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2025-01-14 | MTW-G-C-LT-25.6118.0 | AB | Z0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YF00-P2CJJ-240213 | 1122 | [STEAM TURBINE] LOGIC DIAGRAMS FOR CONTROL SYSTEM (BLOCK #2) | FI | 2020-07-14 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-07-20 | 200060-FC STAMPED | FI | 0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YK00-P2CJJ-240065 | 1123 | [STEAM TURBINE] PROTECTION DIAGRAM FOR I&C (BLOCK #2) | FI | 2020-07-14 |  | 2020-07-14 | 2020-07-14 | MRT-DS-REC-TT-200060-FC | FI | 0 | 2020-07-20 | 200060-FC STAMPED | FI | 0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YK00-P3CJJ-240065 | 1124 | [STEAM TURBINE] PROTECTION DIAGRAM FOR I&C (BLOCK #3,4) | FI | 2020-08-14 |  | 2020-08-25 | 2020-08-26 | MRT-DS-REC-TT-200066-FC | FI | 0 | 2020-08-26 | 200066-FC STAMPED | FI | 0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YD05-P2CJJ-240069 | 1125 | [STEAM TURBINE] HMI DESIGN (BLOCK #2) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-04-08 | 190032-FC STAMPED | FC | 0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YD05-P3CJJ-240069 | 1126 | [STEAM TURBINE] HMI DESIGN (BLOCK #3,4) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YV02-P2CJJ-240113 | 1127 | [STEAM TURBINE] HMI DESIGN FOR CONTROL SYSTEM (BLOCK #2) | FI | 2020-07-14 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-07-20 | 200060-FC STAMPED | FI | 0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YV02-P3CJJ-240105 | 1128 | [STEAM TURBINE] HMI DESIGN FOR CONTROL SYSTEM (BLOCK #3,4) | FI | 2020-08-14 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YL01-P2CJJ-240073 | 1129 | [STEAM TURBINE] LIST OF CABINETS AND JB (BLOCK #2) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-04-08 | 190032-FC STAMPED | FC | 0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YL01-P3CJJ-240073 | 1130 | [STEAM TURBINE] LIST OF CABINETS AND JB (BLOCK #3,4) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YR00-P2CJJ-240055 | 1131 | [STEAM TURBINE] CONTROL SYSTEM ARCHITECTURE (BLOCK #2) | FI | 2018-02-11 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-04-04 | 193/T/MRT/REC/IV/2019 | FI | 1 | I | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YR00-P3CJJ-240055 | 1132 | [STEAM TURBINE] CONTROL SYSTEM ARCHITECTURE (BLOCK #3, 4) | FI | 2018-02-11 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YF02-P2CJJ-240112 | 1133 | [STEAM TURBINE] CONTROL SYSTEM HARDWARE SPECIFICATION (BLOCK #2) | FI | 2018-05-06 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-05-20 | 200041-FC STAMPED | FC | 1 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YF02-P3CJJ-240104 | 1134 | [STEAM TURBINE] CONTROL SYSTEM HARDWARE SPECIFICATION (BLOCK #3, 4) | FI | 2018-05-06 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YF02-P2MAD-240168 | 1135 | [STEAM TURBINE] CONTROL SYSTEM HARDWARE SPECIFICATION FOR VMS (BLOCK #2) | FI | 2019-02-18 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-04-11 | 190037-FC STAMPED | FC | 0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YF02-P3MAD-240178 | 1136 | [STEAM TURBINE] CONTROL SYSTEM HARDWARE SPECIFICATION FOR VMS (BLOCK #3,4) | FI | 2019-09-01 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YF02-P2MAX-220094 | 1137 | [STEAM TURBINE] CONTROL SYSTEM. HARDWARE SPECIFICATION FOR HPH OIL SYSTEM (BLOCK #2) | FI | 2020-07-14 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-07-20 | 200060-FC STAMPED | FI | 0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAX-220143 | 1138 | [STEAM TURBINE] CONTROL SYSTEM. HARDWARE SPECIFICATION FOR HPH OIL SYSTEM (BLOCK #3,4) | FI | 2020-08-14 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YF02-P3MAA-240156 | 1139 | [STEAM TURBINE] CONTROL SYSTEM. HARDWARE SPECIFICATION FOR Synchr. SYSTEM OF TURNING GEAR (BLOCK #3,4) | FI | 2020-08-14 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YL01-P2CJJ-240070 | 1140 | [STEAM TURBINE] I/O LIST (BLOCK #2) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-12-16 | 190241-FC STAMPED | FC | 1 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YL01-P3CJJ-240070 | 1141 | [STEAM TURBINE] I/O LIST (BLOCK #3,4) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YL01-P2MAD-240169 | 1142 | [STEAM TURBINE] I/O LIST FOR VMS (BLOCK #2) | FI | 2020-07-14 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-07-20 | 200060-FC STAMPED | FI | 0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YL01-P3MAD-240179 | 1143 | [STEAM TURBINE] I/O LIST FOR VMS (BLOCK #3,4) | FI | 2020-08-14 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2025-01-14 | MTW-G-C-LT-25.6118.0 | AB | Z0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YL13-P2CJJ-240061 | 1144 | [STEAM TURBINE] SIGNAL TRANSFER LIST BETWEEN TCS AND DCS - HARDWIRE (BLOCK #2) | FI | 2018-03-11 |  | 2018-08-29 | 2018-10-19 | MRT-DS-REC-TT-180592-FC | FC | 0 | 2018-10-26 | 180592-FC STAMPED | FC | 0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YL13-P3CJJ-240061 | 1145 | [STEAM TURBINE] SIGNAL TRANSFER LIST BETWEEN TCS AND DCS (BLOCK #3, 4) | FI | 2018-03-11 |  | 2018-08-29 | 2018-10-19 | MRT-DS-REC-TT-180592-FC | FC | 0 | 2018-10-26 | 180592-FC STAMPED | FC | 0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YS01-P2CJJ-240051 | 1146 | [STEAM TURBINE] CONSUMER SCHEMES FOR I&C (BLOCK #2) | FI | 2020-07-14 |  | 2020-07-14 | 2020-07-14 | MRT-DS-REC-TT-200060-FC | FI | 0 | 2020-07-20 | 200060-FC STAMPED | FI | 0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YS01-P3CJJ-240051 | 1147 | [STEAM TURBINE] CONSUMER SCHEMES FOR I&C (BLOCK #3,4) | FI | 2020-08-14 |  | 2020-08-25 | 2020-08-26 | MRT-DS-REC-TT-200066-FC | FI | 0 | 2020-08-26 | 200066-FC STAMPED | FI | 0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YL00-P2CJJ-240052 | 1148 | [STEAM TURBINE] MEASUREMENT LIST (BLOCK #2) | FI | 2019-02-18 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-04-11 | 190037-FC STAMPED | FC | 0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YL00-P3CJJ-240052 | 1149 | [STEAM TURBINE] MEASUREMENT LIST (BLOCK #3,4) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YL00-P2CJJ-240053 | 1150 | [STEAM TURBINE] CONSUMER LIST FOR I&C (BLOCK #2) | FI | 2020-07-14 |  | 2020-07-14 | 2020-07-14 | MRT-DS-REC-TT-200060-FC | FI | 0 | 2020-07-20 | 200060-FC STAMPED | FI | 0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YL00-P3CJJ-240053 | 1151 | [STEAM TURBINE] CONSUMER LIST FOR I&C (BLOCK #3,4) | FI | 2020-08-14 |  | 2020-08-25 | 2020-08-26 | MRT-DS-REC-TT-200066-FC | FI | 0 | 2020-08-26 | 200066-FC STAMPED | FI | 0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YL08-P2CJJ-240068 | 1152 | [STEAM TURBINE] TRIPS & ALARMS SETTING (BLOCK #2) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-12-03 | 200084-FC STAMPED | FC | 1 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YL08-P3CJJ-240068 | 1153 | [STEAM TURBINE] TRIPS & ALARMS SETTING (BLOCK #3,4) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YT02-P2CJJ-240120 | 1154 | [STEAM TURBINE] INSTRUMENTATION DATA SHEETS (BLOCK #2) | FI | 2018-06-03 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-03-18 | 180759-FC STAMPED | FC | 0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YT02-P3CJJ-240112 | 1155 | [STEAM TURBINE] INSTRUMENTATION DATA SHEETS (BLOCK #3, 4) | FI | 2018-06-03 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YT02-P2MAD-240167 | 1156 | [STEAM TURBINE] INSTRUMENTATION DATA SHEETS FOR VMS (BLOCK #2) | FI | 2020-07-09 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-07-09 | 200058-FC STAMPED | FI | 0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YT02-P3MAD-240177 | 1157 | [STEAM TURBINE] INSTRUMENTATION DATA SHEETS FOR VMS (BLOCK #3,4) | FI | 2019-09-01 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YD00-P2CJA-240057 | 1158 | [STEAM TURBINE] I&C LAYOUTS +3.10M (BLOCK #2) | FI | 2018-08-30 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-08-23 | 19019-FC STAMPED | FC | 3 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YD00-P2CJA-240058 | 1159 | [STEAM TURBINE] I&C LAYOUTS +9.10M (BLOCK #2) | FI | 2018-08-30 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-08-23 | 19019-FC STAMPED | FC | 3 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YD00-P2CJA-240059 | 1160 | [STEAM TURBINE] I&C LAYOUTS +14.60M (BLOCK #2) | FI | 2018-08-30 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-08-23 | 19019-FC STAMPED | FC | 3 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YD00-P3CJA-240057 | 1161 | [STEAM TURBINE] I&C LAYOUTS +3.10M (BLOCK #3,4) | FI | 2018-08-30 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YD00-P3CJA-240058 | 1162 | [STEAM TURBINE] I&C LAYOUTS +9.10M (BLOCK #3,4) | FI | 2018-08-30 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YD00-P3CJA-240059 | 1163 | [STEAM TURBINE] I&C LAYOUTS +14.60M (BLOCK #3,4) | FI | 2018-08-30 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2025-01-14 | MTW-G-C-LT-25.6118.0 | AB | Z0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YK00-P2CJJ-240049 | 1164 | [STEAM TURBINE] HOOK-UPS FOR I&C (BLOCK #2) | FI | 2020-07-14 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-07-20 | 200060-FC STAMPED | FI | 0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YK00-P2CJJ-240119 | 1165 | [STEAM TURBINE] HOOK-UPS FOR FIELD INSTRUMENTATION (BLOCK #2) | FA | 2019-02-12 | 2019-04-30 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-04-08 | 190032-FC STAMPED | FC | 0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YK00-P3CJJ-240049 | 1166 | [STEAM TURBINE] HOOK-UPS FOR I&C (BLOCK #3,4) | FI | 2020-08-14 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YK00-P3CJJ-240111 | 1167 | [STEAM TURBINE] HOOK-UPS FOR FIELD INSTRUMENTATION (BLOCK #3,4) | FA | 2019-02-12 | 2019-04-30 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XT00-P2MAA-220002 | 1168 | [STEAM TURBINE] STEAM TURBINE FOUNDATION EMBEDDED ELEMENTS FOR INSTALLATION (BLOCK #2) | FI | 2017-11-19 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-06-10 | 200049-FC STAMPED | FC | 2 | A | CIVIL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-XT00-P3MAA-220002 | 1169 | [STEAM TURBINE] STEAM TURBINE FOUNDATION EMBEDDED ELEMENTS FOR INSTALLATION (BLOCK #3,4) | FI | 2017-11-19 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-21 | MTW-AS-C-LT-24.5089.0 | AB | Z0 | A | CIVIL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CA07-P2MAA-220003 | 1170 | [STEAM TURBINE] STG FOUNDATION - DESIGN CRITERIA (BLOCK #2) | FI | 2017-10-22 |  | 2017-10-31 | 2017-11-03 | MRT-DS-PLNE-TT-170052 | FI | 0 | 2017-11-21 | 20.027/E04/PLNE/XI/2017 | FI | 0 | I | CIVIL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CA07-P3MAA-220003 | 1171 | [STEAM TURBINE] STG FOUNDATION - DESIGN CRITERIA (BLOCK #3, 4) | FI | 2017-11-19 |  | 2017-11-07 | 2017-11-09 | MRT-DS-PLNE-TT-170060 | FI | 0 | 2017-11-20 | 20.005/E04/PLNE/XI/2017 | FI | 0 | I | CIVIL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-VL00-P2MAA-220001 | 1172 | [STEAM TURBINE] STG FOUNDATION SHAPE - PLANS PART1 FOR INSTALLATION (BLOCK #2) | FI | 2017-10-08 |  | 2019-02-22 | 2019-02-26 | MRT-DS-REC-TT-190033-FC | FC | 2 | 2019-02-26 | 190033-FC STAMPED | FC | 2 | A | CIVIL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-VL00-P3MAA-220001 | 1173 | [STEAM TURBINE] STG FOUNDATION SHAPE - PLANS FOR INSTALLATION (BLOCK #3, 4) | FI | 2017-11-05 |  | 2019-02-22 | 2019-02-26 | MRT-DS-REC-TT-190033-FC | FC | 2 | 2019-02-26 | 190033-FC STAMPED | FC | 2 | A | CIVIL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-VL00-P2MAA-220009 | 1174 | [STEAM TURBINE] STG FOUNDATION SHAPE - SECTIONS FOR INSTALLATION (BLOCK #2) | FI | 2017-10-08 |  | 2019-01-07 | 2019-01-07 | MRT-DS-REC-TT-190003-FC | FC | 1 | 2019-01-07 | 190003-FC STAMPED | FC | 1 | A | CIVIL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-VL00-P3MAA-220009 | 1175 | [STEAM TURBINE] STG FOUNDATION SHAPE - SECTIONS FOR INSTALLATION (BLOCK #3,4) | FI | 2017-11-05 |  | 2019-01-14 | 2019-01-14 | MRT-DS-REC-TT-190005-FC | FC | 1 | 2019-01-14 | 190005-FC STAMPED | FC | 1 | A | CIVIL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-VL00-P2MAA-220010 | 1176 | [STEAM TURBINE] STG FOUNDATION - DIRECTIVES FOR CIVIL WORK FOR INSTALLATION (BLOCK #2) | FI | 2017-10-08 |  | 2019-01-07 | 2019-01-07 | MRT-DS-REC-TT-190003-FC | FC | 1 | 2019-01-07 | 190003-FC STAMPED | FC | 1 | A | CIVIL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-VL00-P3MAA-220010 | 1177 | [STEAM TURBINE] STG FOUNDATION - DIRECTIVES FOR CIVIL WORK FOR INSTALLATION (BLOCK #3,4) | FI | 2017-11-05 |  | 2019-01-14 | 2019-01-14 | MRT-DS-REC-TT-190005-FC | FC | 1 | 2019-01-14 | 190005-FC STAMPED | FC | 1 | A | CIVIL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-UF00-P2MAA-220023 | 1178 | [STEAM TURBINE] STG FOUNDATION LOAD PLAN (BLOCK #2) | FI | 2017-10-08 |  | 2020-12-03 | 2020-12-03 | MRT-DS-REC-TT-200084-FC | FC | 1 | 2020-12-03 | 200084-FC STAMPED | FC | 1 | A | CIVIL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-UF00-P3MAA-220023 | 1179 | [STEAM TURBINE] STG FOUNDATION LOAD PLAN (BLOCK #3, 4) | FI | 2017-11-05 |  | 2019-03-04 | 2019-03-04 | MRT-DS-REC-TT-190062 | FI | 1 | 2019-04-04 | 193/T/MRT/REC/IV/2019 | FI | 1 | I | CIVIL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YD00-P2MAA-220025 | 1180 | [STEAM TURBINE] STG FOUNDATION LOAD PLAN - EQUIPMENT - LEVELS +3,10M (BLOCK #2) | FI | 2018-01-15 |  | 2018-04-16 | 2018-04-16 | MRT-DS-REC-TT-180312 | FI | 0 | 2018-06-29 | 452/T/MRT/REC/VI/2018 | FI | 0 | I | CIVIL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YD00-P3MAA-220025 | 1181 | [STEAM TURBINE] STG FOUNDATION LOAD PLAN - EQUIPMENT - LEVELS +3,10M (BLOCK #3,4) | FI | 2018-01-15 |  | 2018-04-16 | 2018-04-16 | MRT-DS-REC-TT-180312 | FI | 0 | 2018-06-29 | 452/T/MRT/REC/VI/2018 | FI | 0 | I | CIVIL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YD00-P2MAA-220026 | 1182 | [STEAM TURBINE] STG FOUNDATION LOAD PLAN - EQUIPMENT - LEVELS +9,10M (BLOCK #2) | FI | 2018-01-15 |  | 2019-04-08 | 2019-04-08 | MRT-DS-REC-TT-190067 | FI | 1 | 2019-04-10 | 211/T/MRT/REC/IV/2019 | FI | 1 | I | CIVIL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YD00-P3MAA-220026 | 1183 | [STEAM TURBINE] STG FOUNDATION LOAD PLAN - EQUIPMENT - LEVELS +9,10M (BLOCK #3,4) | FI | 2018-01-15 |  | 2019-04-08 | 2019-04-08 | MRT-DS-REC-TT-190067 | FI | 1 | 2019-04-10 | 211/T/MRT/REC/IV/2019 | FI | 1 | I | CIVIL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YD00-P2MAA-220027 | 1184 | [STEAM TURBINE] STG FOUNDATION LOAD PLAN - EQUIPMENT - LEVELS +14,60M (BLOCK #2) | FI | 2018-01-15 |  | 2019-04-08 | 2019-04-08 | MRT-DS-REC-TT-190067 | FI | 1 | 2019-04-10 | 211/T/MRT/REC/IV/2019 | FI | 1 | I | CIVIL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YD00-P3MAA-220027 | 1185 | [STEAM TURBINE] STG FOUNDATION LOAD PLAN - EQUIPMENT - LEVELS +14,60M (BLOCK #3,4) | FI | 2018-01-15 |  | 2019-04-08 | 2019-04-08 | MRT-DS-REC-TT-190067 | FI | 1 | 2019-04-10 | 211/T/MRT/REC/IV/2019 | FI | 1 | I | CIVIL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YD00-P2MAA-220030 | 1186 | [STEAM TURBINE] STG FOUNDATION LOAD PLAN - PENETRATION PLAN - LEVELS +9,10M (BLOCK #2) | FI | 2017-10-08 |  | 2019-02-01 | 2019-02-01 | MRT-DS-REC-TT-190028 | FI | 1 | 2019-03-06 | 104/T/MRT/REC/III/2019 | FI | 1 | I | CIVIL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YD00-P3MAA-220031 | 1187 | [STEAM TURBINE] STG FOUNDATION LOAD PLAN - PENETRATION PLAN - LEVELS +9,10M (BLOCK #3,4) | FI | 2017-11-05 |  | 2019-10-28 | 2019-10-28 | MRT-DS-REC-TT-190217-FC | FC | 2 | 2019-10-28 | 190217-FC STAMPED | FC | 2 | A | CIVIL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YD00-P2MAA-220031 | 1188 | [STEAM TURBINE] STG FOUNDATION LOAD PLAN - PENETRATION PLAN - LEVELS +14,60M (BLOCK #2) | FI | 2017-10-08 |  | 2020-12-03 | 2020-12-03 | MRT-DS-REC-TT-200084-FC | FC | 2 | 2020-12-03 | 200084-FC STAMPED | FC | 2 | A | CIVIL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-YD00-P3MAA-220030 | 1189 | [STEAM TURBINE] STG FOUNDATION LOAD PLAN - PENETRATION PLAN - LEVELS +14,60M (BLOCK #3,4) | FI | 2017-11-05 |  | 2019-10-28 | 2019-10-28 | MRT-DS-REC-TT-190217-FC | FC | 2 | 2019-10-28 | 190217-FC STAMPED | FC | 2 | A | CIVIL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-VL00-P2MAA-220079 | 1190 | [STEAM TURBINE] STG FOUNDATION SHAPE - PLANS PART2 FOR INSTALLATION (BLOCK #2) | FI | 2019-01-04 |  | 2019-01-07 | 2019-01-07 | MRT-DS-REC-TT-190003-FC | FC | 0 | 2019-01-07 | 190003-FC STAMPED | FC | 0 | A | CIVIL | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAA-220134 | 1191 | [STEAM TURBINE] INITIAL SPECIFICATION FOR STEAM TURBINE INSTALLATION (BLOCK 2) | FI | 2018-11-23 |  | 2018-12-19 | 2018-12-19 | MRT-DS-REC-TT-180921-FC | FC | 0 | 2018-12-22 | 180921-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAA-220133 | 1192 | [STEAM TURBINE] INITIAL SPECIFICATION FOR STEAM TURBINE INSTALLATION (BLOCK 3,4) | FI | 2018-11-23 |  | 2018-12-19 | 2018-12-19 | MRT-DS-REC-TT-180921-FC | FC | 0 | 2018-12-22 | 180921-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-QA00-P2MAA-220210 | 1193 | [STEAM TURBINE] MEASUREMENT PROTOCOLS FOR TURBINE FOR INSTALLATION (BLOCK #2) | FI | 2019-05-29 |  | 2019-06-26 | 2019-06-27 | MRT-DS-REC-TT-190138-FC | FC | 0 | 2019-06-27 | 190138-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-QA00-P3MAA-220210 | 1194 | [STEAM TURBINE] MEASUREMENT PROTOCOLS FOR TURBINE FOR INSTALLATION (BLOCK #3,4) | FI | 2019-05-29 |  | 2019-06-26 | 2019-06-27 | MRT-DS-REC-TT-190138-FC | FC | 0 | 2019-06-27 | 190138-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAA-220165 | 1195 | [STEAM TURBINE] INSTRUCTION FOR STEAM TURBINE ASSEMBLY (BLOCK 2) | FI | 2018-11-23 |  | 2019-01-02 | 2019-01-03 | MRT-DS-REC-TT-180920-FC | FC | 0 | 2019-01-07 | 180920-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAA-220174 | 1196 | [STEAM TURBINE] INSTRUCTION FOR STEAM TURBINE ASSEMBLY (BLOCK 3,4) | FI | 2018-12-14 |  | 2019-05-31 | 2019-06-18 | MRT-DS-REC-TT-190131-FC | FC | I | 2019-06-19 | 190131-FC STAMPED | FC | I | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAA-220166 | 1197 | [STEAM TURBINE] MAIN ASSEMBLY MANUAL (BLOCK 2) | FI | 2018-11-23 |  | 2019-01-02 | 2019-01-03 | MRT-DS-REC-TT-180920-FC | FC | 0 | 2019-01-07 | 180920-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAA-220175 | 1198 | [STEAM TURBINE] MAIN ASSEMBLY MANUAL (BLOCK 3,4) | FI | 2018-12-14 |  | 2019-06-26 | 2019-07-01 | MRT-DS-REC-TT-190130-FC | FC | 0 | 2019-07-01 | 190130-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAA-220193 | 1199 | [STEAM TURBINE] ASSEMBLY MANUAL FOR AUXILIARY STEEL STRUCTURES (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAA-220193 | 1200 | [STEAM TURBINE] ASSEMBLY MANUAL FOR AUXILIARY STEEL STRUCTURES (BLOCK #3,4) | FI | 2019-07-24 |  | 2019-09-09 | 2019-09-09 | MRT-DS-REC-TT-190166-FC | FC | 0 | 2019-09-09 | 190166-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2LBS-220087 | 1201 | [STEAM TURBINE] ASSEMBLY MANUAL FOR BUTTERFLY VALVE (BLOCK #2) | FI | 2019-02-20 |  | 2019-05-31 | 2019-06-18 | MRT-DS-REC-TT-190131-FC | FC | I | 2019-06-19 | 190131-FC STAMPED | FC | I | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3LBA-220083 | 1202 | [STEAM TURBINE] ASSEMBLY MANUAL FOR BUTTERFLY VALVE (BLOCK #3,4) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2CJJ-240114 | 1203 | [STEAM TURBINE] ASSEMBLY MANUAL FOR CONTROL SYSTEM (BLOCK #2) | FI | 2019-02-20 |  | 2019-04-01 | 2019-04-12 | MRT-DS-REC-TT-190042-FC | FC | 0 | 2019-04-12 | 190042-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3CJJ-240106 | 1204 | [STEAM TURBINE] ASSEMBLY MANUAL FOR CONTROL SYSTEM (BLOCK #3,4) | FI | 2019-09-01 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAA-220152 | 1205 | [STEAM TURBINE] ASSEMBLY MANUAL FOR EXPANDERS HEX (BLOCK #2) | FI | 2019-02-20 |  | 2019-04-01 | 2019-04-12 | MRT-DS-REC-TT-190042-FC | FC | 0 | 2019-04-12 | 190042-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAA-220161 | 1206 | [STEAM TURBINE] ASSEMBLY MANUAL FOR EXPANDERS HEX (BLOCK #3,4) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053 | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAV-220105 | 1207 | [STEAM TURBINE] ASSEMBLY MANUAL FOR EXPANSION JOINT (BLOCK #2) | FI | 2019-09-01 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAV-220097 | 1208 | [STEAM TURBINE] ASSEMBLY MANUAL FOR EXPANSION JOINT (BLOCK #3,4) | FI | 2019-03-04 |  | 2019-04-05 | 2019-04-11 | MRT-DS-REC-TT-190062-FC | FC | 0 | 2019-04-11 | 190062-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2CJJ-240123 | 1209 | [STEAM TURBINE] ASSEMBLY MANUAL FOR FIELD INSTRUMENTATION (BLOCK #2) | FI | 2019-02-20 |  | 2019-04-01 | 2019-04-12 | MRT-DS-REC-TT-190042-FC | FC | 0 | 2019-04-12 | 190042-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3CJJ-240115 | 1210 | [STEAM TURBINE] ASSEMBLY MANUAL FOR FIELD INSTRUMENTATION (BLOCK #3,4) | FI | 2019-09-01 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAK-220082 | 1211 | [STEAM TURBINE] ASSEMBLY MANUAL FOR GEARBOX (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAX-220096 | 1212 | [STEAM TURBINE] ASSEMBLY MANUAL FOR HPH OIL SYSTEM (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAX-220145 | 1213 | [STEAM TURBINE] ASSEMBLY MANUAL FOR HPH OIL SYSTEM (BLOCK #3,4) | FI | 2019-03-04 |  | 2019-04-05 | 2019-04-11 | MRT-DS-REC-TT-190062-FC | FC | 0 | 2019-04-11 | 190062-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAV-220161 | 1214 | [STEAM TURBINE] ASSEMBLY MANUAL FOR HYDRAULIC BLOCK OF JACKING OIL (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAV-220170 | 1215 | [STEAM TURBINE] ASSEMBLY MANUAL FOR HYDRAULIC BLOCK OF JACKING OIL (BLOCK #3,4) | FI | 2019-09-01 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAV-240136 | 1216 | [STEAM TURBINE] ASSEMBLY MANUAL FOR INTEGRATED OIL SYSTEM (BLOCK #2) | FI | 2019-09-01 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAV-240135 | 1217 | [STEAM TURBINE] ASSEMBLY MANUAL FOR INTEGRATED OIL SYSTEM (BLOCK #3,4) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2LBA-220130 | 1218 | [STEAM TURBINE] ASSEMBLY MANUAL FOR LP STRAINER (BLOCK #2) | FI | 2019-02-20 |  | 2019-04-01 | 2019-04-12 | MRT-DS-REC-TT-190042-FC | FC | 0 | 2019-04-12 | 190042-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3LBA-220129 | 1219 | [STEAM TURBINE] ASSEMBLY MANUAL FOR LP STRAINER (BLOCK #3,4) | FI | 2019-03-04 |  | 2019-04-05 | 2019-04-11 | MRT-DS-REC-TT-190062-FC | FC | 0 | 2019-04-11 | 190062-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2LBS-220090 | 1220 | [STEAM TURBINE] ASSEMBLY MANUAL FOR NON RETURN EXTRACTION FLAPS (BLOCK #2) | FI | 2019-02-20 |  | 2019-04-01 | 2019-04-12 | MRT-DS-REC-TT-190042-FC | FC | 0 | 2019-04-12 | 190042-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3LBC-220086 | 1221 | [STEAM TURBINE] ASSEMBLY MANUAL FOR NON RETURN EXTRACTION FLAPS (BLOCK #3,4) | FI | 2020-08-25 |  | 2020-08-26 | 2020-09-03 | MRT-DS-REC-TT-200068-FC | FI | 0 | 2020-09-03 | 200068-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAV-220101 | 1222 | [STEAM TURBINE] ASSEMBLY MANUAL FOR OIL CLEANING UNIT (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAV-220093 | 1223 | [STEAM TURBINE] ASSEMBLY MANUAL FOR OIL CLEANING UNIT (BLOCK #3,4) | FI | 2019-09-01 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAA-220178 | 1224 | [STEAM TURBINE] ASSEMBLY MANUAL FOR PIPELINE SUPPORTS (BLOCK #2) | FI | 2020-06-22 |  | 2020-06-22 | 2020-06-24 | MRT-DS-REC-TT-200050 | FI | 0 | 2020-06-24 | 200050-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAA-220189 | 1225 | [STEAM TURBINE] ASSEMBLY MANUAL FOR PIPELINE SUPPORTS (BLOCK #3,4) | FI | 2019-09-01 |  | 2020-06-22 | 2020-06-24 | MRT-DS-REC-TT-200050 | FC | 1 | 2020-06-24 | 200050-FC STAMPED | FC | 1 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAA-230180 | 1226 | [STEAM TURBINE] ASSEMBLY MANUAL FOR ROTOR GROUNDING (BLOCK #2) | FI | 2019-09-01 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAA-230191 | 1227 | [STEAM TURBINE] ASSEMBLY MANUAL FOR ROTOR GROUNDING (BLOCK #3,4) | FI | 2019-09-01 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAW-220158 | 1228 | [STEAM TURBINE] ASSEMBLY MANUAL FOR STEAM COOLERS (BLOCK #2) | FI | 2019-09-01 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAW-220167 | 1229 | [STEAM TURBINE] ASSEMBLY MANUAL FOR STEAM COOLERS (BLOCK #3,4) | FI | 2019-09-01 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAA-220155 | 1230 | [STEAM TURBINE] ASSEMBLY MANUAL FOR STEAM TRAPS (BLOCK #2) | FI | 2019-02-20 |  | 2019-04-01 | 2019-04-12 | MRT-DS-REC-TT-190042-FC | FC | 0 | 2019-04-12 | 190042-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAA-220164 | 1231 | [STEAM TURBINE] ASSEMBLY MANUAL FOR STEAM TRAPS (BLOCK #3,4) | FI | 2019-09-01 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAA-220131 | 1232 | [STEAM TURBINE] ASSEMBLY MANUAL FOR STEAM WATER VALVES (BLOCK #2) | FI | 2019-02-20 |  | 2021-08-24 | 2021-08-24 | MRT-DS-REC-TT-210048 | FC | 1 | 2019-04-12 | 190042-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAA-220130 | 1233 | [STEAM TURBINE] ASSEMBLY MANUAL FOR STEAM WATER VALVES (BLOCK #3,4) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAA-240158 | 1234 | [STEAM TURBINE] ASSEMBLY MANUAL FOR SYNCHR. SYSTEM OF TURNING GEAR (BLOCK #3,4) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAA-220199 | 1235 | [STEAM TURBINE] ASSEMBLY MANUAL FOR THERMAL INSULATION OF TURBINE (BLOCK #2) | FI | 2019-03-14 |  | 2020-05-08 | 2020-05-20 | MRT-DS-REC-TT-200041-FC | FC | 1 | 2020-05-20 | 200041-FC STAMPED | FC | 1 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAA-220199 | 1236 | [STEAM TURBINE] ASSEMBLY MANUAL FOR THERMAL INSULATION OF TURBINE (BLOCK #3,4) | FI | 2019-03-14 |  | 2020-05-08 | 2020-05-20 | MRT-DS-REC-TT-200041-FC | FC | 1 | 2020-05-20 | 200041-FC STAMPED | FC | 1 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAW-220108 | 1237 | [STEAM TURBINE] ASSEMBLY MANUAL FOR VALVES - CONTROL (BLOCK #2) | FI | 2019-09-01 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAW-220100 | 1238 | [STEAM TURBINE] ASSEMBLY MANUAL FOR VALVES - CONTROL (BLOCK #3,4) | FI | 2019-09-01 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAD-240172 | 1239 | [STEAM TURBINE] ASSEMBLY MANUAL FOR VMS (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAD-240182 | 1240 | [STEAM TURBINE] ASSEMBLY MANUAL FOR VMS (BLOCK #3,4) | FI | 2019-09-01 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAM-220141 | 1241 | [STEAM TURBINE] ASSEMBLY MANUAL FOR VSC - HEX (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAM-220139 | 1242 | [STEAM TURBINE] ASSEMBLY MANUAL FOR VSC - HEX (BLOCK #3,4) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DN05-P2CJJ-240115 | 1243 | [STEAM TURBINE] COMMISSIONING MANUAL FOR CONTROL SYSTEM (BLOCK #2) | FA | 2019-12-31 | 2020-02-29 | 2020-04-02 | 2020-04-02 | MRT-DS-REC-TT-200034 | FC | 1 | 2023-01-30 | MTW-CS-OM-LT-23.3599.0 | FC | 1 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DN05-P3CJJ-240107 | 1244 | [STEAM TURBINE] COMMISSIONING MANUAL FOR CONTROL SYSTEM (BLOCK #3,4) | FA | 2019-12-31 | 2020-02-29 | 2020-04-02 | 2020-04-02 | MRT-DS-REC-TT-200034 | FC | 1 | 2023-01-30 | MTW-CS-OM-LT-23.3599.0 | FC | 1 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DN05-P2CJJ-240124 | 1245 | [STEAM TURBINE] COMMISSIONING MANUAL FOR FIELD INSTRUMENTATION (BLOCK #2) | FA | 2019-12-31 | 2020-02-29 | 2020-04-02 | 2020-04-02 | MRT-DS-REC-TT-200034 | FC | 1 | 2023-01-30 | MTW-CS-OM-LT-23.3599.0 | FC | 1 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DN05-P3CJJ-240116 | 1246 | [STEAM TURBINE] COMMISSIONING MANUAL FOR FIELD INSTRUMENTATION (BLOCK #3,4) | FA | 2019-12-31 | 2020-02-29 | 2020-04-02 | 2020-04-02 | MRT-DS-REC-TT-200034 | FC | 1 | 2023-01-30 | MTW-CS-OM-LT-23.3599.0 | FC | 1 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DN05-P2MAX-220097 | 1247 | [STEAM TURBINE] COMMISSIONING MANUAL FOR HPH OIL SYSTEM (BLOCK #2) | FA | 2020-06-30 |  | 2020-06-29 | 2020-06-29 | MRT-DS-REC-TT-200055 | FA | 0 | 2023-01-30 | MTW-CS-OM-LT-23.3598.0 | FA | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DN05-P3MAX-220146 | 1248 | [STEAM TURBINE] COMMISSIONING MANUAL FOR HPH OIL SYSTEM (BLOCK #3,4) | FA | 2019-12-31 | 2020-02-29 | 2023-10-19 | 2023-10-19 | MRT-DS-REC-TT-230015 | FC | 2 | 2023-11-19 | DEEMED APPROVAL | FC | 2 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DN05-P2MAV-220162 | 1249 | [STEAM TURBINE] COMMISSIONING MANUAL FOR HYDRAULIC BLOCK OF JACKING OIL (BLOCK #2) | FA | 2020-06-30 |  | 2020-06-29 | 2020-06-29 | MRT-DS-REC-TT-200055 | FA | 0 | 2023-01-30 | MTW-CS-OM-LT-23.3598.0 | FA | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DN05-P3MAV-220171 | 1250 | [STEAM TURBINE] COMMISSIONING MANUAL FOR HYDRAULIC BLOCK OF JACKING OIL (BLOCK #3,4) | FA | 2019-12-31 | 2020-02-29 | 2023-10-19 | 2023-10-19 | MRT-DS-REC-TT-230015 | FC | 1 | 2023-11-19 | DEEMED APPROVAL | FC | 1 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DN05-P2MAV-240137 | 1251 | [STEAM TURBINE] COMMISSIONING MANUAL FOR INTEGRATED OIL SYSTEM (BLOCK #2) | FA | 2019-12-31 | 2020-02-29 | 2020-04-02 | 2020-04-02 | MRT-DS-REC-TT-200034 | FC | 1 | 2023-01-30 | MTW-CS-OM-LT-23.3599.0 | FC | 1 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DN05-P3MAV-240136 | 1252 | [STEAM TURBINE] COMMISSIONING MANUAL FOR INTEGRATED OIL SYSTEM (BLOCK #3,4) | FA | 2019-12-31 | 2020-02-29 | 2020-04-02 | 2020-04-02 | MRT-DS-REC-TT-200034 | FC | 1 | 2023-01-30 | MTW-CS-OM-LT-23.3599.0 | FC | 1 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DN05-P2MAV-220102 | 1253 | [STEAM TURBINE] COMMISSIONING MANUAL FOR OIL CLEANING UNIT (BLOCK #2) | FA | 2020-06-30 |  | 2020-06-29 | 2020-06-29 | MRT-DS-REC-TT-200055 | FA | 0 | 2023-01-30 | MTW-CS-OM-LT-23.3598.0 | FA | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DN05-P3MAV-220094 | 1254 | [STEAM TURBINE] COMMISSIONING MANUAL FOR OIL CLEANING UNIT (BLOCK #3,4) | FA | 2019-12-31 | 2020-02-29 | 2023-10-19 | 2023-10-19 | MRT-DS-REC-TT-230015 | FC | 2 | 2023-11-19 | DEEMED APPROVAL | FC | 2 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DN05-P2MAA-220205 | 1255 | [STEAM TURBINE] COMMISSIONING MANUAL FOR STEAM TURBINE AND ACCESSORIES (BLOCK 2) | FA | 2018-12-14 | 2019-02-15 | 2019-07-09 | 2019-07-12 | MRT-DS-REC-TT-190139-FC | FC | 1 | 2021-01-14 | 001/SER.00.01/LE/2021 | FC | 1 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DN05-P3MAA-220205 | 1256 | [STEAM TURBINE] COMMISSIONING MANUAL FOR STEAM TURBINE AND ACCESSORIES (BLOCK 3,4) | FA | 2019-02-15 | 2019-04-12 | 2019-07-26 | 2019-08-02 | MRT-DS-REC-TT-190157-FC | FC | 0 | 2021-01-14 | 001/SER.00.01/LE/2021 | FC | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DN05-P2MAD-240173 | 1257 | [STEAM TURBINE] COMMISSIONING MANUAL FOR VMS (BLOCK #2) | FA | 2020-06-30 |  | 2020-06-29 | 2020-06-29 | MRT-DS-REC-TT-200055 | FA | 0 | 2023-01-30 | MTW-CS-OM-LT-23.3598.0 | FA | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DN05-P3MAD-240183 | 1258 | [STEAM TURBINE] COMMISSIONING MANUAL FOR VMS (BLOCK #3,4) | FA | 2019-12-31 | 2020-02-29 | 2020-04-02 | 2020-04-02 | MRT-DS-REC-TT-200034 | FC | 1 | 2023-01-05 | MTW-CS-OM-LT-23.3450.0 | FC | 1 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DN05-P2MAM-220142 | 1259 | [STEAM TURBINE] COMMISSIONING MANUAL FOR VSC - HEX (BLOCK #2) | FA | 2020-06-30 |  | 2020-06-29 | 2020-06-29 | MRT-DS-REC-TT-200055 | FA | 0 | 2023-01-30 | MTW-CS-OM-LT-23.3598.0 | FA | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-DN05-P3MAM-220140 | 1260 | [STEAM TURBINE] COMMISSIONING MANUAL FOR VSC - HEX (BLOCK #3,4) | FA | 2019-12-31 | 2020-02-29 | 2020-04-02 | 2020-04-02 | MRT-DS-REC-TT-200034 | FC | 1 | 2023-01-30 | MTW-CS-OM-LT-23.3599.0 | FC | 1 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAA-220201 | 1261 | [STEAM TURBINE] OPERATION INSTRUCTION FOR STEAM TURBINE (BLOCK 2) | FI | 2018-12-14 |  | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220045 | FC | 3 | 2023-01-21 | DEEMED APPROVAL | FC | 3 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAA-220201 | 1262 | [STEAM TURBINE] OPERATION INSTRUCTION FOR STEAM TURBINE (BLOCK 3,4) | FI | 2019-02-15 |  | 2020-12-03 | 2020-12-03 | MRT-DS-REC-TT-200084-FC | FC | 1 | 2020-12-03 | 200084-FC STAMPED | FC | 1 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAA-220202 | 1263 | [STEAM TURBINE] MAINTENANCE INSTRUCTION FOR STEAM TURBINE (BLOCK 2) | FI | 2018-12-14 |  | 2019-07-26 | 2019-08-02 | MRT-DS-REC-TT-190157-FC | FC | 0 | 2019-08-02 | 190157-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAA-220202 | 1264 | [STEAM TURBINE] MAINTENANCE INSTRUCTION FOR STEAM TURBINE (BLOCK 3,4) | FI | 2019-02-15 |  | 2019-09-09 | 2019-09-09 | MRT-DS-REC-TT-190166-FC | FC | 0 | 2019-09-09 | 190166-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAA-220203 | 1265 | [STEAM TURBINE] SUMMARY OPERATION AND MAINTENANCE INSTRUCTIONS (BLOCK #2) | FI | 2020-07-14 |  | 2020-07-14 | 2020-07-14 | MRT-DS-REC-TT-200060-FC | FI | 0 | 2020-07-20 | 200060-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAA-220203 | 1266 | [STEAM TURBINE] SUMMARY OPERATION AND MAINTENANCE INSTRUCTIONS (BLOCK #3,4) | FI | 2020-08-14 |  | 2020-08-25 | 2020-08-26 | MRT-DS-REC-TT-200066-FC | FI | 0 | 2020-08-26 | 200066-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2CJJ-240116 | 1267 | [STEAM TURBINE] O&M MANUAL FOR CONTROL SYSTEM (BLOCK #2) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3CJJ-240108 | 1268 | [STEAM TURBINE] O&M MANUAL FOR CONTROL SYSTEM (BLOCK #3,4) | FI | 2020-08-14 |  | 2020-08-25 | 2020-08-26 | MRT-DS-REC-TT-200066-FC | FI | 0 | 2020-08-26 | 200066-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAA-220153 | 1269 | [STEAM TURBINE] O&M MANUAL FOR EXPANDERS HEX (BLOCK #2) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAA-220162 | 1270 | [STEAM TURBINE] O&M MANUAL FOR EXPANDERS HEX (BLOCK #3,4) | FI | 2020-08-14 |  | 2020-08-25 | 2020-08-26 | MRT-DS-REC-TT-200066-FC | FI | 0 | 2020-08-26 | 200066-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAV-220106 | 1271 | [STEAM TURBINE] O&M MANUAL FOR EXPANSION JOINT (BLOCK #2) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAV-220098 | 1272 | [STEAM TURBINE] O&M MANUAL FOR EXPANSION JOINT (BLOCK #3,4) | FI | 2020-11-26 |  | 2020-12-03 | 2020-12-03 | MRT-DS-REC-TT-200084-FC | FI | 0 | 2020-12-03 | 200084-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2CJJ-240125 | 1273 | [STEAM TURBINE] O&M MANUAL FOR FIELD INSTRUMENTATION (BLOCK #2) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3CJJ-240117 | 1274 | [STEAM TURBINE] O&M MANUAL FOR FIELD INSTRUMENTATION (BLOCK #3,4) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAK-220084 | 1275 | [STEAM TURBINE] O&M MANUAL FOR GEARBOX (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAX-220098 | 1276 | [STEAM TURBINE] O&M MANUAL FOR HPH OIL SYSTEM (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAX-220147 | 1277 | [STEAM TURBINE] O&M MANUAL FOR HPH OIL SYSTEM (BLOCK #3,4) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAV-220163 | 1278 | [STEAM TURBINE] O&M MANUAL FOR HYDRAULIC BLOCK OF JACKING OIL (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAV-220172 | 1279 | [STEAM TURBINE] O&M MANUAL FOR HYDRAULIC BLOCK OF JACKING OIL (BLOCK #3,4) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAV-240138 | 1280 | [STEAM TURBINE] O&M MANUAL FOR INTEGRATED OIL SYSTEM (BLOCK #2) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAV-240137 | 1281 | [STEAM TURBINE] O&M MANUAL FOR INTEGRATED OIL SYSTEM (BLOCK #3,4) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAV-220103 | 1282 | [STEAM TURBINE] O&M MANUAL FOR OIL CLEANING UNIT (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAV-220095 | 1283 | [STEAM TURBINE] O&M MANUAL FOR OIL CLEANING UNIT (BLOCK #3,4) | FI | 2020-08-14 |  | 2020-08-25 | 2020-08-26 | MRT-DS-REC-TT-200066-FC | FI | 0 | 2020-08-26 | 200066-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAA-240145 | 1284 | [STEAM TURBINE] O&M MANUAL FOR OVER SPEED PROTECTION (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAA-220194 | 1285 | [STEAM TURBINE] O&M MANUAL FOR POK POD DN40 (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAA-220194 | 1286 | [STEAM TURBINE] O&M MANUAL FOR POK POD DN40 (BLOCK #3,4) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAA-230181 | 1287 | [STEAM TURBINE] O&M MANUAL FOR ROTOR GROUNDING (BLOCK #2) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAW-220159 | 1288 | [STEAM TURBINE] O&M MANUAL FOR STEAM COOLERS (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAW-220168 | 1289 | [STEAM TURBINE] O&M MANUAL FOR STEAM COOLERS (BLOCK #3,4) | FI | 2020-08-14 |  | 2020-08-25 | 2020-08-26 | MRT-DS-REC-TT-200066-FC | FI | 0 | 2020-08-26 | 200066-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAA-220156 | 1290 | [STEAM TURBINE] O&M MANUAL FOR STEAM TRAPS (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAA-220165 | 1291 | [STEAM TURBINE] O&M MANUAL FOR STEAM TRAPS (BLOCK #3,4) | FI | 2020-08-25 |  | 2020-08-26 | 2020-09-03 | MRT-DS-REC-TT-200068-FC | FI | 0 | 2020-09-03 | 200068-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAA-240159 | 1292 | [STEAM TURBINE] O&M MANUAL FOR SYNCHR. SYSTEM OF TURNING GEAR (BLOCK #3,4) | FI | 2020-08-14 |  | 2020-08-25 | 2020-08-26 | MRT-DS-REC-TT-200066-FC | FI | 0 | 2020-08-26 | 200066-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2LBS-220088 | 1293 | [STEAM TURBINE] O&M MANUAL FOR VALVES - BUTTERFLY VALVES FOR ISOLATION AND CONTROL (BLOCK #2) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3LBA-220084 | 1294 | [STEAM TURBINE] O&M MANUAL FOR VALVES - BUTTERFLY VALVES FOR ISOLATION AND CONTROL (BLOCK #3,4) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAW-220109 | 1295 | [STEAM TURBINE] O&M MANUAL FOR VALVES - CONTROL (BLOCK #2) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAW-220101 | 1296 | [STEAM TURBINE] O&M MANUAL FOR VALVES - CONTROL (BLOCK #3,4) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAA-220132 | 1297 | [STEAM TURBINE] O&M MANUAL FOR VALVES - STEAM & WATER (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAA-220131 | 1298 | [STEAM TURBINE] O&M MANUAL FOR VALVES - STEAM & WATER (BLOCK #3,4) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAD-240174 | 1299 | [STEAM TURBINE] O&M MANUAL FOR VMS (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAD-240184 | 1300 | [STEAM TURBINE] O&M MANUAL FOR VMS (BLOCK #3,4) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAM-220143 | 1301 | [STEAM TURBINE] O&M MANUAL FOR VSC - HEX (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAM-220141 | 1302 | [STEAM TURBINE] O&M MANUAL FOR VSC - HEX (BLOCK#3,4) | FI | 2020-08-14 |  | 2020-08-25 | 2020-08-26 | MRT-DS-REC-TT-200066-FC | FI | 0 | 2020-08-26 | 200066-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | TG_SKODA | 백운홍 | MRT-CY05-P3CJJ-240109 | 1303 | [STEAM TURBINE] TRAINING MANUAL FOR CONTROL SYSTEM (BLOCK #3,4) | FI | 2020-08-25 |  | 2020-08-26 | 2020-09-03 | MRT-DS-REC-TT-200068-FC | FI | 0 | 2020-09-03 | 200068-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE
DHI | HEX | 이승찬 | MRT-YD00-P0PGB-606000 | 1304 | [CCW HEAD TANK]_GENERAL ARRANGEMENT DRAWING FOR CLOSED COOLING WATER HEAD TANK | FA | 2017-09-29 | 2017-12-29 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-09-04 | 180599-FC STAMPED | FC | 3 | A | MECHANICAL | CCW HEAD TANK
DHI | HEX | 이승찬 | MRT-YD00-P0PGB-606001 | 1305 | [CCW HEAD TANK]_GENERAL ARRANGEMENT DRAWING FOR CLOSED COOLING WATER CHEMICAL DOSING TANK | FA | 2017-09-29 | 2017-12-29 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-10-23 | 180785-FC STAMPED | FC | 4 | A | MECHANICAL | CCW HEAD TANK
DHI | HEX | 이승찬 | MRT-YK08-P2MAG-601001 | 1306 | Condenser #2_General Layout | FA | 2017-08-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-09-21 | 180500-FC STAMPED | FC | 4 | A | MECHANICAL | CONDENSER
DHI | HEX | 이승찬 | MRT-YK08-P2MAG-601002 | 1307 | Condenser #2_General Arrangement | FA | 2017-08-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-09-15 | 180434-FC STAMPED | FC | 3 | A | MECHANICAL | CONDENSER
DHI | HEX | 이승찬 | MRT-XL00-P2MAG-601003 | 1308 | Condenser #2_Connection List | FI | 2017-08-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-09-21 | 180501-FC STAMPED | FC | 4 | A | MECHANICAL | CONDENSER
DHI | HEX | 이승찬 | MRT-XL00-P2MAG-601004 | 1309 | Condenser #2_Connection Detail | FI | 2017-08-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-09-21 | 180501-FC STAMPED | FC | 3 | A | MECHANICAL | CONDENSER
DHI | HEX | 이승찬 | MRT-VL00-P2MAG-601005 | 1310 | Condenser #2_Foundation Assembly | FA | 2017-08-31 | 2017-12-29 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-08-13 | 180168-FC STAMPED | FC | 2 | A | CIVIL | CONDENSER
DHI | HEX | 이승찬 | MRT-VL00-P2MAG-601006 | 1311 | Condenser #2_Foundation Detail | FA | 2017-08-31 | 2017-12-29 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-08-13 | 180168-FC STAMPED | FC | 2 | A | CIVIL | CONDENSER
DHI | HEX | 이승찬 | MRT-YT01-P2MAG-601007 | 1312 | Condenser #2_Data Sheet | FA | 2017-08-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-08-24 | 180557-FC STAMPED | FC | 4 | A | MECHANICAL | CONDENSER
DHI | HEX | 이승찬 | MRT-YT01-P2MAG-601008 | 1313 | Condenser #2_Nozzle Force and Moment | FI | 2017-08-31 |  | 2018-03-09 | 2018-03-09 | MRT-DS-REC-TT-180167 | FI | 2 | 2018-04-03 | 151/T/MRT/REC/IV/2018 | FI | 2 | I | MECHANICAL | CONDENSER
DHI | HEX | 이승찬 | MRT-YT01-P2MAG-601009 | 1314 | Condenser #2_Performance Curves | FI | 2017-08-31 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-02-02 | 02.012/E04/PLNE/II/2018 | FI | 1 | A | MECHANICAL | CONDENSER
DHI | HEX | 이승찬 | MRT-YL00-P2MAG-601010 | 1315 | Condenser #2_Instrument list and Datasheet for Condenser #2 | FA | 2018-05-30 | 2018-07-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-10-16 | 180738-FC STAMPED | FC | 1 | A | I&C | CONDENSER
DHI | HEX | 이승찬 | MRT-CQ02-P2MAG-601011 | 1316 | Condenser #2_Instruction Manuals for Erection, Installation, Operation and Maintenance | FI | 2018-07-31 | 2018-09-30 | 2018-08-27 | 2018-11-09 | MRT-DS-REC-TT-180651-FC | FC | 0 | 2018-11-09 | 180651-FC STAMPED | FC | 0 | A | SUPPORT | CONDENSER
DHI | HEX | 이승찬 | MRT-YK08-P3MAG-602001 | 1317 | Condenser #3,4_General Layout | FA | 2017-08-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | CONDENSER
DHI | HEX | 이승찬 | MRT-YK08-P3MAG-602002 | 1318 | Condenser #3,4_General Arrangement | FA | 2017-08-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | CONDENSER
DHI | HEX | 이승찬 | MRT-XL00-P3MAG-602003 | 1319 | Condenser #3,4_Connection List | FI | 2017-08-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | CONDENSER
DHI | HEX | 이승찬 | MRT-XL00-P3MAG-602004 | 1320 | Condenser #3,4_Connection Detail | FI | 2017-08-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | CONDENSER
DHI | HEX | 이승찬 | MRT-VL00-P3MAG-602005 | 1321 | Condenser #3,4_Foundation Assembly | FA | 2017-08-31 | 2017-12-29 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-08-13 | 180168-FC STAMPED | FC | 2 | A | CIVIL | CONDENSER
DHI | HEX | 이승찬 | MRT-VL00-P3MAG-602006 | 1322 | Condenser #3,4_Foundation Detail | FA | 2017-08-31 | 2017-12-29 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-08-13 | 180168-FC STAMPED | FC | 2 | A | CIVIL | CONDENSER
DHI | HEX | 이승찬 | MRT-YT01-P3MAG-602007 | 1323 | Condenser #3,4_Data Sheet | FA | 2017-08-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | CONDENSER
DHI | HEX | 이승찬 | MRT-YT01-P3MAG-602008 | 1324 | Condenser #3,4_Nozzle Force and Moment | FI | 2017-08-31 |  | 2018-03-09 | 2018-03-09 | MRT-DS-REC-TT-180167 | FI | 2 | 2018-04-03 | 151/T/MRT/REC/IV/2018 | FI | 2 | I | MECHANICAL | CONDENSER
DHI | HEX | 이승찬 | MRT-YT01-P3MAG-602009 | 1325 | Condenser #3,4_Performance Curves | FI | 2017-08-31 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | CONDENSER
DHI | HEX | 이승찬 | MRT-YL00-P3MAG-602010 | 1326 | Condenser #3,4_Instrument list and Datasheet for Condenser #3,4 | FA | 2018-05-30 | 2018-07-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5839.0 | AB | Z0 | A | I&C | CONDENSER
DHI | HEX | 이승찬 | MRT-CQ02-P3MAG-602011 | 1327 | Condenser #3,4_Instruction Manuals for Erection, Installation, Operation and Maintenance | FI | 2018-08-31 | 2018-10-31 | 2018-11-12 | 2018-12-03 | MRT-DS-REC-TT-180807-FC | FC | 0 | 2018-12-08 | 180807-FC STAMPED | FC | 0 | A | SUPPORT | CONDENSER
DHI | HEX | 이승찬 | MRT-YT01-P2PAH-604101 | 1328 | [CTCS & Debris Filter]_Condenser Tube Cleaning System_Technical Data Sheet | FA | 2017-11-17 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-08-27 | 180392-FC STAMPED | FC | 2 | A | MECHANICAL | CONDENSER TUBE CLEANING
DHI | HEX | 이승찬 | MRT-XG02-P2PAH-604102 | 1329 | [CTCS & Debris Filter]_Condenser Tube Cleaning System_P & I Diagram | FA | 2017-10-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-08-23 | 180391-FC STAMPRED | FC | 2 | A | MECHANICAL | CONDENSER TUBE CLEANING
DHI | HEX | 이승찬 | MRT-YK08-P2PAH-604103 | 1330 | [CTCS & Debris Filter]_Condenser Tube Cleaning System_Outline Drawing | FA | 2017-10-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-08-23 | 180391-FC STAMPRED | FC | 2 | A | MECHANICAL | CONDENSER TUBE CLEANING
DHI | HEX | 이승찬 | MRT-YK08-P2PAH-604104 | 1331 | [CTCS & Debris Filter]_Condenser Tube Cleaning System_Outline Drawing for Ball Recirculation unit | FA | 2017-10-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2021-04-27 | 051/T/MRT/REC/IV/2021 | FC | 3 | A | MECHANICAL | CONDENSER TUBE CLEANING
DHI | HEX | 이승찬 | MRT-CQ02-P2PAH-604105 | 1332 | [CTCS & Debris Filter]_O&M Manual For Condenser Tube Cleaning System #2 | FI | 2018-12-14 | 2019-01-14 | 2019-01-24 | 2019-01-24 | MRT-DS-REC-TT-180937-FC | FC | 0 | 2019-01-25 | 180937-FC STAMPED | FC | 0 | A | SUPPORT | CONDENSER TUBE CLEANING
DHI | HEX | 이승찬 | MRT-YT01-P2PBB-604111 | 1333 | [CTCS & Debris Filter]_Debris Filter_Technical Data Sheet | FA | 2017-11-17 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-08-27 | 180392-FC STAMPED | FC | 2 | A | MECHANICAL | CONDENSER TUBE CLEANING
DHI | HEX | 이승찬 | MRT-XG02-P2PBB-604112 | 1334 | [CTCS & Debris Filter]_Debris Filter_P & I Diagram for Block 2 | FA | 2017-10-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-12-10 | 180794-FC STAMPED | FC | 3 | A | MECHANICAL | CONDENSER TUBE CLEANING
DHI | HEX | 이승찬 | MRT-YK08-P2PBB-604113 | 1335 | [CTCS & Debris Filter]_Debris Filter_Outline Drawing | FA | 2017-10-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-08-23 | 180391-FC STAMPRED | FC | 2 | A | MECHANICAL | CONDENSER TUBE CLEANING
DHI | HEX | 이승찬 | MRT-CQ02-P2PBB-604114 | 1336 | [CTCS & Debris Filter]_O&M Manual For Debris Filter #2 | FI | 2018-12-14 | 2019-01-14 | 2019-01-24 | 2019-01-24 | MRT-DS-REC-TT-180937-FC | FC | 0 | 2019-01-25 | 180937-FC STAMPED | FC | 0 | A | SUPPORT | CONDENSER TUBE CLEANING
DHI | HEX | 이승찬 | MRT-YF00-P2PAH-604121 | 1337 | [CTCS & Debris Filter]_Control Logic for CTCS & Debris Filter | FI | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-11-01 | 180772-FC STAMPED | FC | 2 | A | I&C | CONDENSER TUBE CLEANING
DHI | HEX | 이승찬 | MRT-YV02-P2PAH-604122 | 1338 | [CTCS & Debris Filter]_Cable Connection & Wiring Diagram for CTCS & Debris Filter | FI | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-11-01 | 180772-FC STAMPED | FC | 3 | A | ELECTRICAL | CONDENSER TUBE CLEANING
DHI | HEX | 이승찬 | MRT-YB03-P2PAH-604123 | 1339 | [CTCS & Debris Filter]_Configuration Diagram of Package System for CTCS & Debris Filter | FA | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-11-01 | 180772-FC STAMPED | FC | 4 | A | I&C | CONDENSER TUBE CLEANING
DHI | HEX | 이승찬 | MRT-YK08-P2PAH-604124 | 1340 | [CTCS & Debris Filter]_Outline Drawing for Control Panel of CTCS & Debris Filter | FA | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-11-01 | 180772-FC STAMPED | FC | 5 | A | I&C | CONDENSER TUBE CLEANING
DHI | HEX | 이승찬 | MRT-YT01-P3PAH-604501 | 1341 | [CTCS & Debris Filter]_Condenser Tube Cleaning System_Technical Data Sheet | FA | 2017-11-17 | 2018-04-30 | 2024-11-25 | 2024-11-25 | MRT-DS-REC-TT-240039 | AB | Z2 | 2024-11-29 | MTW-AS-C-LT-24.6004.0 | AB | Z2 | A | MECHANICAL | CONDENSER TUBE CLEANING
DHI | HEX | 이승찬 | MRT-XG02-P3PAH-604502 | 1342 | [CTCS & Debris Filter]_Condenser Tube Cleaning System_P & I Diagram | FA | 2017-10-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-06-21 | MTW-AS-C-LT-24.5406.0 | AB | Z0 | A | MECHANICAL | CONDENSER TUBE CLEANING
DHI | HEX | 이승찬 | MRT-YK08-P3PAH-604503 | 1343 | [CTCS & Debris Filter]_Condenser Tube Cleaning System_Outline Drawing | FA | 2017-10-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | CONDENSER TUBE CLEANING
DHI | HEX | 이승찬 | MRT-YK08-P3PAH-604504 | 1344 | [CTCS & Debris Filter]_Condenser Tube Cleaning System_Outline Drawing for Ball Recirculation unit | FA | 2017-10-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | CONDENSER TUBE CLEANING
DHI | HEX | 이승찬 | MRT-CQ02-P2PAH-604505 | 1345 | [CTCS & Debris Filter]_O&M Manual For Condenser Tube Cleaning System #3, 4 | FI | 2018-12-14 | 2019-01-14 | 2019-01-24 | 2019-01-24 | MRT-DS-REC-TT-180937-FC | FC | 0 | 2019-01-25 | 180937-FC STAMPED | FC | 0 | A | SUPPORT | CONDENSER TUBE CLEANING
DHI | HEX | 이승찬 | MRT-YT01-P3PBB-604511 | 1346 | [CTCS & Debris Filter]_Debris Filter_Technical Data Sheet | FA | 2017-11-17 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | CONDENSER TUBE CLEANING
DHI | HEX | 이승찬 | MRT-XG02-P3PBB-604512 | 1347 | [CTCS & Debris Filter]_Debris Filter_P & I Diagram for Block 3,4 | FA | 2017-10-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-06-21 | MTW-AS-C-LT-24.5406.0 | AB | Z0 | A | MECHANICAL | CONDENSER TUBE CLEANING
DHI | HEX | 이승찬 | MRT-YK08-P3PBB-604513 | 1348 | [CTCS & Debris Filter]_Debris Filter_Outline Drawing | FA | 2017-10-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | CONDENSER TUBE CLEANING
DHI | HEX | 이승찬 | MRT-CQ02-P2PBB-604514 | 1349 | [CTCS & Debris Filter]_O&M Manual For Debris Filter #3, 4 | FI | 2018-12-14 | 2019-01-14 | 2019-01-24 | 2019-01-24 | MRT-DS-REC-TT-180937-FC | FC | 0 | 2019-01-25 | 180937-FC STAMPED | FC | 0 | A | SUPPORT | CONDENSER TUBE CLEANING
DHI | HEX | 이승찬 | MRT-YF00-P3PAH-604521 | 1350 | [CTCS & Debris Filter]_Control Logic for CTCS & Debris Filter | FI | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5839.0 | AB | Z0 | A | I&C | CONDENSER TUBE CLEANING
DHI | HEX | 이승찬 | MRT-YV02-P3PAH-604522 | 1351 | [CTCS & Debris Filter]_Cable Connection & Wiring Diagram for CTCS & Debris Filter | FI | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-10-15 | MTW-AS-C-LT-24.5844.0 | AB | Z0 | A | ELECTRICAL | CONDENSER TUBE CLEANING
DHI | HEX | 이승찬 | MRT-YB03-P3PAH-604523 | 1352 | [CTCS & Debris Filter]_Configuration Diagram of Package System for CTCS & Debris Filter | FA | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5839.0 | AB | Z0 | A | I&C | CONDENSER TUBE CLEANING
DHI | HEX | 이승찬 | MRT-YK08-P3PAH-604524 | 1353 | [CTCS & Debris Filter]_Outline Drawing for Control Panel of CTCS & Debris Filter | FA | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5839.0 | AB | Z0 | A | I&C | CONDENSER TUBE CLEANING
DHI | HEX | 곽주영 | MRT-YK08-P2LAA-605100 | 1354 | Outline Drawing for Deaerator & Storage Tank #2 | FA | 2017-09-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-08-29 | 180384-FC STAMPED | FC | 4 | A | MECHANICAL | DEAERATOR
DHI | HEX | 곽주영 | MRT-YT01-P2LAA-605101 | 1355 | Datasheet for Deaerator & Storage Tank #2 | FA | 2017-09-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-08-25 | 180383-FC STAMPED | FC | 4 | A | MECHANICAL | DEAERATOR
DHI | HEX | 곽주영 | MRT-YK08-P2LAA-605102 | 1356 | Insulation Support Detail for Deaerator & Storage Tank #2 | FI | 2017-12-22 | 2018-05-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-09-21 | 180514-FC STAMPED | FC | 4 | A | MECHANICAL | DEAERATOR
DHI | HEX | 곽주영 | MRT-CQ02-P2LAA-605103 | 1357 | Installation and O&M Manual For Deaerator & Feedwater Storage Tank #2 | FI | 2018-06-29 | 2018-09-28 | 2018-07-27 | 2018-09-27 | MRT-DS-REC-TT-180598-FC | FC | 0 | 2018-10-05 | 180598-FC STAMPED | FC | 0 | A | SUPPORT | DEAERATOR
DHI | HEX | 곽주영 | MRT-YK08-P3LAA-605500 | 1358 | Outline Drawing for Deaerator & Storage Tank #3,4 | FA | 2017-09-29 | 2018-04-30 | 2024-04-08 | 2024-04-08 | MRT-DS-REC-TT-240008 | AB | Z1 | 2024-04-25 | MTW-AS-C-LT-24.5184.0 | AB | Z1 | A | MECHANICAL | DEAERATOR
DHI | HEX | 곽주영 | MRT-YT01-P3LAA-605501 | 1359 | Datasheet for Deaerator & Storage Tank #3,4 | FA | 2017-09-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | DEAERATOR
DHI | HEX | 곽주영 | MRT-YK08-P3LAA-605502 | 1360 | Insulation Support Detail for Deaerator & Storage Tank #3,4 | FI | 2017-12-22 | 2018-05-31 | 2024-04-08 | 2024-04-08 | MRT-DS-REC-TT-240008 | AB | Z1 | 2024-04-25 | MTW-AS-C-LT-24.5184.0 | AB | Z1 | A | MECHANICAL | DEAERATOR
DHI | HEX | 곽주영 | MRT-CQ02-P3LAA-605503 | 1361 | Installation and O&M Manual For Deaerator & Feedwater Storage Tank #3,4 | FI | 2018-06-29 | 2018-09-28 | 2018-07-27 | 2018-09-27 | MRT-DS-REC-TT-180598-FC | FC | 0 | 2018-10-05 | 180598-FC STAMPED | FC | 0 | A | SUPPORT | DEAERATOR
DHI | HEX | 이승찬 | MRT-YD00-P0QHE-606001 | 1362 | [FLASH TANK]_GENERAL ARRANGEMENT DRAWING FOR ATMOSPHERIC FLASH TANK | FA | 2017-11-10 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-10-23 | 180785-FC STAMPED | FC | 4 | A | MECHANICAL | FLASH TANK
DHI | HEX | 이승찬 | MRT-YD00-P2QHE-606003 | 1363 | [FLASH TANK]_GENERAL ARRANGEMENT DRAWING FOR VACUUM FLASH TANK (For Block 2) | FA | 2017-12-13 | 2018-05-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-10-23 | 180785-FC STAMPED | FC | 3 | A | MECHANICAL | FLASH TANK
DHI | HEX | 이승찬 | MRT-YD00-P3QHE-606003 | 1364 | [FLASH TANK]_GENERAL ARRANGEMENT DRAWING FOR VACUUM FLASH TANK (For Block 3, 4) | FA | 2017-12-13 | 2018-05-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | FLASH TANK
DHI | HEX | 이승찬 | MRT-YD00-P0ERB-606001 | 1365 | [C&D TANK]_GENERAL ARRANGEMENT DRAWING FOR CLEAN OIL TANK | FA | 2017-12-13 | 2018-05-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2020-02-25 | 200003-FC STAMPED | FC | 4 | A | MECHANICAL | OIL TANK
DHI | HEX | 이승찬 | MRT-YD00-P0ERB-606002 | 1366 | [C&D TANK]_GENERAL ARRANGEMENT DRAWING FOR DIRTY OIL TANK | FA | 2017-12-13 | 2018-05-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2020-02-25 | 200003-FC STAMPED | FC | 4 | A | MECHANICAL | OIL TANK
DHI | HEX | 이진재 | MRT-YL00-P2MAJ-603107 | 1367 | Steam Jet Air Ejector #2 - System Description | FA | 2017-10-31 | 2018-05-31 | 2018-07-27 | 2018-08-27 | MRT-DS-REC-TT-180344-FC | FC | 3 | 2018-09-08 | 180344-FC STAMPED | FC | 3 | A | MECHANICAL | STEAM JET AIR EJECTOR
DHI | HEX | 이진재 | MRT-YT01-P2MAJ-603100 | 1368 | Steam Jet Air Ejector #2 - Technical Data Sheet | FA | 2017-10-31 | 2018-02-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-11-29 | 180713-FC STAMPED | FC | 4 | A | MECHANICAL | STEAM JET AIR EJECTOR
DHI | HEX | 이진재 | MRT-XG02-P2MAJ-603101 | 1369 | Steam Jet Air Ejector #2 - P&I Diagram | FA | 2017-10-31 | 2018-05-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-11-29 | 180713-FC STAMPED | FC | 4 | A | MECHANICAL | STEAM JET AIR EJECTOR
DHI | HEX | 이진재 | MRT-YK08-P2MAJ-603102 | 1370 | Steam Jet Air Ejector #2 - Outline drawing | FA | 2017-10-31 | 2018-05-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-11-29 | 180713-FC STAMPED | FC | 3 | A | MECHANICAL | STEAM JET AIR EJECTOR
DHI | HEX | 이진재 | MRT-YT01-P2MAJ-603103 | 1371 | Steam Jet Air Ejector #2 - Heat Exchanger Data & Drawing | FA | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-10-05 | 180593-FC STAMPED | FC | 3 | A | MECHANICAL | STEAM JET AIR EJECTOR
DHI | HEX | 이진재 | MRT-YT01-P2MAJ-603104 | 1372 | Steam Jet Air Ejector #2 - Performance Curves | FI | 2017-10-31 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-02-26 | 025/T/MRT/REC/II/2018 | FI | 1 | I | MECHANICAL | STEAM JET AIR EJECTOR
DHI | HEX | 이진재 | MRT-YL00-P2MAJ-603105 | 1373 | Steam Jet Air Ejector #2 - Instrument List and Data Sheet | FA | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-12-11 | 180714-FC STAMPED | FC | 5 | A | I&C | STEAM JET AIR EJECTOR
DHI | HEX | 이진재 | MRT-XN00-P2MAJ-603106 | 1374 | Steam Jet Air Ejector #2 - Valve List and Data Sheet | FA | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-11-29 | 180713-FC STAMPED | FC | 4 | A | MECHANICAL | STEAM JET AIR EJECTOR
DHI | HEX | 이진재 | MRT-YV02-P2MAJ-603108 | 1375 | Steam Jet Air Ejector #2 - Wiring Diagram | FI | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-12-11 | 180714-FC STAMPED | FC | 5 | A | ELECTRICAL | STEAM JET AIR EJECTOR
DHI | HEX | 이진재 | MRT-CQ02-P2MAJ-603109 | 1376 | Steam Jet Air Ejector #2 - Instruction manual | FI | 2018-07-31 | 2018-10-31 | 2018-07-27 | 2018-08-20 | MRT-DS-REC-TT-180281-FC | FC | 0 | 2018-09-03 | 180281-FC STAMPED | FC | 0 | A | SUPPORT | STEAM JET AIR EJECTOR
DHI | HEX | 이진재 | MRT-YL00-P3MAJ-604107 | 1377 | Steam Jet Air Ejector #3,4 - System Description | FA | 2017-10-31 | 2018-05-31 | 2018-07-27 | 2018-08-27 | MRT-DS-REC-TT-180344-FC | FC | 3 | 2018-09-08 | 180344-FC STAMPED | FC | 3 | A | MECHANICAL | STEAM JET AIR EJECTOR
DHI | HEX | 이진재 | MRT-YT01-P3MAJ-604100 | 1378 | Steam Jet Air Ejector #3,4 - Technical Data Sheet | FA | 2017-10-31 | 2018-02-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | STEAM JET AIR EJECTOR
DHI | HEX | 이진재 | MRT-XG02-P3MAJ-604101 | 1379 | Steam Jet Air Ejector #3,4 - P&I Diagram | FA | 2017-10-31 | 2018-05-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-06-21 | MTW-AS-C-LT-24.5406.0 | AB | Z0 | A | MECHANICAL | STEAM JET AIR EJECTOR
DHI | HEX | 이진재 | MRT-YK08-P3MAJ-604102 | 1380 | Steam Jet Air Ejector #3,4 - Outline drawing | FA | 2017-10-31 | 2018-05-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | STEAM JET AIR EJECTOR
DHI | HEX | 이진재 | MRT-YT01-P3MAJ-604103 | 1381 | Steam Jet Air Ejector #3,4 - Heat Exchanger Data & Drawing | FA | 2017-12-29 | 2018-04-30 | 2024-11-20 | 2024-11-20 | MRT-DS-REC-TT-240038 | AB | Z1 | 2024-11-28 | MTW-AS-C-LT-24.5999.0 | AB | Z1 | A | MECHANICAL | STEAM JET AIR EJECTOR
DHI | HEX | 이진재 | MRT-YT01-P3MAJ-604104 | 1382 | Steam Jet Air Ejector #3,4 - Performance Curves | FI | 2017-10-31 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | STEAM JET AIR EJECTOR
DHI | HEX | 이진재 | MRT-YL00-P3MAJ-604105 | 1383 | Steam Jet Air Ejector #3,4 - Instrument List and Data Sheet | FA | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5839.0 | AB | Z0 | A | I&C | STEAM JET AIR EJECTOR
DHI | HEX | 이진재 | MRT-XN00-P3MAJ-604106 | 1384 | Steam Jet Air Ejector #3,4 - Valve List and Data Sheet | FA | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | STEAM JET AIR EJECTOR
DHI | HEX | 이진재 | MRT-YV02-P3MAJ-604108 | 1385 | Steam Jet Air Ejector #3,4 - Wiring Diagram | FI | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5839.0 | AB | Z0 | A | ELECTRICAL | STEAM JET AIR EJECTOR
DHI | HEX | 이진재 | MRT-CQ02-P3MAJ-603109 | 1386 | Steam Jet Air Ejector #3,4 - Instruction manual | FI | 2018-07-31 | 2018-10-31 | 2018-07-27 | 2018-08-20 | MRT-DS-REC-TT-180281-FC | FC | 0 | 2018-09-03 | 180281-FC STAMPED | FC | 0 | A | SUPPORT | STEAM JET AIR EJECTOR
DHI | HEX | 이승찬 | MRT-YT01-P2MAJ-603110 | 1387 | Steam Jet Air Ejector #2 - Data Sheet for Silencer | FI | 2018-01-12 | 2018-06-15 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-09-24 | 180505-FC STAMPED | FC | 2 | A | MECHANICAL | STEAM JET AIR EJECTOR
DHI | HEX | 이승찬 | MRT-YK08-P2MAJ-603308 | 1388 | Steam Jet Air Ejector #2 - Silencer Drawing | FA | 2018-01-12 | 2018-06-15 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-09-08 | 180344-FC STAMPED | FC | 1 | A | MECHANICAL | STEAM JET AIR EJECTOR
DHI | HEX | 이승찬 | MRT-YT01-P3MAJ-604110 | 1389 | Steam Jet Air Ejector #3,4 - Data Sheet for Silencer | FI | 2018-01-12 | 2018-06-15 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | STEAM JET AIR EJECTOR
DHI | HEX | 이승찬 | MRT-YK08-P3MAJ-604308 | 1390 | Steam Jet Air Ejector #3,4 - Silencer Drawing | FA | 2018-01-12 | 2018-06-15 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | STEAM JET AIR EJECTOR
DHI | HEX | 이진재 | MRT-YK08-P2MAJ-603200 | 1391 | Waterbox Vacuum Pump #2 - Outline Drawing | FA | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-10-16 | 180658-FC STAMPED | FC | 3 | A | MECHANICAL | WATERBOX VACUUM PUMP
DHI | HEX | 이진재 | MRT-XG02-P2MAJ-603201 | 1392 | Waterbox Vacuum Pump #2 - P & I Diagram | FA | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-10-16 | 180658-FC STAMPED | FC | 4 | A | MECHANICAL | WATERBOX VACUUM PUMP
DHI | HEX | 이진재 | MRT-YV02-P2MAJ-603202 | 1393 | Waterbox Vacuum Pump #2 - Wiring Diargam | FI | 2018-01-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2021-07-12 | 210045-FC STAMPED | FC | 3 | A | ELECTRICAL | WATERBOX VACUUM PUMP
DHI | HEX | 이진재 | MRT-YK08-P2MAJ-603203 | 1394 | Waterbox Vacuum Pump #2 - Terminal Box | FI | 2018-01-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-10-05 | 180537-FC STAMPED | FC | 2 | A | ELECTRICAL | WATERBOX VACUUM PUMP
DHI | HEX | 이진재 | MRT-YT01-P2MAJ-603204 | 1395 | Waterbox Vacuum Pump #2 - Technical Datasheet | FA | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-09-13 | 180448-FC STAMPED | FC | 3 | A | MECHANICAL | WATERBOX VACUUM PUMP
DHI | HEX | 이진재 | MRT-YK08-P2MAJ-603205 | 1396 | Waterbox Vacuum Pump #2 - Motor Datasheet & Drawings | FI | 2018-01-31 | 2018-05-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2019-05-29 | 180269-FC STAMPED | FC | 1 | A | ELECTRICAL | WATERBOX VACUUM PUMP
DHI | HEX | 이진재 | MRT-YT01-P2MAJ-603206 | 1397 | Waterbox Vacuum Pump #2 - Heat Exchanger Data Sheet& Drawings | FI | 2018-01-31 | 2018-05-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2019-05-29 | 180448-FC STAMPED | FC | 1 | A | MECHANICAL | WATERBOX VACUUM PUMP
DHI | HEX | 이진재 | MRT-YL00-P2MAJ-603207 | 1398 | Waterbox Vacuum Pump #2_Instrument list with drawing | FA | 2018-01-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-11-29 | 180724-FC STAMPED | FC | 4 | A | I&C | WATERBOX VACUUM PUMP
DHI | HEX | 이진재 | MRT-CQ02-P2MAJ-603208 | 1399 | Waterbox Vacuum Pump #2_Instruction manual | FI | 2018-04-30 | 2018-06-29 | 2018-07-27 | 2018-09-27 | MRT-DS-REC-TT-180569-FC | FC | 1 | 2018-10-10 | 180569-FC STAMPED | FC | 1 | A | SUPPORT | WATERBOX VACUUM PUMP
DHI | HEX | 이진재 | MRT-XS00-P2MAJ-603209 | 1400 | Waterbox Vacuum Pump #2 - System Description & Control Philosophy | FA | 2018-01-31 | 2018-04-30 | 2018-07-27 | 2018-08-29 | MRT-DS-REC-TT-180448-FC | FC | 2 | 2018-09-13 | 180448-FC STAMPED | FC | 2 | A | MECHANICAL | WATERBOX VACUUM PUMP
DHI | HEX | 이진재 | MRT-YK08-P3MAJ-604200 | 1401 | Waterbox Vacuum Pump #3,4 - Outline Drawing | FA | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | WATERBOX VACUUM PUMP
DHI | HEX | 이진재 | MRT-XG02-P3MAJ-604201 | 1402 | Waterbox Vacuum Pump #3,4 - P & I Diagram | FA | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-06-21 | MTW-AS-C-LT-24.5406.0 | AB | Z0 | A | MECHANICAL | WATERBOX VACUUM PUMP
DHI | HEX | 이진재 | MRT-YV02-P3MAJ-604202 | 1403 | Waterbox Vacuum Pump #3,4 - Wiring Diargam | FI | 2018-01-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5839.0 | AB | Z0 | A | ELECTRICAL | WATERBOX VACUUM PUMP
DHI | HEX | 이진재 | MRT-YK08-P3MAJ-604203 | 1404 | Waterbox Vacuum Pump #3,4 - Terminal Box | FI | 2018-01-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5839.0 | AB | Z0 | A | ELECTRICAL | WATERBOX VACUUM PUMP
DHI | HEX | 이진재 | MRT-YT01-P3MAJ-604204 | 1405 | Waterbox Vacuum Pump #3,4 - Technical Datasheet | FA | 2017-12-29 | 2018-04-30 | 2024-11-20 | 2024-11-20 | MRT-DS-REC-TT-240038 | AB | Z1 | 2024-11-28 | MTW-AS-C-LT-24.5999.0 | AB | Z1 | A | MECHANICAL | WATERBOX VACUUM PUMP
DHI | HEX | 이진재 | MRT-YK08-P3MAJ-604205 | 1406 | Waterbox Vacuum Pump #3,4 - Motor Datasheet & Drawings | FI | 2018-01-31 | 2018-05-31 | 2024-11-20 | 2024-11-20 | MRT-DS-REC-TT-240038 | AB | Z1 | 2024-11-28 | MTW-AS-C-LT-24.5999.0 | AB | Z1 | A | ELECTRICAL | WATERBOX VACUUM PUMP
DHI | HEX | 이진재 | MRT-YT01-P3MAJ-604206 | 1407 | Waterbox Vacuum Pump #3,4 - Heat Exchanger Data Sheet& Drawings | FI | 2018-01-31 | 2018-05-31 | 2024-12-02 | 2024-12-02 | MRT-DS-REC-TT-240042 | AB | Z2 | 2024-12-05 | MTW-AS-C-LT-24.6041.0 | AB | Z2 | A | MECHANICAL | WATERBOX VACUUM PUMP
DHI | HEX | 이진재 | MRT-YL00-P3MAJ-604207 | 1408 | Waterbox Vacuum Pump #3,4_Instrument list with drawing | FA | 2018-01-31 | 2018-04-30 | 2024-11-20 | 2024-11-20 | MRT-DS-REC-TT-240037 | AB | Z1 | 2024-12-03 | MTW-AS-C-LT-24.6026.0 | AB | Z1 | A | I&C | WATERBOX VACUUM PUMP
DHI | HEX | 이진재 | MRT-CQ02-P3MAJ-604208 | 1409 | Waterbox Vacuum Pump #3,4_Instruction manual | FI | 2018-04-30 | 2018-06-29 | 2018-07-27 | 2018-09-27 | MRT-DS-REC-TT-180569-FC | FC | 1 | 2018-10-10 | 180569-FC STAMPED | FC | 1 | A | SUPPORT | WATERBOX VACUUM PUMP
DHI | HEX | 이진재 | MRT-XS00-P3MAJ-604209 | 1410 | Waterbox Vacuum Pump #3,4 - System Description & Control Philosophy | FA | 2018-01-31 | 2018-04-30 | 2018-07-27 | 2018-08-29 | MRT-DS-REC-TT-180448-FC | FC | 2 | 2018-09-13 | 180448-FC STAMPED | FC | 2 | A | MECHANICAL | WATERBOX VACUUM PUMP
DHI | TG_SYSTEM | 구태모 | MRT-XW03-P3MKA-210001 | 1411 | HAZARDOUS AREA CLASSIFICATION FOR GENERATOR (Block #3,4) | FI | 2018-04-30 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | SUPPORT | GENERATOR AUXILIARY
DHI | TG_SYSTEM | 구태모 | MRT-XS00-P3MKG-210001 | 1412 | SYSTEM DESCRIPTION FOR H2 & CO2 CONTROL SYSTEM (Block #3,4) | FI | 2018-02-19 | 2018-06-19 | 2018-07-27 | 2018-09-27 | MRT-DS-REC-TT-180591-FC | FC | 1 | 2018-10-05 | 180591-FC STAMPED | FC | 1 | A | MECHANICAL | GENERATOR AUXILIARY
DHI | TG_SYSTEM | 구태모 | MRT-XS00-P3MKW-210001 | 1413 | SYSTEM DESCRIPTION FOR GENERATOR SEAL OIL SYSTEM (Block #3,4) | FI | 2018-02-19 | 2018-06-19 | 2018-07-27 | 2018-09-27 | MRT-DS-REC-TT-180591-FC | FC | 1 | 2018-10-05 | 180591-FC STAMPED | FC | 1 | A | MECHANICAL | GENERATOR AUXILIARY
DHI | TG_SYSTEM | 구태모 | MRT-XG02-P2MKJ-210001 | 1414 | GENERATOR PIPING DIAGRAM FOR LIQUID LEVEL DETECTOR (Block #2) | FI | 2018-02-18 | 2018-06-18 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-10-05 | 180591-FC STAMPED | FC | 1 | A | MECHANICAL | GENERATOR AUXILIARY
DHI | TG_SYSTEM | 구태모 | MRT-XG02-P3MKW-210001 | 1415 | GENERATOR SEAL OIL SYSTEM P & ID (Block #3,4) | FA | 2018-02-19 | 2018-06-19 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUXILIARY
DHI | TG_SYSTEM | 구태모 | MRT-XG02-P3MKG-210001 | 1416 | H2 & CO2 CONTROL SYSTEM P & ID (Block #3,4) | FA | 2018-02-19 | 2018-06-19 | 2023-07-19 | 2023-07-19 | MRT-DS-REC-TT-230012 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5831.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUXILIARY
DHI | TG_SYSTEM | 구태모 | MRT-XL00-P3MKA-210001 | 1417 | LINE LIST FOR GENERATOR (Block #3,4) | FI | 2018-04-02 | 2018-08-02 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUXILIARY
DHI | TG_SYSTEM | 구태모 | MRT-XN00-P3MKA-210001 | 1418 | VALVE LIST FOR GENERATOR (Block #3,4) | FI | 2018-04-02 | 2018-08-02 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUXILIARY
DHI | TG_SYSTEM | 구태모 | MRT-CN00-P3MKG-210001 | 1419 | COMMISSIONING PROCEDURE FOR H2 & CO2 CONTROL SYSTEM (Block #3,4) | FA | 2018-12-31 | 2019-02-28 | 2021-09-03 | 2021-09-03 | MRT-DS-REC-TT-210050 | FC | 2 | 2021-10-03 | DEEMED APPROVAL | FC | 2 | A | SUPPORT | GENERATOR AUXILIARY
DHI | TG_SYSTEM | 구태모 | MRT-CN00-P3MKW-210001 | 1420 | COMMISSIONING PROCEDURE FOR GENERATOR SHAFT SEAL SYSTEM (Block #3,4) | FA | 2018-12-31 | 2019-02-28 | 2021-09-03 | 2021-09-03 | MRT-DS-REC-TT-210050 | FC | 2 | 2021-10-03 | DEEMED APPROVAL | FC | 2 | A | SUPPORT | GENERATOR AUXILIARY
DHI | TG_SYSTEM | 유정운 | MRT-YD00-P3MKW-220002 | 1421 | GENERATOR SEAL OIL SUPPLY UNIT OUTLINE (Block #3,4) | FA | 2018-04-30 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUXILIARY
DHI | TG_SYSTEM | 유정운 | MRT-YV02-P3MKW-230001 | 1422 | GENERATOR SEAL OIL ELECTRICAL CONNECTION DIAGRAM (Block #3,4) | FI | 2018-05-30 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5067.0 | AB | Z0 | A | ELECTRICAL | GENERATOR AUXILIARY
DHI | TG_SYSTEM | 유정운 | MRT-YT01-P3MKA-240002 | 1423 | GENERATOR PUMP AND MOTOR LIST, DRAWING AND DATA SHEET (Block #3,4) | FI | 2018-05-30 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | ELECTRICAL | GENERATOR AUXILIARY
DHI | TG_SYSTEM | 유정운 | MRT-YD00-P3MKW-220004 | 1424 | FLOAT TRAP OUTLINE (Block #3,4) | FA | 2018-04-30 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUXILIARY
DHI | TG_SYSTEM | 유정운 | MRT-YD00-P2MKJ-220001 | 1425 | LIQUID DETECTOR OUTLINE (Block #2) | FA | 2018-04-30 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-10-10 | 180728-FC STAMPED | FC | 1 | A | MECHANICAL | GENERATOR AUXILIARY
DHI | TG_SYSTEM | 유정운 | MRT-YD00-P3MKW-220003 | 1426 | LIQUID DETECTOR OUTLINE (Block #3,4) | FA | 2018-04-30 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUXILIARY
DHI | TG_SYSTEM | 유정운 | MRT-YT01-P3MKA-240003 | 1427 | GENERATOR AUX SYSTEM INSTRUMENT DATA SHEET (Block #3,4) | FI | 2018-05-30 |  | 2024-11-05 | 2024-11-05 | MRT-DS-REC-TT-240024 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6044.0 | AB | Z0 | A | I&C | GENERATOR AUXILIARY
DHI | TG_SYSTEM | 유정운 | MRT-YD00-P3MKG-220004 | 1428 | H2 & CO2 CONTROL SYSTEM_CO2 MANIFOLD OUTLINE (Block #3,4) | FA | 2018-04-30 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUXILIARY
DHI | TG_SYSTEM | 유정운 | MRT-YV02-P3MKW-230002 | 1429 | H2 & CO2 CONTROL SYSTEM_ELECTRICAL CONNECTION DIAGRAM (Block #3,4) | FI | 2018-05-31 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5067.0 | AB | Z0 | A | ELECTRICAL | GENERATOR AUXILIARY
DHI | TG_SYSTEM | 유정운 | MRT-YD00-P3MKG-220006 | 1430 | H2 & CO2 CONTROL SYSTEM_GENERATOR GAS MONITORING SYSTEM OUTLINE (Block #3,4) | FA | 2018-04-30 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUXILIARY
DHI | TG_SYSTEM | 유정운 | MRT-YD00-P3MKG-220005 | 1431 | H2 & CO2 CONTROL SYSTEM_H2 CONTROL CABINET OUTLINE (Block #3,4) | FA | 2018-04-30 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5067.0 | AB | Z0 | A | I&C | GENERATOR AUXILIARY
DHI | TG_SYSTEM | 유정운 | MRT-YD00-P3MKG-220001 | 1432 | H2 & CO2 CONTROL SYSTEM_H2 GAS DRYER OUTLINE (Block #3,4) | FA | 2018-04-30 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUXILIARY
DHI | TG_SYSTEM | 유정운 | MRT-YD00-P3MKG-220003 | 1433 | H2 & CO2 CONTROL SYSTEM_H2 MANIFOLD OUTLINE (Block #3,4) | FA | 2018-04-30 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUXILIARY
DHI | TG_SYSTEM | 유정운 | MRT-CQ02-P3MKG-260001 | 1434 | O&M MANUAL FOR HYDROGEN CONTROL SYSTEM (Block #3,4) | FI | 2018-12-31 |  | 2019-03-06 | 2019-03-08 | MRT-DS-REC-TT-190020-FC | FC | 0 | 2019-03-11 | 190020-FC STAMPED | FC | 0 | A | SUPPORT | GENERATOR AUXILIARY
DHI | TG_SYSTEM | 유정운 | MRT-CQ02-P3MKW-260001 | 1435 | O&M MANUAL FOR GENERATOR SHAFT SEAL SYSTEM (Block #3,4) | FI | 2018-12-31 |  | 2019-03-06 | 2019-03-08 | MRT-DS-REC-TT-190020-FC | FC | 0 | 2019-03-11 | 190020-FC STAMPED | FC | 0 | A | SUPPORT | GENERATOR AUXILIARY
DHI | TG_GEN | 허명구 | MRT-YT01-P2MKA-240001 | 1436 | GENERATOR DATA SHEET (Block #2) | FI | 2018-03-30 | 2018-08-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-09-21 | 180468-FC STAMPED | FC | 1 | A | ELECTRICAL | GENERATOR
DHI | TG_GEN | 허명구 | MRT-YT01-P3MKA-240001 | 1437 | GENERATOR DATA SHEET (Block #3,4) | FI | 2018-03-30 | 2018-09-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | ELECTRICAL | GENERATOR
DHI | TG_GEN | 허명구 | MRT-YK08-P2MKJ-220001 | 1438 | GENERATOR UNIT AIR COOLER OUTLINE (Block #2) | FA | 2018-01-30 | 2018-08-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-08-13 | 180210-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR
DHI | TG_GEN | 허명구 | MRT-YK08-P3MKA-220001 | 1439 | GENERATOR UNIT HYDROGEN COOLER OUTLINE (Block #3,4) | FA | 2018-03-01 | 2018-09-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR
DHI | TG_GEN | 어민혁 | MRT-YD00-P2MKA-220003 | 1440 | GENERATOR MECHANICAL OUTLINE (Block #2) | FA | 2017-11-30 | 2018-08-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-08-28 | 180368-FC STAMPED | FC | 3 | A | MECHANICAL | GENERATOR
DHI | TG_GEN | 어민혁 | MRT-YD00-P3MKA-220003 | 1441 | GENERATOR MECHANICAL OUTLINE (Block #3,4) | FA | 2017-12-30 | 2018-09-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR
DHI | TG_GEN | 어민혁 | MRT-YK08-P2MKA-220002 | 1442 | GENERATOR NAME PLATE (Block #2) | FI | 2018-04-30 | 2019-03-22 | 2019-03-22 | 2019-03-22 | MRT-DS-REC-TT-180264-FC | FC | 0 | 2019-03-22 | 180264-FC STAMPED | FC | 0 | A | ELECTRICAL | GENERATOR
DHI | TG_GEN | 어민혁 | MRT-YK08-P3MKA-220002 | 1443 | GENERATOR NAME PLATE (Block #3,4) | FI | 2018-04-30 | 2019-03-22 | 2019-03-22 | 2019-03-22 | MRT-DS-REC-TT-180264-FC | FC | 0 | 2019-03-22 | 180264-FC STAMPED | FC | 0 | A | ELECTRICAL | GENERATOR
DHI | TG_GEN | 어민혁 | MRT-YD00-P2MKA-220001 | 1444 | GENERATOR PIPING CONNECTION (Block #2) | FI | 2018-03-30 | 2018-08-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-09-05 | 180249-FC STAMPED | FC | 3 | A | MECHANICAL | GENERATOR
DHI | TG_GEN | 어민혁 | MRT-YD00-P3MKA-220001 | 1445 | GENERATOR PIPING CONNECTION (Block #3,4) | FI | 2018-04-30 | 2018-09-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR
DHI | TG_GEN | 어민혁 | MRT-YK10-P2MKA-220003 | 1446 | GENERATOR COOLER ROOF ASSY(Block #2) | FI | 2018-04-30 | 2019-03-22 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2019-03-22 | 180829-FC STAMPED | FC | 1 | A | MECHANICAL | GENERATOR
DHI | TG_GEN | 어민혁 | MRT-YD00-P2MKA-220005 | 1447 | GENERATOR ENCLOSURE ARRANGEMENT(Block #2) | FI | 2018-03-30 | 2018-08-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2019-01-05 | 180929-FC STAMPED | FC | 1 | A | MECHANICAL | GENERATOR
DHI | TG_GEN | 어민혁 | MRT-YK10-P2MKA-220001 | 1448 | GENERATOR END SHIELD ASSY CE(Block #2) | FI | 2018-03-30 | 2018-08-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-08-14 | 180211-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR
DHI | TG_GEN | 어민혁 | MRT-YK10-P3MKA-220001 | 1449 | GENERATOR END SHIELD ASSY CE (Block #3,4) | FI | 2018-04-30 | 2018-09-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR
DHI | TG_GEN | 어민혁 | MRT-YK10-P2MKA-220002 | 1450 | GENERATOR END SHIELD ASSY TE(Block #2) | FI | 2018-03-30 | 2018-08-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-08-14 | 180211-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR
DHI | TG_GEN | 어민혁 | MRT-YK10-P3MKA-220002 | 1451 | GENERATOR END SHIELD ASSY TE (Block #3,4) | FI | 2018-04-30 | 2018-09-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR
DHI | TG_GEN | 어민혁 | MRT-YD00-P3MKA-220005 | 1452 | GENERATOR LAGGING LAYOUT (Block #3,4) | FI | 2018-04-30 | 2018-09-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR
DHI | TG_GEN | 어민혁 | MRT-DM01-P3MKA-220001 | 1453 | TERMINAL BOX BOLTING AND WELDING PROCEDURE | FI | 2018-10-30 | 2018-09-30 | 2018-07-27 | 2018-08-08 | MRT-DS-REC-TT-180191-FC | FC | 0 | 2018-08-14 | 180191-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR
DHI | TG_GEN | 어민혁 | MRT-YK10-P3MKA-220003 | 1454 | GENERATOR TERMINAL BOX ASSEMBLY (Block #3,4) | FI | 2018-03-30 | 2018-09-30 | 2018-07-27 | 2018-08-08 | MRT-DS-REC-TT-180191-FC | FC | 0 | 2018-08-14 | 180191-FC STAMPED | FC | 0 | A | ELECTRICAL | GENERATOR
DHI | TG_GEN | 어민혁 | MRT-YD00-P2MKA-220002 | 1455 | GENERATOR STATOR HANDLING AND SHIPPING DIMENSION (Block #2) | FI | 2018-03-30 | 2018-08-30 | 2018-07-27 | 2018-08-01 | MRT-DS-REC-TT-180068-FC | FC | 0 | 2018-08-13 | 180068-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR
DHI | TG_GEN | 어민혁 | MRT-YD00-P3MKA-220002 | 1456 | GENERATOR STATOR HANDLING AND SHIPPING DIMENSION (Block #3,4) | FI | 2018-04-30 | 2018-09-30 | 2018-07-27 | 2018-08-01 | MRT-DS-REC-TT-180068-FC | FC | 0 | 2018-08-13 | 180068-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR
DHI | TG_GEN | 어민혁 | MRT-XB00-P2MKA-220001 | 1457 | GENERATOR FOUNDATION ARRANGEMENT DRAWING (Block #2) | FA | 2017-11-30 | 2018-08-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-08-13 | 180111-FC STAMPED | FC | 3 | A | CIVIL | GENERATOR
DHI | TG_GEN | 어민혁 | MRT-XB00-P3MKA-220001 | 1458 | GENERATOR FOUNDATION ARRANGEMENT DRAWING (Block #3,4) | FA | 2017-12-30 | 2018-09-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-03-01 | MTW-AS-C-LT-24.5000.0 | AB | Z0 | A | CIVIL | GENERATOR
DHI | TG_GEN | 어민혁 | MRT-YD00-P2MKA-220004 | 1459 | GENERATOR FOUNDATION PLATE ASSY (Block #2) | FI | 2018-03-30 | 2018-08-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-08-14 | 180186-FC STAMPED | FC | 0 | A | CIVIL | GENERATOR
DHI | TG_GEN | 어민혁 | MRT-YD00-P3MKA-220004 | 1460 | GENERATOR FOUNDATION PLATE ASSY (Block #3,4) | FI | 2018-04-30 | 2018-09-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-03-01 | MTW-AS-C-LT-24.5000.0 | AB | Z0 | A | CIVIL | GENERATOR
DHI | TG_GEN | 어민혁 | MRT-DM02-P2MKA-220001 | 1461 | GENERATOR FOUNDATION INSTALLATION DETAIL(Block #2) | FI | 2018-03-30 | 2018-08-30 | 2018-07-27 | 2018-08-08 | MRT-DS-REC-TT-180187-FC | FC | 0 | 2018-08-14 | 180187-FC STAMPED | FC | 0 | A | CIVIL | GENERATOR
DHI | TG_GEN | 어민혁 | MRT-DM02-P3MKA-220001 | 1462 | GENERATOR FOUNDATION INSTALLATION DETAIL | FI | 2018-04-30 | 2018-09-30 | 2018-07-27 | 2018-08-08 | MRT-DS-REC-TT-180187-FC | FC | 0 | 2018-08-14 | 180187-FC STAMPED | FC | 0 | A | CIVIL | GENERATOR
DHI | TG_GEN | 어민혁 | MRT-UF00-P2MKA-220001 | 1463 | GENERATOR FOUNDATION LOADING (Block #2) | FI | 2018-03-30 |  | 2017-12-15 | 2017-12-22 | MRT-DS-PLNE-TT-170136 | FI | 1 | 2017-12-29 | 27.025/E04/PLNE/XII/2017 | FI | 1 | A | CIVIL | GENERATOR
DHI | TG_GEN | 어민혁 | MRT-UF00-P3MKA-220001 | 1464 | GENERATOR FOUNDATION LOADING (Block #3,4) | FI | 2018-04-30 |  | 2017-12-15 | 2017-12-22 | MRT-DS-PLNE-TT-170136 | FI | 1 | 2017-12-29 | 27.025/E04/PLNE/XII/2017 | FI | 1 | A | CIVIL | GENERATOR
DHI | TG_GEN | 김충목 | MRT-YK10-P2MKB-230001 | 1465 | BRUSH HOLDER RIGGING ASSEMBLY (Block #2) | FI | 2018-06-30 | 2018-08-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-10-31 | 180575-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR
DHI | TG_GEN | 김충목 | MRT-YK10-P3MKB-230001 | 1466 | BRUSH HOLDER RIGGING ASSEMBLY (Block #3,4) | FI | 2018-07-30 | 2018-09-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR
DHI | TG_GEN | 김충목 | MRT-XF00-P2MKA-230001 | 1467 | GENERATOR ROTOR HANDLING DIMENSION (Block #2) | FI | 2018-06-30 | 2018-08-30 | 2018-07-27 | 2018-09-24 | MRT-DS-REC-TT-180575-FC | FC | 0 | 2018-10-31 | 180575-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR
DHI | TG_GEN | 김충목 | MRT-XF00-P3MKA-220001 | 1468 | GENERATOR ROTOR HANDLING DIMENSION (Block #3,4) | FI | 2018-07-30 | 2018-09-30 | 2018-07-27 | 2018-09-27 | MRT-DS-REC-TT-180596-FC | FC | 0 | 2018-10-05 | 180596-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR
DHI | TG_GEN | 김충목 | MRT-YK10-P2MKA-230002 | 1469 | FIELD CLEARANCE DIAGRAM (Block #2) | FI | 2018-06-30 | 2018-08-30 | 2019-01-03 | 2019-01-03 | MRT-DS-REC-TT-180928-FC | FC | 1 | 2019-01-05 | 180928-FC STAMPED | FC | 1 | A | MECHANICAL | GENERATOR
DHI | TG_GEN | 김충목 | MRT-YK10-P3MKA-230002 | 1470 | FIELD CLEARANCE DIAGRAM (Block #3,4) | FI | 2018-07-30 | 2018-09-30 | 2018-07-27 | 2018-09-27 | MRT-DS-REC-TT-180596-FC | FC | 0 | 2018-10-05 | 180596-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR
DHI | TG_GEN | 김충목 | MRT-YK10-P2MKA-230003 | 1471 | ROTOR ASSEMBLY AND DISASSEMBLY NOTE (Block #2) | FI | 2018-03-30 | 2018-08-30 | 2018-07-27 | 2018-08-13 | MRT-DS-REC-TT-180227-FC | FC | 0 | 2018-08-27 | 180227-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR
DHI | TG_GEN | 김충목 | MRT-YK10-P3MKA-230003 | 1472 | ROTOR ASSEMBLY AND DISASSEMBLY NOTE (Block #3,4) | FI | 2018-04-30 | 2018-09-30 | 2018-07-27 | 2018-08-13 | MRT-DS-REC-TT-180351-FC | FC | 0 | 2018-08-28 | 180351-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR
DHI | TG_GEN | 김충목 | MRT-YK10-P2MKA-230004 | 1473 | ROTOR ASSEMBLY AND DISASSEMBLY DIAGRAM (Block #2) | FI | 2018-03-30 | 2018-08-30 | 2018-07-27 | 2018-08-13 | MRT-DS-REC-TT-180227-FC | FC | 0 | 2018-08-27 | 180227-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR
DHI | TG_GEN | 김충목 | MRT-YK10-P3MKA-230004 | 1474 | ROTOR ASSEMBLY AND DISASSEMBLY DIAGRAM (Block #3,4) | FI | 2018-04-30 | 2018-09-30 | 2018-07-27 | 2018-08-13 | MRT-DS-REC-TT-180351-FC | FC | 0 | 2018-08-28 | 180351-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR
DHI | TG_GEN | 최성찬 | MRT-YE00-P2MKA-230001 | 1475 | GENERATOR ELECTRICAL CONNECTION OUTLINE WITH PACKAGE WIRING AND TERMINAL (Block #2) | FA | 2018-03-01 | 2018-08-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2019-03-26 | 180942-FC STAMPED | FC | 2 | A | ELECTRICAL | GENERATOR
DHI | TG_GEN | 최성찬 | MRT-YE00-P3MKA-230001 | 1476 | GENERATOR ELECTRICAL CONNECTION OUTLINE WITH PACKAGE WIRING AND TERMINAL (Block #3,4) | FA | 2018-04-30 | 2018-09-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5067.0 | AB | Z0 | A | ELECTRICAL | GENERATOR
DHI | TG_GEN | 최성찬 | MRT-YE00-P2MKA-230002 | 1477 | GENERATOR ELECTRICAL FOUNDATION CONDUITS LAYOUT (Block #2) | FA | 2018-03-01 | 2018-08-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2019-01-25 | 190010-FC STAMPED | FC | 3 | A | ELECTRICAL | GENERATOR
DHI | TG_GEN | 최성찬 | MRT-YE00-P3MKA-230002 | 1478 | GENERATOR ELECTRICAL FOUNDATION CONDUITS LAYOUT (Block #3,4) | FA | 2018-04-30 | 2018-09-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-03-01 | MTW-AS-C-LT-24.5000.0 | AB | Z0 | A | ELECTRICAL | GENERATOR
DHI | TG_GEN | 최성찬 | MRT-YK00-P2BAT-240001 | 1479 | CURRENT TRANSFORMER CONFIGURATION (Block #2) | FA | 2018-03-01 | 2018-08-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-12-08 | 180741-FC STAMPED | FC | 1 | A | ELECTRICAL | GENERATOR
DHI | TG_GEN | 최성찬 | MRT-UC02-P2BAT-240001 | 1480 | GENERATOR NEUTRAL ENCLOSURE INSTALLATION (Block #2) | FA | 2018-03-01 | 2018-08-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2019-03-26 | 180942-FC STAMPED | FC | 2 | A | MECHANICAL | GENERATOR
DHI | TG_GEN | 최성찬 | MRT-YK00-P3BAT-240001 | 1481 | CURRENT TRANSFORMER ASSEMBLY (Block #3,4) | FA | 2018-04-30 | 2018-09-30 | 2018-07-27 | 2018-08-13 | MRT-DS-REC-TT-180352-FC | FC | 0 | 2018-08-28 | 180352-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR
DHI | TG_GEN | 허명구 | MRT-CM02-P2MKA-220001 | 1482 | GENERATOR O&M MANUAL (Block #2) | FI | 2019-01-31 | 2019-03-31 | 2019-02-11 | 2019-02-11 | MRT-DS-REC-TT-190013-FC | FC | 0 | 2019-02-11 | 190013-FC STAMPED | FC | 0 | A | SUPPORT | GENERATOR
DHI | TG_GEN | 허명구 | MRT-CM02-P3MKA-220001 | 1483 | GENERATOR O&M MANUAL (Block #3,4) | FI | 2019-01-31 | 2019-03-31 | 2019-02-11 | 2019-02-11 | MRT-DS-REC-TT-190013-FC | FC | 0 | 2019-02-11 | 190013-FC STAMPED | FC | 0 | A | SUPPORT | GENERATOR
DHI | TG_SYSTEM | 이동혁 | MRT-XH01-P2MKJ-220001 | 1484 | GENERATOR AUXILIARIES PIPING ARRANGEMENT (Block #2) | FA | 2018-03-15 | 2018-05-15 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-09-21 | 180516-FC STAMPED | FC | 1 | A | MECHANICAL | GENERATOR AUX PIPING
DHI | TG_SYSTEM | 이동혁 | MRT-XH01-P3MKA-220001 | 1485 | GENERATOR AUXILIARIES PIPING ARRANGEMENT (Block #3,4) | FA | 2018-05-15 | 2018-07-15 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUX PIPING
DHI | TG_SYSTEM | 이동혁 | MRT-XJ00-P2MKJ-220001 | 1486 | GENERATOR AUXILIARIES PIPING ISO (Block #2) | FA | 2018-03-15 | 2018-05-15 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-10-23 | 180778-FC STAMPED | FC | 3 | A | MECHANICAL | GENERATOR AUX PIPING
DHI | TG_SYSTEM | 이동혁 | MRT-XJ00-P3MKA-220001 | 1487 | GENERATOR AUXILIARIES PIPING ISO (Block #3,4) | FA | 2018-05-15 | 2018-07-15 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUX PIPING
DHI | TG_SYSTEM | 이동혁 | MRT-XK00-P2MKJ-220001 | 1488 | GENERATOR AUXILIARIES PIPING SUPPORT (Block #2) | FA | 2018-03-15 | 2018-05-15 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-10-23 | 180779-FC STAMPED | FC | 2 | A | MECHANICAL | GENERATOR AUX PIPING
DHI | TG_SYSTEM | 이동혁 | MRT-XK00-P3MKA-220001 | 1489 | GENERATOR AUXILIARIES PIPING SUPPORT (Block #3,4) | FA | 2018-05-30 | 2018-07-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUX PIPING
DHI | TG_SYSTEM | 이동혁 | MRT-YD00-P3MKW-220001 | 1490 | GENERATOR BEARING OIL DRAIN ENLARGEMENT OUTLINE (Block #3,4) | FA | 2018-04-15 | 2018-06-15 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUX PIPING
DHI | TG_SYSTEM | 이동혁 | MRT-YD00-P3MKW-220005 | 1491 | GENERATOR SEAL OIL DRAIN ENLARGEMENT OUTLINE (Block #3,4) | FA | 2018-04-15 | 2018-06-15 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUX PIPING
DHI | TG_ELEC&INC | 김강현 | MRT-YR02-P2MKC-230001 | 1492 | DATA FOR POWER SYSTEM STABILITY ANALYSIS #2 | FI | 2019-03-02 | 2019-07-02 | 2019-03-25 | 2019-03-26 | MRT-DS-REC-TT-190068-FC | FC | 0 | 2019-03-26 | 190068-FC STAMPED | FC | 0 | A | ELECTRICAL | STG ELECTRICAL
DHI | TG_ELEC&INC | 김강현 | MRT-YR02-P3MKC-230001 | 1493 | DATA FOR POWER SYSTEM STABILITY ANALYSIS #3,4 | FI | 2019-03-02 | 2019-07-02 | 2019-03-25 | 2019-03-26 | MRT-DS-REC-TT-190068-FC | FC | 0 | 2019-03-26 | 190068-FC STAMPED | FC | 0 | A | ELECTRICAL | STG ELECTRICAL
DHI | TG_ELEC&INC | 김강현 | MRT-YK09-P2MKC-230001 | 1494 | EXCITATION CUBICLE OUTLINE DRAWING #2 | FA | 2018-03-20 | 2018-06-20 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2018-10-05 | 180545-FC STAMPED | FC | 1 | A | ELECTRICAL | STG ELECTRICAL
DHI | TG_ELEC&INC | 김강현 | MRT-YK09-P3MKC-230001 | 1495 | EXCITATION CUBICLE OUTLINE DRAWING #3,4 | FA | 2018-03-20 | 2018-06-20 | 2024-01-08 | 2024-01-08 | MRT-DS-REC-TT-240001 | AB | Z0 | 2024-07-18 | MTW-AS-C-LT-24.5537.0 | AB | Z0 | A | ELECTRICAL | STG ELECTRICAL
DHI | TG_ELEC&INC | 김강현 | MRT-YK09-P2MKC-230006 | 1496 | EXCITATION SYSTEM ELEMENTARY DIAGRAM #2 | FA | 2018-04-30 | 2018-07-30 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2018-10-05 | 180644-FC STAMPED | FC | 1 | A | ELECTRICAL | STG ELECTRICAL
DHI | TG_ELEC&INC | 김강현 | MRT-YK09-P3MKC-230006 | 1497 | EXCITATION SYSTEM ELEMENTARY DIAGRAM #3,4 | FA | 2018-04-30 | 2018-07-30 | 2024-01-08 | 2024-01-08 | MRT-DS-REC-TT-240001 | AB | Z0 | 2024-07-18 | MTW-AS-C-LT-24.5537.0 | AB | Z0 | A | ELECTRICAL | STG ELECTRICAL
DHI | TG_ELEC&INC | 김강현 | MRT-CQ03-P0MKC-230001 | 1498 | O&M MANUAL FOR EXCITATION SYSTEM | FI | 2019-04-30 | 2019-06-28 | 2019-05-09 | 2019-05-17 | MRT-DS-REC-TT-190120-FC | FC | 0 | 2019-05-17 | 190120-FC STAMPED | FC | 0 | A | SUPPORT | STG ELECTRICAL
DHI | TG_ELEC&INC | 정창수 | MRT-YK09-P2MKC-230002 | 1499 | DRAWINGS OF EXCITATION TRANSFORMER FOR ST #2 | FA | 2018-03-20 | 2018-06-20 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2018-12-14 | 180897-FC STAMPED | FC | 4 | A | ELECTRICAL | STG ELECTRICAL
DHI | TG_ELEC&INC | 정창수 | MRT-YK09-P3MKC-230002 | 1500 | DRAWINGS OF EXCITATION TRANSFORMER FOR ST #3,4 | FA | 2018-03-20 | 2018-06-20 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2024-07-16 | MTW-AS-C-LT-24.5529.0 | AB | Z0 | A | ELECTRICAL | STG ELECTRICAL
DHI | TG_ELEC&INC | 정창수 | MRT-YK09-P2MKC-230003 | 1501 | AC & DC BUSDUCT LAYOUT DRAWINGS #2 | FA | 2018-03-20 | 2018-06-20 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2019-02-02 | 190011-FC STAMPED | FC | 2 | A | ELECTRICAL | STG ELECTRICAL
DHI | TG_ELEC&INC | 정창수 | MRT-YK09-P3MKC-230003 | 1502 | AC & DC BUSDUCT LAYOUT DRAWINGS #3,4 | FA | 2018-03-20 | 2018-06-20 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2024-07-16 | MTW-AS-C-LT-24.5529.0 | AB | Z0 | A | ELECTRICAL | STG ELECTRICAL
DHI | TG_ELEC&INC | 정창수 | MRT-YU01-P2MKC-230010 | 1503 | SINGLE LINE DIAGRAMS INCLUDING GENERATOR CONTROL & PROTECTION #2 | FA | 2018-03-20 | 2018-07-30 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2018-10-10 | 180723-FC STAMPED | FC | 1 | A | ELECTRICAL | STG ELECTRICAL
DHI | TG_ELEC&INC | 정창수 | MRT-YU01-P3MKC-230010 | 1504 | SINGLE LINE DIAGRAMS INCLUDING GENERATOR CONTROL & PROTECTION #3,4 | FA | 2018-03-20 | 2018-07-30 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2024-07-16 | MTW-AS-C-LT-24.5529.0 | AB | Z0 | A | ELECTRICAL | STG ELECTRICAL
DHI | TG_ELEC&INC | 정창수 | MRT-YF00-P2MKC-230011 | 1505 | LOGIC DIAGRAMS OF GENERATOR PROTECTION PANEL FOR STG #2 | FI | 2018-04-30 | 2018-07-30 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2018-08-31 | 180360-FC STAMPED | FC | 0 | A | I&C | STG ELECTRICAL
DHI | TG_ELEC&INC | 정창수 | MRT-YF00-P3MKC-230011 | 1506 | LOGIC DIAGRAMS OF GENERATOR PROTECTION PANEL FOR STG #3,4 | FI | 2018-04-30 | 2018-07-30 | 2024-01-08 | 2024-01-08 | MRT-DS-REC-TT-240001 | AB | Z0 | 2024-07-18 | MTW-AS-C-LT-24.5537.0 | AB | Z0 | A | I&C | STG ELECTRICAL
DHI | TG_ELEC&INC | 정창수 | MRT-YS01-P2MKC-230012 | 1507 | SCHEMATIC DIAGRAMS FOR GENERATOR PROTECTION RELAY FOR STG #2 | FA | 2018-04-30 | 2018-07-30 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2018-12-17 | 180909-FC STAMPED | FC | 2 | A | ELECTRICAL | STG ELECTRICAL
DHI | TG_ELEC&INC | 정창수 | MRT-YS01-P3MKC-230012 | 1508 | SCHEMATIC DIAGRAMS FOR GENERATOR PROTECTION RELAY FOR STG #3,4 | FA | 2018-04-30 | 2018-07-30 | 2024-01-08 | 2024-01-08 | MRT-DS-REC-TT-240001 | AB | Z0 | 2024-07-18 | MTW-AS-C-LT-24.5537.0 | AB | Z0 | A | ELECTRICAL | STG ELECTRICAL
DHI | TG_ELEC&INC | 정창수 | MRT-YS01-P2MKC-230013 | 1509 | SCHEMATIC DIAGRAMS FOR GENERATOR METERING & SYNCHRO PANEL #2 | FA | 2018-04-30 | 2018-07-30 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2018-12-17 | 180909-FC STAMPED | FC | 2 | A | ELECTRICAL | STG ELECTRICAL
DHI | TG_ELEC&INC | 정창수 | MRT-YS01-P3MKC-230013 | 1510 | SCHEMATIC DIAGRAMS FOR GENERATOR METERING & SYNCHRO PANEL #3,4 | FA | 2018-04-30 | 2018-07-30 | 2024-01-08 | 2024-01-08 | MRT-DS-REC-TT-240001 | AB | Z0 | 2024-07-18 | MTW-AS-C-LT-24.5537.0 | AB | Z0 | A | ELECTRICAL | STG ELECTRICAL
DHI | TG_ELEC&INC | 정창수 | MRT-YS01-P2MKC-230014 | 1511 | SCHEMATIC DIAGRAMS FOR NGR AND NGTR PANEL FOR STG #2 | FA | 2018-04-30 | 2018-07-30 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2018-12-17 | 180910-FC STAMPED | FC | 3 | A | ELECTRICAL | STG ELECTRICAL
DHI | TG_ELEC&INC | 정창수 | MRT-YS01-P3MKC-230014 | 1512 | SCHEMATIC DIAGRAMS FOR NGR AND NGTR PANEL FOR STG #3,4 | FA | 2018-04-30 | 2018-07-30 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2024-07-16 | MTW-AS-C-LT-24.5529.0 | AB | Z0 | A | ELECTRICAL | STG ELECTRICAL
DHI | TG_ELEC&INC | 정창수 | MRT-YS01-P2MKC-230015 | 1513 | SCHEMATIC DIAGRAMS FOR PT SA PANEL FOR STG #2 | FA | 2018-05-17 | 2018-07-30 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2018-12-17 | 180910-FC STAMPED | FC | 2 | A | ELECTRICAL | STG ELECTRICAL
DHI | TG_ELEC&INC | 정창수 | MRT-YS01-P3MKC-230015 | 1514 | SCHEMATIC DIAGRAMS FOR PT SA PANEL FOR STG #3,4 | FA | 2018-05-17 | 2018-07-30 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2024-07-16 | MTW-AS-C-LT-24.5529.0 | AB | Z0 | A | ELECTRICAL | STG ELECTRICAL
DHI | TG_ELEC&INC | 정창수 | MRT-YS01-P3MKC-230017 | 1515 | SCHEMATIC DIAGRAMS FOR EMERGENCY SEAL OIL DC MOTOR STARTER PANEL #3,4 | FA | 2018-04-30 | 2018-07-30 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2024-07-16 | MTW-AS-C-LT-24.5529.0 | AB | Z0 | A | ELECTRICAL | STG ELECTRICAL
DHI | TG_ELEC&INC | 정창수 | MRT-CQ03-P0MKC-230002 | 1516 | O&M MANUAL FOR EXCITATION TRANSFORMER | FI | 2019-04-30 | 2019-06-28 | 2019-05-10 | 2019-05-21 | MRT-DS-REC-TT-190122-FC | FC | 0 | 2019-05-21 | 190122-FC STAMPED | FC | 0 | A | SUPPORT | STG ELECTRICAL
DHI | TG_ELEC&INC | 정창수 | MRT-CQ03-P0MKC-230012 | 1517 | O&M MANUAL FOR GENERATOR PROTECTION RELAY | FI | 2019-04-30 | 2019-06-28 | 2019-05-31 | 2019-06-22 | MRT-DS-REC-TT-190126-FC | FC | 0 | 2019-06-24 | 190126-FC STAMPED | FC | 0 | A | SUPPORT | STG ELECTRICAL
DHI | TG_ELEC&INC | 정창수 | MRT-CQ03-P0MKC-230013 | 1518 | O&M MANUAL FOR GENERATOR METERING & SYNCHRO PANEL | FI | 2019-04-30 | 2019-06-28 | 2019-05-31 | 2019-06-22 | MRT-DS-REC-TT-190126-FC | FC | 0 | 2019-06-24 | 190126-FC STAMPED | FC | 0 | A | SUPPORT | STG ELECTRICAL
DHI | TG_ELEC&INC | 정창수 | MRT-CQ03-P0MKC-230014 | 1519 | O&M MANUAL FOR NGTR PANEL | FI | 2019-04-30 | 2019-06-28 | 2019-05-10 | 2019-05-21 | MRT-DS-REC-TT-190122-FC | FC | 0 | 2019-05-21 | 190122-FC STAMPED | FC | 0 | A | SUPPORT | STG ELECTRICAL
DHI | TG_ELEC&INC | 정창수 | MRT-CQ03-P0MKC-230015 | 1520 | O&M MANUAL FOR PTSA PANEL | FI | 2019-04-30 | 2019-06-28 | 2019-05-10 | 2019-05-21 | MRT-DS-REC-TT-190122-FC | FC | 0 | 2019-05-21 | 190122-FC STAMPED | FC | 0 | A | SUPPORT | STG ELECTRICAL
DHI | TG_ELEC&INC | 정창수 | MRT-YT10-P2MKC-230016 | 1521 | PROTECTION RELAY SETTING DATA AND CALCULATION FOR STG #2 | FA | 2018-12-30 | 2019-04-30 | 2022-09-15 | 2022-09-15 | MRT-DS-REC-TT-220015 | FC | 1 | 2019-02-14 | 190014-FC STAMPED | FC | 0 | A | ELECTRICAL | STG ELECTRICAL
DHI | TG_ELEC&INC | 정창수 | MRT-YT10-P3MKC-230016 | 1522 | PROTECTION RELAY SETTING DATA AND CALCULATION FOR STG #3,4 | FA | 2018-12-30 | 2019-04-30 | 2019-02-11 | 2019-02-12 | MRT-DS-REC-TT-190014-FC | FC | 0 | 2019-02-14 | 190014-FC STAMPED | FC | 0 | A | ELECTRICAL | STG ELECTRICAL
DHI | TG_ELEC&INC | 정창수 | MRT-CQ03-P0MKC-230017 | 1523 | O&M MANUAL FOR ESOP MOTOR STARTER PANEL | FI | 2019-04-30 | 2019-06-28 | 2019-05-10 | 2019-05-21 | MRT-DS-REC-TT-190122-FC | FC | 0 | 2019-05-21 | 190122-FC STAMPED | FC | 0 | A | SUPPORT | STG ELECTRICAL