## DCL(Log)
DDCL Revision : A | [93 empty] | 127 | 128 | 129 | 130 | 131 | 132 | 132
Create Date: 2025-07-10
Class (주석 : DDCL, Non-design등) | Document Number | Title | Original Purpose | Revision |  |  | Status (주석 : DDCL의 Delay 표시 여부) | Plan |  |  |  | Actual |  |  |  | BG | Team | Workflow | Discipline | Engineer(Originator) | Additional Info. 1 | Additional Info. 2 | Additional Info. 3 | Additional Info. 4 | Additional Info. 5 | Additional Info. 6 | Additional Info. 7 | Additional Info. 8 | Additional Info. 9 | Additional Info. 10 | LatestIssue | [9 empty] | 1stIssue | [7 empty] | 2ndIssue | [7 empty] | 3rdIssue | [7 empty] | 4thIssue | [7 empty] | 5thIssue | [7 empty] | 6thIssue | [7 empty] | 7thIssue |  |  |  |  | 130: 8thIssue |  |  |  |  | 9thIssue | [7 empty] | 10thIssue | [7 empty] | 11thIssue | [7 empty] | 12thIssue | [7 empty] | DIDS URL | Latest DCN Status
[31 empty] | IssuetoClient |  |  |  |  | ReturnFromClient |  |  |  |  | IssuetoClient |  |  |  |  | ReturnFromClient |  |  | IssuetoClient |  |  |  |  | ReturnFromClient |  |  | IssuetoClient |  |  |  |  | ReturnFromClient |  |  | IssuetoClient |  |  |  |  | ReturnFromClient |  |  | IssuetoClient |  |  |  |  | ReturnFromClient |  |  | IssuetoClient |  |  |  |  | ReturnFromClient |  |  | IssuetoClient |  |  |  |  | 127: ReturnFromClient; 130: IssuetoClient |  | ReturnFromClient |  |  | IssuetoClient |  |  |  |  | ReturnFromClient |  |  | IssuetoClient |  |  |  |  | ReturnFromClient |  |  | IssuetoClient |  |  |  |  | ReturnFromClient |  |  | IssuetoClient |  |  |  |  | ReturnFromClient |  |  |  | Issue to Owner |  |  | Reply from Owner
|  |  |  | Latest Purpose | Latest Customer Revision | Latest Interal Revision |  | FA Start Date | FA End Date | FC Start Date | FC End Date | FA Start Date | FA End Date | FC Start Date | FC End Date | [15 empty] | DTNo. | Purpose | REV | Issued Date | Formal Issued Date | Received Date | DTNo. | Purpose | REV | Status | DTNo. | Purpose | REV | Issued Date | Formal Issued Date | Received Date | DTNo. | Status | DTNo. | Purpose | REV | Issued Date | Formal Issued Date | Received Date | DTNo. | Status | DTNo. | Purpose | REV | Issued Date | Formal Issued Date | Received Date | DTNo. | Status | DTNo. | Purpose | REV | Issued Date | Formal Issued Date | Received Date | DTNo. | Status | DTNo. | Purpose | REV | Issued Date | Formal Issued Date | Received Date | DTNo. | Status | DTNo. | Purpose | REV | Issued Date | Formal Issued Date | Received Date | DTNo. | Status | DTNo. | Purpose | REV | Issued Date | Formal Issued Date | Received Date | DTNo. | Status | DTNo. | Purpose | REV | Issued Date | Formal Issued Date | Received Date | DTNo. | Status | DTNo. | Purpose | REV | Issued Date | Formal Issued Date | Received Date | DTNo. | Status | DTNo. | Purpose | REV | Issued Date | Formal Issued Date | Received Date | DTNo. | Status | DTNo. | Purpose | REV | Issued Date | Formal Issued Date | Received Date | DTNo. | Status | DTNo. | Purpose | REV | Issued Date | Formal Issued Date | Received Date | DTNo. | Status |  | DCN No. | Rev | Date | DCN No. | Rev | Date | Status
DDCL | CCP-W-B111-01-ME-B06-0006 | GTG_P&ID Air Intake System Pulse Air Compressor Station | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-07 | 2024-06-24 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0218 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0218 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0218 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0218 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6A0B9AB09192463BAAFAF00E840E46B8
DDCL | CCP-W-B111-01-ME-B06-0003 | GTG_P&ID Air Intake System | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-07 | 2024-05-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D16CC490DC0D4B69B0BAB5F4BD033A3B
DDCL | CCP-W-B022-35-EL-B16-0002 | CABLE SPECIFICATION FOR POWER, CONTROL & FIBER OPTIC | D | D | 01 | _ |  | 2024-03-01 | 2024-04-01 | 2024-06-10 | 2024-07-11 | 2024-08-16 | 2024-08-19 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0434 | D | 01 | 2024-08-27 | 2024-08-28 | 2024-09-07 | CCP-PGU-TRM-EPC-0434 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0434 | D | 01 | 2024-08-27 | 2024-08-28 | 2024-09-07 | CCP-PGU-TRM-EPC-0434 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:403A6F800B324E41812089D6F8D2D8EA
DDCL | CCP-W-B111-01-ME-A11-0019 | GTG_System Description Combustion Chamber Instrumentation | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-29 | 2024-06-21 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3067FF7AA8E0424D8B8F0D414C99A8A8
DDCL | CCP-W-B023-35-EL-B13-0021 | 500/220KV AIS EQUIPMENT INSTALLATION DRAWING OF MAIN EQUIPMENT | D | D | 01 | _ |  | 2024-03-01 | 2024-04-01 | 2024-06-10 | 2024-07-11 | 2024-04-08 | 2024-04-25 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0135 | D | 01 | 2024-04-25 | 2024-04-25 | 2024-05-22 | CCP-PGU-TRM-EPC-0135 | D | 01 | Approved with comment | CCP-EPC-TRM-PGU-0135 | D | 01 | 2024-04-25 | 2024-04-25 | 2024-05-22 | CCP-PGU-TRM-EPC-0135 | Approved with comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E88F83585A6F46D88B9FF53418F0BF91
DDCL | CCP-W-B114-02-ME-B06-0011 | HRSG_P&ID - Blowdown System | D | D | 01 | _ |  | 2024-01-08 | 2024-03-22 | 2024-05-20 | 2024-06-20 | 2024-02-21 | 2024-05-07 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0140 | D | 01 | 2024-05-07 | 2024-05-08 | 2024-05-18 | CCP-PGU-TRM-EPC-0140 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0140 | D | 01 | 2024-05-07 | 2024-05-08 | 2024-05-18 | CCP-PGU-TRM-EPC-0140 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1A9AA0653DF749F199FAFE1D6059A849
DDCL | CCP-W-B114-02-ME-P02-0059 | HRSG_SB Pipe Supports - All Sections | D | D | 01 | _ |  | 2024-09-11 | 2024-11-11 | 2025-01-09 | 2025-02-09 | 2024-10-17 | 2024-10-17 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0492 | D | 01 | 2024-10-17 | 2024-10-21 | 2024-10-31 | CCP-PGU-TRM-EPC-0492 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0492 | D | 01 | 2024-10-17 | 2024-10-21 | 2024-10-31 | CCP-PGU-TRM-EPC-0492 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:0FB7CE3ADA824BC89755733A3D9D8B23
DDCL | CCP-W-B111-01-ME-A11-0015 | GTG_System Description Fuel Gas | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-29 | 2024-06-21 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E2F126331F8942E7A8C6A19A32E398BB
DDCL | CCP-W-B111-01-ME-A11-0020 | GTG_System Description FGS-Enclosure | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-29 | 2024-06-21 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1EFF3E0EE9C64B7E9C7A42F7F2585CC3
DDCL | CCP-W-B022-35-EL-E01-0002 | 220kV Relay Protection and Automation system | D | D | 01 | _ |  | 2024-03-18 | 2024-04-01 | 2024-04-10 | 2024-05-11 | 2024-12-26 | 2024-12-26 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0781 | D | 01 | 2024-12-27 | 2025-01-02 | 2025-01-12 | CCP-EPC-TRM-PGU-0781 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0781 | D | 01 | 2024-12-27 | 2025-01-02 | 2025-01-12 | CCP-EPC-TRM-PGU-0781 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A6878C515E444010A27D27200996230F
DDCL | CCP-W-B111-01-ME-A11-0018 | GTG_System Description Air Intake System | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-29 | 2024-06-21 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:30DAC775CB4641A9A2F7F9B5868C82A9
DDCL | CCP-W-B111-01-ME-B06-0013 | GTG_P&ID Combustion Chamber Instrumentation System | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-07 | 2024-05-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FC38A776F30E454993CEB20109EAC5C5
DDCL | CCP-W-B114-02-ME-B05-0023 | HRSG_LP Drum Drawings | D | D | 01 | _ |  | 2024-05-14 | 2024-07-14 | 2024-09-12 | 2024-10-12 | 2024-04-22 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:19A8D69AB3684952A93368C3A099A8DC
DDCL | CCP-W-B022-35-EL-B16-0701 | AUTO TRANSFORMER | D | D | 01 | _ |  | 2024-01-01 | 2024-02-01 | 2024-03-10 | 2024-04-10 | 2024-05-07 | 2024-05-10 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Auto Transformer | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0143 | D | 01 | 2024-05-10 | 2024-05-11 | 2024-05-21 | CCP-PGU-TRM-EPC-0143 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0143 | D | 01 | 2024-05-10 | 2024-05-11 | 2024-05-21 | CCP-PGU-TRM-EPC-0143 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1C7F59ED48B34BDEB11E2D28DF14F95B
DDCL | CCP-W-B111-01-ME-A11-0009 | GTG_System Description Hydraulic Oil For Inlet Guide Vanes | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-29 | 2024-06-21 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B6E71C92A9C14D28AE727420C53A4A76
DDCL | CCP-W-B111-01-ME-B06-0018 | GTG_P&ID Hydraulic Clearance Optimization System | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-07 | 2024-05-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:AE287FF3D1034222827CD0377E5DAE5A
DDCL | CCP-W-B111-01-ME-B05-0004 | GTG_Assembly Drawing - Hydraulic Clearance Optimization Skid | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-05-29 | 2024-06-24 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0217 | D | 01 | 2024-06-24 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0217 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0217 | D | 01 | 2024-06-24 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0217 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C7EC8404986E4C7B962AF09403F912D8
DDCL | CCP-W-B111-01-ME-B05-0008 | GTG_Assembly Drawing - Turning Device GT | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-05-29 | 2024-06-24 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0217 | D | 01 | 2024-06-24 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0217 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0217 | D | 01 | 2024-06-24 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0217 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:9066E22EC2D74A9B95D0F2B983F69855
DDCL | CCP-W-B111-01-ME-A11-0004 | GTG_System Description Lube Oil Cooler | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-29 | 2024-06-21 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:71762954987A4761B273E540FFC191CF
DDCL | CCP-W-B111-01-ME-B06-0017 | GTG_P&ID Hydraulic Supply System | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-07 | 2024-05-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2DE0084141E54BB9AB1269D5612A2F47
DDCL | CCP-W-B111-01-ME-E03-0003 | GTG_Interconnection Diagram SEE Transformer | D | D | 01 | _ |  | 2024-12-26 | 2025-01-10 | 2025-04-02 | 2025-04-10 | 2025-01-06 | 2025-01-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:0E6C6B8F83F4495AAFFC69E17556E969
DDCL | CCP-W-B114-02-ME-D02-0039 | HRSG_Typical Detail for Steel Structure | D | D | 01 | _ |  | 2024-03-15 | 2024-05-15 | 2024-07-15 | 2024-08-13 | 2024-04-09 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2DE84B3925264B63948A5A97C6B30105
DDCL | CCP-W-B022-35-EL-B16-0401 | 500/220KV AIS CAPACITOR VOLTAGE TRANSFORMER | D | C | 01 | _ |  | 2024-01-01 | 2024-02-01 | 2024-03-10 | 2024-04-10 | 2024-03-21 | 2024-03-25 | 2024-04-12 | 2024-04-15 | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0129 | C | 01 | 2024-04-15 | 2024-04-15 | 2024-05-22 | CCP-PGU-TRM-EPC-0129 | C | 01 | Approved | CCP-EPC-TRM-PGU-0118 | D | 01 | 2024-03-25 | 2024-03-26 | 2024-03-29 | CCP-PGU-TRM-EPC-0118 | Approved | CCP-EPC-TRM-PGU-0129 | C | 01 | 2024-04-15 | 2024-04-15 | 2024-05-22 | CCP-PGU-TRM-EPC-0129 | Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:61055F275E234BEB9716BCA4E1CEC9C4
DDCL | CCP-W-B022-35-EL-B16-0301 | 500/220KV AIS CURRENT TRANSFORMER | D | C | 02 | _ |  | 2024-01-01 | 2024-02-01 | 2024-03-10 | 2024-04-10 | 2024-03-21 | 2024-03-25 | 2024-04-12 | 2024-05-31 | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0167 | C | 02 | 2024-05-31 | 2024-06-04 | 2024-05-22 | CCP-PGU-TRM-EPC-0129 | C | 01 | Approved | CCP-EPC-TRM-PGU-0118 | D | 01 | 2024-03-25 | 2024-03-26 | 2024-03-29 | CCP-PGU-TRM-EPC-0118 | Approved | CCP-EPC-TRM-PGU-0129 | C | 01 | 2024-04-15 | 2024-04-15 | 2024-05-22 | CCP-PGU-TRM-EPC-0129 | Approved | CCP-EPC-TRM-PGU-0167 | C | 02 | 2024-05-31 | 2024-06-04 | [75 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A9D81EDF48894A55B64F3E02DD9AB131
DDCL | CCP-W-B111-01-ME-B06-0019 | GTG_P&ID Hydraulic Oil for Fuel Gas System | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-07 | 2024-05-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E3B873BBD2364D5B8CBE5463F3E6736F
DDCL | CCP-W-B022-35-EL-E28-0001 | ELECTRICAL LOAD & CONSUMPTION LIST for 500/220KV AIS | D | D | 01 | _ |  | 2023-12-15 | 2024-01-15 | 2024-04-10 | 2024-05-11 | 2024-02-16 | 2024-03-26 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0122 | D | 01 | 2024-03-27 | 2024-03-27 | 2024-04-03 | CCP-PGU-TRM-EPC-0122 | D | 01 | Approved | CCP-EPC-TRM-PGU-0119 CCP-EPC-TRM-PGU-0120 CCP-EPC-TRM-PGU-0122 | D | 01 | 2024-03-26 2024-03-27 2024-03-27 | 2024-03-26 2024-03-27 2024-03-27 | 2024-04-03 | CCP-PGU-TRM-EPC-0122 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:AC74AEDFC16C44C89A603EA59A6680CB
DDCL | CCP-W-B111-01-ME-E03-0002 | GTG_Interconnection Diagram SFC Transformer | D | D | 01 | _ |  | 2024-12-26 | 2025-01-10 | 2025-04-02 | 2025-04-10 | 2025-01-06 | 2025-01-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7385C2EDA35145D0A87A62A1590A909F
DDCL | CCP-W-B114-02-ME-B05-0080 | HRSG_Stack Expansion Joints | D | D | 01 | _ |  | 2024-04-15 | 2024-06-14 | 2024-08-12 | 2024-09-12 | 2024-04-09 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3B7603F3139A4409BC48263E8873F8F8
DDCL | CCP-W-B111-01-ME-B06-0011 | GTG_P&ID Blow Off System | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-07 | 2024-05-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E57C689C4FE84715BEB9797C855C4347
DDCL | CCP-W-B111-01-ME-B06-0008 | GTG_P&ID Automatic Compressor Cleaning System (ACCS) | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-07 | 2024-05-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:20839DE10AB9468DAF03D325D98F7505
DDCL | CCP-W-B111-01-ME-A11-0013 | GTG_System Description GT Drain | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-29 | 2024-06-21 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6FFAFB21172B4D43AD0EF07F2C3796E0
DDCL | CCP-W-B022-35-EL-E01-0004 | SCADA system | D | D | 01 | _ |  | 2024-03-01 | 2024-04-01 | 2024-04-10 | 2024-05-11 | 2024-12-26 | 2024-12-26 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0781 | D | 01 | 2024-12-27 | 2025-01-02 | 2025-01-12 | CCP-EPC-TRM-PGU-0781 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0781 | D | 01 | 2024-12-27 | 2025-01-02 | 2025-01-12 | CCP-EPC-TRM-PGU-0781 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3A2214198E6B4D2DBA08614FAE5AC26A
DDCL | CCP-W-B114-02-ME-E04-0090 | HRSG_Cabinets and JB Layout | D | D | 01 | _ |  | 2024-06-13 | 2024-08-13 | 2024-10-11 | 2024-11-11 | 2024-05-23 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:461F10C546654E29B5F1F353D0D159A9
DDCL | CCP-W-B022-35-EL-B16-0101 | 500/220KV AIS CIRCUIT BREAKER | D | D | 01 | _ |  | 2024-01-01 | 2024-02-01 | 2024-03-10 | 2024-04-10 | 2024-03-08 | 2024-03-25 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0119 | D | 01 | 2024-03-26 | 2024-03-26 | 2024-03-29 | CCP-PGU-TRM-EPC-0118 | D | 01 | Approved | CCP-EPC-TRM-PGU-0118 CCP-EPC-TRM-PGU-0119 | D | 01 | 2024-03-25 2024-03-26 | 2024-03-26 2024-03-26 | 2024-03-29 | CCP-PGU-TRM-EPC-0118 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B9C7FB0F6B14446F8B2C837A0A1DFCDD
DDCL | CCP-W-B022-35-EL-E28-0003 | I/O LIST - POWER PLANT INTERFACE PANEL AND AIS | R | C | 01 | _ |  | 2024-05-01 | 2024-06-01 | 2024-07-04 | 2024-07-11 | 2024-09-12 | 2025-02-04 | 2025-02-04 | 2025-02-04 | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:070C46431A0440E9801528A950B581B5
DDCL | CCP-W-B022-35-EL-B16-0901 | 500/220KV AIS LINE HARDWARE & FITTINGS | D | D | 01 | _ |  | 2024-03-01 | 2024-04-01 | 2024-06-10 | 2024-07-11 | 2024-07-15 | 2024-07-15 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0261 | D | 01 | 2024-07-15 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0261 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0261 | D | 01 | 2024-07-15 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0261 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4B7EDF7A09F34967A3F8154226E79609
DDCL | CCP-W-B111-01-ME-B01-0003 | GTG_General Arrangement Drawing for Piping | D | D | 01 | _ |  | 2024-01-26 | 2024-02-10 | 2024-05-02 | 2024-05-10 | 2024-05-29 | 2024-06-24 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0217 | D | 01 | 2024-06-24 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0217 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0217 | D | 01 | 2024-06-24 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0217 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:28B7D2F1A0B7499AA058D4EA63EFE8CB
DDCL | CCP-W-B055-14-ME-E13-0011 | CRANE_ELECTRIC DRAWING FOR OVERHEAD CRANE (STEAM TURBINE) | D | D | 01 | _ |  | 2024-05-15 | 2024-06-14 | 2024-10-15 | 2024-11-15 | 2024-06-21 | 2024-06-21 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Crane and hoist | Mechanical | 안성훈 | [10 empty] | CCP-EPC-TRM-PGU-0211 | D | 01 | 2024-06-21 | 2024-06-24 | 2024-07-04 | CCP-PGU-TRM-EPC-0211 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0211 | D | 01 | 2024-06-21 | 2024-06-24 | 2024-07-04 | CCP-PGU-TRM-EPC-0211 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:BBCEA02A20B442FDAE8E994A5A8F4BAB
DDCL | CCP-W-B022-35-EL-B18-0101 | AIS CONDUCTOR SIZING CALCULATION | D | C | 01 | _ |  | 2024-04-01 | 2024-05-02 | 2024-06-10 | 2024-07-11 | 2024-08-16 | 2024-08-19 | 2024-09-10 | 2024-09-10 | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E4630D59AF414B658A66A0DA705C2C42
DDCL | CCP-W-B053-23-ME-0002 | Equipment Arrangement Drawing for Warehouse Equipment | D | D | 01 | _ |  | 2024-03-26 | 2024-04-26 | 2024-08-31 | 2024-09-30 | 2024-03-05 | 2024-07-25 |  |  | BOP Plant | Plant EPC)기계기술2팀 | Workshop Equipment | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0310 | D | 01 | 2024-07-25 | 2024-07-26 | 2024-08-05 | CCP-PGU-TRM-EPC-0310 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0310 | D | 01 | 2024-07-25 | 2024-07-26 | 2024-08-05 | CCP-PGU-TRM-EPC-0310 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7BD7BAE64FCC4A64A90E651621436C0B
DDCL | CCP-W-B111-01-ME-E03-0007 | GTG_Interconnection Diagram Generator Current Transformer Neutral Side | D | D | 01 | _ |  | 2025-04-22 | 2025-05-07 | 2025-07-28 | 2025-08-05 | 2025-01-06 | 2025-01-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6AF2531B847A4E1187F91CA6DFA80843
DDCL | CCP-W-B114-02-ME-B05-0070 | HRSG_Piping Penetration Expansion Joints | D | D | 01 | _ |  | 2024-04-15 | 2024-06-14 | 2024-08-12 | 2024-09-12 | 2024-04-09 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5C7CADDE3A7448ADAB5ECC82968DA8DA
DDCL | CCP-W-B111-01-ME-A11-0010 | GTG_System Description Hydraulic Oil for Fuel Gas System | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-29 | 2024-06-21 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CBFC4B5F69D34E53AE2379844BB92F9A
DDCL | CCP-W-B114-02-ME-H09-0071 | HRSG_Protection System Diagram | D | D | 01 | _ |  | 2024-07-12 | 2024-09-12 | 2024-11-11 | 2024-12-11 | 2024-08-20 | 2024-09-09 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0472 | D | 01 | 2024-09-09 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0472 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0472 | D | 01 | 2024-09-09 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0472 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6475B98E93E34A258195D89C1C06033F
DDCL | CCP-W-B111-01-ME-A11-0016 | GTG_System Description Blow Off | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-29 | 2024-06-21 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2FC5D7C2C3564910A1643F3D19A451C7
DDCL | CCP-W-B111-01-ME-B01-0002 | GTG_General Arrangement Drawing for Auxiliaries | D | D | 01 | _ |  | 2024-05-29 | 2024-06-13 | 2024-09-03 | 2024-09-11 | 2024-05-29 | 2024-06-24 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0217 | D | 01 | 2024-06-24 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0217 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0217 | D | 01 | 2024-06-24 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0217 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:96E7E62528784D72A915BAE86081EEF0
DDCL | CCP-W-B114-02-ME-B33-0042 | HRSG_Foundation - Auxiliary | D | D | 01 | _ |  | 2024-02-05 | 2024-04-15 | 2024-06-15 | 2024-07-14 | 2024-09-24 | 2024-09-24 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0483 | D | 01 | 2024-09-24 | 2024-09-25 | 2024-10-05 | CCP-PGU-TRM-EPC-0483 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0483 | D | 01 | 2024-09-24 | 2024-09-25 | 2024-10-05 | CCP-PGU-TRM-EPC-0483 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8E12413678E144E4BFEC98BF4B7A6882
DDCL | CCP-W-B111-01-ME-A11-0002 | GTG_System Description Gas Turbine Instrumentation | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-29 | 2024-06-21 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3F85A8C77D544DDC98103A8144DC1490
DDCL | CCP-W-B022-35-EL-B16-0801 | 500/220KV AIS POST INSULATOR | D | D | 02 | _ |  | 2024-03-01 | 2024-04-01 | 2024-06-10 | 2024-07-11 | 2024-04-05 | 2024-06-11 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0181 | D | 02 | 2024-06-12 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0181 | D | 02 | Deemed Approved | CCP-EPC-TRM-PGU-0130 | D | 01 | 2024-04-16 | 2024-04-16 |  |  |  | CCP-EPC-TRM-PGU-0181 | D | 02 | 2024-06-12 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0181 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B6EA3069D0DE41399BA87D65851F3C93
DDCL | CCP-W-B022-35-EL-E13-0011 | 500KV/220KV AIS PROTECTION AND METERING SINGLE LINE DIAGRAM | D | D | 02 | _ |  | 2023-12-15 | 2024-01-15 | 2024-02-01 | 2024-03-03 | 2024-03-21 | 2024-04-16 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0134 | D | 02 | 2024-04-24 | 2024-04-25 | 2024-05-22 | CCP-PGU-TRM-EPC-0134 | D | 02 | Approved with comment | CCP-EPC-TRM-PGU-0119 CCP-EPC-TRM-PGU-0120 CCP-EPC-TRM-PGU-0122 | D | 01 | 2024-03-26 2024-03-27 2024-03-27 | 2024-03-26 2024-03-27 2024-03-27 | 2024-04-03 | CCP-PGU-TRM-EPC-0122 | Approved | CCP-EPC-TRM-PGU-0134 | D | 02 | 2024-04-24 | 2024-04-25 | 2024-05-22 | CCP-PGU-TRM-EPC-0134 | Approved with comment | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FADDE46DC44E4051A705A9B67BB293F2
DDCL | CCP-W-B114-02-ME-P02-0058 | HRSG_SB Pipe Supports - LP | D | D | 01 | _ |  | 2024-09-11 | 2024-11-11 | 2025-01-09 | 2025-02-09 | 2024-10-17 | 2024-10-17 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0492 | D | 01 | 2024-10-17 | 2024-10-21 | 2024-10-31 | CCP-PGU-TRM-EPC-0492 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0492 | D | 01 | 2024-10-17 | 2024-10-21 | 2024-10-31 | CCP-PGU-TRM-EPC-0492 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7BFFE7B847654210949C4A878E4BDF2C
DDCL | CCP-W-B000-42-EL-E04-0001 | OUTLINE DRAWING - FAULT MONITORING SYSTEM | D | D | 01 | _ |  | 2023-12-15 | 2024-01-26 | 2024-03-16 | 2024-04-08 | 2024-05-21 | 2024-07-01 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Protection & Metering System (Elec) | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0237 | D | 01 | 2024-07-01 | 2024-07-04 | 2024-07-14 | CCP-PGU-TRM-EPC-0237 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0237 | D | 01 | 2024-07-01 | 2024-07-04 | 2024-07-14 | CCP-PGU-TRM-EPC-0237 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:9AD3078878504ED6B8B74BBDD0DE8C10
DDCL | CCP-W-B111-01-ME-B06-0023 | GTG_P&ID FGS-Enclosure | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-07 | 2024-05-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:335468E68D45440FA100D823A0575197
DDCL | CCP-W-B022-35-EL-E04-0031 | AIS CONTROL BUILDING ELECTRICAL EQUIPMENT & PANEL LAYOUT(500kV/220kV) | D | D | 01 | _ |  | 2024-02-01 | 2024-03-03 | 2024-03-01 | 2024-04-01 | 2024-02-21 | 2024-03-26 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0122 | D | 01 | 2024-03-27 | 2024-03-27 | 2024-04-03 | CCP-PGU-TRM-EPC-0122 | D | 01 | Approved | CCP-EPC-TRM-PGU-0119 CCP-EPC-TRM-PGU-0120 CCP-EPC-TRM-PGU-0122 | D | 01 | 2024-03-26 2024-03-27 2024-03-27 | 2024-03-26 2024-03-27 2024-03-27 | 2024-04-03 | CCP-PGU-TRM-EPC-0122 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:00EC737E30E64287BD1D413DED414A70
DDCL | CCP-W-B111-01-ME-A11-0006 | GTG_System Description Instrument Air | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-29 | 2024-06-21 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1C24B594375347C98E609F939AA05DF3
DDCL | CCP-W-B114-02-ME-P02-0057 | HRSG_LB Pipe Supports - LP | D | D | 01 | _ |  | 2024-09-11 | 2024-11-11 | 2025-01-09 | 2025-02-09 | 2024-10-17 | 2024-10-17 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0492 | D | 01 | 2024-10-17 | 2024-10-21 | 2024-10-31 | CCP-PGU-TRM-EPC-0492 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0492 | D | 01 | 2024-10-17 | 2024-10-21 | 2024-10-31 | CCP-PGU-TRM-EPC-0492 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8AA932FD22614625B710761320BDAE04
DDCL | CCP-W-B022-35-EL-B16-0501 | 500/220KV AIS LIGHTNING ARRESTER | D | D | 01 | _ |  | 2024-01-01 | 2024-02-01 | 2024-03-10 | 2024-04-10 | 2024-03-11 | 2024-03-25 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0118 | D | 01 | 2024-03-25 | 2024-03-26 | 2024-03-29 | CCP-PGU-TRM-EPC-0118 | D | 01 | Approved | CCP-EPC-TRM-PGU-0118 | D | 01 | 2024-03-25 | 2024-03-26 | 2024-03-29 | CCP-PGU-TRM-EPC-0118 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F45F2D01884943ACA28D7CC8993ADE92
DDCL | CCP-W-B111-01-ME-B06-0021 | GTG_P&ID Instrument Air System | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-07 | 2024-05-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:520CC1EEF51248EDB687BBA849743B42
DDCL | CCP-W-B111-01-ME-B06-0015 | GTG_P&ID Lube Oil Cooler System | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-07 | 2024-05-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:79A85CF851774C4EBC94FBB6A2265FF4
DDCL | CCP-W-B114-02-ME-P01-0055 | HRSG_SB Piping Isometric Drawings - LP | D | D | 01 | _ |  | 2024-10-11 | 2024-12-11 | 2025-02-08 | 2025-03-08 | 2024-09-02 | 2024-09-09 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0472 | D | 01 | 2024-09-09 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0472 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0472 | D | 01 | 2024-09-09 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0472 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8D0F9ECCBFBF489EBD45ABE8B44A0DCE
DDCL | CCP-W-B022-35-EL-D06-0001 | STEEL STRUCTURE DESIGN CALCULATION (Gantry Tower & Beam) | D | D | 01 | _ |  | 2024-02-01 | 2024-03-03 | 2024-05-10 | 2024-06-10 | 2024-05-10 | 2024-05-14 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0145 | D | 01 | 2024-05-14 | 2024-05-14 | 2024-05-24 | CCP-PGU-TRM-EPC-0145 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0145 | D | 01 | 2024-05-14 | 2024-05-14 | 2024-05-24 | CCP-PGU-TRM-EPC-0145 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F7C1E041E43540E9BF841E021946FB3E
DDCL | CCP-W-B111-01-ME-B06-0007 | GTG_P&ID Air Intake System Pulseheader | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-07 | 2024-05-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:0BD07BDCB3534B389651C93B47FE63DB
DDCL | CCP-W-B022-35-EL-D02-0001 | STEEL STRUCTURES FOR GANTRY TOWER FRAME(POST) & BEAM FOR 500KV AIS | D | D | 01 | _ |  | 2024-02-01 | 2024-03-03 | 2024-05-10 | 2024-06-10 | 2024-04-08 | 2024-04-17 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0131 | D | 01 | 2024-04-17 | 2024-04-17 | 2024-04-27 | CCP-PGU-TRM-EPC-0131 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0131 | D | 01 | 2024-04-17 | 2024-04-17 | 2024-04-27 | CCP-PGU-TRM-EPC-0131 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D85715779BE44C91AF8AA8A5A333C49B
DDCL | CCP-W-B111-01-ME-B06-0009 | GTG_P&ID Hydraulic System Inlet Guide Vanes | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-07 | 2024-05-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4150D8AF1A5A461EB46564C651B4077E
DDCL | CCP-W-B022-35-EL-D07-0002 | BASE PLATE & ANCHOR BOLT ARRANGEMENT FOR AIS | D | D | 01 | _ |  | 2024-02-01 | 2024-03-03 | 2024-05-10 | 2024-06-10 | 2024-05-21 | 2024-08-08 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0153 | D | 01 | 2024-05-21 | 2024-05-22 | 2024-06-01 | CCP-PGU-TRM-EPC-0153 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0153 | D | 01 | 2024-05-21 | 2024-05-22 | 2024-06-01 | CCP-PGU-TRM-EPC-0153 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:641D126163664861959E3D73A10A881E
DDCL | CCP-W-B111-01-ME-B01-0001 | GTG_General Arrangement Drawing | D | D | 01 | _ |  | 2024-05-29 | 2024-06-13 | 2024-09-03 | 2024-09-11 | 2024-05-29 | 2024-06-24 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0217 | D | 01 | 2024-06-24 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0217 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0217 | D | 01 | 2024-06-24 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0217 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B5D5A5FFF14D45F98A974A04CAAEC003
DDCL | CCP-W-B111-01-ME-B05-0005 | GTG_Assembly Drawing - Dual Fuel Module | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-05-29 | 2024-06-24 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0217 | D | 01 | 2024-06-24 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0217 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0217 | D | 01 | 2024-06-24 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0217 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A68C2B7E29DB43FD9505842349894442
DDCL | CCP-W-B114-02-ME-H21-0073 | HRSG_Flow Elements | D | D | 01 | _ |  | 2024-07-12 | 2024-09-12 | 2024-11-11 | 2024-12-11 | 2024-08-20 | 2024-09-09 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0472 | D | 01 | 2024-09-09 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0472 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0472 | D | 01 | 2024-09-09 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0472 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A3D3430353B24D49A4FD130BAAB1F0EE
DDCL | CCP-W-B022-35-EL-E01-0001 | 500kV Relay Protection and Automation system | D | C | 01 | _ |  | 2024-03-01 | 2024-04-01 | 2024-04-10 | 2024-05-11 | 2025-04-25 | 2025-04-25 | 2025-07-08 | 2025-07-09 | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CBFAB386F60E4DBF8F034BCF686583BE
DDCL | CCP-W-B111-01-ME-B06-0001 | GTG_P&ID Legend of Symbols | D | D | 01 | _ |  | 2024-03-03 | 2024-03-18 | 2024-06-08 | 2024-06-16 | 2024-02-07 | 2024-05-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:DAC419AEBDE64F88B09B2B265C47F7E5
DDCL | CCP-W-B022-35-EL-B16-0003 | 500/220kV AIS ALUMINIUM CONDUCTOR | D | D | 01 | _ |  | 2024-04-01 | 2024-05-02 | 2024-06-10 | 2024-07-11 | 2024-07-15 | 2024-07-15 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0261 | D | 01 | 2024-07-15 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0261 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0261 | D | 01 | 2024-07-15 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0261 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:9B067767E5984F0A991070A5060363BE
DDCL | CCP-W-B111-01-ME-A11-0007 | GTG_System Description Ignition Gas | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-29 | 2024-06-21 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CA6B262016CB45C9949D3E32F5481946
DDCL | CCP-W-B111-01-ME-B05-0002 | GTG_Assembly Drawing - Instrument Air Skid | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-05-29 | 2024-06-24 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0217 | D | 01 | 2024-06-24 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0217 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0217 | D | 01 | 2024-06-24 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0217 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B01A5A94A7CF4A9086EEEA6C14EB8328
DDCL | CCP-W-B114-02-ME-B06-0001 | HRSG_P&ID - Symbology | D | D | 01 | _ |  | 2024-01-08 | 2024-03-22 | 2024-05-20 | 2024-06-20 | 2024-02-21 | 2024-05-07 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0140 | D | 01 | 2024-05-07 | 2024-05-08 | 2024-05-18 | CCP-PGU-TRM-EPC-0140 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0140 | D | 01 | 2024-05-07 | 2024-05-08 | 2024-05-18 | CCP-PGU-TRM-EPC-0140 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A33587CEC63747B5A8257774BD219885
DDCL | CCP-W-B055-14-ME-E13-0015 | HOIST_ELECTRIC DRAWING | D | D | 01 | _ |  | 2024-05-15 | 2024-06-14 | 2024-10-15 | 2024-11-15 | 2024-06-12 | 2024-06-12 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Crane and hoist | Mechanical | 안성훈 | [10 empty] | CCP-EPC-TRM-PGU-0183 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0183 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0183 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0183 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7119E045808241BF8F90FE3B7727CE4D
DDCL | CCP-W-B111-01-ME-A11-0017 | GTG_System Description Exhaust Gas System | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-29 | 2024-06-21 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3D55F876D0F44582A4EC831302AD8153
DDCL | CCP-W-B111-01-ME-A11-0012 | GTG_System Description Hydraulic Clearance Optimization | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-29 | 2024-06-21 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3E18C24434BF4C22B73FB29D720C54CB
DDCL | CCP-W-B022-35-EL-B16-0201 | 500/220KV AIS DISCONNECTOR SWITCH WITH 1 & 2 EARTH SWITCH | D | D | 02 | _ |  | 2024-01-01 | 2024-02-01 | 2024-03-10 | 2024-04-10 | 2024-03-11 | 2024-06-18 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0199 | D | 02 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0199 | D | 02 | Deemed Approved | CCP-EPC-TRM-PGU-0118 | D | 01 | 2024-03-25 | 2024-03-26 | 2024-03-29 | CCP-PGU-TRM-EPC-0118 | Approved | CCP-EPC-TRM-PGU-0199 | D | 02 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0199 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E0690DDDD1DB433D970D704360047C03
DDCL | CCP-W-B111-01-ME-B06-0022 | GTG_P&ID Pneumatic for Blow Off System | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-07 | 2024-05-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A8BE46F41FE84CF78A29A734E6915158
DDCL | CCP-W-B111-01-ME-B06-0014 | GTG_P&ID Fuel Gas System | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-07 | 2024-05-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:00EBC9D8B85B4CE29D5F9E09BDBF4A4B
DDCL | CCP-W-B114-02-ME-A07-0065 | HRSG_Protection System Description | D | D | 01 | _ |  | 2024-07-12 | 2024-09-12 | 2024-11-11 | 2024-12-11 | 2024-08-20 | 2024-09-09 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0472 | D | 01 | 2024-09-09 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0472 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0472 | D | 01 | 2024-09-09 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0472 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CFB276E3CD4F4A248085460D5B1137B8
DDCL | CCP-W-B111-01-ME-A11-0008 | GTG_System Description Hydraulic System | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-29 | 2024-06-21 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:50A1D61107AC4B4A8256E8D50B45A42C
DDCL | CCP-W-B022-35-EL-E18-0002 | 500/220KV AIS BATTERY & CHARGER SIZING CALCULATION | D | C | 01 | A |  | 2024-02-01 | 2024-03-03 | 2024-06-10 | 2024-07-11 | 2024-10-15 | 2024-10-15 | 2024-11-01 | 2025-06-12 | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D9B02C5ED07F4107A90ED14C64585269
DDCL | CCP-W-B000-42-EL-B19-0001 | CONFIGULATION- FAULT MONITORING SYSTEM | D | D | 01 | _ |  | 2023-11-29 | 2024-01-26 | 2024-03-16 | 2024-04-08 | 2024-05-21 | 2024-07-01 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Protection & Metering System (Elec) | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0237 | D | 01 | 2024-07-01 | 2024-07-04 | 2024-07-14 | CCP-PGU-TRM-EPC-0237 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0237 | D | 01 | 2024-07-01 | 2024-07-04 | 2024-07-14 | CCP-PGU-TRM-EPC-0237 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:70347116F7554EEBBB9BF1463A35AAD1
DDCL | CCP-W-B111-01-ME-B06-0010 | GTG_P&ID Exhaust System | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-07 | 2024-05-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:019D0A0EF5CA463590EA33DD520AC8E6
DDCL | CCP-W-B022-35-EL-E18-0001 | 500/220KV AIS CT & VT CALCULATION | D | C | 01 | _ |  | 2024-02-01 | 2024-03-03 | 2024-06-10 | 2024-07-11 | 2024-10-02 | 2024-10-07 | 2024-10-29 | 2024-10-30 | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8EDD6BC93D684DE4B350AC2C468F37C2
DDCL | CCP-W-B111-01-ME-B06-0004 | GTG_P&ID Air Intake System Air Pre Heater | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-07 | 2024-05-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6D6FDE36755D42A4B797031D42474BD9
DDCL | CCP-W-B022-35-EL-E21-0001 | 500/220KV AIS RELAY SETTING CALCULATION | D | C | 01 | _ |  | 2024-04-10 | 2024-05-11 | 2024-06-10 | 2024-07-11 | 2025-02-27 | 2025-02-27 | 2025-02-27 | 2025-02-27 | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:63E88E876895438AA879451B881457FB
DDCL | CCP-W-B022-35-EL-B19-0001 | CONFIGURATION DIAGRAM OF SCADA SYSTEM FOR 500/220kV AIS | D | D | 01 | _ |  | 2024-01-01 | 2024-02-01 | 2024-03-10 | 2024-04-10 | 2024-02-16 | 2024-03-26 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0122 | D | 01 | 2024-03-27 | 2024-03-27 | 2024-04-03 | CCP-PGU-TRM-EPC-0122 | D | 01 | Approved | CCP-EPC-TRM-PGU-0119 CCP-EPC-TRM-PGU-0120 CCP-EPC-TRM-PGU-0122 | D | 01 | 2024-03-26 2024-03-27 2024-03-27 | 2024-03-26 2024-03-27 2024-03-27 | 2024-04-03 | CCP-PGU-TRM-EPC-0122 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CBC4134E02D347B58CB9A6509319149B
DDCL | CCP-W-B022-35-EL-E14-0001 | 500/220KV AIS MAJOR RELAY LIST | D | D | 01 | _ |  | 2024-03-01 | 2024-04-01 | 2024-06-10 | 2024-07-11 | 2024-07-17 | 2024-07-17 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0287 | D | 01 | 2024-07-17 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0287 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0287 | D | 01 | 2024-07-17 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0287 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:99607AF96B2B407885A41EC85B1E8986
DDCL | CCP-W-B111-01-ME-B05-0003 | GTG_Assembly Drawing - Hydraulic Oil Skid | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-05-29 | 2024-06-24 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0217 | D | 01 | 2024-06-24 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0217 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0217 | D | 01 | 2024-06-24 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0217 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A7026E190D5342FEB6E6DF6B44B87944
DDCL | CCP-W-B111-01-ME-A11-0001 | GTG_System Description Automatic Compressor Cleaning System (ACC | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-29 | 2024-06-21 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8717197494FE480A8F184CBDA2920DFC
DDCL | CCP-W-B111-01-ME-A11-0005 | GTG_System Description Lube and Lifting Oil | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-29 | 2024-06-21 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F5AF58DBDFE44852AF755250A787AB76
DDCL | CCP-W-B053-23-ME-0004 | Equipment List & Specification for Warehouse Equipment | D | D | 01 | _ |  | 2024-03-26 | 2024-04-26 | 2024-08-31 | 2024-09-30 | 2024-03-05 | 2024-07-25 |  |  | BOP Plant | Plant EPC)기계기술2팀 | Chemical Dosing Skid | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0310 | D | 01 | 2024-07-25 | 2024-07-26 | 2024-08-05 | CCP-PGU-TRM-EPC-0310 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0310 | D | 01 | 2024-07-25 | 2024-07-26 | 2024-08-05 | CCP-PGU-TRM-EPC-0310 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FBB8712E647946499CC5E7F39AC9F487
DDCL | CCP-W-B111-01-ME-E03-0004 | GTG_Interconnection Diagram Generator Protection System 2; Synch | D | D | 01 | _ |  | 2024-12-26 | 2025-01-10 | 2025-04-02 | 2025-04-10 | 2025-01-06 | 2025-01-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2A72C6ADAF304B66AE56805D2DB0D1C5
DDCL | CCP-W-B114-02-ME-P05-0074 | HRSG_LB On-Off Valves - Assembly Drawings | D | D | 01 | _ |  | 2024-05-14 | 2024-07-14 | 2024-09-12 | 2024-10-12 | 2024-05-03 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2B8BB2A41AB54A059D9D99AFFF74CE54
DDCL | CCP-W-B111-01-ME-B05-0007 | GTG_Assembly Drawing - Automatic Compressor Cleaning Skid | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-05-29 | 2024-06-24 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0217 | D | 01 | 2024-06-24 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0217 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0217 | D | 01 | 2024-06-24 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0217 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:538F9D440B6D491CAE7F4972A34ACEC6
DDCL | CCP-W-B111-01-ME-B06-0002 | GTG_P&ID GT Instrumentation System | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-07 | 2024-06-24 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0218 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0218 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0218 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0218 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6C3E95961E284C7FA69A57D2ACB3E939
DDCL | CCP-W-B111-01-ME-E03-0005 | GTG_Interconnection Diagram Generator Protection System 1; Measu | D | D | 01 | _ |  | 2024-12-26 | 2025-01-10 | 2025-04-02 | 2025-04-10 | 2025-01-06 | 2025-01-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:47EAE3EF87B3480FAB0D64C5B1B34EF4
DDCL | CCP-W-B022-35-EL-E16-0001 | 500/220KV AIS SHORT CIRCUIT CALCULATION | D | D | 01 | _ |  | 2024-02-01 | 2024-03-03 | 2024-06-10 | 2024-07-11 | 2024-03-13 | 2024-03-26 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0122 | D | 01 | 2024-03-27 | 2024-03-27 | 2024-04-03 | CCP-PGU-TRM-EPC-0122 | D | 01 | Approved | CCP-EPC-TRM-PGU-0120 CCP-EPC-TRM-PGU-0122 | D | 01 | 2024-03-27 2024-03-27 | 2024-03-27 2024-03-27 | 2024-04-03 | CCP-PGU-TRM-EPC-0122 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:664C950B91E04958B5ABC33A8F339D91
DDCL | CCP-W-B111-01-ME-B06-0005 | GTG_P&ID Air Intake System Evaporative Cooler | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-07 | 2024-05-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:98D19224364F4FFDAF39621868C02CF9
DDCL | CCP-W-B111-01-ME-B06-0016 | GTG_P&ID Lube and Lifting Oil System | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-07 | 2024-05-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C797A2F3B9A54782BA35FEEA4D952C62
DDCL | CCP-W-B111-01-ME-B06-0012 | GTG_P&ID GT Drain System | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-07 | 2024-05-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:037D180F0AAD464DA631F0CDDECBDCC5
DDCL | CCP-W-B111-01-ME-B05-0006 | GTG_Assembly Drawing - Base Module | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-05-29 | 2024-06-24 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0217 | D | 01 | 2024-06-24 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0217 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0217 | D | 01 | 2024-06-24 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0217 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A98F427CF7E74AA2926FBD719971DA94
DDCL | CCP-W-B000-42-EL-E01-0001 | SCHEMATIC DAIGRAM - FAULT MONITORING SYSTEM | D | D | 01 | _ |  | 2023-12-15 | 2024-01-26 | 2024-03-16 | 2024-04-08 | 2024-06-03 | 2024-07-01 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Protection & Metering System (Elec) | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0237 | D | 01 | 2024-07-01 | 2024-07-04 | 2024-07-14 | CCP-PGU-TRM-EPC-0237 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0237 | D | 01 | 2024-07-01 | 2024-07-04 | 2024-07-14 | CCP-PGU-TRM-EPC-0237 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7B1F83AB0F444A3FBF1B34349454C961
DDCL | CCP-W-B111-01-ME-B06-0026 | GTG_P&ID Ignition Gas System | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-02-07 | 2024-05-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0256 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0256 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:61363934E138430BA8D246A2F4B07CF9
DDCL | CCP-W-B111-01-ME-E03-0006 | GTG_Interconnection Diagram Generator Neutral Point Grounding Cabinet | D | D | 01 | _ |  | 2024-12-26 | 2025-01-10 | 2025-04-02 | 2025-04-10 | 2025-01-06 | 2025-01-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8EA112DE1A4B4462AB4FACB4A38BC35A
DDCL | CCP-PW-B062-AC-515-0001 | LEB for Block #1_INTERIOR FINISH, DOOR AND WINDOW SCHEDULE | D | D | 02 | _ |  | 2024-02-07 | 2024-05-07 | 2024-05-17 | 2024-07-07 | 2024-03-29 | 2024-05-31 |  |  | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #1 | Architecture & Structure | 김홍재 | [10 empty] | CCP-EPC-TRM-PGU-0164 | D | 02 | 2024-05-31 | 2024-06-03 | 2024-06-10 | CCP-PGU-TRM-EPC-0164 | D | 02 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0164 | D | 02 | 2024-05-31 | 2024-06-03 | 2024-06-10 | CCP-PGU-TRM-EPC-0164 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:48116658C49B4DFDB7E1F8983B020C12
DDCL | CCP-PW-B062-AC-511-0001 | LEB for Block #1_FLOOR PLANS | D | D | 02 | _ |  | 2024-02-07 | 2024-05-07 | 2024-05-17 | 2024-07-07 | 2024-03-29 | 2024-05-31 |  |  | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #1 | Architecture & Structure | 김홍재 | [10 empty] | CCP-EPC-TRM-PGU-0164 | D | 02 | 2024-05-31 | 2024-06-03 | 2024-06-10 | CCP-PGU-TRM-EPC-0164 | D | 02 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0164 | D | 02 | 2024-05-31 | 2024-06-03 | 2024-06-10 | CCP-PGU-TRM-EPC-0164 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:511D38DBBD41479DA5BA4CD7BBEC4ED3
DDCL | CCP-PW-B062-AC-513-0001 | LEB for Block #1_MAIN SECTIONS | D | D | 02 | _ |  | 2024-02-07 | 2024-05-07 | 2024-05-17 | 2024-07-07 | 2024-03-29 | 2024-05-31 |  |  | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #1 | Architecture & Structure | 김홍재 | [10 empty] | CCP-EPC-TRM-PGU-0164 | D | 02 | 2024-05-31 | 2024-06-03 | 2024-06-10 | CCP-PGU-TRM-EPC-0164 | D | 02 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0164 | D | 02 | 2024-05-31 | 2024-06-03 | 2024-06-10 | CCP-PGU-TRM-EPC-0164 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E30236DF00564DA59764EAE7EEFB6DA5
DDCL | CCP-PW-B062-AC-512-0001 | LEB for Block #1_ELEVATIONS | D | D | 02 | _ |  | 2024-02-07 | 2024-05-07 | 2024-05-17 | 2024-07-07 | 2024-03-29 | 2024-05-31 |  |  | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #1 | Architecture & Structure | 김홍재 | [10 empty] | CCP-EPC-TRM-PGU-0164 | D | 02 | 2024-05-31 | 2024-06-03 | 2024-06-10 | CCP-PGU-TRM-EPC-0164 | D | 02 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0164 | D | 02 | 2024-05-31 | 2024-06-03 | 2024-06-10 | CCP-PGU-TRM-EPC-0164 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FE72E4C2B0104589BD86A8E3A1587093
DDCL | CCP-PW-B062-AC-514-0001 | LEB for Block #1_STAIRCASE PLAN & SECTION | D | D | 01 | _ |  | 2024-02-07 | 2024-05-07 | 2024-05-17 | 2024-07-07 | 2024-02-01 | 2024-02-06 |  |  | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #1 | Architecture & Structure | 김홍재 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:DFFE7865AE7244CAA8C871D29B3D2B07
DDCL | CCP-W-B062-AC-514-0002 | LEB for Block #1_TOILET & SHOWER ROOM PLAN & ELEVATION | D | C | 01 | _ |  | 2024-04-20 | 2024-07-19 | 2024-07-29 | 2024-09-18 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2024-09-27 | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #1 | Architecture & Structure | 김홍재 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D84FC5D64CDD4BEAA6976730AE94DCF9
DDCL | CCP-W-B062-AC-514-0003 | LEB for Block #1_WALL SECTION | D | C | 01 | _ |  | 2024-04-20 | 2024-07-19 | 2024-07-29 | 2024-09-18 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2024-09-27 | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #1 | Architecture & Structure | 김홍재 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7DB4829E5C8E40E8B1AC4A540CEB183A
DDCL | CCP-W-B062-AC-514-0004 | LEB for Block #1_OPENING PLAN & ELEVATION | D | C | 01 | _ |  | 2024-09-08 | 2024-12-07 | 2024-12-17 | 2025-02-06 | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #1 | Architecture & Structure | 김홍재 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:87822E54E1D74C9987F80E77F133C388
DDCL | CCP-W-B062-AC-514-0005 | LEB for Block #1_CEILING PLAN | D | C | 01 | _ |  | 2024-09-08 | 2024-12-07 | 2024-12-17 | 2025-02-06 | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #1 | Architecture & Structure | 김홍재 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:75D52E45289942C0A606F9C0E2822F3C
DDCL | CCP-W-B062-AC-514-0006 | LEB for Block #1_ARCHITECTURAL MISC. DETAIL | D | C | 01 | _ |  | 2024-09-08 | 2024-12-07 | 2024-12-17 | 2025-02-06 | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #1 | Architecture & Structure | 김홍재 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:33789EB199EF44B6A2840F004F4ACE1F
DDCL | CCP-PW-B062-AC-561-0001 | LEB for Block #1_STRUCTURAL MISC. DETAIL | D | D | 01 | _ |  | 2024-09-08 | 2024-12-07 | 2024-12-17 | 2025-02-06 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #1 | Architecture & Structure | 김홍재 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:91515668F52F4112B7F5DCFC878415B6
DDCL | CCP-PW-B062-AC-581-0002 | LEB for Block #1_PLUMBING SCHEMATIC DIAGRAM | D | D | 01 | _ |  | 2024-04-20 | 2024-07-19 | 2024-07-29 | 2024-09-18 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #1 | Architecture & Structure | 진백석 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:142FBA50D7FF4D88B230399CC9F54272
DDCL | CCP-PW-B062-AC-581-0003 | LEB for Block #1_PLUMBING EQUIPMENT DRAINAGE PLAN | D | D | 01 | _ |  | 2024-04-20 | 2024-07-19 | 2024-07-29 | 2024-09-18 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #1 | Architecture & Structure | 진백석 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:342678FEFC2F4610A7FDEA46D2F014AA
DDCL | CCP-PW-B062-AC-552-0001 | LEB for Block #1_FOUNDATION ARRANGEMENT PLAN | D | D | 01 | _ |  | 2024-04-20 | 2024-07-19 | 2024-07-29 | 2024-09-18 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #1 | Architecture & Structure | 김홍재 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:000BD6F64012413983F1AA9E8F329884
DDCL | CCP-PW-B062-AC-554-0001 | LEB for Block #1_FLOOR FRAMING PLANS | D | D | 01 | _ |  | 2024-04-20 | 2024-07-19 | 2024-07-29 | 2024-09-18 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #1 | Architecture & Structure | 김홍재 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:376EA53D03E947E6B4DE6D67E7B59472
DDCL | CCP-PW-B062-AC-556-0001 | LEB for Block #1_STAIRCASE FRAMING PLAN & ELEVATION | D | D | 01 | _ |  | 2024-04-20 | 2024-07-19 | 2024-07-29 | 2024-09-18 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #1 | Architecture & Structure | 김홍재 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B857845CD9C5407B89F2BA8AC0DA206A
DDCL | CCP-PW-B062-AC-555-0001 | LEB for Block #1_LINE & ROW FRAMING ELEVATION | D | D | 01 | _ |  | 2024-04-20 | 2024-07-19 | 2024-07-29 | 2024-09-18 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #1 | Architecture & Structure | 김홍재 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:842F4F4F5D364CC1AE4084089E2ACB40
DDCL | CCP-PW-B062-AC-559-0001 | LEB for Block #1_STRUCTURAL MEMBER RE-BAR DETAIL | D | D | 01 | _ |  | 2024-04-20 | 2024-07-19 | 2024-07-29 | 2024-09-18 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #1 | Architecture & Structure | 김홍재 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2E014421C26D46A1BDABE6EB77742770
DDCL | CCP-PW-B264-AC-552-0001 | LEB for Block #2_FOUNDATION ARRANGEMENT PLAN | D | D | 01 | _ |  | 2024-04-20 | 2024-07-19 | 2024-07-29 | 2024-09-18 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #2 | Architecture & Structure | 김홍재 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5752E836326D484DADEAB889E40CB086
DDCL | CCP-W-B264-AC-514-0005 | LEB for Block #2_CEILING PLAN | D | C | 01 | _ |  | 2024-09-08 | 2024-12-07 | 2024-12-17 | 2025-02-06 | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #2 | Architecture & Structure | 김홍재 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:843B040053FB4914862DAA3DB7909C0E
DDCL | CCP-W-B264-AC-514-0006 | LEB for Block #2_ARCHITECTURAL MISC. DETAIL | D | C | 01 | _ |  | 2024-09-08 | 2024-12-07 | 2024-12-17 | 2025-02-06 | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #2 | Architecture & Structure | 김홍재 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:AE5A263FBC1B4160B5D11CAD8A944535
DDCL | CCP-PW-B264-AC-515-0001 | LEB for Block #2_INTERIOR FINISH, DOOR, WINDOW SCHEDULE | D | D | 02 | _ |  | 2024-02-07 | 2024-05-07 | 2024-05-17 | 2024-07-07 | 2024-04-03 | 2024-05-31 |  |  | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #2 | Architecture & Structure | 김홍재 | [10 empty] | CCP-EPC-TRM-PGU-0165 | D | 02 | 2024-05-31 | 2024-06-04 | 2024-06-14 | CCP-PGU-TRM-EPC-0165 | D | 02 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0165 | D | 02 | 2024-05-31 | 2024-06-04 | 2024-06-14 | CCP-PGU-TRM-EPC-0165 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FE17846EB8844555AC8028B777D55817
DDCL | CCP-PW-B264-AC-554-0001 | LEB for Block #2_FLOOR FRAMING PLANS | D | D | 01 | _ |  | 2024-04-20 | 2024-07-19 | 2024-07-29 | 2024-09-18 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #2 | Architecture & Structure | 김홍재 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6B5F0869B9044E698797BBB25F2BDE31
DDCL | CCP-PW-B264-AC-555-0001 | LEB for Block #2_LINE & ROW FRAMING ELEVATIONS | D | D | 01 | _ |  | 2024-04-20 | 2024-07-19 | 2024-07-29 | 2024-09-18 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #2 | Architecture & Structure | 김홍재 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:AB67BF791A304F9F8BCA44F75C74CCFB
DDCL | CCP-PW-B264-AC-559-0001 | LEB for Block #2_STRUCTURAL MEMBER RE-BAR DETAIL | D | D | 01 | _ |  | 2024-04-20 | 2024-07-19 | 2024-07-29 | 2024-09-18 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #2 | Architecture & Structure | 김홍재 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:293D41DA7AB748A698C1F0F3B334EC80
DDCL | CCP-PW-B264-AC-561-0001 | LEB for Block #2_STRUCTURAL MISC. DETAIL | D | D | 01 | _ |  | 2024-09-08 | 2024-12-07 | 2024-12-17 | 2025-02-06 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #2 | Architecture & Structure | 김홍재 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6B930C9FB2C445E29D710CDC907FFCA4
DDCL | CCP-PW-B264-AC-581-0002 | LEB for Block #2_PLUMBING SCHEMATIC DIAGRAM | D | D | 01 | _ |  | 2024-04-20 | 2024-07-19 | 2024-07-29 | 2024-09-18 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #2 | Architecture & Structure | 진백석 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5F33A0C14834439C97A5DCB18E7C7177
DDCL | CCP-PW-B264-AC-581-0003 | LEB for Block #2_PLUMBING EQUIPMENT DRAINAGE PLAN | D | D | 01 | _ |  | 2024-04-20 | 2024-07-19 | 2024-07-29 | 2024-09-18 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #2 | Architecture & Structure | 진백석 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8A4EEC2F25144009A8BAD71450FEB833
DDCL | CCP-PW-B264-AC-514-0001 | LEB for Block #2_STAIRCASE PLAN & SECTION | D | C | 02 | _ |  | 2024-04-20 | 2024-07-19 | 2024-07-29 | 2024-09-18 | 2024-08-21 | 2024-08-21 | 2024-10-25 |  | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #2 | Architecture & Structure | 김홍재 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2FA0B216D667446A815CFF6A2BC63B78
DDCL | CCP-PW-B264-AC-512-0001 | LEB for Block #2_ELEVATIONS | D | D | 02 | _ |  | 2024-02-07 | 2024-05-07 | 2024-05-17 | 2024-07-07 | 2024-04-03 | 2024-05-31 |  |  | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #2 | Architecture & Structure | 김홍재 | [10 empty] | CCP-EPC-TRM-PGU-0165 | D | 02 | 2024-05-31 | 2024-06-04 | 2024-06-14 | CCP-PGU-TRM-EPC-0165 | D | 02 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0165 | D | 02 | 2024-05-31 | 2024-06-04 | 2024-06-14 | CCP-PGU-TRM-EPC-0165 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E891C3AD84E144B3B699B8527EA5786E
DDCL | CCP-PW-B264-AC-513-0001 | LEB for Block #2_MAIN SECTIONS | D | D | 02 | _ |  | 2024-02-07 | 2024-05-07 | 2024-05-17 | 2024-07-07 | 2024-04-03 | 2024-05-31 |  |  | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #2 | Architecture & Structure | 김홍재 | [10 empty] | CCP-EPC-TRM-PGU-0165 | D | 02 | 2024-05-31 | 2024-06-04 | 2024-06-14 | CCP-PGU-TRM-EPC-0165 | D | 02 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0165 | D | 02 | 2024-05-31 | 2024-06-04 | 2024-06-14 | CCP-PGU-TRM-EPC-0165 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5593046D38564CF0A64C5B27AA7853C8
DDCL | CCP-W-B264-AC-514-0002 | LEB for Block #2_TOILET & SHOWER ROOM PLAN & ELEVATION | D | C | 01 | _ |  | 2024-09-08 | 2024-12-07 | 2024-12-17 | 2025-02-06 | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #2 | Architecture & Structure | 김홍재 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E1C7BB86A82A4844828D5B245A6A0921
DDCL | CCP-W-B264-AC-514-0003 | LEB for Block #2_WALL SECTION | D | C | 01 | _ |  | 2024-02-07 | 2024-05-07 | 2024-05-17 | 2024-07-07 | 2024-06-05 | 2024-08-23 | 2024-08-30 | 2024-08-30 | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #2 | Architecture & Structure | 김홍재 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4580BDBDACC1472C8580EAC5DFC9F954
DDCL | CCP-W-B264-AC-514-0004 | LEB for Block #2_OPENING PLAN & ELEVATION | D | C | 01 | _ |  | 2024-04-20 | 2024-07-19 | 2024-07-29 | 2024-09-18 | 2024-02-01 | 2024-08-21 | 2024-10-25 | 2024-10-25 | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #2 | Architecture & Structure | 김홍재 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:9CD91A0EC0BC4987A0A3AB69A13A95DB
DDCL | CCP-PW-B264-AC-556-0001 | LEB for Block #2_STAIRCASE FRAMING PLAN & SECTION | D | D | 01 | _ |  | 2024-04-20 | 2024-07-19 | 2024-07-29 | 2024-09-18 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #2 | Architecture & Structure | 김홍재 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:264D9F3A8CFC4C34AF34E737E18EE4F4
DDCL | CCP-PW-B264-AC-511-0001 | LEB for Block #2_FLOOR PLANS | D | D | 02 | _ |  | 2024-02-07 | 2024-05-07 | 2024-05-17 | 2024-07-07 | 2024-04-03 | 2024-05-31 |  |  | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #2 | Architecture & Structure | 김홍재 | [10 empty] | CCP-EPC-TRM-PGU-0165 | D | 02 | 2024-05-31 | 2024-06-04 | 2024-06-14 | CCP-PGU-TRM-EPC-0165 | D | 02 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0165 | D | 02 | 2024-05-31 | 2024-06-04 | 2024-06-14 | CCP-PGU-TRM-EPC-0165 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:543E497AC1FD4DD79CAA91D6E956885D
DDCL | CCP-PW-B061-AC-515-0001 | Main Building_INTERIOR FINISH, DOOR AND WINDOW SCHEDULE | D | D | 02 | _ |  | 2023-11-21 | 2024-03-20 | 2024-03-30 | 2024-05-20 | 2024-02-08 | 2024-05-08 |  |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 조성은 | [10 empty] | CCP-EPC-TRM-PGU-0142 | D | 02 | 2024-05-09 | 2024-05-09 | 2024-05-24 | CCP-PGU-TRM-EPC-0142 | D | 02 | Rejected | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0142 | D | 02 | 2024-05-09 | 2024-05-09 | 2024-05-24 | CCP-PGU-TRM-EPC-0142 | Rejected | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5BE3D14E188B495986920E636189462A
DDCL | CCP-PW-B061-AC-511-0001 | Main Building_FLOOR PLANS | D | D | 02 | _ |  | 2023-11-21 | 2024-03-20 | 2024-03-30 | 2024-05-20 | 2024-02-08 | 2024-05-08 |  |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 조성은 | [10 empty] | CCP-EPC-TRM-PGU-0142 | D | 02 | 2024-05-09 | 2024-05-09 | 2024-05-24 | CCP-PGU-TRM-EPC-0142 | D | 02 | Rejected | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0142 | D | 02 | 2024-05-09 | 2024-05-09 | 2024-05-24 | CCP-PGU-TRM-EPC-0142 | Rejected | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A5A2DE109EF24DB9948AF0486B34C16E
DDCL | CCP-PW-B061-AC-512-0001 | Main Building_MAIN ELEVATIONS | D | D | 02 | _ |  | 2023-11-21 | 2024-03-20 | 2024-03-30 | 2024-05-20 | 2024-02-08 | 2024-05-08 |  |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 조성은 | [10 empty] | CCP-EPC-TRM-PGU-0142 | D | 02 | 2024-05-09 | 2024-05-09 | 2024-05-24 | CCP-PGU-TRM-EPC-0142 | D | 02 | Rejected | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0142 | D | 02 | 2024-05-09 | 2024-05-09 | 2024-05-24 | CCP-PGU-TRM-EPC-0142 | Rejected | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:9D264CF81F7542B8AD86E5A339F8CAB7
DDCL | CCP-PW-B061-AC-513-0001 | Main Building_MAIN SECTIONS | D | D | 02 | _ |  | 2023-11-21 | 2024-03-20 | 2024-03-30 | 2024-05-20 | 2024-02-08 | 2024-05-08 |  |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 조성은 | [10 empty] | CCP-EPC-TRM-PGU-0142 | D | 02 | 2024-05-09 | 2024-05-09 | 2024-05-24 | CCP-PGU-TRM-EPC-0142 | D | 02 | Rejected | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0142 | D | 02 | 2024-05-09 | 2024-05-09 | 2024-05-24 | CCP-PGU-TRM-EPC-0142 | Rejected | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B2BA10489021436689B9FCB15B2DD159
DDCL | CCP-W-B061-AC-514-0002 | Main Building_TOILET, SHOWER ROOM PLAN & ELEVATION | D | D | 01 | _ |  | 2023-11-21 | 2024-03-20 | 2024-03-30 | 2024-05-20 | 2024-03-18 | 2024-05-08 |  |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 조성은 | [10 empty] | CCP-EPC-TRM-PGU-0142 | D | 01 | 2024-05-09 | 2024-05-09 | 2024-05-19 | CCP-PGU-TRM-EPC-0142 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0142 | D | 01 | 2024-05-09 | 2024-05-09 | 2024-05-19 | CCP-PGU-TRM-EPC-0142 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:75BC310C2431400880241774943C6AE7
DDCL | CCP-W-B061-AC-514-0003 | Main Building_WALL SECTIONS | D | C | 01 | _ |  | 2024-01-23 | 2024-05-22 | 2024-06-01 | 2024-07-22 | 2024-05-03 |  | 2024-08-23 | 2024-08-26 | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 조성은 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CFA40A6595254CCFA04E73366BA0CB4D
DDCL | CCP-W-B061-AC-514-0004 | Main Building_OPENING PLAN & ELEVATION | D | C | 01 | _ |  | 2024-08-22 | 2024-12-20 | 2024-12-30 | 2025-02-19 |  |  | 2024-12-23 | 2024-12-23 | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 손선욱 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B068A062435D4AFDB92488F6D19D107D
DDCL | CCP-PW-B061-AC-561-0001 | Main Building_STEEL PLATFORM FRAMING PLAN & ELEVATION | D | D | 01 | _ |  | 2024-08-22 | 2024-12-20 | 2024-12-30 | 2025-02-19 | 2024-02-08 | 2024-02-06 |  |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 손선욱 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8C2E2F5F714C4C58980951CF13E8462C
DDCL | CCP-W-B061-AC-560-0001 | Main Building_STEEL CONNECTION DETAIL | D | C | 01 | _ |  | 2024-03-24 | 2024-07-22 | 2024-08-01 | 2024-09-21 | 2024-07-02 |  | 2024-09-09 | 2024-09-09 | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 조성은 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4B62BBE3DE224E74B9BA1828090477E1
DDCL | CCP-PW-B061-AC-558-0001 | Main Building_EQUIPMENT PAD ARRANGEMENT PLAN AND DETAIL | D | D | 01 | _ |  | 2024-08-22 | 2024-12-20 | 2024-12-30 | 2025-02-19 | 2024-02-08 | 2024-02-06 |  |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 손선욱 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:AA2DD694392C4C1B8A688BB3DFF93016
DDCL | CCP-PW-B061-AC-559-0001 | Main Building_STRUCTURAL MEMBER RE-BAR DETAIL | D | D | 01 | _ |  | 2023-12-17 | 2024-04-15 | 2024-04-25 | 2024-06-15 | 2024-02-08 | 2024-02-06 |  |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 조성은 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D7C41D2A2AC74C5395D313116D2D6162
DDCL | CCP-PW-B061-AC-561-0002 | Main Building_STRUCTURAL MISC. DETAIL | D | D | 01 | _ |  | 2024-08-22 | 2024-12-20 | 2024-12-30 | 2025-02-19 | 2024-02-08 | 2024-02-06 |  |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 손선욱 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2D83A2ACB54D4DF088CABDD439DAEDEC
DDCL | CCP-PW-B061-AC-581-0002 | Main Building_PLUMBING SCHEMATIC DIAGRAM | D | D | 01 | _ |  | 2024-01-06 | 2024-05-05 | 2024-05-15 | 2024-07-05 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 진백석 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:07A55101E18E40AB9ADC256B9CE7D666
DDCL | CCP-PW-B061-AC-581-0003 | Main Building_PLUMBING EQUIPMENT DRAINAGE PLAN | D | D | 01 | _ |  | 2024-01-06 | 2024-05-05 | 2024-05-15 | 2024-07-05 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 진백석 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C174F2A22AB0402489180D20D49C39BA
DDCL | CCP-PW-B061-AC-552-0003 | Main Building_REINFORCED CONCRETE FRAMING PLAN | R | C | 01 | A |  | 2023-12-17 | 2024-04-15 | 2024-04-25 | 2024-06-15 | 2024-05-03 | 2023-11-13 | 2024-07-24 |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 손선욱 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1B2A00B912404609B6A151C25136158E
DDCL | CCP-W-B061-AC-514-0006 | Main Building_ARCHITECTURAL MISC. DETAIL | D | C | 01 | _ |  | 2024-08-22 | 2024-12-20 | 2024-12-30 | 2025-02-19 |  |  | 2024-12-23 | 2024-12-23 | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 손선욱 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:DC01680D0153438AA30A2B8568A85F8D
DDCL | CCP-PW-B061-AC-552-0001 | Main Building_FOUNDATION ARRANGEMENT PLAN | D | D | 02 | _ |  | 2023-12-17 | 2024-04-15 | 2024-04-25 | 2024-06-15 | 2024-02-08 | 2024-04-24 |  |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 조성은 | [10 empty] | CCP-EPC-TRM-PGU-0136 | D | 02 | 2024-04-25 | 2024-04-25 | 2024-05-22 | CCP-PGU-TRM-EPC-0136 | D | 02 | Approved with comment | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0136 | D | 02 | 2024-04-25 | 2024-04-25 | 2024-05-22 | CCP-PGU-TRM-EPC-0136 | Approved with comment | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:EE72598814554B9796577024DDE7BFBD
DDCL | CCP-PW-B061-AC-552-0002 | Main Building_PEDESTAL ARRANGEMENT PLAN | D | D | 01 | _ |  | 2023-12-17 | 2024-04-15 | 2024-04-25 | 2024-06-15 | 2024-02-08 | 2024-02-06 |  |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 조성은 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:BEDA934056164C0C8795D0C96392C023
DDCL | CCP-PW-B061-AC-552-0004 | Main Building_REINFORCED CONCRETE FRAMING ELEVATIONS | D | D | 02 | _ |  | 2023-12-17 | 2024-04-15 | 2024-04-25 | 2024-06-15 | 2024-02-01 | 2024-04-24 |  |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 조성은 | [10 empty] | CCP-EPC-TRM-PGU-0136 | D | 02 | 2024-04-25 | 2024-04-25 | 2024-05-22 | CCP-PGU-TRM-EPC-0136 | D | 02 | Approved with comment | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0136 | D | 02 | 2024-04-25 | 2024-04-25 | 2024-05-22 | CCP-PGU-TRM-EPC-0136 | Approved with comment | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A35065CD808047CB9B1B110954EC2B08
DDCL | CCP-PW-B061-AC-552-0005 | Main Building_FOUNDATION & COLUMN RE-BAR | D | D | 01 | _ |  | 2023-12-17 | 2024-04-15 | 2024-04-25 | 2024-06-15 | 2024-02-08 | 2024-02-06 |  |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 조성은 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FE5B630C0F894C5E9055C1B2D5192AB7
DDCL | CCP-PW-B061-AC-553-0001 | Main Building_COLUMN ARRANGEMENT PLAN(HRSG AREA) | D | D | 02 | _ |  | 2024-01-23 | 2024-05-22 | 2024-06-01 | 2024-07-22 | 2024-02-01 | 2024-05-14 |  |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 조성은 | [10 empty] | CCP-EPC-TRM-PGU-0147 | D | 02 | 2024-05-14 | 2024-05-15 | 2024-05-25 | CCP-PGU-TRM-EPC-0147 | D | 02 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0147 | D | 02 | 2024-05-14 | 2024-05-15 | 2024-05-25 | CCP-PGU-TRM-EPC-0147 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E6161BB6A8224CD9843CA99A549F2227
DDCL | CCP-PW-B061-AC-554-0001 | Main Building_FLOOR FRAMING PLANS(HRSG AREA) | D | D | 02 | _ |  | 2024-01-23 | 2024-05-22 | 2024-06-01 | 2024-07-22 | 2024-02-01 | 2024-05-14 |  |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 조성은 | [10 empty] | CCP-EPC-TRM-PGU-0147 | D | 02 | 2024-05-14 | 2024-05-15 | 2024-05-25 | CCP-PGU-TRM-EPC-0147 | D | 02 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0147 | D | 02 | 2024-05-14 | 2024-05-15 | 2024-05-25 | CCP-PGU-TRM-EPC-0147 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5B99719F494A480992EF87D5DB4C192F
DDCL | CCP-PW-B061-AC-555-0001 | Main Building_LINE & ROW FRAMING ELEVATION(HRSG AREA) | D | D | 02 | _ |  | 2024-01-23 | 2024-05-22 | 2024-06-01 | 2024-07-22 | 2024-02-01 | 2024-05-14 |  |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 조성은 | [10 empty] | CCP-EPC-TRM-PGU-0147 | D | 02 | 2024-05-14 | 2024-05-15 | 2024-05-25 | CCP-PGU-TRM-EPC-0147 | D | 02 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0147 | D | 02 | 2024-05-14 | 2024-05-15 | 2024-05-25 | CCP-PGU-TRM-EPC-0147 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:0D5F6E737F9D40FFA8E72E3E04883A68
DDCL | CCP-PW-B061-AC-556-0001 | Main Building_STAIRCASE FRAMING PLAN & ELEVATION | D | D | 01 | _ |  | 2024-01-23 | 2024-05-22 | 2024-06-01 | 2024-07-22 | 2024-02-08 | 2024-02-06 |  |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 손선욱 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1122F45BBB9844EBBD21EFFCBAB3D22C
DDCL | CCP-PW-B061-AC-557-0001 | Main Building_PURLIN & GIRT ARRANGEMENT PLAN, ELEVATION AND DETAIL(HRSG AREA) | D | D | 02 | _ |  | 2024-01-23 | 2024-05-22 | 2024-06-01 | 2024-07-22 | 2024-02-01 | 2024-05-14 |  |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 조성은 | [10 empty] | CCP-EPC-TRM-PGU-0147 | D | 02 | 2024-05-14 | 2024-05-15 | 2024-05-25 | CCP-PGU-TRM-EPC-0147 | D | 02 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0147 | D | 02 | 2024-05-14 | 2024-05-15 | 2024-05-25 | CCP-PGU-TRM-EPC-0147 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F54CC88649F24949B9FF5D360CB4F61C
DDCL | CCP-PW-B061-AC-553-0002 | Main Building_COLUMN ARRANGEMENT PLAN(STG AREA) | D | D | 02 | _ |  | 2024-01-23 | 2024-05-22 | 2024-06-01 | 2024-07-22 | 2024-03-26 | 2024-05-16 |  |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 손선욱 | [10 empty] | CCP-EPC-TRM-PGU-0148 | D | 02 | 2024-05-16 | 2024-05-16 | 2024-05-26 | CCP-PGU-TRM-EPC-0148 | D | 02 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0148 | D | 02 | 2024-05-16 | 2024-05-16 | 2024-05-26 | CCP-PGU-TRM-EPC-0148 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:958E92EF1412466CB8843828E6982C96
DDCL | CCP-PW-B061-AC-553-0003 | Main Building_COLUMN ARRANGEMENT PLAN((GTG AREA) | D | D | 02 | _ |  | 2024-01-23 | 2024-05-22 | 2024-06-01 | 2024-07-22 | 2024-04-22 | 2024-05-14 |  |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 조성은 | [10 empty] | CCP-EPC-TRM-PGU-0146 | D | 02 | 2024-05-14 | 2024-05-15 | 2024-05-24 | CCP-PGU-TRM-EPC-0146 | D | 02 | Rejected | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0146 | D | 02 | 2024-05-14 | 2024-05-15 | 2024-05-24 | CCP-PGU-TRM-EPC-0146 | Rejected | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D9529B9FB5574931B79FA0C5196DE4BE
DDCL | CCP-PW-B061-AC-554-0002 | Main Building_FLOOR FRAMING PLANS(STG AREA) | D | D | 02 | _ |  | 2024-01-23 | 2024-05-22 | 2024-06-01 | 2024-07-22 | 2024-03-26 | 2024-05-16 |  |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 손선욱 | [10 empty] | CCP-EPC-TRM-PGU-0148 | D | 02 | 2024-05-16 | 2024-05-16 | 2024-05-26 | CCP-PGU-TRM-EPC-0148 | D | 02 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0148 | D | 02 | 2024-05-16 | 2024-05-16 | 2024-05-26 | CCP-PGU-TRM-EPC-0148 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5C3C62106F5640E0811B9B66B8213A49
DDCL | CCP-PW-B061-AC-555-0002 | Main Building_LINE & ROW FRAMING ELEVATION(STG AREA) | D | D | 02 | _ |  | 2024-01-23 | 2024-05-22 | 2024-06-01 | 2024-07-22 | 2024-03-26 | 2024-05-16 |  |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 손선욱 | [10 empty] | CCP-EPC-TRM-PGU-0148 | D | 02 | 2024-05-16 | 2024-05-16 | 2024-05-26 | CCP-PGU-TRM-EPC-0148 | D | 02 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0148 | D | 02 | 2024-05-16 | 2024-05-16 | 2024-05-26 | CCP-PGU-TRM-EPC-0148 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A65245EDC5B44154AE7F5C8BBB54AD3D
DDCL | CCP-PW-B061-AC-555-0003 | Main Building_LINE & ROW FRAMING ELEVATION(GTG AREA) | D | D | 02 | _ |  | 2024-01-23 | 2024-05-22 | 2024-06-01 | 2024-07-22 | 2024-04-22 | 2024-05-14 |  |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 조성은 | [10 empty] | CCP-EPC-TRM-PGU-0146 | D | 02 | 2024-05-14 | 2024-05-15 | 2024-05-24 | CCP-PGU-TRM-EPC-0146 | D | 02 | Rejected | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0146 | D | 02 | 2024-05-14 | 2024-05-15 | 2024-05-24 | CCP-PGU-TRM-EPC-0146 | Rejected | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:768076CE05D845768B518EB0856F9AE9
DDCL | CCP-PW-B061-AC-557-0002 | Main Building_PURLIN & GIRT ARRANGEMENT PLAN, ELEVATION AND DETAIL(STG AREA) | D | D | 02 | _ |  | 2024-01-23 | 2024-05-22 | 2024-06-01 | 2024-07-22 | 2024-03-26 | 2024-05-16 |  |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 손선욱 | [10 empty] | CCP-EPC-TRM-PGU-0148 | D | 02 | 2024-05-16 | 2024-05-16 | 2024-05-26 | CCP-PGU-TRM-EPC-0148 | D | 02 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0148 | D | 02 | 2024-05-16 | 2024-05-16 | 2024-05-26 | CCP-PGU-TRM-EPC-0148 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5CFF6E9626674D1BAFE24B412976998E
DDCL | CCP-PW-B061-AC-557-0003 | Main Building_PURLIN & GIRT ARRANGEMENT PLAN, ELEVATIONS AND DETAILS(GTG AREA) | D | D | 02 | _ |  | 2024-01-23 | 2024-05-22 | 2024-06-01 | 2024-07-22 | 2024-04-22 | 2024-05-14 |  |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 조성은 | [10 empty] | CCP-EPC-TRM-PGU-0146 | D | 02 | 2024-05-14 | 2024-05-15 | 2024-05-24 | CCP-PGU-TRM-EPC-0146 | D | 02 | Rejected | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0146 | D | 02 | 2024-05-14 | 2024-05-15 | 2024-05-24 | CCP-PGU-TRM-EPC-0146 | Rejected | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CEABB650C756434383030128B1552BD5
DDCL | CCP-W-B061-AC-514-0005 | Main Building_CEILING PLAN | D | C | 01 | _ |  | 2024-08-22 | 2024-12-20 | 2024-12-30 | 2025-02-19 |  |  | 2024-12-20 | 2024-12-20 | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 손선욱 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B0F9A498A95D4CBABBC372E3ACCBAE00
DDCL | CCP-PW-B061-AC-554-0003 | Main Building_FLOOR FRAMING PLANS(GTG AREA) | D | D | 02 | _ |  | 2024-01-23 | 2024-05-22 | 2024-06-01 | 2024-07-22 | 2024-04-22 | 2024-05-14 |  |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 조성은 | [10 empty] | CCP-EPC-TRM-PGU-0146 | D | 02 | 2024-05-14 | 2024-05-15 | 2024-05-24 | CCP-PGU-TRM-EPC-0146 | D | 02 | Rejected | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0146 | D | 02 | 2024-05-14 | 2024-05-15 | 2024-05-24 | CCP-PGU-TRM-EPC-0146 | Rejected | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B30AA3CC2743429CBE35C8BE3B78D6C7
DDCL | CCP-PW-B014-CV-HR-0003 | HEAT RECOVERY STEAM GENERATOR_EQUIPMENT PLAN & SECTION | D | C | 01 | _ |  | 2023-12-15 | 2024-03-14 | 2024-04-23 | 2024-05-03 | 2024-04-09 | 2024-02-06 | 2024-04-09 | 2024-05-27 | BOP Plant | Plant EPC)토목기술2팀 | HEAT RECOVERY STEAM GENERATOR FOUNDATION | Civil | De La VegaEdward Henry | [10 empty] | CCP-EPC-TRM-PGU-0157 | C | 01 | 2024-05-27 | 2024-05-28 | 2024-06-11 | CCP-PGU-TRM-EPC-0157 | C | 01 | Rejected | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0157 | C | 01 | 2024-05-27 | 2024-05-28 | 2024-06-11 | CCP-PGU-TRM-EPC-0157 | Rejected | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:BED9EF6088204042BDE4693C3506EBE9
DDCL | CCP-PW-B014-CV-HR-0006 | HEAT RECOVERY STEAM GENERATOR_RE-BAR DETAIL | D | C | 01 | _ |  | 2023-12-15 | 2024-03-14 | 2024-04-23 | 2024-05-03 | 2024-04-09 | 2024-02-06 | 2024-04-09 | 2024-05-27 | BOP Plant | Plant EPC)토목기술2팀 | HEAT RECOVERY STEAM GENERATOR FOUNDATION | Civil | De La VegaEdward Henry | [10 empty] | CCP-EPC-TRM-PGU-0157 | C | 01 | 2024-05-27 | 2024-05-28 | 2024-06-11 | CCP-PGU-TRM-EPC-0157 | C | 01 | Rejected | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0157 | C | 01 | 2024-05-27 | 2024-05-28 | 2024-06-11 | CCP-PGU-TRM-EPC-0157 | Rejected | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:351FDAB112624D80B44D46DEF91E4CFB
DDCL | CCP-PW-B014-CV-HR-0004 | HEAT RECOVERY STEAM GENERATOR_EXCAVATION PLAN & SECTION | D | C | 01 | _ |  | 2023-12-15 | 2024-03-14 | 2024-04-23 | 2024-05-03 | 2024-04-09 | 2024-02-06 | 2024-04-09 | 2024-05-27 | BOP Plant | Plant EPC)토목기술2팀 | HEAT RECOVERY STEAM GENERATOR FOUNDATION | Civil | De La VegaEdward Henry | [10 empty] | CCP-EPC-TRM-PGU-0157 | C | 01 | 2024-05-27 | 2024-05-28 | 2024-06-11 | CCP-PGU-TRM-EPC-0157 | C | 01 | Rejected | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0157 | C | 01 | 2024-05-27 | 2024-05-28 | 2024-06-11 | CCP-PGU-TRM-EPC-0157 | Rejected | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3FD1FA5EC1764D2CA04818800CB8578A
DDCL | CCP-PW-B014-CV-HR-0005 | HEAT RECOVERY STEAM GENERATOR_PLAN & SECTION | D | C | 01 | _ |  | 2023-12-15 | 2024-03-14 | 2024-04-23 | 2024-05-03 | 2024-04-09 | 2024-02-06 | 2024-04-09 | 2024-05-27 | BOP Plant | Plant EPC)토목기술2팀 | HEAT RECOVERY STEAM GENERATOR FOUNDATION | Civil | De La VegaEdward Henry | [10 empty] | CCP-EPC-TRM-PGU-0157 | C | 01 | 2024-05-27 | 2024-05-28 | 2024-06-11 | CCP-PGU-TRM-EPC-0157 | C | 01 | Rejected | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0157 | C | 01 | 2024-05-27 | 2024-05-28 | 2024-06-11 | CCP-PGU-TRM-EPC-0157 | Rejected | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D37B4C0179D5412E814DAE17FC32A7EB
DDCL | CCP-PW-B017-CV-IPB-0006 | ISOLATED PHASE BUS DUCT_RE-BAR DETAIL | D | C | 01 | A |  | 2024-03-12 | 2024-06-10 | 2024-07-20 | 2024-07-30 |  |  | 2024-09-26 | 2025-01-23 | BOP Plant | Plant EPC)토목기술2팀 | ISOLATED PHASE BUS DUCT FOUNDATION | Civil | 이정수 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A3368F1F3F0A4D799ED4ED64C111F283
DDCL | CCP-PW-B017-CV-IPB-0003 | ISOLATED PHASE BUS DUCT_LAYOUT PLAN | D | C | 01 | A |  | 2024-03-12 | 2024-06-10 | 2024-07-20 | 2024-07-30 |  |  | 2024-09-26 | 2025-01-23 | BOP Plant | Plant EPC)토목기술2팀 | ISOLATED PHASE BUS DUCT FOUNDATION | Civil | 이정수 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:53721DF579C54F34BFE765645FA58B50
DDCL | CCP-PW-B017-CV-IPB-0004 | ISOLATED PHASE BUS DUCT_EXCAVATION PLAN & SECTION | D | C | 01 | A |  | 2024-03-12 | 2024-06-10 | 2024-07-20 | 2024-07-30 |  |  | 2024-09-26 | 2025-01-23 | BOP Plant | Plant EPC)토목기술2팀 | ISOLATED PHASE BUS DUCT FOUNDATION | Civil | 이정수 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3058B31A492B4FA79463211ED33C64F9
DDCL | CCP-PW-B044-CV-FGS-0003 | FUEL GAS SYSTEM AREA_LAYOUT PLAN | D | D | 01 | _ |  | 2024-03-30 | 2024-06-28 | 2024-08-07 | 2024-08-17 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)토목기술2팀 | FUEL GAS SYSTEM AREA FOUNDATION | Civil | 임승덕 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:EBBDDAA706E94969A835A4801409D23F
DDCL | CCP-PW-B043-CV-BSDG-0003 | BLACK START DIESEL GENERATOR_EQUIPMENT PLAN & SECTION | D | C | 01 | A |  | 2024-01-02 | 2024-04-01 | 2024-05-11 | 2024-05-21 | 2024-05-20 | 2024-02-06 | 2024-05-20 |  | BOP Plant | Plant EPC)토목기술2팀 | BLACK START DIESEL GENERATOR FOUNDATION | Civil | 한정일 | [10 empty] | CCP-EPC-TRM-PGU-0172 | C | 01 | 2024-06-10 | 2024-06-11 | 2024-06-21 | CCP-PGU-TRM-EPC-0172 | C | 01 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0172 | C | 01 | 2024-06-10 | 2024-06-11 | 2024-06-21 | CCP-PGU-TRM-EPC-0172 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:591AB7DCEF6B45D89F0545FC08719E23
DDCL | CCP-PW-B032-CV-FFC-0006 | FIN FAN COOLER_RE-BAR DETAIL | D | D | 01 | _ |  | 2024-04-06 | 2024-07-05 | 2024-08-14 | 2024-08-24 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)토목기술2팀 | FIN FAN COOLER FOUNDATION | Civil | 한정일 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A6B37A0769D54B31A7F465904031580B
DDCL | CCP-PW-B043-CV-BSDG-0006 | BLACK START DIESEL GENERATOR_RE-BAR DETAIL | D | C | 01 | A |  | 2024-01-02 | 2024-04-01 | 2024-05-11 | 2024-05-21 | 2024-05-20 | 2024-02-06 | 2024-05-20 |  | BOP Plant | Plant EPC)토목기술2팀 | BLACK START DIESEL GENERATOR FOUNDATION | Civil | 한정일 | [10 empty] | CCP-EPC-TRM-PGU-0172 | C | 01 | 2024-06-10 | 2024-06-11 | 2024-06-21 | CCP-PGU-TRM-EPC-0172 | C | 01 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0172 | C | 01 | 2024-06-10 | 2024-06-11 | 2024-06-21 | CCP-PGU-TRM-EPC-0172 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C7C334AC6D904E9EACA538F834DFEB20
DDCL | CCP-PW-B044-CV-FGS-0006 | FUEL GAS SYSTEM AREA_RE-BAR DETAIL | D | D | 01 | _ |  | 2024-03-30 | 2024-06-28 | 2024-08-07 | 2024-08-17 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)토목기술2팀 | FUEL GAS SYSTEM AREA FOUNDATION | Civil | 임승덕 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C14DA79767F046B1B77BE2E0CDC36358
DDCL | CCP-PW-B032-CV-FFC-0003 | FIN FAN COOLER_EQUIPMENT PLAN & SECTION | D | D | 01 | _ |  | 2024-04-06 | 2024-07-05 | 2024-08-14 | 2024-08-24 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)토목기술2팀 | FIN FAN COOLER FOUNDATION | Civil | 한정일 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3269238601454DD8A4B9DA083C8FB256
DDCL | CCP-PW-B016-CV-ACC-0006 | AIR COOLED CONDENSER_RE-BAR DETAIL | D | D | 01 | _ |  | 2024-01-20 | 2024-04-19 | 2024-05-29 | 2024-06-08 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)토목기술2팀 | AIR COOLED CONDENSER FOUNDATION | Civil | 한정일 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:03D64408A11640C4A1FB71E85B41ADEC
DDCL | CCP-PW-B030-CV-FWF-0006 | FEEDWATER PUMP_RE-BAR DETAIL | D | C | 01 | _ |  | 2024-01-21 | 2024-04-20 | 2024-05-30 | 2024-06-09 | 2024-04-09 | 2024-02-06 | 2024-04-09 | 2024-05-30 | BOP Plant | Plant EPC)토목기술2팀 | FEEDWATER PUMP FOUNDATION | Civil | De La VegaEdward Henry | [10 empty] | CCP-EPC-TRM-PGU-0160 | C | 01 | 2024-05-30 | 2024-05-31 | 2024-06-10 | CCP-PGU-TRM-EPC-0160 | C | 01 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0160 | C | 01 | 2024-05-30 | 2024-05-31 | 2024-06-10 | CCP-PGU-TRM-EPC-0160 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:782E1DD7037B4B1EB1A43BA75ED349B0
DDCL | CCP-PW-B016-CV-ACC-0003 | AIR COOLED CONDENSER_EQUIPMENT PLAN & SECTION | D | D | 01 | _ |  | 2024-01-20 | 2024-04-19 | 2024-05-29 | 2024-06-08 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)토목기술2팀 | AIR COOLED CONDENSER FOUNDATION | Civil | 한정일 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:DDDAFE3A6AA04C089FDDE02FA6D35D2C
DDCL | CCP-PW-B030-CV-FWF-0003 | FEEDWATER PUMP_EQUIPMENT PLAN & SECTION | D | C | 01 | _ |  | 2024-01-21 | 2024-04-20 | 2024-05-30 | 2024-06-09 | 2024-04-09 | 2024-02-06 | 2024-04-09 | 2024-05-30 | BOP Plant | Plant EPC)토목기술2팀 | FEEDWATER PUMP FOUNDATION | Civil | De La VegaEdward Henry | [10 empty] | CCP-EPC-TRM-PGU-0160 | C | 01 | 2024-05-30 | 2024-05-31 | 2024-06-10 | CCP-PGU-TRM-EPC-0160 | C | 01 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0160 | C | 01 | 2024-05-30 | 2024-05-31 | 2024-06-10 | CCP-PGU-TRM-EPC-0160 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7A88545C87714AFEB86DE4987D87ED5C
DDCL | CCP-PW-B030-CV-FWF-0004 | FEEDWATER PUMP_EXCAVATION PLAN & SECTION | D | C | 01 | _ |  | 2024-01-21 | 2024-04-20 | 2024-05-30 | 2024-06-09 | 2024-04-09 | 2024-02-06 | 2024-04-09 | 2024-05-30 | BOP Plant | Plant EPC)토목기술2팀 | FEEDWATER PUMP FOUNDATION | Civil | De La VegaEdward Henry | [10 empty] | CCP-EPC-TRM-PGU-0160 | C | 01 | 2024-05-30 | 2024-05-31 | 2024-06-10 | CCP-PGU-TRM-EPC-0160 | C | 01 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0160 | C | 01 | 2024-05-30 | 2024-05-31 | 2024-06-10 | CCP-PGU-TRM-EPC-0160 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:98BFB1350E7E4802BBD2A3D3F3549DA3
DDCL | CCP-PW-B030-CV-FWF-0005 | FEEDWATER PUMP_PLAN & SECTION | D | C | 01 | _ |  | 2024-01-21 | 2024-04-20 | 2024-05-30 | 2024-06-09 | 2024-04-09 | 2024-02-06 | 2024-04-09 | 2024-05-30 | BOP Plant | Plant EPC)토목기술2팀 | FEEDWATER PUMP FOUNDATION | Civil | De La VegaEdward Henry | [10 empty] | CCP-EPC-TRM-PGU-0160 | C | 01 | 2024-05-30 | 2024-05-31 | 2024-06-10 | CCP-PGU-TRM-EPC-0160 | C | 01 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0160 | C | 01 | 2024-05-30 | 2024-05-31 | 2024-06-10 | CCP-PGU-TRM-EPC-0160 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D41EFC659DAD4BBE91989B1D76728A05
DDCL | CCP-PW-B016-CV-ACC-0004 | AIR COOLED CONDENSER_EXCAVATION PLAN & SECTION | D | D | 01 | _ |  | 2024-01-20 | 2024-04-19 | 2024-05-29 | 2024-06-08 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)토목기술2팀 | AIR COOLED CONDENSER FOUNDATION | Civil | 한정일 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A5191E7B04094BB8953402E84795B5CE
DDCL | CCP-PW-B016-CV-ACC-0005 | AIR COOLED CONDENSER_PLAN & SECTION | D | D | 01 | _ |  | 2024-01-20 | 2024-04-19 | 2024-05-29 | 2024-06-08 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)토목기술2팀 | AIR COOLED CONDENSER FOUNDATION | Civil | 한정일 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:ADDA371CB4B54FF38652907F1A1391DA
DDCL | CCP-PW-B032-CV-FFC-0004 | FIN FAN COOLER_EXCAVATION PLAN & SECTION | D | D | 01 | _ |  | 2024-04-06 | 2024-07-05 | 2024-08-14 | 2024-08-24 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)토목기술2팀 | FIN FAN COOLER FOUNDATION | Civil | 한정일 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:AB7FFCBBF55F49299727CFCD2806CDB9
DDCL | CCP-PW-B032-CV-FFC-0005 | FIN FAN COOLER_PLAN & SECTION | D | D | 01 | _ |  | 2024-04-06 | 2024-07-05 | 2024-08-14 | 2024-08-24 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)토목기술2팀 | FIN FAN COOLER FOUNDATION | Civil | 한정일 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:04CB21B29C224917AD9C597D739CD99D
DDCL | CCP-PW-B043-CV-BSDG-0004 | BLACK START DIESEL GENERATOR_EXCAVATION PLAN & SECTION | D | C | 01 | A |  | 2024-01-02 | 2024-04-01 | 2024-05-11 | 2024-05-21 | 2024-05-20 | 2024-02-06 | 2024-05-20 |  | BOP Plant | Plant EPC)토목기술2팀 | BLACK START DIESEL GENERATOR FOUNDATION | Civil | 한정일 | [10 empty] | CCP-EPC-TRM-PGU-0172 | C | 01 | 2024-06-10 | 2024-06-11 | 2024-06-21 | CCP-PGU-TRM-EPC-0172 | C | 01 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0172 | C | 01 | 2024-06-10 | 2024-06-11 | 2024-06-21 | CCP-PGU-TRM-EPC-0172 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B1F03F0A4DCA4591B7047AE34F4FD19F
DDCL | CCP-PW-B043-CV-BSDG-0005 | BLACK START DIESEL GENERATOR_PLAN & SECTION | D | C | 01 | A |  | 2024-01-02 | 2024-04-01 | 2024-05-11 | 2024-05-21 | 2024-05-20 | 2024-02-06 | 2024-05-20 |  | BOP Plant | Plant EPC)토목기술2팀 | BLACK START DIESEL GENERATOR FOUNDATION | Civil | 한정일 | [10 empty] | CCP-EPC-TRM-PGU-0172 | C | 01 | 2024-06-10 | 2024-06-11 | 2024-06-21 | CCP-PGU-TRM-EPC-0172 | C | 01 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0172 | C | 01 | 2024-06-10 | 2024-06-11 | 2024-06-21 | CCP-PGU-TRM-EPC-0172 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:589B9A7785F54AE2A9D1FC5EC1BF32E8
DDCL | CCP-PW-B044-CV-FGS-0004 | FUEL GAS SYSTEM AREA_EXCAVATION PLAN & SECTION | D | D | 01 | _ |  | 2024-03-30 | 2024-06-28 | 2024-08-07 | 2024-08-17 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)토목기술2팀 | FUEL GAS SYSTEM AREA FOUNDATION | Civil | 임승덕 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:34AB9A5E1627452DA27B9EDDB6162B2A
DDCL | CCP-PW-B044-CV-FGS-0005 | FUEL GAS SYSTEM AREA_PLAN & SECTION | D | D | 01 | _ |  | 2024-03-30 | 2024-06-28 | 2024-08-07 | 2024-08-17 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)토목기술2팀 | FUEL GAS SYSTEM AREA FOUNDATION | Civil | 임승덕 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:51AD6FE1A90C4AD99BA83831DB7F5CF9
DDCL | CCP-PW-B017-CV-IPB-0005 | ISOLATED PHASE BUS DUCT_PLAN & SECTION | D | C | 01 | A |  | 2024-03-12 | 2024-06-10 | 2024-07-20 | 2024-07-30 |  |  | 2024-09-26 | 2025-01-23 | BOP Plant | Plant EPC)토목기술2팀 | ISOLATED PHASE BUS DUCT FOUNDATION | Civil | 이정수 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C6EC400F983B49E2B573B581128513C1
DDCL | CCP-PW-B000-CV-EDB-0003 | CABLE ROUTE_LAYOUT PLAN | D | C | 01 | C |  | 2024-04-02 | 2024-07-01 | 2024-08-10 | 2024-08-20 |  |  | 2024-09-02 | 2025-05-15 | BOP Plant | Plant EPC)토목기술2팀 | CABLE ROUTE | Civil | 임승덕 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CC9D3C26862749D8BE9AF9E587CB3058
DDCL | CCP-PW-B000-CV-EDB-0006 | CABLE ROUTE_RE-BAR DETAIL | D | C | 01 | C |  | 2024-04-02 | 2024-07-01 | 2024-08-10 | 2024-08-20 |  |  | 2024-09-02 | 2025-05-15 | BOP Plant | Plant EPC)토목기술2팀 | CABLE ROUTE | Civil | 임승덕 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E3827F7D1BEF457A9453F8CBBBF6462E
DDCL | CCP-PW-B000-CV-EDB-0004 | CABLE ROUTE_EXCAVATION PLAN & SECTION | D | C | 01 | B |  | 2024-04-02 | 2024-07-01 | 2024-08-10 | 2024-08-20 |  |  | 2024-09-02 | 2025-02-27 | BOP Plant | Plant EPC)토목기술2팀 | CABLE ROUTE | Civil | 임승덕 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:0FF336BA2EE145ECB915DC9D6000AC9B
DDCL | CCP-PW-B000-CV-EDB-0005 | CABLE ROUTE_PLAN & SECTION | D | C | 01 | C |  | 2024-04-02 | 2024-07-01 | 2024-08-10 | 2024-08-20 |  |  | 2024-09-02 | 2025-05-15 | BOP Plant | Plant EPC)토목기술2팀 | CABLE ROUTE | Civil | 임승덕 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:30D0E5B45EB8473F94A64071E9EF3D18
DDCL | CCP-PW-B000-CV-PST-0006 | PIPE SLEEPER AND TRENCH_RE-BAR DETAIL | D | C | 01 | B |  | 2024-04-02 | 2024-07-01 | 2024-08-10 | 2024-08-20 |  |  | 2024-10-25 | 2025-05-14 | BOP Plant | Plant EPC)토목기술2팀 | PIPE SLEEPER AND TRENCH | Civil | 임승덕 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:12508B69AB8D4E4F99743BE263D3209D
DDCL | CCP-PW-B000-CV-PST-0003 | PIPE SLEEPER AND TRENCH_LAYOUT PLAN | D | C | 01 | B |  | 2024-04-02 | 2024-07-01 | 2024-08-10 | 2024-08-20 |  |  | 2024-10-25 | 2025-05-14 | BOP Plant | Plant EPC)토목기술2팀 | PIPE SLEEPER AND TRENCH | Civil | 임승덕 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:37270783A24F40AF8AC1E853B18AA0C2
DDCL | CCP-PW-B000-CV-PST-0004 | PIPE SLEEPER AND TRENCH_EXCAVATION PLAN & SECTION | D | C | 01 | B |  | 2024-04-02 | 2024-07-01 | 2024-08-10 | 2024-08-20 |  |  | 2024-10-25 | 2025-05-14 | BOP Plant | Plant EPC)토목기술2팀 | PIPE SLEEPER AND TRENCH | Civil | 임승덕 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5219AF3B14DF48EF94B55F03CC911CCD
DDCL | CCP-PW-B000-CV-PST-0005 | PIPE SLEEPER AND TRENCH_PLAN & SECTION | D | C | 01 | B |  | 2024-04-02 | 2024-07-01 | 2024-08-10 | 2024-08-20 |  |  | 2024-10-25 | 2025-05-14 | BOP Plant | Plant EPC)토목기술2팀 | PIPE SLEEPER AND TRENCH | Civil | 임승덕 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FACBF76A302A4DD4B53AFDF7FAF19737
DDCL | CCP-PW-B052-CV-EOT-0004 | EMERGENCY OIL UG TANK (500MVA AUTO TR & BSDG AREA)_EXCAVATION PLAN & SECTION | D | C | 01 | A |  | 2024-02-02 | 2024-05-02 | 2024-06-11 | 2024-06-21 |  |  | 2024-07-11 | 2025-02-07 | BOP Plant | Plant EPC)토목기술2팀 | EMERGENCY OIL UG TANK (500MVA AUTO TR & BSDG AREA) | Civil | 류형주 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3A9624D62126460FAF8B8148EC48CEFD
DDCL | CCP-PW-B052-CV-EOT-0005 | EMERGENCY OIL UG TANK (500MVA AUTO TR & BSDG AREA)_PLAN & SECTION | D | C | 01 | A |  | 2024-02-02 | 2024-05-02 | 2024-06-11 | 2024-06-21 |  |  | 2024-07-11 | 2025-02-07 | BOP Plant | Plant EPC)토목기술2팀 | EMERGENCY OIL UG TANK (500MVA AUTO TR & BSDG AREA) | Civil | 류형주 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:EB7C2FF44C8C4730A059330667B47153
DDCL | CCP-PW-B046-CV-DT-0005 | FUEL OIL FALSE START STORAGE TANK PIT_RE-BAR DETAIL | D | C | 01 | _ |  | 2024-02-24 | 2024-05-24 | 2024-07-03 | 2024-07-13 |  |  | 2024-08-23 | 2024-10-17 | BOP Plant | Plant EPC)토목기술2팀 | FUEL OIL FALSE START STORAGE TANK PIT | Civil | 류형주 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:AFA7D70F004745EBA463AB7A069DE661
DDCL | CCP-PW-B026-CV-SBS-0005 | STEAM BLOWING SILENCER_RE-BAR DETAIL | D | D | 01 | _ |  | 2024-04-29 | 2024-07-28 | 2024-09-06 | 2025-07-31 |  |  |  |  | BOP Plant | Plant EPC)토목기술2팀 | STEAM BLOWING SILENCER FOUNDATION | Civil | 임승덕 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A4912F8EE808463788C7D98C0B3A67B0
DDCL | CCP-PW-B052-CV-EOD-0006 | EMERGENCY OIL DRAIN PIT (STG, GTG & TR)_RE-BAR DETAIL | D | C | 01 | A |  | 2024-03-16 | 2024-06-14 | 2024-07-24 | 2024-08-03 |  |  | 2024-09-03 | 2025-04-15 | BOP Plant | Plant EPC)토목기술2팀 | EMERGENCY OIL DRAIN PIT (STG, GTG & TR) | Civil | 류형주 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7FDAC48089C84B91BFE827C38595512B
DDCL | CCP-PW-B052-CV-DT-0005 | DRAIN OIL TANK PIT_RE-BAR DETAIL | D | C | 01 | _ |  | 2024-02-24 | 2024-05-24 | 2024-07-03 | 2024-07-13 |  |  | 2024-08-27 | 2024-08-27 | BOP Plant | Plant EPC)토목기술2팀 | DRAIN OIL TANK PIT | Civil | 류형주 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:13DBE947D77A42849B1CB791F53C6177
DDCL | CCP-PW-B052-CV-EOD-0003 | EMERGENCY OIL DRAIN PIT (STG, GTG & TR)_LAYOUT PLAN | D | C | 01 | A |  | 2024-03-16 | 2024-06-14 | 2024-07-24 | 2024-08-03 |  |  | 2024-09-03 | 2025-04-15 | BOP Plant | Plant EPC)토목기술2팀 | EMERGENCY OIL DRAIN PIT (STG, GTG & TR) | Civil | 류형주 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7EA6ACB2DB954F1892DCB9C61C28811E
DDCL | CCP-PW-B000-CV-MIS-0004 | MISCELLANEOUS_RE-BAR DETAIL | D | C | 01 | A |  | 2024-05-29 | 2024-08-27 | 2024-10-06 | 2024-10-16 |  |  | 2025-02-18 | 2025-04-29 | BOP Plant | Plant EPC)토목기술2팀 | MISCELLANEOUS FOUNDATION | Civil | 류형주 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:0C68A17EB1D04983B66C80716ABDF646
DDCL | CCP-PW-B052-CV-EOT-0003 | EMERGENCY OIL UG TANK (500MVA AUTO TR & BSDG AREA)_LAYOUT PLAN | D | C | 01 | A |  | 2024-02-02 | 2024-05-02 | 2024-06-11 | 2024-06-21 |  |  | 2024-07-11 | 2025-02-07 | BOP Plant | Plant EPC)토목기술2팀 | EMERGENCY OIL UG TANK (500MVA AUTO TR & BSDG AREA) | Civil | 류형주 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6A8DAC9068B7442BBFF7E27DD8A97E18
DDCL | CCP-PW-B052-CV-EOD-0004 | EMERGENCY OIL DRAIN PIT (STG, GTG & TR)_EXCAVATION PLAN & SECTION | D | C | 01 | A |  | 2024-03-16 | 2024-06-14 | 2024-07-24 | 2024-08-03 |  |  | 2024-09-03 | 2025-04-15 | BOP Plant | Plant EPC)토목기술2팀 | EMERGENCY OIL DRAIN PIT (STG, GTG & TR) | Civil | 류형주 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:356DFE03CB874FF995EB0C21689E9BAC
DDCL | CCP-PW-B052-CV-EOD-0005 | EMERGENCY OIL DRAIN PIT (STG, GTG & TR)_PLAN & SECTION | D | C | 01 | A |  | 2024-03-16 | 2024-06-14 | 2024-07-24 | 2024-08-03 |  |  | 2024-09-03 | 2025-04-15 | BOP Plant | Plant EPC)토목기술2팀 | EMERGENCY OIL DRAIN PIT (STG, GTG & TR) | Civil | 류형주 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E1E3834D05664717A20EEC37EBC58201
DDCL | CCP-PW-B052-CV-DT-0003 | DRAIN OIL TANK PIT_EXCAVATION PLAN & SECTION | D | C | 01 | _ |  | 2024-02-24 | 2024-05-24 | 2024-07-03 | 2024-07-13 |  |  | 2024-08-27 | 2024-08-27 | BOP Plant | Plant EPC)토목기술2팀 | DRAIN OIL TANK PIT | Civil | 류형주 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E68DFE7A6390463C9BE3DAAE1B4CC5E7
DDCL | CCP-PW-B052-CV-DT-0004 | DRAIN OIL TANK PIT_PLAN & SECTION | D | C | 01 | _ |  | 2024-02-24 | 2024-05-24 | 2024-07-03 | 2024-07-13 |  |  | 2024-08-27 | 2024-08-27 | BOP Plant | Plant EPC)토목기술2팀 | DRAIN OIL TANK PIT | Civil | 류형주 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D1B60FD9A378479E811DB568E09B37E5
DDCL | CCP-PW-B046-CV-DT-0003 | FUEL OIL FALSE START STORAGE TANK PIT_EXCAVATION PLAN & SECTION | D | C | 01 | _ |  | 2024-02-24 | 2024-05-24 | 2024-07-03 | 2024-07-13 |  |  | 2024-08-23 | 2024-10-17 | BOP Plant | Plant EPC)토목기술2팀 | FUEL OIL FALSE START STORAGE TANK PIT | Civil | 류형주 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:79F8858D3D294FB5AC0D99C503E1A97F
DDCL | CCP-PW-B046-CV-DT-0004 | FUEL OIL FALSE START STORAGE TANK PIT_PLAN & SECTION | D | C | 01 | _ |  | 2024-02-24 | 2024-05-24 | 2024-07-03 | 2024-07-13 |  |  | 2024-08-23 | 2024-10-17 | BOP Plant | Plant EPC)토목기술2팀 | FUEL OIL FALSE START STORAGE TANK PIT | Civil | 류형주 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:383EAD4411EA460CBC80B9F2A9DC2AEC
DDCL | CCP-PW-B026-CV-SBS-0003 | STEAM BLOWING SILENCER_EXCAVATION PLAN & SECTION | D | D | 01 | _ |  | 2024-04-29 | 2024-07-28 | 2024-09-06 | 2024-09-16 |  |  |  |  | BOP Plant | Plant EPC)토목기술2팀 | STEAM BLOWING SILENCER FOUNDATION | Civil | 임승덕 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:849E6765D1AD4010B4CAF8318AA1D82D
DDCL | CCP-PW-B026-CV-SBS-0004 | STEAM BLOWING SILENCER_PLAN & SECTION | D | D | 01 | _ |  | 2024-04-29 | 2024-07-28 | 2024-09-06 | 2024-09-16 |  |  |  |  | BOP Plant | Plant EPC)토목기술2팀 | STEAM BLOWING SILENCER FOUNDATION | Civil | 임승덕 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4821AC35C1B0435891617038283B48C8
DDCL | CCP-PW-B000-CV-MIS-0003 | MISCELLANEOUS_PLAN & SECTION | D | C | 01 | A |  | 2024-05-29 | 2024-08-27 | 2024-10-06 | 2024-10-16 |  |  | 2025-02-18 | 2025-04-29 | BOP Plant | Plant EPC)토목기술2팀 | MISCELLANEOUS FOUNDATION | Civil | 류형주 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C727D50CD3DF454197DADCC472A403CD
DDCL | CCP-PW-B052-CV-EOT-0006 | EMERGENCY OIL UG TANK (500MVA AUTO TR & BSDG AREA)_RE-BAR DETAIL | D | C | 01 | A |  | 2024-02-02 | 2024-05-02 | 2024-06-11 | 2024-06-21 |  |  | 2024-07-11 | 2025-02-07 | BOP Plant | Plant EPC)토목기술2팀 | EMERGENCY OIL UG TANK (500MVA AUTO TR & BSDG AREA) | Civil | 류형주 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:0C192AC9AF18470CB3023846E2C3B899
DDCL | CCP-PW-B013-CV-ST-0003 | STEAM TURBINE GENERATOR_EQUIPMENT PLAN & SECTION | D | C | 01 | A |  | 2023-12-15 | 2024-03-14 | 2024-04-23 | 2024-05-03 | 2024-04-09 | 2024-02-06 | 2024-04-09 |  | BOP Plant | Plant EPC)토목기술2팀 | STEAM TURBINE GENERATOR FOUNDATION | Civil | De La VegaEdward Henry | [10 empty] | CCP-EPC-TRM-PGU-0163 | C | 01 | 2024-05-31 | 2024-05-31 | 2024-06-10 | CCP-PGU-TRM-EPC-0163 | C | 01 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0163 | C | 01 | 2024-05-31 | 2024-05-31 | 2024-06-10 | CCP-PGU-TRM-EPC-0163 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FD868AB30478425D8CA73772F50529DB
DDCL | CCP-PW-B011-CV-GT-0006 | GAS TURBINE GENERATOR_RE-BAR DETAIL | D | C | 01 | _ |  | 2024-01-02 | 2024-04-01 | 2024-05-11 | 2024-05-21 | 2024-04-09 | 2024-02-06 | 2024-04-09 | 2024-05-08 | BOP Plant | Plant EPC)토목기술2팀 | GAS TURBINE GENERATOR FOUNDATION | Civil | De La VegaEdward Henry | [10 empty] | CCP-EPC-TRM-PGU-0141 | C | 01 | 2024-05-08 | 2024-05-09 | 2024-05-24 | CCP-PGU-TRM-EPC-0141 | C | 01 | Rejected | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 |  |  |  | CCP-EPC-TRM-PGU-0141 | C | 01 | 2024-05-08 | 2024-05-09 | 2024-05-24 | CCP-PGU-TRM-EPC-0141 | Rejected | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5918CB58D7464AD0A7A722ACB7F2B3D9
DDCL | CCP-PW-B013-CV-ST-0006 | STEAM TURBINE GENERATOR_RE-BAR DETAIL | D | C | 01 | A |  | 2023-12-15 | 2024-03-14 | 2024-04-23 | 2024-05-03 | 2024-04-09 | 2024-02-06 | 2024-04-09 |  | BOP Plant | Plant EPC)토목기술2팀 | STEAM TURBINE GENERATOR FOUNDATION | Civil | De La VegaEdward Henry | [10 empty] | CCP-EPC-TRM-PGU-0163 | C | 01 | 2024-05-31 | 2024-05-31 | 2024-06-10 | CCP-PGU-TRM-EPC-0163 | C | 01 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0163 | C | 01 | 2024-05-31 | 2024-05-31 | 2024-06-10 | CCP-PGU-TRM-EPC-0163 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A19A1435E8C9457CA99C0BB865211012
DDCL | CCP-PW-B011-CV-GT-0005 | GAS TURBINE GENERATOR_PLAN & SECTION | D | C | 01 | _ |  | 2024-01-02 | 2024-04-01 | 2024-05-11 | 2024-05-21 | 2024-04-09 | 2024-02-06 | 2024-04-09 | 2024-05-08 | BOP Plant | Plant EPC)토목기술2팀 | GAS TURBINE GENERATOR FOUNDATION | Civil | De La VegaEdward Henry | [10 empty] | CCP-EPC-TRM-PGU-0141 | C | 01 | 2024-05-08 | 2024-05-09 | 2024-05-24 | CCP-PGU-TRM-EPC-0141 | C | 01 | Rejected | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 |  |  |  | CCP-EPC-TRM-PGU-0141 | C | 01 | 2024-05-08 | 2024-05-09 | 2024-05-24 | CCP-PGU-TRM-EPC-0141 | Rejected | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:77D144AF261D4D8084549F1113100354
DDCL | CCP-PW-B011-CV-GT-0003 | GAS TURBINE GENERATOR_EQUIPMENT PLAN & SECTION | D | C | 01 | _ |  | 2024-01-02 | 2024-04-01 | 2024-05-11 | 2024-05-21 | 2024-04-09 | 2024-02-06 | 2024-04-09 | 2024-05-08 | BOP Plant | Plant EPC)토목기술2팀 | GAS TURBINE GENERATOR FOUNDATION | Civil | De La VegaEdward Henry | [10 empty] | CCP-EPC-TRM-PGU-0141 | C | 01 | 2024-05-08 | 2024-05-09 | 2024-05-24 | CCP-PGU-TRM-EPC-0141 | C | 01 | Rejected | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 |  |  |  | CCP-EPC-TRM-PGU-0141 | C | 01 | 2024-05-08 | 2024-05-09 | 2024-05-24 | CCP-PGU-TRM-EPC-0141 | Rejected | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5C4D8FAE6278420182B169326F82D13E
DDCL | CCP-PW-B011-CV-GT-0004 | GAS TURBINE GENERATOR_EXCAVATION PLAN & SECTION | D | C | 01 | _ |  | 2024-01-02 | 2024-04-01 | 2024-05-11 | 2024-05-21 | 2024-04-09 | 2024-02-06 | 2024-04-09 | 2024-05-08 | BOP Plant | Plant EPC)토목기술2팀 | GAS TURBINE GENERATOR FOUNDATION | Civil | De La VegaEdward Henry | [10 empty] | CCP-EPC-TRM-PGU-0141 | C | 01 | 2024-05-08 | 2024-05-09 | 2024-05-24 | CCP-PGU-TRM-EPC-0141 | C | 01 | Rejected | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 |  |  |  | CCP-EPC-TRM-PGU-0141 | C | 01 | 2024-05-08 | 2024-05-09 | 2024-05-24 | CCP-PGU-TRM-EPC-0141 | Rejected | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:11C1DA97C7214F36BE7C8A8B1CC0A066
DDCL | CCP-PW-B013-CV-ST-0004 | STEAM TURBINE GENERATOR_EXCAVATION PLAN & SECTION | D | C | 01 | A |  | 2023-12-15 | 2024-03-14 | 2024-04-23 | 2024-05-03 | 2024-04-09 | 2024-02-06 | 2024-04-09 |  | BOP Plant | Plant EPC)토목기술2팀 | STEAM TURBINE GENERATOR FOUNDATION | Civil | De La VegaEdward Henry | [10 empty] | CCP-EPC-TRM-PGU-0163 | C | 01 | 2024-05-31 | 2024-05-31 | 2024-06-10 | CCP-PGU-TRM-EPC-0163 | C | 01 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0163 | C | 01 | 2024-05-31 | 2024-05-31 | 2024-06-10 | CCP-PGU-TRM-EPC-0163 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:744AFD167E4146F9BA9C85754C2FF810
DDCL | CCP-PW-B013-CV-ST-0005 | STEAM TURBINE GENERATOR_PLAN & SECTION | D | C | 01 | A |  | 2023-12-15 | 2024-03-14 | 2024-04-23 | 2024-05-03 | 2024-04-09 | 2024-02-06 | 2024-04-09 |  | BOP Plant | Plant EPC)토목기술2팀 | STEAM TURBINE GENERATOR FOUNDATION | Civil | De La VegaEdward Henry | [10 empty] | CCP-EPC-TRM-PGU-0163 | C | 01 | 2024-05-31 | 2024-05-31 | 2024-06-10 | CCP-PGU-TRM-EPC-0163 | C | 01 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0163 | C | 01 | 2024-05-31 | 2024-05-31 | 2024-06-10 | CCP-PGU-TRM-EPC-0163 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:119BDECBB2DE46369F8A403078427464
DDCL | CCP-PW-B072-EL-370-0001 | ELECTRICAL ROOM LAYOUT DRAWING - WORKSHOP & WAREHOUSE BUILDING | R | C | 01 | B |  | 2024-03-09 | 2024-03-29 | 2024-05-30 | 2024-06-30 | 2024-01-31 | 2023-10-12 | 2024-07-05 | 2025-02-05 | BOP Plant | Plant EPC)전력/배전기술2팀 | ROOM LAYOUT DRAWING | Electrical | 정백경 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D1ED7690483F40E89940A452006BD846
DDCL | CCP-PW-B164-EL-370-0001 | ELECTRICAL ROOM LAYOUT DRAWING - LEB FOR BLOCK #1 | D | D | 01 | _ |  | 2024-03-15 | 2024-03-29 | 2024-05-30 | 2024-06-30 | 2024-01-31 | 2024-03-25 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | ROOM LAYOUT DRAWING | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0117 | D | 01 | 2024-03-25 | 2024-03-26 | 2024-04-05 | CCP-PGU-TRM-EPC-0117 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0117 | D | 01 | 2024-03-25 | 2024-03-26 | 2024-04-05 | CCP-PGU-TRM-EPC-0117 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2CD89614523A4BA3A3421CB305EA1039
DDCL | CCP-PW-B264-EL-370-0001 | ELECTRICAL ROOM LAYOUT DRAWING - LEB FOR BLOCK #2 | D | D | 01 | _ |  | 2024-03-15 | 2024-03-29 | 2024-05-30 | 2024-06-30 | 2024-01-31 | 2024-03-25 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | ROOM LAYOUT DRAWING | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0117 | D | 01 | 2024-03-25 | 2024-03-26 | 2024-04-05 | CCP-PGU-TRM-EPC-0117 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0117 | D | 01 | 2024-03-25 | 2024-03-26 | 2024-04-05 | CCP-PGU-TRM-EPC-0117 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A58DC6229C8E40D096CFF5AC71ACF9A4
DDCL | CCP-PW-B161-EL-370-0001 | ELECTRICAL ROOM LAYOUT DRAWING - STG #1 LOCAL ELECTRICAL ROOM | D | D | 01 | _ |  | 2024-03-15 | 2024-03-29 | 2024-05-30 | 2024-06-30 | 2024-01-31 | 2024-03-25 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | ROOM LAYOUT DRAWING | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0117 | D | 01 | 2024-03-25 | 2024-03-26 | 2024-04-05 | CCP-PGU-TRM-EPC-0117 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0117 | D | 01 | 2024-03-25 | 2024-03-26 | 2024-04-05 | CCP-PGU-TRM-EPC-0117 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:52B46A29573C40FCAD18DB89CB42A56C
DDCL | CCP-PW-B261-EL-370-0001 | ELECTRICAL ROOM LAYOUT DRAWING - STG #2 LOCAL ELECTRICAL ROOM | D | D | 01 | _ |  | 2024-03-15 | 2024-03-29 | 2024-05-30 | 2024-06-30 | 2024-01-31 | 2024-03-25 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | ROOM LAYOUT DRAWING | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0117 | D | 01 | 2024-03-25 | 2024-03-26 | 2024-04-05 | CCP-PGU-TRM-EPC-0117 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0117 | D | 01 | 2024-03-25 | 2024-03-26 | 2024-04-05 | CCP-PGU-TRM-EPC-0117 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2AC3C68D138C448BB80E3EDFD855CC76
DDCL | CCP-PW-B169-EL-370-0001 | ELECTRICAL ROOM LAYOUT DRAWING - CONDENSATE EXTRACTION PUMP (CEP) BUILDING/w ACC LER | D | D | 01 | _ |  | 2024-03-15 | 2024-03-29 | 2024-05-30 | 2024-06-30 | 2024-01-31 | 2024-03-25 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | ROOM LAYOUT DRAWING | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0117 | D | 01 | 2024-03-25 | 2024-03-26 | 2024-04-05 | CCP-PGU-TRM-EPC-0117 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0117 | D | 01 | 2024-03-25 | 2024-03-26 | 2024-04-05 | CCP-PGU-TRM-EPC-0117 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C0F0678BC2214E44B500A0FD039632A0
DDCL | CCP-PW-B049-EL-370-0001 | ELECTRICAL ROOM LAYOUT DRAWING - WATER TREATMENT OF PROCESS AND DEMINERALIZED WATER ZLD PLANT BUILDING | R | C | 01 | B |  | 2024-03-15 | 2024-03-29 | 2024-05-30 | 2024-06-30 | 2024-01-31 | 2023-10-12 | 2024-07-05 | 2025-02-05 | BOP Plant | Plant EPC)전력/배전기술2팀 | ROOM LAYOUT DRAWING | Electrical | 정백경 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A67C5F81DC0A4199BEFC16D29163486D
DDCL | CCP-W-B000-EL-385-0002 | CALCULATION FOR GENERATOR CIRCUIT BREAKER | D | C | 01 | _ |  | 2024-02-09 | 2024-02-23 | 2024-05-17 | 2024-05-24 | 2024-07-15 | 2024-07-15 | 2024-09-10 | 2024-09-10 | BOP Plant | Plant EPC)전력/배전기술2팀 | Generator Circuit Breaker | Electrical | 이재욱 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4CC5E44F7A81438BAF3AE02C7FC54128
DDCL | CCP-W-B000-40-EL-E04-0001 | OUTLINE DRAWING FOR GENERATOR CIRCUIT BREAKER | D | D | 01 | _ |  | 2024-04-29 | 2024-07-28 | 2024-09-06 | 2024-09-16 | 2024-03-07 | 2024-03-28 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Generator Circuit Breaker | Electrical | 이재욱 | [10 empty] | CCP-EPC-TRM-PGU-0123 | D | 01 | 2024-03-28 | 2024-03-28 | 2024-04-03 | CCP-PGU-TRM-EPC-0123 | D | 01 | Approved | CCP-EPC-TRM-PGU-0123 | D | 01 | 2024-03-28 | 2024-03-28 | 2024-04-03 | CCP-PGU-TRM-EPC-0123 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5051FBE01025412D96BD208A53753B1C
DDCL | CCP-W-B000-40-EL-B16-0001 | TECHNICAL SPECIFICATION FOR GENERATOR CIRCUIT BREAKER | D | D | 01 | _ |  | 2024-04-29 | 2024-07-28 | 2024-09-06 | 2024-09-16 | 2024-03-07 | 2024-03-28 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Generator Circuit Breaker | Electrical | 이재욱 | [10 empty] | CCP-EPC-TRM-PGU-0123 | D | 01 | 2024-03-28 | 2024-03-28 | 2024-04-03 | CCP-PGU-TRM-EPC-0123 | D | 01 | Approved | CCP-EPC-TRM-PGU-0123 | D | 01 | 2024-03-28 | 2024-03-28 | 2024-04-03 | CCP-PGU-TRM-EPC-0123 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:891B1ABE69414CA8AE64A704D5F3B4C3
DDCL | CCP-W-B000-40-EL-E01-0001 | SCHEMATIC DIAGRAM FOR GENERATOR CIRCUIT BREAKER | D | D | 01 | _ |  | 2024-04-19 | 2024-05-10 | 2024-06-19 | 2024-07-10 | 2024-04-26 | 2024-06-12 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Generator Circuit Breaker | Electrical | 이재욱 | [10 empty] | CCP-EPC-TRM-PGU-0182 | D | 01 | 2024-06-12 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0182 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0182 | D | 01 | 2024-06-12 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0182 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:52EE8049C6284D779300F606A7FA8007
DDCL | CCP-W-B022-35-EL-E01-0003 | Auto Transformer Protection system | D | C | 01 | _ |  | 2024-12-01 | 2024-12-31 | 2025-01-01 | 2025-01-31 | 2025-04-23 | 2025-04-23 | 2025-06-23 | 2025-06-23 | BOP Plant | Plant EPC)전력/배전기술2팀 | Auto Transformer | Electrical | 정백경 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D64F8E936F254D81A4254596F9425E8F
DDCL | CCP-W-B022-35-EL-B16-0902 | 15.75KV LV EQUIPMENT FOR AUTO TRANSFORMER | D | D | 01 | _ |  | 2025-02-01 | 2025-02-28 | 2025-03-01 | 2025-03-31 | 2025-02-04 | 2025-02-04 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Auto Transformer | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0853 | D | 01 | 2025-02-04 | 2025-02-05 | 2025-02-10 | CCP-PGU-TRM-EPC-0853 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0853 | D | 01 | 2025-02-04 | 2025-02-05 | 2025-02-10 | CCP-PGU-TRM-EPC-0853 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:11A0A66187A24ABCA0425769628FA78F
DDCL | CCP-W-B023-35-EL-B13-0022 | AIS EQUIPMENT INSTALLATION DRAWING OF AUTO TR | D | C | 01 | _ |  | 2025-02-01 | 2025-02-28 | 2025-03-01 | 2025-03-31 | 2025-02-19 | 2025-02-20 | 2025-04-15 | 2025-04-15 | BOP Plant | Plant EPC)전력/배전기술2팀 | Auto Transformer | Electrical | 정백경 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:42747077C90E4354A924294706CDA69A
DDCL | CCP-W-B000-36-EL-E04-0001 | OUTLINE DRAWING FOR 10KV SWITCHBOARD | D | D | 01 | _ |  | 2023-12-22 | 2024-01-26 | 2024-03-22 | 2024-04-12 | 2024-03-04 | 2024-06-14 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 10kV Switchgear | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0189 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0189 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0189 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0189 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8B4179583F5240648FBF3DA0E2A34290
DDCL | CCP-W-B000-36-EL-B16-0001 | TECHNICAL SPECIFICATION FOR MV SWITCHBOARD | D | C | 01 | _ |  | 2023-12-22 | 2024-01-26 | 2024-03-22 | 2024-04-12 | 2024-04-22 | 2024-01-19 | 2024-04-22 | 2024-06-14 | BOP Plant | Plant EPC)전력/배전기술2팀 | 10kV Switchgear | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0188 | C | 01 | 2024-06-14 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0188 | C | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0090 | D | 01 | 2024-01-19 | 2024-01-19 | 2024-01-29 | CCP-PGU-TRM-EPC-0090 | Deemed Approved | CCP-EPC-TRM-PGU-0188 | C | 01 | 2024-06-14 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0188 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F15B450978CE43758D7433E0CE65E7DE
DDCL | CCP-PW-B000-36-EL-E13-0001 | SINGLE LINE DIAGRAM FOR 10KV SWITCHBOARD | D | D | 02 | _ |  | 2023-12-15 | 2024-01-05 | 2024-02-23 | 2024-03-15 | 2024-05-10 | 2024-06-14 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 10kV Switchgear | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0189 | D | 02 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0189 | D | 02 | Deemed Approved | CCP-EPC-TRM-PGU-0067 | D | 01 | 2023-10-30 | 2023-10-30 | 2023-11-09 | CCP-PGU-TRM-EPC-0067 | Deemed Approved | CCP-EPC-TRM-PGU-0189 | D | 02 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0189 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4343DECC67704145AD97E1B941709E1F
DDCL | CCP-W-B000-36-EL-E01-0001 | SCHEMATIC DIAGRAM FOR 10KV SWITCHBORD | D | D | 01 | _ |  | 2024-01-15 | 2024-02-05 | 2024-03-26 | 2024-04-16 | 2024-03-15 | 2024-06-14 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 10kV Switchgear | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0189 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0189 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0189 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0189 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:954F31111C6B49889E4DAA6861036B10
DDCL | CCP-W-B000-36-EL-E04-0003 | LAYOUT DRAWING FOR NON SEGREGATED PHASE BUSDUCT | D | D | 01 | _ |  | 2024-06-24 | 2024-09-30 | 2024-11-25 | 2025-03-25 | 2024-07-05 | 2024-07-08 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 0.4kV Switchgear | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0248 | D | 01 | 2024-07-08 | 2024-07-10 | 2024-07-20 | CCP-PGU-TRM-EPC-0248 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0248 | D | 01 | 2024-07-08 | 2024-07-10 | 2024-07-20 | CCP-PGU-TRM-EPC-0248 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:567312A830614E1A8E28BE53D743AD7E
DDCL | CCP-W-B000-36-EL-E04-0002 | OUTLINE DRAWING FOR 400V SWITCHBOARD AND MCC & DB | D | D | 01 | _ |  | 2024-02-02 | 2024-02-23 | 2024-03-26 | 2024-04-16 | 2024-03-04 | 2024-06-14 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 0.4kV Switchgear | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0189 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0189 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0189 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0189 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:18A776598EA54B8E8B367CEB6B77A899
DDCL | CCP-W-B000-36-EL-B16-0002 | TECHNICAL SPECIFICATION FOR LV SWITCHBOARD & MCC WITH LV TRANSFORMER | D | C | 01 | _ |  | 2023-12-22 | 2024-01-26 | 2024-03-22 | 2024-04-12 | 2024-04-22 | 2024-01-19 | 2024-04-22 | 2024-06-14 | BOP Plant | Plant EPC)전력/배전기술2팀 | 0.4kV Switchgear | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0188 | C | 01 | 2024-06-14 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0188 | C | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0090 | D | 01 | 2024-01-19 | 2024-01-19 | 2024-01-29 | CCP-PGU-TRM-EPC-0090 | Deemed Approved | CCP-EPC-TRM-PGU-0188 | C | 01 | 2024-06-14 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0188 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:73350C4CADF44E289371E43EC0C356EA
DDCL | CCP-W-B000-36-EL-B16-0003 | TECHNICAL SPECIFICATION FOR NON SEGREGATED PHASE BUSDUCT | D | D | 01 | _ |  | 2024-02-15 | 2024-02-29 | 2024-05-21 | 2024-05-28 | 2024-03-04 | 2024-06-14 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 0.4kV Switchgear | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0189 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0189 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0189 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0189 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:EE683B5F502448DA8137417841387721
DDCL | CCP-PW-B000-36-EL-E13-0002 | SINGLE LINE DIAGRAM FOR 400V SWITCHBOARD & MCC | D | D | 02 | _ |  | 2024-01-15 | 2024-02-05 | 2024-04-12 | 2024-05-03 | 2024-05-10 | 2024-06-14 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 0.4kV Switchgear | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0189 | D | 02 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0189 | D | 02 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0189 | D | 02 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0189 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8D90EFB4C6F443B6BBC0CEA3E6C3B805
DDCL | CCP-W-B000-36-EL-E01-0002 | SCHEMATIC DIAGRAM FOR 400V SWITCHBOARD | D | D | 01 | _ |  | 2024-03-03 | 2024-03-24 | 2024-05-03 | 2024-05-24 | 2024-03-15 | 2024-06-14 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 0.4kV Switchgear | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0189 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0189 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0189 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0189 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E9662EFF968445E39CDC42BDA52DFDFF
DDCL | CCP-W-B000-44-EL-E04-0001 | OUTLINE DRAWING FOR DC & UPS SYSTEM | D | D | 01 | _ |  | 2024-05-02 | 2024-06-13 | 2024-06-14 | 2024-07-12 | 2024-09-04 | 2024-09-04 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | DC & UPS | Electrical | 최준호 | [10 empty] | CCP-EPC-TRM-PGU-0464 | D | 01 | 2024-09-04 | 2024-09-06 | 2024-09-16 | CCP-PGU-TRM-EPC-0464 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0464 | D | 01 | 2024-09-04 | 2024-09-06 | 2024-09-16 | CCP-PGU-TRM-EPC-0464 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2725551119C7459481E8850B888D18F2
DDCL | CCP-W-B000-44-EL-B16-0001 | TECHNICAL SPECIFICATION FOR DC & UPS SYSTEMS | D | D | 01 | _ |  | 2024-04-08 | 2024-05-20 | 2024-05-21 | 2024-06-17 | 2024-11-01 | 2024-11-01 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | DC & UPS | Electrical | 최준호 | [10 empty] | CCP-EPC-TRM-PGU-0497 | D | 01 | 2024-11-01 | 2024-11-01 | 2024-11-11 | CCP-EPC-TRM-PGU-0497 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0497 | D | 01 | 2024-11-01 | 2024-11-01 | 2024-11-11 | CCP-EPC-TRM-PGU-0497 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:754C82C6D0F342EF9F607E8155B7CCC3
DDCL | CCP-W-B000-EL-385-0004 | SIZING CALCULATION FOR DC & UPS SYSTEMS | D | D | 01 | _ | FC DELAY | 2024-04-15 | 2024-05-27 | 2024-05-28 | 2024-06-24 | 2024-09-03 | 2024-09-04 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | DC & UPS | Electrical | 최준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:42476FD1C9EB493F95BC3B3698E0DD6D
DDCL | CCP-PW-B000-44-EL-E13-0001 | SINGLE LINE DIAGRAMS FOR DC & UPS SYSTEM | D | D | 01 | _ |  | 2024-04-15 | 2024-05-27 | 2024-05-28 | 2024-06-24 | 2024-09-04 | 2024-09-04 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | DC & UPS | Electrical | 최준호 | [10 empty] | CCP-EPC-TRM-PGU-0464 | D | 01 | 2024-09-04 | 2024-09-06 | 2024-09-16 | CCP-PGU-TRM-EPC-0464 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0464 | D | 01 | 2024-09-04 | 2024-09-06 | 2024-09-16 | CCP-PGU-TRM-EPC-0464 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:9834D58FD12748A1B56722FE7EDBAC11
DDCL | CCP-W-B000-44-EL-E01-0001 | SCHEMATIC DIAGRAMS FOR DC & UPS SYSTEM | D | D | 01 | _ |  | 2024-05-02 | 2024-06-13 | 2024-06-14 | 2024-07-12 | 2025-01-23 | 2025-01-23 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | DC & UPS | Electrical | 최준호 | [10 empty] | CCP-EPC-TRM-PGU-0847 | D | 01 | 2025-01-23 | 2025-02-05 | 2025-02-10 | CCP-PGU-TRM-EPC-0847 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0847 | D | 01 | 2025-01-23 | 2025-02-05 | 2025-02-10 | CCP-PGU-TRM-EPC-0847 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C6339F5122D04D44A7AD393D026525E3
DDCL | CCP-W-B022-41-EL-B16-0008 | TECHNICAL SPECIFICATION - PROTECTION RELAY PANEL | D | D | 01 | _ |  | 2023-11-10 | 2023-12-01 | 2024-02-16 | 2024-03-08 |  | 2023-11-29 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Protection & Metering System (Elec) | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0075 | D | 01 | 2023-11-29 | 2023-11-29 | 2023-12-14 | CCP-PGU-TRM-EPC-0075 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0075 | D | 01 | 2023-11-29 | 2023-11-29 | 2023-12-14 | CCP-PGU-TRM-EPC-0075 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C4C3A6D49CC346EFB727924E669C031D
DDCL | CCP-W-B000-42-EL-B16-0001 | TECHNICAL SPECIFICATION - FAULT MONITORING SYSTEM | D | D | 01 | _ |  | 2023-11-29 | 2024-01-26 | 2024-03-16 | 2024-04-08 | 2024-01-10 | 2024-01-10 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Protection & Metering System (Elec) | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0085 | D | 01 | 2024-01-11 | 2024-01-11 | 2024-01-26 | CCP-PGU-TRM-EPC-0085 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0085 | D | 01 | 2024-01-11 | 2024-01-11 | 2024-01-26 | CCP-PGU-TRM-EPC-0085 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:20AA2F23D34049629A914917348B389F
DDCL | CCP-W-B000-41-EL-E04-0001 | OUTLINE DRAWING - PROTECTION RELAY PANEL | D | D | 01 | _ |  | 2023-12-15 | 2024-01-26 | 2024-04-26 | 2024-05-17 | 2024-03-18 | 2024-07-01 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Protection & Metering System (Elec) | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0237 | D | 01 | 2024-07-01 | 2024-07-04 | 2024-07-14 | CCP-PGU-TRM-EPC-0237 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0237 | D | 01 | 2024-07-01 | 2024-07-04 | 2024-07-14 | CCP-PGU-TRM-EPC-0237 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:943D5C0B6B6A46D89A2B248E483EE936
DDCL | CCP-W-B000-41-EL-E01-0001 | SCHEMATIC DAIGRAM - PROTECTION RELAY PANEL | D | D | 01 | _ |  | 2023-12-15 | 2024-01-26 | 2024-04-26 | 2024-05-17 | 2024-03-18 | 2024-07-01 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Protection & Metering System (Elec) | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0237 | D | 01 | 2024-07-01 | 2024-07-04 | 2024-07-14 | CCP-PGU-TRM-EPC-0237 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0237 | D | 01 | 2024-07-01 | 2024-07-04 | 2024-07-14 | CCP-PGU-TRM-EPC-0237 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1CF1A09EDEAE412CB552101DA8B6F915
DDCL | CCP-W-B089-45-EL-B16-0001 | TECHNICAL SPECIFICATION FOR CABLE TRAY | D | C | 01 | A |  | 2024-03-01 | 2024-04-01 | 2024-04-30 | 2024-05-29 | 2025-01-07 | 2025-01-14 | 2025-02-06 | 2025-03-21 | BOP Plant | Plant EPC)전력/배전기술2팀 | Cable Tray | Electrical | 서정범 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F390402C271E45128F57B64A7B319DB3
DDCL | CCP-PW-B113-EL-371-0001 | CABLE TRAY LAYOUT FOR STG BUILDING #1 AREA | D | D | 01 | _ |  | 2023-12-15 | 2024-01-15 | 2024-05-14 | 2024-06-14 | 2024-01-15 | 2024-01-15 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Cable Tray | Electrical | 서정범 | [10 empty] | CCP-EPC-TRM-PGU-0087 | D | 01 | 2024-01-15 | 2024-01-15 | 2024-01-29 | CCP-PGU-TRM-EPC-0087 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0087 | D | 01 | 2024-01-15 | 2024-01-15 | 2024-01-29 | CCP-PGU-TRM-EPC-0087 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:318402AD907B49C78983C74581AD28D8
DDCL | CCP-PW-B213-EL-371-0001 | CABLE TRAY LAYOUT FOR STG BUILDING #2 AREA | D | D | 01 | _ |  | 2023-12-15 | 2024-01-15 | 2024-05-14 | 2024-06-14 | 2024-01-15 | 2024-01-15 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Cable Tray | Electrical | 서정범 | [10 empty] | CCP-EPC-TRM-PGU-0087 | D | 01 | 2024-01-15 | 2024-01-15 | 2024-01-29 | CCP-PGU-TRM-EPC-0087 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0087 | D | 01 | 2024-01-15 | 2024-01-15 | 2024-01-29 | CCP-PGU-TRM-EPC-0087 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:05D27645E11541679669764009ABA9E0
DDCL | CCP-PW-B111-EL-371-0001 | CABLE TRAY LAYOUT FOR MAIN BUILDING-1 GTG&HRSG AREA | R | C | 01 | A |  | 2023-12-26 | 2024-01-26 | 2024-05-14 | 2024-06-14 | 2024-02-01 | 2023-10-12 | 2024-09-02 | 2025-05-26 | BOP Plant | Plant EPC)전력/배전기술2팀 | Cable Tray | Electrical | 서정범 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5D1E92B69A3C48DCAA29202837DD8204
DDCL | CCP-PW-B212-EL-371-0001 | CABLE TRAY LAYOUT FOR MAIN BUILDING-2 GTG&HRSG AREA | R | C | 01 | A |  | 2023-12-26 | 2024-01-26 | 2024-05-14 | 2024-06-14 | 2024-02-01 | 2023-10-12 | 2024-09-02 | 2025-05-26 | BOP Plant | Plant EPC)전력/배전기술2팀 | Cable Tray | Electrical | 서정범 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8C664A478DC445928823F94DAD5E8365
DDCL | CCP-PW-B062-EL-371-0001 | CABLE TRAY LAYOUT FOR LEB FOR BLOCK#1 | D | C | 01 | A |  | 2023-12-29 | 2024-01-29 | 2024-05-14 | 2024-06-14 | 2024-01-30 | 2024-07-15 | 2024-09-04 | 2025-05-26 | BOP Plant | Plant EPC)전력/배전기술2팀 | Cable Tray | Electrical | 서정범 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:04F04782D6D9483D914792F781BF83DC
DDCL | CCP-PW-B025-EL-371-0001 | CABLE TRAY LAYOUT FOR PIPE RACK & SLEEPER AREA | D | C | 01 | A |  | 2024-01-07 | 2024-01-26 | 2024-02-27 | 2024-03-27 | 2024-01-29 | 2024-07-15 | 2024-09-02 | 2025-04-15 | BOP Plant | Plant EPC)전력/배전기술2팀 | Cable Tray | Electrical | 서정범 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:76F3E646FAD3464DAA8E15B4BDED9B59
DDCL | CCP-PW-B063-EL-371-0001 | CABLE TRAY LAYOUT FOR TRANSFORMER SUBSTATION 1 (10/0.4kV) | D | D | 01 | _ |  | 2024-01-02 | 2024-02-02 | 2024-06-10 | 2024-07-11 | 2024-02-05 | 2024-02-06 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Cable Tray | Electrical | 서정범 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:265699C69DFC418EB5493109A37F69BC
DDCL | CCP-PW-B073-EL-371-0001 | CABLE TRAY LAYOUT FOR ADMINISTRATIVE AND HOUSEHOLD BUILDING | D | D | 01 | _ |  | 2024-01-02 | 2024-02-02 | 2024-02-27 | 2024-03-27 | 2024-02-05 | 2024-02-06 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Cable Tray | Electrical | 서정범 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:DF95DBCF0F0C4B96B334853A67911758
DDCL | CCP-PW-B264-EL-371-0001 | CABLE TRAY LAYOUT FOR LEB FOR BLOCK#2 | D | D | 02 | _ |  | 2024-01-27 | 2024-02-27 | 2024-06-04 | 2024-07-05 | 2024-02-28 | 2024-03-25 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Cable Tray | Electrical | 서정범 | [10 empty] | CCP-EPC-TRM-PGU-0125 | D | 02 | 2024-03-28 | 2024-03-28 | 2024-04-07 | CCP-PGU-TRM-EPC-0125 | D | 02 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0125 | D | 02 | 2024-03-28 | 2024-03-28 | 2024-04-07 | CCP-PGU-TRM-EPC-0125 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:46A02FF48F4F49F295C259CC9A4572CE
DDCL | CCP-PW-B161-EL-371-0001 | CABLE TRAY LAYOUT FOR STG #1 LOCAL ELECTRICAL BUILDING | D | D | 01 | _ |  | 2023-12-15 | 2024-01-15 | 2024-05-14 | 2024-06-14 | 2024-01-15 | 2024-01-15 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Cable Tray | Electrical | 서정범 | [10 empty] | CCP-EPC-TRM-PGU-0087 | D | 01 | 2024-01-15 | 2024-01-15 | 2024-01-29 | CCP-PGU-TRM-EPC-0087 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0087 | D | 01 | 2024-01-15 | 2024-01-15 | 2024-01-29 | CCP-PGU-TRM-EPC-0087 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4813A938DB114EB2B3C00336F224F630
DDCL | CCP-PW-B261-EL-371-0001 | CABLE TRAY LAYOUT FOR STG #2 LOCAL ELECTRICAL BUILDING | D | D | 01 | _ |  | 2023-12-15 | 2024-01-15 | 2024-05-14 | 2024-06-14 | 2024-01-15 | 2024-01-15 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Cable Tray | Electrical | 서정범 | [10 empty] | CCP-EPC-TRM-PGU-0087 | D | 01 | 2024-01-15 | 2024-01-15 | 2024-01-29 | CCP-PGU-TRM-EPC-0087 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0087 | D | 01 | 2024-01-15 | 2024-01-15 | 2024-01-29 | CCP-PGU-TRM-EPC-0087 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3F5E7D6AF2B34980B1AD5076AA294963
DDCL | CCP-PW-B069-EL-371-0001 | CABLE TRAY LAYOUT FOR CONDENSATE EXTRACTION PUMP(CEP) BUILDING | D | D | 02 | _ |  | 2024-01-07 | 2024-02-16 | 2024-04-13 | 2024-05-14 | 2024-02-27 | 2024-03-25 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Cable Tray | Electrical | 서정범 | [10 empty] | CCP-EPC-TRM-PGU-0124K | D | 02 | 2024-03-28 | 2024-03-28 | 2024-04-07 | CCP-PGU-TRM-EPC-0124K | D | 02 | Deemed Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | CCP-EPC-TRM-PGU-0124K | D | 02 | 2024-03-28 | 2024-03-28 | 2024-04-07 | CCP-PGU-TRM-EPC-0124K | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:329B2756AB244128AED7E82AB3418DFF
DDCL | CCP-PW-B083-EL-371-0001 | CABLE TRAY LAYOUT FOR WATER TREATMENT OF PROCESS AND DEMINERALIZED WATER ZLD PLANT BUILDING | D | D | 01 | _ |  | 2024-01-02 | 2024-02-14 | 2024-04-13 | 2024-05-14 | 2024-02-15 | 2024-02-06 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Cable Tray | Electrical | 서정범 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:0B33545C789948FC99A693DA2E40C21F
DDCL | CCP-PW-B071-EL-371-0001 | CABLE TRAY LAYOUT FOR WORKSHOP AND STORAGE. RADIATION SHELTER | D | D | 01 | _ |  | 2024-01-02 | 2024-02-14 | 2024-04-13 | 2024-05-14 | 2024-02-15 | 2024-02-06 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Cable Tray | Electrical | 서정범 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:EE2C4E5812054DB293E480A0D520EF10
DDCL | CCP-PW-B117-EL-372-0001 | CONDUIT LAYOUT FOR GTG#1 & GTG#2 GSUT AND UAT AREA | D | D | 01 | _ |  | 2023-12-17 | 2024-01-17 | 2024-06-10 | 2024-07-11 |  | 2024-01-18 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Conduit | Electrical | 김덕길 | [10 empty] | CCP-EPC-TRM-PGU-0089 | D | 01 | 2024-01-18 | 2024-01-18 | 2024-01-29 | CCP-PGU-TRM-EPC-0089 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0089 | D | 01 | 2024-01-18 | 2024-01-18 | 2024-01-29 | CCP-PGU-TRM-EPC-0089 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:0D76726C71FA48AEAA554C4A516ED308
DDCL | CCP-PW-B119-EL-372-0001 | CONDUIT LAYOUT FOR STG#1 & STG#2 GSUT AREA | D | D | 01 | _ |  | 2023-12-17 | 2024-01-17 | 2024-06-10 | 2024-07-11 |  | 2024-01-18 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Conduit | Electrical | 김덕길 | [10 empty] | CCP-EPC-TRM-PGU-0089 | D | 01 | 2024-01-18 | 2024-01-18 | 2024-01-29 | CCP-PGU-TRM-EPC-0089 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0089 | D | 01 | 2024-01-18 | 2024-01-18 | 2024-01-29 | CCP-PGU-TRM-EPC-0089 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A951D198AB5F4894BF413CCC5E250648
DDCL | CCP-PW-B218-EL-372-0001 | CONDUIT LAYOUT FOR GTG#3 & GTG#4 GSUT AND UAT AREA | D | D | 01 | _ |  | 2023-12-17 | 2024-01-17 | 2024-06-10 | 2024-07-11 |  | 2024-01-18 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Conduit | Electrical | 김덕길 | [10 empty] | CCP-EPC-TRM-PGU-0089 | D | 01 | 2024-01-18 | 2024-01-18 | 2024-01-29 | CCP-PGU-TRM-EPC-0089 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0089 | D | 01 | 2024-01-18 | 2024-01-18 | 2024-01-29 | CCP-PGU-TRM-EPC-0089 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D48817D403B0401FA60D982F8C91A028
DDCL | CCP-PW-B032-EL-372-0001 | CONDUIT LAYOUT FOR FIN FAN COOLER FOR CLOSED COOLING WATER AREA | D | D | 01 | _ |  | 2023-12-27 | 2024-01-27 | 2024-06-10 | 2024-07-11 | 2024-01-30 | 2024-04-12 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Conduit | Electrical | 김덕길 | [10 empty] | CCP-EPC-TRM-PGU-0128 | D | 01 | 2024-04-15 | 2024-04-15 | 2024-05-22 | CCP-EPC-TRM-PGU-0128 | D | 01 | Approved | CCP-EPC-TRM-PGU-0128 | D | 01 | 2024-04-15 | 2024-04-15 | 2024-05-22 | CCP-EPC-TRM-PGU-0128 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:46E496FCB927483295D66269916AC9DD
DDCL | CCP-PW-B032-EL-372-0002 | CONDUIT LAYOUT FOR CCW PUMP/HEAT EXCHANGER BUILDING | D | D | 01 | _ |  | 2023-12-27 | 2024-01-27 | 2024-01-27 | 2024-02-27 | 2024-01-30 | 2024-04-12 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Conduit | Electrical | 김덕길 | [10 empty] | CCP-EPC-TRM-PGU-0128 | D | 01 | 2024-04-15 | 2024-04-15 | 2024-05-22 | CCP-EPC-TRM-PGU-0128 | D | 01 | Approved | CCP-EPC-TRM-PGU-0128 | D | 01 | 2024-04-15 | 2024-04-15 | 2024-05-22 | CCP-EPC-TRM-PGU-0128 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:439B9C9065264671B4CB9200C0A7C6E8
DDCL | CCP-PW-B078-EL-372-0001 | CONDUIT LAYOUT FOR HOT WATER SUPPLY BUILDING | D | D | 01 | _ |  | 2023-12-27 | 2024-01-27 | 2024-01-27 | 2024-02-27 | 2024-03-04 | 2024-02-06 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Conduit | Electrical | 김덕길 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:21488204732F4D6FA71BEF3FCD540600
DDCL | CCP-PW-B079-EL-372-0001 | CONDUIT LAYOUT FOR WATER DISTRIBUTION PUMP STATION | R | C | 01 | A |  | 2023-12-27 | 2024-01-27 | 2024-01-27 | 2024-02-27 | 2024-09-05 | 2023-10-12 | 2024-09-05 | 2025-04-08 | BOP Plant | Plant EPC)전력/배전기술2팀 | Conduit | Electrical | 김덕길 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:EAAAFFB8B9144B77BAC1B46B39E6D44F
DDCL | CCP-PW-B071-EL-372-0001 | CONDUIT LAYOUT FOR WORKSHOP (GROUND FLOOR) | D | D | 01 | _ |  | 2023-12-17 | 2024-01-17 | 2024-01-17 | 2024-02-17 |  | 2024-01-18 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Conduit | Electrical | 김덕길 | [10 empty] | CCP-EPC-TRM-PGU-0089 | D | 01 | 2024-01-18 | 2024-01-18 | 2024-01-29 | CCP-PGU-TRM-EPC-0089 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0089 | D | 01 | 2024-01-18 | 2024-01-18 | 2024-01-29 | CCP-PGU-TRM-EPC-0089 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:AC54EDE7F9434B76A77ACB2D54BE5C3F
DDCL | CCP-PW-B052-EL-372-0002 | CONDUIT LAYOUT FOR LUBRICANT OIL(LO) PUMP STATION AREA | D | D | 01 | _ |  | 2024-01-13 | 2024-02-13 | 2024-04-13 | 2024-05-14 | 2024-03-04 | 2024-02-06 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Conduit | Electrical | 김덕길 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:EA4DE39F14244E189FB4C40BC1FA8DF4
DDCL | CCP-W-B089-46-EL-B16-0001 | TECHNICAL SPECIFICATION FOR PVC CONDUIT | D | D | 01 | _ |  | 2024-03-01 | 2024-04-01 | 2024-04-30 | 2024-05-29 | 2024-08-19 | 2024-08-21 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Conduit | Electrical | 김덕길 | [10 empty] | CCP-EPC-TRM-PGU-0368 | D | 01 | 2024-08-21 | 2024-08-21 | 2024-08-31 | CCP-PGU-TRM-EPC-0368 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0368 | D | 01 | 2024-08-21 | 2024-08-21 | 2024-08-31 | CCP-PGU-TRM-EPC-0368 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E49242FE70154550B225639D5759A406
DDCL | CCP-PW-B111-EL-372-0001 | CONDUIT LAYOUT FOR MAIN BUILDING COMPLEX-#1 GTG&HRSG AREA | D | D | 01 | _ |  | 2023-12-19 | 2024-01-19 | 2024-03-14 | 2024-04-14 | 2024-01-30 | 2024-04-12 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Conduit | Electrical | 김덕길 | [10 empty] | CCP-EPC-TRM-PGU-0128 | D | 01 | 2024-04-15 | 2024-04-15 | 2024-05-22 | CCP-EPC-TRM-PGU-0128 | D | 01 | Approved | CCP-EPC-TRM-PGU-0128 | D | 01 | 2024-04-15 | 2024-04-15 | 2024-05-22 | CCP-EPC-TRM-PGU-0128 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:238315DF16AE43C2B6F5CFCE181D7712
DDCL | CCP-PW-B212-EL-372-0001 | CONDUIT LAYOUT FOR MAIN BUILDING COMPLEX-#2 GTG&HRSG AREA | D | D | 01 | _ |  | 2023-12-19 | 2024-01-19 | 2024-03-14 | 2024-04-14 | 2024-01-30 | 2024-04-12 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Conduit | Electrical | 김덕길 | [10 empty] | CCP-EPC-TRM-PGU-0128 | D | 01 | 2024-04-15 | 2024-04-15 | 2024-05-22 | CCP-EPC-TRM-PGU-0128 | D | 01 | Approved | CCP-EPC-TRM-PGU-0128 | D | 01 | 2024-04-15 | 2024-04-15 | 2024-05-22 | CCP-EPC-TRM-PGU-0128 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3CAFC43EAA7243E98AFBBC072EBDDC8D
DDCL | CCP-PW-B113-EL-372-0001 | CONDUIT LAYOUT FOR STG BUILDING #1 AREA | D | D | 01 | _ |  | 2024-01-01 | 2024-02-01 | 2024-03-14 | 2024-04-14 | 2024-02-15 | 2024-02-06 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Conduit | Electrical | 김덕길 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8F164BE211C248809A3AFB1CFE582CC1
DDCL | CCP-PW-B213-EL-372-0001 | CONDUIT LAYOUT FOR STG BUILDING #2 AREA | D | D | 01 | _ |  | 2023-12-27 | 2024-01-27 | 2024-03-14 | 2024-04-14 | 2024-02-15 | 2024-02-06 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Conduit | Electrical | 김덕길 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5C5B44683E674EEBAC6A6D21D2C77CB8
DDCL | CCP-PW-B062-EL-372-0001 | CONDUIT LAYOUT FOR CENTERIZED CONTROL ROOM (CCR) & LOCAL ELECTRIC ROOM FOR BLOCK #1 (GROUND FLOOR) | D | D | 01 | _ |  | 2023-12-27 | 2024-01-27 | 2024-04-08 | 2024-05-09 | 2024-02-15 | 2024-02-06 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Conduit | Electrical | 김덕길 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FF55D6F475EC4E52805BCCD5394AD4E2
DDCL | CCP-PW-B069-EL-372-0001 | CONDUIT LAYOUT FOR CONDENSATE EXTRACTION PUMP(CEP) BUILDING | D | D | 01 | _ |  | 2023-12-27 | 2024-01-27 | 2024-01-27 | 2024-02-27 | 2024-02-15 | 2024-02-06 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Conduit | Electrical | 김덕길 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:DDC33FC11EB24632BC33AA51AB36F8AB
DDCL | CCP-PW-B038-EL-372-0001 | CONDUIT LAYOUT FOR RAW WATER&FIRE WATER PUMP HOUSE | D | C | 01 | A |  | 2023-12-27 | 2024-01-27 | 2024-01-27 | 2024-02-27 | 2024-01-30 | 2024-09-05 | 2024-09-05 | 2025-04-08 | BOP Plant | Plant EPC)전력/배전기술2팀 | Conduit | Electrical | 김덕길 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:938EF66881854FC8BBFB87DD7081202F
DDCL | CCP-PW-B070-EL-372-0001 | CONDUIT LAYOUT FOR DIESEL OIL PUMP STATION | D | C | 01 | A |  | 2023-12-27 | 2024-01-27 | 2024-01-27 | 2024-02-27 | 2024-01-30 | 2024-09-05 | 2024-09-05 | 2025-04-08 | BOP Plant | Plant EPC)전력/배전기술2팀 | Conduit | Electrical | 김덕길 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:455B507AECC54126B326C7F6DA041877
DDCL | CCP-W-B000-EL-385-0003 | CALCULATION FOR ISOLATED PHASE BUSDUCT | D | C | 01 | _ |  | 2024-02-09 | 2024-02-23 | 2024-05-17 | 2024-05-24 | 2024-07-15 | 2024-07-15 | 2024-09-10 | 2024-09-10 | BOP Plant | Plant EPC)전력/배전기술2팀 | Isolated Phase Busduct | Electrical | 이재욱 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2E6F5CDCCD484937A77F42005FDE24F0
DDCL | CCP-W-B000-39-EL-E04-0001 | OUTLINE DRAWING FOR ISOLATED PHASE BUSDUCT | D | D | 01 | _ |  | 2024-02-19 | 2024-03-11 | 2024-05-20 | 2024-06-10 | 2024-08-07 | 2024-08-08 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Isolated Phase Busduct | Electrical | 이재욱 | [10 empty] | CCP-EPC-TRM-PGU-0330 | D | 01 | 2024-08-08 | 2024-08-14 | 2024-08-24 | CCP-PGU-TRM-EPC-0330 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0330 | D | 01 | 2024-08-08 | 2024-08-14 | 2024-08-24 | CCP-PGU-TRM-EPC-0330 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3DA43CBD7D56421BA3BFC27D9EBC75BD
DDCL | CCP-W-B000-39-EL-B16-0001 | TECHNICAL SPECIFICATION FOR ISOLATED PHASE BUSDUCT | D | D | 01 | _ |  | 2024-03-21 | 2024-04-11 | 2024-06-19 | 2024-07-10 | 2024-08-07 | 2024-08-08 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Isolated Phase Busduct | Electrical | 이재욱 | [10 empty] | CCP-EPC-TRM-PGU-0330 | D | 01 | 2024-08-08 | 2024-08-14 | 2024-08-24 | CCP-PGU-TRM-EPC-0330 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0330 | D | 01 | 2024-08-08 | 2024-08-14 | 2024-08-24 | CCP-PGU-TRM-EPC-0330 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E6F59C00632E4E8AB0CF2EB1D9FA2D2C
DDCL | CCP-W-B000-38-EL-B16-0001 | TECHNICAL SPECIFICATION FOR MV/LV POWER & CONTROL CABLE | D | D | 01 | _ |  | 2024-05-02 | 2024-06-13 | 2024-06-14 | 2024-07-12 | 2025-02-27 | 2025-02-27 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Power & Control Cable | Electrical | 최준호 | [10 empty] | CCP-EPC-TRM-PGU-0862 | D | 01 | 2025-02-28 | 2025-03-06 | 2025-03-17 | CCP-PGU-TRM-EPC-0862 | D | 01 | Deemed approved | CCP-EPC-TRM-PGU-0862 | D | 01 | 2025-02-28 | 2025-03-06 | 2025-03-17 | CCP-PGU-TRM-EPC-0862 | Deemed approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4B4E768930594B3F8ED5E134B8FC3FC7
DDCL | CCP-W-B000-50-EL-B16-0001 | TECHNICAL SPECIFICATION FOR CABLE TERMINATION MATERIAL & ACCESSORIES | D | D | 01 | _ |  | 2024-05-02 | 2024-06-13 | 2024-06-14 | 2024-07-12 | 2025-01-23 | 2025-01-23 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Cable Termination Material | Electrical | 최준호 | [10 empty] | CCP-EPC-TRM-PGU-0846 | D | 01 | 2025-01-23 | 2025-02-05 | 2025-02-10 | CCP-PGU-TRM-EPC-0846 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0846 | D | 01 | 2025-01-23 | 2025-02-05 | 2025-02-10 | CCP-PGU-TRM-EPC-0846 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:90343E2DA31349028A9D40A3C3863FC1
DDCL | CCP-W-B022-35-EL-B16-0004 | 500&220kV AIS CABLE SPECIFICATION FOR FIBER OPTIC | D | D | 01 | _ | FA&FC DELAY | 2025-03-31 | 2025-04-15 | 2025-04-15 | 2025-05-15 |  |  |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FCDA4BE57DB14719A2C8FE036A6C1E63
DDCL | CCP-W-B022-35-EL-E01-0009 | 500&220kV AIS Emergency Control System | D | C | 01 | A |  | 2025-03-31 | 2025-04-15 | 2025-04-15 | 2025-04-30 |  |  | 2025-05-20 | 2025-06-23 | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8E07B1213B0043D29EA8C12C357B7669
DDCL | CCP-W-B022-35-EL-E01-0006 | AIS AC & DC POWER SUPPLY SYSTEM | D | D | 01 | B |  | 2024-11-01 | 2024-11-30 | 2025-01-01 | 2025-02-28 | 2024-11-18 | 2024-12-26 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0781 | D | 01 | 2024-12-27 | 2025-01-02 | 2025-01-12 | CCP-EPC-TRM-PGU-0781 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0555 CCP-EPC-TRM-PGU-0781 | D | 01 | 2024-11-18 2024-12-27 | 2024-11-20 2025-01-02 | 2025-01-12 | CCP-EPC-TRM-PGU-0781 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:441F5905833B4236AFE1D59605155E94
DDCL | CCP-W-B023-35-EL-B18-0002 | TECHNICAL SPECIFICATION – TARIFF METERING SYSTEM, SCADA, RPA, TELECOMMUNICATION SYSTEM, AFPRS | D | D | 01 | _ |  | 2024-07-01 | 2024-07-31 | 2024-10-01 | 2024-10-31 | 2024-07-01 | 2024-07-01 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0238 | D | 01 | 2024-07-01 | 2024-07-05 | 2024-07-15 | CCP-PGU-TRM-EPC-0238 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0238 | D | 01 | 2024-07-01 | 2024-07-05 | 2024-07-15 | CCP-PGU-TRM-EPC-0238 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B86684A954904B1A9B9C07FE6876A4D4
DDCL | CCP-W-B022-35-EL-B16-0016 | 500/220KV AIS Tariff METERING & PQ (ASCME) | D | D | 01 | _ |  | 2024-04-30 | 2024-05-31 | 2024-06-30 | 2024-07-31 | 2024-04-11 | 2024-05-24 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0154 | D | 01 | 2024-05-24 | 2024-05-24 | 2024-06-03 | CCP-PGU-TRM-EPC-0154 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0154 | D | 01 | 2024-05-24 | 2024-05-24 | 2024-06-03 | CCP-PGU-TRM-EPC-0154 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FF7DD5C1C5CE4C48A636AC65A7E43C9F
DDCL | CCP-W-B022-35-EL-E01-0008 | 220kV Outdoor cabinet | D | D | 01 | _ |  | 2024-12-01 | 2024-12-31 | 2025-01-01 | 2025-01-31 | 2024-12-26 | 2024-12-26 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0781 | D | 01 | 2024-12-27 | 2025-01-02 | 2025-01-12 | CCP-EPC-TRM-PGU-0781 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0781 | D | 01 | 2024-12-27 | 2025-01-02 | 2025-01-12 | CCP-EPC-TRM-PGU-0781 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C5CCA937A5844D41B218BDD8792CE0D9
DDCL | CCP-W-B022-35-EL-E01-0007 | 500kV Outdoor cabinet | D | D | 01 | _ |  | 2025-01-09 | 2025-01-23 | 2025-02-16 | 2025-02-23 | 2025-02-11 | 2025-02-11 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0855 | D | 01 | 2025-02-11 | 2025-02-13 | 2025-02-23 | CCP-PGU-TRM-EPC-0855 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0855 | D | 01 | 2025-02-11 | 2025-02-13 | 2025-02-23 | CCP-PGU-TRM-EPC-0855 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1D176B43F29E4D9688F6C1969773C88A
DDCL | CCP-W-B022-35-EL-E01-0005 | 500kV/220kV AIS Telecommunication cabinet | D | D | 01 | _ |  | 2024-12-01 | 2024-12-31 | 2025-01-01 | 2024-12-31 | 2024-12-26 | 2024-12-26 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0781 | D | 01 | 2024-12-27 | 2025-01-02 | 2025-01-12 | CCP-EPC-TRM-PGU-0781 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0781 | D | 01 | 2024-12-27 | 2025-01-02 | 2025-01-12 | CCP-EPC-TRM-PGU-0781 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7A7670431B88454EB909EC4622489CF5
DDCL | CCP-W-B022-35-EL-E04-0002 | 500/220KV AIS OVERALL SUBSTATION SECTION | D | D | 01 | _ |  | 2024-07-09 | 2024-08-10 | 2024-09-10 | 2024-10-10 | 2024-07-09 | 2024-07-09 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0251 | D | 01 | 2024-07-09 | 2024-07-11 | 2024-07-21 | CCP-PGU-TRM-EPC-0251 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0251 | D | 01 | 2024-07-09 | 2024-07-11 | 2024-07-21 | CCP-PGU-TRM-EPC-0251 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:43CB15A2D7194622B4C064CE35E48055
DDCL | CCP-W-B022-35-EL-E04-0023 | 500/220kV AIS Foundation plan | D | D | 01 | _ |  | 2024-04-30 | 2024-05-31 | 2024-07-31 | 2024-08-31 | 2024-04-08 | 2024-04-24 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0133 | D | 01 | 2024-04-24 | 2024-04-24 | 2024-04-24 | CCP-PGU-TRM-EPC-0133 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0133 | D | 01 | 2024-04-24 | 2024-04-24 | 2024-04-24 | CCP-PGU-TRM-EPC-0133 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:71203952AAF042A98B222461177B8019
DDCL | CCP-W-B023-35-EL-D02-0001 | STEEL STRUCTURES FOR GANTRY TOWER FRAME(POST) & BEAM FOR 220KV AIS | D | D | 01 | _ |  | 2024-04-30 | 2024-05-30 | 2024-07-31 | 2024-08-31 | 2024-04-08 | 2024-04-17 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0131 | D | 01 | 2024-04-17 | 2024-04-17 | 2024-04-27 | CCP-PGU-TRM-EPC-0131 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0131 | D | 01 | 2024-04-17 | 2024-04-17 | 2024-04-27 | CCP-PGU-TRM-EPC-0131 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F8E7263C4B694AF9A03925037784787D
DDCL | CCP-W-B022-35-EL-E13-0001 | 500/220KV AIS SINGLE LINE DIAGRAM | D | C | 03 | C |  | 2023-11-25 | 2023-12-25 | 2024-02-01 | 2024-03-03 | 2024-02-01 | 2024-03-06 | 2024-03-07 | 2025-07-03 | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0178 | C | 03 | 2024-06-11 | 2024-06-11 | 2024-04-04 | CCP-PGU-TRM-EPC-0121 | C | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0078 | D | 01 | 2023-12-05 | 2023-12-05 |  |  |  | CCP-EPC-TRM-PGU-0119 CCP-EPC-TRM-PGU-0120 CCP-EPC-TRM-PGU-0121 | C | 01 | 2024-03-26 2024-03-27 2024-03-27 | 2024-03-26 2024-03-27 2024-03-27 | 2024-04-04 | CCP-PGU-TRM-EPC-0121 | Approved With Comment | CCP-EPC-TRM-PGU-0167 | C | 02 | 2024-05-31 | 2024-06-04 |  |  |  | CCP-EPC-TRM-PGU-0178 | C | 03 | 2024-06-11 | 2024-06-11 | [67 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1E8F094D82E740F09EDD1BDA704EFD52
DDCL | CCP-W-B022-35-EL-E04-0001 | 500/220KV AIS OVERALL SUBSTATION LAYOUT | D | C | 01 | D |  | 2023-12-15 | 2024-01-15 | 2024-03-01 | 2024-04-01 | 2024-01-26 | 2024-04-29 | 2024-06-07 | 2025-07-03 | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0171 | C | 01 | 2024-06-07 | 2024-06-07 | 2024-05-09 | CCP-PGU-TRM-EPC-0137 | D | 02 | Deemed Approved | CCP-EPC-TRM-PGU-0092 | D | 01 | 2024-01-26 | 2024-01-26 |  |  |  | CCP-EPC-TRM-PGU-0137 | D | 02 | 2024-04-29 | 2024-04-29 | 2024-05-09 | CCP-PGU-TRM-EPC-0137 | Deemed Approved | CCP-EPC-TRM-PGU-0171 | C | 01 | 2024-06-07 | 2024-06-07 | [75 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A931757E78E549878F822C5679F54A2D
DDCL | CCP-W-B022-35-EL-B16-0802 | 500/220KV AIS DISC INSULATOR | D | D | 01 | _ |  | 2024-08-01 | 2024-08-31 | 2024-09-01 | 2024-09-30 | 2024-07-26 | 2024-08-06 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0328 | D | 01 | 2024-08-07 | 2024-08-14 | 2024-08-24 | CCP-PGU-TRM-EPC-0328 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0328 | D | 01 | 2024-08-07 | 2024-08-14 | 2024-08-24 | CCP-PGU-TRM-EPC-0328 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:9AEFD86172954C87BEC086A012523E2A
DDCL | CCP-W-B023-35-EL-B18-0001 | Technical Specification for AIS component | D | C | 01 | _ |  | 2024-01-01 | 2024-02-01 | 2024-04-01 | 2024-05-01 | 2024-02-01 | 2024-02-01 | 2024-03-13 | 2024-03-26 | BOP Plant | Plant EPC)전력/배전기술2팀 | 500kV/220kV AIS | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0121 | C | 01 | 2024-03-27 | 2024-03-27 | 2024-04-04 | CCP-PGU-TRM-EPC-0121 | C | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0091 | D | 01 | 2024-01-22 | 2024-01-22 | 2024-03-07 | CCP-PGU-TRM-EPC-0091 | Approved | CCP-EPC-TRM-PGU-0119 CCP-EPC-TRM-PGU-0120 CCP-EPC-TRM-PGU-0121 | C | 01 | 2024-03-26 2024-03-27 2024-03-27 | 2024-03-26 2024-03-27 2024-03-27 | 2024-04-04 | CCP-PGU-TRM-EPC-0121 | Approved With Comment | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2FDEC644E40D42A5BB5AF897175E8B8D
DDCL | CCP-W-B000-EL-369-0001 | CONTROL CABLE CONNECTION DIAGRAM | D | C | 01 | _ |  | 2024-05-02 | 2024-06-13 | 2024-06-14 | 2024-07-12 | 2024-10-28 | 2024-10-29 | 2025-02-03 | 2025-02-03 | BOP Plant | Plant EPC)전력/배전기술2팀 | Elec_Cable_Connection Design | Electrical | 정백경 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:923BDB72E8204DC0A35831AE23FB1C95
DDCL | CCP-PW-B000-EL-356-0003 | OVERALL PROTECTION SINGLE LINE DIAGRAM | D | D | 01 | _ |  | 2023-12-15 | 2024-01-26 | 2024-04-26 | 2024-05-17 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Elec_ProtSLD Design | Electrical | 정백경 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:716EC883F3DD416DA7E6E181DDE92400
DDCL | CCP-PW-B089-EL-351-0003 | DESIGN CRITERIA - CABLE TRAY AND CONDUIT | D | C | 01 | _ |  | 2023-12-05 | 2024-01-26 | 2024-11-29 | 2025-01-18 | 2024-01-29 | 2024-12-04 | 2024-12-10 | 2024-12-10 | BOP Plant | Plant EPC)전력/배전기술2팀 | Elec_Cable Raceway Design | Electrical | 서정범 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A2E0473B90224B38B7D3210029D35DEA
DDCL | CCP-PW-B000-EL-354-0001 | UG ELECTRICAL CABLES ROUTE DRAWING (OVER ALL) | D | D | 01 | _ |  | 2023-11-27 | 2023-12-28 | 2024-04-19 | 2024-05-20 | 2024-01-03 | 2024-01-10 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Elec_Cable Raceway Design | Electrical | 서정범 | [10 empty] | CCP-EPC-TRM-PGU-0083 | D | 01 | 2024-01-02 | 2024-01-02 | 2024-01-18 | CCP-PGU-TRM-EPC-0083 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0083 | D | 01 | 2024-01-02 | 2024-01-02 | 2024-01-18 | CCP-PGU-TRM-EPC-0083 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5F862B3F6547428CBF72416592EE1BE0
DDCL | CCP-PW-B000-EL-354-0002 | UG ELECTRICAL CABLES ROUTE DRAWING (ALL AREA) | D | D | 01 | _ |  | 2023-11-27 | 2023-12-28 | 2024-04-19 | 2024-05-20 | 2024-01-08 | 2024-01-11 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Elec_Cable Raceway Design | Electrical | 서정범 | [10 empty] | CCP-EPC-TRM-PGU-0083 | D | 01 | 2024-01-02 | 2024-01-02 | 2024-01-19 | CCP-PGU-TRM-EPC-0083 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0083 | D | 01 | 2024-01-02 | 2024-01-02 | 2024-01-19 | CCP-PGU-TRM-EPC-0083 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:BD533A0F56604761BC5DC1C4C1C4DDD0
DDCL | CCP-PW-B089-EL-377-0001 | TYPICAL INSTALLATION DRAWING FOR CABLE RACEWAY | D | D | 01 | _ |  | 2023-11-24 | 2023-12-25 | 2024-03-09 | 2024-04-09 | 2023-12-26 | 2024-01-03 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Elec_Cable Raceway Design | Electrical | 서정범 | [10 empty] | CCP-EPC-TRM-PGU-0082 | D | 01 | 2023-12-27 | 2023-12-27 | 2024-01-13 | CCP-PGU-TRM-EPC-0082 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0082 | D | 01 | 2023-12-27 | 2023-12-27 | 2024-01-13 | CCP-PGU-TRM-EPC-0082 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:97341B7C8C9B4AEBA311B6619C9FEE52
DDCL | CCP-PW-B000-EL-356-0002 | KEY SINGLE LINE DIAGRAM | D | C | 01 | C |  | 2023-12-22 | 2024-01-12 | 2024-03-22 | 2024-04-12 | 2024-02-28 | 2024-03-05 | 2024-06-14 | 2025-06-11 | BOP Plant | Plant EPC)전력/배전기술2팀 | Elec_KeySLD Design | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0191 | C | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0191 | C | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0077 | D | 01 | 2023-11-30 | 2023-11-30 | 2023-12-10 | CCP-PGU-TRM-EPC-0077 | Deemed Approved | CCP-EPC-TRM-PGU-0191 | C | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0191 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:EA9D97947C554B72B88F726918819124
DDCL | CCP-W-B000-36-EL-E09-0002 | ELECTRICAL CONTROL LOGIC DIAGRAM FOR 400V SWITCHGEAR | D | C | 01 | A |  | 2024-02-02 | 2024-02-23 | 2024-05-02 | 2024-05-23 | 2024-03-13 | 2024-06-04 | 2024-07-15 | 2025-01-10 | BOP Plant | Plant EPC)전력/배전기술2팀 | Elec_Logic Design_LV SWGR | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0265 | C | 01 | 2024-07-15 |  | 2024-06-15 | CCP-PGU-TRM-EPC-0170 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0170 | D | 01 | 2024-06-04 | 2024-06-05 | 2024-06-15 | CCP-PGU-TRM-EPC-0170 | Deemed Approved | CCP-EPC-TRM-PGU-0265 | C | 01 | 2024-07-15 | [84 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:743102B239CA44FCA35ED4A5FD5678F1
DDCL | CCP-W-B000-36-EL-E09-0001 | ELECTRICAL CONTROL LOGIC DIAGRAM FOR 10KV SWITCHGEAR | D | C | 01 | A |  | 2024-02-02 | 2024-02-23 | 2024-05-02 | 2024-05-23 | 2024-03-13 | 2024-06-04 | 2024-07-15 | 2025-01-10 | BOP Plant | Plant EPC)전력/배전기술2팀 | Elec_Logic Design_MV SWGR | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0265 | C | 01 | 2024-07-15 |  | 2024-06-15 | CCP-PGU-TRM-EPC-0170 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0170 | D | 01 | 2024-06-04 | 2024-06-05 | 2024-06-15 | CCP-PGU-TRM-EPC-0170 | Deemed Approved | CCP-EPC-TRM-PGU-0265 | C | 01 | 2024-07-15 | [84 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8740AC66D2B24F1AA20DAE93B7778569
DDCL | CCP-W-B000-36-EL-E09-0010 | ELECTRICAL CONTROL LOGIC DIAGRAM_GSUT/UAT/OVERALL PROTECTION FOR GTG | D | C | 01 | A |  | 2024-02-02 | 2024-02-23 | 2024-05-02 | 2024-05-23 | 2024-03-13 | 2024-06-04 | 2024-07-15 | 2025-01-10 | BOP Plant | Plant EPC)전력/배전기술2팀 | Elec_Logic Design_GEN_TR | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0265 | C | 01 | 2024-07-15 |  | 2024-06-15 | CCP-PGU-TRM-EPC-0170 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0170 | D | 01 | 2024-06-04 | 2024-06-05 | 2024-06-15 | CCP-PGU-TRM-EPC-0170 | Deemed Approved | CCP-EPC-TRM-PGU-0265 | C | 01 | 2024-07-15 | [84 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8C4EF911CBD9424D98C1F3DE41BEA88A
DDCL | CCP-W-B000-36-EL-E09-0011 | ELECTRICAL CONTROL LOGIC DIAGRAM_GSUT/UAT/OVERALL PROTECTION FOR STG | D | C | 01 | A |  | 2024-02-02 | 2024-02-23 | 2024-05-02 | 2024-05-23 | 2024-03-13 | 2024-06-04 | 2024-07-15 | 2025-01-10 | BOP Plant | Plant EPC)전력/배전기술2팀 | Elec_Logic Design_GEN_TR | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0265 | C | 01 | 2024-07-15 |  | 2024-06-15 | CCP-PGU-TRM-EPC-0170 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0170 | D | 01 | 2024-06-04 | 2024-06-05 | 2024-06-15 | CCP-PGU-TRM-EPC-0170 | Deemed Approved | CCP-EPC-TRM-PGU-0265 | C | 01 | 2024-07-15 | [84 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:67F837BB214E457C8FECB30DBF1BA9E1
DDCL | CCP-W-B000-36-EL-E09-0012 | ELECTRICAL CONTROL LOGIC DIAGRAM_BACK UP TR PROTECTION | D | C | 01 | A |  | 2024-02-02 | 2024-02-23 | 2024-05-02 | 2024-05-23 | 2024-03-14 | 2024-06-04 | 2024-07-15 | 2025-01-10 | BOP Plant | Plant EPC)전력/배전기술2팀 | Elec_Logic Design_GEN_TR | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0265 | C | 01 | 2024-07-15 |  | 2024-06-15 | CCP-PGU-TRM-EPC-0170 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0170 | D | 01 | 2024-06-04 | 2024-06-05 | 2024-06-15 | CCP-PGU-TRM-EPC-0170 | Deemed Approved | CCP-EPC-TRM-PGU-0265 | C | 01 | 2024-07-15 | [84 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D82A5CA8C1E04BCEA850FBF2C29EBB7B
DDCL | CCP-PW-B000-EL-356-0004 | PHASE SEQUENCE DIAGRAM | D | D | 01 | _ |  | 2024-02-02 | 2024-02-23 | 2024-05-02 | 2024-05-23 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Elec_Phase Design | Electrical | 이재욱 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FCB75FAFE5F34EC08D5FEE4B8D145C7D
DDCL | CCP-W-B000-EL-353-0001 | POWER CABLE SCHEDULE | D | C | 01 | _ |  | 2024-05-02 | 2024-06-13 | 2024-06-14 | 2024-07-12 | 2024-11-01 | 2024-11-01 | 2025-04-21 | 2025-04-22 | BOP Plant | Plant EPC)전력/배전기술2팀 | Elec_Power & Control Cable Design | Electrical | 최준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:10A53791BC674DA08EB6C9DEB7A5E121
DDCL | CCP-W-B000-EL-353-0002 | CONTROL CABLE SCHEDULE | D | C | 01 | _ |  | 2024-05-02 | 2024-06-13 | 2024-06-14 | 2024-07-12 | 2025-04-29 | 2025-04-29 | 2025-07-04 | 2025-07-07 | BOP Plant | Plant EPC)전력/배전기술2팀 | Elec_Power & Control Cable Design | Electrical | 최준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:0E48891083F04CEF91BBA8F84980B86A
DDCL | CCP-W-B000-41-EL-E20-0001 | PROTECTION RELAY COORDINATION STUDY - GSUT, UAT | D | D | 01 | _ |  | 2024-03-22 | 2024-04-12 | 2024-06-20 | 2024-07-11 | 2024-06-03 | 2024-07-01 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Elec_RelayCoordi Design_GEN_TR | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0237 | D | 01 | 2024-07-01 | 2024-07-04 | 2024-07-14 | CCP-PGU-TRM-EPC-0237 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0237 | D | 01 | 2024-07-01 | 2024-07-04 | 2024-07-14 | CCP-PGU-TRM-EPC-0237 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A286D62454594F83AAD3B224A521E5DC
DDCL | CCP-W-B000-36-EL-E20-0001 | PROTECTION RELAY COORDINATION STUDY - 11KV / 400V SYSTEM | D | D | 01 | _ |  | 2024-03-22 | 2024-04-12 | 2024-06-20 | 2024-07-11 | 2024-08-19 | 2024-08-19 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Elec_RelayCoordi Design_MV SWGR | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0332 | D | 01 | 2024-08-19 | 2024-08-21 | 2024-08-31 | CCP-PGU-TRM-EPC-0332 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0332 | D | 01 | 2024-08-19 | 2024-08-21 | 2024-08-31 | CCP-PGU-TRM-EPC-0332 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:843C0A9DEB3849ADB5CA55FF58FC36BA
DDCL | CCP-W-B000-EL-385-0100 | SHORT CIRCUIT STUDY | D | C | 01 | A |  | 2024-02-02 | 2024-02-23 | 2024-05-10 | 2024-05-31 | 2024-02-15 | 2024-07-01 | 2024-09-12 | 2025-06-05 | BOP Plant | Plant EPC)전력/배전기술2팀 | Elec_SystemStudy Design | Electrical | 정백경 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:EB817F84C9CB49B8AC807ADDDB441D83
DDCL | CCP-W-B000-EL-385-0101 | LOAD FLOW & LARGE MOTOR STARTING STUDY | D | C | 01 | _ |  | 2024-02-08 | 2024-02-29 | 2024-05-10 | 2024-05-31 | 2024-04-17 | 2024-07-01 | 2024-09-12 | 2024-09-12 | BOP Plant | Plant EPC)전력/배전기술2팀 | Elec_SystemStudy Design | Electrical | 정백경 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B8725DDEA89042A795DDD416695D937C
DDCL | CCP-PW-B000-GP-605-0007 | Plant General Arrangement Drawing for STG Area (Section View) | R | C | 01 | A |  | 2023-11-16 | 2024-01-29 | 2024-05-15 | 2024-07-28 | 2024-04-12 | 2023-10-05 | 2024-09-27 |  | BOP Plant | Plant EPC)배치/배관기술2팀 | ARRANGE | GA | 이진우 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C236DDA0D77C4737BCC301A4137BA11C
DDCL | CCP-PW-B000-GP-605-0001 | General Plot Plan | D | C | 01 | _ |  | 2023-11-16 | 2024-01-29 | 2024-05-15 | 2024-07-28 | 2024-03-12 | 2024-06-13 | 2024-06-13 | 2024-06-13 | BOP Plant | Plant EPC)배치/배관기술2팀 | ARRANGE | GA | 이진우 | [10 empty] | CCP-EPC-TRM-PGU-0187 | C | 01 | 2024-06-14 | 2024-06-16 | 2024-06-26 | CCP-PGU-TRM-EPC-0187 | C | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0187 | C | 01 | 2024-06-14 | 2024-06-16 | 2024-06-26 | CCP-PGU-TRM-EPC-0187 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:966416C8D02E462B9114285E6AF187D3
DDCL | CCP-PW-B000-GP-605-0002 | Plant General Arrangement Drawing for GTG & HRSG Area (Plan View) | R | C | 01 | A |  | 2023-11-16 | 2024-01-29 | 2024-05-15 | 2024-07-28 | 2024-04-12 | 2023-10-05 | 2024-09-27 |  | BOP Plant | Plant EPC)배치/배관기술2팀 | ARRANGE | GA | 이진우 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D9CB424851DD4A9EB79204A9F9CAEC29
DDCL | CCP-PW-B000-GP-605-0003 | Plant General Arrangement Drawing for GTG & HRSG Area (Section A-A) | R | C | 01 | A |  | 2023-11-16 | 2024-01-29 | 2024-05-15 | 2024-07-28 | 2024-04-12 | 2023-10-05 | 2024-09-27 |  | BOP Plant | Plant EPC)배치/배관기술2팀 | ARRANGE | GA | 이진우 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:48A25CC364DA4E86B453883CF72682AA
DDCL | CCP-PW-B000-GP-605-0004 | Plant General Arrangement Drawing for GTG & HRSG Area (Section B-B, C-C) | R | C | 01 | A |  | 2023-11-16 | 2024-01-29 | 2024-05-15 | 2024-07-28 | 2024-04-12 | 2023-10-05 | 2024-09-27 |  | BOP Plant | Plant EPC)배치/배관기술2팀 | ARRANGE | GA | 이진우 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2C49BE5D3C9E40C694CA3473268746D4
DDCL | CCP-PW-B000-GP-605-0005 | Plant General Arrangement Drawing for GTG & HRSG Area (Roof Floor Plan) | R | C | 01 | A |  | 2023-11-16 | 2024-01-29 | 2024-05-15 | 2024-07-28 | 2024-04-12 | 2023-10-05 | 2024-09-27 |  | BOP Plant | Plant EPC)배치/배관기술2팀 | ARRANGE | GA | 이진우 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B77FA2426E3844C9A820F69A5EE9A2DB
DDCL | CCP-PW-B000-GP-605-0006 | Plant General Arrangement Drawing for STG Area (Plan View) | R | C | 01 | A |  | 2023-11-16 | 2024-01-29 | 2024-05-15 | 2024-07-28 | 2024-04-12 | 2023-10-05 | 2024-09-27 |  | BOP Plant | Plant EPC)배치/배관기술2팀 | ARRANGE | GA | 이진우 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:17797887B9874585984908836E96FA12
DDCL | CCP-W-B000-46-IA-B16-0001 | TECHNICAL SPECIFICATION FOR I&C CONDUIT & ACCESSORIES | D | D | 01 | _ |  | 2024-03-26 | 2024-04-26 | 2024-06-26 | 2024-07-26 | 2024-07-25 | 2024-08-07 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C Conduit | I&C | 오준호 | [10 empty] | CCP-EPC-TRM-PGU-0311 | D | 01 | 2024-07-26 | 2024-07-26 | 2024-08-05 | CCP-PGU-TRM-EPC-0311 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0311 | D | 01 | 2024-07-26 | 2024-07-26 | 2024-08-05 | CCP-PGU-TRM-EPC-0311 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:9A8D5D0023584F61987EA07F5AEB727F
DDCL | CCP-W-B000-59-IA-B16-0001 | SPECIFICATION & DATASHEET FOR ELECTRICAL HEAT TRACING SYSTEM (BOP) | D | C | 01 | A |  | 2024-03-26 | 2024-04-26 | 2024-06-26 | 2024-07-26 | 2024-10-04 | 2024-11-20 | 2025-03-18 |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Electrical Heat Tracing | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F55188D3533740229D1DB3F4A1349034
DDCL | CCP-W-B000-59-IA-B19-0001 | SINGLE LINE DRAWING FOR ELECTRICAL HEAT TRACING SYSTEM (BOP) | D | C | 01 | A |  | 2024-03-26 | 2024-04-26 | 2024-06-26 | 2024-07-26 | 2024-10-31 | 2024-10-31 | 2025-03-18 |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Electrical Heat Tracing | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1A93E652B21D4D459AA4C36BD50982BB
DDCL | CCP-W-B000-59-IA-B13-0001 | ERECTION DRAWING FOR ELECTRICAL HEAT TRACING SYSTEM (BOP) | D | C | 01 | _ |  | 2024-03-26 | 2024-04-26 | 2024-06-26 | 2024-07-26 | 2024-10-04 | 2024-11-20 | 2025-03-18 | 2025-06-30 | BOP Plant | Plant EPC)제어/계측기술1팀 | Electrical Heat Tracing | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:AA9BF39EBDAB443AA6D6809DB1F9FF69
DDCL | CCP-W-B000-59-IA-B13-0003 | CABLE SCHEDULE FOR ELECTRICAL HEAT TRACING SYSTEM (BOP) | D | C | 01 | _ |  | 2024-03-26 | 2024-04-26 | 2024-06-26 | 2024-07-26 | 2025-04-17 | 2025-04-18 | 2025-06-16 | 2025-06-16 | BOP Plant | Plant EPC)제어/계측기술1팀 | Electrical Heat Tracing | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:AD40E55195F94B03969F24BBFA8763AA
DDCL | CCP-W-B000-59-IA-B13-0002 | INTERCONNECTION WIRING DIAGRAM FOR ELECTRICAL HEAT TRACING (BOP) | D | C | 01 | _ |  | 2024-03-26 | 2024-04-26 | 2024-06-26 | 2024-07-26 | 2025-06-10 | 2025-06-10 | 2025-06-25 | 2025-06-25 | BOP Plant | Plant EPC)제어/계측기술1팀 | Electrical Heat Tracing | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B47F4172CF7247BD933D9AE7D95A7936
DDCL | CCP-W-B000-51-IA-B16-0001 | DCS - FUNCTIONAL DESIGN SPECIFICATION FOR GRAPHIC | D | D | 01 | A |  | 2024-03-10 | 2024-04-10 | 2024-06-10 | 2024-07-10 | 2024-03-14 | 2024-09-10 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Distributed Control System | I&C | 김용근 | [10 empty] | CCP-EPC-TRM-PGU-0225 | D | 01 | 2024-06-28 | 2024-06-28 | 2024-07-08 | CCP-PGU-TRM-EPC-0225 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0225 | D | 01 | 2024-06-28 | 2024-06-28 | 2024-07-08 | CCP-PGU-TRM-EPC-0225 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F49D89B30CB44D38B1A67AF297566ED4
DDCL | CCP-W-B000-51-IA-B16-0002 | DCS - FUNCTIONAL DESIGN SPECIFICATION FOR HARDWARE | D | D | 01 | A |  | 2024-03-10 | 2024-04-10 | 2024-06-10 | 2024-07-10 | 2024-03-14 | 2024-09-10 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Distributed Control System | I&C | 김용근 | [10 empty] | CCP-EPC-TRM-PGU-0225 | D | 01 | 2024-06-28 | 2024-06-28 | 2024-07-08 | CCP-PGU-TRM-EPC-0225 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0225 | D | 01 | 2024-06-28 | 2024-06-28 | 2024-07-08 | CCP-PGU-TRM-EPC-0225 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CA764DBBA9FF4545BADDDDE11F2C4F5E
DDCL | CCP-W-B000-51-IA-B16-0003 | DCS - FUNCTIONAL DESIGN SPECIFICATION FOR SOFTWARE | D | D | 01 | A |  | 2024-03-10 | 2024-04-10 | 2024-06-10 | 2024-07-10 | 2024-03-14 | 2024-09-10 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Distributed Control System | I&C | 김용근 | [10 empty] | CCP-EPC-TRM-PGU-0225 | D | 01 | 2024-06-28 | 2024-06-28 | 2024-07-08 | CCP-PGU-TRM-EPC-0225 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0225 | D | 01 | 2024-06-28 | 2024-06-28 | 2024-07-08 | CCP-PGU-TRM-EPC-0225 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:9F4614DC457D40C395331EB1579F31E2
DDCL | CCP-W-B000-62-IA-B16-0001 | SPECIFICATION & DATASHEET FOR WEATHER STATION | D | C | 01 | _ |  | 2024-03-10 | 2024-04-10 | 2024-06-10 | 2024-07-10 | 2024-07-15 | 2024-09-10 | 2024-09-10 | 2024-09-11 | BOP Plant | Plant EPC)제어/계측기술1팀 | Distributed Control System | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D828F07781AC46ACB7394E925B8B77C6
DDCL | CCP-W-B000-51-IA-B16-0005 | SPECIFICATION & DATASHEET FOR LARGE SCREEN | D | D | 01 | A |  | 2024-03-10 | 2024-04-10 | 2024-06-10 | 2024-07-10 | 2024-03-14 | 2024-09-10 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Distributed Control System | I&C | 김용근 | [10 empty] | CCP-EPC-TRM-PGU-0225 | D | 01 | 2024-06-28 | 2024-06-28 | 2024-07-08 | CCP-PGU-TRM-EPC-0225 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0225 | D | 01 | 2024-06-28 | 2024-06-28 | 2024-07-08 | CCP-PGU-TRM-EPC-0225 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6EB72DCBE60749F4BA7BA1CFAD8D9EDF
DDCL | CCP-W-B000-51-IA-B16-0004 | SPECIFICATION & DATASHEET FOR MASTER CLOCK SYSTEM (GPS) | D | D | 01 | A |  | 2024-03-10 | 2024-04-10 | 2024-06-10 | 2024-07-10 | 2024-03-14 | 2024-09-10 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Distributed Control System | I&C | 김용근 | [10 empty] | CCP-EPC-TRM-PGU-0225 | D | 01 | 2024-06-28 | 2024-06-28 | 2024-07-08 | CCP-PGU-TRM-EPC-0225 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0225 | D | 01 | 2024-06-28 | 2024-06-28 | 2024-07-08 | CCP-PGU-TRM-EPC-0225 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:988CAB72FB9D47AA8CC525713802515A
DDCL | CCP-W-B000-51-IA-B16-0006 | DCS - FUNCTIONAL DESIGN SPECIFICATION FOR SAFETY RELATED SYSTEM | D | D | 01 | A |  | 2024-05-20 | 2024-06-20 | 2024-07-20 | 2024-08-20 | 2024-06-20 | 2024-09-10 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Distributed Control System | I&C | 김용근 | [10 empty] | CCP-EPC-TRM-PGU-0264 | D | 01 | 2024-07-15 | 2024-07-16 | 2024-07-08 | CCP-PGU-TRM-EPC-0225 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0225 CCP-EPC-TRM-PGU-0262 CCP-EPC-TRM-PGU-0264 | D | 01 | 2024-06-28 2024-07-15 2024-07-15 | 2024-06-28 2024-07-16 2024-07-16 | 2024-07-08 | CCP-PGU-TRM-EPC-0225 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7D72B0643ABB4A73B9745BF891C81E5B
DDCL | CCP-W-B000-51-IA-B16-9101 | DCS - SPECIFICATION & DATASHEET FOR HISTORICAL STORAGE AND RETRIEVAL (HSR) SYSTEM | D | D | 01 | A |  | 2024-05-20 | 2024-06-20 | 2024-07-20 | 2024-08-20 | 2024-06-20 | 2024-09-10 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Distributed Control System | I&C | 김용근 | [10 empty] | CCP-EPC-TRM-PGU-0225 | D | 01 | 2024-06-28 | 2024-06-28 | 2024-07-08 | CCP-PGU-TRM-EPC-0225 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0225 | D | 01 | 2024-06-28 | 2024-06-28 | 2024-07-08 | CCP-PGU-TRM-EPC-0225 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7D89ED536A5D4DB09BE1C9312153D4A3
DDCL | CCP-W-B000-51-IA-B16-9104 | DCS - SPECIFICATION & DATASHEET FOR MASTER DATA AQUISITION (MDA) SYSTEM | D | D | 01 | A |  | 2024-07-12 | 2024-07-20 | 2024-09-12 | 2024-09-20 | 2024-07-12 | 2024-09-10 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Distributed Control System | I&C | 김용근 | [10 empty] | CCP-EPC-TRM-PGU-0264 | D | 01 | 2024-07-15 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0264 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0262 CCP-EPC-TRM-PGU-0264 | D | 01 | 2024-07-15 2024-07-15 | 2024-07-16 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0264 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CBA308E080E84A9CBBD9E64182412D8D
DDCL | CCP-W-B000-51-IA-B16-0007 | DCS - FUNCTIONAL DESIGN SPECIFICATION FOR PLANT INFORMATION SYSTEM | D | D | 01 | _ |  | 2024-06-20 | 2024-07-20 | 2024-08-20 | 2024-09-20 | 2024-07-16 | 2024-07-17 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Distributed Control System | I&C | 김용근 | [10 empty] | CCP-EPC-TRM-PGU-0268 | D | 01 | 2024-07-17 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0268 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0268 | D | 01 | 2024-07-17 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0268 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8C7398B5E47C48E08976D28D6C8C8AFB
DDCL | CCP-W-B000-51-IA-B16-0008 | DCS - FUNCTIONAL DESIGN SPECIFICATION FOR CYBER SECURITY SYSTEM | D | D | 01 | _ |  | 2024-06-20 | 2024-07-20 | 2024-08-20 | 2024-09-20 | 2024-07-16 | 2024-07-17 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Distributed Control System | I&C | 김용근 | [10 empty] | CCP-EPC-TRM-PGU-0268 | D | 01 | 2024-07-17 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0268 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0268 | D | 01 | 2024-07-17 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0268 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6996553570614C56A147093946014461
DDCL | CCP-W-B100-51-IA-B19-0001 | DCS - NETWORK CONFIGURATION DIAGRAM (BLOCK) | D | D | 01 | A |  | 2024-03-10 | 2024-04-10 | 2024-06-10 | 2024-07-10 | 2024-03-14 | 2024-09-10 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Distributed Control System | I&C | 김용근 | [10 empty] | CCP-EPC-TRM-PGU-0264 | D | 01 | 2024-07-15 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0264 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0262 CCP-EPC-TRM-PGU-0264 | D | 01 | 2024-07-15 2024-07-15 | 2024-07-16 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0264 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6C2AB53D791C4FB58A604F35B6CD4D20
DDCL | CCP-W-B100-51-IA-B31-0001 | DCS - HMI GRAPHIC DRAWING (BLOCK) | D | D | 01 | _ |  | 2024-08-29 | 2024-09-29 | 2025-02-01 | 2025-03-01 | 2024-09-10 | 2024-09-11 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Distributed Control System | I&C | 김용근 | [10 empty] | CCP-EPC-TRM-PGU-0474 | D | 01 | 2024-09-11 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0474 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0474 | D | 01 | 2024-09-11 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0474 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D98716784E674A7BB646080C8F25F386
DDCL | CCP-W-B000-51-IA-H01-0001 | DCS - IO & MODULE ALLOCATION DRAWING | D | D | 01 | A |  | 2024-03-26 | 2024-04-26 | 2024-06-26 | 2024-07-26 | 2024-06-20 | 2024-09-10 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Distributed Control System | I&C | 김용근 | [10 empty] | CCP-EPC-TRM-PGU-0225 | D | 01 | 2024-06-28 | 2024-06-28 | 2024-07-08 | CCP-PGU-TRM-EPC-0225 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0225 | D | 01 | 2024-06-28 | 2024-06-28 | 2024-07-08 | CCP-PGU-TRM-EPC-0225 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:72702C486F0D4B449E2EC61C81A082EF
DDCL | CCP-W-B000-51-IA-E31-0001 | DCS - GROUNDING DETAIL DRAWING | D | D | 01 | A |  | 2024-03-26 | 2024-04-26 | 2024-06-26 | 2024-07-26 | 2024-06-20 | 2024-09-10 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Distributed Control System | I&C | 김용근 | [10 empty] | CCP-EPC-TRM-PGU-0225 | D | 01 | 2024-06-28 | 2024-06-28 | 2024-07-08 | CCP-PGU-TRM-EPC-0225 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0225 | D | 01 | 2024-06-28 | 2024-06-28 | 2024-07-08 | CCP-PGU-TRM-EPC-0225 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:AFC548B6C8A04BEA8B19F191809F3257
DDCL | CCP-W-B000-IA-342-0001 | DCS IO DATABASE (COMMON) | D | C | 01 | _ |  | 2024-04-01 | 2024-05-01 | 2024-08-01 | 2024-09-01 | 2024-05-23 | 2024-09-10 | 2024-09-25 | 2024-09-26 | BOP Plant | Plant EPC)제어/계측기술1팀 | Distributed Control System | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3F10F792439643D08CF56A32A74F6B20
DDCL | CCP-W-B000-51-IA-H03-0001 | DCS - CABLE LIST | D | D | 01 | A |  | 2024-04-26 | 2024-05-26 | 2024-07-26 | 2024-08-26 | 2024-07-16 | 2024-09-10 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Distributed Control System | I&C | 김용근 | [10 empty] | CCP-EPC-TRM-PGU-0268 | D | 01 | 2024-07-17 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0268 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0268 | D | 01 | 2024-07-17 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0268 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CE5E23793DD240F5A6C9633F6EED7E9D
DDCL | CCP-W-B000-51-IA-H05-0006 | DCS - OUTLINE & DETAIL DRAWING FOR SAFETY RELATED SYSTEM CABINET | D | D | 01 | A |  | 2024-04-26 | 2024-05-26 | 2024-07-26 | 2024-08-26 | 2024-07-15 | 2024-09-10 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Distributed Control System | I&C | 김용근 | [10 empty] | CCP-EPC-TRM-PGU-0264 | D | 01 | 2024-07-15 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0264 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0262 CCP-EPC-TRM-PGU-0264 | D | 01 | 2024-07-15 2024-07-15 | 2024-07-16 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0264 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:0F357DF667E440A5BADC754D2F15E3FC
DDCL | CCP-W-B000-51-IA-H05-0004 | DCS - OUTLINE & DETAIL DRAWING FOR NETWORK CABINET | D | D | 01 | A |  | 2024-04-26 | 2024-05-26 | 2024-07-26 | 2024-08-26 | 2024-07-15 | 2024-09-10 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Distributed Control System | I&C | 김용근 | [10 empty] | CCP-EPC-TRM-PGU-0264 | D | 01 | 2024-07-15 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0264 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0262 CCP-EPC-TRM-PGU-0264 | D | 01 | 2024-07-15 2024-07-15 | 2024-07-16 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0264 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:438CC9C1D916415A8D4BDFBA4FD46FD0
DDCL | CCP-W-B000-51-IA-H05-0002 | DCS - Outline & Detail drawing for SYSTEM AND MARSHALLING CABINET | D | D | 01 | A |  | 2024-04-26 | 2024-05-26 | 2024-07-26 | 2024-08-26 | 2024-07-15 | 2024-09-10 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Distributed Control System | I&C | 김용근 | [10 empty] | CCP-EPC-TRM-PGU-0264 | D | 01 | 2024-07-15 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0264 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0262 CCP-EPC-TRM-PGU-0264 | D | 01 | 2024-07-15 2024-07-15 | 2024-07-16 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0264 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CD3B8AA6C3F249BCA5427CA451570D18
DDCL | CCP-W-B000-51-IA-H05-0005 | DCS - OUTLINE & DETAIL DRAWING FOR POWER DISTRIBUTION CABINET | D | D | 01 | A |  | 2024-04-26 | 2024-05-26 | 2024-07-26 | 2024-08-26 | 2024-07-15 | 2024-09-10 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Distributed Control System | I&C | 김용근 | [10 empty] | CCP-EPC-TRM-PGU-0264 | D | 01 | 2024-07-15 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0264 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0262 CCP-EPC-TRM-PGU-0264 | D | 01 | 2024-07-15 2024-07-15 | 2024-07-16 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0264 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:28207BD4F27F4DD7A7086BE72A77B097
DDCL | CCP-W-B000-51-IA-H05-0001 | DCS - OUTLINE & DETAIL DRAWING FOR CONSOLE DESK & PRINTER DESK | D | D | 01 | A |  | 2024-04-26 | 2024-05-26 | 2024-07-26 | 2024-08-26 | 2024-07-15 | 2024-09-10 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Distributed Control System | I&C | 김용근 | [10 empty] | CCP-EPC-TRM-PGU-0264 | D | 01 | 2024-07-15 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0264 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0262 CCP-EPC-TRM-PGU-0264 | D | 01 | 2024-07-15 2024-07-15 | 2024-07-16 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0264 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:DD61752D61944A828AA3717647AD25F5
DDCL | CCP-W-B000-51-IA-B19-0001 | DCS - NETWORK CONFIGURATION DIAGRAM (COMMON) | D | D | 01 | A |  | 2024-03-10 | 2024-04-10 | 2024-06-10 | 2024-07-10 | 2024-03-14 | 2024-09-10 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Distributed Control System | I&C | 김용근 | [10 empty] | CCP-EPC-TRM-PGU-0264 | D | 01 | 2024-07-15 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0264 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0264 | D | 01 | 2024-07-15 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0264 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B8CD7146B52244A2A35A90F7037FC9DC
DDCL | CCP-W-B000-51-IA-B31-0001 | DCS - HMI GRAPHIC DRAWING (COMMON) | D | D | 01 | _ |  | 2024-08-29 | 2024-09-29 | 2025-02-01 | 2025-03-01 | 2024-09-10 | 2024-09-11 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Distributed Control System | I&C | 김용근 | [10 empty] | CCP-EPC-TRM-PGU-0474 | D | 01 | 2024-09-11 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0474 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0474 | D | 01 | 2024-09-11 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0474 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CAF6C4CFE248424EBE78A8BA068F08AF
DDCL | CCP-W-B000-51-IA-H03-0002 | DCS - INTERNAL CABLE CONNECTION DIAGRAM | D | D | 01 | B |  | 2024-04-26 | 2024-05-26 | 2024-07-26 | 2024-08-26 | 2024-06-20 | 2024-09-10 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Distributed Control System | I&C | 김용근 | [10 empty] | CCP-EPC-TRM-PGU-0264 | D | 01 | 2024-07-15 | 2024-07-16 | 2024-07-08 | CCP-PGU-TRM-EPC-0225 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0225 CCP-EPC-TRM-PGU-0262 CCP-EPC-TRM-PGU-0264 | D | 01 | 2024-06-28 2024-07-15 2024-07-15 | 2024-06-28 2024-07-16 2024-07-16 | 2024-07-08 | CCP-PGU-TRM-EPC-0225 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F54C7518EA0D425EAC1D77095B956D1B
DDCL | CCP-W-B000-53-IA-B16-0001 | SPECIFICATION & DATASHEET FOR VMS (BOP) | D | D | 01 | A |  | 2024-02-15 | 2024-03-15 | 2024-05-15 | 2024-06-15 | 2024-03-25 | 2024-09-11 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Vibration Monitorning & Analysis System | I&C | 김용근 | [10 empty] | CCP-EPC-TRM-PGU-0260 | D | 01 | 2024-07-12 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0260 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0260 | D | 01 | 2024-07-12 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0260 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:9F465E8351CB48B789791E53FE0F638D
DDCL | CCP-W-B000-52-IA-B16-0001 | TECHNICAL SPECIFICATION FOR I&C CABLE | D | C | 01 | _ |  | 2024-03-10 | 2024-04-10 | 2024-06-10 | 2024-07-10 | 2025-02-10 | 2025-02-11 | 2025-03-05 | 2025-03-10 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C Cable | I&C | 박종윤 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C75811794C754604BE05251065EF2587
DDCL | CCP-W-B000-60-IA-B16-0001 | SPECIFICATION & DATASHEET FOR CONTROL VALVE (BOP) | D | D | 01 | _ |  | 2024-03-10 | 2024-04-10 | 2024-06-10 | 2024-07-10 | 2024-03-20 | 2024-08-07 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Control Valve | I&C | 김용근 | [10 empty] | CCP-EPC-TRM-PGU-0290 | D | 01 | 2024-07-19 | 2024-07-24 | 2024-08-03 | CCP-PGU-TRM-EPC-0290 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0290 | D | 01 | 2024-07-19 | 2024-07-24 | 2024-08-03 | CCP-PGU-TRM-EPC-0290 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3D668B660C704CC2ADEA592D72839C43
DDCL | CCP-PW-B000-IA-305-0002 | CONTROL VALVE LIST (BOP) | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 |  | 2023-09-26 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Control Valve | I&C | 오준호 | [10 empty] | CCP-EPC-TRM-PGU-0025 | D | 01 | 2023-09-26 | 2023-09-26 | 2023-10-16 | CCP-PGU-TRM-EPC-0025 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0025 | D | 01 | 2023-09-26 | 2023-09-26 | 2023-10-16 | CCP-PGU-TRM-EPC-0025 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1A2DC8D2C2CD4745ADFA431668C17762
DDCL | CCP-W-B000-58-IA-B16-0002 | SPECIFICATION & DATASHEET FOR PROCESS TRANSMITTER (BOP) | D | D | 01 | A |  | 2024-03-01 | 2024-04-01 | 2024-06-01 | 2024-07-01 | 2024-04-01 | 2024-08-08 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Field Instrument | I&C | 박종윤 | [10 empty] | CCP-EPC-TRM-PGU-0250 | D | 01 | 2024-07-09 | 2024-07-11 | 2024-07-21 | CCP-PGU-TRM-EPC-0250 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0250 | D | 01 | 2024-07-09 | 2024-07-11 | 2024-07-21 | CCP-PGU-TRM-EPC-0250 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FE372D3C28774E1DBDE6517E55F1950F
DDCL | CCP-W-B000-58-IA-B16-0001 | SPECIFICATION & DATASHEET FOR LOCAL INSTRUMENT (BOP) | D | D | 01 | _ |  | 2024-03-01 | 2024-04-01 | 2024-06-01 | 2024-07-01 | 2024-04-16 | 2024-07-24 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Field Instrument | I&C | 박종윤 | [10 empty] | CCP-EPC-TRM-PGU-0309 | D | 01 | 2024-07-24 | 2024-07-25 | 2024-08-04 | CCP-PGU-TRM-EPC-0309 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0309 | D | 01 | 2024-07-24 | 2024-07-25 | 2024-08-04 | CCP-PGU-TRM-EPC-0309 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:94C9E790C96B4BF1A4377379A2D9B930
DDCL | CCP-W-B000-58-IA-B16-0003 | SPECIFICATION & DATASHEET FOR FLOW ELEMENT (BOP) | D | D | 01 | A |  | 2024-03-01 | 2024-04-01 | 2024-06-01 | 2024-07-01 | 2024-04-16 | 2024-08-08 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Field Instrument | I&C | 박종윤 | [10 empty] | CCP-EPC-TRM-PGU-0289 | D | 01 | 2024-07-19 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0289 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0289 | D | 01 | 2024-07-19 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0289 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:0594FC3248F74A94B46F93041A748E32
DDCL | CCP-W-B000-58-IA-B16-0004 | SPECIFICATION & DATASHEET FOR GAS METERING SYSTEM | D | C | 01 | _ |  | 2024-04-26 | 2024-05-26 | 2024-07-26 | 2024-08-26 | 2024-07-12 |  | 2024-10-28 | 2024-10-29 | BOP Plant | Plant EPC)제어/계측기술1팀 | Metering Station | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:173342D14A644F6E87FE75D8FFD67C88
DDCL | CCP-W-B000-58-IA-B16-0005 | SPECIFICATION & DATASHEET FOR OIL METERING SYSTEM | D | C | 01 | _ |  | 2024-06-20 | 2024-07-20 | 2024-08-20 | 2024-09-20 | 2024-07-17 |  | 2024-10-28 | 2024-10-29 | BOP Plant | Plant EPC)제어/계측기술1팀 | Metering Station | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7788C5A8A7654A17AAEA0542EACF3A8A
DDCL | CCP-W-B000-IA-305-0001 | FIELD INSTRUMENT LIST (BOP) | D | C | 01 | A |  | 2024-02-15 | 2024-03-15 | 2024-05-15 | 2024-06-15 | 2024-03-12 | 2024-09-06 | 2024-09-06 | 2025-01-15 | BOP Plant | Plant EPC)제어/계측기술1팀 | Field Instrument | I&C | 박종윤 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:77030F6223864CC0B7D30D457D2E64DD
DDCL | CCP-W-B000-IA-303-0001 | SPECIFICATION & DATASHEET FOR JB & ENCLOSURE | D | C | 01 | A |  | 2024-04-26 | 2024-05-26 | 2024-07-26 | 2024-08-26 | 2024-10-02 | 2024-10-02 | 2024-11-22 | 2025-04-08 | BOP Plant | Plant EPC)제어/계측기술1팀 | Local Box | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:60F3748DB7BD4A56B8CD1DC5F1654272
DDCL | CCP-W-B000-54-IA-B16-0001 | TECHNICAL SPECIFICATION FOR INSTRUMENT INSTALLATION MATERIALS | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-04-05 | 2024-07-08 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | Instrument Installation Material | I&C | 김용근 | [10 empty] | CCP-EPC-TRM-PGU-0249 | D | 01 | 2024-07-09 | 2024-07-11 | 2024-07-21 | CCP-PGU-TRM-EPC-0249 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0249 | D | 01 | 2024-07-09 | 2024-07-11 | 2024-07-21 | CCP-PGU-TRM-EPC-0249 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:05C3CE155E4C4868857D60DB15DE83D1
DDCL | CCP-W-B100-IA-342-0001 | DCS IO DATABASE (BLOCK) | D | C | 01 | _ |  | 2024-04-01 | 2024-05-01 | 2024-08-01 | 2024-09-01 | 2024-05-23 | 2024-09-26 | 2024-09-26 | 2024-09-26 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_DCS_IO | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:58CEDEE358A648C0AA79F0B15A87F5E5
DDCL | CCP-W-B000-IA-342-0002 | DCS IO DATABASE (DATALINK) | D | C | 01 | _ |  | 2024-08-26 | 2024-09-26 | 2024-11-26 | 2024-12-26 | 2024-10-22 | 2024-10-22 | 2024-12-19 | 2024-12-19 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_DCS_IO | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FD07C868139B4C2BA2B20E4D0C4C1334
DDCL | CCP-W-B000-IA-318-0011 | CONTROL LOOP DIAGRAM - OIL FACILITY | D | C | 01 | _ |  | 2024-05-03 | 2024-06-03 | 2024-08-03 | 2024-09-03 | 2024-10-03 | 2024-10-07 | 2024-11-01 | 2024-11-01 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic & Loop | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B99B8016F0EE440AA5FF5BE6C5545E51
DDCL | CCP-W-B000-IA-315-0011 | CONTROL LOGIC DIAGRAM - OIL FACILITY | D | C | 01 | _ |  | 2024-05-03 | 2024-06-03 | 2024-08-03 | 2024-09-03 | 2024-10-03 | 2024-10-07 | 2024-11-01 | 2024-11-01 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic & Loop | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6C3C02FA0A9846269E79E87CA27510F3
DDCL | CCP-W-B000-IA-318-0100 | PLANT MASTER CONTROL DIAGRAM | D | D | 01 | _ | FC DELAY | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2025-04-15 | 2025-04-15 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_PMC | I&C | 박종윤 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CF5037E4220643E3BC37E2A80FA3EBA1
DDCL | CCP-W-B000-IA-318-0016 | CONTROL LOOP DIAGRAM - INTERFACE FOR PACKAGE SYSTEM (BLOCK) | D | C | 01 | _ |  | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2024-09-26 | 2024-09-27 | 2024-11-13 | 2024-11-13 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic & Loop | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:884648F953624C8C9785DB25D0E204F1
DDCL | CCP-W-B000-IA-318-0017 | CONTROL LOOP DIAGRAM - ELECTRICAL SYSTEM | D | C | 01 | _ | FC DELAY | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2024-11-28 | 2024-11-29 | 2024-12-26 |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic & Loop | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:35459A6B686746CD87D92D0A987160D7
DDCL | CCP-W-B000-IA-318-0018 | CONTROL LOOP DIAGRAM - INTERFACE FOR PACKAGE SYSTEM (COMMON) | D | C | 01 | _ |  | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2024-09-26 | 2024-09-27 | 2024-11-13 | 2024-11-13 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic & Loop | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FCD9E86681B64263831B54196D3F5FC9
DDCL | CCP-W-B000-IA-318-0019 | CONTROL LOOP DIAGRAM - INTERFACE FOR TURBINE | D | C | 01 | _ |  | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2024-09-26 | 2024-09-27 | 2024-11-13 | 2024-11-13 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic & Loop | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:37024411B6C44CAF875910D15FE2ED66
DDCL | CCP-W-B000-IA-318-0021 | CONTROL LOOP DIAGRAM - UTILITY DISTRIBUTION SYSTEM | D | C | 01 | _ |  | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2024-11-13 | 2024-11-13 | 2024-12-20 | 2024-12-20 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic & Loop | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3CA92A4A1A234359901A48567814B2A7
DDCL | CCP-W-B000-IA-315-0018 | CONTROL LOGIC DIAGRAM - INTERFACE FOR PACKAGE SYSTEM (COMMON) | D | C | 01 | _ |  | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2024-09-26 | 2024-09-27 | 2024-11-13 | 2024-11-13 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic & Loop | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A9C7E38F6EE8434EADBDDA0C9CBF99BD
DDCL | CCP-W-B000-IA-315-0019 | CONTROL LOGIC DIAGRAM - INTERFACE FOR TURBINE | D | C | 01 | _ |  | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2024-09-26 | 2024-09-27 | 2024-11-13 | 2024-11-13 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic & Loop | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7F05FF4D32794BE6B0E2FB25E527C870
DDCL | CCP-W-B000-IA-318-0003 | CONTROL LOOP DIAGRAM - MAIN AND PROCESS STEAM SYSTEM | D | C | 01 | _ |  | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2024-09-27 | 2024-09-27 | 2024-10-31 | 2024-10-31 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic & Loop | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:26E2FD5760684BEC9282FA2E939FFE16
DDCL | CCP-W-B000-IA-318-0004 | CONTROL LOOP DIAGRAM - AUX STEAM SYSTEM | D | C | 01 | _ |  | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2024-09-27 | 2024-09-27 | 2024-10-31 | 2024-10-31 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic & Loop | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F2FFF8030E974ADAA15DEF8B9F5A8191
DDCL | CCP-W-B000-IA-318-0005 | CONTROL LOOP DIAGRAM - HOT WATER DISTRIBUTION SYSTEM | D | C | 01 | _ |  | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2024-10-21 |  | 2024-11-07 | 2024-11-07 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic & Loop | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:74D443E593664C278E915A5D8BA99E0F
DDCL | CCP-W-B000-IA-318-0007 | CONTROL LOOP DIAGRAM - FEEDWATER SYSTEM | D | C | 01 | _ |  | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2024-10-18 | 2024-10-18 | 2024-11-04 | 2024-11-04 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic & Loop | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:BBB00E0A974F4B9BB696200F6AFD3377
DDCL | CCP-W-B000-IA-318-0008 | CONTROL LOOP DIAGRAM - CONDENSATE SYSTEM | D | C | 01 | _ |  | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2024-09-27 | 2024-09-27 | 2024-11-11 | 2024-11-11 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic & Loop | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:325E11BCDDAB40FFAFC78BD4A256D86D
DDCL | CCP-W-B000-IA-318-0010 | CONTROL LOOP DIAGRAM - CLOSED COOLING WATER SYSTEM | D | C | 01 | _ |  | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2024-09-27 | 2024-09-27 | 2024-11-08 | 2024-11-11 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic & Loop | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D2D260F610C24DC7A24D609FB11EEEAD
DDCL | CCP-W-B000-IA-318-0012 | CONTROL LOOP DIAGRAM - FUEL OIL SYSTEM | D | C | 01 | _ |  | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2024-09-27 | 2024-09-27 | 2024-12-20 | 2024-12-20 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic & Loop | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:845E42BED7F740919B41477FD86B380B
DDCL | CCP-W-B000-IA-315-0003 | CONTROL LOGIC DIAGRAM - MAIN AND PROCESS STEAM SYSTEM | D | C | 01 | _ |  | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2024-09-27 | 2024-09-27 | 2024-10-31 | 2024-10-31 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic & Loop | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CA02E6BF241C4A6FAB82E07674B3DE65
DDCL | CCP-W-B000-IA-315-0004 | CONTROL LOGIC DIAGRAM - AUX STEAM SYSTEM | D | C | 01 | _ |  | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2024-09-27 | 2024-09-27 | 2024-10-31 | 2024-10-31 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic & Loop | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:62B8542ACD4D45D5A56184144C5BA301
DDCL | CCP-W-B000-IA-315-0005 | CONTROL LOGIC DIAGRAM - HOT WATER DISTRIBUTION SYSTEM | D | C | 01 | _ |  | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2024-10-21 |  | 2024-11-07 | 2024-11-07 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic & Loop | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:996EE39F30914ED58005761596810D3E
DDCL | CCP-W-B000-IA-315-0007 | CONTROL LOGIC DIAGRAM - FEEDWATER SYSTEM | D | C | 01 | _ |  | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2024-10-25 | 2024-10-28 | 2024-11-04 | 2024-11-04 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic & Loop | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3601A7E104594C0C9F9B7C96524A085D
DDCL | CCP-W-B000-IA-315-0008 | CONTROL LOGIC DIAGRAM - CONDENSATE SYSTEM | D | C | 01 | _ |  | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2024-09-27 | 2024-09-27 | 2024-11-11 | 2024-11-11 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic & Loop | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:BCCB39EA1E434BF982AB15E7B4350DD2
DDCL | CCP-W-B000-IA-315-0010 | CONTROL LOGIC DIAGRAM - CLOSED COOLING WATER SYSTEM | D | C | 01 | _ |  | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2024-09-27 | 2024-09-27 | 2024-11-08 | 2024-11-11 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic & Loop | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:92D604D19F314E7387316B3D52B028E4
DDCL | CCP-W-B000-IA-315-0012 | CONTROL LOGIC DIAGRAM - FUEL OIL SYSTEM | D | C | 01 | _ |  | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2024-09-27 | 2024-09-27 | 2024-12-20 | 2024-12-20 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic & Loop | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1E78FFFC585748E084788F9A8BC4DC9A
DDCL | CCP-W-B000-IA-315-0016 | CONTROL LOGIC DIAGRAM - INTERFACE FOR PACKAGE SYSTEM (BLOCK) | D | C | 01 | _ |  | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2024-09-26 | 2024-09-27 | 2024-11-13 | 2024-11-13 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic & Loop | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4BBA0865E6B14108B79518E283315DE6
DDCL | CCP-W-B000-IA-315-0017 | CONTROL LOGIC DIAGRAM - ELECTRICAL SYSTEM | D | C | 01 | _ | FC DELAY | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2024-11-28 | 2024-11-29 | 2024-12-26 |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic & Loop | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D97E81EFCEC844E795C9743767A7C820
DDCL | CCP-W-B000-IA-315-0021 | CONTROL LOGIC DIAGRAM - UTILITY DISTRIBUTION SYSTEM | D | C | 01 | _ |  | 2024-12-25 | 2025-01-25 | 2025-01-31 | 2025-02-28 | 2024-12-20 | 2024-12-20 | 2025-03-18 | 2025-03-18 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic & Loop | I&C | 박종윤 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:16054531630141F28625222391AE4C66
DDCL | CCP-W-B000-IA-334-0014 | INSTRUMENT INSTALLATION DETAIL DRAWINGS - INSTRUMENT BOX | D | D | 01 | _ |  | 2024-02-15 | 2024-03-15 | 2024-05-15 | 2024-06-15 | 2024-03-12 | 2024-06-18 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IID(TPP) | I&C | 박종윤 | [10 empty] | CCP-EPC-TRM-PGU-0203 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0203 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0203 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0203 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:65212F35BF4C440D8E927CE54D6FAB5B
DDCL | CCP-W-B000-IA-334-0002 | INSTRUMENT INSTALLATION DETAIL DRAWINGS - SYMBOL & LEGEND | D | D | 01 | _ |  | 2024-02-15 | 2024-03-15 | 2024-05-15 | 2024-06-15 | 2024-03-12 | 2024-06-18 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IID(TPP) | I&C | 박종윤 | [10 empty] | CCP-EPC-TRM-PGU-0203 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0203 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0203 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0203 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8AD7DE538FB44524B18E14BC595049DE
DDCL | CCP-W-B000-IA-334-0003 | INSTRUMENT INSTALLATION DETAIL DRAWINGS - MATERIAL LIST | D | D | 01 | _ |  | 2024-02-15 | 2024-03-15 | 2024-05-15 | 2024-06-15 | 2024-03-12 | 2024-06-18 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IID(TPP) | I&C | 박종윤 | [10 empty] | CCP-EPC-TRM-PGU-0203 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0203 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0203 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0203 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A30178AEB081459B90722C92AE3AE4F4
DDCL | CCP-W-B000-IA-334-0004 | INSTRUMENT INSTALLATION DETAIL DRAWINGS - PRESSURE TRANSMITTER | D | D | 01 | _ |  | 2024-02-15 | 2024-03-15 | 2024-05-15 | 2024-06-15 | 2024-03-12 | 2024-06-18 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IID(TPP) | I&C | 박종윤 | [10 empty] | CCP-EPC-TRM-PGU-0203 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0203 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0203 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0203 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FA1AEC6D48204E1FBB9572118DC8F28E
DDCL | CCP-W-B000-IA-334-0005 | INSTRUMENT INSTALLATION DETAIL DRAWINGS - DIFFERENTIAL PRESSURE TRANSMITTER | D | D | 01 | _ |  | 2024-02-15 | 2024-03-15 | 2024-05-15 | 2024-06-15 | 2024-03-12 | 2024-06-18 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IID(TPP) | I&C | 박종윤 | [10 empty] | CCP-EPC-TRM-PGU-0203 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0203 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0203 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0203 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:39F84257BCBD40869F8E71B16E68C5CD
DDCL | CCP-W-B000-IA-334-0006 | INSTRUMENT INSTALLATION DETAIL DRAWINGS - FLOW TRANSMITTER | D | D | 01 | _ |  | 2024-02-15 | 2024-03-15 | 2024-05-15 | 2024-06-15 | 2024-03-12 | 2024-06-18 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IID(TPP) | I&C | 박종윤 | [10 empty] | CCP-EPC-TRM-PGU-0203 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0203 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0203 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0203 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:EBF2B1105F6C41209DBCF5B029B228F3
DDCL | CCP-W-B000-IA-334-0007 | INSTRUMENT INSTALLATION DETAIL DRAWINGS - LEVEL TRANSMITTER | D | D | 01 | _ |  | 2024-02-15 | 2024-03-15 | 2024-05-15 | 2024-06-15 | 2024-03-12 | 2024-06-18 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IID(TPP) | I&C | 박종윤 | [10 empty] | CCP-EPC-TRM-PGU-0203 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0203 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0203 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0203 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B812FEC121F947EE929F4FD6B9347714
DDCL | CCP-W-B000-IA-334-0008 | INSTRUMENT INSTALLATION DETAIL DRAWINGS - PRESSURE GAUGE | D | D | 01 | _ |  | 2024-02-15 | 2024-03-15 | 2024-05-15 | 2024-06-15 | 2024-03-12 | 2024-06-18 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IID(TPP) | I&C | 박종윤 | [10 empty] | CCP-EPC-TRM-PGU-0203 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0203 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0203 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0203 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C1CAF9CD16C14B87AA7E3F26AE3DD010
DDCL | CCP-W-B000-IA-334-0012 | INSTRUMENT INSTALLATION DETAIL DRAWINGS - PNEUMATIC CONTROL VALVES | D | D | 01 | _ |  | 2024-02-15 | 2024-03-15 | 2024-05-15 | 2024-06-15 | 2024-03-12 | 2024-06-18 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IID(TPP) | I&C | 박종윤 | [10 empty] | CCP-EPC-TRM-PGU-0203 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0203 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0203 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0203 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8414DC21AF1A4732BA80CF09C74FED82
DDCL | CCP-W-B000-IA-334-0009 | INSTRUMENT INSTALLATION DETAIL DRAWINGS - TEMPERATURE TRANSMITTER | D | D | 01 | _ |  | 2024-02-15 | 2024-03-15 | 2024-05-15 | 2024-06-15 | 2024-03-12 | 2024-06-18 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IID(TPP) | I&C | 박종윤 | [10 empty] | CCP-EPC-TRM-PGU-0203 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0203 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0203 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0203 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:76013DA9A88C4E0BA3507D3D76CABC9A
DDCL | CCP-W-B000-IA-334-0010 | INSTRUMENT INSTALLATION DETAIL DRAWINGS - TEMPERATURE GAUGE | D | D | 01 | _ |  | 2024-02-15 | 2024-03-15 | 2024-05-15 | 2024-06-15 | 2024-03-12 | 2024-06-18 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IID(TPP) | I&C | 박종윤 | [10 empty] | CCP-EPC-TRM-PGU-0203 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0203 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0203 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0203 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:886DECB7B98542BA9B6CCDC587C17CDD
DDCL | CCP-W-B000-IA-334-0011 | INSTRUMENT INSTALLATION DETAIL DRAWINGS - TEST WELL | D | D | 01 | _ |  | 2024-02-15 | 2024-03-15 | 2024-05-15 | 2024-06-15 | 2024-03-12 | 2024-06-18 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IID(TPP) | I&C | 박종윤 | [10 empty] | CCP-EPC-TRM-PGU-0203 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0203 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0203 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0203 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D26B589F110242FABEF7D7ED853BDA7F
DDCL | CCP-W-B000-IA-334-0013 | INSTRUMENT INSTALLATION DETAIL DRAWINGS - CONDENSATE POT DETAIL | D | D | 01 | _ |  | 2024-02-15 | 2024-03-15 | 2024-05-15 | 2024-06-15 | 2024-03-12 | 2024-06-18 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IID(TPP) | I&C | 박종윤 | [10 empty] | CCP-EPC-TRM-PGU-0203 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0203 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0203 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0203 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:BC6EB10A367F4D80BAE612A2B8FC2FEC
DDCL | CCP-W-B000-IA-334-0001 | INSTRUMENT INSTALLATION DETAIL DRAWINGS - GENERAL NOTE | D | D | 01 | _ |  | 2024-02-15 | 2024-03-15 | 2024-05-15 | 2024-06-15 | 2024-03-12 | 2024-06-18 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IID(TPP) | I&C | 박종윤 | [10 empty] | CCP-EPC-TRM-PGU-0203 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0203 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0203 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0203 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7835404A44384015B3D581EA242AD455
DDCL | CCP-W-B000-IA-315-0001 | CONTROL LOGIC DIAGRAM - SYMBOL & LEGEND | D | C | 01 | A |  | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2024-09-27 | 2024-09-27 | 2024-10-28 | 2024-10-29 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic&Loop Symbol | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:245A93CC503C4DD19B78CD11D308A23F
DDCL | CCP-W-B000-IA-315-0002 | CONTROL LOGIC DIAGRAM - TYPICAL FUNCTION | D | C | 01 | _ |  | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2024-09-27 | 2024-09-27 | 2024-10-28 | 2024-10-28 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic&Loop Symbol | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:941678E119D7473DA63580C57FF3A072
DDCL | CCP-W-B000-IA-318-0001 | CONTROL LOOP DIAGRAM - SYMBOL & LEGEND | D | C | 01 | _ |  | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2024-09-27 | 2024-09-27 | 2024-10-28 | 2024-10-28 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic&Loop Symbol | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1DB270751FBF4D9895A3423D7E96BBC5
DDCL | CCP-W-B000-IA-318-0002 | CONTROL LOOP DIAGRAM - TYPICAL FUNCTION | D | C | 01 | _ |  | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2024-09-27 | 2024-09-27 | 2024-10-28 | 2024-10-28 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Logic&Loop Symbol | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F82B5E77CBC04524BB24A04C8ED2B6B5
DDCL | CCP-W-B000-IA-315-0100 | PLANT START-UP & SHUTDOWN DIAGRAM - SYMBOL & LEGEND | D | C | 01 | _ |  | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2024-10-28 | 2024-10-28 | 2025-01-21 | 2025-01-21 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Start&Shutdown Diagram(TPP) | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F9BCA0FE59F84C1EA7BD175354363C0E
DDCL | CCP-W-B000-IA-315-0101 | PLANT START-UP & SHUTDOWN DIAGRAM - START-UP SEQUENCE | D | D | 02 | _ | FC DELAY | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2025-02-03 | 2025-05-27 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Start&Shutdown Diagram(TPP) | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:40487873653041F4B41BEF1406719BA2
DDCL | CCP-W-B000-IA-315-0102 | PLANT START-UP & SHUTDOWN DIAGRAM - SHUTDOWN SEQUENCE | D | C | 01 | _ |  | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2025-02-03 | 2025-02-04 | 2025-05-28 | 2025-05-28 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Start&Shutdown Diagram(TPP) | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B1E6C8240A20482E8DBB18BCF98C7EFB
DDCL | CCP-W-B089-IA-301-0112 | TYPICAL ELEMENTARY WIRING DIAGRAM - MV SWGR INCOMER | D | C | 01 | A |  | 2024-03-30 | 2024-04-30 | 2024-06-30 | 2024-07-30 | 2024-03-14 |  | 2024-10-15 | 2024-12-13 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Typical Elementary | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C37B484F0E71452AA1935D855F814CF6
DDCL | CCP-W-B089-IA-301-0113 | TYPICAL ELEMENTARY WIRING DIAGRAM - LV SWGR INCOMER | D | C | 01 | A |  | 2024-03-30 | 2024-04-30 | 2024-06-30 | 2024-07-30 | 2024-03-14 |  | 2024-10-15 | 2024-12-13 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Typical Elementary | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3EAFB7DA950B4ECF839B0AC14D7A4DE0
DDCL | CCP-W-B089-IA-301-0114 | TYPICAL ELEMENTARY WIRING DIAGRAM - MV SWGR BUS TIE | D | C | 01 | A |  | 2024-03-30 | 2024-04-30 | 2024-06-30 | 2024-07-30 | 2024-03-14 |  | 2024-10-15 | 2024-12-13 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Typical Elementary | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D1A9F00266EA437CBDE1D569EF6832C8
DDCL | CCP-W-B089-IA-301-0115 | TYPICAL ELEMENTARY WIRING DIAGRAM - LV SWGR BUS TIE | D | C | 01 | A |  | 2024-03-30 | 2024-04-30 | 2024-06-30 | 2024-07-30 | 2024-03-14 |  | 2024-10-15 | 2024-12-13 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Typical Elementary | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:EA7E7B76908D4F3C8822B616C9B8DB25
DDCL | CCP-W-B089-IA-301-0101 | TYPICAL ELEMENTARY WIRING DIAGRAM - 10KV MV SWGR MOTOR FEEDER | D | C | 01 | A |  | 2024-03-30 | 2024-04-30 | 2024-06-30 | 2024-07-30 | 2024-03-14 | 2024-09-13 | 2024-09-13 | 2024-12-13 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Typical Elementary | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4408072DCAE94457A792E330471E9131
DDCL | CCP-W-B089-IA-301-0102 | TYPICAL ELEMENTARY WIRING DIAGRAM - 400V LV SWGR MOTOR FEEDER (ABOVE 160KW) | D | C | 01 | A |  | 2024-03-30 | 2024-04-30 | 2024-06-30 | 2024-07-30 | 2024-03-14 | 2024-09-13 | 2024-09-13 | 2024-12-13 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Typical Elementary | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:777F4214FBED4738A4998D637D2BB381
DDCL | CCP-W-B089-IA-301-0116 | TYPICAL ELEMENTARY WIRING DIAGRAM - MV SWGR NON-MOTOR FEEDER | D | C | 01 | A |  | 2024-03-30 | 2024-04-30 | 2024-06-30 | 2024-07-30 | 2024-03-14 |  | 2024-10-15 | 2024-12-13 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Typical Elementary | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2E87EA565D354D03B9120EF1A5247049
DDCL | CCP-W-B089-IA-301-0103 | TYPICAL ELEMENTARY WIRING DIAGRAM - 400V LV SWGR MOTOR FEEDER (BELOW 160 KW) | D | C | 01 | A |  | 2024-03-30 | 2024-04-30 | 2024-06-30 | 2024-07-30 | 2024-03-14 | 2024-09-13 | 2024-09-13 | 2024-12-13 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Typical Elementary | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D2D0EC9DA0B143F591D552C9A0A361A3
DDCL | CCP-W-B089-IA-301-0104 | TYPICAL ELEMENTARY WIRING DIAGRAM - FAST BUS TRANSFER SYSTEM | D | C | 01 | A |  | 2024-03-30 | 2024-04-30 | 2024-06-30 | 2024-07-30 | 2024-03-14 |  | 2024-10-15 | 2024-12-13 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Typical Elementary | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C80A587823C140ADB91EA3E4E5306C17
DDCL | CCP-W-B089-IA-301-0107 | TYPICAL ELEMENTARY WIRING DIAGRAM - MODULATING CONTROL VALVE | D | C | 01 | _ |  | 2024-03-30 | 2024-04-30 | 2024-06-30 | 2024-07-30 | 2024-03-14 | 2024-09-13 | 2024-09-13 | 2024-09-13 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Typical Elementary | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C63B830F96594CFCA2B79D06051E5AAB
DDCL | CCP-W-B089-IA-301-0100 | TYPICAL ELEMENTARY WIRING DIAGRAM - INDEX | D | C | 01 | _ |  | 2024-03-30 | 2024-04-30 | 2024-06-30 | 2024-07-30 | 2024-03-14 | 2024-09-13 | 2024-09-13 | 2024-09-13 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Typical Elementary | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7F79DB7ECB284BC9B1EF78A754208162
DDCL | CCP-W-B089-IA-301-0105 | TYPICAL ELEMENTARY WIRING DIAGRAM - MOTOR OPERATED VALVE | D | C | 01 | _ |  | 2024-03-30 | 2024-04-30 | 2024-06-30 | 2024-07-30 | 2024-03-14 | 2024-09-13 | 2024-09-13 | 2024-09-13 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Typical Elementary | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:870CB6600A2147F49B711D81421E41D2
DDCL | CCP-W-B089-IA-301-0106 | TYPICAL ELEMENTARY WIRING DIAGRAM - PNEUMATIC SHUT OFF VALVE | D | C | 01 | _ |  | 2024-03-30 | 2024-04-30 | 2024-06-30 | 2024-07-30 | 2024-03-14 | 2024-09-13 | 2024-09-13 | 2024-09-13 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Typical Elementary | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D48390D57C4543D099292AE3F785C545
DDCL | CCP-W-B089-IA-301-0108 | TYPICAL ELEMENTARY WIRING DIAGRAM - ANALOG INPUT | D | C | 01 | _ |  | 2024-03-30 | 2024-04-30 | 2024-06-30 | 2024-07-30 | 2024-03-14 | 2024-09-13 | 2024-09-13 | 2024-09-13 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Typical Elementary | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C6DA35D0CC794D3EA168F466088A64DF
DDCL | CCP-W-B089-IA-301-0109 | TYPICAL ELEMENTARY WIRING DIAGRAM - ANALOG OUTPUT | D | C | 01 | _ |  | 2024-03-30 | 2024-04-30 | 2024-06-30 | 2024-07-30 | 2024-03-14 | 2024-09-13 | 2024-09-13 | 2024-09-13 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Typical Elementary | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6E860AFB0BCD4A8AA41D2D2B338F05F5
DDCL | CCP-W-B089-IA-301-0110 | TYPICAL ELEMENTARY WIRING DIAGRAM - DIGITAL INPUT | D | C | 01 | _ |  | 2024-03-30 | 2024-04-30 | 2024-06-30 | 2024-07-30 | 2024-03-14 | 2024-09-13 | 2024-09-13 | 2024-09-13 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Typical Elementary | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F5D7BFAA8A5041F6BA1497B4398877B2
DDCL | CCP-W-B089-IA-301-0111 | TYPICAL ELEMENTARY WIRING DIAGRAM - DIGITAL OUTPUT | D | C | 01 | _ |  | 2024-03-30 | 2024-04-30 | 2024-06-30 | 2024-07-30 | 2024-03-14 | 2024-09-13 | 2024-09-13 | 2024-09-13 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Typical Elementary | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:BDB091398DEC4EE3A1AFCCA35787DB3B
DDCL | CCP-W-B000-IA-377-0003 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - INSTRUMENT RACK AND JUNCTION BOX | D | C | 01 | A |  | 2024-03-30 | 2024-04-30 | 2024-06-30 | 2024-07-30 | 2024-03-15 |  | 2024-08-30 | 2025-01-08 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Typical_C_Installation(TPP) | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6FF21A8A649A4D29BA84F826C2544FC9
DDCL | CCP-W-B000-IA-377-0004 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - FIELD INSTRUMENT | D | C | 01 | A |  | 2024-03-30 | 2024-04-30 | 2024-06-30 | 2024-07-30 | 2024-03-15 |  | 2024-08-30 | 2025-01-08 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Typical_C_Installation(TPP) | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:498EDF8B8A434C9FB326AA7B00A83E5C
DDCL | CCP-W-B000-IA-377-0005 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - CONDUIT SUPPORT | D | C | 01 | _ |  | 2024-03-30 | 2024-04-30 | 2024-06-30 | 2024-07-30 | 2024-03-15 |  | 2024-08-30 | 2024-09-03 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Typical_C_Installation(TPP) | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F258B7A7A9EB4CF79FD7D53160E0AE0C
DDCL | CCP-W-B000-IA-377-0001 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - CONTROL VALVE | D | C | 01 | _ |  | 2024-03-30 | 2024-04-30 | 2024-06-30 | 2024-07-30 | 2024-03-15 |  | 2024-08-30 | 2024-09-03 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Typical_C_Installation(TPP) | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1E545BB1B7A7462780A55164291EB992
DDCL | CCP-W-B000-IA-377-0002 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - MOV | D | C | 01 | _ |  | 2024-03-30 | 2024-04-30 | 2024-06-30 | 2024-07-30 | 2024-03-15 |  | 2024-08-30 | 2024-09-03 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Typical_C_Installation(TPP) | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:496116AE2E284E6EBEDC80AF8BB5E8A7
DDCL | CCP-W-B000-IA-353-0002 | I&C CABLE SCHEDULE FOR BOP (PACKAGE SYSTEM) | D | C | 01 | A |  | 2024-08-11 | 2024-09-11 | 2024-11-01 | 2024-12-01 | 2024-09-12 | 2024-09-13 | 2024-11-01 | 2025-02-18 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IWD & Schedule | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:34AB64A4C92E4536B0E3A5F04F7565F6
DDCL | CCP-W-B100-IA-353-0002 | I&C CABLE SCHEDULE FOR GTG | D | C | 01 | _ |  | 2024-08-11 | 2024-09-11 | 2024-11-01 | 2024-12-01 | 2024-09-12 | 2024-09-13 | 2024-11-29 | 2024-12-09 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IWD & Schedule | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6F3F13EFC86442ECBB6C92BDD8C90AA9
DDCL | CCP-W-B089-IA-308-0001 | INTERCONNECTION WIRING DIAGRAM (BOP) - MAIN & PROCESS STEAM SYSTEM | D | C | 01 | _ |  | 2024-11-10 | 2024-12-14 | 2025-03-11 | 2025-04-11 | 2024-11-08 | 2024-11-08 | 2025-03-17 | 2025-03-18 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IWD & Schedule | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:361F3617429E4AC3A79147154FADE2F9
DDCL | CCP-W-B089-IA-308-0002 | INTERCONNECTION WIRING DIAGRAM (BOP) - AUX STEAM SYSTEM | D | C | 01 | _ |  | 2024-11-10 | 2024-12-14 | 2025-03-11 | 2025-04-11 | 2024-07-19 | 2024-11-08 | 2025-03-17 | 2025-03-18 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IWD & Schedule | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:18E30F78CFE8412489BDF8F0A9408414
DDCL | CCP-W-B089-IA-308-0003 | INTERCONNECTION WIRING DIAGRAM (BOP) - CONDENSATE SYSTEM | D | C | 01 | _ |  | 2024-11-10 | 2024-12-14 | 2025-03-11 | 2025-04-11 | 2024-11-08 | 2024-11-08 | 2025-03-18 | 2025-03-18 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IWD & Schedule | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7E41181E8EC3420CB4C8C5025299EAD8
DDCL | CCP-W-B089-IA-308-0004 | INTERCONNECTION WIRING DIAGRAM (BOP) - AIR COOLED CONDENSER | D | C | 01 | _ |  | 2024-11-10 | 2024-12-14 | 2025-03-11 | 2025-04-11 | 2024-11-08 | 2024-11-08 | 2025-03-18 | 2025-03-18 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IWD & Schedule | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:DDA6B1452C994B51AEC620D5D6F4082D
DDCL | CCP-W-B089-IA-308-0005 | INTERCONNECTION WIRING DIAGRAM (BOP) - FEEDWATER SYSTEM | D | C | 01 | _ |  | 2024-11-10 | 2024-12-14 | 2025-03-11 | 2025-04-11 | 2024-11-08 | 2024-11-08 | 2025-03-18 | 2025-03-18 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IWD & Schedule | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:654C1211EE2747809BAA40C230E757E3
DDCL | CCP-W-B089-IA-308-0007 | INTERCONNECTION WIRING DIAGRAM (BOP) - FUEL OIL SYSTEM | D | C | 01 | _ |  | 2024-11-10 | 2024-12-14 | 2025-03-11 | 2025-04-11 | 2024-11-14 | 2024-11-14 | 2025-03-18 | 2025-03-18 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IWD & Schedule | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CC05BFB48A8C4777AE5AF667EA396064
DDCL | CCP-W-B089-IA-308-0008 | INTERCONNECTION WIRING DIAGRAM (BOP) - UTILITY SYSTEM | D | C | 01 | _ |  | 2024-11-10 | 2024-12-14 | 2025-03-11 | 2025-04-11 | 2024-11-14 | 2024-11-14 | 2025-03-18 | 2025-03-18 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IWD & Schedule | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:386A0CEE42A24FAB91AAD7D049FE4997
DDCL | CCP-W-B089-IA-308-0009 | INTERCONNECTION WIRING DIAGRAM (BOP) - CLOSED COOLING WATER SYSTEM | D | C | 01 | _ |  | 2024-11-10 | 2024-12-14 | 2025-03-11 | 2025-04-11 | 2024-11-14 | 2024-11-14 | 2025-03-18 | 2025-03-18 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IWD & Schedule | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A22B46DAF59741A485AE5C00AAFD0349
DDCL | CCP-W-B089-IA-308-0010 | INTERCONNECTION WIRING DIAGRAM (BOP) - STEAM AND WATER ANALYSIS SYSTEM | D | C | 01 | _ |  | 2024-11-10 | 2024-12-14 | 2025-03-11 | 2025-04-11 | 2024-11-14 | 2024-11-14 | 2025-03-17 | 2025-03-18 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IWD & Schedule | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:DFFB431A998E4E06817318A1647034CE
DDCL | CCP-W-B089-IA-308-0011 | INTERCONNECTION WIRING DIAGRAM (BOP) - CHEMICAL DOSING SYSTEM | D | C | 01 | _ |  | 2024-11-10 | 2024-12-14 | 2025-03-11 | 2025-04-11 | 2024-11-14 | 2024-11-14 | 2025-03-17 | 2025-03-18 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IWD & Schedule | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:507A37E06C27464886B419BE048BBF75
DDCL | CCP-W-B089-IA-308-0012 | INTERCONNECTION WIRING DIAGRAM (BOP) - ELECTRICAL SYSTEM | D | C | 01 | _ |  | 2024-11-10 | 2024-12-14 | 2025-03-11 | 2025-04-11 | 2024-11-14 | 2024-11-14 | 2025-04-15 | 2025-04-15 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IWD & Schedule | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A12BC66E31FF4BF397C97CAFFF7D5B1B
DDCL | CCP-W-B000-IA-353-0001 | I&C CABLE SCHEDULE FOR BOP (COMMON) | D | C | 01 | A |  | 2024-08-11 | 2024-09-11 | 2024-11-01 | 2024-12-01 | 2024-09-12 | 2024-09-13 | 2024-11-01 | 2025-02-18 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IWD & Schedule | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3E09E1ADEAA143AEA9C21AA88F31863C
DDCL | CCP-W-B089-IA-308-0013 | INTERCONNECTION WIRING DIAGRAM (BOP) - PACKAGE SYSTEM | D | C | 01 | _ |  | 2024-11-10 | 2024-12-14 | 2025-03-11 | 2025-04-11 | 2024-11-14 | 2024-11-14 | 2025-04-15 | 2025-04-15 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IWD & Schedule | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A18502BDCD7444DD91F4ACAFD4847537
DDCL | CCP-W-B100-IA-353-0001 | I&C CABLE SCHEDULE FOR BOP (BLOCK) | D | C | 01 | A |  | 2024-08-11 | 2024-09-11 | 2024-11-01 | 2024-12-01 | 2024-09-12 | 2024-09-13 | 2024-11-01 | 2025-02-18 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IWD & Schedule | I&C | 김용근 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:16FE6EF9462A49B8AE38E6E21A7FE6ED
DDCL | CCP-W-B089-IA-308-0006 | INTERCONNECTION WIRING DIAGRAM (BOP) - FUEL GAS SYSTEM | D | C | 01 | _ |  | 2024-11-10 | 2024-12-14 | 2025-03-11 | 2025-04-11 | 2024-11-14 | 2024-11-14 | 2025-03-18 | 2025-03-18 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_IWD & Schedule | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3D2D09C4E7EC477F86392869B349B403
DDCL | CCP-PW-B189-IA-301-0002 | PLANT OVERALL CONTROL SYSTEM CONFIGURATION (BLOCK) | D | D | 01 | B |  | 2023-07-12 | 2023-08-16 |  |  | 2024-02-23 | 2024-02-29 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Plant_Overall_Design | I&C | 오준호 | [10 empty] | CCP-EPC-TRM-PGU-0036 | D | 01 | 2023-10-04 | 2023-10-04 | 2023-10-18 | CCP-PGU-TRM-EPC-0036 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0036 | D | 01 | 2023-10-04 | 2023-10-04 | 2023-10-18 | CCP-PGU-TRM-EPC-0036 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:07FDA93A92C141BD8BB8F282858F18AA
DDCL | CCP-PW-B089-IA-301-0003 | PLANT OVERALL CONTROL SYSTEM CONFIGURATION (COMMON) | D | D | 01 | B |  | 2023-07-12 | 2023-08-16 |  |  | 2024-02-23 | 2024-02-29 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Plant_Overall_Design | I&C | 오준호 | [10 empty] | CCP-EPC-TRM-PGU-0036 | D | 01 | 2023-10-04 | 2023-10-04 | 2023-10-18 | CCP-PGU-TRM-EPC-0036 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0036 | D | 01 | 2023-10-04 | 2023-10-04 | 2023-10-18 | CCP-PGU-TRM-EPC-0036 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D69EAF8B3FF94C91A308CABF8252A2A9
DDCL | CCP-PW-B089-IA-301-0001 | DESIGN CRITERIA - I&C | D | D | 01 | _ | FC DELAY | 2024-03-30 | 2024-04-30 | 2024-06-30 | 2024-07-30 | 2024-03-04 |  |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Plant_Overall_Design | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FA4EDDBF96264B96A1C4863EEA21022F
DDCL | CCP-W-B089-IA-301-0004 | DCS POWER DISTRIBUTION CONCEPT DIAGRAM | D | C | 01 | _ |  | 2024-03-20 | 2024-04-20 | 2024-06-20 | 2024-07-20 | 2024-03-12 |  | 2024-10-11 | 2024-10-11 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Plant_Overall_Design | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:43FD77D0A60649D380E9568B9939731A
DDCL | CCP-W-B089-IA-301-0005 | I&C GROUNDING CONCEPT DIAGRAM | D | C | 01 | _ |  | 2024-03-20 | 2024-04-20 | 2024-06-20 | 2024-07-20 | 2024-03-12 |  | 2024-10-07 | 2024-10-07 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Plant_Overall_Design | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B253FE3CF6EE4182868DA4042898781E
DDCL | CCP-PW-B089-IA-301-0006 | PLANT PROTECTION & INTERLOCK DIAGRAM | D | C | 01 | _ |  | 2024-04-10 | 2024-05-10 | 2024-07-10 | 2024-08-10 | 2024-03-04 | 2024-10-07 | 2024-12-09 | 2024-12-09 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Plant_Overall_Design | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C501B7B542304FA3A3A09F914CC23774
DDCL | CCP-PW-B089-IA-301-0008 | I&C CABLE PRINCIPLE DIAGRAM | R | C | 01 | _ |  | 2024-03-30 | 2024-04-30 | 2024-06-30 | 2024-07-30 | 2024-03-04 | 2023-09-26 | 2024-10-11 | 2024-10-11 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Design_Criteria_Cable | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4D81D0EFE44D4CB09AA5357B4BCF642B
DDCL | CCP-W-B089-IA-301-0007 | PLANT CONTROL & MONITORING CONCEPT BLOCK DIAGRAM | D | C | 01 | _ |  | 2024-03-20 | 2024-04-20 | 2024-06-20 | 2024-07-20 | 2024-03-15 |  | 2024-09-06 | 2024-09-13 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Plant_Overall_Design | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:97274600C43644A6B3E7FA33D889885B
DDCL | CCP-W-B112-IA-329-0001 | I&C CABLE RACEWAY DRAWING FOR BOP - GAS TURBINE 2 AREA | D | C | 01 | A |  | 2024-03-15 | 2024-04-15 | 2024-09-15 | 2024-10-15 | 2024-03-13 | 2024-07-03 | 2024-10-08 | 2025-06-17 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Cable Raceway | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D81E8AFCDFC448ACA93E8D0648CB22F3
DDCL | CCP-W-B211-IA-329-0001 | I&C CABLE RACEWAY DRAWING FOR BOP - GAS TURBINE 3 AREA | D | C | 01 | A |  | 2024-03-15 | 2024-04-15 | 2024-09-15 | 2024-10-15 | 2024-03-13 | 2024-07-03 | 2024-10-08 | 2025-06-17 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Cable Raceway | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5F47D2435E0C44D99190DE0B2789FBC9
DDCL | CCP-W-B212-IA-329-0001 | I&C CABLE RACEWAY DRAWING FOR BOP - GAS TURBINE 4 AREA | D | C | 01 | A |  | 2024-03-15 | 2024-04-15 | 2024-09-15 | 2024-10-15 | 2024-03-13 | 2024-07-03 | 2024-10-08 | 2025-06-17 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Cable Raceway | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B915EB2C088542558579A442E41A3C1C
DDCL | CCP-W-B044-IA-329-0001 | I&C CABLE RACEWAY DRAWING FOR BOP - FUEL GAS SUPPLY AREA | D | C | 01 | A |  | 2024-03-15 | 2024-04-15 | 2024-09-15 | 2024-10-15 | 2024-03-19 | 2024-10-08 | 2024-10-08 | 2025-04-11 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Cable Raceway | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:0A2718E9A89C4183BFD2EC6806ED848F
DDCL | CCP-W-B046-IA-329-0001 | I&C CABLE RACEWAY DRAWING FOR BOP - FUEL OIL AREA | D | C | 01 | A |  | 2024-03-15 | 2024-04-15 | 2024-09-15 | 2024-10-15 | 2024-03-13 | 2024-10-08 | 2024-10-08 | 2025-04-11 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Cable Raceway | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1A437A0DCD8B48C4BF95CF5388D6E372
DDCL | CCP-W-B116-IA-329-0001 | I&C CABLE RACEWAY DRAWING FOR BOP - AIR COOLED CONDENSER 1 AREA | D | C | 01 | A |  | 2024-03-15 | 2024-04-15 | 2024-09-15 | 2024-10-15 | 2024-03-13 | 2024-10-08 | 2024-10-08 | 2025-04-11 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Cable Raceway | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:BE234EC9D76F48BB8A45D33F953B1434
DDCL | CCP-W-B216-IA-329-0001 | I&C CABLE RACEWAY DRAWING FOR BOP - AIR COOLED CONDENSER 2 AREA | D | C | 01 | A |  | 2024-03-15 | 2024-04-15 | 2024-09-15 | 2024-10-15 | 2024-03-13 | 2024-10-08 | 2024-10-08 | 2025-04-11 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Cable Raceway | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B579CBF9C29F48E0B1926A9CBE5AFB14
DDCL | CCP-W-B000-IA-329-0003 | I&C CABLE RACEWAY DRAWING FOR BOP - MISCELLANEOUS AREA | D | C | 01 | A |  | 2024-03-15 | 2024-04-15 | 2024-09-15 | 2024-10-15 | 2024-03-13 | 2024-10-08 | 2024-10-08 | 2025-04-18 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Cable Raceway | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6A640E68493F47B4BD15DDF46FE06D76
DDCL | CCP-W-B017-IA-329-0003 | I&C CABLE RACEWAY DRAWING FOR BOP - TRANSFORMER AREA | D | C | 01 | _ |  | 2024-03-15 | 2024-04-15 | 2024-09-15 | 2024-10-15 | 2024-03-13 | 2024-10-08 | 2024-10-08 | 2024-10-08 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Cable Raceway | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D69460164DC444999BE7F98498C46A7C
DDCL | CCP-W-B000-IA-329-0001 | I&C CABLE RACEWAY DRAWING FOR BOP - SYMBOL & LEGEND | D | C | 01 | _ |  | 2024-03-15 | 2024-04-15 | 2024-09-15 | 2024-10-15 | 2024-03-13 | 2024-10-08 | 2024-10-08 | 2024-10-08 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Cable Raceway | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:10A2BD29379B48CEA7DE56807E514A9F
DDCL | CCP-W-B000-IA-329-0002 | I&C CABLE RACEWAY DRAWING FOR BOP - CONDUIT DETAIL DRAWINGS | D | C | 01 | _ |  | 2024-03-15 | 2024-04-15 | 2024-09-15 | 2024-10-15 | 2024-03-13 | 2024-10-08 | 2024-10-08 | 2024-10-08 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Cable Raceway | I&C | 오준호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:AC4E3ADF160540B5A4DD6EDE4FB384F6
DDCL | CCP-W-B114-IA-329-0001 | I&C CABLE RACEWAY DRAWING FOR BOP - HRSG 1 AREA | D | C | 01 | A |  | 2024-03-15 | 2024-04-15 | 2024-09-15 | 2024-10-15 | 2024-03-13 | 2024-07-03 | 2024-10-08 | 2025-05-16 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Cable Raceway | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E479F24B09464317A0BB32233F645E5C
DDCL | CCP-W-B115-IA-329-0001 | I&C CABLE RACEWAY DRAWING FOR BOP - HRSG 2 AREA | D | C | 01 | A |  | 2024-03-15 | 2024-04-15 | 2024-09-15 | 2024-10-15 | 2024-03-13 | 2024-07-03 | 2024-10-08 | 2025-05-16 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Cable Raceway | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8AB1B4FDDDA94ED8B41C4F190832DB8F
DDCL | CCP-W-B214-IA-329-0001 | I&C CABLE RACEWAY DRAWING FOR BOP - HRSG 3 AREA | D | C | 01 | A |  | 2024-03-15 | 2024-04-15 | 2024-09-15 | 2024-10-15 | 2024-03-13 | 2024-07-03 | 2024-10-08 | 2025-05-16 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Cable Raceway | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3079CFE37FC9446D8B3BC8AEC709F6FF
DDCL | CCP-W-B215-IA-329-0001 | I&C CABLE RACEWAY DRAWING FOR BOP - HRSG 4 AREA | D | C | 01 | A |  | 2024-03-15 | 2024-04-15 | 2024-09-15 | 2024-10-15 | 2024-03-13 | 2024-07-03 | 2024-10-08 | 2025-05-16 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Cable Raceway | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F5B98640378541F58617D59902043BA6
DDCL | CCP-W-B113-IA-329-0001 | I&C CABLE RACEWAY DRAWING FOR BOP - STEAM TURBINE 1 AREA | D | C | 01 | A |  | 2024-03-15 | 2024-04-15 | 2024-09-15 | 2024-10-15 | 2024-03-13 | 2024-07-03 | 2024-10-08 | 2025-06-17 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Cable Raceway | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1005DC9A0C354FCDB19570F0525B3154
DDCL | CCP-W-B213-IA-329-0001 | I&C CABLE RACEWAY DRAWING FOR BOP - STEAM TURBINE 2 AREA | D | C | 01 | A |  | 2024-03-15 | 2024-04-15 | 2024-09-15 | 2024-10-15 | 2024-03-13 | 2024-07-03 | 2024-10-08 | 2025-06-17 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Cable Raceway | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6130D5E3077F45349B7D41212345D720
DDCL | CCP-W-B111-IA-329-0001 | I&C CABLE RACEWAY DRAWING FOR BOP - GAS TURBINE 1 AREA | D | C | 01 | A |  | 2024-03-15 | 2024-04-15 | 2024-09-15 | 2024-10-15 | 2024-03-13 | 2024-07-03 | 2024-10-08 | 2025-06-17 | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Cable Raceway | I&C | 최성호 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:48DEAA86DA194AB7A68DE626F2EBE37D
DDCL | CCP-PW-B062-IA-319-0001 | I&C EQUIPMENT LAYOUT DRAWING - CENTRAL CONTROL ROOM | D | D | 01 | _ |  | 2023-12-24 | 2024-01-28 | 2024-06-24 | 2024-07-29 |  | 2023-09-26 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Equipment Layout | I&C | 김용근 | [10 empty] | CCP-EPC-TRM-PGU-0027 | D | 01 | 2023-09-26 | 2023-09-26 | 2023-10-16 | CCP-PGU-TRM-EPC-0027 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0027 | D | 01 | 2023-09-26 | 2023-09-26 | 2023-10-16 | CCP-PGU-TRM-EPC-0027 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1CA4F1CF18B84034B340FAB65FA5945E
DDCL | CCP-PW-B062-IA-319-0002 | I&C EQUIPMENT LAYOUT DRAWING - CENTRAL ELECTRONIC ROOM | D | D | 01 | _ |  | 2024-02-15 | 2024-03-15 | 2024-05-15 | 2024-06-15 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Equipment Layout | I&C | 김용근 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A788FFD0DEB445D4BE8536CA836F9B68
DDCL | CCP-PW-B164-IA-319-0001 | I&C EQUIPMENT LAYOUT DRAWING - LOCAL ELECTRONIC ROOM FOR BLOCK 1 | D | D | 01 | _ |  | 2024-02-15 | 2024-03-15 | 2024-05-15 | 2024-06-15 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Equipment Layout | I&C | 김용근 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5B48C235B88748A388FD3C6742F7088A
DDCL | CCP-PW-B264-IA-319-0001 | I&C EQUIPMENT LAYOUT DRAWING - LOCAL ELECTRONIC ROOM FOR BLOCK 2 | D | D | 01 | _ |  | 2024-02-15 | 2024-03-15 | 2024-05-15 | 2024-06-15 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Equipment Layout | I&C | 김용근 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:189EAF8D54F84694BC92F94619780821
DDCL | CCP-PW-B113-IA-319-0001 | I&C EQUIPMENT LAYOUT DRAWING - LOCAL ELECTRONIC ROOM FOR STG 1 | D | D | 01 | _ |  | 2024-02-15 | 2024-03-15 | 2024-05-15 | 2024-06-15 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Equipment Layout | I&C | 김용근 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:09D03848A2E44D32BC2D3A95D3095037
DDCL | CCP-PW-B213-IA-319-0001 | I&C EQUIPMENT LAYOUT DRAWING - LOCAL ELECTRONIC ROOM FOR STG 2 | D | D | 01 | _ |  | 2024-02-15 | 2024-03-15 | 2024-05-15 | 2024-06-15 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Equipment Layout | I&C | 김용근 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B5DE561F273D4A0287F5D12D2E95DF17
DDCL | CCP-PW-B169-IA-319-0001 | I&C EQUIPMENT LAYOUT DRAWING - LOCAL ELECTRONIC ROOM FOR ACC 1 | D | D | 01 | _ |  | 2024-02-15 | 2024-03-15 | 2024-05-15 | 2024-06-15 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Equipment Layout | I&C | 김용근 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:87D1DE757F3D4F939D954B56C471DB99
DDCL | CCP-PW-B269-IA-319-0001 | I&C EQUIPMENT LAYOUT DRAWING - LOCAK ELECTRONIC ROOM FOR ACC 2 | D | D | 01 | _ |  | 2024-02-15 | 2024-03-15 | 2024-05-15 | 2024-06-15 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Equipment Layout | I&C | 김용근 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7BB9644E52B3408D8C8D16405FE1D94A
DDCL | CCP-PW-B083-IA-319-0001 | I&C EQUIPMENT LAYOUT DRAWING - LOCAL ELECTRONIC ROOM FOR WTP | D | D | 01 | _ |  | 2024-02-15 | 2024-03-15 | 2024-05-15 | 2024-06-15 |  | 2024-02-06 |  |  | BOP Plant | Plant EPC)제어/계측기술1팀 | I&C_Equipment Layout | I&C | 김용근 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2B5561DCCCF74E49821C758E02B371E3
DDCL | CCP-W-B116-04-ME-B16-0002 | Air Cooled Condenser_Performance Curve | D | C | 01 | _ |  | 2024-01-01 | 2024-02-12 | 2024-03-31 | 2024-05-12 | 2024-03-06 | 2024-06-17 | 2024-07-19 | 2024-07-19 | BOP Plant | Plant EPC)주기기기술팀 | Air Cooler Condenser | Mechanical | 김규진 | [10 empty] | CCP-EPC-TRM-PGU-0291 | C | 01 | 2024-07-19 |  | 2024-06-29 | CCP-PGU-TRM-EPC-0198 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0198 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0198 | Deemed Approved | CCP-EPC-TRM-PGU-0291 | C | 01 | 2024-07-19 | [84 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:BDCD93BEA0AA4A03881670DCF083F7AC
DDCL | CCP-W-B116-04-ME-H03-0001 | Air Cooled Condenser_Wiring Diagram | D | C | 01 | A |  | 2024-03-01 | 2024-04-12 | 2024-05-30 | 2024-07-11 | 2024-03-21 | 2024-06-17 | 2024-07-19 | 2025-05-23 | BOP Plant | Plant EPC)주기기기술팀 | Air Cooler Condenser | Mechanical | 김규진 | [10 empty] | CCP-EPC-TRM-PGU-0291 | C | 01 | 2024-07-19 |  | 2024-06-29 | CCP-PGU-TRM-EPC-0198 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0198 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0198 | Deemed Approved | CCP-EPC-TRM-PGU-0291 | C | 01 | 2024-07-19 | [84 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B507619253C84FB8AAE2A4131FC10BC8
DDCL | CCP-W-B116-04-ME-H05-0001 | Air Cooled Condenser_Junction Box Outline and Layout Drawing | D | D | 01 | _ |  | 2024-06-04 | 2024-07-16 | 2024-09-02 | 2024-10-14 | 2024-07-15 | 2024-07-16 |  |  | BOP Plant | Plant EPC)주기기기술팀 | Air Cooler Condenser | Mechanical | 김규진 | [10 empty] | CCP-EPC-TRM-PGU-0266 | D | 01 | 2024-07-16 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0266 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0266 | D | 01 | 2024-07-16 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0266 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D359D9EB9F4A45D296975F2F0C0A54AD
DDCL | CCP-W-B116-04-ME-E04-0001 | Air Cooled Condenser_Lighting & Small Power Layout and Specification | D | C | 01 | A |  | 2024-04-30 | 2024-06-11 | 2024-07-29 | 2024-09-09 | 2024-06-28 | 2024-06-28 | 2024-08-23 | 2024-10-28 | BOP Plant | Plant EPC)주기기기술팀 | Air Cooler Condenser | Mechanical | 김규진 | [10 empty] | CCP-EPC-TRM-PGU-0405 | C | 01 | 2024-08-26 |  | 2024-07-12 | CCP-PGU-TRM-EPC-0232 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0232 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0232 | Deemed Approved | CCP-EPC-TRM-PGU-0405 | C | 01 | 2024-08-26 | [84 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:29DE691D3EB74829B8CFF686D5E5FADB
DDCL | CCP-W-B116-04-ME-E04-0002 | Air Cooled Condenser_Cable Raceway Drawing | D | C | 01 | A |  | 2024-03-31 | 2024-05-12 | 2024-06-29 | 2024-08-10 | 2024-07-18 | 2024-07-18 | 2024-08-23 | 2024-10-28 | BOP Plant | Plant EPC)주기기기술팀 | Air Cooler Condenser | Mechanical | 김규진 | [10 empty] | CCP-EPC-TRM-PGU-0405 | C | 01 | 2024-08-26 |  | 2024-07-29 | CCP-PGU-TRM-EPC-0288 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0288 | D | 01 | 2024-07-18 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0288 | Deemed Approved | CCP-EPC-TRM-PGU-0405 | C | 01 | 2024-08-26 | [84 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:51039E75A9E54E4F90CDCA972F91EA9A
DDCL | CCP-W-B116-04-ME-B16-0010 | Air Cooled Condenser_Steel Structure Drawing | D | D | 01 | _ |  | 2024-06-27 | 2024-07-11 | 2024-10-02 | 2024-10-09 | 2024-05-24 | 2024-06-17 |  |  | BOP Plant | Plant EPC)주기기기술팀 | Air Cooler Condenser | Mechanical | 김규진 | [10 empty] | CCP-EPC-TRM-PGU-0198 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0198 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0198 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0198 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D73EC36ADA5D4E0C95D610F75015057F
DDCL | CCP-W-B116-04-ME-E04-0003 | Air Cooled Condenser_Elec. Heat tracing Layout and Specification | D | C | 01 | A |  | 2024-05-11 | 2024-06-11 | 2024-08-09 | 2024-09-09 | 2024-06-21 | 2024-06-21 | 2024-08-23 | 2024-10-28 | BOP Plant | Plant EPC)주기기기술팀 | Air Cooler Condenser | Mechanical | 김규진 | [10 empty] | CCP-EPC-TRM-PGU-0405 | C | 01 | 2024-08-26 |  | 2024-07-05 | CCP-PGU-TRM-EPC-0216 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0216 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0216 | Deemed Approved | CCP-EPC-TRM-PGU-0405 | C | 01 | 2024-08-26 | [84 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:83E0A283E06F43678692FE0E7813A8EA
DDCL | CCP-W-B116-04-ME-P10-0001 | Air Cooled Condenser_Valve Datasheet | D | D | 01 | _ |  | 2024-03-21 | 2024-05-02 | 2024-06-19 | 2024-07-31 | 2025-01-20 | 2025-01-20 |  |  | BOP Plant | Plant EPC)주기기기술팀 | Air Cooler Condenser | Mechanical | 김규진 | [10 empty] | CCP-EPC-TRM-PGU-0841 | D | 01 | 2025-01-20 | 2025-01-20 | 2025-01-30 | CCP-PGU-TRM-EPC-0841 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0841 | D | 01 | 2025-01-20 | 2025-01-20 | 2025-01-30 | CCP-PGU-TRM-EPC-0841 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:58538C3B508042EF831F3F72BB978F4C
DDCL | CCP-W-B116-04-ME-B16-0003 | Air Cooled Condenser_Fan Technical Specification | D | C | 01 | A |  | 2024-03-21 | 2024-05-02 | 2024-06-19 | 2024-07-31 | 2024-06-25 | 2024-06-25 | 2024-07-19 | 2024-10-28 | BOP Plant | Plant EPC)주기기기술팀 | Air Cooler Condenser | Mechanical | 김규진 | [10 empty] | CCP-EPC-TRM-PGU-0291 | C | 01 | 2024-07-19 |  | 2024-07-07 | CCP-PGU-TRM-EPC-0221 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0221 | D | 01 | 2024-06-25 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0221 | Deemed Approved | CCP-EPC-TRM-PGU-0291 | C | 01 | 2024-07-19 | [84 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C7E75260E20C45BCA1E033E3F7A0838E
DDCL | CCP-W-B116-04-ME-E24-0001 | Air Cooled Condenser_Fan Motor Technical Specification | D | C | 01 | A |  | 2024-03-21 | 2024-05-02 | 2024-06-19 | 2024-07-31 | 2024-05-27 | 2024-06-17 | 2024-07-19 | 2024-10-28 | BOP Plant | Plant EPC)주기기기술팀 | Air Cooler Condenser | Mechanical | 김규진 | [10 empty] | CCP-EPC-TRM-PGU-0291 | C | 01 | 2024-07-19 |  | 2024-06-29 | CCP-PGU-TRM-EPC-0198 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0198 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0198 | Deemed Approved | CCP-EPC-TRM-PGU-0291 | C | 01 | 2024-07-19 | [84 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:95709F2A26444AD9AF6FB16A45C635EE
DDCL | CCP-W-B116-04-ME-B16-0004 | Air Cooled Condenser_Fan Gearbox Technical Specification | D | C | 01 | A |  | 2024-03-21 | 2024-05-02 | 2024-06-19 | 2024-07-31 | 2024-06-25 | 2024-06-25 | 2024-07-19 | 2024-10-28 | BOP Plant | Plant EPC)주기기기술팀 | Air Cooler Condenser | Mechanical | 김규진 | [10 empty] | CCP-EPC-TRM-PGU-0291 | C | 01 | 2024-07-19 |  | 2024-07-07 | CCP-PGU-TRM-EPC-0221 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0221 | D | 01 | 2024-06-25 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0221 | Deemed Approved | CCP-EPC-TRM-PGU-0291 | C | 01 | 2024-07-19 | [84 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C2A8232DCFFC40009522ECF6723F5D83
DDCL | CCP-W-B116-04-ME-B16-0005 | Air Cooled Condenser_Vacuum Pump & Motor Technical Specification | D | C | 01 | A |  | 2024-04-21 | 2024-06-02 | 2024-07-20 | 2024-08-31 | 2024-06-28 | 2024-06-28 | 2024-08-23 | 2024-10-28 | BOP Plant | Plant EPC)주기기기술팀 | Air Cooler Condenser | Mechanical | 김규진 | [10 empty] | CCP-EPC-TRM-PGU-0405 | C | 01 | 2024-08-26 |  | 2024-07-12 | CCP-PGU-TRM-EPC-0231 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0231 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0231 | Deemed Approved | CCP-EPC-TRM-PGU-0405 | C | 01 | 2024-08-26 | [84 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E418AA2F02254BC084DDF447AA393B35
DDCL | CCP-W-B116-04-ME-B16-0006 | Air Cooled Condenser_Condensate Drain Pump & Motor Technical Specification | D | C | 01 | _ |  | 2024-04-21 | 2024-06-02 | 2024-07-20 | 2024-08-31 | 2024-07-18 | 2024-07-18 | 2024-08-23 | 2024-08-26 | BOP Plant | Plant EPC)주기기기술팀 | Air Cooler Condenser | Mechanical | 김규진 | [10 empty] | CCP-EPC-TRM-PGU-0405 | C | 01 | 2024-08-26 |  | 2024-07-29 | CCP-PGU-TRM-EPC-0288 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0288 | D | 01 | 2024-07-18 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0288 | Deemed Approved | CCP-EPC-TRM-PGU-0405 | C | 01 | 2024-08-26 | [84 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CE3783399D374E6EAC8760F0FDB877DC
DDCL | CCP-W-B116-04-ME-B16-0007 | Air Cooled Condenser_Cleaning Water Pump & Motor Technical Specification | D | C | 01 | A |  | 2024-04-21 | 2024-06-02 | 2024-07-20 | 2024-08-31 | 2024-07-18 | 2024-07-18 | 2024-08-23 | 2024-10-28 | BOP Plant | Plant EPC)주기기기술팀 | Air Cooler Condenser | Mechanical | 김규진 | [10 empty] | CCP-EPC-TRM-PGU-0405 | C | 01 | 2024-08-26 |  | 2024-07-29 | CCP-PGU-TRM-EPC-0288 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0288 | D | 01 | 2024-07-18 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0288 | Deemed Approved | CCP-EPC-TRM-PGU-0405 | C | 01 | 2024-08-26 | [84 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:DDD10ECEC8F54513BC470F3593B60710
DDCL | CCP-W-B116-04-ME-B16-0008 | Air Cooled Condenser_Condensate Collecting Tank Outline Drawing | D | C | 01 | A |  | 2024-03-21 | 2024-05-02 | 2024-06-19 | 2024-07-31 | 2024-04-30 | 2024-06-18 | 2024-07-19 | 2024-10-28 | BOP Plant | Plant EPC)주기기기술팀 | Air Cooler Condenser | Mechanical | 김규진 | [10 empty] | CCP-EPC-TRM-PGU-0291 | C | 01 | 2024-07-19 |  | 2024-06-30 | CCP-PGU-TRM-EPC-0204 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0204 | D | 01 | 2024-06-18 | 2024-06-20 | 2024-06-30 | CCP-PGU-TRM-EPC-0204 | Deemed Approved | CCP-EPC-TRM-PGU-0291 | C | 01 | 2024-07-19 | [84 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:792D220577844C66B8DAE2E0EBEE77DE
DDCL | CCP-W-B116-04-ME-B16-0009 | Air Cooled Condenser_Electrical Lifting Hoist Technical Specification | D | D | 01 | _ | FA&FC DELAY | 2024-04-21 | 2024-06-02 | 2024-07-20 | 2024-08-31 |  |  |  |  | BOP Plant | Plant EPC)주기기기술팀 | Air Cooler Condenser | Mechanical | 김규진 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E946DBBBF7E94E3FA822BE3F848041B0
DDCL | CCP-W-B116-04-ME-P16-0001 | Air Cooled Condenser_Piping Arrangement Drawing | D | C | 01 | _ |  | 2024-03-01 | 2024-04-12 | 2024-05-30 | 2024-07-11 | 2024-05-27 | 2024-06-17 | 2024-07-19 | 2024-07-19 | BOP Plant | Plant EPC)주기기기술팀 | Air Cooler Condenser | Mechanical | 김규진 | [10 empty] | CCP-EPC-TRM-PGU-0291 | C | 01 | 2024-07-19 |  | 2024-06-29 | CCP-PGU-TRM-EPC-0198 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0198 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0198 | Deemed Approved | CCP-EPC-TRM-PGU-0291 | C | 01 | 2024-07-19 | [84 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1B23CFB8EBB84554AA9B18A9DED1ABCC
DDCL | CCP-W-B116-04-ME-P01-0001 | Air Cooled Condenser_Piping Isometric Drawring | D | D | 01 | _ |  | 2024-05-30 | 2024-07-11 | 2024-08-28 | 2024-10-09 | 2024-07-10 | 2024-07-10 |  |  | BOP Plant | Plant EPC)주기기기술팀 | Air Cooler Condenser | Mechanical | 김규진 | [10 empty] | CCP-EPC-TRM-PGU-0253E | D | 01 | 2024-07-10 | 2024-07-11 | 2024-07-21 | CCP-PGU-TRM-EPC-0253E | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0253E | D | 01 | 2024-07-10 | 2024-07-11 | 2024-07-21 | CCP-PGU-TRM-EPC-0253E | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D10CCF52FAE94D73993D931E97A6D4F5
DDCL | CCP-W-B116-04-ME-K11-0001 | Air Cooled Condenser_Control Logic Diagram | D | C | 01 | B |  | 2024-03-01 | 2024-04-12 | 2024-05-30 | 2024-07-11 | 2024-07-10 | 2024-07-10 | 2024-09-03 | 2025-05-27 | BOP Plant | Plant EPC)주기기기술팀 | Air Cooler Condenser | Mechanical | 김규진 | [10 empty] | CCP-EPC-TRM-PGU-0448 | C | 01 | 2024-09-03 |  | 2024-07-22 | CCP-PGU-TRM-EPC-0254 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0254 | D | 01 | 2024-07-10 | 2024-07-12 | 2024-07-22 | CCP-PGU-TRM-EPC-0254 | Deemed Approved | CCP-EPC-TRM-PGU-0448 | C | 01 | 2024-09-03 | [84 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:13C82E13CC0540C69951FAE9C0096C3E
DDCL | CCP-W-B116-04-ME-H21-0001 | Air Cooled Condenser_Instrument Datasheet | D | C | 01 | _ |  | 2024-03-01 | 2024-04-12 | 2024-05-30 | 2024-07-11 | 2024-07-18 | 2024-07-18 | 2024-08-23 | 2024-08-26 | BOP Plant | Plant EPC)주기기기술팀 | Air Cooler Condenser | Mechanical | 김규진 | [10 empty] | CCP-EPC-TRM-PGU-0405 | C | 01 | 2024-08-26 |  | 2024-07-29 | CCP-PGU-TRM-EPC-0288 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0288 | D | 01 | 2024-07-18 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0288 | Deemed Approved | CCP-EPC-TRM-PGU-0405 | C | 01 | 2024-08-26 | [84 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B3CDAD765A9D4184993CE11CEA07FD74
DDCL | CCP-W-B116-04-ME-H04-0001 | Air Cooled Condenser_Instrument Installation Detail Drawing | D | C | 01 | _ |  | 2024-03-01 | 2024-04-12 | 2024-05-30 | 2024-07-11 | 2024-04-22 | 2024-06-17 | 2024-07-19 | 2024-07-19 | BOP Plant | Plant EPC)주기기기술팀 | Air Cooler Condenser | Mechanical | 김규진 | [10 empty] | CCP-EPC-TRM-PGU-0291 | C | 01 | 2024-07-19 |  | 2024-06-29 | CCP-PGU-TRM-EPC-0198 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0198 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0198 | Deemed Approved | CCP-EPC-TRM-PGU-0291 | C | 01 | 2024-07-19 | [84 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:BAAF0F207493468589872B352D84D84D
DDCL | CCP-W-B116-04-ME-K06-0001 | Air Cooled Condenser_Functional Description | D | C | 01 | B |  | 2024-01-01 | 2024-02-12 | 2024-03-31 | 2024-05-12 | 2024-03-07 | 2024-06-17 | 2024-07-19 | 2025-05-19 | BOP Plant | Plant EPC)주기기기술팀 | Air Cooler Condenser | Mechanical | 김규진 | [10 empty] | CCP-EPC-TRM-PGU-0291 | C | 01 | 2024-07-19 |  | 2024-06-29 | CCP-PGU-TRM-EPC-0198 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0198 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0198 | Deemed Approved | CCP-EPC-TRM-PGU-0291 | C | 01 | 2024-07-19 | [84 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:766F1BA4FCAF48FFA3F65BC4404D374D
DDCL | CCP-W-B116-04-ME-B16-0001 | Air Cooled Condenser_P&I Diagram | D | C | 01 | B |  | 2024-01-16 | 2024-02-27 | 2024-04-15 | 2024-05-27 | 2024-03-04 | 2024-03-05 | 2024-06-20 | 2025-05-19 | BOP Plant | Plant EPC)주기기기술팀 | Air Cooler Condenser | Mechanical | 김규진 | [10 empty] | CCP-EPC-TRM-PGU-0208 | C | 01 | 2024-06-20 | 2024-06-21 | 2024-03-18 | CCP-PGU-EPC-TRM-0100 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0100 | D | 01 | 2024-03-05 | 2024-03-05 | 2024-03-18 | CCP-PGU-EPC-TRM-0100 | Approved With Comment | CCP-EPC-TRM-PGU-0208 | C | 01 | 2024-06-20 | 2024-06-21 | [83 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:EDED13B506B4402A82272BA237A396F3
DDCL | CCP-W-B116-04-ME-B01-0001 | Air Cooled Condenser_General Arrangement | D | C | 01 | A |  | 2023-12-02 | 2024-01-13 | 2024-03-01 | 2024-04-12 | 2024-03-21 | 2024-06-21 | 2024-07-19 | 2024-10-28 | BOP Plant | Plant EPC)주기기기술팀 | Air Cooler Condenser | Mechanical | 김규진 | [10 empty] | CCP-EPC-TRM-PGU-0291 | C | 01 | 2024-07-19 |  | 2024-07-04 | CCP-PGU-TRM-EPC-0212 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0212 | D | 01 | 2024-06-21 | 2024-06-24 | 2024-07-04 | CCP-PGU-TRM-EPC-0212 | Deemed Approved | CCP-EPC-TRM-PGU-0291 | C | 01 | 2024-07-19 | [84 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C00FA3006B2B4895972A9F34B2774DE8
DDCL | CCP-W-B000-19-ME-B01-0001 | Outline Drawing_Shop Tank (Including Name Plate Drawing) | D | C | 01 | A |  | 2024-02-26 | 2024-03-08 | 2024-05-26 | 2024-06-07 | 2024-05-21 | 2025-01-20 | 2025-01-20 | 2025-05-14 | BOP Plant | Plant EPC)프로세스기술1팀 | Shop Tank | Mechanical | 김정민 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A9BF555288174B5798E23F7B3070F9B7
DDCL | CCP-W-B043-10-ME-A07-0001 | BSEDG_Operation Philosophy | D | D | 01 | A |  | 2024-10-25 | 2024-12-31 | 2025-01-01 | 2025-02-28 | 2025-01-08 | 2025-01-13 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | BSEDG | Mechanical | 박재현 | [10 empty] | CCP-EPC-TRM-PGU-0839 | D | 01 | 2025-01-13 | 2025-01-16 | 2025-01-26 | CCP-EPC-TRM-PGU-0839 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0839 | D | 01 | 2025-01-13 | 2025-01-16 | 2025-01-26 | CCP-EPC-TRM-PGU-0839 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5616DB01742848B1BD81ADDE392EB2B9
DDCL | CCP-W-B043-10-ME-B06-0001 | P&ID_ Black Start Emergency Diesel Generator | D | D | 01 | _ |  | 2023-12-08 | 2024-01-07 | 2024-03-26 | 2024-05-07 | 2024-03-06 | 2024-07-15 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | BSEDG | Mechanical | 박재현 | [10 empty] | CCP-EPC-TRM-PGU-0263 | D | 01 | 2024-07-15 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0263 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0263 | D | 01 | 2024-07-15 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0263 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4539C2C2A0054CAE89F1FF44745EA400
DDCL | CCP-W-B043-10-ME-B01-0001 | General Arrangement Drawing_Black Start Emergency Diesel Generator | D | D | 01 | _ |  | 2023-12-08 | 2024-01-07 | 2024-03-26 | 2024-05-07 | 2024-01-03 | 2024-07-15 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | BSEDG | Mechanical | 박재현 | [10 empty] | CCP-EPC-TRM-PGU-0263 | D | 01 | 2024-07-15 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0263 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0263 | D | 01 | 2024-07-15 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0263 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B8B24F7A5EF04B82BA134C68BAD8F2D1
DDCL | CCP-W-B043-10-ME-B16-0001 | Data Sheet_ Black Start Emergency Diesel Generator | D | D | 01 | _ |  | 2023-12-08 | 2024-01-07 | 2024-03-26 | 2024-05-07 | 2024-03-06 | 2024-07-15 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | BSEDG | Mechanical | 박재현 | [10 empty] | CCP-EPC-TRM-PGU-0263 | D | 01 | 2024-07-15 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0263 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0263 | D | 01 | 2024-07-15 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0263 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5666F120C5244E0699697CA10F20BE23
DDCL | CCP-W-B043-10-ME-B16-0002 | Data Sheet_ Black Start Emergency Diesel Generator Panel/SWGR | D | D | 01 | _ |  | 2024-01-23 | 2024-02-22 | 2024-05-11 | 2024-06-22 | 2024-05-03 | 2024-07-15 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | BSEDG | Mechanical | 박재현 | [10 empty] | CCP-EPC-TRM-PGU-0263 | D | 01 | 2024-07-15 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0263 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0263 | D | 01 | 2024-07-15 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0263 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A6D0907791D14807BA82BBEFE8FECA9A
DDCL | CCP-W-B043-10-ME-E01-0001 | Schematic Wiring Diagram_ Black Start Emergency Diesel Generator | D | D | 01 | _ |  | 2024-02-20 | 2024-03-19 | 2024-04-07 | 2024-05-19 | 2024-06-10 | 2024-07-15 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | BSEDG | Mechanical | 박재현 | [10 empty] | CCP-EPC-TRM-PGU-0263 | D | 01 | 2024-07-15 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0263 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0263 | D | 01 | 2024-07-15 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0263 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CBC9F958A9264EE2B7DB018E0BC12B4C
DDCL | CCP-W-B182-09-ME-B18-0004 | FIN FAN COOLER - DELUGE SPRAY PUMP | D | D | 01 | _ |  | 2024-09-27 | 2024-10-21 | 2024-11-01 | 2025-01-11 | 2024-09-27 | 2024-10-02 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fin Fan Cooler | Mechanical | 김선영 | [10 empty] | CCP-EPC-TRM-PGU-0487 | D | 01 | 2024-10-02 | 2024-10-02 | 2024-10-12 | CCP-PGU-TRM-EPC-0487 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0487 | D | 01 | 2024-10-02 | 2024-10-02 | 2024-10-12 | CCP-PGU-TRM-EPC-0487 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:319E51F3FD7A43D985B52ECF5EB15B3D
DDCL | CCP-W-B134-13-ME-B01-0001 | General Arrangement Drawing_Hot Water Steam Heater (Including Name Plate Drawing) | D | D | 01 | _ |  | 2024-02-16 | 2024-03-17 | 2024-05-13 | 2024-06-24 | 2024-05-13 | 2024-06-14 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Hot Water Steam Heater | Mechanical | 김정민 | [10 empty] | CCP-EPC-TRM-PGU-0192 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0192 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0192 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0192 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:DC8DC6F815E14A6688B6C15EBA7F8211
DDCL | CCP-W-B182-09-ME-B18-0003 | FIN FAN COOLER - DELUGING TANK DATA SHEET & OUTLINE DRAWING | D | D | 01 | _ |  | 2024-07-24 | 2024-09-08 | 2024-09-09 | 2024-10-15 | 2024-07-23 | 2024-07-24 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fin Fan Cooler | Mechanical | 김선영 | [10 empty] | CCP-EPC-TRM-PGU-0308 | D | 01 | 2024-07-24 | 2024-07-25 | 2024-08-04 | CCP-PGU-TRM-EPC-0308 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0308 | D | 01 | 2024-07-24 | 2024-07-25 | 2024-08-04 | CCP-PGU-TRM-EPC-0308 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:74B3B77F5665498BA72457FC9DF031F9
DDCL | CCP-W-B182-09-ME-H05-0002 | FIN FAN COOLER - RACEWAY DRAWING | D | D | 01 | _ |  | 2024-09-27 | 2024-10-31 | 2024-11-30 | 2025-03-31 | 2024-12-17 | 2025-01-07 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fin Fan Cooler | Mechanical | 김선영 | [10 empty] | CCP-EPC-TRM-PGU-0840 | D | 01 | 2025-01-14 | 2025-01-16 | 2025-01-26 | CCP-EPC-TRM-PGU-0840 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0840 | D | 01 | 2025-01-14 | 2025-01-16 | 2025-01-26 | CCP-EPC-TRM-PGU-0840 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B1538B6CD1324B44BA9301E2A39910F5
DDCL | CCP-W-B182-09-ME-H05-0003 | FIN FAN COOLER - POWER DISTRIBUTION PANEL LAYOUT DRAWINGS | D | D | 01 | _ |  | 2024-09-27 | 2024-11-30 | 2024-12-01 | 2025-02-28 | 2024-11-27 | 2024-11-27 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fin Fan Cooler | Mechanical | 김선영 | [10 empty] | CCP-EPC-TRM-PGU-0642 | D | 01 | 2024-12-02 | 2024-12-06 | 2024-12-16 | CCP-PGU-TRM-EPC-0642 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0642 | D | 01 | 2024-12-02 | 2024-12-06 | 2024-12-16 | CCP-PGU-TRM-EPC-0642 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:84AE5740E044409895CADE50EE6A6DA3
DDCL | CCP-W-B182-09-ME-P14-0005 | FIN FAN COOLER - LIGHTING DATA SHEET & OUTLINE DRAWING | D | D | 01 | _ |  | 2024-04-18 | 2024-07-31 | 2024-08-01 | 2024-10-31 | 2024-04-18 | 2024-06-13 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fin Fan Cooler | Mechanical | 김선영 | [10 empty] | CCP-EPC-TRM-PGU-0185 | D | 01 | 2024-06-13 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0185 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0185 | D | 01 | 2024-06-13 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0185 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:59AD6C0517BD4C20970E06A5BCC2D9B8
DDCL | CCP-W-B134-13-ME-B16-0001 | Datasheet_Hot Water Steam Heater | D | D | 01 | _ |  | 2024-02-16 | 2024-03-17 | 2024-05-13 | 2024-06-24 | 2024-05-13 | 2024-06-14 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Hot Water Steam Heater | Mechanical | 김정민 | [10 empty] | CCP-EPC-TRM-PGU-0192 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0192 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0192 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0192 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:37E6521F153E4BF5A79BBC5C39BAB1F7
DDCL | CCP-W-B182-09-ME-P04-0001 | FIN FAN COOLER - PIPE MATERIAL SPECIFICATION | D | D | 01 | _ |  | 2024-04-20 | 2024-05-20 | 2024-06-30 | 2024-08-15 | 2024-09-03 | 2024-09-03 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fin Fan Cooler | Mechanical | 김선영 | [10 empty] | CCP-EPC-TRM-PGU-0471 | D | 01 | 2024-09-06 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0471 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0471 | D | 01 | 2024-09-06 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0471 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:31D5F1A3A85D4F0EA2E691A84FB6F3E8
DDCL | CCP-W-B182-09-ME-P14-0001 | FIN FAN COOLER - PIPE LINE LIST | D | D | 01 | _ |  | 2024-04-20 | 2024-05-20 | 2024-06-30 | 2024-08-15 | 2024-08-20 | 2024-08-21 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fin Fan Cooler | Mechanical | 김선영 | [10 empty] | CCP-EPC-TRM-PGU-0432 | D | 01 | 2024-08-27 | 2024-08-28 | 2024-09-07 | CCP-PGU-TRM-EPC-0432 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0432 | D | 01 | 2024-08-27 | 2024-08-28 | 2024-09-07 | CCP-PGU-TRM-EPC-0432 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A76F62CF3F1F475D834A3BB0C3E6FFA7
DDCL | CCP-W-B182-09-ME-H09-0001 | FIN FAN COOLER - CONTROL LOGIC DIAGRAM | D | D | 01 | _ |  | 2024-07-30 | 2024-08-30 | 2024-10-15 | 2024-12-25 | 2025-02-20 | 2025-02-20 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fin Fan Cooler | Mechanical | 김선영 | [10 empty] | CCP-EPC-TRM-PGU-0860 | D | 01 | 2025-02-24 | 2025-02-25 | 2025-03-07 | CCP-PGU-TRM-EPC-0860 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0860 | D | 01 | 2025-02-24 | 2025-02-25 | 2025-03-07 | CCP-PGU-TRM-EPC-0860 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1B7ACD00D1F7471FA76C36036DE5F650
DDCL | CCP-W-B182-09-ME-H04-0001 | FIN FAN COOLER - INSTRUMENT INSTALLATION DETAIL DRAWING | D | D | 01 | A |  | 2024-05-20 | 2024-06-20 | 2024-07-30 | 2024-09-15 | 2024-08-20 | 2024-08-30 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fin Fan Cooler | Mechanical | 김선영 | [10 empty] | CCP-EPC-TRM-PGU-0444 | D | 01 | 2024-08-30 | 2024-08-30 | 2024-09-09 | CCP-PGU-TRM-EPC-0444 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0444 | D | 01 | 2024-08-30 | 2024-08-30 | 2024-09-09 | CCP-PGU-TRM-EPC-0444 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:17E6BA20ED0C4B5C891864D570E0549B
DDCL | CCP-W-B182-09-ME-H21-0001 | FIN FAN COOLER - INSTRUMENT DATA SHEET | D | D | 01 | _ |  | 2024-05-20 | 2024-06-20 | 2024-07-30 | 2024-09-15 | 2024-08-20 | 2024-08-21 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fin Fan Cooler | Mechanical | 김선영 | [10 empty] | CCP-EPC-TRM-PGU-0432 | D | 01 | 2024-08-27 | 2024-08-28 | 2024-09-07 | CCP-PGU-TRM-EPC-0432 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0432 | D | 01 | 2024-08-27 | 2024-08-28 | 2024-09-07 | CCP-PGU-TRM-EPC-0432 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:54FDFA2EF6204B4CBCA875FE3D263DEC
DDCL | CCP-W-B182-09-ME-H05-0001 | FIN FAN COOLER - JUNCTION BOX OUTLINE AND LAYOUT DRAWING | D | D | 01 | _ |  | 2024-05-26 | 2024-06-26 | 2024-07-30 | 2024-09-15 | 2024-07-04 | 2024-07-04 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fin Fan Cooler | Mechanical | 김선영 | [10 empty] | CCP-EPC-TRM-PGU-0246 | D | 01 | 2024-07-04 | 2024-07-10 | 2024-07-20 | CCP-PGU-TRM-EPC-0246 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0246 | D | 01 | 2024-07-04 | 2024-07-10 | 2024-07-20 | CCP-PGU-TRM-EPC-0246 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FD0CD85A77C44A6FA23D3FE678C0E03E
DDCL | CCP-W-B182-09-ME-E02-0001 | FIN FAN COOLER - WIRING DIAGRAM | D | D | 01 | _ |  | 2024-05-26 | 2024-06-26 | 2024-07-30 | 2024-09-15 | 2024-11-13 | 2024-11-14 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fin Fan Cooler | Mechanical | 김선영 | [10 empty] | CCP-EPC-TRM-PGU-0637 | D | 01 | 2024-11-27 | 2024-11-27 | 2024-12-07 | CCP-PGU-TRM-EPC-0637 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0637 | D | 01 | 2024-11-27 | 2024-11-27 | 2024-12-07 | CCP-PGU-TRM-EPC-0637 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C6D86E3CA4554274A97A631569178319
DDCL | CCP-W-B182-09-ME-B33-0001 | FIN FAN COOLER - FOUNDATION DRAWINGS / CIVIL LOADING DATA WITH EMBEDDED MATERIAL DRAWING | D | D | 01 | _ |  | 2024-03-05 | 2024-04-05 | 2024-05-20 | 2024-06-30 | 2024-07-01 | 2024-07-01 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fin Fan Cooler | Mechanical | 김선영 | [10 empty] | CCP-EPC-TRM-PGU-0234 | D | 01 | 2024-07-01 | 2024-07-04 | 2024-07-14 | CCP-PGU-TRM-EPC-0234 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0234 | D | 01 | 2024-07-01 | 2024-07-04 | 2024-07-14 | CCP-PGU-TRM-EPC-0234 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:DBB2DFD955E340E284F31C909F8B4D6E
DDCL | CCP-W-B182-09-ME-A07-0001 | FIN FAN COOLER - SYSTEM DESCRIPTION | D | D | 01 | _ |  | 2024-01-21 | 2024-02-28 | 2024-04-15 | 2024-05-30 | 2024-03-05 | 2024-06-25 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fin Fan Cooler | Mechanical | 김선영 | [10 empty] | CCP-EPC-TRM-PGU-0222 | D | 01 | 2024-06-25 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0222 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0222 | D | 01 | 2024-06-25 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0222 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6824763BE5C54647B0CD25742DBE37F9
DDCL | CCP-W-B182-09-ME-B06-0001 | FIN FAN COOLER - P&I DIAGRAM | D | D | 01 | _ |  | 2024-01-31 | 2024-03-07 | 2024-04-30 | 2024-06-15 | 2024-02-29 | 2024-06-12 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fin Fan Cooler | Mechanical | 김선영 | [10 empty] | CCP-EPC-TRM-PGU-0180 | D | 01 | 2024-06-12 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0180 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0180 | D | 01 | 2024-06-12 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0180 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C2CA2AEDDAA44BF0A1B5EA018D6B70B4
DDCL | CCP-W-B182-09-ME-B01-0001 | FIN FAN COOLER - GENERAL ARRANGEMENT | D | D | 01 | _ |  | 2024-01-31 | 2024-03-07 | 2024-04-30 | 2024-06-15 | 2024-04-09 | 2024-06-13 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fin Fan Cooler | Mechanical | 김선영 | [10 empty] | CCP-EPC-TRM-PGU-0185 | D | 01 | 2024-06-13 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0185 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0185 | D | 01 | 2024-06-13 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0185 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CF4346926540405D927F79EC98FD72E0
DDCL | CCP-W-B182-09-ME-G18-0001 | FIN FAN COOLER - PERFORMANCE CURVE | D | D | 01 | _ |  | 2024-01-22 | 2024-02-28 | 2024-04-15 | 2024-05-30 | 2024-03-04 | 2024-06-12 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fin Fan Cooler | Mechanical | 김선영 | [10 empty] | CCP-EPC-TRM-PGU-0180 | D | 01 | 2024-06-12 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0180 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0180 | D | 01 | 2024-06-12 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0180 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7C9ED620861D42FF8FD7CAE2F8CAF0B2
DDCL | CCP-W-B182-09-ME-B18-0001 | FIN FAN COOLER - EQUIPMENT LIST | D | D | 01 | _ |  | 2024-01-22 | 2024-02-28 | 2024-04-15 | 2024-05-30 | 2024-03-05 | 2024-06-12 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fin Fan Cooler | Mechanical | 김선영 | [10 empty] | CCP-EPC-TRM-PGU-0180 | D | 01 | 2024-06-12 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0180 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0180 | D | 01 | 2024-06-12 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0180 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:345078EF38124FEAB7CADBAA35D85926
DDCL | CCP-W-B182-09-ME-P10-0001 | FIN FAN COOLER - VALVE DATA SHEET & OUTLINE DRAWING | D | D | 01 | _ |  | 2024-04-20 | 2024-05-20 | 2024-06-30 | 2024-08-15 | 2024-09-26 | 2024-09-30 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fin Fan Cooler | Mechanical | 김선영 | [10 empty] | CCP-EPC-TRM-PGU-0486 | D | 01 | 2024-09-30 | 2024-09-30 | 2024-10-10 | CCP-PGU-TRM-EPC-0486 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0486 | D | 01 | 2024-09-30 | 2024-09-30 | 2024-10-10 | CCP-PGU-TRM-EPC-0486 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4657F864266B4DFA83094F199DDC6159
DDCL | CCP-W-B182-09-ME-E24-0001 | FIN FAN COOLER - FAN DATA SHEET & OUTLINE DRAWING | D | D | 01 | _ |  | 2024-03-20 | 2024-04-20 | 2024-05-30 | 2024-07-15 | 2024-05-17 | 2024-07-11 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fin Fan Cooler | Mechanical | 김선영 | [10 empty] | CCP-EPC-TRM-PGU-0257 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0257 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0257 | D | 01 | 2024-07-11 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0257 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:0AFFD61A42F14371AAACD8E4E99926BA
DDCL | CCP-W-B182-09-ME-E26-0001 | FIN FAN COOLER - FAN MOTOR DATA SHEET & OUTLINE DRAWING | D | D | 01 | _ |  | 2024-03-20 | 2024-04-20 | 2024-05-30 | 2024-07-15 | 2024-05-17 | 2024-06-13 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fin Fan Cooler | Mechanical | 김선영 | [10 empty] | CCP-EPC-TRM-PGU-0185 | D | 01 | 2024-06-13 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0185 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0185 | D | 01 | 2024-06-13 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0185 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:79FC88DE43184CEF97B7AC7260B9129F
DDCL | CCP-W-B182-09-ME-P16-0001 | FIN FAN COOLER - PIPING ARRANGEMENT DRAWING | D | D | 01 | _ |  | 2024-04-20 | 2024-05-20 | 2024-06-30 | 2024-08-15 | 2024-09-26 | 2024-09-30 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fin Fan Cooler | Mechanical | 김선영 | [10 empty] | CCP-EPC-TRM-PGU-0486 | D | 01 | 2024-09-30 | 2024-09-30 | 2024-10-10 | CCP-PGU-TRM-EPC-0486 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0486 | D | 01 | 2024-09-30 | 2024-09-30 | 2024-10-10 | CCP-PGU-TRM-EPC-0486 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:DCC94A31002447F088DBD7F82BA1212C
DDCL | CCP-W-B130-05-ME-B06-0001 | BFP_P&I Diagram | D | D | 01 | _ |  | 2023-12-11 | 2024-01-22 | 2024-03-18 | 2024-04-29 | 2024-03-14 | 2024-03-14 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Boiler Feedwater Pump | Mechanical | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0108 | D | 01 | 2024-03-14 | 2024-03-15 | 2024-04-05 | CCP-PGU-TRM-EPC-0108 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0108 | D | 01 | 2024-03-14 | 2024-03-15 | 2024-04-05 | CCP-PGU-TRM-EPC-0108 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:398247E46FB0455C86E6E18CC052EF6D
DDCL | CCP-W-B129-06-ME-B06-0001 | CEP_P&I Diagram | D | D | 01 | _ |  | 2023-12-08 | 2024-01-19 | 2024-03-14 | 2024-04-25 | 2024-07-01 | 2024-07-01 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Condensate Extraction Pump | Mechanical | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0240 | D | 01 | 2024-07-01 | 2024-07-05 | 2024-07-15 | CCP-PGU-TRM-EPC-0240 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0240 | D | 01 | 2024-07-01 | 2024-07-05 | 2024-07-15 | CCP-PGU-TRM-EPC-0240 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2FC2F55788E44EF28826AB91A6CF46B8
DDCL | CCP-W-B130-05-ME-B04-0002 | BFP_I&C Junction Box & Outline Drawing | D | D | 01 | _ |  | 2024-02-06 | 2024-03-19 | 2024-05-06 | 2024-06-17 | 2024-03-15 | 2024-06-20 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Boiler Feedwater Pump | Mechanical | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0209 | D | 01 | 2024-06-20 | 2024-06-21 | 2024-07-01 | CCP-PGU-TRM-EPC-0209 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0209 | D | 01 | 2024-06-20 | 2024-06-21 | 2024-07-01 | CCP-PGU-TRM-EPC-0209 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5075BCC32F7E45CF9AE45B76CB51E0DF
DDCL | CCP-W-B078-16-ME-H05-0001 | GSP(WATER&OIL)_Panel Drawing | D | D | 01 | _ |  | 2024-03-13 | 2024-04-24 | 2024-06-05 | 2024-07-17 | 2024-06-20 | 2024-06-21 |  |  | BOP Plant | Plant EPC)기계기술1팀 | General Service Pumps | Mechanical | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0215 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0215 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0215 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0215 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:757AAB151E124E149435D4CB2C99BFBA
DDCL | CCP-W-B078-16-ME-B01-0001 | GSP(WATER&OIL)_Outline Drawing (including name plate) | D | D | 01 | _ |  | 2024-01-17 | 2024-02-28 | 2024-04-10 | 2024-05-22 | 2024-04-03 | 2024-06-21 |  |  | BOP Plant | Plant EPC)기계기술1팀 | General Service Pumps | Mechanical | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0215 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0215 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0215 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0215 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3B2C31A5FC4D4543884D5B911304E305
DDCL | CCP-W-B132-08-ME-B01-0001 | Outline Drawing_CCWP (Including Name Plate Drawing) | D | D | 01 | _ |  | 2024-01-13 | 2024-02-12 | 2024-04-12 | 2024-05-24 | 2024-02-20 | 2024-07-03 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Closed Cooling Water Pump | Mechanical | 박재현 | [10 empty] | CCP-EPC-TRM-PGU-0244 | D | 01 | 2024-07-03 | 2024-07-10 | 2024-07-20 | CCP-PGU-TRM-EPC-0244 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0244 | D | 01 | 2024-07-03 | 2024-07-10 | 2024-07-20 | CCP-PGU-TRM-EPC-0244 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:EEB753F45A064B68B0A712BD42946819
DDCL | CCP-W-B134-12-ME-B01-0001 | Outline Drawing_Hot Water Supply Pump (Including Name Plate Drawing) | D | D | 01 | _ |  | 2023-12-23 | 2024-01-22 | 2024-03-27 | 2024-05-26 | 2024-01-23 | 2024-06-14 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Hot Water Supply Pump | Mechanical | 김정민 | [10 empty] | CCP-EPC-TRM-PGU-0193 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0193 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0193 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0193 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:9817AA05A4C947729D5E568B94C8918B
DDCL | CCP-W-B039-15-ME-B01-0001 | Sump Pump_Outline Drawing (including name plate) | D | C | 01 | _ |  | 2024-03-15 | 2024-03-29 | 2024-06-13 | 2024-06-27 | 2024-06-04 | 2024-06-11 | 2024-09-25 | 2024-09-25 | BOP Plant | Plant EPC)기계기술1팀 | Sump Pump | Mechanical | 박대영 | [10 empty] | CCP-EPC-TRM-PGU-0484 | C | 01 | 2024-09-25 |  | 2024-07-25 | CCP-PGU-TRM-EPC-0255 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0255 | D | 01 | 2024-07-10 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0255 | Deemed Approved | CCP-EPC-TRM-PGU-0484 | C | 01 | 2024-09-25 | [84 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:61035E5BFA04429AA9ECC0B5D0137351
DDCL | CCP-W-B130-05-ME-B01-0001 | BFP_Outline Drawing (including Foundation, name plate) | D | D | 01 | _ |  | 2023-12-04 | 2024-01-15 | 2024-03-11 | 2024-04-22 | 2024-03-14 | 2024-03-14 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Boiler Feedwater Pump | Mechanical | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0112 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-05 | CCP-PGU-TRM-EPC-0112 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0112 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-05 | CCP-PGU-TRM-EPC-0112 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:56941EE2BF654F8C8491964C672E3392
DDCL | CCP-W-B129-06-ME-B01-0001 | CEP_Outline Drawing (including Foundation, name plate) | D | D | 01 | _ |  | 2023-12-31 | 2024-02-11 | 2024-03-07 | 2024-04-18 | 2024-07-01 | 2024-07-01 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Condensate Extraction Pump | Mechanical | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0240 | D | 01 | 2024-07-01 | 2024-07-05 | 2024-07-15 | CCP-PGU-TRM-EPC-0240 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0240 | D | 01 | 2024-07-01 | 2024-07-05 | 2024-07-15 | CCP-PGU-TRM-EPC-0240 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5C227CE2A12741AC95DC9975EF8A1620
DDCL | CCP-W-B130-05-ME-B04-0001 | BFP_Motor Outline, Terminal Box & Name Plate Drawing | D | D | 01 | _ |  | 2024-01-08 | 2024-02-19 | 2024-04-07 | 2024-05-19 | 2024-06-17 | 2024-06-18 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Boiler Feedwater Pump | Mechanical | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0206 | D | 01 | 2024-06-18 | 2024-06-20 | 2024-06-30 | CCP-PGU-TRM-EPC-0206 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0206 | D | 01 | 2024-06-18 | 2024-06-20 | 2024-06-30 | CCP-PGU-TRM-EPC-0206 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:16C241525F4940B6ADA49F11987782D2
DDCL | CCP-W-B129-06-ME-B04-0001 | CEP_Motor Outline, Terminal Box & Name Plate Drawing | D | D | 01 | _ |  | 2024-01-01 | 2024-02-12 | 2024-03-31 | 2024-05-12 | 2024-07-02 | 2024-07-03 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Condensate Extraction Pump | Mechanical | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0245 | D | 01 | 2024-07-03 | 2024-07-10 | 2024-07-20 | CCP-PGU-TRM-EPC-0245 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0245 | D | 01 | 2024-07-03 | 2024-07-10 | 2024-07-20 | CCP-PGU-TRM-EPC-0245 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:43DAC91751F840E69D8F5C86A0D8078D
DDCL | CCP-W-B132-08-ME-E26-0001 | Outline Drawing_CCWP Motor (Including Name Plate Drawing) | D | D | 01 | _ |  | 2024-01-30 | 2024-02-29 | 2024-02-14 | 2024-03-27 | 2024-02-20 | 2024-07-03 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Closed Cooling Water Pump | Mechanical | 박재현 | [10 empty] | CCP-EPC-TRM-PGU-0244 | D | 01 | 2024-07-03 | 2024-07-10 | 2024-07-20 | CCP-PGU-TRM-EPC-0244 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0244 | D | 01 | 2024-07-03 | 2024-07-10 | 2024-07-20 | CCP-PGU-TRM-EPC-0244 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B0CE9B5730FB4F278A1AD90675C8A6C7
DDCL | CCP-W-B134-12-ME-E26-0001 | Outline Drawing_Hot Water Supply Pump Motor (Including Name Plate Drawing) | D | D | 01 | _ |  | 2023-12-23 | 2024-01-22 | 2024-03-27 | 2024-05-26 | 2024-01-23 | 2024-06-14 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Hot Water Supply Pump | Mechanical | 김정민 | [10 empty] | CCP-EPC-TRM-PGU-0193 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0193 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0193 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0193 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F8BBDAF6A3784E6BB77993A4854B14ED
DDCL | CCP-W-B078-16-ME-B04-0001 | GSP(WATER&OIL)_Motor Outline, Terminal Box & Name Plate Drawing | D | D | 01 | _ |  | 2024-02-28 | 2024-04-10 | 2024-05-22 | 2024-07-03 | 2024-07-02 | 2024-07-02 |  |  | BOP Plant | Plant EPC)기계기술1팀 | General Service Pumps | Mechanical | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0242 | D | 01 | 2024-07-02 | 2024-07-05 | 2024-07-12 | CCP-PGU-TRM-EPC-0242 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0242 | D | 01 | 2024-07-02 | 2024-07-05 | 2024-07-12 | CCP-PGU-TRM-EPC-0242 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E0758CCEBF42492E82E54C1DDD9CCDD9
DDCL | CCP-W-B129-06-ME-B02-0001 | CEP_Pump Sectional Drawing | D | D | 01 | _ |  | 2024-01-29 | 2024-02-28 | 2024-04-05 | 2024-05-05 | 2024-03-14 | 2024-03-14 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Condensate Extraction Pump | Mechanical | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0106 | D | 01 | 2024-03-14 | 2024-03-14 | 2024-04-02 | CCP-PGU-TRM-EPC-0106 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0106 | D | 01 | 2024-03-14 | 2024-03-14 | 2024-04-02 | CCP-PGU-TRM-EPC-0106 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A4371D4274084278AF8D01FA49FD03B6
DDCL | CCP-W-B130-05-ME-B02-0001 | BFP_Pump Sectional Drawing | D | C | 01 | _ |  | 2024-01-10 | 2024-02-04 | 2024-04-07 | 2024-05-19 | 2024-03-14 | 2024-03-14 | 2024-05-24 | 2024-06-10 | BOP Plant | Plant EPC)기계기술1팀 | Boiler Feedwater Pump | Mechanical | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0173 | C | 01 | 2024-06-10 | 2024-06-11 | 2024-06-21 | CCP-PGU-TRM-EPC-0173 | C | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0113 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-09 | CCP-PGU-TRM-EPC-0113 | Approved With Comment | CCP-EPC-TRM-PGU-0173 | C | 01 | 2024-06-10 | 2024-06-11 | 2024-06-21 | CCP-PGU-TRM-EPC-0173 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:BFD08A8D32464DE692E3337153E4AE90
DDCL | CCP-W-B078-16-ME-B02-0001 | GSP(WATER&OIL)_Pump Sectional Drawing | D | D | 01 | _ |  | 2024-02-14 | 2024-03-27 | 2024-05-08 | 2024-06-19 | 2024-05-03 | 2024-06-21 |  |  | BOP Plant | Plant EPC)기계기술1팀 | General Service Pumps | Mechanical | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0215 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0215 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0215 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0215 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D7BC8B5FA51240608ED1DB5DE8EC39E9
DDCL | CCP-W-B129-06-ME-B04-0002 | CEP_I&C Junction Box & Outline Drawing | D | D | 01 | _ |  | 2024-06-10 | 2024-08-10 | 2024-08-11 | 2024-09-30 | 2024-06-10 | 2024-07-01 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Condensate Extraction Pump | Mechanical | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0240 | D | 01 | 2024-07-01 | 2024-07-05 | 2024-07-15 | CCP-PGU-TRM-EPC-0240 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0240 | D | 01 | 2024-07-01 | 2024-07-05 | 2024-07-15 | CCP-PGU-TRM-EPC-0240 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F2694CEE989B46C8962494DCC2AACA25
DDCL | CCP-W-B039-15-ME-B16-0001 | Sump Pump_Pump Data Sheet & Performance Curve | D | C | 01 | _ |  | 2024-04-14 | 2024-04-28 | 2024-07-13 | 2024-07-27 | 2024-05-24 | 2024-06-11 | 2024-09-25 | 2024-09-25 | BOP Plant | Plant EPC)기계기술1팀 | Sump Pump | Mechanical | 박대영 | [10 empty] | CCP-EPC-TRM-PGU-0484 | C | 01 | 2024-09-25 |  | 2024-07-25 | CCP-PGU-TRM-EPC-0255 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0255 | D | 01 | 2024-07-10 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0255 | Deemed Approved | CCP-EPC-TRM-PGU-0484 | C | 01 | 2024-09-25 | [84 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:20BF49CB3E654207826A9CC6B6804FB7
DDCL | CCP-W-B039-15-ME-E24-0002 | Sump Pump_Motor Data Sheet & Performance Curve | D | C | 01 | _ |  | 2024-05-14 | 2024-05-28 | 2024-08-12 | 2024-08-26 | 2024-06-17 | 2024-06-17 | 2024-09-25 | 2024-09-25 | BOP Plant | Plant EPC)기계기술1팀 | Sump Pump | Mechanical | 박대영 | [10 empty] | CCP-EPC-TRM-PGU-0484 | C | 01 | 2024-09-25 |  | 2024-06-29 | CCP-PGU-TRM-EPC-0202 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0202 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0202 | Deemed Approved | CCP-EPC-TRM-PGU-0484 | C | 01 | 2024-09-25 | [84 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5127AF23FB334F0F8F6DB68DFDB16E1C
DDCL | CCP-W-B134-12-ME-B16-0001 | Datasheet_Hot Water Supply Pump | D | D | 01 | _ |  | 2023-12-23 | 2024-01-22 | 2024-03-27 | 2024-05-26 | 2024-01-23 | 2024-06-14 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Hot Water Supply Pump | Mechanical | 김정민 | [10 empty] | CCP-EPC-TRM-PGU-0193 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0193 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0193 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0193 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:16F9DBFA189C404A82EAB7EE6047C792
DDCL | CCP-W-B134-12-ME-E24-0001 | Datasheet_Hot Water Supply Pump Motor | D | D | 01 | _ |  | 2023-12-23 | 2024-01-22 | 2024-03-27 | 2024-05-26 | 2024-01-23 | 2024-06-14 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Hot Water Supply Pump | Mechanical | 김정민 | [10 empty] | CCP-EPC-TRM-PGU-0193 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0193 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0193 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0193 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:21F48C585CD14EC5B3DF2E2CFDD16417
DDCL | CCP-W-B132-08-ME-B16-0001 | Technical Data_CCWP | D | D | 01 | _ |  | 2024-01-13 | 2024-02-12 | 2024-06-26 | 2024-08-07 | 2024-02-20 | 2024-07-03 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Closed Cooling Water Pump | Mechanical | 박재현 | [10 empty] | CCP-EPC-TRM-PGU-0244 | D | 01 | 2024-07-03 | 2024-07-10 | 2024-07-20 | CCP-PGU-TRM-EPC-0244 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0244 | D | 01 | 2024-07-03 | 2024-07-10 | 2024-07-20 | CCP-PGU-TRM-EPC-0244 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F0DE48511D32479684362971BDC2C34C
DDCL | CCP-W-B132-08-ME-E24-0001 | Technical Data_CCWP Motor | D | D | 01 | _ |  | 2024-01-30 | 2024-02-29 | 2024-07-13 | 2024-08-24 | 2024-02-20 | 2024-07-03 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Closed Cooling Water Pump | Mechanical | 박재현 | [10 empty] | CCP-EPC-TRM-PGU-0244 | D | 01 | 2024-07-03 | 2024-07-10 | 2024-07-20 | CCP-PGU-TRM-EPC-0244 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0244 | D | 01 | 2024-07-03 | 2024-07-10 | 2024-07-20 | CCP-PGU-TRM-EPC-0244 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:925F5B2F238E4751B281FC44D7F68DEB
DDCL | CCP-W-B129-06-ME-B16-0003 | CEP_Suction Strainer Specification | D | D | 01 | _ |  | 2024-01-30 | 2024-03-12 | 2024-04-29 | 2024-06-10 | 2024-02-02 | 2024-03-14 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Condensate Extraction Pump | Mechanical | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0107 | D | 01 | 2024-03-14 | 2024-03-14 | 2024-04-05 | CCP-PGU-TRM-EPC-0107 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0107 | D | 01 | 2024-03-14 | 2024-03-14 | 2024-04-05 | CCP-PGU-TRM-EPC-0107 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:0AAE2847A13D4CB8BF4D22B3BFBE0567
DDCL | CCP-W-B078-16-ME-E24-0002 | GSP(WATER&OIL)_Motor Data Sheet & Performance Curve | D | D | 01 | _ |  | 2024-02-28 | 2024-04-10 | 2024-05-22 | 2024-07-03 | 2024-07-02 | 2024-07-02 |  |  | BOP Plant | Plant EPC)기계기술1팀 | General Service Pumps | Mechanical | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0242 | D | 01 | 2024-07-02 | 2024-07-05 | 2024-07-12 | CCP-PGU-TRM-EPC-0242 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0242 | D | 01 | 2024-07-02 | 2024-07-05 | 2024-07-12 | CCP-PGU-TRM-EPC-0242 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B014D8E9BA74447B9BAA96AF7C41DCB5
DDCL | CCP-W-B078-16-ME-B16-0002 | GSP(WATER&OIL)_Pump Data Sheet & Performance Curve | D | D | 01 | _ |  | 2024-02-28 | 2024-04-10 | 2024-05-22 | 2024-07-03 | 2024-05-13 | 2024-06-21 |  |  | BOP Plant | Plant EPC)기계기술1팀 | General Service Pumps | Mechanical | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0215 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0215 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0215 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0215 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C33EF91CD5344C53BFDA3DFE7A1C28B1
DDCL | CCP-W-B129-06-ME-B16-0001 | CEP_Pump Data Sheet & Characteristic Curve | D | D | 01 | _ |  | 2023-11-30 | 2024-01-11 | 2024-03-07 | 2024-04-18 | 2024-03-14 | 2024-03-14 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Condensate Extraction Pump | Mechanical | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0105 | D | 01 | 2024-03-14 | 2024-03-14 | 2024-04-09 | CCP-PGU-TRM-EPC-0105 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0105 | D | 01 | 2024-03-14 | 2024-03-14 | 2024-04-09 | CCP-PGU-TRM-EPC-0105 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:76A1511BE44D4E3282C54C934510F98A
DDCL | CCP-W-B129-06-ME-E24-0002 | CEP_Motor Data Sheet & Characteristic Curve | D | D | 01 | _ |  | 2024-01-01 | 2024-02-12 | 2024-03-31 | 2024-05-12 | 2024-06-26 | 2024-07-01 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Condensate Extraction Pump | Mechanical | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0240 | D | 01 | 2024-07-01 | 2024-07-05 | 2024-07-15 | CCP-PGU-TRM-EPC-0240 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0240 | D | 01 | 2024-07-01 | 2024-07-05 | 2024-07-15 | CCP-PGU-TRM-EPC-0240 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D27965DF34E24738A994DD4FAF4BD8AD
DDCL | CCP-W-B130-05-ME-B16-0001 | BFP_Pump Data Sheet & Characteristic Curve | D | D | 01 | _ |  | 2023-12-04 | 2024-01-15 | 2024-03-11 | 2024-04-22 | 2024-03-14 | 2024-03-14 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Boiler Feedwater Pump | Mechanical | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-05 | CCP-PGU-TRM-EPC-0110 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-05 | CCP-PGU-TRM-EPC-0110 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:528EAD5CB1864DF0B7A662555B72B4A9
DDCL | CCP-W-B130-05-ME-E24-0002 | BFP_Motor Data Sheet & Characteristic Curve | D | D | 01 | _ |  | 2024-01-08 | 2024-02-19 | 2024-04-07 | 2024-05-19 | 2024-06-18 | 2024-06-18 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Boiler Feedwater Pump | Mechanical | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0206 | D | 01 | 2024-06-18 | 2024-06-20 | 2024-06-30 | CCP-PGU-TRM-EPC-0206 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0206 | D | 01 | 2024-06-18 | 2024-06-20 | 2024-06-30 | CCP-PGU-TRM-EPC-0206 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:BCF8C4785FFF475D9C2F928275681800
DDCL | CCP-W-B130-05-ME-B16-0004 | BFP_Suction Strainer Specification | D | D | 01 | _ |  | 2024-01-04 | 2024-02-15 | 2024-05-04 | 2024-06-15 | 2024-02-02 | 2024-03-14 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Boiler Feedwater Pump | Mechanical | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0109 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-05 | CCP-PGU-TRM-EPC-0109 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0109 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-05 | CCP-PGU-TRM-EPC-0109 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:87B9CCF538E64CBC88E244D198B893AC
DDCL | CCP-W-B129-06-ME-H21-0001 | CEP_Instrument List & Specification | D | D | 01 | _ |  | 2024-02-06 | 2024-03-19 | 2024-05-06 | 2024-06-17 | 2024-03-18 | 2024-07-01 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Condensate Extraction Pump | Mechanical | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0240 | D | 01 | 2024-07-01 | 2024-07-05 | 2024-07-15 | CCP-PGU-TRM-EPC-0240 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0240 | D | 01 | 2024-07-01 | 2024-07-05 | 2024-07-15 | CCP-PGU-TRM-EPC-0240 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:AD041C38873B43BC9AD8D6DE8EF70A8C
DDCL | CCP-W-B130-05-ME-H21-0001 | BFP_Instrument List & Specification | D | D | 01 | _ |  | 2024-02-03 | 2024-03-16 | 2024-05-06 | 2024-06-17 | 2024-03-15 | 2024-06-20 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Boiler Feedwater Pump | Mechanical | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0209 | D | 01 | 2024-06-20 | 2024-06-21 | 2024-07-01 | CCP-PGU-TRM-EPC-0209 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0209 | D | 01 | 2024-06-20 | 2024-06-21 | 2024-07-01 | CCP-PGU-TRM-EPC-0209 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8BA67CBF2A2C494C9D2CD1485F1493C0
DDCL | CCP-W-B078-16-ME-H21-0001 | GSP(WATER&OIL)_Instrument List & Specification | D | D | 01 | _ |  | 2024-04-10 | 2024-05-22 | 2024-07-03 | 2024-08-14 | 2024-06-20 | 2024-06-21 |  |  | BOP Plant | Plant EPC)기계기술1팀 | General Service Pumps | Mechanical | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0215 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0215 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0215 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0215 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:62351DC6FF2645FFB9BF3952B386BFDB
DDCL | CCP-W-B039-15-ME-H21-0001 | Sump Pump_Instrument List & Specification | D | C | 01 | _ |  | 2024-05-14 | 2024-05-28 | 2024-08-12 | 2024-08-26 | 2024-06-28 | 2024-09-25 | 2024-09-25 | 2024-09-25 | BOP Plant | Plant EPC)기계기술1팀 | Sump Pump | Mechanical | 박대영 | [10 empty] | CCP-EPC-TRM-PGU-0484 | C | 01 | 2024-09-25 |  | 2024-07-11 | CCP-PGU-TRM-EPC-0226 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0226 | D | 01 | 2024-06-28 | 2024-07-01 | 2024-07-11 | CCP-PGU-TRM-EPC-0226 | Deemed Approved | CCP-EPC-TRM-PGU-0484 | C | 01 | 2024-09-25 | [84 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C433A1B28AA44C84B5000FFF6745EDE5
DDCL | CCP-W-B039-15-ME-B04-0001 | Sump Pump_Local Control Panel Drawing | D | C | 01 | _ |  | 2024-06-13 | 2024-06-27 | 2024-09-11 | 2024-09-25 | 2024-06-11 | 2024-06-11 | 2024-09-25 | 2024-09-25 | BOP Plant | Plant EPC)기계기술1팀 | Sump Pump | Mechanical | 박대영 | [10 empty] | CCP-EPC-TRM-PGU-0484 | C | 01 | 2024-09-25 |  | 2024-07-25 | CCP-PGU-TRM-EPC-0255 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0255 | D | 01 | 2024-07-10 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0255 | Deemed Approved | CCP-EPC-TRM-PGU-0484 | C | 01 | 2024-09-25 | [84 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D249787E375F41C8A695DE7047924D2D
DDCL | CCP-W-B039-15-ME-E02-0001 | Sump Pump_Wiring Diagram | D | C | 01 | _ |  | 2024-07-13 | 2024-07-27 | 2024-10-11 | 2024-10-25 | 2024-06-11 | 2024-06-11 | 2024-09-25 | 2024-09-25 | BOP Plant | Plant EPC)기계기술1팀 | Sump Pump | Mechanical | 박대영 | [10 empty] | CCP-EPC-TRM-PGU-0484 | C | 01 | 2024-09-25 |  | 2024-07-25 | CCP-PGU-TRM-EPC-0255 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0255 | D | 01 | 2024-07-10 | 2024-07-15 | 2024-07-25 | CCP-PGU-TRM-EPC-0255 | Deemed Approved | CCP-EPC-TRM-PGU-0484 | C | 01 | 2024-09-25 | [84 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:375A4696C63142998AFE88823BB60B30
DDCL | CCP-W-B000-07-ME-B01-0001 | Outline Drawing_Bypass Valves (Including Name Plate Drawing) | D | C | 01 | A |  | 2024-02-02 | 2024-03-15 | 2024-05-19 | 2024-06-30 | 2024-05-21 |  | 2024-10-31 | 2024-11-26 | BOP Plant | Plant EPC)프로세스기술1팀 | Bypass & PRDS | Mechanical | 안진엽 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FBDF9DED16A649BFAFAAF4B6A94136B8
DDCL | CCP-W-B000-07-ME-B16-0001 | Data Sheet and Charateristic Curves_Bypass Valves | D | C | 01 | A |  | 2024-02-02 | 2024-03-15 | 2024-05-19 | 2024-06-30 | 2024-05-21 |  | 2024-10-31 | 2024-11-26 | BOP Plant | Plant EPC)프로세스기술1팀 | Bypass & PRDS | Mechanical | 안진엽 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:73FF74109B9C407AA2C500E6E6468D92
DDCL | CCP-W-B000-18-ME-B01-0001 | Outline Drawing_Safety & Relief Valves (Including Name Plate Drawing) | D | D | 01 | _ |  | 2024-02-26 | 2024-03-08 | 2024-05-26 | 2024-06-07 | 2024-04-24 | 2024-10-23 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | SRV (Safety Relief Valve) | Mechanical | 박재현 | [10 empty] | CCP-EPC-TRM-PGU-0494 | D | 01 | 2024-10-23 | 2024-10-24 | 2024-11-03 | CCP-PGU-TRM-EPC-0494 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0494 | D | 01 | 2024-10-23 | 2024-10-24 | 2024-11-03 | CCP-PGU-TRM-EPC-0494 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6BE4CC7BD43547DEA70C888675513A34
DDCL | CCP-W-B000-18-ME-B16-0001 | Data Sheet_Safety & Relief Valves | D | D | 01 | _ |  | 2024-02-26 | 2024-03-08 | 2024-05-26 | 2024-06-07 | 2024-04-24 | 2024-10-23 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | SRV (Safety Relief Valve) | Mechanical | 박재현 | [10 empty] | CCP-EPC-TRM-PGU-0494 | D | 01 | 2024-10-23 | 2024-10-24 | 2024-11-03 | CCP-PGU-TRM-EPC-0494 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0494 | D | 01 | 2024-10-23 | 2024-10-24 | 2024-11-03 | CCP-PGU-TRM-EPC-0494 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:33F709FDA8D9418482504D03654C567C
DDCL | CCP-W-B000-11-ME-B01-0002 | General Arrangement Drawing_Motor Operated Gate & Globe Valve (Including Name Plate Drawing) | D | D | 01 | _ |  | 2024-02-02 | 2024-03-15 | 2024-05-19 | 2024-06-30 | 2024-04-30 | 2024-06-18 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | MOV (Motor Operated Valve) - Butterfly | Mechanical | 김정민 | [10 empty] | CCP-EPC-TRM-PGU-0207 | D | 01 | 2024-06-18 | 2024-06-21 | 2024-07-01 | CCP-PGU-TRM-EPC-0207 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0207 | D | 01 | 2024-06-18 | 2024-06-21 | 2024-07-01 | CCP-PGU-TRM-EPC-0207 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:038A41953B5F402DB497CA5900492EF0
DDCL | CCP-W-B000-11-ME-B16-0002 | Technical data sheet_Motor operated Gate & Globe Valve | D | D | 01 | _ |  | 2024-02-02 | 2024-03-15 | 2024-05-19 | 2024-06-30 | 2024-04-26 | 2024-06-18 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | MOV (Motor Operated Valve) - Butterfly | Mechanical | 김정민 | [10 empty] | CCP-EPC-TRM-PGU-0207 | D | 01 | 2024-06-18 | 2024-06-21 | 2024-07-01 | CCP-PGU-TRM-EPC-0207 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0207 | D | 01 | 2024-06-18 | 2024-06-21 | 2024-07-01 | CCP-PGU-TRM-EPC-0207 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6EC02CF498A34DDFB7293F3BF31987E7
DDCL | CCP-W-B000-11-ME-B01-0001 | General Arrangement Drawing_Motor Operated Butterfly Valve (Including Name Plate Drawing) | D | D | 01 | _ |  | 2024-02-02 | 2024-03-15 | 2024-05-19 | 2024-06-30 | 2024-04-26 | 2024-06-18 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | MOV (Motor Operated Valve) - Gate / Globe / Ball | Mechanical | 김정민 | [10 empty] | CCP-EPC-TRM-PGU-0205 | D | 01 | 2024-06-18 | 2024-06-20 | 2024-06-30 | CCP-PGU-TRM-EPC-0205 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0205 | D | 01 | 2024-06-18 | 2024-06-20 | 2024-06-30 | CCP-PGU-TRM-EPC-0205 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D7E3CF90676247F3A318BA3E114FE92F
DDCL | CCP-W-B000-11-ME-B16-0001 | Technical data sheet_Motor operated Butterfly Valve | D | D | 01 | _ |  | 2024-02-02 | 2024-03-15 | 2024-05-19 | 2024-06-30 | 2024-04-26 | 2024-06-18 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | MOV (Motor Operated Valve) - Gate / Globe / Ball | Mechanical | 김정민 | [10 empty] | CCP-EPC-TRM-PGU-0205 | D | 01 | 2024-06-18 | 2024-06-20 | 2024-06-30 | CCP-PGU-TRM-EPC-0205 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0205 | D | 01 | 2024-06-18 | 2024-06-20 | 2024-06-30 | CCP-PGU-TRM-EPC-0205 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:EE2621713CF54317AE39844EDD9B8257
DDCL | CCP-W-B000-17-ME-B01-0001 | Outline Drawing_Silencer (Including Name Plate Drawing) | D | D | 01 | _ |  | 2023-12-22 | 2024-02-02 | 2024-03-22 | 2024-05-03 | 2024-02-06 | 2024-06-10 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Silencer | Mechanical | 박재현 | [10 empty] | CCP-EPC-TRM-PGU-0177 | D | 01 | 2024-06-11 | 2024-06-11 | 2024-06-21 | CCP-PGU-TRM-EPC-0177 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0177 | D | 01 | 2024-06-11 | 2024-06-11 | 2024-06-21 | CCP-PGU-TRM-EPC-0177 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:81436382E4F64383B941564FDBFA6ABA
DDCL | CCP-W-B000-17-ME-B16-0001 | Data Sheet_Silencer | D | D | 01 | _ |  | 2023-12-22 | 2024-02-02 | 2024-03-22 | 2024-05-03 | 2024-02-06 | 2024-06-10 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Silencer | Mechanical | 박재현 | [10 empty] | CCP-EPC-TRM-PGU-0177 | D | 01 | 2024-06-11 | 2024-06-11 | 2024-06-21 | CCP-PGU-TRM-EPC-0177 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0177 | D | 01 | 2024-06-11 | 2024-06-11 | 2024-06-21 | CCP-PGU-TRM-EPC-0177 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8BF165134D3643EA935D35D300B46A5E
DDCL | CCP-W-B054-22-ME-0001 | Equipment Arrangement Drawing for Chemical Laboratory Equipment | D | D | 01 | _ |  | 2024-03-26 | 2024-04-26 | 2024-08-31 | 2024-09-30 | 2024-03-27 | 2024-08-30 |  |  | BOP Plant | Plant EPC)기계기술2팀 | Laboratory Equipment | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0443 | D | 01 | 2024-08-30 | 2024-08-30 | 2024-09-09 | CCP-PGU-TRM-EPC-0443 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0443 | D | 01 | 2024-08-30 | 2024-08-30 | 2024-09-09 | CCP-PGU-TRM-EPC-0443 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:DAAD32149ED142E39E250D1B8166A63C
DDCL | CCP-W-B054-22-EL-0003 | Power Line Arrangement Drawing for Chemical Laboratory Equipment | D | D | 01 | _ |  | 2024-05-31 | 2024-06-30 | 2024-08-31 | 2024-09-30 | 2024-03-27 | 2024-09-05 |  |  | BOP Plant | Plant EPC)기계기술2팀 | Laboratory Equipment | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0470 | D | 01 | 2024-09-05 | 2024-09-06 | 2024-09-16 | CCP-PGU-TRM-EPC-0470 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0470 | D | 01 | 2024-09-05 | 2024-09-06 | 2024-09-16 | CCP-PGU-TRM-EPC-0470 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:28005D8D2A934954878B7C115A7337C9
DDCL | CCP-W-B054-22-ME-0004 | Utility Line Arrangement Drawing for Chemical Laboratory Equipment | D | D | 01 | _ |  | 2024-05-31 | 2024-06-30 | 2024-08-31 | 2024-09-30 | 2024-03-05 | 2024-08-30 |  |  | BOP Plant | Plant EPC)기계기술2팀 | Laboratory Equipment | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0443 | D | 01 | 2024-08-30 | 2024-08-30 | 2024-09-09 | CCP-PGU-TRM-EPC-0443 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0443 | D | 01 | 2024-08-30 | 2024-08-30 | 2024-09-09 | CCP-PGU-TRM-EPC-0443 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E2BDD808001446319D3BD175BAB0E116
DDCL | CCP-W-B054-22-ME-0002 | Equipment List & Specification for Chemical Laboratory Equipment | D | D | 02 | A |  | 2024-03-26 | 2024-04-26 | 2024-08-31 | 2024-09-30 | 2024-03-05 | 2024-10-07 |  |  | BOP Plant | Plant EPC)기계기술2팀 | Laboratory Equipment | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0470 | D | 02 | 2024-09-05 | 2024-09-06 | 2024-08-05 | CCP-PGU-TRM-EPC-0310 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0310 | D | 01 | 2024-07-25 | 2024-07-26 | 2024-08-05 | CCP-PGU-TRM-EPC-0310 | Deemed Approved | CCP-EPC-TRM-PGU-0470 | D | 02 | 2024-09-05 | 2024-09-06 | [83 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E4286C44766247A4A54B00B85005A65F
DDCL | CCP-W-B044-25-ME-H21-0002 | FGSS_INSTRUMENT DATA SHEET AND SPECIFICATION FOR PRE- HEATER | D | D | 01 | A |  | 2024-08-26 | 2024-09-10 | 2025-01-02 | 2025-01-10 | 2024-09-03 | 2024-11-04 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0473 | D | 01 | 2024-09-10 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0473 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0473 | D | 01 | 2024-09-10 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0473 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:ABE051736EBA4CDE98A073D892AA319B
DDCL | CCP-W-B044-25-ME-K14-0003 | FGSS_HARDWIRED IO LIST FOR PRE- HEATER | D | D | 01 | A |  | 2024-08-26 | 2024-09-10 | 2025-01-02 | 2025-01-10 | 2024-09-03 | 2024-11-04 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0473 | D | 01 | 2024-09-10 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0473 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0473 | D | 01 | 2024-09-10 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0473 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F064803095B048039C32FC3C0440751F
DDCL | CCP-W-B044-25-ME-H99-0010 | FGSS_INSTRUMENT LIST FOR PRE- HEATER | D | D | 01 | A |  | 2024-08-26 | 2024-09-10 | 2025-01-02 | 2025-01-10 | 2024-09-03 | 2024-11-04 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0473 | D | 01 | 2024-09-10 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0473 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0473 | D | 01 | 2024-09-10 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0473 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4A4C89477F974302B7A052CD4F97E633
DDCL | CCP-W-B044-25-ME-E04-0003 | FGSS_LOCAL CONTROL PANEL LAYOUT DRAWING FOR PRE- HEATER | D | D | 01 | A |  | 2024-08-26 | 2024-09-10 | 2025-01-02 | 2025-01-10 | 2024-09-03 | 2024-11-04 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0473 | D | 01 | 2024-09-10 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0473 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0473 | D | 01 | 2024-09-10 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0473 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A21D5974B94141B88880C8DEFCC7D26F
DDCL | CCP-W-B044-25-ME-H99-0011 | FGSS_INSTRUMENT LOCATION DRAWING FOR PRE- HEATER | D | D | 01 | A |  | 2024-08-26 | 2024-09-10 | 2025-01-02 | 2025-01-10 | 2024-09-03 | 2024-11-04 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0473 | D | 01 | 2024-09-10 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0473 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0473 | D | 01 | 2024-09-10 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0473 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:084038807E5D4692BCA64A4CEBEFD098
DDCL | CCP-W-B044-25-ME-E03-0003 | FGSS_INTERCONNECTION WIRING DIAGRAM FOR PRE- HEATER | D | D | 01 | A |  | 2024-08-26 | 2024-09-10 | 2025-01-02 | 2025-01-10 | 2024-09-03 | 2024-11-04 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0473 | D | 01 | 2024-09-10 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0473 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0473 | D | 01 | 2024-09-10 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0473 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:164B488FE49D4C74822FFFD571184A46
DDCL | CCP-W-B044-25-ME-E03-0002 | FGSS_CONTROL CABINET PANEL WIRING DIAGRAM FOR PRE- HEATER | D | D | 01 | A |  | 2024-08-26 | 2024-09-10 | 2025-01-02 | 2025-01-10 | 2024-09-03 | 2024-11-04 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0473 | D | 01 | 2024-09-10 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0473 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0473 | D | 01 | 2024-09-10 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0473 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:00428C7D73F244D2A47712D193579E39
DDCL | CCP-W-B044-25-ME-H04-0002 | FGSS_INSTRUMENT INSTALLATION DETAIL FOR PRE- HEATER | D | D | 01 | A |  | 2024-08-26 | 2024-09-10 | 2025-01-02 | 2025-01-10 | 2024-09-03 | 2024-11-04 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0473 | D | 01 | 2024-09-10 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0473 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0473 | D | 01 | 2024-09-10 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0473 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FC6B1B5FF6104304A0A8F3C48340AAC6
DDCL | CCP-W-B044-25-ME-P10-0001 | FGSS_DATA SHEET FOR VALVES (POV, MANUAL VALVE) | D | D | 01 | _ |  | 2024-09-28 | 2024-10-13 | 2025-01-05 | 2025-01-13 | 2024-10-21 | 2024-10-24 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0495 | D | 01 | 2024-10-29 | 2024-10-29 | 2024-11-08 | CCP-PGU-TRM-EPC-0495 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0495 | D | 01 | 2024-10-29 | 2024-10-29 | 2024-11-08 | CCP-PGU-TRM-EPC-0495 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4F3CFA3505BA44C484BB52951CFF80D1
DDCL | CCP-W-B044-25-ME-B05-0001 | FGSS_ASSEMBLY DRAWING FOR VALVES (POV, MANUAL VALVE) | D | D | 01 | _ |  | 2024-09-28 | 2024-10-13 | 2025-01-05 | 2025-01-13 | 2024-10-21 | 2024-10-24 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0495 | D | 01 | 2024-10-29 | 2024-10-29 | 2024-11-08 | CCP-PGU-TRM-EPC-0495 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0495 | D | 01 | 2024-10-29 | 2024-10-29 | 2024-11-08 | CCP-PGU-TRM-EPC-0495 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2197EB12CD7F4FACBE1641DC3A469757
DDCL | CCP-W-B044-25-ME-P99-0006 | FGSS-PIPING PLAN DRAWING FOR ESDV, FILTER, INTERCONNECTING AREA | D | D | 01 | _ |  | 2024-10-06 | 2024-10-21 | 2025-01-13 | 2025-01-21 | 2024-10-21 | 2024-10-24 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0495 | D | 01 | 2024-10-29 | 2024-10-29 | 2024-11-08 | CCP-PGU-TRM-EPC-0495 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0495 | D | 01 | 2024-10-29 | 2024-10-29 | 2024-11-08 | CCP-PGU-TRM-EPC-0495 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2E41BC6088FD4AE39527F0E7741B0982
DDCL | CCP-W-B044-25-ME-P99-0009 | FGSS-PIPING PLAN DRAWING FOR INTERCONNECTING BETWEEN FGSS & GT AREA | D | D | 01 | _ |  | 2024-10-06 | 2024-10-21 | 2025-01-13 | 2025-01-21 | 2024-10-21 | 2024-10-24 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0495 | D | 01 | 2024-10-29 | 2024-10-29 | 2024-11-08 | CCP-PGU-TRM-EPC-0495 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0495 | D | 01 | 2024-10-29 | 2024-10-29 | 2024-11-08 | CCP-PGU-TRM-EPC-0495 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6E1CD143A0AE42FC81EBCEEABAA66B1F
DDCL | CCP-W-B044-25-ME-P99-0007 | FGSS-PIPING PLAN DRAWING FOR METERING, HEATER, INTERCONNECTING AREA | D | D | 01 | _ |  | 2024-10-06 | 2024-10-21 | 2025-01-13 | 2025-01-21 | 2024-10-21 | 2024-10-24 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0495 | D | 01 | 2024-10-29 | 2024-10-29 | 2024-11-08 | CCP-PGU-TRM-EPC-0495 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0495 | D | 01 | 2024-10-29 | 2024-10-29 | 2024-11-08 | CCP-PGU-TRM-EPC-0495 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B75DCD4F139A44949A08241D0FC2DBFD
DDCL | CCP-W-B044-25-ME-P99-0008 | FGSS-PIPING PLAN DRAWING FOR PRV, INTERCONNECTING AREA | D | D | 01 | _ |  | 2024-10-06 | 2024-10-21 | 2025-01-13 | 2025-01-21 | 2024-10-21 | 2024-10-24 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0495 | D | 01 | 2024-10-29 | 2024-10-29 | 2024-11-08 | CCP-PGU-TRM-EPC-0495 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0495 | D | 01 | 2024-10-29 | 2024-10-29 | 2024-11-08 | CCP-PGU-TRM-EPC-0495 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8682534C8E8340479B302AD390B40A64
DDCL | CCP-W-B044-25-ME-P10-0002 | FGSS_DATA SHEET FOR RESTRICTION ORIFICE | D | D | 01 | _ |  | 2024-09-28 | 2024-10-13 | 2025-01-05 | 2025-01-13 | 2024-10-21 | 2024-10-24 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0495 | D | 01 | 2024-10-29 | 2024-10-29 | 2024-11-08 | CCP-PGU-TRM-EPC-0495 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0495 | D | 01 | 2024-10-29 | 2024-10-29 | 2024-11-08 | CCP-PGU-TRM-EPC-0495 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B8CE933FC5CA41FDBCFA43280E799565
DDCL | CCP-W-B044-25-ME-B05-0002 | FGSS_ASSEMBLY DRAWING FOR RESTRICTION ORIFICE | D | D | 01 | _ |  | 2024-09-28 | 2024-10-13 | 2025-01-05 | 2025-01-13 | 2024-10-21 | 2024-10-24 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0495 | D | 01 | 2024-10-29 | 2024-10-29 | 2024-11-08 | CCP-PGU-TRM-EPC-0495 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0495 | D | 01 | 2024-10-29 | 2024-10-29 | 2024-11-08 | CCP-PGU-TRM-EPC-0495 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D75D408C85624789814500FB9496D43D
DDCL | CCP-W-B044-25-ME-B01-1001 | FGSS_GENERAL ARRANGEMENT DRAWING FOR ESDV SKID | D | D | 01 | _ |  | 2024-10-16 | 2024-10-31 | 2025-01-23 | 2025-01-31 | 2024-10-31 | 2024-11-04 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0532 | D | 01 | 2024-11-11 | 2024-11-14 | 2024-11-24 | CCP-PGU-TRM-EPC-0532 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0532 | D | 01 | 2024-11-11 | 2024-11-14 | 2024-11-24 | CCP-PGU-TRM-EPC-0532 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4916FF94F9A249FB861A02F79938258E
DDCL | CCP-W-B044-25-ME-B01-1003 | FGSS_GENERAL ARRANGEMENT DRAWING FOR FILTER SEPARATOR SKID | D | D | 01 | _ |  | 2024-10-16 | 2024-10-31 | 2025-01-23 | 2025-01-31 | 2024-10-31 | 2024-11-04 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0532 | D | 01 | 2024-11-11 | 2024-11-14 | 2024-11-24 | CCP-PGU-TRM-EPC-0532 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0532 | D | 01 | 2024-11-11 | 2024-11-14 | 2024-11-24 | CCP-PGU-TRM-EPC-0532 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FCB84057DB6C4CDD818611B9AD9C631D
DDCL | CCP-W-B044-25-ME-B01-1002 | FGSS_GENERAL ARRANGEMENT DRAWING FOR METERING SKID | D | D | 01 | _ |  | 2024-10-16 | 2024-10-31 | 2025-01-23 | 2025-01-31 | 2024-10-31 | 2024-11-04 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0532 | D | 01 | 2024-11-11 | 2024-11-14 | 2024-11-24 | CCP-PGU-TRM-EPC-0532 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0532 | D | 01 | 2024-11-11 | 2024-11-14 | 2024-11-24 | CCP-PGU-TRM-EPC-0532 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C20628B445E84089B072D5D801F1C2F5
DDCL | CCP-W-B044-25-ME-B01-1004 | FGSS_GENERAL ARRANGEMENT DRAWING FOR PRESSURE REGULATING STATION SKID | D | D | 01 | _ |  | 2024-10-16 | 2024-10-31 | 2025-01-23 | 2025-01-31 | 2024-10-31 | 2024-11-04 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0532 | D | 01 | 2024-11-11 | 2024-11-14 | 2024-11-24 | CCP-PGU-TRM-EPC-0532 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0532 | D | 01 | 2024-11-11 | 2024-11-14 | 2024-11-24 | CCP-PGU-TRM-EPC-0532 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:EA1609E3FD8A40B8AC46F5FAD0D52087
DDCL | CCP-W-B044-25-ME-B01-1005 | FGSS_GENERAL ARRANGEMENT DRAWING FOR GAS PRE-HEATER BY-PASS VALVE SKID | D | D | 01 | _ |  | 2024-10-16 | 2024-10-31 | 2025-01-23 | 2025-01-31 | 2024-10-31 | 2024-11-04 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0532 | D | 01 | 2024-11-11 | 2024-11-14 | 2024-11-24 | CCP-PGU-TRM-EPC-0532 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0532 | D | 01 | 2024-11-11 | 2024-11-14 | 2024-11-24 | CCP-PGU-TRM-EPC-0532 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3E8655B8427944DA927D6292EE4C55DB
DDCL | CCP-W-B044-25-ME-B01-1006 | FGSS_GENERAL ARRANGEMENT DRAWING FOR PERFORMANCE HEATER SKID | D | D | 01 | _ |  | 2024-10-16 | 2024-10-31 | 2025-01-23 | 2025-01-31 | 2024-10-31 | 2024-11-04 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0532 | D | 01 | 2024-11-11 | 2024-11-14 | 2024-11-24 | CCP-PGU-TRM-EPC-0532 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0532 | D | 01 | 2024-11-11 | 2024-11-14 | 2024-11-24 | CCP-PGU-TRM-EPC-0532 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6C99B0FF43E54EE99518E167458B1D5B
DDCL | CCP-W-B044-25-ME-B01-1007 | FGSS_GENERAL ARRANGEMENT DRAWING FOR FINAL CHANCE FILTER SKID | D | D | 01 | _ |  | 2024-10-16 | 2024-10-31 | 2025-01-23 | 2025-01-31 | 2024-10-31 | 2024-11-04 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0532 | D | 01 | 2024-11-11 | 2024-11-14 | 2024-11-24 | CCP-PGU-TRM-EPC-0532 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0532 | D | 01 | 2024-11-11 | 2024-11-14 | 2024-11-24 | CCP-PGU-TRM-EPC-0532 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E28A0F47F27A44B0B2C651494FE66C6D
DDCL | CCP-W-B044-25-ME-P05-0001 | FGSS_VALVE LIST | D | D | 01 | _ |  | 2024-10-16 | 2024-10-31 | 2025-01-23 | 2025-01-31 | 2024-10-31 | 2024-11-04 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0532 | D | 01 | 2024-11-11 | 2024-11-14 | 2024-11-24 | CCP-PGU-TRM-EPC-0532 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0532 | D | 01 | 2024-11-11 | 2024-11-14 | 2024-11-24 | CCP-PGU-TRM-EPC-0532 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:654B0E0BC8574D80AEF94039C35A91F7
DDCL | CCP-W-B044-25-ME-P02-0001 | FGSS_PIPING SUPPORT STANDARD DRAWING | D | D | 01 | _ |  | 2024-10-16 | 2024-10-31 | 2025-01-23 | 2025-01-31 | 2024-10-31 | 2024-11-04 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0532 | D | 01 | 2024-11-11 | 2024-11-14 | 2024-11-24 | CCP-PGU-TRM-EPC-0532 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0532 | D | 01 | 2024-11-11 | 2024-11-14 | 2024-11-24 | CCP-PGU-TRM-EPC-0532 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E7BE71C1F2E3452EA127575B2A9D6227
DDCL | CCP-W-B044-25-ME-P02-0003 | FGSS_PIPING SUPPORT DETAIL DRAWING (GT AREA) | D | D | 01 | _ |  | 2024-10-16 | 2024-10-31 | 2025-01-23 | 2025-01-31 | 2024-10-31 | 2024-11-04 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0532 | D | 01 | 2024-11-11 | 2024-11-14 | 2024-11-24 | CCP-PGU-TRM-EPC-0532 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0532 | D | 01 | 2024-11-11 | 2024-11-14 | 2024-11-24 | CCP-PGU-TRM-EPC-0532 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CA31716BFBDA496D985E12E4A115C820
DDCL | CCP-W-B044-25-ME-P02-0002 | FGSS_PIPING SUPPORT DETAIL DRAWING (FGSS AREA) | D | D | 01 | _ |  | 2024-10-16 | 2024-10-31 | 2025-01-23 | 2025-01-31 | 2024-10-31 | 2024-11-04 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0532 | D | 01 | 2024-11-11 | 2024-11-14 | 2024-11-24 | CCP-PGU-TRM-EPC-0532 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0532 | D | 01 | 2024-11-11 | 2024-11-14 | 2024-11-24 | CCP-PGU-TRM-EPC-0532 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:23D881DABA03463EB2B7458890F73E09
DDCL | CCP-W-B044-25-ME-B05-0003 | FGSS_DATA SHEET & ASSEMBLY DRAWING FOR EMERGENCY SHUT DOWN VALVE | D | D | 01 | _ |  | 2024-10-17 | 2024-11-01 | 2025-01-24 | 2025-02-01 | 2024-11-01 | 2024-11-04 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0533 | D | 01 | 2024-11-11 | 2024-11-14 | 2024-11-24 | CCP-PGU-TRM-EPC-0533 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0533 | D | 01 | 2024-11-11 | 2024-11-14 | 2024-11-24 | CCP-PGU-TRM-EPC-0533 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C0C89705C2F041D7B2796EE80B353808
DDCL | CCP-W-B044-25-ME-P01-0001 | FGSS_PIPING ISO FOR FGSS AREA (INSIDE SKID) | D | D | 01 | _ |  | 2024-12-26 | 2025-01-10 | 2025-04-02 | 2025-04-10 | 2025-01-09 | 2025-02-03 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0851 | D | 01 | 2025-02-03 | 2025-02-05 | 2025-02-10 | CCP-PGU-TRM-EPC-0851 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0851 | D | 01 | 2025-02-03 | 2025-02-05 | 2025-02-10 | CCP-PGU-TRM-EPC-0851 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A49EA90631F64355AA73017773A2E475
DDCL | CCP-W-B044-25-ME-P01-0003 | FGSS_PIPING ISO FOR FGSS AREA (OUTSIDE SKID) | D | D | 01 | _ |  | 2024-12-26 | 2025-01-10 | 2025-04-02 | 2025-04-10 | 2025-01-09 | 2025-02-03 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0851 | D | 01 | 2025-02-03 | 2025-02-05 | 2025-02-10 | CCP-PGU-TRM-EPC-0851 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0851 | D | 01 | 2025-02-03 | 2025-02-05 | 2025-02-10 | CCP-PGU-TRM-EPC-0851 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:EC9A2D8944A6423DB53B8F4594FA3839
DDCL | CCP-W-B044-25-ME-P01-0002 | FGSS_PIPING ISO FOR GT AREA (INSIDE SKID) | D | D | 01 | _ |  | 2024-12-26 | 2025-01-10 | 2025-04-02 | 2025-04-10 | 2025-01-09 | 2025-02-03 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0851 | D | 01 | 2025-02-03 | 2025-02-05 | 2025-02-10 | CCP-PGU-TRM-EPC-0851 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0851 | D | 01 | 2025-02-03 | 2025-02-05 | 2025-02-10 | CCP-PGU-TRM-EPC-0851 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:38C10AEB14C44633A42E31E0F2B17289
DDCL | CCP-W-B044-25-ME-P01-0004 | FGSS_PIPING ISO FOR GT AREA (OUTSIDE SKID) | D | D | 01 | _ |  | 2024-12-26 | 2025-01-10 | 2025-04-02 | 2025-04-10 | 2025-01-09 | 2025-02-03 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0851 | D | 01 | 2025-02-03 | 2025-02-05 | 2025-02-10 | CCP-PGU-TRM-EPC-0851 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0851 | D | 01 | 2025-02-03 | 2025-02-05 | 2025-02-10 | CCP-PGU-TRM-EPC-0851 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7737ED5579994CC4A2BD51C201AEBCF8
DDCL | CCP-W-B044-25-ME-H99-0005 | FGSS_INSTRUMENT LIST | D | D | 01 | _ |  | 2025-02-12 | 2025-02-27 | 2025-05-20 | 2025-05-27 | 2025-02-27 | 2025-02-27 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0861 | D | 01 | 2025-02-27 | 2025-03-06 | 2025-03-17 | CCP-PGU-TRM-EPC-0861 | D | 01 | Deemed approved | CCP-EPC-TRM-PGU-0861 | D | 01 | 2025-02-27 | 2025-03-06 | 2025-03-17 | CCP-PGU-TRM-EPC-0861 | Deemed approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:065119DDF725409896EB9AF740972CE2
DDCL | CCP-W-B044-25-ME-H07-0001 | FGSS_PLAN FOR CABLE ROUTING | D | D | 01 | _ |  | 2025-04-15 | 2025-04-30 | 2025-08-22 | 2025-08-30 | 2025-04-24 | 2025-04-24 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8FF891A107A146ABAD84CE59A9371C31
DDCL | CCP-W-B044-25-ME-H99-0008 | FGSS ANALYZER SAMPLING SYSTEM DRAWING | D | D | 01 | _ |  | 2024-02-14 | 2024-02-28 | 2024-05-23 | 2024-05-30 | 2024-01-29 | 2024-06-27 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0229 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0229 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0229 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0229 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3164DFD15DE4475BB6F0D053CFF62F57
DDCL | CCP-W-B044-25-ME-K07-0001 | FGSS_CABLE SCHEDULE AND LIST | D | D | 01 | _ |  | 2024-02-07 | 2024-02-28 | 2024-04-30 | 2024-05-30 | 2024-07-11 | 2024-07-11 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0258 | D | 01 | 2024-07-11 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0258 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0258 | D | 01 | 2024-07-11 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0258 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:026F7D57FED1447BAD74803723950779
DDCL | CCP-W-B044-25-ME-H21-0001 | FGSS_INSTRUMENT DATA SHEET & SPECIFICATION | D | D | 01 | _ |  | 2024-01-24 | 2024-02-28 | 2024-04-30 | 2024-05-30 | 2024-05-24 | 2024-06-27 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0229 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0229 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0229 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0229 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:85FE1F76AC524B1AAECD6AD298D1D354
DDCL | CCP-W-B044-25-ME-H04-0001 | FGSS_INSTRUMENT INSTALLATION DRAWING | D | D | 01 | _ |  | 2024-05-15 | 2024-05-30 | 2024-09-01 | 2024-09-30 | 2024-09-12 | 2024-09-13 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0495 | D | 01 | 2024-10-29 | 2024-10-29 | 2024-11-08 | CCP-PGU-TRM-EPC-0495 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0495 | D | 01 | 2024-10-29 | 2024-10-29 | 2024-11-08 | CCP-PGU-TRM-EPC-0495 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:0A9D089EAB3F44D5AB0DD27C0721B546
DDCL | CCP-W-B044-25-ME-E03-0001 | FGSS_INTERCONNECTION WIRING DIAGRAM | D | D | 01 | _ |  | 2024-03-20 | 2024-03-30 | 2024-05-30 | 2024-06-30 | 2024-07-11 | 2024-07-11 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0258 | D | 01 | 2024-07-11 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0258 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0258 | D | 01 | 2024-07-11 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0258 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:117D4E22471A463AAB79564F21791875
DDCL | CCP-W-B044-25-ME-B04-0001 | FGSS_JUNCTION BOX OUTLINE DRAWING | D | D | 01 | _ |  | 2024-07-10 | 2024-07-30 | 2024-09-30 | 2024-10-30 | 2024-10-22 | 2025-01-10 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0837 | D | 01 | 2025-01-10 | 2025-01-15 | 2025-01-25 | CCP-PGU-TRM-EPC-0837 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0837 | D | 01 | 2025-01-10 | 2025-01-15 | 2025-01-25 | CCP-PGU-TRM-EPC-0837 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D31B5330C62246DBA6066E2E2649DDAA
DDCL | CCP-W-B044-25-ME-B33-0001 | FGSS_FOUNDATION DRAWING INCLUDING LOADINGS (VENDOR PACKAGE) | D | D | 01 | _ |  | 2024-03-30 | 2024-04-30 | 2024-06-30 | 2024-07-30 | 2024-07-11 | 2024-07-11 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0258 | D | 01 | 2024-07-11 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0258 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0258 | D | 01 | 2024-07-11 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0258 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:17B4FF2EEFDC45569D5160245C12CF1F
DDCL | CCP-W-B044-25-ME-P14-0001 | FGSS_LINE LIST | D | D | 01 | _ |  | 2024-01-12 | 2024-01-30 | 2024-03-30 | 2024-04-30 | 2024-07-11 | 2024-07-11 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0258 | D | 01 | 2024-07-11 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0258 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0258 | D | 01 | 2024-07-11 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0258 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:0380487CCCF64ADAAA46761655FC384C
DDCL | CCP-W-B044-25-ME-B01-0003 | FGSS_OUTLINE DRAWING FOR GAS PRESSURE REGULATING STATION | D | D | 01 | _ |  | 2024-04-17 | 2024-04-30 | 2024-08-23 | 2024-08-30 | 2024-05-24 | 2024-06-27 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0473 | D | 01 | 2024-09-10 | 2024-09-11 | 2024-07-12 | CCP-PGU-TRM-EPC-0228 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0228 CCP-EPC-TRM-PGU-0473 | D | 01 | 2024-06-28 2024-09-10 | 2024-07-02 2024-09-11 | 2024-07-12 | CCP-PGU-TRM-EPC-0228 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:0B6C96713E04453F83431A8AE93042B2
DDCL | CCP-W-B044-25-ME-B01-0004 | FGSS_OUTLINE DRAWING FOR GAS PRE-HEATER | D | D | 01 | _ |  | 2024-05-15 | 2024-05-30 | 2024-07-30 | 2024-08-30 | 2024-08-20 | 2024-09-04 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0496 | D | 01 | 2024-10-29 | 2024-10-29 | 2024-11-08 | CCP-PGU-TRM-EPC-0496 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0496 | D | 01 | 2024-10-29 | 2024-10-29 | 2024-11-08 | CCP-PGU-TRM-EPC-0496 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:9C05A3BA1B1C4C9C8FAFFF9479563AFA
DDCL | CCP-W-B044-25-ME-B01-0005 | FGSS_OUTLINE DRAWING FOR FUEL GAS CONDENSATE TANK | D | D | 01 | _ |  | 2024-02-29 | 2024-03-30 | 2024-05-31 | 2024-06-30 | 2024-06-18 | 2024-06-27 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0228 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0228 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0228 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0228 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:60D0A7FF7CA84AE099355F017660B6B8
DDCL | CCP-W-B044-25-ME-B01-0006 | FGSS_OUTLINE DRAWING FOR FUEL GAS PERFORMANCE HEATER | D | D | 01 | _ |  | 2024-02-21 | 2024-03-30 | 2024-05-30 | 2024-06-30 | 2024-06-18 | 2024-06-27 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0228 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0228 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0228 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0228 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:EBFBFE4A928F497E959CA9933617BE00
DDCL | CCP-W-B044-25-ME-B01-0007 | FGSS_OUTLINE DRAWING FOR FUEL CONDENSATE PUMPS | D | D | 01 | _ |  | 2024-02-21 | 2024-02-28 | 2024-05-30 | 2024-06-30 | 2024-10-22 | 2024-11-11 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0530 | D | 01 | 2024-11-11 | 2024-11-14 | 2024-11-24 | CCP-PGU-TRM-EPC-0530 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0530 | D | 01 | 2024-11-11 | 2024-11-14 | 2024-11-24 | CCP-PGU-TRM-EPC-0530 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:99943F17C35E49ADADD28C109EB0B6F8
DDCL | CCP-W-B044-25-ME-B01-0008 | FGSS_OUTLINE DRAWING FOR COLD VENT STACK | D | D | 01 | _ |  | 2024-02-21 | 2024-03-30 | 2024-05-30 | 2024-06-30 | 2024-08-20 | 2024-09-03 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0458 | D | 01 | 2024-09-03 | 2024-09-06 | 2024-09-16 | CCP-PGU-TRM-EPC-0458 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0458 | D | 01 | 2024-09-03 | 2024-09-06 | 2024-09-16 | CCP-PGU-TRM-EPC-0458 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7D65F66449484222BD80C65123E2491B
DDCL | CCP-W-B044-25-ME-H05-0001 | FGSS_CONTROL CABINET LAYOUT DRAWING | D | D | 01 | _ |  | 2024-02-29 | 2024-03-30 | 2024-05-30 | 2024-06-30 | 2024-10-22 | 2025-01-10 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0837 | D | 01 | 2025-01-10 | 2025-01-15 | 2025-01-25 | CCP-PGU-TRM-EPC-0837 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0837 | D | 01 | 2025-01-10 | 2025-01-15 | 2025-01-25 | CCP-PGU-TRM-EPC-0837 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FB830C4760424867B00D8153315ADD92
DDCL | CCP-W-B044-25-ME-H09-0001 | FGSS_CONTROL LOGIC AND LOOP DIAGRAM | D | D | 01 | _ |  | 2024-02-16 | 2024-03-30 | 2024-05-30 | 2024-06-30 | 2024-10-22 | 2025-01-10 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0837 | D | 01 | 2025-01-10 | 2025-01-15 | 2025-01-25 | CCP-PGU-TRM-EPC-0837 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0837 | D | 01 | 2025-01-10 | 2025-01-15 | 2025-01-25 | CCP-PGU-TRM-EPC-0837 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A73D962AB35E4478984524ACFE704E2E
DDCL | CCP-W-B044-25-ME-E13-0001 | FGSS_POWER SUPPLY DISTRIBUTION DRAWING INCLUDING SINGLE LINE DIAGRAM | D | D | 01 | _ |  | 2024-02-16 | 2024-03-30 | 2024-05-30 | 2024-06-30 | 2024-07-11 | 2024-07-11 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0258 | D | 01 | 2024-07-11 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0258 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0258 | D | 01 | 2024-07-11 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0258 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5BBFEBB5C3454519AC818DA6F81F7A85
DDCL | CCP-W-B044-25-ME-K14-0001 | FGSS_HARDWIRED IO LIST | D | D | 01 | _ |  | 2024-02-29 | 2024-03-30 | 2024-05-31 | 2024-06-30 | 2024-06-03 | 2024-06-27 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0229 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0229 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0229 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0229 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:49BE4078E9DA4D25B4BFC131095CDC5B
DDCL | CCP-W-B044-25-ME-K14-0002 | FGSS_DATA LINK IO LIST (MODBUS MAPPING LIST) | D | D | 01 | _ |  | 2024-02-29 | 2024-03-30 | 2024-05-31 | 2024-06-30 | 2024-10-22 | 2025-01-10 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0837 | D | 01 | 2025-01-10 | 2025-01-15 | 2025-01-25 | CCP-PGU-TRM-EPC-0837 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0837 | D | 01 | 2025-01-10 | 2025-01-15 | 2025-01-25 | CCP-PGU-TRM-EPC-0837 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:EB360906F2D943CAB543A3BAB8DCEF64
DDCL | CCP-W-B044-25-ME-B16-0001 | FGSS_EQUIPMENT DATA SHEET FOR FUEL GAS ANALYZER | D | D | 01 | _ |  | 2024-01-02 | 2024-01-30 | 2024-03-30 | 2024-04-30 | 2024-04-02 | 2024-06-27 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0228 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0228 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0228 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0228 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B6FCC5B7F1DD48ABA774AEA32905A402
DDCL | CCP-W-B044-25-ME-B16-0002 | FGSS_EQUIPMENT DATA SHEET FOR FILTER SEPERATOR AND FINAL CHANCE FILTER | D | D | 01 | _ |  | 2024-02-29 | 2024-03-30 | 2024-05-31 | 2024-06-30 | 2024-06-18 | 2024-06-27 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0228 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0228 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0228 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0228 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E34E0FD49BFF4A9E8C1F3364AD830A80
DDCL | CCP-W-B044-25-ME-B16-0003 | FGSS_EQUIPMENT DATA SHEET FOR GAS PRESSURE REGULATING STATION | D | D | 01 | _ |  | 2024-02-29 | 2024-03-30 | 2024-05-31 | 2024-06-30 | 2024-06-03 | 2024-06-27 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0228 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0228 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0228 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0228 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3E4C94AECC0248FF976F8853BBDBB360
DDCL | CCP-W-B044-25-ME-B16-0004 | FGSS_EQUIPMENT DATA SHEET FOR GAS PRE-HEATER | D | D | 01 | _ |  | 2024-02-29 | 2024-03-30 | 2024-05-31 | 2024-06-30 | 2024-07-11 | 2024-09-04 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0473 | D | 01 | 2024-09-10 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0473 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0473 | D | 01 | 2024-09-10 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0473 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:38E59B1B53034AE28E4BBE3E7D8869EE
DDCL | CCP-W-B044-25-ME-B16-0005 | FGSS_EQUIPMENT DATA SHEET FOR FUEL GAS CONDENSATE TANK | D | D | 01 | _ |  | 2024-02-16 | 2024-03-30 | 2024-05-30 | 2024-06-30 | 2024-06-18 | 2024-06-27 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0228 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0228 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0228 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0228 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:240ECDE9E21B47A08A5AA379A10B6B9B
DDCL | CCP-W-B044-25-ME-B16-0006 | FGSS_EQUIPMENT DATA SHEET FOR FUEL GAS PERFORMANCE HEATER | D | D | 01 | _ |  | 2024-02-29 | 2024-03-30 | 2024-05-30 | 2024-06-30 | 2024-06-18 | 2024-06-27 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0228 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0228 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0228 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0228 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B391EE3F79E94FD5B743937D08BA6286
DDCL | CCP-W-B044-25-ME-B16-0007 | FGSS_EQUIPMENT DATA SHEET FOR FUEL GAS CONDENSATE PUMPS | D | D | 01 | _ |  | 2024-02-16 | 2024-03-30 | 2024-05-30 | 2024-06-30 | 2024-10-22 | 2024-11-11 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0530 | D | 01 | 2024-11-11 | 2024-11-14 | 2024-11-24 | CCP-PGU-TRM-EPC-0530 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0530 | D | 01 | 2024-11-11 | 2024-11-14 | 2024-11-24 | CCP-PGU-TRM-EPC-0530 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:DAEB32B266E4471BA909135F2919A19B
DDCL | CCP-W-B044-25-ME-B16-0008 | FGSS_EQUIPMENT DATA SHEET AND DRAWING FOR PRESSURE SAFETY VALVE | D | D | 01 | _ |  | 2024-02-29 | 2024-03-30 | 2024-05-30 | 2024-06-30 | 2024-10-18 | 2024-10-24 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0495 | D | 01 | 2024-10-29 | 2024-10-29 | 2024-11-08 | CCP-PGU-TRM-EPC-0495 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0495 | D | 01 | 2024-10-29 | 2024-10-29 | 2024-11-08 | CCP-PGU-TRM-EPC-0495 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CF7770AB342843B0BD192CF3859A4EF8
DDCL | CCP-W-B044-25-ME-B01-0001 | FGSS_OUTLINE DRAWING FOR FUEL GAS ANALYZER CABINET | D | D | 01 | _ |  | 2024-02-29 | 2024-03-30 | 2024-05-31 | 2024-06-30 | 2024-03-28 | 2024-06-27 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0228 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0228 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0228 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0228 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A4EC0C85BE214F7E9637D70D9892BDA0
DDCL | CCP-W-B044-25-ME-B01-0002 | FGSS_OUTLINE DRAWING FOR FILTER SEPERATOR AND FINAL CHANCE FILTER | D | D | 01 | _ |  | 2024-02-29 | 2024-03-30 | 2024-05-31 | 2024-06-30 | 2024-06-18 | 2024-06-27 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0228 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0228 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0228 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0228 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:9C1F1A3D6C414D62A516F225777B109E
DDCL | CCP-W-B113-03-ME-B01-0025 | STG_Line and Neutral Cubicles Outline | D | D | 01 | _ |  | 2024-05-16 | 2024-05-30 | 2024-08-23 | 2024-08-30 | 2024-04-30 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CBE8E0DFB85C4510BD46B842CA06B8B3
DDCL | CCP-W-B113-03-ME-B33-0001 | STG_Foundation - Shape & Anchoring | D | D | 01 | _ |  | 2024-01-07 | 2024-02-06 | 2024-04-30 | 2024-05-30 | 2024-02-02 | 2024-06-10 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0174 | D | 01 | 2024-06-10 | 2024-06-11 | 2024-06-21 | CCP-PGU-TRM-EPC-0174 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0174 | D | 01 | 2024-06-10 | 2024-06-11 | 2024-06-21 | CCP-PGU-TRM-EPC-0174 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:9DBEA8F42B3C49BD808187A74F9F08D4
DDCL | CCP-W-B113-03-ME-B33-0002 | STG_Foundation - Embedded Elements | D | D | 01 | _ |  | 2024-01-26 | 2024-02-25 | 2024-04-30 | 2024-05-30 | 2024-02-02 | 2024-06-10 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0174 | D | 01 | 2024-06-10 | 2024-06-11 | 2024-06-21 | CCP-PGU-TRM-EPC-0174 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0174 | D | 01 | 2024-06-10 | 2024-06-11 | 2024-06-21 | CCP-PGU-TRM-EPC-0174 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B863E18CDD0E437E9B466C0C0327BA4B
DDCL | CCP-W-B113-03-ME-B33-0003 | STG_Foundation Design Criteria | D | C | 01 | _ |  | 2023-09-28 | 2023-10-28 | 2024-03-16 | 2024-04-15 | 2023-10-24 | 2023-12-05 | 2024-03-18 | 2024-05-07 | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0138 | C | 01 | 2024-05-07 | 2024-05-07 | 2024-05-22 | CCP-PGU-TRM-EPC-0138 | C | 01 | Approved with comment | CCP-EPC-TRM-PGU-0079 | D | 01 | 2023-12-05 | 2023-12-05 |  |  |  | CCP-EPC-TRM-PGU-0138 | C | 01 | 2024-05-07 | 2024-05-07 | 2024-05-22 | CCP-PGU-TRM-EPC-0138 | Approved with comment | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:043B6220CAD14471B6B6AC2DFCCEAE19
DDCL | CCP-W-B113-03-ME-B04-0004 | STG_Auxiliary Steel Structures | D | D | 01 | _ | FC DELAY | 2024-08-23 | 2024-09-22 | 2024-09-27 | 2024-10-27 | 2024-12-20 | 2024-12-20 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0741 | D | 01 | 2024-12-20 | 2024-12-30 | 2025-01-09 | CCP-PGU-TRM-EPC-0741 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0741 | D | 01 | 2024-12-20 | 2024-12-30 | 2025-01-09 | CCP-PGU-TRM-EPC-0741 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:03F4B223CF9E45268DF6D226225A125A
DDCL | CCP-W-B113-03-ME-B06-0005 | STG_P&I Diagrams for Steam-water | D | D | 01 | _ |  | 2024-01-08 | 2024-02-07 | 2024-05-15 | 2024-06-14 | 2024-01-23 | 2024-01-23 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0088 | D | 01 | 2024-01-18 | 2024-01-18 | 2024-02-15 | CCP-PGU-TRM-EPC-0088 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0088 | D | 01 | 2024-01-18 | 2024-01-18 | 2024-02-15 | CCP-PGU-TRM-EPC-0088 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:125284F8E07E4A7682C821B7C0D60A6C
DDCL | CCP-W-B113-03-ME-B06-0006 | STG_P&I Diagrams for Lubrication Oil System | D | D | 01 | _ |  | 2024-01-08 | 2024-02-07 | 2024-05-15 | 2024-06-14 | 2024-01-23 | 2024-01-23 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0088 | D | 01 | 2024-01-18 | 2024-01-18 | 2024-02-15 | CCP-PGU-TRM-EPC-0088 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0088 | D | 01 | 2024-01-18 | 2024-01-18 | 2024-02-15 | CCP-PGU-TRM-EPC-0088 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:ADC8F2916AE54A46883C98241A4CFEC1
DDCL | CCP-W-B113-03-ME-B06-0007 | STG_P&I Diagrams for Control Oil System | D | D | 01 | _ |  | 2024-01-08 | 2024-02-07 | 2024-05-15 | 2024-06-14 | 2024-01-23 | 2024-01-23 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0088 | D | 01 | 2024-01-18 | 2024-01-18 | 2024-02-15 | CCP-PGU-TRM-EPC-0088 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0088 | D | 01 | 2024-01-18 | 2024-01-18 | 2024-02-15 | CCP-PGU-TRM-EPC-0088 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:238073EA06594E9FA951B7B2059C9E34
DDCL | CCP-W-B113-03-ME-B06-0008 | STG_P&I Diagrams for Generator | D | D | 01 | _ |  | 2024-01-08 | 2024-02-07 | 2024-05-15 | 2024-06-14 | 2024-04-08 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1BE034331EF248C8A61C18011CBFCD13
DDCL | CCP-W-B113-03-ME-B33-0008 | STG_Foundation load plan | D | D | 01 | _ |  | 2024-01-26 | 2024-02-25 | 2024-04-30 | 2024-05-30 | 2024-02-21 | 2024-06-10 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0174 | D | 01 | 2024-06-10 | 2024-06-11 | 2024-06-21 | CCP-PGU-TRM-EPC-0174 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0174 | D | 01 | 2024-06-10 | 2024-06-11 | 2024-06-21 | CCP-PGU-TRM-EPC-0174 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2162F447F12C4067B972E4A659508EC2
DDCL | CCP-W-B113-03-ME-D14-0009 | STG_Loads plan - Levels | D | D | 01 | _ |  | 2023-12-27 | 2024-01-26 | 2024-06-29 | 2024-07-29 | 2024-05-29 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6DCAC095DAAB4F01AC794BB399C7F3BF
DDCL | CCP-W-B113-03-ME-D14-0010 | STG_Lay down plan | D | D | 01 | _ |  | 2023-12-05 | 2024-01-04 | 2024-04-30 | 2024-05-30 | 2024-03-04 | 2024-03-05 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0098 | D | 01 | 2024-03-05 | 2024-03-05 | 2024-03-18 | CCP-PGU-EPC-TRM-0098 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0098 | D | 01 | 2024-03-05 | 2024-03-05 | 2024-03-18 | CCP-PGU-EPC-TRM-0098 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:EF8CF8C77BB146B287D777B919282787
DDCL | CCP-W-B113-03-ME-B01-0011 | STG_General Layout Plan for STG and Auxiliaries | D | D | 01 | _ |  | 2024-01-07 | 2024-02-06 | 2024-07-14 | 2024-08-13 | 2024-03-06 | 2024-05-07 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0139 | D | 01 | 2024-05-07 | 2024-05-07 | 2024-05-17 | CCP-PGU-TRM-EPC-0139 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0139 | D | 01 | 2024-05-07 | 2024-05-07 | 2024-05-17 | CCP-PGU-TRM-EPC-0139 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B7301A4B118D4F0F9E4ACF454AA1E255
DDCL | CCP-W-B113-03-ME-B01-0012 | STG_General Arrangement Drawing-Longitudinal section | D | D | 01 | _ |  | 2023-12-27 | 2024-01-26 | 2024-04-30 | 2024-05-30 | 2024-03-15 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8E7FA0E410E34C42918007335378A68E
DDCL | CCP-W-B113-03-ME-B01-0014 | STG_Steam Turbine Mechanical Outline and Assembly | D | D | 01 | _ |  | 2024-01-11 | 2024-02-10 | 2024-07-14 | 2024-08-13 | 2024-04-01 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:809C1DAC0D224BA3A99BEB8392ECEA22
DDCL | CCP-W-B113-03-ME-B01-0015 | STG_Main Stop Valve / Control Valve Outline and Assembly (including blowing inserts and cover) | D | D | 01 | _ |  | 2024-01-11 | 2024-02-10 | 2024-07-14 | 2024-08-13 | 2024-03-06 | 2024-05-07 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0139 | D | 01 | 2024-05-07 | 2024-05-07 | 2024-05-17 | CCP-PGU-TRM-EPC-0139 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0139 | D | 01 | 2024-05-07 | 2024-05-07 | 2024-05-17 | CCP-PGU-TRM-EPC-0139 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A1B9DF89598D4F5AAFA1E467CE622D5D
DDCL | CCP-W-B113-03-ME-B01-0016 | STG_Vent Steam Condenser Outline and Foundation (including exhasuter fan) | D | D | 01 | _ |  | 2024-01-11 | 2024-02-10 | 2024-07-14 | 2024-08-13 | 2024-03-06 | 2024-05-07 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0139 | D | 01 | 2024-05-07 | 2024-05-07 | 2024-05-17 | CCP-PGU-TRM-EPC-0139 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0139 | D | 01 | 2024-05-07 | 2024-05-07 | 2024-05-17 | CCP-PGU-TRM-EPC-0139 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A5DCAAE2D47147D280194896C45BFEE1
DDCL | CCP-W-B113-03-ME-B01-0017 | STG_Lube Oil Skid Outline and Foundation | D | D | 01 | _ |  | 2024-01-11 | 2024-02-10 | 2024-07-14 | 2024-08-13 | 2024-03-04 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:76C6E4FF1ECF4B23A9B5CA9BB707281A
DDCL | CCP-W-B113-03-ME-B01-0019 | STG_Vacuum Flash Tank and Pump Outline | D | D | 01 | _ |  | 2024-01-11 | 2024-02-10 | 2024-07-14 | 2024-08-13 | 2024-05-29 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:495687679FDA45AE898B4852895DB0D7
DDCL | CCP-W-B113-03-ME-B16-0020 | STG_Specification of Lube Oil Heater | D | D | 01 | _ |  | 2024-04-25 | 2024-05-25 | 2024-06-30 | 2024-07-30 | 2024-06-07 | 2024-07-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0259 | D | 01 | 2024-07-12 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0259 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0259 | D | 01 | 2024-07-12 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0259 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2254ECF4554F4A5DBF1127329255B62D
DDCL | CCP-W-B113-03-ME-B01-0021 | STG_Turning Gear Outline and Motor Detail | D | D | 01 | _ |  | 2024-01-11 | 2024-02-10 | 2024-07-14 | 2024-08-13 | 2024-05-29 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:451F35E4F7E9473387CB06DB752DDEF6
DDCL | CCP-W-B113-03-ME-B16-0022 | STG_Specification for Steam Turbine | D | D | 01 | _ |  | 2023-12-19 | 2024-01-18 | 2024-02-15 | 2024-03-16 | 2024-06-12 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:537ADDEBCA444D5A9D5930E4CBDCE8CD
DDCL | CCP-W-B113-03-ME-B01-0023 | STG_Generator Outline | D | D | 01 | _ |  | 2024-01-11 | 2024-02-10 | 2024-06-29 | 2024-07-29 | 2024-04-30 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:495532FE78684A3CA415D42A389BF997
DDCL | CCP-W-B113-03-ME-B01-0024 | STG_Excitation system Outline and Foundation | D | D | 01 | _ |  | 2024-01-11 | 2024-02-10 | 2024-06-29 | 2024-07-29 | 2024-03-04 | 2024-03-05 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0098 | D | 01 | 2024-03-05 | 2024-03-05 | 2024-03-18 | CCP-PGU-TRM-EPC-0098 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0098 | D | 01 | 2024-03-05 | 2024-03-05 | 2024-03-18 | CCP-PGU-TRM-EPC-0098 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:47C1003711B74ABD87034ED39087D58F
DDCL | CCP-W-B113-03-ME-E02-0027 | STG_Schematic, Connection Diagram of Excitation Control Panel | D | D | 01 | _ |  | 2024-06-18 | 2024-07-18 | 2024-07-19 | 2024-08-18 | 2024-07-15 | 2024-07-16 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0267 | D | 01 | 2024-07-16 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0267 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0267 | D | 01 | 2024-07-16 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0267 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D6C4E55677D545F8B83643E1E8BCD394
DDCL | CCP-W-B113-03-ME-E02-0028 | STG_Schematic, Connection Diagram of STG Neutral Grounding Transformer Cubicle and Main terminal box | D | D | 01 | _ |  | 2024-06-18 | 2024-07-18 | 2024-07-19 | 2024-08-18 | 2024-07-15 | 2024-07-16 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0267 | D | 01 | 2024-07-16 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0267 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0267 | D | 01 | 2024-07-16 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0267 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6DA03A89CF9E4D0E93150809C7CEF717
DDCL | CCP-W-B113-03-ME-E02-0029 | STG_Schematic, Connection Diagram of generator protection | D | D | 01 | _ |  | 2024-06-18 | 2024-07-18 | 2024-07-19 | 2024-08-18 | 2024-07-15 | 2024-07-16 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0267 | D | 01 | 2024-07-16 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0267 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0267 | D | 01 | 2024-07-16 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0267 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E59F638F24214E59A080A9C0EEC53152
DDCL | CCP-W-B113-03-ME-E02-0030 | STG_Schematic, Connection Diagram of Synchronization/Measurement Panel | D | D | 01 | _ |  | 2024-06-18 | 2024-07-18 | 2024-07-19 | 2024-08-18 | 2024-07-15 | 2024-07-16 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0267 | D | 01 | 2024-07-16 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0267 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0267 | D | 01 | 2024-07-16 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0267 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:9DAB95C7119C4727AA115E8167C6B942
DDCL | CCP-W-B113-03-ME-E02-0031 | STG_Schematic and Connection Diagram, SLD of DC motor starter | D | D | 01 | _ |  | 2024-06-18 | 2024-07-18 | 2024-07-19 | 2024-08-18 | 2024-07-15 | 2024-07-16 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0267 | D | 01 | 2024-07-16 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0267 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0267 | D | 01 | 2024-07-16 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0267 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5C0ECEDA805549B684F0737666AA8F8C
DDCL | CCP-W-B113-03-ME-E02-0032 | STG_Schematic and Connection Diagram, SLD of frequency converter | D | D | 01 | _ |  | 2024-06-18 | 2024-07-18 | 2024-07-19 | 2024-08-18 | 2024-07-15 | 2024-07-16 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0267 | D | 01 | 2024-07-16 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0267 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0267 | D | 01 | 2024-07-16 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0267 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:447CF8E57C754E22BCB597BA691B2E7C
DDCL | CCP-W-B113-03-ME-B01-0033 | STG_Genrator Protection Outline | D | D | 01 | _ |  | 2023-12-19 | 2024-01-18 | 2024-10-12 | 2024-11-11 | 2024-03-04 | 2024-03-05 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0098 | D | 01 | 2024-03-05 | 2024-03-05 | 2024-03-18 | CCP-PGU-EPC-TRM-0098 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0098 | D | 01 | 2024-03-05 | 2024-03-05 | 2024-03-18 | CCP-PGU-EPC-TRM-0098 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:661D2B3B35CC4A0FBA28A49676CDEC29
DDCL | CCP-W-B113-03-ME-P14-0034 | STG_Piping System Design Data and Line List | D | D | 01 | _ |  | 2024-01-26 | 2024-02-25 | 2024-05-15 | 2024-06-14 | 2024-04-25 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D3C1136E3F514815B73A5AADC25F0184
DDCL | CCP-W-B113-03-ME-P10-0035 | STG_Pneumatic, Motor and Manual Valve List (Including Safety valve) | D | D | 01 | _ |  | 2024-02-10 | 2024-03-11 | 2024-05-30 | 2024-06-29 | 2024-04-25 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:176548EB47BD40719A0C2FB9782B0EB0
DDCL | CCP-W-B113-03-ME-B01-0036 | STG_Pneumatic, Motor, Manual Valve Outline and Datasheet (Including Safety valve) | D | D | 01 | _ |  | 2024-06-24 | 2024-07-24 | 2024-08-19 | 2024-09-18 | 2024-07-22 | 2024-07-22 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0292 | D | 01 | 2024-07-22 | 2024-07-25 | 2024-08-04 | CCP-PGU-TRM-EPC-0292 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0292 | D | 01 | 2024-07-22 | 2024-07-25 | 2024-08-04 | CCP-PGU-TRM-EPC-0292 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A7A7EFF6EF4348AEAB62D2C25AF909B4
DDCL | CCP-W-B113-03-ME-B01-0037 | STG_Pipeline Strainer Outline Drawing | D | D | 01 | _ |  | 2024-01-11 | 2024-02-10 | 2024-05-30 | 2024-06-29 | 2024-05-31 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7D41C23E3F7042529FD2AD1339E3CC96
DDCL | CCP-W-B113-03-ME-B01-0038 | STG_Steam Trap Outline Drawing and Specification | D | D | 01 | _ |  | 2024-04-25 | 2024-05-25 | 2024-06-30 | 2024-07-30 | 2024-05-31 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6ECAEBF7D44C49629D06F3328ECF774E
DDCL | CCP-W-B113-03-ME-B18-0039 | STG_Equipment List | D | D | 01 | _ |  | 2024-01-26 | 2024-02-25 | 2024-07-29 | 2024-08-28 | 2024-04-01 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:83AB20632EBE44DB8B97067C296C2DEA
DDCL | CCP-W-B113-03-ME-B18-0040 | STG_Terminal Point List | D | D | 01 | _ |  | 2024-01-26 | 2024-02-25 | 2024-07-29 | 2024-08-28 | 2024-04-03 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A73C55DAECBC4DFD95C2A46AEC7EEB2B
DDCL | CCP-W-B113-03-ME-B18-0041 | STG_Tag/Labeling List | D | D | 01 | _ | FC DELAY | 2024-04-25 | 2024-05-25 | 2024-06-30 | 2024-07-30 | 2025-02-19 | 2025-04-17 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:94D7D5D0C73943C4A936046A64AAC539
DDCL | CCP-W-B113-03-ME-P13-0042 | STG_Allowable loadings and displacements | D | D | 01 | _ |  | 2024-01-26 | 2024-02-25 | 2024-07-29 | 2024-08-28 | 2024-03-06 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1C702F939BD94B43A1F0B519A7427C80
DDCL | CCP-W-B113-03-ME-P01-0043 | STG_Detail drawings - piping, components and BOM | D | D | 01 | _ |  | 2024-07-24 | 2024-08-23 | 2024-12-26 | 2025-01-25 | 2024-11-01 | 2024-11-04 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0582 | D | 01 | 2024-11-25 | 2024-11-25 | 2024-12-05 | CCP-PGU-TRM-EPC-0582 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0582 | D | 01 | 2024-11-25 | 2024-11-25 | 2024-12-05 | CCP-PGU-TRM-EPC-0582 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:47F0A87D08A745128E075291A1930D32
DDCL | CCP-W-B113-03-ME-K06-0045 | STG_Functional description | D | D | 01 | _ |  | 2023-12-27 | 2024-01-26 | 2024-03-31 | 2024-04-30 | 2024-06-12 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C1B313B7751645B09785A3B04473DB84
DDCL | CCP-W-B113-03-ME-H10-0066 | STG_Control system function philosophy | D | D | 01 | _ |  | 2024-08-23 | 2024-09-22 | 2024-09-22 | 2024-10-22 | 2024-11-14 | 2024-11-14 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0547 | D | 01 | 2024-11-14 | 2024-11-15 | 2024-11-25 | CCP-PGU-TRM-EPC-0547 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0547 | D | 01 | 2024-11-14 | 2024-11-15 | 2024-11-25 | CCP-PGU-TRM-EPC-0547 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:06DC0F119A0D4FD28100D2F22419ACEB
DDCL | CCP-W-B113-03-ME-H09-0067 | STG_Control Block Diagram | D | D | 01 | _ |  | 2024-02-25 | 2024-03-26 | 2024-04-30 | 2024-05-30 | 2024-04-01 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:86F924EBE5254D7C995F309715C150D9
DDCL | CCP-W-B113-03-ME-A07-0068 | STG_System Description for STG TCS/TPS and TPC/OPS | D | D | 01 | _ |  | 2023-12-27 | 2024-01-26 | 2024-05-30 | 2024-06-29 | 2024-06-12 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5EE88195FA054253805A352F78479845
DDCL | CCP-W-B113-03-ME-H10-0069 | STG_Control System specification | D | D | 01 | _ |  | 2024-04-25 | 2024-05-25 | 2024-05-30 | 2024-06-29 | 2024-07-11 | 2024-07-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0259 | D | 01 | 2024-07-12 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0259 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0259 | D | 01 | 2024-07-12 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0259 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:DCF8BB24B26F43BA82A35E640CFAD57D
DDCL | CCP-W-B113-03-ME-H09-0070 | STG_Logic diagrams for control of functional groups | D | D | 01 | A |  | 2024-06-24 | 2024-07-24 | 2024-07-24 | 2024-08-23 | 2024-08-16 | 2024-09-24 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0485 | D | 01 | 2024-09-26 | 2024-09-27 | 2024-08-31 | CCP-PGU-TRM-EPC-0333 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0333 CCP-EPC-TRM-PGU-0485 | D | 01 | 2024-08-19 2024-09-26 | 2024-08-21 2024-09-27 | 2024-08-31 | CCP-PGU-TRM-EPC-0333 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FBDF47AB021445A6B7AC3A7AABB63611
DDCL | CCP-W-B113-03-ME-K13-0071 | STG_Alarm/Trip List and Philosophy | D | D | 01 | _ |  | 2024-06-24 | 2024-07-24 | 2024-08-28 | 2024-09-27 | 2024-05-07 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6B0565A025734FE58A2C91B9746C253B
DDCL | CCP-W-B113-03-ME-K13-0072 | STG_List of signals | D | D | 01 | _ |  | 2024-05-24 | 2024-06-07 | 2024-08-28 | 2024-09-27 | 2024-07-22 | 2024-07-22 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0292 | D | 01 | 2024-07-22 | 2024-07-25 | 2024-08-04 | CCP-PGU-TRM-EPC-0292 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0292 | D | 01 | 2024-07-22 | 2024-07-25 | 2024-08-04 | CCP-PGU-TRM-EPC-0292 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CB4730F31239419383C54654627F5133
DDCL | CCP-W-B113-03-ME-H99-0073 | STG_HMI design | D | D | 01 | _ |  | 2024-06-24 | 2024-07-24 | 2024-08-28 | 2024-09-27 | 2024-09-24 | 2024-09-24 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0485 | D | 01 | 2024-09-26 | 2024-09-27 | 2024-10-07 | CCP-PGU-TRM-EPC-0485 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0485 | D | 01 | 2024-09-26 | 2024-09-27 | 2024-10-07 | CCP-PGU-TRM-EPC-0485 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:20DE8F08C12A4C01A9AFA3B5CAD24E59
DDCL | CCP-W-B113-03-ME-H99-0074 | STG_I/O list | D | D | 01 | _ |  | 2024-06-24 | 2024-07-24 | 2024-10-12 | 2024-11-11 | 2024-07-22 | 2024-07-22 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0292 | D | 01 | 2024-07-22 | 2024-07-25 | 2024-08-04 | CCP-PGU-TRM-EPC-0292 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0292 | D | 01 | 2024-07-22 | 2024-07-25 | 2024-08-04 | CCP-PGU-TRM-EPC-0292 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B86E7EDB27F24A0EB323785E183D1551
DDCL | CCP-W-B113-03-ME-E10-0075 | STG_Cable Interconnection Connection List and Schedule | D | D | 01 | _ |  | 2024-06-28 | 2024-07-12 | 2024-10-12 | 2024-11-11 | 2024-08-16 | 2024-08-19 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0333 | D | 01 | 2024-08-19 | 2024-08-21 | 2024-08-31 | CCP-PGU-TRM-EPC-0333 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0333 | D | 01 | 2024-08-19 | 2024-08-21 | 2024-08-31 | CCP-PGU-TRM-EPC-0333 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:DA673F75AED34449AF625EB2010CE64E
DDCL | CCP-W-B113-03-ME-H17-0076 | STG_loop Diagrams | D | D | 01 | _ |  | 2024-06-24 | 2024-07-24 | 2024-10-12 | 2024-11-11 | 2024-09-24 | 2024-09-24 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0485 | D | 01 | 2024-09-26 | 2024-09-27 | 2024-10-07 | CCP-PGU-TRM-EPC-0485 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0485 | D | 01 | 2024-09-26 | 2024-09-27 | 2024-10-07 | CCP-PGU-TRM-EPC-0485 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6D2F2125674C4E9BB752F9C3E8FA60C9
DDCL | CCP-W-B113-03-ME-A07-0077 | STG_System Description for High presure Hydraulic | D | D | 01 | _ |  | 2024-01-20 | 2024-02-19 | 2024-07-23 | 2024-08-23 | 2024-03-06 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:692483B8A2574285A6613E04DFBC1D40
DDCL | CCP-W-B113-03-ME-B15-0085 | STG_Thermal Insulation Specification | D | D | 01 | _ |  | 2024-06-24 | 2024-07-24 | 2024-07-24 | 2024-08-23 | 2024-05-29 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A862FE5296F547EDBEAD0DC80FB634F8
DDCL | CCP-W-B113-03-ME-P02-0090 | STG Pipe supports list | D | D | 01 | _ |  | 2024-05-25 | 2024-06-24 | 2024-07-24 | 2024-08-23 | 2024-10-14 | 2024-10-14 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0491 | D | 01 | 2024-10-14 | 2024-10-16 | 2024-10-26 | CCP-PGU-TRM-EPC-0491 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0491 | D | 01 | 2024-10-14 | 2024-10-16 | 2024-10-26 | CCP-PGU-TRM-EPC-0491 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:886C0A688A0E4057AFCE09145F70E20E
DDCL | CCP-W-B113-03-ME-P04-0096 | STG_Piping Material Specification | D | D | 01 | _ |  | 2023-12-27 | 2024-01-26 | 2024-01-26 | 2024-02-25 | 2024-04-01 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:290A78B3A9034C5793932F79EF9742FA
DDCL | CCP-W-B113-03-ME-P01-0096 | STG_Pipe Isometric Drawing and Stress Analysis | D | D | 01 | _ |  | 2024-04-25 | 2024-05-25 | 2024-05-25 | 2024-06-24 | 2024-06-07 | 2024-07-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0259 | D | 01 | 2024-07-12 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0259 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0259 | D | 01 | 2024-07-12 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0259 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:27BFEBAED60845D0B479818942109C2F
DDCL | CCP-W-B113-03-ME-E14-0065 | STG_Instrument Location Drawings | D | D | 01 | _ |  | 2024-04-09 | 2024-05-09 | 2024-10-27 | 2024-11-26 | 2024-07-15 | 2024-07-22 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0292 | D | 01 | 2024-07-22 | 2024-07-25 | 2024-08-04 | CCP-PGU-TRM-EPC-0292 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0292 | D | 01 | 2024-07-22 | 2024-07-25 | 2024-08-04 | CCP-PGU-TRM-EPC-0292 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E8A87AF599044B43A4C6060A8E5A6040
DDCL | CCP-W-B113-03-ME-B01-0013 | STG_General Arrangement Drawing-Cross section | D | D | 01 | _ |  | 2023-12-27 | 2024-01-26 | 2024-04-30 | 2024-05-30 | 2024-03-15 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CD8AA4FAC6744986AB6A97958B027252
DDCL | CCP-W-B113-03-ME-E02-0046 | STG_Single Line Diagram | D | D | 01 | _ |  | 2024-01-26 | 2024-02-25 | 2024-07-29 | 2024-08-28 | 2024-03-06 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2F69ADFC27084FE5BA9A3BFA1EE23D6C
DDCL | CCP-W-B113-03-ME-B16-0047 | STG_Generator Description, Characteristic Data & Curve | D | D | 01 | _ |  | 2024-01-11 | 2024-02-10 | 2024-06-29 | 2024-07-29 | 2024-06-12 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6153438F1FCB4F81A103C47AC35ACCDA
DDCL | CCP-W-B113-03-ME-E04-0051 | STG_Frequency Converter Outline and Arrangement | D | D | 01 | _ |  | 2023-12-19 | 2024-01-18 | 2024-05-30 | 2024-06-29 | 2024-03-04 | 2024-03-05 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0098 | D | 01 | 2024-03-05 | 2024-03-05 | 2024-03-18 | CCP-PGU-EPC-TRM-0098 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0098 | D | 01 | 2024-03-05 | 2024-03-05 | 2024-03-18 | CCP-PGU-EPC-TRM-0098 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CB3CEA1D49BD4501A69F230F63CC03B4
DDCL | CCP-W-B113-03-ME-E04-0052 | STG_Measuring and Synchronization Outline and Arrangement | D | D | 01 | _ |  | 2024-01-11 | 2024-02-10 | 2024-07-09 | 2024-08-08 | 2024-04-01 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:65205CCB99CD46839083F657F66D1B60
DDCL | CCP-W-B113-03-ME-E04-0053 | STG_DC motor starter Outline and Arrangement | D | D | 01 | _ |  | 2024-01-11 | 2024-02-10 | 2024-07-09 | 2024-08-08 | 2024-03-04 | 2024-03-05 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0098 | D | 01 | 2024-03-05 | 2024-03-05 | 2024-03-18 | CCP-PGU-TRM-EPC-0098 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0098 | D | 01 | 2024-03-05 | 2024-03-05 | 2024-03-18 | CCP-PGU-TRM-EPC-0098 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5272F6D566574A98BE5FE8359FEDCC2A
DDCL | CCP-W-B113-03-ME-B04-0054 | STG_Outline for Three Phase Induction Motor | D | D | 01 | _ |  | 2024-04-25 | 2024-05-25 | 2024-05-31 | 2024-06-30 | 2024-07-15 | 2024-07-16 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0267 | D | 01 | 2024-07-16 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0267 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0267 | D | 01 | 2024-07-16 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0267 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1431B755A00D494BB678571F821E7E1E
DDCL | CCP-W-B113-03-ME-B04-0055 | STG_Outline for Three Phase Induction DC Motor | D | D | 01 | _ |  | 2024-04-25 | 2024-05-25 | 2024-06-30 | 2024-07-30 | 2024-07-15 | 2024-07-16 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0267 | D | 01 | 2024-07-16 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0267 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0267 | D | 01 | 2024-07-16 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0267 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B73858746D574961BDBF83CA5A34CA1B
DDCL | CCP-W-B113-03-ME-E24-0056 | STG_Motor Datasheet & Curve | D | D | 01 | _ |  | 2023-12-27 | 2024-01-26 | 2024-05-30 | 2024-06-29 | 2024-07-15 | 2024-07-16 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0267 | D | 01 | 2024-07-16 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0267 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0267 | D | 01 | 2024-07-16 | 2024-07-19 | 2024-07-29 | CCP-PGU-TRM-EPC-0267 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E22FA9B1ED1D47818B0094BFB8B29BF1
DDCL | CCP-W-B113-03-ME-A07-0057 | STG_Electrical system description | D | D | 01 | _ |  | 2023-12-27 | 2024-01-26 | 2024-03-16 | 2024-04-15 | 2024-04-22 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C6F393CEEFFB49F5B615DE462F6805FA
DDCL | CCP-W-B113-03-ME-H04-0058 | STG_Instrument Hook ups | D | D | 01 | _ |  | 2024-06-28 | 2024-07-12 | 2024-10-27 | 2024-11-26 | 2024-07-15 | 2024-07-22 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0292 | D | 01 | 2024-07-22 | 2024-07-25 | 2024-08-04 | CCP-PGU-TRM-EPC-0292 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0292 | D | 01 | 2024-07-22 | 2024-07-25 | 2024-08-04 | CCP-PGU-TRM-EPC-0292 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:73D9333500DA4A38A0A681411E0AD9DE
DDCL | CCP-W-B113-03-ME-H21-0059 | STG_Instrumentation data sheets | D | D | 01 | _ |  | 2024-02-13 | 2024-03-14 | 2024-10-27 | 2024-11-26 | 2024-08-16 | 2024-08-19 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0333 | D | 01 | 2024-08-19 | 2024-08-21 | 2024-08-31 | CCP-PGU-TRM-EPC-0333 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0333 | D | 01 | 2024-08-19 | 2024-08-21 | 2024-08-31 | CCP-PGU-TRM-EPC-0333 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E2E0FFA107854376A7DCB3BB9141C2D3
DDCL | CCP-W-B113-03-ME-H20-0060 | STG_Measurement list | D | D | 01 | _ |  | 2024-06-28 | 2024-07-12 | 2024-10-27 | 2024-11-26 | 2024-07-22 | 2024-07-22 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0292 | D | 01 | 2024-07-22 | 2024-07-25 | 2024-08-04 | CCP-PGU-TRM-EPC-0292 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0292 | D | 01 | 2024-07-22 | 2024-07-25 | 2024-08-04 | CCP-PGU-TRM-EPC-0292 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:BA49E52D97044E56AE59ECC0C323C129
DDCL | CCP-W-B113-03-ME-H10-0061 | STG_Control system architecture | D | D | 01 | _ |  | 2024-01-11 | 2024-02-10 | 2024-05-15 | 2024-06-14 | 2024-04-01 | 2024-06-12 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0184 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0184 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4AA1CC6290EC4669A05E23339B4F3FBD
DDCL | CCP-W-B113-03-ME-E14-0062 | STG_Outline and Arrangement of TCS/TPS and TPC/OPS Cabinet | D | D | 01 | _ |  | 2024-01-11 | 2024-02-10 | 2024-07-09 | 2024-08-08 | 2024-06-20 | 2024-06-21 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0213 | D | 01 | 2024-06-21 | 2024-06-24 | 2024-07-04 | CCP-PGU-TRM-EPC-0213 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0213 | D | 01 | 2024-06-21 | 2024-06-24 | 2024-07-04 | CCP-PGU-TRM-EPC-0213 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:81A8B3F7366942308637FFD07439151C
DDCL | CCP-W-B113-03-ME-E14-0063 | STG_Outline of Local Instrument Rack and Stanchion | D | D | 01 | _ |  | 2024-04-09 | 2024-05-09 | 2024-10-27 | 2024-11-26 | 2024-06-20 | 2024-06-21 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0213 | D | 01 | 2024-06-21 | 2024-06-24 | 2024-07-04 | CCP-PGU-TRM-EPC-0213 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0213 | D | 01 | 2024-06-21 | 2024-06-24 | 2024-07-04 | CCP-PGU-TRM-EPC-0213 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5A2A2A034C2E43B792A128ECDBC17793
DDCL | CCP-W-B113-03-ME-E14-0064 | STG_Outline of Terminal Box, Junction Box | D | D | 01 | _ |  | 2024-04-09 | 2024-05-09 | 2024-10-27 | 2024-11-26 | 2024-06-20 | 2024-06-21 |  |  | BOP Plant | Plant EPC)주기기기술팀 | STEAM_TURBINE_GENERATOR | Mechanical | 김태균 | [10 empty] | CCP-EPC-TRM-PGU-0213 | D | 01 | 2024-06-21 | 2024-06-24 | 2024-07-04 | CCP-PGU-TRM-EPC-0213 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0213 | D | 01 | 2024-06-21 | 2024-06-24 | 2024-07-04 | CCP-PGU-TRM-EPC-0213 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E395D77F6B7042ABB6F8F61101D94105
DDCL | CCP-W-B055-14-ME-A05-0032 | NAMEPLATE DRAWING FOR CRANE AND HOIST | D | D | 01 | _ |  | 2024-05-15 | 2024-06-14 | 2024-10-15 | 2024-11-14 | 2024-06-21 | 2024-06-21 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Crane and hoist | Mechanical | 안성훈 | [10 empty] | CCP-EPC-TRM-PGU-0210 | D | 01 | 2024-06-21 | 2024-06-24 | 2024-07-04 | CCP-PGU-TRM-EPC-0210 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0210 | D | 01 | 2024-06-21 | 2024-06-24 | 2024-07-04 | CCP-PGU-TRM-EPC-0210 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:DCAAE2F0B8644A2E9DF1D5CD1F962524
DDCL | CCP-W-B055-14-ME-B01-0005 | HOIST_GENERAL ARRANGEMENT DRAWING | D | D | 02 | _ |  | 2024-03-15 | 2024-04-15 | 2024-07-15 | 2024-08-15 | 2024-04-12 | 2024-06-28 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Crane and hoist | Mechanical | 안성훈 | [10 empty] | CCP-EPC-TRM-PGU-0227 | D | 02 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0227 | D | 02 | Deemed Approved | CCP-EPC-TRM-PGU-0158 | D | 01 | 2024-05-28 | 2024-05-29 | 2024-06-11 | CCP-PGU-TRM-EPC-0158 | Rejected | CCP-EPC-TRM-PGU-0227 | D | 02 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0227 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:19DFC0284B9A414087BBD46D45B074BB
DDCL | CCP-W-B055-14-ME-B01-0002 | CRANE_GENERAL ARRANGEMENT DRAWING FOR OVERHEAD CRANE (STEAM TURBINE) | D | D | 01 | _ |  | 2024-03-15 | 2024-04-15 | 2024-07-15 | 2024-08-15 | 2024-05-03 | 2024-06-12 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Crane and hoist | Mechanical | 안성훈 | [10 empty] | CCP-EPC-TRM-PGU-0183 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0183 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0183 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0183 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5DC94C6C701B44A2B0E0C8A994F3053D
DDCL | CCP-W-B055-14-ME-B01-0001 | CRANE_GENERAL ARRANGEMENT DRAWING FOR OVERHEAD CRANE (GAS TURBINE) | D | D | 01 | _ |  | 2024-03-15 | 2024-04-15 | 2024-07-15 | 2024-08-15 | 2024-05-07 | 2024-06-12 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Crane and hoist | Mechanical | 안성훈 | [10 empty] | CCP-EPC-TRM-PGU-0183 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0183 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0183 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0183 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:453A14DD61AE405B9733A297D343633E
DDCL | CCP-W-B055-14-ME-B01-0003 | CRANE_GENERAL ARRANGEMENT DRAWING FOR JIB CRANE | D | D | 01 | _ |  | 2024-03-15 | 2024-04-15 | 2024-07-15 | 2024-08-15 | 2024-05-03 | 2024-06-12 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Crane and hoist | Mechanical | 안성훈 | [10 empty] | CCP-EPC-TRM-PGU-0183 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0183 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0183 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0183 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B8CD1A5847A34E6AADC9F99AB2450C88
DDCL | CCP-W-B055-14-ME-B01-0004 | CRANE_GENERAL ARRANGEMENT DRAWING FOR SUSPENSION CRANE | D | D | 02 | _ |  | 2024-03-15 | 2024-04-15 | 2024-07-15 | 2024-08-15 | 2024-04-12 | 2024-06-28 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Crane and hoist | Mechanical | 안성훈 | [10 empty] | CCP-EPC-TRM-PGU-0227 | D | 02 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0227 | D | 02 | Deemed Approved | CCP-EPC-TRM-PGU-0158 | D | 01 | 2024-05-28 | 2024-05-29 | 2024-06-11 | CCP-PGU-TRM-EPC-0158 | Rejected | CCP-EPC-TRM-PGU-0227 | D | 02 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0227 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2747523F0D6148D0849D8807F76750E4
DDCL | CCP-W-B055-14-ME-E13-0012 | CRANE_ELECTRIC DRAWING FOR OVERHEAD CRANE (GAS TURBINE) | D | D | 01 | _ |  | 2024-05-15 | 2024-06-14 | 2024-10-15 | 2024-11-15 | 2024-07-01 | 2024-07-01 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Crane and hoist | Mechanical | 안성훈 | [10 empty] | CCP-EPC-TRM-PGU-0233 | D | 01 | 2024-07-01 | 2024-07-03 | 2024-07-11 | CCP-PGU-TRM-EPC-0233 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0233 | D | 01 | 2024-07-01 | 2024-07-03 | 2024-07-11 | CCP-PGU-TRM-EPC-0233 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:76607F260E784B0288B618331AB6563C
DDCL | CCP-W-B055-14-ME-E13-0013 | CRANE_ELECTRIC DRAWING FOR JIB CRANE | D | D | 01 | _ |  | 2024-05-15 | 2024-06-14 | 2024-10-15 | 2024-11-15 | 2024-06-27 | 2024-06-27 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Crane and hoist | Mechanical | 안성훈 | [10 empty] | CCP-EPC-TRM-PGU-0224 | D | 01 | 2024-06-27 | 2024-06-28 | 2024-07-08 | CCP-PGU-TRM-EPC-0224 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0224 | D | 01 | 2024-06-27 | 2024-06-28 | 2024-07-08 | CCP-PGU-TRM-EPC-0224 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A7309B81566947008429EAEC910FFBA1
DDCL | CCP-W-B055-14-ME-E13-0014 | CRANE_ELECTRIC DRAWING FOR SUSPENSION CRANE | D | D | 01 | _ |  | 2024-05-15 | 2024-06-14 | 2024-10-15 | 2024-11-15 | 2024-06-21 | 2024-06-21 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Crane and hoist | Mechanical | 안성훈 | [10 empty] | CCP-EPC-TRM-PGU-0211 | D | 01 | 2024-06-21 | 2024-06-24 | 2024-07-04 | CCP-PGU-TRM-EPC-0211 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0211 | D | 01 | 2024-06-21 | 2024-06-24 | 2024-07-04 | CCP-PGU-TRM-EPC-0211 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6EB913E04F4B4866B679A63F589D55B0
DDCL | CCP-W-B055-14-ME-B16-0007 | CRANE_TECHNICAL DATA SHEETS FOR OVERHEAD CRANE (STEAM TURBINE) | D | D | 01 | _ |  | 2024-03-15 | 2024-04-15 | 2024-07-15 | 2024-08-15 | 2024-04-23 | 2024-06-12 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Crane and hoist | Mechanical | 안성훈 | [10 empty] | CCP-EPC-TRM-PGU-0183 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0183 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0183 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0183 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B0ED67771D7A4ADC8623DE5C77E0960F
DDCL | CCP-W-B055-14-ME-B16-0010 | HOIST_TECHNICAL DATA SHEETS | D | D | 01 | _ |  | 2024-03-15 | 2024-04-15 | 2024-07-15 | 2024-08-15 | 2024-04-18 | 2024-05-28 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Crane and hoist | Mechanical | 안성훈 | [10 empty] | CCP-EPC-TRM-PGU-0159 | D | 01 | 2024-05-28 | 2024-05-29 | 2024-06-08 | CCP-PGU-TRM-EPC-0159 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0159 | D | 01 | 2024-05-28 | 2024-05-29 | 2024-06-08 | CCP-PGU-TRM-EPC-0159 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:987DAE6E7E514C8EB11FC48DE33558E5
DDCL | CCP-W-B055-14-ME-B16-0006 | CRANE_TECHNICAL DATA SHEETS FOR OVERHEAD CRANE (GAS TURBINE) | D | D | 01 | _ |  | 2024-03-15 | 2024-04-15 | 2024-07-15 | 2024-08-15 | 2024-04-23 | 2024-06-12 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Crane and hoist | Mechanical | 안성훈 | [10 empty] | CCP-EPC-TRM-PGU-0183 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0183 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0183 | D | 01 | 2024-06-12 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0183 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1915A94C6F5A42EA9DB4AE23CD336947
DDCL | CCP-W-B055-14-ME-B16-0008 | CRANE_TECHNICAL DATA SHEETS FOR JIB CRANE | D | D | 01 | _ |  | 2024-03-15 | 2024-04-15 | 2024-07-15 | 2024-08-15 | 2024-04-18 | 2024-05-28 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Crane and hoist | Mechanical | 안성훈 | [10 empty] | CCP-EPC-TRM-PGU-0159 | D | 01 | 2024-05-28 | 2024-05-29 | 2024-06-11 | CCP-PGU-TRM-EPC-0159 | D | 01 | Approved with comment | CCP-EPC-TRM-PGU-0159 | D | 01 | 2024-05-28 | 2024-05-29 | 2024-06-11 | CCP-PGU-TRM-EPC-0159 | Approved with comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4E4B96246D524565BEF0DCD27A8893AE
DDCL | CCP-W-B055-14-ME-B16-0009 | CRANE_TECHNICAL DATA SHEETS FOR SUSPENSION CRANE | D | D | 01 | _ |  | 2024-03-15 | 2024-04-15 | 2024-07-15 | 2024-08-15 | 2024-04-18 | 2024-05-28 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Crane and hoist | Mechanical | 안성훈 | [10 empty] | CCP-EPC-TRM-PGU-0159 | D | 01 | 2024-05-28 | 2024-05-29 | 2024-06-11 | CCP-PGU-TRM-EPC-0159 | D | 01 | Approved with comment | CCP-EPC-TRM-PGU-0159 | D | 01 | 2024-05-28 | 2024-05-29 | 2024-06-11 | CCP-PGU-TRM-EPC-0159 | Approved with comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D4762165B0AD4845901F4779E66384A7
DDCL | CCP-W-B111-01-ME-C46-0001 | GTG_Noise Protection Concept | D | D | 01 | _ |  | 2024-01-17 | 2024-02-01 | 2024-04-23 | 2024-05-01 | 2024-02-22 | 2024-06-24 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0219 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0219 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0219 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0219 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:24979CF88EA94085B7F4DB74434BA121
DDCL | CCP-W-B111-01-ME-B05-0001 | GTG_Gas Turbine Turboset, Assembly Outline Drawing | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-03-15 | 2024-06-24 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0217 | D | 01 | 2024-06-24 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0217 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0217 | D | 01 | 2024-06-24 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0217 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:03C3F00161E44187BA5B4B0D47B09C65
DDCL | CCP-W-B111-01-ME-B05-0010 | GTG_Outline Drawing - Generator | D | D | 01 | _ |  | 2024-03-03 | 2024-03-18 | 2024-06-08 | 2024-06-16 | 2024-03-15 | 2024-06-24 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0217 | D | 01 | 2024-06-24 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0217 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0217 | D | 01 | 2024-06-24 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0217 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:794227FF533746138A5B023F5C9D6806
DDCL | CCP-W-B111-01-ME-E14-0001 | GTG_Data Sheet Generator | D | D | 01 | _ |  | 2024-03-03 | 2024-03-18 | 2024-06-08 | 2024-06-16 | 2024-03-15 | 2024-06-24 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0219 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0219 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0219 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0219 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:9E6C0CEA4D904AB1BF0B87877C9E8829
DDCL | CCP-W-B111-01-ME-E13-0001 | GTG_Single Line Diagram | D | D | 01 | _ |  | 2024-01-27 | 2024-02-11 | 2024-05-03 | 2024-05-11 | 2024-04-16 | 2024-06-24 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0219 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0219 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0219 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0219 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FC8B28FB0B254C589C671750A2D63AE1
DDCL | CCP-W-B111-01-ME-E13-0002 | GTG_Single Line Diagram Generator Protection, Measuring and Sync | D | D | 01 | _ |  | 2024-03-02 | 2024-03-17 | 2024-06-07 | 2024-06-15 | 2024-04-16 | 2024-06-24 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0219 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0219 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0219 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0219 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:9EA8DFF748DF47FEB493E0E5B3D4FC5D
DDCL | CCP-W-B111-01-ME-B06-0027 | GTG_P&ID Generator | D | D | 01 | _ |  | 2024-03-17 | 2024-04-01 | 2024-06-22 | 2024-06-30 | 2024-04-16 | 2024-06-24 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0218 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0218 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0218 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0218 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A92251C403B74F9EB9F77AD781422D62
DDCL | CCP-W-B111-01-ME-H20-0002 | GTG_Measurements List | D | D | 01 | _ |  | 2024-03-31 | 2024-04-15 | 2024-07-06 | 2024-07-14 | 2024-04-26 | 2024-06-24 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0219 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0219 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0219 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0219 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C9C7AC051B59482AA5A5BAFB547937B0
DDCL | CCP-W-B111-01-ME-E04-0003 | GTG_Dimension Drawing SFC Transformer | D | D | 01 | _ |  | 2024-04-11 | 2024-04-26 | 2024-07-17 | 2024-07-25 | 2024-04-26 | 2024-06-24 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0219 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0219 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0219 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0219 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:963065493B4745E6B276BD2906AE45A8
DDCL | CCP-W-B111-01-ME-E04-0005 | GTG_Dimension Drawing SEE Transformer | D | D | 01 | _ |  | 2024-04-11 | 2024-04-26 | 2024-07-17 | 2024-07-25 | 2024-04-26 | 2024-06-24 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0219 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0219 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0219 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0219 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:15EA819AACEE444BA842A9A843F7229D
DDCL | CCP-W-B111-01-ME-B06-0020 | GTG_P&ID Hydraulic Oil for Fuel Oil System | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-05-27 | 2024-06-24 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0218 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0218 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0218 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0218 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:03E9EC3A1942419DAA6D89BDA4661796
DDCL | CCP-W-B111-01-ME-B06-0024 | GTG_P&ID Fuel Oil System | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-05-27 | 2024-06-24 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0218 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0218 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0218 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0218 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8A29EB4805F34604A71416F4452321EA
DDCL | CCP-W-B111-01-ME-B06-0025 | GTG_P&ID Purge Water System | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-05-27 | 2024-06-24 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0218 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0218 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0218 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0218 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FC894BCCF216492880A84B88AF3F2E3B
DDCL | CCP-W-B111-01-ME-B01-0004 | GTG_General Arrangement Drawing Air Intake System | D | D | 01 | _ |  | 2024-05-05 | 2024-05-20 | 2024-08-10 | 2024-08-18 | 2024-05-27 | 2024-06-24 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0217 | D | 01 | 2024-06-24 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0217 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0217 | D | 01 | 2024-06-24 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0217 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:DE9EA50473D9471E8A1766C3B64CC09E
DDCL | CCP-W-B111-01-ME-E02-0001 | GTG_Auxiliary Wiring Diagrams | D | D | 01 | _ |  | 2024-04-26 | 2024-05-11 | 2024-08-01 | 2024-08-09 | 2024-05-27 | 2024-06-24 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0219 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0219 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0219 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0219 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FAC8FC817B514C7D9E454C366B14CC61
DDCL | CCP-W-B111-01-ME-A11-0003 | GTG_System Description Purge Water | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-06-18 | 2024-06-21 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B135BF5374FB4DECB59A1CCEC85C3E12
DDCL | CCP-W-B111-01-ME-A11-0011 | GTG_System Description Hydraulic for Fuel Oil System | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-06-18 | 2024-06-21 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C8BA9952CBCF401597E830FE845A2173
DDCL | CCP-W-B111-01-ME-A11-0014 | GTG_System Description Fuel Oil | D | D | 01 | _ |  | 2024-02-18 | 2024-03-04 | 2024-05-25 | 2024-06-02 | 2024-06-18 | 2024-06-21 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0214 | D | 01 | 2024-06-21 | 2024-06-25 | 2024-07-05 | CCP-PGU-TRM-EPC-0214 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:16EF0CC157BB43DD80E1E304FA74CB4C
DDCL | CCP-W-B111-01-ME-B01-0005 | GTG_General Arrangement Drawing Exhaust Gas Diffuser | D | D | 01 | _ |  | 2024-06-14 | 2024-06-29 | 2024-09-19 | 2024-09-27 | 2024-08-26 | 2024-08-27 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0433 | D | 01 | 2024-08-27 | 2024-08-28 | 2024-09-07 | CCP-PGU-TRM-EPC-0433 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0433 | D | 01 | 2024-08-27 | 2024-08-28 | 2024-09-07 | CCP-PGU-TRM-EPC-0433 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E94D0ABCE60C463EB9287C7FDCEC665A
DDCL | CCP-W-B111-01-ME-B01-0006 | GTG_General Arrangement Drawing Power Control Center | D | D | 01 | _ |  | 2025-02-04 | 2025-02-19 | 2025-05-12 | 2025-05-20 | 2025-02-07 | 2025-02-14 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:68C5F8FAF8B741C2A0275A7D82323952
DDCL | CCP-W-B111-01-ME-B01-0009 | GTG_General Arrangement Drawing GT Noise Enclosure | D | D | 01 | _ |  | 2024-06-14 | 2024-06-29 | 2024-09-19 | 2024-09-27 | 2024-08-26 | 2024-08-27 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0433 | D | 01 | 2024-08-27 | 2024-08-28 | 2024-09-07 | CCP-PGU-TRM-EPC-0433 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0433 | D | 01 | 2024-08-27 | 2024-08-28 | 2024-09-07 | CCP-PGU-TRM-EPC-0433 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:74E8797825064669B75D1F4E2325F7F3
DDCL | CCP-W-B111-01-ME-B01-0010 | GTG_Generator Neutral Point Grounding Cabinet Arrangement Drawing | D | D | 01 | _ |  | 2024-12-11 | 2024-12-26 | 2025-03-18 | 2025-03-26 | 2025-01-09 | 2025-01-10 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8B964C54063D4F29BEDABD65B974B2BE
DDCL | CCP-W-B111-01-ME-B19-0001 | GTG_Turbine Control System Architecture | D | D | 01 | _ |  | 2025-01-17 | 2025-02-01 | 2025-04-24 | 2025-05-02 | 2025-02-07 | 2025-02-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:AA6DC07556684F51BFB2C46D9C45F01E
DDCL | CCP-W-B111-01-ME-H99-0001 | GTG_HMI-Displays | D | D | 01 | _ |  | 2025-05-02 | 2025-05-17 | 2025-08-07 | 2025-08-15 | 2025-05-07 | 2025-05-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0863 | D | 01 | 2025-05-08 | 2025-05-12 | 2025-05-22 | CCP-PGU-TRM-EPC-0863 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0863 | D | 01 | 2025-05-08 | 2025-05-12 | 2025-05-22 | CCP-PGU-TRM-EPC-0863 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A70AEFA781F34AFDB2830FCFEBFF3C9D
DDCL | CCP-W-B111-01-ME-E04-0004 | GTG_SEE Transformer Housing Dimension Drawing | D | D | 01 | _ |  | 2024-04-12 | 2024-04-26 | 2024-07-18 | 2024-07-25 | 2024-04-26 | 2024-06-24 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0219 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0219 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0219 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0219 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C0EAC778F89B41EA9BC30EBC3CA2229C
DDCL | CCP-W-B111-01-ME-E04-0002 | GTG_SFC Transformer Housing Dimension Drawing | D | D | 01 | _ |  | 2024-04-12 | 2024-04-26 | 2024-07-18 | 2024-07-25 | 2024-04-26 | 2024-06-24 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0219 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0219 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0219 | D | 01 | 2024-06-24 | 2024-06-27 | 2024-07-07 | CCP-PGU-TRM-EPC-0219 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:40119E96646B40D8AB5E3D1F33678ED2
DDCL | CCP-W-B111-01-ME-E07-0002 | GTG_Connection Diagram for Lube Oil Tank Heater_(MBY10GF002) | D | D | 01 | _ |  | 2025-01-18 | 2025-02-01 | 2025-04-24 | 2025-05-01 | 2025-01-10 | 2025-01-10 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D00D0463F8EB4C7CB4354320B5CB2527
DDCL | CCP-W-B111-01-ME-E07-0011 | GTG_Connection Diagram for Turning Device GT_(MBY45GF001) | D | D | 01 | _ |  | 2025-01-18 | 2025-02-01 | 2025-04-24 | 2025-05-01 | 2025-01-10 | 2025-01-10 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:453B66902E654CB7BCCFBE9B87AFD90B
DDCL | CCP-W-B111-01-ME-E07-0007 | GTG_Connection Diagram for IGV, VGV Rotary Encoder_(MBY30GF020) | D | D | 01 | _ |  | 2025-01-18 | 2025-02-01 | 2025-04-24 | 2025-05-01 | 2025-01-10 | 2025-01-10 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7C426DC51EEE454EAC49D1B96C2C3B2C
DDCL | CCP-W-B111-01-ME-E07-0014 | GTG_Connection Diagram for Blow Off Racck (Pressure Measuring)_(MYB30GF012) | D | D | 01 | _ |  | 2025-01-18 | 2025-02-01 | 2025-04-24 | 2025-05-01 | 2025-01-10 | 2025-01-10 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1A28CFA6D1C040328E284B2617A48421
DDCL | CCP-W-B111-01-ME-E07-0018 | GTG_Connection Diagram for Left Combust Chamber Top_(MYB30GF103) | D | D | 01 | _ |  | 2025-01-18 | 2025-02-01 | 2025-04-24 | 2025-05-01 | 2025-01-10 | 2025-01-10 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F51F1A547F494F8AB8B09DBD3F8A9679
DDCL | CCP-W-B111-01-ME-E07-0019 | GTG_Connection Diagram for Right Combust Chamber Top_(MYB30GF203) | D | D | 01 | _ |  | 2025-01-18 | 2025-02-01 | 2025-04-24 | 2025-05-01 | 2025-01-10 | 2025-01-10 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6E4AAE057C4C4511A1C4A77A33188DE4
DDCL | CCP-W-B111-01-ME-E07-0015 | GTG_Connection Diagram for Ignition Gas_(MYB30GF021) | D | D | 01 | _ |  | 2025-01-18 | 2025-02-01 | 2025-04-24 | 2025-05-01 | 2025-01-10 | 2025-01-10 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8DBE2FCEA8004595A42DB39392792067
DDCL | CCP-W-B111-01-ME-E07-0021 | GTG_Connection Diagram for Automatic Compressor Cleaning Skid_(MBA30GF020) | D | D | 01 | _ |  | 2025-01-18 | 2025-02-01 | 2025-04-24 | 2025-05-01 | 2025-01-10 | 2025-01-10 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:53ED87F3111A4E378E2714026F4C678B
DDCL | CCP-W-B111-01-ME-E07-0006 | GTG_Connection Diagram for Turbine Bearing Housing_(MBY18GF001) | D | D | 01 | _ |  | 2025-01-18 | 2025-02-01 | 2025-04-24 | 2025-05-01 | 2025-01-10 | 2025-01-10 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:685BB51CE4F94403BC409BC6C9D37CEA
DDCL | CCP-W-B111-01-ME-E07-0020 | GTG_Connection Diagram for Right Combust Chamber Bottom_(MYB30GF202) | D | D | 01 | _ |  | 2025-01-18 | 2025-02-01 | 2025-04-24 | 2025-05-01 | 2025-01-10 | 2025-01-10 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B18F5B8B07F4412BAC5DD8D4273CF5F8
DDCL | CCP-W-B111-01-ME-E07-0013 | GTG_Connection Diagram for GT Drainage_(MYB17GF010) | D | D | 01 | _ |  | 2025-01-18 | 2025-02-01 | 2025-04-24 | 2025-05-01 | 2025-01-10 | 2025-01-10 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:02DADA39458A4CEDA4CE2266D060EBB8
DDCL | CCP-W-B111-01-ME-E07-0009 | GTG_Connection Diagram for Measuring Points at Compressor Bearing_(MBY40GF001) | D | D | 01 | _ |  | 2025-01-18 | 2025-02-01 | 2025-04-24 | 2025-05-01 | 2025-01-10 | 2025-01-10 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6AB9AD6869D3452D9F03A0F82BFC9F09
DDCL | CCP-W-B111-01-ME-E07-0022 | GTG_Connection Diagram for Fuel Gas Skid_(MBY09GF001) | D | D | 01 | _ |  | 2025-01-18 | 2025-02-01 | 2025-04-24 | 2025-05-01 | 2025-01-10 | 2025-01-10 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:98F8DBC14EF24966A6D73441A8544FBC
DDCL | CCP-W-B111-01-ME-E07-0008 | GTG_Connection Diagram for Instrument Air Skid_(MBY40GH001, MBX20GF001) | D | D | 01 | _ |  | 2025-01-18 | 2025-02-01 | 2025-04-24 | 2025-05-01 | 2025-01-10 | 2025-01-10 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:176286E9702E42EC9EF74B42A1E53BF2
DDCL | CCP-W-B111-01-ME-E07-0004 | GTG_Connection Diagram for Hydraulic Clearance Optimization Skid_(MBA50GF030, MBY15GF030 ) | D | D | 01 | _ |  | 2025-01-18 | 2025-02-01 | 2025-04-24 | 2025-05-01 | 2025-01-10 | 2025-01-10 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F5EFE29B5FE14CA8A6926EE6330934BE
DDCL | CCP-W-B111-01-ME-E07-0012 | GTG_Connection Diagram for Piping Skid, Left (Compressor and Turbine Outlet Temperature)_(MYB12GF010) | D | D | 01 | _ |  | 2025-01-18 | 2025-02-01 | 2025-04-24 | 2025-05-01 | 2025-01-10 | 2025-01-10 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:0CF4DA9955284B9EB13DA47DFA9648F2
DDCL | CCP-W-B111-01-ME-E07-0003 | GTG_Connection Diagram for Purge Water Skid_(MBY11GF001) | D | D | 01 | _ |  | 2025-01-18 | 2025-02-01 | 2025-04-24 | 2025-05-01 | 2025-01-10 | 2025-01-10 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B1063608FE5A44FF9ABA3E65FB0BFCFD
DDCL | CCP-W-B111-01-ME-E07-0005 | GTG_Connection Diagram for Lube Oil Skid_(MBY15GF001, MBV15GF001) | D | D | 01 | _ |  | 2025-01-18 | 2025-02-01 | 2025-04-24 | 2025-05-01 | 2025-01-10 | 2025-01-10 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B5A705888DAB4A5CB2782055AD80FEB4
DDCL | CCP-W-B111-01-ME-E07-0016 | GTG_Connection Diagram for Pipig Skid, Front (Compressor Inlet Temperature)_(MYB30GF010) | D | D | 01 | _ |  | 2025-01-18 | 2025-02-01 | 2025-04-24 | 2025-05-01 | 2025-01-10 | 2025-01-10 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F242D66D8E5C4833BB97AE20BE8CD233
DDCL | CCP-W-B111-01-ME-E07-0001 | GTG_Connection Diagram for Hydraulic Oil Skid_(MBY10GF001,MBX01GF001 ) | D | D | 01 | _ |  | 2025-01-18 | 2025-02-01 | 2025-04-24 | 2025-05-01 | 2025-01-10 | 2025-01-10 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:65EECE5BB42E4FE9B349C81E82CA9F3E
DDCL | CCP-W-B111-01-ME-E07-0017 | GTG_Connection Diagram for Left Combust Chamber Bottom_(MYB30GF102) | D | D | 01 | _ |  | 2025-01-18 | 2025-02-01 | 2025-04-24 | 2025-05-01 | 2025-01-10 | 2025-01-10 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5DE2269FF4474AA4A1DFD3583F785796
DDCL | CCP-W-B111-01-ME-E07-0010 | GTG_Connection Diagram for Turning Gear Control Block_(MBY44GF001, MBV35GF001) | D | D | 01 | _ |  | 2025-01-18 | 2025-02-01 | 2025-04-24 | 2025-05-01 | 2025-01-10 | 2025-01-10 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8D78D77C2C3D4F03B991646B86454CCF
DDCL | CCP-W-B111-01-ME-E03-0009 | GTG_Interconnection Diagram Battery Charger | D | D | 01 | _ |  | 2025-04-22 | 2025-05-07 | 2025-07-28 | 2025-08-05 | 2025-01-06 | 2025-01-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:577AD4739D1C4C8CA07BFE926AD3DD96
DDCL | CCP-W-B111-01-ME-E03-0001 | GTG_Interconnection Diagram SEE, SFC Equipment | D | D | 01 | _ |  | 2025-04-22 | 2025-05-07 | 2025-07-28 | 2025-08-05 | 2025-01-06 | 2025-01-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:59F30913EE7542B9BF2BD2A25781BAEC
DDCL | CCP-W-B111-01-ME-E03-0008 | GTG_Interconnection Diagram Generator Current Transformer Line Side | D | D | 01 | _ |  | 2025-04-22 | 2025-05-07 | 2025-07-28 | 2025-08-05 | 2025-01-06 | 2025-01-07 |  |  | TG Plant | Plant EPC)주기기기술팀 | Gas Turbine and Generator package | Mechanical | 박현찬 | [10 empty] | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0858 | D | 01 | 2025-02-19 | 2025-02-20 | 2025-03-02 | CCP-PGU-TRM-EPC-0858 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:0F37D52C5AFB4FFAA733511378632B09
DDCL | CCP-W-B114-02-ME-H21-0065 | HRSG_Level Switches | D | D | 01 | _ |  | 2024-09-11 | 2024-11-11 | 2025-01-09 | 2025-02-09 | 2024-10-07 | 2024-10-07 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0488 | D | 01 | 2024-10-07 | 2024-10-10 | 2024-10-20 | CCP-PGU-TRM-EPC-0488 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0488 | D | 01 | 2024-10-07 | 2024-10-10 | 2024-10-20 | CCP-PGU-TRM-EPC-0488 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F2ED5231465A4720852048A1249519D3
DDCL | CCP-W-B114-02-ME-H21-0069 | HRSG_Level Indicator | D | D | 01 | _ |  | 2024-09-11 | 2024-11-11 | 2025-01-09 | 2025-02-09 | 2024-10-07 | 2024-10-07 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0488 | D | 01 | 2024-10-07 | 2024-10-10 | 2024-10-20 | CCP-PGU-TRM-EPC-0488 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0488 | D | 01 | 2024-10-07 | 2024-10-10 | 2024-10-20 | CCP-PGU-TRM-EPC-0488 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7B16B401A26545EF99AEAC621BCB7398
DDCL | CCP-W-B114-02-ME-H21-0071 | HRSG_Thermoelements | D | D | 01 | _ |  | 2024-09-11 | 2024-11-11 | 2025-01-09 | 2025-02-09 | 2024-10-07 | 2024-10-07 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0488 | D | 01 | 2024-10-07 | 2024-10-10 | 2024-10-20 | CCP-PGU-TRM-EPC-0488 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0488 | D | 01 | 2024-10-07 | 2024-10-10 | 2024-10-20 | CCP-PGU-TRM-EPC-0488 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:11A310E2ED6148A59389410E481D7674
DDCL | CCP-W-B114-02-ME-H21-0067 | HRSG_Pressure and Temperature Gauges | D | D | 01 | _ |  | 2024-09-11 | 2024-11-11 | 2025-01-09 | 2025-02-10 | 2024-11-07 | 2024-11-08 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0527 | D | 01 | 2024-11-08 | 2024-11-08 | 2024-11-18 | CCP-PGU-TRM-EPC-0527 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0527 | D | 01 | 2024-11-08 | 2024-11-08 | 2024-11-18 | CCP-PGU-TRM-EPC-0527 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B95B91F64E1347E4BF7CFC5CC273B382
DDCL | CCP-W-B114-02-ME-B15-0001 | HRSG_Thermal Insulation List | D | D | 01 | _ |  | 2024-09-11 | 2024-11-11 | 2025-01-09 | 2025-02-10 | 2024-11-07 | 2024-11-08 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0527 | D | 01 | 2024-11-08 | 2024-11-08 | 2024-11-18 | CCP-PGU-TRM-EPC-0527 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0527 | D | 01 | 2024-11-08 | 2024-11-08 | 2024-11-18 | CCP-PGU-TRM-EPC-0527 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:DDD34D1107F84B3FA236C0145C38F795
DDCL | CCP-W-B114-02-ME-B16-0045 | HRSG_Spec. & Drawing of Bypass Stack Silencer | D | D | 01 | _ |  | 2024-08-22 | 2024-10-23 | 2024-12-20 | 2025-01-20 | 2024-09-11 | 2024-09-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0475 | D | 01 | 2024-09-11 | 2024-09-12 | 2024-09-22 | CCP-PGU-TRM-EPC-0475 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0475 | D | 01 | 2024-09-11 | 2024-09-12 | 2024-09-22 | CCP-PGU-TRM-EPC-0475 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A4E6ECCB1DFE45A8BBF0EE90A1FF0F39
DDCL | CCP-W-B114-02-ME-E04-0093 | HRSG_Grounding System | D | D | 01 | _ |  | 2024-08-22 | 2024-10-23 | 2024-12-20 | 2025-01-20 | 2024-09-11 | 2024-09-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0475 | D | 01 | 2024-09-11 | 2024-09-12 | 2024-09-22 | CCP-PGU-TRM-EPC-0475 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0475 | D | 01 | 2024-09-11 | 2024-09-12 | 2024-09-22 | CCP-PGU-TRM-EPC-0475 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E6C77EBE7E764838832FE226479C3906
DDCL | CCP-W-B114-02-ME-B33-0034 | HRSG_Foundation - Exhaust Stack Template | D | D | 01 | _ |  | 2024-02-05 | 2024-04-15 | 2024-06-15 | 2024-07-14 | 2024-01-29 | 2024-04-08 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0126 | D | 01 | 2024-04-08 | 2024-04-08 | 2024-04-18 | CCP-PGU-TRM-EPC-0126 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0126 | D | 01 | 2024-04-08 | 2024-04-08 | 2024-04-18 | CCP-PGU-TRM-EPC-0126 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D60B03533A1F41C685E2E4F75B8FC439
DDCL | CCP-W-B114-02-ME-P01-0052 | HRSG_LB Piping Isometric Drawings - HP | D | D | 01 | _ |  | 2024-10-11 | 2024-12-11 | 2025-02-08 | 2025-03-08 | 2024-09-02 | 2024-09-09 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0472 | D | 01 | 2024-09-09 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0472 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0472 | D | 01 | 2024-09-09 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0472 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:22B1182990474B63A7B8DD2965C726F4
DDCL | CCP-W-B114-02-ME-P01-0053 | HRSG_LB Piping Isometric Drawings - LP | D | D | 01 | _ |  | 2024-10-11 | 2024-12-11 | 2025-02-08 | 2025-03-08 | 2024-09-02 | 2024-09-09 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0472 | D | 01 | 2024-09-09 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0472 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0472 | D | 01 | 2024-09-09 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0472 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:DAC3B094B1924B99A715FCF7D705A92B
DDCL | CCP-W-B114-02-ME-H04-0080 | HRSG_Hook Up Drawing | D | D | 01 | _ |  | 2024-06-13 | 2024-08-13 | 2024-10-11 | 2024-11-11 | 2024-05-27 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:23017CB4C57B4E6D98102116725D5A2C
DDCL | CCP-W-B114-02-ME-P05-0078 | HRSG_SB On-Off Valves - Assembly Drawings | D | D | 01 | _ |  | 2024-05-14 | 2024-07-14 | 2024-09-12 | 2024-10-12 | 2024-06-26 | 2024-06-27 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0223 | D | 01 | 2024-06-27 | 2024-06-28 | 2024-07-08 | CCP-PGU-TRM-EPC-0223 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0223 | D | 01 | 2024-06-27 | 2024-06-28 | 2024-07-08 | CCP-PGU-TRM-EPC-0223 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B7065D8F22404D4397E1EA6D19448016
DDCL | CCP-W-B114-02-ME-P05-0081 | HRSG_Drain Valves - Assembly Drawings | D | D | 01 | _ |  | 2024-08-12 | 2024-10-12 | 2024-12-10 | 2025-01-10 | 2024-09-06 | 2024-09-09 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0472 | D | 01 | 2024-09-09 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0472 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0472 | D | 01 | 2024-09-09 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0472 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:DB26F22484CA423DB7DD9BACD8EFE90F
DDCL | CCP-W-B114-02-ME-H21-0081 | HRSG_Spec. & Drawing of CEMS | D | D | 01 | _ |  | 2024-07-12 | 2024-09-12 | 2024-11-11 | 2024-12-11 | 2024-09-24 | 2024-09-24 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0483 | D | 01 | 2024-09-24 | 2024-09-25 | 2024-10-05 | CCP-PGU-TRM-EPC-0483 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0483 | D | 01 | 2024-09-24 | 2024-09-25 | 2024-10-05 | CCP-PGU-TRM-EPC-0483 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E07D050552B04FF3B5721B0DC6D3A312
DDCL | CCP-W-B114-02-ME-E14-0084 | HRSG_Low Voltage Panels | D | D | 01 | _ |  | 2024-06-13 | 2024-08-13 | 2024-10-11 | 2024-11-11 | 2024-07-12 | 2024-08-13 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0331 | D | 01 | 2024-08-13 | 2024-08-14 | 2024-08-24 | CCP-PGU-TRM-EPC-0331 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0331 | D | 01 | 2024-08-13 | 2024-08-14 | 2024-08-24 | CCP-PGU-TRM-EPC-0331 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:9DD16192365E4E828EE8B9AA16D9585E
DDCL | CCP-W-B114-02-ME-E04-0085 | HRSG_Lighting System | D | D | 01 | _ |  | 2024-06-13 | 2024-08-13 | 2024-10-11 | 2024-11-11 | 2024-05-23 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8FBE92361A234205BCD846091703E9BB
DDCL | CCP-W-B114-02-ME-E14-0086 | HRSG_Junction Boxes | D | D | 01 | _ |  | 2024-06-13 | 2024-08-13 | 2024-10-11 | 2024-11-11 | 2024-07-12 | 2024-08-13 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0331 | D | 01 | 2024-08-13 | 2024-08-14 | 2024-08-24 | CCP-PGU-TRM-EPC-0331 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0331 | D | 01 | 2024-08-13 | 2024-08-14 | 2024-08-24 | CCP-PGU-TRM-EPC-0331 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:49E227F25C4441E2810649B30C5B27AC
DDCL | CCP-W-B114-02-ME-E10-0087 | HRSG_Cable Schedule | D | D | 01 | _ |  | 2024-06-13 | 2024-08-13 | 2024-10-11 | 2024-11-11 | 2024-07-10 | 2024-08-13 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0331 | D | 01 | 2024-08-13 | 2024-08-14 | 2024-08-24 | CCP-PGU-TRM-EPC-0331 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0331 | D | 01 | 2024-08-13 | 2024-08-14 | 2024-08-24 | CCP-PGU-TRM-EPC-0331 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:001D0759BFF244849B03D92D36CE81D9
DDCL | CCP-W-B114-02-ME-E04-0089 | HRSG_Cable Tray | D | D | 01 | _ |  | 2024-06-13 | 2024-08-13 | 2024-10-11 | 2024-11-11 | 2024-07-10 | 2024-08-13 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0331 | D | 01 | 2024-08-13 | 2024-08-14 | 2024-08-24 | CCP-PGU-TRM-EPC-0331 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0331 | D | 01 | 2024-08-13 | 2024-08-14 | 2024-08-24 | CCP-PGU-TRM-EPC-0331 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E102721F6622473092CB21CD58DCD0DA
DDCL | CCP-W-B114-02-ME-H21-0074 | HRSG_Field Instruments | D | D | 01 | _ |  | 2024-07-12 | 2024-09-12 | 2024-11-11 | 2024-12-11 | 2024-08-20 | 2024-09-09 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0472 | D | 01 | 2024-09-09 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0472 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0472 | D | 01 | 2024-09-09 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0472 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:427C3073C95E4DE89EABDB2E546CB131
DDCL | CCP-W-B114-02-ME-P01-0054 | HRSG_SB Piping Isometric Drawings - HP | D | D | 01 | _ |  | 2024-10-11 | 2024-12-11 | 2025-02-08 | 2025-03-08 | 2024-09-02 | 2024-09-09 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0472 | D | 01 | 2024-09-09 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0472 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0472 | D | 01 | 2024-09-09 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0472 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:0ADC39AFFAD1408A98ADBEB278985F3C
DDCL | CCP-W-B114-02-ME-P02-0055 | HRSG_LB Pipe Supports - HP | D | D | 01 | _ |  | 2024-09-11 | 2024-11-11 | 2025-01-09 | 2025-02-09 | 2024-10-17 | 2024-10-17 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0492 | D | 01 | 2024-10-17 | 2024-10-21 | 2024-10-31 | CCP-PGU-TRM-EPC-0492 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0492 | D | 01 | 2024-10-17 | 2024-10-21 | 2024-10-31 | CCP-PGU-TRM-EPC-0492 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:77DE88C2766E4629BC2081DEF23A6A09
DDCL | CCP-W-B114-02-ME-P02-0056 | HRSG_SB Pipe Supports - HP | D | D | 01 | _ |  | 2024-09-11 | 2024-11-11 | 2025-01-09 | 2025-02-09 | 2024-10-17 | 2024-10-17 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0492 | D | 01 | 2024-10-17 | 2024-10-21 | 2024-10-31 | CCP-PGU-TRM-EPC-0492 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0492 | D | 01 | 2024-10-17 | 2024-10-21 | 2024-10-31 | CCP-PGU-TRM-EPC-0492 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7CABD80CD051480DA4B0B053DDD3C777
DDCL | CCP-W-B114-02-ME-B05-0057 | HRSG_LB Piping Arrangement | D | D | 01 | _ |  | 2024-08-12 | 2024-10-12 | 2024-12-10 | 2025-01-10 | 2024-09-24 | 2024-09-24 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0483 | D | 01 | 2024-09-24 | 2024-09-25 | 2024-10-05 | CCP-PGU-TRM-EPC-0483 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0483 | D | 01 | 2024-09-24 | 2024-09-25 | 2024-10-05 | CCP-PGU-TRM-EPC-0483 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:9E813FA44E9342E2953522FFC474B91A
DDCL | CCP-W-B114-02-ME-P99-0059 | HRSG_Filters Data Sheet | D | D | 01 | _ |  | 2024-07-12 | 2024-09-12 | 2024-11-11 | 2024-12-11 | 2024-08-20 | 2024-09-09 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0472 | D | 01 | 2024-09-09 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0472 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0472 | D | 01 | 2024-09-09 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0472 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C6FBE62E0BBA4FF99FF32E9EF42F7C63
DDCL | CCP-W-B114-02-ME-P04-0060 | HRSG_Piping Class Specification | D | D | 01 | _ |  | 2024-03-15 | 2024-05-15 | 2024-07-15 | 2024-08-13 | 2024-04-09 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4C726E2C9E224DE9A285FE0FBFE53203
DDCL | CCP-W-B114-02-ME-P10-0061 | HRSG_Valves List | D | D | 01 | _ |  | 2024-02-05 | 2024-04-15 | 2024-06-15 | 2024-07-14 | 2024-03-12 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2490EE5BE5E744CBBC91298B600CE19F
DDCL | CCP-W-B114-02-ME-P14-0062 | HRSG_Lines List | D | D | 01 | _ |  | 2024-02-05 | 2024-04-15 | 2024-06-15 | 2024-07-14 | 2024-03-12 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2449F58770944E1D82861771D70149EE
DDCL | CCP-W-B114-02-ME-A07-0064 | HRSG_Control and Automation Description | D | D | 01 | _ |  | 2024-03-15 | 2024-05-15 | 2024-07-15 | 2024-08-13 | 2024-04-09 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5A86677B4A1E409B98DB64B53297F540
DDCL | CCP-W-B114-02-ME-H20-0068 | HRSG_Instrument List | D | D | 01 | _ |  | 2024-03-05 | 2024-05-05 | 2024-07-05 | 2024-08-03 | 2024-03-29 | 2024-06-10 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0175 | D | 01 | 2024-06-10 | 2024-06-11 | 2024-06-21 | CCP-PGU-TRM-EPC-0175 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0175 | D | 01 | 2024-06-10 | 2024-06-11 | 2024-06-21 | CCP-PGU-TRM-EPC-0175 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6B1472D9DE2B465DA3C358BA2852DDDB
DDCL | CCP-W-B114-02-ME-H09-0070 | HRSG_Control and Automation Diagram | D | D | 01 | _ |  | 2024-07-12 | 2024-09-12 | 2024-11-11 | 2024-12-11 | 2024-08-20 | 2024-09-09 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0472 | D | 01 | 2024-09-09 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0472 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0472 | D | 01 | 2024-09-09 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0472 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5E635557FF08434A9397608FF873767E
DDCL | CCP-W-B114-02-ME-P05-0072 | HRSG_LB On-Off Valves – Actuator Datasheet | D | D | 01 | _ |  | 2024-05-14 | 2024-07-14 | 2024-09-12 | 2024-10-12 | 2024-05-03 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:AC5BCBEEC7B047CCB826A552C3714AB9
DDCL | CCP-W-B114-02-ME-P05-0073 | HRSG_LB On-Off Valves - Wiring and Pneumatic Diagram | D | D | 01 | _ |  | 2024-08-12 | 2024-10-12 | 2024-12-10 | 2025-01-10 | 2024-05-03 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E3DD7C85F211424691DE707564291BBC
DDCL | CCP-W-B114-02-ME-E14-0078 | HRSG_Aircraft Warning Lights | D | D | 01 | _ |  | 2024-06-13 | 2024-08-13 | 2024-10-11 | 2024-11-11 | 2024-06-03 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A85C5BA6BA034D30B7FE9911B6B76313
DDCL | CCP-W-B114-02-ME-H04-0079 | HRSG_Instrument Air Distribution Layout | D | D | 01 | _ |  | 2024-06-13 | 2024-08-13 | 2024-10-11 | 2024-11-11 | 2024-05-23 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:82DD99E267944C328CB534BF98730820
DDCL | CCP-W-B114-02-ME-H05-1010 | HRSG_Diverter Damper - HPU General Assembly | D | D | 01 | _ |  | 2024-06-13 | 2024-08-13 | 2024-10-11 | 2024-11-11 | 2024-04-18 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:51EA25AA01274816A8DFF78DC413356A
DDCL | CCP-W-B114-02-ME-E02-1012 | HRSG_Diverter Damper - HPU, PLC Wiring Diagram & Drawing | D | D | 01 | _ |  | 2024-06-13 | 2024-08-13 | 2024-10-11 | 2024-11-11 | 2024-05-29 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7EC5E62364BB405F9E52784B8E8AA2D9
DDCL | CCP-W-B114-02-ME-P10-1013 | HRSG_Diverter Damper - Valves List | D | D | 01 | _ |  | 2024-06-13 | 2024-08-13 | 2024-10-11 | 2024-11-11 | 2024-06-17 | 2024-06-17 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0196 | D | 01 | 2024-06-17 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0196 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0196 | D | 01 | 2024-06-17 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0196 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:EB421B63972345C5853C158F177A6169
DDCL | CCP-W-B114-02-ME-H20-1014 | HRSG_Diverter Damper - Instrument List | D | D | 01 | _ |  | 2024-06-13 | 2024-08-13 | 2024-10-11 | 2024-11-11 | 2024-04-18 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:48434DD24B33476185E133EBEF87E054
DDCL | CCP-W-B114-02-ME-H21-1015 | HRSG_Diverter Damper - Instrument Data Sheet | D | D | 01 | _ |  | 2024-06-13 | 2024-08-13 | 2024-10-11 | 2024-11-11 | 2024-07-17 | 2024-08-13 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0331 | D | 01 | 2024-08-13 | 2024-08-14 | 2024-08-24 | CCP-PGU-TRM-EPC-0331 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0331 | D | 01 | 2024-08-13 | 2024-08-14 | 2024-08-24 | CCP-PGU-TRM-EPC-0331 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:414A8725F44B4712B7C99D1F44E45382
DDCL | CCP-W-B114-02-ME-H09-1017 | HRSG_Diverter Damper - Control and Protection Logic Diagrams | D | D | 01 | _ |  | 2024-06-13 | 2024-08-13 | 2024-10-11 | 2024-11-11 | 2024-04-18 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C31679FD068F496AB53B59D35DFE4E4B
DDCL | CCP-W-B114-02-ME-A07-0001 | HRSG_Performance and Operational Data | D | D | 01 | _ |  | 2023-12-07 | 2024-02-15 | 2024-04-15 | 2024-05-15 | 2024-06-11 | 2024-06-14 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0186 | D | 01 | 2024-06-14 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0186 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0186 | D | 01 | 2024-06-14 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0186 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:53DC8239DF754C04B19D72BFB002BDC1
DDCL | CCP-W-B114-02-ME-B06-0003 | HRSG_P&ID - Exhaust Gas System | D | D | 01 | _ |  | 2024-01-08 | 2024-03-22 | 2024-05-20 | 2024-06-20 | 2024-02-21 | 2024-05-07 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0140 | D | 01 | 2024-05-07 | 2024-05-08 | 2024-05-18 | CCP-PGU-TRM-EPC-0140 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0140 | D | 01 | 2024-05-07 | 2024-05-08 | 2024-05-18 | CCP-PGU-TRM-EPC-0140 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4998337B3D394CB6967A21A2C2285012
DDCL | CCP-W-B114-02-ME-B06-0004 | HRSG_P&ID - HP SH System | D | D | 01 | _ |  | 2024-01-08 | 2024-03-22 | 2024-05-20 | 2024-06-20 | 2024-02-21 | 2024-05-07 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0140 | D | 01 | 2024-05-07 | 2024-05-08 | 2024-05-18 | CCP-PGU-TRM-EPC-0140 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0140 | D | 01 | 2024-05-07 | 2024-05-08 | 2024-05-18 | CCP-PGU-TRM-EPC-0140 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C61F889BB83C4D5FBA10BD6B9BF7E1E8
DDCL | CCP-W-B114-02-ME-B06-0005 | HRSG_P&ID - HP EVA System | D | D | 01 | _ |  | 2024-01-08 | 2024-03-22 | 2024-05-20 | 2024-06-20 | 2024-02-21 | 2024-05-07 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0140 | D | 01 | 2024-05-07 | 2024-05-08 | 2024-05-18 | CCP-PGU-TRM-EPC-0140 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0140 | D | 01 | 2024-05-07 | 2024-05-08 | 2024-05-18 | CCP-PGU-TRM-EPC-0140 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B13E288188614CB4A4AA97793EA80E6C
DDCL | CCP-W-B114-02-ME-B06-0006 | HRSG_P&ID - HP ECO System | D | D | 01 | _ |  | 2024-01-08 | 2024-03-22 | 2024-05-20 | 2024-06-20 | 2024-02-21 | 2024-05-07 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0140 | D | 01 | 2024-05-07 | 2024-05-08 | 2024-05-18 | CCP-PGU-TRM-EPC-0140 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0140 | D | 01 | 2024-05-07 | 2024-05-08 | 2024-05-18 | CCP-PGU-TRM-EPC-0140 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:84EC302BC6BA43CA893F8607337D9472
DDCL | CCP-W-B114-02-ME-B06-0007 | HRSG_P&ID - LP SH System | D | D | 01 | _ |  | 2024-01-08 | 2024-03-22 | 2024-05-20 | 2024-06-20 | 2024-02-21 | 2024-05-07 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0140 | D | 01 | 2024-05-07 | 2024-05-08 | 2024-05-18 | CCP-PGU-TRM-EPC-0140 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0140 | D | 01 | 2024-05-07 | 2024-05-08 | 2024-05-18 | CCP-PGU-TRM-EPC-0140 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:EF767D296C604B23A9187E92A1137454
DDCL | CCP-W-B114-02-ME-B06-0008 | HRSG_P&ID - LP EVA System | D | D | 01 | _ |  | 2024-01-08 | 2024-03-22 | 2024-05-20 | 2024-06-20 | 2024-02-21 | 2024-05-07 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0140 | D | 01 | 2024-05-07 | 2024-05-08 | 2024-05-18 | CCP-PGU-TRM-EPC-0140 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0140 | D | 01 | 2024-05-07 | 2024-05-08 | 2024-05-18 | CCP-PGU-TRM-EPC-0140 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8D0C0A8C5320403BA93F3058167A55AD
DDCL | CCP-W-B114-02-ME-B06-0009 | HRSG_P&ID - Feedwater HTR System | D | D | 01 | _ |  | 2024-01-08 | 2024-03-22 | 2024-05-20 | 2024-06-20 | 2024-02-21 | 2024-05-07 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0140 | D | 01 | 2024-05-07 | 2024-05-08 | 2024-05-18 | CCP-PGU-TRM-EPC-0140 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0140 | D | 01 | 2024-05-07 | 2024-05-08 | 2024-05-18 | CCP-PGU-TRM-EPC-0140 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4FC575844DF74D2CB655EBA6A5E18856
DDCL | CCP-W-B114-02-ME-B06-0010 | HRSG_P&ID - Utility System | D | D | 01 | _ |  | 2024-01-08 | 2024-03-22 | 2024-05-20 | 2024-06-20 | 2024-02-21 | 2024-05-07 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0140 | D | 01 | 2024-05-07 | 2024-05-08 | 2024-05-18 | CCP-PGU-TRM-EPC-0140 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0140 | D | 01 | 2024-05-07 | 2024-05-08 | 2024-05-18 | CCP-PGU-TRM-EPC-0140 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:9484FAAC250342558C9886D4A4BF1A0F
DDCL | CCP-W-B114-02-ME-A07-0011 | HRSG_Blowdown Tanks Sizing | D | D | 01 | _ |  | 2024-02-05 | 2024-04-15 | 2024-06-15 | 2024-07-14 | 2024-03-12 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:0F94AB9690A94AD6BAF4A0385D1AB2CF
DDCL | CCP-W-B114-02-ME-B05-0014 | HRSG_Pressure Part General Assembly | D | D | 02 | _ |  | 2024-01-08 | 2024-03-22 | 2024-05-20 | 2024-06-20 | 2024-01-30 | 2024-06-14 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0186 | D | 02 | 2024-06-14 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0186 | D | 02 | Deemed Approved | CCP-EPC-TRM-PGU-0116 | D | 01 | 2024-03-25 | 2024-03-25 | 2024-04-02 | CCP-PGU-TRM-EPC-0116 | Approved With Comment | CCP-EPC-TRM-PGU-0186 | D | 02 | 2024-06-14 | 2024-06-17 | 2024-06-27 | CCP-PGU-TRM-EPC-0186 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:183B2559E5D04D0A97ADEA54F0E2D2B0
DDCL | CCP-W-B114-02-ME-B05-0015 | HRSG_HP Drum Drawings | D | D | 01 | _ |  | 2024-05-14 | 2024-07-14 | 2024-09-12 | 2024-10-12 | 2024-04-22 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1EC78591F1B54BB999DCF6CA0821FA0B
DDCL | CCP-W-B114-02-ME-B05-0021 | HRSG_Continuous Blowdown Tank Drawings | D | D | 01 | _ |  | 2024-04-15 | 2024-06-14 | 2024-08-12 | 2024-09-12 | 2024-06-03 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CF636DB1A8224D0EB91D84B93DDF6D5A
DDCL | CCP-W-B114-02-ME-B05-0022 | HRSG_Atmospheric Blowdown Tank Drawings | D | D | 01 | _ |  | 2024-04-15 | 2024-06-14 | 2024-08-12 | 2024-09-12 | 2024-06-03 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D9E98D2DF220488DBB138094446EE4E1
DDCL | CCP-W-B114-02-ME-F01-0026 | HRSG_Job Themal Data Sheet | D | D | 01 | _ |  | 2024-01-08 | 2024-03-22 | 2024-05-20 | 2024-06-20 | 2024-01-25 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:9E360737B4F54380AEE6F3F8C025C54C
DDCL | CCP-W-B114-02-ME-P05-0027 | HRSG_Control Valves and Desuperheater | D | D | 01 | _ |  | 2024-05-14 | 2024-07-14 | 2024-09-12 | 2024-10-12 | 2024-04-16 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7B6B0C22DE5645BE96F8916B45BB8700
DDCL | CCP-W-B114-02-ME-B16-0028 | HRSG_Spec. & Drawing of Drain Pump | D | D | 01 | _ |  | 2024-05-14 | 2024-07-14 | 2024-09-12 | 2024-10-12 | 2024-04-16 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2586412A183C4A5D8D5571119E0DF94C
DDCL | CCP-W-B114-02-ME-P05-0032 | HRSG_Safety and Relief Valves | D | D | 01 | _ |  | 2024-05-14 | 2024-07-14 | 2024-09-12 | 2024-10-12 | 2024-04-22 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:84031ECD4542428FB3DDF63796FB0FD2
DDCL | CCP-W-B114-02-ME-B16-0030 | HRSG_Spec. & Drawing of Exhaust Stack Damper | D | D | 01 | _ |  | 2024-05-14 | 2024-07-14 | 2024-09-12 | 2024-10-12 | 2024-04-16 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2E3B37D9E89F41CC914664470A868882
DDCL | CCP-W-B114-02-ME-B16-0031 | HRSG_Spec. & Drawing of Steam Silencer | D | D | 01 | _ |  | 2024-05-14 | 2024-07-14 | 2024-09-12 | 2024-10-12 | 2024-04-16 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B2A65A70191C42FDBE78B2790428026B
DDCL | CCP-W-B114-02-ME-B16-0032 | HRSG_Spec. & Drawing of Deaerator | D | D | 01 | _ |  | 2024-06-13 | 2024-08-13 | 2024-10-11 | 2024-11-11 | 2024-04-24 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:78061E7CD78645EA8C9988470C9AB693
DDCL | CCP-W-B114-02-ME-B06-1001 | HRSG_Diverter Damper - P&ID | D | D | 01 | _ |  | 2024-06-13 | 2024-08-13 | 2024-10-11 | 2024-11-11 | 2024-04-18 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:62274986BA434642A0362F0D0AE4E76F
DDCL | CCP-W-B114-02-ME-A07-1002 | HRSG_Diverter Damper - Functional and Protection Description | D | D | 01 | _ |  | 2024-06-13 | 2024-08-13 | 2024-10-11 | 2024-11-11 | 2024-04-18 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:0E2FF83F80C0475EA6A3C0FDD170EC70
DDCL | CCP-W-B114-02-ME-B33-1003 | HRSG_Diverter Damper - Foundation Loads and Details | D | D | 01 | _ |  | 2024-06-13 | 2024-08-13 | 2024-10-11 | 2024-11-11 | 2024-05-30 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0176 | D | 01 | 2024-06-11 | 2024-06-11 | 2024-06-21 | CCP-PGU-TRM-EPC-0176 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0176 | D | 01 | 2024-06-11 | 2024-06-11 | 2024-06-21 | CCP-PGU-TRM-EPC-0176 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:0882A0CA93C6434D8C0294C376C46C49
DDCL | CCP-W-B114-02-ME-B33-1004 | HRSG_Diverter Damper - Seal Air Fan | D | D | 01 | _ |  | 2024-06-13 | 2024-08-13 | 2024-10-11 | 2024-11-11 | 2024-04-18 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:0520DFAD866243B382FD13BF8EFD6899
DDCL | CCP-W-B114-02-ME-B05-1005 | HRSG_Diverter Damper - General Assembly | D | D | 01 | _ |  | 2024-06-13 | 2024-08-13 | 2024-10-11 | 2024-11-11 | 2024-04-18 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3C9E3FD5CAC744F6B8B8140F427202F9
DDCL | CCP-W-B114-02-ME-B05-1006 | HRSG_Diverter Damper - HPU | D | D | 01 | _ |  | 2024-06-13 | 2024-08-13 | 2024-10-11 | 2024-11-11 | 2024-04-18 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B6D2AF5BAF344710A271420984B1230C
DDCL | CCP-W-B114-02-ME-B05-1007 | HRSG_Diverter Damper - Data Sheet | D | D | 01 | _ |  | 2024-06-13 | 2024-08-13 | 2024-10-11 | 2024-11-11 | 2024-04-18 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7791398FB30C4A77A2760629DAA29053
DDCL | CCP-W-B114-02-ME-B05-0034 | HRSG_Spec. & Drawing of Hoist | D | D | 01 | _ |  | 2024-09-11 | 2024-11-11 | 2025-01-09 | 2025-02-09 | 2025-02-04 | 2025-02-04 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0854 | D | 01 | 2025-02-05 | 2025-02-05 | 2025-02-10 | CCP-PGU-TRM-EPC-0854 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0854 | D | 01 | 2025-02-05 | 2025-02-05 | 2025-02-10 | CCP-PGU-TRM-EPC-0854 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4AADFD29D9A54354B0CB07F5C4078D16
DDCL | CCP-W-B114-02-ME-B16-0035 | HRSG_Spec. & Drawing of Recirculation Pump | D | D | 01 | _ |  | 2024-05-14 | 2024-07-14 | 2024-09-12 | 2024-10-12 | 2024-04-16 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:9C2F87410C524380A2EE308A8A673101
DDCL | CCP-W-B114-02-ME-B33-0036 | HRSG_Foundation - Footprint Main Loads | D | D | 01 | _ |  | 2024-02-05 | 2024-04-15 | 2024-06-15 | 2024-07-14 | 2024-03-12 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D9EC8D6848564A65A24ACE71BE975456
DDCL | CCP-W-B114-02-ME-B33-0037 | HRSG_Foundation - Loads Table | D | D | 01 | _ |  | 2024-02-05 | 2024-04-15 | 2024-06-15 | 2024-07-14 | 2024-03-12 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3C28947E73E64CE2B73B5AF3CFBC3146
DDCL | CCP-W-B114-02-ME-B33-0038 | HRSG_Foundation - Assembly and Detail Drawings | D | D | 01 | _ |  | 2024-02-05 | 2024-04-15 | 2024-06-15 | 2024-07-14 | 2024-01-29 | 2024-04-08 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0126 | D | 01 | 2024-04-08 | 2024-04-08 | 2024-04-18 | CCP-PGU-TRM-EPC-0126 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0126 | D | 01 | 2024-04-08 | 2024-04-08 | 2024-04-18 | CCP-PGU-TRM-EPC-0126 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:40506C73BD664613AF8DB936F3BF1806
DDCL | CCP-W-B114-02-ME-B33-0039 | HRSG_Foundation - Exhaust Stack | D | D | 01 | _ |  | 2024-02-05 | 2024-04-15 | 2024-06-15 | 2024-07-14 | 2024-01-29 | 2024-04-08 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0126 | D | 01 | 2024-04-08 | 2024-04-08 | 2024-04-18 | CCP-PGU-TRM-EPC-0126 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0126 | D | 01 | 2024-04-08 | 2024-04-08 | 2024-04-18 | CCP-PGU-TRM-EPC-0126 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:994821185AED4E9EA0106866F2CA26A4
DDCL | CCP-W-B114-02-ME-D02-0040 | HRSG_Secondary Structure Basic Drawing | D | D | 01 | _ |  | 2024-03-15 | 2024-05-15 | 2024-07-15 | 2024-08-13 | 2024-04-09 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1C81694CCDFD4A42A11FB7BE8BD240DC
DDCL | CCP-W-B114-02-ME-B01-0044 | HRSG_General Arrangement | D | D | 01 | _ |  | 2024-01-08 | 2024-03-22 | 2024-05-20 | 2024-06-20 | 2024-02-22 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8AF24A72914E4032AD2668580DB45D11
DDCL | CCP-W-B114-02-ME-B01-0045 | HRSG_Name Plate | D | D | 01 | _ |  | 2024-05-21 | 2024-07-21 | 2024-09-20 | 2024-10-31 | 2024-06-17 | 2024-06-17 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0196 | D | 01 | 2024-06-17 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0196 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0196 | D | 01 | 2024-06-17 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0196 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A93331F0BC3442889C6F3A484E2DB601
DDCL | CCP-W-B114-02-ME-B05-0049 | HRSG_Arrangement of Casing | D | D | 01 | _ |  | 2024-04-15 | 2024-06-14 | 2024-08-12 | 2024-09-12 | 2024-04-09 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A7687F3C5E8F49C6BE0BED613787FEB0
DDCL | CCP-W-B114-02-ME-B05-0051 | HRSG_Exhaust Stack General Assembly | D | D | 01 | _ |  | 2024-04-15 | 2024-06-14 | 2024-08-12 | 2024-09-12 | 2024-04-09 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B2F14F20B324499DB93B5AB2ABE4AB6E
DDCL | CCP-W-B114-02-ME-B05-0052 | HRSG_Bypass Stack General Assembly | D | D | 01 | _ |  | 2024-04-15 | 2024-06-14 | 2024-08-12 | 2024-09-12 | 2024-04-09 | 2024-06-11 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0179 | D | 01 | 2024-06-11 | 2024-06-14 | 2024-06-24 | CCP-PGU-TRM-EPC-0179 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CDAFC735495D44629E6AA4B11806E52F
DDCL | CCP-W-B114-02-ME-B33-0040 | HRSG_Foundation - Stairtower | D | D | 01 | _ |  | 2024-02-05 | 2024-04-15 | 2024-06-15 | 2024-07-14 | 2024-01-29 | 2024-04-08 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0126 | D | 01 | 2024-04-08 | 2024-04-08 | 2024-04-18 | CCP-PGU-TRM-EPC-0126 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0126 | D | 01 | 2024-04-08 | 2024-04-08 | 2024-04-18 | CCP-PGU-TRM-EPC-0126 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:BDDC50679BC344FB99FD927D7536566C
DDCL | CCP-W-B114-02-ME-B33-0041 | HRSG_Foundation - Bypass Stack | D | D | 01 | _ |  | 2024-02-05 | 2024-04-15 | 2024-06-15 | 2024-07-14 | 2024-01-29 | 2024-04-08 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0126 | D | 01 | 2024-04-08 | 2024-04-08 | 2024-04-18 | CCP-PGU-TRM-EPC-0126 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0126 | D | 01 | 2024-04-08 | 2024-04-08 | 2024-04-18 | CCP-PGU-TRM-EPC-0126 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D65F318AAF644BCEA4E7E2A7B4BD59B3
DDCL | CCP-W-B114-02-ME-P05-0076 | HRSG_SB On-Off Valves - Actuator Datasheet | D | D | 01 | _ |  | 2024-05-14 | 2024-07-14 | 2024-09-12 | 2024-10-12 | 2024-06-26 | 2024-06-27 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0223 | D | 01 | 2024-06-27 | 2024-06-28 | 2024-07-08 | CCP-PGU-TRM-EPC-0223 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0223 | D | 01 | 2024-06-27 | 2024-06-28 | 2024-07-08 | CCP-PGU-TRM-EPC-0223 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:77F0A4B1B7F14BD7B937CBC0DB0AFE64
DDCL | CCP-W-B114-02-ME-P05-0077 | HRSG_SB On-Off Valves - Wiring Diagram | D | D | 01 | _ |  | 2024-05-14 | 2024-07-14 | 2024-09-12 | 2024-10-12 | 2024-06-26 | 2024-06-27 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0223 | D | 01 | 2024-06-27 | 2024-06-28 | 2024-07-08 | CCP-PGU-TRM-EPC-0223 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0223 | D | 01 | 2024-06-27 | 2024-06-28 | 2024-07-08 | CCP-PGU-TRM-EPC-0223 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1EC450D9571B4C9F843C129E6144733B
DDCL | CCP-W-B114-02-ME-P05-0079 | HRSG_Drain Valves - Actuator Datasheet | D | D | 01 | _ |  | 2024-08-12 | 2024-10-12 | 2024-12-10 | 2025-01-10 | 2024-09-06 | 2024-09-09 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0472 | D | 01 | 2024-09-09 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0472 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0472 | D | 01 | 2024-09-09 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0472 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:DCC12A5AC2754BACAA17947FA0144366
DDCL | CCP-W-B114-02-ME-P05-0080 | HRSG_Drain Valves - Wiring Diagram | D | D | 01 | _ |  | 2024-08-12 | 2024-10-12 | 2024-12-10 | 2025-01-10 | 2024-09-06 | 2024-09-09 |  |  | BOP Plant | Plant EPC)주기기기술팀 | HRSG | Mechanical | 오슬기 | [10 empty] | CCP-EPC-TRM-PGU-0472 | D | 01 | 2024-09-09 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0472 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0472 | D | 01 | 2024-09-09 | 2024-09-11 | 2024-09-21 | CCP-PGU-TRM-EPC-0472 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:554D9B88181B4C778D11ED8D59D70260
DDCL | CCP-W-B044-25-ME-P99-0003 | FGSS_OVERALL LAYOUT FOR FGSS AREA | D | D | 01 | _ |  | 2024-05-17 | 2024-05-31 | 2024-09-30 | 2024-11-19 | 2024-05-02 | 2024-06-27 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0230 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0230 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0230 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0230 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D8D51F0626AE4B589156286117461004
DDCL | CCP-W-B044-25-ME-B33-0002 | FGSS_FOUNDATION DRAWING INCLUDING LOADINGS FOR GT AREA | D | D | 01 | _ |  | 2024-06-29 | 2024-07-13 | 2024-10-06 | 2024-10-13 | 2024-07-11 | 2024-07-11 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0258 | D | 01 | 2024-07-11 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0258 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0258 | D | 01 | 2024-07-11 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0258 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E52D47E9C0AE4461AAF0CD8F721A6824
DDCL | CCP-W-B044-25-ME-H99-0001 | FGSS_TECHNICAL SPECIFICATION FOR GAS LEAKAGE DETECTOR | D | D | 01 | _ |  | 2024-08-27 | 2024-09-10 | 2025-01-03 | 2025-01-10 | 2024-09-03 | 2024-09-03 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0458 | D | 01 | 2024-09-03 | 2024-09-06 | 2024-09-16 | CCP-PGU-TRM-EPC-0458 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0458 | D | 01 | 2024-09-03 | 2024-09-06 | 2024-09-16 | CCP-PGU-TRM-EPC-0458 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A9BC2589C9E34E02910C3C3E5BD6BA66
DDCL | CCP-W-B044-25-ME-E22-0001 | FGSS_TECHNICAL SPECIFICATION FOR ELECTRICAL HEAT TRACING | D | D | 01 | _ |  | 2025-02-01 | 2025-02-15 | 2025-05-08 | 2025-05-15 | 2025-02-10 | 2025-02-10 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0856 | D | 01 | 2025-02-12 | 2025-02-13 | 2025-02-23 | CCP-PGU-TRM-EPC-0856 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0856 | D | 01 | 2025-02-12 | 2025-02-13 | 2025-02-23 | CCP-PGU-TRM-EPC-0856 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:27E92239744D4EA08988DC74578EC99B
DDCL | CCP-W-B044-25-ME-P04-0001 | FGSS_PIPING MATERIAL SPECIFICATION | D | D | 01 | _ |  | 2024-03-15 | 2024-03-30 | 2024-07-22 | 2024-07-30 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0258 | D | 01 | 2024-07-11 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0258 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0258 | D | 01 | 2024-07-11 | 2024-07-16 | 2024-07-26 | CCP-PGU-TRM-EPC-0258 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A85473BE0A7B49CC9CF45D5DBF4ECEB2
DDCL | CCP-W-B044-25-ME-H99-0003 | FGSS_PLC SPECIFICATION | D | D | 01 | _ |  | 2024-03-28 | 2024-04-30 | 2024-06-30 | 2024-07-30 | 2024-03-28 | 2024-06-27 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0229 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0229 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0229 | D | 01 | 2024-06-28 | 2024-07-02 | 2024-07-12 | CCP-PGU-TRM-EPC-0229 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6020AB712B50489884704A9CEF5A1B92
DDCL | CCP-W-B044-25-ME-H99-0006 | FGSS_INSTRUMENT LOCATION DRAWING | D | D | 01 | _ |  | 2025-02-01 | 2025-02-15 | 2025-05-08 | 2025-05-15 | 2025-02-10 | 2025-02-10 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0856 | D | 01 | 2025-02-12 | 2025-02-13 | 2025-02-23 | CCP-PGU-TRM-EPC-0856 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0856 | D | 01 | 2025-02-12 | 2025-02-13 | 2025-02-23 | CCP-PGU-TRM-EPC-0856 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8C9990860CFB4CC3A7259BA952A8AE9C
DDCL | CCP-W-B044-25-ME-H24-0001 | FGSS_INSTRUMENT HOOKUP DRAWING | D | D | 01 | _ |  | 2025-02-01 | 2025-02-15 | 2025-05-08 | 2025-05-15 | 2025-02-10 | 2025-02-10 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0856 | D | 01 | 2025-02-12 | 2025-02-13 | 2025-02-23 | CCP-PGU-TRM-EPC-0856 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0856 | D | 01 | 2025-02-12 | 2025-02-13 | 2025-02-23 | CCP-PGU-TRM-EPC-0856 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:571868D8082F4541A84FFFFFE4012B17
DDCL | CCP-W-B044-25-ME-E02-0001 | FGSS_PLC CONTROL CABINET PANEL WIRING DIAGRAM | D | D | 01 | A |  | 2024-09-29 | 2024-10-13 | 2025-01-06 | 2025-01-13 | 2024-09-12 | 2024-09-13 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Gas Supply System_VENDOR | Mechanical | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0495 | D | 01 | 2024-10-29 | 2024-10-29 | 2024-11-08 | CCP-PGU-TRM-EPC-0495 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0495 | D | 01 | 2024-10-29 | 2024-10-29 | 2024-11-08 | CCP-PGU-TRM-EPC-0495 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2B843E523A88471FB342F2436B943F40
DDCL | CCP-W-B042-21-ME-B16-0005 | Technical Data Sheet for Chemical Dosing System | D | D | 01 | _ |  | 2024-01-20 | 2024-02-20 | 2024-04-20 | 2024-05-20 | 2024-03-15 | 2024-05-10 |  |  | BOP Plant | Plant EPC)기계기술2팀 | Chemical Dosing Skid | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0144 | D | 01 | 2024-05-13 | 2024-05-13 | 2024-05-23 | CCP-PGU-TRM-EPC-0144 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0144 | D | 01 | 2024-05-13 | 2024-05-13 | 2024-05-23 | CCP-PGU-TRM-EPC-0144 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5704B1B174314AECB1B3CC03E35D7D37
DDCL | CCP-W-B042-21-ME-D08-0014 | Foundation Drawing for Chemical Dosing System | D | C | 01 | _ |  | 2025-03-16 | 2025-03-30 | 2025-04-20 | 2025-05-20 | 2025-04-04 |  | 2025-05-26 | 2025-05-27 | BOP Plant | Plant EPC)기계기술2팀 | Chemical Dosing Skid | Mechanical | 김준영 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E8AE94CA989A42A78FFAE47AEC52CED8
DDCL | CCP-W-B042-21-ME-B18-0007 | Instrument List for Chemical Dosing System | D | D | 01 | _ |  | 2024-01-20 | 2024-02-20 | 2024-04-20 | 2024-05-20 | 2024-03-15 | 2024-05-10 |  |  | BOP Plant | Plant EPC)기계기술2팀 | Chemical Dosing Skid | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0144 | D | 01 | 2024-05-13 | 2024-05-13 | 2024-05-23 | CCP-PGU-TRM-EPC-0144 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0144 | D | 01 | 2024-05-13 | 2024-05-13 | 2024-05-23 | CCP-PGU-TRM-EPC-0144 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:9B513C813C6E4DFDA436B6CE92EF5ECE
DDCL | CCP-W-B042-21-EL-E29-0009 | Control Configuration DIAgram for Chemical Dosing System | D | D | 01 | _ |  | 2024-01-20 | 2024-02-20 | 2024-04-20 | 2024-05-20 | 2024-03-15 | 2024-06-14 |  |  | BOP Plant | Plant EPC)기계기술2팀 | Chemical Dosing Skid | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0190 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0190 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0190 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0190 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:48E31750F6FA45FB92C21D6C8F839797
DDCL | CCP-W-B042-21-EL-E04-0013 | Raceway Plan Drawing for Chemical Dosing System | D | D | 01 | _ |  | 2024-01-20 | 2024-02-20 | 2024-04-20 | 2024-05-20 | 2024-03-15 | 2024-06-14 |  |  | BOP Plant | Plant EPC)기계기술2팀 | Chemical Dosing Skid | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0190 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0190 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0190 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0190 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:9241DA5250574751A53CC76FE8DF5E5E
DDCL | CCP-W-B042-21-EL-E03-0011 | Schematic & Wiring Diagram for Chemical Dosing System | D | D | 01 | _ |  | 2024-01-20 | 2024-02-20 | 2024-04-20 | 2024-05-20 | 2024-03-15 | 2024-06-14 |  |  | BOP Plant | Plant EPC)기계기술2팀 | Chemical Dosing Skid | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0190 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0190 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0190 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0190 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7498D7F4AEA24406B56B068C3D996044
DDCL | CCP-W-B042-21-IA-E09-0010 | Control Loop & Logic Diagram for Chemical Dosing System | D | D | 01 | _ |  | 2024-01-20 | 2024-02-20 | 2024-04-20 | 2024-05-20 | 2024-03-15 | 2024-06-14 |  |  | BOP Plant | Plant EPC)기계기술2팀 | Chemical Dosing Skid | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0190 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0190 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0190 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0190 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:0C68A5F66F7F421A9BAEAE37895B40DC
DDCL | CCP-W-B042-21-EL-E29-0008 | Control Panel Layout Drawing for Chemical Dosing System | D | D | 01 | _ |  | 2024-01-20 | 2024-02-20 | 2024-04-20 | 2024-05-20 | 2024-03-15 | 2024-06-14 |  |  | BOP Plant | Plant EPC)기계기술2팀 | Chemical Dosing Skid | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0190 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0190 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0190 | D | 01 | 2024-06-14 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0190 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:DA1796E587944A00860FCC3FFE48A0F0
DDCL | CCP-W-B042-21-ME-B01-0012 | Piping Arrangement Drawing for Chemical Dosing System | D | D | 01 | _ |  | 2024-01-20 | 2024-02-20 | 2024-04-20 | 2024-05-20 | 2024-03-15 | 2024-05-10 |  |  | BOP Plant | Plant EPC)기계기술2팀 | Chemical Dosing Skid | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0144 | D | 01 | 2024-05-13 | 2024-05-13 | [5 empty] | CCP-EPC-TRM-PGU-0144 | D | 01 | 2024-05-13 | 2024-05-13 | [91 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:EABC06AEF90A4570823C6BBBD3D47BAA
DDCL | CCP-W-B042-21-ME-B18-0006 | Valve List for Chemical Dosing System | D | D | 01 | _ |  | 2024-01-20 | 2024-02-20 | 2024-04-20 | 2024-05-20 | 2024-03-15 | 2024-05-10 |  |  | BOP Plant | Plant EPC)기계기술2팀 | Chemical Dosing Skid | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0144 | D | 01 | 2024-05-13 | 2024-05-13 | 2024-05-23 | CCP-PGU-TRM-EPC-0144 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0144 | D | 01 | 2024-05-13 | 2024-05-13 | 2024-05-23 | CCP-PGU-TRM-EPC-0144 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F3CDD7BA265E4070B030CC559E225FAF
DDCL | CCP-W-B042-21-ME-B06-0003 | P&ID for Chemical Dosing System | D | D | 01 | _ |  | 2024-01-20 | 2024-02-20 | 2024-04-20 | 2024-05-20 | 2024-03-15 | 2024-05-10 |  |  | BOP Plant | Plant EPC)기계기술2팀 | chemical dosing skid | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0144 | D | 01 | 2024-05-13 | 2024-05-13 | 2024-05-23 | CCP-PGU-TRM-EPC-0144 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0144 | D | 01 | 2024-05-13 | 2024-05-13 | 2024-05-23 | CCP-PGU-TRM-EPC-0144 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D49B716CF3EA49E99AF539F405F16256
DDCL | CCP-W-B042-21-ME-G07-0004 | Calculation Sheet for Chemical Dosing System | D | D | 01 | _ |  | 2024-01-20 | 2024-02-20 | 2024-04-20 | 2024-05-20 | 2024-03-15 | 2024-05-10 |  |  | BOP Plant | Plant EPC)기계기술2팀 | chemical dosing skid | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0144 | D | 01 | 2024-05-13 | 2024-05-13 | [5 empty] | CCP-EPC-TRM-PGU-0144 | D | 01 | 2024-05-13 | 2024-05-13 | [91 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A6D252B4A3594FCB863CB2D7E6CCEBE0
DDCL | CCP-W-B042-21-ME-B01-0002 | General Arrangement Drawing for Chemical Dosing System | D | D | 01 | _ |  | 2024-01-20 | 2024-02-20 | 2024-04-20 | 2024-05-20 | 2024-03-15 | 2024-05-10 |  |  | BOP Plant | Plant EPC)기계기술2팀 | chemical dosing skid | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0144 | D | 01 | 2024-05-13 | 2024-05-13 | 2024-05-23 | CCP-PGU-TRM-EPC-0144 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0144 | D | 01 | 2024-05-13 | 2024-05-13 | 2024-05-23 | CCP-PGU-TRM-EPC-0144 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E48ADAD6913144B7A0FA22A5588A6547
DDCL | CCP-W-B042-21-ME-A07-0001 | System Description for Chemical Dosing System | D | D | 01 | _ |  | 2024-01-20 | 2024-02-20 | 2024-04-20 | 2024-05-20 | 2024-03-15 | 2024-05-10 |  |  | BOP Plant | Plant EPC)기계기술2팀 | chemical dosing skid | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0144 | D | 01 | 2024-05-13 | 2024-05-13 | 2024-05-23 | CCP-PGU-TRM-EPC-0144 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0144 | D | 01 | 2024-05-13 | 2024-05-13 | 2024-05-23 | CCP-PGU-TRM-EPC-0144 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:46C505D86B1C4995A1EDD773AD03F9D0
DDCL | CCP-W-B053-23-ME-0001 | Equipment Arrangement Drawing for Workshop Equipment | D | D | 01 | _ |  | 2024-03-26 | 2024-04-26 | 2024-08-31 | 2024-09-30 | 2024-03-05 | 2024-07-25 |  |  | BOP Plant | Plant EPC)기계기술2팀 | Workshop Equipment | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0310 | D | 01 | 2024-07-25 | 2024-07-26 | 2024-08-05 | CCP-PGU-TRM-EPC-0310 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0310 | D | 01 | 2024-07-25 | 2024-07-26 | 2024-08-05 | CCP-PGU-TRM-EPC-0310 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:463B4EF2E2354121B6986BD7DD672B75
DDCL | CCP-W-B053-23-EL-0006 | Power Line Arrangement Drawing for Workshop Equipment | D | D | 01 | _ |  | 2024-05-31 | 2024-06-30 | 2024-08-31 | 2024-09-30 | 2024-03-05 | 2024-07-25 |  |  | BOP Plant | Plant EPC)기계기술2팀 | Workshop Equipment | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0310 | D | 01 | 2024-07-25 | 2024-07-26 | 2024-08-05 | CCP-PGU-TRM-EPC-0310 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0310 | D | 01 | 2024-07-25 | 2024-07-26 | 2024-08-05 | CCP-PGU-TRM-EPC-0310 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:41F85A526D98476399AB379EAD5F3A90
DDCL | CCP-W-B053-23-CV-0005 | Foundation and Loading Data for Workshop Equipment | D | D | 01 | _ |  | 2024-03-26 | 2024-04-26 | 2024-08-31 | 2024-09-30 | 2024-03-05 | 2024-07-25 |  |  | BOP Plant | Plant EPC)기계기술2팀 | Workshop Equipment | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0310 | D | 01 | 2024-07-25 | 2024-07-26 | 2024-08-05 | CCP-PGU-TRM-EPC-0310 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0310 | D | 01 | 2024-07-25 | 2024-07-26 | 2024-08-05 | CCP-PGU-TRM-EPC-0310 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:226C767931354E5A8E8B26A597924B44
DDCL | CCP-W-B053-23-ME-0003 | Equipment List & Specification for Workshop Equipment | D | D | 01 | _ |  | 2024-05-31 | 2024-06-30 | 2024-08-31 | 2024-09-30 | 2024-03-05 | 2024-07-25 |  |  | BOP Plant | Plant EPC)기계기술2팀 | Workshop Equipment | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0310 | D | 01 | 2024-07-25 | 2024-07-26 | 2024-08-05 | CCP-PGU-TRM-EPC-0310 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0310 | D | 01 | 2024-07-25 | 2024-07-26 | 2024-08-05 | CCP-PGU-TRM-EPC-0310 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8A377B6BFC0B472FBA279208CED8D7D5
DDCL | CCP-W-B041-20-ME-B01-0002 | General Arrangement Drawing for Steam and Water Analysis System | D | D | 01 | _ |  | 2024-01-20 | 2024-02-20 | 2024-04-20 | 2024-05-20 | 2024-03-18 | 2024-06-17 |  |  | BOP Plant | Plant EPC)기계기술2팀 | Steam and Water Analysis Container | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0197 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0197 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0197 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0197 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:BA877ED90FDE4DAEB6A5F4FF6466F267
DDCL | CCP-W-B041-20-ME-B06-0003 | P&ID for Steam and Water Analysis System | D | D | 01 | _ |  | 2024-01-20 | 2024-02-20 | 2024-04-20 | 2024-05-20 | 2024-03-18 | 2024-06-17 |  |  | BOP Plant | Plant EPC)기계기술2팀 | Steam and Water Analysis Container | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0197 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0197 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0197 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0197 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:644C5DBA7D18495C8C6744E8D9B359E0
DDCL | CCP-W-B041-20-ME-B06-0021 | P&ID for Glycol Analyzer Cabinet | D | C | 01 | _ |  | 2025-01-17 | 2025-01-31 | 2025-04-23 | 2025-04-30 | 2025-01-13 |  | 2025-04-08 | 2025-04-08 | BOP Plant | Plant EPC)기계기술2팀 | Steam and Water Analysis Container | Mechanical | 김준영 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D41209C5A65247E98C0413AD25C8C5DB
DDCL | CCP-W-B041-20-ME-B18-0005 | Valve List for Steam and Water Analysis System | D | D | 01 | _ |  | 2024-01-20 | 2024-02-20 | 2024-04-20 | 2024-05-20 | 2024-03-18 | 2024-06-17 |  |  | BOP Plant | Plant EPC)기계기술2팀 | Steam and Water Analysis Container | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0197 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0197 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0197 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0197 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:395EDA292B914448A09710D4675A06ED
DDCL | CCP-W-B041-20-ME-A07-0001 | System Description for Steam and Water Analysis System | D | D | 01 | _ |  | 2024-01-20 | 2024-02-20 | 2024-04-20 | 2024-05-20 | 2024-03-18 | 2024-06-17 |  |  | BOP Plant | Plant EPC)기계기술2팀 | Steam and Water Analysis Container | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0197 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0197 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0197 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0197 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FBF8D02DFEC64FB3869835EF5430945F
DDCL | CCP-W-B041-20-ME-B01-0022 | Outline drawing for Glycol Analyzer Cabinet | D | C | 01 | _ |  | 2025-01-17 | 2025-01-31 | 2025-04-23 | 2025-04-30 | 2025-01-13 |  | 2025-04-08 | 2025-04-08 | BOP Plant | Plant EPC)기계기술2팀 | Steam and Water Analysis Container | Mechanical | 김준영 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8AFBABA3135346698F975D937ADA8CBE
DDCL | CCP-W-B041-20-IA-E09-0007 | Control Loop & Logic Diagram for Steam and Water Analysis System | D | D | 01 | _ |  | 2024-01-20 | 2024-02-20 | 2024-04-20 | 2024-05-20 | 2024-03-18 | 2024-06-17 |  |  | BOP Plant | Plant EPC)기계기술2팀 | Steam and Water Analysis Container | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0197 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0197 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0197 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0197 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:AB3984A0E780406698CAEC1E41DA3E90
DDCL | CCP-W-B041-20-ME-B18-0006 | Instrument List for Steam and Water Analysis System | D | D | 01 | _ |  | 2024-01-20 | 2024-02-20 | 2024-04-20 | 2024-05-20 | 2024-03-18 | 2024-06-17 |  |  | BOP Plant | Plant EPC)기계기술2팀 | Steam and Water Analysis Container | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0197 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0197 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0197 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0197 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B72813DC17C14F6F8237AB8DA9344FBC
DDCL | CCP-W-B041-20-EL-E03-0008 | Schematic & Wiring Diagram for Steam and Water Analysis System | D | D | 01 | _ |  | 2024-01-20 | 2024-02-20 | 2024-04-20 | 2024-05-20 | 2024-03-18 | 2024-06-17 |  |  | BOP Plant | Plant EPC)기계기술2팀 | Steam and Water Analysis Container | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0197 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0197 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0197 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0197 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:DD461970EFDF498A8CC1230C8370CE91
DDCL | CCP-W-B041-20-EL-E03-0024 | Schematic & Wiring Diagram for Glycol Analyzer | D | C | 01 | _ |  | 2025-01-17 | 2025-01-31 | 2025-04-23 | 2025-04-30 | 2025-01-13 |  | 2025-04-08 | 2025-04-08 | BOP Plant | Plant EPC)기계기술2팀 | Steam and Water Analysis Container | Mechanical | 김준영 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C45E28F505E34B89ACD7B40F0E283F27
DDCL | CCP-W-B041-20-ME-B16-0004 | Technical Data Sheet for Steam and Water Analysis System | D | D | 01 | _ |  | 2024-01-20 | 2024-02-20 | 2024-04-20 | 2024-05-20 | 2024-03-18 | 2024-06-17 |  |  | BOP Plant | Plant EPC)기계기술2팀 | Steam and Water Analysis Container | Mechanical | 김준영 | [10 empty] | CCP-EPC-TRM-PGU-0197 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0197 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0197 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0197 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:9520F9A4E14B455689EAF7FF704EC4A8
DDCL | CCP-W-B041-20-ME-B16-0023 | Technical Data Sheet for Glycol Analyzer Cabinet | D | C | 01 | _ |  | 2025-01-17 | 2025-01-31 | 2025-04-23 | 2025-04-30 | 2025-01-13 |  | 2025-04-08 | 2025-04-08 | BOP Plant | Plant EPC)기계기술2팀 | Steam and Water Analysis Container | Mechanical | 김준영 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:DB8E298035304F1F87D32B791DA92BC8
DDCL | CCP-W-B000-EM-SPC-0001 | Description for Identification System | D | C | 01 | B |  | 2024-07-01 | 2024-07-20 | 2024-08-09 | 2024-08-30 | 2024-07-01 | 2024-07-01 | 2024-08-21 |  | BOP Plant | Plant EPC)Plant EPC EM1팀 | General Technical Document | Common | 최진 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1742EE4F228E43CEA586E38CB793EB61
DDCL | CCP-W-B114-PI-121-0001-003 | PIPING ARRANGEMENT DRAWING FOR HRSG #1 AREA PLAN | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8BA4B7C5D0A649538DC278EED2156B8F
DDCL | CCP-W-B000-PI-121-0017-001 | PIPING ARRANGEMENT DRAWING FOR CCW H/W&PUMP AREA(UNIT 2) | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:502BCBD1A2C646A5BDADE13DF4125D43
DDCL | CCP-W-B115-PI-121-0001-001 | PIPING ARRANGEMENT DRAWING FOR HRSG #2 AREA PLAN | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:9FA5822E4F44410A839B1AEE4DD6EE00
DDCL | CCP-W-B115-PI-121-0001-002 | PIPING ARRANGEMENT DRAWING FOR HRSG #2 AREA PLAN | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C32029C07E0C460793EC70CE0724EB99
DDCL | CCP-W-B115-PI-121-0001-003 | PIPING ARRANGEMENT DRAWING FOR HRSG #2 AREA PLAN | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1BBC495407204A10896A43BF3AB44B24
DDCL | CCP-W-B214-PI-121-0001-001 | PIPING ARRANGEMENT DRAWING FOR HRSG #3 AREA PLAN | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3212E7F72C444FF39E51873850D62405
DDCL | CCP-W-B214-PI-121-0001-002 | PIPING ARRANGEMENT DRAWING FOR HRSG #3 AREA PLAN | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D690CFEDEE074297B3B0A20EA1B1AC0E
DDCL | CCP-W-B214-PI-121-0001-003 | PIPING ARRANGEMENT DRAWING FOR HRSG #3 AREA PLAN | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C773F9ABDF7345F88AAE395A383386A5
DDCL | CCP-W-B215-PI-121-0001-001 | PIPING ARRANGEMENT DRAWING FOR HRSG #4 AREA PLAN | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:EA024F23BC2346F589B70DFEE2E92BBE
DDCL | CCP-W-B215-PI-121-0001-002 | PIPING ARRANGEMENT DRAWING FOR HRSG #4 AREA PLAN | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:622401C4F35F458AAEF619A1106C9367
DDCL | CCP-W-B215-PI-121-0001-003 | PIPING ARRANGEMENT DRAWING FOR HRSG #4 AREA PLAN | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1D233DB93EDC43938B98168E91162EFA
DDCL | CCP-W-B025-PI-121-0001-001 | PIPING ARRANGEMENT DRAWING FOR HRSG PIPERACK AREA(UNIT 1) | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:AFB6BB5E21FE461AB0E33BE38D5A2587
DDCL | CCP-W-B025-PI-121-0002-001 | PIPING ARRANGEMENT DRAWING FOR ST PIPE RACK AREA | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:130210AE2CCD4DD0BD94F99BB9EA997C
DDCL | CCP-W-B025-PI-121-0003-001 | PIPING ARRANGEMENT DRAWING FOR HRSG PIPERACK AREA(UNIT 2) | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A5D66F9F781E497B8A6776ECA316B48E
DDCL | CCP-W-B000-PI-121-0018-001 | PIPING ARRANGEMENT DRAWING FOR OIL STORAGE DIKE AREA | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:71BF3D108FF741B5B3C0E728079AE25A
DDCL | CCP-W-B000-PI-121-0019-001 | PIPING ARRANGEMENT DRAWING FOR AIS & PIPERACK AREA | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:40702DB3500A4817B4FCE7F22361870C
DDCL | CCP-W-B113-PI-121-0001-001 | PIPING ARRANGEMENT DRAWING FOR STEAM TURBINE #1 AREA PLAN | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:188CC69159EA4F9AA9548C67BEEF3BFC
DDCL | CCP-W-B113-PI-121-0001-002 | PIPING ARRANGEMENT DRAWING FOR STEAM TURBINE #1 AREA PLAN | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8E172A869A3946B388FA5F14FA7E66A7
DDCL | CCP-W-B113-PI-121-0002-001 | PIPING ARRANGEMENT DRAWING FOR STEAM TURBINE #1 AREA PLAN | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:278C689F1B07452C9AE10A0830D97DB2
DDCL | CCP-W-B113-PI-121-0002-002 | PIPING ARRANGEMENT DRAWING FOR STEAM TURBINE #1 AREA PLAN | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E5B27F8AF8F34F83B2FEC1E5D2E55CD8
DDCL | CCP-W-B213-PI-121-0001-001 | PIPING ARRANGEMENT DRAWING FOR STEAM TURBINE #2 AREA PLAN | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:76BF200C5B5D4AA1A5FA049D25479CED
DDCL | CCP-W-B213-PI-121-0001-002 | PIPING ARRANGEMENT DRAWING FOR STEAM TURBINE #2 AREA PLAN | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D9F024F5FD56488CB107C1351754144C
DDCL | CCP-W-B213-PI-121-0002-001 | PIPING ARRANGEMENT DRAWING FOR STEAM TURBINE #2 AREA PLAN | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5D1294DD850245DEB28166285ADBC9EB
DDCL | CCP-W-B213-PI-121-0002-002 | PIPING ARRANGEMENT DRAWING FOR STEAM TURBINE #2 AREA PLAN | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4AA5E87BB89C4F3FABB66E159F21BD2B
DDCL | CCP-W-B114-PI-121-0001-001 | PIPING ARRANGEMENT DRAWING FOR HRSG #1 AREA PLAN | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:722C32D06281408FA69EC8BF7791A265
DDCL | CCP-W-B114-PI-121-0001-002 | PIPING ARRANGEMENT DRAWING FOR HRSG #1 AREA PLAN | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0111 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-04-24 | CCP-PGU-TRM-EPC-0111 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:616DDFEAB34F4EC99CBBE74DB31FCF77
DDCL | CCP-W-B000-PI-121-0009-001 | PIPING ARRANGEMENT DRAWING FOR POTABLE WATER TANK AREA | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:BF62229B4B46449D891546E2978FEBED
DDCL | CCP-W-B000-PI-121-0010-001 | PIPING ARRANGEMENT DRAWING FOR RAW WATER TANK AREA | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6FD429BABEA64CD18792A6F63B038D02
DDCL | CCP-W-B000-PI-121-0011-001 | PIPING ARRANGEMENT DRAWING FOR ACC AREA -1 | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2D49017AA65A4ABB950A46E671CEBE30
DDCL | CCP-W-B000-PI-121-0012-001 | PIPING ARRANGEMENT DRAWING FOR ACC AREA -2 | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F774613E76B64904AE0A38C33936E62D
DDCL | CCP-W-B000-PI-121-0013-001 | PIPING ARRANGEMENT DRAWING FOR DIESEL OIL PUMP & UNLOADING AREA -1 | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5F40509E99C64558AFF4B708A4EEFB0B
DDCL | CCP-W-B000-PI-121-0013-002 | PIPING ARRANGEMENT DRAWING FOR DIESEL OIL PUMP & UNLOADING AREA -2 | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:BAB61576D8DE46ACA12CCAC8193EB6F0
DDCL | CCP-W-B000-PI-121-0013-003 | PIPING ARRANGEMENT DRAWING FOR DIESEL OIL PUMP & UNLOADING AREA -3 | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C40AA0D398DB47C59017141A9FCBB6FB
DDCL | CCP-W-B000-PI-121-0014-001 | PIPING ARRANGEMENT DRAWING FOR N2 GENERATION AREA | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1E558A45357A4203BBF70BD81F78BF3E
DDCL | CCP-W-B000-PI-121-0015-001 | PIPING ARRANGEMENT DRAWING FOR DIESEL OIL TANK AREA -1 | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5FE5B5AC0DC84ED4AA6988A61D77276E
DDCL | CCP-W-B000-PI-121-0015-002 | PIPING ARRANGEMENT DRAWING FOR DIESEL OIL TANK AREA -2 | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A9A6A4C7B5C449A89163DCDE677AA4DE
DDCL | CCP-W-B000-PI-121-0015-003 | PIPING ARRANGEMENT DRAWING FOR DIESEL OIL TANK AREA -3 | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FBB1101464FF49119C4BF60DE6F4D37C
DDCL | CCP-W-B000-PI-121-0016-001 | PIPING ARRANGEMENT DRAWING FOR LOCAL ELECTRIC ROOM BLOCK #2 | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3BC594E3821B42DB8931E059EE0C5597
DDCL | CCP-W-B000-PI-120-0001-001 | PIPING ARRANGEMENT DRAWING - KEY PLAN | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F20D1FE23CA94162B1E284E64BC4D765
DDCL | CCP-W-B000-PI-121-0001-001 | PIPING ARRANGEMENT DRAWING FOR BLACK START DIESEL GENERATOR AREA | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-14 | 2024-03-14 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0104 | D | 01 | 2024-03-14 | 2024-03-14 | 2024-04-02 | CCP-PGU-TRM-EPC-0104 | D | 01 | Rejected | CCP-EPC-TRM-PGU-0104 | D | 01 | 2024-03-14 | 2024-03-14 | 2024-04-02 | CCP-PGU-TRM-EPC-0104 | Rejected | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4EF79F658F874DDBB0FBB3479FA32A96
DDCL | CCP-W-B000-PI-121-0002-001 | PIPING ARRANGEMENT DRAWING FOR WORKSHOP & WAREHOUSE AREA | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:27CC64EFD61B4AC1914B5044CFC5C208
DDCL | CCP-W-B000-PI-121-0003-001 | PIPING ARRANGEMENT DRAWING FOR AUX.BOILER AREA | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B4C00C98C0D0420787FFCE5D212152C6
DDCL | CCP-W-B000-PI-121-0004-001 | PIPING ARRANGEMENT DRAWING FOR CONTROL BLDG.AREA(UNIT 1) | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:AE2C69F92F21446B845CAAEA67BE2E5A
DDCL | CCP-W-B000-PI-121-0005-001 | PIPING ARRANGEMENT DRAWING FOR CCW H/E&PUMP AREA(UNIT 1) | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:9C57DDA6C47745BFBE9E2724D24AEF17
DDCL | CCP-W-B000-PI-121-0006-001 | PIPING ARRANGEMENT DRAWING FOR DEMI. WATER TANK AREA | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7A41F272AF734CDBAAD9EF0AC0F91464
DDCL | CCP-W-B000-PI-121-0007-001 | PIPING ARRANGEMENT DRAWING FOR SERVIEC WATER TANK AREA | D | D | 01 | _ |  | 2023-11-01 | 2024-01-26 | 2024-02-12 | 2024-04-26 | 2024-03-15 | 2024-03-15 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | Piping Arrangement | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0114 | D | 01 | 2024-03-15 | 2024-03-15 | 2024-03-25 | CCP-PGU-TRM-EPC-0114 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4DC5064F59FD4373B4161E3AADBCAA4B
DDCL | CCP-W-B000-PI-223-0002 | Stress Analysis Report for LP STEAM & BYPASS PIPING SYSTEM | D | C | 01 | _ |  | 2023-12-18 | 2024-02-16 | 2024-03-13 | 2024-05-26 | 2024-03-20 | 2024-10-08 | 2024-10-08 | 2024-10-10 | BOP Plant | Plant EPC)배치/배관기술2팀 | PIPING SA | Piping | 송준이 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:344FB01AE9054BC98FFCBF34F1369AF0
DDCL | CCP-W-B000-PI-223-0001 | Stress Analysis Report for HP STEAM & BYPASS PIPING SYSTEM | D | C | 01 | _ |  | 2023-12-18 | 2024-02-16 | 2024-03-13 | 2024-05-26 | 2024-03-20 | 2024-10-08 | 2024-10-08 | 2024-10-10 | BOP Plant | Plant EPC)배치/배관기술2팀 | PIPING SA | Piping | 송준이 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B8E95861CBA44760A37E5E78423FEBE3
DDCL | CCP-W-B000-PI-SPC-0001 | PIPING MATERIAL SPECIFICATION | D | D | 02 | _ |  | 2024-01-06 | 2024-02-20 | 2024-03-17 | 2024-05-30 | 2024-03-04 | 2024-05-30 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | PIPING | Piping | 윤승완 | [10 empty] | CCP-EPC-TRM-PGU-0329 | D | 02 | 2024-08-07 | 2024-08-14 | 2024-03-29 | CCP-PGU-TRM-EPC-0101 | D | 01 | Rejected | CCP-EPC-TRM-PGU-0101 | D | 01 | 2024-03-11 | 2024-03-11 | 2024-03-29 | CCP-PGU-TRM-EPC-0101 | Rejected | CCP-EPC-TRM-PGU-0329 | D | 02 | 2024-08-07 | 2024-08-14 | [83 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:267A8EABCA074CD39F7AC9D4D83DA55D
DDCL | CCP-W-B000-PI-SPC-0002 | PIPING INSULATION SPECIFICATION | D | D | 01 | _ |  | 2024-01-06 | 2024-02-20 | 2024-03-17 | 2024-05-30 | 2024-03-11 | 2024-03-11 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | PIPING | Piping | 윤승완 | [10 empty] | CCP-EPC-TRM-PGU-0103 | D | 01 | 2024-03-11 | 2024-03-11 | 2024-03-29 | CCP-PGU-TRM-EPC-0103 | D | 01 | Rejected | CCP-EPC-TRM-PGU-0103 | D | 01 | 2024-03-11 | 2024-03-11 | 2024-03-29 | CCP-PGU-TRM-EPC-0103 | Rejected | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4B5B2B6CD73945EAB0C93F7819437A2D
DDCL | CCP-W-B000-PI-223-0003 | Stress Analysis Report for FEEDWATER SYSTEM | D | C | 01 | _ |  | 2023-12-18 | 2024-02-16 | 2024-03-13 | 2024-05-26 | 2024-03-20 | 2024-10-08 | 2024-10-08 | 2024-10-10 | BOP Plant | Plant EPC)배치/배관기술2팀 | PIPING SA | Piping | 송준이 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F5B3D208209446FDA4E78E7530C3D2AA
DDCL | CCP-W-B000-PI-009-0001 | PIPING LINE LIST | D | D | 01 | _ |  | 2024-01-06 | 2024-02-20 | 2024-03-02 | 2024-05-30 | 2024-03-11 | 2024-03-11 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | PIPING | Piping | 오운석 | [10 empty] | CCP-EPC-TRM-PGU-0102 | D | 01 | 2024-03-11 | 2024-03-11 | 2024-04-01 | CCP-PGU-TRM-EPC-0102 | D | 01 | Rejected | CCP-EPC-TRM-PGU-0102 | D | 01 | 2024-03-11 | 2024-03-11 | 2024-04-01 | CCP-PGU-TRM-EPC-0102 | Rejected | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3F91D8110DC24247A176748142484E99
DDCL | CCP-W-B000-PI-SPC-0004 | PIPING SPECIALTY LIST | D | D | 01 | _ |  | 2023-11-17 | 2024-01-16 | 2024-07-08 | 2024-09-20 | 2024-05-24 | 2024-05-27 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | PIPING | Piping | 윤승완 | [10 empty] | CCP-EPC-TRM-PGU-0200 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0200 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0200 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0200 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4FA74B4FE4954917B29A762AAE094AE1
DDCL | CCP-W-B000-PI-SPC-0003 | MANUAL VALVE LIST | D | D | 01 | _ |  | 2023-11-17 | 2024-01-16 | 2024-07-08 | 2024-09-20 | 2024-06-03 | 2024-06-03 |  |  | BOP Plant | Plant EPC)배치/배관기술2팀 | PIPING | Piping | 윤승완 | [10 empty] | CCP-EPC-TRM-PGU-0201 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0201 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0201 | D | 01 | 2024-06-18 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0201 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:214D8BD4C39B4CB5AFDE077424BC2364
DDCL | CCP-PW-B040-PR-007-0001 | P&ID_Compressed Air System | D | C | 01 | B |  | 2023-08-01 | 2023-09-12 | 2024-05-01 | 2024-05-26 | 2024-01-30 | 2023-09-22 | 2024-01-30 | 2024-09-04 | BOP Plant | Plant EPC)기계기술1팀 | Compressed Air System | Process | 김광희 | [10 empty] | CCP-EPC-TRM-PGU-0166 | C | 01 | 2024-05-31 | 2024-06-04 | 2024-06-14 | CCP-PGU-TRM-EPC-0166 | C | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0023 | D | 01 | 2023-09-22 | 2023-09-22 | 2023-10-13 | CCP-PGU-TRM-EPC-0023 | Approved With Comment | CCP-EPC-TRM-PGU-0166 | C | 01 | 2024-05-31 | 2024-06-04 | 2024-06-14 | CCP-PGU-TRM-EPC-0166 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F6C9041BC34B44249B8654D9430B6A65
DDCL | CCP-PW-B040-PR-005-0001 | PROCESS FLOW DIAGRAM_Compressed Air System | D | D | 01 | _ |  | 2023-12-21 | 2024-02-01 | 2024-08-29 | 2024-09-23 | 2024-03-11 | 2024-05-31 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Compressed Air System | Process | 김광희 | [10 empty] | CCP-EPC-TRM-PGU-0162 | D | 01 | 2024-05-31 | 2024-06-03 | 2024-06-13 | CCP-PGU-TRM-EPC-0162 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0162 | D | 01 | 2024-05-31 | 2024-06-03 | 2024-06-13 | CCP-PGU-TRM-EPC-0162 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:755685511E7640C1B7D646B9B50C68AF
DDCL | CCP-PW-B128-PR-007-0001-001 | P&ID_Auxiliary Steam System | D | D | 01 | _ |  | 2023-08-01 | 2023-09-12 | 2024-02-11 | 2024-03-24 |  | 2023-09-12 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Auxiliary Steam Distribution System | Process | 안진엽 | [10 empty] | CCP-EPC-TRM-PGU-0010 | D | 01 | 2023-09-12 | 2023-09-12 | 2023-10-06 | CCP-PGU-TRM-EPC-0010 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0010 | D | 01 | 2023-09-12 | 2023-09-12 | 2023-10-06 | CCP-PGU-TRM-EPC-0010 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6B37C09D6A8D4BF3A13C939B1D7C1B4D
DDCL | CCP-PW-B128-PR-005-0001-001 | PFD_Auxiliary Steam System | D | D | 01 | _ |  | 2023-12-16 | 2024-01-27 | 2024-06-15 | 2024-07-27 | 2024-03-15 | 2024-06-17 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Auxiliary Steam Distribution System | Process | 안진엽 | [10 empty] | CCP-EPC-TRM-PGU-0195 | D | 01 | 2024-06-17 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0195 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0195 | D | 01 | 2024-06-17 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0195 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A97CDAE00ABA495B8228B91C8599298E
DDCL | CCP-PW-B129-PR-007-0001-001 | P&ID_Condensate System | D | D | 01 | _ |  | 2023-07-14 | 2023-09-12 | 2024-01-24 | 2024-03-24 |  | 2023-09-12 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Condensate System | Process | 김정민 | [10 empty] | CCP-EPC-TRM-PGU-0010 | D | 01 | 2023-09-12 | 2023-09-12 | 2023-10-06 | CCP-PGU-TRM-EPC-0010 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0010 | D | 01 | 2023-09-12 | 2023-09-12 | 2023-10-06 | CCP-PGU-TRM-EPC-0010 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D4D2EB1E4A2F4CA193E9D46CEEAD50D5
DDCL | CCP-PW-B129-PR-005-0001 | PFD_Condensate System | D | C | 01 | _ |  | 2023-11-28 | 2024-01-27 | 2024-05-28 | 2024-07-27 | 2024-08-21 | 2024-08-26 | 2024-08-26 | 2024-08-26 | BOP Plant | Plant EPC)프로세스기술1팀 | Condensate System | Process | 김정민 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8E36B5A290F54BCA8BE9E72C42A4DB07
DDCL | CCP-PW-B035-PR-007-0001-001 | P&ID_Demineralized Water System (1 of 3) | D | C | 01 | A |  | 2023-12-13 | 2024-01-24 | 2024-07-10 | 2024-08-21 | 2024-01-24 | 2024-09-10 | 2024-09-10 | 2025-01-20 | BOP Plant | Plant EPC)프로세스기술1팀 | Demineralized Water System | Process | 박성용 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D478176E74CC448FB23B83680F568099
DDCL | CCP-PW-B035-PR-007-0001-002 | P&ID_Demineralized Water System (2 of 3) | D | C | 01 | A |  | 2023-12-13 | 2024-01-24 | 2024-07-10 | 2024-08-21 | 2024-01-24 | 2024-09-10 | 2024-09-10 | 2025-01-20 | BOP Plant | Plant EPC)프로세스기술1팀 | Demineralized Water System | Process | 박성용 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8D761F7563C849CA858656D5E6318E5C
DDCL | CCP-PW-B035-PR-007-0001-003 | P&ID_Demineralized Water System (3 of 3) | D | C | 01 | A |  | 2023-12-13 | 2024-01-24 | 2024-07-10 | 2024-08-21 | 2024-01-24 | 2024-09-10 | 2024-09-10 | 2025-01-20 | BOP Plant | Plant EPC)프로세스기술1팀 | Demineralized Water System | Process | 박성용 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F4D4711B3E5347B7934CB18C25E20FF6
DDCL | CCP-PW-B035-PR-006-0001 | UFD_Demineralized Water Distribution System | D | C | 01 | _ |  | 2023-12-16 | 2024-01-27 | 2024-06-15 | 2024-07-27 | 2024-03-08 | 2024-09-10 | 2024-09-10 | 2024-09-11 | BOP Plant | Plant EPC)프로세스기술1팀 | Demineralized Water System | Process | 박성용 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:BEC8054CE26B4479858D3F9CE6D88729
DDCL | CCP-PW-B130-PR-007-0001-001 | P&ID_Feedwater System | D | D | 01 | _ |  | 2023-08-01 | 2023-09-12 | 2024-02-11 | 2024-03-24 |  | 2023-09-12 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Feedwater System | Process | 박성용 | [10 empty] | CCP-EPC-TRM-PGU-0010 | D | 01 | 2023-09-12 | 2023-09-12 | 2023-10-06 | CCP-PGU-TRM-EPC-0010 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0010 | D | 01 | 2023-09-12 | 2023-09-12 | 2023-10-06 | CCP-PGU-TRM-EPC-0010 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CFE86239924045F7A3C364BEC9E83EFB
DDCL | CCP-PW-B130-PR-005-0001 | PFD_ Feedwater System | D | C | 01 | _ |  | 2023-12-16 | 2024-01-27 | 2024-06-15 | 2024-07-27 | 2024-03-08 | 2024-08-21 | 2024-08-21 | 2024-08-21 | BOP Plant | Plant EPC)프로세스기술1팀 | Feedwater System | Process | 박성용 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:19EFEC4C58354D3397DB831E4950A2D1
DDCL | CCP-PW-B133-PR-007-0001-001 | P&ID_Atmospheric Flash Tank System | D | D | 01 | _ |  | 2023-08-01 | 2023-09-12 | 2024-02-11 | 2024-03-24 |  | 2023-09-12 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Atmospheric Flash Tank System | Process | 안진엽 | [10 empty] | CCP-EPC-TRM-PGU-0010 | D | 01 | 2023-09-12 | 2023-09-12 | 2023-10-06 | CCP-PGU-TRM-EPC-0010 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0010 | D | 01 | 2023-09-12 | 2023-09-12 | 2023-10-06 | CCP-PGU-TRM-EPC-0010 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FF214C359AD64D9890D4B681F30A7A45
DDCL | CCP-PW-B051-PR-007-0001-001 | P&ID_Nitrogen Gas Distribution System | D | D | 01 | _ |  | 2023-08-01 | 2023-09-12 | 2024-02-11 | 2024-03-24 |  | 2023-09-12 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Nitrogen Gas Distribution System | Process | 박재현 | [10 empty] | CCP-EPC-TRM-PGU-0010 | D | 01 | 2023-09-12 | 2023-09-12 | 2023-10-06 | CCP-PGU-TRM-EPC-0010 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0010 | D | 01 | 2023-09-12 | 2023-09-12 | 2023-10-06 | CCP-PGU-TRM-EPC-0010 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:17B2BC56095742749858D491B059B3A7
DDCL | CCP-PW-B051-PR-006-0001-001 | UFD_Nitrogen Gas Distribution System | D | D | 01 | _ |  | 2023-12-16 | 2024-01-27 | 2024-06-15 | 2024-07-27 | 2024-03-15 | 2024-06-17 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Nitrogen Gas Distribution System | Process | 박재현 | [10 empty] | CCP-EPC-TRM-PGU-0195 | D | 01 | 2024-06-17 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0195 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0195 | D | 01 | 2024-06-17 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0195 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F74F7902CF2C474E94509499DEF31DDF
DDCL | CCP-PW-B130-PR-007-0002-001 | P&ID_Fuel Gas Performance Heater System | D | D | 01 | _ |  | 2023-08-01 | 2023-09-12 | 2024-02-11 | 2024-03-24 |  | 2023-09-12 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Fuel Gas Performance Heater System | Process | 박성용 | [10 empty] | CCP-EPC-TRM-PGU-0010 | D | 01 | 2023-09-12 | 2023-09-12 | 2023-10-06 | CCP-PGU-TRM-EPC-0010 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0010 | D | 01 | 2023-09-12 | 2023-09-12 | 2023-10-06 | CCP-PGU-TRM-EPC-0010 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6AEF1E4931EE489090984887FD7F9902
DDCL | CCP-PW-B044-PR-007-0001 | P&ID_Fuel gas supply system | D | D | 01 | _ |  | 2023-08-01 | 2023-09-12 | 2024-05-01 | 2024-05-26 |  | 2023-09-22 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel gas supply system | Process | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0023 | D | 01 | 2023-09-22 | 2023-09-22 | 2023-10-13 | CCP-PGU-TRM-EPC-0023 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0023 | D | 01 | 2023-09-22 | 2023-09-22 | 2023-10-13 | CCP-PGU-TRM-EPC-0023 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:81AE48A799364A09A4BCB0D050849234
DDCL | CCP-PW-B046-PR-007-0001 | P&I DIagram_Fuel Oil System | D | C | 01 | B |  | 2023-06-30 | 2023-07-30 | 2024-04-26 | 2024-05-26 | 2024-02-01 | 2023-09-22 | 2024-02-01 | 2025-07-04 | BOP Plant | Plant EPC)기계기술1팀 | Fuel Oil System | Process | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0169 | C | 01 | 2024-06-04 | 2024-06-04 | 2024-06-14 | CCP-PGU-TRM-EPC-0169 | C | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0023 | D | 01 | 2023-09-22 | 2023-09-22 | 2023-10-02 | CCP-PGU-TRM-EPC-0023 | Deemed Approved | CCP-EPC-TRM-PGU-0169 | C | 01 | 2024-06-04 | 2024-06-04 | 2024-06-14 | CCP-PGU-TRM-EPC-0169 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:140AEAC4D30B4567A5AB0729C2C09F9F
DDCL | CCP-PW-B052-PR-007-0001 | P&I DIagram_Oil facility system | D | C | 01 | C |  | 2023-08-01 | 2023-09-12 | 2024-05-01 | 2024-05-26 | 2024-01-30 | 2023-09-22 | 2024-01-30 | 2025-07-03 | BOP Plant | Plant EPC)기계기술1팀 | Oil facility system | Process | 김광희 | [10 empty] | CCP-EPC-TRM-PGU-0166 | C | 01 | 2024-05-31 | 2024-06-04 | 2024-06-14 | CCP-PGU-TRM-EPC-0166 | C | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0023 | D | 01 | 2023-09-22 | 2023-09-22 | 2023-10-13 | CCP-PGU-TRM-EPC-0023 | Approved With Comment | CCP-EPC-TRM-PGU-0166 | C | 01 | 2024-05-31 | 2024-06-04 | 2024-06-14 | CCP-PGU-TRM-EPC-0166 | Deemed Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:25F2A14D758D4462A1FA4901A2FC6046
DDCL | CCP-PW-B044-PR-005-0001 | UTILITY FLOW DIAGRAM_Fuel gas supply system | R | C | 01 | _ |  | 2023-12-21 | 2024-02-01 | 2024-08-29 | 2024-09-23 | 2024-06-05 | 2023-09-22 | 2024-07-17 | 2024-10-11 | BOP Plant | Plant EPC)기계기술1팀 | Fuel gas supply system | Process | 박동준 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:50E9B5774D964130A5851DB7473EC6D5
DDCL | CCP-PW-B046-PR-005-0001 | UFD_Fuel Oil System | D | D | 01 | _ |  | 2024-01-03 | 2024-02-02 | 2024-10-08 | 2024-11-07 | 2024-02-01 | 2024-06-03 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Oil System | Process | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0168 | D | 01 | 2024-06-03 | 2024-06-04 | 2024-06-14 | CCP-PGU-TRM-EPC-0168 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0168 | D | 01 | 2024-06-03 | 2024-06-04 | 2024-06-14 | CCP-PGU-TRM-EPC-0168 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CB41696C62DB43D0BD17405E1586C721
DDCL | CCP-PW-B132-PR-007-0001-002 | P&ID_Closed Cooling Water System (2 of 3) | D | D | 01 | _ |  | 2023-07-14 | 2023-09-12 | 2024-01-24 | 2024-03-24 |  | 2023-09-12 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Closed Cooling Water System | Process | 박재현 | [10 empty] | CCP-EPC-TRM-PGU-0010 | D | 01 | 2023-09-12 | 2023-09-12 | 2023-10-06 | CCP-PGU-TRM-EPC-0010 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0010 | D | 01 | 2023-09-12 | 2023-09-12 | 2023-10-06 | CCP-PGU-TRM-EPC-0010 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E1F26BD8A0BB4AA58518A245EC1403A6
DDCL | CCP-PW-B132-PR-007-0001-003 | P&ID_Closed Cooling Water System (3 of 3) | D | D | 01 | _ |  | 2023-07-14 | 2023-09-12 | 2024-01-24 | 2024-03-24 |  | 2023-09-12 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Closed Cooling Water System | Process | 박재현 | [10 empty] | CCP-EPC-TRM-PGU-0010 | D | 01 | 2023-09-12 | 2023-09-12 | 2023-10-06 | CCP-PGU-TRM-EPC-0010 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0010 | D | 01 | 2023-09-12 | 2023-09-12 | 2023-10-06 | CCP-PGU-TRM-EPC-0010 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3C83D6F67A754881869A4F21D2BE37D5
DDCL | CCP-PW-B132-PR-007-0001-001 | P&ID_Closed Cooling Water System (1 of 3) | D | D | 01 | _ |  | 2023-07-14 | 2023-09-12 | 2024-01-24 | 2024-03-24 |  | 2023-09-12 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Closed Cooling Water System | Process | 박재현 | [10 empty] | CCP-EPC-TRM-PGU-0010 | D | 01 | 2023-09-12 | 2023-09-12 | 2023-10-06 | CCP-PGU-TRM-EPC-0010 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0010 | D | 01 | 2023-09-12 | 2023-09-12 | 2023-10-06 | CCP-PGU-TRM-EPC-0010 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:DEB3890D90664AD4B4BFA198583BB21D
DDCL | CCP-PW-B132-PR-006-0001 | UFD_Closed Cooling Water System | D | C | 01 | A |  | 2023-11-28 | 2024-01-27 | 2024-05-28 | 2024-07-27 | 2024-03-07 | 2024-08-26 | 2024-08-26 | 2025-03-05 | BOP Plant | Plant EPC)프로세스기술1팀 | Closed Cooling Water System | Process | 박재현 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:AEAFF80E979F4BE9947F2B42871DF876
DDCL | CCP-PW-B126-PR-007-0001-001 | P&ID_HP & LP Steam System (1 of 2) | D | D | 01 | _ |  | 2023-08-01 | 2023-09-12 | 2024-02-11 | 2024-03-24 |  | 2023-09-12 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | HP & LP Steam System | Process | 안진엽 | [10 empty] | CCP-EPC-TRM-PGU-0010 | D | 01 | 2023-09-12 | 2023-09-12 | 2023-10-06 | CCP-PGU-TRM-EPC-0010 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0010 | D | 01 | 2023-09-12 | 2023-09-12 | 2023-10-06 | CCP-PGU-TRM-EPC-0010 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:468B5F4FC22A477395FDF2B57BCD9035
DDCL | CCP-PW-B127-PR-007-0001-002 | P&ID_HP & LP Steam System (2 of 2) | D | D | 01 | _ |  | 2023-08-01 | 2023-09-12 | 2024-02-11 | 2024-03-24 |  | 2023-09-12 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | HP & LP Steam System | Process | 안진엽 | [10 empty] | CCP-EPC-TRM-PGU-0010 | D | 01 | 2023-09-12 | 2023-09-12 | 2023-10-06 | CCP-PGU-TRM-EPC-0010 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0010 | D | 01 | 2023-09-12 | 2023-09-12 | 2023-10-06 | CCP-PGU-TRM-EPC-0010 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:AC9E81D6267047D99606758EF011D950
DDCL | CCP-PW-B126-PR-005-0001-001 | PFD_HP & LP Steam System (1 of 2) | D | D | 01 | _ |  | 2023-12-16 | 2024-01-27 | 2024-06-15 | 2024-07-27 | 2024-03-15 | 2024-06-17 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | HP & LP Steam System | Process | 안진엽 | [10 empty] | CCP-EPC-TRM-PGU-0195 | D | 01 | 2024-06-17 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0195 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0195 | D | 01 | 2024-06-17 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0195 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:AF147C3B732A45AFB4B1144F2ECF6E05
DDCL | CCP-PW-B127-PR-005-0001-002 | PFD_HP & LP Steam System (2 of 2) | D | D | 01 | _ |  | 2023-12-16 | 2024-01-27 | 2024-06-15 | 2024-07-27 | 2024-03-15 | 2024-06-17 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | HP & LP Steam System | Process | 안진엽 | [10 empty] | CCP-EPC-TRM-PGU-0195 | D | 01 | 2024-06-17 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0195 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0195 | D | 01 | 2024-06-17 | 2024-06-19 | 2024-06-29 | CCP-PGU-TRM-EPC-0195 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1A06C34A6BD4413CA61FABAF36101CF7
DDCL | CCP-PW-B039-PR-007-0001 | P&I Diagram_Waste Water Transfer System(Chemical Waste Water_Main BLDG) | R | C | 01 | _ |  | 2024-02-15 | 2024-03-16 | 2024-05-15 | 2024-06-14 | 2024-03-13 | 2023-06-23 | 2024-11-08 | 2024-11-08 | BOP Plant | Plant EPC)기계기술1팀 | Waste Water Transfer System | Process | 박대영 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:08A94702448E4597A8D9F6B2936F3DD8
DDCL | CCP-PW-B036-PR-007-0001 | P&I DIagram_Service Water System | D | D | 01 | _ |  | 2023-08-01 | 2023-09-12 | 2024-05-01 | 2024-05-26 |  | 2023-09-27 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Service Water System | Process | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0032 | D | 01 | 2023-09-27 | 2023-09-27 | 2023-10-13 | CCP-PGU-TRM-EPC-0032 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0032 | D | 01 | 2023-09-27 | 2023-09-27 | 2023-10-13 | CCP-PGU-TRM-EPC-0032 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:089C9A5436714308885F26920CE44AA5
DDCL | CCP-PW-B134-PR-007-0001-001 | P&ID_Hot Water Distribution System (1 of 3) | D | D | 01 | _ |  | 2023-07-14 | 2023-09-12 | 2024-01-24 | 2024-03-24 |  | 2023-09-12 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Hot Water Distribution System | Process | 김정민 | [10 empty] | CCP-EPC-TRM-PGU-0010 | D | 01 | 2023-09-12 | 2023-09-12 | 2023-10-06 | CCP-PGU-TRM-EPC-0010 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0010 | D | 01 | 2023-09-12 | 2023-09-12 | 2023-10-06 | CCP-PGU-TRM-EPC-0010 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:702C18DC7B074513844857C2A90723F8
DDCL | CCP-PW-B134-PR-007-0001-002 | P&ID_Hot Water Distribution System (2 of 3) | D | D | 01 | _ |  | 2023-07-14 | 2023-09-12 | 2024-01-24 | 2024-03-24 |  | 2023-09-12 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Hot Water Distribution System | Process | 김정민 | [10 empty] | CCP-EPC-TRM-PGU-0010 | D | 01 | 2023-09-12 | 2023-09-12 | 2023-10-06 | CCP-PGU-TRM-EPC-0010 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0010 | D | 01 | 2023-09-12 | 2023-09-12 | 2023-10-06 | CCP-PGU-TRM-EPC-0010 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:6809D49530444570AF4B58D861555766
DDCL | CCP-PW-B134-PR-007-0001-003 | P&ID_Hot Water Distribution System (3 of 3) | D | D | 01 | _ |  | 2023-07-14 | 2023-09-12 | 2024-01-24 | 2024-03-24 |  | 2023-09-12 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Hot Water Distribution System | Process | 김정민 | [10 empty] | CCP-EPC-TRM-PGU-0010 | D | 01 | 2023-09-12 | 2023-09-12 | 2023-10-06 | CCP-PGU-TRM-EPC-0010 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0010 | D | 01 | 2023-09-12 | 2023-09-12 | 2023-10-06 | CCP-PGU-TRM-EPC-0010 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:43D43BA87F034137B8A6E8D05410C7D9
DDCL | CCP-PW-B038-PR-007-0001 | P&I DIagram_Raw Water System | D | D | 01 | _ |  | 2023-08-01 | 2023-09-12 | 2024-05-01 | 2024-05-26 |  | 2023-09-27 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Raw Water System | Process | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0032 | D | 01 | 2023-09-27 | 2023-09-27 | 2023-10-13 | CCP-PGU-TRM-EPC-0032 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0032 | D | 01 | 2023-09-27 | 2023-09-27 | 2023-10-13 | CCP-PGU-TRM-EPC-0032 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8CFEE928394B493C8EAE67A207861F37
DDCL | CCP-PW-B037-PR-007-0001 | P&I DIagram_Potable Water System | D | D | 01 | _ |  | 2023-08-01 | 2023-09-12 | 2024-05-01 | 2024-05-26 |  | 2023-09-27 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Potable Water System | Process | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0032 | D | 01 | 2023-09-27 | 2023-09-27 | 2023-10-13 | CCP-PGU-TRM-EPC-0032 | D | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0032 | D | 01 | 2023-09-27 | 2023-09-27 | 2023-10-13 | CCP-PGU-TRM-EPC-0032 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3D242F708C874AF7B8CD016348AE9A48
DDCL | CCP-PW-B037-PR-005-0001 | Utility Flow_Diagram_Potable Water System | D | C | 01 | A |  | 2023-12-21 | 2024-02-01 | 2024-10-13 | 2024-11-07 | 2024-05-03 | 2024-07-22 | 2024-07-23 | 2024-09-06 | BOP Plant | Plant EPC)기계기술1팀 | Potable Water System | Process | 홍성민 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C98D19D399B549EEAB6D0EE0FB56120C
DDCL | CCP-PW-B038-PR-005-0001 | Utility Flow_Diagram_Raw Water System | D | C | 01 | A |  | 2023-12-21 | 2024-02-01 | 2024-08-29 | 2024-09-23 | 2024-05-03 | 2024-07-22 | 2024-07-23 | 2024-09-04 | BOP Plant | Plant EPC)기계기술1팀 | Raw Water System | Process | 홍성민 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:521C24E3B1CF4591A1ADD0D489600608
DDCL | CCP-PW-B036-PR-005-0001 | Utility Flow_Diagram_Service Water System | D | C | 01 | A |  | 2023-12-21 | 2024-02-01 | 2024-08-29 | 2024-09-23 | 2024-05-03 | 2024-07-22 | 2024-07-23 | 2024-09-04 | BOP Plant | Plant EPC)기계기술1팀 | Service Water System | Process | 홍성민 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:295B980B6CE942AF9B94D2CD1B148678
DDCL | CCP-PW-B134-PR-006-0001 | UFD for Hot Water Distribution System | R | C | 01 | _ |  | 2023-11-28 | 2024-01-27 | 2024-05-23 | 2024-07-22 | 2024-03-08 | 2023-08-16 | 2024-08-22 | 2024-09-02 | BOP Plant | Plant EPC)프로세스기술1팀 | Hot Water Distribution System | Process | 김정민 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:85AA7FDC175948B4B83FC26A16F19A4D
DDCL | CCP-W-B000-PR-REP-0002 | HAZARDOUS AREA CLASSIFICATION | D | D | 01 | _ |  | 2024-01-05 | 2024-02-16 | 2024-04-05 | 2024-05-24 | 2024-02-08 | 2024-06-17 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Plant Overall design | Process | 이현지 | [10 empty] | CCP-EPC-TRM-PGU-0194 | D | 01 | 2024-06-17 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0194 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0194 | D | 01 | 2024-06-17 | 2024-06-18 | 2024-06-28 | CCP-PGU-TRM-EPC-0194 | Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1796B228553B42BC9467375748CE3169
DDCL | CCP-W-B000-PR-REP-0001 | HAZOP SIL CLASSIFICATION PROCEDURE | D | C | 01 | _ |  | 2024-02-16 | 2024-03-29 | 2024-05-17 | 2024-06-28 | 2024-03-15 | 2024-05-20 | 2024-07-02 | 2024-07-04 | BOP Plant | Plant EPC)프로세스기술1팀 | Plant Overall design | Process | 이현지 | [10 empty] | CCP-EPC-TRM-PGU-0247 | C | 01 | 2024-07-04 | 2024-08-05 | 2024-05-30 | CCP-PGU-TRM-EPC-0151 | D | 01 | Deemed Approved | CCP-EPC-TRM-PGU-0151 | D | 01 | 2024-05-20 | 2024-05-20 | 2024-05-30 | CCP-PGU-TRM-EPC-0151 | Deemed Approved | CCP-EPC-TRM-PGU-0247 | C | 01 | 2024-07-04 | 2024-08-05 | [83 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1097273819B040B5BE9A1ACF97CAF5DF
DDCL | CCP-W-B000-PR-REP-0003 | HAZOP STUDY REPORT | D | C | 01 | _ |  | 2024-08-09 | 2024-09-13 | 2024-11-01 | 2024-12-20 | 2024-10-16 | 2024-10-16 | 2024-11-27 | 2024-11-28 | BOP Plant | Plant EPC)프로세스기술1팀 | Plant Overall design | Process | 이현지 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:39F1312D62794E85816C115BD01B2FCF
DDCL | CCP-W-B000-PR-REP-0004 | SIL CLASSIFICATION STUDY REPORT | D | C | 01 | _ |  | 2024-09-02 | 2024-11-10 | 2024-11-11 | 2024-12-29 | 2024-11-01 | 2025-03-18 | 2025-04-09 | 2025-04-09 | BOP Plant | Plant EPC)프로세스기술1팀 | Plant Overall design | Process | 이현지 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:BC7059D6B9C041F88D2F2972A443454D
DDCL | CCP-W-B000-PR-026-0003 | Steam Blowing Out Procedure | D | D | 01 | _ | FA DELAY | 2025-05-23 | 2025-07-04 | 2025-08-20 | 2026-10-01 |  |  |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Plant Overall design | Process | 안진엽 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A829DC4952C94DE49ECCF5706EE50EBE
DDCL | CCP-W-B000-PR-026-0002 | Plant Start-up & Shutdown Procedure | D | C | 01 | _ |  | 2024-04-29 | 2024-05-10 | 2024-06-28 | 2024-08-09 | 2025-04-01 | 2025-04-01 | 2025-05-20 | 2025-05-20 | BOP Plant | Plant EPC)프로세스기술1팀 | Plant Overall design | Process | 이현지 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:5B73D5AB67464C9FA14833FE777CF9D1
DDCL | CCP-W-B000-PR-026-0001 | Plant Operation Philosophy | D | C | 01 | _ |  | 2024-03-15 | 2024-04-26 | 2024-06-14 | 2024-07-26 | 2024-10-25 | 2024-10-25 | 2025-02-19 | 2025-02-19 | BOP Plant | Plant EPC)프로세스기술1팀 | Plant Overall design | Process | 이현지 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:50046D70EC1C47909264DE46586ED953
DDCL | CCP-P-B000-PR-HBD-0001 | Heat and mass Balance Diagram | D | C | 01 | _ |  | 2023-06-08 | 2023-07-20 | 2025-01-24 | 2025-01-31 | 2024-01-22 | 2023-07-20 | 2025-01-20 | 2025-01-23 | BOP Plant | Plant EPC)프로세스기술1팀 | Plant Overall design | Process | 박성용 | [116 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:A186AAB4193D4C02962690B360CF08E8
DDCL | CCP-P-B062-AC-550-0001 | LEB for Block #1_CALCULATION | D | D | 01 | _ |  | 2023-12-07: 2024-04-20; 2024-02-15: 2024-07-19 |  |  | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #1 | Architecture & Structure | 김홍재 | [10 empty] | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | D | 01 | Approved | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E40516B2E2534F3DB8CAF8CBD4B5564D
DDCL | CCP-P-B264-AC-550-0001 | LEB for Block #2_CALCULATION | D | D | 01 | _ |  | 2023-12-07: 2024-04-20; 2024-02-15: 2024-07-19 |  |  | BOP Plant | Plant EPC)건축기술2팀 | LEB for Block #2 | Architecture & Structure | 김홍재 | [10 empty] | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | D | 01 | Approved | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:0A9DE388780D4B4F9E6EC018E6CC40EE
DDCL | CCP-P-B061-AC-550-0001 | Main Building_CALCULATION | D | D | 01 | _ |  | 2023-12-07: 2024-01-23; 2024-02-15: 2024-05-22 |  |  | BOP Plant | Plant EPC)건축기술2팀 | Main Building | Architecture & Structure | 조성은 | [10 empty] | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | D | 01 | Approved | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CAD5215FF1F24BC6994F937EFACAAC5F
DDCL | CCP-P-B089-EL-351-0001 | DESIGN CRITERIA_ELECTRICAL SYSTEM | D | D | 01 | _ |  | 2023-12-07: 2024-01-05; 2024-02-15: 2024-01-26; 2024-06-14: 2023-12-11 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Elec_Design Criteria Design | Electrical | 정백경 | [10 empty] | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | D | 01 | Approved | CCP-EPC-TRM-PGU-0017 | R | 01 | 2023-09-18 | 2023-09-18 | 2023-10-06 | CCP-PGU-TRM-EPC-0017 | Approved With Comment | CCP-EPC-TRM-PGU-0080 CCP-DE-LTR-PGU-0290 | D | 01 | 2023-12-11 2024-02-06 | 2023-12-11 2024-02-06 | 2024-01-13 2024-05-27 | CCP-PGU-TRM-EPC-0080 CCP-PGU-LTR-DE-0457 | Approved With Comment Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:AFDE0B68CBC548309362EEA24FFF2393
DDCL | CCP-P-B089-EL-356-0001 | SYMBOL & LEGENDS_ELECTRICAL SYSTEM | D | D | 01 | _ |  | 2023-12-07: 2024-01-05; 2024-02-15: 2024-01-26; 2024-06-14: 2023-10-26 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Elec_KeySLD Design | Electrical | 정백경 | [10 empty] | CCP-EPC-TRM-PGU-0066 | D | 01 | 2023-10-26 | 2023-10-26 | 2023-10-16 | CCP-PGU-TRM-EPC-0040 | R | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0040 | R | 01 | 2023-10-06 | 2023-10-06 | 2023-10-16 | CCP-PGU-TRM-EPC-0040 | Approved With Comment | CCP-EPC-TRM-PGU-0066 | D | 01 | 2023-10-26 | 2023-10-26 | [83 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4AB6041A53E24DC6957A46E61DAC274C
DDCL | CCP-P-B089-EL-351-0002 | DESIGN CRITERIA & CABLE SIZING CALCULATION - MV/LV POWER CABLE | D | D | 01 | _ |  | 2023-12-07: 2024-01-18; 2024-02-15: 2024-02-29; 2024-06-14: 2024-02-06 |  |  | BOP Plant | Plant EPC)전력/배전기술2팀 | Elec_Power & Control Cable Design | Electrical | 최준호 | [10 empty] | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | D | 01 | Approved | CCP-EPC-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | CCP-PGU-LTR-EPC-0290 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:87CC1584B9E5446F8B89B441F9680542
DDCL | CCP-P-B043-PR-049-0001 | Sizing Calculation_Black Start Emergency Diesel Generator | R | R | 01 | _ |  | 2023-12-07: 2023-07-15; 2024-02-15: 2023-09-13; 2024-06-14: 2023-09-19 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | BSEDG | Mechanical | 박재현 | [10 empty] | CCP-EPC-TRM-PGU-0018 | R | 01 | 2023-09-19 | 2023-09-19 | 2023-10-05 | CCP-PGU-TRM-EPC-0018 | R | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0018 | R | 01 | 2023-09-19 | 2023-09-19 | 2023-10-05 | CCP-PGU-TRM-EPC-0018 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:85814241846D4E58B74C69032E4E63F7
DDCL | CCP-P-B043-PR-003-0001 | System Description for Black Start Emergency Diesel Generator | R | R | 01 | _ |  | 2023-08-12 | 2023-10-11 |  |  | 2024-01-03 | 2023-07-17 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | BSEDG | Mechanical | 박재현 | [10 empty] | CCP-EPC-TRM-PGU-0001 | R | 01 | 2023-07-17 | 2023-07-17 | 2023-07-22 | CCP-PGU-LTR-EPC-0066 | R | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0001 | R | 01 | 2023-07-17 | 2023-07-17 | 2023-07-22 | CCP-PGU-LTR-EPC-0066 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:523442E295A64C14897D1C947935EE65
DDCL | CCP-P-B134-PR-049-0001 | Sizing Calculation_Hot Water Supply Pump | D | D | 01 | _ |  | 2023-12-07: 2023-07-15; 2024-02-15: 2023-09-13; 2024-06-11: 2024-03-08 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Hot Water Supply Pump | Mechanical | 김정민 | [10 empty] | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | D | 01 | Approved | CCP-EPC-TRM-PGU-0018 | R | 01 | 2023-09-19 | 2023-09-19 | 2023-10-05 | CCP-PGU-TRM-EPC-0018 | Approved With Comment | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E1B8451B950E48C6979045363A2E6BCE
DDCL | CCP-P-B000-EM-PPI-0001 | Document Numbering Procedure | D | D | 01 | _ |  | 2023-12-07: 2024-03-11; 2024-02-15: 2024-04-10 |  |  | BOP Plant | Plant EPC)Plant EPC EM1팀 | General Technical Document | Common | 서장원 | [10 empty] | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | D | 01 | Approved | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:147B22AE193F4884B454C2A79359157C
DDCL | CCP-P-B000-EM-SPC-0002 | Unit, Equipment, Line and Instrument Numbering Procedure | D | D | 01 | _ |  | 2024-03-11 | 2024-04-10 |  |  | 2024-02-29 | 2024-05-31 |  |  | BOP Plant | Plant EPC)Plant EPC EM1팀 | General Technical Document | Common | 서장원 | [10 empty] | CCP-EPC-TRM-PGU-0161 | D | 01 | 2024-05-31 | 2024-05-31 | 2024-06-10 | CCP-PGU-TRM-EPC-0161 | D | 01 | Deemed Approved | CCP-DE-LTR-PGU-0290 CCP-EPC-TRM-PGU-0161 | D | 01 | 2024-02-06 2024-05-31 | 2024-02-06 2024-05-31 | 2024-05-27 2024-06-10 | CCP-PGU-LTR-DE-0457 CCP-PGU-TRM-EPC-0161 | Approved Deemed Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:794A8368268341E288C34CC71C4FA857
DDCL | CCP-P-B040-PR-003-0002 | SYSTEM DESCRIPTION_Compressed Air System | D | D | 01 | _ |  | 2023-12-07: 2023-08-23; 2024-02-15: 2023-10-04; 2024-06-14: 2023-09-21 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Compressed Air System | Process | 김광희 | [10 empty] | CCP-EPC-TRM-PGU-0021 | D | 01 | 2023-09-21 | 2023-09-21 | [5 empty] | CCP-EPC-TRM-PGU-0021 | D | 01 | 2023-09-21 | 2023-09-21 | [91 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8FD3D48D04DC4A69B70F4DAB7AD20719
DDCL | CCP-P-B040-PR-003-0001 | DESIGN CRITERIA_Compressed Air System | D | D | 01 | _ |  | 2023-12-07: 2023-08-23; 2024-02-15: 2023-10-04; 2024-06-14: 2023-09-21 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Compressed Air System | Process | 김광희 | [10 empty] | CCP-EPC-TRM-PGU-0021 | D | 01 | 2023-09-21 | 2023-09-21 | [5 empty] | CCP-EPC-TRM-PGU-0021 | D | 01 | 2023-09-21 | 2023-09-21 | [91 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3A79FF9076404356A4C2EF951E2CD6AE
DDCL | CCP-P-B040-PR-049-0001 | SIZING CALCULATION_Compressed Air System | D | D | 01 | _ |  | 2023-08-31 | 2023-10-12 |  |  | 2024-03-11 | 2024-05-31 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Compressed Air System | Process | 김광희 | [10 empty] | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | D | 01 | Approved | CCP-EPC-TRM-PGU-0013 | R | 01 | 2023-09-15 | 2023-09-15 | 2023-10-09 | CCP-PGU-TRM-EPC-0013 | Approved With Comment | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:59D0E99DC1A44990AABFE8BA502F13EB
DDCL | CCP-P-B128-PR-003-0001 | System Description_Auxiliary Steam System | R | R | 01 | _ |  | 2023-12-07: 2023-10-01; 2024-02-15: 2023-11-12; 2024-06-14: 2023-07-17 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Auxiliary Steam Distribution System | Process | 안진엽 | [10 empty] | CCP-EPC-TRM-PGU-0001 | R | 01 | 2023-07-17 | 2023-07-17 | 2023-07-22 | CCP-PGU-LTR-EPC-0066 | R | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0001 | R | 01 | 2023-07-17 | 2023-07-17 | 2023-07-22 | CCP-PGU-LTR-EPC-0066 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:8509F1D8DCCE490F83918BB14759C62C
DDCL | CCP-P-B128-PR-021-0001 | Design Criteria_Auxiliary Steam System | R | R | 01 | _ |  | 2023-12-07: 2023-08-19; 2024-02-15: 2023-09-30; 2024-06-14: 2023-07-04 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Auxiliary Steam Distribution System | Process | 안진엽 | [10 empty] | CCP-EPC-LTR-PGU-0020 | R | 01 | 2023-07-04 | 2023-07-04 | [5 empty] | CCP-EPC-LTR-PGU-0020 | R | 01 | 2023-07-04 | 2023-07-04 | [91 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:AFD01955B5EB4F9D97AAE325FF3509AB
DDCL | CCP-P-B129-PR-003-0001 | System Description_Condensate System | R | R | 01 | _ |  | 2023-12-07: 2023-08-12; 2024-02-15: 2023-10-11; 2024-06-14: 2023-07-17 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Condensate System | Process | 김정민 | [10 empty] | CCP-EPC-TRM-PGU-0001 | R | 01 | 2023-07-17 | 2023-07-17 | 2023-07-22 | CCP-PGU-LTR-EPC-0066 | R | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0001 | R | 01 | 2023-07-17 | 2023-07-17 | 2023-07-22 | CCP-PGU-LTR-EPC-0066 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:ACAFE5DED1A24186B866CD7ACF4167A9
DDCL | CCP-P-B129-PR-021-0001 | Design Criteria_Condensate System | R | R | 01 | _ |  | 2023-12-07: 2023-08-12; 2024-02-15: 2023-10-11; 2024-06-14: 2023-07-04 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Condensate System | Process | 김정민 | [10 empty] | CCP-EPC-LTR-PGU-0020 | R | 01 | 2023-07-04 | 2023-07-04 | [5 empty] | CCP-EPC-LTR-PGU-0020 | R | 01 | 2023-07-04 | 2023-07-04 | [91 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2E799F9BD3734D668F5ACC3B4ADD46DA
DDCL | CCP-P-B129-PR-049-0001 | Sizing Calculation_Condensate Extraction Pump | D | D | 01 | _ |  | 2023-12-07: 2023-07-15; 2024-02-15: 2023-09-13; 2024-06-11: 2024-03-05 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Condensate System | Process | 김정민 | [10 empty] | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | D | 01 | Approved | CCP-EPC-TRM-PGU-0018 | R | 01 | 2023-09-19 | 2023-09-19 | 2023-10-05 | CCP-PGU-TRM-EPC-0018 | Approved With Comment | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:F020768F15424E5CB3268649C63CEFE3
DDCL | CCP-P-B035-PR-003-0001 | System Description_Demineralized Water System | R | R | 01 | _ |  | 2023-12-07: 2023-10-01; 2024-02-15: 2023-11-12; 2024-06-14: 2023-07-17 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Demineralized Water System | Process | 박성용 | [10 empty] | CCP-EPC-TRM-PGU-0001 | R | 01 | 2023-07-17 | 2023-07-17 | 2023-07-22 | CCP-PGU-LTR-EPC-0066 | R | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0001 | R | 01 | 2023-07-17 | 2023-07-17 | 2023-07-22 | CCP-PGU-LTR-EPC-0066 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4F9957F5D13B4CB48D5FCA7F7B6ACC87
DDCL | CCP-P-B035-PR-021-0001 | Design Criteria_Demineralized Water System | R | R | 01 | _ |  | 2023-12-07: 2023-08-19; 2024-02-15: 2023-09-30; 2024-06-14: 2023-07-04 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Demineralized Water System | Process | 박성용 | [10 empty] | CCP-EPC-LTR-PGU-0020 | R | 01 | 2023-07-04 | 2023-07-04 | [5 empty] | CCP-EPC-LTR-PGU-0020 | R | 01 | 2023-07-04 | 2023-07-04 | [91 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FC2F0BD39C8D46BDBD56CB90F0976D6F
DDCL | CCP-P-B035-PR-049-0001 | Sizing Calculation_Demi Water Pump | R | R | 01 | _ |  | 2023-12-07: 2023-08-02; 2024-02-15: 2023-09-13; 2024-06-14: 2023-09-19 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Demineralized Water System | Process | 박성용 | [10 empty] | CCP-EPC-TRM-PGU-0018 | R | 01 | 2023-09-19 | 2023-09-19 | 2023-10-05 | CCP-PGU-TRM-EPC-0018 | R | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0018 | R | 01 | 2023-09-19 | 2023-09-19 | 2023-10-05 | CCP-PGU-TRM-EPC-0018 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2A6EAEE5195F415FAB4F409C6D4A6978
DDCL | CCP-P-B130-PR-003-0001 | System Description_Feedwater System | R | R | 01 | _ |  | 2023-12-07: 2023-10-01; 2024-02-15: 2023-11-12; 2024-06-14: 2023-07-17 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Feedwater System | Process | 박성용 | [10 empty] | CCP-EPC-TRM-PGU-0001 | R | 01 | 2023-07-17 | 2023-07-17 | 2023-07-22 | CCP-PGU-LTR-EPC-0066 | R | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0001 | R | 01 | 2023-07-17 | 2023-07-17 | 2023-07-22 | CCP-PGU-LTR-EPC-0066 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C920230671414829856F27D0A45736EB
DDCL | CCP-P-B130-PR-021-0001 | Design Criteria_Feedwater System | R | R | 01 | _ |  | 2023-12-07: 2023-08-19; 2024-02-15: 2023-09-30; 2024-06-14: 2023-07-04 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Feedwater System | Process | 박성용 | [10 empty] | CCP-EPC-LTR-PGU-0020 | R | 01 | 2023-07-04 | 2023-07-04 | [5 empty] | CCP-EPC-LTR-PGU-0020 | R | 01 | 2023-07-04 | 2023-07-04 | [91 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:11194EB0FFFB48A0887FD6D198960A0E
DDCL | CCP-P-B130-PR-049-0001 | Sizing Calculation_Boiler Feed Pump | R | R | 01 | _ |  | 2023-12-07: 2023-08-02; 2024-02-15: 2023-09-13; 2024-06-14: 2023-09-19 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Feedwater System | Process | 박성용 | [10 empty] | CCP-EPC-TRM-PGU-0018 | R | 01 | 2023-09-19 | 2023-09-19 | 2023-10-05 | CCP-PGU-TRM-EPC-0018 | R | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0018 | R | 01 | 2023-09-19 | 2023-09-19 | 2023-10-05 | CCP-PGU-TRM-EPC-0018 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:85E9C9B5084E4C9DAB083009AE34D5AA
DDCL | CCP-P-B046-PR-003-0002 | System Description_Fuel Oil System | D | D | 01 | A |  | 2023-12-07: 2023-07-22; 2024-02-15: 2023-08-21; 2024-06-11: 2025-05-30 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Oil System | Process | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0021 | D | 01 | 2023-09-21 | 2023-09-21 | [5 empty] | CCP-EPC-TRM-PGU-0021 | D | 01 | 2023-09-21 | 2023-09-21 | [91 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:50FF52FD9EFA4C05AA5425324C95A4D8
DDCL | CCP-P-B044-PR-003-0002 | SYSTEM DESCRIPTION_Fuel gas supply system | D | D | 01 | _ |  | 2023-12-07: 2023-08-23; 2024-02-15: 2023-10-04; 2024-06-14: 2023-09-21 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel gas supply system | Process | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0021 | D | 01 | 2023-09-21 | 2023-09-21 | [5 empty] | CCP-EPC-TRM-PGU-0021 | D | 01 | 2023-09-21 | 2023-09-21 | [91 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7088D62AAC4842FE8AC515ADEEFA11EE
DDCL | CCP-P-B052-PR-003-0002 | System Description_Oil facility system | D | D | 01 | A |  | 2023-12-07: 2023-08-23; 2024-02-15: 2023-10-04; 2024-06-11: 2025-03-14 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Oil facility system | Process | 김광희 | [10 empty] | CCP-EPC-TRM-PGU-0021 | D | 01 | 2023-09-21 | 2023-09-21 | [5 empty] | CCP-EPC-TRM-PGU-0021 | D | 01 | 2023-09-21 | 2023-09-21 | [91 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7F21DED6F8AC4B7683882A5395C87875
DDCL | CCP-P-B046-PR-003-0001 | Design Criteria_Fuel Oil System | D | D | 01 | A |  | 2023-12-07: 2023-07-22; 2024-02-15: 2023-08-21; 2024-06-11: 2025-05-30 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Oil System | Process | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0021 | D | 01 | 2023-09-21 | 2023-09-21 | [5 empty] | CCP-EPC-TRM-PGU-0021 | D | 01 | 2023-09-21 | 2023-09-21 | [91 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:519F54313D774804A9E285D8651A952D
DDCL | CCP-P-B052-PR-003-0001 | Design Criteria_Oil facility system | D | D | 01 | A |  | 2023-12-07: 2023-08-23; 2024-02-15: 2023-10-04; 2024-06-11: 2025-03-14 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Oil facility system | Process | 김광희 | [10 empty] | CCP-EPC-TRM-PGU-0021 | D | 01 | 2023-09-21 | 2023-09-21 | [5 empty] | CCP-EPC-TRM-PGU-0021 | D | 01 | 2023-09-21 | 2023-09-21 | [91 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:47FF62071D314451A23D7BEB0345BD6C
DDCL | CCP-P-B044-PR-003-0001 | DESIGN CRITERIA_Fuel gas supply system | D | D | 01 | _ |  | 2023-12-07: 2023-08-23; 2024-02-15: 2023-10-04; 2024-06-14: 2023-09-21 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel gas supply system | Process | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0021 | D | 01 | 2023-09-21 | 2023-09-21 | [5 empty] | CCP-EPC-TRM-PGU-0021 | D | 01 | 2023-09-21 | 2023-09-21 | [91 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4017D50FF1B24C8381D0695C9B66C940
DDCL | CCP-P-B046-PR-049-0001 | Sizing Calculation_Fuel Oil System | R | R | 01 | _ |  | 2023-12-07: 2023-07-30; 2024-02-15: 2023-08-29; 2024-06-14: 2023-09-15 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel Oil System | Process | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0013 | R | 01 | 2023-09-15 | 2023-09-15 | 2023-10-09 | CCP-PGU-TRM-EPC-0013 | R | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0013 | R | 01 | 2023-09-15 | 2023-09-15 | 2023-10-09 | CCP-PGU-TRM-EPC-0013 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:601F51A141DF4DB9A1D38AC12D43E21F
DDCL | CCP-P-B044-PR-049-0001 | SIZING CALCULATION_Fuel gas supply system | R | R | 01 | _ |  | 2023-12-07: 2023-08-31; 2024-02-15: 2023-10-12; 2024-06-14: 2023-09-15 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Fuel gas supply system | Process | 박동준 | [10 empty] | CCP-EPC-TRM-PGU-0013 | R | 01 | 2023-09-15 | 2023-09-15 | 2023-10-09 | CCP-PGU-TRM-EPC-0013 | R | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0013 | R | 01 | 2023-09-15 | 2023-09-15 | 2023-10-09 | CCP-PGU-TRM-EPC-0013 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:4EACDA3094F54FB3A0D116EB174DC259
DDCL | CCP-P-B052-PR-049-0001 | Sizing Calculation_Oil facility system | D | D | 01 | _ |  | 2023-08-31 | 2023-10-12 |  |  | 2024-02-01 | 2024-03-05 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Oil facility system | Process | 김광희 | [10 empty] | CCP-EPC-TRM-PGU-0099 | D | 01 | 2024-03-05 | 2024-03-05 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | D | 01 | Approved | CCP-EPC-TRM-PGU-0013 | R | 01 | 2023-09-15 | 2023-09-15 | 2023-10-09 | CCP-PGU-TRM-EPC-0013 | Approved With Comment | CCP-DE-LTR-PGU-0290 CCP-EPC-TRM-PGU-0099 | D | 01 | 2024-02-06 2024-03-05 | 2024-02-06 2024-03-05 | 2024-03-18 2024-05-27 | CCP-PGU-EPC-TRM-0099 CCP-PGU-LTR-DE-0457 | Approved With Comment Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CB309C1B1CD744F1B871CDD19EF58CE2
DDCL | CCP-P-B132-PR-003-0001 | System Description_Closed Cooling Water System | R | R | 01 | _ |  | 2023-12-07: 2023-08-12; 2024-02-15: 2023-10-11; 2024-06-14: 2023-07-17 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Closed Cooling Water System | Process | 박재현 | [10 empty] | CCP-EPC-TRM-PGU-0001 | R | 01 | 2023-07-17 | 2023-07-17 | 2023-07-22 | CCP-PGU-LTR-EPC-0066 | R | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0001 | R | 01 | 2023-07-17 | 2023-07-17 | 2023-07-22 | CCP-PGU-LTR-EPC-0066 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:E87929C3FB1443228C6F053C3C90CAEE
DDCL | CCP-P-B132-PR-021-0001 | Design Criteria_Сlosed Сooling Water System | R | R | 01 | _ |  | 2023-12-07: 2023-08-12; 2024-02-15: 2023-10-11; 2024-06-14: 2023-07-04 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Closed Cooling Water System | Process | 박재현 | [10 empty] | CCP-EPC-LTR-PGU-0020 | R | 01 | 2023-07-04 | 2023-07-04 | [5 empty] | CCP-EPC-LTR-PGU-0020 | R | 01 | 2023-07-04 | 2023-07-04 | [91 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:91414A93020A443D878EF35A4D1C1EA7
DDCL | CCP-P-B132-PR-049-0001 | Sizing Calculation_Closed Cooling Water Pump | D | D | 01 | _ |  | 2023-12-07: 2023-07-15; 2024-02-15: 2023-09-13; 2024-06-11: 2024-05-14 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Closed Cooling Water System | Process | 박재현 | [10 empty] | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | D | 01 | Approved | CCP-EPC-TRM-PGU-0018 | R | 01 | 2023-09-19 | 2023-09-19 | 2023-10-05 | CCP-PGU-TRM-EPC-0018 | Approved With Comment | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:58D95605AF284C8B85DA3F44433EF4A2
DDCL | CCP-P-B126-PR-003-0001 | System Description_HP & LP Steam System | R | R | 01 | _ |  | 2023-12-07: 2023-10-01; 2024-02-15: 2023-11-12; 2024-06-14: 2023-07-17 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | HP & LP Steam System | Process | 안진엽 | [10 empty] | CCP-EPC-TRM-PGU-0001 | R | 01 | 2023-07-17 | 2023-07-17 | 2023-07-22 | CCP-PGU-LTR-EPC-0066 | R | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0001 | R | 01 | 2023-07-17 | 2023-07-17 | 2023-07-22 | CCP-PGU-LTR-EPC-0066 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:D196D79701CB42A1870C3B15D9D5956B
DDCL | CCP-P-B126-PR-021-0001 | Design Criteria_HP & LP Steam System | R | R | 01 | _ |  | 2023-12-07: 2023-08-19; 2024-02-15: 2023-09-30; 2024-06-14: 2023-07-04 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | HP & LP Steam System | Process | 안진엽 | [10 empty] | CCP-EPC-LTR-PGU-0020 | R | 01 | 2023-07-04 | 2023-07-04 | [5 empty] | CCP-EPC-LTR-PGU-0020 | R | 01 | 2023-07-04 | 2023-07-04 | [91 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FF1465770B4C4243BEC31B099DF24168
DDCL | CPP-P-B134-PR-003-0001 | System Description for Hot Water Distribution System | R | R | 01 | _ |  | 2023-12-07: 2023-08-12; 2024-02-15: 2023-10-11; 2024-06-14: 2023-07-17 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Hot Water Distribution System | Process | 김정민 | [10 empty] | CCP-EPC-TRM-PGU-0001 | R | 01 | 2023-07-17 | 2023-07-17 | [5 empty] | CCP-EPC-TRM-PGU-0001 | R | 01 | 2023-07-17 | 2023-07-17 | [91 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CC589AFDF8AC49F4A485DFC2681BBAFC
DDCL | CCP-P-B036-PR-003-0002 | System Description_Service Water System | D | D | 01 | _ |  | 2023-12-07: 2023-08-23; 2024-02-15: 2023-10-04; 2024-06-11: 2024-02-14 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Service Water System | Process | 홍성민 | [10 empty] | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | D | 01 | Approved | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:FB900C43C0A14B93B1E555ECB1014BA1
DDCL | CCP-P-B038-PR-003-0002 | System Description_Raw Water System | D | D | 01 | _ |  | 2023-12-07: 2023-08-23; 2024-02-15: 2023-10-04; 2024-06-11: 2024-02-14 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Raw Water System | Process | 홍성민 | [10 empty] | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | D | 01 | Approved | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:1802C8D219AF4DB7863010F8DCA23357
DDCL | CCP-P-B037-PR-003-0002 | System Description_Potable Water System | D | D | 01 | _ |  | 2023-12-07: 2023-08-23; 2024-02-15: 2023-10-04; 2024-06-11: 2024-02-14 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Potable Water System | Process | 홍성민 | [10 empty] | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | D | 01 | Approved | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:7A18CE1A25684FC5A62924F964849987
DDCL | CCP-P-B037-PR-003-0001 | Design Criteria_Potable Water System | D | D | 01 | _ |  | 2023-12-07: 2023-08-23; 2024-02-15: 2023-10-04; 2024-06-11: 2024-02-14 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Potable Water System | Process | 홍성민 | [10 empty] | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | D | 01 | Approved | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C8BC9CF694944835BD89F8343C2F83F4
DDCL | CCP-P-B038-PR-003-0001 | Design Criteria_Raw Water System | D | D | 01 | _ |  | 2023-12-07: 2023-08-23; 2024-02-15: 2023-10-04; 2024-06-11: 2024-02-14 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Raw Water System | Process | 홍성민 | [10 empty] | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | D | 01 | Approved | CCP-EPC-TRM-PGU-0007 | R | 01 | 2023-08-22 | 2023-08-22 |  |  |  | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:32DF3ACCFDA14F5A964A60A276F69900
DDCL | CCP-P-B036-PR-003-0001 | Design Criteria_Service Water System | D | D | 01 | _ |  | 2023-12-07: 2023-08-23; 2024-02-15: 2023-10-04; 2024-06-11: 2024-02-14 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Service Water System | Process | 홍성민 | [10 empty] | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | D | 01 | Approved | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | Approved | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:320684A9734243F7845B15F6468E7DB4
DDCL | CCP-P-B134-PR-021-0001 | Design Criteria_Hot Water Distribution System | R | R | 01 | _ |  | 2023-12-07: 2023-08-12; 2024-02-15: 2023-10-11; 2024-06-14: 2023-07-04 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Hot Water Distribution System | Process | 김정민 | [10 empty] | CCP-EPC-LTR-PGU-0020 | R | 01 | 2023-07-04 | 2023-07-04 | [5 empty] | CCP-EPC-LTR-PGU-0020 | R | 01 | 2023-07-04 | 2023-07-04 | [91 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:B014F1BC76484A8AB0429B769C4A3718
DDCL | CCP-P-B036-PR-049-0001 | Sizing Calculation_Service Water System | R | R | 01 | _ |  | 2023-12-07: 2023-08-31; 2024-02-15: 2023-10-12; 2024-06-14: 2023-09-15 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Service Water System | Process | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0013 | R | 01 | 2023-09-15 | 2023-09-15 | 2023-10-09 | CCP-PGU-TRM-EPC-0013 | R | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0013 | R | 01 | 2023-09-15 | 2023-09-15 | 2023-10-09 | CCP-PGU-TRM-EPC-0013 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:62498ED733534C589149A2083F79AA6A
DDCL | CCP-P-B038-PR-049-0001 | Sizing Calculation_Raw Water System | R | R | 01 | _ |  | 2023-12-07: 2023-08-31; 2024-02-15: 2023-10-12; 2024-06-14: 2023-09-15 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Raw Water System | Process | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0013 | R | 01 | 2023-09-15 | 2023-09-15 | 2023-10-09 | CCP-PGU-TRM-EPC-0013 | R | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0013 | R | 01 | 2023-09-15 | 2023-09-15 | 2023-10-09 | CCP-PGU-TRM-EPC-0013 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:65E2861FD0BD498B95FE4E77872DBB95
DDCL | CCP-P-B037-PR-049-0001 | Sizing Calculation_Potable Water System | R | R | 01 | _ |  | 2023-12-07: 2023-08-31; 2024-02-15: 2023-10-12; 2024-06-14: 2023-09-15 |  |  | BOP Plant | Plant EPC)기계기술1팀 | Potable Water System | Process | 홍성민 | [10 empty] | CCP-EPC-TRM-PGU-0013 | R | 01 | 2023-09-15 | 2023-09-15 | 2023-10-09 | CCP-PGU-TRM-EPC-0013 | R | 01 | Approved With Comment | CCP-EPC-TRM-PGU-0013 | R | 01 | 2023-09-15 | 2023-09-15 | 2023-10-09 | CCP-PGU-TRM-EPC-0013 | Approved With Comment | [88 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:C488ECC28CCE4262B02610FD52C7DE7F
DDCL | CCP-P-B189-PR-007-0001-001 | P&ID_Symbol & Legend (1 of 4) | D | D | 01 | _ |  | 2023-12-07: 2023-08-01; 2024-02-15: 2023-09-12; 2024-06-14: 2023-09-12 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Symbol & Legend | Process | 안진엽 | [10 empty] | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | D | 01 | Approved | CCP-EPC-LTR-PGU-0012 | R | 01 | 2023-06-20 | 2023-06-20 | 2023-07-12 | CCP-EPC-LTR-PGU-0058 | Approved With Comment | CCP-EPC-TRM-PGU-0010 CCP-DE-LTR-PGU-0290 | D | 01 | 2023-09-12 2024-02-06 | 2023-09-12 2024-02-06 | 2023-10-06 2024-05-27 | CCP-PGU-TRM-EPC-0010 CCP-PGU-LTR-DE-0457 | Approved With Comment Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:CA45A9F13C034D1CBB045BE2BDB91CEE
DDCL | CCP-P-B189-PR-007-0001-002 | P&ID_Symbol & Legend (2 of 4) | D | D | 01 | _ |  | 2023-12-07: 2023-08-01; 2024-02-15: 2023-09-12; 2024-06-14: 2023-09-12 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Symbol & Legend | Process | 안진엽 | [10 empty] | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | D | 01 | Approved | CCP-EPC-LTR-PGU-0013 | R | 01 | 2023-06-21 | 2023-06-21 | 2023-07-12 | CCP-EPC-LTR-PGU-0058 | Approved With Comment | CCP-EPC-TRM-PGU-0010 CCP-DE-LTR-PGU-0290 | D | 01 | 2023-09-12 2024-02-06 | 2023-09-12 2024-02-06 | 2023-10-06 2024-05-27 | CCP-PGU-TRM-EPC-0010 CCP-PGU-LTR-DE-0457 | Approved With Comment Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:3A80439D20554190BC627983E087AB63
DDCL | CCP-P-B189-PR-007-0001-003 | P&ID_Symbol & Legend (3 of 4) | D | D | 01 | _ |  | 2023-12-07: 2023-08-01; 2024-02-15: 2023-09-12; 2024-06-14: 2023-09-12 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Symbol & Legend | Process | 안진엽 | [10 empty] | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | D | 01 | Approved | CCP-EPC-LTR-PGU-0014 | R | 01 | 2023-06-22 | 2023-06-22 | 2023-07-12 | CCP-EPC-LTR-PGU-0058 | Approved With Comment | CCP-EPC-TRM-PGU-0010 CCP-DE-LTR-PGU-0290 | D | 01 | 2023-09-12 2024-02-06 | 2023-09-12 2024-02-06 | 2023-10-06 2024-05-27 | CCP-PGU-TRM-EPC-0010 CCP-PGU-LTR-DE-0457 | Approved With Comment Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:2EB8D7DBF6A34AC68BC7D5377C89FC33
DDCL | CCP-P-B189-PR-007-0001-004 | P&ID_Symbol & Legend (4 of 4) | D | D | 01 | _ |  | 2023-12-07: 2023-08-01; 2024-02-15: 2023-09-12; 2024-06-14: 2023-09-12 |  |  | BOP Plant | Plant EPC)프로세스기술1팀 | Symbol & Legend | Process | 안진엽 | [10 empty] | CCP-DE-LTR-PGU-0290 | D | 01 | 2024-02-06 | 2024-02-06 | 2024-05-27 | CCP-PGU-LTR-DE-0457 | D | 01 | Approved | CCP-EPC-LTR-PGU-0015 | R | 01 | 2023-06-23 | 2023-06-23 | 2023-07-12 | CCP-EPC-LTR-PGU-0058 | Approved With Comment | CCP-EPC-TRM-PGU-0010 CCP-DE-LTR-PGU-0290 | D | 01 | 2023-09-12 2024-02-06 | 2023-09-12 2024-02-06 | 2023-10-06 2024-05-27 | CCP-PGU-TRM-EPC-0010 CCP-PGU-LTR-DE-0457 | Approved With Comment Approved | [80 empty] | http://dids.doosanenerbility.com/DIDS/?StartItem=DHI_EDB:05095E5ADD8A43A8A7B223F749FBCC07