## 1. Offshore (Engineering)
No- | DocumentNumber | [6 empty] | TITLE | Purpose (FI/FA) | Ukudu L4 Schedule |  | Team | 담당자 | Information | [5 empty] | Additional Information |  |  | AS-Built Schedule |  | Remark | Latest Submission | [5 empty] | 1st Submission | [5 empty] | 2nd Submission | [5 empty] | 3rd submission | [5 empty] | 4th submission | [5 empty] | 5th submission | [5 empty] | 6th submission | [5 empty] | 7th submission | [5 empty] | 8th submission | [5 empty] | 9th submission | [5 empty] | 10th submission | [5 empty] | 11th submission | [5 empty] | 12th submission | [5 empty] | 13th submission | [5 empty] | 14th submission | [5 empty] | 15th submission
| Project Code | UAS Code | Plant Code | KKS Code | Serial Number | Detail No. (Optional) | Total
[10 empty] | First Issue | FC Issue |  |  | Building Permit (B) | PE Stamp (P :Stamp, R :Only Review) | GPA Review (G) | GPA Review Type (FA/FI) | Package Name | Site Area (CCPP, DG, Fuel) | System | Discipline | Submission Class | Plan | Actual |  | DT Number | Issued date | Revision | CRS Number | Reply Date | Status | DT Number | Issued date | Revision | CRS Number | Reply Date | Status | DT Number | Issued date | Revision | CRS Number | Reply Date | Status | DT Number | Issued date | Revision | CRS Number | Reply Date | Status | DT Number | Issued date | Revision | CRS Number | Reply Date | Status | DT Number | Issued date | Revision | CRS Number | Reply Date | Status | DT Number | Issued date | Revision | CRS Number | Reply Date | Status | DT Number | Issued date | Revision | CRS Number | Reply Date | Status | DT Number | Issued date | Revision | CRS Number | Reply Date | Status | DT Number | Issued date | Revision | CRS Number | Reply Date | Status | DT Number | Issued date | Revision | CRS Number | Reply Date | Status | DT Number | Issued date | Revision | CRS Number | Reply Date | Status | DT Number | Issued date | Revision | CRS Number | Reply Date | Status | DT Number | Issued date | Revision | CRS Number | Reply Date | Status | DT Number | Issued date | Revision | CRS Number | Reply Date | Status | DT Number | Issued date | Revision | CRS Number | Reply Date | Status
[7 empty] | Doc No. | TITLE | Purpose | First | FC | Team | 담당자 | B | P | G | GRT | PN | SA | System | Discipline | Sub class | Plan | Actual | Remark | DT Number | Issued date | Revision | CRS Number | Reply Date | Status
| GUP | XG05 | P1 | ZEN | 110001 |  | GUP-XG05-P1ZEN-110001 | HEAT & MASS BALANCE DIAGRAM | FA | 2021-04-05 | 2022-07-29 | Power EPC프로세스기술팀(Mech.) | 박성용 | [5 empty] | CCPP | Plant | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-22-760 | 2022-10-05 | 0 | CRS-GUP-DHI-DT-22-1130 | 2022-11-23 | AA | DHI-GUP-DT-21-001 | 2021-04-15 | 0 | CRS-GUP-DHI-DT-21-017 | 2021-09-29 | NC | DHI-GUP-DT-21-144 | 2021-12-03 | B | CRS-GUP-DHI-DT-21-104 | 2021-12-27 | RC | DHI-GUP-DT-22-067 | 2022-02-14 | C | CRS-GUP-DHI-DT-22-241 | 2022-03-07 | RC | DE-GUP-DT-E-22-550 | 2022-08-24 | D | CRS-GUP-DHI-DT-22-748 | 2022-09-12 | AA | DE-GUP-DT-E-22-760 | 2022-10-05 | 0 | CRS-GUP-DHI-DT-22-1130 | 2022-11-23 | AA
| GUP | XS03 | P1 | ZEN | 110002 |  | GUP-XS03-P1ZEN-110002 | PLANT OPERATION PHILOSOPHY | FA | 2022-08-02 | 2023-03-30 | Power EPC프로세스기술팀(Mech.) | 김광희 | [5 empty] | CCPP | Plant | General | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-22-1246 | 2023-01-10 | 0 | CRS-GUP-DHI-DT-23-1517 | 2023-02-14 | AA | DE-GUP-DT-E-22-504 | 2022-08-16 | A | CRS-GUP-DHI-DT-22-712 | 2022-09-05 | RC | DE-GUP-DT-E-22-894 | 2022-11-01 | B | CRS-GUP-DHI-DT-22-1325 | 2022-12-28 | AA | DE-GUP-DT-E-22-1246 | 2023-01-10 | 0 | CRS-GUP-DHI-DT-23-1517 | 2023-02-14 | AA
| GUP | XW01 | P1 | ZEN | 110003 |  | GUP-XW01-P1ZEN-110003 | HAZOP STUDY REPORT | FI | 2022-09-08 |  | Power EPC프로세스기술팀(Mech.) | 김광희 | [5 empty] | CCPP | Plant | General | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-22-1121 | 2022-12-19 | 1 | CRS-GUP-DHI-DT-22-1405 | 2023-01-07 | NC | DE-GUP-DT-E-22-947 | 2022-11-16 | A | CRS-GUP-DHI-DT-22-1160 | 2022-11-24 | RC | DE-GUP-DT-E-22-1006 | 2022-11-29 | 0 | CRS-GUP-DHI-DT-22-1233 | 2022-12-13 | RC | DE-GUP-DT-E-22-1121 | 2022-12-19 | 1 | CRS-GUP-DHI-DT-22-1405 | 2023-01-07 | NC
| GUP | CN00 | P1 | ZEN | 110007 |  | GUP-CN00-P1ZEN-110007 | HAZOP STUDY PROCEDURE | FI | 2022-09-05 |  | Power EPC프로세스기술팀(Mech.) | 김광희 | [5 empty] | CCPP | Plant | General | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-22-616 | 2022-09-05 | 0 | CRS-GUP-DHI-DT-22-802 | 2022-09-19 | NC | DE-GUP-DT-E-22-616 | 2022-09-05 | 0 | CRS-GUP-DHI-DT-22-802 | 2022-09-19 | NC
| GUP | XW01 | P1 | ZEN | 110008 |  | GUP-XW01-P1ZEN-110008 | HAZARDOUS AREA CLASSIFICATION | FA | 2022-10-21 | 2023-03-10 | Power EPC프로세스기술팀(Mech.) | 김광희 | [5 empty] | CCPP | Plant | General | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-175 | 2023-02-14 | 0 | CRS-GUP-DHI-DT-23-1482 | 2023-02-11 | AA | DE-GUP-DT-E-22-844 | 2022-10-24 | A | CRS-GUP-DHI-DT-22-1051 | 2022-11-17 | RC | DE-GUP-DT-E-22-1046 | 2022-12-08 | B | CRS-GUP-DHI-DT-22-1288 | 2022-12-21 | RC | DE-GUP-DT-E-22-1158 | 2022-12-22 | C | CRS-GUP-DHI-DT-23-1482 | 2023-02-11 | AA | DE-GUP-DT-E-23-175 | 2023-02-14 | 0
| GUP | CN00 | P1 | ZEN | 110004 |  | GUP-CN00-P1ZEN-110004 | STARTUP & SHUTDOWN PROCEDURE | FA | 2023-07-10 | 2024-01-12 | Power EPC프로세스기술팀(Mech.) | 김광희 | [5 empty] | CCPP | Plant | General | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-046 | 2024-02-16 | 0 | CRS-GUP-DHI-DT-24-003 | 2024-01-23 | AA | DE-GUP-DT-E-23-659 | 2023-07-03 | A | CRS-GUP-DHI-DT-23-2086 | 2023-08-08 | RC | DE-GUP-DT-E-23-786 | 2023-09-04 | B | CRS-GUP-DHI-DT-23-2115 | 2023-09-27 | RC | DE-GUP-DT-E-23-988 | 2023-12-13 | C | CRS-GUP-DHI-DT-24-003 | 2024-01-23 | AA | DE-GUP-DT-E-24-046 | 2024-02-16 | 0
| GUP | CN00 | P1 | ZEN | 110005 |  | GUP-CN00-P1ZEN-110005 | STEAM BLOWING OUT PROCEDURE | FA | 2023-05-02 | 2024-02-23 | Power EPC프로세스기술팀(Mech.) | 김광희 | [5 empty] | CCPP | Plant | General | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-298 | 2024-12-23 | 1 | 자체 CRS 개정 후 제출 | 2024-12-22 | N/A | DE-GUP-DT-E-23-694 | 2023-07-18 | A | CRS-GUP-DHI-DT-23-2131 | 2023-11-01 | RC | DE-GUP-DT-E-23-989 | 2023-12-13 | B | CRS-GUP-DHI-DT-24-034 | 2024-03-12 | RC | DE-GUP-DT-E-24-151 | 2024-06-11 | C | CRS-GUP-DHI-DT-24-068 | 2024-08-16 | AA | DE-GUP-DT-E-24-204 | 2024-08-20 | 0 | 자체 CRS 개정 후 제출 | 2024-12-22 | N/A | DE-GUP-DT-E-24-298 | 2024-12-23 | 1
| GUP | XG02 | P1 | ZEN | 110201 |  | GUP-XG02-P1ZEN-110201 | SYMBOL & LEGEND_P&I DIAGRAM | FA | 2021-06-02 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김광희 | [5 empty] | CCPP | Plant | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-889 | 2023-11-09 | 2 | N/A(9/27 메일로 송부) | 2022-09-27 | AA | DHI-GUP-DT-21-003 | 2021-05-28 | A | CRS-GUP-DHI-DT-21-034 | 2021-10-06 | RC | DHI-GUP-DT-21-122 | 2021-11-26 | B | CRS-GUP-DHI-DT-21-126 | 2022-01-11 | AA | DHI-GUP-DT-22-160 | 2022-04-11 | 0 | CRS-GUP-DHI-DT-22-321 | 2022-05-02 | AC | DE-GUP-DT-E-22-344 | 2022-06-29 | 1(CP) | N/A(9/27 메일로 송부) | 2022-09-27 | AA | DE-GUP-DT-E-23-889 | 2023-11-09 | 2
| GUP | XW01 | P1 | ZEN | 110006 |  | GUP-XW01-P1ZEN-110006 | MECHANICAL DESIGN CRITERIA | FA | 2021-10-08 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김광희 |  | P |  |  |  | CCPP | Plant | General | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-22-1218 | 2023-01-04 | 2 | CRS-GUP-DHI-DT-23-1512 | 2023-02-14 | AA | DHI-GUP-DT-21-060 | 2021-10-08 | A | CRS-GUP-DHI-DT-21-044 | 2021-10-29 | RC | DHI-GUP-DT-21-171 | 2021-12-14 | B | CRS-GUP-DHI-DT-21-123 | 2022-01-07 | RC | DHI-GUP-DT-22-036 | 2022-01-26 | C | CRS-GUP-DHI-DT-21-188 | 2022-02-04 | AA | DHI-GUP-DT-22-160 | 2022-04-11 | 0 | CRS-GUP-DHI-DT-22-321 | 2022-05-02 | AC | DE-GUP-DT-E-22-344 | 2022-06-29 | 1(CP) | N/A(9/27 메일로 송부) | 2022-09-27 | AA | DE-GUP-DT-E-22-1218 | 2023-01-04 | 2 | CRS-GUP-DHI-DT-23-1512 | 2023-02-14 | AA
| GUP | XW01 | P1 | PGB | 115101 |  | GUP-XW01-P1PGB-115101 | CLOSED COOLING WATER SYSTEM_DESIGN CRITERIA | FA | 2021-07-23 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김광희 |  | P |  |  |  | CCPP | Closed Cooling Water | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-946 | 2023-11-24 | 2 | 자체 CRS 개정 후 제출 | 2023-11-23 | N/A | DHI-GUP-DT-21-007 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-011 | 2021-09-28 | RC | DHI-GUP-DT-21-120 | 2021-11-26 | B | CRS-GUP-DHI-DT-21-092 | 2021-12-23 | AA | DHI-GUP-DT-22-167 | 2022-04-12 | 0 | CRS-GUP-DHI-DT-22-356 | 2022-05-22 | AA | DE-GUP-DT-E-22-454 | 2022-07-26 | 1(CP) | 자체 CRS 개정 후 제출 | 2023-11-23 | N/A | DE-GUP-DT-E-23-946 | 2023-11-24 | 2
| GUP | XG02 | P1 | PGB | 115201 |  | GUP-XG02-P1PGB-115201 | CLOSED COOLING WATER SYSTEM_P&I DIAGRAM | FA | 2021-06-02 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김광희 | [5 empty] | CCPP | Closed Cooling Water | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-947 | 2023-11-24 | 2 | 자체 CRS 개정 후 제출 | 2023-11-23 | N/A | DHI-GUP-DT-21-003 | 2021-05-28 | A | CRS-GUP-DHI-DT-21-034 | 2021-10-06 | RC | DHI-GUP-DT-21-120 | 2021-11-26 | B | CRS-GUP-DHI-DT-21-092 | 2021-12-23 | AC | DHI-GUP-DT-22-167 | 2022-04-12 | 0 | CRS-GUP-DHI-DT-22-356 | 2022-05-22 | RC | DE-GUP-DT-E-22-454 | 2022-07-26 | 1 | 자체 CRS 개정 후 제출 | 2023-11-23 | N/A | DE-GUP-DT-E-23-947 | 2023-11-24 | 2
| GUP | XG08 | P1 | PGB | 115202 |  | GUP-XG08-P1PGB-115202 | CLOSED COOLING WATER SYSTEM_PROCESS FLOW DIAGRAM | FA | 2021-09-29 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김광희 |  | P |  |  |  | CCPP | Closed Cooling Water | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-947 | 2023-11-24 | 2 | 자체 CRS 개정 후 제출 | 2023-11-23 | N/A | DHI-GUP-DT-21-041 | 2021-09-29 | A | CRS-GUP-DHI-DT-21-064 | 2021-11-17 | RC | DHI-GUP-DT-21-120 | 2021-11-26 | B | CRS-GUP-DHI-DT-21-092 | 2021-12-23 | AC | DHI-GUP-DT-22-167 | 2022-04-12 | 0 | CRS-GUP-DHI-DT-22-356 | 2022-05-22 | RC | DE-GUP-DT-E-22-454 | 2022-07-26 | 1 | 자체 CRS 개정 후 제출 | 2023-11-23 | N/A | DE-GUP-DT-E-23-947 | 2023-11-24 | 2
| GUP | XS00 | P1 | PGB | 115301 |  | GUP-XS00-P1PGB-115301 | CLOSED COOLING WATER SYSTEM_SYSTEM DESCRIPTION | FA | 2021-07-23 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김광희 |  | P |  |  |  | CCPP | Closed Cooling Water | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-946 | 2023-11-24 | 2 | 자체 CRS 개정 후 제출 | 2023-11-23 | N/A | DHI-GUP-DT-21-008 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-011 | 2021-09-28 | RC | DHI-GUP-DT-21-120 | 2021-11-26 | B | CRS-GUP-DHI-DT-21-092 | 2021-12-23 | AA | DHI-GUP-DT-22-167 | 2022-04-12 | 0 | CRS-GUP-DHI-DT-22-356 | 2022-05-22 | AA | DE-GUP-DT-E-22-454 | 2022-07-26 | 1(CP) | 자체 CRS 개정 후 제출 | 2023-11-23 | N/A | DE-GUP-DT-E-23-946 | 2023-11-24 | 2
| GUP | XW01 | P1 | LA | 112101 |  | GUP-XW01-P1LA-112101 | FEEDWATER SYSTEM_DESIGN CRITERIA | FA | 2021-07-23 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김석희 |  | P |  |  |  | CCPP | Feedwater | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-943 | 2023-11-23 | 2 | 자체 CRS 개정 후 제출 | 2023-11-22 | N/A | DHI-GUP-DT-21-007 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-012 | 2021-09-28 | RC | DHI-GUP-DT-21-126 | 2021-11-29 | B | CRS-GUP-DHI-DT-21-128 | 2022-01-11 | AA | DHI-GUP-DT-22-170 | 2022-04-13 | 0 | CRS-GUP-DHI-DT-22-324 | 2022-05-02 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-634 | 2022-09-07 | 1(CP) | 자체 CRS 개정 후 제출 | 2023-11-22 | N/A | DE-GUP-DT-E-23-943 | 2023-11-23 | 2
| GUP | XG02 | P1 | LA | 112201 |  | GUP-XG02-P1LA-112201 | FEEDWATER SYSTEM_P&I DIAGRAM | FA | 2021-06-02 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김석희 | [5 empty] | CCPP | Feedwater | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-995 | 2023-12-15 | 2 | N/A(메일로 송부) | 2023-12-14 | AA | DHI-GUP-DT-21-003 | 2021-05-28 | A | CRS-GUP-DHI-DT-21-021 | 2021-10-04 | AC | DHI-GUP-DT-21-126 | 2021-11-29 | B | CRS-GUP-DHI-DT-21-128 | 2022-01-11 | AC | DHI-GUP-DT-22-170 | 2022-04-13 | 0 | CRS-GUP-DHI-DT-22-324 | 2022-05-02 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-634 | 2022-09-07 | 1(CP) | 자체 CRS 개정 후 제출 | 2023-11-22 | N/A | DE-GUP-DT-E-23-943 | 2023-11-23 | 2 | N/A(메일로 송부) | 2023-12-14 | AA | DE-GUP-DT-E-23-995 | 2023-12-15 | 2
| GUP | XG08 | P1 | LA | 112202 |  | GUP-XG08-P1LA-112202 | FEEDWATER SYSTEM_PROCESS FLOW DIAGRAM | FA | 2021-10-06 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김석희 |  | P |  |  |  | CCPP | Feedwater | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-943 | 2023-11-23 | 2 | 자체 CRS 개정 후 제출 | 2023-11-22 | N/A | DHI-GUP-DT-21-053 | 2021-10-07 | A | CRS-GUP-DHI-DT-21-044 | 2021-10-29 | RC | DHI-GUP-DT-21-126 | 2021-11-29 | B | CRS-GUP-DHI-DT-21-128 | 2022-01-11 | AA | DHI-GUP-DT-22-170 | 2022-04-13 | 0 | CRS-GUP-DHI-DT-22-324 | 2022-05-02 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-634 | 2022-09-07 | 1(CP) | 자체 CRS 개정 후 제출 | 2023-11-22 | N/A | DE-GUP-DT-E-23-943 | 2023-11-23 | 2
| GUP | XS00 | P1 | LA | 112301 |  | GUP-XS00-P1LA-112301 | FEEDWATER SYSTEM_SYSTEM DESCRIPTION | FA | 2021-07-23 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김석희 |  | P |  |  |  | CCPP | Feedwater | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-943 | 2023-11-23 | 2 | 자체 CRS 개정 후 제출 | 2023-11-22 | N/A | DHI-GUP-DT-21-008 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-012 | 2021-09-28 | RC | DHI-GUP-DT-21-126 | 2021-11-29 | B | CRS-GUP-DHI-DT-21-128 | 2022-01-11 | AA | DHI-GUP-DT-22-170 | 2022-04-13 | 0 | CRS-GUP-DHI-DT-22-324 | 2022-05-02 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-634 | 2022-09-07 | 1(CP) | 자체 CRS 개정 후 제출 | 2023-11-22 | N/A | DE-GUP-DT-E-23-943 | 2023-11-23 | 2
| GUP | XG02 | P1 | LA | 112203 |  | GUP-XG02-P1LA-112203 | GT AIR PERFORMANCE HEATER SYSTEM_P&I DIAGRAM | FA | 2021-07-23 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김석희 | [5 empty] | CCPP | Feedwater | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-995 | 2023-12-15 | 2 | N/A(메일로 송부) | 2023-12-14 | AA | DHI-GUP-DT-21-003 | 2021-05-28 | A | CRS-GUP-DHI-DT-21-034 | 2021-10-04 | AC | DHI-GUP-DT-21-126 | 2021-11-29 | B | CRS-GUP-DHI-DT-21-128 | 2022-01-11 | AC | DHI-GUP-DT-22-170 | 2022-04-13 | 0 | CRS-GUP-DHI-DT-22-324 | 2022-05-02 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-634 | 2022-09-07 | 1(CP) | N/A(메일로 송부) | 2023-12-14 | AA | DE-GUP-DT-E-23-995 | 2023-12-15 | 2
| GUP | XG02 | P1 | QJA | 117201 |  | GUP-XG02-P1QJA-117201 | N2 GAS SYSTEM_P&I DIAGRAM | FA | 2021-06-02 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김광희 | [5 empty] | CCPP | N2 Gas | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-299 | 2024-12-23 | 3 | 자체 CRS 개정 후 제출 | 2024-12-22 | N/A | DHI-GUP-DT-21-003 | 2021-05-28 | A | CRS-GUP-DHI-DT-21-034 | 2021-10-06 | RC | DHI-GUP-DT-21-177 | 2021-12-16 | B | CRS-GUP-DHI-DT-21-122 | 2022-01-07 | AC | DE-GUP-DT-E-22-230 | 2022-05-19 | 0 | CRS-GUP-DHI-DT-22-376 | 2022-05-30 | AC | DE-GUP-DT-E-22-910 | 2022-11-04 | 1(CP) | CRS-GUP-DHI-DT-22-1151 | 2022-11-23 | AA | DE-GUP-DT-E-23-991 | 2023-12-14 | 2 | 자체 CRS 개정 후 제출 | 2024-12-22 | N/A | DE-GUP-DT-E-24-299 | 2024-12-23 | 3
| GUP | XG08 | P1 | QJA | 117202 |  | GUP-XG08-P1QJA-117202 | N2 GAS SYSTEM_PROCESS FLOW DIAGRAM | FA | 2021-10-06 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김광희 |  | P |  |  |  | CCPP | N2 Gas | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-956 | 2023-11-30 | 2 | CRS-GUP-DHI-DT-22-1151 | 2022-11-23 | AA | DHI-GUP-DT-21-054 | 2021-10-07 | A | CRS-GUP-DHI-DT-21-044 | 2021-10-29 | RC | DHI-GUP-DT-21-177 | 2021-12-16 | B | CRS-GUP-DHI-DT-21-122 | 2022-01-07 | AA | DE-GUP-DT-E-22-230 | 2022-05-19 | 0 | CRS-GUP-DHI-DT-22-376 | 2022-05-30 | AC | DE-GUP-DT-E-22-910 | 2022-11-04 | 1(CP) | CRS-GUP-DHI-DT-22-1151 | 2022-11-23 | AA | DE-GUP-DT-E-23-956 | 2023-11-30 | 2
| GUP | XW01 | P1 | QJA | 111102 |  | GUP-XW01-P1QJA-111102 | N2 GAS SYSTEM_DESIGN CRITERIA | FA | 2021-12-20 | 2022-04-20 | Power EPC프로세스기술팀(Mech.) | 김광희 |  | P |  |  |  | CCPP | N2 Gas | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-956 | 2023-11-30 | 2 | CRS-GUP-DHI-DT-22-1151 | 2022-11-23 | AA | DHI-GUP-DT-21-177 | 2022-02-11 | A | CRS-GUP-DHI-DT-21-122 | 2022-01-07 | AA | DE-GUP-DT-E-22-230 | 2022-05-19 | 0 | CRS-GUP-DHI-DT-22-376 | 2022-05-30 | AC | DE-GUP-DT-E-22-910 | 2022-11-04 | 1(CP) | CRS-GUP-DHI-DT-22-1151 | 2022-11-23 | AA | DE-GUP-DT-E-23-956 | 2023-11-30 | 2
| GUP | XW01 | P1 | LB | 111101 |  | GUP-XW01-P1LB-111101 | MAIN AND REHEAT STEAM SYSTEM_DESIGN CRITERIA | FA | 2021-07-23 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김광희 |  | P |  |  |  | CCPP | Steam | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-955 | 2023-11-30 | 2 | 자체 CRS 개정 후 제출 | 2023-11-29 | N/A | DHI-GUP-DT-21-007 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-013 | 2021-09-29 | RC | DHI-GUP-DT-21-166 | 2021-12-10 | B | CRS-GUP-DHI-DT-21-125 | 2022-01-07 | AA | DHI-GUP-DT-22-171 | 2022-04-13 | 0 | CRS-GUP-DHI-DT-22-325 | 2022-05-02 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-660 | 2022-09-14 | 1(CP) | 자체 CRS 개정 후 제출 | 2023-11-29 | N/A | DE-GUP-DT-E-23-955 | 2023-11-30 | 2
| GUP | XG02 | P1 | LBA | 111201 |  | GUP-XG02-P1LBA-111201 | HP STEAM SYSTEM_P&I DIAGRAM | FA | 2021-06-02 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김광희 | [5 empty] | CCPP | Steam | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-990 | 2023-12-14 | 2 | N/A(메일로 송부) | 2023-12-13 | AA | DHI-GUP-DT-21-003 | 2021-05-28 | A | CRS-GUP-DHI-DT-21-034 | 2021-10-06 | RC | DHI-GUP-DT-21-166 | 2021-12-10 | B | CRS-GUP-DHI-DT-21-125 | 2022-01-07 | AC | DHI-GUP-DT-22-171 | 2022-04-13 | 0 | CRS-GUP-DHI-DT-22-325 | 2022-05-02 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-660 | 2022-09-14 | 1(CP) | N/A(메일로 송부) | 2023-12-13 | AA | DE-GUP-DT-E-23-990 | 2023-12-14 | 2
| GUP | XG02 | P1 | LBC | 111211 |  | GUP-XG02-P1LBC-111211 | COLD REHEAT STEAM SYSTEM_P&I DIAGRAM | FA | 2021-06-02 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김광희 | [5 empty] | CCPP | Steam | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-990 | 2023-12-14 | 2 | N/A(메일로 송부) | 2023-12-13 | AA | DHI-GUP-DT-21-003 | 2021-05-28 | A | CRS-GUP-DHI-DT-21-034 | 2021-10-06 | RC | DHI-GUP-DT-21-166 | 2021-12-10 | B | CRS-GUP-DHI-DT-21-125 | 2022-01-07 | AC | DHI-GUP-DT-22-171 | 2022-04-13 | 0 | CRS-GUP-DHI-DT-22-325 | 2022-05-02 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-660 | 2022-09-14 | 1(CP) | N/A(메일로 송부) | 2023-12-13 | AA | DE-GUP-DT-E-23-990 | 2023-12-14 | 2
| GUP | XG02 | P1 | LBB | 111221 |  | GUP-XG02-P1LBB-111221 | HOT REHEAT STEAM SYSTEM_P&I DIAGRAM | FA | 2021-06-02 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김광희 | [5 empty] | CCPP | Steam | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-990 | 2023-12-14 | 2 | N/A(메일로 송부) | 2023-12-13 | AA | DHI-GUP-DT-21-003 | 2021-05-28 | A | CRS-GUP-DHI-DT-21-034 | 2021-10-06 | RC | DHI-GUP-DT-21-166 | 2021-12-10 | B | CRS-GUP-DHI-DT-21-125 | 2022-01-07 | AC | DHI-GUP-DT-22-171 | 2022-04-13 | 0 | CRS-GUP-DHI-DT-22-325 | 2022-05-02 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-660 | 2022-09-14 | 1(CP) | N/A(메일로 송부) | 2023-12-13 | AA | DE-GUP-DT-E-23-990 | 2023-12-14 | 2
| GUP | XG02 | P1 | LBA | 111231 |  | GUP-XG02-P1LBA-111231 | LP STEAM SYSTEM_P&I DIAGRAM | FA | 2021-06-02 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김광희 | [5 empty] | CCPP | Steam | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-990 | 2023-12-14 | 2 | N/A(메일로 송부) | 2023-12-13 | AA | DHI-GUP-DT-21-003 | 2021-05-28 | A | CRS-GUP-DHI-DT-21-034 | 2021-10-06 | RC | DHI-GUP-DT-21-166 | 2021-12-10 | B | CRS-GUP-DHI-DT-21-125 | 2022-01-07 | AC | DHI-GUP-DT-22-171 | 2022-04-13 | 0 | CRS-GUP-DHI-DT-22-325 | 2022-05-02 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-660 | 2022-09-14 | 1(CP) | N/A(메일로 송부) | 2023-12-13 | AA | DE-GUP-DT-E-23-990 | 2023-12-14 | 2
| GUP | XG08 | P1 | LB | 111202 |  | GUP-XG08-P1LB-111202 | MAIN STEAM SYSTEM_PROCESS FLOW DIAGRAM | FA | 2021-10-06 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김광희 |  | P |  |  |  | CCPP | Steam | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-955 | 2023-11-30 | 2 | 자체 CRS 개정 후 제출 | 2023-11-29 | N/A | DHI-GUP-DT-21-054 | 2021-10-07 | A | CRS-GUP-DHI-DT-21-044 | 2021-10-29 | RC | DHI-GUP-DT-21-166 | 2021-12-10 | B | CRS-GUP-DHI-DT-21-125 | 2022-01-07 | AA | DHI-GUP-DT-22-171 | 2022-04-13 | 0 | CRS-GUP-DHI-DT-22-325 | 2022-05-02 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-660 | 2022-09-14 | 1(CP) | 자체 CRS 개정 후 제출 | 2023-11-29 | N/A | DE-GUP-DT-E-23-955 | 2023-11-30 | 2
| GUP | XS00 | P1 | LB | 111301 |  | GUP-XS00-P1LB-111301 | MAIN AND REHEAT STEAM SYSTEM_SYSTEM DESCRIPTION | FA | 2021-07-23 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김광희 |  | P |  |  |  | CCPP | Steam | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-955 | 2023-11-30 | 2 | 자체 CRS 개정 후 제출 | 2023-11-29 | N/A | DHI-GUP-DT-21-008 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-013 | 2021-09-29 | RC | DHI-GUP-DT-21-166 | 2021-12-10 | B | CRS-GUP-DHI-DT-21-125 | 2022-01-07 | AC | DHI-GUP-DT-22-171 | 2022-04-13 | 0 | CRS-GUP-DHI-DT-22-325 | 2022-05-02 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-660 | 2022-09-14 | 1(CP) | 자체 CRS 개정 후 제출 | 2023-11-29 | N/A | DE-GUP-DT-E-23-955 | 2023-11-30 | 2
| GUP | XW03 | P1 | LB | 111001 |  | GUP-XW03-P1LB-111001 | MAIN AND REHEAT STEAM SYSTEM_DESIGN CALCULATION | FA | 2021-09-09 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김광희 |  | P |  |  |  | CCPP | Steam | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-955 | 2023-11-30 | 2 | 자체 CRS 개정 후 제출 | 2023-11-29 | N/A | DHI-GUP-DT-21-020 | 2021-09-09 | A | CRS-GUP-DHI-DT-21-013 | 2021-09-29 | RC | DHI-GUP-DT-21-166 | 2021-12-10 | B | CRS-GUP-DHI-DT-21-125 | 2022-01-07 | AA | DHI-GUP-DT-22-171 | 2022-04-13 | 0 | CRS-GUP-DHI-DT-22-325 | 2022-05-02 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-660 | 2022-09-14 | 1(CP) | 자체 CRS 개정 후 제출 | 2023-11-29 | N/A | DE-GUP-DT-E-23-955 | 2023-11-30 | 2
| GUP | XW01 | P1 | GHC | 116101 |  | GUP-XW01-P1GHC-116101 | DEMI WATER SYSTEM_DESIGN CRITERIA | FA | 2021-07-23 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 강석채 |  | P |  |  |  | CCPP | Demi Water | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-937 | 2023-11-23 | 2 | CRS-GUP-DHI-DT-22-1127 | 2022-11-23 | AA | DHI-GUP-DT-21-007 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-014 | 2021-09-29 | RC | DHI-GUP-DT-21-117 | 2021-11-26 | B | CRS-GUP-DHI-DT-21-090 | 2021-12-23 | AA | DHI-GUP-DT-22-165 | 2022-04-12 | 0 | CRS-GUP-DHI-DT-22-323 | 2022-05-02 | AC | DE-GUP-DT-E-22-748 | 2022-10-04 | 1(CP) | CRS-GUP-DHI-DT-22-1127 | 2022-11-23 | AA | DE-GUP-DT-E-23-937 | 2023-11-23 | 2
| GUP | XG02 | P1 | GHC | 116201 |  | GUP-XG02-P1GHC-116201 | DEMI WATER SYSTEM_P&I DIAGRAM | FA | 2021-06-02 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 강석채 | [5 empty] | CCPP | Demi Water | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-937 | 2023-11-23 | 2 | CRS-GUP-DHI-DT-22-1127 | 2022-11-23 | AA | DHI-GUP-DT-21-003 | 2021-05-28 | A | CRS-GUP-DHI-DT-21-034 | 2021-10-06 | RC | DHI-GUP-DT-21-117 | 2021-11-26 | B | CRS-GUP-DHI-DT-21-090 | 2021-12-23 | AC | DHI-GUP-DT-22-165 | 2022-04-12 | 0 | CRS-GUP-DHI-DT-22-323 | 2022-05-02 | AC | DE-GUP-DT-E-22-748 | 2022-10-04 | 1(CP) | CRS-GUP-DHI-DT-22-1127 | 2022-11-23 | AA | DE-GUP-DT-E-23-937 | 2023-11-23 | 2
| GUP | XG08 | P1 | GHC | 116202 |  | GUP-XG08-P1GHC-116202 | DEMI WATER SYSTEM_PROCESS FLOW DIAGRAM | FA | 2021-09-29 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 강석채 |  | P |  |  |  | CCPP | Demi Water | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-937 | 2023-11-23 | 2 | CRS-GUP-DHI-DT-22-1127 | 2022-11-23 | AA | DHI-GUP-DT-21-041 | 2021-09-29 | A | CRS-GUP-DHI-DT-21-064 | 2021-11-17 | RC | DHI-GUP-DT-21-117 | 2021-11-26 | B | CRS-GUP-DHI-DT-21-090 | 2021-12-23 | AC | DHI-GUP-DT-22-165 | 2022-04-12 | 0 | CRS-GUP-DHI-DT-22-323 | 2022-05-02 | AC | DE-GUP-DT-E-22-748 | 2022-10-04 | 1(CP) | CRS-GUP-DHI-DT-22-1127 | 2022-11-23 | AA | DE-GUP-DT-E-23-937 | 2023-11-23 | 2
| GUP | XS00 | P1 | GHC | 116301 |  | GUP-XS00-P1GHC-116301 | DEMI WATER SYSTEM_SYSTEM DESCRIPTION | FA | 2021-07-23 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 강석채 |  | P |  |  |  | CCPP | Demi Water | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-937 | 2023-11-23 | 2 | CRS-GUP-DHI-DT-22-1127 | 2022-11-23 | AA | DHI-GUP-DT-21-008 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-014 | 2021-09-29 | RC | DHI-GUP-DT-21-117 | 2021-11-26 | B | CRS-GUP-DHI-DT-21-090 | 2021-12-23 | AC | DHI-GUP-DT-22-165 | 2022-04-12 | 0 | CRS-GUP-DHI-DT-22-323 | 2022-05-02 | AC | DE-GUP-DT-E-22-748 | 2022-10-04 | 1(CP) | CRS-GUP-DHI-DT-22-1127 | 2022-11-23 | AA | DE-GUP-DT-E-23-937 | 2023-11-23 | 2
| GUP | XW01 | P1 | LC | 113101 |  | GUP-XW01-P1LC-113101 | CONDENSATE SYSTEM_DESIGN CRITERIA | FA | 2021-07-23 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김석희 |  | P |  |  |  | CCPP | Condensate | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-943 | 2023-11-23 | 2 | 자체 CRS 개정 후 제출 | 2023-11-22 | N/A | DHI-GUP-DT-21-007 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-015 | 2021-09-29 | RC | DHI-GUP-DT-21-126 | 2021-11-29 | B | CRS-GUP-DHI-DT-21-128 | 2022-01-11 | AA | DHI-GUP-DT-22-170 | 2022-04-13 | 0 | CRS-GUP-DHI-DT-22-324 | 2022-05-02 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-634 | 2022-09-07 | 1(CP) | 자체 CRS 개정 후 제출 | 2023-11-22 | N/A | DE-GUP-DT-E-23-943 | 2023-11-23 | 2
| GUP | XG02 | P1 | LC | 113201 |  | GUP-XG02-P1LC-113201 | CONDENSATE SYSTEM_P&I DIAGRAM | FA | 2021-06-02 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김석희 | [5 empty] | CCPP | Condensate | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-995 | 2023-12-15 | 2 | N/A(메일로 송부) | 2023-12-14 | AA | DHI-GUP-DT-21-003 | 2021-05-28 | A | CRS-GUP-DHI-DT-21-034 | 2021-10-06 | RC | DHI-GUP-DT-21-126 | 2021-11-29 | B | CRS-GUP-DHI-DT-21-128 | 2022-01-11 | AA | DHI-GUP-DT-22-170 | 2022-04-13 | 0 | CRS-GUP-DHI-DT-22-324 | 2022-05-02 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-634 | 2022-09-07 | 1(CP) | N/A(메일로 송부) | 2023-12-14 | AA | DE-GUP-DT-E-23-995 | 2023-12-15 | 2
| GUP | XG08 | P1 | LC | 113202 |  | GUP-XG08-P1LC-113202 | CONDENSATE SYSTEM_PROCESS FLOW DIAGRAM | FA | 2021-10-06 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김석희 |  | P |  |  |  | CCPP | Condensate | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-943 | 2023-11-23 | 2 | 자체 CRS 개정 후 제출 | 2023-11-22 | N/A | DHI-GUP-DT-21-053 | 2021-10-07 | A | CRS-GUP-DHI-DT-21-044 | 2021-10-29 | RC | DHI-GUP-DT-21-126 | 2021-11-29 | B | CRS-GUP-DHI-DT-21-128 | 2022-01-11 | AC | DHI-GUP-DT-22-170 | 2022-04-13 | 0 | CRS-GUP-DHI-DT-22-324 | 2022-05-02 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-634 | 2022-09-07 | 1(CP) | 자체 CRS 개정 후 제출 | 2023-11-22 | N/A | DE-GUP-DT-E-23-943 | 2023-11-23 | 2
| GUP | XS00 | P1 | LC | 113301 |  | GUP-XS00-P1LC-113301 | CONDENSATE SYSTEM_SYSTEM DESCRIPTION | FA | 2021-07-23 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김석희 |  | P |  |  |  | CCPP | Condensate | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-943 | 2023-11-23 | 2 | 자체 CRS 개정 후 제출 | 2023-11-22 | N/A | DHI-GUP-DT-21-008 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-015 | 2021-09-29 | RC | DHI-GUP-DT-21-126 | 2021-11-29 | B | CRS-GUP-DHI-DT-21-128 | 2022-01-11 | AA | DHI-GUP-DT-22-170 | 2022-04-13 | 0 | CRS-GUP-DHI-DT-22-324 | 2022-05-02 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-634 | 2022-09-07 | 1(CP) | 자체 CRS 개정 후 제출 | 2023-11-22 | N/A | DE-GUP-DT-E-23-943 | 2023-11-23 | 2
| GUP | XW01 | P1 | PAB | 114101 |  | GUP-XW01-P1PAB-114101 | CIRCULATING WATER SYSTEM_DESIGN CRITERIA | FA | 2021-07-23 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김광희 |  | P |  |  |  | CCPP | Circulating Water | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-935 | 2023-11-23 | 2 | CRS-GUP-DHI-DT-22-1119 | 2022-11-23 | AA | DHI-GUP-DT-21-007 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-010 | 2021-09-28 | RC | DHI-GUP-DT-21-122 | 2021-11-26 | B | CRS-GUP-DHI-DT-21-126 | 2022-01-11 | AC | DHI-GUP-DT-22-167 | 2022-04-12 | 0 | CRS-GUP-DHI-DT-22-356 | 2022-05-22 | AA | DE-GUP-DT-E-22-699 | 2022-09-23 | 1(CP) | CRS-GUP-DHI-DT-22-1119 | 2022-11-23 | AA | DE-GUP-DT-E-23-935 | 2023-11-23 | 2
| GUP | XG02 | P1 | PAB | 114201 |  | GUP-XG02-P1PAB-114201 | CIRCULATING WATER SYSTEM_P&I DIAGRAM | FA | 2021-06-02 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  | G | FI |  | CCPP | Circulating Water | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-932 | 2023-11-23 | 2 | CRS-GUP-DHI-DT-22-1119 | 2022-11-23 | AA | DHI-GUP-DT-21-003 | 2021-05-28 | A | CRS-GUP-DHI-DT-21-034 | 2021-10-06 | RC | DHI-GUP-DT-21-122 | 2021-11-26 | B | CRS-GUP-DHI-DT-21-126 | 2022-01-11 | AC | DHI-GUP-DT-22-167 | 2022-04-12 | 0 | CRS-GUP-DHI-DT-22-356 | 2022-05-22 | RC | DE-GUP-DT-E-22-699 | 2022-09-23 | 1(CP) | CRS-GUP-DHI-DT-22-1119 | 2022-11-23 | AA | DE-GUP-DT-E-23-932 | 2023-11-23 | 2
| GUP | XG08 | P1 | PAB | 114202 |  | GUP-XG08-P1PAB-114202 | CIRCULATING WATER SYSTEM_PROCESS FLOW DIAGRAM | FA | 2021-09-29 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김광희 |  | P | G | FI |  | CCPP | Circulating Water | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-939 | 2023-11-23 | 2 | CRS-GUP-DHI-DT-22-1119 | 2022-11-23 | AA | DHI-GUP-DT-21-041 | 2021-09-29 | A | CRS-GUP-DHI-DT-21-064 | 2021-11-17 | RC | DHI-GUP-DT-21-122 | 2021-11-26 | B | CRS-GUP-DHI-DT-21-126 | 2022-01-11 | AC | DHI-GUP-DT-22-167 | 2022-04-12 | 0 | CRS-GUP-DHI-DT-22-356 | 2022-05-22 | RC | DE-GUP-DT-E-22-699 | 2022-09-23 | 1(CP) | CRS-GUP-DHI-DT-22-1119 | 2022-11-23 | AA | DE-GUP-DT-E-23-939 | 2023-11-23 | 2
| GUP | XS00 | P1 | PAB | 114301 |  | GUP-XS00-P1PAB-114301 | CIRCULATING WATER SYSTEM_SYSTEM DESCRIPTION | FA | 2021-07-23 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김광희 |  | P | G | FI |  | CCPP | Circulating Water | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-934 | 2023-11-23 | 2 | CRS-GUP-DHI-DT-22-1119 | 2022-11-23 | AA | DHI-GUP-DT-21-008 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-010 | 2021-09-28 | AC | DHI-GUP-DT-21-122 | 2021-11-26 | B | CRS-GUP-DHI-DT-21-126 | 2022-01-11 | AC | DHI-GUP-DT-22-167 | 2022-04-12 | 0 | CRS-GUP-DHI-DT-22-356 | 2022-05-22 | AA | DE-GUP-DT-E-22-699 | 2022-09-23 | 1(CP) | CRS-GUP-DHI-DT-22-1119 | 2022-11-23 | AA | DE-GUP-DT-E-23-934 | 2023-11-23 | 2
| GUP | BP00 | P1 | PAB | 114901 |  | GUP-BP00-P1PAB-114901 | CIRCULATING WATER SYSTEM_SURGE ANALYSIS REPORT | FI | 2023-01-20 |  | Power EPC프로세스기술팀(Mech.) | 김광희 | [5 empty] | CCPP | Circulating Water | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-209 | 2023-02-20 | 0 | CRS-GUP-DHI-DT-23-1694 | 2023-03-14 | NC | DE-GUP-DT-E-23-209 | 2023-02-20 | 0 | CRS-GUP-DHI-DT-23-1694 | 2023-03-14 | NC
| GUP | XG02 | P1 | LCM | 111241 |  | GUP-XG02-P1LCM-111241 | FLASH TANK DRAIN SYSTEM_P&I DIAGRAM | FA | 2021-06-02 | 2022-02-09 | Power EPC프로세스기술팀(Mech.) | 김광희 | [5 empty] | CCPP | Flash Tank Drain | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-990 | 2023-12-14 | 2 | N/A(메일로 송부) | 2023-12-13 | AA | DHI-GUP-DT-21-003 | 2021-05-28 | A | CRS-GUP-DHI-DT-21-034 | 2021-10-06 | RC | DHI-GUP-DT-21-166 | 2021-12-10 | B | CRS-GUP-DHI-DT-21-125 | 2022-01-07 | AA | DHI-GUP-DT-22-171 | 2022-04-13 | 0 | CRS-GUP-DHI-DT-22-325 | 2022-05-02 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-660 | 2022-09-14 | 1(CP) | N/A(메일로 송부) | 2023-12-13 | AA | DE-GUP-DT-E-23-990 | 2023-12-14 | 2
| GUP | YD00 | P1 | LBG | 127111 |  | GUP-YD00-P1LBG-127111 | SILENCER_OUTLINE DRAWING | FI | 2023-05-01 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  | R |  |  | Silencer | CCPP | Steam | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-429 | 2023-04-06 | 1 | CRS-GUP-DHI-DT-23-1885 | 2023-05-02 | NC | DE-GUP-DT-E-22-1087 | 2022-12-14 | 0 | CRS-GUP-DHI-DT-22-1298 | 2022-12-21 | NC | DE-GUP-DT-E-23-429 | 2023-04-06 | 1 | CRS-GUP-DHI-DT-23-1885 | 2023-05-02 | NC
| GUP | YT01 | P1 | LBG | 127401 |  | GUP-YT01-P1LBG-127401 | SILENCER_DATA SHEET | FI | 2023-05-01 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | Silencer | CCPP | Steam | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-429 | 2023-04-06 | 1 | CRS-GUP-DHI-DT-23-1885 | 2023-05-02 | NC | DE-GUP-DT-E-22-1087 | 2022-12-14 | 0 | CRS-GUP-DHI-DT-22-1298 | 2022-12-21 | NC | DE-GUP-DT-E-23-429 | 2023-04-06 | 1 | CRS-GUP-DHI-DT-23-1885 | 2023-05-02 | NC
| GUP | CQ02 | P1 | LBG | 126006 |  | GUP-CQ02-P1LBG-126006 | SILENCER_OPERATING AND MAINTENANCE MANUAL | FI | 2023-11-30 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | Silencer | CCPP | Steam | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-938 | 2023-11-23 | 0 | CRS-GUP-DHI-DT-24-036 | 2024-03-14 | NC | DE-GUP-DT-E-23-938 | 2023-11-23 | 0 | CRS-GUP-DHI-DT-24-036 | 2024-03-14 | NC
| GUP | YD00 | P1 | LF | 127131 |  | GUP-YD00-P1LF-127131 | SRV_OUTLINE DRAWING | FI | 2023-01-18 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  | R |  |  | SRV | CCPP | Plant | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1060 | 2022-12-09 | 0 | CRS-GUP-DHI-DT-22-1293 | 2022-12-21 | NC | DE-GUP-DT-E-22-1060 | 2022-12-09 | 0 | CRS-GUP-DHI-DT-22-1293 | 2022-12-21 | NC
| GUP | YT01 | P1 | LF | 127411 |  | GUP-YT01-P1LF-127411 | SRV_DATA SHEET | FI | 2023-01-18 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | SRV | CCPP | Plant | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1060 | 2022-12-09 | 0 | CRS-GUP-DHI-DT-22-1293 | 2022-12-21 | NC | DE-GUP-DT-E-22-1060 | 2022-12-09 | 0 | CRS-GUP-DHI-DT-22-1293 | 2022-12-21 | NC
| GUP | CQ02 | P1 | LF | 126007 |  | GUP-CQ02-P1LF-126007 | SRV_OPERATING AND MAINTENANCE MANUAL | FI | 2023-11-30 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | SRV | CCPP | Plant | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-891 | 2023-11-09 | 0 | CRS-GUP-DHI-DT-24-035 | 2024-03-14 | NC | DE-GUP-DT-E-23-891 | 2023-11-09 | 0 | CRS-GUP-DHI-DT-24-035 | 2024-03-14 | NC
| GUP | YT01 | P1 | MAN | 127121 |  | GUP-YT01-P1MAN-127121 | BYPASS & PRDS_DATA SHEET | FA | 2022-10-24 | 2023-01-24 | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | Bypass & PRDS | CCPP | Bypass & PRDS | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-430 | 2023-04-06 | 0 | CRS-GUP-DHI-DT-23-1771 | 2023-03-27 | AA | DE-GUP-DT-E-22-824 | 2022-10-20 | A | CRS-GUP-DHI-DT-22-1102 | 2022-11-21 | RC | DE-GUP-DT-E-22-1212 | 2023-01-03 | B | CRS-GUP-DHI-DT-23-1490 | 2023-02-11 | RC | DE-GUP-DT-E-23-200 | 2023-02-17 | C | CRS-GUP-DHI-DT-23-1771 | 2023-03-27 | AA | DE-GUP-DT-E-23-430 | 2023-04-06 | 0
| GUP | YK08 | P1 | MAN | 127421 |  | GUP-YK08-P1MAN-127421 | BYPASS & PRDS_OUTLINE DRAWING | FI | 2023-01-24 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  | R |  |  | Bypass & PRDS | CCPP | Bypass & PRDS | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-447 | 2023-04-12 | 1 | CRS-GUP-DHI-DT-23-1867 | 2023-04-19 | NC | DE-GUP-DT-E-22-847 | 2022-10-24 | 0 | CRS-GUP-DHI-DT-22-1177 | 2022-11-30 | NC | DE-GUP-DT-E-23-447 | 2023-04-12 | 1 | CRS-GUP-DHI-DT-23-1867 | 2023-04-19 | NC
| GUP | YS18 | P1 | MAN | 127511 |  | GUP-YS18-P1MAN-127511 | BYPASS & PRDS_PNEUMATIC DIAGRAM | FI | 2023-01-24 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | Bypass & PRDS | CCPP | Bypass & PRDS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-958 | 2022-11-18 | 0 | CRS-GUP-DHI-DT-22-1162 | 2022-11-24 | NC | DE-GUP-DT-E-22-958 | 2022-11-18 | 0 | CRS-GUP-DHI-DT-22-1162 | 2022-11-24 | NC
| GUP | YS00 | P1 | MAN | 127611 |  | GUP-YS00-P1MAN-127611 | BYPASS & PRDS_WIRING DIAGRAM | FI | 2023-01-24 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | Bypass & PRDS | CCPP | Bypass & PRDS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1021 | 2022-12-01 | 0 | CRS-GUP-DHI-DT-22-1309 | 2022-12-22 | NC | DE-GUP-DT-E-22-1021 | 2022-12-01 | 0 | CRS-GUP-DHI-DT-22-1309 | 2022-12-22 | NC
| GUP | XL00 | P1 | MAN | 127701 |  | GUP-XL00-P1MAN-127701 | BYPASS & PRDS_SPECIAL TOOL DRAWING | FI | 2023-01-24 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | Bypass & PRDS | CCPP | Bypass & PRDS | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1038 | 2022-12-06 | 0 | CRS-GUP-DHI-DT-22-1311 | 2022-12-22 | NC | DE-GUP-DT-E-22-1038 | 2022-12-06 | 0 | CRS-GUP-DHI-DT-22-1311 | 2022-12-22 | NC
| GUP | CQ02 | P1 | MAN | 126004 |  | GUP-CQ02-P1MAN-126004 | BYPASS & PRDS_OPERATING AND MAINTENANCE MANUAL | FI | 2023-11-30 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | Bypass & PRDS | CCPP | Bypass & PRDS | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-944 | 2023-11-23 | 0 | CRS-GUP-DHI-DT-24-038 | 2024-03-18 | NC | DE-GUP-DT-E-23-944 | 2023-11-23 | 0 | CRS-GUP-DHI-DT-24-038 | 2024-03-18 | NC
| GUP | XS00 | P1 | QJA | 127301 |  | GUP-XS00-P1QJA-127301 | N2 GAS PACKAGE_SYSTEM DESCRIPTION | FA | 2022-12-05 | 2023-03-07 | Power EPC프로세스기술팀(Mech.) | 김광희 |  | R |  |  | N2 Gas | CCPP | N2 Gas | Mech. | 1 | 2025-06-30 |  |  | DE-GUP-DT-E-23-299 | 2023-03-10 | 0 | CRS-GUP-DHI-DT-23-1779 | 2023-03-27 | NC | DE-GUP-DT-E-22-1157 | 2022-12-22 | A | CRS-GUP-DHI-DT-23-1492 | 2023-02-11 | AA | DE-GUP-DT-E-23-299 | 2023-03-10 | 0 | CRS-GUP-DHI-DT-23-1779 | 2023-03-27 | NC
| GUP | XN00 | P1 | QJA | 127101 |  | GUP-XN00-P1QJA-127101 | N2 GAS PACKAGE_VALVE LIST | FI | 2023-03-07 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  | R |  |  | N2 Gas | CCPP | N2 Gas | Piping | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-960 | 2023-11-30 | 1 | CRS-GUP-DHI-DT-23-1630 | 2023-03-02 | NC | DE-GUP-DT-E-23-157 | 2023-02-10 | 0 | CRS-GUP-DHI-DT-23-1630 | 2023-03-02 | NC | DE-GUP-DT-E-23-960 | 2023-11-30 | 1
| GUP | YL00 | P1 | QJA | 127501 |  | GUP-YL00-P1QJA-127501 | N2 GAS PACKAGE_INSTRUMENT LIST | FI | 2023-03-07 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | N2 Gas | CCPP | N2 Gas | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-157 | 2023-02-10 | 0 | CRS-GUP-DHI-DT-23-1630 | 2023-03-02 | NC | DE-GUP-DT-E-23-157 | 2023-02-10 | 0 | CRS-GUP-DHI-DT-23-1630 | 2023-03-02 | NC
| GUP | YK10 | P1 | QJA | 127601 |  | GUP-YK10-P1QJA-127601 | N2 GAS PACKAGE_EQUIPMENT ASSEMBLY AND DETAIL DRAWING | FI | 2023-03-07 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | N2 Gas | CCPP | N2 Gas | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-960 | 2023-11-30 | 1 | CRS-GUP-DHI-DT-23-1630 | 2023-03-02 | NC | DE-GUP-DT-E-23-157 | 2023-02-10 | 0 | CRS-GUP-DHI-DT-23-1630 | 2023-03-02 | NC | DE-GUP-DT-E-23-960 | 2023-11-30 | 1
| GUP | CQ02 | P1 | QJA | 126005 |  | GUP-CQ02-P1QJA-126005 | N2 GAS PACKAGE_OPERATING AND MAINTENANCE MANUAL | FI | 2023-11-30 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | N2 Gas | CCPP | N2 Gas | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-958 | 2023-11-30 | 0 | CRS-GUP-DHI-DT-24-039 | 2024-03-18 | NC | DE-GUP-DT-E-23-958 | 2023-11-30 | 0 | CRS-GUP-DHI-DT-24-039 | 2024-03-18 | NC
| GUP | YD00 | P1 | MJ | 120401 |  | GUP-YD00-P1MJ-120401 | DIESEL GENERATOR_GA DRAWING | FI | 2022-12-07 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | EDG | CCPP | Diesel Generator | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-180 | 2024-07-08 | 3 | 자체 CRS 개정 후 제출 | 2024-07-07 | N/A | DE-GUP-DT-E-23-216 | 2023-02-21 | 0 | CRS-GUP-DHI-DT-23-1697 | 2023-03-14 | NC | DE-GUP-DT-E-23-886 | 2023-11-07 | 1 | 자체 CRS 개정 후 제출 | 2024-01-21 | N/A | DE-GUP-DT-E-24-017 | 2024-01-22 | 2 | 자체 CRS 개정 후 제출 | 2024-07-07 | N/A | DE-GUP-DT-E-24-180 | 2024-07-08 | 3
| GUP | XG01 | P1 | MJ | 120201 |  | GUP-XG01-P1MJ-120201 | DIESEL GENERATOR_P&I DIAGRAM | FA | 2022-09-07 | 2022-12-07 | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | EDG | CCPP | Diesel Generator | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-239 | 2024-09-30 | 3 | 자체 CRS 개정 후 제출 | 2024-09-29 | N/A | DE-GUP-DT-E-22-766 | 2022-10-07 | A | CRS-GUP-DHI-DT-22-1215 | 2022-12-03 | RC | DE-GUP-DT-E-23-423 | 2023-04-05 | B | CRS-GUP-DHI-DT-23-1870 | 2023-04-25 | AA | DE-GUP-DT-E-23-548 | 2023-05-12 | 0 | CRS-GUP-DHI-DT-23-1957 | 2023-05-18 | AA | DE-GUP-DT-E-23-902 | 2023-11-10 | 1 | 자체 CRS 개정 후 제출 | 2024-01-21 | N/A | DE-GUP-DT-E-24-017 | 2024-01-22 | 2 | 자체 CRS 개정 후 제출 | 2024-09-29 | N/A | DE-GUP-DT-E-24-239 | 2024-09-30 | 3
| GUP | YU02 | P1 | MJ | 120301 |  | GUP-YU02-P1MJ-120301 | DIESEL GENERATOR_SINGLE LINE DRAWING | FA | 2022-09-07 | 2022-12-07 | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | EDG | CCPP | Diesel Generator | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-868 | 2023-10-25 | 1 | CRS-GUP-DHI-DT-23-1957 | 2023-05-18 | AA | DE-GUP-DT-E-22-766 | 2022-10-07 | A | CRS-GUP-DHI-DT-22-1215 | 2022-12-03 | RC | DE-GUP-DT-E-23-423 | 2023-04-05 | B | CRS-GUP-DHI-DT-23-1870 | 2023-04-25 | AA | DE-GUP-DT-E-23-548 | 2023-05-12 | 0 | CRS-GUP-DHI-DT-23-1957 | 2023-05-18 | AA | DE-GUP-DT-E-23-868 | 2023-10-25 | 1
| GUP | YT01 | P1 | MJ | 120121 |  | GUP-YT01-P1MJ-120121 | DIESEL GENERATOR_DATA SHEET | FA | 2022-09-07 | 2022-12-07 | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | EDG | CCPP | Diesel Generator | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-051 | 2024-02-21 | 2 | 별도메일접수 25-015 | 2025-05-22 | AA | DE-GUP-DT-E-22-766 | 2022-10-07 | A | CRS-GUP-DHI-DT-22-1215 | 2022-12-03 | RC | DE-GUP-DT-E-23-423 | 2023-04-05 | B | CRS-GUP-DHI-DT-23-1870 | 2023-04-25 | AA | DE-GUP-DT-E-23-548 | 2023-05-12 | 0 | CRS-GUP-DHI-DT-23-1957 | 2023-05-18 | RC | DE-GUP-DT-E-23-903 | 2023-11-10 | 1 | CRS-GUP-DHI-DT-24-004 | 2024-01-23 | RC | DE-GUP-DT-E-24-051 | 2024-02-21 | 2 | 별도메일접수 25-015 | 2025-05-22 | AA
| GUP | YD00 | P1 | MJ | 120421 |  | GUP-YD00-P1MJ-120421 | DIESEL GENERATOR_EQUIPMENT OUTLINE DRAWING | FI | 2022-12-07 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  | R |  |  | EDG | CCPP | Diesel Generator | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-017 | 2024-01-22 | 2 | 자체 CRS 개정 후 제출 | 2024-01-21 | N/A | DE-GUP-DT-E-23-216 | 2023-02-21 | 0 | CRS-GUP-DHI-DT-23-1697 | 2023-03-14 | NC | DE-GUP-DT-E-23-886 | 2023-11-07 | 1 | 자체 CRS 개정 후 제출 | 2024-01-21 | N/A | DE-GUP-DT-E-24-017 | 2024-01-22 | 2
| GUP | YF00 | P1 | MJ | 120321 |  | GUP-YF00-P1MJ-120321 | DIESEL GENERATOR_CONTROL LOGIC DIAGRAM | FA | 2022-12-07 | 2023-03-07 | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | EDG | CCPP | Diesel Generator | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-732 | 2023-08-07 | 0 | CRS-GUP-DHI-DT-23-2076 | 2023-07-27 | AA | DE-GUP-DT-E-23-543 | 2023-05-12 | A | CRS-GUP-DHI-DT-23-1969 | 2023-06-01 | RC | DE-GUP-DT-E-23-707 | 2023-07-21 | B | CRS-GUP-DHI-DT-23-2076 | 2023-07-27 | AA | DE-GUP-DT-E-23-732 | 2023-08-07 | 0
| GUP | YU03 | P1 | MJ | 120341 |  | GUP-YU03-P1MJ-120341 | DIESEL GENERATOR_SCHEMATIC WIRING DRAWING | FI | 2022-12-07 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | EDG | CCPP | Diesel Generator | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-036 | 2024-02-07 | 4 | 자체 CRS 개정 후 제출 | 2024-02-06 | N/A | DE-GUP-DT-E-23-543 | 2023-05-12 | 0 | CRS-GUP-DHI-DT-23-1969 | 2023-06-01 | RC | DE-GUP-DT-E-23-707 | 2023-07-21 | 1 | CRS-GUP-DHI-DT-23-2076 | 2023-07-27 | NC | DE-GUP-DT-E-23-868 | 2023-10-25 | 2 | 자체 CRS 개정 후 제출 | 2024-01-01 | N/A | DE-GUP-DT-E-24-002 | 2024-01-02 | 3 | 자체 CRS 개정 후 제출 | 2024-02-06 | N/A | DE-GUP-DT-E-24-036 | 2024-02-07 | 4
| GUP | YL00 | P1 | MJ | 120441 |  | GUP-YL00-P1MJ-120441 | DIESEL GENERATOR_INSTRUMENT LIST & DATA SHEET | FI | 2022-12-07 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | EDG | CCPP | Diesel Generator | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-498 | 2023-04-24 | 0 | CRS-GUP-DHI-DT-23-1941 | 2023-05-11 | NC | DE-GUP-DT-E-23-498 | 2023-04-24 | 0 | CRS-GUP-DHI-DT-23-1941 | 2023-05-11 | NC
| GUP | XB02 | P1 | MJ | 120231 |  | GUP-XB02-P1MJ-120231 | DIESEL GENERATOR_FOUNDATION DRAWING | FA | 2022-09-07 | 2022-12-07 | Power EPC프로세스기술팀(Mech.) | 김광희 |  | R |  |  | EDG | CCPP | Diesel Generator | Civil | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-324 | 2023-03-17 | 1 | CRS-GUP-DHI-DT-23-1651 | 2023-03-07 | AA | DE-GUP-DT-E-22-766 | 2022-10-07 | A | CRS-GUP-DHI-DT-22-1215 | 2022-12-03 | AC | DE-GUP-DT-E-22-1093 | 2022-12-16 | B | CRS-GUP-DHI-DT-22-1338 | 2022-12-28 | AA | DE-GUP-DT-E-23-001 | 2023-01-11 | 0 | CRS-GUP-DHI-DT-23-1651 | 2023-03-07 | AA | DE-GUP-DT-E-23-324 | 2023-03-17 | 1
| GUP | XS00 | P1 | MJ | 120331 |  | GUP-XS00-P1MJ-120331 | DIESEL GENERATOR_OPERATING DESCRIPTION | FA | 2022-09-07 | 2022-12-07 | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | EDG | CCPP | Diesel Generator | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-423 | 2023-04-05 | 1 | CRS-GUP-DHI-DT-23-1870 | 2023-04-25 | AA | DE-GUP-DT-E-22-766 | 2022-10-07 | A | CRS-GUP-DHI-DT-22-1215 | 2022-12-03 | AA | DE-GUP-DT-E-23-001 | 2023-01-11 | 0 | CRS-GUP-DHI-DT-23-1651 | 2023-03-07 | AA | DE-GUP-DT-E-23-423 | 2023-04-05 | 1 | CRS-GUP-DHI-DT-23-1870 | 2023-04-25 | AA
| GUP | CQ02 | P1 | MJ | 126001 |  | GUP-CQ02-P1MJ-126001 | DIESEL GENERATOR_OPERATING AND MAINTENANCE MANUAL | FI | 2023-11-30 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | EDG | CCPP | Diesel Generator | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-209 | 2024-08-23 | 1 | CRS-GUP-DHI-DT-23-2122 | 2023-10-26 | NC | DE-GUP-DT-E-23-809 | 2023-09-13 | 0 | CRS-GUP-DHI-DT-23-2122 | 2023-10-26 | NC | DE-GUP-DT-E-24-209 | 2024-08-23 | 1
| GUP | YT01 | P1 | ZEN | 126101 |  | GUP-YT01-P1ZEN-126101 | MOV (BUTTERFLY)_DATA SHEET | FI | 2022-11-08 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | MOV | CCPP | Plant | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-422 | 2023-04-05 | 1 | CRS-GUP-DHI-DT-23-1883 | 2023-05-02 | NC | DE-GUP-DT-E-22-1005 | 2022-11-29 | 0 | CRS-GUP-DHI-DT-22-1306 | 2022-12-22 | NC | DE-GUP-DT-E-23-422 | 2023-04-05 | 1 | CRS-GUP-DHI-DT-23-1883 | 2023-05-02 | NC
| GUP | YK10 | P1 | ZEN | 126401 |  | GUP-YK10-P1ZEN-126401 | MOV (BUTTERFLY)_OUTLINE DRAWING | FI | 2022-11-08 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  | R |  |  | MOV | CCPP | Plant | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-047 | 2024-02-16 | 4 | 자체 CRS 개정 후 제출 | 2024-02-15 | N/A | DE-GUP-DT-E-22-1005 | 2022-11-29 | 0 | CRS-GUP-DHI-DT-22-1306 | 2022-12-22 | NC | DE-GUP-DT-E-23-422 | 2023-04-05 | 1 | CRS-GUP-DHI-DT-23-1883 | 2023-05-02 | NC | DE-GUP-DT-E-23-613 | 2023-06-12 | 2 | CRS-GUP-DHI-DT-23-2017 | 2023-06-21 | NC | DE-GUP-DT-E-24-019 | 2024-01-22 | 3 | 자체 CRS 개정 후 제출 | 2024-02-15 | N/A | DE-GUP-DT-E-24-047 | 2024-02-16 | 4
| GUP | CQ02 | P1 | ZEN | 126002 |  | GUP-CQ02-P1ZEN-126002 | MOV (BUTTERFLY)_OPERATING AND MAINTENANCE MANUAL | FI | 2023-11-30 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | MOV | CCPP | Plant | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-804 | 2023-09-11 | 0 | CRS-GUP-DHI-DT-23-2122 | 2023-10-26 | NC | DE-GUP-DT-E-23-804 | 2023-09-11 | 0 | CRS-GUP-DHI-DT-23-2122 | 2023-10-26 | NC
| GUP | YT01 | P1 | ZEN | 126111 |  | GUP-YT01-P1ZEN-126111 | MOV (GATE&GLOBE)_DATA SHEET | FI | 2023-02-08 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | MOV | CCPP | Plant | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-276 | 2024-11-26 | 4 | 자체 CRS 개정 후 제출 | 2024-11-25 | N/A | DE-GUP-DT-E-23-178 | 2023-02-14 | 0 | CRS-GUP-DHI-DT-23-1634 | 2023-03-03 | NC | DE-GUP-DT-E-23-613 | 2023-06-12 | 1 | CRS-GUP-DHI-DT-23-2017 | 2023-06-21 | NC | DE-GUP-DT-E-23-731 | 2023-08-07 | 2 | 자체 CRS 개정 후 제출 | 2024-02-06 | N/A | DE-GUP-DT-E-24-035 | 2024-02-07 | 3 | 자체 CRS 개정 후 제출 | 2024-11-25 | N/A | DE-GUP-DT-E-24-276 | 2024-11-26 | 4
| GUP | YK10 | P1 | ZEN | 126411 |  | GUP-YK10-P1ZEN-126411 | MOV (GATE&GLOBE)_OUTLINE DRAWING | FI | 2023-02-08 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  | R |  |  | MOV | CCPP | Plant | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-276 | 2024-11-26 | 3 | 자체 CRS 개정 후 제출 | 2024-11-25 | N/A | DE-GUP-DT-E-23-178 | 2023-02-14 | 0 | CRS-GUP-DHI-DT-23-1634 | 2023-03-03 | NC | DE-GUP-DT-E-23-613 | 2023-06-12 | 1 | CRS-GUP-DHI-DT-23-2017 | 2023-06-21 | NC | DE-GUP-DT-E-23-731 | 2023-08-07 | 2 | 자체 CRS 개정 후 제출 | 2024-11-25 | N/A | DE-GUP-DT-E-24-276 | 2024-11-26 | 3
| GUP | CQ02 | P1 | ZEN | 126003 |  | GUP-CQ02-P1ZEN-126003 | MOV (GATE&GLOBE)_OPERATING AND MAINTENANCE MANUAL | FI | 2023-11-30 |  | Power EPC프로세스기술팀(Mech.) | 원승환 |  |  |  |  | MOV | CCPP | Plant | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-804 | 2023-09-11 | 0 | CRS-GUP-DHI-DT-23-2122 | 2023-10-26 | NC | DE-GUP-DT-E-23-804 | 2023-09-11 | 0 | CRS-GUP-DHI-DT-23-2122 | 2023-10-26 | NC
| GUP | YT01 | P1 | PGB | 128141 |  | GUP-YT01-P1PGB-128141 | PHE_TECHNICAL DATA SHEET | FI | 2023-01-18 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | PHE | CCPP | Closed Cooling Water | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-876 | 2022-10-28 | 1 | CRS-GUP-DHI-DT-22-1022 | 2022-11-13 | NC | DE-GUP-DT-E-22-454 | 2022-07-26 | 0 | CRS-GUP-DHI-DT-22-676 | 2022-08-22 | NC | DE-GUP-DT-E-22-876 | 2022-10-28 | 1 | CRS-GUP-DHI-DT-22-1022 | 2022-11-13 | NC
| GUP | YD00 | P1 | PGB | 128441 |  | GUP-YD00-P1PGB-128441 | PHE_OUTLINE & FOUNDATION DRAWING | FI | 2023-01-18 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  | R |  |  | PHE | CCPP | Closed Cooling Water | Civil | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-238 | 2024-09-30 | 3 | 자체 CRS 개정 후 제출 | 2024-09-29 | N/A | DE-GUP-DT-E-22-876 | 2022-10-28 | 0 | CRS-GUP-DHI-DT-22-1022 | 2022-11-13 | NC | DE-GUP-DT-E-22-1007 | 2022-11-29 | 1 | CRS-GUP-DHI-DT-22-1280 | 2022-12-21 | NC | DE-GUP-DT-E-23-770 | 2023-08-29 | 2 | 자체 CRS 개정 후 제출 | 2024-09-29 | N/A | DE-GUP-DT-E-24-238 | 2024-09-30 | 3
| GUP | CQ02 | P1 | PGB | 128451 |  | GUP-CQ02-P1PGB-128451 | PHE_INSTALLATION, OPERATION AND MAINTENANCE MANUAL | FI | 2023-11-30 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | PHE | CCPP | Closed Cooling Water | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-805 | 2023-09-11 | 0 | CRS-GUP-DHI-DT-23-2122 | 2023-10-26 | NC | DE-GUP-DT-E-23-805 | 2023-09-11 | 0 | CRS-GUP-DHI-DT-23-2122 | 2023-10-26 | NC
| GUP | XG02 | P1 | PGB | 128231 |  | GUP-XG02-P1PGB-128231 | CCWP_P&I DIAGRAM | FA | 2022-10-19 | 2023-01-18 | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  | G | FI | CCWP | CCPP | Closed Cooling Water | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1138 | 2022-12-20 | 1 | CRS-GUP-DHI-DT-22-1269 | 2022-12-16 | AA | DE-GUP-DT-E-22-628 | 2022-09-07 | A | CRS-GUP-DHI-DT-22-778 | 2022-09-16 | RC | DE-GUP-DT-E-22-776 | 2022-10-11 | B | CRS-GUP-DHI-DT-22-1089 | 2022-11-21 | AA | DE-GUP-DT-E-22-1010 | 2022-11-30 | 0 | CRS-GUP-DHI-DT-22-1269 | 2022-12-16 | AA | DE-GUP-DT-E-22-1138 | 2022-12-20 | 1
| GUP | YD00 | P1 | PGB | 128401 |  | GUP-YD00-P1PGB-128401 | CCWP_PUMP OUTLINE DRAWING | FI | 2023-01-18 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  | R |  |  | CCWP | CCPP | Closed Cooling Water | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-758 | 2023-08-24 | 3 | CRS-GUP-DHI-DT-22-1376 | 2022-12-31 | NC | DE-GUP-DT-E-22-628 | 2022-09-07 | 0 | CRS-GUP-DHI-DT-22-778 | 2022-09-16 | NC | DE-GUP-DT-E-22-959 | 2022-11-18 | 1 | CRS-GUP-DHI-DT-22-1163 | 2022-11-24 | NC | DE-GUP-DT-E-22-1138 | 2022-12-20 | 2 | CRS-GUP-DHI-DT-22-1376 | 2022-12-31 | NC | DE-GUP-DT-E-23-758 | 2023-08-24 | 3
| GUP | YT01 | P1 | PGB | 128151 |  | GUP-YT01-P1PGB-128151 | CCWP_PUMP DATA SHEET & CHARACTERISTIC CURVE | FA | 2022-10-19 | 2023-01-18 | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | CCWP | CCPP | Closed Cooling Water | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-776 | 2022-10-11 | 0 | CRS-GUP-DHI-DT-22-1089 | 2022-11-21 | AA | DE-GUP-DT-E-22-628 | 2022-09-07 | A | CRS-GUP-DHI-DT-22-778 | 2022-09-16 | AA | DE-GUP-DT-E-22-776 | 2022-10-11 | 0 | CRS-GUP-DHI-DT-22-1089 | 2022-11-21 | AA
| GUP | YK09 | P1 | PGB | 128411 |  | GUP-YK09-P1PGB-128411 | CCWP_PUMP SECTIONAL DRAWING | FI | 2023-01-18 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  | R |  |  | CCWP | CCPP | Closed Cooling Water | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-628 | 2022-09-07 | 0 | CRS-GUP-DHI-DT-22-778 | 2022-09-16 | NC | DE-GUP-DT-E-22-628 | 2022-09-07 | 0 | CRS-GUP-DHI-DT-22-778 | 2022-09-16 | NC
| GUP | YT01 | P1 | PGB | 128161 |  | GUP-YT01-P1PGB-128161 | CCWP_MOTOR DATA SHEET & CHARACTERISTIC CURVE | FI | 2023-01-18 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | CCWP | CCPP | Closed Cooling Water | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1010 | 2022-11-30 | 0 | CRS-GUP-DHI-DT-22-1269 | 2022-12-16 | NC | DE-GUP-DT-E-22-1010 | 2022-11-30 | 0 | CRS-GUP-DHI-DT-22-1269 | 2022-12-16 | NC
| GUP | YD00 | P1 | PGB | 128421 |  | GUP-YD00-P1PGB-128421 | CCWP_MOTOR OUTLINE DRAWING | FI | 2023-01-18 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  | R |  |  | CCWP | CCPP | Closed Cooling Water | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1010 | 2022-11-30 | 0 | CRS-GUP-DHI-DT-22-1269 | 2022-12-16 | NC | DE-GUP-DT-E-22-1010 | 2022-11-30 | 0 | CRS-GUP-DHI-DT-22-1269 | 2022-12-16 | NC
| GUP | YT02 | P1 | PGB | 128521 |  | GUP-YT02-P1PGB-128521 | CCWP_INSTRUMENT LIST & DATA SHEET | FI | 2023-01-18 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | CCWP | CCPP | Closed Cooling Water | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1010 | 2022-11-30 | 0 | CRS-GUP-DHI-DT-22-1269 | 2022-12-16 | NC | DE-GUP-DT-E-22-1010 | 2022-11-30 | 0 | CRS-GUP-DHI-DT-22-1269 | 2022-12-16 | NC
| GUP | YK09 | P1 | PGB | 128431 |  | GUP-YK09-P1PGB-128431 | CCWP_MOTOR TERMINAL BOX DRAWING | FI | 2023-01-18 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  | R |  |  | CCWP | CCPP | Closed Cooling Water | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1010 | 2022-11-30 | 0 | CRS-GUP-DHI-DT-22-1269 | 2022-12-16 | NC | DE-GUP-DT-E-22-1010 | 2022-11-30 | 0 | CRS-GUP-DHI-DT-22-1269 | 2022-12-16 | NC
| GUP | CQ02 | P1 | PGB | 128711 |  | GUP-CQ02-P1PGB-128711 | CCWP_OPERATION & MAINTENANCE MANUAL | FI | 2023-11-30 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | CCWP | CCPP | Closed Cooling Water | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-805 | 2023-09-11 | 0 | CRS-GUP-DHI-DT-23-2122 | 2023-10-26 | NC | DE-GUP-DT-E-23-805 | 2023-09-11 | 0 | CRS-GUP-DHI-DT-23-2122 | 2023-10-26 | NC
| GUP | XG02 | P1 | PCC | 129211 |  | GUP-XG02-P1PCC-129211 | ACWP_P&I DIAGRAM | FA | 2022-08-10 | 2022-11-09 | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | ACWP | CCPP | Circulating Water | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-205 | 2023-02-20 | 0 | CRS-GUP-DHI-DT-23-1466 | 2023-02-08 | AA | DE-GUP-DT-E-22-658 | 2022-09-14 | A | CRS-GUP-DHI-DT-22-880 | 2022-10-09 | RC | DE-GUP-DT-E-22-1100 | 2022-12-16 | B | CRS-GUP-DHI-DT-23-1466 | 2023-02-08 | AA | DE-GUP-DT-E-23-205 | 2023-02-20 | 0
| GUP | YD00 | P1 | PCC | 129441 |  | GUP-YD00-P1PCC-129441 | ACWP_PUMP OUTLINE DRAWING | FI | 2022-11-09 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  | R |  |  | ACWP | CCPP | Circulating Water | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-658 | 2023-06-30 | 3 | CRS-GUP-DHI-DT-23-2048 | 2023-07-14 | NC | DE-GUP-DT-E-22-639 | 2022-09-08 | 0 | CRS-GUP-DHI-DT-22-856 | 2022-09-24 | RC | DE-GUP-DT-E-22-1047 | 2022-12-08 | 1 | CRS-GUP-DHI-DT-22-1289 | 2022-12-21 | RC | DE-GUP-DT-E-22-1240 | 2023-01-09 | 2 | CRS-GUP-DHI-DT-23-1465 | 2023-02-08 | NC | DE-GUP-DT-E-23-658 | 2023-06-30 | 3 | CRS-GUP-DHI-DT-23-2048 | 2023-07-14 | NC
| GUP | YT01 | P1 | PCC | 129121 |  | GUP-YT01-P1PCC-129121 | ACWP_PUMP DATA SHEET & CHARACTERISTIC CURVE | FA | 2022-11-09 | 2023-02-09 | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | ACWP | CCPP | Circulating Water | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-205 | 2023-02-20 | 0 | CRS-GUP-DHI-DT-23-1466 | 2023-02-08 | AA | DE-GUP-DT-E-22-658 | 2022-09-14 | A | CRS-GUP-DHI-DT-22-880 | 2022-10-09 | RC | DE-GUP-DT-E-22-1100 | 2022-12-16 | B | CRS-GUP-DHI-DT-23-1466 | 2023-02-08 | AA | DE-GUP-DT-E-23-205 | 2023-02-20 | 0
| GUP | YK09 | P1 | PCC | 129451 |  | GUP-YK09-P1PCC-129451 | ACWP_PUMP SECTIONAL DRAWING | FI | 2022-11-09 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  | R |  |  | ACWP | CCPP | Circulating Water | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1084 | 2022-12-14 | 0 | CRS-GUP-DHI-DT-22-1297 | 2022-12-21 | NC | DE-GUP-DT-E-22-1084 | 2022-12-14 | 0 | CRS-GUP-DHI-DT-22-1297 | 2022-12-21 | NC
| GUP | YT01 | P1 | PCC | 129131 |  | GUP-YT01-P1PCC-129131 | ACWP_MOTOR DATA SHEET & CHARACTERISTIC CURVE | FI | 2022-11-09 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | ACWP | CCPP | Circulating Water | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-291 | 2023-03-09 | 1 | CRS-GUP-DHI-DT-23-1777 | 2023-03-27 | NC | DE-GUP-DT-E-22-1217 | 2023-01-04 | 0 | CRS-GUP-DHI-DT-22-1462 | 2023-02-05 | RC | DE-GUP-DT-E-23-291 | 2023-03-09 | 1 | CRS-GUP-DHI-DT-23-1777 | 2023-03-27 | NC
| GUP | YD00 | P1 | PCC | 129461 |  | GUP-YD00-P1PCC-129461 | ACWP_MOTOR OUTLINE DRAWING | FI | 2022-11-09 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  | R |  |  | ACWP | CCPP | Circulating Water | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-291 | 2023-03-09 | 1 | CRS-GUP-DHI-DT-23-1777 | 2023-03-27 | NC | DE-GUP-DT-E-22-1217 | 2023-01-04 | 0 | CRS-GUP-DHI-DT-22-1462 | 2023-02-05 | RC | DE-GUP-DT-E-23-291 | 2023-03-09 | 1 | CRS-GUP-DHI-DT-23-1777 | 2023-03-27 | NC
| GUP | YT02 | P1 | PCC | 129511 |  | GUP-YT02-P1PCC-129511 | ACWP_INSTRUMENT LIST & DATA SHEET | FI | 2022-11-09 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | ACWP | CCPP | Circulating Water | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-616 | 2023-06-14 | 3 | CRS-GUP-DHI-DT-23-2018 | 2023-06-21 | NC | DE-GUP-DT-E-23-312 | 2023-03-15 | 0 | CRS-GUP-DHI-DT-23-1786 | 2023-03-30 | NC | DE-GUP-DT-E-23-446 | 2023-04-12 | 1 | CRS-GUP-DHI-DT-23-1899 | 2023-05-05 | RC | DE-GUP-DT-E-23-555 | 2023-05-16 | 2 | CRS-GUP-DHI-DT-23-1961 | 2023-05-24 | RC | DE-GUP-DT-E-23-616 | 2023-06-14 | 3 | CRS-GUP-DHI-DT-23-2018 | 2023-06-21 | NC
| GUP | YK09 | P1 | PCC | 129611 |  | GUP-YK09-P1PCC-129611 | ACWP_MOTOR TERMINAL BOX DRAWING | FI | 2022-11-09 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  | R |  |  | ACWP | CCPP | Circulating Water | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-291 | 2023-03-09 | 1 | CRS-GUP-DHI-DT-23-1777 | 2023-03-27 | NC | DE-GUP-DT-E-22-1217 | 2023-01-04 | 0 | CRS-GUP-DHI-DT-22-1462 | 2023-02-05 | RC | DE-GUP-DT-E-23-291 | 2023-03-09 | 1 | CRS-GUP-DHI-DT-23-1777 | 2023-03-27 | NC
| GUP | XG02 | P1 | PAC | 129201 |  | GUP-XG02-P1PAC-129201 | CWP_P&I DIAGRAM | FA | 2022-08-10 | 2022-11-09 | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | CWP | CCPP | Circulating Water | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-205 | 2023-02-20 | 0 | CRS-GUP-DHI-DT-23-1466 | 2023-02-08 | AA | DE-GUP-DT-E-22-658 | 2022-09-14 | A | CRS-GUP-DHI-DT-22-880 | 2022-10-09 | RC | DE-GUP-DT-E-22-1100 | 2022-12-16 | B | CRS-GUP-DHI-DT-23-1466 | 2023-02-08 | AA | DE-GUP-DT-E-23-205 | 2023-02-20 | 0
| GUP | YD00 | P1 | PAC | 129401 |  | GUP-YD00-P1PAC-129401 | CWP_PUMP OUTLINE DRAWING | FI | 2022-11-09 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  | R |  |  | CWP | CCPP | Circulating Water | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-658 | 2023-06-30 | 3 | CRS-GUP-DHI-DT-23-2048 | 2023-07-14 | NC | DE-GUP-DT-E-22-639 | 2022-09-08 | 0 | CRS-GUP-DHI-DT-22-856 | 2022-09-24 | RC | DE-GUP-DT-E-22-1047 | 2022-12-08 | 1 | CRS-GUP-DHI-DT-22-1289 | 2022-12-21 | RC | DE-GUP-DT-E-22-1240 | 2023-01-09 | 2 | CRS-GUP-DHI-DT-23-1465 | 2023-02-08 | NC | DE-GUP-DT-E-23-658 | 2023-06-30 | 3 | CRS-GUP-DHI-DT-23-2048 | 2023-07-14 | NC
| GUP | YT01 | P1 | PAC | 129101 |  | GUP-YT01-P1PAC-129101 | CWP_PUMP DATA SHEET & CHARACTERISTIC CURVE | FA | 2022-08-10 | 2022-11-09 | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | CWP | CCPP | Circulating Water | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-205 | 2023-02-20 | 0 | CRS-GUP-DHI-DT-23-1466 | 2023-02-08 | AA | DE-GUP-DT-E-22-658 | 2022-09-14 | A | CRS-GUP-DHI-DT-22-880 | 2022-10-09 | RC | DE-GUP-DT-E-22-1100 | 2022-12-16 | B | CRS-GUP-DHI-DT-23-1466 | 2023-02-08 | AA | DE-GUP-DT-E-23-205 | 2023-02-20 | 0
| GUP | YK09 | P1 | PAC | 129411 |  | GUP-YK09-P1PAC-129411 | CWP_PUMP SECTIONAL DRAWING | FI | 2022-11-09 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  | R |  |  | CWP | CCPP | Circulating Water | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1084 | 2022-12-14 | 0 | CRS-GUP-DHI-DT-22-1297 | 2022-12-21 | NC | DE-GUP-DT-E-22-1084 | 2022-12-14 | 0 | CRS-GUP-DHI-DT-22-1297 | 2022-12-21 | NC
| GUP | YT01 | P1 | PAC | 129111 |  | GUP-YT01-P1PAC-129111 | CWP_MOTOR DATA SHEET & CHARACTERISTIC CURVE | FI | 2022-11-09 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | CWP | CCPP | Circulating Water | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1198 | 2022-12-26 | 0 | CRS-GUP-DHI-DT-22-1458 | 2023-02-04 | NC | DE-GUP-DT-E-22-1198 | 2022-12-26 | 0 | CRS-GUP-DHI-DT-22-1458 | 2023-02-04 | NC
| GUP | YD00 | P1 | PAC | 129421 |  | GUP-YD00-P1PAC-129421 | CWP_MOTOR OUTLINE DRAWING | FI | 2022-11-09 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  | R |  |  | CWP | CCPP | Circulating Water | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1198 | 2022-12-26 | 0 | CRS-GUP-DHI-DT-22-1458 | 2023-02-04 | NC | DE-GUP-DT-E-22-1198 | 2022-12-26 | 0 | CRS-GUP-DHI-DT-22-1458 | 2023-02-04 | NC
| GUP | YT02 | P1 | PAC | 129501 |  | GUP-YT02-P1PAC-129501 | CWP_INSTRUMENT LIST & DATA SHEET | FI | 2022-11-09 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | CWP | CCPP | Circulating Water | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-555 | 2023-05-16 | 1 | CRS-GUP-DHI-DT-23-1961 | 2023-05-24 | NC | DE-GUP-DT-E-23-446 | 2023-04-12 | 0 | CRS-GUP-DHI-DT-23-1899 | 2023-05-05 | RC | DE-GUP-DT-E-23-555 | 2023-05-16 | 1 | CRS-GUP-DHI-DT-23-1961 | 2023-05-24 | NC
| GUP | YK09 | P1 | PAC | 129431 |  | GUP-YK09-P1PAC-129431 | CWP_MOTOR TERMINAL BOX DRAWING | FI | 2022-11-09 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  | R |  |  | CWP | CCPP | Circulating Water | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1198 | 2022-12-26 | 0 | CRS-GUP-DHI-DT-22-1458 | 2023-02-04 | NC | DE-GUP-DT-E-22-1198 | 2022-12-26 | 0 | CRS-GUP-DHI-DT-22-1458 | 2023-02-04 | NC
| GUP | CT00 | P1 | PUA | 129601 |  | GUP-CT00-P1PUA-129601 | CWP & ACWP_INSTALLATION, OPERATION & MAINTENANCE MANUAL | FI | 2023-11-30 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | CWP | CCPP | Circulating Water | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-805 | 2023-09-11 | 0 | CRS-GUP-DHI-DT-23-2122 | 2023-10-26 | NC | DE-GUP-DT-E-23-805 | 2023-09-11 | 0 | CRS-GUP-DHI-DT-23-2122 | 2023-10-26 | NC
| GUP | DD01 | P1 | PAC | 129998 |  | GUP-DD01-P1PAC-129998 | CW SYSTEM_SUMP MODEL TEST PROCEDURE | FI | 2022-06-30 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  |  |  |  | CWP | CCPP | Circulating Water | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-445 | 2022-07-26 | 1 | CRS-GUP-DHI-DT-22-647 | 2022-08-20 | NC | DE-GUP-DT-E-22-330 | 2022-06-24 | 0 | CRS-GUP-DHI-DT-22-528 | 2022-07-19 | NC | DE-GUP-DT-E-22-445 | 2022-07-26 | 1 | CRS-GUP-DHI-DT-22-647 | 2022-08-20 | NC
| GUP | DD00 | P1 | PAC | 129999 |  | GUP-DD00-P1PAC-129999 | CW SYSTEM_SUMP MODEL TEST REPORT | FI | 2022-11-04 |  | Power EPC프로세스기술팀(Mech.) | 김광희 |  | R |  |  | CWP | CCPP | Circulating Water | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1245 | 2023-01-10 | 1 | CRS-GUP-DHI-DT-23-1516 | 2023-02-14 | NC | DE-GUP-DT-E-22-843 | 2022-10-24 | 0 | CRS-GUP-DHI-DT-22-1167 | 2022-11-26 | RC | DE-GUP-DT-E-22-1245 | 2023-01-10 | 1 | CRS-GUP-DHI-DT-23-1516 | 2023-02-14 | NC
| GUP | XW03 | P1 | MJ | 120001 |  | GUP-XW03-P1MJ-120001 | DIESEL GENERATOR_SIZING CALCULATION | FA | 2021-10-01 | 2022-06-24 | Power EPC프로세스기술팀(Mech.) | 김광희 |  | P |  |  |  | CCPP | Diesel Generator | Mech. | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-22-779 | 2022-10-11 | 1 | CRS-GUP-DHI-DT-22-815 | 2022-09-20 | AA | DHI-GUP-DT-21-046 | 2021-10-01 | A | CRS-GUP-DHI-DT-21-064 | 2021-11-17 | RC | DHI-GUP-DT-22-053 | 2022-01-28 | B | CRS-GUP-DHI-DT-22-212 | 2022-02-20 | RC | DHI-GUP-DT-22-209 | 2022-05-11 | C | CRS-GUP-DHI-DT-22-391 | 2022-06-07 | AA | DE-GUP-DT-E-22-505 | 2022-08-16 | 0(CP) | CRS-GUP-DHI-DT-22-815 | 2022-09-20 | AA | DE-GUP-DT-E-22-779 | 2022-10-11 | 1
| GUP | XW03 | P1 | QJA | 127001 |  | GUP-XW03-P1QJA-127001 | N2 GAS_SIZING CALCULATION | FA | 2021-09-09 | 2022-01-28 | Power EPC프로세스기술팀(Mech.) | 김광희 |  | P |  |  |  | CCPP | N2 Gas | Mech. | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-956 | 2023-11-30 | 2 | CRS-GUP-DHI-DT-22-1151 | 2022-11-23 | AA | DHI-GUP-DT-21-020 | 2021-09-09 | A | CRS-GUP-DHI-DT-21-013 | 2021-09-29 | RC | DHI-GUP-DT-21-177 | 2021-12-16 | B | CRS-GUP-DHI-DT-21-122 | 2022-01-07 | AC | DE-GUP-DT-E-22-230 | 2022-05-19 | 0 | CRS-GUP-DHI-DT-22-376 | 2022-05-30 | AC | DE-GUP-DT-E-22-910 | 2022-11-04 | 1(CP) | CRS-GUP-DHI-DT-22-1151 | 2022-11-23 | AA | DE-GUP-DT-E-23-956 | 2023-11-30 | 2
| GUP | XW03 | P1 | PGB | 128901 |  | GUP-XW03-P1PGB-128901 | CCWP_SIZING CALCULATION | FA | 2021-09-09 | 2022-01-28 | Power EPC프로세스기술팀(Mech.) | 김광희 |  | P |  |  |  | CCPP | Closed Cooling Water | Mech. | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-946 | 2023-11-24 | 2 | 자체 CRS 개정 후 제출 | 2023-11-23 | N/A | DHI-GUP-DT-21-020 | 2021-09-09 | A | CRS-GUP-DHI-DT-21-011 | 2021-09-28 | RC | DHI-GUP-DT-21-120 | 2021-11-26 | B | CRS-GUP-DHI-DT-21-092 | 2021-12-23 | AC | DHI-GUP-DT-22-167 | 2022-04-12 | 0 | CRS-GUP-DHI-DT-22-356 | 2022-05-22 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-454 | 2022-07-26 | 1(CP) | 자체 CRS 개정 후 제출 | 2023-11-23 | N/A | DE-GUP-DT-E-23-946 | 2023-11-24 | 2
| GUP | XW03 | P1 | PAC | 129901 |  | GUP-XW03-P1PAC-129901 | CWP_SIZING CALCULATION | FA | 2021-09-09 | 2022-01-28 | Power EPC프로세스기술팀(Mech.) | 김광희 |  | P |  |  |  | CCPP | Circulating Water | Mech. | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-936 | 2023-11-23 | 2 | CRS-GUP-DHI-DT-22-1119 | 2022-11-23 | AA | DHI-GUP-DT-21-020 | 2021-09-09 | A | CRS-GUP-DHI-DT-21-010 | 2021-09-28 | RC | DHI-GUP-DT-21-122 | 2021-11-26 | B | CRS-GUP-DHI-DT-21-126 | 2022-01-11 | AC | DHI-GUP-DT-22-167 | 2022-04-12 | 0 | CRS-GUP-DHI-DT-22-356 | 2022-05-22 | RC | DE-GUP-DT-E-22-699 | 2022-09-23 | 1(CP) | CRS-GUP-DHI-DT-22-1119 | 2022-11-23 | AA | DE-GUP-DT-E-23-936 | 2023-11-23 | 2
| GUP | XW03 | P1 | PCC | 129911 |  | GUP-XW03-P1PCC-129911 | ACWP_SIZING CALCULATION | FA | 2021-09-09 | 2022-01-28 | Power EPC프로세스기술팀(Mech.) | 김광희 |  | P |  |  |  | CCPP | Circulating Water | Mech. | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-936 | 2023-11-23 | 2 | CRS-GUP-DHI-DT-22-1119 | 2022-11-23 | AA | DHI-GUP-DT-21-020 | 2021-09-09 | A | CRS-GUP-DHI-DT-21-010 | 2021-09-28 | RC | DHI-GUP-DT-21-122 | 2021-11-26 | B | CRS-GUP-DHI-DT-21-126 | 2022-01-11 | AC | DHI-GUP-DT-22-167 | 2022-04-12 | 0 | CRS-GUP-DHI-DT-22-356 | 2022-05-22 | AC | DE-GUP-DT-E-22-699 | 2022-09-23 | 1(CP) | CRS-GUP-DHI-DT-22-1119 | 2022-11-23 | AA | DE-GUP-DT-E-23-936 | 2023-11-23 | 2
| GUP | XW03 | P1 | LC | 126911 |  | GUP-XW03-P1LC-126911 | CEP_SIZING CALCULATION | FA | 2021-09-09 | 2022-02-25 | Power EPC프로세스기술팀(Mech.) | 김석희 |  | P |  |  |  | CCPP | Condensate | Mech. | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-943 | 2023-11-23 | 2 | 자체 CRS 개정 후 제출 | 2023-11-22 | N/A | DHI-GUP-DT-21-020 | 2021-09-09 | A | CRS-GUP-DHI-DT-21-015 | 2021-09-29 | RC | DHI-GUP-DT-21-126 | 2021-11-29 | B | CRS-GUP-DHI-DT-21-128 | 2022-01-11 | AC | DHI-GUP-DT-22-170 | 2022-04-13 | 0 | CRS-GUP-DHI-DT-22-324 | 2022-05-02 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-634 | 2022-09-07 | 1(CP) | 자체 CRS 개정 후 제출 | 2023-11-22 | N/A | DE-GUP-DT-E-23-943 | 2023-11-23 | 2
| GUP | XW03 | P1 | LA | 126901 |  | GUP-XW03-P1LA-126901 | BFP_SIZING CALCULATION | FA | 2021-09-09 | 2022-02-25 | Power EPC프로세스기술팀(Mech.) | 김석희 |  | P |  |  |  | CCPP | Feedwater | Mech. | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-943 | 2023-11-23 | 2 | CRS-GUP-DHI-DT-22-324 | 2022-05-02 | AA(승인등급 변경-Email 접수) | DHI-GUP-DT-21-020 | 2021-09-09 | A | CRS-GUP-DHI-DT-21-012 | 2021-09-28 | RC | DHI-GUP-DT-21-126 | 2021-11-29 | B | CRS-GUP-DHI-DT-21-128 | 2022-01-11 | AA | DHI-GUP-DT-22-170 | 2022-04-13 | 0 | CRS-GUP-DHI-DT-22-324 | 2022-05-02 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-634 | 2022-09-07 | 1(CP) | 자체 CRS 개정 후 제출 | 2023-11-22 | N/A | DE-GUP-DT-E-23-943 | 2023-11-23 | 2
| GUP | XW03 | P1 | GHC | 116901 |  | GUP-XW03-P1GHC-116901 | DWP_SIZING CALCULATION | FA | 2021-11-19 | 2022-01-28 | Power EPC프로세스기술팀(Mech.) | 강석채 |  | P |  |  |  | CCPP | Demi Water | Mech. | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-937 | 2023-11-23 | 2 | CRS-GUP-DHI-DT-22-1127 | 2022-11-23 | AA | DHI-GUP-DT-21-117 | 2021-11-26 | A | CRS-GUP-DHI-DT-21-090 | 2021-12-23 | AC | DHI-GUP-DT-22-165 | 2022-04-12 | 0 | CRS-GUP-DHI-DT-22-323 | 2022-05-02 | AC | DE-GUP-DT-E-22-748 | 2022-10-04 | 1(CP) | CRS-GUP-DHI-DT-22-1127 | 2022-11-23 | AA | DE-GUP-DT-E-23-937 | 2023-11-23 | 2
| GUP | XW03 | P1 | LCM | 111001 |  | GUP-XW03-P1LCM-111001 | SIZING CALCULATION_FLASH TANK DRAIN PUMP AND TANK | FA | 2021-12-13 | 2022-06-13 | Power EPC프로세스기술팀(Mech.) | 김광희 |  | P |  |  |  | CCPP | Steam | Mech. | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-955 | 2023-11-30 | 1 | N/A-메일로 회신 받음 | 2023-02-07 | AA | DHI-GUP-DT-21-166 | 2021-12-19 | A | CRS-GUP-DHI-DT-21-125 | 2021-12-20 | RC | DHI-GUP-DT-22-171 | 2022-04-13 | B | CRS-GUP-DHI-DT-22-325 | 2022-05-02 | AC | DE-GUP-DT-E-22-352 | 2022-07-01 | 0(CP) | N/A-메일로 회신 받음 | 2023-02-07 | AA | DE-GUP-DT-E-23-955 | 2023-11-30 | 1
| GUP | YK10 | P1 | EGB | 436001 |  | GUP-YK10-P1EGB-436001 | ULSD STORAGE TANK_GENERAL ARRANGEMENT DRAWING | FA | 2021-11-03 | 2022-06-04 | Water EPC프로세스기술팀(Mech.) | 박상익 | B | P |  |  |  | CCPP | ULSD Tank | Mech. | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-194 | 2024-08-05 | 4 | 자체 CRS 개정 후 제출 | 2024-08-04 | N/A | DHI-GUP-DT-21-009 | 2021-07-12 | A | CRS-GUP-DHI-DT-21-020 | 2021-09-30 | RR | DHI-GUP-DT-21-095 | 2021-11-10 | B | CRS-GUP-DHI-DT-21-074 | 2021-11-30 | RC | DHI-GUP-DT-21-194 | 2021-12-23 | C | CRS-GUP-DHI-DT-21-138 | 2022-01-11 | AA | DE-GUP-DT-E-22-573 | 2022-08-29 | 0(CP) | CRS-GUP-DHI-DT-22-763 | 2022-09-14 | AA | DE-GUP-DT-E-23-813 | 2023-09-15 | 1(CP) | 자체 CRS 개정 후 제출 | 2023-11-08 | N/A | DE-GUP-DT-E-23-898 | 2023-11-09 | 2 | 자체 CRS 개정 후 제출 | 2024-03-14 | N/A | DE-GUP-DT-E-24-077 | 2024-03-15 | 3 | 자체 CRS 개정 후 제출 | 2024-08-04 | N/A | DE-GUP-DT-E-24-194 | 2024-08-05 | 4
| GUP | YK09 | P1 | EGB | 436002 |  | GUP-YK09-P1EGB-436002 | ULSD STORAGE TANK_NOZZLE ORIENTATION DRAWING | FI | 2021-11-03 |  | Water EPC프로세스기술팀(Mech.) | 박상익 |  | P |  |  |  | CCPP | ULSD Tank | Mech. | 3 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-194 | 2024-08-05 | 8 | 자체 CRS 개정 후 제출 | 2024-08-04 | N/A | DHI-GUP-DT-21-009 | 2021-07-12 | 0 | CRS-GUP-DHI-DT-21-020 | 2021-09-30 | RC | DHI-GUP-DT-21-095 | 2021-11-10 | 1 | CRS-GUP-DHI-DT-21-074 | 2021-11-30 | I | DHI-GUP-DT-21-194 | 2021-12-23 | 2 | CRS-GUP-DHI-DT-21-138 | 2022-01-11 | I | DE-GUP-DT-E-22-573 | 2022-08-29 | 3 | CRS-GUP-DHI-DT-22-763 | 2022-09-14 | AA | DE-GUP-DT-E-23-810 | 2023-09-15 | 4 | 자체 CRS 개정 후 제출 | 2023-11-08 | N/A | DE-GUP-DT-E-23-898 | 2023-11-09 | 5 | 자체 CRS 개정 후 제출 | 2024-03-14 | N/A | DE-GUP-DT-E-24-077 | 2024-03-15 | 6 | 자체 CRS 개정 후 제출 | 2024-04-02 | N/A | DE-GUP-DT-E-24-100 | 2024-04-03 | 7 | 자체 CRS 개정 후 제출 | 2024-08-04 | N/A | DE-GUP-DT-E-24-194 | 2024-08-05 | 8
| GUP | YK09 | P1 | EGB | 436003 |  | GUP-YK09-P1EGB-436003 | ULSD STORAGE TANK_NAME PLATE DRAWING | FI | 2022-06-18 |  | Water EPC프로세스기술팀(Mech.) | 박상익 | [5 empty] | CCPP | ULSD Tank | Mech. | 4 | 2025-06-30 | 2025-07-01 |  | DHI-GUP-DT-22-061 | 2022-02-11 | 0 | CRS-GUP-DHI-DT-22-217 | 2022-02-20 | NC | DHI-GUP-DT-22-061 | 2022-02-11 | 0 | CRS-GUP-DHI-DT-22-217 | 2022-02-20 | NC
| GUP | XW03 | P1 | EGB | 436101 |  | GUP-XW03-P1EGB-436101 | ULSD STORAGE TANK_MECHANICAL STRENGTH CALCULATION | FI | 2022-02-16 |  | Water EPC프로세스기술팀(Mech.) | 박상익 |  | P |  |  |  | CCPP | ULSD Tank | Mech. | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-078 | 2024-03-15 | 3 | 자체 CRS 개정 후 제출 | 2024-03-14 | N/A | DHI-GUP-DT-21-095 | 2021-11-10 | 0 | CRS-GUP-DHI-DT-21-074 | 2021-11-30 | NC | DE-GUP-DT-E-22-856 | 2022-10-26 | 1 | CRS-GUP-DHI-DT-22-1018 | 2022-11-13 | NC | DE-GUP-DT-E-23-813 | 2023-09-15 | 2 | 자체 CRS 개정 후 제출 | 2024-03-14 | N/A | DE-GUP-DT-E-24-078 | 2024-03-15 | 3
| GUP | YK09 | P1 | EGB | 436202 |  | GUP-YK09-P1EGB-436202 | ULSD STORAGE TANK_DETAIL DRAWINGS FOR CATHODIC PROTECTION SYSTEM | FI | 2022-07-25 |  | Water EPC프로세스기술팀(Mech.) | 박상익 | [5 empty] | CCPP | ULSD Tank | Elec. | 4 | 2025-06-30 |  |  | DE-GUP-DT-E-22-457 | 2022-07-27 | 0 | CRS-GUP-DHI-DT-22-677 | 2022-08-22 | NC | DE-GUP-DT-E-22-457 | 2022-07-27 | 0 | CRS-GUP-DHI-DT-22-677 | 2022-08-22 | NC
| GUP | YK10 | P1 | GHC | 431001 |  | GUP-YK10-P1GHC-431001 | DEMI. WATER STORAGE TANK_GENERAL ARRANGEMENT DRAWING | FA | 2021-11-03 | 2022-06-04 | Water EPC프로세스기술팀(Mech.) | 박상익 | B | P |  |  |  | CCPP | DW Tank | Mech. | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-077 | 2024-03-15 | 3 | 자체 CRS 개정 후 제출 | 2024-03-14 | N/A | DHI-GUP-DT-21-009 | 2021-07-12 | A | CRS-GUP-DHI-DT-21-020 | 2021-09-30 | RR | DHI-GUP-DT-21-095 | 2021-11-10 | B | CRS-GUP-DHI-DT-21-074 | 2021-11-30 | RC | DHI-GUP-DT-21-194 | 2021-12-23 | C | CRS-GUP-DHI-DT-21-138 | 2022-01-11 | AA | DE-GUP-DT-E-22-573 | 2022-08-29 | 0(CP) | CRS-GUP-DHI-DT-22-763 | 2022-09-14 | AA | DE-GUP-DT-E-23-811 | 2023-09-15 | 1 | 자체 CRS 개정 후 제출 | 2023-11-08 | N/A | DE-GUP-DT-E-23-898 | 2023-11-09 | 2 | 자체 CRS 개정 후 제출 | 2024-03-14 | N/A | DE-GUP-DT-E-24-077 | 2024-03-15 | 3
| GUP | YK09 | P1 | GHC | 431002 |  | GUP-YK09-P1GHC-431002 | DEMI. WATER STORAGE TANK_NOZZLE ORIENTATION DRAWING | FI | 2021-11-03 |  | Water EPC프로세스기술팀(Mech.) | 박상익 |  | P |  |  |  | CCPP | DW Tank | Mech. | 3 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-077 | 2024-03-15 | 6 | 자체 CRS 개정 후 제출 | 2024-03-14 | N/A | DHI-GUP-DT-21-009 | 2021-07-12 | 0 | CRS-GUP-DHI-DT-21-020 | 2021-09-30 | RC | DHI-GUP-DT-21-095 | 2021-11-10 | 1 | CRS-GUP-DHI-DT-21-074 | 2021-11-30 | I | DHI-GUP-DT-21-194 | 2021-12-23 | 2 | CRS-GUP-DHI-DT-21-138 | 2022-01-11 | I | DE-GUP-DT-E-22-573 | 2022-08-29 | 3 | CRS-GUP-DHI-DT-22-763 | 2022-09-14 | AA | DE-GUP-DT-E-23-811 | 2023-09-15 | 4 | 자체 CRS 개정 후 제출 | 2023-11-08 | N/A | DE-GUP-DT-E-23-898 | 2023-11-09 | 5 | 자체 CRS 개정 후 제출 | 2024-03-14 | N/A | DE-GUP-DT-E-24-077 | 2024-03-15 | 6
| GUP | YK09 | P1 | GHC | 431003 |  | GUP-YK09-P1GHC-431003 | DEMI. WATER STORAGE TANK_NAME PLATE DRAWING | FI | 2022-06-18 |  | Water EPC프로세스기술팀(Mech.) | 박상익 | [5 empty] | CCPP | DW Tank | Mech. | 4 | 2025-06-30 | 2025-07-01 |  | DHI-GUP-DT-22-061 | 2022-02-11 | 0 | CRS-GUP-DHI-DT-22-217 | 2022-02-20 | NC | DHI-GUP-DT-22-061 | 2022-02-11 | 0 | CRS-GUP-DHI-DT-22-217 | 2022-02-20 | NC
| GUP | XW03 | P1 | GHC | 431101 |  | GUP-XW03-P1GHC-431101 | DEMI. WATER STORAGE TANK_MECHANICAL STRENGTH CALCULATION | FI | 2022-02-16 |  | Water EPC프로세스기술팀(Mech.) | 박상익 |  | P |  |  |  | CCPP | DW Tank | Mech. | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-078 | 2024-03-15 | 2 | CRS-GUP-DHI-DT-22-1018 | 2022-11-13 | NC | DHI-GUP-DT-21-095 | 2021-11-10 | 0 | CRS-GUP-DHI-DT-21-074 | 2021-11-30 | NC | DE-GUP-DT-E-22-856 | 2022-10-26 | 1 | CRS-GUP-DHI-DT-22-1018 | 2022-11-13 | NC | DE-GUP-DT-E-24-078 | 2024-03-15 | 2
| GUP | YK09 | P1 | GHC | 431202 |  | GUP-YK09-P1GHC-431202 | DEMI. WATER STORAGE TANK_DETAIL DRAWINGS FOR CATHODIC PROTECTION SYSTEM | FI | 2022-07-25 |  | Water EPC프로세스기술팀(Mech.) | 박상익 | [5 empty] | CCPP | ULSD Tank | Elec. | 4 | 2025-06-30 |  |  | DE-GUP-DT-E-23-274 | 2023-03-07 | 1 | CRS-GUP-DHI-DT-23-1774 | 2023-03-27 | NC | DE-GUP-DT-E-22-576 | 2022-08-30 | 0 | CRS-GUP-DHI-DT-22-868 | 2022-10-09 | RC | DE-GUP-DT-E-23-274 | 2023-03-07 | 1 | CRS-GUP-DHI-DT-23-1774 | 2023-03-27 | NC
| GUP | YK10 | P1 | GHB | 432001 |  | GUP-YK10-P1GHB-432001 | TREATED WATER STORAGE TANK_GENERAL ARRANGEMENT DRAWING | FA | 2021-11-03 | 2022-06-04 | Water EPC프로세스기술팀(Mech.) | 박상익 | B | P |  |  |  | CCPP | TW Tank | Mech. | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-077 | 2024-03-15 | 2 | 자체 CRS 개정 후 제출 | 2024-03-14 | N/A | DHI-GUP-DT-21-009 | 2021-07-12 | A | CRS-GUP-DHI-DT-21-020 | 2021-09-30 | RR | DHI-GUP-DT-21-095 | 2021-11-10 | B | CRS-GUP-DHI-DT-21-074 | 2021-11-30 | RC | DHI-GUP-DT-21-194 | 2021-12-23 | C | CRS-GUP-DHI-DT-21-138 | 2022-01-11 | AA | DE-GUP-DT-E-22-573 | 2022-08-29 | 0(CP) | CRS-GUP-DHI-DT-22-763 | 2022-09-14 | AA | DE-GUP-DT-E-23-897 | 2023-11-09 | 1 | 자체 CRS 개정 후 제출 | 2024-03-14 | N/A | DE-GUP-DT-E-24-077 | 2024-03-15 | 2
| GUP | YK09 | P1 | GHB | 432002 |  | GUP-YK09-P1GHB-432002 | TREATED WATER STORAGE TANK_NOZZLE ORIENTATION DRAWING | FI | 2021-11-03 |  | Water EPC프로세스기술팀(Mech.) | 박상익 |  | P |  |  |  | CCPP | TW Tank | Mech. | 3 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-152 | 2024-06-11 | 7 | 자체 CRS 개정 후 제출 | 2024-06-10 | N/A | DHI-GUP-DT-21-009 | 2021-07-12 | 0 | CRS-GUP-DHI-DT-21-020 | 2021-09-30 | RC | DHI-GUP-DT-21-095 | 2021-11-10 | 1 | CRS-GUP-DHI-DT-21-074 | 2021-11-30 | I | DHI-GUP-DT-21-194 | 2021-12-23 | 2 | CRS-GUP-DHI-DT-21-138 | 2022-01-11 | I | DE-GUP-DT-E-22-573 | 2022-08-29 | 3 | CRS-GUP-DHI-DT-22-763 | 2022-09-14 | AA | DE-GUP-DT-E-23-811 | 2023-09-15 | 4 | 자체 CRS 개정 후 제출 | 2023-11-08 | N/A | DE-GUP-DT-E-23-898 | 2023-11-09 | 5 | 자체 CRS 개정 후 제출 | 2024-03-14 | N/A | DE-GUP-DT-E-24-077 | 2024-03-15 | 6 | 자체 CRS 개정 후 제출 | 2024-06-10 | N/A | DE-GUP-DT-E-24-152 | 2024-06-11 | 7
| GUP | YK09 | P1 | GHB | 432003 |  | GUP-YK09-P1GHB-432003 | TREATED WATER STORAGE TANK_NAME PLATE DRAWING | FI | 2022-06-18 |  | Water EPC프로세스기술팀(Mech.) | 박상익 | [5 empty] | CCPP | TW Tank | Mech. | 4 | 2025-06-30 | 2025-07-01 |  | DHI-GUP-DT-22-061 | 2022-02-11 | 0 | CRS-GUP-DHI-DT-22-217 | 2022-02-20 | NC | DHI-GUP-DT-22-061 | 2022-02-11 | 0 | CRS-GUP-DHI-DT-22-217 | 2022-02-20 | NC
| GUP | XW03 | P1 | GHB | 432101 |  | GUP-XW03-P1GHB-432101 | TREATED WATER STORAGE TANK_MECHANICAL STRENGTH CALCULATION | FI | 2022-02-16 |  | Water EPC프로세스기술팀(Mech.) | 박상익 |  | P |  |  |  | CCPP | TW Tank | Mech. | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-078 | 2024-03-15 | 2 | CRS-GUP-DHI-DT-22-1018 | 2022-11-13 | NC | DHI-GUP-DT-21-095 | 2021-11-10 | 0 | CRS-GUP-DHI-DT-21-074 | 2021-11-30 | NC | DE-GUP-DT-E-22-856 | 2022-10-26 | 1 | CRS-GUP-DHI-DT-22-1018 | 2022-11-13 | NC | DE-GUP-DT-E-24-078 | 2024-03-15 | 2
| GUP | YK09 | P1 | GHB | 432202 |  | GUP-YK09-P1GHB-432202 | TREATED WATER STORAGE TANK_DETAIL DRAWINGS FOR CATHODIC PROTECTION SYSTEM | FI | 2022-07-25 |  | Water EPC프로세스기술팀(Mech.) | 박상익 | [5 empty] | CCPP | ULSD Tank | Elec. | 4 | 2025-06-30 |  |  | DE-GUP-DT-E-24-206 | 2024-08-22 | 1 | CRS-GUP-DHI-DT-22-677 | 2022-08-22 | NC | DE-GUP-DT-E-22-457 | 2022-07-27 | 0 | CRS-GUP-DHI-DT-22-677 | 2022-08-22 | NC | DE-GUP-DT-E-24-206 | 2024-08-22 | 1
| GUP | YK10 | P1 | LAA | 433001 |  | GUP-YK10-P1LAA-433001 | UF FEED WATER STORAGE TANK_GENERAL ARRANGEMENT DRAWING | FA | 2021-11-03 | 2022-10-31 | Water EPC프로세스기술팀(Mech.) | 박상익 | B | P |  |  |  | CCPP | UF FW Tank | Mech. | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-077 | 2024-03-15 | 1 | 자체 CRS 개정 후 제출 | 2024-03-14 | N/A | DHI-GUP-DT-21-028 | 2021-09-17 | A | CRS-GUP-DHI-DT-21-035 | 2021-10-06 | RR | DE-GUP-DT-E-22-326 | 2022-06-22 | B | CRS-GUP-DHI-DT-22-545 | 2022-07-25 | RC | DE-GUP-DT-E-22-572 | 2022-08-29 | C | CRS-GUP-DHI-DT-22-786 | 2022-09-19 | RC | DE-GUP-DT-E-22-988 | 2022-11-25 | D | CRS-GUP-DHI-DT-22-1302 | 2022-12-21 | AA | DE-GUP-DT-E-22-1233 | 2023-01-06 | 0 | 자체 CRS 개정 후 제출 | 2024-03-14 | N/A | DE-GUP-DT-E-24-077 | 2024-03-15 | 1
| GUP | YK09 | P1 | LAA | 433002 |  | GUP-YK09-P1LAA-433002 | UF FEED WATER STORAGE TANK_NOZZLE ORIENTATION DRAWING | FI | 2021-11-03 |  | Water EPC프로세스기술팀(Mech.) | 박상익 |  | P |  |  |  | CCPP | UF FW Tank | Mech. | 3 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-077 | 2024-03-15 | 4 | 자체 CRS 개정 후 제출 | 2024-03-14 | N/A | DHI-GUP-DT-21-028 | 2021-09-17 | 0 | CRS-GUP-DHI-DT-21-035 | 2021-10-06 | NC | DE-GUP-DT-E-22-326 | 2022-06-22 | 1 | CRS-GUP-DHI-DT-22-545 | 2022-07-25 | NC | DE-GUP-DT-E-22-572 | 2022-08-29 | 2 | CRS-GUP-DHI-DT-22-786 | 2022-09-19 | NC | DE-GUP-DT-E-23-898 | 2023-11-09 | 3 | 자체 CRS 개정 후 제출 | 2024-03-14 | N/A | DE-GUP-DT-E-24-077 | 2024-03-15 | 4
| GUP | YK09 | P1 | LAA | 433003 |  | GUP-YK09-P1LAA-433003 | UF FEED WATER STORAGE TANK_NAME PLATE DRAWING | FI | 2022-12-03 |  | Water EPC프로세스기술팀(Mech.) | 박상익 | [5 empty] | CCPP | UF FW Tank | Mech. | 4 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-22-1244 | 2023-01-10 | 0 | CRS-GUP-DHI-DT-23-1515 | 2023-02-14 | NC | DE-GUP-DT-E-22-1244 | 2023-01-10 | 0 | CRS-GUP-DHI-DT-23-1515 | 2023-02-14 | NC
| GUP | XW03 | P1 | LAA | 433101 |  | GUP-XW03-P1LAA-433101 | UF FEED WATER STORAGE TANK_MECHANICAL STRENGTH CALCULATION | FI | 2022-08-01 |  | Water EPC프로세스기술팀(Mech.) | 박상익 |  | P |  |  |  | CCPP | UF FW Tank | Mech. | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-079 | 2024-03-15 | 1 | CRS-GUP-DHI-DT-22-753 | 2022-09-12 | NC | DE-GUP-DT-E-22-556 | 2022-08-25 | 0 | CRS-GUP-DHI-DT-22-753 | 2022-09-12 | NC | DE-GUP-DT-E-24-079 | 2024-03-15 | 1
| GUP | YK09 | P1 | LAA | 433202 |  | GUP-YK09-P1LAA-433202 | UF FEED WATER STORAGE TANK_DETAIL DRAWINGS FOR CATHODIC PROTECTION SYSTEM | FI | 2022-07-25 |  | Water EPC프로세스기술팀(Mech.) | 박상익 | [5 empty] | CCPP | ULSD Tank | Elec. | 4 | 2025-06-30 |  |  | DE-GUP-DT-E-23-274 | 2023-03-07 | 1 | CRS-GUP-DHI-DT-23-1774 | 2023-03-27 | NC | DE-GUP-DT-E-22-576 | 2022-08-30 | 0 | CRS-GUP-DHI-DT-22-868 | 2022-10-09 | RC | DE-GUP-DT-E-23-274 | 2023-03-07 | 1 | CRS-GUP-DHI-DT-23-1774 | 2023-03-27 | NC
| GUP | YK10 | P1 | GKB | 434001 |  | GUP-YK10-P1GKB-434001 | POTABLE WATER STORAGE TANK_GENERAL ARRANGEMENT DRAWING | FA | 2021-11-03 | 2022-10-31 | Water EPC프로세스기술팀(Mech.) | 박상익 | B | P |  |  |  | CCPP | PW Tank | Mech. | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-077 | 2024-03-15 | 2 | 자체 CRS 개정 후 제출 | 2024-03-14 | N/A | DHI-GUP-DT-21-028 | 2021-09-17 | A | CRS-GUP-DHI-DT-21-035 | 2021-10-06 | RR | DHI-GUP-DT-21-099 | 2021-11-11 | B | CRS-GUP-DHI-DT-21-074 | 2021-11-30 | RC | DHI-GUP-DT-22-007 | 2022-01-07 | C | CRS-GUP-DHI-DT-21-172 | 2022-01-24 | RC | DHI-GUP-DT-22-082 | 2022-02-18 | D | CRS-GUP-DHI-DT-22-248 | 2022-03-14 | RC | DHI-GUP-DT-22-210 | 2022-05-10 | E | CRS-GUP-DHI-DT-22-392 | 2022-06-07 | AC | DE-GUP-DT-E-22-524 | 2022-08-19 | F | CRS-GUP-DHI-DT-22-697 | 2022-08-29 | AC | DE-GUP-DT-E-22-1037 | 2022-12-06 | 0(CP) | CRS-GUP-DHI-DT-22-1391 | 2023-01-05 | AA | DE-GUP-DT-E-23-898 | 2023-11-09 | 1 | 자체 CRS 개정 후 제출 | 2024-03-14 | N/A | DE-GUP-DT-E-24-077 | 2024-03-15 | 2
| GUP | YK09 | P1 | GKB | 434002 |  | GUP-YK09-P1GKB-434002 | POTABLE WATER STORAGE TANK_NOZZLE ORIENTATION DRAWING | FI | 2021-11-03 |  | Water EPC프로세스기술팀(Mech.) | 박상익 |  | P |  |  |  | CCPP | PW Tank | Mech. | 3 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-077 | 2024-03-15 | 7 | 자체 CRS 개정 후 제출 | 2024-03-14 | N/A | DHI-GUP-DT-21-028 | 2021-09-17 | 0 | CRS-GUP-DHI-DT-21-035 | 2021-10-06 | NC | DHI-GUP-DT-21-099 | 2021-11-11 | 1 | CRS-GUP-DHI-DT-21-074 | 2021-11-30 | I | DHI-GUP-DT-22-007 | 2022-01-07 | 2 | CRS-GUP-DHI-DT-21-172 | 2022-01-24 | I | DHI-GUP-DT-22-210 | 2022-05-10 | 3 | CRS-GUP-DHI-DT-22-392 | 2022-06-07 | NC | DE-GUP-DT-E-22-524 | 2022-08-19 | 4 | CRS-GUP-DHI-DT-22-697 | 2022-08-29 | NC | DE-GUP-DT-E-22-1037 | 2022-12-06 | 5 | CRS-GUP-DHI-DT-22-1391 | 2023-01-05 | NC | DE-GUP-DT-E-23-898 | 2023-11-09 | 6 | 자체 CRS 개정 후 제출 | 2024-03-14 | N/A | DE-GUP-DT-E-24-077 | 2024-03-15 | 7
| GUP | YK09 | P1 | GKB | 434003 |  | GUP-YK09-P1GKB-434003 | POTABLE WATER STORAGE TANK_NAME PLATE DRAWING | FI | 2022-07-12 |  | Water EPC프로세스기술팀(Mech.) | 박상익 | [5 empty] | CCPP | PW Tank | Mech. | 4 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-22-1037 | 2022-12-06 | 0 | CRS-GUP-DHI-DT-22-1391 | 2023-01-05 | NC | DE-GUP-DT-E-22-1037 | 2022-12-06 | 0 | CRS-GUP-DHI-DT-22-1391 | 2023-01-05 | NC
| GUP | XW03 | P1 | GKB | 434101 |  | GUP-XW03-P1GKB-434101 | POTABLE WATER STORAGE TANK_MECHANICAL STRENGTH CALCULATION | FI | 2022-02-26 |  | Water EPC프로세스기술팀(Mech.) | 박상익 |  | P |  |  |  | CCPP | PW Tank | Mech. | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-078 | 2024-03-15 | 2 | CRS-GUP-DHI-DT-22-1018 | 2022-11-13 | NC | DHI-GUP-DT-21-099 | 2021-11-11 | 0 | CRS-GUP-DHI-DT-21-074 | 2021-11-30 | NC | DE-GUP-DT-E-22-856 | 2022-10-26 | 1 | CRS-GUP-DHI-DT-22-1018 | 2022-11-13 | NC | DE-GUP-DT-E-24-078 | 2024-03-15 | 2
| GUP | YK09 | P1 | GKB | 434202 |  | GUP-YK09-P1GKB-434202 | POTABLE WATER STORAGE TANK_DETAIL DRAWINGS FOR CATHODIC PROTECTION SYSTEM | FI | 2022-07-25 |  | Water EPC프로세스기술팀(Mech.) | 박상익 | [5 empty] | CCPP | ULSD Tank | Elec. | 4 | 2025-06-30 |  |  | DE-GUP-DT-E-24-068 | 2024-03-07 | 2 | CRS-GUP-DHI-DT-23-1774 | 2023-03-27 | NC | DE-GUP-DT-E-22-576 | 2022-08-30 | 0 | CRS-GUP-DHI-DT-22-868 | 2022-10-09 | RC | DE-GUP-DT-E-23-274 | 2023-03-07 | 1 | CRS-GUP-DHI-DT-23-1774 | 2023-03-27 | NC | DE-GUP-DT-E-24-068 | 2024-03-07 | 2
| GUP | YK10 | P1 | GKB | 435001 |  | GUP-YK10-P1GKB-435001 | FIREFIGHTING WATER STORAGE TANK_GENERAL ARRANGEMENT DRAWING | FA | 2022-08-01 | 2022-10-31 | Water EPC프로세스기술팀(Mech.) | 박상익 | B | P |  |  |  | CCPP | FF Tank | Mech. | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-077 | 2024-03-15 | 1 | CRS-GUP-DHI-DT-23-1514 | 2023-02-14 | AA | DHI-GUP-DT-22-221 | 2022-05-16 | A | CRS-GUP-DHI-DT-22-432 | 2022-06-15 | RC | DE-GUP-DT-E-22-545 | 2022-08-24 | B | CRS-GUP-DHI-DT-22-783 | 2022-09-19 | RC | DE-GUP-DT-E-22-988 | 2022-11-25 | C | CRS-GUP-DHI-DT-22-1302 | 2022-12-21 | AA | DE-GUP-DT-E-22-1233 | 2023-01-06 | 0 | CRS-GUP-DHI-DT-23-1514 | 2023-02-14 | AA | DE-GUP-DT-E-24-077 | 2024-03-15 | 1
| GUP | YK09 | P1 | GKB | 435002 |  | GUP-YK09-P1GKB-435002 | FIREFIGHTING WATER STORAGE TANK_NOZZLE ORIENTATION DRAWING | FI | 2022-08-01 |  | Water EPC프로세스기술팀(Mech.) | 박상익 |  | P |  |  |  | CCPP | FF Tank | Mech. | 3 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-077 | 2024-03-15 | 4 | 자체 CRS 개정 후 제출 | 2023-11-08 | N/A | DHI-GUP-DT-22-221 | 2022-05-16 | 0 | CRS-GUP-DHI-DT-22-432 | 2022-06-15 | NC | DE-GUP-DT-E-22-545 | 2022-08-24 | 1 | CRS-GUP-DHI-DT-22-783 | 2022-09-19 | NC | DE-GUP-DT-E-22-988 | 2022-11-25 | 2 | CRS-GUP-DHI-DT-22-1207 | 2022-11-30 | NC | DE-GUP-DT-E-23-898 | 2023-11-09 | 3 | 자체 CRS 개정 후 제출 | 2023-11-08 | N/A | DE-GUP-DT-E-24-077 | 2024-03-15 | 4
| GUP | YK09 | P1 | GKB | 435003 |  | GUP-YK09-P1GKB-435003 | FIREFIGHTING WATER STORAGE TANK_NAME PLATE DRAWING | FI | 2022-12-03 |  | Water EPC프로세스기술팀(Mech.) | 박상익 | [5 empty] | CCPP | FF Tank | Mech. | 4 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-22-1244 | 2023-01-10 | 0 | CRS-GUP-DHI-DT-23-1515 | 2023-02-14 | NC | DE-GUP-DT-E-22-1244 | 2023-01-10 | 0 | CRS-GUP-DHI-DT-23-1515 | 2023-02-14 | NC
| GUP | XW03 | P1 | GKB | 435101 |  | GUP-XW03-P1GKB-435101 | FIREFIGHTING WATER STORAGE TANK_MECHANICAL STRENGTH CALCULATION | FI | 2022-08-01 |  | Water EPC프로세스기술팀(Mech.) | 박상익 |  | P |  |  |  | CCPP | FF Tank | Mech. | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-079 | 2024-03-15 | 1 | CRS-GUP-DHI-DT-22-741 | 2022-09-12 | NC | DE-GUP-DT-E-22-540 | 2022-08-23 | 0 | CRS-GUP-DHI-DT-22-741 | 2022-09-12 | NC | DE-GUP-DT-E-24-079 | 2024-03-15 | 1
| GUP | YK09 | P1 | GKB | 435202 |  | GUP-YK09-P1GKB-435202 | FIREFIGHTING WATER STORAGE TANK_DETAIL DRAWINGS FOR CATHODIC PROTECTION SYSTEM | FI | 2022-07-25 |  | Water EPC프로세스기술팀(Mech.) | 박상익 | [5 empty] | CCPP | ULSD Tank | Elec. | 4 | 2025-06-30 |  |  | DE-GUP-DT-E-23-274 | 2023-03-07 | 1 | CRS-GUP-DHI-DT-23-1774 | 2023-03-27 | NC | DE-GUP-DT-E-22-576 | 2022-08-30 | 0 | CRS-GUP-DHI-DT-22-868 | 2022-10-09 | RC | DE-GUP-DT-E-23-274 | 2023-03-07 | 1 | CRS-GUP-DHI-DT-23-1774 | 2023-03-27 | NC
| GUP | YR02 | P1 | LYA | 436201 |  | GUP-YR02-P1LYA-436201 | TECHNICAL SPECIFICATION OF CATHODIC PROTECTION SYSTEM FOR FIELD ERECTION TANKS | FI | 2022-07-08 |  | Water EPC프로세스기술팀(Mech.) | 박상익 | [5 empty] | CCPP | ULSD Tank | Elec. | 4 | 2025-06-30 |  |  | DE-GUP-DT-E-22-370 | 2022-07-07 | 0 | CRS-GUP-DHI-DT-22-607 | 2022-08-16 | NC | DE-GUP-DT-E-22-370 | 2022-07-07 | 0 | CRS-GUP-DHI-DT-22-607 | 2022-08-16 | NC
| GUP | XW01 | P1 | GHD | 120501 |  | GUP-XW01-P1GHD-120501 | SERVICE WATER SYSTEM_DESIGN CRITERIA | FA | 2021-07-09 | 2022-06-18 | 플랜트기술팀(Mech.) | 조상환 |  | P |  |  |  | CCPP | Service Water | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-22-390 | 2022-07-13 | 0 | CRS-GUP-DHI-DT-21-144 | 2022-01-12 | AA | DHI-GUP-DT-21-007 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-016 | 2021-09-29 | RC | DHI-GUP-DT-21-153 | 2021-12-08 | B | CRS-GUP-DHI-DT-21-144 | 2022-01-12 | AA | DE-GUP-DT-E-22-390 | 2022-07-13 | 0
| GUP | XG02 | P1 | GHD | 120502 |  | GUP-XG02-P1GHD-120502 | SERVICE WATER SYSTEM_P&I DIAGRAM | FA | 2021-06-01 | 2022-06-18 | 플랜트기술팀(Mech.) | 조상환 | [5 empty] | CCPP | Service Water | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-005 | 2024-01-05 | 1 | 자체 CRS 개정 후 제출 | 2024-01-04 | N/A | DHI-GUP-DT-21-003 | 2021-05-28 | A | N/A | 2021-12-07 | N/A | DHI-GUP-DT-21-153 | 2021-12-08 | B | CRS-GUP-DHI-DT-21-144 | 2022-01-12 | RC | DHI-GUP-DT-22-099 | 2022-03-07 | C | CRS-GUP-DHI-DT-22-265 | 2022-03-29 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-390 | 2022-07-13 | 0(CP) | 자체 CRS 개정 후 제출 | 2024-01-04 | N/A | DE-GUP-DT-E-24-005 | 2024-01-05 | 1
| GUP | XS00 | P1 | GHD | 120503 |  | GUP-XS00-P1GHD-120503 | SERVICE WATER SYSTEM_SYSTEM DESCRIPTION | FA | 2021-07-06 | 2022-06-18 | 플랜트기술팀(Mech.) | 조상환 |  | P |  |  |  | CCPP | Service Water | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-005 | 2024-01-05 | 1 | 자체 CRS 개정 후 제출 | 2024-01-04 | N/A | DHI-GUP-DT-21-008 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-034 | 2021-10-06 | RC | DHI-GUP-DT-21-153 | 2021-12-08 | B | CRS-GUP-DHI-DT-21-144 | 2022-01-12 | AC | DHI-GUP-DT-22-099 | 2022-03-07 | C | CRS-GUP-DHI-DT-22-265 | 2022-03-29 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-390 | 2022-07-13 | 0(CP) | 자체 CRS 개정 후 제출 | 2024-01-04 | N/A | DE-GUP-DT-E-24-005 | 2024-01-05 | 1
| GUP | XW01 | P1 | SCA | 120504 |  | GUP-XW01-P1SCA-120504 | AIR COMPRESSOR_DESIGN CRITERIA | FA | 2021-09-09 | 2022-08-15 | 플랜트기술팀(Mech.) | 조상환 |  | P |  |  |  | CCPP | Air Comp. | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-172 | 2024-07-02 | 3 | CRS-GUP-DHI-DT-24-033 | 2024-03-12 | AA | DHI-GUP-DT-21-034 | 2021-09-17 | A | CRS-GUP-DHI-DT-21-030 | 2021-10-06 | RC | DHI-GUP-DT-21-198 | 2021-12-24 | B | CRS-GUP-DHI-DT-21-163 | 2022-01-17 | RC | DHI-GUP-DT-22-094 | 2022-02-25 | C | CRS-GUP-DHI-DT-22-257 | 2022-03-16 | RC | DE-GUP-DT-E-22-252 | 2022-05-27 | D | CRS-GUP-DHI-DT-22-453 | 2022-06-21 | AC | DE-GUP-DT-E-22-491 | 2022-08-10 | 0(CP) | CRS-GUP-DHI-DT-22-708 | 2022-09-05 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-1144 | 2022-12-21 | 1(CP) | 자체 CRS 개정 후 제출 | 2023-11-22 | N/A | DE-GUP-DT-E-23-941 | 2023-11-23 | 2(CP) | CRS-GUP-DHI-DT-24-033 | 2024-03-12 | AA | DE-GUP-DT-E-24-172 | 2024-07-02 | 3
| GUP | XG01 | P1 | SCA | 120505 |  | GUP-XG01-P1SCA-120505 | COMPRESSED AIR SYSTEM_P&I DIAGRAM | FA | 2021-06-01 | 2022-08-15 | 플랜트기술팀(Mech.) | 조상환 | [5 empty] | CCPP | Air Comp. | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-167 | 2024-06-28 | 2 | CRS-GUP-DHI-DT-25-051 | 2025-03-19 | AA | DHI-GUP-DT-21-003 | 2021-05-28 | A | CRS-GUP-DHI-DT-21-030 | 2021-10-06 | RC | DHI-GUP-DT-21-198 | 2021-12-24 | B | CRS-GUP-DHI-DT-21-163 | 2022-01-17 | RC | DHI-GUP-DT-22-094 | 2022-02-25 | C | CRS-GUP-DHI-DT-22-257 | 2022-03-16 | RC | DE-GUP-DT-E-22-252 | 2022-05-27 | D | CRS-GUP-DHI-DT-22-453 | 2022-06-21 | AC | DE-GUP-DT-E-22-491 | 2022-08-10 | 0(CP) | CRS-GUP-DHI-DT-22-708 | 2022-09-05 | AC | DE-GUP-DT-E-23-941 | 2023-11-23 | 1(CP) | CRS-GUP-DHI-DT-24-033 | 2024-03-12 | AC | DE-GUP-DT-E-24-167 | 2024-06-28 | 2 | CRS-GUP-DHI-DT-25-051 | 2025-03-19 | AA
| GUP | XG01 | P1 | QFB | 120506 |  | GUP-XG01-P1QFB-120506 | INSTRUMENT AIR SYSTEM_P&I DIAGRAM | FA | 2021-06-01 | 2022-05-19 | 플랜트기술팀(Mech.) | 조상환 | [5 empty] | CCPP | Air Comp. | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-167 | 2024-06-28 | 3 | CRS-GUP-DHI-DT-25-051 | 2025-03-19 | AA | DHI-GUP-DT-21-003 | 2021-05-28 | A | CRS-GUP-DHI-DT-21-030 | 2021-10-06 | RC | DHI-GUP-DT-21-198 | 2021-12-24 | B | CRS-GUP-DHI-DT-21-163 | 2022-01-17 | AC | DHI-GUP-DT-22-094 | 2022-02-25 | C | CRS-GUP-DHI-DT-22-257 | 2022-03-16 | AC | DE-GUP-DT-E-22-252 | 2022-05-27 | 0 | CRS-GUP-DHI-DT-22-453 | 2022-06-21 | AA | DE-GUP-DT-E-22-491 | 2022-08-10 | 1 | CRS-GUP-DHI-DT-22-708 | 2022-09-05 | AC | DE-GUP-DT-E-23-941 | 2023-11-23 | 2 | CRS-GUP-DHI-DT-24-033 | 2024-03-12 | AC | DE-GUP-DT-E-24-167 | 2024-06-28 | 3 | CRS-GUP-DHI-DT-25-051 | 2025-03-19 | AA
| GUP | XG01 | P1 | SCB | 120507 |  | GUP-XG01-P1SCB-120507 | SERVICE AIR SYSTEM_P&I DIAGRAM | FA | 2021-06-01 | 2022-05-19 | 플랜트기술팀(Mech.) | 조상환 | [5 empty] | CCPP | Air Comp. | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-167 | 2024-06-28 | 3 | CRS-GUP-DHI-DT-25-051 | 2025-03-19 | AA | DHI-GUP-DT-21-003 | 2021-05-28 | A | CRS-GUP-DHI-DT-21-030 | 2021-10-06 | RC | DHI-GUP-DT-21-198 | 2021-12-24 | B | CRS-GUP-DHI-DT-21-163 | 2022-01-17 | AC | DHI-GUP-DT-22-094 | 2022-02-25 | C | CRS-GUP-DHI-DT-22-257 | 2022-03-16 | AC | DE-GUP-DT-E-22-252 | 2022-05-27 | 0 | CRS-GUP-DHI-DT-22-453 | 2022-06-21 | AA | DE-GUP-DT-E-22-491 | 2022-08-10 | 1 | CRS-GUP-DHI-DT-22-708 | 2022-09-05 | AC | DE-GUP-DT-E-23-941 | 2023-11-23 | 2 | CRS-GUP-DHI-DT-24-033 | 2024-03-12 | AC | DE-GUP-DT-E-24-167 | 2024-06-28 | 3 | CRS-GUP-DHI-DT-25-051 | 2025-03-19 | AA
| GUP | XS00 | P1 | SCA | 120508 |  | GUP-XS00-P1SCA-120508 | AIR COMPRESSOR_SYSTEM DESCRIPTION | FA | 2021-09-09 | 2022-05-19 | 플랜트기술팀(Mech.) | 조상환 |  | P |  |  |  | CCPP | Air Comp. | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-172 | 2024-07-02 | 4 | CRS-GUP-DHI-DT-24-033 | 2024-03-12 | AA | DHI-GUP-DT-21-034 | 2021-09-17 | A | CRS-GUP-DHI-DT-21-030 | 2021-10-06 | RC | DHI-GUP-DT-21-198 | 2021-12-24 | B | CRS-GUP-DHI-DT-21-163 | 2022-01-17 | AC | DHI-GUP-DT-22-094 | 2022-02-25 | C | CRS-GUP-DHI-DT-22-257 | 2022-03-16 | AC | DE-GUP-DT-E-22-252 | 2022-05-27 | 0 | CRS-GUP-DHI-DT-22-453 | 2022-06-21 | AC | DE-GUP-DT-E-22-491 | 2022-08-10 | 1(CP) | CRS-GUP-DHI-DT-22-708 | 2022-09-05 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-1144 | 2022-12-21 | 2(CP) | 자체 CRS 개정 후 제출 | 2023-11-22 | N/A | DE-GUP-DT-E-23-941 | 2023-11-23 | 3(CP) | CRS-GUP-DHI-DT-24-033 | 2024-03-12 | AA | DE-GUP-DT-E-24-172 | 2024-07-02 | 4
| GUP | YD00 | P1 | GM | 120509 |  | GUP-YD00-P1GM-120509 | SUMP PUMP_PUMP ARRANGEMENT DRAWING | FI | 2022-10-25 |  | 플랜트기술팀(Mech.) | 조상환 |  | R |  |  | Sump pump | CCPP | Sump pump | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-520 | 2023-04-28 | 0 | CRS-GUP-DHI-DT-23-1934 | 2023-05-05 | NC | DE-GUP-DT-E-23-142 | 2023-02-08 | 0 | CRS-GUP-DHI-DT-23-1629 | 2023-03-02 | NC | DE-GUP-DT-E-23-520 | 2023-04-28 |  | CRS-GUP-DHI-DT-23-1934 | 2023-05-05 | NC
| GUP | YT01 | P1 | GM | 120510 |  | GUP-YT01-P1GM-120510 | SUMP PUMP_PUMP DATA SHEET & CHARACTERISTIC CURVE | FA | 2022-10-25 | 2023-02-25 | 플랜트기술팀(Mech.) | 조상환 |  |  |  |  | Sump pump | CCPP | Sump pump | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-630 | 2023-06-20 | 1 | 자체 CRS 개정 후 제출 | 2023-03-02 | N/A | DE-GUP-DT-E-23-110 | 2023-02-03 | A | 자체 CRS 개정 후 제출 | 2023-03-02 | N/A | DE-GUP-DT-E-23-303 | 2023-03-13 | 0 | 자체 CRS 개정 후 제출 | 2023-03-02 | N/A | DE-GUP-DT-E-23-630 | 2023-06-20 | 1
| GUP | YM01 | P1 | GM | 120511 |  | GUP-YM01-P1GM-120511 | SUMP PUMP_MOTOR DATA SHEET & CHARACTERISTIC CURVE | FI | 2022-11-25 |  | 플랜트기술팀(Mech.) | 조상환 |  |  |  |  | Sump pump | CCPP | Sump pump | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-110 | 2023-02-03 | 0 | CRS-GUP-DHI-DT-23-1616 | 2023-03-02 | NC | DE-GUP-DT-E-23-110 | 2023-02-03 | 0 | CRS-GUP-DHI-DT-23-1616 | 2023-03-02 | NC
| GUP | YT01 | P1 | GM | 120512 |  | GUP-YT01-P1GM-120512 | SUMP PUMP_MOTOR OUTLINE, TERMINAL BOX, NAME PLATE DRAWING | FI | 2022-11-25 |  | 플랜트기술팀(Mech.) | 조상환 |  |  |  |  | Sump pump | CCPP | Sump pump | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-110 | 2023-02-03 | 0 | CRS-GUP-DHI-DT-23-1616 | 2023-03-02 | NC | DE-GUP-DT-E-23-110 | 2023-02-03 | 0 | CRS-GUP-DHI-DT-23-1616 | 2023-03-02 | NC
| GUP | YL01 | P1 | GM | 120513 |  | GUP-YL01-P1GM-120513 | SUMP PUMP_INSTRUMENT LIST | FI | 2022-11-25 |  | 플랜트기술팀(Mech.) | 조상환 |  | R |  |  | Sump pump | CCPP | Sump pump | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-829 | 2023-09-26 | 1 | CRS-GUP-DHI-DT-23-1711 | 2023-03-14 | NC | DE-GUP-DT-E-23-259 | 2023-02-28 | 0 | CRS-GUP-DHI-DT-23-1711 | 2023-03-14 | NC | DE-GUP-DT-E-23-829 | 2023-09-26 | 1
| GUP | YL22 | P1 | GM | 120514 |  | GUP-YL22-P1GM-120514 | SUMP PUMP_NAME PLATE DRAWING | FI | 2022-11-25 |  | 플랜트기술팀(Mech.) | 조상환 |  |  |  |  | Sump pump | CCPP | Sump pump | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-259 | 2023-02-28 | 0 | CRS-GUP-DHI-DT-23-1711 | 2023-03-14 | NC | DE-GUP-DT-E-23-259 | 2023-02-28 | 0 | CRS-GUP-DHI-DT-23-1711 | 2023-03-14 | NC
| GUP | YR05 | P1 | GM | 120516 |  | GUP-YR05-P1GM-120516 | SUMP PUMP_LOCAL PANEL SCHEMATIC DIAGRAM & OUTLINE DRAWING | FI | 2022-12-25 |  | 플랜트기술팀(Mech.) | 조상환 |  |  |  |  | Sump pump | CCPP | Sump pump | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-292 | 2024-12-11 | 2 | CRS-GUP-DHI-DT-23-2100 | 2023-08-22 | NC | DE-GUP-DT-E-23-194 | 2023-02-17 | 0 | CRS-GUP-DHI-DT-23-1687 | 2023-03-14 | NC | DE-GUP-DT-E-23-741 | 2023-08-16 | 1 | CRS-GUP-DHI-DT-23-2100 | 2023-08-22 | NC | DE-GUP-DT-E-24-292 | 2024-12-11 | 2
| GUP | YK00 | P1 | GM | 120530 |  | GUP-YK00-P1GM-120530 | SUMP PUMP_INSTRUMENTATION HOOK-UP DRAWING | FI | 2023-03-08 |  | 플랜트기술팀(Mech.) | 조상환 |  |  |  |  | Sump pump | CCPP | Sump pump | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-416 | 2023-04-04 | 0 | CRS-GUP-DHI-DT-23-1862 | 2023-04-19 | NC | DE-GUP-DT-E-23-416 | 2023-04-04 | 0 | CRS-GUP-DHI-DT-23-1862 | 2023-04-19 | NC
| GUP | YL01 | P1 | GM | 120531 |  | GUP-YL01-P1GM-120531 | SUMP PUMP_IO LIST | FI | 2023-03-01 |  | 플랜트기술팀(Mech.) | 조상환 |  |  |  |  | Sump pump | CCPP | Sump pump | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-225 | 2023-02-22 | 0 | CRS-GUP-DHI-DT-23-1700 | 2023-03-14 | NC | DE-GUP-DT-E-23-225 | 2023-02-22 | 0 | CRS-GUP-DHI-DT-23-1700 | 2023-03-14 | NC
| GUP | YT01 | P1 | GM | 120532 |  | GUP-YT01-P1GM-120532 | SUMP PUMP_INSTRUMENT DATA SHEET | FI | 2023-03-01 |  | 플랜트기술팀(Mech.) | 조상환 |  |  |  |  | Sump pump | CCPP | Sump pump | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-259 | 2023-02-28 | 0 | CRS-GUP-DHI-DT-23-1711 | 2023-03-14 | NC | DE-GUP-DT-E-23-259 | 2023-02-28 | 0 | CRS-GUP-DHI-DT-23-1711 | 2023-03-14 | NC
| GUP | YK01 | P1 | GM | 120533 |  | GUP-YK01-P1GM-120533 | SUMP PUMP_SECTIONAL DRAWING | FI | 2023-03-01 |  | 플랜트기술팀(Mech.) | 조상환 |  |  |  |  | Sump pump | CCPP | Sump pump | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-259 | 2023-02-28 | 0 | CRS-GUP-DHI-DT-23-1711 | 2023-03-14 | NC | DE-GUP-DT-E-23-259 | 2023-02-28 | 0 | CRS-GUP-DHI-DT-23-1711 | 2023-03-14 | NC
| GUP | CQ02 | P1 | GM | 120534 |  | GUP-CQ02-P1GM-120534 | SUMP PUMP_OPERATION & MAINTENANCE (O&M) MANUAL | FI | 2023-07-28 |  | 플랜트기술팀(Mech.) | 조상환 |  |  |  |  | Sump pump | CCPP | Sump pump | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-828 | 2023-09-26 | 0 | CRS-GUP-DHI-DT-23-2122 | 2023-10-26 | NC | DE-GUP-DT-E-23-828 | 2023-09-26 | 0 | CRS-GUP-DHI-DT-23-2122 | 2023-10-26 | NC
| GUP | XW01 | P0 | GM | 120517 |  | GUP-XW01-P0GM-120517 | WASTE WATER TRANSFER SYSTEM_DESIGN CRITERIA | FA | 2021-08-31 | 2022-08-15 | 플랜트기술팀(Mech.) | 조상환 |  | P | G | FI |  | CCPP | Waste Water Transfer | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-904 | 2023-11-10 | 1 | 자체 CRS 개정 후 제출 | 2023-11-09 | N/A | DHI-GUP-DT-21-007 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-019 | 2021-09-29 | RC | DHI-GUP-DT-22-031 | 2022-01-24 | B | CRS-GUP-DHI-DT-21-202 | 2022-02-13 | RC | DE-GUP-DT-E-22-234 | 2022-05-20 | C | CRS-GUP-DHI-DT-22-403 | 2022-06-09 | RC | DE-GUP-DT-E-22-396 | 2022-07-13 | D | CRS-GUP-DHI-DT-22-611 | 2022-08-16 | RC | DE-GUP-DT-E-22-1035 | 2022-12-06 | E | CRS-GUP-DHI-DT-22-1287 | 2022-12-21 | AA | DE-GUP-DT-E-23-015 | 2023-01-12 | 0 | 자체 CRS 개정 후 제출 | 2023-11-09 | N/A | DE-GUP-DT-E-23-904 | 2023-11-10 | 1
| GUP | XG02 | P0 | GM | 120518 |  | GUP-XG02-P0GM-120518 | WASTE WATER TRANSFER SYSTEM_P&I DIAGRAM | FA | 2021-06-01 | 2022-08-15 | 플랜트기술팀(Mech.) | 조상환 |  |  | G | FI |  | CCPP | Waste Water Transfer | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-257 | 2024-10-31 | 2 | 자체 CRS 개정 후 제출 | 2024-10-30 | N/A | DHI-GUP-DT-21-003 | 2021-05-28 | A | CRS-GUP-DHI-DT-21-019 | 2021-09-29 | RC | DHI-GUP-DT-22-031 | 2022-01-24 | B | CRS-GUP-DHI-DT-21-202 | 2022-02-13 | RC | DE-GUP-DT-E-22-234 | 2022-05-20 | C | CRS-GUP-DHI-DT-22-403 | 2022-06-09 | RC | DE-GUP-DT-E-22-396 | 2022-07-13 | D | CRS-GUP-DHI-DT-22-611 | 2022-08-16 | RC | DE-GUP-DT-E-22-1035 | 2022-12-06 | E | CRS-GUP-DHI-DT-22-1287 | 2022-12-21 | AA | DE-GUP-DT-E-23-015 | 2023-01-12 | 0 | 자체 CRS 개정 후 제출 | 2023-11-09 | N/A | DE-GUP-DT-E-23-904 | 2023-11-10 | 1 | 자체 CRS 개정 후 제출 | 2024-10-30 | N/A | DE-GUP-DT-E-24-257 | 2024-10-31 | 2
| GUP | XS00 | P0 | GM | 120519 |  | GUP-XS00-P0GM-120519 | WASTE WATER TRANSFER SYSTEM_SYSTEM DESCRIPTION | FA | 2021-08-31 | 2022-08-15 | 플랜트기술팀(Mech.) | 조상환 |  | P | G | FI |  | CCPP | Waste Water Transfer | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-904 | 2023-11-10 | 1 | 자체 CRS 개정 후 제출 | 2023-11-09 | N/A | DHI-GUP-DT-21-024 | 2021-09-16 | A | CRS-GUP-DHI-DT-21-019 | 2021-09-29 | RC | DHI-GUP-DT-22-031 | 2022-01-24 | B | CRS-GUP-DHI-DT-21-202 | 2022-02-13 | RC | DE-GUP-DT-E-22-234 | 2022-05-20 | C | CRS-GUP-DHI-DT-22-403 | 2022-06-09 | RC | DE-GUP-DT-E-22-396 | 2022-07-13 | D | CRS-GUP-DHI-DT-22-611 | 2022-08-16 | RC | DE-GUP-DT-E-22-1035 | 2022-12-06 | E | CRS-GUP-DHI-DT-22-1287 | 2022-12-21 | AA | DE-GUP-DT-E-23-015 | 2023-01-12 | 0 | 자체 CRS 개정 후 제출 | 2023-11-09 | N/A | DE-GUP-DT-E-23-904 | 2023-11-10 | 1
| GUP | XG07 | P0 | ZEN | 120520 |  | GUP-XG07-P0ZEN-120520 | WATER BALANCE DIAGRAM | FA | 2021-06-01 | 2022-06-18 | 플랜트기술팀(Mech.) | 조상환 |  | P | G | FI |  | CCPP | Plant | General | 1 | 2025-06-30 |  |  | DE-GUP-DT-E-23-409 | 2023-03-31 | 1 | CRS-GUP-DHI-DT-22-462 | 2022-06-21 | AA | DHI-GUP-DT-21-059 | 2021-10-08 | A | CRS-GUP-DHI-DT-21-044 | 2021-10-29 | RC | DHI-GUP-DT-21-186 | 2021-12-17 | B | CRS-GUP-DHI-DT-21-137 | 2022-01-11 | RC | DHI-GUP-DT-22-068 | 2022-02-14 | C | CRS-GUP-DHI-DT-22-230 | 2022-03-07 | RC | DHI-GUP-DT-22-182 | 2022-04-20 | D | CRS-GUP-DHI-DT-22-355 | 2022-05-19 | AC | DE-GUP-DT-E-22-276 | 2022-06-08 | 0 | CRS-GUP-DHI-DT-22-462 | 2022-06-21 | AA | DE-GUP-DT-E-23-409 | 2023-03-31 | 1
| GUP | XG08 | P1 | SCA | 120521 |  | GUP-XG08-P1SCA-120521 | AIR COMPRESSOR SYSTEM_PROCESS FLOW DIAGRAM | FA | 2021-09-17 | 2022-08-15 | 플랜트기술팀(Mech.) | 조상환 |  | R |  |  | AIR COMP. | CCPP | Air Comp. | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-941 | 2023-11-23 | 2 | CRS-GUP-DHI-DT-24-033 | 2024-03-12 | AA | DHI-GUP-DT-21-034 | 2021-09-17 | A | N/A | 2021-12-23 | N/A | DHI-GUP-DT-21-198 | 2021-12-24 | B | CRS-GUP-DHI-DT-21-163 | 2022-01-17 | AC | DHI-GUP-DT-22-094 | 2022-02-25 | C | CRS-GUP-DHI-DT-22-257 | 2022-03-16 | RC | DE-GUP-DT-E-22-252 | 2022-05-27 | D | CRS-GUP-DHI-DT-22-453 | 2022-06-21 | AA | DE-GUP-DT-E-22-491 | 2022-08-10 | 0 | CRS-GUP-DHI-DT-22-708 | 2022-09-05 | AC | DE-GUP-DT-E-22-1144 | 2022-12-21 | 1 | 자체 CRS 개정 후 제출 | 2023-11-22 | N/A | DE-GUP-DT-E-23-941 | 2023-11-23 | 2 | CRS-GUP-DHI-DT-24-033 | 2024-03-12 | AA
| GUP | XG08 | P1 | GHD | 120522 |  | GUP-XG08-P1GHD-120522 | SERVICE WATER SYSTEM_PROCESS FLOW DIAGRAM | FA | 2021-09-17 | 2022-08-15 | 플랜트기술팀(Mech.) | 조상환 |  | P |  |  | SERVICE WATER | CCPP | Service Water | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-005 | 2024-01-05 | 1 | 자체 CRS 개정 후 제출 | 2024-01-04 | N/A | DHI-GUP-DT-21-034 | 2021-09-17 | A | N/A | 2021-12-07 | N/A | DHI-GUP-DT-21-153 | 2021-12-08 | B | CRS-GUP-DHI-DT-21-144 | 2022-01-12 | RC | DHI-GUP-DT-22-099 | 2022-03-07 | C | CRS-GUP-DHI-DT-22-265 | 2022-03-29 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-390 | 2022-07-13 | 0(CP) | 자체 CRS 개정 후 제출 | 2024-01-04 | N/A | DE-GUP-DT-E-24-005 | 2024-01-05 | 1
| GUP | XG08 | P0 | GKC | 120523 |  | GUP-XG08-P0GKC-120523 | POTABLE WATER SYSTEM_PROCESS FLOW DIAGRAM | FA | 2021-09-17 | 2022-06-18 | 플랜트기술팀(Mech.) | 조상환 |  | P | G | FI | POTABLE WATER | CCPP | Potable Water | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-993 | 2023-12-14 | 2 | CRS-GUP-DHI-DT-23-2138 | 2023-11-17 | AA | DHI-GUP-DT-21-034 | 2021-09-17 | A | N/A | 2021-11-28 | N/A | DHI-GUP-DT-21-125 | 2021-11-29 | B | CRS-GUP-DHI-DT-21-127 | 2022-01-11 | AC | DHI-GUP-DT-22-081 | 2022-02-18 | C | CRS-GUP-DHI-DT-22-247 | 2022-03-14 | RC | DE-GUP-DT-E-22-224 | 2022-05-18 | D | CRS-GUP-DHI-DT-22-374 | 2022-05-30 | AC | DE-GUP-DT-E-22-304 | 2022-06-16 | 0(CP) | CRS-GUP-DHI-DT-22-508 | 2022-07-11 | AC | DE-GUP-DT-E-23-864 | 2023-10-23 | 1(CP) | CRS-GUP-DHI-DT-23-2138 | 2023-11-17 | AA | DE-GUP-DT-E-23-993 | 2023-12-14 | 2
| GUP | XG08 | P0 | GM | 120524 |  | GUP-XG08-P0GM-120524 | WASTE WATER TRANSFER SYSTEM_PROCESS FLOW DIAGRAM | FA | 2021-09-15 | 2022-08-15 | 플랜트기술팀(Mech.) | 조상환 |  | P | G | FI | WASTE WATER TRANSFER | CCPP | Waste Water Transfer | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-257 | 2024-10-31 | 2 | 자체 CRS 개정 후 제출 | 2024-10-30 | N/A | DHI-GUP-DT-21-034 | 2021-09-17 | A | CRS-GUP-DHI-DT-21-019 | 2021-09-29 | RC | DHI-GUP-DT-22-031 | 2022-01-24 | B | CRS-GUP-DHI-DT-21-202 | 2022-02-13 | RC | DE-GUP-DT-E-22-234 | 2022-05-20 | C | CRS-GUP-DHI-DT-22-403 | 2022-06-09 | RC | DE-GUP-DT-E-22-396 | 2022-07-13 | D | CRS-GUP-DHI-DT-22-611 | 2022-08-16 | RC | DE-GUP-DT-E-22-1035 | 2022-12-06 | E | CRS-GUP-DHI-DT-22-1287 | 2022-12-21 | AA | DE-GUP-DT-E-23-015 | 2023-01-12 | 0 | 자체 CRS 개정 후 제출 | 2023-11-09 | N/A | DE-GUP-DT-E-23-904 | 2023-11-10 | 1 | 자체 CRS 개정 후 제출 | 2024-10-30 | N/A | DE-GUP-DT-E-24-257 | 2024-10-31 | 2
| GUP | YD00 | P1 | SCA | 120600 |  | GUP-YD00-P1SCA-120600 | AIR COMPRESSOR_EQUIPMENT GENERAL ARRANGEMENT | FA | 2022-07-31 | 2022-11-30 | 플랜트기술팀(Mech.) | 조상환 |  | R |  |  | AIR COMP. | CCPP | Air Comp. | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-700 | 2023-07-20 | 1 | 자체 CRS 개정 후 제출 | 2023-07-19 | N/A | DE-GUP-DT-E-22-714 | 2022-09-29 | A | CRS-GUP-DHI-DT-22-1048 | 2022-11-17 | RC | DE-GUP-DT-E-22-1049 | 2022-12-08 | B | CRS-GUP-DHI-DT-22-1290 | 2022-12-21 | RC | DE-GUP-DT-E-23-059 | 2023-01-19 | C | CRS-GUP-DHI-DT-23-1723 | 2023-03-17 | AA | DE-GUP-DT-E-23-397 | 2023-03-30 | 0 | 자체 CRS 개정 후 제출 | 2023-07-19 | N/A | DE-GUP-DT-E-23-700 | 2023-07-20 | 1
| GUP | XW01 | P1 | SCA | 120601 |  | GUP-XW01-P1SCA-120601 | AIR COMPRESSOR_TECHNICAL DESCRIPTION | FA | 2022-07-31 | 2022-11-30 | 플랜트기술팀(Mech.) | 조상환 |  | R |  |  | AIR COMP. | CCPP | Air Comp. | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-940 | 2023-11-23 | 1 | 자체 CRS 개정 후 제출 | 2023-11-22 | N/A | DE-GUP-DT-E-22-828 | 2022-10-20 | A | CRS-GUP-DHI-DT-22-1104 | 2022-11-21 | RC | DE-GUP-DT-E-22-1066 | 2022-12-09 | B | CRS-GUP-DHI-DT-22-1258 | 2022-12-13 | RC | DE-GUP-DT-E-22-1181 | 2022-12-23 | C | CRS-GUP-DHI-DT-22-1403 | 2023-01-07 | AA | DE-GUP-DT-E-23-083 | 2023-01-27 | 0 | 자체 CRS 개정 후 제출 | 2023-11-22 | N/A | DE-GUP-DT-E-23-940 | 2023-11-23 | 1
| GUP | YF00 | P1 | SCA | 120602 |  | GUP-YF00-P1SCA-120602 | AIR COMPRESSOR_CONTROL LOGIC AND LOOP DIAGRAM | FI | 2022-09-30 |  | 플랜트기술팀(Mech.) | 조상환 |  | R |  |  | AIR COMP. | CCPP | Air Comp. | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-700 | 2023-07-20 | 1 | CRS-GUP-DHI-DT-23-1574 | 2023-02-23 | NC | DE-GUP-DT-E-23-068 | 2023-01-20 | 0 | CRS-GUP-DHI-DT-23-1574 | 2023-02-23 | NC | DE-GUP-DT-E-23-700 | 2023-07-20 | 1
| GUP | YF02 | P1 | SCA | 120603 |  | GUP-YF02-P1SCA-120603 | AIR COMPRESSOR_CONTROL SYSTEM CONFIGURATION DRAWINGS | FA | 2022-09-30 | 2023-01-31 | 플랜트기술팀(Mech.) | 조상환 |  | R |  |  | AIR COMP. | CCPP | Air Comp. | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-136 | 2023-02-07 | 0 | CRS-GUP-DHI-DT-23-1627 | 2023-03-02 | AA | DE-GUP-DT-E-22-828 | 2022-10-20 | A | CRS-GUP-DHI-DT-22-1104 | 2022-11-21 | AA | DE-GUP-DT-E-23-136 | 2023-02-07 | 0 | CRS-GUP-DHI-DT-23-1627 | 2023-03-02 | AA
| GUP | YU03 | P1 | SCA | 120604 |  | GUP-YU03-P1SCA-120604 | AIR COMPRESSOR_ELECTRICAL SCHEMATIC DRAWINGS | FA | 2022-09-30 | 2023-01-31 | 플랜트기술팀(Mech.) | 조상환 |  | R |  |  | AIR COMP. | CCPP | Air Comp. | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-408 | 2023-03-31 | 0 | CRS-GUP-DHI-DT-23-1726 | 2023-03-17 | AA | DE-GUP-DT-E-23-136 | 2023-02-07 | A | CRS-GUP-DHI-DT-23-1726 | 2023-03-17 | AA | DE-GUP-DT-E-23-408 | 2023-03-31 | 0
| GUP | XF00 | P1 | SCA | 120605 |  | GUP-XF00-P1SCA-120605 | AIR COMPRESSOR_PLC GENERAL ARRANGEMENT DRAWING | FI | 2022-09-30 |  | 플랜트기술팀(Mech.) | 조상환 |  |  |  |  | AIR COMP. | CCPP | Air Comp. | I&C | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-562 | 2023-05-18 | 3 | CRS-GUP-DHI-DT-23-1978 | 2023-06-08 | NC | DE-GUP-DT-E-22-923 | 2022-11-08 | 0 | CRS-GUP-DHI-DT-22-1200 | 2022-11-30 | NC | DE-GUP-DT-E-23-136 | 2023-02-07 | 1 | CRS-GUP-DHI-DT-23-1591 | 2023-02-28 | NC | DE-GUP-DT-E-23-480 | 2023-04-20 | 2 | CRS-GUP-DHI-DT-23-1907 | 2023-05-05 | NC | DE-GUP-DT-E-23-562 | 2023-05-18 | 3 | CRS-GUP-DHI-DT-23-1978 | 2023-06-08 | NC
| GUP | YD00 | P1 | SCA | 120606 |  | GUP-YD00-P1SCA-120606 | AIR COMPRESSOR_ASSEMBLY & DIMENSIONAL DRAWING | FI | 2022-07-31 |  | 플랜트기술팀(Mech.) | 조상환 |  | R |  |  | AIR COMP. | CCPP | Air Comp. | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-561 | 2023-05-18 | 2 | CRS-GUP-DHI-DT-23-1977 | 2023-06-08 | NC | DE-GUP-DT-E-22-978 | 2022-11-23 | 0 | CRS-GUP-DHI-DT-22-1205 | 2022-11-30 | NC | DE-GUP-DT-E-23-246 | 2023-02-24 | 1 | CRS-GUP-DHI-DT-23-1707 | 2023-03-14 | NC | DE-GUP-DT-E-23-561 | 2023-05-18 | 2 | CRS-GUP-DHI-DT-23-1977 | 2023-06-08 | NC
| GUP | YL00 | P1 | SCA | 120607 |  | GUP-YL00-P1SCA-120607 | AIR COMPRESSOR_INSTRUMENT LIST&DATA SHEET | FI | 2022-09-30 |  | 플랜트기술팀(Mech.) | 조상환 |  | R |  |  | AIR COMP. | CCPP | Air Comp. | I&C | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-136 | 2023-02-07 | 0 | CRS-GUP-DHI-DT-23-1627 | 2023-03-02 | NC | DE-GUP-DT-E-23-136 | 2023-02-07 | 0 | CRS-GUP-DHI-DT-23-1627 | 2023-03-02 | NC
| GUP | YK00 | P1 | SCA | 120608 |  | GUP-YK00-P1SCA-120608 | AIR COMPRESSOR_INSTRUMENT INSTALLATION DRAWING | FI | 2022-09-30 |  | 플랜트기술팀(Mech.) | 조상환 |  |  |  |  | AIR COMP. | CCPP | Air Comp. | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-246 | 2023-02-24 | 0 | CRS-GUP-DHI-DT-23-1707 | 2023-03-14 | NC | DE-GUP-DT-E-23-246 | 2023-02-24 | 0 | CRS-GUP-DHI-DT-23-1707 | 2023-03-14 | NC
| GUP | YF03 | P1 | SCA | 120609 |  | GUP-YF03-P1SCA-120609 | AIR COMPRESSOR_PLC HMI GRAPHIC | FI | 2022-09-30 |  | 플랜트기술팀(Mech.) | 조상환 |  |  |  |  | AIR COMP. | CCPP | Air Comp. | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-701 | 2023-07-20 | 1 | CRS-GUP-DHI-DT-22-1258 | 2022-12-13 | NC | DE-GUP-DT-E-22-1066 | 2022-12-09 | 0 | CRS-GUP-DHI-DT-22-1258 | 2022-12-13 | NC | DE-GUP-DT-E-23-701 | 2023-07-20 | 1
| GUP | YD04 | P1 | SCA | 120610 |  | GUP-YD04-P1SCA-120610 | AIR COMPRESSOR_CABLE RACEWAY DRAWING | FI | 2022-09-30 |  | 플랜트기술팀(Mech.) | 조상환 |  |  |  |  | AIR COMP. | CCPP | Air Comp. | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-701 | 2023-07-20 | 2 | CRS-GUP-DHI-DT-23-1720 | 2023-03-14 | NC | DE-GUP-DT-E-23-136 | 2023-02-07 | 0 | CRS-GUP-DHI-DT-23-1627 | 2023-03-02 | NC | DE-GUP-DT-E-23-286 | 2023-03-09 | 1 | CRS-GUP-DHI-DT-23-1720 | 2023-03-14 | NC | DE-GUP-DT-E-23-701 | 2023-07-20 | 2
| GUP | YL17 | P1 | SCA | 120611 |  | GUP-YL17-P1SCA-120611 | AIR COMPRESSOR_INTERCONNECTION WIRING DIAGRAM | FI | 2022-09-30 |  | 플랜트기술팀(Mech.) | 조상환 |  |  |  |  | AIR COMP. | CCPP | Air Comp. | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-182 | 2023-02-16 | 0 | CRS-GUP-DHI-DT-23-1635 | 2023-03-03 | NC | DE-GUP-DT-E-23-182 | 2023-02-16 | 0 | CRS-GUP-DHI-DT-23-1635 | 2023-03-03 | NC
| GUP | YL22 | P1 | SCA | 120612 |  | GUP-YL22-P1SCA-120612 | AIR COMPRESSOR_NAME PLATE DRAWING | FI | 2022-09-30 |  | 플랜트기술팀(Mech.) | 조상환 |  |  |  |  | AIR COMP. | CCPP | Air Comp. | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-246 | 2023-02-24 | 0 | CRS-GUP-DHI-DT-23-1707 | 2023-03-14 | NC | DE-GUP-DT-E-23-246 | 2023-02-24 | 0 | CRS-GUP-DHI-DT-23-1707 | 2023-03-14 | NC
| GUP | YT01 | P1 | SCA | 120613 |  | GUP-YT01-P1SCA-120613 | AIR COMPRESSOR_MOTOR VENDOR PRINT | FI | 2022-08-31 |  | 플랜트기술팀(Mech.) | 조상환 |  |  |  |  | AIR COMP. | CCPP | Air Comp. | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-136 | 2023-02-07 | 1 | CRS-GUP-DHI-DT-23-1627 | 2023-03-02 | NC | DE-GUP-DT-E-22-1011 | 2022-11-30 | 0 | CRS-GUP-DHI-DT-22-1270 | 2022-12-16 | NC | DE-GUP-DT-E-23-136 | 2023-02-07 | 1 | CRS-GUP-DHI-DT-23-1627 | 2023-03-02 | NC
| GUP | XG02 | P1 | SCA | 120614 |  | GUP-XG02-P1SCA-120614 | AIR COMPRESSOR_P&I DIAGRAM FOR PACKAGE INTERNAL | FI | 2022-07-31 |  | 플랜트기술팀(Mech.) | 조상환 |  |  |  |  | AIR COMP. | CCPP | Air Comp. | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-940 | 2023-11-23 | 3 | CRS-GUP-DHI-DT-22-1403 | 2023-01-07 | NC | DE-GUP-DT-E-22-828 | 2022-10-20 | 0 | CRS-GUP-DHI-DT-22-1104 | 2022-11-21 | RC | DE-GUP-DT-E-22-1066 | 2022-12-09 | 1 | CRS-GUP-DHI-DT-22-1258 | 2022-12-13 | RC | DE-GUP-DT-E-22-1181 | 2022-12-23 | 2 | CRS-GUP-DHI-DT-22-1403 | 2023-01-07 | NC | DE-GUP-DT-E-23-940 | 2023-11-23 | 3
| GUP | YL01 | P1 | SCA | 120615 |  | GUP-YL01-P1SCA-120615 | AIR COMPRESSOR_HARDWIRE IO LIST | FI | 2022-09-30 |  | 플랜트기술팀(Mech.) | 조상환 |  |  |  |  | AIR COMP. | CCPP | Air Comp. | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-977 | 2022-11-23 | 0 | CRS-GUP-DHI-DT-22-1204 | 2022-11-30 | NC | DE-GUP-DT-E-22-977 | 2022-11-23 | 0 | CRS-GUP-DHI-DT-22-1204 | 2022-11-30 | NC
| GUP | YT01 | P1 | SCA | 120616 |  | GUP-YT01-P1SCA-120616 | AIR COMPRESSOR_EQUIPMENT DATA SHEET | FI | 2022-11-30 |  | 플랜트기술팀(Mech.) | 조상환 |  |  |  |  | AIR COMP. | CCPP | Air Comp. | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-260 | 2023-03-02 | 1 | CRS-GUP-DHI-DT-23-1712 | 2023-03-14 | NC | DE-GUP-DT-E-22-1017 | 2022-11-30 | 0 | CRS-GUP-DHI-DT-22-1313 | 2022-12-22 | NC | DE-GUP-DT-E-23-260 | 2023-03-02 | 1 | CRS-GUP-DHI-DT-23-1712 | 2023-03-14 | NC
| GUP | XH01 | P1 | SCA | 120617 |  | GUP-XH01-P1SCA-120617 | AIR COMPRESSOR_PIPING ARRANGEMENT DRAWING | FI | 2022-12-10 |  | 플랜트기술팀(Mech.) | 조상환 |  |  |  |  | AIR COMP. | CCPP | Air Comp. | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-700 | 2023-07-20 | 1 | CRS-GUP-DHI-DT-23-1613 | 2023-03-02 | NC | DE-GUP-DT-E-23-097 | 2023-01-31 | 0 | CRS-GUP-DHI-DT-23-1613 | 2023-03-02 | NC | DE-GUP-DT-E-23-700 | 2023-07-20 | 1
| GUP | XJ00 | P1 | SCA | 120618 |  | GUP-XJ00-P1SCA-120618 | AIR COMPRESSOR_PIPING ISOMETRIC DARWING | FI | 2022-12-10 |  | 플랜트기술팀(Mech.) | 조상환 |  |  |  |  | AIR COMP. | CCPP | Air Comp. | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-700 | 2023-07-20 | 1 | CRS-GUP-DHI-DT-23-1613 | 2023-03-02 | NC | DE-GUP-DT-E-23-097 | 2023-01-31 | 0 | CRS-GUP-DHI-DT-23-1613 | 2023-03-02 | NC | DE-GUP-DT-E-23-700 | 2023-07-20 | 1
| GUP | XH01 | P1 | SCA | 120619 |  | GUP-XH01-P1SCA-120619 | AIR COMPRESSOR_PIPING SUPPORT DRAWING | FI | 2022-12-10 |  | 플랜트기술팀(Mech.) | 조상환 |  |  |  |  | AIR COMP. | CCPP | Air Comp. | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-576 | 2023-05-24 | 1 | CRS-GUP-DHI-DT-23-2002 | 2023-06-15 | NC | DE-GUP-DT-E-23-097 | 2023-01-31 | 0 | CRS-GUP-DHI-DT-23-1613 | 2023-03-02 | NC | DE-GUP-DT-E-23-576 | 2023-05-24 | 1 | CRS-GUP-DHI-DT-23-2002 | 2023-06-15 | NC
| GUP | YT01 | P1 | SCA | 120620 |  | GUP-YT01-P1SCA-120620 | AIR COMPRESSOR_VALVE LIST & DATA SHEET | FI | 2022-12-20 |  | 플랜트기술팀(Mech.) | 조상환 |  |  |  |  | AIR COMP. | CCPP | Air Comp. | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-136 | 2023-02-07 | 0 | CRS-GUP-DHI-DT-23-1627 | 2023-03-02 | NC | DE-GUP-DT-E-23-136 | 2023-02-07 | 0 | CRS-GUP-DHI-DT-23-1627 | 2023-03-02 | NC
| GUP | YL01 | P1 | SCA | 120621 |  | GUP-YL01-P1SCA-120621 | AIR COMPRESSOR_DATALINK INTERFACE IO LIST | FI | 2022-11-30 |  | 플랜트기술팀(Mech.) | 조상환 |  |  |  |  | AIR COMP. | CCPP | Air Comp. | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-182 | 2023-02-16 | 1 | CRS-GUP-DHI-DT-23-1635 | 2023-03-03 | NC | DE-GUP-DT-E-22-1017 | 2022-11-30 | 0 | CRS-GUP-DHI-DT-22-1313 | 2022-12-22 | NC | DE-GUP-DT-E-23-182 | 2023-02-16 | 1 | CRS-GUP-DHI-DT-23-1635 | 2023-03-03 | NC
| GUP | CQ02 | P1 | SCA | 120622 |  | GUP-CQ02-P1SCA-120622 | AIR COMPRESSOR_OPERATION & MAINTENANCE (O&M) MANUAL | FI | 2023-07-28 |  | 플랜트기술팀(Mech.) | 조상환 |  |  |  |  | AIR COMP. | CCPP | Air Comp. | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-828 | 2023-09-26 | 0 | CRS-GUP-DHI-DT-23-2122 | 2023-10-26 | NC | DE-GUP-DT-E-23-828 | 2023-09-26 | 0 | CRS-GUP-DHI-DT-23-2122 | 2023-10-26 | NC
| GUP | XG02 | P1 | LAC | 120650 |  | GUP-XG02-P1LAC-120650 | BFP_P&I DIAGRAM | FA | 2022-07-28 | 2022-11-25 | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | BFP | CCPP | BFP | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-049 | 2023-01-19 | 0 | CRS-GUP-DHI-DT-22-1329 | 2022-12-28 | AA | DE-GUP-DT-E-22-501 | 2022-08-16 | A | CRS-GUP-DHI-DT-22-694 | 2022-08-29 | RC | DE-GUP-DT-E-22-1068 | 2022-12-09 | B | CRS-GUP-DHI-DT-22-1329 | 2022-12-28 | AA | DE-GUP-DT-E-23-049 | 2023-01-19 | 0
| GUP | YD00 | P1 | LAC | 120651 |  | GUP-YD00-P1LAC-120651 | BFP_PUMP ARRANGEMENT DRAWING | FI | 2022-07-21 |  | 플랜트기술팀(Mech.) | UPPALA |  | R |  |  | BFP | CCPP | BFP | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-284 | 2023-03-08 | 2 | CRS-GUP-DHI-DT-23-1719 | 2023-03-14 | NC | DE-GUP-DT-E-22-621 | 2022-09-05 | 0 | CRS-GUP-DHI-DT-22-806 | 2022-09-19 | NC | DE-GUP-DT-E-22-1072 | 2022-12-09 | 1 | CRS-GUP-DHI-DT-22-1296 | 2022-12-21 | NC | DE-GUP-DT-E-23-284 | 2023-03-08 | 2 | CRS-GUP-DHI-DT-23-1719 | 2023-03-14 | NC
| GUP | YT01 | P1 | LAC | 120652 |  | GUP-YT01-P1LAC-120652 | BFP_PUMP DATA SHEET & CHARACTERISTIC CURVE | FA | 2022-07-28 | 2022-11-25 | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | BFP | CCPP | BFP | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-186 | 2023-02-16 | 0 | CRS-GUP-DHI-DT-23-1485 | 2023-02-11 | AA | DE-GUP-DT-E-22-469 | 2022-07-28 | A | CRS-GUP-DHI-DT-22-680 | 2022-08-22 | RC | DE-GUP-DT-E-22-767 | 2022-10-07 | B | CRS-GUP-DHI-DT-22-1086 | 2022-11-21 | RC | DE-GUP-DT-E-22-1016 | 2022-11-30 | C | CRS-GUP-DHI-DT-22-1272 | 2022-12-16 | RC | DE-GUP-DT-E-22-1173 | 2022-12-23 | D | CRS-GUP-DHI-DT-23-1485 | 2023-02-11 | AA | DE-GUP-DT-E-23-186 | 2023-02-16 | 0
| GUP | YK01 | P1 | LAC | 120653 |  | GUP-YK01-P1LAC-120653 | BFP_PUMP SECTIONAL DRAWING | FI | 2022-08-12 |  | 플랜트기술팀(Mech.) | UPPALA |  | R |  |  | BFP | CCPP | BFP | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-393 | 2023-03-30 | 3 | CRS-GUP-DHI-DT-23-1851 | 2023-04-19 | NC | DE-GUP-DT-E-22-529 | 2022-08-23 | 0 | CRS-GUP-DHI-DT-22-736 | 2022-09-12 | NC | DE-GUP-DT-E-22-1015 | 2022-11-30 | 1 | CRS-GUP-DHI-DT-22-1308 | 2022-12-22 | NC | DE-GUP-DT-E-23-158 | 2023-02-13 | 2 | CRS-GUP-DHI-DT-23-1631 | 2023-03-03 | NC | DE-GUP-DT-E-23-393 | 2023-03-30 | 3 | CRS-GUP-DHI-DT-23-1851 | 2023-04-19 | NC
| GUP | YT01 | P1 | LAC | 120654 |  | GUP-YT01-P1LAC-120654 | BFP_MOTOR DATA SHEET & CHARACTERISTIC CURVE | FI | 2022-08-25 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | BFP | CCPP | BFP | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1156 | 2022-12-22 | 1 | CRS-GUP-DHI-DT-22-1372 | 2022-12-30 | NC | DE-GUP-DT-E-22-641 | 2022-09-08 | 0 | CRS-GUP-DHI-DT-22-857 | 2022-09-24 | NC | DE-GUP-DT-E-22-1156 | 2022-12-22 | 1 | CRS-GUP-DHI-DT-22-1372 | 2022-12-30 | NC
| GUP | YM01 | P1 | LAC | 120655 |  | GUP-YM01-P1LAC-120655 | BFP_MOTOR OUTLINE, TERMINAL BOX, NAME PLATE DRAWING | FI | 2022-08-25 |  | 플랜트기술팀(Mech.) | UPPALA |  | R |  |  | BFP | CCPP | BFP | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1156 | 2022-12-22 | 1 | CRS-GUP-DHI-DT-22-1372 | 2022-12-30 | NC | DE-GUP-DT-E-22-641 | 2022-09-08 | 0 | CRS-GUP-DHI-DT-22-857 | 2022-09-24 | NC | DE-GUP-DT-E-22-1156 | 2022-12-22 | 1 | CRS-GUP-DHI-DT-22-1372 | 2022-12-30 | NC
| GUP | CV03 | P1 | LAC | 120656 |  | GUP-CV03-P1LAC-120656 | BFP_INSTRUMENT SPECIFICATION | FI | 2022-09-23 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | BFP | CCPP | BFP | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-125 | 2023-02-06 | 1 | CRS-GUP-DHI-DT-23-1540 | 2023-02-15 | NC | DE-GUP-DT-E-22-704 | 2022-09-26 | 0 | CRS-GUP-DHI-DT-22-917 | 2022-10-19 | NC | DE-GUP-DT-E-23-125 | 2023-02-06 | 1 | CRS-GUP-DHI-DT-23-1540 | 2023-02-15 | NC
| GUP | YT01 | P1 | LAB | 120657 |  | GUP-YT01-P1LAB-120657 | BFP_DATA SHEET & OUTLINE DRAWING FOR SUCTION STRAINER | FI | 2022-09-28 |  | 플랜트기술팀(Mech.) | UPPALA |  | R |  |  | BFP | CCPP | BFP | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-891 | 2022-11-01 | 0 | CRS-GUP-DHI-DT-22-1027 | 2022-11-13 | NC | DE-GUP-DT-E-22-891 | 2022-11-01 | 0 | CRS-GUP-DHI-DT-22-1027 | 2022-11-13 | NC
| GUP | XF00 | P1 | LAC | 120658 |  | GUP-XF00-P1LAC-120658 | BFP_NAME PLATE DRAWING FOR PUMP | FI | 2022-10-10 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | BFP | CCPP | BFP | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-188 | 2023-02-16 | 1 | CRS-GUP-DHI-DT-23-1686 | 2023-03-13 | NC | DE-GUP-DT-E-22-1065 | 2022-12-09 | 0 | CRS-GUP-DHI-DT-22-1294 | 2022-12-21 | NC | DE-GUP-DT-E-23-188 | 2023-02-16 | 1 | CRS-GUP-DHI-DT-23-1686 | 2023-03-13 | NC
| GUP | CV03 | P1 | LAC | 120659 |  | GUP-CV03-P1LAC-120659 | BFP_MECHANICAL SEAL SPECIFICATION | FI | 2022-10-14 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | BFP | CCPP | BFP | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1135 | 2022-12-20 | 1 | CRS-GUP-DHI-DT-22-1369 | 2022-12-30 | NC | DE-GUP-DT-E-22-817 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1100 | 2022-11-21 | NC | DE-GUP-DT-E-22-1135 | 2022-12-20 | 1 | CRS-GUP-DHI-DT-22-1369 | 2022-12-30 | NC
| GUP | CV03 | P1 | LAC | 120660 |  | GUP-CV03-P1LAC-120660 | BFP_THERMAL INSULATION SPECIFICATION | FI | 2022-11-07 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | BFP | CCPP | BFP | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-230 | 2023-02-23 | 0 | CRS-GUP-DHI-DT-23-1702 | 2023-03-14 | NC | DE-GUP-DT-E-23-230 | 2023-02-23 | 0 | CRS-GUP-DHI-DT-23-1702 | 2023-03-14 | NC
| GUP | CV03 | P1 | LAC | 120661 |  | GUP-CV03-P1LAC-120661 | BFP_COUPLING SPECIFICATION | FI | 2022-11-04 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | BFP | CCPP | BFP | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-127 | 2023-02-06 | 1 | CRS-GUP-DHI-DT-23-1542 | 2023-02-15 | NC | DE-GUP-DT-E-22-818 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1101 | 2022-11-21 | NC | DE-GUP-DT-E-23-127 | 2023-02-06 | 1 | CRS-GUP-DHI-DT-23-1542 | 2023-02-15 | NC
| GUP | CV03 | P1 | LAB | 120662 |  | GUP-CV03-P1LAB-120662 | BFP_SAFETY RELIEF VALVE SPECIFICATION | FI | 2022-09-30 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | BFP | CCPP | BFP | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-970 | 2022-11-22 | 0 | CRS-GUP-DHI-DT-22-1195 | 2022-11-30 | NC | DE-GUP-DT-E-22-970 | 2022-11-22 | 0 | CRS-GUP-DHI-DT-22-1195 | 2022-11-30 | NC
| GUP | CV03 | P1 | LAB | 120663 |  | GUP-CV03-P1LAB-120663 | BFP_VFD SPECIFICATION | FA | 2022-08-12 | 2022-12-10 | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | BFP | CCPP | BFP | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1243 | 2023-01-09 | 0 | CRS-GUP-DHI-DT-22-1068 | 2022-11-19 | AA | DE-GUP-DT-E-22-499 | 2022-08-12 | A | CRS-GUP-DHI-DT-22-693 | 2022-08-29 | RC | DE-GUP-DT-E-22-706 | 2022-09-28 | B | CRS-GUP-DHI-DT-22-1068 | 2022-11-19 | AA | DE-GUP-DT-E-22-1243 | 2023-01-09 | 0
| GUP | YV02 | P1 | LAC | 120664 |  | GUP-YV02-P1LAC-120664 | BFP_I&C JUNCTION BOX OUTLINE/INTERNAL LAYOUT DRAWING | FI | 2022-09-23 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | BFP | CCPP | BFP | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-064 | 2023-01-20 | 1 | CRS-GUP-DHI-DT-23-1475 | 2023-02-09 | NC | DE-GUP-DT-E-22-670 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-909 | 2022-10-19 | NC | DE-GUP-DT-E-23-064 | 2023-01-20 | 1 | CRS-GUP-DHI-DT-23-1475 | 2023-02-09 | NC
| GUP | XB00 | P1 | LAC | 120665 |  | GUP-XB00-P1LAC-120665 | BFP_FOUNDATION DRAWING & LOAD DATA OF EQUIPMENT | FI | 2022-07-21 |  | 플랜트기술팀(Mech.) | UPPALA |  | R |  |  | BFP | CCPP | BFP | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-471 | 2022-07-28 | 0 | CRS-GUP-DHI-DT-22-651 | 2022-08-20 | NC | DE-GUP-DT-E-22-471 | 2022-07-28 | 0 | CRS-GUP-DHI-DT-22-651 | 2022-08-20 | NC
| GUP | CQ02 | P1 | LAC | 120682 |  | GUP-CQ02-P1LAC-120682 | BFP_OPERATION & MAINTENANCE (O&M) MANUAL | FI | 2023-07-28 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | BFP | CCPP | BFP | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-709 | 2023-07-24 | 0 | CRS-GUP-DHI-DT-23-2088 | 2023-08-08 | NC | DE-GUP-DT-E-23-709 | 2023-07-24 | 0 | CRS-GUP-DHI-DT-23-2088 | 2023-08-08 | NC
| GUP | XG02 | P1 | LCB | 120700 |  | GUP-XG02-P1LCB-120700 | CEP_P&I DIAGRAM | FA | 2022-07-08 | 2022-11-05 | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | CEP | CCPP | CEP | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-385 | 2023-03-29 | 2 | CRS-GUP-DHI-DT-22-1126 | 2022-11-23 | AA | DE-GUP-DT-E-22-380 | 2022-07-11 | A | CRS-GUP-DHI-DT-22-546 | 2022-07-25 | RC | DE-GUP-DT-E-22-607 | 2022-09-01 | B | CRS-GUP-DHI-DT-22-765 | 2022-09-14 | AA | DE-GUP-DT-E-22-739 | 2022-09-30 | 0 | CRS-GUP-DHI-DT-22-1126 | 2022-11-23 | AA | DE-GUP-DT-E-22-1133 | 2022-12-20 | 1 | CRS 메일접수안됨3/29 |  |  | DE-GUP-DT-E-23-385 | 2023-03-29 | 2
| GUP | YD00 | P1 | LCB | 120701 |  | GUP-YD00-P1LCB-120701 | CEP_PUMP ARRANGEMENT DRAWING | FI | 2022-07-12 |  | 플랜트기술팀(Mech.) | UPPALA |  | R |  |  | CEP | CCPP | CEP | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-342 | 2023-03-22 | 4 | DE-GUP-DT-E-23-1825 | 2023-04-12 | NC | DE-GUP-DT-E-22-382 | 2022-07-11 | 0 | CRS-GUP-DHI-DT-22-609 | 2022-08-16 | NC | DE-GUP-DT-E-22-577 | 2022-08-30 | 1 | CRS-GUP-DHI-DT-22-787 | 2022-09-19 | NC | DE-GUP-DT-E-22-1167 | 2022-12-23 | 2 | CRS-GUP-DHI-DT-22-1358 | 2022-12-29 | NC | DE-GUP-DT-E-23-128 | 2023-02-06 | 3 | CRS-GUP-DHI-DT-23-1624 | 2023-03-02 | NC | DE-GUP-DT-E-23-342 | 2023-03-22 | 4 | DE-GUP-DT-E-23-1825 | 2023-04-12 | NC
| GUP | YT01 | P1 | LCB | 120702 |  | GUP-YT01-P1LCB-120702 | CEP_PUMP DATA SHEET & CHARACTERISTIC CURVE | FA | 2022-07-06 | 2022-11-03 | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | CEP | CCPP | CEP | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-739 | 2022-09-30 | 0 | CRS-GUP-DHI-DT-22-1126 | 2022-11-23 | AA | DE-GUP-DT-E-22-380 | 2022-07-11 | A | CRS-GUP-DHI-DT-22-546 | 2022-07-25 | RC | DE-GUP-DT-E-22-607 | 2022-09-01 | B | CRS-GUP-DHI-DT-22-765 | 2022-09-14 | AA | DE-GUP-DT-E-22-739 | 2022-09-30 | 0 | CRS-GUP-DHI-DT-22-1126 | 2022-11-23 | AA
| GUP | YK01 | P1 | LCB | 120703 |  | GUP-YK01-P1LCB-120703 | CEP_PUMP SECTIONAL DRAWING | FI | 2022-07-15 |  | 플랜트기술팀(Mech.) | UPPALA |  | R |  |  | CEP | CCPP | CEP | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-341 | 2023-03-22 | 3 | CRS-GUP-DHI-DT-23-1824 | 2023-04-12 | NC | DE-GUP-DT-E-22-381 | 2022-07-11 | 0 | CRS-GUP-DHI-DT-22-543 | 2022-07-25 | NC | DE-GUP-DT-E-22-579 | 2022-08-30 | 1 | CRS-GUP-DHI-DT-22-788 | 2022-09-19 | NC | DE-GUP-DT-E-22-768 | 2022-10-07 | 2 | CRS-GUP-DHI-DT-22-999 | 2022-11-13 | NC | DE-GUP-DT-E-23-341 | 2023-03-22 | 3 | CRS-GUP-DHI-DT-23-1824 | 2023-04-12 | NC
| GUP | YT01 | P1 | LCB | 120704 |  | GUP-YT01-P1LCB-120704 | CEP_MOTOR DATA SHEET & CHARACTERISTIC CURVE | FI | 2022-07-25 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | CEP | CCPP | CEP | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-448 | 2022-07-26 | 0 | CRS-GUP-DHI-DT-22-637 | 2022-08-18 | NC | DE-GUP-DT-E-22-448 | 2022-07-26 | 0 | CRS-GUP-DHI-DT-22-637 | 2022-08-18 | NC
| GUP | YM01 | P1 | LCB | 120705 |  | GUP-YM01-P1LCB-120705 | CEP_MOTOR OUTLINE, TERMINAL BOX, NAME PLATE DRAWING | FI | 2022-07-25 |  | 플랜트기술팀(Mech.) | UPPALA |  | R |  |  | CEP | CCPP | CEP | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1139 | 2022-12-21 | 1 | CRS-GUP-DHI-DT-22-1371 | 2022-12-30 | NC | DE-GUP-DT-E-22-448 | 2022-07-26 | 0 | CRS-GUP-DHI-DT-22-637 | 2022-08-18 | NC | DE-GUP-DT-E-22-1139 | 2022-12-21 | 1 | CRS-GUP-DHI-DT-22-1371 | 2022-12-30 | NC
| GUP | CV03 | P1 | LCB | 120706 |  | GUP-CV03-P1LCB-120706 | CEP_INSTRUMENT SPECIFICATION | FI | 2022-08-12 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | CEP | CCPP | CEP | I&C | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-279 | 2023-03-08 | 3 | CRS-GUP-DHI-DT-23-1717 | 2023-03-14 | NC | DE-GUP-DT-E-22-717 | 2022-09-29 | 0 | CRS-GUP-DHI-DT-22-919 | 2022-10-19 | NC | DE-GUP-DT-E-22-884 | 2022-10-31 | 1 | CRS-GUP-DHI-DT-22-1025 | 2022-11-13 | NC | DE-GUP-DT-E-22-1069 | 2022-12-09 | 2 | CRS-GUP-DHI-DT-22-1364 | 2022-12-30 | NC | DE-GUP-DT-E-23-279 | 2023-03-08 | 3 | CRS-GUP-DHI-DT-23-1717 | 2023-03-14 | NC
| GUP | YT01 | P1 | LCA | 120707 |  | GUP-YT01-P1LCA-120707 | CEP_DATA SHEET & OUTLINE DRAWING FOR SUCTION STRAINER | FI | 2022-08-25 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | CEP | CCPP | CEP | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-129 | 2023-02-06 | 2 | CRS-GUP-DHI-DT-23-1543 | 2023-02-16 | NC | DE-GUP-DT-E-22-722 | 2022-09-29 | 0 | CRS-GUP-DHI-DT-22-995 | 2022-11-13 | NC | DE-GUP-DT-E-22-1070 | 2022-12-09 | 1 | CRS-GUP-DHI-DT-22-1295 | 2022-12-21 | NC | DE-GUP-DT-E-23-129 | 2023-02-06 | 2 | CRS-GUP-DHI-DT-23-1543 | 2023-02-16 | NC
| GUP | XF00 | P1 | LCB | 120708 |  | GUP-XF00-P1LCB-120708 | CEP_NAME PLATE DRAWING FOR PUMP | FI | 2022-08-12 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | CEP | CCPP | CEP | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-880 | 2022-10-31 | 1 | CRS-GUP-DHI-DT-22-1171 | 2022-11-28 | NC | DE-GUP-DT-E-22-447 | 2022-07-26 | 0 | CRS-GUP-DHI-DT-22-636 | 2022-08-18 | NC | DE-GUP-DT-E-22-880 | 2022-10-31 | 1 | CRS-GUP-DHI-DT-22-1171 | 2022-11-28 | NC
| GUP | CV03 | P1 | LCB | 120709 |  | GUP-CV03-P1LCB-120709 | CEP_MECHANICAL SEAL SPECIFICATION | FI | 2022-09-01 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | CEP | CCPP | CEP | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1136 | 2022-12-20 | 1 | CRS-GUP-DHI-DT-22-1370 | 2022-12-30 | NC | DE-GUP-DT-E-22-447 | 2022-07-26 | 0 | CRS-GUP-DHI-DT-22-636 | 2022-08-18 | NC | DE-GUP-DT-E-22-1136 | 2022-12-20 | 1 | CRS-GUP-DHI-DT-22-1370 | 2022-12-30 | NC
| GUP | CV03 | P1 | LCB | 120710 |  | GUP-CV03-P1LCB-120710 | CEP_COUPLING SPECIFICATION | FI | 2022-09-01 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | CEP | CCPP | CEP | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-435 | 2022-07-22 | 0 | CRS-GUP-DHI-DT-22-673 | 2022-08-22 | NC | DE-GUP-DT-E-22-435 | 2022-07-22 | 0 | CRS-GUP-DHI-DT-22-673 | 2022-08-22 | NC
| GUP | XB00 | P1 | LCB | 120711 |  | GUP-XB00-P1LCB-120711 | CEP_FOUNDATION DRAWING & LOAD DATA OF EQUIPMENT | FI | 2022-07-12 |  | 플랜트기술팀(Mech.) | UPPALA |  | R |  |  | CEP | CCPP | CEP | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1170 | 2022-12-23 | 2 | CRS-GUP-DHI-DT-22-1347 | 2022-12-28 | NC | DE-GUP-DT-E-22-382 | 2022-07-11 | 0 | CRS-GUP-DHI-DT-22-609 | 2022-08-16 | NC | DE-GUP-DT-E-22-723 | 2022-09-29 | 1 | CRS-GUP-DHI-DT-22-937 | 2022-10-21 | NC | DE-GUP-DT-E-22-1170 | 2022-12-23 | 2 | CRS-GUP-DHI-DT-22-1347 | 2022-12-28 | NC
| GUP | CQ02 | P1 | LCB | 120726 |  | GUP-CQ02-P1LCB-120726 | CEP_OPERATION & MAINTENANCE (O&M) MANUAL | FI | 2023-07-28 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | CEP | CCPP | CEP | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-710 | 2023-07-24 | 0 | CRS-GUP-DHI-DT-23-2089 | 2023-08-08 | NC | DE-GUP-DT-E-23-710 | 2023-07-24 | 0 | CRS-GUP-DHI-DT-23-2089 | 2023-08-08 | NC
| GUP | YD00 | P1 | GHC | 120750 |  | GUP-YD00-P1GHC-120750 | GSP(WATER)_PUMP ARRANGEMENT DRAWING | FI | 2022-12-12 |  | 플랜트기술팀(Mech.) | UPPALA |  | R |  |  | GSP(WATER) | CCPP | GSP(WATER) | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-818 | 2023-09-21 | 4 | 자체 CRS 개정 후 제출 | 2023-09-20 | N/A | DE-GUP-DT-E-22-1109 | 2022-12-16 | 0 | CRS-GUP-DHI-DT-22-1300 | 2022-12-21 | NC | DE-GUP-DT-E-23-130 | 2023-02-06 | 1 | CRS-GUP-DHI-DT-23-1544 | 2023-02-16 | NC | DE-GUP-DT-E-23-343 | 2023-03-22 | 2 | CRS-GUP-DHI-DT-23-1826 | 2023-04-12 | NC | DE-GUP-DT-E-23-807 | 2023-09-12 | 3 | 자체 CRS 개정 후 제출 | 2023-09-20 | N/A | DE-GUP-DT-E-23-818 | 2023-09-21 | 4
| GUP | YT01 | P1 | GHC | 120751 |  | GUP-YT01-P1GHC-120751 | GSP(WATER)_PUMP DATA SHEET & CHARACTERISTIC CURVE | FA | 2022-12-09 | 2023-03-30 | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | GSP(WATER) | CCPP | GSP(WATER) | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-503 | 2023-04-25 | 0 | CRS-GUP-DHI-DT-23-1924 | 2023-05-05 | AA | DE-GUP-DT-E-22-1088 | 2022-12-14 | A | CRS-GUP-DHI-DT-22-1337 | 2022-12-28 | RC | DE-GUP-DT-E-23-058 | 2023-01-19 | B | CRS-GUP-DHI-DT-23-1660 | 2023-03-09 | RC | DE-GUP-DT-E-23-413 | 2023-04-03 | C | CRS-GUP-DHI-DT-23-1861 | 2023-04-19 | AA | DE-GUP-DT-E-23-503 | 2023-04-25 | 0 | CRS-GUP-DHI-DT-23-1924 | 2023-05-05 | AA
| GUP | YK01 | P1 | GHC | 120752 |  | GUP-YK01-P1GHC-120752 | GSP(WATER)_PUMP SECTIONAL DRAWING | FI | 2022-12-07 |  | 플랜트기술팀(Mech.) | UPPALA |  | R |  |  | GSP(WATER) | CCPP | GSP(WATER) | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-065 | 2023-01-20 | 1 | CRS-GUP-DHI-DT-23-1534 | 2023-02-15 | NC | DE-GUP-DT-E-22-1053 | 2022-12-08 | 0 | CRS-GUP-DHI-DT-22-1291 | 2022-12-21 | NC | DE-GUP-DT-E-23-065 | 2023-01-20 | 1 | CRS-GUP-DHI-DT-23-1534 | 2023-02-15 | NC
| GUP | YT01 | P1 | GHC | 120753 |  | GUP-YT01-P1GHC-120753 | GSP(WATER)_MOTOR DATA SHEET & CHARACTERISTIC CURVE | FI | 2022-12-23 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | GSP(WATER) | CCPP | GSP(WATER) | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-477 | 2023-04-18 | 1 | CRS-GUP-DHI-DT-23-1905 | 2023-05-05 | NC | DE-GUP-DT-E-22-1169 | 2022-12-23 | 0 | CRS-GUP-DHI-DT-23-1484 | 2023-02-11 | NC | DE-GUP-DT-E-23-477 | 2023-04-18 | 1 | CRS-GUP-DHI-DT-23-1905 | 2023-05-05 | NC
| GUP | YM01 | P1 | GHC | 120754 |  | GUP-YM01-P1GHC-120754 | GSP(WATER)_MOTOR OUTLINE, TERMINAL BOX, NAME PLATE DRAWING | FI | 2022-12-23 |  | 플랜트기술팀(Mech.) | UPPALA |  | R |  |  | GSP(WATER) | CCPP | GSP(WATER) | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-477 | 2023-04-18 | 1 | CRS-GUP-DHI-DT-23-1905 | 2023-05-05 | NC | DE-GUP-DT-E-22-1169 | 2022-12-23 | 0 | CRS-GUP-DHI-DT-23-1484 | 2023-02-11 | NC | DE-GUP-DT-E-23-477 | 2023-04-18 | 1 | CRS-GUP-DHI-DT-23-1905 | 2023-05-05 | NC
| GUP | CV03 | P1 | GHC | 120755 |  | GUP-CV03-P1GHC-120755 | GSP(WATER)_INSTRUMENT SPECIFICATION | FI | 2022-12-23 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | GSP(WATER) | CCPP | GSP(WATER) | I&C | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-428 | 2023-04-06 | 1 | CRS-GUP-DHI-DT-23-1884 | 2023-05-02 | NC | DE-GUP-DT-E-22-1164 | 2022-12-23 | 0 | CRS-GUP-DHI-DT-22-1398 | 2023-01-06 | NC | DE-GUP-DT-E-23-428 | 2023-04-06 | 1 | CRS-GUP-DHI-DT-23-1884 | 2023-05-02 | NC
| GUP | XF00 | P1 | GHC | 120756 |  | GUP-XF00-P1GHC-120756 | GSP(WATER)_NAME PLATE DRAWING FOR PUMP | FI | 2022-12-16 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | GSP(WATER) | CCPP | GSP(WATER) | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-126 | 2023-02-06 | 1 | CRS-GUP-DHI-DT-23-1541 | 2023-02-15 | NC | DE-GUP-DT-E-22-1108 | 2022-12-16 | 0 | CRS-GUP-DHI-DT-22-1299 | 2022-12-21 | NC | DE-GUP-DT-E-23-126 | 2023-02-06 | 1 | CRS-GUP-DHI-DT-23-1541 | 2023-02-15 | NC
| GUP | CV03 | P1 | GHC | 120757 |  | GUP-CV03-P1GHC-120757 | GSP(WATER)_MECHANICAL SEAL SPECIFICATION | FI | 2022-12-16 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | GSP(WATER) | CCPP | GSP(WATER) | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-280 | 2023-03-08 | 1 | CRS-GUP-DHI-DT-23-1718 | 2023-03-14 | NC | DE-GUP-DT-E-22-1111 | 2022-12-16 | 0 | CRS-GUP-DHI-DT-22-1301 | 2022-12-21 | NC | DE-GUP-DT-E-23-280 | 2023-03-08 | 1 | CRS-GUP-DHI-DT-23-1718 | 2023-03-14 | NC
| GUP | CQ02 | P0 | GHC | 120763 |  | GUP-CQ02-P0GHC-120763 | GSP(WATER)_OPERATION & MAINTENANCE (O&M) MANUAL | FI | 2023-07-28 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | GSP(WATER) | CCPP | GSP(WATER) | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-711 | 2023-07-24 | 0 | CRS-GUP-DHI-DT-23-2090 | 2023-08-08 | NC | DE-GUP-DT-E-23-711 | 2023-07-24 | 0 | CRS-GUP-DHI-DT-23-2090 | 2023-08-08 | NC
| GUP | XG02 | P0 | EG | 120800 |  | GUP-XG02-P0EG-120800 | ULSD SYSTEM_P&I DIAGRAM | FA | 2021-06-02 | 2022-09-30 | 플랜트기술팀(Mech.) | UPPALA |  |  | G | FA | ULSD | CCPP | ULSD | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-246 | 2024-10-08 | 4 | 별도 메일접수 24-013 | 2024-12-04 | RC | DHI-GUP-DT-21-003 | 2021-05-28 | A | CRS-GUP-DHI-DT-21-034 | 2021-10-06 | RC | DHI-GUP-DT-21-187 | 2021-12-17 | B | CRS-GUP-DHI-DT-21-135 | 2022-01-11 | AC | DHI-GUP-DT-22-089 | 2022-02-24 | C | CRS-GUP-DHI-DT-22-250 | 2022-03-14 | AC | DE-GUP-DT-E-22-753 | 2022-10-04 | D | CRS-GUP-DHI-DT-22-1073 | 2022-11-19 | AC | DE-GUP-DT-E-23-055 | 2023-01-19 | 0(CP) | CRS-GUP-DHI-DT-23-1656 | 2023-03-07 | AA | DE-GUP-DT-E-23-490 | 2023-04-21 | 1 | CRS-GUP-DHI-DT-23-1915 | 2023-05-05 | AA | DE-GUP-DT-E-24-008 | 2024-01-10 | 3 | 자체 CRS 개정 후 제출 | 2024-10-07 | N/A | DE-GUP-DT-E-24-246 | 2024-10-08 | 4 | 별도 메일접수 24-013 | 2024-12-04 | RC
| GUP | XS00 | P0 | EG | 120801 |  | GUP-XS00-P0EG-120801 | ULSD SYSTEM_SYSTEM DESCRIPTION | FA | 2021-07-14 | 2022-09-30 | 플랜트기술팀(Mech.) | UPPALA |  | P | G | FA | ULSD | CCPP | ULSD | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-258 | 2024-10-31 | 2 | 별도 메일접수 24-019 | 2024-12-04 | RC | DHI-GUP-DT-21-008 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-009 | 2021-09-28 | RC | DHI-GUP-DT-21-187 | 2021-12-17 | B | CRS-GUP-DHI-DT-21-135 | 2022-01-11 | RC | DHI-GUP-DT-22-089 | 2022-02-24 | C | CRS-GUP-DHI-DT-22-250 | 2022-03-14 | AC | DE-GUP-DT-E-22-753 | 2022-10-04 | D | CRS-GUP-DHI-DT-22-1073 | 2022-11-19 | AA | DE-GUP-DT-E-23-055 | 2023-01-19 | 0 | CRS-GUP-DHI-DT-23-1656 | 2023-03-07 | AA | DE-GUP-DT-E-24-059 | 2024-02-27 | 1 | 자체 CRS 개정 후 제출 | 2024-10-30 | N/A | DE-GUP-DT-E-24-258 | 2024-10-31 | 2 | 별도 메일접수 24-019 | 2024-12-04 | RC
| GUP | XW01 | P0 | EG | 120802 |  | GUP-XW01-P0EG-120802 | ULSD SYSTEM_DESIGN CRITERIA | FA | 2021-07-14 | 2022-09-30 | 플랜트기술팀(Mech.) | UPPALA |  | P | G | FA | ULSD | CCPP | ULSD | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-055 | 2023-01-19 | 0 | CRS-GUP-DHI-DT-23-1656 | 2023-03-07 | AA | DHI-GUP-DT-21-007 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-009 | 2021-09-28 | RC | DHI-GUP-DT-21-187 | 2021-12-17 | B | CRS-GUP-DHI-DT-21-135 | 2022-01-11 | AC | DHI-GUP-DT-22-089 | 2022-02-24 | C | CRS-GUP-DHI-DT-22-250 | 2022-03-14 | AC | DE-GUP-DT-E-22-753 | 2022-10-04 | D | CRS-GUP-DHI-DT-22-1073 | 2022-11-19 | AA | DE-GUP-DT-E-23-055 | 2023-01-19 | 0 | CRS-GUP-DHI-DT-23-1656 | 2023-03-07 | AA
| GUP | YD00 | P1 | EGD | 121101 |  | GUP-YD00-P1EGD-121101 | ULSD System Particle Filter Specification | FI | 2024-09-30 |  | 플랜트기술팀(Mech.) | 김동주 |  |  |  |  | ULSD | CCPP | ULSD | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-224 | 2024-09-06 | 0 | CRS-GUP-DHI-DT-25-010 | 2025-01-10 | NC | DE-GUP-DT-E-24-224 | 2024-09-06 | 0 | CRS-GUP-DHI-DT-25-010 | 2025-01-10 | NC
| GUP | YD00 | P1 | EH | 120803 |  | GUP-YD00-P1EH-120803 | ULSD TREATMENT_ARRANGEMENT DRAWING | FA | 2022-11-14 | 2023-03-17 | 플랜트기술팀(Mech.) | UPPALA |  | R |  |  | ULSD TREATMENT | CCPP | ULSD Treatment | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-102 | 2024-04-04 | 1 | 자체 CRS 개정 후 제출 | 2024-04-03 | N/A | DE-GUP-DT-E-22-1120 | 2022-12-19 | A | CRS-GUP-DHI-DT-22-1375 | 2022-12-31 | RC | DE-GUP-DT-E-23-232 | 2023-02-23 | B | CRS-GUP-DHI-DT-23-1739 | 2023-03-17 | AA | DE-GUP-DT-E-23-394 | 2023-03-30 | 0 | 자체 CRS 개정 후 제출 | 2024-04-03 | N/A | DE-GUP-DT-E-24-102 | 2024-04-04 | 1
| GUP | CV03 | P1 | EH | 120804 |  | GUP-CV03-P1EH-120804 | ULSD TREATMENT_SPECIFICATION | FA | 2022-11-04 | 2023-03-06 | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | ULSD TREATMENT | CCPP | ULSD Treatment | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-287 | 2023-03-09 | 0 | CRS-GUP-DHI-DT-23-1481 | 2023-02-11 | AA | DE-GUP-DT-E-22-887 | 2022-10-31 | A | CRS-GUP-DHI-DT-22-1169 | 2022-11-26 | RC | DE-GUP-DT-E-22-1134 | 2022-12-20 | B | CRS-GUP-DHI-DT-23-1481 | 2023-02-11 | AA | DE-GUP-DT-E-23-287 | 2023-03-09 | 0
| GUP | XG02 | P1 | EH | 120805 |  | GUP-XG02-P1EH-120805 | ULSD TREATMENT_P&I DIAGRAM | FA | 2022-11-18 | 2023-03-24 | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | ULSD TREATMENT | CCPP | ULSD Treatment | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-101 | 2024-04-04 | 1 | 자체 CRS 개정 후 제출 | 2024-04-03 | N/A | DE-GUP-DT-E-22-1122 | 2022-12-19 | A | CRS-GUP-DHI-DT-22-1394 | 2023-01-06 | RC | DE-GUP-DT-E-23-224 | 2023-02-22 | B | CRS-GUP-DHI-DT-23-1756 | 2023-03-22 | AA | DE-GUP-DT-E-23-394 | 2023-03-30 | 0 | 자체 CRS 개정 후 제출 | 2024-04-03 | N/A | DE-GUP-DT-E-24-101 | 2024-04-04 | 1
| GUP | CV03 | P1 | EH | 120836 |  | GUP-CV03-P1EH-120836 | ULSD TREATMENT_INSTRUMENT SPECIFICATION | FI | 2023-05-03 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | ULSD TREATMENT | CCPP | ULSD Treatment | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-514 | 2023-04-28 | 0 | CRS-GUP-DHI-DT-23-1945 | 2023-05-11 | NC | DE-GUP-DT-E-23-514 | 2023-04-28 | 0 | CRS-GUP-DHI-DT-23-1945 | 2023-05-11 | NC
| GUP | CQ02 | P1 | EH | 120818 |  | GUP-CQ02-P1EH-120818 | ULSD TREATMENT_OPERATION & MAINTENANCE (O&M) MANUAL | FI | 2023-11-15 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | ULSD TREATMENT | CCPP | ULSD Treatment | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-114 | 2024-04-29 | 0 | CRS-GUP-DHI-DT-25-003 | 2025-01-10 | NC | DE-GUP-DT-E-24-114 | 2024-04-29 | 0 | CRS-GUP-DHI-DT-25-003 | 2025-01-10 | NC
| GUP | XS01 | P1 | EH | 120834 |  | GUP-XS01-P1EH-120834 | ULSD TREATMENT_OPERATION & CONTROL PHILOSOPHY | FI | 2023-07-28 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | ULSD TREATMENT | CCPP | ULSD Treatment | I&C | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-981 | 2023-12-11 | 0 | CRS-GUP-DHI-DT-24-071 | 2024-08-28 | N/A | DE-GUP-DT-E-23-981 | 2023-12-11 | 0 | CRS-GUP-DHI-DT-24-071 | 2024-08-28 | N/A
| GUP | YU02 | P1 | EH | 120827 |  | GUP-YU02-P1EH-120827 | ULSD TREATMENT_SINGLE LINE DIAGRAM | FI | 2023-09-28 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | ULSD TREATMENT | CCPP | ULSD Treatment | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-099 | 2024-04-03 | 1 | CRS-GUP-DHI-DT-23-2130 | 2023-11-01 | NC | DE-GUP-DT-E-23-808 | 2023-09-12 | 0 | CRS-GUP-DHI-DT-23-2130 | 2023-11-01 | NC | DE-GUP-DT-E-24-099 | 2024-04-03 | 1
| GUP | YD00 | P0 | EGY | 121901 |  | GUP-YD00-P0EGY-121901 | SPECIFICATION FOR BATCH CONTROL & OVERFILL PROTECTION | FI | 2024-10-30 |  | 플랜트기술팀(Mech.) | 김동주 |  |  |  |  | Batch Control & Overfill Protection | CCPP | Batch Control & Overfill Protection | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-252 | 2024-10-21 | 0 | 별도 메일접수 24-017 | 2024-12-04 | RC | DE-GUP-DT-E-24-252 | 2024-10-21 | 0 | 별도 메일접수 24-017 | 2024-12-04 | RC
| GUP | YD00 | P0 | EG | 120858 |  | GUP-YD00-P0EG-120858 | GSP(OIL)_PUMP ARRANGEMENT DRAWING | FI | 2022-12-12 |  | 플랜트기술팀(Mech.) | UPPALA |  | R |  |  | GSP(OIL) | CCPP | GSP(OIL) | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-177 | 2024-07-05 | 4 | 자체 CRS 개정 후 제출 | 2024-07-04 | N/A | DE-GUP-DT-E-22-1109 | 2022-12-16 | 0 | CRS-GUP-DHI-DT-22-1300 | 2022-12-21 | NC | DE-GUP-DT-E-23-130 | 2023-02-06 | 1 | CRS-GUP-DHI-DT-23-1544 | 2023-02-16 | NC | DE-GUP-DT-E-23-343 | 2023-03-22 | 2 | CRS-GUP-DHI-DT-23-1826 | 2023-04-12 | NC | DE-GUP-DT-E-23-807 | 2023-09-12 | 3 | 자체 CRS 개정 후 제출 | 2024-07-04 | N/A | DE-GUP-DT-E-24-177 | 2024-07-05 | 4
| GUP | YT01 | P0 | EG | 120859 |  | GUP-YT01-P0EG-120859 | GSP(OIL)_PUMP DATA SHEET & CHARACTERISTIC CURVE | FA | 2022-12-09 | 2023-03-30 | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | GSP(OIL) | CCPP | GSP(OIL) | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-177 | 2024-07-05 | 1 | 자체 CRS 개정 후 제출 | 2024-07-04 | N/A | DE-GUP-DT-E-22-1088 | 2022-12-14 | A | CRS-GUP-DHI-DT-22-1337 | 2022-12-28 | RC | DE-GUP-DT-E-23-058 | 2023-01-19 | B | CRS-GUP-DHI-DT-23-1660 | 2023-03-09 | AA | DE-GUP-DT-E-23-387 | 2023-03-29 | 0 | 자체 CRS 개정 후 제출 | 2024-07-04 | N/A | DE-GUP-DT-E-24-177 | 2024-07-05 | 1
| GUP | YK01 | P0 | EG | 120860 |  | GUP-YK01-P0EG-120860 | GSP(OIL)_PUMP SECTIONAL DRAWING | FI | 2022-12-07 |  | 플랜트기술팀(Mech.) | UPPALA |  | R |  |  | GSP(OIL) | CCPP | GSP(OIL) | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-065 | 2023-01-20 | 1 | CRS-GUP-DHI-DT-23-1534 | 2023-02-15 | NC | DE-GUP-DT-E-22-1053 | 2022-12-08 | 0 | CRS-GUP-DHI-DT-22-1291 | 2022-12-21 | NC | DE-GUP-DT-E-23-065 | 2023-01-20 | 1 | CRS-GUP-DHI-DT-23-1534 | 2023-02-15 | NC
| GUP | YT01 | P0 | EG | 120861 |  | GUP-YT01-P0EG-120861 | GSP(OIL)_MOTOR DATA SHEET & CHARACTERISTIC CURVE | FI | 2022-12-23 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | GSP(OIL) | CCPP | GSP(OIL) | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-177 | 2024-07-05 | 2 | CRS-GUP-DHI-DT-23-1905 | 2023-05-05 | NC | DE-GUP-DT-E-22-1169 | 2022-12-23 | 0 | CRS-GUP-DHI-DT-23-1484 | 2023-02-11 | NC | DE-GUP-DT-E-23-477 | 2023-04-18 | 1 | CRS-GUP-DHI-DT-23-1905 | 2023-05-05 | NC | DE-GUP-DT-E-24-177 | 2024-07-05 | 2
| GUP | YM01 | P0 | EG | 120862 |  | GUP-YM01-P0EG-120862 | GSP(OIL)_MOTOR OUTLINE, TERMINAL BOX, NAME PLATE DRAWING | FI | 2022-12-23 |  | 플랜트기술팀(Mech.) | UPPALA |  | R |  |  | GSP(OIL) | CCPP | GSP(OIL) | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-177 | 2024-07-05 | 2 | CRS-GUP-DHI-DT-23-1905 | 2023-05-05 | NC | DE-GUP-DT-E-22-1169 | 2022-12-23 | 0 | CRS-GUP-DHI-DT-23-1484 | 2023-02-11 | NC | DE-GUP-DT-E-23-477 | 2023-04-18 | 1 | CRS-GUP-DHI-DT-23-1905 | 2023-05-05 | NC | DE-GUP-DT-E-24-177 | 2024-07-05 | 2
| GUP | CV03 | P0 | EG | 120863 |  | GUP-CV03-P0EG-120863 | GSP(OIL)_INSTRUMENT SPECIFICATION SHEET | FI | 2022-12-23 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | GSP(OIL) | CCPP | GSP(OIL) | I&C | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-428 | 2023-04-06 | 1 | CRS-GUP-DHI-DT-23-1884 | 2023-05-02 | NC | DE-GUP-DT-E-22-1164 | 2022-12-23 | 0 | CRS-GUP-DHI-DT-22-1398 | 2023-01-06 | NC | DE-GUP-DT-E-23-428 | 2023-04-06 | 1 | CRS-GUP-DHI-DT-23-1884 | 2023-05-02 | NC
| GUP | XF00 | P0 | EG | 120864 |  | GUP-XF00-P0EG-120864 | GSP(OIL)_INSTRUMENT SPECIFICATION SHEET | FI | 2022-12-16 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | GSP(OIL) | CCPP | GSP(OIL) | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-177 | 2024-07-05 | 2 | CRS-GUP-DHI-DT-23-1541 | 2023-02-15 | NC | DE-GUP-DT-E-22-1108 | 2022-12-16 | 0 | CRS-GUP-DHI-DT-22-1299 | 2022-12-21 | NC | DE-GUP-DT-E-23-126 | 2023-02-06 | 1 | CRS-GUP-DHI-DT-23-1541 | 2023-02-15 | NC | DE-GUP-DT-E-24-177 | 2024-07-05 | 2
| GUP | CV03 | P0 | EG | 120865 |  | GUP-CV03-P0EG-120865 | GSP(OIL)_MECHANICAL SEAL SPECIFICATION | FI | 2022-12-16 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | GSP(OIL) | CCPP | GSP(OIL) | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-280 | 2023-03-08 | 1 | CRS-GUP-DHI-DT-23-1718 | 2023-03-14 | NC | DE-GUP-DT-E-22-1111 | 2022-12-16 | 0 | CRS-GUP-DHI-DT-22-1301 | 2022-12-21 | NC | DE-GUP-DT-E-23-280 | 2023-03-08 | 1 | CRS-GUP-DHI-DT-23-1718 | 2023-03-14 | NC
| GUP | CQ02 | P0 | EG | 120871 |  | GUP-CQ02-P0EG-120871 | GSP(OIL)_OPERATION & MAINTENANCE (O&M) MANUAL | FI | 2023-07-28 |  | 플랜트기술팀(Mech.) | UPPALA |  |  |  |  | GSP(OIL) | CCPP | GSP(OIL) | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-711 | 2023-07-24 | 0 | CRS-GUP-DHI-DT-23-2090 | 2023-08-08 | NC | DE-GUP-DT-E-23-711 | 2023-07-24 | 0 | CRS-GUP-DHI-DT-23-2090 | 2023-08-08 | NC
| GUP | XA00 | P1 | SM | 120900 |  | GUP-XA00-P1SM-120900 | HOIST_GENERAL ARRANGEMENT DRAWING | FI | 2022-06-30 |  | 플랜트기술팀(Mech.) | 안성훈 |  | R |  |  | HOIST | CCPP | HOIST | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-304 | 2024-12-30 | 5 | 자체 CRS 개정 후 제출 | 2024-12-29 | N/A | DE-GUP-DT-E-22-339 | 2022-06-27 | 0 | CRS-GUP-DHI-DT-22-532 | 2022-07-19 | NC | DE-GUP-DT-E-22-588 | 2022-08-31 | 1 | CRS-GUP-DHI-DT-22-794 | 2022-09-19 | RC | DE-GUP-DT-E-22-841 | 2022-10-21 | 2 | CRS-GUP-DHI-DT-22-1174 | 2022-11-30 | NC | DE-GUP-DT-E-23-451 | 2023-04-13 | 3 | CRS-GUP-DHI-DT-23-1902 | 2023-05-05 | NC | DE-GUP-DT-E-23-749 | 2023-08-21 | 4 | 자체 CRS 개정 후 제출 | 2024-12-29 | N/A | DE-GUP-DT-E-24-304 | 2024-12-30 | 5
| GUP | YT01 | P1 | SM | 120901 |  | GUP-YT01-P1SM-120901 | HOIST_TECHNICAL DATA SHEETS | FI | 2022-06-30 |  | 플랜트기술팀(Mech.) | 안성훈 |  |  |  |  | HOIST | CCPP | HOIST | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-304 | 2024-12-30 | 4 | CRS-GUP-DHI-DT-23-1902 | 2023-05-05 | NC | DE-GUP-DT-E-22-339 | 2022-06-27 | 0 | CRS-GUP-DHI-DT-22-532 | 2022-07-19 | NC | DE-GUP-DT-E-22-588 | 2022-08-31 | 1 | CRS-GUP-DHI-DT-22-794 | 2022-09-19 | RC | DE-GUP-DT-E-22-841 | 2022-10-21 | 2 | CRS-GUP-DHI-DT-22-1174 | 2022-11-30 | NC | DE-GUP-DT-E-23-451 | 2023-04-13 | 3 | CRS-GUP-DHI-DT-23-1902 | 2023-05-05 | NC | DE-GUP-DT-E-24-304 | 2024-12-30 | 4
| GUP | XA00 | P1 | SM | 120903 |  | GUP-XA00-P1SM-120903 | HOIST_ELECTRICAL DETAIL DRAWING | FI | 2022-07-29 |  | 플랜트기술팀(Mech.) | 안성훈 |  | R |  |  | HOIST | CCPP | HOIST | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1241 | 2023-01-09 | 1 | CRS-GUP-DHI-DT-23-1497 | 2023-02-13 | NC | DE-GUP-DT-E-22-778 | 2022-10-11 | 0 | CRS-GUP-DHI-DT-22-986 | 2022-11-08 | RC | DE-GUP-DT-E-22-1241 | 2023-01-09 | 1 | CRS-GUP-DHI-DT-23-1497 | 2023-02-13 | NC
| GUP | XA00 | P1 | SM | 120910 |  | GUP-XA00-P1SM-120910 | Hoist General Arrangement Drawing For Liquid Fuel Skid | FI | 2024-11-01 |  | 플랜트기술팀(Mech.) | 안성훈 |  |  |  |  | HOIST | CCPP | HOIST | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-259 | 2024-10-31 | 0 | 별도 메일접수 25-001 | 2025-03-13 | AA | DE-GUP-DT-E-24-259 | 2024-10-31 | 0 | 별도 메일접수 25-001 | 2025-03-13 | AA
| GUP | XW01 | P0 | GKC | 120952 |  | GUP-XW01-P0GKC-120952 | POTABLE WATER SYSTEM_DESIGN CRITERIA | FA | 2021-07-20 | 2022-06-18 | 플랜트기술팀(Mech.) | 조상환 |  | P | G | FA |  | CCPP | Potable Water | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-168 | 2024-06-28 | 1 | CRS-GUP-DHI-DT-25-049 | 2025-03-19 | AA | DHI-GUP-DT-21-007 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-016 | 2021-09-29 | RC | DHI-GUP-DT-21-125 | 2021-11-29 | B | CRS-GUP-DHI-DT-21-127 | 2022-01-11 | AC | DHI-GUP-DT-22-081 | 2022-02-18 | C | CRS-GUP-DHI-DT-22-247 | 2022-03-14 | RC | DE-GUP-DT-E-22-224 | 2022-05-18 | D | CRS-GUP-DHI-DT-22-374 | 2022-05-30 | AC | DE-GUP-DT-E-22-304 | 2022-06-16 | 0(CP) | CRS-GUP-DHI-DT-22-508 | 2022-07-11 | AC | DE-GUP-DT-E-24-168 | 2024-06-28 | 1 | CRS-GUP-DHI-DT-25-049 | 2025-03-19 | AA
| GUP | XG02 | P0 | GKC | 120953 |  | GUP-XG02-P0GKC-120953 | POTABLE WATER SYSTEM_P&I DIAGRAM | FA | 2021-06-01 | 2022-06-18 | 플랜트기술팀(Mech.) | 조상환 |  |  | G | FA |  | CCPP | Potable Water | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-993 | 2023-12-14 | 2 | CRS-GUP-DHI-DT-23-2138 | 2023-11-17 | AA | DHI-GUP-DT-21-003 | 2021-05-28 | A | CRS-GUP-DHI-DT-21-034 | 2021-10-06 | RC | DHI-GUP-DT-21-125 | 2021-11-29 | B | CRS-GUP-DHI-DT-21-127 | 2022-01-11 | AC | DHI-GUP-DT-22-081 | 2022-02-18 | C | CRS-GUP-DHI-DT-22-247 | 2022-03-14 | RC | DE-GUP-DT-E-22-224 | 2022-05-18 | D | CRS-GUP-DHI-DT-22-374 | 2022-05-30 | AC | DE-GUP-DT-E-22-304 | 2022-06-16 | 0(CP) | CRS-GUP-DHI-DT-22-508 | 2022-07-11 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-23-864 | 2023-10-23 | 1(CP) | CRS-GUP-DHI-DT-23-2138 | 2023-11-17 | AA | DE-GUP-DT-E-23-993 | 2023-12-14 | 2
| GUP | XS00 | P0 | GKC | 120954 |  | GUP-XS00-P0GKC-120954 | POTABLE WATER SYSTEM_SYSTEM DESCRIPTION | FA | 2021-07-13 | 2022-06-18 | 플랜트기술팀(Mech.) | 조상환 |  | P | G | FA |  | CCPP | Potable Water | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-864 | 2023-10-23 | 1 | CRS-GUP-DHI-DT-23-2138 | 2023-11-17 | AA | DHI-GUP-DT-21-008 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-016 | 2021-09-29 | RC | DHI-GUP-DT-21-125 | 2021-11-29 | B | CRS-GUP-DHI-DT-21-127 | 2022-01-11 | AC | DHI-GUP-DT-22-081 | 2022-02-18 | C | CRS-GUP-DHI-DT-22-247 | 2022-03-14 | RC | DE-GUP-DT-E-22-224 | 2022-05-18 | D | CRS-GUP-DHI-DT-22-374 | 2022-05-30 | AC | DE-GUP-DT-E-22-304 | 2022-06-16 | 0(CP) | CRS-GUP-DHI-DT-22-508 | 2022-07-11 | AA | DE-GUP-DT-E-23-864 | 2023-10-23 | 1 | CRS-GUP-DHI-DT-23-2138 | 2023-11-17 | AA
| GUP | XW03 | P1 | SCA | 120955 |  | GUP-XW03-P1SCA-120955 | AIR COMPRESSOR_SIZING CALCULATION | FA | 2021-09-07 | 2022-08-15 | 플랜트기술팀(Mech.) | 조상환 |  | P |  |  |  | CCPP | Air Comp. | Mech. | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-172 | 2024-07-01 | 3 | CRS-GUP-DHI-DT-24-033 | 2024-03-12 | AA | DHI-GUP-DT-21-059 | 2021-10-08 | A | CRS-GUP-DHI-DT-21-044 | 2021-10-29 | RC | DHI-GUP-DT-21-198 | 2021-12-24 | B | CRS-GUP-DHI-DT-21-163 | 2022-01-17 | RC | DHI-GUP-DT-22-094 | 2022-02-25 | C | CRS-GUP-DHI-DT-22-257 | 2022-03-16 | RC | DE-GUP-DT-E-22-252 | 2022-05-27 | D | CRS-GUP-DHI-DT-22-453 | 2022-06-21 | AC | DE-GUP-DT-E-22-491 | 2022-08-10 | 0(CP) | CRS-GUP-DHI-DT-22-708 | 2022-09-05 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-1144 | 2022-12-21 | 1(CP) | 자체 CRS 개정 후 제출 | 2023-11-22 | N/A | DE-GUP-DT-E-23-941 | 2023-11-23 | 2(CP) | CRS-GUP-DHI-DT-24-033 | 2024-03-12 | AA | DE-GUP-DT-E-24-172 | 2024-07-01 | 3
| GUP | XW03 | P1 | GHD | 120956 |  | GUP-XW03-P1GHD-120956 | GSP(SERVICE WATER)_SIZING CALCULATION | FA | 2021-09-16 | 2022-07-01 | 플랜트기술팀(Mech.) | 조상환 |  | P |  |  |  | CCPP | GSP(Water) | Mech. | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-005 | 2024-01-05 | 1 | 자체 CRS 개정 후 제출 | 2024-01-04 | N/A | DHI-GUP-DT-21-153 | 2021-12-08 | A | CRS-GUP-DHI-DT-21-144 | 2022-01-12 | RC | DHI-GUP-DT-22-099 | 2022-03-07 | B | CRS-GUP-DHI-DT-22-265 | 2022-03-29 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-390 | 2022-07-13 | 0(CP) | 자체 CRS 개정 후 제출 | 2024-01-04 | N/A | DE-GUP-DT-E-24-005 | 2024-01-05 | 1
| GUP | XW03 | P1 | GKC | 120957 |  | GUP-XW03-P1GKC-120957 | GSP(POTABLE WATER)_SIZING CALCULATION | FA | 2021-09-16 | 2022-06-18 | 플랜트기술팀(Mech.) | 조상환 |  | P |  |  |  | CCPP | GSP(Water) | Mech. | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-864 | 2023-10-23 | 1 | CRS-GUP-DHI-DT-23-2138 | 2023-11-17 | AA | DHI-GUP-DT-21-125 | 2021-11-29 | A | CRS-GUP-DHI-DT-21-127 | 2022-01-11 | AC | DHI-GUP-DT-22-081 | 2022-02-18 | B | CRS-GUP-DHI-DT-22-247 | 2022-03-14 | RC | DE-GUP-DT-E-22-224 | 2022-05-18 | C | CRS-GUP-DHI-DT-22-374 | 2022-05-30 | AC | DE-GUP-DT-E-22-304 | 2022-06-16 | 0(CP) | CRS-GUP-DHI-DT-22-508 | 2022-07-11 | AA | DE-GUP-DT-E-23-864 | 2023-10-23 | 1 | CRS-GUP-DHI-DT-23-2138 | 2023-11-17 | AA
| GUP | XW03 | P0 | EG | 120958 |  | GUP-XW03-P0EG-120958 | GSP(OIL)_SIZING CALCULATION | FA | 2021-09-01 | 2022-09-30 | 플랜트기술팀(Mech.) | UPPALA |  | P |  |  |  | CCPP | GSP(Oil) | Mech. | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-225 | 2024-09-06 | 2 | 자체 CRS 개정 후 제출 | 2024-09-05 | N/A | DHI-GUP-DT-21-018 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-009 | 2021-09-28 | RC | DHI-GUP-DT-21-187 | 2021-12-17 | B | CRS-GUP-DHI-DT-21-135 | 2022-01-11 | AC | DHI-GUP-DT-22-089 | 2022-02-24 | C | CRS-GUP-DHI-DT-22-250 | 2022-03-14 | AC | DE-GUP-DT-E-22-753 | 2022-10-04 | D | CRS-GUP-DHI-DT-22-1073 | 2022-11-19 | AC | DE-GUP-DT-E-23-055 | 2023-01-19 | 0(CP) | CRS-GUP-DHI-DT-23-1656 | 2023-03-07 | AA | DE-GUP-DT-E-24-007 | 2024-01-10 | 1 | 자체 CRS 개정 후 제출 | 2024-09-05 | N/A | DE-GUP-DT-E-24-225 | 2024-09-06 | 2
| GUP | XG08 | P0 | EG | 120959 |  | GUP-XG08-P0EG-120959 | ULSD SYSTEM_PROCESS FLOW DIAGRAM | FA | 2021-09-17 | 2022-09-30 | 플랜트기술팀(Mech.) | UPPALA |  | P |  |  | ULSD | CCPP | ULSD | Mech. | 1 | 2025-06-30 |  |  | DE-GUP-DT-E-24-008 | 2024-01-10 | 3 | CRS-GUP-DHI-DT-23-1915 | 2023-05-05 | AA | DHI-GUP-DT-21-029 | 2021-09-17 | A | CRS-GUP-DHI-DT-21-034 | 2021-10-06 | RC | DHI-GUP-DT-21-187 | 2021-12-17 | B | CRS-GUP-DHI-DT-21-135 | 2022-01-11 | AC | DHI-GUP-DT-22-089 | 2022-02-24 | C | CRS-GUP-DHI-DT-22-250 | 2022-03-14 | AC | DE-GUP-DT-E-22-753 | 2022-10-04 | D | CRS-GUP-DHI-DT-22-1073 | 2022-11-19 | AC | DE-GUP-DT-E-23-055 | 2023-01-19 | 0(CP) | CRS-GUP-DHI-DT-23-1656 | 2023-03-07 | AA | DE-GUP-DT-E-23-490 | 2023-04-21 | 1 | CRS-GUP-DHI-DT-23-1915 | 2023-05-05 | AA | DE-GUP-DT-E-24-008 | 2024-01-10 | 3
| GUP | XW03 | P0 | GM | 120960 |  | GUP-XW03-P0GM-120960 | WASTE WATER TRANSFER SYSTEM_SIZING CALCULATION | FA | 2022-05-19 | 2022-09-19 | 플랜트기술팀(Mech.) | 조상환 |  | P |  |  | WASTE WATER TRANSFER | CCPP | Waste Water Transfer | Mech. | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-904 | 2023-11-10 | 1 | 자체 CRS 개정 후 제출 | 2023-11-09 | N/A | DE-GUP-DT-E-22-234 | 2022-05-20 | A | CRS-GUP-DHI-DT-22-403 | 2022-06-09 | RC | DE-GUP-DT-E-22-396 | 2022-07-13 | B | CRS-GUP-DHI-DT-22-611 | 2022-08-16 | RC | DE-GUP-DT-E-22-1035 | 2022-12-06 | C | CRS-GUP-DHI-DT-22-1287 | 2022-12-21 | AA | DE-GUP-DT-E-23-015 | 2023-01-12 | 0 | 자체 CRS 개정 후 제출 | 2023-11-09 | N/A | DE-GUP-DT-E-23-904 | 2023-11-10 | 1
| GUP | XA00 | P1 | SM | 120970 |  | GUP-XA00-P1SM-120970 | CRANE_GENERAL ARRANGEMENT DRAWING FOR STG BLDG | FA | 2022-06-30 | 2022-10-31 | 플랜트기술팀(Mech.) | 안성훈 |  | R |  |  | CRANE | CCPP | CRANE | Mech. | 2 | 2025-05-01 |  |  | DE-GUP-DT-E-23-683 | 2023-07-10 | 1 | 자체 CRS 개정 후 제출 | 2023-07-09 | N/A | DE-GUP-DT-E-22-300 | 2022-06-15 | A | CRS-GUP-DHI-DT-22-496 | 2022-07-06 | RC | DE-GUP-DT-E-22-609 | 2022-09-02 | B | CRS-GUP-DHI-DT-22-766 | 2022-09-14 | RC | DE-GUP-DT-E-22-721 | 2022-09-29 | C | CRS-GUP-DHI-DT-22-883 | 2022-10-09 | AA | DE-GUP-DT-E-22-1029 | 2022-12-05 | 0 | 자체 CRS 개정 후 제출 | 2023-07-09 | N/A | DE-GUP-DT-E-23-683 | 2023-07-10 | 1
| GUP | XA00 | P1 | SM | 120976 |  | GUP-XA00-P1SM-120976 | CRANE_GENERAL ARRANGEMENT DRAWING FOR WORKSHOP | FA | 2022-11-30 | 2023-02-28 | 플랜트기술팀(Mech.) | 안성훈 |  | R |  |  | CRANE | CCPP | CRANE | Mech. | 2 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-23-355 | 2023-03-24 | 0 | CRS-GUP-DHI-DT-23-1734 | 2023-03-17 | AA | DE-GUP-DT-E-22-892 | 2022-11-01 | A | CRS-GUP-DHI-DT-22-1179 | 2022-11-30 | RC | DE-GUP-DT-E-23-198 | 2023-02-17 | B | CRS-GUP-DHI-DT-23-1734 | 2023-03-17 | AA | DE-GUP-DT-E-23-355 | 2023-03-24 | 0
| GUP | YT01 | P1 | SM | 120971 |  | GUP-YT01-P1SM-120971 | CRANE_TECHNICAL DATA SHEETS | FA | 2022-06-30 | 2022-10-31 | 플랜트기술팀(Mech.) | 안성훈 |  | R |  |  | CRANE | CCPP | CRANE | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-355 | 2023-03-24 | 0 | CRS-GUP-DHI-DT-23-1734 | 2023-03-17 | AA | DE-GUP-DT-E-22-300 | 2022-06-15 | A | CRS-GUP-DHI-DT-22-496 | 2022-07-06 | RC | DE-GUP-DT-E-22-609 | 2022-09-02 | B | CRS-GUP-DHI-DT-22-1062 | 2022-11-19 | RC | DE-GUP-DT-E-23-198 | 2023-02-17 | C | CRS-GUP-DHI-DT-23-1734 | 2023-03-17 | AA | DE-GUP-DT-E-23-355 | 2023-03-24 | 0
| GUP | XA00 | P1 | SM | 120972 |  | GUP-XA00-P1SM-120972 | CRANE_MECHANICAL DETAIL DRAWING FOR STG BLDG | FI | 2022-09-30 |  | 플랜트기술팀(Mech.) | 안성훈 |  | R |  |  | CRANE | CCPP | CRANE | Mech. | 3 | 2025-05-01 |  |  | DE-GUP-DT-E-22-1165 | 2022-12-23 | 1 | CRS-GUP-DHI-DT-22-1346 | 2022-12-28 | NC | DE-GUP-DT-E-22-810 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1097 | 2022-11-21 | NC | DE-GUP-DT-E-22-1165 | 2022-12-23 | 1 | CRS-GUP-DHI-DT-22-1346 | 2022-12-28 | NC
| GUP | XA00 | P1 | SM | 120977 |  | GUP-XA00-P1SM-120977 | CRANE_MECHANICAL DETAIL DRAWING FOR WORKSHOP | FI | 2023-01-31 |  | 플랜트기술팀(Mech.) | 안성훈 |  | R |  |  | CRANE | CCPP | CRANE | Mech. | 3 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-23-816 | 2023-09-18 | 1 | CRS-GUP-DHI-DT-23-1611 | 2023-03-02 | NC | DE-GUP-DT-E-23-094 | 2023-01-30 | 0 | CRS-GUP-DHI-DT-23-1611 | 2023-03-02 | NC | DE-GUP-DT-E-23-816 | 2023-09-18 | 1
| GUP | XA00 | P1 | SM | 120973 |  | GUP-XA00-P1SM-120973 | CRANE_ELECTRICAL DETAIL DRAWING | FI | 2022-07-29 |  | 플랜트기술팀(Mech.) | 안성훈 |  | R |  |  | CRANE | CCPP | CRANE | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1166 | 2022-12-23 | 1 | CRS-GUP-DHI-DT-22-1357 | 2022-12-29 | NC | DE-GUP-DT-E-22-522 | 2022-08-19 | 0 | CRS-GUP-DHI-DT-22-717 | 2022-09-05 | NC | DE-GUP-DT-E-22-1166 | 2022-12-23 | 1 | CRS-GUP-DHI-DT-22-1357 | 2022-12-29 | NC
| GUP | XW03 | P1 | SM | 120974 |  | GUP-XW03-P1SM-120974 | CRANE_DESIGN BASIS REPORT | FI | 2022-07-29 |  | 플랜트기술팀(Mech.) | 안성훈 |  | R |  |  | CRANE | CCPP | CRANE | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-826 | 2022-10-20 | 1 | CRS-GUP-DHI-DT-22-1103 | 2022-11-21 | NC | DE-GUP-DT-E-22-492 | 2022-08-10 | 0 | CRS-GUP-DHI-DT-22-727 | 2022-09-09 | RC | DE-GUP-DT-E-22-826 | 2022-10-20 | 1 | CRS-GUP-DHI-DT-22-1103 | 2022-11-21 | NC
| GUP | YT10 | P1 | SM | 120975 |  | GUP-YT10-P1SM-120975 | CRANE_CALCULATION SHEET | FI | 2022-07-29 |  | 플랜트기술팀(Mech.) | 안성훈 |  | R |  |  | CRANE | CCPP | CRANE | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1165 | 2022-12-23 | 1 | CRS-GUP-DHI-DT-22-1346 | 2022-12-28 | NC | DE-GUP-DT-E-22-492 | 2022-08-10 | 0 | CRS-GUP-DHI-DT-22-727 | 2022-09-09 | NC | DE-GUP-DT-E-22-1165 | 2022-12-23 | 1 | CRS-GUP-DHI-DT-22-1346 | 2022-12-28 | NC
| GUP | CQ02 | P1 | SM | 120978 |  | GUP-CQ02-P1SM-120978 | CRANE AND HOIST_OPERATION & MAINTENANCE (O&M) MANUAL | FI | 2023-12-24 |  | 플랜트기술팀(Mech.) | 안성훈 |  |  |  |  | CRANE | CCPP | CRANE | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-073 | 2024-03-13 | 0 | CRS-GUP-DHI-DT-24-059 | 2024-07-04 | NC | DE-GUP-DT-E-24-073 | 2024-03-13 | 0 | CRS-GUP-DHI-DT-24-059 | 2024-07-04 | NC
| GUP | XS00 | P1 | HYA | 121000 |  | GUP-XS00-P1HYA-121000 | HRSG_SYSTEM DESCRIPTION | FA | 2021-09-13 | 2022-02-10 | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 1 | 2025-06-30 |  |  | DE-GUP-DT-E-24-098 | 2024-03-29 | 2 | CRS-GUP-DHI-DT-22-1137 | 2022-11-23 | AA | DHI-GUP-DT-21-025 | 2021-09-16 | A | CRS-GUP-DHI-DT-21-025 | 2021-10-04 | RC | DHI-GUP-DT-22-041 | 2022-01-27 | B | CRS-GUP-DHI-DT-21-196 | 2022-02-10 | RC | DHI-GUP-DT-22-145 | 2022-04-01 | C | CRS-GUP-DHI-DT-22-301 | 2022-04-17 | AC | DE-GUP-DT-E-22-543 | 2022-08-24 | 0(CP) | CRS-GUP-DHI-DT-22-744 | 2022-09-12 | AA | DE-GUP-DT-E-22-805 | 2022-10-14 | 1 | CRS-GUP-DHI-DT-22-1137 | 2022-11-23 | AA | DE-GUP-DT-E-24-098 | 2024-03-29 | 2
| GUP | XG02 | P1 | HYA | 121001 |  | GUP-XG02-P1HYA-121001 | HRSG_P&I DIAGRAM | FA | 2021-09-13 | 2022-02-10 | 플랜트기술팀(Mech.) | 박동준 |  |  | G | FI | HRSG | CCPP | HRSG | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-962 | 2022-11-21 | 0 | CRS-GUP-DHI-DT-22-1241 | 2022-12-13 | AA | DHI-GUP-DT-21-025 | 2021-09-16 | A | CRS-GUP-DHI-DT-21-038 | 2021-10-06 | RC | DE-GUP-DT-E-22-532 | 2022-08-23 | B | CRS-GUP-DHI-DT-22-759 | 2022-09-14 | AA | DE-GUP-DT-E-22-962 | 2022-11-21 | 0 | CRS-GUP-DHI-DT-22-1241 | 2022-12-13 | AA
| GUP | XB02 | P1 | HBA | 121002 |  | GUP-XB02-P1HBA-121002 | HRSG_SECONDARY FOUNDATION LOADING & LOCATION DRAWING | FA | 2021-12-12 | 2022-05-10 | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-095 | 2024-03-27 | 1 | CRS-GUP-DHI-DT-24-024 | 2024-03-11 | AA | DHI-GUP-DT-21-158 | 2021-12-09 | A | CRS-GUP-DHI-DT-21-113 | 2022-01-05 | RC | DHI-GUP-DT-22-041 | 2022-02-09 | B | CRS-GUP-DHI-DT-21-196 | 2022-02-10 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-570 | 2022-08-26 | 0(CP) | CRS-GUP-DHI-DT-24-024 | 2024-03-11 | AA | DE-GUP-DT-E-24-095 | 2024-03-27 | 1
| GUP | XW03 | P1 | HBA | 121011 |  | GUP-XW03-P1HBA-121011 | HRSG_COLUMN LOCATION FOR HRSG STEEL STRUCTURE AND STACK | FI | 2021-09-13 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-729 | 2022-09-30 | 3 | CRS-GUP-DHI-DT-22-889 | 2022-10-10 | NC | DHI-GUP-DT-21-026 | 2021-09-16 | 0 | CRS-GUP-DHI-DT-21-022 | 2021-10-04 | RC | DHI-GUP-DT-21-164 | 2021-12-10 | 1 | CRS-GUP-DHI-DT-21-116 | 2022-01-05 | I | DHI-GUP-DT-22-041 | 2022-01-27 | 2 | CRS-GUP-DHI-DT-21-196 | 2022-02-10 | RC | DE-GUP-DT-E-22-729 | 2022-09-30 | 3 | CRS-GUP-DHI-DT-22-889 | 2022-10-10 | NC
| GUP | XW03 | P1 | HBA | 121012 |  | GUP-XW03-P1HBA-121012 | HRSG_FOUNDATION LOAD TABLE FOR HRSG STEEL STRUCTURE AND STACK | FI | 2021-09-13 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-729 | 2022-09-30 | 3 | CRS-GUP-DHI-DT-22-889 | 2022-10-10 | NC | DHI-GUP-DT-21-026 | 2021-09-16 | 0 | CRS-GUP-DHI-DT-21-022 | 2021-10-04 | RC | DHI-GUP-DT-21-164 | 2021-12-10 | 1 | CRS-GUP-DHI-DT-21-116 | 2022-01-05 | I | DHI-GUP-DT-22-041 | 2022-01-27 | 2 | CRS-GUP-DHI-DT-21-196 | 2022-02-10 | RC | DE-GUP-DT-E-22-729 | 2022-09-30 | 3 | CRS-GUP-DHI-DT-22-889 | 2022-10-10 | NC
| GUP | XW03 | P1 | HBA | 121013 |  | GUP-XW03-P1HBA-121013 | HRSG_BASE PLATE AND ANCHOR BOLT DETAIL FOR HRSG (STEEL STRUCTURE)(1/2) | FI | 2021-09-13 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-729 | 2022-09-30 | 3 | CRS-GUP-DHI-DT-22-889 | 2022-10-10 | NC | DHI-GUP-DT-21-026 | 2021-09-16 | 0 | CRS-GUP-DHI-DT-21-022 | 2021-10-04 | RC | DHI-GUP-DT-21-164 | 2021-12-10 | 1 | CRS-GUP-DHI-DT-21-116 | 2022-01-05 | I | DHI-GUP-DT-22-041 | 2022-01-27 | 2 | CRS-GUP-DHI-DT-21-196 | 2022-02-10 | RC | DE-GUP-DT-E-22-729 | 2022-09-30 | 3 | CRS-GUP-DHI-DT-22-889 | 2022-10-10 | NC
| GUP | XW03 | P1 | HBA | 121014 |  | GUP-XW03-P1HBA-121014 | HRSG_BASE PLATE AND ANCHOR BOLT DETAIL FOR HRSG (STEEL STRUCTURE)(2/2) | FI | 2021-09-13 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-729 | 2022-09-30 | 3 | CRS-GUP-DHI-DT-22-889 | 2022-10-10 | NC | DHI-GUP-DT-21-026 | 2021-09-16 | 0 | CRS-GUP-DHI-DT-21-022 | 2021-10-04 | RC | DHI-GUP-DT-21-164 | 2021-12-10 | 1 | CRS-GUP-DHI-DT-21-116 | 2022-01-05 | I | DHI-GUP-DT-22-041 | 2022-01-27 | 2 | CRS-GUP-DHI-DT-21-196 | 2022-02-10 | RC | DE-GUP-DT-E-22-729 | 2022-09-30 | 3 | CRS-GUP-DHI-DT-22-889 | 2022-10-10 | NC
| GUP | XW03 | P1 | HBA | 121015 |  | GUP-XW03-P1HBA-121015 | HRSG_BASE PLATE AND ANCHOR BOLT DETAIL FOR HRSG MAIN STACK | FI | 2021-09-13 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-729 | 2022-09-30 | 2 | CRS-GUP-DHI-DT-22-889 | 2022-10-10 | NC | DHI-GUP-DT-21-026 | 2021-09-16 | 0 | CRS-GUP-DHI-DT-21-022 | 2021-10-04 | RC | DHI-GUP-DT-21-164 | 2021-12-10 | 1 | CRS-GUP-DHI-DT-21-116 | 2022-01-05 | I | DE-GUP-DT-E-22-729 | 2022-09-30 | 2 | CRS-GUP-DHI-DT-22-889 | 2022-10-10 | NC
| GUP | XW03 | P1 | HBA | 121016 |  | GUP-XW03-P1HBA-121016 | HRSG_BASE PLATE AND ANCHOR BOLT DETAIL FOR BYPASS STACK | FI | 2021-09-13 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-729 | 2022-09-30 | 3 | CRS-GUP-DHI-DT-22-889 | 2022-10-10 | NC | DHI-GUP-DT-21-026 | 2021-09-16 | 0 | CRS-GUP-DHI-DT-21-022 | 2021-10-04 | RC | DHI-GUP-DT-21-164 | 2021-12-10 | 1 | CRS-GUP-DHI-DT-21-116 | 2022-01-05 | I | DHI-GUP-DT-22-041 | 2022-01-27 | 2 | CRS-GUP-DHI-DT-21-196 | 2022-02-10 | RC | DE-GUP-DT-E-22-729 | 2022-09-30 | 3 | CRS-GUP-DHI-DT-22-889 | 2022-10-10 | NC
| GUP | XR01 | P1 | HAX | 121101 |  | GUP-XR01-P1HAX-121101 | HRSG_SPEC. & DRAWING FOR DESUPERHEATER | FA | 2022-08-15 | 2022-12-13 | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-010 | 2025-01-21 | 1 | CRS-GUP-DHI-DT-23-1524 | 2023-02-14 | AA | DE-GUP-DT-E-22-749 | 2022-10-04 | A | CRS-GUP-DHI-DT-22-1072 | 2022-11-19 | AA | DE-GUP-DT-E-23-017 | 2023-01-13 | 0 | CRS-GUP-DHI-DT-23-1524 | 2023-02-14 | AA | DE-GUP-DT-E-25-010 | 2025-01-21 | 1
| GUP | XR01 | P1 | HAN | 121102 |  | GUP-XR01-P1HAN-121102 | HRSG_SPEC. & DRAWING FOR BLOW DOWN TANK | FA | 2022-01-11 | 2022-06-10 | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-095 | 2024-03-27 | 1 | CRS-GUP-DHI-DT-22-762 | 2022-09-14 | AA | DHI-GUP-DT-21-119 | 2021-11-26 | A | CRS-GUP-DHI-DT-21-091 | 2021-12-23 | AC | DE-GUP-DT-E-22-568 | 2022-08-26 | 0(CP) | CRS-GUP-DHI-DT-22-762 | 2022-09-14 | AA | DE-GUP-DT-E-24-095 | 2024-03-27 | 1
| GUP | XR01 | P1 | HAN | 121104 |  | GUP-XR01-P1HAN-121104 | HRSG_SPEC. & DRAWING FOR SAFETY & RELIEF VALVE | FI | 2022-01-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-805 | 2022-10-14 | 2 | CRS-GUP-DHI-DT-22-1096 | 2022-11-21 | NC | DHI-GUP-DT-21-158 | 2021-12-09 | 0 | CRS-GUP-DHI-DT-21-113 | 2022-01-05 | NC | DE-GUP-DT-E-22-262 | 2022-06-02 | 1 | CRS-GUP-DHI-DT-22-478 | 2022-07-03 | NC | DE-GUP-DT-E-22-805 | 2022-10-14 | 2 | CRS-GUP-DHI-DT-22-1096 | 2022-11-21 | NC
| GUP | XR01 | P1 | HNA | 121105 |  | GUP-XR01-P1HNA-121105 | HRSG_SPEC. & DRAWING FOR STACK DAMPER | FI | 2022-01-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-914 | 2022-11-08 | 2 | CRS-GUP-DHI-DT-22-1030 | 2022-11-13 | NC | DHI-GUP-DT-22-006 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-171 | 2022-01-24 | NC | DE-GUP-DT-E-22-275 | 2022-06-08 | 1 | CRS-GUP-DHI-DT-22-461 | 2022-06-21 | NC | DE-GUP-DT-E-22-914 | 2022-11-08 | 2 | CRS-GUP-DHI-DT-22-1030 | 2022-11-13 | NC
| GUP | XR01 | P1 | HAN | 121106 |  | GUP-XR01-P1HAN-121106 | HRSG_SPEC. & DRAWING FOR VENT SILENCER | FI | 2022-01-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-010 | 2025-01-21 | 2 | CRS-GUP-DHI-DT-22-1005 | 2022-11-13 | NC | DHI-GUP-DT-22-006 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-171 | 2022-01-24 | NC | DE-GUP-DT-E-22-805 | 2022-10-14 | 1 | CRS-GUP-DHI-DT-22-1005 | 2022-11-13 | NC | DE-GUP-DT-E-25-010 | 2025-01-21 | 2
| GUP | XR01 | P1 | HBE | 121107 |  | GUP-XR01-P1HBE-121107 | HRSG_SPEC. & DRAWING FOR DEAERATOR | FA | 2022-01-11 | 2022-06-10 | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-797 | 2022-10-13 | 1 | CRS-GUP-DHI-DT-22-1092 | 2022-11-21 | AA | DHI-GUP-DT-21-119 | 2021-11-26 | A | CRS-GUP-DHI-DT-21-091 | 2021-12-23 | AC | DHI-GUP-DT-22-187 | 2022-04-25 | 0 | CRS-GUP-DHI-DT-22-344 | 2022-05-18 | AC | DE-GUP-DT-E-22-797 | 2022-10-13 | 1 | CRS-GUP-DHI-DT-22-1092 | 2022-11-21 | AA
| GUP | XR01 | P1 | HAN | 121108 |  | GUP-XR01-P1HAN-121108 | HRSG_SPEC. & DRAWING FOR BYPASS STACK SILENCER | FI | 2022-01-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-805 | 2022-10-14 | 1 | CRS-GUP-DHI-DT-22-1005 | 2022-11-13 | NC | DHI-GUP-DT-22-023 | 2022-01-26 | 0 | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | NC | DE-GUP-DT-E-22-805 | 2022-10-14 | 1 | CRS-GUP-DHI-DT-22-1005 | 2022-11-13 | NC
| GUP | XR01 | P1 | HYA | 121109 |  | GUP-XR01-P1HYA-121109 | HRSG_SPEC. & DRAWING FOR HOIST | FI | 2022-01-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1036 | 2022-12-06 | 1 | CRS-GUP-DHI-DT-22-1310 | 2022-12-22 | NC | DHI-GUP-DT-22-039 | 2022-01-27 | 0 | CRS-GUP-DHI-DT-22-220 | 2022-02-20 | NC | DE-GUP-DT-E-22-1036 | 2022-12-06 | 1 | CRS-GUP-DHI-DT-22-1310 | 2022-12-22 | NC
| GUP | XR01 | P1 | HTH | 121110 |  | GUP-XR01-P1HTH-121110 | HRSG_SPEC. & DRAWING FOR RECIRCULATION PUMP | FA | 2022-01-11 | 2022-06-10 | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-095 | 2024-03-27 | 1 | CRS-GUP-DHI-DT-22-723 | 2022-09-05 | AA | DHI-GUP-DT-21-158 | 2021-12-09 | A | CRS-GUP-DHI-DT-21-113 | 2022-01-05 | RC | DE-GUP-DT-E-22-257 | 2022-05-27 | B | CRS-GUP-DHI-DT-22-455 | 2022-06-21 | AC | DE-GUP-DT-E-22-544 | 2022-08-24 | 0(CP) | CRS-GUP-DHI-DT-22-723 | 2022-09-05 | AA | DE-GUP-DT-E-24-095 | 2024-03-27 | 1
| GUP | XR01 | P1 | HNA | 121111 |  | GUP-XR01-P1HNA-121111 | HRSG_SPEC. & DRAWING FOR DIVERTER DAMPER | FI | 2022-01-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-285 | 2024-12-03 | 4 | CRS-GUP-DHI-DT-23-1524 | 2023-02-14 | NC | DHI-GUP-DT-22-006 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-171 | 2022-01-24 | NC | DE-GUP-DT-E-22-275 | 2022-06-08 | 1 | CRS-GUP-DHI-DT-22-461 | 2022-06-21 | NC | DE-GUP-DT-E-22-797 | 2022-10-13 | 2 | CRS-GUP-DHI-DT-22-1004 | 2022-11-13 | NC | DE-GUP-DT-E-23-017 | 2023-01-13 | 3 | CRS-GUP-DHI-DT-23-1524 | 2023-02-14 | NC | DE-GUP-DT-E-24-285 | 2024-12-03 | 4
| GUP | XR01 | P1 | HSG | 121112 |  | GUP-XR01-P1HSG-121112 | HRSG_SPEC. & DRAWING FOR SCR | FI | 2022-02-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-797 | 2022-10-13 | 1 | CRS-GUP-DHI-DT-22-1092 | 2022-11-21 | NC | DHI-GUP-DT-22-023 | 2022-01-26 | 0 | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | NC | DE-GUP-DT-E-22-797 | 2022-10-13 | 1 | CRS-GUP-DHI-DT-22-1092 | 2022-11-21 | NC
| GUP | XR01 | P1 | HSY | 121294 |  | GUP-XR01-P1HSY-121294 | HRSG_SPEC. & DRAWING FOR VOC ANALYZER | FI | 2024-02-08 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-066 | 2024-03-06 | 0 | CRS-GUP-DHI-DT-24-071 | 2024-08-28 | NC | DE-GUP-DT-E-24-066 | 2024-03-06 | 0 | CRS-GUP-DHI-DT-24-071 | 2024-08-28 | NC
| GUP | XR01 | P1 | HNA | 121171 |  | GUP-XR01-P1HNA-121171 | HRSG_FOUNDATION DRAWING FOR DIVERTER DAMPER PACKAGE | FI | 2022-02-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Civil | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-285 | 2024-12-03 | 4 | CRS-GUP-DHI-DT-22-965 | 2022-11-07 | NC | DHI-GUP-DT-22-076 | 2022-03-06 | 0 | CRS-GUP-DHI-DT-22-237 | 2022-03-07 | NC | DE-GUP-DT-E-22-316 | 2022-06-20 | A | CRS-GUP-DHI-DT-22-605 | 2022-08-16 | RC | DE-GUP-DT-E-22-730 | 2022-09-30 | 2 | CRS-GUP-DHI-DT-22-890 | 2022-10-10 | NC | DE-GUP-DT-E-22-842 | 2022-10-21 | 3 | CRS-GUP-DHI-DT-22-965 | 2022-11-07 | NC | DE-GUP-DT-E-24-285 | 2024-12-03 | 4
| GUP | XR01 | P1 | HSG | 121116 |  | GUP-XR01-P1HSG-121116 | SCR PERFORMANCE SUMMARY INCLUDING AMMONIA CONSUMPTION FOR HRSG SCR | FI | 2022-02-11 |  | 플랜트기술팀(Mech.) | 박동준 |  |  | G | FI | HRSG | CCPP | HRSG | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-532 | 2022-08-23 | 0 | CRS-GUP-DHI-DT-22-782 | 2022-09-19 | AA | DHI-GUP-DT-22-023 | 2022-01-26 | A | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | AC | DE-GUP-DT-E-22-532 | 2022-08-23 | 0 | CRS-GUP-DHI-DT-22-782 | 2022-09-19 | AA
| GUP | XR01 | P1 | HSG | 121126 |  | GUP-XR01-P1HSG-121126 | DESIGN SPECIFICATION FOR HRSG SCR | FA | 2022-02-11 | 2022-06-11 | 플랜트기술팀(Mech.) | 박동준 |  |  | G | FI | HRSG | CCPP | HRSG | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-798 | 2022-10-13 | 0 | CRS-GUP-DHI-DT-22-1136 | 2022-11-23 | AA | DHI-GUP-DT-22-023 | 2022-01-26 | A | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | RC | DE-GUP-DT-E-22-528 | 2022-08-23 | B | CRS-GUP-DHI-DT-22-735 | 2022-09-12 | AA | DE-GUP-DT-E-22-798 | 2022-10-13 | 0 | CRS-GUP-DHI-DT-22-1136 | 2022-11-23 | AA
| GUP | XR01 | P1 | HSG | 121128 |  | GUP-XR01-P1HSG-121128 | AIG ARRAGEMENT DRAWING FOR HRSG SCR | FA | 2022-02-11 | 2022-06-11 | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-095 | 2024-03-27 | 1 | CRS-GUP-DHI-DT-24-023 | 2024-03-11 | AA | DHI-GUP-DT-22-023 | 2022-01-26 | A | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-569 | 2022-08-26 | 0(CP) | CRS-GUP-DHI-DT-24-023 | 2024-03-11 | AA | DE-GUP-DT-E-24-095 | 2024-03-27 | 1
| GUP | XR01 | P1 | HSG | 121129 |  | GUP-XR01-P1HSG-121129 | CATALYST FRAME & SEALING ARRANGEMENT DRAWING FOR HRSG SCR | FI | 2022-02-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-25-002 | 2025-01-17 | 1 | CRS-GUP-DHI-DT-22-785 | 2022-09-19 | NC | DHI-GUP-DT-22-023 | 2022-01-26 | A | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | AC | DE-GUP-DT-E-22-569 | 2022-08-26 | 0 | CRS-GUP-DHI-DT-22-785 | 2022-09-19 | NC | DE-GUP-DT-E-25-002 | 2025-01-17 | 1
| GUP | XR01 | P1 | HSG | 121130 |  | GUP-XR01-P1HSG-121130 | AMMONIA DISTRIBUTION HEADER DRAWING FOR HRSG SCR | FI | 2022-02-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-763 | 2022-10-07 | 1 | CRS-GUP-DHI-DT-22-1085 | 2022-11-21 | NC | DHI-GUP-DT-22-023 | 2022-01-26 | A | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | AC | DE-GUP-DT-E-22-569 | 2022-08-26 | 0 | CRS-GUP-DHI-DT-22-785 | 2022-09-19 | NC | DE-GUP-DT-E-22-763 | 2022-10-07 | 1 | CRS-GUP-DHI-DT-22-1085 | 2022-11-21 | NC
| GUP | XR01 | P1 | HSG | 121131 |  | GUP-XR01-P1HSG-121131 | CATALYST DATA SHEET & DRAWING FOR HRSG SCR | FA | 2022-02-11 | 2022-06-11 | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-095 | 2024-03-27 | 1 | CRS-GUP-DHI-DT-24-023 | 2024-03-11 | AA | DHI-GUP-DT-22-023 | 2022-01-26 | A | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-22-569 | 2022-08-26 | 0(CP) | CRS-GUP-DHI-DT-24-023 | 2024-03-11 | AA | DE-GUP-DT-E-24-095 | 2024-03-27 | 1
| GUP | XR01 | P1 | HSG | 121132 |  | GUP-XR01-P1HSG-121132 | CATALYST BLOCK DRAWING FOR HRSG SCR | FI | 2022-02-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-569 | 2022-08-26 | 0 | CRS-GUP-DHI-DT-22-785 | 2022-09-19 | NC | DHI-GUP-DT-22-023 | 2022-01-26 | A | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | AC | DE-GUP-DT-E-22-569 | 2022-08-26 | 0 | CRS-GUP-DHI-DT-22-785 | 2022-09-19 | NC
| GUP | XR01 | P1 | HSG | 121133 |  | GUP-XR01-P1HSG-121133 | AMMONIA STORAGE TANK DATA SHEET & DRAWING FOR HRSG SCR | FI | 2022-02-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-845 | 2022-10-24 | 1 | CRS-GUP-DHI-DT-22-1175 | 2022-11-30 | NC | DHI-GUP-DT-22-023 | 2022-01-26 | A | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | RC | DE-GUP-DT-E-22-419 | 2022-07-20 | 0 | CRS-GUP-DHI-DT-22-616 | 2022-08-16 | NC | DE-GUP-DT-E-22-845 | 2022-10-24 | 1 | CRS-GUP-DHI-DT-22-1175 | 2022-11-30 | NC
| GUP | XR01 | P1 | HSG | 121134 |  | GUP-XR01-P1HSG-121134 | AMMONIA DILUTION TANK DATA SHEET & DRAWING FOR HRSG SCR | FI | 2022-02-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-963 | 2022-11-21 | 1 | CRS-GUP-DHI-DT-22-1193 | 2022-11-30 | NC | DHI-GUP-DT-22-023 | 2022-01-26 | A | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | AC | DE-GUP-DT-E-22-532 | 2022-08-23 | 0 | CRS-GUP-DHI-DT-22-782 | 2022-09-19 | NC | DE-GUP-DT-E-22-963 | 2022-11-21 | 1 | CRS-GUP-DHI-DT-22-1193 | 2022-11-30 | NC
| GUP | XR01 | P1 | HSG | 121135 |  | GUP-XR01-P1HSG-121135 | HOT GAS CIRCULATION FAN DATA SHEET & DRAWING FOR HRSG SCR | FI | 2022-02-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-25-002 | 2025-01-17 | 2 | CRS-GUP-DHI-DT-22-1085 | 2022-11-21 | NC | DHI-GUP-DT-22-023 | 2022-01-26 | A | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | AC | DE-GUP-DT-E-22-532 | 2022-08-23 | 0 | CRS-GUP-DHI-DT-22-782 | 2022-09-19 | NC | DE-GUP-DT-E-22-763 | 2022-10-07 | 1 | CRS-GUP-DHI-DT-22-1085 | 2022-11-21 | NC | DE-GUP-DT-E-25-002 | 2025-01-17 | 2
| GUP | XR01 | P1 | HSG | 121136 |  | GUP-XR01-P1HSG-121136 | VAPORIZER DATA SHEET & DRAWING FOR HRSG SCR | FI | 2022-02-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-25-002 | 2025-01-17 | 2 | CRS-GUP-DHI-DT-22-1085 | 2022-11-21 | NC | DHI-GUP-DT-22-023 | 2022-01-26 | A | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | AC | DE-GUP-DT-E-22-569 | 2022-08-26 | 0 | CRS-GUP-DHI-DT-22-785 | 2022-09-19 | NC | DE-GUP-DT-E-22-763 | 2022-10-07 | 1 | CRS-GUP-DHI-DT-22-1085 | 2022-11-21 | NC | DE-GUP-DT-E-25-002 | 2025-01-17 | 2
| GUP | XR01 | P1 | HSG | 121137 |  | GUP-XR01-P1HSG-121137 | AMMONIA SUPPLY PUMP DATA SHEET & DRAWING FOR HRSG SCR | FI | 2022-02-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-564 | 2022-08-26 | 0 | CRS-GUP-DHI-DT-22-862 | 2022-09-26 | NC | DHI-GUP-DT-22-023 | 2022-01-26 | A | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | AC | DE-GUP-DT-E-22-564 | 2022-08-26 | 0 | CRS-GUP-DHI-DT-22-862 | 2022-09-26 | NC
| GUP | XR01 | P1 | HSG | 121138 |  | GUP-XR01-P1HSG-121138 | AMMONIA INJECTION NOZZLE DATA SHEET FOR HRSG SCR | FI | 2022-02-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-569 | 2022-08-26 | 0 | CRS-GUP-DHI-DT-22-785 | 2022-09-19 | NC | DHI-GUP-DT-22-023 | 2022-01-26 | A | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | AC | DE-GUP-DT-E-22-569 | 2022-08-26 | 0 | CRS-GUP-DHI-DT-22-785 | 2022-09-19 | NC
| GUP | XR01 | P1 | HSG | 121139 |  | GUP-XR01-P1HSG-121139 | AMMONIA FLOW CONTROL SKID LAYOUT DRAWING FOR HRSG SCR | FI | 2022-02-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1036 | 2022-12-06 | 2 | CRS-GUP-DHI-DT-22-1310 | 2022-12-22 | NC | DHI-GUP-DT-22-023 | 2022-01-26 | A | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | AC | DE-GUP-DT-E-22-569 | 2022-08-26 | 0 | CRS-GUP-DHI-DT-22-785 | 2022-09-19 | NC | DE-GUP-DT-E-22-983 | 2022-11-24 | 1 | CRS-GUP-DHI-DT-22-1206 | 2022-11-30 | NC | DE-GUP-DT-E-22-1036 | 2022-12-06 | 2 | CRS-GUP-DHI-DT-22-1310 | 2022-12-22 | NC
| GUP | XR01 | P1 | HSG | 121140 |  | GUP-XR01-P1HSG-121140 | EYE SHOWER DRAWING FOR HRSG SCR | FI | 2022-02-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-569 | 2022-08-26 | 0 | CRS-GUP-DHI-DT-22-785 | 2022-09-19 | NC | DHI-GUP-DT-22-023 | 2022-01-26 | A | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | AC | DE-GUP-DT-E-22-569 | 2022-08-26 | 0 | CRS-GUP-DHI-DT-22-785 | 2022-09-19 | NC
| GUP | XR01 | P1 | HSG | 121141 |  | GUP-XR01-P1HSG-121141 | CATALYST MATERIAL INFORMATION FOR HRSG SCR | FI | 2022-02-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DHI-GUP-DT-22-023 | 2022-01-26 | 0 | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | NC | DHI-GUP-DT-22-023 | 2022-01-26 | 0 | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | NC
| GUP | XR01 | P1 | HSG | 121142 |  | GUP-XR01-P1HSG-121142 | P&I DIAGRAM FOR HRSG SCR | FA | 2022-02-11 | 2022-06-11 | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-25-025 | 2025-02-13 | 2 | CRS-GUP-DHI-DT-22-1085 | 2022-11-21 | NC | DHI-GUP-DT-22-023 | 2022-01-26 | A | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | AC | DE-GUP-DT-E-22-532 | 2022-08-23 | 0 | CRS-GUP-DHI-DT-22-782 | 2022-09-19 | AA | DE-GUP-DT-E-22-763 | 2022-10-07 | 1 | CRS-GUP-DHI-DT-22-1085 | 2022-11-21 | NC | DE-GUP-DT-E-25-025 | 2025-02-13 | 2
| GUP | XR01 | P1 | HSG | 121147 |  | GUP-XR01-P1HSG-121147 | VALVE LIST FOR HRSG SCR | FI | 2022-04-08 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Piping | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-679 | 2022-09-16 | 1 | CRS-GUP-DHI-DT-22-906 | 2022-10-12 | NC | DHI-GUP-DT-22-169 | 2022-04-13 | 0 | CRS-GUP-DHI-DT-22-354 | 2022-05-20 | NC | DE-GUP-DT-E-22-679 | 2022-09-16 | 1 | CRS-GUP-DHI-DT-22-906 | 2022-10-12 | NC
| GUP | XR01 | P1 | HSG | 121148 |  | GUP-XR01-P1HSG-121148 | LINE LIST FOR HRSG SCR | FA | 2022-04-08 | 2022-07-08 | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Piping | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-679 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-906 | 2022-10-12 | AA | DHI-GUP-DT-22-169 | 2022-04-13 | A | CRS-GUP-DHI-DT-22-354 | 2022-05-20 | AC | DE-GUP-DT-E-22-679 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-906 | 2022-10-12 | AA
| GUP | XR01 | P1 | HSG | 121152 |  | GUP-XR01-P1HSG-121152 | PIPING MATERIAL SPECIFICATION FOR HRSG SCR | FA | 2022-02-11 | 2022-06-11 | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Piping | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-807 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1138 | 2022-11-23 | AA | DHI-GUP-DT-22-023 | 2022-01-26 | A | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | RC | DE-GUP-DT-E-22-542 | 2022-08-24 | B | CRS-GUP-DHI-DT-22-743 | 2022-09-12 | AA | DE-GUP-DT-E-22-807 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1138 | 2022-11-23 | AA
| GUP | XR01 | P1 | HSG | 121154 |  | GUP-XR01-P1HSG-121154 | SPECIAL ITEM LIST & DRAWING FOR HRSG SCR | FI | 2022-09-15 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Piping | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-845 | 2022-10-24 | 1 | CRS-GUP-DHI-DT-22-1015 | 2022-11-13 | NC | DE-GUP-DT-E-22-679 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-906 | 2022-10-12 | NC | DE-GUP-DT-E-22-845 | 2022-10-24 | 1 | CRS-GUP-DHI-DT-22-1015 | 2022-11-13 | NC
| GUP | XR01 | P1 | HSG | 121155 |  | GUP-XR01-P1HSG-121155 | EQUIPMENT FOUNDATION LOADING DRAWING & DATA FOR HRSG SCR INDOOR | FI | 2022-02-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Civil | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-542 | 2022-08-24 | 0 | CRS-GUP-DHI-DT-22-743 | 2022-09-12 | NC | DHI-GUP-DT-22-023 | 2022-01-26 | A | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | RC | DE-GUP-DT-E-22-542 | 2022-08-24 | 0 | CRS-GUP-DHI-DT-22-743 | 2022-09-12 | NC
| GUP | XR01 | P1 | HSG | 121156 |  | GUP-XR01-P1HSG-121156 | EQUIPMENT FOUNDATION LOADING DRAWING & DATA FOR HRSG SCR OUTDOOR | FI | 2022-02-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Civil | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-542 | 2022-08-24 | 0 | CRS-GUP-DHI-DT-22-1348 | 2022-12-28 | NC | DHI-GUP-DT-22-023 | 2022-01-26 | A | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | RC | DE-GUP-DT-E-22-542 | 2022-08-24 | 0 | CRS-GUP-DHI-DT-22-743 | 2022-09-12 | NC | DE-GUP-DT-E-22-1177 | ;2022-12-23 | 1 | CRS-GUP-DHI-DT-22-1348 | 2022-12-28 | NC
| GUP | XR01 | P1 | HSG | 121163 |  | GUP-XR01-P1HSG-121163 | SYSTEM CONFIGURATION FOR HRSG SCR | FI | 2022-02-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DHI-GUP-DT-22-023 | 2022-01-26 | 0 | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | NC | DHI-GUP-DT-22-023 | 2022-01-26 | 0 | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | NC
| GUP | XR01 | P1 | HSG | 121164 |  | GUP-XR01-P1HSG-121164 | CABLE LIST & SCHEDULE FOR HRSG SCR | FI | 2022-02-11 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-758 | 2022-10-05 | 0 | CRS-GUP-DHI-DT-22-928 | 2022-10-19 | NC | DHI-GUP-DT-22-023 | 2022-01-26 | A | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | RC | DE-GUP-DT-E-22-758 | 2022-10-05 | 0 | CRS-GUP-DHI-DT-22-928 | 2022-10-19 | NC
| GUP | XR01 | P1 | HSG | 121165 |  | GUP-XR01-P1HSG-121165 | CABLE INTERCONNECTION WIRING DIAGRAM FOR HRSG SCR | FA | 2022-04-08 | 2022-07-08 | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-004 | 2025-01-17 | 1 | 자체 CRS 개정 후 제출 | 2025-01-16 | N/A | DHI-GUP-DT-22-169 | 2022-04-13 | A | CRS-GUP-DHI-DT-22-331 | 2022-05-20 | RC | DE-GUP-DT-E-22-681 | 2022-09-16 | B | CRS-GUP-DHI-DT-22-907 | 2022-10-12 | AA | DE-GUP-DT-E-22-963 | 2022-11-21 | 0 | 자체 CRS 개정 후 제출 | 2025-01-16 | N/A | DE-GUP-DT-E-25-004 | 2025-01-17 | 1
| GUP | XR01 | P1 | HSG | 121166 |  | GUP-XR01-P1HSG-121166 | CONDUIT & CABLE TRAY LAYOUT DRAWING FOR HRSG SCR | FI | 2022-02-11 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-845 | 2022-10-24 | 0 | CRS-GUP-DHI-DT-22-1015 | 2022-11-13 | NC | DHI-GUP-DT-22-023 | 2022-01-26 | A | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | RC | DE-GUP-DT-E-22-845 | 2022-10-24 | 0 | CRS-GUP-DHI-DT-22-1015 | 2022-11-13 | NC
| GUP | XR01 | P1 | HSG | 121167 |  | GUP-XR01-P1HSG-121167 | EARTHING DRAWING FOR HRSG SCR | FA | 2022-04-08 | 2022-07-08 | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-681 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-907 | 2022-10-12 | AA | DHI-GUP-DT-22-169 | 2022-04-13 | A | CRS-GUP-DHI-DT-22-354 | 2022-05-20 | AA | DE-GUP-DT-E-22-681 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-907 | 2022-10-12 | AA
| GUP | XR01 | P1 | HSG | 121169 |  | GUP-XR01-P1HSG-121169 | JUNCTION BOX LAYOUT DRAWING FOR HRSG SCR | FA | 2022-04-08 | 2022-07-08 | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-004 | 2025-01-17 | 2 | CRS-GUP-DHI-DT-22-1242 | 2022-12-13 | AA | DHI-GUP-DT-22-169 | 2022-04-13 | A | CRS-GUP-DHI-DT-22-354 | 2022-05-20 | AA | DE-GUP-DT-E-22-277 | 2022-06-08 | 0 | CRS-GUP-DHI-DT-22-463 | 2022-06-21 | NC | DE-GUP-DT-E-22-681 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-907 | 2022-10-12 | AA | DE-GUP-DT-E-22-963 | 2022-11-21 | 1 | CRS-GUP-DHI-DT-22-1242 | 2022-12-13 | AA | DE-GUP-DT-E-25-004 | 2025-01-17 | 2
| GUP | XR01 | P1 | HSG | 121172 |  | GUP-XR01-P1HSG-121172 | FUNCTIONAL VALVE LIST AND DATA SHEET FOR HRSG SCR | FA | 2022-04-08 | 2022-07-08 | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-025 | 2025-02-13 | 2 | 자체 CRS 개정 후 제출 | 2025-02-12 | N/A | DHI-GUP-DT-22-169 | 2022-04-13 | A | CRS-GUP-DHI-DT-22-354 | 2022-05-20 | AA | DE-GUP-DT-E-22-678 | 2022-09-16 | 0(CP) | CRS-GUP-DHI-DT-22-905 | 2022-10-12 | NC | DE-GUP-DT-E-24-095 | 2024-03-27 | 1 | 자체 CRS 개정 후 제출 | 2025-02-12 | N/A | DE-GUP-DT-E-25-025 | 2025-02-13 | 2
| GUP | XR01 | P1 | HSG | 121173 |  | GUP-XR01-P1HSG-121173 | INSTRUMENT LIST FOR HRSG SCR | FI | 2022-02-11 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DHI-GUP-DT-22-023 | 2022-01-26 | 0 | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | NC | DHI-GUP-DT-22-023 | 2022-01-26 | 0 | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | NC
| GUP | XR01 | P1 | HSG | 121174 |  | GUP-XR01-P1HSG-121174 | INSTRUMENT DATA SHEET & DRAWING FOR HRSG SCR | FI | 2022-02-11 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-763 | 2022-10-07 | 1 | CRS-GUP-DHI-DT-22-929 | 2022-10-19 | NC | DHI-GUP-DT-22-023 | 2022-01-26 | A | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | AC | DE-GUP-DT-E-22-542 | 2022-08-24 | 0 | CRS-GUP-DHI-DT-22-722 | 2022-09-05 | NC | DE-GUP-DT-E-22-763 | 2022-10-07 | 1 | CRS-GUP-DHI-DT-22-929 | 2022-10-19 | NC
| GUP | XR01 | P1 | HSG | 121175 |  | GUP-XR01-P1HSG-121175 | INSTRUMENT INSTALLATION DRAWING FOR HRSG SCR | FA | 2022-04-08 | 2022-07-08 | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-681 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-354 | 2022-05-20 | AA | DHI-GUP-DT-22-169 | 2022-04-13 | A | CRS-GUP-DHI-DT-22-354 | 2022-05-20 | AA | DE-GUP-DT-E-22-681 | 2022-09-16 | 0
| GUP | XR01 | P1 | HSG | 121176 |  | GUP-XR01-P1HSG-121176 | INSTRUMENT LOCATION DRAWING FOR HRSG SCR | FI | 2022-02-11 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-681 | 2022-09-16 | 1 | CRS-GUP-DHI-DT-22-907 | 2022-10-12 | NC | DHI-GUP-DT-22-023 | 2022-01-26 | 0 | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | NC | DE-GUP-DT-E-22-681 | 2022-09-16 | 1 | CRS-GUP-DHI-DT-22-907 | 2022-10-12 | NC
| GUP | XR01 | P1 | HSG | 121177 |  | GUP-XR01-P1HSG-121177 | GAS ANALYZER DATA SHEET & DRAWING FOR SCR | FI | 2022-02-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-569 | 2022-08-26 | 0 | CRS-GUP-DHI-DT-22-840 | 2022-09-24 | NC | DHI-GUP-DT-22-023 | 2022-01-26 | A | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | AC | DE-GUP-DT-E-22-569 | 2022-08-26 | 0 | CRS-GUP-DHI-DT-22-840 | 2022-09-24 | NC
| GUP | XR01 | P1 | HSG | 121178 |  | GUP-XR01-P1HSG-121178 | CONTROL LOGIC DIAGRAM FOR HRSG SCR | FI | 2022-04-08 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-024 | 2025-02-13 | 3 | 자체 CRS 개정 후 제출 | 2025-02-12 | N/A | DHI-GUP-DT-22-169 | 2022-04-13 | 0 | CRS-GUP-DHI-DT-22-354 | 2022-05-20 | NC | DE-GUP-DT-E-22-681 | 2022-09-16 | 1 | CRS-GUP-DHI-DT-22-907 | 2022-10-12 | NC | DE-GUP-DT-E-25-004 | 2025-01-17 | 2 | 자체 CRS 개정 후 제출 | 2025-02-12 | N/A | DE-GUP-DT-E-25-024 | 2025-02-13 | 3
| GUP | XR01 | P1 | HSG | 121179 |  | GUP-XR01-P1HSG-121179 | CONTROL LOOP DIAGRAM FOR HRSG SCR | FI | 2022-04-08 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-024 | 2025-02-13 | 2 | CRS-GUP-DHI-DT-22-907 | 2022-10-12 | NC | DHI-GUP-DT-22-169 | 2022-04-13 | 0 | CRS-GUP-DHI-DT-22-354 | 2022-05-20 | NC | DE-GUP-DT-E-22-681 | 2022-09-16 | 1 | CRS-GUP-DHI-DT-22-907 | 2022-10-12 | NC | DE-GUP-DT-E-25-024 | 2025-02-13 | 2
| GUP | XR01 | P1 | HSY | 121113 |  | GUP-XR01-P1HSY-121113 | HRSG_SPEC. & DRAWING FOR CEMS | FI | 2022-02-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-002 | 2025-01-17 | 4 | CRS-GUP-DHI-DT-22-1286 | 2022-12-21 | NC | DHI-GUP-DT-22-023 | 2022-01-26 | 0 | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | NC | DE-GUP-DT-E-22-626 | 2022-09-07 | 1 | CRS-GUP-DHI-DT-22-850 | 2022-09-24 | NC | DE-GUP-DT-E-22-921 | 2022-11-08 | 2 | CRS-GUP-DHI-DT-22-1183 | 2022-11-30 | NC | DE-GUP-DT-E-22-1034 | 2022-12-05 | 3 | CRS-GUP-DHI-DT-22-1286 | 2022-12-21 | NC | DE-GUP-DT-E-25-002 | 2025-01-17 | 4
| GUP | XR01 | P1 | HSY | 121193 |  | GUP-XR01-P1HSY-121193 | HRSG_SYSTEM CONFIGURATION FOR CEMS | FI | 2022-02-11 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-921 | 2022-11-08 | 2 | CRS-GUP-DHI-DT-22-1183 | 2022-11-30 | NC | DHI-GUP-DT-22-023 | 2022-01-26 | 0 | CRS-GUP-DHI-DT-22-221 | 2022-02-21 | NC | DE-GUP-DT-E-22-626 | 2022-09-07 | 1 | CRS-GUP-DHI-DT-22-850 | 2022-09-24 | NC | DE-GUP-DT-E-22-921 | 2022-11-08 | 2 | CRS-GUP-DHI-DT-22-1183 | 2022-11-30 | NC
| GUP | XR01 | P1 | HSY | 121194 |  | GUP-XR01-P1HSY-121194 | HRSG_PANEL LAYOUT DRAWING FOR CEMS | FI | 2022-03-24 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-004 | 2025-01-17 | 4 | CRS-GUP-DHI-DT-22-1286 | 2022-12-21 | NC | DHI-GUP-DT-22-168 | 2022-04-12 | 0 | CRS-GUP-DHI-DT-22-340 | 2022-05-18 | NC | DE-GUP-DT-E-22-626 | 2022-09-07 | 1 | CRS-GUP-DHI-DT-22-850 | 2022-09-24 | NC | DE-GUP-DT-E-22-921 | 2022-11-08 | 2 | CRS-GUP-DHI-DT-22-1032 | 2022-11-13 | NC | DE-GUP-DT-E-22-1034 | 2022-12-05 | 3 | CRS-GUP-DHI-DT-22-1286 | 2022-12-21 | NC | DE-GUP-DT-E-25-004 | 2025-01-17 | 4
| GUP | XR01 | P1 | HSY | 121195 |  | GUP-XR01-P1HSY-121195 | HRSG_SHELTER LAYOUT DRAWING FOR CEMS | FI | 2022-03-24 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-002 | 2025-01-17 | 4 | CRS-GUP-DHI-DT-22-1286 | 2022-12-21 | NC | DHI-GUP-DT-22-168 | 2022-04-12 | 0 | CRS-GUP-DHI-DT-22-340 | 2022-05-18 | NC | DE-GUP-DT-E-22-626 | 2022-09-07 | 1 | CRS-GUP-DHI-DT-22-850 | 2022-09-24 | NC | DE-GUP-DT-E-22-921 | 2022-11-08 | 2 | CRS-GUP-DHI-DT-22-1032 | 2022-11-13 | NC | DE-GUP-DT-E-22-1034 | 2022-12-05 | 3 | CRS-GUP-DHI-DT-22-1286 | 2022-12-21 | NC | DE-GUP-DT-E-25-002 | 2025-01-17 | 4
| GUP | XR01 | P1 | HSY | 121196 |  | GUP-XR01-P1HSY-121196 | HMI GRAPHIC FOR CEMS | FI | 2022-04-12 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-004 | 2025-01-17 | 1 | CRS-GUP-DHI-DT-22-340 | 2022-05-18 | NC | DHI-GUP-DT-22-168 | 2022-04-12 | 0 | CRS-GUP-DHI-DT-22-340 | 2022-05-18 | NC | DE-GUP-DT-E-25-004 | 2025-01-17 | 1
| GUP | XR01 | P1 | HNA | 121197 |  | GUP-XR01-P1HNA-121197 | SYSTEM DESCRIPTOIN FOR DIVERTER DAMPER | FI | 2022-06-08 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-983 | 2022-11-24 | 1 | CRS-GUP-DHI-DT-22-1206 | 2022-11-30 | NC | N/A | N/A | N/A | N/A | N/A | N/A | DE-GUP-DT-E-22-983 | 2022-11-24 | 1 | CRS-GUP-DHI-DT-22-1206 | 2022-11-30 | NC
| GUP | XR01 | P1 | HNA | 121200 |  | GUP-XR01-P1HNA-121200 | VALVE LIST & DATA SHEET FOR DIVERTER DAMPER | FI | 2022-06-08 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-983 | 2022-11-24 | 1 | CRS-GUP-DHI-DT-22-1206 | 2022-11-30 | NC | DE-GUP-DT-E-22-277 | 2022-06-08 | 0 | CRS-GUP-DHI-DT-22-463 | 2022-06-21 | NC | DE-GUP-DT-E-22-983 | 2022-11-24 | 1 | CRS-GUP-DHI-DT-22-1206 | 2022-11-30 | NC
| GUP | XR01 | P1 | HNA | 121181 |  | GUP-XR01-P1HNA-121181 | CABLE TRAY & CONDUIT ROUTE DRAWING FOR DIVERTER DAMPER | FI | 2022-06-08 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-277 | 2022-06-08 | 0 | CRS-GUP-DHI-DT-22-463 | 2022-06-21 | NC | DE-GUP-DT-E-22-277 | 2022-06-08 | 0 | CRS-GUP-DHI-DT-22-463 | 2022-06-21 | NC
| GUP | XR01 | P1 | HNA | 121185 |  | GUP-XR01-P1HNA-121185 | CABLE SCHDULE DIAGRAM FOR DIVERTER DAMPER | FI | 2022-06-08 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-003 | 2025-01-17 | 2 | 자체 CRS 개정 후 제출 | 2025-01-16 | N/A | DE-GUP-DT-E-22-277 | 2022-06-08 | 0 | CRS-GUP-DHI-DT-22-463 | 2022-06-21 | NC | DE-GUP-DT-E-24-286 | 2024-12-03 | 1 | 자체 CRS 개정 후 제출 | 2025-01-16 | N/A | DE-GUP-DT-E-25-003 | 2025-01-17 | 2
| GUP | XR01 | P1 | HNA | 121187 |  | GUP-XR01-P1HNA-121187 | CABLE INTERCONNECTION WIRING DIAGRAM FOR DIVERTER DAMPER | FI | 2022-06-08 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-286 | 2024-12-03 | 1 | CRS-GUP-DHI-DT-22-463 | 2022-06-21 | NC | DE-GUP-DT-E-22-277 | 2022-06-08 | 0 | CRS-GUP-DHI-DT-22-463 | 2022-06-21 | NC | DE-GUP-DT-E-24-286 | 2024-12-03 | 1
| GUP | XR01 | P1 | HNA | 121190 |  | GUP-XR01-P1HNA-121190 | INSTRUMENT DATA SHEET & DRAWING & CATALOG FOR DIVERTER DAMPER | FI | 2022-06-08 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-286 | 2024-12-03 | 1 | CRS-GUP-DHI-DT-22-463 | 2022-06-21 | NC | DE-GUP-DT-E-22-277 | 2022-06-08 | 0 | CRS-GUP-DHI-DT-22-463 | 2022-06-21 | NC | DE-GUP-DT-E-24-286 | 2024-12-03 | 1
| GUP | XR01 | P1 | HNA | 121191 |  | GUP-XR01-P1HNA-121191 | POWER DISTRIBUTION PANEL DRAWING FOR DIVERTER DAMPER | FI | 2022-06-08 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-287 | 2024-12-03 | 2 | CRS-GUP-DHI-DT-22-1030 | 2022-11-13 | NC | DE-GUP-DT-E-22-277 | 2022-06-08 | 0 | CRS-GUP-DHI-DT-22-463 | 2022-06-21 | NC | DE-GUP-DT-E-22-914 | 2022-11-08 | 1 | CRS-GUP-DHI-DT-22-1030 | 2022-11-13 | NC | DE-GUP-DT-E-24-287 | 2024-12-03 | 2
| GUP | YD00 | P1 | HBK | 121010 |  | GUP-YD00-P1HBK-121010 | HRSG_GENERAL ARRANGEMENT | FA | 2021-10-13 | 2022-03-12 | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-25-010 | 2025-01-21 | 2 | CRS-GUP-DHI-DT-22-1124 | 2022-11-23 | AA | DHI-GUP-DT-21-025 | 2021-09-16 | A | CRS-GUP-DHI-DT-21-026 | 2021-10-04 | AC | DHI-GUP-DT-22-048 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-207 | 2022-02-28 | RC | DE-GUP-DT-E-22-720 | 2022-09-29 | 1 | CRS-GUP-DHI-DT-22-1124 | 2022-11-23 | AA | DE-GUP-DT-E-25-010 | 2025-01-21 | 2
| GUP | XR01 | P1 | HYA | 121027 |  | GUP-XR01-P1HYA-121027 | HRSG_SPECIALTY DATA SHEET & DRAWING | FA | 2021-11-12 | 2022-06-30 | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-805 | 2022-10-14 | 0 | CRS-GUP-DHI-DT-22-1137 | 2022-11-23 | AA | DHI-GUP-DT-21-078 | 2021-10-28 | A | CRS-GUP-DHI-DT-21-062 | 2021-11-17 | AA | DE-GUP-DT-E-22-805 | 2022-10-14 | 0 | CRS-GUP-DHI-DT-22-1137 | 2022-11-23 | AA
| GUP | DE00 | P1 | HYA | 121026 |  | GUP-DE00-P1HYA-121026 | HRSG_PIPING MATERIAL CLASSIFICATION (FOR HRSG) | FA | 2021-12-12 | 2022-09-30 | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Piping | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-002 | 2023-01-11 | 0 | CRS-GUP-DHI-DT-22-1090 | 2022-11-21 | AA | DHI-GUP-DT-21-025 | 2021-09-16 | A | CRS-GUP-DHI-DT-21-026 | 2021-10-04 | RR | DE-GUP-DT-E-22-787 | 2022-10-11 | B | CRS-GUP-DHI-DT-22-1090 | 2022-11-21 | AA | DE-GUP-DT-E-23-002 | 2023-01-11 | 0
| GUP | XN00 | P1 | HYB | 121018 |  | GUP-XN00-P1HYB-121018 | HRSG_MOV LIST | FI | 2021-11-12 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-785 | 2022-10-11 | 2 | CRS-GUP-DHI-DT-22-976 | 2022-11-07 | NC | DHI-GUP-DT-21-078 | 2021-10-28 | 0 | CRS-GUP-DHI-DT-21-062 | 2021-11-17 | RC | DE-GUP-DT-E-22-246 | 2022-05-24 | 1 | CRS-GUP-DHI-DT-22-448 | 2022-06-17 | NC | DE-GUP-DT-E-22-785 | 2022-10-11 | 2 | CRS-GUP-DHI-DT-22-976 | 2022-11-07 | NC
| GUP | YL30 | P1 | HYB | 121019 |  | GUP-YL30-P1HYB-121019 | HRSG_CONTROL VALVE LIST | FI | 2021-11-12 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-785 | 2022-10-11 | 1 | CRS-GUP-DHI-DT-22-976 | 2022-11-07 | NC | DHI-GUP-DT-21-078 | 2021-10-28 | 0 | CRS-GUP-DHI-DT-21-062 | 2021-11-17 | RC | DE-GUP-DT-E-22-785 | 2022-10-11 | 1 | CRS-GUP-DHI-DT-22-976 | 2022-11-07 | NC
| GUP | XV00 | P1 | HYA | 121020 |  | GUP-XV00-P1HYA-121020 | HRSG_LINE LIST | FI | 2021-11-12 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Piping | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-797 | 2022-10-13 | 1 | CRS-GUP-DHI-DT-22-1004 | 2022-11-13 | NC | DHI-GUP-DT-21-078 | 2021-10-28 | 0 | CRS-GUP-DHI-DT-21-062 | 2021-11-17 | NC | DE-GUP-DT-E-22-797 | 2022-10-13 | 1 | CRS-GUP-DHI-DT-22-1004 | 2022-11-13 | NC
| GUP | YF00 | P1 | HYB | 121031 |  | GUP-YF00-P1HYB-121031 | HRSG_SYSTEM CONFIGURATION DIAGRAM | FA | 2021-10-13 | 2022-06-30 | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-805 | 2022-10-14 | 0 | CRS-GUP-DHI-DT-22-1137 | 2022-11-23 | AA | DHI-GUP-DT-21-025 | 2021-09-16 | A | CRS-GUP-DHI-DT-21-025 | 2021-10-04 | RC | DHI-GUP-DT-22-048 | 2022-01-28 | B | CRS-GUP-DHI-DT-22-207 | 2022-02-28 | AA | DE-GUP-DT-E-22-805 | 2022-10-14 | 0 | CRS-GUP-DHI-DT-22-1137 | 2022-11-23 | AA
| GUP | YD05 | P1 | HYB | 121032 |  | GUP-YD05-P1HYB-121032 | HRSG_HMI GRAPHIC FOR DCS INTERFACE | FI | 2021-10-13 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-785 | 2022-10-11 | 1 | CRS-GUP-DHI-DT-22-976 | 2022-11-07 | NC | DHI-GUP-DT-21-026 | 2021-09-16 | 0 | CRS-GUP-DHI-DT-21-064 | 2021-11-17 | NC | DE-GUP-DT-E-22-785 | 2022-10-11 | 1 | CRS-GUP-DHI-DT-22-976 | 2022-11-07 | NC
| GUP | YL00 | P1 | HYB | 121025 |  | GUP-YL00-P1HYB-121025 | HRSG_INSTRUMENT LIST | FI | 2021-09-13 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-785 | 2022-10-11 | 3 | CRS-GUP-DHI-DT-22-976 | 2022-11-07 | NC | DHI-GUP-DT-21-026 | 2021-09-16 | 0 | CRS-GUP-DHI-DT-21-064 | 2021-11-17 | NC | DHI-GUP-DT-22-048 | 2022-01-28 | 1 | CRS-GUP-DHI-DT-22-207 | 2022-02-28 | NC | DE-GUP-DT-E-22-332 | 2022-06-24 | 2 | CRS-GUP-DHI-DT-22-529 | 2022-07-19 | NC | DE-GUP-DT-E-22-785 | 2022-10-11 | 3 | CRS-GUP-DHI-DT-22-976 | 2022-11-07 | NC
| GUP | YF00 | P1 | HYB | 121033 |  | GUP-YF00-P1HYB-121033 | HRSG_CONTROL LOGIC DIAGRAM | FI | 2021-12-12 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-594 | 2022-08-31 | 1 | CRS-GUP-DHI-DT-22-796 | 2022-09-19 | NC | DHI-GUP-DT-21-119 | 2021-11-26 | 0 | CRS-GUP-DHI-DT-21-091 | 2021-12-23 | NC | DE-GUP-DT-E-22-594 | 2022-08-31 | 1 | CRS-GUP-DHI-DT-22-796 | 2022-09-19 | NC
| GUP | YF00 | P1 | HYB | 121034 |  | GUP-YF00-P1HYB-121034 | HRSG_CONTROL LOOP DIAGRAM | FI | 2021-12-12 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-594 | 2022-08-31 | 1 | CRS-GUP-DHI-DT-22-796 | 2022-09-19 | NC | DHI-GUP-DT-21-119 | 2021-11-26 | 0 | CRS-GUP-DHI-DT-21-091 | 2021-12-23 | NC | DE-GUP-DT-E-22-594 | 2022-08-31 | 1 | CRS-GUP-DHI-DT-22-796 | 2022-09-19 | NC
| GUP | XR01 | P1 | HYA | 121028 |  | GUP-XR01-P1HYA-121028 | HRSG_MANUAL VALVE LIST & DRAWINGS | FI | 2022-01-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-805 | 2022-10-14 | 1 | CRS-GUP-DHI-DT-22-1005 | 2022-11-13 | NC | DHI-GUP-DT-21-078 | 2021-10-28 | 0 | CRS-GUP-DHI-DT-21-062 | 2021-11-17 | NC | DE-GUP-DT-E-22-805 | 2022-10-14 | 1 | CRS-GUP-DHI-DT-22-1005 | 2022-11-13 | NC
| GUP | XR01 | P1 | HYB | 121041 |  | GUP-XR01-P1HYB-121041 | HRSG_MOV DATA SHEET & DRAWINGS | FI | 2022-01-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1067 | 2022-12-09 | 3 | CRS-GUP-DHI-DT-22-1363 | 2022-12-30 | NC | DHI-GUP-DT-21-119 | 2021-11-26 | 0 | CRS-GUP-DHI-DT-21-091 | 2021-12-23 | NC | DE-GUP-DT-E-22-332 | 2022-06-24 | 1 | CRS-GUP-DHI-DT-22-529 | 2022-07-19 | NC | DE-GUP-DT-E-22-785 | 2022-10-11 | 2 | CRS-GUP-DHI-DT-22-976 | 2022-11-07 | NC | DE-GUP-DT-E-22-1067 | 2022-12-09 | 3 | CRS-GUP-DHI-DT-22-1363 | 2022-12-30 | NC
| GUP | XR01 | P1 | HYB | 121042 |  | GUP-XR01-P1HYB-121042 | HRSG_CONTROL VALVE DATA SHEET & DRAWINGS | FI | 2022-08-15 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-546 | 2022-08-24 | 0 | CRS-GUP-DHI-DT-22-745 | 2022-09-12 | NC | DE-GUP-DT-E-22-546 | 2022-08-24 | 0 | CRS-GUP-DHI-DT-22-745 | 2022-09-12 | NC
| GUP | XR01 | P1 | HYB | 121043 |  | GUP-XR01-P1HYB-121043 | HRSG LEVEL GAUGE DATA SHEET & DRAWINGS & CATALOG | FI | 2022-01-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-638 | 2022-09-08 | 2 | CRS-GUP-DHI-DT-22-808 | 2022-09-19 | NC | DHI-GUP-DT-21-078 | 2021-10-28 | 0 | CRS-GUP-DHI-DT-21-062 | 2021-11-17 | NC | DE-GUP-DT-E-22-332 | 2022-06-24 | 1 | CRS-GUP-DHI-DT-22-529 | 2022-07-19 | NC | DE-GUP-DT-E-22-638 | 2022-09-08 | 2 | CRS-GUP-DHI-DT-22-808 | 2022-09-19 | NC
| GUP | XR01 | P1 | HYB | 121044 |  | GUP-XR01-P1HYB-121044 | HRSG_REMOTE DRUM LEVEL INDICATOR DATASHEET/DRAWINGS CATALOG | FI | 2022-01-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-332 | 2022-06-24 | 2 | CRS-GUP-DHI-DT-22-529 | 2022-07-19 | NC | DHI-GUP-DT-21-078 | 2021-10-28 | 0 | CRS-GUP-DHI-DT-21-062 | 2021-11-17 | NC | DHI-GUP-DT-22-048 | 2022-01-28 | 1 | CRS-GUP-DHI-DT-22-207 | 2022-02-28 | NC | DE-GUP-DT-E-22-332 | 2022-06-24 | 2 | CRS-GUP-DHI-DT-22-529 | 2022-07-19 | NC
| GUP | XR01 | P1 | HYB | 121045 |  | GUP-XR01-P1HYB-121045 | HRSG_ LOCAL GAUGE AND TEMPERATURE ELEMENT DATA SHEET&DRAWINGS &CATALOG | FI | 2022-01-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-011 | 2025-01-21 | 2 | CRS-GUP-DHI-DT-22-808 | 2022-09-19 | NC | DHI-GUP-DT-21-078 | 2021-10-28 | 0 | CRS-GUP-DHI-DT-21-062 | 2021-11-17 | NC | DE-GUP-DT-E-22-638 | 2022-09-08 | 1 | CRS-GUP-DHI-DT-22-808 | 2022-09-19 | NC | DE-GUP-DT-E-25-011 | 2025-01-21 | 2
| GUP | XR01 | P1 | HYB | 121046 |  | GUP-XR01-P1HYB-121046 | HRSG_ TRANSMITTER DATA SHEET & DRAWINGS &CATALOG | FI | 2022-01-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-638 | 2022-09-08 | 2 | CRS-GUP-DHI-DT-22-808 | 2022-09-19 | NC | DHI-GUP-DT-21-078 | 2021-10-28 | 0 | CRS-GUP-DHI-DT-21-062 | 2021-11-17 | RC | DE-GUP-DT-E-22-246 | 2022-05-24 | 1 | CRS-GUP-DHI-DT-22-448 | 2022-06-17 | NC | DE-GUP-DT-E-22-638 | 2022-09-08 | 2 | CRS-GUP-DHI-DT-22-808 | 2022-09-19 | NC
| GUP | XR01 | P1 | HYB | 121047 |  | GUP-XR01-P1HYB-121047 | HRSG_ LEVEL SWITCH DATA SHEET & DRAWINGS &CATALOG | FI | 2022-01-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-638 | 2022-09-08 | 2 | CRS-GUP-DHI-DT-22-808 | 2022-09-19 | NC | DHI-GUP-DT-21-078 | 2021-10-28 | 0 | CRS-GUP-DHI-DT-21-062 | 2021-11-17 | NC | DHI-GUP-DT-22-048 | 2022-01-28 | 1 | CRS-GUP-DHI-DT-22-207 | 2022-02-28 | NC | DE-GUP-DT-E-22-638 | 2022-09-08 | 2 | CRS-GUP-DHI-DT-22-808 | 2022-09-19 | NC
| GUP | XR01 | P1 | HYB | 121048 |  | GUP-XR01-P1HYB-121048 | HRSG_ FLOW ELEMENT DATA SHEET & DRAWINGS &CATALOG | FI | 2022-01-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-332 | 2022-06-24 | 2 | CRS-GUP-DHI-DT-22-529 | 2022-07-19 | NC | DHI-GUP-DT-21-078 | 2021-10-28 | 0 | CRS-GUP-DHI-DT-21-062 | 2021-11-17 | RC | DHI-GUP-DT-22-048 | 2022-01-28 | 1 | CRS-GUP-DHI-DT-22-207 | 2022-02-28 | NC | DE-GUP-DT-E-22-332 | 2022-06-24 | 2 | CRS-GUP-DHI-DT-22-529 | 2022-07-19 | NC
| GUP | YL01 | P1 | HYB | 121022 |  | GUP-YL01-P1HYB-121022 | HRSG_DCS I/O LIST | FI | 2021-10-13 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-010 | 2023-01-12 | 1 | CRS-GUP-DHI-DT-23-1521 | 2023-02-14 | NC | DHI-GUP-DT-21-026 | 2021-09-16 | 0 | CRS-GUP-DHI-DT-21-064 | 2021-11-17 | NC | DE-GUP-DT-E-23-010 | 2023-01-12 | 1 | CRS-GUP-DHI-DT-23-1521 | 2023-02-14 | NC
| GUP | YF00 | P1 | HYB | 121035 |  | GUP-YF00-P1HYB-121035 | HRSG_START-UP & SHUT-DOWN SEQUENCE DIAGRAM | FA | 2021-12-12 | 2022-09-30 | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-011 | 2025-01-21 | 1 | CRS-GUP-DHI-DT-22-1132 | 2022-11-23 | AA | DHI-GUP-DT-21-078 | 2021-10-28 | A | CRS-GUP-DHI-DT-21-062 | 2021-11-17 | RC | DE-GUP-DT-E-22-532 | 2022-08-23 | B | CRS-GUP-DHI-DT-22-720 | 2022-09-05 | AA | DE-GUP-DT-E-22-784 | 2022-10-11 | 0 | CRS-GUP-DHI-DT-22-1132 | 2022-11-23 | AA | DE-GUP-DT-E-25-011 | 2025-01-21 | 1
| GUP | YD08 | P1 | HYB | 121036 |  | GUP-YD08-P1HYB-121036 | HRSG_INSTRUMENT LOCATION DIAGRAM | FI | 2022-01-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-662 | 2022-09-14 | 2 | CRS-GUP-DHI-DT-22-860 | 2022-09-24 | NC | DHI-GUP-DT-21-119 | 2021-11-26 | 0 | CRS-GUP-DHI-DT-21-091 | 2021-12-23 | NC | DE-GUP-DT-E-22-263 | 2022-06-02 | 1 | CRS-GUP-DHI-DT-22-486 | 2022-07-06 | NC | DE-GUP-DT-E-22-662 | 2022-09-14 | 2 | CRS-GUP-DHI-DT-22-860 | 2022-09-24 | NC
| GUP | YK00 | P1 | HYB | 121037 |  | GUP-YK00-P1HYB-121037 | HRSG_INSTRUMENT INSTALLATION DETAIL DRAWINGS | FI | 2022-01-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-011 | 2025-01-21 | 3 | CRS-GUP-DHI-DT-23-1571 | 2023-02-23 | NC | DHI-GUP-DT-21-119 | 2021-11-26 | 0 | CRS-GUP-DHI-DT-21-091 | 2021-12-23 | NC | DE-GUP-DT-E-22-662 | 2022-09-14 | 1 | CRS-GUP-DHI-DT-22-860 | 2022-09-24 | NC | DE-GUP-DT-E-23-017 | 2023-01-13 | 2 | CRS-GUP-DHI-DT-23-1571 | 2023-02-23 | NC | DE-GUP-DT-E-25-011 | 2025-01-21 | 3
| GUP | YT01 | P1 | HYB | 121038 |  | GUP-YT01-P1HYB-121038 | HRSG_AIRCRAFT WARNING LIGHT DATA SHEET & LAYOUT DRAWING | FI | 2022-02-10 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-662 | 2022-09-14 | 2 | CRS-GUP-DHI-DT-22-882 | 2022-10-09 | NC | DHI-GUP-DT-22-006 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-171 | 2022-01-24 | NC | DE-GUP-DT-E-22-419 | 2022-07-20 | 1 | CRS-GUP-DHI-DT-22-604 | 2022-08-13 | RC | DE-GUP-DT-E-22-662 | 2022-09-14 | 2 | CRS-GUP-DHI-DT-22-882 | 2022-10-09 | NC
| GUP | YE03 | P1 | HYB | 121051 |  | GUP-YE03-P1HYB-121051 | HRSG_EARTHING AND LIGHTNING LAYOUT DRAWING | FI | 2022-06-20 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-662 | 2022-09-14 | 1 | CRS-GUP-DHI-DT-22-860 | 2022-09-24 | NC | DHI-GUP-DT-21-119 | 2021-11-26 | 0 | CRS-GUP-DHI-DT-21-091 | 2021-12-23 | NC | DE-GUP-DT-E-22-662 | 2022-09-14 | 1 | CRS-GUP-DHI-DT-22-860 | 2022-09-24 | NC
| GUP | YU01 | P1 | HYB | 121052 |  | GUP-YU01-P1HYB-121052 | HRSG_ELECTRICAL SINGLE LINE DIAGRAMS | FA | 2021-12-12 | 2022-08-15 | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-095 | 2024-03-27 | 1 | CRS-GUP-DHI-DT-22-1247 | 2022-12-13 | AA | DHI-GUP-DT-21-078 | 2021-10-28 | A | CRS-GUP-DHI-DT-21-062 | 2021-11-17 | RC | DE-GUP-DT-E-22-527 | 2022-08-22 | B | CRS-GUP-DHI-DT-22-730 | 2022-09-09 | AC | DE-GUP-DT-E-22-983 | 2022-11-24 | 0(CP) | CRS-GUP-DHI-DT-22-1247 | 2022-12-13 | AA | DE-GUP-DT-E-24-095 | 2024-03-27 | 1
| GUP | YR05 | P1 | HYB | 121053 |  | GUP-YR05-P1HYB-121053 | HRSG_POWER DISTRIBUTION PANEL DRAWINGS | FI | 2022-01-11 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-914 | 2022-11-08 | 2 | CRS-GUP-DHI-DT-22-1030 | 2022-11-13 | NC | DHI-GUP-DT-21-119 | 2021-11-26 | 0 | CRS-GUP-DHI-DT-21-091 | 2021-12-23 | NC | DE-GUP-DT-E-22-662 | 2022-09-14 | 1 | CRS-GUP-DHI-DT-22-860 | 2022-09-24 | NC | DE-GUP-DT-E-22-914 | 2022-11-08 | 2 | CRS-GUP-DHI-DT-22-1030 | 2022-11-13 | NC
| GUP | YQ01 | P1 | HYB | 121054 |  | GUP-YQ01-P1HYB-121054 | HRSG_LIGHTING & SMALL POWER LAYOUT DRAWING | FI | 2022-02-10 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-914 | 2022-11-08 | 2 | CRS-GUP-DHI-DT-22-1030 | 2022-11-13 | NC | DHI-GUP-DT-22-006 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-171 | 2022-01-24 | NC | DE-GUP-DT-E-22-662 | 2022-09-14 | 1 | CRS-GUP-DHI-DT-22-882 | 2022-10-09 | NC | DE-GUP-DT-E-22-914 | 2022-11-08 | 2 | CRS-GUP-DHI-DT-22-1030 | 2022-11-13 | NC
| GUP | YD00 | P1 | HYB | 121055 |  | GUP-YD00-P1HYB-121055 | HRSG_JUNCTION BOX & INSTRUMENT RACK DRAWING | FI | 2022-01-11 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-914 | 2022-11-08 | 2 | CRS-GUP-DHI-DT-22-1030 | 2022-11-13 | NC | DHI-GUP-DT-21-119 | 2021-11-26 | 0 | CRS-GUP-DHI-DT-21-091 | 2021-12-23 | NC | DE-GUP-DT-E-22-662 | 2022-09-14 | 1 | CRS-GUP-DHI-DT-22-860 | 2022-09-24 | NC | DE-GUP-DT-E-22-914 | 2022-11-08 | 2 | CRS-GUP-DHI-DT-22-1030 | 2022-11-13 | NC
| GUP | YL16 | P1 | HYB | 121056 |  | GUP-YL16-P1HYB-121056 | HRSG_CABLE SCHEDULE | FI | 2022-02-10 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-348 | 2023-03-22 | 2 | CRS-GUP-DHI-DT-23-1793 | 2023-03-30 | NC | DHI-GUP-DT-22-006 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-171 | 2022-01-24 | NC | DE-GUP-DT-E-22-754 | 2022-10-04 | 1 | CRS-GUP-DHI-DT-22-926 | 2022-10-19 | NC | DE-GUP-DT-E-23-348 | 2023-03-22 | 2 | CRS-GUP-DHI-DT-23-1793 | 2023-03-30 | NC
| GUP | YR04 | P1 | HYB | 121057 |  | GUP-YR04-P1HYB-121057 | HRSG_CABLE SPECIFICATION | FI | 2022-02-10 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-754 | 2022-10-04 | 1 | CRS-GUP-DHI-DT-22-926 | 2022-10-19 | NC | DHI-GUP-DT-21-119 | 2021-11-26 | 0 | CRS-GUP-DHI-DT-21-091 | 2021-12-23 | NC | DE-GUP-DT-E-22-754 | 2022-10-04 | 1 | CRS-GUP-DHI-DT-22-926 | 2022-10-19 | NC
| GUP | YV02 | P1 | HYB | 121058 |  | GUP-YV02-P1HYB-121058 | HRSG_CABLE CONNECTION DIAGRAM | FI | 2022-02-10 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-011 | 2025-01-21 | 2 | CRS-GUP-DHI-DT-22-926 | 2022-10-19 | NC | DHI-GUP-DT-22-006 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-171 | 2022-01-24 | NC | DE-GUP-DT-E-22-754 | 2022-10-04 | 1 | CRS-GUP-DHI-DT-22-926 | 2022-10-19 | NC | DE-GUP-DT-E-25-011 | 2025-01-21 | 2
| GUP | YE00 | P1 | HYB | 121059 |  | GUP-YE00-P1HYB-121059 | HRSG_CABLE TRAY & RACEWAY LAYOUT | FI | 2022-02-10 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-983 | 2022-11-24 | 3 | CRS-GUP-DHI-DT-22-1214 | 2022-11-30 | NC | DHI-GUP-DT-21-119 | 2021-11-26 | 0 | CRS-GUP-DHI-DT-21-091 | 2021-12-23 | NC | DHI-GUP-DT-22-048 | 2022-01-28 | 1 | CRS-GUP-DHI-DT-22-207 | 2022-02-28 | NC | DE-GUP-DT-E-22-624 | 2022-09-07 | 2 | CRS-GUP-DHI-DT-22-869 | 2022-10-09 | NC | DE-GUP-DT-E-22-983 | 2022-11-24 | 3 | CRS-GUP-DHI-DT-22-1214 | 2022-11-30 | NC | DE-GUP-DT-E-25-011 | 1900-01-03
| GUP | YD02 | P1 | HYB | 121060 |  | GUP-YD02-P1HYB-121060 | HRSG_CONDUIT PLAN & SPECIFICATION | FI | 2022-02-10 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-011 | 2025-01-21 | 2 | CRS-GUP-DHI-DT-22-926 | 2022-10-19 | NC | DHI-GUP-DT-22-006 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-171 | 2022-01-24 | NC | DE-GUP-DT-E-22-754 | 2022-10-04 | 1 | CRS-GUP-DHI-DT-22-926 | 2022-10-19 | NC | DE-GUP-DT-E-25-011 | 2025-01-21 | 2
| GUP | XR01 | P1 | HSG | 121170 |  | GUP-XR01-P1HSG-121170 | CONTROL PHILOSOPHY / NARRATIVES FOR HRSG SCR | FI | 2022-03-24 |  | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-615 | 2022-09-05 | 1 | CRS-GUP-DHI-DT-22-895 | 2022-10-12 | NC | DHI-GUP-DT-21-119 | 2021-11-26 | 0 | CRS-GUP-DHI-DT-21-091 | 2021-12-23 | NC | DHI-GUP-DT-22-048 | 2022-01-28 | 1 | CRS-GUP-DHI-DT-22-207 | 2022-02-28 | NC | DE-GUP-DT-E-22-615 | 2022-09-05 | 1 | CRS-GUP-DHI-DT-22-895 | 2022-10-12 | NC
| GUP | YD00 | P1 | HYA | 121201 |  | GUP-YD00-P1HYA-121201 | HRSG_NAME PLATE DRAWING | FI | 2021-10-30 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-783 | 2022-10-11 | 2 | CRS-GUP-DHI-DT-22-1002 | 2022-11-13 | NC | DHI-GUP-DT-21-078 | 2021-10-28 | 0 | CRS-GUP-DHI-DT-21-062 | 2021-11-17 | NC | DE-GUP-DT-E-22-419 | 2022-07-20 | 1 | CRS-GUP-DHI-DT-22-616 | 2022-08-16 | NC | DE-GUP-DT-E-22-783 | 2022-10-11 | 2 | CRS-GUP-DHI-DT-22-1002 | 2022-11-13 | NC
| GUP | CQ02 | P1 | HBK | 121009 |  | GUP-CQ02-P1HBK-121009 | HRSG_OPERATION & MAINTENANCE (O&M) MANUAL | FI | 2023-12-31 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-137 | 2024-05-22 | 0 | CRS-GUP-DHI-DT-24-064 | 2024-07-17 | NC | DE-GUP-DT-E-24-137 | 2024-05-22 | 0 | CRS-GUP-DHI-DT-24-064 | 2024-07-17 | NC
| GUP | XR01 | P0 | EKT | 124101 |  | GUP-XR01-P0EKT-124101 | EQUIPMENT DATA SHEET AND DRAWING FOR GT PERFORMANCE HEATER | FA | 2025-01-31 | 2025-03-31 | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-040 | 2025-03-25 | 0 | 별도 메일접수 25-011 | 2025-03-14 | AA | DE-GUP-DT-E-25-014 | 2025-01-22 | A | 별도 메일접수 25-011 | 2025-03-14 | AA | DE-GUP-DT-E-25-040 | 2025-03-25 | 0
| GUP | XR01 | P0 | EKT | 124102 |  | GUP-XR01-P0EKT-124102 | EQUIPMENT DATA SHEET AND DRAWING FOR FUEL CONDENSATE PUMP FOR HEATER & FILTER | FA | 2025-01-31 | 2025-03-31 | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-040 | 2025-03-25 | 0 | 별도 메일접수 25-011 | 2025-03-14 | RC | DE-GUP-DT-E-25-014 | 2025-01-22 | A | 별도 메일접수 25-011 | 2025-03-14 | RC | DE-GUP-DT-E-25-040 | 2025-03-25 | 0
| GUP | XR01 | P0 | EKT | 124103 |  | GUP-XR01-P0EKT-124103 | EQUIPMENT DATA SHEET AND DRAWING FOR FUEL CONDENSATE TANK FOR HEATER & FILTER | FA | 2025-01-31 | 2025-03-31 | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-040 | 2025-03-25 | 0 | 별도 메일접수 25-011 | 2025-03-14 | AA | DE-GUP-DT-E-25-014 | 2025-01-22 | A | 별도 메일접수 25-011 | 2025-03-14 | AA | DE-GUP-DT-E-25-040 | 2025-03-25 | 0
| GUP | XR01 | P0 | EKT | 124104 |  | GUP-XR01-P0EKT-124104 | EQUIPMENT DATA SHEET AND DRAWING FOR PRESSURE SAFETY VALVE (PERFORMANCE HEATER PACKAGE) | FI | 2025-01-31 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  | Add (20250606) | DE-GUP-DT-E-25-031 | 2025-03-12 | 0 |  |  |  | DE-GUP-DT-E-25-031 | 2025-03-12 | 0
| GUP | XN00 | P0 | EKT | 124105 |  | GUP-XN00-P0EKT-124105 | OnOff VALVE DATA SHEET FOR GT PERFORMANCE HEATER PACKAGE | FA | 2025-01-31 | 2025-03-31 | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-060 | 2025-05-30 | B | 별도 메일접수 25-011 | 2025-03-14 | RC | DE-GUP-DT-E-25-014 | 2025-01-22 | A | 별도 메일접수 25-011 | 2025-03-14 | RC | DE-GUP-DT-E-25-060 | 2025-05-30 | B
| GUP | XA00 | P0 | EKT | 124106 |  | GUP-XA00-P0EKT-124106 | GENERAL ARRANGEMENT DRAWING FOR GT PERFORMANCE HEATER SKID | FA | 2025-01-31 | 2025-03-31 | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-060 | 2025-05-30 | 0 | 별도 메일접수 25-011 | 2025-03-14 | AA | DE-GUP-DT-E-25-014 | 2025-01-22 | A | 별도 메일접수 25-011 | 2025-03-14 | AA | DE-GUP-DT-E-25-060 | 2025-05-30 | 0
| GUP | CC08 | P0 | EKT | 124107 |  | GUP-CC08-P0EKT-124107 | FOUNDATION DRAWING INCLUDING LOADINGS FOR GT PERFORMANCE HEATER SKID | FA | 2025-01-31 | 2025-03-31 | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Civil | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-061 | 2025-05-30 | 0 | 별도 메일접수 25-011 | 2025-03-14 | AA | DE-GUP-DT-E-25-014 | 2025-01-22 | A | 별도 메일접수 25-011 | 2025-03-14 | AA | DE-GUP-DT-E-25-061 | 2025-05-30 | 0
| GUP | YT10 | P0 | EKT | 124108 |  | GUP-YT10-P0EKT-124108 | ANCHOR BOLT DETAIL AND CALCULATION FOR GT PERFORMANCE HEATER SKID | FA | 2025-01-31 | 2025-03-31 | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-060 | 2025-05-30 | 0 | 별도 메일접수 25-011 | 2025-03-14 | AA | DE-GUP-DT-E-25-014 | 2025-01-22 | A | 별도 메일접수 25-011 | 2025-03-14 | AA | DE-GUP-DT-E-25-060 | 2025-05-30 | 0
| GUP | XG02 | P0 | EKT | 124109 |  | GUP-XG02-P0EKT-124109 | P&ID FOR GT PERFORMANCE HEATER PACKAGE | FA | 2025-01-31 | 2025-03-31 | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-060 | 2025-05-30 | B | 별도 메일접수 25-011 | 2025-03-14 | RC | DE-GUP-DT-E-25-014 | 2025-01-22 | A | 별도 메일접수 25-011 | 2025-03-14 | RC | DE-GUP-DT-E-25-060 | 2025-05-30 | B
| GUP | YS02 | P0 | EKT | 124110 |  | GUP-YS02-P0EKT-124110 | INTERCONNECTION WIRING DIAGRAM FOR GT PERFORMANCE HEATER PACKAGE | FA | 2025-01-31 | 2025-03-31 | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  | Add (20250606) | DE-GUP-DT-E-25-033 | 2025-03-31 | A |  |  |  | DE-GUP-DT-E-25-033 | 2025-03-31 | A
| GUP | YT02 | P0 | EKT | 124113 |  | GUP-YT02-P0EKT-124113 | INSTRUMENT DATA SHEET & SPECIFICATION FOR GT PERFORMANCE HEATER PACKAGE | FA | 2025-01-31 | 2025-03-31 | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-059 | 2025-05-27 | 0 | 별도 메일접수 25-007 | 2025-03-13 | AA | DE-GUP-DT-E-25-016 | 2025-01-22 | A | 별도 메일접수 25-007 | 2025-03-13 | AA | DE-GUP-DT-E-25-059 | 2025-05-27 | 0
| GUP | YK00 | P0 | EKT | 124114 |  | GUP-YK00-P0EKT-124114 | INSTRUMENT HOOK-UP DRAWING FOR GT PERFORMANCE HEATER PACKAGE | FI | 2025-01-31 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  | Add (20250606) | DE-GUP-DT-E-25-041 | 2025-03-26 | 0 |  |  |  | DE-GUP-DT-E-25-041 | 2025-03-26 | 0
| GUP | YL00 | P0 | EKT | 124115 |  | GUP-YL00-P0EKT-124115 | INSTRUMENT LIST FOR GT PERFORMANCE HEATER PACKAGE | FA | 2025-01-31 | 2025-03-31 | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-059 | 2025-05-27 | 0 | 별도 메일접수 25-007 | 2025-03-13 | AA | DE-GUP-DT-E-25-016 | 2025-01-22 | A | 별도 메일접수 25-007 | 2025-03-13 | AA | DE-GUP-DT-E-25-059 | 2025-05-27 | 0
| GUP | YR05 | P0 | EKT | 124116 |  | GUP-YR05-P0EKT-124116 | JUNCTION BOX OUTLINE DRAWING FOR GT PERFORMANCE HEATER PACKAGE | FI | 2025-01-31 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  | Add (20250606) | DE-GUP-DT-E-25-033 | 2025-03-31 | 0 |  |  |  | DE-GUP-DT-E-25-033 | 2025-03-31 | 0
| GUP | XN00 | P0 | EKT | 124119 |  | GUP-XN00-P0EKT-124119 | VALVE LIST FOR GT PERFORMANCE HEATER PACKAGE | FA | 2025-01-31 | 2025-03-31 | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-068 | 2025-06-25 | 0 | 별도 메일접수 25-009 | 2025-03-13 | AA | DE-GUP-DT-E-25-015 | 2025-01-22 | A | 별도 메일접수 25-009 | 2025-03-13 | AA | DE-GUP-DT-E-25-068 | 2025-06-25 | 0
| GUP | VO00 | P0 | EKT | 124120 |  | GUP-VO00-P0EKT-124120 | LINE LIST FOR GT PERFORMANCE HEATER PACKAGE | FI | 2025-01-31 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  | Add (20250606) | DE-GUP-DT-E-25-032 | 2025-03-18 | 0 | CRS-GUP-DHI-DT-25-053 | 2025-06-16 | NC | DE-GUP-DT-E-25-032 | 2025-03-18 | 0 | CRS-GUP-DHI-DT-25-053 | 2025-06-16 | NC
| GUP | XR01 | P0 | EKT | 124201 |  | GUP-XR01-P0EKT-124201 | SPEC & DRAWING FOR FINAL CHANCE FILTER | FA | 2025-01-31 | 2025-03-31 | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-043 | 2025-03-27 | 0 | 별도 메일접수 25-010 | 2025-03-14 | NC | DE-GUP-DT-E-25-012 | 2025-01-22 | A | 별도 메일접수 25-010 | 2025-03-14 | NC | DE-GUP-DT-E-25-043 | 2025-03-27 | 0
| GUP | XR01 | P0 | EKT | 124202 |  | GUP-XR01-P0EKT-124202 | DATA SHEET AND DRAWING FOR PRESSURE SAFETY VALVE (FINAL CHANCE FILTER PACKAGE) | FI | 2025-01-31 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  | Add (20250606) | DE-GUP-DT-E-25-028 | 2025-03-07 | 0 | CRS-GUP-DHI-DT-25-052 | 2025-06-16 | NC | DE-GUP-DT-E-25-028 | 2025-03-07 | 0 | CRS-GUP-DHI-DT-25-052 | 2025-06-16 | NC
| GUP | XR01 | P0 | EKT | 124203 |  | GUP-XR01-P0EKT-124203 | GENERAL ARRANGEMENT DRAWING FOR FINAL CHANCE FILTER SKID | FA | 2025-01-31 | 2025-03-31 | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  | Add (20250606) | DE-GUP-DT-E-25-066 | 2025-06-24 | 0 | CRS-GUP-DHI-DT-25-052 | 2025-06-16 | AA | DE-GUP-DT-E-25-028 | 2025-03-07 | A | CRS-GUP-DHI-DT-25-052 | 2025-06-16 | AA | DE-GUP-DT-E-25-066 | 2025-06-24 | 0
| GUP | XR01 | P0 | EKT | 124204 |  | GUP-XR01-P0EKT-124204 | FOUNDATION DRAWING INCLUDING LOADINGS FOR FINAL CHANCE FILTER SKID | FA | 2025-01-31 | 2025-03-31 | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Civil | 3 | 2025-06-30 |  | Add (20250606) | DE-GUP-DT-E-25-066 | 2025-06-24 | 0 | CRS-GUP-DHI-DT-25-052 | 2025-06-16 | AA | DE-GUP-DT-E-25-028 | 2025-03-07 | A | CRS-GUP-DHI-DT-25-052 | 2025-06-16 | AA | DE-GUP-DT-E-25-066 | 2025-06-24 | 0
| GUP | XR01 | P0 | EKT | 124205 |  | GUP-XR01-P0EKT-124205 | ANCHOR BOLT DETAIL AND CALCULATION FOR FINAL CHANCE FILTER SKID | FI | 2025-01-31 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Civil | 3 | 2025-06-30 |  | Add (20250606) | DE-GUP-DT-E-25-028 | 2025-03-07 | 0 | CRS-GUP-DHI-DT-25-052 | 2025-06-16 | NC | DE-GUP-DT-E-25-028 | 2025-03-07 | 0 | CRS-GUP-DHI-DT-25-052 | 2025-06-16 | NC
| GUP | XR01 | P0 | EKT | 124206 |  | GUP-XR01-P0EKT-124206 | P&ID FOR FINAL CHANCE FILTER PACKAGE | FA | 2025-01-31 | 2025-03-31 | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Civil | 3 | 2025-06-30 |  | Add (20250606) | DE-GUP-DT-E-25-065 | 2025-06-24 | 0 | CRS-GUP-DHI-DT-25-054 | 2025-06-16 | AA | DE-GUP-DT-E-25-037 | 2025-03-24 | A | CRS-GUP-DHI-DT-25-054 | 2025-06-16 | AA | DE-GUP-DT-E-25-065 | 2025-06-24 | 0
| GUP | XR01 | P0 | EKT | 124207 |  | GUP-XR01-P0EKT-124207 | INTERCONNECTION WIRING DIAGRAM FOR FINAL CHANCE FILTER PACKAGE | FA | 2025-01-31 | 2025-03-31 | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-063 | 2025-06-10 | 0 | 별도 메일접수 25-036 | 2025-03-14 | AA | DE-GUP-DT-E-25-013 | 2025-01-22 | A | 별도 메일접수 25-036 | 2025-03-14 | AA | DE-GUP-DT-E-25-063 | 2025-06-10 | 0
| GUP | XR01 | P0 | EKT | 124209 |  | GUP-XR01-P0EKT-124209 | INSTRUMENT LIST , DATA SHEET & SPECIFICATION FOR FINAL CHANCE FILTER PACKAGE | FA | 2025-01-31 | 2025-03-31 | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-063 | 2025-06-10 | 0 | 별도 메일접수 25-036 | 2025-03-14 | AA | DE-GUP-DT-E-25-013 | 2025-01-22 | A | 별도 메일접수 25-036 | 2025-03-14 | AA | DE-GUP-DT-E-25-063 | 2025-06-10 | 0
| GUP | XR01 | P0 | EKT | 124210 |  | GUP-XR01-P0EKT-124210 | INSTRUMENT HOOK-UP DRAWING FOR FINAL CHANCE FILTER PACKAGE | FI | 2025-01-31 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | I&C | 3 | 2025-06-30 |  | Add (20250606) | DE-GUP-DT-E-25-038 | 2025-03-24 | 0 |  |  |  | DE-GUP-DT-E-25-038 | 2025-03-24 | 0
| GUP | YD08 | P0 | EKT | 124212 |  | GUP-YD08-P0EKT-124212 | JUNCTION BOX OUTLINE DRAWING FOR FINAL CHANCE FILTER PACKAGE | FI | 2025-01-31 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  | Add (20250606) | DE-GUP-DT-E-25-029 | 2025-03-07 | 0 |  |  |  | DE-GUP-DT-E-25-029 | 2025-03-07 | 0
| GUP | XR01 | P0 | EKT | 124215 |  | GUP-XR01-P0EKT-124215 | VALVE LIST, DATA SHEET AND DRAWING FOR FINAL CHANCE FILTER | FI | 2025-01-31 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  | Add (20250606) | DE-GUP-DT-E-25-030 | 2025-03-07 | 0 |  |  |  | DE-GUP-DT-E-25-030 | 2025-03-07 | 0
| GUP | XR01 | P0 | EKT | 124216 |  | GUP-XR01-P0EKT-124216 | DATA SHEET AND DRAWING FOR ORIFICES (FINAL CHANCE FILTER PACKAGE) | FI | 2025-01-31 |  | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | HRSG | CCPP | HRSG | Mech. | 3 | 2025-06-30 |  | Add (20250606) | DE-GUP-DT-E-25-039 | 2025-03-24 | 0 |  |  |  | DE-GUP-DT-E-25-039 | 2025-03-24 | 0
| GUP | CQ02 | P1 | PAB | 122502 |  | GUP-CQ02-P1PAB-122502 | COOLING TOWER_OPERATION&MANINTENANCE MANUAL | FI | 2022-10-15 |  | 플랜트기술팀(Mech.) | 박대영 |  |  |  |  | COOLING TOWER | CCPP | COOLING TOWER | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-210 | 2024-08-26 | 1 | CRS-GUP-DHI-DT-23-1625 | 2023-03-02 | NC | DE-GUP-DT-E-23-131 | 2023-02-06 | 0 | CRS-GUP-DHI-DT-23-1625 | 2023-03-02 | NC | DE-GUP-DT-E-24-210 | 2024-08-26 | 1
| GUP | CT00 | P1 | PAB | 122503 |  | GUP-CT00-P1PAB-122503 | COOLING TOWER_STORAGE PROCEDURE | FI | 2022-03-15 |  | 플랜트기술팀(Mech.) | 박대영 |  |  |  |  | COOLING TOWER | CCPP | COOLING TOWER | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-547 | 2022-08-24 | 0 | CRS-GUP-DHI-DT-22-746 | 2022-09-12 | NC | DE-GUP-DT-E-22-547 | 2022-08-24 | 0 | CRS-GUP-DHI-DT-22-746 | 2022-09-12 | NC
| GUP | YT10 | P1 | PAB | 122504 |  | GUP-YT10-P1PAB-122504 | COOLING TOWER_CALCULATION FOR THERMAL DESIGN | FA | 2021-12-05 | 2022-06-04 | 플랜트기술팀(Mech.) | 박대영 |  | R |  |  | COOLING TOWER | CCPP | COOLING TOWER | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-813 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1139 | 2022-11-23 | AA | DHI-GUP-DT-21-159 | 2021-12-09 | A | CRS-GUP-DHI-DT-21-114 | 2022-01-05 | RC | DE-GUP-DT-E-22-554 | 2022-08-25 | B | CRS-GUP-DHI-DT-22-724 | 2022-09-05 | AA | DE-GUP-DT-E-22-813 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1139 | 2022-11-23 | AA
| GUP | YT10 | P1 | PAB | 122506 |  | GUP-YT10-P1PAB-122506 | COOLING TOWER_CALCULATION FOR MAKE-UP AND BLOWDOWN | FA | 2021-12-05 | 2022-06-04 | 플랜트기술팀(Mech.) | 박대영 |  | R |  |  | COOLING TOWER | CCPP | COOLING TOWER | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-429 | 2022-07-22 | 0 | CRS-GUP-DHI-DT-22-575 | 2022-08-03 | AA | DHI-GUP-DT-21-116 | 2021-11-24 | A | CRS-GUP-DHI-DT-21-089 | 2021-12-23 | RC | DHI-GUP-DT-22-047 | 2022-01-28 | B | CRS-GUP-DHI-DT-21-198 | 2022-02-13 | AA | DE-GUP-DT-E-22-429 | 2022-07-22 | 0 | CRS-GUP-DHI-DT-22-575 | 2022-08-03 | AA
| GUP | YT01 | P1 | PAB | 122507 |  | GUP-YT01-P1PAB-122507 | COOLING TOWER_PERFORMANCE CURVE | FA | 2021-12-05 | 2022-06-04 | 플랜트기술팀(Mech.) | 박대영 |  |  |  |  | COOLING TOWER | CCPP | COOLING TOWER | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-727 | 2022-09-30 | 0 | CRS-GUP-DHI-DT-22-1125 | 2022-11-23 | AA | DHI-GUP-DT-21-178 | 2021-12-16 | A | CRS-GUP-DHI-DT-21-121 | 2022-01-07 | RC | DE-GUP-DT-E-22-555 | 2022-08-25 | B | CRS-GUP-DHI-DT-22-752 | 2022-09-12 | AA | DE-GUP-DT-E-22-727 | 2022-09-30 | 0 | CRS-GUP-DHI-DT-22-1125 | 2022-11-23 | AA
| GUP | DB00 | P1 | PAB | 122508 |  | GUP-DB00-P1PAB-122508 | COOLING TOWER_CHARACTERISTIC CURVE | FA | 2021-12-05 | 2022-06-04 | 플랜트기술팀(Mech.) | 박대영 |  |  |  |  | COOLING TOWER | CCPP | COOLING TOWER | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-727 | 2022-09-30 | 0 | CRS-GUP-DHI-DT-22-1125 | 2022-11-23 | AA | DHI-GUP-DT-21-178 | 2021-12-16 | A | CRS-GUP-DHI-DT-21-121 | 2022-01-07 | RC | DE-GUP-DT-E-22-555 | 2022-08-25 | B | CRS-GUP-DHI-DT-22-752 | 2022-09-12 | AA | DE-GUP-DT-E-22-727 | 2022-09-30 | 0 | CRS-GUP-DHI-DT-22-1125 | 2022-11-23 | AA
| GUP | XG02 | P1 | PAB | 122509 |  | GUP-XG02-P1PAB-122509 | COOLING TOWER_P&I DIAGRAM | FA | 2022-01-28 | 2022-07-27 | 플랜트기술팀(Mech.) | 박대영 |  |  |  |  | COOLING TOWER | CCPP | COOLING TOWER | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-344 | 2023-03-22 | 0 | CRS-GUP-DHI-DT-23-1662 | 2023-03-09 | AA | DHI-GUP-DT-22-049 | 2022-01-28 | A | CRS-GUP-DHI-DT-22-208 | 2022-02-20 | RC | DE-GUP-DT-E-22-968 | 2022-11-22 | B | CRS-GUP-DHI-DT-22-1194 | 2022-11-30 | RC | DE-GUP-DT-E-23-140 | 2023-02-08 | C | CRS-GUP-DHI-DT-23-1662 | 2023-03-09 | AA | DE-GUP-DT-E-23-344 | 2023-03-22 | 0
| GUP | YD00 | P1 | PAB | 122510 |  | GUP-YD00-P1PAB-122510 | COOLING TOWER_GENERAL ARRANGEMENT | FA | 2021-11-15 | 2022-02-15 | 플랜트기술팀(Mech.) | 박대영 |  | R |  |  | COOLING TOWER | CCPP | COOLING TOWER | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-212 | 2024-08-29 | 1 | 자체 CRS 개정 후 제출 | 2024-08-28 | N/A | DHI-GUP-DT-21-116 | 2021-11-24 | 0 | CRS-GUP-DHI-DT-21-089 | 2021-12-23 | RC | DHI-GUP-DT-22-047 | 2022-01-28 | 1 | CRS-GUP-DHI-DT-21-198 | 2022-02-13 | RC | DE-GUP-DT-E-22-361 | 2022-07-05 | C | CRS-GUP-DHI-DT-22-572 | 2022-08-03 | AA | DE-GUP-DT-E-22-990 | 2022-11-25 | 0 | 자체 CRS 개정 후 제출 | 2024-08-28 | N/A | DE-GUP-DT-E-24-212 | 2024-08-29 | 1
| GUP | CY03 | P1 | PAB | 122511 |  | GUP-CY03-P1PAB-122511 | COOLING TOWER_SYSTEM DESCRIPTION | FA | 2022-01-28 | 2022-07-27 | 플랜트기술팀(Mech.) | 박대영 |  | R |  |  | COOLING TOWER | CCPP | COOLING TOWER | Mech. | 1 | 2025-06-30 |  |  | DE-GUP-DT-E-23-165 | 2023-02-13 | 0 | CRS-GUP-DHI-DT-23-1469 | 2023-02-09 | AA | DHI-GUP-DT-22-032 | 2022-01-25 | A | CRS-GUP-DHI-DT-21-197 | 2022-02-13 | RC | DE-GUP-DT-E-22-1020 | 2022-11-30 | B | CRS-GUP-DHI-DT-22-1234 | 2022-12-13 | RC | DE-GUP-DT-E-22-1159 | 2022-12-22 | C | CRS-GUP-DHI-DT-23-1469 | 2023-02-09 | AA | DE-GUP-DT-E-23-165 | 2023-02-13 | 0
| GUP | YT01 | P1 | PAB | 122512 |  | GUP-YT01-P1PAB-122512 | COOLING TOWER_DATA SHEET | FA | 2021-11-15 | 2022-05-14 | 플랜트기술팀(Mech.) | 박대영 |  |  |  |  | COOLING TOWER | CCPP | COOLING TOWER | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-727 | 2022-09-30 | 0 | CRS-GUP-DHI-DT-22-1125 | 2022-11-23 | AA | DHI-GUP-DT-21-116 | 2021-11-24 | A | CRS-GUP-DHI-DT-21-089 | 2021-12-23 | RC | DHI-GUP-DT-22-047 | 2022-01-28 | B | CRS-GUP-DHI-DT-21-198 | 2022-02-13 | AC | DE-GUP-DT-E-22-361 | 2022-07-05 | C | CRS-GUP-DHI-DT-22-572 | 2022-08-03 | AA | DE-GUP-DT-E-22-727 | 2022-09-30 | 0 | CRS-GUP-DHI-DT-22-1125 | 2022-11-23 | AA
| GUP | YK01 | P1 | PAB | 122514 |  | GUP-YK01-P1PAB-122514 | COOLING TOWER_FAN STACK DRAWING | FI | 2022-03-28 |  | 플랜트기술팀(Mech.) | 박대영 |  | R |  |  | COOLING TOWER | CCPP | COOLING TOWER | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-780 | 2022-10-11 | 1 | CRS-GUP-DHI-DT-22-1000 | 2022-11-13 | NC | DHI-GUP-DT-22-205 | 2022-05-04 | 0 | CRS-GUP-DHI-DT-22-377 | 2022-05-30 | NC | DE-GUP-DT-E-22-780 | 2022-10-11 | 1 | CRS-GUP-DHI-DT-22-1000 | 2022-11-13 | NC
| GUP | YK01 | P1 | PAB | 122515 |  | GUP-YK01-P1PAB-122515 | COOLING TOWER_DRIFT ELIMINATOR DRAWING | FI | 2022-03-15 |  | 플랜트기술팀(Mech.) | 박대영 |  | R |  |  | COOLING TOWER | CCPP | COOLING TOWER | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-781 | 2022-10-11 | 1 | CRS-GUP-DHI-DT-22-1001 | 2022-11-13 | NC | DHI-GUP-DT-22-114 | 2022-03-11 | 0 | CRS-GUP-DHI-DT-22-275 | 2022-04-02 | NC | DE-GUP-DT-E-22-781 | 2022-10-11 | 1 | CRS-GUP-DHI-DT-22-1001 | 2022-11-13 | NC
| GUP | YK01 | P1 | PAB | 122516 |  | GUP-YK01-P1PAB-122516 | COOLING TOWER_DISTRIBUTION SYSTEM DRAWING | FI | 2022-03-15 |  | 플랜트기술팀(Mech.) | 박대영 |  | R |  |  | COOLING TOWER | CCPP | COOLING TOWER | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-781 | 2022-10-11 | 1 | CRS-GUP-DHI-DT-22-1001 | 2022-11-13 | NC | DHI-GUP-DT-22-114 | 2022-03-11 | 0 | CRS-GUP-DHI-DT-22-275 | 2022-04-02 | NC | DE-GUP-DT-E-22-781 | 2022-10-11 | 1 | CRS-GUP-DHI-DT-22-1001 | 2022-11-13 | NC
| GUP | YK01 | P1 | PAB | 122517 |  | GUP-YK01-P1PAB-122517 | COOLING TOWER_FILL DRAWING | FI | 2022-02-28 |  | 플랜트기술팀(Mech.) | 박대영 |  | R |  |  | COOLING TOWER | CCPP | COOLING TOWER | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-781 | 2022-10-11 | 1 | CRS-GUP-DHI-DT-22-1001 | 2022-11-13 | NC | DHI-GUP-DT-22-114 | 2022-03-11 | 0 | CRS-GUP-DHI-DT-22-275 | 2022-04-02 | NC | DE-GUP-DT-E-22-781 | 2022-10-11 | 1 | CRS-GUP-DHI-DT-22-1001 | 2022-11-13 | NC
| GUP | YK01 | P1 | PAB | 122518 |  | GUP-YK01-P1PAB-122518 | COOLING TOWER_TRAP DOOR AND INSPECTION LADDER ASSEMBLY | FI | 2022-04-15 |  | 플랜트기술팀(Mech.) | 박대영 |  | R |  |  | COOLING TOWER | CCPP | COOLING TOWER | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-780 | 2022-10-11 | 1 | CRS-GUP-DHI-DT-22-1000 | 2022-11-13 | NC | DHI-GUP-DT-22-205 | 2022-05-04 | 0 | CRS-GUP-DHI-DT-22-377 | 2022-05-30 | NC | DE-GUP-DT-E-22-780 | 2022-10-11 | 1 | CRS-GUP-DHI-DT-22-1000 | 2022-11-13 | NC
| GUP | YK01 | P1 | PAB | 122519 |  | GUP-YK01-P1PAB-122519 | COOLING TOWER_SUPPORT DRAWING | FI | 2022-02-28 |  | 플랜트기술팀(Mech.) | 박대영 |  | R |  |  | COOLING TOWER | CCPP | COOLING TOWER | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-479 | 2023-04-20 | 1 | CRS-GUP-DHI-DT-23-1906 | 2023-05-05 | NC | DE-GUP-DT-E-22-488 | 2022-08-09 | 0 | CRS-GUP-DHI-DT-22-725 | 2022-09-09 | NC | DE-GUP-DT-E-23-479 | 2023-04-20 | 1 | CRS-GUP-DHI-DT-23-1906 | 2023-05-05 | NC
| GUP | YT01 | P1 | PAB | 122520 |  | GUP-YT01-P1PAB-122520 | COOLING TOWER_MOTOR DATA SHEET | FI | 2021-12-15 |  | 플랜트기술팀(Mech.) | 박대영 |  |  |  |  | COOLING TOWER | CCPP | COOLING TOWER | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-431 | 2022-07-22 | 1 | CRS-GUP-DHI-DT-22-646 | 2022-08-20 | NC | DHI-GUP-DT-21-193 | 2021-12-22 | 0 | CRS-GUP-DHI-DT-21-158 | 2022-01-12 | NC | DE-GUP-DT-E-22-431 | 2022-07-22 | 1 | CRS-GUP-DHI-DT-22-646 | 2022-08-20 | NC
| GUP | YT01 | P1 | PAB | 122521 |  | GUP-YT01-P1PAB-122521 | COOLING TOWER_INSTRUMENT LIST | FI | 2021-12-31 |  | 플랜트기술팀(Mech.) | 박대영 |  |  |  |  | COOLING TOWER | CCPP | COOLING TOWER | I&C | 3 | 2025-06-30 |  |  | DHI-GUP-DT-22-018 | 2022-01-14 | 0 | CRS-GUP-DHI-DT-21-191 | 2022-02-06 | NC | DHI-GUP-DT-22-018 | 2022-01-14 | 0 | CRS-GUP-DHI-DT-21-191 | 2022-02-06 | NC
| GUP | YT01 | P1 | PAB | 122522 |  | GUP-YT01-P1PAB-122522 | COOLING TOWER_Wiring Diagram | FI | 2022-02-28 |  | 플랜트기술팀(Mech.) | 박대영 |  |  |  |  | COOLING TOWER | CCPP | COOLING TOWER | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-335 | 2022-06-24 | 0 | CRS-GUP-DHI-DT-22-531 | 2022-07-19 | NC | DE-GUP-DT-E-22-335 | 2022-06-24 | 0 | CRS-GUP-DHI-DT-22-531 | 2022-07-19 | NC
| GUP | YT01 | P1 | PAB | 122523 |  | GUP-YT01-P1PAB-122523 | COOLING TOWER_Instrument Data Sheet | FI | 2022-02-28 |  | 플랜트기술팀(Mech.) | 박대영 |  |  |  |  | COOLING TOWER | CCPP | COOLING TOWER | I&C | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-249 | 2022-05-26 | 0 | CRS-GUP-DHI-DT-22-467 | 2022-06-22 | NC | DE-GUP-DT-E-22-249 | 2022-05-26 | 0 | CRS-GUP-DHI-DT-22-467 | 2022-06-22 | NC
| GUP | XV00 | P1 | MB | 123042 |  | GUP-XV00-P1MB-123042 | GT_Aggregate component list - Air Intake System MBL | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | XV00 | P1 | MB | 123044 |  | GUP-XV00-P1MB-123044 | GT_Aggregate component list - Compressor washing system | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | XV00 | P1 | MB | 123045 |  | GUP-XV00-P1MB-123045 | GT_Aggregate component list - Cooling and Sealing Air MBH10 | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | XV00 | P1 | MB | 123046 |  | GUP-XV00-P1MB-123046 | GT_Aggregate component list - Drying System Stationary MPS | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | XV00 | P1 | MB | 123047 |  | GUP-XV00-P1MB-123047 | GT_Aggregate component list - Inlet Heat System | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | XV00 | P1 | MB | 123048 |  | GUP-XV00-P1MB-123048 | GT_Aggregate component list - Fire Detection and Extinguishing System SGJ | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | XV00 | P1 | MB | 123049 |  | GUP-XV00-P1MB-123049 | GT_Aggregate component list - Gas Detection System SFY | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | XV00 | P1 | MB | 123050 |  | GUP-XV00-P1MB-123050 | GT_Aggregate component list - Gas Fuel System MBP | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | XV00 | P1 | MB | 123051 |  | GUP-XV00-P1MB-123051 | GT_Aggregate component list - Gas Turbine System MBA | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | XV00 | P1 | MB | 123052 |  | GUP-XV00-P1MB-123052 | GT_Aggregate component list - Gear system MBK | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | XV00 | P1 | MB | 123053 |  | GUP-XV00-P1MB-123053 | GT_Aggregate component list - Generator System MKA | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | XV00 | P1 | MB | 123054 |  | GUP-XV00-P1MB-123054 | GT_Aggregate component list - HVAC for LER | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | XV00 | P1 | MB | 123055 |  | GUP-XV00-P1MB-123055 | GT_Aggregate component list - Liquid fuel system | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | XV00 | P1 | MB | 123056 |  | GUP-XV00-P1MB-123056 | GT_Aggregate component list - Lube Oil System MBV | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | XV00 | P1 | MB | 123057 |  | GUP-XV00-P1MB-123057 | GT_Aggregate component list - Pulsation Monitoring System MBX | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | XV00 | P1 | MB | 123058 |  | GUP-XV00-P1MB-123058 | GT_Aggregate component list - Purge air system | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | XV00 | P1 | MB | 123060 |  | GUP-XV00-P1MB-123060 | GT_Aggregate component list - Ventilation System GT -Enclosure SAG | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | XV00 | P1 | MB | 123061 |  | GUP-XV00-P1MB-123061 | GT_Aggregate component list- Starting System MBJ | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | XA00 | P1 | MB | 123073 |  | GUP-XA00-P1MB-123073 | GT_Auxiliary System Layout | FI | 2022-04-01 |  | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-243 | 2022-05-23 | 1 | CRS-GUP-DHI-DT-22-427 | 2022-06-14 | NC | DHI-GUP-DT-21-069 | 2021-10-15 | 0 | CRS-GUP-DHI-DT-21-060 | 2021-11-08 | RC | DE-GUP-DT-E-22-243 | 2022-05-23 | 1 | CRS-GUP-DHI-DT-22-427 | 2022-06-14 | NC
| GUP | XS00 | P1 | MB | 123092 |  | GUP-XS00-P1MB-123092 | GT_Cause & Effect Matrix | FI | 2022-08-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | I&C | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-241 | 2022-05-23 | 0 | CRS-GUP-DHI-DT-22-415 | 2022-06-13 | NC | DE-GUP-DT-E-22-241 | 2022-05-23 | 0 | CRS-GUP-DHI-DT-22-415 | 2022-06-13 | NC
| GUP | YS02 | P1 | MB | 123087 |  | GUP-YS02-P1MB-123087 | GT_Circuit Diagram | FI | 2022-08-01 |  | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-342 | 2022-06-28 | 0 | CRS-GUP-DHI-DT-22-549 | 2022-07-27 | NC | DE-GUP-DT-E-22-342 | 2022-06-28 | 0 | CRS-GUP-DHI-DT-22-549 | 2022-07-27 | NC
| GUP | XA00 | P1 | MB | 123093 |  | GUP-XA00-P1MB-123093 | GT_Classification of Hazardous Areas | FI | 2022-08-01 |  | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-051 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-210 | 2022-02-20 | NC | DHI-GUP-DT-22-051 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-210 | 2022-02-20 | NC
| GUP | YS02 | P1 | MB | 123088 |  | GUP-YS02-P1MB-123088 | GT_Connection table | FI | 2022-08-01 |  | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | I&C | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-342 | 2022-06-28 | 0 | CRS-GUP-DHI-DT-22-549 | 2022-07-27 | NC | DE-GUP-DT-E-22-342 | 2022-06-28 | 0 | CRS-GUP-DHI-DT-22-549 | 2022-07-27 | NC
| GUP | XS00 | P1 | MB | 123095 |  | GUP-XS00-P1MB-123095 | GT_Control System Overview | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | I&C | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-864 | 2022-10-27 | 0 | CRS-GUP-DHI-DT-22-1236 | 2022-12-13 | AA | DHI-GUP-DT-22-211 | 2022-05-11 | A | CRS-GUP-DHI-DT-22-393 | 2022-06-07 | RC | DE-GUP-DT-E-22-654 | 2022-09-14 | B | CRS-GUP-DHI-DT-22-897 | 2022-10-12 | AA | DE-GUP-DT-E-22-864 | 2022-10-27 | 0 | CRS-GUP-DHI-DT-22-1236 | 2022-12-13 | AA
| GUP | PL03 | P1 | MB | 123104 |  | GUP-PL03-P1MB-123104 | GT_Delivery Limits (Electrical) | FI | 2022-08-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Elec. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-241 | 2022-05-23 | 0 | CRS-GUP-DHI-DT-22-415 | 2022-06-13 | NC | DE-GUP-DT-E-22-241 | 2022-05-23 | 0 | CRS-GUP-DHI-DT-22-415 | 2022-06-13 | NC
| GUP | YE03 | P1 | MB | 123109 |  | GUP-YE03-P1MB-123109 | GT_External earthing layout | FI | 2022-04-01 |  | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Elec. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-713 | 2022-09-29 | 1 | CRS-GUP-DHI-DT-22-918 | 2022-10-19 | NC | DHI-GUP-DT-22-211 | 2022-05-11 | 0 | CRS-GUP-DHI-DT-22-393 | 2022-06-07 | RC | DE-GUP-DT-E-22-713 | 2022-09-29 | 1 | CRS-GUP-DHI-DT-22-918 | 2022-10-19 | NC
| GUP | XA00 | P1 | MB | 123079 |  | GUP-XA00-P1MB-123079 | GT_Foundation General Layout | FI | 2022-04-01 |  | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Civil | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-835 | 2022-10-21 | 1 | CRS-GUP-DHI-DT-22-963 | 2022-11-07 | NC | DHI-GUP-DT-21-096 | 2021-11-10 | 0 | CRS-GUP-DHI-DT-21-081 | 2021-12-13 | NC | DE-GUP-DT-E-22-835 | 2022-10-21 | 1 | CRS-GUP-DHI-DT-22-963 | 2022-11-07 | NC
| GUP | XA00 | P1 | MB | 123083 |  | GUP-XA00-P1MB-123083 | GT_Foundation General Layout - Roof | FI | 2022-04-01 |  | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Civil | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-835 | 2022-10-21 | 1 | CRS-GUP-DHI-DT-22-963 | 2022-11-07 | NC | DHI-GUP-DT-21-096 | 2021-11-10 | 0 | CRS-GUP-DHI-DT-21-081 | 2021-12-13 | NC | DE-GUP-DT-E-22-835 | 2022-10-21 | 1 | CRS-GUP-DHI-DT-22-963 | 2022-11-07 | NC
| GUP | CC07 | P1 | MB | 123082 |  | GUP-CC07-P1MB-123082 | GT_Foundation Loads Intensity | FI | 2022-04-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Civil | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-835 | 2022-10-21 | 2 | CRS-GUP-DHI-DT-22-963 | 2022-11-07 | NC | DHI-GUP-DT-21-096 | 2021-11-10 | 0 | N/A | 2021-12-14 | N/A | DHI-GUP-DT-21-173 | 2021-12-15 | 1 | CRS-GUP-DHI-DT-21-150 | 2022-01-12 | NC | DE-GUP-DT-E-22-835 | 2022-10-21 | 2 | CRS-GUP-DHI-DT-22-963 | 2022-11-07 | NC
| GUP | XA00 | P1 | MB | 123072 |  | GUP-XA00-P1MB-123072 | GT_General Arrangement Drawing | FI | 2022-04-01 |  | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Mech. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-243 | 2022-05-23 | 1 | CRS-GUP-DHI-DT-22-427 | 2022-06-14 | NC | DHI-GUP-DT-21-069 | 2021-10-15 | 0 | CRS-GUP-DHI-DT-21-060 | 2021-11-08 | RC | DE-GUP-DT-E-22-243 | 2022-05-23 | 1 | CRS-GUP-DHI-DT-22-427 | 2022-06-14 | NC
| GUP | XA00 | P1 | MB | 123091 |  | GUP-XA00-P1MB-123091 | GT_Generator control panel layout CHA | FI | 2022-08-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Elec. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-241 | 2022-05-23 | 0 | CRS-GUP-DHI-DT-22-415 | 2022-06-13 | NC | DE-GUP-DT-E-22-241 | 2022-05-23 | 0 | CRS-GUP-DHI-DT-22-415 | 2022-06-13 | NC
| GUP | YT10 | P1 | MB | 123106 |  | GUP-YT10-P1MB-123106 | GT_Generator Relay Protection | FI | 2022-08-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Elec. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-907 | 2022-11-03 | 1 | CRS-GUP-DHI-DT-22-1055 | 2022-11-17 | NC | DE-GUP-DT-E-22-241 | 2022-05-23 | 0 | CRS-GUP-DHI-DT-22-415 | 2022-06-13 | RC | DE-GUP-DT-E-22-907 | 2022-11-03 | 1 | CRS-GUP-DHI-DT-22-1055 | 2022-11-17 | NC
| GUP | XA00 | P1 | MB | 123094 |  | GUP-XA00-P1MB-123094 | GT_Hazardous Area Layout | FI | 2022-08-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-051 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-210 | 2022-02-20 | NC | DHI-GUP-DT-22-051 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-210 | 2022-02-20 | NC
| GUP | XA00 | P1 | MB | 123100 |  | GUP-XA00-P1MB-123100 | GT_Installation drawings | FI | 2022-12-31 |  | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-1140 | 2022-12-21 | 0 | CRS-GUP-DHI-DT-22-1388 | 2023-01-03 | NC | DE-GUP-DT-E-22-1140 | 2022-12-21 | 0 | CRS-GUP-DHI-DT-22-1388 | 2023-01-03 | NC
| GUP | XA00 | P1 | MB | 123090 |  | GUP-XA00-P1MB-123090 | GT_LER internal layout | FI | 2022-08-01 |  | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | I&C | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-907 | 2022-11-03 | 1 | CRS-GUP-DHI-DT-22-1029 | 2022-11-13 | NC | DE-GUP-DT-E-22-241 | 2022-05-23 | 0 | CRS-GUP-DHI-DT-22-415 | 2022-06-13 | NC | DE-GUP-DT-E-22-907 | 2022-11-03 | 1 | CRS-GUP-DHI-DT-22-1029 | 2022-11-13 | NC
| GUP | XW01 | P1 | MB | 123107 |  | GUP-XW01-P1MB-123107 | GT_Lube Oil Specification | FI | 2022-04-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-211 | 2022-05-11 | 0 | CRS-GUP-DHI-DT-22-393 | 2022-06-07 | NC | DHI-GUP-DT-22-211 | 2022-05-11 | 0 | CRS-GUP-DHI-DT-22-393 | 2022-06-07 | NC
| GUP | XG02 | P1 | MB | 123023 |  | GUP-XG02-P1MB-123023 | GT_P&ID Air Intake System MBL | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-996 | 2023-12-15 | 1 | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AC | DE-GUP-DT-E-22-640 | 2022-09-08 | 0(CP) | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-23-996 | 2023-12-15 | 1
| GUP | XG02 | P1 | MB | 123024 |  | GUP-XG02-P1MB-123024 | GT_P&ID Compressor Washing System SDB | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-996 | 2023-12-15 | 1 | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AC | DE-GUP-DT-E-22-619 | 2022-09-05 | 0(CP) | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-23-996 | 2023-12-15 | 1
| GUP | XG02 | P1 | MB | 123025 |  | GUP-XG02-P1MB-123025 | GT_P&ID Cooling and Sealing Air System MBH10 | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-816 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1140 | 2022-11-23 | AA | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AA | DE-GUP-DT-E-22-816 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1140 | 2022-11-23 | AA
| GUP | XG02 | P1 | MB | 123026 |  | GUP-XG02-P1MB-123026 | GT_P&ID Drying system, stationary | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-816 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1140 | 2022-11-23 | AA | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AA | DE-GUP-DT-E-22-816 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1140 | 2022-11-23 | AA
| GUP | XG02 | P1 | MB | 123027 |  | GUP-XG02-P1MB-123027 | GT_P&ID Inlet Heat System | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-816 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1140 | 2022-11-23 | AA | DHI-GUP-DT-22-223 | 2022-05-17 | A | CRS-GUP-DHI-DT-22-402 | 2022-06-08 | AA | DE-GUP-DT-E-22-816 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1140 | 2022-11-23 | AA
| GUP | XG02 | P1 | MB | 123028 |  | GUP-XG02-P1MB-123028 | GT_P&ID Fire Detection and Extinguishing System SGJ | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-816 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1140 | 2022-11-23 | AA | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AA | DE-GUP-DT-E-22-816 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1140 | 2022-11-23 | AA
| GUP | XG02 | P1 | MB | 123029 |  | GUP-XG02-P1MB-123029 | GT_P&ID Gas Detection System SFY | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-996 | 2023-12-15 | 1 | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AC | DE-GUP-DT-E-22-652 | 2022-09-08 | 0(CP) | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-23-996 | 2023-12-15 | 1
| GUP | XG02 | P1 | MB | 123030 |  | GUP-XG02-P1MB-123030 | GT_P&ID Gas Fuel System MBP | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-074 | 2024-03-14 | 1 | CRS-GUP-DHI-DT-24-025 | 2024-03-11 | AA | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AC | DE-GUP-DT-E-22-619 | 2022-09-05 | 0(CP) | CRS-GUP-DHI-DT-24-025 | 2024-03-11 | AA | DE-GUP-DT-E-24-074 | 2024-03-14 | 1
| GUP | XG02 | P1 | MB | 123031 |  | GUP-XG02-P1MB-123031 | GT_P&ID Gas Turbine System MBA | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-1239 | 2023-01-09 | 1 | CRS-GUP-DHI-DT-22-1071 | 2022-11-19 | AA | DHI-GUP-DT-21-110 | 2021-11-19 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AC | DE-GUP-DT-E-22-713 | 2022-09-29 | 0(CP) | CRS-GUP-DHI-DT-22-1071 | 2022-11-19 | AA | DE-GUP-DT-E-22-1239 | 2023-01-09 | 1
| GUP | XG02 | P1 | MB | 123032 |  | GUP-XG02-P1MB-123032 | GT_P&ID Gear system MBK | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-996 | 2023-12-15 | 1 | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AC | DE-GUP-DT-E-22-619 | 2022-09-05 | 0(CP) | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-23-996 | 2023-12-15 | 1
| GUP | XG02 | P1 | MB | 123033 |  | GUP-XG02-P1MB-123033 | GT_P&ID Generator System MKA | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-996 | 2023-12-15 | 1 | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AC | DE-GUP-DT-E-22-619 | 2022-09-05 | 0(CP) | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-23-996 | 2023-12-15 | 1
| GUP | XG02 | P1 | MB | 123034 |  | GUP-XG02-P1MB-123034 | GT_P&ID HVAC for LER | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-996 | 2023-12-15 | 1 | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AC | DE-GUP-DT-E-22-619 | 2022-09-05 | 0(CP) | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-23-996 | 2023-12-15 | 1
| GUP | XG02 | P1 | MB | 123035 |  | GUP-XG02-P1MB-123035 | GT_P&ID Instrument Air System QFA | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-825 | 2022-10-20 | 0 | CRS-GUP-DHI-DT-22-1142 | 2022-11-23 | AA | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AC | DE-GUP-DT-E-22-652 | 2022-09-08 | B | CRS-GUP-DHI-DT-22-877 | 2022-10-09 | AA | DE-GUP-DT-E-22-825 | 2022-10-20 | 0 | CRS-GUP-DHI-DT-22-1142 | 2022-11-23 | AA
| GUP | XG02 | P1 | MB | 123022 |  | GUP-XG02-P1MB-123022 | GT_P&ID Legend for Symbols | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-640 | 2022-09-08 | 0 | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AA | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AA | DE-GUP-DT-E-22-640 | 2022-09-08 | 0
| GUP | XG02 | P1 | MB | 123036 |  | GUP-XG02-P1MB-123036 | GT_P&ID Liquid fuel system | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-996 | 2023-12-15 | 1 | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AC | DE-GUP-DT-E-22-640 | 2022-09-08 | 0(CP) | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-23-996 | 2023-12-15 | 1
| GUP | XG02 | P1 | MB | 123037 |  | GUP-XG02-P1MB-123037 | GT_P&ID Lube Oil System MBV | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-996 | 2023-12-15 | 1 | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AC | DE-GUP-DT-E-22-619 | 2022-09-05 | 0(CP) | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-23-996 | 2023-12-15 | 1
| GUP | XG02 | P1 | MB | 123038 |  | GUP-XG02-P1MB-123038 | GT_P&ID Pulsation Monitoring System MBX | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-864 | 2022-10-27 | 0 | CRS-GUP-DHI-DT-22-1145 | 2022-11-23 | AA | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AC | DE-GUP-DT-E-22-652 | 2022-09-08 | B | CRS-GUP-DHI-DT-22-877 | 2022-10-09 | AA | DE-GUP-DT-E-22-864 | 2022-10-27 | 0 | CRS-GUP-DHI-DT-22-1145 | 2022-11-23 | AA
| GUP | XG02 | P1 | MB | 123039 |  | GUP-XG02-P1MB-123039 | GT_P&ID Purge air system | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-996 | 2023-12-15 | 1 | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AC | DE-GUP-DT-E-22-619 | 2022-09-05 | 0(CP) | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-23-996 | 2023-12-15 | 1
| GUP | XG02 | P1 | MB | 123040 |  | GUP-XG02-P1MB-123040 | GT_P&ID Starting System MBJ | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-816 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1140 | 2022-11-23 | AA | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AA | DE-GUP-DT-E-22-816 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1140 | 2022-11-23 | AA
| GUP | XG02 | P1 | MB | 123041 |  | GUP-XG02-P1MB-123041 | GT_P&ID Ventilation System GT-Enclosure SAG | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-816 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1140 | 2022-11-23 | AA | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AA | DE-GUP-DT-E-22-816 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1140 | 2022-11-23 | AA
| GUP | XA00 | P1 | MB | 123105 |  | GUP-XA00-P1MB-123105 | GT_Removal and Service Layout | FI | 2022-04-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-21-108 | 2021-11-18 | 0 | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | NC | DHI-GUP-DT-21-108 | 2021-11-18 | 0 | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | NC
| GUP | YF00 | P1 | MB | 123108 |  | GUP-YF00-P1MB-123108 | GT_Sequence Diagram | FI | 2022-07-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-241 | 2022-05-23 | 0 | CRS-GUP-DHI-DT-22-415 | 2022-06-13 | NC | DE-GUP-DT-E-22-241 | 2022-05-23 | 0 | CRS-GUP-DHI-DT-22-415 | 2022-06-13 | NC
| GUP | YL21 | P1 | MB | 123062 |  | GUP-YL21-P1MB-123062 | GT_Setting List - Gas Fuel System MBP | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | YL21 | P1 | MB | 123063 |  | GUP-YL21-P1MB-123063 | GT_Setting List - Gas Turbine System MBA | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | YL21 | P1 | MB | 123064 |  | GUP-YL21-P1MB-123064 | GT_Setting List - Air Intake System MBL | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | YL21 | P1 | MB | 123065 |  | GUP-YL21-P1MB-123065 | GT_Setting List - Compressor Washing System SDB | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | YL21 | P1 | MB | 123066 |  | GUP-YL21-P1MB-123066 | GT_Setting List - Purge air system | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | YL21 | P1 | MB | 123067 |  | GUP-YL21-P1MB-123067 | GT_Setting List - Drying System Stationary MPS | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | YL21 | P1 | MB | 123068 |  | GUP-YL21-P1MB-123068 | GT_Setting List - Inlet Heat System | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | YL21 | P1 | MB | 123069 |  | GUP-YL21-P1MB-123069 | GT_Setting List - Fire Detection and Extinguishing System SGJ | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | YL21 | P1 | MB | 123070 |  | GUP-YL21-P1MB-123070 | GT_Setting List - Gas Detection System SFY | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | YL21 | P1 | MB | 123071 |  | GUP-YL21-P1MB-123071 | GT_Setting List - Gear System MBK | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | YL21 | P1 | MB | 123075 |  | GUP-YL21-P1MB-123075 | GT_Setting List - Generator System MKA | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | YL21 | P1 | MB | 123076 |  | GUP-YL21-P1MB-123076 | GT_Setting List - HVAC for LER | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | YL21 | P1 | MB | 123077 |  | GUP-YL21-P1MB-123077 | GT_Setting List - Liquid fuel system | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | YL21 | P1 | MB | 123078 |  | GUP-YL21-P1MB-123078 | GT_Setting List - Lube Oil System MBV | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | YL21 | P1 | MB | 123081 |  | GUP-YL21-P1MB-123081 | GT_Setting List - Starting System MBJ | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | YL21 | P1 | MB | 123084 |  | GUP-YL21-P1MB-123084 | GT_Setting List - Ventilation System GT-Enclosure SAG | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | YL13 | P1 | MB | 123089 |  | GUP-YL13-P1MB-123089 | GT_Signal Exchange List (HW) | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-241 | 2022-05-23 | 0 | CRS-GUP-DHI-DT-22-415 | 2022-06-13 | NC | DE-GUP-DT-E-22-241 | 2022-05-23 | 0 | CRS-GUP-DHI-DT-22-415 | 2022-06-13 | NC
| GUP | YL13 | P1 | MB | 123103 |  | GUP-YL13-P1MB-123103 | GT_Signal Transfer List (DCS) OPC | FI | 2022-07-01 |  | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-241 | 2022-05-23 | 0 | CRS-GUP-DHI-DT-22-415 | 2022-06-13 | NC | DE-GUP-DT-E-22-241 | 2022-05-23 | 0 | CRS-GUP-DHI-DT-22-415 | 2022-06-13 | NC
| GUP | YU01 | P1 | MB | 123085 |  | GUP-YU01-P1MB-123085 | GT_Single Line Diagram LV | FI | 2022-07-01 |  | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Elec. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-241 | 2022-05-23 | 0 | CRS-GUP-DHI-DT-22-415 | 2022-06-13 | NC | DE-GUP-DT-E-22-241 | 2022-05-23 | 0 | CRS-GUP-DHI-DT-22-415 | 2022-06-13 | NC
| GUP | YU01 | P1 | MB | 123086 |  | GUP-YU01-P1MB-123086 | GT_Single Line Diagram MV | FI | 2022-07-01 |  | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Elec. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-241 | 2022-05-23 | 0 | CRS-GUP-DHI-DT-22-415 | 2022-06-13 | NC | DE-GUP-DT-E-22-241 | 2022-05-23 | 0 | CRS-GUP-DHI-DT-22-415 | 2022-06-13 | NC
| GUP | XA00 | P1 | MB | 123102 |  | GUP-XA00-P1MB-123102 | GT_Site El Layout | FI | 2022-07-01 |  | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-241 | 2022-05-23 | 0 | CRS-GUP-DHI-DT-22-415 | 2022-06-13 | NC | DE-GUP-DT-E-22-241 | 2022-05-23 | 0 | CRS-GUP-DHI-DT-22-415 | 2022-06-13 | NC
| GUP | XS00 | P1 | MB | 123000 |  | GUP-XS00-P1MB-123000 | GT_System Description - Air Intake System MBL | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Mech. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-996 | 2023-12-15 | 1 | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AC | DE-GUP-DT-E-22-640 | 2022-09-08 | 0(CP) | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-23-996 | 2023-12-15 | 1
| GUP | XS00 | P1 | MB | 123001 |  | GUP-XS00-P1MB-123001 | GT_System Description - Compressor Washing System SDB | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Mech. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-996 | 2023-12-15 | 1 | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AC | DE-GUP-DT-E-22-619 | 2022-09-05 | 0(CP) | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-23-996 | 2023-12-15 | 1
| GUP | XS00 | P1 | MB | 123002 |  | GUP-XS00-P1MB-123002 | GT_System Description - Control System | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Mech. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-816 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1140 | 2022-11-23 | AA | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AC | DE-GUP-DT-E-22-251 | 2022-05-26 | B | CRS-GUP-DHI-DT-22-452 | 2022-06-21 | AA | DE-GUP-DT-E-22-816 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1140 | 2022-11-23 | AA
| GUP | XS00 | P1 | MB | 123003 |  | GUP-XS00-P1MB-123003 | GT_System Description - Cooling and Sealing Air System MBH10 | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Mech. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-816 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1140 | 2022-11-23 | AA | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AA | DE-GUP-DT-E-22-816 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1140 | 2022-11-23 | AA
| GUP | XS00 | P1 | MB | 123004 |  | GUP-XS00-P1MB-123004 | GT_System Description - Inlet Heat System | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Mech. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-816 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1140 | 2022-11-23 | AA | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AC | DHI-GUP-DT-22-223 | 2022-05-17 | B | CRS-GUP-DHI-DT-22-402 | 2022-06-08 | AA | DE-GUP-DT-E-22-816 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1140 | 2022-11-23 | AA
| GUP | XS00 | P1 | MB | 123005 |  | GUP-XS00-P1MB-123005 | GT_System Description - Fire Detection and Extinguishing System SGJ | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Mech. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-816 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1140 | 2022-11-23 | AA | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AA | DE-GUP-DT-E-22-816 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1140 | 2022-11-23 | AA
| GUP | XS00 | P1 | MB | 123006 |  | GUP-XS00-P1MB-123006 | GT_System Description - Gas Detection System SFY | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Mech. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-996 | 2023-12-15 | 1 | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AC | DE-GUP-DT-E-22-652 | 2022-09-08 | 0(CP) | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-23-996 | 2023-12-15 | 1
| GUP | XS00 | P1 | MB | 123007 |  | GUP-XS00-P1MB-123007 | GT_System Description - Gas Fuel System MBP | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Mech. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-996 | 2023-12-15 | 1 | CRS-GUP-DHI-DT-24-025 | 2024-03-11 | AA | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AC | DE-GUP-DT-E-22-619 | 2022-09-05 | 0(CP) | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-23-996 | 2023-12-15 | 1 | CRS-GUP-DHI-DT-24-025 | 2024-03-11 | AA
| GUP | XS00 | P1 | MB | 123008 |  | GUP-XS00-P1MB-123008 | GT_System Description - Gas Turbine System MBA | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Mech. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-1239 | 2023-01-09 | 1 | CRS-GUP-DHI-DT-22-1071 | 2022-11-19 | AA | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AC | DE-GUP-DT-E-22-713 | 2022-09-29 | 0(CP) | CRS-GUP-DHI-DT-22-1071 | 2022-11-19 | AA | DE-GUP-DT-E-22-1239 | 2023-01-09 | 1
| GUP | XS00 | P1 | MB | 123009 |  | GUP-XS00-P1MB-123009 | GT_System Description - Gear System MBK | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Mech. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-996 | 2023-12-15 | 1 | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AC | DE-GUP-DT-E-22-619 | 2022-09-05 | 0(CP) | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-23-996 | 2023-12-15 | 1
| GUP | XS00 | P1 | MB | 123010 |  | GUP-XS00-P1MB-123010 | GT_System Description - Generator System MKA | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Mech. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-996 | 2023-12-15 | 1 | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AC | DE-GUP-DT-E-22-619 | 2022-09-05 | 0(CP) | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-23-996 | 2023-12-15 | 1
| GUP | XS00 | P1 | MB | 123011 |  | GUP-XS00-P1MB-123011 | GT_System Description - HVAC for LER | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Mech. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-996 | 2023-12-15 | 1 | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AC | DE-GUP-DT-E-22-619 | 2022-09-05 | 0(CP) | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-23-996 | 2023-12-15 | 1
| GUP | XS00 | P1 | MB | 123012 |  | GUP-XS00-P1MB-123012 | GT_System Description - Liquid fuel system | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Mech. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-996 | 2023-12-15 | 1 | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AC | DE-GUP-DT-E-22-640 | 2022-09-08 | 0(CP) | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-23-996 | 2023-12-15 | 1
| GUP | XS00 | P1 | MB | 123013 |  | GUP-XS00-P1MB-123013 | GT_System Description - Lube Oil System MBV | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Mech. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-996 | 2023-12-15 | 1 | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AC | DE-GUP-DT-E-22-619 | 2022-09-05 | 0(CP) | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-23-996 | 2023-12-15 | 1
| GUP | XS00 | P1 | MB | 123014 |  | GUP-XS00-P1MB-123014 | GT_System Description - Pulsation Monitoring System MBX | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Mech. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-864 | 2022-10-27 | 0 | CRS-GUP-DHI-DT-22-1145 | 2022-11-23 | AA | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AC | DE-GUP-DT-E-22-652 | 2022-09-08 | B | CRS-GUP-DHI-DT-22-877 | 2022-10-09 | AA | DE-GUP-DT-E-22-864 | 2022-10-27 | 0 | CRS-GUP-DHI-DT-22-1145 | 2022-11-23 | AA
| GUP | XS00 | P1 | MB | 123015 |  | GUP-XS00-P1MB-123015 | GT_System Description - Safety System | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Mech. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-1105 | 2022-12-16 | 0 | CRS-GUP-DHI-DT-22-1063 | 2022-11-19 | AA | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | RC | DE-GUP-DT-E-22-654 | 2022-09-14 | B | CRS-GUP-DHI-DT-22-1063 | 2022-11-19 | AA | DE-GUP-DT-E-22-1105 | 2022-12-16 | 0
| GUP | XS00 | P1 | MB | 123016 |  | GUP-XS00-P1MB-123016 | GT_System Description - Starting System MBJ | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Mech. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-816 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1140 | 2022-11-23 | AA | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AA | DE-GUP-DT-E-22-816 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1140 | 2022-11-23 | AA
| GUP | XS00 | P1 | MB | 123017 |  | GUP-XS00-P1MB-123017 | GT_System Description - Turbine Governor | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Mech. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-1105 | 2022-12-16 | 0 | CRS-GUP-DHI-DT-22-1071 | 2022-11-19 | AA | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AC | DE-GUP-DT-E-22-713 | 2022-09-29 | B | CRS-GUP-DHI-DT-22-1071 | 2022-11-19 | AA | DE-GUP-DT-E-22-1105 | 2022-12-16 | 0
| GUP | XS00 | P1 | MB | 123018 |  | GUP-XS00-P1MB-123018 | GT_System Description - Ventilation System GT-Enclosure SAG | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Mech. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-816 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1140 | 2022-11-23 | AA | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AA | DE-GUP-DT-E-22-816 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1140 | 2022-11-23 | AA
| GUP | XS00 | P1 | MB | 123019 |  | GUP-XS00-P1MB-123019 | GT_System Description -Drying System Stationary MPS | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Mech. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-816 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1140 | 2022-11-23 | AA | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AA | DE-GUP-DT-E-22-816 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1140 | 2022-11-23 | AA
| GUP | XS00 | P1 | MB | 123020 |  | GUP-XS00-P1MB-123020 | GT_System Description -Purge air system | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Mech. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-996 | 2023-12-15 | 1 | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DHI-GUP-DT-21-107 | 2021-11-18 | A | CRS-GUP-DHI-DT-21-080 | 2021-12-13 | AC | DE-GUP-DT-E-22-619 | 2022-09-05 | 0(CP) | N/A(메일로 송부) | 2023-12-14 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-23-996 | 2023-12-15 | 1
| GUP | PL03 | P1 | MB | 123074 |  | GUP-PL03-P1MB-123074 | GT_Terminal Points Drawing (Delivery Limit Drawing) | FI | 2022-07-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-243 | 2022-05-23 | 1 | CRS-GUP-DHI-DT-22-427 | 2022-06-14 | NC | DHI-GUP-DT-21-069 | 2021-10-15 | 0 | CRS-GUP-DHI-DT-21-060 | 2021-11-08 | RC | DE-GUP-DT-E-22-243 | 2022-05-23 | 1 | CRS-GUP-DHI-DT-22-427 | 2022-06-14 | NC
| GUP | XA00 | P1 | MB | 123099 |  | GUP-XA00-P1MB-123099 | GT_Turbine control panel layout CJP | FI | 2022-07-01 |  | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | I&C | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-241 | 2022-05-23 | 0 | CRS-GUP-DHI-DT-22-415 | 2022-06-13 | NC | DE-GUP-DT-E-22-241 | 2022-05-23 | 0 | CRS-GUP-DHI-DT-22-415 | 2022-06-13 | NC
| GUP | XA00 | P1 | MB | 123098 |  | GUP-XA00-P1MB-123098 | GT_Unit Control Panel Layout CJD | FI | 2022-07-01 |  | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | I&C | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-241 | 2022-05-23 | 0 | CRS-GUP-DHI-DT-22-415 | 2022-06-13 | NC | DE-GUP-DT-E-22-241 | 2022-05-23 | 0 | CRS-GUP-DHI-DT-22-415 | 2022-06-13 | NC
| GUP | XS00 | P1 | MB | 123101 |  | GUP-XS00-P1MB-123101 | GT_System description - Instrument air system QFA | FA | 2022-04-01 | 2022-09-01 | 플랜트기술팀(Mech.) | 정재원 |  | R |  |  | GTG | CCPP | GT | Mech. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-1239 | 2023-01-09 | 1 | CRS-GUP-DHI-DT-22-779 | 2022-09-16 | AA | DHI-GUP-DT-22-052 | 2022-01-28 | A | CRS-GUP-DHI-DT-22-211 | 2022-02-20 | AC | DE-GUP-DT-E-22-652 | 2022-09-08 | 0(CP) | CRS-GUP-DHI-DT-22-779 | 2022-09-16 | AA | DE-GUP-DT-E-22-1239 | 2023-01-09 | 1
| GUP | XV00 | P1 | MB | 123152 |  | GUP-XV00-P1MB-123152 | GT_Aggregate component list - Instrument air system QFA | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-050 | 2022-02-09 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC | DHI-GUP-DT-22-050 | 2022-02-09 | 0 | CRS-GUP-DHI-DT-22-209 | 2022-02-20 | NC
| GUP | XV03 | P1 | MB | 123153 |  | GUP-XV03-P1MB-123153 | GT_Technical Specification Synchronous Generator | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Elec. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-241 | 2022-05-23 | 0 | CRS-GUP-DHI-DT-22-415 | 2022-06-13 | NC | DE-GUP-DT-E-22-241 | 2022-05-23 | 0 | CRS-GUP-DHI-DT-22-415 | 2022-06-13 | NC
| GUP | XS00 | P1 | MB | 123148 |  | GUP-XS00-P1MB-123148 | GT_Utility Requirements | FI | 2022-07-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GT | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-342 | 2022-06-28 | 0 | CRS-GUP-DHI-DT-22-549 | 2022-07-27 | NC | DE-GUP-DT-E-22-342 | 2022-06-28 | 0 | CRS-GUP-DHI-DT-22-549 | 2022-07-27 | NC
| GUP | YR04 | P1 | MB | 123135 |  | GUP-YR04-P1MB-123135 | GT_Remote connection description | FI | 2022-08-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GTG | I&C | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-342 | 2022-06-28 | 0 | CRS-GUP-DHI-DT-22-549 | 2022-07-27 | NC | DE-GUP-DT-E-22-342 | 2022-06-28 | 0 | CRS-GUP-DHI-DT-22-549 | 2022-07-27 | NC
| GUP | YR04 | P1 | MB | 123136 |  | GUP-YR04-P1MB-123136 | GT_Remote connection requirements | FI | 2022-08-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GTG | I&C | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-342 | 2022-06-28 | 0 | CRS-GUP-DHI-DT-22-549 | 2022-07-27 | NC | DE-GUP-DT-E-22-342 | 2022-06-28 | 0 | CRS-GUP-DHI-DT-22-549 | 2022-07-27 | NC
| GUP | YR04 | P1 | MB | 123137 |  | GUP-YR04-P1MB-123137 | GT_Remote Services cRSP Security Concept | FI | 2022-08-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GTG | I&C | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-342 | 2022-06-28 | 0 | CRS-GUP-DHI-DT-22-549 | 2022-07-27 | NC | DE-GUP-DT-E-22-342 | 2022-06-28 | 0 | CRS-GUP-DHI-DT-22-549 | 2022-07-27 | NC
| GUP | YL16 | P1 | MB | 123112 |  | GUP-YL16-P1MB-123112 | GT_Cable table | FI | 2022-08-01 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GTG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-342 | 2022-06-28 | 0 | CRS-GUP-DHI-DT-22-549 | 2022-07-27 | NC | DE-GUP-DT-E-22-342 | 2022-06-28 | 0 | CRS-GUP-DHI-DT-22-549 | 2022-07-27 | NC
| GUP | CQ02 | P1 | LCB | 123154 |  | GUP-CQ02-P1LCB-123154 | GT_OPERATION & MAINTENANCE (O&M) MANUAL | FI | 2023-12-26 |  | 플랜트기술팀(Mech.) | 정재원 |  |  |  |  | GTG | CCPP | GTG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-075 | 2024-03-14 | 0 | CRS-GUP-DHI-DT-24-064 | 2024-07-17 | NC | DE-GUP-DT-E-24-075 | 2024-03-14 | 0 | CRS-GUP-DHI-DT-24-064 | 2024-07-17 | NC
| GUP | XW01 | P1 | EKG | 124021 |  | GUP-XW01-P1EKG-124021 | SYSTEM DESCRIPTION FOR FUEL GAS SUPPLY SYSTEM | FA | 2022-07-30 | 2022-11-30 | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | FGSS | CCPP | FGSS | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-401 | 2023-03-30 | 0 | CRS-GUP-DHI-DT-23-1677 | 2023-03-14 | AA | DHI-GUP-DT-21-044 | 2021-09-30 | A | CRS-GUP-DHI-DT-21-041 | 2021-10-18 | RC | DE-GUP-DT-E-22-643 | 2022-09-08 | B | CRS-GUP-DHI-DT-22-809 | 2022-09-19 | RC | DE-GUP-DT-E-23-037 | 2023-01-17 | C | CRS-GUP-DHI-DT-23-1677 | 2023-03-14 | AA | DE-GUP-DT-E-23-401 | 2023-03-30 | 0
| GUP | XW01 | P1 | EKG | 124022 |  | GUP-XW01-P1EKG-124022 | DESIGN CRITERIA FOR FUEL GAS SUPPLY SYSTEM | FA | 2022-07-30 | 2022-11-30 | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | FGSS | CCPP | FGSS | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-401 | 2023-03-30 | 0 | CRS-GUP-DHI-DT-23-1677 | 2023-03-14 | AA | DHI-GUP-DT-21-044 | 2021-09-30 | A | CRS-GUP-DHI-DT-21-041 | 2021-10-18 | RC | DE-GUP-DT-E-22-643 | 2022-09-08 | B | CRS-GUP-DHI-DT-22-809 | 2022-09-19 | RC | DE-GUP-DT-E-23-037 | 2023-01-17 | C | CRS-GUP-DHI-DT-23-1677 | 2023-03-14 | AA | DE-GUP-DT-E-23-401 | 2023-03-30 | 0
| GUP | XG02 | P1 | EKG | 124023 |  | GUP-XG02-P1EKG-124023 | P&I DIAGRAM FOR FUEL GAS SUPPLY SYSTEM | FA | 2022-07-30 | 2022-11-30 | 플랜트기술팀(Mech.) | 박동준 |  |  |  |  | FGSS | CCPP | FGSS | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-401 | 2023-03-30 | 0 | CRS-GUP-DHI-DT-23-1677 | 2023-03-14 | AA | DE-GUP-DT-E-22-643 | 2022-09-08 | A | CRS-GUP-DHI-DT-22-809 | 2022-09-19 | RC | DE-GUP-DT-E-23-037 | 2023-01-17 | B | CRS-GUP-DHI-DT-23-1677 | 2023-03-14 | AA | DE-GUP-DT-E-23-401 | 2023-03-30 | 0
| GUP | XG08 | P1 | EKG | 124024 |  | GUP-XG08-P1EKG-124024 | PROCESS FLOW DIAGRAM FOR FUEL GAS SUPPLY SYSTEM | FA | 2022-07-30 | 2022-11-30 | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | FGSS | CCPP | FGSS | Process | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-401 | 2023-03-30 | 0 | CRS-GUP-DHI-DT-23-1677 | 2023-03-14 | AA | DE-GUP-DT-E-22-643 | 2022-09-08 | A | CRS-GUP-DHI-DT-22-809 | 2022-09-19 | RC | DE-GUP-DT-E-23-037 | 2023-01-17 | B | CRS-GUP-DHI-DT-23-1677 | 2023-03-14 | AA | DE-GUP-DT-E-23-401 | 2023-03-30 | 0
| GUP | XW03 | P1 | EKG | 124025 |  | GUP-XW03-P1EKG-124025 | SIZING CALCULATION FOR FUEL GAS SUPPLY SYSTEM | FA | 2022-07-30 | 2022-11-30 | 플랜트기술팀(Mech.) | 박동준 |  | R |  |  | FGSS | CCPP | FGSS | Process | 2 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-401 | 2023-03-30 | 0 | CRS-GUP-DHI-DT-23-1677 | 2023-03-14 | AA | DE-GUP-DT-E-22-643 | 2022-09-08 | A | CRS-GUP-DHI-DT-22-809 | 2022-09-19 | RC | DE-GUP-DT-E-23-037 | 2023-01-17 | B | CRS-GUP-DHI-DT-23-1677 | 2023-03-14 | AA | DE-GUP-DT-E-23-401 | 2023-03-30 | 0
| GUP | CM01 | P1 | MAA | 125000 |  | GUP-CM01-P1MAA-125000 | ST_AM - Initial specification for TG installation | FI | 2023-01-01 |  | 플랜트기술팀(Mech.) | 오광일 |  | R |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-407 | 2022-07-18 | 0 | CRS-GUP-DHI-DT-22-614 | 2022-08-16 | NC | DE-GUP-DT-E-22-407 | 2022-07-18 | 0 | CRS-GUP-DHI-DT-22-614 | 2022-08-16 | NC
| GUP | CM01 | P1 | MAA | 125003 |  | GUP-CM01-P1MAA-125003 | ST_MAIN ASSEMBLY MANUAL | FI | 2023-03-01 |  | 플랜트기술팀(Mech.) | 오광일 |  | R |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-211 | 2024-08-26 | 2 | 자체 CRS 개정 후 제출 | 2024-08-25 | N/A | DE-GUP-DT-E-23-257 | 2023-02-28 | 0 | CRS-GUP-DHI-DT-23-1710 | 2023-03-14 | NC | DE-GUP-DT-E-23-878 | 2023-11-01 | 1 | 자체 CRS 개정 후 제출 | 2024-08-25 | N/A | DE-GUP-DT-E-24-211 | 2024-08-26 | 2
| GUP | CM01 | P1 | MAA | 125004 |  | GUP-CM01-P1MAA-125004 | ST_Operating Instruction for the Steam Turbine and Acc. | FI | 2022-12-26 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-690 | 2022-09-22 | 0 | CRS-GUP-DHI-DT-22-945 | 2022-10-22 | NC | DE-GUP-DT-E-22-690 | 2022-09-22 | 0 | CRS-GUP-DHI-DT-22-945 | 2022-10-22 | NC
| GUP | CM01 | P1 | MAA | 125005 |  | GUP-CM01-P1MAA-125005 | ST_Maintenance Instruction for the steam turbine and acc. | FI | 2022-12-26 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-048 | 2024-02-19 | 1 | CRS-GUP-DHI-DT-22-749 | 2022-09-12 | NC | DE-GUP-DT-E-22-551 | 2022-08-24 | 0 | CRS-GUP-DHI-DT-22-749 | 2022-09-12 | NC | DE-GUP-DT-E-24-048 | 2024-02-19 | 1
| GUP | XA00 | P1 | MAA | 125008 |  | GUP-XA00-P1MAA-125008 | ST_Layout - Level +6,00m | FI | 2021-12-01 |  | 플랜트기술팀(Mech.) | 오광일 |  | R |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-049 | 2024-02-21 | 2 | CRS-GUP-DHI-DT-22-345 | 2022-05-18 | NC | DHI-GUP-DT-21-179 | 2021-12-16 | 0 | CRS-GUP-DHI-DT-21-120 | 2022-01-07 | NC | DHI-GUP-DT-22-190 | 2022-04-27 | 1 | CRS-GUP-DHI-DT-22-345 | 2022-05-18 | NC | DE-GUP-DT-E-24-049 | 2024-02-21 | 2
| GUP | XA00 | P1 | MAA | 125009 |  | GUP-XA00-P1MAA-125009 | ST_Layout - Level +0,20m | FI | 2021-12-01 |  | 플랜트기술팀(Mech.) | 오광일 |  | R |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-048 | 2024-02-19 | 2 | CRS-GUP-DHI-DT-22-345 | 2022-05-18 | NC | DHI-GUP-DT-21-179 | 2021-12-16 | 0 | CRS-GUP-DHI-DT-21-120 | 2022-01-07 | NC | DHI-GUP-DT-22-190 | 2022-04-27 | 1 | CRS-GUP-DHI-DT-22-345 | 2022-05-18 | NC | DE-GUP-DT-E-24-048 | 2024-02-19 | 2
| GUP | XA00 | P1 | MAA | 125010 |  | GUP-XA00-P1MAA-125010 | ST_Layout - Longitudinal section A-A | FI | 2021-12-01 |  | 플랜트기술팀(Mech.) | 오광일 |  | R |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-049 | 2024-02-21 | 2 | CRS-GUP-DHI-DT-22-345 | 2022-05-18 | NC | DHI-GUP-DT-21-179 | 2021-12-16 | 0 | CRS-GUP-DHI-DT-21-120 | 2022-01-07 | NC | DHI-GUP-DT-22-190 | 2022-04-27 | 1 | CRS-GUP-DHI-DT-22-345 | 2022-05-18 | NC | DE-GUP-DT-E-24-049 | 2024-02-21 | 2
| GUP | XA00 | P1 | MAA | 125011 |  | GUP-XA00-P1MAA-125011 | ST_Layout - Longitudinal section B-B | FI | 2021-12-01 |  | 플랜트기술팀(Mech.) | 오광일 |  | R |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-049 | 2024-02-21 | 2 | CRS-GUP-DHI-DT-22-345 | 2022-05-18 | NC | DHI-GUP-DT-21-179 | 2021-12-16 | 0 | CRS-GUP-DHI-DT-21-120 | 2022-01-07 | NC | DHI-GUP-DT-22-190 | 2022-04-27 | 1 | CRS-GUP-DHI-DT-22-345 | 2022-05-18 | NC | DE-GUP-DT-E-24-049 | 2024-02-21 | 2
| GUP | XA00 | P1 | MAA | 125012 |  | GUP-XA00-P1MAA-125012 | ST_Layout - Cross section 1-1 | FI | 2021-12-01 |  | 플랜트기술팀(Mech.) | 오광일 |  | R |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-049 | 2024-02-21 | 2 | CRS-GUP-DHI-DT-22-345 | 2022-05-18 | NC | DHI-GUP-DT-21-179 | 2021-12-16 | 0 | CRS-GUP-DHI-DT-21-120 | 2022-01-07 | NC | DHI-GUP-DT-22-190 | 2022-04-27 | 1 | CRS-GUP-DHI-DT-22-345 | 2022-05-18 | NC | DE-GUP-DT-E-24-049 | 2024-02-21 | 2
| GUP | XA00 | P1 | MAA | 125013 |  | GUP-XA00-P1MAA-125013 | ST_Layout - Cross section 2-2 | FI | 2021-12-01 |  | 플랜트기술팀(Mech.) | 오광일 |  | R |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-049 | 2024-02-21 | 2 | CRS-GUP-DHI-DT-22-345 | 2022-05-18 | NC | DHI-GUP-DT-21-179 | 2021-12-16 | 0 | CRS-GUP-DHI-DT-21-120 | 2022-01-07 | NC | DHI-GUP-DT-22-190 | 2022-04-27 | 1 | CRS-GUP-DHI-DT-22-345 | 2022-05-18 | NC | DE-GUP-DT-E-24-049 | 2024-02-21 | 2
| GUP | XJ00 | P1 | MAA | 125016 |  | GUP-XJ00-P1MAA-125016 | ST_Detail Drawings. Piping and BOM | FI | 2022-11-06 |  | 플랜트기술팀(Mech.) | 오광일 |  | R |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-25-022 | 2025-02-10 | 4 | 자체 CRS 개정 후 제출 | 2025-02-09 | N/A | DE-GUP-DT-E-23-257 | 2023-02-28 | 0 | DE-GUP-DT-E-23-1710 | 2023-03-14 | NC | DE-GUP-DT-E-23-322 | 2023-03-16 | 1 | CRS-GUP-DHI-DT-23-1797 | 2023-04-04 | NC | DE-GUP-DT-E-23-511 | 2023-04-27 | 2 | CRS-GUP-DHI-DT-23-1944 | 2023-05-11 | NC | DE-GUP-DT-E-24-049 | 2024-02-21 | 3 | 자체 CRS 개정 후 제출 | 2025-02-09 | N/A | DE-GUP-DT-E-25-022 | 2025-02-10 | 4
| GUP | UF00 | P1 | MAA | 125019 |  | GUP-UF00-P1MAA-125019 | ST_TG Foundation Load Plan | FI | 2021-11-15 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Civil | 2 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-079 | 2022-02-18 | 1 | CRS-GUP-DHI-DT-22-239 | 2022-03-07 | NC | DHI-GUP-DT-21-185 | 2021-12-17 | 0 | CRS-GUP-DHI-DT-21-119 | 2022-01-07 | RC | DHI-GUP-DT-22-079 | 2022-02-18 | 1 | CRS-GUP-DHI-DT-22-239 | 2022-03-07 | NC
| GUP | VE01 | P1 | MAA | 125022 |  | GUP-VE01-P1MAA-125022 | ST_Allowable Loadings and Displacements | FI | 2021-11-15 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Civil | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-964 | 2022-11-21 | 2 | CRS-GUP-DHI-DT-22-1202 | 2022-11-30 | NC | DHI-GUP-DT-22-008 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-173 | 2022-01-24 | NC | DE-GUP-DT-E-22-497 | 2022-08-12 | 1 | CRS-GUP-DHI-DT-22-710 | 2022-09-05 | NC | DE-GUP-DT-E-22-964 | 2022-11-21 | 2 | CRS-GUP-DHI-DT-22-1202 | 2022-11-30 | NC
| GUP | CC08 | P1 | MAA | 125023 |  | GUP-CC08-P1MAA-125023 | ST_PENETRATIONS PLAN – LEVEL +6.00m FOR TURBINE | FI | 2022-04-06 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Civil | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-964 | 2022-11-21 | 1 | CRS-GUP-DHI-DT-22-1202 | 2022-11-30 | NC | DHI-GUP-DT-22-161 | 2022-04-11 | 0 | CRS-GUP-DHI-DT-22-322 | 2022-05-02 | NC | DE-GUP-DT-E-22-964 | 2022-11-21 | 1 | CRS-GUP-DHI-DT-22-1202 | 2022-11-30 | NC
| GUP | UF00 | P1 | MAA | 125024 |  | GUP-UF00-P1MAA-125024 | ST_Loading table | FI | 2022-02-15 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Civil | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-580 | 2022-08-30 | 0 | CRS-GUP-DHI-DT-22-789 | 2022-09-19 | NC | DE-GUP-DT-E-22-580 | 2022-08-30 | 0 | CRS-GUP-DHI-DT-22-789 | 2022-09-19 | NC
| GUP | CC08 | P1 | MAA | 125026 |  | GUP-CC08-P1MAA-125026 | ST_STG Foundation- Embedded Elements | FI | 2021-12-01 |  | 플랜트기술팀(Mech.) | 오광일 |  | R |  |  | STG | CCPP | STG | Civil | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-301 | 2022-06-15 | 4 | CRS-GUP-DHI-DT-22-504 | 2022-07-07 | NC | DHI-GUP-DT-21-179 | 2021-12-16 | 0 | CRS-GUP-DHI-DT-21-120 | 2022-01-07 | NC | DHI-GUP-DT-22-062 | 2022-02-11 | 1 | CRS-GUP-DHI-DT-22-224 | 2022-03-05 | I | DHI-GUP-DT-22-107 | 2022-03-08 | 2 | CRS-GUP-DHI-DT-22-269 | 2022-03-29 | RC | DE-GUP-DT-E-22-238 | 2022-05-20 | 3 | CRS-GUP-DHI-DT-22-405 | 2022-06-09 | RC | DE-GUP-DT-E-22-301 | 2022-06-15 | 4 | CRS-GUP-DHI-DT-22-504 | 2022-07-07 | NC
| GUP | CA07 | P1 | MAA | 125027 |  | GUP-CA07-P1MAA-125027 | ST_STG Foundation- Directires for civil work | FI | 2021-11-15 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Civil | 2 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-21-111 | 2021-11-22 | 0 | CRS-GUP-DHI-DT-21-081 | 2021-12-13 | NC | DHI-GUP-DT-21-111 | 2021-11-22 | 0 | CRS-GUP-DHI-DT-21-081 | 2021-12-13 | NC
| GUP | CA07 | P1 | MAA | 125028 |  | GUP-CA07-P1MAA-125028 | ST_STG Foundation- Design criteria and Calculation | FI | 2021-11-15 |  | 플랜트기술팀(Mech.) | 오광일 |  | R |  |  | STG | CCPP | STG | Civil | 2 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-21-111 | 2021-11-22 | 0 | CRS-GUP-DHI-DT-21-081 | 2021-12-13 | NC | DHI-GUP-DT-21-111 | 2021-11-22 | 0 | CRS-GUP-DHI-DT-21-081 | 2021-12-13 | NC
| GUP | CC08 | P1 | MAA | 125029 |  | GUP-CC08-P1MAA-125029 | ST_STG Foundation- Shape&Anchoring | FI | 2021-11-15 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Civil | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-301 | 2022-06-15 | 4 | CRS-GUP-DHI-DT-22-504 | 2022-07-07 | NC | DHI-GUP-DT-21-179 | 2021-12-16 | 0 | CRS-GUP-DHI-DT-21-120 | 2022-01-07 | RC | DHI-GUP-DT-22-062 | 2022-02-11 | 1 | CRS-GUP-DHI-DT-22-224 | 2022-03-05 | I | DHI-GUP-DT-22-107 | 2022-03-08 | 2 | CRS-GUP-DHI-DT-22-269 | 2022-03-29 | NC | DE-GUP-DT-E-22-238 | 2022-05-20 | 3 | CRS-GUP-DHI-DT-22-405 | 2022-06-09 | RC | DE-GUP-DT-E-22-301 | 2022-06-15 | 4 | CRS-GUP-DHI-DT-22-504 | 2022-07-07 | NC
| GUP | YD00 | P1 | MAA | 125030 |  | GUP-YD00-P1MAA-125030 | ST_Lay down plan | FI | 2022-02-15 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-278 | 2022-06-08 | 0 | CRS-GUP-DHI-DT-22-481 | 2022-07-03 | NC | DE-GUP-DT-E-22-278 | 2022-06-08 | 0 | CRS-GUP-DHI-DT-22-481 | 2022-07-03 | NC
| GUP | XV00 | P1 | MAA | 125033 |  | GUP-XV00-P1MAA-125033 | ST_List of Pipelines - Steam-water | FI | 2021-12-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Piping | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-008 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-173 | 2022-01-24 | NC | DHI-GUP-DT-22-008 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-173 | 2022-01-24 | NC
| GUP | XV00 | P1 | MAA | 125034 |  | GUP-XV00-P1MAA-125034 | ST_List of Pipelines - Oil | FI | 2021-12-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Piping | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-008 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-173 | 2022-01-24 | NC | DHI-GUP-DT-22-008 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-173 | 2022-01-24 | NC
| GUP | XV00 | P1 | MAA | 125035 |  | GUP-XV00-P1MAA-125035 | ST_List of Pipelines - HPH | FI | 2021-12-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Piping | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-008 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-173 | 2022-01-24 | NC | DHI-GUP-DT-22-008 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-173 | 2022-01-24 | NC
| GUP | XN00 | P1 | MAA | 125036 |  | GUP-XN00-P1MAA-125036 | ST_List of Valves - Steam-water | FI | 2021-12-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-713 | 2023-07-24 | 1 | CRS-GUP-DHI-DT-23-2091 | 2023-08-08 | NC | DHI-GUP-DT-22-008 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-173 | 2022-01-24 | NC | DE-GUP-DT-E-23-713 | 2023-07-24 | 1 | CRS-GUP-DHI-DT-23-2091 | 2023-08-08 | NC
| GUP | XN00 | P1 | MAA | 125037 |  | GUP-XN00-P1MAA-125037 | ST_List of Valves - Oil | FI | 2021-12-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-008 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-173 | 2022-01-24 | NC | DHI-GUP-DT-22-008 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-173 | 2022-01-24 | NC
| GUP | XN00 | P1 | MAA | 125038 |  | GUP-XN00-P1MAA-125038 | ST_List of Valves - HPH | FI | 2021-12-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-008 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-173 | 2022-01-24 | NC | DHI-GUP-DT-22-008 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-173 | 2022-01-24 | NC
| GUP | CM01 | P1 | MAA | 125041 |  | GUP-CM01-P1MAA-125041 | ST_Assembly manual for Turbine Insulation | FI | 2022-08-15 |  | 플랜트기술팀(Mech.) | 오광일 |  | R |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-006 | 2023-01-12 | 0 | CRS-GUP-DHI-DT-23-1520 | 2023-02-14 | NC | DE-GUP-DT-E-23-006 | 2023-01-12 | 0 | CRS-GUP-DHI-DT-23-1520 | 2023-02-14 | NC
| GUP | XS03 | P1 | MAA | 125042 |  | GUP-XS03-P1MAA-125042 | ST_CM - Start-up conditions | FI | 2021-12-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-161 | 2022-04-11 | 2 | CRS-GUP-DHI-DT-22-322 | 2022-05-02 | NC | DHI-GUP-DT-22-008 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-173 | 2022-01-24 | NC | DHI-GUP-DT-22-062 | 2022-02-11 | 1 | CRS-GUP-DHI-DT-22-224 | 2022-03-05 | I | DHI-GUP-DT-22-161 | 2022-04-11 | 2 | CRS-GUP-DHI-DT-22-322 | 2022-05-02 | NC
| GUP | XG02 | P1 | MAA | 125044 |  | GUP-XG02-P1MAA-125044 | ST_P&I Diagram Steam-Water | FA | 2021-11-01 | 2022-08-15 | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-878 | 2023-11-01 | 1 | CRS-GUP-DHI-DT-22-749 | 2022-09-12 | AA | DHI-GUP-DT-21-118 | 2021-11-26 | A | CRS-GUP-DHI-DT-21-085 | 2021-12-23 | RC | DHI-GUP-DT-22-130 | 2022-03-24 | B | CRS-GUP-DHI-DT-22-291 | 2022-04-17 | RC | DE-GUP-DT-E-22-318 | 2022-06-20 | C | CRS-GUP-DHI-DT-22-606 | 2022-08-16 | AA | DE-GUP-DT-E-22-551 | 2022-08-24 | 0 | CRS-GUP-DHI-DT-22-749 | 2022-09-12 | AA | DE-GUP-DT-E-23-878 | 2023-11-01 | 1
| GUP | XG02 | P1 | MAA | 125045 |  | GUP-XG02-P1MAA-125045 | ST_P&I Diagram Oil | FA | 2021-11-01 | 2022-06-15 | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-601 | 2022-09-01 | 0 | CRS-GUP-DHI-DT-22-345 | 2022-05-18 | AA | DHI-GUP-DT-21-142 | 2021-12-03 | A | CRS-GUP-DHI-DT-21-102 | 2021-12-27 | RC | DHI-GUP-DT-22-079 | 2022-02-18 | B | CRS-GUP-DHI-DT-22-239 | 2022-03-07 | AA | DHI-GUP-DT-22-190 | 2022-04-27 | C | CRS-GUP-DHI-DT-22-345 | 2022-05-18 | AA | DE-GUP-DT-E-22-601 | 2022-09-01 | 0
| GUP | XG02 | P1 | MAA | 125046 |  | GUP-XG02-P1MAA-125046 | ST_P&I Diagram HP Hydraulic | FA | 2021-11-01 | 2022-06-15 | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-301 | 2022-06-15 | 0 | CRS-GUP-DHI-DT-22-504 | 2022-07-07 | NC | DHI-GUP-DT-21-118 | 2021-11-26 | A | CRS-GUP-DHI-DT-21-085 | 2021-12-23 | RC | DHI-GUP-DT-22-085 | 2022-02-23 | B | CRS-GUP-DHI-DT-22-249 | 2022-03-14 | AA | DE-GUP-DT-E-22-301 | 2022-06-15 | 0 | CRS-GUP-DHI-DT-22-504 | 2022-07-07 | NC
| GUP | XG02 | P1 | MAA | 125047 |  | GUP-XG02-P1MAA-125047 | ST_P&I DIAGRAM Vibrations | FA | 2021-11-01 | 2022-06-15 | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-301 | 2022-06-15 | 0 | CRS-GUP-DHI-DT-22-225 | 2022-03-05 | AA | DHI-GUP-DT-21-118 | 2021-11-26 | A | CRS-GUP-DHI-DT-21-085 | 2021-12-23 | AA | DHI-GUP-DT-22-063 | 2022-02-11 | B | CRS-GUP-DHI-DT-22-225 | 2022-03-05 | AA | DE-GUP-DT-E-22-301 | 2022-06-15 | 0
| GUP | XS03 | P1 | MAA | 125048 |  | GUP-XS03-P1MAA-125048 | ST_Functional Description | FA | 2022-03-15 | 2022-08-15 | 플랜트기술팀(Mech.) | 오광일 |  | R |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-106 | 2023-02-02 | 0 | CRS-GUP-DHI-DT-22-845 | 2022-09-24 | AA | DHI-GUP-DT-22-162 | 2022-04-11 | A | CRS-GUP-DHI-DT-22-326 | 2022-05-02 | RC | DE-GUP-DT-E-22-603 | 2022-09-01 | B | CRS-GUP-DHI-DT-22-845 | 2022-09-24 | AA | DE-GUP-DT-E-23-106 | 2023-02-02 | 0
| GUP | YU02 | P1 | MKA | 125050 |  | GUP-YU02-P1MKA-125050 | ST_Single line diagram for Steam Turbine Generator | FI | 2021-12-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-497 | 2022-08-12 | 3 | CRS-GUP-DHI-DT-22-710 | 2022-09-05 | NC | DHI-GUP-DT-22-008 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-173 | 2022-01-24 | NC | DHI-GUP-DT-22-164 | 2022-04-11 | 1 | CRS-GUP-DHI-DT-22-328 | 2022-06-07 | NC | DE-GUP-DT-E-22-301 | 2022-06-15 | 2 | CRS-GUP-DHI-DT-22-504 | 2022-07-07 | NC | DE-GUP-DT-E-22-497 | 2022-08-12 | 3 | CRS-GUP-DHI-DT-22-710 | 2022-09-05 | NC
| GUP | YT10 | P1 | MKY | 125443 |  | GUP-YT10-P1MKY-125443 | ST_Recommended setting report for generator protection relay | FI | 2022-09-15 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-25-050 | 2025-05-13 | 1 | CRS-GUP-DHI-DT-22-709 | 2022-09-05 | NC | DE-GUP-DT-E-22-496 | 2022-08-16 | 0 | CRS-GUP-DHI-DT-22-709 | 2022-09-05 | NC | DE-GUP-DT-E-25-050 | 2025-05-13 | 1
| GUP | YR05 | P1 | MKY | 125056 |  | GUP-YR05-P1MKY-125056 | ST_Technical specification for Generator Control Panel | FA | 2022-07-01 | 2022-11-01 | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-551 | 2022-08-24 | 0 | CRS-GUP-DHI-DT-22-749 | 2022-09-12 | AA | DHI-GUP-DT-22-009 | 2022-01-07 | A | CRS-GUP-DHI-DT-21-174 | 2022-01-24 | RC | DHI-GUP-DT-22-218 | 2022-05-13 | B | CRS-GUP-DHI-DT-22-398 | 2022-06-07 | RC | DE-GUP-DT-E-22-301 | 2022-06-15 | C | CRS-GUP-DHI-DT-22-504 | 2022-07-07 | AA | DE-GUP-DT-E-22-551 | 2022-08-24 | 0 | CRS-GUP-DHI-DT-22-749 | 2022-09-12 | AA
| GUP | XA01 | P1 | MKA | 125058 |  | GUP-XA01-P1MKA-125058 | ST_Sectional drawing of generator | FI | 2021-12-01 |  | 플랜트기술팀(Mech.) | 오광일 |  | R |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-918 | 2022-11-08 | 2 | CRS-GUP-DHI-DT-22-1031 | 2022-11-13 | NC | DHI-GUP-DT-22-008 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-173 | 2022-01-24 | NC | DE-GUP-DT-E-22-278 | 2022-06-08 | 1 | CRS-GUP-DHI-DT-22-481 | 2022-07-03 | NC | DE-GUP-DT-E-22-918 | 2022-11-08 | 2 | CRS-GUP-DHI-DT-22-1031 | 2022-11-13 | NC
| GUP | XA01 | P1 | MKA | 125059 |  | GUP-XA01-P1MKA-125059 | ST_Dimensional drawing of the generator coolers | FI | 2022-08-16 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-523 | 2022-08-19 | 0 | CRS-GUP-DHI-DT-22-718 | 2022-09-05 | NC | DE-GUP-DT-E-22-523 | 2022-08-19 | 0 | CRS-GUP-DHI-DT-22-718 | 2022-09-05 | NC
| GUP | XW03 | P1 | MKA | 125060 |  | GUP-XW03-P1MKA-125060 | ST_Data sheet including characteristic curve for Generator | FA | 2021-12-01 | 2022-08-15 | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-497 | 2022-08-12 | 0 | CRS-GUP-DHI-DT-22-481 | 2022-07-03 | AA | DHI-GUP-DT-22-009 | 2022-01-07 | A | CRS-GUP-DHI-DT-21-174 | 2022-01-24 | RC | DE-GUP-DT-E-22-278 | 2022-06-08 | B | CRS-GUP-DHI-DT-22-481 | 2022-07-03 | AA | DE-GUP-DT-E-22-497 | 2022-08-12 | 0
| GUP | XW03 | P1 | MKA | 125062 |  | GUP-XW03-P1MKA-125062 | ST_Technical datasheet of the generator coolers | FA | 2022-08-16 | 2022-09-22 | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-690 | 2022-09-22 | 0 | CRS-GUP-DHI-DT-22-912 | 2022-10-19 | AA | DE-GUP-DT-E-22-523 | 2022-08-19 | A | CRS-GUP-DHI-DT-22-718 | 2022-09-05 | RC | DE-GUP-DT-E-22-690 | 2022-09-22 | 0 | CRS-GUP-DHI-DT-22-912 | 2022-10-19 | AA
| GUP | YF00 | P1 | CJN | 125065 |  | GUP-YF00-P1CJN-125065 | ST_AVR mathematical model | FI | 2022-05-15 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-601 | 2022-09-01 | 1 | CRS-GUP-DHI-DT-22-777 | 2022-09-16 | NC | DHI-GUP-DT-22-159 | 2022-04-11 | 0 | CRS-GUP-DHI-DT-22-320 | 2022-05-02 | NC | DE-GUP-DT-E-22-601 | 2022-09-01 | 1 | CRS-GUP-DHI-DT-22-777 | 2022-09-16 | NC
| GUP | XG01 | P1 | MKA | 125070 |  | GUP-XG01-P1MKA-125070 | ST_Generator PID | FA | 2022-04-15 | 2022-08-15 | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-301 | 2022-06-15 | 0 | CRS-GUP-DHI-DT-22-504 | 2022-07-07 | NC | DHI-GUP-DT-22-113 | 2022-03-11 | A | CRS-GUP-DHI-DT-22-274 | 2022-04-02 | RC | DHI-GUP-DT-22-218 | 2022-05-13 | B | CRS-GUP-DHI-DT-22-398 | 2022-06-07 | AA | DE-GUP-DT-E-22-301 | 2022-06-15 | 0 | CRS-GUP-DHI-DT-22-504 | 2022-07-07 | NC
| GUP | XA01 | P1 | MKA | 125073 |  | GUP-XA01-P1MKA-125073 | ST_GENERATOR SHAFT END DRAWING | FI | 2022-05-15 |  | 플랜트기술팀(Mech.) | 오광일 |  | R |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-159 | 2022-04-11 | 0 | CRS-GUP-DHI-DT-22-320 | 2022-05-02 | NC | DHI-GUP-DT-22-159 | 2022-04-11 | 0 | CRS-GUP-DHI-DT-22-320 | 2022-05-02 | NC
| GUP | YR02 | P1 | MKA | 125075 |  | GUP-YR02-P1MKA-125075 | ST_NAME PLATE OF GENERATOR & EXCITER | FI | 2022-09-15 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-883 | 2022-10-31 | 0 | CRS-GUP-DHI-DT-22-1024 | 2022-11-13 | NC | DE-GUP-DT-E-22-883 | 2022-10-31 | 0 | CRS-GUP-DHI-DT-22-1024 | 2022-11-13 | NC
| GUP | CM02 | P1 | MKA | 125077 |  | GUP-CM02-P1MKA-125077 | ST_Generator rotor withdrawal procedure | FI | 2022-05-01 |  | 플랜트기술팀(Mech.) | 오광일 |  | R |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-159 | 2022-04-11 | 0 | CRS-GUP-DHI-DT-22-320 | 2022-05-02 | NC | DHI-GUP-DT-22-159 | 2022-04-11 | 0 | CRS-GUP-DHI-DT-22-320 | 2022-05-02 | NC
| GUP | YR05 | P1 | MKY | 125082 |  | GUP-YR05-P1MKY-125082 | ST_LINE AND NEUTRAL CUBICLES | FI | 2022-05-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-149 | 2023-02-09 | 3 | CRS-GUP-DHI-DT-23-1592 | 2023-02-28 | NC | DHI-GUP-DT-22-155 | 2022-04-08 | 0 | CRS-GUP-DHI-DT-22-312 | 2022-04-29 | RC | DHI-GUP-DT-22-212 | 2022-05-11 | 1 | CRS-GUP-DHI-DT-22-394 | 2022-06-07 | NC | DE-GUP-DT-E-22-301 | 2022-06-15 | 2 | CRS-GUP-DHI-DT-22-504 | 2022-07-07 | NC | DE-GUP-DT-E-23-149 | 2023-02-09 | 3 | CRS-GUP-DHI-DT-23-1592 | 2023-02-28 | NC
| GUP | XV00 | P1 | MAA | 125087 |  | GUP-XV00-P1MAA-125087 | ST_Lubricant List | FI | 2022-03-15 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-106 | 2023-02-02 | 1 | CRS-GUP-DHI-DT-23-1614 | 2023-03-02 | NC | DHI-GUP-DT-22-161 | 2022-04-11 | 0 | CRS-GUP-DHI-DT-22-322 | 2022-05-02 | NC | DE-GUP-DT-E-23-106 | 2023-02-02 | 1 | CRS-GUP-DHI-DT-23-1614 | 2023-03-02 | NC
| GUP | YS01 | P1 | MAY | 125091 |  | GUP-YS01-P1MAY-125091 | ST_Softstarter for turning gear | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-149 | 2023-02-09 | 3 | CRS-GUP-DHI-DT-23-1592 | 2023-02-28 | NC | DHI-GUP-DT-22-155 | 2022-04-08 | 0 | CRS-GUP-DHI-DT-22-312 | 2022-04-29 | RC | DHI-GUP-DT-22-212 | 2022-05-11 | 1 | CRS-GUP-DHI-DT-22-394 | 2022-06-07 | RC | DE-GUP-DT-E-22-301 | 2022-06-15 | 2 | CRS-GUP-DHI-DT-22-504 | 2022-07-07 | NC | DE-GUP-DT-E-23-149 | 2023-02-09 | 3 | CRS-GUP-DHI-DT-23-1592 | 2023-02-28 | NC
| GUP | YS01 | P1 | MAY | 125092 |  | GUP-YS01-P1MAY-125092 | ST_DC motor starter | FI | 2022-06-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-149 | 2023-02-09 | 3 | CRS-GUP-DHI-DT-23-1592 | 2023-02-28 | NC | DHI-GUP-DT-22-155 | 2022-04-08 | 0 | CRS-GUP-DHI-DT-22-312 | 2022-04-29 | RC | DHI-GUP-DT-22-212 | 2022-05-11 | 1 | CRS-GUP-DHI-DT-22-394 | 2022-06-07 | NC | DE-GUP-DT-E-22-301 | 2022-06-15 | 2 | CRS-GUP-DHI-DT-22-504 | 2022-07-07 | NC | DE-GUP-DT-E-23-149 | 2023-02-09 | 3 | CRS-GUP-DHI-DT-23-1592 | 2023-02-28 | NC
| GUP | YK00 | P1 | MAY | 125094 |  | GUP-YK00-P1MAY-125094 | ST_I02 - Hook ups for STG | FI | 2022-09-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-432 | 2023-04-07 | 2 | CRS-GUP-DHI-DT-23-1886 | 2023-04-28 | NC | DE-GUP-DT-E-22-278 | 2022-06-08 | 0 | CRS-GUP-DHI-DT-22-481 | 2022-07-03 | NC | DE-GUP-DT-E-22-814 | 2022-10-17 | 1 | CRS-GUP-DHI-DT-22-981 | 2022-11-07 | NC | DE-GUP-DT-E-23-432 | 2023-04-07 | 2 | CRS-GUP-DHI-DT-23-1886 | 2023-04-28 | NC
| GUP | YS00 | P1 | MAY | 125095 |  | GUP-YS00-P1MAY-125095 | ST_I04 - Consumer Schemes | FI | 2022-10-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-407 | 2022-07-18 | 1 | CRS-GUP-DHI-DT-22-614 | 2022-08-16 | NC | DE-GUP-DT-E-22-278 | 2022-06-08 | 0 | CRS-GUP-DHI-DT-22-481 | 2022-07-03 | NC | DE-GUP-DT-E-22-407 | 2022-07-18 | 1 | CRS-GUP-DHI-DT-22-614 | 2022-08-16 | NC
| GUP | YL00 | P1 | MAY | 125096 |  | GUP-YL00-P1MAY-125096 | ST_I05 - MEASUREMENT LIST | FI | 2022-08-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-048 | 2024-02-19 | 2 | CRS-GUP-DHI-DT-22-981 | 2022-11-07 | NC | DE-GUP-DT-E-22-407 | 2022-07-18 | 0 | CRS-GUP-DHI-DT-22-629 | 2022-08-18 | NC | DE-GUP-DT-E-22-814 | 2022-10-17 | 1 | CRS-GUP-DHI-DT-22-981 | 2022-11-07 | NC | DE-GUP-DT-E-24-048 | 2024-02-19 | 2
| GUP | YL19 | P1 | MAY | 125097 |  | GUP-YL19-P1MAY-125097 | ST_I06 - CONSUMER LIST | FI | 2021-12-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-21-155 | 2021-12-08 | 0 | CRS-GUP-DHI-DT-21-148 | 2022-01-12 | NC | DHI-GUP-DT-21-155 | 2021-12-08 | 0 | CRS-GUP-DHI-DT-21-148 | 2022-01-12 | NC
| GUP | YF02 | P1 | MAY | 125098 |  | GUP-YF02-P1MAY-125098 | ST_I08 - CONTROL SYSTEM ARCHITECTURE | FA | 2021-11-01 | 2022-03-01 | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-301 | 2022-06-15 | 0 | CRS-GUP-DHI-DT-22-504 | 2022-07-07 | NC | DHI-GUP-DT-21-139 | 2021-12-01 | A | CRS-GUP-DHI-DT-21-100 | 2021-12-27 | RC | DHI-GUP-DT-22-066 | 2022-02-14 | B | CRS-GUP-DHI-DT-22-228 | 2022-03-05 | AA | DHI-GUP-DT-22-113 | 2022-03-11 | C | CRS-GUP-DHI-DT-22-274 | 2022-04-02 | AA | DE-GUP-DT-E-22-301 | 2022-06-15 | 0 | CRS-GUP-DHI-DT-22-504 | 2022-07-07 | NC
| GUP | YR00 | P1 | CJJ | 125099 |  | GUP-YR00-P1CJJ-125099 | ST_Control system Hardware specification | FI | 2022-08-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-814 | 2022-10-17 | 1 | CRS-GUP-DHI-DT-22-981 | 2022-11-07 | NC | DE-GUP-DT-E-22-407 | 2022-07-18 | 0 | CRS-GUP-DHI-DT-22-629 | 2022-08-18 | RC | DE-GUP-DT-E-22-814 | 2022-10-17 | 1 | CRS-GUP-DHI-DT-22-981 | 2022-11-07 | NC
| GUP | CV03 | P1 | MAY | 125100 |  | GUP-CV03-P1MAY-125100 | ST_Hardware specification for Field Instrumentation for STG | FI | 2022-09-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-057 | 2024-02-26 | 1 | CRS-GUP-DHI-DT-22-718 | 2022-09-05 | NC | DE-GUP-DT-E-22-523 | 2022-08-19 | 0 | CRS-GUP-DHI-DT-22-718 | 2022-09-05 | NC | DE-GUP-DT-E-24-057 | 2024-02-26 | 1
| GUP | YL01 | P1 | CJJ | 125104 |  | GUP-YL01-P1CJJ-125104 | ST_I11 - Signal transfer list between TCS and DCS (internal) | FI | 2022-04-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-407 | 2022-07-18 | 1 | CRS-GUP-DHI-DT-22-614 | 2022-08-16 | NC | DHI-GUP-DT-22-008 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-173 | 2022-01-24 | NC | DE-GUP-DT-E-22-407 | 2022-07-18 | 1 | CRS-GUP-DHI-DT-22-614 | 2022-08-16 | NC
| GUP | YF00 | P1 | CJJ | 125105 |  | GUP-YF00-P1CJJ-125105 | ST_LOGIC DIAGRAMS FOR CONTROL OF FUNCTIONAL GROUPS | FI | 2022-09-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-923 | 2023-11-21 | 3 | CRS-GUP-DHI-DT-22-1024 | 2022-11-13 | NC | DE-GUP-DT-E-22-407 | 2022-07-18 | 0 | CRS-GUP-DHI-DT-22-629 | 2022-08-18 | NC | DE-GUP-DT-E-22-690 | 2022-09-22 | 1 | CRS-GUP-DHI-DT-22-912 | 2022-10-19 | NC | DE-GUP-DT-E-22-883 | 2022-10-31 | 2 | CRS-GUP-DHI-DT-22-1024 | 2022-11-13 | NC | DE-GUP-DT-E-23-923 | 2023-11-21 | 3
| GUP | YL08 | P1 | MAY | 125106 |  | GUP-YL08-P1MAY-125106 | ST_I15 - Trip & Alarm Setting | FI | 2022-08-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-690 | 2022-09-22 | 0 | CRS-GUP-DHI-DT-22-912 | 2022-10-19 | NC | DE-GUP-DT-E-22-690 | 2022-09-22 | 0 | CRS-GUP-DHI-DT-22-912 | 2022-10-19 | NC
| GUP | YD05 | P1 | CJJ | 125108 |  | GUP-YD05-P1CJJ-125108 | ST_I16 - HMI Design | FI | 2022-09-15 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-318 | 2022-06-20 | 0 | CRS-GUP-DHI-DT-22-606 | 2022-08-16 | NC | DE-GUP-DT-E-22-318 | 2022-06-20 | 0 | CRS-GUP-DHI-DT-22-606 | 2022-08-16 | NC
| GUP | YL01 | P1 | CJJ | 125110 |  | GUP-YL01-P1CJJ-125110 | ST_CS - I/O List for TCS/TPS | FI | 2022-08-15 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-250 | 2024-10-18 | 3 | CRS-GUP-DHI-DT-22-737 | 2022-09-12 | NC | DE-GUP-DT-E-22-278 | 2022-06-08 | 0 | CRS-GUP-DHI-DT-22-481 | 2022-07-03 | NC | DE-GUP-DT-E-22-446 | 2022-07-26 | 1 | CRS-GUP-DHI-DT-22-648 | 2022-08-20 | NC | DE-GUP-DT-E-22-531 | 2022-08-23 | 2 | CRS-GUP-DHI-DT-22-737 | 2022-09-12 | NC | DE-GUP-DT-E-24-250 | 2024-10-18 | 3
| GUP | XV00 | P1 | MAA | 125117 |  | GUP-XV00-P1MAA-125117 | ST_List of Equipments | FI | 2021-12-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-008 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-173 | 2022-01-24 | NC | DHI-GUP-DT-22-008 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-173 | 2022-01-24 | NC
| GUP | XL00 | P1 | MAA | 125118 |  | GUP-XL00-P1MAA-125118 | ST_Radiated heat | FI | 2022-10-15 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-690 | 2022-09-22 | 1 | CRS-GUP-DHI-DT-22-992 | 2022-11-13 | NC | DE-GUP-DT-E-22-580 | 2022-08-30 | 0 | CRS-GUP-DHI-DT-22-789 | 2022-09-19 | NC | DE-GUP-DT-E-22-690 | 2022-09-22 | 1 | CRS-GUP-DHI-DT-22-992 | 2022-11-13 | NC
| GUP | DF04 | P1 | MAA | 125119 |  | GUP-DF04-P1MAA-125119 | ST_Rotor dynamics calculation report | FI | 2022-07-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-918 | 2022-11-08 | 0 | CRS-GUP-DHI-DT-22-1031 | 2022-11-13 | NC | DE-GUP-DT-E-22-918 | 2022-11-08 | 0 | CRS-GUP-DHI-DT-22-1031 | 2022-11-13 | NC
| GUP | YT01 | P1 | MAA | 125122 |  | GUP-YT01-P1MAA-125122 | ST_FLASH PIPE for STG - Data for Design | FI | 2022-10-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-288 | 2022-06-13 | 0 | CRS-GUP-DHI-DT-22-524 | 2022-07-19 | NC | DE-GUP-DT-E-22-288 | 2022-06-13 | 0 | CRS-GUP-DHI-DT-22-524 | 2022-07-19 | NC
| GUP | CV03 | P1 | MAY | 125124 |  | GUP-CV03-P1MAY-125124 | ST_VMS of STG - Control system Hardware specification | FI | 2022-09-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-253 | 2022-05-27 | 0 | CRS-GUP-DHI-DT-22-468 | 2022-06-22 | NC | DE-GUP-DT-E-22-253 | 2022-05-27 | 0 | CRS-GUP-DHI-DT-22-468 | 2022-06-22 | NC
| GUP | YL15 | P1 | MAY | 125127 |  | GUP-YL15-P1MAY-125127 | ST_VMS of STG - Cable list | FI | 2022-09-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-253 | 2022-05-27 | 0 | CRS-GUP-DHI-DT-22-468 | 2022-06-22 | NC | DE-GUP-DT-E-22-253 | 2022-05-27 | 0 | CRS-GUP-DHI-DT-22-468 | 2022-06-22 | NC
| GUP | YT01 | P1 | MAA | 125131 |  | GUP-YT01-P1MAA-125131 | ST_Fan & Motor Data sheet for VSC | FI | 2022-09-15 |  | 플랜트기술팀(Mech.) | 오광일 |  | R |  |  | STG | CCPP | STG | Elec. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-918 | 2022-11-08 | 0 | CRS-GUP-DHI-DT-22-1031 | 2022-11-13 | NC | DE-GUP-DT-E-22-918 | 2022-11-08 | 0 | CRS-GUP-DHI-DT-22-1031 | 2022-11-13 | NC
| GUP | YL22 | P1 | MAA | 125137 |  | GUP-YL22-P1MAA-125137 | ST_Tag/Labeling List | FI | 2022-06-08 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-278 | 2022-06-08 | 0 | CRS-GUP-DHI-DT-22-481 | 2022-07-03 | NC | DE-GUP-DT-E-22-278 | 2022-06-08 | 0 | CRS-GUP-DHI-DT-22-481 | 2022-07-03 | NC
| GUP | DE00 | P1 | MAA | 125147 |  | GUP-DE00-P1MAA-125147 | ST_Specification for Steam Trap for Auxiliary ST_Steam and Turbine Drain | FI | 2022-08-16 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-496 | 2022-08-12 | 0 | CRS-GUP-DHI-DT-22-709 | 2022-09-05 | NC | DE-GUP-DT-E-22-496 | 2022-08-12 | 0 | CRS-GUP-DHI-DT-22-709 | 2022-09-05 | NC
| GUP | YF02 | P1 | MAA | 125149 |  | GUP-YF02-P1MAA-125149 | ST_Turbine Overspeed Calculation | FI | 2022-04-11 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-161 | 2022-04-11 | 0 | CRS-GUP-DHI-DT-22-322 | 2022-05-02 | NC | DHI-GUP-DT-22-161 | 2022-04-11 | 0 | CRS-GUP-DHI-DT-22-322 | 2022-05-02 | NC
| GUP | CC05 | P1 | MAA | 125157 |  | GUP-CC05-P1MAA-125157 | ST_STEAM TURBINE MECHANICAL OUTLINE | FI | 2022-01-06 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-008 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-173 | 2022-01-24 | NC | DHI-GUP-DT-22-008 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-173 | 2022-01-24 | NC
| GUP | CC05 | P1 | MAA | 125158 |  | GUP-CC05-P1MAA-125158 | ST_GLAND STEAM CONDENSER OUTLINE_GLAND STEAM EXHAUSTER OUTLINE | FI | 2022-01-06 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-008 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-173 | 2022-01-24 | NC | DHI-GUP-DT-22-008 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-173 | 2022-01-24 | NC
| GUP | CC05 | P1 | MAA | 125165 |  | GUP-CC05-P1MAA-125165 | ST_Manual and Motor Operated Valve Drawings | FI | 2022-08-16 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-496 | 2022-08-12 | 0 | CRS-GUP-DHI-DT-22-709 | 2022-09-05 | NC | DE-GUP-DT-E-22-496 | 2022-08-12 | 0 | CRS-GUP-DHI-DT-22-709 | 2022-09-05 | NC
| GUP | CC05 | P1 | MAA | 125166 |  | GUP-CC05-P1MAA-125166 | ST_LP Steam Strainer Drawing | FI | 2022-04-11 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-646 | 2023-06-28 | 1 | CRS-GUP-DHI-DT-22-322 | 2022-05-02 | NC | DHI-GUP-DT-22-161 | 2022-04-11 | 0 | CRS-GUP-DHI-DT-22-322 | 2022-05-02 | NC | DE-GUP-DT-E-23-646 | 2023-06-28 | 1
| GUP | CC05 | P1 | MAA | 125167 |  | GUP-CC05-P1MAA-125167 | ST_Float Trap Section Outline | FI | 2022-04-11 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-161 | 2022-04-11 | 0 | CRS-GUP-DHI-DT-22-322 | 2022-05-02 | NC | DHI-GUP-DT-22-161 | 2022-04-11 | 0 | CRS-GUP-DHI-DT-22-322 | 2022-05-02 | NC
| GUP | CC05 | P1 | MAA | 125169 |  | GUP-CC05-P1MAA-125169 | ST_Turning gear unit Outline | FI | 2022-02-07 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-066 | 2022-02-14 | 0 | CRS-GUP-DHI-DT-22-228 | 2022-03-05 | NC | DHI-GUP-DT-22-066 | 2022-02-14 | 0 | CRS-GUP-DHI-DT-22-228 | 2022-03-05 | NC
| GUP | XA00 | P1 | PAH | 125177 |  | GUP-XA00-P1PAH-125177 | ST_Condenser Tube Cleaning Systém_Control Panel Outline Drawing | FI | 2022-04-11 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-123 | 2024-05-03 | 1 | CRS-GUP-DHI-DT-22-328 | 2022-06-07 | NC | DHI-GUP-DT-22-164 | 2022-04-11 | 0 | CRS-GUP-DHI-DT-22-328 | 2022-06-07 | NC | DE-GUP-DT-E-24-123 | 2024-05-03 | 1
| GUP | CC05 | P1 | MAA | 125178 |  | GUP-CC05-P1MAA-125178 | ST_Outline of TCS/TPS Cabinet | FI | 2022-08-16 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-161 | 2022-04-11 | 1 | CRS-GUP-DHI-DT-22-322 | 2022-05-02 | NC | DHI-GUP-DT-22-008 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-173 | 2022-01-24 | NC | DHI-GUP-DT-22-161 | 2022-04-11 | 1 | CRS-GUP-DHI-DT-22-322 | 2022-05-02 | NC
| GUP | YT01 | P1 | MAJ | 125181 |  | GUP-YT01-P1MAJ-125181 | ST_Condenser Vacuum Pump | FI | 2022-01-15 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-511 | 2023-04-27 | 3 | CRS-GUP-DHI-DT-23-1944 | 2023-05-11 | NC | DHI-GUP-DT-22-008 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-173 | 2022-01-24 | NC | DE-GUP-DT-E-22-407 | 2022-07-18 | 1 | CRS-GUP-DHI-DT-22-614 | 2022-08-16 | NC | DE-GUP-DT-E-22-531 | 2022-08-23 | 2 | CRS-GUP-DHI-DT-22-737 | 2022-09-12 | NC | DE-GUP-DT-E-23-511 | 2023-04-27 | 3 | CRS-GUP-DHI-DT-23-1944 | 2023-05-11 | NC
| GUP | CC05 | P1 | MAA | 125183 |  | GUP-CC05-P1MAA-125183 | ST_Outline of High Pressure Hydraulic (HPH) Oil Unit (KKS : P1MAX01) | FI | 2022-08-24 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-551 | 2022-08-24 | 1 | CRS-GUP-DHI-DT-22-749 | 2022-09-12 | NC | DHI-GUP-DT-22-016 | 2022-01-07 | 0 | CRS-GUP-DHI-DT-21-173 | 2022-01-24 | NC | DE-GUP-DT-E-22-551 | 2022-08-24 | 1 | CRS-GUP-DHI-DT-22-749 | 2022-09-12 | NC
| GUP | XS03 | P1 | MAX | 125186 |  | GUP-XS03-P1MAX-125186 | ST_Functional description of HPH system | FI | 2022-02-11 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-062 | 2022-03-06 | 0 | CRS-GUP-DHI-DT-22-224 | 2022-03-07 | NC | DHI-GUP-DT-22-062 | 2022-03-06 | 0 | CRS-GUP-DHI-DT-22-224 | 2022-03-07 | NC
| GUP | EC00 | P1 | MKA | 125204 |  | GUP-EC00-P1MKA-125204 | ST_Automatic Synchronizer & Synchronism Check Relay Setting Value Calculation | FI | 2022-07-20 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-407 | 2022-07-18 | 0 | CRS-GUP-DHI-DT-22-629 | 2022-08-18 | NC | DE-GUP-DT-E-22-407 | 2022-07-18 | 0 | CRS-GUP-DHI-DT-22-629 | 2022-08-18 | NC
| GUP | CC05 | P1 | MKA | 125206 |  | GUP-CC05-P1MKA-125206 | ST_Outline Drawing of STG Generator Protection Panel | FI | 2022-03-11 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-113 | 2022-03-11 | 1 | CRS-GUP-DHI-DT-22-274 | 2022-04-02 | NC | DHI-GUP-DT-22-069 | 2022-02-15 | 0 | CRS-GUP-DHI-DT-22-231 | 2022-03-07 | RC | DHI-GUP-DT-22-113 | 2022-03-11 | 1 | CRS-GUP-DHI-DT-22-274 | 2022-04-02 | NC
| GUP | YT01 | P1 | MKY | 125208 |  | GUP-YT01-P1MKY-125208 | ST_Outline of AVR/GCP Cubicle | FI | 2022-03-11 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-113 | 2022-03-11 | 1 | CRS-GUP-DHI-DT-22-274 | 2022-04-02 | NC | DHI-GUP-DT-22-069 | 2022-02-15 | 0 | CRS-GUP-DHI-DT-22-231 | 2022-03-07 | RC | DHI-GUP-DT-22-113 | 2022-03-11 | 1 | CRS-GUP-DHI-DT-22-274 | 2022-04-02 | NC
| GUP | YK09 | P1 | MAA | 125211 |  | GUP-YK09-P1MAA-125211 | ST_CONDENSER OUTLINE AND CONNECTION DETAIL | FI | 2022-04-11 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-105 | 2024-04-04 | 3 | CRS-GUP-DHI-DT-23-1589 | 2023-02-28 | NC | DHI-GUP-DT-22-069 | 2022-02-15 | 0 | CRS-GUP-DHI-DT-22-231 | 2022-03-07 | NC | DHI-GUP-DT-22-159 | 2022-04-11 | 1 | CRS-GUP-DHI-DT-22-320 | 2022-05-02 | NC | DE-GUP-DT-E-23-093 | 2023-01-30 | 2 | CRS-GUP-DHI-DT-23-1589 | 2023-02-28 | NC | DE-GUP-DT-E-24-105 | 2024-04-04 | 3
| GUP | XS03 | P1 | MAA | 125212 |  | GUP-XS03-P1MAA-125212 | ST_Steam Turbine Generator D-EHC system description | FI | 2022-02-15 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-407 | 2022-07-18 | 1 | CRS-GUP-DHI-DT-22-614 | 2022-08-16 | NC | DHI-GUP-DT-22-066 | 2022-02-14 | 0 | CRS-GUP-DHI-DT-22-228 | 2022-03-05 | NC | DE-GUP-DT-E-22-407 | 2022-07-18 | 1 | CRS-GUP-DHI-DT-22-614 | 2022-08-16 | NC
| GUP | YT01 | P1 | PAH | 125214 |  | GUP-YT01-P1PAH-125214 | ST_Condenser_Technical Data Sheet | FI | 2022-02-15 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-066 | 2022-02-14 | 0 | CRS-GUP-DHI-DT-22-228 | 2022-03-05 | NC | DHI-GUP-DT-22-066 | 2022-02-14 | 0 | CRS-GUP-DHI-DT-22-228 | 2022-03-05 | NC
| GUP | XV00 | P1 | MAA | 125215 |  | GUP-XV00-P1MAA-125215 | ST_Specification for STG Lube Oil and Hydraulic Oil | FI | 2022-02-10 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-066 | 2022-02-14 | 0 | CRS-GUP-DHI-DT-22-228 | 2022-03-05 | NC | DHI-GUP-DT-22-066 | 2022-02-14 | 0 | CRS-GUP-DHI-DT-22-228 | 2022-03-05 | NC
| GUP | DM02 | P1 | MAA | 125255 |  | GUP-DM02-P1MAA-125255 | ST_Installation_manual - Generator | FI | 2023-03-31 |  | 플랜트기술팀(Mech.) | 오광일 |  | R |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-257 | 2023-02-28 | 0 | CRS-GUP-DHI-DT-23-1710 | 2023-03-14 | NC | DE-GUP-DT-E-23-257 | 2023-02-28 | 0 | CRS-GUP-DHI-DT-23-1710 | 2023-03-14 | NC
| GUP | CQ02 | P1 | MAA | 125256 |  | GUP-CQ02-P1MAA-125256 | ST_Operatiing_Maintenance_Manual-Generator | FI | 2023-02-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-093 | 2023-01-30 | 0 | CRS-GUP-DHI-DT-23-1610 | 2023-03-02 | NC | DE-GUP-DT-E-23-093 | 2023-01-30 | 0 | CRS-GUP-DHI-DT-23-1610 | 2023-03-02 | NC
| GUP | DN05 | P1 | MAA | 125257 |  | GUP-DN05-P1MAA-125257 | ST_Commissioning manual - Generator | FI | 2023-02-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-006 | 2023-01-12 | 0 | CRS-GUP-DHI-DT-23-1520 | 2023-02-14 | NC | DE-GUP-DT-E-23-006 | 2023-01-12 | 0 | CRS-GUP-DHI-DT-23-1520 | 2023-02-14 | NC
| GUP | DM02 | P1 | MAA | 125260 |  | GUP-DM02-P1MAA-125260 | ST_Installation manual_Condenser | FI | 2023-12-31 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-631 | 2023-06-20 | 0 | CRS-GUP-DHI-DT-23-2056 | 2023-07-15 | NC | DE-GUP-DT-E-23-631 | 2023-06-20 | 0 | CRS-GUP-DHI-DT-23-2056 | 2023-07-15 | NC
| GUP | CY05 | P1 | MAA | 125262 |  | GUP-CY05-P1MAA-125262 | ST_Training Manual for Steam Turbine | FI | 2023-04-16 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-322 | 2023-03-16 | 0 | CRS-GUP-DHI-DT-23-1797 | 2023-04-04 | NC | DE-GUP-DT-E-23-322 | 2023-03-16 | 0 | CRS-GUP-DHI-DT-23-1797 | 2023-04-04 | NC
| GUP | DM02 | P1 | NAA | 125264 |  | GUP-DM02-P1NAA-125264 | ST_Installation manual_NRV | FI | 2023-12-31 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-631 | 2023-06-20 | 0 | CRS-GUP-DHI-DT-23-2056 | 2023-07-15 | NC | DE-GUP-DT-E-23-631 | 2023-06-20 | 0 | CRS-GUP-DHI-DT-23-2056 | 2023-07-15 | NC
| GUP | CQ02 | P1 | NAA | 125265 |  | GUP-CQ02-P1NAA-125265 | ST_Operating and Maintainance Manual Non return extraction flaps (P0LBC01AA201) | FI | 2022-07-29 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-486 | 2022-07-29 | 0 | CRS-GUP-DHI-DT-22-656 | 2022-08-20 | NC | DE-GUP-DT-E-22-486 | 2022-07-29 | 0 | CRS-GUP-DHI-DT-22-656 | 2022-08-20 | NC
| GUP | DN05 | P1 | NAA | 125266 |  | GUP-DN05-P1NAA-125266 | ST_Commisioning_manual Non return extraction flaps (P0LBC01AA201) | FI | 2022-08-24 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-551 | 2022-08-24 | 0 | CRS-GUP-DHI-DT-22-749 | 2022-09-12 | NC | DE-GUP-DT-E-22-551 | 2022-08-24 | 0 | CRS-GUP-DHI-DT-22-749 | 2022-09-12 | NC
| GUP | DM02 | P1 | NAA | 125267 |  | GUP-DM02-P1NAA-125267 | ST_Installation manual_Butterfly valve | FI | 2023-12-31 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-631 | 2023-06-20 | 0 | CRS-GUP-DHI-DT-23-2056 | 2023-07-15 | NC | DE-GUP-DT-E-23-631 | 2023-06-20 | 0 | CRS-GUP-DHI-DT-23-2056 | 2023-07-15 | NC
| GUP | CQ02 | P1 | NAA | 125268 |  | GUP-CQ02-P1NAA-125268 | ST_Operation and Maintenance Manual (butterfly valve) | FI | 2022-08-23 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-531 | 2022-08-23 | 0 | CRS-GUP-DHI-DT-22-737 | 2022-09-12 | NC | DE-GUP-DT-E-22-531 | 2022-08-23 | 0 | CRS-GUP-DHI-DT-22-737 | 2022-09-12 | NC
| GUP | DN05 | P1 | NAA | 125269 |  | GUP-DN05-P1NAA-125269 | ST_Commissioning Manual (Butterfly Valves for isolation and control) | FI | 2022-08-24 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-551 | 2022-08-24 | 0 | CRS-GUP-DHI-DT-22-749 | 2022-09-12 | NC | DE-GUP-DT-E-22-551 | 2022-08-24 | 0 | CRS-GUP-DHI-DT-22-749 | 2022-09-12 | NC
| GUP | CQ02 | P1 | MAA | 125271 |  | GUP-CQ02-P1MAA-125271 | ST_Operating_Maintenance_Manual-Steam Trap | FI | 2023-03-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-093 | 2023-01-30 | 0 | CRS-GUP-DHI-DT-23-1610 | 2023-03-02 | NC | DE-GUP-DT-E-23-093 | 2023-01-30 | 0 | CRS-GUP-DHI-DT-23-1610 | 2023-03-02 | NC
| GUP | CQ02 | P1 | MAW | 125277 |  | GUP-CQ02-P1MAW-125277 | ST_Operating_Maintenance_Manual_Control valves | FI | 2023-12-31 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-867 | 2023-10-24 | 0 | CRS-GUP-DHI-DT-24-055 | 2024-07-04 | NC | DE-GUP-DT-E-23-867 | 2023-10-24 | 0 | CRS-GUP-DHI-DT-24-055 | 2024-07-04 | NC
| GUP | DN05 | P1 | MAA | 125278 |  | GUP-DN05-P1MAA-125278 | ST_Installation, Commssioning and O&M Manual for Desuperheater System | FI | 2023-04-16 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-322 | 2023-03-16 | 0 | CRS-GUP-DHI-DT-23-1797 | 2023-04-04 | NC | DE-GUP-DT-E-23-322 | 2023-03-16 | 0 | CRS-GUP-DHI-DT-23-1797 | 2023-04-04 | NC
| GUP | DM02 | P1 | MAA | 125279 |  | GUP-DM02-P1MAA-125279 | ST_Installation manual_Generator monitoring system | FI | 2023-12-31 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-132 | 2024-05-13 | 1 | CRS-GUP-DHI-DT-23-2056 | 2023-07-15 | NC | DE-GUP-DT-E-23-631 | 2023-06-20 | 0 | CRS-GUP-DHI-DT-23-2056 | 2023-07-15 | NC | DE-GUP-DT-E-24-132 | 2024-05-13 | 1
| GUP | CQ02 | P1 | MAA | 125280 |  | GUP-CQ02-P1MAA-125280 | ST_Generator Monitoring_Operation and Maintenance Manual | FI | 2022-09-22 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-132 | 2024-05-13 | 1 | CRS-GUP-DHI-DT-22-945 | 2022-10-22 | NC | DE-GUP-DT-E-22-690 | 2022-09-22 | 0 | CRS-GUP-DHI-DT-22-945 | 2022-10-22 | NC | DE-GUP-DT-E-24-132 | 2024-05-13 | 1
| GUP | DN05 | P1 | MAA | 125281 |  | GUP-DN05-P1MAA-125281 | ST_Generator monitoring system_Commisioning manual | FI | 2022-11-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-132 | 2024-05-13 | 1 | CRS-GUP-DHI-DT-22-1024 | 2022-11-13 | NC | DE-GUP-DT-E-22-883 | 2022-10-31 | 0 | CRS-GUP-DHI-DT-22-1024 | 2022-11-13 | NC | DE-GUP-DT-E-24-132 | 2024-05-13 | 1
| GUP | DM02 | P1 | MAA | 125283 |  | GUP-DM02-P1MAA-125283 | ST_Operating_Maintenance_Manual_Valves-package of steam-water, oil valves | FI | 2023-12-31 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-631 | 2023-06-20 | 0 | CRS-GUP-DHI-DT-23-2056 | 2023-07-15 | NC | DE-GUP-DT-E-23-631 | 2023-06-20 | 0 | CRS-GUP-DHI-DT-23-2056 | 2023-07-15 | NC
| GUP | CY05 | P1 | MAA | 125284 |  | GUP-CY05-P1MAA-125284 | ST_Generator Monitoring System Training Manual | FI | 2022-11-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-883 | 2022-10-31 | 0 | CRS-GUP-DHI-DT-22-1024 | 2022-11-13 | NC | DE-GUP-DT-E-22-883 | 2022-10-31 | 0 | CRS-GUP-DHI-DT-22-1024 | 2022-11-13 | NC
| GUP | DM02 | P1 | MAA | 125285 |  | GUP-DM02-P1MAA-125285 | ST_Installation, Operation and Maintenance Manual for Flash Tank Booster Pumps | FI | 2023-07-31 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-257 | 2023-02-28 | 0 | CRS-GUP-DHI-DT-23-1710 | 2023-03-14 | NC | DE-GUP-DT-E-23-257 | 2023-02-28 | 0 | CRS-GUP-DHI-DT-23-1710 | 2023-03-14 | NC
| GUP | DM02 | P1 | MAA | 125291 |  | GUP-DM02-P1MAA-125291 | ASSEMBLY MANUAL - LP Strainer (P0LBA11AT001) | FI | 2022-11-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-814 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1008 | 2022-11-13 | NC | DE-GUP-DT-E-22-814 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1008 | 2022-11-13 | NC
| GUP | CQ02 | P1 | MAA | 125292 |  | GUP-CQ02-P1MAA-125292 | OPERATING MAINTAINANCE MANUALLP Strainer | FI | 2022-09-30 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-814 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1008 | 2022-11-13 | NC | DE-GUP-DT-E-22-814 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1008 | 2022-11-13 | NC
| GUP | CQ02 | P1 | MAK | 125294 |  | GUP-CQ02-P1MAK-125294 | ST_OnM manual for electrical panels | FI | 2022-08-24 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-523 | 2022-08-19 | 0 | CRS-GUP-DHI-DT-22-718 | 2022-09-05 | NC | DE-GUP-DT-E-22-523 | 2022-08-19 | 0 | CRS-GUP-DHI-DT-22-718 | 2022-09-05 | NC
| GUP | DN05 | P1 | MAK | 125295 |  | GUP-DN05-P1MAK-125295 | ST_Commissioning manual for Electrical panels | FI | 2022-08-24 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-551 | 2022-08-24 | 0 | CRS-GUP-DHI-DT-22-749 | 2022-09-12 | NC | DE-GUP-DT-E-22-551 | 2022-08-24 | 0 | CRS-GUP-DHI-DT-22-749 | 2022-09-12 | NC
| GUP | CY05 | P1 | MAK | 125296 |  | GUP-CY05-P1MAK-125296 | ST_Training manual for electrical part | FI | 2022-08-24 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-523 | 2022-08-19 | 0 | CRS-GUP-DHI-DT-22-718 | 2022-09-05 | NC | DE-GUP-DT-E-22-523 | 2022-08-19 | 0 | CRS-GUP-DHI-DT-22-718 | 2022-09-05 | NC
| GUP | DM02 | P1 | MAG | 125297 |  | GUP-DM02-P1MAG-125297 | ST_Assembly manual_Flash tank | FI | 2024-03-10 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-050 | 2024-02-21 | 0 | CRS-GUP-DHI-DT-24-056 | 2024-07-04 | NC | DE-GUP-DT-E-24-050 | 2024-02-21 | 0 | CRS-GUP-DHI-DT-24-056 | 2024-07-04 | NC
| GUP | CQ02 | P1 | MAA | 125300 |  | GUP-CQ02-P1MAA-125300 | ST_User Manual_Induction equipment + HYTORC | FI | 2023-04-16 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-761 | 2023-08-24 | 0 | CRS-GUP-DHI-DT-23-2129 | 2023-11-01 | NC | DE-GUP-DT-E-23-761 | 2023-08-24 | 0 | CRS-GUP-DHI-DT-23-2129 | 2023-11-01 | NC
| GUP | CQ02 | P1 | MAX | 125302 |  | GUP-CQ02-P1MAX-125302 | ST_Hydraulic block of jacking oil-Operation and Maintenance Manual | FI | 2022-05-11 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-212 | 2022-05-11 | 0 | CRS-GUP-DHI-DT-22-394 | 2022-06-07 | NC | DHI-GUP-DT-22-212 | 2022-05-11 | 0 | CRS-GUP-DHI-DT-22-394 | 2022-06-07 | NC
| GUP | DN05 | P1 | MAV | 125307 |  | GUP-DN05-P1MAV-125307 | ST_Integrated Oil System_Commissioning Manual | FI | 2023-03-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-199 | 2023-02-17 | 0 | CRS-GUP-DHI-DT-23-1689 | 2023-03-14 | NC | DE-GUP-DT-E-23-199 | 2023-02-17 | 0 | CRS-GUP-DHI-DT-23-1689 | 2023-03-14 | NC
| GUP | DM02 | P1 | MAA | 125308 |  | GUP-DM02-P1MAA-125308 | ST_Installation manual_Expansion joint on STG outlet (P0MAB01HA0011MR01) | FI | 2023-12-31 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-631 | 2023-06-20 | 0 | CRS-GUP-DHI-DT-23-2056 | 2023-07-15 | NC | DE-GUP-DT-E-23-631 | 2023-06-20 | 0 | CRS-GUP-DHI-DT-23-2056 | 2023-07-15 | NC
| GUP | CQ02 | P1 | MAA | 125309 |  | GUP-CQ02-P1MAA-125309 | ST_O&M manual for expansion joint on the outlet from the STG(P0MAB01HA001MR01) | FI | 2023-03-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-199 | 2023-02-17 | 0 | CRS-GUP-DHI-DT-23-1689 | 2023-03-14 | NC | DE-GUP-DT-E-23-199 | 2023-02-17 | 0 | CRS-GUP-DHI-DT-23-1689 | 2023-03-14 | NC
| GUP | CQ02 | P1 | MAA | 125311 |  | GUP-CQ02-P1MAA-125311 | ST_Installation manual_Expansion Joint (P0PAB21/22/31/32BR001MR01) | FI | 2023-12-31 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-631 | 2023-06-20 | 0 | CRS-GUP-DHI-DT-23-2056 | 2023-07-15 | NC | DE-GUP-DT-E-23-631 | 2023-06-20 | 0 | CRS-GUP-DHI-DT-23-2056 | 2023-07-15 | NC
| GUP | DM02 | P1 | MAM | 125312 |  | GUP-DM02-P1MAM-125312 | ST_Installation manual_Vent Steam Condenser | FI | 2023-12-31 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-631 | 2023-06-20 | 0 | CRS-GUP-DHI-DT-23-2056 | 2023-07-15 | NC | DE-GUP-DT-E-23-631 | 2023-06-20 | 0 | CRS-GUP-DHI-DT-23-2056 | 2023-07-15 | NC
| GUP | CQ02 | P1 | MAM | 125313 |  | GUP-CQ02-P1MAM-125313 | ST_Vent Steam Condenser Operating and Maintenance Manual | FI | 2022-08-23 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-883 | 2022-10-31 | 1 | CRS-GUP-DHI-DT-22-1024 | 2022-11-13 | NC | DE-GUP-DT-E-22-531 | 2022-08-23 | 0 | CRS-GUP-DHI-DT-22-737 | 2022-09-12 | NC | DE-GUP-DT-E-22-883 | 2022-10-31 | 1 | CRS-GUP-DHI-DT-22-1024 | 2022-11-13 | NC
| GUP | DN05 | P1 | MAM | 125314 |  | GUP-DN05-P1MAM-125314 | ST_Commisioning manual (VSC) | FI | 2022-07-29 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-486 | 2022-07-29 | 0 | CRS-GUP-DHI-DT-22-656 | 2022-08-20 | NC | DE-GUP-DT-E-22-486 | 2022-07-29 | 0 | CRS-GUP-DHI-DT-22-656 | 2022-08-20 | NC
| GUP | DM02 | P1 | MAV | 125317 |  | GUP-DM02-P1MAV-125317 | ST_Installation manual_Oil Cleaning Unit | FI | 2023-12-31 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-631 | 2023-06-20 | 0 | CRS-GUP-DHI-DT-23-2056 | 2023-07-15 | NC | DE-GUP-DT-E-23-631 | 2023-06-20 | 0 | CRS-GUP-DHI-DT-23-2056 | 2023-07-15 | NC
| GUP | CQ02 | P1 | MAV | 125318 |  | GUP-CQ02-P1MAV-125318 | ST_Operating_Maintainance_Manual_Oil cleaning unit | FI | 2023-03-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-093 | 2023-01-30 | 0 | CRS-GUP-DHI-DT-23-1610 | 2023-03-02 | NC | DE-GUP-DT-E-23-093 | 2023-01-30 | 0 | CRS-GUP-DHI-DT-23-1610 | 2023-03-02 | NC
| GUP | DM02 | P1 | MAA | 125320 |  | GUP-DM02-P1MAA-125320 | ST_Installation Manual for Field Instrumentation | FI | 2023-04-16 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-322 | 2023-03-16 | 0 | CRS-GUP-DHI-DT-23-1797 | 2023-04-04 | NC | DE-GUP-DT-E-23-322 | 2023-03-16 | 0 | CRS-GUP-DHI-DT-23-1797 | 2023-04-04 | NC
| GUP | CQ02 | P1 | MAA | 125321 |  | GUP-CQ02-P1MAA-125321 | ST_O&M Manual for Field Instrumentation | FI | 2023-04-16 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-322 | 2023-03-16 | 0 | CRS-GUP-DHI-DT-23-1797 | 2023-04-04 | NC | DE-GUP-DT-E-23-322 | 2023-03-16 | 0 | CRS-GUP-DHI-DT-23-1797 | 2023-04-04 | NC
| GUP | DN05 | P1 | MAJ | 125322 |  | GUP-DN05-P1MAJ-125322 | ST_Commissioning Manual for Condenser Vacuum Pumps | FI | 2023-05-31 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-511 | 2023-04-27 | 0 | CRS-GUP-DHI-DT-23-1944 | 2023-05-11 | NC | DE-GUP-DT-E-23-511 | 2023-04-27 | 0 | CRS-GUP-DHI-DT-23-1944 | 2023-05-11 | NC
| GUP | DM02 | P1 | MAA | 125325 |  | GUP-DM02-P1MAA-125325 | ST_Installation manual_TPC/OPS Panel | FI | 2023-12-31 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-631 | 2023-06-20 | 0 | CRS-GUP-DHI-DT-23-2056 | 2023-07-15 | NC | DE-GUP-DT-E-23-631 | 2023-06-20 | 0 | CRS-GUP-DHI-DT-23-2056 | 2023-07-15 | NC
| GUP | YS01 | P1 | CJJ | 125326 |  | GUP-YS01-P1CJJ-125326 | ST_CS_TCS/TPS Wiring Diagrams | FI | 2022-11-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-820 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1009 | 2022-11-13 | NC | DE-GUP-DT-E-22-820 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1009 | 2022-11-13 | NC
| GUP | DM02 | P1 | MAK | 125328 |  | GUP-DM02-P1MAK-125328 | ST_Installation, Commissioning and O&M Manual for Gearbox | FI | 2023-04-16 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-322 | 2023-03-16 | 0 | CRS-GUP-DHI-DT-23-1797 | 2023-04-04 | NC | DE-GUP-DT-E-23-322 | 2023-03-16 | 0 | CRS-GUP-DHI-DT-23-1797 | 2023-04-04 | NC
| GUP | DM02 | P1 | CJJ | 125331 |  | GUP-DM02-P1CJJ-125331 | ST_Installation manual_TCS/TPS | FI | 2023-12-31 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-631 | 2023-06-20 | 0 | CRS-GUP-DHI-DT-23-2056 | 2023-07-15 | NC | DE-GUP-DT-E-23-631 | 2023-06-20 | 0 | CRS-GUP-DHI-DT-23-2056 | 2023-07-15 | NC
| GUP | CQ02 | P1 | CJJ | 125332 |  | GUP-CQ02-P1CJJ-125332 | ST_O&M Manual for TCS/TPS | FI | 2023-06-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-432 | 2023-04-07 | 0 | CRS-GUP-DHI-DT-23-1886 | 2023-04-28 | NC | DE-GUP-DT-E-23-432 | 2023-04-07 | 0 | CRS-GUP-DHI-DT-23-1886 | 2023-04-28 | NC
| GUP | DN05 | P1 | CJJ | 125333 |  | GUP-DN05-P1CJJ-125333 | ST_Commissioning manual Turbine Control System | FI | 2023-03-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-250 | 2024-10-18 | 1 | 자체 CRS 개정 후 제출 | 2024-10-17 | N/A | DE-GUP-DT-E-23-199 | 2023-02-17 | 0 | 자체 CRS 개정 후 제출 | 2024-10-17 | N/A | DE-GUP-DT-E-24-250 | 2024-10-18 | 1
| GUP | CY05 | P1 | CJJ | 125334 |  | GUP-CY05-P1CJJ-125334 | ST_Control System Training Manual | FI | 2023-03-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-093 | 2023-01-30 | 0 | CRS-GUP-DHI-DT-23-1610 | 2023-03-02 | NC | DE-GUP-DT-E-23-093 | 2023-01-30 | 0 | CRS-GUP-DHI-DT-23-1610 | 2023-03-02 | NC
| GUP | DM02 | P1 | MAA | 125339 |  | GUP-DM02-P1MAA-125339 | ST_Manual for Installation and O&M Manual Expansion joint P0MAV56 BR001, P0MAL10 BR001 MR01/MR02/MR03 | FI | 2023-03-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-199 | 2023-02-17 | 0 | CRS-GUP-DHI-DT-23-1689 | 2023-03-14 | NC | DE-GUP-DT-E-23-199 | 2023-02-17 | 0 | CRS-GUP-DHI-DT-23-1689 | 2023-03-14 | NC
| GUP | DM02 | P1 | MAA | 125340 |  | GUP-DM02-P1MAA-125340 | ST_Pipelines supports | FI | 2023-06-01 |  | 플랜트기술팀(Mech.) | 오광일 |  | R |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-571 | 2023-05-22 | 0 | CRS-GUP-DHI-DT-23-2001 | 2023-06-16 | NC | DE-GUP-DT-E-23-199 | 2023-02-17 | 0 | CRS-GUP-DHI-DT-23-1689 | 2023-03-14 | NC | DE-GUP-DT-E-23-571 | 2023-05-22 | 0 | CRS-GUP-DHI-DT-23-2001 | 2023-06-16 | NC
| GUP | DM02 | P1 | MAA | 125341 |  | GUP-DM02-P1MAA-125341 | ST_VIBRATION MONITORING SYSTEM ASSEMBLY MANUAL | FI | 2022-11-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-814 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1008 | 2022-11-13 | NC | DE-GUP-DT-E-22-814 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1008 | 2022-11-13 | NC
| GUP | CQ02 | P1 | MAA | 125342 |  | GUP-CQ02-P1MAA-125342 | ST_VIBRATION MONITORING SYSTEM OPERATING AND MAINTENANCE MANUAL | FI | 2022-08-23 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-531 | 2022-08-23 | 0 | CRS-GUP-DHI-DT-22-737 | 2022-09-12 | NC | DE-GUP-DT-E-22-531 | 2022-08-23 | 0 | CRS-GUP-DHI-DT-22-737 | 2022-09-12 | NC
| GUP | DN05 | P1 | MAA | 125343 |  | GUP-DN05-P1MAA-125343 | ST_Commissioning manual Vibration Monitoring System | FI | 2022-07-29 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-486 | 2022-07-29 | 0 | CRS-GUP-DHI-DT-22-656 | 2022-08-20 | NC | DE-GUP-DT-E-22-486 | 2022-07-29 | 0 | CRS-GUP-DHI-DT-22-656 | 2022-08-20 | NC
| GUP | CY05 | P1 | MAA | 125344 |  | GUP-CY05-P1MAA-125344 | VIBRATION MONITORING SYSTEM TRAINING MANUAL | FI | 2022-11-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-814 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1008 | 2022-11-13 | NC | DE-GUP-DT-E-22-814 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1008 | 2022-11-13 | NC
| GUP | DM02 | P1 | MAX | 125345 |  | GUP-DM02-P1MAX-125345 | ST_Installation manual_HPH System | FI | 2023-12-31 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-631 | 2023-06-20 | 0 | CRS-GUP-DHI-DT-23-2056 | 2023-07-15 | NC | DE-GUP-DT-E-23-631 | 2023-06-20 | 0 | CRS-GUP-DHI-DT-23-2056 | 2023-07-15 | NC
| GUP | CQ02 | P1 | MAX | 125346 |  | GUP-CQ02-P1MAX-125346 | ST_High Pressure Hydraulic system Operation and Maintenance Manual | FI | 2022-11-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-814 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1008 | 2022-11-13 | NC | DE-GUP-DT-E-22-814 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1008 | 2022-11-13 | NC
| GUP | DN05 | P1 | MAX | 125347 |  | GUP-DN05-P1MAX-125347 | ST_High Pressure Hydraulic system Commisioning manual | FI | 2022-11-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-883 | 2022-10-31 | 0 | CRS-GUP-DHI-DT-22-1024 | 2022-11-13 | NC | DE-GUP-DT-E-22-883 | 2022-10-31 | 0 | CRS-GUP-DHI-DT-22-1024 | 2022-11-13 | NC
| GUP | DM02 | P1 | MAJ | 125348 |  | GUP-DM02-P1MAJ-125348 | ST_Installation manual_Condenser Vacuum Pump | FI | 2023-12-31 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-631 | 2023-06-20 | 0 | CRS-GUP-DHI-DT-23-2056 | 2023-07-15 | NC | DE-GUP-DT-E-23-631 | 2023-06-20 | 0 | CRS-GUP-DHI-DT-23-2056 | 2023-07-15 | NC
| GUP | CQ02 | P1 | MAJ | 125349 |  | GUP-CQ02-P1MAJ-125349 | ST_Operating_Maintenance_Manual-Condenser Vacuum Pump | FI | 2023-03-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-093 | 2023-01-30 | 0 | CRS-GUP-DHI-DT-23-1610 | 2023-03-02 | NC | DE-GUP-DT-E-23-093 | 2023-01-30 | 0 | CRS-GUP-DHI-DT-23-1610 | 2023-03-02 | NC
| GUP | CC05 | P1 | NAA | 125352 |  | GUP-CC05-P1NAA-125352 | ST_Valves - Non return extraction flaps (P0LBC01AA201-Y01) | FI | 2022-05-27 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-253 | 2022-05-27 | 0 | CRS-GUP-DHI-DT-22-468 | 2022-06-22 | NC | DE-GUP-DT-E-22-253 | 2022-05-27 | 0 | CRS-GUP-DHI-DT-22-468 | 2022-06-22 | NC
| GUP | CC05 | P1 | MAA | 125353 |  | GUP-CC05-P1MAA-125353 | ST_Drawings for butterfly valves for isolation and control (P0MAW31AA051, P0MAW35AA051, P0LBA11AA051, P0LBA11AA081) | FI | 2023-05-31 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-511 | 2023-04-27 | 0 | CRS-GUP-DHI-DT-23-1944 | 2023-05-11 | NC | DE-GUP-DT-E-23-511 | 2023-04-27 | 0 | CRS-GUP-DHI-DT-23-1944 | 2023-05-11 | NC
| GUP | CC05 | P1 | MAW | 125355 |  | GUP-CC05-P1MAW-125355 | ST_Drawings for control valves (P0LBW01AA081, P0MAL50AA081, P0MAW11AA081, P0MAW31AA081, P0MAW36AA081) | FI | 2022-08-23 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-432 | 2023-04-07 | 1 | CRS-GUP-DHI-DT-23-1886 | 2023-04-28 | NC | DE-GUP-DT-E-22-531 | 2022-08-23 | 0 | CRS-GUP-DHI-DT-22-737 | 2022-09-12 | NC | DE-GUP-DT-E-23-432 | 2023-04-07 | 1 | CRS-GUP-DHI-DT-23-1886 | 2023-04-28 | NC
| GUP | CC05 | P1 | MAA | 125357 |  | GUP-CC05-P1MAA-125357 | ST_Drawings Sketches-Package of Steam-Water & Oil Valves | FI | 2023-06-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-432 | 2023-04-07 | 0 | CRS-GUP-DHI-DT-23-1886 | 2023-04-28 | NC | DE-GUP-DT-E-23-432 | 2023-04-07 | 0 | CRS-GUP-DHI-DT-23-1886 | 2023-04-28 | NC
| GUP | CC05 | P1 | MAA | 125358 |  | GUP-CC05-P1MAA-125358 | ST_Flash tank booster pump | FI | 2022-09-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-792 | 2023-09-06 | 1 | CRS-GUP-DHI-DT-22-749 | 2022-09-12 | NC | DE-GUP-DT-E-22-551 | 2022-08-24 | 0 | CRS-GUP-DHI-DT-22-749 | 2022-09-12 | NC | DE-GUP-DT-E-23-792 | 2023-09-06 | 1
| GUP | CC05 | P1 | MAX | 125360 |  | GUP-CC05-P1MAX-125360 | ST_Hydraulic block of jacking oil _Drawings sketches | FI | 2022-05-11 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-212 | 2022-05-11 | 0 | CRS-GUP-DHI-DT-22-394 | 2022-06-07 | NC | DHI-GUP-DT-22-212 | 2022-05-11 | 0 | CRS-GUP-DHI-DT-22-394 | 2022-06-07 | NC
| GUP | CC05 | P1 | MAV | 125361 |  | GUP-CC05-P1MAV-125361 | ST_IOS_Layout&Anchoring (lube oil skid layout/foundation) | FI | 2022-08-23 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-25-020 | 2025-02-04 | 1 | CRS-GUP-DHI-DT-22-737 | 2022-09-12 | NC | DE-GUP-DT-E-22-531 | 2022-08-23 | 0 | CRS-GUP-DHI-DT-22-737 | 2022-09-12 | NC | DE-GUP-DT-E-25-020 | 2025-02-04 | 1
| GUP | CC05 | P1 | MAA | 125362 |  | GUP-CC05-P1MAA-125362 | ST_Assembly_Drawings_sketches - Expansion joint (P0MAB01HA001MR01) | FI | 2023-05-31 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-511 | 2023-04-27 | 0 | CRS-GUP-DHI-DT-23-1944 | 2023-05-11 | NC | DE-GUP-DT-E-23-511 | 2023-04-27 | 0 | CRS-GUP-DHI-DT-23-1944 | 2023-05-11 | NC
| GUP | CC05 | P1 | MAA | 125363 |  | GUP-CC05-P1MAA-125363 | ST_Assembly_Drawings_sketches - Expansion joint (P0PAB21/22/31/32BR001MR01) | FI | 2023-05-31 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-511 | 2023-04-27 | 0 | CRS-GUP-DHI-DT-23-1944 | 2023-05-11 | NC | DE-GUP-DT-E-23-511 | 2023-04-27 | 0 | CRS-GUP-DHI-DT-23-1944 | 2023-05-11 | NC
| GUP | CC05 | P1 | MAV | 125366 |  | GUP-CC05-P1MAV-125366 | ST_Outline drawing of oil cleaning unit | FI | 2022-08-15 |  | 플랜트기술팀(Mech.) | 오광일 |  | R |  |  | STG | CCPP | STG | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-006 | 2023-01-12 | 0 | CRS-GUP-DHI-DT-23-1520 | 2023-02-14 | NC | DE-GUP-DT-E-23-006 | 2023-01-12 | 0 | CRS-GUP-DHI-DT-23-1520 | 2023-02-14 | NC
| GUP | CC05 | P1 | MAK | 125368 |  | GUP-CC05-P1MAK-125368 | ST_Gearbox Dimensional Drawing | FI | 2022-06-08 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-25-058 | 2025-05-26 | 1 | CRS-GUP-DHI-DT-22-481 | 2022-07-03 | NC | DE-GUP-DT-E-22-278 | 2022-06-08 | 0 | CRS-GUP-DHI-DT-22-481 | 2022-07-03 | NC | DE-GUP-DT-E-25-058 | 2025-05-26 | 1
| GUP | CV03 | P1 | MAK | 125370 |  | GUP-CV03-P1MAK-125370 | GENERATOR PROTECTION & SYNCHRONIZATION SYSTEM | FA | 2022-08-16 | 2022-12-31 | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-149 | 2023-02-09 | 1 | CRS-GUP-DHI-DT-22-1008 | 2022-11-13 | AA | DHI-GUP-DT-22-155 | 2022-04-08 | A | CRS-GUP-DHI-DT-22-312 | 2022-04-29 | RC | DHI-GUP-DT-22-212 | 2022-05-11 | B | CRS-GUP-DHI-DT-22-394 | 2022-06-07 | RC | DE-GUP-DT-E-22-301 | 2022-06-15 | C | CRS-GUP-DHI-DT-22-504 | 2022-07-07 | RC | DE-GUP-DT-E-22-497 | 2022-08-12 | D | CRS-GUP-DHI-DT-22-710 | 2022-09-05 | AA | DE-GUP-DT-E-22-814 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1008 | 2022-11-13 | AA | DE-GUP-DT-E-23-149 | 2023-02-09 | 1
| GUP | CV03 | P1 | MAK | 125374 |  | GUP-CV03-P1MAK-125374 | GENERATOR EXCITATION SYSTEM | FA | 2022-06-15 | 2022-12-31 | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-149 | 2023-02-09 | 1 | 메일로 회신 받음 | 2022-11-03 | AA | DHI-GUP-DT-22-155 | 2022-04-08 | A | CRS-GUP-DHI-DT-22-312 | 2022-04-29 | RC | DHI-GUP-DT-22-212 | 2022-05-11 | B | CRS-GUP-DHI-DT-22-394 | 2022-06-07 | AC | DE-GUP-DT-E-22-301 | 2022-06-15 | 0(CP) | 메일로 회신 받음 | 2022-11-03 | AA | DE-GUP-DT-E-23-149 | 2023-02-09 | 1
| GUP | CQ02 | P1 | CJJ | 125375 |  | GUP-CQ02-P1CJJ-125375 | ST_TCS TPS NETWORK ARCHITECTURE & CONNECTION | FI | 2022-06-08 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-278 | 2022-06-08 | 0 | CRS-GUP-DHI-DT-22-481 | 2022-07-03 | NC | DE-GUP-DT-E-22-278 | 2022-06-08 | 0 | CRS-GUP-DHI-DT-22-481 | 2022-07-03 | NC
| GUP | CQ02 | P1 | MAA | 125381 |  | GUP-CQ02-P1MAA-125381 | ST_REDIGO (Bearing grounding system) Operation and Maintenance Manual | FI | 2022-08-23 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-531 | 2022-08-23 | 0 | CRS-GUP-DHI-DT-22-737 | 2022-09-12 | NC | DE-GUP-DT-E-22-531 | 2022-08-23 | 0 | CRS-GUP-DHI-DT-22-737 | 2022-09-12 | NC
| GUP | YF00 | P1 | MAA | 125384 |  | GUP-YF00-P1MAA-125384 | ST_I20_FI_CS_Loop_diagrams | FI | 2022-08-15 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-25-046 | 2025-04-18 | 2 | CRS-GUP-DHI-DT-22-1008 | 2022-11-13 | NC | DE-GUP-DT-E-22-814 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1008 | 2022-11-13 | NC | DE-GUP-DT-E-24-048 | 2024-02-19 | 1 |  |  |  | DE-GUP-DT-E-25-046 | 2025-04-18 | 2
| GUP | DD02 | P1 | CJJ | 125386 |  | GUP-DD02-P1CJJ-125386 | ST_CS-Function design specification for HMI | FI | 2022-07-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-006 | 2023-01-12 | 0 | CRS-GUP-DHI-DT-23-1520 | 2023-02-14 | NC | DE-GUP-DT-E-23-006 | 2023-01-12 | 0 | CRS-GUP-DHI-DT-23-1520 | 2023-02-14 | NC
| GUP | YL01 | P1 | CJJ | 125387 |  | GUP-YL01-P1CJJ-125387 | ST_I17_CS_I/O list | FI | 2022-06-20 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-25-046 | 2025-04-18 | 1 | CRS-GUP-DHI-DT-22-606 | 2022-08-16 | NC | DE-GUP-DT-E-22-318 | 2022-06-20 | 0 | CRS-GUP-DHI-DT-22-606 | 2022-08-16 | NC | DE-GUP-DT-E-25-046 | 2025-04-18 | 1
| GUP | CC05 | P1 | MAA | 125389 |  | GUP-CC05-P1MAA-125389 | ST_Spray cooler assembly_Drawings (P0MAW11AC001, P0MAW01AC001, P0LCE13AA081, P0LCE10AA081) | FI | 2022-08-26 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-446 | 2022-07-26 | 0 | CRS-GUP-DHI-DT-22-648 | 2022-08-20 | NC | DE-GUP-DT-E-22-446 | 2022-07-26 | 0 | CRS-GUP-DHI-DT-22-648 | 2022-08-20 | NC
| GUP | CQ02 | P1 | MAX | 125390 |  | GUP-CQ02-P1MAX-125390 | High Pressure Hydraulic system Technical description | FI | 2022-07-24 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-551 | 2022-08-24 | 0 | CRS-GUP-DHI-DT-22-749 | 2022-09-12 | NC | DE-GUP-DT-E-22-551 | 2022-08-24 | 0 | CRS-GUP-DHI-DT-22-749 | 2022-09-12 | NC
| GUP | XA00 | P1 | MAA | 125394 |  | GUP-XA00-P1MAA-125394 | Steel Structures | FI | 2022-11-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-551 | 2022-08-24 | 3 | CRS-GUP-DHI-DT-22-749 | 2022-09-12 | NC | DHI-GUP-DT-22-130 | 2022-03-24 | 0 | CRS-GUP-DHI-DT-22-291 | 2022-04-14 | NC | DHI-GUP-DT-22-213 | 2022-05-11 | 1 | CRS-GUP-DHI-DT-22-395 | 2022-06-07 | RC | DE-GUP-DT-E-22-301 | 2022-06-15 | 2 | CRS-GUP-DHI-DT-22-504 | 2022-07-07 | NC | DE-GUP-DT-E-22-551 | 2022-08-24 | 3 | CRS-GUP-DHI-DT-22-749 | 2022-09-12 | NC
| GUP | XV00 | P1 | MAA | 125398 |  | GUP-XV00-P1MAA-125398 | ST_Specification of TPC-OPS Cubicles and Panels (STG Island) | FA | 2022-04-15 | 2022-09-15 | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-690 | 2022-09-22 | 0 | CRS-GUP-DHI-DT-22-777 | 2022-09-16 | AA | DHI-GUP-DT-22-162 | 2022-04-11 | A | CRS-GUP-DHI-DT-22-326 | 2022-05-02 | RC | DE-GUP-DT-E-22-407 | 2022-07-18 | B | CRS-GUP-DHI-DT-22-629 | 2022-08-18 | RC | DE-GUP-DT-E-22-601 | 2022-09-01 | C | CRS-GUP-DHI-DT-22-777 | 2022-09-16 | AA | DE-GUP-DT-E-22-690 | 2022-09-22 | 0
| GUP | XV00 | P1 | MAA | 125399 |  | GUP-XV00-P1MAA-125399 | ST_Specification of VMS Cubicles and Panels (STG Island) | FA | 2022-04-15 | 2022-09-15 | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-690 | 2022-09-22 | 0 | CRS-GUP-DHI-DT-22-777 | 2022-09-16 | AA | DHI-GUP-DT-22-162 | 2022-04-11 | A | CRS-GUP-DHI-DT-22-326 | 2022-05-02 | RC | DE-GUP-DT-E-22-407 | 2022-07-18 | B | CRS-GUP-DHI-DT-22-629 | 2022-08-18 | RC | DE-GUP-DT-E-22-601 | 2022-09-01 | C | CRS-GUP-DHI-DT-22-777 | 2022-09-16 | AA | DE-GUP-DT-E-22-690 | 2022-09-22 | 0
| GUP | YT01 | P1 | PAH | 125400 |  | GUP-YT01-P1PAH-125400 | ST_Condenser Tube Cleaning System_Outline Drawing for Strainer Section | FI | 2022-08-19 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-523 | 2022-08-19 | 1 | CRS-GUP-DHI-DT-22-718 | 2022-09-05 | NC | DHI-GUP-DT-22-164 | 2022-04-11 | 0 | CRS-GUP-DHI-DT-22-328 | 2022-05-02 | NC | DE-GUP-DT-E-22-523 | 2022-08-19 | 1 | CRS-GUP-DHI-DT-22-718 | 2022-09-05 | NC
| GUP | YT01 | P1 | PAH | 125401 |  | GUP-YT01-P1PAH-125401 | ST_Condenser Tube Cleaning System_Outline Drawing for Ball Recirculation | FI | 2022-08-23 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-531 | 2022-08-23 | 2 | CRS-GUP-DHI-DT-22-737 | 2022-09-12 | NC | DHI-GUP-DT-22-164 | 2022-04-11 | 0 | CRS-GUP-DHI-DT-22-328 | 2022-05-02 | NC | DE-GUP-DT-E-22-486 | 2022-07-29 | 1 | CRS-GUP-DHI-DT-22-656 | 2022-08-20 | NC | DE-GUP-DT-E-22-531 | 2022-08-23 | 2 | CRS-GUP-DHI-DT-22-737 | 2022-09-12 | NC
| GUP | YT01 | P1 | PAH | 125402 |  | GUP-YT01-P1PAH-125402 | ST_Condenser Tube Cleaning System__P&I Diagram | FI | 2022-08-19 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-523 | 2022-08-19 | 1 | CRS-GUP-DHI-DT-22-718 | 2022-09-05 | NC | DHI-GUP-DT-22-164 | 2022-04-11 | 0 | CRS-GUP-DHI-DT-22-328 | 2022-05-02 | NC | DE-GUP-DT-E-22-523 | 2022-08-19 | 1 | CRS-GUP-DHI-DT-22-718 | 2022-09-05 | NC
| GUP | YK10 | P1 | MAA | 125404 |  | GUP-YK10-P1MAA-125404 | ST_Steam Turbine Assembly_HP part | FI | 2022-04-11 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-161 | 2022-04-11 | 0 | CRS-GUP-DHI-DT-22-322 | 2022-05-02 | NC | DHI-GUP-DT-22-161 | 2022-04-11 | 0 | CRS-GUP-DHI-DT-22-322 | 2022-05-02 | NC
| GUP | YK10 | P1 | MAA | 125405 |  | GUP-YK10-P1MAA-125405 | ST_Steam Turbine Assembly_IP-LP part | FI | 2022-04-11 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-161 | 2022-04-11 | 0 | CRS-GUP-DHI-DT-22-322 | 2022-05-02 | NC | DHI-GUP-DT-22-161 | 2022-04-11 | 0 | CRS-GUP-DHI-DT-22-322 | 2022-05-02 | NC
| GUP | XW03 | P1 | MAA | 125407 |  | GUP-XW03-P1MAA-125407 | ST_Valve Characteristic Curves | FI | 2022-04-11 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-161 | 2022-04-11 | 0 | CRS-GUP-DHI-DT-22-322 | 2022-05-02 | NC | DHI-GUP-DT-22-161 | 2022-04-11 | 0 | CRS-GUP-DHI-DT-22-322 | 2022-05-02 | NC
| GUP | DE00 | P1 | MAA | 125408 |  | GUP-DE00-P1MAA-125408 | ST_Cathodic Protection System for Condenser Waterbox_Technical Specification | FI | 2022-04-11 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-159 | 2022-04-11 | 0 |  |  |  | DHI-GUP-DT-22-159 | 2022-04-11 | 0
| GUP | YT01 | P1 | PAH | 125410 |  | GUP-YT01-P1PAH-125410 | ST_Condenser Tube Cleaning System_Technical data sheet | FI | 2022-04-11 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-006 | 2023-01-12 | 1 | CRS-GUP-DHI-DT-23-1605 | 2023-03-02 | NC | DHI-GUP-DT-22-164 | 2022-04-11 | A | CRS-GUP-DHI-DT-22-328 | 2022-05-02 | RC | DE-GUP-DT-E-23-006 | 2023-01-12 | 1 | CRS-GUP-DHI-DT-23-1605 | 2023-03-02 | NC
| GUP | CQ02 | P1 | MAA | 125412 |  | GUP-CQ02-P1MAA-125412 | ST_Operation and Maintenance Manual for TPC/OPS | FI | 2023-04-16 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-322 | 2023-03-16 | 0 | CRS-GUP-DHI-DT-23-1797 | 2023-04-04 | NC | DE-GUP-DT-E-23-322 | 2023-03-16 | 0 | CRS-GUP-DHI-DT-23-1797 | 2023-04-04 | NC
| GUP | YT01 | P1 | MAA | 125413 |  | GUP-YT01-P1MAA-125413 | ST_TPC(Turbine Protection Components) / OPS(Overspeed Protection Protection) INSTRUMENTATION DATASHEETS | FI | 2023-05-31 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-511 | 2023-04-27 | 0 | CRS-GUP-DHI-DT-23-1944 | 2023-05-11 | NC | DE-GUP-DT-E-23-511 | 2023-04-27 | 0 | CRS-GUP-DHI-DT-23-1944 | 2023-05-11 | NC
| GUP | YL01 | P1 | MAA | 125414 |  | GUP-YL01-P1MAA-125414 | ST_TPC(Turbine Protection Components) / OPS(Overspeed Protection Protection) I/O list | FI | 2023-05-31 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-511 | 2023-04-27 | 0 | CRS-GUP-DHI-DT-23-1944 | 2023-05-11 | NC | DE-GUP-DT-E-23-511 | 2023-04-27 | 0 | CRS-GUP-DHI-DT-23-1944 | 2023-05-11 | NC
| GUP | CQ02 | P1 | MAA | 125415 |  | GUP-CQ02-P1MAA-125415 | ST_TPC OPS Control System Hardware Specification | FI | 2022-07-20 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-407 | 2022-07-18 | 0 | CRS-GUP-DHI-DT-22-629 | 2022-08-18 | NC | DE-GUP-DT-E-22-407 | 2022-07-18 | 0 | CRS-GUP-DHI-DT-22-629 | 2022-08-18 | NC
| GUP | YS01 | P1 | MAA | 125416 |  | GUP-YS01-P1MAA-125416 | ST_TPC/OPS Wiring_diagrams | FI | 2022-05-27 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-814 | 2022-10-17 | 1 | CRS-GUP-DHI-DT-22-981 | 2022-11-07 | NC | DE-GUP-DT-E-22-253 | 2022-05-27 | 0 | CRS-GUP-DHI-DT-22-468 | 2022-06-22 | NC | DE-GUP-DT-E-22-814 | 2022-10-17 | 1 | CRS-GUP-DHI-DT-22-981 | 2022-11-07 | NC
| GUP | YT01 | P1 | MAA | 125417 |  | GUP-YT01-P1MAA-125417 | ST_VMS of STG - Instrumentation datasheets | FI | 2022-08-19 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-523 | 2022-08-19 | 0 | CRS-GUP-DHI-DT-22-718 | 2022-09-05 | NC | DE-GUP-DT-E-22-523 | 2022-08-19 | 0 | CRS-GUP-DHI-DT-22-718 | 2022-09-05 | NC
| GUP | CQ02 | P1 | MAA | 125419 |  | GUP-CQ02-P1MAA-125419 | ST_VMS of STG - I/O List | FI | 2022-11-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-883 | 2022-10-31 | 0 | CRS-GUP-DHI-DT-22-1024 | 2022-11-13 | NC | DE-GUP-DT-E-22-883 | 2022-10-31 | 0 | CRS-GUP-DHI-DT-22-1024 | 2022-11-13 | NC
| GUP | YS01 | P1 | MAA | 125420 |  | GUP-YS01-P1MAA-125420 | ST_VMS of STG - Wiring diagrams | FI | 2022-11-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-814 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1008 | 2022-11-13 | NC | DE-GUP-DT-E-22-814 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1008 | 2022-11-13 | NC
| GUP | CC05 | P1 | MAA | 125425 |  | GUP-CC05-P1MAA-125425 | ST_Continual tube cleaning system_Drawing for Ball injection pipe & Sight glass | FI | 2022-08-19 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-523 | 2022-08-19 | 0 | CRS-GUP-DHI-DT-22-718 | 2022-09-05 | NC | DE-GUP-DT-E-22-523 | 2022-08-19 | 0 | CRS-GUP-DHI-DT-22-718 | 2022-09-05 | NC
| GUP | DM02 | P1 | MAA | 125427 |  | GUP-DM02-P1MAA-125427 | ST_Installation manual_CTCS | FI | 2023-12-31 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-631 | 2023-06-20 | 0 | CRS-GUP-DHI-DT-23-2056 | 2023-07-15 | NC | DE-GUP-DT-E-23-631 | 2023-06-20 | 0 | CRS-GUP-DHI-DT-23-2056 | 2023-07-15 | NC
| GUP | CQ02 | P1 | MAA | 125428 |  | GUP-CQ02-P1MAA-125428 | ST_Condenser Tube Cleaning System O&M Manual | FI | 2023-01-03 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-006 | 2023-01-12 | 0 | CRS-GUP-DHI-DT-23-1520 | 2023-02-14 | NC | DE-GUP-DT-E-23-006 | 2023-01-12 | 0 | CRS-GUP-DHI-DT-23-1520 | 2023-02-14 | NC
| GUP | DN05 | P1 | MAA | 125429 |  | GUP-DN05-P1MAA-125429 | ST_Condenser Tube Cleaning System Commissioning Manual | FI | 2023-01-03 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-006 | 2023-01-12 | 0 | CRS-GUP-DHI-DT-23-1520 | 2023-02-14 | NC | DE-GUP-DT-E-23-006 | 2023-01-12 | 0 | CRS-GUP-DHI-DT-23-1520 | 2023-02-14 | NC
| GUP | DM02 | P1 | MAA | 125431 |  | GUP-DM02-P1MAA-125431 | ST_ASSEMBLY MANUAL - THERMAL INSULATION (PIPING) | FI | 2023-01-03 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-867 | 2023-10-24 | 1 | CRS-GUP-DHI-DT-23-1520 | 2023-02-14 | NC | DE-GUP-DT-E-23-006 | 2023-01-12 | 0 | CRS-GUP-DHI-DT-23-1520 | 2023-02-14 | NC | DE-GUP-DT-E-23-867 | 2023-10-24 | 1
| GUP | YT10 | P1 | MKA | 125432 |  | GUP-YT10-P1MKA-125432 | ST_Calculation Sheet of CT & VT Burden | FI | 2022-06-08 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-814 | 2022-10-17 | 1 | CRS-GUP-DHI-DT-22-1008 | 2022-11-13 | NC | DE-GUP-DT-E-22-278 | 2022-06-08 | 0 | CRS-GUP-DHI-DT-22-481 | 2022-07-03 | NC | DE-GUP-DT-E-22-814 | 2022-10-17 | 1 | CRS-GUP-DHI-DT-22-1008 | 2022-11-13 | NC
| GUP | YT10 | P1 | MKA | 125433 |  | GUP-YT10-P1MKA-125433 | ST_Calculation Sheet of STG Neutral Grounding Equipment | FI | 2022-06-08 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-278 | 2022-06-08 | 0 | CRS-GUP-DHI-DT-22-481 | 2022-07-03 | NC | DE-GUP-DT-E-22-278 | 2022-06-08 | 0 | CRS-GUP-DHI-DT-22-481 | 2022-07-03 | NC
| GUP | YK10 | P1 | MAA | 125435 |  | GUP-YK10-P1MAA-125435 | ST_Control Valve, On-off Valve and Safety Valve Specification and Assembly Drawing | FI | 2022-06-08 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-278 | 2022-06-08 | 0 | CRS-GUP-DHI-DT-22-481 | 2022-07-03 | NC | DE-GUP-DT-E-22-278 | 2022-06-08 | 0 | CRS-GUP-DHI-DT-22-481 | 2022-07-03 | NC
| GUP | YT01 | P1 | PAH | 125442 |  | GUP-YT01-P1PAH-125442 | ST_System Description & Control Philosophy for CTCS | FI | 2023-01-03 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-006 | 2023-01-12 | 0 | CRS-GUP-DHI-DT-23-1520 | 2023-02-14 | NC | DE-GUP-DT-E-23-006 | 2023-01-12 | 0 | CRS-GUP-DHI-DT-23-1520 | 2023-02-14 | NC
| GUP | CC05 | P1 | MKA | 125444 |  | GUP-CC05-P1MKA-125444 | ST_Outline for Three Phase Induction Motors (for non-skid base) | FI | 2022-08-16 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-496 | 2022-08-12 | 0 | CRS-GUP-DHI-DT-22-709 | 2022-09-05 | NC | DE-GUP-DT-E-22-496 | 2022-08-12 | 0 | CRS-GUP-DHI-DT-22-709 | 2022-09-05 | NC
| GUP | CC05 | P1 | MKA | 125445 |  | GUP-CC05-P1MKA-125445 | ST_Outline for DC Motor | FI | 2022-08-16 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-496 | 2022-08-12 | 0 | CRS-GUP-DHI-DT-22-709 | 2022-09-05 | NC | DE-GUP-DT-E-22-496 | 2022-08-12 | 0 | CRS-GUP-DHI-DT-22-709 | 2022-09-05 | NC
| GUP | YT01 | P1 | MKA | 125446 |  | GUP-YT01-P1MKA-125446 | ST_Motor Datasheet & Curve for STG | FI | 2022-08-22 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-006 | 2023-01-12 | 1 | CRS-GUP-DHI-DT-23-1520 | 2023-02-14 | NC | DE-GUP-DT-E-22-496 | 2022-08-12 | 0 | CRS-GUP-DHI-DT-22-709 | 2022-09-05 | NC | DE-GUP-DT-E-23-006 | 2023-01-12 | 1 | CRS-GUP-DHI-DT-23-1520 | 2023-02-14 | NC
| GUP | DE00 | P1 | MAA | 125448 |  | GUP-DE00-P1MAA-125448 | ST_Thermal Insulation Specification for STG and Auxiliaries - device + piping, turbine | FI | 2022-08-24 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-551 | 2022-08-24 | 0 | CRS-GUP-DHI-DT-22-749 | 2022-09-12 | NC | DE-GUP-DT-E-22-551 | 2022-08-24 | 0 | CRS-GUP-DHI-DT-22-749 | 2022-09-12 | NC
| GUP | DP00 | P1 | MAA | 125451 |  | GUP-DP00-P1MAA-125451 | ST_Condenser - Performance Curves | FI | 2022-09-22 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-690 | 2022-09-22 | 1 | CRS-GUP-DHI-DT-22-992 | 2022-11-13 | NC | DE-GUP-DT-E-22-523 | 2022-08-19 | 0 | CRS-GUP-DHI-DT-22-718 | 2022-09-05 | NC | DE-GUP-DT-E-22-690 | 2022-09-22 | 1 | CRS-GUP-DHI-DT-22-992 | 2022-11-13 | NC
| GUP | XJ00 | P1 | MAA | 125454 |  | GUP-XJ00-P1MAA-125454 | ST_Drawings and BOMs for Turbine | FI | 2022-08-22 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-199 | 2023-02-17 | 3 | CRS-GUP-DHI-DT-23-1689 | 2023-03-14 | NC | DE-GUP-DT-E-22-496 | 2022-08-12 | 0 | CRS-GUP-DHI-DT-22-709 | 2022-09-05 | NC | DE-GUP-DT-E-22-883 | 2022-10-31 | 1 | CRS-GUP-DHI-DT-22-1024 | 2022-11-13 | NC | DE-GUP-DT-E-23-006 | 2023-01-12 | 2 | CRS-GUP-DHI-DT-23-1520 | 2023-02-14 | NC | DE-GUP-DT-E-23-199 | 2023-02-17 | 3 | CRS-GUP-DHI-DT-23-1689 | 2023-03-14 | NC
| GUP | YL01 | P1 | MKA | 125456 |  | GUP-YL01-P1MKA-125456 | ST_I/O List for Generator and Auxiliaries | FI | 2022-08-16 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-199 | 2023-02-17 | 1 | CRS-GUP-DHI-DT-23-1689 | 2023-03-14 | NC | DE-GUP-DT-E-22-496 | 2022-08-12 | 0 | CRS-GUP-DHI-DT-22-709 | 2022-09-05 | NC | DE-GUP-DT-E-23-199 | 2023-02-17 | 1 | CRS-GUP-DHI-DT-23-1689 | 2023-03-14 | NC
| GUP | CV03 | P1 | MAV | 125457 |  | GUP-CV03-P1MAV-125457 | ST_Specification of Lube Oil Heater | FI | 2022-08-22 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-496 | 2022-08-12 | 0 | CRS-GUP-DHI-DT-22-709 | 2022-09-05 | NC | DE-GUP-DT-E-22-496 | 2022-08-12 | 0 | CRS-GUP-DHI-DT-22-709 | 2022-09-05 | NC
| GUP | UF00 | P1 | MAA | 125461 |  | GUP-UF00-P1MAA-125461 | ST_Loads Plan Level +4,8m | FI | 2022-09-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Civil | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-580 | 2022-08-30 | 0 | CRS-GUP-DHI-DT-22-789 | 2022-09-19 | NC | DE-GUP-DT-E-22-580 | 2022-08-30 | 0 | CRS-GUP-DHI-DT-22-789 | 2022-09-19 | NC
| GUP | UF00 | P1 | MAA | 125462 |  | GUP-UF00-P1MAA-125462 | ST_Loads Plan Level +0.00m -2 | FI | 2022-09-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Civil | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-580 | 2022-08-30 | 0 | CRS-GUP-DHI-DT-22-789 | 2022-09-19 | NC | DE-GUP-DT-E-22-580 | 2022-08-30 | 0 | CRS-GUP-DHI-DT-22-789 | 2022-09-19 | NC
| GUP | UF00 | P1 | MAA | 125463 |  | GUP-UF00-P1MAA-125463 | ST_Loads Plan Level +0.00m -1 | FI | 2022-09-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Civil | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-580 | 2022-08-30 | 0 | CRS-GUP-DHI-DT-22-789 | 2022-09-19 | NC | DE-GUP-DT-E-22-580 | 2022-08-30 | 0 | CRS-GUP-DHI-DT-22-789 | 2022-09-19 | NC
| GUP | UF00 | P1 | MAA | 125464 |  | GUP-UF00-P1MAA-125464 | ST_Loads Plan Level +6,33m | FI | 2022-09-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Civil | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-580 | 2022-08-30 | 0 | CRS-GUP-DHI-DT-22-789 | 2022-09-19 | NC | DE-GUP-DT-E-22-580 | 2022-08-30 | 0 | CRS-GUP-DHI-DT-22-789 | 2022-09-19 | NC
| GUP | YS00 | P1 | MAJ | 125465 |  | GUP-YS00-P1MAJ-125465 | ST_Condenser Vacuum Pump_Terminal Box | FI | 2022-09-22 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-690 | 2022-09-22 | 0 | CRS-GUP-DHI-DT-22-945 | 2022-10-22 | NC | DE-GUP-DT-E-22-690 | 2022-09-22 | 0 | CRS-GUP-DHI-DT-22-945 | 2022-10-22 | NC
| GUP | YD08 | P1 | MAA | 125467 |  | GUP-YD08-P1MAA-125467 | ST_Instrument Location Drawings +6.0m | FI | 2022-11-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-814 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1008 | 2022-11-13 | NC | DE-GUP-DT-E-22-814 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1008 | 2022-11-13 | NC
| GUP | YD08 | P1 | MAA | 125468 |  | GUP-YD08-P1MAA-125468 | ST_Instrument Location Drawings +0.0m | FI | 2022-11-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-814 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1008 | 2022-11-13 | NC | DE-GUP-DT-E-22-814 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1008 | 2022-11-13 | NC
| GUP | YS01 | P1 | MAA | 125469 |  | GUP-YS01-P1MAA-125469 | ST_GENERATOR MONITORING SYSTEM WIRING DIAGRAM | FI | 2022-11-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-814 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1008 | 2022-11-13 | NC | DE-GUP-DT-E-22-814 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1008 | 2022-11-13 | NC
| GUP | CC05 | P1 | MAA | 125470 |  | GUP-CC05-P1MAA-125470 | ST_Outline of Local Instrument Rack and Stanchion | FI | 2022-11-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-814 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1008 | 2022-11-13 | NC | DE-GUP-DT-E-22-814 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1008 | 2022-11-13 | NC
| GUP | CC05 | P1 | MAA | 125471 |  | GUP-CC05-P1MAA-125471 | ST_I18_Generator_Wiring_diagrams | FI | 2022-11-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-820 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1009 | 2022-11-13 | NC | DE-GUP-DT-E-22-820 | 2022-10-18 | 0 | CRS-GUP-DHI-DT-22-1009 | 2022-11-13 | NC
| GUP | YS01 | P1 | MAA | 125472 |  | GUP-YS01-P1MAA-125472 | ST_Condenser Tube Cleaning System Wiring Diagram | FI | 2022-11-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | I&C | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-964 | 2022-11-21 | 1 | CRS-GUP-DHI-DT-22-1202 | 2022-11-30 | NC | DE-GUP-DT-E-22-883 | 2022-10-31 | 0 | CRS-GUP-DHI-DT-22-1024 | 2022-11-13 | NC | DE-GUP-DT-E-22-964 | 2022-11-21 | 1 | CRS-GUP-DHI-DT-22-1202 | 2022-11-30 | NC
| GUP | CV03 | P1 | MAA | 125473 |  | GUP-CV03-P1MAA-125473 | ST_Generator_monitoring_system | FI | 2022-11-01 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Elec. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-132 | 2024-05-13 | 1 | CRS-GUP-DHI-DT-22-1024 | 2022-11-13 | NC | DE-GUP-DT-E-22-883 | 2022-10-31 | 0 | CRS-GUP-DHI-DT-22-1024 | 2022-11-13 | NC | DE-GUP-DT-E-24-132 | 2024-05-13 | 1
| GUP | YL00 | P1 | MAJ | 125474 |  | GUP-YL00-P1MAJ-125474 | ST_Condenser Vacuum pump - Instrument List & Catalogue | FI | 2022-11-15 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-964 | 2022-11-21 | 0 | CRS-GUP-DHI-DT-22-1202 | 2022-11-30 | NC | DE-GUP-DT-E-22-964 | 2022-11-21 | 0 | CRS-GUP-DHI-DT-22-1202 | 2022-11-30 | NC
| GUP | DD00 | P1 | MAA | 125477 |  | GUP-DD00-P1MAA-125477 | ST_Site Test Procedure Guidance for Mechanical | FI | 2023-04-16 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-062 | 2024-02-29 | 1 | CRS-GUP-DHI-DT-23-1797 | 2023-04-04 | NC | DE-GUP-DT-E-23-322 | 2023-03-16 | 0 | CRS-GUP-DHI-DT-23-1797 | 2023-04-04 | NC | DE-GUP-DT-E-24-062 | 2024-02-29 | 1
| GUP | CC05 | P1 | MAA | 125479 |  | GUP-CC05-P1MAA-125479 | ST_Assembly_Drawings_sketches - Expansion joint P0MAV56BR001, P0MAL10BR001 MR01/MR02/MR03 | FI | 2023-05-31 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-511 | 2023-04-27 | 0 | CRS-GUP-DHI-DT-23-1944 | 2023-05-11 | NC | DE-GUP-DT-E-23-511 | 2023-04-27 | 0 | CRS-GUP-DHI-DT-23-1944 | 2023-05-11 | NC
| GUP | DN05 | P1 | MAK | 125481 |  | GUP-DN05-P1MAK-125481 | ST_Commissioning manual for TPC/OPS | FI | 2024-05-31 |  | 플랜트기술팀(Mech.) | 오광일 |  |  |  |  | STG | CCPP | STG | Mech. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-063 | 2024-02-29 | 0 | CRS-GUP-DHI-DT-24-057 | 2024-07-04 | NC | DE-GUP-DT-E-24-063 | 2024-02-29 | 0 | CRS-GUP-DHI-DT-24-057 | 2024-07-04 | NC
| GUP | DE00 | P0 | ZEN | 140001 |  | GUP-DE00-P0ZEN-140001 | PIPING MATERIAL SPECIFICATION | FA | 2021-08-20 | 2022-07-01 | 배치/배관기술2팀(Piping) | 권태중 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-056 | 2024-02-26 | 1 | 자체 CRS 개정 후 제출 | 2024-02-25 | N/A | DHI-GUP-DT-21-010 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-020 | 2021-09-30 | RC | DHI-GUP-DT-21-109 | 2021-11-19 | B | CRS-GUP-DHI-DT-21-082 | 2021-12-13 | RC | DE-GUP-DT-E-22-703 | 2022-09-26 | C | CRS-GUP-DHI-DT-22-1067 | 2022-11-19 | AA | DE-GUP-DT-E-22-1080 | 2022-12-12 | 0 | 자체 CRS 개정 후 제출 | 2024-02-25 | N/A | DE-GUP-DT-E-24-056 | 2024-02-26 | 1
| GUP | DE00 | P0 | ZEN | 140002 |  | GUP-DE00-P0ZEN-140002 | PIPING INSULATION SPECIFICATION | FA | 2021-11-05 | 2022-07-08 | 배치/배관기술2팀(Piping) | 권태중 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-053 | 2024-02-23 | 1 | CRS-GUP-DHI-DT-22-1129 | 2022-11-23 | AA | DHI-GUP-DT-21-091 | 2021-11-05 | A | CRS-GUP-DHI-DT-21-076 | 2021-11-30 | RC | DHI-GUP-DT-22-196 | 2022-05-02 | B | CRS-GUP-DHI-DT-22-349 | 2022-05-18 | RC | DE-GUP-DT-E-22-233 | 2022-05-19 | C | CRS-GUP-DHI-DT-22-410 | 2022-06-10 | AA | DE-GUP-DT-E-22-759 | 2022-10-05 | 0 | CRS-GUP-DHI-DT-22-1129 | 2022-11-23 | AA | DE-GUP-DT-E-24-053 | 2024-02-23 | 1
| GUP | XV00 | P0 | ZEN | 140003 |  | GUP-XV00-P0ZEN-140003 | PIPING LINE LIST for BOP Area | FI | 2022-07-08 |  | 배치/배관기술2팀(Piping) | 권태중 | [5 empty] | CCPP | Plant | Piping | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-578 | 2022-08-30 | 0 | CRS-GUP-DHI-DT-22-841 | 2022-09-24 | NC | DE-GUP-DT-E-22-578 | 2022-08-30 | 0 | CRS-GUP-DHI-DT-22-841 | 2022-09-24 | NC
| GUP | XN00 | P0 | ZEN | 140005 |  | GUP-XN00-P0ZEN-140005 | PIPING SPECIALTY LIST | FI | 2021-10-15 |  | 배치/배관기술2팀(Piping) | 권태중 | [5 empty] | CCPP | Plant | Piping | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-21-070 | 2021-10-18 | 0 | CRS-GUP-DHI-DT-21-064 | 2021-11-17 | NC | DHI-GUP-DT-21-070 | 2021-10-18 | 0 | CRS-GUP-DHI-DT-21-064 | 2021-11-17 | NC
| GUP | XN00 | P0 | ZEN | 140004 |  | GUP-XN00-P0ZEN-140004 | MANUAL VALVE LIST | FI | 2021-10-15 |  | 배치/배관기술2팀(Piping) | 권태중 | [5 empty] | CCPP | Plant | Piping | 3 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-21-070 | 2021-10-18 | 0 | CRS-GUP-DHI-DT-21-064 | 2021-11-17 | NC | DHI-GUP-DT-21-070 | 2021-10-18 | 0 | CRS-GUP-DHI-DT-21-064 | 2021-11-17 | NC
| GUP | XH01 | P1 | UMA | 140031 |  | GUP-XH01-P1UMA-140031 | Piping Arrangement Drawing for Turbine Building Area | FA | 2022-02-09 | 2022-08-06 | 배치/배관기술2팀(Piping) | 김용헌 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-042 | 2023-01-18 | 0 | CRS-GUP-DHI-DT-22-1307 | 2022-12-22 | AA | DHI-GUP-DT-21-084 | 2021-11-02 | A | CRS-GUP-DHI-DT-21-066 | 2021-11-16 | RC | DE-GUP-DT-E-22-441 | 2022-07-25 | B | CRS-GUP-DHI-DT-22-663 | 2022-08-22 | RC | DE-GUP-DT-E-22-925 | 2022-11-09 | C | CRS-GUP-DHI-DT-22-1170 | 2022-11-26 | RC | DE-GUP-DT-E-22-1008 | 2022-11-29 | D | CRS-GUP-DHI-DT-22-1307 | 2022-12-22 | AA | DE-GUP-DT-E-23-042 | 2023-01-18 | 0
| GUP | XH01 | P1 | UHA | 140032 |  | GUP-XH01-P1UHA-140032 | Piping Arrangement Drawing for HRSG Area | FA | 2022-02-09 | 2022-08-06 | 배치/배관기술2팀(Piping) | 김용헌 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-1052 | 2022-12-08 | 0 | CRS-GUP-DHI-DT-22-1099 | 2022-11-21 | AA | DHI-GUP-DT-21-084 | 2021-11-02 | A | CRS-GUP-DHI-DT-21-066 | 2021-11-16 | RC | DE-GUP-DT-E-22-442 | 2022-07-25 | B | CRS-GUP-DHI-DT-22-664 | 2022-08-22 | RC | DE-GUP-DT-E-22-815 | 2022-10-18 | C | CRS-GUP-DHI-DT-22-1099 | 2022-11-21 | AA | DE-GUP-DT-E-22-1052 | 2022-12-08 | 0
| GUP | XH01 | P1 | ZEN | 140033 |  | GUP-XH01-P1ZEN-140033 | Piping Arrangement Drawing for Yard Area | FA | 2022-07-06 | 2022-09-07 | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-261 | 2023-03-02 | 0 | CRS-GUP-DHI-DT-23-1489 | 2023-02-11 | AA | DE-GUP-DT-E-22-383 | 2022-07-11 | A | CRS-GUP-DHI-DT-22-610 | 2022-08-16 | RC | DE-GUP-DT-E-22-796 | 2022-10-13 | B | CRS-GUP-DHI-DT-22-1091 | 2022-11-21 | RC | DE-GUP-DT-E-22-1211 | 2023-01-03 | C | CRS-GUP-DHI-DT-23-1489 | 2023-02-11 | AA | DE-GUP-DT-E-23-261 | 2023-03-02 | 0
| GUP | XH01 | P1 | ZEN | 140034 |  | GUP-XH01-P1ZEN-140034 | Piping Arrangement Drawing for Yard Area(Underground) | FA | 2022-06-29 | 2022-08-31 | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-859 | 2022-10-26 | 0 | CRS-GUP-DHI-DT-22-1235 | 2022-12-13 | AA | DE-GUP-DT-E-22-353 | 2022-07-01 | A | CRS-GUP-DHI-DT-22-521 | 2022-07-19 | AA | DE-GUP-DT-E-22-859 | 2022-10-26 | 0 | CRS-GUP-DHI-DT-22-1235 | 2022-12-13 | AA
| GUP | XH01 | P1 | UMY | 140035 |  | GUP-XH01-P1UMY-140035 | Piping Arrangement Drawing for Pipe Rack | FA | 2022-04-02 | 2022-06-24 | 배치/배관기술2팀(Piping) | 김용헌 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-819 | 2023-09-22 | 2 | 자체 CRS 개정 후 제출 | 2023-09-21 | N/A | DHI-GUP-DT-22-100 | 2022-03-08 | A | CRS-GUP-DHI-DT-22-266 | 2022-03-29 | RC | DHI-GUP-DT-22-215 | 2022-05-12 | B | CRS-GUP-DHI-DT-22-380 | 2022-05-30 | RC | DE-GUP-DT-E-22-271 | 2022-06-03 | C | CRS-GUP-DHI-DT-22-431 | 2022-06-15 | RC | DE-GUP-DT-E-22-341 | 2022-06-28 | D | CRS-GUP-DHI-DT-22-547 | 2022-07-25 | AC | DE-GUP-DT-E-22-608 | 2022-09-01 | 0 | N/A-Self revision | N/A | N/A | DE-GUP-DT-E-22-1013 | 2022-11-30 | 1 | 자체 CRS 개정 후 제출 | 2023-09-21 | N/A | DE-GUP-DT-E-23-819 | 2023-09-22 | 2
| GUP | XJ00 | P1 | LBA | 140101 |  | GUP-XJ00-P1LBA-140101 | Piping ISO (Large Bore) - HP Steam System | FI | 2022-02-23 |  | 배치/배관기술2팀(Piping) | 김용헌 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-131 | 2024-05-10 | 3 | CRS-GUP-DHI-DT-23-1920 | 2023-05-05 | NC | DHI-GUP-DT-21-160 | 2021-12-09 | 0 | CRS-GUP-DHI-DT-21-115 | 2022-01-05 | NC | DE-GUP-DT-E-22-432 | 2022-07-22 | 1 | CRS-GUP-DHI-DT-22-631 | 2022-08-18 | NC | DE-GUP-DT-E-23-497 | 2023-04-24 | 2 | CRS-GUP-DHI-DT-23-1920 | 2023-05-05 | NC | DE-GUP-DT-E-24-131 | 2024-05-10 | 3
| GUP | XJ00 | P1 | LBB | 140102 |  | GUP-XJ00-P1LBB-140102 | Piping ISO (Large Bore) - Hot reheat Steam System | FI | 2022-02-23 |  | 배치/배관기술2팀(Piping) | 김용헌 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-131 | 2024-05-10 | 3 | CRS-GUP-DHI-DT-23-1920 | 2023-05-05 | NC | DHI-GUP-DT-21-161 | 2021-12-09 | 0 | CRS-GUP-DHI-DT-21-115 | 2022-01-05 | NC | DE-GUP-DT-E-22-433 | 2022-07-22 | 1 | CRS-GUP-DHI-DT-22-632 | 2022-08-18 | NC | DE-GUP-DT-E-23-497 | 2023-04-24 | 2 | CRS-GUP-DHI-DT-23-1920 | 2023-05-05 | NC | DE-GUP-DT-E-24-131 | 2024-05-10 | 3
| GUP | XJ00 | P1 | LBC | 140103 |  | GUP-XJ00-P1LBC-140103 | Piping ISO (Large Bore) - Cold reheat Steam System | FI | 2022-02-23 |  | 배치/배관기술2팀(Piping) | 김용헌 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-131 | 2024-05-10 | 3 | CRS-GUP-DHI-DT-23-1920 | 2023-05-05 | NC | DHI-GUP-DT-21-162 | 2021-12-09 | 0 | CRS-GUP-DHI-DT-21-115 | 2022-01-05 | NC | DE-GUP-DT-E-22-434 | 2022-07-22 | 1 | CRS-GUP-DHI-DT-22-633 | 2022-08-18 | NC | DE-GUP-DT-E-23-497 | 2023-04-24 | 2 | CRS-GUP-DHI-DT-23-1920 | 2023-05-05 | NC | DE-GUP-DT-E-24-131 | 2024-05-10 | 3
| GUP | XJ00 | P1 | LBG | 140104 |  | GUP-XJ00-P1LBG-140104 | Piping ISO (Large Bore) - LP Steam System | FI | 2022-07-22 |  | 배치/배관기술2팀(Piping) | 김용헌 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-131 | 2024-05-10 | 2 | CRS-GUP-DHI-DT-23-1920 | 2023-05-05 | NC | DE-GUP-DT-E-22-422 | 2022-07-20 | 0 | CRS-GUP-DHI-DT-22-618 | 2022-08-16 | NC | DE-GUP-DT-E-23-497 | 2023-04-24 | 1 | CRS-GUP-DHI-DT-23-1920 | 2023-05-05 | NC | DE-GUP-DT-E-24-131 | 2024-05-10 | 2
| GUP | XJ00 | P1 | LAB | 140106 |  | GUP-XJ00-P1LAB-140106 | Piping ISO (Large Bore) - Feedwater System | FI | 2022-07-22 |  | 배치/배관기술2팀(Piping) | 김용헌 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-131 | 2024-05-10 | 2 | CRS-GUP-DHI-DT-23-2058 | 2023-07-15 | NC | DE-GUP-DT-E-22-421 | 2022-07-20 | 0 | CRS-GUP-DHI-DT-22-617 | 2022-08-16 | NC | DE-GUP-DT-E-23-638 | 2023-06-23 | 1 | CRS-GUP-DHI-DT-23-2058 | 2023-07-15 | NC | DE-GUP-DT-E-24-131 | 2024-05-10 | 2
| GUP | XJ00 | P1 | LCA | 140107 |  | GUP-XJ00-P1LCA-140107 | Piping ISO (Large Bore) - Condensate System | FI | 2022-10-21 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-131 | 2024-05-10 | 2 | CRS-GUP-DHI-DT-23-2058 | 2023-07-15 | NC | DE-GUP-DT-E-22-837 | 2022-10-21 | 0 | CRS-GUP-DHI-DT-22-1013 | 2022-11-13 | NC | DE-GUP-DT-E-23-638 | 2023-06-23 | 1 | CRS-GUP-DHI-DT-23-2058 | 2023-07-15 | NC | DE-GUP-DT-E-24-131 | 2024-05-10 | 2
| GUP | XJ00 | P1 | PGB | 140108 |  | GUP-XJ00-P1PGB-140108 | Piping ISO (Large Bore) - CCW System | FI | 2022-10-07 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-131 | 2024-05-10 | 2 | CRS-GUP-DHI-DT-23-2058 | 2023-07-15 | NC | DE-GUP-DT-E-22-809 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1006 | 2022-11-13 | NC | DE-GUP-DT-E-23-638 | 2023-06-23 | 1 | CRS-GUP-DHI-DT-23-2058 | 2023-07-15 | NC | DE-GUP-DT-E-24-131 | 2024-05-10 | 2
| GUP | XJ00 | P1 | LCM | 140109 |  | GUP-XJ00-P1LCM-140109 | Piping ISO (Large Bore) - Steam Drain System | FI | 2022-10-21 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-131 | 2024-05-10 | 2 | CRS-GUP-DHI-DT-23-2058 | 2023-07-15 | NC | DE-GUP-DT-E-23-133 | 2023-02-06 | 0 | CRS-GUP-DHI-DT-23-1626 | 2023-03-02 | NC | DE-GUP-DT-E-23-638 | 2023-06-23 | 1 | CRS-GUP-DHI-DT-23-2058 | 2023-07-15 | NC | DE-GUP-DT-E-24-131 | 2024-05-10 | 2
| GUP | XJ00 | P1 | PAB | 140110 |  | GUP-XJ00-P1PAB-140110 | Piping ISO (Large Bore) - Circulating Water System | FI | 2022-06-15 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-131 | 2024-05-10 | 3 | CRS-GUP-DHI-DT-23-2058 | 2023-07-15 | NC | DHI-GUP-DT-22-204 | 2022-05-04 | 0 | CRS-GUP-DHI-DT-22-378 | 2022-05-30 | RR | DE-GUP-DT-E-22-296 | 2022-06-14 | 1 | CRS-GUP-DHI-DT-22-819 | 2022-09-22 | NC | DE-GUP-DT-E-23-638 | 2023-06-23 | 2 | CRS-GUP-DHI-DT-23-2058 | 2023-07-15 | NC | DE-GUP-DT-E-24-131 | 2024-05-10 | 3
| GUP | XJ00 | P1 | EGA | 140112 |  | GUP-XJ00-P1EGA-140112 | Piping ISO (Large Bore) - Fuel Oil System | FI | 2022-10-14 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-131 | 2024-05-10 | 2 | CRS-GUP-DHI-DT-23-2058 | 2023-07-15 | NC | DE-GUP-DT-E-22-809 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1006 | 2022-11-13 | NC | DE-GUP-DT-E-23-638 | 2023-06-23 | 1 | CRS-GUP-DHI-DT-23-2058 | 2023-07-15 | NC | DE-GUP-DT-E-24-131 | 2024-05-10 | 2
| GUP | XJ00 | P1 | EKG | 140113 |  | GUP-XJ00-P1EKG-140113 | Piping ISO (Large Bore) - Fuel Gas System | FI | 2022-10-14 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-131 | 2024-05-10 | 2 | CRS-GUP-DHI-DT-23-2058 | 2023-07-15 | NC | DE-GUP-DT-E-22-809 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1006 | 2022-11-13 | NC | DE-GUP-DT-E-23-638 | 2023-06-23 | 1 | CRS-GUP-DHI-DT-23-2058 | 2023-07-15 | NC | DE-GUP-DT-E-24-131 | 2024-05-10 | 2
| GUP | XJ00 | P1 | GHC | 140114 |  | GUP-XJ00-P1GHC-140114 | Piping ISO (Large Bore) - Demi water System | FI | 2022-10-05 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-131 | 2024-05-10 | 2 | CRS-GUP-DHI-DT-23-2058 | 2023-07-15 | NC | DE-GUP-DT-E-22-809 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1006 | 2022-11-13 | NC | DE-GUP-DT-E-23-638 | 2023-06-23 | 1 | CRS-GUP-DHI-DT-23-2058 | 2023-07-15 | NC | DE-GUP-DT-E-24-131 | 2024-05-10 | 2
| GUP | XJ00 | P1 | QFB | 140115 |  | GUP-XJ00-P1QFB-140115 | Piping ISO (Large Bore) - Instrument Air System | FI | 2022-10-14 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-131 | 2024-05-10 | 2 | CRS-GUP-DHI-DT-23-2058 | 2023-07-15 | NC | DE-GUP-DT-E-22-837 | 2022-10-21 | 0 | CRS-GUP-DHI-DT-22-1013 | 2022-11-13 | NC | DE-GUP-DT-E-23-638 | 2023-06-23 | 1 | CRS-GUP-DHI-DT-23-2058 | 2023-07-15 | NC | DE-GUP-DT-E-24-131 | 2024-05-10 | 2
| GUP | XJ00 | P1 | SCB | 140116 |  | GUP-XJ00-P1SCB-140116 | Piping ISO (Large Bore) - Service Air System System | FI | 2022-10-14 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-131 | 2024-05-10 | 2 | CRS-GUP-DHI-DT-23-2058 | 2023-07-15 | NC | DE-GUP-DT-E-22-837 | 2022-10-21 | 0 | CRS-GUP-DHI-DT-22-1013 | 2022-11-13 | NC | DE-GUP-DT-E-23-638 | 2023-06-23 | 1 | CRS-GUP-DHI-DT-23-2058 | 2023-07-15 | NC | DE-GUP-DT-E-24-131 | 2024-05-10 | 2
| GUP | XJ00 | P1 | GHD | 140117 |  | GUP-XJ00-P1GHD-140117 | Piping ISO (Large Bore) - Service Water System | FI | 2022-10-21 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-131 | 2024-05-10 | 2 | CRS-GUP-DHI-DT-23-2058 | 2023-07-15 | NC | DE-GUP-DT-E-22-837 | 2022-10-21 | 0 | CRS-GUP-DHI-DT-22-1013 | 2022-11-13 | NC | DE-GUP-DT-E-23-638 | 2023-06-23 | 1 | CRS-GUP-DHI-DT-23-2058 | 2023-07-15 | NC | DE-GUP-DT-E-24-131 | 2024-05-10 | 2
| GUP | XJ00 | P1 | GKB | 140118 |  | GUP-XJ00-P1GKB-140118 | Piping ISO (Large Bore) - Potable Water System | FI | 2022-10-21 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-131 | 2024-05-10 | 2 | CRS-GUP-DHI-DT-23-2058 | 2023-07-15 | NC | DE-GUP-DT-E-22-837 | 2022-10-21 | 0 | CRS-GUP-DHI-DT-22-1013 | 2022-11-13 | NC | DE-GUP-DT-E-23-638 | 2023-06-23 | 1 | CRS-GUP-DHI-DT-23-2058 | 2023-07-15 | NC | DE-GUP-DT-E-24-131 | 2024-05-10 | 2
| GUP | XJ00 | P1 | ZEN | 140122 |  | GUP-XJ00-P1ZEN-140122 | Piping ISO (Large Bore) - GT_ST MISC System | FI | 2022-10-21 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-131 | 2024-05-10 | 2 | CRS-GUP-DHI-DT-23-2058 | 2023-07-15 | NC | DE-GUP-DT-E-23-252 | 2023-02-27 | 0 | CRS-GUP-DHI-DT-23-1708 | 2023-03-14 | NC | DE-GUP-DT-E-23-638 | 2023-06-23 | 1 | CRS-GUP-DHI-DT-23-2058 | 2023-07-15 | NC | DE-GUP-DT-E-24-131 | 2024-05-10 | 2
| GUP | XJ00 | P1 | SGA | 140123 |  | GUP-XJ00-P1SGA-140123 | Piping ISO (Large Bore) - Fire Fighting Ringmain System | FI | 2022-10-21 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-131 | 2024-05-10 | 2 | CRS-GUP-DHI-DT-23-2058 | 2023-07-15 | NC | DE-GUP-DT-E-22-850 | 2022-10-25 | 0 | CRS-GUP-DHI-DT-22-982 | 2022-11-07 | NC | DE-GUP-DT-E-23-421 | 2023-04-05 | 1 | CRS-GUP-DHI-DT-23-1882 | 2023-05-02 | NC | DE-GUP-DT-E-23-638 | 2023-06-23 | 2 | CRS-GUP-DHI-DT-23-2058 | 2023-07-15 | NC | DE-GUP-DT-E-24-131 | 2024-05-10 | 2
| GUP | XJ00 | P1 | LBA | 140201 |  | GUP-XJ00-P1LBA-140201 | Piping ISO (Small Bore) - HP Steam System | FI | 2023-03-31 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-834 | 2023-09-27 | 1 | CRS-GUP-DHI-DT-23-2012 | 2023-06-21 | NC | DE-GUP-DT-E-23-600 | 2023-06-02 | 0 | CRS-GUP-DHI-DT-23-2012 | 2023-06-21 | NC | DE-GUP-DT-E-23-834 | 2023-09-27 | 1
| GUP | XJ00 | P1 | LBB | 140202 |  | GUP-XJ00-P1LBB-140202 | Piping ISO (Small Bore) - Hot reheat Steam System | FI | 2023-03-31 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-834 | 2023-09-27 | 1 | CRS-GUP-DHI-DT-23-2012 | 2023-06-21 | NC | DE-GUP-DT-E-23-600 | 2023-06-02 | 0 | CRS-GUP-DHI-DT-23-2012 | 2023-06-21 | NC | DE-GUP-DT-E-23-834 | 2023-09-27 | 1
| GUP | XJ00 | P1 | LBC | 140203 |  | GUP-XJ00-P1LBC-140203 | Piping ISO (Small Bore) - Cold reheat Steam System | FI | 2023-03-31 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-834 | 2023-09-27 | 1 | CRS-GUP-DHI-DT-23-2012 | 2023-06-21 | NC | DE-GUP-DT-E-23-600 | 2023-06-02 | 0 | CRS-GUP-DHI-DT-23-2012 | 2023-06-21 | NC | DE-GUP-DT-E-23-834 | 2023-09-27 | 1
| GUP | XJ00 | P1 | LBG | 140204 |  | GUP-XJ00-P1LBG-140204 | Piping ISO (Small Bore) - LP Steam System | FI | 2023-03-31 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-834 | 2023-09-27 | 1 | CRS-GUP-DHI-DT-23-2012 | 2023-06-21 | NC | DE-GUP-DT-E-23-600 | 2023-06-02 | 0 | CRS-GUP-DHI-DT-23-2012 | 2023-06-21 | NC | DE-GUP-DT-E-23-834 | 2023-09-27 | 1
| GUP | XJ00 | P1 | LAB | 140206 |  | GUP-XJ00-P1LAB-140206 | Piping ISO (Small Bore) - Feedwater System | FI | 2023-04-14 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-842 | 2023-10-10 | 1 | CRS-GUP-DHI-DT-23-2012 | 2023-06-21 | NC | DE-GUP-DT-E-23-600 | 2023-06-02 | 0 | CRS-GUP-DHI-DT-23-2012 | 2023-06-21 | NC | DE-GUP-DT-E-23-842 | 2023-10-10 | 1
| GUP | XJ00 | P1 | LCA | 140207 |  | GUP-XJ00-P1LCA-140207 | Piping ISO (Small Bore) - Condensate System | FI | 2023-04-14 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-834 | 2023-09-27 | 1 | CRS-GUP-DHI-DT-23-2012 | 2023-06-21 | NC | DE-GUP-DT-E-23-600 | 2023-06-02 | 0 | CRS-GUP-DHI-DT-23-2012 | 2023-06-21 | NC | DE-GUP-DT-E-23-834 | 2023-09-27 | 1
| GUP | XJ00 | P1 | PGB | 140208 |  | GUP-XJ00-P1PGB-140208 | Piping ISO (Small Bore) - CCW System | FI | 2023-04-14 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-847 | 2023-10-12 | 1 | CRS-GUP-DHI-DT-23-2015 | 2023-06-21 | NC | DE-GUP-DT-E-23-606 | 2023-06-07 | 0 | CRS-GUP-DHI-DT-23-2015 | 2023-06-21 | NC | DE-GUP-DT-E-23-847 | 2023-10-12 | 1
| GUP | XJ00 | P1 | LCM | 140209 |  | GUP-XJ00-P1LCM-140209 | Piping ISO (Small Bore) - Steam Drain System | FI | 2023-04-21 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-834 | 2023-09-27 | 1 | CRS-GUP-DHI-DT-23-1982 | 2023-06-08 | NC | DE-GUP-DT-E-23-570 | 2023-05-22 | 0 | CRS-GUP-DHI-DT-23-1982 | 2023-06-08 | NC | DE-GUP-DT-E-23-834 | 2023-09-27 | 1
| GUP | XJ00 | P1 | PAB | 140210 |  | GUP-XJ00-P1PAB-140210 | Piping ISO (Small Bore) - Circulating Water System | FI | 2023-03-22 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-834 | 2023-09-27 | 1 | CRS-GUP-DHI-DT-23-1980 | 2023-06-08 | NC | DE-GUP-DT-E-23-564 | 2023-05-19 | 0 | CRS-GUP-DHI-DT-23-1980 | 2023-06-08 | NC | DE-GUP-DT-E-23-834 | 2023-09-27 | 1
| GUP | XJ00 | P1 | EGA | 140212 |  | GUP-XJ00-P1EGA-140212 | Piping ISO (Small Bore) - Fuel Oil System | FI | 2023-04-28 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-842 | 2023-10-10 | 1 | CRS-GUP-DHI-DT-23-2003 | 2023-06-15 | NC | DE-GUP-DT-E-23-577 | 2023-05-24 | 0 | CRS-GUP-DHI-DT-23-2003 | 2023-06-15 | NC | DE-GUP-DT-E-23-842 | 2023-10-10 | 1
| GUP | XJ00 | P1 | GHC | 140214 |  | GUP-XJ00-P1GHC-140214 | Piping ISO (Small Bore) - Demi water System | FI | 2023-04-28 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-847 | 2023-10-12 | 1 | CRS-GUP-DHI-DT-23-1963 | 2023-06-01 | NC | DE-GUP-DT-E-23-524 | 2023-05-05 | 0 | CRS-GUP-DHI-DT-23-1963 | 2023-06-01 | NC | DE-GUP-DT-E-23-847 | 2023-10-12 | 1
| GUP | XJ00 | P1 | QFB | 140215 |  | GUP-XJ00-P1QFB-140215 | Piping ISO (Small Bore) - Instrument Air System | FI | 2023-04-28 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-856 | 2023-10-19 | 1 | CRS-GUP-DHI-DT-23-1967 | 2023-06-01 | NC | DE-GUP-DT-E-23-536 | 2023-05-09 | 0 | CRS-GUP-DHI-DT-23-1967 | 2023-06-01 | NC | DE-GUP-DT-E-23-856 | 2023-10-19 | 1
| GUP | XJ00 | P1 | SCB | 140216 |  | GUP-XJ00-P1SCB-140216 | Piping ISO (Small Bore) - Service Air System System | FI | 2023-04-28 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-842 | 2023-10-10 | 1 | CRS-GUP-DHI-DT-23-1979 | 2023-06-08 | NC | DE-GUP-DT-E-23-563 | 2023-05-19 | 0 | CRS-GUP-DHI-DT-23-1979 | 2023-06-08 | NC | DE-GUP-DT-E-23-842 | 2023-10-10 | 1
| GUP | XJ00 | P1 | GHD | 140217 |  | GUP-XJ00-P1GHD-140217 | Piping ISO (Small Bore) - Service Water System | FI | 2023-05-04 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-856 | 2023-10-19 | 1 | CRS-GUP-DHI-DT-23-1963 | 2023-06-01 | NC | DE-GUP-DT-E-23-524 | 2023-05-05 | 0 | CRS-GUP-DHI-DT-23-1963 | 2023-06-01 | NC | DE-GUP-DT-E-23-856 | 2023-10-19 | 1
| GUP | XJ00 | P1 | GKB | 140218 |  | GUP-XJ00-P1GKB-140218 | Piping ISO (Small Bore) - Potable Water System | FI | 2023-05-04 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-856 | 2023-10-19 | 1 | CRS-GUP-DHI-DT-23-1963 | 2023-06-01 | NC | DE-GUP-DT-E-23-524 | 2023-05-05 | 0 | CRS-GUP-DHI-DT-23-1963 | 2023-06-01 | NC | DE-GUP-DT-E-23-856 | 2023-10-19 | 1
| GUP | XJ00 | P1 | ZEN | 140222 |  | GUP-XJ00-P1ZEN-140222 | Piping ISO (Small Bore) - GT_ST MISC System | FI | 2023-05-26 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-856 | 2023-10-19 | 1 | CRS-GUP-DHI-DT-23-2016 | 2023-06-21 | NC | DE-GUP-DT-E-23-611 | 2023-06-09 | 0 | CRS-GUP-DHI-DT-23-2016 | 2023-06-21 | NC | DE-GUP-DT-E-23-856 | 2023-10-19 | 1
| GUP | XJ00 | P1 | QJA | 140223 |  | GUP-XJ00-P1QJA-140223 | Piping ISO (Small Bore) - N2 Gas System | FI | 2023-06-02 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-856 | 2023-10-19 | 1 | CRS-GUP-DHI-DT-23-2012 | 2023-06-21 | NC | DE-GUP-DT-E-23-600 | 2023-06-02 | 0 | CRS-GUP-DHI-DT-23-2012 | 2023-06-21 | NC | DE-GUP-DT-E-23-856 | 2023-10-19 | 1
| GUP | XJ00 | P1 | QCA | 140224 |  | GUP-XJ00-P1QCA-140224 | Piping ISO (Small Bore) - Chemical Dosing System | FI | 2023-06-02 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-847 | 2023-10-12 | 1 | CRS-GUP-DHI-DT-23-2015 | 2023-06-21 | NC | DE-GUP-DT-E-23-606 | 2023-06-07 | 0 | CRS-GUP-DHI-DT-23-2015 | 2023-06-21 | NC | DE-GUP-DT-E-23-847 | 2023-10-12 | 1
| GUP | XJ00 | P1 | QUB | 140225 |  | GUP-XJ00-P1QUB-140225 | Piping ISO (Small Bore) - Sampling System | FI | 2023-06-02 |  | 배치/배관기술2팀(Piping) | 김민석 |  | P |  |  |  | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-834 | 2023-09-27 | 1 | CRS-GUP-DHI-DT-23-2012 | 2023-06-21 | NC | DE-GUP-DT-E-23-600 | 2023-06-02 | 0 | CRS-GUP-DHI-DT-23-2012 | 2023-06-21 | NC | DE-GUP-DT-E-23-834 | 2023-09-27 | 1
| GUP | DF04 | P1 | LBA | 140021 |  | GUP-DF04-P1LBA-140021 | Stress Analysis Report - Main & Cold reheat steam Piping | FA | 2022-02-23 | 2022-07-20 | 배치/배관기술2팀(Piping) | 김용헌 | [5 empty] | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-170 | 2024-06-28 | 1 | CRS-GUP-DHI-DT-24-026 | 2024-03-11 | AA | DHI-GUP-DT-21-115 | 2021-11-24 | A | CRS-GUP-DHI-DT-21-088 | 2021-12-23 | RC | DE-GUP-DT-E-22-413 | 2022-07-18 | B | CRS-GUP-DHI-DT-22-627 | 2022-08-18 | RC | DE-GUP-DT-E-22-955 | 2022-11-17 | C | CRS-GUP-DHI-DT-22-1191 | 2022-11-30 | AA(승인등급 변경-Email 접수) | DE-GUP-DT-E-23-044 | 2023-01-18 | 0(CP) | CRS-GUP-DHI-DT-24-026 | 2024-03-11 | AA | DE-GUP-DT-E-24-170 | 2024-06-28 | 1
| GUP | DF04 | P1 | LBB | 140022 |  | GUP-DF04-P1LBB-140022 | Stress Analysis Report - Hot reheat steam Piping | FA | 2022-03-09 | 2022-08-03 | 배치/배관기술2팀(Piping) | 김용헌 | [5 empty] | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-020 | 2024-01-23 | 1 | CRS-GUP-DHI-DT-23-1655 | 2023-03-07 | AA | DHI-GUP-DT-21-167 | 2021-12-10 | A | CRS-GUP-DHI-DT-21-141 | 2022-01-11 | RC | DE-GUP-DT-E-22-412 | 2022-07-18 | B | CRS-GUP-DHI-DT-22-559 | 2022-08-01 | RC | DE-GUP-DT-E-22-956 | 2022-11-17 | C | CRS-GUP-DHI-DT-22-1192 | 2022-11-30 | AC | DE-GUP-DT-E-23-046 | 2023-01-18 | 0(CP) | CRS-GUP-DHI-DT-23-1655 | 2023-03-07 | AA | DE-GUP-DT-E-24-020 | 2024-01-23 | 1
| GUP | DF04 | P1 | LBG | 140023 |  | GUP-DF04-P1LBG-140023 | Stress Analysis Report - LP Steam Piping | FA | 2022-07-27 | 2022-09-21 | 배치/배관기술2팀(Piping) | 김용헌 | [5 empty] | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-541 | 2023-05-11 | 0 | CRS-GUP-DHI-DT-23-1901 | 2023-05-05 | AA | DE-GUP-DT-E-22-846 | 2022-10-24 | A | CRS-GUP-DHI-DT-22-1176 | 2022-11-30 | RC | DE-GUP-DT-E-23-449 | 2023-04-13 | B | CRS-GUP-DHI-DT-23-1901 | 2023-05-05 | AA | DE-GUP-DT-E-23-541 | 2023-05-11 | 0
| GUP | DF04 | P1 | LAB | 140024 |  | GUP-DF04-P1LAB-140024 | Stress Analysis Report - Feedwater Piping | FA | 2022-07-27 | 2022-09-21 | 배치/배관기술2팀(Piping) | 김용헌 | [5 empty] | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-020 | 2024-01-23 | 1 | CRS-GUP-DHI-DT-23-1653 | 2023-03-07 | AA | DE-GUP-DT-E-22-827 | 2022-10-20 | A | CRS-GUP-DHI-DT-22-1173 | 2022-11-30 | AC | DE-GUP-DT-E-23-012 | 2023-01-12 | 0(CP) | CRS-GUP-DHI-DT-23-1653 | 2023-03-07 | AA | DE-GUP-DT-E-24-020 | 2024-01-23 | 1
| GUP | DF04 | P1 | LBG | 140025 |  | GUP-DF04-P1LBG-140025 | Stress Analysis Report - Steam blowing | FA | 2023-11-24 | 2024-01-26 | 배치/배관기술2팀(Piping) | 김용헌 | [5 empty] | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-218 | 2024-09-03 | 1 | 자체 CRS 개정 후 제출 | 2024-09-02 | N/A | DE-GUP-DT-E-24-001 | 2024-01-02 | A | CRS-GUP-DHI-DT-24-001 | 2024-01-03 | AA | DE-GUP-DT-E-24-103 | 2024-04-04 | 0 | 자체 CRS 개정 후 제출 | 2024-09-02 | N/A | DE-GUP-DT-E-24-218 | 2024-09-03 | 1
| GUP | XK00 | P0 | ZEN | 143000 |  | GUP-XK00-P0ZEN-143000 | TYPICAL INSTALLATION DRAWING FOR PIPE SUPPORT | FI | 2023-04-28 |  | 배치/배관기술2팀(Piping) | 김용헌 | [5 empty] | CCPP | Plant | Piping | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-647 | 2023-06-28 | 0 | CRS-GUP-DHI-DT-23-2061 | 2023-07-15 | NC | DE-GUP-DT-E-23-647 | 2023-06-28 | 0 | CRS-GUP-DHI-DT-23-2061 | 2023-07-15 | NC
| GUP | UC07 | P0 | ZEN | 140011 |  | GUP-UC07-P0ZEN-140011 | SITE PLAN | FA | 2021-03-31 | 2023-03-31 | 배치/배관기술2팀(Piping) | 이진우 | B | P |  |  |  | CCPP | Plant | Piping | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-164 | 2024-06-26 | 1 | 자체 CRS 개정 후 제출 | 2024-06-24 | N/A | DHI-GUP-DT-21-002 | 2021-04-16 | A | CRS-GUP-DHI-DT-21-001 | 2021-09-27 | RC | DHI-GUP-DT-21-073 | 2021-10-22 | B | CRS-GUP-DHI-DT-21-053 | 2021-11-07 | AC | DE-GUP-DT-E-23-174 | 2023-02-14 | C | CRS-GUP-DHI-DT-23-1730 | 2023-03-17 | AA | DE-GUP-DT-E-23-352 | 2023-03-24 | 0(CP) | 자체 CRS 개정 후 제출 | 2024-06-24 | N/A | DE-GUP-DT-E-24-164 | 2024-06-26 | 1
| GUP | UC07 | P0 | ZEN | 140012 |  | GUP-UC07-P0ZEN-140012 | PLOT PLAN-198MW CCPP- | FA | 2021-03-31 | 2023-03-31 | 배치/배관기술2팀(Piping) | 이진우 | B | P |  |  |  | CCPP | Plant | Piping | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-164 | 2024-06-26 | 1 | 자체 CRS 개정 후 제출 | 2024-06-24 | N/A | DHI-GUP-DT-21-002 | 2021-04-16 | A | CRS-GUP-DHI-DT-21-001 | 2021-09-27 | RC | DHI-GUP-DT-21-073 | 2021-10-22 | B | CRS-GUP-DHI-DT-21-053 | 2021-11-07 | AC | DE-GUP-DT-E-23-174 | 2023-02-14 | C | CRS-GUP-DHI-DT-23-1730 | 2023-03-17 | AA | DE-GUP-DT-E-23-352 | 2023-03-24 | 0(CP) | 자체 CRS 개정 후 제출 | 2024-06-24 | N/A | DE-GUP-DT-E-24-164 | 2024-06-26 | 1
| GUP | UE00 | P1 | UMJ | 140014 |  | GUP-UE00-P1UMJ-140014 | GENERAL ARRANGEMENT GTG BUILDING PLAN | FA | 2021-04-26 | 2022-09-16 | 배치/배관기술2팀(Piping) | 이진우 | B | P | G | FI |  | CCPP | Plant | Piping | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-174 | 2024-07-02 | 1 | CRS-GUP-DHI-DT-23-1738 | 2023-03-17 | AC | DHI-GUP-DT-21-021 | 2021-09-14 | A | CRS-GUP-DHI-DT-21-026 | 2021-10-04 | RC | DHI-GUP-DT-21-157 | 2021-12-09 | B | CRS-GUP-DHI-DT-21-112 | 2022-01-05 | RC | DHI-GUP-DT-22-180 | 2022-04-19 | C | CRS-GUP-DHI-DT-22-342 | 2022-05-18 | AC | DE-GUP-DT-E-23-229 | 2023-02-23 | 0(CP) | CRS-GUP-DHI-DT-23-1738 | 2023-03-17 | AC | DE-GUP-DT-E-24-174 | 2024-07-02 | 1
| GUP | UE00 | P1 | UHA | 140015 |  | GUP-UE00-P1UHA-140015 | GENERAL ARRANGEMENT HRSG BUILDING PLAN | FA | 2021-04-26 | 2022-09-16 | 배치/배관기술2팀(Piping) | 이진우 | B | P | G | FI |  | CCPP | Plant | Piping | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-174 | 2024-07-02 | 1 | CRS-GUP-DHI-DT-23-1738 | 2023-03-17 | AC | DHI-GUP-DT-21-021 | 2021-09-14 | A | CRS-GUP-DHI-DT-21-026 | 2021-10-04 | RC | DHI-GUP-DT-21-157 | 2021-12-09 | B | CRS-GUP-DHI-DT-21-112 | 2022-01-05 | RC | DHI-GUP-DT-22-180 | 2022-04-19 | C | CRS-GUP-DHI-DT-22-342 | 2022-05-18 | AC | DE-GUP-DT-E-23-229 | 2023-02-23 | 0(CP) | CRS-GUP-DHI-DT-23-1738 | 2023-03-17 | AC | DE-GUP-DT-E-24-174 | 2024-07-02 | 1
| GUP | UE00 | P1 | UMJ | 140016 |  | GUP-UE00-P1UMJ-140016 | GENERAL ARRANGEMENT GTG & HRSG BUILDING SECTION C-C, SECTION D-D | FA | 2021-04-26 | 2022-09-16 | 배치/배관기술2팀(Piping) | 이진우 | B | P |  |  |  | CCPP | Plant | Piping | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-173 | 2024-07-02 | 1 | CRS-GUP-DHI-DT-23-1937 | 2023-05-05 | AA | DHI-GUP-DT-21-021 | 2021-09-14 | A | CRS-GUP-DHI-DT-21-026 | 2021-10-04 | RC | DHI-GUP-DT-21-157 | 2021-12-09 | B | CRS-GUP-DHI-DT-21-112 | 2022-01-05 | RC | DHI-GUP-DT-22-180 | 2022-04-19 | C | CRS-GUP-DHI-DT-22-335 | 2022-05-16 | RC | DE-GUP-DT-E-23-229 | 2023-02-23 | D | CRS-GUP-DHI-DT-23-1738 | 2023-03-17 | AC | DE-GUP-DT-E-23-475 | 2023-04-17 | 0(CP) | CRS-GUP-DHI-DT-23-1937 | 2023-05-05 | AA | DE-GUP-DT-E-24-173 | 2024-07-02 | 1
| GUP | UE00 | P1 | UMA | 140017 |  | GUP-UE00-P1UMA-140017 | GENERAL ARRANGEMENT STG BUILDING PLAN | FA | 2021-04-26 | 2022-09-16 | 배치/배관기술2팀(Piping) | 이진우 | B | P | G | FI |  | CCPP | Plant | Piping | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-174 | 2024-07-02 | 1 | CRS-GUP-DHI-DT-23-1863 | 2023-04-19 | AA | DHI-GUP-DT-21-021 | 2021-09-14 | A | CRS-GUP-DHI-DT-21-026 | 2021-10-04 | RC | DHI-GUP-DT-21-197 | 2021-12-24 | B | CRS-GUP-DHI-DT-21-153 | 2022-01-12 | RC | DE-GUP-DT-E-22-317 | 2022-06-20 | C | CRS-GUP-DHI-DT-22-526 | 2022-07-19 | RC | DE-GUP-DT-E-23-045 | 2023-01-18 | D | CRS-GUP-DHI-DT-23-1659 | 2023-03-09 | AC | DE-GUP-DT-E-23-417 | 2023-04-04 | 0(CP) | CRS-GUP-DHI-DT-23-1863 | 2023-04-19 | AA | DE-GUP-DT-E-24-174 | 2024-07-02 | 1
| GUP | UE00 | P1 | UMA | 140018 |  | GUP-UE00-P1UMA-140018 | GENERAL ARRANGEMENT STG SECTION A-A, SECTION B-B | FA | 2021-04-26 | 2022-09-16 | 배치/배관기술2팀(Piping) | 이진우 | B | P |  |  |  | CCPP | Plant | Piping | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-173 | 2024-07-02 | 1 | CRS-GUP-DHI-DT-23-1863 | 2023-04-19 | AA | DHI-GUP-DT-21-021 | 2021-09-14 | A | CRS-GUP-DHI-DT-21-026 | 2021-10-04 | RC | DHI-GUP-DT-21-197 | 2021-12-24 | B | CRS-GUP-DHI-DT-21-153 | 2022-01-12 | RC | DE-GUP-DT-E-22-317 | 2022-06-20 | C | CRS-GUP-DHI-DT-22-526 | 2022-07-19 | RC | DE-GUP-DT-E-23-045 | 2023-01-18 | D | CRS-GUP-DHI-DT-23-1659 | 2023-03-09 | AC | DE-GUP-DT-E-23-417 | 2023-04-04 | 0(CP) | CRS-GUP-DHI-DT-23-1863 | 2023-04-19 | AA | DE-GUP-DT-E-24-173 | 2024-07-02 | 1
| GUP | UE00 | P1 | BAT | 140019 |  | GUP-UE00-P1BAT-140019 | GENERAL ARRANGEMENT TR AREA PLAN | FA | 2022-06-03 | 2022-09-16 | 배치/배관기술2팀(Piping) | 이진우 |  | P |  |  |  | CCPP | Plant | Piping | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-173 | 2024-07-02 | 1 | 자체 CRS 개정 후 제출 | 2024-07-01 | N/A | DE-GUP-DT-E-22-272 | 2022-06-03 | A | CRS-GUP-DHI-DT-22-472 | 2022-06-27 | RC | DE-GUP-DT-E-22-646 | 2022-09-08 | B | CRS-GUP-DHI-DT-22-875 | 2022-10-09 | RC | DE-GUP-DT-E-22-916 | 2022-11-08 | C | CRS-GUP-DHI-DT-22-1221 | 2022-12-05 | AA | DE-GUP-DT-E-23-201 | 2023-02-17 | 0(CP) | 자체 CRS 개정 후 제출 | 2024-07-01 | N/A | DE-GUP-DT-E-24-173 | 2024-07-02 | 1
| GUP | UE00 | P1 | BAT | 140020 |  | GUP-UE00-P1BAT-140020 | GENERAL ARRANGEMENT TR AREA SECTION | FA | 2022-06-03 | 2022-09-16 | 배치/배관기술2팀(Piping) | 이진우 |  | P |  |  |  | CCPP | Plant | Piping | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-173 | 2024-07-02 | 1 | 자체 CRS 개정 후 제출 | 2024-07-01 | N/A | DE-GUP-DT-E-22-272 | 2022-06-03 | A | CRS-GUP-DHI-DT-22-472 | 2022-06-27 | RC | DE-GUP-DT-E-22-646 | 2022-09-08 | B | CRS-GUP-DHI-DT-22-875 | 2022-10-09 | RC | DE-GUP-DT-E-22-916 | 2022-11-08 | C | CRS-GUP-DHI-DT-22-1221 | 2022-12-05 | AA | DE-GUP-DT-E-23-201 | 2023-02-17 | 0(CP) | 자체 CRS 개정 후 제출 | 2024-07-01 | N/A | DE-GUP-DT-E-24-173 | 2024-07-02 | 1
| GUP | UE00 | P1 | PAB | 140021 |  | GUP-UE00-P1PAB-140021 | GENERAL ARRANGEMENT COOLING TOWER AREA PLAN | FA | 2022-08-24 | 2022-11-30 | 배치/배관기술2팀(Piping) | 이진우 |  | P |  |  |  | CCPP | Plant | Piping | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-363 | 2023-03-24 | 0 | CRS-GUP-DHI-DT-23-1754 | 2023-03-22 | AA | DE-GUP-DT-E-22-548 | 2022-08-24 | A | CRS-GUP-DHI-DT-22-747 | 2022-09-12 | RC | DE-GUP-DT-E-22-896 | 2022-11-01 | B | CRS-GUP-DHI-DT-22-1180 | 2022-11-30 | RC | DE-GUP-DT-E-23-187 | 2023-02-16 | C | CRS-GUP-DHI-DT-23-1754 | 2023-03-22 | AA | DE-GUP-DT-E-23-363 | 2023-03-24 | 0
| GUP | UE00 | P1 | PAB | 140022 |  | GUP-UE00-P1PAB-140022 | GENERAL ARRANGEMENT COOLING TOWER AREA SECTION | FA | 2022-08-24 | 2022-11-30 | 배치/배관기술2팀(Piping) | 이진우 |  | P |  |  |  | CCPP | Plant | Piping | 1 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-363 | 2023-03-24 | 0 | CRS-GUP-DHI-DT-23-1754 | 2023-03-22 | AA | DE-GUP-DT-E-22-548 | 2022-08-24 | A | CRS-GUP-DHI-DT-22-747 | 2022-09-12 | RC | DE-GUP-DT-E-22-896 | 2022-11-01 | B | CRS-GUP-DHI-DT-22-1180 | 2022-11-30 | RC | DE-GUP-DT-E-23-187 | 2023-02-16 | C | CRS-GUP-DHI-DT-23-1754 | 2023-03-22 | AA | DE-GUP-DT-E-23-363 | 2023-03-24 | 0
| GUP | XK00 | P0 | ZEN | 140901 |  | GUP-XK00-P0ZEN-140901 | SUPPORT DETAIL DRAWING FOR BOP CRITICAL SYSTEM | FI | 2023-04-28 |  | 파워서비스배관기술팀 | 이국진 | [5 empty] | CCPP | Plant | Piping | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-183 | 2024-07-17 | 1 | CRS-GUP-DHI-DT-23-2124 | 2023-10-26 | NC | DE-GUP-DT-E-23-826 | 2023-09-26 | 0 | CRS-GUP-DHI-DT-23-2124 | 2023-10-26 | NC | DE-GUP-DT-E-24-183 | 2024-07-17 | 1
| GUP | XK00 | P0 | ZEN | 140902 |  | GUP-XK00-P0ZEN-140902 | SUPPORT DETAIL DRAWING FOR BOP GENERAL SYSTEM | FI | 2023-04-28 |  | 파워서비스배관기술팀 | 이국진 | [5 empty] | CCPP | Plant | Piping | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-183 | 2024-07-17 | 1 | CRS-GUP-DHI-DT-23-2125 | 2023-10-26 | NC | DE-GUP-DT-E-23-827 | 2023-09-26 | 0 | CRS-GUP-DHI-DT-23-2125 | 2023-10-26 | NC | DE-GUP-DT-E-24-183 | 2024-07-17 | 1
| GUP | YD00 | P1 | SHA | 136103 |  | GUP-YD00-P1SHA-136103 | STOP GATE FOR COOLING WATER PUMP_GENERAL ARRANGEMENT DRAWING | FA | 2022-08-29 | 2022-11-29 | 수처리설비기술팀(Water) | 곽병철 |  | R |  |  | STOP GATE | CCPP | Stop gate | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-530 | 2023-05-08 | 0 | CRS-GUP-DHI-DT-23-1904 | 2023-05-05 | AA | DE-GUP-DT-E-22-636 | 2022-09-07 | A | CRS-GUP-DHI-DT-22-854 | 2022-09-24 | RC | DE-GUP-DT-E-22-870 | 2022-10-27 | B | CRS-GUP-DHI-DT-22-1168 | 2022-11-26 | RC | DE-GUP-DT-E-22-1248 | 2023-01-11 | C | CRS-GUP-DHI-DT-23-1580 | 2023-02-25 | RC | DE-GUP-DT-E-23-453 | 2023-04-13 | D | CRS-GUP-DHI-DT-23-1904 | 2023-05-05 | AA | DE-GUP-DT-E-23-530 | 2023-05-08 | 0
| GUP | XS00 | P1 | SHA | 136104 |  | GUP-XS00-P1SHA-136104 | STOP GATE FOR COOLING WATER PUMP_SYSTEM DESCRIPTION | FA | 2022-07-29 | 2022-10-29 | 수처리설비기술팀(Water) | 곽병철 |  | R |  |  | STOP GATE | CCPP | Stop gate | Mech. | 1 | 2025-06-30 |  |  | DE-GUP-DT-E-23-358 | 2023-03-24 | 0 | CRS-GUP-DHI-DT-23-1737 | 2023-03-17 | AA | DE-GUP-DT-E-22-636 | 2022-09-07 | A | CRS-GUP-DHI-DT-22-854 | 2022-09-24 | RC | DE-GUP-DT-E-22-836 | 2022-10-21 | B | CRS-GUP-DHI-DT-22-1166 | 2022-11-26 | RC | DE-GUP-DT-E-22-1077 | 2022-12-12 | C | CRS-GUP-DHI-DT-22-1333 | 2022-12-28 | RC | DE-GUP-DT-E-22-1232 | 2023-01-06 | D | CRS-GUP-DHI-DT-23-1471 | 2023-02-09 | RC | DE-GUP-DT-E-23-226 | 2023-02-22 | E | CRS-GUP-DHI-DT-23-1737 | 2023-03-17 | AA | DE-GUP-DT-E-23-358 | 2023-03-24 | 0
| GUP | YK10 | P1 | SHA | 136201 |  | GUP-YK10-P1SHA-136201 | STOP GATE FOR COOLING WATER PUMP_EQUIPMENT DRAWING | FI | 2022-08-29 |  | 수처리설비기술팀(Water) | 곽병철 |  | R |  |  | STOP GATE | CCPP | Stop gate | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-047 | 2023-01-19 | 1 | CRS-GUP-DHI-DT-23-1606 | 2023-03-02 | NC | DE-GUP-DT-E-22-636 | 2022-09-07 | 0 | CRS-GUP-DHI-DT-22-854 | 2022-09-24 | NC | DE-GUP-DT-E-23-047 | 2023-01-19 | 1 | CRS-GUP-DHI-DT-23-1606 | 2023-03-02 | NC
| GUP | YT01 | P1 | SHA | 136204 |  | GUP-YT01-P1SHA-136204 | STOP GATE FOR COOLING WATER PUMP_TECHNICAL DATASHEET | FI | 2022-08-29 |  | 수처리설비기술팀(Water) | 곽병철 |  |  |  |  | STOP GATE | CCPP | Stop gate | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-836 | 2022-10-21 | 1 | CRS-GUP-DHI-DT-22-1012 | 2022-11-13 | NC | DE-GUP-DT-E-22-636 | 2022-09-07 | 0 | CRS-GUP-DHI-DT-22-854 | 2022-09-24 | NC | DE-GUP-DT-E-22-836 | 2022-10-21 | 1 | CRS-GUP-DHI-DT-22-1012 | 2022-11-13 | NC
| GUP | CQ02 | P1 | SHA | 136106 |  | GUP-CQ02-P1SHA-136106 | STOP GATE FOR COOLING WATER PUMP_O&M MANUAL | FI | 2023-05-25 |  | 수처리설비기술팀(Water) | 곽병철 |  |  |  |  | STOP GATE | CCPP | Stop gate | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-601 | 2023-06-02 | 0 | CRS-GUP-DHI-DT-23-2013 | 2023-06-21 | NC | DE-GUP-DT-E-23-601 | 2023-06-02 | 0 | CRS-GUP-DHI-DT-23-2013 | 2023-06-21 | NC
| GUP | US01 | P1 | SHA | 136152 |  | GUP-US01-P1SHA-136152 | STOP GATE FOR COOLING WATER PUMP_EMBEDDED MATERIAL DRAWING | FI | 2022-08-29 |  | 수처리설비기술팀(Water) | 곽병철 |  | R |  |  | STOP GATE | CCPP | Stop gate | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-888 | 2022-10-31 | 1 | CRS-GUP-DHI-DT-22-1026 | 2022-11-13 | NC | DE-GUP-DT-E-22-636 | 2022-09-07 | 0 | CRS-GUP-DHI-DT-22-854 | 2022-09-24 | NC | DE-GUP-DT-E-22-888 | 2022-10-31 | 1 | CRS-GUP-DHI-DT-22-1026 | 2022-11-13 | NC
| GUP | XA00 | P1 | STG | 136411 |  | GUP-XA00-P1STG-136411 | LABORATORY EQUIPMENT_EQUIPMENT ARRANGEMENT DRAWING | FA | 2022-11-10 | 2023-02-13 | 수처리설비기술팀(Water) | 이용재 |  | R |  |  | LAB | CCPP | Laboratory Equipment | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-386 | 2023-03-29 | 0 | CRS-GUP-DHI-DT-23-1743 | 2023-03-17 | AA | DE-GUP-DT-E-23-254 | 2023-02-27 | A | CRS-GUP-DHI-DT-23-1743 | 2023-03-17 | AA | DE-GUP-DT-E-23-386 | 2023-03-29 | 0
| GUP | YT01 | P1 | STG | 136504 |  | GUP-YT01-P1STG-136504 | LABORATORY EQUIPMENT_EQUIPMENT LIST & SPECIFICATION | FA | 2022-11-10 | 2023-02-13 | 수처리설비기술팀(Water) | 이용재 |  | R |  |  | LAB | CCPP | Laboratory Equipment | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-386 | 2023-03-29 | 0 | CRS-GUP-DHI-DT-23-1743 | 2023-03-17 | AA | DE-GUP-DT-E-23-254 | 2023-02-27 | A | CRS-GUP-DHI-DT-23-1743 | 2023-03-17 | AA | DE-GUP-DT-E-23-386 | 2023-03-29 | 0
| GUP | XA00 | P1 | STG | 136412 |  | GUP-XA00-P1STG-136412 | LABORATORY EQUIPMENT_POWER LINE ARRANGEMENT DRAWING | FI | 2022-12-10 |  | 수처리설비기술팀(Water) | 이용재 |  | R |  |  | LAB | CCPP | Laboratory Equipment | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-254 | 2023-02-27 | 0 | CRS-GUP-DHI-DT-23-1743 | 2023-03-17 | NC | DE-GUP-DT-E-23-254 | 2023-02-27 | 0 | CRS-GUP-DHI-DT-23-1743 | 2023-03-17 | NC
| GUP | XA00 | P1 | STG | 136413 |  | GUP-XA00-P1STG-136413 | LABORATORY EQUIPMENT_UTILITY LINE ARRANGEMENT DRAWING | FI | 2022-12-10 |  | 수처리설비기술팀(Water) | 이용재 |  | R |  |  | LAB | CCPP | Laboratory Equipment | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-254 | 2023-02-27 | 0 | CRS-GUP-DHI-DT-23-1743 | 2023-03-17 | NC | DE-GUP-DT-E-23-254 | 2023-02-27 | 0 | CRS-GUP-DHI-DT-23-1743 | 2023-03-17 | NC
| GUP | CQ02 | P1 | STG | 136406 |  | GUP-CQ02-P1STG-136406 | LABORATORY EQUIPMENT_O&M MANUAL | FI | 2023-07-10 |  | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | LAB | CCPP | Laboratory Equipment | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-744 | 2023-08-17 | 0 | CRS-GUP-DHI-DT-23-2102 | 2023-08-30 | NC | DE-GUP-DT-E-23-744 | 2023-08-17 | 0 | CRS-GUP-DHI-DT-23-2102 | 2023-08-30 | NC
| GUP | XG02 | P1 | QC | 135101 |  | GUP-XG02-P1QC-135101 | CHEMICAL DOSING SYSTEM_P&I DIAGRAM | FA | 2022-08-17 | 2022-11-17 | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | CDS | CCPP | Chemical Dosing | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-349 | 2023-03-23 | 0 | CRS-GUP-DHI-DT-24-028 | 2024-03-11 | AA | DE-GUP-DT-E-22-745 | 2022-10-04 | A | CRS-GUP-DHI-DT-22-1172 | 2022-11-30 | RC | DE-GUP-DT-E-22-1202 | 2022-12-28 | B | CRS-GUP-DHI-DT-23-1488 | 2023-02-11 | AA | DE-GUP-DT-E-23-349 | 2023-03-23 | 0 | CRS-GUP-DHI-DT-24-028 | 2024-03-11 | AA
| GUP | XA00 | P1 | QC | 135103 |  | GUP-XA00-P1QC-135103 | CHEMICAL DOSING SYSTEM_GENERAL ARRANGEMENT DRAWING | FA | 2022-08-17 | 2022-11-17 | 수처리설비기술팀(Water) | 이용재 |  | R |  |  | CDS | CCPP | Chemical Dosing | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-349 | 2023-03-23 | 0 | CRS-GUP-DHI-DT-24-028 | 2024-03-11 | AA | DE-GUP-DT-E-22-920 | 2022-11-08 | A | CRS-GUP-DHI-DT-22-1182 | 2022-11-30 | RC | DE-GUP-DT-E-22-1203 | 2022-12-28 | B | CRS-GUP-DHI-DT-23-1487 | 2023-02-11 | AA | DE-GUP-DT-E-23-349 | 2023-03-23 | 0 | CRS-GUP-DHI-DT-24-028 | 2024-03-11 | AA
| GUP | XS00 | P1 | QC | 135104 |  | GUP-XS00-P1QC-135104 | CHEMICAL DOSING SYSTEM_SYSTEM DESCRIPTION | FA | 2022-08-17 | 2022-11-17 | 수처리설비기술팀(Water) | 이용재 |  | R |  |  | CDS | CCPP | Chemical Dosing | Mech. | 1 | 2025-06-30 |  |  | DE-GUP-DT-E-23-349 | 2023-03-23 | 0 | CRS-GUP-DHI-DT-24-028 | 2024-03-11 | AA | DE-GUP-DT-E-22-745 | 2022-10-04 | A | CRS-GUP-DHI-DT-22-1172 | 2022-11-30 | RC | DE-GUP-DT-E-22-1202 | 2022-12-28 | B | CRS-GUP-DHI-DT-23-1488 | 2023-02-11 | AC | DE-GUP-DT-E-23-349 | 2023-03-23 | 0 | CRS-GUP-DHI-DT-24-028 | 2024-03-11 | AA
| GUP | CC07 | P1 | QC | 135105 |  | GUP-CC07-P1QC-135105 | CHEMICAL DOSING SYSTEM_CALCULATION SHEET | FA | 2022-08-17 | 2022-11-17 | 수처리설비기술팀(Water) | 이용재 |  | R |  |  | CDS | CCPP | Chemical Dosing | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-349 | 2023-03-23 | 0 | CRS-GUP-DHI-DT-24-028 | 2024-03-11 | AA | DE-GUP-DT-E-22-745 | 2022-10-04 | A | CRS-GUP-DHI-DT-22-1172 | 2022-11-30 | RC | DE-GUP-DT-E-22-1202 | 2022-12-28 | B | CRS-GUP-DHI-DT-23-1488 | 2023-02-11 | AA | DE-GUP-DT-E-23-349 | 2023-03-23 | 0 | CRS-GUP-DHI-DT-24-028 | 2024-03-11 | AA
| GUP | YD00 | P1 | QC | 135301 |  | GUP-YD00-P1QC-135301 | CHEMICAL DOSING SYSTEM_CONTROL PANEL ARRANGEMENT DRAWING | FI | 2022-10-17 |  | 수처리설비기술팀(Water) | 이용재 |  | R |  |  | CDS | CCPP | Chemical Dosing | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-109 | 2023-02-03 | 1 | CRS-GUP-DHI-DT-23-1615 | 2023-03-02 | NC | DE-GUP-DT-E-22-1127 | 2022-12-19 | 0 | CRS-GUP-DHI-DT-22-1410 | 2023-01-07 | NC | DE-GUP-DT-E-23-109 | 2023-02-03 | 1 | CRS-GUP-DHI-DT-23-1615 | 2023-03-02 | NC
| GUP | YF02 | P1 | QC | 135303 |  | GUP-YF02-P1QC-135303 | CHEMICAL DOSING SYSTEM_CONTROL CONFIGURATION DIAGRAM | FA | 2022-09-17 | 2022-12-17 | 수처리설비기술팀(Water) | 이용재 |  | R |  |  | CDS | CCPP | Chemical Dosing | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-024 | 2023-01-13 | 0 | CRS-GUP-DHI-DT-22-1367 | 2022-12-30 | AA | DE-GUP-DT-E-22-1090 | 2022-12-16 | A | CRS-GUP-DHI-DT-22-1367 | 2022-12-30 | AA | DE-GUP-DT-E-23-024 | 2023-01-13 | 0
| GUP | YL00 | P1 | QC | 135304 |  | GUP-YL00-P1QC-135304 | CHEMICAL DOSING SYSTEM_INSTRUMENT LIST | FI | 2022-09-17 |  | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | CDS | CCPP | Chemical Dosing | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-971 | 2022-11-22 | 0 | CRS-GUP-DHI-DT-22-1244 | 2022-12-13 | NC | DE-GUP-DT-E-22-971 | 2022-11-22 | 0 | CRS-GUP-DHI-DT-22-1244 | 2022-12-13 | NC
| GUP | XN00 | P1 | QC | 135207 |  | GUP-XN00-P1QC-135207 | CHEMICAL DOSING SYSTEM_VALVE LIST | FI | 2022-09-17 |  | 수처리설비기술팀(Water) | 이용재 |  | R |  |  | CDS | CCPP | Chemical Dosing | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-109 | 2023-02-03 | 0 | CRS-GUP-DHI-DT-23-1679 | 2023-03-13 | NC | DE-GUP-DT-E-23-109 | 2023-02-03 | 0 | CRS-GUP-DHI-DT-23-1679 | 2023-03-13 | NC
| GUP | XB02 | P1 | QC | 135151 |  | GUP-XB02-P1QC-135151 | CHEMICAL DOSING SYSTEM_FOUNDATION AND LOADING DATA | FI | 2022-09-17 |  | 수처리설비기술팀(Water) | 이용재 |  | R |  |  | CDS | CCPP | Chemical Dosing | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1203 | 2022-12-28 | 0 | CRS-GUP-DHI-DT-23-1487 | 2023-02-11 | NC | DE-GUP-DT-E-22-1203 | 2022-12-28 | 0 | CRS-GUP-DHI-DT-23-1487 | 2023-02-11 | NC
| GUP | YK10 | P1 | QC | 135201 |  | GUP-YK10-P1QC-135201 | CHEMICAL DOSING SYSTEM_EQUIPMENT ASSEMBLY DRAWING | FI | 2022-10-17 |  | 수처리설비기술팀(Water) | 이용재 |  | R |  |  | CDS | CCPP | Chemical Dosing | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1203 | 2022-12-28 | 0 | CRS-GUP-DHI-DT-23-1487 | 2023-02-11 | NC | DE-GUP-DT-E-22-1203 | 2022-12-28 | 0 | CRS-GUP-DHI-DT-23-1487 | 2023-02-11 | NC
| GUP | XH01 | P1 | QC | 135209 |  | GUP-XH01-P1QC-135209 | CHEMICAL DOSING SYSTEM_PIPING ARRANGEMENT DRAWING | FI | 2022-10-17 |  | 수처리설비기술팀(Water) | 이용재 |  | R |  |  | CDS | CCPP | Chemical Dosing | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1203 | 2022-12-28 | 0 | CRS-GUP-DHI-DT-23-1487 | 2023-02-11 | NC | DE-GUP-DT-E-22-1203 | 2022-12-28 | 0 | CRS-GUP-DHI-DT-23-1487 | 2023-02-11 | NC
| GUP | YT01 | P1 | QC | 135204 |  | GUP-YT01-P1QC-135204 | CHEMICAL DOSING SYSTEM_TECHNICAL DATASHEET | FA | 2022-10-17 | 2023-01-17 | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | CDS | CCPP | Chemical Dosing | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-605 | 2023-06-07 | 0 | CRS-GUP-DHI-DT-23-1972 | 2023-06-01 | AA | DE-GUP-DT-E-22-971 | 2022-11-22 | A | CRS-GUP-DHI-DT-22-1244 | 2022-12-13 | RC | DE-GUP-DT-E-23-153 | 2023-02-10 | B | CRS-GUP-DHI-DT-23-1683 | 2023-03-13 | RC | DE-GUP-DT-E-23-427 | 2023-04-06 | C | CRS-GUP-DHI-DT-23-1876 | 2023-04-27 | RC | DE-GUP-DT-E-23-551 | 2023-05-15 | D | CRS-GUP-DHI-DT-23-1972 | 2023-06-01 | AA | DE-GUP-DT-E-23-605 | 2023-06-07 | 0
| GUP | YV02 | P1 | QC | 135309 |  | GUP-YV02-P1QC-135309 | CHEMICAL DOSING SYSTEM_INTERCONNECTION WIRING DIAGRAM | FI | 2022-10-30 |  | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | CDS | CCPP | Chemical Dosing | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-109 | 2023-02-03 | 1 | CRS-GUP-DHI-DT-23-1590 | 2023-02-28 | NC | DE-GUP-DT-E-22-1127 | 2022-12-19 | 0 | CRS-GUP-DHI-DT-22-1410 | 2023-01-07 | NC | DE-GUP-DT-E-23-109 | 2023-02-03 | 1 | CRS-GUP-DHI-DT-23-1590 | 2023-02-28 | NC
| GUP | YS01 | P1 | QC | 135311 |  | GUP-YS01-P1QC-135311 | CHEMICAL DOSING SYSTEM_SCHEMATIC DIAGRAM | FA | 2022-10-17 | 2023-01-17 | 수처리설비기술팀(Water) | 이용재 |  | R |  |  | CDS | CCPP | Chemical Dosing | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-109 | 2023-02-03 | 0 | CRS-GUP-DHI-DT-23-1590 | 2023-02-28 | AA | DE-GUP-DT-E-22-1127 | 2022-12-19 | A | CRS-GUP-DHI-DT-22-1410 | 2023-01-07 | AA | DE-GUP-DT-E-23-109 | 2023-02-03 | 0 | CRS-GUP-DHI-DT-23-1590 | 2023-02-28 | AA
| GUP | CQ02 | P1 | QC | 135106 |  | GUP-CQ02-P1QC-135106 | CHEMICAL DOSING SYSTEM_O&M MANUAL | FI | 2024-02-29 |  | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | CDS | CCPP | Chemical Dosing | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-129 | 2024-05-08 | 0 | CRS-GUP-DHI-DT-24-064 | 2024-07-17 | NC | DE-GUP-DT-E-24-129 | 2024-05-08 | 0 | CRS-GUP-DHI-DT-24-064 | 2024-07-17 | NC
| GUP | YL16 | P1 | QC | 135313 |  | GUP-YL16-P1QC-135313 | CHEMICAL DOSING SYSTEM_CABLE SCHEDULE | FI | 2022-10-17 |  | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | CDS | CCPP | Chemical Dosing | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-109 | 2023-02-03 | 1 | CRS-GUP-DHI-DT-23-1590 | 2023-02-28 | NC | DE-GUP-DT-E-22-1127 | 2022-12-19 | 0 | CRS-GUP-DHI-DT-22-1410 | 2023-01-07 | NC | DE-GUP-DT-E-23-109 | 2023-02-03 | 1 | CRS-GUP-DHI-DT-23-1590 | 2023-02-28 | NC
| GUP | XG02 | P1 | QU | 135601 |  | GUP-XG02-P1QU-135601 | SAMPLING SYSTEM_P&I DIAGRAM | FA | 2022-07-29 | 2022-11-02 | 수처리설비기술팀(Water) | 김희정 |  |  |  |  | SWAS | CCPP | Sampling | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-297 | 2024-12-23 | 2 | 자체 CRS 개정 후 제출 | 2024-12-22 | N/A | DE-GUP-DT-E-22-439 | 2022-07-25 | 0 | CRS-GUP-DHI-DT-22-634 | 2022-08-18 | NC | DE-GUP-DT-E-22-602 | 2022-09-01 | A | CRS-GUP-DHI-DT-22-799 | 2022-09-19 | RC | DE-GUP-DT-E-22-853 | 2022-10-25 | B | CRS-GUP-DHI-DT-22-1017 | 2022-11-13 | AA | DE-GUP-DT-E-22-984 | 2022-11-24 | 0 | CRS-GUP-DHI-DT-22-1248 | 2022-12-13 | AA | DE-GUP-DT-E-24-044 | 2024-02-16 | 1 | 자체 CRS 개정 후 제출 | 2024-12-22 | N/A | DE-GUP-DT-E-24-297 | 2024-12-23 | 2
| GUP | XA00 | P1 | QU | 135603 |  | GUP-XA00-P1QU-135603 | SAMPLING SYSTEM_GENERAL ARRANGEMENT DRAWING | FA | 2022-07-29 | 2022-11-02 | 수처리설비기술팀(Water) | 김희정 |  | R |  |  | SWAS | CCPP | Sampling | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-044 | 2024-02-16 | 1 | CRS-GUP-DHI-DT-22-1248 | 2022-12-13 | AA | DE-GUP-DT-E-22-439 | 2022-07-25 | 0 | CRS-GUP-DHI-DT-22-634 | 2022-08-18 | NC | DE-GUP-DT-E-22-602 | 2022-09-01 | A | CRS-GUP-DHI-DT-22-799 | 2022-09-19 | RC | DE-GUP-DT-E-22-853 | 2022-10-25 | B | CRS-GUP-DHI-DT-22-1017 | 2022-11-13 | AA | DE-GUP-DT-E-22-984 | 2022-11-24 | 0 | CRS-GUP-DHI-DT-22-1248 | 2022-12-13 | AA | DE-GUP-DT-E-24-044 | 2024-02-16 | 1
| GUP | XS00 | P1 | QU | 135604 |  | GUP-XS00-P1QU-135604 | SAMPLING SYSTEM_SYSTEM DESCRIPTION | FA | 2022-07-29 | 2022-11-02 | 수처리설비기술팀(Water) | 김희정 |  | R |  |  | SWAS | CCPP | Sampling | Mech. | 1 | 2025-06-30 |  |  | DE-GUP-DT-E-24-297 | 2024-12-23 | 1 | CRS-GUP-DHI-DT-22-1248 | 2022-12-13 | AA | DE-GUP-DT-E-22-439 | 2022-07-25 | 0 | CRS-GUP-DHI-DT-22-634 | 2022-08-18 | NC | DE-GUP-DT-E-22-602 | 2022-09-01 | A | CRS-GUP-DHI-DT-22-799 | 2022-09-19 | RC | DE-GUP-DT-E-22-853 | 2022-10-25 | B | CRS-GUP-DHI-DT-22-1017 | 2022-11-13 | AA | DE-GUP-DT-E-22-984 | 2022-11-24 | 0 | CRS-GUP-DHI-DT-22-1248 | 2022-12-13 | AA | DE-GUP-DT-E-24-297 | 2024-12-23 | 1
| GUP | YL00 | P1 | QU | 135804 |  | GUP-YL00-P1QU-135804 | SAMPLING SYSTEM_INSTRUMENT LIST | FI | 2022-08-29 |  | 수처리설비기술팀(Water) | 김희정 |  |  |  |  | SWAS | CCPP | Sampling | I&C | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-293 | 2024-12-16 | 1 | CRS-GUP-DHI-DT-22-719 | 2022-09-05 | NC | DE-GUP-DT-E-22-526 | 2022-08-22 | 0 | CRS-GUP-DHI-DT-22-719 | 2022-09-05 | NC | DE-GUP-DT-E-24-293 | 2024-12-16 | 1
| GUP | XN00 | P1 | QU | 135707 |  | GUP-XN00-P1QU-135707 | SAMPLING SYSTEM_VALVE LIST | FI | 2022-08-29 |  | 수처리설비기술팀(Water) | 김희정 |  |  |  |  | SWAS | CCPP | Sampling | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-526 | 2022-08-22 | 0 | CRS-GUP-DHI-DT-22-719 | 2022-09-05 | NC | DE-GUP-DT-E-22-526 | 2022-08-22 | 0 | CRS-GUP-DHI-DT-22-719 | 2022-09-05 | NC
| GUP | YT01 | P1 | QU | 135704 |  | GUP-YT01-P1QU-135704 | SAMPLING SYSTEM_TECHNICAL DATASHEET | FA | 2022-09-29 | 2022-12-29 | 수처리설비기술팀(Water) | 김희정 |  |  |  |  | SWAS | CCPP | Sampling | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-984 | 2022-11-24 | 0 | CRS-GUP-DHI-DT-22-1248 | 2022-12-13 | AA | DE-GUP-DT-E-22-675 | 2022-09-16 | A | CRS-GUP-DHI-DT-22-904 | 20+AJ851+AI848 | RC | DE-GUP-DT-E-22-853 | 2022-10-25 | B | CRS-GUP-DHI-DT-22-1017 | 2022-11-13 | AA | DE-GUP-DT-E-22-984 | 2022-11-24 | 0 | CRS-GUP-DHI-DT-22-1248 | 2022-12-13 | AA
| GUP | YT01 | P1 | QU | 135805 |  | GUP-YT01-P1QU-135805 | SAMPLING SYSTEM_INSTRUMENT DATA SHEET | FA | 2022-09-29 | 2022-12-29 | 수처리설비기술팀(Water) | 김희정 |  |  |  |  | SWAS | CCPP | Sampling | I&C | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-293 | 2024-12-16 | 2 | 자체 CRS 개정 후 제출 | 2024-12-15 | N/A | DE-GUP-DT-E-22-602 | 2022-09-01 | A | CRS-GUP-DHI-DT-22-799 | 2022-09-19 | RC | DE-GUP-DT-E-22-853 | 2022-10-25 | B | CRS-GUP-DHI-DT-22-1017 | 2022-11-13 | AA | DE-GUP-DT-E-22-984 | 2022-11-24 | 0 | CRS-GUP-DHI-DT-22-1248 | 2022-12-13 | AA | DE-GUP-DT-E-24-044 | 2024-02-16 | 1 | 자체 CRS 개정 후 제출 | 2024-12-15 | N/A | DE-GUP-DT-E-24-293 | 2024-12-16 | 2
| GUP | YS01 | P1 | QU | 135811 |  | GUP-YS01-P1QU-135811 | SAMPLING SYSTEM_SCHEMATIC DIAGRAM | FA | 2022-09-29 | 2022-12-29 | 수처리설비기술팀(Water) | 김희정 |  | R |  |  | SWAS | CCPP | Sampling | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-044 | 2024-02-16 | 1 | CRS-GUP-DHI-DT-22-1248 | 2022-12-13 | AA | DE-GUP-DT-E-22-675 | 2022-09-16 | A | CRS-GUP-DHI-DT-22-904 | 2022-10-12 | RC | DE-GUP-DT-E-22-853 | 2022-10-25 | B | CRS-GUP-DHI-DT-22-1017 | 2022-11-13 | AA | DE-GUP-DT-E-22-984 | 2022-11-24 | 0 | CRS-GUP-DHI-DT-22-1248 | 2022-12-13 | AA | DE-GUP-DT-E-24-044 | 2024-02-16 | 1
| GUP | CQ02 | P1 | QU | 135606 |  | GUP-CQ02-P1QU-135606 | SAMPLING SYSTEM_O&M MANUAL | FI | 2024-02-29 |  | 수처리설비기술팀(Water) | 김희정 |  |  |  |  | SWAS | CCPP | Sampling | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-045 | 2024-02-16 | 0 | CRS-GUP-DHI-DT-24-064 | 2024-07-17 | NC | DE-GUP-DT-E-24-045 | 2024-02-16 | 0 | CRS-GUP-DHI-DT-24-064 | 2024-07-17 | NC
| GUP | XA00 | P1 | SR | 136711 |  | GUP-XA00-P1SR-136711 | WORKSHOP EQUIPMENT_EQUIPMENT ARRANGEMENT DRAWING | FA | 2022-11-10 | 2023-02-13 | 수처리설비기술팀(Water) | 이용재 |  | R |  |  | MECH.WORKSHOP EQUIP. | CCPP | Workshop Equipment | Mech. | 2 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-23-434 | 2023-04-07 | 0 | CRS-GUP-DHI-DT-23-1796 | 2023-04-04 | AA | DE-GUP-DT-E-22-1002 | 2022-11-29 | A | CRS-GUP-DHI-DT-22-1267 | 2022-12-16 | RC | DE-GUP-DT-E-23-139 | 2023-02-07 | B | CRS-GUP-DHI-DT-23-1657 | 2023-03-07 | RC | DE-GUP-DT-E-23-321 | 2023-03-16 | C | CRS-GUP-DHI-DT-23-1796 | 2023-04-04 | AA | DE-GUP-DT-E-23-434 | 2023-04-07 | 0
| GUP | YT01 | P1 | SR | 136704 |  | GUP-YT01-P1SR-136704 | WORKSHOP EQUIPMENT_EQUIPMENT LIST & SPECIFICATION | FA | 2022-11-10 | 2023-02-13 | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | MECH.WORKSHOP EQUIP. | CCPP | Workshop Equipment | Mech. | 2 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-23-321 | 2023-03-16 | 0 | CRS-GUP-DHI-DT-23-1796 | 2023-04-04 | AA | DE-GUP-DT-E-22-1002 | 2022-11-29 | A | CRS-GUP-DHI-DT-22-1267 | 2022-12-16 | RC | DE-GUP-DT-E-23-139 | 2023-02-07 | B | CRS-GUP-DHI-DT-23-1657 | 2023-03-07 | AA | DE-GUP-DT-E-23-321 | 2023-03-16 | 0 | CRS-GUP-DHI-DT-23-1796 | 2023-04-04 | AA
| GUP | XA00 | P1 | SR | 136712 |  | GUP-XA00-P1SR-136712 | WORKSHOP EQUIPMENT_POWER LINE ARRANGEMENT DRAWING | FI | 2022-12-25 |  | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | MECH.WORKSHOP EQUIP. | CCPP | Workshop Equipment | Elec. | 3 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-23-253 | 2023-02-27 | 0 | CRS-GUP-DHI-DT-23-1709 | 2023-03-14 | NC | DE-GUP-DT-E-23-253 | 2023-02-27 | 0 | CRS-GUP-DHI-DT-23-1709 | 2023-03-14 | NC
| GUP | XA00 | P1 | SR | 136713 |  | GUP-XA00-P1SR-136713 | WORKSHOP EQUIPMENT_UTILITY LINE ARRANGEMENT DRAWING | FI | 2023-03-03 |  | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | MECH.WORKSHOP EQUIP. | CCPP | Workshop Equipment | Elec. | 3 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-23-253 | 2023-02-27 | 0 | CRS-GUP-DHI-DT-23-1709 | 2023-03-14 | NC | DE-GUP-DT-E-23-253 | 2023-02-27 | 0 | CRS-GUP-DHI-DT-23-1709 | 2023-03-14 | NC
| GUP | CQ02 | P1 | SR | 136706 |  | GUP-CQ02-P1SR-136706 | WORKSHOP EQUIPMENT_O&M MANUAL | FI | 2024-02-29 |  | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | MECH.WORKSHOP EQUIP. | CCPP | Workshop Equipment | Mech. | 3 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-24-076 | 2024-03-14 | 0 | CRS-GUP-DHI-DT-24-060 | 2024-07-04 | NC | DE-GUP-DT-E-24-076 | 2024-03-14 | 0 | CRS-GUP-DHI-DT-24-060 | 2024-07-04 | NC
| GUP | XA00 | P1 | SR | 136911 |  | GUP-XA00-P1SR-136911 | WAREHOUSE EQUIPMENT_EQUIPMENT ARRANGEMENT DRAWING | FA | 2022-11-10 | 2023-02-13 | 수처리설비기술팀(Water) | 이용재 |  | R |  |  | WAREHOUSE EQUIP. | CCPP | WareHouse Equipment | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-434 | 2023-04-07 | 0 | CRS-GUP-DHI-DT-23-1796 | 2023-04-04 | AA | DE-GUP-DT-E-22-1002 | 2022-11-29 | A | CRS-GUP-DHI-DT-22-1267 | 2022-12-16 | RC | DE-GUP-DT-E-23-139 | 2023-02-07 | B | CRS-GUP-DHI-DT-23-1657 | 2023-03-07 | RC | DE-GUP-DT-E-23-321 | 2023-03-16 | C | CRS-GUP-DHI-DT-23-1796 | 2023-04-04 | AA | DE-GUP-DT-E-23-434 | 2023-04-07 | 0
| GUP | YT01 | P1 | SR | 136904 |  | GUP-YT01-P1SR-136904 | WAREHOUSE EQUIPMENT_EQUIPMENT LIST & DATA SHEET | FA | 2022-11-10 | 2023-02-13 | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | WAREHOUSE EQUIP. | CCPP | WareHouse Equipment | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-321 | 2023-03-16 | 0 | CRS-GUP-DHI-DT-23-1796 | 2023-04-04 | AA | DE-GUP-DT-E-22-1002 | 2022-11-29 | A | CRS-GUP-DHI-DT-22-1267 | 2022-12-16 | RC | DE-GUP-DT-E-23-139 | 2023-02-07 | B | CRS-GUP-DHI-DT-23-1657 | 2023-03-07 | AA | DE-GUP-DT-E-23-321 | 2023-03-16 | 0 | CRS-GUP-DHI-DT-23-1796 | 2023-04-04 | AA
| GUP | XG02 | P1 | G | 134101 |  | GUP-XG02-P1G-134101 | WATER & WASTE WATER TREATMENT PLANT_P&I DIAGRAM | FA | 2022-02-10 | 2022-10-10 | 수처리설비기술팀(Water) | 이용재 |  |  | G | FA | WTP | CCPP | Water Treatment | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-187 | 2024-07-23 | 2 | 자체 CRS 개정 후 제출 | 2024-07-22 | N/A | DHI-GUP-DT-22-117 | 2022-03-18 | A | CRS-GUP-DHI-DT-22-278 | 2022-04-07 | RC | DE-GUP-DT-E-22-264 | 2022-06-02 | B | CRS-GUP-DHI-DT-22-458 | 2022-06-21 | RC | DE-GUP-DT-E-22-503 | 2022-08-16 | C | CRS-GUP-DHI-DT-22-711 | 2022-09-05 | RC | DE-GUP-DT-E-22-1081 | 2022-12-12 | D | CRS-GUP-DHI-DT-22-1335 | 2022-12-28 | AC | DE-GUP-DT-E-23-007 | 2023-01-12 | 0(CP) | CRS-GUP-DHI-DT-23-1652 | 2023-03-07 | AA | DE-GUP-DT-E-23-1002 | 2023-12-20 | 1 | 자체 CRS 개정 후 제출 | 2024-07-22 | N/A | DE-GUP-DT-E-24-187 | 2024-07-23 | 2
| GUP | XA00 | P1 | G | 134103 |  | GUP-XA00-P1G-134103 | WATER & WASTE WATER TREATMENT PLANT_GENERAL ARRANGEMENT DRAWING | FA | 2021-12-09 | 2022-08-09 | 수처리설비기술팀(Water) | 이용재 |  | R | G | FA | WTP | CCPP | Water Treatment | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-748 | 2023-08-17 | 1 | 자체 CRS 개정 후 제출 | 2023-08-16 | N/A | DHI-GUP-DT-21-174 | 2021-12-15 | A | CRS-GUP-DHI-DT-21-161 | 2022-01-14 | RC | DHI-GUP-DT-22-117 | 2022-03-18 | B | CRS-GUP-DHI-DT-22-278 | 2022-04-07 | RC | DE-GUP-DT-E-22-264 | 2022-06-02 | C | CRS-GUP-DHI-DT-22-458 | 2022-06-21 | RC | DE-GUP-DT-E-22-503 | 2022-08-16 | D | CRS-GUP-DHI-DT-22-711 | 2022-09-05 | RC | DE-GUP-DT-E-22-1027 | 2022-12-02 | E | CRS-GUP-DHI-DT-22-1277 | 2022-12-16 | AA | DE-GUP-DT-E-23-008 | 2023-01-12 | 0 | 자체 CRS 개정 후 제출 | 2023-08-16 | N/A | DE-GUP-DT-E-23-748 | 2023-08-17 | 1
| GUP | XS00 | P1 | G | 134104 |  | GUP-XS00-P1G-134104 | WATER & WASTE WATER TREATMENT PLANT_SYSTEM DESCRIPTION | FA | 2021-12-03 | 2022-08-03 | 수처리설비기술팀(Water) | 이용재 |  | R | G | FA | WTP | CCPP | Water Treatment | Mech. | 1 | 2025-06-30 |  |  | DE-GUP-DT-E-23-1002 | 2023-12-20 | 1 | CRS-GUP-DHI-DT-22-1278 | 2022-12-16 | AA | DHI-GUP-DT-21-165 | 2021-12-10 | A | CRS-GUP-DHI-DT-21-129 | 2022-01-11 | RC | DHI-GUP-DT-22-117 | 2022-03-18 | B | CRS-GUP-DHI-DT-22-278 | 2022-04-07 | RC | DE-GUP-DT-E-22-264 | 2022-06-02 | C | CRS-GUP-DHI-DT-22-458 | 2022-06-21 | RC | DE-GUP-DT-E-22-503 | 2022-08-16 | D | CRS-GUP-DHI-DT-22-711 | 2022-09-05 | AC | DE-GUP-DT-E-22-1028 | 2022-12-02 | 0(CP) | CRS-GUP-DHI-DT-22-1278 | 2022-12-16 | AA | DE-GUP-DT-E-23-1002 | 2023-12-20 | 1
| GUP | CC07 | P1 | G | 134105 |  | GUP-CC07-P1G-134105 | WATER & WASTE WATER TREATMENT PLANT_CALCULATION SHEET | FA | 2021-12-03 | 2022-08-03 | 수처리설비기술팀(Water) | 이용재 |  | R |  |  | WTP | CCPP | Water Treatment | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-1002 | 2023-12-20 | 1 | CRS-GUP-DHI-DT-22-1278 | 2022-12-16 | AA | DHI-GUP-DT-21-165 | 2021-12-10 | A | CRS-GUP-DHI-DT-21-129 | 2022-01-11 | RC | DHI-GUP-DT-22-117 | 2022-03-18 | B | CRS-GUP-DHI-DT-22-278 | 2022-04-07 | RC | DE-GUP-DT-E-22-264 | 2022-06-02 | C | CRS-GUP-DHI-DT-22-458 | 2022-06-21 | AC | DE-GUP-DT-E-22-503 | 2022-08-16 | D | CRS-GUP-DHI-DT-22-711 | 2022-09-05 | AC | DE-GUP-DT-E-22-1028 | 2022-12-02 | 0(CP) | CRS-GUP-DHI-DT-22-1278 | 2022-12-16 | AA | DE-GUP-DT-E-23-1002 | 2023-12-20 | 1
| GUP | XG08 | P1 | G | 134102 |  | GUP-XG08-P1G-134102 | WATER & WASTE WATER TREATMENT PLANT_PROCESS FLOW DIAGRAM & MASS BALANCE | FA | 2021-12-03 | 2022-08-03 | 수처리설비기술팀(Water) | 이용재 |  |  | G | FA | WTP | CCPP | Water Treatment | Mech. | 1 | 2025-06-30 |  |  | DE-GUP-DT-E-23-1002 | 2023-12-20 | 1 | CRS-GUP-DHI-DT-22-1278 | 2022-12-16 | AA | DHI-GUP-DT-21-165 | 2021-12-10 | A | CRS-GUP-DHI-DT-21-129 | 2022-01-11 | RC | DHI-GUP-DT-22-117 | 2022-03-18 | B | CRS-GUP-DHI-DT-22-278 | 2022-04-07 | RC | DE-GUP-DT-E-22-264 | 2022-06-02 | C | CRS-GUP-DHI-DT-22-458 | 2022-06-21 | RC | DE-GUP-DT-E-22-503 | 2022-08-16 | D | CRS-GUP-DHI-DT-22-711 | 2022-09-05 | AC | DE-GUP-DT-E-22-1028 | 2022-12-02 | 0(CP) | CRS-GUP-DHI-DT-22-1278 | 2022-12-16 | AA | DE-GUP-DT-E-23-1002 | 2023-12-20 | 1
| GUP | YD00 | P1 | G | 134301 |  | GUP-YD00-P1G-134301 | WATER & WASTE WATER TREATMENT PLANT_CONTROL PANEL ARRANGEMENT DRAWING | FI | 2022-02-18 |  | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | WTP | CCPP | Water Treatment | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-138 | 2024-05-22 | 1 | CRS-GUP-DHI-DT-22-509 | 2022-07-11 | NC | DE-GUP-DT-E-22-313 | 2022-06-17 | 0 | CRS-GUP-DHI-DT-22-509 | 2022-07-11 | NC | DE-GUP-DT-E-24-138 | 2024-05-22 | 1
| GUP | YU01 | P1 | G | 134401 |  | GUP-YU01-P1G-134401 | WATER & WASTE WATER TREATMENT PLANT_SINGLE LINE DIAGRAM | FA | 2022-02-18 | 2022-10-18 | 수처리설비기술팀(Water) | 이용재 |  | R |  |  | WTP | CCPP | Water Treatment | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-138 | 2024-05-22 | 1 | CRS-GUP-DHI-DT-22-1366 | 2022-12-30 | AA | DE-GUP-DT-E-22-530 | 2022-08-23 | A | CRS-GUP-DHI-DT-22-758 | 2022-09-14 | RC | DE-GUP-DT-E-22-855 | 2022-10-26 | B | CRS-GUP-DHI-DT-22-1052 | 2022-11-17 | AA | DE-GUP-DT-E-22-1082 | 2022-12-12 | 0 | CRS-GUP-DHI-DT-22-1366 | 2022-12-30 | AA | DE-GUP-DT-E-24-138 | 2024-05-22 | 1
| GUP | YD00 | P1 | G | 134402 |  | GUP-YD00-P1G-134402 | WATER & WASTE WATER TREATMENT PLANT_MCC ARRANGEMENT DRAWING | FI | 2022-02-18 |  | 수처리설비기술팀(Water) | 이용재 |  | R |  |  | WTP | CCPP | Water Treatment | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-189 | 2024-07-23 | 4 | 자체 CRS 개정 후 제출 | 2024-07-22 | N/A | DE-GUP-DT-E-22-530 | 2022-08-23 | 0 | CRS-GUP-DHI-DT-22-758 | 2022-09-14 | RC | DE-GUP-DT-E-22-855 | 2022-10-26 | 1 | CRS-GUP-DHI-DT-22-1052 | 2022-11-17 | NC | DE-GUP-DT-E-22-1082 | 2022-12-12 | 2 | CRS-GUP-DHI-DT-22-1366 | 2022-12-30 | NC | DE-GUP-DT-E-24-138 | 2024-05-22 | 3 | 자체 CRS 개정 후 제출 | 2024-07-22 | N/A | DE-GUP-DT-E-24-189 | 2024-07-23 | 4
| GUP | YF02 | P1 | G | 134303 |  | GUP-YF02-P1G-134303 | WATER & WASTE WATER TREATMENT PLANT_CONTROL CONFIGURATION DIAGRAM | FA | 2022-02-10 | 2022-10-10 | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | WTP | CCPP | Water Treatment | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-138 | 2024-05-22 | 1 | 자체 CRS 개정 후 제출 | 2024-05-21 | N/A | DE-GUP-DT-E-22-313 | 2022-06-17 | A | CRS-GUP-DHI-DT-22-509 | 2022-07-11 | RC | DE-GUP-DT-E-22-861 | 2022-10-27 | B | CRS-GUP-DHI-DT-22-1021 | 2022-11-13 | RC | DE-GUP-DT-E-22-993 | 2022-11-28 | C | CRS-GUP-DHI-DT-22-1261 | 2022-12-16 | AA | DE-GUP-DT-E-22-1148 | 2022-12-22 | 0 | 자체 CRS 개정 후 제출 | 2024-05-21 | N/A | DE-GUP-DT-E-24-138 | 2024-05-22 | 1
| GUP | YL00 | P1 | G | 134304 |  | GUP-YL00-P1G-134304 | WATER & WASTE WATER TREATMENT PLANT_INSTRUMENT LIST | FI | 2022-02-10 |  | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | WTP | CCPP | Water Treatment | I&C | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-313 | 2022-06-17 | 1 | CRS-GUP-DHI-DT-22-509 | 2022-07-11 | NC | DHI-GUP-DT-22-173 | 2022-04-14 | 0 | CRS-GUP-DHI-DT-22-311 | 2022-04-26 | RR | DE-GUP-DT-E-22-313 | 2022-06-17 | 1 | CRS-GUP-DHI-DT-22-509 | 2022-07-11 | NC
| GUP | YN00 | P1 | G | 134207 |  | GUP-YN00-P1G-134207 | WATER & WASTE WATER TREATMENT PLANT_VALVE LIST | FI | 2022-02-10 |  | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | WTP | CCPP | Water Treatment | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-1001 | 2023-12-20 | 2 | CRS-GUP-DHI-DT-22-525 | 2022-07-19 | NC | DHI-GUP-DT-22-173 | 2022-04-14 | 0 | CRS-GUP-DHI-DT-22-311 | 2022-04-26 | RR | DE-GUP-DT-E-22-315 | 2022-06-20 | 1 | CRS-GUP-DHI-DT-22-525 | 2022-07-19 | NC | DE-GUP-DT-E-23-1001 | 2023-12-20 | 2
| GUP | XB02 | P1 | G | 134151 |  | GUP-XB02-P1G-134151 | WATER & WASTE WATER TREATMENT PLANT_FOUNDATION AND LOADING DATA | FI | 2022-03-31 |  | 수처리설비기술팀(Water) | 이용재 |  | R |  |  | WTP | CCPP | Water Treatment | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-748 | 2023-08-17 | 2 | CRS-GUP-DHI-DT-22-1250 | 2022-12-13 | NC | DE-GUP-DT-E-22-480 | 2022-07-29 | 0 | CRS-GUP-DHI-DT-22-683 | 2022-08-22 | NC | DE-GUP-DT-E-22-1081 | 2022-12-12 | 1 | CRS-GUP-DHI-DT-22-1250 | 2022-12-13 | NC | DE-GUP-DT-E-23-748 | 2023-08-17 | 2
| GUP | YK10 | P1 | G | 134201 |  | GUP-YK10-P1G-134201 | WATER & WASTE WATER TREATMENT PLANT_EQUIPMENT ASSEMBLY DRAWING | FI | 2022-03-31 |  | 수처리설비기술팀(Water) | 이용재 |  | R |  |  | WTP | CCPP | Water Treatment | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-1001 | 2023-12-20 | 3 | CRS-GUP-DHI-DT-22-1374 | 2022-12-31 | NC | DE-GUP-DT-E-22-480 | 2022-07-29 | 0 | CRS-GUP-DHI-DT-22-683 | 2022-08-22 | RC | DE-GUP-DT-E-22-775 | 2022-10-07 | 1 | CRS-GUP-DHI-DT-22-1076 | 2022-11-19 | NC | DE-GUP-DT-E-22-1118 | 2022-12-19 | 2 | CRS-GUP-DHI-DT-22-1374 | 2022-12-31 | NC | DE-GUP-DT-E-23-1001 | 2023-12-20 | 3
| GUP | YD00 | P1 | G | 134302 |  | GUP-YD00-P1G-134302 | WATER & WASTE WATER TREATMENT PLANT_OTHER PANEL ARRANGEMENT DRAWING | FI | 2022-02-18 |  | 수처리설비기술팀(Water) | 이용재 |  | R |  |  | WTP | CCPP | Water Treatment | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-313 | 2022-06-17 | 0 | CRS-GUP-DHI-DT-22-509 | 2022-07-11 | NC | DE-GUP-DT-E-22-313 | 2022-06-17 | 0 | CRS-GUP-DHI-DT-22-509 | 2022-07-11 | NC
| GUP | XH01 | P1 | G | 134209 |  | GUP-XH01-P1G-134209 | WATER & WASTE WATER TREATMENT PLANT_PIPING ARRANGEMENT DRAWING | FI | 2022-05-31 |  | 수처리설비기술팀(Water) | 이용재 |  | R |  |  | WTP | CCPP | Water Treatment | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-756 | 2022-10-05 | 0 | CRS-GUP-DHI-DT-22-998 | 2022-11-13 | NC | DE-GUP-DT-E-22-756 | 2022-10-05 | 0 | CRS-GUP-DHI-DT-22-998 | 2022-11-13 | NC
| GUP | YT01 | P1 | G | 134501 |  | GUP-YT01-P1G-134501 | WATER & WASTE WATER TREATMENT PLANT_TECHNICAL DATASHEET-Pre-treatment System | FA | 2022-06-10 | 2022-10-10 | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | WTP | CCPP | Water Treatment | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-1002 | 2023-12-20 | 1 | CRS-GUP-DHI-DT-23-1850 | 2023-04-19 | AA | DE-GUP-DT-E-22-285 | 2022-06-10 | A | CRS-GUP-DHI-DT-22-491 | 2022-07-06 | RC | DE-GUP-DT-E-22-657 | 2022-09-14 | B | CRS-GUP-DHI-DT-22-879 | 2022-10-09 | RC | DE-GUP-DT-E-22-1045 | 2022-12-08 | C | CRS-GUP-DHI-DT-22-1319 | 2022-12-22 | RC | DE-GUP-DT-E-23-391 | 2023-03-30 | 0(CP) | CRS-GUP-DHI-DT-23-1850 | 2023-04-19 | AA | DE-GUP-DT-E-23-1002 | 2023-12-20 | 1
| GUP | YT01 | P1 | G | 134601 |  | GUP-YT01-P1G-134601 | WATER & WASTE WATER TREATMENT PLANT_TECHNICAL DATASHEET-Demi.Water System | FA | 2022-06-10 | 2022-10-10 | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | WTP | CCPP | Water Treatment | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-1002 | 2023-12-20 | 1 | CRS-GUP-DHI-DT-22-1319 | 2022-12-22 | AA | DE-GUP-DT-E-22-285 | 2022-06-10 | A | CRS-GUP-DHI-DT-22-491 | 2022-07-06 | RC | DE-GUP-DT-E-22-657 | 2022-09-14 | B | CRS-GUP-DHI-DT-22-879 | 2022-10-09 | AC | DE-GUP-DT-E-22-1045 | 2022-12-08 | 0(CP) | CRS-GUP-DHI-DT-22-1319 | 2022-12-22 | AA | DE-GUP-DT-E-23-1002 | 2023-12-20 | 1
| GUP | YT01 | P1 | G | 134701 |  | GUP-YT01-P1G-134701 | WATER & WASTE WATER TREATMENT PLANT_TECHNICAL DATASHEET-Chemical Dosing System | FA | 2022-06-10 | 2022-10-10 | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | WTP | CCPP | Water Treatment | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-1001 | 2023-12-20 | 1 | CRS-GUP-DHI-DT-22-1312 | 2022-12-22 | AA | DE-GUP-DT-E-22-285 | 2022-06-10 | A | CRS-GUP-DHI-DT-22-491 | 2022-07-06 | RC | DE-GUP-DT-E-22-657 | 2022-09-14 | B | CRS-GUP-DHI-DT-22-879 | 2022-10-09 | AA | DE-GUP-DT-E-22-1045 | 2022-12-08 | 0 | CRS-GUP-DHI-DT-22-1312 | 2022-12-22 | AA | DE-GUP-DT-E-23-1001 | 2023-12-20 | 1
| GUP | YT01 | P1 | G | 134801 |  | GUP-YT01-P1G-134801 | WATER & WASTE WATER TREATMENT PLANT_TECHNICAL DATASHEET-Waste Water Treatment System | FA | 2022-06-10 | 2022-10-10 | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | WTP | CCPP | Water Treatment | Mech. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-1002 | 2023-12-20 | 1 | CRS-GUP-DHI-DT-22-1319 | 2022-12-22 | AA | DE-GUP-DT-E-22-285 | 2022-06-10 | A | CRS-GUP-DHI-DT-22-491 | 2022-07-06 | RC | DE-GUP-DT-E-22-657 | 2022-09-14 | B | CRS-GUP-DHI-DT-22-879 | 2022-10-09 | AC | DE-GUP-DT-E-22-1045 | 2022-12-08 | 0(CP) | CRS-GUP-DHI-DT-22-1319 | 2022-12-22 | AA | DE-GUP-DT-E-23-1002 | 2023-12-20 | 1
| GUP | YT01 | P1 | G | 134206 |  | GUP-YT01-P1G-134206 | WATER & WASTE WATER TREATMENT PLANT_MOTOR DATA SHEET | FI | 2022-02-28 |  | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | WTP | CCPP | Water Treatment | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-189 | 2024-07-23 | 1 | CRS-GUP-DHI-DT-22-879 | 2022-10-09 | NC | DE-GUP-DT-E-22-657 | 2022-09-14 | 0 | CRS-GUP-DHI-DT-22-879 | 2022-10-09 | NC | DE-GUP-DT-E-24-189 | 2024-07-23 | 1
| GUP | YT01 | P1 | G | 134205 |  | GUP-YT01-P1G-134205 | WATER & WASTE WATER TREATMENT PLANT_PUMP DATA SHEET | FA | 2022-02-28 | 2022-10-10 | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | WTP | CCPP | Water Treatment | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-494 | 2023-04-21 | 1 | CRS-GUP-DHI-DT-23-1918 | 2023-05-05 | AA | DE-GUP-DT-E-22-620 | 2022-09-05 | A | CRS-GUP-DHI-DT-22-805 | 2022-09-19 | RC | DE-GUP-DT-E-22-1026 | 2022-12-02 | B | CRS-GUP-DHI-DT-22-1276 | 2022-12-16 | RC | DE-GUP-DT-E-23-007 | 2023-01-12 | C | CRS-GUP-DHI-DT-23-1676 | 2023-03-13 | AC | DE-GUP-DT-E-23-391 | 2023-03-30 | 0(CP) | CRS-GUP-DHI-DT-23-1850 | 2023-04-19 | AA | DE-GUP-DT-E-23-494 | 2023-04-21 | 1 | CRS-GUP-DHI-DT-23-1918 | 2023-05-05 | AA
| GUP | YT01 | P1 | G | 134208 |  | GUP-YT01-P1G-134208 | WATER & WASTE WATER TREATMENT PLANT_VALVE DATA SHEET | FI | 2022-02-28 |  | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | WTP | CCPP | Water Treatment | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-1001 | 2023-12-20 | 2 | CRS-GUP-DHI-DT-22-525 | 2022-07-19 | NC | DHI-GUP-DT-22-173 | 2022-04-14 | 0 | CRS-GUP-DHI-DT-22-311 | 2022-04-26 | RR | DE-GUP-DT-E-22-315 | 2022-06-20 | 1 | CRS-GUP-DHI-DT-22-525 | 2022-07-19 | NC | DE-GUP-DT-E-23-1001 | 2023-12-20 | 2
| GUP | YT01 | P1 | G | 134308 |  | GUP-YT01-P1G-134308 | WATER & WASTE WATER TREATMENT PLANT_PLC DATA SHEET | FI | 2022-02-28 |  | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | WTP | CCPP | Water Treatment | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-313 | 2022-06-17 | 0 | CRS-GUP-DHI-DT-22-509 | 2022-07-11 | NC | DE-GUP-DT-E-22-313 | 2022-06-17 | 0 | CRS-GUP-DHI-DT-22-509 | 2022-07-11 | NC
| GUP | YT01 | P1 | G | 134305 |  | GUP-YT01-P1G-134305 | WATER & WASTE WATER TREATMENT PLANT_INSTRUMENT DATA SHEET | FI | 2022-02-10 |  | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | WTP | CCPP | Water Treatment | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-313 | 2022-06-17 | 1 | CRS-GUP-DHI-DT-22-509 | 2022-07-11 | NC | DHI-GUP-DT-22-173 | 2022-04-14 | 0 | CRS-GUP-DHI-DT-22-311 | 2022-04-26 | RR | DE-GUP-DT-E-22-313 | 2022-06-17 | 1 | CRS-GUP-DHI-DT-22-509 | 2022-07-11 | NC
| GUP | XH01 | P1 | G | 134210 |  | GUP-XH01-P1G-134210 | WATER & WASTE WATER TREATMENT PLANT_PIPE SUPPORT LOCATION & DETAIL DRAWING | FI | 2022-05-31 |  | 수처리설비기술팀(Water) | 이용재 |  | R |  |  | WTP | CCPP | Water Treatment | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-756 | 2022-10-05 | 0 | CRS-GUP-DHI-DT-22-998 | 2022-11-13 | NC | DE-GUP-DT-E-22-756 | 2022-10-05 | 0 | CRS-GUP-DHI-DT-22-998 | 2022-11-13 | NC
| GUP | YV02 | P1 | G | 134309 |  | GUP-YV02-P1G-134309 | WATER & WASTE WATER TREATMENT PLANT_INTERCONNECTION WIRING DIAGRAM | FI | 2022-03-07 |  | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | WTP | CCPP | Water Treatment | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1204 | 2022-12-28 | 1 | CRS-GUP-DHI-DT-23-1440 | 2023-01-31 | NC | DE-GUP-DT-E-22-533 | 2022-08-23 | 0 | CRS-GUP-DHI-DT-22-721 | 2022-09-05 | RC | DE-GUP-DT-E-22-1204 | 2022-12-28 | 1 | CRS-GUP-DHI-DT-23-1440 | 2023-01-31 | NC
| GUP | YL22 | P1 | G | 134202 |  | GUP-YL22-P1G-134202 | WATER & WASTE WATER TREATMENT PLANT_NAME PLATE DRAWING | FI | 2022-03-31 |  | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | WTP | CCPP | Water Treatment | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-620 | 2022-09-05 | 0 | CRS-GUP-DHI-DT-22-805 | 2022-09-19 | NC | DE-GUP-DT-E-22-620 | 2022-09-05 | 0 | CRS-GUP-DHI-DT-22-805 | 2022-09-19 | NC
| GUP | YL01 | P1 | G | 134307 |  | GUP-YL01-P1G-134307 | WATER & WASTE WATER TREATMENT PLANT_PLC I/O LIST | FI | 2022-02-28 |  | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | WTP | CCPP | Water Treatment | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-313 | 2022-06-17 | 0 | CRS-GUP-DHI-DT-22-509 | 2022-07-11 | NC | DE-GUP-DT-E-22-313 | 2022-06-17 | 0 | CRS-GUP-DHI-DT-22-509 | 2022-07-11 | NC
| GUP | YF00 | P1 | G | 134310 |  | GUP-YF00-P1G-134310 | WATER & WASTE WATER TREATMENT PLANT_CONTROL LOOP & LOGIC DIAGRAM | FI | 2022-03-31 |  | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | WTP | CCPP | Water Treatment | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-756 | 2022-10-05 | 0 | CRS-GUP-DHI-DT-22-998 | 2022-11-13 | NC | DE-GUP-DT-E-22-756 | 2022-10-05 | 0 | CRS-GUP-DHI-DT-22-998 | 2022-11-13 | NC
| GUP | YS01 | P1 | G | 134411 |  | GUP-YS01-P1G-134411 | WATER & WASTE WATER TREATMENT PLANT_MCC SCHEMATIC DIAGRAM | FA | 2022-03-07 | 2022-10-07 | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | WTP | CCPP | Water Treatment | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-139 | 2024-05-24 | 2 | CRS-GUP-DHI-DT-22-1366 | 2022-12-30 | NC | DE-GUP-DT-E-22-530 | 2022-08-23 | 0 | CRS-GUP-DHI-DT-22-758 | 2022-09-14 | NC | DE-GUP-DT-E-22-830 | 2022-10-20 | 0 | CRS-GUP-DHI-DT-22-1196 | 2022-11-30 | NC | DE-GUP-DT-E-22-1082 | 2022-12-12 | 1 | CRS-GUP-DHI-DT-22-1366 | 2022-12-30 | NC | DE-GUP-DT-E-24-139 | 2024-05-24 | 2
| GUP | YS01 | P1 | G | 134311 |  | GUP-YS01-P1G-134311 | WATER & WASTE WATER TREATMENT PLANT_SCHEMATIC DIAGRAM | FA | 2022-02-28 | 2022-10-28 | 수처리설비기술팀(Water) | 이용재 |  | R |  |  | WTP | CCPP | Water Treatment | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-138 | 2024-05-22 | 1 | CRS-GUP-DHI-DT-22-1261 | 2022-12-16 | AA | DE-GUP-DT-E-22-313 | 2022-06-17 | A | CRS-GUP-DHI-DT-22-509 | 2022-07-11 | AA | DE-GUP-DT-E-22-993 | 2022-11-28 | 0 | CRS-GUP-DHI-DT-22-1261 | 2022-12-16 | AA | DE-GUP-DT-E-24-138 | 2024-05-22 | 1
| GUP | YE00 | P1 | G | 134404 |  | GUP-YE00-P1G-134404 | WATER & WASTE WATER TREATMENT PLANT_CABLE TRAY LAYOUT DRAWING | FI | 2022-03-07 |  | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | WTP | CCPP | Water Treatment | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-754 | 2023-08-23 | 2 | CRS-GUP-DHI-DT-23-1440 | 2023-01-31 | NC | DE-GUP-DT-E-22-596 | 2022-08-31 | 0 | CRS-GUP-DHI-DT-22-798 | 2022-09-19 | NC | DE-GUP-DT-E-22-1204 | 2022-12-28 | 1 | CRS-GUP-DHI-DT-23-1440 | 2023-01-31 | NC | DE-GUP-DT-E-23-754 | 2023-08-23 | 2
| GUP | YD05 | P1 | G | 134312 |  | GUP-YD05-P1G-134312 | WATER & WASTE WATER TREATMENT PLANT_HMI GRAPHICS | FI | 2022-03-07 |  | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | WTP | CCPP | Water Treatment | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-993 | 2022-11-28 | 1 | CRS-GUP-DHI-DT-22-1261 | 2022-12-16 | NC | DE-GUP-DT-E-22-620 | 2022-09-05 | 0 | CRS-GUP-DHI-DT-22-805 | 2022-09-19 | RC | DE-GUP-DT-E-22-993 | 2022-11-28 | 1 | CRS-GUP-DHI-DT-22-1261 | 2022-12-16 | NC
| GUP | CQ02 | P1 | G | 134106 |  | GUP-CQ02-P1G-134106 | WATER & WASTE WATER TREATMENT PLANT_O&M MANUAL | FI | 2024-02-29 |  | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | WTP | CCPP | Water Treatment | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-107 | 2024-04-08 | 0 | 별도 메일접수 24-020 | 2024-12-04 | RC | DE-GUP-DT-E-24-107 | 2024-04-08 | 0 | 별도 메일접수 24-020 | 2024-12-04 | RC
| GUP | US01 | P1 | G | 134152 |  | GUP-US01-P1G-134152 | WATER & WASTE WATER TREATMENT PLANT_EMBEDDED MATERIAL DRAWING | FI | 2022-03-31 |  | 수처리설비기술팀(Water) | 이용재 |  | R |  |  | WTP | CCPP | Water Treatment | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-1001 | 2023-12-20 | 2 | CRS-GUP-DHI-DT-22-1250 | 2022-12-13 | NC | DE-GUP-DT-E-22-595 | 2022-08-31 | 0 | CRS-GUP-DHI-DT-22-797 | 2022-09-19 | NC | DE-GUP-DT-E-22-1081 | 2022-12-12 | 1 | CRS-GUP-DHI-DT-22-1250 | 2022-12-13 | NC | DE-GUP-DT-E-23-1001 | 2023-12-20 | 2
| GUP | XH01 | P1 | G | 134153 |  | GUP-XH01-P1G-134153 | WATER & WASTE WATER TREATMENT PLANT_SLEEVE & WALL OPENING DRAWING | FI | 2022-03-31 |  | 수처리설비기술팀(Water) | 이용재 |  | R |  |  | WTP | CCPP | Water Treatment | Mech. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-1001 | 2023-12-20 | 2 | CRS-GUP-DHI-DT-22-1250 | 2022-12-13 | NC | DE-GUP-DT-E-22-595 | 2022-08-31 | 0 | CRS-GUP-DHI-DT-22-797 | 2022-09-19 | NC | DE-GUP-DT-E-22-1081 | 2022-12-12 | 1 | CRS-GUP-DHI-DT-22-1250 | 2022-12-13 | NC | DE-GUP-DT-E-23-1001 | 2023-12-20 | 2
| GUP | YL16 | P1 | G | 134313 |  | GUP-YL16-P1G-134313 | WATER & WASTE WATER TREATMENT PLANT_CABLE SCHEDULE | FI | 2022-03-31 |  | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | WTP | CCPP | Water Treatment | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-138 | 2024-05-22 | 2 | CRS-GUP-DHI-DT-23-1440 | 2023-01-31 | NC | DE-GUP-DT-E-22-533 | 2022-08-23 | 0 | CRS-GUP-DHI-DT-22-721 | 2022-09-05 | RC | DE-GUP-DT-E-22-1204 | 2022-12-28 | 1 | CRS-GUP-DHI-DT-23-1440 | 2023-01-31 | NC | DE-GUP-DT-E-24-138 | 2024-05-22 | 2
| GUP | YK00 | P1 | G | 134314 |  | GUP-YK00-P1G-134314 | WATER & WASTE WATER TREATMENT PLANT_HOOK UP DRAWING | FI | 2024-02-15 |  | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | WTP | CCPP | Water Treatment | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-040 | 2024-02-08 | 0 | CRS-GUP-DHI-DT-24-037 | 2024-03-14 | NC | DE-GUP-DT-E-24-040 | 2024-02-08 | 0 | CRS-GUP-DHI-DT-24-037 | 2024-03-14 | NC
| GUP | YD08 | P1 | G | 134315 |  | GUP-YD08-P1G-134315 | WATER & WASTE WATER TREATMENT PLANT_INSTRUMENT LOCATION DRAWING | FI | 2024-02-15 |  | 수처리설비기술팀(Water) | 이용재 |  |  |  |  | WTP | CCPP | Water Treatment | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-040 | 2024-02-08 | 0 | CRS-GUP-DHI-DT-24-037 | 2024-03-14 | NC | DE-GUP-DT-E-24-040 | 2024-02-08 | 0 | CRS-GUP-DHI-DT-24-037 | 2024-03-14 | NC
| GUP | HM00 | P0 | SAA | 131001 |  | GUP-HM00-P0SAA-131001 | HVAC SYSTEM_DESIGN CRITERIA | FA | 2021-09-01 | 2021-11-30 | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | Plant | HVAC | 1 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-152 | 2022-04-07 | 0 | CRS-GUP-DHI-DT-22-318 | 2022-05-02 | AA | DHI-GUP-DT-21-023 | 2021-09-15 | A | CRS-GUP-DHI-DT-21-027 | 2021-10-04 | RC | DHI-GUP-DT-21-093 | 2021-11-09 | B | CRS-GUP-DHI-DT-21-075 | 2021-11-30 | AC | DHI-GUP-DT-22-152 | 2022-04-07 | 0 | CRS-GUP-DHI-DT-22-318 | 2022-05-02 | AA
| GUP | HM04 | P0 | SAA | 131002 |  | GUP-HM04-P0SAA-131002 | HVAC SYSTEM_STANDARD DRAWING | FA | 2021-09-15 | 2021-12-14 | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | Plant | HVAC | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-160 | 2024-06-20 | 2 | 자체 CRS 개정 후 제출 | 2024-06-19 | N/A | DHI-GUP-DT-21-027 | 2021-09-16 | A | CRS-GUP-DHI-DT-21-064 | 2021-11-17 | AA | DHI-GUP-DT-22-030 | 2022-01-21 | 0 | CRS-GUP-DHI-DT-22-192 | 2022-02-06 | AA | DE-GUP-DT-E-22-581 | 2022-08-30 | 1 | 자체 CRS 개정 후 제출 | 2024-06-19 | N/A | DE-GUP-DT-E-24-160 | 2024-06-20 | 2
| GUP | HM04 | P0 | SAA | 131003 |  | GUP-HM04-P0SAA-131003 | HVAC SYSTEM_VENDOR PRINT | FI | 2022-09-21 |  | 기계기술팀(HVAC) | 김재환 |  | P |  |  | HVAC System | CCPP | Plant | HVAC | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-215 | 2024-08-29 | 3 | CRS-GUP-DHI-DT-23-2011 | 2023-06-21 | NC | DE-GUP-DT-E-22-535 | 2022-08-23 | 0 | CRS-GUP-DHI-DT-22-738 | 2022-09-12 | NC | DE-GUP-DT-E-23-320 | 2023-03-16 | 1 | CRS-GUP-DHI-DT-23-1790 | 2023-03-30 | NC | DE-GUP-DT-E-23-591 | 2023-05-30 | 2 | CRS-GUP-DHI-DT-23-2011 | 2023-06-21 | NC | DE-GUP-DT-E-24-215 | 2024-08-29 | 3
| GUP | HM04 | P0 | SAA | 131004 |  | GUP-HM04-P0SAA-131004 | HVAC SYSTEM_O&M MANUAL | FI | 2023-05-19 |  | 기계기술팀(HVAC) | 김재환 |  |  |  |  | HVAC System | CCPP | Plant | HVAC | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-581 | 2023-05-25 | 0 | CRS-GUP-DHI-DT-23-2005 | 2023-06-15 | NC | DE-GUP-DT-E-23-581 | 2023-05-25 | 0 | CRS-GUP-DHI-DT-23-2005 | 2023-06-15 | NC
| GUP | HM05 | P1 | SAL | 131021 |  | GUP-HM05-P1SAL-131021 | HVAC SYSTEM_MAINTENANCE WORKSHOP AND STORE BUILDING_LOAD CALCULATION | FA | 2023-01-04 | 2023-03-29 | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | Workshop Building | HVAC | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-984 | 2023-12-12 | 1 | 자체 CRS 개정 후 제출 | 2023-12-11 | N/A | DE-GUP-DT-E-22-1054 | 2022-12-08 | A | CRS-GUP-DHI-DT-22-1320 | 2022-12-22 | RC | DE-GUP-DT-E-23-329 | 2023-03-20 | B | CRS-GUP-DHI-DT-23-1802 | 2023-04-04 | RC | DE-GUP-DT-E-23-452 | 2023-04-13 | C | CRS-GUP-DHI-DT-23-1903 | 2023-05-05 | RC | DE-GUP-DT-E-23-547 | 2023-05-12 | D | CRS-GUP-DHI-DT-23-1971 | 2023-06-01 | AA | DE-GUP-DT-E-23-603 | 2023-06-02 | 0 | 자체 CRS 개정 후 제출 | 2023-12-11 | N/A | DE-GUP-DT-E-23-984 | 2023-12-12 | 1
| GUP | HM01 | P1 | SAL | 131022 |  | GUP-HM01-P1SAL-131022 | HVAC SYSTEM_MAINTENANCE WORKSHOP AND STORE BUILDING_AIR FLOW DIAGRAM | FI | 2023-01-04 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | Workshop Building | HVAC | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-984 | 2023-12-12 | 5 | 자체 CRS 개정 후 제출 | 2023-12-11 | N/A | DE-GUP-DT-E-22-1054 | 2022-12-08 | 0 | CRS-GUP-DHI-DT-22-1320 | 2022-12-22 | RC | DE-GUP-DT-E-23-329 | 2023-03-20 | 1 | CRS-GUP-DHI-DT-23-1802 | 2023-04-04 | RC | DE-GUP-DT-E-23-452 | 2023-04-13 | 2 | CRS-GUP-DHI-DT-23-1903 | 2023-05-05 | RC | DE-GUP-DT-E-23-547 | 2023-05-12 | 3 | CRS-GUP-DHI-DT-23-1971 | 2023-06-01 | NC | DE-GUP-DT-E-23-603 | 2023-06-02 | 4 | 자체 CRS 개정 후 제출 | 2023-12-11 | N/A | DE-GUP-DT-E-23-984 | 2023-12-12 | 5
| GUP | HM01 | P1 | SAL | 131023 |  | GUP-HM01-P1SAL-131023 | HVAC SYSTEM_MAINTENANCE WORKSHOP AND STORE BUILDING_DUCT & PIPING PLAN | FI | 2023-01-04 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | Workshop Building | HVAC | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-984 | 2023-12-12 | 5 | 자체 CRS 개정 후 제출 | 2023-12-11 | N/A | DE-GUP-DT-E-22-1054 | 2022-12-08 | 0 | CRS-GUP-DHI-DT-22-1320 | 2022-12-22 | RC | DE-GUP-DT-E-23-329 | 2023-03-20 | 1 | CRS-GUP-DHI-DT-23-1802 | 2023-04-04 | RC | DE-GUP-DT-E-23-452 | 2023-04-13 | 2 | CRS-GUP-DHI-DT-23-1903 | 2023-05-05 | RC | DE-GUP-DT-E-23-547 | 2023-05-12 | 3 | CRS-GUP-DHI-DT-23-1971 | 2023-06-01 | NC | DE-GUP-DT-E-23-603 | 2023-06-02 | 4 | 자체 CRS 개정 후 제출 | 2023-12-11 | N/A | DE-GUP-DT-E-23-984 | 2023-12-12 | 5
| GUP | HM04 | P1 | SAL | 131024 |  | GUP-HM04-P1SAL-131024 | HVAC SYSTEM_MAINTENANCE WORKSHOP AND STORE BUILDING_EQUIPMENT SCHEDULE | FI | 2023-01-04 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | Workshop Building | HVAC | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-984 | 2023-12-12 | 5 | 자체 CRS 개정 후 제출 | 2023-12-11 | N/A | DE-GUP-DT-E-22-1054 | 2022-12-08 | 0 | CRS-GUP-DHI-DT-22-1320 | 2022-12-22 | RC | DE-GUP-DT-E-23-329 | 2023-03-20 | 1 | CRS-GUP-DHI-DT-23-1802 | 2023-04-04 | RC | DE-GUP-DT-E-23-452 | 2023-04-13 | 2 | CRS-GUP-DHI-DT-23-1903 | 2023-05-05 | RC | DE-GUP-DT-E-23-547 | 2023-05-12 | 3 | CRS-GUP-DHI-DT-23-1971 | 2023-06-01 | NC | DE-GUP-DT-E-23-603 | 2023-06-02 | 4 | 자체 CRS 개정 후 제출 | 2023-12-11 | N/A | DE-GUP-DT-E-23-984 | 2023-12-12 | 5
| GUP | HM05 | P1 | SAK | 131031 |  | GUP-HM05-P1SAK-131031 | HVAC SYSTEM_WT & WWT BLDG & SHELTER_LOAD CALCULATION | FA | 2021-11-29 | 2022-10-21 | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | WT & WWT Building | HVAC | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-24-191 | 2024-07-25 | 3 | 자체 CRS 개정 후 제출 | 2024-07-24 | N/A | DHI-GUP-DT-21-136 | 2021-11-30 | A | CRS-GUP-DHI-DT-21-098 | 2021-12-27 | RC | DE-GUP-DT-E-22-292 | 2022-06-13 | B | CRS-GUP-DHI-DT-22-493 | 2022-07-06 | RC | DE-GUP-DT-E-22-834 | 2022-10-21 | C | CRS-GUP-DHI-DT-22-1106 | 2022-11-21 | AC | DE-GUP-DT-E-22-1014 | 2022-11-30 | 0(CP) | CRS-GUP-DHI-DT-22-1281 | 2022-12-21 | AA | DE-GUP-DT-E-23-402 | 2023-03-30 | 1 | 자체 CRS 개정 후 제출 | 2023-12-11 | N/A | DE-GUP-DT-E-23-985 | 2023-12-12 | 2 | 자체 CRS 개정 후 제출 | 2024-07-24 | N/A | DE-GUP-DT-E-24-191 | 2024-07-25 | 3
| GUP | HM01 | P1 | SAK | 131032 |  | GUP-HM01-P1SAK-131032 | HVAC SYSTEM_WT & WWT BLDG & SHELTER_AIR FLOW DIAGRAM | FI | 2021-11-29 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | WT & WWT Building | HVAC | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-24-191 | 2024-07-25 | 6 | 자체 CRS 개정 후 제출 | 2024-07-24 | N/A | DHI-GUP-DT-21-136 | 2021-11-30 | 0 | CRS-GUP-DHI-DT-21-098 | 2021-12-27 | NC | DE-GUP-DT-E-22-292 | 2022-06-13 | 1 | CRS-GUP-DHI-DT-22-493 | 2022-07-06 | NC | DE-GUP-DT-E-22-834 | 2022-10-21 | 2 | CRS-GUP-DHI-DT-22-1011 | 2022-11-13 | NC | DE-GUP-DT-E-22-1014 | 2022-11-30 | 3 | CRS-GUP-DHI-DT-22-1281 | 2022-12-21 | NC | DE-GUP-DT-E-23-402 | 2023-03-30 | 4 | 자체 CRS 개정 후 제출 | 2023-12-11 | N/A | DE-GUP-DT-E-23-985 | 2023-12-12 | 5 | 자체 CRS 개정 후 제출 | 2024-07-24 | N/A | DE-GUP-DT-E-24-191 | 2024-07-25 | 6
| GUP | HM01 | P1 | SAK | 131033 |  | GUP-HM01-P1SAK-131033 | HVAC SYSTEM_WT & WWT BLDG & SHELTER_DUCT & PIPING PLAN | FI | 2021-11-29 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | WT & WWT Building | HVAC | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-24-191 | 2024-07-25 | 6 | 자체 CRS 개정 후 제출 | 2024-07-24 | N/A | DHI-GUP-DT-21-136 | 2021-11-30 | 0 | CRS-GUP-DHI-DT-21-098 | 2021-12-27 | NC | DE-GUP-DT-E-22-292 | 2022-06-13 | 1 | CRS-GUP-DHI-DT-22-493 | 2022-07-06 | NC | DE-GUP-DT-E-22-834 | 2022-10-21 | 2 | CRS-GUP-DHI-DT-22-1011 | 2022-11-13 | NC | DE-GUP-DT-E-22-1014 | 2022-11-30 | 3 | CRS-GUP-DHI-DT-22-1281 | 2022-12-21 | NC | DE-GUP-DT-E-23-402 | 2023-03-30 | 4 | 자체 CRS 개정 후 제출 | 2023-12-11 | N/A | DE-GUP-DT-E-23-985 | 2023-12-12 | 5 | 자체 CRS 개정 후 제출 | 2024-07-24 | N/A | DE-GUP-DT-E-24-191 | 2024-07-25 | 6
| GUP | HM04 | P1 | SAK | 131034 |  | GUP-HM04-P1SAK-131034 | HVAC SYSTEM_WT & WWT BLDG & SHELTER_EQUIPMENT SCHEDULE | FI | 2021-11-29 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | WT & WWT Building | HVAC | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-24-191 | 2024-07-25 | 6 | 자체 CRS 개정 후 제출 | 2024-07-24 | N/A | DHI-GUP-DT-21-136 | 2021-11-30 | 0 | CRS-GUP-DHI-DT-21-098 | 2021-12-27 | NC | DE-GUP-DT-E-22-292 | 2022-06-13 | 1 | CRS-GUP-DHI-DT-22-493 | 2022-07-06 | NC | DE-GUP-DT-E-22-834 | 2022-10-21 | 2 | CRS-GUP-DHI-DT-22-1011 | 2022-11-13 | NC | DE-GUP-DT-E-22-1014 | 2022-11-30 | 3 | CRS-GUP-DHI-DT-22-1281 | 2022-12-21 | NC | DE-GUP-DT-E-23-402 | 2023-03-30 | 4 | 자체 CRS 개정 후 제출 | 2023-12-11 | N/A | DE-GUP-DT-E-23-985 | 2023-12-12 | 5 | 자체 CRS 개정 후 제출 | 2024-07-24 | N/A | DE-GUP-DT-E-24-191 | 2024-07-25 | 6
| GUP | HM05 | P1 | SAN | 131121 |  | GUP-HM05-P1SAN-131121 | HVAC SYSTEM_HRSG#1 BUILDING_LOAD CALCULATION | FA | 2022-03-04 | 2022-07-29 | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | HRSG#1 Building | HVAC | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-718 | 2022-09-29 | 0 | CRS-GUP-DHI-DT-22-1122 | 2022-11-23 | AA | DHI-GUP-DT-22-091 | 2022-02-25 | A | CRS-GUP-DHI-DT-22-254 | 2022-03-16 | RC | DE-GUP-DT-E-22-302 | 2022-06-16 | B | CRS-GUP-DHI-DT-22-497 | 2022-07-06 | RC | DE-GUP-DT-E-22-647 | 2022-09-08 | C | CRS-GUP-DHI-DT-22-828 | 2022-09-22 | AA | DE-GUP-DT-E-22-718 | 2022-09-29 | 0 | CRS-GUP-DHI-DT-22-1122 | 2022-11-23 | AA
| GUP | HM01 | P1 | SAN | 131122 |  | GUP-HM01-P1SAN-131122 | HVAC SYSTEM_HRSG#1 BUILDING_AIR FLOW DIAGRAM | FI | 2022-03-04 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | HRSG#1 Building | HVAC | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-718 | 2022-09-29 | 2 | CRS-GUP-DHI-DT-22-993 | 2022-11-13 | NC | DHI-GUP-DT-22-091 | 2022-02-25 | 0 | CRS-GUP-DHI-DT-22-254 | 2022-03-16 | NC | DE-GUP-DT-E-22-647 | 2022-09-08 | 1 | CRS-GUP-DHI-DT-22-828 | 2022-09-22 | NC | DE-GUP-DT-E-22-718 | 2022-09-29 | 2 | CRS-GUP-DHI-DT-22-993 | 2022-11-13 | NC
| GUP | HM01 | P1 | SAN | 131123 |  | GUP-HM01-P1SAN-131123 | HVAC SYSTEM_HRSG#1 BUILDING_DUCT & PIPING PLAN | FI | 2022-03-04 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | HRSG#1 Building | HVAC | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-718 | 2022-09-29 | 2 | CRS-GUP-DHI-DT-22-993 | 2022-11-13 | NC | DHI-GUP-DT-22-091 | 2022-02-25 | 0 | CRS-GUP-DHI-DT-22-254 | 2022-03-16 | NC | DE-GUP-DT-E-22-647 | 2022-09-08 | 1 | CRS-GUP-DHI-DT-22-828 | 2022-09-22 | NC | DE-GUP-DT-E-22-718 | 2022-09-29 | 2 | CRS-GUP-DHI-DT-22-993 | 2022-11-13 | NC
| GUP | HM04 | P1 | SAN | 131124 |  | GUP-HM04-P1SAN-131124 | HVAC SYSTEM_HRSG#1 BUILDING_EQUIPMENT SCHEDULE | FI | 2022-03-04 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | HRSG#1 Building | HVAC | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-718 | 2022-09-29 | 2 | CRS-GUP-DHI-DT-22-993 | 2022-11-13 | NC | DHI-GUP-DT-22-091 | 2022-02-25 | 0 | CRS-GUP-DHI-DT-22-254 | 2022-03-16 | NC | DE-GUP-DT-E-22-647 | 2022-09-08 | 1 | CRS-GUP-DHI-DT-22-828 | 2022-09-22 | NC | DE-GUP-DT-E-22-718 | 2022-09-29 | 2 | CRS-GUP-DHI-DT-22-993 | 2022-11-13 | NC
| GUP | HM05 | P1 | SAN | 131131 |  | GUP-HM05-P1SAN-131131 | HVAC SYSTEM_HRSG#2 BUILDING_LOAD CALCULATION | FA | 2022-03-04 | 2022-07-29 | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | HRSG#2 Building | HVAC | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-719 | 2022-09-29 | 0 | CRS-GUP-DHI-DT-22-1123 | 2022-11-23 | AA | DHI-GUP-DT-22-092 | 2022-02-25 | A | CRS-GUP-DHI-DT-22-255 | 2022-03-16 | RC | DE-GUP-DT-E-22-305 | 2022-06-16 | B | CRS-GUP-DHI-DT-22-499 | 2022-07-06 | RC | DE-GUP-DT-E-22-648 | 2022-09-08 | C | CRS-GUP-DHI-DT-22-829 | 2022-09-22 | AA | DE-GUP-DT-E-22-719 | 2022-09-29 | 0 | CRS-GUP-DHI-DT-22-1123 | 2022-11-23 | AA
| GUP | HM01 | P1 | SAN | 131132 |  | GUP-HM01-P1SAN-131132 | HVAC SYSTEM_HRSG#2 BUILDING_AIR FLOW DIAGRAM | FI | 2022-03-04 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | HRSG#2 Building | HVAC | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-719 | 2022-09-29 | 2 | CRS-GUP-DHI-DT-22-994 | 2022-11-13 | NC | DHI-GUP-DT-22-092 | 2022-02-25 | 0 | CRS-GUP-DHI-DT-22-255 | 2022-03-16 | NC | DE-GUP-DT-E-22-648 | 2022-09-08 | 1 | CRS-GUP-DHI-DT-22-829 | 2022-09-22 | NC | DE-GUP-DT-E-22-719 | 2022-09-29 | 2 | CRS-GUP-DHI-DT-22-994 | 2022-11-13 | NC
| GUP | HM01 | P1 | SAN | 131133 |  | GUP-HM01-P1SAN-131133 | HVAC SYSTEM_HRSG#2 BUILDING_DUCT & PIPING PLAN | FI | 2022-03-04 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | HRSG#2 Building | HVAC | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-719 | 2022-09-29 | 2 | CRS-GUP-DHI-DT-22-994 | 2022-11-13 | NC | DHI-GUP-DT-22-092 | 2022-02-25 | 0 | CRS-GUP-DHI-DT-22-255 | 2022-03-16 | NC | DE-GUP-DT-E-22-648 | 2022-09-08 | 1 | CRS-GUP-DHI-DT-22-829 | 2022-09-22 | NC | DE-GUP-DT-E-22-719 | 2022-09-29 | 2 | CRS-GUP-DHI-DT-22-994 | 2022-11-13 | NC
| GUP | HM04 | P1 | SAN | 131134 |  | GUP-HM04-P1SAN-131134 | HVAC SYSTEM_HRSG#2 BUILDING_EQUIPMENT SCHEDULE | FI | 2022-03-04 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | HRSG#2 Building | HVAC | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-719 | 2022-09-29 | 2 | CRS-GUP-DHI-DT-22-994 | 2022-11-13 | NC | DHI-GUP-DT-22-092 | 2022-02-25 | 0 | CRS-GUP-DHI-DT-22-255 | 2022-03-16 | NC | DE-GUP-DT-E-22-648 | 2022-09-08 | 1 | CRS-GUP-DHI-DT-22-829 | 2022-09-22 | NC | DE-GUP-DT-E-22-719 | 2022-09-29 | 2 | CRS-GUP-DHI-DT-22-994 | 2022-11-13 | NC
| GUP | HM05 | P1 | SAN | 131141 |  | GUP-HM05-P1SAN-131141 | HVAC SYSTEM_HRSG#3 BUILDING_LOAD CALCULATION | FA | 2022-03-04 | 2022-07-29 | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | HRSG#3 Building | HVAC | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-1003 | 2023-12-20 | 1 | CRS-GUP-DHI-DT-22-1133 | 2022-11-23 | AA | DHI-GUP-DT-22-093 | 2022-02-25 | A | CRS-GUP-DHI-DT-22-256 | 2022-03-16 | RC | DE-GUP-DT-E-22-303 | 2022-06-16 | B | CRS-GUP-DHI-DT-22-498 | 2022-07-06 | RC | DE-GUP-DT-E-22-649 | 2022-09-08 | C | CRS-GUP-DHI-DT-22-876 | 2022-10-09 | AC | DE-GUP-DT-E-22-788 | 2022-10-12 | 0(CP) | CRS-GUP-DHI-DT-22-1133 | 2022-11-23 | AA | DE-GUP-DT-E-23-1003 | 2023-12-20 | 1
| GUP | HM01 | P1 | SAN | 131142 |  | GUP-HM01-P1SAN-131142 | HVAC SYSTEM_HRSG#3 BUILDING_AIR FLOW DIAGRAM | FI | 2022-03-04 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | HRSG#3 Building | HVAC | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-788 | 2022-10-12 | 2 | CRS-GUP-DHI-DT-22-1003 | 2022-11-13 | NC | DHI-GUP-DT-22-093 | 2022-02-25 | 0 | CRS-GUP-DHI-DT-22-256 | 2022-03-16 | NC | DE-GUP-DT-E-22-649 | 2022-09-08 | 1 | CRS-GUP-DHI-DT-22-876 | 2022-10-09 | NC | DE-GUP-DT-E-22-788 | 2022-10-12 | 2 | CRS-GUP-DHI-DT-22-1003 | 2022-11-13 | NC
| GUP | HM01 | P1 | SAN | 131143 |  | GUP-HM01-P1SAN-131143 | HVAC SYSTEM_HRSG#3 BUILDING_DUCT & PIPING PLAN | FI | 2022-03-04 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | HRSG#3 Building | HVAC | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-788 | 2022-10-12 | 2 | CRS-GUP-DHI-DT-22-1003 | 2022-11-13 | NC | DHI-GUP-DT-22-093 | 2022-02-25 | 0 | CRS-GUP-DHI-DT-22-256 | 2022-03-16 | NC | DE-GUP-DT-E-22-649 | 2022-09-08 | 1 | CRS-GUP-DHI-DT-22-876 | 2022-10-09 | NC | DE-GUP-DT-E-22-788 | 2022-10-12 | 2 | CRS-GUP-DHI-DT-22-1003 | 2022-11-13 | NC
| GUP | HM04 | P1 | SAN | 131144 |  | GUP-HM04-P1SAN-131144 | HVAC SYSTEM_HRSG#3 BUILDING_EQUIPMENT SCHEDULE | FI | 2022-03-04 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | HRSG#3 Building | HVAC | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-788 | 2022-10-12 | 2 | CRS-GUP-DHI-DT-22-1003 | 2022-11-13 | NC | DHI-GUP-DT-22-093 | 2022-02-25 | 0 | CRS-GUP-DHI-DT-22-256 | 2022-03-16 | NC | DE-GUP-DT-E-22-649 | 2022-09-08 | 1 | CRS-GUP-DHI-DT-22-876 | 2022-10-09 | NC | DE-GUP-DT-E-22-788 | 2022-10-12 | 2 | CRS-GUP-DHI-DT-22-1003 | 2022-11-13 | NC
| GUP | HM05 | P1 | SAH | 131041 |  | GUP-HM05-P1SAH-131041 | HVAC SYSTEM_STEAM TURBINE BUILDING_LOAD CALCULATION | FA | 2022-02-20 | 2022-09-21 | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | ST Building | HVAC | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-305 | 2023-03-14 | 1 | CRS-GUP-DHI-DT-22-1768 | 2023-03-22 | AA | DHI-GUP-DT-22-001 | 2022-01-03 | A | CRS-GUP-DHI-DT-21-166 | 2022-01-19 | RC | DHI-GUP-DT-22-073 | 2022-02-16 | B | CRS-GUP-DHI-DT-22-234 | 2022-03-07 | AC | DE-GUP-DT-E-22-752 | 2022-10-04 | 0(CP) | CRS-GUP-DHI-DT-22-1128 | 2022-11-23 | AA | DE-GUP-DT-E-23-305 | 2023-03-14 | 1 | CRS-GUP-DHI-DT-22-1768 | 2023-03-22 | AA
| GUP | HM01 | P1 | SAH | 131042 |  | GUP-HM01-P1SAH-131042 | HVAC SYSTEM_STEAM TURBINE BUILDING_AIR FLOW DIAGRAM | FI | 2022-02-20 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | ST Building | HVAC | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-305 | 2023-03-14 | 3 | CRS-GUP-DHI-DT-22-1768 | 2023-03-22 | NC | DHI-GUP-DT-22-001 | 2022-01-03 | 0 | CRS-GUP-DHI-DT-21-166 | 2022-01-19 | NC | DHI-GUP-DT-22-073 | 2022-02-16 | 1 | CRS-GUP-DHI-DT-22-234 | 2022-03-07 | NC | DE-GUP-DT-E-22-752 | 2022-10-04 | 2 | CRS-GUP-DHI-DT-22-997 | 2022-11-13 | NC | DE-GUP-DT-E-23-305 | 2023-03-14 | 3 | CRS-GUP-DHI-DT-22-1768 | 2023-03-22 | NC
| GUP | HM01 | P1 | SAH | 131043 |  | GUP-HM01-P1SAH-131043 | HVAC SYSTEM_STEAM TURBINE BUILDING_DUCT & PIPING PLAN | FI | 2022-02-20 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | ST Building | HVAC | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-305 | 2023-03-14 | 3 | CRS-GUP-DHI-DT-22-1768 | 2023-03-22 | NC | DHI-GUP-DT-22-001 | 2022-01-03 | 0 | CRS-GUP-DHI-DT-21-166 | 2022-01-19 | RC | DHI-GUP-DT-22-073 | 2022-02-16 | 1 | CRS-GUP-DHI-DT-22-234 | 2022-03-07 | NC | DE-GUP-DT-E-22-752 | 2022-10-04 | 2 | CRS-GUP-DHI-DT-22-997 | 2022-11-13 | NC | DE-GUP-DT-E-23-305 | 2023-03-14 | 3 | CRS-GUP-DHI-DT-22-1768 | 2023-03-22 | NC
| GUP | HM04 | P1 | SAH | 131044 |  | GUP-HM04-P1SAH-131044 | HVAC SYSTEM_STEAM TURBINE BUILDING_EQUIPMENT SCHEDULE | FI | 2022-02-20 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | ST Building | HVAC | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-305 | 2023-03-14 | 3 | CRS-GUP-DHI-DT-22-1768 | 2023-03-22 | NC | DHI-GUP-DT-22-001 | 2022-01-03 | 0 | CRS-GUP-DHI-DT-21-166 | 2022-01-19 | NC | DHI-GUP-DT-22-073 | 2022-02-16 | 1 | CRS-GUP-DHI-DT-22-234 | 2022-03-07 | NC | DE-GUP-DT-E-22-752 | 2022-10-04 | 2 | CRS-GUP-DHI-DT-22-997 | 2022-11-13 | NC | DE-GUP-DT-E-23-305 | 2023-03-14 | 3 | CRS-GUP-DHI-DT-22-1768 | 2023-03-22 | NC
| GUP | HM05 | P1 | SAF | 131151 |  | GUP-HM05-P1SAF-131151 | HVAC SYSTEM_GAS TURBINE BUILDING_LOAD CALCULATION | FA | 2021-12-28 | 2022-06-30 | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | GT Building | HVAC | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-304 | 2023-03-14 | 1 | CRS-GUP-DHI-DT-23-1780 | 2023-03-27 | AA | DHI-GUP-DT-21-200 | 2021-12-27 | A | CRS-GUP-DHI-DT-21-155 | 2022-01-12 | RC | DHI-GUP-DT-22-072 | 2022-02-16 | B | CRS-GUP-DHI-DT-22-233 | 2022-03-07 | AC | DE-GUP-DT-E-22-293 | 2022-06-13 | 0(CP) | CRS 미접수 |  |  | DE-GUP-DT-E-23-304 | 2023-03-14 | 1 | CRS-GUP-DHI-DT-23-1780 | 2023-03-27 | AA
| GUP | HM01 | P1 | SAF | 131152 |  | GUP-HM01-P1SAF-131152 | HVAC SYSTEM_GAS TURBINE BUILDING_AIR FLOW DIAGRAM | FI | 2021-12-28 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | GT Building | HVAC | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-304 | 2023-03-14 | 2 | CRS-GUP-DHI-DT-23-1780 | 2023-03-27 | NC | DHI-GUP-DT-21-200 | 2021-12-27 | 0 | CRS-GUP-DHI-DT-21-155 | 2022-01-12 | NC | DHI-GUP-DT-22-072 | 2022-02-16 | 1 | CRS-GUP-DHI-DT-22-233 | 2022-03-07 | NC | DE-GUP-DT-E-23-304 | 2023-03-14 | 2 | CRS-GUP-DHI-DT-23-1780 | 2023-03-27 | NC
| GUP | HM01 | P1 | SAF | 131153 |  | GUP-HM01-P1SAF-131153 | HVAC SYSTEM_GAS TURBINE BUILDING_DUCT & PIPING PLAN | FI | 2021-12-28 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | GT Building | HVAC | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-304 | 2023-03-14 | 2 | CRS-GUP-DHI-DT-23-1780 | 2023-03-27 | NC | DHI-GUP-DT-21-200 | 2021-12-27 | 0 | CRS-GUP-DHI-DT-21-155 | 2022-01-12 | RC | DHI-GUP-DT-22-072 | 2022-02-16 | 1 | CRS-GUP-DHI-DT-22-233 | 2022-03-07 | NC | DE-GUP-DT-E-23-304 | 2023-03-14 | 2 | CRS-GUP-DHI-DT-23-1780 | 2023-03-27 | NC
| GUP | HM04 | P1 | SAF | 131154 |  | GUP-HM04-P1SAF-131154 | HVAC SYSTEM_GAS TURBINE BUILDING_EQUIPMENT SCHEDULE | FI | 2021-12-28 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | GT Building | HVAC | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-304 | 2023-03-14 | 2 | CRS-GUP-DHI-DT-23-1780 | 2023-03-27 | NC | DHI-GUP-DT-21-200 | 2021-12-27 | 0 | CRS-GUP-DHI-DT-21-155 | 2022-01-12 | NC | DHI-GUP-DT-22-072 | 2022-02-16 | 1 | CRS-GUP-DHI-DT-22-233 | 2022-03-07 | NC | DE-GUP-DT-E-23-304 | 2023-03-14 | 2 | CRS-GUP-DHI-DT-23-1780 | 2023-03-27 | NC
| GUP | HM05 | P1 | SAJ | 131051 |  | GUP-HM05-P1SAJ-131051 | HVAC SYSTEM_BESS ELECTRICAL & CONTROL BUILDING_LOAD CALCULATION | FA | 2022-10-14 | 2023-01-11 | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | BESS Building | HVAC | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-987 | 2023-12-12 | 1 | CRS-GUP-DHI-DT-23-1855 | 2023-04-19 | AA | DE-GUP-DT-E-22-761 | 2022-10-06 | A | CRS-GUP-DHI-DT-22-1156 | 2022-11-24 | RC | DE-GUP-DT-E-22-1227 | 2023-01-05 | B | CRS-GUP-DHI-DT-22-1455 | 2023-02-04 | RC | DE-GUP-DT-E-23-310 | 2023-03-15 | C | CRS-GUP-DHI-DT-23-1769 | 2023-03-22 | AC | DE-GUP-DT-E-23-400 | 2023-03-30 | 0(CP) | CRS-GUP-DHI-DT-23-1855 | 2023-04-19 | AA | DE-GUP-DT-E-23-987 | 2023-12-12 | 1
| GUP | HM01 | P1 | SAJ | 131052 |  | GUP-HM01-P1SAJ-131052 | HVAC SYSTEM_BESS ELECTRICAL & CONTROL BUILDING_AIR FLOW DIAGRAM | FI | 2022-10-14 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | BESS Building | HVAC | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-987 | 2023-12-12 | 3 | CRS-GUP-DHI-DT-23-1769 | 2023-03-22 | NC | DE-GUP-DT-E-22-761 | 2022-10-06 | 0 | CRS-GUP-DHI-DT-22-1156 | 2022-11-24 | RC | DE-GUP-DT-E-22-1227 | 2023-01-05 | 1 | CRS-GUP-DHI-DT-22-1455 | 2023-02-04 | NC | DE-GUP-DT-E-23-310 | 2023-03-15 | 2 | CRS-GUP-DHI-DT-23-1769 | 2023-03-22 | NC | DE-GUP-DT-E-23-987 | 2023-12-12 | 3
| GUP | HM01 | P1 | SAJ | 131053 |  | GUP-HM01-P1SAJ-131053 | HVAC SYSTEM_BESS ELECTRICAL & CONTROL BUILDING_DUCT & PIPING PLAN | FI | 2022-10-14 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | BESS Building | HVAC | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-987 | 2023-12-12 | 3 | CRS-GUP-DHI-DT-23-1769 | 2023-03-22 | NC | DE-GUP-DT-E-22-761 | 2022-10-06 | 0 | CRS-GUP-DHI-DT-22-1156 | 2022-11-24 | RC | DE-GUP-DT-E-22-1227 | 2023-01-05 | 1 | CRS-GUP-DHI-DT-22-1455 | 2023-02-04 | NC | DE-GUP-DT-E-23-310 | 2023-03-15 | 2 | CRS-GUP-DHI-DT-23-1769 | 2023-03-22 | NC | DE-GUP-DT-E-23-987 | 2023-12-12 | 3
| GUP | HM04 | P1 | SAJ | 131054 |  | GUP-HM04-P1SAJ-131054 | HVAC SYSTEM_BESS ELECTRICAL & CONTROL BUILDING_EQUIPMENT SCHEDULE | FI | 2022-10-14 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | BESS Building | HVAC | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-987 | 2023-12-12 | 3 | CRS-GUP-DHI-DT-23-1769 | 2023-03-22 | NC | DE-GUP-DT-E-22-761 | 2022-10-06 | 0 | CRS-GUP-DHI-DT-22-1156 | 2022-11-24 | NC | DE-GUP-DT-E-22-1227 | 2023-01-05 | 1 | CRS-GUP-DHI-DT-22-1455 | 2023-02-04 | NC | DE-GUP-DT-E-23-310 | 2023-03-15 | 2 | CRS-GUP-DHI-DT-23-1769 | 2023-03-22 | NC | DE-GUP-DT-E-23-987 | 2023-12-12 | 3
| GUP | HM05 | P1 | SAD | 131061 |  | GUP-HM05-P1SAD-131061 | HVAC SYSTEM_SWITCHYARD CONTROL BUILDING_LOAD CALCULATION | FA | 2022-02-10 | 2022-11-23 | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | SWYD Building | HVAC | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-24-192 | 2024-07-25 | 2 | 자체 CRS 개정 후 제출 | 2024-07-24 | N/A | DHI-GUP-DT-21-090 | 2021-11-03 | A | CRS-GUP-DHI-DT-21-075 | 2021-11-30 | RC | DHI-GUP-DT-21-150 | 2021-12-07 | B | CRS-GUP-DHI-DT-21-143 | 2022-01-12 | AA | DE-GUP-DT-E-22-632 | 2022-09-07 | 0(CP) | CRS-GUP-DHI-DT-22-872 | 2022-10-09 | AA | DE-GUP-DT-E-23-931 | 2023-11-23 | 1 | 자체 CRS 개정 후 제출 | 2024-07-24 | N/A | DE-GUP-DT-E-24-192 | 2024-07-25 | 2
| GUP | HM01 | P1 | SAD | 131062 |  | GUP-HM01-P1SAD-131062 | HVAC SYSTEM_SWITCHYARD CONTROL BUILDING_AIR FLOW DIAGRAM | FI | 2022-02-10 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | SWYD Building | HVAC | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-24-192 | 2024-07-25 | 3 | CRS-GUP-DHI-DT-22-872 | 2022-10-09 | NC | DHI-GUP-DT-21-090 | 2021-11-03 | 0 | CRS-GUP-DHI-DT-21-075 | 2021-11-30 | RC | DHI-GUP-DT-21-150 | 2021-12-07 | 1 | CRS-GUP-DHI-DT-21-143 | 2022-01-12 | NC | DE-GUP-DT-E-22-632 | 2022-09-07 | 2 | CRS-GUP-DHI-DT-22-872 | 2022-10-09 | NC | DE-GUP-DT-E-24-192 | 2024-07-25 | 3
| GUP | HM01 | P1 | SAD | 131063 |  | GUP-HM01-P1SAD-131063 | HVAC SYSTEM_SWITCHYARD CONTROL BUILDING_DUCT & PIPING PLAN | FI | 2022-02-10 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | SWYD Building | HVAC | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-24-192 | 2024-07-25 | 3 | CRS-GUP-DHI-DT-22-872 | 2022-10-09 | NC | DHI-GUP-DT-21-090 | 2021-11-03 | 0 | CRS-GUP-DHI-DT-21-075 | 2021-11-30 | RC | DHI-GUP-DT-21-150 | 2021-12-07 | 1 | CRS-GUP-DHI-DT-21-143 | 2022-01-12 | NC | DE-GUP-DT-E-22-632 | 2022-09-07 | 2 | CRS-GUP-DHI-DT-22-872 | 2022-10-09 | NC | DE-GUP-DT-E-24-192 | 2024-07-25 | 3
| GUP | HM04 | P1 | SAD | 131064 |  | GUP-HM04-P1SAD-131064 | HVAC SYSTEM_SWITCHYARD CONTROL BUILDING_EQUIPMENT SCHEDULE | FI | 2022-02-10 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | SWYD Building | HVAC | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-24-192 | 2024-07-25 | 3 | CRS-GUP-DHI-DT-22-872 | 2022-10-09 | NC | DHI-GUP-DT-21-090 | 2021-11-03 | 0 | CRS-GUP-DHI-DT-21-075 | 2021-11-30 | RC | DHI-GUP-DT-21-150 | 2021-12-07 | 1 | CRS-GUP-DHI-DT-21-143 | 2022-01-12 | NC | DE-GUP-DT-E-22-632 | 2022-09-07 | 2 | CRS-GUP-DHI-DT-22-872 | 2022-10-09 | NC | DE-GUP-DT-E-24-192 | 2024-07-25 | 3
| GUP | HM05 | P1 | SAE | 131081 |  | GUP-HM05-P1SAE-131081 | HVAC SYSTEM_GATE HOUSE_LOAD CALCULATION | FA | 2022-09-14 | 2023-01-18 | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | Gate House | HVAC | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-345 | 2023-03-22 | 0 | CRS-GUP-DHI-DT-23-1827 | 2023-04-12 | AA | DE-GUP-DT-E-22-534 | 2022-08-23 | A | CRS-GUP-DHI-DT-22-731 | 2022-09-09 | RC | DE-GUP-DT-E-22-1061 | 2022-12-09 | B | CRS-GUP-DHI-DT-22-1322 | 2022-12-22 | RC | DE-GUP-DT-E-23-048 | 2023-01-19 | C | CRS-GUP-DHI-DT-23-1607 | 2023-03-02 | AA | DE-GUP-DT-E-23-345 | 2023-03-22 | 0 | CRS-GUP-DHI-DT-23-1827 | 2023-04-12 | AA
| GUP | HM01 | P1 | SAE | 131082 |  | GUP-HM01-P1SAE-131082 | HVAC SYSTEM_GATE HOUSE_AIR FLOW DIAGRAM | FI | 2022-09-14 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | Gate House | HVAC | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-345 | 2023-03-22 | 3 | CRS-GUP-DHI-DT-23-1827 | 2023-04-12 | NC | DE-GUP-DT-E-22-534 | 2022-08-23 | 0 | CRS-GUP-DHI-DT-22-731 | 2022-09-09 | NC | DE-GUP-DT-E-22-1061 | 2022-12-09 | 1 | CRS-GUP-DHI-DT-22-1322 | 2022-12-22 | NC | DE-GUP-DT-E-23-048 | 2023-01-19 | 2 | CRS-GUP-DHI-DT-23-1607 | 2023-03-02 | NC | DE-GUP-DT-E-23-345 | 2023-03-22 | 3 | CRS-GUP-DHI-DT-23-1827 | 2023-04-12 | NC
| GUP | HM01 | P1 | SAE | 131083 |  | GUP-HM01-P1SAE-131083 | HVAC SYSTEM_GATE HOUSE_DUCT & PIPING PLAN | FI | 2022-09-14 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | Gate House | HVAC | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-345 | 2023-03-22 | 3 | CRS-GUP-DHI-DT-23-1827 | 2023-04-12 | NC | DE-GUP-DT-E-22-534 | 2022-08-23 | 0 | CRS-GUP-DHI-DT-22-731 | 2022-09-09 | NC | DE-GUP-DT-E-22-1061 | 2022-12-09 | 1 | CRS-GUP-DHI-DT-22-1322 | 2022-12-22 | NC | DE-GUP-DT-E-23-048 | 2023-01-19 | 2 | CRS-GUP-DHI-DT-23-1607 | 2023-03-02 | NC | DE-GUP-DT-E-23-345 | 2023-03-22 | 3 | CRS-GUP-DHI-DT-23-1827 | 2023-04-12 | NC
| GUP | HM04 | P1 | SAE | 131084 |  | GUP-HM04-P1SAE-131084 | HVAC SYSTEM_GATE HOUSE_EQUIPMENT SCHEDULE | FI | 2022-09-14 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | Gate House | HVAC | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-345 | 2023-03-22 | 3 | CRS-GUP-DHI-DT-23-1827 | 2023-04-12 | NC | DE-GUP-DT-E-22-534 | 2022-08-23 | 0 | CRS-GUP-DHI-DT-22-731 | 2022-09-09 | NC | DE-GUP-DT-E-22-1061 | 2022-12-09 | 1 | CRS-GUP-DHI-DT-22-1322 | 2022-12-22 | NC | DE-GUP-DT-E-23-048 | 2023-01-19 | 2 | CRS-GUP-DHI-DT-23-1607 | 2023-03-02 | NC | DE-GUP-DT-E-23-345 | 2023-03-22 | 3 | CRS-GUP-DHI-DT-23-1827 | 2023-04-12 | NC
| GUP | HM05 | P1 | SAC | 131091 |  | GUP-HM05-P1SAC-131091 | HVAC SYSTEM_CONTROL & ELECTRICAL BUILDING_LOAD CALCULATION | FA | 2021-10-30 | 2022-03-30 | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | C&E Building | HVAC | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-24-193 | 2024-07-25 | 4 | 자체 CRS 개정 후 제출 | 2024-07-24 | N/A | DHI-GUP-DT-21-094 | 2021-11-09 | A | N/A | 2021-12-16 | N/A | DHI-GUP-DT-21-183 | 2021-12-17 | B | CRS-GUP-DHI-DT-21-133 | 2022-01-11 | RC | DHI-GUP-DT-22-097 | 2022-03-03 | C | CRS-GUP-DHI-DT-22-264 | 2022-03-25 | AC | DHI-GUP-DT-22-163 | 2022-04-11 | 0 | CRS-GUP-DHI-DT-22-327 | 2022-05-02 | AC | DE-GUP-DT-E-22-1003 | 2022-11-29 | 1(CP) | CRS-GUP-DHI-DT-22-1279 | 2022-12-21 | AA | DE-GUP-DT-E-23-553 | 2023-05-16 | 2 | 자체 CRS 개정 후 제출 | 2023-12-11 | N/A | DE-GUP-DT-E-23-983 | 2023-12-12 | 3 | 자체 CRS 개정 후 제출 | 2024-07-24 | N/A | DE-GUP-DT-E-24-193 | 2024-07-25 | 4
| GUP | HM01 | P1 | SAC | 131092 |  | GUP-HM01-P1SAC-131092 | HVAC SYSTEM_CONTROL & ELECTRICAL BUILDING_AIR FLOW DIAGRAM | FI | 2021-10-30 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | C&E Building | HVAC | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-24-193 | 2024-07-25 | 7 | 자체 CRS 개정 후 제출 | 2024-07-24 | N/A | DHI-GUP-DT-21-094 | 2021-11-09 | 0 | N/A | 2021-12-16 | N/A | DHI-GUP-DT-21-183 | 2021-12-17 | 1 | CRS-GUP-DHI-DT-21-133 | 2022-01-11 | NC | DHI-GUP-DT-22-097 | 2022-03-03 | 2 | CRS-GUP-DHI-DT-22-264 | 2022-03-25 | NC | DHI-GUP-DT-22-163 | 2022-04-11 | 3 | CRS-GUP-DHI-DT-22-327 | 2022-05-02 | NC | DE-GUP-DT-E-22-1003 | 2022-11-29 | 4 | CRS-GUP-DHI-DT-22-1279 | 2022-12-21 | NC | DE-GUP-DT-E-23-553 | 2023-05-16 | 5 | 자체 CRS 개정 후 제출 | 2023-12-11 | N/A | DE-GUP-DT-E-23-983 | 2023-12-12 | 6 | 자체 CRS 개정 후 제출 | 2024-07-24 | N/A | DE-GUP-DT-E-24-193 | 2024-07-25 | 7
| GUP | HM01 | P1 | SAC | 131093 |  | GUP-HM01-P1SAC-131093 | HVAC SYSTEM_CONTROL & ELECTRICAL BUILDING_DUCT & PIPING PLAN | FI | 2021-10-30 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | C&E Building | HVAC | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-24-193 | 2024-07-25 | 7 | 자체 CRS 개정 후 제출 | 2024-07-24 | N/A | DHI-GUP-DT-21-094 | 2021-11-09 | 0 | N/A | 2021-12-16 | N/A | DHI-GUP-DT-21-183 | 2021-12-17 | 1 | CRS-GUP-DHI-DT-21-133 | 2022-01-11 | NC | DHI-GUP-DT-22-097 | 2022-03-03 | 2 | CRS-GUP-DHI-DT-22-264 | 2022-03-25 | NC | DHI-GUP-DT-22-163 | 2022-04-11 | 3 | CRS-GUP-DHI-DT-22-327 | 2022-05-02 | NC | DE-GUP-DT-E-22-1003 | 2022-11-29 | 4 | CRS-GUP-DHI-DT-22-1279 | 2022-12-21 | NC | DE-GUP-DT-E-23-553 | 2023-05-16 | 5 | 자체 CRS 개정 후 제출 | 2023-12-11 | N/A | DE-GUP-DT-E-23-983 | 2023-12-12 | 6 | 자체 CRS 개정 후 제출 | 2024-07-24 | N/A | DE-GUP-DT-E-24-193 | 2024-07-25 | 7
| GUP | HM04 | P1 | SAC | 131094 |  | GUP-HM04-P1SAC-131094 | HVAC SYSTEM_CONTROL & ELECTRICAL BUILDING_EQUIPMENT SCHEDULE | FI | 2021-10-30 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | C&E Building | HVAC | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-24-193 | 2024-07-25 | 7 | 자체 CRS 개정 후 제출 | 2024-07-24 | N/A | DHI-GUP-DT-21-094 | 2021-11-09 | 0 | N/A | 2021-12-16 | N/A | DHI-GUP-DT-21-183 | 2021-12-17 | 1 | CRS-GUP-DHI-DT-21-133 | 2022-01-11 | NC | DHI-GUP-DT-22-097 | 2022-03-03 | 2 | CRS-GUP-DHI-DT-22-264 | 2022-03-25 | NC | DHI-GUP-DT-22-163 | 2022-04-11 | 3 | CRS-GUP-DHI-DT-22-327 | 2022-05-02 | NC | DE-GUP-DT-E-22-1003 | 2022-11-29 | 4 | CRS-GUP-DHI-DT-22-1279 | 2022-12-21 | NC | DE-GUP-DT-E-23-553 | 2023-05-16 | 5 | 자체 CRS 개정 후 제출 | 2023-12-11 | N/A | DE-GUP-DT-E-23-983 | 2023-12-12 | 6 | 자체 CRS 개정 후 제출 | 2024-07-24 | N/A | DE-GUP-DT-E-24-193 | 2024-07-25 | 7
| GUP | HM05 | P1 | SAM | 131161 |  | GUP-HM05-P1SAM-131161 | HVAC SYSTEM_FIRE PROTECTION PUMP BUILDING_LOAD CALCULATION | FA | 2022-07-11 | 2022-10-28 | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | Fire Protection Pump Building | HVAC | 2 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-380 | 2023-03-28 | 0 | CRS-GUP-DHI-DT-23-1609 | 2023-03-02 | AA | DHI-GUP-DT-22-179 | 2022-04-18 | A | CRS-GUP-DHI-DT-22-309 | 2022-04-25 | RR | DE-GUP-DT-E-22-849 | 2022-10-25 | B | CRS-GUP-DHI-DT-22-1178 | 2022-11-30 | RC | DE-GUP-DT-E-22-1092 | 2022-12-16 | C | CRS-GUP-DHI-DT-22-1382 | 2023-01-03 | RC | DE-GUP-DT-E-23-076 | 2023-01-26 | D | CRS-GUP-DHI-DT-23-1609 | 2023-03-02 | AA | DE-GUP-DT-E-23-380 | 2023-03-28 | 0
| GUP | HM01 | P1 | SAM | 131162 |  | GUP-HM01-P1SAM-131162 | HVAC SYSTEM_FIRE PROTECTION PUMP BUILDING_AIR FLOW DIAGRAM | FI | 2022-07-11 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | Fire Protection Pump Building | HVAC | 2 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-076 | 2023-01-26 | 3 | CRS-GUP-DHI-DT-23-1609 | 2023-03-02 | NC | DHI-GUP-DT-22-179 | 2022-04-18 | 0 | CRS-GUP-DHI-DT-22-309 | 2022-04-25 | RR | DE-GUP-DT-E-22-849 | 2022-10-25 | 1 | CRS-GUP-DHI-DT-22-1178 | 2022-11-30 | NC | DE-GUP-DT-E-22-1092 | 2022-12-16 | 2 | CRS-GUP-DHI-DT-22-1382 | 2023-01-03 | NC | DE-GUP-DT-E-23-076 | 2023-01-26 | 3 | CRS-GUP-DHI-DT-23-1609 | 2023-03-02 | NC
| GUP | HM01 | P1 | SAM | 131163 |  | GUP-HM01-P1SAM-131163 | HVAC SYSTEM_FIRE PROTECTION PUMP BUILDING_DUCT & PIPING PLAN | FI | 2022-07-11 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | Fire Protection Pump Building | HVAC | 2 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-076 | 2023-01-26 | 3 | CRS-GUP-DHI-DT-23-1609 | 2023-03-02 | NC | DHI-GUP-DT-22-179 | 2022-04-18 | 0 | CRS-GUP-DHI-DT-22-309 | 2022-04-25 | RR | DE-GUP-DT-E-22-849 | 2022-10-25 | 1 | CRS-GUP-DHI-DT-22-1178 | 2022-11-30 | NC | DE-GUP-DT-E-22-1092 | 2022-12-16 | 2 | CRS-GUP-DHI-DT-22-1382 | 2023-01-03 | NC | DE-GUP-DT-E-23-076 | 2023-01-26 | 3 | CRS-GUP-DHI-DT-23-1609 | 2023-03-02 | NC
| GUP | HM04 | P1 | SAM | 131164 |  | GUP-HM04-P1SAM-131164 | HVAC SYSTEM_FIRE PROTECTION PUMP BUILDING_EQUIPMENT SCHEDULE | FI | 2022-07-11 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | Fire Protection Pump Building | HVAC | 2 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-076 | 2023-01-26 | 3 | CRS-GUP-DHI-DT-23-1609 | 2023-03-02 | NC | DHI-GUP-DT-22-179 | 2022-04-18 | 0 | CRS-GUP-DHI-DT-22-309 | 2022-04-25 | RR | DE-GUP-DT-E-22-849 | 2022-10-25 | 1 | CRS-GUP-DHI-DT-22-1016 | 2022-11-13 | NC | DE-GUP-DT-E-22-1092 | 2022-12-16 | 2 | CRS-GUP-DHI-DT-22-1382 | 2023-01-03 | NC | DE-GUP-DT-E-23-076 | 2023-01-26 | 3 | CRS-GUP-DHI-DT-23-1609 | 2023-03-02 | NC
| GUP | HM05 | P1 | SAB | 131111 |  | GUP-HM05-P1SAB-131111 | HVAC SYSTEM_ADMINISTRATION BUILDING_LOAD CALCULATION | FA | 2022-09-10 | 2023-01-04 | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | Admin. Building | HVAC | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-982 | 2023-12-12 | 1 | CRS-GUP-DHI-DT-23-1976 | 2023-06-08 | AA | DE-GUP-DT-E-22-502 | 2022-08-16 | A | CRS-GUP-DHI-DT-22-728 | 2022-09-09 | RC | DE-GUP-DT-E-22-1250 | 2023-01-11 | B | CRS-GUP-DHI-DT-22-1456 | 2023-02-04 | RC | DE-GUP-DT-E-23-448 | 2023-04-13 | C | CRS-GUP-DHI-DT-23-1900 | 2023-05-05 | AA | DE-GUP-DT-E-23-546 | 2023-05-12 | 0 | CRS-GUP-DHI-DT-23-1976 | 2023-06-08 | AA | DE-GUP-DT-E-23-982 | 2023-12-12 | 1
| GUP | HM01 | P1 | SAB | 131112 |  | GUP-HM01-P1SAB-131112 | HVAC SYSTEM_ADMINISTRATION BUILDING_AIR FLOW DIAGRAM | FI | 2022-09-10 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | Admin. Building | HVAC | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-982 | 2023-12-12 | 4 | CRS-GUP-DHI-DT-23-1976 | 2023-06-08 | NC | DE-GUP-DT-E-22-502 | 2022-08-16 | 0 | CRS-GUP-DHI-DT-22-728 | 2022-09-09 | NC | DE-GUP-DT-E-22-1250 | 2023-01-11 | 1 | CRS-GUP-DHI-DT-22-1456 | 2023-02-04 | NC | DE-GUP-DT-E-23-448 | 2023-04-13 | 2 | CRS-GUP-DHI-DT-23-1900 | 2023-05-05 | NC | DE-GUP-DT-E-23-546 | 2023-05-12 | 3 | CRS-GUP-DHI-DT-23-1976 | 2023-06-08 | NC | DE-GUP-DT-E-23-982 | 2023-12-12 | 4
| GUP | HM01 | P1 | SAB | 131113 |  | GUP-HM01-P1SAB-131113 | HVAC SYSTEM_ADMINISTRATION BUILDING_DUCT & PIPING PLAN | FI | 2022-09-10 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | Admin. Building | HVAC | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-982 | 2023-12-12 | 4 | CRS-GUP-DHI-DT-23-1976 | 2023-06-08 | NC | DE-GUP-DT-E-22-502 | 2022-08-16 | 0 | CRS-GUP-DHI-DT-22-728 | 2022-09-09 | NC | DE-GUP-DT-E-22-1250 | 2023-01-11 | 1 | CRS-GUP-DHI-DT-22-1456 | 2023-02-04 | NC | DE-GUP-DT-E-23-448 | 2023-04-13 | 2 | CRS-GUP-DHI-DT-23-1900 | 2023-05-05 | NC | DE-GUP-DT-E-23-546 | 2023-05-12 | 3 | CRS-GUP-DHI-DT-23-1976 | 2023-06-08 | NC | DE-GUP-DT-E-23-982 | 2023-12-12 | 4
| GUP | HM04 | P1 | SAB | 131114 |  | GUP-HM04-P1SAB-131114 | HVAC SYSTEM_ADMINISTRATION BUILDING_EQUIPMENT SCHEDULE | FI | 2022-09-10 |  | 기계기술팀(HVAC) | 김재환 | B | P |  |  |  | CCPP | Admin. Building | HVAC | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-982 | 2023-12-12 | 4 | CRS-GUP-DHI-DT-23-1976 | 2023-06-08 | NC | DE-GUP-DT-E-22-502 | 2022-08-16 | 0 | CRS-GUP-DHI-DT-22-728 | 2022-09-09 | NC | DE-GUP-DT-E-22-1250 | 2023-01-11 | 1 | CRS-GUP-DHI-DT-22-1456 | 2023-02-04 | NC | DE-GUP-DT-E-23-448 | 2023-04-13 | 2 | CRS-GUP-DHI-DT-23-1900 | 2023-05-05 | NC | DE-GUP-DT-E-23-546 | 2023-05-12 | 3 | CRS-GUP-DHI-DT-23-1976 | 2023-06-08 | NC | DE-GUP-DT-E-23-982 | 2023-12-12 | 4
| GUP | FF01 | P1 | SGA | 137021 |  | GUP-FF01-P1SGA-137021 | FIRE FIGHTING PUMP SYSTEM_PIPE LAYOUT AND DETAIL DRAWING | FI | 2022-09-01 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | General FF | FF | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-457 | 2023-04-14 | 0 | CRS-GUP-DHI-DT-22-1259 | 2022-12-16 | NC | DE-GUP-DT-E-22-633 | 2022-09-07 | 0 | CRS-GUP-DHI-DT-22-896 | 2022-10-12 | NC | DE-GUP-DT-E-22-986 | 2022-11-24 | 1 | CRS-GUP-DHI-DT-22-1259 | 2022-12-16 | NC | DE-GUP-DT-E-23-457 | 2023-04-14
| GUP | FF01 | P1 | SGA | 137051 |  | GUP-FF01-P1SGA-137051 | FIRE SERVICE RING MAIN SYSTEM_OUTDOOR HYDRANT ARRANGEMENT | FI | 2022-07-11 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | General FF | FF | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-973 | 2023-12-05 | 6 | 자체 CRS 개정 후 제출 | 2023-12-04 | N/A | DE-GUP-DT-E-22-227 | 2022-05-19 | A | CRS-GUP-DHI-DT-22-411 | 2022-06-13 | RC | DE-GUP-DT-E-22-319 | 2022-06-20 | 0 | CRS-GUP-DHI-DT-22-571 | 2022-08-03 | RC | DE-GUP-DT-E-22-519 | 2022-08-19 | 1 | CRS-GUP-DHI-DT-22-781 | 2022-09-19 | RC | DE-GUP-DT-E-22-772 | 2022-10-07 | 2 | CRS-GUP-DHI-DT-22-1087 | 2022-11-21 | NC | DE-GUP-DT-E-23-281 | 2023-03-08 | 3 | CRS-GUP-DHI-DT-23-1760 | 2023-03-22 | NC | DE-GUP-DT-E-23-740 | 2023-08-11 | 4 | 자체 CRS 개정 후 제출 | 2023-09-26 | N/A | DE-GUP-DT-E-23-830 | 2023-09-27 | 5 | 자체 CRS 개정 후 제출 | 2023-12-04 | N/A | DE-GUP-DT-E-23-973 | 2023-12-05 | 6
| GUP | FF00 | P1 | SGA | 137071 |  | GUP-FF00-P1SGA-137071 | FIRE FIGHTING PUMP SYSTEM_DATASHEET | FA | 2022-09-10 | 2023-01-09 | 기계기술팀(FF) | 엄재식 |  |  |  |  | FF | CCPP | General FF | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-288 | 2024-12-06 | 2 | 자체 CRS 개정 후 제출 | 2024-12-05 | N/A | DE-GUP-DT-E-22-674 | 2022-09-16 | A | CRS-GUP-DHI-DT-22-971 | 2022-11-07 | RC | DE-GUP-DT-E-22-1097 | 2022-12-16 | B | CRS-GUP-DHI-DT-22-1341 | 2022-12-28 | AA | DE-GUP-DT-E-23-038 | 2023-01-17 | 0 | 자체 CRS 개정 후 제출 | 2024-04-03 | N/A | DE-GUP-DT-E-24-104 | 2024-04-04 | 1 | 자체 CRS 개정 후 제출 | 2024-12-05 | N/A | DE-GUP-DT-E-24-288 | 2024-12-06 | 2
| GUP | FF00 | P1 | SGA | 137072 |  | GUP-FF00-P1SGA-137072 | OUTDOOR HYDRANT SYSTEM_DATASHEET | FI | 2022-09-10 |  | 기계기술팀(FF) | 엄재식 |  |  |  |  | FF | CCPP | General FF | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-456 | 2023-04-14 | 1 | CRS-GUP-DHI-DT-22-913 | 2022-10-19 | NC | DE-GUP-DT-E-22-694 | 2022-09-23 | 0 | CRS-GUP-DHI-DT-22-913 | 2022-10-19 | NC | DE-GUP-DT-E-23-456 | 2023-04-14 | 1
| GUP | FF00 | P1 | SGA | 137073 |  | GUP-FF00-P1SGA-137073 | INDOOR HYDRANT SYSTEM_DATASHEET | FI | 2022-09-10 |  | 기계기술팀(FF) | 엄재식 |  |  |  |  | FF | CCPP | General FF | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-456 | 2023-04-14 | 1 | CRS-GUP-DHI-DT-22-971 | 2022-11-07 | NC | DE-GUP-DT-E-22-674 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-971 | 2022-11-07 | NC | DE-GUP-DT-E-23-456 | 2023-04-14 | 1
| GUP | FF00 | P1 | SGE | 137074 |  | GUP-FF00-P1SGE-137074 | SPRINKLER SYSTEM_DATASHEET | FI | 2022-09-10 |  | 기계기술팀(FF) | 엄재식 |  |  |  |  | FF | CCPP | General FF | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-290 | 2024-12-06 | 1 | CRS-GUP-DHI-DT-22-902 | 2022-10-12 | NC | DE-GUP-DT-E-22-665 | 2022-09-15 | 0 | CRS-GUP-DHI-DT-22-902 | 2022-10-12 | NC | DE-GUP-DT-E-24-290 | 2024-12-06 | 1
| GUP | FF00 | P1 | SGC | 137075 |  | GUP-FF00-P1SGC-137075 | WATER SPRAY SYSTEM_DATASHEET | FI | 2022-09-10 |  | 기계기술팀(FF) | 엄재식 |  |  |  |  | FF | CCPP | General FF | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-456 | 2023-04-14 | 1 | CRS-GUP-DHI-DT-22-1105 | 2022-11-21 | NC | DE-GUP-DT-E-22-829 | 2022-10-20 | 0 | CRS-GUP-DHI-DT-22-1105 | 2022-11-21 | NC | DE-GUP-DT-E-23-456 | 2023-04-14 | 1
| GUP | FF00 | P1 | SGF | 137076 |  | GUP-FF00-P1SGF-137076 | FOAM SYSTEM_DATASHEET | FI | 2022-09-10 |  | 기계기술팀(FF) | 엄재식 |  |  |  |  | FF | CCPP | General FF | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-1043 | 2022-12-08 | 1 | CRS-GUP-DHI-DT-22-1318 | 2022-12-22 | NC | DE-GUP-DT-E-22-829 | 2022-10-20 | 0 | CRS-GUP-DHI-DT-22-1105 | 2022-11-21 | RC | DE-GUP-DT-E-22-1043 | 2022-12-08 | 1 | CRS-GUP-DHI-DT-22-1318 | 2022-12-22 | NC
| GUP | FF00 | P1 | SGE | 137077 |  | GUP-FF00-P1SGE-137077 | PRE-ACTION SPRINKLER_DATASHEET | FI | 2022-09-10 |  | 기계기술팀(FF) | 엄재식 |  |  |  |  | FF | CCPP | General FF | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-829 | 2022-10-20 | 0 | CRS-GUP-DHI-DT-22-1105 | 2022-11-21 | NC | DE-GUP-DT-E-22-829 | 2022-10-20 | 0 | CRS-GUP-DHI-DT-22-1105 | 2022-11-21 | NC
| GUP | FF00 | P1 | SGK | 137078 |  | GUP-FF00-P1SGK-137078 | CLEAN AGENT SYSTEM_DATASHEET | FI | 2022-09-10 |  | 기계기술팀(FF) | 엄재식 |  |  |  |  | FF | CCPP | General FF | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-661 | 2022-09-14 | 0 | CRS-GUP-DHI-DT-22-899 | 2022-10-12 | NC | DE-GUP-DT-E-22-661 | 2022-09-14 | 0 | CRS-GUP-DHI-DT-22-899 | 2022-10-12 | NC
| GUP | FF00 | P1 | SGZ | 137081 |  | GUP-FF00-P1SGZ-137081 | FIRE EXTINGUISHER_DATASHEET | FI | 2022-09-10 |  | 기계기술팀(FF) | 엄재식 |  |  |  |  | FF | CCPP | General FF | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-456 | 2023-04-14 | 1 | CRS-GUP-DHI-DT-22-913 | 2022-10-19 | NC | DE-GUP-DT-E-22-694 | 2022-09-23 | 0 | CRS-GUP-DHI-DT-22-913 | 2022-10-19 | NC | DE-GUP-DT-E-23-456 | 2023-04-14 | 1
| GUP | FF00 | P1 | SGA | 137082 |  | GUP-FF00-P1SGA-137082 | PIPE AND BULK MATERIAL_DATASHEET | FI | 2022-09-10 |  | 기계기술팀(FF) | 엄재식 |  |  |  |  | FF | CCPP | General FF | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-147 | 2023-02-09 | 1 | CRS-GUP-DHI-DT-23-1546 | 2023-02-16 | NC | DE-GUP-DT-E-22-829 | 2022-10-20 | 0 | CRS-GUP-DHI-DT-22-1105 | 2022-11-21 | NC | DE-GUP-DT-E-23-147 | 2023-02-09 | 1 | CRS-GUP-DHI-DT-23-1546 | 2023-02-16 | NC
| GUP | FF00 | P1 | CYE | 137083 |  | GUP-FF00-P1CYE-137083 | FIRE DETECTION AND ALARM SYSTEM_DATASHEET | FI | 2022-09-10 |  | 기계기술팀(FF) | 엄재식 |  |  |  |  | FF | CCPP | General FF | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-1101 | 2022-12-16 | 1 | CRS-GUP-DHI-DT-22-1344 | 2022-12-28 | NC | DE-GUP-DT-E-22-674 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-971 | 2022-11-07 | RC | DE-GUP-DT-E-22-1101 | 2022-12-16 | 1 | CRS-GUP-DHI-DT-22-1344 | 2022-12-28 | NC
| GUP | FF00 | P1 | CYE | 137084 |  | GUP-FF00-P1CYE-137084 | CABLE AND BULK MATERIAL_DATASHEET | FI | 2022-09-10 |  | 기계기술팀(FF) | 엄재식 |  |  |  |  | FF | CCPP | General FF | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-146 | 2023-02-09 | 1 | CRS-GUP-DHI-DT-23-1545 | 2023-02-16 | NC | DE-GUP-DT-E-22-829 | 2022-10-20 | 0 | CRS-GUP-DHI-DT-22-1105 | 2022-11-21 | NC | DE-GUP-DT-E-23-146 | 2023-02-09 | 1 | CRS-GUP-DHI-DT-23-1545 | 2023-02-16 | NC
| GUP | FF03 | P1 | CYE | 137041 |  | GUP-FF03-P1CYE-137041 | FIRE DETECTION AND ALARM SYSTEM_CAUSE AND EFFECT DIAGRAM_MFAP | FA | 2023-01-10 | 2023-06-10 | 기계기술팀(FF) | 엄재식 |  |  |  |  | FF | CCPP | General FF | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-067 | 2024-03-07 | 3 | CRS-GUP-DHI-DT-24-030 | 2024-03-11 | AA | DE-GUP-DT-E-23-111 | 2023-02-03 | A | CRS-GUP-DHI-DT-23-1680 | 2023-03-13 | AC | DE-GUP-DT-E-23-395 | 2023-03-30 | 0(CP) | CRS-GUP-DHI-DT-23-1852 | 2023-04-19 | AC | DE-GUP-DT-E-23-579 | 2023-05-22 | 1(CP) | CRS-GUP-DHI-DT-23-2004 | 2023-06-15 | AC | DE-GUP-DT-E-23-879 | 2023-11-01 | 2 | 자체 CRS 개정 후 제출 | 2024-03-06 | N/A | DE-GUP-DT-E-24-067 | 2024-03-07 | 3 | CRS-GUP-DHI-DT-24-030 | 2024-03-11 | AA
| GUP | FF03 | P1 | CYE | 137042 |  | GUP-FF03-P1CYE-137042 | FIRE DETECTION AND ALARM SYSTEM_CAUSE AND EFFECT DIAGRAM_LFAP-01 | FA | 2023-01-10 | 2023-06-10 | 기계기술팀(FF) | 엄재식 |  |  |  |  | FF | CCPP | General FF | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-879 | 2023-11-01 | 2 | CRS-GUP-DHI-DT-24-030 | 2024-03-11 | AA | DE-GUP-DT-E-23-111 | 2023-02-03 | A | CRS-GUP-DHI-DT-23-1680 | 2023-03-13 | AC | DE-GUP-DT-E-23-395 | 2023-03-30 | 0(CP) | CRS-GUP-DHI-DT-23-1852 | 2023-04-19 | AC | DE-GUP-DT-E-23-579 | 2023-05-22 | 1(CP) | CRS-GUP-DHI-DT-23-2004 | 2023-06-15 | AC | DE-GUP-DT-E-23-879 | 2023-11-01 | 2 | CRS-GUP-DHI-DT-24-030 | 2024-03-11 | AA
| GUP | FF03 | P1 | CYE | 137043 |  | GUP-FF03-P1CYE-137043 | FIRE DETECTION AND ALARM SYSTEM_CAUSE AND EFFECT DIAGRAM_LFAP-02 | FA | 2023-01-10 | 2023-06-10 | 기계기술팀(FF) | 엄재식 |  |  |  |  | FF | CCPP | General FF | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-879 | 2023-11-01 | 2 | CRS-GUP-DHI-DT-24-030 | 2024-03-11 | AA | DE-GUP-DT-E-23-111 | 2023-02-03 | A | CRS-GUP-DHI-DT-23-1680 | 2023-03-13 | AC | DE-GUP-DT-E-23-395 | 2023-03-30 | 0(CP) | CRS-GUP-DHI-DT-23-1852 | 2023-04-19 | AC | DE-GUP-DT-E-23-579 | 2023-05-22 | 1(CP) | CRS-GUP-DHI-DT-23-2004 | 2023-06-15 | AC | DE-GUP-DT-E-23-879 | 2023-11-01 | 2 | CRS-GUP-DHI-DT-24-030 | 2024-03-11 | AA
| GUP | FF03 | P1 | CYE | 137044 |  | GUP-FF03-P1CYE-137044 | FIRE DETECTION AND ALARM SYSTEM_CAUSE AND EFFECT DIAGRAM_LFAP-03 | FA | 2023-01-10 | 2023-06-10 | 기계기술팀(FF) | 엄재식 |  |  |  |  | FF | CCPP | General FF | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-067 | 2024-03-07 | 3 | CRS-GUP-DHI-DT-24-030 | 2024-03-11 | AA | DE-GUP-DT-E-23-111 | 2023-02-03 | A | CRS-GUP-DHI-DT-23-1680 | 2023-03-13 | AC | DE-GUP-DT-E-23-395 | 2023-03-30 | 0(CP) | CRS-GUP-DHI-DT-23-1852 | 2023-04-19 | AC | DE-GUP-DT-E-23-579 | 2023-05-22 | 1(CP) | CRS-GUP-DHI-DT-23-2004 | 2023-06-15 | AC | DE-GUP-DT-E-23-879 | 2023-11-01 | 2 | 자체 CRS 개정 후 제출 | 2024-03-06 | N/A | DE-GUP-DT-E-24-067 | 2024-03-07 | 3 | CRS-GUP-DHI-DT-24-030 | 2024-03-11 | AA
| GUP | FF03 | P1 | CYE | 137045 |  | GUP-FF03-P1CYE-137045 | FIRE DETECTION AND ALARM SYSTEM_CAUSE AND EFFECT DIAGRAM_LFAP-04 | FA | 2023-01-10 | 2023-06-10 | 기계기술팀(FF) | 엄재식 |  |  |  |  | FF | CCPP | General FF | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-25-021 | 2025-02-10 | 3 | CRS-GUP-DHI-DT-24-030 | 2024-03-11 | AA | DE-GUP-DT-E-23-111 | 2023-02-03 | A | CRS-GUP-DHI-DT-23-1680 | 2023-03-13 | AC | DE-GUP-DT-E-23-395 | 2023-03-30 | 0(CP) | CRS-GUP-DHI-DT-23-1852 | 2023-04-19 | AC | DE-GUP-DT-E-23-579 | 2023-05-22 | 1(CP) | CRS-GUP-DHI-DT-23-2004 | 2023-06-15 | AC | DE-GUP-DT-E-23-879 | 2023-11-01 | 2 | CRS-GUP-DHI-DT-24-030 | 2024-03-11 | AA | DE-GUP-DT-E-25-021 | 2025-02-10 | 3
| GUP | FF04 | P1 | SGA | 137008 |  | GUP-FF04-P1SGA-137008 | FIRE FIGHTING SYSTEM_O&M MANUAL | FI | 2023-12-01 |  | 기계기술팀(FF) | 엄재식 |  |  |  |  | FF | CCPP | General FF | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-242 | 2024-10-07 | 1 | CRS-GUP-DHI-DT-24-031 | 2024-03-11 | NC | DE-GUP-DT-E-23-986 | 2023-12-12 | 0 | CRS-GUP-DHI-DT-24-031 | 2024-03-11 | NC | DE-GUP-DT-E-24-242 | 2024-10-07 | 1
| GUP | FF03 | P1 | CYE | 137031 |  | GUP-FF03-P1CYE-137031 | FIRE DETECTION AND ALARM SYSTEM_WIRING DIAGRAM_MFAP | FI | 2023-01-10 |  | 기계기술팀(FF) | 엄재식 |  | P |  |  | FF | CCPP | General FF | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-067 | 2024-03-07 | 2 | 자체 CRS 개정 후 제출 | 2024-03-06 | N/A | DE-GUP-DT-E-22-1252 | 2023-01-11 | 0 | CRS-GUP-DHI-DT-23-1518 | 2023-02-14 | NC | DE-GUP-DT-E-23-814 | 2023-09-15 | 1 | 자체 CRS 개정 후 제출 | 2024-03-06 | N/A | DE-GUP-DT-E-24-067 | 2024-03-07 | 2
| GUP | FF03 | P1 | CYE | 137032 |  | GUP-FF03-P1CYE-137032 | FIRE DETECTION AND ALARM SYSTEM_WIRING DIAGRAM_LFAP-01 | FI | 2023-01-10 |  | 기계기술팀(FF) | 엄재식 |  | P |  |  | FF | CCPP | General FF | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-814 | 2023-09-15 | 1 | CRS-GUP-DHI-DT-23-1518 | 2023-02-14 | NC | DE-GUP-DT-E-22-1252 | 2023-01-11 | 0 | CRS-GUP-DHI-DT-23-1518 | 2023-02-14 | NC | DE-GUP-DT-E-23-814 | 2023-09-15 | 1
| GUP | FF03 | P1 | CYE | 137033 |  | GUP-FF03-P1CYE-137033 | FIRE DETECTION AND ALARM SYSTEM_WIRING DIAGRAM_LFAP-02 | FI | 2023-01-10 |  | 기계기술팀(FF) | 엄재식 |  | P |  |  | FF | CCPP | General FF | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-814 | 2023-09-15 | 1 | CRS-GUP-DHI-DT-23-1518 | 2023-02-14 | NC | DE-GUP-DT-E-22-1252 | 2023-01-11 | 0 | CRS-GUP-DHI-DT-23-1518 | 2023-02-14 | NC | DE-GUP-DT-E-23-814 | 2023-09-15 | 1
| GUP | FF03 | P1 | CYE | 137034 |  | GUP-FF03-P1CYE-137034 | FIRE DETECTION AND ALARM SYSTEM_WIRING DIAGRAM_LFAP-03 | FI | 2023-01-10 |  | 기계기술팀(FF) | 엄재식 |  | P |  |  | FF | CCPP | General FF | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-067 | 2024-03-07 | 2 | 자체 CRS 개정 후 제출 | 2024-03-06 | N/A | DE-GUP-DT-E-22-1252 | 2023-01-11 | 0 | CRS-GUP-DHI-DT-23-1518 | 2023-02-14 | NC | DE-GUP-DT-E-23-814 | 2023-09-15 | 1 | 자체 CRS 개정 후 제출 | 2024-03-06 | N/A | DE-GUP-DT-E-24-067 | 2024-03-07 | 2
| GUP | FF03 | P1 | CYE | 137035 |  | GUP-FF03-P1CYE-137035 | FIRE DETECTION AND ALARM SYSTEM_WIRING DIAGRAM_LFAP-04 | FI | 2023-01-10 |  | 기계기술팀(FF) | 엄재식 |  | P |  |  | FF | CCPP | General FF | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-814 | 2023-09-15 | 2 | CRS-GUP-DHI-DT-23-2057 | 2023-07-15 | NC | DE-GUP-DT-E-22-1252 | 2023-01-11 | 0 | CRS-GUP-DHI-DT-23-1518 | 2023-02-14 | NC | DE-GUP-DT-E-23-635 | 2023-06-21 | 1 | CRS-GUP-DHI-DT-23-2057 | 2023-07-15 | NC | DE-GUP-DT-E-23-814 | 2023-09-15 | 2
| GUP | FF03 | P1 | CYE | 137036 |  | GUP-FF03-P1CYE-137036 | FIRE DETECTION AND ALARM SYSTEM_WIRING DIAGRAM_RFAP | FI | 2023-01-10 |  | 기계기술팀(FF) | 엄재식 |  | P |  |  | FF | CCPP | General FF | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-814 | 2023-09-15 | 1 | CRS-GUP-DHI-DT-23-1518 | 2023-02-14 | NC | DE-GUP-DT-E-22-1252 | 2023-01-11 | 0 | CRS-GUP-DHI-DT-23-1518 | 2023-02-14 | NC | DE-GUP-DT-E-23-814 | 2023-09-15 | 1
| GUP | FF03 | P1 | CYE | 137065 |  | GUP-FF03-P1CYE-137065 | FIRE DETECTION AND ALARM SYSTEM_TYPICAL MOUNTING AND INSTALLATION DETAILS | FI | 2023-01-10 |  | 기계기술팀(FF) | 엄재식 |  | P |  |  | FF | CCPP | General FF | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-775 | 2023-08-29 | 2 | 자체 CRS 개정 후 제출 | 2023-08-28 | N/A | DE-GUP-DT-E-23-039 | 2023-01-17 | 0 | CRS-GUP-DHI-DT-23-1531 | 2023-02-14 | NC | DE-GUP-DT-E-23-458 | 2023-04-14 | 1 | 자체 CRS 개정 후 제출 | 2023-08-28 | N/A | DE-GUP-DT-E-23-775 | 2023-08-29 | 2
| GUP | FF04 | P1 | SGA | 137009 |  | GUP-FF04-P1SGA-137009 | FIRE FIGHTING SYSTEM_COMMISSIONING & PERFORMANCE TEST PROCEDURES | FI | 2023-01-10 |  | 기계기술팀(FF) | 엄재식 |  |  |  |  | FF | CCPP | General FF | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-112 | 2023-02-03 | 0 | CRS-GUP-DHI-DT-23-1681 | 2023-03-13 | NC | DE-GUP-DT-E-23-112 | 2023-02-03 | 0 | CRS-GUP-DHI-DT-23-1681 | 2023-03-13 | NC
| GUP | FF04 | P1 | SGA | 137004 |  | GUP-FF04-P1SGA-137004 | FF GENERAL_SYMBOL AND LEGEND | FI | 2022-11-10 |  | 기계기술팀(FF) | 엄재식 |  |  |  |  | FF | CCPP | General FF | FF | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-633 | 2022-09-07 | 0 | CRS-GUP-DHI-DT-22-873 | 2022-10-09 | NC | DE-GUP-DT-E-22-633 | 2022-09-07 | 0 | CRS-GUP-DHI-DT-22-873 | 2022-10-09 | NC
| GUP | FF00 | P1 | SGA | 137002 |  | GUP-FF00-P1SGA-137002 | FIRE FIGHTING SYSTEM DESIGN CRITERIA | FA | 2022-07-11 | 2022-12-25 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | General FF | FF | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-1216 | 2023-01-04 | 0 | CRS-GUP-DHI-DT-23-1511 | 2023-02-14 | AA | DE-GUP-DT-E-22-228 | 2022-05-19 | A | CRS-GUP-DHI-DT-22-412 | 2022-06-13 | RC | DE-GUP-DT-E-22-306 | 2022-06-16 | B | CRS-GUP-DHI-DT-22-500 | 2022-07-06 | RC | DE-GUP-DT-E-22-392 | 2022-07-13 | C | CRS-GUP-DHI-DT-22-574 | 2022-08-03 | RC | DE-GUP-DT-E-22-519 | 2022-08-19 | D | CRS-GUP-DHI-DT-22-781 | 2022-09-19 | RC | DE-GUP-DT-E-22-790 | 2022-10-12 | E | CRS-GUP-DHI-DT-22-978 | 2022-11-07 | RC | DE-GUP-DT-E-22-966 | 2022-11-21 | F | CRS-GUP-DHI-DT-22-1255 | 2022-12-13 | AA | DE-GUP-DT-E-22-1216 | 2023-01-04 | 0 | CRS-GUP-DHI-DT-23-1511 | 2023-02-14 | AA
| GUP | FF03 | P1 | SGA | 137024 |  | GUP-FF03-P1SGA-137024 | FIRE WATER TANK P&ID | FA | 2022-07-11 | 2022-11-24 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | General FF | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-133 | 2024-05-13 | 3 | 자체 CRS 개정 후 제출 | 2024-05-12 | N/A | DE-GUP-DT-E-22-226 | 2022-05-19 | A | CRS-GUP-DHI-DT-22-430 | 2022-06-15 | RC | DE-GUP-DT-E-22-379 | 2022-07-11 | B | CRS-GUP-DHI-DT-22-573 | 2022-08-03 | RC | DE-GUP-DT-E-22-519 | 2022-08-19 | C | CRS-GUP-DHI-DT-22-781 | 2022-09-19 | AA | DE-GUP-DT-E-22-1116 | 2022-12-16 | D | CRS-GUP-DHI-DT-22-1355 | 2022-12-29 | AA | DE-GUP-DT-E-22-1215 | 2023-01-04 | 0 | CRS-GUP-DHI-DT-23-1510 | 2023-02-14 | AA | DE-GUP-DT-E-23-347 | 2023-03-22 | 1 | 자체 CRS 개정 후 제출 | 2023-08-10 | N/A | DE-GUP-DT-E-23-739 | 2023-08-11 | 2 | 자체 CRS 개정 후 제출 | 2024-05-12 | N/A | DE-GUP-DT-E-24-133 | 2024-05-13 | 3
| GUP | FF03 | P1 | SGA | 137022 |  | GUP-FF03-P1SGA-137022 | FIRE FIGHTING PUMP SYSTEM_P&I DIAGRAM | FA | 2022-09-01 | 2022-12-31 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | General FF | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-747 | 2023-08-17 | 2 | 자체 CRS 개정 후 제출 | 2023-08-16 | N/A | DE-GUP-DT-E-22-633 | 2022-09-07 | A | CRS-GUP-DHI-DT-22-896 | 2022-10-12 | RC | DE-GUP-DT-E-22-986 | 2022-11-24 | B | CRS-GUP-DHI-DT-22-1256 | 2022-12-13 | AA | DE-GUP-DT-E-22-1215 | 2023-01-04 | 0 | CRS-GUP-DHI-DT-23-1510 | 2023-02-14 | AA | DE-GUP-DT-E-23-457 | 2023-04-14 | 1 | 자체 CRS 개정 후 제출 | 2023-08-16 | N/A | DE-GUP-DT-E-23-747 | 2023-08-17 | 2
| GUP | FF03 | P1 | SGA | 137052 |  | GUP-FF03-P1SGA-137052 | FIRE SERVICE RING MAIN SYSTEM_P&I DIAGRAM | FA | 2022-09-25 | 2023-03-25 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | General FF | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-740 | 2023-08-11 | 2 | 자체 CRS 개정 후 제출 | 2023-08-10 | N/A | DE-GUP-DT-E-22-227 | 2022-05-19 | A | CRS-GUP-DHI-DT-22-411 | 2022-06-13 | RC | DE-GUP-DT-E-22-319 | 2022-06-20 | 0 | CRS-GUP-DHI-DT-22-571 | 2022-08-03 | RC | DE-GUP-DT-E-22-519 | 2022-08-19 | C | CRS-GUP-DHI-DT-22-781 | 2022-09-19 | RC | DE-GUP-DT-E-22-773 | 2022-10-07 | D | CRS-GUP-DHI-DT-22-1088 | 2022-11-21 | AC | DE-GUP-DT-E-22-1104 | 2022-12-16 | 0(CP) | CRS-GUP-DHI-DT-22-1345 | 2022-12-28 | AA | DE-GUP-DT-E-23-281 | 2023-03-08 | 1 | 자체 CRS 개정 후 제출 | 2023-08-10 | N/A | DE-GUP-DT-E-23-740 | 2023-08-11 | 2
| GUP | FF03 | P1 | CYE | 137005 |  | GUP-FF03-P1CYE-137005 | FIRE DETECTION AND ALARM SYSTEM_BLOCK DIAGRAM | FA | 2022-11-10 | 2023-01-25 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | General FF | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-774 | 2023-08-29 | 1 | 자체 CRS 개정 후 제출 | 2023-08-28 | N/A | DE-GUP-DT-E-22-698 | 2022-09-23 | A | CRS-GUP-DHI-DT-22-915 | 2022-10-19 | RC | DE-GUP-DT-E-22-941 | 2022-11-15 | B | CRS-GUP-DHI-DT-22-1111 | 2022-11-21 | RC | DE-GUP-DT-E-22-1174 | 2022-12-23 | C | CRS-GUP-DHI-DT-23-1483 | 2023-02-11 | AA | DE-GUP-DT-E-23-185 | 2023-02-16 | 0 | 자체 CRS 개정 후 제출 | 2023-08-28 | N/A | DE-GUP-DT-E-23-774 | 2023-08-29 | 1
| GUP | FF05 | P1 | SGA | 137053 |  | GUP-FF05-P1SGA-137053 | FIRE SERVICE RING MAIN SYSTEM_CALCULATION | FI | 2022-12-13 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | General FF | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-050 | 2023-01-19 | 1 | CRS-GUP-DHI-DT-23-1560 | 2023-02-23 | NC | DE-GUP-DT-E-22-1102 | 2022-12-16 | 0 | CRS-GUP-DHI-DT-22-1384 | 2023-01-03 | RC | DE-GUP-DT-E-23-050 | 2023-01-19 | 1 | CRS-GUP-DHI-DT-23-1560 | 2023-02-23 | NC
| GUP | FF03 | P1 | CYE | 137062 |  | GUP-FF03-P1CYE-137062 | FIRE DETECTION AND ALARM SYSTEM_YARD AREA_SINGLE LINE DIAGRAM | FI | 2022-12-09 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | General FF | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-470 | 2023-04-14 | 1 | CRS-GUP-DHI-DT-23-1892 | 2023-05-02 | NC | DE-GUP-DT-E-22-1172 | 2022-12-23 | 0 | CRS-GUP-DHI-DT-23-1505 | 2023-02-14 | NC | DE-GUP-DT-E-23-470 | 2023-04-14 | 1 | CRS-GUP-DHI-DT-23-1892 | 2023-05-02 | NC
| GUP | FF02 | P1 | CYE | 137061 |  | GUP-FF02-P1CYE-137061 | FIRE DETECTION AND ALARM SYSTEM_YARD AREA_LAYOUT AND DETAIL DRAWING | FI | 2022-12-09 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | General FF | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-470 | 2023-04-14 | 1 | CRS-GUP-DHI-DT-23-1892 | 2023-05-02 | NC | DE-GUP-DT-E-22-1172 | 2022-12-23 | 0 | CRS-GUP-DHI-DT-23-1505 | 2023-02-14 | NC | DE-GUP-DT-E-23-470 | 2023-04-14 | 1 | CRS-GUP-DHI-DT-23-1892 | 2023-05-02 | NC
| GUP | FF03 | P1 | CYE | 137063 |  | GUP-FF03-P1CYE-137063 | FIRE DETECTION AND ALARM SYSTEM_FIRE ALARM PANEL ZONE MAP | FI | 2023-05-01 |  | 기계기술팀(FF) | 엄재식 |  |  |  |  | FF | CCPP | General FF | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-282 | 2024-11-29 | 2 | 자체 CRS 개정 후 제출 | 2024-11-28 | N/A | DE-GUP-DT-E-23-470 | 2023-04-14 | 0 | CRS-GUP-DHI-DT-23-1892 | 2023-05-02 | NC | DE-GUP-DT-E-23-825 | 2023-09-22 | 1 | 자체 CRS 개정 후 제출 | 2024-11-28 | N/A | DE-GUP-DT-E-24-282 | 2024-11-29 | 2
| GUP | FF03 | P1 | CYE | 137064 |  | GUP-FF03-P1CYE-137064 | FIRE DETECTION AND ALARM SYSTEM_MIMIC BOARD | FI | 2023-05-01 |  | 기계기술팀(FF) | 엄재식 |  |  |  |  | FF | CCPP | General FF | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-25-018 | 2025-01-23 | 3 | 자체 CRS 개정 후 제출 | 2025-01-22 | N/A | DE-GUP-DT-E-23-470 | 2023-04-14 | 0 | CRS-GUP-DHI-DT-23-1892 | 2023-05-02 | NC | DE-GUP-DT-E-23-790 | 2023-09-06 | 1 | 자체 CRS 개정 후 제출 | 2024-11-18 | N/A | DE-GUP-DT-E-24-274 | 2024-11-19 | 2 | 자체 CRS 개정 후 제출 | 2025-01-22 | N/A | DE-GUP-DT-E-25-018 | 2025-01-23 | 3
| GUP | FF03 | P1 | SGA | 137210 |  | GUP-FF03-P1SGA-137210 | INDOOR HYDRANT SYSTEM_MAINTENANCE WORKSHOP AND STORE BUILDING_P&I DIAGRAM | FA | 2023-06-10 | 2023-10-14 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Workshop Building | FF | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-405 | 2023-03-30 | 0 | CRS-GUP-DHI-DT-23-1858 | 2023-04-19 | AA | DE-GUP-DT-E-23-221 | 2023-02-22 | A | CRS-GUP-DHI-DT-23-1736 | 2023-03-17 | NC | DE-GUP-DT-E-23-405 | 2023-03-30 | 0 | CRS-GUP-DHI-DT-23-1858 | 2023-04-19 | AA
| GUP | FF01 | P1 | SGA | 137110 |  | GUP-FF01-P1SGA-137110 | INDOOR HYDRANT SYSTEM_MAINTENANCE WORKSHOP AND STORE BUILDING_PIPE LAYOUT AND DETAIL DRAWING | FA | 2023-06-10 | 2023-10-14 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Workshop Building | FF | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-094 | 2024-03-25 | 2 | 자체 CRS 개정 후 제출 | 2024-03-24 | N/A | DE-GUP-DT-E-23-221 | 2023-02-22 | A | CRS-GUP-DHI-DT-23-1736 | 2023-03-17 | AA | DE-GUP-DT-E-23-362 | 2023-03-24 | 0 | 자체 CRS 개정 후 제출 | 2023-09-21 | N/A | DE-GUP-DT-E-23-822 | 2023-09-22 | 1 | 자체 CRS 개정 후 제출 | 2024-03-24 | N/A | DE-GUP-DT-E-24-094 | 2024-03-25 | 2
| GUP | FF05 | P1 | SGA | 137310 |  | GUP-FF05-P1SGA-137310 | INDOOR HYDRANT SYSTEM_MAINTENANCE WORKSHOP AND STORE BUILDING_HYDRAULIC CALCULATION | FI | 2023-06-10 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Workshop Building | FF | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-221 | 2023-02-22 | 0 |  |  |  | DE-GUP-DT-E-23-221 | 2023-02-22 | 0
| GUP | FF03 | P1 | SGE | 138210 |  | GUP-FF03-P1SGE-138210 | SPRINKLER SYSTEM_MAINTENANCE WORKSHOP AND STORE BUILDING_P&I DIAGRAM | FA | 2023-06-10 | 2023-10-14 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Workshop Building | FF | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-362 | 2023-03-24 | 0 | CRS-GUP-DHI-DT-23-1714 | 2023-03-14 | AA | DE-GUP-DT-E-23-266 | 2023-03-06 | A | CRS-GUP-DHI-DT-23-1714 | 2023-03-14 | AA | DE-GUP-DT-E-23-362 | 2023-03-24 | 0
| GUP | FF01 | P1 | SGE | 138110 |  | GUP-FF01-P1SGE-138110 | SPRINKLER SYSTEM_MAINTENANCE WORKSHOP AND STORE BUILDING_PIPE LAYOUT AND DETAIL DRAWING | FI | 2023-06-10 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Workshop Building | FF | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-283 | 2024-11-29 | 2 | 자체 CRS 개정 후 제출 | 2024-11-28 | N/A | DE-GUP-DT-E-23-266 | 2023-03-06 | 0 | CRS-GUP-DHI-DT-23-1714 | 2023-03-14 | NC | DE-GUP-DT-E-24-094 | 2024-03-26 | 1 | 자체 CRS 개정 후 제출 | 2024-11-28 | N/A | DE-GUP-DT-E-24-283 | 2024-11-29 | 2
| GUP | FF05 | P1 | SGE | 138310 |  | GUP-FF05-P1SGE-138310 | SPRINKLER SYSTEM_MAINTENANCE WORKSHOP AND STORE BUILDING_HYDRAULIC CALCULATION | FI | 2023-06-10 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Workshop Building | FF | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-266 | 2023-03-06 | 0 | CRS-GUP-DHI-DT-23-1714 | 2023-03-14 | NC | DE-GUP-DT-E-23-266 | 2023-03-06 | 0 | CRS-GUP-DHI-DT-23-1714 | 2023-03-14 | NC
| GUP | FF03 | P1 | CYE | 139910 |  | GUP-FF03-P1CYE-139910 | FIRE DETECTION AND ALARM SYSTEM_MAINTENANCE WORKSHOP AND STORE BUILDING_SINGLE LINE DIAGRAM | FI | 2023-06-10 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | Workshop Building | FF | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-865 | 2023-10-24 | 1 | 자체 CRS 개정 후 제출 | 2023-10-23 | N/A | DE-GUP-DT-E-23-221 | 2023-02-22 | 0 | 자체 CRS 개정 후 제출 | 2023-10-23 | N/A | DE-GUP-DT-E-23-865 | 2023-10-24 | 1
| GUP | FF02 | P1 | CYE | 139810 |  | GUP-FF02-P1CYE-139810 | FIRE DETECTION AND ALARM SYSTEM_MAINTENANCE WORKSHOP AND STORE BUILDING_LAYOUT AND DETAIL DRAWING | FA | 2023-06-10 | 2023-10-14 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Workshop Building | FF | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-865 | 2023-10-24 | 1 | CRS-GUP-DHI-DT-23-1858 | 2023-04-19 | AA | DE-GUP-DT-E-23-221 | 2023-02-22 | A | CRS-GUP-DHI-DT-23-1736 | 2023-03-17 | NC | DE-GUP-DT-E-23-405 | 2023-03-30 | 0 | CRS-GUP-DHI-DT-23-1858 | 2023-04-19 | AA | DE-GUP-DT-E-23-865 | 2023-10-24 | 1
| GUP | FF01 | P1 | SGZ | 139710 |  | GUP-FF01-P1SGZ-139710 | FIRE EXTINGUISHER_MAINTENANCE WORKSHOP AND STORE BUILDING_LAYOUT AND DETAIL DRAWING | FA | 2023-06-10 | 2023-10-14 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Workshop Building | FF | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-921 | 2023-11-20 | 1 | 자체 CRS 개정 후 제출 | 2023-11-19 | N/A | DE-GUP-DT-E-23-221 | 2023-02-22 | A | CRS-GUP-DHI-DT-23-1736 | 2023-03-17 | AA | DE-GUP-DT-E-23-362 | 2023-03-24 | 0 | 자체 CRS 개정 후 제출 | 2023-11-19 | N/A | DE-GUP-DT-E-23-921 | 2023-11-20 | 1
| GUP | FF03 | P1 | SGA | 137216 |  | GUP-FF03-P1SGA-137216 | INDOOR HYDRANT SYSTEM_WT & WWT BLDG & SHELTER_P&I DIAGRAM | FA | 2023-01-10 | 2023-06-12 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | WT & WWT Building | FF | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-773 | 2023-08-29 | 1 | 자체 CRS 개정 후 제출 | 2023-08-28 | N/A | DE-GUP-DT-E-22-1025 | 2022-12-02 | A | CRS-GUP-DHI-DT-22-1275 | 2022-12-16 | AA | DE-GUP-DT-E-23-087 | 2023-01-30 | 0 | 자체 CRS 개정 후 제출 | 2023-08-28 | N/A | DE-GUP-DT-E-23-773 | 2023-08-29 | 1
| GUP | FF01 | P1 | SGA | 137116 |  | GUP-FF01-P1SGA-137116 | INDOOR HYDRANT SYSTEM_WT & WWT BLDG & SHELTER_PIPE LAYOUT AND DETAIL DRAWING | FI | 2023-01-10 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | WT & WWT Building | FF | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-24-144 | 2024-06-03 | 4 | 자체 CRS 개정 후 제출 | 2024-06-02 | N/A | DE-GUP-DT-E-22-1025 | 2022-12-02 | 0 | CRS-GUP-DHI-DT-22-1275 | 2022-12-16 | NC | DE-GUP-DT-E-23-468 | 2023-04-14 | 1 | 자체 CRS 개정 후 제출 | 2023-08-28 | N/A | DE-GUP-DT-E-23-773 | 2023-08-29 | 2 | 자체 CRS 개정 후 제출 | 2023-12-04 | N/A | DE-GUP-DT-E-23-968 | 2023-12-05 | 3 | 자체 CRS 개정 후 제출 | 2024-06-02 | N/A | DE-GUP-DT-E-24-144 | 2024-06-03 | 4
| GUP | FF05 | P1 | SGA | 137316 |  | GUP-FF05-P1SGA-137316 | INDOOR HYDRANT SYSTEM_WT & WWT BLDG & SHELTER_HYDRAULIC CALCULATION | FI | 2023-01-10 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | WT & WWT Building | FF | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-22-1025 | 2022-12-02 | 0 | CRS-GUP-DHI-DT-22-1275 | 2022-12-16 | NC | DE-GUP-DT-E-22-1025 | 2022-12-02 | 0 | CRS-GUP-DHI-DT-22-1275 | 2022-12-16 | NC
| GUP | FF03 | P1 | SGK | 139216 |  | GUP-FF03-P1SGK-139216 | CLEAN AGENT SYSTEM_WT & WWT BLDG & SHELTER_P&I DIAGRAM | FA | 2023-01-10 | 2023-06-12 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | WT & WWT Building | FF | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-773 | 2023-08-29 | 1 | 자체 CRS 개정 후 제출 | 2023-08-28 | N/A | DE-GUP-DT-E-22-1025 | 2022-12-02 | A | CRS-GUP-DHI-DT-22-1275 | 2022-12-16 | AA | DE-GUP-DT-E-23-087 | 2023-01-30 | 0 | 자체 CRS 개정 후 제출 | 2023-08-28 | N/A | DE-GUP-DT-E-23-773 | 2023-08-29 | 1
| GUP | FF01 | P1 | SGK | 139116 |  | GUP-FF01-P1SGK-139116 | CLEAN AGENT SYSTEM_WT & WWT BLDG & SHELTER_P&I DIAGRAM | FI | 2023-01-10 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | WT & WWT Building | FF | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-773 | 2023-08-29 | 1 | CRS-GUP-DHI-DT-22-1275 | 2022-12-16 | NC | DE-GUP-DT-E-22-1025 | 2022-12-02 | 0 | CRS-GUP-DHI-DT-22-1275 | 2022-12-16 | NC | DE-GUP-DT-E-23-773 | 2023-08-29 | 1
| GUP | FF05 | P1 | SGK | 139316 |  | GUP-FF05-P1SGK-139316 | CLEAN AGENT SYSTEM_WT & WWT BLDG & SHELTER_FLOW CALCULATION | FI | 2023-01-10 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | WT & WWT Building | FF | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-22-1025 | 2022-12-02 | 0 | CRS-GUP-DHI-DT-22-1275 | 2022-12-16 | NC | DE-GUP-DT-E-22-1025 | 2022-12-02 | 0 | CRS-GUP-DHI-DT-22-1275 | 2022-12-16 | NC
| GUP | FF03 | P1 | CYE | 139916 |  | GUP-FF03-P1CYE-139916 | FIRE DETECTION AND ALARM SYSTEM_WT & WWT BLDG & SHELTER_SINGLE LINE DIAGRAM | FI | 2023-01-10 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | WT & WWT Building | FF | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-866 | 2023-10-24 | 2 | 자체 CRS 개정 후 제출 | 2023-10-23 | N/A | DE-GUP-DT-E-22-1176 | 2022-12-23 | 0 | CRS-GUP-DHI-DT-23-1423 | 2023-01-31 | NC | DE-GUP-DT-E-23-773 | 2023-08-29 | 1 | 자체 CRS 개정 후 제출 | 2023-10-23 | N/A | DE-GUP-DT-E-23-866 | 2023-10-24 | 2
| GUP | FF02 | P1 | CYE | 139816 |  | GUP-FF02-P1CYE-139816 | FIRE DETECTION AND ALARM SYSTEM_WT & WWT BLDG & SHELTER_LAYOUT AND DETAIL DRAWING | FI | 2023-01-10 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | WT & WWT Building | FF | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-866 | 2023-10-24 | 2 | 자체 CRS 개정 후 제출 | 2023-10-23 | N/A | DE-GUP-DT-E-22-1176 | 2022-12-23 | 0 | CRS-GUP-DHI-DT-23-1423 | 2023-01-31 | NC | DE-GUP-DT-E-23-773 | 2023-08-29 | 1 | 자체 CRS 개정 후 제출 | 2023-10-23 | N/A | DE-GUP-DT-E-23-866 | 2023-10-24 | 2
| GUP | FF01 | P1 | SGZ | 139716 |  | GUP-FF01-P1SGZ-139716 | FIRE EXTINGUISHER_WT & WWT BLDG & SHELTER_LAYOUT AND DETAIL DRAWING | FI | 2023-01-10 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | WT & WWT Building | FF | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-824 | 2023-09-22 | 2 | 자체 CRS 개정 후 제출 | 2023-09-21 | N/A | DE-GUP-DT-E-22-1025 | 2022-12-02 | 0 | CRS-GUP-DHI-DT-22-1275 | 2022-12-16 | NC | DE-GUP-DT-E-23-468 | 2023-04-14 | 1 | 자체 CRS 개정 후 제출 | 2023-09-21 | N/A | DE-GUP-DT-E-23-824 | 2023-09-22 | 2
| GUP | FF03 | P1 | SGA | 137209 |  | GUP-FF03-P1SGA-137209 | INDOOR HYDRANT SYSTEM_HRSG BUILDING_P&I DIAGRAM | FA | 2023-03-15 | 2023-07-11 | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | HRSG Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-293 | 2023-03-10 | 0 | CRS-GUP-DHI-DT-22-1419 | 2023-02-03 | AA | DE-GUP-DT-E-22-1152 | 2022-12-22 | A | CRS-GUP-DHI-DT-22-1419 | 2023-02-03 | AA | DE-GUP-DT-E-23-293 | 2023-03-10 | 0
| GUP | FF01 | P1 | SGA | 137109 |  | GUP-FF01-P1SGA-137109 | INDOOR HYDRANT SYSTEM_HRSG BUILDING_PIPE LAYOUT AND DETAIL DRAWING | FI | 2023-03-15 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | HRSG Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-24-130 | 2024-05-08 | 2 | 자체 CRS 개정 후 제출 | 2024-05-07 | N/A | DE-GUP-DT-E-22-1152 | 2022-12-22 | 0 | CRS-GUP-DHI-DT-22-1419 | 2023-02-03 | NC | DE-GUP-DT-E-23-464 | 2023-04-14 | 1 | 자체 CRS 개정 후 제출 | 2024-05-07 | N/A | DE-GUP-DT-E-24-130 | 2024-05-08 | 2
| GUP | FF05 | P1 | SGA | 137309 |  | GUP-FF05-P1SGA-137309 | INDOOR HYDRANT SYSTEM_HRSG BUILDING_HYDRAULIC CALCULATION | FI | 2023-03-15 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | HRSG Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-1152 | 2022-12-22 | 0 | CRS-GUP-DHI-DT-22-1419 | 2023-02-03 | NC | DE-GUP-DT-E-22-1152 | 2022-12-22 | 0 | CRS-GUP-DHI-DT-22-1419 | 2023-02-03 | NC
| GUP | FF03 | P1 | CYE | 139909 |  | GUP-FF03-P1CYE-139909 | FIRE DETECTION AND ALARM SYSTEM_HRSG BUILDING_SINGLE LINE DIAGRAM | FI | 2023-03-15 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | HRSG Building | FF | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-833 | 2023-09-27 | 1 | CRS-GUP-DHI-DT-23-1620 | 2023-03-02 | NC | DE-GUP-DT-E-23-116 | 2023-02-03 | 0 | CRS-GUP-DHI-DT-23-1620 | 2023-03-02 | NC | DE-GUP-DT-E-23-833 | 2023-09-27 | 1
| GUP | FF02 | P1 | CYE | 139809 |  | GUP-FF02-P1CYE-139809 | FIRE DETECTION AND ALARM SYSTEM_HRSG BUILDING_LAYOUT AND DETAIL DRAWING | FI | 2023-03-15 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | HRSG Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-833 | 2023-09-27 | 1 | CRS-GUP-DHI-DT-23-1620 | 2023-03-02 | NC | DE-GUP-DT-E-23-116 | 2023-02-03 | 0 | CRS-GUP-DHI-DT-23-1620 | 2023-03-02 | NC | DE-GUP-DT-E-23-833 | 2023-09-27 | 1
| GUP | FF01 | P1 | SGZ | 139709 |  | GUP-FF01-P1SGZ-139709 | FIRE EXTINGUISHER_HRSG BUILDING_LAYOUT AND DETAIL DRAWING | FI | 2023-03-15 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | HRSG Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-1152 | 2022-12-22 | 0 | CRS-GUP-DHI-DT-22-1419 | 2023-02-03 | NC | DE-GUP-DT-E-22-1152 | 2022-12-22 | 0 | CRS-GUP-DHI-DT-22-1419 | 2023-02-03 | NC
| GUP | FF03 | P1 | SGA | 137212 |  | GUP-FF03-P1SGA-137212 | INDOOR HYDRANT SYSTEM_STEAM TURBINE BUILDING_P&I DIAGRAM | FA | 2022-12-15 | 2023-04-30 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | ST Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-080 | 2023-01-27 | 0 | CRS-GUP-DHI-DT-22-1112 | 2022-11-21 | AA | DE-GUP-DT-E-22-942 | 2022-11-15 | A | CRS-GUP-DHI-DT-22-1112 | 2022-11-21 | AA | DE-GUP-DT-E-23-080 | 2023-01-27 | 0
| GUP | FF01 | P1 | SGA | 137112 |  | GUP-FF01-P1SGA-137112 | INDOOR HYDRANT SYSTEM_STEAM TURBINE BUILDING_PIPE LAYOUT AND DETAIL DRAWING | FI | 2022-12-15 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | ST Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-824 | 2023-09-22 | 2 | 자체 CRS 개정 후 제출 | 2023-09-21 | N/A | DE-GUP-DT-E-22-942 | 2022-11-15 | 0 | CRS-GUP-DHI-DT-22-1112 | 2022-11-21 | NC | DE-GUP-DT-E-23-465 | 2023-04-14 | 1 | 자체 CRS 개정 후 제출 | 2023-09-21 | N/A | DE-GUP-DT-E-23-824 | 2023-09-22 | 2
| GUP | FF05 | P1 | SGA | 137312 |  | GUP-FF05-P1SGA-137312 | INDOOR HYDRANT SYSTEM_STEAM TURBINE BUILDING_HYDRAULIC CALCULATION | FI | 2022-12-15 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | ST Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-942 | 2022-11-15 | 0 | CRS-GUP-DHI-DT-22-1112 | 2022-11-21 | NC | DE-GUP-DT-E-22-942 | 2022-11-15 | 0 | CRS-GUP-DHI-DT-22-1112 | 2022-11-21 | NC
| GUP | FF03 | P1 | SGE | 138212 |  | GUP-FF03-P1SGE-138212 | SPRINKLER SYSTEM_STEAM TURBINE BUILDING_P&I DIAGRAM | FA | 2022-12-15 | 2023-04-30 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | ST Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-362 | 2023-03-24 | 0 | CRS-GUP-DHI-DT-23-1533 | 2023-02-15 | AA | DE-GUP-DT-E-22-943 | 2022-11-15 | A | CRS-GUP-DHI-DT-22-1113 | 2022-11-21 | RC | DE-GUP-DT-E-22-1251 | 2023-01-11 | B | CRS-GUP-DHI-DT-23-1533 | 2023-02-15 | AA | DE-GUP-DT-E-23-362 | 2023-03-24 | 0
| GUP | FF01 | P1 | SGE | 138112 |  | GUP-FF01-P1SGE-138112 | SPRINKLER SYSTEM_STEAM TURBINE BUILDING_PIPE LAYOUT AND DETAIL DRAWING | FA | 2022-12-15 | 2023-04-30 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | ST Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-970 | 2023-12-05 | 2 | 자체 CRS 개정 후 제출 | 2023-12-04 | N/A | DE-GUP-DT-E-22-943 | 2022-11-15 | A | CRS-GUP-DHI-DT-22-1113 | 2022-11-21 | RC | DE-GUP-DT-E-22-1251 | 2023-01-11 | B | CRS-GUP-DHI-DT-23-1533 | 2023-02-15 | AA | DE-GUP-DT-E-23-362 | 2023-03-24 | 0 | CRS-GUP-DHI-DT-23-1533 | 2023-02-15 | AA | DE-GUP-DT-E-23-465 | 2023-04-14 | 1 | 자체 CRS 개정 후 제출 | 2023-12-04 | N/A | DE-GUP-DT-E-23-970 | 2023-12-05 | 2
| GUP | FF05 | P1 | SGE | 138312 |  | GUP-FF05-P1SGE-138312 | SPRINKLER SYSTEM_STEAM TURBINE BUILDING_HYDRAULIC CALCULATION | FI | 2022-12-15 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | ST Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-943 | 2022-11-15 | 0 | CRS-GUP-DHI-DT-22-1113 | 2022-11-21 | NC | DE-GUP-DT-E-22-943 | 2022-11-15 | 0 | CRS-GUP-DHI-DT-22-1113 | 2022-11-21 | NC
| GUP | FF03 | P1 | SGC | 138812 |  | GUP-FF03-P1SGC-138812 | WATER SPRAY SYSTEM_STEAM TURBINE BUILDING_P&I DIAGRAM | FA | 2022-12-15 | 2023-04-30 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | ST Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-790 | 2023-09-06 | 1 | 자체 CRS 개정 후 제출 | 2023-09-05 | N/A | DE-GUP-DT-E-22-1091 | 2022-12-16 | A | CRS-GUP-DHI-DT-22-1381 | 2023-01-03 | AA | DE-GUP-DT-E-23-080 | 2023-01-27 | 0 | 자체 CRS 개정 후 제출 | 2023-09-05 | N/A | DE-GUP-DT-E-23-790 | 2023-09-06 | 1
| GUP | FF01 | P1 | SGC | 138712 |  | GUP-FF01-P1SGC-138712 | WATER SPRAY SYSTEM_STEAM TURBINE BUILDING_PIPE LAYOUT AND DETAIL DRAWING | FI | 2022-12-15 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | ST Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-821 | 2023-09-22 | 2 | 자체 CRS 개정 후 제출 | 2023-09-21 | N/A | DE-GUP-DT-E-22-1091 | 2022-12-16 | 0 | CRS-GUP-DHI-DT-22-1381 | 2023-01-03 | NC | DE-GUP-DT-E-23-802 | 2023-09-07 | 1 | 자체 CRS 개정 후 제출 | 2023-09-21 | N/A | DE-GUP-DT-E-23-821 | 2023-09-22 | 2
| GUP | FF05 | P1 | SGC | 138912 |  | GUP-FF05-P1SGC-138912 | WATER SPRAY SYSTEM_STEAM TURBINE BUILDING_HYDRAULIC CALCULATION | FI | 2022-12-15 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | ST Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-1091 | 2022-12-16 | 0 | CRS-GUP-DHI-DT-22-1381 | 2023-01-03 | NC | DE-GUP-DT-E-22-1091 | 2022-12-16 | 0 | CRS-GUP-DHI-DT-22-1381 | 2023-01-03 | NC
| GUP | FF03 | P1 | SGE | 138512 |  | GUP-FF03-P1SGE-138512 | PRE-ACTION SPRINKLER_STEAM TURBINE BUILDING_P&I DIAGRAM | FA | 2022-12-15 | 2023-04-30 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | ST Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-362 | 2023-03-24 | 0 | CRS-GUP-DHI-DT-22-1421 | 2023-02-03 | AA | DE-GUP-DT-E-22-944 | 2022-11-15 | A | CRS-GUP-DHI-DT-22-1114 | 2022-11-21 | RC | DE-GUP-DT-E-22-1182 | 2022-12-23 | B | CRS-GUP-DHI-DT-22-1421 | 2023-02-03 | AA | DE-GUP-DT-E-23-362 | 2023-03-24 | 0
| GUP | FF01 | P1 | SGE | 138412 |  | GUP-FF01-P1SGE-138412 | PRE-ACTION SPRINKLER_STEAM TURBINE BUILDING_PIPE LAYOUT AND DETAIL DRAWING | FI | 2022-12-15 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | ST Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-752 | 2023-08-23 | 2 | CRS-GUP-DHI-DT-22-1421 | 2023-02-03 | NC | DE-GUP-DT-E-22-944 | 2022-11-15 | 0 | CRS-GUP-DHI-DT-22-1114 | 2022-11-21 | RC | DE-GUP-DT-E-22-1182 | 2022-12-23 | 1 | CRS-GUP-DHI-DT-22-1421 | 2023-02-03 | NC | DE-GUP-DT-E-23-752 | 2023-08-23 | 2
| GUP | FF05 | P1 | SGE | 138612 |  | GUP-FF05-P1SGE-138612 | PRE-ACTION SPRINKLER_STEAM TURBINE BUILDING_HYDRAULIC CALCULATION | FI | 2022-12-15 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | ST Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-1182 | 2022-12-23 | 1 | CRS-GUP-DHI-DT-22-1421 | 2023-02-03 | NC | DE-GUP-DT-E-22-944 | 2022-11-15 | 0 | CRS-GUP-DHI-DT-22-1114 | 2022-11-21 | RC | DE-GUP-DT-E-22-1182 | 2022-12-23 | 1 | CRS-GUP-DHI-DT-22-1421 | 2023-02-03 | NC
| GUP | FF03 | P1 | CYE | 139912 |  | GUP-FF03-P1CYE-139912 | FIRE DETECTION AND ALARM SYSTEM_STEAM TURBINE BUILDING_SINGLE LINE DIAGRAM | FI | 2022-12-15 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | ST Building | FF | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-841 | 2023-10-10 | 2 | 자체 CRS 개정 후 제출 | 2023-10-09 | N/A | DE-GUP-DT-E-22-1091 | 2022-12-16 | 0 | CRS-GUP-DHI-DT-22-1381 | 2023-01-03 | NC | DE-GUP-DT-E-23-763 | 2023-08-25 | 1 | 자체 CRS 개정 후 제출 | 2023-10-09 | N/A | DE-GUP-DT-E-23-841 | 2023-10-10 | 2
| GUP | FF02 | P1 | CYE | 139812 |  | GUP-FF02-P1CYE-139812 | FIRE DETECTION AND ALARM SYSTEM_STEAM TURBINE BUILDING_LAYOUT AND DETAIL DRAWING | FI | 2022-12-15 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | ST Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-841 | 2023-10-10 | 2 | 자체 CRS 개정 후 제출 | 2023-10-09 | N/A | DE-GUP-DT-E-22-1091 | 2022-12-16 | 0 | CRS-GUP-DHI-DT-22-1381 | 2023-01-03 | NC | DE-GUP-DT-E-23-763 | 2023-08-25 | 1 | 자체 CRS 개정 후 제출 | 2023-10-09 | N/A | DE-GUP-DT-E-23-841 | 2023-10-10 | 2
| GUP | FF01 | P1 | SGZ | 139712 |  | GUP-FF01-P1SGZ-139712 | FIRE EXTINGUISHER_STEAM TURBINE BUILDING_LAYOUT AND DETAIL DRAWING | FI | 2022-12-15 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | ST Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-933 | 2023-11-23 | 2 | 자체 CRS 개정 후 제출 | 2023-09-21 | N/A | DE-GUP-DT-E-22-1091 | 2022-12-16 | 0 | CRS-GUP-DHI-DT-22-1381 | 2023-01-03 | NC | DE-GUP-DT-E-23-465 | 2023-04-14 | 1 | 자체 CRS 개정 후 제출 | 2023-09-21 | N/A | DE-GUP-DT-E-23-933 | 2023-11-23 | 2
| GUP | FF03 | P1 | SGA | 137207 |  | GUP-FF03-P1SGA-137207 | INDOOR HYDRANT SYSTEM_GAS TURBINE BUILDING_P&I DIAGRAM | FA | 2022-11-11 | 2023-06-12 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | GT Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-079 | 2023-01-27 | 0 | CRS-GUP-DHI-DT-22-1109 | 2022-11-21 | AA | DE-GUP-DT-E-22-886 | 2022-10-31 | A | CRS-GUP-DHI-DT-22-1109 | 2022-11-21 | AA | DE-GUP-DT-E-23-079 | 2023-01-27 | 0
| GUP | FF01 | P1 | SGA | 137107 |  | GUP-FF01-P1SGA-137107 | INDOOR HYDRANT SYSTEM_GAS TURBINE BUILDING_PIPE LAYOUT AND DETAIL DRAWING | FA | 2022-11-11 | 2023-06-12 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | GT Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-823 | 2023-09-22 | 1 | 자체 CRS 개정 후 제출 | 2023-09-21 | N/A | DE-GUP-DT-E-22-886 | 2022-10-31 | A | CRS-GUP-DHI-DT-22-1109 | 2022-11-21 | AA | DE-GUP-DT-E-23-283 | 2023-03-08 | 0 | 자체 CRS 개정 후 제출 | 2023-09-21 | N/A | DE-GUP-DT-E-23-823 | 2023-09-22 | 1
| GUP | FF05 | P1 | SGA | 137307 |  | GUP-FF05-P1SGA-137307 | INDOOR HYDRANT SYSTEM_GAS TURBINE BUILDING_HYDRAULIC CALCULATION | FI | 2022-11-11 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | GT Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-886 | 2022-10-31 | 0 | CRS-GUP-DHI-DT-22-1109 | 2022-11-21 | NC | DE-GUP-DT-E-22-886 | 2022-10-31 | 0 | CRS-GUP-DHI-DT-22-1109 | 2022-11-21 | NC
| GUP | FF03 | P1 | SGE | 132107 |  | GUP-FF03-P1SGE-132107 | SPRINKLER SYSTEM_GAS TURBINE BUILDING_P&I DIAGRAM | FA | 2022-11-11 | 2023-06-12 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | GT Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-362 | 2023-03-24 | 0 | CRS-GUP-DHI-DT-23-1562 | 2023-02-23 | AA | DE-GUP-DT-E-22-886 | 2022-10-31 | A | CRS-GUP-DHI-DT-22-1109 | 2022-11-21 | RC | DE-GUP-DT-E-22-1099 | 2022-12-16 | B | CRS-GUP-DHI-DT-22-1343 | 2022-12-28 | RC | DE-GUP-DT-E-23-052 | 2023-01-19 | C | CRS-GUP-DHI-DT-23-1562 | 2023-02-23 | AA | DE-GUP-DT-E-23-362 | 2023-03-24 | 0
| GUP | FF01 | P1 | SGE | 132207 |  | GUP-FF01-P1SGE-132207 | SPRINKLER SYSTEM_GAS TURBINE BUILDING_PIPE LAYOUT AND DETAIL DRAWING | FA | 2022-11-11 | 2023-06-12 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | GT Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-362 | 2023-03-24 | 0 | 자체 CRS 개정 후 제출 | 2023-09-21 | N/A | DE-GUP-DT-E-22-886 | 2022-10-31 | A | CRS-GUP-DHI-DT-22-1109 | 2022-11-21 | RC | DE-GUP-DT-E-22-1099 | 2022-12-16 | B | CRS-GUP-DHI-DT-22-1343 | 2022-12-28 | RC | DE-GUP-DT-E-23-052 | 2023-01-19 | C | CRS-GUP-DHI-DT-23-1562 | 2023-02-23 | AA | DE-GUP-DT-E-23-362 | 2023-03-24 | 0 | 자체 CRS 개정 후 제출 | 2023-09-21 | N/A | DE-GUP-DT-E-23-823 | 2023-09-22 | 1
| GUP | FF05 | P1 | SGE | 132307 |  | GUP-FF05-P1SGE-132307 | SPRINKLER SYSTEM_GAS TURBINE BUILDING_HYDRAULIC CALCULATION | FI | 2022-11-11 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | GT Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-1099 | 2022-12-16 | 1 | CRS-GUP-DHI-DT-22-1343 | 2022-12-28 | NC | DE-GUP-DT-E-22-886 | 2022-10-31 | 0 | CRS-GUP-DHI-DT-22-1109 | 2022-11-21 | RC | DE-GUP-DT-E-22-1099 | 2022-12-16 | 1 | CRS-GUP-DHI-DT-22-1343 | 2022-12-28 | NC
| GUP | FF03 | P1 | CYE | 139907 |  | GUP-FF03-P1CYE-139907 | FIRE DETECTION AND ALARM SYSTEM_GAS TURBINE BUILDING_SINGLE LINE DIAGRAM | FI | 2022-11-11 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | GT Building | FF | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-25-017 | 2025-01-22 | 5 | 자체 CRS 개정 후 제출 | 2025-01-21 | N/A | DE-GUP-DT-E-22-930 | 2022-11-10 | 0 | CRS-GUP-DHI-DT-22-1110 | 2022-11-21 | RC | DE-GUP-DT-E-22-1183 | 2022-12-23 | 1 | CRS-GUP-DHI-DT-23-1553 | 2023-02-23 | NC | DE-GUP-DT-E-23-776 | 2023-08-29 | 2 | 자체 CRS 개정 후 제출 | 2023-10-09 | N/A | DE-GUP-DT-E-23-840 | 2023-10-10 | 3 | 자체 CRS 개정 후 제출 | 2024-01-17 | N/A | DE-GUP-DT-E-24-016 | 2024-01-18 | 4 | 자체 CRS 개정 후 제출 | 2025-01-21 | N/A | DE-GUP-DT-E-25-017 | 2025-01-22 | 5
| GUP | FF02 | P1 | CYE | 139807 |  | GUP-FF02-P1CYE-139807 | FIRE DETECTION AND ALARM SYSTEM_GAS TURBINE BUILDING_LAYOUT AND DETAIL DRAWING | FI | 2022-11-11 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | GT Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-25-017 | 2025-01-22 | 5 | 자체 CRS 개정 후 제출 | 2025-01-21 | N/A | DE-GUP-DT-E-22-930 | 2022-11-10 | 0 | CRS-GUP-DHI-DT-22-1110 | 2022-11-21 | RC | DE-GUP-DT-E-22-1183 | 2022-12-23 | 1 | CRS-GUP-DHI-DT-22-1420 | 2023-02-03 | NC | DE-GUP-DT-E-23-745 | 2023-08-17 | 2 | 자체 CRS 개정 후 제출 | 2023-10-09 | N/A | DE-GUP-DT-E-23-840 | 2023-10-10 | 3 | 자체 CRS 개정 후 제출 | 2024-01-17 | N/A | DE-GUP-DT-E-24-016 | 2024-01-18 | 4 | 자체 CRS 개정 후 제출 | 2025-01-21 | N/A | DE-GUP-DT-E-25-017 | 2025-01-22 | 5
| GUP | FF01 | P1 | SGZ | 139707 |  | GUP-FF01-P1SGZ-139707 | FIRE EXTINGUISHER_GAS TURBINE BUILDING_LAYOUT AND DETAIL DRAWING | FI | 2022-11-11 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | GT Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-933 | 2023-11-23 | 2 | 자체 CRS 개정 후 제출 | 2023-09-21 | N/A | DE-GUP-DT-E-22-886 | 2022-10-31 | 0 | CRS-GUP-DHI-DT-22-1109 | 2022-11-21 | NC | DE-GUP-DT-E-23-469 | 2023-04-14 | 1 | 자체 CRS 개정 후 제출 | 2023-09-21 | N/A | DE-GUP-DT-E-23-933 | 2023-11-23 | 2
| GUP | FF03 | P1 | SGA | 137203 |  | GUP-FF03-P1SGA-137203 | INDOOR HYDRANT SYSTEM_BESS ELECTRICAL & CONTROL BUILDING_P&I DIAGRAM | FA | 2023-04-08 | 2023-08-10 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | BESS Building | FF | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-293 | 2023-03-10 | 0 | CRS-GUP-DHI-DT-22-1418 | 2023-02-03 | AA | DE-GUP-DT-E-22-1150 | 2022-12-22 | A | CRS-GUP-DHI-DT-22-1418 | 2023-02-03 | AA | DE-GUP-DT-E-23-293 | 2023-03-10 | 0
| GUP | FF01 | P1 | SGA | 137103 |  | GUP-FF01-P1SGA-137103 | INDOOR HYDRANT SYSTEM_BESS ELECTRICAL & CONTROL BUILDING_PIPE LAYOUT AND DETAIL DRAWING | FA | 2023-04-08 | 2023-08-10 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | BESS Building | FF | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-790 | 2023-09-06 | 1 | 자체 CRS 개정 후 제출 | 2023-09-05 | N/A | DE-GUP-DT-E-22-1150 | 2022-12-22 | A | CRS-GUP-DHI-DT-22-1418 | 2023-02-03 | AA | DE-GUP-DT-E-23-293 | 2023-03-10 | 0 | 자체 CRS 개정 후 제출 | 2023-09-05 | N/A | DE-GUP-DT-E-23-790 | 2023-09-06 | 1
| GUP | FF05 | P1 | SGA | 137303 |  | GUP-FF05-P1SGA-137303 | INDOOR HYDRANT SYSTEM_BESS ELECTRICAL & CONTROL BUILDING_HYDRAULIC CALCULATION | FI | 2023-04-08 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | BESS Building | FF | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-22-1150 | 2022-12-22 | 0 | CRS-GUP-DHI-DT-22-1418 | 2023-02-03 | NC | DE-GUP-DT-E-22-1150 | 2022-12-22 | 0 | CRS-GUP-DHI-DT-22-1418 | 2023-02-03 | NC
| GUP | FF03 | P1 | SGK | 139203 |  | GUP-FF03-P1SGK-139203 | CLEAN AGENT SYSTEM_BESS ELECTRICAL & CONTROL BUILDING_P&I DIAGRAM | FA | 2023-04-08 | 2023-08-10 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | BESS Building | FF | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-768 | 2023-08-25 | 1 | 자체 CRS 개정 후 제출) | 2023-08-24 | N/A | DE-GUP-DT-E-22-1150 | 2022-12-22 | A | CRS-GUP-DHI-DT-22-1418 | 2023-02-03 | AA | DE-GUP-DT-E-23-293 | 2023-03-10 | 0 | 자체 CRS 개정 후 제출) | 2023-08-24 | N/A | DE-GUP-DT-E-23-768 | 2023-08-25 | 1
| GUP | FF01 | P1 | SGK | 139103 |  | GUP-FF01-P1SGK-139103 | CLEAN AGENT SYSTEM_BESS ELECTRICAL & CONTROL BUILDING_PIPE LAYOUT AND DETAIL DRAWING | FI | 2023-04-08 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | BESS Building | FF | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-768 | 2023-08-25 | 1 | CRS-GUP-DHI-DT-22-1418 | 2023-02-03 | NC | DE-GUP-DT-E-22-1150 | 2022-12-22 | 0 | CRS-GUP-DHI-DT-22-1418 | 2023-02-03 | NC | DE-GUP-DT-E-23-768 | 2023-08-25 | 1
| GUP | FF05 | P1 | SGK | 139303 |  | GUP-FF05-P1SGK-139303 | CLEAN AGENT SYSTEM_BESS ELECTRICAL & CONTROL BUILDING_HYDRAULIC CALCULATION | FI | 2023-04-08 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | BESS Building | FF | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-22-1150 | 2022-12-22 | 0 | CRS-GUP-DHI-DT-22-1418 | 2023-02-03 | NC | DE-GUP-DT-E-22-1150 | 2022-12-22 | 0 | CRS-GUP-DHI-DT-22-1418 | 2023-02-03 | NC
| GUP | FF03 | P1 | CYE | 139903 |  | GUP-FF03-P1CYE-139903 | FIRE DETECTION AND ALARM SYSTEM_BESS ELECTRICAL & CONTROL BUILDING_SINGLE LINE DIAGRAM | FI | 2023-04-08 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | BESS Building | FF | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-876 | 2023-10-30 | 2 | 자체 CRS 개정 후 제출) | 2023-10-29 | N/A | DE-GUP-DT-E-22-1150 | 2022-12-22 | 0 | CRS-GUP-DHI-DT-22-1418 | 2023-02-03 | NC | DE-GUP-DT-E-23-750 | 2023-08-22 | 1 | 자체 CRS 개정 후 제출) | 2023-10-29 | N/A | DE-GUP-DT-E-23-876 | 2023-10-30 | 2
| GUP | FF02 | P1 | CYE | 139803 |  | GUP-FF02-P1CYE-139803 | FIRE DETECTION AND ALARM SYSTEM_BESS ELECTRICAL & CONTROL BUILDING_LAYOUT AND DETAIL DRAWING | FI | 2023-04-08 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | BESS Building | FF | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-750 | 2023-08-22 | 1 | CRS-GUP-DHI-DT-22-1418 | 2023-02-03 | NC | DE-GUP-DT-E-22-1150 | 2022-12-22 | 0 | CRS-GUP-DHI-DT-22-1418 | 2023-02-03 | NC | DE-GUP-DT-E-23-750 | 2023-08-22 | 1
| GUP | FF01 | P1 | SGZ | 139703 |  | GUP-FF01-P1SGZ-139703 | FIRE EXTINGUISHER_BESS ELECTRICAL & CONTROL BUILDING_LAYOUT AND DETAIL DRAWING | FI | 2023-04-08 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | BESS Building | FF | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-933 | 2023-11-23 | 2 | 자체 CRS 개정 후 제출) | 2023-11-22 | N/A | DE-GUP-DT-E-22-1150 | 2022-12-22 | 0 | CRS-GUP-DHI-DT-22-1418 | 2023-02-03 | NC | DE-GUP-DT-E-23-469 | 2023-04-14 | 1 | 자체 CRS 개정 후 제출) | 2023-11-22 | N/A | DE-GUP-DT-E-23-933 | 2023-11-23 | 2
| GUP | FF03 | P1 | SGA | 137213 |  | GUP-FF03-P1SGA-137213 | INDOOR HYDRANT SYSTEM_SWITCHYARD CONTROL BUILDING_P&I DIAGRAM | FA | 2022-09-12 | 2023-01-19 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | SWYD Building | FF | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-073 | 2023-01-26 | 0 | CRS-GUP-DHI-DT-22-971 | 2022-11-07 | AA | DE-GUP-DT-E-22-674 | 2022-09-16 | A | CRS-GUP-DHI-DT-22-971 | 2022-11-07 | AA | DE-GUP-DT-E-23-073 | 2023-01-26 | 0
| GUP | FF01 | P1 | SGA | 137113 |  | GUP-FF01-P1SGA-137113 | INDOOR HYDRANT SYSTEM_SWITCHYARD CONTROL BUILDING_PIPE LAYOUT AND DETAIL DRAWING | FA | 2022-09-12 | 2023-01-19 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | SWYD Building | FF | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-753 | 2023-08-23 | 1 | 자체 CRS 개정 후 제출) | 2023-08-22 | N/A | DE-GUP-DT-E-22-671 | 2022-09-16 | A | CRS-GUP-DHI-DT-22-910 | 2022-10-19 | RC | DE-GUP-DT-E-22-1041 | 2022-12-08 | B | CRS-GUP-DHI-DT-22-1316 | 2022-12-22 | AA | DE-GUP-DT-E-23-184 | 2023-02-16 | 0 | 자체 CRS 개정 후 제출) | 2023-08-22 | N/A | DE-GUP-DT-E-23-753 | 2023-08-23 | 1
| GUP | FF05 | P1 | SGA | 137313 |  | GUP-FF05-P1SGA-137313 | INDOOR HYDRANT SYSTEM_SWITCHYARD CONTROL BUILDING_HYDRAULIC CALCULATION | FI | 2022-09-12 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | SWYD Building | FF | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-22-665 | 2022-09-15 | 0 | CRS-GUP-DHI-DT-22-902 | 2022-10-12 | NC | DE-GUP-DT-E-22-665 | 2022-09-15 | 0 | CRS-GUP-DHI-DT-22-902 | 2022-10-12 | NC
| GUP | FF03 | P1 | SGK | 139213 |  | GUP-FF03-P1SGK-139213 | CLEAN AGENT SYSTEM_SWITCHYARD CONTROL BUILDING_P&I DIAGRAM | FA | 2022-09-12 | 2023-01-19 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | SWYD Building | FF | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-765 | 2023-08-25 | 1 | 자체 CRS 개정 후 제출) | 2023-08-23 | N/A | DE-GUP-DT-E-22-697 | 2022-09-23 | A | CRS-GUP-DHI-DT-22-914 | 2022-10-19 | RC | DE-GUP-DT-E-22-1040 | 2022-12-08 | B | CRS-GUP-DHI-DT-22-1315 | 2022-12-22 | AA | DE-GUP-DT-E-23-073 | 2023-01-26 | 0 | 자체 CRS 개정 후 제출) | 2023-08-23 | N/A | DE-GUP-DT-E-23-765 | 2023-08-25 | 1
| GUP | FF01 | P1 | SGK | 139113 |  | GUP-FF01-P1SGK-139113 | CLEAN AGENT SYSTEM_SWITCHYARD CONTROL BUILDING_PIPE LAYOUT AND DETAIL DRAWING | FI | 2022-09-12 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | SWYD Building | FF | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-24-055 | 2024-02-23 | 3 | 자체 CRS 개정 후 제출) | 2024-02-22 | N/A | DE-GUP-DT-E-22-673 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-911 | 2022-10-19 | RC | DE-GUP-DT-E-22-1040 | 2022-12-08 | 1 | CRS-GUP-DHI-DT-22-1315 | 2022-12-22 | NC | DE-GUP-DT-E-23-753 | 2023-08-23 | 2 | 자체 CRS 개정 후 제출) | 2024-02-22 | N/A | DE-GUP-DT-E-24-055 | 2024-02-23 | 3
| GUP | FF05 | P1 | SGK | 139313 |  | GUP-FF05-P1SGK-139313 | CLEAN AGENT SYSTEM_SWITCHYARD CONTROL BUILDING_FLOW CALCULATION | FA | 2022-09-12 | 2023-01-19 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | SWYD Building | FF | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-137 | 2023-02-07 | 0 | CRS-GUP-DHI-DT-22-1315 | 2022-12-22 | AA | DE-GUP-DT-E-22-674 | 2022-09-16 | A | CRS-GUP-DHI-DT-22-971 | 2022-11-07 | AA | DE-GUP-DT-E-22-1040 | 2022-12-08 | B | CRS-GUP-DHI-DT-22-1315 | 2022-12-22 | AA | DE-GUP-DT-E-23-137 | 2023-02-07 | 0
| GUP | FF03 | P1 | CYE | 139913 |  | GUP-FF03-P1CYE-139913 | FIRE DETECTION AND ALARM SYSTEM_SWITCHYARD CONTROL BUILDING_SINGLE LINE DIAGRAM | FI | 2022-09-12 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | SWYD Building | FF | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-876 | 2023-10-30 | 3 | 자체 CRS 개정 후 제출) | 2023-10-29 | N/A | DE-GUP-DT-E-22-697 | 2022-09-23 | 0 | CRS-GUP-DHI-DT-22-914 | 2022-10-19 | RC | DE-GUP-DT-E-22-1042 | 2022-12-08 | 1 | CRS-GUP-DHI-DT-22-1317 | 2022-12-22 | NC | DE-GUP-DT-E-23-466 | 2023-04-14 | 2 | 자체 CRS 개정 후 제출) | 2023-10-29 | N/A | DE-GUP-DT-E-23-876 | 2023-10-30 | 3
| GUP | FF02 | P1 | CYE | 139813 |  | GUP-FF02-P1CYE-139813 | FIRE DETECTION AND ALARM SYSTEM_SWITCHYARD CONTROL BUILDING_LAYOUT AND DETAIL DRAWING | FI | 2022-09-12 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | SWYD Building | FF | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-466 | 2023-04-14 | 2 | CRS-GUP-DHI-DT-22-1317 | 2022-12-22 | NC | DE-GUP-DT-E-22-697 | 2022-09-23 | 0 | CRS-GUP-DHI-DT-22-914 | 2022-10-19 | RC | DE-GUP-DT-E-22-1042 | 2022-12-08 | 1 | CRS-GUP-DHI-DT-22-1317 | 2022-12-22 | NC | DE-GUP-DT-E-23-466 | 2023-04-14 | 2
| GUP | FF01 | P1 | SGZ | 139713 |  | GUP-FF01-P1SGZ-139713 | FIRE EXTINGUISHER_SWITCHYARD CONTROL BUILDING_LAYOUT AND DETAIL DRAWING | FI | 2022-09-12 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | SWYD Building | FF | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-933 | 2023-11-23 | 2 | 자체 CRS 개정 후 제출 | 2023-09-21 | N/A | DE-GUP-DT-E-22-671 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-910 | 2022-10-19 | NC | DE-GUP-DT-E-23-466 | 2023-04-14 | 1 | 자체 CRS 개정 후 제출 | 2023-09-21 | N/A | DE-GUP-DT-E-23-933 | 2023-11-23 | 2
| GUP | FF03 | P1 | CYE | 139908 |  | GUP-FF03-P1CYE-139908 | FIRE DETECTION AND ALARM SYSTEM_GATE HOUSE_SINGLE LINE DIAGRAM | FI | 2023-09-10 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | Gate House | FF | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-373 | 2023-03-27 | 0 | CRS-GUP-DHI-DT-23-1845 | 2023-04-19 | NC | DE-GUP-DT-E-23-373 | 2023-03-27 | 0 | CRS-GUP-DHI-DT-23-1845 | 2023-04-19 | NC
| GUP | FF02 | P1 | CYE | 139808 |  | GUP-FF02-P1CYE-139808 | FIRE DETECTION AND ALARM SYSTEM_GATE HOUSE_LAYOUT AND DETAIL DRAWING | FI | 2023-09-10 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | Gate House | FF | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-373 | 2023-03-27 | 0 | CRS-GUP-DHI-DT-23-1845 | 2023-04-19 | NC | DE-GUP-DT-E-23-373 | 2023-03-27 | 0 | CRS-GUP-DHI-DT-23-1845 | 2023-04-19 | NC
| GUP | FF01 | P1 | SGZ | 139708 |  | GUP-FF01-P1SGZ-139708 | FIRE EXTINGUISHER_GATE HOUSE_LAYOUT AND DETAIL DRAWING | FI | 2023-09-10 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Gate House | FF | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-921 | 2023-11-20 | 1 | CRS-GUP-DHI-DT-23-1699 | 2023-03-14 | NC | DE-GUP-DT-E-23-223 | 2023-02-22 | 0 | CRS-GUP-DHI-DT-23-1699 | 2023-03-14 | NC | DE-GUP-DT-E-23-921 | 2023-11-20 | 1
| GUP | FF03 | P1 | SGA | 137202 |  | GUP-FF03-P1SGA-137202 | INDOOR HYDRANT SYSTEM_CONTROL & ELECTRICAL BUILDING_P&I DIAGRAM | FA | 2022-09-13 | 2023-01-31 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | C&E Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-24-166 | 2024-06-27 | 1 | 자체 CRS 개정 후 제출 | 2024-06-26 | N/A | DE-GUP-DT-E-22-695 | 2022-09-23 | A | CRS-GUP-DHI-DT-22-972 | 2022-11-07 | AA | DE-GUP-DT-E-23-071 | 2023-01-26 | 0 | 자체 CRS 개정 후 제출 | 2024-06-26 | N/A | DE-GUP-DT-E-24-166 | 2024-06-27 | 1
| GUP | FF01 | P1 | SGA | 137102 |  | GUP-FF01-P1SGA-137102 | INDOOR HYDRANT SYSTEM_CONTROL & ELECTRICAL BUILDING_PIPE LAYOUT AND DETAIL DRAWING | FA | 2022-09-13 | 2023-01-31 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | C&E Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-785 | 2023-09-01 | 1 | 자체 CRS 개정 후 제출) | 2023-08-31 | N/A | DE-GUP-DT-E-22-673 | 2022-09-16 | A | CRS-GUP-DHI-DT-22-911 | 2022-10-19 | RC | DE-GUP-DT-E-22-1039 | 2022-12-08 | B | CRS-GUP-DHI-DT-22-1314 | 2022-12-22 | AA | DE-GUP-DT-E-23-138 | 2023-02-07 | 0 | 자체 CRS 개정 후 제출) | 2023-08-31 | N/A | DE-GUP-DT-E-23-785 | 2023-09-01 | 1
| GUP | FF05 | P1 | SGA | 137302 |  | GUP-FF05-P1SGA-137302 | INDOOR HYDRANT SYSTEM_CONTROL & ELECTRICAL BUILDING_HYDRAULIC CALCULATION | FI | 2022-09-13 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | C&E Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-1039 | 2022-12-08 | 1 | CRS-GUP-DHI-DT-22-1314 | 2022-12-22 | NC | DE-GUP-DT-E-22-673 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-911 | 2022-10-19 | RC | DE-GUP-DT-E-22-1039 | 2022-12-08 | 1 | CRS-GUP-DHI-DT-22-1314 | 2022-12-22 | NC
| GUP | FF03 | P1 | SGE | 138202 |  | GUP-FF03-P1SGE-138202 | SPRINKLER SYSTEM_CONTROL & ELECTRICAL BUILDING_P&I DIAGRAM | FA | 2022-09-13 | 2023-01-31 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | C&E Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-283 | 2023-03-08 | 0 | CRS-GUP-DHI-DT-23-1561 | 2023-02-23 | AA | DE-GUP-DT-E-22-695 | 2022-09-23 | A | CRS-GUP-DHI-DT-22-1065 | 2022-11-19 | RC | DE-GUP-DT-E-22-1098 | 2022-12-16 | B | CRS-GUP-DHI-DT-22-1342 | 2022-12-28 | RC | DE-GUP-DT-E-23-051 | 2023-01-19 | C | CRS-GUP-DHI-DT-23-1561 | 2023-02-23 | AA | DE-GUP-DT-E-23-283 | 2023-03-08 | 0
| GUP | FF01 | P1 | SGE | 138102 |  | GUP-FF01-P1SGE-138102 | SPRINKLER SYSTEM_CONTROL & ELECTRICAL BUILDING_PIPE LAYOUT AND DETAIL DRAWING | FI | 2022-09-13 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | C&E Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-785 | 2023-09-01 | 3 | CRS-GUP-DHI-DT-23-1561 | 2023-02-23 | NC | DE-GUP-DT-E-22-695 | 2022-09-23 | 0 | CRS-GUP-DHI-DT-22-1065 | 2022-11-19 | RC | DE-GUP-DT-E-22-1098 | 2022-12-16 | 1 | CRS-GUP-DHI-DT-22-1342 | 2022-12-28 | RC | DE-GUP-DT-E-23-051 | 2023-01-19 | 2 | CRS-GUP-DHI-DT-23-1561 | 2023-02-23 | NC | DE-GUP-DT-E-23-785 | 2023-09-01 | 3
| GUP | FF05 | P1 | SGE | 138302 |  | GUP-FF05-P1SGE-138302 | SPRINKLER SYSTEM_CONTROL & ELECTRICAL BUILDING_HYDRAULIC CALCULATION | FI | 2022-09-13 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | C&E Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-695 | 2022-09-23 | 0 | CRS-GUP-DHI-DT-22-972 | 2022-11-07 | NC | DE-GUP-DT-E-22-695 | 2022-09-23 | 0 | CRS-GUP-DHI-DT-22-972 | 2022-11-07 | NC
| GUP | FF03 | P1 | SGK | 139202 |  | GUP-FF03-P1SGK-139202 | CLEAN AGENT SYSTEM_CONTROL & ELECTRICAL BUILDING_P&I DIAGRAM | FA | 2022-09-13 | 2023-01-31 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | C&E Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-785 | 2023-09-01 | 1 | 자체 CRS 개정 후 제출) | 2023-08-31 | N/A | DE-GUP-DT-E-22-695 | 2022-09-23 | A | CRS-GUP-DHI-DT-22-1065 | 2022-11-19 | RC | DE-GUP-DT-E-22-1098 | 2022-12-16 | B | CRS-GUP-DHI-DT-22-1342 | 2022-12-28 | AA | DE-GUP-DT-E-23-071 | 2023-01-26 | 0 | 자체 CRS 개정 후 제출) | 2023-08-31 | N/A | DE-GUP-DT-E-23-785 | 2023-09-01 | 1
| GUP | FF01 | P1 | SGK | 139102 |  | GUP-FF01-P1SGK-139102 | CLEAN AGENT SYSTEM_CONTROL & ELECTRICAL BUILDING_PIPE LAYOUT AND DETAIL DRAWING | FI | 2022-09-13 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | C&E Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-24-165 | 2024-06-27 | 4 | 자체 CRS 개정 후 제출 | 2024-06-26 | N/A | DE-GUP-DT-E-22-695 | 2022-09-23 | 0 | CRS-GUP-DHI-DT-22-1065 | 2022-11-19 | RC | DE-GUP-DT-E-22-1098 | 2022-12-16 | 1 | CRS-GUP-DHI-DT-22-1342 | 2022-12-28 | NC | DE-GUP-DT-E-23-785 | 2023-09-01 | 2 | 자체 CRS 개정 후 제출) | 2023-10-18 | N/A | DE-GUP-DT-E-23-858 | 2023-10-19 | 3 | 자체 CRS 개정 후 제출 | 2024-06-26 | N/A | DE-GUP-DT-E-24-165 | 2024-06-27 | 4
| GUP | FF05 | P1 | SGK | 139302 |  | GUP-FF05-P1SGK-139302 | CLEAN AGENT SYSTEM_CONTROL & ELECTRICAL BUILDING_FLOW CALCULATION | FI | 2022-09-13 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | C&E Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-674 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-971 | 2022-11-07 | NC | DE-GUP-DT-E-22-674 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-971 | 2022-11-07 | NC
| GUP | FF03 | P1 | CYE | 139902 |  | GUP-FF03-P1CYE-139902 | FIRE DETECTION AND ALARM SYSTEM_CONTROL & ELECTRICAL BUILDING_SINGLE LINE DIAGRAM | FI | 2022-09-13 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | C&E Building | FF | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-24-067 | 2024-03-07 | 4 | 자체 CRS 개정 후 제출 | 2024-03-06 | N/A | DE-GUP-DT-E-22-695 | 2022-09-23 | 0 | CRS-GUP-DHI-DT-22-972 | 2022-11-07 | RC | DE-GUP-DT-E-22-1175 | 2022-12-23 | 1 | CRS-GUP-DHI-DT-22-1424 | 2023-02-03 | NC | DE-GUP-DT-E-23-460 | 2023-04-14 | 2 | CRS-GUP-DHI-DT-23-1889 | 2023-05-02 | NC | DE-GUP-DT-E-23-831 | 2023-09-27 | 3 | 자체 CRS 개정 후 제출 | 2024-03-06 | N/A | DE-GUP-DT-E-24-067 | 2024-03-07 | 4
| GUP | FF02 | P1 | CYE | 139802 |  | GUP-FF02-P1CYE-139802 | FIRE DETECTION AND ALARM SYSTEM_CONTROL & ELECTRICAL BUILDING_LAYOUT AND DETAIL DRAWING | FI | 2022-09-13 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | C&E Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-831 | 2023-09-27 | 3 | CRS-GUP-DHI-DT-23-1889 | 2023-05-02 | NC | DE-GUP-DT-E-22-695 | 2022-09-23 | 0 | CRS-GUP-DHI-DT-22-972 | 2022-11-07 | RC | DE-GUP-DT-E-22-1175 | 2022-12-23 | 1 | CRS-GUP-DHI-DT-22-1424 | 2023-02-03 | NC | DE-GUP-DT-E-23-460 | 2023-04-14 | 2 | CRS-GUP-DHI-DT-23-1889 | 2023-05-02 | NC | DE-GUP-DT-E-23-831 | 2023-09-27 | 3
| GUP | FF01 | P1 | SGZ | 139702 |  | GUP-FF01-P1SGZ-139702 | FIRE EXTINGUISHER_CONTROL & ELECTRICAL BUILDING_LAYOUT AND DETAIL DRAWING | FI | 2022-09-13 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | C&E Building | FF | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-933 | 2023-11-23 | 4 | CRS-GUP-DHI-DT-23-1889 | 2023-05-02 | NC | DE-GUP-DT-E-22-674 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-971 | 2022-11-07 | NC | DE-GUP-DT-E-22-1098 | 2022-12-16 | 1 | CRS-GUP-DHI-DT-22-1342 | 2022-12-28 | RC | DE-GUP-DT-E-23-051 | 2023-01-19 | 2 | CRS-GUP-DHI-DT-23-1561 | 2023-02-23 | NC | DE-GUP-DT-E-23-460 | 2023-04-14 | 3 | CRS-GUP-DHI-DT-23-1889 | 2023-05-02 | NC | DE-GUP-DT-E-23-933 | 2023-11-23 | 4
| GUP | FF03 | P1 | CYE | 139905 |  | GUP-FF03-P1CYE-139905 | FIRE DETECTION AND ALARM SYSTEM_FOAM STATION SHELTER_SINGLE LINE DIAGRAM | FI | 2023-03-15 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Foam shelter | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-289 | 2024-12-06 | 1 | CRS-GUP-DHI-DT-23-1417 | 2023-01-30 | NC | DE-GUP-DT-E-22-1151 | 2022-12-22 | 0 | CRS-GUP-DHI-DT-23-1417 | 2023-01-30 | NC | DE-GUP-DT-E-24-289 | 2024-12-06 | 1
| GUP | FF02 | P1 | CYE | 139805 |  | GUP-FF02-P1CYE-139805 | FIRE DETECTION AND ALARM SYSTEM_FOAM STATION SHELTER_LAYOUT AND DETAIL DRAWING | FI | 2023-03-15 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | Foam shelter | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-1151 | 2022-12-22 | 0 | CRS-GUP-DHI-DT-23-1417 | 2023-01-30 | NC | DE-GUP-DT-E-22-1151 | 2022-12-22 | 0 | CRS-GUP-DHI-DT-23-1417 | 2023-01-30 | NC
| GUP | FF03 | P1 | SGA | 137204 |  | GUP-FF03-P1SGA-137204 | INDOOR HYDRANT SYSTEM_FIRE PROTECTION PUMP BUILDING_P&I DIAGRAM | FA | 2022-10-31 | 2023-03-08 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Fire Protection Pump Building | FF | 2 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-072 | 2023-01-26 | 0 | CRS-GUP-DHI-DT-22-975 | 2022-11-07 | AA | DE-GUP-DT-E-22-777 | 2022-10-11 | A | CRS-GUP-DHI-DT-22-975 | 2022-11-07 | AA | DE-GUP-DT-E-23-072 | 2023-01-26 | 0
| GUP | FF01 | P1 | SGA | 137104 |  | GUP-FF01-P1SGA-137104 | INDOOR HYDRANT SYSTEM_FIRE PROTECTION PUMP BUILDING_PIPE LAYOUT AND DETAIL DRAWING | FI | 2022-10-31 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Fire Protection Pump Building | FF | 2 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-883 | 2023-11-07 | 2 | CRS-GUP-DHI-DT-23-1745 | 2023-03-17 | NC | DE-GUP-DT-E-22-777 | 2022-10-11 | 0 | CRS-GUP-DHI-DT-22-975 | 2022-11-07 | RC | DE-GUP-DT-E-23-256 | 2023-02-28 | 1 | CRS-GUP-DHI-DT-23-1745 | 2023-03-17 | NC | DE-GUP-DT-E-23-883 | 2023-11-07 | 2
| GUP | FF05 | P1 | SGA | 137304 |  | GUP-FF05-P1SGA-137304 | INDOOR HYDRANT SYSTEM_FIRE PROTECTION PUMP BUILDING_HYDRAULIC CALCULATION | FI | 2022-10-31 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Fire Protection Pump Building | FF | 2 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-256 | 2023-02-28 | 1 | CRS-GUP-DHI-DT-23-1745 | 2023-03-17 | NC | DE-GUP-DT-E-22-777 | 2022-10-11 | 0 | CRS-GUP-DHI-DT-22-975 | 2022-11-07 | RC | DE-GUP-DT-E-23-256 | 2023-02-28 | 1 | CRS-GUP-DHI-DT-23-1745 | 2023-03-17 | NC
| GUP | FF03 | P1 | SGE | 138204 |  | GUP-FF03-P1SGE-138204 | SPRINKLER SYSTEM_FIRE PROTECTION PUMP BUILDING_P&I DIAGRAM | FA | 2022-10-31 | 2023-03-08 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Fire Protection Pump Building | FF | 2 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-362 | 2023-03-24 | 0 | CRS-GUP-DHI-DT-23-1532 | 2023-02-15 | AA | DE-GUP-DT-E-22-873 | 2022-10-28 | A | CRS-GUP-DHI-DT-22-1107 | 2022-11-21 | RC | DE-GUP-DT-E-22-1249 | 2023-01-11 | B | CRS-GUP-DHI-DT-23-1532 | 2023-02-15 | AA | DE-GUP-DT-E-23-362 | 2023-03-24 | 0
| GUP | FF01 | P1 | SGE | 138104 |  | GUP-FF01-P1SGE-138104 | SPRINKLER SYSTEM_FIRE PROTECTION PUMP BUILDING_PIPE LAYOUT AND DETAIL DRAWING | FI | 2022-10-31 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Fire Protection Pump Building | FF | 2 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-969 | 2023-12-05 | 3 | 자체 CRS 개정 후 제출 | 2023-12-04 | N/A | DE-GUP-DT-E-22-873 | 2022-10-28 | 0 | CRS-GUP-DHI-DT-22-1107 | 2022-11-21 | RC | DE-GUP-DT-E-22-1249 | 2023-01-11 | 1 | CRS-GUP-DHI-DT-23-1532 | 2023-02-15 | NC | DE-GUP-DT-E-23-463 | 2023-04-14 | 2 | 자체 CRS 개정 후 제출 | 2023-12-04 | N/A | DE-GUP-DT-E-23-969 | 2023-12-05 | 3
| GUP | FF05 | P1 | SGE | 138304 |  | GUP-FF05-P1SGE-138304 | SPRINKLER SYSTEM_FIRE PROTECTION PUMP BUILDING_HYDRAULIC CALCULATION | FI | 2022-10-31 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Fire Protection Pump Building | FF | 2 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-22-1184 | 2022-12-23 | 1 | CRS-GUP-DHI-DT-22-1425 | 2023-02-03 | NC | DE-GUP-DT-E-22-873 | 2022-10-28 | 0 | CRS-GUP-DHI-DT-22-1107 | 2022-11-21 | RC | DE-GUP-DT-E-22-1184 | 2022-12-23 | 1 | CRS-GUP-DHI-DT-22-1425 | 2023-02-03 | NC
| GUP | FF03 | P1 | CYE | 139904 |  | GUP-FF03-P1CYE-139904 | FIRE DETECTION AND ALARM SYSTEM_FIRE PROTECTION PUMP BUILDING_SINGLE LINE DIAGRAM | FI | 2022-10-31 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | Fire Protection Pump Building | FF | 3 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-871 | 2023-10-26 | 1 | CRS-GUP-DHI-DT-22-1108 | 2022-11-21 | NC | DE-GUP-DT-E-22-874 | 2022-10-28 | 0 | CRS-GUP-DHI-DT-22-1108 | 2022-11-21 | NC | DE-GUP-DT-E-23-871 | 2023-10-26 | 1
| GUP | FF02 | P1 | CYE | 139804 |  | GUP-FF02-P1CYE-139804 | FIRE DETECTION AND ALARM SYSTEM_FIRE PROTECTION PUMP BUILDING_LAYOUT AND DETAIL DRAWING | FI | 2022-10-31 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | Fire Protection Pump Building | FF | 2 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-871 | 2023-10-26 | 1 | CRS-GUP-DHI-DT-22-1108 | 2022-11-21 | NC | DE-GUP-DT-E-22-874 | 2022-10-28 | 0 | CRS-GUP-DHI-DT-22-1108 | 2022-11-21 | NC | DE-GUP-DT-E-23-871 | 2023-10-26 | 1
| GUP | FF01 | P1 | SGZ | 139704 |  | GUP-FF01-P1SGZ-139704 | FIRE EXTINGUISHER_FIRE PROTECTION PUMP BUILDING_LAYOUT AND DETAIL DRAWING | FI | 2022-10-31 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Fire Protection Pump Building | FF | 2 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-933 | 2023-11-23 | 2 | 자체 CRS 개정 후 제출 | 2023-11-22 | N/A | DE-GUP-DT-E-22-789 | 2022-10-12 | 0 | CRS-GUP-DHI-DT-22-977 | 2022-11-07 | NC | DE-GUP-DT-E-23-463 | 2023-04-14 | 1 | 자체 CRS 개정 후 제출 | 2023-11-22 | N/A | DE-GUP-DT-E-23-933 | 2023-11-23 | 2
| GUP | FF03 | P1 | SGA | 137201 |  | GUP-FF03-P1SGA-137201 | INDOOR HYDRANT SYSTEM_ADMINISTRATION BUILDING_P&I DIAGRAM | FA | 2023-06-12 | 2023-10-13 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Admin. Building | FF | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-404 | 2023-03-30 | 0 | CRS-GUP-DHI-DT-23-1857 | 2023-04-19 | AA | DE-GUP-DT-E-23-197 | 2023-02-17 | A | CRS-GUP-DHI-DT-23-1688 | 2023-03-14 | NC | DE-GUP-DT-E-23-404 | 2023-03-30 | 0 | CRS-GUP-DHI-DT-23-1857 | 2023-04-19 | AA
| GUP | FF01 | P1 | SGA | 137101 |  | GUP-FF01-P1SGA-137101 | INDOOR HYDRANT SYSTEM_ADMINISTRATION BUILDING_PIPE LAYOUT AND DETAIL DRAWING | FA | 2023-06-12 | 2023-10-13 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Admin. Building | FF | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-812 | 2023-09-15 | 1 | CRS-GUP-DHI-DT-23-1857 | 2023-04-19 | AA | DE-GUP-DT-E-23-197 | 2023-02-17 | A | CRS-GUP-DHI-DT-23-1688 | 2023-03-14 | NC | DE-GUP-DT-E-23-404 | 2023-03-30 | 0 | CRS-GUP-DHI-DT-23-1857 | 2023-04-19 | AA | DE-GUP-DT-E-23-812 | 2023-09-15 | 1
| GUP | FF05 | P1 | SGA | 137301 |  | GUP-FF05-P1SGA-137301 | INDOOR HYDRANT SYSTEM_ADMINISTRATION BUILDING_HYDRAULIC CALCULATION | FI | 2023-06-12 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Admin. Building | FF | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-197 | 2023-02-17 | 0 | CRS-GUP-DHI-DT-23-1688 | 2023-03-14 | NC | DE-GUP-DT-E-23-197 | 2023-02-17 | 0 | CRS-GUP-DHI-DT-23-1688 | 2023-03-14 | NC
| GUP | FF03 | P1 | SGE | 138201 |  | GUP-FF03-P1SGE-138201 | SPRINKLER SYSTEM_ADMINISTRATION BUILDING_P&I DIAGRAM | FA | 2023-06-12 | 2023-10-13 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Admin. Building | FF | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-764 | 2023-08-25 | 1 | 자체 CRS 개정 후 제출 | 2023-08-24 | N/A | DE-GUP-DT-E-22-1149 | 2022-12-22 | A | CRS-GUP-DHI-DT-22-1408 | 2023-01-07 | AA | DE-GUP-DT-E-23-070 | 2023-01-26 | 0 | 자체 CRS 개정 후 제출 | 2023-08-24 | N/A | DE-GUP-DT-E-23-764 | 2023-08-25 | 1
| GUP | FF01 | P1 | SGE | 138101 |  | GUP-FF01-P1SGE-138101 | SPRINKLER SYSTEM_ADMINISTRATION BUILDING_PIPE LAYOUT AND DETAIL DRAWING | FI | 2023-06-12 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Admin. Building | FF | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-029 | 2024-01-31 | 5 | 자체 CRS 개정 후 제출 | 2024-01-30 | N/A | DE-GUP-DT-E-22-1149 | 2022-12-22 | 0 | CRS-GUP-DHI-DT-22-1408 | 2023-01-07 | NC | DE-GUP-DT-E-23-459 | 2023-04-14 | 1 | 자체 CRS 개정 후 제출 | 2023-08-06 | N/A | DE-GUP-DT-E-23-735 | 2023-08-07 | 2 | 자체 CRS 개정 후 제출 | 2023-09-14 | N/A | DE-GUP-DT-E-23-812 | 2023-09-15 | 3 | 자체 CRS 개정 후 제출 | 2023-11-28 | N/A | DE-GUP-DT-E-23-953 | 2023-11-29 | 4 | 자체 CRS 개정 후 제출 | 2024-01-30 | N/A | DE-GUP-DT-E-24-029 | 2024-01-31 | 5
| GUP | FF05 | P1 | SGE | 138301 |  | GUP-FF05-P1SGE-138301 | SPRINKLER SYSTEM_ADMINISTRATION BUILDING_HYDRAULIC CALCULATION | FI | 2023-06-12 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Admin. Building | FF | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-801 | 2023-09-07 | 1 | CRS-GUP-DHI-DT-22-1408 | 2023-01-07 | NC | DE-GUP-DT-E-22-1149 | 2022-12-22 | 0 | CRS-GUP-DHI-DT-22-1408 | 2023-01-07 | NC | DE-GUP-DT-E-23-801 | 2023-09-07 | 1
| GUP | FF03 | P1 | CYE | 139901 |  | GUP-FF03-P1CYE-139901 | FIRE DETECTION AND ALARM SYSTEM_ADMINISTRATION BUILDING_SINGLE LINE DIAGRAM | FI | 2023-06-12 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | Admin. Building | FF | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-067 | 2024-03-07 | 3 | 자체 CRS 개정 후 제출 | 2024-03-06 | N/A | DE-GUP-DT-E-23-115 | 2023-02-03 | 0 | CRS-GUP-DHI-DT-23-1619 | 2023-03-02 | NC | DE-GUP-DT-E-23-734 | 2023-08-07 | 1 | 자체 CRS 개정 후 제출 | 2023-09-14 | N/A | DE-GUP-DT-E-23-812 | 2023-09-15 | 2 | 자체 CRS 개정 후 제출 | 2024-03-06 | N/A | DE-GUP-DT-E-24-067 | 2024-03-07 | 3
| GUP | FF02 | P1 | CYE | 139801 |  | GUP-FF02-P1CYE-139801 | FIRE DETECTION AND ALARM SYSTEM_ADMINISTRATION BUILDING_LAYOUT AND DETAIL DRAWING | FI | 2023-06-12 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | Admin. Building | FF | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-812 | 2023-09-15 | 2 | 자체 CRS 개정 후 제출 | 2023-09-14 | N/A | DE-GUP-DT-E-23-115 | 2023-02-03 | 0 | CRS-GUP-DHI-DT-23-1619 | 2023-03-02 | NC | DE-GUP-DT-E-23-733 | 2023-08-07 | 1 | 자체 CRS 개정 후 제출 | 2023-09-14 | N/A | DE-GUP-DT-E-23-812 | 2023-09-15 | 2
| GUP | FF01 | P1 | SGZ | 139701 |  | GUP-FF01-P1SGZ-139701 | FIRE EXTINGUISHER_ADMINISTRATION BUILDING_LAYOUT AND DETAIL DRAWING | FI | 2023-06-12 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Admin. Building | FF | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-921 | 2023-11-20 | 2 | 자체 CRS 개정 후 제출 | 2023-11-19 | N/A | DE-GUP-DT-E-23-115 | 2023-02-03 | 0 | CRS-GUP-DHI-DT-23-1619 | 2023-03-02 | NC | DE-GUP-DT-E-23-459 | 2023-04-14 | 1 | 자체 CRS 개정 후 제출 | 2023-11-19 | N/A | DE-GUP-DT-E-23-921 | 2023-11-20 | 2
| GUP | FF03 | P1 | SGA | 137219 |  | GUP-FF03-P1SGA-137219 | INDOOR HYDRANT SYSTEM_COOLING TOWER_P&I DIAGRAM | FA | 2023-02-14 | 2023-06-12 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Cooling Tower | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-406 | 2023-03-30 | 0 | CRS-GUP-DHI-DT-23-1859 | 2023-04-19 | AA | DE-GUP-DT-E-23-208 | 2023-02-20 | A | CRS-GUP-DHI-DT-23-1693 | 2023-03-14 | AA | DE-GUP-DT-E-23-406 | 2023-03-30 | 0 | CRS-GUP-DHI-DT-23-1859 | 2023-04-19 | AA
| GUP | FF01 | P1 | SGA | 137119 |  | GUP-FF01-P1SGA-137119 | INDOOR HYDRANT SYSTEM_COOLING TOWER_PIPE LAYOUT AND DETAIL DRAWING | FI | 2023-02-14 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Cooling Tower | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-027 | 2024-01-29 | 2 | CRS-GUP-DHI-DT-23-1890 | 2023-05-02 | NC | DE-GUP-DT-E-23-208 | 2023-02-20 | 0 | CRS-GUP-DHI-DT-23-1693 | 2023-03-14 | NC | DE-GUP-DT-E-23-461 | 2023-04-14 | 1 | CRS-GUP-DHI-DT-23-1890 | 2023-05-02 | NC | DE-GUP-DT-E-24-027 | 2024-01-29 | 2
| GUP | FF05 | P1 | SGA | 137319 |  | GUP-FF05-P1SGA-137319 | INDOOR HYDRANT SYSTEM_COOLING TOWER_HYDRAULIC CALCULATION | FI | 2023-02-14 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Cooling Tower | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-208 | 2023-02-20 | 0 | CRS-GUP-DHI-DT-23-1693 | 2023-03-14 | NC | DE-GUP-DT-E-23-208 | 2023-02-20 | 0 | CRS-GUP-DHI-DT-23-1693 | 2023-03-14 | NC
| GUP | FF03 | P1 | SGC | 138819 |  | GUP-FF03-P1SGC-138819 | WATER SPRAY SYSTEM_COOLING TOWER_P&I DIAGRAM | FA | 2023-02-14 | 2023-06-12 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Cooling Tower | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-362 | 2023-03-24 | 0 | CRS-GUP-DHI-DT-23-1695 | 2023-03-14 | AA | DE-GUP-DT-E-23-210 | 2023-02-20 | A | CRS-GUP-DHI-DT-23-1695 | 2023-03-14 | AA | DE-GUP-DT-E-23-362 | 2023-03-24 | 0
| GUP | FF01 | P1 | SGC | 138719 |  | GUP-FF01-P1SGC-138719 | WATER SPRAY SYSTEM_COOLING TOWER_PIPE LAYOUT AND DETAIL DRAWING | FI | 2023-02-14 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Cooling Tower | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-880 | 2023-11-02 | 1 | CRS-GUP-DHI-DT-23-1695 | 2023-03-14 | NC | DE-GUP-DT-E-23-210 | 2023-02-20 | 0 | CRS-GUP-DHI-DT-23-1695 | 2023-03-14 | NC | DE-GUP-DT-E-23-880 | 2023-11-02 | 1
| GUP | FF05 | P1 | SGC | 138919 |  | GUP-FF05-P1SGC-138919 | WATER SPRAY SYSTEM_COOLING TOWER_HYDRAULIC CALCULATION | FI | 2023-02-14 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Cooling Tower | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-210 | 2023-02-20 | 0 | CRS-GUP-DHI-DT-23-1695 | 2023-03-14 | NC | DE-GUP-DT-E-23-210 | 2023-02-20 | 0 | CRS-GUP-DHI-DT-23-1695 | 2023-03-14 | NC
| GUP | FF03 | P1 | CYE | 139919 |  | GUP-FF03-P1CYE-139919 | FIRE DETECTION AND ALARM SYSTEM_COOLING TOWER_SINGLE LINE DIAGRAM | FI | 2023-02-14 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | Cooling Tower | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-884 | 2023-11-07 | 1 | CRS-GUP-DHI-DT-23-1622 | 2023-03-02 | NC | DE-GUP-DT-E-23-120 | 2023-02-03 | 0 | CRS-GUP-DHI-DT-23-1622 | 2023-03-02 | NC | DE-GUP-DT-E-23-884 | 2023-11-07 | 1
| GUP | FF02 | P1 | CYE | 139819 |  | GUP-FF02-P1CYE-139819 | FIRE DETECTION AND ALARM SYSTEM_COOLING TOWER_LAYOUT AND DETAIL DRAWING | FI | 2023-02-14 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | Cooling Tower | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-884 | 2023-11-07 | 1 | CRS-GUP-DHI-DT-23-1622 | 2023-03-02 | NC | DE-GUP-DT-E-23-120 | 2023-02-03 | 0 | CRS-GUP-DHI-DT-23-1622 | 2023-03-02 | NC | DE-GUP-DT-E-23-884 | 2023-11-07 | 1
| GUP | FF03 | P1 | SGC | 138820 |  | GUP-FF03-P1SGC-138820 | WATER SPRAY SYSTEM_TRANSFORMER_P&I DIAGRAM | FA | 2022-09-12 | 2023-03-10 | 기계기술팀(FF) | 엄재식 | B |  | G | FI | FF | CCPP | TR Area | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-184 | 2024-07-17 | 1 | 자체 CRS 개정 후 제출 | 2024-07-16 | N/A | DE-GUP-DT-E-22-676 | 2022-09-23 | A | CRS-GUP-DHI-DT-22-973 | 2022-11-07 | RC | DE-GUP-DT-E-22-1071 | 2022-12-09 | B | CRS-GUP-DHI-DT-22-1323 | 2022-12-22 | AA | DE-GUP-DT-E-23-081 | 2023-01-27 | 0 | 자체 CRS 개정 후 제출 | 2024-07-16 | N/A | DE-GUP-DT-E-24-184 | 2024-07-17 | 1
| GUP | FF01 | P1 | SGC | 138720 |  | GUP-FF01-P1SGC-138720 | WATER SPRAY SYSTEM_TRANSFORMER_PIPE LAYOUT AND DETAIL DRAWING | FI | 2022-09-12 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | TR Area | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-755 | 2023-08-23 | 2 | CRS-GUP-DHI-DT-23-1828 | 2023-04-12 | NC | DE-GUP-DT-E-22-685 | 2022-09-21 | 0 | CRS-GUP-DHI-DT-22-990 | 2022-11-13 | NC | DE-GUP-DT-E-23-346 | 2023-03-22 | 1 | CRS-GUP-DHI-DT-23-1828 | 2023-04-12 | NC | DE-GUP-DT-E-23-755 | 2023-08-23 | 2
| GUP | FF05 | P1 | SGC | 138920 |  | GUP-FF05-P1SGC-138920 | WATER SPRAY SYSTEM_TRANSFORMER_HYDRAULIC CALCULATION | FI | 2022-09-12 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | TR Area | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-778 | 2023-08-29 | 3 | CRS-GUP-DHI-DT-23-2108 | 2023-09-13 | NC | DE-GUP-DT-E-22-676 | 2022-09-23 | 0 | CRS-GUP-DHI-DT-22-973 | 2022-11-07 | RC | DE-GUP-DT-E-22-1071 | 2022-12-09 | 1 | CRS-GUP-DHI-DT-22-1323 | 2022-12-22 | RC | DE-GUP-DT-E-23-282 | 2023-03-08 | 2 | CRS-GUP-DHI-DT-23-1776 | 2023-03-27 | RC | DE-GUP-DT-E-23-778 | 2023-08-29 | 3 | CRS-GUP-DHI-DT-23-2108 | 2023-09-13 | NC
| GUP | FF03 | P1 | CYE | 139920 |  | GUP-FF03-P1CYE-139920 | FIRE DETECTION AND ALARM SYSTEM_TRANSFORMER_SINGLE LINE DIAGRAM | FI | 2022-09-12 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | TR Area | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-767 | 2023-08-25 | 2 | CRS-GUP-DHI-DT-22-1323 | 2022-12-22 | NC | DE-GUP-DT-E-22-696 | 2022-09-23 | 0 | CRS-GUP-DHI-DT-22-973 | 2022-11-07 | RC | DE-GUP-DT-E-22-1071 | 2022-12-09 | 1 | CRS-GUP-DHI-DT-22-1323 | 2022-12-22 | NC | DE-GUP-DT-E-23-767 | 2023-08-25 | 2
| GUP | FF02 | P1 | CYE | 139820 |  | GUP-FF02-P1CYE-139820 | FIRE DETECTION AND ALARM SYSTEM_TRANSFORMER_LAYOUT AND DETAIL DRAWING | FI | 2022-09-12 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | TR Area | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-767 | 2023-08-25 | 2 | CRS-GUP-DHI-DT-22-1323 | 2022-12-22 | NC | DE-GUP-DT-E-22-696 | 2022-09-23 | 0 | CRS-GUP-DHI-DT-22-973 | 2022-11-07 | RC | DE-GUP-DT-E-22-1071 | 2022-12-09 | 1 | CRS-GUP-DHI-DT-22-1323 | 2022-12-22 | NC | DE-GUP-DT-E-23-767 | 2023-08-25 | 2
| GUP | FF01 | P1 | SGZ | 139720 |  | GUP-FF01-P1SGZ-139720 | FIRE EXTINGUISHER_TRANSFORMER_LAYOUT AND DETAIL DRAWING | FI | 2022-09-12 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | TR Area | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-933 | 2023-11-23 | 2 | 자체 CRS 개정 후 제출 | 2023-11-22 | N/A | DE-GUP-DT-E-22-661 | 2022-09-14 | 0 | CRS-GUP-DHI-DT-22-899 | 2022-10-12 | NC | DE-GUP-DT-E-23-469 | 2023-04-14 | 1 | 자체 CRS 개정 후 제출 | 2023-11-22 | N/A | DE-GUP-DT-E-23-933 | 2023-11-23 | 2
| GUP | FF03 | P1 | SGC | 138821 |  | GUP-FF03-P1SGC-138821 | WATER SPRAY SYSTEM_DIESEL GENERATOR DAY TANK_P&I DIAGRAM | FA | 2023-06-10 | 2023-10-13 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Diesel Generator Day Tank | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-790 | 2023-09-06 | 1 | 자체 CRS 개정 후 제출 | 2023-09-05 | N/A | DE-GUP-DT-E-23-113 | 2023-02-03 | A | CRS-GUP-DHI-DT-23-1617 | 2023-03-02 | AA | DE-GUP-DT-E-23-362 | 2023-03-24 | 0 | 자체 CRS 개정 후 제출 | 2023-09-05 | N/A | DE-GUP-DT-E-23-790 | 2023-09-06 | 1
| GUP | FF01 | P1 | SGC | 138721 |  | GUP-FF01-P1SGC-138721 | WATER SPRAY SYSTEM_DIESEL GENERATOR DAY TANK_PIPE LAYOUT AND DETAIL DRAWING | FI | 2023-06-10 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Diesel Generator Day Tank | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-880 | 2023-11-02 | 2 | 자체 CRS 개정 후 제출 | 2023-11-01 | N/A | DE-GUP-DT-E-23-113 | 2023-02-03 | 0 | CRS-GUP-DHI-DT-23-1617 | 2023-03-02 | NC | DE-GUP-DT-E-23-462 | 2023-04-14 | 1 | 자체 CRS 개정 후 제출 | 2023-11-01 | N/A | DE-GUP-DT-E-23-880 | 2023-11-02 | 2
| GUP | FF05 | P1 | SGC | 138921 |  | GUP-FF05-P1SGC-138921 | WATER SPRAY SYSTEM_DIESEL GENERATOR DAY TANK_HYDRAULIC CALCULATION | FI | 2023-06-10 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | Diesel Generator Day Tank | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-113 | 2023-02-03 | 0 | CRS-GUP-DHI-DT-23-1617 | 2023-03-02 | NC | DE-GUP-DT-E-23-113 | 2023-02-03 | 0 | CRS-GUP-DHI-DT-23-1617 | 2023-03-02 | NC
| GUP | FF03 | P1 | CYE | 139922 |  | GUP-FF03-P1CYE-139922 | FIRE DETECTION AND ALARM SYSTEM_DIESEL GENERATOR DAY TANK_SINGLE LINE DIAGRAM | FI | 2023-06-10 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | Diesel Generator Day Tank | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-952 | 2023-11-29 | 2 | 자체 CRS 개정 후 제출 | 2023-11-28 | N/A | DE-GUP-DT-E-23-114 | 2023-02-03 | 0 | CRS-GUP-DHI-DT-23-1618 | 2023-03-02 | NC | DE-GUP-DT-E-23-772 | 2023-08-29 | 1 | 자체 CRS 개정 후 제출 | 2023-11-28 | N/A | DE-GUP-DT-E-23-952 | 2023-11-29 | 2
| GUP | FF02 | P1 | CYE | 139822 |  | GUP-FF02-P1CYE-139822 | FIRE DETECTION AND ALARM SYSTEM_DIESEL GENERATOR DAY TANK_LAYOUT AND DETAIL DRAWING | FI | 2023-06-10 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | Diesel Generator Day Tank | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-952 | 2023-11-29 | 2 | 자체 CRS 개정 후 제출 | 2023-11-28 | N/A | DE-GUP-DT-E-23-114 | 2023-02-03 | 0 | CRS-GUP-DHI-DT-23-1618 | 2023-03-02 | NC | DE-GUP-DT-E-23-772 | 2023-08-29 | 1 | 자체 CRS 개정 후 제출 | 2023-11-28 | N/A | DE-GUP-DT-E-23-952 | 2023-11-29 | 2
| GUP | FF03 | P1 | SGF | 137223 |  | GUP-FF03-P1SGF-137223 | FOAM HYDRANT SYSTEM_ULSD TANK & UNLOADING SHELTER_P&I DIAGRAM | FA | 2023-03-16 | 2023-07-11 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | ULSD Tank | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-766 | 2023-08-25 | 1 | 자체 CRS 개정 후 제출 | 2023-08-23 | N/A | DE-GUP-DT-E-22-799 | 2022-10-14 | A | CRS-GUP-DHI-DT-22-1093 | 2022-11-21 | AA | DE-GUP-DT-E-23-082 | 2023-01-27 | 0 | 자체 CRS 개정 후 제출 | 2023-08-23 | N/A | DE-GUP-DT-E-23-766 | 2023-08-25 | 1
| GUP | FF01 | P1 | SGF | 137123 |  | GUP-FF01-P1SGF-137123 | FOAM HYDRANT SYSTEM_ULSD TANK & UNLOADING SHELTER_PIPE LAYOUT AND DETAIL DRAWING | FI | 2023-03-16 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | ULSD Tank | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-954 | 2023-11-29 | 3 | 자체 CRS 개정 후 제출 | 2023-11-28 | N/A | DE-GUP-DT-E-22-799 | 2022-10-14 | 0 | CRS-GUP-DHI-DT-22-1116 | 2022-11-21 | NC | DE-GUP-DT-E-23-467 | 2023-04-14 | 1 | CRS-GUP-DHI-DT-23-1891 | 2023-05-02 | NC | DE-GUP-DT-E-23-756 | 2023-08-23 | 2 | 자체 CRS 개정 후 제출 | 2023-11-28 | N/A | DE-GUP-DT-E-23-954 | 2023-11-29 | 3
| GUP | FF05 | P1 | SGF | 137323 |  | GUP-FF05-P1SGF-137323 | FOAM HYDRANT SYSTEM_ULSD TANK & UNLOADING SHELTER_HYDRAULIC CALCULATION | FI | 2023-03-16 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | ULSD Tank | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-799 | 2022-10-14 | 0 | CRS-GUP-DHI-DT-22-1093 | 2022-11-21 | NC | DE-GUP-DT-E-22-799 | 2022-10-14 | 0 | CRS-GUP-DHI-DT-22-1093 | 2022-11-21 | NC
| GUP | FF03 | P1 | SGF | 137823 |  | GUP-FF03-P1SGF-137823 | FOAM INJECTION SYSTEM_ULSD TANK_P&I DIAGRAM | FA | 2022-10-14 | 2023-02-10 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | ULSD Tank | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-766 | 2023-08-25 | 1 | 자체 CRS 개정 후 제출 | 2023-08-23 | N/A | DE-GUP-DT-E-22-799 | 2022-10-14 | A | CRS-GUP-DHI-DT-22-1093 | 2022-11-21 | AA | DE-GUP-DT-E-23-082 | 2023-01-27 | 0 | 자체 CRS 개정 후 제출 | 2023-08-23 | N/A | DE-GUP-DT-E-23-766 | 2023-08-25 | 1
| GUP | FF01 | P1 | SGF | 137723 |  | GUP-FF01-P1SGF-137723 | FOAM INJECTION SYSTEM_ULSD TANK_PIPE LAYOUT AND DETAIL DRAWING | FI | 2022-10-14 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | ULSD Tank | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-213 | 2024-08-29 | 4 | 자체 CRS 개정 후 제출 | 2024-08-28 | N/A | DE-GUP-DT-E-22-799 | 2022-10-14 | 0 | CRS-GUP-DHI-DT-22-1093 | 2022-11-21 | NC | DE-GUP-DT-E-23-467 | 2023-04-14 | 1 | CRS-GUP-DHI-DT-23-1891 | 2023-05-02 | NC | DE-GUP-DT-E-23-756 | 2023-08-23 | 2 | 자체 CRS 개정 후 제출 | 2024-07-22 | N/A | DE-GUP-DT-E-24-186 | 2024-07-23 | 3 | 자체 CRS 개정 후 제출 | 2024-08-28 | N/A | DE-GUP-DT-E-24-213 | 2024-08-29 | 4
| GUP | FF05 | P1 | SGF | 137923 |  | GUP-FF05-P1SGF-137923 | FOAM INJECTION SYSTEM_ULSD TANK_HYDRAULIC CALCULATION | FI | 2022-10-14 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | ULSD Tank | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-799 | 2022-10-14 | 0 | CRS-GUP-DHI-DT-22-1093 | 2022-11-21 | NC | DE-GUP-DT-E-22-799 | 2022-10-14 | 0 | CRS-GUP-DHI-DT-22-1093 | 2022-11-21 | NC
| GUP | FF03 | P1 | SGC | 138823 |  | GUP-FF03-P1SGC-138823 | COOLING WATER SPRAY SYSTEM_ULSD TANK_P&I DIAGRAM | FA | 2022-10-14 | 2023-02-10 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | ULSD Tank | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-467 | 2023-04-14 | 1 | CRS-GUP-DHI-DT-22-1093 | 2022-11-21 | AA | DE-GUP-DT-E-22-799 | 2022-10-14 | A | CRS-GUP-DHI-DT-22-1093 | 2022-11-21 | AA | DE-GUP-DT-E-23-082 | 2023-01-27 | 0 | N/A | N/A | N/A | DE-GUP-DT-E-23-467 | 2023-04-14 | 1
| GUP | FF01 | P1 | SGC | 138723 |  | GUP-FF01-P1SGC-138723 | COOLING WATER SPRAY SYSTEM_ULSD TANK_PIPE LAYOUT AND DETAIL DRAWING | FI | 2022-10-14 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | ULSD Tank | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-159 | 2024-06-19 | 4 | 자체 CRS 개정 후 제출 | 2024-06-18 | N/A | DE-GUP-DT-E-22-799 | 2022-10-14 | 0 | CRS-GUP-DHI-DT-22-1093 | 2022-11-21 | NC | DE-GUP-DT-E-23-467 | 2023-04-14 | 1 | CRS-GUP-DHI-DT-23-1891 | 2023-05-02 | NC | DE-GUP-DT-E-23-756 | 2023-08-23 | 2 | 자체 CRS 개정 후 제출 | 2023-10-08 | N/A | DE-GUP-DT-E-23-859 | 2023-10-19 | 3 | 자체 CRS 개정 후 제출 | 2024-06-18 | N/A | DE-GUP-DT-E-24-159 | 2024-06-19 | 4
| GUP | FF05 | P1 | SGC | 138923 |  | GUP-FF05-P1SGC-138923 | COOLING WATER SPRAY SYSTEM_ULSD TANK_HYDRAULIC CALCULATION | FI | 2022-10-14 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | ULSD Tank | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-799 | 2022-10-14 | 0 | CRS-GUP-DHI-DT-22-1093 | 2022-11-21 | NC | DE-GUP-DT-E-22-799 | 2022-10-14 | 0 | CRS-GUP-DHI-DT-22-1093 | 2022-11-21 | NC
| GUP | FF03 | P1 | CYE | 139923 |  | GUP-FF03-P1CYE-139923 | FIRE DETECTION AND ALARM SYSTEM_ULSD TANK & UNLOADING SHELTER_SINGLE LINE DIAGRAM | FI | 2022-10-14 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | ULSD Tank | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-756 | 2023-08-23 | 2 | CRS-GUP-DHI-DT-23-1891 | 2023-05-02 | NC | DE-GUP-DT-E-22-799 | 2022-10-14 | 0 | CRS-GUP-DHI-DT-22-1093 | 2022-11-21 | NC | DE-GUP-DT-E-23-467 | 2023-04-14 | 1 | CRS-GUP-DHI-DT-23-1891 | 2023-05-02 | NC | DE-GUP-DT-E-23-756 | 2023-08-23 | 2
| GUP | FF02 | P1 | CYE | 139823 |  | GUP-FF02-P1CYE-139823 | FIRE DETECTION AND ALARM SYSTEM_ULSD TANK & UNLOADING SHELTER_LAYOUT AND DETAIL DRAWING | FI | 2022-10-14 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | ULSD Tank | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-756 | 2023-08-23 | 2 | CRS-GUP-DHI-DT-23-1891 | 2023-05-02 | NC | DE-GUP-DT-E-22-799 | 2022-10-14 | 0 | CRS-GUP-DHI-DT-22-1093 | 2022-11-21 | NC | DE-GUP-DT-E-23-467 | 2023-04-14 | 1 | CRS-GUP-DHI-DT-23-1891 | 2023-05-02 | NC | DE-GUP-DT-E-23-756 | 2023-08-23 | 2
| GUP | FF01 | P1 | SGZ | 139723 |  | GUP-FF01-P1SGZ-139723 | FIRE EXTINGUISHER_ULSD TANK & UNLOADING SHELTER_LAYOUT AND DETAIL DRAWING | FI | 2023-03-16 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | ULSD Tank | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-145 | 2024-06-03 | 3 | 자체 CRS 개정 후 제출 | 2024-06-02 | N/A | DE-GUP-DT-E-22-799 | 2022-10-14 | 0 | CRS-GUP-DHI-DT-22-1093 | 2022-11-21 | NC | DE-GUP-DT-E-23-467 | 2023-04-14 | 1 | CRS-GUP-DHI-DT-23-1891 | 2023-05-02 | NC | DE-GUP-DT-E-23-933 | 2023-11-23 | 2 | 자체 CRS 개정 후 제출 | 2024-06-02 | N/A | DE-GUP-DT-E-24-145 | 2024-06-03 | 3
| GUP | FF01 | P1 | SGZ | 139729 |  | GUP-FF01-P1SGZ-139729 | FIRE EXTINGUISHER_MISCELLANEOUS SHELTERS_LAYOUT AND DETAIL DRAWING | FI | 2023-03-16 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | MISCELLANEOUS SHELTER | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-921 | 2023-11-20 | 1 | CRS-GUP-DHI-DT-23-1698 | 2023-03-14 | NC | DE-GUP-DT-E-23-222 | 2023-02-22 | 0 | CRS-GUP-DHI-DT-23-1698 | 2023-03-14 | NC | DE-GUP-DT-E-23-921 | 2023-11-20 | 1
| GUP | FF02 | P1 | CYE | 139829 |  | GUP-FF02-P1CYE-139829 | FIRE DETECTION AND ALARM SYSTEM_MISCELLANEOUS SHELTERS_LAYOUT AND DETAIL DRAWING | FI | 2023-03-16 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | MISCELLANEOUS SHELTER | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-746 | 2023-08-17 | 1 | CRS-GUP-DHI-DT-23-1621 | 2023-03-02 | NC | DE-GUP-DT-E-23-118 | 2023-02-03 | 0 | CRS-GUP-DHI-DT-23-1621 | 2023-03-02 | NC | DE-GUP-DT-E-23-746 | 2023-08-17 | 1
| GUP | FF03 | P1 | CYE | 139929 |  | GUP-FF03-P1CYE-139929 | FIRE DETECTION AND ALARM SYSTEM_MISCELLANEOUS SHELTERS_SINGLE LINE DIAGRAM | FI | 2023-03-16 |  | 기계기술팀(FF) | 엄재식 | B | P |  |  | FF | CCPP | MISCELLANEOUS SHELTER | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-777 | 2023-08-29 | 1 | CRS-GUP-DHI-DT-23-1621 | 2023-03-02 | NC | DE-GUP-DT-E-23-118 | 2023-02-03 | 0 | CRS-GUP-DHI-DT-23-1621 | 2023-03-02 | NC | DE-GUP-DT-E-23-777 | 2023-08-29 | 1
| GUP | FF01 | P1 | SGC | 138729 |  | GUP-FF01-P1SGC-138729 | WATER SPRAY SYSTEM_ULSD BUFFER TANK_PIPE LAYOUT AND DETAIL DRAWING | FI | 2023-03-16 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | ULSD Buffer Tank | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-907 | 2023-11-13 | 1 | CRS-GUP-DHI-DT-23-1744 | 2023-03-17 | NC | DE-GUP-DT-E-23-255 | 2023-02-28 | 0 | CRS-GUP-DHI-DT-23-1744 | 2023-03-17 | NC | DE-GUP-DT-E-23-907 | 2023-11-13 | 1
| GUP | FF03 | P1 | SGC | 138829 |  | GUP-FF03-P1SGC-138829 | WATER SPRAY SYSTEM_ULSD BUFFER TANK_P&I DIAGRAM | FA | 2023-03-16 | 2023-07-11 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | ULSD Buffer Tank | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-726 | 2023-07-28 | 0 | CRS-GUP-DHI-DT-23-1744 | 2023-03-17 | AA | DE-GUP-DT-E-23-255 | 2023-02-28 | A | CRS-GUP-DHI-DT-23-1744 | 2023-03-17 | AA | DE-GUP-DT-E-23-726 | 2023-07-28 | 0
| GUP | FF05 | P1 | SGC | 138929 |  | GUP-FF05-P1SGC-138929 | WATER SPRAY SYSTEM_ULSD BUFFER TANK_HYDRAULIC CALCULATION | FI | 2023-03-16 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | ULSD Buffer Tank | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-255 | 2023-02-28 | 0 | CRS-GUP-DHI-DT-23-1744 | 2023-03-17 | NC | DE-GUP-DT-E-23-255 | 2023-02-28 | 0 | CRS-GUP-DHI-DT-23-1744 | 2023-03-17 | NC
| GUP | FF01 | P1 | SGF | 138728 |  | GUP-FF01-P1SGF-138728 | FOAM WATER SPRAY SYSTEM_UNLOADING SHELTER_PIPE LAYOUT AND DETAIL DRAWING | FI | 2023-03-16 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | UNLOADING SHELTER | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-213 | 2024-08-29 | 3 | 자체 CRS 개정 후 제출 | 2024-08-28 | N/A | DE-GUP-DT-E-22-799 | 2022-10-14 | 0 | CRS-GUP-DHI-DT-22-1093 | 2022-11-21 | NC | DE-GUP-DT-E-23-467 | 2023-04-14 | 1 | CRS-GUP-DHI-DT-23-1891 | 2023-05-02 | NC | DE-GUP-DT-E-23-757 | 2023-08-23 | 2 | 자체 CRS 개정 후 제출 | 2024-08-28 | N/A | DE-GUP-DT-E-24-213 | 2024-08-29 | 3
| GUP | FF03 | P1 | SGF | 138828 |  | GUP-FF03-P1SGF-138828 | FOAM WATER SPRAY SYSTEM_UNLOADING SHELTER_P&I DIAGRAM | FA | 2023-03-16 | 2023-07-11 | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | UNLOADING SHELTER | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-790 | 2023-09-06 | 1 | 자체 CRS 개정 후 제출 | 2023-09-05 | N/A | DE-GUP-DT-E-22-799 | 2022-10-14 | A | CRS-GUP-DHI-DT-22-1093 | 2022-11-21 | AA | DE-GUP-DT-E-23-086 | 2023-01-30 | 0 | 자체 CRS 개정 후 제출 | 2023-09-05 | N/A | DE-GUP-DT-E-23-790 | 2023-09-06 | 1
| GUP | FF01 | P1 | SGF | 138928 |  | GUP-FF01-P1SGF-138928 | FOAM WATER SPRAY SYSTEM_UNLOADING SHELTER_HYDRAULIC CALCULATION | FI | 2023-03-16 |  | 기계기술팀(FF) | 엄재식 | B |  |  |  | FF | CCPP | UNLOADING SHELTER | FF | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-799 | 2022-10-14 | 0 | CRS-GUP-DHI-DT-22-1093 | 2022-11-21 | NC | DE-GUP-DT-E-22-799 | 2022-10-14 | 0 | CRS-GUP-DHI-DT-22-1093 | 2022-11-21 | NC
| GUP | FF03 | P1 | SGC | 138830 |  | GUP-FF03-P1SGC-138830 | WATER SPRAY SYSTEM_FLUSHED FUEL STORAGE TANK_P&I DIAGRAM | FA | 2024-11-22 | 2025-01-22 | 기계기술팀(FF) | 호재원 | B |  |  |  | FF | CCPP | FLUSHED FUEL STORAGE TANK | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-25-026 | 2025-02-18 | 0 | 자체 CRS 개정 후 제출 | 2025-02-17 | N/A | DE-GUP-DT-E-24-269 | 2024-11-12 | A | 자체 CRS 개정 후 제출 | 2025-02-17 | N/A | DE-GUP-DT-E-25-026 | 2025-02-18 | 0
| GUP | FF01 | P1 | SGC | 138730 |  | GUP-FF01-P1SGC-138730 | WATER SPRAY SYSTEM_ FLUSHED FUEL STORAGE TANK _PIPE LAYOUT AND DETAIL DRAWING | FI | 2024-11-22 |  | 기계기술팀(FF) | 호재원 | B |  |  |  | FF | CCPP | FLUSHED FUEL STORAGE TANK | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-25-019 | 2025-02-04 | 1 | 별도 메일접수 25-008 | 2025-03-13 | AA | DE-GUP-DT-E-24-268 | 2024-11-12 | 0 | 자체 CRS 개정 후 제출 | 2025-02-03 | N/A | DE-GUP-DT-E-25-019 | 2025-02-04 | 1 | 별도 메일접수 25-008 | 2025-03-13 | AA
| GUP | FF05 | P1 | SGC | 138930 |  | GUP-FF05-P1SGC-138930 | WATER SPRAY SYSTEM_ FLUSHED FUEL STORAGE TANK _HYDRAULIC CALCULATION | FI | 2024-11-22 |  | 기계기술팀(FF) | 호재원 | B |  |  |  | FF | CCPP | FLUSHED FUEL STORAGE TANK | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-270 | 2024-11-13 | 0 | 별도 메일접수 25-005 | 2025-03-13 | AA | DE-GUP-DT-E-24-270 | 2024-11-13 | 0 | 별도 메일접수 25-005 | 2025-03-13 | AA
| GUP | FF02 | P1 | CYE | 139830 |  | GUP-FF02-P1CYE-139830 | FIRE DETECTION AND ALARM SYSTEM_ FLUSHED FUEL STORAGE TANK _LAYOUT AND DETAIL DRAWING | FI | 2024-11-22 |  | 기계기술팀(FF) | 호재원 | B |  |  |  | FF | CCPP | FLUSHED FUEL STORAGE TANK | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-266 | 2024-11-12 | 0 | 별도 메일접수 25-002 | 2025-03-13 | AA | DE-GUP-DT-E-24-266 | 2024-11-12 | 0 | 별도 메일접수 25-002 | 2025-03-13 | AA
| GUP | FF03 | P1 | CYE | 139930 |  | GUP-FF03-P1CYE-139930 | FIRE DETECTION AND ALARM SYSTEM_ FLUSHED FUEL STORAGE TANK _SINGLE LINE DIAGRAM | FI | 2024-11-22 |  | 기계기술팀(FF) | 호재원 | B |  |  |  | FF | CCPP | FLUSHED FUEL STORAGE TANK | FF | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-267 | 2024-11-12 | 0 | 별도 메일접수 25-004 | 2025-03-13 | AA | DE-GUP-DT-E-24-267 | 2024-11-12 | 0 | 별도 메일접수 25-004 | 2025-03-13 | AA
| GUP | UH00 | P1 | ZEN | 170006 |  | GUP-UH00-P1ZEN-170006 | SITE PREPARATION (CCPP PLANT AREA)_LAYOUT | FA | 2021-07-14 | 2021-09-17 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | Plant | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-071 | 2022-02-16 | 3 | CRS-GUP-DHI-DT-22-242 | 2022-03-09 | AA | DHI-GUP-DT-21-005 | 2021-06-23 | A | N/A | N/A | N/A | DHI-GUP-DT-21-035 | 2021-09-27 | 0 | CRS-GUP-DHI-DT-21-007 | 2021-09-28 | RR | DHI-GUP-DT-21-065 | 2021-10-15 | 1 | CRS-GUP-DHI-DT-21-047 | 2021-10-29 | AC | DHI-GUP-DT-21-188 | 2021-12-17 | 2 | CRS-GUP-DHI-DT-21-118 | 2022-01-07 | AC | DHI-GUP-DT-22-071 | 2022-02-16 | 3 | CRS-GUP-DHI-DT-22-242 | 2022-03-09 | AA
| GUP | CC02 | P1 | ZEN | 170008 |  | GUP-CC02-P1ZEN-170008 | SITE PREPARATION (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2021-07-14 | 2022-09-17 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | Plant | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DHI-GUP-DT-22-071 | 2022-02-16 | 3 | CRS-GUP-DHI-DT-22-242 | 2022-03-09 | AA | DHI-GUP-DT-21-005 | 2021-06-23 | A | N/A | N/A | N/A | DHI-GUP-DT-21-035 | 2021-09-27 | 0 | CRS-GUP-DHI-DT-21-007 | 2021-09-28 | RR | DHI-GUP-DT-21-065 | 2021-10-15 | 1 | CRS-GUP-DHI-DT-21-047 | 2021-10-29 | AC | DHI-GUP-DT-21-188 | 2021-12-17 | 2 | CRS-GUP-DHI-DT-21-118 | 2022-01-07 | RC | DHI-GUP-DT-22-071 | 2022-02-16 | 3 | CRS-GUP-DHI-DT-22-242 | 2022-03-09 | AA
| GUP | CC07 | P1 | UMA | 170012 |  | GUP-CC07-P1UMA-170012 | STEAM TURBINE GENERATOR FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2022-03-21 | 2022-08-31 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | ST Building | Civil. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-645 | 2023-06-27 | 1 | CRS-GUP-DHI-DT-22-936 | 2022-10-21 | AA | DHI-GUP-DT-22-102 | 2022-03-08 | A | CRS-GUP-DHI-DT-22-261 | 2022-03-17 | RC | DHI-GUP-DT-22-198 | 2022-05-02 | B | CRS-GUP-DHI-DT-22-361 | 2022-05-23 | RC | DE-GUP-DT-E-22-409 | 2022-07-18 | C | CRS-GUP-DHI-DT-22-586 | 2022-08-08 | RC | DE-GUP-DT-E-22-552 | 2022-08-25 | D | CRS-GUP-DHI-DT-22-750 | 2022-09-12 | RC | DE-GUP-DT-E-22-702 | 2022-09-26 | E | CRS-GUP-DHI-DT-22-866 | 2022-09-26 | AA | DE-GUP-DT-E-22-715 | 2022-09-29 | 0(CP) | CRS-GUP-DHI-DT-22-936 | 2022-10-21 | AA | DE-GUP-DT-E-23-645 | 2023-06-27 | 1
| GUP | CC02 | P1 | UMA | 170014 |  | GUP-CC02-P1UMA-170014 | STEAM TURBINE GENERATOR FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2022-03-21 | 2022-08-31 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | ST Building | Civil. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-645 | 2023-06-27 | 3 | CRS-GUP-DHI-DT-22-1264 | 2022-12-16 | AA | DHI-GUP-DT-22-102 | 2022-03-08 | A | CRS-GUP-DHI-DT-22-261 | 2022-03-17 | RC | DHI-GUP-DT-22-198 | 2022-05-02 | B | CRS-GUP-DHI-DT-22-361 | 2022-05-23 | RC | DE-GUP-DT-E-22-409 | 2022-07-18 | C | CRS-GUP-DHI-DT-22-586 | 2022-08-08 | RC | DE-GUP-DT-E-22-552 | 2022-08-25 | D | CRS-GUP-DHI-DT-22-750 | 2022-09-12 | RC | DE-GUP-DT-E-22-702 | 2022-09-26 | E | CRS-GUP-DHI-DT-22-866 | 2022-09-26 | AA | DE-GUP-DT-E-22-715 | 2022-09-29 | 0(CP) | CRS-GUP-DHI-DT-22-936 | 2022-10-21 | AA | DE-GUP-DT-E-22-867 | 2022-10-27 | 1(CP) | CRS-GUP-DHI-DT-22-1146 | 2022-11-23 | AA | DE-GUP-DT-E-22-997 | 2022-11-28 | 2(CP) | CRS-GUP-DHI-DT-22-1264 | 2022-12-16 | AA | DE-GUP-DT-E-23-645 | 2023-06-27 | 3
| GUP | CC04 | P1 | UMA | 170016 |  | GUP-CC04-P1UMA-170016 | STEAM TURBINE GENERATOR FOUNDATION (CCPP PLANT AREA)_DETAIL | FI | 2022-03-21 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | ST Building | Civil. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-24-296 | 2024-12-19 | 10 | 자체 CRS 개정 후 제출 | 2024-12-18 | N/A | DHI-GUP-DT-22-102 | 2022-03-08 | 0 | CRS-GUP-DHI-DT-22-261 | 2022-03-17 | RC | DHI-GUP-DT-22-198 | 2022-05-02 | 1 | CRS-GUP-DHI-DT-22-361 | 2022-05-23 | RC | DE-GUP-DT-E-22-409 | 2022-07-18 | 2 | CRS-GUP-DHI-DT-22-586 | 2022-08-08 | RC | DE-GUP-DT-E-22-552 | 2022-08-25 | 3 | CRS-GUP-DHI-DT-22-750 | 2022-09-12 | RC | DE-GUP-DT-E-22-702 | 2022-09-26 | 4 | CRS-GUP-DHI-DT-22-866 | 2022-09-26 | NC | DE-GUP-DT-E-22-715 | 2022-09-29 | 5 | CRS-GUP-DHI-DT-22-936 | 2022-10-21 | NC | DE-GUP-DT-E-22-867 | 2022-10-27 | 6 | CRS-GUP-DHI-DT-22-969 | 2022-11-07 | NC | DE-GUP-DT-E-22-997 | 2022-11-28 | 7 | CRS-GUP-DHI-DT-22-1264 | 2022-12-16 | NC | DE-GUP-DT-E-23-075 | 2023-01-26 | 8 | CRS-GUP-DHI-DT-23-1563 | 2023-02-23 | NC | DE-GUP-DT-E-23-645 | 2023-06-27 | 9 | 자체 CRS 개정 후 제출 | 2024-12-18 | N/A | DE-GUP-DT-E-24-296 | 2024-12-19 | 10
| GUP | CC03 | P1 | UMA | 170018 |  | GUP-CC03-P1UMA-170018 | STEAM TURBINE GENERATOR FOUNDATION (CCPP PLANT AREA)_REBAR DETAIL | FI | 2022-03-21 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | ST Building | Civil. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-645 | 2023-06-27 | 8 | CRS-GUP-DHI-DT-22-1264 | 2022-12-16 | NC | DHI-GUP-DT-22-102 | 2022-03-08 | 0 | CRS-GUP-DHI-DT-22-261 | 2022-03-17 | NC | DHI-GUP-DT-22-198 | 2022-05-02 | 1 | CRS-GUP-DHI-DT-22-361 | 2022-05-23 | RC | DE-GUP-DT-E-22-409 | 2022-07-18 | 2 | CRS-GUP-DHI-DT-22-586 | 2022-08-08 | RC | DE-GUP-DT-E-22-552 | 2022-08-25 | 3 | CRS-GUP-DHI-DT-22-750 | 2022-09-12 | RC | DE-GUP-DT-E-22-702 | 2022-09-26 | 4 | CRS-GUP-DHI-DT-22-866 | 2022-09-26 | NC | DE-GUP-DT-E-22-715 | 2022-09-29 | 5 | CRS-GUP-DHI-DT-22-936 | 2022-10-21 | NC | DE-GUP-DT-E-22-867 | 2022-10-27 | 6 | CRS-GUP-DHI-DT-22-969 | 2022-11-07 | NC | DE-GUP-DT-E-22-997 | 2022-11-28 | 7 | CRS-GUP-DHI-DT-22-1264 | 2022-12-16 | NC | DE-GUP-DT-E-23-645 | 2023-06-27 | 8
| GUP | CC07 | P1 | MPA | 170020 |  | GUP-CC07-P1MPA-170020 | GAS TURBINE GENERATOR FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2022-01-30 | 2022-06-30 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | GT Building | Civil. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-644 | 2023-06-27 | 2 | CRS-GUP-DHI-DT-23-2060 | 2023-07-15 | AA | DHI-GUP-DT-21-066 | 2021-10-15 | A | CRS-GUP-DHI-DT-21-045 | 2021-10-29 | RR | DHI-GUP-DT-21-191 | 2021-12-22 | B | CRS-GUP-DHI-DT-21-136 | 2022-01-11 | AC | DHI-GUP-DT-22-110 | 2022-03-10 | C | CRS-GUP-DHI-DT-22-271 | 2022-03-29 | AC | DE-GUP-DT-E-22-404 | 2022-07-15 | 0(CP) | CRS-GUP-DHI-DT-22-583 | 2022-08-08 | AC | DE-GUP-DT-E-22-553 | 2022-08-25 | 1(CP) | CRS-GUP-DHI-DT-22-751 | 2022-09-12 | AC | DE-GUP-DT-E-23-644 | 2023-06-27 | 2 | CRS-GUP-DHI-DT-23-2060 | 2023-07-15 | AA
| GUP | CC02 | P1 | MPA | 170022 |  | GUP-CC02-P1MPA-170022 | GAS TURBINE GENERATOR FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2022-01-30 | 2022-06-30 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | GT Building | Civil. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-996 | 2022-11-28 | 2 | CRS-GUP-DHI-DT-22-1263 | 2022-12-16 | AA | DHI-GUP-DT-21-066 | 2021-10-15 | A | CRS-GUP-DHI-DT-21-045 | 2021-10-29 | RR | DHI-GUP-DT-21-191 | 2021-12-22 | B | CRS-GUP-DHI-DT-21-136 | 2022-01-11 | AC | DHI-GUP-DT-22-110 | 2022-03-10 | C | CRS-GUP-DHI-DT-22-271 | 2022-03-29 | AC | DE-GUP-DT-E-22-404 | 2022-07-15 | 0(CP) | CRS-GUP-DHI-DT-22-583 | 2022-08-08 | AC | DE-GUP-DT-E-22-553 | 2022-08-25 | 1 | CRS-GUP-DHI-DT-22-751 | 2022-09-12 | AC | DE-GUP-DT-E-22-996 | 2022-11-28 | 2 | CRS-GUP-DHI-DT-22-1263 | 2022-12-16 | AA
| GUP | CC04 | P1 | MPA | 170024 |  | GUP-CC04-P1MPA-170024 | GAS TURBINE GENERATOR FOUNDATION (CCPP PLANT AREA)_DETAIL | FI | 2022-01-30 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | GT Building | Civil. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-996 | 2022-11-28 | 5 | CRS-GUP-DHI-DT-22-1263 | 2022-12-16 | NC | DHI-GUP-DT-21-066 | 2021-10-15 | 0 | CRS-GUP-DHI-DT-21-045 | 2021-10-29 | RC | DHI-GUP-DT-21-191 | 2021-12-22 | 1 | CRS-GUP-DHI-DT-21-136 | 2022-01-11 | RC | DHI-GUP-DT-22-110 | 2022-03-10 | 2 | CRS-GUP-DHI-DT-22-271 | 2022-03-29 | NC | DE-GUP-DT-E-22-404 | 2022-07-15 | 3 | CRS-GUP-DHI-DT-22-583 | 2022-08-08 | NC | DE-GUP-DT-E-22-553 | 2022-08-25 | 4 | CRS-GUP-DHI-DT-22-751 | 2022-09-12 | NC | DE-GUP-DT-E-22-996 | 2022-11-28 | 5 | CRS-GUP-DHI-DT-22-1263 | 2022-12-16 | NC
| GUP | CC03 | P1 | MPA | 170026 |  | GUP-CC03-P1MPA-170026 | GAS TURBINE GENERATOR FOUNDATION (CCPP PLANT AREA)_REBAR DETAIL | FI | 2022-01-30 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | GT Building | Civil. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-996 | 2022-11-28 | 5 | CRS-GUP-DHI-DT-22-1263 | 2022-12-16 | NC | DHI-GUP-DT-21-066 | 2021-10-15 | 0 | CRS-GUP-DHI-DT-21-045 | 2021-10-29 | RC | DHI-GUP-DT-21-191 | 2021-12-22 | 1 | CRS-GUP-DHI-DT-21-136 | 2022-01-11 | RC | DHI-GUP-DT-22-110 | 2022-03-10 | 2 | CRS-GUP-DHI-DT-22-271 | 2022-03-29 | RC | DE-GUP-DT-E-22-404 | 2022-07-15 | 3 | CRS-GUP-DHI-DT-22-583 | 2022-08-08 | NC | DE-GUP-DT-E-22-553 | 2022-08-25 | 4 | CRS-GUP-DHI-DT-22-751 | 2022-09-12 | NC | DE-GUP-DT-E-22-996 | 2022-11-28 | 5 | CRS-GUP-DHI-DT-22-1263 | 2022-12-16 | NC
| GUP | CC07 | P1 | UBG | 170028 |  | GUP-CC07-P1UBG-170028 | STEP-UP & UNIT AUXILIARY TRANSFORMER FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2022-06-27 | 2022-09-25 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | TR Area | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-442 | 2023-04-10 | 1 | CRS-GUP-DHI-DT-23-1550 | 2023-02-19 | AA | DHI-GUP-DT-22-065 | 2022-02-14 | A | CRS-GUP-DHI-DT-22-227 | 2022-03-05 | RC | DHI-GUP-DT-22-147 | 2022-04-04 | B | CRS-GUP-DHI-DT-22-303 | 2022-04-17 | RC | DE-GUP-DT-E-22-378 | 2022-07-11 | C | CRS-GUP-DHI-DT-22-626 | 2022-08-18 | RR | DE-GUP-DT-E-22-680 | 2022-09-16 | D | CRS-GUP-DHI-DT-22-934 | 2022-10-21 | RC | DE-GUP-DT-E-22-960 | 2022-11-18 | E | CRS-GUP-DHI-DT-22-1223 | 2022-12-13 | RC | DE-GUP-DT-E-22-1219 | 2023-01-04 | F | CRS-GUP-DHI-DT-23-1441 | 2023-01-31 | AC | DE-GUP-DT-E-23-102 | 2023-02-01 | 0(CP) | CRS-GUP-DHI-DT-23-1550 | 2023-02-19 | AA | DE-GUP-DT-E-23-442 | 2023-04-10 | 1
| GUP | CC02 | P1 | UBG | 170030 |  | GUP-CC02-P1UBG-170030 | STEP-UP & UNIT AUXILIARY TRANSFORMER FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2022-06-27 | 2022-09-25 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | TR Area | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-442 | 2023-04-10 | 1 | CRS-GUP-DHI-DT-23-1550 | 2023-02-19 | AA | DHI-GUP-DT-22-065 | 2022-02-14 | A | CRS-GUP-DHI-DT-22-227 | 2022-03-05 | RC | DHI-GUP-DT-22-147 | 2022-04-04 | B | CRS-GUP-DHI-DT-22-303 | 2022-04-17 | RC | DE-GUP-DT-E-22-378 | 2022-07-11 | C | CRS-GUP-DHI-DT-22-626 | 2022-08-18 | RR | DE-GUP-DT-E-22-680 | 2022-09-16 | D | CRS-GUP-DHI-DT-22-934 | 2022-10-21 | RC | DE-GUP-DT-E-22-960 | 2022-11-18 | E | CRS-GUP-DHI-DT-22-1223 | 2022-12-13 | RC | DE-GUP-DT-E-22-1219 | 2023-01-04 | F | CRS-GUP-DHI-DT-23-1441 | 2023-01-31 | AC | DE-GUP-DT-E-23-102 | 2023-02-01 | 0(CP) | CRS-GUP-DHI-DT-23-1550 | 2023-02-19 | AA | DE-GUP-DT-E-23-442 | 2023-04-10 | 1
| GUP | CC03 | P1 | UBG | 170034 |  | GUP-CC03-P1UBG-170034 | STEP-UP & UNIT AUXILIARY TRANSFORMER FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FI | 2022-06-27 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | TR Area | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-442 | 2023-04-10 | 7 | CRS-GUP-DHI-DT-23-1550 | 2023-02-19 | NC | DHI-GUP-DT-22-065 | 2022-02-14 | 0 | CRS-GUP-DHI-DT-22-227 | 2022-03-05 | RC | DHI-GUP-DT-22-147 | 2022-04-04 | 1 | CRS-GUP-DHI-DT-22-303 | 2022-04-17 | NC | DE-GUP-DT-E-22-378 | 2022-07-11 | 2 | CRS-GUP-DHI-DT-22-626 | 2022-08-18 | RR | DE-GUP-DT-E-22-680 | 2022-09-16 | 3 | CRS-GUP-DHI-DT-22-934 | 2022-10-21 | NC | DE-GUP-DT-E-22-960 | 2022-11-18 | 4 | CRS-GUP-DHI-DT-22-1223 | 2022-12-13 | NC | DE-GUP-DT-E-22-1219 | 2023-01-04 | 5 | CRS-GUP-DHI-DT-23-1441 | 2023-01-31 | NC | DE-GUP-DT-E-23-102 | 2023-02-01 | 6 | CRS-GUP-DHI-DT-23-1550 | 2023-02-19 | NC | DE-GUP-DT-E-23-442 | 2023-04-10 | 7
| GUP | CC07 | P1 | BAA | 170060 |  | GUP-CC07-P1BAA-170060 | NSPB FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2022-08-23 | 2022-12-21 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | NSPB | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-892 | 2023-11-09 | 1 | CRS-GUP-DHI-DT-23-1573 | 2023-02-23 | AA | DE-GUP-DT-E-22-897 | 2022-11-01 | A | CRS-GUP-DHI-DT-22-1039 | 2022-11-16 | AC | DE-GUP-DT-E-23-054 | 2023-01-19 | 0(CP) | CRS-GUP-DHI-DT-23-1573 | 2023-02-23 | AA | DE-GUP-DT-E-23-892 | 2023-11-09 | 1
| GUP | CC02 | P1 | BAA | 170062 |  | GUP-CC02-P1BAA-170062 | NSPB FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2022-08-23 | 2022-12-21 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | NSPB | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-892 | 2023-11-09 | 2 | CRS-GUP-DHI-DT-23-2070 | 2023-07-02 | AA | DE-GUP-DT-E-22-897 | 2022-11-01 | A | CRS-GUP-DHI-DT-22-1039 | 2022-11-16 | AC | DE-GUP-DT-E-23-054 | 2023-01-19 | 0(CP) | CRS-GUP-DHI-DT-23-1573 | 2023-02-23 | AC | DE-GUP-DT-E-23-688 | 2023-07-12 | 1(CP) | CRS-GUP-DHI-DT-23-2070 | 2023-07-02 | AA | DE-GUP-DT-E-23-892 | 2023-11-09 | 2
| GUP | CC07 | P1 | EKF | 170068 |  | GUP-CC07-P1EKF-170068 | FUEL GAS STATION FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2024-11-29 | 2025-02-05 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | FUEL GAS STATION | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-25-042 | 2025-03-26 | 0 | 별도 메일접수 25-014 | 2025-03-14 | AC | DE-GUP-DT-E-24-251 | 2024-10-21 | A | 별도 메일접수 25-014 | 2025-03-14 | AC | DE-GUP-DT-E-25-042 | 2025-03-26 | 0
| GUP | CC02 | P1 | EKF | 170070 |  | GUP-CC02-P1EKF-170070 | FUEL GAS STATION FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FI | 2024-11-29 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | FUEL GAS STATION | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-251 | 2024-10-21 | 0 | 별도 메일접수 25-014 | 2025-03-14 | AC | DE-GUP-DT-E-24-251 | 2024-10-21 | 0 | 별도 메일접수 25-014 | 2025-03-14 | AC
| GUP | CC07 | P1 | QLC | 170076 |  | GUP-CC07-P1QLC-170076 | CEP & CONDENSER FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2022-08-11 | 2022-11-11 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | CEP & Condenser | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-650 | 2023-06-28 | 2 | CRS-GUP-DHI-DT-23-1434 | 2023-01-31 | AA | DE-GUP-DT-E-22-458 | 2022-07-27 | A | CRS-GUP-DHI-DT-22-678 | 2022-08-22 | RC | DE-GUP-DT-E-22-724 | 2022-09-29 | B | CRS-GUP-DHI-DT-22-888 | 2022-10-10 | AC | DE-GUP-DT-E-22-863 | 2022-10-27 | 0(CP) | CRS-GUP-DHI-DT-22-968 | 2022-11-07 | AC | DE-GUP-DT-E-22-1224 | 2023-01-05 | 1(CP) | CRS-GUP-DHI-DT-23-1434 | 2023-01-31 | AA | DE-GUP-DT-E-23-650 | 2023-06-28 | 2
| GUP | CC02 | P1 | QLC | 170078 |  | GUP-CC02-P1QLC-170078 | CEP & CONDENSER FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2022-08-11 | 2022-11-11 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | CEP & Condenser | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-650 | 2023-06-28 | 2 | CRS-GUP-DHI-DT-23-1434 | 2023-01-31 | AA | DE-GUP-DT-E-22-458 | 2022-07-27 | A | CRS-GUP-DHI-DT-22-678 | 2022-08-22 | RC | DE-GUP-DT-E-22-724 | 2022-09-29 | B | CRS-GUP-DHI-DT-22-888 | 2022-10-10 | AC | DE-GUP-DT-E-22-863 | 2022-10-27 | 0(CP) | CRS-GUP-DHI-DT-22-968 | 2022-11-07 | AC | DE-GUP-DT-E-22-1224 | 2023-01-05 | 1(CP) | CRS-GUP-DHI-DT-23-1434 | 2023-01-31 | AA | DE-GUP-DT-E-23-650 | 2023-06-28 | 2
| GUP | CC07 | P1 | HBA | 170084 |  | GUP-CC07-P1HBA-170084 | HEAT RECOVERY STEAM GENERATOR FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2021-12-31 | 2022-06-30 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | HRSG Building | Civil. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-649 | 2023-06-28 | 2 | CRS-GUP-DHI-DT-23-2062 | 2023-07-15 | AA | DHI-GUP-DT-21-199 | 2021-12-24 | A | CRS-GUP-DHI-DT-21-154 | 2022-01-12 | RC | DHI-GUP-DT-22-070 | 2022-02-15 | B | CRS-GUP-DHI-DT-22-232 | 2022-03-07 | RC | DHI-GUP-DT-22-146 | 2022-04-04 | C | CRS-GUP-DHI-DT-22-302 | 2022-04-17 | AC | DE-GUP-DT-E-22-372 | 2022-07-08 | 0(CP) | CRS-GUP-DHI-DT-22-566 | 2022-08-02 | AC | DE-GUP-DT-E-22-590 | 2022-08-31 | 1(CP) | CRS-GUP-DHI-DT-22-826 | 2022-09-22 | AC | DE-GUP-DT-E-23-649 | 2023-06-28 | 2 | CRS-GUP-DHI-DT-23-2062 | 2023-07-15 | AA
| GUP | CC02 | P1 | HBA | 170086 |  | GUP-CC02-P1HBA-170086 | HEAT RECOVERY STEAM GENERATOR FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2021-12-31 | 2022-06-30 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | HRSG Building | Civil. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-649 | 2023-06-28 | 3 | CRS-GUP-DHI-DT-23-2062 | 2023-07-15 | AA | DHI-GUP-DT-21-199 | 2021-12-24 | A | CRS-GUP-DHI-DT-21-154 | 2022-01-12 | RC | DHI-GUP-DT-22-070 | 2022-02-15 | B | CRS-GUP-DHI-DT-22-232 | 2022-03-07 | RC | DHI-GUP-DT-22-146 | 2022-04-04 | C | CRS-GUP-DHI-DT-22-302 | 2022-04-17 | AC | DE-GUP-DT-E-22-372 | 2022-07-08 | 0(CP) | CRS-GUP-DHI-DT-22-566 | 2022-08-02 | AC | DE-GUP-DT-E-22-590 | 2022-08-31 | 1(CP) | CRS-GUP-DHI-DT-22-826 | 2022-09-22 | AC | DE-GUP-DT-E-23-180 | 2023-02-15 | 2(CP) | CRS-GUP-DHI-DT-23-1599 | 2023-02-28 | AA | DE-GUP-DT-E-23-649 | 2023-06-28 | 3 | CRS-GUP-DHI-DT-23-2062 | 2023-07-15 | AA
| GUP | CC03 | P1 | HBA | 170090 |  | GUP-CC03-P1HBA-170090 | HEAT RECOVERY STEAM GENERATOR FOUNDATION (CCPP PLANT AREA)_REBAR DETAIL | FI | 2021-12-31 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | HRSG Building | Civil. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-649 | 2023-06-28 | 4 | CRS-GUP-DHI-DT-23-2062 | 2023-07-15 | NC | DHI-GUP-DT-21-199 | 2021-12-24 | 0 | CRS-GUP-DHI-DT-21-154 | 2022-01-12 | NC | DHI-GUP-DT-22-070 | 2022-02-15 | 1 | CRS-GUP-DHI-DT-22-232 | 2022-03-07 | NC | DE-GUP-DT-E-22-372 | 2022-07-08 | 2 | CRS-GUP-DHI-DT-22-566 | 2022-08-02 | RC | DE-GUP-DT-E-23-180 | 2023-02-15 | 3 | CRS-GUP-DHI-DT-23-1599 | 2023-02-28 | NC | DE-GUP-DT-E-23-649 | 2023-06-28 | 4 | CRS-GUP-DHI-DT-23-2062 | 2023-07-15 | NC
| GUP | CC07 | P1 | HBA | 170092 |  | GUP-CC07-P1HBA-170092 | HRSG MISC. FOUNDATION (CCPP PLANT AREA)_CALCULATION | FI | 2022-10-01 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | HRSG MISC. | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-022 | 2023-01-13 | 2 | CRS-GUP-DHI-DT-23-1526 | 2023-02-14 | NC | DE-GUP-DT-E-22-354 | 2022-07-01 | A | CRS-GUP-DHI-DT-22-522 | 2022-07-19 | RC | DE-GUP-DT-E-22-1012 | 2022-11-30 | 1 | CRS-GUP-DHI-DT-22-1271 | 2022-12-16 | NC | DE-GUP-DT-E-23-022 | 2023-01-13 | 2 | CRS-GUP-DHI-DT-23-1526 | 2023-02-14 | NC
| GUP | CC02 | P1 | HBA | 170094 |  | GUP-CC02-P1HBA-170094 | HRSG MISC. FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FI | 2022-10-01 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | HRSG MISC. | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-290 | 2023-03-09 | 3 | CRS-GUP-DHI-DT-23-1763 | 2023-03-22 | NC | DE-GUP-DT-E-22-354 | 2022-07-01 | A | CRS-GUP-DHI-DT-22-522 | 2022-07-19 | RC | DE-GUP-DT-E-22-1012 | 2022-11-30 | 1 | CRS-GUP-DHI-DT-22-1271 | 2022-12-16 | NC | DE-GUP-DT-E-23-022 | 2023-01-13 | 2 | CRS-GUP-DHI-DT-23-1526 | 2023-02-14 | NC | DE-GUP-DT-E-23-290 | 2023-03-09 | 3 | CRS-GUP-DHI-DT-23-1763 | 2023-03-22 | NC
| GUP | CC07 | P1 | HBA | 170100 |  | GUP-CC07-P1HBA-170100 | CHEMICAL DOSING SKID FOUNDATION FOR HRSG (CCPP PLANT AREA)_CALCULATION | FA | 2022-10-26 | 2022-12-25 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | CHEMICAL DOSING SKID | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-657 | 2023-06-30 | 2 | CRS-GUP-DHI-DT-23-1650 | 2023-03-07 | AA | DE-GUP-DT-E-22-936 | 2022-11-11 | A | CRS-GUP-DHI-DT-22-1188 | 2022-11-30 | AC | DE-GUP-DT-E-23-029 | 2023-01-16 | 0(CP) | CRS-GUP-DHI-DT-22-1453 | 2023-02-03 | AC | DE-GUP-DT-E-23-219 | 2023-02-22 | 1(CP) | CRS-GUP-DHI-DT-23-1650 | 2023-03-07 | AA | DE-GUP-DT-E-23-657 | 2023-06-30 | 2
| GUP | CC02 | P1 | HBA | 170102 |  | GUP-CC02-P1HBA-170102 | CHEMICAL DOSING SKID FOUNDATION FOR HRSG (CCPP PLANT AREA)_PLAN AND SECTION | FI | 2022-10-26 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | CHEMICAL DOSING SKID | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-657 | 2023-06-30 | 3 | CRS-GUP-DHI-DT-23-1650 | 2023-03-07 | NC | DE-GUP-DT-E-22-936 | 2022-11-11 | 0 | CRS-GUP-DHI-DT-22-1188 | 2022-11-30 | RC | DE-GUP-DT-E-23-029 | 2023-01-16 | 1 | CRS-GUP-DHI-DT-22-1453 | 2023-02-03 | RC | DE-GUP-DT-E-23-219 | 2023-02-22 | 2 | CRS-GUP-DHI-DT-23-1650 | 2023-03-07 | NC | DE-GUP-DT-E-23-657 | 2023-06-30 | 3
| GUP | CC03 | P1 | HBA | 170106 |  | GUP-CC03-P1HBA-170106 | CHEMICAL DOSING SKID FOUNDATION FOR HRSG (CCPP PLANT AREA)_REBAR DETAIL | FI | 2022-10-26 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | CHEMICAL DOSING SKID | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-657 | 2023-06-30 | 2 | CRS-GUP-DHI-DT-22-1453 | 2023-02-03 | NC | DE-GUP-DT-E-22-936 | 2022-11-11 | 0 | CRS-GUP-DHI-DT-22-1188 | 2022-11-30 | NC | DE-GUP-DT-E-23-029 | 2023-01-16 | 1 | CRS-GUP-DHI-DT-22-1453 | 2023-02-03 | NC | DE-GUP-DT-E-23-657 | 2023-06-30 | 2
| GUP | CC07 | P1 | QLA | 170108 |  | GUP-CC07-P1QLA-170108 | HP & IP FEED WATER PUMP FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2022-09-27 | 2022-11-26 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | BFP | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-673 | 2023-07-11 | 1 | CRS-GUP-DHI-DT-23-2066 | 2023-07-24 | AA | DE-GUP-DT-E-22-452 | 2022-07-26 | A | CRS-GUP-DHI-DT-22-594 | 2022-08-08 | AC | DE-GUP-DT-E-22-732 | 2022-09-30 | 0(CP) | CRS-GUP-DHI-DT-22-891 | 2022-10-10 | AA | DE-GUP-DT-E-23-673 | 2023-07-11 | 1 | CRS-GUP-DHI-DT-23-2066 | 2023-07-24 | AA
| GUP | CC02 | P1 | QLA | 170110 |  | GUP-CC02-P1QLA-170110 | HP & IP FEED WATER PUMP FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FI | 2022-09-27 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | BFP | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-673 | 2023-07-11 | 2 | CRS-GUP-DHI-DT-23-2066 | 2023-07-24 | NC | DE-GUP-DT-E-22-452 | 2022-07-26 | A | CRS-GUP-DHI-DT-22-594 | 2022-08-08 | AC | DE-GUP-DT-E-22-732 | 2022-09-30 | 1 | CRS-GUP-DHI-DT-22-891 | 2022-10-10 | RC | DE-GUP-DT-E-23-673 | 2023-07-11 | 2 | CRS-GUP-DHI-DT-23-2066 | 2023-07-24 | NC
| GUP | CC07 | P1 | QUA | 170116 |  | GUP-CC07-P1QUA-170116 | SAMPLING SYSTEM FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2023-01-05 | 2023-04-05 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | SAMPLING | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-651 | 2023-06-29 | 1 | CRS-GUP-DHI-DT-23-1429 | 2023-01-31 | AA | DE-GUP-DT-E-22-1132 | 2022-12-20 | A | CRS-GUP-DHI-DT-22-1387 | 2023-01-03 | AC | DE-GUP-DT-E-22-1220 | 2023-01-04 | 0(CP) | CRS-GUP-DHI-DT-23-1429 | 2023-01-31 | AA | DE-GUP-DT-E-23-651 | 2023-06-29 | 1
| GUP | CC02 | P1 | QUA | 170118 |  | GUP-CC02-P1QUA-170118 | SAMPLING SYSTEM FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FI | 2023-01-05 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | SAMPLING | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-1220 | 2023-01-04 | 1 | CRS-GUP-DHI-DT-23-1429 | 2023-01-31 | NC | DE-GUP-DT-E-22-1132 | 2022-12-20 | 0 | CRS-GUP-DHI-DT-22-1387 | 2023-01-03 | RC | DE-GUP-DT-E-22-1220 | 2023-01-04 | 1 | CRS-GUP-DHI-DT-23-1429 | 2023-01-31 | NC
| GUP | CC07 | P1 | PAD | 170124 |  | GUP-CC07-P1PAD-170124 | COOLING TOWER FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2022-07-17 | 2022-10-15 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | Cooling Tower | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-665 | 2023-07-04 | 4 | CRS-GUP-DHI-DT-23-1803 | 2023-04-04 | AA | DHI-GUP-DT-22-027 | 2022-01-20 | A | CRS-GUP-DHI-DT-21-185 | 2022-02-04 | RC | DE-GUP-DT-E-22-477 | 2022-07-29 | B | CRS-GUP-DHI-DT-22-690 | 2022-08-23 | AC | DE-GUP-DT-E-22-750 | 2022-10-04 | 0(CP) | CRS-GUP-DHI-DT-22-925 | 2022-10-19 | AC | DE-GUP-DT-E-22-1180 | 2022-12-23 | 1(CP) | CRS-GUP-DHI-DT-22-1402 | 2023-01-07 | AA | DE-GUP-DT-E-23-206 | 2023-02-20 | 2(CP) | CRS-GUP-DHI-DT-23-1691 | 2023-03-14 | RC | DE-GUP-DT-E-23-330 | 2023-03-20 | 3(CP) | CRS-GUP-DHI-DT-23-1803 | 2023-04-04 | AA | DE-GUP-DT-E-23-665 | 2023-07-04 | 4
| GUP | CC02 | P1 | PAD | 170126 |  | GUP-CC02-P1PAD-170126 | COOLING TOWER FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2022-07-17 | 2022-10-15 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | Cooling Tower | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-665 | 2023-07-04 | 4 | CRS-GUP-DHI-DT-23-1803 | 2023-04-04 | AA | DHI-GUP-DT-22-027 | 2022-01-20 | A | CRS-GUP-DHI-DT-21-185 | 2022-02-04 | RC | DE-GUP-DT-E-22-477 | 2022-07-29 | B | CRS-GUP-DHI-DT-22-690 | 2022-08-23 | AC | DE-GUP-DT-E-22-750 | 2022-10-04 | 0(CP) | CRS-GUP-DHI-DT-22-925 | 2022-10-19 | AC | DE-GUP-DT-E-22-1180 | 2022-12-23 | 1(CP) | CRS-GUP-DHI-DT-22-1402 | 2023-01-07 | AA | DE-GUP-DT-E-23-206 | 2023-02-20 | 2(CP) | CRS-GUP-DHI-DT-23-1691 | 2023-03-14 | RC | DE-GUP-DT-E-23-330 | 2023-03-20 | 3(CP) | CRS-GUP-DHI-DT-23-1803 | 2023-04-04 | AA | DE-GUP-DT-E-23-665 | 2023-07-04 | 4
| GUP | CC03 | P1 | PAD | 170130 |  | GUP-CC03-P1PAD-170130 | COOLING TOWER FOUNDATION (CCPP PLANT AREA)_REBAR DETAIL | FI | 2022-07-17 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | Cooling Tower | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-665 | 2023-07-04 | 6 | CRS-GUP-DHI-DT-23-1803 | 2023-04-04 | NC | DHI-GUP-DT-22-027 | 2022-01-20 | 0 | CRS-GUP-DHI-DT-21-185 | 2022-02-04 | RC | DE-GUP-DT-E-22-477 | 2022-07-29 | 1 | CRS-GUP-DHI-DT-22-690 | 2022-08-23 | NC | DE-GUP-DT-E-22-750 | 2022-10-04 | 2 | CRS-GUP-DHI-DT-22-925 | 2022-10-19 | NC | DE-GUP-DT-E-22-1180 | 2022-12-23 | 3 | CRS-GUP-DHI-DT-22-1402 | 2023-01-07 | NC | DE-GUP-DT-E-23-206 | 2023-02-20 | 4 | CRS-GUP-DHI-DT-23-1691 | 2023-03-14 | RC | DE-GUP-DT-E-23-330 | 2023-03-20 | 5 | CRS-GUP-DHI-DT-23-1803 | 2023-04-04 | NC | DE-GUP-DT-E-23-665 | 2023-07-04 | 6
| GUP | CC07 | P1 | QLC | 170132 |  | GUP-CC07-P1QLC-170132 | CONDENSER VACUUM PUMP FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2022-12-18 | 2023-02-16 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | CVP | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-484 | 2023-04-21 | 2 | CRS-GUP-DHI-DT-23-1909 | 2023-05-05 | AA | DE-GUP-DT-E-22-451 | 2022-07-26 | A | CRS-GUP-DHI-DT-22-593 | 2022-08-08 | AC | DE-GUP-DT-E-22-735 | 2022-09-30 | 0(CP) | CRS-GUP-DHI-DT-22-892 | 2022-10-10 | AA | DE-GUP-DT-E-22-1221 | 2023-01-04 | 1(CP) | CRS-GUP-DHI-DT-22-1444 | 2023-02-01 | AA | DE-GUP-DT-E-23-484 | 2023-04-21 | 2 | CRS-GUP-DHI-DT-23-1909 | 2023-05-05 | AA
| GUP | CC02 | P1 | QLC | 170134 |  | GUP-CC02-P1QLC-170134 | CONDENSER VACUUM PUMP FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FI | 2022-12-18 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | CVP | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-484 | 2023-04-21 | 3 | CRS-GUP-DHI-DT-23-1909 | 2023-05-05 | NC | DE-GUP-DT-E-22-451 | 2022-07-26 | A | CRS-GUP-DHI-DT-22-593 | 2022-08-08 | AC | DE-GUP-DT-E-22-735 | 2022-09-30 | 1 | CRS-GUP-DHI-DT-22-892 | 2022-10-10 | RC | DE-GUP-DT-E-22-1221 | 2023-01-04 | 2 | CRS-GUP-DHI-DT-22-1444 | 2023-02-01 | NC | DE-GUP-DT-E-23-484 | 2023-04-21 | 3 | CRS-GUP-DHI-DT-23-1909 | 2023-05-05 | NC
| GUP | CC07 | P1 | PAC | 170140 |  | GUP-CC07-P1PAC-170140 | CLOSED COOLING WATER PUMP FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2022-10-04 | 2023-01-02 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | CCWP | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-679 | 2023-07-07 | 1 | CRS-GUP-DHI-DT-22-966 | 2022-11-07 | AA | DE-GUP-DT-E-22-771 | 2022-10-07 | A | CRS-GUP-DHI-DT-22-932 | 2022-10-19 | RR | DE-GUP-DT-E-22-848 | 2022-10-24 | B | CRS-GUP-DHI-DT-22-966 | 2022-11-07 | AA | DE-GUP-DT-E-23-021 | 2023-01-13 | 0(CP) | N/A 발주처에서 보낸 첨부파일 참고 | N/A | AA | DE-GUP-DT-E-23-679 | 2023-07-07 | 1
| GUP | CC02 | P1 | PAC | 170142 |  | GUP-CC02-P1PAC-170142 | CLOSED COOLING WATER PUMP FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2022-10-04 | 2023-01-02 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | CCWP | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-679 | 2023-07-07 | 1 | CRS-GUP-DHI-DT-22-966 | 2022-11-07 | AA | DE-GUP-DT-E-22-771 | 2022-10-07 | A | CRS-GUP-DHI-DT-22-932 | 2022-10-19 | RR | DE-GUP-DT-E-22-848 | 2022-10-24 | B | CRS-GUP-DHI-DT-22-966 | 2022-11-07 | AA | DE-GUP-DT-E-23-021 | 2023-01-13 | 0(CP) | N/A 발주처에서 보낸 첨부파일 참고 | N/A | AA | DE-GUP-DT-E-23-679 | 2023-07-07 | 1
| GUP | CC07 | P1 | PBJ | 170148 |  | GUP-CC07-P1PBJ-170148 | CLOSED COOLING WATER COOLER FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2022-11-29 | 2023-02-27 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | CCW COOLER | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-893 | 2023-11-09 | 1 | CRS-GUP-DHI-DT-22-1452 | 2023-02-03 | AA | DE-GUP-DT-E-22-1030 | 2022-12-05 | A | CRS-GUP-DHI-DT-22-1284 | 2022-12-21 | AC | DE-GUP-DT-E-23-013 | 2023-01-12 | 0(CP) | CRS-GUP-DHI-DT-22-1452 | 2023-02-03 | AA | DE-GUP-DT-E-23-893 | 2023-11-09 | 1
| GUP | CC02 | P1 | PBJ | 170150 |  | GUP-CC02-P1PBJ-170150 | CLOSED COOLING WATER COOLER FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FI | 2022-11-29 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | CCW COOLER | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-420 | 2023-04-05 | 3 | CRS-GUP-DHI-DT-23-1868 | 2023-04-20 | NC | DE-GUP-DT-E-22-1030 | 2022-12-05 | 0 | CRS-GUP-DHI-DT-22-1284 | 2022-12-21 | RC | DE-GUP-DT-E-23-013 | 2023-01-12 | 1 | CRS-GUP-DHI-DT-22-1452 | 2023-02-03 | NC | DE-GUP-DT-E-23-271 | 2023-03-07 | 2 | CRS-GUP-DHI-DT-23-1757 | 2023-03-22 | NC | DE-GUP-DT-E-23-420 | 2023-04-05 | 3 | CRS-GUP-DHI-DT-23-1868 | 2023-04-20 | NC
| GUP | CC07 | P1 | PAH | 170156 |  | GUP-CC07-P1PAH-170156 | BALL RECIRCULATION PUMP FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2022-08-18 | 2022-11-21 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | Ball Recir. Pump | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-680 | 2023-07-07 | 3 | CRS-GUP-DHI-DT-23-1896 | 2023-05-02 | AA | DE-GUP-DT-E-22-450 | 2022-07-26 | A | CRS-GUP-DHI-DT-22-592 | 2022-08-08 | AC | DE-GUP-DT-E-22-716 | 2022-09-29 | 0(CP) | CRS-GUP-DHI-DT-22-1121 | 2022-11-23 | AA | DE-GUP-DT-E-22-1222 | 2023-01-04 | 1(CP) | CRS-GUP-DHI-DT-23-1433 | 2023-01-31 | AA | DE-GUP-DT-E-23-483 | 2023-04-21 | 2 | CRS-GUP-DHI-DT-23-1896 | 2023-05-02 | AA | DE-GUP-DT-E-23-680 | 2023-07-07 | 3
| GUP | CC02 | P1 | PAH | 170158 |  | GUP-CC02-P1PAH-170158 | BALL RECIRCULATION PUMP FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2022-08-18 | 2022-11-21 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | Ball Recir. Pump | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-680 | 2023-07-07 | 3 | CRS-GUP-DHI-DT-23-1896 | 2023-05-02 | AA | DE-GUP-DT-E-22-450 | 2022-07-26 | A | CRS-GUP-DHI-DT-22-592 | 2022-08-08 | AC | DE-GUP-DT-E-22-716 | 2022-09-29 | 0(CP) | CRS-GUP-DHI-DT-22-1121 | 2022-11-23 | AA | DE-GUP-DT-E-22-1222 | 2023-01-04 | 1(CP) | CRS-GUP-DHI-DT-23-1433 | 2023-01-31 | AC | DE-GUP-DT-E-23-483 | 2023-04-21 | 2(CP) | CRS-GUP-DHI-DT-23-1896 | 2023-05-02 | AA | DE-GUP-DT-E-23-680 | 2023-07-07 | 3
| GUP | CC07 | P1 | UTS | 170164 |  | GUP-CC07-P1UTS-170164 | CHEMIC ADDITIVE TANK FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2022-10-11 | 2022-12-10 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | CHEMIC INJECTION TANK | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-656 | 2023-06-30 | 1 | CRS-GUP-DHI-DT-22-931 | 2022-10-19 | AA | DE-GUP-DT-E-22-395 | 2022-07-13 | A | CRS-GUP-DHI-DT-22-569 | 2022-08-02 | AC | DE-GUP-DT-E-22-765 | 2022-10-07 | 0(CP) | CRS-GUP-DHI-DT-22-931 | 2022-10-19 | AA | DE-GUP-DT-E-23-656 | 2023-06-30 | 1
| GUP | CC02 | P1 | UTS | 170166 |  | GUP-CC02-P1UTS-170166 | CHEMIC ADDITIVE TANK FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FI | 2022-10-11 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | CHEMIC INJECTION TANK | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-656 | 2023-06-30 | 5 | CRS-GUP-DHI-DT-23-1840 | 2023-04-18 | NC | DE-GUP-DT-E-22-395 | 2022-07-13 | A | CRS-GUP-DHI-DT-22-569 | 2022-08-02 | AC | DE-GUP-DT-E-22-765 | 2022-10-07 | 1 | CRS-GUP-DHI-DT-22-931 | 2022-10-19 | NC | DE-GUP-DT-E-23-019 | 2023-01-13 | 2 | CRS-GUP-DHI-DT-23-1464 | 2023-02-08 | NC | DE-GUP-DT-E-23-268 | 2023-03-06 | 3 | CRS-GUP-DHI-DT-23-1715 | 2023-03-14 | RC | DE-GUP-DT-E-23-438 | 2023-04-07 | 4 | CRS-GUP-DHI-DT-23-1840 | 2023-04-18 | NC | DE-GUP-DT-E-23-656 | 2023-06-30 | 5
| GUP | CC03 | P1 | UTS | 170170 |  | GUP-CC03-P1UTS-170170 | CHEMIC ADDITIVE TANK FOUNDATION (CCPP PLANT AREA)_REBAR DETAIL | FI | 2022-10-11 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | CHEMIC INJECTION TANK | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-656 | 2023-06-30 | 5 | CRS-GUP-DHI-DT-23-1840 | 2023-04-18 | NC | DE-GUP-DT-E-22-395 | 2022-07-13 | 0 | CRS-GUP-DHI-DT-22-569 | 2022-08-02 | RC | DE-GUP-DT-E-22-765 | 2022-10-07 | 1 | CRS-GUP-DHI-DT-22-931 | 2022-10-19 | NC | DE-GUP-DT-E-23-019 | 2023-01-13 | 2 | CRS-GUP-DHI-DT-23-1464 | 2023-02-08 | NC | DE-GUP-DT-E-23-268 | 2023-03-06 | 3 | CRS-GUP-DHI-DT-23-1715 | 2023-03-14 | NC | DE-GUP-DT-E-23-438 | 2023-04-07 | 4 | CRS-GUP-DHI-DT-23-1840 | 2023-04-18 | NC | DE-GUP-DT-E-23-656 | 2023-06-30 | 5
| GUP | CC07 | P1 | PAC | 170172 |  | GUP-CC07-P1PAC-170172 | COOLING WATER PUMP STATION FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2022-07-17 | 2022-10-15 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | CWP | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-663 | 2023-07-04 | 1 | CRS-GUP-DHI-DT-23-1597 | 2023-02-28 | AA | DHI-GUP-DT-22-132 | 2022-03-24 | A | CRS-GUP-DHI-DT-22-293 | 2022-04-17 | RR | DE-GUP-DT-E-22-478 | 2022-07-29 | B | CRS-GUP-DHI-DT-22-642 | 2022-08-20 | RR | DE-GUP-DT-E-22-751 | 2022-10-04 | C | DRM메일_신효철 차장님 수신 | 2022-10-28 | RR | DE-GUP-DT-E-22-919 | 2022-11-08 | D | CRS-GUP-DHI-DT-22-1047 | 2022-11-16 | RC | DE-GUP-DT-E-22-1171 | 2022-12-23 | E | CRS-GUP-DHI-DT-22-1414 | 2023-01-11 | RC | DE-GUP-DT-E-23-018 | 2023-01-13 | F | CRS-GUP-DHI-DT-23-1463 | 2023-02-08 | AC | DE-GUP-DT-E-23-176 | 2023-02-14 | 0(CP) | CRS-GUP-DHI-DT-23-1597 | 2023-02-28 | AA | DE-GUP-DT-E-23-663 | 2023-07-04 | 1
| GUP | CC02 | P1 | PAC | 170174 |  | GUP-CC02-P1PAC-170174 | COOLING WATER PUMP STATION FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2022-07-17 | 2022-10-15 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | CWP | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-663 | 2023-07-04 | 1 | CRS-GUP-DHI-DT-23-1597 | 2023-02-28 | AA | DHI-GUP-DT-22-132 | 2022-03-24 | A | CRS-GUP-DHI-DT-22-293 | 2022-04-17 | RR | DE-GUP-DT-E-22-478 | 2022-07-29 | B | CRS-GUP-DHI-DT-22-642 | 2022-08-20 | RR | DE-GUP-DT-E-22-751 | 2022-10-04 | C | DRM메일_신효철 차장님 수신 | 2022-10-28 | RR | DE-GUP-DT-E-22-919 | 2022-11-08 | D | CRS-GUP-DHI-DT-22-1047 | 2022-11-16 | RC | DE-GUP-DT-E-22-1171 | 2022-12-23 | E | CRS-GUP-DHI-DT-22-1414 | 2023-01-11 | RC | DE-GUP-DT-E-23-018 | 2023-01-13 | F | CRS-GUP-DHI-DT-23-1463 | 2023-02-08 | AC | DE-GUP-DT-E-23-176 | 2023-02-14 | 0(CP) | CRS-GUP-DHI-DT-23-1597 | 2023-02-28 | AA | DE-GUP-DT-E-23-663 | 2023-07-04 | 1
| GUP | CC04 | P1 | PAC | 170176 |  | GUP-CC04-P1PAC-170176 | COOLING WATER PUMP STATION FOUNDATION (CCPP PLANT AREA)_DETAIL | FI | 2022-07-17 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | CWP | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-663 | 2023-07-04 | 7 | CRS-GUP-DHI-DT-23-1597 | 2023-02-28 | NC | DHI-GUP-DT-22-132 | 2022-03-24 | 0 | CRS-GUP-DHI-DT-22-293 | 2022-04-17 | RR | DE-GUP-DT-E-22-478 | 2022-07-29 | 1 | CRS-GUP-DHI-DT-22-642 | 2022-08-20 | RR | DE-GUP-DT-E-22-751 | 2022-10-04 | 2 | DRM메일_신효철 차장님 수신 | 2022-10-28 | RR | DE-GUP-DT-E-22-919 | 2022-11-08 | 3 | CRS-GUP-DHI-DT-22-1047 | 2022-11-16 | RC | DE-GUP-DT-E-22-1171 | 2022-12-23 | 4 | CRS-GUP-DHI-DT-22-1414 | 2023-01-11 | RC | DE-GUP-DT-E-23-018 | 2023-01-13 | 5 | CRS-GUP-DHI-DT-23-1463 | 2023-02-08 | NC | DE-GUP-DT-E-23-176 | 2023-02-14 | 6 | CRS-GUP-DHI-DT-23-1597 | 2023-02-28 | NC | DE-GUP-DT-E-23-663 | 2023-07-04 | 7
| GUP | CC03 | P1 | PAC | 170178 |  | GUP-CC03-P1PAC-170178 | COOLING WATER PUMP STATION FOUNDATION (CCPP PLANT AREA)_REBAR DETAIL | FI | 2022-07-17 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | CWP | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-663 | 2023-07-04 | 7 | CRS-GUP-DHI-DT-23-1597 | 2023-02-28 | NC | DHI-GUP-DT-22-132 | 2022-03-24 | 0 | CRS-GUP-DHI-DT-22-293 | 2022-04-17 | RR | DE-GUP-DT-E-22-478 | 2022-07-29 | 1 | CRS-GUP-DHI-DT-22-642 | 2022-08-20 | RR | DE-GUP-DT-E-22-751 | 2022-10-04 | 2 | DRM메일_신효철 차장님 수신 | 2022-10-28 | RR | DE-GUP-DT-E-22-919 | 2022-11-08 | 3 | CRS-GUP-DHI-DT-22-1047 | 2022-11-16 | RC | DE-GUP-DT-E-22-1171 | 2022-12-23 | 4 | CRS-GUP-DHI-DT-22-1414 | 2023-01-11 | RC | DE-GUP-DT-E-23-018 | 2023-01-13 | 5 | CRS-GUP-DHI-DT-23-1463 | 2023-02-08 | NC | DE-GUP-DT-E-23-176 | 2023-02-14 | 6 | CRS-GUP-DHI-DT-23-1597 | 2023-02-28 | NC | DE-GUP-DT-E-23-663 | 2023-07-04 | 7
| GUP | UH00 | P1 | PAB | 170182 |  | GUP-UH00-P1PAB-170182 | COOLING WATER PIPE CIVIL WORKS (CCPP PLANT AREA)_LAYOUT | FA | 2022-05-14 | 2022-10-06 | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | CCPP | CW PIPE | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-664 | 2023-07-04 | 1 | CRS-GUP-DHI-DT-23-1432 | 2023-01-31 | AA | DHI-GUP-DT-21-143 | 2021-12-03 | 0 | CRS-GUP-DHI-DT-21-103 | 2021-12-27 | RC | DHI-GUP-DT-22-059 | 2022-02-07 | 1 | CRS-GUP-DHI-DT-22-216 | 2022-02-20 | RC | DHI-GUP-DT-22-124 | 2022-03-21 | 2 | CRS-GUP-DHI-DT-22-285 | 2022-04-07 | RC | DE-GUP-DT-E-22-567 | 2022-08-26 | 3 | CRS-GUP-DHI-DT-22-784 | 2022-09-19 | RC | DE-GUP-DT-E-22-908 | 2022-11-04 | E | CRS-GUP-DHI-DT-22-1252 | 2022-12-13 | AA | DE-GUP-DT-E-22-1223 | 2023-01-05 | 0(CP) | CRS-GUP-DHI-DT-23-1432 | 2023-01-31 | AA | DE-GUP-DT-E-23-664 | 2023-07-04 | 1
| GUP | CC02 | P1 | PAB | 170184 |  | GUP-CC02-P1PAB-170184 | COOLING WATER PIPE CIVIL WORKS (CCPP PLANT AREA)_PLAN AND SECTION | FI | 2022-05-14 |  | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | CCPP | CW PIPE | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-664 | 2023-07-04 | 6 | CRS-GUP-DHI-DT-23-1432 | 2023-01-31 | NC | DHI-GUP-DT-21-143 | 2021-12-03 | 0 | CRS-GUP-DHI-DT-21-103 | 2021-12-27 | RC | DHI-GUP-DT-22-059 | 2022-02-07 | 1 | CRS-GUP-DHI-DT-22-216 | 2022-02-20 | NC | DHI-GUP-DT-22-124 | 2022-03-21 | 2 | CRS-GUP-DHI-DT-22-285 | 2022-04-07 | RC | DE-GUP-DT-E-22-567 | 2022-08-26 | 3 | CRS-GUP-DHI-DT-22-784 | 2022-09-19 | RC | DE-GUP-DT-E-22-908 | 2022-11-04 | 4 | CRS-GUP-DHI-DT-22-1252 | 2022-12-13 | NC | DE-GUP-DT-E-22-1223 | 2023-01-05 | 5 | CRS-GUP-DHI-DT-23-1432 | 2023-01-31 | NC | DE-GUP-DT-E-23-664 | 2023-07-04 | 6
| GUP | CC07 | P1 | LAA | 170192 |  | GUP-CC07-P1LAA-170192 | STARTUP FLASH TANK FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2022-08-30 | 2022-11-28 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | STARTUP FLASH TANK | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-538 | 2023-05-09 | 1 | CRS-GUP-DHI-DT-22-924 | 2022-10-19 | AA | DE-GUP-DT-E-22-394 | 2022-07-13 | A | CRS-GUP-DHI-DT-22-568 | 2022-08-02 | RC | DE-GUP-DT-E-22-610 | 2022-09-02 | B | CRS-GUP-DHI-DT-22-767 | 2022-09-14 | AC | DE-GUP-DT-E-22-747 | 2022-10-04 | 0(CP) | CRS-GUP-DHI-DT-22-924 | 2022-10-19 | AA | DE-GUP-DT-E-23-538 | 2023-05-09 | 1
| GUP | CC02 | P1 | LAA | 170194 |  | GUP-CC02-P1LAA-170194 | STARTUP FLASH TANK FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2022-08-30 | 2022-11-28 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | STARTUP FLASH TANK | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-815 | 2023-09-18 | 3 | 자체 CRS 개정 후 제출 | 2023-09-17 | N/A | DE-GUP-DT-E-22-394 | 2022-07-13 | A | CRS-GUP-DHI-DT-22-568 | 2022-08-02 | RC | DE-GUP-DT-E-22-610 | 2022-09-02 | B | CRS-GUP-DHI-DT-22-767 | 2022-09-14 | AC | DE-GUP-DT-E-22-747 | 2022-10-04 | 0(CP) | CRS-GUP-DHI-DT-22-924 | 2022-10-19 | AA | DE-GUP-DT-E-22-998 | 2022-11-28 | 1(CP) | CRS-GUP-DHI-DT-22-1265 | 2022-12-16 | AA | DE-GUP-DT-E-23-538 | 2023-05-09 | 2 | 자체 CRS 개정 후 제출 | 2023-09-17 | N/A | DE-GUP-DT-E-23-815 | 2023-09-18 | 3
| GUP | CC03 | P1 | LAA | 170198 |  | GUP-CC03-P1LAA-170198 | STARTUP FLASH TANK FOUNDATION (CCPP PLANT AREA)_REBAR DETAIL | FI | 2022-08-30 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | STARTUP FLASH TANK | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-815 | 2023-09-18 | 5 | 자체 CRS 개정 후 제출 | 2023-09-17 | N/A | DE-GUP-DT-E-22-394 | 2022-07-13 | 0 | CRS-GUP-DHI-DT-22-568 | 2022-08-02 | RC | DE-GUP-DT-E-22-610 | 2022-09-02 | 1 | CRS-GUP-DHI-DT-22-767 | 2022-09-14 | NC | DE-GUP-DT-E-22-747 | 2022-10-04 | 2 | CRS-GUP-DHI-DT-22-924 | 2022-10-19 | NC | DE-GUP-DT-E-22-998 | 2022-11-28 | 3 | CRS-GUP-DHI-DT-22-1265 | 2022-12-16 | NC | DE-GUP-DT-E-23-538 | 2023-05-09 | 4 | 자체 CRS 개정 후 제출 | 2023-09-17 | N/A | DE-GUP-DT-E-23-815 | 2023-09-18 | 5
| GUP | CC02 | P1 | GUB | 170210 |  | GUP-CC02-P1GUB-170210 | STORMWATER POND (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2023-05-29 | 2023-08-26 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | Stormwater Pond | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-127 | 2024-05-03 | 3 | 자체 CRS 개정 후 제출 | 2024-05-02 | N/A | DE-GUP-DT-E-22-838 | 2022-10-21 | A | CRS-GUP-DHI-DT-22-1036 | 2022-11-16 | RC | DE-GUP-DT-E-22-1076 | 2022-12-12 | B | CRS-GUP-DHI-DT-22-1332 | 2022-12-28 | AA | DE-GUP-DT-E-23-361 | 2023-03-24 | 0 | 자체 CRS 개정 후 제출 | 2023-07-24 | N/A | DE-GUP-DT-E-23-719 | 2023-07-25 | 1(CP) | 자체 CRS 개정 후 제출 | 2023-11-09 | N/A | DE-GUP-DT-E-23-899 | 2023-11-10 | 2(CP) | 자체 CRS 개정 후 제출 | 2024-05-02 | N/A | DE-GUP-DT-E-24-127 | 2024-05-03 | 3
| GUP | CC07 | P1 | UAH | 170216 |  | GUP-CC07-P1UAH-170216 | SWITCH YARD FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2022-07-28 | 2022-10-26 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | SWYD Building | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-687 | 2023-07-12 | 2 | CRS-GUP-DHI-DT-22-1451 | 2023-02-03 | AA | DHI-GUP-DT-22-103 | 2022-03-08 | A | CRS-GUP-DHI-DT-22-262 | 2022-03-18 | RC | DHI-GUP-DT-22-197 | 2022-05-02 | B | CRS-GUP-DHI-DT-22-350 | 2022-05-18 | RC | DE-GUP-DT-E-22-438 | 2022-07-22 | C | CRS-GUP-DHI-DT-22-674 | 2022-08-22 | RC | DE-GUP-DT-E-22-736 | 2022-09-30 | D | CRS-GUP-DHI-DT-22-893 | 2022-10-10 | RC | DE-GUP-DT-E-22-871 | 2022-10-28 | E | CRS-GUP-DHI-DT-22-1081 | 2022-11-19 | AC | DE-GUP-DT-E-22-1153 | 2022-12-22 | 0(CP) | CRS-GUP-DHI-DT-22-1390 | 2023-01-03 | AC | DE-GUP-DT-E-22-1253 | 2023-01-11 | 1(CP) | CRS-GUP-DHI-DT-22-1451 | 2023-02-03 | AA | DE-GUP-DT-E-23-687 | 2023-07-12 | 2
| GUP | CC02 | P1 | UAH | 170218 |  | GUP-CC02-P1UAH-170218 | SWITCH YARD FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2022-07-28 | 2022-10-26 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | SWYD Building | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-011 | 2024-01-16 | 3 | N/A(자체 CRS 개정 후 제출) | 2024-01-15 | N/A | DHI-GUP-DT-22-103 | 2022-03-08 | A | CRS-GUP-DHI-DT-22-262 | 2022-03-18 | RC | DHI-GUP-DT-22-197 | 2022-05-02 | B | CRS-GUP-DHI-DT-22-350 | 2022-05-18 | RC | DE-GUP-DT-E-22-438 | 2022-07-22 | C | CRS-GUP-DHI-DT-22-674 | 2022-08-22 | RC | DE-GUP-DT-E-22-736 | 2022-09-30 | D | CRS-GUP-DHI-DT-22-893 | 2022-10-10 | RC | DE-GUP-DT-E-22-871 | 2022-10-28 | E | CRS-GUP-DHI-DT-22-1081 | 2022-11-19 | AC | DE-GUP-DT-E-22-1153 | 2022-12-22 | 0(CP) | CRS-GUP-DHI-DT-22-1390 | 2023-01-03 | AC | DE-GUP-DT-E-22-1253 | 2023-01-11 | 1(CP) | CRS-GUP-DHI-DT-22-1451 | 2023-02-03 | AA | DE-GUP-DT-E-23-687 | 2023-07-12 | 2 | N/A(자체 CRS 개정 후 제출) | 2024-01-15 | N/A | DE-GUP-DT-E-24-011 | 2024-01-16 | 3
| GUP | CC03 | P1 | UAH | 170222 |  | GUP-CC03-P1UAH-170222 | SWITCH YARD FOUNDATION (CCPP PLANT AREA)_REBAR DETAIL | FI | 2022-07-28 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | SWYD Building | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-011 | 2024-01-16 | 8 | N/A(자체 CRS 개정 후 제출) | 2024-01-15 | N/A | DHI-GUP-DT-22-103 | 2022-03-08 | 0 | CRS-GUP-DHI-DT-22-262 | 2022-03-18 | NC | DHI-GUP-DT-22-197 | 2022-05-02 | 1 | CRS-GUP-DHI-DT-22-350 | 2022-05-18 | RC | DE-GUP-DT-E-22-438 | 2022-07-22 | 2 | CRS-GUP-DHI-DT-22-674 | 2022-08-22 | RC | DE-GUP-DT-E-22-736 | 2022-09-30 | 3 | CRS-GUP-DHI-DT-22-893 | 2022-10-10 | RC | DE-GUP-DT-E-22-871 | 2022-10-28 | 4 | CRS-GUP-DHI-DT-22-1081 | 2022-11-19 | AC | DE-GUP-DT-E-22-1153 | 2022-12-22 | 5 | CRS-GUP-DHI-DT-22-1390 | 2023-01-03 | RC | DE-GUP-DT-E-22-1253 | 2023-01-11 | 6 | CRS-GUP-DHI-DT-22-1451 | 2023-02-03 | NC | DE-GUP-DT-E-23-687 | 2023-07-12 | 7 | N/A(자체 CRS 개정 후 제출) | 2024-01-15 | N/A | DE-GUP-DT-E-24-011 | 2024-01-16 | 8
| GUP | CC07 | P1 | UXX | 170224 |  | GUP-CC07-P1UXX-170224 | BESS AREA CIVIL WORKS (CCPP PLANT AREA)_CALCULATION | FA | 2023-03-14 | 2023-06-12 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | BESS Building | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-126 | 2024-05-03 | 2 | CRS-GUP-DHI-DT-24-017 | 2024-02-21 | AA | DE-GUP-DT-E-23-316 | 2023-03-15 | A | CRS-GUP-DHI-DT-23-1787 | 2023-03-30 | RC | DE-GUP-DT-E-23-634 | 2023-06-21 | B | CRS-GUP-DHI-DT-23-2028 | 2023-07-04 | AC | DE-GUP-DT-E-23-682 | 2023-07-07 | 0(CP) | CRS-GUP-DHI-DT-23-2069 | 2023-07-24 | AA | DE-GUP-DT-E-23-914 | 2023-11-16 | 1(CP) | CRS-GUP-DHI-DT-24-017 | 2024-02-21 | AA | DE-GUP-DT-E-24-126 | 2024-05-03 | 2
| GUP | CC02 | P1 | UXX | 170226 |  | GUP-CC02-P1UXX-170226 | BESS AREA CIVIL WORKS (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2023-03-14 | 2023-06-12 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | BESS Building | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-126 | 2024-05-03 | 2 | CRS-GUP-DHI-DT-24-017 | 2024-02-21 | AA | DE-GUP-DT-E-23-316 | 2023-03-15 | A | CRS-GUP-DHI-DT-23-1787 | 2023-03-30 | RC | DE-GUP-DT-E-23-634 | 2023-06-21 | B | CRS-GUP-DHI-DT-23-2028 | 2023-07-04 | AC | DE-GUP-DT-E-23-682 | 2023-07-07 | 0(CP) | CRS-GUP-DHI-DT-23-2069 | 2023-07-24 | AC | DE-GUP-DT-E-23-914 | 2023-11-16 | 1(CP) | CRS-GUP-DHI-DT-24-017 | 2024-02-21 | AA | DE-GUP-DT-E-24-126 | 2024-05-03 | 2
| GUP | CC07 | P1 | EGB | 170232 |  | GUP-CC07-P1EGB-170232 | ULSD STORAGE TANK FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2022-04-13 | 2022-07-12 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | ULSD Tank | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-587 | 2023-05-30 | 2 | CRS-GUP-DHI-DT-23-1995 | 2023-06-13 | AA | DHI-GUP-DT-21-068 | 2021-10-15 | A | CRS-GUP-DHI-DT-21-049 | 2021-11-01 | RC | DHI-GUP-DT-21-148 | 2021-12-06 | B | CRS-GUP-DHI-DT-21-105 | 2021-12-27 | RC | DE-GUP-DT-E-22-240 | 2022-05-20 | C | CRS-GUP-DHI-DT-22-406 | 2022-06-09 | RC | DE-GUP-DT-E-22-356 | 2022-07-01 | D | CRS-GUP-DHI-DT-22-514 | 2022-07-12 | AC | DE-GUP-DT-E-22-401 | 2022-07-15 | 0(CP) | CRS-GUP-DHI-DT-22-580 | 2022-08-08 | AC | DE-GUP-DT-E-22-957 | 2022-11-17 | 0(CP) | CRS-GUP-DHI-DT-22-1217 | 2022-12-03 | AA | DE-GUP-DT-E-23-587 | 2023-05-30 | 2 | CRS-GUP-DHI-DT-23-1995 | 2023-06-13 | AA
| GUP | CC02 | P1 | EGB | 170234 |  | GUP-CC02-P1EGB-170234 | ULSD STORAGE TANK FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2022-04-13 | 2022-07-12 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | ULSD Tank | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-025 | 2024-01-25 | 5 | CRS-GUP-DHI-DT-23-1995 | 2023-06-13 | AA | DHI-GUP-DT-21-068 | 2021-10-15 | A | CRS-GUP-DHI-DT-21-049 | 2021-11-01 | RC | DHI-GUP-DT-21-148 | 2021-12-06 | B | CRS-GUP-DHI-DT-21-105 | 2021-12-27 | RC | DHI-GUP-DT-22-057 | 2022-01-28 | C | CRS-GUP-DHI-DT-22-214 | 2022-02-20 | RC | DE-GUP-DT-E-22-240 | 2022-05-20 | D | CRS-GUP-DHI-DT-22-406 | 2022-06-09 | RC | DE-GUP-DT-E-22-356 | 2022-07-01 | E | CRS-GUP-DHI-DT-22-514 | 2022-07-12 | AC | DE-GUP-DT-E-22-401 | 2022-07-15 | 0(CP) | CRS-GUP-DHI-DT-22-580 | 2022-08-08 | AC | DE-GUP-DT-E-22-957 | 2022-11-17 | 1(CP) | CRS-GUP-DHI-DT-22-1217 | 2022-12-03 | AA | DE-GUP-DT-E-23-270 | 2023-03-07 | 2(CP) | N/A(자체 CRS 개정 후 제출) | 2023-05-29 | N/C | DE-GUP-DT-E-23-587 | 2023-05-30 | 3 | CRS-GUP-DHI-DT-23-1995 | 2023-06-13 | AA | DE-GUP-DT-E-23-817 | 2023-09-19 | 4 | N/A(자체 CRS 개정 후 제출) | 2023-05-29 | N/C | DE-GUP-DT-E-24-025 | 2024-01-25 | 5
| GUP | CC04 | P1 | EGB | 170236 |  | GUP-CC04-P1EGB-170236 | ULSD STORAGE TANK FOUNDATION (CCPP PLANT AREA)_DETAIL | FI | 2022-04-13 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | ULSD Tank | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-817 | 2023-09-19 | 8 | CRS-GUP-DHI-DT-23-1995 | 2023-06-13 | NC | DHI-GUP-DT-21-068 | 2021-10-15 | 0 | CRS-GUP-DHI-DT-21-049 | 2021-11-01 | RC | DHI-GUP-DT-21-148 | 2021-12-06 | 1 | CRS-GUP-DHI-DT-21-105 | 2021-12-27 | NC | DHI-GUP-DT-22-057 | 2022-01-28 | 2 | CRS-GUP-DHI-DT-22-214 | 2022-02-20 | I | DE-GUP-DT-E-22-240 | 2022-05-20 | 3 | CRS-GUP-DHI-DT-22-406 | 2022-06-09 | RC | DE-GUP-DT-E-22-356 | 2022-07-01 | 4 | CRS-GUP-DHI-DT-22-514 | 2022-07-12 | NC | DE-GUP-DT-E-22-957 | 2022-11-17 | 5 | CRS-GUP-DHI-DT-22-1217 | 2022-12-03 | NC | DE-GUP-DT-E-23-270 | 2023-03-07 | 6 | CRS-GUP-DHI-DT-23-1750 | 2023-03-18 | NC | DE-GUP-DT-E-23-587 | 2023-05-30 | 7 | CRS-GUP-DHI-DT-23-1995 | 2023-06-13 | NC | DE-GUP-DT-E-23-817 | 2023-09-19 | 8
| GUP | CC03 | P1 | EGB | 170238 |  | GUP-CC03-P1EGB-170238 | ULSD STORAGE TANK FOUNDATION (CCPP PLANT AREA)_REBAR DETAIL | FI | 2022-04-13 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | ULSD Tank | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-587 | 2023-05-30 | 6 | CRS-GUP-DHI-DT-23-1995 | 2023-06-13 | NC | DHI-GUP-DT-21-068 | 2021-10-15 | 0 | CRS-GUP-DHI-DT-21-049 | 2021-11-01 | RC | DHI-GUP-DT-21-148 | 2021-12-06 | 1 | CRS-GUP-DHI-DT-21-105 | 2021-12-27 | NC | DHI-GUP-DT-22-057 | 2022-01-28 | 2 | CRS-GUP-DHI-DT-22-214 | 2022-02-20 | I | DE-GUP-DT-E-22-240 | 2022-05-20 | 3 | CRS-GUP-DHI-DT-22-406 | 2022-06-09 | RC | DE-GUP-DT-E-22-356 | 2022-07-01 | 4 | CRS-GUP-DHI-DT-22-514 | 2022-07-12 | NC | DE-GUP-DT-E-22-957 | 2022-11-17 | 5 | CRS-GUP-DHI-DT-22-1217 | 2022-12-03 | NC | DE-GUP-DT-E-23-587 | 2023-05-30 | 6 | CRS-GUP-DHI-DT-23-1995 | 2023-06-13 | NC
| GUP | CC07 | P1 | LAA | 170240 |  | GUP-CC07-P1LAA-170240 | UF FEED WATER TANK FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2022-08-28 | 2022-11-26 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | UF FW Tank | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-334 | 2023-03-21 | 2 | CRS-GUP-DHI-DT-23-1807 | 2023-04-04 | AA | DE-GUP-DT-E-22-368 | 2022-07-07 | A | CRS-GUP-DHI-DT-22-564 | 2022-08-02 | RC | DE-GUP-DT-E-22-563 | 2022-08-26 | B | CRS-GUP-DHI-DT-22-772 | 2022-09-15 | AC | DE-GUP-DT-E-22-746 | 2022-10-04 | 0(CP) | CRS-GUP-DHI-DT-22-923 | 2022-10-19 | AC | DE-GUP-DT-E-22-1242 | 2023-01-09 | 1(CP) | CRS-GUP-DHI-DT-23-1443 | 2023-01-31 | AA | DE-GUP-DT-E-23-334 | 2023-03-21 | 2 | CRS-GUP-DHI-DT-23-1807 | 2023-04-04 | AA
| GUP | CC02 | P1 | LAA | 170242 |  | GUP-CC02-P1LAA-170242 | UF FEED WATER TANK FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2022-08-28 | 2022-11-26 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | UF FW Tank | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-334 | 2023-03-21 | 2 | CRS-GUP-DHI-DT-23-1807 | 2023-04-04 | AA | DE-GUP-DT-E-22-368 | 2022-07-07 | A | CRS-GUP-DHI-DT-22-564 | 2022-08-02 | RC | DE-GUP-DT-E-22-563 | 2022-08-26 | B | CRS-GUP-DHI-DT-22-772 | 2022-09-15 | AC | DE-GUP-DT-E-22-746 | 2022-10-04 | 0(CP) | CRS-GUP-DHI-DT-22-923 | 2022-10-19 | AC | DE-GUP-DT-E-22-1242 | 2023-01-09 | 1(CP) | CRS-GUP-DHI-DT-23-1443 | 2023-01-31 | AA | DE-GUP-DT-E-23-334 | 2023-03-21 | 2 | CRS-GUP-DHI-DT-23-1807 | 2023-04-04 | AA
| GUP | CC04 | P1 | LAA | 170244 |  | GUP-CC04-P1LAA-170244 | UF FEED WATER TANK FOUNDATION (CCPP PLANT AREA)_DETAIL | FI | 2022-08-28 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | UF FW Tank | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-334 | 2023-03-21 | 4 | CRS-GUP-DHI-DT-23-1807 | 2023-04-04 | NC | DE-GUP-DT-E-22-368 | 2022-07-07 | 0 | CRS-GUP-DHI-DT-22-564 | 2022-08-02 | RC | DE-GUP-DT-E-22-563 | 2022-08-26 | 1 | CRS-GUP-DHI-DT-22-772 | 2022-09-15 | RC | DE-GUP-DT-E-22-746 | 2022-10-04 | 2 | CRS-GUP-DHI-DT-22-923 | 2022-10-19 | RC | DE-GUP-DT-E-22-1242 | 2023-01-09 | 3 | CRS-GUP-DHI-DT-23-1443 | 2023-01-31 | NC | DE-GUP-DT-E-23-334 | 2023-03-21 | 4 | CRS-GUP-DHI-DT-23-1807 | 2023-04-04 | NC
| GUP | CC03 | P1 | LAA | 170246 |  | GUP-CC03-P1LAA-170246 | UF FEED WATER TANK FOUNDATION (CCPP PLANT AREA)_REBAR DETAIL | FI | 2022-08-28 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | UF FW Tank | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-334 | 2023-03-21 | 4 | CRS-GUP-DHI-DT-23-1807 | 2023-04-04 | NC | DE-GUP-DT-E-22-368 | 2022-07-07 | 0 | CRS-GUP-DHI-DT-22-564 | 2022-08-02 | NC | DE-GUP-DT-E-22-563 | 2022-08-26 | 1 | CRS-GUP-DHI-DT-22-772 | 2022-09-15 | NC | DE-GUP-DT-E-22-746 | 2022-10-04 | 2 | CRS-GUP-DHI-DT-22-923 | 2022-10-19 | NC | DE-GUP-DT-E-22-1242 | 2023-01-09 | 3 | CRS-GUP-DHI-DT-23-1443 | 2023-01-31 | NC | DE-GUP-DT-E-23-334 | 2023-03-21 | 4 | CRS-GUP-DHI-DT-23-1807 | 2023-04-04 | NC
| GUP | CC07 | P1 | GBB | 170248 |  | GUP-CC07-P1GBB-170248 | WATER TREATMENT AREA FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2022-10-30 | 2023-01-28 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | WT & WWT Building | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-971 | 2023-12-05 | 4 | 자체 CRS 개정 후 제출 | 2023-12-04 | N/A | DHI-GUP-DT-22-134 | 2022-03-25 | A | CRS-GUP-DHI-DT-22-295 | 2022-04-17 | RR | DE-GUP-DT-E-22-405 | 2022-07-15 | B | CRS-GUP-DHI-DT-22-584 | 2022-08-08 | RR | DE-GUP-DT-E-22-823 | 2022-10-19 | C | CRS-GUP-DHI-DT-22-1035 | 2022-11-16 | AC | DE-GUP-DT-E-22-939 | 2022-11-14 | 0(CP) | CRS-GUP-DHI-DT-22-1211 | 2022-11-30 | AC | DE-GUP-DT-E-22-1115 | 2022-12-16 | 1(CP) | CRS-GUP-DHI-DT-22-1354 | 2022-12-29 | AA | DE-GUP-DT-E-23-169 | 2023-02-13 | 2(CP) | N/A(자체 CRS 개정 후 제출) | 2023-05-15 | NC | DE-GUP-DT-E-23-554 | 2023-05-16 | 3 | 자체 CRS 개정 후 제출 | 2023-12-04 | N/A | DE-GUP-DT-E-23-971 | 2023-12-05 | 4
| GUP | CC02 | P1 | GBB | 170250 |  | GUP-CC02-P1GBB-170250 | WATER TREATMENT AREA FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2022-10-30 | 2023-01-28 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | WT & WWT Building | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-971 | 2023-12-05 | 4 | 자체 CRS 개정 후 제출 | 2023-12-04 | N/A | DHI-GUP-DT-22-134 | 2022-03-25 | A | CRS-GUP-DHI-DT-22-295 | 2022-04-17 | RR | DE-GUP-DT-E-22-405 | 2022-07-15 | B | CRS-GUP-DHI-DT-22-584 | 2022-08-08 | RR | DE-GUP-DT-E-22-823 | 2022-10-19 | C | CRS-GUP-DHI-DT-22-1035 | 2022-11-16 | AC | DE-GUP-DT-E-22-939 | 2022-11-14 | 0(CP) | CRS-GUP-DHI-DT-22-1211 | 2022-11-30 | AC | DE-GUP-DT-E-22-1115 | 2022-12-16 | 1(CP) | CRS-GUP-DHI-DT-22-1354 | 2022-12-29 | AA | DE-GUP-DT-E-23-169 | 2023-02-13 | 2(CP) | N/A(자체 CRS 개정 후 제출) | 2023-05-15 | NC | DE-GUP-DT-E-23-554 | 2023-05-16 | 3 | 자체 CRS 개정 후 제출 | 2023-12-04 | N/A | DE-GUP-DT-E-23-971 | 2023-12-05 | 4
| GUP | CC04 | P1 | GBB | 170252 |  | GUP-CC04-P1GBB-170252 | WATER TREATMENT AREA FOUNDATION (CCPP PLANT AREA)_DETAIL | FI | 2022-10-30 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | WT & WWT Building | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-971 | 2023-12-05 | 7 | 자체 CRS 개정 후 제출 | 2023-12-04 | N/A | DHI-GUP-DT-22-134 | 2022-03-25 | 0 | CRS-GUP-DHI-DT-22-295 | 2022-04-17 | RR | DE-GUP-DT-E-22-405 | 2022-07-15 | 1 | CRS-GUP-DHI-DT-22-584 | 2022-08-08 | RR | DE-GUP-DT-E-22-823 | 2022-10-19 | 2 | CRS-GUP-DHI-DT-22-1035 | 2022-11-16 | NC | DE-GUP-DT-E-22-939 | 2022-11-14 | 3 | CRS-GUP-DHI-DT-22-1211 | 2022-11-30 | NC | DE-GUP-DT-E-22-1115 | 2022-12-16 | 4 | CRS-GUP-DHI-DT-22-1354 | 2022-12-29 | NC | DE-GUP-DT-E-23-169 | 2023-02-13 | 5 | N/A(자체 CRS 개정 후 제출) | 2023-05-15 | NC | DE-GUP-DT-E-23-554 | 2023-05-16 | 6 | 자체 CRS 개정 후 제출 | 2023-12-04 | N/A | DE-GUP-DT-E-23-971 | 2023-12-05 | 7
| GUP | CC03 | P1 | GBB | 170254 |  | GUP-CC03-P1GBB-170254 | WATER TREATMENT AREA FOUNDATION (CCPP PLANT AREA)_REBAR DETAIL | FI | 2022-10-30 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | WT & WWT Building | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-971 | 2023-12-05 | 7 | 자체 CRS 개정 후 제출 | 2023-12-04 | N/A | DHI-GUP-DT-22-134 | 2022-03-25 | 0 | CRS-GUP-DHI-DT-22-295 | 2022-04-17 | RR | DE-GUP-DT-E-22-405 | 2022-07-15 | 1 | CRS-GUP-DHI-DT-22-584 | 2022-08-08 | RR | DE-GUP-DT-E-22-823 | 2022-10-19 | 2 | CRS-GUP-DHI-DT-22-1035 | 2022-11-16 | NC | DE-GUP-DT-E-22-939 | 2022-11-14 | 3 | CRS-GUP-DHI-DT-22-1211 | 2022-11-30 | NC | DE-GUP-DT-E-22-1115 | 2022-12-16 | 4 | CRS-GUP-DHI-DT-22-1354 | 2022-12-29 | NC | DE-GUP-DT-E-23-169 | 2023-02-13 | 5 | N/A(자체 CRS 개정 후 제출) | 2023-05-15 | NC | DE-GUP-DT-E-23-554 | 2023-05-16 | 6 | 자체 CRS 개정 후 제출 | 2023-12-04 | N/A | DE-GUP-DT-E-23-971 | 2023-12-05 | 7
| GUP | CC07 | P1 | GHB | 170256 |  | GUP-CC07-P1GHB-170256 | TREATED WATER TANK FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2022-04-28 | 2022-07-27 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | TW Tank | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-335 | 2023-03-21 | 2 | CRS-GUP-DHI-DT-23-1808 | 2023-04-04 | AA | DHI-GUP-DT-21-067 | 2021-10-15 | A | CRS-GUP-DHI-DT-21-049 | 2021-11-01 | RC | DHI-GUP-DT-21-149 | 2021-12-06 | B | CRS-GUP-DHI-DT-21-086 | 2021-12-23 | RC | DE-GUP-DT-E-22-239 | 2022-05-20 | C | CRS-GUP-DHI-DT-22-426 | 2022-06-14 | RC | DE-GUP-DT-E-22-357 | 2022-07-01 | D | CRS-GUP-DHI-DT-22-520 | 2022-07-15 | RC | DE-GUP-DT-E-22-453 | 2022-07-26 | 0(CP) | CRS-GUP-DHI-DT-22-649 | 2022-08-20 | AC | DE-GUP-DT-E-22-1113 | 2022-12-16 | 1(CP) | CRS-GUP-DHI-DT-22-1353 | 2022-12-29 | AA | DE-GUP-DT-E-23-335 | 2023-03-21 | 2 | CRS-GUP-DHI-DT-23-1808 | 2023-04-04 | AA
| GUP | CC02 | P1 | GHB | 170258 |  | GUP-CC02-P1GHB-170258 | TREATED WATER TANK FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2022-04-28 | 2022-07-27 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | TW Tank | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-154 | 2024-06-14 | 3 | CRS-GUP-DHI-DT-23-1808 | 2023-04-04 | AA | DHI-GUP-DT-21-067 | 2021-10-15 | A | CRS-GUP-DHI-DT-21-049 | 2021-11-01 | RC | DHI-GUP-DT-21-149 | 2021-12-06 | B | CRS-GUP-DHI-DT-21-086 | 2021-12-23 | RC | DHI-GUP-DT-22-058 | 2022-01-28 | C | CRS-GUP-DHI-DT-22-215 | 2022-02-20 | RC | DE-GUP-DT-E-22-239 | 2022-05-20 | D | CRS-GUP-DHI-DT-22-426 | 2022-06-14 | RC | DE-GUP-DT-E-22-357 | 2022-07-01 | E | CRS-GUP-DHI-DT-22-520 | 2022-07-15 | RC | DE-GUP-DT-E-22-424 | 2022-07-20 | F | CRS-GUP-DHI-DT-22-544 | 2022-07-25 | AC | DE-GUP-DT-E-22-453 | 2022-07-26 | 0(CP) | CRS-GUP-DHI-DT-22-649 | 2022-08-20 | AC | DE-GUP-DT-E-22-1113 | 2022-12-16 | 1(CP) | CRS-GUP-DHI-DT-22-1353 | 2022-12-29 | AA | DE-GUP-DT-E-23-335 | 2023-03-21 | 2 | CRS-GUP-DHI-DT-23-1808 | 2023-04-04 | AA | DE-GUP-DT-E-24-154 | 2024-06-14 | 3
| GUP | CC04 | P1 | GHB | 170260 |  | GUP-CC04-P1GHB-170260 | TREATED WATER TANK FOUNDATION (CCPP PLANT AREA)_DETAIL | FI | 2022-04-28 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | TW Tank | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-154 | 2024-06-14 | 9 | CRS-GUP-DHI-DT-23-1808 | 2023-04-04 | NC | DHI-GUP-DT-21-067 | 2021-10-15 | 0 | CRS-GUP-DHI-DT-21-049 | 2021-11-01 | RC | DHI-GUP-DT-21-149 | 2021-12-06 | 1 | CRS-GUP-DHI-DT-21-086 | 2021-12-23 | NC | DHI-GUP-DT-22-058 | 2022-01-28 | 2 | CRS-GUP-DHI-DT-22-215 | 2022-02-20 | I | DE-GUP-DT-E-22-239 | 2022-05-20 | 3 | CRS-GUP-DHI-DT-22-426 | 2022-06-14 | RC | DE-GUP-DT-E-22-357 | 2022-07-01 | 4 | CRS-GUP-DHI-DT-22-520 | 2022-07-15 | RC | DE-GUP-DT-E-22-424 | 2022-07-20 | 5 | CRS-GUP-DHI-DT-22-544 | 2022-07-25 | NC | DE-GUP-DT-E-22-453 | 2022-07-26 | 6 | CRS-GUP-DHI-DT-22-649 | 2022-08-20 | NC | DE-GUP-DT-E-22-1113 | 2022-12-16 | 7 | CRS-GUP-DHI-DT-22-1353 | 2022-12-29 | NC | DE-GUP-DT-E-23-335 | 2023-03-21 | 8 | CRS-GUP-DHI-DT-23-1808 | 2023-04-04 | NC | DE-GUP-DT-E-24-154 | 2024-06-14 | 9
| GUP | CC03 | P1 | GHB | 170262 |  | GUP-CC03-P1GHB-170262 | TREATED WATER TANK FOUNDATION (CCPP PLANT AREA)_REBAR DETAIL | FI | 2022-04-28 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | TW Tank | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-335 | 2023-03-21 | 7 | CRS-GUP-DHI-DT-23-1808 | 2023-04-04 | NC | DHI-GUP-DT-21-067 | 2021-10-15 | 0 | CRS-GUP-DHI-DT-21-049 | 2021-11-01 | RC | DHI-GUP-DT-21-149 | 2021-12-06 | 1 | CRS-GUP-DHI-DT-21-086 | 2021-12-23 | NC | DHI-GUP-DT-22-058 | 2022-01-28 | 2 | CRS-GUP-DHI-DT-22-215 | 2022-02-20 | I | DE-GUP-DT-E-22-239 | 2022-05-20 | 3 | CRS-GUP-DHI-DT-22-426 | 2022-06-14 | RC | DE-GUP-DT-E-22-357 | 2022-07-01 | 4 | CRS-GUP-DHI-DT-22-520 | 2022-07-15 | NC | DE-GUP-DT-E-22-453 | 2022-07-26 | 5 | CRS-GUP-DHI-DT-22-649 | 2022-08-20 | NC | DE-GUP-DT-E-22-1113 | 2022-12-16 | 6 | CRS-GUP-DHI-DT-22-1353 | 2022-12-29 | NC | DE-GUP-DT-E-23-335 | 2023-03-21 | 7 | CRS-GUP-DHI-DT-23-1808 | 2023-04-04 | NC | DE-GUP-DT-E-24-154 | 1900-01-07
| GUP | CC07 | P1 | SGA | 170264 |  | GUP-CC07-P1SGA-170264 | FIRE WATER STORAGE TANK FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2022-09-01 | 2022-11-30 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | FF Tank | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-333 | 2023-03-20 | 1 | CRS-GUP-DHI-DT-23-1806 | 2023-04-04 | AA | DE-GUP-DT-E-22-366 | 2022-07-07 | A | CRS-GUP-DHI-DT-22-562 | 2022-08-02 | RC | DE-GUP-DT-E-22-565 | 2022-08-26 | B | CRS-GUP-DHI-DT-22-773 | 2022-09-15 | RC | DE-GUP-DT-E-22-743 | 2022-09-30 | C | CRS-GUP-DHI-DT-22-921 | 2022-10-19 | RC | DE-GUP-DT-E-22-862 | 2022-10-27 | D | CRS-GUP-DHI-DT-22-967 | 2022-11-07 | RC | DE-GUP-DT-E-22-950 | 2022-11-17 | E | CRS-GUP-DHI-DT-22-1216 | 2022-12-03 | AC | DE-GUP-DT-E-22-1238 | 2023-01-09 | 0(CP) | CRS-GUP-DHI-DT-23-1442 | 2023-01-31 | AA | DE-GUP-DT-E-23-333 | 2023-03-20 | 1 | CRS-GUP-DHI-DT-23-1806 | 2023-04-04 | AA
| GUP | CC02 | P1 | SGA | 170266 |  | GUP-CC02-P1SGA-170266 | FIRE WATER STORAGE TANK FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2022-09-01 | 2022-11-30 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | FF Tank | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-333 | 2023-03-20 | 1 | CRS-GUP-DHI-DT-23-1806 | 2023-04-04 | AA | DE-GUP-DT-E-22-366 | 2022-07-07 | A | CRS-GUP-DHI-DT-22-562 | 2022-08-02 | RC | DE-GUP-DT-E-22-565 | 2022-08-26 | B | CRS-GUP-DHI-DT-22-773 | 2022-09-15 | RC | DE-GUP-DT-E-22-743 | 2022-09-30 | C | CRS-GUP-DHI-DT-22-921 | 2022-10-19 | RC | DE-GUP-DT-E-22-862 | 2022-10-27 | D | CRS-GUP-DHI-DT-22-967 | 2022-11-07 | RC | DE-GUP-DT-E-22-950 | 2022-11-17 | E | CRS-GUP-DHI-DT-22-1216 | 2022-12-03 | AC | DE-GUP-DT-E-22-1238 | 2023-01-09 | 0(CP) | CRS-GUP-DHI-DT-23-1442 | 2023-01-31 | AA | DE-GUP-DT-E-23-333 | 2023-03-20 | 1 | CRS-GUP-DHI-DT-23-1806 | 2023-04-04 | AA
| GUP | CC04 | P1 | SGA | 170268 |  | GUP-CC04-P1SGA-170268 | FIRE WATER STORAGE TANK FOUNDATION (CCPP PLANT AREA)_DETAIL | FI | 2022-09-01 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | FF Tank | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-333 | 2023-03-20 | 6 | CRS-GUP-DHI-DT-23-1806 | 2023-04-04 | NC | DE-GUP-DT-E-22-366 | 2022-07-07 | 0 | CRS-GUP-DHI-DT-22-562 | 2022-08-02 | NC | DE-GUP-DT-E-22-565 | 2022-08-26 | 1 | CRS-GUP-DHI-DT-22-773 | 2022-09-15 | RC | DE-GUP-DT-E-22-743 | 2022-09-30 | 2 | CRS-GUP-DHI-DT-22-921 | 2022-10-19 | RC | DE-GUP-DT-E-22-862 | 2022-10-27 | 3 | CRS-GUP-DHI-DT-22-967 | 2022-11-07 | RC | DE-GUP-DT-E-22-950 | 2022-11-17 | 4 | CRS-GUP-DHI-DT-22-1216 | 2022-12-03 | NC | DE-GUP-DT-E-22-1238 | 2023-01-09 | 5 | CRS-GUP-DHI-DT-23-1442 | 2023-01-31 | NC | DE-GUP-DT-E-23-333 | 2023-03-20 | 6 | CRS-GUP-DHI-DT-23-1806 | 2023-04-04 | NC
| GUP | CC03 | P1 | SGA | 170270 |  | GUP-CC03-P1SGA-170270 | FIRE WATER STORAGE TANK FOUNDATION (CCPP PLANT AREA)_REBAR DETAIL | FI | 2022-09-01 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | FF Tank | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-333 | 2023-03-20 | 6 | CRS-GUP-DHI-DT-23-1806 | 2023-04-04 | NC | DE-GUP-DT-E-22-366 | 2022-07-07 | 0 | CRS-GUP-DHI-DT-22-562 | 2022-08-02 | NC | DE-GUP-DT-E-22-565 | 2022-08-26 | 1 | CRS-GUP-DHI-DT-22-773 | 2022-09-15 | RC | DE-GUP-DT-E-22-743 | 2022-09-30 | 2 | CRS-GUP-DHI-DT-22-921 | 2022-10-19 | RC | DE-GUP-DT-E-22-862 | 2022-10-27 | 3 | CRS-GUP-DHI-DT-22-967 | 2022-11-07 | RC | DE-GUP-DT-E-22-950 | 2022-11-17 | 4 | CRS-GUP-DHI-DT-22-1216 | 2022-12-03 | NC | DE-GUP-DT-E-22-1238 | 2023-01-09 | 5 | CRS-GUP-DHI-DT-23-1442 | 2023-01-31 | NC | DE-GUP-DT-E-23-333 | 2023-03-20 | 6 | CRS-GUP-DHI-DT-23-1806 | 2023-04-04 | NC
| GUP | CC07 | P1 | GKB | 170272 |  | GUP-CC07-P1GKB-170272 | POTABLE WATER TANK FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2023-01-07 | 2023-03-08 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | PW Tank | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-332 | 2023-03-20 | 1 | CRS-GUP-DHI-DT-23-1805 | 2023-04-04 | AA | DE-GUP-DT-E-22-367 | 2022-07-07 | A | CRS-GUP-DHI-DT-22-563 | 2022-08-02 | AC | DE-GUP-DT-E-22-562 | 2022-08-26 | B | CRS-GUP-DHI-DT-22-771 | 2022-09-15 | AC | DE-GUP-DT-E-22-1226 | 2023-01-05 | 0(CP) | CRS-GUP-DHI-DT-23-1430 | 2023-01-31 | AA | DE-GUP-DT-E-23-332 | 2023-03-20 | 1 | CRS-GUP-DHI-DT-23-1805 | 2023-04-04 | AA
| GUP | CC02 | P1 | GKB | 170274 |  | GUP-CC02-P1GKB-170274 | POTABLE WATER TANK FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2023-01-07 | 2023-03-08 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | PW Tank | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-071 | 2024-03-11 | 2 | CRS-GUP-DHI-DT-23-1805 | 2023-04-04 | AA | DE-GUP-DT-E-22-367 | 2022-07-07 | A | CRS-GUP-DHI-DT-22-563 | 2022-08-02 | AC | DE-GUP-DT-E-22-562 | 2022-08-26 | B | CRS-GUP-DHI-DT-22-771 | 2022-09-15 | AC | DE-GUP-DT-E-22-1226 | 2023-01-05 | 0(CP) | CRS-GUP-DHI-DT-23-1430 | 2023-01-31 | AA | DE-GUP-DT-E-23-332 | 2023-03-20 | 1 | CRS-GUP-DHI-DT-23-1805 | 2023-04-04 | AA | DE-GUP-DT-E-24-071 | 2024-03-11 | 2
| GUP | CC04 | P1 | GKB | 170276 |  | GUP-CC04-P1GKB-170276 | POTABLE WATER TANK FOUNDATION (CCPP PLANT AREA)_DETAIL | FI | 2023-01-07 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | PW Tank | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-332 | 2023-03-20 | 3 | CRS-GUP-DHI-DT-23-1805 | 2023-04-04 | NC | DE-GUP-DT-E-22-367 | 2022-07-07 | 0 | CRS-GUP-DHI-DT-22-563 | 2022-08-02 | RC | DE-GUP-DT-E-22-562 | 2022-08-26 | 1 | CRS-GUP-DHI-DT-22-771 | 2022-09-15 | NC | DE-GUP-DT-E-22-1226 | 2023-01-05 | 2 | CRS-GUP-DHI-DT-23-1430 | 2023-01-31 | NC | DE-GUP-DT-E-23-332 | 2023-03-20 | 3 | CRS-GUP-DHI-DT-23-1805 | 2023-04-04 | NC
| GUP | CC03 | P1 | GKB | 170278 |  | GUP-CC03-P1GKB-170278 | POTABLE WATER TANK FOUNDATION (CCPP PLANT AREA)_REBAR DETAIL | FI | 2023-01-07 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | PW Tank | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-332 | 2023-03-20 | 3 | CRS-GUP-DHI-DT-23-1805 | 2023-04-04 | NC | DE-GUP-DT-E-22-367 | 2022-07-07 | 0 | CRS-GUP-DHI-DT-22-563 | 2022-08-02 | NC | DE-GUP-DT-E-22-562 | 2022-08-26 | 1 | CRS-GUP-DHI-DT-22-771 | 2022-09-15 | NC | DE-GUP-DT-E-22-1226 | 2023-01-05 | 2 | CRS-GUP-DHI-DT-23-1430 | 2023-01-31 | NC | DE-GUP-DT-E-23-332 | 2023-03-20 | 3 | CRS-GUP-DHI-DT-23-1805 | 2023-04-04 | NC
| GUP | CC07 | P1 | UGD | 170280 |  | GUP-CC07-P1UGD-170280 | DEMI WATERTANK FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2022-09-28 | 2022-12-27 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | DW Tank | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-331 | 2023-03-20 | 1 | CRS-GUP-DHI-DT-23-1804 | 2023-04-04 | AA | DE-GUP-DT-E-22-365 | 2022-07-07 | A | CRS-GUP-DHI-DT-22-541 | 2022-07-25 | RC | DE-GUP-DT-E-22-566 | 2022-08-26 | B | CRS-GUP-DHI-DT-22-774 | 2022-09-15 | AC | DE-GUP-DT-E-22-1225 | 2023-01-05 | 0(CP) | CRS-GUP-DHI-DT-23-1431 | 2023-01-31 | AA | DE-GUP-DT-E-23-331 | 2023-03-20 | 1 | CRS-GUP-DHI-DT-23-1804 | 2023-04-04 | AA
| GUP | CC02 | P1 | UGD | 170282 |  | GUP-CC02-P1UGD-170282 | DEMI WATERTANK FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2022-09-28 | 2022-12-27 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | DW Tank | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-155 | 2024-06-14 | 2 | CRS-GUP-DHI-DT-23-1804 | 2023-04-04 | AA | DE-GUP-DT-E-22-365 | 2022-07-07 | A | CRS-GUP-DHI-DT-22-541 | 2022-07-25 | RC | DE-GUP-DT-E-22-566 | 2022-08-26 | B | CRS-GUP-DHI-DT-22-774 | 2022-09-15 | AC | DE-GUP-DT-E-22-1225 | 2023-01-05 | 0(CP) | CRS-GUP-DHI-DT-23-1431 | 2023-01-31 | AA | DE-GUP-DT-E-23-331 | 2023-03-20 | 1 | CRS-GUP-DHI-DT-23-1804 | 2023-04-04 | AA | DE-GUP-DT-E-24-155 | 2024-06-14 | 2
| GUP | CC04 | P1 | UGD | 170284 |  | GUP-CC04-P1UGD-170284 | DEMI WATERTANK FOUNDATION (CCPP PLANT AREA)_DETAIL | FI | 2022-09-28 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | DW Tank | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-155 | 2024-06-14 | 4 | CRS-GUP-DHI-DT-23-1804 | 2023-04-04 | NC | DE-GUP-DT-E-22-365 | 2022-07-07 | 0 | CRS-GUP-DHI-DT-22-541 | 2022-07-25 | RC | DE-GUP-DT-E-22-566 | 2022-08-26 | 1 | CRS-GUP-DHI-DT-22-774 | 2022-09-15 | NC | DE-GUP-DT-E-22-1225 | 2023-01-05 | 2 | CRS-GUP-DHI-DT-23-1431 | 2023-01-31 | NC | DE-GUP-DT-E-23-331 | 2023-03-20 | 3 | CRS-GUP-DHI-DT-23-1804 | 2023-04-04 | NC | DE-GUP-DT-E-24-155 | 2024-06-14 | 4
| GUP | CC03 | P1 | UGD | 170286 |  | GUP-CC03-P1UGD-170286 | DEMI WATERTANK FOUNDATION (CCPP PLANT AREA)_REBAR DETAIL | FI | 2022-09-28 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | DW Tank | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-155 | 2024-06-14 | 4 | CRS-GUP-DHI-DT-23-1804 | 2023-04-04 | NC | DE-GUP-DT-E-22-365 | 2022-07-07 | 0 | CRS-GUP-DHI-DT-22-541 | 2022-07-25 | RC | DE-GUP-DT-E-22-566 | 2022-08-26 | 1 | CRS-GUP-DHI-DT-22-774 | 2022-09-15 | NC | DE-GUP-DT-E-22-1225 | 2023-01-05 | 2 | CRS-GUP-DHI-DT-23-1431 | 2023-01-31 | NC | DE-GUP-DT-E-23-331 | 2023-03-20 | 3 | CRS-GUP-DHI-DT-23-1804 | 2023-04-04 | NC | DE-GUP-DT-E-24-155 | 2024-06-14 | 4
| GUP | CC07 | P1 | MKA | 170288 |  | GUP-CC07-P1MKA-170288 | EDG FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2022-10-22 | 2023-01-20 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | EDG | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-998 | 2023-12-18 | 2 | 자체 CRS 개정 후 제출 | 2023-12-17 | N/A | DE-GUP-DT-E-22-979 | 2022-11-23 | A | CRS-GUP-DHI-DT-22-1230 | 2022-12-13 | AC | DE-GUP-DT-E-23-053 | 2023-01-19 | 0(CP) | CRS-GUP-DHI-DT-23-1572 | 2023-02-23 | AA | DE-GUP-DT-E-23-652 | 2023-06-29 | 1 | 자체 CRS 개정 후 제출 | 2023-12-17 | N/A | DE-GUP-DT-E-23-998 | 2023-12-18 | 2
| GUP | CC02 | P1 | MKA | 170290 |  | GUP-CC02-P1MKA-170290 | EDG FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FI | 2022-10-22 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | EDG | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-998 | 2023-12-18 | 3 | CRS-GUP-DHI-DT-23-1751 | 2023-03-18 | NC | DE-GUP-DT-E-22-979 | 2022-11-23 | 0 | CRS-GUP-DHI-DT-22-1230 | 2022-12-13 | RC | DE-GUP-DT-E-23-053 | 2023-01-19 | 1 | CRS-GUP-DHI-DT-23-1572 | 2023-02-23 | NC | DE-GUP-DT-E-23-272 | 2023-03-07 | 2 | CRS-GUP-DHI-DT-23-1751 | 2023-03-18 | NC | DE-GUP-DT-E-23-998 | 2023-12-18 | 3
| GUP | CC03 | P1 | MKA | 170294 |  | GUP-CC03-P1MKA-170294 | EDG FOUNDATION (CCPP PLANT AREA)_REBAR DETAIL | FI | 2022-10-22 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | EDG | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-998 | 2023-12-18 | 3 | CRS-GUP-DHI-DT-23-1751 | 2023-03-18 | NC | DE-GUP-DT-E-22-979 | 2022-11-23 | 0 | CRS-GUP-DHI-DT-22-1230 | 2022-12-13 | NC | DE-GUP-DT-E-23-053 | 2023-01-19 | 1 | CRS-GUP-DHI-DT-23-1572 | 2023-02-23 | NC | DE-GUP-DT-E-23-272 | 2023-03-07 | 2 | CRS-GUP-DHI-DT-23-1751 | 2023-03-18 | NC | DE-GUP-DT-E-23-998 | 2023-12-18 | 3
| GUP | CC07 | P1 | UEM | 170296 |  | GUP-CC07-P1UEM-170296 | ULSD BUFFER TANK FOUNDATION AND ULSD SLUDGE PIT (CCPP PLANT AREA)_CALCULATION | FA | 2023-07-27 | 2023-10-25 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | ULSD Filter | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-666 | 2023-07-04 | 3 | CRS-GUP-DHI-DT-23-1943 | 2023-05-11 | AA | DE-GUP-DT-E-22-1164 | 2022-12-22 | A | CRS-GUP-DHI-DT-22-1397 | 2023-01-06 | AC | DE-GUP-DT-E-23-145 | 2023-02-09 | 0(CP) | CRS-GUP-DHI-DT-23-1577 | 2023-02-23 | AC | DE-GUP-DT-E-23-435 | 2023-04-07 | 1(CP) | CRS-GUP-DHI-DT-23-1838 | 2023-04-18 | AA | DE-GUP-DT-E-23-505 | 2023-04-25 | 2(CP) | CRS-GUP-DHI-DT-23-1943 | 2023-05-11 | AA | DE-GUP-DT-E-23-666 | 2023-07-04 | 3
| GUP | CC02 | P1 | UEM | 170298 |  | GUP-CC02-P1UEM-170298 | ULSD BUFFER TANK FOUNDATION AND ULSD SLUDGE PIT (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2023-07-27 | 2023-10-25 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | ULSD Filter | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-666 | 2023-07-04 | 3 | CRS-GUP-DHI-DT-23-1943 | 2023-05-11 | AA | DE-GUP-DT-E-22-1164 | 2022-12-22 | A | CRS-GUP-DHI-DT-22-1397 | 2023-01-06 | AC | DE-GUP-DT-E-23-145 | 2023-02-09 | 0(CP) | CRS-GUP-DHI-DT-23-1577 | 2023-02-23 | AC | DE-GUP-DT-E-23-435 | 2023-04-07 | 1(CP) | CRS-GUP-DHI-DT-23-1838 | 2023-04-18 | AC | DE-GUP-DT-E-23-505 | 2023-04-25 | 2(CP) | CRS-GUP-DHI-DT-23-1943 | 2023-05-11 | AA | DE-GUP-DT-E-23-666 | 2023-07-04 | 3
| GUP | CC04 | P1 | UEM | 170300 |  | GUP-CC04-P1UEM-170300 | ULSD BUFFER TANK FOUNDATION AND ULSD SLUDGE PIT (CCPP PLANT AREA)_DETAIL | FI | 2023-07-27 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | ULSD Filter | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-666 | 2023-07-04 | 4 | CRS-GUP-DHI-DT-23-1943 | 2023-05-11 | NC | DE-GUP-DT-E-22-1164 | 2022-12-22 | 0 | CRS-GUP-DHI-DT-22-1397 | 2023-01-06 | NC | DE-GUP-DT-E-23-145 | 2023-02-09 | 1 | CRS-GUP-DHI-DT-23-1577 | 2023-02-23 | NC | DE-GUP-DT-E-23-435 | 2023-04-07 | 2 | CRS-GUP-DHI-DT-23-1838 | 2023-04-18 | NC | DE-GUP-DT-E-23-505 | 2023-04-25 | 3 | CRS-GUP-DHI-DT-23-1943 | 2023-05-11 | NC | DE-GUP-DT-E-23-666 | 2023-07-04 | 4
| GUP | CC03 | P1 | UEM | 170302 |  | GUP-CC03-P1UEM-170302 | ULSD BUFFER TANK FOUNDATION AND ULSD SLUDGE PIT (CCPP PLANT AREA)_REBAR DETAIL | FI | 2023-07-27 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | ULSD Filter | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-666 | 2023-07-04 | 4 | CRS-GUP-DHI-DT-23-1943 | 2023-05-11 | NC | DE-GUP-DT-E-22-1164 | 2022-12-22 | 0 | CRS-GUP-DHI-DT-22-1397 | 2023-01-06 | NC | DE-GUP-DT-E-23-145 | 2023-02-09 | 1 | CRS-GUP-DHI-DT-23-1577 | 2023-02-23 | NC | DE-GUP-DT-E-23-435 | 2023-04-07 | 2 | CRS-GUP-DHI-DT-23-1838 | 2023-04-18 | NC | DE-GUP-DT-E-23-505 | 2023-04-25 | 3 | CRS-GUP-DHI-DT-23-1943 | 2023-05-11 | NC | DE-GUP-DT-E-23-666 | 2023-07-04 | 4
| GUP | CC07 | P1 | UTG | 170304 |  | GUP-CC07-P1UTG-170304 | SERVICE GAS SUPPLY FACILITY(N2) FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2022-12-15 | 2023-02-13 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | N2 Gas Facility | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-125 | 2024-05-03 | 2 | CRS-GUP-DHI-DT-24-019 | 2024-03-09 | AA | DE-GUP-DT-E-23-077 | 2023-01-26 | A | CRS-GUP-DHI-DT-23-1564 | 2023-02-23 | AC | DE-GUP-DT-E-23-275 | 2023-03-07 | 0(CP) | CRS-GUP-DHI-DT-23-1753 | 2023-03-18 | AC | DE-GUP-DT-E-23-913 | 2023-11-16 | 1(CP) | CRS-GUP-DHI-DT-24-019 | 2024-03-09 | AA | DE-GUP-DT-E-24-125 | 2024-05-03 | 2
| GUP | CC02 | P1 | UTG | 170306 |  | GUP-CC02-P1UTG-170306 | SERVICE GAS SUPPLY FACILITY(N2) FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2022-12-15 | 2023-02-13 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | N2 Gas Facility | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-125 | 2024-05-03 | 2 | CRS-GUP-DHI-DT-24-019 | 2024-03-09 | AA | DE-GUP-DT-E-23-077 | 2023-01-26 | A | CRS-GUP-DHI-DT-23-1564 | 2023-02-23 | AC | DE-GUP-DT-E-23-275 | 2023-03-07 | 0(CP) | CRS-GUP-DHI-DT-23-1753 | 2023-03-18 | AC | DE-GUP-DT-E-23-913 | 2023-11-16 | 1(CP) | CRS-GUP-DHI-DT-24-019 | 2024-03-09 | AA | DE-GUP-DT-E-24-125 | 2024-05-03 | 2
| GUP | CC07 | P1 | EKC | 170312 |  | GUP-CC07-P1EKC-170312 | PERFORMANCE HEATER & FINAL CHANCE FILTER FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2024-10-04 | 2025-02-05 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | PERFORMANCE HEATER & FINAL CHANCE FILTER | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-25-035 | 2025-03-19 | 0 | 별도 메일접수 25-006 | 2025-03-13 | AA | DE-GUP-DT-E-24-247 | 2024-10-11 | A | 별도 메일접수 24-009 | 2024-11-05 | RC | DE-GUP-DT-E-25-005 | 2025-01-17 | B | 별도 메일접수 25-006 | 2025-03-13 | AA | DE-GUP-DT-E-25-035 | 2025-03-19 | 0
| GUP | CC02 | P1 | EKC | 170314 |  | GUP-CC02-P1EKC-170314 | PERFORMANCE HEATER & FINAL CHANCE FILTER FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2024-10-04 | 2025-02-05 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | PERFORMANCE HEATER & FINAL CHANCE FILTER | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-25-035 | 2025-03-19 | 0 | 별도 메일접수 25-006 | 2025-03-13 | AA | DE-GUP-DT-E-24-247 | 2024-10-11 | A | 별도 메일접수 24-009 | 2024-11-05 | RC | DE-GUP-DT-E-25-005 | 2025-01-17 | B | 별도 메일접수 25-006 | 2025-03-13 | AA | DE-GUP-DT-E-25-035 | 2025-03-19 | 0
| GUP | UH00 | P1 | UZK | 170320 |  | GUP-UH00-P1UZK-170320 | LANDSCAPING_LAYOUT | FA | 2023-05-29 | 2023-08-26 | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | CCPP | Landscaping | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-697 | 2023-07-19 | 0 | CRS-GUP-DHI-DT-23-1727 | 2023-03-17 | AA | DE-GUP-DT-E-23-150 | 2023-02-09 | A | CRS-GUP-DHI-DT-23-1727 | 2023-03-17 | AA | DE-GUP-DT-E-23-697 | 2023-07-19 | 0
| GUP | CC07 | P1 | UZA | 170326 |  | GUP-CC07-P1UZA-170326 | ROAD & PAVING (CCPP PLANT AREA)_CALCULATION | FA | 2023-05-29 | 2023-08-26 | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | CCPP | Road & Paving | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-197 | 2024-08-08 | 0 | CRS-GUP-DHI-DT-24-069 | 2024-08-16 | AA | DE-GUP-DT-E-23-481 | 2023-04-20 | A | CRS-GUP-DHI-DT-23-1895 | 2023-05-02 | RC | DE-GUP-DT-E-23-632 | 2023-06-20 | B | CRS-GUP-DHI-DT-23-2027 | 2023-07-04 | RC | DE-GUP-DT-E-23-699 | 2023-07-20 | C | CRS-GUP-DHI-DT-23-2099 | 2023-08-22 | RC | DE-GUP-DT-E-23-780 | 2023-08-30 | D | CRS-GUP-DHI-DT-23-2110 | 2023-09-13 | RC | DE-GUP-DT-E-24-197 | 2024-08-08 | 0 | CRS-GUP-DHI-DT-24-069 | 2024-08-16 | AA
| GUP | UH00 | P1 | UZA | 170328 |  | GUP-UH00-P1UZA-170328 | ROAD & PAVING (CCPP PLANT AREA)_LAYOUT | FA | 2023-05-29 | 2023-08-26 | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | CCPP | Road & Paving | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-272 | 2024-12-09 | 1 | 자체 CRS 개정 후 제출 | 2024-11-13 | N/A | DE-GUP-DT-E-23-481 | 2023-04-20 | A | CRS-GUP-DHI-DT-23-1895 | 2023-05-02 | RC | DE-GUP-DT-E-23-632 | 2023-06-20 | B | CRS-GUP-DHI-DT-23-2027 | 2023-07-04 | RC | DE-GUP-DT-E-23-699 | 2023-07-20 | C | CRS-GUP-DHI-DT-23-2099 | 2023-08-22 | RC | DE-GUP-DT-E-23-780 | 2023-08-30 | D | CRS-GUP-DHI-DT-23-2110 | 2023-09-13 | RC | DE-GUP-DT-E-23-901 | 2023-11-10 | E | CRS-GUP-DHI-DT-23-2145 | 2023-12-30 | RC | DE-GUP-DT-E-24-092 | 2024-03-26 | F | 자체 CRS 개정 후 제출 | 2024-05-01 | N/A | DE-GUP-DT-E-24-121 | 2024-05-02 | G | CRS-GUP-DHI-DT-24-053 | 2024-06-03 | RC | DE-GUP-DT-E-24-197 | 2024-08-08 | H | CRS-GUP-DHI-DT-24-069 | 2024-08-16 | AA | DE-GUP-DT-E-24-227 | 2024-09-13 | 0 | 자체 CRS 개정 후 제출 | 2024-11-13 | N/A | DE-GUP-DT-E-24-272 | 2024-12-09 | 1
| GUP | CC02 | P1 | UZA | 170330 |  | GUP-CC02-P1UZA-170330 | ROAD & PAVING (CCPP PLANT AREA)_PLAN AND SECTION | FI | 2023-05-29 |  | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | CCPP | Road & Paving | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-272 | 2024-12-09 | 9 | 자체 CRS 개정 후 제출 | 2024-11-13 | N/A | DE-GUP-DT-E-23-481 | 2023-04-20 | 0 | CRS-GUP-DHI-DT-23-1895 | 2023-05-02 | RC | DE-GUP-DT-E-23-632 | 2023-06-20 | 1 | CRS-GUP-DHI-DT-23-2027 | 2023-07-04 | RC | DE-GUP-DT-E-23-699 | 2023-07-20 | 2 | CRS-GUP-DHI-DT-23-2099 | 2023-08-22 | RC | DE-GUP-DT-E-23-780 | 2023-08-30 | 3 | CRS-GUP-DHI-DT-23-2110 | 2023-09-13 | RC | DE-GUP-DT-E-23-901 | 2023-11-10 | 4 | CRS-GUP-DHI-DT-23-2145 | 2023-12-30 | RC | DE-GUP-DT-E-24-092 | 2024-03-26 | 5 | 자체 CRS 개정 후 제출 | 2024-05-01 | N/A | DE-GUP-DT-E-24-121 | 2024-05-02 | 6 | CRS-GUP-DHI-DT-24-053 | 2024-06-03 | RC | DE-GUP-DT-E-24-197 | 2024-08-08 | 7 | CRS-GUP-DHI-DT-24-069 | 2024-08-16 | NC | DE-GUP-DT-E-24-227 | 2024-09-13 | 8 | 자체 CRS 개정 후 제출 | 2024-11-13 | N/A | DE-GUP-DT-E-24-272 | 2024-12-09 | 9
| GUP | CC04 | P1 | UZA | 170332 |  | GUP-CC04-P1UZA-170332 | ROAD & PAVING (CCPP PLANT AREA)_DETAIL | FI | 2023-05-29 |  | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | CCPP | Road & Paving | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-272 | 2024-12-09 | 7 | 자체 CRS 개정 후 제출 | 2024-11-13 | N/A | DE-GUP-DT-E-23-481 | 2023-04-20 | 0 | CRS-GUP-DHI-DT-23-1895 | 2023-05-02 | RC | DE-GUP-DT-E-23-632 | 2023-06-20 | 1 | CRS-GUP-DHI-DT-23-2027 | 2023-07-04 | RC | DE-GUP-DT-E-23-699 | 2023-07-20 | 2 | CRS-GUP-DHI-DT-23-2099 | 2023-08-22 | RC | DE-GUP-DT-E-23-780 | 2023-08-30 | 3 | CRS-GUP-DHI-DT-23-2110 | 2023-09-13 | RC | DE-GUP-DT-E-23-901 | 2023-11-10 | 4 | CRS-GUP-DHI-DT-23-2145 | 2023-12-30 | NC | DE-GUP-DT-E-24-092 | 2024-03-26 | 5 | 자체 CRS 개정 후 제출 | 2024-09-05 | N/A | DE-GUP-DT-E-24-227 | 2024-09-13 | 6 | 자체 CRS 개정 후 제출 | 2024-11-13 | N/A | DE-GUP-DT-E-24-272 | 2024-12-09 | 7
| GUP | CC07 | P1 | UZA | 170336 |  | GUP-CC07-P1UZA-170336 | LIGHTING POLE & CCTV FOUNDATION (CCPP PLANT AREA)_CALCULATION | FI | 2023-05-29 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | LIGHTING POLE & CCTV | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-929 | 2023-11-22 | 2 | CRS-GUP-DHI-DT-24-005 | 2024-01-23 | NC | DE-GUP-DT-E-23-557 | 2023-05-16 | 0 | CRS-GUP-DHI-DT-23-1974 | 2023-06-01 | RC | DE-GUP-DT-E-23-633 | 2023-06-20 | 1 | CRS-GUP-DHI-DT-23-2034 | 2023-07-04 | NC | DE-GUP-DT-E-23-929 | 2023-11-22 | 2 | CRS-GUP-DHI-DT-24-005 | 2024-01-23 | NC
| GUP | UH00 | P1 | UZA | 170338 |  | GUP-UH00-P1UZA-170338 | LIGHTING POLE & CCTV FOUNDATION (CCPP PLANT AREA)_LAYOUT | FI | 2023-05-29 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | LIGHTING POLE & CCTV | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-264 | 2024-11-11 | 6 | 자체 CRS 개정 후 제출 | 2024-11-10 | N/A | DE-GUP-DT-E-23-557 | 2023-05-16 | 0 | CRS-GUP-DHI-DT-23-1974 | 2023-06-01 | NC | DE-GUP-DT-E-23-633 | 2023-06-20 | 1 | CRS-GUP-DHI-DT-23-2034 | 2023-07-04 | RC | DE-GUP-DT-E-23-929 | 2023-11-22 | 2 | CRS-GUP-DHI-DT-24-005 | 2024-01-23 | RC | DE-GUP-DT-E-24-093 | 2024-03-26 | 3 | 자체 CRS 개정 후 제출 | 2024-05-02 | N/A | DE-GUP-DT-E-24-124 | 2024-05-03 | 4 | CRS-GUP-DHI-DT-24-054 | 2024-06-03 | NC | DE-GUP-DT-E-24-201 | 2024-08-09 | 5 | 자체 CRS 개정 후 제출 | 2024-11-10 | N/A | DE-GUP-DT-E-24-264 | 2024-11-11 | 6
| GUP | CC02 | P1 | UZA | 170340 |  | GUP-CC02-P1UZA-170340 | LIGHTING POLE & CCTV FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FI | 2023-05-29 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | LIGHTING POLE & CCTV | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-264 | 2024-11-11 | 6 | 자체 CRS 개정 후 제출 | 2024-11-10 | N/A | DE-GUP-DT-E-23-557 | 2023-05-16 | 0 | CRS-GUP-DHI-DT-23-1974 | 2023-06-01 | NC | DE-GUP-DT-E-23-633 | 2023-06-20 | 1 | CRS-GUP-DHI-DT-23-2034 | 2023-07-04 | RC | DE-GUP-DT-E-23-929 | 2023-11-22 | 2 | CRS-GUP-DHI-DT-24-005 | 2024-01-23 | RC | DE-GUP-DT-E-24-093 | 2024-03-26 | 3 | 자체 CRS 개정 후 제출 | 2024-05-02 | N/A | DE-GUP-DT-E-24-124 | 2024-05-03 | 4 | CRS-GUP-DHI-DT-24-054 | 2024-06-03 | NC | DE-GUP-DT-E-24-201 | 2024-08-09 | 5 | 자체 CRS 개정 후 제출 | 2024-11-10 | N/A | DE-GUP-DT-E-24-264 | 2024-11-11 | 6
| GUP | CC04 | P1 | UZA | 170342 |  | GUP-CC04-P1UZA-170342 | LIGHTING POLE & CCTV FOUNDATION (CCPP PLANT AREA)_DETAIL | FI | 2023-05-29 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | LIGHTING POLE & CCTV | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-201 | 2024-08-09 | 4 | CRS-GUP-DHI-DT-24-054 | 2024-06-03 | NC | DE-GUP-DT-E-23-557 | 2023-05-16 | 0 | CRS-GUP-DHI-DT-23-1974 | 2023-06-01 | RC | DE-GUP-DT-E-23-633 | 2023-06-20 | 1 | CRS-GUP-DHI-DT-23-2034 | 2023-07-04 | NC | DE-GUP-DT-E-23-929 | 2023-11-22 | 2 | CRS-GUP-DHI-DT-24-005 | 2024-01-23 | NC | DE-GUP-DT-E-24-124 | 2024-05-03 | 3 | CRS-GUP-DHI-DT-24-054 | 2024-06-03 | NC | DE-GUP-DT-E-24-201 | 2024-08-09 | 4
| GUP | UH00 | P1 | SGA | 170350 |  | GUP-UH00-P1SGA-170350 | FIRE FIGHTING CIVIL WORKS (CCPP PLANT AREA)_LAYOUT | FA | 2022-11-22 | 2023-02-20 | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | CCPP | FF Civil | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-140 | 2024-05-27 | 3 | 자체 CRS 개정 후 제출 | 2024-05-26 | N/A | DE-GUP-DT-E-22-764 | 2022-10-07 | A | CRS-GUP-DHI-DT-22-930 | 2022-10-19 | RR | DE-GUP-DT-E-22-946 | 2022-11-16 | B | CRS-GUP-DHI-DT-22-1190 | 2022-11-30 | RC | DE-GUP-DT-E-23-117 | 2023-02-03 | C | CRS-GUP-DHI-DT-23-1552 | 2023-02-19 | AC | DE-GUP-DT-E-23-328 | 2023-03-20 | 0(CP) | CRS-GUP-DHI-DT-23-1801 | 2023-04-04 | AA | DE-GUP-DT-E-23-593 | 2023-05-30 | 1 | CRS-GUP-DHI-DT-23-2006 | 2023-06-15 | AA | DE-GUP-DT-E-23-850 | 2023-10-12 | 2 | 자체 CRS 개정 후 제출 | 2024-05-26 | N/A | DE-GUP-DT-E-24-140 | 2024-05-27 | 3
| GUP | CC02 | P1 | SGA | 170352 |  | GUP-CC02-P1SGA-170352 | FIRE FIGHTING CIVIL WORKS (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2022-11-22 | 2023-02-20 | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | CCPP | FF Civil | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-140 | 2024-05-27 | 3 | 자체 CRS 개정 후 제출 | 2024-05-26 | N/A | DE-GUP-DT-E-22-764 | 2022-10-07 | A | CRS-GUP-DHI-DT-22-930 | 2022-10-19 | RR | DE-GUP-DT-E-22-946 | 2022-11-16 | B | CRS-GUP-DHI-DT-22-1190 | 2022-11-30 | RC | DE-GUP-DT-E-23-117 | 2023-02-03 | C | CRS-GUP-DHI-DT-23-1552 | 2023-02-19 | AC | DE-GUP-DT-E-23-328 | 2023-03-20 | 0(CP) | CRS-GUP-DHI-DT-23-1801 | 2023-04-04 | AA | DE-GUP-DT-E-23-593 | 2023-05-30 | 1 | CRS-GUP-DHI-DT-23-2006 | 2023-06-15 | AA | DE-GUP-DT-E-23-850 | 2023-10-12 | 2 | 자체 CRS 개정 후 제출 | 2024-05-26 | N/A | DE-GUP-DT-E-24-140 | 2024-05-27 | 3
| GUP | CC04 | P1 | SGA | 170354 |  | GUP-CC04-P1SGA-170354 | FIRE FIGHTING CIVIL WORKS (CCPP PLANT AREA)_DETAIL | FI | 2022-11-22 |  | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | CCPP | FF Civil | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-140 | 2024-05-27 | 6 | 자체 CRS 개정 후 제출 | 2024-05-26 | N/A | DE-GUP-DT-E-22-764 | 2022-10-07 | 0 | CRS-GUP-DHI-DT-22-930 | 2022-10-19 | RR | DE-GUP-DT-E-22-946 | 2022-11-16 | 1 | CRS-GUP-DHI-DT-22-1190 | 2022-11-30 | RC | DE-GUP-DT-E-23-117 | 2023-02-03 | 2 | CRS-GUP-DHI-DT-23-1552 | 2023-02-19 | NC | DE-GUP-DT-E-23-328 | 2023-03-20 | 3 | CRS-GUP-DHI-DT-23-1801 | 2023-04-04 | NC | DE-GUP-DT-E-23-593 | 2023-05-30 | 4 | CRS-GUP-DHI-DT-23-2006 | 2023-06-15 | NC | DE-GUP-DT-E-23-850 | 2023-10-12 | 5 | 자체 CRS 개정 후 제출 | 2024-05-26 | N/A | DE-GUP-DT-E-24-140 | 2024-05-27 | 6
| GUP | CC07 | P1 | GUB | 170360 |  | GUP-CC07-P1GUB-170360 | STORM WATER DRAINAGE (CCPP PLANT AREA)_CALCULATION | FA | 2023-05-29 | 2023-08-26 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | STORM Water Drainage | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-669 | 2023-07-05 | 1 | CRS-GUP-DHI-DT-23-2074 | 2023-07-27 | AA | DE-GUP-DT-E-22-839 | 2022-10-21 | A | CRS-GUP-DHI-DT-22-964 | 2022-11-07 | RC | DE-GUP-DT-E-22-1059 | 2022-12-09 | B | CRS-GUP-DHI-DT-22-1328 | 2022-12-28 | AC | DE-GUP-DT-E-23-360 | 2023-03-24 | 0 | CRS-GUP-DHI-DT-23-1815 | 2023-04-12 | AA | DE-GUP-DT-E-23-669 | 2023-07-05 | 1 | CRS-GUP-DHI-DT-23-2074 | 2023-07-27 | AA
| GUP | UH00 | P1 | GUB | 170362 |  | GUP-UH00-P1GUB-170362 | STORM WATER DRAINAGE (CCPP PLANT AREA)_LAYOUT | FA | 2023-05-29 | 2023-08-26 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | STORM Water Drainage | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-271 | 2024-11-14 | 8 | 자체 CRS 개정 후 제출 | 2024-11-13 | N/A | DE-GUP-DT-E-22-839 | 2022-10-21 | A | CRS-GUP-DHI-DT-22-964 | 2022-11-07 | RC | DE-GUP-DT-E-22-1059 | 2022-12-09 | B | CRS-GUP-DHI-DT-22-1328 | 2022-12-28 | AC | DE-GUP-DT-E-23-360 | 2023-03-24 | 0 | CRS-GUP-DHI-DT-23-1815 | 2023-04-12 | AA | DE-GUP-DT-E-23-669 | 2023-07-05 | 1(CP) | CRS-GUP-DHI-DT-23-2074 | 2023-07-27 | AC | DE-GUP-DT-E-23-738 | 2023-08-11 | 2(CP) | CRS-GUP-DHI-DT-23-2095 | 2023-08-16 | AC | DE-GUP-DT-E-23-779 | 2023-08-30 | 3(CP) | CRS-GUP-DHI-DT-23-2109 | 2023-09-13 | AC | DE-GUP-DT-E-23-900 | 2023-11-10 | 4(CP) | CRS-GUP-DHI-DT-24-042 | 2024-03-19 | AA | DE-GUP-DT-E-24-096 | 2024-03-28 | 5 | 자체 CRS 개정 후 제출 | 2024-05-01 | N/A | DE-GUP-DT-E-24-122 | 2024-05-02 | 6 | 자체 CRS 개정 후 제출 | 2024-08-28 | N/A | DE-GUP-DT-E-24-214 | 2024-09-13 | 7 | 자체 CRS 개정 후 제출 | 2024-11-13 | N/A | DE-GUP-DT-E-24-271 | 2024-11-14 | 8
| GUP | CC02 | P1 | GUB | 170364 |  | GUP-CC02-P1GUB-170364 | STORM WATER DRAINAGE (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2023-05-29 | 2023-08-26 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | STORM Water Drainage | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-271 | 2024-11-14 | 8 | 자체 CRS 개정 후 제출 | 2024-11-13 | N/A | DE-GUP-DT-E-22-839 | 2022-10-21 | A | CRS-GUP-DHI-DT-22-964 | 2022-11-07 | RC | DE-GUP-DT-E-22-1059 | 2022-12-09 | B | CRS-GUP-DHI-DT-22-1328 | 2022-12-28 | AC | DE-GUP-DT-E-23-360 | 2023-03-24 | 0 | CRS-GUP-DHI-DT-23-1815 | 2023-04-12 | AA | DE-GUP-DT-E-23-669 | 2023-07-05 | 1(CP) | CRS-GUP-DHI-DT-23-2074 | 2023-07-27 | AA | DE-GUP-DT-E-23-738 | 2023-08-11 | 2(CP) | CRS-GUP-DHI-DT-23-2095 | 2023-08-16 | AA | DE-GUP-DT-E-23-779 | 2023-08-30 | 3(CP) | CRS-GUP-DHI-DT-23-2109 | 2023-09-13 | AA | DE-GUP-DT-E-23-900 | 2023-11-10 | 4(CP) | 자체 CRS 개정 후 제출 | 2024-03-27 | N/A | DE-GUP-DT-E-24-096 | 2024-03-28 | 5 | 자체 CRS 개정 후 제출 | 2024-05-01 | N/A | DE-GUP-DT-E-24-122 | 2024-05-02 | 6 | 자체 CRS 개정 후 제출 | 2024-08-28 | N/A | DE-GUP-DT-E-24-214 | 2024-09-13 | 7 | 자체 CRS 개정 후 제출 | 2024-11-13 | N/A | DE-GUP-DT-E-24-271 | 2024-11-14 | 8
| GUP | CC04 | P1 | GUB | 170366 |  | GUP-CC04-P1GUB-170366 | STORM WATER DRAINAGE (CCPP PLANT AREA)_DETAIL | FI | 2023-05-29 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | STORM Water Drainage | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-214 | 2024-09-13 | 8 | 자체 CRS 개정 후 제출 | 2024-08-28 | N/A | DE-GUP-DT-E-22-839 | 2022-10-21 | 0 | CRS-GUP-DHI-DT-22-964 | 2022-11-07 | RC | DE-GUP-DT-E-22-1059 | 2022-12-09 | 1 | CRS-GUP-DHI-DT-22-1328 | 2022-12-28 | RC | DE-GUP-DT-E-23-360 | 2023-03-24 | 2 | CRS-GUP-DHI-DT-23-1815 | 2023-04-12 | RC | DE-GUP-DT-E-23-669 | 2023-07-05 | 3 | CRS-GUP-DHI-DT-23-2074 | 2023-07-27 | NC | DE-GUP-DT-E-23-738 | 2023-08-11 | 4 | CRS-GUP-DHI-DT-23-2095 | 2023-08-16 | NC | DE-GUP-DT-E-23-779 | 2023-08-30 | 5 | CRS-GUP-DHI-DT-23-2109 | 2023-09-13 | NC | DE-GUP-DT-E-23-900 | 2023-11-10 | 6 | 자체 CRS 개정 후 제출 | 2024-03-27 | N/A | DE-GUP-DT-E-24-096 | 2024-03-28 | 7 | 자체 CRS 개정 후 제출 | 2024-08-28 | N/A | DE-GUP-DT-E-24-214 | 2024-09-13 | 8
| GUP | VH00 | P1 | GUB | 170370 |  | GUP-VH00-P1GUB-170370 | STORM WATER DRAINAGE (CCPP PLANT AREA)_SCHEDULE | FI | 2023-05-29 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | STORM Water Drainage | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-214 | 2024-09-13 | 8 | 자체 CRS 개정 후 제출 | 2024-08-28 | N/A | DE-GUP-DT-E-22-839 | 2022-10-21 | 0 | CRS-GUP-DHI-DT-22-964 | 2022-11-07 | RC | DE-GUP-DT-E-22-1059 | 2022-12-09 | 1 | CRS-GUP-DHI-DT-22-1328 | 2022-12-28 | NC | DE-GUP-DT-E-23-360 | 2023-03-24 | 2 | CRS-GUP-DHI-DT-23-1815 | 2023-04-12 | NC | DE-GUP-DT-E-23-669 | 2023-07-05 | 3 | CRS-GUP-DHI-DT-23-2074 | 2023-07-27 | NC | DE-GUP-DT-E-23-738 | 2023-08-11 | 4 | CRS-GUP-DHI-DT-23-2095 | 2023-08-16 | NC | DE-GUP-DT-E-23-779 | 2023-08-30 | 5 | CRS-GUP-DHI-DT-23-2109 | 2023-09-13 | NC | DE-GUP-DT-E-24-096 | 2024-03-28 | 6 | 자체 CRS 개정 후 제출 | 2024-05-01 | N/A | DE-GUP-DT-E-24-122 | 2024-05-02 | 7 | 자체 CRS 개정 후 제출 | 2024-08-28 | N/A | DE-GUP-DT-E-24-214 | 2024-09-13 | 8
| GUP | CC07 | P1 | GQB | 170372 |  | GUP-CC07-P1GQB-170372 | WASTE WATER DRAINAGE (CCPP PLANT AREA)_CALCULATION | FA | 2023-05-29 | 2023-08-26 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | CHEMICAL Water Drainage | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-894 | 2023-11-09 | 1 | CRS-GUP-DHI-DT-23-1921 | 2023-05-05 | AA | DE-GUP-DT-E-23-101 | 2023-02-01 | A | CRS-GUP-DHI-DT-23-1565 | 2023-02-23 | RC | DE-GUP-DT-E-23-367 | 2023-03-24 | B | CRS-GUP-DHI-DT-23-1817 | 2023-04-12 | AA | DE-GUP-DT-E-23-499 | 2023-04-24 | 0(CP) | CRS-GUP-DHI-DT-23-1921 | 2023-05-05 | AA | DE-GUP-DT-E-23-894 | 2023-11-09 | 1
| GUP | UH00 | P1 | GQB | 170374 |  | GUP-UH00-P1GQB-170374 | WASTE WATER DRAINAGE (CCPP PLANT AREA)_LAYOUT | FA | 2023-05-29 | 2023-08-26 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | CHEMICAL Water Drainage | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-263 | 2024-11-07 | 4 | 자체 CRS 개정 후 제출 | 2024-11-06 | N/A | DE-GUP-DT-E-22-994 | 2022-11-28 | A | CRS-GUP-DHI-DT-22-1262 | 2022-12-16 | RC | DE-GUP-DT-E-23-101 | 2023-02-01 | B | CRS-GUP-DHI-DT-23-1565 | 2023-02-23 | RC | DE-GUP-DT-E-23-367 | 2023-03-24 | C | CRS-GUP-DHI-DT-23-1817 | 2023-04-12 | AC | DE-GUP-DT-E-23-499 | 2023-04-24 | 0(CP) | CRS-GUP-DHI-DT-23-1921 | 2023-05-05 | AA | DE-GUP-DT-E-23-670 | 2023-07-05 | 1(CP) | CRS-GUP-DHI-DT-23-2065 | 2023-07-24 | AA | DE-GUP-DT-E-23-894 | 2023-11-09 | 2 | 자체 CRS 개정 후 제출 | 2024-04-29 | N/A | DE-GUP-DT-E-24-116 | 2024-04-30 | 3 | 자체 CRS 개정 후 제출 | 2024-11-06 | N/A | DE-GUP-DT-E-24-263 | 2024-11-07 | 4
| GUP | CC02 | P1 | GQB | 170376 |  | GUP-CC02-P1GQB-170376 | WASTE WATER DRAINAGE (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2023-05-29 | 2023-08-26 | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | CHEMICAL Water Drainage | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-263 | 2024-11-07 | 4 | 자체 CRS 개정 후 제출 | 2024-11-06 | N/A | DE-GUP-DT-E-22-994 | 2022-11-28 | A | CRS-GUP-DHI-DT-22-1262 | 2022-12-16 | RC | DE-GUP-DT-E-23-101 | 2023-02-01 | B | CRS-GUP-DHI-DT-23-1565 | 2023-02-23 | RC | DE-GUP-DT-E-23-367 | 2023-03-24 | C | CRS-GUP-DHI-DT-23-1817 | 2023-04-12 | AC | DE-GUP-DT-E-23-499 | 2023-04-24 | 0(CP) | CRS-GUP-DHI-DT-23-1921 | 2023-05-05 | AA | DE-GUP-DT-E-23-670 | 2023-07-05 | 1(CP) | CRS-GUP-DHI-DT-23-2065 | 2023-07-24 | AA | DE-GUP-DT-E-23-894 | 2023-11-09 | 2 | 자체 CRS 개정 후 제출 | 2024-04-29 | N/A | DE-GUP-DT-E-24-116 | 2024-04-30 | 3 | 자체 CRS 개정 후 제출 | 2024-11-06 | N/A | DE-GUP-DT-E-24-263 | 2024-11-07 | 4
| GUP | CC04 | P1 | GQB | 170378 |  | GUP-CC04-P1GQB-170378 | WASTE WATER DRAINAGE (CCPP PLANT AREA)_DETAIL | FI | 2023-05-29 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | CHEMICAL Water Drainage | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-116 | 2024-04-30 | 6 | 자체 CRS 개정 후 제출 | 2024-04-29 | N/A | DE-GUP-DT-E-22-994 | 2022-11-28 | 0 | CRS-GUP-DHI-DT-22-1262 | 2022-12-16 | NC | DE-GUP-DT-E-23-101 | 2023-02-01 | 1 | CRS-GUP-DHI-DT-23-1565 | 2023-02-23 | RC | DE-GUP-DT-E-23-367 | 2023-03-24 | 2 | CRS-GUP-DHI-DT-23-1817 | 2023-04-12 | RC | DE-GUP-DT-E-23-499 | 2023-04-24 | 3 | CRS-GUP-DHI-DT-23-1921 | 2023-05-05 | RC | DE-GUP-DT-E-23-670 | 2023-07-05 | 4 | CRS-GUP-DHI-DT-23-2065 | 2023-07-24 | NC | DE-GUP-DT-E-23-894 | 2023-11-09 | 5 | 자체 CRS 개정 후 제출 | 2024-04-29 | N/A | DE-GUP-DT-E-24-116 | 2024-04-30 | 6
| GUP | VH00 | P1 | GQB | 170382 |  | GUP-VH00-P1GQB-170382 | WASTE WATER DRAINAGE (CCPP PLANT AREA)_SCHEDULE | FI | 2023-05-29 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P |  |  |  | CCPP | CHEMICAL Water Drainage | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-263 | 2024-11-07 | 7 | 자체 CRS 개정 후 제출 | 2024-11-06 | N/A | DE-GUP-DT-E-22-994 | 2022-11-28 | 0 | CRS-GUP-DHI-DT-22-1262 | 2022-12-16 | NC | DE-GUP-DT-E-23-101 | 2023-02-01 | 1 | CRS-GUP-DHI-DT-23-1565 | 2023-02-23 | RC | DE-GUP-DT-E-23-367 | 2023-03-24 | 2 | CRS-GUP-DHI-DT-23-1817 | 2023-04-12 | RC | DE-GUP-DT-E-23-499 | 2023-04-24 | 3 | CRS-GUP-DHI-DT-23-1921 | 2023-05-05 | NC | DE-GUP-DT-E-23-670 | 2023-07-05 | 4 | CRS-GUP-DHI-DT-23-2065 | 2023-07-24 | NC | DE-GUP-DT-E-23-894 | 2023-11-09 | 5 | 자체 CRS 개정 후 제출 | 2024-04-29 | N/A | DE-GUP-DT-E-24-116 | 2024-04-30 | 6 | 자체 CRS 개정 후 제출 | 2024-11-06 | N/A | DE-GUP-DT-E-24-263 | 2024-11-07 | 7
| GUP | CC02 | P1 | UZJ | 170412 |  | GUP-CC02-P1UZJ-170412 | FENCE & GATE (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2023-10-24 | 2024-01-22 | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | CCPP | Gate House | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-25-036 | 2025-03-20 | 4 | CRS-GUP-DHI-DT-25-048 | 2025-03-19 | AA | DE-GUP-DT-E-23-326 | 2023-03-17 | A | CRS-GUP-DHI-DT-23-1800 | 2023-04-04 | RC | DE-GUP-DT-E-23-532 | 2023-05-09 | B | CRS-GUP-DHI-DT-23-1950 | 2023-05-17 | RC | DE-GUP-DT-E-23-595 | 2023-05-31 | C | CRS-GUP-DHI-DT-23-2008 | 2023-06-15 | RC | DE-GUP-DT-E-23-627 | 2023-06-16 | D | CRS-GUP-DHI-DT-23-2024 | 2023-06-22 | RC | DE-GUP-DT-E-23-640 | 2023-06-27 | E | CRS-GUP-DHI-DT-23-2030 | 2023-07-04 | RC | DE-GUP-DT-E-23-718 | 2023-07-25 | F | CRS-GUP-DHI-DT-23-2077 | 2023-07-27 | RC | DE-GUP-DT-E-23-737 | 2023-08-11 | G | CRS-GUP-DHI-DT-23-2107 | 2023-09-13 | AC | DE-GUP-DT-E-23-905 | 2023-11-10 | H | CRS-GUP-DHI-DT-23-2142 | 2023-12-01 | AC | DE-GUP-DT-E-23-999 | 2023-12-19 | 0(CP) | CRS-GUP-DHI-DT-24-006 | 2024-01-23 | AC | DE-GUP-DT-E-24-090 | 2024-03-26 | 1(CP) | CRS-GUP-DHI-DT-24-051 | 2024-04-15 | AC | DE-GUP-DT-E-24-175 | 2024-07-03 | 2(CP) | CRS-GUP-DHI-DT-24-067 | 2024-08-16 | AC | DE-GUP-DT-E-24-226 | 2024-09-06 | 3(CP) | CRS-GUP-DHI-DT-25-048 | 2025-03-19 | AA | DE-GUP-DT-E-25-036 | 2025-03-20 | 4
| GUP | CC04 | P1 | UZJ | 170414 |  | GUP-CC04-P1UZJ-170414 | FENCE & GATE (CCPP PLANT AREA)_DETAIL | FI | 2023-10-24 |  | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | CCPP | Gate House | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-175 | 2024-07-03 | 10 | CRS-GUP-DHI-DT-24-067 | 2024-08-16 | NC | DE-GUP-DT-E-23-326 | 2023-03-17 | 0 | CRS-GUP-DHI-DT-23-1800 | 2023-04-04 | RC | DE-GUP-DT-E-23-532 | 2023-05-09 | 1 | CRS-GUP-DHI-DT-23-1950 | 2023-05-17 | RC | DE-GUP-DT-E-23-595 | 2023-05-31 | 2 | CRS-GUP-DHI-DT-23-2008 | 2023-06-15 | RC | DE-GUP-DT-E-23-627 | 2023-06-16 | 3 | CRS-GUP-DHI-DT-23-2024 | 2023-06-22 | RC | DE-GUP-DT-E-23-640 | 2023-06-27 | 4 | CRS-GUP-DHI-DT-23-2030 | 2023-07-04 | RC | DE-GUP-DT-E-23-718 | 2023-07-25 | 5 | CRS-GUP-DHI-DT-23-2077 | 2023-07-27 | RC | DE-GUP-DT-E-23-737 | 2023-08-11 | 6 | CRS-GUP-DHI-DT-23-2107 | 2023-09-13 | RC | DE-GUP-DT-E-23-905 | 2023-11-10 | 7 | CRS-GUP-DHI-DT-23-2142 | 2023-12-01 | RC | DE-GUP-DT-E-23-999 | 2023-12-19 | 8 | CRS-GUP-DHI-DT-24-006 | 2024-01-23 | AC | DE-GUP-DT-E-24-090 | 2024-03-26 | 9 | CRS-GUP-DHI-DT-24-051 | 2024-04-15 | AC | DE-GUP-DT-E-24-175 | 2024-07-03 | 10 | CRS-GUP-DHI-DT-24-067 | 2024-08-16 | NC
| GUP | CC07 | P1 | UZT | 170420 |  | GUP-CC07-P1UZT-170420 | CABLE ROUTE CIVIL WORKS (CCPP PLANT AREA)_CALCULATION | FA | 2022-08-08 | 2022-10-22 | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | CCPP | Cable Route | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-556 | 2023-05-16 | 2 | CRS-GUP-DHI-DT-23-1601 | 2023-02-28 | AA | DHI-GUP-DT-22-022 | 2022-01-17 | A | CRS-GUP-DHI-DT-21-184 | 2022-02-04 | AC | DE-GUP-DT-E-22-369 | 2022-07-07 | B | CRS-GUP-DHI-DT-22-565 | 2022-08-02 | AC | DE-GUP-DT-E-22-591 | 2022-08-31 | 0(CP) | CRS-GUP-DHI-DT-22-863 | 2022-09-26 | AC | DE-GUP-DT-E-23-191 | 2023-02-16 | 1(CP) | CRS-GUP-DHI-DT-23-1601 | 2023-02-28 | AA | DE-GUP-DT-E-23-556 | 2023-05-16 | 2
| GUP | UH00 | P1 | UZT | 170422 |  | GUP-UH00-P1UZT-170422 | CABLE ROUTE CIVIL WORKS (CCPP PLANT AREA)_LAYOUT | FA | 2022-08-08 | 2022-10-22 | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | CCPP | Cable Route | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-848 | 2023-10-12 | 3 | 자체 CRS 개정 후 제출 | 2023-10-11 | N/A | DHI-GUP-DT-22-022 | 2022-01-17 | A | CRS-GUP-DHI-DT-21-184 | 2022-02-04 | AC | DE-GUP-DT-E-22-369 | 2022-07-07 | B | CRS-GUP-DHI-DT-22-565 | 2022-08-02 | AC | DE-GUP-DT-E-22-591 | 2022-08-31 | 0(CP) | CRS-GUP-DHI-DT-22-863 | 2022-09-26 | AC | DE-GUP-DT-E-23-191 | 2023-02-16 | 1(CP) | CRS-GUP-DHI-DT-23-1601 | 2023-02-28 | AA | DE-GUP-DT-E-23-556 | 2023-05-16 | 2 | 자체 CRS 개정 후 제출 | 2023-10-11 | N/A | DE-GUP-DT-E-23-848 | 2023-10-12 | 3
| GUP | CC02 | P1 | UZT | 170424 |  | GUP-CC02-P1UZT-170424 | CABLE ROUTE CIVIL WORKS (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2022-08-08 | 2022-10-22 | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | CCPP | Cable Route | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-848 | 2023-10-12 | 3 | 자체 CRS 개정 후 제출 | 2023-10-11 | N/A | DHI-GUP-DT-22-022 | 2022-01-17 | A | CRS-GUP-DHI-DT-21-184 | 2022-02-04 | AC | DE-GUP-DT-E-22-369 | 2022-07-07 | B | CRS-GUP-DHI-DT-22-565 | 2022-08-02 | AC | DE-GUP-DT-E-22-591 | 2022-08-31 | 0(CP) | CRS-GUP-DHI-DT-22-863 | 2022-09-26 | AC | DE-GUP-DT-E-23-191 | 2023-02-16 | 1(CP) | CRS-GUP-DHI-DT-23-1601 | 2023-02-28 | AA | DE-GUP-DT-E-23-556 | 2023-05-16 | 2 | 자체 CRS 개정 후 제출 | 2023-10-11 | N/A | DE-GUP-DT-E-23-848 | 2023-10-12 | 3
| GUP | CC04 | P1 | UZT | 170426 |  | GUP-CC04-P1UZT-170426 | CABLE ROUTE CIVIL WORKS (CCPP PLANT AREA)_DETAIL | FI | 2022-08-08 |  | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | CCPP | Cable Route | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-848 | 2023-10-12 | 5 | 자체 CRS 개정 후 제출 | 2023-10-11 | N/A | DHI-GUP-DT-22-022 | 2022-01-17 | 0 | CRS-GUP-DHI-DT-21-184 | 2022-02-04 | NC | DE-GUP-DT-E-22-369 | 2022-07-07 | 1 | CRS-GUP-DHI-DT-22-565 | 2022-08-02 | NC | DE-GUP-DT-E-22-591 | 2022-08-31 | 2 | CRS-GUP-DHI-DT-22-795 | 2022-09-19 | NC | DE-GUP-DT-E-23-191 | 2023-02-16 | 3 | CRS-GUP-DHI-DT-23-1601 | 2023-02-28 | NC | DE-GUP-DT-E-23-556 | 2023-05-16 | 4 | 자체 CRS 개정 후 제출 | 2023-10-11 | N/A | DE-GUP-DT-E-23-848 | 2023-10-12 | 5
| GUP | VH00 | P1 | UZT | 170430 |  | GUP-VH00-P1UZT-170430 | CABLE ROUTE CIVIL WORKS (CCPP PLANT AREA)_SCHEDULE | FI | 2022-08-08 |  | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | CCPP | Cable Route | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-848 | 2023-10-12 | 5 | 자체 CRS 개정 후 제출 | 2023-10-11 | N/A | DHI-GUP-DT-22-022 | 2022-01-17 | 0 | CRS-GUP-DHI-DT-21-184 | 2022-02-04 | NC | DE-GUP-DT-E-22-369 | 2022-07-07 | 1 | CRS-GUP-DHI-DT-22-565 | 2022-08-02 | NC | DE-GUP-DT-E-22-591 | 2022-08-31 | 2 | CRS-GUP-DHI-DT-22-795 | 2022-09-19 | NC | DE-GUP-DT-E-23-191 | 2023-02-16 | 3 | CRS-GUP-DHI-DT-23-1601 | 2023-02-28 | NC | DE-GUP-DT-E-23-556 | 2023-05-16 | 4 | 자체 CRS 개정 후 제출 | 2023-10-11 | N/A | DE-GUP-DT-E-23-848 | 2023-10-12 | 5
| GUP | CC07 | P1 | UZT | 170432 |  | GUP-CC07-P1UZT-170432 | PIPE SLEEPER & EARTH WORKS (CCPP PLANT AREA)_CALCULATION | FI | 2022-08-25 |  | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | CCPP | PIPE SLEEPER & EARTH | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-378 | 2023-03-27 | 3 | CRS-GUP-DHI-DT-23-1846 | 2023-04-19 | NC | DE-GUP-DT-E-22-584 | 2022-08-30 | A | CRS-GUP-DHI-DT-22-791 | 2022-09-19 | RC | DE-GUP-DT-E-22-938 | 2022-11-14 | 1 | CRS-GUP-DHI-DT-22-1189 | 2022-11-30 | AC | DE-GUP-DT-E-23-108 | 2023-02-03 | 2 | CRS-GUP-DHI-DT-23-1551 | 2023-02-19 | NC | DE-GUP-DT-E-23-378 | 2023-03-27 | 3 | CRS-GUP-DHI-DT-23-1846 | 2023-04-19 | NC
| GUP | UH00 | P1 | UZT | 170434 |  | GUP-UH00-P1UZT-170434 | PIPE SLEEPER & EARTH WORKS (CCPP PLANT AREA)_LAYOUT | FA | 2022-08-25 | 2022-11-25 | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | CCPP | PIPE SLEEPER & EARTH | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-091 | 2024-03-26 | 4 | 자체 CRS 개정 후 제출 | 2024-03-25 | N/A | DE-GUP-DT-E-22-584 | 2022-08-30 | A | CRS-GUP-DHI-DT-22-791 | 2022-09-19 | RC | DE-GUP-DT-E-22-938 | 2022-11-14 | B | CRS-GUP-DHI-DT-22-1189 | 2022-11-30 | AC | DE-GUP-DT-E-23-108 | 2023-02-03 | 0(CP) | CRS-GUP-DHI-DT-23-1551 | 2023-02-19 | AA | DE-GUP-DT-E-23-378 | 2023-03-27 | 1 | N/A(자체 CRS 개정 후 제출) | 2023-05-29 | N/A | DE-GUP-DT-E-23-588 | 2023-05-30 | 2 | CRS-GUP-DHI-DT-23-1984 | 2023-06-08 | AA | DE-GUP-DT-E-23-848 | 2023-10-12 | 3 | 자체 CRS 개정 후 제출 | 2024-03-25 | N/A | DE-GUP-DT-E-24-091 | 2024-03-26 | 4
| GUP | CC02 | P1 | UZT | 170436 |  | GUP-CC02-P1UZT-170436 | PIPE SLEEPER & EARTH WORKS (CCPP PLANT AREA)_PLAN AND SECTION | FI | 2022-08-25 |  | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | CCPP | PIPE SLEEPER & EARTH | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-091 | 2024-03-26 | 6 | 자체 CRS 개정 후 제출 | 2024-03-25 | N/A | DE-GUP-DT-E-22-584 | 2022-08-30 | A | CRS-GUP-DHI-DT-22-791 | 2022-09-19 | RC | DE-GUP-DT-E-22-938 | 2022-11-14 | 1 | CRS-GUP-DHI-DT-22-1189 | 2022-11-30 | NC | DE-GUP-DT-E-23-108 | 2023-02-03 | 2 | CRS-GUP-DHI-DT-23-1551 | 2023-02-19 | NC | DE-GUP-DT-E-23-378 | 2023-03-27 | 3 | CRS-GUP-DHI-DT-23-1846 | 2023-04-19 | NC | DE-GUP-DT-E-23-588 | 2023-05-30 | 4 | CRS-GUP-DHI-DT-23-1984 | 2023-06-08 | NC | DE-GUP-DT-E-23-848 | 2023-10-12 | 5 | 자체 CRS 개정 후 제출 | 2024-03-25 | N/A | DE-GUP-DT-E-24-091 | 2024-03-26 | 6
| GUP | CC04 | P1 | UZT | 170438 |  | GUP-CC04-P1UZT-170438 | PIPE SLEEPER & EARTH WORKS (CCPP PLANT AREA)_DETAIL | FI | 2022-08-25 |  | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | CCPP | PIPE SLEEPER & EARTH | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-091 | 2024-03-26 | 5 | CRS-GUP-DHI-DT-23-1984 | 2023-06-08 | NC | DE-GUP-DT-E-22-584 | 2022-08-30 | 0 | CRS-GUP-DHI-DT-22-791 | 2022-09-19 | RC | DE-GUP-DT-E-22-938 | 2022-11-14 | 1 | CRS-GUP-DHI-DT-22-1189 | 2022-11-30 | RC | DE-GUP-DT-E-23-108 | 2023-02-03 | 2 | CRS-GUP-DHI-DT-23-1551 | 2023-02-19 | NC | DE-GUP-DT-E-23-378 | 2023-03-27 | 3 | CRS-GUP-DHI-DT-23-1846 | 2023-04-19 | NC | DE-GUP-DT-E-23-588 | 2023-05-30 | 4 | CRS-GUP-DHI-DT-23-1984 | 2023-06-08 | NC | DE-GUP-DT-E-24-091 | 2024-03-26 | 5
| GUP | VH00 | P1 | UZT | 170442 |  | GUP-VH00-P1UZT-170442 | PIPE SLEEPER & EARTH WORKS (CCPP PLANT AREA)_SCHEDULE | FI | 2022-08-25 |  | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | CCPP | PIPE SLEEPER & EARTH | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-848 | 2023-10-12 | 5 | CRS-GUP-DHI-DT-23-1984 | 2023-06-08 | NC | DE-GUP-DT-E-22-584 | 2022-08-30 | 0 | CRS-GUP-DHI-DT-22-791 | 2022-09-19 | RC | DE-GUP-DT-E-22-938 | 2022-11-14 | 1 | CRS-GUP-DHI-DT-22-1189 | 2022-11-30 | NC | DE-GUP-DT-E-23-108 | 2023-02-03 | 2 | CRS-GUP-DHI-DT-23-1551 | 2023-02-19 | NC | DE-GUP-DT-E-23-378 | 2023-03-27 | 3 | CRS-GUP-DHI-DT-23-1846 | 2023-04-19 | NC | DE-GUP-DT-E-23-588 | 2023-05-30 | 4 | CRS-GUP-DHI-DT-23-1984 | 2023-06-08 | NC | DE-GUP-DT-E-23-848 | 2023-10-12 | 5
| GUP | CC07 | P1 | UZA | 170488 |  | GUP-CC07-P1UZA-170488 | ACCESS ROAD (OUTSIDE OF CCPP PLANT AREA)_CALCULATION | FA | 2023-05-29 | 2023-08-26 | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | CCPP | Access Road | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-979 | 2023-12-08 | 1 | CRS-GUP-DHI-DT-23-1939 | 2023-05-11 | AA | DE-GUP-DT-E-22-928 | 2022-11-09 | A | CRS-GUP-DHI-DT-22-1222 | 2022-12-05 | RC | DE-GUP-DT-E-23-085 | 2023-01-27 | B | CRS-GUP-DHI-DT-23-1646 | 2023-03-07 | AA | DE-GUP-DT-E-23-476 | 2023-04-18 | 0(CP) | CRS-GUP-DHI-DT-23-1939 | 2023-05-11 | AA | DE-GUP-DT-E-23-979 | 2023-12-08 | 1
| GUP | CC02 | P1 | UZA | 170492 |  | GUP-CC02-P1UZA-170492 | ACCESS ROAD (OUTSIDE OF CCPP PLANT AREA)_PLAN AND SECTION | FA | 2023-05-29 | 2023-08-26 | 인프라토목기술팀(Civil.) | 이정수 | B |  | G | FI |  | CCPP | Access Road | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-072 | 2024-03-11 | 1 | 자체 CRS 개정 후 제출 | 2024-03-10 | N/A | DE-GUP-DT-E-22-928 | 2022-11-09 | A | CRS-GUP-DHI-DT-22-1185 | 2022-11-30 | RC | DE-GUP-DT-E-23-085 | 2023-01-27 | B | CRS-GUP-DHI-DT-23-1646 | 2023-03-07 | RC | DE-GUP-DT-E-23-476 | 2023-04-18 | C | CRS-GUP-DHI-DT-23-1939 | 2023-05-11 | RC | DE-GUP-DT-E-23-845 | 2023-10-11 | D | CRS-GUP-DHI-DT-23-2141 | 2023-11-28 | AA | DE-GUP-DT-E-23-979 | 2023-12-08 | 0 | 자체 CRS 개정 후 제출 | 2024-03-10 | N/A | DE-GUP-DT-E-24-072 | 2024-03-11 | 1
| GUP | CC04 | P1 | UZA | 170494 |  | GUP-CC04-P1UZA-170494 | ACCESS ROAD (OUTSIDE OF CCPP PLANT AREA)_DETAIL | FI | 2023-05-29 |  | 인프라토목기술팀(Civil.) | 이정수 | B |  | G | FI |  | CCPP | Access Road | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-072 | 2024-03-11 | 5 | 자체 CRS 개정 후 제출 | 2024-03-10 | N/A | DE-GUP-DT-E-22-928 | 2022-11-09 | 0 | CRS-GUP-DHI-DT-22-1185 | 2022-11-30 | RC | DE-GUP-DT-E-23-085 | 2023-01-27 | 1 | CRS-GUP-DHI-DT-23-1646 | 2023-03-07 | RC | DE-GUP-DT-E-23-476 | 2023-04-18 | 2 | CRS-GUP-DHI-DT-23-1939 | 2023-05-11 | NC | DE-GUP-DT-E-23-845 | 2023-10-11 | 3 | CRS-GUP-DHI-DT-23-2141 | 2023-11-28 | NC | DE-GUP-DT-E-23-979 | 2023-12-08 | 4 | 자체 CRS 개정 후 제출 | 2024-03-10 | N/A | DE-GUP-DT-E-24-072 | 2024-03-11 | 5
| GUP | CC07 | P6 | UAH | 170498 |  | GUP-CC07-P6UAH-170498 | HARMON SUBSTATION SWITCHYARD EQUIPMENT FOUNDATION_CALCULATION | FA | 2022-08-30 | 2022-11-30 | 인프라토목기술팀(Civil.) | 이정수 | B | P | G | FA |  | Harmon S/S | Harmon S/S | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-028 | 2024-01-30 | 4 | 별도 메일접수 24-011 | 2024-11-22 | AA | DHI-GUP-DT-22-101 | 2022-03-08 | A | CRS-GUP-DHI-DT-22-260 | 2022-03-17 | RC | DHI-GUP-DT-22-176 | 2022-04-15 | B | CRS-GUP-DHI-DT-22-333 | 2022-05-16 | RC | DE-GUP-DT-E-22-668 | 2022-09-16 | C | CRS-GUP-DHI-DT-22-884 | 2022-10-10 | RC | DE-GUP-DT-E-22-872 | 2022-10-28 | D | CRS-GUP-DHI-DT-22-1059 | 2022-11-16 | AC | DE-GUP-DT-E-23-016 | 2023-01-12 | 0(CP) | CRS-GUP-DHI-DT-23-1523 | 2023-02-14 | AA | DE-GUP-DT-E-23-450 | 2023-04-13 | 1 | CRS-GUP-DHI-DT-23-1874 | 2023-04-25 | RC | DE-GUP-DT-E-23-516 | 2023-04-28 | 2 | CRS-GUP-DHI-DT-23-1948 | 2023-05-17 | RC | DE-GUP-DT-E-23-578 | 2023-05-24 | 3 | CRS-GUP-DHI-DT-23-2113 | 2023-09-27 | RC | DE-GUP-DT-E-24-028 | 2024-01-30 | 4 | 별도 메일접수 24-011 | 2024-11-22 | AA
| GUP | CC02 | P6 | UAH | 170500 |  | GUP-CC02-P6UAH-170500 | HARMON SUBSTATION SWITCHYARD EQUIPMENT FOUNDATION_PLAN AND SECTION | FA | 2022-08-30 | 2022-11-30 | 인프라토목기술팀(Civil.) | 이정수 | B | P | G | FA |  | Harmon S/S | Harmon S/S | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-028 | 2024-01-30 | 4 | 별도 메일접수 24-011 | 2024-11-22 | AA | DHI-GUP-DT-22-101 | 2022-03-08 | A | CRS-GUP-DHI-DT-22-260 | 2022-03-17 | RC | DHI-GUP-DT-22-176 | 2022-04-15 | B | CRS-GUP-DHI-DT-22-333 | 2022-05-16 | RC | DE-GUP-DT-E-22-668 | 2022-09-16 | C | CRS-GUP-DHI-DT-22-884 | 2022-10-10 | RC | DE-GUP-DT-E-22-872 | 2022-10-28 | D | CRS-GUP-DHI-DT-22-1059 | 2022-11-16 | AC | DE-GUP-DT-E-23-016 | 2023-01-12 | 0(CP) | CRS-GUP-DHI-DT-23-1523 | 2023-02-14 | AA | DE-GUP-DT-E-23-450 | 2023-04-13 | 1 | CRS-GUP-DHI-DT-23-1874 | 2023-04-25 | RC | DE-GUP-DT-E-23-516 | 2023-04-28 | 2 | CRS-GUP-DHI-DT-23-1948 | 2023-05-17 | RC | DE-GUP-DT-E-23-578 | 2023-05-24 | 3 | CRS-GUP-DHI-DT-23-2113 | 2023-09-27 | RC | DE-GUP-DT-E-24-028 | 2024-01-30 | 4 | 별도 메일접수 24-011 | 2024-11-22 | AA
| GUP | CC03 | P6 | UAH | 170504 |  | GUP-CC03-P6UAH-170504 | HARMON SUBSTATION SWITCHYARD EQUIPMENT FOUNDATION_REBAR DETAIL | FI | 2022-08-30 |  | 인프라토목기술팀(Civil.) | 이정수 | B | P | G | FA |  | Harmon S/S | Harmon S/S | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-028 | 2024-01-30 | 8 | CRS-GUP-DHI-DT-23-2113 | 2023-09-27 | NC | DHI-GUP-DT-22-101 | 2022-03-08 | 0 | CRS-GUP-DHI-DT-22-260 | 2022-03-17 | RC | DHI-GUP-DT-22-176 | 2022-04-15 | 1 | CRS-GUP-DHI-DT-22-333 | 2022-05-16 | RC | DE-GUP-DT-E-22-668 | 2022-09-16 | 2 | CRS-GUP-DHI-DT-22-884 | 2022-10-10 | RC | DE-GUP-DT-E-22-872 | 2022-10-28 | 3 | CRS-GUP-DHI-DT-22-1059 | 2022-11-16 | RC | DE-GUP-DT-E-23-016 | 2023-01-12 | 4 | CRS-GUP-DHI-DT-23-1523 | 2023-02-14 | NC | DE-GUP-DT-E-23-450 | 2023-04-13 | 5 | CRS-GUP-DHI-DT-23-1874 | ;2023-04-25 | NC | DE-GUP-DT-E-23-516 | 2023-04-28 | 6 | CRS-GUP-DHI-DT-23-1948 | 2023-05-17 | RC | DE-GUP-DT-E-23-578 | 2023-05-24 | 7 | CRS-GUP-DHI-DT-23-2113 | 2023-09-27 | NC | DE-GUP-DT-E-24-028 | 2024-01-30 | 8
| GUP | CC07 | P1 | GHC | 170510 |  | GUP-CC07-P1GHC-170510 | YARD PUMP FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2023-02-07 | 2023-04-08 | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | Harmon S/S | Yard pump | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-672 | 2023-07-05 | 2 | CRS-GUP-DHI-DT-23-1898 | 2023-05-05 | AA | DE-GUP-DT-E-22-1168 | 2022-12-23 | A | CRS-GUP-DHI-DT-22-1399 | 2023-01-06 | AC | DE-GUP-DT-E-23-098 | 2023-01-31 | 0(CP) | CRS-GUP-DHI-DT-23-1549 | 2023-02-20 | AA | DE-GUP-DT-E-23-214 | 2023-02-21 | 1(CP) | CRS-GUP-DHI-DT-23-1898 | 2023-05-05 | AA | DE-GUP-DT-E-23-672 | 2023-07-05 | 2
| GUP | CC02 | P1 | GHC | 170512 |  | GUP-CC02-P1GHC-170512 | YARD PUMP FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FI | 2023-02-07 |  | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | Harmon S/S | Yard pump | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-535 | 2023-05-09 | 3 | CRS-GUP-DHI-DT-23-1952 | 2023-05-17 | NC | DE-GUP-DT-E-22-1168 | 2022-12-23 | 0 | CRS-GUP-DHI-DT-22-1399 | 2023-01-06 | RC | DE-GUP-DT-E-23-098 | 2023-01-31 | 1 | CRS-GUP-DHI-DT-23-1549 | 2023-02-20 | AA | DE-GUP-DT-E-23-214 | 2023-02-21 | 2 | CRS-GUP-DHI-DT-23-1898 | 2023-05-05 | NC | DE-GUP-DT-E-23-535 | 2023-05-09 | 3 | CRS-GUP-DHI-DT-23-1952 | 2023-05-17 | NC
| GUP | CC07 | P1 | GHC | 170520 |  | GUP-CC07-P1GHC-170520 | YARD SUPPORT FOUNDATION (CCPP PLANT AREA)_CALCULATION | FA | 2023-02-07 | 2023-04-08 | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | Harmon S/S | Yard pump | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-592 | 2023-05-30 | 1 | CRS-GUP-DHI-DT-23-1997 | 2023-06-13 | AA | DE-GUP-DT-E-23-168 | 2023-02-13 | A | CRS-GUP-DHI-DT-23-1583 | 2023-02-25 | AC | DE-GUP-DT-E-23-277 | 2023-03-08 | 0(CP) | CRS-GUP-DHI-DT-23-1758 | 2023-03-22 | AA | DE-GUP-DT-E-23-592 | 2023-05-30 | 1 | CRS-GUP-DHI-DT-23-1997 | 2023-06-13 | AA
| GUP | CC02 | P1 | GHC | 170522 |  | GUP-CC02-P1GHC-170522 | YARD SUPPORT FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FI | 2023-02-07 |  | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | Harmon S/S | Yard pump | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-262 | 2024-11-07 | 6 | CRS-GUP-DHI-DT-24-007 | 2024-01-24 | NC | DE-GUP-DT-E-23-168 | 2023-02-13 | 0 | CRS-GUP-DHI-DT-23-1583 | 2023-02-25 | RC | DE-GUP-DT-E-23-277 | 2023-03-08 | 1 | CRS-GUP-DHI-DT-23-1758 | 2023-03-22 | NC | DE-GUP-DT-E-23-592 | 2023-05-30 | 2 | CRS-GUP-DHI-DT-23-1997 | 2023-06-13 | NC | DE-GUP-DT-E-23-698 | 2023-07-19 | 3 | CRS-GUP-DHI-DT-23-2079 | 2023-07-27 | NC | DE-GUP-DT-E-23-915 | 2023-11-17 | 4 | 자체 CRS 개정 후 제출 | 2024-01-22 | N/A | DE-GUP-DT-E-24-021 | 2024-01-23 | 5 | CRS-GUP-DHI-DT-24-007 | 2024-01-24 | NC | DE-GUP-DT-E-24-262 | 2024-11-07 | 6
| GUP | CC04 | P1 | GHC | 170524 |  | GUP-CC04-P1GHC-170524 | YARD SUPPORT FOUNDATION (CCPP PLANT AREA)_DETAIL | FI | 2023-02-07 |  | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | Harmon S/S | Yard pump | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-262 | 2024-11-07 | 6 | CRS-GUP-DHI-DT-24-007 | 2024-01-24 | NC | DE-GUP-DT-E-23-168 | 2023-02-13 | 0 | CRS-GUP-DHI-DT-23-1583 | 2023-02-25 | RC | DE-GUP-DT-E-23-277 | 2023-03-08 | 1 | CRS-GUP-DHI-DT-23-1758 | 2023-03-22 | RC | DE-GUP-DT-E-23-592 | 2023-05-30 | 2 | CRS-GUP-DHI-DT-23-1997 | 2023-06-13 | RC | DE-GUP-DT-E-23-698 | 2023-07-19 | 3 | CRS-GUP-DHI-DT-23-2079 | 2023-07-27 | RC | DE-GUP-DT-E-23-916 | 2023-11-17 | 4 | 자체 CRS 개정 후 제출 | 2024-01-22 | N/A | DE-GUP-DT-E-24-021 | 2024-01-23 | 5 | CRS-GUP-DHI-DT-24-007 | 2024-01-24 | NC | DE-GUP-DT-E-24-262 | 2024-11-07 | 6
| GUP | CC07 | P1 | UEM | 170526 |  | GUP-CC07-P1UEM-170526 | DRAIN OILY BUFFER TANK FOUNDATION (CCPP PLANT AREA)_CALCULATION | FI | 2024-09-30 |  | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | CCPP | DRAIN OILY BUFFER TANK | Civil. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-265 | 2024-11-11 | 1 | 별도 메일접수 25-003 | 2025-03-13 | NC | DE-GUP-DT-E-24-236 | 2024-09-23 | 0 | 별도 메일접수 24-008 | 2024-11-05 | NC | DE-GUP-DT-E-24-265 | 2024-11-11 | 1 | 별도 메일접수 25-003 | 2025-03-13 | NC
| GUP | CC02 | P1 | UEM | 170528 |  | GUP-CC02-P1UEM-170528 | DRAIN OILY BUFFER TANK FOUNDATION (CCPP PLANT AREA)_PLAN AND SECTION | FA | 2024-09-30 | 2025-02-05 | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | CCPP | DRAIN OILY BUFFER TANK | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-25-034 | 2025-03-19 | 0 | 별도 메일접수 25-003 | 2025-03-13 | AA | DE-GUP-DT-E-24-228 | 2024-09-13 | A | 별도 메일접수 24-008 | 2024-11-05 | RC | DE-GUP-DT-E-24-265 | 2024-11-11 | B | 별도 메일접수 25-003 | 2025-03-13 | AA | DE-GUP-DT-E-25-034 | 2025-03-19 | 0
| GUP | CC04 | P1 | UEM | 170530 |  | GUP-CC04-P1UEM-170530 | DRAIN OILY BUFFER TANK FOUNDATION (CCPP PLANT AREA)_DETAIL | FI | 2024-09-30 |  | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | CCPP | DRAIN OILY BUFFER TANK | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-25-034 | 2025-03-19 | 2 | 별도 메일접수 25-003 | 2025-03-13 | NC | DE-GUP-DT-E-24-228 | 2024-09-13 | 0 | 별도 메일접수 24-008 | 2024-11-05 | NC | DE-GUP-DT-E-24-265 | 2024-11-11 | 1 | 별도 메일접수 25-003 | 2025-03-13 | NC | DE-GUP-DT-E-25-034 | 2025-03-19 | 2
| GUP | CC03 | P1 | UEM | 170532 |  | GUP-CC03-P1UEM-170532 | DRAIN OILY BUFFER TANK FOUNDATION (CCPP PLANT AREA)_REBAR DETAIL | FI | 2024-09-30 |  | 인프라토목기술팀(Civil.) | 이정수 | B |  |  |  |  | CCPP | DRAIN OILY BUFFER TANK | Civil. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-25-034 | 2025-03-19 | 2 | 별도 메일접수 25-003 | 2025-03-13 | NC | DE-GUP-DT-E-24-228 | 2024-09-13 | 0 | 별도 메일접수 24-008 | 2024-11-05 | RC | DE-GUP-DT-E-24-265 | 2024-11-11 | 1 | 별도 메일접수 25-003 | 2025-03-13 | NC | DE-GUP-DT-E-25-034 | 2025-03-19 | 2
| GUP | VD00 | P0 | ZEN | 180001 |  | GUP-VD00-P0ZEN-180001 | EXTERIOR & INTERIOR COLOR SCHEME | FA | 2022-07-04 | 2022-12-30 | 건축기술2팀(Arch.) | 구남영 |  |  | G | FA |  | CCPP | Plant | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-240 | 2024-09-30 | 2 | 자체 CRS 개정 후 제출 | 2024-09-29 | N/A | DE-GUP-DT-E-22-360 | 2022-07-04 | A | CRS-GUP-DHI-DT-22-558 | 2022-08-01 | RC | DE-GUP-DT-E-22-521 | 2022-08-19 | B | CRS-GUP-DHI-DT-22-838 | 2022-09-24 | RC | DE-GUP-DT-E-22-1145 | 2022-12-22 | C | CRS-GUP-DHI-DT-22-1396 | 2023-01-06 | AA | DE-GUP-DT-E-23-092 | 2023-01-30 | 0 | 자체 CRS 개정 후 제출 | 2024-07-23 | N/A | DE-GUP-DT-E-24-190 | 2024-07-24 | 1 | 자체 CRS 개정 후 제출 | 2024-09-29 | N/A | DE-GUP-DT-E-24-240 | 2024-09-30 | 2 | [51 empty] | DE-GUP-DT-E-22-250 | 2022-05-26 | 0
| GUP | VD00 | P0 | ZEN | 180002 |  | GUP-VD00-P0ZEN-180002 | CCR INTERIOR COLOR SCHEME | FA | 2023-01-17 | 2023-04-17 | 건축기술2팀(Arch.) | 구남영 | [5 empty] | CCPP | Plant | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-573 | 2023-05-22 | 1 | CRS-GUP-DHI-DT-23-1778 | 2023-03-27 | AA | DE-GUP-DT-E-22-1131 | 2022-12-21 | A | CRS-GUP-DHI-DT-23-1480 | 2023-02-11 | AC | DE-GUP-DT-E-23-295 | 2023-03-10 | 0(CP) | CRS-GUP-DHI-DT-23-1778 | 2023-03-27 | AA | DE-GUP-DT-E-23-573 | 2023-05-22 | 1 | [69 empty] | DE-GUP-DT-E-22-250 | 2022-05-26 | 0
| GUP | CA06 | P1 | UMX | 181101 |  | GUP-CA06-P1UMX-181101 | GAS TURBINE BUILDING_CALCULATION SHEET | FA | 2021-12-31 | 2022-05-30 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GT Building | Arch. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-668 | 2023-07-04 | 2 | CRS-GUP-DHI-DT-22-1450 | 2023-02-03 | AA | DHI-GUP-DT-21-081 | 2021-10-29 | A | CRS-GUP-DHI-DT-21-063 | 2021-11-16 | RC | DHI-GUP-DT-21-196 | 2021-12-23 | B | CRS-GUP-DHI-DT-21-152 | 2022-01-12 | RC | DHI-GUP-DT-22-054 | 2022-01-28 | C | CRS-GUP-DHI-DT-22-213 | 2022-02-20 | RC | DHI-GUP-DT-22-127 | 2022-03-22 | D | CRS-GUP-DHI-DT-22-288 | 2022-04-07 | RC | DHI-GUP-DT-22-181 | 2022-04-19 | E | CRS-GUP-DHI-DT-22-308 | 2022-04-24 | AC | DHI-GUP-DT-22-202 | 2022-05-04 | F | CRS-GUP-DHI-DT-22-351 | 2022-05-18 | AC | DE-GUP-DT-E-22-250 | 2022-05-26 | 0 | CRS-GUP-DHI-DT-22-419 | 2022-06-13 | AC | DE-GUP-DT-E-22-1230 | 2023-01-06 | 1(CP) | CRS-GUP-DHI-DT-22-1450 | 2023-02-03 | AA | DE-GUP-DT-E-23-668 | 2023-07-04 | 2 | [33 empty] | DE-GUP-DT-E-22-250 | 2022-05-26 | 0
| GUP | CA01 | P1 | UMX | 181131 |  | GUP-CA01-P1UMX-181131 | GAS TURBINE BUILDING_FOUNDATION ARRANGEMENT PLAN | FA | 2022-12-31 | 2022-05-30 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GT Building | Arch. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-668 | 2023-07-04 | 2 | CRS-GUP-DHI-DT-22-1450 | 2023-02-03 | AA | DHI-GUP-DT-21-081 | 2021-10-29 | A | CRS-GUP-DHI-DT-21-063 | 2021-11-16 | RC | DHI-GUP-DT-21-196 | 2021-12-23 | B | CRS-GUP-DHI-DT-21-152 | 2022-01-12 | RC | DHI-GUP-DT-22-054 | 2022-01-28 | C | CRS-GUP-DHI-DT-22-213 | 2022-02-20 | RC | DHI-GUP-DT-22-127 | 2022-03-22 | D | CRS-GUP-DHI-DT-22-288 | 2022-04-07 | RC | DHI-GUP-DT-22-181 | 2022-04-19 | E | CRS-GUP-DHI-DT-22-308 | 2022-04-24 | AC | DHI-GUP-DT-22-202 | 2022-05-04 | F | CRS-GUP-DHI-DT-22-351 | 2022-05-18 | AC | DE-GUP-DT-E-22-250 | 2022-05-26 | 0 | CRS-GUP-DHI-DT-22-419 | 2022-06-13 | AC | DE-GUP-DT-E-22-1230 | 2023-01-06 | 1(CP) | CRS-GUP-DHI-DT-22-1450 | 2023-02-03 | AA | DE-GUP-DT-E-23-668 | 2023-07-04 | 2 | [33 empty] | DE-GUP-DT-E-22-250 | 2022-05-26 | 0
| GUP | CA01 | P1 | UMX | 181132 |  | GUP-CA01-P1UMX-181132 | GAS TURBINE BUILDING_FOUNDATION LONGITUDINAL SECTION | FA | 2022-12-31 | 2022-05-30 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GT Building | Arch. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-668 | 2023-07-04 | 2 | CRS-GUP-DHI-DT-22-1450 | 2023-02-03 | AA | DHI-GUP-DT-21-081 | 2021-10-29 | A | CRS-GUP-DHI-DT-21-063 | 2021-11-16 | RC | DHI-GUP-DT-21-196 | 2021-12-23 | B | CRS-GUP-DHI-DT-21-152 | 2022-01-12 | RC | DHI-GUP-DT-22-054 | 2022-01-28 | C | CRS-GUP-DHI-DT-22-213 | 2022-02-20 | RC | DHI-GUP-DT-22-127 | 2022-03-22 | D | CRS-GUP-DHI-DT-22-288 | 2022-04-07 | RC | DHI-GUP-DT-22-181 | 2022-04-19 | E | CRS-GUP-DHI-DT-22-308 | 2022-04-24 | AC | DHI-GUP-DT-22-202 | 2022-05-04 | F | CRS-GUP-DHI-DT-22-351 | 2022-05-18 | AC | DE-GUP-DT-E-22-250 | 2022-05-26 | 0 | CRS-GUP-DHI-DT-22-419 | 2022-06-13 | AC | DE-GUP-DT-E-22-1230 | 2023-01-06 | 1(CP) | CRS-GUP-DHI-DT-22-1450 | 2023-02-03 | AA | DE-GUP-DT-E-23-668 | 2023-07-04 | 2 | [33 empty] | DE-GUP-DT-E-22-250 | 2022-05-26 | 0
| GUP | CA02 | P1 | UMX | 181133 |  | GUP-CA02-P1UMX-181133 | GAS TURBINE BUILDING_FOUNDATION RE-BAR DETAIL | FI | 2022-12-31 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GT Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-668 | 2023-07-04 | 9 | CRS-GUP-DHI-DT-22-1450 | 2023-02-03 | AA | DHI-GUP-DT-21-081 | 2021-10-29 | 0 | CRS-GUP-DHI-DT-21-063 | 2021-11-16 | NC | DHI-GUP-DT-21-196 | 2021-12-23 | 1 | CRS-GUP-DHI-DT-21-152 | 2022-01-12 | RC | DHI-GUP-DT-22-054 | 2022-01-28 | 2 | CRS-GUP-DHI-DT-22-213 | 2022-02-20 | RC | DHI-GUP-DT-22-127 | 2022-03-22 | 3 | CRS-GUP-DHI-DT-22-288 | 2022-04-07 | RC | DHI-GUP-DT-22-181 | 2022-04-19 | 4 | CRS-GUP-DHI-DT-22-308 | 2022-04-24 | NC | DHI-GUP-DT-22-202 | 2022-05-04 | 5 | CRS-GUP-DHI-DT-22-351 | 2022-05-18 | RC | DE-GUP-DT-E-22-250 | 2022-05-26 | 6 | CRS-GUP-DHI-DT-22-419 | 2022-06-13 | RC | DE-GUP-DT-E-22-676 | 2022-09-16 | 7 | CRS-GUP-DHI-DT-22-886 | 2022-10-10 | NC | DE-GUP-DT-E-22-1230 | 2023-01-06 | 8 | CRS-GUP-DHI-DT-22-1450 | 2023-02-03 | AA | DE-GUP-DT-E-23-668 | 2023-07-04 | 9 | [27 empty] | DE-GUP-DT-E-22-250 | 2022-05-26 | 6
| GUP | CA00 | P1 | UMX | 181111 |  | GUP-CA00-P1UMX-181111 | GAS TURBINE BUILDING_DOOR & WINDOW SCHEDULE | FA | 2022-12-31 | 2022-05-30 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GT Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-668 | 2023-07-04 | 2 | CRS-GUP-DHI-DT-22-1450 | 2023-02-03 | AA | DHI-GUP-DT-21-196 | 2021-12-23 | A | CRS-GUP-DHI-DT-21-152 | 2022-01-12 | AC | DHI-GUP-DT-22-054 | 2022-01-28 | B | CRS-GUP-DHI-DT-22-213 | 2022-02-20 | AC | DHI-GUP-DT-22-127 | 2022-03-22 | C | CRS-GUP-DHI-DT-22-288 | 2022-04-07 | AC | DHI-GUP-DT-22-181 | 2022-04-19 | D | CRS-GUP-DHI-DT-22-308 | 2022-04-24 | AC | DHI-GUP-DT-22-202 | 2022-05-04 | E | CRS-GUP-DHI-DT-22-351 | 2022-05-18 | AC | DE-GUP-DT-E-22-250 | 2022-05-26 | 0 | CRS-GUP-DHI-DT-22-419 | 2022-06-13 | AC | DE-GUP-DT-E-22-1230 | 2023-01-06 | 1(CP) | CRS-GUP-DHI-DT-22-1450 | 2023-02-03 | AA | DE-GUP-DT-E-23-668 | 2023-07-04 | 2
| GUP | CA00 | P1 | UMX | 181112 |  | GUP-CA00-P1UMX-181112 | GAS TURBINE BUILDING_GROUND FLOOR PLAN | FA | 2022-12-31 | 2022-05-30 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GT Building | Arch. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-668 | 2023-07-04 | 2 | CRS-GUP-DHI-DT-22-1450 | 2023-02-03 | AA | DHI-GUP-DT-21-081 | 2021-10-29 | A | CRS-GUP-DHI-DT-21-063 | 2021-11-16 | RC | DHI-GUP-DT-21-196 | 2021-12-23 | B | CRS-GUP-DHI-DT-21-152 | 2022-01-12 | AC | DHI-GUP-DT-22-054 | 2022-01-28 | C | CRS-GUP-DHI-DT-22-213 | 2022-02-20 | AC | DHI-GUP-DT-22-127 | 2022-03-22 | D | CRS-GUP-DHI-DT-22-288 | 2022-04-07 | AC | DHI-GUP-DT-22-181 | 2022-04-19 | E | CRS-GUP-DHI-DT-22-308 | 2022-04-24 | AC | DHI-GUP-DT-22-202 | 2022-05-04 | F | CRS-GUP-DHI-DT-22-351 | 2022-05-18 | AC | DE-GUP-DT-E-22-250 | 2022-05-26 | 0 | CRS-GUP-DHI-DT-22-419 | 2022-06-13 | AC | DE-GUP-DT-E-22-1230 | 2023-01-06 | 1(CP) | CRS-GUP-DHI-DT-22-1450 | 2023-02-03 | AA | DE-GUP-DT-E-23-668 | 2023-07-04 | 2 | [33 empty] | DE-GUP-DT-E-22-250 | 2022-05-26 | 0
| GUP | CA00 | P1 | UMX | 181113 |  | GUP-CA00-P1UMX-181113 | GAS TURBINE BUILDING_ROOF PLAN | FA | 2022-12-31 | 2022-05-30 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GT Building | Arch. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-668 | 2023-07-04 | 2 | CRS-GUP-DHI-DT-22-1450 | 2023-02-03 | AA | DHI-GUP-DT-21-081 | 2021-10-29 | A | CRS-GUP-DHI-DT-21-063 | 2021-11-16 | RC | DHI-GUP-DT-21-196 | 2021-12-23 | B | CRS-GUP-DHI-DT-21-152 | 2022-01-12 | AC | DHI-GUP-DT-22-054 | 2022-01-28 | C | CRS-GUP-DHI-DT-22-213 | 2022-02-20 | AC | DHI-GUP-DT-22-127 | 2022-03-22 | D | CRS-GUP-DHI-DT-22-288 | 2022-04-07 | AC | DHI-GUP-DT-22-181 | 2022-04-19 | E | CRS-GUP-DHI-DT-22-308 | 2022-04-24 | AC | DHI-GUP-DT-22-202 | 2022-05-04 | F | CRS-GUP-DHI-DT-22-351 | 2022-05-18 | AC | DE-GUP-DT-E-22-250 | 2022-05-26 | 0 | CRS-GUP-DHI-DT-22-419 | 2022-06-13 | AC | DE-GUP-DT-E-22-1230 | 2023-01-06 | 1(CP) | CRS-GUP-DHI-DT-22-1450 | 2023-02-03 | AA | DE-GUP-DT-E-23-668 | 2023-07-04 | 2 | [33 empty] | DE-GUP-DT-E-22-250 | 2022-05-26 | 0
| GUP | CA00 | P1 | UMX | 181114 |  | GUP-CA00-P1UMX-181114 | GAS TURBINE BUILDING_MAIN SECTION | FA | 2022-12-31 | 2022-05-30 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GT Building | Arch. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-668 | 2023-07-04 | 2 | CRS-GUP-DHI-DT-22-1450 | 2023-02-03 | AA | DHI-GUP-DT-21-081 | 2021-10-29 | A | CRS-GUP-DHI-DT-21-063 | 2021-11-16 | RC | DHI-GUP-DT-21-196 | 2021-12-23 | B | CRS-GUP-DHI-DT-21-152 | 2022-01-12 | AC | DHI-GUP-DT-22-054 | 2022-01-28 | C | CRS-GUP-DHI-DT-22-213 | 2022-02-20 | AC | DHI-GUP-DT-22-127 | 2022-03-22 | D | CRS-GUP-DHI-DT-22-288 | 2022-04-07 | AC | DHI-GUP-DT-22-181 | 2022-04-19 | E | CRS-GUP-DHI-DT-22-308 | 2022-04-24 | AC | DHI-GUP-DT-22-202 | 2022-05-04 | F | CRS-GUP-DHI-DT-22-351 | 2022-05-18 | AC | DE-GUP-DT-E-22-250 | 2022-05-26 | 0 | CRS-GUP-DHI-DT-22-419 | 2022-06-13 | AC | DE-GUP-DT-E-22-1230 | 2023-01-06 | 1(CP) | CRS-GUP-DHI-DT-22-1450 | 2023-02-03 | AA | DE-GUP-DT-E-23-668 | 2023-07-04 | 2 | [33 empty] | DE-GUP-DT-E-22-250 | 2022-05-26 | 0
| GUP | CA00 | P1 | UMX | 181115 |  | GUP-CA00-P1UMX-181115 | GAS TURBINE BUILDING_SIDE ELEVATION | FA | 2022-12-31 | 2022-05-30 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GT Building | Arch. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-668 | 2023-07-04 | 2 | CRS-GUP-DHI-DT-22-1450 | 2023-02-03 | AA | DHI-GUP-DT-21-081 | 2021-10-29 | A | CRS-GUP-DHI-DT-21-063 | 2021-11-16 | RC | DHI-GUP-DT-21-196 | 2021-12-23 | B | CRS-GUP-DHI-DT-21-152 | 2022-01-12 | AC | DHI-GUP-DT-22-054 | 2022-01-28 | C | CRS-GUP-DHI-DT-22-213 | 2022-02-20 | AC | DHI-GUP-DT-22-127 | 2022-03-22 | D | CRS-GUP-DHI-DT-22-288 | 2022-04-07 | AA | DHI-GUP-DT-22-181 | 2022-04-19 | E | CRS-GUP-DHI-DT-22-308 | 2022-04-24 | AC | DHI-GUP-DT-22-202 | 2022-05-04 | F | CRS-GUP-DHI-DT-22-351 | 2022-05-18 | AC | DE-GUP-DT-E-22-250 | 2022-05-26 | 0 | CRS-GUP-DHI-DT-22-419 | 2022-06-13 | AC | DE-GUP-DT-E-22-1230 | 2023-01-06 | 1(CP) | CRS-GUP-DHI-DT-22-1450 | 2023-02-03 | AA | DE-GUP-DT-E-23-668 | 2023-07-04 | 2 | [33 empty] | DE-GUP-DT-E-22-250 | 2022-05-26 | 0
| GUP | CA00 | P1 | UMX | 181116 |  | GUP-CA00-P1UMX-181116 | GAS TURBINE BUILDING_WALL SECTION | FA | 2022-12-31 | 2022-05-30 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GT Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-668 | 2023-07-04 | 2 | CRS-GUP-DHI-DT-22-1450 | 2023-02-03 | AA | DHI-GUP-DT-21-081 | 2021-10-29 | A | CRS-GUP-DHI-DT-21-063 | 2021-11-16 | RC | DHI-GUP-DT-21-196 | 2021-12-23 | B | CRS-GUP-DHI-DT-21-152 | 2022-01-12 | AC | DHI-GUP-DT-22-054 | 2022-01-28 | C | CRS-GUP-DHI-DT-22-213 | 2022-02-20 | AC | DHI-GUP-DT-22-127 | 2022-03-22 | D | CRS-GUP-DHI-DT-22-288 | 2022-04-07 | AA | DHI-GUP-DT-22-181 | 2022-04-19 | E | CRS-GUP-DHI-DT-22-308 | 2022-04-24 | AC | DHI-GUP-DT-22-202 | 2022-05-04 | F | CRS-GUP-DHI-DT-22-351 | 2022-05-18 | AC | DE-GUP-DT-E-22-250 | 2022-05-26 | 0 | CRS-GUP-DHI-DT-22-419 | 2022-06-13 | AC | DE-GUP-DT-E-22-1230 | 2023-01-06 | 1(CP) | CRS-GUP-DHI-DT-22-1450 | 2023-02-03 | AA | DE-GUP-DT-E-23-668 | 2023-07-04 | 2 | [33 empty] | DE-GUP-DT-E-22-250 | 2022-05-26 | 0
| GUP | CA00 | P1 | UMX | 181117 |  | GUP-CA00-P1UMX-181117 | GAS TURBINE BUILDING_STAIR PLAN & SECTION | FA | 2022-12-31 | 2022-05-30 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GT Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-668 | 2023-07-04 | 2 | CRS-GUP-DHI-DT-22-1450 | 2023-02-03 | AA | DHI-GUP-DT-21-081 | 2021-10-29 | A | CRS-GUP-DHI-DT-21-063 | 2021-11-16 | RC | DHI-GUP-DT-21-196 | 2021-12-23 | B | CRS-GUP-DHI-DT-21-152 | 2022-01-12 | AC | DHI-GUP-DT-22-054 | 2022-01-28 | C | CRS-GUP-DHI-DT-22-213 | 2022-02-20 | AC | DHI-GUP-DT-22-127 | 2022-03-22 | D | CRS-GUP-DHI-DT-22-288 | 2022-04-07 | AC | DHI-GUP-DT-22-181 | 2022-04-19 | E | CRS-GUP-DHI-DT-22-308 | 2022-04-24 | AC | DHI-GUP-DT-22-202 | 2022-05-04 | F | CRS-GUP-DHI-DT-22-351 | 2022-05-18 | AC | DE-GUP-DT-E-22-250 | 2022-05-26 | 0 | CRS-GUP-DHI-DT-22-419 | 2022-06-13 | AC | DE-GUP-DT-E-22-1230 | 2023-01-06 | 1(CP) | CRS-GUP-DHI-DT-22-1450 | 2023-02-03 | AA | DE-GUP-DT-E-23-668 | 2023-07-04 | 2 | [33 empty] | DE-GUP-DT-E-22-250 | 2022-05-26 | 0
| GUP | CA00 | P1 | UMX | 181118 |  | GUP-CA00-P1UMX-181118 | GAS TURBINE BUILDING_ARCHITECTURAL MISC. DETAIL | FA | 2022-08-30 | 2022-10-30 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GT Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-667 | 2023-07-04 | 1 | CRS-GUP-DHI-DT-23-2128 | 2023-11-01 | AA | DE-GUP-DT-E-22-393 | 2022-07-13 | A | CRS-GUP-DHI-DT-22-579 | 2022-08-08 | RC | DE-GUP-DT-E-22-676 | 2022-09-16 | B | CRS-GUP-DHI-DT-22-886 | 2022-10-10 | AC | DE-GUP-DT-E-22-795 | 2022-10-13 | C | CRS-GUP-DHI-DT-22-962 | 2022-11-07 | AC | DE-GUP-DT-E-23-262 | 2023-03-03 | 0(CP) | CRS-GUP-DHI-DT-23-1749 | 2023-03-18 | AA | DE-GUP-DT-E-23-667 | 2023-07-04 | 1 | CRS-GUP-DHI-DT-23-2128 | 2023-11-01 | AA
| GUP | CA03 | P1 | UMX | 181151 |  | GUP-CA03-P1UMX-181151 | GAS TURBINE BUILDING_COLUMN ARRANGEMENT PLAN | FI | 2022-02-01 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GT Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-965 | 2022-11-21 | 5 | CRS-GUP-DHI-DT-22-1224 | 2022-12-13 | NC | DHI-GUP-DT-21-097 | 2021-11-11 | 0 | CRS-GUP-DHI-DT-21-061 | 2021-11-15 | RR | DHI-GUP-DT-22-055 | 2022-01-28 | 1 | CRS-GUP-DHI-DT-22-222 | 2022-02-28 | RR | DHI-GUP-DT-22-201 | 2022-05-04 | 2 | CRS-GUP-DHI-DT-22-352 | 2022-05-19 | NC | DE-GUP-DT-E-22-280 | 2022-06-09 | 3 | CRS-GUP-DHI-DT-22-482 | 2022-07-03 | NC | DE-GUP-DT-E-22-511 | 2022-08-18 | 4 | CRS-GUP-DHI-DT-22-696 | 2022-08-29 | NC | DE-GUP-DT-E-22-965 | 2022-11-21 | 5 | CRS-GUP-DHI-DT-22-1224 | 2022-12-13 | NC
| GUP | CA03 | P1 | UMX | 181152 |  | GUP-CA03-P1UMX-181152 | GAS TURBINE BUILDING_COLUMN SCHEDULE | FI | 2022-02-01 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GT Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-965 | 2022-11-21 | 4 | CRS-GUP-DHI-DT-22-1224 | 2022-12-13 | NC | DHI-GUP-DT-21-097 | 2021-11-11 | 0 | CRS-GUP-DHI-DT-21-061 | 2021-11-15 | RR | DHI-GUP-DT-22-055 | 2022-01-28 | 1 | CRS-GUP-DHI-DT-22-222 | 2022-02-28 | RR | DHI-GUP-DT-22-201 | 2022-05-04 | 2 | CRS-GUP-DHI-DT-22-352 | 2022-05-19 | NC | DE-GUP-DT-E-22-511 | 2022-08-18 | 3 | CRS-GUP-DHI-DT-22-696 | 2022-08-29 | NC | DE-GUP-DT-E-22-965 | 2022-11-21 | 4 | CRS-GUP-DHI-DT-22-1224 | 2022-12-13 | NC
| GUP | CA03 | P1 | UMX | 181153 |  | GUP-CA03-P1UMX-181153 | GAS TURBINE BUILDING_GROUND & PLATFORM FRAMING PLAN | FI | 2022-02-01 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GT Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-965 | 2022-11-21 | 5 | CRS-GUP-DHI-DT-22-1224 | 2022-12-13 | NC | DHI-GUP-DT-21-097 | 2021-11-11 | 0 | CRS-GUP-DHI-DT-21-061 | 2021-11-15 | RR | DHI-GUP-DT-22-055 | 2022-01-28 | 1 | CRS-GUP-DHI-DT-22-222 | 2022-02-28 | RR | DHI-GUP-DT-22-201 | 2022-05-04 | 2 | CRS-GUP-DHI-DT-22-352 | 2022-05-19 | NC | DE-GUP-DT-E-22-280 | 2022-06-09 | 3 | CRS-GUP-DHI-DT-22-482 | 2022-07-03 | RC | DE-GUP-DT-E-22-511 | 2022-08-18 | 4 | CRS-GUP-DHI-DT-22-696 | 2022-08-29 | RC | DE-GUP-DT-E-22-965 | 2022-11-21 | 5 | CRS-GUP-DHI-DT-22-1224 | 2022-12-13 | NC
| GUP | CA03 | P1 | UMX | 181154 |  | GUP-CA03-P1UMX-181154 | GAS TURBINE BUILDING_ROOF FRAMING PLAN | FI | 2022-02-01 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GT Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-965 | 2022-11-21 | 5 | CRS-GUP-DHI-DT-22-1224 | 2022-12-13 | NC | DHI-GUP-DT-21-097 | 2021-11-11 | 0 | CRS-GUP-DHI-DT-21-061 | 2021-11-15 | RR | DHI-GUP-DT-22-055 | 2022-01-28 | 1 | CRS-GUP-DHI-DT-22-222 | 2022-02-28 | RR | DHI-GUP-DT-22-201 | 2022-05-04 | 2 | CRS-GUP-DHI-DT-22-352 | 2022-05-19 | NC | DE-GUP-DT-E-22-280 | 2022-06-09 | 3 | CRS-GUP-DHI-DT-22-482 | 2022-07-03 | NC | DE-GUP-DT-E-22-511 | 2022-08-18 | 4 | CRS-GUP-DHI-DT-22-696 | 2022-08-29 | RC | DE-GUP-DT-E-22-965 | 2022-11-21 | 5 | CRS-GUP-DHI-DT-22-1224 | 2022-12-13 | NC
| GUP | CA03 | P1 | UMX | 181155 |  | GUP-CA03-P1UMX-181155 | GAS TURBINE BUILDING_LINE FRAMING ELEVATION | FI | 2022-02-01 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GT Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-965 | 2022-11-21 | 5 | CRS-GUP-DHI-DT-22-1224 | 2022-12-13 | NC | DHI-GUP-DT-21-097 | 2021-11-11 | 0 | CRS-GUP-DHI-DT-21-061 | 2021-11-15 | RR | DHI-GUP-DT-22-055 | 2022-01-28 | 1 | CRS-GUP-DHI-DT-22-222 | 2022-02-28 | RR | DHI-GUP-DT-22-201 | 2022-05-04 | 2 | CRS-GUP-DHI-DT-22-352 | 2022-05-19 | NC | DE-GUP-DT-E-22-280 | 2022-06-09 | 3 | CRS-GUP-DHI-DT-22-482 | 2022-07-03 | NC | DE-GUP-DT-E-22-511 | 2022-08-18 | 4 | CRS-GUP-DHI-DT-22-696 | 2022-08-29 | RC | DE-GUP-DT-E-22-965 | 2022-11-21 | 5 | CRS-GUP-DHI-DT-22-1224 | 2022-12-13 | NC
| GUP | CA03 | P1 | UMX | 181156 |  | GUP-CA03-P1UMX-181156 | GAS TURBINE BUILDING_ROW FRAMING ELEVATION | FI | 2022-02-01 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GT Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-965 | 2022-11-21 | 5 | CRS-GUP-DHI-DT-22-1224 | 2022-12-13 | NC | DHI-GUP-DT-21-097 | 2021-11-11 | 0 | CRS-GUP-DHI-DT-21-061 | 2021-11-15 | RR | DHI-GUP-DT-22-055 | 2022-01-28 | 1 | CRS-GUP-DHI-DT-22-222 | 2022-02-28 | RR | DHI-GUP-DT-22-201 | 2022-05-04 | 2 | CRS-GUP-DHI-DT-22-352 | 2022-05-19 | NC | DE-GUP-DT-E-22-280 | 2022-06-09 | 3 | CRS-GUP-DHI-DT-22-482 | 2022-07-03 | NC | DE-GUP-DT-E-22-511 | 2022-08-18 | 4 | CRS-GUP-DHI-DT-22-696 | 2022-08-29 | RC | DE-GUP-DT-E-22-965 | 2022-11-21 | 5 | CRS-GUP-DHI-DT-22-1224 | 2022-12-13 | NC
| GUP | CA03 | P1 | UMX | 181158 |  | GUP-CA03-P1UMX-181158 | GAS TURBINE BUILDING_GIRT LINE ELEVATION | FI | 2022-06-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GT Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-965 | 2022-11-21 | 2 | CRS-GUP-DHI-DT-22-1224 | 2022-12-13 | NC | DE-GUP-DT-E-22-280 | 2022-06-09 | 0 | CRS-GUP-DHI-DT-22-482 | 2022-07-03 | NC | DE-GUP-DT-E-22-511 | 2022-08-18 | 1 | CRS-GUP-DHI-DT-22-696 | 2022-08-29 | NC | DE-GUP-DT-E-22-965 | 2022-11-21 | 2 | CRS-GUP-DHI-DT-22-1224 | 2022-12-13 | NC
| GUP | CA03 | P1 | UMX | 181159 |  | GUP-CA03-P1UMX-181159 | GAS TURBINE BUILDING_GIRT ROW ELEVATION | FI | 2022-06-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GT Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-965 | 2022-11-21 | 2 | CRS-GUP-DHI-DT-22-1224 | 2022-12-13 | NC | DE-GUP-DT-E-22-280 | 2022-06-09 | 0 | CRS-GUP-DHI-DT-22-482 | 2022-07-03 | NC | DE-GUP-DT-E-22-511 | 2022-08-18 | 1 | CRS-GUP-DHI-DT-22-696 | 2022-08-29 | RC | DE-GUP-DT-E-22-965 | 2022-11-21 | 2 | CRS-GUP-DHI-DT-22-1224 | 2022-12-13 | NC
| GUP | CA03 | P1 | UMX | 181162 |  | GUP-CA03-P1UMX-181162 | GAS TURBINE BUILDING_STAIR FRAMING PLAN & ELEVATION | FI | 2022-06-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GT Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-511 | 2022-08-18 | 1 | CRS-GUP-DHI-DT-22-696 | 2022-08-29 | NC | DE-GUP-DT-E-22-280 | 2022-06-09 | 0 | CRS-GUP-DHI-DT-22-482 | 2022-07-03 | NC | DE-GUP-DT-E-22-511 | 2022-08-18 | 1 | CRS-GUP-DHI-DT-22-696 | 2022-08-29 | NC
| GUP | CA03 | P1 | UMX | 181164 |  | GUP-CA03-P1UMX-181164 | GAS TURBINE BUILDING_CONNECTION DETAIL | FI | 2022-06-30 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | GT Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-22-965 | 2022-11-21 | 1 | CRS-GUP-DHI-DT-22-1224 | 2022-12-13 | NC | DE-GUP-DT-E-22-511 | 2022-08-18 | A | CRS-GUP-DHI-DT-22-696 | 2022-08-29 | RC | DE-GUP-DT-E-22-965 | 2022-11-21 | 1 | CRS-GUP-DHI-DT-22-1224 | 2022-12-13 | NC
| GUP | CA01 | P1 | UMX | 181134 |  | GUP-CA01-P1UMX-181134 | GAS TURBINE BUILDING_EQUIPMENT FOUNDATION & SLAB OUTLINE PLAN | FA | 2022-08-30 | 2022-12-30 | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | GT Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-667 | 2023-07-04 | 1 | CRS-GUP-DHI-DT-23-2128 | 2023-11-01 | AA | DE-GUP-DT-E-22-393 | 2022-07-13 | A | CRS-GUP-DHI-DT-22-579 | 2022-08-08 | RC | DE-GUP-DT-E-22-676 | 2022-09-16 | B | CRS-GUP-DHI-DT-22-886 | 2022-10-10 | RC | DE-GUP-DT-E-22-795 | 2022-10-13 | C | CRS-GUP-DHI-DT-22-962 | 2022-11-07 | AC | DE-GUP-DT-E-23-262 | 2023-03-03 | 0(CP) | CRS-GUP-DHI-DT-23-1749 | 2023-03-18 | AA | DE-GUP-DT-E-23-667 | 2023-07-04 | 1 | CRS-GUP-DHI-DT-23-2128 | 2023-11-01 | AA
| GUP | CA02 | P1 | UMX | 181135 |  | GUP-CA02-P1UMX-181135 | GAS TURBINE BUILDING_EQUIPMENT FOUNDATION RE-BAR DETAIL | FI | 2022-08-30 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | GT Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-667 | 2023-07-04 | 4 | CRS-GUP-DHI-DT-23-2128 | 2023-11-01 | NC | DE-GUP-DT-E-22-393 | 2022-07-13 | 0 | CRS-GUP-DHI-DT-22-579 | 2022-08-08 | RC | DE-GUP-DT-E-22-676 | 2022-09-16 | 1 | CRS-GUP-DHI-DT-22-886 | 2022-10-10 | NC | DE-GUP-DT-E-22-795 | 2022-10-13 | 2 | CRS-GUP-DHI-DT-22-962 | 2022-11-07 | NC | DE-GUP-DT-E-23-262 | 2023-03-03 | 3 | CRS-GUP-DHI-DT-23-1749 | 2023-03-18 | NC | DE-GUP-DT-E-23-667 | 2023-07-04 | 4 | CRS-GUP-DHI-DT-23-2128 | 2023-11-01 | NC
| GUP | CA01 | P1 | UMX | 181136 |  | GUP-CA01-P1UMX-181136 | GAS TURBINE BUILDING_STRUCTURAL MISC. DETAIL | FI | 2022-06-01 |  | 건축기술2팀(Arch.) | 구남영 | [5 empty] | CCPP | GT Building | Arch. |  | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-667 | 2023-07-04 | 1 | CRS-GUP-DHI-DT-23-2128 | 2023-11-01 | NC | DE-GUP-DT-E-23-262 | 2023-03-03 | 0 | CRS-GUP-DHI-DT-23-1749 | 2023-03-18 | NC | DE-GUP-DT-E-23-667 | 2023-07-04 | 1 | CRS-GUP-DHI-DT-23-2128 | 2023-11-01 | NC
| GUP | CA06 | P1 | UMA | 181201 |  | GUP-CA06-P1UMA-181201 | STEAM TURBINE BUILDING_CALCULATION SHEET | FA | 2022-01-30 | 2022-08-30 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ST Building | Arch. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-684 | 2023-07-11 | 3 | CRS-GUP-DHI-DT-23-1788 | 2023-03-30 | AA | DHI-GUP-DT-21-195 | 2021-12-23 | A | CRS-GUP-DHI-DT-21-140 | 2022-01-11 | RC | DHI-GUP-DT-22-045 | 2022-01-28 | B | CRS-GUP-DHI-DT-22-205 | 2022-02-20 | RC | DHI-GUP-DT-22-133 | 2022-03-25 | C | CRS-GUP-DHI-DT-22-294 | 2022-04-17 | RC | DE-GUP-DT-E-22-297 | 2022-06-14 | D | CRS-GUP-DHI-DT-22-495 | 2022-07-06 | AC | DE-GUP-DT-E-22-464 | 2022-07-28 | E | CRS-GUP-DHI-DT-22-638 | 2022-08-18 | AC | DE-GUP-DT-E-22-650 | 2022-09-08 | F | CRS-GUP-DHI-DT-22-830 | 2022-09-22 | AC | DE-GUP-DT-E-22-953 | 2022-11-17 | 0(CP) | CRS-GUP-DHI-DT-22-1213 | 2022-11-30 | AC | DE-GUP-DT-E-23-089 | 2023-01-30 | 1(CP) | CRS-GUP-DHI-DT-23-1547 | 2023-02-19 | AC | DE-GUP-DT-E-23-318 | 2023-03-15 | 2(CP) | CRS-GUP-DHI-DT-23-1788 | 2023-03-30 | AA | DE-GUP-DT-E-23-684 | 2023-07-11 | 3
| GUP | CA01 | P1 | UMA | 181231 |  | GUP-CA01-P1UMA-181231 | STEAM TURBINE BUILDING_FOUNDATION ARRANGEMENT PLAN | FA | 2022-01-30 | 2022-08-30 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ST Building | Arch. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-684 | 2023-07-11 | 3 | CRS-GUP-DHI-DT-23-1788 | 2023-03-30 | AA | DHI-GUP-DT-21-195 | 2021-12-23 | A | CRS-GUP-DHI-DT-21-140 | 2022-01-11 | RC | DHI-GUP-DT-22-045 | 2022-01-28 | B | CRS-GUP-DHI-DT-22-205 | 2022-02-20 | RC | DHI-GUP-DT-22-133 | 2022-03-25 | C | CRS-GUP-DHI-DT-22-294 | 2022-04-17 | RC | DE-GUP-DT-E-22-297 | 2022-06-14 | D | CRS-GUP-DHI-DT-22-495 | 2022-07-06 | AC | DE-GUP-DT-E-22-464 | 2022-07-28 | E | CRS-GUP-DHI-DT-22-638 | 2022-08-18 | AC | DE-GUP-DT-E-22-650 | 2022-09-08 | F | CRS-GUP-DHI-DT-22-830 | 2022-09-22 | AC | DE-GUP-DT-E-22-953 | 2022-11-17 | 0(CP) | CRS-GUP-DHI-DT-22-1213 | 2022-11-30 | AC | DE-GUP-DT-E-23-089 | 2023-01-30 | 1(CP) | CRS-GUP-DHI-DT-23-1547 | 2023-02-19 | AC | DE-GUP-DT-E-23-318 | 2023-03-15 | 2(CP) | CRS-GUP-DHI-DT-23-1788 | 2023-03-30 | AA | DE-GUP-DT-E-23-684 | 2023-07-11 | 3
| GUP | CA01 | P1 | UMA | 181232 |  | GUP-CA01-P1UMA-181232 | STEAM TURBINE BUILDING_FOUNDATION LONGITUDINAL SECTION | FA | 2022-01-30 | 2022-08-30 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ST Building | Arch. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-684 | 2023-07-11 | 3 | CRS-GUP-DHI-DT-23-1788 | 2023-03-30 | AA | DHI-GUP-DT-21-195 | 2021-12-23 | A | CRS-GUP-DHI-DT-21-140 | 2022-01-11 | RC | DHI-GUP-DT-22-045 | 2022-01-28 | B | CRS-GUP-DHI-DT-22-205 | 2022-02-20 | RC | DHI-GUP-DT-22-133 | 2022-03-25 | C | CRS-GUP-DHI-DT-22-294 | 2022-04-17 | RC | DE-GUP-DT-E-22-297 | 2022-06-14 | D | CRS-GUP-DHI-DT-22-495 | 2022-07-06 | AC | DE-GUP-DT-E-22-464 | 2022-07-28 | E | CRS-GUP-DHI-DT-22-638 | 2022-08-18 | AC | DE-GUP-DT-E-22-650 | 2022-09-08 | F | CRS-GUP-DHI-DT-22-830 | 2022-09-22 | AC | DE-GUP-DT-E-22-953 | 2022-11-17 | 0(CP) | CRS-GUP-DHI-DT-22-1213 | 2022-11-30 | AC | DE-GUP-DT-E-23-089 | 2023-01-30 | 1(CP) | CRS-GUP-DHI-DT-23-1547 | 2023-02-19 | AC | DE-GUP-DT-E-23-318 | 2023-03-15 | 2(CP) | CRS-GUP-DHI-DT-23-1788 | 2023-03-30 | AA | DE-GUP-DT-E-23-684 | 2023-07-11 | 3
| GUP | CA02 | P1 | UMA | 181233 |  | GUP-CA02-P1UMA-181233 | STEAM TURBINE BUILDING_FOUNDATION RE-BAR DETAIL | FI | 2022-01-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ST Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-684 | 2023-07-11 | 9 | CRS-GUP-DHI-DT-23-1788 | 2023-03-30 | NC | DHI-GUP-DT-21-195 | 2021-12-23 | 0 | CRS-GUP-DHI-DT-21-140 | 2022-01-11 | NC | DHI-GUP-DT-22-045 | 2022-01-28 | 1 | CRS-GUP-DHI-DT-22-205 | 2022-02-20 | I | DHI-GUP-DT-22-133 | 2022-03-25 | 2 | CRS-GUP-DHI-DT-22-294 | 2022-04-17 | RC | DE-GUP-DT-E-22-297 | 2022-06-14 | 3 | CRS-GUP-DHI-DT-22-495 | 2022-07-06 | RC | DE-GUP-DT-E-22-464 | 2022-07-28 | 4 | CRS-GUP-DHI-DT-22-638 | 2022-08-18 | NC | DE-GUP-DT-E-22-650 | 2022-09-08 | 5 | CRS-GUP-DHI-DT-22-830 | 2022-09-22 | NC | DE-GUP-DT-E-22-953 | 2022-11-17 | 6 | CRS-GUP-DHI-DT-22-1213 | 2022-11-30 | NC | DE-GUP-DT-E-23-089 | 2023-01-30 | 7 | CRS-GUP-DHI-DT-23-1547 | 2023-02-19 | RC | DE-GUP-DT-E-23-318 | 2023-03-15 | 8 | CRS-GUP-DHI-DT-23-1788 | 2023-03-30 | NC | DE-GUP-DT-E-23-684 | 2023-07-11 | 9
| GUP | CA00 | P1 | UMA | 181212 |  | GUP-CA00-P1UMA-181212 | STEAM TURBINE BUILDING_DOOR & WINDOW SCHEDULE | FA | 2022-01-30 | 2022-10-30 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ST Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-684 | 2023-07-11 | 3 | CRS-GUP-DHI-DT-23-1788 | 2023-03-30 | AA | DHI-GUP-DT-21-195 | 2021-12-23 | A | CRS-GUP-DHI-DT-21-140 | 2022-01-11 | AC | DHI-GUP-DT-22-045 | 2022-01-28 | B | CRS-GUP-DHI-DT-22-205 | 2022-02-20 | AC | DHI-GUP-DT-22-133 | 2022-03-25 | C | CRS-GUP-DHI-DT-22-294 | 2022-04-17 | AA | DE-GUP-DT-E-22-297 | 2022-06-14 | D | CRS-GUP-DHI-DT-22-495 | 2022-07-06 | AC | DE-GUP-DT-E-22-464 | 2022-07-28 | E | CRS-GUP-DHI-DT-22-638 | 2022-08-18 | AC | DE-GUP-DT-E-22-650 | 2022-09-08 | F | CRS-GUP-DHI-DT-22-830 | 2022-09-22 | AC | DE-GUP-DT-E-22-953 | 2022-11-17 | 0(CP) | CRS-GUP-DHI-DT-22-1213 | 2022-11-30 | AC | DE-GUP-DT-E-23-089 | 2023-01-30 | 1(CP) | CRS-GUP-DHI-DT-23-1547 | 2023-02-19 | AC | DE-GUP-DT-E-23-318 | 2023-03-15 | 2(CP) | CRS-GUP-DHI-DT-23-1788 | 2023-03-30 | AA | DE-GUP-DT-E-23-684 | 2023-07-11 | 3
| GUP | CA00 | P1 | UMA | 181213 |  | GUP-CA00-P1UMA-181213 | STEAM TURBINE BUILDING_GROUND FLOOR PLAN | FA | 2022-01-30 | 2022-08-30 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ST Building | Arch. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-684 | 2023-07-11 | 3 | CRS-GUP-DHI-DT-23-1788 | 2023-03-30 | AA | DHI-GUP-DT-21-195 | 2021-12-23 | A | CRS-GUP-DHI-DT-21-140 | 2022-01-11 | AC | DHI-GUP-DT-22-045 | 2022-01-28 | B | CRS-GUP-DHI-DT-22-205 | 2022-02-20 | AA | DHI-GUP-DT-22-133 | 2022-03-25 | C | CRS-GUP-DHI-DT-22-294 | 2022-04-17 | AA | DE-GUP-DT-E-22-297 | 2022-06-14 | D | CRS-GUP-DHI-DT-22-495 | 2022-07-06 | AC | DE-GUP-DT-E-22-464 | 2022-07-28 | E | CRS-GUP-DHI-DT-22-638 | 2022-08-18 | AC | DE-GUP-DT-E-22-650 | 2022-09-08 | F | CRS-GUP-DHI-DT-22-830 | 2022-09-22 | AC | DE-GUP-DT-E-22-953 | 2022-11-17 | 0(CP) | CRS-GUP-DHI-DT-22-1213 | 2022-11-30 | AC | DE-GUP-DT-E-23-089 | 2023-01-30 | 1(CP) | CRS-GUP-DHI-DT-23-1547 | 2023-02-19 | AC | DE-GUP-DT-E-23-318 | 2023-03-15 | 2(CP) | CRS-GUP-DHI-DT-23-1788 | 2023-03-30 | AA | DE-GUP-DT-E-23-684 | 2023-07-11 | 3
| GUP | CA00 | P1 | UMA | 181214 |  | GUP-CA00-P1UMA-181214 | STEAM TURBINE BUILDING_ROOF PLAN | FA | 2022-01-30 | 2022-08-30 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ST Building | Arch. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-684 | 2023-07-11 | 3 | CRS-GUP-DHI-DT-23-1788 | 2023-03-30 | AA | DHI-GUP-DT-21-195 | 2021-12-23 | A | CRS-GUP-DHI-DT-21-140 | 2022-01-11 | AC | DHI-GUP-DT-22-045 | 2022-01-28 | B | CRS-GUP-DHI-DT-22-205 | 2022-02-20 | AC | DHI-GUP-DT-22-133 | 2022-03-25 | C | CRS-GUP-DHI-DT-22-294 | 2022-04-17 | AC | DE-GUP-DT-E-22-297 | 2022-06-14 | D | CRS-GUP-DHI-DT-22-495 | 2022-07-06 | AC | DE-GUP-DT-E-22-464 | 2022-07-28 | E | CRS-GUP-DHI-DT-22-638 | 2022-08-18 | AC | DE-GUP-DT-E-22-650 | 2022-09-08 | F | CRS-GUP-DHI-DT-22-830 | 2022-09-22 | AC | DE-GUP-DT-E-22-953 | 2022-11-17 | 0(CP) | CRS-GUP-DHI-DT-22-1213 | 2022-11-30 | AC | DE-GUP-DT-E-23-089 | 2023-01-30 | 1(CP) | CRS-GUP-DHI-DT-23-1547 | 2023-02-19 | AC | DE-GUP-DT-E-23-318 | 2023-03-15 | 2(CP) | CRS-GUP-DHI-DT-23-1788 | 2023-03-30 | AA | DE-GUP-DT-E-23-684 | 2023-07-11 | 3
| GUP | CA00 | P1 | UMA | 181215 |  | GUP-CA00-P1UMA-181215 | STEAM TURBINE BUILDING_MAIN SECTION | FA | 2022-01-30 | 2022-08-30 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ST Building | Arch. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-684 | 2023-07-11 | 3 | CRS-GUP-DHI-DT-23-1788 | 2023-03-30 | AA | DHI-GUP-DT-21-195 | 2021-12-23 | A | CRS-GUP-DHI-DT-21-140 | 2022-01-11 | AC | DHI-GUP-DT-22-045 | 2022-01-28 | B | CRS-GUP-DHI-DT-22-205 | 2022-02-20 | AC | DHI-GUP-DT-22-133 | 2022-03-25 | C | CRS-GUP-DHI-DT-22-294 | 2022-04-17 | AC | DE-GUP-DT-E-22-297 | 2022-06-14 | D | CRS-GUP-DHI-DT-22-495 | 2022-07-06 | AC | DE-GUP-DT-E-22-464 | 2022-07-28 | E | CRS-GUP-DHI-DT-22-638 | 2022-08-18 | AC | DE-GUP-DT-E-22-650 | 2022-09-08 | F | CRS-GUP-DHI-DT-22-830 | 2022-09-22 | AC | DE-GUP-DT-E-22-953 | 2022-11-17 | 0(CP) | CRS-GUP-DHI-DT-22-1213 | 2022-11-30 | AC | DE-GUP-DT-E-23-089 | 2023-01-30 | 1(CP) | CRS-GUP-DHI-DT-23-1547 | 2023-02-19 | AC | DE-GUP-DT-E-23-318 | 2023-03-15 | 2(CP) | CRS-GUP-DHI-DT-23-1788 | 2023-03-30 | AA | DE-GUP-DT-E-23-684 | 2023-07-11 | 3
| GUP | CA00 | P1 | UMA | 181216 |  | GUP-CA00-P1UMA-181216 | STEAM TURBINE BUILDING_SIDE ELEVATION | FA | 2022-01-30 | 2022-08-30 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ST Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-684 | 2023-07-11 | 3 | CRS-GUP-DHI-DT-23-1788 | 2023-03-30 | AA | DHI-GUP-DT-21-195 | 2021-12-23 | A | CRS-GUP-DHI-DT-21-140 | 2022-01-11 | AC | DHI-GUP-DT-22-045 | 2022-01-28 | B | CRS-GUP-DHI-DT-22-205 | 2022-02-20 | AA | DHI-GUP-DT-22-133 | 2022-03-25 | C | CRS-GUP-DHI-DT-22-294 | 2022-04-17 | AC | DE-GUP-DT-E-22-297 | 2022-06-14 | D | CRS-GUP-DHI-DT-22-495 | 2022-07-06 | AC | DE-GUP-DT-E-22-464 | 2022-07-28 | E | CRS-GUP-DHI-DT-22-638 | 2022-08-18 | AC | DE-GUP-DT-E-22-650 | 2022-09-08 | F | CRS-GUP-DHI-DT-22-830 | 2022-09-22 | AC | DE-GUP-DT-E-22-953 | 2022-11-17 | 0(CP) | CRS-GUP-DHI-DT-22-1213 | 2022-11-30 | AC | DE-GUP-DT-E-23-089 | 2023-01-30 | 1(CP) | CRS-GUP-DHI-DT-23-1547 | 2023-02-19 | AC | DE-GUP-DT-E-23-318 | 2023-03-15 | 2(CP) | CRS-GUP-DHI-DT-23-1788 | 2023-03-30 | AA | DE-GUP-DT-E-23-684 | 2023-07-11 | 3
| GUP | CA00 | P1 | UMA | 181217 |  | GUP-CA00-P1UMA-181217 | STEAM TURBINE BUILDING_OPERATING & CRANE GIRDER FLOOR PLAN | FA | 2022-01-30 | 2022-08-30 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ST Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-684 | 2023-07-11 | 3 | CRS-GUP-DHI-DT-23-1788 | 2023-03-30 | AA | DHI-GUP-DT-21-195 | 2021-12-23 | A | CRS-GUP-DHI-DT-21-140 | 2022-01-11 | AC | DHI-GUP-DT-22-045 | 2022-01-28 | B | CRS-GUP-DHI-DT-22-205 | 2022-02-20 | AC | DHI-GUP-DT-22-133 | 2022-03-25 | C | CRS-GUP-DHI-DT-22-294 | 2022-04-17 | AC | DE-GUP-DT-E-22-297 | 2022-06-14 | D | CRS-GUP-DHI-DT-22-495 | 2022-07-06 | AC | DE-GUP-DT-E-22-464 | 2022-07-28 | E | CRS-GUP-DHI-DT-22-638 | 2022-08-18 | AC | DE-GUP-DT-E-22-650 | 2022-09-08 | F | CRS-GUP-DHI-DT-22-830 | 2022-09-22 | AC | DE-GUP-DT-E-22-953 | 2022-11-17 | 0(CP) | CRS-GUP-DHI-DT-22-1213 | 2022-11-30 | AC | DE-GUP-DT-E-23-089 | 2023-01-30 | 1(CP) | CRS-GUP-DHI-DT-23-1547 | 2023-02-19 | AC | DE-GUP-DT-E-23-318 | 2023-03-15 | 2(CP) | CRS-GUP-DHI-DT-23-1788 | 2023-03-30 | AA | DE-GUP-DT-E-23-684 | 2023-07-11 | 3
| GUP | CA00 | P1 | UMA | 181219 |  | GUP-CA00-P1UMA-181219 | STEAM TURBINE BUILDING_WALL SECTION | FI | 2022-01-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ST Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-684 | 2023-07-11 | 9 | CRS-GUP-DHI-DT-23-1788 | 2023-03-30 | NC | DHI-GUP-DT-21-195 | 2021-12-23 | 0 | CRS-GUP-DHI-DT-21-140 | 2022-01-11 | RC | DHI-GUP-DT-22-045 | 2022-01-28 | 1 | CRS-GUP-DHI-DT-22-205 | 2022-02-20 | I | DHI-GUP-DT-22-133 | 2022-03-25 | 2 | CRS-GUP-DHI-DT-22-294 | 2022-04-17 | NC | DE-GUP-DT-E-22-297 | 2022-06-14 | 3 | CRS-GUP-DHI-DT-22-495 | 2022-07-06 | NC | DE-GUP-DT-E-22-464 | 2022-07-28 | 4 | CRS-GUP-DHI-DT-22-638 | 2022-08-18 | NC | DE-GUP-DT-E-22-650 | 2022-09-08 | 5 | CRS-GUP-DHI-DT-22-830 | 2022-09-22 | NC | DE-GUP-DT-E-22-953 | 2022-11-17 | 6 | CRS-GUP-DHI-DT-22-1213 | 2022-11-30 | RC | DE-GUP-DT-E-23-089 | 2023-01-30 | 7 | CRS-GUP-DHI-DT-23-1547 | 2023-02-19 | NC | DE-GUP-DT-E-23-318 | 2023-03-15 | 8 | CRS-GUP-DHI-DT-23-1788 | 2023-03-30 | NC | DE-GUP-DT-E-23-684 | 2023-07-11 | 9
| GUP | CA00 | P1 | UMA | 181220 |  | GUP-CA00-P1UMA-181220 | STEAM TURBINE BUILDING_STAIR PLAN & SECTION | FI | 2022-01-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ST Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-684 | 2023-07-11 | 9 | CRS-GUP-DHI-DT-23-1788 | 2023-03-30 | NC | DHI-GUP-DT-21-195 | 2021-12-23 | 0 | CRS-GUP-DHI-DT-21-140 | 2022-01-11 | RC | DHI-GUP-DT-22-045 | 2022-01-28 | 1 | CRS-GUP-DHI-DT-22-205 | 2022-02-20 | I | DHI-GUP-DT-22-133 | 2022-03-25 | 2 | CRS-GUP-DHI-DT-22-294 | 2022-04-17 | NC | DE-GUP-DT-E-22-297 | 2022-06-14 | 3 | CRS-GUP-DHI-DT-22-495 | 2022-07-06 | NC | DE-GUP-DT-E-22-464 | 2022-07-28 | 4 | CRS-GUP-DHI-DT-22-638 | 2022-08-18 | NC | DE-GUP-DT-E-22-650 | 2022-09-08 | 5 | CRS-GUP-DHI-DT-22-830 | 2022-09-22 | NC | DE-GUP-DT-E-22-953 | 2022-11-17 | 6 | CRS-GUP-DHI-DT-22-1213 | 2022-11-30 | RC | DE-GUP-DT-E-23-089 | 2023-01-30 | 7 | CRS-GUP-DHI-DT-23-1547 | 2023-02-19 | RC | DE-GUP-DT-E-23-318 | 2023-03-15 | 8 | CRS-GUP-DHI-DT-23-1788 | 2023-03-30 | NC | DE-GUP-DT-E-23-684 | 2023-07-11 | 9
| GUP | CA00 | P1 | UMA | 181222 |  | GUP-CA00-P1UMA-181222 | STEAM TURBINE BUILDING_ARCHITECTURAL MISC. DETAIL | FA | 2022-09-30 | 2023-01-30 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ST Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-962 | 2023-12-01 | 4 | 자체 CRS 개정 후 제출 | 2023-11-30 | N/A | DHI-GUP-DT-22-045 | 2022-01-28 | A | CRS-GUP-DHI-DT-22-205 | 2022-02-20 | AC | DHI-GUP-DT-22-133 | 2022-03-25 | B | CRS-GUP-DHI-DT-22-294 | 2022-04-17 | AA | DE-GUP-DT-E-22-297 | 2022-06-14 | C | CRS-GUP-DHI-DT-22-495 | 2022-07-06 | AC | DE-GUP-DT-E-22-464 | 2022-07-28 | D | CRS-GUP-DHI-DT-22-638 | 2022-08-18 | AC | DE-GUP-DT-E-22-650 | 2022-09-08 | E | CRS-GUP-DHI-DT-22-830 | 2022-09-22 | AC | DE-GUP-DT-E-22-953 | 2022-11-17 | 0(CP) | CRS-GUP-DHI-DT-22-1213 | 2022-11-30 | AC | DE-GUP-DT-E-23-089 | 2023-01-30 | 1(CP) | CRS-GUP-DHI-DT-23-1547 | 2023-02-19 | AC | DE-GUP-DT-E-23-318 | 2023-03-15 | 2(CP) | CRS-GUP-DHI-DT-23-1788 | 2023-03-30 | AA | DE-GUP-DT-E-23-684 | 2023-07-11 | 3 | 자체 CRS 개정 후 제출 | 2023-11-30 | N/A | DE-GUP-DT-E-23-962 | 2023-12-01 | 4
| GUP | CA03 | P1 | UMA | 181251 |  | GUP-CA03-P1UMA-181251 | STEAM TURBINE BUILDING_COLUMN ARRANGEMENT PLAN | FI | 2022-01-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ST Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-315 | 2023-03-15 | 4 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC | DHI-GUP-DT-22-046 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-206 | 2022-02-20 | NC | DE-GUP-DT-E-22-465 | 2022-07-28 | 1 | CRS-GUP-DHI-DT-22-650 | 2022-08-20 | NC | DE-GUP-DT-E-22-651 | 2022-09-08 | 2 | CRS-GUP-DHI-DT-22-831 | 2022-09-22 | NC | DE-GUP-DT-E-22-1141 | 2022-12-21 | 3 | CRS-GUP-DHI-DT-22-1389 | 2023-01-03 | NC | DE-GUP-DT-E-23-315 | 2023-03-15 | 4 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC
| GUP | CA03 | P1 | UMA | 181252 |  | GUP-CA03-P1UMA-181252 | STEAM TURBINE BUILDING_COLUMN SCHEDULE | FI | 2022-01-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ST Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-315 | 2023-03-15 | 4 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC | DHI-GUP-DT-22-046 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-206 | 2022-02-20 | NC | DE-GUP-DT-E-22-465 | 2022-07-28 | 1 | CRS-GUP-DHI-DT-22-650 | 2022-08-20 | NC | DE-GUP-DT-E-22-651 | 2022-09-08 | 2 | CRS-GUP-DHI-DT-22-831 | 2022-09-22 | NC | DE-GUP-DT-E-22-1141 | 2022-12-21 | 3 | CRS-GUP-DHI-DT-22-1389 | 2023-01-03 | NC | DE-GUP-DT-E-23-315 | 2023-03-15 | 4 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC
| GUP | CA03 | P1 | UMA | 181253 |  | GUP-CA03-P1UMA-181253 | STEAM TURBINE BUILDING_GROUND FLOOR FRAMING PLAN | FI | 2022-01-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ST Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-315 | 2023-03-15 | 4 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC | DHI-GUP-DT-22-046 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-206 | 2022-02-20 | NC | DE-GUP-DT-E-22-465 | 2022-07-28 | 1 | CRS-GUP-DHI-DT-22-650 | 2022-08-20 | NC | DE-GUP-DT-E-22-651 | 2022-09-08 | 2 | CRS-GUP-DHI-DT-22-831 | 2022-09-22 | RC | DE-GUP-DT-E-22-1141 | 2022-12-21 | 3 | CRS-GUP-DHI-DT-22-1389 | 2023-01-03 | NC | DE-GUP-DT-E-23-315 | 2023-03-15 | 4 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC
| GUP | CA03 | P1 | UMA | 181254 |  | GUP-CA03-P1UMA-181254 | STEAM TURBINE BUILDING_OPERATING & CRANE GIRDER FLOOR FRAMING PLAN | FI | 2022-01-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ST Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-24-294 | 2024-12-17 | 5 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC | DHI-GUP-DT-22-046 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-206 | 2022-02-20 | NC | DE-GUP-DT-E-22-465 | 2022-07-28 | 1 | CRS-GUP-DHI-DT-22-650 | 2022-08-20 | NC | DE-GUP-DT-E-22-651 | 2022-09-08 | 2 | CRS-GUP-DHI-DT-22-831 | 2022-09-22 | RC | DE-GUP-DT-E-22-1141 | 2022-12-21 | 3 | CRS-GUP-DHI-DT-22-1389 | 2023-01-03 | RC | DE-GUP-DT-E-23-315 | 2023-03-15 | 4 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC | DE-GUP-DT-E-24-294 | 2024-12-17 | 5
| GUP | CA03 | P1 | UMA | 181255 |  | GUP-CA03-P1UMA-181255 | STEAM TURBINE BUILDING_ROOF FRAMING PLAN | FI | 2022-01-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ST Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-315 | 2023-03-15 | 4 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC | DHI-GUP-DT-22-046 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-206 | 2022-02-20 | NC | DE-GUP-DT-E-22-465 | 2022-07-28 | 1 | CRS-GUP-DHI-DT-22-650 | 2022-08-20 | NC | DE-GUP-DT-E-22-651 | 2022-09-08 | 2 | CRS-GUP-DHI-DT-22-831 | 2022-09-22 | NC | DE-GUP-DT-E-22-1141 | 2022-12-21 | 3 | CRS-GUP-DHI-DT-22-1389 | 2023-01-03 | NC | DE-GUP-DT-E-23-315 | 2023-03-15 | 4 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC
| GUP | CA03 | P1 | UMA | 181256 |  | GUP-CA03-P1UMA-181256 | STEAM TURBINE BUILDING_LINE FRAMING ELEVATION | FI | 2022-01-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ST Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-315 | 2023-03-15 | 4 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC | DHI-GUP-DT-22-046 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-206 | 2022-02-20 | NC | DE-GUP-DT-E-22-465 | 2022-07-28 | 1 | CRS-GUP-DHI-DT-22-650 | 2022-08-20 | NC | DE-GUP-DT-E-22-651 | 2022-09-08 | 2 | CRS-GUP-DHI-DT-22-831 | 2022-09-22 | NC | DE-GUP-DT-E-22-1141 | 2022-12-21 | 3 | CRS-GUP-DHI-DT-22-1389 | 2023-01-03 | NC | DE-GUP-DT-E-23-315 | 2023-03-15 | 4 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC
| GUP | CA03 | P1 | UMA | 181257 |  | GUP-CA03-P1UMA-181257 | STEAM TURBINE BUILDING_ROW FRAMING ELEVATION | FI | 2022-01-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ST Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-315 | 2023-03-15 | 4 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC | DHI-GUP-DT-22-046 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-206 | 2022-02-20 | NC | DE-GUP-DT-E-22-465 | 2022-07-28 | 1 | CRS-GUP-DHI-DT-22-650 | 2022-08-20 | NC | DE-GUP-DT-E-22-651 | 2022-09-08 | 2 | CRS-GUP-DHI-DT-22-831 | 2022-09-22 | NC | DE-GUP-DT-E-22-1141 | 2022-12-21 | 3 | CRS-GUP-DHI-DT-22-1389 | 2023-01-03 | NC | DE-GUP-DT-E-23-315 | 2023-03-15 | 4 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC
| GUP | CA03 | P1 | UMA | 181259 |  | GUP-CA03-P1UMA-181259 | STEAM TURBINE BUILDING_GIRT LINE ELEVATION | FI | 2022-07-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ST Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-315 | 2023-03-15 | 4 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC | DHI-GUP-DT-22-046 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-206 | 2022-02-20 | NC | DE-GUP-DT-E-22-465 | 2022-07-28 | 1 | CRS-GUP-DHI-DT-22-650 | 2022-08-20 | NC | DE-GUP-DT-E-22-651 | 2022-09-08 | 2 | CRS-GUP-DHI-DT-22-831 | 2022-09-22 | RC | DE-GUP-DT-E-22-1141 | 2022-12-21 | 3 | CRS-GUP-DHI-DT-22-1389 | 2023-01-03 | NC | DE-GUP-DT-E-23-315 | 2023-03-15 | 4 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC
| GUP | CA03 | P1 | UMA | 181260 |  | GUP-CA03-P1UMA-181260 | STEAM TURBINE BUILDING_GIRT ROW ELEVATION | FI | 2022-07-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ST Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-315 | 2023-03-15 | 4 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC | DHI-GUP-DT-22-046 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-206 | 2022-02-20 | NC | DE-GUP-DT-E-22-465 | 2022-07-28 | 1 | CRS-GUP-DHI-DT-22-650 | 2022-08-20 | NC | DE-GUP-DT-E-22-651 | 2022-09-08 | 2 | CRS-GUP-DHI-DT-22-831 | 2022-09-22 | NC | DE-GUP-DT-E-22-1141 | 2022-12-21 | 3 | CRS-GUP-DHI-DT-22-1389 | 2023-01-03 | RC | DE-GUP-DT-E-23-315 | 2023-03-15 | 4 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC
| GUP | CA03 | P1 | UMA | 181261 |  | GUP-CA03-P1UMA-181261 | STEAM TURBINE BUILDING_PURLIN ARRANGEMENT PLAN | FI | 2022-09-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ST Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-315 | 2023-03-15 | 4 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC | DHI-GUP-DT-22-046 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-206 | 2022-02-20 | NC | DE-GUP-DT-E-22-465 | 2022-07-28 | 1 | CRS-GUP-DHI-DT-22-650 | 2022-08-20 | NC | DE-GUP-DT-E-22-651 | 2022-09-08 | 2 | CRS-GUP-DHI-DT-22-831 | 2022-09-22 | RC | DE-GUP-DT-E-22-1141 | 2022-12-21 | 3 | CRS-GUP-DHI-DT-22-1389 | 2023-01-03 | NC | DE-GUP-DT-E-23-315 | 2023-03-15 | 4 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC
| GUP | CA03 | P1 | UMA | 181262 |  | GUP-CA03-P1UMA-181262 | STEAM TURBINE BUILDING_MISC. PLATFORM FRAMING PLAN & ELEVATION | FI | 2022-09-30 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | ST Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-315 | 2023-03-15 | 1 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC | DE-GUP-DT-E-22-1141 | 2022-12-21 | 0 | CRS-GUP-DHI-DT-22-1389 | 2023-01-03 | NC | DE-GUP-DT-E-23-315 | 2023-03-15 | 1 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC
| GUP | CA03 | P1 | UMA | 181263 |  | GUP-CA03-P1UMA-181263 | STEAM TURBINE BUILDING_STAIR FRAMING PLAN & ELEVATION | FI | 2022-09-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ST Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-315 | 2023-03-15 | 4 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC | DHI-GUP-DT-22-046 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-206 | 2022-02-20 | NC | DE-GUP-DT-E-22-465 | 2022-07-28 | 1 | CRS-GUP-DHI-DT-22-650 | 2022-08-20 | NC | DE-GUP-DT-E-22-651 | 2022-09-08 | 2 | CRS-GUP-DHI-DT-22-831 | 2022-09-22 | RC | DE-GUP-DT-E-22-1141 | 2022-12-21 | 3 | CRS-GUP-DHI-DT-22-1389 | 2023-01-03 | NC | DE-GUP-DT-E-23-315 | 2023-03-15 | 4 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC
| GUP | CA03 | P1 | UMA | 181264 |  | GUP-CA03-P1UMA-181264 | STEAM TURBINE BUILDING_ROOF WALKWAY FRAMING PLAN & ELEVATION | FI | 2022-09-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ST Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-315 | 2023-03-15 | 1 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC | DE-GUP-DT-E-22-1141 | 2022-12-21 | 0 | CRS-GUP-DHI-DT-22-1389 | 2023-01-03 | NC | DE-GUP-DT-E-23-315 | 2023-03-15 | 1 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC
| GUP | CA03 | P1 | UMA | 181265 |  | GUP-CA03-P1UMA-181265 | STEAM TURBINE BUILDING_CRANE GIRDER DETAIL | FI | 2022-07-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ST Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-315 | 2023-03-15 | 4 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC | DHI-GUP-DT-22-046 | 2022-01-28 | 0 | CRS-GUP-DHI-DT-22-206 | 2022-02-20 | NC | DE-GUP-DT-E-22-465 | 2022-07-28 | 1 | CRS-GUP-DHI-DT-22-650 | 2022-08-20 | NC | DE-GUP-DT-E-22-651 | 2022-09-08 | 2 | CRS-GUP-DHI-DT-22-831 | 2022-09-22 | RC | DE-GUP-DT-E-22-1141 | 2022-12-21 | 3 | CRS-GUP-DHI-DT-22-1389 | 2023-01-03 | NC | DE-GUP-DT-E-23-315 | 2023-03-15 | 4 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC
| GUP | CA03 | P1 | UMA | 181266 |  | GUP-CA03-P1UMA-181266 | STEAM TURBINE BUILDING_CONNECTION DETAIL | FI | 2022-07-30 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | ST Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-315 | 2023-03-15 | 4 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC | DHI-GUP-DT-22-046 | 2022-01-28 | A | CRS-GUP-DHI-DT-22-206 | 2022-02-20 | AC | DE-GUP-DT-E-22-465 | 2022-07-28 | B | CRS-GUP-DHI-DT-22-650 | 2022-08-20 | AC | DE-GUP-DT-E-22-651 | 2022-09-08 | 2 | CRS-GUP-DHI-DT-22-831 | 2022-09-22 | NC | DE-GUP-DT-E-22-1141 | 2022-12-21 | 3 | CRS-GUP-DHI-DT-22-1389 | 2023-01-03 | NC | DE-GUP-DT-E-23-315 | 2023-03-15 | 4 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC
| GUP | CA01 | P1 | UMA | 181234 |  | GUP-CA01-P1UMA-181234 | STEAM TURBINE BUILDING_EQUIPMENT FOUNDATION & SLAB OUTLINE PLAN | FA | 2022-09-30 | 2022-12-30 | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | ST Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-1000 | 2023-12-20 | 1 | CRS-GUP-DHI-DT-23-1835 | 2023-04-18 | AA | DE-GUP-DT-E-23-315 | 2023-03-15 | A | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | AC | DE-GUP-DT-E-23-383 | 2023-03-29 | 0(CP) | CRS-GUP-DHI-DT-23-1835 | 2023-04-18 | AA | DE-GUP-DT-E-23-1000 | 2023-12-20 | 1
| GUP | CA02 | P1 | UMA | 181235 |  | GUP-CA02-P1UMA-181235 | STEAM TURBINE BUILDING_EQUIPMENT FOUNDATION RE-BAR DETAIL | FI | 2022-09-30 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | ST Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-383 | 2023-03-29 | 1 | CRS-GUP-DHI-DT-23-1835 | 2023-04-18 | NC | DE-GUP-DT-E-23-315 | 2023-03-15 | 0 | CRS-GUP-DHI-DT-23-1770 | 2023-03-22 | NC | DE-GUP-DT-E-23-383 | 2023-03-29 | 1 | CRS-GUP-DHI-DT-23-1835 | 2023-04-18 | NC
| GUP | CA03 | P1 | UMY | 181281 |  | GUP-CA03-P1UMY-181281 | STEAM TURBINE BUILDING_PLATFORM PLAN & SECTION DETAIL | FI | 2024-03-31 |  | 건축기술2팀(Arch.) | 구남영 | [5 empty] | CCPP | ST Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-24-295 | 2024-12-18 | 3 | 별도 메일접수 24-005 | 2024-11-04 | RC | DE-GUP-DT-E-24-081 | 2024-03-18 | 0 | CRS-GUP-DHI-DT-24-050 | 2024-04-15 | RC | DE-GUP-DT-E-24-134 | 2024-05-16 | 1 | CRS-GUP-DHI-DT-24-065 | 2024-08-02 | RC | DE-GUP-DT-E-24-237 | 2024-09-24 | 2 | 별도 메일접수 24-005 | 2024-11-04 | RC | DE-GUP-DT-E-24-295 | 2024-12-18 | 3
| GUP | CA06 | P1 | UHA | 181301 |  | GUP-CA06-P1UHA-181301 | HRSG BUILDING_CALCULATION SHEET | FA | 2022-02-15 | 2022-09-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | HRSG Building | Arch. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-565 | 2023-05-19 | 2 | CRS-GUP-DHI-DT-23-1981 | 2023-06-08 | AA | DHI-GUP-DT-22-038 | 2022-01-26 | A | CRS-GUP-DHI-DT-21-195 | 2022-02-10 | RC | DHI-GUP-DT-22-131 | 2022-03-24 | B | CRS-GUP-DHI-DT-22-292 | 2022-04-17 | RC | DE-GUP-DT-E-22-284 | 2022-06-10 | C | CRS-GUP-DHI-DT-22-490 | 2022-07-06 | RC | DE-GUP-DT-E-22-425 | 2022-07-20 | D | CRS-GUP-DHI-DT-22-577 | 2022-08-03 | AC | DE-GUP-DT-E-22-525 | 2022-08-19 | E | CRS-GUP-DHI-DT-22-729 | 2022-09-09 | AC | DE-GUP-DT-E-22-858 | 2022-10-26 | 0(CP) | CRS-GUP-DHI-DT-22-1020 | 2022-11-13 | AA | DE-GUP-DT-E-23-091 | 2023-01-30 | 1 | CRS-GUP-DHI-DT-23-1548 | 2023-02-19 | AC | DE-GUP-DT-E-23-565 | 2023-05-19 | 2 | CRS-GUP-DHI-DT-23-1981 | 2023-06-08 | AA
| GUP | CA01 | P1 | UHA | 181331 |  | GUP-CA01-P1UHA-181331 | HRSG BUILDING_FOUNDATION ARRANGEMENT PLAN | FA | 2022-02-15 | 2022-09-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | HRSG Building | Arch. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-565 | 2023-05-19 | 2 | CRS-GUP-DHI-DT-23-1981 | 2023-06-08 | AA | DHI-GUP-DT-22-038 | 2022-01-26 | A | CRS-GUP-DHI-DT-21-195 | 2022-02-10 | RC | DHI-GUP-DT-22-131 | 2022-03-24 | B | CRS-GUP-DHI-DT-22-292 | 2022-04-17 | RC | DE-GUP-DT-E-22-284 | 2022-06-10 | C | CRS-GUP-DHI-DT-22-490 | 2022-07-06 | RC | DE-GUP-DT-E-22-425 | 2022-07-20 | D | CRS-GUP-DHI-DT-22-577 | 2022-08-03 | RC | DE-GUP-DT-E-22-525 | 2022-08-19 | E | CRS-GUP-DHI-DT-22-729 | 2022-09-09 | AC | DE-GUP-DT-E-22-858 | 2022-10-26 | 0(CP) | CRS-GUP-DHI-DT-22-1020 | 2022-11-13 | AA | DE-GUP-DT-E-23-091 | 2023-01-30 | 1 | CRS-GUP-DHI-DT-23-1548 | 2023-02-19 | AA | DE-GUP-DT-E-23-565 | 2023-05-19 | 2 | CRS-GUP-DHI-DT-23-1981 | 2023-06-08 | AA
| GUP | CA02 | P1 | UHA | 181333 |  | GUP-CA02-P1UHA-181333 | HRSG BUILDING_FOUNDATION RE-BAR DETAIL | FI | 2022-02-15 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | HRSG Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-565 | 2023-05-19 | 7 | CRS-GUP-DHI-DT-23-1981 | 2023-06-08 | NC | DHI-GUP-DT-22-038 | 2022-01-26 | 0 | CRS-GUP-DHI-DT-21-195 | 2022-02-10 | RC | DHI-GUP-DT-22-131 | 2022-03-24 | 1 | CRS-GUP-DHI-DT-22-292 | 2022-04-17 | RC | DE-GUP-DT-E-22-284 | 2022-06-10 | 2 | CRS-GUP-DHI-DT-22-490 | 2022-07-06 | NC | DE-GUP-DT-E-22-425 | 2022-07-20 | 3 | CRS-GUP-DHI-DT-22-577 | 2022-08-03 | NC | DE-GUP-DT-E-22-525 | 2022-08-19 | 4 | CRS-GUP-DHI-DT-22-729 | 2022-09-09 | NC | DE-GUP-DT-E-22-858 | 2022-10-26 | 5 | CRS-GUP-DHI-DT-22-1020 | 2022-11-13 | NC | DE-GUP-DT-E-23-091 | 2023-01-30 | 6 | CRS-GUP-DHI-DT-23-1548 | 2023-02-19 | NC | DE-GUP-DT-E-23-565 | 2023-05-19 | 7 | CRS-GUP-DHI-DT-23-1981 | 2023-06-08 | NC
| GUP | CA00 | P1 | UHA | 181311 |  | GUP-CA00-P1UHA-181311 | HRSG BUILDING_DOOR & WINDOW SCHEDULE | FI | 2022-02-15 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | HRSG Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-565 | 2023-05-19 | 7 | CRS-GUP-DHI-DT-23-1981 | 2023-06-08 | NC | DHI-GUP-DT-22-038 | 2022-01-26 | 0 | CRS-GUP-DHI-DT-21-195 | 2022-02-10 | RC | DHI-GUP-DT-22-131 | 2022-03-24 | 1 | CRS-GUP-DHI-DT-22-292 | 2022-04-17 | NC | DE-GUP-DT-E-22-284 | 2022-06-10 | 2 | CRS-GUP-DHI-DT-22-490 | 2022-07-06 | RC | DE-GUP-DT-E-22-425 | 2022-07-20 | 3 | CRS-GUP-DHI-DT-22-577 | 2022-08-03 | NC | DE-GUP-DT-E-22-525 | 2022-08-19 | 4 | CRS-GUP-DHI-DT-22-729 | 2022-09-09 | NC | DE-GUP-DT-E-22-858 | 2022-10-26 | 5 | CRS-GUP-DHI-DT-22-1020 | 2022-11-13 | NC | DE-GUP-DT-E-23-091 | 2023-01-30 | 6 | CRS-GUP-DHI-DT-23-1548 | 2023-02-19 | NC | DE-GUP-DT-E-23-565 | 2023-05-19 | 7 | CRS-GUP-DHI-DT-23-1981 | 2023-06-08 | NC
| GUP | CA00 | P1 | UHA | 181312 |  | GUP-CA00-P1UHA-181312 | HRSG BUILDING_GROUND FLOOR PLAN | FA | 2022-02-15 | 2022-10-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | HRSG Building | Arch. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-717 | 2023-07-25 | 3 | CRS-GUP-DHI-DT-23-1981 | 2023-06-08 | AA | DHI-GUP-DT-22-038 | 2022-01-26 | A | CRS-GUP-DHI-DT-21-195 | 2022-02-10 | AA | DHI-GUP-DT-22-131 | 2022-03-24 | B | CRS-GUP-DHI-DT-22-292 | 2022-04-17 | AA | DE-GUP-DT-E-22-284 | 2022-06-10 | C | CRS-GUP-DHI-DT-22-490 | 2022-07-06 | AC | DE-GUP-DT-E-22-425 | 2022-07-20 | D | CRS-GUP-DHI-DT-22-577 | 2022-08-03 | AC | DE-GUP-DT-E-22-525 | 2022-08-19 | E | CRS-GUP-DHI-DT-22-729 | 2022-09-09 | AC | DE-GUP-DT-E-22-858 | 2022-10-26 | 0(CP) | CRS-GUP-DHI-DT-22-1020 | 2022-11-13 | AC | DE-GUP-DT-E-23-091 | 2023-01-30 | 1(CP) | CRS-GUP-DHI-DT-23-1548 | 2023-02-19 | AC | DE-GUP-DT-E-23-565 | 2023-05-19 | 2(CP) | CRS-GUP-DHI-DT-23-1981 | 2023-06-08 | AA | DE-GUP-DT-E-23-717 | 2023-07-25 | 3
| GUP | CA00 | P1 | UHA | 181313 |  | GUP-CA00-P1UHA-181313 | HRSG BUILDING_ROOF PLAN | FA | 2022-02-15 | 2022-10-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | HRSG Building | Arch. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-717 | 2023-07-25 | 2 | CRS-GUP-DHI-DT-23-1981 | 2023-06-08 | AA | DHI-GUP-DT-22-038 | 2022-01-26 | A | CRS-GUP-DHI-DT-21-195 | 2022-02-10 | AC | DHI-GUP-DT-22-131 | 2022-03-24 | B | CRS-GUP-DHI-DT-22-292 | 2022-04-17 | AC | DE-GUP-DT-E-22-284 | 2022-06-10 | C | CRS-GUP-DHI-DT-22-490 | 2022-07-06 | RC | DE-GUP-DT-E-22-425 | 2022-07-20 | D | CRS-GUP-DHI-DT-22-577 | 2022-08-03 | AC | DE-GUP-DT-E-22-525 | 2022-08-19 | E | CRS-GUP-DHI-DT-22-729 | 2022-09-09 | RC | DE-GUP-DT-E-22-858 | 2022-10-26 | F | CRS-GUP-DHI-DT-22-1020 | 2022-11-13 | AC | DE-GUP-DT-E-23-091 | 2023-01-30 | 0(CP) | CRS-GUP-DHI-DT-23-1548 | 2023-02-19 | AC | DE-GUP-DT-E-23-565 | 2023-05-19 | 1(CP) | CRS-GUP-DHI-DT-23-1981 | 2023-06-08 | AA | DE-GUP-DT-E-23-717 | 2023-07-25 | 2
| GUP | CA00 | P1 | UHA | 181314 |  | GUP-CA00-P1UHA-181314 | HRSG BUILDING_MAIN SECTION | FA | 2022-02-15 | 2022-10-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | HRSG Building | Arch. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-565 | 2023-05-19 | 1 | CRS-GUP-DHI-DT-23-1981 | 2023-06-08 | AA | DHI-GUP-DT-22-038 | 2022-01-26 | A | CRS-GUP-DHI-DT-21-195 | 2022-02-10 | AC | DHI-GUP-DT-22-131 | 2022-03-24 | B | CRS-GUP-DHI-DT-22-292 | 2022-04-17 | AC | DE-GUP-DT-E-22-284 | 2022-06-10 | C | CRS-GUP-DHI-DT-22-490 | 2022-07-06 | AC | DE-GUP-DT-E-22-425 | 2022-07-20 | D | CRS-GUP-DHI-DT-22-577 | 2022-08-03 | AC | DE-GUP-DT-E-22-525 | 2022-08-19 | E | CRS-GUP-DHI-DT-22-729 | 2022-09-09 | RC | DE-GUP-DT-E-22-858 | 2022-10-26 | F | CRS-GUP-DHI-DT-22-1020 | 2022-11-13 | AA | DE-GUP-DT-E-23-091 | 2023-01-30 | 0 | CRS-GUP-DHI-DT-23-1548 | 2023-02-19 | AC | DE-GUP-DT-E-23-565 | 2023-05-19 | 1 | CRS-GUP-DHI-DT-23-1981 | 2023-06-08 | AA
| GUP | CA00 | P1 | UHA | 181315 |  | GUP-CA00-P1UHA-181315 | HRSG BUILDING_SIDE ELEVATION | FA | 2022-02-15 | 2022-10-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | HRSG Building | Arch. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-717 | 2023-07-25 | 2 | CRS-GUP-DHI-DT-23-1981 | 2023-06-08 | AA | DHI-GUP-DT-22-038 | 2022-01-26 | A | CRS-GUP-DHI-DT-21-195 | 2022-02-10 | AC | DHI-GUP-DT-22-131 | 2022-03-24 | B | CRS-GUP-DHI-DT-22-292 | 2022-04-17 | AC | DE-GUP-DT-E-22-284 | 2022-06-10 | C | CRS-GUP-DHI-DT-22-490 | 2022-07-06 | AC | DE-GUP-DT-E-22-425 | 2022-07-20 | D | CRS-GUP-DHI-DT-22-577 | 2022-08-03 | AC | DE-GUP-DT-E-22-525 | 2022-08-19 | E | CRS-GUP-DHI-DT-22-729 | 2022-09-09 | RC | DE-GUP-DT-E-22-858 | 2022-10-26 | F | CRS-GUP-DHI-DT-22-1020 | 2022-11-13 | AC | DE-GUP-DT-E-23-091 | 2023-01-30 | 0(CP) | CRS-GUP-DHI-DT-23-1548 | 2023-02-19 | AC | DE-GUP-DT-E-23-565 | 2023-05-19 | 1 | CRS-GUP-DHI-DT-23-1981 | 2023-06-08 | AA | DE-GUP-DT-E-23-717 | 2023-07-25 | 2
| GUP | CA00 | P1 | UHA | 181319 |  | GUP-CA00-P1UHA-181319 | HRSG BUILDING_WALL SECTION | FI | 2022-02-15 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | HRSG Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-717 | 2023-07-25 | 8 | CRS-GUP-DHI-DT-23-1981 | 2023-06-08 | NC | DHI-GUP-DT-22-038 | 2022-01-26 | 0 | CRS-GUP-DHI-DT-21-195 | 2022-02-10 | RC | DHI-GUP-DT-22-131 | 2022-03-24 | 1 | CRS-GUP-DHI-DT-22-292 | 2022-04-17 | NC | DE-GUP-DT-E-22-284 | 2022-06-10 | 2 | CRS-GUP-DHI-DT-22-490 | 2022-07-06 | RC | DE-GUP-DT-E-22-425 | 2022-07-20 | 3 | CRS-GUP-DHI-DT-22-577 | 2022-08-03 | NC | DE-GUP-DT-E-22-525 | 2022-08-19 | 4 | CRS-GUP-DHI-DT-22-729 | 2022-09-09 | NC | DE-GUP-DT-E-22-858 | 2022-10-26 | 5 | CRS-GUP-DHI-DT-22-1020 | 2022-11-13 | NC | DE-GUP-DT-E-23-091 | 2023-01-30 | 6 | CRS-GUP-DHI-DT-23-1548 | 2023-02-19 | NC | DE-GUP-DT-E-23-565 | 2023-05-19 | 7 | CRS-GUP-DHI-DT-23-1981 | 2023-06-08 | NC | DE-GUP-DT-E-23-717 | 2023-07-25 | 8
| GUP | CA03 | P1 | UHA | 181351 |  | GUP-CA03-P1UHA-181351 | HRSG BUILDING_COLUMN ARRANGEMENT PLAN | FI | 2022-02-15 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | HRSG Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-135 | 2023-02-07 | 3 | CRS-GUP-DHI-DT-23-1568 | 2023-02-23 | NC | DHI-GUP-DT-22-038 | 2022-01-26 | 0 | CRS-GUP-DHI-DT-21-195 | 2022-02-10 | NC | DE-GUP-DT-E-22-287 | 2022-06-13 | 1 | CRS-GUP-DHI-DT-22-492 | 2022-07-06 | RC | DE-GUP-DT-E-22-443 | 2022-07-25 | 2 | CRS-GUP-DHI-DT-22-635 | 2022-08-18 | NC | DE-GUP-DT-E-23-135 | 2023-02-07 | 3 | CRS-GUP-DHI-DT-23-1568 | 2023-02-23 | NC
| GUP | CA03 | P1 | UHA | 181352 |  | GUP-CA03-P1UHA-181352 | HRSG BUILDING_COLUMN SCHEDULE | FI | 2022-02-15 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | HRSG Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-135 | 2023-02-07 | 3 | CRS-GUP-DHI-DT-23-1568 | 2023-02-23 | NC | DHI-GUP-DT-22-038 | 2022-01-26 | 0 | CRS-GUP-DHI-DT-21-195 | 2022-02-10 | RC | DE-GUP-DT-E-22-287 | 2022-06-13 | 1 | CRS-GUP-DHI-DT-22-492 | 2022-07-06 | RC | DE-GUP-DT-E-22-443 | 2022-07-25 | 2 | CRS-GUP-DHI-DT-22-635 | 2022-08-18 | NC | DE-GUP-DT-E-23-135 | 2023-02-07 | 3 | CRS-GUP-DHI-DT-23-1568 | 2023-02-23 | NC
| GUP | CA03 | P1 | UHA | 181353 |  | GUP-CA03-P1UHA-181353 | HRSG BUILDING_GROUND FLOOR FRAMING PLAN | FI | 2022-02-15 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | HRSG Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-135 | 2023-02-07 | 3 | CRS-GUP-DHI-DT-23-1568 | 2023-02-23 | NC | DHI-GUP-DT-22-038 | 2022-01-26 | 0 | CRS-GUP-DHI-DT-21-195 | 2022-02-10 | RC | DE-GUP-DT-E-22-287 | 2022-06-13 | 1 | CRS-GUP-DHI-DT-22-492 | 2022-07-06 | RC | DE-GUP-DT-E-22-443 | 2022-07-25 | 2 | CRS-GUP-DHI-DT-22-635 | 2022-08-18 | NC | DE-GUP-DT-E-23-135 | 2023-02-07 | 3 | CRS-GUP-DHI-DT-23-1568 | 2023-02-23 | NC
| GUP | CA03 | P1 | UHA | 181354 |  | GUP-CA03-P1UHA-181354 | HRSG BUILDING_PIPE SUPPORT FRAMING PLAN | FI | 2022-02-15 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | HRSG Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-706 | 2023-07-20 | 4 | CRS-GUP-DHI-DT-23-2083 | 2023-08-02 | NC | DHI-GUP-DT-22-038 | 2022-01-26 | 0 | CRS-GUP-DHI-DT-21-195 | 2022-02-10 | NC | DE-GUP-DT-E-22-287 | 2022-06-13 | 1 | CRS-GUP-DHI-DT-22-492 | 2022-07-06 | RC | DE-GUP-DT-E-22-443 | 2022-07-25 | 2 | CRS-GUP-DHI-DT-22-635 | 2022-08-18 | NC | DE-GUP-DT-E-23-135 | 2023-02-07 | 3 | CRS-GUP-DHI-DT-23-1568 | 2023-02-23 | NC | DE-GUP-DT-E-23-706 | 2023-07-20 | 4 | CRS-GUP-DHI-DT-23-2083 | 2023-08-02 | NC
| GUP | CA03 | P1 | UHA | 181355 |  | GUP-CA03-P1UHA-181355 | HRSG BUILDING_ROOF FRAMING PLAN | FI | 2022-02-15 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | HRSG Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-135 | 2023-02-07 | 3 | CRS-GUP-DHI-DT-23-1568 | 2023-02-23 | NC | DHI-GUP-DT-22-038 | 2022-01-26 | 0 | CRS-GUP-DHI-DT-21-195 | 2022-02-10 | RC | DE-GUP-DT-E-22-287 | 2022-06-13 | 1 | CRS-GUP-DHI-DT-22-492 | 2022-07-06 | RC | DE-GUP-DT-E-22-443 | 2022-07-25 | 2 | CRS-GUP-DHI-DT-22-635 | 2022-08-18 | NC | DE-GUP-DT-E-23-135 | 2023-02-07 | 3 | CRS-GUP-DHI-DT-23-1568 | 2023-02-23 | NC
| GUP | CA03 | P1 | UHA | 181356 |  | GUP-CA03-P1UHA-181356 | HRSG BUILDING_LINE FRAMING ELEVATION | FI | 2022-02-15 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | HRSG Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-135 | 2023-02-07 | 3 | CRS-GUP-DHI-DT-23-1568 | 2023-02-23 | NC | DHI-GUP-DT-22-038 | 2022-01-26 | 0 | CRS-GUP-DHI-DT-21-195 | 2022-02-10 | NC | DE-GUP-DT-E-22-287 | 2022-06-13 | 1 | CRS-GUP-DHI-DT-22-492 | 2022-07-06 | RC | DE-GUP-DT-E-22-443 | 2022-07-25 | 2 | CRS-GUP-DHI-DT-22-635 | 2022-08-18 | NC | DE-GUP-DT-E-23-135 | 2023-02-07 | 3 | CRS-GUP-DHI-DT-23-1568 | 2023-02-23 | NC
| GUP | CA03 | P1 | UHA | 181357 |  | GUP-CA03-P1UHA-181357 | HRSG BUILDING_ROW FRAMING ELEVATION | FI | 2022-02-15 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | HRSG Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-135 | 2023-02-07 | 3 | CRS-GUP-DHI-DT-23-1568 | 2023-02-23 | NC | DHI-GUP-DT-22-038 | 2022-01-26 | 0 | CRS-GUP-DHI-DT-21-195 | 2022-02-10 | NC | DE-GUP-DT-E-22-287 | 2022-06-13 | 1 | CRS-GUP-DHI-DT-22-492 | 2022-07-06 | RC | DE-GUP-DT-E-22-443 | 2022-07-25 | 2 | CRS-GUP-DHI-DT-22-635 | 2022-08-18 | NC | DE-GUP-DT-E-23-135 | 2023-02-07 | 3 | CRS-GUP-DHI-DT-23-1568 | 2023-02-23 | NC
| GUP | CA03 | P1 | UHA | 181359 |  | GUP-CA03-P1UHA-181359 | HRSG BUILDING_GIRT LINE ELEVATION | FI | 2022-08-28 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | HRSG Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-135 | 2023-02-07 | 1 | CRS-GUP-DHI-DT-23-1568 | 2023-02-23 | NC | DE-GUP-DT-E-22-443 | 2022-07-25 | 0 | CRS-GUP-DHI-DT-22-635 | 2022-08-18 | NC | DE-GUP-DT-E-23-135 | 2023-02-07 | 1 | CRS-GUP-DHI-DT-23-1568 | 2023-02-23 | NC
| GUP | CA03 | P1 | UHA | 181360 |  | GUP-CA03-P1UHA-181360 | HRSG BUILDING_GIRT ROW ELEVATION | FI | 2022-08-28 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | HRSG Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-135 | 2023-02-07 | 1 | CRS-GUP-DHI-DT-23-1568 | 2023-02-23 | NC | DE-GUP-DT-E-22-443 | 2022-07-25 | 0 | CRS-GUP-DHI-DT-22-635 | 2022-08-18 | NC | DE-GUP-DT-E-23-135 | 2023-02-07 | 1 | CRS-GUP-DHI-DT-23-1568 | 2023-02-23 | NC
| GUP | CA03 | P1 | UHA | 181361 |  | GUP-CA03-P1UHA-181361 | HRSG BUILDING_PURLIN ARRANGEMENT PLAN | FI | 2022-08-28 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | HRSG Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-135 | 2023-02-07 | 1 | CRS-GUP-DHI-DT-23-1568 | 2023-02-23 | NC | DE-GUP-DT-E-22-443 | 2022-07-25 | 0 | CRS-GUP-DHI-DT-22-635 | 2022-08-18 | NC | DE-GUP-DT-E-23-135 | 2023-02-07 | 1 | CRS-GUP-DHI-DT-23-1568 | 2023-02-23 | NC
| GUP | CA03 | P1 | UHA | 181364 |  | GUP-CA03-P1UHA-181364 | HRSG BUILDING_ROOF WALKWAY FRAMING PLAN & ELEVATION | FI | 2022-08-28 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | HRSG Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-706 | 2023-07-20 | 1 | CRS-GUP-DHI-DT-23-2083 | 2023-08-02 | NC | DE-GUP-DT-E-23-135 | 2023-02-07 | 0 | CRS-GUP-DHI-DT-23-1568 | 2023-02-23 | RC | DE-GUP-DT-E-23-706 | 2023-07-20 | 1 | CRS-GUP-DHI-DT-23-2083 | 2023-08-02 | NC
| GUP | CA03 | P1 | UHA | 181365 |  | GUP-CA03-P1UHA-181365 | HRSG BUILDING_CONNECTION DETAIL | FI | 2022-08-28 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | HRSG Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-706 | 2023-07-20 | 1 | CRS-GUP-DHI-DT-23-2083 | 2023-08-02 | NC | DE-GUP-DT-E-23-135 | 2023-02-07 | A | CRS-GUP-DHI-DT-23-1568 | 2023-02-23 | RC | DE-GUP-DT-E-23-706 | 2023-07-20 | 1 | CRS-GUP-DHI-DT-23-2083 | 2023-08-02 | NC
| GUP | CA01 | P1 | UHA | 181334 |  | GUP-CA01-P1UHA-181334 | HRSG BUILDING_EQUIPMENT FOUNDATION & SLAB OUTLINE PLAN | FA | 2022-08-28 | 2022-12-27 | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | HRSG Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-565 | 2023-05-19 | 1 | CRS-GUP-DHI-DT-23-1981 | 2023-06-08 | AA | DE-GUP-DT-E-22-284 | 2022-06-10 | A | CRS-GUP-DHI-DT-22-490 | 2022-07-06 | RC | DE-GUP-DT-E-22-425 | 2022-07-20 | B | CRS-GUP-DHI-DT-22-577 | 2022-08-03 | RC | DE-GUP-DT-E-22-525 | 2022-08-19 | C | CRS-GUP-DHI-DT-22-729 | 2022-09-09 | RC | DE-GUP-DT-E-22-858 | 2022-10-26 | D | CRS-GUP-DHI-DT-22-1020 | 2022-11-13 | AA | DE-GUP-DT-E-23-091 | 2023-01-30 | 0 | CRS-GUP-DHI-DT-23-1548 | 2023-02-19 | AA | DE-GUP-DT-E-23-565 | 2023-05-19 | 1 | CRS-GUP-DHI-DT-23-1981 | 2023-06-08 | AA
| GUP | CA02 | P1 | UHA | 181335 |  | GUP-CA02-P1UHA-181335 | HRSG BUILDING_EQUIPMENT FOUNDATION RE-BAR DETAIL | FI | 2022-08-28 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | HRSG Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-565 | 2023-05-19 | 5 | CRS-GUP-DHI-DT-23-1981 | 2023-06-08 | NC | DE-GUP-DT-E-22-284 | 2022-06-10 | 0 | CRS-GUP-DHI-DT-22-490 | 2022-07-06 | NC | DE-GUP-DT-E-22-425 | 2022-07-20 | 1 | CRS-GUP-DHI-DT-22-577 | 2022-08-03 | RC | DE-GUP-DT-E-22-525 | 2022-08-19 | 2 | CRS-GUP-DHI-DT-22-729 | 2022-09-09 | NC | DE-GUP-DT-E-22-858 | 2022-10-26 | 3 | CRS-GUP-DHI-DT-22-1020 | 2022-11-13 | NC | DE-GUP-DT-E-23-091 | 2023-01-30 | 4 | CRS-GUP-DHI-DT-23-1548 | 2023-02-19 | NC | DE-GUP-DT-E-23-565 | 2023-05-19 | 5 | CRS-GUP-DHI-DT-23-1981 | 2023-06-08 | NC
| GUP | CA01 | P1 | UHA | 181336 |  | GUP-CA01-P1UHA-181336 | HRSG BUILDING_STRUCTURAL MISC. DETAIL | FI | 2022-08-28 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | HRSG Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-565 | 2023-05-19 | 5 | CRS-GUP-DHI-DT-23-1981 | 2023-06-08 | NC | DE-GUP-DT-E-22-284 | 2022-06-10 | 0 | CRS-GUP-DHI-DT-22-490 | 2022-07-06 | NC | DE-GUP-DT-E-22-425 | 2022-07-20 | 1 | CRS-GUP-DHI-DT-22-577 | 2022-08-03 | NC | DE-GUP-DT-E-22-525 | 2022-08-19 | 2 | CRS-GUP-DHI-DT-22-729 | 2022-09-09 | NC | DE-GUP-DT-E-22-858 | 2022-10-26 | 3 | CRS-GUP-DHI-DT-22-1020 | 2022-11-13 | NC | DE-GUP-DT-E-23-091 | 2023-01-30 | 4 | CRS-GUP-DHI-DT-23-1548 | 2023-02-19 | NC | DE-GUP-DT-E-23-565 | 2023-05-19 | 5 | CRS-GUP-DHI-DT-23-1981 | 2023-06-08 | NC
| GUP | CA06 | P1 | UCB | 181401 |  | GUP-CA06-P1UCB-181401 | CONTROL & ELECTRICAL BUILDING_CALCULATION SHEET | FA | 2021-10-28 | 2022-04-11 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | C&E Building | Arch. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-963 | 2023-12-01 | 3 | CRS-GUP-DHI-DT-23-1983 | 2023-06-08 | AA | DHI-GUP-DT-21-017 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-005 | 2021-09-27 | RR | DHI-GUP-DT-21-079 | 2021-10-29 | B | CRS-GUP-DHI-DT-21-055 | 2021-11-07 | RC | DHI-GUP-DT-21-163 | 2021-12-09 | C | CRS-GUP-DHI-DT-21-083 | 2021-12-22 | RC | DHI-GUP-DT-22-013 | 2022-01-11 | D | CRS-GUP-DHI-DT-21-164 | 2022-01-18 | RC | DHI-GUP-DT-22-035 | 2022-01-25 | E | CRS-GUP-DHI-DT-21-194 | 2022-02-10 | RC | DHI-GUP-DT-22-086 | 2022-02-24 | F | CRS-GUP-DHI-DT-22-223 | 2022-03-02 | RC | DHI-GUP-DT-22-098 | 2022-03-04 | G | CRS-GUP-DHI-DT-22-229 | 2022-03-05 | AC | DHI-GUP-DT-22-200 | 2022-05-04 | H | CRS-GUP-DHI-DT-22-363 | 2022-05-23 | AC | DE-GUP-DT-E-22-857 | 2022-10-26 | 0(CP) | CRS-GUP-DHI-DT-22-1019 | 2022-11-13 | AA | DE-GUP-DT-E-23-074 | 2023-01-26 | 1 | CRS-GUP-DHI-DT-23-1535 | 2023-02-15 | AC | DE-GUP-DT-E-23-573 | 2023-05-22 | 2 | CRS-GUP-DHI-DT-23-1983 | 2023-06-08 | AA | DE-GUP-DT-E-23-963 | 2023-12-01 | 3
| GUP | CA01 | P1 | UCB | 181431 |  | GUP-CA01-P1UCB-181431 | CONTROL & ELECTRICAL BUILDING_FOUNDATION ARRANGEMENT PLAN | FA | 2021-10-28 | 2022-03-11 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | C&E Building | Arch. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-573 | 2023-05-22 | 3 | CRS-GUP-DHI-DT-23-1983 | 2023-06-08 | AA | DHI-GUP-DT-21-017 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-005 | 2021-09-27 | RR | DHI-GUP-DT-21-079 | 2021-10-29 | B | CRS-GUP-DHI-DT-21-055 | 2021-11-07 | RC | DHI-GUP-DT-21-163 | 2021-12-09 | C | CRS-GUP-DHI-DT-21-083 | 2021-12-22 | RC | DHI-GUP-DT-22-013 | 2022-01-11 | D | CRS-GUP-DHI-DT-21-164 | 2022-01-18 | RC | DHI-GUP-DT-22-035 | 2022-01-25 | E | CRS-GUP-DHI-DT-21-194 | 2022-02-10 | RC | DHI-GUP-DT-22-086 | 2022-02-24 | F | CRS-GUP-DHI-DT-22-223 | 2022-03-02 | RC | DHI-GUP-DT-22-098 | 2022-03-04 | G | CRS-GUP-DHI-DT-22-229 | 2022-03-05 | AC | DHI-GUP-DT-22-200 | 2022-05-04 | 0(CP) | CRS-GUP-DHI-DT-22-363 | 2022-05-23 | RC | DE-GUP-DT-E-22-857 | 2022-10-26 | 1(CP) | CRS-GUP-DHI-DT-22-1019 | 2022-11-13 | AA | DE-GUP-DT-E-23-074 | 2023-01-26 | 2 | CRS-GUP-DHI-DT-23-1535 | 2023-02-15 | AA | DE-GUP-DT-E-23-573 | 2023-05-22 | 3 | CRS-GUP-DHI-DT-23-1983 | 2023-06-08 | AA
| GUP | CA02 | P1 | UCB | 181432 |  | GUP-CA02-P1UCB-181432 | CONTROL & ELECTRICAL BUILDING_FOUNDATION RE-BAR SCHEDULE | FI | 2021-10-28 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-573 | 2023-05-22 | 10 | CRS-GUP-DHI-DT-23-1983 | 2023-06-08 | NC | DHI-GUP-DT-21-017 | 2021-09-07 | 0 | CRS-GUP-DHI-DT-21-005 | 2021-09-27 | RR | DHI-GUP-DT-21-079 | 2021-10-29 | 1 | CRS-GUP-DHI-DT-21-055 | 2021-11-07 | RC | DHI-GUP-DT-21-163 | 2021-12-09 | 2 | CRS-GUP-DHI-DT-21-083 | 2021-12-22 | I | DHI-GUP-DT-22-013 | 2022-01-11 | 3 | CRS-GUP-DHI-DT-21-164 | 2022-01-18 | RC | DHI-GUP-DT-22-035 | 2022-01-25 | 4 | CRS-GUP-DHI-DT-21-194 | 2022-02-10 | RC | DHI-GUP-DT-22-086 | 2022-02-24 | 5 | CRS-GUP-DHI-DT-22-223 | 2022-03-02 | RC | DHI-GUP-DT-22-098 | 2022-03-04 | 6 | CRS-GUP-DHI-DT-22-229 | 2022-03-05 | AC | DHI-GUP-DT-22-200 | 2022-05-04 | 7 | CRS-GUP-DHI-DT-22-363 | 2022-05-23 | RC | DE-GUP-DT-E-22-857 | 2022-10-26 | 8 | CRS-GUP-DHI-DT-22-1037 | 2022-11-16 | NC | DE-GUP-DT-E-23-074 | 2023-01-26 | 9 | CRS-GUP-DHI-DT-23-1535 | 2023-02-15 | NC | DE-GUP-DT-E-23-573 | 2023-05-22 | 10 | CRS-GUP-DHI-DT-23-1983 | 2023-06-08 | NC
| GUP | CA00 | P1 | UCB | 181411 |  | GUP-CA00-P1UCB-181411 | CONTROL & ELECTRICAL BUILDING_INTERIOR FINISH SCHEDULE | FA | 2021-10-28 | 2022-03-11 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-963 | 2023-12-01 | 4 | CRS-GUP-DHI-DT-23-1983 | 2023-06-08 | AA | DHI-GUP-DT-21-017 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-005 | 2021-09-27 | RR | DHI-GUP-DT-21-079 | 2021-10-29 | B | CRS-GUP-DHI-DT-21-055 | 2021-11-07 | RC | DHI-GUP-DT-21-163 | 2021-12-09 | C | CRS-GUP-DHI-DT-21-083 | 2021-12-22 | AC | DHI-GUP-DT-22-013 | 2022-01-11 | D | CRS-GUP-DHI-DT-21-164 | 2022-01-18 | AA | DHI-GUP-DT-22-035 | 2022-01-25 | E | CRS-GUP-DHI-DT-21-194 | 2022-02-10 | AA | DHI-GUP-DT-22-086 | 2022-02-24 | F | CRS-GUP-DHI-DT-22-223 | 2022-03-02 | AA | DHI-GUP-DT-22-098 | 2022-03-04 | G | CRS-GUP-DHI-DT-22-229 | 2022-03-05 | AA | DHI-GUP-DT-22-200 | 2022-05-04 | 0 | CRS-GUP-DHI-DT-22-363 | 2022-05-23 | AC | DE-GUP-DT-E-22-857 | 2022-10-26 | 1 | CRS-GUP-DHI-DT-22-1019 | 2022-11-13 | AA | DE-GUP-DT-E-23-074 | 2023-01-26 | 2 | CRS-GUP-DHI-DT-23-1535 | 2023-02-15 | AA | DE-GUP-DT-E-23-573 | 2023-05-22 | 3 | CRS-GUP-DHI-DT-23-1983 | 2023-06-08 | AA | DE-GUP-DT-E-23-963 | 2023-12-01 | 4
| GUP | CA00 | P1 | UCB | 181412 |  | GUP-CA00-P1UCB-181412 | CONTROL & ELECTRICAL BUILDING_DOOR & WINDOW SCHEDULE | FA | 2021-10-28 | 2022-03-30 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-963 | 2023-12-01 | 4 | CRS-GUP-DHI-DT-23-1983 | 2023-06-08 | AA | DHI-GUP-DT-21-017 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-005 | 2021-09-27 | RR | DHI-GUP-DT-21-079 | 2021-10-29 | B | CRS-GUP-DHI-DT-21-055 | 2021-11-07 | RC | DHI-GUP-DT-21-163 | 2021-12-09 | C | CRS-GUP-DHI-DT-21-083 | 2021-12-22 | AC | DHI-GUP-DT-22-013 | 2022-01-11 | D | CRS-GUP-DHI-DT-21-164 | 2022-01-18 | AC | DHI-GUP-DT-22-035 | 2022-01-25 | E | CRS-GUP-DHI-DT-21-194 | 2022-02-10 | AA | DHI-GUP-DT-22-086 | 2022-02-24 | F | CRS-GUP-DHI-DT-22-223 | 2022-03-02 | AA | DHI-GUP-DT-22-098 | 2022-03-04 | G | CRS-GUP-DHI-DT-22-229 | 2022-03-05 | AA | DHI-GUP-DT-22-200 | 2022-05-04 | 0 | CRS-GUP-DHI-DT-22-363 | 2022-05-23 | AC | DE-GUP-DT-E-22-857 | 2022-10-26 | 1 | CRS-GUP-DHI-DT-22-1019 | 2022-11-13 | AA | DE-GUP-DT-E-23-074 | 2023-01-26 | 2 | CRS-GUP-DHI-DT-23-1535 | 2023-02-15 | AA | DE-GUP-DT-E-23-573 | 2023-05-22 | 3 | CRS-GUP-DHI-DT-23-1983 | 2023-06-08 | AA | DE-GUP-DT-E-23-963 | 2023-12-01 | 4
| GUP | CA00 | P1 | UCB | 181413 |  | GUP-CA00-P1UCB-181413 | CONTROL & ELECTRICAL BUILDING_GROUND FLOOR PLAN | FA | 2021-10-28 | 2022-03-11 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | C&E Building | Arch. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-573 | 2023-05-22 | 3 | CRS-GUP-DHI-DT-23-1983 | 2023-06-08 | AA | DHI-GUP-DT-21-017 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-005 | 2021-09-27 | RR | DHI-GUP-DT-21-079 | 2021-10-29 | B | CRS-GUP-DHI-DT-21-055 | 2021-11-07 | RC | DHI-GUP-DT-21-163 | 2021-12-09 | C | CRS-GUP-DHI-DT-21-083 | 2021-12-22 | AC | DHI-GUP-DT-22-013 | 2022-01-11 | D | CRS-GUP-DHI-DT-21-164 | 2022-01-18 | AA | DHI-GUP-DT-22-035 | 2022-01-25 | E | CRS-GUP-DHI-DT-21-194 | 2022-02-10 | AA | DHI-GUP-DT-22-086 | 2022-02-24 | F | CRS-GUP-DHI-DT-22-223 | 2022-03-02 | AA | DHI-GUP-DT-22-098 | 2022-03-04 | G | CRS-GUP-DHI-DT-22-229 | 2022-03-05 | AA | DHI-GUP-DT-22-200 | 2022-05-04 | 0 | CRS-GUP-DHI-DT-22-363 | 2022-05-23 | AC | DE-GUP-DT-E-22-857 | 2022-10-26 | 1 | CRS-GUP-DHI-DT-22-1019 | 2022-11-13 | AA | DE-GUP-DT-E-23-074 | 2023-01-26 | 2 | CRS-GUP-DHI-DT-23-1535 | 2023-02-15 | AC | DE-GUP-DT-E-23-573 | 2023-05-22 | 3 | CRS-GUP-DHI-DT-23-1983 | 2023-06-08 | AA
| GUP | CA00 | P1 | UCB | 181414 |  | GUP-CA00-P1UCB-181414 | CONTROL & ELECTRICAL BUILDING_SECOND FLOOR PLAN | FA | 2021-10-28 | 2022-03-11 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | C&E Building | Arch. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-963 | 2023-12-01 | 4 | CRS-GUP-DHI-DT-23-1983 | 2023-06-08 | AA | DHI-GUP-DT-21-017 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-005 | 2021-09-27 | RR | DHI-GUP-DT-21-079 | 2021-10-29 | B | CRS-GUP-DHI-DT-21-055 | 2021-11-07 | RC | DHI-GUP-DT-21-163 | 2021-12-09 | C | CRS-GUP-DHI-DT-21-083 | 2021-12-22 | AC | DHI-GUP-DT-22-013 | 2022-01-11 | D | CRS-GUP-DHI-DT-21-164 | 2022-01-18 | AA | DHI-GUP-DT-22-035 | 2022-01-25 | E | CRS-GUP-DHI-DT-21-194 | 2022-02-10 | AA | DHI-GUP-DT-22-086 | 2022-02-24 | F | CRS-GUP-DHI-DT-22-223 | 2022-03-02 | AA | DHI-GUP-DT-22-098 | 2022-03-04 | G | CRS-GUP-DHI-DT-22-229 | 2022-03-05 | AA | DHI-GUP-DT-22-200 | 2022-05-04 | 0 | CRS-GUP-DHI-DT-22-363 | 2022-05-23 | AC | DE-GUP-DT-E-22-857 | 2022-10-26 | 1 | CRS-GUP-DHI-DT-22-1019 | 2022-11-13 | AA | DE-GUP-DT-E-23-074 | 2023-01-26 | 2 | CRS-GUP-DHI-DT-23-1535 | 2023-02-15 | AC | DE-GUP-DT-E-23-573 | 2023-05-22 | 3 | CRS-GUP-DHI-DT-23-1983 | 2023-06-08 | AA | DE-GUP-DT-E-23-963 | 2023-12-01 | 4
| GUP | CA00 | P1 | UCB | 181415 |  | GUP-CA00-P1UCB-181415 | CONTROL & ELECTRICAL BUILDING_THIRD FLOOR PLAN | FA | 2021-10-28 | 2022-03-11 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | C&E Building | Arch. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-963 | 2023-12-01 | 4 | CRS-GUP-DHI-DT-23-1983 | 2023-06-08 | AA | DHI-GUP-DT-21-017 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-005 | 2021-09-27 | RR | DHI-GUP-DT-21-079 | 2021-10-29 | B | CRS-GUP-DHI-DT-21-055 | 2021-11-07 | RC | DHI-GUP-DT-21-163 | 2021-12-09 | C | CRS-GUP-DHI-DT-21-083 | 2021-12-22 | AC | DHI-GUP-DT-22-013 | 2022-01-11 | D | CRS-GUP-DHI-DT-21-164 | 2022-01-18 | AA | DHI-GUP-DT-22-035 | 2022-01-25 | E | CRS-GUP-DHI-DT-21-194 | 2022-02-10 | AA | DHI-GUP-DT-22-086 | 2022-02-24 | F | CRS-GUP-DHI-DT-22-223 | 2022-03-02 | AA | DHI-GUP-DT-22-098 | 2022-03-04 | G | CRS-GUP-DHI-DT-22-229 | 2022-03-05 | AA | DHI-GUP-DT-22-200 | 2022-05-04 | 0 | CRS-GUP-DHI-DT-22-363 | 2022-05-23 | AC | DE-GUP-DT-E-22-857 | 2022-10-26 | 1 | CRS-GUP-DHI-DT-22-1019 | 2022-11-13 | AA | DE-GUP-DT-E-23-074 | 2023-01-26 | 2 | CRS-GUP-DHI-DT-23-1535 | 2023-02-15 | AC | DE-GUP-DT-E-23-573 | 2023-05-22 | 3 | CRS-GUP-DHI-DT-23-1983 | 2023-06-08 | AA | DE-GUP-DT-E-23-963 | 2023-12-01 | 4
| GUP | CA00 | P1 | UCB | 181416 |  | GUP-CA00-P1UCB-181416 | CONTROL & ELECTRICAL BUILDING_ROOF PLAN | FA | 2021-10-28 | 2022-03-11 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | C&E Building | Arch. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-963 | 2023-12-01 | 4 | CRS-GUP-DHI-DT-23-1983 | 2023-06-08 | AA | DHI-GUP-DT-21-017 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-005 | 2021-09-27 | RR | DHI-GUP-DT-21-079 | 2021-10-29 | B | CRS-GUP-DHI-DT-21-055 | 2021-11-07 | RC | DHI-GUP-DT-21-163 | 2021-12-09 | C | CRS-GUP-DHI-DT-21-083 | 2021-12-22 | AC | DHI-GUP-DT-22-013 | 2022-01-11 | D | CRS-GUP-DHI-DT-21-164 | 2022-01-18 | AA | DHI-GUP-DT-22-035 | 2022-01-25 | E | CRS-GUP-DHI-DT-21-194 | 2022-02-10 | AA | DHI-GUP-DT-22-086 | 2022-02-24 | F | CRS-GUP-DHI-DT-22-223 | 2022-03-02 | AA | DHI-GUP-DT-22-098 | 2022-03-04 | G | CRS-GUP-DHI-DT-22-229 | 2022-03-05 | AA | DHI-GUP-DT-22-200 | 2022-05-04 | 0 | CRS-GUP-DHI-DT-22-363 | 2022-05-23 | AC | DE-GUP-DT-E-22-857 | 2022-10-26 | 1 | CRS-GUP-DHI-DT-22-1019 | 2022-11-13 | AC | DE-GUP-DT-E-23-074 | 2023-01-26 | 2(CP) | CRS-GUP-DHI-DT-23-1535 | 2023-02-15 | AC | DE-GUP-DT-E-23-573 | 2023-05-22 | 3 | CRS-GUP-DHI-DT-23-1983 | 2023-06-08 | AA | DE-GUP-DT-E-23-963 | 2023-12-01 | 4
| GUP | CA00 | P1 | UCB | 181417 |  | GUP-CA00-P1UCB-181417 | CONTROL & ELECTRICAL BUILDING_MAIN SECTION | FA | 2021-10-28 | 2022-03-11 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | C&E Building | Arch. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-573 | 2023-05-22 | 3 | CRS-GUP-DHI-DT-23-1983 | 2023-06-08 | AA | DHI-GUP-DT-21-017 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-005 | 2021-09-27 | RR | DHI-GUP-DT-21-079 | 2021-10-29 | B | CRS-GUP-DHI-DT-21-055 | 2021-11-07 | RC | DHI-GUP-DT-21-163 | 2021-12-09 | C | CRS-GUP-DHI-DT-21-083 | 2021-12-22 | AC | DHI-GUP-DT-22-013 | 2022-01-11 | D | CRS-GUP-DHI-DT-21-164 | 2022-01-18 | AA | DHI-GUP-DT-22-035 | 2022-01-25 | E | CRS-GUP-DHI-DT-21-194 | 2022-02-10 | AA | DHI-GUP-DT-22-086 | 2022-02-24 | F | CRS-GUP-DHI-DT-22-223 | 2022-03-02 | AA | DHI-GUP-DT-22-098 | 2022-03-04 | G | CRS-GUP-DHI-DT-22-229 | 2022-03-05 | AA | DHI-GUP-DT-22-200 | 2022-05-04 | 0 | CRS-GUP-DHI-DT-22-363 | 2022-05-23 | AC | DE-GUP-DT-E-22-857 | 2022-10-26 | 1 | CRS-GUP-DHI-DT-22-1019 | 2022-11-13 | AA | DE-GUP-DT-E-23-074 | 2023-01-26 | 2 | CRS-GUP-DHI-DT-23-1535 | 2023-02-15 | AC | DE-GUP-DT-E-23-573 | 2023-05-22 | 3 | CRS-GUP-DHI-DT-23-1983 | 2023-06-08 | AA
| GUP | CA00 | P1 | UCB | 181418 |  | GUP-CA00-P1UCB-181418 | CONTROL & ELECTRICAL BUILDING_SIDE ELEVATION | FA | 2021-10-28 | 2022-03-11 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | C&E Building | Arch. | 2 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-963 | 2023-12-01 | 4 | CRS-GUP-DHI-DT-23-1983 | 2023-06-08 | NC | DHI-GUP-DT-21-017 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-005 | 2021-09-27 | RR | DHI-GUP-DT-21-079 | 2021-10-29 | B | CRS-GUP-DHI-DT-21-055 | 2021-11-07 | RC | DHI-GUP-DT-21-163 | 2021-12-09 | C | CRS-GUP-DHI-DT-21-083 | 2021-12-22 | AC | DHI-GUP-DT-22-013 | 2022-01-11 | D | CRS-GUP-DHI-DT-21-164 | 2022-01-18 | AA | DHI-GUP-DT-22-035 | 2022-01-25 | E | CRS-GUP-DHI-DT-21-194 | 2022-02-10 | AA | DHI-GUP-DT-22-086 | 2022-02-24 | F | CRS-GUP-DHI-DT-22-223 | 2022-03-02 | AA | DHI-GUP-DT-22-098 | 2022-03-04 | G | CRS-GUP-DHI-DT-22-229 | 2022-03-05 | AA | DHI-GUP-DT-22-200 | 2022-05-04 | 0 | CRS-GUP-DHI-DT-22-363 | 2022-05-23 | AC | DE-GUP-DT-E-22-857 | 2022-10-26 | 1 | CRS-GUP-DHI-DT-22-1019 | 2022-11-13 | AA | DE-GUP-DT-E-23-074 | 2023-01-26 | 2 | CRS-GUP-DHI-DT-23-1535 | 2023-02-15 | AA | DE-GUP-DT-E-23-573 | 2023-05-22 | 3 | CRS-GUP-DHI-DT-23-1983 | 2023-06-08 | NC | DE-GUP-DT-E-23-963 | 2023-12-01 | 4
| GUP | CA00 | P1 | UCB | 181419 |  | GUP-CA00-P1UCB-181419 | CONTROL & ELECTRICAL BUILDING_ENLARGED STAIRCASE & ELEVATOR PLAN & SECTION | FI | 2022-04-21 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-963 | 2023-12-01 | 8 | 자체 CRS 개정 후 제출 | 2023-11-30 | N/A | DHI-GUP-DT-22-013 | 2022-01-11 | 0 | CRS-GUP-DHI-DT-21-164 | 2022-01-18 | RC | DHI-GUP-DT-22-035 | 2022-01-25 | 1 | CRS-GUP-DHI-DT-21-194 | 2022-02-10 | RC | DHI-GUP-DT-22-086 | 2022-02-24 | 2 | CRS-GUP-DHI-DT-22-223 | 2022-03-02 | I | DHI-GUP-DT-22-098 | 2022-03-04 | 3 | CRS-GUP-DHI-DT-22-229 | 2022-03-05 | NC | DHI-GUP-DT-22-200 | 2022-05-04 | 4 | CRS-GUP-DHI-DT-22-363 | 2022-05-23 | RC | DE-GUP-DT-E-22-857 | 2022-10-26 | 5 | CRS-GUP-DHI-DT-22-1037 | 2022-11-16 | NC | DE-GUP-DT-E-23-074 | 2023-01-26 | 6 | CRS-GUP-DHI-DT-23-1535 | 2023-02-15 | NC | DE-GUP-DT-E-23-573 | 2023-05-22 | 7 | 자체 CRS 개정 후 제출 | 2023-11-30 | N/A | DE-GUP-DT-E-23-963 | 2023-12-01 | 8
| GUP | CA00 | P1 | UCB | 181420 |  | GUP-CA00-P1UCB-181420 | CONTROL & ELECTRICAL BUILDING_ENLARGED TOILET PLAN & ELEVATION | FI | 2022-04-21 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-637 | 2023-06-23 | 4 | CRS-GUP-DHI-DT-23-1598 | 2023-02-28 | NC | DHI-GUP-DT-22-199 | 2022-05-03 | 0 | CRS-GUP-DHI-DT-22-362 | 2022-05-23 | RC | DE-GUP-DT-E-22-320 | 2022-06-21 | 1 | CRS-GUP-DHI-DT-22-512 | 2022-07-12 | RC | DE-GUP-DT-E-22-549 | 2022-08-24 | 2 | CRS-GUP-DHI-DT-22-733 | 2022-09-09 | NC | DE-GUP-DT-E-23-177 | 2023-02-14 | 3 | CRS-GUP-DHI-DT-23-1598 | 2023-02-28 | NC | DE-GUP-DT-E-23-637 | 2023-06-23 | 4
| GUP | CA00 | P1 | UCB | 181421 |  | GUP-CA00-P1UCB-181421 | CONTROL & ELECTRICAL BUILDING_WALL SECTION | FI | 2022-04-21 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-637 | 2023-06-23 | 4 | CRS-GUP-DHI-DT-23-1598 | 2023-02-28 | NC | DHI-GUP-DT-22-199 | 2022-05-03 | 0 | CRS-GUP-DHI-DT-22-362 | 2022-05-23 | RC | DE-GUP-DT-E-22-320 | 2022-06-21 | 1 | CRS-GUP-DHI-DT-22-512 | 2022-07-12 | NC | DE-GUP-DT-E-22-549 | 2022-08-24 | 2 | CRS-GUP-DHI-DT-22-733 | 2022-09-09 | NC | DE-GUP-DT-E-23-177 | 2023-02-14 | 3 | CRS-GUP-DHI-DT-23-1598 | 2023-02-28 | NC | DE-GUP-DT-E-23-637 | 2023-06-23 | 4
| GUP | CA00 | P1 | UCB | 181422 |  | GUP-CA00-P1UCB-181422 | CONTROL & ELECTRICAL BUILDING_WALL OPENING PLAN & ELEVATION | FI | 2022-04-21 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-637 | 2023-06-23 | 4 | CRS-GUP-DHI-DT-23-1598 | 2023-02-28 | NC | DHI-GUP-DT-22-199 | 2022-05-03 | 0 | CRS-GUP-DHI-DT-22-362 | 2022-05-23 | RC | DE-GUP-DT-E-22-320 | 2022-06-21 | 1 | CRS-GUP-DHI-DT-22-512 | 2022-07-12 | NC | DE-GUP-DT-E-22-549 | 2022-08-24 | 2 | CRS-GUP-DHI-DT-22-733 | 2022-09-09 | NC | DE-GUP-DT-E-23-177 | 2023-02-14 | 3 | CRS-GUP-DHI-DT-23-1598 | 2023-02-28 | NC | DE-GUP-DT-E-23-637 | 2023-06-23 | 4
| GUP | CA00 | P1 | UCB | 181423 |  | GUP-CA00-P1UCB-181423 | CONTROL & ELECTRICAL BUILDING_CEILING PLAN | FI | 2022-04-21 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-637 | 2023-06-23 | 4 | CRS-GUP-DHI-DT-23-1598 | 2023-02-28 | NC | DHI-GUP-DT-22-199 | 2022-05-03 | 0 | CRS-GUP-DHI-DT-22-362 | 2022-05-23 | RC | DE-GUP-DT-E-22-320 | 2022-06-21 | 1 | CRS-GUP-DHI-DT-22-512 | 2022-07-12 | NC | DE-GUP-DT-E-22-549 | 2022-08-24 | 2 | CRS-GUP-DHI-DT-22-733 | 2022-09-09 | NC | DE-GUP-DT-E-23-177 | 2023-02-14 | 3 | CRS-GUP-DHI-DT-23-1598 | 2023-02-28 | NC | DE-GUP-DT-E-23-637 | 2023-06-23 | 4
| GUP | CA00 | P1 | UCB | 181424 |  | GUP-CA00-P1UCB-181424 | CONTROL & ELECTRICAL BUILDING_ARCHITECTURAL MISC. DETAIL | FA | 2022-04-21 | 2022-11-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-637 | 2023-06-23 | 1 | CRS-GUP-DHI-DT-23-1598 | 2023-02-28 | AA | DHI-GUP-DT-22-199 | 2022-05-03 | A | CRS-GUP-DHI-DT-22-362 | 2022-05-23 | RC | DE-GUP-DT-E-22-320 | 2022-06-21 | B | CRS-GUP-DHI-DT-22-512 | 2022-07-12 | AC | DE-GUP-DT-E-22-549 | 2022-08-24 | C | CRS-GUP-DHI-DT-22-733 | 2022-09-09 | AC | DE-GUP-DT-E-23-177 | 2023-02-14 | 0(CP) | CRS-GUP-DHI-DT-23-1598 | 2023-02-28 | AA | DE-GUP-DT-E-23-637 | 2023-06-23 | 1
| GUP | CA03 | P1 | UCB | 181451 |  | GUP-CA03-P1UCB-181451 | CONTROL & ELECTRICAL BUILDING_COLUMN ARRANGEMENT PLAN | FI | 2022-01-05 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-088 | 2023-01-30 | 5 | CRS-GUP-DHI-DT-23-1536 | 2023-02-15 | NC | DHI-GUP-DT-21-100 | 2021-11-12 | 0 | N/A | 2022-01-04 | N/A | DHI-GUP-DT-22-004 | 2022-01-05 | 1 | CRS-GUP-DHI-DT-21-165 | 2022-01-18 | RR | DHI-GUP-DT-22-106 | 2022-03-08 | 2 | CRS-GUP-DHI-DT-22-251 | 2022-03-15 | NC | DE-GUP-DT-E-22-733 | 2022-09-30 | 3 | CRS-GUP-DHI-DT-22-938 | 2022-10-21 | RC | DE-GUP-DT-E-22-931 | 2022-11-10 | 4 | CRS-GUP-DHI-DT-22-1210 | 2022-11-30 | NC | DE-GUP-DT-E-23-088 | 2023-01-30 | 5 | CRS-GUP-DHI-DT-23-1536 | 2023-02-15 | NC
| GUP | CA03 | P1 | UCB | 181452 |  | GUP-CA03-P1UCB-181452 | CONTROL & ELECTRICAL BUILDING_GROUND FLOOR FRAMING PLAN | FI | 2022-01-05 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-088 | 2023-01-30 | 4 | CRS-GUP-DHI-DT-23-1536 | 2023-02-15 | NC | DHI-GUP-DT-21-100 | 2021-11-12 | 0 | N/A | 2022-01-04 | N/A | DHI-GUP-DT-22-004 | 2022-01-05 | 1 | CRS-GUP-DHI-DT-21-165 | 2022-01-18 | RR | DHI-GUP-DT-22-106 | 2022-03-08 | 2 | CRS-GUP-DHI-DT-22-251 | 2022-03-15 | NC | DE-GUP-DT-E-22-733 | 2022-09-30 | 3 | CRS-GUP-DHI-DT-22-938 | 2022-10-21 | RC | DE-GUP-DT-E-23-088 | 2023-01-30 | 4 | CRS-GUP-DHI-DT-23-1536 | 2023-02-15 | NC
| GUP | CA03 | P1 | UCB | 181453 |  | GUP-CA03-P1UCB-181453 | CONTROL & ELECTRICAL BUILDING_SECOND FLOOR FRAMING PLAN | FI | 2022-01-05 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-705 | 2023-07-20 | 6 | CRS-GUP-DHI-DT-23-2082 | 2023-08-02 | NC | DHI-GUP-DT-21-100 | 2021-11-12 | 0 | N/A | 2022-01-04 | N/A | DHI-GUP-DT-22-004 | 2022-01-05 | 1 | CRS-GUP-DHI-DT-21-165 | 2022-01-18 | RR | DHI-GUP-DT-22-106 | 2022-03-08 | 2 | CRS-GUP-DHI-DT-22-251 | 2022-03-15 | NC | DE-GUP-DT-E-22-733 | 2022-09-30 | 3 | CRS-GUP-DHI-DT-22-938 | 2022-10-21 | RC | DE-GUP-DT-E-22-931 | 2022-11-10 | 4 | CRS-GUP-DHI-DT-22-1210 | 2022-11-30 | NC | DE-GUP-DT-E-23-088 | 2023-01-30 | 5 | CRS-GUP-DHI-DT-23-1536 | 2023-02-15 | NC | DE-GUP-DT-E-23-705 | 2023-07-20 | 6 | CRS-GUP-DHI-DT-23-2082 | 2023-08-02 | NC
| GUP | CA03 | P1 | UCB | 181454 |  | GUP-CA03-P1UCB-181454 | CONTROL & ELECTRICAL BUILDING THIRD FLOOR FRAMING PLAN | FI | 2022-01-05 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-088 | 2023-01-30 | 5 | CRS-GUP-DHI-DT-23-1536 | 2023-02-15 | NC | DHI-GUP-DT-21-100 | 2021-11-12 | 0 | N/A | 2022-01-04 | N/A | DHI-GUP-DT-22-004 | 2022-01-05 | 1 | CRS-GUP-DHI-DT-21-165 | 2022-01-18 | RR | DHI-GUP-DT-22-106 | 2022-03-08 | 2 | CRS-GUP-DHI-DT-22-251 | 2022-03-15 | NC | DE-GUP-DT-E-22-733 | 2022-09-30 | 3 | CRS-GUP-DHI-DT-22-938 | 2022-10-21 | RC | DE-GUP-DT-E-22-931 | 2022-11-10 | 4 | CRS-GUP-DHI-DT-22-1210 | 2022-11-30 | NC | DE-GUP-DT-E-23-088 | 2023-01-30 | 5 | CRS-GUP-DHI-DT-23-1536 | 2023-02-15 | NC
| GUP | CA03 | P1 | UCB | 181455 |  | GUP-CA03-P1UCB-181455 | CONTROL & ELECTRICAL BUILDING_ROOF FRAMING PLAN | FI | 2022-01-05 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-705 | 2023-07-20 | 5 | CRS-GUP-DHI-DT-23-2082 | 2023-08-02 | NC | DHI-GUP-DT-21-100 | 2021-11-12 | 0 | N/A | 2022-01-04 | N/A | DHI-GUP-DT-22-004 | 2022-01-05 | 1 | CRS-GUP-DHI-DT-21-165 | 2022-01-18 | RR | DHI-GUP-DT-22-106 | 2022-03-08 | 2 | CRS-GUP-DHI-DT-22-251 | 2022-03-15 | NC | DE-GUP-DT-E-22-733 | 2022-09-30 | 3 | CRS-GUP-DHI-DT-22-938 | 2022-10-21 | RC | DE-GUP-DT-E-23-088 | 2023-01-30 | 4 | CRS-GUP-DHI-DT-23-1536 | 2023-02-15 | RC | DE-GUP-DT-E-23-705 | 2023-07-20 | 5 | CRS-GUP-DHI-DT-23-2082 | 2023-08-02 | NC
| GUP | CA03 | P1 | UCB | 181456 |  | GUP-CA03-P1UCB-181456 | CONTROL & ELECTRICAL BUILDING_LINE FRAMING ELEVATION | FI | 2022-01-05 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-088 | 2023-01-30 | 4 | CRS-GUP-DHI-DT-23-1536 | 2023-02-15 | NC | DHI-GUP-DT-21-100 | 2021-11-12 | 0 | N/A | 2022-01-04 | N/A | DHI-GUP-DT-22-004 | 2022-01-05 | 1 | CRS-GUP-DHI-DT-21-165 | 2022-01-18 | RR | DHI-GUP-DT-22-106 | 2022-03-08 | 2 | CRS-GUP-DHI-DT-22-251 | 2022-03-15 | NC | DE-GUP-DT-E-22-733 | 2022-09-30 | 3 | CRS-GUP-DHI-DT-22-938 | 2022-10-21 | RC | DE-GUP-DT-E-23-088 | 2023-01-30 | 4 | CRS-GUP-DHI-DT-23-1536 | 2023-02-15 | NC
| GUP | CA03 | P1 | UCB | 181457 |  | GUP-CA03-P1UCB-181457 | CONTROL & ELECTRICAL BUILDING_ROW FRAMING ELEVATION | FI | 2022-01-05 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-088 | 2023-01-30 | 4 | CRS-GUP-DHI-DT-23-1536 | 2023-02-15 | NC | DHI-GUP-DT-21-100 | 2021-11-12 | 0 | N/A | 2022-01-04 | N/A | DHI-GUP-DT-22-004 | 2022-01-05 | 1 | CRS-GUP-DHI-DT-21-165 | 2022-01-18 | RR | DHI-GUP-DT-22-106 | 2022-03-08 | 2 | CRS-GUP-DHI-DT-22-251 | 2022-03-15 | NC | DE-GUP-DT-E-22-733 | 2022-09-30 | 3 | CRS-GUP-DHI-DT-22-938 | 2022-10-21 | RC | DE-GUP-DT-E-23-088 | 2023-01-30 | 4 | CRS-GUP-DHI-DT-23-1536 | 2023-02-15 | NC
| GUP | CA03 | P1 | UCB | 181460 |  | GUP-CA03-P1UCB-181460 | CONTROL & ELECTRICAL BUILDING_GIRT LINE ELEVATION | FI | 2022-01-05 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-705 | 2023-07-20 | 6 | CRS-GUP-DHI-DT-23-2082 | 2023-08-02 | NC | DHI-GUP-DT-21-100 | 2021-11-12 | 0 | N/A | 2022-01-04 | N/A | DHI-GUP-DT-22-004 | 2022-01-05 | 1 | CRS-GUP-DHI-DT-21-165 | 2022-01-18 | RR | DHI-GUP-DT-22-106 | 2022-03-08 | 2 | CRS-GUP-DHI-DT-22-251 | 2022-03-15 | NC | DE-GUP-DT-E-22-733 | 2022-09-30 | 3 | CRS-GUP-DHI-DT-22-938 | 2022-10-21 | NC | DE-GUP-DT-E-22-931 | 2022-11-10 | 4 | CRS-GUP-DHI-DT-22-1210 | 2022-11-30 | NC | DE-GUP-DT-E-23-088 | 2023-01-30 | 5 | CRS-GUP-DHI-DT-23-1536 | 2023-02-15 | NC | DE-GUP-DT-E-23-705 | 2023-07-20 | 6 | CRS-GUP-DHI-DT-23-2082 | 2023-08-02 | NC
| GUP | CA03 | P1 | UCB | 181461 |  | GUP-CA03-P1UCB-181461 | CONTROL & ELECTRICAL BUILDING_GIRT ROW ELEVATION | FI | 2022-01-05 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-705 | 2023-07-20 | 5 | CRS-GUP-DHI-DT-23-2082 | 2023-08-02 | NC | DHI-GUP-DT-21-100 | 2021-11-12 | 0 | N/A | 2022-01-04 | N/A | DHI-GUP-DT-22-004 | 2022-01-05 | 1 | CRS-GUP-DHI-DT-21-165 | 2022-01-18 | RR | DHI-GUP-DT-22-106 | 2022-03-08 | 2 | CRS-GUP-DHI-DT-22-251 | 2022-03-15 | NC | DE-GUP-DT-E-22-733 | 2022-09-30 | 3 | CRS-GUP-DHI-DT-22-938 | 2022-10-21 | NC | DE-GUP-DT-E-23-088 | 2023-01-30 | 4 | CRS-GUP-DHI-DT-23-1536 | 2023-02-15 | NC | DE-GUP-DT-E-23-705 | 2023-07-20 | 5 | CRS-GUP-DHI-DT-23-2082 | 2023-08-02 | NC
| GUP | CA03 | P1 | UCB | 181458 |  | GUP-CA03-P1UCB-181458 | CONTROL & ELECTRICAL BUILDING_STAIRCASE FRAMING PLAN & ELEVATION | FI | 2022-01-05 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-705 | 2023-07-20 | 6 | CRS-GUP-DHI-DT-23-2082 | 2023-08-02 | NC | DHI-GUP-DT-21-100 | 2021-11-12 | 0 | N/A | 2022-01-04 | N/A | DHI-GUP-DT-22-004 | 2022-01-05 | 1 | CRS-GUP-DHI-DT-21-165 | 2022-01-18 | RR | DHI-GUP-DT-22-106 | 2022-03-08 | 2 | CRS-GUP-DHI-DT-22-251 | 2022-03-15 | NC | DE-GUP-DT-E-22-733 | 2022-09-30 | 3 | CRS-GUP-DHI-DT-22-938 | 2022-10-21 | RC | DE-GUP-DT-E-22-931 | 2022-11-10 | 4 | CRS-GUP-DHI-DT-22-1210 | 2022-11-30 | RC | DE-GUP-DT-E-23-088 | 2023-01-30 | 5 | CRS-GUP-DHI-DT-23-1536 | 2023-02-15 | RC | DE-GUP-DT-E-23-705 | 2023-07-20 | 6 | CRS-GUP-DHI-DT-23-2082 | 2023-08-02 | NC
| GUP | CA01 | P1 | UCB | 181433 |  | GUP-CA01-P1UCB-181433 | CONTROL & ELECTRICAL BUILDING_SLAB OPENING ARRANGEMENT PLAN | FI | 2022-04-21 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-637 | 2023-06-23 | 4 | CRS-GUP-DHI-DT-23-1598 | 2023-02-28 | NC | DHI-GUP-DT-22-199 | 2022-05-03 | 0 | CRS-GUP-DHI-DT-22-362 | 2022-05-23 | RC | DE-GUP-DT-E-22-320 | 2022-06-21 | 1 | CRS-GUP-DHI-DT-22-512 | 2022-07-12 | RC | DE-GUP-DT-E-22-549 | 2022-08-24 | 2 | CRS-GUP-DHI-DT-22-733 | 2022-09-09 | RC | DE-GUP-DT-E-23-177 | 2023-02-14 | 3 | CRS-GUP-DHI-DT-23-1598 | 2023-02-28 | NC | DE-GUP-DT-E-23-637 | 2023-06-23 | 4
| GUP | CA01 | P1 | UCB | 181434 |  | GUP-CA01-P1UCB-181434 | CONTROL & ELECTRICAL BUILDING_EMBEDDED PLATE ARRANGEMENT PLAN | FI | 2022-04-21 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-637 | 2023-06-23 | 4 | CRS-GUP-DHI-DT-23-1598 | 2023-02-28 | NC | DHI-GUP-DT-22-199 | 2022-05-03 | 0 | CRS-GUP-DHI-DT-22-362 | 2022-05-23 | RC | DE-GUP-DT-E-22-320 | 2022-06-21 | 1 | CRS-GUP-DHI-DT-22-512 | 2022-07-12 | RC | DE-GUP-DT-E-22-549 | 2022-08-24 | 2 | CRS-GUP-DHI-DT-22-733 | 2022-09-09 | NC | DE-GUP-DT-E-23-177 | 2023-02-14 | 3 | CRS-GUP-DHI-DT-23-1598 | 2023-02-28 | NC | DE-GUP-DT-E-23-637 | 2023-06-23 | 4
| GUP | CA03 | P1 | UCB | 181459 |  | GUP-CA03-P1UCB-181459 | CONTROL & ELECTRICAL BUILDING_PANEL SUPPORT FRAME LAYOUT & DETAIL | FI | 2022-04-21 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-637 | 2023-06-23 | 4 | CRS-GUP-DHI-DT-23-1598 | 2023-02-28 | NC | DHI-GUP-DT-22-199 | 2022-05-03 | 0 | CRS-GUP-DHI-DT-22-362 | 2022-05-23 | RC | DE-GUP-DT-E-22-320 | 2022-06-21 | 1 | CRS-GUP-DHI-DT-22-512 | 2022-07-12 | RC | DE-GUP-DT-E-22-549 | 2022-08-24 | 2 | CRS-GUP-DHI-DT-22-733 | 2022-09-09 | RC | DE-GUP-DT-E-23-177 | 2023-02-14 | 3 | CRS-GUP-DHI-DT-23-1598 | 2023-02-28 | NC | DE-GUP-DT-E-23-637 | 2023-06-23 | 4
| GUP | CA01 | P1 | UCB | 181435 |  | GUP-CA01-P1UCB-181435 | CONTROL & ELECTRICAL BUILDING_STRUCTURAL MISC. DETAIL | FI | 2022-04-21 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-637 | 2023-06-23 | 4 | CRS-GUP-DHI-DT-23-1598 | 2023-02-28 | NC | DHI-GUP-DT-22-199 | 2022-05-03 | 0 | CRS-GUP-DHI-DT-22-362 | 2022-05-23 | RC | DE-GUP-DT-E-22-320 | 2022-06-21 | 1 | CRS-GUP-DHI-DT-22-512 | 2022-07-12 | RC | DE-GUP-DT-E-22-549 | 2022-08-24 | 2 | CRS-GUP-DHI-DT-22-733 | 2022-09-09 | RC | DE-GUP-DT-E-23-177 | 2023-02-14 | 3 | CRS-GUP-DHI-DT-23-1598 | 2023-02-28 | NC | DE-GUP-DT-E-23-637 | 2023-06-23 | 4
| GUP | CA02 | P1 | UCB | 181436 |  | GUP-CA02-P1UCB-181436 | CONTROL & ELECTRICAL BUILDING_COLUMN RE-BAR SCHEDULE | FI | 2022-04-21 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-088 | 2023-01-30 | 4 | CRS-GUP-DHI-DT-23-1536 | 2023-02-15 | NC | DHI-GUP-DT-21-100 | 2021-11-12 | 0 | N/A | 2022-01-04 | N/A | DHI-GUP-DT-22-004 | 2022-01-05 | 1 | CRS-GUP-DHI-DT-21-165 | 2022-01-18 | RR | DHI-GUP-DT-22-106 | 2022-03-08 | 2 | CRS-GUP-DHI-DT-22-251 | 2022-03-15 | NC | DE-GUP-DT-E-22-733 | 2022-09-30 | 3 | CRS-GUP-DHI-DT-22-938 | 2022-10-21 | RC | DE-GUP-DT-E-23-088 | 2023-01-30 | 4 | CRS-GUP-DHI-DT-23-1536 | 2023-02-15 | NC
| GUP | CA02 | P1 | UCB | 181437 |  | GUP-CA02-P1UCB-181437 | CONTROL & ELECTRICAL BUILDING_BEAM & GIRDER RE-BAR SCHEDULE | FI | 2022-03-11 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-088 | 2023-01-30 | 4 | CRS-GUP-DHI-DT-23-1536 | 2023-02-15 | NC | DHI-GUP-DT-21-100 | 2021-11-12 | 0 | N/A | 2022-01-04 | N/A | DHI-GUP-DT-22-004 | 2022-01-05 | 1 | CRS-GUP-DHI-DT-21-165 | 2022-01-18 | RR | DHI-GUP-DT-22-106 | 2022-03-08 | 2 | CRS-GUP-DHI-DT-22-251 | 2022-03-15 | NC | DE-GUP-DT-E-22-733 | 2022-09-30 | 3 | CRS-GUP-DHI-DT-22-938 | 2022-10-21 | RC | DE-GUP-DT-E-23-088 | 2023-01-30 | 4 | CRS-GUP-DHI-DT-23-1536 | 2023-02-15 | NC
| GUP | CA02 | P1 | UCB | 181438 |  | GUP-CA02-P1UCB-181438 | CONTROL & ELECTRICAL BUILDING_SLAB & MISC. RE-BAR SCHEDULE | FI | 2022-03-11 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-23-705 | 2023-07-20 | 5 | CRS-GUP-DHI-DT-23-2082 | 2023-08-02 | NC | DHI-GUP-DT-21-100 | 2021-11-12 | 0 | N/A | 2022-01-04 | N/A | DHI-GUP-DT-22-004 | 2022-01-05 | 1 | CRS-GUP-DHI-DT-21-165 | 2022-01-18 | RR | DHI-GUP-DT-22-106 | 2022-03-08 | 2 | CRS-GUP-DHI-DT-22-251 | 2022-03-15 | NC | DE-GUP-DT-E-22-733 | 2022-09-30 | 3 | CRS-GUP-DHI-DT-22-938 | 2022-10-21 | RC | DE-GUP-DT-E-23-088 | 2023-01-30 | 4 | CRS-GUP-DHI-DT-23-1536 | 2023-02-15 | NC | DE-GUP-DT-E-23-705 | 2023-07-20 | 5 | CRS-GUP-DHI-DT-23-2082 | 2023-08-02 | NC
| GUP | CA06 | P1 | UAB | 181801 |  | GUP-CA06-P1UAB-181801 | SWITCHYARD CONTROL BUILDING_CALCULATION SHEET | FA | 2022-05-30 | 2022-10-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | SWYD Building | Arch. | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-161 | 2023-02-13 | 1 | CRS-GUP-DHI-DT-23-1570 | 2023-02-23 | AA | DHI-GUP-DT-21-016 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-004 | 2021-09-27 | RR | DHI-GUP-DT-22-014 | 2022-01-12 | B | CRS-GUP-DHI-DT-21-176 | 2022-01-24 | RC | DHI-GUP-DT-22-111 | 2022-03-11 | C | CRS-GUP-DHI-DT-22-272 | 2022-04-11 | RC | DE-GUP-DT-E-22-232 | 2022-05-19 | D | CRS-GUP-DHI-DT-22-409 | 2022-06-10 | RC | DE-GUP-DT-E-22-363 | 2022-07-07 | E | CRS-GUP-DHI-DT-22-523 | 2022-07-19 | AC | DE-GUP-DT-E-22-561 | 2022-08-26 | F | CRS-GUP-DHI-DT-22-761 | 2022-09-14 | AC | DE-GUP-DT-E-22-900 | 2022-11-03 | 0(CP) | CRS-GUP-DHI-DT-22-1040 | 2022-11-16 | AA | DE-GUP-DT-E-23-161 | 2023-02-13 | 1 | CRS-GUP-DHI-DT-23-1570 | 2023-02-23 | AA
| GUP | CA01 | P1 | UAB | 181831 |  | GUP-CA01-P1UAB-181831 | SWITCHYARD CONTROL BUILDING_FOUNDATION ARRANGEMENT PLAN | FA | 2022-05-30 | 2022-10-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | SWYD Building | Arch. | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-384 | 2023-03-29 | 2 | CRS-GUP-DHI-DT-23-1570 | 2023-02-23 | AA | DHI-GUP-DT-21-016 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-004 | 2021-09-27 | RR | DHI-GUP-DT-22-014 | 2022-01-12 | B | CRS-GUP-DHI-DT-21-176 | 2022-01-24 | RC | DHI-GUP-DT-22-111 | 2022-03-11 | C | CRS-GUP-DHI-DT-22-272 | 2022-04-11 | RC | DE-GUP-DT-E-22-232 | 2022-05-19 | D | CRS-GUP-DHI-DT-22-409 | 2022-06-10 | RC | DE-GUP-DT-E-22-363 | 2022-07-07 | E | CRS-GUP-DHI-DT-22-523 | 2022-07-19 | RC | DE-GUP-DT-E-22-561 | 2022-08-26 | F | CRS-GUP-DHI-DT-22-761 | 2022-09-14 | AC | DE-GUP-DT-E-22-900 | 2022-11-03 | 0(CP) | CRS-GUP-DHI-DT-22-1040 | 2022-11-16 | AA | DE-GUP-DT-E-23-161 | 2023-02-13 | 1 | CRS-GUP-DHI-DT-23-1570 | 2023-02-23 | AA | DE-GUP-DT-E-23-384 | 2023-03-29 | 2
| GUP | CA02 | P1 | UAB | 181832 |  | GUP-CA02-P1UAB-181832 | SWITCHYARD CONTROL BUILDING_FOUNDATION RE-BAR SCHEDULE | FI | 2022-05-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | SWYD Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-384 | 2023-03-29 | 5 | CRS-GUP-DHI-DT-23-1849 | 2023-04-19 | NC | DE-GUP-DT-E-22-232 | 2022-05-19 | 0 | CRS-GUP-DHI-DT-22-409 | 2022-06-10 | RC | DE-GUP-DT-E-22-363 | 2022-07-07 | 1 | CRS-GUP-DHI-DT-22-523 | 2022-07-19 | RC | DE-GUP-DT-E-22-561 | 2022-08-26 | 2 | CRS-GUP-DHI-DT-22-761 | 2022-09-14 | NC | DE-GUP-DT-E-22-900 | 2022-11-03 | 3 | CRS-GUP-DHI-DT-22-1040 | 2022-11-16 | NC | DE-GUP-DT-E-23-161 | 2023-02-13 | 4 | CRS-GUP-DHI-DT-23-1570 | 2023-02-23 | NC | DE-GUP-DT-E-23-384 | 2023-03-29 | 5 | CRS-GUP-DHI-DT-23-1849 | 2023-04-19 | NC
| GUP | CA00 | P1 | UAB | 181810 |  | GUP-CA00-P1UAB-181810 | SWITCHYARD CONTROL BUILDING_DOOR & WINDOW SCHEDULE | FA | 2022-05-30 | 2022-10-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | SWYD Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-925 | 2023-11-21 | 3 | 자체 CRS 개정 후 제출 | 2023-11-20 | N/A | DHI-GUP-DT-21-016 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-004 | 2021-09-27 | RR | DHI-GUP-DT-22-014 | 2022-01-12 | B | CRS-GUP-DHI-DT-21-176 | 2022-01-24 | AC | DHI-GUP-DT-22-111 | 2022-03-11 | C | CRS-GUP-DHI-DT-22-272 | 2022-04-11 | AC | DE-GUP-DT-E-22-232 | 2022-05-19 | D | CRS-GUP-DHI-DT-22-409 | 2022-06-10 | AC | DE-GUP-DT-E-22-363 | 2022-07-07 | E | CRS-GUP-DHI-DT-22-523 | 2022-07-19 | AC | DE-GUP-DT-E-22-561 | 2022-08-26 | F | CRS-GUP-DHI-DT-22-761 | 2022-09-14 | AC | DE-GUP-DT-E-22-900 | 2022-11-03 | 0(CP) | CRS-GUP-DHI-DT-22-1040 | 2022-11-16 | AA | DE-GUP-DT-E-23-161 | 2023-02-13 | 1 | CRS-GUP-DHI-DT-23-1570 | 2023-02-23 | AA | DE-GUP-DT-E-23-384 | 2023-03-29 | 2 | 자체 CRS 개정 후 제출 | 2023-11-20 | N/A | DE-GUP-DT-E-23-925 | 2023-11-21 | 3
| GUP | CA00 | P1 | UAB | 181811 |  | GUP-CA00-P1UAB-181811 | SWITCHYARD CONTROL BUILDING_INTERIOR FINISH SCHEDULE | FA | 2022-05-30 | 2022-10-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | SWYD Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-384 | 2023-03-29 | 2 | CRS-GUP-DHI-DT-23-1849 | 2023-04-19 | AA | DHI-GUP-DT-21-016 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-004 | 2021-09-27 | RR | DHI-GUP-DT-22-014 | 2022-01-12 | B | CRS-GUP-DHI-DT-21-176 | 2022-01-24 | AC | DHI-GUP-DT-22-111 | 2022-03-11 | C | CRS-GUP-DHI-DT-22-272 | 2022-04-11 | AC | DE-GUP-DT-E-22-232 | 2022-05-19 | D | CRS-GUP-DHI-DT-22-409 | 2022-06-10 | AC | DE-GUP-DT-E-22-363 | 2022-07-07 | E | CRS-GUP-DHI-DT-22-523 | 2022-07-19 | AC | DE-GUP-DT-E-22-561 | 2022-08-26 | F | CRS-GUP-DHI-DT-22-761 | 2022-09-14 | AC | DE-GUP-DT-E-22-900 | 2022-11-03 | 0(CP) | CRS-GUP-DHI-DT-22-1040 | 2022-11-16 | AA | DE-GUP-DT-E-23-161 | 2023-02-13 | 1 | CRS-GUP-DHI-DT-23-1570 | 2023-02-23 | AC | DE-GUP-DT-E-23-384 | 2023-03-29 | 2 | CRS-GUP-DHI-DT-23-1849 | 2023-04-19 | AA
| GUP | CA00 | P1 | UAB | 181812 |  | GUP-CA00-P1UAB-181812 | SWITCHYARD CONTROL BUILDING_GROUND FLOOR PLAN | FA | 2022-05-30 | 2022-10-01 | 건축기술2팀(Arch.) | 구남영 | B | P | G | FI |  | CCPP | SWYD Building | Arch. | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-24-097 | 2024-03-28 | 4 | 자체 CRS 개정 후 제출 | 2024-03-27 | N/A | DHI-GUP-DT-21-016 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-004 | 2021-09-27 | RR | DHI-GUP-DT-22-014 | 2022-01-12 | B | CRS-GUP-DHI-DT-21-176 | 2022-01-24 | AC | DHI-GUP-DT-22-111 | 2022-03-11 | C | CRS-GUP-DHI-DT-22-272 | 2022-04-11 | AC | DE-GUP-DT-E-22-232 | 2022-05-19 | D | CRS-GUP-DHI-DT-22-409 | 2022-06-10 | AC | DE-GUP-DT-E-22-363 | 2022-07-07 | E | CRS-GUP-DHI-DT-22-523 | 2022-07-19 | AC | DE-GUP-DT-E-22-561 | 2022-08-26 | F | CRS-GUP-DHI-DT-22-761 | 2022-09-14 | AC | DE-GUP-DT-E-22-900 | 2022-11-03 | 0(CP) | CRS-GUP-DHI-DT-22-1040 | 2022-11-16 | AA | DE-GUP-DT-E-23-161 | 2023-02-13 | 1 | CRS-GUP-DHI-DT-23-1570 | 2023-02-23 | AC | DE-GUP-DT-E-23-384 | 2023-03-29 | 2 | CRS-GUP-DHI-DT-23-1849 | 2023-04-19 | AA | DE-GUP-DT-E-23-925 | 2023-11-21 | 3 | 자체 CRS 개정 후 제출 | 2024-03-27 | N/A | DE-GUP-DT-E-24-097 | 2024-03-28 | 4
| GUP | CA00 | P1 | UAB | 181813 |  | GUP-CA00-P1UAB-181813 | SWITCHYARD CONTROL BUILDING_ROOF PLAN | FA | 2022-05-30 | 2022-10-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | SWYD Building | Arch. | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-925 | 2023-11-21 | 3 | 자체 CRS 개정 후 제출 | 2023-11-20 | N/A | DHI-GUP-DT-21-016 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-004 | 2021-09-27 | RR | DHI-GUP-DT-22-014 | 2022-01-12 | B | CRS-GUP-DHI-DT-21-176 | 2022-01-24 | AC | DHI-GUP-DT-22-111 | 2022-03-11 | C | CRS-GUP-DHI-DT-22-272 | 2022-04-11 | AC | DE-GUP-DT-E-22-232 | 2022-05-19 | D | CRS-GUP-DHI-DT-22-409 | 2022-06-10 | AC | DE-GUP-DT-E-22-363 | 2022-07-07 | E | CRS-GUP-DHI-DT-22-523 | 2022-07-19 | AC | DE-GUP-DT-E-22-561 | 2022-08-26 | F | CRS-GUP-DHI-DT-22-761 | 2022-09-14 | AC | DE-GUP-DT-E-22-900 | 2022-11-03 | 0(CP) | CRS-GUP-DHI-DT-22-1040 | 2022-11-16 | AA | DE-GUP-DT-E-23-161 | 2023-02-13 | 1 | CRS-GUP-DHI-DT-23-1570 | 2023-02-23 | AA | DE-GUP-DT-E-23-384 | 2023-03-29 | 2 | 자체 CRS 개정 후 제출 | 2023-11-20 | N/A | DE-GUP-DT-E-23-925 | 2023-11-21 | 3
| GUP | CA00 | P1 | UAB | 181814 |  | GUP-CA00-P1UAB-181814 | SWITCHYARD CONTROL BUILDING_MAIN SECTION | FA | 2022-05-30 | 2022-10-01 | 건축기술2팀(Arch.) | 구남영 | B | P | G | FI |  | CCPP | SWYD Building | Arch. | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-925 | 2023-11-21 | 3 | CRS-GUP-DHI-DT-23-1849 | 2023-04-19 | AA | DHI-GUP-DT-21-016 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-004 | 2021-09-27 | RR | DHI-GUP-DT-22-014 | 2022-01-12 | B | CRS-GUP-DHI-DT-21-176 | 2022-01-24 | AC | DHI-GUP-DT-22-111 | 2022-03-11 | C | CRS-GUP-DHI-DT-22-272 | 2022-04-11 | AC | DE-GUP-DT-E-22-232 | 2022-05-19 | D | CRS-GUP-DHI-DT-22-409 | 2022-06-10 | AC | DE-GUP-DT-E-22-363 | 2022-07-07 | E | CRS-GUP-DHI-DT-22-523 | 2022-07-19 | AC | DE-GUP-DT-E-22-561 | 2022-08-26 | F | CRS-GUP-DHI-DT-22-761 | 2022-09-14 | AC | DE-GUP-DT-E-22-900 | 2022-11-03 | 0(CP) | CRS-GUP-DHI-DT-22-1040 | 2022-11-16 | AA | DE-GUP-DT-E-23-161 | 2023-02-13 | 1 | CRS-GUP-DHI-DT-23-1570 | 2023-02-23 | AC | DE-GUP-DT-E-23-384 | 2023-03-29 | 2 | CRS-GUP-DHI-DT-23-1849 | 2023-04-19 | AA | DE-GUP-DT-E-23-925 | 2023-11-21 | 3
| GUP | CA00 | P1 | UAB | 181815 |  | GUP-CA00-P1UAB-181815 | SWITCHYARD CONTROL BUILDING_SIDE ELEVATION | FA | 2022-05-30 | 2022-10-01 | 건축기술2팀(Arch.) | 구남영 | B | P | G | FI |  | CCPP | SWYD Building | Arch. | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-925 | 2023-11-21 | 3 | CRS-GUP-DHI-DT-23-1849 | 2023-04-19 | NC | DHI-GUP-DT-21-016 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-004 | 2021-09-27 | RR | DHI-GUP-DT-22-014 | 2022-01-12 | B | CRS-GUP-DHI-DT-21-176 | 2022-01-24 | AC | DHI-GUP-DT-22-111 | 2022-03-11 | C | CRS-GUP-DHI-DT-22-272 | 2022-04-11 | AC | DE-GUP-DT-E-22-232 | 2022-05-19 | D | CRS-GUP-DHI-DT-22-409 | 2022-06-10 | AC | DE-GUP-DT-E-22-363 | 2022-07-07 | E | CRS-GUP-DHI-DT-22-523 | 2022-07-19 | AC | DE-GUP-DT-E-22-561 | 2022-08-26 | F | CRS-GUP-DHI-DT-22-761 | 2022-09-14 | AC | DE-GUP-DT-E-22-900 | 2022-11-03 | 0(CP) | CRS-GUP-DHI-DT-22-1040 | 2022-11-16 | AA | DE-GUP-DT-E-23-161 | 2023-02-13 | 1 | CRS-GUP-DHI-DT-23-1570 | 2023-02-23 | AC | DE-GUP-DT-E-23-384 | 2023-03-29 | 2 | CRS-GUP-DHI-DT-23-1849 | 2023-04-19 | NC | DE-GUP-DT-E-23-925 | 2023-11-21 | 3
| GUP | CA00 | P1 | UAB | 181816 |  | GUP-CA00-P1UAB-181816 | SWITCHYARD CONTROL BUILDING_CEILING PLAN | FI | 2022-10-01 |  | 건축기술2팀(Arch.) | 구남영 | B | P | G | FI |  | CCPP | SWYD Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-925 | 2023-11-21 | 3 | CRS-GUP-DHI-DT-23-1849 | 2023-04-19 | NC | DE-GUP-DT-E-22-900 | 2022-11-03 | 0 | CRS-GUP-DHI-DT-22-1040 | 2022-11-16 | NC | DE-GUP-DT-E-23-161 | 2023-02-13 | 1 | CRS-GUP-DHI-DT-23-1570 | 2023-02-23 | NC | DE-GUP-DT-E-23-384 | 2023-03-29 | 2 | CRS-GUP-DHI-DT-23-1849 | 2023-04-19 | NC | DE-GUP-DT-E-23-925 | 2023-11-21 | 3
| GUP | CA00 | P1 | UAB | 181817 |  | GUP-CA00-P1UAB-181817 | SWITCHYARD CONTROL BUILDING_ARCHITECTURAL MISC. DETAIL | FA | 2022-10-01 | 2023-01-30 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | SWYD Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-24-097 | 2024-03-28 | 4 | 자체 CRS 개정 후 제출 | 2024-03-27 | N/A | DHI-GUP-DT-22-014 | 2022-01-12 | A | CRS-GUP-DHI-DT-21-176 | 2022-01-24 | AC | DHI-GUP-DT-22-111 | 2022-03-11 | B | CRS-GUP-DHI-DT-22-272 | 2022-04-11 | AC | DE-GUP-DT-E-22-232 | 2022-05-19 | C | CRS-GUP-DHI-DT-22-409 | 2022-06-10 | AC | DE-GUP-DT-E-22-363 | 2022-07-07 | D | CRS-GUP-DHI-DT-22-523 | 2022-07-19 | AC | DE-GUP-DT-E-22-561 | 2022-08-26 | E | CRS-GUP-DHI-DT-22-761 | 2022-09-14 | AC | DE-GUP-DT-E-22-900 | 2022-11-03 | 0(CP) | CRS-GUP-DHI-DT-22-1040 | 2022-11-16 | AA | DE-GUP-DT-E-23-161 | 2023-02-13 | 1 | CRS-GUP-DHI-DT-23-1570 | 2023-02-23 | AA | DE-GUP-DT-E-23-384 | 2023-03-29 | 2 | 자체 CRS 개정 후 제출 | 2023-11-20 | N/A | DE-GUP-DT-E-23-925 | 2023-11-21 | 3 | 자체 CRS 개정 후 제출 | 2024-03-27 | N/A | DE-GUP-DT-E-24-097 | 2024-03-28 | 4
| GUP | CA00 | P1 | UAB | 181818 |  | GUP-CA00-P1UAB-181818 | SWITCHYARD CONTROL BUILDING_WALL SECTION | FI | 2022-05-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P | G | FI |  | CCPP | SWYD Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-925 | 2023-11-21 | 9 | CRS-GUP-DHI-DT-23-1849 | 2023-04-19 | NC | DHI-GUP-DT-21-016 | 2021-09-07 | 0 | CRS-GUP-DHI-DT-21-004 | 2021-09-27 | RC | DHI-GUP-DT-22-014 | 2022-01-12 | 1 | CRS-GUP-DHI-DT-21-176 | 2022-01-24 | NC | DHI-GUP-DT-22-111 | 2022-03-11 | 2 | CRS-GUP-DHI-DT-22-272 | 2022-04-11 | NC | DE-GUP-DT-E-22-232 | 2022-05-19 | 3 | CRS-GUP-DHI-DT-22-409 | 2022-06-10 | RC | DE-GUP-DT-E-22-363 | 2022-07-07 | 4 | CRS-GUP-DHI-DT-22-523 | 2022-07-19 | NC | DE-GUP-DT-E-22-561 | 2022-08-26 | 5 | CRS-GUP-DHI-DT-22-761 | 2022-09-14 | NC | DE-GUP-DT-E-22-900 | 2022-11-03 | 6 | CRS-GUP-DHI-DT-22-1040 | 2022-11-16 | NC | DE-GUP-DT-E-23-161 | 2023-02-13 | 7 | CRS-GUP-DHI-DT-23-1570 | 2023-02-23 | RC | DE-GUP-DT-E-23-384 | 2023-03-29 | 8 | CRS-GUP-DHI-DT-23-1849 | 2023-04-19 | NC | DE-GUP-DT-E-23-925 | 2023-11-21 | 9
| GUP | CA00 | P1 | UAB | 181819 |  | GUP-CA00-P1UAB-181819 | SWITCHYARD CONTROL BUILDING_ENLARGED TOILET PLAN & ELEVATION | FI | 2022-05-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | SWYD Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-384 | 2023-03-29 | 8 | CRS-GUP-DHI-DT-23-1849 | 2023-04-19 | NC | DHI-GUP-DT-21-016 | 2021-09-07 | 0 | CRS-GUP-DHI-DT-21-004 | 2021-09-27 | RC | DHI-GUP-DT-22-014 | 2022-01-12 | 1 | CRS-GUP-DHI-DT-21-176 | 2022-01-24 | NC | DHI-GUP-DT-22-111 | 2022-03-11 | 2 | CRS-GUP-DHI-DT-22-272 | 2022-04-11 | NC | DE-GUP-DT-E-22-232 | 2022-05-19 | 3 | CRS-GUP-DHI-DT-22-409 | 2022-06-10 | RC | DE-GUP-DT-E-22-363 | 2022-07-07 | 4 | CRS-GUP-DHI-DT-22-523 | 2022-07-19 | NC | DE-GUP-DT-E-22-561 | 2022-08-26 | 5 | CRS-GUP-DHI-DT-22-761 | 2022-09-14 | NC | DE-GUP-DT-E-22-900 | 2022-11-03 | 6 | CRS-GUP-DHI-DT-22-1040 | 2022-11-16 | NC | DE-GUP-DT-E-23-161 | 2023-02-13 | 7 | CRS-GUP-DHI-DT-23-1570 | 2023-02-23 | RC | DE-GUP-DT-E-23-384 | 2023-03-29 | 8 | CRS-GUP-DHI-DT-23-1849 | 2023-04-19 | NC
| GUP | CA01 | P1 | UAB | 181833 |  | GUP-CA01-P1UAB-181833 | SWITCHYARD CONTROL BUILDING_COLUMN ARRANGEMENT PLAN | FI | 2022-06-27 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | SWYD Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-382 | 2023-03-29 | 4 | CRS-GUP-DHI-DT-23-1848 | 2023-04-19 | NC | DHI-GUP-DT-21-098 | 2021-11-11 | 0 | CRS-GUP-DHI-DT-21-061 | 2021-11-15 | RR | DE-GUP-DT-E-22-630 | 2022-09-07 | 1 | CRS-GUP-DHI-DT-22-827 | 2022-09-22 | NC | DE-GUP-DT-E-22-901 | 2022-11-03 | 2 | CRS-GUP-DHI-DT-22-1041 | 2022-11-16 | NC | DE-GUP-DT-E-23-163 | 2023-02-13 | 3 | CRS-GUP-DHI-DT-23-1579 | 2023-02-23 | NC | DE-GUP-DT-E-23-382 | 2023-03-29 | 4 | CRS-GUP-DHI-DT-23-1848 | 2023-04-19 | NC
| GUP | CA01 | P1 | UAB | 181834 |  | GUP-CA01-P1UAB-181834 | SWITCHYARD CONTROL BUILDING_GROUND FLOOR FRAMING PLAN | FI | 2022-06-27 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | SWYD Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-24-097 | 2024-03-28 | 5 | CRS-GUP-DHI-DT-23-1848 | 2023-04-19 | NC | DHI-GUP-DT-21-098 | 2021-11-11 | 0 | CRS-GUP-DHI-DT-21-061 | 2021-11-15 | RR | DE-GUP-DT-E-22-630 | 2022-09-07 | 1 | CRS-GUP-DHI-DT-22-827 | 2022-09-22 | RC | DE-GUP-DT-E-22-901 | 2022-11-03 | 2 | CRS-GUP-DHI-DT-22-1041 | 2022-11-16 | NC | DE-GUP-DT-E-23-163 | 2023-02-13 | 3 | CRS-GUP-DHI-DT-23-1579 | 2023-02-23 | RC | DE-GUP-DT-E-23-382 | 2023-03-29 | 4 | CRS-GUP-DHI-DT-23-1848 | 2023-04-19 | NC | DE-GUP-DT-E-24-097 | 2024-03-28 | 5
| GUP | CA01 | P1 | UAB | 181835 |  | GUP-CA01-P1UAB-181835 | SWITCHYARD CONTROL BUILDING_ROOF FRAMING PLAN | FI | 2022-06-27 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | SWYD Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-382 | 2023-03-29 | 4 | CRS-GUP-DHI-DT-23-1848 | 2023-04-19 | NC | DHI-GUP-DT-21-098 | 2021-11-11 | 0 | CRS-GUP-DHI-DT-21-061 | 2021-11-15 | RR | DE-GUP-DT-E-22-630 | 2022-09-07 | 1 | CRS-GUP-DHI-DT-22-827 | 2022-09-22 | NC | DE-GUP-DT-E-22-901 | 2022-11-03 | 2 | CRS-GUP-DHI-DT-22-1041 | 2022-11-16 | NC | DE-GUP-DT-E-23-163 | 2023-02-13 | 3 | CRS-GUP-DHI-DT-23-1579 | 2023-02-23 | NC | DE-GUP-DT-E-23-382 | 2023-03-29 | 4 | CRS-GUP-DHI-DT-23-1848 | 2023-04-19 | NC
| GUP | CA01 | P1 | UAB | 181836 |  | GUP-CA01-P1UAB-181836 | SWITCHYARD CONTROL BUILDING_LINE FRAMING ELEVATION | FI | 2022-06-27 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | SWYD Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-382 | 2023-03-29 | 4 | CRS-GUP-DHI-DT-23-1848 | 2023-04-19 | NC | DHI-GUP-DT-21-098 | 2021-11-11 | 0 | CRS-GUP-DHI-DT-21-061 | 2021-11-15 | RR | DE-GUP-DT-E-22-630 | 2022-09-07 | 1 | CRS-GUP-DHI-DT-22-827 | 2022-09-22 | NC | DE-GUP-DT-E-22-901 | 2022-11-03 | 2 | CRS-GUP-DHI-DT-22-1041 | 2022-11-16 | NC | DE-GUP-DT-E-23-163 | 2023-02-13 | 3 | CRS-GUP-DHI-DT-23-1579 | 2023-02-23 | RC | DE-GUP-DT-E-23-382 | 2023-03-29 | 4 | CRS-GUP-DHI-DT-23-1848 | 2023-04-19 | NC
| GUP | CA01 | P1 | UAB | 181837 |  | GUP-CA01-P1UAB-181837 | SWITCHYARD CONTROL BUILDING_ROW FRAMING ELEVATION | FI | 2022-06-27 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | SWYD Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-382 | 2023-03-29 | 4 | CRS-GUP-DHI-DT-23-1848 | 2023-04-19 | NC | DHI-GUP-DT-21-098 | 2021-11-11 | 0 | CRS-GUP-DHI-DT-21-061 | 2021-11-15 | RR | DE-GUP-DT-E-22-630 | 2022-09-07 | 1 | CRS-GUP-DHI-DT-22-827 | 2022-09-22 | NC | DE-GUP-DT-E-22-901 | 2022-11-03 | 2 | CRS-GUP-DHI-DT-22-1041 | 2022-11-16 | NC | DE-GUP-DT-E-23-163 | 2023-02-13 | 3 | CRS-GUP-DHI-DT-23-1579 | 2023-02-23 | RC | DE-GUP-DT-E-23-382 | 2023-03-29 | 4 | CRS-GUP-DHI-DT-23-1848 | 2023-04-19 | NC
| GUP | CA01 | P1 | UAB | 181838 |  | GUP-CA01-P1UAB-181838 | SWITCHYARD CONTROL BUILDING_STRUCTURAL MISC. DETAIL | FI | 2022-10-01 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | SWYD Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-382 | 2023-03-29 | 3 | CRS-GUP-DHI-DT-23-1848 | 2023-04-19 | NC | DE-GUP-DT-E-22-630 | 2022-09-07 | 0 | CRS-GUP-DHI-DT-22-827 | 2022-09-22 | NC | DE-GUP-DT-E-22-901 | 2022-11-03 | 1 | CRS-GUP-DHI-DT-22-1041 | 2022-11-16 | NC | DE-GUP-DT-E-23-163 | 2023-02-13 | 2 | CRS-GUP-DHI-DT-23-1579 | 2023-02-23 | NC | DE-GUP-DT-E-23-382 | 2023-03-29 | 3 | CRS-GUP-DHI-DT-23-1848 | 2023-04-19 | NC
| GUP | CA02 | P1 | UAB | 181839 |  | GUP-CA02-P1UAB-181839 | SWITCHYARD CONTROL BUILDING_COLUMN RE-BAR SCHEDULE | FI | 2022-06-27 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | SWYD Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-382 | 2023-03-29 | 4 | CRS-GUP-DHI-DT-23-1848 | 2023-04-19 | NC | DHI-GUP-DT-21-098 | 2021-11-11 | 0 | CRS-GUP-DHI-DT-21-061 | 2021-11-15 | RR | DE-GUP-DT-E-22-630 | 2022-09-07 | 1 | CRS-GUP-DHI-DT-22-827 | 2022-09-22 | NC | DE-GUP-DT-E-22-901 | 2022-11-03 | 2 | CRS-GUP-DHI-DT-22-1041 | 2022-11-16 | NC | DE-GUP-DT-E-23-163 | 2023-02-13 | 3 | CRS-GUP-DHI-DT-23-1579 | 2023-02-23 | NC | DE-GUP-DT-E-23-382 | 2023-03-29 | 4 | CRS-GUP-DHI-DT-23-1848 | 2023-04-19 | NC
| GUP | CA02 | P1 | UAB | 181840 |  | GUP-CA02-P1UAB-181840 | SWITCHYARD CONTROL BUILDING_BEAM & GIRDER RE-BAR SCHEDULE | FI | 2022-06-27 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | SWYD Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-382 | 2023-03-29 | 4 | CRS-GUP-DHI-DT-23-1848 | 2023-04-19 | NC | DHI-GUP-DT-21-098 | 2021-11-11 | 0 | CRS-GUP-DHI-DT-21-061 | 2021-11-15 | RR | DE-GUP-DT-E-22-630 | 2022-09-07 | 1 | CRS-GUP-DHI-DT-22-827 | 2022-09-22 | NC | DE-GUP-DT-E-22-901 | 2022-11-03 | 2 | CRS-GUP-DHI-DT-22-1041 | 2022-11-16 | NC | DE-GUP-DT-E-23-163 | 2023-02-13 | 3 | CRS-GUP-DHI-DT-23-1579 | 2023-02-23 | NC | DE-GUP-DT-E-23-382 | 2023-03-29 | 4 | CRS-GUP-DHI-DT-23-1848 | 2023-04-19 | NC
| GUP | CA02 | P1 | UAB | 181841 |  | GUP-CA02-P1UAB-181841 | SWITCHYARD CONTROL BUILDING_SLAB & MISC. RE-BAR SCHEDULE | FI | 2022-10-01 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | SWYD Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-382 | 2023-03-29 | 3 | CRS-GUP-DHI-DT-23-1579 | 2023-02-23 | NC | DE-GUP-DT-E-22-630 | 2022-09-07 | 0 | CRS-GUP-DHI-DT-22-827 | 2022-09-22 | RC | DE-GUP-DT-E-22-901 | 2022-11-03 | 1 | CRS-GUP-DHI-DT-22-1041 | 2022-11-16 | NC | DE-GUP-DT-E-23-163 | 2023-02-13 | 2 | CRS-GUP-DHI-DT-23-1579 | 2023-02-23 | NC | DE-GUP-DT-E-23-382 | 2023-03-29 | 3
| GUP | CA03 | P1 | UAB | 181842 |  | GUP-CA03-P1UAB-181842 | SWITCHYARD CONTROL BUILDING_PANEL SUPPORT FRAME LAYOUT & DETAIL | FI | 2022-10-01 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | SWYD Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-382 | 2023-03-29 | 1 | CRS-GUP-DHI-DT-23-1579 | 2023-02-23 | NC | DE-GUP-DT-E-23-163 | 2023-02-13 | 0 | CRS-GUP-DHI-DT-23-1579 | 2023-02-23 | NC | DE-GUP-DT-E-23-382 | 2023-03-29 | 1
| GUP | CA06 | P1 | UCB | 182301 |  | GUP-CA06-P1UCB-182301 | BESS ELECTRICAL & CONTROL BUILDING_CALCULATION SHEET | FA | 2022-08-13 | 2022-12-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | BESS Building | Arch. | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-510 | 2023-04-26 | 2 | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | AA | DE-GUP-DT-E-22-786 | 2022-10-11 | A | CRS-GUP-DHI-DT-22-933 | 2022-10-19 | RR | DE-GUP-DT-E-22-932 | 2022-11-10 | B | CRS-GUP-DHI-DT-22-1186 | 2022-11-30 | RC | DE-GUP-DT-E-22-1123 | 2022-12-19 | C | CRS-GUP-DHI-DT-22-1386 | 2023-01-03 | AA | DE-GUP-DT-E-23-190 | 2023-02-16 | 0 | CRS-GUP-DHI-DT-23-1600 | 2023-02-28 | AA | DE-GUP-DT-E-23-374 | 2023-03-27 | 1 | CRS-GUP-DHI-DT-23-1819 | 2023-04-12 | AA | DE-GUP-DT-E-23-510 | 2023-04-26 | 2 | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | AA
| GUP | CA01 | P1 | UCB | 182331 |  | GUP-CA01-P1UCB-182331 | BESS ELECTRICAL & CONTROL BUILDING_FOUNDATION & COLUMN ARRANGEMENT PLAN | FA | 2022-08-13 | 2022-12-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | BESS Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-510 | 2023-04-26 | 2 | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | AA | DE-GUP-DT-E-22-786 | 2022-10-11 | A | CRS-GUP-DHI-DT-22-933 | 2022-10-19 | RR | DE-GUP-DT-E-22-932 | 2022-11-10 | B | CRS-GUP-DHI-DT-22-1186 | 2022-11-30 | RC | DE-GUP-DT-E-22-1123 | 2022-12-19 | C | CRS-GUP-DHI-DT-22-1386 | 2023-01-03 | AA | DE-GUP-DT-E-23-190 | 2023-02-16 | 0 | CRS-GUP-DHI-DT-23-1600 | 2023-02-28 | AA | DE-GUP-DT-E-23-374 | 2023-03-27 | 1 | CRS-GUP-DHI-DT-23-1819 | 2023-04-12 | AA | DE-GUP-DT-E-23-510 | 2023-04-26 | 2 | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | AA
| GUP | CA00 | P1 | UCB | 182310 |  | GUP-CA00-P1UCB-182310 | BESS ELECTRICAL & CONTROL BUILDING_DOOR & WINDOW SCHEDULE | FA | 2022-08-13 | 2022-12-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | BESS Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-685 | 2023-07-12 | 1 | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | AA | DE-GUP-DT-E-22-786 | 2022-10-11 | A | CRS-GUP-DHI-DT-22-933 | 2022-10-19 | RR | DE-GUP-DT-E-22-932 | 2022-11-10 | B | CRS-GUP-DHI-DT-22-1186 | 2022-11-30 | RC | DE-GUP-DT-E-22-1123 | 2022-12-19 | C | CRS-GUP-DHI-DT-22-1386 | 2023-01-03 | RC | DE-GUP-DT-E-23-190 | 2023-02-16 | D | CRS-GUP-DHI-DT-23-1600 | 2023-02-28 | RC | DE-GUP-DT-E-23-374 | 2023-03-27 | E | CRS-GUP-DHI-DT-23-1819 | 2023-04-12 | AA | DE-GUP-DT-E-23-510 | 2023-04-26 | 0(cp) | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | AA | DE-GUP-DT-E-23-685 | 2023-07-12 | 1
| GUP | CA00 | P1 | UCB | 182311 |  | GUP-CA00-P1UCB-182311 | BESS ELECTRICAL & CONTROL BUILDING_GROUND FLOOR & ROOF PLAN | FA | 2022-08-13 | 2022-12-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | BESS Building | Arch. | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-685 | 2023-07-12 | 1 | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | AA | DE-GUP-DT-E-22-786 | 2022-10-11 | A | CRS-GUP-DHI-DT-22-933 | 2022-10-19 | RR | DE-GUP-DT-E-22-932 | 2022-11-10 | B | CRS-GUP-DHI-DT-22-1186 | 2022-11-30 | RC | DE-GUP-DT-E-22-1123 | 2022-12-19 | C | CRS-GUP-DHI-DT-22-1386 | 2023-01-03 | RC | DE-GUP-DT-E-23-190 | 2023-02-16 | D | CRS-GUP-DHI-DT-23-1600 | 2023-02-28 | RC | DE-GUP-DT-E-23-374 | 2023-03-27 | E | CRS-GUP-DHI-DT-23-1819 | 2023-04-12 | AA | DE-GUP-DT-E-23-510 | 2023-04-26 | 0(cp) | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | AA | DE-GUP-DT-E-23-685 | 2023-07-12 | 1
| GUP | CA00 | P1 | UCB | 182312 |  | GUP-CA00-P1UCB-182312 | BESS ELECTRICAL & CONTROL BUILDING_MAIN SECTION | FA | 2022-08-13 | 2022-12-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | BESS Building | Arch. | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-685 | 2023-07-12 | 3 | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | AA | DE-GUP-DT-E-22-786 | 2022-10-11 | A | CRS-GUP-DHI-DT-22-933 | 2022-10-19 | RR | DE-GUP-DT-E-22-932 | 2022-11-10 | B | CRS-GUP-DHI-DT-22-1186 | 2022-11-30 | RC | DE-GUP-DT-E-22-1123 | 2022-12-19 | C | CRS-GUP-DHI-DT-22-1386 | 2023-01-03 | AA | DE-GUP-DT-E-23-190 | 2023-02-16 | 0 | CRS-GUP-DHI-DT-23-1600 | 2023-02-28 | AC | DE-GUP-DT-E-23-374 | 2023-03-27 | 1 | CRS-GUP-DHI-DT-23-1819 | 2023-04-12 | AA | DE-GUP-DT-E-23-510 | 2023-04-26 | 2 | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | AA | DE-GUP-DT-E-23-685 | 2023-07-12 | 3
| GUP | CA00 | P1 | UCB | 182313 |  | GUP-CA00-P1UCB-182313 | BESS ELECTRICAL & CONTROL BUILDING_SIDE ELEVATION | FA | 2022-08-13 | 2022-12-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | BESS Building | Arch. | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-685 | 2023-07-12 | 1 | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | AA | DE-GUP-DT-E-22-786 | 2022-10-11 | A | CRS-GUP-DHI-DT-22-933 | 2022-10-19 | RR | DE-GUP-DT-E-22-932 | 2022-11-10 | B | CRS-GUP-DHI-DT-22-1186 | 2022-11-30 | RC | DE-GUP-DT-E-22-1123 | 2022-12-19 | C | CRS-GUP-DHI-DT-22-1386 | 2023-01-03 | RC | DE-GUP-DT-E-23-190 | 2023-02-16 | D | CRS-GUP-DHI-DT-23-1600 | 2023-02-28 | RC | DE-GUP-DT-E-23-374 | 2023-03-27 | E | CRS-GUP-DHI-DT-23-1819 | 2023-04-12 | AA | DE-GUP-DT-E-23-510 | 2023-04-26 | 0(cp) | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | AA | DE-GUP-DT-E-23-685 | 2023-07-12 | 1
| GUP | CA00 | P1 | UCB | 182314 |  | GUP-CA00-P1UCB-182314 | BESS ELECTRICAL & CONTROL BUILDING_ARCHITECTURAL MISC. DETAIL | FA | 2023-02-07 | 2023-04-30 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | BESS Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-685 | 2023-07-12 | 3 | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | AA | DE-GUP-DT-E-22-786 | 2022-10-11 | A | CRS-GUP-DHI-DT-22-933 | 2022-10-19 | RR | DE-GUP-DT-E-22-932 | 2022-11-10 | B | CRS-GUP-DHI-DT-22-1186 | 2022-11-30 | RC | DE-GUP-DT-E-22-1123 | 2022-12-19 | C | CRS-GUP-DHI-DT-22-1386 | 2023-01-03 | AA | DE-GUP-DT-E-23-190 | 2023-02-16 | 0 | CRS-GUP-DHI-DT-23-1600 | 2023-02-28 | AA | DE-GUP-DT-E-23-374 | 2023-03-27 | 1 | CRS-GUP-DHI-DT-23-1819 | 2023-04-12 | AA | DE-GUP-DT-E-23-510 | 2023-04-26 | 2 | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | AA | DE-GUP-DT-E-23-685 | 2023-07-12 | 3
| GUP | CA00 | P1 | UCB | 182315 |  | GUP-CA00-P1UCB-182315 | BESS ELECTRICAL & CONTROL BUILDING_CEILING PLAN | FI | 2022-08-13 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | BESS Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-510 | 2023-04-26 | 5 | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | NC | DE-GUP-DT-E-22-786 | 2022-10-11 | 0 | CRS-GUP-DHI-DT-22-933 | 2022-10-19 | RR | DE-GUP-DT-E-22-932 | 2022-11-10 | 1 | CRS-GUP-DHI-DT-22-1186 | 2022-11-30 | RC | DE-GUP-DT-E-22-1123 | 2022-12-19 | 2 | CRS-GUP-DHI-DT-22-1386 | 2023-01-03 | NC | DE-GUP-DT-E-23-190 | 2023-02-16 | 3 | CRS-GUP-DHI-DT-23-1600 | 2023-02-28 | NC | DE-GUP-DT-E-23-374 | 2023-03-27 | 4 | CRS-GUP-DHI-DT-23-1819 | 2023-04-12 | NC | DE-GUP-DT-E-23-510 | 2023-04-26 | 5 | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | NC
| GUP | CA01 | P1 | UCB | 182333 |  | GUP-CA01-P1UCB-182333 | BESS ELECTRICAL & CONTROL BUILDING_GROUND FLOOR FRAMING PLAN | FI | 2022-08-13 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | BESS Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-685 | 2023-07-12 | 6 | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | NC | DE-GUP-DT-E-22-786 | 2022-10-11 | 0 | CRS-GUP-DHI-DT-22-933 | 2022-10-19 | RR | DE-GUP-DT-E-22-932 | 2022-11-10 | 1 | CRS-GUP-DHI-DT-22-1186 | 2022-11-30 | NC | DE-GUP-DT-E-22-1123 | 2022-12-19 | 2 | CRS-GUP-DHI-DT-22-1386 | 2023-01-03 | NC | DE-GUP-DT-E-23-190 | 2023-02-16 | 3 | CRS-GUP-DHI-DT-23-1600 | 2023-02-28 | NC | DE-GUP-DT-E-23-374 | 2023-03-27 | 4 | CRS-GUP-DHI-DT-23-1819 | 2023-04-12 | NC | DE-GUP-DT-E-23-510 | 2023-04-26 | 5 | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | NC | DE-GUP-DT-E-23-685 | 2023-07-12 | 6
| GUP | CA01 | P1 | UCB | 182334 |  | GUP-CA01-P1UCB-182334 | BESS ELECTRICAL & CONTROL BUILDING_ROOF FRAMING PLAN | FI | 2022-08-13 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | BESS Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-685 | 2023-07-12 | 6 | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | NC | DE-GUP-DT-E-22-786 | 2022-10-11 | 0 | CRS-GUP-DHI-DT-22-933 | 2022-10-19 | RR | DE-GUP-DT-E-22-932 | 2022-11-10 | 1 | CRS-GUP-DHI-DT-22-1186 | 2022-11-30 | RC | DE-GUP-DT-E-22-1123 | 2022-12-19 | 2 | CRS-GUP-DHI-DT-22-1386 | 2023-01-03 | RC | DE-GUP-DT-E-23-190 | 2023-02-16 | 3 | CRS-GUP-DHI-DT-23-1600 | 2023-02-28 | NC | DE-GUP-DT-E-23-374 | 2023-03-27 | 4 | CRS-GUP-DHI-DT-23-1819 | 2023-04-12 | NC | DE-GUP-DT-E-23-510 | 2023-04-26 | 5 | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | NC | DE-GUP-DT-E-23-685 | 2023-07-12 | 6
| GUP | CA01 | P1 | UCB | 182335 |  | GUP-CA01-P1UCB-182335 | BESS ELECTRICAL & CONTROL BUILDING_LINE FRAMING ELEVATION | FI | 2022-08-13 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | BESS Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-685 | 2023-07-12 | 6 | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | NC | DE-GUP-DT-E-22-786 | 2022-10-11 | 0 | CRS-GUP-DHI-DT-22-933 | 2022-10-19 | RR | DE-GUP-DT-E-22-932 | 2022-11-10 | 1 | CRS-GUP-DHI-DT-22-1186 | 2022-11-30 | NC | DE-GUP-DT-E-22-1123 | 2022-12-19 | 2 | CRS-GUP-DHI-DT-22-1386 | 2023-01-03 | NC | DE-GUP-DT-E-23-190 | 2023-02-16 | 3 | CRS-GUP-DHI-DT-23-1600 | 2023-02-28 | RC | DE-GUP-DT-E-23-374 | 2023-03-27 | 4 | CRS-GUP-DHI-DT-23-1819 | 2023-04-12 | NC | DE-GUP-DT-E-23-510 | 2023-04-26 | 5 | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | NC | DE-GUP-DT-E-23-685 | 2023-07-12 | 6
| GUP | CA01 | P1 | UCB | 182336 |  | GUP-CA01-P1UCB-182336 | BESS ELECTRICAL & CONTROL BUILDING_ROW FRAMING ELEVATION | FI | 2022-08-13 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | BESS Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-510 | 2023-04-26 | 5 | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | NC | DE-GUP-DT-E-22-786 | 2022-10-11 | 0 | CRS-GUP-DHI-DT-22-933 | 2022-10-19 | RR | DE-GUP-DT-E-22-932 | 2022-11-10 | 1 | CRS-GUP-DHI-DT-22-1186 | 2022-11-30 | RC | DE-GUP-DT-E-22-1123 | 2022-12-19 | 2 | CRS-GUP-DHI-DT-22-1386 | 2023-01-03 | NC | DE-GUP-DT-E-23-190 | 2023-02-16 | 3 | CRS-GUP-DHI-DT-23-1600 | 2023-02-28 | RC | DE-GUP-DT-E-23-374 | 2023-03-27 | 4 | CRS-GUP-DHI-DT-23-1819 | 2023-04-12 | NC | DE-GUP-DT-E-23-510 | 2023-04-26 | 5 | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | NC
| GUP | CA01 | P1 | UCB | 182337 |  | GUP-CA01-P1UCB-182337 | BESS ELECTRICAL & CONTROL BUILDING_STRUCTURAL MISC. DETAIL | FI | 2022-08-13 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | BESS Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-510 | 2023-04-26 | 5 | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | NC | DE-GUP-DT-E-22-786 | 2022-10-11 | 0 | CRS-GUP-DHI-DT-22-933 | 2022-10-19 | RR | DE-GUP-DT-E-22-932 | 2022-11-10 | 1 | CRS-GUP-DHI-DT-22-1186 | 2022-11-30 | NC | DE-GUP-DT-E-22-1123 | 2022-12-19 | 2 | CRS-GUP-DHI-DT-22-1386 | 2023-01-03 | NC | DE-GUP-DT-E-23-190 | 2023-02-16 | 3 | CRS-GUP-DHI-DT-23-1600 | 2023-02-28 | NC | DE-GUP-DT-E-23-374 | 2023-03-27 | 4 | CRS-GUP-DHI-DT-23-1819 | 2023-04-12 | NC | DE-GUP-DT-E-23-510 | 2023-04-26 | 5 | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | NC
| GUP | CA02 | P1 | UCB | 182338 |  | GUP-CA02-P1UCB-182338 | BESS ELECTRICAL & CONTROL BUILDING_RE-BAR SCHEDULE | FI | 2022-08-13 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | BESS Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-510 | 2023-04-26 | 5 | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | NC | DE-GUP-DT-E-22-786 | 2022-10-11 | 0 | CRS-GUP-DHI-DT-22-933 | 2022-10-19 | RR | DE-GUP-DT-E-22-932 | 2022-11-10 | 1 | CRS-GUP-DHI-DT-22-1186 | 2022-11-30 | NC | DE-GUP-DT-E-22-1123 | 2022-12-19 | 2 | CRS-GUP-DHI-DT-22-1386 | 2023-01-03 | NC | DE-GUP-DT-E-23-190 | 2023-02-16 | 3 | CRS-GUP-DHI-DT-23-1600 | 2023-02-28 | NC | DE-GUP-DT-E-23-374 | 2023-03-27 | 4 | CRS-GUP-DHI-DT-23-1819 | 2023-04-12 | NC | DE-GUP-DT-E-23-510 | 2023-04-26 | 5 | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | NC
| GUP | CA02 | P1 | UCB | 182339 |  | GUP-CA02-P1UCB-182339 | BESS ELECTRICAL & CONTROL BUILDING_SLAB & MISC. RE-BAR SCHEDULE | FI | 2023-02-07 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | BESS Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-510 | 2023-04-26 | 5 | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | NC | DE-GUP-DT-E-22-786 | 2022-10-11 | 0 | CRS-GUP-DHI-DT-22-933 | 2022-10-19 | RR | DE-GUP-DT-E-22-932 | 2022-11-10 | 1 | CRS-GUP-DHI-DT-22-1186 | 2022-11-30 | NC | DE-GUP-DT-E-22-1123 | 2022-12-19 | 2 | CRS-GUP-DHI-DT-22-1386 | 2023-01-03 | NC | DE-GUP-DT-E-23-190 | 2023-02-16 | 3 | CRS-GUP-DHI-DT-23-1600 | 2023-02-28 | NC | DE-GUP-DT-E-23-374 | 2023-03-27 | 4 | CRS-GUP-DHI-DT-23-1819 | 2023-04-12 | NC | DE-GUP-DT-E-23-510 | 2023-04-26 | 5 | CRS-GUP-DHI-DT-23-1929 | 2023-05-05 | NC
| GUP | CA06 | P1 | UNX | 183602 |  | GUP-CA06-P1UNX-183602 | GCB SHELTER FOR GT_CALCULATION SHEET | FA | 2022-07-10 | 2022-11-10 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GCB SHELTER FOR GT | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-254 | 2024-10-24 | 2 | 자체 CRS 개정 후 제출 | 2024-10-23 | N/A | DE-GUP-DT-E-22-376 | 2022-07-08 | A | CRS-GUP-DHI-DT-22-567 | 2022-08-02 | RC | DE-GUP-DT-E-22-693 | 2022-09-23 | B | CRS-GUP-DHI-DT-22-935 | 2022-10-21 | AC | DE-GUP-DT-E-22-905 | 2022-11-03 | C | CRS-GUP-DHI-DT-22-1042 | 2022-11-16 | AA | DE-GUP-DT-E-22-1051 | 2022-12-08 | 0 | CRS-GUP-DHI-DT-22-1361 | 2022-12-31 | AA | DE-GUP-DT-E-23-920 | 2023-11-20 | 1 | 자체 CRS 개정 후 제출 | 2024-10-23 | N/A | DE-GUP-DT-E-24-254 | 2024-10-24 | 2
| GUP | CA01 | P1 | UNX | 183641 |  | GUP-CA01-P1UNX-183641 | GCB SHELTER FOR GT_FOUNDATION ARRANGEMENT PLAN | FA | 2022-07-10 | 2022-11-10 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GCB SHELTER FOR ST | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-1051 | 2022-12-08 | 0 | CRS-GUP-DHI-DT-22-1361 | 2022-12-31 | AA | DE-GUP-DT-E-22-376 | 2022-07-08 | A | CRS-GUP-DHI-DT-22-567 | 2022-08-02 | RC | DE-GUP-DT-E-22-693 | 2022-09-23 | B | CRS-GUP-DHI-DT-22-935 | 2022-10-21 | AC | DE-GUP-DT-E-22-905 | 2022-11-03 | C | CRS-GUP-DHI-DT-22-1042 | 2022-11-16 | AA | DE-GUP-DT-E-22-1051 | 2022-12-08 | 0 | CRS-GUP-DHI-DT-22-1361 | 2022-12-31 | AA
| GUP | CA00 | P1 | UNX | 183621 |  | GUP-CA00-P1UNX-183621 | GCB SHELTER FOR GT_GROUND FLOOR & ROOF PLAN | FA | 2022-07-10 | 2022-11-10 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GCB SHELTER FOR ST | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-920 | 2023-11-20 | 1 | CRS-GUP-DHI-DT-22-1361 | 2022-12-31 | AA | DE-GUP-DT-E-22-376 | 2022-07-08 | A | CRS-GUP-DHI-DT-22-567 | 2022-08-02 | RC | DE-GUP-DT-E-22-693 | 2022-09-23 | B | CRS-GUP-DHI-DT-22-935 | 2022-10-21 | AC | DE-GUP-DT-E-22-905 | 2022-11-03 | C | CRS-GUP-DHI-DT-22-1042 | 2022-11-16 | AA | DE-GUP-DT-E-22-1051 | 2022-12-08 | 0 | CRS-GUP-DHI-DT-22-1361 | 2022-12-31 | AA | DE-GUP-DT-E-23-920 | 2023-11-20 | 1
| GUP | CA00 | P1 | UNX | 183622 |  | GUP-CA00-P1UNX-183622 | GCB SHELTER FOR GT_MAIN SECTION | FA | 2022-07-10 | 2022-11-10 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GCB SHELTER FOR ST | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-254 | 2024-10-24 | 2 | 자체 CRS 개정 후 제출 | 2024-10-23 | N/A | DE-GUP-DT-E-22-376 | 2022-07-08 | A | CRS-GUP-DHI-DT-22-567 | 2022-08-02 | RC | DE-GUP-DT-E-22-693 | 2022-09-23 | B | CRS-GUP-DHI-DT-22-935 | 2022-10-21 | AC | DE-GUP-DT-E-22-905 | 2022-11-03 | C | CRS-GUP-DHI-DT-22-1042 | 2022-11-16 | AA | DE-GUP-DT-E-22-1051 | 2022-12-08 | 0 | CRS-GUP-DHI-DT-22-1361 | 2022-12-31 | AA | DE-GUP-DT-E-23-920 | 2023-11-20 | 1 | 자체 CRS 개정 후 제출 | 2024-10-23 | N/A | DE-GUP-DT-E-24-254 | 2024-10-24 | 2
| GUP | CA00 | P1 | UNX | 183623 |  | GUP-CA00-P1UNX-183623 | GCB SHELTER FOR GT_SIDE ELEVATION | FA | 2022-07-10 | 2022-11-10 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GCB SHELTER FOR ST | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-254 | 2024-10-24 | 2 | 자체 CRS 개정 후 제출 | 2024-10-23 | N/A | DE-GUP-DT-E-22-376 | 2022-07-08 | A | CRS-GUP-DHI-DT-22-567 | 2022-08-02 | RC | DE-GUP-DT-E-22-693 | 2022-09-23 | B | CRS-GUP-DHI-DT-22-935 | 2022-10-21 | AC | DE-GUP-DT-E-22-905 | 2022-11-03 | C | CRS-GUP-DHI-DT-22-1042 | 2022-11-16 | AA | DE-GUP-DT-E-22-1051 | 2022-12-08 | 0 | CRS-GUP-DHI-DT-22-1361 | 2022-12-31 | AA | DE-GUP-DT-E-23-920 | 2023-11-20 | 1 | 자체 CRS 개정 후 제출 | 2024-10-23 | N/A | DE-GUP-DT-E-24-254 | 2024-10-24 | 2
| GUP | CA03 | P1 | UNX | 183661 |  | GUP-CA03-P1UNX-183661 | GCB SHELTER FOR GT_COLUMN ARRANGEMENT & ROOF FRAMING PLAN | FI | 2022-07-10 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GCB SHELTER FOR ST | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-1051 | 2022-12-08 | 3 | CRS-GUP-DHI-DT-22-1361 | 2022-12-31 | NC | DE-GUP-DT-E-22-376 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-567 | 2022-08-02 | RC | DE-GUP-DT-E-22-693 | 2022-09-23 | 1 | CRS-GUP-DHI-DT-22-935 | 2022-10-21 | NC | DE-GUP-DT-E-22-905 | 2022-11-03 | 2 | CRS-GUP-DHI-DT-22-1042 | 2022-11-16 | NC | DE-GUP-DT-E-22-1051 | 2022-12-08 | 3 | CRS-GUP-DHI-DT-22-1361 | 2022-12-31 | NC
| GUP | CA03 | P1 | UNX | 183662 |  | GUP-CA03-P1UNX-183662 | GCB SHELTER FOR GT_LINE & ROW FRAMING ELEVATION | FI | 2022-07-10 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GCB SHELTER FOR ST | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-254 | 2024-10-24 | 4 | CRS-GUP-DHI-DT-22-1361 | 2022-12-31 | NC | DE-GUP-DT-E-22-376 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-567 | 2022-08-02 | RC | DE-GUP-DT-E-22-693 | 2022-09-23 | 1 | CRS-GUP-DHI-DT-22-935 | 2022-10-21 | NC | DE-GUP-DT-E-22-905 | 2022-11-03 | 2 | CRS-GUP-DHI-DT-22-1042 | 2022-11-16 | NC | DE-GUP-DT-E-22-1051 | 2022-12-08 | 3 | CRS-GUP-DHI-DT-22-1361 | 2022-12-31 | NC | DE-GUP-DT-E-24-254 | 2024-10-24 | 4
| GUP | CA03 | P1 | UNX | 183663 |  | GUP-CA03-P1UNX-183663 | GCB SHELTER FOR GT_PURLIN ARRANGEMENT PLAN | FI | 2022-07-10 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GCB SHELTER FOR ST | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-254 | 2024-10-24 | 4 | CRS-GUP-DHI-DT-22-1361 | 2022-12-31 | NC | DE-GUP-DT-E-22-376 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-567 | 2022-08-02 | RC | DE-GUP-DT-E-22-693 | 2022-09-23 | 1 | CRS-GUP-DHI-DT-22-935 | 2022-10-21 | NC | DE-GUP-DT-E-22-905 | 2022-11-03 | 2 | CRS-GUP-DHI-DT-22-1042 | 2022-11-16 | NC | DE-GUP-DT-E-22-1051 | 2022-12-08 | 3 | CRS-GUP-DHI-DT-22-1361 | 2022-12-31 | NC | DE-GUP-DT-E-24-254 | 2024-10-24 | 4
| GUP | CA06 | P1 | UNX | 183601 |  | GUP-CA06-P1UNX-183601 | GCB SHELTER FOR ST_CALCULATION SHEET | FA | 2022-06-01 | 2022-09-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GCB SHELTER FOR ST | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-253 | 2024-10-24 | 3 | 자체 CRS 개정 후 제출 | 2024-10-23 | N/A | DHI-GUP-DT-21-181 | 2021-12-17 | 0 | CRS-GUP-DHI-DT-21-132 | 2022-01-11 | RC | DHI-GUP-DT-22-056 | 2022-01-28 | 1 | CRS-GUP-DHI-DT-22-218 | 2022-02-20 | NC | DE-GUP-DT-E-22-408 | 2022-07-18 | C | CRS-GUP-DHI-DT-22-585 | 2022-08-08 | AA | DE-GUP-DT-E-22-865 | 2022-10-27 | 0 | CRS-GUP-DHI-DT-22-1058 | 2022-11-17 | AC | DE-GUP-DT-E-22-1019 | 2022-11-30 | 1 | CRS-GUP-DHI-DT-22-1274 | 2022-12-16 | AA | DE-GUP-DT-E-23-896 | 2023-11-09 | 2 | 자체 CRS 개정 후 제출 | 2024-10-23 | N/A | DE-GUP-DT-E-24-253 | 2024-10-24 | 3
| GUP | CA01 | P1 | UNX | 183631 |  | GUP-CA01-P1UNX-183631 | GCB SHELTER FOR ST_FOUNDATION ARRANGEMENT PLAN | FA | 2022-06-01 | 2022-09-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GCB SHELTER FOR ST | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-1019 | 2022-11-30 | 1 | CRS-GUP-DHI-DT-22-1274 | 2022-12-16 | AA | DHI-GUP-DT-21-181 | 2021-12-17 | 0 | CRS-GUP-DHI-DT-21-132 | 2022-01-11 | RC | DHI-GUP-DT-22-056 | 2022-01-28 | 1 | CRS-GUP-DHI-DT-22-218 | 2022-02-20 | NC | DE-GUP-DT-E-22-408 | 2022-07-18 | C | CRS-GUP-DHI-DT-22-585 | 2022-08-08 | AA | DE-GUP-DT-E-22-865 | 2022-10-27 | 0 | CRS-GUP-DHI-DT-22-1058 | 2022-11-17 | AC | DE-GUP-DT-E-22-1019 | 2022-11-30 | 1 | CRS-GUP-DHI-DT-22-1274 | 2022-12-16 | AA
| GUP | CA00 | P1 | UNX | 183611 |  | GUP-CA00-P1UNX-183611 | GCB SHELTER FOR ST_GROUND FLOOR & ROOF PLAN | FA | 2022-06-01 | 2022-09-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GCB SHELTER FOR ST | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-896 | 2023-11-09 | 2 | CRS-GUP-DHI-DT-22-1274 | 2022-12-16 | AA | DHI-GUP-DT-21-181 | 2021-12-17 | A | CRS-GUP-DHI-DT-21-132 | 2022-01-11 | AC | DHI-GUP-DT-22-056 | 2022-01-28 | B | CRS-GUP-DHI-DT-22-218 | 2022-02-20 | AC | DE-GUP-DT-E-22-408 | 2022-07-18 | C | CRS-GUP-DHI-DT-22-585 | 2022-08-08 | AC | DE-GUP-DT-E-22-865 | 2022-10-27 | 0(CP) | CRS-GUP-DHI-DT-22-1058 | 2022-11-17 | AC | DE-GUP-DT-E-22-1019 | 2022-11-30 | 1(CP) | CRS-GUP-DHI-DT-22-1274 | 2022-12-16 | AA | DE-GUP-DT-E-23-896 | 2023-11-09 | 2
| GUP | CA00 | P1 | UNX | 183612 |  | GUP-CA00-P1UNX-183612 | GCB SHELTER FOR ST_MAIN SECTION | FA | 2022-06-01 | 2022-09-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GCB SHELTER FOR ST | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-253 | 2024-10-24 | 3 | 자체 CRS 개정 후 제출 | 2024-10-23 | N/A | DHI-GUP-DT-21-181 | 2021-12-17 | A | CRS-GUP-DHI-DT-21-132 | 2022-01-11 | AC | DHI-GUP-DT-22-056 | 2022-01-28 | B | CRS-GUP-DHI-DT-22-218 | 2022-02-20 | AC | DE-GUP-DT-E-22-408 | 2022-07-18 | C | CRS-GUP-DHI-DT-22-585 | 2022-08-08 | AC | DE-GUP-DT-E-22-865 | 2022-10-27 | 0(CP) | CRS-GUP-DHI-DT-22-1058 | 2022-11-17 | AC | DE-GUP-DT-E-22-1019 | 2022-11-30 | 1(CP) | CRS-GUP-DHI-DT-22-1274 | 2022-12-16 | AA | DE-GUP-DT-E-23-896 | 2023-11-09 | 2 | 자체 CRS 개정 후 제출 | 2024-10-23 | N/A | DE-GUP-DT-E-24-253 | 2024-10-24 | 3
| GUP | CA00 | P1 | UNX | 183613 |  | GUP-CA00-P1UNX-183613 | GCB SHELTER FOR ST_SIDE ELEVATION | FA | 2022-06-01 | 2022-09-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GCB SHELTER FOR ST | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-253 | 2024-10-24 | 3 | 자체 CRS 개정 후 제출 | 2024-10-23 | N/A | DHI-GUP-DT-21-181 | 2021-12-17 | A | CRS-GUP-DHI-DT-21-132 | 2022-01-11 | AC | DHI-GUP-DT-22-056 | 2022-01-28 | B | CRS-GUP-DHI-DT-22-218 | 2022-02-20 | AC | DE-GUP-DT-E-22-408 | 2022-07-18 | C | CRS-GUP-DHI-DT-22-585 | 2022-08-08 | AC | DE-GUP-DT-E-22-865 | 2022-10-27 | 0(CP) | CRS-GUP-DHI-DT-22-1058 | 2022-11-17 | AC | DE-GUP-DT-E-22-1019 | 2022-11-30 | 1(CP) | CRS-GUP-DHI-DT-22-1274 | 2022-12-16 | AA | DE-GUP-DT-E-23-896 | 2023-11-09 | 2 | 자체 CRS 개정 후 제출 | 2024-10-23 | N/A | DE-GUP-DT-E-24-253 | 2024-10-24 | 3
| GUP | CA03 | P1 | UNX | 183651 |  | GUP-CA03-P1UNX-183651 | GCB SHELTER FOR ST_COLUMN ARRANGEMENT & ROOF FRAMING PLAN | FI | 2022-06-01 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GCB SHELTER FOR ST | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-896 | 2023-11-09 | 5 | CRS-GUP-DHI-DT-22-1274 | 2022-12-16 | NC | DHI-GUP-DT-21-181 | 2021-12-17 | 0 | CRS-GUP-DHI-DT-21-132 | 2022-01-11 | NC | DHI-GUP-DT-22-056 | 2022-01-28 | 1 | CRS-GUP-DHI-DT-22-218 | 2022-02-20 | NC | DE-GUP-DT-E-22-408 | 2022-07-18 | 2 | CRS-GUP-DHI-DT-22-585 | 2022-08-08 | NC | DE-GUP-DT-E-22-865 | 2022-10-27 | 3 | CRS-GUP-DHI-DT-22-1158 | 2022-11-24 | NC | DE-GUP-DT-E-22-1019 | 2022-11-30 | 4 | CRS-GUP-DHI-DT-22-1274 | 2022-12-16 | NC | DE-GUP-DT-E-23-896 | 2023-11-09 | 5
| GUP | CA03 | P1 | UNX | 183652 |  | GUP-CA03-P1UNX-183652 | GCB SHELTER FOR ST_LINE & ROW FRAMING ELEVATION | FI | 2022-06-01 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GCB SHELTER FOR ST | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-253 | 2024-10-24 | 6 | 자체 CRS 개정 후 제출 | 2024-10-23 | N/A | DHI-GUP-DT-21-181 | 2021-12-17 | 0 | CRS-GUP-DHI-DT-21-132 | 2022-01-11 | NC | DHI-GUP-DT-22-056 | 2022-01-28 | 1 | CRS-GUP-DHI-DT-22-218 | 2022-02-20 | NC | DE-GUP-DT-E-22-408 | 2022-07-18 | 2 | CRS-GUP-DHI-DT-22-585 | 2022-08-08 | NC | DE-GUP-DT-E-22-865 | 2022-10-27 | 3 | CRS-GUP-DHI-DT-22-1158 | 2022-11-24 | NC | DE-GUP-DT-E-22-1019 | 2022-11-30 | 4 | CRS-GUP-DHI-DT-22-1274 | 2022-12-16 | NC | DE-GUP-DT-E-23-896 | 2023-11-09 | 5 | 자체 CRS 개정 후 제출 | 2024-10-23 | N/A | DE-GUP-DT-E-24-253 | 2024-10-24 | 6
| GUP | CA03 | P1 | UNX | 183653 |  | GUP-CA03-P1UNX-183653 | GCB SHELTER FOR ST_PURLIN ARRANGEMENT PLAN | FI | 2022-06-01 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | GCB SHELTER FOR ST | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-253 | 2024-10-24 | 5 | CRS-GUP-DHI-DT-22-1274 | 2022-12-16 | NC | DHI-GUP-DT-21-181 | 2021-12-17 | 0 | CRS-GUP-DHI-DT-21-132 | 2022-01-11 | NC | DHI-GUP-DT-22-056 | 2022-01-28 | 1 | CRS-GUP-DHI-DT-22-218 | 2022-02-20 | NC | DE-GUP-DT-E-22-408 | 2022-07-18 | 2 | CRS-GUP-DHI-DT-22-585 | 2022-08-08 | NC | DE-GUP-DT-E-22-865 | 2022-10-27 | 3 | CRS-GUP-DHI-DT-22-1158 | 2022-11-24 | NC | DE-GUP-DT-E-22-1019 | 2022-11-30 | 4 | CRS-GUP-DHI-DT-22-1274 | 2022-12-16 | NC | DE-GUP-DT-E-24-253 | 2024-10-24 | 5
| GUP | CA06 | P1 | UGD | 181601 |  | GUP-CA06-P1UGD-181601 | WT & WWT BLDG & SHELTER_CALCULATION SHEET | FA | 2022-01-30 | 2022-09-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | WT & WWT Building | Arch. | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-124 | 2023-02-06 | 1 | CRS-GUP-DHI-DT-23-1623 | 2023-03-02 | AA | DHI-GUP-DT-21-042 | 2021-09-30 | 0 | N/A | 2022-01-13 | N/A | DHI-GUP-DT-22-017 | 2022-01-14 | B | CRS-GUP-DHI-DT-21-181 | 2022-02-04 | RC | DHI-GUP-DT-22-112 | 2022-03-11 | C | CRS-GUP-DHI-DT-22-244 | 2022-03-11 | RR | DE-GUP-DT-E-22-377 | 2022-07-08 | D | CRS-GUP-DHI-DT-22-542 | 2022-07-25 | RC | DE-GUP-DT-E-22-512 | 2022-08-18 | E | CRS-GUP-DHI-DT-22-714 | 2022-09-05 | RC | DE-GUP-DT-E-22-737 | 2022-09-30 | F | CRS-GUP-DHI-DT-22-894 | 2022-10-10 | AC | DE-GUP-DT-E-22-913 | 2022-11-04 | G | CRS-GUP-DHI-DT-22-1046 | 2022-11-16 | AA | DE-GUP-DT-E-22-1073 | 2022-12-09 | 0 | CRS-GUP-DHI-DT-22-1330 | 2022-12-28 | AA | DE-GUP-DT-E-23-124 | 2023-02-06 | 1 | CRS-GUP-DHI-DT-23-1623 | 2023-03-02 | AA
| GUP | CA01 | P1 | UGD | 181631 |  | GUP-CA01-P1UGD-181631 | WT & WWT BLDG & SHELTER_FOUNDATION ARRANGEMENT PLAN | FA | 2022-01-30 | 2022-09-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | WT & WWT Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-124 | 2023-02-06 | 2 | CRS-GUP-DHI-DT-23-1623 | 2023-03-02 | AA | DHI-GUP-DT-22-112 | 2022-03-11 | A | CRS-GUP-DHI-DT-22-244 | 2022-03-11 | RR | DE-GUP-DT-E-22-377 | 2022-07-08 | B | CRS-GUP-DHI-DT-22-542 | 2022-07-25 | RC | DE-GUP-DT-E-22-512 | 2022-08-18 | C | CRS-GUP-DHI-DT-22-714 | 2022-09-05 | RC | DE-GUP-DT-E-22-737 | 2022-09-30 | D | CRS-GUP-DHI-DT-22-894 | 2022-10-10 | AC | DE-GUP-DT-E-22-913 | 2022-11-04 | E | CRS-GUP-DHI-DT-22-1046 | 2022-11-16 | AA | DE-GUP-DT-E-22-1073 | 2022-12-09 | 0 | CRS-GUP-DHI-DT-22-1330 | 2022-12-28 | AA | DE-GUP-DT-E-23-026 | 2023-01-13 | 1 | CRS-GUP-DHI-DT-22-1447 | 2023-02-01 | AA | DE-GUP-DT-E-23-124 | 2023-02-06 | 2 | CRS-GUP-DHI-DT-23-1623 | 2023-03-02 | AA
| GUP | CA02 | P1 | UGD | 181632 |  | GUP-CA02-P1UGD-181632 | WT & WWT BLDG & SHELTER_FOUNDATION RE-BAR SCHEDULE | FI | 2022-01-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | WT & WWT Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-124 | 2023-02-06 | 9 | CRS-GUP-DHI-DT-23-1623 | 2023-03-02 | NC | DHI-GUP-DT-21-042 | 2021-09-30 | 0 | CRS-GUP-DHI-DT-21-033 | 2021-10-06 | RC | DHI-GUP-DT-22-017 | 2022-01-14 | 1 | CRS-GUP-DHI-DT-21-181 | 2022-02-04 | NC | DHI-GUP-DT-22-112 | 2022-03-11 | 2 | CRS-GUP-DHI-DT-22-244 | 2022-03-11 | RR | DE-GUP-DT-E-22-377 | 2022-07-08 | 3 | CRS-GUP-DHI-DT-22-542 | 2022-07-25 | RC | DE-GUP-DT-E-22-512 | 2022-08-18 | 4 | CRS-GUP-DHI-DT-22-714 | 2022-09-05 | RC | DE-GUP-DT-E-22-737 | 2022-09-30 | 5 | CRS-GUP-DHI-DT-22-894 | 2022-10-10 | AC | DE-GUP-DT-E-22-913 | 2022-11-04 | 6 | CRS-GUP-DHI-DT-22-1046 | 2022-11-16 | NC | DE-GUP-DT-E-22-1073 | 2022-12-09 | 7 | CRS-GUP-DHI-DT-22-1330 | 2022-12-28 | NC | DE-GUP-DT-E-23-026 | 2023-01-13 | 8 | CRS-GUP-DHI-DT-22-1447 | 2023-02-01 | NC | DE-GUP-DT-E-23-124 | 2023-02-06 | 9 | CRS-GUP-DHI-DT-23-1623 | 2023-03-02 | NC
| GUP | CA00 | P1 | UGD | 181611 |  | GUP-CA00-P1UGD-181611 | WT & WWT BLDG & SHELTER_INTERIOR FINISH SCHEDULE | FA | 2022-01-30 | 2022-09-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | WT & WWT Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-124 | 2023-02-06 | 2 | CRS-GUP-DHI-DT-23-1623 | 2023-03-02 | AA | DHI-GUP-DT-21-042 | 2021-09-30 | A | CRS-GUP-DHI-DT-21-033 | 2021-10-06 | RR | DHI-GUP-DT-22-017 | 2022-01-14 | B | CRS-GUP-DHI-DT-21-181 | 2022-02-04 | RC | DHI-GUP-DT-22-112 | 2022-03-11 | C | CRS-GUP-DHI-DT-22-244 | 2022-03-11 | RR | DE-GUP-DT-E-22-377 | 2022-07-08 | D | CRS-GUP-DHI-DT-22-542 | 2022-07-25 | RC | DE-GUP-DT-E-22-512 | 2022-08-18 | E | CRS-GUP-DHI-DT-22-714 | 2022-09-05 | AC | DE-GUP-DT-E-22-737 | 2022-09-30 | F | CRS-GUP-DHI-DT-22-894 | 2022-10-10 | AC | DE-GUP-DT-E-22-913 | 2022-11-04 | G | CRS-GUP-DHI-DT-22-1046 | 2022-11-16 | AA | DE-GUP-DT-E-22-1073 | 2022-12-09 | 0 | CRS-GUP-DHI-DT-22-1330 | 2022-12-28 | AA | DE-GUP-DT-E-23-026 | 2023-01-13 | 1 | CRS-GUP-DHI-DT-22-1447 | 2023-02-01 | AA | DE-GUP-DT-E-23-124 | 2023-02-06 | 2 | CRS-GUP-DHI-DT-23-1623 | 2023-03-02 | AA
| GUP | CA00 | P1 | UGD | 181612 |  | GUP-CA00-P1UGD-181612 | WT & WWT BLDG & SHELTER_DOOR & WINDOW SCHEDULE | FA | 2022-01-30 | 2022-09-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | WT & WWT Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-797 | 2023-09-07 | 3 | CRS-GUP-DHI-DT-23-2117 | 2023-09-27 | AA | DHI-GUP-DT-21-042 | 2021-09-30 | A | CRS-GUP-DHI-DT-21-033 | 2021-10-06 | RR | DHI-GUP-DT-22-017 | 2022-01-14 | B | CRS-GUP-DHI-DT-21-181 | 2022-02-04 | RC | DHI-GUP-DT-22-112 | 2022-03-11 | C | CRS-GUP-DHI-DT-22-244 | 2022-03-11 | RR | DE-GUP-DT-E-22-377 | 2022-07-08 | D | CRS-GUP-DHI-DT-22-542 | 2022-07-25 | AC | DE-GUP-DT-E-22-512 | 2022-08-18 | E | CRS-GUP-DHI-DT-22-714 | 2022-09-05 | AC | DE-GUP-DT-E-22-737 | 2022-09-30 | F | CRS-GUP-DHI-DT-22-894 | 2022-10-10 | AC | DE-GUP-DT-E-22-913 | 2022-11-04 | G | CRS-GUP-DHI-DT-22-1046 | 2022-11-16 | AA | DE-GUP-DT-E-22-1073 | 2022-12-09 | 0 | CRS-GUP-DHI-DT-22-1330 | 2022-12-28 | AA | DE-GUP-DT-E-23-026 | 2023-01-13 | 1 | CRS-GUP-DHI-DT-22-1447 | 2023-02-01 | AA | DE-GUP-DT-E-23-124 | 2023-02-06 | 2 | CRS-GUP-DHI-DT-23-1623 | 2023-03-02 | AA | DE-GUP-DT-E-23-797 | 2023-09-07 | 3 | CRS-GUP-DHI-DT-23-2117 | 2023-09-27 | AA
| GUP | CA00 | P1 | UGD | 181613 |  | GUP-CA00-P1UGD-181613 | WT & WWT BLDG & SHELTER_BASEMENT FLOOR PLAN | FA | 2022-01-30 | 2022-09-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | WT & WWT Building | Arch. | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-124 | 2023-02-06 | 2 | CRS-GUP-DHI-DT-23-1623 | 2023-03-02 | AA | DHI-GUP-DT-21-042 | 2021-09-30 | A | CRS-GUP-DHI-DT-21-033 | 2021-10-06 | RR | DHI-GUP-DT-22-017 | 2022-01-14 | B | CRS-GUP-DHI-DT-21-181 | 2022-02-04 | RC | DHI-GUP-DT-22-112 | 2022-03-11 | C | CRS-GUP-DHI-DT-22-244 | 2022-03-11 | RR | DE-GUP-DT-E-22-377 | 2022-07-08 | D | CRS-GUP-DHI-DT-22-542 | 2022-07-25 | RC | DE-GUP-DT-E-22-512 | 2022-08-18 | E | CRS-GUP-DHI-DT-22-714 | 2022-09-05 | AC | DE-GUP-DT-E-22-737 | 2022-09-30 | F | CRS-GUP-DHI-DT-22-894 | 2022-10-10 | AC | DE-GUP-DT-E-22-913 | 2022-11-04 | G | CRS-GUP-DHI-DT-22-1046 | 2022-11-16 | AA | DE-GUP-DT-E-22-1073 | 2022-12-09 | 0 | CRS-GUP-DHI-DT-22-1330 | 2022-12-28 | AA | DE-GUP-DT-E-23-026 | 2023-01-13 | 1 | CRS-GUP-DHI-DT-22-1447 | 2023-02-01 | AA | DE-GUP-DT-E-23-124 | 2023-02-06 | 2 | CRS-GUP-DHI-DT-23-1623 | 2023-03-02 | AA
| GUP | CA00 | P1 | UGD | 181614 |  | GUP-CA00-P1UGD-181614 | WT & WWT BLDG & SHELTER_GROUND FLOOR PLAN | FA | 2022-01-30 | 2022-09-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | WT & WWT Building | Arch. | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-797 | 2023-09-07 | 2 | CRS-GUP-DHI-DT-23-2117 | 2023-09-27 | AA | DHI-GUP-DT-21-042 | 2021-09-30 | A | CRS-GUP-DHI-DT-21-033 | 2021-10-06 | RR | DHI-GUP-DT-22-017 | 2022-01-14 | B | CRS-GUP-DHI-DT-21-181 | 2022-02-04 | RC | DHI-GUP-DT-22-112 | 2022-03-11 | C | CRS-GUP-DHI-DT-22-244 | 2022-03-11 | RR | DE-GUP-DT-E-22-377 | 2022-07-08 | D | CRS-GUP-DHI-DT-22-542 | 2022-07-25 | RC | DE-GUP-DT-E-22-512 | 2022-08-18 | E | CRS-GUP-DHI-DT-22-714 | 2022-09-05 | AC | DE-GUP-DT-E-22-737 | 2022-09-30 | F | CRS-GUP-DHI-DT-22-894 | 2022-10-10 | AC | DE-GUP-DT-E-22-913 | 2022-11-04 | G | CRS-GUP-DHI-DT-22-1046 | 2022-11-16 | RC | DE-GUP-DT-E-22-1073 | 2022-12-09 | H | CRS-GUP-DHI-DT-22-1330 | 2022-12-28 | AA | DE-GUP-DT-E-23-026 | 2023-01-13 | I | CRS-GUP-DHI-DT-22-1447 | 2023-02-01 | AA | DE-GUP-DT-E-23-124 | 2023-02-06 | 1 | CRS-GUP-DHI-DT-23-1623 | 2023-03-02 | AA | DE-GUP-DT-E-23-797 | 2023-09-07 | 2 | CRS-GUP-DHI-DT-23-2117 | 2023-09-27 | AA
| GUP | CA00 | P1 | UGD | 181615 |  | GUP-CA00-P1UGD-181615 | WT & WWT BLDG & SHELTER_SECOND FLOOR & ROOF PLAN | FA | 2022-01-30 | 2022-09-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | WT & WWT Building | Arch. | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-797 | 2023-09-07 | 3 | CRS-GUP-DHI-DT-23-2117 | 2023-09-27 | AA | DHI-GUP-DT-21-042 | 2021-09-30 | A | CRS-GUP-DHI-DT-21-033 | 2021-10-06 | RR | DHI-GUP-DT-22-017 | 2022-01-14 | B | CRS-GUP-DHI-DT-21-181 | 2022-02-04 | RC | DHI-GUP-DT-22-112 | 2022-03-11 | C | CRS-GUP-DHI-DT-22-244 | 2022-03-11 | RR | DE-GUP-DT-E-22-377 | 2022-07-08 | D | CRS-GUP-DHI-DT-22-542 | 2022-07-25 | AC | DE-GUP-DT-E-22-512 | 2022-08-18 | E | CRS-GUP-DHI-DT-22-714 | 2022-09-05 | AC | DE-GUP-DT-E-22-737 | 2022-09-30 | F | CRS-GUP-DHI-DT-22-894 | 2022-10-10 | AC | DE-GUP-DT-E-22-913 | 2022-11-04 | G | CRS-GUP-DHI-DT-22-1046 | 2022-11-16 | AA | DE-GUP-DT-E-22-1073 | 2022-12-09 | 0 | CRS-GUP-DHI-DT-22-1330 | 2022-12-28 | AA | DE-GUP-DT-E-23-026 | 2023-01-13 | 1 | CRS-GUP-DHI-DT-22-1447 | 2023-02-01 | AC | DE-GUP-DT-E-23-124 | 2023-02-06 | 2 | CRS-GUP-DHI-DT-23-1623 | 2023-03-02 | AA | DE-GUP-DT-E-23-797 | 2023-09-07 | 3 | CRS-GUP-DHI-DT-23-2117 | 2023-09-27 | AA
| GUP | CA00 | P1 | UGD | 181616 |  | GUP-CA00-P1UGD-181616 | WT & WWT BLDG & SHELTER_MAIN SECTION | FA | 2022-01-30 | 2022-09-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | WT & WWT Building | Arch. | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-797 | 2023-09-07 | 3 | CRS-GUP-DHI-DT-23-2117 | 2023-09-27 | AA | DHI-GUP-DT-21-042 | 2021-09-30 | A | CRS-GUP-DHI-DT-21-033 | 2021-10-06 | RR | DHI-GUP-DT-22-017 | 2022-01-14 | B | CRS-GUP-DHI-DT-21-181 | 2022-02-04 | RC | DHI-GUP-DT-22-112 | 2022-03-11 | C | CRS-GUP-DHI-DT-22-244 | 2022-03-11 | RR | DE-GUP-DT-E-22-377 | 2022-07-08 | D | CRS-GUP-DHI-DT-22-542 | 2022-07-25 | AC | DE-GUP-DT-E-22-512 | 2022-08-18 | E | CRS-GUP-DHI-DT-22-714 | 2022-09-05 | AC | DE-GUP-DT-E-22-737 | 2022-09-30 | F | CRS-GUP-DHI-DT-22-894 | 2022-10-10 | AC | DE-GUP-DT-E-22-913 | 2022-11-04 | G | CRS-GUP-DHI-DT-22-1046 | 2022-11-16 | AA | DE-GUP-DT-E-22-1073 | 2022-12-09 | 0 | CRS-GUP-DHI-DT-22-1330 | 2022-12-28 | AA | DE-GUP-DT-E-23-026 | 2023-01-13 | 1 | CRS-GUP-DHI-DT-22-1447 | 2023-02-01 | AA | DE-GUP-DT-E-23-124 | 2023-02-06 | 2 | CRS-GUP-DHI-DT-23-1623 | 2023-03-02 | AA | DE-GUP-DT-E-23-797 | 2023-09-07 | 3 | CRS-GUP-DHI-DT-23-2117 | 2023-09-27 | AA
| GUP | CA00 | P1 | UGD | 181617 |  | GUP-CA00-P1UGD-181617 | WT & WWT BLDG & SHELTER_SIDE ELEVATION | FA | 2022-01-30 | 2022-09-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | WT & WWT Building | Arch. | 2 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-797 | 2023-09-07 | 3 | CRS-GUP-DHI-DT-23-2117 | 2023-09-27 | AA | DHI-GUP-DT-21-042 | 2021-09-30 | A | N/A | 2022-01-13 | N/A | DHI-GUP-DT-22-017 | 2022-01-14 | B | CRS-GUP-DHI-DT-21-181 | 2022-02-04 | RC | DHI-GUP-DT-22-112 | 2022-03-11 | C | CRS-GUP-DHI-DT-22-244 | 2022-03-11 | RR | DE-GUP-DT-E-22-377 | 2022-07-08 | D | CRS-GUP-DHI-DT-22-542 | 2022-07-25 | AC | DE-GUP-DT-E-22-512 | 2022-08-18 | E | CRS-GUP-DHI-DT-22-714 | 2022-09-05 | AC | DE-GUP-DT-E-22-737 | 2022-09-30 | F | CRS-GUP-DHI-DT-22-894 | 2022-10-10 | AC | DE-GUP-DT-E-22-913 | 2022-11-04 | G | CRS-GUP-DHI-DT-22-1046 | 2022-11-16 | AA | DE-GUP-DT-E-22-1073 | 2022-12-09 | 0 | CRS-GUP-DHI-DT-22-1330 | 2022-12-28 | AA | DE-GUP-DT-E-23-026 | 2023-01-13 | 1 | CRS-GUP-DHI-DT-22-1447 | 2023-02-01 | AA | DE-GUP-DT-E-23-124 | 2023-02-06 | 2 | CRS-GUP-DHI-DT-23-1623 | 2023-03-02 | AA | DE-GUP-DT-E-23-797 | 2023-09-07 | 3 | CRS-GUP-DHI-DT-23-2117 | 2023-09-27 | AA
| GUP | CA00 | P1 | UGD | 181618 |  | GUP-CA00-P1UGD-181618 | WT & WWT BLDG & SHELTER_ENLARGED TOILET PLAN & ELEVATION | FA | 2022-06-04 | 2022-09-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | WT & WWT Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-124 | 2023-02-06 | 2 | CRS-GUP-DHI-DT-23-1623 | 2023-03-02 | AA | DHI-GUP-DT-22-112 | 2022-03-11 | 0 | CRS-GUP-DHI-DT-22-244 | 2022-03-11 | RR | DE-GUP-DT-E-22-377 | 2022-07-08 | 1 | N/A | N/A | N/A | DE-GUP-DT-E-22-512 | 2022-08-18 | 2 | CRS-GUP-DHI-DT-22-714 | 2022-09-05 | NC | DE-GUP-DT-E-22-737 | 2022-09-30 | 3 | CRS-GUP-DHI-DT-22-894 | 2022-10-10 | NC | DE-GUP-DT-E-22-913 | 2022-11-04 | 4 | CRS-GUP-DHI-DT-22-1046 | 2022-11-16 | AA | DE-GUP-DT-E-22-1073 | 2022-12-09 | 0 | CRS-GUP-DHI-DT-22-1330 | 2022-12-28 | AA | DE-GUP-DT-E-23-026 | 2023-01-13 | 1 | CRS-GUP-DHI-DT-22-1447 | 2023-02-01 | AA | DE-GUP-DT-E-23-124 | 2023-02-06 | 2 | CRS-GUP-DHI-DT-23-1623 | 2023-03-02 | AA
| GUP | CA00 | P1 | UGD | 181619 |  | GUP-CA00-P1UGD-181619 | WT & WWT BLDG & SHELTER_ENLARGED STAIRCASE PLAN & SECTION | FI | 2022-01-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | WT & WWT Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-797 | 2023-09-07 | 10 | CRS-GUP-DHI-DT-23-2117 | 2023-09-27 | NC | DHI-GUP-DT-21-042 | 2021-09-30 | 0 | N/A | 2022-01-13 | N/A | DHI-GUP-DT-22-017 | 2022-01-14 | 1 | CRS-GUP-DHI-DT-21-181 | 2022-02-04 | RC | DHI-GUP-DT-22-112 | 2022-03-11 | 2 | CRS-GUP-DHI-DT-22-244 | 2022-03-11 | RR | DE-GUP-DT-E-22-377 | 2022-07-08 | 3 | CRS-GUP-DHI-DT-22-542 | 2022-07-25 | NC | DE-GUP-DT-E-22-512 | 2022-08-18 | 4 | CRS-GUP-DHI-DT-22-714 | 2022-09-05 | NC | DE-GUP-DT-E-22-737 | 2022-09-30 | 5 | CRS-GUP-DHI-DT-22-894 | 2022-10-10 | NC | DE-GUP-DT-E-22-913 | 2022-11-04 | 6 | CRS-GUP-DHI-DT-22-1046 | 2022-11-16 | NC | DE-GUP-DT-E-22-1073 | 2022-12-09 | 7 | CRS-GUP-DHI-DT-22-1330 | 2022-12-28 | NC | DE-GUP-DT-E-23-026 | 2023-01-13 | 8 | CRS-GUP-DHI-DT-22-1447 | 2023-02-01 | NC | DE-GUP-DT-E-23-124 | 2023-02-06 | 9 | CRS-GUP-DHI-DT-23-1623 | 2023-03-02 | NC | DE-GUP-DT-E-23-797 | 2023-09-07 | 10 | CRS-GUP-DHI-DT-23-2117 | 2023-09-27 | NC
| GUP | CA00 | P1 | UGD | 181620 |  | GUP-CA00-P1UGD-181620 | WT & WWT BLDG & SHELTER_WALL OPENING ARRANGEMENT PLAN | FI | 2022-10-30 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | WT & WWT Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-797 | 2023-09-07 | 2 | CRS-GUP-DHI-DT-23-2117 | 2023-09-27 | NC | DE-GUP-DT-E-23-026 | 2023-01-13 | 0 | CRS-GUP-DHI-DT-22-1447 | 2023-02-01 | NC | DE-GUP-DT-E-23-124 | 2023-02-06 | 1 | CRS-GUP-DHI-DT-23-1725 | 2023-03-17 | NC | DE-GUP-DT-E-23-797 | 2023-09-07 | 2 | CRS-GUP-DHI-DT-23-2117 | 2023-09-27 | NC
| GUP | CA00 | P1 | UGD | 181621 |  | GUP-CA00-P1UGD-181621 | WT & WWT BLDG & SHELTER_CEILING PLAN | FI | 2022-06-04 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | WT & WWT Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-797 | 2023-09-07 | 8 | CRS-GUP-DHI-DT-23-2117 | 2023-09-27 | NC | DHI-GUP-DT-22-112 | 2022-03-11 | 0 | CRS-GUP-DHI-DT-22-244 | 2022-03-11 | RR | DE-GUP-DT-E-22-377 | 2022-07-08 | 1 | CRS-GUP-DHI-DT-22-542 | 2022-07-25 | NC | DE-GUP-DT-E-22-512 | 2022-08-18 | 2 | CRS-GUP-DHI-DT-22-714 | 2022-09-05 | NC | DE-GUP-DT-E-22-737 | 2022-09-30 | 3 | CRS-GUP-DHI-DT-22-894 | 2022-10-10 | NC | DE-GUP-DT-E-22-913 | 2022-11-04 | 4 | CRS-GUP-DHI-DT-22-1046 | 2022-11-16 | NC | DE-GUP-DT-E-22-1073 | 2022-12-09 | 5 | CRS-GUP-DHI-DT-22-1330 | 2022-12-28 | NC | DE-GUP-DT-E-23-026 | 2023-01-13 | 6 | CRS-GUP-DHI-DT-22-1447 | 2023-02-01 | NC | DE-GUP-DT-E-23-124 | 2023-02-06 | 7 | CRS-GUP-DHI-DT-23-1623 | 2023-03-02 | NC | DE-GUP-DT-E-23-797 | 2023-09-07 | 8 | CRS-GUP-DHI-DT-23-2117 | 2023-09-27 | NC
| GUP | CA00 | P1 | UGD | 181622 |  | GUP-CA00-P1UGD-181622 | WT & WWT BLDG & SHELTER_ARCHITECTURAL DETAIL | FA | 2022-10-30 | 2023-01-30 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | WT & WWT Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-797 | 2023-09-07 | 3 | CRS-GUP-DHI-DT-23-2117 | 2023-09-27 | AA | DE-GUP-DT-E-22-913 | 2022-11-04 | A | CRS-GUP-DHI-DT-22-1046 | 2022-11-16 | AA | DE-GUP-DT-E-22-1073 | 2022-12-09 | 0 | CRS-GUP-DHI-DT-22-1330 | 2022-12-28 | AA | DE-GUP-DT-E-23-026 | 2023-01-13 | 1 | CRS-GUP-DHI-DT-22-1447 | 2023-02-01 | AA | DE-GUP-DT-E-23-124 | 2023-02-06 | 2 | CRS-GUP-DHI-DT-23-1623 | 2023-03-02 | AA | DE-GUP-DT-E-23-797 | 2023-09-07 | 3 | CRS-GUP-DHI-DT-23-2117 | 2023-09-27 | AA
| GUP | CA00 | P1 | UGD | 181623 |  | GUP-CA00-P1UGD-181623 | WT & WWT BLDG & SHELTER_WALL SECTION | FA | 2022-06-04 | 2023-01-30 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | WT & WWT Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-124 | 2023-02-06 | 2 | CRS-GUP-DHI-DT-23-1623 | 2023-03-02 | AA | DHI-GUP-DT-22-112 | 2022-03-11 | A | CRS-GUP-DHI-DT-22-244 | 2022-03-11 | RR | DE-GUP-DT-E-22-377 | 2022-07-08 | B | CRS-GUP-DHI-DT-22-542 | 2022-07-25 | RC | DE-GUP-DT-E-22-512 | 2022-08-18 | C | CRS-GUP-DHI-DT-22-714 | 2022-09-05 | AC | DE-GUP-DT-E-22-737 | 2022-09-30 | D | CRS-GUP-DHI-DT-22-894 | 2022-10-10 | AC | DE-GUP-DT-E-22-913 | 2022-11-04 | E | CRS-GUP-DHI-DT-22-1046 | 2022-11-16 | AA | DE-GUP-DT-E-22-1073 | 2022-12-09 | 0 | CRS-GUP-DHI-DT-22-1330 | 2022-12-28 | AA | DE-GUP-DT-E-23-026 | 2023-01-13 | 1 | CRS-GUP-DHI-DT-22-1447 | 2023-02-01 | AA | DE-GUP-DT-E-23-124 | 2023-02-06 | 2 | CRS-GUP-DHI-DT-23-1623 | 2023-03-02 | AA
| GUP | CA01 | P1 | UGD | 181633 |  | GUP-CA01-P1UGD-181633 | WT & WWT BLDG & SHELTER_RC COLUMN ARRANGEMENT PLAN | FI | 2022-08-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | WT & WWT Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-189 | 2023-02-16 | 5 | CRS-GUP-DHI-DT-23-1668 | 2023-03-10 | NC | DE-GUP-DT-E-22-513 | 2022-08-18 | 0 | CRS-GUP-DHI-DT-22-715 | 2022-09-05 | RC | DE-GUP-DT-E-22-738 | 2022-09-30 | 1 | CRS-GUP-DHI-DT-22-920 | 2022-10-19 | RC | DE-GUP-DT-E-22-912 | 2022-11-04 | 2 | CRS-GUP-DHI-DT-22-1045 | 2022-11-16 | NC | DE-GUP-DT-E-22-1074 | 2022-12-09 | 3 | CRS-GUP-DHI-DT-22-1331 | 2022-12-28 | NC | DE-GUP-DT-E-23-025 | 2023-01-13 | 4 | CRS-GUP-DHI-DT-22-1446 | 2023-02-01 | NC | DE-GUP-DT-E-23-189 | 2023-02-16 | 5 | CRS-GUP-DHI-DT-23-1668 | 2023-03-10 | NC
| GUP | CA03 | P1 | UGD | 181651 |  | GUP-CA03-P1UGD-181651 | WT & WWT BLDG & SHELTER_STEEL COLUMN ARRANGEMENT PLAN | FI | 2022-08-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | WT & WWT Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-189 | 2023-02-16 | 5 | CRS-GUP-DHI-DT-23-1668 | 2023-03-10 | NC | DE-GUP-DT-E-22-513 | 2022-08-18 | 0 | CRS-GUP-DHI-DT-22-715 | 2022-09-05 | RC | DE-GUP-DT-E-22-738 | 2022-09-30 | 1 | CRS-GUP-DHI-DT-22-920 | 2022-10-19 | RC | DE-GUP-DT-E-22-912 | 2022-11-04 | 2 | CRS-GUP-DHI-DT-22-1045 | 2022-11-16 | NC | DE-GUP-DT-E-22-1074 | 2022-12-09 | 3 | CRS-GUP-DHI-DT-22-1331 | 2022-12-28 | NC | DE-GUP-DT-E-23-025 | 2023-01-13 | 4 | CRS-GUP-DHI-DT-22-1446 | 2023-02-01 | NC | DE-GUP-DT-E-23-189 | 2023-02-16 | 5 | CRS-GUP-DHI-DT-23-1668 | 2023-03-10 | NC
| GUP | CA01 | P1 | UGD | 181634 |  | GUP-CA01-P1UGD-181634 | WT & WWT BLDG & SHELTER_BASEMENT FLOOR FRAMING PLAN | FI | 2022-08-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | WT & WWT Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-189 | 2023-02-16 | 5 | CRS-GUP-DHI-DT-23-1668 | 2023-03-10 | NC | DE-GUP-DT-E-22-513 | 2022-08-18 | 0 | CRS-GUP-DHI-DT-22-715 | 2022-09-05 | RC | DE-GUP-DT-E-22-738 | 2022-09-30 | 1 | CRS-GUP-DHI-DT-22-920 | 2022-10-19 | NC | DE-GUP-DT-E-22-912 | 2022-11-04 | 2 | CRS-GUP-DHI-DT-22-1045 | 2022-11-16 | NC | DE-GUP-DT-E-22-1074 | 2022-12-09 | 3 | CRS-GUP-DHI-DT-22-1331 | 2022-12-28 | NC | DE-GUP-DT-E-23-025 | 2023-01-13 | 4 | CRS-GUP-DHI-DT-22-1446 | 2023-02-01 | NC | DE-GUP-DT-E-23-189 | 2023-02-16 | 5 | CRS-GUP-DHI-DT-23-1668 | 2023-03-10 | NC
| GUP | CA03 | P1 | UGD | 181652 |  | GUP-CA03-P1UGD-181652 | WT & WWT BLDG & SHELTER_GROUND FLOOR FRAMING PLAN | FI | 2022-08-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | WT & WWT Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-189 | 2023-02-16 | 5 | CRS-GUP-DHI-DT-23-1668 | 2023-03-10 | NC | DE-GUP-DT-E-22-513 | 2022-08-18 | 0 | CRS-GUP-DHI-DT-22-715 | 2022-09-05 | RC | DE-GUP-DT-E-22-738 | 2022-09-30 | 1 | CRS-GUP-DHI-DT-22-920 | 2022-10-19 | RC | DE-GUP-DT-E-22-912 | 2022-11-04 | 2 | CRS-GUP-DHI-DT-22-1045 | 2022-11-16 | NC | DE-GUP-DT-E-22-1074 | 2022-12-09 | 3 | CRS-GUP-DHI-DT-22-1331 | 2022-12-28 | NC | DE-GUP-DT-E-23-025 | 2023-01-13 | 4 | CRS-GUP-DHI-DT-22-1446 | 2023-02-01 | NC | DE-GUP-DT-E-23-189 | 2023-02-16 | 5 | CRS-GUP-DHI-DT-23-1668 | 2023-03-10 | NC
| GUP | CA03 | P1 | UGD | 181653 |  | GUP-CA03-P1UGD-181653 | WT & WWT BLDG & SHELTER_ROOF FRAMING PLAN | FI | 2022-08-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | WT & WWT Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-671 | 2023-07-05 | 6 | CRS-GUP-DHI-DT-23-1668 | 2023-03-10 | NC | DE-GUP-DT-E-22-513 | 2022-08-18 | 0 | CRS-GUP-DHI-DT-22-715 | 2022-09-05 | RC | DE-GUP-DT-E-22-738 | 2022-09-30 | 1 | CRS-GUP-DHI-DT-22-920 | 2022-10-19 | RC | DE-GUP-DT-E-22-912 | 2022-11-04 | 2 | CRS-GUP-DHI-DT-22-1045 | 2022-11-16 | NC | DE-GUP-DT-E-22-1074 | 2022-12-09 | 3 | CRS-GUP-DHI-DT-22-1331 | 2022-12-28 | NC | DE-GUP-DT-E-23-025 | 2023-01-13 | 4 | CRS-GUP-DHI-DT-22-1446 | 2023-02-01 | NC | DE-GUP-DT-E-23-189 | 2023-02-16 | 5 | CRS-GUP-DHI-DT-23-1668 | 2023-03-10 | NC | DE-GUP-DT-E-23-671 | 2023-07-05 | 6
| GUP | CA03 | P1 | UGD | 181654 |  | GUP-CA03-P1UGD-181654 | WT & WWT BLDG & SHELTER_LINE FRAMING ELEVATION | FI | 2022-08-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | WT & WWT Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-189 | 2023-02-16 | 5 | CRS-GUP-DHI-DT-23-1668 | 2023-03-10 | NC | DE-GUP-DT-E-22-513 | 2022-08-18 | 0 | CRS-GUP-DHI-DT-22-715 | 2022-09-05 | RC | DE-GUP-DT-E-22-738 | 2022-09-30 | 1 | CRS-GUP-DHI-DT-22-920 | 2022-10-19 | RC | DE-GUP-DT-E-22-912 | 2022-11-04 | 2 | CRS-GUP-DHI-DT-22-1045 | 2022-11-16 | NC | DE-GUP-DT-E-22-1074 | 2022-12-09 | 3 | CRS-GUP-DHI-DT-22-1331 | 2022-12-28 | NC | DE-GUP-DT-E-23-025 | 2023-01-13 | 4 | CRS-GUP-DHI-DT-22-1446 | 2023-02-01 | NC | DE-GUP-DT-E-23-189 | 2023-02-16 | 5 | CRS-GUP-DHI-DT-23-1668 | 2023-03-10 | NC
| GUP | CA03 | P1 | UGD | 181655 |  | GUP-CA03-P1UGD-181655 | WT & WWT BLDG & SHELTER_ROW FRAMING ELEVATION | FI | 2022-08-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | WT & WWT Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-189 | 2023-02-16 | 5 | CRS-GUP-DHI-DT-23-1668 | 2023-03-10 | NC | DE-GUP-DT-E-22-513 | 2022-08-18 | 0 | CRS-GUP-DHI-DT-22-715 | 2022-09-05 | RC | DE-GUP-DT-E-22-738 | 2022-09-30 | 1 | CRS-GUP-DHI-DT-22-920 | 2022-10-19 | NC | DE-GUP-DT-E-22-912 | 2022-11-04 | 2 | CRS-GUP-DHI-DT-22-1045 | 2022-11-16 | NC | DE-GUP-DT-E-22-1074 | 2022-12-09 | 3 | CRS-GUP-DHI-DT-22-1331 | 2022-12-28 | NC | DE-GUP-DT-E-23-025 | 2023-01-13 | 4 | CRS-GUP-DHI-DT-22-1446 | 2023-02-01 | RC | DE-GUP-DT-E-23-189 | 2023-02-16 | 5 | CRS-GUP-DHI-DT-23-1668 | 2023-03-10 | NC
| GUP | CA03 | P1 | UGD | 181658 |  | GUP-CA03-P1UGD-181658 | WT & WWT BLDG & SHELTER_CONNECTION DETAIL | FI | 2022-09-30 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | WT & WWT Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-796 | 2023-09-07 | 4 | CRS-GUP-DHI-DT-23-1668 | 2023-03-10 | NC | DE-GUP-DT-E-22-912 | 2022-11-04 | 0 | CRS-GUP-DHI-DT-22-1045 | 2022-11-16 | NC | DE-GUP-DT-E-22-1074 | 2022-12-09 | 1 | CRS-GUP-DHI-DT-22-1331 | 2022-12-28 | NC | DE-GUP-DT-E-23-025 | 2023-01-13 | 2 | CRS-GUP-DHI-DT-22-1446 | 2023-02-01 | NC | DE-GUP-DT-E-23-189 | 2023-02-16 | 3 | CRS-GUP-DHI-DT-23-1668 | 2023-03-10 | NC | DE-GUP-DT-E-23-796 | 2023-09-07 | 4
| GUP | CA03 | P1 | UGD | 181635 |  | GUP-CA03-P1UGD-181635 | WT & WWT BLDG & SHELTER_ENLARGED STAIRCASE FRAMING PLAN & SECTION | FI | 2022-08-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | WT & WWT Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-189 | 2023-02-16 | 5 | CRS-GUP-DHI-DT-23-1668 | 2023-03-10 | NC | DE-GUP-DT-E-22-513 | 2022-08-18 | 0 | CRS-GUP-DHI-DT-22-715 | 2022-09-05 | RC | DE-GUP-DT-E-22-738 | 2022-09-30 | 1 | CRS-GUP-DHI-DT-22-920 | 2022-10-19 | NC | DE-GUP-DT-E-22-912 | 2022-11-04 | 2 | CRS-GUP-DHI-DT-22-1045 | 2022-11-16 | NC | DE-GUP-DT-E-22-1074 | 2022-12-09 | 3 | CRS-GUP-DHI-DT-22-1331 | 2022-12-28 | NC | DE-GUP-DT-E-23-025 | 2023-01-13 | 4 | CRS-GUP-DHI-DT-22-1446 | 2023-02-01 | NC | DE-GUP-DT-E-23-189 | 2023-02-16 | 5 | CRS-GUP-DHI-DT-23-1668 | 2023-03-10 | NC
| GUP | CA01 | P1 | UGD | 181636 |  | GUP-CA01-P1UGD-181636 | WT & WWT BLDG & SHELTER_EQUIPMENT FOUNDATION DETAIL | FI | 2022-10-30 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | WT & WWT Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-671 | 2023-07-05 | 4 | CRS-GUP-DHI-DT-23-1668 | 2023-03-10 | NC | DE-GUP-DT-E-22-912 | 2022-11-04 | 0 | CRS-GUP-DHI-DT-22-1045 | 2022-11-16 | RC | DE-GUP-DT-E-22-1074 | 2022-12-09 | 1 | CRS-GUP-DHI-DT-22-1331 | 2022-12-28 | NC | DE-GUP-DT-E-23-025 | 2023-01-13 | 2 | CRS-GUP-DHI-DT-22-1446 | 2023-02-01 | RC | DE-GUP-DT-E-23-189 | 2023-02-16 | 3 | CRS-GUP-DHI-DT-23-1668 | 2023-03-10 | NC | DE-GUP-DT-E-23-671 | 2023-07-05 | 4
| GUP | CA01 | P1 | UGD | 181637 |  | GUP-CA01-P1UGD-181637 | WT & WWT BLDG & SHELTER_STRUCTURAL MISC. DETAIL | FI | 2022-10-30 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | WT & WWT Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-189 | 2023-02-16 | 3 | CRS-GUP-DHI-DT-23-1668 | 2023-03-10 | NC | DE-GUP-DT-E-22-912 | 2022-11-04 | 0 | CRS-GUP-DHI-DT-22-1045 | 2022-11-16 | RC | DE-GUP-DT-E-22-1074 | 2022-12-09 | 1 | CRS-GUP-DHI-DT-22-1331 | 2022-12-28 | NC | DE-GUP-DT-E-23-025 | 2023-01-13 | 2 | CRS-GUP-DHI-DT-22-1446 | 2023-02-01 | NC | DE-GUP-DT-E-23-189 | 2023-02-16 | 3 | CRS-GUP-DHI-DT-23-1668 | 2023-03-10 | NC
| GUP | CA02 | P1 | UGD | 181638 |  | GUP-CA02-P1UGD-181638 | WT & WWT BLDG & SHELTER_COLUMN RE-BAR SCHEDULE | FI | 2022-08-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | WT & WWT Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-189 | 2023-02-16 | 5 | CRS-GUP-DHI-DT-23-1668 | 2023-03-10 | NC | DE-GUP-DT-E-22-513 | 2022-08-18 | 0 | CRS-GUP-DHI-DT-22-715 | 2022-09-05 | RC | DE-GUP-DT-E-22-738 | 2022-09-30 | 1 | CRS-GUP-DHI-DT-22-920 | 2022-10-19 | RC | DE-GUP-DT-E-22-912 | 2022-11-04 | 2 | CRS-GUP-DHI-DT-22-1045 | 2022-11-16 | NC | DE-GUP-DT-E-22-1074 | 2022-12-09 | 3 | CRS-GUP-DHI-DT-22-1331 | 2022-12-28 | NC | DE-GUP-DT-E-23-025 | 2023-01-13 | 4 | CRS-GUP-DHI-DT-22-1446 | 2023-02-01 | NC | DE-GUP-DT-E-23-189 | 2023-02-16 | 5 | CRS-GUP-DHI-DT-23-1668 | 2023-03-10 | NC
| GUP | CA02 | P1 | UGD | 181639 |  | GUP-CA02-P1UGD-181639 | WT & WWT BLDG & SHELTER_BEAM & GIRDER RE-BAR SCHEDULE | FI | 2022-08-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | WT & WWT Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-189 | 2023-02-16 | 5 | CRS-GUP-DHI-DT-23-1668 | 2023-03-10 | NC | DE-GUP-DT-E-22-513 | 2022-08-18 | 0 | CRS-GUP-DHI-DT-22-715 | 2022-09-05 | RC | DE-GUP-DT-E-22-738 | 2022-09-30 | 1 | CRS-GUP-DHI-DT-22-920 | 2022-10-19 | RC | DE-GUP-DT-E-22-912 | 2022-11-04 | 2 | CRS-GUP-DHI-DT-22-1045 | 2022-11-16 | NC | DE-GUP-DT-E-22-1074 | 2022-12-09 | 3 | CRS-GUP-DHI-DT-22-1331 | 2022-12-28 | NC | DE-GUP-DT-E-23-025 | 2023-01-13 | 4 | CRS-GUP-DHI-DT-22-1446 | 2023-02-01 | NC | DE-GUP-DT-E-23-189 | 2023-02-16 | 5 | CRS-GUP-DHI-DT-23-1668 | 2023-03-10 | NC
| GUP | CA02 | P1 | UGD | 181640 |  | GUP-CA02-P1UGD-181640 | WT & WWT BLDG & SHELTER_SLAB & MISC. RE-BAR SCHEDULE | FI | 2022-08-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | WT & WWT Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-671 | 2023-07-05 | 6 | CRS-GUP-DHI-DT-23-1668 | 2023-03-10 | NC | DE-GUP-DT-E-22-513 | 2022-08-18 | 0 | CRS-GUP-DHI-DT-22-715 | 2022-09-05 | RC | DE-GUP-DT-E-22-738 | 2022-09-30 | 1 | CRS-GUP-DHI-DT-22-920 | 2022-10-19 | RC | DE-GUP-DT-E-22-912 | 2022-11-04 | 2 | CRS-GUP-DHI-DT-22-1045 | 2022-11-16 | RC | DE-GUP-DT-E-22-1074 | 2022-12-09 | 3 | CRS-GUP-DHI-DT-22-1331 | 2022-12-28 | NC | DE-GUP-DT-E-23-025 | 2023-01-13 | 4 | CRS-GUP-DHI-DT-22-1446 | 2023-02-01 | NC | DE-GUP-DT-E-23-189 | 2023-02-16 | 5 | CRS-GUP-DHI-DT-23-1668 | 2023-03-10 | NC | DE-GUP-DT-E-23-671 | 2023-07-05 | 6
| GUP | CC05 | P0 | ZEN | 181012 |  | GUP-CC05-P0ZEN-181012 | S&A STANDARD_PLUMBING STANDARD SYMBOL & ABBREVIATION | FA | 2021-12-15 | 2022-05-30 | 건축기술2팀(Arch.) | 진백석 | B | P |  |  |  | CCPP | Plant | Arch. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-614 | 2022-09-02 | 0 | CRS-GUP-DHI-DT-22-803 | 2022-09-19 | AA | DHI-GUP-DT-21-103 | 2021-11-16 | A | CRS-GUP-DHI-DT-21-078 | 2021-12-08 | AA | DE-GUP-DT-E-22-614 | 2022-09-02 | 0 | CRS-GUP-DHI-DT-22-803 | 2022-09-19 | AA
| GUP | CC05 | P0 | ZEN | 181013 |  | GUP-CC05-P0ZEN-181013 | S&A STANDARD_PLUMBING STANDARD GENERAL DETAILS | FA | 2021-12-15 | 2022-05-30 | 건축기술2팀(Arch.) | 진백석 | B | P |  |  |  | CCPP | Plant | Arch. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-023 | 2024-01-24 | 1 | CRS-GUP-DHI-DT-23-1782 | 2023-03-27 | AA | DHI-GUP-DT-21-103 | 2021-11-16 | A | CRS-GUP-DHI-DT-21-078 | 2021-12-08 | RC | DE-GUP-DT-E-22-617 | 2022-09-05 | B | CRS-GUP-DHI-DT-22-803 | 2022-09-19 | RC | DE-GUP-DT-E-23-159 | 2023-02-13 | C | CRS-GUP-DHI-DT-23-1569 | 2023-02-23 | AC | DE-GUP-DT-E-23-313 | 2023-03-15 | 0(CP) | CRS-GUP-DHI-DT-23-1782 | 2023-03-27 | AA | DE-GUP-DT-E-24-023 | 2024-01-24 | 1
| GUP | CC05 | P0 | ZEN | 181001 |  | GUP-CC05-P0ZEN-181001 | S&A STANDARD_DESIGN CRITERIA FOR BUILDINGS & STRUCTURES | FA | 2021-10-15 | 2022-03-30 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Plant | Arch. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-388 | 2022-07-12 | 0 | CRS-GUP-DHI-DT-22-343 | 2022-05-18 | AA | DHI-GUP-DT-21-015 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-003 | 2021-09-27 | RC | DHI-GUP-DT-21-075 | 2021-10-22 | B | CRS-GUP-DHI-DT-21-052 | 2021-11-07 | RC | DHI-GUP-DT-21-124 | 2021-11-26 | C | CRS-GUP-DHI-DT-21-095 | 2021-12-23 | RC | DHI-GUP-DT-22-020 | 2022-01-14 | D | CRS-GUP-DHI-DT-21-182 | 2022-02-04 | RC | DHI-GUP-DT-22-064 | 2022-02-11 | E | CRS-GUP-DHI-DT-22-226 | 2022-03-05 | RC | DHI-GUP-DT-22-136 | 2022-03-25 | F | CRS-GUP-DHI-DT-22-297 | 2022-04-17 | AC | DHI-GUP-DT-22-186 | 2022-04-21 | G | CRS-GUP-DHI-DT-22-343 | 2022-05-18 | AA | DE-GUP-DT-E-22-388 | 2022-07-12 | 0
| GUP | CC05 | P0 | ZEN | 181002 |  | GUP-CC05-P0ZEN-181002 | S&A STANDARD_GENERAL NOTES, ABBREVIATION,LEGEND & SYMBOLS | FA | 2021-11-15 | 2022-04-30 | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | Plant | Arch. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-574 | 2023-05-22 | 1 | CRS-GUP-DHI-DT-21-057 | 2021-11-08 | AA | DHI-GUP-DT-21-043 | 2021-09-30 | A | CRS-GUP-DHI-DT-21-039 | 2021-10-08 | AC | DHI-GUP-DT-21-080 | 2021-10-29 | B | CRS-GUP-DHI-DT-21-057 | 2021-11-08 | AA | DE-GUP-DT-E-22-1032 | 2022-12-05 | 0 |  |  |  | DE-GUP-DT-E-23-574 | 2023-05-22 | 1
| GUP | CC05 | P0 | ZEN | 181003 |  | GUP-CC05-P0ZEN-181003 | S&A STANDARD_INTERIOR FINISH DETAILS | FA | 2021-11-15 | 2022-04-30 | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | Plant | Arch. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-648 | 2023-06-28 | 1 | 자체 CRS 개정 후 제출 | 2023-06-27 | N/A | DHI-GUP-DT-21-043 | 2021-09-30 | A | CRS-GUP-DHI-DT-21-039 | 2021-10-08 | AC | DHI-GUP-DT-21-080 | 2021-10-29 | B | CRS-GUP-DHI-DT-21-057 | 2021-11-08 | AC | DE-GUP-DT-E-22-279 | 2022-06-09 | C | CRS-GUP-DHI-DT-22-464 | 2022-06-21 | AA | DE-GUP-DT-E-22-1032 | 2022-12-05 | 0 | 자체 CRS 개정 후 제출 | 2023-06-27 | N/A | DE-GUP-DT-E-23-648 | 2023-06-28 | 1
| GUP | CC05 | P0 | ZEN | 181004 |  | GUP-CC05-P0ZEN-181004 | S&A STANDARD_CLADDING JOINT DETAILS | FA | 2021-11-15 | 2022-04-30 | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | Plant | Arch. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-648 | 2023-06-28 | 1 | 자체 CRS 개정 후 제출 | 2023-06-27 | N/A | DHI-GUP-DT-21-043 | 2021-09-30 | A | CRS-GUP-DHI-DT-21-039 | 2021-10-08 | AC | DHI-GUP-DT-21-080 | 2021-10-29 | B | CRS-GUP-DHI-DT-21-057 | 2021-11-08 | AA | DE-GUP-DT-E-22-1032 | 2022-12-05 | 0 | 자체 CRS 개정 후 제출 | 2023-06-27 | N/A | DE-GUP-DT-E-23-648 | 2023-06-28 | 1
| GUP | CC05 | P0 | ZEN | 181005 |  | GUP-CC05-P0ZEN-181005 | S&A STANDARD_MISC. ARCHITECTURAL DETAILS | FA | 2021-11-15 | 2022-04-30 | 건축기술2팀(Arch.) | 구남영 |  | P | G | FA |  | CCPP | Plant | Arch. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-648 | 2023-06-28 | 1 | 자체 CRS 개정 후 제출 | 2023-06-27 | N/A | DHI-GUP-DT-21-043 | 2021-09-30 | A | CRS-GUP-DHI-DT-21-039 | 2021-10-08 | AC | DHI-GUP-DT-21-080 | 2021-10-29 | B | CRS-GUP-DHI-DT-21-057 | 2021-11-08 | AA | DE-GUP-DT-E-22-1032 | 2022-12-05 | 0 | 자체 CRS 개정 후 제출 | 2023-06-27 | N/A | DE-GUP-DT-E-23-648 | 2023-06-28 | 1
| GUP | CC05 | P0 | ZEN | 181006 |  | GUP-CC05-P0ZEN-181006 | S&A STANDARD_DOOR & WINDOW SCHEDULE AND DETAILS | FA | 2021-11-15 | 2022-07-30 | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | Plant | Arch. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-1032 | 2022-12-05 | 0 | CRS-GUP-DHI-DT-21-057 | 2021-11-08 | AA | DHI-GUP-DT-21-043 | 2021-09-30 | A | CRS-GUP-DHI-DT-21-039 | 2021-10-08 | AC | DHI-GUP-DT-21-080 | 2021-10-29 | B | CRS-GUP-DHI-DT-21-057 | 2021-11-08 | AA | DE-GUP-DT-E-22-1032 | 2022-12-05 | 0
| GUP | CC05 | P0 | ZEN | 181007 |  | GUP-CC05-P0ZEN-181007 | S&A STANDARD_RE-BAR STANDARDS | FA | 2021-11-15 | 2022-04-30 | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | Plant | Arch. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-331 | 2022-06-24 | 0 | CRS-GUP-DHI-DT-24-022 | 2024-03-11 | AA | DHI-GUP-DT-21-022 | 2021-09-14 | A | CRS-GUP-DHI-DT-21-008 | 2021-09-28 | AC | DHI-GUP-DT-21-074 | 2021-10-22 | B | CRS-GUP-DHI-DT-21-051 | 2021-11-07 | AC | DHI-GUP-DT-21-137 | 2021-11-30 | C | CRS-GUP-DHI-DT-21-099 | 2021-12-27 | AC | DE-GUP-DT-E-22-331 | 2022-06-24 | 0 | CRS-GUP-DHI-DT-24-022 | 2024-03-11 | AA
| GUP | CC05 | P0 | ZEN | 181008 |  | GUP-CC05-P0ZEN-181008 | S&A STANDARD_STEEL CONNECTION DETAILS | FA | 2021-11-15 | 2022-04-30 | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | Plant | Arch. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-331 | 2022-06-24 | 0 | CRS-GUP-DHI-DT-24-022 | 2024-03-11 | AA | DHI-GUP-DT-21-022 | 2021-09-14 | A | CRS-GUP-DHI-DT-21-008 | 2021-09-28 | AC | DHI-GUP-DT-21-074 | 2021-10-22 | B | CRS-GUP-DHI-DT-21-051 | 2021-11-07 | AC | DHI-GUP-DT-21-137 | 2021-11-30 | C | CRS-GUP-DHI-DT-21-099 | 2021-12-27 | AC | DHI-GUP-DT-22-024 | 2022-01-17 | D | CRS-GUP-DHI-DT-21-179 | 2022-01-31 | RC | DHI-GUP-DT-22-087 | 2022-02-24 | E | CRS-GUP-DHI-DT-22-243 | 2022-03-09 | AC | DE-GUP-DT-E-22-258 | 2022-05-31 | F | CRS-GUP-DHI-DT-22-456 | 2022-06-21 | AA | DE-GUP-DT-E-22-331 | 2022-06-24 | 0 | CRS-GUP-DHI-DT-24-022 | 2024-03-11 | AA
| GUP | CC05 | P0 | ZEN | 181009 |  | GUP-CC05-P0ZEN-181009 | S&A STANDARD_TYPICAL STAIR AND HANDRAIL DETAILS | FA | 2021-11-15 | 2022-04-30 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Plant | Arch. | 1 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-521 | 2023-05-03 | 2 | CRS-GUP-DHI-DT-24-022 | 2024-03-11 | AA | DHI-GUP-DT-21-022 | 2021-09-14 | A | CRS-GUP-DHI-DT-21-008 | 2021-09-28 | AC | DHI-GUP-DT-21-074 | 2021-10-22 | B | CRS-GUP-DHI-DT-21-051 | 2021-11-07 | AC | DHI-GUP-DT-21-137 | 2021-11-30 | C | CRS-GUP-DHI-DT-21-099 | 2021-12-27 | AC | DHI-GUP-DT-22-024 | 2022-01-17 | D | CRS-GUP-DHI-DT-21-179 | 2022-01-31 | AC | DHI-GUP-DT-22-087 | 2022-02-24 | E | CRS-GUP-DHI-DT-22-243 | 2022-03-09 | AA | DE-GUP-DT-E-22-331 | 2022-06-24 | 0 | N/A(자체 CRS 개정 후 제출) | 2022-11-08 | N/A | DE-GUP-DT-E-22-924 | 2022-11-09 | 1 | CRS-GUP-DHI-DT-22-1061 | 2022-11-17 | AA | DE-GUP-DT-E-23-521 | 2023-05-03 | 2 | CRS-GUP-DHI-DT-24-022 | 2024-03-11 | AA
| GUP | CA06 | P1 | UTA | 183501 |  | GUP-CA06-P1UTA-183501 | CHEMICAL DOSING SHELTER FOR COOLING TOWER_CALCULATION SHEET | FI | 2022-09-04 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | CHEMICAL DOSING SHELTER FOR CT | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-507 | 2023-04-25 | 3 | CRS-GUP-DHI-DT-23-1927 | 2023-05-05 | NC | DE-GUP-DT-E-22-999 | 2022-11-28 | 0 | CRS-GUP-DHI-DT-22-1266 | 2022-12-16 | RC | DE-GUP-DT-E-23-023 | 2023-01-13 | 1 | CRS-GUP-DHI-DT-22-1416 | 2023-01-26 | NC | DE-GUP-DT-E-23-132 | 2023-02-06 | 2 | CRS-GUP-DHI-DT-23-1567 | 2023-02-23 | NC | DE-GUP-DT-E-23-507 | 2023-04-25 | 3 | CRS-GUP-DHI-DT-23-1927 | 2023-05-05 | NC
| GUP | CA01 | P1 | UTA | 183531 |  | GUP-CA01-P1UTA-183531 | CHEMICAL DOSING SHELTER FOR COOLING TOWER_FOUNDATION ARRANGEMENT PLAN | FA | 2022-07-20 | 2022-11-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | CHEMICAL DOSING SHELTER FOR CT | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-507 | 2023-04-25 | 1 | CRS-GUP-DHI-DT-23-1927 | 2023-05-05 | AA | DE-GUP-DT-E-22-999 | 2022-11-28 | A | CRS-GUP-DHI-DT-22-1266 | 2022-12-16 | AC | DE-GUP-DT-E-23-023 | 2023-01-13 | B | CRS-GUP-DHI-DT-22-1416 | 2023-01-26 | AA | DE-GUP-DT-E-23-132 | 2023-02-06 | 0 | CRS-GUP-DHI-DT-23-1567 | 2023-02-23 | AA | DE-GUP-DT-E-23-507 | 2023-04-25 | 1 | CRS-GUP-DHI-DT-23-1927 | 2023-05-05 | AA
| GUP | CA02 | P1 | UTA | 183532 |  | GUP-CA02-P1UTA-183532 | CHEMICAL DOSING SHELTER FOR COOLING TOWER_FOUNDATION RE-BAR SCHEDULE | FI | 2022-07-20 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | CHEMICAL DOSING SHELTER FOR CT | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-507 | 2023-04-25 | 3 | CRS-GUP-DHI-DT-23-1927 | 2023-05-05 | NC | DE-GUP-DT-E-22-999 | 2022-11-28 | 0 | CRS-GUP-DHI-DT-22-1266 | 2022-12-16 | RC | DE-GUP-DT-E-23-023 | 2023-01-13 | 1 | CRS-GUP-DHI-DT-22-1416 | 2023-01-26 | NC | DE-GUP-DT-E-23-132 | 2023-02-06 | 2 | CRS-GUP-DHI-DT-23-1567 | 2023-02-23 | NC | DE-GUP-DT-E-23-507 | 2023-04-25 | 3 | CRS-GUP-DHI-DT-23-1927 | 2023-05-05 | NC
| GUP | CA00 | P1 | UTA | 183511 |  | GUP-CA00-P1UTA-183511 | CHEMICAL DOSING SHELTER FOR COOLING TOWER_GROUND FLOOR & ROOF PLAN | FA | 2022-07-20 | 2022-11-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | CHEMICAL DOSING SHELTER FOR CT | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-006 | 2024-01-09 | 2 | CRS-GUP-DHI-DT-23-1927 | 2023-05-05 | AA | DE-GUP-DT-E-22-999 | 2022-11-28 | A | CRS-GUP-DHI-DT-22-1266 | 2022-12-16 | AC | DE-GUP-DT-E-23-023 | 2023-01-13 | B | CRS-GUP-DHI-DT-22-1416 | 2023-01-26 | AA | DE-GUP-DT-E-23-132 | 2023-02-06 | 0 | CRS-GUP-DHI-DT-23-1567 | 2023-02-23 | AA | DE-GUP-DT-E-23-507 | 2023-04-25 | 1 | CRS-GUP-DHI-DT-23-1927 | 2023-05-05 | AA | DE-GUP-DT-E-24-006 | 2024-01-09 | 2
| GUP | CA00 | P1 | UTA | 183512 |  | GUP-CA00-P1UTA-183512 | CHEMICAL DOSING SHELTER FOR COOLING TOWER_MAIN SECTION | FA | 2022-07-20 | 2022-11-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | CHEMICAL DOSING SHELTER FOR CT | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-006 | 2024-01-09 | 2 | CRS-GUP-DHI-DT-23-1927 | 2023-05-05 | AA | DE-GUP-DT-E-22-999 | 2022-11-28 | A | CRS-GUP-DHI-DT-22-1266 | 2022-12-16 | AC | DE-GUP-DT-E-23-023 | 2023-01-13 | B | CRS-GUP-DHI-DT-22-1416 | 2023-01-26 | AA | DE-GUP-DT-E-23-132 | 2023-02-06 | 0 | CRS-GUP-DHI-DT-23-1567 | 2023-02-23 | AA | DE-GUP-DT-E-23-507 | 2023-04-25 | 1 | CRS-GUP-DHI-DT-23-1927 | 2023-05-05 | AA | DE-GUP-DT-E-24-006 | 2024-01-09 | 2
| GUP | CA00 | P1 | UTA | 183513 |  | GUP-CA00-P1UTA-183513 | CHEMICAL DOSING SHELTER FOR COOLING TOWER_SIDE ELEVATION | FA | 2022-07-20 | 2022-11-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | CHEMICAL DOSING SHELTER FOR CT | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-507 | 2023-04-25 | 1 | CRS-GUP-DHI-DT-23-1927 | 2023-05-05 | AA | DE-GUP-DT-E-22-999 | 2022-11-28 | A | CRS-GUP-DHI-DT-22-1266 | 2022-12-16 | AC | DE-GUP-DT-E-23-023 | 2023-01-13 | B | CRS-GUP-DHI-DT-22-1416 | 2023-01-26 | AA | DE-GUP-DT-E-23-132 | 2023-02-06 | 0 | CRS-GUP-DHI-DT-23-1567 | 2023-02-23 | AA | DE-GUP-DT-E-23-507 | 2023-04-25 | 1 | CRS-GUP-DHI-DT-23-1927 | 2023-05-05 | AA
| GUP | CA00 | P1 | UTA | 183514 |  | GUP-CA00-P1UTA-183514 | CHEMICAL DOSING SHELTER FOR COOLING TOWER_ARCHITECTURAL MISC. DETAIL | FA | 2022-07-20 | 2022-12-30 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | CHEMICAL DOSING SHELTER FOR CT | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-006 | 2024-01-09 | 2 | CRS-GUP-DHI-DT-23-1927 | 2023-05-05 | AA | DE-GUP-DT-E-22-999 | 2022-11-28 | A | CRS-GUP-DHI-DT-22-1266 | 2022-12-16 | AC | DE-GUP-DT-E-23-023 | 2023-01-13 | B | CRS-GUP-DHI-DT-22-1416 | 2023-01-26 | AA | DE-GUP-DT-E-23-132 | 2023-02-06 | 0 | CRS-GUP-DHI-DT-23-1567 | 2023-02-23 | AA | DE-GUP-DT-E-23-507 | 2023-04-25 | 1 | CRS-GUP-DHI-DT-23-1927 | 2023-05-05 | AA | DE-GUP-DT-E-24-006 | 2024-01-09 | 2
| GUP | CA03 | P1 | UTA | 183551 |  | GUP-CA03-P1UTA-183551 | CHEMICAL DOSING SHELTER FOR COOLING TOWER_GROUND FLOOR & ROOF FRAMING PLAN | FI | 2022-07-20 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | CHEMICAL DOSING SHELTER FOR CT | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-507 | 2023-04-25 | 3 | CRS-GUP-DHI-DT-23-1927 | 2023-05-05 | NC | DE-GUP-DT-E-22-999 | 2022-11-28 | 0 | CRS-GUP-DHI-DT-22-1266 | 2022-12-16 | RC | DE-GUP-DT-E-23-023 | 2023-01-13 | 1 | CRS-GUP-DHI-DT-22-1416 | 2023-01-26 | NC | DE-GUP-DT-E-23-132 | 2023-02-06 | 2 | CRS-GUP-DHI-DT-23-1567 | 2023-02-23 | NC | DE-GUP-DT-E-23-507 | 2023-04-25 | 3 | CRS-GUP-DHI-DT-23-1927 | 2023-05-05 | NC
| GUP | CA03 | P1 | UTA | 183552 |  | GUP-CA03-P1UTA-183552 | CHEMICAL DOSING SHELTER FOR COOLING TOWER_LINE & ROW FRAMING ELEVATION | FI | 2022-07-20 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | CHEMICAL DOSING SHELTER FOR CT | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-507 | 2023-04-25 | 3 | CRS-GUP-DHI-DT-23-1927 | 2023-05-05 | NC | DE-GUP-DT-E-22-999 | 2022-11-28 | 0 | CRS-GUP-DHI-DT-22-1266 | 2022-12-16 | RC | DE-GUP-DT-E-23-023 | 2023-01-13 | 1 | CRS-GUP-DHI-DT-22-1416 | 2023-01-26 | NC | DE-GUP-DT-E-23-132 | 2023-02-06 | 2 | CRS-GUP-DHI-DT-23-1567 | 2023-02-23 | NC | DE-GUP-DT-E-23-507 | 2023-04-25 | 3 | CRS-GUP-DHI-DT-23-1927 | 2023-05-05 | NC
| GUP | CA03 | P1 | UTA | 183553 |  | GUP-CA03-P1UTA-183553 | CHEMICAL DOSING SHELTER FOR COOLING TOWER_PURLIN ARRANGEMENT PLAN | FI | 2022-07-20 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | CHEMICAL DOSING SHELTER FOR CT | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-507 | 2023-04-25 | 3 | CRS-GUP-DHI-DT-23-1927 | 2023-05-05 | NC | DE-GUP-DT-E-22-999 | 2022-11-28 | 0 | CRS-GUP-DHI-DT-22-1266 | 2022-12-16 | RC | DE-GUP-DT-E-23-023 | 2023-01-13 | 1 | CRS-GUP-DHI-DT-22-1416 | 2023-01-26 | NC | DE-GUP-DT-E-23-132 | 2023-02-06 | 2 | CRS-GUP-DHI-DT-23-1567 | 2023-02-23 | NC | DE-GUP-DT-E-23-507 | 2023-04-25 | 3 | CRS-GUP-DHI-DT-23-1927 | 2023-05-05 | NC
| GUP | CA01 | P1 | UTA | 183533 |  | GUP-CA01-P1UTA-183533 | CHEMICAL DOSING SHELTER FOR COOLING TOWER_STRUCTURAL DETAIL | FI | 2022-07-20 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | CHEMICAL DOSING SHELTER FOR CT | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-507 | 2023-04-25 | 3 | CRS-GUP-DHI-DT-23-1927 | 2023-05-05 | NC | DE-GUP-DT-E-22-999 | 2022-11-28 | 0 | CRS-GUP-DHI-DT-22-1266 | 2022-12-16 | RC | DE-GUP-DT-E-23-023 | 2023-01-13 | 1 | CRS-GUP-DHI-DT-22-1416 | 2023-01-26 | NC | DE-GUP-DT-E-23-132 | 2023-02-06 | 2 | CRS-GUP-DHI-DT-23-1567 | 2023-02-23 | NC | DE-GUP-DT-E-23-507 | 2023-04-25 | 3 | CRS-GUP-DHI-DT-23-1927 | 2023-05-05 | NC
| GUP | CA06 | P1 | UST | 181501 |  | GUP-CA06-P1UST-181501 | MAINTENANCE WORKSHOP AND STORE BUILDING_CALCULATION SHEET | FA | 2022-11-01 | 2023-02-25 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Workshop Building | Arch. | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-602 | 2023-06-02 | 1 | DE-GUP-DT-E-23-1880 | 2023-04-27 | AA | DE-GUP-DT-E-22-869 | 2022-10-27 | A | CRS-GUP-DHI-DT-22-970 | 2022-11-07 | RR | DE-GUP-DT-E-22-1188 | 2022-12-23 | B | CRS-GUP-DHI-DT-22-1449 | 2023-02-03 | RC | DE-GUP-DT-E-23-248 | 2023-02-27 | C | CRS-GUP-DHI-DT-23-1674 | 2023-03-10 | RC | DE-GUP-DT-E-23-365 | 2023-03-24 | D | DE-GUP-DT-E-23-1823 | 2023-04-12 | AA | DE-GUP-DT-E-23-472 | 2023-04-14 | 0(CP) | DE-GUP-DT-E-23-1880 | 2023-04-27 | AA | DE-GUP-DT-E-23-602 | 2023-06-02 | 1
| GUP | CA01 | P1 | UST | 181531 |  | GUP-CA01-P1UST-181531 | MAINTENANCE WORKSHOP AND STORE BUILDING_FOUNDATION ARRANGEMENT PLAN | FA | 2022-11-01 | 2023-02-25 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Workshop Building | Arch. | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-602 | 2023-06-02 | 1 | DE-GUP-DT-E-23-1880 | 2023-04-27 | AA | DE-GUP-DT-E-22-869 | 2022-10-27 | A | CRS-GUP-DHI-DT-22-970 | 2022-11-07 | RR | DE-GUP-DT-E-22-1188 | 2022-12-23 | B | CRS-GUP-DHI-DT-22-1449 | 2023-02-03 | RC | DE-GUP-DT-E-23-248 | 2023-02-27 | C | CRS-GUP-DHI-DT-23-1674 | 2023-03-10 | RC | DE-GUP-DT-E-23-365 | 2023-03-24 | D | DE-GUP-DT-E-23-1823 | 2023-04-12 | AA | DE-GUP-DT-E-23-472 | 2023-04-14 | 0(CP) | DE-GUP-DT-E-23-1880 | 2023-04-27 | AA | DE-GUP-DT-E-23-602 | 2023-06-02 | 1
| GUP | CA02 | P1 | UST | 181532 |  | GUP-CA02-P1UST-181532 | MAINTENANCE WORKSHOP AND STORE BUILDING_FOUNDATION RE-BAR SCHEDULE | FI | 2022-11-01 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Workshop Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-602 | 2023-06-02 | 5 | DE-GUP-DT-E-23-1880 | 2023-04-27 | NC | DE-GUP-DT-E-22-869 | 2022-10-27 | 0 | CRS-GUP-DHI-DT-22-970 | 2022-11-07 | RR | DE-GUP-DT-E-22-1188 | 2022-12-23 | 1 | CRS-GUP-DHI-DT-22-1449 | 2023-02-03 | RC | DE-GUP-DT-E-23-248 | 2023-02-27 | 2 | CRS-GUP-DHI-DT-23-1674 | 2023-03-10 | RC | DE-GUP-DT-E-23-365 | 2023-03-24 | 3 | DE-GUP-DT-E-23-1823 | 2023-04-12 | NC | DE-GUP-DT-E-23-472 | 2023-04-14 | 4 | DE-GUP-DT-E-23-1880 | 2023-04-27 | NC | DE-GUP-DT-E-23-602 | 2023-06-02 | 5
| GUP | CA00 | P1 | UST | 181510 |  | GUP-CA00-P1UST-181510 | MAINTENANCE WORKSHOP AND STORE BUILDING_DOOR & WINDOW SCHEDULE | FA | 2022-11-01 | 2023-02-25 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Workshop Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-909 | 2023-11-14 | 2 | 자체 CRS 개정 후 제출 | 2023-11-13 | N/A | DE-GUP-DT-E-22-869 | 2022-10-27 | A | CRS-GUP-DHI-DT-22-970 | 2022-11-07 | RR | DE-GUP-DT-E-22-1188 | 2022-12-23 | B | CRS-GUP-DHI-DT-22-1449 | 2023-02-03 | RC | DE-GUP-DT-E-23-248 | 2023-02-27 | C | CRS-GUP-DHI-DT-23-1674 | 2023-03-10 | RC | DE-GUP-DT-E-23-365 | 2023-03-24 | D | DE-GUP-DT-E-23-1823 | 2023-04-12 | AA | DE-GUP-DT-E-23-472 | 2023-04-14 | 0(CP) | DE-GUP-DT-E-23-1880 | 2023-04-27 | AA | DE-GUP-DT-E-23-602 | 2023-06-02 | 1 | 자체 CRS 개정 후 제출 | 2023-11-13 | N/A | DE-GUP-DT-E-23-909 | 2023-11-14 | 2
| GUP | CA00 | P1 | UST | 181511 |  | GUP-CA00-P1UST-181511 | MAINTENANCE WORKSHOP AND STORE BUILDING_INTERIOR FINISH SCHEDULE | FA | 2022-11-01 | 2023-02-25 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Workshop Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-602 | 2023-06-02 | 1 | DE-GUP-DT-E-23-1880 | 2023-04-27 | AA | DE-GUP-DT-E-22-869 | 2022-10-27 | A | CRS-GUP-DHI-DT-22-970 | 2022-11-07 | RR | DE-GUP-DT-E-22-1188 | 2022-12-23 | B | CRS-GUP-DHI-DT-22-1449 | 2023-02-03 | RC | DE-GUP-DT-E-23-248 | 2023-02-27 | C | CRS-GUP-DHI-DT-23-1674 | 2023-03-10 | RC | DE-GUP-DT-E-23-365 | 2023-03-24 | D | DE-GUP-DT-E-23-1823 | 2023-04-12 | AA | DE-GUP-DT-E-23-472 | 2023-04-14 | 0(CP) | DE-GUP-DT-E-23-1880 | 2023-04-27 | AA | DE-GUP-DT-E-23-602 | 2023-06-02 | 1
| GUP | CA00 | P1 | UST | 181512 |  | GUP-CA00-P1UST-181512 | MAINTENANCE WORKSHOP AND STORE BUILDING_GROUND FLOOR PLAN | FA | 2022-11-01 | 2023-02-25 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Workshop Building | Arch. | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-602 | 2023-06-02 | 1 | DE-GUP-DT-E-23-1880 | 2023-04-27 | AA | DE-GUP-DT-E-22-869 | 2022-10-27 | A | CRS-GUP-DHI-DT-22-970 | 2022-11-07 | RR | DE-GUP-DT-E-22-1188 | 2022-12-23 | B | CRS-GUP-DHI-DT-22-1449 | 2023-02-03 | RC | DE-GUP-DT-E-23-248 | 2023-02-27 | C | CRS-GUP-DHI-DT-23-1674 | 2023-03-10 | RC | DE-GUP-DT-E-23-365 | 2023-03-24 | D | DE-GUP-DT-E-23-1823 | 2023-04-12 | AA | DE-GUP-DT-E-23-472 | 2023-04-14 | 0(CP) | DE-GUP-DT-E-23-1880 | 2023-04-27 | AA | DE-GUP-DT-E-23-602 | 2023-06-02 | 1
| GUP | CA00 | P1 | UST | 181513 |  | GUP-CA00-P1UST-181513 | MAINTENANCE WORKSHOP AND STORE BUILDING_ROOF PLAN | FA | 2022-11-01 | 2023-02-25 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Workshop Building | Arch. | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-909 | 2023-11-14 | 2 | 자체 CRS 개정 후 제출 | 2023-11-13 | N/A | DE-GUP-DT-E-22-869 | 2022-10-27 | A | CRS-GUP-DHI-DT-22-970 | 2022-11-07 | RR | DE-GUP-DT-E-22-1188 | 2022-12-23 | B | CRS-GUP-DHI-DT-22-1449 | 2023-02-03 | RC | DE-GUP-DT-E-23-248 | 2023-02-27 | C | CRS-GUP-DHI-DT-23-1674 | 2023-03-10 | RC | DE-GUP-DT-E-23-365 | 2023-03-24 | D | DE-GUP-DT-E-23-1823 | 2023-04-12 | AA | DE-GUP-DT-E-23-472 | 2023-04-14 | 0(CP) | DE-GUP-DT-E-23-1880 | 2023-04-27 | AA | DE-GUP-DT-E-23-602 | 2023-06-02 | 1 | 자체 CRS 개정 후 제출 | 2023-11-13 | N/A | DE-GUP-DT-E-23-909 | 2023-11-14 | 2
| GUP | CA00 | P1 | UST | 181514 |  | GUP-CA00-P1UST-181514 | MAINTENANCE WORKSHOP AND STORE BUILDING_MAIN SECTION | FA | 2022-11-01 | 2023-02-25 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Workshop Building | Arch. | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-602 | 2023-06-02 | 1 | DE-GUP-DT-E-23-1880 | 2023-04-27 | AA | DE-GUP-DT-E-22-869 | 2022-10-27 | A | CRS-GUP-DHI-DT-22-970 | 2022-11-07 | RR | DE-GUP-DT-E-22-1188 | 2022-12-23 | B | CRS-GUP-DHI-DT-22-1449 | 2023-02-03 | RC | DE-GUP-DT-E-23-248 | 2023-02-27 | C | CRS-GUP-DHI-DT-23-1674 | 2023-03-10 | RC | DE-GUP-DT-E-23-365 | 2023-03-24 | D | DE-GUP-DT-E-23-1823 | 2023-04-12 | AA | DE-GUP-DT-E-23-472 | 2023-04-14 | 0(CP) | DE-GUP-DT-E-23-1880 | 2023-04-27 | AA | DE-GUP-DT-E-23-602 | 2023-06-02 | 1
| GUP | CA00 | P1 | UST | 181515 |  | GUP-CA00-P1UST-181515 | MAINTENANCE WORKSHOP AND STORE BUILDING_SIDE ELEVATION | FA | 2022-11-01 | 2023-02-25 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Workshop Building | Arch. | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-602 | 2023-06-02 | 1 | DE-GUP-DT-E-23-1880 | 2023-04-27 | AA | DE-GUP-DT-E-22-869 | 2022-10-27 | A | CRS-GUP-DHI-DT-22-970 | 2022-11-07 | RR | DE-GUP-DT-E-22-1188 | 2022-12-23 | B | CRS-GUP-DHI-DT-22-1449 | 2023-02-03 | RC | DE-GUP-DT-E-23-248 | 2023-02-27 | C | CRS-GUP-DHI-DT-23-1674 | 2023-03-10 | RC | DE-GUP-DT-E-23-365 | 2023-03-24 | D | DE-GUP-DT-E-23-1823 | 2023-04-12 | AA | DE-GUP-DT-E-23-472 | 2023-04-14 | 0(CP) | DE-GUP-DT-E-23-1880 | 2023-04-27 | AA | DE-GUP-DT-E-23-602 | 2023-06-02 | 1
| GUP | CA00 | P1 | UST | 181516 |  | GUP-CA00-P1UST-181516 | MAINTENANCE WORKSHOP AND STORE BUILDING_ENLARGED TOILET PLAN & ELEVATION | FI | 2022-11-01 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | Workshop Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-602 | 2023-06-02 | 5 | DE-GUP-DT-E-23-1880 | 2023-04-27 | NC | DE-GUP-DT-E-22-869 | 2022-10-27 | 0 | CRS-GUP-DHI-DT-22-970 | 2022-11-07 | RR | DE-GUP-DT-E-22-1188 | 2022-12-23 | 1 | CRS-GUP-DHI-DT-22-1449 | 2023-02-03 | RC | DE-GUP-DT-E-23-248 | 2023-02-27 | 2 | CRS-GUP-DHI-DT-23-1674 | 2023-03-10 | RC | DE-GUP-DT-E-23-365 | 2023-03-24 | 3 | DE-GUP-DT-E-23-1823 | 2023-04-12 | NC | DE-GUP-DT-E-23-472 | 2023-04-14 | 4 | DE-GUP-DT-E-23-1880 | 2023-04-27 | NC | DE-GUP-DT-E-23-602 | 2023-06-02 | 5
| GUP | CA00 | P1 | UST | 181517 |  | GUP-CA00-P1UST-181517 | MAINTENANCE WORKSHOP AND STORE BUILDING_CEILING PLAN | FI | 2022-11-01 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Workshop Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-909 | 2023-11-14 | 6 | 자체 CRS 개정 후 제출 | 2023-11-13 | N/A | DE-GUP-DT-E-22-869 | 2022-10-27 | 0 | CRS-GUP-DHI-DT-22-970 | 2022-11-07 | RR | DE-GUP-DT-E-22-1188 | 2022-12-23 | 1 | CRS-GUP-DHI-DT-22-1449 | 2023-02-03 | RC | DE-GUP-DT-E-23-248 | 2023-02-27 | 2 | CRS-GUP-DHI-DT-23-1674 | 2023-03-10 | RC | DE-GUP-DT-E-23-365 | 2023-03-24 | 3 | DE-GUP-DT-E-23-1823 | 2023-04-12 | NC | DE-GUP-DT-E-23-472 | 2023-04-14 | 4 | DE-GUP-DT-E-23-1880 | 2023-04-27 | NC | DE-GUP-DT-E-23-602 | 2023-06-02 | 5 | 자체 CRS 개정 후 제출 | 2023-11-13 | N/A | DE-GUP-DT-E-23-909 | 2023-11-14 | 6
| GUP | CA00 | P1 | UST | 181518 |  | GUP-CA00-P1UST-181518 | MAINTENANCE WORKSHOP AND STORE BUILDING_ARCHITECTURAL MISC. DETAIL | FA | 2023-02-01 | 2023-06-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Workshop Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-909 | 2023-11-14 | 2 | 자체 CRS 개정 후 제출 | 2023-11-13 | N/A | DE-GUP-DT-E-22-869 | 2022-10-27 | A | CRS-GUP-DHI-DT-22-970 | 2022-11-07 | RR | DE-GUP-DT-E-22-1188 | 2022-12-23 | B | CRS-GUP-DHI-DT-22-1449 | 2023-02-03 | RC | DE-GUP-DT-E-23-248 | 2023-02-27 | C | CRS-GUP-DHI-DT-23-1674 | 2023-03-10 | RC | DE-GUP-DT-E-23-365 | 2023-03-24 | D | DE-GUP-DT-E-23-1823 | 2023-04-12 | AA | DE-GUP-DT-E-23-472 | 2023-04-14 | 0(CP) | DE-GUP-DT-E-23-1880 | 2023-04-27 | AA | DE-GUP-DT-E-23-602 | 2023-06-02 | 1 | 자체 CRS 개정 후 제출 | 2023-11-13 | N/A | DE-GUP-DT-E-23-909 | 2023-11-14 | 2
| GUP | CA00 | P1 | UST | 181519 |  | GUP-CA00-P1UST-181519 | MAINTENANCE WORKSHOP AND STORE BUILDING_WALL SECTION | FA | 2023-02-01 | 2023-06-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Workshop Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-909 | 2023-11-14 | 2 | 자체 CRS 개정 후 제출 | 2023-11-13 | N/A | DE-GUP-DT-E-22-869 | 2022-10-27 | A | CRS-GUP-DHI-DT-22-970 | 2022-11-07 | RR | DE-GUP-DT-E-22-1188 | 2022-12-23 | B | CRS-GUP-DHI-DT-22-1449 | 2023-02-03 | RC | DE-GUP-DT-E-23-248 | 2023-02-27 | C | CRS-GUP-DHI-DT-23-1674 | 2023-03-10 | RC | DE-GUP-DT-E-23-365 | 2023-03-24 | D | DE-GUP-DT-E-23-1823 | 2023-04-12 | AA | DE-GUP-DT-E-23-472 | 2023-04-14 | 0(CP) | DE-GUP-DT-E-23-1880 | 2023-04-27 | AA | DE-GUP-DT-E-23-602 | 2023-06-02 | 1 | 자체 CRS 개정 후 제출 | 2023-11-13 | N/A | DE-GUP-DT-E-23-909 | 2023-11-14 | 2
| GUP | CA03 | P1 | UST | 181551 |  | GUP-CA03-P1UST-181551 | MAINTENANCE WORKSHOP AND STORE BUILDING_STEEL COLUMN ARRANGEMENT PLAN | FI | 2023-01-14 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Workshop Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-526 | 2023-05-05 | 2 | CRS-GUP-DHI-DT-23-1949 | 2023-05-17 | NC | DE-GUP-DT-E-23-249 | 2023-02-27 | 0 | CRS-GUP-DHI-DT-23-1675 | 2023-03-10 | RC | DE-GUP-DT-E-23-366 | 2023-03-24 | 1 | CRS-GUP-DHI-DT-23-1813 | 2023-04-12 | NC | DE-GUP-DT-E-23-526 | 2023-05-05 | 2 | CRS-GUP-DHI-DT-23-1949 | 2023-05-17 | NC
| GUP | CA03 | P1 | UST | 181552 |  | GUP-CA03-P1UST-181552 | MAINTENANCE WORKSHOP AND STORE BUILDING_GROUND FLOOR FRAMING PLAN | FI | 2023-01-14 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Workshop Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-526 | 2023-05-05 | 2 | CRS-GUP-DHI-DT-23-1949 | 2023-05-17 | NC | DE-GUP-DT-E-23-249 | 2023-02-27 | 0 | CRS-GUP-DHI-DT-23-1675 | 2023-03-10 | RC | DE-GUP-DT-E-23-366 | 2023-03-24 | 1 | CRS-GUP-DHI-DT-23-1813 | 2023-04-12 | RC | DE-GUP-DT-E-23-526 | 2023-05-05 | 2 | CRS-GUP-DHI-DT-23-1949 | 2023-05-17 | NC
| GUP | CA03 | P1 | UST | 181554 |  | GUP-CA03-P1UST-181554 | MAINTENANCE WORKSHOP AND STORE BUILDING_ROOF FRAMING PLAN | FI | 2023-01-14 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Workshop Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-526 | 2023-05-05 | 2 | CRS-GUP-DHI-DT-23-1949 | 2023-05-17 | NC | DE-GUP-DT-E-23-249 | 2023-02-27 | 0 | CRS-GUP-DHI-DT-23-1675 | 2023-03-10 | RC | DE-GUP-DT-E-23-366 | 2023-03-24 | 1 | CRS-GUP-DHI-DT-23-1813 | 2023-04-12 | NC | DE-GUP-DT-E-23-526 | 2023-05-05 | 2 | CRS-GUP-DHI-DT-23-1949 | 2023-05-17 | NC
| GUP | CA03 | P1 | UST | 181555 |  | GUP-CA03-P1UST-181555 | MAINTENANCE WORKSHOP AND STORE BUILDING_LINE FRAMING ELEVATION | FI | 2023-01-14 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Workshop Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-526 | 2023-05-05 | 2 | CRS-GUP-DHI-DT-23-1949 | 2023-05-17 | NC | DE-GUP-DT-E-23-249 | 2023-02-27 | 0 | CRS-GUP-DHI-DT-23-1675 | 2023-03-10 | RC | DE-GUP-DT-E-23-366 | 2023-03-24 | 1 | CRS-GUP-DHI-DT-23-1813 | 2023-04-12 | NC | DE-GUP-DT-E-23-526 | 2023-05-05 | 2 | CRS-GUP-DHI-DT-23-1949 | 2023-05-17 | NC
| GUP | CA03 | P1 | UST | 181556 |  | GUP-CA03-P1UST-181556 | MAINTENANCE WORKSHOP AND STORE BUILDING_ROW FRAMING ELEVATION | FI | 2023-01-14 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Workshop Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-526 | 2023-05-05 | 2 | CRS-GUP-DHI-DT-23-1949 | 2023-05-17 | NC | DE-GUP-DT-E-23-249 | 2023-02-27 | 0 | CRS-GUP-DHI-DT-23-1675 | 2023-03-10 | RC | DE-GUP-DT-E-23-366 | 2023-03-24 | 1 | CRS-GUP-DHI-DT-23-1813 | 2023-04-12 | NC | DE-GUP-DT-E-23-526 | 2023-05-05 | 2 | CRS-GUP-DHI-DT-23-1949 | 2023-05-17 | NC
| GUP | CA03 | P1 | UST | 181557 |  | GUP-CA03-P1UST-181557 | MAINTENANCE WORKSHOP AND STORE BUILDING_PURLIN ARRANGEMENT PLAN | FI | 2023-02-01 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Workshop Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-526 | 2023-05-05 | 2 | CRS-GUP-DHI-DT-23-1949 | 2023-05-17 | NC | DE-GUP-DT-E-23-249 | 2023-02-27 | 0 | CRS-GUP-DHI-DT-23-1675 | 2023-03-10 | RC | DE-GUP-DT-E-23-366 | 2023-03-24 | 1 | CRS-GUP-DHI-DT-23-1813 | 2023-04-12 | NC | DE-GUP-DT-E-23-526 | 2023-05-05 | 2 | CRS-GUP-DHI-DT-23-1949 | 2023-05-17 | NC
| GUP | CA03 | P1 | UST | 181559 |  | GUP-CA03-P1UST-181559 | MAINTENANCE WORKSHOP AND STORE BUILDING_GIRT LINE ELEVATION | FI | 2023-02-01 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Workshop Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-526 | 2023-05-05 | 2 | CRS-GUP-DHI-DT-23-1949 | 2023-05-17 | NC | DE-GUP-DT-E-23-249 | 2023-02-27 | 0 | CRS-GUP-DHI-DT-23-1675 | 2023-03-10 | RC | DE-GUP-DT-E-23-366 | 2023-03-24 | 1 | CRS-GUP-DHI-DT-23-1813 | 2023-04-12 | NC | DE-GUP-DT-E-23-526 | 2023-05-05 | 2 | CRS-GUP-DHI-DT-23-1949 | 2023-05-17 | NC
| GUP | CA03 | P1 | UST | 181560 |  | GUP-CA03-P1UST-181560 | MAINTENANCE WORKSHOP AND STORE BUILDING_GIRT ROW ELEVATION | FI | 2023-02-01 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Workshop Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-526 | 2023-05-05 | 2 | CRS-GUP-DHI-DT-23-1949 | 2023-05-17 | NC | DE-GUP-DT-E-23-249 | 2023-02-27 | 0 | CRS-GUP-DHI-DT-23-1675 | 2023-03-10 | RC | DE-GUP-DT-E-23-366 | 2023-03-24 | 1 | CRS-GUP-DHI-DT-23-1813 | 2023-04-12 | NC | DE-GUP-DT-E-23-526 | 2023-05-05 | 2 | CRS-GUP-DHI-DT-23-1949 | 2023-05-17 | NC
| GUP | CA03 | P1 | UST | 181561 |  | GUP-CA03-P1UST-181561 | MAINTENANCE WORKSHOP AND STORE BUILDING_ROOF WALKWAY FRAMING PLAN & ELEVATION | FI | 2023-02-01 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Workshop Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-526 | 2023-05-05 | 2 | CRS-GUP-DHI-DT-23-1949 | 2023-05-17 | NC | DE-GUP-DT-E-23-249 | 2023-02-27 | 0 | CRS-GUP-DHI-DT-23-1675 | 2023-03-10 | RC | DE-GUP-DT-E-23-366 | 2023-03-24 | 1 | CRS-GUP-DHI-DT-23-1813 | 2023-04-12 | NC | DE-GUP-DT-E-23-526 | 2023-05-05 | 2 | CRS-GUP-DHI-DT-23-1949 | 2023-05-17 | NC
| GUP | CA01 | P1 | UST | 181533 |  | GUP-CA01-P1UST-181533 | MAINTENANCE WORKSHOP AND STORE BUILDING_EQUIPMENT FOUNDATION DETAIL | FI | 2023-02-01 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | Workshop Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-800 | 2023-09-07 | 1 | CRS-GUP-DHI-DT-23-2119 | 2023-09-27 | NC | DE-GUP-DT-E-23-602 | 2023-06-02 | 0 | CRS-GUP-DHI-DT-23-2014 | 2023-06-21 | RC | DE-GUP-DT-E-23-800 | 2023-09-07 | 1 | CRS-GUP-DHI-DT-23-2119 | 2023-09-27 | NC
| GUP | CA01 | P1 | UST | 181534 |  | GUP-CA01-P1UST-181534 | MAINTENANCE WORKSHOP AND STORE BUILDING_STRUCTURAL MISC. DETAIL | FI | 2023-02-01 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | Workshop Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-526 | 2023-05-05 | 2 | CRS-GUP-DHI-DT-23-1949 | 2023-05-17 | NC | DE-GUP-DT-E-23-249 | 2023-02-27 | 0 | CRS-GUP-DHI-DT-23-1675 | 2023-03-10 | RC | DE-GUP-DT-E-23-366 | 2023-03-24 | 1 | CRS-GUP-DHI-DT-23-1813 | 2023-04-12 | NC | DE-GUP-DT-E-23-526 | 2023-05-05 | 2 | CRS-GUP-DHI-DT-23-1949 | 2023-05-17 | NC
| GUP | CA02 | P1 | UST | 181535 |  | GUP-CA02-P1UST-181535 | MAINTENANCE WORKSHOP AND STORE BUILDING_SLAB & MISC. RE-BAR SCHEDULE | FI | 2023-02-01 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | Workshop Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-526 | 2023-05-05 | 2 | CRS-GUP-DHI-DT-23-1949 | 2023-05-17 | NC | DE-GUP-DT-E-23-249 | 2023-02-27 | 0 | CRS-GUP-DHI-DT-23-1675 | 2023-03-10 | RC | DE-GUP-DT-E-23-366 | 2023-03-24 | 1 | CRS-GUP-DHI-DT-23-1813 | 2023-04-12 | NC | DE-GUP-DT-E-23-526 | 2023-05-05 | 2 | CRS-GUP-DHI-DT-23-1949 | 2023-05-17 | NC
| GUP | CA06 | P1 | USG | 181901 |  | GUP-CA06-P1USG-181901 | FIRE PROTECTION PUMP BUILDING_CALCULATION SHEET | FI | 2022-06-28 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Fire Protection Pump Building | Arch. | 2 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-496 | 2023-04-24 | 4 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | NC | DHI-GUP-DT-22-185 | 2022-04-21 | 0 | CRS-GUP-DHI-DT-22-310 | 2022-04-25 | RR | DE-GUP-DT-E-22-801 | 2022-10-14 | 1 | CRS-GUP-DHI-DT-22-1117 | 2022-11-28 | RC | DE-GUP-DT-E-22-1197 | 2022-12-26 | 2 | CRS-GUP-DHI-DT-23-1426 | 2023-01-31 | NC | DE-GUP-DT-E-23-121 | 2023-02-03 | 3 | CRS-GUP-DHI-DT-23-1566 | 2023-02-23 | NC | DE-GUP-DT-E-23-496 | 2023-04-24 | 4 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | NC
| GUP | CA01 | P1 | USG | 181931 |  | GUP-CA01-P1USG-181931 | FIRE PROTECTION PUMP BUILDING_FOUNDATION ARRANGEMENT PLAN | FA | 2022-06-28 | 2022-11-20 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Fire Protection Pump Building | Arch. | 3 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-496 | 2023-04-24 | 1 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | AA | DHI-GUP-DT-22-185 | 2022-04-21 | A | CRS-GUP-DHI-DT-22-310 | 2022-04-25 | RR | DE-GUP-DT-E-22-801 | 2022-10-14 | B | CRS-GUP-DHI-DT-22-1094 | 2022-11-28 | AC | DE-GUP-DT-E-22-1197 | 2022-12-26 | C | CRS-GUP-DHI-DT-23-1426 | 2023-01-31 | AA | DE-GUP-DT-E-23-121 | 2023-02-03 | 0 | CRS-GUP-DHI-DT-23-1566 | 2023-02-23 | AA | DE-GUP-DT-E-23-496 | 2023-04-24 | 1 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | AA
| GUP | CA02 | P1 | USG | 181932 |  | GUP-CA02-P1USG-181932 | FIRE PROTECTION PUMP BUILDING_FOUNDATION RE-BAR SCHEDULE | FI | 2022-06-28 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Fire Protection Pump Building | Arch. | 3 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-496 | 2023-04-24 | 4 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | NC | DHI-GUP-DT-22-185 | 2022-04-21 | 0 | CRS-GUP-DHI-DT-22-310 | 2022-04-25 | RR | DE-GUP-DT-E-22-801 | 2022-10-14 | 1 | CRS-GUP-DHI-DT-22-1117 | 2022-11-28 | RC | DE-GUP-DT-E-22-1197 | 2022-12-26 | 2 | CRS-GUP-DHI-DT-23-1426 | 2023-01-31 | NC | DE-GUP-DT-E-23-121 | 2023-02-03 | 3 | CRS-GUP-DHI-DT-23-1566 | 2023-02-23 | NC | DE-GUP-DT-E-23-496 | 2023-04-24 | 4 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | NC
| GUP | CA00 | P1 | USG | 181911 |  | GUP-CA00-P1USG-181911 | FIRE PROTECTION PUMP BUILDING_DOOR & WINDOW SCHEDULE | FA | 2022-06-28 | 2022-11-20 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Fire Protection Pump Building | Arch. | 3 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-496 | 2023-04-24 | 1 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | AA | DHI-GUP-DT-22-185 | 2022-04-21 | A | CRS-GUP-DHI-DT-22-310 | 2022-04-25 | RR | DE-GUP-DT-E-22-801 | 2022-10-14 | B | CRS-GUP-DHI-DT-22-1094 | 2022-11-28 | AC | DE-GUP-DT-E-22-1197 | 2022-12-26 | C | CRS-GUP-DHI-DT-23-1426 | 2023-01-31 | AA | DE-GUP-DT-E-23-121 | 2023-02-03 | 0 | CRS-GUP-DHI-DT-23-1566 | 2023-02-23 | AA | DE-GUP-DT-E-23-496 | 2023-04-24 | 1 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | AA
| GUP | CA00 | P1 | USG | 181912 |  | GUP-CA00-P1USG-181912 | FIRE PROTECTION PUMP BUILDING_GROUND FLOOR PLAN | FA | 2022-06-28 | 2022-11-20 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Fire Protection Pump Building | Arch. | 2 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-839 | 2023-10-05 | 2 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | AA | DHI-GUP-DT-22-185 | 2022-04-21 | A | CRS-GUP-DHI-DT-22-310 | 2022-04-25 | RR | DE-GUP-DT-E-22-801 | 2022-10-14 | B | CRS-GUP-DHI-DT-22-1094 | 2022-11-28 | RC | DE-GUP-DT-E-22-1197 | 2022-12-26 | C | CRS-GUP-DHI-DT-23-1426 | 2023-01-31 | AC | DE-GUP-DT-E-23-121 | 2023-02-03 | 0(CP) | CRS-GUP-DHI-DT-23-1566 | 2023-02-23 | AC | DE-GUP-DT-E-23-496 | 2023-04-24 | 1(cp) | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | AA | DE-GUP-DT-E-23-839 | 2023-10-05 | 2
| GUP | CA00 | P1 | USG | 181913 |  | GUP-CA00-P1USG-181913 | FIRE PROTECTION PUMP BUILDING_ROOF PLAN | FA | 2022-06-28 | 2022-11-20 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Fire Protection Pump Building | Arch. | 2 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-897 | 2023-11-09 | 3 | 자체 CRS 개정 후 제출 | 2023-11-08 | N/A | DHI-GUP-DT-22-185 | 2022-04-21 | A | CRS-GUP-DHI-DT-22-310 | 2022-04-25 | RR | DE-GUP-DT-E-22-801 | 2022-10-14 | B | CRS-GUP-DHI-DT-22-1094 | 2022-11-28 | AC | DE-GUP-DT-E-22-1197 | 2022-12-26 | C | CRS-GUP-DHI-DT-23-1426 | 2023-01-31 | AA | DE-GUP-DT-E-23-121 | 2023-02-03 | 0 | CRS-GUP-DHI-DT-23-1566 | 2023-02-23 | AC | DE-GUP-DT-E-23-496 | 2023-04-24 | 1 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | AA | DE-GUP-DT-E-23-839 | 2023-10-05 | 2 | 자체 CRS 개정 후 제출 | 2023-11-08 | N/A | DE-GUP-DT-E-23-897 | 2023-11-09 | 3
| GUP | CA00 | P1 | USG | 181914 |  | GUP-CA00-P1USG-181914 | FIRE PROTECTION PUMP BUILDING_MAIN SECTION | FA | 2022-06-28 | 2022-11-20 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Fire Protection Pump Building | Arch. | 2 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-897 | 2023-11-09 | 3 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | AA | DHI-GUP-DT-22-185 | 2022-04-21 | A | CRS-GUP-DHI-DT-22-310 | 2022-04-25 | RR | DE-GUP-DT-E-22-801 | 2022-10-14 | B | CRS-GUP-DHI-DT-22-1094 | 2022-11-28 | AC | DE-GUP-DT-E-22-1197 | 2022-12-26 | C | CRS-GUP-DHI-DT-23-1426 | 2023-01-31 | AA | DE-GUP-DT-E-23-121 | 2023-02-03 | 0 | CRS-GUP-DHI-DT-23-1566 | 2023-02-23 | AC | DE-GUP-DT-E-23-496 | 2023-04-24 | 1 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | AA | DE-GUP-DT-E-23-839 | 2023-10-05 | 2 | 자체 CRS 개정 후 제출 | 2023-11-08 | N/A | DE-GUP-DT-E-23-897 | 2023-11-09 | 3
| GUP | CA00 | P1 | USG | 181915 |  | GUP-CA00-P1USG-181915 | FIRE PROTECTION PUMP BUILDING_SIDE ELEVATION | FA | 2022-06-28 | 2022-11-20 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Fire Protection Pump Building | Arch. | 2 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-839 | 2023-10-05 | 2 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | AA | DHI-GUP-DT-22-185 | 2022-04-21 | A | CRS-GUP-DHI-DT-22-310 | 2022-04-25 | RR | DE-GUP-DT-E-22-801 | 2022-10-14 | B | CRS-GUP-DHI-DT-22-1094 | 2022-11-28 | AC | DE-GUP-DT-E-22-1197 | 2022-12-26 | C | CRS-GUP-DHI-DT-23-1426 | 2023-01-31 | AC | DE-GUP-DT-E-23-121 | 2023-02-03 | 0(CP) | CRS-GUP-DHI-DT-23-1566 | 2023-02-23 | AC | DE-GUP-DT-E-23-496 | 2023-04-24 | 1(cp) | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | AA | DE-GUP-DT-E-23-839 | 2023-10-05 | 2
| GUP | CA00 | P1 | USG | 181916 |  | GUP-CA00-P1USG-181916 | FIRE PROTECTION PUMP BUILDING_ARCHITECTURAL MISC. DETAIL | FA | 2022-09-29 | 2023-01-28 | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | Fire Protection Pump Building | Arch. | 3 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-839 | 2023-10-05 | 2 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | AA | DHI-GUP-DT-22-185 | 2022-04-21 | A | CRS-GUP-DHI-DT-22-310 | 2022-04-25 | RR | DE-GUP-DT-E-22-801 | 2022-10-14 | B | CRS-GUP-DHI-DT-22-1094 | 2022-11-28 | AC | DE-GUP-DT-E-22-1197 | 2022-12-26 | C | CRS-GUP-DHI-DT-23-1426 | 2023-01-31 | AA | DE-GUP-DT-E-23-121 | 2023-02-03 | 0 | CRS-GUP-DHI-DT-23-1566 | 2023-02-23 | AA | DE-GUP-DT-E-23-496 | 2023-04-24 | 1 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | AA | DE-GUP-DT-E-23-839 | 2023-10-05 | 2
| GUP | CA01 | P1 | USG | 181933 |  | GUP-CA01-P1USG-181933 | FIRE PROTECTION PUMP BUILDING_COLUMN ARRANGEMENT PLAN | FI | 2022-07-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Fire Protection Pump Building | Arch. | 3 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-496 | 2023-04-24 | 4 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | NC | DHI-GUP-DT-22-185 | 2022-04-21 | 0 | CRS-GUP-DHI-DT-22-310 | 2022-04-25 | RR | DE-GUP-DT-E-22-801 | 2022-10-14 | 1 | CRS-GUP-DHI-DT-22-1117 | 2022-11-28 | NC | DE-GUP-DT-E-22-1197 | 2022-12-26 | 2 | CRS-GUP-DHI-DT-23-1426 | 2023-01-31 | NC | DE-GUP-DT-E-23-121 | 2023-02-03 | 3 | CRS-GUP-DHI-DT-23-1566 | 2023-02-23 | NC | DE-GUP-DT-E-23-496 | 2023-04-24 | 4 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | NC
| GUP | CA01 | P1 | USG | 181934 |  | GUP-CA01-P1USG-181934 | FIRE PROTECTION PUMP BUILDING_GROUND FLOOR FRAMING PLAN | FI | 2022-07-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Fire Protection Pump Building | Arch. | 3 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-496 | 2023-04-24 | 4 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | NC | DHI-GUP-DT-22-185 | 2022-04-21 | 0 | CRS-GUP-DHI-DT-22-310 | 2022-04-25 | RR | DE-GUP-DT-E-22-801 | 2022-10-14 | 1 | CRS-GUP-DHI-DT-22-1117 | 2022-11-28 | RC | DE-GUP-DT-E-22-1197 | 2022-12-26 | 2 | CRS-GUP-DHI-DT-23-1426 | 2023-01-31 | NC | DE-GUP-DT-E-23-121 | 2023-02-03 | 3 | CRS-GUP-DHI-DT-23-1566 | 2023-02-23 | RC | DE-GUP-DT-E-23-496 | 2023-04-24 | 4 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | NC
| GUP | CA01 | P1 | USG | 181935 |  | GUP-CA01-P1USG-181935 | FIRE PROTECTION PUMP BUILDING_ROOF FRAMING PLAN | FI | 2022-07-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Fire Protection Pump Building | Arch. | 3 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-839 | 2023-10-05 | 5 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | NC | DHI-GUP-DT-22-185 | 2022-04-21 | 0 | CRS-GUP-DHI-DT-22-310 | 2022-04-25 | RR | DE-GUP-DT-E-22-801 | 2022-10-14 | 1 | CRS-GUP-DHI-DT-22-1117 | 2022-11-28 | NC | DE-GUP-DT-E-22-1197 | 2022-12-26 | 2 | CRS-GUP-DHI-DT-23-1426 | 2023-01-31 | NC | DE-GUP-DT-E-23-121 | 2023-02-03 | 3 | CRS-GUP-DHI-DT-23-1566 | 2023-02-23 | RC | DE-GUP-DT-E-23-496 | 2023-04-24 | 4 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | NC | DE-GUP-DT-E-23-839 | 2023-10-05 | 5
| GUP | CA01 | P1 | USG | 181936 |  | GUP-CA01-P1USG-181936 | FIRE PROTECTION PUMP BUILDING_LINE FRAMING ELEVATION | FI | 2022-07-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Fire Protection Pump Building | Arch. | 3 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-496 | 2023-04-24 | 4 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | NC | DHI-GUP-DT-22-185 | 2022-04-21 | 0 | CRS-GUP-DHI-DT-22-310 | 2022-04-25 | RR | DE-GUP-DT-E-22-801 | 2022-10-14 | 1 | CRS-GUP-DHI-DT-22-1117 | 2022-11-28 | NC | DE-GUP-DT-E-22-1197 | 2022-12-26 | 2 | CRS-GUP-DHI-DT-23-1426 | 2023-01-31 | NC | DE-GUP-DT-E-23-121 | 2023-02-03 | 3 | CRS-GUP-DHI-DT-23-1566 | 2023-02-23 | RC | DE-GUP-DT-E-23-496 | 2023-04-24 | 4 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | NC
| GUP | CA01 | P1 | USG | 181937 |  | GUP-CA01-P1USG-181937 | FIRE PROTECTION PUMP BUILDING_ROW FRAMING ELEVATION | FI | 2022-07-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Fire Protection Pump Building | Arch. | 3 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-839 | 2023-10-05 | 5 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | NC | DHI-GUP-DT-22-185 | 2022-04-21 | 0 | CRS-GUP-DHI-DT-22-310 | 2022-04-25 | RR | DE-GUP-DT-E-22-801 | 2022-10-14 | 1 | CRS-GUP-DHI-DT-22-1117 | 2022-11-28 | RC | DE-GUP-DT-E-22-1197 | 2022-12-26 | 2 | CRS-GUP-DHI-DT-23-1426 | 2023-01-31 | NC | DE-GUP-DT-E-23-121 | 2023-02-03 | 3 | CRS-GUP-DHI-DT-23-1566 | 2023-02-23 | RC | DE-GUP-DT-E-23-496 | 2023-04-24 | 4 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | NC | DE-GUP-DT-E-23-839 | 2023-10-05 | 5
| GUP | CA01 | P1 | USG | 181938 |  | GUP-CA01-P1USG-181938 | FIRE PROTECTION PUMP BUILDING_EQUIPMENT FOUNDATION DETAIL | FI | 2022-11-29 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | Fire Protection Pump Building | Arch. | 3 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-496 | 2023-04-24 | 2 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | NC | DE-GUP-DT-E-22-1197 | 2022-12-26 | 0 | CRS-GUP-DHI-DT-23-1426 | 2023-01-31 | RC | DE-GUP-DT-E-23-121 | 2023-02-03 | 1 | CRS-GUP-DHI-DT-23-1566 | 2023-02-23 | NC | DE-GUP-DT-E-23-496 | 2023-04-24 | 2 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | NC
| GUP | CA01 | P1 | USG | 181939 |  | GUP-CA01-P1USG-181939 | FIRE PROTECTION PUMP BUILDING_STRUCTURAL MISC. DETAIL | FI | 2022-11-29 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | Fire Protection Pump Building | Arch. | 3 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-839 | 2023-10-05 | 3 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | NC | DE-GUP-DT-E-22-1197 | 2022-12-26 | 0 | CRS-GUP-DHI-DT-23-1426 | 2023-01-31 | RC | DE-GUP-DT-E-23-121 | 2023-02-03 | 1 | CRS-GUP-DHI-DT-23-1566 | 2023-02-23 | NC | DE-GUP-DT-E-23-496 | 2023-04-24 | 2 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | NC | DE-GUP-DT-E-23-839 | 2023-10-05 | 3
| GUP | CA02 | P1 | USG | 181940 |  | GUP-CA02-P1USG-181940 | FIRE PROTECTION PUMP BUILDING_SLAB & MISC. RE-BAR SCHEDULE | FI | 2022-11-29 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Fire Protection Pump Building | Arch. | 3 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-496 | 2023-04-24 | 4 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | NC | DHI-GUP-DT-22-185 | 2022-04-21 | 0 | CRS-GUP-DHI-DT-22-310 | 2022-04-25 | RR | DE-GUP-DT-E-22-801 | 2022-10-14 | 1 | CRS-GUP-DHI-DT-22-1117 | 2022-11-28 | RC | DE-GUP-DT-E-22-1197 | 2022-12-26 | 2 | CRS-GUP-DHI-DT-23-1426 | 2023-01-31 | NC | DE-GUP-DT-E-23-121 | 2023-02-03 | 3 | CRS-GUP-DHI-DT-23-1566 | 2023-02-23 | NC | DE-GUP-DT-E-23-496 | 2023-04-24 | 4 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | NC
| GUP | CA02 | P1 | USG | 181941 |  | GUP-CA02-P1USG-181941 | FIRE PROTECTION PUMP BUILDING_BEAM & GIRDER RE-BAR SCHEDULE | FI | 2022-11-29 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Fire Protection Pump Building | Arch. | 3 | 2025-03-18 | 2025-07-02 |  | DE-GUP-DT-E-23-496 | 2023-04-24 | 4 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | NC | DHI-GUP-DT-22-185 | 2022-04-21 | 0 | CRS-GUP-DHI-DT-22-310 | 2022-04-25 | RR | DE-GUP-DT-E-22-801 | 2022-10-14 | 1 | CRS-GUP-DHI-DT-22-1117 | 2022-11-28 | RC | DE-GUP-DT-E-22-1197 | 2022-12-26 | 2 | CRS-GUP-DHI-DT-23-1426 | 2023-01-31 | NC | DE-GUP-DT-E-23-121 | 2023-02-03 | 3 | CRS-GUP-DHI-DT-23-1566 | 2023-02-23 | NC | DE-GUP-DT-E-23-496 | 2023-04-24 | 4 | CRS-GUP-DHI-DT-23-1919 | 2023-05-05 | NC
| GUP | CA06 | P1 | UTA | 183301 |  | GUP-CA06-P1UTA-183301 | FOAM STATION SHELTER_CALCULATION SHEET | FI | 2022-07-14 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | FOAM STATION SHELTER | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-515 | 2023-04-28 | 3 | CRS-GUP-DHI-DT-23-1932 | 2023-05-05 | NC | DE-GUP-DT-E-22-385 | 2022-07-12 | 0 | CRS-GUP-DHI-DT-22-518 | 2022-07-15 | RR | DE-GUP-DT-E-22-972 | 2022-11-22 | 1 | CRS-GUP-DHI-DT-22-1225 | 2022-12-13 | NC | DE-GUP-DT-E-23-009 | 2023-01-12 | 2 | CRS-GUP-DHI-DT-23-1438 | 2023-01-31 | NC | DE-GUP-DT-E-23-515 | 2023-04-28 | 3 | CRS-GUP-DHI-DT-23-1932 | 2023-05-05 | NC
| GUP | CA01 | P1 | UTA | 183331 |  | GUP-CA01-P1UTA-183331 | FOAM STATION SHELTER_FOUNDATION ARRANGEMENT PLAN | FA | 2022-07-14 | 2022-12-20 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | FOAM STATION SHELTER | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-515 | 2023-04-28 | 1 | CRS-GUP-DHI-DT-23-1932 | 2023-05-05 | AA | DE-GUP-DT-E-22-385 | 2022-07-12 | A | CRS-GUP-DHI-DT-22-518 | 2022-07-15 | RR | DE-GUP-DT-E-22-972 | 2022-11-22 | B | CRS-GUP-DHI-DT-22-1225 | 2022-12-13 | AC | DE-GUP-DT-E-23-009 | 2023-01-12 | 0(CP) | CRS-GUP-DHI-DT-23-1438 | 2023-01-31 | AA | DE-GUP-DT-E-23-515 | 2023-04-28 | 1 | CRS-GUP-DHI-DT-23-1932 | 2023-05-05 | AA
| GUP | CA02 | P1 | UTA | 183332 |  | GUP-CA02-P1UTA-183332 | FOAM STATION SHELTER_FOUNDATION RE-BAR SCHEDULE | FI | 2022-07-14 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | FOAM STATION SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-515 | 2023-04-28 | 3 | CRS-GUP-DHI-DT-23-1932 | 2023-05-05 | NC | DE-GUP-DT-E-22-385 | 2022-07-12 | 0 | CRS-GUP-DHI-DT-22-518 | 2022-07-15 | RR | DE-GUP-DT-E-22-972 | 2022-11-22 | 1 | CRS-GUP-DHI-DT-22-1225 | 2022-12-13 | NC | DE-GUP-DT-E-23-009 | 2023-01-12 | 2 | CRS-GUP-DHI-DT-23-1438 | 2023-01-31 | NC | DE-GUP-DT-E-23-515 | 2023-04-28 | 3 | CRS-GUP-DHI-DT-23-1932 | 2023-05-05 | NC
| GUP | CA00 | P1 | UTA | 183311 |  | GUP-CA00-P1UTA-183311 | FOAM STATION SHELTER_GROUND FLOOR & ROOF PLAN | FA | 2022-07-14 | 2022-12-20 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | FOAM STATION SHELTER | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-515 | 2023-04-28 | 1 | CRS-GUP-DHI-DT-23-1932 | 2023-05-05 | AA | DE-GUP-DT-E-22-385 | 2022-07-12 | A | CRS-GUP-DHI-DT-22-518 | 2022-07-15 | RR | DE-GUP-DT-E-22-972 | 2022-11-22 | B | CRS-GUP-DHI-DT-22-1225 | 2022-12-13 | AC | DE-GUP-DT-E-23-009 | 2023-01-12 | 0(CP) | CRS-GUP-DHI-DT-23-1438 | 2023-01-31 | AA | DE-GUP-DT-E-23-515 | 2023-04-28 | 1 | CRS-GUP-DHI-DT-23-1932 | 2023-05-05 | AA
| GUP | CA00 | P1 | UTA | 183312 |  | GUP-CA00-P1UTA-183312 | FOAM STATION SHELTER_MAIN SECTION | FA | 2022-07-14 | 2022-12-20 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | FOAM STATION SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-515 | 2023-04-28 | 1 | CRS-GUP-DHI-DT-23-1932 | 2023-05-05 | AA | DE-GUP-DT-E-22-385 | 2022-07-12 | A | CRS-GUP-DHI-DT-22-518 | 2022-07-15 | RR | DE-GUP-DT-E-22-972 | 2022-11-22 | B | CRS-GUP-DHI-DT-22-1225 | 2022-12-13 | AC | DE-GUP-DT-E-23-009 | 2023-01-12 | 0(CP) | CRS-GUP-DHI-DT-23-1438 | 2023-01-31 | AA | DE-GUP-DT-E-23-515 | 2023-04-28 | 1 | CRS-GUP-DHI-DT-23-1932 | 2023-05-05 | AA
| GUP | CA00 | P1 | UTA | 183313 |  | GUP-CA00-P1UTA-183313 | FOAM STATION SHELTER_SIDE ELEVATION | FA | 2022-07-14 | 2022-12-20 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | FOAM STATION SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-515 | 2023-04-28 | 1 | CRS-GUP-DHI-DT-23-1932 | 2023-05-05 | AA | DE-GUP-DT-E-22-385 | 2022-07-12 | A | CRS-GUP-DHI-DT-22-518 | 2022-07-15 | RR | DE-GUP-DT-E-22-972 | 2022-11-22 | B | CRS-GUP-DHI-DT-22-1225 | 2022-12-13 | AC | DE-GUP-DT-E-23-009 | 2023-01-12 | 0(CP) | CRS-GUP-DHI-DT-23-1438 | 2023-01-31 | AA | DE-GUP-DT-E-23-515 | 2023-04-28 | 1 | CRS-GUP-DHI-DT-23-1932 | 2023-05-05 | AA
| GUP | CA03 | P1 | UTA | 183351 |  | GUP-CA03-P1UTA-183351 | FOAM STATION SHELTER_GROUND FLOOR & ROOF FRAMING PLAN | FI | 2022-07-14 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | FOAM STATION SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-515 | 2023-04-28 | 3 | CRS-GUP-DHI-DT-23-1932 | 2023-05-05 | NC | DE-GUP-DT-E-22-385 | 2022-07-12 | 0 | CRS-GUP-DHI-DT-22-518 | 2022-07-15 | RR | DE-GUP-DT-E-22-972 | 2022-11-22 | 1 | CRS-GUP-DHI-DT-22-1225 | 2022-12-13 | NC | DE-GUP-DT-E-23-009 | 2023-01-12 | 2 | CRS-GUP-DHI-DT-23-1438 | 2023-01-31 | NC | DE-GUP-DT-E-23-515 | 2023-04-28 | 3 | CRS-GUP-DHI-DT-23-1932 | 2023-05-05 | NC
| GUP | CA03 | P1 | UTA | 183352 |  | GUP-CA03-P1UTA-183352 | FOAM STATION SHELTER_LINE & ROW FRAMING ELEVATION | FI | 2022-07-14 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | FOAM STATION SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-515 | 2023-04-28 | 3 | CRS-GUP-DHI-DT-23-1932 | 2023-05-05 | NC | DE-GUP-DT-E-22-385 | 2022-07-12 | 0 | CRS-GUP-DHI-DT-22-518 | 2022-07-15 | RR | DE-GUP-DT-E-22-972 | 2022-11-22 | 1 | CRS-GUP-DHI-DT-22-1225 | 2022-12-13 | NC | DE-GUP-DT-E-23-009 | 2023-01-12 | 2 | CRS-GUP-DHI-DT-23-1438 | 2023-01-31 | NC | DE-GUP-DT-E-23-515 | 2023-04-28 | 3 | CRS-GUP-DHI-DT-23-1932 | 2023-05-05 | NC
| GUP | CA02 | P1 | UTA | 183353 |  | GUP-CA02-P1UTA-183353 | FOAM STATION SHELTER_BEAM, SLAB & MISC. RE-BAR SCHEDULE | FI | 2022-07-14 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | FOAM STATION SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-515 | 2023-04-28 | 3 | CRS-GUP-DHI-DT-23-1932 | 2023-05-05 | NC | DE-GUP-DT-E-22-385 | 2022-07-12 | 0 | CRS-GUP-DHI-DT-22-518 | 2022-07-15 | RR | DE-GUP-DT-E-22-972 | 2022-11-22 | 1 | CRS-GUP-DHI-DT-22-1225 | 2022-12-13 | NC | DE-GUP-DT-E-23-009 | 2023-01-12 | 2 | CRS-GUP-DHI-DT-23-1438 | 2023-01-31 | NC | DE-GUP-DT-E-23-515 | 2023-04-28 | 3 | CRS-GUP-DHI-DT-23-1932 | 2023-05-05 | NC
| GUP | CA06 | P1 | UEL | 183101 |  | GUP-CA06-P1UEL-183101 | ULSD PUMP AND TREATMENT SHELTER_CALCULATION SHEET | FI | 2022-08-15 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ULSD PUMP AND TREATMENT SHELTER | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-517 | 2023-04-28 | 3 | CRS-GUP-DHI-DT-23-1933 | 2023-05-05 | NC | DE-GUP-DT-E-22-509 | 2022-08-17 | 0 | CRS-GUP-DHI-DT-22-713 | 2022-09-05 | RR | DE-GUP-DT-E-23-036 | 2023-01-17 | 1 | CRS-GUP-DHI-DT-23-1476 | 2023-02-09 | RC | DE-GUP-DT-E-23-298 | 2023-03-10 | 2 | CRS-GUP-DHI-DT-23-1767 | 2023-03-22 | NC | DE-GUP-DT-E-23-517 | 2023-04-28 | 3 | CRS-GUP-DHI-DT-23-1933 | 2023-05-05 | NC
| GUP | CA01 | P1 | UEL | 183131 |  | GUP-CA01-P1UEL-183131 | ULSD PUMP AND TREATMENT SHELTER_FOUNDATION ARRANGEMENT PLAN | FA | 2022-08-15 | 2023-02-03 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ULSD PUMP AND TREATMENT SHELTER | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-703 | 2023-07-20 | 2 | CRS-GUP-DHI-DT-23-1933 | 2023-05-05 | AA | DE-GUP-DT-E-22-509 | 2022-08-17 | A | CRS-GUP-DHI-DT-22-713 | 2022-09-05 | RR | DE-GUP-DT-E-23-036 | 2023-01-17 | B | CRS-GUP-DHI-DT-23-1476 | 2023-02-09 | AC | DE-GUP-DT-E-23-298 | 2023-03-10 | 0(CP) | CRS-GUP-DHI-DT-23-1767 | 2023-03-22 | AC | DE-GUP-DT-E-23-517 | 2023-04-28 | 1(CP) | CRS-GUP-DHI-DT-23-1933 | 2023-05-05 | AA | DE-GUP-DT-E-23-703 | 2023-07-20 | 2
| GUP | CA02 | P1 | UEL | 183132 |  | GUP-CA02-P1UEL-183132 | ULSD PUMP AND TREATMENT SHELTER_FOUNDATION RE-BAR SCHEDULE | FI | 2022-08-15 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ULSD PUMP AND TREATMENT SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-517 | 2023-04-28 | 3 | CRS-GUP-DHI-DT-23-1933 | 2023-05-05 | NC | DE-GUP-DT-E-22-509 | 2022-08-17 | 0 | CRS-GUP-DHI-DT-22-713 | 2022-09-05 | RR | DE-GUP-DT-E-23-036 | 2023-01-17 | 1 | CRS-GUP-DHI-DT-23-1476 | 2023-02-09 | NC | DE-GUP-DT-E-23-298 | 2023-03-10 | 2 | CRS-GUP-DHI-DT-23-1767 | 2023-03-22 | NC | DE-GUP-DT-E-23-517 | 2023-04-28 | 3 | CRS-GUP-DHI-DT-23-1933 | 2023-05-05 | NC
| GUP | CA00 | P1 | UEL | 183111 |  | GUP-CA00-P1UEL-183111 | ULSD PUMP AND TREATMENT SHELTER_GROUND FLOOR & ROOF PLAN | FA | 2022-08-15 | 2023-02-03 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ULSD PUMP AND TREATMENT SHELTER | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-517 | 2023-04-28 | 1 | CRS-GUP-DHI-DT-23-1933 | 2023-05-05 | AA | DE-GUP-DT-E-22-509 | 2022-08-17 | A | CRS-GUP-DHI-DT-22-713 | 2022-09-05 | RR | DE-GUP-DT-E-23-036 | 2023-01-17 | B | CRS-GUP-DHI-DT-23-1476 | 2023-02-09 | AC | DE-GUP-DT-E-23-298 | 2023-03-10 | 0(CP) | CRS-GUP-DHI-DT-23-1767 | 2023-03-22 | AA | DE-GUP-DT-E-23-517 | 2023-04-28 | 1 | CRS-GUP-DHI-DT-23-1933 | 2023-05-05 | AA
| GUP | CA00 | P1 | UEL | 183112 |  | GUP-CA00-P1UEL-183112 | ULSD PUMP AND TREATMENT SHELTER_MAIN SECTION | FA | 2022-08-15 | 2023-02-03 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ULSD PUMP AND TREATMENT SHELTER | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-517 | 2023-04-28 | 1 | CRS-GUP-DHI-DT-23-1933 | 2023-05-05 | AA | DE-GUP-DT-E-22-509 | 2022-08-17 | A | CRS-GUP-DHI-DT-22-713 | 2022-09-05 | RR | DE-GUP-DT-E-23-036 | 2023-01-17 | B | CRS-GUP-DHI-DT-23-1476 | 2023-02-09 | AC | DE-GUP-DT-E-23-298 | 2023-03-10 | 0(CP) | CRS-GUP-DHI-DT-23-1767 | 2023-03-22 | AA | DE-GUP-DT-E-23-517 | 2023-04-28 | 1 | CRS-GUP-DHI-DT-23-1933 | 2023-05-05 | AA
| GUP | CA00 | P1 | UEL | 183113 |  | GUP-CA00-P1UEL-183113 | ULSD PUMP AND TREATMENT SHELTER_SIDE ELEVATION | FA | 2022-08-15 | 2023-02-03 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ULSD PUMP AND TREATMENT SHELTER | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-517 | 2023-04-28 | 1 | CRS-GUP-DHI-DT-23-1933 | 2023-05-05 | AA | DE-GUP-DT-E-22-509 | 2022-08-17 | A | CRS-GUP-DHI-DT-22-713 | 2022-09-05 | RR | DE-GUP-DT-E-23-036 | 2023-01-17 | B | CRS-GUP-DHI-DT-23-1476 | 2023-02-09 | AC | DE-GUP-DT-E-23-298 | 2023-03-10 | 0(CP) | CRS-GUP-DHI-DT-23-1767 | 2023-03-22 | AA | DE-GUP-DT-E-23-517 | 2023-04-28 | 1 | CRS-GUP-DHI-DT-23-1933 | 2023-05-05 | AA
| GUP | CA00 | P1 | UEL | 183114 |  | GUP-CA00-P1UEL-183114 | ULSD PUMP AND TREATMENT SHELTER_ARCHITECTURAL MISC. DETAIL | FA | 2022-08-15 | 2023-03-03 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ULSD PUMP AND TREATMENT SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-703 | 2023-07-20 | 2 | CRS-GUP-DHI-DT-23-1933 | 2023-05-05 | AA | DE-GUP-DT-E-22-509 | 2022-08-17 | A | CRS-GUP-DHI-DT-22-713 | 2022-09-05 | RR | DE-GUP-DT-E-23-036 | 2023-01-17 | B | CRS-GUP-DHI-DT-23-1476 | 2023-02-09 | AC | DE-GUP-DT-E-23-298 | 2023-03-10 | 0(CP) | CRS-GUP-DHI-DT-23-1767 | 2023-03-22 | AA | DE-GUP-DT-E-23-517 | 2023-04-28 | 1 | CRS-GUP-DHI-DT-23-1933 | 2023-05-05 | AA | DE-GUP-DT-E-23-703 | 2023-07-20 | 2
| GUP | CA03 | P1 | UEL | 183151 |  | GUP-CA03-P1UEL-183151 | ULSD PUMP AND TREATMENT SHELTER_GROUND FLOOR FRAMING PLAN | FI | 2022-08-15 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ULSD PUMP AND TREATMENT SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-517 | 2023-04-28 | 3 | CRS-GUP-DHI-DT-23-1933 | 2023-05-05 | NC | DE-GUP-DT-E-22-509 | 2022-08-17 | 0 | CRS-GUP-DHI-DT-22-713 | 2022-09-05 | RR | DE-GUP-DT-E-23-036 | 2023-01-17 | 1 | CRS-GUP-DHI-DT-23-1476 | 2023-02-09 | RC | DE-GUP-DT-E-23-298 | 2023-03-10 | 2 | CRS-GUP-DHI-DT-23-1767 | 2023-03-22 | NC | DE-GUP-DT-E-23-517 | 2023-04-28 | 3 | CRS-GUP-DHI-DT-23-1933 | 2023-05-05 | NC
| GUP | CA03 | P1 | UEL | 183152 |  | GUP-CA03-P1UEL-183152 | ULSD PUMP AND TREATMENT SHELTER_ROOF FRAMING PLAN | FI | 2022-08-15 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ULSD PUMP AND TREATMENT SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-517 | 2023-04-28 | 3 | CRS-GUP-DHI-DT-23-1933 | 2023-05-05 | NC | DE-GUP-DT-E-22-509 | 2022-08-17 | 0 | CRS-GUP-DHI-DT-22-713 | 2022-09-05 | RR | DE-GUP-DT-E-23-036 | 2023-01-17 | 1 | CRS-GUP-DHI-DT-23-1476 | 2023-02-09 | NC | DE-GUP-DT-E-23-298 | 2023-03-10 | 2 | CRS-GUP-DHI-DT-23-1767 | 2023-03-22 | NC | DE-GUP-DT-E-23-517 | 2023-04-28 | 3 | CRS-GUP-DHI-DT-23-1933 | 2023-05-05 | NC
| GUP | CA03 | P1 | UEL | 183153 |  | GUP-CA03-P1UEL-183153 | ULSD PUMP AND TREATMENT SHELTER_LINE & ROW FRAMING ELEVATION | FI | 2022-08-15 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ULSD PUMP AND TREATMENT SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-517 | 2023-04-28 | 3 | CRS-GUP-DHI-DT-23-1933 | 2023-05-05 | NC | DE-GUP-DT-E-22-509 | 2022-08-17 | 0 | CRS-GUP-DHI-DT-22-713 | 2022-09-05 | RR | DE-GUP-DT-E-23-036 | 2023-01-17 | 1 | CRS-GUP-DHI-DT-23-1476 | 2023-02-09 | NC | DE-GUP-DT-E-23-298 | 2023-03-10 | 2 | CRS-GUP-DHI-DT-23-1767 | 2023-03-22 | NC | DE-GUP-DT-E-23-517 | 2023-04-28 | 3 | CRS-GUP-DHI-DT-23-1933 | 2023-05-05 | NC
| GUP | CA01 | P1 | UEL | 183133 |  | GUP-CA01-P1UEL-183133 | ULSD PUMP AND TREATMENT SHELTER_EQUIPMENT FOUNDATION DETAIL | FI | 2022-08-15 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | ULSD PUMP AND TREATMENT SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-517 | 2023-04-28 | 2 | CRS-GUP-DHI-DT-23-1933 | 2023-05-05 | NC | DE-GUP-DT-E-23-036 | 2023-01-17 | 0 | CRS-GUP-DHI-DT-23-1476 | 2023-02-09 | NC | DE-GUP-DT-E-23-298 | 2023-03-10 | 1 | CRS-GUP-DHI-DT-23-1767 | 2023-03-22 | NC | [6 empty] | DE-GUP-DT-E-23-517 | 2023-04-28 | 2 | CRS-GUP-DHI-DT-23-1933 | 2023-05-05 | NC
| GUP | CA02 | P1 | UEL | 183134 |  | GUP-CA02-P1UEL-183134 | ULSD PUMP AND TREATMENT SHELTER_BEAM, SLAB & MISC. RE-BAR SCEHDULE | FI | 2022-08-15 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | ULSD PUMP AND TREATMENT SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-703 | 2023-07-20 | 4 | CRS-GUP-DHI-DT-23-1933 | 2023-05-05 | NC | DE-GUP-DT-E-22-509 | 2022-08-17 | 0 | CRS-GUP-DHI-DT-22-713 | 2022-09-05 | RR | DE-GUP-DT-E-23-036 | 2023-01-17 | 1 | CRS-GUP-DHI-DT-23-1476 | 2023-02-09 | RC | DE-GUP-DT-E-23-298 | 2023-03-10 | 2 | CRS-GUP-DHI-DT-23-1767 | 2023-03-22 | NC | DE-GUP-DT-E-23-517 | 2023-04-28 | 3 | CRS-GUP-DHI-DT-23-1933 | 2023-05-05 | NC | DE-GUP-DT-E-23-703 | 2023-07-20 | 4
| GUP | CA06 | P1 | UTF | 183801 |  | GUP-CA06-P1UTF-183801 | COMPRESSED AIR PACKAGE SHELTER_CALCULATION SHEET | FI | 2022-07-13 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | COMPRESSED AIR PACKAGE SHELTER | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-506 | 2023-04-25 | 4 | CRS-GUP-DHI-DT-23-1926 | 2023-05-05 | NC | DE-GUP-DT-E-22-387 | 2022-07-12 | 0 | CRS-GUP-DHI-DT-22-517 | 2022-07-13 | RR | DE-GUP-DT-E-22-875 | 2022-10-28 | 1 | CRS-GUP-DHI-DT-22-1082 | 2022-11-19 | RR | DE-GUP-DT-E-22-1237 | 2023-01-09 | 2 | CRS-GUP-DHI-DT-22-1445 | 2023-02-01 | RC | DE-GUP-DT-E-23-228 | 2023-02-23 | 3 | CRS-GUP-DHI-DT-23-1672 | 2023-03-10 | NC | DE-GUP-DT-E-23-506 | 2023-04-25 | 4 | CRS-GUP-DHI-DT-23-1926 | 2023-05-05 | NC
| GUP | CA01 | P1 | UTF | 183831 |  | GUP-CA01-P1UTF-183831 | COMPRESSED AIR PACKAGE SHELTER_FOUNDATION ARRANGEMENT PLAN | FA | 2022-07-13 | 2022-11-02 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | COMPRESSED AIR PACKAGE SHELTER | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-506 | 2023-04-25 | 1 | CRS-GUP-DHI-DT-23-1926 | 2023-05-05 | AA | DE-GUP-DT-E-22-387 | 2022-07-12 | A | CRS-GUP-DHI-DT-22-517 | 2022-07-13 | RR | DE-GUP-DT-E-22-875 | 2022-10-28 | B | CRS-GUP-DHI-DT-22-1082 | 2022-11-19 | RR | DE-GUP-DT-E-22-1237 | 2023-01-09 | C | CRS-GUP-DHI-DT-22-1445 | 2023-02-01 | AC | DE-GUP-DT-E-23-228 | 2023-02-23 | 0(CP) | CRS-GUP-DHI-DT-23-1672 | 2023-03-10 | AA | DE-GUP-DT-E-23-506 | 2023-04-25 | 1 | CRS-GUP-DHI-DT-23-1926 | 2023-05-05 | AA
| GUP | CA02 | P1 | UTF | 183832 |  | GUP-CA02-P1UTF-183832 | COMPRESSED AIR PACKAGE SHELTER_FOUNDATION RE-BAR SCHEDULE | FI | 2022-07-13 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | COMPRESSED AIR PACKAGE SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-506 | 2023-04-25 | 4 | CRS-GUP-DHI-DT-23-1926 | 2023-05-05 | NC | DE-GUP-DT-E-22-387 | 2022-07-12 | 0 | CRS-GUP-DHI-DT-22-517 | 2022-07-13 | RR | DE-GUP-DT-E-22-875 | 2022-10-28 | 1 | CRS-GUP-DHI-DT-22-1082 | 2022-11-19 | RR | DE-GUP-DT-E-22-1237 | 2023-01-09 | 2 | CRS-GUP-DHI-DT-22-1445 | 2023-02-01 | NC | DE-GUP-DT-E-23-228 | 2023-02-23 | 3 | CRS-GUP-DHI-DT-23-1672 | 2023-03-10 | NC | DE-GUP-DT-E-23-506 | 2023-04-25 | 4 | CRS-GUP-DHI-DT-23-1926 | 2023-05-05 | NC
| GUP | CA00 | P1 | UTF | 183811 |  | GUP-CA00-P1UTF-183811 | COMPRESSED AIR PACKAGE SHELTER_GROUND FLOOR & ROOF PLAN | FA | 2022-07-13 | 2022-11-02 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | COMPRESSED AIR PACKAGE SHELTER | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-924 | 2023-11-21 | 2 | CRS-GUP-DHI-DT-23-1926 | 2023-05-05 | AA | DE-GUP-DT-E-22-387 | 2022-07-12 | A | CRS-GUP-DHI-DT-22-517 | 2022-07-13 | RR | DE-GUP-DT-E-22-875 | 2022-10-28 | B | CRS-GUP-DHI-DT-22-1082 | 2022-11-19 | RR | DE-GUP-DT-E-22-1237 | 2023-01-09 | C | CRS-GUP-DHI-DT-22-1445 | 2023-02-01 | AC | DE-GUP-DT-E-23-228 | 2023-02-23 | 0(CP) | CRS-GUP-DHI-DT-23-1672 | 2023-03-10 | AA | DE-GUP-DT-E-23-506 | 2023-04-25 | 1 | CRS-GUP-DHI-DT-23-1926 | 2023-05-05 | AA | DE-GUP-DT-E-23-924 | 2023-11-21 | 2
| GUP | CA00 | P1 | UTF | 183812 |  | GUP-CA00-P1UTF-183812 | COMPRESSED AIR PACKAGE SHELTER_MAIN SECTION | FA | 2022-07-13 | 2022-11-02 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | COMPRESSED AIR PACKAGE SHELTER | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-924 | 2023-11-21 | 2 | CRS-GUP-DHI-DT-23-1926 | 2023-05-05 | AA | DE-GUP-DT-E-22-387 | 2022-07-12 | A | CRS-GUP-DHI-DT-22-517 | 2022-07-13 | RR | DE-GUP-DT-E-22-875 | 2022-10-28 | B | CRS-GUP-DHI-DT-22-1082 | 2022-11-19 | RR | DE-GUP-DT-E-22-1237 | 2023-01-09 | C | CRS-GUP-DHI-DT-22-1445 | 2023-02-01 | AC | DE-GUP-DT-E-23-228 | 2023-02-23 | 0(CP) | CRS-GUP-DHI-DT-23-1672 | 2023-03-10 | AA | DE-GUP-DT-E-23-506 | 2023-04-25 | 1 | CRS-GUP-DHI-DT-23-1926 | 2023-05-05 | AA | DE-GUP-DT-E-23-924 | 2023-11-21 | 2
| GUP | CA00 | P1 | UTF | 183813 |  | GUP-CA00-P1UTF-183813 | COMPRESSED AIR PACKAGE SHELTER_SIDE ELEVATION | FA | 2022-07-13 | 2022-11-02 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | COMPRESSED AIR PACKAGE SHELTER | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-924 | 2023-11-21 | 2 | CRS-GUP-DHI-DT-23-1926 | 2023-05-05 | AA | DE-GUP-DT-E-22-387 | 2022-07-12 | A | CRS-GUP-DHI-DT-22-517 | 2022-07-13 | RR | DE-GUP-DT-E-22-875 | 2022-10-28 | B | CRS-GUP-DHI-DT-22-1082 | 2022-11-19 | RR | DE-GUP-DT-E-22-1237 | 2023-01-09 | C | CRS-GUP-DHI-DT-22-1445 | 2023-02-01 | AC | DE-GUP-DT-E-23-228 | 2023-02-23 | 0(CP) | CRS-GUP-DHI-DT-23-1672 | 2023-03-10 | AA | DE-GUP-DT-E-23-506 | 2023-04-25 | 1 | CRS-GUP-DHI-DT-23-1926 | 2023-05-05 | AA | DE-GUP-DT-E-23-924 | 2023-11-21 | 2
| GUP | CA00 | P1 | UTF | 183814 |  | GUP-CA00-P1UTF-183814 | COMPRESSED AIR PACKAGE SHELTER_ARCHITECTURAL MISC. DETAIL | FA | 2022-07-13 | 2022-11-02 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | COMPRESSED AIR PACKAGE SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-924 | 2023-11-21 | 2 | CRS-GUP-DHI-DT-23-1926 | 2023-05-05 | AA | DE-GUP-DT-E-22-387 | 2022-07-12 | A | CRS-GUP-DHI-DT-22-517 | 2022-07-13 | RR | DE-GUP-DT-E-22-875 | 2022-10-28 | B | CRS-GUP-DHI-DT-22-1082 | 2022-11-19 | RR | DE-GUP-DT-E-22-1237 | 2023-01-09 | C | CRS-GUP-DHI-DT-22-1445 | 2023-02-01 | AC | DE-GUP-DT-E-23-228 | 2023-02-23 | 0(CP) | CRS-GUP-DHI-DT-23-1672 | 2023-03-10 | AA | DE-GUP-DT-E-23-506 | 2023-04-25 | 1 | CRS-GUP-DHI-DT-23-1926 | 2023-05-05 | AA | DE-GUP-DT-E-23-924 | 2023-11-21 | 2
| GUP | CA01 | P1 | UTF | 183833 |  | GUP-CA01-P1UTF-183833 | COMPRESSED AIR PACKAGE SHELTER_GROUND FLOOR FRAMING PLAN | FI | 2022-07-13 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | COMPRESSED AIR PACKAGE SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-924 | 2023-11-21 | 5 | CRS-GUP-DHI-DT-23-1926 | 2023-05-05 | NC | DE-GUP-DT-E-22-387 | 2022-07-12 | 0 | CRS-GUP-DHI-DT-22-517 | 2022-07-13 | RR | DE-GUP-DT-E-22-875 | 2022-10-28 | 1 | CRS-GUP-DHI-DT-22-1082 | 2022-11-19 | RR | DE-GUP-DT-E-22-1237 | 2023-01-09 | 2 | CRS-GUP-DHI-DT-22-1445 | 2023-02-01 | RC | DE-GUP-DT-E-23-228 | 2023-02-23 | 3 | CRS-GUP-DHI-DT-23-1672 | 2023-03-10 | NC | DE-GUP-DT-E-23-506 | 2023-04-25 | 4 | CRS-GUP-DHI-DT-23-1926 | 2023-05-05 | NC | DE-GUP-DT-E-23-924 | 2023-11-21 | 5
| GUP | CA01 | P1 | UTF | 183834 |  | GUP-CA01-P1UTF-183834 | COMPRESSED AIR PACKAGE SHELTER_ROOF FRAMING PLAN | FI | 2022-07-13 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | COMPRESSED AIR PACKAGE SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-506 | 2023-04-25 | 4 | CRS-GUP-DHI-DT-23-1926 | 2023-05-05 | NC | DE-GUP-DT-E-22-387 | 2022-07-12 | 0 | CRS-GUP-DHI-DT-22-517 | 2022-07-13 | RR | DE-GUP-DT-E-22-875 | 2022-10-28 | 1 | CRS-GUP-DHI-DT-22-1082 | 2022-11-19 | RR | DE-GUP-DT-E-22-1237 | 2023-01-09 | 2 | CRS-GUP-DHI-DT-22-1445 | 2023-02-01 | NC | DE-GUP-DT-E-23-228 | 2023-02-23 | 3 | CRS-GUP-DHI-DT-23-1672 | 2023-03-10 | NC | DE-GUP-DT-E-23-506 | 2023-04-25 | 4 | CRS-GUP-DHI-DT-23-1926 | 2023-05-05 | NC
| GUP | CA01 | P1 | UTF | 183835 |  | GUP-CA01-P1UTF-183835 | COMPRESSED AIR PACKAGE SHELTER_LINE & ROW FRAMING ELEVATION | FI | 2022-07-13 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | COMPRESSED AIR PACKAGE SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-506 | 2023-04-25 | 4 | CRS-GUP-DHI-DT-23-1926 | 2023-05-05 | NC | DE-GUP-DT-E-22-387 | 2022-07-12 | 0 | CRS-GUP-DHI-DT-22-517 | 2022-07-13 | RR | DE-GUP-DT-E-22-875 | 2022-10-28 | 1 | CRS-GUP-DHI-DT-22-1082 | 2022-11-19 | RR | DE-GUP-DT-E-22-1237 | 2023-01-09 | 2 | CRS-GUP-DHI-DT-22-1445 | 2023-02-01 | NC | DE-GUP-DT-E-23-228 | 2023-02-23 | 3 | CRS-GUP-DHI-DT-23-1672 | 2023-03-10 | NC | DE-GUP-DT-E-23-506 | 2023-04-25 | 4 | CRS-GUP-DHI-DT-23-1926 | 2023-05-05 | NC
| GUP | CA02 | P1 | UTF | 183836 |  | GUP-CA02-P1UTF-183836 | COMPRESSED AIR PACKAGE SHELTER_BEAM & GIRDER RE-BAR SCHEDULE | FI | 2022-07-13 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | COMPRESSED AIR PACKAGE SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-924 | 2023-11-21 | 5 | CRS-GUP-DHI-DT-23-1926 | 2023-05-05 | NC | DE-GUP-DT-E-22-387 | 2022-07-12 | 0 | CRS-GUP-DHI-DT-22-517 | 2022-07-13 | RR | DE-GUP-DT-E-22-875 | 2022-10-28 | 1 | CRS-GUP-DHI-DT-22-1082 | 2022-11-19 | RR | DE-GUP-DT-E-22-1237 | 2023-01-09 | 2 | CRS-GUP-DHI-DT-22-1445 | 2023-02-01 | NC | DE-GUP-DT-E-23-228 | 2023-02-23 | 3 | CRS-GUP-DHI-DT-23-1672 | 2023-03-10 | NC | DE-GUP-DT-E-23-506 | 2023-04-25 | 4 | CRS-GUP-DHI-DT-23-1926 | 2023-05-05 | NC | DE-GUP-DT-E-23-924 | 2023-11-21 | 5
| GUP | CA02 | P1 | UTF | 183837 |  | GUP-CA02-P1UTF-183837 | COMPRESSED AIR PACKAGE SHELTER_SLAB & MISC. RE-BAR SCHEDULE | FI | 2022-07-13 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | COMPRESSED AIR PACKAGE SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-924 | 2023-11-21 | 5 | CRS-GUP-DHI-DT-23-1926 | 2023-05-05 | NC | DE-GUP-DT-E-22-387 | 2022-07-12 | 0 | CRS-GUP-DHI-DT-22-517 | 2022-07-13 | RR | DE-GUP-DT-E-22-875 | 2022-10-28 | 1 | CRS-GUP-DHI-DT-22-1082 | 2022-11-19 | RR | DE-GUP-DT-E-22-1237 | 2023-01-09 | 2 | CRS-GUP-DHI-DT-22-1445 | 2023-02-01 | RC | DE-GUP-DT-E-23-228 | 2023-02-23 | 3 | CRS-GUP-DHI-DT-23-1672 | 2023-03-10 | NC | DE-GUP-DT-E-23-506 | 2023-04-25 | 4 | CRS-GUP-DHI-DT-23-1926 | 2023-05-05 | NC | DE-GUP-DT-E-23-924 | 2023-11-21 | 5
| GUP | CA06 | P1 | UVE | 183401 |  | GUP-CA06-P1UVE-183401 | AMMONIA STORAGE AND UNLOADING SHELTER_CALCULATION SHEET | FI | 2022-09-05 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | AMMONIA STORAGE AND UNLOADING SHELTER | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-795 | 2023-09-06 | 6 | 자체 CRS 개정 후 제출 | 2023-09-05 | N/A | DE-GUP-DT-E-22-606 | 2022-09-01 | 0 | CRS-GUP-DHI-DT-22-800 | 2022-09-19 | RR | DE-GUP-DT-E-22-802 | 2022-10-14 | 1 | CRS-GUP-DHI-DT-22-1034 | 2022-11-16 | RC | DE-GUP-DT-E-22-1107 | 2022-12-16 | 2 | CRS-GUP-DHI-DT-22-1351 | 2022-12-29 | NC | DE-GUP-DT-E-23-090 | 2023-01-30 | 3 | CRS-GUP-DHI-DT-23-1537 | 2023-02-15 | NC | DE-GUP-DT-E-23-336 | 2023-03-21 | 4 | CRS-GUP-DHI-DT-23-1809 | 2023-04-04 | NC | DE-GUP-DT-E-23-702 | 2023-07-20 | 5 | 자체 CRS 개정 후 제출 | 2023-09-05 | N/A | DE-GUP-DT-E-23-795 | 2023-09-06 | 6
| GUP | CA01 | P1 | UVE | 183431 |  | GUP-CA01-P1UVE-183431 | AMMONIA STORAGE AND UNLOADING SHELTER_FOUNDATION ARRANGEMENT PLAN | FA | 2022-09-05 | 2022-12-05 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | AMMONIA STORAGE AND UNLOADING SHELTER | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-702 | 2023-07-20 | 2 | CRS-GUP-DHI-DT-23-1809 | 2023-04-04 | AA | DE-GUP-DT-E-22-606 | 2022-09-01 | A | CRS-GUP-DHI-DT-22-800 | 2022-09-19 | RR | DE-GUP-DT-E-22-802 | 2022-10-14 | B | CRS-GUP-DHI-DT-22-1034 | 2022-11-16 | RC | DE-GUP-DT-E-22-1107 | 2022-12-16 | C | CRS-GUP-DHI-DT-22-1351 | 2022-12-29 | AC | DE-GUP-DT-E-23-090 | 2023-01-30 | 0(CP) | CRS-GUP-DHI-DT-23-1537 | 2023-02-15 | AC | DE-GUP-DT-E-23-336 | 2023-03-21 | 1(CP) | CRS-GUP-DHI-DT-23-1809 | 2023-04-04 | AA | DE-GUP-DT-E-23-702 | 2023-07-20 | 2
| GUP | CA02 | P1 | UVE | 183432 |  | GUP-CA02-P1UVE-183432 | AMMONIA STORAGE AND UNLOADING SHELTER_FOUNDATION RE-BAR SCHEDULE | FI | 2022-09-05 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | AMMONIA STORAGE AND UNLOADING SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-336 | 2023-03-21 | 4 | CRS-GUP-DHI-DT-23-1809 | 2023-04-04 | NC | DE-GUP-DT-E-22-606 | 2022-09-01 | 0 | CRS-GUP-DHI-DT-22-800 | 2022-09-19 | RR | DE-GUP-DT-E-22-802 | 2022-10-14 | 1 | CRS-GUP-DHI-DT-22-1095 | 2022-11-21 | NC | DE-GUP-DT-E-22-1107 | 2022-12-16 | 2 | CRS-GUP-DHI-DT-22-1351 | 2022-12-29 | NC | DE-GUP-DT-E-23-090 | 2023-01-30 | 3 | CRS-GUP-DHI-DT-23-1537 | 2023-02-15 | NC | DE-GUP-DT-E-23-336 | 2023-03-21 | 4 | CRS-GUP-DHI-DT-23-1809 | 2023-04-04 | NC
| GUP | CA00 | P1 | UVE | 183411 |  | GUP-CA00-P1UVE-183411 | AMMONIA STORAGE AND UNLOADING SHELTER_GROUND FLOOR & ROOF PLAN | FA | 2022-09-05 | 2022-12-05 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | AMMONIA STORAGE AND UNLOADING SHELTER | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-702 | 2023-07-20 | 2 | CRS-GUP-DHI-DT-23-1809 | 2023-04-04 | AA | DE-GUP-DT-E-22-606 | 2022-09-01 | A | CRS-GUP-DHI-DT-22-800 | 2022-09-19 | RR | DE-GUP-DT-E-22-802 | 2022-10-14 | B | CRS-GUP-DHI-DT-22-1034 | 2022-11-16 | RC | DE-GUP-DT-E-22-1107 | 2022-12-16 | C | CRS-GUP-DHI-DT-22-1351 | 2022-12-29 | AC | DE-GUP-DT-E-23-090 | 2023-01-30 | 0(CP) | CRS-GUP-DHI-DT-23-1537 | 2023-02-15 | AC | DE-GUP-DT-E-23-336 | 2023-03-21 | 1(CP) | CRS-GUP-DHI-DT-23-1809 | 2023-04-04 | AA | DE-GUP-DT-E-23-702 | 2023-07-20 | 2
| GUP | CA00 | P1 | UVE | 183412 |  | GUP-CA00-P1UVE-183412 | AMMONIA STORAGE AND UNLOADING SHELTER_MAIN SECTION | FA | 2022-09-05 | 2022-12-05 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | AMMONIA STORAGE AND UNLOADING SHELTER | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-702 | 2023-07-20 | 2 | CRS-GUP-DHI-DT-23-1809 | 2023-04-04 | AA | DE-GUP-DT-E-22-606 | 2022-09-01 | A | CRS-GUP-DHI-DT-22-800 | 2022-09-19 | RR | DE-GUP-DT-E-22-802 | 2022-10-14 | B | CRS-GUP-DHI-DT-22-1034 | 2022-11-16 | RC | DE-GUP-DT-E-22-1107 | 2022-12-16 | C | CRS-GUP-DHI-DT-22-1351 | 2022-12-29 | AC | DE-GUP-DT-E-23-090 | 2023-01-30 | 0(CP) | CRS-GUP-DHI-DT-23-1537 | 2023-02-15 | AC | DE-GUP-DT-E-23-336 | 2023-03-21 | 1(CP) | CRS-GUP-DHI-DT-23-1809 | 2023-04-04 | AA | DE-GUP-DT-E-23-702 | 2023-07-20 | 2
| GUP | CA00 | P1 | UVE | 183413 |  | GUP-CA00-P1UVE-183413 | AMMONIA STORAGE AND UNLOADING SHELTER_SIDE ELEVATION | FA | 2022-09-05 | 2022-12-05 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | AMMONIA STORAGE AND UNLOADING SHELTER | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-702 | 2023-07-20 | 2 | CRS-GUP-DHI-DT-23-1809 | 2023-04-04 | AA | DE-GUP-DT-E-22-606 | 2022-09-01 | A | CRS-GUP-DHI-DT-22-800 | 2022-09-19 | RR | DE-GUP-DT-E-22-802 | 2022-10-14 | B | CRS-GUP-DHI-DT-22-1034 | 2022-11-16 | RC | DE-GUP-DT-E-22-1107 | 2022-12-16 | C | CRS-GUP-DHI-DT-22-1351 | 2022-12-29 | AC | DE-GUP-DT-E-23-090 | 2023-01-30 | 0(CP) | CRS-GUP-DHI-DT-23-1537 | 2023-02-15 | AC | DE-GUP-DT-E-23-336 | 2023-03-21 | 1(CP) | CRS-GUP-DHI-DT-23-1809 | 2023-04-04 | AA | DE-GUP-DT-E-23-702 | 2023-07-20 | 2
| GUP | CA00 | P1 | UVE | 183414 |  | GUP-CA00-P1UVE-183414 | AMMONIA STORAGE AND UNLOADING SHELTER_ARCHITECTURAL MISC. DETAIL | FA | 2022-09-05 | 2022-12-05 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | AMMONIA STORAGE AND UNLOADING SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-702 | 2023-07-20 | 2 | CRS-GUP-DHI-DT-23-1809 | 2023-04-04 | AA | DE-GUP-DT-E-22-606 | 2022-09-01 | A | CRS-GUP-DHI-DT-22-800 | 2022-09-19 | RR | DE-GUP-DT-E-22-802 | 2022-10-14 | B | CRS-GUP-DHI-DT-22-1034 | 2022-11-16 | RC | DE-GUP-DT-E-22-1107 | 2022-12-16 | C | CRS-GUP-DHI-DT-22-1351 | 2022-12-29 | AA | DE-GUP-DT-E-23-090 | 2023-01-30 | 0(CP) | CRS-GUP-DHI-DT-23-1537 | 2023-02-15 | AC | DE-GUP-DT-E-23-336 | 2023-03-21 | 1(CP) | CRS-GUP-DHI-DT-23-1809 | 2023-04-04 | AA | DE-GUP-DT-E-23-702 | 2023-07-20 | 2
| GUP | CA03 | P1 | UVE | 183451 |  | GUP-CA03-P1UVE-183451 | AMMONIA STORAGE AND UNLOADING SHELTER_COLUMN ARRANGEMENT PLAN | FI | 2022-09-05 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | AMMONIA STORAGE AND UNLOADING SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-336 | 2023-03-21 | 4 | CRS-GUP-DHI-DT-23-1809 | 2023-04-04 | NC | DE-GUP-DT-E-22-606 | 2022-09-01 | 0 | CRS-GUP-DHI-DT-22-800 | 2022-09-19 | RR | DE-GUP-DT-E-22-802 | 2022-10-14 | 1 | CRS-GUP-DHI-DT-22-1095 | 2022-11-21 | NC | DE-GUP-DT-E-22-1107 | 2022-12-16 | 2 | CRS-GUP-DHI-DT-22-1351 | 2022-12-29 | NC | DE-GUP-DT-E-23-090 | 2023-01-30 | 3 | CRS-GUP-DHI-DT-23-1537 | 2023-02-15 | NC | DE-GUP-DT-E-23-336 | 2023-03-21 | 4 | CRS-GUP-DHI-DT-23-1809 | 2023-04-04 | NC
| GUP | CA03 | P1 | UVE | 183452 |  | GUP-CA03-P1UVE-183452 | AMMONIA STORAGE AND UNLOADING SHELTER_GROUND FLOOR FRAMING PLAN | FI | 2022-09-05 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | AMMONIA STORAGE AND UNLOADING SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-336 | 2023-03-21 | 4 | CRS-GUP-DHI-DT-23-1809 | 2023-04-04 | NC | DE-GUP-DT-E-22-606 | 2022-09-01 | 0 | CRS-GUP-DHI-DT-22-800 | 2022-09-19 | RR | DE-GUP-DT-E-22-802 | 2022-10-14 | 1 | CRS-GUP-DHI-DT-22-1034 | 2022-11-16 | RC | DE-GUP-DT-E-22-1107 | 2022-12-16 | 2 | CRS-GUP-DHI-DT-22-1351 | 2022-12-29 | RC | DE-GUP-DT-E-23-090 | 2023-01-30 | 3 | CRS-GUP-DHI-DT-23-1537 | 2023-02-15 | RC | DE-GUP-DT-E-23-336 | 2023-03-21 | 4 | CRS-GUP-DHI-DT-23-1809 | 2023-04-04 | NC
| GUP | CA03 | P1 | UVE | 183453 |  | GUP-CA03-P1UVE-183453 | AMMONIA STORAGE AND UNLOADING SHELTER_ROOF FRAMING PLAN | FI | 2022-09-05 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | AMMONIA STORAGE AND UNLOADING SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-336 | 2023-03-21 | 4 | CRS-GUP-DHI-DT-23-1809 | 2023-04-04 | NC | DE-GUP-DT-E-22-606 | 2022-09-01 | 0 | CRS-GUP-DHI-DT-22-800 | 2022-09-19 | RR | DE-GUP-DT-E-22-802 | 2022-10-14 | 1 | CRS-GUP-DHI-DT-22-1095 | 2022-11-21 | NC | DE-GUP-DT-E-22-1107 | 2022-12-16 | 2 | CRS-GUP-DHI-DT-22-1351 | 2022-12-29 | NC | DE-GUP-DT-E-23-090 | 2023-01-30 | 3 | CRS-GUP-DHI-DT-23-1537 | 2023-02-15 | NC | DE-GUP-DT-E-23-336 | 2023-03-21 | 4 | CRS-GUP-DHI-DT-23-1809 | 2023-04-04 | NC
| GUP | CA03 | P1 | UVE | 183454 |  | GUP-CA03-P1UVE-183454 | AMMONIA STORAGE AND UNLOADING SHELTER_LINE FRAMING ELEVATION | FI | 2022-09-05 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | AMMONIA STORAGE AND UNLOADING SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-336 | 2023-03-21 | 4 | CRS-GUP-DHI-DT-23-1809 | 2023-04-04 | NC | DE-GUP-DT-E-22-606 | 2022-09-01 | 0 | CRS-GUP-DHI-DT-22-800 | 2022-09-19 | RR | DE-GUP-DT-E-22-802 | 2022-10-14 | 1 | CRS-GUP-DHI-DT-22-1095 | 2022-11-21 | NC | DE-GUP-DT-E-22-1107 | 2022-12-16 | 2 | CRS-GUP-DHI-DT-22-1351 | 2022-12-29 | NC | DE-GUP-DT-E-23-090 | 2023-01-30 | 3 | CRS-GUP-DHI-DT-23-1537 | 2023-02-15 | NC | DE-GUP-DT-E-23-336 | 2023-03-21 | 4 | CRS-GUP-DHI-DT-23-1809 | 2023-04-04 | NC
| GUP | CA03 | P1 | UVE | 183455 |  | GUP-CA03-P1UVE-183455 | AMMONIA STORAGE AND UNLOADING SHELTER_ROW FRAMING ELEVATION | FI | 2022-09-05 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | AMMONIA STORAGE AND UNLOADING SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-336 | 2023-03-21 | 4 | CRS-GUP-DHI-DT-23-1809 | 2023-04-04 | NC | DE-GUP-DT-E-22-606 | 2022-09-01 | 0 | CRS-GUP-DHI-DT-22-800 | 2022-09-19 | RR | DE-GUP-DT-E-22-802 | 2022-10-14 | 1 | CRS-GUP-DHI-DT-22-1095 | 2022-11-21 | NC | DE-GUP-DT-E-22-1107 | 2022-12-16 | 2 | CRS-GUP-DHI-DT-22-1351 | 2022-12-29 | NC | DE-GUP-DT-E-23-090 | 2023-01-30 | 3 | CRS-GUP-DHI-DT-23-1537 | 2023-02-15 | NC | DE-GUP-DT-E-23-336 | 2023-03-21 | 4 | CRS-GUP-DHI-DT-23-1809 | 2023-04-04 | NC
| GUP | CA01 | P1 | UVE | 183433 |  | GUP-CA01-P1UVE-183433 | AMMONIA STORAGE AND UNLOADING SHELTER_EQUIPMENT FOUNDATION DETAIL | FI | 2022-09-05 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | AMMONIA STORAGE AND UNLOADING SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-795 | 2023-09-06 | 4 | 자체 CRS 개정 후 제출 | 2023-09-05 | N/A | DE-GUP-DT-E-22-1107 | 2022-12-16 | 0 | CRS-GUP-DHI-DT-22-1351 | 2022-12-29 | NC | DE-GUP-DT-E-23-090 | 2023-01-30 | 1 | CRS-GUP-DHI-DT-23-1537 | 2023-02-15 | NC | DE-GUP-DT-E-23-336 | 2023-03-21 | 2 | CRS-GUP-DHI-DT-23-1809 | 2023-04-04 | NC | DE-GUP-DT-E-23-702 | 2023-07-20 | 3 | 자체 CRS 개정 후 제출 | 2023-09-05 | N/A | DE-GUP-DT-E-23-795 | 2023-09-06 | 4
| GUP | CA03 | P1 | UVE | 183456 |  | GUP-CA03-P1UVE-183456 | AMMONIA STORAGE AND UNLOADING SHELTER_PURLIN ARRANGEMENT PLAN | FI | 2022-09-05 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | AMMONIA STORAGE AND UNLOADING SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-336 | 2023-03-21 | 4 | CRS-GUP-DHI-DT-23-1809 | 2023-04-04 | NC | DE-GUP-DT-E-22-606 | 2022-09-01 | 0 | CRS-GUP-DHI-DT-22-800 | 2022-09-19 | RR | DE-GUP-DT-E-22-802 | 2022-10-14 | 1 | CRS-GUP-DHI-DT-22-1095 | 2022-11-21 | NC | DE-GUP-DT-E-22-1107 | 2022-12-16 | 2 | CRS-GUP-DHI-DT-22-1351 | 2022-12-29 | NC | DE-GUP-DT-E-23-090 | 2023-01-30 | 3 | CRS-GUP-DHI-DT-23-1537 | 2023-02-15 | NC | DE-GUP-DT-E-23-336 | 2023-03-21 | 4 | CRS-GUP-DHI-DT-23-1809 | 2023-04-04 | NC
| GUP | CA01 | P1 | UVE | 183434 |  | GUP-CA01-P1UVE-183434 | AMMONIA STORAGE AND UNLOADING SHELTER_STRUCTURAL DETAIL | FI | 2022-09-05 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | AMMONIA STORAGE AND UNLOADING SHELTER | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-336 | 2023-03-21 | 4 | CRS-GUP-DHI-DT-23-1809 | 2023-04-04 | NC | DE-GUP-DT-E-22-606 | 2022-09-01 | 0 | CRS-GUP-DHI-DT-22-800 | 2022-09-19 | RR | DE-GUP-DT-E-22-802 | 2022-10-14 | 1 | CRS-GUP-DHI-DT-22-1095 | 2022-11-21 | NC | DE-GUP-DT-E-22-1107 | 2022-12-16 | 2 | CRS-GUP-DHI-DT-22-1351 | 2022-12-29 | NC | DE-GUP-DT-E-23-090 | 2023-01-30 | 3 | CRS-GUP-DHI-DT-23-1537 | 2023-02-15 | NC | DE-GUP-DT-E-23-336 | 2023-03-21 | 4 | CRS-GUP-DHI-DT-23-1809 | 2023-04-04 | NC
| GUP | CA06 | P1 | UYC | 181701 |  | GUP-CA06-P1UYC-181701 | ADMINISTRATION BUILDING_CALCULATION SHEET | FA | 2022-08-12 | 2022-11-02 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Admin. Building | Arch. | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-539 | 2023-05-10 | 3 | CRS-GUP-DHI-DT-23-1960 | 2023-05-24 | AA | DE-GUP-DT-E-22-403 | 2022-07-15 | A | CRS-GUP-DHI-DT-22-582 | 2022-08-08 | RC | DE-GUP-DT-E-22-981 | 2022-11-24 | B | CRS-GUP-DHI-DT-22-1246 | 2022-12-13 | AC | DE-GUP-DT-E-22-1186 | 2022-12-23 | 0(CP) | CRS-GUP-DHI-DT-22-1404 | 2023-01-07 | AA | DE-GUP-DT-E-23-212 | 2023-02-21 | 1 | CRS-GUP-DHI-DT-23-1649 | 2023-03-07 | AA | DE-GUP-DT-E-23-379 | 2023-03-28 | 2 | N/A-자체 CRS 개정 | 2023-05-19 | N/A | DE-GUP-DT-E-23-539 | 2023-05-10 | 3 | CRS-GUP-DHI-DT-23-1960 | 2023-05-24 | AA
| GUP | CA01 | P1 | UYC | 181731 |  | GUP-CA01-P1UYC-181731 | ADMINISTRATION BUILDING_FOUNDATION ARRANGEMENT PLAN | FA | 2022-08-12 | 2022-11-02 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Admin. Building | Arch. | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-539 | 2023-05-10 | 3 | CRS-GUP-DHI-DT-23-1960 | 2023-05-24 | AA | DE-GUP-DT-E-22-403 | 2022-07-15 | A | CRS-GUP-DHI-DT-22-582 | 2022-08-08 | RC | DE-GUP-DT-E-22-981 | 2022-11-24 | B | CRS-GUP-DHI-DT-22-1246 | 2022-12-13 | AC | DE-GUP-DT-E-22-1186 | 2022-12-23 | 0(CP) | CRS-GUP-DHI-DT-22-1404 | 2023-01-07 | AC | DE-GUP-DT-E-23-212 | 2023-02-21 | 1(CP) | CRS-GUP-DHI-DT-23-1649 | 2023-03-07 | AA | DE-GUP-DT-E-23-379 | 2023-03-28 | 2 | CRS-GUP-DHI-DT-23-1821 | 2023-04-12 | AA | DE-GUP-DT-E-23-539 | 2023-05-10 | 3 | CRS-GUP-DHI-DT-23-1960 | 2023-05-24 | AA
| GUP | CA02 | P1 | UYC | 181732 |  | GUP-CA02-P1UYC-181732 | ADMINISTRATION BUILDING_FOUNDATION RE-BAR SCHEDULE | FI | 2022-08-12 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Admin. Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-539 | 2023-05-10 | 5 | CRS-GUP-DHI-DT-23-1960 | 2023-05-24 | NC | DE-GUP-DT-E-22-403 | 2022-07-15 | 0 | CRS-GUP-DHI-DT-22-582 | 2022-08-08 | RC | DE-GUP-DT-E-22-981 | 2022-11-24 | 1 | CRS-GUP-DHI-DT-22-1246 | 2022-12-13 | RC | DE-GUP-DT-E-22-1186 | 2022-12-23 | 2 | CRS-GUP-DHI-DT-22-1404 | 2023-01-07 | RC | DE-GUP-DT-E-23-212 | 2023-02-21 | 3 | CRS-GUP-DHI-DT-23-1649 | 2023-03-07 | NC | DE-GUP-DT-E-23-379 | 2023-03-28 | 4 | CRS-GUP-DHI-DT-23-1821 | 2023-04-12 | NC | DE-GUP-DT-E-23-539 | 2023-05-10 | 5 | CRS-GUP-DHI-DT-23-1960 | 2023-05-24 | NC
| GUP | CA00 | P1 | UYC | 181711 |  | GUP-CA00-P1UYC-181711 | ADMINISTRATION BUILDING_INTERIOR FINISH SCHEDULE | FA | 2022-08-12 | 2023-01-11 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Admin. Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-539 | 2023-05-10 | 3 | CRS-GUP-DHI-DT-23-1960 | 2023-05-24 | AA | DE-GUP-DT-E-22-403 | 2022-07-15 | A | CRS-GUP-DHI-DT-22-582 | 2022-08-08 | RC | DE-GUP-DT-E-22-981 | 2022-11-24 | B | CRS-GUP-DHI-DT-22-1246 | 2022-12-13 | AC | DE-GUP-DT-E-22-1186 | 2022-12-23 | 0(CP) | CRS-GUP-DHI-DT-22-1404 | 2023-01-07 | AA | DE-GUP-DT-E-23-212 | 2023-02-21 | 1 | CRS-GUP-DHI-DT-23-1649 | 2023-03-07 | AC | DE-GUP-DT-E-23-379 | 2023-03-28 | 2 | CRS-GUP-DHI-DT-23-1821 | 2023-04-12 | AA | DE-GUP-DT-E-23-539 | 2023-05-10 | 3 | CRS-GUP-DHI-DT-23-1960 | 2023-05-24 | AA
| GUP | CA00 | P1 | UYC | 181712 |  | GUP-CA00-P1UYC-181712 | ADMINISTRATION BUILDING_DOOR & WINDOW SCHEDULE | FA | 2022-08-12 | 2023-01-11 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Admin. Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-069 | 2024-03-08 | 5 | 자체 CRS 개정 후 제출 | 2024-03-07 | N/A | DE-GUP-DT-E-22-403 | 2022-07-15 | A | CRS-GUP-DHI-DT-22-582 | 2022-08-08 | RC | DE-GUP-DT-E-22-981 | 2022-11-24 | B | CRS-GUP-DHI-DT-22-1246 | 2022-12-13 | AC | DE-GUP-DT-E-22-1186 | 2022-12-23 | 0(CP) | CRS-GUP-DHI-DT-22-1404 | 2023-01-07 | AA | DE-GUP-DT-E-23-212 | 2023-02-21 | 1 | CRS-GUP-DHI-DT-23-1649 | 2023-03-07 | AC | DE-GUP-DT-E-23-379 | 2023-03-28 | 2 | CRS-GUP-DHI-DT-23-1821 | 2023-04-12 | AA | DE-GUP-DT-E-23-539 | 2023-05-10 | 3 | CRS-GUP-DHI-DT-23-1960 | 2023-05-24 | AA | DE-GUP-DT-E-23-783 | 2023-08-31 | 4 | 자체 CRS 개정 후 제출 | 2024-03-07 | N/A | DE-GUP-DT-E-24-069 | 2024-03-08 | 5
| GUP | CA00 | P1 | UYC | 181713 |  | GUP-CA00-P1UYC-181713 | ADMINISTRATION BUILDING_GROUND FLOOR PLAN | FA | 2022-08-12 | 2022-11-02 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Admin. Building | Arch. | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-069 | 2024-03-08 | 5 | 자체 CRS 개정 후 제출 | 2024-03-07 | N/A | DE-GUP-DT-E-22-403 | 2022-07-15 | A | CRS-GUP-DHI-DT-22-582 | 2022-08-08 | RC | DE-GUP-DT-E-22-981 | 2022-11-24 | B | CRS-GUP-DHI-DT-22-1246 | 2022-12-13 | AC | DE-GUP-DT-E-22-1186 | 2022-12-23 | 0(CP) | CRS-GUP-DHI-DT-22-1404 | 2023-01-07 | AC | DE-GUP-DT-E-23-212 | 2023-02-21 | 1(CP) | CRS-GUP-DHI-DT-23-1649 | 2023-03-07 | AC | DE-GUP-DT-E-23-379 | 2023-03-28 | 2(CP) | CRS-GUP-DHI-DT-23-1821 | 2023-04-12 | AA | DE-GUP-DT-E-23-539 | 2023-05-10 | 3 | CRS-GUP-DHI-DT-23-1960 | 2023-05-24 | AA | DE-GUP-DT-E-23-783 | 2023-08-31 | 4 | 자체 CRS 개정 후 제출 | 2024-03-07 | N/A | DE-GUP-DT-E-24-069 | 2024-03-08 | 5
| GUP | CA00 | P1 | UYC | 181714 |  | GUP-CA00-P1UYC-181714 | ADMINISTRATION BUILDING_SECOND FLOOR PLAN | FA | 2022-08-12 | 2022-11-02 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Admin. Building | Arch. | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-188 | 2024-07-23 | 6 | 자체 CRS 개정 후 제출 | 2024-07-22 | N/A | DE-GUP-DT-E-22-403 | 2022-07-15 | A | CRS-GUP-DHI-DT-22-582 | 2022-08-08 | RC | DE-GUP-DT-E-22-981 | 2022-11-24 | B | CRS-GUP-DHI-DT-22-1246 | 2022-12-13 | AC | DE-GUP-DT-E-22-1186 | 2022-12-23 | 0(CP) | CRS-GUP-DHI-DT-22-1404 | 2023-01-07 | AA | DE-GUP-DT-E-23-212 | 2023-02-21 | 1 | CRS-GUP-DHI-DT-23-1649 | 2023-03-07 | AC | DE-GUP-DT-E-23-379 | 2023-03-28 | 2 | CRS-GUP-DHI-DT-23-1821 | 2023-04-12 | AA | DE-GUP-DT-E-23-539 | 2023-05-10 | 3 | CRS-GUP-DHI-DT-23-1960 | 2023-05-24 | AA | DE-GUP-DT-E-23-783 | 2023-08-31 | 4 | 자체 CRS 개정 후 제출 | 2024-07-08 | N/A | DE-GUP-DT-E-24-181 | 2024-07-09 | 5 | 자체 CRS 개정 후 제출 | 2024-07-22 | N/A | DE-GUP-DT-E-24-188 | 2024-07-23 | 6
| GUP | CA00 | P1 | UYC | 181715 |  | GUP-CA00-P1UYC-181715 | ADMINISTRATION BUILDING_ROOF PLAN | FA | 2022-08-12 | 2022-11-02 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Admin. Building | Arch. | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-689 | 2023-07-13 | 4 | CRS-GUP-DHI-DT-23-1960 | 2023-05-24 | AA | DE-GUP-DT-E-22-403 | 2022-07-15 | A | CRS-GUP-DHI-DT-22-582 | 2022-08-08 | RC | DE-GUP-DT-E-22-981 | 2022-11-24 | B | CRS-GUP-DHI-DT-22-1246 | 2022-12-13 | AC | DE-GUP-DT-E-22-1186 | 2022-12-23 | 0(CP) | CRS-GUP-DHI-DT-22-1404 | 2023-01-07 | AC | DE-GUP-DT-E-23-212 | 2023-02-21 | 1(CP) | CRS-GUP-DHI-DT-23-1649 | 2023-03-07 | AC | DE-GUP-DT-E-23-379 | 2023-03-28 | 2(CP) | CRS-GUP-DHI-DT-23-1821 | 2023-04-12 | AA | DE-GUP-DT-E-23-539 | 2023-05-10 | 3 | CRS-GUP-DHI-DT-23-1960 | 2023-05-24 | AA | DE-GUP-DT-E-23-689 | 2023-07-13 | 4
| GUP | CA00 | P1 | UYC | 181716 |  | GUP-CA00-P1UYC-181716 | ADMINISTRATION BUILDING_MAIN SECTION | FA | 2022-08-12 | 2022-11-02 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Admin. Building | Arch. | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-783 | 2023-08-31 | 4 | CRS-GUP-DHI-DT-23-1960 | 2023-05-24 | AA | DE-GUP-DT-E-22-403 | 2022-07-15 | A | CRS-GUP-DHI-DT-22-582 | 2022-08-08 | RC | DE-GUP-DT-E-22-981 | 2022-11-24 | B | CRS-GUP-DHI-DT-22-1246 | 2022-12-13 | AC | DE-GUP-DT-E-22-1186 | 2022-12-23 | 0(CP) | CRS-GUP-DHI-DT-22-1404 | 2023-01-07 | AA | DE-GUP-DT-E-23-212 | 2023-02-21 | 1 | CRS-GUP-DHI-DT-23-1649 | 2023-03-07 | AC | DE-GUP-DT-E-23-379 | 2023-03-28 | 2 | CRS-GUP-DHI-DT-23-1821 | 2023-04-12 | AA | DE-GUP-DT-E-23-539 | 2023-05-10 | 3 | CRS-GUP-DHI-DT-23-1960 | 2023-05-24 | AA | DE-GUP-DT-E-23-783 | 2023-08-31 | 4
| GUP | CA00 | P1 | UYC | 181717 |  | GUP-CA00-P1UYC-181717 | ADMINISTRATION BUILDING_SIDE ELEVATION | FA | 2022-08-12 | 2022-11-02 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Admin. Building | Arch. | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-783 | 2023-08-31 | 5 | 자체 CRS 개정 후 제출 | 2023-08-30 | N/A | DE-GUP-DT-E-22-403 | 2022-07-15 | A | CRS-GUP-DHI-DT-22-582 | 2022-08-08 | RC | DE-GUP-DT-E-22-981 | 2022-11-24 | B | CRS-GUP-DHI-DT-22-1246 | 2022-12-13 | AC | DE-GUP-DT-E-22-1186 | 2022-12-23 | 0(CP) | CRS-GUP-DHI-DT-22-1404 | 2023-01-07 | AA | DE-GUP-DT-E-23-212 | 2023-02-21 | 1 | CRS-GUP-DHI-DT-23-1649 | 2023-03-07 | AC | DE-GUP-DT-E-23-379 | 2023-03-28 | 2 | CRS-GUP-DHI-DT-23-1821 | 2023-04-12 | AA | DE-GUP-DT-E-23-539 | 2023-05-10 | 3 | CRS-GUP-DHI-DT-23-1960 | 2023-05-24 | AA | DE-GUP-DT-E-23-689 | 2023-07-13 | 4 | 자체 CRS 개정 후 제출 | 2023-08-30 | N/A | DE-GUP-DT-E-23-783 | 2023-08-31 | 5
| GUP | CA00 | P1 | UYC | 181718 |  | GUP-CA00-P1UYC-181718 | ADMINISTRATION BUILDING_ENLARGED STAIRCASE & ELEVATOR PLAN & SECTION | FA | 2022-08-12 | 2022-11-02 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Admin. Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-783 | 2023-08-31 | 5 | 자체 CRS 개정 후 제출 | 2023-08-30 | N/A | DE-GUP-DT-E-22-403 | 2022-07-15 | A | CRS-GUP-DHI-DT-22-582 | 2022-08-08 | RC | DE-GUP-DT-E-22-981 | 2022-11-24 | B | CRS-GUP-DHI-DT-22-1246 | 2022-12-13 | AC | DE-GUP-DT-E-22-1186 | 2022-12-23 | 0(CP) | CRS-GUP-DHI-DT-22-1404 | 2023-01-07 | AA | DE-GUP-DT-E-23-212 | 2023-02-21 | 1 | CRS-GUP-DHI-DT-23-1649 | 2023-03-07 | AC | DE-GUP-DT-E-23-379 | 2023-03-28 | 2 | CRS-GUP-DHI-DT-23-1821 | 2023-04-12 | AA | DE-GUP-DT-E-23-539 | 2023-05-10 | 3 | CRS-GUP-DHI-DT-23-1960 | 2023-05-24 | AA | DE-GUP-DT-E-23-689 | 2023-07-13 | 4 | 자체 CRS 개정 후 제출 | 2023-08-30 | N/A | DE-GUP-DT-E-23-783 | 2023-08-31 | 5
| GUP | CA00 | P1 | UYC | 181719 |  | GUP-CA00-P1UYC-181719 | ADMINISTRATION BUILDING_ENLARGED TOILET PLAN & ELEVATION | FA | 2022-12-01 | 2023-04-03 | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | Admin. Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-188 | 2024-07-23 | 4 | 자체 CRS 개정 후 제출 | 2024-07-22 | N/A | DE-GUP-DT-E-23-353 | 2023-03-24 | A | CRS-GUP-DHI-DT-23-1812 | 2023-04-12 | AC | DE-GUP-DT-E-23-518 | 2023-04-28 | 0(CP) | CRS-GUP-DHI-DT-23-1946 | 2023-05-11 | AA | DE-GUP-DT-E-23-598 | 2023-06-02 | 1 | CRS-GUP-DHI-DT-23-1998 | 2023-06-13 | AA | DE-GUP-DT-E-23-677 | 2023-07-06 | 2 | CRS-GUP-DHI-DT-23-2050 | 2023-07-14 | AA | DE-GUP-DT-E-24-181 | 2024-07-09 | 3 | 자체 CRS 개정 후 제출 | 2024-07-22 | N/A | DE-GUP-DT-E-24-188 | 2024-07-23 | 4
| GUP | CA00 | P1 | UYC | 181720 |  | GUP-CA00-P1UYC-181720 | ADMINISTRATION BUILDING_ENLARGED SHOWER ROOM PLAN & ELEVATION | FA | 2022-12-01 | 2023-04-03 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Admin. Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-188 | 2024-07-23 | 4 | 자체 CRS 개정 후 제출 | 2024-07-22 | N/A | DE-GUP-DT-E-23-353 | 2023-03-24 | A | CRS-GUP-DHI-DT-23-1812 | 2023-04-12 | AA | DE-GUP-DT-E-23-518 | 2023-04-28 | 0 | CRS-GUP-DHI-DT-23-1946 | 2023-05-11 | AC | DE-GUP-DT-E-23-598 | 2023-06-02 | 1 | CRS-GUP-DHI-DT-23-1998 | 2023-06-13 | AC | DE-GUP-DT-E-23-677 | 2023-07-06 | 2 | CRS-GUP-DHI-DT-23-2050 | 2023-07-14 | AA | DE-GUP-DT-E-24-181 | 2024-07-09 | 3 | 자체 CRS 개정 후 제출 | 2024-07-22 | N/A | DE-GUP-DT-E-24-188 | 2024-07-23 | 4
| GUP | CA00 | P1 | UYC | 181721 |  | GUP-CA00-P1UYC-181721 | ADMINISTRATION BUILDING_WALL SECTION | FA | 2022-12-01 | 2023-04-03 | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | Admin. Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-783 | 2023-08-31 | 3 | CRS-GUP-DHI-DT-23-2050 | 2023-07-14 | AA | DE-GUP-DT-E-23-353 | 2023-03-24 | A | CRS-GUP-DHI-DT-23-1812 | 2023-04-12 | AA | DE-GUP-DT-E-23-518 | 2023-04-28 | 0 | CRS-GUP-DHI-DT-23-1946 | 2023-05-11 | AA | DE-GUP-DT-E-23-598 | 2023-06-02 | 1 | CRS-GUP-DHI-DT-23-1998 | 2023-06-13 | AA | DE-GUP-DT-E-23-677 | 2023-07-06 | 2 | CRS-GUP-DHI-DT-23-2050 | 2023-07-14 | AA | DE-GUP-DT-E-23-783 | 2023-08-31 | 3
| GUP | CA00 | P1 | UYC | 181722 |  | GUP-CA00-P1UYC-181722 | ADMINISTRATION BUILDING_WALL OPENING PLAN & ELEVATION | FA | 2022-12-01 | 2023-04-03 | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | Admin. Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-783 | 2023-08-31 | 3 | CRS-GUP-DHI-DT-23-2050 | 2023-07-14 | AA | DE-GUP-DT-E-23-353 | 2023-03-24 | A | CRS-GUP-DHI-DT-23-1812 | 2023-04-12 | AC | DE-GUP-DT-E-23-518 | 2023-04-28 | 0(CP) | CRS-GUP-DHI-DT-23-1946 | 2023-05-11 | AA | DE-GUP-DT-E-23-598 | 2023-06-02 | 1 | CRS-GUP-DHI-DT-23-1998 | 2023-06-13 | AA | DE-GUP-DT-E-23-677 | 2023-07-06 | 2 | CRS-GUP-DHI-DT-23-2050 | 2023-07-14 | AA | DE-GUP-DT-E-23-783 | 2023-08-31 | 3
| GUP | CA00 | P1 | UYC | 181723 |  | GUP-CA00-P1UYC-181723 | ADMINISTRATION BUILDING_CEILING PLAN | FA | 2022-12-01 | 2023-04-03 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Admin. Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-181 | 2024-07-09 | 5 | 자체 CRS 개정 후 제출 | 2024-07-08 | N/A | DE-GUP-DT-E-22-403 | 2022-07-15 | A | CRS-GUP-DHI-DT-22-582 | 2022-08-08 | RC | DE-GUP-DT-E-22-981 | 2022-11-24 | B | CRS-GUP-DHI-DT-22-1246 | 2022-12-13 | AC | DE-GUP-DT-E-22-1186 | 2022-12-23 | 0(CP) | CRS-GUP-DHI-DT-22-1404 | 2023-01-07 | AC | DE-GUP-DT-E-23-212 | 2023-02-21 | 1(CP) | CRS-GUP-DHI-DT-23-1649 | 2023-03-07 | AC | DE-GUP-DT-E-23-379 | 2023-03-28 | 2(CP) | CRS-GUP-DHI-DT-23-1821 | 2023-04-12 | AC | DE-GUP-DT-E-23-539 | 2023-05-10 | 3(CP) | CRS-GUP-DHI-DT-23-1960 | 2023-05-24 | AA | DE-GUP-DT-E-23-689 | 2023-07-13 | 4 | 자체 CRS 개정 후 제출 | 2024-07-08 | N/A | DE-GUP-DT-E-24-181 | 2024-07-09 | 5
| GUP | CA00 | P1 | UYC | 181724 |  | GUP-CA00-P1UYC-181724 | ADMINISTRATION BUILDING_ARCHITECTURAL MISC. DETAIL | FA | 2022-12-01 | 2023-04-03 | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | Admin. Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-677 | 2023-07-06 | 2 | CRS-GUP-DHI-DT-23-2050 | 2023-07-14 | AA | DE-GUP-DT-E-23-353 | 2023-03-24 | A | CRS-GUP-DHI-DT-23-1812 | 2023-04-12 | AA | DE-GUP-DT-E-23-518 | 2023-04-28 | 0 | CRS-GUP-DHI-DT-23-1946 | 2023-05-11 | AA | DE-GUP-DT-E-23-598 | 2023-06-02 | 1 | CRS-GUP-DHI-DT-23-1998 | 2023-06-13 | AA | DE-GUP-DT-E-23-677 | 2023-07-06 | 2 | CRS-GUP-DHI-DT-23-2050 | 2023-07-14 | AA
| GUP | CA01 | P1 | UYC | 181733 |  | GUP-CA01-P1UYC-181733 | ADMINISTRATION BUILDING_COLUMN ARRANGEMENT PLAN | FI | 2022-09-12 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Admin. Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-784 | 2023-08-31 | 6 | CRS-GUP-DHI-DT-23-2009 | 2023-06-15 | NC | DE-GUP-DT-E-22-1001 | 2022-11-29 | 0 | CRS-GUP-DHI-DT-22-1257 | 2022-12-13 | NC | DE-GUP-DT-E-22-1231 | 2023-01-06 | 1 | CRS-GUP-DHI-DT-22-1448 | 2023-02-02 | NC | DE-GUP-DT-E-23-213 | 2023-02-21 | 2 | CRS-GUP-DHI-DT-23-1671 | 2023-03-10 | RC | DE-GUP-DT-E-23-375 | 2023-03-27 | 3 | CRS-GUP-DHI-DT-23-1820 | 2023-04-12 | RC | DE-GUP-DT-E-23-519 | 2023-04-28 | 4 | CRS-GUP-DHI-DT-23-1947 | 2023-05-11 | RC | DE-GUP-DT-E-23-597 | 2023-06-01 | 5 | CRS-GUP-DHI-DT-23-2009 | 2023-06-15 | NC | DE-GUP-DT-E-23-784 | 2023-08-31 | 6
| GUP | CA01 | P1 | UYC | 181734 |  | GUP-CA01-P1UYC-181734 | ADMINISTRATION BUILDING_GROUND FLOOR FRAMING PLAN | FI | 2022-09-12 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Admin. Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-026 | 2024-01-25 | 7 | 자체 CRS 개정 후 제출 | 2024-01-24 | N/A | DE-GUP-DT-E-22-1001 | 2022-11-29 | 0 | CRS-GUP-DHI-DT-22-1257 | 2022-12-13 | NC | DE-GUP-DT-E-22-1231 | 2023-01-06 | 1 | CRS-GUP-DHI-DT-22-1448 | 2023-02-02 | NC | DE-GUP-DT-E-23-213 | 2023-02-21 | 2 | CRS-GUP-DHI-DT-23-1671 | 2023-03-10 | RC | DE-GUP-DT-E-23-375 | 2023-03-27 | 3 | CRS-GUP-DHI-DT-23-1820 | 2023-04-12 | RC | DE-GUP-DT-E-23-519 | 2023-04-28 | 4 | CRS-GUP-DHI-DT-23-1947 | 2023-05-11 | RC | DE-GUP-DT-E-23-597 | 2023-06-01 | 5 | CRS-GUP-DHI-DT-23-2009 | 2023-06-15 | NC | DE-GUP-DT-E-23-784 | 2023-08-31 | 6 | 자체 CRS 개정 후 제출 | 2024-01-24 | N/A | DE-GUP-DT-E-24-026 | 2024-01-25 | 7
| GUP | CA01 | P1 | UYC | 181735 |  | GUP-CA01-P1UYC-181735 | ADMINISTRATION BUILDING_SECOND FLOOR FRAMING PLAN | FI | 2022-09-12 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Admin. Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-026 | 2024-01-25 | 7 | 자체 CRS 개정 후 제출 | 2024-01-24 | N/A | DE-GUP-DT-E-22-1001 | 2022-11-29 | 0 | CRS-GUP-DHI-DT-22-1257 | 2022-12-13 | NC | DE-GUP-DT-E-22-1231 | 2023-01-06 | 1 | CRS-GUP-DHI-DT-22-1448 | 2023-02-02 | NC | DE-GUP-DT-E-23-213 | 2023-02-21 | 2 | CRS-GUP-DHI-DT-23-1671 | 2023-03-10 | RC | DE-GUP-DT-E-23-375 | 2023-03-27 | 3 | CRS-GUP-DHI-DT-23-1820 | 2023-04-12 | RC | DE-GUP-DT-E-23-519 | 2023-04-28 | 4 | CRS-GUP-DHI-DT-23-1947 | 2023-05-11 | RC | DE-GUP-DT-E-23-597 | 2023-06-01 | 5 | CRS-GUP-DHI-DT-23-2009 | 2023-06-15 | NC | DE-GUP-DT-E-23-784 | 2023-08-31 | 6 | 자체 CRS 개정 후 제출 | 2024-01-24 | N/A | DE-GUP-DT-E-24-026 | 2024-01-25 | 7
| GUP | CA01 | P1 | UYC | 181736 |  | GUP-CA01-P1UYC-181736 | ADMINISTRATION BUILDING_ROOF FRAMING PLAN | FI | 2022-09-12 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Admin. Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-026 | 2024-01-25 | 6 | CRS-GUP-DHI-DT-23-2009 | 2023-06-15 | NC | DE-GUP-DT-E-22-1001 | 2022-11-29 | 0 | CRS-GUP-DHI-DT-22-1257 | 2022-12-13 | NC | DE-GUP-DT-E-22-1231 | 2023-01-06 | 1 | CRS-GUP-DHI-DT-22-1448 | 2023-02-02 | NC | DE-GUP-DT-E-23-213 | 2023-02-21 | 2 | CRS-GUP-DHI-DT-23-1671 | 2023-03-10 | RC | DE-GUP-DT-E-23-375 | 2023-03-27 | 3 | CRS-GUP-DHI-DT-23-1820 | 2023-04-12 | NC | DE-GUP-DT-E-23-519 | 2023-04-28 | 4 | CRS-GUP-DHI-DT-23-1947 | 2023-05-11 | RC | DE-GUP-DT-E-23-597 | 2023-06-01 | 5 | CRS-GUP-DHI-DT-23-2009 | 2023-06-15 | NC | DE-GUP-DT-E-24-026 | 2024-01-25 | 6
| GUP | CA01 | P1 | UYC | 181737 |  | GUP-CA01-P1UYC-181737 | ADMINISTRATION BUILDING_LINE FRAMING ELEVATION | FI | 2022-09-12 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Admin. Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-026 | 2024-01-25 | 7 | 자체 CRS 개정 후 제출 | 2024-01-24 | N/A | DE-GUP-DT-E-22-1001 | 2022-11-29 | 0 | CRS-GUP-DHI-DT-22-1257 | 2022-12-13 | NC | DE-GUP-DT-E-22-1231 | 2023-01-06 | 1 | CRS-GUP-DHI-DT-22-1448 | 2023-02-02 | NC | DE-GUP-DT-E-23-213 | 2023-02-21 | 2 | CRS-GUP-DHI-DT-23-1671 | 2023-03-10 | NC | DE-GUP-DT-E-23-375 | 2023-03-27 | 3 | CRS-GUP-DHI-DT-23-1820 | 2023-04-12 | NC | DE-GUP-DT-E-23-519 | 2023-04-28 | 4 | CRS-GUP-DHI-DT-23-1947 | 2023-05-11 | NC | DE-GUP-DT-E-23-597 | 2023-06-01 | 5 | CRS-GUP-DHI-DT-23-2009 | 2023-06-15 | NC | DE-GUP-DT-E-23-784 | 2023-08-31 | 6 | 자체 CRS 개정 후 제출 | 2024-01-24 | N/A | DE-GUP-DT-E-24-026 | 2024-01-25 | 7
| GUP | CA01 | P1 | UYC | 181738 |  | GUP-CA01-P1UYC-181738 | ADMINISTRATION BUILDING_ROW FRAMING ELEVATION | FI | 2022-09-12 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Admin. Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-026 | 2024-01-25 | 7 | 자체 CRS 개정 후 제출 | 2024-01-24 | N/A | DE-GUP-DT-E-22-1001 | 2022-11-29 | 0 | CRS-GUP-DHI-DT-22-1257 | 2022-12-13 | NC | DE-GUP-DT-E-22-1231 | 2023-01-06 | 1 | CRS-GUP-DHI-DT-22-1448 | 2023-02-02 | NC | DE-GUP-DT-E-23-213 | 2023-02-21 | 2 | CRS-GUP-DHI-DT-23-1671 | 2023-03-10 | NC | DE-GUP-DT-E-23-375 | 2023-03-27 | 3 | CRS-GUP-DHI-DT-23-1820 | 2023-04-12 | NC | DE-GUP-DT-E-23-519 | 2023-04-28 | 4 | CRS-GUP-DHI-DT-23-1947 | 2023-05-11 | NC | DE-GUP-DT-E-23-597 | 2023-06-01 | 5 | CRS-GUP-DHI-DT-23-2009 | 2023-06-15 | NC | DE-GUP-DT-E-23-784 | 2023-08-31 | 6 | 자체 CRS 개정 후 제출 | 2024-01-24 | N/A | DE-GUP-DT-E-24-026 | 2024-01-25 | 7
| GUP | CA01 | P1 | UYC | 181739 |  | GUP-CA01-P1UYC-181739 | ADMINISTRATION BUILDING_STAIRCASE FRAMING PLAN & ELEVATION | FI | 2022-09-12 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Admin. Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-026 | 2024-01-25 | 7 | 자체 CRS 개정 후 제출 | 2024-01-24 | N/A | DE-GUP-DT-E-22-1001 | 2022-11-29 | 0 | CRS-GUP-DHI-DT-22-1257 | 2022-12-13 | NC | DE-GUP-DT-E-22-1231 | 2023-01-06 | 1 | CRS-GUP-DHI-DT-22-1448 | 2023-02-02 | NC | DE-GUP-DT-E-23-213 | 2023-02-21 | 2 | CRS-GUP-DHI-DT-23-1671 | 2023-03-10 | NC | DE-GUP-DT-E-23-375 | 2023-03-27 | 3 | CRS-GUP-DHI-DT-23-1820 | 2023-04-12 | NC | DE-GUP-DT-E-23-519 | 2023-04-28 | 4 | CRS-GUP-DHI-DT-23-1947 | 2023-05-11 | NC | DE-GUP-DT-E-23-597 | 2023-06-01 | 5 | CRS-GUP-DHI-DT-23-2009 | 2023-06-15 | NC | DE-GUP-DT-E-23-784 | 2023-08-31 | 6 | 자체 CRS 개정 후 제출 | 2024-01-24 | N/A | DE-GUP-DT-E-24-026 | 2024-01-25 | 7
| GUP | CA01 | P1 | UYC | 181740 |  | GUP-CA01-P1UYC-181740 | ADMINISTRATION BUILDING_STRUCTURAL MISC. DETAIL | FI | 2022-12-01 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | Admin. Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-026 | 2024-01-25 | 6 | 자체 CRS 개정 후 제출 | 2024-01-24 | N/A | DE-GUP-DT-E-22-1231 | 2023-01-06 | 0 | CRS-GUP-DHI-DT-22-1448 | 2023-02-02 | NC | DE-GUP-DT-E-23-213 | 2023-02-21 | 1 | CRS-GUP-DHI-DT-23-1671 | 2023-03-10 | NC | DE-GUP-DT-E-23-375 | 2023-03-27 | 2 | CRS-GUP-DHI-DT-23-1820 | 2023-04-12 | NC | DE-GUP-DT-E-23-519 | 2023-04-28 | 3 | CRS-GUP-DHI-DT-23-1947 | 2023-05-11 | NC | DE-GUP-DT-E-23-597 | 2023-06-01 | 4 | CRS-GUP-DHI-DT-23-2009 | 2023-06-15 | NC | DE-GUP-DT-E-23-784 | 2023-08-31 | 5 | 자체 CRS 개정 후 제출 | 2024-01-24 | N/A | DE-GUP-DT-E-24-026 | 2024-01-25 | 6
| GUP | CA02 | P1 | UYC | 181741 |  | GUP-CA02-P1UYC-181741 | ADMINISTRATION BUILDING_COLUMN RE-BAR SCHEDULE | FI | 2022-09-12 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Admin. Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-597 | 2023-06-01 | 5 | CRS-GUP-DHI-DT-23-2009 | 2023-06-15 | NC | DE-GUP-DT-E-22-1001 | 2022-11-29 | 0 | CRS-GUP-DHI-DT-22-1257 | 2022-12-13 | NC | DE-GUP-DT-E-22-1231 | 2023-01-06 | 1 | CRS-GUP-DHI-DT-22-1448 | 2023-02-02 | NC | DE-GUP-DT-E-23-213 | 2023-02-21 | 2 | CRS-GUP-DHI-DT-23-1671 | 2023-03-10 | RC | DE-GUP-DT-E-23-375 | 2023-03-27 | 3 | CRS-GUP-DHI-DT-23-1820 | 2023-04-12 | NC | DE-GUP-DT-E-23-519 | 2023-04-28 | 4 | CRS-GUP-DHI-DT-23-1947 | 2023-05-11 | NC | DE-GUP-DT-E-23-597 | 2023-06-01 | 5 | CRS-GUP-DHI-DT-23-2009 | 2023-06-15 | NC
| GUP | CA02 | P1 | UYC | 181742 |  | GUP-CA02-P1UYC-181742 | ADMINISTRATION BUILDING_BEAM & GIRDER RE-BAR SCHEDULE | FI | 2022-09-12 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Admin. Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-597 | 2023-06-01 | 5 | CRS-GUP-DHI-DT-23-2009 | 2023-06-15 | NC | DE-GUP-DT-E-22-1001 | 2022-11-29 | 0 | CRS-GUP-DHI-DT-22-1257 | 2022-12-13 | NC | DE-GUP-DT-E-22-1231 | 2023-01-06 | 1 | CRS-GUP-DHI-DT-22-1448 | 2023-02-02 | NC | DE-GUP-DT-E-23-213 | 2023-02-21 | 2 | CRS-GUP-DHI-DT-23-1671 | 2023-03-10 | RC | DE-GUP-DT-E-23-375 | 2023-03-27 | 3 | CRS-GUP-DHI-DT-23-1820 | 2023-04-12 | NC | DE-GUP-DT-E-23-519 | 2023-04-28 | 4 | CRS-GUP-DHI-DT-23-1947 | 2023-05-11 | NC | DE-GUP-DT-E-23-597 | 2023-06-01 | 5 | CRS-GUP-DHI-DT-23-2009 | 2023-06-15 | NC
| GUP | CA02 | P1 | UYC | 181743 |  | GUP-CA02-P1UYC-181743 | ADMINISTRATION BUILDING_SLAB & MISC. RE-BAR SCHEDULE | FI | 2022-12-01 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | Admin. Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-026 | 2024-01-25 | 6 | CRS-GUP-DHI-DT-23-2009 | 2023-06-15 | NC | DE-GUP-DT-E-22-1001 | 2022-11-29 | 0 | CRS-GUP-DHI-DT-22-1257 | 2022-12-13 | NC | DE-GUP-DT-E-22-1231 | 2023-01-06 | 1 | CRS-GUP-DHI-DT-22-1448 | 2023-02-02 | NC | DE-GUP-DT-E-23-213 | 2023-02-21 | 2 | CRS-GUP-DHI-DT-23-1671 | 2023-03-10 | RC | DE-GUP-DT-E-23-375 | 2023-03-27 | 3 | CRS-GUP-DHI-DT-23-1820 | 2023-04-12 | NC | DE-GUP-DT-E-23-519 | 2023-04-28 | 4 | CRS-GUP-DHI-DT-23-1947 | 2023-05-11 | NC | DE-GUP-DT-E-23-597 | 2023-06-01 | 5 | CRS-GUP-DHI-DT-23-2009 | 2023-06-15 | NC | DE-GUP-DT-E-24-026 | 2024-01-25 | 6
| GUP | CA06 | P1 | UYF | 182001 |  | GUP-CA06-P1UYF-182001 | GATE HOUSE_CALCULATION SHEET | FI | 2022-07-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Gate House | Arch. | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-013 | 2024-01-16 | 3 | CRS-GUP-DHI-DT-24-044 | 2024-03-25 | NC | DE-GUP-DT-E-22-459 | 2022-07-27 | 0 | CRS-GUP-DHI-DT-22-623 | 2022-08-17 | RC | DE-GUP-DT-E-22-629 | 2022-09-07 | 1 | CRS-GUP-DHI-DT-22-851 | 2022-09-24 | NC | DE-GUP-DT-E-22-1050 | 2022-12-08 | 2 | CRS-GUP-DHI-DT-22-1360 | 2022-12-31 | NC | DE-GUP-DT-E-24-013 | 2024-01-16 | 3 | CRS-GUP-DHI-DT-24-044 | 2024-03-25 | NC
| GUP | CA01 | P1 | UYF | 182031 |  | GUP-CA01-P1UYF-182031 | GATE HOUSE_FOUNDATION ARRANGEMENT PLAN | FA | 2022-07-30 | 2022-12-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Gate House | Arch. | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-22-1050 | 2022-12-08 | 0 | CRS-GUP-DHI-DT-22-1360 | 2022-12-31 | AA | DE-GUP-DT-E-22-459 | 2022-07-27 | A | CRS-GUP-DHI-DT-22-623 | 2022-08-17 | RC | DE-GUP-DT-E-22-629 | 2022-09-07 | B | CRS-GUP-DHI-DT-22-851 | 2022-09-24 | AA | DE-GUP-DT-E-22-1050 | 2022-12-08 | 0 | CRS-GUP-DHI-DT-22-1360 | 2022-12-31 | AA
| GUP | CA02 | P1 | UYF | 182032 |  | GUP-CA02-P1UYF-182032 | GATE HOUSE_FOUNDATION RE-BAR SCHEDULE | FI | 2022-07-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Gate House | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-013 | 2024-01-16 | 3 | CRS-GUP-DHI-DT-24-044 | 2024-03-25 | NC | DE-GUP-DT-E-22-459 | 2022-07-27 | 0 | CRS-GUP-DHI-DT-22-623 | 2022-08-17 | RC | DE-GUP-DT-E-22-629 | 2022-09-07 | 1 | CRS-GUP-DHI-DT-22-851 | 2022-09-24 | AA | DE-GUP-DT-E-22-1050 | 2022-12-08 | 2 | CRS-GUP-DHI-DT-22-1360 | 2022-12-31 | NC | DE-GUP-DT-E-24-013 | 2024-01-16 | 3 | CRS-GUP-DHI-DT-24-044 | 2024-03-25 | NC
| GUP | CA00 | P1 | UYF | 182011 |  | GUP-CA00-P1UYF-182011 | GATE HOUSE_INTERIOR FINISH, DOOR & WINDOW SCHEDULE | FA | 2022-07-30 | 2022-12-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Gate House | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-013 | 2024-01-16 | 1 | CRS-GUP-DHI-DT-24-044 | 2024-03-25 | AA | DE-GUP-DT-E-22-459 | 2022-07-27 | A | CRS-GUP-DHI-DT-22-623 | 2022-08-17 | RC | DE-GUP-DT-E-22-629 | 2022-09-07 | B | CRS-GUP-DHI-DT-22-851 | 2022-09-24 | AA | DE-GUP-DT-E-22-1050 | 2022-12-08 | 0 | CRS-GUP-DHI-DT-22-1360 | 2022-12-31 | AA | DE-GUP-DT-E-24-013 | 2024-01-16 | 1 | CRS-GUP-DHI-DT-24-044 | 2024-03-25 | AA
| GUP | CA00 | P1 | UYF | 182012 |  | GUP-CA00-P1UYF-182012 | GATE HOUSE_GROUND FLOOR & ROOF PLAN | FA | 2022-07-30 | 2022-12-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Gate House | Arch. | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-013 | 2024-01-16 | 1 | CRS-GUP-DHI-DT-24-044 | 2024-03-25 | AA | DE-GUP-DT-E-22-459 | 2022-07-27 | A | CRS-GUP-DHI-DT-22-623 | 2022-08-17 | RC | DE-GUP-DT-E-22-629 | 2022-09-07 | B | CRS-GUP-DHI-DT-22-851 | 2022-09-24 | AA | DE-GUP-DT-E-22-1050 | 2022-12-08 | 0 | CRS-GUP-DHI-DT-22-1360 | 2022-12-31 | AA | DE-GUP-DT-E-24-013 | 2024-01-16 | 1 | CRS-GUP-DHI-DT-24-044 | 2024-03-25 | AA
| GUP | CA00 | P1 | UYF | 182013 |  | GUP-CA00-P1UYF-182013 | GATE HOUSE_MAIN SECTION | FA | 2022-07-30 | 2022-12-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Gate House | Arch. | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-013 | 2024-01-16 | 1 | CRS-GUP-DHI-DT-24-044 | 2024-03-25 | AA | DE-GUP-DT-E-22-459 | 2022-07-27 | A | CRS-GUP-DHI-DT-22-623 | 2022-08-17 | RC | DE-GUP-DT-E-22-629 | 2022-09-07 | B | CRS-GUP-DHI-DT-22-851 | 2022-09-24 | AA | DE-GUP-DT-E-22-1050 | 2022-12-08 | 0 | CRS-GUP-DHI-DT-22-1360 | 2022-12-31 | AA | DE-GUP-DT-E-24-013 | 2024-01-16 | 1 | CRS-GUP-DHI-DT-24-044 | 2024-03-25 | AA
| GUP | CA00 | P1 | UYF | 182014 |  | GUP-CA00-P1UYF-182014 | GATE HOUSE_SIDE ELEVATION | FA | 2022-07-30 | 2022-12-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Gate House | Arch. | 2 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-013 | 2024-01-16 | 1 | CRS-GUP-DHI-DT-24-044 | 2024-03-25 | AA | DE-GUP-DT-E-22-459 | 2022-07-27 | A | CRS-GUP-DHI-DT-22-623 | 2022-08-17 | RC | DE-GUP-DT-E-22-629 | 2022-09-07 | B | CRS-GUP-DHI-DT-22-851 | 2022-09-24 | AA | DE-GUP-DT-E-22-1050 | 2022-12-08 | 0 | CRS-GUP-DHI-DT-22-1360 | 2022-12-31 | AA | DE-GUP-DT-E-24-013 | 2024-01-16 | 1 | CRS-GUP-DHI-DT-24-044 | 2024-03-25 | AA
| GUP | CA00 | P1 | UYF | 182015 |  | GUP-CA00-P1UYF-182015 | GATE HOUSE_ARCHITECTURAL MISC. DETAIL | FA | 2022-07-30 | 2022-12-01 | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | Gate House | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-013 | 2024-01-16 | 1 | CRS-GUP-DHI-DT-24-044 | 2024-03-25 | AA | DE-GUP-DT-E-22-459 | 2022-07-27 | A | CRS-GUP-DHI-DT-22-623 | 2022-08-17 | RC | DE-GUP-DT-E-22-629 | 2022-09-07 | B | CRS-GUP-DHI-DT-22-851 | 2022-09-24 | AA | DE-GUP-DT-E-22-1050 | 2022-12-08 | 0 | CRS-GUP-DHI-DT-22-1360 | 2022-12-31 | AA | DE-GUP-DT-E-24-013 | 2024-01-16 | 1 | CRS-GUP-DHI-DT-24-044 | 2024-03-25 | AA
| GUP | CA00 | P1 | UYF | 182016 |  | GUP-CA00-P1UYF-182016 | GATE HOUSE_CEILING PLAN | FA | 2022-07-30 | 2022-12-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  |  | Gate House | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-141 | 2024-05-28 | 2 | CRS-GUP-DHI-DT-24-044 | 2024-03-25 | AA | DE-GUP-DT-E-22-459 | 2022-07-27 | A | CRS-GUP-DHI-DT-22-623 | 2022-08-17 | RC | DE-GUP-DT-E-22-629 | 2022-09-07 | B | CRS-GUP-DHI-DT-22-851 | 2022-09-24 | AA | DE-GUP-DT-E-22-1050 | 2022-12-08 | 0 | CRS-GUP-DHI-DT-22-1360 | 2022-12-31 | AA | DE-GUP-DT-E-24-013 | 2024-01-16 | 1 | CRS-GUP-DHI-DT-24-044 | 2024-03-25 | AA | DE-GUP-DT-E-24-141 | 2024-05-28 | 2
| GUP | CA01 | P1 | UYF | 182033 |  | GUP-CA01-P1UYF-182033 | GATE HOUSE_GROUND FLOOR & ROOF FRAMING PLAN | FI | 2022-07-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Gate House | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-013 | 2024-01-16 | 3 | CRS-GUP-DHI-DT-24-044 | 2024-03-25 | NC | DE-GUP-DT-E-22-459 | 2022-07-27 | 0 | CRS-GUP-DHI-DT-22-623 | 2022-08-17 | RC | DE-GUP-DT-E-22-629 | 2022-09-07 | 1 | CRS-GUP-DHI-DT-22-851 | 2022-09-24 | NC | DE-GUP-DT-E-22-1050 | 2022-12-08 | 2 | CRS-GUP-DHI-DT-22-1360 | 2022-12-31 | NC | DE-GUP-DT-E-24-013 | 2024-01-16 | 3 | CRS-GUP-DHI-DT-24-044 | 2024-03-25 | NC
| GUP | CA01 | P1 | UYF | 182034 |  | GUP-CA01-P1UYF-182034 | GATE HOUSE_LINE FRAMING ELEVATION | FI | 2022-07-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Gate House | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-013 | 2024-01-16 | 3 | CRS-GUP-DHI-DT-24-044 | 2024-03-25 | NC | DE-GUP-DT-E-22-459 | 2022-07-27 | 0 | CRS-GUP-DHI-DT-22-623 | 2022-08-17 | RC | DE-GUP-DT-E-22-629 | 2022-09-07 | 1 | CRS-GUP-DHI-DT-22-851 | 2022-09-24 | NC | DE-GUP-DT-E-22-1050 | 2022-12-08 | 2 | CRS-GUP-DHI-DT-22-1360 | 2022-12-31 | NC | DE-GUP-DT-E-24-013 | 2024-01-16 | 3 | CRS-GUP-DHI-DT-24-044 | 2024-03-25 | NC
| GUP | CA02 | P1 | UYF | 182035 |  | GUP-CA02-P1UYF-182035 | GATE HOUSE_BEAM & GIRDER RE-BAR SCHEDULE | FI | 2022-07-30 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Gate House | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-013 | 2024-01-16 | 3 | CRS-GUP-DHI-DT-24-044 | 2024-03-25 | NC | DE-GUP-DT-E-22-459 | 2022-07-27 | 0 | CRS-GUP-DHI-DT-22-623 | 2022-08-17 | RC | DE-GUP-DT-E-22-629 | 2022-09-07 | 1 | CRS-GUP-DHI-DT-22-851 | 2022-09-24 | NC | DE-GUP-DT-E-22-1050 | 2022-12-08 | 2 | CRS-GUP-DHI-DT-22-1360 | 2022-12-31 | NC | DE-GUP-DT-E-24-013 | 2024-01-16 | 3 | CRS-GUP-DHI-DT-24-044 | 2024-03-25 | NC
| GUP | CA02 | P1 | UYF | 182036 |  | GUP-CA02-P1UYF-182036 | GATE HOUSE_SLAB & MISC. RE-BAR SCHEDULE | FI | 2022-07-30 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | Gate House | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-013 | 2024-01-16 | 3 | CRS-GUP-DHI-DT-24-044 | 2024-03-25 | NC | DE-GUP-DT-E-22-459 | 2022-07-27 | 0 | CRS-GUP-DHI-DT-22-623 | 2022-08-17 | RC | DE-GUP-DT-E-22-629 | 2022-09-07 | 1 | CRS-GUP-DHI-DT-22-851 | 2022-09-24 | NC | DE-GUP-DT-E-22-1050 | 2022-12-08 | 2 | CRS-GUP-DHI-DT-22-1360 | 2022-12-31 | NC | DE-GUP-DT-E-24-013 | 2024-01-16 | 3 | CRS-GUP-DHI-DT-24-044 | 2024-03-25 | NC
| GUP | CA06 | P1 | UMY | 184101 |  | GUP-CA06-P1UMY-184101 | PIPE RACK #1_CALCULATION SHEET | FA | 2022-06-12 | 2022-10-11 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Pipe Rack #1 | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-771 | 2023-08-29 | 2 | CRS-GUP-DHI-DT-23-2112 | 2023-09-26 | AA | DHI-GUP-DT-21-038 | 2021-09-29 | A | CRS-GUP-DHI-DT-21-031 | 2021-10-06 | RR | DHI-GUP-DT-22-043 | 2022-01-27 | B | CRS-GUP-DHI-DT-21-200 | 2022-02-13 | RC | DHI-GUP-DT-22-153 | 2022-04-07 | C | CRS-GUP-DHI-DT-22-305 | 2022-04-17 | RC | DE-GUP-DT-E-22-294 | 2022-06-14 | D | CRS-GUP-DHI-DT-22-466 | 2022-06-21 | RC | DE-GUP-DT-E-22-350 | 2022-06-30 | E | CRS-GUP-DHI-DT-22-519 | 2022-07-15 | RC | DE-GUP-DT-E-22-476 | 2022-07-29 | F | CRS-GUP-DHI-DT-22-653 | 2022-08-20 | AC | DE-GUP-DT-E-22-909 | 2022-11-04 | 0(CP) | CRS-GUP-DHI-DT-22-1044 | 2022-11-16 | AA | DE-GUP-DT-E-23-704 | 2023-07-20 | 1 | CRS-GUP-DHI-DT-23-2081 | 2023-08-02 | AA | DE-GUP-DT-E-23-771 | 2023-08-29 | 2 | CRS-GUP-DHI-DT-23-2112 | 2023-09-26 | AA
| GUP | CA01 | P1 | UMY | 184131 |  | GUP-CA01-P1UMY-184131 | PIPE RACK #1_FOUNDATION ARRANGEMENT PLAN | FA | 2022-06-12 | 2022-08-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Pipe Rack #1 | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-704 | 2023-07-20 | 1 | CRS-GUP-DHI-DT-23-2081 | 2023-08-02 | AA | DHI-GUP-DT-21-038 | 2021-09-29 | A | CRS-GUP-DHI-DT-21-031 | 2021-10-06 | RR | DHI-GUP-DT-22-043 | 2022-01-27 | B | CRS-GUP-DHI-DT-21-200 | 2022-02-13 | RC | DHI-GUP-DT-22-153 | 2022-04-07 | C | CRS-GUP-DHI-DT-22-305 | 2022-04-17 | RC | DE-GUP-DT-E-22-294 | 2022-06-14 | D | CRS-GUP-DHI-DT-22-466 | 2022-06-21 | RC | DE-GUP-DT-E-22-350 | 2022-06-30 | E | CRS-GUP-DHI-DT-22-519 | 2022-07-15 | RC | DE-GUP-DT-E-22-476 | 2022-07-29 | F | CRS-GUP-DHI-DT-22-653 | 2022-08-20 | AC | DE-GUP-DT-E-22-909 | 2022-11-04 | 0(CP) | CRS-GUP-DHI-DT-22-1044 | 2022-11-16 | AC | DE-GUP-DT-E-23-704 | 2023-07-20 | 1 | CRS-GUP-DHI-DT-23-2081 | 2023-08-02 | AA
| GUP | CA02 | P1 | UMY | 184132 |  | GUP-CA02-P1UMY-184132 | PIPE RACK #1_FOUNDATION RE-BAR SCHEDULE | FI | 2022-06-12 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Pipe Rack #1 | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-704 | 2023-07-20 | 7 | CRS-GUP-DHI-DT-23-2081 | 2023-08-02 | NC | DHI-GUP-DT-21-038 | 2021-09-29 | 0 | CRS-GUP-DHI-DT-21-031 | 2021-10-06 | RC | DHI-GUP-DT-22-043 | 2022-01-27 | 1 | CRS-GUP-DHI-DT-21-200 | 2022-02-13 | RC | DHI-GUP-DT-22-153 | 2022-04-07 | 2 | CRS-GUP-DHI-DT-22-305 | 2022-04-17 | RC | DE-GUP-DT-E-22-294 | 2022-06-14 | 3 | CRS-GUP-DHI-DT-22-466 | 2022-06-21 | RC | DE-GUP-DT-E-22-350 | 2022-06-30 | 4 | CRS-GUP-DHI-DT-22-519 | 2022-07-15 | RC | DE-GUP-DT-E-22-476 | 2022-07-29 | 5 | CRS-GUP-DHI-DT-22-653 | 2022-08-20 | RC | DE-GUP-DT-E-22-909 | 2022-11-04 | 6 | CRS-GUP-DHI-DT-22-1044 | 2022-11-16 | RC | DE-GUP-DT-E-23-704 | 2023-07-20 | 7 | CRS-GUP-DHI-DT-23-2081 | 2023-08-02 | NC
| GUP | CA03 | P1 | UMY | 184151 |  | GUP-CA03-P1UMY-184151 | PIPE RACK #1_COLUMN ARRANGEMENT PLAN | FA | 2022-06-12 | 2022-09-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Pipe Rack #1 | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-704 | 2023-07-20 | 1 | CRS-GUP-DHI-DT-23-2081 | 2023-08-02 | AA | DHI-GUP-DT-21-038 | 2021-09-29 | A | CRS-GUP-DHI-DT-21-031 | 2021-10-06 | RR | DHI-GUP-DT-22-043 | 2022-01-27 | B | CRS-GUP-DHI-DT-21-200 | 2022-02-13 | RC | DHI-GUP-DT-22-153 | 2022-04-07 | C | CRS-GUP-DHI-DT-22-305 | 2022-04-17 | RC | DE-GUP-DT-E-22-294 | 2022-06-14 | D | CRS-GUP-DHI-DT-22-466 | 2022-06-21 | RC | DE-GUP-DT-E-22-350 | 2022-06-30 | E | CRS-GUP-DHI-DT-22-519 | 2022-07-15 | RC | DE-GUP-DT-E-22-476 | 2022-07-29 | F | CRS-GUP-DHI-DT-22-653 | 2022-08-20 | AC | DE-GUP-DT-E-22-909 | 2022-11-04 | 0(CP) | CRS-GUP-DHI-DT-22-1044 | 2022-11-16 | AA | DE-GUP-DT-E-23-704 | 2023-07-20 | 1 | CRS-GUP-DHI-DT-23-2081 | 2023-08-02 | AA
| GUP | CA03 | P1 | UMY | 184152 |  | GUP-CA03-P1UMY-184152 | PIPE RACK #1_FRAMING PLAN | FA | 2022-06-12 | 2022-09-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Pipe Rack #1 | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-704 | 2023-07-20 | 1 | CRS-GUP-DHI-DT-23-2081 | 2023-08-02 | AA | DHI-GUP-DT-21-038 | 2021-09-29 | A | CRS-GUP-DHI-DT-21-031 | 2021-10-06 | RR | DHI-GUP-DT-22-043 | 2022-01-27 | B | CRS-GUP-DHI-DT-21-200 | 2022-02-13 | RC | DHI-GUP-DT-22-153 | 2022-04-07 | C | CRS-GUP-DHI-DT-22-305 | 2022-04-17 | RC | DE-GUP-DT-E-22-294 | 2022-06-14 | D | CRS-GUP-DHI-DT-22-466 | 2022-06-21 | RC | DE-GUP-DT-E-22-350 | 2022-06-30 | E | CRS-GUP-DHI-DT-22-519 | 2022-07-15 | RC | DE-GUP-DT-E-22-476 | 2022-07-29 | F | CRS-GUP-DHI-DT-22-653 | 2022-08-20 | AC | DE-GUP-DT-E-22-909 | 2022-11-04 | 0(CP) | CRS-GUP-DHI-DT-22-1044 | 2022-11-16 | AC | DE-GUP-DT-E-23-704 | 2023-07-20 | 1 | CRS-GUP-DHI-DT-23-2081 | 2023-08-02 | AA
| GUP | CA03 | P1 | UMY | 184155 |  | GUP-CA03-P1UMY-184155 | PIPE RACK #1_LINE FRAMING ELEVATION | FI | 2022-06-12 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Pipe Rack #1 | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-771 | 2023-08-29 | 8 | CRS-GUP-DHI-DT-23-2112 | 2023-09-26 | NC | DHI-GUP-DT-21-038 | 2021-09-29 | 0 | CRS-GUP-DHI-DT-21-031 | 2021-10-06 | RC | DHI-GUP-DT-22-043 | 2022-01-27 | 1 | CRS-GUP-DHI-DT-21-200 | 2022-02-13 | RC | DHI-GUP-DT-22-153 | 2022-04-07 | 2 | CRS-GUP-DHI-DT-22-305 | 2022-04-17 | RC | DE-GUP-DT-E-22-294 | 2022-06-14 | 3 | CRS-GUP-DHI-DT-22-466 | 2022-06-21 | RC | DE-GUP-DT-E-22-350 | 2022-06-30 | 4 | CRS-GUP-DHI-DT-22-519 | 2022-07-15 | RC | DE-GUP-DT-E-22-476 | 2022-07-29 | 5 | CRS-GUP-DHI-DT-22-653 | 2022-08-20 | RC | DE-GUP-DT-E-22-909 | 2022-11-04 | 6 | CRS-GUP-DHI-DT-22-1044 | 2022-11-16 | NC | DE-GUP-DT-E-23-704 | 2023-07-20 | 7 | CRS-GUP-DHI-DT-23-2081 | 2023-08-02 | NC | DE-GUP-DT-E-23-771 | 2023-08-29 | 8 | CRS-GUP-DHI-DT-23-2112 | 2023-09-26 | NC
| GUP | CA03 | P1 | UMY | 184156 |  | GUP-CA03-P1UMY-184156 | PIPE RACK #1_ROW FRAMING ELEVATION | FI | 2022-06-12 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Pipe Rack #1 | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-704 | 2023-07-20 | 7 | CRS-GUP-DHI-DT-23-2081 | 2023-08-02 | NC | DHI-GUP-DT-21-038 | 2021-09-29 | 0 | CRS-GUP-DHI-DT-21-031 | 2021-10-06 | RC | DHI-GUP-DT-22-043 | 2022-01-27 | 1 | CRS-GUP-DHI-DT-21-200 | 2022-02-13 | RC | DHI-GUP-DT-22-153 | 2022-04-07 | 2 | CRS-GUP-DHI-DT-22-305 | 2022-04-17 | RC | DE-GUP-DT-E-22-294 | 2022-06-14 | 3 | CRS-GUP-DHI-DT-22-466 | 2022-06-21 | RC | DE-GUP-DT-E-22-350 | 2022-06-30 | 4 | CRS-GUP-DHI-DT-22-519 | 2022-07-15 | RC | DE-GUP-DT-E-22-476 | 2022-07-29 | 5 | CRS-GUP-DHI-DT-22-653 | 2022-08-20 | RC | DE-GUP-DT-E-22-909 | 2022-11-04 | 6 | CRS-GUP-DHI-DT-22-1044 | 2022-11-16 | NC | DE-GUP-DT-E-23-704 | 2023-07-20 | 7 | CRS-GUP-DHI-DT-23-2081 | 2023-08-02 | NC
| GUP | CA03 | P1 | UMY | 184157 |  | GUP-CA03-P1UMY-184157 | PIPE RACK #1_CONNECTION DETAIL | FI | 2022-06-12 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Pipe Rack #1 | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-909 | 2022-11-04 | 4 | CRS-GUP-DHI-DT-22-1044 | 2022-11-16 | NC | DHI-GUP-DT-21-038 | 2021-09-29 | 0 | CRS-GUP-DHI-DT-21-031 | 2021-10-06 | RC | DHI-GUP-DT-22-043 | 2022-01-27 | 1 | CRS-GUP-DHI-DT-21-200 | 2022-02-13 | RC | DHI-GUP-DT-22-153 | 2022-04-07 | 2 | CRS-GUP-DHI-DT-22-305 | 2022-04-17 | RC | DE-GUP-DT-E-22-294 | 2022-06-14 | 3 | CRS-GUP-DHI-DT-22-466 | 2022-06-21 | RC | DE-GUP-DT-E-22-909 | 2022-11-04 | 4 | CRS-GUP-DHI-DT-22-1044 | 2022-11-16 | NC
| GUP | CA06 | P1 | UMY | 184201 |  | GUP-CA06-P1UMY-184201 | PIPE RACK #2_CALCULATION SHEET | FA | 2022-06-12 | 2022-10-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Pipe Rack #2 | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-853 | 2023-10-13 | 1 | CRS-GUP-DHI-DT-22-1339 | 2022-12-28 | AA | DHI-GUP-DT-21-039 | 2021-09-29 | A | CRS-GUP-DHI-DT-21-032 | 2021-10-06 | RR | DHI-GUP-DT-22-044 | 2022-01-28 | B | CRS-GUP-DHI-DT-21-201 | 2022-02-13 | RC | DHI-GUP-DT-22-154 | 2022-04-07 | C | CRS-GUP-DHI-DT-22-306 | 2022-04-17 | RC | DE-GUP-DT-E-22-295 | 2022-06-14 | D | CRS-GUP-DHI-DT-22-494 | 2022-07-06 | RC | DE-GUP-DT-E-22-483 | 2022-07-29 | E | CRS-GUP-DHI-DT-22-691 | 2022-08-23 | RC | DE-GUP-DT-E-22-791 | 2022-10-12 | F | CRS-GUP-DHI-DT-22-956 | 2022-10-22 | AC | DE-GUP-DT-E-22-1095 | 2022-12-16 | 0(CP) | CRS-GUP-DHI-DT-22-1339 | 2022-12-28 | AA | DE-GUP-DT-E-23-853 | 2023-10-13 | 1
| GUP | CA01 | P1 | UMY | 184231 |  | GUP-CA01-P1UMY-184231 | PIPE RACK #2_FOUNDATION ARRANGEMENT PLAN | FA | 2022-06-12 | 2022-10-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Pipe Rack #2 | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-853 | 2023-10-13 | 1 | CRS-GUP-DHI-DT-22-1339 | 2022-12-28 | AA | DHI-GUP-DT-21-039 | 2021-09-29 | A | CRS-GUP-DHI-DT-21-032 | 2021-10-06 | RR | DHI-GUP-DT-22-044 | 2022-01-28 | B | CRS-GUP-DHI-DT-21-201 | 2022-02-13 | RC | DHI-GUP-DT-22-154 | 2022-04-07 | C | CRS-GUP-DHI-DT-22-306 | 2022-04-17 | RC | DE-GUP-DT-E-22-295 | 2022-06-14 | D | CRS-GUP-DHI-DT-22-494 | 2022-07-06 | RC | DE-GUP-DT-E-22-483 | 2022-07-29 | E | CRS-GUP-DHI-DT-22-691 | 2022-08-23 | AC | DE-GUP-DT-E-22-791 | 2022-10-12 | F | CRS-GUP-DHI-DT-22-956 | 2022-10-22 | AC | DE-GUP-DT-E-22-1095 | 2022-12-16 | 0(CP) | CRS-GUP-DHI-DT-22-1339 | 2022-12-28 | AA | DE-GUP-DT-E-23-853 | 2023-10-13 | 1
| GUP | CA02 | P1 | UMY | 184232 |  | GUP-CA02-P1UMY-184232 | PIPE RACK #2_FOUNDATION RE-BAR SCHEDULE | FI | 2022-06-12 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Pipe Rack #2 | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-853 | 2023-10-13 | 7 | CRS-GUP-DHI-DT-22-1339 | 2022-12-28 | NC | DHI-GUP-DT-21-039 | 2021-09-29 | 0 | CRS-GUP-DHI-DT-21-032 | 2021-10-06 | RC | DHI-GUP-DT-22-044 | 2022-01-28 | 1 | CRS-GUP-DHI-DT-21-201 | 2022-02-13 | RC | DHI-GUP-DT-22-154 | 2022-04-07 | 2 | CRS-GUP-DHI-DT-22-306 | 2022-04-17 | RC | DE-GUP-DT-E-22-295 | 2022-06-14 | 3 | CRS-GUP-DHI-DT-22-494 | 2022-07-06 | RC | DE-GUP-DT-E-22-483 | 2022-07-29 | 4 | CRS-GUP-DHI-DT-22-691 | 2022-08-23 | NC | DE-GUP-DT-E-22-791 | 2022-10-12 | 5 | CRS-GUP-DHI-DT-22-956 | 2022-10-22 | NC | DE-GUP-DT-E-22-1095 | 2022-12-16 | 6 | CRS-GUP-DHI-DT-22-1339 | 2022-12-28 | NC | DE-GUP-DT-E-23-853 | 2023-10-13 | 7
| GUP | CA03 | P1 | UMY | 184251 |  | GUP-CA03-P1UMY-184251 | PIPE RACK #2_COLUMN ARRANGEMENT PLAN | FA | 2022-06-12 | 2022-10-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Pipe Rack #2 | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-853 | 2023-10-13 | 1 | CRS-GUP-DHI-DT-22-1339 | 2022-12-28 | AA | DHI-GUP-DT-21-039 | 2021-09-29 | A | CRS-GUP-DHI-DT-21-032 | 2021-10-06 | RR | DHI-GUP-DT-22-044 | 2022-01-28 | B | CRS-GUP-DHI-DT-21-201 | 2022-02-13 | RC | DHI-GUP-DT-22-154 | 2022-04-07 | C | CRS-GUP-DHI-DT-22-306 | 2022-04-17 | RC | DE-GUP-DT-E-22-295 | 2022-06-14 | D | CRS-GUP-DHI-DT-22-494 | 2022-07-06 | RC | DE-GUP-DT-E-22-483 | 2022-07-29 | E | CRS-GUP-DHI-DT-22-691 | 2022-08-23 | AC | DE-GUP-DT-E-22-791 | 2022-10-12 | F | CRS-GUP-DHI-DT-22-956 | 2022-10-22 | AC | DE-GUP-DT-E-22-1095 | 2022-12-16 | 0(CP) | CRS-GUP-DHI-DT-22-1339 | 2022-12-28 | AA | DE-GUP-DT-E-23-853 | 2023-10-13 | 1
| GUP | CA03 | P1 | UMY | 184252 |  | GUP-CA03-P1UMY-184252 | PIPE RACK #2_FRAMING PLAN | FA | 2022-06-12 | 2022-10-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Pipe Rack #2 | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-853 | 2023-10-13 | 1 | CRS-GUP-DHI-DT-22-1339 | 2022-12-28 | AA | DHI-GUP-DT-21-039 | 2021-09-29 | A | CRS-GUP-DHI-DT-21-032 | 2021-10-06 | RR | DHI-GUP-DT-22-044 | 2022-01-28 | B | CRS-GUP-DHI-DT-21-201 | 2022-02-13 | RC | DHI-GUP-DT-22-154 | 2022-04-07 | C | CRS-GUP-DHI-DT-22-306 | 2022-04-17 | RC | DE-GUP-DT-E-22-295 | 2022-06-14 | D | CRS-GUP-DHI-DT-22-494 | 2022-07-06 | RC | DE-GUP-DT-E-22-483 | 2022-07-29 | E | CRS-GUP-DHI-DT-22-691 | 2022-08-23 | AC | DE-GUP-DT-E-22-791 | 2022-10-12 | F | CRS-GUP-DHI-DT-22-956 | 2022-10-22 | AC | DE-GUP-DT-E-22-1095 | 2022-12-16 | 0(CP) | CRS-GUP-DHI-DT-22-1339 | 2022-12-28 | AA | DE-GUP-DT-E-23-853 | 2023-10-13 | 1
| GUP | CA03 | P1 | UMY | 184255 |  | GUP-CA03-P1UMY-184255 | PIPE RACK #2_LINE FRAMING ELEVATION | FI | 2022-06-12 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Pipe Rack #2 | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-853 | 2023-10-13 | 7 | CRS-GUP-DHI-DT-22-1339 | 2022-12-28 | NC | DHI-GUP-DT-21-039 | 2021-09-29 | 0 | CRS-GUP-DHI-DT-21-032 | 2021-10-06 | RC | DHI-GUP-DT-22-044 | 2022-01-28 | 1 | CRS-GUP-DHI-DT-21-201 | 2022-02-13 | RC | DHI-GUP-DT-22-154 | 2022-04-07 | 2 | CRS-GUP-DHI-DT-22-306 | 2022-04-17 | RC | DE-GUP-DT-E-22-295 | 2022-06-14 | 3 | CRS-GUP-DHI-DT-22-494 | 2022-07-06 | RC | DE-GUP-DT-E-22-483 | 2022-07-29 | 4 | CRS-GUP-DHI-DT-22-691 | 2022-08-23 | NC | DE-GUP-DT-E-22-791 | 2022-10-12 | 5 | CRS-GUP-DHI-DT-22-956 | 2022-10-22 | NC | DE-GUP-DT-E-22-1095 | 2022-12-16 | 6 | CRS-GUP-DHI-DT-22-1339 | 2022-12-28 | NC | DE-GUP-DT-E-23-853 | 2023-10-13 | 7
| GUP | CA03 | P1 | UMY | 184256 |  | GUP-CA03-P1UMY-184256 | PIPE RACK #2_ROW FRAMING ELEVATION | FI | 2022-06-12 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Pipe Rack #2 | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-853 | 2023-10-13 | 7 | CRS-GUP-DHI-DT-22-1339 | 2022-12-28 | NC | DHI-GUP-DT-21-039 | 2021-09-29 | 0 | CRS-GUP-DHI-DT-21-032 | 2021-10-06 | RC | DHI-GUP-DT-22-044 | 2022-01-28 | 1 | CRS-GUP-DHI-DT-21-201 | 2022-02-13 | RC | DHI-GUP-DT-22-154 | 2022-04-07 | 2 | CRS-GUP-DHI-DT-22-306 | 2022-04-17 | RC | DE-GUP-DT-E-22-295 | 2022-06-14 | 3 | CRS-GUP-DHI-DT-22-494 | 2022-07-06 | RC | DE-GUP-DT-E-22-483 | 2022-07-29 | 4 | CRS-GUP-DHI-DT-22-691 | 2022-08-23 | NC | DE-GUP-DT-E-22-791 | 2022-10-12 | 5 | CRS-GUP-DHI-DT-22-956 | 2022-10-22 | NC | DE-GUP-DT-E-22-1095 | 2022-12-16 | 6 | CRS-GUP-DHI-DT-22-1339 | 2022-12-28 | NC | DE-GUP-DT-E-23-853 | 2023-10-13 | 7
| GUP | CA06 | P1 | UMY | 184301 |  | GUP-CA06-P1UMY-184301 | PIPE RACK #3_CALCULATION SHEET | FA | 2022-06-12 | 2022-10-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Pipe Rack #3 | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-012 | 2024-01-16 | 1 | CRS-GUP-DHI-DT-22-1340 | 2022-12-28 | AA | DHI-GUP-DT-21-040 | 2021-09-29 | A | CRS-GUP-DHI-DT-21-036 | 2021-10-06 | RR | DE-GUP-DT-E-22-508 | 2022-08-17 | B | CRS-GUP-DHI-DT-22-695 | 2022-08-29 | RC | DE-GUP-DT-E-22-906 | 2022-11-03 | C | CRS-GUP-DHI-DT-22-1043 | 2022-11-16 | AC | DE-GUP-DT-E-22-1096 | 2022-12-16 | 0(CP) | CRS-GUP-DHI-DT-22-1340 | 2022-12-28 | AA | DE-GUP-DT-E-24-012 | 2024-01-16 | 1
| GUP | CA01 | P1 | UMY | 184331 |  | GUP-CA01-P1UMY-184331 | PIPE RACK #3_FOUNDATION ARRANGEMENT PLAN | FA | 2022-06-12 | 2022-10-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Pipe Rack #3 | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-012 | 2024-01-16 | 1 | CRS-GUP-DHI-DT-22-1340 | 2022-12-28 | AA | DHI-GUP-DT-21-040 | 2021-09-29 | A | CRS-GUP-DHI-DT-21-036 | 2021-10-06 | RR | DE-GUP-DT-E-22-508 | 2022-08-17 | B | CRS-GUP-DHI-DT-22-695 | 2022-08-29 | RC | DE-GUP-DT-E-22-906 | 2022-11-03 | C | CRS-GUP-DHI-DT-22-1043 | 2022-11-16 | AC | DE-GUP-DT-E-22-1096 | 2022-12-16 | 0(CP) | CRS-GUP-DHI-DT-22-1340 | 2022-12-28 | AA | DE-GUP-DT-E-24-012 | 2024-01-16 | 1
| GUP | CA02 | P1 | UMY | 184332 |  | GUP-CA02-P1UMY-184332 | PIPE RACK #3_FOUNDATION RE-BAR SCHEDULE | FI | 2022-06-12 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Pipe Rack #3 | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-22-1096 | 2022-12-16 | 3 | CRS-GUP-DHI-DT-22-1340 | 2022-12-28 | NC | DHI-GUP-DT-21-040 | 2021-09-29 | 0 | CRS-GUP-DHI-DT-21-036 | 2021-10-06 | RC | DE-GUP-DT-E-22-508 | 2022-08-17 | 1 | CRS-GUP-DHI-DT-22-695 | 2022-08-29 | RC | DE-GUP-DT-E-22-906 | 2022-11-03 | 2 | CRS-GUP-DHI-DT-22-1043 | 2022-11-16 | RC | DE-GUP-DT-E-22-1096 | 2022-12-16 | 3 | CRS-GUP-DHI-DT-22-1340 | 2022-12-28 | NC
| GUP | CA03 | P1 | UMY | 184351 |  | GUP-CA03-P1UMY-184351 | PIPE RACK #3_COLUMN ARRANGEMENT PLAN | FA | 2022-06-12 | 2022-10-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Pipe Rack #3 | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-012 | 2024-01-16 | 1 | CRS-GUP-DHI-DT-22-1340 | 2022-12-28 | AA | DHI-GUP-DT-21-040 | 2021-09-29 | A | CRS-GUP-DHI-DT-21-036 | 2021-10-06 | RR | DE-GUP-DT-E-22-508 | 2022-08-17 | B | CRS-GUP-DHI-DT-22-695 | 2022-08-29 | RC | DE-GUP-DT-E-22-906 | 2022-11-03 | C | CRS-GUP-DHI-DT-22-1043 | 2022-11-16 | AC | DE-GUP-DT-E-22-1096 | 2022-12-16 | 0(CP) | CRS-GUP-DHI-DT-22-1340 | 2022-12-28 | AA | DE-GUP-DT-E-24-012 | 2024-01-16 | 1
| GUP | CA03 | P1 | UMY | 184352 |  | GUP-CA03-P1UMY-184352 | PIPE RACK #3_FRAMING PLAN | FA | 2022-06-12 | 2022-10-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Pipe Rack #3 | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-012 | 2024-01-16 | 1 | CRS-GUP-DHI-DT-22-1340 | 2022-12-28 | AA | DHI-GUP-DT-21-040 | 2021-09-29 | A | CRS-GUP-DHI-DT-21-036 | 2021-10-06 | RR | DE-GUP-DT-E-22-508 | 2022-08-17 | B | CRS-GUP-DHI-DT-22-695 | 2022-08-29 | RC | DE-GUP-DT-E-22-906 | 2022-11-03 | C | CRS-GUP-DHI-DT-22-1043 | 2022-11-16 | AC | DE-GUP-DT-E-22-1096 | 2022-12-16 | 0(CP) | CRS-GUP-DHI-DT-22-1340 | 2022-12-28 | AA | DE-GUP-DT-E-24-012 | 2024-01-16 | 1
| GUP | CA03 | P1 | UMY | 184355 |  | GUP-CA03-P1UMY-184355 | PIPE RACK #3_LINE FRAMING ELEVATION | FI | 2022-06-12 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Pipe Rack #3 | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-012 | 2024-01-16 | 4 | CRS-GUP-DHI-DT-22-1340 | 2022-12-28 | NC | DHI-GUP-DT-21-040 | 2021-09-29 | 0 | CRS-GUP-DHI-DT-21-036 | 2021-10-06 | RC | DE-GUP-DT-E-22-508 | 2022-08-17 | 1 | CRS-GUP-DHI-DT-22-695 | 2022-08-29 | RC | DE-GUP-DT-E-22-906 | 2022-11-03 | 2 | CRS-GUP-DHI-DT-22-1043 | 2022-11-16 | RC | DE-GUP-DT-E-22-1096 | 2022-12-16 | 3 | CRS-GUP-DHI-DT-22-1340 | 2022-12-28 | NC | DE-GUP-DT-E-24-012 | 2024-01-16 | 4
| GUP | CA03 | P1 | UMY | 184356 |  | GUP-CA03-P1UMY-184356 | PIPE RACK #3_ROW FRAMING ELEVATION | FI | 2022-06-12 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Pipe Rack #3 | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-012 | 2024-01-16 | 4 | CRS-GUP-DHI-DT-22-1340 | 2022-12-28 | NC | DHI-GUP-DT-21-040 | 2021-09-29 | 0 | CRS-GUP-DHI-DT-21-036 | 2021-10-06 | RC | DE-GUP-DT-E-22-508 | 2022-08-17 | 1 | CRS-GUP-DHI-DT-22-695 | 2022-08-29 | RC | DE-GUP-DT-E-22-906 | 2022-11-03 | 2 | CRS-GUP-DHI-DT-22-1043 | 2022-11-16 | RC | DE-GUP-DT-E-22-1096 | 2022-12-16 | 3 | CRS-GUP-DHI-DT-22-1340 | 2022-12-28 | NC | DE-GUP-DT-E-24-012 | 2024-01-16 | 4
| GUP | CA06 | P1 | UMY | 184401 |  | GUP-CA06-P1UMY-184401 | PIPE RACK #4_CALCULATION SHEET | FA | 2022-12-05 | 2023-04-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Pipe Rack #4 | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-580 | 2023-05-25 | 1 | CRS-GUP-DHI-DT-23-1759 | 2023-03-22 | AA | DE-GUP-DT-E-23-066 | 2023-01-20 | A | CRS-GUP-DHI-DT-23-1495 | 2023-02-11 | RC | DE-GUP-DT-E-23-231 | 2023-02-23 | B | CRS-GUP-DHI-DT-23-1703 | 2023-03-06 | AA | DE-GUP-DT-E-23-278 | 2023-03-08 | 0 | CRS-GUP-DHI-DT-23-1759 | 2023-03-22 | AA | DE-GUP-DT-E-23-580 | 2023-05-25 | 1
| GUP | CA01 | P1 | UMY | 184431 |  | GUP-CA01-P1UMY-184431 | PIPE RACK #4_FOUNDATION ARRANGEMENT PLAN | FA | 2022-12-05 | 2023-04-01 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Pipe Rack #4 | Arch. | 2 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-580 | 2023-05-25 | 1 | CRS-GUP-DHI-DT-23-1759 | 2023-03-22 | AA | DE-GUP-DT-E-23-066 | 2023-01-20 | A | CRS-GUP-DHI-DT-23-1495 | 2023-02-11 | RC | DE-GUP-DT-E-23-231 | 2023-02-23 | B | CRS-GUP-DHI-DT-23-1703 | 2023-03-06 | AA | DE-GUP-DT-E-23-278 | 2023-03-08 | 0 | CRS-GUP-DHI-DT-23-1759 | 2023-03-22 | AA | DE-GUP-DT-E-23-580 | 2023-05-25 | 1
| GUP | CA02 | P1 | UMY | 184432 |  | GUP-CA02-P1UMY-184432 | PIPE RACK #4_FOUNDATION RE-BAR SCHEDULE | FI | 2022-12-05 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Pipe Rack #4 | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-580 | 2023-05-25 | 3 | CRS-GUP-DHI-DT-23-1759 | 2023-03-22 | NC | DE-GUP-DT-E-23-066 | 2023-01-20 | 0 | CRS-GUP-DHI-DT-23-1495 | 2023-02-11 | NC | DE-GUP-DT-E-23-231 | 2023-02-23 | 1 | CRS-GUP-DHI-DT-23-1703 | 2023-03-06 | NC | DE-GUP-DT-E-23-278 | 2023-03-08 | 2 | CRS-GUP-DHI-DT-23-1759 | 2023-03-22 | NC | DE-GUP-DT-E-23-580 | 2023-05-25 | 3
| GUP | CA03 | P1 | UMY | 184451 |  | GUP-CA03-P1UMY-184451 | PIPE RACK #4_COLUMN ARRANGEMENT PLAN | FI | 2022-12-05 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Pipe Rack #4 | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-580 | 2023-05-25 | 3 | CRS-GUP-DHI-DT-23-1759 | 2023-03-22 | NC | DE-GUP-DT-E-23-066 | 2023-01-20 | A | CRS-GUP-DHI-DT-23-1495 | 2023-02-11 | RC | DE-GUP-DT-E-23-231 | 2023-02-23 | 1 | CRS-GUP-DHI-DT-23-1703 | 2023-03-06 | NC | DE-GUP-DT-E-23-278 | 2023-03-08 | 2 | CRS-GUP-DHI-DT-23-1759 | 2023-03-22 | NC | DE-GUP-DT-E-23-580 | 2023-05-25 | 3
| GUP | CA03 | P1 | UMY | 184452 |  | GUP-CA03-P1UMY-184452 | PIPE RACK #4_FRAMING PLAN | FI | 2022-12-05 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Pipe Rack #4 | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-580 | 2023-05-25 | 3 | CRS-GUP-DHI-DT-23-1759 | 2023-03-22 | NC | DE-GUP-DT-E-23-066 | 2023-01-20 | A | CRS-GUP-DHI-DT-23-1495 | 2023-02-11 | RC | DE-GUP-DT-E-23-231 | 2023-02-23 | 1 | CRS-GUP-DHI-DT-23-1703 | 2023-03-06 | NC | DE-GUP-DT-E-23-278 | 2023-03-08 | 2 | CRS-GUP-DHI-DT-23-1759 | 2023-03-22 | NC | DE-GUP-DT-E-23-580 | 2023-05-25 | 3
| GUP | CA03 | P1 | UMY | 184455 |  | GUP-CA03-P1UMY-184455 | PIPE RACK #4_LINE FRAMING ELEVATION | FI | 2022-12-05 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Pipe Rack #4 | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-580 | 2023-05-25 | 3 | CRS-GUP-DHI-DT-23-1759 | 2023-03-22 | NC | DE-GUP-DT-E-23-066 | 2023-01-20 | 0 | CRS-GUP-DHI-DT-23-1495 | 2023-02-11 | NC | DE-GUP-DT-E-23-231 | 2023-02-23 | 1 | CRS-GUP-DHI-DT-23-1703 | 2023-03-06 | NC | DE-GUP-DT-E-23-278 | 2023-03-08 | 2 | CRS-GUP-DHI-DT-23-1759 | 2023-03-22 | NC | DE-GUP-DT-E-23-580 | 2023-05-25 | 3
| GUP | CA03 | P1 | UMY | 184456 |  | GUP-CA03-P1UMY-184456 | PIPE RACK #4_ROW FRAMING ELEVATION | FI | 2022-12-05 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Pipe Rack #4 | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-580 | 2023-05-25 | 3 | CRS-GUP-DHI-DT-23-1759 | 2023-03-22 | NC | DE-GUP-DT-E-23-066 | 2023-01-20 | 0 | CRS-GUP-DHI-DT-23-1495 | 2023-02-11 | NC | DE-GUP-DT-E-23-231 | 2023-02-23 | 1 | CRS-GUP-DHI-DT-23-1703 | 2023-03-06 | NC | DE-GUP-DT-E-23-278 | 2023-03-08 | 2 | CRS-GUP-DHI-DT-23-1759 | 2023-03-22 | NC | DE-GUP-DT-E-23-580 | 2023-05-25 | 3
| GUP | CA03 | P1 | UMY | 184457 |  | GUP-CA03-P1UMY-184457 | PIPE RACK #4_CONNECTION DETAIL | FI | 2022-12-05 |  | 건축기술2팀(Arch.) | 구남영 |  | P |  |  |  | CCPP | Pipe Rack #4 | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-580 | 2023-05-25 | 3 | CRS-GUP-DHI-DT-23-1759 | 2023-03-22 | NC | DE-GUP-DT-E-23-066 | 2023-01-20 | 0 | CRS-GUP-DHI-DT-23-1495 | 2023-02-11 | NC | DE-GUP-DT-E-23-231 | 2023-02-23 | 1 | CRS-GUP-DHI-DT-23-1703 | 2023-03-06 | NC | DE-GUP-DT-E-23-278 | 2023-03-08 | 2 | CRS-GUP-DHI-DT-23-1759 | 2023-03-22 | NC | DE-GUP-DT-E-23-580 | 2023-05-25 | 3
| GUP | CA03 | P1 | UGY | 184461 |  | GUP-CA03-P1UGY-184461 | YARD PLATFORM_OVERBRIDGE LOCATION PLAN | FI | 2024-03-31 |  | 건축기술2팀(Arch.) | 구남영 | [5 empty] | CCPP | Yard Flatform | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-082 | 2024-03-18 | 0 | CRS-GUP-DHI-DT-24-045 | 2024-04-08 | NC | DE-GUP-DT-E-24-082 | 2024-03-18 | 0 | CRS-GUP-DHI-DT-24-045 | 2024-04-08 | NC
| GUP | CA03 | P1 | UGY | 184462 |  | GUP-CA03-P1UGY-184462 | YARD PLATFORM_OVERBRIDGE DETAIL | FI | 2024-03-31 |  | 건축기술2팀(Arch.) | 구남영 | [5 empty] | CCPP | Yard Flatform | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-082 | 2024-03-18 | 0 | CRS-GUP-DHI-DT-24-045 | 2024-04-08 | NC | DE-GUP-DT-E-24-082 | 2024-03-18 | 0 | CRS-GUP-DHI-DT-24-045 | 2024-04-08 | NC
| GUP | CA03 | P1 | UGY | 184463 |  | GUP-CA03-P1UGY-184463 | YARD PLATFORM_FOUNDATION & ANCHOR BOLT DETAIL | FI | 2024-03-31 |  | 건축기술2팀(Arch.) | 구남영 | [5 empty] | CCPP | Yard Flatform | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-082 | 2024-03-18 | 0 | CRS-GUP-DHI-DT-24-045 | 2024-04-08 | NC | DE-GUP-DT-E-24-082 | 2024-03-18 | 0 | CRS-GUP-DHI-DT-24-045 | 2024-04-08 | NC
| GUP | CA03 | P1 | UGY | 184464 |  | GUP-CA03-P1UGY-184464 | YARD PLATFORM_STRUCTURAL MISC. DETAIL | FI | 2024-03-31 |  | 건축기술2팀(Arch.) | 구남영 | [5 empty] | CCPP | Yard Flatform | Arch. | 3 | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-24-082 | 2024-03-18 | 0 | CRS-GUP-DHI-DT-24-045 | 2024-04-08 | NC | DE-GUP-DT-E-24-082 | 2024-03-18 | 0 | CRS-GUP-DHI-DT-24-045 | 2024-04-08 | NC
| GUP | CA06 | P1 | UTA | 183502 |  | GUP-CA06-P1UTA-183502 | CHEMICAL STORAGE SHED_CALCULATION SHEET | FI | 2023-03-28 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Chemical Storage Shed | Arch. |  | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-803 | 2023-09-08 | 4 | 자체 CRS 개정 후 제출 | 2023-09-07 | N/A | DE-GUP-DT-E-23-455 | 2023-04-14 | 0 | CRS-GUP-DHI-DT-23-1888 | 2023-05-17 | RC | DE-GUP-DT-E-23-559 | 2023-05-17 | 1 | CRS-GUP-DHI-DT-23-1975 | 2023-06-01 | NC | DE-GUP-DT-E-23-636 | 2023-06-22 | 2 | CRS-GUP-DHI-DT-23-2029 | 2023-07-04 | NC | DE-GUP-DT-E-23-720 | 2023-07-25 | 3 | 자체 CRS 개정 후 제출 | 2023-09-07 | N/A | DE-GUP-DT-E-23-803 | 2023-09-08 | 4
| GUP | CA00 | P1 | UTA | 183521 |  | GUP-CA00-P1UTA-183521 | CHEMICAL STORAGE SHED_GROUND FLOOR & ROOF PLAN | FA | 2023-03-28 | 2023-07-04 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Chemical Storage Shed | Arch. |  | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-803 | 2023-09-08 | 2 | CRS-GUP-DHI-DT-23-2029 | 2023-07-04 | AA | DE-GUP-DT-E-23-454 | 2023-04-13 | A | CRS-GUP-DHI-DT-23-1875 | 2023-04-25 | AC | DE-GUP-DT-E-23-559 | 2023-05-17 | 0(CP) | CRS-GUP-DHI-DT-23-1975 | 2023-06-01 | AA | DE-GUP-DT-E-23-636 | 2023-06-22 | 1 | CRS-GUP-DHI-DT-23-2029 | 2023-07-04 | AA | DE-GUP-DT-E-23-803 | 2023-09-08 | 2
| GUP | CA00 | P1 | UTA | 183522 |  | GUP-CA00-P1UTA-183522 | CHEMICAL STORAGE SHED_MAIN SECTION | FA | 2023-03-28 | 2023-07-04 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Chemical Storage Shed | Arch. |  | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-803 | 2023-09-08 | 2 | CRS-GUP-DHI-DT-23-2029 | 2023-07-04 | AA | DE-GUP-DT-E-23-454 | 2023-04-13 | A | CRS-GUP-DHI-DT-23-1875 | 2023-04-25 | AC | DE-GUP-DT-E-23-559 | 2023-05-17 | 0(CP) | CRS-GUP-DHI-DT-23-1975 | 2023-06-01 | AA | DE-GUP-DT-E-23-636 | 2023-06-22 | 1 | CRS-GUP-DHI-DT-23-2029 | 2023-07-04 | AA | DE-GUP-DT-E-23-803 | 2023-09-08 | 2
| GUP | CA00 | P1 | UTA | 183523 |  | GUP-CA00-P1UTA-183523 | CHEMICAL STORAGE SHED_SIDE ELEVATION | FA | 2023-03-28 | 2023-07-04 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Chemical Storage Shed | Arch. |  | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-803 | 2023-09-08 | 2 | CRS-GUP-DHI-DT-23-2029 | 2023-07-04 | AA | DE-GUP-DT-E-23-454 | 2023-04-13 | A | CRS-GUP-DHI-DT-23-1875 | 2023-04-25 | AC | DE-GUP-DT-E-23-559 | 2023-05-17 | 0(CP) | CRS-GUP-DHI-DT-23-1975 | 2023-06-01 | AA | DE-GUP-DT-E-23-636 | 2023-06-22 | 1 | CRS-GUP-DHI-DT-23-2029 | 2023-07-04 | AA | DE-GUP-DT-E-23-803 | 2023-09-08 | 2
| GUP | CA00 | P1 | UTA | 183524 |  | GUP-CA00-P1UTA-183524 | CHEMICAL STORAGE SHED_ARCHITECTURAL MISC. DETAIL | FA | 2023-03-28 | 2023-07-04 | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Chemical Storage Shed | Arch. |  | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-803 | 2023-09-08 | 3 | 자체 CRS 개정 후 제출 | 2023-09-07 | N/A | DE-GUP-DT-E-23-454 | 2023-04-13 | A | CRS-GUP-DHI-DT-23-1875 | 2023-04-25 | AC | DE-GUP-DT-E-23-559 | 2023-05-17 | 0(CP) | CRS-GUP-DHI-DT-23-1975 | 2023-06-01 | AA | DE-GUP-DT-E-23-636 | 2023-06-22 | 1 | CRS-GUP-DHI-DT-23-2029 | 2023-07-04 | AA | DE-GUP-DT-E-23-720 | 2023-07-25 | 2 | 자체 CRS 개정 후 제출 | 2023-09-07 | N/A | DE-GUP-DT-E-23-803 | 2023-09-08 | 3
| GUP | CA01 | P1 | UTA | 183541 |  | GUP-CA01-P1UTA-183541 | CHEMICAL STORAGE SHED_FOUNDATION, GROUND & ROOF FRAMING PLAN | FI | 2023-03-28 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Chemical Storage Shed | Arch. |  | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-803 | 2023-09-08 | 4 | 자체 CRS 개정 후 제출 | 2023-09-07 | N/A | DE-GUP-DT-E-23-454 | 2023-04-13 | 0 | CRS-GUP-DHI-DT-23-1875 | 2023-04-25 | RC | DE-GUP-DT-E-23-559 | 2023-05-17 | 1 | CRS-GUP-DHI-DT-23-1975 | 2023-06-01 | RC | DE-GUP-DT-E-23-636 | 2023-06-22 | 2 | CRS-GUP-DHI-DT-23-2029 | 2023-07-04 | NC | DE-GUP-DT-E-23-720 | 2023-07-25 | 3 | 자체 CRS 개정 후 제출 | 2023-09-07 | N/A | DE-GUP-DT-E-23-803 | 2023-09-08 | 4
| GUP | CA01 | P1 | UTA | 183542 |  | GUP-CA01-P1UTA-183542 | CHEMICAL STORAGE SHED_LINE & ROW FRAMING ELEVATION | FI | 2023-03-28 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Chemical Storage Shed | Arch. |  | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-803 | 2023-09-08 | 3 | CRS-GUP-DHI-DT-23-2029 | 2023-07-04 | NC | DE-GUP-DT-E-23-454 | 2023-04-13 | 0 | CRS-GUP-DHI-DT-23-1875 | 2023-04-25 | RC | DE-GUP-DT-E-23-559 | 2023-05-17 | 1 | CRS-GUP-DHI-DT-23-1975 | 2023-06-01 | RC | DE-GUP-DT-E-23-636 | 2023-06-22 | 2 | CRS-GUP-DHI-DT-23-2029 | 2023-07-04 | NC | DE-GUP-DT-E-23-803 | 2023-09-08 | 3
| GUP | CA02 | P1 | UTA | 183543 |  | GUP-CA02-P1UTA-183543 | CHEMICAL STORAGE SHED_BEAM,GIRDER,SLAB & MISC. RE-BAR SCHEDULE | FI | 2023-03-28 |  | 건축기술2팀(Arch.) | 구남영 | B | P |  |  |  | CCPP | Chemical Storage Shed | Arch. |  | 2025-06-30 | 2025-07-02 |  | DE-GUP-DT-E-23-803 | 2023-09-08 | 4 | 자체 CRS 개정 후 제출 | 2023-09-07 | N/A | DE-GUP-DT-E-23-454 | 2023-04-13 | 0 | CRS-GUP-DHI-DT-23-1875 | 2023-04-25 | RC | DE-GUP-DT-E-23-559 | 2023-05-17 | 1 | CRS-GUP-DHI-DT-23-1975 | 2023-06-01 | NC | DE-GUP-DT-E-23-636 | 2023-06-22 | 2 | CRS-GUP-DHI-DT-23-2029 | 2023-07-04 | NC | DE-GUP-DT-E-23-720 | 2023-07-25 | 3 | 자체 CRS 개정 후 제출 | 2023-09-07 | N/A | DE-GUP-DT-E-23-803 | 2023-09-08 | 4
| GUP | CA05 | P1 | UST | 181571 |  | GUP-CA05-P1UST-181571 | MAINTENANCE WORKSHOP AND STORE BUILDING_PLUMBING EQUIPMENT SCHEDULE | FI | 2022-12-25 |  | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | Workshop Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-23-799 | 2023-09-07 | 4 | CRS-GUP-DHI-DT-23-2118 | 2023-09-27 | NC | DE-GUP-DT-E-22-974 | 2022-11-23 | 0 | CRS-GUP-DHI-DT-22-1227 | 2022-12-13 | RR | DE-GUP-DT-E-23-239 | 2023-02-23 | 1 | CRS-GUP-DHI-DT-23-1673 | 2023-03-10 | NC | DE-GUP-DT-E-23-440 | 2023-04-10 | 2 | CRS-GUP-DHI-DT-23-1841 | 2023-04-18 | NC | DE-GUP-DT-E-23-712 | 2023-07-24 | 3 | CRS-GUP-DHI-DT-23-2084 | 2023-08-02 | NC | DE-GUP-DT-E-23-799 | 2023-09-07 | 4 | CRS-GUP-DHI-DT-23-2118 | 2023-09-27 | NC
| GUP | CA05 | P1 | UST | 181572 |  | GUP-CA05-P1UST-181572 | MAINTENANCE WORKSHOP AND STORE BUILDING_PLUMBING SCHEMATIC DIAGRAM | FA | 2022-12-25 | 2023-03-26 | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | Workshop Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-279 | 2024-11-27 | 4 | 자체 CRS 개정 후 제출 | 2024-11-26 | N/A | DE-GUP-DT-E-22-974 | 2022-11-23 | A | CRS-GUP-DHI-DT-22-1227 | 2022-12-13 | RR | DE-GUP-DT-E-23-239 | 2023-02-23 | B | CRS-GUP-DHI-DT-23-1673 | 2023-03-10 | AC | DE-GUP-DT-E-23-440 | 2023-04-10 | 0(CP) | CRS-GUP-DHI-DT-23-1841 | 2023-04-18 | AC | DE-GUP-DT-E-23-712 | 2023-07-24 | 1(CP) | CRS-GUP-DHI-DT-23-2084 | 2023-08-02 | AC | DE-GUP-DT-E-23-799 | 2023-09-07 | 2(CP) | CRS-GUP-DHI-DT-23-2118 | 2023-09-27 | AA | DE-GUP-DT-E-23-1006 | 2023-12-21 | 3 | 자체 CRS 개정 후 제출 | 2024-11-26 | N/A | DE-GUP-DT-E-24-279 | 2024-11-27 | 4
| GUP | CA05 | P1 | UST | 181573 |  | GUP-CA05-P1UST-181573 | MAINTENANCE WORKSHOP AND STORE BUILDING_PLUMBING PLAN | FA | 2022-12-25 | 2023-03-26 | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | Workshop Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-279 | 2024-11-27 | 4 | 자체 CRS 개정 후 제출 | 2024-11-26 | N/A | DE-GUP-DT-E-22-974 | 2022-11-23 | A | CRS-GUP-DHI-DT-22-1227 | 2022-12-13 | RR | DE-GUP-DT-E-23-239 | 2023-02-23 | B | CRS-GUP-DHI-DT-23-1673 | 2023-03-10 | AC | DE-GUP-DT-E-23-440 | 2023-04-10 | 0(CP) | CRS-GUP-DHI-DT-23-1841 | 2023-04-18 | AC | DE-GUP-DT-E-23-712 | 2023-07-24 | 1(CP) | CRS-GUP-DHI-DT-23-2084 | 2023-08-02 | AC | DE-GUP-DT-E-23-799 | 2023-09-07 | 2(CP) | CRS-GUP-DHI-DT-23-2118 | 2023-09-27 | AA | DE-GUP-DT-E-23-1006 | 2023-12-21 | 3 | 자체 CRS 개정 후 제출 | 2024-11-26 | N/A | DE-GUP-DT-E-24-279 | 2024-11-27 | 4
| GUP | CA05 | P1 | UST | 181574 |  | GUP-CA05-P1UST-181574 | MAINTENANCE WORKSHOP AND STORE BUILDING_ENLARGED PLUMBING PLAN | FI | 2022-12-25 |  | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | Workshop Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-279 | 2024-11-27 | 5 | CRS-GUP-DHI-DT-23-2118 | 2023-09-27 | NC | DE-GUP-DT-E-22-974 | 2022-11-23 | 0 | CRS-GUP-DHI-DT-22-1227 | 2022-12-13 | RR | DE-GUP-DT-E-23-239 | 2023-02-23 | 1 | CRS-GUP-DHI-DT-23-1673 | 2023-03-10 | RC | DE-GUP-DT-E-23-440 | 2023-04-10 | 2 | CRS-GUP-DHI-DT-23-1841 | 2023-04-18 | RC | DE-GUP-DT-E-23-712 | 2023-07-24 | 3 | CRS-GUP-DHI-DT-23-2084 | 2023-08-02 | RC | DE-GUP-DT-E-23-799 | 2023-09-07 | 4 | CRS-GUP-DHI-DT-23-2118 | 2023-09-27 | NC | DE-GUP-DT-E-24-279 | 2024-11-27 | 5
| GUP | CA05 | P1 | UST | 181575 |  | GUP-CA05-P1UST-181575 | MAINTENANCE WORKSHOP AND STORE BUILDING_PLUMBING ISO DRAWING | FI | 2022-12-25 |  | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | Workshop Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-279 | 2024-11-27 | 5 | CRS-GUP-DHI-DT-23-2118 | 2023-09-27 | NC | DE-GUP-DT-E-22-974 | 2022-11-23 | 0 | CRS-GUP-DHI-DT-22-1227 | 2022-12-13 | RR | DE-GUP-DT-E-23-239 | 2023-02-23 | 1 | CRS-GUP-DHI-DT-23-1673 | 2023-03-10 | NC | DE-GUP-DT-E-23-440 | 2023-04-10 | 2 | CRS-GUP-DHI-DT-23-1841 | 2023-04-18 | NC | DE-GUP-DT-E-23-712 | 2023-07-24 | 3 | CRS-GUP-DHI-DT-23-2084 | 2023-08-02 | NC | DE-GUP-DT-E-23-799 | 2023-09-07 | 4 | CRS-GUP-DHI-DT-23-2118 | 2023-09-27 | NC | DE-GUP-DT-E-24-279 | 2024-11-27 | 5
| GUP | CA05 | P1 | UGD | 181671 |  | GUP-CA05-P1UGD-181671 | WT & WWT BLDG & SHELTER_PLUMBING EQUIPMENT SCHEDULE | FI | 2022-07-25 |  | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | WT & WWT Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-24-280 | 2024-11-29 | 5 | 자체 CRS 개정 후 제출 | 2024-11-28 | N/A | DE-GUP-DT-E-22-428 | 2022-07-21 | 0 | CRS-GUP-DHI-DT-22-628 | 2022-08-18 | RC | DE-GUP-DT-E-22-982 | 2022-11-24 | 1 | CRS-GUP-DHI-DT-22-1231 | 2022-12-13 | NC | DE-GUP-DT-E-23-294 | 2023-03-10 | 2 | CRS-GUP-DHI-DT-23-1765 | 2023-03-22 | NC | DE-GUP-DT-E-23-1005 | 2023-12-21 | 3 | 자체 CRS 개정 후 제출 | 2024-05-01 | N/A | DE-GUP-DT-E-24-117 | 2024-05-02 | 4 | 자체 CRS 개정 후 제출 | 2024-11-28 | N/A | DE-GUP-DT-E-24-280 | 2024-11-29 | 5
| GUP | CA05 | P1 | UGD | 181672 |  | GUP-CA05-P1UGD-181672 | WT & WWT BLDG & SHELTER_PLUMBING SCHEMATIC DIAGRAM | FA | 2022-07-25 | 2022-11-01 | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | WT & WWT Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-24-280 | 2024-11-29 | 3 | 자체 CRS 개정 후 제출 | 2024-11-28 | N/A | DE-GUP-DT-E-22-428 | 2022-07-21 | A | CRS-GUP-DHI-DT-22-628 | 2022-08-18 | RC | DE-GUP-DT-E-22-982 | 2022-11-24 | B | CRS-GUP-DHI-DT-22-1231 | 2022-12-13 | AC | DE-GUP-DT-E-23-294 | 2023-03-10 | 0(CP) | CRS-GUP-DHI-DT-23-1765 | 2023-03-22 | AA | DE-GUP-DT-E-23-1004 | 2023-12-21 | 1 | 자체 CRS 개정 후 제출 | 2024-05-01 | N/A | DE-GUP-DT-E-24-117 | 2024-05-02 | 2 | 자체 CRS 개정 후 제출 | 2024-11-28 | N/A | DE-GUP-DT-E-24-280 | 2024-11-29 | 3
| GUP | CA05 | P1 | UGD | 181673 |  | GUP-CA05-P1UGD-181673 | WT & WWT BLDG & SHELTER_PLUMBING PLAN | FA | 2022-07-25 | 2022-11-01 | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | WT & WWT Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-24-280 | 2024-11-29 | 3 | 자체 CRS 개정 후 제출 | 2024-11-28 | N/A | DE-GUP-DT-E-22-428 | 2022-07-21 | A | CRS-GUP-DHI-DT-22-628 | 2022-08-18 | RC | DE-GUP-DT-E-22-982 | 2022-11-24 | B | CRS-GUP-DHI-DT-22-1231 | 2022-12-13 | AC | DE-GUP-DT-E-23-294 | 2023-03-10 | 0(CP) | CRS-GUP-DHI-DT-23-1765 | 2023-03-22 | AA | DE-GUP-DT-E-23-1004 | 2023-12-21 | 1 | 자체 CRS 개정 후 제출 | 2024-05-01 | N/A | DE-GUP-DT-E-24-117 | 2024-05-02 | 2 | 자체 CRS 개정 후 제출 | 2024-11-28 | N/A | DE-GUP-DT-E-24-280 | 2024-11-29 | 3
| GUP | CA05 | P1 | UGD | 181674 |  | GUP-CA05-P1UGD-181674 | WT & WWT BLDG & SHELTER_ENLARGED PLUMBING PLAN | FI | 2022-07-25 |  | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | WT & WWT Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-24-280 | 2024-11-29 | 5 | 자체 CRS 개정 후 제출 | 2024-11-28 | N/A | DE-GUP-DT-E-22-428 | 2022-07-21 | 0 | CRS-GUP-DHI-DT-22-628 | 2022-08-18 | RC | DE-GUP-DT-E-22-982 | 2022-11-24 | 1 | CRS-GUP-DHI-DT-22-1231 | 2022-12-13 | NC | DE-GUP-DT-E-23-294 | 2023-03-10 | 2 | CRS-GUP-DHI-DT-23-1765 | 2023-03-22 | NC | DE-GUP-DT-E-23-1005 | 2023-12-21 | 3 | 자체 CRS 개정 후 제출 | 2024-05-01 | N/A | DE-GUP-DT-E-24-117 | 2024-05-02 | 4 | 자체 CRS 개정 후 제출 | 2024-11-28 | N/A | DE-GUP-DT-E-24-280 | 2024-11-29 | 5
| GUP | CA05 | P1 | UGD | 181675 |  | GUP-CA05-P1UGD-181675 | WT & WWT BLDG & SHELTER_PLUMBING ISO DRAWING | FI | 2022-07-25 |  | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | WT & WWT Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-24-280 | 2024-11-29 | 5 | 자체 CRS 개정 후 제출 | 2024-11-28 | N/A | DE-GUP-DT-E-22-428 | 2022-07-21 | 0 | CRS-GUP-DHI-DT-22-628 | 2022-08-18 | NC | DE-GUP-DT-E-22-982 | 2022-11-24 | 1 | CRS-GUP-DHI-DT-22-1231 | 2022-12-13 | NC | DE-GUP-DT-E-23-294 | 2023-03-10 | 2 | CRS-GUP-DHI-DT-23-1765 | 2023-03-22 | NC | DE-GUP-DT-E-23-1005 | 2023-12-21 | 3 | 자체 CRS 개정 후 제출 | 2024-05-01 | N/A | DE-GUP-DT-E-24-117 | 2024-05-02 | 4 | 자체 CRS 개정 후 제출 | 2024-11-28 | N/A | DE-GUP-DT-E-24-280 | 2024-11-29 | 5
| GUP | CA05 | P1 | UHA | 181371 |  | GUP-CA05-P1UHA-181371 | HRSG BUILDING_EQUIPMENT DRAIN SCHEMATIC DIAGRAM | FA | 2022-09-01 | 2022-12-31 | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | HRSG Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-24-120 | 2024-05-02 | 2 | CRS-GUP-DHI-DT-23-1704 | 2023-03-14 | NC | DHI-GUP-DT-22-143 | 2022-04-01 | A | CRS-GUP-DHI-DT-22-300 | 2022-04-17 | NC | DE-GUP-DT-E-22-282 | 2022-06-09 | 0 | CRS-GUP-DHI-DT-22-489 | 2022-07-06 | NC | DE-GUP-DT-E-23-235 | 2023-02-23 | 1 | CRS-GUP-DHI-DT-23-1704 | 2023-03-14 | NC | DE-GUP-DT-E-24-120 | 2024-05-02 | 2
| GUP | CA05 | P1 | UHA | 181372 |  | GUP-CA05-P1UHA-181372 | HRSG BUILDING_EQUIPMENT DRAIN PLAN | FA | 2022-09-01 | 2022-12-31 | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | HRSG Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-24-120 | 2024-05-02 | 2 | CRS-GUP-DHI-DT-23-1704 | 2023-03-14 | NC | DHI-GUP-DT-22-143 | 2022-04-01 | A | CRS-GUP-DHI-DT-22-300 | 2022-04-17 | NC | DE-GUP-DT-E-22-282 | 2022-06-09 | 0 | CRS-GUP-DHI-DT-22-489 | 2022-07-06 | NC | DE-GUP-DT-E-23-235 | 2023-02-23 | 1 | CRS-GUP-DHI-DT-23-1704 | 2023-03-14 | NC | DE-GUP-DT-E-24-120 | 2024-05-02 | 2
| GUP | CA05 | P1 | UHA | 181373 |  | GUP-CA05-P1UHA-181373 | HRSG BUILDING_EQUIPMENT DRAIN ISO DRAWING | FI | 2022-09-01 |  | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | HRSG Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-24-120 | 2024-05-02 | 3 | CRS-GUP-DHI-DT-23-1704 | 2023-03-14 | NC | DHI-GUP-DT-22-143 | 2022-04-01 | 0 | CRS-GUP-DHI-DT-22-300 | 2022-04-17 | NC | DE-GUP-DT-E-22-282 | 2022-06-09 | 1 | CRS-GUP-DHI-DT-22-489 | 2022-07-06 | NC | DE-GUP-DT-E-23-235 | 2023-02-23 | 2 | CRS-GUP-DHI-DT-23-1704 | 2023-03-14 | NC | DE-GUP-DT-E-24-120 | 2024-05-02 | 3
| GUP | CA05 | P1 | UMA | 181271 |  | GUP-CA05-P1UMA-181271 | STEAM TURBINE BUILDING_EQUIPMENT DRAIN SCHEMATIC DIAGRAM | FA | 2022-07-04 | 2022-11-03 | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | ST Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-24-119 | 2024-05-02 | 1 | 자체 CRS 개정 후 제출 | 2024-05-01 | N/A | DE-GUP-DT-E-22-430 | 2022-07-22 | A | CRS-GUP-DHI-DT-22-645 | 2022-08-20 | AA | DE-GUP-DT-E-22-954 | 2022-11-17 | B | CRS-GUP-DHI-DT-22-1253 | 2022-12-13 | AA | DE-GUP-DT-E-22-1137 | 2022-12-20 | 0 | 자체 CRS 개정 후 제출 | 2024-05-01 | N/A | DE-GUP-DT-E-24-119 | 2024-05-02 | 1
| GUP | CA05 | P1 | UMA | 181272 |  | GUP-CA05-P1UMA-181272 | STEAM TURBINE BUILDING_EQUIPMENT DRAIN PLAN | FA | 2022-07-04 | 2022-11-03 | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | ST Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-24-119 | 2024-05-02 | 1 | 자체 CRS 개정 후 제출 | 2024-05-01 | N/A | DE-GUP-DT-E-22-430 | 2022-07-22 | A | CRS-GUP-DHI-DT-22-645 | 2022-08-20 | RC | DE-GUP-DT-E-22-954 | 2022-11-17 | B | CRS-GUP-DHI-DT-22-1253 | 2022-12-13 | AA | DE-GUP-DT-E-22-1137 | 2022-12-20 | 0 | 자체 CRS 개정 후 제출 | 2024-05-01 | N/A | DE-GUP-DT-E-24-119 | 2024-05-02 | 1
| GUP | CA05 | P1 | UMA | 181273 |  | GUP-CA05-P1UMA-181273 | STEAM TURBINE BUILDING_EQUIPMENT DRAIN ISO DRAWING | FI | 2022-07-04 |  | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | ST Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-24-119 | 2024-05-02 | 3 | 자체 CRS 개정 후 제출 | 2024-05-01 | N/A | DE-GUP-DT-E-22-430 | 2022-07-22 | 0 | CRS-GUP-DHI-DT-22-630 | 2022-08-18 | NC | DE-GUP-DT-E-22-954 | 2022-11-17 | 1 | CRS-GUP-DHI-DT-22-1253 | 2022-12-13 | NC | DE-GUP-DT-E-22-1137 | 2022-12-20 | 2 | 자체 CRS 개정 후 제출 | 2024-05-01 | N/A | DE-GUP-DT-E-24-119 | 2024-05-02 | 3
| GUP | CA05 | P1 | UMX | 181171 |  | GUP-CA05-P1UMX-181171 | GAS TURBINE BUILDING_EQUIPMENT DRAIN SCHEMATIC DIAGRAM | FA | 2022-03-02 | 2022-08-20 | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | GT Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-24-118 | 2024-05-02 | 1 | 자체 CRS 개정 후 제출 | 2024-05-01 | N/A | DHI-GUP-DT-22-037 | 2022-01-26 | A | CRS-GUP-DHI-DT-21-199 | 2022-02-14 | RC | DE-GUP-DT-E-22-398 | 2022-07-14 | B | CRS-GUP-DHI-DT-22-560 | 2022-08-01 | RC | DE-GUP-DT-E-22-806 | 2022-10-17 | C | CRS-GUP-DHI-DT-22-1218 | 2022-12-05 | RC | DE-GUP-DT-E-22-1185 | 2022-12-23 | D | CRS-GUP-DHI-DT-23-1486 | 2023-02-11 | AA | DE-GUP-DT-E-23-218 | 2023-02-22 | 0 | 자체 CRS 개정 후 제출 | 2024-05-01 | N/A | DE-GUP-DT-E-24-118 | 2024-05-02 | 1
| GUP | CA05 | P1 | UMX | 181172 |  | GUP-CA05-P1UMX-181172 | GAS TURBINE BUILDING_EQUIPMENT DRAIN PLAN | FA | 2022-03-02 | 2022-08-20 | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | GT Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-24-118 | 2024-05-02 | 1 | 자체 CRS 개정 후 제출 | 2024-05-01 | N/A | DHI-GUP-DT-22-037 | 2022-01-26 | A | CRS-GUP-DHI-DT-21-199 | 2022-02-14 | RC | DE-GUP-DT-E-22-398 | 2022-07-14 | B | CRS-GUP-DHI-DT-22-560 | 2022-08-01 | RC | DE-GUP-DT-E-22-806 | 2022-10-17 | C | CRS-GUP-DHI-DT-22-1218 | 2022-12-05 | RC | DE-GUP-DT-E-22-1185 | 2022-12-23 | D | CRS-GUP-DHI-DT-23-1486 | 2023-02-11 | AA | DE-GUP-DT-E-23-218 | 2023-02-22 | 0 | 자체 CRS 개정 후 제출 | 2024-05-01 | N/A | DE-GUP-DT-E-24-118 | 2024-05-02 | 1
| GUP | CA05 | P1 | UMX | 181173 |  | GUP-CA05-P1UMX-181173 | GAS TURBINE BUILDING_EQUIPMENT DRAIN ISO DRAWING | FA | 2022-03-02 | 2022-08-20 | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | GT Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-24-118 | 2024-05-02 | 1 | 자체 CRS 개정 후 제출 | 2024-05-01 | N/A | DHI-GUP-DT-22-037 | 2022-01-26 | A | CRS-GUP-DHI-DT-21-199 | 2022-02-14 | AA | DE-GUP-DT-E-22-398 | 2022-07-14 | B | CRS-GUP-DHI-DT-22-560 | 2022-08-01 | RC | DE-GUP-DT-E-22-806 | 2022-10-17 | C | CRS-GUP-DHI-DT-22-1218 | 2022-12-05 | RC | DE-GUP-DT-E-22-1185 | 2022-12-23 | D | CRS-GUP-DHI-DT-23-1486 | 2023-02-11 | AA | DE-GUP-DT-E-23-218 | 2023-02-22 | 0 | 자체 CRS 개정 후 제출 | 2024-05-01 | N/A | DE-GUP-DT-E-24-118 | 2024-05-02 | 1
| GUP | CA05 | P1 | UAB | 181177 |  | GUP-CA05-P1UAB-181177 | SWITCHYARD CONTROL BUILDING_PLUMBING EQUIPMENT SCHEDULE | FI | 2022-08-14 |  | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | SWYD Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-23-708 | 2023-07-21 | 3 | CRS-GUP-DHI-DT-23-1752 | 2023-03-18 | NC | DE-GUP-DT-E-22-677 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-887 | 2022-10-10 | NC | DE-GUP-DT-E-22-935 | 2022-11-10 | 1 | CRS-GUP-DHI-DT-22-1165 | 2022-11-26 | NC | DE-GUP-DT-E-23-273 | 2023-03-07 | 2 | CRS-GUP-DHI-DT-23-1752 | 2023-03-18 | NC | DE-GUP-DT-E-23-708 | 2023-07-21 | 3
| GUP | CA05 | P1 | UAB | 181178 |  | GUP-CA05-P1UAB-181178 | SWITCHYARD CONTROL BUILDING_PLUMBING SCHEMATIC DIAGRAM | FA | 2022-08-14 | 2022-11-14 | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | SWYD Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-24-281 | 2024-11-29 | 2 | 자체 CRS 개정 후 제출 | 2024-11-28 | N/A | DE-GUP-DT-E-22-677 | 2022-09-16 | A | CRS-GUP-DHI-DT-22-887 | 2022-10-10 | RC | DE-GUP-DT-E-22-935 | 2022-11-10 | B | CRS-GUP-DHI-DT-22-1165 | 2022-11-26 | AC | DE-GUP-DT-E-23-273 | 2023-03-07 | 0(CP) | CRS-GUP-DHI-DT-23-1752 | 2023-03-18 | AA | DE-GUP-DT-E-23-708 | 2023-07-21 | 1 | 자체 CRS 개정 후 제출 | 2024-11-28 | N/A | DE-GUP-DT-E-24-281 | 2024-11-29 | 2
| GUP | CA05 | P1 | UAB | 181179 |  | GUP-CA05-P1UAB-181179 | SWITCHYARD CONTROL BUILDING_PLUMBING PLAN | FA | 2022-08-14 | 2022-11-14 | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | SWYD Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-24-281 | 2024-11-29 | 2 | 자체 CRS 개정 후 제출 | 2024-11-28 | N/A | DE-GUP-DT-E-22-677 | 2022-09-16 | A | CRS-GUP-DHI-DT-22-887 | 2022-10-10 | RC | DE-GUP-DT-E-22-935 | 2022-11-10 | B | CRS-GUP-DHI-DT-22-1165 | 2022-11-26 | AA | DE-GUP-DT-E-23-273 | 2023-03-07 | 0 | CRS-GUP-DHI-DT-23-1752 | 2023-03-18 | AA | DE-GUP-DT-E-23-708 | 2023-07-21 | 1 | 자체 CRS 개정 후 제출 | 2024-11-28 | N/A | DE-GUP-DT-E-24-281 | 2024-11-29 | 2
| GUP | CA05 | P1 | UAB | 181180 |  | GUP-CA05-P1UAB-181180 | SWITCHYARD CONTROL BUILDING_ENLARGED PLUMBING PLAN | FI | 2022-08-14 |  | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | SWYD Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-24-281 | 2024-11-29 | 4 | 자체 CRS 개정 후 제출 | 2024-11-28 | N/A | DE-GUP-DT-E-22-677 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-887 | 2022-10-10 | RC | DE-GUP-DT-E-22-935 | 2022-11-10 | 1 | CRS-GUP-DHI-DT-22-1165 | 2022-11-26 | NC | DE-GUP-DT-E-23-273 | 2023-03-07 | 2 | CRS-GUP-DHI-DT-23-1752 | 2023-03-18 | NC | DE-GUP-DT-E-23-708 | 2023-07-21 | 3 | 자체 CRS 개정 후 제출 | 2024-11-28 | N/A | DE-GUP-DT-E-24-281 | 2024-11-29 | 4
| GUP | CA05 | P1 | UAB | 181181 |  | GUP-CA05-P1UAB-181181 | SWITCHYARD CONTROL BUILDING_PLUMBING ISO DRAWING | FI | 2022-08-14 |  | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | SWYD Building | Arch. | 3 | 2025-04-17 | 2025-07-02 |  | DE-GUP-DT-E-24-281 | 2024-11-29 | 4 | 자체 CRS 개정 후 제출 | 2024-11-28 | N/A | DE-GUP-DT-E-22-677 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-887 | 2022-10-10 | NC | DE-GUP-DT-E-22-935 | 2022-11-10 | 1 | CRS-GUP-DHI-DT-22-1165 | 2022-11-26 | NC | DE-GUP-DT-E-23-273 | 2023-03-07 | 2 | CRS-GUP-DHI-DT-23-1752 | 2023-03-18 | NC | DE-GUP-DT-E-23-708 | 2023-07-21 | 3 | 자체 CRS 개정 후 제출 | 2024-11-28 | N/A | DE-GUP-DT-E-24-281 | 2024-11-29 | 4
| GUP | CA05 | P1 | UYF | 182071 |  | GUP-CA05-P1UYF-182071 | GATE HOUSE_PLUMBING EQUIPMENT SCHEDULE & SCHEMATIC DIAGRAM | FA | 2022-10-25 | 2023-02-25 | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | Gate House | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-277 | 2024-11-27 | 2 | 자체 CRS 개정 후 제출 | 2024-11-26 | N/A | DE-GUP-DT-E-22-951 | 2022-11-17 | A | CRS-GUP-DHI-DT-22-1212 | 2022-11-30 | RC | DE-GUP-DT-E-23-354 | 2023-03-24 | B | CRS-GUP-DHI-DT-23-1813 | 2023-04-12 | AA | DE-GUP-DT-E-23-491 | 2023-04-21 | 0 | CRS-GUP-DHI-DT-23-1916 | 2023-05-05 | AA | DE-GUP-DT-E-23-930 | 2023-11-22 | 1 | 자체 CRS 개정 후 제출 | 2024-11-26 | N/A | DE-GUP-DT-E-24-277 | 2024-11-27 | 2
| GUP | CA05 | P1 | UYF | 182072 |  | GUP-CA05-P1UYF-182072 | GATE HOUSE_PLUMBING PLAN | FA | 2022-10-25 | 2023-02-25 | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | Gate House | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-277 | 2024-11-27 | 2 | 자체 CRS 개정 후 제출 | 2024-11-26 | N/A | DE-GUP-DT-E-22-951 | 2022-11-17 | A | CRS-GUP-DHI-DT-22-1212 | 2022-11-30 | RC | DE-GUP-DT-E-23-354 | 2023-03-24 | B | CRS-GUP-DHI-DT-23-1813 | 2023-04-12 | AA | DE-GUP-DT-E-23-491 | 2023-04-21 | 0 | CRS-GUP-DHI-DT-23-1916 | 2023-05-05 | AA | DE-GUP-DT-E-23-930 | 2023-11-22 | 1 | 자체 CRS 개정 후 제출 | 2024-11-26 | N/A | DE-GUP-DT-E-24-277 | 2024-11-27 | 2
| GUP | CA05 | P1 | UYF | 182073 |  | GUP-CA05-P1UYF-182073 | GATE HOUSE_PLUMBING ISO DRAWING | FI | 2022-10-25 |  | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | Gate House | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-277 | 2024-11-27 | 4 | 자체 CRS 개정 후 제출 | 2024-11-26 | N/A | DE-GUP-DT-E-22-951 | 2022-11-17 | 0 | CRS-GUP-DHI-DT-22-1212 | 2022-11-30 | RC | DE-GUP-DT-E-23-354 | 2023-03-24 | 1 | CRS-GUP-DHI-DT-23-1813 | 2023-04-12 | NC | DE-GUP-DT-E-23-491 | 2023-04-21 | 2 | CRS-GUP-DHI-DT-23-1916 | 2023-05-05 | NC | DE-GUP-DT-E-23-930 | 2023-11-22 | 3 | 자체 CRS 개정 후 제출 | 2024-11-26 | N/A | DE-GUP-DT-E-24-277 | 2024-11-27 | 4
| GUP | CA05 | P1 | UCB | 181471 |  | GUP-CA05-P1UCB-181471 | CONTROL & ELECTRICAL BUILDING_PLUMBING EQUIPMENT SCHEDULE | FI | 2022-02-16 |  | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-24-278 | 2024-11-27 | 6 | CRS-GUP-DHI-DT-23-1733 | 2023-03-17 | NC | DHI-GUP-DT-22-077 | 2022-02-17 | 0 | CRS-GUP-DHI-DT-22-238 | 2022-03-07 | NC | DHI-GUP-DT-22-149 | 2022-04-04 | 1 | CRS-GUP-DHI-DT-22-304 | 2022-04-17 | NC | DE-GUP-DT-E-22-340 | 2022-06-27 | 2 | CRS-GUP-DHI-DT-22-533 | 2022-07-19 | NC | DE-GUP-DT-E-22-582 | 2022-08-30 | 3 | CRS-GUP-DHI-DT-22-842 | 2022-09-19 | NC | DE-GUP-DT-E-22-961 | 2022-11-18 | 4 | CRS-GUP-DHI-DT-22-1201 | 2022-11-30 | NC | DE-GUP-DT-E-23-192 | 2023-02-16 | 5 | CRS-GUP-DHI-DT-23-1733 | 2023-03-17 | NC | DE-GUP-DT-E-24-278 | 2024-11-27 | 6
| GUP | CA05 | P1 | UCB | 181472 |  | GUP-CA05-P1UCB-181472 | CONTROL & ELECTRICAL BUILDING_PLUMBING SCHEMATIC DIAGRAM | FA | 2022-02-16 | 2022-07-20 | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-24-278 | 2024-11-27 | 1 | 자체 CRS 개정 후 제출 | 2024-11-26 | N/A | DHI-GUP-DT-22-077 | 2022-02-17 | A | CRS-GUP-DHI-DT-22-238 | 2022-03-07 | RC | DHI-GUP-DT-22-149 | 2022-04-04 | B | CRS-GUP-DHI-DT-22-304 | 2022-04-17 | RC | DE-GUP-DT-E-22-340 | 2022-06-27 | C | CRS-GUP-DHI-DT-22-513 | 2022-07-12 | AC | DE-GUP-DT-E-22-582 | 2022-08-30 | D | CRS-GUP-DHI-DT-22-790 | 2022-09-19 | AC | DE-GUP-DT-E-22-961 | 2022-11-18 | E | CRS-GUP-DHI-DT-22-1254 | 2022-12-13 | AA | DE-GUP-DT-E-23-192 | 2023-02-16 | 0 | 자체 CRS 개정 후 제출 | 2024-11-26 | N/A | DE-GUP-DT-E-24-278 | 2024-11-27 | 1
| GUP | CA05 | P1 | UCB | 181473 |  | GUP-CA05-P1UCB-181473 | CONTROL & ELECTRICAL BUILDING_PLUMBING PLAN | FA | 2022-02-16 | 2022-07-20 | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-24-278 | 2024-11-27 | 1 | 자체 CRS 개정 후 제출 | 2024-11-26 | N/A | DHI-GUP-DT-22-077 | 2022-02-17 | A | CRS-GUP-DHI-DT-22-238 | 2022-03-07 | RC | DHI-GUP-DT-22-149 | 2022-04-04 | B | CRS-GUP-DHI-DT-22-304 | 2022-04-17 | RC | DE-GUP-DT-E-22-340 | 2022-06-27 | C | CRS-GUP-DHI-DT-22-513 | 2022-07-12 | RC | DE-GUP-DT-E-22-582 | 2022-08-30 | D | CRS-GUP-DHI-DT-22-790 | 2022-09-19 | AC | DE-GUP-DT-E-22-961 | 2022-11-18 | E | CRS-GUP-DHI-DT-22-1254 | 2022-12-13 | AA | DE-GUP-DT-E-23-192 | 2023-02-16 | 0 | 자체 CRS 개정 후 제출 | 2024-11-26 | N/A | DE-GUP-DT-E-24-278 | 2024-11-27 | 1
| GUP | CA05 | P1 | UCB | 181475 |  | GUP-CA05-P1UCB-181475 | CONTROL & ELECTRICAL BUILDING_ENLARGED PLUMBING PLAN | FI | 2022-02-16 |  | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-24-278 | 2024-11-27 | 6 | CRS-GUP-DHI-DT-23-1733 | 2023-03-17 | NC | DHI-GUP-DT-22-077 | 2022-02-17 | 0 | CRS-GUP-DHI-DT-22-238 | 2022-03-07 | RC | DHI-GUP-DT-22-149 | 2022-04-04 | 1 | CRS-GUP-DHI-DT-22-304 | 2022-04-17 | RC | DE-GUP-DT-E-22-340 | 2022-06-27 | 2 | CRS-GUP-DHI-DT-22-513 | 2022-07-12 | RC | DE-GUP-DT-E-22-582 | 2022-08-30 | 3 | CRS-GUP-DHI-DT-22-790 | 2022-09-19 | NC | DE-GUP-DT-E-22-961 | 2022-11-18 | 4 | CRS-GUP-DHI-DT-22-1201 | 2022-11-30 | NC | DE-GUP-DT-E-23-192 | 2023-02-16 | 5 | CRS-GUP-DHI-DT-23-1733 | 2023-03-17 | NC | DE-GUP-DT-E-24-278 | 2024-11-27 | 6
| GUP | CA05 | P1 | UCB | 181476 |  | GUP-CA05-P1UCB-181476 | CONTROL & ELECTRICAL BUILDING_PLUMBING ISO DRAWING | FI | 2022-02-16 |  | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | C&E Building | Arch. | 3 | 2025-05-01 | 2025-07-02 |  | DE-GUP-DT-E-24-278 | 2024-11-27 | 6 | CRS-GUP-DHI-DT-23-1733 | 2023-03-17 | NC | DHI-GUP-DT-22-077 | 2022-02-17 | 0 | CRS-GUP-DHI-DT-22-238 | 2022-03-07 | RC | DHI-GUP-DT-22-149 | 2022-04-04 | 1 | CRS-GUP-DHI-DT-22-304 | 2022-04-17 | NC | DE-GUP-DT-E-22-340 | 2022-06-27 | 2 | CRS-GUP-DHI-DT-22-513 | 2022-07-12 | NC | DE-GUP-DT-E-22-582 | 2022-08-30 | 3 | CRS-GUP-DHI-DT-22-790 | 2022-09-19 | NC | DE-GUP-DT-E-22-961 | 2022-11-18 | 4 | CRS-GUP-DHI-DT-22-1201 | 2022-11-30 | NC | DE-GUP-DT-E-23-192 | 2023-02-16 | 5 | CRS-GUP-DHI-DT-23-1733 | 2023-03-17 | NC | DE-GUP-DT-E-24-278 | 2024-11-27 | 6
| GUP | CA05 | P1 | UYC | 181771 |  | GUP-CA05-P1UYC-181771 | ADMINISTRATION BUILDING_PLUMBING EQUIPMENT SCHEDULE | FI | 2022-09-30 |  | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | Admin. Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-249 | 2024-10-14 | 6 | 자체 CRS 개정 후 제출 | 2024-10-13 | N/A | DE-GUP-DT-E-22-1112 | 2022-12-16 | 0 | CRS-GUP-DHI-DT-22-1352 | 2022-12-29 | NC | DHI-GUP-DT-23-292 | 2023-03-09 | 1 | CRS-GUP-DHI-DT-23-1764 | 2023-03-22 | NC | DE-GUP-DT-E-23-441 | 2023-04-10 | 2 | CRS-GUP-DHI-DT-23-1865 | 2023-04-19 | NC | DE-GUP-DT-E-23-537 | 2023-05-09 | 3 | CRS-GUP-DHI-DT-23-1955 | 2023-05-18 | NC | DE-GUP-DT-E-23-948 | 2023-11-28 | 4 | CRS-GUP-DHI-DT-24-018 | 2024-02-21 | NC | DE-GUP-DT-E-24-182 | 2024-07-15 | 5 | 자체 CRS 개정 후 제출 | 2024-10-13 | N/A | DE-GUP-DT-E-24-249 | 2024-10-14 | 6
| GUP | CA05 | P1 | UYC | 181772 |  | GUP-CA05-P1UYC-181772 | ADMINISTRATION BUILDING_PLUMBING SCHEMATIC DIAGRAM | FA | 2022-09-30 | 2023-01-29 | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | Admin. Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | 자체 CRS 개정 후 제출 | 2024-11-28 | N/A | 자체 CRS 개정 후 제출 | 2024-11-28 | N/A | DE-GUP-DT-E-22-1112 | 2022-12-16 | A | CRS-GUP-DHI-DT-22-1352 | 2022-12-29 | RC | DHI-GUP-DT-23-292 | 2023-03-09 | B | CRS-GUP-DHI-DT-23-1764 | 2023-03-22 | RC | DE-GUP-DT-E-23-441 | 2023-04-10 | C | CRS-GUP-DHI-DT-23-1865 | 2023-04-19 | AC | DE-GUP-DT-E-23-537 | 2023-05-09 | 0 | CRS-GUP-DHI-DT-23-1955 | 2023-05-18 | AC | DE-GUP-DT-E-23-948 | 2023-11-28 | 1(CP) | CRS-GUP-DHI-DT-24-018 | 2024-02-21 | AA | DE-GUP-DT-E-24-163 | 2024-06-25 | 2 | 자체 CRS 개정 후 제출 | 2024-07-14 | N/A | DE-GUP-DT-E-24-182 | 2024-07-15 | 3 | 자체 CRS 개정 후 제출 | 2024-10-13 | N/A | DE-GUP-DT-E-24-249 | 2024-10-14 | 4 | 자체 CRS 개정 후 제출 | 2024-11-28 | N/A | DE-GUP-DT-E-24-284 | 2024-11-28 | 5
| GUP | CA05 | P1 | UYC | 181773 |  | GUP-CA05-P1UYC-181773 | ADMINISTRATION BUILDING_PLUMBING PLAN | FA | 2022-09-30 | 2023-01-29 | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | Admin. Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-249 | 2024-10-14 | 4 | 자체 CRS 개정 후 제출 | 2024-10-13 | N/A | DE-GUP-DT-E-22-1112 | 2022-12-16 | A | CRS-GUP-DHI-DT-22-1352 | 2022-12-29 | RC | DHI-GUP-DT-23-292 | 2023-03-09 | B | CRS-GUP-DHI-DT-23-1764 | 2023-03-22 | RC | DE-GUP-DT-E-23-441 | 2023-04-10 | C | CRS-GUP-DHI-DT-23-1865 | 2023-04-19 | AC | DE-GUP-DT-E-23-537 | 2023-05-09 | 0 | CRS-GUP-DHI-DT-23-1955 | 2023-05-18 | AC | DE-GUP-DT-E-23-948 | 2023-11-28 | 1(CP) | CRS-GUP-DHI-DT-24-018 | 2024-02-21 | AA | DE-GUP-DT-E-24-163 | 2024-06-25 | 2 | 자체 CRS 개정 후 제출 | 2024-07-14 | N/A | DE-GUP-DT-E-24-182 | 2024-07-15 | 3 | 자체 CRS 개정 후 제출 | 2024-10-13 | N/A | DE-GUP-DT-E-24-249 | 2024-10-14 | 4
| GUP | CA05 | P1 | UYC | 181774 |  | GUP-CA05-P1UYC-181774 | ADMINISTRATION BUILDING_ENLARGED PLUMBING PLAN | FI | 2022-09-30 |  | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | Admin. Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-284 | 2024-11-29 | 7 | 자체 CRS 개정 후 제출 | 2024-11-28 | N/A | DE-GUP-DT-E-22-1112 | 2022-12-16 | 0 | CRS-GUP-DHI-DT-22-1352 | 2022-12-29 | RC | DHI-GUP-DT-23-292 | 2023-03-09 | 1 | CRS-GUP-DHI-DT-23-1764 | 2023-03-22 | RC | DE-GUP-DT-E-23-441 | 2023-04-10 | 2 | CRS-GUP-DHI-DT-23-1865 | 2023-04-19 | NC | DE-GUP-DT-E-23-537 | 2023-05-09 | 3 | CRS-GUP-DHI-DT-23-1955 | 2023-05-18 | NC | DE-GUP-DT-E-23-948 | 2023-11-28 | 4 | CRS-GUP-DHI-DT-24-018 | 2024-02-21 | NC | DE-GUP-DT-E-24-182 | 2024-07-15 | 5 | 자체 CRS 개정 후 제출 | 2024-10-13 | N/A | DE-GUP-DT-E-24-249 | 2024-10-14 | 6 | 자체 CRS 개정 후 제출 | 2024-11-28 | N/A | DE-GUP-DT-E-24-284 | 2024-11-29 | 7
| GUP | CA05 | P1 | UYC | 181775 |  | GUP-CA05-P1UYC-181775 | ADMINISTRATION BUILDING_PLUMBING ISO DRAWING | FI | 2022-09-30 |  | 건축기술2팀(Arch.) | 진백석 | B |  |  |  |  | CCPP | Admin. Building | Arch. | 3 | 2025-04-01 | 2025-07-02 |  | DE-GUP-DT-E-24-284 | 2024-11-29 | 7 | 자체 CRS 개정 후 제출 | 2024-11-28 | N/A | DE-GUP-DT-E-22-1112 | 2022-12-16 | 0 | CRS-GUP-DHI-DT-22-1352 | 2022-12-29 | NC | DHI-GUP-DT-23-292 | 2023-03-09 | 1 | CRS-GUP-DHI-DT-23-1764 | 2023-03-22 | NC | DE-GUP-DT-E-23-441 | 2023-04-10 | 2 | CRS-GUP-DHI-DT-23-1865 | 2023-04-19 | NC | DE-GUP-DT-E-23-537 | 2023-05-09 | 3 | CRS-GUP-DHI-DT-23-1955 | 2023-05-18 | NC | DE-GUP-DT-E-23-948 | 2023-11-28 | 4 | CRS-GUP-DHI-DT-24-018 | 2024-02-21 | NC | DE-GUP-DT-E-24-182 | 2024-07-15 | 5 | 자체 CRS 개정 후 제출 | 2024-10-13 | N/A | DE-GUP-DT-E-24-249 | 2024-10-14 | 6 | 자체 CRS 개정 후 제출 | 2024-11-28 | N/A | DE-GUP-DT-E-24-284 | 2024-11-29 | 7
| GUP | YR02 | P1 | ZEN | 150011 |  | GUP-YR02-P1ZEN-150011 | DESIGN CRITERIA_ELECTRICAL SYSTEM | FA | 2021-09-20 | 2022-06-15 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA |  | CCPP | Plant | Elec. | 1 | 2025-06-30 |  |  | DE-GUP-DT-E-23-895 | 2023-11-09 | 2 | CRS-GUP-DHI-DT-23-1773 | 2023-03-27 | AA | DHI-GUP-DT-21-033 | 2021-09-17 | A | CRS-GUP-DHI-DT-21-027 | 2021-10-04 | RC | DHI-GUP-DT-21-085 | 2021-11-01 | B | CRS-GUP-DHI-DT-21-067 | 2021-11-16 | RC | DE-GUP-DT-E-22-261 | 2022-05-31 | C | CRS-GUP-DHI-DT-22-457 | 2022-06-21 | RC | DE-GUP-DT-E-22-355 | 2022-07-01 | D | CRS-GUP-DHI-DT-22-540 | 2022-07-24 | AC | DE-GUP-DT-E-22-585 | 2022-08-30 | 0(CP) | CRS-GUP-DHI-DT-22-776 | 2022-09-15 | RC | DE-GUP-DT-E-23-267 | 2023-03-06 | 1(CP) | CRS-GUP-DHI-DT-23-1773 | 2023-03-27 | AA | DE-GUP-DT-E-23-895 | 2023-11-09 | 2
| GUP | YR08 | P1 | ZEN | 150002 |  | GUP-YR08-P1ZEN-150002 | SYMBOL & LEGENDS_ELECTRICAL SYSTEM | FA | 2021-09-29 | 2022-08-31 | 전력기술팀(Elec.) | 정민구 |  |  | G | FA |  | CCPP | Plant | Elec. | 1 | 2025-06-30 |  |  | DE-GUP-DT-E-22-298 | 2022-06-14 | 0 | CRS-GUP-DHI-DT-22-502 | 2022-07-07 | AA | DHI-GUP-DT-21-050 | 2021-10-05 | A | CRS-GUP-DHI-DT-21-043 | 2021-10-29 | RC | DHI-GUP-DT-21-123 | 2021-11-26 | B | CRS-GUP-DHI-DT-21-094 | 2021-12-23 | AA | DE-GUP-DT-E-22-298 | 2022-06-14 | 0 | CRS-GUP-DHI-DT-22-502 | 2022-07-07 | AA
| GUP | YU01 | P1 | ZEN | 150001 |  | GUP-YU01-P1ZEN-150001 | KEY SINGLE LINE DIAGRAM | FA | 2022-01-10 | 2022-08-31 | 전력기술팀(Elec.) | 정민구 |  |  | G | FA |  | CCPP | Plant | Elec. | 1 | 2025-06-30 |  |  | DE-GUP-DT-E-23-957 | 2023-11-30 | 1 | 자체 CRS 개정 후 제출 | 2023-11-29 | N/A | DHI-GUP-DT-21-050 | 2021-10-05 | A | CRS-GUP-DHI-DT-21-043 | 2021-10-29 | RC | DHI-GUP-DT-21-123 | 2021-11-26 | B | CRS-GUP-DHI-DT-21-094 | 2021-12-23 | RC | DHI-GUP-DT-22-078 | 2022-02-18 | C | CRS-GUP-DHI-DT-22-245 | 2022-03-14 | RC | DE-GUP-DT-E-22-298 | 2022-06-14 | D | CRS-GUP-DHI-DT-22-502 | 2022-07-07 | RC | DE-GUP-DT-E-22-495 | 2022-08-12 | E | CRS-GUP-DHI-DT-22-703 | 2022-09-03 | AA | DE-GUP-DT-E-22-623 | 2022-09-05 | 0 | 자체 CRS 개정 후 제출 | 2023-11-29 | N/A | DE-GUP-DT-E-23-957 | 2023-11-30 | 1
| GUP | YL06 | P1 | ZEN | 150004 |  | GUP-YL06-P1ZEN-150004 | ELECTRICAL LOAD LIST | FA | 2022-02-09 | 2022-09-06 | 전력기술팀(Elec.) | 정민구 |  |  | G | FI |  | CCPP | Plant | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-950 | 2023-11-28 | 1 | CRS-GUP-DHI-DT-22-953 | 2022-10-22 | AA | DHI-GUP-DT-21-089 | 2021-11-03 | 0 | CRS-GUP-DHI-DT-21-073 | 2021-11-24 | RC | DHI-GUP-DT-22-129 | 2022-03-23 | B | CRS-GUP-DHI-DT-22-290 | 2022-04-17 | RC | DE-GUP-DT-E-22-386 | 2022-07-12 | C | CRS-GUP-DHI-DT-22-596 | 2022-08-13 | AC | DE-GUP-DT-E-22-726 | 2022-09-29 | 0(CP) | CRS-GUP-DHI-DT-22-953 | 2022-10-22 | AA | DE-GUP-DT-E-23-950 | 2023-11-28 | 1
| GUP | YU01 | P1 | ZEN | 150003 |  | GUP-YU01-P1ZEN-150003 | OVERALL PROTECTION AND METERING SINGLE LINE DIAGRAM | FA | 2022-02-09 | 2022-08-31 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA |  | CCPP | Plant | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-895 | 2023-11-09 | 1 | CRS-GUP-DHI-DT-22-1064 | 2022-11-19 | AA | DHI-GUP-DT-21-083 | 2021-10-29 | A | CRS-GUP-DHI-DT-21-065 | 2021-11-16 | RC | DHI-GUP-DT-22-137 | 2022-03-28 | B | CRS-GUP-DHI-DT-22-298 | 2022-04-17 | RC | DE-GUP-DT-E-22-329 | 2022-06-23 | C | CRS-GUP-DHI-DT-22-536 | 2022-07-24 | RC | DE-GUP-DT-E-22-583 | 2022-08-30 | D | CRS-GUP-DHI-DT-22-775 | 2022-09-15 | D | DE-GUP-DT-E-22-669 | 2022-09-16 | 0(CP) | CRS-GUP-DHI-DT-22-1064 | 2022-11-19 | AA | DE-GUP-DT-E-23-895 | 2023-11-09 | 1
| GUP | YF00 | P1 | ZEN | 150031 |  | GUP-YF00-P1ZEN-150031 | ELECTRICAL CONTROL LOGIC DIAGRAM_GSUT/UAT/LINE/OVERALL PROTECTION | FA | 2022-02-09 | 2022-09-08 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA |  | CCPP | Plant | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-337 | 2023-03-22 | 0 | CRS-GUP-DHI-DT-23-1637 | 2023-03-04 | AA | DHI-GUP-DT-21-140 | 2021-12-01 | A | CRS-GUP-DHI-DT-21-101 | 2021-12-27 | RC | DE-GUP-DT-E-22-770 | 2022-10-07 | B | CRS-GUP-DHI-DT-22-1115 | 2022-11-21 | RC | DE-GUP-DT-E-23-056 | 2023-01-19 | C | CRS-GUP-DHI-DT-23-1637 | 2023-03-04 | AA | DE-GUP-DT-E-23-337 | 2023-03-22 | 0
| GUP | YF00 | P1 | ZEN | 150032 |  | GUP-YF00-P1ZEN-150032 | ELECTRICAL CONTROL LOGIC DIAGRAM_MV SWITCHGEAR | FA | 2022-05-25 | 2022-09-22 | 전력기술팀(Elec.) | 정민구 | [5 empty] | CCPP | MV SWGR | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-843 | 2023-10-10 | 1 | 자체 CRS 개정 후 제출 | 2023-10-09 | N/A | DE-GUP-DT-E-22-397 | 2022-07-13 | A | CRS-GUP-DHI-DT-22-597 | 2022-08-13 | RC | DE-GUP-DT-E-22-833 | 2022-10-21 | B | CRS-GUP-DHI-DT-22-1050 | 2022-11-17 | AA | DE-GUP-DT-E-22-1044 | 2022-12-08 | 0 | 자체 CRS 개정 후 제출 | 2023-10-09 | N/A | DE-GUP-DT-E-23-843 | 2023-10-10 | 1
| GUP | YF00 | P1 | ZEN | 150033 |  | GUP-YF00-P1ZEN-150033 | ELECTRICAL CONTROL LOGIC DIAGRAM_480V SWITCHGEAR | FA | 2022-05-25 | 2022-09-22 | 전력기술팀(Elec.) | 정민구 | [5 empty] | CCPP | LV SWGR | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-004 | 2023-01-12 | 0 | CRS-GUP-DHI-DT-22-1334 | 2022-12-28 | AA | DE-GUP-DT-E-22-286 | 2022-06-10 | A | CRS-GUP-DHI-DT-22-505 | 2022-07-10 | RC | DE-GUP-DT-E-22-755 | 2022-10-04 | B | CRS-GUP-DHI-DT-22-1074 | 2022-11-19 | RC | DE-GUP-DT-E-22-1079 | 2022-12-12 | C | CRS-GUP-DHI-DT-22-1334 | 2022-12-28 | AA | DE-GUP-DT-E-23-004 | 2023-01-12 | 0
| GUP | YT10 | P1 | ZEN | 150021 |  | GUP-YT10-P1ZEN-150021 | SHORT CIRCUIT STUDY | FA | 2021-11-28 | 2022-08-31 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA |  | CCPP | Plant | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-399 | 2023-03-30 | 2 | CRS-GUP-DHI-DT-23-1772 | 2023-03-27 | AA | DHI-GUP-DT-22-012 | 2022-01-10 | A | CRS-GUP-DHI-DT-21-177 | 2022-01-31 | RC | DHI-GUP-DT-22-178 | 2022-04-18 | B | CRS-GUP-DHI-DT-22-329 | 2022-05-06 | RC | DE-GUP-DT-E-22-493 | 2022-08-11 | C | CRS-GUP-DHI-DT-22-702 | 2022-09-03 | RC | DE-GUP-DT-E-22-656 | 2022-09-14 | D | CRS-GUP-DHI-DT-22-878 | 2022-10-09 | RC | DE-GUP-DT-E-22-879 | 2022-10-28 | E | CRS-GUP-DHI-DT-22-1083 | 2022-11-19 | AC | DE-GUP-DT-E-22-1189 | 2022-12-23 | 0(CP) | CRS-GUP-DHI-DT-23-1494 | 2023-02-11 | RC | DE-GUP-DT-E-23-264 | 2023-03-06 | 1(CP) | CRS-GUP-DHI-DT-23-1772 | 2023-03-27 | AA | DE-GUP-DT-E-23-399 | 2023-03-30 | 2
| GUP | YT10 | P1 | ZEN | 150022 |  | GUP-YT10-P1ZEN-150022 | LOAD FLOW & LARGE MOTOR STARTING STUDY | FA | 2021-11-28 | 2022-08-31 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA |  | CCPP | Plant | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-852 | 2023-10-13 | 2 | CRS-GUP-DHI-DT-23-2136 | 2023-11-17 | AA | DHI-GUP-DT-22-012 | 2022-01-10 | A | CRS-GUP-DHI-DT-21-177 | 2022-01-31 | AC | DHI-GUP-DT-22-178 | 2022-04-18 | B | CRS-GUP-DHI-DT-22-329 | 2022-05-06 | RC | DE-GUP-DT-E-22-493 | 2022-08-11 | C | CRS-GUP-DHI-DT-22-702 | 2022-09-03 | RC | DE-GUP-DT-E-22-656 | 2022-09-14 | D | CRS-GUP-DHI-DT-22-878 | 2022-10-09 | RC | DE-GUP-DT-E-22-879 | 2022-10-28 | E | CRS-GUP-DHI-DT-22-1083 | 2022-11-19 | RC | DE-GUP-DT-E-22-1189 | 2022-12-23 | F | CRS-GUP-DHI-DT-23-1494 | 2023-02-11 | RC | DE-GUP-DT-E-23-264 | 2023-03-06 | G | CRS-GUP-DHI-DT-23-1772 | 2023-03-27 | AC | DE-GUP-DT-E-23-399 | 2023-03-30 | 0(CP) | CRS-GUP-DHI-DT-23-1881 | 2023-05-02 | AA | DE-GUP-DT-E-23-549 | 2023-05-12 | 1 | CRS-GUP-DHI-DT-23-2101 | 2023-08-30 | AC | DE-GUP-DT-E-23-852 | 2023-10-13 | 2 | CRS-GUP-DHI-DT-23-2136 | 2023-11-17 | AA
| GUP | YT10 | P1 | ZEN | 150023 |  | GUP-YT10-P1ZEN-150023 | PROTECTION RELAY COORDINATION STUDY - GSUT/UAT/OVERALL | FA | 2022-08-26 | 2022-12-27 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA |  | CCPP | Plant | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-724 | 2023-07-26 | 0 | CRS-GUP-DHI-DT-23-2038 | 2023-07-06 | AA | DE-GUP-DT-E-23-134 | 2023-02-07 | A | CRS-GUP-DHI-DT-23-1667 | 2023-03-10 | RC | DE-GUP-DT-E-23-620 | 2023-06-14 | B | CRS-GUP-DHI-DT-23-2038 | 2023-07-06 | AA | DE-GUP-DT-E-23-724 | 2023-07-26 | 0
| GUP | YT10 | P1 | ZEN | 150024 |  | GUP-YT10-P1ZEN-150024 | PROTECTION RELAY COORDINATION STUDY - MV SWITCHGEAR | FA | 2022-08-26 | 2022-12-27 | 전력기술팀(Elec.) | 정민구 | [5 empty] | CCPP | MV SWGR | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-722 | 2023-07-25 | 0 | CRS-GUP-DHI-DT-23-2025 | 2023-07-04 | AA | DE-GUP-DT-E-23-134 | 2023-02-07 | A | CRS-GUP-DHI-DT-23-1667 | 2023-03-10 | RC | DE-GUP-DT-E-23-619 | 2023-06-14 | B | CRS-GUP-DHI-DT-23-2025 | 2023-07-04 | AA | DE-GUP-DT-E-23-722 | 2023-07-25 | 0
| GUP | YT10 | P1 | ZEN | 150025 |  | GUP-YT10-P1ZEN-150025 | PROTECTION RELAY COORDINATION STUDY - 480V SWITCHGEAR | FA | 2022-08-26 | 2022-12-27 | 전력기술팀(Elec.) | 정민구 | [5 empty] | CCPP | LV SWGR | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-722 | 2023-07-25 | 0 | CRS-GUP-DHI-DT-23-2025 | 2023-07-04 | AA | DE-GUP-DT-E-23-141 | 2023-02-08 | A | CRS-GUP-DHI-DT-23-1663 | 2023-03-09 | RC | DE-GUP-DT-E-23-619 | 2023-06-14 | B | CRS-GUP-DHI-DT-23-2025 | 2023-07-04 | AA | DE-GUP-DT-E-23-722 | 2023-07-25 | 0
| GUP | YR02 | P1 | ZEN | 150012 |  | GUP-YR02-P1ZEN-150012 | DESIGN CRITERIA_POWER CABLE | FA | 2021-08-30 | 2022-06-30 | 전력기술팀(Elec.) | 허규범 | [5 empty] | CCPP | cable | Elec. | 1 | 2025-06-30 |  |  | DE-GUP-DT-E-22-362 | 2022-07-06 | 0 | CRS-GUP-DHI-DT-22-479 | 2022-07-03 | AA | DHI-GUP-DT-21-057 | 2021-10-07 | A | CRS-GUP-DHI-DT-21-064 | 2021-11-17 | RC | DHI-GUP-DT-21-146 | 2021-12-06 | B | CRS-GUP-DHI-DT-21-109 | 2022-01-05 | AC | DHI-GUP-DT-22-194 | 2022-04-29 | C | CRS-GUP-DHI-DT-22-359 | 2022-05-22 | AC | DE-GUP-DT-E-22-266 | 2022-06-02 | D | CRS-GUP-DHI-DT-22-479 | 2022-07-03 | AA | DE-GUP-DT-E-22-362 | 2022-07-06 | 0
| GUP | YL16 | P1 | ZEN | 152811 |  | GUP-YL16-P1ZEN-152811 | POWER CABLE SCHEDULE | FI | 2022-10-10 |  | 전력기술팀(Elec.) | 허규범 |  |  | G | FI |  | CCPP | cable | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1209 | 2023-01-02 | 0 | CRS-GUP-DHI-DT-23-1508 | 2023-02-14 | NC | DE-GUP-DT-E-22-1209 | 2023-01-02 | 0 | CRS-GUP-DHI-DT-23-1508 | 2023-02-14 | NC
| GUP | YL16 | P1 | ZEN | 152812 |  | GUP-YL16-P1ZEN-152812 | CONTROL CABLE SCHEDULE | FI | 2022-10-10 |  | 전력기술팀(Elec.) | 허규범 |  |  | G | FI |  | CCPP | cable | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-238 | 2023-02-23 | 0 | CRS-GUP-DHI-DT-23-1644 | 2023-03-04 | RC | DE-GUP-DT-E-23-238 | 2023-02-23 | 0 | CRS-GUP-DHI-DT-23-1644 | 2023-03-04 | RC
| GUP | YB03 | P1 | ZEN | 150005 |  | GUP-YB03-P1ZEN-150005 | CONTROL CABLE CONNECTION DIAGRAM | FI | 2022-12-10 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FI |  | CCPP | cable | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-062 | 2025-05-30 | 2 | CRS-GUP-DHI-DT-24-014 | 2024-02-15 | RC | DE-GUP-DT-E-23-234 | 2023-02-23 | 0 | CRS-GUP-DHI-DT-23-1643 | 2023-03-04 | RC | DE-GUP-DT-E-23-951 | 2023-11-28 | 1 | CRS-GUP-DHI-DT-24-014 | 2024-02-15 | RC | DE-GUP-DT-E-25-062 | 2025-05-30 | 2
| GUP | YR02 | P1 | ZEN | 150013 |  | GUP-YR02-P1ZEN-150013 | DESIGN CRITERIA_EARTHING & LIGHTNING SYSTEM | FA | 2021-09-15 | 2021-12-14 | 전력기술팀(Elec.) | 박경수 |  |  | G | FI |  | CCPP | Earthing & Lightning | Elec. | 1 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1206 | 2022-12-29 | 1 | CRS-GUP-DHI-DT-22-1327 | 2022-12-28 | AA | DHI-GUP-DT-21-082 | 2021-10-29 | A | CRS-GUP-DHI-DT-21-069 | 2021-11-16 | RC | DE-GUP-DT-E-22-622 | 2022-09-05 | B | CRS-GUP-DHI-DT-22-849 | 2022-09-24 | RC | DE-GUP-DT-E-22-898 | 2022-11-01 | C | CRS-GUP-DHI-DT-22-1220 | 2022-12-05 | AC | DE-GUP-DT-E-22-1057 | 2022-12-09 | 0(CP) | CRS-GUP-DHI-DT-22-1327 | 2022-12-28 | AA | DE-GUP-DT-E-22-1206 | 2022-12-29 | 1
| GUP | YE03 | P1 | BAU | 153103 |  | GUP-YE03-P1BAU-153103 | MAIN EARTHING GRID GENERAL ARRANGEMENT | FA | 2021-09-10 | 2022-04-15 | 전력기술팀(Elec.) | 박경수 | B |  | G | FI |  | CCPP | Earthing & Lightning | Elec. | 1 | 2025-06-30 |  |  | DE-GUP-DT-E-23-919 | 2023-11-20 | 1(CP) | CRS-GUP-DHI-DT-25-050 | 2025-03-19 | AA | DHI-GUP-DT-21-030 | 2021-09-17 | A | CRS-GUP-DHI-DT-21-028 | 2021-10-06 | RC | DE-GUP-DT-E-22-613 | 2022-09-02 | B | CRS-GUP-DHI-DT-22-848 | 2022-09-24 | RC | DE-GUP-DT-E-23-183 | 2023-02-16 | C | CRS-GUP-DHI-DT-23-1732 | 2023-03-17 | AC | DE-GUP-DT-E-23-337 | 2023-03-22 | 0(CP) | CRS-GUP-DHI-DT-23-1832 | 2023-04-18 | AC | DE-GUP-DT-E-23-919 | 2023-11-20 | 1(CP) | CRS-GUP-DHI-DT-25-050 | 2025-03-19 | AA
| GUP | YE04 | P1 | ZEN | 153102 |  | GUP-YE04-P1ZEN-153102 | TYPICAL INSTALLATION DRAWING_EARTHING & LIGHTNING SYSTEM | FA | 2021-09-15 | 2021-12-14 | 전력기술팀(Elec.) | 박경수 |  |  | G | FI |  | CCPP | Earthing & Lightning | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-898 | 2022-11-01 | 0 | CRS-GUP-DHI-DT-22-1149 | 2022-11-23 | AA | DHI-GUP-DT-21-030 | 2021-09-17 | A | CRS-GUP-DHI-DT-21-028 | 2021-10-06 | RC | DHI-GUP-DT-21-127 | 2021-11-29 | B | CRS-GUP-DHI-DT-21-117 | 2022-01-07 | RC | DE-GUP-DT-E-22-687 | 2022-09-21 | C | CRS-GUP-DHI-DT-22-943 | 2022-10-22 | AA | DE-GUP-DT-E-22-898 | 2022-11-01 | 0 | CRS-GUP-DHI-DT-22-1149 | 2022-11-23 | AA
| GUP | XW03 | P1 | BAU | 153104 |  | GUP-XW03-P1BAU-153104 | MAIN GRID EARTHING CALCULATION | FA | 2022-04-11 | 2022-07-10 | 전력기술팀(Elec.) | 박경수 |  |  | G | FI |  | CCPP | Earthing & Lightning | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-337 | 2023-03-22 | 0 | CRS-GUP-DHI-DT-23-1728 | 2023-03-17 | AA | DE-GUP-DT-E-22-878 | 2022-10-28 | A | CRS-GUP-DHI-DT-22-1054 | 2022-11-17 | RC | DE-GUP-DT-E-22-989 | 2022-11-25 | B | CRS-GUP-DHI-DT-22-1303 | 2022-12-21 | RC | DE-GUP-DT-E-23-156 | 2023-02-10 | C | CRS-GUP-DHI-DT-23-1728 | 2023-03-17 | AA | DE-GUP-DT-E-23-337 | 2023-03-22 | 0
| GUP | YR02 | P1 | ZEN | 150014 |  | GUP-YR02-P1ZEN-150014 | DESIGN CRITERIA_LIGHTING & SMALL POWER SYSTEM | FA | 2021-09-15 | 2021-12-14 | 전력기술팀(Elec.) | 고승호 | [5 empty] | CCPP | Lighting & Small Power | Elec. | 1 | 2025-06-30 |  |  | DE-GUP-DT-E-22-336 | 2022-06-24 | 0 | CRS-GUP-DHI-DT-21-139 | 2022-01-11 | AA | DHI-GUP-DT-21-061 | 2021-10-14 | A | CRS-GUP-DHI-DT-21-059 | 2021-11-08 | RC | DHI-GUP-DT-21-189 | 2021-12-20 | B | CRS-GUP-DHI-DT-21-139 | 2022-01-11 | AA | DE-GUP-DT-E-22-336 | 2022-06-24 | 0
| GUP | YQ01 | P1 | ZEN | 153202 |  | GUP-YQ01-P1ZEN-153202 | TYPICAL INSTALLATION DRAWING_LIGHTING & SMALL POWER SYSTEM | FA | 2021-09-30 | 2021-12-29 | 전력기술팀(Elec.) | 고승호 | [5 empty] | CCPP | Lighting & Small Power | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-994 | 2023-12-14 | 1 | 자체 CRS 개정 후 제출 | 2023-12-13 | N/A | DHI-GUP-DT-21-061 | 2021-10-14 | A | CRS-GUP-DHI-DT-21-059 | 2021-11-08 | AA | DE-GUP-DT-E-22-328 | 2022-06-22 | B | CRS-GUP-DHI-DT-22-535 | 2022-07-24 | AA | DE-GUP-DT-E-22-462 | 2022-07-27 | 0 | 자체 CRS 개정 후 제출 | 2023-12-13 | N/A | DE-GUP-DT-E-23-994 | 2023-12-14 | 1
| GUP | YR02 | P1 | ZEN | 150015 |  | GUP-YR02-P1ZEN-150015 | DESIGN CRITERIA_RACEWAY SYSTEM | FA | 2021-08-30 | 2022-06-15 | 전력기술팀(Elec.) | 허규범 |  |  | G | FI |  | CCPP | Raceway | Elec. | 1 | 2025-06-30 |  |  | DE-GUP-DT-E-22-362 | 2022-07-06 | 0 | CRS-GUP-DHI-DT-22-479 | 2022-07-03 | AA | DHI-GUP-DT-21-058 | 2021-10-07 | A | CRS-GUP-DHI-DT-21-064 | 2021-11-17 | RC | DHI-GUP-DT-21-147 | 2021-12-06 | B | CRS-GUP-DHI-DT-21-109 | 2022-01-05 | RC | DE-GUP-DT-E-22-266 | 2022-06-02 | C | CRS-GUP-DHI-DT-22-479 | 2022-07-03 | AA | DE-GUP-DT-E-22-362 | 2022-07-06 | 0
| GUP | YQ02 | P1 | ZEN | 152902 |  | GUP-YQ02-P1ZEN-152902 | TYPICAL INSTALLATION DRAWING_RACEWAY SYSTEM | FA | 2021-08-07 | 2022-06-15 | 전력기술팀(Elec.) | 허규범 | [5 empty] | CCPP | Raceway | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-312 | 2022-06-17 | 0 | CRS-GUP-DHI-DT-21-064 | 2021-11-17 | AA | DHI-GUP-DT-21-037 | 2021-09-28 | A | CRS-GUP-DHI-DT-21-064 | 2021-11-17 | AA | DE-GUP-DT-E-22-312 | 2022-06-17 | 0
| GUP | YD16 | P1 | ZEN | 153011 |  | GUP-YD16-P1ZEN-153011 | MAIN CABLE ROUTE PLAN OVERALL | FA | 2021-08-07 | 2022-07-10 | 전력기술팀(Elec.) | 허규범 |  |  | G | FI |  | CCPP | Raceway | Elec. | 1 | 2025-06-30 |  |  | DE-GUP-DT-E-24-031 | 2024-02-01 | 1 | 자체 CRS 개정 후 제출 | 2024-01-31 | N/A | DHI-GUP-DT-21-036 | 2021-09-28 | A | CRS-GUP-DHI-DT-21-064 | 2021-11-17 | AA | DHI-GUP-DT-21-175 | 2021-12-15 | B | CRS-GUP-DHI-DT-21-149 | 2022-01-12 | NC | DE-GUP-DT-E-22-474 | 2022-07-29 | C | CRS-GUP-DHI-DT-22-641 | 2022-08-20 | RC | DE-GUP-DT-E-22-782 | 2022-10-11 | D | CRS-GUP-DHI-DT-22-987 | 2022-11-08 | RC | DE-GUP-DT-E-22-1209 | 2023-01-02 | E | CRS-GUP-DHI-DT-23-1508 | 2023-02-14 | AA | DE-GUP-DT-E-23-217 | 2023-02-21 | 0 | 자체 CRS 개정 후 제출 | 2024-01-31 | N/A | DE-GUP-DT-E-24-031 | 2024-02-01 | 1
| GUP | YR07 | P1 | ZEN | 150016 |  | GUP-YR07-P1ZEN-150016 | DESIGN CRITERIA_COMMUNICATION SYSTEM | FA | 2021-09-15 | 2022-02-18 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA |  | CCPP | Communication | Elec. | 1 | 2025-06-30 |  |  | DE-GUP-DT-E-23-339 | 2023-03-22 | 0 | CRS-GUP-DHI-DT-23-1740 | 2023-03-17 | AA | DHI-GUP-DT-21-045 | 2021-09-30 | A | CRS-GUP-DHI-DT-21-064 | 2021-11-17 | RC | DE-GUP-DT-E-22-410 | 2022-07-18 | B | CRS-GUP-DHI-DT-22-599 | 2022-08-13 | RC | DE-GUP-DT-E-23-240 | 2023-02-23 | C | CRS-GUP-DHI-DT-23-1740 | 2023-03-17 | AA | DE-GUP-DT-E-23-339 | 2023-03-22 | 0
| GUP | YQ03 | P1 | CYA | 153302 |  | GUP-YQ03-P1CYA-153302 | TYPICAL INSTALLATION DRAWING_COMMUNICATION SYSTEM | FA | 2021-09-30 | 2022-02-25 | 전력기술팀(Elec.) | 박경수 |  |  | G | FI |  | CCPP | Communication | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-977 | 2023-12-06 | 1 | N/A-자체 CRS 개정 | 2023-12-05 | N/A | DHI-GUP-DT-21-048 | 2021-10-01 | A | CRS-GUP-DHI-DT-21-064 | 2021-11-17 | RC | DE-GUP-DT-E-22-410 | 2022-07-18 | B | CRS-GUP-DHI-DT-22-599 | 2022-08-13 | RC | DE-GUP-DT-E-23-240 | 2023-02-23 | C | CRS-GUP-DHI-DT-23-1740 | 2023-03-17 | AA | DE-GUP-DT-E-23-339 | 2023-03-22 | 0 | N/A-자체 CRS 개정 | 2023-12-05 | N/A | DE-GUP-DT-E-23-977 | 2023-12-06 | 1
| GUP | YK08 | P1 | CYA | 153303 |  | GUP-YK08-P1CYA-153303 | CONFIGURATION DIAGRAM_COMMUNICATION SYSTEM | FA | 2021-09-30 | 2022-02-25 | 전력기술팀(Elec.) | 박경수 | [5 empty] | CCPP | Communication | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-977 | 2023-12-06 | 1 | N/A-자체 CRS 개정 | 2023-12-05 | N/A | DHI-GUP-DT-21-047 | 2021-10-01 | A | CRS-GUP-DHI-DT-21-064 | 2021-11-17 | RC | DE-GUP-DT-E-22-410 | 2022-07-18 | B | CRS-GUP-DHI-DT-22-599 | 2022-08-13 | RC | DE-GUP-DT-E-23-240 | 2023-02-23 | C | CRS-GUP-DHI-DT-23-1740 | 2023-03-17 | AA | DE-GUP-DT-E-23-339 | 2023-03-22 | 0 | N/A-자체 CRS 개정 | 2023-12-05 | N/A | DE-GUP-DT-E-23-977 | 2023-12-06 | 1
| GUP | YR02 | P1 | ZEN | 153001 |  | GUP-YR02-P1ZEN-153001 | TECHNICAL SPECIFICATION_EMBEDDED CONDUIT & ACCESSORIES | FI | 2022-04-11 |  | 전력기술팀(Elec.) | 허규범 |  |  |  |  | CONDUIT | CCPP | Raceway | Elec. | 2 | 2025-06-30 |  |  | DHI-GUP-DT-21-056 | 2021-10-07 | 1 | CRS-GUP-DHI-DT-21-044 | 2021-10-29 | NC | DHI-GUP-DT-21-011 | 2021-09-07 | 0 | CRS-GUP-DHI-DT-21-017 | 2021-09-29 | NC | DHI-GUP-DT-21-056 | 2021-10-07 | 1 | CRS-GUP-DHI-DT-21-044 | 2021-10-29 | NC
| GUP | YR02 | P1 | AE | 151001 |  | GUP-YR02-P1AE-151001 | TECHNICAL SPECIFICATION_115kV AIS HV EQUIPMENT | FA | 2021-11-30 | 2022-05-13 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | AIS | CCPP | AIS | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-822 | 2022-10-18 | 1 | CRS-GUP-DHI-DT-22-1141 | 2022-11-23 | AA | DHI-GUP-DT-21-180 | 2021-12-16 | A | CRS-GUP-DHI-DT-21-131 | 2022-01-11 | RC | DHI-GUP-DT-22-206 | 2022-05-04 | B | CRS-GUP-DHI-DT-22-381 | 2022-05-31 | RC | DE-GUP-DT-E-22-402 | 2022-07-15 | C | CRS-GUP-DHI-DT-22-581 | 2022-08-08 | AA | DE-GUP-DT-E-22-520 | 2022-08-19 | 0 | CRS-GUP-DHI-DT-22-833 | 2022-09-23 | AC | DE-GUP-DT-E-22-822 | 2022-10-18 | 1 | CRS-GUP-DHI-DT-22-1141 | 2022-11-23 | AA
| GUP | YR02 | P1 | AE | 151002 |  | GUP-YR02-P1AE-151002 | TECHNICAL SPECIFICATION_115kV AIS CONTROL & PROTECTION SYSTEM | FA | 2022-02-12 | 2022-05-23 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | AIS | CCPP | AIS | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-062 | 2023-01-20 | 1 | CRS-GUP-DHI-DT-22-1075 | 2022-11-19 | AA | DHI-GUP-DT-22-140 | 2022-03-29 | A | CRS-GUP-DHI-DT-22-307 | 2022-04-23 | RC | DE-GUP-DT-E-22-355 | 2022-07-01 | B | CRS-GUP-DHI-DT-22-540 | 2022-07-24 | RC | DE-GUP-DT-E-22-479 | 2022-07-29 | C | CRS-GUP-DHI-DT-22-814 | 2022-09-20 | RC | DE-GUP-DT-E-22-762 | 2022-10-06 | D | CRS-GUP-DHI-DT-22-1075 | 2022-11-19 | AA | DE-GUP-DT-E-22-1022 | 2022-12-01 | 0 | N/A-자체 CRS 개정 | N/A | N/A | DE-GUP-DT-E-23-062 | 2023-01-20 | 1
| GUP | YR02 | P1 | AE | 151003 |  | GUP-YR02-P1AE-151003 | TECHNICAL SPECIFICATION_115kV AIS F/O MATERIALS | FI | 2023-02-06 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FI | AIS | CCPP | AIS | Elec. |  | 2025-06-30 |  |  | DE-GUP-DT-E-23-445 | 2023-04-11 | 2 | CRS-GUP-DHI-DT-23-2104 | 2023-09-13 | NC | DE-GUP-DT-E-23-100 | 2023-02-01 | 0 | CRS-GUP-DHI-DT-23-1575 | 2023-02-23 | RC | DE-GUP-DT-E-23-300 | 2023-03-10 | 1 | CRS-GUP-DHI-DT-23-1794 | 2023-04-04 | RC | DE-GUP-DT-E-23-445 | 2023-04-11 | 2 | CRS-GUP-DHI-DT-23-2104 | 2023-09-13 | NC
| GUP | YR02 | P1 | AE | 151004 |  | GUP-YR02-P1AE-151004 | TECHNICAL SPECIFICATION_115kV AIS MISCELLANEOUS ITEMS | FA | 2022-03-14 | 2022-05-13 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | AIS | CCPP | AIS | Elec. |  | 2025-06-30 |  |  | DE-GUP-DT-E-22-973 | 2022-11-23 | 0 | CRS-GUP-DHI-DT-22-1226 | 2022-12-13 | AA | DHI-GUP-DT-22-140 | 2022-03-29 | A | CRS-GUP-DHI-DT-22-307 | 2022-04-23 | RC | DE-GUP-DT-E-22-245 | 2022-05-24 | B | CRS-GUP-DHI-DT-22-418 | 2022-06-13 | RC | DE-GUP-DT-E-22-343 | 2022-06-28 | C | CRS-GUP-DHI-DT-22-537 | 2022-07-26 | AC | DE-GUP-DT-E-22-473 | 2022-07-29 | D | CRS-GUP-DHI-DT-22-640 | 2022-08-20 | RC | DE-GUP-DT-E-22-622 | 2022-09-05 | E | CRS-GUP-DHI-DT-22-849 | 2022-09-24 | RC | DE-GUP-DT-E-22-762 | 2022-10-06 | F | CRS-GUP-DHI-DT-22-1075 | 2022-11-19 | AA | DE-GUP-DT-E-22-973 | 2022-11-23 | 0 | CRS-GUP-DHI-DT-22-1226 | 2022-12-13 | AA
| GUP | YR02 | P1 | AE | 151005 |  | GUP-YR02-P1AE-151005 | TECHNICAL SPECIFICATION_115kV AIS PHYSICAL ITEMS | FI | 2022-12-16 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FI | AIS | CCPP | AIS | Elec. |  | 2025-06-30 |  |  | DE-GUP-DT-E-23-084 | 2023-01-27 | 1 | CRS-GUP-DHI-DT-23-1588 | 2023-02-28 | NC | DE-GUP-DT-E-22-1086 | 2022-12-14 | 0 | CRS-GUP-DHI-DT-22-1336 | 2022-12-28 | RC | DE-GUP-DT-E-23-084 | 2023-01-27 | 1 | CRS-GUP-DHI-DT-23-1588 | 2023-02-28 | NC
| GUP | YF00 | P1 | ZEN | 151006 |  | GUP-YF00-P1ZEN-151006 | ELECTRICAL CONTROL LOGIC DIAGRAM_115kV AIS | FA | 2022-02-19 | 2022-05-13 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | AIS | CCPP | AIS | Elec. |  | 2025-06-30 |  |  | DE-GUP-DT-E-22-1155 | 2022-12-22 | 1 | CRS-GUP-DHI-DT-22-1147 | 2022-11-23 | AA | DHI-GUP-DT-22-175 | 2022-04-14 | A | CRS-GUP-DHI-DT-22-332 | 2022-05-16 | RC | DE-GUP-DT-E-22-323 | 2022-06-21 | B | CRS-GUP-DHI-DT-22-516 | 2022-07-12 | RC | DE-GUP-DT-E-22-500 | 2022-08-12 | C | CRS-GUP-DHI-DT-22-704 | 2022-09-03 | RC | DE-GUP-DT-E-22-663 | 2022-09-14 | E | CRS-GUP-DHI-DT-22-900 | 2022-10-12 | AA | DE-GUP-DT-E-22-885 | 2022-10-31 | 0 | CRS-GUP-DHI-DT-22-1147 | 2022-11-23 | AA | DE-GUP-DT-E-22-1155 | 2022-12-22 | 1
| GUP | YT10 | P1 | ZEN | 151007 |  | GUP-YT10-P1ZEN-151007 | PROTECTION RELAY COORDINATION STUDY_115kV AIS | FA | 2022-07-09 | 2022-09-07 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | AIS | CCPP | AIS | Elec. |  | 2025-06-30 |  |  | DE-GUP-DT-E-23-350 | 2023-03-23 | 0 | CRS-GUP-DHI-DT-23-1746 | 2023-03-17 | AA | DE-GUP-DT-E-22-889 | 2022-10-31 | A | CRS-GUP-DHI-DT-22-1219 | 2022-12-05 | RC | DE-GUP-DT-E-23-258 | 2023-02-28 | B | CRS-GUP-DHI-DT-23-1746 | 2023-03-17 | AA | DE-GUP-DT-E-23-350 | 2023-03-23 | 0
| GUP | YL01 | P1 | ZEN | 151009 |  | GUP-YL01-P1ZEN-151009 | IO LIST_115kV AIS | FI | 2023-05-31 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FI | AIS | CCPP | AIS | Elec. |  | 2025-06-30 |  |  | DE-GUP-DT-E-24-010 | 2024-01-15 | 1 | CRS-GUP-DHI-DT-24-016 | 2024-02-21 | NC | DE-GUP-DT-E-23-575 | 2023-05-23 | 0 | CRS-GUP-DHI-DT-23-2019 | 2023-06-22 | RC | DE-GUP-DT-E-24-010 | 2024-01-15 | 1 | CRS-GUP-DHI-DT-24-016 | 2024-02-21 | NC
| GUP | YR02 | P1 | ZEN | 151010 |  | GUP-YR02-P1ZEN-151010 | DESIGN CRITERIA_115kV AIS | FA | 2022-01-20 | 2022-05-13 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | AIS | CCPP | AIS | Elec. |  | 2025-06-30 |  |  | DE-GUP-DT-E-22-945 | 2022-11-15 | 0 | CRS-GUP-DHI-DT-22-1238 | 2022-12-13 | AA | DHI-GUP-DT-22-042 | 2022-02-09 | A | CRS-GUP-DHI-DT-22-204 | 2022-02-20 | RC | DE-GUP-DT-E-22-236 | 2022-05-20 | B | CRS-GUP-DHI-DT-22-413 | 2022-06-13 | RC | DE-GUP-DT-E-22-426 | 2022-07-20 | C | CRS-GUP-DHI-DT-22-590 | 2022-08-08 | RC | DE-GUP-DT-E-22-622 | 2022-09-05 | D | CRS-GUP-DHI-DT-22-849 | 2022-09-24 | RC | DE-GUP-DT-E-22-762 | 2022-10-06 | E | CRS-GUP-DHI-DT-22-958 | 2022-11-03 | AA | DE-GUP-DT-E-22-945 | 2022-11-15 | 0 | CRS-GUP-DHI-DT-22-1238 | 2022-12-13 | AA
| GUP | YU02 | P1 | AE | 151011 |  | GUP-YU02-P1AE-151011 | OVERALL SINGLE LINE DIAGRAM_115kV AIS SUBSTATION | FA | 2021-11-30 | 2022-05-13 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | AIS | CCPP | AIS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1130 | 2022-12-20 | 1 | CRS-GUP-DHI-DT-22-1134 | 2022-11-23 | AA | DHI-GUP-DT-21-180 | 2021-12-16 | A | CRS-GUP-DHI-DT-21-131 | 2022-01-11 | RC | DHI-GUP-DT-22-206 | 2022-05-04 | B | CRS-GUP-DHI-DT-22-381 | 2022-05-31 | RC | DE-GUP-DT-E-22-314 | 2022-06-17 | C | CRS-GUP-DHI-DT-22-510 | 2022-07-11 | RC | DE-GUP-DT-E-22-455 | 2022-07-26 | D | CRS-GUP-DHI-DT-22-701 | 2022-09-03 | RC | DE-GUP-DT-E-22-672 | 2022-09-16 | E | CRS-GUP-DHI-DT-22-885 | 2022-10-10 | AA | DE-GUP-DT-E-22-792 | 2022-10-12 | 0 | CRS-GUP-DHI-DT-22-1134 | 2022-11-23 | AA | DE-GUP-DT-E-22-1130 | 2022-12-20 | 1
| GUP | YU02 | P1 | AE | 151013 |  | GUP-YU02-P1AE-151013 | SINGLE LINE DIAGRAM_115kV AIS LVAC SYSTEM | FA | 2022-02-12 | 2022-05-13 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | AIS | CCPP | AIS | Elec. |  | 2025-06-30 |  |  | DE-GUP-DT-E-23-890 | 2023-11-09 | 1 | CRS-GUP-DHI-DT-22-1075 | 2022-11-19 | AA | DHI-GUP-DT-22-177 | 2022-04-15 | A | CRS-GUP-DHI-DT-22-334 | 2022-05-16 | RC | DE-GUP-DT-E-22-349 | 2022-06-29 | B | CRS-GUP-DHI-DT-22-539 | 2022-07-24 | RC | DE-GUP-DT-E-22-481 | 2022-07-29 | C | CRS-GUP-DHI-DT-22-643 | 2022-08-20 | RC | DE-GUP-DT-E-22-631 | 2022-09-07 | D | CRS-GUP-DHI-DT-22-852 | 2022-09-24 | AA | DE-GUP-DT-E-22-762 | 2022-10-06 | 0 | CRS-GUP-DHI-DT-22-1075 | 2022-11-19 | AA | DE-GUP-DT-E-23-890 | 2023-11-09 | 1
| GUP | YU02 | P1 | AE | 151014 |  | GUP-YU02-P1AE-151014 | SINGLE LINE DIAGRAM_115kV AIS DC SYSTEM SYSTEM | FA | 2022-02-12 | 2022-05-13 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | AIS | CCPP | AIS | Elec. |  | 2025-06-30 |  |  | DE-GUP-DT-E-22-1130 | 2022-12-20 | 1 | CRS-GUP-DHI-DT-22-1141 | 2022-11-23 | AA | DHI-GUP-DT-22-177 | 2022-04-15 | A | CRS-GUP-DHI-DT-22-334 | 2022-05-16 | RC | DE-GUP-DT-E-22-349 | 2022-06-29 | B | CRS-GUP-DHI-DT-22-539 | 2022-07-24 | AC | DE-GUP-DT-E-22-487 | 2022-08-08 | C | CRS-GUP-DHI-DT-22-707 | 2022-09-05 | RC | DE-GUP-DT-E-22-672 | 2022-09-16 | D | CRS-GUP-DHI-DT-22-885 | 2022-10-10 | AC | DE-GUP-DT-E-22-822 | 2022-10-18 | 0(CP) | CRS-GUP-DHI-DT-22-1141 | 2022-11-23 | AA | DE-GUP-DT-E-22-1130 | 2022-12-20 | 1
| GUP | YU02 | P1 | AE | 151015 |  | GUP-YU02-P1AE-151015 | SUBSTATION AUTOMATION SYSTEM CONFIGURATION | FA | 2022-01-29 | 2022-06-21 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | AIS | CCPP | AIS | Elec. |  | 2025-06-30 |  |  | DE-GUP-DT-E-23-926 | 2023-11-21 | 1 | CRS-GUP-DHI-DT-22-1239 | 2022-12-13 | AA | DHI-GUP-DT-22-180 | 2022-04-20 | A | CRS-GUP-DHI-DT-21-131 | 2022-01-11 | RC | DHI-GUP-DT-22-222 | 2022-05-17 | B | CRS-GUP-DHI-DT-22-401 | 2022-06-08 | RC | DE-GUP-DT-E-22-364 | 2022-07-07 | C | CRS-GUP-DHI-DT-22-595 | 2022-08-13 | RC | DE-GUP-DT-E-22-622 | 2022-09-05 | D | CRS-GUP-DHI-DT-22-849 | 2022-09-24 | RC | DE-GUP-DT-E-22-774 | 2022-10-07 | E | CRS-GUP-DHI-DT-22-959 | 2022-11-03 | AA | DE-GUP-DT-E-22-949 | 2022-11-17 | 0 | CRS-GUP-DHI-DT-22-1239 | 2022-12-13 | AA | DE-GUP-DT-E-23-926 | 2023-11-21 | 1
| GUP | YT10 | P1 | ZEN | 151016 |  | GUP-YT10-P1ZEN-151016 | CT & VT CALCULATION_115kV AIS | FA | 2022-02-04 | 2022-05-13 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | AIS | CCPP | AIS | Elec. |  | 2025-06-30 |  |  | DE-GUP-DT-E-22-622 | 2022-09-05 | 0 | CRS-GUP-DHI-DT-22-849 | 2022-09-24 | AA | DHI-GUP-DT-22-183 | 2022-04-20 | A | CRS-GUP-DHI-DT-22-336 | 2022-05-16 | RC | DE-GUP-DT-E-22-299 | 2022-06-14 | B | CRS-GUP-DHI-DT-22-503 | 2022-07-07 | RC | DE-GUP-DT-E-22-444 | 2022-07-26 | C | CRS-GUP-DHI-DT-22-700 | 2022-09-03 | AA | DE-GUP-DT-E-22-622 | 2022-09-05 | 0 | CRS-GUP-DHI-DT-22-849 | 2022-09-24 | AA
| GUP | YT10 | P1 | ZEN | 151017 |  | GUP-YT10-P1ZEN-151017 | SIZING CALCULATION_DC SYSTEM_115kV AIS | FA | 2022-02-19 | 2022-05-13 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | AIS | CCPP | AIS | Elec. |  | 2025-06-30 |  |  | DE-GUP-DT-E-22-672 | 2022-09-16 | 1 | CRS-GUP-DHI-DT-22-885 | 2022-10-10 | AA | DHI-GUP-DT-22-177 | 2022-04-15 | A | CRS-GUP-DHI-DT-22-334 | 2022-05-16 | RC | DE-GUP-DT-E-22-349 | 2022-06-29 | B | CRS-GUP-DHI-DT-22-539 | 2022-07-24 | AA | DE-GUP-DT-E-22-455 | 2022-07-26 | 0 | CRS-GUP-DHI-DT-22-701 | 2022-09-03 | RC | DE-GUP-DT-E-22-672 | 2022-09-16 | 1 | CRS-GUP-DHI-DT-22-885 | 2022-10-10 | AA
| GUP | YT10 | P1 | ZEN | 151018 |  | GUP-YT10-P1ZEN-151018 | LOADING CALCULATION_115kV AIS SWITCHYARD | FA | 2022-01-23 | 2022-05-13 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | AIS | CCPP | AIS | Elec. |  | 2025-06-30 |  |  | DE-GUP-DT-E-22-854 | 2022-10-25 | 1 | CRS-GUP-DHI-DT-22-1144 | 2022-11-23 | AA | DHI-GUP-DT-22-042 | 2022-02-09 | A | CRS-GUP-DHI-DT-22-204 | 2022-02-20 | RC | DHI-GUP-DT-22-220 | 2022-05-13 | B | CRS-GUP-DHI-DT-22-400 | 2022-06-07 | RC | DE-GUP-DT-E-22-343 | 2022-06-28 | C | CRS-GUP-DHI-DT-22-537 | 2022-07-24 | RC | DE-GUP-DT-E-22-514 | 2022-08-18 | D | CRS-GUP-DHI-DT-22-705 | 2022-09-03 | AA | DE-GUP-DT-E-22-663 | 2022-09-14 | 0 | N/A | N/A | N/A | DE-GUP-DT-E-22-854 | 2022-10-25 | 1 | CRS-GUP-DHI-DT-22-1144 | 2022-11-23 | AA
| GUP | YD00 | P1 | AE | 151021 |  | GUP-YD00-P1AE-151021 | OUTLINE DRAWING_115kV AIS HV EQUIPMENT | FI | 2021-11-30 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | AIS | CCPP | AIS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-520 | 2022-08-19 | 3 | CRS-GUP-DHI-DT-22-833 | 2022-09-23 | NC | DHI-GUP-DT-21-180 | 2021-12-16 | 0 | CRS-GUP-DHI-DT-21-131 | 2022-01-11 | RC | DHI-GUP-DT-22-214 | 2022-05-12 | 1 | CRS-GUP-DHI-DT-22-396 | 2022-06-07 | RC | DE-GUP-DT-E-22-402 | 2022-07-15 | 2 | CRS-GUP-DHI-DT-22-598 | 2022-08-13 | RC | DE-GUP-DT-E-22-520 | 2022-08-19 | 3 | CRS-GUP-DHI-DT-22-833 | 2022-09-23 | NC
| GUP | YD00 | P1 | AE | 151022 |  | GUP-YD00-P1AE-151022 | OUTLINE DRAWING_115kV AIS CONTROL & PROTECTION SYSTEM | FI | 2022-01-28 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | AIS | CCPP | AIS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-890 | 2023-11-09 | 4 | CRS-GUP-DHI-DT-23-1578 | 2023-02-23 | NC | DHI-GUP-DT-22-140 | 2022-03-29 | 0 | CRS-GUP-DHI-DT-22-307 | 2022-04-23 | RC | DE-GUP-DT-E-22-374 | 2022-07-08 | 1 | CRS-GUP-DHI-DT-22-821 | 2022-09-22 | RC | DE-GUP-DT-E-22-774 | 2022-10-07 | 2 | N/A | N/A | N/A | DE-GUP-DT-E-23-154 | 2023-02-10 | 3 | CRS-GUP-DHI-DT-23-1578 | 2023-02-23 | NC | DE-GUP-DT-E-23-890 | 2023-11-09 | 4
| GUP | YD00 | P1 | AE | 151023 |  | GUP-YD00-P1AE-151023 | OUTLINE DRAWING_115kV AIS LVAC SYSTEM | FI | 2022-07-18 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | AIS | CCPP | AIS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1130 | 2022-12-20 | 2 | CRS-GUP-DHI-DT-23-1502 | 2023-02-14 | NC | DE-GUP-DT-E-22-406 | 2022-07-15 | 0 | CRS-GUP-DHI-DT-22-812 | 2022-09-20 | RC | DE-GUP-DT-E-22-822 | 2022-10-18 | 1 | CRS-GUP-DHI-DT-22-961 | 2022-11-03 | RC | DE-GUP-DT-E-22-1130 | 2022-12-20 | 2 | CRS-GUP-DHI-DT-23-1502 | 2023-02-14 | NC
| GUP | YD00 | P1 | AE | 151024 |  | GUP-YD00-P1AE-151024 | OUTLINE DRAWING_115kV AIS DC & AC INVERTER SYSTEM | FI | 2022-07-18 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | AIS | CCPP | AIS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1083 | 2022-12-13 | 2 | CRS-GUP-DHI-DT-22-1392 | 2023-01-05 | NC | DE-GUP-DT-E-22-406 | 2022-07-15 | 0 | CRS-GUP-DHI-DT-22-812 | 2022-09-20 | RC | DE-GUP-DT-E-22-822 | 2022-10-18 | 1 | CRS-GUP-DHI-DT-22-961 | 2022-11-03 | RC | DE-GUP-DT-E-22-1083 | 2022-12-13 | 2 | CRS-GUP-DHI-DT-22-1392 | 2023-01-05 | NC
| GUP | YF02 | P1 | AE | 151031 |  | GUP-YF02-P1AE-151031 | SCHEMATIC DIAGRAM_115kV AIS HV EQUIPMENT | FA | 2022-02-04 | 2022-05-15 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | AIS | CCPP | AIS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-084 | 2023-01-27 | 1 | CRS-GUP-DHI-DT-22-1077 | 2022-11-19 | AA | DHI-GUP-DT-22-135 | 2022-03-25 | A | CRS-GUP-DHI-DT-22-296 | 2022-04-17 | RC | DE-GUP-DT-E-22-402 | 2022-07-15 | B | CRS-GUP-DHI-DT-22-581 | 2022-08-08 | RC | DE-GUP-DT-E-22-536 | 2022-08-23 | C | CRS-GUP-DHI-DT-22-760 | 2022-09-14 | AC | DE-GUP-DT-E-22-840 | 2022-10-21 | 0(CP) | CRS-GUP-DHI-DT-22-1077 | 2022-11-19 | AA | DE-GUP-DT-E-23-084 | 2023-01-27 | 1
| GUP | YF02 | P1 | AE | 151032 |  | GUP-YF02-P1AE-151032 | SCHEMATIC DIAGRAM_115kV AIS CONTROL & PROTECTION SYSTEM | FA | 2022-03-06 | 2022-06-14 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | AIS | CCPP | AIS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-890 | 2023-11-09 | 2 | CRS-GUP-DHI-DT-23-1581 | 2023-02-25 | AA | DE-GUP-DT-E-22-416 | 2022-07-19 | A | CRS-GUP-DHI-DT-22-813 | 2022-09-20 | RC | DE-GUP-DT-E-22-840 | 2022-10-21 | B | CRS-GUP-DHI-DT-22-1077 | 2022-11-19 | AA | DE-GUP-DT-E-22-1205 | 2022-12-28 | 0 | CRS-GUP-DHI-DT-22-1379 | 2022-12-31 | RC | DE-GUP-DT-E-23-062 | 2023-01-20 | 1 | CRS-GUP-DHI-DT-23-1581 | 2023-02-25 | AA | DE-GUP-DT-E-23-890 | 2023-11-09 | 2
| GUP | YF02 | P1 | AE | 151033 |  | GUP-YF02-P1AE-151033 | SCHEMATIC DIAGRAM_115kV AIS LVAC SYSTEM | FI | 2022-07-18 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | AIS | CCPP | AIS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-890 | 2023-11-09 | 2 | CRS-GUP-DHI-DT-22-852 | 2022-09-24 | NC | DE-GUP-DT-E-22-481 | 2022-07-29 | A | CRS-GUP-DHI-DT-22-643 | 2022-08-20 | RC | DE-GUP-DT-E-22-631 | 2022-09-07 | 1 | CRS-GUP-DHI-DT-22-852 | 2022-09-24 | NC | DE-GUP-DT-E-23-890 | 2023-11-09 | 2
| GUP | YF02 | P1 | AE | 151034 |  | GUP-YF02-P1AE-151034 | SCHEMATIC DIAGRAM_115kV AIS DC & AC INVERTER SYSTEM | FI | 2022-07-18 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | AIS | CCPP | AIS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-672 | 2022-09-16 | 1 | CRS-GUP-DHI-DT-22-885 | 2022-10-10 | NC | DE-GUP-DT-E-22-487 | 2022-08-08 | A | CRS-GUP-DHI-DT-22-707 | 2022-09-05 | RC | DE-GUP-DT-E-22-672 | 2022-09-16 | 1 | CRS-GUP-DHI-DT-22-885 | 2022-10-10 | NC
| GUP | YD00 | P1 | AE | 151041 |  | GUP-YD00-P1AE-151041 | LAYOUT DRAWING_115kV AIS SWITCHYARD | FA | 2021-11-30 | 2022-05-13 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | AIS | CCPP | AIS | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-885 | 2022-10-31 | 0 | CRS-GUP-DHI-DT-22-1147 | 2022-11-23 | AA | DHI-GUP-DT-21-180 | 2021-12-16 | A | CRS-GUP-DHI-DT-21-131 | 2022-01-11 | RC | DHI-GUP-DT-22-206 | 2022-05-04 | B | CRS-GUP-DHI-DT-22-381 | 2022-05-31 | RC | DE-GUP-DT-E-22-307 | 2022-06-16 | C | CRS-GUP-DHI-DT-22-506 | 2022-07-10 | RC | DE-GUP-DT-E-22-402 | 2022-07-15 | D | CRS-GUP-DHI-DT-22-581 | 2022-08-08 | RC | DE-GUP-DT-E-22-514 | 2022-08-18 | E | CRS-GUP-DHI-DT-22-705 | 2022-09-03 | RC | DE-GUP-DT-E-22-663 | 2022-09-14 | F | CRS-GUP-DHI-DT-22-900 | 2022-10-12 | AA | DE-GUP-DT-E-22-885 | 2022-10-31 | 0 | CRS-GUP-DHI-DT-22-1147 | 2022-11-23 | AA
| GUP | YD00 | P1 | AE | 151043 |  | GUP-YD00-P1AE-151043 | FOUNDATION DRAWING_115kV AIS SWITCHYARD | FA | 2021-12-28 | 2022-05-13 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | AIS | CCPP | AIS | Elec. |  | 2025-06-30 |  |  | DE-GUP-DT-E-23-351 | 2023-03-23 | 0 | CRS-GUP-DHI-DT-23-1724 | 2023-03-17 | AA | DHI-GUP-DT-22-042 | 2022-02-09 | 0 | CRS-GUP-DHI-DT-22-204 | 2022-02-20 | NC | DE-GUP-DT-E-22-231 | 2022-05-19 | 1 | CRS-GUP-DHI-DT-22-408 | 2022-06-10 | RC | DE-GUP-DT-E-22-345 | 2022-06-29 | 2 | CRS-GUP-DHI-DT-22-557 | 2022-08-01 | RC | DE-GUP-DT-E-22-520 | 2022-08-19 | D | N/A-공식적으로는 미접수 | 2023-01-10 | RC | DE-GUP-DT-E-23-084 | 2023-01-27 | E | CRS-GUP-DHI-DT-23-1724 | 2023-03-17 | AA | DE-GUP-DT-E-23-351 | 2023-03-23 | 0
| GUP | YD04 | P1 | AE | 151101 |  | GUP-YD04-P1AE-151101 | CABLE TRAY & CONDUIT LAYOUT DRAWING_115kV AIS SWITCHYARD | FA | 2022-01-11 | 2022-05-13 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | AIS | CCPP | AIS | Elec. |  | 2025-04-17 |  |  | DE-GUP-DT-E-23-034 | 2023-01-17 | 2 | CRS-GUP-DHI-DT-22-1412 | 2023-01-11 | AA | DHI-GUP-DT-22-135 | 2022-03-25 | 0 | CRS-GUP-DHI-DT-22-296 | 2022-04-17 | NC | DE-GUP-DT-E-22-256 | 2022-05-27 | 1 | CRS-GUP-DHI-DT-22-454 | 2022-06-21 | RC | DE-GUP-DT-E-22-343 | 2022-06-28 | 2 | CRS-GUP-DHI-DT-22-554 | 2022-07-27 | RC | DE-GUP-DT-E-22-514 | 2022-08-18 | D | CRS-GUP-DHI-DT-22-705 | 2022-09-03 | RC | DE-GUP-DT-E-22-700 | 2022-09-23 | E | CRS-GUP-DHI-DT-22-1066 | 2022-11-19 | AC | DE-GUP-DT-E-22-973 | 2022-11-23 | 0(CP) | CRS-GUP-DHI-DT-22-1226 | 2022-12-13 | AC | DE-GUP-DT-E-22-1128 | 2022-12-19 | 1(CP) | CRS-GUP-DHI-DT-22-1412 | 2023-01-11 | AA | DE-GUP-DT-E-23-034 | 2023-01-17 | 2
| GUP | YD04 | P1 | AE | 151102 |  | GUP-YD04-P1AE-151102 | EARTHING LAYOUT DRAWING_115kV AIS SWITCHYARD | FA | 2022-01-11 | 2022-05-13 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | AIS | CCPP | AIS | Elec. |  | 2025-04-17 |  |  | DE-GUP-DT-E-22-1022 | 2022-12-01 | 1 | CRS-GUP-DHI-DT-24-021 | 2024-03-11 | AA | DHI-GUP-DT-22-135 | 2022-03-25 | 0 | CRS-GUP-DHI-DT-22-296 | 2022-04-17 | NC | DE-GUP-DT-E-22-437 | 2022-07-22 | B | CRS-GUP-DHI-DT-22-591 | 2022-08-08 | RC | DE-GUP-DT-E-22-514 | 2022-08-18 | C | CRS-GUP-DHI-DT-22-705 | 2022-09-03 | RC | DE-GUP-DT-E-22-672 | 2022-09-16 | D | CRS-GUP-DHI-DT-22-885 | 2022-10-10 | AC | DE-GUP-DT-E-22-822 | 2022-10-18 | 0(CP) | CRS-GUP-DHI-DT-22-961 | 2022-11-03 | AC | DE-GUP-DT-E-22-1022 | 2022-12-01 | 1 | CRS-GUP-DHI-DT-24-021 | 2024-03-11 | AA
| GUP | YD04 | P1 | AE | 151103 |  | GUP-YD04-P1AE-151103 | LIGHTNING PROTECTION LAYOUT DRAWING_115kV AIS SWITCHYARD | FA | 2022-01-11 | 2022-05-13 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | AIS | CCPP | AIS | Elec. |  | 2025-04-17 |  |  | DE-GUP-DT-E-22-792 | 2022-10-12 | 0 | CRS-GUP-DHI-DT-22-1134 | 2022-11-23 | AA | DHI-GUP-DT-22-135 | 2022-03-25 | 0 | CRS-GUP-DHI-DT-22-296 | 2022-04-17 | RC | DE-GUP-DT-E-22-231 | 2022-05-19 | 1 | CRS-GUP-DHI-DT-22-408 | 2022-06-10 | RC | DE-GUP-DT-E-22-359 | 2022-07-04 | 2 | CRS-GUP-DHI-DT-22-867 | 2022-10-09 | NC | DE-GUP-DT-E-22-792 | 2022-10-12 | 0 | CRS-GUP-DHI-DT-22-1134 | 2022-11-23 | AA
| GUP | YD04 | P1 | AE | 151104 |  | GUP-YD04-P1AE-151104 | OUTDOOR LIGHTING LAYOUT DRAWING_115kV AIS SWITCHYARD | FA | 2022-05-13 | 2022-08-13 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | AIS | CCPP | AIS | Elec. |  | 2025-04-17 |  |  | DE-GUP-DT-E-23-351 | 2023-03-23 | 2 | CRS-GUP-DHI-DT-23-1724 | 2023-03-17 | AA | DE-GUP-DT-E-22-479 | 2022-07-29 | A | CRS-GUP-DHI-DT-22-682 | 2022-08-22 | RC | DE-GUP-DT-E-22-686 | 2022-09-21 | B | CRS-GUP-DHI-DT-22-942 | 2022-10-22 | AC | DE-GUP-DT-E-22-1056 | 2022-12-09 | 0(CP) | CRS-GUP-DHI-DT-22-1326 | 2022-12-28 | AC | DE-GUP-DT-E-23-084 | 2023-01-27 | 1(CP) | CRS-GUP-DHI-DT-23-1724 | 2023-03-17 | AA | DE-GUP-DT-E-23-351 | 2023-03-23 | 2
| GUP | YD04 | P1 | AE | 151105 |  | GUP-YD04-P1AE-151105 | OUTDOOR LIGHTING CALCULATION_115kV AIS SWITCHYARD | FI | 2022-05-20 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | AIS | CCPP | AIS | Elec. |  | 2025-04-17 |  |  | DE-GUP-DT-E-22-479 | 2022-07-29 | 0 | CRS-GUP-DHI-DT-22-682 | 2022-08-22 | NC | DE-GUP-DT-E-22-479 | 2022-07-29 | 0 | CRS-GUP-DHI-DT-22-682 | 2022-08-22 | NC
| GUP | YL16 | P1 | ZEN | 151110 |  | GUP-YL16-P1ZEN-151110 | CABLE CONNECTION DIAGRAM & SCHEDULE_115kV AIS SWITCHYARD | FI | 2024-02-15 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FI | AIS | CCPP | AIS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-080 | 2024-03-18 | 1 | CRS-GUP-DHI-DT-24-049 | 2024-04-15 | NC | DE-GUP-DT-E-24-043 | 2024-02-08 | 0 | 메일로 회신- | 2024-02-15 | RC | DE-GUP-DT-E-24-080 | 2024-03-18 | 1 | CRS-GUP-DHI-DT-24-049 | 2024-04-15 | NC
| GUP | YD00 | P1 | BAT | 152013 |  | GUP-YD00-P1BAT-152013 | OUTLINE DRAWING_GENERATOR STEP UP TRANSFORMER | FI | 2021-11-01 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FI | TR | CCPP | Transformer | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-492 | 2023-04-21 | 3 | CRS-GUP-DHI-DT-23-1917 | 2023-05-05 | NC | DHI-GUP-DT-21-086 | 2021-11-02 | 0 | CRS-GUP-DHI-DT-21-068 | 2021-11-16 | NC | DHI-GUP-DT-21-190 | 2021-12-20 | 1 | CRS-GUP-DHI-DT-21-157 | 2022-01-12 | NC | DE-GUP-DT-E-22-742 | 2022-09-30 | 2 | CRS-GUP-DHI-DT-22-996 | 2022-11-13 | NC | DE-GUP-DT-E-23-492 | 2023-04-21 | 3 | CRS-GUP-DHI-DT-23-1917 | 2023-05-05 | NC
| GUP | YU03 | P1 | BAT | 152014 |  | GUP-YU03-P1BAT-152014 | SCHEMATIC DIAGRAM_GENERATOR STEP UP TRANSFORMER | FA | 2021-12-01 | 2022-07-29 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | TR | CCPP | Transformer | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-922 | 2022-11-08 | 0 | CRS-GUP-DHI-DT-22-1152 | 2022-11-23 | AA | DHI-GUP-DT-21-156 | 2021-12-08 | A | CRS-GUP-DHI-DT-21-111 | 2022-01-05 | RC | DHI-GUP-DT-22-096 | 2022-03-02 | B | CRS-GUP-DHI-DT-22-471 | 2022-06-22 | RC | DE-GUP-DT-E-22-456 | 2022-07-27 | C | CRS-GUP-DHI-DT-22-602 | 2022-08-13 | RC | DE-GUP-DT-E-22-604 | 2022-09-01 | D | CRS-GUP-DHI-DT-22-846 | 2022-09-24 | RC | DE-GUP-DT-E-22-808 | 2022-10-17 | E | CRS-GUP-DHI-DT-22-960 | 2022-11-03 | AA | DE-GUP-DT-E-22-922 | 2022-11-08 | 0 | CRS-GUP-DHI-DT-22-1152 | 2022-11-23 | AA
| GUP | YR02 | P1 | BAT | 152011 |  | GUP-YR02-P1BAT-152011 | TECHNICAL SPECIFICATION_GENERATOR STEP UP TRANSFORMER | FA | 2021-11-01 | 2022-07-29 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | TR | CCPP | Transformer | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-420 | 2022-07-20 | 0 | CRS-GUP-DHI-DT-22-672 | 2022-08-22 | AA | DHI-GUP-DT-21-086 | 2021-11-02 | A | CRS-GUP-DHI-DT-21-068 | 2021-11-16 | RC | DHI-GUP-DT-21-190 | 2021-12-20 | B | CRS-GUP-DHI-DT-21-157 | 2022-01-12 | RC | DHI-GUP-DT-22-095 | 2022-03-02 | C | CRS-GUP-DHI-DT-22-259 | 2022-03-17 | AC | DE-GUP-DT-E-22-311 | 2022-06-17 | D | CRS-GUP-DHI-DT-22-507 | 2022-07-10 | AA | DE-GUP-DT-E-22-420 | 2022-07-20 | 0 | CRS-GUP-DHI-DT-22-672 | 2022-08-22 | AA
| GUP | YR02 | P1 | BBT | 152021 |  | GUP-YR02-P1BBT-152021 | TECHNICAL SPECIFICATION_UNIT AUXILIARY TRANSFORMER | FA | 2021-11-01 | 2022-07-29 | 전력기술팀(Elec.) | 박경수 |  |  |  |  | TR | CCPP | Transformer | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-461 | 2022-07-27 | 0 | CRS-GUP-DHI-DT-22-507 | 2022-07-10 | AA | DHI-GUP-DT-21-086 | 2021-11-02 | A | CRS-GUP-DHI-DT-21-068 | 2021-11-16 | RC | DHI-GUP-DT-21-190 | 2021-12-20 | B | CRS-GUP-DHI-DT-21-157 | 2022-01-12 | RC | DHI-GUP-DT-22-095 | 2022-03-02 | C | CRS-GUP-DHI-DT-22-259 | 2022-03-17 | RC | DE-GUP-DT-E-22-311 | 2022-06-17 | D | CRS-GUP-DHI-DT-22-507 | 2022-07-10 | AA | DE-GUP-DT-E-22-461 | 2022-07-27 | 0
| GUP | YD00 | P1 | BBT | 152023 |  | GUP-YD00-P1BBT-152023 | OUTLINE DRAWING_UNIT AUXILIARY TRANSFORMER | FI | 2021-11-01 |  | 전력기술팀(Elec.) | 박경수 |  |  |  |  | TR | CCPP | Transformer | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-492 | 2023-04-21 | 3 | CRS-GUP-DHI-DT-23-1917 | 2023-05-05 | NC | DHI-GUP-DT-21-086 | 2021-11-02 | 0 | CRS-GUP-DHI-DT-21-068 | 2021-11-16 | NC | DHI-GUP-DT-21-190 | 2021-12-20 | 1 | CRS-GUP-DHI-DT-21-157 | 2022-01-12 | NC | DE-GUP-DT-E-22-742 | 2022-09-30 | 2 | CRS-GUP-DHI-DT-22-996 | 2022-11-13 | NC | DE-GUP-DT-E-23-492 | 2023-04-21 | 3 | CRS-GUP-DHI-DT-23-1917 | 2023-05-05 | NC
| GUP | YU03 | P1 | BBT | 152024 |  | GUP-YU03-P1BBT-152024 | SCHEMATIC DIAGRAM_UNIT AUXILIARY TRANSFORMER | FA | 2021-12-01 | 2022-07-29 | 전력기술팀(Elec.) | 박경수 |  |  |  |  | TR | CCPP | Transformer | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-461 | 2022-07-27 | 0 | CRS-GUP-DHI-DT-22-507 | 2022-07-10 | AA | DHI-GUP-DT-21-156 | 2021-12-08 | A | CRS-GUP-DHI-DT-21-111 | 2022-01-05 | RC | DHI-GUP-DT-22-105 | 2022-03-08 | B | CRS-GUP-DHI-DT-22-268 | 2022-03-29 | AC | DE-GUP-DT-E-22-311 | 2022-06-17 | C | CRS-GUP-DHI-DT-22-507 | 2022-07-10 | AA | DE-GUP-DT-E-22-461 | 2022-07-27 | 0
| GUP | YR02 | P1 | BAT | 152015 |  | GUP-YR02-P1BAT-152015 | VENDOR PRINT_DISSOLVED GAS ANALYSIS SYSTEM FOR GENERATOR STEP UP TRANSFORMER | FA | 2022-02-21 | 2022-07-29 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | TR | CCPP | Transformer | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-667 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-903 | 2022-10-12 | AA | DHI-GUP-DT-22-083 | 2022-02-22 | A | CRS-GUP-DHI-DT-22-252 | 2022-03-16 | RC | DHI-GUP-DT-22-184 | 2022-04-20 | B | CRS-GUP-DHI-DT-22-337 | 2022-05-16 | RC | DE-GUP-DT-E-22-322 | 2022-06-21 | C | CRS-GUP-DHI-DT-22-527 | 2022-07-19 | AA | DE-GUP-DT-E-22-667 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-903 | 2022-10-12 | AA
| GUP | YD00 | P1 | BAC | 152103 |  | GUP-YD00-P1BAC-152103 | OUTLINE DRAWING_GENERATOR CIRCUIT BREAKER | FI | 2021-10-15 |  | 전력기술팀(Elec.) | 박경수 |  |  |  |  | GCB | CCPP | GCB | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-267 | 2022-06-02 | 1 | CRS-GUP-DHI-DT-22-460 | 2022-06-21 | NC | DHI-GUP-DT-21-131 | 2021-11-30 | 0 | CRS-GUP-DHI-DT-21-096 | 2021-12-27 | RC | DE-GUP-DT-E-22-267 | 2022-06-02 | 1 | CRS-GUP-DHI-DT-22-460 | 2022-06-21 | NC
| GUP | YU03 | P1 | BAC | 152104 |  | GUP-YU03-P1BAC-152104 | SCHEMATIC DIAGRAM_GENERATOR CIRCUIT BREAKER | FA | 2022-01-03 | 2022-08-12 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | GCB | CCPP | GCB | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-104 | 2023-02-02 | 0 | CRS-GUP-DHI-DT-23-1428 | 2023-01-31 | AA | DHI-GUP-DT-22-115 | 2022-03-14 | A | CRS-GUP-DHI-DT-22-276 | 2022-04-02 | RC | DE-GUP-DT-E-22-321 | 2022-06-21 | B | CRS-GUP-DHI-DT-22-515 | 2022-07-12 | AC | DE-GUP-DT-E-22-414 | 2022-07-19 | C | CRS-GUP-DHI-DT-22-587 | 2022-08-08 | RC | DE-GUP-DT-E-22-515 | 2022-08-18 | D | CRS-GUP-DHI-DT-22-706 | 2022-09-03 | RC | DE-GUP-DT-E-22-860 | 2022-10-27 | E | CRS-GUP-DHI-DT-22-1079 | 2022-11-19 | RC | DE-GUP-DT-E-22-1208 | 2023-01-02 | F | CRS-GUP-DHI-DT-23-1428 | 2023-01-31 | AA | DE-GUP-DT-E-23-104 | 2023-02-02 | 0
| GUP | YR02 | P1 | BAC | 152101 |  | GUP-YR02-P1BAC-152101 | TECHNICAL SPECIFICATION_GENERATOR CIRCUIT BREAKER | FA | 2021-10-15 | 2022-07-29 | 전력기술팀(Elec.) | 박경수 |  |  |  |  | GCB | CCPP | GCB | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-384 | 2022-07-11 | 0 | CRS-GUP-DHI-DT-22-480 | 2022-07-03 | AA | DHI-GUP-DT-21-131 | 2021-11-30 | A | CRS-GUP-DHI-DT-21-096 | 2021-12-27 | RC | DHI-GUP-DT-22-151 | 2022-04-07 | B | CRS-GUP-DHI-DT-22-317 | 2022-05-02 | RC | DE-GUP-DT-E-22-268 | 2022-06-02 | C | CRS-GUP-DHI-DT-22-480 | 2022-07-03 | AA | DE-GUP-DT-E-22-384 | 2022-07-11 | 0
| GUP | YE00 | P1 | BBA | 152204 |  | GUP-YE00-P1BBA-152204 | GENERAL ARRANGEMENT DRAWING_NON-SEGREGATED PHASE BUSDUCT | FI | 2022-09-02 |  | 전력기술팀(Elec.) | 박경수 |  |  |  |  | NSPB | CCPP | NSPB | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-835 | 2023-09-27 | 2 | CRS-GUP-DHI-DT-23-1917 | 2023-05-05 | NC | DE-GUP-DT-E-22-642 | 2022-09-08 | 0 | CRS-GUP-DHI-DT-22-858 | 2022-09-24 | NC | DE-GUP-DT-E-23-492 | 2023-04-21 | 1 | CRS-GUP-DHI-DT-23-1917 | 2023-05-05 | NC | DE-GUP-DT-E-23-835 | 2023-09-27 | 2
| GUP | XW03 | P1 | BBA | 152205 |  | GUP-XW03-P1BBA-152205 | SUPPORT STEEL WORK CALCULATION_NON-SEGREGATED PHASE BUSDUCT | FI | 2022-09-02 |  | 전력기술팀(Elec.) | 박경수 |  |  |  |  | NSPB | CCPP | NSPB | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-917 | 2022-11-08 | 0 | CRS-GUP-DHI-DT-22-1060 | 2022-11-17 | NC | DE-GUP-DT-E-22-917 | 2022-11-08 | 0 | CRS-GUP-DHI-DT-22-1060 | 2022-11-17 | NC
| GUP | YR02 | P1 | BAA | 152201 |  | GUP-YR02-P1BAA-152201 | TECHNICAL SPECIFICATION_NON-SEGREGATED PHASE BUSDUCT | FA | 2022-08-12 | 2022-10-11 | 전력기술팀(Elec.) | 박경수 |  |  |  |  | NSPB | CCPP | NSPB | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-992 | 2022-11-28 | 0 | CRS-GUP-DHI-DT-22-1070 | 2022-11-19 | AA | DE-GUP-DT-E-22-490 | 2022-08-10 | A | CRS-GUP-DHI-DT-22-726 | 2022-09-09 | RC | DE-GUP-DT-E-22-712 | 2022-09-29 | B | CRS-GUP-DHI-DT-22-1070 | 2022-11-19 | AA | DE-GUP-DT-E-22-992 | 2022-11-28 | 0
| GUP | YD00 | P1 | BBA | 152302 |  | GUP-YD00-P1BBA-152302 | OUTLINE DRAWING_MV SWITCHGEAR | FI | 2022-06-17 |  | 전력기술팀(Elec.) | 정민구 |  |  |  |  | MV SWGR | CCPP | SWGR | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1094 | 2022-12-16 | 1 | CRS-GUP-DHI-DT-22-1383 | 2023-01-03 | NC | DE-GUP-DT-E-22-734 | 2022-09-30 | 0 | CRS-GUP-DHI-DT-22-955 | 2022-10-22 | RC | DE-GUP-DT-E-22-1094 | 2022-12-16 | 1 | CRS-GUP-DHI-DT-22-1383 | 2023-01-03 | NC
| GUP | YU03 | P1 | BBA | 152304 |  | GUP-YU03-P1BBA-152304 | SCHEMATIC DIAGRAM_MV SWITCHGEAR | FA | 2022-06-30 | 2022-10-18 | 전력기술팀(Elec.) | 정민구 |  |  |  |  | MV SWGR | CCPP | MV SWGR | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-376 | 2023-03-27 | 0 | CRS-GUP-DHI-DT-22-1368 | 2022-12-30 | AA | DE-GUP-DT-E-22-793 | 2022-10-12 | A | CRS-GUP-DHI-DT-22-1209 | 2022-11-30 | RC | DE-GUP-DT-E-22-1110 | 2022-12-16 | B | CRS-GUP-DHI-DT-22-1368 | 2022-12-30 | AA | DE-GUP-DT-E-23-376 | 2023-03-27 | 0
| GUP | YU02 | P1 | BBA | 152303 |  | GUP-YU02-P1BBA-152303 | SINGLE LINE DIAGRAM_MV SWITCHGEAR | FA | 2022-06-24 | 2022-10-11 | 전력기술팀(Elec.) | 정민구 |  |  |  |  | MV SWGR | CCPP | MV SWGR | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-155 | 2023-02-10 | 0 | CRS-GUP-DHI-DT-22-1383 | 2023-01-03 | AA | DE-GUP-DT-E-22-734 | 2022-09-30 | A | CRS-GUP-DHI-DT-22-955 | 2022-10-22 | RC | DE-GUP-DT-E-22-1094 | 2022-12-16 | B | CRS-GUP-DHI-DT-22-1383 | 2023-01-03 | AA | DE-GUP-DT-E-23-155 | 2023-02-10 | 0
| GUP | YR02 | P1 | BBA | 152301 |  | GUP-YR02-P1BBA-152301 | TECHNICAL SPECIFICATION_MV SWITCHGEAR | FA | 2022-04-27 | 2022-07-26 | 전력기술팀(Elec.) | 정민구 |  |  |  |  | MV SWGR | CCPP | MV SWGR | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1114 | 2022-12-16 | 1 | CRS-GUP-DHI-DT-22-1148 | 2022-11-23 | AA | DHI-GUP-DT-22-080 | 2022-02-18 | A | CRS-GUP-DHI-DT-22-246 | 2022-03-14 | RC | DE-GUP-DT-E-22-397 | 2022-07-13 | B | CRS-GUP-DHI-DT-22-597 | 2022-08-13 | RC | DE-GUP-DT-E-22-709 | 2022-09-28 | C | CRS-GUP-DHI-DT-22-949 | 2022-10-22 | AA | DE-GUP-DT-E-22-893 | 2022-11-01 | 0 | CRS-GUP-DHI-DT-22-1148 | 2022-11-23 | AA | DE-GUP-DT-E-22-1114 | 2022-12-16 | 1
| GUP | YU02 | P1 | ZEN | 150006 |  | GUP-YU02-P1ZEN-150006 | SIZING CALCULATION_CT & VT | FA | 2022-07-11 | 2022-10-09 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA |  | CCPP | Plant | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-549 | 2023-05-12 | 0 | CRS-GUP-DHI-DT-23-1936 | 2023-05-05 | AA | DE-GUP-DT-E-22-821 | 2022-10-18 | A | CRS-GUP-DHI-DT-22-1049 | 2022-11-17 | RC | DE-GUP-DT-E-22-1106 | 2022-12-16 | B | CRS-GUP-DHI-DT-22-1393 | 2023-01-06 | RC | DE-GUP-DT-E-23-034 | 2023-01-17 | C | CRS-GUP-DHI-DT-23-1636 | 2023-03-04 | RC | DE-GUP-DT-E-23-445 | 2023-04-11 | D | CRS-GUP-DHI-DT-23-1936 | 2023-05-05 | AA | DE-GUP-DT-E-23-549 | 2023-05-12 | 0
| GUP | YD00 | P1 | BFA | 152402 |  | GUP-YD00-P1BFA-152402 | OUTLINE DRAWING_LV SWITCHGEAR / LV TRANSFORMER | FI | 2022-06-17 |  | 전력기술팀(Elec.) | 정민구 |  |  |  |  | LV SWGR | CCPP | SWGR | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1214 | 2023-01-04 | 3 | CRS-GUP-DHI-DT-22-1461 | 2023-02-05 | NC | DE-GUP-DT-E-22-440 | 2022-07-25 | 0 | CRS-GUP-DHI-DT-22-675 | 2022-08-22 | RC | DE-GUP-DT-E-22-741 | 2022-09-30 | 1 | CRS-GUP-DHI-DT-22-985 | 2022-11-08 | NC | DE-GUP-DT-E-22-937 | 2022-11-11 | 2 | CRS-GUP-DHI-DT-22-1057 | 2022-11-17 | NC | DE-GUP-DT-E-22-1214 | 2023-01-04 | 3 | CRS-GUP-DHI-DT-22-1461 | 2023-02-05 | NC
| GUP | YD00 | P1 | BFD | 152412 |  | GUP-YD00-P1BFD-152412 | OUTLINE DRAWING_480V MCC | FI | 2022-06-17 |  | 전력기술팀(Elec.) | 정민구 |  |  |  |  | LV SWGR | CCPP | MCC | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1228 | 2023-01-06 | 3 | CRS-GUP-DHI-DT-23-1496 | 2023-02-12 | NC | DE-GUP-DT-E-22-466 | 2022-07-28 | 0 | CRS-GUP-DHI-DT-22-665 | 2022-08-22 | RC | DE-GUP-DT-E-22-707 | 2022-09-28 | 1 | CRS-GUP-DHI-DT-22-948 | 2022-10-22 | NC | DE-GUP-DT-E-22-934 | 2022-11-10 | 2 | CRS-GUP-DHI-DT-22-1187 | 2022-11-30 | NC | DE-GUP-DT-E-22-1228 | 2023-01-06 | 3 | CRS-GUP-DHI-DT-23-1496 | 2023-02-12 | NC
| GUP | YU03 | P1 | BFA | 152404 |  | GUP-YU03-P1BFA-152404 | SCHEMATIC DIAGRAM_LV SWITCHGEAR / LV TRANSFORMER | FA | 2022-06-30 | 2022-08-29 | 전력기술팀(Elec.) | 정민구 |  |  |  |  | LV SWGR | CCPP | LV SWGR | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-376 | 2023-03-27 | 0 | CRS-GUP-DHI-DT-23-1498 | 2023-02-13 | AA | DE-GUP-DT-E-22-655 | 2022-09-14 | A | CRS-GUP-DHI-DT-22-898 | 2022-10-12 | RC | DE-GUP-DT-E-22-1254 | 2023-01-11 | B | CRS-GUP-DHI-DT-23-1498 | 2023-02-13 | AA | DE-GUP-DT-E-23-376 | 2023-03-27 | 0
| GUP | YU03 | P1 | BFB | 152414 |  | GUP-YU03-P1BFB-152414 | SCHEMATIC DIAGRAM_480V MCC | FA | 2022-06-30 | 2022-08-29 | 전력기술팀(Elec.) | 정민구 |  |  |  |  | LV SWGR | CCPP | MCC | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-242 | 2023-02-24 | 0 | CRS-GUP-DHI-DT-23-1496 | 2023-02-12 | AA | DE-GUP-DT-E-22-655 | 2022-09-14 | A | CRS-GUP-DHI-DT-22-898 | 2022-10-12 | RC | DE-GUP-DT-E-22-1228 | 2023-01-06 | B | CRS-GUP-DHI-DT-23-1496 | 2023-02-12 | AA | DE-GUP-DT-E-23-242 | 2023-02-24 | 0
| GUP | YU02 | P1 | BFA | 152403 |  | GUP-YU02-P1BFA-152403 | SINGLE LINE DIAGRAM_LV SWITCHGEAR / LV TRANSFORMER | FA | 2022-06-17 | 2022-08-16 | 전력기술팀(Elec.) | 정민구 |  |  |  |  | LV SWGR | CCPP | LV SWGR | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1214 | 2023-01-04 | 1 | CRS-GUP-DHI-DT-22-1461 | 2023-02-05 | AA | DE-GUP-DT-E-22-440 | 2022-07-25 | A | CRS-GUP-DHI-DT-22-675 | 2022-08-22 | RC | DE-GUP-DT-E-22-741 | 2022-09-30 | B | CRS-GUP-DHI-DT-22-985 | 2022-11-08 | AA | DE-GUP-DT-E-22-937 | 2022-11-11 | 0 | CRS-GUP-DHI-DT-22-1057 | 2022-11-17 | AA | DE-GUP-DT-E-22-1214 | 2023-01-04 | 1 | CRS-GUP-DHI-DT-22-1461 | 2023-02-05 | AA
| GUP | YU02 | P1 | BFB | 152411 |  | GUP-YU02-P1BFB-152411 | SINGLE LINE DRAWING_480V MCC | FA | 2022-06-17 | 2022-08-16 | 전력기술팀(Elec.) | 정민구 |  |  |  |  | LV SWGR | CCPP | MCC | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1228 | 2023-01-06 | 1 | CRS-GUP-DHI-DT-23-1496 | 2023-02-12 | AA | DE-GUP-DT-E-22-466 | 2022-07-28 | A | CRS-GUP-DHI-DT-22-665 | 2022-08-22 | RC | DE-GUP-DT-E-22-707 | 2022-09-28 | B | CRS-GUP-DHI-DT-22-948 | 2022-10-22 | AA | DE-GUP-DT-E-22-934 | 2022-11-10 | 0 | CRS-GUP-DHI-DT-22-1155 | 2022-11-23 | AA | DE-GUP-DT-E-22-1228 | 2023-01-06 | 1 | CRS-GUP-DHI-DT-23-1496 | 2023-02-12 | AA
| GUP | YR02 | P1 | BFA | 152421 |  | GUP-YR02-P1BFA-152421 | TECHNICAL SPECIFICATION_LV SWITCHGEAR / LV TRANSFORMER | FA | 2022-04-27 | 2022-07-26 | 전력기술팀(Elec.) | 정민구 |  |  |  |  | LV SWGR | CCPP | LV SWGR | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1114 | 2022-12-16 | 2 | CRS-GUP-DHI-DT-22-1154 | 2022-11-23 | AA | DHI-GUP-DT-22-026 | 2022-01-19 | A | CRS-GUP-DHI-DT-21-169 | 2022-01-24 | RR | DE-GUP-DT-E-22-274 | 2022-06-08 | B | CRS-GUP-DHI-DT-22-488 | 2022-07-06 | AA | DE-GUP-DT-E-22-489 | 2022-08-10 | 0 | N/A(자체 CRS 개정 후 제출) | 2022-11-09 | N/A | DE-GUP-DT-E-22-933 | 2022-11-10 | 1 | CRS-GUP-DHI-DT-22-1154 | 2022-11-23 | AA | DE-GUP-DT-E-22-1114 | 2022-12-16 | 2
| GUP | YD00 | P1 | BTW | 152604 |  | GUP-YD00-P1BTW-152604 | OUTLINE DRAWING_DC & UPS SYSTEM | FI | 2022-06-24 |  | 전력기술팀(Elec.) | 박경수 |  |  |  |  | DC&UPS | CCPP | DC & UPS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-473 | 2023-04-14 | 2 | CRS-GUP-DHI-DT-23-1893 | 2023-05-02 | NC | DE-GUP-DT-E-22-473 | 2022-07-29 | 0 | CRS-GUP-DHI-DT-22-681 | 2022-08-22 | NC | DE-GUP-DT-E-22-1117 | 2022-12-16 | 1 | CRS-GUP-DHI-DT-22-1385 | 2023-01-03 | RC | DE-GUP-DT-E-23-473 | 2023-04-14 | 2 | CRS-GUP-DHI-DT-23-1893 | 2023-05-02 | NC
| GUP | YU03 | P1 | BTW | 152605 |  | GUP-YU03-P1BTW-152605 | SCHEMATIC DRAWING_DC & UPS SYSTEM | FA | 2022-07-22 | 2022-10-22 | 전력기술팀(Elec.) | 박경수 |  |  | G | FI | DC&UPS | CCPP | DC & UPS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-549 | 2023-05-12 | 0 | CRS-GUP-DHI-DT-23-1940 | 2023-05-11 | AA | DE-GUP-DT-E-23-202 | 2023-02-17 | A | CRS-GUP-DHI-DT-23-1669 | 2023-03-10 | RC | DE-GUP-DT-E-23-492 | 2023-04-21 | B | CRS-GUP-DHI-DT-23-1940 | 2023-05-11 | AA | DE-GUP-DT-E-23-549 | 2023-05-12 | 0
| GUP | YU02 | P1 | BTW | 152603 |  | GUP-YU02-P1BTW-152603 | SINGLE LINE DIAGRAM_DC & UPS SYSTEM | FA | 2022-06-24 | 2022-10-24 | 전력기술팀(Elec.) | 박경수 |  |  |  |  | DC&UPS | CCPP | DC & UPS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-549 | 2023-05-12 | 0 | CRS-GUP-DHI-DT-23-1893 | 2023-05-02 | AA | DE-GUP-DT-E-22-854 | 2022-10-25 | A | CRS-GUP-DHI-DT-22-1078 | 2022-11-19 | RC | DE-GUP-DT-E-22-1117 | 2022-12-16 | B | CRS-GUP-DHI-DT-22-1385 | 2023-01-03 | RC | DE-GUP-DT-E-23-473 | 2023-04-14 | C | CRS-GUP-DHI-DT-23-1893 | 2023-05-02 | AA | DE-GUP-DT-E-23-549 | 2023-05-12 | 0
| GUP | YR02 | P1 | BTW | 152601 |  | GUP-YR02-P1BTW-152601 | TECHNICAL SPECIFICATION_DC & UPS SYSTEM | FA | 2022-02-16 | 2022-08-12 | 전력기술팀(Elec.) | 박경수 |  |  |  |  | DC&UPS | CCPP | DC & UPS | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-473 | 2023-04-14 | 2 | CRS-GUP-DHI-DT-23-1893 | 2023-05-02 | AA | DHI-GUP-DT-21-192 | 2021-12-22 | A | CRS-GUP-DHI-DT-21-162 | 2022-01-14 | RC | DE-GUP-DT-E-22-487 | 2022-08-08 | B | CRS-GUP-DHI-DT-22-692 | 2022-08-29 | AA | DE-GUP-DT-E-22-593 | 2022-08-31 | 0 | 자체 CRS 개정 후 제출 | 2022-12-15 | N/A | DE-GUP-DT-E-22-1117 | 2022-12-16 | 1 | CRS-GUP-DHI-DT-22-1385 | 2023-01-03 | RC | DE-GUP-DT-E-23-473 | 2023-04-14 | 2 | CRS-GUP-DHI-DT-23-1893 | 2023-05-02 | AA
| GUP | YD00 | P1 | ASR | 152522 |  | GUP-YD00-P1ASR-152522 | OUTLINE DRAWING_FAULT MONITORING SYSTEM | FI | 2022-08-19 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | FMS | CCPP | FMS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-978 | 2023-12-07 | 5 | CRS-GUP-DHI-DT-23-1519 | 2023-02-14 | NC | DE-GUP-DT-E-22-537 | 2022-08-23 | 0 | CRS-GUP-DHI-DT-22-732 | 2022-09-09 | RC | DE-GUP-DT-E-22-725 | 2022-09-29 | 1 | CRS-GUP-DHI-DT-22-952 | 2022-10-22 | NC | DE-GUP-DT-E-22-940 | 2022-11-15 | 2 | CRS-GUP-DHI-DT-22-1237 | 2022-12-13 | RC | DE-GUP-DT-E-22-1143 | 2022-12-21 | 3 | CRS-GUP-DHI-DT-22-1395 | 2023-01-06 | NC | DE-GUP-DT-E-23-004 | 2023-01-12 | 4 | CRS-GUP-DHI-DT-23-1519 | 2023-02-14 | NC | DE-GUP-DT-E-23-978 | 2023-12-07 | 5
| GUP | YK08 | P1 | ASR | 152524 |  | GUP-YK08-P1ASR-152524 | CONFIGURATION DIAGRAM_FAULT MONITORING SYSTEM | FI | 2022-08-31 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | FMS | CCPP | FMS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-978 | 2023-12-07 | 3 | CRS-GUP-DHI-DT-23-1576 | 2023-02-23 | NC | DE-GUP-DT-E-22-597 | 2022-08-31 | 0 | CRS-GUP-DHI-DT-22-864 | 2022-09-26 | RC | DE-GUP-DT-E-22-866 | 2022-10-27 | 1 | CRS-GUP-DHI-DT-22-1080 | 2022-11-19 | NC | DE-GUP-DT-E-23-134 | 2023-02-07 | 2 | CRS-GUP-DHI-DT-23-1576 | 2023-02-23 | NC | DE-GUP-DT-E-23-978 | 2023-12-07 | 3
| GUP | YR02 | P1 | ASR | 152521 |  | GUP-YR02-P1ASR-152521 | TECHNICAL SPECIFICATION_FAULT MONITORING SYSTEM | FA | 2022-08-19 | 2022-11-17 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | FMS | CCPP | FMS | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-978 | 2023-12-07 | 1 | 자체 CRS 개정 후 제출 | 2023-12-06 | N/A | DE-GUP-DT-E-22-537 | 2022-08-23 | A | CRS-GUP-DHI-DT-22-732 | 2022-09-09 | RC | DE-GUP-DT-E-22-725 | 2022-09-29 | B | CRS-GUP-DHI-DT-22-952 | 2022-10-22 | RC | DE-GUP-DT-E-22-940 | 2022-11-15 | C | CRS-GUP-DHI-DT-22-1237 | 2022-12-13 | RC | DE-GUP-DT-E-22-1143 | 2022-12-21 | D | CRS-GUP-DHI-DT-22-1395 | 2023-01-06 | AA | DE-GUP-DT-E-23-004 | 2023-01-12 | 0 | 자체 CRS 개정 후 제출 | 2023-12-06 | N/A | DE-GUP-DT-E-23-978 | 2023-12-07 | 1
| GUP | YU03 | P1 | ASR | 152523 |  | GUP-YU03-P1ASR-152523 | SCHEMATIC DAIGRAM_FAULT MONITORING SYSTEM | FA | 2022-08-31 | 2022-11-29 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | FMS | CCPP | FMS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-978 | 2023-12-07 | 1 | 자체 CRS 개정 후 제출 | 2023-12-06 | N/A | DE-GUP-DT-E-22-597 | 2022-08-31 | A | CRS-GUP-DHI-DT-22-864 | 2022-09-26 | AC | DE-GUP-DT-E-22-866 | 2022-10-27 | B | CRS-GUP-DHI-DT-22-1080 | 2022-11-19 | RC | DE-GUP-DT-E-22-1236 | 2023-01-09 | C | CRS-GUP-DHI-DT-23-1437 | 2023-01-31 | AA | DE-GUP-DT-E-23-134 | 2023-02-07 | 0 | 자체 CRS 개정 후 제출 | 2023-12-06 | N/A | DE-GUP-DT-E-23-978 | 2023-12-07 | 1
| GUP | YL01 | P1 | ASR | 152526 |  | GUP-YL01-P1ASR-152526 | IED LIST_FAULT MONITORING SYSTEM | FI | 2022-08-31 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | FMS | CCPP | FMS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-728 | 2022-09-30 | 0 | CRS-GUP-DHI-DT-22-954 | 2022-10-22 | NC | DE-GUP-DT-E-22-728 | 2022-09-30 | 0 | CRS-GUP-DHI-DT-22-954 | 2022-10-22 | NC
| GUP | YD05 | P1 | ASR | 152525 |  | GUP-YD05-P1ASR-152525 | HMI_FAULT MONITORING SYSTEM | FI | 2022-08-31 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | FMS | CCPP | FMS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-866 | 2022-10-27 | 1 | CRS-GUP-DHI-DT-22-1080 | 2022-11-19 | NC | DE-GUP-DT-E-22-597 | 2022-08-31 | 0 | CRS-GUP-DHI-DT-22-864 | 2022-09-26 | RC | DE-GUP-DT-E-22-866 | 2022-10-27 | 1 | CRS-GUP-DHI-DT-22-1080 | 2022-11-19 | NC
| GUP | YD00 | P1 | ASR | 152502 |  | GUP-YD00-P1ASR-152502 | OUTLINE DRAWING_PROTECTION RELAY PANEL | FI | 2022-08-20 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | PRP | CCPP | PRP | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-978 | 2023-12-07 | 2 | 자체 CRS 개정 후 제출 | 2023-12-06 | N/A | DE-GUP-DT-E-22-538 | 2022-08-23 | 0 | CRS-GUP-DHI-DT-22-739 | 2022-09-12 | NC | DE-GUP-DT-E-23-062 | 2023-01-20 | 1 | 자체 CRS 개정 후 제출 | 2023-12-06 | N/A | DE-GUP-DT-E-23-978 | 2023-12-07 | 2
| GUP | YU03 | P1 | ASR | 152503 |  | GUP-YU03-P1ASR-152503 | SCHEMATIC DAIGRAM_PROTECTION RELAY PANEL | FI | 2022-09-17 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | PRP | CCPP | PRP | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-978 | 2023-12-07 | 2 | CRS-GUP-DHI-DT-23-1690 | 2023-03-14 | NC | DE-GUP-DT-E-22-688 | 2022-09-21 | 0 | CRS-GUP-DHI-DT-22-944 | 2022-10-22 | RC | DE-GUP-DT-E-23-204 | 2023-02-20 | 1 | CRS-GUP-DHI-DT-23-1690 | 2023-03-14 | NC | DE-GUP-DT-E-23-978 | 2023-12-07 | 2
| GUP | YR02 | P1 | ASR | 152501 |  | GUP-YR02-P1ASR-152501 | TECHNICAL SPECIFICATION_PROTECTION RELAY PANEL | FI | 2022-08-20 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | PRP | CCPP | PRP | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-978 | 2023-12-07 | 1 | CRS-GUP-DHI-DT-22-739 | 2022-09-12 | NC | DE-GUP-DT-E-22-538 | 2022-08-23 | 0 | CRS-GUP-DHI-DT-22-739 | 2022-09-12 | NC | DE-GUP-DT-E-23-978 | 2023-12-07 | 1
| GUP | CV03 | P1 | ASQ | 152532 |  | GUP-CV03-P1ASQ-152532 | OUTLINE DRAWING_PLANT METERING PANEL | FI | 2022-08-20 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | Plant Metering | CCPP | Plant Metering | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-978 | 2023-12-07 | 3 | CRS-GUP-DHI-DT-23-1581 | 2023-02-25 | NC | DE-GUP-DT-E-22-539 | 2022-08-23 | 0 | CRS-GUP-DHI-DT-22-740 | 2022-09-12 | RC | DE-GUP-DT-E-22-711 | 2022-09-28 | 1 | CRS-GUP-DHI-DT-22-951 | 2022-10-22 | RC | DE-GUP-DT-E-23-062 | 2023-01-20 | 2 | CRS-GUP-DHI-DT-23-1581 | 2023-02-25 | NC | DE-GUP-DT-E-23-978 | 2023-12-07 | 3
| GUP | YF02 | P1 | ASQ | 152533 |  | GUP-YF02-P1ASQ-152533 | SCHEMATIC DAIGRAM_PLANT METERING PANEL | FI | 2022-09-17 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | Plant Metering | CCPP | Plant Metering | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-978 | 2023-12-07 | 2 | CRS-GUP-DHI-DT-23-1690 | 2023-03-14 | NC | DE-GUP-DT-E-22-688 | 2022-09-21 | 0 | CRS-GUP-DHI-DT-22-944 | 2022-10-22 | RC | DE-GUP-DT-E-23-204 | 2023-02-20 | 1 | CRS-GUP-DHI-DT-23-1690 | 2023-03-14 | NC | DE-GUP-DT-E-23-978 | 2023-12-07 | 2
| GUP | CV03 | P1 | ASQ | 152531 |  | GUP-CV03-P1ASQ-152531 | TECHNICAL SPECIFICATION_PLANT METERING PANEL | FI | 2022-08-20 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | Plant Metering | CCPP | Plant Metering | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-978 | 2023-12-07 | 3 | CRS-GUP-DHI-DT-23-1581 | 2023-02-25 | NC | DE-GUP-DT-E-22-539 | 2022-08-23 | 0 | CRS-GUP-DHI-DT-22-740 | 2022-09-12 | RC | DE-GUP-DT-E-22-711 | 2022-09-28 | 1 | CRS-GUP-DHI-DT-22-951 | 2022-10-22 | RC | DE-GUP-DT-E-23-062 | 2023-01-20 | 2 | CRS-GUP-DHI-DT-23-1581 | 2023-02-25 | NC | DE-GUP-DT-E-23-978 | 2023-12-07 | 3
| GUP | YR02 | P1 | ZEN | 152801 |  | GUP-YR02-P1ZEN-152801 | TECHNICAL SPECIFICATION_POWER & CONTROL CABLE | FA | 2022-09-13 | 2023-01-11 | 전력기술팀(Elec.) | 허규범 |  |  | G | FA | CABLE | CCPP | Cable | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-615 | 2023-06-13 | 0 | CRS-GUP-DHI-DT-23-1988 | 2023-06-12 | AA | DE-GUP-DT-E-22-987 | 2022-11-25 | A | CRS-GUP-DHI-DT-22-1260 | 2022-12-16 | RC | DE-GUP-DT-E-23-032 | 2023-01-16 | B | CRS-GUP-DHI-DT-23-1558 | 2023-02-23 | RC | DE-GUP-DT-E-23-323 | 2023-03-16 | C | CRS-GUP-DHI-DT-23-1798 | 2023-04-04 | RC | DE-GUP-DT-E-23-436 | 2023-04-07 | D | CRS-GUP-DHI-DT-23-1988 | 2023-06-12 | AA | DE-GUP-DT-E-23-615 | 2023-06-13 | 0
| GUP | YR02 | P1 | ZEN | 152802 |  | GUP-YR02-P1ZEN-152802 | TECHNICAL SPECIFICATION_CABLE TERMINATION MATERIALS | FI | 2022-09-13 |  | 전력기술팀(Elec.) | 허규범 |  |  | G | FA | CABLE | CCPP | Cable | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-251 | 2023-02-27 | 1 | CRS-GUP-DHI-DT-23-1748 | 2023-03-18 | NC | DE-GUP-DT-E-22-782 | 2022-10-11 | 0 | CRS-GUP-DHI-DT-22-987 | 2022-11-08 | RC | DE-GUP-DT-E-23-251 | 2023-02-27 | 1 | CRS-GUP-DHI-DT-23-1748 | 2023-03-18 | NC
| GUP | YR02 | P1 | ZEN | 152803 |  | GUP-YR02-P1ZEN-152803 | TECHNICAL SPECIFICATION_FIRE STOP MATERIALS | FI | 2023-01-15 |  | 전력기술팀(Elec.) | 허규범 |  |  | G | FA | FIRE STOP | CCPP | FIRE STOP | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-032 | 2023-01-16 | 0 | CRS-GUP-DHI-DT-23-1529 | 2023-02-14 | NC | DE-GUP-DT-E-23-032 | 2023-01-16 | 0 | CRS-GUP-DHI-DT-23-1529 | 2023-02-14 | NC
| GUP | YR02 | P1 | BAU | 153101 |  | GUP-YR02-P1BAU-153101 | TECHNICAL SPECIFICATION_EARTHING & LIGHTNING PROTECTION SYSTEM | FA | 2022-04-21 | 2022-07-19 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | EARTHING | CCPP | Earthing & Lightning | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-269 | 2022-06-03 | 0 | CRS-GUP-DHI-DT-22-314 | 2022-05-02 | AA | DHI-GUP-DT-22-040 | 2022-01-27 | A | CRS-GUP-DHI-DT-22-203 | 2022-02-20 | RC | DHI-GUP-DT-22-109 | 2022-03-10 | B | CRS-GUP-DHI-DT-22-273 | 2022-03-31 | RC | DHI-GUP-DT-22-144 | 2022-04-01 | C | CRS-GUP-DHI-DT-22-314 | 2022-05-02 | AA | DE-GUP-DT-E-22-269 | 2022-06-03 | 0
| GUP | YR02 | P1 | ZEN | 153201 |  | GUP-YR02-P1ZEN-153201 | TECHNICAL SPECIFICATION_LIGHTING & SMALL POWER SYSTEM | FI | 2022-08-31 |  | 전력기술팀(Elec.) | 고승호 |  |  | G | FA | LIGHTING | CCPP | Lighting & Small Power | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-976 | 2023-12-06 | 1 | CRS-GUP-DHI-DT-22-1199 | 2022-11-30 | NC | DE-GUP-DT-E-22-904 | 2022-11-03 | 0 | CRS-GUP-DHI-DT-22-1199 | 2022-11-30 | NC | DE-GUP-DT-E-23-976 | 2023-12-06 | 1
| GUP | YD02 | P1 | ZEN | 153203 |  | GUP-YD02-P1ZEN-153203 | OUTLINE AND SCHEMATIC DRAWING OF LIGHTING DISTRIBUTION PANEL | FI | 2023-01-28 |  | 전력기술팀(Elec.) | 고승호 |  |  | G | FA | LIGHTING | CCPP | Lighting & Small Power | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-471 | 2023-04-14 | 1 | CRS-GUP-DHI-DT-23-1879 | 2023-04-27 | NC | DE-GUP-DT-E-22-1247 | 2023-01-11 | 0 | CRS-GUP-DHI-DT-23-1499 | 2023-02-13 | RC | DE-GUP-DT-E-23-471 | 2023-04-14 | 1 | CRS-GUP-DHI-DT-23-1879 | 2023-04-27 | NC
| GUP | YR02 | P1 | ZEN | 152901 |  | GUP-YR02-P1ZEN-152901 | TECHNICAL SPECIFICATION_CABLE TRAY & ACCESSORIES | FI | 2022-08-25 |  | 전력기술팀(Elec.) | 허규범 |  |  | G | FA | CABLE TRAY | CCPP | Raceway | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1193 | 2022-12-23 | 1 | CRS-GUP-DHI-DT-22-1457 | 2023-02-04 | NC | DE-GUP-DT-E-22-782 | 2022-10-11 | 0 | CRS-GUP-DHI-DT-22-987 | 2022-11-08 | RC | DE-GUP-DT-E-22-1193 | 2022-12-23 | 1 | CRS-GUP-DHI-DT-22-1457 | 2023-02-04 | NC
| GUP | YR02 | P1 | ZEN | 153002 |  | GUP-YR02-P1ZEN-153002 | TECHNICAL SPECIFICATION_CONDUIT & ACCESSORIES | FI | 2022-08-25 |  | 전력기술팀(Elec.) | 허규범 |  |  | G | FA | CONDUIT | CCPP | Raceway | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1194 | 2022-12-23 | 0 | CRS-GUP-DHI-DT-22-1454 | 2023-02-04 | NC | DE-GUP-DT-E-22-1194 | 2022-12-23 | 0 | CRS-GUP-DHI-DT-22-1454 | 2023-02-04 | NC
| GUP | YR02 | P1 | CYA | 153301 |  | GUP-YR02-P1CYA-153301 | TECHNICAL SPECIFICATION_COMMUNICATION SYSTEM | FA | 2022-11-02 | 2023-02-01 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA | COMMUNICATION | CCPP | Communication | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-042 | 2024-02-08 | 0 | CRS-GUP-DHI-DT-24-041 | 2024-03-19 | AA | DE-GUP-DT-E-23-250 | 2023-02-27 | A | CRS-GUP-DHI-DT-23-1742 | 2023-03-17 | RC | DE-GUP-DT-E-23-493 | 2023-04-21 | B | CRS-GUP-DHI-DT-23-1958 | 2023-05-24 | RC | DE-GUP-DT-E-23-609 | 2023-06-08 | C | CRS-GUP-DHI-DT-23-2033 | 2023-07-04 | RC | DE-GUP-DT-E-23-769 | 2023-08-28 | D | CRS-GUP-DHI-DT-23-2114 | 2023-09-27 | RC | DE-GUP-DT-E-23-922 | 2023-11-20 | E | CRS-GUP-DHI-DT-24-009 | 2024-02-05 | AC | DE-GUP-DT-E-24-042 | 2024-02-08 | 0 | CRS-GUP-DHI-DT-24-041 | 2024-03-19 | AA
| GUP | YR02 | P1 | PUR | 152701 |  | GUP-YR02-P1PUR-152701 | TECHNICAL SPECIFICATION_CATHODIC PROTECTION SYSTEM | FA | 2022-07-29 | 2022-10-28 | 전력기술팀(Elec.) | 정민구 |  |  | G | FA | CATHODIC | CCPP | Cathodic Protection | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-942 | 2023-11-23 | 1 | CRS-GUP-DHI-DT-23-1527 | 2023-02-14 | AA | DE-GUP-DT-E-22-485 | 2022-07-29 | A | CRS-GUP-DHI-DT-22-668 | 2022-08-22 | RC | DE-GUP-DT-E-22-731 | 2022-09-30 | B | CRS-GUP-DHI-DT-22-984 | 2022-11-08 | AC | DE-GUP-DT-E-23-027 | 2023-01-13 | 0(CP) | CRS-GUP-DHI-DT-23-1527 | 2023-02-14 | AA | DE-GUP-DT-E-23-942 | 2023-11-23 | 1
| GUP | VT10 | P1 | PUR | 152705 |  | GUP-VT10-P1PUR-152705 | CALCULATION_CATHODIC PROTECTION SYSTEM | FA | 2022-07-29 | 2022-10-28 | 전력기술팀(Elec.) | 정민구 |  |  | G | FA | CATHODIC | CCPP | Cathodic Protection | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-967 | 2023-12-01 | 1 | CRS-GUP-DHI-DT-23-1527 | 2023-02-14 | AA | DE-GUP-DT-E-22-485 | 2022-07-29 | A | CRS-GUP-DHI-DT-22-668 | 2022-08-22 | RC | DE-GUP-DT-E-22-731 | 2022-09-30 | B | CRS-GUP-DHI-DT-22-984 | 2022-11-08 | AA | DE-GUP-DT-E-23-027 | 2023-01-13 | 0 | CRS-GUP-DHI-DT-23-1527 | 2023-02-14 | AA | DE-GUP-DT-E-23-967 | 2023-12-01 | 1
| GUP | YK09 | P1 | PUR | 152703 |  | GUP-YK09-P1PUR-152703 | GENERAL ARRANGEMENT DRAWING_CATHODIC PROTECTION SYSTEM | FA | 2022-07-29 | 2022-10-28 | 전력기술팀(Elec.) | 정민구 |  |  | G | FA | CATHODIC | CCPP | Cathodic Protection | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-949 | 2023-11-28 | 1 | CRS-GUP-DHI-DT-23-1837 | 2023-04-18 | AA | DE-GUP-DT-E-22-598 | 2022-08-31 | A | CRS-GUP-DHI-DT-22-843 | 2022-09-24 | RC | DE-GUP-DT-E-22-819 | 2022-10-18 | B | CRS-GUP-DHI-DT-22-989 | 2022-11-08 | RC | DE-GUP-DT-E-22-1196 | 2022-12-26 | C | CRS-GUP-DHI-DT-23-1427 | 2023-01-31 | RC | DE-GUP-DT-E-23-107 | 2023-02-02 | D | CRS-GUP-DHI-DT-23-1648 | 2023-03-07 | AC | DE-GUP-DT-E-23-407 | 2023-03-31 | 0 | CRS-GUP-DHI-DT-23-1837 | 2023-04-18 | AA | DE-GUP-DT-E-23-949 | 2023-11-28 | 1
| GUP | YK08 | P1 | PUR | 152704 |  | GUP-YK08-P1PUR-152704 | OUTLINE DRAWING_CATHODIC PROTECTION SYSTEM | FI | 2022-07-29 |  | 전력기술팀(Elec.) | 정민구 |  |  | G | FA | CATHODIC | CCPP | Cathodic Protection | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-967 | 2023-12-01 | 3 | CRS-GUP-DHI-DT-23-1527 | 2023-02-14 | NC | DE-GUP-DT-E-22-485 | 2022-07-29 | 0 | CRS-GUP-DHI-DT-22-668 | 2022-08-22 | RC | DE-GUP-DT-E-22-731 | 2022-09-30 | 1 | CRS-GUP-DHI-DT-22-984 | 2022-11-08 | NC | DE-GUP-DT-E-23-027 | 2023-01-13 | 2 | CRS-GUP-DHI-DT-23-1527 | 2023-02-14 | NC | DE-GUP-DT-E-23-967 | 2023-12-01 | 3
| GUP | YL00 | P1 | PUR | 152702 |  | GUP-YL00-P1PUR-152702 | BLOCK DIAGRAM_CATHODIC PROTECTION SYSTEM | FA | 2022-07-29 | 2022-10-28 | 전력기술팀(Elec.) | 정민구 |  |  | G | FA | CATHODIC | CCPP | Cathodic Protection | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-967 | 2023-12-01 | 1 | 자체 CRS 개정 후 제출 | 2023-11-30 | N/A | DE-GUP-DT-E-22-485 | 2022-07-29 | A | CRS-GUP-DHI-DT-22-668 | 2022-08-22 | RC | DE-GUP-DT-E-22-731 | 2022-09-30 | B | CRS-GUP-DHI-DT-22-984 | 2022-11-08 | RC | DE-GUP-DT-E-23-027 | 2023-01-13 | C | CRS-GUP-DHI-DT-23-1527 | 2023-02-14 | AA | DE-GUP-DT-E-23-407 | 2023-03-31 | 0 | 자체 CRS 개정 후 제출 | 2023-11-30 | N/A | DE-GUP-DT-E-23-967 | 2023-12-01 | 1
| GUP | XG11 | P1 | PUR | 152706 |  | GUP-XG11-P1PUR-152706 | SCHEMATIC DIAGRAM_CATHODIC PROTECTION SYSTEM | FI | 2022-07-29 |  | 전력기술팀(Elec.) | 정민구 |  |  | G | FA | CATHODIC | CCPP | Cathodic Protection | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-967 | 2023-12-01 | 3 | CRS-GUP-DHI-DT-23-1527 | 2023-02-14 | NC | DE-GUP-DT-E-22-485 | 2022-07-29 | 0 | CRS-GUP-DHI-DT-22-668 | 2022-08-22 | RC | DE-GUP-DT-E-22-731 | 2022-09-30 | 1 | CRS-GUP-DHI-DT-22-984 | 2022-11-08 | NC | DE-GUP-DT-E-23-027 | 2023-01-13 | 2 | CRS-GUP-DHI-DT-23-1527 | 2023-02-14 | NC | DE-GUP-DT-E-23-967 | 2023-12-01 | 3
| GUP | YQ08 | P1 | CYA | 153311 |  | GUP-YQ08-P1CYA-153311 | COMMUNICATION LAYOUT DRAWING_MAINTENANCE WORKSHOP AND STORE BUILDING | FI | 2023-01-15 |  | 전력기술팀(Elec.) | 박경수 |  | P |  |  |  | CCPP | Communication | Elec. | 3 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-23-980 | 2023-12-08 | 2 | CRS-GUP-DHI-DT-23-2078 | 2023-07-27 | NC | DE-GUP-DT-E-23-171 | 2023-02-14 | 0 | CRS-GUP-DHI-DT-23-1632 | 2023-03-03 | NC | DE-GUP-DT-E-23-655 | 2023-06-30 | 1 | CRS-GUP-DHI-DT-23-2078 | 2023-07-27 | NC | DE-GUP-DT-E-23-980 | 2023-12-08 | 2
| GUP | YQ08 | P1 | CYA | 153312 |  | GUP-YQ08-P1CYA-153312 | COMMUNICATION LAYOUT DRAWING_WT & WWT BLDG & SHELTER | FI | 2022-08-31 |  | 전력기술팀(Elec.) | 박경수 |  | P |  |  |  | CCPP | Communication | Elec. | 3 | 2025-04-17 |  |  | DE-GUP-DT-E-23-639 | 2023-06-27 | 1 | CRS-GUP-DHI-DT-23-2059 | 2023-07-15 | NC | DE-GUP-DT-E-22-659 | 2022-09-14 | 0 | CRS-GUP-DHI-DT-22-881 | 2022-10-09 | NC | DE-GUP-DT-E-23-639 | 2023-06-27 | 1 | CRS-GUP-DHI-DT-23-2059 | 2023-07-15 | NC
| GUP | YQ08 | P1 | CYA | 153313 |  | GUP-YQ08-P1CYA-153313 | COMMUNICATION LAYOUT DRAWING_HRSG BUILDING | FI | 2022-09-28 |  | 전력기술팀(Elec.) | 박경수 |  | P |  |  |  | CCPP | Communication | Elec. | 3 | 2025-05-01 |  |  | DE-GUP-DT-E-23-639 | 2023-06-27 | 1 | CRS-GUP-DHI-DT-23-2059 | 2023-07-15 | NC | DE-GUP-DT-E-22-812 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1007 | 2022-11-13 | NC | DE-GUP-DT-E-23-639 | 2023-06-27 | 1 | CRS-GUP-DHI-DT-23-2059 | 2023-07-15 | NC
| GUP | YQ08 | P1 | CYA | 153314 |  | GUP-YQ08-P1CYA-153314 | COMMUNICATION LAYOUT DRAWING_STEAM TURBINE BUILDING | FI | 2022-09-07 |  | 전력기술팀(Elec.) | 박경수 |  | P |  |  |  | CCPP | Communication | Elec. | 3 | 2025-05-01 |  |  | DE-GUP-DT-E-23-639 | 2023-06-27 | 1 | CRS-GUP-DHI-DT-23-2059 | 2023-07-15 | NC | DE-GUP-DT-E-22-659 | 2022-09-14 | 0 | CRS-GUP-DHI-DT-22-881 | 2022-10-09 | NC | DE-GUP-DT-E-23-639 | 2023-06-27 | 1 | CRS-GUP-DHI-DT-23-2059 | 2023-07-15 | NC
| GUP | YQ08 | P1 | CYA | 153315 |  | GUP-YQ08-P1CYA-153315 | COMMUNICATION LAYOUT DRAWING_GAS TURBINE BUILDING | FI | 2022-07-12 |  | 전력기술팀(Elec.) | 박경수 |  | P |  |  |  | CCPP | Communication | Elec. | 3 | 2025-05-01 |  |  | DE-GUP-DT-E-23-759 | 2023-08-24 | 2 | CRS-GUP-DHI-DT-23-2059 | 2023-07-15 | NC | DE-GUP-DT-E-22-411 | 2022-07-18 | 0 | CRS-GUP-DHI-DT-22-615 | 2022-08-16 | NC | DE-GUP-DT-E-23-639 | 2023-06-27 | 1 | CRS-GUP-DHI-DT-23-2059 | 2023-07-15 | NC | DE-GUP-DT-E-23-759 | 2023-08-24 | 2
| GUP | YQ08 | P1 | CYA | 153316 |  | GUP-YQ08-P1CYA-153316 | COMMUNICATION LAYOUT DRAWING_BESS ELECTRICAL & CONTROL BUILDING | FI | 2022-10-19 |  | 전력기술팀(Elec.) | 박경수 |  | P |  |  |  | CCPP | Communication | Elec. | 3 | 2025-04-17 |  |  | DE-GUP-DT-E-23-639 | 2023-06-27 | 1 | CRS-GUP-DHI-DT-23-2059 | 2023-07-15 | NC | DE-GUP-DT-E-22-812 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1007 | 2022-11-13 | NC | DE-GUP-DT-E-23-639 | 2023-06-27 | 1 | CRS-GUP-DHI-DT-23-2059 | 2023-07-15 | NC
| GUP | YQ08 | P1 | CYA | 153317 |  | GUP-YQ08-P1CYA-153317 | COMMUNICATION LAYOUT DRAWING_SWITCHYARD CONTROL BUILDING | FI | 2022-03-12 |  | 전력기술팀(Elec.) | 박경수 |  | P | G | FI |  | CCPP | Communication | Elec. | 3 | 2025-04-17 |  |  | DE-GUP-DT-E-23-875 | 2023-10-27 | 3 | CRS-GUP-DHI-DT-24-052 | 2024-04-22 | NC | DHI-GUP-DT-21-132 | 2021-11-30 | 0 | CRS-GUP-DHI-DT-21-145 | 2022-01-12 | NC | DE-GUP-DT-E-23-020 | 2023-01-13 | 1 | CRS-GUP-DHI-DT-23-1654 | 2023-03-07 | RC | DE-GUP-DT-E-23-622 | 2023-06-16 | 2 | CRS-GUP-DHI-DT-23-2120 | 2023-10-18 | RC | DE-GUP-DT-E-23-875 | 2023-10-27 | 3 | CRS-GUP-DHI-DT-24-052 | 2024-04-22 | NC
| GUP | YQ08 | P1 | CYA | 153318 |  | GUP-YQ08-P1CYA-153318 | COMMUNICATION LAYOUT DRAWING_GATE HOUSE | FI | 2022-12-21 |  | 전력기술팀(Elec.) | 박경수 |  | P |  |  |  | CCPP | Communication | Elec. | 3 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-23-959 | 2023-11-30 | 2 | CRS-GUP-DHI-DT-23-2059 | 2023-07-15 | NC | DE-GUP-DT-E-23-020 | 2023-01-13 | 0 | CRS-GUP-DHI-DT-23-1557 | 2023-02-23 | NC | DE-GUP-DT-E-23-639 | 2023-06-27 | 1 | CRS-GUP-DHI-DT-23-2059 | 2023-07-15 | NC | DE-GUP-DT-E-23-959 | 2023-11-30 | 2
| GUP | YQ08 | P1 | CYA | 153319 |  | GUP-YQ08-P1CYA-153319 | COMMUNICATION LAYOUT DRAWING_CONTROL & ELECTRICAL BUILDING | FI | 2022-03-12 |  | 전력기술팀(Elec.) | 박경수 |  | P |  |  |  | CCPP | Communication | Elec. | 3 | 2025-05-01 |  |  | DE-GUP-DT-E-23-759 | 2023-08-24 | 3 | 자체 CRS 개정 후 제출 | 2023-08-23 | N/A | DHI-GUP-DT-21-132 | 2021-11-30 | 0 | CRS-GUP-DHI-DT-21-145 | 2022-01-12 | NC | DE-GUP-DT-E-23-020 | 2023-01-13 | 1 | CRS-GUP-DHI-DT-23-1525 | 2023-02-14 | NC | DE-GUP-DT-E-23-639 | 2023-06-27 | 2 | 자체 CRS 개정 후 제출 | 2023-08-23 | N/A | DE-GUP-DT-E-23-759 | 2023-08-24 | 3
| GUP | YQ08 | P1 | CYA | 153320 |  | GUP-YQ08-P1CYA-153320 | COMMUNICATION LAYOUT DRAWING_FIRE PROTECTION PUMP BUILDING | FI | 2022-09-28 |  | 전력기술팀(Elec.) | 박경수 |  | P |  |  |  | CCPP | Communication | Elec. | 3 | 2025-03-18 | 2025-03-31 |  | DE-GUP-DT-E-23-980 | 2023-12-08 | 2 | CRS-GUP-DHI-DT-23-2059 | 2023-07-15 | NC | DE-GUP-DT-E-22-812 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1007 | 2022-11-13 | NC | DE-GUP-DT-E-23-639 | 2023-06-27 | 1 | CRS-GUP-DHI-DT-23-2059 | 2023-07-15 | NC | DE-GUP-DT-E-23-980 | 2023-12-08 | 2
| GUP | YQ08 | P1 | CYA | 153321 |  | GUP-YQ08-P1CYA-153321 | COMMUNICATION LAYOUT DRAWING_ADMINISTRATION BUILDING | FI | 2022-11-16 |  | 전력기술팀(Elec.) | 박경수 |  | P |  |  |  | CCPP | Communication | Elec. | 3 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-23-980 | 2023-12-08 | 2 | 자체 CRS 개정 후 제출 | 2023-12-07 | N/A | DE-GUP-DT-E-23-020 | 2023-01-13 | 0 | CRS-GUP-DHI-DT-23-1557 | 2023-02-23 | NC | DE-GUP-DT-E-23-639 | 2023-06-27 | 1 | 자체 CRS 개정 후 제출 | 2023-12-07 | N/A | DE-GUP-DT-E-23-980 | 2023-12-08 | 2
| GUP | YQ08 | P1 | CYA | 153322 |  | GUP-YQ08-P1CYA-153322 | COMMUNICATION LAYOUT DRAWING - OUTDOOR TELEPHONE & PA | FI | 2023-03-08 |  | 전력기술팀(Elec.) | 박경수 |  | P |  |  |  | CCPP | Communication | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-655 | 2023-06-30 | 1 | CRS-GUP-DHI-DT-23-2078 | 2023-07-27 | NC | DE-GUP-DT-E-23-338 | 2023-03-22 | 0 | CRS-GUP-DHI-DT-23-1792 | 2023-03-30 | NC | DE-GUP-DT-E-23-655 | 2023-06-30 | 1 | CRS-GUP-DHI-DT-23-2078 | 2023-07-27 | NC
| GUP | YQ08 | P1 | CYA | 153323 |  | GUP-YQ08-P1CYA-153323 | COMMUNICATION LAYOUT DRAWING - OVERALL SECURITY CCTV | FI | 2023-03-08 |  | 전력기술팀(Elec.) | 박경수 |  | P |  |  |  | CCPP | Communication | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-975 | 2023-12-06 | 2 | CRS-GUP-DHI-DT-24-040 | 2024-03-18 | AA | DE-GUP-DT-E-23-338 | 2023-03-22 | 0 | CRS-GUP-DHI-DT-23-1792 | 2023-03-30 | NC | DE-GUP-DT-E-23-655 | 2023-06-30 | 1 | CRS-GUP-DHI-DT-23-2078 | 2023-07-27 | RC | DE-GUP-DT-E-23-975 | 2023-12-06 | 2 | CRS-GUP-DHI-DT-24-040 | 2024-03-18 | AA
| GUP | YE03 | P1 | BAU | 153111 |  | GUP-YE03-P1BAU-153111 | EARTHING LAYOUT DRAWING_MAINTENANCE WORKSHOP AND STORE BUILDING | FA | 2023-01-10 | 2023-04-10 | 전력기술팀(Elec.) | 박경수 | B | P |  |  |  | CCPP | Earthing | Elec. | 3 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-23-736 | 2023-08-08 | 1 | 자체 CRS 개정 후 제출 | 2023-08-07 | N/A | DE-GUP-DT-E-23-011 | 2023-01-12 | A | CRS-GUP-DHI-DT-23-1556 | 2023-02-23 | AA | DE-GUP-DT-E-23-263 | 2023-03-03 | 0 | 자체 CRS 개정 후 제출 | 2023-08-07 | N/A | DE-GUP-DT-E-23-736 | 2023-08-08 | 1
| GUP | YE01 | P1 | BAU | 153141 |  | GUP-YE01-P1BAU-153141 | LIGHTNING PROTECTION LAYOUT DRAWING_MAINTENANCE WORKSHOP AND STORE BUILDING | FI | 2023-01-10 |  | 전력기술팀(Elec.) | 박경수 |  | P |  |  |  | CCPP | Lightning | Elec. | 3 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-24-273 | 2024-11-15 | 2 | 자체 CRS 개정 후 제출 | 2024-11-14 | N/A | DE-GUP-DT-E-23-011 | 2023-01-12 | 0 | CRS-GUP-DHI-DT-23-1522 | 2023-02-14 | NC | DE-GUP-DT-E-23-736 | 2023-08-08 | 1 | 자체 CRS 개정 후 제출 | 2024-11-14 | N/A | DE-GUP-DT-E-24-273 | 2024-11-15 | 2
| GUP | YE03 | P1 | BAU | 153112 |  | GUP-YE03-P1BAU-153112 | EARTHING LAYOUT DRAWING_WT & WWT BLDG & SHELTER | FA | 2022-06-15 | 2022-10-26 | 전력기술팀(Elec.) | 박경수 | B | P |  |  |  | CCPP | Earthing | Elec. | 3 | 2025-04-17 |  |  | DE-GUP-DT-E-24-273 | 2024-11-15 | 2 | 자체 CRS 개정 후 제출 | 2024-11-14 | N/A | DE-GUP-DT-E-22-463 | 2022-07-27 | A | CRS-GUP-DHI-DT-22-639 | 2022-08-20 | RC | DE-GUP-DT-E-22-1200 | 2022-12-27 | B | CRS-GUP-DHI-DT-23-1439 | 2023-01-31 | AA | DE-GUP-DT-E-23-151 | 2023-02-09 | 0 | 자체 CRS 개정 후 제출 | 2023-07-23 | N/A | DE-GUP-DT-E-23-715 | 2023-07-24 | 1 | 자체 CRS 개정 후 제출 | 2024-11-14 | N/A | DE-GUP-DT-E-24-273 | 2024-11-15 | 2
| GUP | YE01 | P1 | BAU | 153142 |  | GUP-YE01-P1BAU-153142 | LIGHTNING PROTECTION LAYOUT DRAWING_WT & WWT BLDG & SHELTER | FI | 2022-08-15 |  | 전력기술팀(Elec.) | 박경수 |  | P |  |  |  | CCPP | Lightning | Elec. | 3 | 2025-04-17 |  |  | DE-GUP-DT-E-24-273 | 2024-11-15 | 3 | 자체 CRS 개정 후 제출 | 2024-11-14 | N/A | DE-GUP-DT-E-22-463 | 2022-07-27 | 0 | CRS-GUP-DHI-DT-22-639 | 2022-08-20 | RC | DE-GUP-DT-E-22-1200 | 2022-12-27 | 1 | CRS-GUP-DHI-DT-23-1439 | 2023-01-31 | NC | DE-GUP-DT-E-23-715 | 2023-07-24 | 2 | 자체 CRS 개정 후 제출 | 2024-11-14 | N/A | DE-GUP-DT-E-24-273 | 2024-11-15 | 3
| GUP | YE03 | P1 | BAU | 153113 |  | GUP-YE03-P1BAU-153113 | EARTHING LAYOUT DRAWING_HRSG BUILDING | FA | 2022-06-27 | 2022-09-25 | 전력기술팀(Elec.) | 박경수 | B | P |  |  |  | CCPP | Earthing | Elec. | 3 | 2025-05-01 |  |  | DE-GUP-DT-E-23-846 | 2023-10-11 | 1 | 자체 CRS 개정 후 제출 | 2023-10-10 | N/A | DE-GUP-DT-E-22-347 | 2022-06-29 | A | CRS-GUP-DHI-DT-22-538 | 2022-07-24 | RC | DE-GUP-DT-E-22-611 | 2022-09-02 | B | CRS-GUP-DHI-DT-22-847 | 2022-09-24 | RC | DE-GUP-DT-E-22-1009 | 2022-11-30 | C | CRS-GUP-DHI-DT-22-1268 | 2022-12-16 | RC | DE-GUP-DT-E-22-1200 | 2022-12-27 | D | CRS-GUP-DHI-DT-23-1439 | 2023-01-31 | AA | DE-GUP-DT-E-23-151 | 2023-02-09 | 0 | 자체 CRS 개정 후 제출 | 2023-10-10 | N/A | DE-GUP-DT-E-23-846 | 2023-10-11 | 1
| GUP | YE01 | P1 | BAU | 153143 |  | GUP-YE01-P1BAU-153143 | LIGHTNING PROTECTION LAYOUT DRAWING_HRSG BUILDING | FI | 2022-06-27 |  | 전력기술팀(Elec.) | 박경수 |  | P |  |  |  | CCPP | Lightning | Elec. | 3 | 2025-05-01 |  |  | DE-GUP-DT-E-24-273 | 2024-11-15 | 2 | 자체 CRS 개정 후 제출 | 2024-11-14 | N/A | DE-GUP-DT-E-22-347 | 2022-06-29 | 0 | CRS-GUP-DHI-DT-22-538 | 2022-07-24 | NC | DE-GUP-DT-E-23-846 | 2023-10-11 | 1 | 자체 CRS 개정 후 제출 | 2024-11-14 | N/A | DE-GUP-DT-E-24-273 | 2024-11-15 | 2
| GUP | YE03 | P1 | BAU | 153114 |  | GUP-YE03-P1BAU-153114 | EARTHING LAYOUT DRAWING_STEAM TURBINE BUILDING | FA | 2022-06-03 | 2022-09-25 | 전력기술팀(Elec.) | 박경수 | B | P |  |  |  | CCPP | Earthing | Elec. | 3 | 2025-05-01 |  |  | DE-GUP-DT-E-23-860 | 2023-10-19 | 2 | CRS-GUP-DHI-DT-23-1439 | 2023-01-31 | AA | DE-GUP-DT-E-22-463 | 2022-07-27 | A | CRS-GUP-DHI-DT-22-639 | 2022-08-20 | RC | DE-GUP-DT-E-22-692 | 2022-09-22 | B | CRS-GUP-DHI-DT-22-946 | 2022-10-22 | AA | DE-GUP-DT-E-22-1009 | 2022-11-30 | 0 | CRS-GUP-DHI-DT-22-1268 | 2022-12-16 | AA | DE-GUP-DT-E-22-1200 | 2022-12-27 | 1 | CRS-GUP-DHI-DT-23-1439 | 2023-01-31 | AA | DE-GUP-DT-E-23-860 | 2023-10-19 | 2
| GUP | YE01 | P1 | BAU | 153144 |  | GUP-YE01-P1BAU-153144 | LIGHTNING PROTECTION LAYOUT DRAWING_STEAM TURBINE BUILDING | FI | 2022-06-03 |  | 전력기술팀(Elec.) | 박경수 |  | P |  |  |  | CCPP | Lightning | Elec. | 3 | 2025-05-01 |  |  | DE-GUP-DT-E-24-273 | 2024-11-15 | 3 | 자체 CRS 개정 후 제출 | 2024-11-14 | N/A | DE-GUP-DT-E-22-463 | 2022-07-27 | 0 | CRS-GUP-DHI-DT-22-639 | 2022-08-20 | RC | DE-GUP-DT-E-22-692 | 2022-09-22 | 1 | CRS-GUP-DHI-DT-22-946 | 2022-10-22 | NC | DE-GUP-DT-E-23-860 | 2023-10-19 | 2 | 자체 CRS 개정 후 제출 | 2024-11-14 | N/A | DE-GUP-DT-E-24-273 | 2024-11-15 | 3
| GUP | YE03 | P1 | BAU | 153115 |  | GUP-YE03-P1BAU-153115 | EARTHING LAYOUT DRAWING_GAS TURBINE BUILDING | FA | 2022-04-27 | 2022-07-09 | 전력기술팀(Elec.) | 박경수 | B | P |  |  |  | CCPP | Earthing | Elec. | 3 | 2025-05-01 |  |  | DE-GUP-DT-E-24-022 | 2024-01-23 | 2 | CRS-GUP-DHI-DT-23-1732 | 2023-03-17 | AA | DHI-GUP-DT-22-021 | 2022-01-14 | A | CRS-GUP-DHI-DT-21-183 | 2022-02-04 | RC | DE-GUP-DT-E-22-484 | 2022-07-29 | B | CRS-GUP-DHI-DT-22-689 | 2022-08-22 | AA | DE-GUP-DT-E-22-611 | 2022-09-02 | 0 | CRS-GUP-DHI-DT-22-847 | 2022-09-24 | RC | DE-GUP-DT-E-23-183 | 2023-02-16 | 1 | CRS-GUP-DHI-DT-23-1732 | 2023-03-17 | AA | DE-GUP-DT-E-24-022 | 2024-01-23 | 2
| GUP | YE01 | P1 | BAU | 153145 |  | GUP-YE01-P1BAU-153145 | LIGHTNING PROTECTION LAYOUT DRAWING_GAS TURBINE BUILDING | FI | 2022-04-27 |  | 전력기술팀(Elec.) | 박경수 |  | P |  |  |  | CCPP | Lightning | Elec. | 3 | 2025-05-01 |  |  | DE-GUP-DT-E-24-273 | 2024-11-15 | 4 | 자체 CRS 개정 후 제출 | 2024-11-14 | N/A | DHI-GUP-DT-22-021 | 2022-01-14 | 0 | CRS-GUP-DHI-DT-21-183 | 2022-02-04 | NC | DE-GUP-DT-E-22-484 | 2022-07-29 | 1 | CRS-GUP-DHI-DT-22-655 | 2022-08-20 | NC | DE-GUP-DT-E-23-183 | 2023-02-16 | 2 | CRS-GUP-DHI-DT-23-1685 | 2023-03-13 | NC | DE-GUP-DT-E-24-022 | 2024-01-23 | 3 | 자체 CRS 개정 후 제출 | 2024-11-14 | N/A | DE-GUP-DT-E-24-273 | 2024-11-15 | 4
| GUP | YE03 | P1 | BAU | 153116 |  | GUP-YE03-P1BAU-153116 | EARTHING LAYOUT DRAWING_BESS ELECTRICAL & CONTROL BUILDING | FA | 2022-07-14 | 2022-10-12 | 전력기술팀(Elec.) | 박경수 | B | P |  |  |  | CCPP | Earthing | Elec. | 3 | 2025-04-17 |  |  | DE-GUP-DT-E-24-022 | 2024-01-23 | 1 | CRS-GUP-DHI-DT-23-1439 | 2023-01-31 | AA | DE-GUP-DT-E-22-463 | 2022-07-27 | A | CRS-GUP-DHI-DT-22-639 | 2022-08-20 | RC | DE-GUP-DT-E-22-1009 | 2022-11-30 | B | CRS-GUP-DHI-DT-22-1268 | 2022-12-16 | AA | DE-GUP-DT-E-22-1200 | 2022-12-27 | 0 | CRS-GUP-DHI-DT-23-1439 | 2023-01-31 | AA | DE-GUP-DT-E-24-022 | 2024-01-23 | 1
| GUP | YE01 | P1 | BAU | 153146 |  | GUP-YE01-P1BAU-153146 | LIGHTNING PROTECTION LAYOUT DRAWING_BESS ELECTRICAL & CONTROL BUILDING | FI | 2022-07-14 |  | 전력기술팀(Elec.) | 박경수 |  | P |  |  |  | CCPP | Lightning | Elec. | 3 | 2025-04-17 |  |  | DE-GUP-DT-E-24-273 | 2024-11-15 | 4 | 자체 CRS 개정 후 제출 | 2024-11-14 | N/A | DE-GUP-DT-E-22-463 | 2022-07-27 | 0 | CRS-GUP-DHI-DT-22-639 | 2022-08-20 | RC | DE-GUP-DT-E-22-1009 | 2022-11-30 | 1 | CRS-GUP-DHI-DT-22-1268 | 2022-12-16 | NC | DE-GUP-DT-E-22-1200 | 2022-12-27 | 2 | CRS-GUP-DHI-DT-23-1439 | 2023-01-31 | NC | DE-GUP-DT-E-24-022 | 2024-01-23 | 3 | 자체 CRS 개정 후 제출 | 2024-11-14 | N/A | DE-GUP-DT-E-24-273 | 2024-11-15 | 4
| GUP | YE03 | P1 | BAU | 153117 |  | GUP-YE03-P1BAU-153117 | EARTHING LAYOUT DRAWING_SWITCHYARD CONTROL BUILDING | FA | 2022-02-10 | 2022-05-11 | 전력기술팀(Elec.) | 박경수 | B | P | G | FI |  | CCPP | Earthing | Elec. | 3 | 2025-04-17 |  |  | DE-GUP-DT-E-24-034 | 2024-02-02 | 1 | 자체 CRS 개정 후 제출 | 2024-02-01 | N/A | DHI-GUP-DT-21-127 | 2021-11-29 | A | CRS-GUP-DHI-DT-21-117 | 2022-01-07 | RC | DE-GUP-DT-E-22-611 | 2022-09-02 | B | CRS-GUP-DHI-DT-22-847 | 2022-09-24 | RC | DE-GUP-DT-E-23-141 | 2023-02-08 | C | CRS-GUP-DHI-DT-23-1663 | 2023-03-09 | RC | DE-GUP-DT-E-23-433 | 2023-04-07 | D | CRS-GUP-DHI-DT-23-1935 | 2023-05-05 | RC | DE-GUP-DT-E-23-549 | 2023-05-12 | E | CRS-GUP-DHI-DT-23-2000 | 2023-06-15 | AA | DE-GUP-DT-E-23-626 | 2023-06-16 | 0 | 자체 CRS 개정 후 제출 | 2024-02-01 | N/A | DE-GUP-DT-E-24-034 | 2024-02-02 | 1
| GUP | YE01 | P1 | BAU | 153147 |  | GUP-YE01-P1BAU-153147 | LIGHTNING PROTECTION LAYOUT DRAWING_SWITCHYARD CONTROL BUILDING | FI | 2022-02-10 |  | 전력기술팀(Elec.) | 박경수 |  | P | G | FI |  | CCPP | Lightning | Elec. | 3 | 2025-04-17 |  |  | DE-GUP-DT-E-24-273 | 2024-11-15 | 2 | 자체 CRS 개정 후 제출 | 2024-11-14 | N/A | DHI-GUP-DT-21-127 | 2021-11-29 | 0 | CRS-GUP-DHI-DT-21-117 | 2022-01-07 | NC | DE-GUP-DT-E-24-034 | 2024-02-02 | 1 | 자체 CRS 개정 후 제출 | 2024-11-14 | N/A | DE-GUP-DT-E-24-273 | 2024-11-15 | 2
| GUP | YE03 | P1 | BAU | 153118 |  | GUP-YE03-P1BAU-153118 | EARTHING LAYOUT DRAWING_GATE HOUSE | FA | 2022-08-30 | 2023-01-15 | 전력기술팀(Elec.) | 박경수 | B | P |  |  |  | CCPP | Earthing | Elec. | 3 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-23-560 | 2023-05-17 | 1 | 자체 CRS 개정 후 제출 | 2023-05-16 | N/A | DE-GUP-DT-E-22-644 | 2022-09-08 | A | CRS-GUP-DHI-DT-22-874 | 2022-10-09 | RC | DE-GUP-DT-E-23-141 | 2023-02-08 | B | CRS-GUP-DHI-DT-23-1663 | 2023-03-09 | AA | DE-GUP-DT-E-23-350 | 2023-03-23 | 0 | 자체 CRS 개정 후 제출 | 2023-05-16 | N/A | DE-GUP-DT-E-23-560 | 2023-05-17 | 1
| GUP | YE01 | P1 | BAU | 153148 |  | GUP-YE01-P1BAU-153148 | LIGHTNING PROTECTION LAYOUT DRAWING_GATE HOUSE | FI | 2022-08-30 |  | 전력기술팀(Elec.) | 박경수 |  | P |  |  |  | CCPP | Lightning | Elec. | 3 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-23-560 | 2023-05-17 | 1 | CRS-GUP-DHI-DT-22-874 | 2022-10-09 | NC | DE-GUP-DT-E-22-644 | 2022-09-08 | 0 | CRS-GUP-DHI-DT-22-874 | 2022-10-09 | NC | DE-GUP-DT-E-23-560 | 2023-05-17 | 1
| GUP | YE03 | P1 | BAU | 153119 |  | GUP-YE03-P1BAU-153119 | EARTHING LAYOUT DRAWING_CONTROL & ELECTRICAL BUILDING | FA | 2022-02-10 | 2022-05-11 | 전력기술팀(Elec.) | 박경수 | B | P |  |  |  | CCPP | Earthing | Elec. | 3 | 2025-05-01 |  |  | DE-GUP-DT-E-24-273 | 2024-11-15 | 3 | CRS-GUP-DHI-DT-23-2007 | 2023-06-15 | AA | DHI-GUP-DT-21-127 | 2021-11-29 | A | CRS-GUP-DHI-DT-21-117 | 2022-01-07 | RC | DE-GUP-DT-E-22-347 | 2022-06-29 | B | CRS-GUP-DHI-DT-22-538 | 2022-07-24 | AA | DE-GUP-DT-E-22-470 | 2022-07-28 | 0 | 자체 CRS 개정 후 제출 | N/A | N/A | DE-GUP-DT-E-22-1200 | 2022-12-27 | 1 | CRS-GUP-DHI-DT-23-1439 | 2023-01-31 | AA | DE-GUP-DT-E-23-594 | 2023-05-31 | 2 | CRS-GUP-DHI-DT-23-2007 | 2023-06-15 | AA | DE-GUP-DT-E-24-273 | 2024-11-15 | 3
| GUP | YE01 | P1 | BAU | 153149 |  | GUP-YE01-P1BAU-153149 | LIGHTNING PROTECTION LAYOUT DRAWING_CONTROL & ELECTRICAL BUILDING | FI | 2022-02-10 |  | 전력기술팀(Elec.) | 박경수 |  | P |  |  |  | CCPP | Lightning | Elec. | 3 | 2025-05-01 |  |  | DE-GUP-DT-E-24-273 | 2024-11-15 | 4 | 자체 CRS 개정 후 제출 | 2024-11-14 | N/A | DHI-GUP-DT-21-127 | 2021-11-29 | 0 | CRS-GUP-DHI-DT-21-117 | 2022-01-07 | NC | DE-GUP-DT-E-22-347 | 2022-06-29 | 1 | CRS-GUP-DHI-DT-22-538 | 2022-07-24 | NC | DE-GUP-DT-E-23-594 | 2023-05-31 | 2 | CRS-GUP-DHI-DT-23-2007 | 2023-06-15 | NC | DE-GUP-DT-E-23-686 | 2023-07-12 | 3 | 자체 CRS 개정 후 제출 | 2024-11-14 | N/A | DE-GUP-DT-E-24-273 | 2024-11-15 | 4
| GUP | YE03 | P1 | BAU | 153120 |  | GUP-YE03-P1BAU-153120 | EARTHING LAYOUT DRAWING_AMMONIA STORAGE AND UNLOADING SHELTER | FA | 2022-08-31 | 2022-11-29 | 전력기술팀(Elec.) | 박경수 | B | P |  |  |  | CCPP | Earthing | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-560 | 2023-05-17 | 1 | CRS-GUP-DHI-DT-23-1439 | 2023-01-31 | AA | DE-GUP-DT-E-22-644 | 2022-09-08 | A | CRS-GUP-DHI-DT-22-874 | 2022-10-09 | RC | DE-GUP-DT-E-22-1009 | 2022-11-30 | B | CRS-GUP-DHI-DT-22-1268 | 2022-12-16 | AA | DE-GUP-DT-E-22-1200 | 2022-12-27 | 0 | CRS-GUP-DHI-DT-23-1439 | 2023-01-31 | AA | DE-GUP-DT-E-23-560 | 2023-05-17 | 1
| GUP | YE01 | P1 | BAU | 153150 |  | GUP-YE01-P1BAU-153150 | LIGHTNING PROTECTION LAYOUT DRAWING_AMMONIA STORAGE AND UNLOADING SHELTER | FI | 2022-08-31 |  | 전력기술팀(Elec.) | 박경수 |  | P |  |  |  | CCPP | Lightning | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-560 | 2023-05-17 | 1 | CRS-GUP-DHI-DT-22-874 | 2022-10-09 | NC | DE-GUP-DT-E-22-644 | 2022-09-08 | 0 | CRS-GUP-DHI-DT-22-874 | 2022-10-09 | NC | DE-GUP-DT-E-23-560 | 2023-05-17 | 1
| GUP | YE03 | P1 | BAU | 153121 |  | GUP-YE03-P1BAU-153121 | EARTHING LAYOUT DRAWING_FOAM STATION SHELTER | FA | 2022-07-22 | 2022-10-21 | 전력기술팀(Elec.) | 박경수 | B | P |  |  |  | CCPP | Earthing | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-560 | 2023-05-17 | 1 | 자체 CRS 개정 후 제출 | 2023-05-16 | N/A | DE-GUP-DT-E-22-470 | 2022-07-28 | A | CRS-GUP-DHI-DT-22-688 | 2022-08-22 | RC | DE-GUP-DT-E-23-141 | 2023-02-08 | B | CRS-GUP-DHI-DT-23-1663 | 2023-03-09 | AA | DE-GUP-DT-E-23-350 | 2023-03-23 | 0 | 자체 CRS 개정 후 제출 | 2023-05-16 | N/A | DE-GUP-DT-E-23-560 | 2023-05-17 | 1
| GUP | YE01 | P1 | BAU | 153151 |  | GUP-YE01-P1BAU-153151 | LIGHTNING PROTECTION LAYOUT DRAWING_FOAM STATION SHELTER | FI | 2022-07-22 |  | 전력기술팀(Elec.) | 박경수 |  | P |  |  |  | CCPP | Lightning | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-560 | 2023-05-17 | 2 | CRS-GUP-DHI-DT-23-1628 | 2023-03-02 | NC | DE-GUP-DT-E-22-470 | 2022-07-28 | 0 | CRS-GUP-DHI-DT-22-688 | 2022-08-22 | RC | DE-GUP-DT-E-23-141 | 2023-02-08 | 1 | CRS-GUP-DHI-DT-23-1628 | 2023-03-02 | NC | DE-GUP-DT-E-23-560 | 2023-05-17 | 2
| GUP | YE03 | P1 | BAU | 153122 |  | GUP-YE03-P1BAU-153122 | EARTHING LAYOUT DRAWING_CHEMICAL DOSING SHELTER FOR COOLING TOWER | FA | 2022-10-15 | 2023-02-10 | 전력기술팀(Elec.) | 박경수 | B | P |  |  |  | CCPP | Earthing | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-108 | 2024-04-19 | 2 | 자체 CRS 개정 후 제출 | 2024-04-18 | N/A | DE-GUP-DT-E-23-011 | 2023-01-12 | A | CRS-GUP-DHI-DT-23-1556 | 2023-02-23 | AA | DE-GUP-DT-E-23-263 | 2023-03-03 | 0 | 자체 CRS 개정 후 제출 | 2023-05-16 | N/A | DE-GUP-DT-E-23-560 | 2023-05-17 | 1 | 자체 CRS 개정 후 제출 | 2024-04-18 | N/A | DE-GUP-DT-E-24-108 | 2024-04-19 | 2
| GUP | YE01 | P1 | BAU | 153152 |  | GUP-YE01-P1BAU-153152 | LIGHTNING PROTECTION LAYOUT DRAWING_CHEMICAL DOSING SHELTER FOR COOLING TOWER | FI | 2022-10-15 |  | 전력기술팀(Elec.) | 박경수 |  | P |  |  |  | CCPP | Lightning | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-108 | 2024-04-19 | 2 | 자체 CRS 개정 후 제출 | 2024-04-18 | N/A | DE-GUP-DT-E-23-011 | 2023-01-12 | 0 | CRS-GUP-DHI-DT-23-1522 | 2023-02-14 | NC | DE-GUP-DT-E-23-560 | 2023-05-17 | 1 | 자체 CRS 개정 후 제출 | 2024-04-18 | N/A | DE-GUP-DT-E-24-108 | 2024-04-19 | 2
| GUP | YE03 | P1 | BAU | 153123 |  | GUP-YE03-P1BAU-153123 | EARTHING LAYOUT DRAWING_GCB SHELTER FOR ST (ABOVE ONLY) | FA | 2022-06-01 | 2022-10-15 | 전력기술팀(Elec.) | 박경수 | B | P |  |  |  | CCPP | Earthing | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-560 | 2023-05-17 | 1 | CRS-GUP-DHI-DT-23-1439 | 2023-01-31 | AA | DE-GUP-DT-E-22-463 | 2022-07-27 | A | CRS-GUP-DHI-DT-22-639 | 2022-08-20 | RC | DE-GUP-DT-E-22-1009 | 2022-11-30 | B | CRS-GUP-DHI-DT-22-1268 | 2022-12-16 | AA | DE-GUP-DT-E-22-1200 | 2022-12-27 | 0 | CRS-GUP-DHI-DT-23-1439 | 2023-01-31 | AA | DE-GUP-DT-E-23-560 | 2023-05-17 | 1
| GUP | YE01 | P1 | BAU | 153153 |  | GUP-YE01-P1BAU-153153 | LIGHTNING PROTECTION LAYOUT DRAWING_GCB SHELTER FOR ST (ABOVE ONLY) | FI | 2022-06-01 |  | 전력기술팀(Elec.) | 박경수 |  | P |  |  |  | CCPP | Lightning | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-560 | 2023-05-17 | 2 | CRS-GUP-DHI-DT-22-1268 | 2022-12-16 | NC | DE-GUP-DT-E-22-463 | 2022-07-27 | 0 | CRS-GUP-DHI-DT-22-639 | 2022-08-20 | RC | DE-GUP-DT-E-22-1009 | 2022-11-30 | 1 | CRS-GUP-DHI-DT-22-1268 | 2022-12-16 | NC | DE-GUP-DT-E-23-560 | 2023-05-17 | 2
| GUP | YE03 | P1 | BAU | 153124 |  | GUP-YE03-P1BAU-153124 | EARTHING LAYOUT DRAWING_ULSD PUMP AND TREATMENT SHELTER | FA | 2022-09-10 | 2023-02-27 | 전력기술팀(Elec.) | 박경수 | B | P |  |  |  | CCPP | Earthing | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-560 | 2023-05-17 | 1 | 자체 CRS 개정 후 제출 | 2023-05-16 | N/A | DE-GUP-DT-E-22-726 | 2022-09-29 | A | CRS-GUP-DHI-DT-22-953 | 2022-10-22 | AA | DE-GUP-DT-E-22-1031 | 2022-12-05 | 0 | 자체 CRS 개정 후 제출 | 2023-05-16 | N/A | DE-GUP-DT-E-23-560 | 2023-05-17 | 1
| GUP | YE01 | P1 | BAU | 153154 |  | GUP-YE01-P1BAU-153154 | LIGHTNING PROTECTION LAYOUT DRAWING_ULSD PUMP AND TREATMENT SHELTER | FI | 2022-09-10 |  | 전력기술팀(Elec.) | 박경수 |  | P |  |  |  | CCPP | Lightning | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-560 | 2023-05-17 | 1 | CRS-GUP-DHI-DT-22-953 | 2022-10-22 | NC | DE-GUP-DT-E-22-726 | 2022-09-29 | 0 | CRS-GUP-DHI-DT-22-953 | 2022-10-22 | NC | DE-GUP-DT-E-23-560 | 2023-05-17 | 1
| GUP | YE03 | P1 | BAU | 153126 |  | GUP-YE03-P1BAU-153126 | EARTHING LAYOUT DRAWING_COMPRESSED AIR PACKAGE SHELTER | FA | 2022-07-30 | 2022-10-28 | 전력기술팀(Elec.) | 박경수 | B | P |  |  |  | CCPP | Earthing | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-594 | 2023-05-31 | 1 | CRS-GUP-DHI-DT-23-2007 | 2023-06-15 | AA | DE-GUP-DT-E-22-541 | 2022-08-24 | A | CRS-GUP-DHI-DT-22-834 | 2022-09-23 | RC | DE-GUP-DT-E-22-1009 | 2022-11-30 | B | CRS-GUP-DHI-DT-22-1268 | 2022-12-16 | AA | DE-GUP-DT-E-22-1200 | 2022-12-27 | 0 | CRS-GUP-DHI-DT-23-1439 | 2023-01-31 | AA | DE-GUP-DT-E-23-594 | 2023-05-31 | 1 | CRS-GUP-DHI-DT-23-2007 | 2023-06-15 | AA
| GUP | YE01 | P1 | BAU | 153156 |  | GUP-YE01-P1BAU-153156 | LIGHTNING PROTECTION LAYOUT DRAWING_COMPRESSED AIR PACKAGE SHELTER | FI | 2022-07-30 |  | 전력기술팀(Elec.) | 박경수 |  | P |  |  |  | CCPP | Lightning | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-273 | 2024-11-15 | 2 | CRS-GUP-DHI-DT-23-2007 | 2023-06-15 | NC | DE-GUP-DT-E-22-541 | 2022-08-24 | 0 | CRS-GUP-DHI-DT-22-742 | 2022-09-12 | NC | DE-GUP-DT-E-23-594 | 2023-05-31 | 1 | CRS-GUP-DHI-DT-23-2007 | 2023-06-15 | NC | DE-GUP-DT-E-24-273 | 2024-11-15 | 2
| GUP | YE03 | P1 | BAU | 153127 |  | GUP-YE03-P1BAU-153127 | EARTHING LAYOUT DRAWING_FIRE PROTECTION PUMP BUILDING | FA | 2022-07-15 | 2022-10-10 | 전력기술팀(Elec.) | 박경수 | B | P |  |  |  | CCPP | Earthing | Elec. | 3 | 2025-03-18 | 2025-03-31 |  | DE-GUP-DT-E-23-594 | 2023-05-31 | 1 | CRS-GUP-DHI-DT-23-2007 | 2023-06-15 | AA | DE-GUP-DT-E-22-463 | 2022-07-27 | A | CRS-GUP-DHI-DT-22-639 | 2022-08-20 | RC | DE-GUP-DT-E-22-1009 | 2022-11-30 | B | CRS-GUP-DHI-DT-22-1268 | 2022-12-16 | AA | DE-GUP-DT-E-22-1200 | 2022-12-27 | 0 | CRS-GUP-DHI-DT-23-1439 | 2023-01-31 | AA | DE-GUP-DT-E-23-594 | 2023-05-31 | 1 | CRS-GUP-DHI-DT-23-2007 | 2023-06-15 | AA
| GUP | YE01 | P1 | BAU | 153157 |  | GUP-YE01-P1BAU-153157 | LIGHTNING PROTECTION LAYOUT DRAWING_FIRE PROTECTION PUMP BUILDING | FI | 2022-07-15 |  | 전력기술팀(Elec.) | 박경수 |  | P |  |  |  | CCPP | Lightning | Elec. | 3 | 2025-03-18 | 2025-03-31 |  | DE-GUP-DT-E-23-594 | 2023-05-31 | 2 | CRS-GUP-DHI-DT-23-2007 | 2023-06-15 | NC | DE-GUP-DT-E-22-463 | 2022-07-27 | 0 | CRS-GUP-DHI-DT-22-639 | 2022-08-20 | RC | DE-GUP-DT-E-22-1009 | 2022-11-30 | 1 | CRS-GUP-DHI-DT-22-1268 | 2022-12-16 | NC | DE-GUP-DT-E-23-594 | 2023-05-31 | 2 | CRS-GUP-DHI-DT-23-2007 | 2023-06-15 | NC
| GUP | YE03 | P1 | BAU | 153128 |  | GUP-YE03-P1BAU-153128 | EARTHING LAYOUT DRAWING_ADMINISTRATION BUILDING | FA | 2022-08-30 | 2022-11-20 | 전력기술팀(Elec.) | 박경수 | B | P |  |  |  | CCPP | Earthing | Elec. | 3 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-23-653 | 2023-06-29 | 1 | CRS-GUP-DHI-DT-23-1439 | 2023-01-31 | AA | DE-GUP-DT-E-22-644 | 2022-09-08 | A | CRS-GUP-DHI-DT-22-874 | 2022-10-09 | RC | DE-GUP-DT-E-22-1009 | 2022-11-30 | B | CRS-GUP-DHI-DT-22-1268 | 2022-12-16 | AA | DE-GUP-DT-E-22-1200 | 2022-12-27 | 0 | CRS-GUP-DHI-DT-23-1439 | 2023-01-31 | AA | DE-GUP-DT-E-23-653 | 2023-06-29 | 1
| GUP | YE01 | P1 | BAU | 153158 |  | GUP-YE01-P1BAU-153158 | LIGHTNING PROTECTION LAYOUT DRAWING_ADMINISTRATION BUILDING | FI | 2022-08-30 |  | 전력기술팀(Elec.) | 박경수 |  | P |  |  |  | CCPP | Lightning | Elec. | 3 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-24-273 | 2024-11-15 | 3 | 자체 CRS 개정 후 제출 | 2024-11-14 | N/A | DE-GUP-DT-E-22-644 | 2022-09-08 | 0 | CRS-GUP-DHI-DT-22-874 | 2022-10-09 | NC | DE-GUP-DT-E-22-1200 | 2022-12-27 | 1 | CRS-GUP-DHI-DT-23-1439 | 2023-01-31 | NC | DE-GUP-DT-E-23-653 | 2023-06-29 | 2 | 자체 CRS 개정 후 제출 | 2024-11-14 | N/A | DE-GUP-DT-E-24-273 | 2024-11-15 | 3
| GUP | YE03 | P1 | BAU | 153131 |  | GUP-YE03-P1BAU-153131 | EARTHING LAYOUT DRAWING_TRANSFORMER AREA | FA | 2022-08-30 | 2022-11-20 | 전력기술팀(Elec.) | 박경수 | B | P |  |  |  | CCPP | Earthing | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-860 | 2023-10-19 | 1 | CRS-GUP-DHI-DT-23-1931 | 2023-05-05 | AA | DE-GUP-DT-E-22-611 | 2022-09-02 | A | CRS-GUP-DHI-DT-22-847 | 2022-09-24 | RC | DE-GUP-DT-E-23-141 | 2023-02-08 | B | CRS-GUP-DHI-DT-23-1663 | 2023-03-09 | RC | DE-GUP-DT-E-23-433 | 2023-04-07 | C | CRS-GUP-DHI-DT-23-1872 | 2023-04-25 | AA | DE-GUP-DT-E-23-513 | 2023-04-27 | 0 | CRS-GUP-DHI-DT-23-1931 | 2023-05-05 | AA | DE-GUP-DT-E-23-860 | 2023-10-19 | 1
| GUP | YE01 | P1 | BAU | 153161 |  | GUP-YE01-P1BAU-153161 | LIGHTNING PROTECTION LAYOUT DRAWING_TRANSFORMER AREA | FI | 2022-08-30 |  | 전력기술팀(Elec.) | 박경수 |  | P |  |  |  | CCPP | Lightning | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-860 | 2023-10-19 | 2 | CRS-GUP-DHI-DT-23-1628 | 2023-03-02 | NC | DE-GUP-DT-E-22-611 | 2022-09-02 | 0 | CRS-GUP-DHI-DT-22-847 | 2022-09-24 | RC | DE-GUP-DT-E-23-141 | 2023-02-08 | 1 | CRS-GUP-DHI-DT-23-1628 | 2023-03-02 | NC | DE-GUP-DT-E-23-860 | 2023-10-19 | 2
| GUP | YE03 | P1 | BAU | 153132 |  | GUP-YE03-P1BAU-153132 | EARTHING LAYOUT DRAWING_COOLING TOWER | FA | 2022-12-30 | 2023-04-15 | 전력기술팀(Elec.) | 박경수 | B | P |  |  |  | CCPP | Earthing | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-022 | 2024-01-23 | 1 | 자체 CRS 개정 후 제출 | 2024-01-22 | N/A | DE-GUP-DT-E-22-1201 | 2022-12-27 | A | CRS-GUP-DHI-DT-23-1585 | 2023-02-28 | RC | DE-GUP-DT-E-23-309 | 2023-03-15 |  | CRS-GUP-DHI-DT-23-1785 | 2023-03-30 | AA | DE-GUP-DT-E-23-419 | 2023-04-04 | 0 | 자체 CRS 개정 후 제출 | 2024-01-22 | N/A | DE-GUP-DT-E-24-022 | 2024-01-23 | 1
| GUP | YE03 | P1 | BAU | 153133 |  | GUP-YE03-P1BAU-153133 | EARTHING LAYOUT DRAWING_TANK AREA | FA | 2023-05-26 | 2023-08-30 | 전력기술팀(Elec.) | 박경수 | B | P |  |  |  | CCPP | Earthing | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-003 | 2024-01-03 | 0 | CRS-GUP-DHI-DT-23-2144 | 2023-12-27 | AA | DE-GUP-DT-E-23-585 | 2023-05-30 | A | CRS-GUP-DHI-DT-23-2010 | 2023-06-21 | RC | DE-GUP-DT-E-23-654 | 2023-06-30 | B | CRS-GUP-DHI-DT-23-2064 | 2023-07-24 | RC | DE-GUP-DT-E-23-725 | 2023-07-27 | C | CRS-GUP-DHI-DT-23-2085 | 2023-08-02 | RC | DE-GUP-DT-E-23-760 | 2023-08-24 | D | CRS-GUP-DHI-DT-23-2103 | 2023-08-30 | RC | DE-GUP-DT-E-23-887 | 2023-11-08 | E | CRS-GUP-DHI-DT-23-2144 | 2023-12-27 | AA | DE-GUP-DT-E-24-003 | 2024-01-03 | 0
| GUP | YD04 | P1 | ZEN | 152903 |  | GUP-YD04-P1ZEN-152903 | CABLE TRAY LAYOUT DRAWING_MAINTENANCE WORKSHOP AND STORE BUILDING | FI | 2023-01-26 |  | 전력기술팀(Elec.) | 허규범 | [5 empty] | CCPP | Raceway | Elec. | 3 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-22-1213 | 2023-01-04 | 0 | CRS-GUP-DHI-DT-22-1460 | 2023-02-05 | NC | DE-GUP-DT-E-22-1213 | 2023-01-04 | 0 | CRS-GUP-DHI-DT-22-1460 | 2023-02-05 | NC
| GUP | YD04 | P1 | ZEN | 152904 |  | GUP-YD04-P1ZEN-152904 | CABLE TRAY LAYOUT DRAWING_WT & WWT BLDG & SHELTER | FI | 2022-10-11 |  | 전력기술팀(Elec.) | 허규범 | [5 empty] | CCPP | Raceway | Elec. | 3 | 2025-04-17 |  |  | DE-GUP-DT-E-23-237 | 2023-02-23 | 1 | CRS-GUP-DHI-DT-23-1602 | 2023-03-01 | NC | DE-GUP-DT-E-22-899 | 2022-11-03 | 0 | CRS-GUP-DHI-DT-22-1198 | 2022-11-30 | NC | DE-GUP-DT-E-23-237 | 2023-02-23 | 1 | CRS-GUP-DHI-DT-23-1602 | 2023-03-01 | NC
| GUP | YD04 | P1 | ZEN | 152905 |  | GUP-YD04-P1ZEN-152905 | CABLE TRAY LAYOUT DRAWING_HRSG BUILDING | FA | 2022-07-20 | 2022-11-30 | 전력기술팀(Elec.) | 허규범 | [5 empty] | CCPP | Raceway | Elec. | 3 | 2025-05-01 |  |  | DE-GUP-DT-E-23-392 | 2023-03-30 | 0 | CRS-GUP-DHI-DT-23-1642 | 2023-03-04 | AA | DE-GUP-DT-E-22-436 | 2022-07-22 | A | CRS-GUP-DHI-DT-22-576 | 2022-08-03 | RC | DE-GUP-DT-E-23-233 | 2023-02-23 | B | CRS-GUP-DHI-DT-23-1642 | 2023-03-04 | AA | DE-GUP-DT-E-23-392 | 2023-03-30 | 0
| GUP | YD04 | P1 | ZEN | 152906 |  | GUP-YD04-P1ZEN-152906 | CABLE TRAY LAYOUT DRAWING_STEAM TURBINE BUILDING | FA | 2022-08-30 | 2022-12-10 | 전력기술팀(Elec.) | 허규범 | [5 empty] | CCPP | Raceway | Elec. | 3 | 2025-05-01 |  |  | DE-GUP-DT-E-23-166 | 2023-02-13 | 0 | CRS-GUP-DHI-DT-22-1459 | 2023-02-05 | AA | DE-GUP-DT-E-22-625 | 2022-09-07 | A | CRS-GUP-DHI-DT-22-870 | 2022-10-09 | RC | DE-GUP-DT-E-22-1190 | 2022-12-23 | B | CRS-GUP-DHI-DT-22-1459 | 2023-02-05 | AA | DE-GUP-DT-E-23-166 | 2023-02-13 | 0
| GUP | YD04 | P1 | ZEN | 152907 |  | GUP-YD04-P1ZEN-152907 | CABLE TRAY LAYOUT DRAWING_GAS TURBINE BUILDING | FA | 2022-04-10 | 2022-07-10 | 전력기술팀(Elec.) | 허규범 | [5 empty] | CCPP | Raceway | Elec. | 3 | 2025-05-01 |  |  | DE-GUP-DT-E-24-150 | 2024-06-27 | 1 | 자체 CRS 개정 후 제출 | 2024-06-10 | N/A | DHI-GUP-DT-22-003 | 2022-01-04 | 0 | CRS-GUP-DHI-DT-21-170 | 2022-01-24 | RC | DE-GUP-DT-E-22-327 | 2022-06-22 | 1 | CRS-GUP-DHI-DT-22-552 | 2022-07-27 | NC | DE-GUP-DT-E-22-571 | 2022-08-26 | 0 | 자체 CRS 개정 후 제출 | 2024-06-10 | N/A | DE-GUP-DT-E-24-150 | 2024-06-27 | 1
| GUP | YD04 | P1 | ZEN | 152908 |  | GUP-YD04-P1ZEN-152908 | CABLE TRAY LAYOUT DRAWING_PIPE RACK | FA | 2022-03-13 | 2022-10-20 | 전력기술팀(Elec.) | 허규범 | [5 empty] | CCPP | Raceway | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-863 | 2023-10-23 | 1 | CRS-GUP-DHI-DT-22-950 | 2022-10-22 | AA | DHI-GUP-DT-21-133 | 2021-11-30 | 0 | CRS-GUP-DHI-DT-21-145 | 2022-01-12 | NC | DE-GUP-DT-E-22-710 | 2022-09-28 | 0 | CRS-GUP-DHI-DT-22-950 | 2022-10-22 | AA | DE-GUP-DT-E-23-863 | 2023-10-23 | 1
| GUP | YD04 | P1 | ZEN | 152911 |  | GUP-YD04-P1ZEN-152911 | CABLE TRAY LAYOUT DRAWING_CONTROL & ELECTRICAL BUILDING | FA | 2022-02-10 | 2022-05-10 | 전력기술팀(Elec.) | 허규범 | [5 empty] | CCPP | Raceway | Elec. | 3 | 2025-05-01 |  |  | DE-GUP-DT-E-23-743 | 2023-08-17 | 2 | 자체 CRS 개정 후 제출 | 2023-08-16 | N/A | DHI-GUP-DT-21-112 | 2021-11-22 | 0 | CRS-GUP-DHI-DT-21-147 | 2022-01-12 | NC | DE-GUP-DT-E-22-684 | 2022-09-21 | 0 | CRS-GUP-DHI-DT-22-1118 | 2022-11-23 | AA | DE-GUP-DT-E-23-377 | 2023-03-27 | 1 | 자체 CRS 개정 후 제출 | 2023-08-16 | N/A | DE-GUP-DT-E-23-743 | 2023-08-17 | 2
| GUP | YD04 | P1 | ZEN | 152912 |  | GUP-YD04-P1ZEN-152912 | CABLE TRAY LAYOUT DRAWING_ADMINISTRATION BUILDING | FA | 2022-09-20 | 2023-01-03 | 전력기술팀(Elec.) | 허규범 | [5 empty] | CCPP | Raceway | Elec. | 3 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-23-392 | 2023-03-30 | 0 | CRS-GUP-DHI-DT-23-1594 | 2023-02-28 | AA | DE-GUP-DT-E-22-710 | 2022-09-28 | A | CRS-GUP-DHI-DT-22-950 | 2022-10-22 | RC | DE-GUP-DT-E-23-160 | 2023-02-13 | B | CRS-GUP-DHI-DT-23-1594 | 2023-02-28 | AA | DE-GUP-DT-E-23-392 | 2023-03-30 | 0
| GUP | YD04 | P1 | ZEN | 152913 |  | GUP-YD04-P1ZEN-152913 | CABLE TRAY LAYOUT DRAWING_PIPE SLEEPER & TRENCH (CCPP PLANT AREA) | FA | 2022-03-12 | 2022-06-12 | 전력기술팀(Elec.) | 허규범 | [5 empty] | CCPP | Raceway | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1199 | 2022-12-27 | 0 | CRS-GUP-DHI-DT-23-1507 | 2023-02-14 | AA | DHI-GUP-DT-21-134 | 2021-11-30 | 0 | CRS-GUP-DHI-DT-21-145 | 2022-01-12 | NC | DE-GUP-DT-E-22-1199 | 2022-12-27 | 0 | CRS-GUP-DHI-DT-23-1507 | 2023-02-14 | AA
| GUP | YD04 | P1 | ZEN | 152914 |  | GUP-YD04-P1ZEN-152914 | CABLE TRAY LAYOUT DRAWING_COOLING TOWER | FA | 2022-09-23 | 2023-01-30 | 전력기술팀(Elec.) | 허규범 | [5 empty] | CCPP | Raceway | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-392 | 2023-03-30 | 0 | CRS-GUP-DHI-DT-23-1594 | 2023-02-28 | AA | DE-GUP-DT-E-22-782 | 2022-10-11 | A | CRS-GUP-DHI-DT-22-987 | 2022-11-08 | RC | DE-GUP-DT-E-23-160 | 2023-02-13 | B | CRS-GUP-DHI-DT-23-1594 | 2023-02-28 | AA | DE-GUP-DT-E-23-392 | 2023-03-30 | 0
| GUP | YE00 | P1 | ZEN | 153012 |  | GUP-YE00-P1ZEN-153012 | EMBEDDED CONDUIT LAYOUT DRAWING_MAINTENANCE WORKSHOP AND STORE BUILDING | FI | 2022-12-27 |  | 전력기술팀(Elec.) | 허규범 | [5 empty] | CCPP | Raceway | Elec. | 3 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-24-030 | 2024-01-31 | 1 | CRS-GUP-DHI-DT-22-1460 | 2023-02-05 | NC | DE-GUP-DT-E-22-1213 | 2023-01-04 | 0 | CRS-GUP-DHI-DT-22-1460 | 2023-02-05 | NC | DE-GUP-DT-E-24-030 | 2024-01-31 | 1
| GUP | YE00 | P1 | ZEN | 153013 |  | GUP-YE00-P1ZEN-153013 | EMBEDDED CONDUIT LAYOUT DRAWING_WT & WWT BLDG & SHELTER | FI | 2022-08-20 |  | 전력기술팀(Elec.) | 허규범 | [5 empty] | CCPP | Raceway | Elec. | 3 | 2025-04-17 |  |  | DE-GUP-DT-E-23-043 | 2023-01-18 | 1 | CRS-GUP-DHI-DT-23-1559 | 2023-02-23 | NC | DE-GUP-DT-E-22-612 | 2022-09-02 | 0 | CRS-GUP-DHI-DT-22-801 | 2022-09-19 | NC | DE-GUP-DT-E-23-043 | 2023-01-18 | 1 | CRS-GUP-DHI-DT-23-1559 | 2023-02-23 | NC
| GUP | YE00 | P1 | ZEN | 153014 |  | GUP-YE00-P1ZEN-153014 | EMBEDDED CONDUIT LAYOUT DRAWING_HRSG BUILDING | FI | 2022-06-26 |  | 전력기술팀(Elec.) | 허규범 | [5 empty] | CCPP | Raceway | Elec. | 3 | 2025-05-01 |  |  | DE-GUP-DT-E-24-032 | 2024-02-01 | 2 | CRS-GUP-DHI-DT-22-1292 | 2022-12-21 | NC | DE-GUP-DT-E-22-338 | 2022-06-27 | 0 | CRS-GUP-DHI-DT-22-553 | 2022-07-27 | NC | DE-GUP-DT-E-22-1058 | 2022-12-09 | 1 | CRS-GUP-DHI-DT-22-1292 | 2022-12-21 | NC | DE-GUP-DT-E-24-032 | 2024-02-01 | 2
| GUP | YE00 | P1 | ZEN | 153015 |  | GUP-YE00-P1ZEN-153015 | EMBEDDED CONDUIT LAYOUT DRAWING_STEAM TURBINE BUILDING | FI | 2022-07-26 |  | 전력기술팀(Elec.) | 허규범 | [5 empty] | CCPP | Raceway | Elec. | 3 | 2025-05-01 |  |  | DE-GUP-DT-E-24-032 | 2024-02-01 | 4 | CRS-GUP-DHI-DT-23-2075 | 2023-07-27 | NC | DE-GUP-DT-E-22-460 | 2022-07-27 | 0 | CRS-GUP-DHI-DT-22-679 | 2022-08-22 | NC | DE-GUP-DT-E-22-683 | 2022-09-21 | 1 | CRS-GUP-DHI-DT-22-941 | 2022-10-22 | NC | DE-GUP-DT-E-22-1191 | 2022-12-23 | 2 | CRS-GUP-DHI-DT-22-1349 | 2022-12-28 | NC | DE-GUP-DT-E-23-681_Rev 3 | 2023-07-07 | 3 | CRS-GUP-DHI-DT-23-2075 | 2023-07-27 | NC | DE-GUP-DT-E-24-032 | 2024-02-01 | 4
| GUP | YE00 | P1 | ZEN | 153016 |  | GUP-YE00-P1ZEN-153016 | EMBEDDED CONDUIT LAYOUT DRAWING_GAS TURBINE BUILDING | FI | 2022-04-10 |  | 전력기술팀(Elec.) | 허규범 | [5 empty] | CCPP | Raceway | Elec. | 3 | 2025-05-01 |  |  | DE-GUP-DT-E-23-793 | 2023-09-06 | 3 | CRS-GUP-DHI-DT-23-1559 | 2023-02-23 | NC | DHI-GUP-DT-22-002 | 2022-01-04 | 0 | CRS-GUP-DHI-DT-21-168 | 2022-01-22 | NC | DE-GUP-DT-E-22-710 | 2022-09-28 | 1 | CRS-GUP-DHI-DT-22-950 | 2022-10-22 | NC | DE-GUP-DT-E-23-043 | 2023-01-18 | 2 | CRS-GUP-DHI-DT-23-1559 | 2023-02-23 | NC | DE-GUP-DT-E-23-793 | 2023-09-06 | 3
| GUP | YE00 | P1 | ZEN | 153019 |  | GUP-YE00-P1ZEN-153019 | EMBEDDED CONDUIT LAYOUT DRAWING_GATE HOUSE | FI | 2022-08-20 |  | 전력기술팀(Elec.) | 허규범 | [5 empty] | CCPP | Raceway | Elec. | 3 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-23-170 | 2023-02-14 | 1 | CRS-GUP-DHI-DT-23-1596 | 2023-02-28 | NC | DE-GUP-DT-E-22-574 | 2022-08-29 | 0 | CRS-GUP-DHI-DT-22-836 | 2022-09-23 | RC | DE-GUP-DT-E-23-170 | 2023-02-14 | 1 | CRS-GUP-DHI-DT-23-1596 | 2023-02-28 | NC
| GUP | YE00 | P1 | ZEN | 153021 |  | GUP-YE00-P1ZEN-153021 | EMBEDDED CONDUIT LAYOUT DRAWING_FIRE PROTECTION PUMP BUILDING | FI | 2022-07-10 |  | 전력기술팀(Elec.) | 허규범 | [5 empty] | CCPP | Raceway | Elec. | 3 | 2025-03-18 | 2025-03-31 |  | DE-GUP-DT-E-22-926 | 2022-11-09 | 1 | CRS-GUP-DHI-DT-22-1056 | 2022-11-17 | NC | DE-GUP-DT-E-22-423 | 2022-07-21 | 0 | CRS-GUP-DHI-DT-22-619 | 2022-08-16 | NC | DE-GUP-DT-E-22-926 | 2022-11-09 | 1 | CRS-GUP-DHI-DT-22-1056 | 2022-11-17 | NC
| GUP | YE00 | P1 | ZEN | 153022 |  | GUP-YE00-P1ZEN-153022 | EMBEDDED CONDUIT LAYOUT DRAWING_ADMINISTRATION BUILDING | FI | 2022-08-20 |  | 전력기술팀(Elec.) | 허규범 | [5 empty] | CCPP | Raceway | Elec. | 3 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-24-032 | 2024-02-01 | 2 | CRS-GUP-DHI-DT-23-1559 | 2023-02-23 | NC | DE-GUP-DT-E-22-574 | 2022-08-29 | 0 | CRS-GUP-DHI-DT-22-836 | 2022-09-23 | RC | DE-GUP-DT-E-23-043 | 2023-01-18 | 1 | CRS-GUP-DHI-DT-23-1559 | 2023-02-23 | NC | DE-GUP-DT-E-24-032 | 2024-02-01 | 2
| GUP | YE00 | P1 | ZEN | 153023 |  | GUP-YE00-P1ZEN-153023 | EMBEDDED CONDUIT LAYOUT DRAWING_TRANSFORMER AREA | FI | 2022-06-26 |  | 전력기술팀(Elec.) | 허규범 | [5 empty] | CCPP | Raceway | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-793 | 2023-09-06 | 2 | CRS-GUP-DHI-DT-23-1559 | 2023-02-23 | NC | DE-GUP-DT-E-22-423 | 2022-07-21 | 0 | CRS-GUP-DHI-DT-22-619 | 2022-08-16 | NC | DE-GUP-DT-E-23-043 | 2023-01-18 | 1 | CRS-GUP-DHI-DT-23-1559 | 2023-02-23 | NC | DE-GUP-DT-E-23-793 | 2023-09-06 | 2
| GUP | YE00 | P1 | ZEN | 153024 |  | GUP-YE00-P1ZEN-153024 | EMBEDDED CONDUIT LAYOUT DRAWING_COMPRESSED AIR PACKAGE SHELTER | FI | 2022-07-20 |  | 전력기술팀(Elec.) | 허규범 | [5 empty] | CCPP | Raceway | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-870 | 2023-10-25 | 2 | CRS-GUP-DHI-DT-22-1350 | 2022-12-28 | NC | DE-GUP-DT-E-22-423 | 2022-07-21 | 0 | CRS-GUP-DHI-DT-22-619 | 2022-08-16 | NC | DE-GUP-DT-E-22-1192 | 2022-12-23 | 1 | CRS-GUP-DHI-DT-22-1350 | 2022-12-28 | NC | DE-GUP-DT-E-23-870 | 2023-10-25 | 2
| GUP | YE00 | P1 | ZEN | 153025 |  | GUP-YE00-P1ZEN-153025 | EMBEDDED CONDUIT LAYOUT DRAWING_ULSD PUMP AND TREATMENT SHELTER | FI | 2022-09-15 |  | 전력기술팀(Elec.) | 허규범 | [5 empty] | CCPP | Raceway | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-793 | 2023-09-06 | 1 | CRS-GUP-DHI-DT-22-940 | 2022-10-22 | NC | DE-GUP-DT-E-22-682 | 2022-09-21 | 0 | CRS-GUP-DHI-DT-22-940 | 2022-10-22 | NC | DE-GUP-DT-E-23-793 | 2023-09-06 | 1
| GUP | YE00 | P1 | ZEN | 153026 |  | GUP-YE00-P1ZEN-153026 | EMBEDDED CONDUIT LAYOUT DRAWING_MISCELLANEOUS area | FI | 2023-02-15 |  | 전력기술팀(Elec.) | 허규범 | [5 empty] | CCPP | Raceway | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-032 | 2024-02-01 | 2 | 자체 CRS 개정 후 제출 | 2024-01-31 | N/A | DE-GUP-DT-E-23-245 | 2023-02-24 | 0 | CRS-GUP-DHI-DT-23-1604 | 2023-03-01 | NC | DE-GUP-DT-E-23-793 | 2023-09-06 | 1 | 자체 CRS 개정 후 제출 | 2024-01-31 | N/A | DE-GUP-DT-E-24-032 | 2024-02-01 | 2
| GUP | XW03 | P1 | ZEN | 153241 |  | GUP-XW03-P1ZEN-153241 | ILLUMINATION CALCULATION_MAINTENANCE WORKSHOP AND STORE BUILDING | FI | 2023-01-10 |  | 전력기술팀(Elec.) | 고승호 | [5 empty] | CCPP | Lighting & Small Power | Elec. | 3 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-24-158 | 2024-06-17 | 1 | CRS-GUP-DHI-DT-23-1603 | 2023-03-01 | NC | DE-GUP-DT-E-23-243 | 2023-02-24 | 0 | CRS-GUP-DHI-DT-23-1603 | 2023-03-01 | NC | DE-GUP-DT-E-24-158 | 2024-06-17 | 1
| GUP | YZ03 | P1 | ZEN | 153211 |  | GUP-YZ03-P1ZEN-153211 | LIGHTING & SMALL POWER LAYOUT DRAWING_MAINTENANCE WORKSHOP AND STORE BUILDING | FI | 2023-01-10 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-24-158 | 2024-06-17 | 1 | CRS-GUP-DHI-DT-23-1603 | 2023-03-01 | NC | DE-GUP-DT-E-23-243 | 2023-02-24 | 0 | CRS-GUP-DHI-DT-23-1603 | 2023-03-01 | NC | DE-GUP-DT-E-24-158 | 2024-06-17 | 1
| GUP | YB11 | P1 | ZEN | 153271 |  | GUP-YB11-P1ZEN-153271 | LIGHTING PANEL BOARD SCHEDULE_MAINTENANCE WORKSHOP AND STORE BUILDING | FI | 2023-01-10 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-24-158 | 2024-06-17 | 1 | CRS-GUP-DHI-DT-23-1603 | 2023-03-01 | NC | DE-GUP-DT-E-23-243 | 2023-02-24 | 0 | CRS-GUP-DHI-DT-23-1603 | 2023-03-01 | NC | DE-GUP-DT-E-24-158 | 2024-06-17 | 1
| GUP | XW03 | P1 | ZEN | 153242 |  | GUP-XW03-P1ZEN-153242 | ILLUMINATION CALCULATION_WT & WWT BLDG & SHELTER | FI | 2022-09-13 |  | 전력기술팀(Elec.) | 고승호 | [5 empty] | CCPP | Lighting & Small Power | Elec. | 3 | 2025-04-17 |  |  | DE-GUP-DT-E-22-811 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1098 | 2022-11-21 | NC | DE-GUP-DT-E-22-811 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1098 | 2022-11-21 | NC
| GUP | YZ03 | P1 | ZEN | 153212 |  | GUP-YZ03-P1ZEN-153212 | LIGHTING & SMALL POWER LAYOUT DRAWING_WT & WWT BLDG & SHELTER | FI | 2022-09-13 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-04-17 |  |  | DE-GUP-DT-E-22-811 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1098 | 2022-11-21 | NC | DE-GUP-DT-E-22-811 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1098 | 2022-11-21 | NC
| GUP | YB11 | P1 | ZEN | 153272 |  | GUP-YB11-P1ZEN-153272 | LIGHTING PANEL BOARD SCHEDULE_WT & WWT BLDG & SHELTER | FI | 2022-09-13 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-04-17 |  |  | DE-GUP-DT-E-22-811 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1098 | 2022-11-21 | NC | DE-GUP-DT-E-22-811 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1098 | 2022-11-21 | NC
| GUP | XW03 | P1 | ZEN | 153243 |  | GUP-XW03-P1ZEN-153243 | ILLUMINATION CALCULATION_HRSG BUILDING | FI | 2022-07-27 |  | 전력기술팀(Elec.) | 고승호 | [5 empty] | CCPP | Lighting & Small Power | Elec. | 3 | 2025-05-01 |  |  | DE-GUP-DT-E-23-622 | 2023-06-16 | 1 | CRS-GUP-DHI-DT-23-2026 | 2023-07-04 | NC | DE-GUP-DT-E-22-560 | 2022-08-26 | 0 | CRS-GUP-DHI-DT-22-835 | 2022-09-23 | NC | DE-GUP-DT-E-23-622 | 2023-06-16 | 1 | CRS-GUP-DHI-DT-23-2026 | 2023-07-04 | NC
| GUP | YZ03 | P1 | ZEN | 153213 |  | GUP-YZ03-P1ZEN-153213 | LIGHTING & SMALL POWER LAYOUT DRAWING_HRSG BUILDING | FI | 2022-07-27 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-05-01 |  |  | DE-GUP-DT-E-23-622 | 2023-06-16 | 1 | CRS-GUP-DHI-DT-23-2026 | 2023-07-04 | NC | DE-GUP-DT-E-22-560 | 2022-08-26 | 0 | CRS-GUP-DHI-DT-22-835 | 2022-09-23 | RC | DE-GUP-DT-E-23-622 | 2023-06-16 | 1 | CRS-GUP-DHI-DT-23-2026 | 2023-07-04 | NC
| GUP | YB11 | P1 | ZEN | 153273 |  | GUP-YB11-P1ZEN-153273 | LIGHTING PANEL BOARD SCHEDULE_HRSG BUILDING | FI | 2022-07-27 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-05-01 |  |  | DE-GUP-DT-E-23-622 | 2023-06-16 | 1 | CRS-GUP-DHI-DT-23-2026 | 2023-07-04 | NC | DE-GUP-DT-E-22-560 | 2022-08-26 | 0 | CRS-GUP-DHI-DT-22-835 | 2022-09-23 | NC | DE-GUP-DT-E-23-622 | 2023-06-16 | 1 | CRS-GUP-DHI-DT-23-2026 | 2023-07-04 | NC
| GUP | XW03 | P1 | ZEN | 153244 |  | GUP-XW03-P1ZEN-153244 | ILLUMINATION CALCULATION_STEAM TURBINE BUILDING | FI | 2022-07-03 |  | 전력기술팀(Elec.) | 고승호 | [5 empty] | CCPP | Lighting & Small Power | Elec. | 3 | 2025-05-01 |  |  | DE-GUP-DT-E-23-838 | 2023-10-05 | 1 | CRS-GUP-DHI-DT-22-608 | 2022-08-16 | NC | DE-GUP-DT-E-22-371 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-608 | 2022-08-16 | NC | DE-GUP-DT-E-23-838 | 2023-10-05 | 1
| GUP | YZ03 | P1 | ZEN | 153214 |  | GUP-YZ03-P1ZEN-153214 | LIGHTING & SMALL POWER LAYOUT DRAWING_STEAM TURBINE BUILDING | FI | 2022-07-03 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-05-01 |  |  | DE-GUP-DT-E-23-838 | 2023-10-05 | 1 | CRS-GUP-DHI-DT-22-608 | 2022-08-16 | NC | DE-GUP-DT-E-22-371 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-608 | 2022-08-16 | NC | DE-GUP-DT-E-23-838 | 2023-10-05 | 1
| GUP | YB11 | P1 | ZEN | 153274 |  | GUP-YB11-P1ZEN-153274 | LIGHTING PANEL BOARD SCHEDULE_STEAM TURBINE BUILDING | FI | 2022-07-03 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-05-01 |  |  | DE-GUP-DT-E-23-838 | 2023-10-05 | 1 | CRS-GUP-DHI-DT-22-608 | 2022-08-16 | NC | DE-GUP-DT-E-22-371 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-608 | 2022-08-16 | NC | DE-GUP-DT-E-23-838 | 2023-10-05 | 1
| GUP | XW03 | P1 | ZEN | 153245 |  | GUP-XW03-P1ZEN-153245 | ILLUMINATION CALCULATION_GAS TURBINE BUILDING | FI | 2022-05-10 |  | 전력기술팀(Elec.) | 고승호 | [5 empty] | CCPP | Lighting & Small Power | Elec. | 3 | 2025-05-01 |  |  | DHI-GUP-DT-22-104 | 2022-03-08 | 0 | CRS-GUP-DHI-DT-22-267 | 2022-03-29 | NC | DHI-GUP-DT-22-104 | 2022-03-08 | 0 | CRS-GUP-DHI-DT-22-267 | 2022-03-29 | NC
| GUP | YZ03 | P1 | ZEN | 153215 |  | GUP-YZ03-P1ZEN-153215 | LIGHTING & SMALL POWER LAYOUT DRAWING_GAS TURBINE BUILDING | FI | 2022-05-10 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-05-01 |  |  | DHI-GUP-DT-22-104 | 2022-03-08 | 0 | CRS-GUP-DHI-DT-22-267 | 2022-03-29 | NC | DHI-GUP-DT-22-104 | 2022-03-08 | 0 | CRS-GUP-DHI-DT-22-267 | 2022-03-29 | NC
| GUP | YB11 | P1 | ZEN | 153275 |  | GUP-YB11-P1ZEN-153275 | LIGHTING PANEL BOARD SCHEDULE_GAS TURBINE BUILDING | FI | 2022-05-10 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-05-01 |  |  | DHI-GUP-DT-22-104 | 2022-03-08 | 0 | CRS-GUP-DHI-DT-22-267 | 2022-03-29 | NC | DHI-GUP-DT-22-104 | 2022-03-08 | 0 | CRS-GUP-DHI-DT-22-267 | 2022-03-29 | NC
| GUP | XW03 | P1 | ZEN | 153246 |  | GUP-XW03-P1ZEN-153246 | ILLUMINATION CALCULATION_PIPE RACK | FI | 2022-04-12 |  | 전력기술팀(Elec.) | 고승호 | [5 empty] | CCPP | Lighting & Small Power | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-033 | 2024-02-02 | 1 | CRS-GUP-DHI-DT-21-167 | 2022-01-22 | NC | DHI-GUP-DT-22-005 | 2022-01-06 | 0 | CRS-GUP-DHI-DT-21-167 | 2022-01-22 | NC | DE-GUP-DT-E-24-033 | 2024-02-02 | 1
| GUP | YZ03 | P1 | ZEN | 153216 |  | GUP-YZ03-P1ZEN-153216 | LIGHTING & SMALL POWER LAYOUT DRAWING_PIPE RACK | FI | 2022-04-12 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-033 | 2024-02-02 | 1 | CRS-GUP-DHI-DT-21-167 | 2022-01-22 | NC | DHI-GUP-DT-22-005 | 2022-01-06 | 0 | CRS-GUP-DHI-DT-21-167 | 2022-01-22 | NC | DE-GUP-DT-E-24-033 | 2024-02-02 | 1
| GUP | XW03 | P1 | ZEN | 153247 |  | GUP-XW03-P1ZEN-153247 | ILLUMINATION CALCULATION_BESS ELECTRICAL & CONTROL BUILDING | FI | 2022-08-13 |  | 전력기술팀(Elec.) | 고승호 | [5 empty] | CCPP | Lighting & Small Power | Elec. | 3 | 2025-04-17 |  |  | DE-GUP-DT-E-24-161 | 2024-06-24 | 4 | 자체 CRS 개정 후 제출 | 2024-06-23 | N/A | DE-GUP-DT-E-22-705 | 2022-09-26 | 0 | CRS-GUP-DHI-DT-22-947 | 2022-10-22 | RC | DE-GUP-DT-E-23-622 | 2023-06-16 | 1 | CRS-GUP-DHI-DT-23-2026 | 2023-07-04 | NC | DE-GUP-DT-E-23-798 | 2023-09-07 | 2 | 자체 CRS 개정 후 제출 | 2024-02-22 | N/A | DE-GUP-DT-E-24-054 | 2024-02-23 | 3 | 자체 CRS 개정 후 제출 | 2024-06-23 | N/A | DE-GUP-DT-E-24-161 | 2024-06-24 | 4
| GUP | YZ03 | P1 | ZEN | 153217 |  | GUP-YZ03-P1ZEN-153217 | LIGHTING & SMALL POWER LAYOUT DRAWING_BESS ELECTRICAL & CONTROL BUILDING | FI | 2022-08-13 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-04-17 |  |  | DE-GUP-DT-E-24-161 | 2024-06-24 | 4 | 자체 CRS 개정 후 제출 | 2024-06-23 | N/A | DE-GUP-DT-E-22-705 | 2022-09-26 | 0 | CRS-GUP-DHI-DT-22-947 | 2022-10-22 | RC | DE-GUP-DT-E-23-622 | 2023-06-16 | 1 | CRS-GUP-DHI-DT-23-2026 | 2023-07-04 | NC | DE-GUP-DT-E-23-798 | 2023-09-07 | 2 | 자체 CRS 개정 후 제출 | 2024-02-22 | N/A | DE-GUP-DT-E-24-054 | 2024-02-23 | 3 | 자체 CRS 개정 후 제출 | 2024-06-23 | N/A | DE-GUP-DT-E-24-161 | 2024-06-24 | 4
| GUP | YB11 | P1 | ZEN | 153277 |  | GUP-YB11-P1ZEN-153277 | LIGHTING PANEL BOARD SCHEDULE_BESS ELECTRICAL & CONTROL BUILDING | FI | 2022-08-13 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-04-17 |  |  | DE-GUP-DT-E-24-054 | 2024-02-23 | 3 | 자체 CRS 개정 후 제출 | 2024-02-22 | N/A | DE-GUP-DT-E-22-705 | 2022-09-26 | 0 | CRS-GUP-DHI-DT-22-947 | 2022-10-22 | RC | DE-GUP-DT-E-23-622 | 2023-06-16 | 1 | CRS-GUP-DHI-DT-23-2026 | 2023-07-04 | NC | DE-GUP-DT-E-23-798 | 2023-09-07 | 2 | 자체 CRS 개정 후 제출 | 2024-02-22 | N/A | DE-GUP-DT-E-24-054 | 2024-02-23 | 3
| GUP | XW03 | P1 | ZEN | 153248 |  | GUP-XW03-P1ZEN-153248 | ILLUMINATION CALCULATION_SWITCHYARD CONTROL BUILDING | FI | 2022-03-12 |  | 전력기술팀(Elec.) | 고승호 | [5 empty] | CCPP | Lighting & Small Power | Elec. | 3 | 2025-04-17 |  |  | DE-GUP-DT-E-23-798 | 2023-09-07 | 2 | CRS-GUP-DHI-DT-23-1713 | 2023-03-14 | NC | DHI-GUP-DT-21-130 | 2021-11-30 | 0 | CRS-GUP-DHI-DT-21-145 | 2022-01-12 | NC | DE-GUP-DT-E-23-265 | 2023-03-06 | 1 | CRS-GUP-DHI-DT-23-1713 | 2023-03-14 | NC | DE-GUP-DT-E-23-798 | 2023-09-07 | 2
| GUP | YZ03 | P1 | ZEN | 153218 |  | GUP-YZ03-P1ZEN-153218 | LIGHTING & SMALL POWER LAYOUT DRAWING_SWITCHYARD CONTROL BUILDING | FI | 2022-03-12 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-04-17 |  |  | DE-GUP-DT-E-23-798 | 2023-09-07 | 2 | CRS-GUP-DHI-DT-23-1713 | 2023-03-14 | NC | DHI-GUP-DT-21-130 | 2021-11-30 | 0 | CRS-GUP-DHI-DT-21-145 | 2022-01-12 | NC | DE-GUP-DT-E-23-265 | 2023-03-06 | 1 | CRS-GUP-DHI-DT-23-1713 | 2023-03-14 | NC | DE-GUP-DT-E-23-798 | 2023-09-07 | 2
| GUP | YB11 | P1 | ZEN | 153278 |  | GUP-YB11-P1ZEN-153278 | LIGHTING PANEL BOARD SCHEDULE_SWITCHYARD CONTROL BUILDING | FI | 2022-03-12 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-04-17 |  |  | DE-GUP-DT-E-23-798 | 2023-09-07 | 2 | CRS-GUP-DHI-DT-23-1713 | 2023-03-14 | NC | DHI-GUP-DT-21-130 | 2021-11-30 | 0 | CRS-GUP-DHI-DT-21-145 | 2022-01-12 | NC | DE-GUP-DT-E-23-265 | 2023-03-06 | 1 | CRS-GUP-DHI-DT-23-1713 | 2023-03-14 | NC | DE-GUP-DT-E-23-798 | 2023-09-07 | 2
| GUP | XW03 | P1 | ZEN | 153249 |  | GUP-XW03-P1ZEN-153249 | ILLUMINATION CALCULATION_GATE HOUSE | FI | 2022-09-14 |  | 전력기술팀(Elec.) | 고승호 | [5 empty] | CCPP | Lighting & Small Power | Elec. | 3 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-24-158 | 2024-06-17 | 2 | CRS-GUP-DHI-DT-23-2026 | 2023-07-04 | NC | DE-GUP-DT-E-22-666 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-957 | 2022-10-22 | NC | DE-GUP-DT-E-23-622 | 2023-06-16 | 1 | CRS-GUP-DHI-DT-23-2026 | 2023-07-04 | NC | DE-GUP-DT-E-24-158 | 2024-06-17 | 2
| GUP | YZ03 | P1 | ZEN | 153219 |  | GUP-YZ03-P1ZEN-153219 | LIGHTING & SMALL POWER LAYOUT DRAWING_GATE HOUSE | FI | 2022-09-14 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-24-176 | 2024-07-04 | 3 | 자체 CRS 개정 후 제출 | 2024-07-03 | N/A | DE-GUP-DT-E-22-666 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-957 | 2022-10-22 | RC | DE-GUP-DT-E-23-622 | 2023-06-16 | 1 | CRS-GUP-DHI-DT-23-2026 | 2023-07-04 | NC | DE-GUP-DT-E-24-158 | 2024-06-17 | 2 | 자체 CRS 개정 후 제출 | 2024-07-03 | N/A | DE-GUP-DT-E-24-176 | 2024-07-04 | 3
| GUP | YB11 | P1 | ZEN | 153279 |  | GUP-YB11-P1ZEN-153279 | LIGHTING PANEL BOARD SCHEDULE_GATE HOUSE | FI | 2022-09-14 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-24-176 | 2024-07-04 | 3 | 자체 CRS 개정 후 제출 | 2024-07-03 | N/A | DE-GUP-DT-E-22-666 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-957 | 2022-10-22 | RC | DE-GUP-DT-E-23-622 | 2023-06-16 | 1 | CRS-GUP-DHI-DT-23-2026 | 2023-07-04 | NC | DE-GUP-DT-E-24-158 | 2024-06-17 | 2 | 자체 CRS 개정 후 제출 | 2024-07-03 | N/A | DE-GUP-DT-E-24-176 | 2024-07-04 | 3
| GUP | XW03 | P1 | ZEN | 153250 |  | GUP-XW03-P1ZEN-153250 | ILLUMINATION CALCULATION_CONTROL & ELECTRICAL BUILDING | FI | 2022-03-12 |  | 전력기술팀(Elec.) | 고승호 | [5 empty] | CCPP | Lighting & Small Power | Elec. | 3 | 2025-05-01 |  |  | DE-GUP-DT-E-24-054 | 2024-02-23 | 3 | 자체 CRS 개정 후 제출 | 2024-02-22 | N/A | DHI-GUP-DT-21-129 | 2021-11-30 | 0 | CRS-GUP-DHI-DT-21-145 | 2022-01-12 | NC | DE-GUP-DT-E-23-265 | 2023-03-06 | 1 | CRS-GUP-DHI-DT-23-1713 | 2023-03-14 | NC | DE-GUP-DT-E-23-918 | 2023-11-20 | 2 | 자체 CRS 개정 후 제출 | 2024-02-22 | N/A | DE-GUP-DT-E-24-054 | 2024-02-23 | 3
| GUP | YZ03 | P1 | ZEN | 153220 |  | GUP-YZ03-P1ZEN-153220 | LIGHTING & SMALL POWER LAYOUT DRAWING_CONTROL & ELECTRICAL BUILDING | FI | 2022-03-12 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-05-01 |  |  | DE-GUP-DT-E-24-054 | 2024-02-23 | 3 | 자체 CRS 개정 후 제출 | 2024-02-22 | N/A | DHI-GUP-DT-21-129 | 2021-11-30 | 0 | CRS-GUP-DHI-DT-21-145 | 2022-01-12 | NC | DE-GUP-DT-E-23-265 | 2023-03-06 | 1 | CRS-GUP-DHI-DT-23-1713 | 2023-03-14 | NC | DE-GUP-DT-E-23-918 | 2023-11-20 | 2 | 자체 CRS 개정 후 제출 | 2024-02-22 | N/A | DE-GUP-DT-E-24-054 | 2024-02-23 | 3
| GUP | YB11 | P1 | ZEN | 153280 |  | GUP-YB11-P1ZEN-153280 | LIGHTING PANEL BOARD SCHEDULE_CONTROL & ELECTRICAL BUILDING | FI | 2022-03-12 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-05-01 |  |  | DE-GUP-DT-E-24-054 | 2024-02-23 | 3 | 자체 CRS 개정 후 제출 | 2024-02-22 | N/A | DHI-GUP-DT-21-129 | 2021-11-30 | 0 | CRS-GUP-DHI-DT-21-145 | 2022-01-12 | NC | DE-GUP-DT-E-23-265 | 2023-03-06 | 1 | CRS-GUP-DHI-DT-23-1713 | 2023-03-14 | NC | DE-GUP-DT-E-23-918 | 2023-11-20 | 2 | 자체 CRS 개정 후 제출 | 2024-02-22 | N/A | DE-GUP-DT-E-24-054 | 2024-02-23 | 3
| GUP | XW03 | P1 | ZEN | 153251 |  | GUP-XW03-P1ZEN-153251 | ILLUMINATION CALCULATION_AMMONIA STORAGE AND UNLOADING SHELTER | FI | 2022-09-30 |  | 전력기술팀(Elec.) | 고승호 | [5 empty] | CCPP | Lighting & Small Power | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-798 | 2023-09-07 | 1 | CRS-GUP-DHI-DT-22-1098 | 2022-11-21 | NC | DE-GUP-DT-E-22-811 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1098 | 2022-11-21 | NC | DE-GUP-DT-E-23-798 | 2023-09-07 | 1
| GUP | YZ03 | P1 | ZEN | 153221 |  | GUP-YZ03-P1ZEN-153221 | LIGHTING & SMALL POWER LAYOUT DRAWING_AMMONIA STORAGE AND UNLOADING SHELTER | FI | 2022-09-30 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-798 | 2023-09-07 | 1 | CRS-GUP-DHI-DT-22-1098 | 2022-11-21 | NC | DE-GUP-DT-E-22-811 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1098 | 2022-11-21 | NC | DE-GUP-DT-E-23-798 | 2023-09-07 | 1
| GUP | XW03 | P1 | ZEN | 153252 |  | GUP-XW03-P1ZEN-153252 | ILLUMINATION CALCULATION_FOAM STATION SHELTER | FI | 2022-08-23 |  | 전력기술팀(Elec.) | 고승호 | [5 empty] | CCPP | Lighting & Small Power | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-798 | 2023-09-07 | 2 | CRS-GUP-DHI-DT-23-2026 | 2023-07-04 | NC | DE-GUP-DT-E-22-666 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-957 | 2022-10-23 | NC | DE-GUP-DT-E-23-622 | 2023-06-16 | 1 | CRS-GUP-DHI-DT-23-2026 | 2023-07-04 | NC | DE-GUP-DT-E-23-798 | 2023-09-07 | 2
| GUP | YZ03 | P1 | ZEN | 153222 |  | GUP-YZ03-P1ZEN-153222 | LIGHTING & SMALL POWER LAYOUT DRAWING_FOAM STATION SHELTER | FI | 2022-08-23 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-798 | 2023-09-07 | 2 | CRS-GUP-DHI-DT-23-2026 | 2023-07-04 | NC | DE-GUP-DT-E-22-666 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-957 | 2022-10-23 | RC | DE-GUP-DT-E-23-622 | 2023-06-16 | 1 | CRS-GUP-DHI-DT-23-2026 | 2023-07-04 | NC | DE-GUP-DT-E-23-798 | 2023-09-07 | 2
| GUP | XW03 | P1 | ZEN | 153253 |  | GUP-XW03-P1ZEN-153253 | ILLUMINATION CALCULATION_CHEMICAL DOSING SHELTER FOR COOLING TOWER | FI | 2022-09-30 |  | 전력기술팀(Elec.) | 고승호 | [5 empty] | CCPP | Lighting & Small Power | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-811 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1098 | 2022-11-21 | NC | DE-GUP-DT-E-22-811 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1098 | 2022-11-21 | NC
| GUP | YZ03 | P1 | ZEN | 153223 |  | GUP-YZ03-P1ZEN-153223 | LIGHTING & SMALL POWER LAYOUT DRAWING_CHEMICAL DOSING SHELTER FOR COOLING TOWER | FI | 2022-09-30 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-811 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1098 | 2022-11-21 | NC | DE-GUP-DT-E-22-811 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1098 | 2022-11-21 | NC
| GUP | YB11 | P1 | ZEN | 153283 |  | GUP-YB11-P1ZEN-153283 | LIGHTING PANEL BOARD SCHEDULE_CHEMICAL DOSING SHELTER FOR COOLING TOWER | FI | 2022-09-30 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-811 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1098 | 2022-11-21 | NC | DE-GUP-DT-E-22-811 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1098 | 2022-11-21 | NC
| GUP | XW03 | P1 | ZEN | 153254 |  | GUP-XW03-P1ZEN-153254 | ILLUMINATION CALCULATION_GCB SHELTER FOR ST (ABOVE ONLY) | FI | 2022-07-01 |  | 전력기술팀(Elec.) | 고승호 | [5 empty] | CCPP | Lighting & Small Power | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-736 | 2023-08-08 | 1 | CRS-GUP-DHI-DT-22-339 | 2022-05-18 | NC | DHI-GUP-DT-22-166 | 2022-04-12 | 0 | CRS-GUP-DHI-DT-22-339 | 2022-05-18 | NC | DE-GUP-DT-E-23-736 | 2023-08-08 | 1
| GUP | YZ03 | P1 | ZEN | 153224 |  | GUP-YZ03-P1ZEN-153224 | LIGHTING & SMALL POWER LAYOUT DRAWING_GCB SHELTER FOR ST | FI | 2022-07-01 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-736 | 2023-08-08 | 1 | CRS-GUP-DHI-DT-22-339 | 2022-05-18 | NC | DHI-GUP-DT-22-166 | 2022-04-12 | 0 | CRS-GUP-DHI-DT-22-339 | 2022-05-18 | NC | DE-GUP-DT-E-23-736 | 2023-08-08 | 1
| GUP | XW03 | P1 | ZEN | 153255 |  | GUP-XW03-P1ZEN-153255 | ILLUMINATION CALCULATION_ULSD PUMP AND TREATMENT SHELTER | FI | 2022-09-30 |  | 전력기술팀(Elec.) | 고승호 | [5 empty] | CCPP | Lighting & Small Power | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-798 | 2023-09-07 | 1 | CRS-GUP-DHI-DT-22-1098 | 2022-11-21 | NC | DE-GUP-DT-E-22-811 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1098 | 2022-11-21 | NC | DE-GUP-DT-E-23-798 | 2023-09-07 | 1
| GUP | YZ03 | P1 | ZEN | 153225 |  | GUP-YZ03-P1ZEN-153225 | LIGHTING & SMALL POWER LAYOUT DRAWING_ULSD PUMP AND TREATMENT SHELTER | FI | 2022-09-30 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-798 | 2023-09-07 | 1 | CRS-GUP-DHI-DT-22-1098 | 2022-11-21 | NC | DE-GUP-DT-E-22-811 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1098 | 2022-11-21 | NC | DE-GUP-DT-E-23-798 | 2023-09-07 | 1
| GUP | YB11 | P1 | ZEN | 153285 |  | GUP-YB11-P1ZEN-153285 | LIGHTING PANEL BOARD SCHEDULE_ULSD PUMP AND TREATMENT SHELTER | FI | 2022-09-30 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-798 | 2023-09-07 | 1 | CRS-GUP-DHI-DT-22-1098 | 2022-11-21 | NC | DE-GUP-DT-E-22-811 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1098 | 2022-11-21 | NC | DE-GUP-DT-E-23-798 | 2023-09-07 | 1
| GUP | XW03 | P1 | ZEN | 153257 |  | GUP-XW03-P1ZEN-153257 | ILLUMINATION CALCULATION_COMPRESSED AIR PACKAGE SHELTER | FI | 2022-08-27 |  | 전력기술팀(Elec.) | 고승호 | [5 empty] | CCPP | Lighting & Small Power | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-113 | 2024-04-29 | 3 | 자체 CRS 개정 후 제출 | 2024-04-28 | N/A | DE-GUP-DT-E-22-666 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-957 | 2022-10-22 | NC | DE-GUP-DT-E-23-622 | 2023-06-16 | 1 | CRS-GUP-DHI-DT-23-2026 | 2023-07-04 | NC | DE-GUP-DT-E-23-798 | 2023-09-07 | 2 | 자체 CRS 개정 후 제출 | 2024-04-28 | N/A | DE-GUP-DT-E-24-113 | 2024-04-29 | 3
| GUP | YZ03 | P1 | ZEN | 153227 |  | GUP-YZ03-P1ZEN-153227 | LIGHTING & SMALL POWER LAYOUT DRAWING_COMPRESSED AIR PACKAGE SHELTER | FI | 2022-08-27 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-113 | 2024-04-29 | 3 | 자체 CRS 개정 후 제출 | 2024-04-28 | N/A | DE-GUP-DT-E-22-666 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-957 | 2022-10-22 | RC | DE-GUP-DT-E-23-622 | 2023-06-16 | 1 | CRS-GUP-DHI-DT-23-2026 | 2023-07-04 | NC | DE-GUP-DT-E-23-798 | 2023-09-07 | 2 | 자체 CRS 개정 후 제출 | 2024-04-28 | N/A | DE-GUP-DT-E-24-113 | 2024-04-29 | 3
| GUP | XW03 | P1 | ZEN | 153258 |  | GUP-XW03-P1ZEN-153258 | ILLUMINATION CALCULATION_FIRE PROTECTION PUMP BUILDING | FI | 2022-07-24 |  | 전력기술팀(Elec.) | 고승호 | [5 empty] | CCPP | Lighting & Small Power | Elec. | 3 | 2025-03-18 | 2025-03-31 |  | DE-GUP-DT-E-23-798 | 2023-09-07 | 1 | CRS-GUP-DHI-DT-22-644 | 2022-08-20 | NC | DE-GUP-DT-E-22-507 | 2022-08-16 | 0 | CRS-GUP-DHI-DT-22-644 | 2022-08-20 | NC | DE-GUP-DT-E-23-798 | 2023-09-07 | 1
| GUP | YZ03 | P1 | ZEN | 153228 |  | GUP-YZ03-P1ZEN-153228 | LIGHTING & SMALL POWER LAYOUT DRAWING_FIRE PROTECTION PUMP BUILDING | FI | 2022-07-24 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-03-18 | 2025-03-31 |  | DE-GUP-DT-E-23-798 | 2023-09-07 | 1 | CRS-GUP-DHI-DT-22-644 | 2022-08-20 | NC | DE-GUP-DT-E-22-507 | 2022-08-16 | 0 | CRS-GUP-DHI-DT-22-644 | 2022-08-20 | NC | DE-GUP-DT-E-23-798 | 2023-09-07 | 1
| GUP | YB11 | P1 | ZEN | 153288 |  | GUP-YB11-P1ZEN-153288 | LIGHTING PANEL BOARD SCHEDULE_FIRE PROTECTION PUMP BUILDING | FI | 2022-07-24 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-03-18 | 2025-03-31 |  | DE-GUP-DT-E-23-798 | 2023-09-07 | 1 | CRS-GUP-DHI-DT-22-644 | 2022-08-20 | NC | DE-GUP-DT-E-22-507 | 2022-08-16 | 0 | CRS-GUP-DHI-DT-22-644 | 2022-08-20 | NC | DE-GUP-DT-E-23-798 | 2023-09-07 | 1
| GUP | XW03 | P1 | ZEN | 153259 |  | GUP-XW03-P1ZEN-153259 | ILLUMINATION CALCULATION_ADMINISTRATION BUILDING | FI | 2022-09-10 |  | 전력기술팀(Elec.) | 고승호 | [5 empty] | CCPP | Lighting & Small Power | Elec. | 3 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-23-1008 | 2023-12-22 | 1 | CRS-GUP-DHI-DT-22-1098 | 2022-11-21 | NC | DE-GUP-DT-E-22-811 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1098 | 2022-11-21 | NC | DE-GUP-DT-E-23-1008 | 2023-12-22 | 1
| GUP | YZ03 | P1 | ZEN | 153229 |  | GUP-YZ03-P1ZEN-153229 | LIGHTING & SMALL POWER LAYOUT DRAWING_ADMINISTRATION BUILDING | FI | 2022-09-10 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-23-1008 | 2023-12-22 | 1 | CRS-GUP-DHI-DT-22-1098 | 2022-11-21 | NC | DE-GUP-DT-E-22-811 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1098 | 2022-11-21 | NC | DE-GUP-DT-E-23-1008 | 2023-12-22 | 1
| GUP | YB11 | P1 | ZEN | 153289 |  | GUP-YB11-P1ZEN-153289 | LIGHTING PANEL BOARD SCHEDULE_ADMINISTRATION BUILDING | FI | 2022-09-10 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-23-1008 | 2023-12-22 | 1 | CRS-GUP-DHI-DT-22-1098 | 2022-11-21 | NC | DE-GUP-DT-E-22-811 | 2022-10-17 | 0 | CRS-GUP-DHI-DT-22-1098 | 2022-11-21 | NC | DE-GUP-DT-E-23-1008 | 2023-12-22 | 1
| GUP | XW03 | P1 | ZEN | 153260 |  | GUP-XW03-P1ZEN-153260 | ILLUMINATION CALCULATION_ROAD & PAVING (CCPP PLANT AREA) | FI | 2022-12-30 |  | 전력기술팀(Elec.) | 고승호 | [5 empty] | CCPP | Lighting & Small Power | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-158 | 2024-06-17 | 1 | CRS-GUP-DHI-DT-23-1595 | 2023-02-28 | NC | DE-GUP-DT-E-23-167 | 2023-02-13 | 0 | CRS-GUP-DHI-DT-23-1595 | 2023-02-28 | NC | DE-GUP-DT-E-24-158 | 2024-06-17 | 1
| GUP | YZ03 | P1 | ZEN | 153230 |  | GUP-YZ03-P1ZEN-153230 | LIGHTING & SMALL POWER LAYOUT DRAWING_ROAD & FENCE (CCPP PLANT AREA) | FI | 2022-12-30 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-158 | 2024-06-17 | 1 | CRS-GUP-DHI-DT-23-1595 | 2023-02-28 | NC | DE-GUP-DT-E-23-167 | 2023-02-13 | 0 | CRS-GUP-DHI-DT-23-1595 | 2023-02-28 | NC | DE-GUP-DT-E-24-158 | 2024-06-17 | 1
| GUP | YB11 | P1 | ZEN | 153290 |  | GUP-YB11-P1ZEN-153290 | LIGHTING PANEL BOARD SCHEDULE_ROAD & PAVING (CCPP PLANT AREA) | FI | 2022-12-30 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-158 | 2024-06-17 | 1 | CRS-GUP-DHI-DT-23-1595 | 2023-02-28 | NC | DE-GUP-DT-E-23-167 | 2023-02-13 | 0 | CRS-GUP-DHI-DT-23-1595 | 2023-02-28 | NC | DE-GUP-DT-E-24-158 | 2024-06-17 | 1
| GUP | XW03 | P1 | ZEN | 153261 |  | GUP-XW03-P1ZEN-153261 | ILLUMINATION CALCULATION_TRANSFORMER AREA | FI | 2022-12-30 |  | 전력기술팀(Elec.) | 고승호 | [5 empty] | CCPP | Lighting & Small Power | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-736 | 2023-08-08 | 1 | CRS-GUP-DHI-DT-23-1595 | 2023-02-28 | NC | DE-GUP-DT-E-23-167 | 2023-02-13 | 0 | CRS-GUP-DHI-DT-23-1595 | 2023-02-28 | NC | DE-GUP-DT-E-23-736 | 2023-08-08 | 1
| GUP | YZ03 | P1 | ZEN | 153231 |  | GUP-YZ03-P1ZEN-153231 | LIGHTING & SMALL POWER LAYOUT DRAWING_TRANSFORMER AREA | FI | 2022-12-30 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-736 | 2023-08-08 | 1 | CRS-GUP-DHI-DT-23-1595 | 2023-02-28 | NC | DE-GUP-DT-E-23-167 | 2023-02-13 | 0 | CRS-GUP-DHI-DT-23-1595 | 2023-02-28 | NC | DE-GUP-DT-E-23-736 | 2023-08-08 | 1
| GUP | XW03 | P1 | ZEN | 153262 |  | GUP-XW03-P1ZEN-153262 | ILLUMINATION CALCULATION_MISCELLANEOUS AREA | FI | 2022-12-30 |  | 전력기술팀(Elec.) | 고승호 | [5 empty] | CCPP | Lighting & Small Power | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-736 | 2023-08-08 | 1 | CRS-GUP-DHI-DT-23-1603 | 2023-03-01 | NC | DE-GUP-DT-E-23-243 | 2023-02-24 | 0 | CRS-GUP-DHI-DT-23-1603 | 2023-03-01 | NC | DE-GUP-DT-E-23-736 | 2023-08-08 | 1
| GUP | YZ03 | P1 | ZEN | 153232 |  | GUP-YZ03-P1ZEN-153232 | LIGHTING & SMALL POWER LAYOUT DRAWING_MISCELLANEOUS AREA | FI | 2022-12-30 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-736 | 2023-08-08 | 1 | CRS-GUP-DHI-DT-23-1595 | 2023-02-28 | NC | DE-GUP-DT-E-23-167 | 2023-02-13 | 0 | CRS-GUP-DHI-DT-23-1595 | 2023-02-28 | NC | DE-GUP-DT-E-23-736 | 2023-08-08 | 1
| GUP | XW03 | P1 | ZEN | 153263 |  | GUP-XW03-P1ZEN-153263 | ILLUMINATION CALCULATION_COOLING TOWER | FI | 2023-06-16 |  | 전력기술팀(Elec.) | 고승호 | [5 empty] | CCPP | Lighting & Small Power | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-033 | 2024-02-02 | 1 | CRS-GUP-DHI-DT-23-2037 | 2023-07-06 | NC | DE-GUP-DT-E-23-614 | 2023-06-12 | 0 | CRS-GUP-DHI-DT-23-2037 | 2023-07-06 | NC | DE-GUP-DT-E-24-033 | 2024-02-02 | 1
| GUP | YZ03 | P1 | ZEN | 153233 |  | GUP-YZ03-P1ZEN-153233 | LIGHTING & SMALL POWER LAYOUT DRAWING_COOLING TOWER | FI | 2023-06-16 |  | 전력기술팀(Elec.) | 고승호 | B | P |  |  |  | CCPP | Lighting & Small Power | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-033 | 2024-02-02 | 1 | CRS-GUP-DHI-DT-23-2037 | 2023-07-06 | NC | DE-GUP-DT-E-23-614 | 2023-06-12 | 0 | CRS-GUP-DHI-DT-23-2037 | 2023-07-06 | NC | DE-GUP-DT-E-24-033 | 2024-02-02 | 1
| GUP | YD00 | P1 | ZEN | 150051 |  | GUP-YD00-P1ZEN-150051 | ELECTRICAL ROOM LAYOUT DRAWING_MAINTENANCE WORKSHOP AND STORE BUILDING | FA | 2022-12-26 | 2023-03-27 | 전력기술팀(Elec.) | 정민구 | [5 empty] | CCPP | Equipment arrnagement | Elec. | 2 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-23-407 | 2023-03-31 | 0 | CRS-GUP-DHI-DT-23-1678 | 2023-03-13 | AA | DE-GUP-DT-E-23-095 | 2023-01-30 | A | CRS-GUP-DHI-DT-23-1678 | 2023-03-13 | AA | DE-GUP-DT-E-23-407 | 2023-03-31 | 0
| GUP | YD00 | P1 | ZEN | 150052 |  | GUP-YD00-P1ZEN-150052 | ELECTRICAL ROOM LAYOUT DRAWING_WT & WWT BLDG & SHELTER | FA | 2022-06-15 | 2022-10-15 | 전력기술팀(Elec.) | 정민구 | [5 empty] | CCPP | Equipment arrnagement | Elec. | 2 | 2025-04-17 |  |  | DE-GUP-DT-E-22-794 | 2022-10-13 | 0 | CRS-GUP-DHI-DT-22-1135 | 2022-11-23 | AA | DE-GUP-DT-E-22-467 | 2022-07-28 | A | CRS-GUP-DHI-DT-22-666 | 2022-08-22 | RC | DE-GUP-DT-E-22-664 | 2022-09-15 | B | CRS-GUP-DHI-DT-22-901 | 2022-10-12 | AA | DE-GUP-DT-E-22-794 | 2022-10-13 | 0 | CRS-GUP-DHI-DT-22-1135 | 2022-11-23 | AA
| GUP | YD00 | P1 | ZEN | 150053 |  | GUP-YD00-P1ZEN-150053 | ELECTRICAL ROOM LAYOUT DRAWING_115kV AIS CONTROL BUILDING | FA | 2022-04-02 | 2022-07-03 | 전력기술팀(Elec.) | 박경수 |  |  | G | FI |  | CCPP | Equipment arrnagement | Elec. | 2 | 2025-04-17 |  |  | DE-GUP-DT-E-23-895 | 2023-11-09 | 1 | CRS-GUP-DHI-DT-23-1501 | 2023-02-14 | AA | DHI-GUP-DT-21-180 | 2021-12-16 | A | CRS-GUP-DHI-DT-21-131 | 2022-01-11 | RC | DHI-GUP-DT-22-150 | 2022-04-05 | B | CRS-GUP-DHI-DT-22-316 | 2022-05-02 | RC | DHI-GUP-DT-22-216 | 2022-05-12 | C | CRS-GUP-DHI-DT-22-397 | 2022-06-07 | RC | DE-GUP-DT-E-22-333 | 2022-06-24 | D | CRS-GUP-DHI-DT-22-530 | 2022-07-19 | RC | DE-GUP-DT-E-22-427 | 2022-07-21 | E | CRS-GUP-DHI-DT-22-699 | 2022-09-03 | RC | DE-GUP-DT-E-22-672 | 2022-09-16 | F | CRS-GUP-DHI-DT-22-885 | 2022-10-10 | RC | DE-GUP-DT-E-22-822 | 2022-10-18 | G | CRS-GUP-DHI-DT-22-961 | 2022-11-03 | AC | DE-GUP-DT-E-22-1126 | 2022-12-19 | 0(CP) | CRS-GUP-DHI-DT-23-1501 | 2023-02-14 | AA | DE-GUP-DT-E-23-895 | 2023-11-09 | 1
| GUP | YD00 | P1 | ZEN | 150054 |  | GUP-YD00-P1ZEN-150054 | ELECTRICAL ROOM LAYOUT DRAWING_CONTROL & ELECTRICAL BUILDING | FA | 2022-01-11 | 2022-04-11 | 전력기술팀(Elec.) | 정민구 | [5 empty] | CCPP | Equipment arrnagement | Elec. | 2 | 2025-05-01 |  |  | DE-GUP-DT-E-23-945 | 2023-11-24 | 1 | 자체 CRS 개정 후 제출 | 2023-11-23 | N/A | DHI-GUP-DT-21-062 | 2021-10-14 | A | CRS-GUP-DHI-DT-21-048 | 2021-11-01 | RC | DHI-GUP-DT-21-114 | 2021-11-23 | B | CRS-GUP-DHI-DT-21-077 | 2021-12-08 | RC | DHI-GUP-DT-21-170 | 2021-12-13 | C | CRS-GUP-DHI-DT-21-084 | 2021-12-22 | AC | DE-GUP-DT-E-22-399 | 2022-07-15 | D | CRS-GUP-DHI-DT-22-612 | 2022-08-16 | AC | DE-GUP-DT-E-22-575 | 2022-08-29 | 0(CP) | 자체 CRS 개정 후 제출 | 2023-11-23 | N/A | DE-GUP-DT-E-23-945 | 2023-11-24 | 1
| GUP | YD00 | P1 | ZEN | 150055 |  | GUP-YD00-P1ZEN-150055 | ELECTRICAL ROOM LAYOUT DRAWING_ADMINISTRATION BUILDING | FA | 2022-08-26 | 2022-11-16 | 전력기술팀(Elec.) | 정민구 | [5 empty] | CCPP | Equipment arrnagement | Elec. | 2 | 2025-04-01 | 2025-01-17 |  | DE-GUP-DT-E-23-407 | 2023-03-31 | 0 | CRS-GUP-DHI-DT-23-1593 | 2023-02-28 | AA | DE-GUP-DT-E-22-800 | 2022-10-14 | A | CRS-GUP-DHI-DT-22-988 | 2022-11-08 | RC | DE-GUP-DT-E-23-151 | 2023-02-09 | B | CRS-GUP-DHI-DT-23-1593 | 2023-02-28 | AA | DE-GUP-DT-E-23-407 | 2023-03-31 | 0
| GUP | XW03 | P1 | BAC | 152102 |  | GUP-XW03-P1BAC-152102 | SIZING CALCULATION_GENERATOR CIRCUIT BREAKER | FA | 2021-11-28 | 2022-08-12 | 전력기술팀(Elec.) | 박경수 | [5 empty] | CCPP | GCB | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-289 | 2022-06-14 | 0 | CRS-GUP-DHI-DT-22-416 | 2022-06-13 | AA | DHI-GUP-DT-21-135 | 2021-11-30 | A | CRS-GUP-DHI-DT-21-097 | 2021-12-27 | RC | DHI-GUP-DT-22-075 | 2022-02-16 | B | CRS-GUP-DHI-DT-22-236 | 2022-03-07 | RC | DE-GUP-DT-E-22-242 | 2022-05-23 | C | CRS-GUP-DHI-DT-22-416 | 2022-06-13 | AA | DE-GUP-DT-E-22-289 | 2022-06-14 | 0
| GUP | XW03 | P1 | BAT | 152012 |  | GUP-XW03-P1BAT-152012 | SIZING CALCULATION_GENERATOR STEP UP TRANSFORMER | FA | 2021-11-28 | 2022-02-26 | 전력기술팀(Elec.) | 박경수 |  |  | G | FI |  | CCPP | Transformer | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-229 | 2022-05-19 | 0 | CRS-GUP-DHI-DT-22-407 | 2022-06-10 | AA | DHI-GUP-DT-21-151 | 2021-12-07 | A | CRS-GUP-DHI-DT-21-110 | 2022-01-05 | RC | DHI-GUP-DT-22-084 | 2022-02-22 | B | CRS-GUP-DHI-DT-22-253 | 2022-03-16 | RC | DHI-GUP-DT-22-192 | 2022-04-29 | C | CRS-GUP-DHI-DT-22-347 | 2022-05-18 | AA | DE-GUP-DT-E-22-229 | 2022-05-19 | 0 | CRS-GUP-DHI-DT-22-407 | 2022-06-10 | AA
| GUP | XW03 | P1 | BAA | 152202 |  | GUP-XW03-P1BAA-152202 | SIZING CALCULATION_NON-SEGREGATED PHASE BUSDUCT | FA | 2021-11-28 | 2022-07-29 | 전력기술팀(Elec.) | 박경수 |  |  | G | FI |  | CCPP | NSPB | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-290 | 2022-06-14 | 0 | CRS-GUP-DHI-DT-22-414 | 2022-06-13 | AA | DHI-GUP-DT-21-135 | 2021-11-30 | A | CRS-GUP-DHI-DT-21-097 | 2021-12-27 | RC | DHI-GUP-DT-22-028 | 2022-01-20 | B | CRS-GUP-DHI-DT-21-186 | 2022-02-04 | RC | DE-GUP-DT-E-22-237 | 2022-05-20 | C | CRS-GUP-DHI-DT-22-414 | 2022-06-13 | AA | DE-GUP-DT-E-22-290 | 2022-06-14 | 0
| GUP | XW03 | P1 | BBT | 152222 |  | GUP-XW03-P1BBT-152222 | SIZING CALCULATION_UNIT AUXILIARY TRANSFORMER | FA | 2021-11-28 | 2022-07-22 | 전력기술팀(Elec.) | 박경수 | [5 empty] | CCPP | Transformer | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-449 | 2022-07-26 | 0 | CRS-GUP-DHI-DT-22-501 | 2022-07-07 | AA | DHI-GUP-DT-21-141 | 2021-12-03 | A | CRS-GUP-DHI-DT-21-156 | 2022-01-12 | RC | DHI-GUP-DT-22-029 | 2022-01-20 | B | CRS-GUP-DHI-DT-21-187 | 2022-02-04 | RC | DE-GUP-DT-E-22-291 | 2022-06-13 | C | CRS-GUP-DHI-DT-22-501 | 2022-07-07 | AA | DE-GUP-DT-E-22-449 | 2022-07-26 | 0
| GUP | XW03 | P1 | BFT | 152401 |  | GUP-XW03-P1BFT-152401 | SIZING CALCULATION_LV TRANSFORMER | FA | 2022-03-29 | 2022-07-22 | 전력기술팀(Elec.) | 정민구 | [5 empty] | CCPP | LV SWGR | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-506 | 2022-08-16 | 0 | CRS-GUP-DHI-DT-22-600 | 2022-08-13 | AA | DHI-GUP-DT-21-182 | 2021-12-17 | 0 | CRS-GUP-DHI-DT-21-160 | 2022-01-14 | NC | DE-GUP-DT-E-22-260 | 2022-05-31 | B | CRS-GUP-DHI-DT-22-470 | 2022-06-22 | RC | DE-GUP-DT-E-22-415 | 2022-07-19 | C | CRS-GUP-DHI-DT-22-600 | 2022-08-13 | AA | DE-GUP-DT-E-22-506 | 2022-08-16 | 0
| GUP | XW03 | P1 | BBW | 152602 |  | GUP-XW03-P1BBW-152602 | SIZING CALCULATION_DC & UPS SYSTEM | FA | 2021-11-28 | 2022-07-31 | 전력기술팀(Elec.) | 박경수 |  |  | G | FI |  | CCPP | DC & UPS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-906 | 2023-11-13 | 1 | CRS-GUP-DHI-DT-22-1149 | 2022-11-23 | AA | DHI-GUP-DT-21-172 | 2021-12-14 | A | CRS-GUP-DHI-DT-21-130 | 2022-01-11 | RC | DE-GUP-DT-E-22-402 | 2022-07-15 | B | CRS-GUP-DHI-DT-22-598 | 2022-08-13 | RC | DE-GUP-DT-E-22-585 | 2022-08-30 | C | CRS-GUP-DHI-DT-22-776 | 2022-09-15 | RC | DE-GUP-DT-E-22-672 | 2022-09-16 | D | CRS-GUP-DHI-DT-22-885 | 2022-10-10 | AC | DE-GUP-DT-E-22-898 | 2022-11-01 | 0(CP) | CRS-GUP-DHI-DT-22-1149 | 2022-11-23 | AA | DE-GUP-DT-E-23-906 | 2023-11-13 | 1
| GUP | XW03 | P1 | UZT | 150010 |  | GUP-XW03-P1UZT-150010 | SIZING CALCULATION_POWER CABLE | FA | 2021-09-30 | 2022-06-20 | 전력기술팀(Elec.) | 허규범 |  |  | G | FA |  | CCPP | Cable | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-324 | 2022-06-22 | 0 | CRS-GUP-DHI-DT-22-360 | 2022-05-23 | AA | DHI-GUP-DT-21-076 | 2021-10-22 | A | CRS-GUP-DHI-DT-21-058 | 2021-11-08 | RC | DHI-GUP-DT-21-145 | 2021-12-06 | B | CRS-GUP-DHI-DT-21-142 | 2022-01-11 | RC | DHI-GUP-DT-22-126 | 2022-03-22 | C | CRS-GUP-DHI-DT-22-289 | 2022-04-17 | RC | DHI-GUP-DT-22-195 | 2022-04-29 | D | CRS-GUP-DHI-DT-22-360 | 2022-05-23 | AA | DE-GUP-DT-E-22-324 | 2022-06-22 | 0
| GUP | YR02 | P6 | AE | 151501 |  | GUP-YR02-P6AE-151501 | TECHNICAL SPECIFICATION_115kV AIS HV EQUIPMENT (Harmon S/S) | FA | 2022-02-15 | 2022-06-13 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA |  | Harmon S/S | Harmon S/S | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-084 | 2023-01-27 | 1 | CRS-GUP-DHI-DT-24-027 | 2024-03-11 | AA | DHI-GUP-DT-22-135 | 2022-03-25 | A | CRS-GUP-DHI-DT-22-296 | 2022-04-17 | RC | DE-GUP-DT-E-22-402 | 2022-07-15 | B | CRS-GUP-DHI-DT-22-581 | 2022-08-08 | RC | DE-GUP-DT-E-22-520 | 2022-08-19 | C | CRS-GUP-DHI-DT-22-757 | 2022-09-14 | AC | DE-GUP-DT-E-22-708 | 2022-09-28 | 0(CP) | CRS-GUP-DHI-DT-22-1069 | 2022-11-19 | AC | DE-GUP-DT-E-23-084 | 2023-01-27 | 1 | CRS-GUP-DHI-DT-24-027 | 2024-03-11 | AA
| GUP | YR02 | P6 | AE | 151502 |  | GUP-YR02-P6AE-151502 | TECHNICAL SPECIFICATION_115kV AIS CONTROL & PROTECTION SYSTEM (Harmon S/S) | FA | 2022-02-15 | 2022-06-13 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA |  | Harmon S/S | Harmon S/S | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1022 | 2022-12-13 | 0 | CRS-GUP-DHI-DT-22-1075 | 2022-11-19 | AA | DHI-GUP-DT-22-140 | 2022-03-29 | A | CRS-GUP-DHI-DT-22-307 | 2022-04-23 | RC | DE-GUP-DT-E-22-355 | 2022-07-01 | B | CRS-GUP-DHI-DT-22-550 | 2022-07-27 | RC | DE-GUP-DT-E-22-479 | 2022-07-29 | C | CRS-GUP-DHI-DT-22-824 | 2022-09-22 | RC | DE-GUP-DT-E-22-762 | 2022-10-06 | D | CRS-GUP-DHI-DT-22-1075 | 2022-11-19 | AA | DE-GUP-DT-E-22-1022 | 2022-12-13 | 0
| GUP | YR02 | P6 | AE | 151504 |  | GUP-YR02-P6AE-151504 | TECHNICAL SPECIFICATION_115kV AIS MISCELLANEOUS ITEMS (Harmon S/S) | FA | 2022-02-28 | 2022-06-13 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA |  | Harmon S/S | Harmon S/S | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-708 | 2022-09-28 | 0 | CRS-GUP-DHI-DT-22-1120 | 2022-11-23 | AA | DHI-GUP-DT-22-140 | 2022-03-29 | A | CRS-GUP-DHI-DT-22-307 | 2022-04-23 | RC | DE-GUP-DT-E-22-245 | 2022-05-24 | B | CRS-GUP-DHI-DT-22-418 | 2022-06-13 | RC | DE-GUP-DT-E-22-343 | 2022-06-28 | C | CRS-GUP-DHI-DT-22-537 | 2022-07-24 | RC | DE-GUP-DT-E-22-473 | 2022-07-29 | D | CRS-GUP-DHI-DT-22-640 | 2022-08-20 | RC | DE-GUP-DT-E-22-622 | 2022-09-05 | E | CRS-GUP-DHI-DT-22-849 | 2022-09-24 | AA | DE-GUP-DT-E-22-708 | 2022-09-28 | 0 | CRS-GUP-DHI-DT-22-1120 | 2022-11-23 | AA
| GUP | YF00 | P6 | ZEN | 151506 |  | GUP-YF00-P6ZEN-151506 | ELECTRICAL CONTROL LOGIC DIAGRAM_115kV AIS (Harmon S/S) | FA | 2022-02-28 | 2022-06-20 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA |  | Harmon S/S | Harmon S/S | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-672 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-885 | 2022-10-10 | AA | DE-GUP-DT-E-22-235 | 2022-05-19 | A | CRS-GUP-DHI-DT-22-404 | 2022-06-09 | RC | DE-GUP-DT-E-22-355 | 2022-07-01 | B | CRS-GUP-DHI-DT-22-540 | 2022-07-24 | RC | DE-GUP-DT-E-22-479 | 2022-07-29 | C | CRS-GUP-DHI-DT-22-769 | 2022-09-15 | AA | DE-GUP-DT-E-22-672 | 2022-09-16 | 0 | CRS-GUP-DHI-DT-22-885 | 2022-10-10 | AA
| GUP | YT10 | P6 | ZEN | 151507 |  | GUP-YT10-P6ZEN-151507 | PROTECTION RELAY COORDINATION STUDY_115kV AIS (Harmon S/S) | FA | 2022-06-18 | 2022-09-10 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA |  | Harmon S/S | Harmon S/S | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-350 | 2023-03-23 | 0 | CRS-GUP-DHI-DT-23-1746 | 2023-03-17 | AA | DE-GUP-DT-E-22-889 | 2022-10-31 | A | CRS-GUP-DHI-DT-22-1219 | 2022-12-05 | RC | DE-GUP-DT-E-23-258 | 2023-02-28 | B | CRS-GUP-DHI-DT-23-1746 | 2023-03-17 | AA | DE-GUP-DT-E-23-350 | 2023-03-23 | 0
| GUP | YR02 | P6 | ZEN | 151510 |  | GUP-YR02-P6ZEN-151510 | DESIGN CRITERIA_115kV AIS (Harmon S/S) | FA | 2021-12-30 | 2022-06-13 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA |  | Harmon S/S | Harmon S/S | Elec. | 1 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1103 | 2022-12-16 | 1 | CRS-GUP-DHI-DT-22-1249 | 2022-12-13 | AA | DHI-GUP-DT-22-042 | 2022-01-27 | A | CRS-GUP-DHI-DT-22-204 | 2022-02-20 | RC | DE-GUP-DT-E-22-236 | 2022-05-20 | B | CRS-GUP-DHI-DT-22-413 | 2022-06-13 | RC | DE-GUP-DT-E-22-426 | 2022-07-20 | C | CRS-GUP-DHI-DT-22-590 | 2022-08-08 | RC | DE-GUP-DT-E-22-622 | 2022-09-05 | D | CRS-GUP-DHI-DT-22-849 | 2022-09-24 | RC | DE-GUP-DT-E-22-762 | 2022-10-06 | E | CRS-GUP-DHI-DT-22-1075 | 2022-11-19 | AC | DE-GUP-DT-E-22-985 | 2022-11-24 | 0(CP) | CRS-GUP-DHI-DT-22-1249 | 2022-12-13 | AA | DE-GUP-DT-E-22-1103 | 2022-12-16 | 1
| GUP | YU02 | P6 | AE | 151511 |  | GUP-YU02-P6AE-151511 | OVERALL SINGLE LINE DIAGRAM_115kV AIS SUBSTATION (Harmon S/S) | FA | 2021-12-17 | 2022-06-13 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA |  | Harmon S/S | Harmon S/S | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-985 | 2022-11-24 | 0 | CRS-GUP-DHI-DT-22-1249 | 2022-12-13 | AA | DHI-GUP-DT-22-042 | 2022-01-27 | A | CRS-GUP-DHI-DT-22-204 | 2022-02-20 | RC | DHI-GUP-DT-22-206 | 2022-05-04 | B | CRS-GUP-DHI-DT-22-381 | 2022-05-31 | RC | DE-GUP-DT-E-22-314 | 2022-06-17 | C | CRS-GUP-DHI-DT-22-510 | 2022-07-11 | RC | DE-GUP-DT-E-22-455 | 2022-07-26 | D | CRS-GUP-DHI-DT-22-601 | 2022-08-13 | RC | DE-GUP-DT-E-22-520 | 2022-08-19 | E | CRS-GUP-DHI-DT-22-833 | 2022-09-23 | AA | DE-GUP-DT-E-22-700 | 2022-09-23 | 0 | CRS-GUP-DHI-DT-22-1066 | 2022-11-19 | AA | DE-GUP-DT-E-22-985 | 2022-11-24 | 0 | CRS-GUP-DHI-DT-22-1249 | 2022-12-13 | AA
| GUP | YU02 | P6 | AE | 151513 |  | GUP-YU02-P6AE-151513 | SINGLE LINE DIAGRAM_115kV AIS LVAC SYSTEM (Harmon S/S) | FA | 2022-02-28 | 2022-06-13 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA |  | Harmon S/S | Harmon S/S | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-084 | 2023-01-27 | 1 | CRS-GUP-DHI-DT-23-1724 | 2023-03-17 | AA | DHI-GUP-DT-22-191 | 2022-04-29 | A | CRS-GUP-DHI-DT-22-346 | 2022-05-18 | RC | DE-GUP-DT-E-22-389 | 2022-07-12 | B | CRS-GUP-DHI-DT-22-822 | 2022-09-22 | AA | DE-GUP-DT-E-22-708 | 2022-09-28 | 0 | CRS-GUP-DHI-DT-22-908 | 2022-10-13 | RC | DE-GUP-DT-E-23-084 | 2023-01-27 | 1 | CRS-GUP-DHI-DT-23-1724 | 2023-03-17 | AA
| GUP | YU02 | P6 | AE | 151514 |  | GUP-YU02-P6AE-151514 | SINGLE LINE DIAGRAM_115kV AIS DC SYSTEM (Harmon S/S) | FA | 2022-02-28 | 2022-06-13 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA |  | Harmon S/S | Harmon S/S | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-084 | 2023-01-27 | 1 | CRS-GUP-DHI-DT-23-1724 | 2023-03-17 | AA | DHI-GUP-DT-22-191 | 2022-04-29 | A | CRS-GUP-DHI-DT-22-346 | 2022-05-18 | RC | DE-GUP-DT-E-22-389 | 2022-07-12 | B | CRS-GUP-DHI-DT-22-822 | 2022-09-22 | AA | DE-GUP-DT-E-22-708 | 2022-09-28 | 0 | CRS-GUP-DHI-DT-22-908 | 2022-10-13 | RC | DE-GUP-DT-E-23-084 | 2023-01-27 | 1 | CRS-GUP-DHI-DT-23-1724 | 2023-03-17 | AA
| GUP | YT10 | P6 | ZEN | 151516 |  | GUP-YT10-P6ZEN-151516 | CT & VT CALCULATION_115kV AIS (Harmon S/S) | FA | 2022-02-18 | 2022-07-13 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA |  | Harmon S/S | Harmon S/S | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-622 | 2022-09-05 | 0 | CRS-GUP-DHI-DT-22-849 | 2022-09-24 | AA | DHI-GUP-DT-22-183 | 2022-04-20 | A | CRS-GUP-DHI-DT-22-336 | 2022-05-16 | RC | DE-GUP-DT-E-22-299 | 2022-06-14 | B | CRS-GUP-DHI-DT-22-503 | 2022-07-07 | RC | DE-GUP-DT-E-22-444 | 2022-07-26 | C | CRS-GUP-DHI-DT-22-700 | 2022-09-03 | AA | DE-GUP-DT-E-22-622 | 2022-09-05 | 0 | CRS-GUP-DHI-DT-22-849 | 2022-09-24 | AA
| GUP | YT10 | P6 | ZEN | 151518 |  | GUP-YT10-P6ZEN-151518 | LOADING CALCULATION_115kV AIS SWITCHYARD (Harmon S/S) | FA | 2022-01-09 | 2022-07-13 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA |  | Harmon S/S | Harmon S/S | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-854 | 2022-10-25 | 1 | CRS-GUP-DHI-DT-22-1144 | 2022-11-23 | AA | DHI-GUP-DT-22-042 | 2022-01-27 | A | CRS-GUP-DHI-DT-22-204 | 2022-02-20 | RC | DHI-GUP-DT-22-220 | 2022-05-13 | B | CRS-GUP-DHI-DT-22-400 | 2022-06-07 | RC | DE-GUP-DT-E-22-343 | 2022-06-28 | C | CRS-GUP-DHI-DT-22-554 | 2022-07-27 | RC | DE-GUP-DT-E-22-514 | 2022-08-18 | D | CRS-GUP-DHI-DT-22-705 | 2022-09-03 | AA | DE-GUP-DT-E-22-663 | 2022-09-14 | 0 | CRS-GUP-DHI-DT-22-900 | 2022-10-12 | AA | DE-GUP-DT-E-22-854 | 2022-10-25 | 1 | CRS-GUP-DHI-DT-22-1144 | 2022-11-23 | AA
| GUP | YD00 | P6 | AE | 151521 |  | GUP-YD00-P6AE-151521 | OUTLINE DRAWING_115kV AIS HV EQUIPMENT (Harmon S/S) | FI | 2022-02-15 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FA |  | Harmon S/S | Harmon S/S | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-973 | 2022-11-23 | 2 | CRS-GUP-DHI-DT-22-1226 | 2022-12-13 | NC | DHI-GUP-DT-22-192 | 2022-04-29 | 0 | CRS-GUP-DHI-DT-22-348 | 2022-05-18 | RC | DE-GUP-DT-E-22-402 | 2022-07-15 | 1 | CRS-GUP-DHI-DT-22-823 | 2022-09-22 | RC | DE-GUP-DT-E-22-973 | 2022-11-23 | 2 | CRS-GUP-DHI-DT-22-1226 | 2022-12-13 | NC
| GUP | YD00 | P6 | AE | 151522 |  | GUP-YD00-P6AE-151522 | OUTLINE DRAWING_115kV AIS CONTROL & PROTECTION SYSTEM (Harmon S/S) | FI | 2022-02-13 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FA |  | Harmon S/S | Harmon S/S | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-890 | 2023-11-09 | 2 | CRS-GUP-DHI-DT-22-698 | 2022-09-03 | NC | DHI-GUP-DT-22-140 | 2022-03-29 | 0 | CRS-GUP-DHI-DT-22-307 | 2022-04-23 | RC | DE-GUP-DT-E-22-374 | 2022-07-08 | 1 | CRS-GUP-DHI-DT-22-698 | 2022-09-03 | NC | DE-GUP-DT-E-23-890 | 2023-11-09 | 2
| GUP | YF02 | P6 | AE | 151531 |  | GUP-YF02-P6AE-151531 | SCHEMATIC DIAGRAM_115kV AIS HV EQUIPMENT (Harmon S/S) | FA | 2022-02-15 | 2022-07-13 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA |  | Harmon S/S | Harmon S/S | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-084 | 2023-01-27 | 1 | CRS-GUP-DHI-DT-22-1077 | 2022-11-19 | AA | DHI-GUP-DT-22-135 | 2022-03-25 | A | CRS-GUP-DHI-DT-22-296 | 2022-04-17 | RC | DE-GUP-DT-E-22-402 | 2022-07-15 | B | CRS-GUP-DHI-DT-22-581 | 2022-08-08 | RC | DE-GUP-DT-E-22-536 | 2022-08-23 | C | CRS-GUP-DHI-DT-22-760 | 2022-09-14 | AC | DE-GUP-DT-E-22-840 | 2022-10-21 | 0(CP) | CRS-GUP-DHI-DT-22-1077 | 2022-11-19 | AA | DE-GUP-DT-E-23-084 | 2023-01-27 | 1
| GUP | YF02 | P6 | AE | 151532 |  | GUP-YF02-P6AE-151532 | SCHEMATIC DIAGRAM_115kV AIS CONTROL & PROTECTION SYSTEM (Harmon S/S) | FA | 2022-03-31 | 2022-06-23 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA |  | Harmon S/S | Harmon S/S | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-890 | 2023-11-09 | 1 | 자체 CRS 개정 후 제출 | 2023-11-08 | N/A | DE-GUP-DT-E-22-416 | 2022-07-19 | A | CRS-GUP-DHI-DT-22-813 | 2022-09-20 | RC | DE-GUP-DT-E-22-840 | 2022-10-21 | B | CRS-GUP-DHI-DT-22-1077 | 2022-11-19 | RC | DE-GUP-DT-E-22-1155 | 2022-12-22 | C | CRS-GUP-DHI-DT-22-1413 | 2023-01-11 | RC | DE-GUP-DT-E-23-103 | 2023-02-01 | D | CRS-GUP-DHI-DT-23-1639 | 2023-03-04 | AA | DE-GUP-DT-E-23-350 | 2023-03-23 | 0 | 자체 CRS 개정 후 제출 | 2023-11-08 | N/A | DE-GUP-DT-E-23-890 | 2023-11-09 | 1
| GUP | YD00 | P6 | AE | 151541 |  | GUP-YD00-P6AE-151541 | LAYOUT DRAWING_115kV AIS SWITCHYARD (Harmon S/S) | FA | 2022-01-14 | 2022-07-13 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA |  | Harmon S/S | Harmon S/S | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-885 | 2022-10-31 | 0 | CRS-GUP-DHI-DT-22-1147 | 2022-11-23 | AA | DHI-GUP-DT-22-042 | 2022-01-27 | A | CRS-GUP-DHI-DT-22-204 | 2022-02-20 | RC | DHI-GUP-DT-22-206 | 2022-05-04 | B | CRS-GUP-DHI-DT-22-381 | 2022-05-31 | RC | DE-GUP-DT-E-22-307 | 2022-06-16 | C | CRS-GUP-DHI-DT-22-506 | 2022-07-10 | RC | DE-GUP-DT-E-22-402 | 2022-07-15 | D | CRS-GUP-DHI-DT-22-581 | 2022-08-08 | RC | DE-GUP-DT-E-22-514 | 2022-08-18 | E | CRS-GUP-DHI-DT-22-705 | 2022-09-03 | RC | DE-GUP-DT-E-22-663 | 2022-09-14 | F | CRS-GUP-DHI-DT-22-900 | 2022-10-12 | AA | DE-GUP-DT-E-22-885 | 2022-10-31 | 0 | CRS-GUP-DHI-DT-22-1147 | 2022-11-23 | AA
| GUP | YD00 | P6 | AE | 151543 |  | GUP-YD00-P6AE-151543 | FOUNDATION DRAWING_115kV AIS SWITCHYARD (Harmon S/S) | FI | 2022-01-14 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FA |  | Harmon S/S | Harmon S/S | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-840 | 2022-10-21 | 1 | CRS-GUP-DHI-DT-22-1014 | 2022-11-13 | NC | DHI-GUP-DT-22-042 | 2022-01-27 | 0 | CRS-GUP-DHI-DT-22-204 | 2022-02-20 | NC | DE-GUP-DT-E-22-840 | 2022-10-21 | 1 | CRS-GUP-DHI-DT-22-1014 | 2022-11-13 | NC
| GUP | YD04 | P6 | AE | 151701 |  | GUP-YD04-P6AE-151701 | CABLE TRAY & CONDUIT LAYOUT DRAWING_115kV AIS SWITCHYARD (Harmon S/S) | FI | 2022-01-29 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FA |  | Harmon S/S | Harmon S/S | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-549 | 2023-05-12 | 1 | CRS-GUP-DHI-DT-22-487 | 2022-07-06 | NC | DE-GUP-DT-E-22-270 | 2022-06-03 | 0 | CRS-GUP-DHI-DT-22-487 | 2022-07-06 | NC | DE-GUP-DT-E-23-549 | 2023-05-12 | 1
| GUP | YD04 | P6 | AE | 151702 |  | GUP-YD04-P6AE-151702 | EARTHING LAYOUT DRAWING_115kV AIS SWITCHYARD (Harmon S/S) | FI | 2022-01-29 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FA |  | Harmon S/S | Harmon S/S | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-183 | 2023-02-16 | 1 | CRS-GUP-DHI-DT-23-1732 | 2023-03-17 | NC | DHI-GUP-DT-22-042 | 2022-01-27 | 0 | CRS-GUP-DHI-DT-22-204 | 2022-02-20 | NC | DE-GUP-DT-E-23-183 | 2023-02-16 | 1 | CRS-GUP-DHI-DT-23-1732 | 2023-03-17 | NC
| GUP | YD04 | P6 | AE | 151703 |  | GUP-YD04-P6AE-151703 | LIGHTNING PROTECTION LAYOUT DRAWING_115kV AIS SWITCHYARD (Harmon S/S) | FI | 2022-01-29 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FA |  | Harmon S/S | Harmon S/S | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-115 | 2024-04-30 | 5 | CRS-GUP-DHI-DT-23-1588 | 2023-02-28 | NC | DHI-GUP-DT-22-042 | 2022-01-27 | 0 | CRS-GUP-DHI-DT-22-204 | 2022-02-20 | NC | DE-GUP-DT-E-22-231 | 2022-05-19 | 1 | CRS-GUP-DHI-DT-22-408 | 2022-06-10 | RC | DE-GUP-DT-E-22-359 | 2022-07-04 | 2 | CRS-GUP-DHI-DT-22-551 | 2022-07-27 | RC | DE-GUP-DT-E-22-686 | 2022-09-21 | 3 | CRS-GUP-DHI-DT-22-942 | 2022-10-22 | RC | DE-GUP-DT-E-23-084 | 2023-01-27 | 4 | CRS-GUP-DHI-DT-23-1588 | 2023-02-28 | NC | DE-GUP-DT-E-24-115 | 2024-04-30 | 5
| GUP | YD00 | P6 | ZEN | 151542 |  | GUP-YD00-P6ZEN-151542 | ELECTRICAL ROOM LAYOUT DRAWING_115kV AIS CONTROL BUILDING (Harmon S/S) | FA | 2022-01-29 | 2022-07-13 | 전력기술팀(Elec.) | 박경수 |  |  | G | FA |  | Harmon S/S | Harmon S/S | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-283 | 2022-06-10 | 0 | CRS-GUP-DHI-DT-22-397 | 2022-06-07 | AA | DHI-GUP-DT-22-042 | 2022-01-27 | A | CRS-GUP-DHI-DT-22-204 | 2022-02-20 | RC | DHI-GUP-DT-22-216 | 2022-05-12 | B | CRS-GUP-DHI-DT-22-397 | 2022-06-07 | AA | DE-GUP-DT-E-22-283 | 2022-06-10 | 0
| GUP | YL16 | P6 | ZEN | 151710 |  | GUP-YL16-P6ZEN-151710 | CABLE CONNECTION DIAGRAM & SCHEDULE_115kV AIS (Harmon S/S) | FI | 2024-02-15 |  | 전력기술팀(Elec.) | 박경수 |  |  | G | FI |  | Harmon S/S | Harmon S/S | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-043 | 2024-02-08 | 0 | CRS-GUP-DHI-DT-24-049 | 2024-04-15 | NC | DE-GUP-DT-E-24-043 | 2024-02-08 | 0 | CRS-GUP-DHI-DT-24-049 | 2024-04-15 | NC
| GUP | YR02 | P1 | AE | 154001 |  | GUP-YR02-P1AE-154001 | O&M MANUAL_115kV AIS HV EQUIPMENT | FI | 2024-06-30 |  | 전력기술팀(Elec.) | 박경수 | [5 empty] | CCPP | AIS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-136 | 2024-05-21 | 0 | CRS-GUP-DHI-DT-24-137 | 2024-12-16 | RC | DE-GUP-DT-E-24-136 | 2024-05-21 | 0 | CRS-GUP-DHI-DT-24-137 | 2024-12-16 | RC
| GUP | YR02 | P1 | BAT | 154011 |  | GUP-YR02-P1BAT-154011 | O&M MANUAL_GENERATOR STEP UP TRANSFORMER | FI | 2024-06-30 |  | 전력기술팀(Elec.) | 박경수 | [5 empty] | CCPP | Transformer | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-217 | 2024-08-30 | 1 | CRS-GUP-DHI-DT-24-064 | 2024-07-17 | NC | DE-GUP-DT-E-24-136 | 2024-05-21 | 0 | CRS-GUP-DHI-DT-24-064 | 2024-07-17 | NC | DE-GUP-DT-E-24-217 | 2024-08-30 | 1
| GUP | YR02 | P1 | BAA | 154031 |  | GUP-YR02-P1BAA-154031 | O&M MANUAL_NON-SEGREGATED PHASE BUSDUCT | FI | 2024-06-30 |  | 전력기술팀(Elec.) | 박경수 | [5 empty] | CCPP | NSPB | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-136 | 2024-05-21 | 0 | CRS-GUP-DHI-DT-24-061 | 2024-07-04 | NC | DE-GUP-DT-E-24-136 | 2024-05-21 | 0 | CRS-GUP-DHI-DT-24-061 | 2024-07-04 | NC
| GUP | YR02 | P1 | BAC | 154021 |  | GUP-YR02-P1BAC-154021 | O&M MANUAL_GENERATOR CIRCUIT BREAKER | FI | 2024-06-30 |  | 전력기술팀(Elec.) | 박경수 | [5 empty] | CCPP | GCB | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-136 | 2024-05-21 | 0 | CRS-GUP-DHI-DT-24-061 | 2024-07-04 | NC | DE-GUP-DT-E-24-136 | 2024-05-21 | 0 | CRS-GUP-DHI-DT-24-061 | 2024-07-04 | NC
| GUP | YR02 | P1 | BBA | 154041 |  | GUP-YR02-P1BBA-154041 | O&M MANUAL_MV SWITCHGEAR | FI | 2024-06-30 |  | 전력기술팀(Elec.) | 박경수 | [5 empty] | CCPP | MV SWGR | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-195 | 2024-08-06 | 0 | CRS-GUP-DHI-DT-24-140 | 2024-12-16 | RC | DE-GUP-DT-E-24-195 | 2024-08-06 | 0 | CRS-GUP-DHI-DT-24-140 | 2024-12-16 | RC
| GUP | YR02 | P1 | BFA | 154051 |  | GUP-YR02-P1BFA-154051 | O&M MANUAL_LV SWITCHGEAR / LV TRANSFORMER | FI | 2024-06-30 |  | 전력기술팀(Elec.) | 박경수 | [5 empty] | CCPP | LV SWGR | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-200 | 2024-08-09 | 0 | CRS-GUP-DHI-DT-24-141 | 2024-12-16 | RC | DE-GUP-DT-E-24-200 | 2024-08-09 | 0 | CRS-GUP-DHI-DT-24-141 | 2024-12-16 | RC
| GUP | YR02 | P1 | BTW | 154061 |  | GUP-YR02-P1BTW-154061 | O&M MANUAL_DC & UPS SYSTEM | FI | 2024-06-30 |  | 전력기술팀(Elec.) | 박경수 | [5 empty] | CCPP | DC & UPS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-136 | 2024-05-21 | 0 | CRS-GUP-DHI-DT-24-061 | 2024-07-04 | NC | DE-GUP-DT-E-24-136 | 2024-05-21 | 0 | CRS-GUP-DHI-DT-24-061 | 2024-07-04 | NC
| GUP | YR02 | P1 | ASR | 154071 |  | GUP-YR02-P1ASR-154071 | O&M MANUAL_FAULT MONITORING SYSTEM | FI | 2024-06-30 |  | 전력기술팀(Elec.) | 박경수 | [5 empty] | CCPP | FMS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-217 | 2024-08-30 | 0 | CRS-GUP-DHI-DT-25-008 | 2025-01-10 | NC | DE-GUP-DT-E-24-217 | 2024-08-30 | 0 | CRS-GUP-DHI-DT-25-008 | 2025-01-10 | NC
| GUP | YR02 | P1 | CYA | 154081 |  | GUP-YR02-P1CYA-154081 | O&M MANUAL_COMMUNICATION SYSTEM | FI | 2024-06-30 |  | 전력기술팀(Elec.) | 박경수 | [5 empty] | CCPP | Communication | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-220 | 2024-09-03 | 0 | CRS-GUP-DHI-DT-25-009 | 2025-01-10 | NC | DE-GUP-DT-E-24-220 | 2024-09-03 | 0 | CRS-GUP-DHI-DT-25-009 | 2025-01-10 | NC
| GUP | YR02 | P1 | PUR | 154091 |  | GUP-YR02-P1PUR-154091 | O&M MANUAL_CATHODIC PROTECTION SYSTEM | FI | 2024-06-30 |  | 전력기술팀(Elec.) | 박경수 | [5 empty] | CCPP | Cathodic Protection | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-195 | 2024-08-06 | 0 | CRS-GUP-DHI-DT-24-138 | 2024-12-16 | RC | DE-GUP-DT-E-24-195 | 2024-08-06 | 0 | CRS-GUP-DHI-DT-24-138 | 2024-12-16 | RC
| GUP | YD08 | P1 | ZEN | 160105 |  | GUP-YD08-P1ZEN-160105 | INSTRUMENT LOCATION DRAWING_INDEX, SYMBOL & LEGEND_BOP | FI | 2022-08-26 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Field Instrument | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-301 | 2024-12-23 | 4 | 자체 CRS 개정 후 제출 | 2024-12-22 | N/A | DE-GUP-DT-E-22-587 | 2022-08-31 | 0 | CRS-GUP-DHI-DT-22-793 | 2022-09-19 | NC | DE-GUP-DT-E-23-523 | 2023-05-04 | 1 | CRS-GUP-DHI-DT-23-1962 | 2023-06-01 | NC | DE-GUP-DT-E-23-781 | 2023-08-31 | 2 | 자체 CRS 개정 후 제출 | 2024-09-12 | N/A | DE-GUP-DT-E-23-234 | 2024-09-13 | 3 | 자체 CRS 개정 후 제출 | 2024-12-22 | N/A | DE-GUP-DT-E-24-301 | 2024-12-23 | 4
| GUP | YD08 | P1 | ZEN | 160106 |  | GUP-YD08-P1ZEN-160106 | INSTRUMENT LOCATION DRAWING_TURBINE BUILDING AREA_STG TURBINE_BOP | FI | 2022-08-26 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Field Instrument | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-234 | 2024-09-13 | 4 | 자체 CRS 개정 후 제출 | 2024-09-12 | N/A | DE-GUP-DT-E-22-587 | 2022-08-31 | 0 | CRS-GUP-DHI-DT-22-793 | 2022-09-19 | NC | DE-GUP-DT-E-23-523 | 2023-05-04 | 1 | CRS-GUP-DHI-DT-23-1962 | 2023-06-01 | NC | DE-GUP-DT-E-23-781 | 2023-08-31 | 2 | 자체 CRS 개정 후 제출 | 2023-12-21 | N/A | DE-GUP-DT-E-23-1007 | 2023-12-22 | 3 | 자체 CRS 개정 후 제출 | 2024-09-12 | N/A | DE-GUP-DT-E-23-234 | 2024-09-13 | 4
| GUP | YD08 | P1 | ZEN | 160107 |  | GUP-YD08-P1ZEN-160107 | INSTRUMENT LOCATION DRAWING_TURBINE BUILDING AREA_SURFACE CONDENSER_BOP | FI | 2022-08-26 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Field Instrument | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-234 | 2024-09-13 | 4 | 자체 CRS 개정 후 제출 | 2024-09-12 | N/A | DE-GUP-DT-E-22-587 | 2022-08-31 | 0 | CRS-GUP-DHI-DT-22-793 | 2022-09-19 | NC | DE-GUP-DT-E-23-523 | 2023-05-04 | 1 | CRS-GUP-DHI-DT-23-1962 | 2023-06-01 | NC | DE-GUP-DT-E-23-781 | 2023-08-31 | 2 | 자체 CRS 개정 후 제출 | 2024-02-07 | N/A | DE-GUP-DT-E-24-039 | 2024-02-08 | 3 | 자체 CRS 개정 후 제출 | 2024-09-12 | N/A | DE-GUP-DT-E-23-234 | 2024-09-13 | 4
| GUP | YD08 | P1 | ZEN | 160108 |  | GUP-YD08-P1ZEN-160108 | INSTRUMENT LOCATION DRAWING_TURBINE BUILDING AREA_CLOSED COOLING WATER_BOP | FI | 2022-08-26 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Field Instrument | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-301 | 2024-12-23 | 4 | 자체 CRS 개정 후 제출 | 2024-12-22 | N/A | DE-GUP-DT-E-22-587 | 2022-08-31 | 0 | CRS-GUP-DHI-DT-22-793 | 2022-09-19 | NC | DE-GUP-DT-E-23-523 | 2023-05-04 | 1 | CRS-GUP-DHI-DT-23-1962 | 2023-06-01 | NC | DE-GUP-DT-E-23-1007 | 2023-12-22 | 2 | 자체 CRS 개정 후 제출 | 2024-09-12 | N/A | DE-GUP-DT-E-23-234 | 2024-09-13 | 3 | 자체 CRS 개정 후 제출 | 2024-12-22 | N/A | DE-GUP-DT-E-24-301 | 2024-12-23 | 4
| GUP | YD08 | P1 | ZEN | 160109 |  | GUP-YD08-P1ZEN-160109 | INSTRUMENT LOCATION DRAWING_TURBINE BUILDING AREA_COOLING TOWER_BOP | FI | 2022-08-26 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Field Instrument | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-234 | 2024-09-13 | 3 | 자체 CRS 개정 후 제출 | 2024-09-12 | N/A | DE-GUP-DT-E-22-587 | 2022-08-31 | 0 | CRS-GUP-DHI-DT-22-793 | 2022-09-19 | NC | DE-GUP-DT-E-23-523 | 2023-05-04 | 1 | CRS-GUP-DHI-DT-23-1962 | 2023-06-01 | NC | DE-GUP-DT-E-23-1007 | 2023-12-22 | 2 | 자체 CRS 개정 후 제출 | 2024-09-12 | N/A | DE-GUP-DT-E-23-234 | 2024-09-13 | 3
| GUP | YD08 | P1 | ZEN | 160110 |  | GUP-YD08-P1ZEN-160110 | INSTRUMENT LOCATION DRAWING_FUEL OIL SYSTEM AREA_BOP | FI | 2022-08-26 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Field Instrument | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-523 | 2023-05-04 | 1 | CRS-GUP-DHI-DT-23-1962 | 2023-06-01 | NC | DE-GUP-DT-E-22-587 | 2022-08-31 | 0 | CRS-GUP-DHI-DT-22-793 | 2022-09-19 | NC | DE-GUP-DT-E-23-523 | 2023-05-04 | 1 | CRS-GUP-DHI-DT-23-1962 | 2023-06-01 | NC
| GUP | YD08 | P1 | ZEN | 160112 |  | GUP-YD08-P1ZEN-160112 | INSTRUMENT LOCATION DRAWING_DEMI WATER AREA_BOP | FI | 2022-08-26 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Field Instrument | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-234 | 2024-09-13 | 3 | 자체 CRS 개정 후 제출 | 2024-09-12 | N/A | DE-GUP-DT-E-22-587 | 2022-08-31 | 0 | CRS-GUP-DHI-DT-22-793 | 2022-09-19 | NC | DE-GUP-DT-E-23-523 | 2023-05-04 | 1 | CRS-GUP-DHI-DT-23-1962 | 2023-06-01 | NC | DE-GUP-DT-E-23-1007 | 2023-12-22 | 2 | 자체 CRS 개정 후 제출 | 2024-09-12 | N/A | DE-GUP-DT-E-23-234 | 2024-09-13 | 3
| GUP | YD08 | P1 | ZEN | 160113 |  | GUP-YD08-P1ZEN-160113 | INSTRUMENT LOCATION DRAWING_MISCELLANEOUS_BOP | FI | 2022-08-26 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Field Instrument | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-301 | 2024-12-23 | 5 | 자체 CRS 개정 후 제출 | 2024-12-22 | N/A | DE-GUP-DT-E-22-587 | 2022-08-31 | 0 | CRS-GUP-DHI-DT-22-793 | 2022-09-19 | NC | DE-GUP-DT-E-23-523 | 2023-05-04 | 1 | CRS-GUP-DHI-DT-23-1962 | 2023-06-01 | NC | DE-GUP-DT-E-23-1007 | 2023-12-22 | 2 | 자체 CRS 개정 후 제출 | 2024-03-17 | N/A | DE-GUP-DT-E-24-083 | 2024-03-18 | 3 | 자체 CRS 개정 후 제출 | 2024-09-12 | N/A | DE-GUP-DT-E-23-234 | 2024-09-13 | 4 | 자체 CRS 개정 후 제출 | 2024-12-22 | N/A | DE-GUP-DT-E-24-301 | 2024-12-23 | 5
| GUP | YD02 | P1 | ZEN | 160130 |  | GUP-YD02-P1ZEN-160130 | CONDUIT LAYOUT DRAWING_INDEX, SYMBOL & LEGEND_BOP | FI | 2022-10-26 |  | 계측기술팀(I&C) | 김려도 | [5 empty] | CCPP | Conduit | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-300 | 2024-12-23 | 4 | 자체 CRS 개정 후 제출 | 2024-12-20 | N/A | DE-GUP-DT-E-22-881 | 2022-10-31 | 0 | CRS-GUP-DHI-DT-22-1197 | 2022-11-30 | NC | DE-GUP-DT-E-23-398 | 2023-03-30 | 1 | CRS-GUP-DHI-DT-23-1854 | 2023-04-19 | NC | DE-GUP-DT-E-23-972 | 2023-12-05 | 2 | 자체 CRS 개정 후 제출 | 2024-09-12 | N/A | DE-GUP-DT-E-24-233 | 2024-09-13 | 3 | 자체 CRS 개정 후 제출 | 2024-12-20 | N/A | DE-GUP-DT-E-24-300 | 2024-12-23 | 4
| GUP | YD02 | P1 | ZEN | 160131 |  | GUP-YD02-P1ZEN-160131 | CONDUIT LAYOUT DRAWING_TURBINE BUILDING AREA_STG TURBINE_BOP | FI | 2022-10-26 |  | 계측기술팀(I&C) | 김려도 | [5 empty] | CCPP | Conduit | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-300 | 2024-12-23 | 6 | 자체 CRS 개정 후 제출 | 2024-12-20 | N/A | DE-GUP-DT-E-22-881 | 2022-10-31 | 0 | CRS-GUP-DHI-DT-22-1197 | 2022-11-30 | NC | DE-GUP-DT-E-23-398 | 2023-03-30 | 1 | CRS-GUP-DHI-DT-23-1854 | 2023-04-19 | NC | DE-GUP-DT-E-23-972 | 2023-12-05 | 2 | 자체 CRS 개정 후 제출 | 2024-02-07 | N/A | DE-GUP-DT-E-24-039 | 2024-02-08 | 3 | 자체 CRS 개정 후 제출 | 2024-03-17 | N/A | DE-GUP-DT-E-24-083 | 2024-03-18 | 4 | 자체 CRS 개정 후 제출 | 2024-09-12 | N/A | DE-GUP-DT-E-24-233 | 2024-09-13 | 5 | 자체 CRS 개정 후 제출 | 2024-12-20 | N/A | DE-GUP-DT-E-24-300 | 2024-12-23 | 6
| GUP | YD02 | P1 | ZEN | 160132 |  | GUP-YD02-P1ZEN-160132 | CONDUIT LAYOUT DRAWING_TURBINE BUILDING AREA_SURFACE CONDENSER_BOP | FI | 2022-10-26 |  | 계측기술팀(I&C) | 김려도 | [5 empty] | CCPP | Conduit | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-233 | 2024-09-13 | 4 | 자체 CRS 개정 후 제출 | 2024-09-12 | N/A | DE-GUP-DT-E-22-881 | 2022-10-31 | 0 | CRS-GUP-DHI-DT-22-1197 | 2022-11-30 | NC | DE-GUP-DT-E-23-398 | 2023-03-30 | 1 | CRS-GUP-DHI-DT-23-1854 | 2023-04-19 | NC | DE-GUP-DT-E-23-972 | 2023-12-05 | 2 | 자체 CRS 개정 후 제출 | 2024-02-07 | N/A | DE-GUP-DT-E-24-039 | 2024-02-08 | 3 | 자체 CRS 개정 후 제출 | 2024-09-12 | N/A | DE-GUP-DT-E-24-233 | 2024-09-13 | 4
| GUP | YD02 | P1 | ZEN | 160133 |  | GUP-YD02-P1ZEN-160133 | CONDUIT LAYOUT DRAWING_TURBINE BUILDING AREA_CLOSED COOLING WATER_BOP | FI | 2022-10-26 |  | 계측기술팀(I&C) | 김려도 | [5 empty] | CCPP | Conduit | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-300 | 2024-12-23 | 5 | 자체 CRS 개정 후 제출 | 2024-12-20 | N/A | DE-GUP-DT-E-22-881 | 2022-10-31 | 0 | CRS-GUP-DHI-DT-22-1197 | 2022-11-30 | NC | DE-GUP-DT-E-23-398 | 2023-03-30 | 1 | CRS-GUP-DHI-DT-23-1854 | 2023-04-19 | NC | DE-GUP-DT-E-23-972 | 2023-12-05 | 2 | 자체 CRS 개정 후 제출 | 2024-02-07 | N/A | DE-GUP-DT-E-24-039 | 2024-02-08 | 3 | 자체 CRS 개정 후 제출 | 2024-09-12 | N/A | DE-GUP-DT-E-24-233 | 2024-09-13 | 4 | 자체 CRS 개정 후 제출 | 2024-12-20 | N/A | DE-GUP-DT-E-24-300 | 2024-12-23 | 5
| GUP | YD02 | P1 | ZEN | 160134 |  | GUP-YD02-P1ZEN-160134 | CONDUIT LAYOUT DRAWING_TURBINE BUILDING AREA_COOLING TOWER_BOP | FI | 2022-10-26 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Conduit | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-300 | 2024-12-23 | 5 | 자체 CRS 개정 후 제출 | 2024-12-20 | N/A | DE-GUP-DT-E-22-881 | 2022-10-31 | 0 | CRS-GUP-DHI-DT-22-1197 | 2022-11-30 | NC | DE-GUP-DT-E-23-398 | 2023-03-30 | 1 | CRS-GUP-DHI-DT-23-1854 | 2023-04-19 | NC | DE-GUP-DT-E-23-972 | 2023-12-05 | 2 | 자체 CRS 개정 후 제출 | 2024-02-07 | N/A | DE-GUP-DT-E-24-039 | 2024-02-08 | 3 | 자체 CRS 개정 후 제출 | 2024-09-12 | N/A | DE-GUP-DT-E-24-233 | 2024-09-13 | 4 | 자체 CRS 개정 후 제출 | 2024-12-20 | N/A | DE-GUP-DT-E-24-300 | 2024-12-23 | 5
| GUP | YD02 | P1 | ZEN | 160135 |  | GUP-YD02-P1ZEN-160135 | CONDUIT LAYOUT DRAWING_FUEL OIL SYSTEM AREA_BOP | FI | 2022-10-26 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Conduit | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-039 | 2024-02-08 | 3 | 자체 CRS 개정 후 제출 | 2024-02-07 | N/A | DE-GUP-DT-E-22-881 | 2022-10-31 | 0 | CRS-GUP-DHI-DT-22-1197 | 2022-11-30 | NC | DE-GUP-DT-E-23-398 | 2023-03-30 | 1 | CRS-GUP-DHI-DT-23-1854 | 2023-04-19 | NC | DE-GUP-DT-E-23-972 | 2023-12-05 | 2 | 자체 CRS 개정 후 제출 | 2024-02-07 | N/A | DE-GUP-DT-E-24-039 | 2024-02-08 | 3
| GUP | YD02 | P1 | ZEN | 160137 |  | GUP-YD02-P1ZEN-160137 | CONDUIT LAYOUT DRAWING_DEMI WATER AREA_BOP | FI | 2022-10-26 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Conduit | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-233 | 2024-09-13 | 4 | 자체 CRS 개정 후 제출 | 2024-09-12 | N/A | DE-GUP-DT-E-22-881 | 2022-10-31 | 0 | CRS-GUP-DHI-DT-22-1197 | 2022-11-30 | NC | DE-GUP-DT-E-23-398 | 2023-03-30 | 1 | CRS-GUP-DHI-DT-23-1854 | 2023-04-19 | NC | DE-GUP-DT-E-23-972 | 2023-12-05 | 2 | 자체 CRS 개정 후 제출 | 2024-02-07 | N/A | DE-GUP-DT-E-24-039 | 2024-02-08 | 3 | 자체 CRS 개정 후 제출 | 2024-09-12 | N/A | DE-GUP-DT-E-24-233 | 2024-09-13 | 4
| GUP | YD02 | P1 | ZEN | 160138 |  | GUP-YD02-P1ZEN-160138 | CONDUIT LAYOUT DRAWING_MISCELLANEOUS_BOP | FI | 2022-10-26 |  | 계측기술팀(I&C) | 김려도 | [5 empty] | CCPP | Conduit | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-300 | 2024-12-23 | 6 | 자체 CRS 개정 후 제출 | 2024-12-20 | N/A | DE-GUP-DT-E-22-881 | 2022-10-31 | 0 | CRS-GUP-DHI-DT-22-1197 | 2022-11-30 | NC | DE-GUP-DT-E-23-398 | 2023-03-30 | 1 | CRS-GUP-DHI-DT-23-1854 | 2023-04-19 | NC | DE-GUP-DT-E-23-972 | 2023-12-05 | 2 | 자체 CRS 개정 후 제출 | 2024-02-07 | N/A | DE-GUP-DT-E-24-039 | 2024-02-08 | 3 | 자체 CRS 개정 후 제출 | 2024-03-17 | N/A | DE-GUP-DT-E-24-083 | 2024-03-18 | 4 | 자체 CRS 개정 후 제출 | 2024-09-12 | N/A | DE-GUP-DT-E-24-233 | 2024-09-13 | 5 | 자체 CRS 개정 후 제출 | 2024-12-20 | N/A | DE-GUP-DT-E-24-300 | 2024-12-23 | 6
| GUP | YS05 | P1 | ZEN | 160125 |  | GUP-YS05-P1ZEN-160125 | TYPICAL I&C CABLE INSTALLATION DRAWING_CONTROL VALVE | FI | 2021-08-31 |  | 계측기술팀(I&C) | 우현아 | [5 empty] | CCPP | Cable | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-199 | 2024-08-09 | 2 | CRS-GUP-DHI-DT-21-056 | 2021-11-07 | NC | DHI-GUP-DT-21-019 | 2021-09-09 | 0 | CRS-GUP-DHI-DT-21-006 | 2021-09-27 | RC | DHI-GUP-DT-21-072 | 2021-10-22 | 1 | CRS-GUP-DHI-DT-21-056 | 2021-11-07 | NC | DE-GUP-DT-E-24-199 | 2024-08-09 | 2
| GUP | YS05 | P1 | ZEN | 160126 |  | GUP-YS05-P1ZEN-160126 | TYPICAL I&C CABLE INSTALLATION DRAWING_MOV | FI | 2021-08-31 |  | 계측기술팀(I&C) | 우현아 | [5 empty] | CCPP | Cable | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-199 | 2024-08-09 | 2 | CRS-GUP-DHI-DT-21-056 | 2021-11-07 | NC | DHI-GUP-DT-21-019 | 2021-09-09 | 0 | CRS-GUP-DHI-DT-21-006 | 2021-09-27 | RC | DHI-GUP-DT-21-072 | 2021-10-22 | 1 | CRS-GUP-DHI-DT-21-056 | 2021-11-07 | NC | DE-GUP-DT-E-24-199 | 2024-08-09 | 2
| GUP | YS05 | P1 | ZEN | 160127 |  | GUP-YS05-P1ZEN-160127 | TYPICAL I&C CABLE INSTALLATION DRAWING_TT BOX AND JUNCTION BOX | FI | 2021-08-31 |  | 계측기술팀(I&C) | 우현아 | [5 empty] | CCPP | Cable | I&C | 3 | 2025-06-30 |  |  | DHI-GUP-DT-21-072 | 2021-10-22 | 1 | CRS-GUP-DHI-DT-21-056 | 2021-11-07 | NC | DHI-GUP-DT-21-019 | 2021-09-09 | 0 | CRS-GUP-DHI-DT-21-006 | 2021-09-27 | RC | DHI-GUP-DT-21-072 | 2021-10-22 | 1 | CRS-GUP-DHI-DT-21-056 | 2021-11-07 | NC
| GUP | YS05 | P1 | ZEN | 160128 |  | GUP-YS05-P1ZEN-160128 | TYPICAL I&C CABLE INSTALLATION DRAWING_FIELD INSTRUMENT | FI | 2021-08-31 |  | 계측기술팀(I&C) | 우현아 | [5 empty] | CCPP | Cable | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-199 | 2024-08-09 | 2 | CRS-GUP-DHI-DT-21-056 | 2021-11-07 | NC | DHI-GUP-DT-21-019 | 2021-09-09 | 0 | CRS-GUP-DHI-DT-21-006 | 2021-09-27 | RC | DHI-GUP-DT-21-072 | 2021-10-22 | 1 | CRS-GUP-DHI-DT-21-056 | 2021-11-07 | NC | DE-GUP-DT-E-24-199 | 2024-08-09 | 2
| GUP | YS05 | P1 | ZEN | 160129 |  | GUP-YS05-P1ZEN-160129 | TYPICAL I&C CABLE INSTALLATION DRAWING_CONDUIT SUPPORT | FI | 2021-08-31 |  | 계측기술팀(I&C) | 우현아 | [5 empty] | CCPP | Cable | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-199 | 2024-08-09 | 2 | CRS-GUP-DHI-DT-21-056 | 2021-11-07 | NC | DHI-GUP-DT-21-019 | 2021-09-09 | 0 | CRS-GUP-DHI-DT-21-006 | 2021-09-27 | RC | DHI-GUP-DT-21-072 | 2021-10-22 | 1 | CRS-GUP-DHI-DT-21-056 | 2021-11-07 | NC | DE-GUP-DT-E-24-199 | 2024-08-09 | 2
| GUP | YS02 | P1 | ZEN | 160103 |  | GUP-YS02-P1ZEN-160103 | I&C CABLE INTERCONNECTION WIRING DIAGRAM_INTERFACE WITH OTHER CONTROL SYSTEM | FI | 2023-02-11 |  | 계측기술팀(I&C) | 김려도 | [5 empty] | CCPP | Cable | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-302 | 2024-12-27 | 4 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-23-227 | 2023-02-22 | 0 | CRS-GUP-DHI-DT-23-1701 | 2023-03-14 | NC | DE-GUP-DT-E-23-972 | 2023-12-05 | 1 | 자체 CRS 개정 후 제출 | 2024-04-25 | N/A | DE-GUP-DT-E-24-112 | 2024-04-26 | 2 | 자체 CRS 개정 후 제출 | 2024-09-12 | N/A | DE-GUP-DT-E-24-235 | 2024-09-13 | 3 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-24-302 | 2024-12-27 | 4
| GUP | YL16 | P1 | ZEN | 160092 |  | GUP-YL16-P1ZEN-160092 | I&C CABLE SCHEDULE_INTERFACE WITH OTHER CONTROL SYSTEM | FI | 2022-10-26 |  | 계측기술팀(I&C) | 김려도 | [5 empty] | CCPP | Cable | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-303 | 2024-12-27 | 5 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-22-868 | 2022-10-27 | 0 | CRS-GUP-DHI-DT-22-1053 | 2022-11-17 | RC | DE-GUP-DT-E-23-247 | 2023-02-27 | 1 | CRS-GUP-DHI-DT-23-1741 | 2023-03-17 | NC | DE-GUP-DT-E-23-584 | 2023-05-25 | 2 | CRS-GUP-DHI-DT-23-1993 | 2023-06-13 | NC | DE-GUP-DT-E-23-972 | 2023-12-05 | 3 | 자체 CRS 개정 후 제출 | 2024-03-18 | N/A | DE-GUP-DT-E-24-083 | 2024-03-19 | 4 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-24-303 | 2024-12-27 | 5
| GUP | YS02 | P1 | ZEN | 160102 |  | GUP-YS02-P1ZEN-160102 | I&C CABLE INTERCONNECTION WIRING DIAGRAM_MISCELLANEOUS SYSTEM | FI | 2023-02-11 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Cable | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-302 | 2024-12-27 | 4 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-23-227 | 2023-02-22 | 0 | CRS-GUP-DHI-DT-23-1701 | 2023-03-14 | NC | DE-GUP-DT-E-23-972 | 2023-12-05 | 1 | 자체 CRS 개정 후 제출 | 2024-04-25 | N/A | DE-GUP-DT-E-24-112 | 2024-04-26 | 2 | 자체 CRS 개정 후 제출 | 2024-09-12 | N/A | DE-GUP-DT-E-24-235 | 2024-09-13 | 3 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-24-302 | 2024-12-27 | 4
| GUP | YL16 | P1 | ZEN | 160093 |  | GUP-YL16-P1ZEN-160093 | I&C CABLE SCHEDULE_MISCELLANEOUS SYSTEM | FI | 2022-10-26 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Cable | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-303 | 2024-12-27 | 5 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-22-868 | 2022-10-27 | 0 | CRS-GUP-DHI-DT-22-1053 | 2022-11-17 | RC | DE-GUP-DT-E-23-247 | 2023-02-27 | 1 | CRS-GUP-DHI-DT-23-1741 | 2023-03-17 | NC | DE-GUP-DT-E-23-584 | 2023-05-25 | 2 | CRS-GUP-DHI-DT-23-1993 | 2023-06-13 | NC | DE-GUP-DT-E-23-972 | 2023-12-05 | 3 | 자체 CRS 개정 후 제출 | 2024-03-18 | N/A | DE-GUP-DT-E-24-083 | 2024-03-19 | 4 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-24-303 | 2024-12-27 | 5
| GUP | YS02 | P1 | ZEN | 160104 |  | GUP-YS02-P1ZEN-160104 | I&C CABLE INTERCONNECTION WIRING DIAGRAM_ELECTRICAL EQUIPMENT INTERFACE_BOP | FI | 2023-02-11 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Cable | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-302 | 2024-12-27 | 4 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-23-227 | 2023-02-22 | 0 | CRS-GUP-DHI-DT-23-1701 | 2023-03-14 | NC | DE-GUP-DT-E-23-972 | 2023-12-05 | 1 | 자체 CRS 개정 후 제출 | 2024-04-25 | N/A | DE-GUP-DT-E-24-112 | 2024-04-26 | 2 | 자체 CRS 개정 후 제출 | 2024-09-12 | N/A | DE-GUP-DT-E-24-235 | 2024-09-13 | 3 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-24-302 | 2024-12-27 | 4
| GUP | CV03 | P1 | ZEN | 160074 |  | GUP-CV03-P1ZEN-160074 | TECHNICAL SPECIFICATION & DATASHEET_CONTROL VALVE | FA | 2022-07-26 | 2022-10-27 | 계측기술팀(I&C) | 우현아 |  |  |  |  | Control Valve | CCPP | Control Valve | I&C | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-221 | 2024-09-03 | 2 | 자체 CRS 개정 후 제출 | 2024-09-02 | N/A | DE-GUP-DT-E-22-472 | 2022-07-28 | A | CRS-GUP-DHI-DT-22-652 | 2022-08-20 | RC | DE-GUP-DT-E-22-645 | 2022-09-08 | B | CRS-GUP-DHI-DT-22-859 | 2022-09-24 | AA | DE-GUP-DT-E-22-903 | 2022-11-03 | 0 | CRS-GUP-DHI-DT-22-1150 | 2022-11-23 | AA | DE-GUP-DT-E-23-041 | 2023-01-18 | 1 | 자체 CRS 개정 후 제출 | 2024-09-02 | N/A | DE-GUP-DT-E-24-221 | 2024-09-03 | 2
| GUP | CV03 | P1 | ZEN | 160082 |  | GUP-CV03-P1ZEN-160082 | TECHNICAL SPECIFICATION & DATASHEET_WEATHER STATION | FA | 2022-12-14 | 2023-04-15 | 계측기술팀(I&C) | 고경환 |  |  |  |  | Weather Station | CCPP | Weather Station | I&C | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-143 | 2024-06-03 | 1 | 자체 CRS 개정 후 제출 | 2024-06-02 | N/A | DE-GUP-DT-E-23-122 | 2023-02-06 | A | CRS-GUP-DHI-DT-23-1682 | 2023-03-13 | AA | DE-GUP-DT-E-23-389 | 2023-03-29 | 0 | 자체 CRS 개정 후 제출 | 2024-06-02 | N/A | DE-GUP-DT-E-24-143 | 2024-06-03 | 1
| GUP | YL01 | P1 | ZEN | 160071 |  | GUP-YL01-P1ZEN-160071 | DDC IO LIST_HVAC | FI | 2022-08-17 |  | 계측기술팀(I&C) | 우현아 |  |  |  |  | HVAC | CCPP | HVAC | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-009 | 2025-01-17 | 4 | 자체 CRS 개정 후 제출 | 2025-01-16 | N/A | DE-GUP-DT-E-22-475 | 2022-07-29 | 0 | CRS-GUP-DHI-DT-22-667 | 2022-08-22 | NC | DE-GUP-DT-E-23-488_ | 2023-04-21 | 1 | CRS-GUP-DHI-DT-23-1913 | 2023-05-05 | NC | DE-GUP-DT-E-23-782 | 2023-08-31 | 2 | 자체 CRS 개정 후 제출 | 2024-08-12 | N/A | DE-GUP-DT-E-24-202 | 2024-08-13 | 3 | 자체 CRS 개정 후 제출 | 2025-01-16 | N/A | DE-GUP-DT-E-25-009 | 2025-01-17 | 4
| GUP | YL00 | P1 | ZEN | 160072 |  | GUP-YL00-P1ZEN-160072 | TECHNICAL SPECIFICATION & DATASHEET_FIELD INSTRUMENT_HVAC I&C | FI | 2022-08-26 |  | 계측기술팀(I&C) | 우현아 |  |  |  |  | HVAC | CCPP | HVAC | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1161 | 2022-12-22 | 1 | CRS-GUP-DHI-DT-22-1377 | 2022-12-31 | NC | DE-GUP-DT-E-22-475 | 2022-07-29 | 0 | CRS-GUP-DHI-DT-22-667 | 2022-08-22 | NC | DE-GUP-DT-E-22-1161 | 2022-12-22 | 1 | CRS-GUP-DHI-DT-22-1377 | 2022-12-31 | NC
| GUP | CV03 | P1 | ZEN | 160073 |  | GUP-CV03-P1ZEN-160073 | TECHNICAL SPECIFICATION & DATASHEET_HVAC I&C | FA | 2022-09-15 | 2022-11-15 | 계측기술팀(I&C) | 우현아 |  |  |  |  | HVAC | CCPP | HVAC | I&C | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-486 | 2023-04-21 | 2 | CRS-GUP-DHI-DT-23-1911 | 2023-05-05 | AA | DE-GUP-DT-E-22-618 | 2022-09-05 | A | CRS-GUP-DHI-DT-22-804 | 2022-09-19 | RC | DE-GUP-DT-E-22-877 | 2022-10-28 | B | CRS-GUP-DHI-DT-22-1023 | 2022-11-13 | AA | DE-GUP-DT-E-22-952 | 2022-11-17 | 0 | CRS-GUP-DHI-DT-22-1240 | 2022-12-13 | AA | DE-GUP-DT-E-23-060 | 2023-01-20 | 1 | N/A(자체 CRS 개정 후 제출) | 2023-04-20 | N/C | DE-GUP-DT-E-23-486 | 2023-04-21 | 2 | CRS-GUP-DHI-DT-23-1911 | 2023-05-05 | AA
| GUP | YF00 | P1 | ZEN | 160053 |  | GUP-YF00-P1ZEN-160053 | CONTROL LOGIC & LOOP DIAGRAM_HVAC | FI | 2022-09-15 |  | 계측기술팀(I&C) | 우현아 |  |  |  |  | HVAC | CCPP | HVAC | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-782 | 2023-08-31 | 1 | CRS-GUP-DHI-DT-22-927 | 2022-10-19 | NC | DE-GUP-DT-E-22-757 | 2022-10-05 | 0 | CRS-GUP-DHI-DT-22-927 | 2022-10-19 | NC | DE-GUP-DT-E-23-782 | 2023-08-31 | 1
| GUP | CV03 | P1 | ZEN | 160080 |  | GUP-CV03-P1ZEN-160080 | TECHNICAL SPECIFICATION_JUNCTION BOX & RACKS | FI | 2022-11-12 |  | 계측기술팀(I&C) | 백지원 |  |  | G | FI | Junction Box & Racks | CCPP | Junction Box | I&C | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-203 | 2024-08-20 | 4 | 자체 CRS 개정 후 제출 | 2024-08-19 | N/A | DE-GUP-DT-E-22-1179 | 2022-12-23 | 0 | CRS-GUP-DHI-DT-22-1401 | 2023-01-07 | NC | DE-GUP-DT-E-23-357 | 2023-03-24 | 1 | CRS-GUP-DHI-DT-23-1829 | 2023-04-12 | NC | DE-GUP-DT-E-23-552 | 2023-05-15 | 2 | CRS-GUP-DHI-DT-23-1973 | 2023-06-01 | NC | DE-GUP-DT-E-24-058 | 2024-02-26 | 3 | 자체 CRS 개정 후 제출 | 2024-08-19 | N/A | DE-GUP-DT-E-24-203 | 2024-08-20 | 4
| GUP | CV03 | P1 | ZEN | 160078 |  | GUP-CV03-P1ZEN-160078 | TECHNICAL SPECIFICATION & DATASHEET_PROCESS TRANSMITTER_BOP | FA | 2022-08-26 | 2022-11-28 | 계측기술팀(I&C) | 신동인 |  |  |  |  | Process Transmitter | CCPP | Field Instrument | I&C | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-25-085 | 2025-07-15 | 2 | 자체 CRS 개정 후 제출 | 2023-11-07 | N/A | DE-GUP-DT-E-22-558 | 2022-08-25 | A | CRS-GUP-DHI-DT-22-755 | 2022-09-12 | RC | DE-GUP-DT-E-22-915 | 2022-11-08 | B | CRS-GUP-DHI-DT-22-1181 | 2022-11-30 | AA | DE-GUP-DT-E-22-1085 | 2022-12-14 | 0 | 자체 CRS 개정 후 제출 | 2023-11-07 | N/A | DE-GUP-DT-E-23-888 | 2023-11-08 | 1 |  |  |  | DE-GUP-DT-E-25-085 | 2025-07-15 | 2
| GUP | CV03 | P1 | ZEN | 160077 |  | GUP-CV03-P1ZEN-160077 | TECHNICAL SPECIFICATION & DATASHEET_LOCAL INSTRUMENT_BOP | FA | 2022-08-26 | 2022-11-28 | 계측기술팀(I&C) | 신동인 |  |  |  |  | Local Insturment | CCPP | Field Instrument | I&C | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-820 | 2023-09-22 | 1 | 자체 CRS 개정 후 제출 | 2023-09-21 | N/A | DE-GUP-DT-E-22-516 | 2022-08-18 | A | CRS-GUP-DHI-DT-22-780 | 2022-09-19 | RC | DE-GUP-DT-E-22-804 | 2022-10-14 | B | CRS-GUP-DHI-DT-22-980 | 2022-11-07 | AA | DE-GUP-DT-E-22-1048 | 2022-12-08 | 0 | 자체 CRS 개정 후 제출 | 2023-09-21 | N/A | DE-GUP-DT-E-23-820 | 2023-09-22 | 1
| GUP | CV03 | P1 | ZEN | 160079 |  | GUP-CV03-P1ZEN-160079 | TECHNICAL SPECIFICATION & DATASHEET_FLOW ELEMENT_BOP | FA | 2022-08-26 | 2022-10-28 | 계측기술팀(I&C) | 신동인 |  |  |  |  | Flow Element | CCPP | Field Instrument | I&C | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-888 | 2023-11-08 | 1 | CRS-GUP-DHI-DT-22-1153 | 2022-11-23 | AA | DE-GUP-DT-E-22-482 | 2022-07-29 | A | CRS-GUP-DHI-DT-22-654 | 2022-08-20 | RC | DE-GUP-DT-E-22-744 | 2022-09-30 | B | CRS-GUP-DHI-DT-22-922 | 2022-10-19 | AA | DE-GUP-DT-E-22-929 | 2022-11-09 | 0 | CRS-GUP-DHI-DT-22-1153 | 2022-11-23 | AA | DE-GUP-DT-E-23-888 | 2023-11-08 | 1
| GUP | YL00 | P1 | ZEN | 160076 |  | GUP-YL00-P1ZEN-160076 | FIELD INSTRUMENT LIST_BOP | FA | 2022-02-16 | 2023-01-03 | 계측기술팀(I&C) | 신동인 | [5 empty] | CCPP | Field Instrument | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-085 | 2025-07-15 | 2 | CRS-GUP-DHI-DT-22-1285 | 2022-12-21 | AA | DHI-GUP-DT-21-105 | 2021-11-17 | A | CRS-GUP-DHI-DT-21-079 | 2021-12-08 | RC | DE-GUP-DT-E-22-559 | 2022-08-25 | B | CRS-GUP-DHI-DT-22-756 | 2022-09-12 | AA | DE-GUP-DT-E-22-1033 | 2022-12-05 | 0 | CRS-GUP-DHI-DT-22-1285 | 2022-12-21 | AA | DE-GUP-DT-E-23-888 | 2023-11-08 | 1 |  |  |  | DE-GUP-DT-E-25-085 | 2025-07-15 | 2
| GUP | CV03 | P1 | ZEN | 160081 |  | GUP-CV03-P1ZEN-160081 | TECHNICAL SPECIFICATION_I&C CABLE_BOP | FI | 2022-11-10 |  | 계측기술팀(I&C) | 백지원 |  |  |  |  | I&C Cable | CCPP | Cable | I&C | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1075 | 2022-12-09 | 0 | CRS-GUP-DHI-DT-22-1365 | 2022-12-30 | NC | DE-GUP-DT-E-22-1075 | 2022-12-09 | 0 | CRS-GUP-DHI-DT-22-1365 | 2022-12-30 | NC
| GUP | CV03 | P1 | ZEN | 160084 |  | GUP-CV03-P1ZEN-160084 | TECHNICAL SPECIFICATION_I&C CONDUIT & ACCESSORIES_BOP | FI | 2022-12-23 |  | 계측기술팀(I&C) | 백지원 |  |  |  |  | I&C Conduit | CCPP | Conduit | I&C | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1178 | 2022-12-23 | 0 | CRS-GUP-DHI-DT-22-1400 | 2023-01-06 | NC | DE-GUP-DT-E-22-1178 | 2022-12-23 | 0 | CRS-GUP-DHI-DT-22-1400 | 2023-01-06 | NC
| GUP | CV03 | P1 | ZEN | 160054 |  | GUP-CV03-P1ZEN-160054 | TECHNICAL SPECIFICATION_DCS | FA | 2022-02-17 | 2022-08-06 | 계측기술팀(I&C) | 고경환 |  |  |  |  | DCS | CCPP | DCS | I&C | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-179 | 2024-07-08 | 2 | CRS-GUP-DHI-DT-24-032 | 2024-03-11 | AA | DHI-GUP-DT-21-092 | 2021-11-05 | A | CRS-GUP-DHI-DT-21-071 | 2021-11-22 | RC | DE-GUP-DT-E-22-358 | 2022-07-04 | B | CRS-GUP-DHI-DT-22-555 | 2022-07-27 | RC | DE-GUP-DT-E-22-600 | 2022-09-01 | C | CRS-GUP-DHI-DT-22-844 | 2022-09-24 | RC | DE-GUP-DT-E-22-882 | 2022-10-31 | D | CRS-GUP-DHI-DT-22-1084 | 2022-11-19 | AC | DE-GUP-DT-E-23-078 | 2023-01-27 | 0(CP) | CRS-GUP-DHI-DT-23-1478 | 2023-02-10 | AC | DE-GUP-DT-E-24-009 | 2024-01-11 | 1(CP) | CRS-GUP-DHI-DT-24-032 | 2024-03-11 | AA | DE-GUP-DT-E-24-179 | 2024-07-08 | 2
| GUP | MA01 | P1 | ZEN | 160055 |  | GUP-MA01-P1ZEN-160055 | NETWORK CONFIGURATION DIAGRAM_DCS | FA | 2022-04-16 | 2022-09-11 | 계측기술팀(I&C) | 고경환 |  |  | G | FI | DCS | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-317 | 2023-03-15 | 0 | CRS-GUP-DHI-DT-23-1587 | 2023-02-28 | AA | DHI-GUP-DT-22-010 | 2022-01-07 | A | CRS-GUP-DHI-DT-21-175 | 2022-01-24 | RC | DE-GUP-DT-E-22-637 | 2022-09-08 | B | CRS-GUP-DHI-DT-22-855 | 2022-09-24 | RC | DE-GUP-DT-E-22-995 | 2022-11-28 | C | CRS-GUP-DHI-DT-22-1304 | 2022-12-21 | RC | DE-GUP-DT-E-23-063 | 2023-01-20 | D | CRS-GUP-DHI-DT-23-1587 | 2023-02-28 | AA | DE-GUP-DT-E-23-317 | 2023-03-15 | 0
| GUP | YV02 | P1 | ZEN | 160066 |  | GUP-YV02-P1ZEN-160066 | NETWORK AND POWER CABLE CONNECTION LIST_DCS | FI | 2022-09-15 |  | 계측기술팀(I&C) | 고경환 |  |  | G | FI | DCS | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-135 | 2024-05-21 | 2 | 자체 CRS 개정 후 제출 | 2024-05-20 | N/A | DE-GUP-DT-E-22-701 | 2022-09-23 | 0 | CRS-GUP-DHI-DT-22-916 | 2022-10-19 | NC | DE-GUP-DT-E-24-038 | 2024-02-08 | 1 | 자체 CRS 개정 후 제출 | 2024-05-20 | N/A | DE-GUP-DT-E-24-135 | 2024-05-21 | 2
| GUP | YE03 | P1 | ZEN | 160057 |  | GUP-YE03-P1ZEN-160057 | GROUNDING CONCEPT & DETAIL DRAWING_DCS | FI | 2022-08-15 |  | 계측기술팀(I&C) | 고경환 |  |  | G | FI | DCS | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-004 | 2024-01-04 | 1 | CRS-GUP-DHI-DT-22-451 | 2022-06-17 | NC | DE-GUP-DT-E-22-254 | 2022-05-27 | 0 | CRS-GUP-DHI-DT-22-451 | 2022-06-17 | NC | DE-GUP-DT-E-24-004 | 2024-01-04 | 1
| GUP | YD05 | P1 | ZEN | 160067 |  | GUP-YD05-P1ZEN-160067 | HMI GRAPHIC DISPLAY_DCS | FI | 2023-05-13 |  | 계측기술팀(I&C) | 고경환 |  |  |  |  | DCS | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-788 | 2023-09-06 | 1 | CRS-GUP-DHI-DT-23-2111 | 2023-09-14 | NC | DE-GUP-DT-E-23-624 | 2023-06-16 | 0 | CRS-GUP-DHI-DT-23-2039 | 2023-07-14 | RC | DE-GUP-DT-E-23-788 | 2023-09-06 | 1 | CRS-GUP-DHI-DT-23-2111 | 2023-09-14 | NC
| GUP | YV02 | P1 | ZEN | 160065 |  | GUP-YV02-P1ZEN-160065 | INTERNAL CABLE CONNECTION DIAGRAM_DCS | FI | 2022-09-15 |  | 계측기술팀(I&C) | 고경환 |  |  |  |  | DCS | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-088 | 2024-03-25 | 2 | CRS-GUP-DHI-DT-23-1721 | 2023-03-14 | NC | DE-GUP-DT-E-22-701 | 2022-09-23 | 0 | CRS-GUP-DHI-DT-22-916 | 2022-10-19 | NC | DE-GUP-DT-E-23-301 | 2023-03-10 | 1 | CRS-GUP-DHI-DT-23-1721 | 2023-03-14 | NC | DE-GUP-DT-E-24-088 | 2024-03-25 | 2
| GUP | YD07 | P1 | ZEN | 160056 |  | GUP-YD07-P1ZEN-160056 | I/O & MODULE ALLOCATION_DCS | FI | 2022-07-16 |  | 계측기술팀(I&C) | 고경환 |  |  |  |  | DCS | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-088 | 2024-03-25 | 1 | CRS-GUP-DHI-DT-22-613 | 2022-08-16 | NC | DE-GUP-DT-E-22-400 | 2022-07-15 | 0 | CRS-GUP-DHI-DT-22-613 | 2022-08-16 | NC | DE-GUP-DT-E-24-088 | 2024-03-25 | 1
| GUP | YR05 | P1 | ZEN | 160063 |  | GUP-YR05-P1ZEN-160063 | OUTLINE & DETAIL DRAWING_CONSOLE & DESK_DCS | FI | 2022-05-17 |  | 계측기술팀(I&C) | 고경환 |  |  | G | FI | DCS | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-031 | 2023-01-16 | 1 | CRS-GUP-DHI-DT-23-1472 | 2023-02-09 | NC | DHI-GUP-DT-22-025 | 2022-01-18 | 0 | CRS-GUP-DHI-DT-21-189 | 2022-02-04 | NC | DE-GUP-DT-E-23-031 | 2023-01-16 | 1 | CRS-GUP-DHI-DT-23-1472 | 2023-02-09 | NC
| GUP | YR05 | P1 | ZEN | 160060 |  | GUP-YR05-P1ZEN-160060 | OUTLINE & DETAIL DRAWING_NETWORK CABINET_DCS | FI | 2022-05-17 |  | 계측기술팀(I&C) | 고경환 |  |  | G | FI | DCS | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-031 | 2023-01-16 | 1 | CRS-GUP-DHI-DT-23-1472 | 2023-02-09 | NC | DHI-GUP-DT-22-025 | 2022-01-18 | 0 | CRS-GUP-DHI-DT-21-189 | 2022-02-04 | NC | DE-GUP-DT-E-23-031 | 2023-01-16 | 1 | CRS-GUP-DHI-DT-23-1472 | 2023-02-09 | NC
| GUP | YR05 | P1 | ZEN | 160058 |  | GUP-YR05-P1ZEN-160058 | OUTLINE & DETAIL DRAWING_CABINET TYPICAL_DCS | FI | 2022-05-17 |  | 계측기술팀(I&C) | 고경환 |  |  | G | FI | DCS | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-031 | 2023-01-16 | 1 | CRS-GUP-DHI-DT-23-1472 | 2023-02-09 | NC | DHI-GUP-DT-22-025 | 2022-01-18 | 0 | CRS-GUP-DHI-DT-21-189 | 2022-02-04 | NC | DE-GUP-DT-E-23-031 | 2023-01-16 | 1 | CRS-GUP-DHI-DT-23-1472 | 2023-02-09 | NC
| GUP | YR05 | P1 | ZEN | 160061 |  | GUP-YR05-P1ZEN-160061 | OUTLINE & DETAIL DRAWING_MARSHALLING CABINET_DCS | FI | 2022-05-17 |  | 계측기술팀(I&C) | 고경환 |  |  | G | FI | DCS | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-031 | 2023-01-16 | 1 | CRS-GUP-DHI-DT-23-1472 | 2023-02-09 | NC | DHI-GUP-DT-22-025 | 2022-01-18 | 0 | CRS-GUP-DHI-DT-21-189 | 2022-02-04 | NC | DE-GUP-DT-E-23-031 | 2023-01-16 | 1 | CRS-GUP-DHI-DT-23-1472 | 2023-02-09 | NC
| GUP | YR05 | P1 | ZEN | 160064 |  | GUP-YR05-P1ZEN-160064 | OUTLINE & DETAIL DRAWING_POWER DISTRIBUTION CABINET_DCS | FI | 2022-05-17 |  | 계측기술팀(I&C) | 고경환 |  |  | G | FI | DCS | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-031 | 2023-01-16 | 1 | CRS-GUP-DHI-DT-23-1472 | 2023-02-09 | NC | DHI-GUP-DT-22-025 | 2022-01-18 | 0 | CRS-GUP-DHI-DT-21-189 | 2022-02-04 | NC | DE-GUP-DT-E-23-031 | 2023-01-16 | 1 | CRS-GUP-DHI-DT-23-1472 | 2023-02-09 | NC
| GUP | YR05 | P1 | ZEN | 160062 |  | GUP-YR05-P1ZEN-160062 | OUTLINE & DETAIL DRAWING_INTERPOSING RELAY CABINET_DCS | FI | 2022-05-17 |  | 계측기술팀(I&C) | 고경환 |  |  | G | FI | DCS | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-031 | 2023-01-16 | 1 | CRS-GUP-DHI-DT-23-1472 | 2023-02-09 | NC | DHI-GUP-DT-22-025 | 2022-01-18 | 0 | CRS-GUP-DHI-DT-21-189 | 2022-02-04 | NC | DE-GUP-DT-E-23-031 | 2023-01-16 | 1 | CRS-GUP-DHI-DT-23-1472 | 2023-02-09 | NC
| GUP | YR05 | P1 | ZEN | 160059 |  | GUP-YR05-P1ZEN-160059 | OUTLINE & DETAIL DRAWING_SYSTEM CABINET_DCS | FI | 2022-05-17 |  | 계측기술팀(I&C) | 고경환 |  |  | G | FI | DCS | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-031 | 2023-01-16 | 1 | CRS-GUP-DHI-DT-23-1472 | 2023-02-09 | NC | DHI-GUP-DT-22-025 | 2022-01-18 | 0 | CRS-GUP-DHI-DT-21-189 | 2022-02-04 | NC | DE-GUP-DT-E-23-031 | 2023-01-16 | 1 | CRS-GUP-DHI-DT-23-1472 | 2023-02-09 | NC
| GUP | CV03 | P1 | ZEN | 160070 |  | GUP-CV03-P1ZEN-160070 | TECHNICAL SPECIFICATION_EMERGENCY PUSH BUTTON_DCS | FI | 2022-02-15 |  | 계측기술팀(I&C) | 고경환 |  |  |  |  | DCS | CCPP | DCS | I&C | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-004 | 2024-01-04 | 1 | CRS-GUP-DHI-DT-21-071 | 2021-11-22 | NC | DHI-GUP-DT-21-092 | 2021-11-05 | 0 | CRS-GUP-DHI-DT-21-071 | 2021-11-22 | NC | DE-GUP-DT-E-24-004 | 2024-01-04 | 1
| GUP | CV03 | P1 | ZEN | 160068 |  | GUP-CV03-P1ZEN-160068 | TECHNICAL SPECIFICATION_LARGE SCREEN DISPLAY_DCS | FA | 2022-02-15 | 2022-08-28 | 계측기술팀(I&C) | 고경환 |  |  |  |  | DCS | CCPP | DCS | I&C | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-997 | 2023-12-15 | 1 | CRS-GUP-DHI-DT-22-1131 | 2022-11-23 | AA | DHI-GUP-DT-21-092 | 2021-11-05 | A | CRS-GUP-DHI-DT-21-071 | 2021-11-22 | RC | DE-GUP-DT-E-22-254 | 2022-05-27 | B | CRS-GUP-DHI-DT-22-451 | 2022-06-17 | AC | DE-GUP-DT-E-22-586 | 2022-08-30 | C | CRS-GUP-DHI-DT-22-792 | 2022-09-19 | AA | DE-GUP-DT-E-22-769 | 2022-10-07 | 0 | CRS-GUP-DHI-DT-22-1131 | 2022-11-23 | AA | DE-GUP-DT-E-23-997 | 2023-12-15 | 1
| GUP | CV03 | P1 | ZEN | 160069 |  | GUP-CV03-P1ZEN-160069 | TECHNICAL SPECIFICATION_TIME SYNCHRONIZATION_DCS | FA | 2022-02-15 | 2022-08-28 | 계측기술팀(I&C) | 고경환 |  |  | G | FI | DCS | CCPP | DCS | I&C | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-24-015 | 2024-01-17 | 1 | CRS-GUP-DHI-DT-22-1243 | 2022-12-13 | AA | DHI-GUP-DT-21-092 | 2021-11-05 | A | CRS-GUP-DHI-DT-21-071 | 2021-11-22 | RC | DHI-GUP-DT-22-142 | 2022-03-31 | B | CRS-GUP-DHI-DT-22-353 | 2022-05-19 | RC | DE-GUP-DT-E-22-769 | 2022-10-07 | C | CRS-GUP-DHI-DT-22-974 | 2022-11-07 | AA | DE-GUP-DT-E-22-969 | 2022-11-22 | 0 | CRS-GUP-DHI-DT-22-1243 | 2022-12-13 | AA | DE-GUP-DT-E-24-015 | 2024-01-17 | 1
| GUP | YS00 | P1 | ZEN | 160014 |  | GUP-YS00-P1ZEN-160014 | TYPICAL ELEMENTARY WIRING DIAGRAM_6.9KV SWGR (MOTOR STARTER) | FI | 2021-09-17 |  | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | Plant | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-518 | 2022-08-19 | 2 | CRS-GUP-DHI-DT-22-716 | 2022-09-05 | NC | DHI-GUP-DT-21-032 | 2021-09-17 | 0 | CRS-GUP-DHI-DT-21-029 | 2021-10-06 | NC | DHI-GUP-DT-22-139 | 2022-03-29 | 1 | CRS-GUP-DHI-DT-22-338 | 2022-05-18 | NC | DE-GUP-DT-E-22-518 | 2022-08-19 | 2 | CRS-GUP-DHI-DT-22-716 | 2022-09-05 | NC
| GUP | YS00 | P1 | ZEN | 160015 |  | GUP-YS00-P1ZEN-160015 | TYPICAL ELEMENTARY WIRING DIAGRAM_480V SWGR (MOTOR STARTER) | FI | 2021-09-17 |  | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | Plant | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-518 | 2022-08-19 | 2 | CRS-GUP-DHI-DT-22-716 | 2022-09-05 | NC | DHI-GUP-DT-21-032 | 2021-09-17 | 0 | CRS-GUP-DHI-DT-21-029 | 2021-10-06 | NC | DHI-GUP-DT-22-139 | 2022-03-29 | 1 | CRS-GUP-DHI-DT-22-338 | 2022-05-18 | NC | DE-GUP-DT-E-22-518 | 2022-08-19 | 2 | CRS-GUP-DHI-DT-22-716 | 2022-09-05 | NC
| GUP | YS00 | P1 | ZEN | 160016 |  | GUP-YS00-P1ZEN-160016 | TYPICAL ELEMENTARY WIRING DIAGRAM_480V MCC (MOTOR STARTER) | FI | 2021-09-17 |  | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | Plant | I&C | 3 | 2025-06-30 |  |  | DHI-GUP-DT-22-139 | 2022-03-29 | 1 | CRS-GUP-DHI-DT-22-338 | 2022-05-18 | NC | DHI-GUP-DT-21-032 | 2021-09-17 | 0 | CRS-GUP-DHI-DT-21-029 | 2021-10-06 | NC | DHI-GUP-DT-22-139 | 2022-03-29 | 1 | CRS-GUP-DHI-DT-22-338 | 2022-05-18 | NC
| GUP | YS00 | P1 | ZEN | 160017 |  | GUP-YS00-P1ZEN-160017 | TYPICAL ELEMENTARY WIRING DIAGRAM_6.9KV SWGR | FI | 2021-09-17 |  | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | Plant | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-518 | 2022-08-19 | 2 | CRS-GUP-DHI-DT-22-716 | 2022-09-05 | NC | DHI-GUP-DT-21-032 | 2021-09-17 | 0 | CRS-GUP-DHI-DT-21-029 | 2021-10-06 | NC | DHI-GUP-DT-22-139 | 2022-03-29 | 1 | CRS-GUP-DHI-DT-22-338 | 2022-05-18 | NC | DE-GUP-DT-E-22-518 | 2022-08-19 | 2 | CRS-GUP-DHI-DT-22-716 | 2022-09-05 | NC
| GUP | YS00 | P1 | ZEN | 160018 |  | GUP-YS00-P1ZEN-160018 | TYPICAL ELEMENTARY WIRING DIAGRAM_480V SWGR | FI | 2021-09-17 |  | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | Plant | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-518 | 2022-08-19 | 2 | CRS-GUP-DHI-DT-22-716 | 2022-09-05 | NC | DHI-GUP-DT-21-032 | 2021-09-17 | 0 | CRS-GUP-DHI-DT-21-029 | 2021-10-06 | NC | DHI-GUP-DT-22-139 | 2022-03-29 | 1 | CRS-GUP-DHI-DT-22-338 | 2022-05-18 | NC | DE-GUP-DT-E-22-518 | 2022-08-19 | 2 | CRS-GUP-DHI-DT-22-716 | 2022-09-05 | NC
| GUP | YS00 | P1 | ZEN | 160019 |  | GUP-YS00-P1ZEN-160019 | TYPICAL ELEMENTARY WIRING DIAGRAM_480V MCC | FI | 2021-09-17 |  | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | Plant | I&C | 3 | 2025-06-30 |  |  | DHI-GUP-DT-22-139 | 2022-03-29 | 1 | CRS-GUP-DHI-DT-22-338 | 2022-05-18 | NC | DHI-GUP-DT-21-032 | 2021-09-17 | 0 | CRS-GUP-DHI-DT-21-029 | 2021-10-06 | NC | DHI-GUP-DT-22-139 | 2022-03-29 | 1 | CRS-GUP-DHI-DT-22-338 | 2022-05-18 | NC
| GUP | YS00 | P1 | ZEN | 160020 |  | GUP-YS00-P1ZEN-160020 | TYPICAL ELEMENTARY WIRING DIAGRAM_MOTOR OPERATED VALVE | FI | 2021-09-17 |  | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | Plant | I&C | 3 | 2025-06-30 |  |  | DHI-GUP-DT-22-139 | 2022-03-29 | 1 | CRS-GUP-DHI-DT-22-338 | 2022-05-18 | NC | DHI-GUP-DT-21-032 | 2021-09-17 | 0 | CRS-GUP-DHI-DT-21-029 | 2021-10-06 | NC | DHI-GUP-DT-22-139 | 2022-03-29 | 1 | CRS-GUP-DHI-DT-22-338 | 2022-05-18 | NC
| GUP | YS00 | P1 | ZEN | 160021 |  | GUP-YS00-P1ZEN-160021 | TYPICAL ELEMENTARY WIRING DIAGRAM_CONTROL VALVE | FI | 2021-09-17 |  | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | Plant | I&C | 3 | 2025-06-30 |  |  | DHI-GUP-DT-22-139 | 2022-03-29 | 1 | CRS-GUP-DHI-DT-22-338 | 2022-05-18 | NC | DHI-GUP-DT-21-032 | 2021-09-17 | 0 | CRS-GUP-DHI-DT-21-029 | 2021-10-06 | NC | DHI-GUP-DT-22-139 | 2022-03-29 | 1 | CRS-GUP-DHI-DT-22-338 | 2022-05-18 | NC
| GUP | YS00 | P1 | ZEN | 160022 |  | GUP-YS00-P1ZEN-160022 | TYPICAL ELEMENTARY WIRING DIAGRAM_SOLENOID VALVE | FI | 2021-09-17 |  | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | Plant | I&C | 3 | 2025-06-30 |  |  | DHI-GUP-DT-22-139 | 2022-03-29 | 1 | CRS-GUP-DHI-DT-22-338 | 2022-05-18 | NC | DHI-GUP-DT-21-032 | 2021-09-17 | 0 | CRS-GUP-DHI-DT-21-029 | 2021-10-06 | NC | DHI-GUP-DT-22-139 | 2022-03-29 | 1 | CRS-GUP-DHI-DT-22-338 | 2022-05-18 | NC
| GUP | YS00 | P1 | ZEN | 160023 |  | GUP-YS00-P1ZEN-160023 | TYPICAL ELEMENTARY WIRING DIAGRAM_ANALOG INPUT | FI | 2021-09-17 |  | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | Plant | I&C | 3 | 2025-06-30 |  |  | DHI-GUP-DT-22-139 | 2022-03-29 | 1 | CRS-GUP-DHI-DT-22-338 | 2022-05-18 | NC | DHI-GUP-DT-21-032 | 2021-09-17 | 0 | CRS-GUP-DHI-DT-21-029 | 2021-10-06 | NC | DHI-GUP-DT-22-139 | 2022-03-29 | 1 | CRS-GUP-DHI-DT-22-338 | 2022-05-18 | NC
| GUP | YS00 | P1 | ZEN | 160024 |  | GUP-YS00-P1ZEN-160024 | TYPICAL ELEMENTARY WIRING DIAGRAM_ANALOG OUTPUT | FI | 2021-09-17 |  | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | Plant | I&C | 3 | 2025-06-30 |  |  | DHI-GUP-DT-22-139 | 2022-03-29 | 1 | CRS-GUP-DHI-DT-22-338 | 2022-05-18 | NC | DHI-GUP-DT-21-032 | 2021-09-17 | 0 | CRS-GUP-DHI-DT-21-029 | 2021-10-06 | NC | DHI-GUP-DT-22-139 | 2022-03-29 | 1 | CRS-GUP-DHI-DT-22-338 | 2022-05-18 | NC
| GUP | YS00 | P1 | ZEN | 160025 |  | GUP-YS00-P1ZEN-160025 | TYPICAL ELEMENTARY WIRING DIAGRAM_DIGITAL INPUT | FI | 2021-09-17 |  | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | Plant | I&C | 3 | 2025-06-30 |  |  | DHI-GUP-DT-22-139 | 2022-03-29 | 1 | CRS-GUP-DHI-DT-22-338 | 2022-05-18 | NC | DHI-GUP-DT-21-032 | 2021-09-17 | 0 | CRS-GUP-DHI-DT-21-029 | 2021-10-06 | NC | DHI-GUP-DT-22-139 | 2022-03-29 | 1 | CRS-GUP-DHI-DT-22-338 | 2022-05-18 | NC
| GUP | YS00 | P1 | ZEN | 160026 |  | GUP-YS00-P1ZEN-160026 | TYPICAL ELEMENTARY WIRING DIAGRAM_DIGITAL OUTPUT | FI | 2021-09-17 |  | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | Plant | I&C | 3 | 2025-06-30 |  |  | DHI-GUP-DT-22-139 | 2022-03-29 | 1 | CRS-GUP-DHI-DT-22-338 | 2022-05-18 | NC | DHI-GUP-DT-21-032 | 2021-09-17 | 0 | CRS-GUP-DHI-DT-21-029 | 2021-10-06 | NC | DHI-GUP-DT-22-139 | 2022-03-29 | 1 | CRS-GUP-DHI-DT-22-338 | 2022-05-18 | NC
| GUP | YL02 | P1 | ZEN | 160009 |  | GUP-YL02-P1ZEN-160009 | I&C CABLE PRINCIPLE DIAGRAM | FA | 2021-07-09 | 2021-12-04 | 계측기술팀(I&C) | 우현아 | [5 empty] | CCPP | Plant | I&C | 3 | 2025-06-30 |  |  | DHI-GUP-DT-22-033 | 2022-01-25 | 0 | CRS-GUP-DHI-DT-21-093 | 2021-12-23 | AA | DHI-GUP-DT-21-006 | 2021-07-09 | A | CRS-GUP-DHI-DT-21-018 | 2021-09-29 | RC | DHI-GUP-DT-21-121 | 2021-11-26 | B | CRS-GUP-DHI-DT-21-093 | 2021-12-23 | AA | DHI-GUP-DT-22-033 | 2022-01-25 | 0
| GUP | YF00 | P1 | ZEN | 160012 |  | GUP-YF00-P1ZEN-160012 | PLANT UNIT MASTER CONTROL DIAGRAM | FA | 2022-11-13 | 2023-04-13 | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | Plant | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-512 | 2023-04-27 | 0 | CRS-GUP-DHI-DT-23-1930 | 2023-05-05 | AA | DE-GUP-DT-E-23-196 | 2023-02-17 | A | CRS-GUP-DHI-DT-23-1755 | 2023-03-22 | RC | DE-GUP-DT-E-23-414 | 2023-04-04 | B | CRS-GUP-DHI-DT-23-1838 | 2023-04-18 | AA | DE-GUP-DT-E-23-512 | 2023-04-27 | 0 | CRS-GUP-DHI-DT-23-1930 | 2023-05-05 | AA
| GUP | YL01 | P1 | ZEN | 160010 |  | GUP-YL01-P1ZEN-160010 | DCS IO LIST | FI | 2021-12-12 |  | 계측기술팀(I&C) | 우현아 | [5 empty] | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-087 | 2024-03-21 | 2 | CRS-GUP-DHI-DT-23-1716 | 2023-03-14 | NC | DHI-GUP-DT-21-014 | 2021-09-07 | 0 | CRS-GUP-DHI-DT-21-017 | 2021-09-29 | NC | DE-GUP-DT-E-23-269 | 2023-03-07 | 1 | CRS-GUP-DHI-DT-23-1716 | 2023-03-14 | NC | DE-GUP-DT-E-24-087 | 2024-03-21 | 2
| GUP | YL01 | P1 | ZEN | 160011 |  | GUP-YL01-P1ZEN-160011 | DCS IO LIST_3RD PARTY DATALINK | FI | 2023-01-08 |  | 계측기술팀(I&C) | 우현아 | [5 empty] | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-064 | 2024-02-29 | 2 | 자체 CRS 개정 후 제출 | 2024-02-28 | N/A | DE-GUP-DT-E-23-173 | 2023-02-14 | 0 | CRS-GUP-DHI-DT-23-1633 | 2023-03-03 | NC | DE-GUP-DT-E-23-910 | 2023-11-15 | 1 | 자체 CRS 개정 후 제출 | 2024-02-28 | N/A | DE-GUP-DT-E-24-064 | 2024-02-29 | 2
| GUP | XW01 | P0 | ZEN | 160001 |  | GUP-XW01-P0ZEN-160001 | I&C GENERAL DESIGN CRITERIA | FA | 2021-07-09 | 2021-12-04 | 계측기술팀(I&C) | 우현아 | [5 empty] | CCPP | Plant | I&C | 1 | 2025-06-30 |  |  | DHI-GUP-DT-22-174 | 2022-04-14 | 0 | CRS-GUP-DHI-DT-22-341 | 2022-05-18 | AA | DHI-GUP-DT-22-174 | 2022-04-14 | 0 | CRS-GUP-DHI-DT-22-341 | 2022-05-18 | AA
| GUP | MA01 | P1 | ZEN | 160002 |  | GUP-MA01-P1ZEN-160002 | PLANT CONTROL SYSTEM CONFIGURATION DIAGRAM | FA | 2021-07-15 | 2021-12-31 | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | Plant | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-391 | 2022-07-13 | 1 | CRS-GUP-DHI-DT-21-180 | 2022-02-07 | AA | DHI-GUP-DT-21-012 | 2021-07-15 | A | CRS-GUP-DHI-DT-21-021 | 2021-10-04 | AC | DHI-GUP-DT-22-019 | 2022-01-14 | 0 | CRS-GUP-DHI-DT-21-180 | 2022-02-07 | AA | DE-GUP-DT-E-22-391 | 2022-07-13 | 1
| GUP | YU04 | P1 | ZEN | 160003 |  | GUP-YU04-P1ZEN-160003 | PLANT CONTROL BLOCK DIAGRAM | FA | 2021-08-15 | 2022-12-15 | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | Plant | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1210 | 2023-01-03 | 0 | CRS-GUP-DHI-DT-23-1509 | 2023-02-14 | AA | DHI-GUP-DT-21-013 | 2021-09-07 | A | CRS-GUP-DHI-DT-21-002 | 2021-09-27 | RC | DHI-GUP-DT-21-104 | 2021-11-16 | B | CRS-GUP-DHI-DT-21-079 | 2021-12-08 | RC | DE-GUP-DT-E-22-334 | 2022-06-24 | C | CRS-GUP-DHI-DT-22-556 | 2022-08-01 | RC | DE-GUP-DT-E-22-1064 | 2022-12-09 | D | CRS-GUP-DHI-DT-22-1362 | 2022-12-30 | AA | DE-GUP-DT-E-22-1210 | 2023-01-03 | 0 | CRS-GUP-DHI-DT-23-1509 | 2023-02-14 | AA
| GUP | YF01 | P1 | ZEN | 160004 |  | GUP-YF01-P1ZEN-160004 | PLANT PROTECTION & INTERLOCK DIAGRAM | FA | 2022-10-19 | 2023-04-17 | 계측기술팀(I&C) | 고경환 |  |  | G | FA |  | CCPP | Plant | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-003 | 2023-01-12 | 0 | CRS-GUP-DHI-DT-22-983 | 2022-11-07 | AA | DE-GUP-DT-E-22-852 | 2022-10-25 | A | CRS-GUP-DHI-DT-22-983 | 2022-11-07 | AA | DE-GUP-DT-E-23-003 | 2023-01-12 | 0
| GUP | YF00 | P1 | ZEN | 160027 |  | GUP-YF00-P1ZEN-160027 | CONTROL LOGIC DIAGRAM_SYMBOL & LEGEND_BOP | FI | 2022-07-09 |  | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-241 | 2024-10-02 | 2 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-22-373 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-24-157 | 2024-06-17 | 1 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-24-241 | 2024-10-02 | 2
| GUP | YF00 | P1 | ZEN | 160028 |  | GUP-YF00-P1ZEN-160028 | CONTROL LOGIC DIAGRAM_TYPICAL FUNCTION_BOP | FI | 2022-07-09 |  | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-241 | 2024-10-02 | 2 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-22-373 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-24-157 | 2024-06-17 | 1 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-24-241 | 2024-10-02 | 2
| GUP | YF00 | P1 | ZEN | 160029 |  | GUP-YF00-P1ZEN-160029 | CONTROL LOGIC DIAGRAM_MAIN AND REHEAT STEAM SYSTEM_BOP | FI | 2022-07-09 |  | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-241 | 2024-10-02 | 2 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-22-373 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-24-157 | 2024-06-17 | 1 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-24-241 | 2024-10-02 | 2
| GUP | YF00 | P1 | ZEN | 160030 |  | GUP-YF00-P1ZEN-160030 | CONTROL LOGIC DIAGRAM_FEEDWATER SYSTEM_BOP | FI | 2022-07-09 |  | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-241 | 2024-10-02 | 2 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-22-373 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-24-157 | 2024-06-17 | 1 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-24-241 | 2024-10-02 | 2
| GUP | YF00 | P1 | ZEN | 160031 |  | GUP-YF00-P1ZEN-160031 | CONTROL LOGIC DIAGRAM_CONDENSATE SYSTEM_BOP | FI | 2022-07-09 |  | 계측기술팀(I&C) | 우현아 | [5 empty] | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-241 | 2024-10-02 | 2 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-22-373 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-24-157 | 2024-06-17 | 1 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-24-241 | 2024-10-02 | 2
| GUP | YF00 | P1 | ZEN | 160032 |  | GUP-YF00-P1ZEN-160032 | CONTROL LOGIC DIAGRAM_CIRCULATING WATER SYSTEM_BOP | FI | 2022-07-09 |  | 계측기술팀(I&C) | 우현아 | [5 empty] | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-241 | 2024-10-02 | 2 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-22-373 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-24-157 | 2024-06-17 | 1 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-24-241 | 2024-10-02 | 2
| GUP | YF00 | P1 | ZEN | 160034 |  | GUP-YF00-P1ZEN-160034 | CONTROL LOGIC DIAGRAM_CLOSED COOLING WATER SYSTEM_BOP | FI | 2022-07-09 |  | 계측기술팀(I&C) | 신동인 | [5 empty] | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-241 | 2024-10-02 | 2 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-22-373 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-24-157 | 2024-06-17 | 1 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-24-241 | 2024-10-02 | 2
| GUP | YF00 | P1 | ZEN | 160035 |  | GUP-YF00-P1ZEN-160035 | CONTROL LOGIC DIAGRAM_DEMI WATER SYSTEM_BOP | FI | 2022-07-09 |  | 계측기술팀(I&C) | 신동인 | [5 empty] | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-241 | 2024-10-02 | 2 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-22-373 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-24-157 | 2024-06-17 | 1 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-24-241 | 2024-10-02 | 2
| GUP | YF00 | P1 | ZEN | 160036 |  | GUP-YF00-P1ZEN-160036 | CONTROL LOGIC DIAGRAM_CHEMICAL DOSING SYSTEM_BOP | FI | 2022-07-09 |  | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-241 | 2024-10-02 | 2 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-22-373 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-24-157 | 2024-06-17 | 1 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-24-241 | 2024-10-02 | 2
| GUP | YF00 | P1 | ZEN | 160147 |  | GUP-YF00-P1ZEN-160147 | CONTROL LOGIC DIAGRAM_FUEL OIL/GAS SYSTEM_BOP | FI | 2022-07-09 |  | 계측기술팀(I&C) | 우현아 | [5 empty] | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-241 | 2024-10-02 | 2 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-22-373 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-24-157 | 2024-06-17 | 1 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-24-241 | 2024-10-02 | 2
| GUP | YF00 | P1 | ZEN | 160037 |  | GUP-YF00-P1ZEN-160037 | CONTROL LOGIC DIAGRAM_MISCELLANEOUS SYSTEM | FI | 2022-07-09 |  | 계측기술팀(I&C) | 우현아 | [5 empty] | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-241 | 2024-10-02 | 2 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-22-373 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-24-157 | 2024-06-17 | 1 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-24-241 | 2024-10-02 | 2
| GUP | YF00 | P1 | ZEN | 160038 |  | GUP-YF00-P1ZEN-160038 | CONTROL LOGIC DIAGRAM_INTERFACE WITH OTHER CONTROL SYSTEM | FI | 2022-07-09 |  | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-241 | 2024-10-02 | 2 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-22-373 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-24-157 | 2024-06-17 | 1 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-24-241 | 2024-10-02 | 2
| GUP | YF00 | P1 | ZEN | 160039 |  | GUP-YF00-P1ZEN-160039 | CONTROL LOGIC DIAGRAM_ELECTRICAL EQUIPMENT INTERFACE | FI | 2022-07-09 |  | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-241 | 2024-10-02 | 2 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-22-373 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-24-157 | 2024-06-17 | 1 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-24-241 | 2024-10-02 | 2
| GUP | YF00 | P1 | ZEN | 160040 |  | GUP-YF00-P1ZEN-160040 | FUNCTIONAL LOOP DIAGRAM_SYMBOL & LEGEND_BOP | FI | 2022-07-09 |  | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-241 | 2024-10-02 | 2 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-22-373 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-24-157 | 2024-06-17 | 1 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-24-241 | 2024-10-02 | 2
| GUP | YF00 | P1 | ZEN | 160041 |  | GUP-YF00-P1ZEN-160041 | FUNCTIONAL LOOP DIAGRAM_TYPICAL FUNCTION_BOP | FI | 2022-07-09 |  | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-241 | 2024-10-02 | 2 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-22-373 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-24-157 | 2024-06-17 | 1 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-24-241 | 2024-10-02 | 2
| GUP | YF00 | P1 | ZEN | 160042 |  | GUP-YF00-P1ZEN-160042 | FUNCTIONAL LOOP DIAGRAM_MAIN AND REHEAT STEAM SYSTEM_BOP | FI | 2022-07-09 |  | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-241 | 2024-10-02 | 2 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-22-373 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-24-157 | 2024-06-17 | 1 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-24-241 | 2024-10-02 | 2
| GUP | YF00 | P1 | ZEN | 160043 |  | GUP-YF00-P1ZEN-160043 | FUNCTIONAL LOOP DIAGRAM_FEEDWATER SYSTEM_BOP | FI | 2022-07-09 |  | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-241 | 2024-10-02 | 2 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-22-373 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-24-157 | 2024-06-17 | 1 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-24-241 | 2024-10-02 | 2
| GUP | YF00 | P1 | ZEN | 160044 |  | GUP-YF00-P1ZEN-160044 | FUNCTIONAL LOOP DIAGRAM_CONDENSATE SYSTEM_BOP | FI | 2022-07-09 |  | 계측기술팀(I&C) | 우현아 | [5 empty] | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-241 | 2024-10-02 | 2 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-22-373 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-24-157 | 2024-06-17 | 1 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-24-241 | 2024-10-02 | 2
| GUP | YF00 | P1 | ZEN | 160045 |  | GUP-YF00-P1ZEN-160045 | FUNCTIONAL LOOP DIAGRAM_CIRCULATING WATER SYSTEM_BOP | FI | 2022-07-09 |  | 계측기술팀(I&C) | 우현아 | [5 empty] | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-241 | 2024-10-02 | 2 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-22-373 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-24-157 | 2024-06-17 | 1 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-24-241 | 2024-10-02 | 2
| GUP | YF00 | P1 | ZEN | 160047 |  | GUP-YF00-P1ZEN-160047 | FUNCTIONAL LOOP DIAGRAM_CLOSED COOLING WATER SYSTEM_BOP | FI | 2022-07-09 |  | 계측기술팀(I&C) | 신동인 | [5 empty] | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-241 | 2024-10-02 | 2 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-22-373 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-24-157 | 2024-06-17 | 1 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-24-241 | 2024-10-02 | 2
| GUP | YF00 | P1 | ZEN | 160048 |  | GUP-YF00-P1ZEN-160048 | FUNCTIONAL LOOP DIAGRAM_DEMI WATER SYSTEM_BOP | FI | 2022-07-09 |  | 계측기술팀(I&C) | 신동인 | [5 empty] | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-241 | 2024-10-02 | 2 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-22-373 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-24-157 | 2024-06-17 | 1 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-24-241 | 2024-10-02 | 2
| GUP | YF00 | P1 | ZEN | 160049 |  | GUP-YF00-P1ZEN-160049 | FUNCTIONAL LOOP DIAGRAM_CHEMICAL DOSING SYSTEM_BOP | FI | 2022-07-09 |  | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-241 | 2024-10-02 | 2 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-22-373 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-24-157 | 2024-06-17 | 1 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-24-241 | 2024-10-02 | 2
| GUP | YF00 | P1 | ZEN | 160148 |  | GUP-YF00-P1ZEN-160148 | FUNCTIONAL LOOP DIAGRAM_FUEL OIL/GAS SYSTEM_BOP | FI | 2022-07-09 |  | 계측기술팀(I&C) | 우현아 | [5 empty] | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-241 | 2024-10-02 | 2 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-22-373 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-24-157 | 2024-06-17 | 1 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-24-241 | 2024-10-02 | 2
| GUP | YF00 | P1 | ZEN | 160050 |  | GUP-YF00-P1ZEN-160050 | FUNCTIONAL LOOP DIAGRAM_MISCELLANEOUS SYSTEM | FI | 2022-07-09 |  | 계측기술팀(I&C) | 우현아 | [5 empty] | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-241 | 2024-10-02 | 2 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-22-373 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-24-157 | 2024-06-17 | 1 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-24-241 | 2024-10-02 | 2
| GUP | YF00 | P1 | ZEN | 160051 |  | GUP-YF00-P1ZEN-160051 | FUNCTIONAL LOOP DIAGRAM_INTERFACE WITH OTHER CONTROL SYSTEM | FI | 2022-07-09 |  | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-241 | 2024-10-02 | 2 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-22-373 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-24-157 | 2024-06-17 | 1 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-24-241 | 2024-10-02 | 2
| GUP | YF00 | P1 | ZEN | 160052 |  | GUP-YF00-P1ZEN-160052 | FUNCTIONAL LOOP DIAGRAM_ELECTRICAL EQUIPMENT INTERFACE | FI | 2022-07-09 |  | 계측기술팀(I&C) | 고경환 | [5 empty] | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-241 | 2024-10-02 | 2 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-22-373 | 2022-07-08 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-24-157 | 2024-06-17 | 1 | 자체 CRS 개정 후 제출 | 2024-10-01 | N/A | DE-GUP-DT-E-24-241 | 2024-10-02 | 2
| GUP | YD00 | P1 | ZEN | 160005 |  | GUP-YD00-P1ZEN-160005 | I&C EQUIPMENT LAYOUT DRAWING_CENTRAL CONTROL ROOM | FA | 2021-10-15 | 2022-02-04 | 계측기술팀(I&C) | 우현아 | [5 empty] | CCPP | C&E Building | I&C | 2 | 2025-05-01 |  |  | DE-GUP-DT-E-24-222 | 2024-09-03 | 4 | N/A(자체 CRS 개정 후 제출) | 2024-09-02 | N/A | DHI-GUP-DT-21-063 | 2021-10-14 | A | CRS-GUP-DHI-DT-21-048 | 2021-11-01 | RC | DHI-GUP-DT-21-102 | 2021-11-16 | B | CRS-GUP-DHI-DT-21-077 | 2021-12-08 | RC | DHI-GUP-DT-21-169 | 2021-12-13 | C | CRS-GUP-DHI-DT-21-124 | 2022-01-07 | AC | DE-GUP-DT-E-22-248 | 2022-05-26 | D | CRS-GUP-DHI-DT-22-450 | 2022-06-17 | AA | DE-GUP-DT-E-22-325 | 2022-06-22 | 0 | N/A | N/A | N/A | DE-GUP-DT-E-22-851 | 2022-10-25 | 1 | CRS-GUP-DHI-DT-22-1143 | 2022-11-23 | AA | DE-GUP-DT-E-23-119 | 2023-02-03 | 2 | N/A(자체 CRS 개정 후 제출) | 2023-05-29 | N/A | DE-GUP-DT-E-23-589 | 2023-05-30 | 3 | N/A(자체 CRS 개정 후 제출) | 2024-09-02 | N/A | DE-GUP-DT-E-24-222 | 2024-09-03 | 4
| GUP | YD00 | P1 | ZEN | 160006 |  | GUP-YD00-P1ZEN-160006 | I&C EQUIPMENT LAYOUT DRAWING_MAIN ELECTRONIC ROOM | FA | 2021-10-15 | 2022-02-04 | 계측기술팀(I&C) | 우현아 | [5 empty] | CCPP | C&E Building | I&C | 2 | 2025-05-01 |  |  | DE-GUP-DT-E-23-589 | 2023-05-30 | 3 | N/A(자체 CRS 개정 후 제출) | 2023-05-29 | N/A | DHI-GUP-DT-21-063 | 2021-10-14 | A | CRS-GUP-DHI-DT-21-048 | 2021-11-01 | RC | DHI-GUP-DT-21-102 | 2021-11-16 | B | CRS-GUP-DHI-DT-21-077 | 2021-12-08 | RC | DHI-GUP-DT-21-169 | 2021-12-13 | C | CRS-GUP-DHI-DT-21-124 | 2022-01-07 | AA | DE-GUP-DT-E-22-248 | 2022-05-26 | 0 | CRS-GUP-DHI-DT-22-450 | 2022-06-17 | AA | DE-GUP-DT-E-22-851 | 2022-10-25 | 1 | CRS-GUP-DHI-DT-22-1143 | 2022-11-23 | AA | DE-GUP-DT-E-23-119 | 2023-02-03 | 2 | N/A(자체 CRS 개정 후 제출) | 2023-05-29 | N/A | DE-GUP-DT-E-23-589 | 2023-05-30 | 3
| GUP | YD00 | P1 | ZEN | 160007 |  | GUP-YD00-P1ZEN-160007 | I&C EQUIPMENT LAYOUT DRAWING_ENGINEERING ROOM | FA | 2021-10-15 | 2022-02-04 | 계측기술팀(I&C) | 우현아 | [5 empty] | CCPP | C&E Building | I&C | 2 | 2025-05-01 |  |  | DE-GUP-DT-E-23-589 | 2023-05-30 | 3 | N/A(자체 CRS 개정 후 제출) | 2023-05-29 | N/A | DHI-GUP-DT-21-063 | 2021-10-14 | A | CRS-GUP-DHI-DT-21-048 | 2021-11-01 | RC | DHI-GUP-DT-21-102 | 2021-11-16 | B | CRS-GUP-DHI-DT-21-077 | 2021-12-08 | RC | DHI-GUP-DT-21-169 | 2021-12-13 | C | CRS-GUP-DHI-DT-21-124 | 2022-01-07 | AA | DE-GUP-DT-E-22-248 | 2022-05-26 | 0 | CRS-GUP-DHI-DT-22-450 | 2022-06-17 | AA | DE-GUP-DT-E-22-851 | 2022-10-25 | 1 | CRS-GUP-DHI-DT-22-1143 | 2022-11-23 | AA | DE-GUP-DT-E-23-119 | 2023-02-03 | 2 | N/A(자체 CRS 개정 후 제출) | 2023-05-29 | N/A | DE-GUP-DT-E-23-589 | 2023-05-30 | 3
| GUP | YF00 | P1 | ZEN | 160013 |  | GUP-YF00-P1ZEN-160013 | PLANT START-UP & SHUTDOWN SEQUENCE DIAGRAM | FA | 2022-12-16 | 2023-03-13 | 계측기술팀(I&C) | 고경환 |  |  | G | FA |  | CCPP | Plant | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-482 | 2023-04-21 | 0 | CRS-GUP-DHI-DT-23-1908 | 2023-05-05 | AA | DE-GUP-DT-E-23-172 | 2023-02-14 | A | CRS-GUP-DHI-DT-23-1729 | 2023-03-17 | RC | DE-GUP-DT-E-23-388 | 2023-03-29 | B | CRS-GUP-DHI-DT-23-1836 | 2023-04-18 | AA | DE-GUP-DT-E-23-482 | 2023-04-21 | 0 | CRS-GUP-DHI-DT-23-1908 | 2023-05-05 | AA
| GUP | YK00 | P1 | ZEN | 160114 |  | GUP-YK00-P1ZEN-160114 | INSTRUMENT INSTALLATION DETAIL DRAWING_GENERAL NOTES_BOP | FI | 2022-06-26 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Instrument Installation Materials | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-248 | 2024-10-14 | 4 | 자체 CRS 개정 후 제출 | 2024-10-13 | N/A | DE-GUP-DT-E-22-351 | 2022-07-01 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-23-152 | 2023-02-10 | 1 | CRS-GUP-DHI-DT-23-1582 | 2023-02-25 | NC | DE-GUP-DT-E-24-109 | 2024-04-22 | 2 | 자체 CRS 개정 후 제출 | 2024-08-20 | N/A | DE-GUP-DT-E-24-205 | 32024-08-21 | 3 | 자체 CRS 개정 후 제출 | 2024-10-13 | N/A | DE-GUP-DT-E-24-248 | 2024-10-14 | 4
| GUP | YK00 | P1 | ZEN | 160115 |  | GUP-YK00-P1ZEN-160115 | INSTRUMENT INSTALLATION DETAIL DRAWING_SYMBOL & LEGEND_BOP | FI | 2022-06-26 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Instrument Installation Materials | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-152 | 2023-02-10 | 1 | CRS-GUP-DHI-DT-23-1582 | 2023-02-25 | NC | DE-GUP-DT-E-22-351 | 2022-07-01 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-23-152 | 2023-02-10 | 1 | CRS-GUP-DHI-DT-23-1582 | 2023-02-25 | NC
| GUP | YK00 | P1 | ZEN | 160116 |  | GUP-YK00-P1ZEN-160116 | INSTRUMENT INSTALLATION DETAIL DRAWING_MATERIAL LIST_BOP | FI | 2022-06-26 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Instrument Installation Materials | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-152 | 2023-02-10 | 1 | CRS-GUP-DHI-DT-23-1582 | 2023-02-25 | NC | DE-GUP-DT-E-22-351 | 2022-07-01 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-23-152 | 2023-02-10 | 1 | CRS-GUP-DHI-DT-23-1582 | 2023-02-25 | NC
| GUP | YK00 | P1 | ZEN | 160117 |  | GUP-YK00-P1ZEN-160117 | INSTRUMENT INSTALLATION DETAIL DRAWING_PRESSURE TRANSMITTER_BOP | FI | 2022-06-26 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Instrument Installation Materials | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-205 | 2024-08-21 | 2 | CRS-GUP-DHI-DT-23-1582 | 2023-02-25 | NC | DE-GUP-DT-E-22-351 | 2022-07-01 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-23-152 | 2023-02-10 | 1 | CRS-GUP-DHI-DT-23-1582 | 2023-02-25 | NC | DE-GUP-DT-E-24-205 | 2024-08-21 | 2
| GUP | YK00 | P1 | ZEN | 160118 |  | GUP-YK00-P1ZEN-160118 | INSTRUMENT INSTALLATION DETAIL DRAWING_DIFF. PRESSURE TRANSMITTER_BOP | FI | 2022-06-26 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Instrument Installation Materials | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-152 | 2023-02-10 | 1 | CRS-GUP-DHI-DT-23-1582 | 2023-02-25 | NC | DE-GUP-DT-E-22-351 | 2022-07-01 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-23-152 | 2023-02-10 | 1 | CRS-GUP-DHI-DT-23-1582 | 2023-02-25 | NC
| GUP | YK00 | P1 | ZEN | 160119 |  | GUP-YK00-P1ZEN-160119 | INSTRUMENT INSTALLATION DETAIL DRAWING_FLOW TRANSMITTER_BOP | FI | 2022-06-26 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Instrument Installation Materials | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-152 | 2023-02-10 | 1 | CRS-GUP-DHI-DT-23-1582 | 2023-02-25 | NC | DE-GUP-DT-E-22-351 | 2022-07-01 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-23-152 | 2023-02-10 | 1 | CRS-GUP-DHI-DT-23-1582 | 2023-02-25 | NC
| GUP | YK00 | P1 | ZEN | 160120 |  | GUP-YK00-P1ZEN-160120 | INSTRUMENT INSTALLATION DETAIL DRAWING_LEVEL INSTRUMENT_BOP | FI | 2022-06-26 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Instrument Installation Materials | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-248 | 2024-10-14 | 3 | 자체 CRS 개정 후 제출 | 2024-10-13 | N/A | DE-GUP-DT-E-22-351 | 2022-07-01 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-23-152 | 2023-02-10 | 1 | CRS-GUP-DHI-DT-23-1582 | 2023-02-25 | NC | DE-GUP-DT-E-24-109 | 2024-04-22 | 2 | 자체 CRS 개정 후 제출 | 2024-10-13 | N/A | DE-GUP-DT-E-24-248 | 2024-10-14 | 3
| GUP | YK00 | P1 | ZEN | 160121 |  | GUP-YK00-P1ZEN-160121 | INSTRUMENT INSTALLATION DETAIL DRAWING_PRESSURE GAUGE_BOP | FI | 2022-06-26 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Instrument Installation Materials | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-109 | 2024-04-22 | 2 | CRS-GUP-DHI-DT-23-1582 | 2023-02-25 | NC | DE-GUP-DT-E-22-351 | 2022-07-01 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-23-152 | 2023-02-10 | 1 | CRS-GUP-DHI-DT-23-1582 | 2023-02-25 | NC | DE-GUP-DT-E-24-109 | 2024-04-22 | 2
| GUP | YK00 | P1 | ZEN | 160122 |  | GUP-YK00-P1ZEN-160122 | INSTRUMENT INSTALLATION DETAIL DRAWING_CONTROL VALVE_BOP | FI | 2022-06-26 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Instrument Installation Materials | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-248 | 2024-10-14 | 2 | CRS-GUP-DHI-DT-23-1582 | 2023-02-25 | NC | DE-GUP-DT-E-22-351 | 2022-07-01 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-23-152 | 2023-02-10 | 1 | CRS-GUP-DHI-DT-23-1582 | 2023-02-25 | NC | DE-GUP-DT-E-24-248 | 2024-10-14 | 2
| GUP | YK00 | P1 | ZEN | 160123 |  | GUP-YK00-P1ZEN-160123 | INSTRUMENT INSTALLATION DETAIL DRAWING_TEMPERATURE INSTRUMENT_BOP | FI | 2022-06-26 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Instrument Installation Materials | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-248 | 2024-10-14 | 4 | 자체 CRS 개정 후 제출 | 2024-10-13 | N/A | DE-GUP-DT-E-22-351 | 2022-07-01 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-23-152 | 2023-02-10 | 1 | CRS-GUP-DHI-DT-23-1582 | 2023-02-25 | NC | DE-GUP-DT-E-24-109 | 2024-04-22 | 2 | 자체 CRS 개정 후 제출 | 2024-08-20 | N/A | DE-GUP-DT-E-24-205 | 32024-08-21 | 3 | 자체 CRS 개정 후 제출 | 2024-10-13 | N/A | DE-GUP-DT-E-24-248 | 2024-10-14 | 4
| GUP | YK00 | P1 | ZEN | 160124 |  | GUP-YK00-P1ZEN-160124 | INSTRUMENT INSTALLATION DETAIL DRAWING_STANCHION_BOP | FI | 2022-06-26 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Instrument Installation Materials | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-152 | 2023-02-10 | 1 | CRS-GUP-DHI-DT-23-1582 | 2023-02-25 | NC | DE-GUP-DT-E-22-351 | 2022-07-01 | 0 | CRS-GUP-DHI-DT-22-548 | 2022-07-27 | NC | DE-GUP-DT-E-23-152 | 2023-02-10 | 1 | CRS-GUP-DHI-DT-23-1582 | 2023-02-25 | NC
| GUP | YS02 | P1 | ZEN | 160094 |  | GUP-YS02-P1ZEN-160094 | I&C CABLE INTERCONNECTION WIRING DIAGRAM_MAIN AND REHEAT STEAM SYSTEM | FI | 2023-02-11 |  | 계측기술팀(I&C) | 김려도 | [5 empty] | CCPP | Cable | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-302 | 2024-12-27 | 4 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-23-227 | 2023-02-22 | 0 | CRS-GUP-DHI-DT-23-1701 | 2023-03-14 | NC | DE-GUP-DT-E-23-972 | 2023-12-05 | 1 | 자체 CRS 개정 후 제출 | 2024-04-25 | N/A | DE-GUP-DT-E-24-112 | 2024-04-26 | 2 | 자체 CRS 개정 후 제출 | 2024-09-12 | N/A | DE-GUP-DT-E-24-235 | 2024-09-13 | 3 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-24-302 | 2024-12-27 | 4
| GUP | YS02 | P1 | ZEN | 160095 |  | GUP-YS02-P1ZEN-160095 | I&C CABLE INTERCONNECTION WIRING DIAGRAM_FEEDWATER SYSTEM | FI | 2023-02-11 |  | 계측기술팀(I&C) | 김려도 | [5 empty] | CCPP | Cable | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-235 | 2024-09-13 | 3 | 자체 CRS 개정 후 제출 | 2024-09-12 | N/A | DE-GUP-DT-E-23-227 | 2023-02-22 | 0 | CRS-GUP-DHI-DT-23-1701 | 2023-03-14 | NC | DE-GUP-DT-E-23-972 | 2023-12-05 | 1 | 자체 CRS 개정 후 제출 | 2024-04-25 | N/A | DE-GUP-DT-E-24-112 | 2024-04-26 | 2 | 자체 CRS 개정 후 제출 | 2024-09-12 | N/A | DE-GUP-DT-E-24-235 | 2024-09-13 | 3
| GUP | YS02 | P1 | ZEN | 160100 |  | GUP-YS02-P1ZEN-160100 | I&C CABLE INTERCONNECTION WIRING DIAGRAM_DEMI WATER SYSTEM | FI | 2023-02-11 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Cable | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-112 | 2024-04-26 | 2 | 자체 CRS 개정 후 제출 | 2024-04-25 | N/A | DE-GUP-DT-E-23-227 | 2023-02-22 | 0 | CRS-GUP-DHI-DT-23-1701 | 2023-03-14 | NC | DE-GUP-DT-E-23-972 | 2023-12-05 | 1 | 자체 CRS 개정 후 제출 | 2024-04-25 | N/A | DE-GUP-DT-E-24-112 | 2024-04-26 | 2
| GUP | YS02 | P1 | ZEN | 160096 |  | GUP-YS02-P1ZEN-160096 | I&C CABLE INTERCONNECTION WIRING DIAGRAM_CONDENSATE SYSTEM | FI | 2023-02-11 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Cable | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-302 | 2024-12-27 | 4 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-23-227 | 2023-02-22 | 0 | CRS-GUP-DHI-DT-23-1701 | 2023-03-14 | NC | DE-GUP-DT-E-23-972 | 2023-12-05 | 1 | 자체 CRS 개정 후 제출 | 2024-04-25 | N/A | DE-GUP-DT-E-24-112 | 2024-04-26 | 2 | 자체 CRS 개정 후 제출 | 2024-09-12 | N/A | DE-GUP-DT-E-24-235 | 2024-09-13 | 3 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-24-302 | 2024-12-27 | 4
| GUP | YS02 | P1 | ZEN | 160099 |  | GUP-YS02-P1ZEN-160099 | I&C CABLE INTERCONNECTION WIRING DIAGRAM_CLOSED COOLING WATER SYSTEM | FI | 2023-02-11 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Cable | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-302 | 2024-12-27 | 3 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-23-227 | 2023-02-22 | 0 | CRS-GUP-DHI-DT-23-1701 | 2023-03-14 | NC | DE-GUP-DT-E-23-972 | 2023-12-05 | 1 | 자체 CRS 개정 후 제출 | 2024-04-25 | N/A | DE-GUP-DT-E-24-112 | 2024-04-26 | 2 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-24-302 | 2024-12-27 | 3
| GUP | YS02 | P1 | ZEN | 160097 |  | GUP-YS02-P1ZEN-160097 | I&C CABLE INTERCONNECTION WIRING DIAGRAM_CIRCULATING WATER SYSTEM | FI | 2023-02-11 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Cable | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-302 | 2024-12-27 | 4 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-23-227 | 2023-02-22 | 0 | CRS-GUP-DHI-DT-23-1701 | 2023-03-14 | NC | DE-GUP-DT-E-23-972 | 2023-12-05 | 1 | 자체 CRS 개정 후 제출 | 2024-04-25 | N/A | DE-GUP-DT-E-24-112 | 2024-04-26 | 2 | 자체 CRS 개정 후 제출 | 2024-09-12 | N/A | DE-GUP-DT-E-24-235 | 2024-09-13 | 3 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-24-302 | 2024-12-27 | 4
| GUP | YL16 | P1 | ZEN | 160084 |  | GUP-YL16-P1ZEN-160084 | I&C CABLE SCHEDULE_MAIN AND REHEAT STEAM SYSTEM_BOP | FI | 2022-10-26 |  | 계측기술팀(I&C) | 김려도 | [5 empty] | CCPP | Cable | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-303 | 2024-12-27 | 4 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-22-868 | 2022-10-27 | 0 | CRS-GUP-DHI-DT-22-1053 | 2022-11-17 | RC | DE-GUP-DT-E-23-247 | 2023-02-27 | 1 | CRS-GUP-DHI-DT-23-1741 | 2023-03-17 | NC | DE-GUP-DT-E-23-584 | 2023-05-25 | 2 | CRS-GUP-DHI-DT-23-1993 | 2023-06-13 | NC | DE-GUP-DT-E-23-972 | 2023-12-05 | 3 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-24-303 | 2024-12-27 | 4
| GUP | YL16 | P1 | ZEN | 160085 |  | GUP-YL16-P1ZEN-160085 | I&C CABLE SCHEDULE_FEEDWATER SYSTEM_BOP | FI | 2022-10-26 |  | 계측기술팀(I&C) | 김려도 | [5 empty] | CCPP | Cable | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-303 | 2024-12-27 | 4 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-22-868 | 2022-10-27 | 0 | CRS-GUP-DHI-DT-22-1053 | 2022-11-17 | RC | DE-GUP-DT-E-23-247 | 2023-02-27 | 1 | CRS-GUP-DHI-DT-23-1741 | 2023-03-17 | NC | DE-GUP-DT-E-23-584 | 2023-05-25 | 2 | CRS-GUP-DHI-DT-23-1993 | 2023-06-13 | NC | DE-GUP-DT-E-23-972 | 2023-12-05 | 3 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-24-303 | 2024-12-27 | 4
| GUP | YL16 | P1 | ZEN | 160090 |  | GUP-YL16-P1ZEN-160090 | I&C CABLE SCHEDULE_DEMI WATER SYSTEM_BOP | FI | 2022-10-26 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Cable | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-303 | 2024-12-27 | 4 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-22-868 | 2022-10-27 | 0 | CRS-GUP-DHI-DT-22-1053 | 2022-11-17 | RC | DE-GUP-DT-E-23-247 | 2023-02-27 | 1 | CRS-GUP-DHI-DT-23-1741 | 2023-03-17 | NC | DE-GUP-DT-E-23-584 | 2023-05-25 | 2 | CRS-GUP-DHI-DT-23-1993 | 2023-06-13 | NC | DE-GUP-DT-E-23-972 | 2023-12-05 | 3 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-24-303 | 2024-12-27 | 4
| GUP | YL16 | P1 | ZEN | 160086 |  | GUP-YL16-P1ZEN-160086 | I&C CABLE SCHEDULE_CONDENSATE SYSTEM_BOP | FI | 2022-10-26 |  | 계측기술팀(I&C) | 김려도 | [5 empty] | CCPP | Cable | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-083 | 2024-03-19 | 4 | 자체 CRS 개정 후 제출 | 2024-03-18 | N/A | DE-GUP-DT-E-22-868 | 2022-10-27 | 0 | CRS-GUP-DHI-DT-22-1053 | 2022-11-17 | RC | DE-GUP-DT-E-23-247 | 2023-02-27 | 1 | CRS-GUP-DHI-DT-23-1741 | 2023-03-17 | NC | DE-GUP-DT-E-23-584 | 2023-05-25 | 2 | CRS-GUP-DHI-DT-23-1993 | 2023-06-13 | NC | DE-GUP-DT-E-23-972 | 2023-12-05 | 3 | 자체 CRS 개정 후 제출 | 2024-03-18 | N/A | DE-GUP-DT-E-24-083 | 2024-03-19 | 4
| GUP | YL16 | P1 | ZEN | 160089 |  | GUP-YL16-P1ZEN-160089 | I&C CABLE SCHEDULE_CLOSED COOLING WATER SYSTEM_BOP | FI | 2022-10-26 |  | 계측기술팀(I&C) | 김려도 | [5 empty] | CCPP | Cable | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-303 | 2024-12-27 | 5 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-22-868 | 2022-10-27 | 0 | CRS-GUP-DHI-DT-22-1053 | 2022-11-17 | RC | DE-GUP-DT-E-23-247 | 2023-02-27 | 1 | CRS-GUP-DHI-DT-23-1741 | 2023-03-17 | NC | DE-GUP-DT-E-23-584 | 2023-05-25 | 2 | CRS-GUP-DHI-DT-23-1993 | 2023-06-13 | NC | DE-GUP-DT-E-23-972 | 2023-12-05 | 3 | 자체 CRS 개정 후 제출 | 2024-03-18 | N/A | DE-GUP-DT-E-24-083 | 2024-03-19 | 4 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-24-303 | 2024-12-27 | 5
| GUP | YL16 | P1 | ZEN | 160087 |  | GUP-YL16-P1ZEN-160087 | I&C CABLE SCHEDULE_CIRCULATING WATER SYSTEM_BOP | FI | 2022-10-26 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Cable | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-303 | 2024-12-27 | 5 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-22-868 | 2022-10-27 | 0 | CRS-GUP-DHI-DT-22-1053 | 2022-11-17 | RC | DE-GUP-DT-E-23-247 | 2023-02-27 | 1 | CRS-GUP-DHI-DT-23-1741 | 2023-03-17 | NC | DE-GUP-DT-E-23-584 | 2023-05-25 | 2 | CRS-GUP-DHI-DT-23-1993 | 2023-06-13 | NC | DE-GUP-DT-E-23-972 | 2023-12-05 | 3 | 자체 CRS 개정 후 제출 | 2024-03-18 | N/A | DE-GUP-DT-E-24-083 | 2024-03-19 | 4 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-24-303 | 2024-12-27 | 5
| GUP | YL16 | P1 | ZEN | 160152 |  | GUP-YL16-P1ZEN-160152 | I&C CABLE SCHEDULE_ELECTRICAL EQUIPMENT INTERFACE_BOP | FI | 2022-10-26 |  | 계측기술팀(I&C) | 김려도 | [5 empty] | CCPP | Cable | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-303 | 2024-12-27 | 4 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-23-247 | 2023-02-27 | 0 | CRS-GUP-DHI-DT-23-1741 | 2023-03-17 | NC | DE-GUP-DT-E-23-584 | 2023-05-25 | 1 | CRS-GUP-DHI-DT-23-1993 | 2023-06-13 | NC | DE-GUP-DT-E-23-972 | 2023-12-05 | 2 | 자체 CRS 개정 후 제출 | 2024-03-17 | N/A | DE-GUP-DT-E-24-083 | 2024-03-18 | 3 | 자체 CRS 개정 후 제출 | 2024-12-26 | N/A | DE-GUP-DT-E-24-303 | 2024-12-27 | 4
| GUP | YE03 | P1 | ZEN | 160139 |  | GUP-YE03-P1ZEN-160139 | I&C GROUNDING CONCEPT DIAGRAM | FI | 2021-11-15 |  | 계측기술팀(I&C) | 고경환 |  |  | G | FI |  | CCPP | Plant | I&C | 3 | 2025-06-30 |  |  | DHI-GUP-DT-21-128 | 2021-11-30 | 0 | CRS-GUP-DHI-DT-21-145 | 2022-01-12 | NC | DHI-GUP-DT-21-128 | 2021-11-30 | 0 | CRS-GUP-DHI-DT-21-145 | 2022-01-12 | NC
| GUP | YS02 | P1 | ZEN | 160141 |  | GUP-YS02-P1ZEN-160141 | I&C CABLE INTERCONNECTION WIRING DIAGRAM_HVAC | FI | 2022-12-27 |  | 계측기술팀(I&C) | 우현아 |  |  |  |  | HVAC | CCPP | HVAC | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-009 | 2025-01-17 | 5 | 자체 CRS 개정 후 제출 | 2025-01-16 | N/A | DE-GUP-DT-E-23-028 | 2023-01-16 | 0 | CRS-GUP-DHI-DT-23-1467 | 2023-02-09 | NC | DE-GUP-DT-E-23-195 | 2023-02-17 | 1 | CRS-GUP-DHI-DT-23-1658 | 2023-03-07 | NC | DE-GUP-DT-E-23-485 | 2023-04-21 | 2 | CRS-GUP-DHI-DT-23-1910 | 2023-05-05 | NC | DE-GUP-DT-E-23-882 | 2023-11-07 | 3 | 자체 CRS 개정 후 제출 | 2024-08-12 | N/A | DE-GUP-DT-E-24-202 | 2024-08-13 | 4 | 자체 CRS 개정 후 제출 | 2025-01-16 | N/A | DE-GUP-DT-E-25-009 | 2025-01-17 | 5
| GUP | YL16 | P1 | ZEN | 160142 |  | GUP-YL16-P1ZEN-160142 | I&C CABLE SCHEDULE_HVAC | FI | 2022-12-27 |  | 계측기술팀(I&C) | 우현아 |  |  |  |  | HVAC | CCPP | HVAC | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-009 | 2025-01-17 | 3 | 자체 CRS 개정 후 제출 | 2025-01-16 | N/A | DE-GUP-DT-E-23-236 | 2023-02-23 | 0 | CRS-GUP-DHI-DT-23-1705 | 2023-03-14 | NC | DE-GUP-DT-E-23-882 | 2023-11-07 | 1 | 자체 CRS 개정 후 제출 | 2024-08-12 | N/A | DE-GUP-DT-E-24-202 | 2024-08-13 | 2 | 자체 CRS 개정 후 제출 | 2025-01-16 | N/A | DE-GUP-DT-E-25-009 | 2025-01-17 | 3
| GUP | MA01 | P1 | ZEN | 160143 |  | GUP-MA01-P1ZEN-160143 | CONTROL SYSTEM CONFIGURATION DIAGRAM_HVAC | FI | 2022-03-14 |  | 계측기술팀(I&C) | 우현아 |  |  |  |  | HVAC | CCPP | HVAC | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-902 | 2022-11-03 | 1 | CRS-GUP-DHI-DT-22-1028 | 2022-11-13 | NC | DHI-GUP-DT-21-138 | 2021-11-30 | 0 | CRS-GUP-DHI-DT-21-145 | 2022-01-12 | NC | DE-GUP-DT-E-22-902 | 2022-11-03 | 1 | CRS-GUP-DHI-DT-22-1028 | 2022-11-13 | NC
| GUP | YR05 | P1 | ZEN | 160144 |  | GUP-YR05-P1ZEN-160144 | OUTLINE & DETAIL DRAWING_HVAC CABINET | FI | 2022-09-26 |  | 계측기술팀(I&C) | 우현아 |  |  |  |  | HVAC | CCPP | HVAC | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-009 | 2025-01-17 | 5 | 자체 CRS 개정 후 제출 | 2025-01-16 | N/A | DE-GUP-DT-E-22-803 | 2022-10-14 | 0 | CRS-GUP-DHI-DT-22-979 | 2022-11-07 | NC | DE-GUP-DT-E-22-1163 | 2022-12-22 | 1 | CRS-GUP-DHI-DT-22-1378 | 2022-12-31 | NC | DE-GUP-DT-E-23-123 | 2023-02-06 | 2 | CRS-GUP-DHI-DT-23-1539 | 2023-02-15 | NC | DE-GUP-DT-E-23-489 | 2023-04-21 | 3 | CRS-GUP-DHI-DT-23-1914 | 2023-05-05 | NC | DE-GUP-DT-E-24-202 | 2024-08-13 | 4 | 자체 CRS 개정 후 제출 | 2025-01-16 | N/A | DE-GUP-DT-E-25-009 | 2025-01-17 | 5
| GUP | YD05 | P1 | ZEN | 160145 |  | GUP-YD05-P1ZEN-160145 | HMI GRAPHIC DISPLAY DIAGRAM_HVAC | FI | 2022-12-27 |  | 계측기술팀(I&C) | 우현아 |  |  |  |  | HVAC | CCPP | HVAC | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-009 | 2025-01-17 | 4 | 자체 CRS 개정 후 제출 | 2025-01-16 | N/A | DE-GUP-DT-E-23-061 | 2023-01-20 | 0 | CRS-GUP-DHI-DT-23-1474 | 2023-02-09 | NC | DE-GUP-DT-E-23-220 | 2023-02-22 | 1 | CRS-GUP-DHI-DT-23-1584 | 2023-02-25 | NC | DE-GUP-DT-E-23-487 | 2023-04-21 | 2 | CRS-GUP-DHI-DT-23-1912 | 2023-05-05 | NC | DE-GUP-DT-E-23-782 | 2023-08-31 | 3 | 자체 CRS 개정 후 제출 | 2025-01-16 | N/A | DE-GUP-DT-E-25-009 | 2025-01-17 | 4
| GUP | YD02 | P1 | ZEN | 160146 |  | GUP-YD02-P1ZEN-160146 | CONDUIT LAYOUT DRAWING_HVAC | FI | 2022-12-27 |  | 계측기술팀(I&C) | 우현아 |  |  |  |  | HVAC | CCPP | HVAC | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-202 | 2024-08-13 | 2 | 자체 CRS 개정 후 제출 | 2024-08-12 | N/A | DE-GUP-DT-E-23-244 | 2023-02-24 | 0 | CRS-GUP-DHI-DT-23-1706 | 2023-03-14 | NC | DE-GUP-DT-E-23-882 | 2023-11-07 | 1 | 자체 CRS 개정 후 제출 | 2024-08-12 | N/A | DE-GUP-DT-E-24-202 | 2024-08-13 | 2
| GUP | YR04 | P1 | ZEN | 160149 |  | GUP-YR04-P1ZEN-160149 | DCS POWER DISTRIBUTION DIAGRAMS WITH POWER CONSUMPTION & HEAT DISSIPATION | FI | 2022-07-14 |  | 계측기술팀(I&C) | 고경환 |  |  |  |  | DCS | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-997 | 2023-12-15 | 2 | CRS-GUP-DHI-DT-23-1473 | 2023-02-09 | NC | DE-GUP-DT-E-22-254 | 2022-05-27 | 0 | CRS-GUP-DHI-DT-22-451 | 2022-06-17 | NC | DE-GUP-DT-E-23-040 | 2023-01-17 | 1 | CRS-GUP-DHI-DT-23-1473 | 2023-02-09 | NC | DE-GUP-DT-E-23-997 | 2023-12-15 | 2
| GUP | YK00 | P1 | ZEN | 160150 |  | GUP-YK00-P1ZEN-160150 | TECHNICAL SPECIFICATION_INSTRUMENT INSTALLATION MATERIALS | FI | 2022-11-26 |  | 계측기술팀(I&C) | 백지원 | [5 empty] | CCPP | Instrument Installation Materials | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-105 | 2023-02-02 | 1 | CRS-GUP-DHI-DT-23-1538 | 2023-02-15 | NC | DE-GUP-DT-E-22-1018 | 2022-11-30 | 0 | CRS-GUP-DHI-DT-22-1273 | 2022-12-16 | NC | DE-GUP-DT-E-23-105 | 2023-02-02 | 1 | CRS-GUP-DHI-DT-23-1538 | 2023-02-15 | NC
| GUP | CV03 | P1 | ZEN | 160151 |  | GUP-CV03-P1ZEN-160151 | TECHNICAL SPECIFICATION_CYBER SECURITY & ANTI VIRUS_DCS | FA | 2022-04-15 | 2022-08-19 | 계측기술팀(I&C) | 고경환 |  |  | G | FA | DCS | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-22-980 | 2022-11-24 | 0 | CRS-GUP-DHI-DT-22-1245 | 2022-12-13 | AA | DHI-GUP-DT-22-158 | 2022-04-11 | A | CRS-GUP-DHI-DT-22-313 | 2022-05-02 | RC | DE-GUP-DT-E-22-600 | 2022-09-01 | B | CRS-GUP-DHI-DT-22-844 | 2022-09-24 | RC | DE-GUP-DT-E-22-882 | 2022-10-31 | C | CRS-GUP-DHI-DT-22-1084 | 2022-11-19 | AA | DE-GUP-DT-E-22-980 | 2022-11-24 | 0 | CRS-GUP-DHI-DT-22-1245 | 2022-12-13 | AA
| GUP | CV05 | P1 | ZEN | 160201 |  | GUP-CV05-P1ZEN-160201 | DCS_O&M Manual | FI | 2024-06-30 |  | 계측기술팀(I&C) | 고경환 |  |  |  |  | DCS | CCPP | DCS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-153 | 2024-06-12 | 0 | CRS-GUP-DHI-DT-24-063 | 2024-07-17 | NC | DE-GUP-DT-E-24-153 | 2024-06-12 | 0 | CRS-GUP-DHI-DT-24-063 | 2024-07-17 | NC
| GUP | CV05 | P1 | ZEN | 160202 |  | GUP-CV05-P1ZEN-160202 | Weather Station_O&M Manual | FI | 2024-06-30 |  | 계측기술팀(I&C) | 고경환 |  |  |  |  | Weather Station | CCPP | Weather Station | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-153 | 2024-06-12 | 0 | CRS-GUP-DHI-DT-25-004 | 2025-01-10 | NC | DE-GUP-DT-E-24-153 | 2024-06-12 | 0 | CRS-GUP-DHI-DT-25-004 | 2025-01-10 | NC
| GUP | CV05 | P1 | ZEN | 160203 |  | GUP-CV05-P1ZEN-160203 | Control Valves_BOP_O&M Manual | FI | 2024-06-30 |  | 계측기술팀(I&C) | 고경환 |  |  |  |  | Control Valve | CCPP | Control Valve | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-153 | 2024-06-12 | 0 | CRS-GUP-DHI-DT-24-063 | 2024-07-17 | NC | DE-GUP-DT-E-24-153 | 2024-06-12 | 0 | CRS-GUP-DHI-DT-24-063 | 2024-07-17 | NC
| GUP | CV05 | P1 | ZEN | 160204 |  | GUP-CV05-P1ZEN-160204 | PROCESS TRANSMITTER_BOP_O&M Manual | FI | 2024-06-30 |  | 계측기술팀(I&C) | 고경환 |  |  |  |  | Process Transmitter | CCPP | Process Transmitter | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-196 | 2024-08-06 | 0 | CRS-GUP-DHI-DT-25-006 | 2025-01-10 | NC | DE-GUP-DT-E-24-196 | 2024-08-06 | 0 | CRS-GUP-DHI-DT-25-006 | 2025-01-10 | NC
| GUP | CV05 | P1 | ZEN | 160205 |  | GUP-CV05-P1ZEN-160205 | LOCAL INSTRUMENT_BOP_O&M Manual | FI | 2024-06-30 |  | 계측기술팀(I&C) | 고경환 |  |  |  |  | Local Insturment | CCPP | Local Insturment | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-196 | 2024-08-06 | 0 | CRS-GUP-DHI-DT-25-005 | 2025-01-10 | NC | DE-GUP-DT-E-24-196 | 2024-08-06 | 0 | CRS-GUP-DHI-DT-25-005 | 2025-01-10 | NC
| GUP | CV05 | P1 | ZEN | 160206 |  | GUP-CV05-P1ZEN-160206 | FLOW ELEMENT_BOP_O&M Manual | FI | 2024-06-30 |  | 계측기술팀(I&C) | 고경환 |  |  |  |  | Flow Element | CCPP | Flow Element | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-196 | 2024-08-06 | 0 | CRS-GUP-DHI-DT-25-007 | 2025-01-10 | NC | DE-GUP-DT-E-24-196 | 2024-08-06 | 0 | CRS-GUP-DHI-DT-25-007 | 2025-01-10 | NC
| GUP | CV05 | P1 | ZEN | 160207 |  | GUP-CV05-P1ZEN-160207 | HVAC I&C_O&M Manual | FI | 2024-06-30 |  | 계측기술팀(I&C) | 고경환 |  |  |  |  | HVAC I&C | CCPP | HVAC I&C | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-24-230 | 2024-09-13 | 1 | CRS-GUP-DHI-DT-24-063 | 2024-07-17 | NC | DE-GUP-DT-E-24-153 | 2024-06-12 | 0 | CRS-GUP-DHI-DT-24-063 | 2024-07-17 | NC | DE-GUP-DT-E-24-230 | 2024-09-13 | 1
| GUP | XA01 | P1 | LBG | 430003 |  | GUP-XA01-P1LBG-430003 | OUTLINE DRAWING FOR ATMOSPHERIC FLASH TANK | FI | 2022-04-06 |  | TM System설계팀(Mech.) | 이응수 |  | P |  |  |  | CCPP | MISC. TANK | mech. | 3 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-403 | 2023-03-30 | 5 | CRS-GUP-DHI-DT-23-1856 | 2023-04-19 | NC | DHI-GUP-DT-21-087 | 2021-11-02 | 0 | CRS-GUP-DHI-DT-21-146 | 2022-01-12 | NC | DHI-GUP-DT-22-034 | 2022-01-25 | 1 | CRS-GUP-DHI-DT-22-219 | 2022-02-20 | NC | DE-GUP-DT-E-22-627 | 2022-09-07 | 2 | CRS-GUP-DHI-DT-22-871 | 2022-10-09 | NC | DE-GUP-DT-E-22-967 | 2022-11-22 | 3 | CRS-GUP-DHI-DT-22-1203 | 2022-11-30 | NC | DE-GUP-DT-E-23-035 | 2023-01-17 | 4 | CRS-GUP-DHI-DT-23-1530 | 2023-02-14 | NC | DE-GUP-DT-E-23-403 | 2023-03-30 | 5 | CRS-GUP-DHI-DT-23-1856 | 2023-04-19 | NC
| GUP | XA01 | P1 | PG | 430004 |  | GUP-XA01-P1PG-430004 | OUTLINE DRAWING FOR CCW CHEMICAL ADDITIVE TANK | FI | 2021-12-14 |  | TM System설계팀(Mech.) | 이응수 |  | P |  |  |  | CCPP | MISC. TANK | mech. | 3 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-403 | 2023-03-30 | 4 | CRS-GUP-DHI-DT-23-1856 | 2023-04-19 | NC | DHI-GUP-DT-21-077 | 2021-10-25 | 0 | CRS-GUP-DHI-DT-21-146 | 2022-01-12 | NC | DHI-GUP-DT-22-034 | 2022-01-25 | 1 | CRS-GUP-DHI-DT-22-219 | 2022-02-20 | NC | DE-GUP-DT-E-22-1078 | 2022-12-12 | 2 | CRS-GUP-DHI-DT-22-1324 | 2022-12-22 | NC | DE-GUP-DT-E-23-035 | 2023-01-17 | 3 | CRS-GUP-DHI-DT-23-1530 | 2023-02-14 | NC | DE-GUP-DT-E-23-403 | 2023-03-30 | 4 | CRS-GUP-DHI-DT-23-1856 | 2023-04-19 | NC
| GUP | XA01 | P1 | PG | 430005 |  | GUP-XA01-P1PG-430005 | OUTLINE DRAWING FOR CCW HEAD TANK | FI | 2021-12-14 |  | TM System설계팀(Mech.) | 이응수 |  | P |  |  |  | CCPP | MISC. TANK | mech. | 3 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-403 | 2023-03-30 | 3 | CRS-GUP-DHI-DT-23-1856 | 2023-04-19 | NC | DHI-GUP-DT-21-077 | 2021-10-25 | 0 | CRS-GUP-DHI-DT-21-146 | 2022-01-12 | NC | DHI-GUP-DT-22-034 | 2022-01-25 | 1 | CRS-GUP-DHI-DT-22-219 | 2022-02-20 | NC | DE-GUP-DT-E-23-035 | 2023-01-17 | 2 | CRS-GUP-DHI-DT-23-1530 | 2023-02-14 | NC | DE-GUP-DT-E-23-403 | 2023-03-30 | 3 | CRS-GUP-DHI-DT-23-1856 | 2023-04-19 | NC
| GUP | XA01 | P1 | EG | 430006 |  | GUP-XA01-P1EG-430006 | OUTLINE DRAWING FOR ULSD BUFFER TANK | FI | 2022-10-01 |  | TM System설계팀(Mech.) | 이응수 |  | P |  |  |  | CCPP | MISC. TANK | mech. | 3 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-23-509 | 2023-04-26 | 4 | CRS-GUP-DHI-DT-23-1928 | 2023-05-05 | NC | DE-GUP-DT-E-22-689 | 2022-09-22 | 0 | CRS-GUP-DHI-DT-22-991 | 2022-11-13 | NC | DE-GUP-DT-E-22-1004 | 2022-11-29 | 1 | CRS-GUP-DHI-DT-22-1305 | 2022-12-22 | NC | DE-GUP-DT-E-23-035 | 2023-01-17 | 2 | CRS-GUP-DHI-DT-23-1530 | 2023-02-14 | NC | DE-GUP-DT-E-23-403 | 2023-03-30 | 3 | CRS-GUP-DHI-DT-23-1856 | 2023-04-19 | NC | DE-GUP-DT-E-23-509 | 2023-04-26 | 4 | CRS-GUP-DHI-DT-23-1928 | 2023-05-05 | NC
| GUP | XA01 | P0 | EGB | 430007 |  | GUP-XA01-P0EGB-430007 | Outline Drawing for Flushed Fuel Storage Tank | FI | 2024-11-01 |  | TM System설계팀(Mech.) | 이응수 |  | P |  |  |  | CCPP | MISC. TANK | mech. | 3 | 2025-06-30 | 2025-07-01 |  | DE-GUP-DT-E-24-260 | 2024-11-07 | 0 | CRS-GUP-DHI-DT-25-015 | 2025-02-04 | RC | DE-GUP-DT-E-24-260 | 2024-11-07 | 0 | CRS-GUP-DHI-DT-25-015 | 2025-02-04 | RC
| GUP | YF02 | P1 | BT | 190001 |  | GUP-YF02-P1BT-190001 | CONTROL SYSTEM CONFIGURATION DRAWING_BESS | FA | 2021-12-27 | 2022-03-28 | ESS팀 | 장형성 |  |  | G | FA |  | CCPP | BESS | I&C | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-533 | 2023-05-09 | 1 | CRS-GUP-DHI-DT-23-1951 | 2023-05-17 | AA | DHI-GUP-DT-21-031 | 2021-09-17 | A | CRS-GUP-DHI-DT-21-025 | 2021-10-04 | RC | DHI-GUP-DT-21-154 | 2021-12-08 | B | CRS-GUP-DHI-DT-21-108 | 2022-01-05 | RC | DHI-GUP-DT-22-011 | 2022-01-10 | C | CRS-GUP-DHI-DT-21-178 | 2022-01-31 | AA | DE-GUP-DT-E-22-1142 | 2022-12-21 | 0 | CRS-GUP-DHI-DT-23-1503 | 2023-02-14 | AA | DE-GUP-DT-E-23-533 | 2023-05-09 | 1 | CRS-GUP-DHI-DT-23-1951 | 2023-05-17 | AA
| GUP | YL01 | P1 | BT | 190002 |  | GUP-YL01-P1BT-190002 | CONTROL SYSTEM IO LIST_BESS | FI | 2023-01-28 |  | ESS팀 | 백지원 | [5 empty] | CCPP | BESS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-837 | 2023-10-04 | 1 | CRS-GUP-DHI-DT-23-1692 | 2023-03-14 | NC | DE-GUP-DT-E-23-207 | 2023-02-20 | 0 | CRS-GUP-DHI-DT-23-1692 | 2023-03-14 | NC | DE-GUP-DT-E-23-837 | 2023-10-04 | 1
| GUP | YD05 | P1 | BT | 190003 |  | GUP-YD05-P1BT-190003 | HMI GRAPHIC_BESS | FI | 2023-01-28 |  | ESS팀 | 백지원 | [5 empty] | CCPP | BESS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-862 | 2023-10-20 | 1 | CRS-GUP-DHI-DT-23-2133 | 2023-11-01 | NC | DE-GUP-DT-E-23-696 | 2023-07-18 | 0 | CRS-GUP-DHI-DT-23-2094 | 2023-08-16 | RC | DE-GUP-DT-E-23-862 | 2023-10-20 | 1 | CRS-GUP-DHI-DT-23-2133 | 2023-11-01 | NC
| GUP | YR05 | P1 | BT | 190004 |  | GUP-YR05-P1BT-190004 | ENERGY MANAGEMENT SYSTEM SPECIFICATION_BESS | FA | 2022-11-13 | 2023-04-13 | ESS팀 | 장형성 |  |  |  |  | BESS | CCPP | BESS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-534 | 2023-05-09 | 1 | CRS-GUP-DHI-DT-23-1641 | 2023-03-04 | AA | DE-GUP-DT-E-22-1142 | 2022-12-21 | A | CRS-GUP-DHI-DT-22-1406 | 2023-01-07 | RC | DE-GUP-DT-E-23-193 | 2023-02-16 | B | CRS-GUP-DHI-DT-23-1641 | 2023-03-04 | AA | DE-GUP-DT-E-23-306 | 2023-03-14 | 0 | N/A |  |  | DE-GUP-DT-E-23-534 | 2023-05-09 | 1
| GUP | YD00 | P1 | BT | 190005 |  | GUP-YD00-P1BT-190005 | I&C AND ELECTRICAL EQUIPMENT LAYOUT DRAWING_BESS CONTROL BUILDING | FI | 2022-03-28 |  | ESS팀 | 장형성 |  | P |  |  |  | CCPP | BESS | I&C | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-544 | 2023-05-12 | 3 | CRS-GUP-DHI-DT-23-1999 | 2023-06-15 | NC | DHI-GUP-DT-21-176 | 2021-12-16 | 0 | CRS-GUP-DHI-DT-21-151 | 2022-01-12 | NC | DE-GUP-DT-E-22-895 | 2022-11-01 | 1 | CRS-GUP-DHI-DT-22-1159 | 2022-11-24 | NC | DE-GUP-DT-E-22-1234 | 2023-01-06 | 2 | CRS-GUP-DHI-DT-22-1415 | 2023-01-11 | NC | DE-GUP-DT-E-23-544 | 2023-05-12 | 3 | CRS-GUP-DHI-DT-23-1999 | 2023-06-15 | NC
| GUP | XW01 | P1 | BT | 190006 |  | GUP-XW01-P1BT-190006 | DESIGN CRITERIA FOR BESS | FA | 2021-12-27 | 2022-03-28 | ESS팀 | 김홍기 |  | P | G | FA |  | CCPP | BESS | Elec. | 1 | 2025-06-30 |  |  | DE-GUP-DT-E-24-178 | 2024-07-08 | 5 | CRS-GUP-DHI-DT-24-058 | 2024-07-04 | AA | DHI-GUP-DT-21-031 | 2021-09-17 | A | CRS-GUP-DHI-DT-21-027 | 2021-10-04 | RC | DHI-GUP-DT-21-154 | 2021-12-08 | B | CRS-GUP-DHI-DT-21-108 | 2022-01-05 | AC | DE-GUP-DT-E-22-635 | 2022-09-07 | C | CRS-GUP-DHI-DT-22-807 | 2022-09-19 | RC | DE-GUP-DT-E-22-911 | 2022-11-04 | D | CRS-GUP-DHI-DT-22-1157 | 2022-11-24 | AC | DE-GUP-DT-E-23-285 | 2023-03-08 | 0(CP) | CRS-GUP-DHI-DT-23-1810 | 2023-04-04 | AC | DE-GUP-DT-E-23-495 | 2023-04-21 | 1(CP) | CRS-GUP-DHI-DT-23-1953 | 2023-05-18 | AC | DE-GUP-DT-E-23-730 | 2023-07-28 | 2(CP) | CRS-GUP-DHI-DT-23-2106 | 2023-09-13 | AC | DE-GUP-DT-E-23-851 | 2023-10-13 | 3(CP) | CRS-GUP-DHI-DT-23-2135 | 2023-11-17 | AC | DE-GUP-DT-E-24-065 | 2024-03-06 | 4(CP) | CRS-GUP-DHI-DT-24-058 | 2024-07-04 | AA | DE-GUP-DT-E-24-178 | 2024-07-08 | 5
| GUP | YU02 | P1 | BT | 190007 |  | GUP-YU02-P1BT-190007 | SINGLE LINE DRAWING FOR BESS | FA | 2021-12-27 | 2022-03-28 | ESS팀 | 김홍기 |  |  | G | FA |  | CCPP | BESS | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-674 | 2023-07-05 | 3 | DE-GUP-DT-E-23-1822 | 2023-04-12 | AA | DHI-GUP-DT-21-031 | 2021-09-17 | A | CRS-GUP-DHI-DT-21-037 | 2021-10-06 | RC | DHI-GUP-DT-21-154 | 2021-12-08 | B | CRS-GUP-DHI-DT-21-108 | 2022-01-05 | AA | DE-GUP-DT-E-22-635 | 2022-09-07 | C | CRS-GUP-DHI-DT-22-807 | 2022-09-19 | RC | DE-GUP-DT-E-22-911 | 2022-11-04 | D | CRS-GUP-DHI-DT-22-1157 | 2022-11-24 | AC | DE-GUP-DT-E-23-033 | 2023-01-16 | 0(CP) | DE-GUP-DT-E-23-1645 | 2023-03-07 | AC | DE-GUP-DT-E-23-296 | 2023-03-10 | 1(CP) | CRS-GUP-DHI-DT-23-1783 | 2023-03-30 | AC | DE-GUP-DT-E-23-411 | 2023-04-03 | 2(CP) | DE-GUP-DT-E-23-1822 | 2023-04-12 | AA | DE-GUP-DT-E-23-674 | 2023-07-05 | 3
| GUP | YD00 | P1 | BT | 190008 |  | GUP-YD00-P1BT-190008 | GENERAL ARRANGEMENT DRAWING OF BESS | FA | 2021-12-27 | 2022-03-28 | ESS팀 | 김홍기 |  | P | G | FI |  | CCPP | BESS | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-662 | 2023-07-04 | 2 | CRS-GUP-DHI-DT-23-1766 | 2023-03-22 | AA | DHI-GUP-DT-21-031 | 2021-09-17 | A | CRS-GUP-DHI-DT-21-037 | 2021-10-06 | RC | DHI-GUP-DT-21-154 | 2021-12-08 | B | CRS-GUP-DHI-DT-21-108 | 2022-01-05 | AC | DE-GUP-DT-E-22-635 | 2022-09-07 | C | CRS-GUP-DHI-DT-22-807 | 2022-09-19 | AC | DE-GUP-DT-E-22-911 | 2022-11-04 | D | CRS-GUP-DHI-DT-22-1157 | 2022-11-24 | AC | DE-GUP-DT-E-23-164 | 2023-02-13 | 0(CP) | CRS-GUP-DHI-DT-23-1640 | 2023-03-04 | AC | DE-GUP-DT-E-23-297 | 2023-03-10 | 1(CP) | CRS-GUP-DHI-DT-23-1766 | 2023-03-22 | AA | DE-GUP-DT-E-23-662 | 2023-07-04 | 2
| GUP | XW03 | P1 | BT | 190009 |  | GUP-XW03-P1BT-190009 | SIZING CALCULATION - BESS | FA | 2022-03-28 | 2022-06-26 | ESS팀 | 박종현 |  | P | G | FA |  | CCPP | BESS | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-610 | 2023-06-08 | 1 | CRS-GUP-DHI-DT-23-1761 | 2023-03-22 | AA | DHI-GUP-DT-21-184 | 2021-12-17 | A | CRS-GUP-DHI-DT-21-134 | 2022-01-11 | RC | DHI-GUP-DT-22-141 | 2022-03-29 | B | CRS-GUP-DHI-DT-22-299 | 2022-04-17 | AC | DE-GUP-DT-E-22-635 | 2022-09-07 | C | CRS-GUP-DHI-DT-22-853 | 2022-09-24 | RC | DE-GUP-DT-E-22-911 | 2022-11-04 | D | CRS-GUP-DHI-DT-22-1157 | 2022-11-24 | AC | DE-GUP-DT-E-23-288 | 2023-03-09 | 0(CP) | CRS-GUP-DHI-DT-23-1761 | 2023-03-22 | AA | DE-GUP-DT-E-23-610 | 2023-06-08 | 1
| GUP | YL06 | P1 | BT | 190010 |  | GUP-YL06-P1BT-190010 | ELECTRICAL LOAD LIST - BESS | FA | 2022-11-25 | 2023-02-23 | ESS팀 | 김홍기 |  |  | G | FA |  | CCPP | BESS | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-854 | 2023-10-17 | 1 | CRS-GUP-DHI-DT-23-2116 | 2023-09-27 | AA | DE-GUP-DT-E-23-364 | 2023-03-24 | A | CRS-GUP-DHI-DT-23-1834 | 2023-04-18 | RC | DE-GUP-DT-E-23-599 | 2023-06-02 | B | CRS-GUP-DHI-DT-23-2021 | 2023-06-22 | AC | DE-GUP-DT-E-23-791 | 2023-09-06 | 0(CP) | CRS-GUP-DHI-DT-23-2116 | 2023-09-27 | AA | DE-GUP-DT-E-23-854 | 2023-10-17 | 1
| GUP | YL16 | P1 | BT | 190011 |  | GUP-YL16-P1BT-190011 | POWER & CONTROL CABLE SCHEDULE - BESS | FI | 2023-03-29 |  | ESS팀 | 김홍기 |  |  | G | FI |  | CCPP | BESS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-678 | 2023-07-06 | 1 | CRS-GUP-DHI-DT-23-2068 | 2023-07-24 | NC | DE-GUP-DT-E-23-437 | 2023-04-07 | 0 | CRS-GUP-DHI-DT-23-1878 | 2023-04-27 | NC | DE-GUP-DT-E-23-678 | 2023-07-06 | 1 | CRS-GUP-DHI-DT-23-2068 | 2023-07-24 | NC
| GUP | YS02 | P1 | BT | 190012 |  | GUP-YS02-P1BT-190012 | CABLE CONNECTION DIAGRAM - BESS | FI | 2023-03-29 |  | ESS팀 | 김홍기 |  |  | G | FI |  | CCPP | BESS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-762 | 2023-08-24 | 0 | CRS-GUP-DHI-DT-23-2123 | 2023-10-26 | NC | DE-GUP-DT-E-23-762 | 2023-08-24 | 0 | CRS-GUP-DHI-DT-23-2123 | 2023-10-26 | NC
| GUP | YD16 | P1 | BT | 190013 |  | GUP-YD16-P1BT-190013 | CABLE TRAY LAYOUT DRAWING_BESS | FI | 2023-01-12 |  | ESS팀 | 김홍기 | [5 empty] | CCPP | BESS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-861 | 2023-10-20 | 2 | CRS-GUP-DHI-DT-23-2067 | 2023-07-24 | NC | DE-GUP-DT-E-23-327 | 2023-03-17 | 0 | CRS-GUP-DHI-DT-23-1791 | 2023-03-30 | NC | DE-GUP-DT-E-23-675 | 2023-07-06 | 1 | CRS-GUP-DHI-DT-23-2067 | 2023-07-24 | NC | DE-GUP-DT-E-23-861 | 2023-10-20 | 2
| GUP | YR02 | P1 | BT | 190015 |  | GUP-YR02-P1BT-190015 | TECHNICAL SPECIFICATION - MV SWGR & DB FOR BESS | FA | 2022-11-13 | 2023-02-13 | ESS팀 | 김홍기 |  |  |  |  | BESS | CCPP | BESS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-966 | 2023-12-01 | 2 | 자체 CRS 개정 후 제출 | 2023-11-30 | N/A | DE-GUP-DT-E-23-057 | 2023-01-19 | A | CRS-GUP-DHI-DT-23-1608 | 2023-03-02 | RC | DE-GUP-DT-E-23-412 | 2023-04-03 | B | CRS-GUP-DHI-DT-23-1830 | 2023-04-12 | RC | DE-GUP-DT-E-23-542 | 2023-05-11 | C | CRS-GUP-DHI-DT-23-1968 | 2023-06-01 | AA | DE-GUP-DT-E-23-612 | 2023-06-09 | 0 | CRS-GUP-DHI-DT-23-2022 | 2023-06-22 | AA | DE-GUP-DT-E-23-789 | 2023-09-06 | 1 | 자체 CRS 개정 후 제출 | 2023-11-30 | N/A | DE-GUP-DT-E-23-966 | 2023-12-01 | 2
| GUP | YR02 | P1 | BT | 190017 |  | GUP-YR02-P1BT-190017 | TECHNICAL SPECIFICATION - PCS FOR BESS | FA | 2023-01-13 | 2023-04-13 | ESS팀 | 장형성 |  |  |  |  | BESS | CCPP | BESS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-617 | 2023-06-14 | 2 | CRS-GUP-DHI-DT-23-1996 | 2023-06-13 | AA | DE-GUP-DT-E-22-1235 | 2023-01-09 | A | CRS-GUP-DHI-DT-23-1554 | 2023-02-23 | AC | DE-GUP-DT-E-23-522 | 2023-05-04 | 0(CP) | CRS-GUP-DHI-DT-23-1954 | 2023-05-18 | AC | DE-GUP-DT-E-23-590 | 2023-05-30 | 1(CP) | CRS-GUP-DHI-DT-23-1996 | 2023-06-13 | AA | DE-GUP-DT-E-23-617 | 2023-06-14 | 2
| GUP | YR02 | P1 | BT | 190018 |  | GUP-YR02-P1BT-190018 | TECHNICAL SPECIFICATION - BATTERY FOR BESS | FA | 2023-01-13 | 2023-04-13 | ESS팀 | 박종현 |  | P | G | FI | BESS | CCPP | BESS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-794 | 2023-09-06 | 1 | 자체 CRS 개정 후 제출 | 2023-09-05 | N/A | DE-GUP-DT-E-23-067 | 2023-01-20 | A | CRS-GUP-DHI-DT-23-1638 | 2023-03-04 | AA | DE-GUP-DT-E-23-425 | 2023-04-05 | 0 | 자체 CRS 개정 후 제출 | 2023-09-05 | N/A | DE-GUP-DT-E-23-794 | 2023-09-06 | 1
| GUP | YR02 | P1 | BT | 190019 |  | GUP-YR02-P1BT-190019 | TECHNICAL SPECIFICATION - BATTERY CONTAINER | FA | 2023-01-13 | 2023-04-13 | ESS팀 | 김홍기 |  | P |  |  | BESS | CCPP | BESS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-660 | 2023-07-03 | 1 | CRS-GUP-DHI-DT-23-2049 | 2023-07-14 | AA | DE-GUP-DT-E-23-005 | 2023-01-12 | A | CRS-GUP-DHI-DT-23-1555 | 2023-02-23 | RC | DE-GUP-DT-E-23-319 | 2023-03-15 | B | CRS-GUP-DHI-DT-23-1789 | 2023-03-30 | AC | DE-GUP-DT-E-23-566 | 2023-05-19 | 0(CP) | CRS-GUP-DHI-DT-23-1990 | 2023-06-13 | AA | DE-GUP-DT-E-23-660 | 2023-07-03 | 1 | CRS-GUP-DHI-DT-23-2049 | 2023-07-14 | AA
| GUP | YR02 | P1 | BT | 190040 |  | GUP-YR02-P1BT-190040 | TECHNICAL SPECIFICATION - CABLE TERMINATION MATERIAL FOR BESS PCS TR | FI | 2023-04-30 |  | ESS팀 | 장형성 |  |  |  |  | BESS | CCPP | BESS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-410 | 2023-04-03 | 0 | CRS-GUP-DHI-DT-23-1860 | 2023-04-19 | NC | DE-GUP-DT-E-23-410 | 2023-04-03 | 0 | CRS-GUP-DHI-DT-23-1860 | 2023-04-19 | NC
| GUP | YR02 | P1 | BT | 190041 |  | GUP-YR02-P1BT-190041 | TECHNICAL SPECIFICATION - ELECTRICAL AND I&C CABLE FOR BESS | FA | 2023-05-15 | 2023-07-15 | ESS팀 | 장형성 |  |  |  |  | BESS | CCPP | BESS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-607 | 2023-06-07 | 0 | CRS-GUP-DHI-DT-23-1970 | 2023-06-01 | AA | DE-GUP-DT-E-23-501 | 2023-04-24 | A | CRS-GUP-DHI-DT-23-1923 | 2023-05-05 | RC | DE-GUP-DT-E-23-545 | 2023-05-12 | B | CRS-GUP-DHI-DT-23-1970 | 2023-06-01 | AA | DE-GUP-DT-E-23-607 | 2023-06-07 | 0
| GUP | YD00 | P1 | BT | 190021 |  | GUP-YD00-P1BT-190021 | OUTLINE DRAWING & SINGLE LINE DIAGRAM – MV SWGR & DB FOR BESS | FI | 2022-11-13 |  | ESS팀 | 김홍기 |  |  |  |  | BESS | CCPP | BESS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-965 | 2023-12-01 | 4 | 자체 CRS 개정 후 제출 | 2023-11-30 | N/A | DE-GUP-DT-E-23-057 | 2023-01-19 | 0 | CRS-GUP-DHI-DT-23-1608 | 2023-03-02 | RC | DE-GUP-DT-E-23-412 | 2023-04-03 | 1 | CRS-GUP-DHI-DT-23-1830 | 2023-04-12 | RC | DE-GUP-DT-E-23-542 | 2023-05-11 | 2 | CRS-GUP-DHI-DT-23-1968 | 2023-06-01 | NC | DE-GUP-DT-E-23-676 | 2023-07-06 | 3 | 자체 CRS 개정 후 제출 | 2023-11-30 | N/A | DE-GUP-DT-E-23-965 | 2023-12-01 | 4
| GUP | YD00 | P1 | BT | 190023 |  | GUP-YD00-P1BT-190023 | OUTLINE DRAWING - BATTERY CONTAINER | FI | 2023-01-13 |  | ESS팀 | 김홍기 |  | P |  |  | BESS | CCPP | BESS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-857 | 2023-10-19 | 3 | CRS-GUP-DHI-DT-23-2098 | 2023-08-21 | NC | DE-GUP-DT-E-23-005 | 2023-01-12 | 0 | CRS-GUP-DHI-DT-23-1555 | 2023-02-23 | RC | DE-GUP-DT-E-23-319 | 2023-03-15 | 1 | CRS-GUP-DHI-DT-23-1789 | 2023-03-30 | NC | DE-GUP-DT-E-23-742 | 2023-08-16 | 2 | CRS-GUP-DHI-DT-23-2098 | 2023-08-21 | NC | DE-GUP-DT-E-23-857 | 2023-10-19 | 3
| GUP | YU01 | P1 | BT | 190024 |  | GUP-YU01-P1BT-190024 | PROTECTION AND METERING SINGLE LINE DIAGRAM - BESS | FA | 2023-01-26 | 2023-04-26 | ESS팀 | 김홍기 |  |  | G | FA | BESS | CCPP | BESS | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-621 | 2023-06-16 | 1 | CRS-GUP-DHI-DT-23-2023 | 2023-06-22 | AA | DE-GUP-DT-E-23-096 | 2023-01-31 | A | CRS-GUP-DHI-DT-23-1612 | 2023-03-02 | RC | DE-GUP-DT-E-23-474 | 2023-04-17 | B | CRS-GUP-DHI-DT-23-1938 | 2023-05-11 | AC | DE-GUP-DT-E-23-586 | 2023-05-30 | 0(CP) | CRS-GUP-DHI-DT-23-1994 | 2023-06-13 | AA | DE-GUP-DT-E-23-621 | 2023-06-16 | 1 | CRS-GUP-DHI-DT-23-2023 | 2023-06-22 | AA
| GUP | YF00 | P1 | BT | 190025 |  | GUP-YF00-P1BT-190025 | ELECTRICAL CONTROL LOGIC DIAGRAM - MV SWITCHGEAR FOR BESS | FA | 2023-02-26 | 2023-05-26 | ESS팀 | 김홍기 |  |  | G | FA | BESS | CCPP | BESS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-751 | 2023-08-23 | 0 | CRS-GUP-DHI-DT-23-2097 | 2023-08-21 | AA | DE-GUP-DT-E-23-628 | 2023-06-19 | A | CRS-GUP-DHI-DT-23-2046 | 2023-07-14 | RC | DE-GUP-DT-E-23-729 | 2023-07-28 | B | CRS-GUP-DHI-DT-23-2097 | 2023-08-21 | AA | DE-GUP-DT-E-23-751 | 2023-08-23 | 0
| GUP | YT10 | P1 | BT | 190042 |  | GUP-YT10-P1BT-190042 | PROTECTION RELAY COORDINATION STUDY – MV SWGR FOR BESS | FA | 2023-08-15 | 2023-10-15 | ESS팀 | 김홍기 |  |  |  |  | BESS | CCPP | BESS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-25-064 | 2025-06-13 | 1 | CRS-GUP-DHI-DT-25-047 | 2025-03-19 | AA | DE-GUP-DT-E-23-881 | 2023-11-07 | A | CRS-GUP-DHI-DT-24-011 | 2024-02-13 | AC | DE-GUP-DT-E-24-110 | 2024-04-22 | 0(CP) | CRS-GUP-DHI-DT-25-047 | 2025-03-19 | AA | DE-GUP-DT-E-25-064 | 2025-06-13 | 1
| GUP | YF00 | P1 | BT | 190026 |  | GUP-YF00-P1BT-190026 | DESIGN CRITERIA_BESS DC CABLE | FA | 2022-11-29 | 2023-02-28 | ESS팀 | 김홍기 |  |  |  |  | BESS | CCPP | BESS | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-22-1229 | 2023-01-06 | 1 | CRS-GUP-DHI-DT-23-1513 | 2023-02-14 | AA | DE-GUP-DT-E-22-1000 | 2022-11-28 | A | CRS-GUP-DHI-DT-22-1232 | 2022-12-13 | AC | DE-GUP-DT-E-22-1129 | 2022-12-20 | 0(CP) | CRS-GUP-DHI-DT-22-1356 | 2022-12-29 | AA | DE-GUP-DT-E-22-1229 | 2023-01-06 | 1 | CRS-GUP-DHI-DT-23-1513 | 2023-02-14 | AA
| GUP | YR05 | P1 | BT | 190027 |  | GUP-YR05-P1BT-190027 | OUTLINE DRAWING - CABINET & CONSOLE FOR BESS EMS | FI | 2023-01-13 |  | ESS팀 | 장형성 |  |  |  |  | BESS | CCPP | BESS | I&C | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-806 | 2023-09-11 | 1 | CRS-GUP-DHI-DT-22-1406 | 2023-01-07 | NC | DE-GUP-DT-E-22-1142 | 2022-12-21 | 0 | CRS-GUP-DHI-DT-22-1406 | 2023-01-07 | NC | DE-GUP-DT-E-23-806 | 2023-09-11 | 1
| GUP | HM00 | P1 | BT | 190028 |  | GUP-HM00-P1BT-190028 | HVAC CALCULATION AND DATASHEET - BATTERY CONTAINER | FA | 2023-01-20 | 2023-04-20 | ESS팀 | 김홍기 |  |  |  |  | BESS | CCPP | BESS | Elec. | 2 | 2025-06-30 |  |  | DE-GUP-DT-E-23-911 | 2023-11-16 | 1 | CRS-GUP-DHI-DT-23-2049 | 2023-07-14 | AA | DE-GUP-DT-E-23-005 | 2023-01-12 | A | CRS-GUP-DHI-DT-23-1555 | 2023-02-23 | RC | DE-GUP-DT-E-23-319 | 2023-03-15 | B | CRS-GUP-DHI-DT-23-1789 | 2023-03-30 | RC | DE-GUP-DT-E-23-566 | 2023-05-19 | C | CRS-GUP-DHI-DT-23-1990 | 2023-06-13 | AA | DE-GUP-DT-E-23-660 | 2023-07-03 | 0 | CRS-GUP-DHI-DT-23-2049 | 2023-07-14 | AA | DE-GUP-DT-E-23-911 | 2023-11-16 | 1
| GUP | YU03 | P1 | BT | 190029 |  | GUP-YU03-P1BT-190029 | SCHEMATIC DIAGRAM - MV SWGR & DB FOR BESS | FA | 2023-02-20 | 2023-05-20 | ESS팀 | 김홍기 |  |  |  |  | BESS | CCPP | BESS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-961 | 2023-12-01 | 1 | 자체 CRS 개정 후 제출 | 2023-11-30 | N/A | DE-GUP-DT-E-23-381 | 2023-03-28 | A | CRS-GUP-DHI-DT-23-1847 | 2023-04-19 | AA | DE-GUP-DT-E-23-623 | 2023-06-16 | 0 | 자체 CRS 개정 후 제출 | 2023-11-30 | N/A | DE-GUP-DT-E-23-961 | 2023-12-01 | 1
| GUP | DP00 | P1 | BT | 190030 |  | GUP-DP00-P1BT-190030 | TECHNICAL SPECIFICATION – EMERGENCY SHOWER FOR BESS AREA | FA | 2023-02-20 | 2023-05-20 | ESS팀 | 장형성 |  |  |  |  | BESS | CCPP | BESS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-572 | 2023-05-25 | 2 | CRS-GUP-DHI-DT-23-1922 | 2023-05-05 | AA | DE-GUP-DT-E-23-340 | 2023-03-22 | A | CRS-GUP-DHI-DT-23-1811 | 2023-04-04 | AC | DE-GUP-DT-E-23-443 | 2023-04-10 | 0(cp) | CRS-GUP-DHI-DT-23-1866 | 2023-04-19 | AC | DE-GUP-DT-E-23-500 | 2023-04-24 | 1(CP) | CRS-GUP-DHI-DT-23-1922 | 2023-05-05 | AA | DE-GUP-DT-E-23-572 | 2023-05-25 | 2
| GUP | BV02 | P1 | BT | 190031 |  | GUP-BV02-P1BT-190031 | FAILURE MODES AND EFFECTS ANALYSIS (FMEA) - BESS | FA | 2023-02-10 | 2023-05-10 | ESS팀 | 장형성 | [5 empty] | CCPP | BESS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-618 | 2023-06-14 | 2 | CRS-GUP-DHI-DT-23-1991 | 2023-06-13 | AA | DE-GUP-DT-E-23-439 | 2023-04-07 | A | CRS-GUP-DHI-DT-23-1873 | 2023-04-25 | AC | DE-GUP-DT-E-23-540 | 2023-05-10 | 0(CP) | CRS-GUP-DHI-DT-23-1956 | 2023-05-18 | AC | DE-GUP-DT-E-23-582 | 2023-05-25 | 1(CP) | CRS-GUP-DHI-DT-23-1991 | 2023-06-13 | AA | DE-GUP-DT-E-23-618 | 2023-06-14 | 2
| GUP | MA01 | P1 | BT | 190032 |  | GUP-MA01-P1BT-190032 | HVAC CONTROL BLOCK DIAGRAM - BATTERY CONTAINER | FA | 2023-02-28 | 2023-05-28 | ESS팀 | 김홍기 |  |  |  |  | BESS | CCPP | BESS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-912 | 2023-11-16 | 1 | 자체 CRS 개정 후 제출 | 2023-11-15 | N/A | DE-GUP-DT-E-23-308 | 2023-03-14 | A | CRS-GUP-DHI-DT-23-1784 | 2023-03-30 | RC | DE-GUP-DT-E-23-426 | 2023-04-06 | B | CRS-GUP-DHI-DT-23-1871 | 2023-04-25 | AA | DE-GUP-DT-E-23-528 | 2023-05-08 | 0 | 자체 CRS 개정 후 제출 | 2023-11-15 | N/A | DE-GUP-DT-E-23-912 | 2023-11-16 | 1
| GUP | CA03 | P1 | BT | 190033 |  | GUP-CA03-P1BT-190033 | STRUCTURE DRAWING AND STUDY - BATTERY CONTAINER | FA | 2023-02-28 | 2023-05-28 | ESS팀 | 김홍기 |  |  |  |  | BESS | CCPP | BESS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-661 | 2023-07-04 | 0 | CRS-GUP-DHI-DT-23-2073 | 2023-07-27 | AA | DE-GUP-DT-E-23-289 | 2023-03-09 | A | CRS-GUP-DHI-DT-23-1762 | 2023-03-22 | RC | DE-GUP-DT-E-23-478 | 2023-04-19 | B | CRS-GUP-DHI-DT-23-1894 | 2023-05-02 | AA | DE-GUP-DT-E-23-661 | 2023-07-04 | 0 | CRS-GUP-DHI-DT-23-2073 | 2023-07-27 | AA
| GUP | FF00 | P1 | BT | 190034 |  | GUP-FF00-P1BT-190034 | FIRE FIGHTING CALCULATION AND DATASHEET - BATTERY CONTAINER | FA | 2023-02-28 | 2023-05-28 | ESS팀 | 김홍기 |  | P |  |  | BESS | CCPP | BESS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-928 | 2023-11-21 | 1 | 자체 CRS 개정 후 제출 | 2023-11-20 | N/A | DE-GUP-DT-E-23-307 | 2023-03-14 | A | CRS-GUP-DHI-DT-23-1781 | 2023-03-27 | RC | DE-GUP-DT-E-23-396 | 2023-03-30 | B | CRS-GUP-DHI-DT-23-1853 | 2023-04-19 | RC | DE-GUP-DT-E-23-558 | 2023-05-17 | C | CRS-GUP-DHI-DT-23-1985 | 2023-06-08 | AA | DE-GUP-DT-E-23-691 | 2023-07-14 | 0 | 자체 CRS 개정 후 제출 | 2023-11-20 | N/A | DE-GUP-DT-E-23-928 | 2023-11-21 | 1
| GUP | FF04 | P1 | BT | 190035 |  | GUP-FF04-P1BT-190035 | FIRE FIGHTING EQUIPMENT DIAGRAM AND OUTLINE - BATTERY CONTAINER | FA | 2023-03-31 | 2023-06-30 | ESS팀 | 김홍기 |  | P |  |  | BESS | CCPP | BESS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-927 | 2023-11-21 | 1 | 자체 CRS 개정 후 제출 | 2023-11-20 | N/A | DE-GUP-DT-E-23-356 | 2023-03-24 | A | CRS-GUP-DHI-DT-23-1814 | 2023-04-12 | RC | DE-GUP-DT-E-23-527 | 2023-05-08 | B | CRS-GUP-DHI-DT-23-1965 | 2023-06-01 | AA | DE-GUP-DT-E-23-690 | 2023-07-14 | 0 | 자체 CRS 개정 후 제출 | 2023-11-20 | N/A | DE-GUP-DT-E-23-927 | 2023-11-21 | 1
| GUP | XW03 | P1 | BT | 190036 |  | GUP-XW03-P1BT-190036 | ELECTRICAL DRAWING AND DATASHEET - BATTERY CONTAINER | FA | 2023-02-28 | 2023-05-28 | ESS팀 | 김홍기 |  |  |  |  | BESS | CCPP | BESS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-917 | 2023-11-17 | 2 | 자체 CRS 개정 후 제출 | 2023-11-16 | N/A | DE-GUP-DT-E-23-415 | 2023-04-04 | A | CRS-GUP-DHI-DT-23-1831 | 2023-04-12 | AC | DE-GUP-DT-E-23-583 | 2023-05-25 | 0(CP) | CRS-GUP-DHI-DT-23-1992 | 2023-06-13 | AA | DE-GUP-DT-E-23-692 | 2023-07-17 | 1 | 자체 CRS 개정 후 제출 | 2023-11-16 | N/A | DE-GUP-DT-E-23-917 | 2023-11-17 | 2
| GUP | YD16 | P1 | BT | 190037 |  | GUP-YD16-P1BT-190037 | CABLE SCHEDULE AND ROUTE PLAN - BATTERY CONTAINER | FI | 2023-03-31 |  | ESS팀 | 김홍기 |  |  |  |  | BESS | CCPP | BESS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-869 | 2023-10-25 | 2 | CRS-GUP-DHI-DT-23-2092 | 2023-08-08 | NC | DE-GUP-DT-E-23-529 | 2023-05-08 | 0 | CRS-GUP-DHI-DT-23-1966 | 2023-06-01 | NC | DE-GUP-DT-E-23-716 | 2023-07-24 | 1 | CRS-GUP-DHI-DT-23-2092 | 2023-08-08 | NC | DE-GUP-DT-E-23-869 | 2023-10-25 | 2
| GUP | YQ01 | P1 | BT | 190038 |  | GUP-YQ01-P1BT-190038 | Lighting Illumination Calculation – Battery Container | FI | 2023-04-30 |  | ESS팀 | 김홍기 |  |  |  |  | BESS | CCPP | BESS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-418 | 2023-04-04 | 0 | CRS-GUP-DHI-DT-23-1864 | 2023-04-19 | NC | DE-GUP-DT-E-23-418 | 2023-04-04 | 0 | CRS-GUP-DHI-DT-23-1864 | 2023-04-19 | NC
| GUP | CM00 | P1 | BT | 190039 |  | GUP-CM00-P1BT-190039 | INSTALLATION AND ERECTION MANUAL - BATTERY CONTAINER | FI | 2023-05-31 |  | ESS팀 | 김홍기 |  |  |  |  | BESS | CCPP | BESS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-877 | 2023-10-31 | 0 | CRS-GUP-DHI-DT-24-012 | 2024-02-13 | NC | DE-GUP-DT-E-23-877 | 2023-10-31 | 0 | CRS-GUP-DHI-DT-24-012 | 2024-02-13 | NC
| GUP | YF00 | P1 | BT | 190040 |  | GUP-YF00-P1BT-190040 | EMS CONTROL LOGIC DIAGRAM - BESS | FI | 2023-05-31 |  | ESS팀 | 백지원 |  |  |  |  | BESS | CCPP | BESS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-885 | 2023-11-07 | 2 | CRS-GUP-DHI-DT-23-2143 | 2023-12-27 | NC | DE-GUP-DT-E-23-696 | 2023-07-18 | 0 | CRS-GUP-DHI-DT-23-2094 | 2023-08-16 | RC | DE-GUP-DT-E-23-862 | 2023-10-20 | 1 | CRS-GUP-DHI-DT-23-2133 | 2023-11-01 | RC | DE-GUP-DT-E-23-885 | 2023-11-07 | 2 | CRS-GUP-DHI-DT-23-2143 | 2023-12-27 | NC
| GUP | CQ02 | P1 | BT | 190041 |  | GUP-CQ02-P1BT-190041 | BESS_OPERATING AND MAINTENANCE MANUAL | FI | 2023-11-30 |  | ESS팀 | 장형성 |  |  |  |  | BESS | CCPP | BESS | Elec. | 3 | 2025-06-30 |  |  | DE-GUP-DT-E-23-992 | 2023-12-14 | 0 | CRS-GUP-DHI-DT-24-013 | 2024-02-13 | NC | DE-GUP-DT-E-23-992 | 2023-12-14 | 0 | CRS-GUP-DHI-DT-24-013 | 2024-02-13 | NC
| GUP | QA00 | P0 | ZEN | 040001 |  | GUP-QA00-P0ZEN-040001 | Project Quality Plan | FI | 2022-01-25 |  | 건설품질관리팀(Quality) | 신일수 |  |  | G | FA |  | CCPP |  | Quality | 2 |  |  |  | DHI-GUP-DT-21-064 | 2021-12-26 | 0 | CRS-GUP-DHI-DT-21-107 | 2021-12-27 | RC | DHI-GUP-DT-21-064 | 2021-12-26 | 0 | CRS-GUP-DHI-DT-21-107 | 2021-12-27 | RC
| GUP | QM01 | P0 | ZEN | 040001 |  | GUP-QM01-P0ZEN-040001 | Inspection & Test Plan for Offshore Equipment | FA | 2021-12-25 | 2022-03-25 | 건설품질관리팀(Quality) | 신일수 |  |  | G | FA |  | CCPP |  | Quality | 2 |  |  |  | DE-GUP-DT-E-22-605 | 2022-09-01 | 1 | CRS-GUP-DHI-DT-22-277 | 2022-04-07 | AA | DHI-GUP-DT-21-064 | 2021-12-26 | A | CRS-GUP-DHI-DT-21-107 | 2021-12-26 | RC | DHI-GUP-DT-22-015 | 2022-01-13 | B | CRS-GUP-DHI-DT-22-193 | 2022-02-07 | RC | DHI-GUP-DT-22-090 | 2022-02-24 | C | CRS-GUP-DHI-DT-22-258 | 2022-03-17 | AC | DHI-GUP-DT-22-116 | 2022-03-18 | 0 | CRS-GUP-DHI-DT-22-277 | 2022-04-07 | AA | DE-GUP-DT-E-22-605 | 2022-09-01 | 1
| GUP | DA01 | P0 | ZEN | 020001 |  | GUP-DA01-P0ZEN-020001 | DOCUMENT IDENTIFICATION | FA | 2021-12-13 | 2022-04-13 | EM | 백재희 | [5 empty] | CCPP |  | General | 1 |  |  |  | DHI-GUP-DT-21-049 | 2021-10-01 | B |  |  |  | N/A | 2021-02-24 | A |  |  |  | DHI-GUP-DT-21-049 | 2021-10-01 | B
| GUP | DA01 | P0 | ZEN | 020002 |  | GUP-DA01-P0ZEN-020002 | EQUIPMENT AND SYSTEM IDENTIFICATION | FA | 2021-12-13 | 2022-04-13 | EM | 백재희 | [5 empty] | CCPP |  | General | 1 |  |  |  | DE-GUP-DT-E-22-498 | 2022-08-12 | C | N/A | 2022-08-11 | N/A | N/A | 2021-02-24 | A | N/A | 2021-07-09 | RC | DHI-GUP-DT-21-049 | 2021-10-01 | B | N/A | 2022-08-11 | N/A | DE-GUP-DT-E-22-498 | 2022-08-12 | C
| GUP | DD02 | P0 | ZEN | 070001 |  | GUP-DD02-P0-ZEN-070001 | PAINTING PROCEDURE | FI | 2022-03-15 |  | EHS/관리)출하기술팀 (PACKING) | 문대성 | [5 empty] | CCPP |  | General | 1 |  |  |  | DE-GUP-DT-E-22-948 | 2022-11-16 | 5 | CRS-GUP-DHI-DT-22-1161 | 2022-11-24 | NC | DHI-GUP-DT-22-156 | 2022-04-08 | 0 | CRS-GUP-DHI-DT-22-319 | 2022-05-02 | RC | DE-GUP-DT-E-22-281 | 2022-06-09 | 1 | CRS-GUP-DHI-DT-22-485 | 2022-07-04 | RC | DE-GUP-DT-E-22-468 | 2022-07-28 | 2 | CRS-GUP-DHI-DT-22-624 | 2022-08-17 | NC | DE-GUP-DT-E-22-592 | 2022-08-31 | 3 | CRS-GUP-DHI-DT-22-764 | 2022-09-14 | NC | DE-GUP-DT-E-22-691 | 2022-09-22 | 4 | N/A | N/A | N/A | DE-GUP-DT-E-22-948 | 2022-11-16 | 5 | CRS-GUP-DHI-DT-22-1161 | 2022-11-24 | NC
| GUP | DD02 | P0 | ZEN | 070002 |  | GUP-DD02-P0ZEN-070002 | PACKING PROCEDURE | FI | 2022-03-15 |  | EHS/관리)출하기술팀 (PACKING) | 오동주 | [5 empty] | CCPP |  | General | 1 |  |  |  | DHI-GUP-DT-22-088 | 2022-02-24 | 0 |  |  |  | DHI-GUP-DT-22-088 | 2022-02-24 | 0
| GUP | VH00 | P5 | ZEN | 570001 |  | GUP-VH00-P5ZEN-570001 | Basis of Design for Civil_ULSD and LNG Pipeline | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-25-054 | 2025-05-24 | 10 | 별도 메일접수 24-015 | 2024-12-04 | RC | DHI-GUP-DT-22-120 | 2022-03-18 | 0 | CRS-GUP-DHI-DT-22-281 | 2022-04-07 | NC | DE-GUP-DT-E-22-244 | 2022-05-24 | B | CRS-GUP-DHI-DT-22-417 | 2022-06-13 | RC | DE-GUP-DT-E-22-418 | 2022-07-19 | C | CRS-GUP-DHI-DT-22-589 | 2022-08-08 | NC | DE-GUP-DT-E-22-557 | 2022-08-25 | 0 | CRS-GUP-DHI-DT-22-754 | 2022-09-12 | AC | DE-GUP-DT-E-23-203 | 2023-02-20 | 1 | CRS-GUP-DHI-DT-23-1670 | 2023-03-10 | AC | DE-GUP-DT-E-23-502 | 2023-04-24 | 2 | CRS-GUP-DHI-DT-23-1942 | 2023-05-11 | AC | DE-GUP-DT-E-23-569 | 2023-05-19 | 3 | 자체 CRS 개정 후 제출 | 2023-06-07 | N/A | DE-GUP-DT-E-23-604 | 2023-06-08 | 4 | CRS-GUP-DHI-DT-23-2071 | 2023-07-27 | RC | DE-GUP-DT-E-23-855 | 2023-10-18 | 5 | CRS-GUP-DHI-DT-23-2137 | 2023-11-17 | RC | DE-GUP-DT-E-24-052 | 2024-02-23 | 6 | CRS-GUP-DHI-DT-24-047 | 2024-04-15 | RC | DE-GUP-DT-E-24-169 | 2024-06-28 | 7 | FST-DUP-TR-24-048-별도 메일접수 | 2024-08-19 | RC | DE-GUP-DT-E-24-216 | 2024-08-29 | 8 | 자체 CRS 개정 후 제출 | 2024-10-28 | N/A | DE-GUP-DT-E-24-256 | 2024-10-29 | 9 | 별도 메일접수 24-015 | 2024-12-04 | RC | DE-GUP-DT-E-25-054 | 2025-05-24 | 10
| GUP | CA00 | P5 | ZEN | 590001 |  | GUP-CA00-P5ZEN-590001 | Basis of Design for Architectural_ULSD and LNG Pipeline | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-25-053 | 2025-05-24 | 1 | CRS-GUP-DHI-DT-23-1436 | 2023-01-31 | AA | DHI-GUP-DT-22-118 | 2022-03-18 | 0 | CRS-GUP-DHI-DT-22-279 | 2022-04-07 | RC | DHI-GUP-DT-22-219 | 2022-05-13 | B | CRS-GUP-DHI-DT-22-399 | 2022-06-07 | NC | DE-GUP-DT-E-22-1207 | 2023-01-02 | 0(CP) | CRS-GUP-DHI-DT-23-1436 | 2023-01-31 | AA | DE-GUP-DT-E-25-053 | 2025-05-24 | 1
| GUP | CA01 | P5 | ZEN | 580001 |  | GUP-CA01-P5ZEN-580001 | Basis of Design for Structural_ULSD and LNG Pipeline | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-25-055 | 2025-05-24 | 1 | CRS-GUP-DHI-DT-22-1411 | 2023-01-11 | AA | DHI-GUP-DT-22-123 | 2022-03-18 | 0 | CRS-GUP-DHI-DT-22-284 | 2022-04-07 | RC | DE-GUP-DT-E-22-375 | 2022-07-08 | B | CRS-GUP-DHI-DT-22-578 | 2022-08-08 | RC | DE-GUP-DT-E-22-976 | 2022-11-23 | C | CRS-GUP-DHI-DT-22-1229 | 2022-12-13 | AC | DE-GUP-DT-E-22-1119 | 2022-12-19 | 0(CP) | CRS-GUP-DHI-DT-22-1411 | 2023-01-11 | AA | DE-GUP-DT-E-25-055 | 2025-05-24 | 1
| GUP | CC05 | P5 | ZEN | 520001 |  | GUP-CC05-P5ZEN-520001 | Basis of Design for Mechanical_ULSD and LNG Pipeline | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-24-232 | 2024-09-13 | F | 별도메일접수 24-006 | 2024-11-04 | RC | DHI-GUP-DT-22-122 | 2022-03-18 | 0 | CRS-GUP-DHI-DT-22-283 | 2022-04-07 | RC | DE-GUP-DT-E-22-259 | 2022-05-31 | B | CRS-GUP-DHI-DT-22-469 | 2022-06-22 | RC | DE-GUP-DT-E-22-1089 | 2022-12-16 | C | CRS-GUP-DHI-DT-23-1479 | 2023-02-11 | RC | DE-GUP-DT-E-23-368 | 2023-03-27 | D | CRS-GUP-DHI-DT-23-1842 | 2023-04-19 | RC | DE-GUP-DT-E-23-844 | 2023-10-11 | E | CRS-GUP-DHI-DT-23-2134 | 2023-11-17 | RC | DE-GUP-DT-E-24-232 | 2024-09-13 | F | 별도메일접수 24-006 | 2024-11-04 | RC
| GUP | YS18 | P5 | ZEN | 550001 |  | GUP-YS18-P5ZEN-550001 | Basis of Design for Electrical_ULSD and LNG Pipeline | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-24-162 | 2024-06-24 | 0 | CRS-GUP-DHI-DT-23-1747 | 2023-03-18 | AA | DHI-GUP-DT-22-121 | 2022-03-18 | 0 | CRS-GUP-DHI-DT-22-282 | 2022-04-07 | NC | DE-GUP-DT-E-22-494 | 2022-08-11 | B | CRS-GUP-DHI-DT-22-770 | 2022-09-15 | RC | DE-GUP-DT-E-22-1195 | 2022-12-26 | C | CRS-GUP-DHI-DT-23-1435 | 2023-01-31 | RC | DE-GUP-DT-E-23-241 | 2023-02-24 | D | CRS-GUP-DHI-DT-23-1747 | 2023-03-18 | AA | DE-GUP-DT-E-24-162 | 2024-06-24 | 0
| GUP | CA06 | P5 | ZEN | 580001 |  | GUP-CA06-P5ZEN-580001 | Calculation for Structural_ULSD and LNG Pipeline | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-25-055 | 2025-05-24 | 1 | CRS-GUP-DHI-DT-22-1411 | 2023-01-11 | AA | DHI-GUP-DT-22-123 | 2022-03-18 | 0 | CRS-GUP-DHI-DT-22-284 | 2022-04-07 | RC | DE-GUP-DT-E-22-375 | 2022-07-08 | B | CRS-GUP-DHI-DT-22-578 | 2022-08-08 | RC | DE-GUP-DT-E-22-976 | 2022-11-23 | C | CRS-GUP-DHI-DT-22-1229 | 2022-12-13 | AC | DE-GUP-DT-E-22-1119 | 2022-12-19 | 0(CP) | CRS-GUP-DHI-DT-22-1411 | 2023-01-11 | AA | DE-GUP-DT-E-25-055 | 2025-05-24 | 1
| GUP | XW03 | P5 | ZEN | 540001 |  | GUP-XW03-P5ZEN-540001 | Calculation for Mechanical_ULSD and LNG Pipeline | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-24-232 | 2024-09-13 | F | 별도메일접수 24-006 | 2024-11-04 | RC | DHI-GUP-DT-22-122 | 2022-03-18 | 0 | CRS-GUP-DHI-DT-22-283 | 2022-04-07 | RC | DE-GUP-DT-E-22-259 | 2022-05-31 | B | CRS-GUP-DHI-DT-22-469 | 2022-06-22 | RC | DE-GUP-DT-E-22-1089 | 2022-12-16 | C | CRS-GUP-DHI-DT-23-1479 | 2023-02-11 | RC | DE-GUP-DT-E-23-368 | 2023-03-27 | D | CRS-GUP-DHI-DT-23-1842 | 2023-04-19 | RC | DE-GUP-DT-E-23-844 | 2023-10-11 | E | CRS-GUP-DHI-DT-23-2134 | 2023-11-17 | RC | DE-GUP-DT-E-24-232 | 2024-09-13 | F | 별도메일접수 24-006 | 2024-11-04 | RC
| GUP | XW03 | P5 | ZEN | 550001 |  | GUP-XW03-P5ZEN-550001 | Calculation for Electrical_ULSD and LNG Pipeline | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-24-162 | 2024-06-24 | 0 | CRS-GUP-DHI-DT-23-1747 | 2023-03-18 | AA | DHI-GUP-DT-22-121 | 2022-03-18 | 0 | CRS-GUP-DHI-DT-22-282 | 2022-04-07 | NC | DE-GUP-DT-E-22-494 | 2022-08-11 | B | CRS-GUP-DHI-DT-22-770 | 2022-09-15 | RC | DE-GUP-DT-E-22-1195 | 2022-12-26 | C | CRS-GUP-DHI-DT-23-1435 | 2023-01-31 | RC | DE-GUP-DT-E-23-241 | 2023-02-24 | D | CRS-GUP-DHI-DT-23-1747 | 2023-03-18 | AA | DE-GUP-DT-E-24-162 | 2024-06-24 | 0
| GUP | YK09 | P5 | ZEN | 550001 |  | GUP-YK09-P5ZEN-550001 | Drawing for Cathodic Protection System_ULSD and LNG Pipeline | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  | P | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-24-146 | 2024-06-04 | 4 | 자체 CRS 개정 후 제출 | 2024-06-03 | N/A | DHI-GUP-DT-22-119 | 2022-03-18 | 0 | CRS-GUP-DHI-DT-22-280 | 2022-04-07 | NC | DHI-GUP-DT-22-207 | 2022-05-10 | 1 | CRS-GUP-DHI-DT-22-382 | 2022-06-02 | NC | DE-GUP-DT-E-22-348 | 2022-06-29 | C | CRS-GUP-DHI-DT-22-534 | 2022-07-19 | RC | DE-GUP-DT-E-22-599 | 2022-08-31 | D | CRS-GUP-DHI-DT-22-865 | 2022-09-26 | RC | DE-GUP-DT-E-22-1023 | 2022-12-02 | E | CRS-GUP-DHI-DT-22-1282 | 2022-12-21 | AC | DE-GUP-DT-E-23-030 | 2023-01-16 | 0(CP) | CRS-GUP-DHI-DT-23-1528 | 2023-02-14 | AA | DE-GUP-DT-E-23-431 | 2023-04-06 | 1 | CRS-GUP-DHI-DT-23-1877 | 2023-04-27 | AC | DE-GUP-DT-E-23-596 | 2023-05-31 | 2 | CRS-GUP-DHI-DT-23-2020 | 2023-06-22 | AA | DE-GUP-DT-E-24-024 | 2024-01-25 | 3 | 자체 CRS 개정 후 제출 | 2024-06-03 | N/A | DE-GUP-DT-E-24-146 | 2024-06-04 | 4
| GUP | XW03 | P5 | ZEN | 550002 |  | GUP-XW03-P5ZEN-550002 | Calculation for Cathodic Protection_ULSD and LNG Pipeline | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-22-1124 | 2022-12-19 | 0 | CRS-GUP-DHI-DT-23-1500 | 2023-02-14 | AA | DHI-GUP-DT-22-119 | 2022-03-18 | 0 | CRS-GUP-DHI-DT-22-280 | 2022-04-07 | RC | DHI-GUP-DT-22-207 | 2022-05-10 | 1 | CRS-GUP-DHI-DT-22-382 | 2022-06-02 | RC | DE-GUP-DT-E-22-348 | 2022-06-29 | C | CRS-GUP-DHI-DT-22-534 | 2022-07-19 | AA | DE-GUP-DT-E-22-599 | 2022-08-31 | D | CRS-GUP-DHI-DT-22-865 | 2022-09-26 | AA | DE-GUP-DT-E-22-1124 | 2022-12-19 | 0 | CRS-GUP-DHI-DT-23-1500 | 2023-02-14 | AA
| GUP | CC05 | P5 | ZEN | 500002 |  | GUP-CC05-P5ZEN-500002 | Drawing for Architectural_ULSD and LNG Pipeline | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  | P | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-25-053 | 2025-05-24 | 4 | CRS-GUP-DHI-DT-23-2063 | 2023-07-24 | AA | DHI-GUP-DT-22-118 | 2022-03-18 | 0 | CRS-GUP-DHI-DT-22-279 | 2022-04-07 | RC | DHI-GUP-DT-22-219 | 2022-05-13 | B | CRS-GUP-DHI-DT-22-399 | 2022-06-07 | RC | DE-GUP-DT-E-22-975 | 2022-11-23 | C | CRS-GUP-DHI-DT-22-1228 | 2022-12-13 | AC | DE-GUP-DT-E-22-1207 | 2023-01-02 | 0(CP) | CRS-GUP-DHI-DT-23-1436 | 2023-01-31 | RC | DE-GUP-DT-E-23-144 | 2023-02-09 | 1(CP) | CRS-GUP-DHI-DT-23-1665 | 2023-03-09 | AC | DE-GUP-DT-E-23-424 | 2023-04-05 | 2(CP) | CRS-GUP-DHI-DT-23-1897 | 2023-05-02 | AC | DE-GUP-DT-E-23-641 | 2023-06-27 | 3(CP) | CRS-GUP-DHI-DT-23-2063 | 2023-07-24 | AA | DE-GUP-DT-E-25-053 | 2025-05-24 | 4
| GUP | CC05 | P5 | ZEN | 500001 |  | GUP-CC05-P5ZEN-500001 | Drawing for Civil_ULSD and LNG Pipeline | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  | P | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-25-054 | 2025-05-24 | 9 | 별도 메일접수 24-015 | 2024-12-04 | RC | DHI-GUP-DT-22-120 | 2022-03-18 | 0 | CRS-GUP-DHI-DT-22-281 | 2022-04-07 | NC | DE-GUP-DT-E-22-244 | 2022-05-24 | B | CRS-GUP-DHI-DT-22-417 | 2022-06-13 | RC | DE-GUP-DT-E-22-418 | 2022-07-19 | C | CRS-GUP-DHI-DT-22-589 | 2022-08-08 | RC | DE-GUP-DT-E-22-557 | 2022-08-25 | D | CRS-GUP-DHI-DT-22-754 | 2022-09-12 | RC | DE-GUP-DT-E-22-740 | 2022-09-30 | E | CRS-GUP-DHI-DT-22-939 | 2022-10-21 | AC | DE-GUP-DT-E-23-203 | 2023-02-20 | 0(CP) | CRS-GUP-DHI-DT-23-1670 | 2023-03-10 | AC | DE-GUP-DT-E-23-502 | 2023-04-24 | 1(CP) | CRS-GUP-DHI-DT-23-1942 | 2023-05-11 | AC | DE-GUP-DT-E-23-569 | 2023-05-19 | 2(CP) | 자체 CRS 개정 후 제출 | 2023-06-07 | N/A | DE-GUP-DT-E-23-604 | 2023-06-08 | 3(CP) | CRS-GUP-DHI-DT-23-2071 | 2023-07-27 | RC | DE-GUP-DT-E-23-855 | 2023-10-18 | 4(CP) | CRS-GUP-DHI-DT-23-2137 | 2023-11-17 | RC | DE-GUP-DT-E-24-052 | 2024-02-23 | 5 | CRS-GUP-DHI-DT-24-047 | 2024-04-15 | RC | DE-GUP-DT-E-24-169 | 2024-06-28 | 6 | FST-DUP-TR-24-048-별도 메일접수 | 2024-08-19 | RC | DE-GUP-DT-E-24-216 | 2024-08-29 | 7 | 자체 CRS 개정 후 제출 | 2024-10-28 | N/A | DE-GUP-DT-E-24-256 | 2024-10-29 | 8 | 별도 메일접수 24-015 | 2024-12-04 | RC | DE-GUP-DT-E-25-054 | 2025-05-24 | 9
| GUP | CC05 | P5 | ZEN | 500005 |  | GUP-CC05-P5ZEN-500005 | Drawing for Electrical_ULSD and LNG Pipeline | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  | P | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-24-243 | 2024-10-07 | 1 | 별도메일접수 24-012 | 2024-12-04 | RC | DHI-GUP-DT-22-121 | 2022-03-18 | 0 | CRS-GUP-DHI-DT-22-282 | 2022-04-07 | NC | DHI-GUP-DT-22-208 | 2022-05-10 | 1 | CRS-GUP-DHI-DT-22-383 | 2022-06-02 | NC | DE-GUP-DT-E-22-494 | 2022-08-11 | C | CRS-GUP-DHI-DT-22-770 | 2022-09-15 | RC | DE-GUP-DT-E-22-1195 | 2022-12-26 | D | CRS-GUP-DHI-DT-23-1435 | 2023-01-31 | RC | DE-GUP-DT-E-23-241 | 2023-02-24 | E | CRS-GUP-DHI-DT-23-1747 | 2023-03-18 | AA | DE-GUP-DT-E-23-787 | 2023-09-04 | 0 | 자체 CRS 개정 후 제출 | 2024-10-06 | N/A | DE-GUP-DT-E-24-243 | 2024-10-07 | 1 | 별도메일접수 24-012 | 2024-12-04 | RC
| GUP | CC05 | P5 | ZEN | 500004 |  | GUP-CC05-P5ZEN-500004 | Drawing for Mechanical_ULSD and LNG Pipeline | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  | P | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-24-232 | 2024-09-13 | F | 별도메일접수 24-006 | 2024-11-04 | RC | DHI-GUP-DT-22-122 | 2022-03-18 | 0 | CRS-GUP-DHI-DT-22-283 | 2022-04-07 | RC | DE-GUP-DT-E-22-259 | 2022-05-31 | B | CRS-GUP-DHI-DT-22-469 | 2022-06-22 | RC | DE-GUP-DT-E-22-1089 | 2022-12-16 | C | CRS-GUP-DHI-DT-23-1479 | 2023-02-11 | RC | DE-GUP-DT-E-23-368 | 2023-03-27 | D | CRS-GUP-DHI-DT-23-1842 | 2023-04-19 | RC | DE-GUP-DT-E-23-844 | 2023-10-11 | E | CRS-GUP-DHI-DT-23-2134 | 2023-11-17 | RC | DE-GUP-DT-E-24-232 | 2024-09-13 | F | 별도메일접수 24-006 | 2024-11-04 | RC
| GUP | CC05 | P5 | ZEN | 500003 |  | GUP-CC05-P5ZEN-500003 | Drawing for Structural_ULSD and LNG Pipeline | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  | P | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-24-111 | 2024-04-23 | 2 | 자체 CRS 개정 후 제출 | 2024-04-22 | N/A | DHI-GUP-DT-22-123 | 2022-03-18 | 0 | CRS-GUP-DHI-DT-22-284 | 2022-04-07 | RC | DE-GUP-DT-E-22-375 | 2022-07-08 | B | CRS-GUP-DHI-DT-22-578 | 2022-08-08 | RC | DE-GUP-DT-E-22-976 | 2022-11-23 | C | CRS-GUP-DHI-DT-22-1229 | 2022-12-13 | AC | DE-GUP-DT-E-22-1119 | 2022-12-19 | 0(CP) | CRS-GUP-DHI-DT-22-1411 | 2023-01-11 | AA | DE-GUP-DT-E-23-695 | 2023-07-18 | 1 | 자체 CRS 개정 후 제출 | 2024-04-22 | N/A | DE-GUP-DT-E-24-111 | 2024-04-23 | 2
| GUP | DP00 | P5 | ZEN | 500016 |  | GUP-DP00-P5ZEN-500016 | Specification for Architectural_ULSD and LNG Pipeline | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-25-053 | 2025-05-24 | 1 | CRS-GUP-DHI-DT-23-1436 | 2023-01-31 | AA | DHI-GUP-DT-22-118 | 2022-03-18 | A | CRS-GUP-DHI-DT-22-279 | 2022-04-07 | RC | DHI-GUP-DT-22-219 | 2022-05-13 | B | CRS-GUP-DHI-DT-22-399 | 2022-06-07 | AC | DE-GUP-DT-E-22-1207 | 2023-01-02 | 0(CP) | CRS-GUP-DHI-DT-23-1436 | 2023-01-31 | AA | DE-GUP-DT-E-25-053 | 2025-05-24 | 1
| GUP | VB00 | P5 | ZEN | 500015 |  | GUP-VB00-P5ZEN-500015 | Specification for Civil_ULSD and LNG Pipeline | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-23-502 | 2023-04-24 | 1 | CRS-GUP-DHI-DT-23-1942 | 2023-05-11 | AA | DHI-GUP-DT-22-120 | 2022-03-18 | A | CRS-GUP-DHI-DT-22-281 | 2022-04-07 | RC | DE-GUP-DT-E-22-244 | 2022-05-24 | B | CRS-GUP-DHI-DT-22-417 | 2022-06-13 | RC | DE-GUP-DT-E-22-418 | 2022-07-19 | C | CRS-GUP-DHI-DT-22-589 | 2022-08-08 | RC | DE-GUP-DT-E-22-557 | 2022-08-25 | D | CRS-GUP-DHI-DT-22-754 | 2022-09-12 | AC | DE-GUP-DT-E-23-203 | 2023-02-20 | 0(CP) | CRS-GUP-DHI-DT-23-1670 | 2023-03-10 | AA | DE-GUP-DT-E-23-502 | 2023-04-24 | 1 | CRS-GUP-DHI-DT-23-1942 | 2023-05-11 | AA
| GUP | YR02 | P5 | ZEN | 500019 |  | GUP-YR02-P5ZEN-500019 | Specification for Electrical_ULSD and LNG Pipeline | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-24-162 | 2024-06-24 | 0 | 별도메일접수 24-002 | 2024-08-23 | AA | DHI-GUP-DT-22-121 | 2022-03-18 | A | CRS-GUP-DHI-DT-22-282 | 2022-04-07 | RC | DHI-GUP-DT-22-208 | 2022-05-10 | B | CRS-GUP-DHI-DT-22-383 | 2022-06-02 | RC | DE-GUP-DT-E-22-494 | 2022-08-11 | C | CRS-GUP-DHI-DT-22-770 | 2022-09-15 | RC | DE-GUP-DT-E-22-1195 | 2022-12-26 | D | CRS-GUP-DHI-DT-23-1435 | 2023-01-31 | RC | DE-GUP-DT-E-23-241 | 2023-02-24 | E | CRS-GUP-DHI-DT-23-1747 | 2023-03-18 | AA | DE-GUP-DT-E-24-162 | 2024-06-24 | 0 | 별도메일접수 24-002 | 2024-08-23 | AA
| GUP | DP00 | P5 | ZEN | 500018 |  | GUP-DP00-P5ZEN-500018 | Specification for Mechanical_ULSD and LNG Pipeline | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-24-232 | 2024-09-13 | F | 별도메일접수 24-006 | 2024-11-04 | RC | DHI-GUP-DT-22-122 | 2022-03-18 | A | CRS-GUP-DHI-DT-22-283 | 2022-04-07 | RC | DE-GUP-DT-E-22-259 | 2022-05-31 | B | CRS-GUP-DHI-DT-22-469 | 2022-06-22 | RC | DE-GUP-DT-E-22-1089 | 2022-12-16 | C | CRS-GUP-DHI-DT-23-1479 | 2023-02-11 | RC | DE-GUP-DT-E-23-368 | 2023-03-27 | D | CRS-GUP-DHI-DT-23-1842 | 2023-04-19 | RC | DE-GUP-DT-E-23-844 | 2023-10-11 | E | CRS-GUP-DHI-DT-23-2134 | 2023-11-17 | RC | DE-GUP-DT-E-24-232 | 2024-09-13 | F | 별도메일접수 24-006 | 2024-11-04 | RC
| GUP | DP00 | P5 | ZEN | 500017 |  | GUP-DP00-P5ZEN-500017 | Specification for Structural_ULSD and LNG Pipeline | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-25-055 | 2025-05-24 | 1 | CRS-GUP-DHI-DT-22-1411 | 2023-01-11 | AA | DHI-GUP-DT-22-123 | 2022-03-18 | A | CRS-GUP-DHI-DT-22-284 | 2022-04-07 | RC | DE-GUP-DT-E-22-375 | 2022-07-08 | B | CRS-GUP-DHI-DT-22-578 | 2022-08-08 | RC | DE-GUP-DT-E-22-976 | 2022-11-23 | C | CRS-GUP-DHI-DT-22-1229 | 2022-12-13 | AC | DE-GUP-DT-E-22-1119 | 2022-12-19 | 0(CP) | CRS-GUP-DHI-DT-22-1411 | 2023-01-11 | AA | DE-GUP-DT-E-25-055 | 2025-05-24 | 1
| GUP | CC05 | P5 | ZEN | 500020 |  | GUP-CC05-P5ZEN-500020 | Drawing for Potable Water Utility Piping | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  | P | G | FA | Utility Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-23-629 | 2023-06-19 | 1 | CRS-GUP-DHI-DT-23-1775 | 2023-03-27 | AA | DHI-GUP-DT-22-108 | 2022-03-08 | 0 | CRS-GUP-DHI-DT-22-270 | 2022-03-29 | RC | DE-GUP-DT-E-22-1063 | 2022-12-09 | B | CRS-GUP-DHI-DT-22-1373 | 2022-12-31 | RC | DE-GUP-DT-E-23-276 | 2023-03-07 | C | CRS-GUP-DHI-DT-23-1775 | 2023-03-27 | AA | DE-GUP-DT-E-23-629 | 2023-06-19 | 1
| GUP | CC05 | P5 | ZEN | 500021 |  | GUP-CC05-P5ZEN-500021 | Drawing for Sewer Utility Piping | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  | P | G | FA | Utility Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-24-060 | 2024-02-29 | 3 | CRS-GUP-DHI-DT-24-048 | 2024-04-15 | AC | DHI-GUP-DT-22-108 | 2022-03-08 | 0 | CRS-GUP-DHI-DT-22-270 | 2022-03-29 | RC | DE-GUP-DT-E-22-1146 | 2022-12-22 | B | CRS-GUP-DHI-DT-22-1407 | 2023-01-07 | AC | DE-GUP-DT-E-23-629 | 2023-06-19 | 1 | CRS-GUP-DHI-DT-23-2080 | 2023-07-27 | AC | DE-GUP-DT-E-23-832 | 2023-09-27 | 2 | CRS-GUP-DHI-DT-23-2132 | 2023-11-01 | AC | DE-GUP-DT-E-24-060 | 2024-02-29 | 3 | CRS-GUP-DHI-DT-24-048 | 2024-04-15 | AC
| GUP | VH00 | P5 | ZEN | 570002 |  | GUP-VH00-P5ZEN-570002 | Basis of Design for Potable Water Utility Piping | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  |  | G | FA | Utility Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-25-079 | 2025-07-04 | 0 | CRS-GUP-DHI-DT-23-1775 | 2023-03-27 | AA | DHI-GUP-DT-22-108 | 2022-03-08 | 0 | CRS-GUP-DHI-DT-22-270 | 2022-03-29 | RC | DE-GUP-DT-E-22-1063 | 2022-12-09 | B | CRS-GUP-DHI-DT-22-1373 | 2022-12-31 | RC | DE-GUP-DT-E-23-276 | 2023-03-07 | C | CRS-GUP-DHI-DT-23-1775 | 2023-03-27 | AA | DE-GUP-DT-E-25-079 | 2025-07-04 | 0
| GUP | VH00 | P5 | ZEN | 570003 |  | GUP-VH00-P5ZEN-570003 | Basis of Design for Sewer Utility Piping | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  |  | G | FA | Utility Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-25-079 | 2025-07-04 | 0 | CRS-GUP-DHI-DT-22-1407 | 2023-01-07 | AA | DHI-GUP-DT-22-108 | 2022-03-08 | 0 | CRS-GUP-DHI-DT-22-270 | 2022-03-29 | RC | DE-GUP-DT-E-22-1146 | 2022-12-22 | B | CRS-GUP-DHI-DT-22-1407 | 2023-01-07 | AA | DE-GUP-DT-E-25-079 | 2025-07-04 | 0
| GUP | VH00 | P5 | ZEN | 570004 |  | GUP-VH00-P5ZEN-570004 | Basis of Design for Grey Water Line | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  |  | G | FA | Utility Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-24-086 | 2024-07-08 | 1 | 별도메일접수 24-010 | 2024-10-25 | RC | DHI-GUP-DT-22-125 | 2022-03-21 | 0 | CRS-GUP-DHI-DT-22-286 | 2022-04-07 | RC | DE-GUP-DT-E-22-589 | 2022-08-31 | B | CRS-GUP-DHI-DT-22-734 | 2022-09-09 | RC | DE-GUP-DT-E-23-148 | 2023-02-09 | C | CRS-GUP-DHI-DT-23-1666 | 2023-03-09 | AC | DE-GUP-DT-E-23-964 | 2023-12-01 | 0(CP) | CRS-GUP-DHI-DT-24-010 | 2024-02-06 | RC | DE-GUP-DT-E-24-086 | 2024-07-08 | 1 | 별도메일접수 24-010 | 2024-10-25 | RC
| GUP | CC05 | P5 | ZEN | 570006 |  | GUP-CC05-P5ZEN-570006 | Drawing for Grey Water Line | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  | P | G | FA | Utility Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-24-291 | 2024-12-10 | 5 | 별도 메일접수 25-013 | 2025-03-14 | RC | DHI-GUP-DT-22-125 | 2022-03-21 | 0 | CRS-GUP-DHI-DT-22-286 | 2022-04-07 | RC | DE-GUP-DT-E-22-589 | 2022-08-31 | B | CRS-GUP-DHI-DT-22-734 | 2022-09-09 | RC | DE-GUP-DT-E-23-148 | 2023-02-09 | C | CRS-GUP-DHI-DT-23-1666 | 2023-03-09 | AC | DE-GUP-DT-E-23-629 | 2023-06-19 | 1 | CRS-GUP-DHI-DT-23-2080 | 2023-07-27 | AC | DE-GUP-DT-E-23-836 | 2023-09-27 | 2 | CRS-GUP-DHI-DT-23-2126 | 2023-10-27 | AC | DE-GUP-DT-E-23-964 | 2023-12-01 | 3 | CRS-GUP-DHI-DT-24-010 | 2024-02-06 | RC | DE-GUP-DT-E-24-086 | 2024-07-08 | 4 | 별도메일접수 24-010 | 2024-10-25 | RC | DE-GUP-DT-E-24-291 | 2024-12-10 | 5 | 별도 메일접수 25-013 | 2025-03-14 | RC
| GUP | CC07 | P5 | ZEN | 570007 |  | GUP-CC07-P5ZEN-570007 | Calculation for Grey Water Line | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  |  | G | FA | Utility Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-24-086 | 2024-07-08 | 1 | 별도메일접수 24-010 | 2024-10-25 | RC | DE-GUP-DT-E-23-148 | 2023-02-09 | A | CRS-GUP-DHI-DT-23-1666 | 2023-03-09 | AA | DE-GUP-DT-E-23-964 | 2023-12-01 | 0 | CRS-GUP-DHI-DT-24-010 | 2024-02-06 | RC | DE-GUP-DT-E-24-086 | 2024-07-08 | 1 | 별도메일접수 24-010 | 2024-10-25 | RC
| GUP | DP00 | P5 | ZEN | 570013 |  | GUP-DP00-P5ZEN-570013 | Specification for Grey Waterline (Re-Used Water) | FA | 2024-03-31 | 2024-06-30 | EM | 신효철 |  |  | G | FA | Utility Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-24-086 | 2024-07-08 | A | 별도메일접수 24-010 | 2024-10-25 | RC | DE-GUP-DT-E-24-086 | 2024-07-08 | A | 별도메일접수 24-010 | 2024-10-25 | RC
| GUP | CC07 | P5 | ZEN | 570009 |  | GUP-CC07-P5ZEN-570009 | Calculation for Sewer Utility Piping | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  |  | G | FA | Utility Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-25-079 | 2025-07-04 | 0 | CRS-GUP-DHI-DT-22-1407 | 2023-01-07 | AA | DHI-GUP-DT-22-108 | 2022-03-08 | 0 | CRS-GUP-DHI-DT-22-270 | 2022-03-29 | RC | DE-GUP-DT-E-22-1146 | 2022-12-22 | B | CRS-GUP-DHI-DT-22-1407 | 2023-01-07 | AA | DE-GUP-DT-E-25-079 | 2025-07-04 | 0
| GUP | DP00 | P5 | ZEN | 570012 |  | GUP-DP00-P5ZEN-570012 | Specification for Potable Water & Sewer Utility Piping | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  |  | G | FA | Utility Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-25-079 | 2025-07-04 | 0 | CRS-GUP-DHI-DT-23-1775 | 2023-03-27 | AA | DHI-GUP-DT-22-108 | 2022-03-08 | A | CRS-GUP-DHI-DT-22-270 | 2022-03-29 | RC | DE-GUP-DT-E-22-1063 | 2022-12-09 | B | CRS-GUP-DHI-DT-22-1373 | 2022-12-31 | RC | DE-GUP-DT-E-23-276 | 2023-03-07 | C | CRS-GUP-DHI-DT-23-1775 | 2023-03-27 | AA | DE-GUP-DT-E-25-079 | 2025-07-04 | 0
| GUP | YR02 | P5 | ZEN | 500022 |  | GUP-YR02-P5ZEN-500022 | Technical Specification for PIMS(Piping Integrity Management System)_ULSD and LNG Pipeline | FA | 2022-06-30 | 2022-09-30 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-22-1124 | 2022-12-19 | 0 | CRS-GUP-DHI-DT-23-1500 | 2023-02-14 | AA | DE-GUP-DT-E-22-309 | 2022-06-16 | A | CRS-GUP-DHI-DT-22-570 | 2022-08-02 | RC | DE-GUP-DT-E-22-517 | 2022-08-19 | B | CRS-GUP-DHI-DT-22-837 | 2022-09-23 | AA | DE-GUP-DT-E-22-1124 | 2022-12-19 | 0 | CRS-GUP-DHI-DT-23-1500 | 2023-02-14 | AA
| GUP | YR02 | P5 | ZEN | 500023 |  | GUP-YR02-P5ZEN-500023 | Technical Specification for LDS(Leak Detection System)_ULSD and LNG Pipeline | FA | 2022-06-30 | 2022-09-30 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-24-198 | 2024-08-09 | 3 | CRS-GUP-DHI-DT-24-015 | 2024-02-15 | AA | DE-GUP-DT-E-22-832 | 2022-10-20 | A | CRS-GUP-DHI-DT-22-1010 | 2022-11-13 | RC | DE-GUP-DT-E-22-1147 | 2022-12-22 | B | CRS-GUP-DHI-DT-23-1491 | 2023-02-11 | RC | DE-GUP-DT-E-23-369 | 2023-03-27 | C | CRS-GUP-DHI-DT-23-1818 | 2023-04-12 | RC | DE-GUP-DT-E-23-727 | 2023-07-28 | D | CRS-GUP-DHI-DT-23-2096 | 2023-08-21 | AC | DE-GUP-DT-E-23-872 | 2023-10-27 | 0 | CRS-GUP-DHI-DT-23-2139 | 2023-11-17 | AC | DE-GUP-DT-E-23-974 | 2023-12-05 | 1 | CRS-GUP-DHI-DT-24-008 | 2024-01-25 | AC | DE-GUP-DT-E-24-041 | 2024-02-08 | 2 | CRS-GUP-DHI-DT-24-015 | 2024-02-15 | AA | DE-GUP-DT-E-24-198 | 2024-08-09 | 3
| GUP | DC01 | P5 | ZEN | 720006 |  | GUP-DC01-P5ZEN-720006 | Datasheet for Water Utility Piping, Fitting and Accessories | FA | 2022-05-30 | 2022-07-31 | EM | 신효철 |  |  | G | FA | Utility Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-22-247 | 2022-05-25 | 0 | CRS-GUP-DHI-DT-22-449 | 2022-06-17 | NC | DHI-GUP-DT-22-172 | 2022-04-13 | 0 | CRS-GUP-DHI-DT-22-357 | 2022-05-22 | NC | DE-GUP-DT-E-22-247 | 2022-05-25 | 0 | CRS-GUP-DHI-DT-22-449 | 2022-06-17 | NC
| GUP | DC01 | P5 | ZEN | 550006 |  | GUP-DC01-P5ZEN-550006 | Datasheet for Fiber Optic Splice Closure_ULSD and LNG Pipeline | FA | 2022-05-30 | 2022-07-31 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-23-014 | 2023-01-12 | 2 | CRS-GUP-DHI-DT-23-1586 | 2023-02-28 | AA | DHI-GUP-DT-22-148 | 2022-04-04 | 0 | CRS-GUP-DHI-DT-22-315 | 2022-05-02 | NC | DE-GUP-DT-E-22-337 | 2022-06-24 | 0 | N/A | N/A | N/A | DE-GUP-DT-E-22-991 | 2022-11-25 | 1 | CRS-GUP-DHI-DT-22-1359 | 2022-12-29 | RC | DE-GUP-DT-E-23-014 | 2023-01-12 | 2 | CRS-GUP-DHI-DT-23-1586 | 2023-02-28 | AA
| GUP | DC01 | P5 | EGA | 540001 |  | GUP-DC01-P5EGA-540001 | Datasheet for Pipe Materials inc. fitting - ERW_ULSD and LNG Pipeline | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-24-223 | 2024-09-06 | 3 | 자체 CRS 개정 후 제출 | 2024-09-05 | N/A | DHI-GUP-DT-22-137 | 2022-03-28 | 0 | N/A | 2022-05-18 | N/A | DE-GUP-DT-E-22-225 | 2022-05-19 | B | CRS-GUP-DHI-DT-22-375 | 2022-05-30 | RC | DE-GUP-DT-E-22-273 | 2022-06-03 | C | CRS-GUP-DHI-DT-22-473 | 2022-06-27 | RC | DE-GUP-DT-E-22-346 | 2022-06-29 | D | CRS-GUP-DHI-DT-22-820 | 2022-09-22 | RC | DE-GUP-DT-E-22-1024 | 2022-12-02 | E | CRS-GUP-DHI-DT-22-1283 | 2022-12-21 | AA | DE-GUP-DT-E-22-1160 | 2022-12-22 | 0 | CRS-GUP-DHI-DT-23-1504 | 2023-02-14 | AA | DE-GUP-DT-E-24-037 | 2024-02-07 | 1 | 자체 CRS 개정 후 제출 | 2024-03-07 | N/A | DE-GUP-DT-E-24-070 | 2024-03-08 | 2 | 자체 CRS 개정 후 제출 | 2024-09-05 | N/A | DE-GUP-DT-E-24-223 | 2024-09-06 | 3
| GUP | DC01 | P5 | EGA | 540002 |  | GUP-DC01-P5EGA-540002 | Datasheet for Pipe Coating_ULSD and LNG Pipeline | FA | 2022-03-31 | 2022-07-31 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-22-1125 | 2022-12-19 | 0 | CRS-GUP-DHI-DT-22-588 | 2022-08-08 | AA | DHI-GUP-DT-22-137 | 2022-03-28 | 0 | N/A | 2022-05-18 | N/A | DE-GUP-DT-E-22-225 | 2022-05-19 | B | CRS-GUP-DHI-DT-22-375 | 2022-05-30 | RC | DE-GUP-DT-E-22-417 | 2022-07-19 | C | CRS-GUP-DHI-DT-22-588 | 2022-08-08 | AA | DE-GUP-DT-E-22-1125 | 2022-12-19 | 0
| GUP | DC01 | P5 | EGA | 550001 |  | GUP-DC01-P5EGA-550001 | Datasheet for Cathodic System_ULSD and LNG Pipeline | FA | 2022-05-30 | 2022-07-31 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-24-146 | 2024-06-04 | 1 | CRS-GUP-DHI-DT-23-1500 | 2023-02-14 | AA | DHI-GUP-DT-22-189 | 2022-04-27 | A | N/A | 2022-06-28 | N/A | DE-GUP-DT-E-22-348 | 2022-06-29 | B | CRS-GUP-DHI-DT-22-483 | 2022-07-03 | AA | DE-GUP-DT-E-22-599 | 2022-08-31 | C | CRS-GUP-DHI-DT-22-865 | 2022-09-26 | AA | DE-GUP-DT-E-22-1124 | 2022-12-19 | 0 | CRS-GUP-DHI-DT-23-1500 | 2023-02-14 | AA | DE-GUP-DT-E-24-146 | 2024-06-04 | 1
| GUP | DC01 | P5 | EGA | 550002 |  | GUP-DC01-P5EGA-550002 | Datasheet for FO Cable_ULSD and LNG Pipeline | FA | 2022-05-30 | 2022-07-31 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-24-207 | 2024-08-22 | 1 | CRS-GUP-DHI-DT-24-089 | 2024-10-09 | AA | DHI-GUP-DT-22-188 | 2022-04-26 | A | CRS-GUP-DHI-DT-22-358 | 2022-05-22 | RR | DE-GUP-DT-E-22-255 | 2022-05-27 | B | CRS-GUP-DHI-DT-22-428 | 2022-06-14 | RC | DE-GUP-DT-E-22-310 | 2022-06-16 | C | CRS-GUP-DHI-DT-22-511 | 2022-07-12 | AA | DE-GUP-DT-E-22-1124 | 2022-12-19 | 0 | CRS-GUP-DHI-DT-23-1500 | 2023-02-14 | AA | DE-GUP-DT-E-24-207 | 2024-08-22 | 1 | CRS-GUP-DHI-DT-24-089 | 2024-10-09 | AA
| GUP | DC01 | P5 | EGA | 550004 |  | GUP-DC01-P5EGA-550004 | Datasheet for Conduit Fitting_ULSD and LNG Pipeline | FA | 2022-06-30 | 2022-09-30 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-23-908 | 2023-11-13 | 1 | 메일로 회신-CRS 파일 없음 | 2022-12-09 | AA | DE-GUP-DT-E-22-308 | 2022-06-16 | A | 메일로 회신-CRS 파일 없음 | 2022-12-09 | AA | DE-GUP-DT-E-23-390 | 2023-03-29 | 0 | N/A | N/A | N/A | DE-GUP-DT-E-23-908 | 2023-11-13 | 1
| GUP | DC01 | P5 | EGA | 540005 |  | GUP-DC01-P5EGA-540005 | Datasheet for Valve_ULSD and LNG Pipeline | FA | 2022-06-30 | 2022-09-30 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-25-081 | 2025-07-04 | 1 | CRS-GUP-DHI-DT-23-1989 | 2023-06-13 | AA | DE-GUP-DT-E-22-1055 | 2022-12-08 | A | CRS-GUP-DHI-DT-22-1321 | 2022-12-22 | RC | DE-GUP-DT-E-23-099 | 2023-01-31 | B | CRS-GUP-DHI-DT-23-1647 | 2023-03-07 | AC | DE-GUP-DT-E-23-550 | 2023-05-15 | 0(CP) | CRS-GUP-DHI-DT-23-1989 | 2023-06-13 | AA | DE-GUP-DT-E-25-081 | 2025-07-04 | 1
| GUP | DC01 | P5 | EGA | 550005 |  | GUP-DC01-P5EGA-550005 | Datasheet for Panel_ULSD and LNG Pipeline | FA | 2022-06-30 | 2022-09-30 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-24-085 | 2024-03-21 | 1 | 자체 CRS 개정 후 제출 | 2024-03-20 | N/A | DE-GUP-DT-E-23-325 | 2023-03-17 | A | CRS-GUP-DHI-DT-23-1799 | 2023-04-04 | RC | DE-GUP-DT-E-23-567 | 2023-05-19 | B | CRS-GUP-DHI-DT-23-2035 | 2023-07-06 | AA | DE-GUP-DT-E-23-721 | 2023-07-25 | 0 | 자체 CRS 개정 후 제출 | 2024-03-20 | N/A | DE-GUP-DT-E-24-085 | 2024-03-21 | 1
| GUP | CC05 | P5 | ZEN | 500006 |  | GUP-CC05-P5ZEN-500006 | Drawing for Corrosion and Erosion Monitoring System for PIMS (Pipeline Integrity Management System)_ULSD and LNG Pipeline | FA | 2022-08-01 | 2022-09-30 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-25-084 | 2025-07-04 | 2 | CRS-GUP-DHI-DT-24-029 | 2024-03-11 | AA | DE-GUP-DT-E-22-831 | 2022-10-20 | A | CRS-GUP-DHI-DT-22-1251 | 2022-12-13 | RC | DE-GUP-DT-E-23-069 | 2023-01-20 | B | CRS-GUP-DHI-DT-23-1661 | 2023-03-09 | RC | DE-GUP-DT-E-23-370 | 2023-03-27 | C | CRS-GUP-DHI-DT-23-1843 | 2023-04-19 | AC | DE-GUP-DT-E-23-625 | 2023-06-16 | 0(cp) | CRS-GUP-DHI-DT-23-2093 | 2023-08-16 | AC | DE-GUP-DT-E-23-873 | 2023-10-27 | 1(CP) | CRS-GUP-DHI-DT-24-029 | 2024-03-11 | AA | DE-GUP-DT-E-25-084 | 2025-07-04 | 2
| GUP | CC05 | P5 | ZEN | 500007 |  | GUP-CC05-P5ZEN-500007 | Drawing for Power Supply System for PIMS (Pipeline Integrity Management System)_ULSD and LNG Pipeline | FA | 2022-08-30 | 2022-10-29 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-25-082 | 2025-07-04 | 2 | CRS-GUP-DHI-DT-24-029 | 2024-03-11 | AA | DE-GUP-DT-E-22-831 | 2022-10-20 | A | CRS-GUP-DHI-DT-22-1251 | 2022-12-13 | RC | DE-GUP-DT-E-23-069 | 2023-01-20 | B | CRS-GUP-DHI-DT-23-1661 | 2023-03-09 | RC | DE-GUP-DT-E-23-370 | 2023-03-27 | C | CRS-GUP-DHI-DT-23-1843 | 2023-04-19 | AC | DE-GUP-DT-E-23-625 | 2023-06-16 | 0(cp) | CRS-GUP-DHI-DT-23-2093 | 2023-08-16 | AC | DE-GUP-DT-E-23-873 | 2023-10-27 | 1(CP) | CRS-GUP-DHI-DT-24-029 | 2024-03-11 | AA | DE-GUP-DT-E-25-082 | 2025-07-04 | 2
| GUP | CC05 | P5 | ZEN | 500008 |  | GUP-CC05-P5ZEN-500008 | Drawing for Leak Detection System _ULSD and LNG Pipeline | FA | 2022-08-30 | 2022-10-29 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-23-504 | 2023-04-25 | 0 | CRS-GUP-DHI-DT-23-1925 | 2023-05-05 | AA | DE-GUP-DT-E-23-211 | 2023-02-21 | A | CRS-GUP-DHI-DT-23-1696 | 2023-03-14 | RC | DE-GUP-DT-E-23-371 | 2023-03-27 | B | CRS-GUP-DHI-DT-23-1844 | 2023-04-19 | AA | DE-GUP-DT-E-23-504 | 2023-04-25 | 0 | CRS-GUP-DHI-DT-23-1925 | 2023-05-05 | AA
| GUP | CC05 | P5 | ZEN | 500009 |  | GUP-CC05-P5ZEN-500009 | Drawing for Metering_ULSD and LNG Pipeline | FA | 2022-09-30 | 2022-11-29 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-24-147 | 2024-06-05 | B | 별도메일접수 24-003 | 2024-09-02 | RC | DE-GUP-DT-E-23-162 | 2023-02-13 | A | CRS-GUP-DHI-DT-23-1684 | 2023-03-13 | RC | DE-GUP-DT-E-24-147 | 2024-06-05 | B | 별도메일접수 24-003 | 2024-09-02 | RC
| GUP | DC01 | P5 | EGA | 550006 |  | GUP-DC01-P5EGA-550006 | Datasheet for Power, Control and Instrument cable_ULSD and LNG Pipeline | FA | 2022-08-15 | 2022-10-14 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-25-0780 | 2025-07-04 | 0 | CRS-GUP-DHI-DT-24-070 | 2024-08-16 | AA | DE-GUP-DT-E-23-643 | 2023-06-27 | A | CRS-GUP-DHI-DT-23-2072 | 2023-07-27 | RC | DE-GUP-DT-E-24-171 | 2024-07-01 | B | CRS-GUP-DHI-DT-24-070 | 2024-08-16 | AA | DE-GUP-DT-E-25-0780 | 2025-07-04 | 0
| GUP | DC01 | P5 | EGA | 550007 |  | GUP-DC01-P5EGA-550007 | Datasheet for grounding and bonding_ULSD and LNG Pipeline | FA | 2022-08-15 | 2022-10-14 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-23-723 | 2023-07-26 | 1 | 자체 CRS 개정 후 제출 | 2023-07-25 | N/A | DE-GUP-DT-E-22-890 | 2022-10-31 | A | CRS-GUP-DHI-DT-22-1208 | 2022-11-30 | RC | DE-GUP-DT-E-22-1154 | 2022-12-22 | B | CRS-GUP-DHI-DT-23-1468 | 2023-02-09 | AA | DE-GUP-DT-E-23-314 | 2023-03-15 | 0 | 자체 CRS 개정 후 제출 | 2023-07-25 | N/A | DE-GUP-DT-E-23-723 | 2023-07-26 | 1
| GUP | DC01 | P5 | EGA | 550008 |  | GUP-DC01-P5EGA-550008 | Datasheet for Leak Detection System_ULSD and LNG Pipeline | FA | 2022-08-30 | 2022-10-29 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-24-061 | 2024-02-29 | 0 | CRS-GUP-DHI-DT-24-043 | 2024-03-20 | AA | DE-GUP-DT-E-23-444 | 2023-04-10 | A | CRS-GUP-DHI-DT-23-1887 | 2023-05-02 | RC | DE-GUP-DT-E-23-693 | 2023-07-18 | B | CRS-GUP-DHI-DT-23-2087 | 2023-08-08 | RC | DE-GUP-DT-E-23-874 | 2023-10-27 | C | CRS-GUP-DHI-DT-23-2140 | 2023-11-17 | AA | DE-GUP-DT-E-24-061 | 2024-02-29 | 0 | CRS-GUP-DHI-DT-24-043 | 2024-03-20 | AA
| GUP | DC01 | P5 | EGA | 550009 |  | GUP-DC01-P5EGA-550009 | Datasheet for Lighting and Small Power_ULSD and LNG Pipeline | FA | 2022-08-15 | 2022-10-14 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-23-314 | 2023-03-15 | 0 | CRS-GUP-DHI-DT-23-1468 | 2023-02-09 | AA | DE-GUP-DT-E-22-890 | 2022-10-31 | A | CRS-GUP-DHI-DT-22-1208 | 2022-11-30 | RC | DE-GUP-DT-E-22-1154 | 2022-12-22 | B | CRS-GUP-DHI-DT-23-1468 | 2023-02-09 | AA | DE-GUP-DT-E-23-314 | 2023-03-15 | 0
| GUP | DC01 | P5 | EGA | 550010 |  | GUP-DC01-P5EGA-550010 | Datasheet for Metering System_ULSD and LNG Pipeline | FA | 2022-09-30 | 2022-11-29 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-25-083 | 2025-07-04 | 0 | CRS-GUP-DHI-DT-23-1869 | 2023-04-20 | AC | DE-GUP-DT-E-22-1187 | 2022-12-23 | A | CRS-GUP-DHI-DT-23-1493 | 2023-02-11 | RC | DE-GUP-DT-E-23-372 | 2023-03-27 | B | CRS-GUP-DHI-DT-23-1869 | 2023-04-20 | AC | DE-GUP-DT-E-25-083 | 2025-07-04 | 0
| GUP | DC01 | P5 | EGA | 540006 |  | GUP-DC01-P5EGA-540006 | Datasheet for Pumps_ULSD and LNG Pipeline | FA | 2022-09-30 | 2022-11-29 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-23-302 | 2023-03-13 | A | CRS-GUP-DHI-DT-23-1795 | 2023-04-04 | RC | DE-GUP-DT-E-23-302 | 2023-03-13 | A | CRS-GUP-DHI-DT-23-1795 | 2023-04-04 | RC
| GUP | DC01 | P5 | EGA | 550013 |  | GUP-DC01-P5EGA-550013 | Datasheet for ULSD Pump Skid Local Control Panel_ULSD and LNG Pipeline | FA | 2024-04-15 | 2024-06-14 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-24-245 | 2024-10-07 | A | 별도메일접수 25-063 | 2025-05-20 | RC | DE-GUP-DT-E-24-245 | 2024-10-07 | A | 별도메일접수 25-063 | 2025-05-20 | RC
| GUP | YR02 | P5 | EGA | 500024 |  | GUP-YR02-P5EGA-500024 | Technical Specification for Metering System _ULSD and LNG Pipeline | FA | 2022-09-30 | 2022-11-29 | EM | 신효철 |  |  | G | FA | Fuel Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-24-275 | 2024-11-19 | B | CRS-GUP-DHI-DT-25-014 | 2025-02-04 | RC | DE-GUP-DT-E-24-089 | 2024-03-25 | A | CRS-GUP-DHI-DT-24-062 | 2024-07-04 | RC | DE-GUP-DT-E-24-275 | 2024-11-19 | B | CRS-GUP-DHI-DT-25-014 | 2025-02-04 | RC
| GUP | YK09 | P5 | ZEN | 520001 |  | GUP-YK09-P5ZEN-520001 | Drawing for Pump Skid_ULSD and LNG Pipeline | FA | 2022-09-30 | 2022-11-29 | EM | 신효철 |  |  | G | FA | Utility Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-24-244 | 2024-10-07 | 0 | 별도메일접수 24-004 | 2024-09-02 | AA | DE-GUP-DT-E-23-215 | 2023-02-21 | A | CRS-GUP-DHI-DT-23-1735 | 2023-03-17 | RC | DE-GUP-DT-E-23-359 | 2023-03-24 | B | CRS-GUP-DHI-DT-23-1833 | 2023-04-18 | RC | DE-GUP-DT-E-24-142 | 2024-05-29 | C | 별도메일접수 24-004 | 2024-09-02 | AA | DE-GUP-DT-E-24-244 | 2024-10-07 | 0
| GUP | DC01 | P5 | EGA | 540007 |  | GUP-DC01-P5EGA-540007 | Datasheet For Grey Water Pump_ULSD and LNG Pipeline | FA | 2022-09-30 | 2022-11-29 | EM | 신효철 |  |  | G | FA | Utility Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-23-508 | 2023-04-26 | 0 | CRS-GUP-DHI-DT-23-1731 | 2023-03-17 | AA | DE-GUP-DT-E-23-179 | 2023-02-15 | A | CRS-GUP-DHI-DT-23-1731 | 2023-03-17 | AA | DE-GUP-DT-E-23-508 | 2023-04-26 | 0
| GUP | DC01 | P5 | EGA | 570001 |  | GUP-DC01-P5EGA-570001 | Datasheet for Fiber Optic Handhole | FA | 2022-09-30 | 2022-11-29 | EM | 신효철 |  |  | G | FA | Utility Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-23-714 | 2023-07-24 | 0 | CRS-GUP-DHI-DT-23-2121 | 2023-10-19 | AA | DE-GUP-DT-E-23-531 | 2023-05-09 | A | CRS-GUP-DHI-DT-23-1959 | 2023-05-24 | RC | DE-GUP-DT-E-23-642 | 2023-06-27 | B | CRS-GUP-DHI-DT-23-2047 | 2023-07-14 | AA | DE-GUP-DT-E-23-714 | 2023-07-24 | 0 | CRS-GUP-DHI-DT-23-2121 | 2023-10-19 | AA
| GUP | YR02 | P5 | ZEN | 500024 |  | GUP-YR02-P5ZEN-500024 | Technical Specification for SCADA ULSD Pipeline | FA | 2023-06-30 | 2023-09-30 | EM | 신효철 |  |  | G | FI | Utility Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-25-067 | 2025-06-24 | F | FST-DUP-TR-25-069 | 2025-06-02 | RC | DE-GUP-DT-E-23-608 | 2023-06-07 | A | CRS-GUP-DHI-DT-23-2036 | 2023-07-06 | RC | DE-GUP-DT-E-24-084 | 2024-03-19 | B | CRS-GUP-DHI-DT-24-066 | 2024-08-05 | RC | DE-GUP-DT-E-24-255 | 2024-10-25 | C | 별도메일접수 24-018 | 2024-12-04 | RC | DE-GUP-DT-E-25-023 | 2025-02-11 | D | 별도 메일접수 25-012 | 2025-03-14 | RC | DE-GUP-DT-E-25-048 | 2025-04-21 | E | FST-DUP-TR-25-069 | 2025-06-02 | RC | DE-GUP-DT-E-25-067 | 2025-06-24 | F
| GUP | DC01 | P5 | EGA | 540008 |  | GUP-DC01-P5EGA-540008 | Datasheet for Submersible Sewage Pump | FA | 2023-08-30 | 2023-10-29 | EM | 신효철 |  |  | G | FA | Utility Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-23-728 | 2023-07-28 | A | CRS-GUP-DHI-DT-23-2105 | 2023-09-13 | RC | DE-GUP-DT-E-23-728 | 2023-07-28 | A | CRS-GUP-DHI-DT-23-2105 | 2023-09-13 | RC
| GUP | DC01 | P5 | EGA | 550014 |  | GUP-DC01-P5EGA-550014 | Datasheet for Sewer Line Pump Local Control Panel | FA | 2024-04-15 | 2024-06-14 | EM | 신효철 |  |  | G | FA | Utility Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-24-156 | 2024-06-14 | A | 별도메일접수 24-014 | 2024-12-04 | RC | DE-GUP-DT-E-24-156 | 2024-06-14 | A | 별도메일접수 24-014 | 2024-12-04 | RC
| GUP | DC01 | P5 | EGA | 540015 |  | GUP-DC01-P5EGA-550015 | Datasheet for Instrument Sewer Line System | FA | 2024-04-15 | 2024-06-14 | EM | 신효철 |  |  | G | FA | Utility Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-25-057 | 2025-05-26 | B | 별도메일접수 24-007 | 2024-11-04 | RC | DE-GUP-DT-E-24-229 | 2024-09-13 | A | 별도메일접수 24-007 | 2024-11-04 | RC | DE-GUP-DT-E-25-057 | 2025-05-26 | B
| GUP | DC01 | P5 | EGA | 550011 |  | GUP-DC01-P5EGA-550011 | Datasheet for Control Panel Grey Water Line | FA | 2023-08-30 | 2023-10-29 | EM | 신효철 |  |  | G | FA | Utility Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-25-051 | 2025-05-24 | 0 | CRS-GUP-DHI-DT-24-072 | 2024-09-05 | AC | DE-GUP-DT-E-23-728 | 2023-07-28 | A | CRS-GUP-DHI-DT-23-2105 | 2023-09-13 | RC | DE-GUP-DT-E-24-149 | 2024-06-05 | B | CRS-GUP-DHI-DT-24-072 | 2024-09-05 | AC | DE-GUP-DT-E-25-051 | 2025-05-24 | 0
| GUP | DC01 | P5 | EGA | 550012 |  | GUP-DC01-P5EGA-550012 | Datasheet for Instrument Grey Water Line System | FA | 2023-08-30 | 2023-10-29 | EM | 신효철 |  |  | G | FA | Utility Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-25-051 | 2025-05-24 | 0 | CRS-GUP-DHI-DT-24-072 | 2024-09-05 | AC | DE-GUP-DT-E-23-728 | 2023-07-28 | A | CRS-GUP-DHI-DT-23-2105 | 2023-09-13 | RC | DE-GUP-DT-E-24-149 | 2024-06-05 | B | CRS-GUP-DHI-DT-24-072 | 2024-09-05 | AC | DE-GUP-DT-E-25-051 | 2025-05-24 | 0
| GUP | DC01 | P5 | EGA | 550016 |  | GUP-DC01-P5EGA-550016 | Datasheet for Panels_Grey Water Line (Re-Use Water) | FA | 2024-09-01 | 2024-10-31 | EM | 신효철 |  |  | G | FA | Utility Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-25-052 | 2025-05-24 | 0 | CRS-GUP-DHI-DT-24-090 | 2024-10-09 | AA | DE-GUP-DT-E-24-208 | 2024-08-23 | A | CRS-GUP-DHI-DT-24-090 | 2024-10-09 | AA | DE-GUP-DT-E-25-052 | 2025-05-24 | 0
| GUP | DC01 | P5 | EGA | 550017 |  | GUP-DC01-P5EGA-550017 | Datasheet for Lighting and Small Power_Grey Water Line (Re-Use Water) | FA | 2024-09-01 | 2024-10-31 | EM | 신효철 |  |  | G | FA | Utility Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-25-056 | 2025-05-24 | 0 | 별도메일접수 24-016 | 2024-12-04 | AA | DE-GUP-DT-E-24-219 | 2024-09-03 | A | 별도메일접수 24-016 | 2024-12-04 | AA | DE-GUP-DT-E-25-056 | 2025-05-24 | 0
| GUP | DC01 | P5 | EGA | 540009 |  | GUP-DC01-P5EGA-540009 | Datasheet for Airconditioning ULSD and LNG Pipeline and Grey Waterline (Re-Used Water) | FA | 2024-11-15 | 2025-01-14 | EM | 신효철 |  |  | G | FA | Utility Line | Fuel & Utility | Fuel & Utility Line | [5 empty] | DE-GUP-DT-E-24-261 | 2024-11-06 | A | CRS-GUP-DHI-DT-25-013 | 2025-02-04 | AA | DE-GUP-DT-E-24-261 | 2024-11-06 | A | CRS-GUP-DHI-DT-25-013 | 2025-02-04 | AA
| GUP | CC05 | P6 | ZEN | 670001 |  | GUP-CC05-P6ZEN-670001 | Basis of Design for Transmission Line Civil Work | FA | LATER | LATER | Doosan Ukudu Power LLC, Site | 김승호 |  |  | G | FA | OHTL | Transmission Line | Transmission Line | [5 empty] | DE-GUP-DT-E-23-525 | 2023-05-05 | 0 | CRS-GUP-DHI-DT-23-1964 | 2023-06-01 | AA | DE-GUP-DT-E-22-653 | 2022-09-08 | A | CRS-GUP-DHI-DT-22-818 | 2022-09-20 | RC | DE-GUP-DT-E-23-525 | 2023-05-05 | 0 | CRS-GUP-DHI-DT-23-1964 | 2023-06-01 | AA
| GUP | CC05 | P6 | ZEN | 650002 |  | GUP-CC05-P6ZEN-650002 | Basis of Design for Transmission Line Electrical Work | FA | LATER | LATER | Doosan Ukudu Power LLC, Site | 김승호 |  |  | G | FA | OHTL | Transmission Line | Transmission Line | [5 empty] | DE-GUP-DT-E-24-128 | 2024-05-07 | 1 | CRS-GUP-DHI-DT-23-1664 | 2023-03-09 | AA | DE-GUP-DT-E-22-653 | 2022-09-08 | A | CRS-GUP-DHI-DT-22-818 | 2022-09-20 | RC | DE-GUP-DT-E-22-927 | 2022-11-09 | B | CRS-GUP-DHI-DT-22-1184 | 2022-11-30 | AA | DE-GUP-DT-E-23-143 | 2023-02-08 | 0 | CRS-GUP-DHI-DT-23-1664 | 2023-03-09 | AA | DE-GUP-DT-E-24-128 | 2024-05-07 | 1
| GUP | CC05 | P6 | ZEN | 680003 |  | GUP-CC05-P6ZEN-680003 | Basis of Design for Transmission Line Structural Work | FA | LATER | LATER | Doosan Ukudu Power LLC, Site | 김승호 |  |  | G | FA | OHTL | Transmission Line | Transmission Line | [5 empty] | DE-GUP-DT-E-24-018 | 2024-01-22 | 1 | CRS-GUP-DHI-DT-23-1964 | 2023-06-01 | AA | DE-GUP-DT-E-22-653 | 2022-09-08 | A | CRS-GUP-DHI-DT-22-818 | 2022-09-20 | RC | DE-GUP-DT-E-23-525 | 2023-05-05 | 0 | CRS-GUP-DHI-DT-23-1964 | 2023-06-01 | AA | DE-GUP-DT-E-24-018 | 2024-01-22 | 1
| GUP | CC05 | P6 | ZEN | 650004 |  | GUP-CC05-P6ZEN-650004 | Drawing for Transmission Line Electrical Work | FA | LATER | LATER | Doosan Ukudu Power LLC, Site | 김승호 |  |  | G | FA | OHTL | Transmission Line | Transmission Line | [5 empty] | DE-GUP-DT-E-24-018 | 2024-01-22 | 1 | CRS-GUP-DHI-DT-23-1964 | 2023-06-01 | AA | DE-GUP-DT-E-22-653 | 2022-09-08 | A | CRS-GUP-DHI-DT-22-818 | 2022-09-20 | RC | DE-GUP-DT-E-22-927 | 2022-11-09 | B | CRS-GUP-DHI-DT-22-1184 | 2022-11-30 | RC | DE-GUP-DT-E-22-1062 | 2022-12-09 | C | CRS-GUP-DHI-DT-22-1380 | 2023-01-03 | RC | DE-GUP-DT-E-23-143 | 2023-02-08 | D | CRS-GUP-DHI-DT-23-1664 | 2023-03-09 | AA | DE-GUP-DT-E-23-525 | 2023-05-05 | 0 | CRS-GUP-DHI-DT-23-1964 | 2023-06-01 | AA | DE-GUP-DT-E-24-018 | 2024-01-22 | 1
| GUP | YR02 | P6 | ZEN | 650005 |  | GUP-YR02-P6ZEN-650005 | Specification for Transmission Line Electrical Work | FA | LATER | LATER | Doosan Ukudu Power LLC, Site | 김승호 |  |  | G | FA | OHTL | Transmission Line | Transmission Line | [5 empty] | DE-GUP-DT-E-23-143 | 2023-02-08 | 0 | CRS-GUP-DHI-DT-23-1664 | 2023-03-09 | AA | DE-GUP-DT-E-22-653 | 2022-09-08 | A | CRS-GUP-DHI-DT-22-818 | 2022-09-20 | RC | DE-GUP-DT-E-22-927 | 2022-11-09 | B | CRS-GUP-DHI-DT-22-1184 | 2022-11-30 | RC | DE-GUP-DT-E-22-1062 | 2022-12-09 | C | CRS-GUP-DHI-DT-22-1380 | 2023-01-03 | AA | DE-GUP-DT-E-23-143 | 2023-02-08 | 0 | CRS-GUP-DHI-DT-23-1664 | 2023-03-09 | AA
Formulas:
Issued date = IF([Issued date]="", "",MAX([Issued date],[Issued date],[Issued date],[Issued date],[Issued date],[Issued date],[Issued date],[Issued date],[Issued date],[Issued date],[Issued date],[Issued date],[Issued date],[Issued date],[Issued date]))
Issued date = IF([Issued date]="", "",MAX([Issued date],[Issued date],[Issued date],[Issued date],[Issued date, row below],[Issued date],[Issued date],[Issued date],[Issued date],[Issued date],[Issued date],[Issued date],[Issued date],[Issued date],[Issued date]))
Reply Date = IF([Reply Date]="", "",MAX([Reply Date],[Reply Date],[Reply Date],[Reply Date],[Reply Date],[Reply Date],[Reply Date],[Reply Date],[Reply Date],[Reply Date],[Reply Date],[Reply Date],[Reply Date],[Reply Date],[Reply Date]))
Reply Date = IF([Reply Date]="", "",MAX([Reply Date],[Reply Date],[Reply Date],[Reply Date, row below],[Reply Date],[Reply Date],[Reply Date],[Reply Date],[Reply Date],[Reply Date],[Reply Date],[Reply Date],[Reply Date],[Reply Date],[Reply Date]))
FC Issue = 120+[First Issue]
FC Issue = [First Issue]+60