## Generated Schedule
source_file | document_no | title | deliverable | equipment | system | building | itb_sources | rule_query | matched_rule | submission_type | matched_activity_id | matched_activity_name | matched_activity_wbs_path | matched_activity_start_date | matched_activity_finish_date | fa_earliest | fa_recommended | fa_latest | fc_earliest | fc_recommended | fc_latest | date_range_status | date_range_confidence | ntp_shift_days
itb_candidates |  | HRSG Performance and Operational Data | OPERATIONAL DATA | Heat Recovery Steam Generator |  |  | R&N_ITB:p82(score=0.80) ¦ R&N_ITB:p82, 83(score=0.82) ¦ R&N_ITB:p82, 83(score=0.81) ¦ R&N_ITB:p82, 83(score=0.83) | OPERATIONAL DATA for HRSG |  | FA | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-11-27 | 2024-12-27 | 2025-01-26 | 2025-02-10 | 2025-02-25 | 2025-03-12 | generated | 0.90 | 6210
itb_candidates |  | PERFORMANCE AND OPERATIONAL DATA | OPERATIONAL DATA | Heat Recovery Steam Generator |  |  | R&N_ITB:p79(score=0.76) ¦ R&N_ITB:p81(score=0.79) ¦ R&N_ITB:p82(score=0.80) ¦ R&N_ITB:p82, 83(score=0.82) | OPERATIONAL DATA for HRSG |  | FA | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-11-27 | 2024-12-27 | 2025-01-26 | 2025-02-10 | 2025-02-25 | 2025-03-12 | generated | 0.90 | 6210
itb_candidates |  | Condensate System | DESIGN CRITERIA |  | Condensate System |  | R&N_ITB:p81(score=0.81) | DESIGN CRITERIA for Condensate System | Water Treatment System | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
itb_candidates |  | DESIGN CRITERIA FOR FUEL GAS SUPPLY SYSTEM | DESIGN CRITERIA | Fuel Gas Package |  |  | R&N_ITB:p81(score=0.81) ¦ R&N_ITB:p81(score=0.79) ¦ R&N_ITB:p81(score=0.76) | DESIGN CRITERIA for FGP |  | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-06-06 | 2024-07-06 | 2024-08-05 | 2024-08-20 | 2024-09-04 | 2024-09-19 | generated | 0.90 | 6210
itb_candidates |  | DESIGN CRITERIA FOR STEAM AND BYPASS SYSTEM | DESIGN CRITERIA |  | STEAM AND BYPASS SYSTEM |  | R&N_ITB:p80, 81(score=0.81) ¦ R&N_ITB:p83(score=0.81) | DESIGN CRITERIA for STEAM AND BYPASS SYSTEM | Intake Screening System | FA | 1EF2510W00A01.1 | (Bypass System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Bypass System | 2007-04-02 | 2007-11-01 | 2024-04-16 | 2024-05-16 | 2024-06-15 | 2024-06-30 | 2024-07-15 | 2024-07-30 | generated | 0.90 | 6210
itb_candidates |  | CONDENSATE SYSTEM DESIGN CRITERIA | DESIGN CRITERIA | CONDENSATE SYSTEM |  |  | R&N_ITB:p80, 81(score=0.79) ¦ R&N_ITB:p81(score=0.81) | DESIGN CRITERIA for CONDENSATE SYSTEM | Water Treatment System | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
itb_candidates |  | DESIGN CRITERIA FOR CONDENSATE SYSTEM | DESIGN CRITERIA |  | CONDENSATE SYSTEM |  | R&N_ITB:p80, 81(score=0.80) ¦ R&N_ITB:p81(score=0.81) | DESIGN CRITERIA for CONDENSATE SYSTEM | Water Treatment System | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
itb_candidates |  | Design Criteria Condensate System | Design Criteria |  | Condensate System |  | R&N_ITB:p81(score=0.81) | Design Criteria for Condensate System | Water Treatment System | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
itb_candidates |  | GTG System Description Gas Turbine Instrumentation | SYSTEM DESCRIPTION | Gas Turbine Generator |  |  | R&N_ITB:p94(score=0.81) ¦ R&N_ITB:p94(score=0.79) ¦ R&N_ITB:p95(score=0.77) ¦ R&N_ITB:p95(score=0.81) | System Description for GTG |  | FA | 3CF1265W90A06 | (Air&Flue Gas System) Installation- I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Air and Flue Gas System | 2008-07-02 | 2008-07-15 | 2025-12-08 | 2026-01-07 | 2026-02-06 | 2026-02-21 | 2026-03-08 | 2026-03-23 | generated | 0.90 | 6210
itb_candidates |  | DESIGN CRITERIA FOR HVAC SYSTEM | DESIGN CRITERIA |  | HVAC SYSTEM |  | R&N_ITB:p83(score=0.81) | DESIGN CRITERIA for HVAC SYSTEM | Water Treatment System | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
itb_candidates |  | CONTROL SYSTEM DESCRIPTION | SYSTEM DESCRIPTION | Gas Turbine Generator |  |  | R&N_ITB:p95(score=0.81) | System Description for GTG |  | FA | 1CF1265W90A17.8 | (Control Oil) Installation- I&C | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Auxiliary System | 2008-05-03 | 2008-05-16 | 2025-10-09 | 2025-11-08 | 2025-12-08 | 2025-12-23 | 2026-01-07 | 2026-01-22 | generated | 0.90 | 6210
itb_candidates |  | HVAC Design Criteria- | Design Criteria |  | HVAC |  | R&N_ITB:p83(score=0.81) | Design Criteria for HVAC | Water Treatment System | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
itb_candidates |  | HRSG Pressure Part Arrangement of HRSG | ARRANGEMENT | Heat Recovery Steam Generator |  |  | R&N_ITB:p82, 83(score=0.81) | ARRANGEMENT for HRSG |  | FA | 3EF1600W00A02 | (HRSG #31/#32) HRSG Process, GA Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | 2007-03-01 | 2007-03-30 | 2024-05-27 | 2024-06-26 | 2024-07-26 | 2024-08-10 | 2024-08-25 | 2024-09-09 | generated | 0.90 | 6210
itb_candidates |  | HVAC Design Criteria | Design Criteria |  | HVAC |  | R&N_ITB:p83(score=0.80) ¦ R&N_ITB:p83(score=0.80) ¦ R&N_ITB:p83(score=0.80) | Design Criteria for HVAC | Water Treatment System | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
itb_candidates |  | PERFORMANCE TEST PROCEDURE FOR NOISE EMISSION | PROCEDURE |  |  |  | R&N_ITB:p85(score=0.80) | PROCEDURE |  | FA | 1SF9042W62A15 | (Comm'g) Performance Test (Fuel Gas & Fuel Oil) | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | 2009-08-20 | 2009-08-31 | 2027-08-20 | 2027-09-10 | 2027-10-01 | 2027-10-25 | 2027-11-09 | 2027-11-24 | generated | 0.90 | 6210
itb_candidates |  | CONTROL SYSTEM OVERVIEW | OVERVIEW | Gas Turbine Generator |  |  | R&N_ITB:p95(score=0.80) | OVERVIEW for GTG |  | FA | 1SF1265W62A18 | (Control Oil) Loop chek | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | 2008-05-17 | 2008-05-21 | 2025-09-13 | 2025-10-13 | 2025-11-12 | 2025-11-27 | 2025-12-12 | 2025-12-27 | generated | 0.90 | 6210
itb_candidates |  | STG Design Criteria | DESIGN CRITERIA | Steam Turbine & Generator |  |  | R&N_ITB:p79(score=0.80) ¦ R&N_ITB:p80, 81(score=0.80) ¦ R&N_ITB:p81(score=0.80) ¦ R&N_ITB:p84, 85(score=0.76) | DESIGN CRITERIA for STG |  | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-09-18 | 2024-10-18 | 2024-11-17 | 2024-12-02 | 2024-12-17 | 2025-01-01 | generated | 0.90 | 6210
itb_candidates |  | GTG Foundation Design Requirements | DESIGN REQUIREMENTS | Gas Turbine Generator |  |  | R&N_ITB:p79(score=0.77) ¦ R&N_ITB:p79(score=0.77) ¦ R&N_ITB:p79(score=0.80) ¦ R&N_ITB:p79(score=0.80) ¦ R&N_ITB:p79(score=0.78) | DESIGN REQUIREMENTS for GTG |  | FA | 1EF1210W16A07 | (GTG Common BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-08-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
itb_candidates |  | Design Criteria Auxiliary Steam System | Design Criteria |  | Auxiliary Steam System |  | R&N_ITB:p90(score=0.80) | Design Criteria for Auxiliary Steam System | Water Treatment System | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
itb_candidates |  | WATER & WASTE WATER TREATMENT PLANT O&M MANUAL | MANUAL | Water Treatment Plant |  |  | R&N_ITB:p86, 87(score=0.80) | MANUAL for Water Treatment Plant | Water Treatment System | FI | 0PF4035W42A06.1T | (WWTS) Transportation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2008-09-02 | 2008-10-16 | 2025-07-19 | 2025-08-18 | 2025-09-17 | 2025-10-02 | 2025-10-17 | 2025-11-01 | generated | 0.90 | 6210
itb_candidates |  | WATER & WASTE WATER TREATMENT PLANT TECHNICAL DATASHEET-Pre-treatment System | TECHNICAL DATASHEET | Water Treatment Plant |  |  | R&N_ITB:p86, 87(score=0.80) | TECHNICAL DATASHEET for Water Treatment Plant | Water Treatment System | FI | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-09-01 | 2024-11-02 | 2024-12-02 | 2025-01-01 | 2025-01-16 | 2025-01-31 | 2025-02-15 | generated | 0.90 | 6210
itb_candidates |  | GTG Turbine Foundation Design Requirements | DESIGN REQUIREMENTS | Gas Turbine Generator |  |  | R&N_ITB:p79(score=0.77) ¦ R&N_ITB:p79(score=0.80) ¦ R&N_ITB:p79(score=0.77) ¦ R&N_ITB:p81(score=0.78) ¦ R&N_ITB:p81(score=0.80) | DESIGN REQUIREMENTS for GTG |  | FA | 1EF1210W16A07 | (GTG Common BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | 2007-03-01 | 2007-08-01 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
itb_candidates |  | TECHNICAL SPECIFICATION – TARIFF METERING SYSTEM, SCADA, RPA, TELECOMMUNICATION SYSTEM, AFPRS | TECHNICAL SPECIFICATION |  | TARIFF METERING SYSTEM, SCADA, RPA, TELECOMMUNICATION SYSTEM, AFPRS |  | R&N_ITB:p91(score=0.80) | Technical Specification for TARIFF METERING SYSTEM, SCADA, RPA, TELECOMMUNICATION SYSTEM, AFPRS | Protection & Metering System | SKIP | 0EF6500W70A01.7 | (Power Metering Equip) MPS Issue | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power Metering System |  | 2007-05-01 | [6 empty] | skip |  | 6210
itb_candidates |  | DESIGN CRITERIA Fuel gas supply system | DESIGN CRITERIA | Fuel Gas Package |  |  | R&N_ITB:p81(score=0.80) ¦ R&N_ITB:p81(score=0.76) | DESIGN CRITERIA for FGP |  | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | 2024-06-06 | 2024-07-06 | 2024-08-05 | 2024-08-20 | 2024-09-04 | 2024-09-19 | generated | 0.90 | 6210
itb_candidates |  | GTG Auxiliary System Layout | LAYOUT | Gas Turbine Generator |  |  | R&N_ITB:p90(score=0.80) ¦ R&N_ITB:p91(score=0.78) ¦ R&N_ITB:p91(score=0.77) ¦ R&N_ITB:p95(score=0.79) ¦ R&N_ITB:p95(score=0.79) | Layout Drawing for GTG | Substation | SKIP | 1EF6500W00A09 | (GTG #11 & UAT Shelter) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-05-31 | [7 empty] | skip |  | 6210
itb_candidates |  | DESIGN CRITERIA | DESIGN CRITERIA | HP & LP steam system |  |  | R&N_ITB:p83(score=0.80) ¦ R&N_ITB:p83(score=0.79) ¦ R&N_ITB:p83(score=0.79) ¦ R&N_ITB:p83(score=0.80) | DESIGN CRITERIA for HP & LP steam system | Water Treatment System | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
itb_candidates |  | MAIN AND REHEAT STEAM SYSTEM DESIGN CRITERIA | DESIGN CRITERIA | MAIN AND REHEAT STEAM SYSTEM |  |  | R&N_ITB:p80, 81(score=0.80) | DESIGN CRITERIA for MAIN AND REHEAT STEAM SYSTEM | Chemical Dosing System | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
itb_candidates |  | CONTROL LOGIC DIAGRAM FUEL OIL/GAS SYSTEM BOP | CONTROL LOGIC DIAGRAM | Fuel Oil System |  |  | R&N_ITB:p94(score=0.79) | CONTROL LOGIC DIAGRAM for Fuel Oil System | Fuel Gas System | FA | 0EF3520W00A02.2 | (FOSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System | 2007-03-15 | 2007-10-29 | 2024-06-07 | 2024-07-19 | 2024-08-30 | 2024-08-09 | 2024-09-20 | 2024-11-01 | generated | 0.90 | 6210
itb_candidates |  | POWER METERING SYSTEM | TECHNICAL SPECIFICATION |  | POWER METERING SYSTEM |  | R&N_ITB:p91(score=0.79) | Technical Specification for POWER METERING SYSTEM | Protection & Metering System | SKIP | 0PF6500W70A02.7P | (Power Metering Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Power Metering System | 2007-07-13 | 2008-02-12 | [6 empty] | skip |  | 6210
itb_candidates |  | H2 & CO2 CONTROL SYSTEM H2 GAS DRYER OUTLINE (Block #3,4) | OUTLINE | H2 & CO2 CONTROL SYSTEM |  |  | R&N_ITB:p95(score=0.79) | OUTLINE for H2 & CO2 CONTROL SYSTEM | H2, CO2 Supply System | FA | 0PF3515W42A08P | (H2) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Common Equipment & Infrastructure > H2 Generation Plant | 2007-09-24 | 2008-07-23 | 2024-11-23 | 2024-12-23 | 2025-01-22 | 2025-02-06 | 2025-02-21 | 2025-03-08 | generated | 0.90 | 6210
itb_candidates |  | WATER & WASTE WATER TREATMENT PLANT GENERAL ARRANGEMENT DRAWING | GENERAL ARRANGEMENT DRAWING | Water Treatment Plant |  |  | R&N_ITB:p86, 87(score=0.79) | GENERAL ARRANGEMENT DRAWING for Water Treatment Plant | Water Treatment System | FA | 0EF4035W00A01.2 | (WWT LEB) GA & Load Data to Civil Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 |  | 2024-12-02 | 2025-01-01 | 2025-01-31 | 2025-02-15 | 2025-03-02 | 2025-03-17 | generated | 0.90 | 6210
itb_candidates |  | GTG P&ID Fuel Oil System | P&ID | Gas Turbine Generator |  |  | R&N_ITB:p94(score=0.79) | P&ID for GTG |  | FA | 1PF1265W42A02.00P | (Fuel oil injection System) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | 2007-03-01 | 2008-02-29 | 2024-08-12 | 2024-09-11 | 2024-10-11 | 2024-10-26 | 2024-11-10 | 2024-11-25 | generated | 0.90 | 6210
itb_candidates |  | System Description Auxiliary Steam System | System Description |  | Auxiliary Steam System |  | R&N_ITB:p90(score=0.79) | System Description for Auxiliary Steam System |  | FA | 1EF3030W00A01 | (ACWS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | 2007-04-02 | 2007-10-05 | 2024-07-14 | 2024-08-13 | 2024-09-12 | 2024-09-27 | 2024-10-12 | 2024-10-27 | generated | 0.90 | 6210
itb_candidates |  | DESIGN CRITERIA FOR WASTE WATER TRANSFER SYSTEM | DESIGN CRITERIA |  | WASTE WATER TRANSFER SYSTEM |  | R&N_ITB:p85(score=0.77) ¦ R&N_ITB:p87(score=0.79) ¦ R&N_ITB:p87(score=0.76) | DESIGN CRITERIA for WASTE WATER TRANSFER SYSTEM | Water Treatment System | FA | 0EF4035W16A02.1 | (WWTS) Civil Design(incl. FDN) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-02-01 | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 | 6210
itb_candidates |  | GTG System Description Combustion Chamber Instrumentation | SYSTEM DESCRIPTION | Gas Turbine Generator |  |  | R&N_ITB:p94(score=0.78) ¦ R&N_ITB:p95(score=0.79) | System Description for GTG |  | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | 2024-08-20 | 2024-09-19 | 2024-10-19 | 2024-11-03 | 2024-11-18 | 2024-12-03 | generated | 0.90 | 6210
itb_candidates |  | FUEL OIL SYSTEM | CONTROL LOOP DIAGRAM | Fuel Oil System |  |  | R&N_ITB:p94(score=0.79) | CONTROL LOOP DIAGRAM for Fuel Oil System | Fuel Gas System | FA | 0PF3520W42A04.3P | (FOFP) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System > Fuel Oil Forward Station | 2007-07-02 | 2008-03-28 | 2024-09-24 | 2024-11-05 | 2024-12-17 | 2024-11-26 | 2025-01-07 | 2025-02-18 | generated | 0.90 | 6210
itb_candidates |  | DESIGN REQUIREMENTS FOR VT & SURGE, BAB36 | DESIGN REQUIREMENTS | Gas Turbine Generator |  |  | R&N_ITB:p79(score=0.76) ¦ R&N_ITB:p81(score=0.78) ¦ R&N_ITB:p81(score=0.79) ¦ R&N_ITB:p84(score=0.77) | DESIGN REQUIREMENTS for GTG |  | FA | 3EF1213W16A01 | (GT #31) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | 2007-04-30 | 2007-07-30 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-31 | generated | 0.90 | 6210
itb_candidates |  | CONSUMER SCHEMES FOR I&C (BLOCK #2) |  | Steam Turbine | Instrumentation & Control (BLOCK #2) |  | R&N_ITB:p92(score=0.79) | for STG |  | FA | 2PF1660W86A07.1P | (HRSG #22 I&C Vendor Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Auxiliary System | 2007-10-02 | 2008-09-03 | 2025-04-07 | 2025-05-07 | 2025-06-06 | 2025-06-21 | 2025-07-06 | 2025-07-21 | generated | 0.90 | 6210
itb_candidates |  | WATER & WASTE WATER TREATMENT PLANT SCHEMATIC DIAGRAM | SCHEMATIC DIAGRAM | Water Treatment Plant |  |  | R&N_ITB:p86, 87(score=0.79) | SCHEMATIC DIAGRAM for Water Treatment Plant | Water Treatment System | FI | 0EF4035W00A01.1 | (WWTS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-04-02 | 2007-12-07 | 2024-07-31 | 2024-08-30 | 2024-09-29 | 2024-10-14 | 2024-10-29 | 2024-11-13 | generated | 0.90 | 6210
itb_candidates |  | FUEL OIL SYSTEM | CONTROL LOGIC DIAGRAM | Fuel Oil System |  |  | R&N_ITB:p94(score=0.79) | CONTROL LOGIC DIAGRAM for Fuel Oil System | Fuel Gas System | FA | 0EF3520W00A02.2 | (FOSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Oil Supply System | 2007-03-15 | 2007-10-29 | 2024-06-07 | 2024-07-19 | 2024-08-30 | 2024-08-09 | 2024-09-20 | 2024-11-01 | generated | 0.90 | 6210
itb_candidates |  | WATER & WASTE WATER TREATMENT PLANT TECHNICAL DATASHEET-Demi.Water System | TECHNICAL DATASHEET | Water Treatment Plant |  |  | R&N_ITB:p86, 87(score=0.78) | TECHNICAL DATASHEET for Water Treatment Plant | Water Treatment System | FI | 0PF4035W42A05.1P | (WWTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-09-01 | 2024-11-02 | 2024-12-02 | 2025-01-01 | 2025-01-16 | 2025-01-31 | 2025-02-15 | generated | 0.90 | 6210
itb_candidates |  | Condenser Performance Curves | PERFORMANCE CURVE | Condenser |  |  | R&N_ITB:p95, 96(score=0.78) ¦ R&N_ITB:p95, 96(score=0.78) ¦ R&N_ITB:p95, 96(score=0.78) | PERFORMANCE CURVE for Condenser |  | FA | 1PF3020W42A20P | (COND) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-07-30 | 2025-01-20 | 2025-02-19 | 2025-03-21 | 2025-04-05 | 2025-04-20 | 2025-05-05 | generated | 0.90 | 6210
itb_candidates |  | CONTROL LOGIC DIAGRAM FOR GT ROTOR COOLING AIR SYSTEM | CONTROL LOGIC DIAGRAM | GT | ROTOR COOLING AIR SYSTEM |  | R&N_ITB:p94(score=0.78) | CONTROL LOGIC DIAGRAM for GT |  | FA | 1PF1265W42A13.4P | (TCA Cooler) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Gas Supply System | 2007-03-01 | 2008-02-29 | 2025-03-04 | 2025-04-03 | 2025-05-03 | 2025-05-18 | 2025-06-02 | 2025-06-17 | generated | 0.90 | 6210
itb_candidates |  | Auxiliary Steam Distribution System | DESIGN CRITERIA |  | Auxiliary Steam Distribution System |  | R&N_ITB:p90(score=0.78) ¦ R&N_ITB:p90(score=0.78) | DESIGN CRITERIA for Auxiliary Steam Distribution System | Chemical Dosing System | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
itb_candidates |  | Inlet Heat System | SYSTEM DESCRIPTION |  | Inlet Heat System |  | R&N_ITB:p94(score=0.78) | System Description for Inlet Heat System |  | FA | 0EF3025W00A01.0 | (Intake Screening System) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Intake Pump Structure | 2007-03-15 | 2007-10-29 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
itb_candidates |  | Waste Water Transfer System | DESIGN CRITERIA |  | Waste Water Transfer System |  | R&N_ITB:p85(score=0.76) ¦ R&N_ITB:p85(score=0.76) ¦ R&N_ITB:p87(score=0.78) ¦ R&N_ITB:p87(score=0.78) ¦ R&N_ITB:p87(score=0.75) | DESIGN CRITERIA for Waste Water Transfer System | Water Treatment System | FA | 0EF4035W16A02.1 | (WWTS) Civil Design(incl. FDN) | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System | 2007-09-03 | 2008-02-01 | 2024-10-03 | 2024-11-02 | 2024-12-02 | 2024-12-17 | 2025-01-01 | 2025-01-16 | generated | 0.90 | 6210
itb_candidates |  | GTG Auxiliary Wiring Diagrams | WIRING DIAGRAM | Gas Turbine Generator |  |  | R&N_ITB:p95(score=0.78) | WIRING DIAGRAM for GTG |  | FA | 1PF6500W70A04.1P | (GTG UAT) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2007-03-30 | 2008-03-17 | 2024-06-22 | 2024-07-22 | 2024-08-21 | 2024-09-05 | 2024-09-20 | 2024-10-05 | generated | 0.90 | 6210
itb_candidates |  | Fuel Gas System | DESIGN CRITERIA | Fuel Gas Package |  |  | R&N_ITB:p81(score=0.78) ¦ R&N_ITB:p81(score=0.78) ¦ R&N_ITB:p84, 85(score=0.76) ¦ R&N_ITB:p84, 85(score=0.76) | DESIGN CRITERIA for FGP |  | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-06-06 | 2024-07-06 | 2024-08-05 | 2024-08-20 | 2024-09-04 | 2024-09-19 | generated | 0.90 | 6210
itb_candidates |  | DATA SHEETS FOR I&C EQUIPMENT | DATA SHEET | Gas Turbine Generator |  |  | R&N_ITB:p94(score=0.78) ¦ R&N_ITB:p94(score=0.78) | Data Sheet for GTG |  | FA | 3EF1200W00A03 | (GTG #31/#32) Utility Consumption Data | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | 2007-03-01 | 2007-04-26 | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 | 6210
itb_candidates |  | ELECTRICAL SYSTEM |  | DESIGN CRIETRIA | ELECTRICAL SYSTEM |  | R&N_ITB:p92(score=0.78) | for DESIGN CRIETRIA |  | FI | 0EF5544W16A09 | (GIS BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Extra High Voltage Substation (GIS/AIS) | 2007-03-01 | 2007-06-29 | 2024-03-01 | 2024-03-01 | 2024-03-31 | 2024-04-15 | 2024-04-30 | 2024-05-15 | generated | 0.90 | 6210
itb_candidates |  | CONTROL LOOP DIAGRAM FOR GT ROTOR COOLING AIR SYSTEM | CONTROL LOOP DIAGRAM | GT | ROTOR COOLING AIR SYSTEM |  | R&N_ITB:p94(score=0.78) | CONTROL LOOP DIAGRAM for GT |  | FA | 3SF1265W62A18 | (Control Oil) Loop chek | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Auxiliary System | 2008-07-16 | 2008-07-20 | 2026-01-27 | 2026-02-26 | 2026-03-28 | 2026-04-12 | 2026-04-27 | 2026-05-12 | generated | 0.90 | 6210
itb_candidates |  | DESIGN CRITERIA FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | DESIGN CRITERIA |  | DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM |  | R&N_ITB:p85(score=0.75) ¦ R&N_ITB:p86(score=0.76) ¦ R&N_ITB:p87(score=0.78) | DESIGN CRITERIA for DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | Water Treatment System | FA | 0EF3010W16A02 | (DWP Chemical Storage Tank Shelter) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Chemical Storage Tank | 2007-10-02 | 2008-01-24 | 2024-11-01 | 2024-12-01 | 2024-12-31 | 2025-01-15 | 2025-01-30 | 2025-02-14 | generated | 0.90 | 6210
itb_candidates |  | I&C | DESIGN CRITERIA |  | Instrumentation & Control |  | R&N_ITB:p83(score=0.76) ¦ R&N_ITB:p83(score=0.76) ¦ R&N_ITB:p83(score=0.76) ¦ R&N_ITB:p83(score=0.76) ¦ R&N_ITB:p92(score=0.78) | DESIGN CRITERIA for Instrumentation & Control |  | FI | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-03-01 | 2024-03-15 | 2024-04-14 | 2024-04-29 | 2024-05-14 | 2024-05-29 | generated | 0.90 | 6210
itb_candidates |  | GTG System Description Fuel Gas | SYSTEM DESCRIPTION | Gas Turbine Generator |  |  | R&N_ITB:p94(score=0.78) | System Description for GTG |  | FA | 0EF3520W00A01 | (FGSS) P&ID & System Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-15 | 2007-09-20 | 2024-08-20 | 2024-09-19 | 2024-10-19 | 2024-11-03 | 2024-11-18 | 2024-12-03 | generated | 0.90 | 6210
itb_candidates |  | DESIGN CRITERIA FOR ELECTRICAL SYSTEM | DESIGN CRITERIA |  | ELECTRICAL SYSTEM |  | R&N_ITB:p92(score=0.78) | DESIGN CRITERIA for ELECTRICAL SYSTEM | Water Treatment System | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
itb_candidates |  | GSUT / UAT / OVERALL PROTECTION FOR GTG UNIT | ELECTRICAL CONTROL LOGIC DIAGRAM | Gas Turbine Generator |  |  | R&N_ITB:p95(score=0.78) | ELECTRICAL CONTROL LOGIC DIAGRAM for GTG |  | FA | 1PF1255W70A01P | (GTG#11 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | 2007-03-01 | 2008-03-31 | 2024-05-23 | 2024-06-22 | 2024-07-22 | 2024-08-06 | 2024-08-21 | 2024-09-05 | generated | 0.90 | 6210
itb_candidates |  | GTG P&ID Combustion Chamber Instrumentation System | P&ID | Gas Turbine Generator |  |  | R&N_ITB:p94(score=0.78) | P&ID for GTG |  | FA | 1PF1255W70A01.1P | (GTG#12 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Electrical System | 2007-03-01 | 2008-03-31 | 2024-08-12 | 2024-09-11 | 2024-10-11 | 2024-10-26 | 2024-11-10 | 2024-11-25 | generated | 0.90 | 6210
itb_candidates |  | Condenser #2 Performance Curves | PERFORMANCE CURVE | Condenser #2 |  |  | R&N_ITB:p95, 96(score=0.78) | PERFORMANCE CURVE for Condenser #2 |  | FA | 2PF3020W42A20P | (COND) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | 2007-10-03 | 2008-08-29 | 2025-01-20 | 2025-02-19 | 2025-03-21 | 2025-04-05 | 2025-04-20 | 2025-05-05 | generated | 0.90 | 6210
itb_candidates |  | GTG I&C SCHEMATICS | SCHEMATICS | Gas Turbine Generator |  |  | R&N_ITB:p94(score=0.78) | SCHEMATICS for GTG |  | FA | 1PF1255W70A01P | (GTG#11 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | 2007-03-01 | 2008-03-31 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
itb_candidates |  | DESIGN CRITERIA ELECTRICAL SYSTEM | DESIGN CRITERIA |  | ELECTRICAL SYSTEM |  | R&N_ITB:p92(score=0.78) ¦ R&N_ITB:p92(score=0.77) | DESIGN CRITERIA for ELECTRICAL SYSTEM | Water Treatment System | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
itb_candidates |  | Gas Treatment Plant | PLAN | Gas Treatment Plant |  |  | R&N_ITB:p97(score=0.77) | Plan for Gas Treatment Plant |  | FA | 0CF3010W42A07 | (WTS) Installation | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2008-10-17 | 2008-12-01 |  |  |  | 2025-07-20 | 2025-08-19 | 2025-09-18 | generated | 0.90 | 6210
itb_candidates |  | Control Logic Diagram for BOP | CONTROL LOGIC DIAGRAM | AUX Steam System_I&C_Logic |  |  | R&N_ITB:p92(score=0.77) ¦ R&N_ITB:p93(score=0.76) | CONTROL LOGIC DIAGRAM for AUX Steam System_I&C_Logic |  | FA | 3PF1655W86A11P | (HRSG #31 I&C Vendor Equip) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Auxiliary System | 2007-10-02 | 2008-10-03 | 2025-04-14 | 2025-05-14 | 2025-06-13 | 2025-06-28 | 2025-07-13 | 2025-07-28 | generated | 0.90 | 6210
itb_candidates |  | ELECTRICAL SYSTEM | DESIGN CRITERIA |  | ELECTRICAL SYSTEM |  | R&N_ITB:p92(score=0.77) | DESIGN CRITERIA for ELECTRICAL SYSTEM | Water Treatment System | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
itb_candidates |  | Auxiliary Steam System (Common) | CONTROL LOOP DIAGRAM |  | Auxiliary Steam System (Common) |  | R&N_ITB:p93(score=0.77) | CONTROL LOOP DIAGRAM for Auxiliary Steam System (Common) |  | FA | 3SF1265W62A18 | (Control Oil) Loop chek | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Auxiliary System | 2008-07-16 | 2008-07-20 | 2026-01-27 | 2026-02-26 | 2026-03-28 | 2026-04-12 | 2026-04-27 | 2026-05-12 | generated | 0.90 | 6210
itb_candidates |  | Design Criteria Fuel Oil System | DESIGN CRITERIA | Fuel Oil System |  |  | R&N_ITB:p81(score=0.77) ¦ R&N_ITB:p84, 85(score=0.75) | DESIGN CRITERIA for Fuel Oil System | Chemical Dosing System | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
itb_candidates |  | Air Intake System MBL | MBL |  | Air Intake System |  | R&N_ITB:p94(score=0.77) | MBL for Air Intake System |  | FA | 3SF1230W62A14 | (Air Intake) Function Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Air Intake System | 2008-08-10 | 2008-08-12 |  |  |  | 2025-05-13 | 2025-06-12 | 2025-07-12 | generated | 0.30 | 6210
itb_candidates |  | WASTE WATER TRANSFER SYSTEM DESIGN CRITERIA | DESIGN CRITERIA | WASTE WATER TRANSFER SYSTEM |  |  | R&N_ITB:p85(score=0.77) | DESIGN CRITERIA for WASTE WATER TRANSFER SYSTEM | Water Treatment System | FA | 0EF4035W16A02.2 | (WWT LEB) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Waste Water Treatment System > Waste Water Treatment LEB | 2007-11-02 | 2008-02-01 | 2024-12-02 | 2025-01-01 | 2025-01-31 | 2025-02-15 | 2025-03-02 | 2025-03-17 | generated | 0.90 | 6210
itb_candidates |  | Gas Treatment Plant General Data | Data | Gas Treatment Plant |  |  | R&N_ITB:p97(score=0.77) | Data for Gas Treatment Plant | Water Treatment System | FI | 0PF3010W42A05P | (WTS) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System | 2007-08-31 | 2008-09-01 | 2024-11-29 | 2024-12-29 | 2025-01-28 | 2025-02-12 | 2025-02-27 | 2025-03-14 | generated | 0.90 | 6210
itb_candidates |  | Design Criteria Demineralized Water System | Design Criteria |  | Demineralized Water System |  | R&N_ITB:p86(score=0.77) | Design Criteria for Demineralized Water System | Water Treatment System | FA | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 | 6210
itb_candidates |  | ELECTRICAL CONTROL LOGIC DIAGRAM BACK UP TR PROTECTION | DIAGRAM |  |  |  | R&N_ITB:p93(score=0.77) | Diagram |  | FA | 0PF6500W70A02.6P | (Electrical Protection Panel) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2007-08-30 | 2008-03-10 | 2024-10-25 | 2024-11-24 | 2024-12-24 | 2025-01-08 | 2025-01-23 | 2025-02-07 | generated | 0.90 | 6210
itb_candidates |  | GSUT/UAT/OVERALL | STUDY | Generator Step-Up Transformer/UNIT AUXILIARY TRANSFORMER/OVERALL |  |  | R&N_ITB:p88(score=0.77) | STUDY for Generator Step-Up Transformer/UNIT AUXILIARY TRANSFORMER/OVERALL |  | FA | 1SF6500W62A08.1 | (GTG UAT) Function Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Electrical System > Auxiliary Transformer | 2008-06-18 | 2008-06-21 |  |  |  | 2025-03-21 | 2025-04-20 | 2025-05-20 | generated | 0.90 | 6210
itb_candidates |  | Air Intake System MBL | MBL |  | Air Intake System |  | R&N_ITB:p94(score=0.77) | MBL for Air Intake System |  | FA | 3SF1230W62A14 | (Air Intake) Function Test | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Air Intake System | 2008-08-10 | 2008-08-12 |  |  |  | 2025-05-13 | 2025-06-12 | 2025-07-12 | generated | 0.30 | 6210
itb_candidates |  | Instrument Air System | DESIGN CRITERIA |  | Instrument Air System |  | R&N_ITB:p83(score=0.76) ¦ R&N_ITB:p83(score=0.76) | DESIGN CRITERIA for Instrument Air System |  | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-08-20 | 2024-09-19 | 2024-10-19 | 2024-11-03 | 2024-11-18 | 2024-12-03 | generated | 0.90 | 6210
itb_candidates |  | ELECTRICAL CONTROL LOGIC DIAGRAM GSUT/UAT/LINE/OVERALL PROTECTION | DIAGRAM |  |  |  | R&N_ITB:p93(score=0.76) | Diagram |  | FA | 0PF6500W70A02.6P | (Electrical Protection Panel) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Electrical System > Electrical Protection Panel | 2007-08-30 | 2008-03-10 | 2024-10-25 | 2024-11-24 | 2024-12-24 | 2025-01-08 | 2025-01-23 | 2025-02-07 | generated | 0.90 | 6210
itb_candidates |  | Demiralized Water Distribution System | DESIGN CRITERIA |  | Demiralized Water Distribution System |  | R&N_ITB:p86(score=0.75) ¦ R&N_ITB:p86(score=0.75) ¦ R&N_ITB:p87(score=0.76) | DESIGN CRITERIA for Demiralized Water Distribution System | Water Treatment System | FA | 0EF5534W16A02 | (DWP BLDG) FDN Design | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Water Treatment System > Demi. Water Plant Building | 2007-08-31 | 2008-01-01 | 2024-09-30 | 2024-10-30 | 2024-11-29 | 2024-12-14 | 2024-12-29 | 2025-01-13 | generated | 0.90 | 6210
itb_candidates |  | Design Criteria Oil facility system | Design Criteria |  | Oil facility system |  | R&N_ITB:p79(score=0.76) | Design Criteria for Oil facility system | Water Treatment System | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-04-14 | 2024-05-14 | 2024-06-13 | 2024-06-28 | 2024-07-13 | 2024-07-28 | generated | 0.90 | 6210
itb_candidates |  | I&C General Design Criteria | DESIGN CRITERIA | INC_Plant_Overall_Design |  |  | R&N_ITB:p83(score=0.76) | DESIGN CRITERIA for INC_Plant_Overall_Design |  | FI | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-03-01 | 2024-03-15 | 2024-04-14 | 2024-04-29 | 2024-05-14 | 2024-05-29 | generated | 0.90 | 6210
itb_candidates |  | DESIGN CRITERIA FOR FUEL GAS SYSTEM | DESIGN CRITERIA | Fuel Gas Package |  |  | R&N_ITB:p84, 85(score=0.76) | DESIGN CRITERIA for FGP |  | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 | 2024-06-06 | 2024-07-06 | 2024-08-05 | 2024-08-20 | 2024-09-04 | 2024-09-19 | generated | 0.90 | 6210
itb_candidates |  | Plant Air System | PLAN |  | Plant Air System |  | R&N_ITB:p84(score=0.76) | Plan for Plant Air System |  | FA | 0EF3510W00A02 | (COMP Air System) Compressed Air Sys. Key data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Water & Air Supply System > Compressed Air System | 2007-03-30 | 2007-04-30 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.90 | 6210
itb_candidates |  | FGSS EQUIPMENT DATA SHEET FOR FUEL GAS PERFORMANCE HEATER | DATA SHEET | FGSS |  |  | R&N_ITB:p97(score=0.76) | Data Sheet for FGSS |  | FA | 0EF3520W00A02 | (FGSS) FGSS Key Data | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Fuel Gas & Oil Supply Systems > Fuel Gas Supply System | 2007-03-01 | 2007-03-30 | 2024-05-10 | 2024-06-09 | 2024-07-09 | 2024-07-24 | 2024-08-08 | 2024-08-23 | generated | 0.90 | 6210
itb_candidates |  | GSUT / OVERALL PROTECTION FOR STG UNIT | STUDY | Steam Turbine & Generator |  |  | R&N_ITB:p88(score=0.76) | STUDY for STG |  | FA | 1PF6500W70A07P | (STG #10 & UST Shelter) P.O & Procurement - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-06-29 | 2008-06-22 | 2025-01-02 | 2025-02-01 | 2025-03-03 | 2025-03-18 | 2025-04-02 | 2025-04-17 | generated | 0.90 | 6210
itb_candidates |  | GTG Connection Diagram for Fuel Gas Skid (MBY09GF001) | DIAGRAM | Gas Turbine Generator |  |  | R&N_ITB:p81(score=0.76) | Diagram for GTG |  | FA | 1PF1265W42A03P | (Gas Final Filter & Metering Skid) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Gas Supply System | 2007-03-01 | 2008-01-30 | 2024-06-27 | 2024-07-27 | 2024-08-26 | 2024-09-10 | 2024-09-25 | 2024-10-10 | generated | 0.90 | 6210
itb_candidates |  | Performance Curves For Condenser Vacuum Pump | PERFORMANCE CURVE | Condenser Vacuum Pump |  |  | R&N_ITB:p95, 96(score=0.76) | PERFORMANCE CURVE for Condenser Vacuum Pump |  | FA | 1SF3020W62A28 | (COND System) Pump Operation | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | 2009-01-18 | 2009-01-22 | 2026-05-08 | 2026-06-07 | 2026-07-07 | 2026-07-22 | 2026-08-06 | 2026-08-21 | generated | 0.90 | 6210
itb_candidates |  | Calculation | Calculation |  |  |  | R&N_ITB:p97(score=0.76) | Calculation sheet |  | FA | 0PF6020W58A02P | (Piping) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Plant Common > BOP Piping for Plant Common > Piping Material Procurement | 2007-09-14 | 2008-06-11 | 2025-02-01 | 2025-03-03 | 2025-04-02 | 2025-04-17 | 2025-05-02 | 2025-05-17 | generated | 0.90 | 6210
itb_candidates |  | PERFORMANCE HEATER & FINAL CHANCE FILTER FOUNDATION (CCPP PLANT AREA) CALCULATION | CALCULATION | Performance Heater |  |  | R&N_ITB:p96, 97(score=0.75) ¦ R&N_ITB:p97(score=0.76) | Calculation sheet for Performance Heater |  | FA | 1CF3520W16A02.2 | (Gas HTR) FDN Work | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Early Power Block Common > Fuel Gas Supply System > Gas Heater | 2007-10-02 | 2007-11-28 |  |  |  | 2024-07-04 | 2024-08-03 | 2024-09-02 | generated | 0.90 | 6210
itb_candidates |  | Design Basis | Design Basis |  |  |  | R&N_ITB:p90(score=0.76) ¦ R&N_ITB:p90(score=0.76) | Design Basis |  | FA | 0EF1000W00A04 | Mechanical Design Criteria | CCPP Project Standard Schedule_20181012_Idea > Plant General > Plant Engineering > Basic Engineering & Design | 2007-03-15 | 2007-07-24 |  |  |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | generated | 0.30 | 6210
itb_candidates |  | Control Logic Diagram for BOP | CONTROL LOGIC DIAGRAM | HP & LP steam system_I&C_Logic |  |  | R&N_ITB:p93(score=0.76) | CONTROL LOGIC DIAGRAM for HP & LP steam system_I&C_Logic |  | FA | 0PF7000W86A02P | (Control Valve) P.O & Procurement for Early power | CCPP Project Standard Schedule_20181012_Idea > Plant Common > Instrument & Control Systems > Control Valves | 2007-10-01 | 2008-08-15 | 2025-04-13 | 2025-05-13 | 2025-06-12 | 2025-06-27 | 2025-07-12 | 2025-07-27 | generated | 0.90 | 6210
itb_candidates |  | GSUT / UAT / OVERALL PROTECTION FOR GTG UNIT | STUDY | Gas Turbine Generator |  |  | R&N_ITB:p88(score=0.76) | STUDY for GTG |  | FA | 1PF6500W70A07P | (STG #10 & UST Shelter) P.O & Procurement - Main TR | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | 2007-06-29 | 2008-06-22 | 2024-10-25 | 2024-11-24 | 2024-12-24 | 2025-01-08 | 2025-01-23 | 2025-02-07 | generated | 0.90 | 6210
itb_candidates |  | PROTECTION DIAGRAM FOR I&C (BLOCK #2) | DIAGRAM | Steam Turbine |  |  | R&N_ITB:p93(score=0.75) | Diagram for STG |  | FA | 2PF2020W42A10P | (ST #20) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | 2007-03-01 | 2008-10-01 | 2024-10-21 | 2024-11-20 | 2024-12-20 | 2025-01-04 | 2025-01-19 | 2025-02-03 | generated | 0.90 | 6210
itb_candidates |  | GENERATOR, EXCITATION SYSTEM, AND POWER SYSTEM STABILIZER MODEL | MODEL | Gas Turbine Generator |  |  | R&N_ITB:p88(score=0.75) | MODEL for GTG |  | FA | 3PF1255W70A01P | (GTG#31 Electrical) P.O & Procurement | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Electrical System | 2007-04-30 | 2008-05-28 | 2024-08-26 | 2024-09-25 | 2024-10-25 | 2024-11-09 | 2024-11-24 | 2024-12-09 | generated | 0.90 | 6210