## 제출현황 (hidden)
2016-12-07 기준
|  | Total Doc. |  | Plan/Issue Doc. | [5 empty] | Delayed Doc. |  |  | Submitted
|  |  |  | FI |  | FA |  | FC
|  | FI | FA | Plan | Issue | Plan | Issue | Plan | Issue | FI | FA | FC
EM3팀 | EM(02) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
배치/운반기술팀 | GA(10) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
성능/프로세스기술팀 | PS(11) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
플랜트기술팀 | PT(12) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
기계기술팀(WT) | WT(13) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
기계기술팀(HVAC) | HVAC(13) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
기계기술팀(FF) | FF(13) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
배관기술팀 | PP(14) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
전력계통기술팀 | EL(15) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
계측제어기술팀 | I&C(16) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
토목기술팀 | CV(17) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
건축기술팀 | S&A(18) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
P/E Center Total |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0

## DDCL(DHI-PP) 2020-10-21
Documents & Drawings Control log For Grati Block 2 Add-on Project
No. | Scope | Document No | Serial | Title | Pur | First Plan | Final Plan | Latest Issue to Client |  |  |  | Latest Reply from Client |  |  |  |  | First Actual | Final Actual
| DHI/PP |  |  |  | FA/FI | FA | FC | Issue Date (To Owner) | DT No | DT Pur. | DT Rev. | Date | DT No. | Pur. | Rev. | Status | FA | FC
1 | DHI | GRT-DA01-P0ZEN-020001 | 020001 | DOCUMENT IDENTIFICATION | FA | 2017-01-10 | 2017-04-10 | 2017-04-18 | GRT-DS-IP-DT-170048 | FC | 0 | 2017-05-31 | APPROVED | FC | 0 | A | 2017-01-10 | 2017-04-18
2 | DHI | GRT-DA01-P0ZEN-020002 | 020002 | EQUIPMENT AND SYSTEM IDENTIFICATION | FA | 2017-01-10 | 2017-04-10 | 2017-04-18 | GRT-DS-IP-DT-170048 | FC | 0 | 2017-06-01 | APPROVED | FC | 0 | A | 2017-01-10 | 2017-04-18
3 | DHI | GRT-QM01-P0ZEN-040001 | 040001 | Shop Inspection and Test Plan for Manufacturing | FA | 2017-03-10 | 2017-06-10 | 2017-09-20 | GRT-DS-IP-DT-170311 | FC | 0 | 2017-09-26 | 040001-0 | FC | 0 | B | 2017-03-22 | 2017-09-20
4 | DHI | GRT-QA00-P0H-040002 | 040002 | [HRSG]_NDE Procedure for HRSG HP Drum | FI | 2017-06-20 | 2017-09-20 | 2017-07-31 | GRT-DS-IP-DT-170214 | FC | 0 | 2017-08-11 |  | FC | 0 | A | 2017-07-06 | 2017-07-31
5 | DHI | GRT-QA00-P0H-040003 | 040003 | [HRSG]_NDE Procedure for HRSG LP Drum | FI | 2017-06-20 | 2017-09-20 | 2017-07-31 | GRT-DS-IP-DT-170214 | FC | 0 | 2017-08-11 |  | FC | 0 | A | 2017-07-06 | 2017-07-31
6 | DHI | GRT-QA00-P0H-040004 | 040004 | [HRSG]_Heat Treatment Procedure for HRSG Heat Exchanger | FI | 2017-06-20 | 2017-09-20 | 2017-10-26 | GRT-DS-IP-DT-170377 | FC | 1 | 2017-11-02 | 040004-1 | FC | 1 | B | 2017-07-06 | 2017-09-06
7 | DHI | GRT-QA00-P0H-040005 | 040005 | [HRSG]_NDE Procedure for HRSG Heat Exchanger | FI | 2017-06-20 | 2017-09-20 | 2017-10-26 | GRT-DS-IP-DT-170377 | FC | 1 | 2017-11-02 | 040005-1 | FC | 1 | A | 2017-07-06 | 2017-07-31
8 | DHI | GRT-QA00-P0H-040006 | 040006 | [HRSG]_Shop Quality Manual for HRSG | FI | 2017-06-23 | 2017-09-23 | 2017-07-31 | GRT-DS-IP-DT-170214 | FC | 0 | 2017-08-11 |  | FC | 0 | A | 2017-07-06 | 2017-07-31
9 | DHI | GRT-QA00-P0H-040007 | 040007 | [HRSG]_Welders List for HRSG Heat Exchanger | FI | 2017-08-29 | 2017-11-29 | 2017-10-26 | GRT-DS-IP-DT-170330 | FC | 0 | 2017-11-02 | 040007-0 | FC | 0 | A | 2017-09-06 | 2017-10-26
10 | DHI | GRT-QA00-P0H-040008 | 040008 | [HRSG]_WPS&PQR for HRSG Heat Exchanger | FI | 2017-08-29 | 2017-11-29 | 2017-10-26 | GRT-DS-IP-DT-170330 | FC | 0 | 2017-11-02 | 040008-0 | FC | 0 | A | 2017-09-06 | 2017-10-26
11 | DHI | GRT-QA00-P0H-040009 | 040009 | [HRSG]_Welders List for HRSG HP Drum | FI | 2017-08-29 | 2017-11-29 | 2017-10-26 | GRT-DS-IP-DT-170330 | FC | 0 | 2017-11-02 | 040009-0 | FC | 0 | A | 2017-09-06 | 2017-10-26
12 | DHI | GRT-QA00-P0H-040010 | 040010 | [HRSG]_WPS&PQR for HRSG HP Drum | FI | 2017-08-29 | 2017-11-29 | 2017-10-26 | GRT-DS-IP-DT-170330 | FC | 0 | 2017-11-02 | 040010-0 | FC | 0 | A | 2017-09-06 | 2017-10-26
13 | DHI | GRT-QA00-P0H-040011 | 040011 | [HRSG]_Welders List for HRSG LP Drum | FI | 2017-08-29 | 2017-11-29 | 2017-10-26 | GRT-DS-IP-DT-170330 | FC | 0 | 2017-11-02 | 040011-0 | FC | 0 | A | 2017-09-06 | 2017-10-26
14 | DHI | GRT-QA00-P0H-040012 | 040012 | [HRSG]_WPS&PQR for HRSG LP Drum | FI | 2017-08-29 | 2017-11-29 | 2017-10-26 | GRT-DS-IP-DT-170330 | FC | 0 | 2017-11-02 | 040012-0 | FC | 0 | A | 2017-09-06 | 2017-10-26
15 | DHI | GRT-QA00-P0H-040013 | 040013 | NDE Procedure for HRSG Piping | FI | 2017-08-29 | 2017-11-29 | 2017-10-26 | GRT-DS-IP-DT-170330 | FC | 0 | 2017-11-02 | 040013-0 | FC | 0 | A | 2017-09-06 | 2017-10-26
16 | DHI | GRT-QA00-P0H-040014 | 040014 | Heat Treatment Procedure for HRSG Piping | FI | 2017-08-29 | 2017-11-29 | 2017-10-26 | GRT-DS-IP-DT-170330 | FC | 0 | 2017-11-02 | 040014-0 | FC | 0 | A | 2017-09-06 | 2017-10-26
17 | DHI | GRT-QA00-P0H-040015 | 040015 | Welders List for HRSG Piping | FI | 2017-08-29 | 2017-11-29 | 2017-10-26 | GRT-DS-IP-DT-170330 | FC | 0 | 2017-11-02 | 040015-0 | FC | 0 | A | 2017-09-06 | 2017-10-26
18 | DHI | GRT-QA00-P0H-040016 | 040016 | WPS&PQR for HRSG Piping | FI | 2017-08-29 | 2017-11-29 | 2017-10-26 | GRT-DS-IP-DT-170330 | FC | 0 | 2017-11-02 | 040016-0 | FC | 0 | A | 2017-09-06 | 2017-10-26
19 | DHI | GRT-QA00-P0H-040017 | 040017 | [HRSG]_Welding Consumable Control Procedure for HRSG Pressure Part | FI | 2017-09-06 | 2017-12-06 | 2017-09-29 | GRT-DS-IP-DT-170323 | FC | 0 | 2017-10-02 | 040017-0 | FC | 0 | A | 2017-09-11 | 2017-09-29
20 | DHI | GRT-QA00-P0H-040018 | 040018 | [HRSG]_Welding Consumable Control Procedure for HRSG Piping | FI | 2017-09-28 | 2017-12-28 | 2018-01-06 | GRT-DS-IP-DT-180002 | FC | 0 | 2018-01-06 | 040018-0 | FC | 0 | A | 2017-10-10 | 2018-01-06
21 | DHI | GRT-DP00-P0ZEN-070001 | 070001 | Painting specification | FA | 2017-06-21 | 2017-09-21 | 2017-11-29 | GRT-DS-IP-DT-170490 | FC | 0 | 2018-04-26 | 75-5th DRM | FC | 0 | A | 2017-07-06 | 2017-11-29
22 | DHI | GRT-UC07-P0ZEN-100001 | 100001 | PLOT PLAN | FA | 2017-02-10 | 2017-06-06 | 2018-08-02 | GRT-DS-IP-DT-180194 | FC | 1 | 2018-08-14 | 1000001-1 | FC | 1 | A | 2017-02-10 | 2017-03-22
23 | DHI | GRT-UC08-P0ZEN-100002 | 100002 | General Arrangement of Power Block | FA | 2017-03-17 | 2018-10-01 | 2018-10-02 | GRT-DS-IP-DT-180230 | FC | 0 | 2018-10-02 | 100002-1 | FC | 0 | A | 2017-04-06 | #VALUE!
24 | DHI | GRT-UE00-P0ZEN-100003 | 100003 | General Arrangement of Steam Turbine Building Ground Floor | FA | 2017-03-17 | 2018-10-01 | 2018-07-19 | GRT-DS-IP-DT-180181 | FC | 0 | 2018-07-27 | 100003-0 | FC | 0 | A | 2017-03-22 | #VALUE!
25 | DHI | GRT-UE00-P0ZEN-100004 | 100004 | General Arrangement of Steam Turbine Building Mezzanine Floor | FA | 2017-03-17 | 2018-10-01 | 2018-07-19 | GRT-DS-IP-DT-180181 | FC | 0 | 2018-07-27 | 100004-0 | FC | 0 | A | 2017-03-22 | #VALUE!
26 | DHI | GRT-UE00-P0ZEN-100005 | 100005 | General Arrangement of Steam Turbine Building Operating Floor | FA | 2017-03-17 | 2018-10-01 | 2018-07-19 | GRT-DS-IP-DT-180181 | FC | 0 | 2018-07-27 | 100005-0 | FC | 0 | A | 2017-03-22 | #VALUE!
27 | DHI | GRT-UE00-P0ZEN-100006 | 100006 | General Arrangement of Steam Turbine Building Deaerator Floor | FA | 2017-03-17 | 2018-10-01 | 2018-07-19 | GRT-DS-IP-DT-180181 | FC | 0 | 2018-07-27 | 100006-0 | FC | 0 | A | 2017-03-22 | #VALUE!
28 | DHI | GRT-UE00-P0ZEN-100007 | 100007 | General Arrangement of Steam Turbine Building Basement Floor | FA | 2017-03-17 | 2018-10-01 | 2018-07-19 | GRT-DS-IP-DT-180181 | FC | 0 | 2018-07-27 | 100007-0 | FC | 0 | A | 2017-03-22 | #VALUE!
29 | DHI | GRT-UE00-P0ZEN-100008 | 100008 | General Arrangement of Steam Turbine Building Section A-A | FA | 2017-03-17 | 2018-10-01 | 2018-07-19 | GRT-DS-IP-DT-180181 | FC | 0 | 2018-07-27 | 100008-0 | FC | 0 | A | 2017-03-22 | #VALUE!
30 | DHI | GRT-UE00-P0ZEN-100009 | 100009 | General Arrangement of Steam Turbine Building Section B-B | FA | 2017-03-17 | 2018-10-01 | 2018-07-19 | GRT-DS-IP-DT-180181 | FC | 0 | 2018-07-27 | 100009-0 | FC | 0 | A | 2017-03-22 | #VALUE!
31 | DHI | GRT-XG05-P0ZEN-110001 | 110001 | [Plant Overall]_HEAT BALANCE DIAGRAMS | FI | 2017-02-10 | 2017-07-14 | 2017-07-04 | GRT-DS-IP-DT-170145 | FC | 0 | 2017-07-19 |  | FC | 0 | B | 2017-02-10 | 2017-07-04
32 | DHI | GRT-XG05-P0ZEN-110002 | 110002 | [Symbol & Legend]_P&I DIAGRAM | FA | 2017-02-10 | 2017-06-10 | 2017-05-30 | GRT-DS-IP-DT-170082 | FC | 0 | 2017-05-20 | 110002-1 | FC | 0 | A | 2017-02-13 | #VALUE!
33 | DHI | GRT-XG02-P0LBA-110003 | 110003 | [HP & LP steam system]_P&I DIAGRAM | FA | 2017-02-22 | 2017-07-14 | 2019-01-08 | GRT-DS-IP-DT-190001 | FC | 2 | 2019-01-08 | 110003-1 | FC | 2 | A | 2017-02-13 | 2017-07-17
34 | DHI | GRT-XG02-P0LBG-110004 | 110004 | [AUX Steam System]_P&I DIAGRAM | FA | 2017-02-22 | 2017-07-14 | 2018-09-12 | GRT-DS-IP-DT-180215 | FC | 2 | 2018-09-20 | 110004-2 | FC | 2 | A | 2017-02-13 | 2017-07-17
35 | DHI | GRT-XG02-P0LCM-110005 | 110005 | [Steam drain system]_P&ID DIAGRAM | FA | 2017-02-22 | 2017-07-14 | 2018-09-12 | GRT-DS-IP-DT-180215 | FC | 2 | 2018-09-20 | 110005-2 | FC | 2 | A | 2017-02-13 | 2017-07-17
36 | DHI | GRT-XG02-P0LA-110006 | 110006 | [Feedwater system]_P&I DIAGRAM | FA | 2017-02-22 | 2017-07-14 | 2020-01-21 | GRT-DS-IP-DT-200012 | FC | 2 | 2018-03-13 | 08.002/E04/PLNE/III/2018 | DCR | 1DCR2 | A | 2017-02-13 | 2017-07-18
37 | DHI | GRT-XG02-P0LC-110007 | 110007 | [Condensate system]_P&I DIAGRAM | FA | 2017-02-22 | 2017-07-14 | 2017-10-26 | GRT-DS-IP-DT-170366 | FC | 1 | 2017-11-02 | 110007-0 | FC | 1 | A | 2017-02-13 | 2017-07-18
38 | DHI | GRT-XG02-P0PA-110008 | 110008 | [Aux. Cooling Water System]_P&I DIAGRAM | FA | 2017-02-22 | 2017-07-14 | 2020-01-22 | GRT-DS-IP-DT-200014 | FC | 1 | 2020-01-22 | 110008-3 | FC | 1 | A | 2017-02-13 | 2017-08-21
39 | DHI | GRT-XG02-P0PG-110009 | 110009 | [Closed cooling water system]_P&I DIAGRAM | FA | 2017-02-22 | 2017-07-14 | 2020-01-22 | GRT-DS-IP-DT-200015 | FC | 2 | 2020-01-22 | 110009-3 | FC | 2 | A | 2017-02-13 | 2017-09-06
40 | DHI | GRT-XG02-P0QJA-110010 | 110010 | [N2 Gas system]_P&I DIAGRAM | FA | 2017-02-22 | 2017-07-14 | 2017-12-15 | GRT-DS-IP-DT-170515 | FC | 2 | 2018-04-26 | 87-5th DRM | FC | 2 | A | 2017-02-13 | 2017-07-17
41 | DHI | GRT-CN00-P0ZEN-110100 | 110100 | [Plant Overall]_OPERATION PHILOSOPHY OF OVERALL PLANT | FA | 2017-07-14 | 2017-10-12 | 2020-07-10 | GRT-DS-IP-DT-200061 | FC | 1 | [5 empty] | 2017-07-19 | 2017-11-01
42 | DHI | GRT-CN00-P0ZEN-110102 | 110102 | [Plant Overall]_PLANT START - UP AND SHUT - DOWN PROCEDURE | FA | 2017-08-18 | 2017-11-16 | 2020-04-06 | GRT-DS-IP-DT-200037 | DCR | 0DCR2 | 2020-04-07 | 110102-2 | DCR | 0DCR2 | C | 2017-08-25 | 2018-01-11
43 | DHI | GRT-YR01-P0ZEN-110103 | 110103 | [Plant Overall]_STEAM BLOWING - OUT PROCEDURE | FA | 2018-02-26 | 2018-05-27 | 2020-02-07 | GRT-DS-IP-DT-200011 | FC | 2 | 2020-02-07 | 110103-2 | FC | 2 | A | 2018-03-19 | #VALUE!
44 | DHI | GRT-CN00-P0ZEN-110104 | 110104 | [Plant Overall]_Hazardous Area Classification | FA | 2017-05-30 | 2017-08-28 | 2017-08-30 | GRT-DS-IP-DT-170267 | FC | 0 | 2017-09-08 | 110104-0 | FC | 0 | A | 2017-06-05 | 2017-08-30
45 | DHI | GRT-YR01-P0ZEN-110105 | 110105 | [HP & LP steam system]_Pressure drop calculation | FA | 2017-03-30 | 2017-07-14 | 2017-07-19 | GRT-DS-IP-DT-170175 | FC | 0 | 2017-07-19 |  | FC | 0 | B | 2017-04-10 | 2017-07-19
46 | DHI | GRT-CN00-P0ZEN-110106 | 110106 | [Steam drain system]_Flash tank calculation | FA | 2017-03-30 | 2017-07-14 | 2017-07-19 | GRT-DS-IP-DT-170175 | FC | 0 | 2017-07-19 |  | FC | 0 | B | 2017-04-10 | 2017-07-19
47 | DHI | GRT-YR01-P0ZEN-110107 | 110107 | [Plant Overall]_STEAM FLUSHING - DIAGRAM | FI | 2018-04-06 | 2018-06-15 | 2018-07-19 | GRT-DS-IP-DT-180161 | FC | 0 | 2018-08-02 | 110107-0 | FC | 0 | A | 2018-05-16 | #VALUE!
48 | DHI | GRT-XW01-P0LBA-110200 | 110200 | [HP & LP steam system]_DESIGN CRITERIA | FA | 2017-02-22 | 2017-07-14 | 2017-07-17 | GRT-DS-IP-DT-170159 | FC | 0 | 2017-07-17 |  | FC | 0 | A | 2017-03-09 | 2017-07-17
49 | DHI | GRT-XW01-P0LBG-110201 | 110201 | [AUX Steam System]_DESIGN CRITERIA | FA | 2017-02-22 | 2017-07-14 | 2017-07-17 | GRT-DS-IP-DT-170159 | FC | 0 | 2017-07-17 |  | FC | 0 | A | 2017-03-09 | 2017-07-17
50 | DHI | GRT-XW01-P0LA-110202 | 110202 | [Feedwater system]_DESIGN CRITERIA | FA | 2017-02-22 | 2017-07-14 | 2017-07-05 | GRT-DS-IP-DT-170135 | FC | 0 | 2017-07-19 |  | FC | 0 | B | 2017-03-09 | 2017-07-05
51 | DHI | GRT-XW01-P0LC-110203 | 110203 | [Condensate system]_DESIGN CRITERIA | FA | 2017-02-22 | 2017-07-14 | 2017-07-05 | GRT-DS-IP-DT-170135 | FC | 0 | 2017-07-19 |  | FC | 0 | B | 2017-03-09 | 2017-07-05
52 | DHI | GRT-XW01-P0PA-110204 | 110204 | [Aux. Cooling Water System]_DESIGN CRITERIA | FA | 2017-02-22 | 2017-07-14 | 2017-07-17 | GRT-DS-IP-DT-170149 | FC | 0 | 2017-07-19 |  | FC | 0 | A | 2017-03-09 | 2017-07-17
53 | DHI | GRT-XW01-P0PG-110205 | 110205 | [Closed cooling water system]_DESIGN CRITERIA | FA | 2017-02-22 | 2017-07-14 | 2017-07-17 | GRT-DS-IP-DT-170149 | FC | 0 | 2017-07-19 |  | FC | 0 | A | 2017-03-09 | 2017-07-17
54 | DHI | GRT-XW01-P0QJA-110206 | 110206 | [N2 Gas system]_Design Criteria | FA | 2017-02-22 | 2017-07-14 | 2017-12-15 | GRT-DS-IP-DT-170515 | FC | 1 | 2018-04-26 | 81-5th DRM | FC | 1 | A | 2017-03-09 | 2017-06-20
55 | DHI | GRT-XG07-P0LBA-110300 | 110300 | [Steam, Feedwater & Condensate system]_PROCESS FLOW DIAGRAM | FA | 2017-03-15 | 2017-07-14 | 2017-07-18 | GRT-DS-IP-DT-170174 | FC | 0 | 2017-07-19 |  | FC | 0 | B | 2017-03-15 | 2017-07-18
56 | DHI | GRT-XG07-P0PA-110304 | 110304 | [Aux. & Closed Cooling Water System]_PROCESS FLOW DIAGRAM | FA | 2017-03-15 | 2017-07-14 | 2017-08-21 | GRT-DS-IP-DT-170236 | FC | 0 | 2017-08-22 |  | FC | 0 | B | 2017-03-15 | 2017-08-21
57 | DHI | GRT-XS00-P0LBA-110400 | 110400 | [HP & LP steam system]_SYSTEM DESCRIPTION | FA | 2017-02-28 | 2017-07-14 | 2017-06-20 | GRT-DS-IP-DT-170123 | FC | 0 | 2017-06-20 |  | FC | 0 | A | 2017-03-09 | 2017-06-20
58 | DHI | GRT-XS00-P0LBG-110401 | 110401 | [AUX Steam System]_SYSTEM DESCRIPTION | FA | 2017-02-28 | 2017-07-14 | 2017-06-20 | GRT-DS-IP-DT-170123 | FC | 0 | 2017-06-20 |  | FC | 0 | A | 2017-03-09 | 2017-06-20
59 | DHI | GRT-XS00-P0LA-110402 | 110402 | [Feedwater system]_SYSTEM DESCRIPTION | FA | 2017-02-28 | 2017-07-14 | 2017-07-05 | GRT-DS-IP-DT-170132 | FC | 0 | 2017-07-19 |  | FC | 0 | A | 2017-03-09 | 2017-07-06
60 | DHI | GRT-XS00-P0LC-110403 | 110403 | [Condensate system]_SYSTEM DESCRIPTION | FA | 2017-02-28 | 2017-07-14 | 2017-05-23 | GRT-DS-IP-DT-170078 | FC | 0 | 2017-06-16 | 02.031/E04/PLNE/VI/2017 | FC | 0 | B | 2017-03-09 | 2017-05-23
61 | DHI | GRT-XS00-P0PA-110404 | 110404 | [Aux. Cooling Water System]_SYSTEM DESCRIPTION | FA | 2017-02-28 | 2017-07-14 | 2017-07-17 | GRT-DS-IP-DT-170149 | FC | 0 | 2017-07-19 |  | FC | 0 | A | 2017-03-09 | 2017-07-17
62 | DHI | GRT-XS00-P0PG-110405 | 110405 | [Closed cooling water system]_SYSTEM DESCRIPTION | FA | 2017-02-28 | 2017-07-14 | 2017-07-17 | GRT-DS-IP-DT-170149 | FC | 0 | 2017-07-19 |  | FC | 0 | A | 2017-03-09 | 2017-07-17
63 | DHI | GRT-XS00-P0QJA-110406 | 110406 | [N2 Gas system]_system description | FA | 2017-02-28 | 2017-07-14 | 2017-12-15 | GRT-DS-IP-DT-170515 | FC | 1 | 2018-04-26 | 82-5th DRM | FC | 1 | A | 2017-03-09 | 2017-06-20
64 | DHI | GRT-XW03-P0LA-110500 | 110500 | [BFP_Design]_sizing Calculation | FA | 2017-03-03 | 2017-07-14 | 2017-07-17 | GRT-DS-IP-DT-170157 | FC | 0 | 2017-07-17 |  | FC | 0 | B | 2017-03-22 | 2017-07-17
65 | DHI | GRT-XW03-P0LC-110501 | 110501 | [CEP_Design]_sizing Calculation | FA | 2017-03-15 | 2017-06-13 | 2017-06-08 | GRT-DS-IP-DT-170101 | FC | 0 | 2017-06-08 | APPROVED | FC | 0 | A | 2017-03-22 | 2017-06-08
66 | DHI | GRT-YD00-P0QJA-111000 | 111000 | [N2 Gas System]_General Arrangement Drawing | FA | 2017-08-08 | 2017-11-06 | 2017-11-27 | GRT-DS-IP-DT-170483 | FC | 0 | 2018-04-26 | 42-5th DRM | FC | 0 | A | 2017-08-21 | 2017-11-27
67 | DHI | GRT-XW03-P0QJA-111001 | 111001 | [N2 Gas System_Design]_sizing Calculation | FA | 2017-04-07 | 2017-07-14 | 2017-07-19 | GRT-DS-IP-DT-170175 | FC | 0 | 2017-07-19 |  | FC | 0 | B | 2017-04-18 | 2017-07-19
68 | DHI | GRT-CT00-P0QJA-111011 | 111011 | [N2 GAS SYSTEM]_OPERATION & MAINTENANCE MANUAL | FI | 2018-04-20 | 2018-05-31 | 2018-07-05 | GRT-DS-IP-DT-180150 | FC | 0 | 2018-07-12 | 111011-1 | FC | 0 | B | 2018-05-07 | 2018-05-07
69 | DHI | GRT-YT01-P0LB-111100 | 111100 | [Bypass Valve & PRDS]_DATA SHEET FOR BYPASS AND PRDS | FA | 2017-07-14 | 2017-10-12 | 2017-12-15 | GRT-DS-IP-DT-170515 | FC | 1 | 2018-04-26 | 83-5th DRM | FC | 1 | A | 2017-07-26 | 2017-10-13
70 | DHI | GRT-YK08-P0LB-111101 | 111101 | [Bypass Valve & PRDS]_OUTLINE DRAWING FOR BYPASS AND PRDS | FA | 2017-07-14 | 2017-10-12 | 2018-08-24 | GRT-DS-IP-DT-180210 | FC | 1 | 2018-08-30 | 111101-1 | FC | 1 | A | 2017-07-26 | 2017-11-27
71 | DHI | GRT-YK08-P0LB-111102 | 111102 | [Bypass Valve & PRDS]_OUTLINE DRAWING FOR HYDRAULIC POWER UNIT | FI | 2017-07-28 | 2017-10-26 | 2020-01-18 | GRT-DS-IP-DT-200010 | FC | 2 | 2020-01-18 | 1111102-2 | FC | 2 | A | 2017-07-28 | 2017-12-04
72 | DHI | GRT-YS18-P0LB-111103 | 111103 | [Bypass Valve & PRDS]_CIRCUIT DIAGRAM FOR HYDRAULIC POWER UNIT | FI | 2017-07-28 | 2017-10-26 | 2018-08-24 | GRT-DS-IP-DT-180210 | FC | 1 | 2018-08-30 | 111103-1 | FC | 1 | A | 2017-08-30 | 2017-11-01
73 | DHI | GRT-XS01-P0LB-111105 | 111105 | [Bypass Valve & PRDS]_Operating Description for HPU system for Bypass System | FI | 2017-07-28 | 2017-10-26 | 2017-11-27 | GRT-DS-IP-DT-170472 | FC | 0 | 2018-04-26 | 44-5th DRM | FC | 0 | A | 2017-08-30 | 2017-11-27
74 | DHI | GRT-YK09-P0LB-111106 | 111106 | [Bypass Valve & PRDS]_Sectional drawing | FI | 2017-07-14 | 2017-10-12 | 2018-08-24 | GRT-DS-IP-DT-180210 | FC | 1 | 2018-08-30 | 111106-1 | FC | 1 | A | 2017-07-26 | 2017-10-13
75 | DHI | GRT-YS18-P0LB-111107 | 111107 | [Bypass Valve & PRDS]_P&ID for HPU | FA | 2017-07-28 | 2017-10-26 | 2017-11-27 | GRT-DS-IP-DT-170472 | FC | 0 | 2018-04-26 | 45-5th DRM | FC | 0 | A | 2017-07-28 | 2017-11-27
76 | DHI | GRT-YL22-P0LB-111108 | 111108 | [Bypass Valve & PRDS]_Name Plate Drawing | FA | 2017-09-14 | 2017-12-13 | 2017-11-01 | GRT-DS-IP-DT-170431 | FC | 0 | 2018-04-26 | 3-5th DRM | FC | 0 | A | 2017-09-27 | 2017-11-01
77 | DHI | GRT-XL35-P0LB-111109 | 111109 | [Bypass Valve & PRDS]_Instrument List & Database Sheet | FA | 2017-07-14 | 2017-10-12 | 2017-11-27 | GRT-DS-IP-DT-170472 | FC | 0 | 2018-04-26 | 46-5th DRM | FC | 0 | A | 2017-07-26 | 2017-11-27
78 | DHI | GRT-YT01-P0LB-111110 | 111110 | [Bypass Valve & PRDS]_Data Sheet for HPU | FA | 2017-07-28 | 2017-10-26 | 2017-11-27 | GRT-DS-IP-DT-170472 | FC | 0 | 2018-04-26 | 47-5th DRM | FC | 0 | A | 2017-07-28 | 2017-11-27
79 | DHI | GRT-YS18-P0LB-111111 | 111111 | [Bypass Valve & PRDS]_Pneumatic Diagram | FI | 2017-07-14 | 2017-10-12 | 2018-07-12 | GRT-DS-IP-DT-180173 | FC | 1 | 2018-07-19 | 111111-1 | FC | 1 | A | 2017-07-26 | 2017-12-04
80 | DHI | GRT-YS00-P0LB-111112 | 111112 | [Bypass Valve & PRDS]_Wiring Diagram | FI | 2017-07-14 | 2017-10-12 | 2020-01-18 | GRT-DS-IP-DT-200010 | FC | 2 | 2020-01-18 | 1111102-2 | FC | 2 | A | 2017-07-26 | 2017-12-04
81 | DHI | GRT-YK08-P0ZEN-111200 | 111200 | [Safety Relief Valve(DHI)]_OUTLINE DRAWING FOR SAFEY AND RELIEF VALVE | FI | 2017-09-26 | 2017-12-25 | 2017-10-13 | GRT-DS-IP-DT-170354 | FC | 0 | 2017-10-29 | 20.015/E04/PLNE/IX/2017 | FI | A | I | 2017-09-15 | 2017-10-13
82 | DHI | GRT-YT01-P0ZEN-111201 | 111201 | [Safety Relief Valve(DHI)]_DATA SHEET FOR SAFETY AND RELIEF VALVE | FA | 2017-09-26 | 2017-12-25 | 2017-10-13 | GRT-DS-IP-DT-170354 | FC | 0 | 2017-10-29 | 20.015/E04/PLNE/IX/2017 | FA | A | B | 2017-09-15 | 2017-10-13
83 | DHI | GRT-CT00-P0LB-111210 | 111210 | [Bypass]_O&M Manual | FI | 2018-04-20 | 2018-05-31 | 2018-07-05 | GRT-DS-IP-DT-180150 | FC | 0 | 2018-07-12 | 111210-1 | FC | 0 | A | 2018-05-31 | 2018-07-05
84 | DHI | GRT-YK08-P0LBG-111300 | 111300 | [Silencer]_OUTLINE DRAWING FOR SILENCER | FA | 2017-10-24 | 2018-01-22 | 2017-12-22 | GRT-DS-IP-DT-170432 | FC | 0 | 2018-04-26 | 84-5th DRM | FC | 0 | A | 2017-09-06 | 2017-12-22
85 | DHI | GRT-YT01-P0LBG-111301 | 111301 | [Silencer]_DATA SHEET FOR SILENCER | FA | 2017-10-24 | 2018-01-22 | 2017-12-22 | GRT-DS-IP-DT-170432 | FC | 0 | 2018-04-26 | 85-5th DRM | FC | 0 | A | 2017-09-06 | 2017-12-22
86 | DHI | GRT-YD00-P0PCC-113001 | 113001 | [Aux. Cooling Water Pump]_GENERAL ARRANGEMENT DRAWING FOR AUXILIARY COOLING WATER PUMP | FA | 2017-06-05 | 2017-09-03 | 2020-01-22 | GRT-DS-IP-DT-200013 | FC | 1 | 2020-01-22 | 113001-3 | FC | 1 | A | 2017-06-08 | 2017-09-14
87 | DHI | GRT-YT01-P0PCC-113002 | 113002 | [Aux. Cooling Water Pump]_DATA SHEET FOR AUXILIARY COOLING WATER PUMP | FA | 2017-06-05 | 2017-09-03 | 2020-01-22 | GRT-DS-IP-DT-200013 | FC | 1 | 2020-01-22 | 113002-3 | FC | 1 | A | 2017-06-08 | 2017-08-30
88 | DHI | GRT-YK10-P0PCC-113003 | 113003 | [Aux. Cooling Water Pump]_Pump Sectional Drawing | FA | 2017-06-05 | 2017-09-03 | 2017-08-30 | GRT-DS-IP-DT-170260 | FC | 0 | 2017-09-08 | 113003-0 | FC | 0 | A | 2017-06-08 | 2017-08-30
89 | DHI | GRT-YT01-P0PCC-113004 | 113004 | [Aux. Cooling Water Pump]_DATA SHEET FOR AUXILIARY COOLING WATER PUMP MOTOR | FA | 2017-06-05 | 2017-09-03 | 2017-08-30 | GRT-DS-IP-DT-170261 | FC | 0 | 2017-09-08 | 113004-0 | FC | 0 | B | 2017-06-14 | 2017-08-30
90 | DHI | GRT-YD00-P0PCC-113005 | 113005 | [Aux. Cooling Water Pump]_OUTLINE DRAWING FOR AUXILIARY COOLING WATER PUMP MOTOR | FA | 2017-06-05 | 2017-09-03 | 2017-11-27 | GRT-DS-IP-DT-170482 | FC | 1 | 2018-04-26 | 48-5th DRM | FC | 1 | A | 2017-06-14 | 2017-08-30
91 | DHI | GRT-YD00-P0PCC-113007 | 113007 | [Aux. Cooling Water Pump]_MAIN TERMINAL BOX DRAWING FOR AUXILIARY COOLING WATER PUMP MOTOR | FA | 2017-08-12 | 2017-11-10 | 2017-11-01 | GRT-DS-IP-DT-170426 | FC | 0 | 2017-11-02 | 113007-0 | FC | 0 | A | 2017-06-14 | 2017-11-01
92 | DHI | GRT-YL22-P0PCC-113008 | 113008 | [Aux. Cooling Water Pump]_NAMEPLATE DRAWING FOR AUXILIARY COOLING WATER PUMP | FA | 2017-08-12 | 2017-11-10 | 2017-10-13 | GRT-DS-IP-DT-170355 | FC | 0 | 2017-10-13 | 113008-0 | FC | 0 | B | 2017-07-21 | 2017-10-13
93 | DHI | GRT-YL22-P0PCC-113009 | 113009 | [Aux. Cooling Water Pump]_NAMEPLATE DRAWING FOR AUXILIARY COOLING WATER PUMP MOTOR | FA | 2017-08-12 | 2017-11-10 | 2017-10-26 | GRT-DS-IP-DT-170358 | FC | 0 | 2017-11-02 | 113009-0 | FC | 0 | A | 2017-08-15 | 2017-10-26
94 | DHI | GRT-XW03-P0PCC-113010 | 113010 | [Aux. Cooling Water Pump_Design]_SIZING CALCULATION FOR AUXILIARY COOLING WATER PUMP | FA | 2017-04-14 | 2017-09-03 | 2017-08-21 | GRT-DS-IP-DT-170236 | FC | 0 | 2017-08-22 |  | FC | 0 | B | 2017-04-18 | 2017-08-21
95 | DHI | GRT-YL22-P0PCC-113017 | 113017 | [ACWP]_OPERATION & MAINTENANCE MANUAL | FI | 2018-04-20 | 2018-05-31 | 2018-06-28 | GRT-DS-IP-DT-180152 | FC | 0 | 2018-06-29 | 113017-1 | FC | 0 | A | 2018-05-04 | 2018-06-28
96 | DHI | GRT-YD00-P0PGB-113101 | 113101 | [CCWP ]_GENERAL ARRANGEMENT DRAWING FOR CLOSED COOLING WATER PUMP | FA | 2017-06-12 | 2017-09-10 | 2017-09-14 | GRT-DS-IP-DT-170295 | FC | 0 | 2017-09-18 | 13.010/E04/PLNE/IX/2017 | FA | B | B | 2017-06-08 | 2017-09-14
97 | DHI | GRT-YT01-P0PGB-113102 | 113102 | [CCWP ]_DATA SHEET FOR CLOSED COOLING WATER PUMP | FA | 2017-06-12 | 2017-09-10 | 2017-09-14 | GRT-DS-IP-DT-170295 | FC | 0 | 2017-09-18 | 13.010/E04/PLNE/IX/2017 | FA | C | A | 2017-06-08 | 2017-09-14
98 | DHI | GRT-YK10-P0PGB-113103 | 113103 | [CCWP ]_Pump Sectional Drawing | FA | 2017-06-12 | 2017-09-10 | 2017-08-30 | GRT-DS-IP-DT-170260 | FC | 0 | 2017-09-08 | 113103-0 | FC | 0 | A | 2017-06-08 | 2017-08-30
99 | DHI | GRT-YT01-P0PGB-113104 | 113104 | [CCWP ]_DATA SHEET FOR CLOSED COOLING WATER PUMP MOTOR | FA | 2017-06-12 | 2017-09-10 | 2017-08-30 | GRT-DS-IP-DT-170261 | FC | 0 | 2017-09-08 | 113104-0 | FC | 0 | B | 2017-06-14 | 2017-08-30
100 | DHI | GRT-YD00-P0PGB-113105 | 113105 | [CCWP ]_OUTLINE DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | FA | 2017-06-12 | 2017-09-10 | 2017-11-27 | GRT-DS-IP-DT-170482 | FC | 1 | 2018-04-26 | 49-5th DRM | FC | 1 | A | 2017-06-14 | 2017-08-30
101 | DHI | GRT-YD00-P0PGB-113107 | 113107 | [CCWP ]_MAIN TERMINAL BOX DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | FA | 2017-08-12 | 2017-11-10 | 2017-11-29 | GRT-DS-IP-DT-170494 | FC | 0 | 2018-04-26 | 50-5th DRM | FC | 0 | A | 2017-06-14 | 2017-11-29
102 | DHI | GRT-YL22-P0PGB-113108 | 113108 | [CCWP ]_NAMEPLATE DRAWING FOR CLOSED COOLING WATER PUMP | FA | 2017-08-12 | 2017-11-10 | 2017-10-13 | GRT-DS-IP-DT-170355 | FC | 0 | 2017-10-13 | 113108-0 | FC | 0 | B | 2017-07-21 | 2017-10-13
103 | DHI | GRT-YL22-P0PGB-113109 | 113109 | [CCWP ]_NAMEPLATE DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | FA | 2017-08-12 | 2017-11-10 | 2017-10-26 | GRT-DS-IP-DT-170358 | FC | 0 | 2017-11-02 | 113109-0 | FC | 0 | A | 2017-08-15 | 2017-10-26
104 | DHI | GRT-XW03-P0PGB-113110 | 113110 | [CCWP_Design]_SIZING CALCULATION FOR CLOSED COOLING WATER PUMP | FA | 2017-04-14 | 2017-07-14 | 2017-09-06 | GRT-DS-IP-DT-170272 | FC | 0 | 2017-09-08 | 113110-0 | FC | 0 | B | 2017-04-18 | 2017-09-06
105 | DHI | GRT-YL22-P0PGB-113117 | 113117 | [CCWP]_OPERATION & MAINTENANCE MANUAL | FI | 2018-04-20 | 2018-05-31 | 2018-08-24 | GRT-DS-IP-DT-180211 | FC | 1 | 2018-08-30 | 113117-2 | FC | 1 | A | 2018-05-04 | 2018-06-28
106 | DHI | GRT-YT01-P0PGB-113200 | 113200 | [Blowdown Cooler]_DATA SHEET FOR PLATE TYPE HEAT EXCHANGER | FA | 2017-07-24 | 2017-10-22 | 2017-08-21 | GRT-DS-IP-DT-170239 | FC | 0 | 2017-08-22 |  | FC | 0 | B | 2017-07-06 | 2017-08-21
107 | DHI | GRT-YD00-P0PGB-113201 | 113201 | [Blowdown Cooler]_OUTLINE DRAWING FOR PLATE TYPE HEAT EXCHANGER | FA | 2017-07-24 | 2017-10-22 | 2017-11-27 | GRT-DS-IP-DT-170481 | FC | 1 | 2018-04-26 | 51-5th DRM | FC | 1 | A | 2017-07-06 | 2017-10-13
108 | DHI | GRT-YD00-P0PGB-113205 | 113205 | [Blowdown Cooler]_INSTALLATION, OPERATION AND MAINTENANCE MANUAL | FI | 2018-04-20 | 2018-05-31 | 2018-06-28 | GRT-DS-IP-DT-180152 | FC | 0 | 2018-06-29 | 113205-1 | FC | 0 | A | 2018-05-04 | 2018-06-28
109 | DHI | GRT-YK10-P0ZEN-113300 | 113300 | [MOV (Gate & Globe)(DHI)]_OUTLINE DRAWING FOR MOV (G&G) | FA | 2017-08-15 | 2017-11-13 | 2017-11-29 | GRT-DS-IP-DT-170488 | FC | 0 | 2018-04-26 | 52-5th DRM | FC | 0 | A | 2017-11-01 | 2017-11-29
110 | DHI | GRT-YT01-P0ZEN-113301 | 113301 | [MOV (Gate & Globe)(DHI)]_VALVE LIST & DATA SHEET FOR MOV (G&G) | FA | 2017-08-15 | 2017-11-13 | 2017-11-29 | GRT-DS-IP-DT-170488 | FC | 0 | 2018-04-26 | 53-5th DRM | FC | 0 | A | 2017-11-01 | 2017-11-29
111 | DHI | GRT-YK10-P0ZEN-113400 | 113400 | [MOV (Butterfly)(DHI)]_OUTLINE DRAWING FOR MOV (BUTTERFLY) | FA | 2017-08-15 | 2017-11-13 | 2017-10-26 | GRT-DS-IP-DT-170383 | FC | 0 | 2017-11-02 | 113400-0 | FC | 0 | B | 2017-09-11 | 2017-10-26
112 | DHI | GRT-YT01-P0ZEN-113401 | 113401 | [MOV (Butterfly)(DHI)]_VALVE LIST & DATA SHEET FOR MOV (BUTTERFLY) | FA | 2017-08-15 | 2017-11-13 | 2017-10-26 | GRT-DS-IP-DT-170383 | FC | 0 | 2017-11-02 | 113401-0 | FC | 0 | B | 2017-09-11 | 2017-10-26
113 | DHI | GRT-XG02-P0SC-120001 | 120001 | [Compressed air system]_P&I DIAGRAM FOR COMPRESSED AIR SYSTEM | FA | 2017-02-06 | 2017-07-14 | 2020-01-24 | GRT-DS-IP-DT-200024 | FC | 1 | 2020-01-31 | 120001-3 | FC | 1 | A | 2017-02-10 | 2017-08-15
114 | DHI | GRT-XG02-P0SC-120002 | 120002 | [Compressed air system]_P&I DIAGRAM FOR INSTRUMENT AIR SYSTEM | FA | 2017-02-06 | 2017-07-14 | 2020-01-24 | GRT-DS-IP-DT-200024 | FC | 1 | 2020-01-31 | 120002-3 | FC | 1 | A | 2017-02-10 | 2017-08-15
115 | DHI | GRT-XG02-P0SC-120003 | 120003 | [Compressed air system]_P&I DIAGRAM FOR SERVICE AIR SYSTEM | FA | 2017-02-06 | 2017-07-14 | 2020-01-24 | GRT-DS-IP-DT-200024 | FC | 2 | 2020-01-31 | 120003-3 | FC | 2 | A | 2017-02-10 | 2017-08-15
116 | DHI | GRT-XS00-P0SC-120004 | 120004 | [Compressed air system]_SYSTEM DESCRIPTION FOR COMPRESSED AIR SYSTEM | FA | 2017-02-20 | 2017-06-20 | 2017-06-16 | GRT-DS-IP-DT-170113 | FC | 0 | 2017-06-16 |  | FC | 0 | A | 2017-03-22 | 2017-06-14
117 | DHI | GRT-XS00-P0SC-120005 | 120005 | [Compressed air system]_DESIGN CRITERIA FOR COMPRESSED AIR SYSTEM | FA | 2017-02-06 | 2017-06-06 | 2017-07-20 | GRT-DS-IP-DT-170118 | FC | 1 | 2018-04-26 | 4-5th DRM | FC | 1 | A | 2017-02-22 | 2017-04-10
118 | DHI | GRT-XW03-P0SC-120006 | 120006 | [Compressed air system]_SIZING CALCULATION_COMPRESSED AIR SYSTEM | FA | 2017-02-06 | 2017-07-14 | 2017-07-24 | GRT-DS-IP-DT-170202 | FC | 0 | 2017-07-24 |  | FC | 0 | B | 2017-02-22 | 2017-07-24
119 | DHI | GRT-YD00-P0SCA-120007 | 120007 | [Air Compressor]_AIR COMPRESSOR_GENERAL ARRANGEMENT DRAWING FOR AIR COMPRESSORS PACKAGE | FA | 2017-04-20 | 2017-07-19 | 2020-01-24 | GRT-DS-IP-DT-200024 | FC | 3 | 2020-01-31 | 120007-3 | FC | 3 | A | 2017-05-17 | 2017-08-15
120 | DHI | GRT-XG02-P0SCA-120008 | 120008 | [Air Compressor]_P&I DIAGRAM FOR AIR COMPRESSOR PACKAGE | FA | 2017-04-20 | 2017-07-19 | 2017-08-15 | GRT-DS-IP-DT-170232 | FC | 0 | 2017-09-11 | 04.032/E04/PLNE/VIII/2017 | FA | B | A | 2017-05-17 | 2017-08-15
121 | DHI | GRT-XW01-P0SCA-120009 | 120009 | [Air Compressor]_AIR COMPRESSOR SPECIFICATION | FA | 2017-04-20 | 2017-07-19 | 2017-07-27 | GRT-DS-IP-DT-170203 | FC | 0 | 2017-08-03 |  | FC | 0 | A | 2017-05-17 | 2017-07-27
122 | DHI | GRT-XW01-P0SCA-120010 | 120010 | [Air Compressor]_AIR DRYER SPECIFICATION | FA | 2017-04-20 | 2017-07-19 | 2017-07-27 | GRT-DS-IP-DT-170203 | FC | 0 | 2017-08-03 |  | FC | 0 | B | 2017-05-17 | 2017-07-27
123 | DHI | GRT-XW01-P0SCA-120011 | 120011 | [Air Compressor]_AIR RECEIVER SPECIFICATION | FA | 2017-04-20 | 2017-07-19 | 2017-07-27 | GRT-DS-IP-DT-170203 | FC | 0 | 2017-08-03 |  | FC | 0 | A | 2017-05-17 | 2017-07-27
124 | DHI | GRT-XW01-P0SCA-120012 | 120012 | [Air Compressor]_AIR FILTER SPECIFICATION | FA | 2017-04-20 | 2017-07-19 | 2017-07-27 | GRT-DS-IP-DT-170203 | FC | 0 | 2017-08-03 |  | FC | 0 | A | 2017-05-17 | 2017-07-27
125 | DHI | GRT-XB00-P0SCA-120013 | 120013 | [Air Compressor]_FOUNDATION DRAWINGS | FI | 2017-04-20 | 2017-07-19 | 2017-09-15 | GRT-DS-IP-DT-170297 | FC | 1 | 2017-09-26 | 120013-0 | FC | 1 | A | 2017-05-19 | 2017-08-15
126 | DHI | GRT-YU02-P0SCA-120014 | 120014 | [Air Compressor]_SINGLE LINE DIAGRAM | FA | 2017-05-20 | 2017-09-17 | 2020-01-24 | GRT-DS-IP-DT-200024 | FC | 1 | 2020-01-31 | 120014-3 | FC | 1 | A | 2017-06-20 | 2017-09-20
127 | DHI | GRT-YV02-P0SCA-120015 | 120015 | [Air Compressor]_ELECTRICAL WIRING DIAGRAMS | FI | 2017-05-20 | 2017-10-17 | 2017-10-26 | GRT-DS-IP-DT-170394 | FC | 0 | 2017-11-02 | 120015-0 | FC | 0 | A | 2017-05-23 | 2017-10-26
128 | DHI | GRT-YU03-P0SCA-120016 | 120016 | [Air Compressor]_ELECTRICAL SCHEMATIC DIAGRAM | FI | 2017-05-20 | 2017-10-17 | 2017-10-26 | GRT-DS-IP-DT-170394 | FC | 0 | 2017-11-02 | 120016-0 | FC | 0 | A | 2017-05-23 | 2017-10-26
129 | DHI | GRT-YF02-P0SCA-120017 | 120017 | [Air Compressor]_CONTROL DESCRIPTION (PHILOSOPHY) | FA | 2017-05-20 | 2017-09-17 | 2017-09-29 | GRT-DS-IP-DT-170329 | FC | 0 | 2017-10-02 | 120017-0 | FC | 0 | B | 2017-05-23 | 2017-09-29
130 | DHI | GRT-YD05-P0SCA-120018 | 120018 | [Air Compressor]_PLC HMI GRAPHICS | FA | 2017-06-20 | 2017-10-18 | 2017-10-26 | GRT-DS-IP-DT-170394 | FC | 0 | 2017-11-02 | 120018-0 | FC | 0 | A | 2017-07-06 | 2017-10-26
131 | DHI | GRT-YL01-P0SCA-120019 | 120019 | [Air Compressor]_PLC HARDWIRED IO LIST | FA | 2017-05-20 | 2017-09-17 | 2017-09-20 | GRT-DS-IP-DT-170300 | FC | 0 | 2017-09-26 | 120019-0 | FC | 0 | B | 2017-06-02 | 2017-09-20
132 | DHI | GRT-YL01-P0SCA-120020 | 120020 | [Air Compressor]_DATALINK INTERFACE IO LIST | FA | 2017-05-20 | 2017-09-17 | 2017-09-20 | GRT-DS-IP-DT-170300 | FC | 0 | 2017-09-26 | 120020-0 | FC | 0 | B | 2017-06-02 | 2017-09-20
133 | DHI | GRT-YF00-P0SCA-120021 | 120021 | [Air Compressor]_CONTROL LOGIC & LOOP DIAGRAM | FA | 2017-05-20 | 2017-09-17 | 2017-10-26 | GRT-DS-IP-DT-170394 | FC | 0 | 2017-11-02 | 120021-0 | FC | 0 | A | 2017-06-14 | 2017-10-26
134 | DHI | GRT-YV02-P0SCA-120022 | 120022 | [Air Compressor]_I&C WIRING DIAGRAMS | FI | 2017-05-20 | 2017-10-17 | 2020-01-24 | GRT-DS-IP-DT-200024 | FC | 2 | 2020-01-31 | 120022-3 | FC | 2 | A | 2017-06-14 | 2017-10-26
135 | DHI | GRT-YL00-P0SCA-120023 | 120023 | [Air Compressor]_INSTRUMENT LIST | FA | 2017-05-20 | 2017-09-17 | 2017-09-22 | GRT-DS-IP-DT-170301 | FC | 0 | 2017-09-26 | 120023-0 | FC | 0 | A | 2017-05-30 | 2017-09-22
136 | DHI | GRT-CV03-P0SCA-120024 | 120024 | [Air Compressor]_INSTRUMENT SPECIFICATION | FA | 2017-05-20 | 2017-09-17 | 2017-09-22 | GRT-DS-IP-DT-170301 | FC | 0 | 2017-09-26 | 120024-0 | FC | 0 | A | 2017-05-30 | 2017-09-22
137 | DHI | GRT-YK00-P0SCA-120025 | 120025 | [Air Compressor]_INSTRUMENTATION HOOK - UP DRAWING | FA | 2017-05-20 | 2017-09-17 | 2017-09-22 | GRT-DS-IP-DT-170301 | FC | 0 | 2017-09-26 | 120025-0 | FC | 0 | A | 2017-06-14 | 2017-09-22
138 | DHI | GRT-YF02-P0SCA-120026 | 120026 | [Air Compressor]_PLC PANEL DRAWING | FA | 2017-05-20 | 2017-09-17 | 2017-11-27 | GRT-DS-IP-DT-170484 | FC | 0 | 2017-12-18 | 120026-0 | FC | 0 | B | 2017-06-14 | 2017-11-27
139 | DHI | GRT-XF00-P0SCA-120027 | 120027 | [Air Compressor]_NAME PLATE DRAWING | FA | 2017-06-20 | 2017-10-18 | 2017-10-26 | GRT-DS-IP-DT-170394 | FC | 0 | 2017-11-02 | 120027-0 | FC | 0 | A | 2017-07-06 | 2017-10-26
140 | DHI | GRT-XN00-P0SCA-120028 | 120028 | [Air Compressor]_VALVE LIST | FI | 2017-05-20 | 2017-10-17 | 2017-10-26 | GRT-DS-IP-DT-170394 | FC | 0 | 2017-11-02 | 120028-0 | FC | 0 | A | 2017-05-30 | 2017-10-26
141 | DHI | GRT-XW01-P0SCA-120029 | 120029 | [Air Compressor]_VALVE SPECIFICATION | FI | 2017-05-20 | 2017-10-17 | 2017-10-26 | GRT-DS-IP-DT-170394 | FC | 0 | 2017-11-02 | 120029-0 | FC | 0 | A | 2017-06-14 | 2017-10-26
142 | DHI | GRT-CQ02-P0SCA-120030 | 120030 | [Air Compressor]_O & M MANUAL | FA | 2017-07-20 | 2017-11-17 | 2017-11-27 | GRT-DS-IP-DT-170484 | FC | 0 | 2017-12-18 | 120030-0 | FC | 0 | A | 2017-09-15 | 2017-11-27
143 | DHI | GRT-XW01-P0SCA-120031 | 120031 | [Air Compressor]_MAIN MOTOR SPECIFICATION | FA | 2017-08-30 | 2017-10-30 | 2017-11-01 | GRT-DS-IP-DT-170438 | FC | 0 | 2017-11-02 | 120031-0 | FC | 0 | A | 2017-09-14 | 2017-11-01
144 | DHI | GRT-YD00-P0LCB-121001 | 121001 | [Condensate Extraction Pump]_GENERAL ARRANGEMENT DRAWING | FA | 2017-04-20 | 2017-07-20 | 2017-10-26 | GRT-DS-IP-DT-170376 | FC | 0 | 2018-04-26 | 5-5th DRM | FC | 0 | A | 2017-05-19 | 2017-10-26
145 | DHI | GRT-XG02-P0LCB-121002 | 121002 | [Condensate Extraction Pump]_P&I DIAGRAM | FA | 2017-04-20 | 2017-07-20 | 2017-11-27 | GRT-DS-IP-DT-170469 | FC | 1 | 2017-12-18 | 121002-1 | FC | 1 | A | 2017-05-19 | 2017-08-15
146 | DHI | GRT-YT01-P0LCB-121003 | 121003 | [Condensate Extraction Pump]_DATA SHEET & CHARACTERISTIC CURVE | FI | 2017-04-20 | 2017-07-20 | 2017-11-01 | GRT-DS-IP-DT-170443 | FC | 1 | 2018-04-26 | 6-5th DRM | FC | 1 | A | 2017-05-19 | 2017-08-15
147 | DHI | GRT-YK09-P0LCB-121004 | 121004 | [Condensate Extraction Pump]_PUMP SECTIONAL DRAWING | FA | 2017-05-20 | 2017-08-20 | 2017-08-21 | GRT-DS-IP-DT-170234 | FC | 0 | 2017-08-22 |  | FC | 0 | A | 2017-05-26 | 2017-08-21
148 | DHI | GRT-YT01-P0LCB-121005 | 121005 | [Condensate Extraction Pump]_MECHANICAL SEAL SPECIFICATION | FA | 2017-06-20 | 2017-09-20 | 2017-11-01 | GRT-DS-IP-DT-170443 | FC | 1 | 2018-04-26 | 7-5th DRM | FC | 1 | A | 2017-07-06 | 2017-08-23
149 | DHI | GRT-YT01-P0LCB-121006 | 121006 | [Condensate Extraction Pump]_COUPLING SPECIFICATION | FI | 2017-05-20 | 2017-08-20 | 2017-08-21 | GRT-DS-IP-DT-170234 | FC | 0 | 2017-08-22 |  | FC | 0 | A | 2017-05-26 | 2017-08-21
150 | DHI | GRT-YT01-P0LCB-121007 | 121007 | [Condensate Extraction Pump]_SUCTION STRAINER SPECIFICATION | FI | 2017-06-20 | 2017-09-20 | 2017-11-27 | GRT-DS-IP-DT-170469 | FC | 0 | 2017-12-18 | 121007-0 | FC | 0 | A | 2017-07-06 | 2017-11-27
151 | DHI | GRT-YD00-P0LCB-121008 | 121008 | [Condensate Extraction Pump]_FOUNDATION DRAWINGS | FA | 2017-04-20 | 2017-07-20 | 2017-08-15 | GRT-DS-IP-DT-170233 | FC | 0 | 2017-08-25 |  | FC | 0 | A | 2017-05-19 | 2017-08-15
152 | DHI | GRT-YM01-P0LCB-121009 | 121009 | [Condensate Extraction Pump]_MOTOR DATA SHEET & CHARACTERISTIC CURVE | FA | 2017-05-20 | 2017-09-20 | 2017-11-01 | GRT-DS-IP-DT-170443 | FC | 0 | 2018-04-26 | 8-5th DRM | FC | 0 | A | 2017-05-26 | 2017-11-01
153 | DHI | GRT-YL00-P0LCB-121010 | 121010 | [Condensate Extraction Pump]_INSTRUMENT LIST | FI | 2017-06-20 | 2017-10-20 | 2017-10-26 | GRT-DS-IP-DT-170411 | FC | 0 | 2017-11-02 | 121010-0 | FC | 0 | A | 2017-07-12 | 2017-10-26
154 | DHI | GRT-YK00-P0LCB-121011 | 121011 | [Condensate Extraction Pump]_INSTRUMENTATION HOOK - UP DRAWING | FI | 2017-06-20 | 2017-10-20 | 2017-11-27 | GRT-DS-IP-DT-170469 | FC | 0 | 2017-12-18 | 121011-0 | FC | 0 | A | 2017-07-12 | 2017-11-27
155 | DHI | GRT-YL22-P0LCB-121012 | 121012 | [Condensate Extraction Pump]_NAME PLATE DRAWING | FI | 2017-06-20 | 2017-10-20 | 2017-10-26 | GRT-DS-IP-DT-170411 | FC | 0 | 2017-11-02 | 121012-0 | FC | 0 | A | 2017-07-06 | 2017-10-26
156 | DHI | GRT-CQ02-P0LCB-121013 | 121013 | [Condensate Extraction Pump]_O&M MANUAL | FA | 2018-01-22 | 2018-04-22 | 2018-10-02 | GRT-DS-IP-DT-180231 | FC | 1 | 2018-10-02 | 121013-2 | FC | 1 | A | 2018-03-01 | 2018-04-25
157 | DHI | GRT-YD00-P0LCB-121014 | 121014 | [Condensate Extraction Pump]_VFD OUTLINE AND DATA SHEET | FI | 2017-08-25 | 2017-10-25 | 2017-12-15 | GRT-DS-IP-DT-170514 | FC | 1 | 2018-04-26 | 76-5th DRM | FC | 1 | A | 2017-10-10 | 2017-11-01
158 | DHI | GRT-XG02-P0LAC-122001 | 122001 | [HP Feed Water Pump]_P&I DIAGRAM | FA | 2017-04-20 | 2017-07-20 | 2017-11-01 | GRT-DS-IP-DT-170417 | FC | 0 | 2018-04-26 | 33-5th DRM | FC | 0 | A | 2017-05-19 | 2017-11-01
159 | DHI | GRT-YD00-P0LAC-122002 | 122002 | [HP Feed Water Pump]_GENERAL ARRANGEMENT DRAWING | FA | 2017-05-20 | 2017-08-20 | 2017-11-01 | GRT-DS-IP-DT-170417 | FC | 0 | 2018-04-26 | 9-5th DRM | FC | 0 | A | 2017-05-30 | 2017-11-01
160 | DHI | GRT-YT01-P0LAC-122003 | 122003 | [HP Feed Water Pump]_DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | FA | 2017-04-20 | 2017-07-20 | 2017-11-13 | GRT-DS-IP-DT-170452 | FC | 0 | 2017-11-13 | 122003-0 | FC | 0 | B | 2017-05-19 | 2017-11-13
161 | DHI | GRT-YK10-P0LAC-122004 | 122004 | [HP Feed Water Pump]_SECTIONAL DRAWING FOR PUMP | FA | 2017-05-20 | 2017-08-20 | 2017-09-25 | GRT-DS-IP-DT-170315 | FC | 0 | 2017-09-26 | 122004-0 | FC | 0 | A | 2017-05-30 | 2017-09-25
162 | DHI | GRT-YT01-P0LAC-122005 | 122005 | [HP Feed Water Pump]_DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | FA | 2017-04-20 | 2017-07-20 | 2017-11-01 | GRT-DS-IP-DT-170417 | FC | 0 | 2018-04-26 | 10-5th DRM | FC | 0 | A | 2017-05-19 | 2017-11-01
163 | DHI | GRT-YT02-P0LAC-122006 | 122006 | [HP Feed Water Pump]_LIST AND DATA SHEET FOR INSTRUMENT | FA | 2017-06-20 | 2017-10-20 | 2017-10-26 | GRT-DS-IP-DT-170405 | FC | 0 | 2017-11-02 | 122006-0 | FC | 0 | A | 2017-07-28 | 2017-10-26
164 | DHI | GRT-YL22-P0LAC-122007 | 122007 | [HP Feed Water Pump]_NAME PLATE DRAWING | FA | 2017-06-20 | 2017-09-20 | 2017-09-25 | GRT-DS-IP-DT-170318 | FC | 0 | 2017-09-26 | 122007-0 | FC | 0 | A | 2017-07-28 | 2017-09-25
165 | DHI | GRT-YL22-P0LAC-122008 | 122008 | [HP Feed Water Pump]_Hydraulic Coupling Data Sheet | FA | 2017-10-31 | 2017-11-30 | 2018-07-19 | GRT-DS-IP-DT-180174 | FC | 1 | 2018-08-02 | 122008-1 | FC | 1 | A | 2017-11-13 | 2017-11-27
166 | DHI | GRT-CQ02-P0LAC-122022 | 122022 | [HP Feed Water Pump]_Operational & Maintenance Manual | FI | 2018-04-20 | 2018-05-31 | 2018-08-16 | GRT-DS-IP-DT-180202 | FC | 0 | 2018-08-30 | 122022-1 | FC | 0 | A | 2018-07-05 | #VALUE!
167 | DHI | GRT-XG02-P0LAC-122501 | 122501 | [LP Feed Water Pump]_P&I DIAGRAM | FA | 2017-04-20 | 2017-07-20 | 2017-11-01 | GRT-DS-IP-DT-170417 | FC | 0 | 2018-04-26 | 40-5th DRM | FC | 0 | A | 2017-05-19 | 2017-11-01
168 | DHI | GRT-YD00-P0LAC-122502 | 122502 | [LP Feed Water Pump]_GENERAL ARRANGEMENT DRAWING | FA | 2017-05-20 | 2017-08-20 | 2017-11-01 | GRT-DS-IP-DT-170417 | FC | 0 | 2018-04-26 | 11-5th DRM | FC | 0 | A | 2017-05-30 | 2017-11-01
169 | DHI | GRT-YT01-P0LAC-122503 | 122503 | [LP Feed Water Pump]_DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | FA | 2017-04-20 | 2017-07-20 | 2017-11-13 | GRT-DS-IP-DT-170452 | FC | 0 | 2017-11-13 | 122503-0 | FC | 0 | B | 2017-05-19 | 2017-11-13
170 | DHI | GRT-YK10-P0LAC-122504 | 122504 | [LP Feed Water Pump]_SECTIONAL DRAWING FOR PUMP | FA | 2017-05-20 | 2017-08-20 | 2017-11-01 | GRT-DS-IP-DT-170417 | FC | 0 | 2018-04-26 | 12-5th DRM | FC | 0 | A | 2017-05-30 | 2017-11-01
171 | DHI | GRT-YT01-P0LAC-122505 | 122505 | [LP Feed Water Pump]_DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | FA | 2017-04-20 | 2017-07-20 | 2017-11-01 | GRT-DS-IP-DT-170417 | FC | 0 | 2018-04-26 | 13-5th DRM | FC | 0 | A | 2017-05-19 | 2017-11-01
172 | DHI | GRT-YT02-P0LAC-122506 | 122506 | [LP Feed Water Pump]_LIST AND DATA SHEET FOR INSTRUMENT | FA | 2017-06-20 | 2017-10-20 | 2017-10-26 | GRT-DS-IP-DT-170405 | FC | 0 | 2017-11-02 | 122506-0 | FC | 0 | A | 2017-07-28 | 2017-10-26
173 | DHI | GRT-YL22-P0LAC-122507 | 122507 | [LP Feed Water Pump]_NAME PLATE DRAWING | FA | 2017-06-20 | 2017-09-20 | 2017-09-25 | GRT-DS-IP-DT-170318 | FC | 0 | 2017-09-26 | 122507-0 | FC | 0 | A | 2017-07-28 | 2017-09-25
174 | DHI | GRT-YD00-P0LAC-122508 | 122508 | [LP Feed Water Pump]_VFD OUTLINE AND DATA SHEET | FI | 2017-08-25 | 2017-10-25 | 2018-07-26 | GRT-DS-IP-DT-180187 | FC | 1 | 2018-08-02 | 122508-1 | FC | 1 | A | 2017-10-13 | 2017-12-22
175 | DHI | GRT-CQ02-P0LAC-122522 | 122522 | [LP Feed Water Pump]_Operational & Maintenance Manual | FI | 2018-04-20 | 2018-05-31 | 2018-08-16 | GRT-DS-IP-DT-180202 | FC | 0 | 2018-08-30 | 122522-1 | FC | 0 | A | 2018-07-05 | #VALUE!
176 | DHI | GRT-YD00-P0SM-123001 | 123001 | [Crane & Hoist(DHI)]_HOIST_GA DRAWING FOR HOISTS | FA | 2017-05-19 | 2017-08-18 | 2017-10-26 | GRT-DS-IP-DT-170379 | FC | 0 | 2017-11-02 | 123001-0 | FC | 0 | B | 2017-06-21 | 2017-10-26
177 | DHI | GRT-YT01-P0SM-123002 | 123002 | [Crane & Hoist(DHI)]_HOIST_DATA SHEETS FOR HOISTS | FA | 2017-05-19 | 2017-08-18 | 2017-10-26 | GRT-DS-IP-DT-170379 | FC | 0 | 2017-11-02 | 123002-0 | FC | 0 | B | 2017-06-21 | 2017-10-26
178 | DHI | GRT-CQ02-P0SM-123003 | 123003 | [Crane & Hoist(DHI)]_HOIST_O&M MANUAL FOR HOIST | FI | 2018-04-20 | 2018-05-31 | 2018-06-05 | GRT-DS-IP-DT-180144 | FC | 0 | 2018-06-08 | 123003-1 | FC | 0 | A | 2018-05-04 | 2018-06-05
179 | DHI | GRT-XG02-P0QC-130001 | 130001 | [Chemical Dosing System]_P&ID | FA | 2017-07-11 | 2017-10-23 | 2018-01-19 | GRT-DS-IP-DT-180016 | FC | 1 | 2018-01-24 | 130001-1 | FC | 1 | A | 2017-07-13 | 2017-11-01
180 | DHI | GRT-XA00-P0QC-130002 | 130002 | [Chemical Dosing System]_GENERAL ARRANGEMENT DRAWING | FA | 2017-07-11 | 2017-10-23 | 2018-01-19 | GRT-DS-IP-DT-180016 | FC | 1 | 2018-01-24 | 130002-1 | FC | 1 | A | 2017-07-13 | 2017-11-01
181 | DHI | GRT-XS00-P0QC-130003 | 130003 | [Chemical Dosing System]_SYSTEM DESCRIPTION | FA | 2017-07-11 | 2017-10-23 | 2018-01-19 | GRT-DS-IP-DT-180016 | FC | 1 | 2018-01-24 | 130003-1 | FC | 1 | A | 2017-07-13 | 2017-11-01
182 | DHI | GRT-CC07-P0QC-130004 | 130004 | [Chemical Dosing System]_CALCULATION SHEET | FA | 2017-07-11 | 2017-10-23 | 2017-11-01 | GRT-DS-IP-DT-170421 | FC | 0 | 2017-11-03 | 130004-0 | FC | 0 | B | 2017-07-13 | 2017-11-01
183 | DHI | GRT-YD00-P0QC-130005 | 130005 | [Chemical Dosing System]_CONTROL PANEL ARRANGEMENT DRAWING | FA | 2017-07-11 | 2017-10-23 | 2018-02-27 | GRT-DS-IP-DT-180046 | FC | 1 | 2018-03-06 | 130005-1 | FC | 1 | A | 2017-07-13 | 2017-11-01
184 | DHI | GRT-YF02-P0QC-130006 | 130006 | [Chemical Dosing System]_CONTROL CONFIGURATION DIAGRAM | FA | 2017-07-11 | 2017-10-23 | 2017-12-22 | GRT-DS-IP-DT-170540 | FC | 1 | 2018-04-26 | 88-5th DRM | FC | 1 | A | 2017-07-13 | 2017-11-30
185 | DHI | GRT-YL00-P0QC-130007 | 130007 | [Chemical Dosing System]_INSTRUMENT LIST | FI | 2017-07-11 | 2017-10-23 | 2018-01-19 | GRT-DS-IP-DT-180016 | FC | 1 | 2018-04-26 | 122-5th DRM | FC | 1 | A | 2017-07-13 | 2017-11-01
186 | DHI | GRT-XN00-P0QC-130008 | 130008 | [Chemical Dosing System]_VALVE LIST | FI | 2017-07-11 | 2017-10-23 | 2018-02-27 | GRT-DS-IP-DT-180046 | FC | 1 | 2018-03-01 | 130008-1 | FC | 1 | A | 2017-07-13 | 2017-11-01
187 | DHI | GRT-XB02-P0QC-130009 | 130009 | [Chemical Dosing System]_FOUNDATION AND LOADING DATA | FI | 2017-08-10 | 2017-11-22 | 2018-01-19 | GRT-DS-IP-DT-180016 | FC | 1 | 2018-01-29 | 130009-1 | FC | 1 | B | 2017-09-06 | 2017-11-30
188 | DHI | GRT-YK10-P0QC-130010 | 130010 | [Chemical Dosing System]_EQUIPMENT ASSEMBLY DRAWING | FI | 2017-08-10 | 2017-11-22 | 2018-03-21 | GRT-DS-IP-DT-180071 | FC | 2 | 2018-03-27 | 130010-2 | FC | 2 | A | 2017-09-06 | 2017-11-30
189 | DHI | GRT-XH01-P0QC-130011 | 130011 | [Chemical Dosing System]_PIPING ARRANGEMENT DRAWING | FI | 2017-08-10 | 2017-11-22 | 2018-01-19 | GRT-DS-IP-DT-180016 | FC | 1 | 2018-01-24 | 130011-1 | FC | 1 | A | 2017-08-23 | 2017-11-30
190 | DHI | GRT-YT01-P0QC-130012 | 130012 | [Chemical Dosing System]_TECHNICAL DATASHEET | FA | 2017-08-10 | 2017-11-22 | 2017-11-13 | GRT-DS-IP-DT-170458 | FC | 0 | 2017-11-13 | 130012-0 | FC | 0 | A | 2017-09-06 | 2017-11-13
191 | DHI | GRT-YT01-P0QC-130013 | 130013 | [Chemical Dosing System]_MOTOR DATA SHEET | FA | 2017-08-10 | 2017-11-22 | 2017-11-13 | GRT-DS-IP-DT-170458 | FC | 0 | 2017-11-13 | 130013-0 | FC | 0 | A | 2017-08-23 | 2017-11-13
192 | DHI | GRT-YT01-P0QC-130014 | 130014 | [Chemical Dosing System]_PUMP DATA SHEET | FA | 2017-08-10 | 2017-11-22 | 2017-11-30 | GRT-DS-IP-DT-170498 | FC | 0 | 2017-12-18 | 130014-0 | FC | 0 | B | 2017-08-23 | 2017-11-30
193 | DHI | GRT-YT01-P0QC-130015 | 130015 | [Chemical Dosing System]_VALVE DATA SHEET | FA | 2017-08-10 | 2017-11-22 | 2018-02-27 | GRT-DS-IP-DT-180046 | FC | 1 | 2018-03-01 | 130015-1 | FC | 1 | A | 2017-08-23 | 2017-11-30
194 | DHI | GRT-YT01-P0QC-130016 | 130016 | [Chemical Dosing System]_INSTRUMENT DATA SHEET | FA | 2017-08-10 | 2017-11-22 | 2018-02-27 | GRT-DS-IP-DT-180046 | FC | 1 | 2018-03-01 | 130016-1 | FC | 1 | A | 2017-08-23 | 2017-11-30
195 | DHI | GRT-YV02-P0QC-130017 | 130017 | [Chemical Dosing System]_INTERCONNECTION WIRING DIAGRAM | FI | 2017-09-09 | 2017-12-22 | 2019-04-01 | GRT-DS-IP-DT-190055 | FC | 1 | 2019-04-01 | 130017-2 | FC | 1 | A | 2017-09-15 | 2017-12-22
196 | DHI | GRT-YL22-P0QC-130018 | 130018 | [Chemical Dosing System]_NAME PLATE DRAWING | FI | 2017-09-09 | 2017-12-22 | 2018-03-21 | GRT-DS-IP-DT-180074 | FC | 1 | 2018-03-27 | 130018-1 | FC | 1 | A | 2017-09-15 | 2017-12-22
197 | DHI | GRT-YF00-P0QC-130019 | 130019 | [Chemical Dosing System]_CONTROL LOOP & LOGIC DIAGRAM | FI | 2017-09-09 | 2017-12-22 | 2018-02-27 | GRT-DS-IP-DT-180046 | FC | 1 | 2018-03-01 | 130019-1 | FC | 1 | A | 2017-09-15 | 2017-12-22
198 | DHI | GRT-YS01-P0QC-130020 | 130020 | [Chemical Dosing System]_SCHEMATIC DIAGRAM | FI | 2017-09-09 | 2017-12-22 | 2019-02-13 | GRT-DS-IP-DT-190024 | FC | 2 | 2019-02-13 | 130020-3 | FC | 2 | A | 2017-09-15 | 2017-12-22
199 | DHI | GRT-YE00-P0QC-130021 | 130021 | [Chemical Dosing System]_CABLE TRAY LAYOUT DRAWING | FI | 2017-09-09 | 2017-12-22 | 2017-12-22 | GRT-DS-IP-DT-170538 | FC | 0 | 2018-04-26 | 90-5th DRM | FC | 0 | A | 2017-09-15 | 2017-12-22
200 | DHI | GRT-YK00-P0QC-130022 | 130022 | [Chemical Dosing System]_HOOK UP DRAWING | FI | 2017-09-09 | 2017-12-22 | 2018-03-21 | GRT-DS-IP-DT-180071 | FC | 2 | 2018-03-27 | 130022-2 | FC | 2 | A | 2017-09-15 | 2017-12-22
201 | DHI | GRT-CQ02-P0QC-130023 | 130023 | [Chemical Dosing System]_O&M MANUAL | FI | 2018-01-17 | 2018-05-01 | 2018-04-27 | GRT-DS-IP-DT-180118 | FC | 0 | 2018-05-04 | 130023-2 | FC | 0 | B | 2018-01-17 | 2018-04-27
202 | DHI | GRT-XG02-P0QU-130024 | 130024 | [Sampling System]_P&ID | FA | 2017-06-20 | 2017-10-02 | 2017-11-27 | GRT-DS-IP-DT-170470 | FC | 0 | 2018-04-26 | 54-5th DRM | FC | 0 | A | 2017-07-06 | 2017-11-27
203 | DHI | GRT-XA00-P0QU-130025 | 130025 | [Sampling System]_GENERAL ARRANGEMENT DRAWING | FA | 2017-06-20 | 2017-10-02 | 2018-04-02 | GRT-DS-IP-DT-180079 | FC | 1 | 2018-04-13 | 130025-1 | FC | 1 | A | 2017-07-06 | 2017-11-27
204 | DHI | GRT-XS00-P0QU-130026 | 130026 | [Sampling System]_SYSTEM DESCRIPTION | FA | 2017-06-20 | 2017-10-02 | 2017-11-27 | GRT-DS-IP-DT-170470 | FC | 0 | 2018-04-26 | 14-5th DRM | FC | 0 | A | 2017-07-06 | 2017-11-27
205 | DHI | GRT-YF02-P0QU-130027 | 130027 | [Sampling System]_CONTROL CONFIGURATION DIAGRAM | FA | 2017-07-20 | 2017-11-01 | 2017-11-27 | GRT-DS-IP-DT-170470 | FC | 0 | 2018-04-26 | 15-5th DRM | FC | 0 | A | 2017-07-26 | 2017-11-27
206 | DHI | GRT-YL00-P0QU-130028 | 130028 | [Sampling System]_INSTRUMENT LIST | FI | 2017-07-20 | 2017-11-01 | 2017-11-27 | GRT-DS-IP-DT-170470 | FC | 0 | 2018-04-26 | 16-5th DRM | FC | 0 | A | 2017-07-26 | 2017-11-27
207 | DHI | GRT-XN00-P0QU-130029 | 130029 | [Sampling System]_VALVE LIST | FI | 2017-07-20 | 2017-11-01 | 2017-11-27 | GRT-DS-IP-DT-170470 | FC | 0 | 2018-04-26 | 55-5th DRM | FC | 0 | A | 2017-07-26 | 2017-11-27
208 | DHI | GRT-YT01-P0QU-130030 | 130030 | [Sampling System]_TECHNICAL DATASHEET | FA | 2017-08-19 | 2017-12-01 | 2017-11-27 | GRT-DS-IP-DT-170470 | FC | 0 | 2018-04-26 | 17-5th DRM | FC | 0 | A | 2017-08-23 | 2017-11-27
209 | DHI | GRT-YT01-P0QU-130031 | 130031 | [Sampling System]_INSTRUMENT DATA SHEET | FA | 2017-08-19 | 2017-12-01 | 2017-11-27 | GRT-DS-IP-DT-170470 | FC | 0 | 2018-04-26 | 18-5th DRM | FC | 0 | A | 2017-08-23 | 2017-11-27
210 | DHI | GRT-YV02-P0QU-130032 | 130032 | [Sampling System]_INTERCONNECTION WIRING DIAGRAM | FI | 2017-09-18 | 2017-12-31 | 2018-04-13 | GRT-DS-IP-DT-180097 | FC | 1 | 2018-04-25 | 130032-1 | FC | 1 | A | 2017-09-29 | 2017-11-13
211 | DHI | GRT-YF00-P0QU-130033 | 130033 | [Sampling System]_CONTROL LOOP & LOGIC DIAGRAM | FI | 2017-09-18 | 2017-12-31 | 2017-11-13 | GRT-DS-IP-DT-170446 | FC | 0 | 2017-11-13 | 130033-0 | FC | 0 | A | 2017-09-29 | 2017-11-13
212 | DHI | GRT-YS01-P0QU-130034 | 130034 | [Sampling System]_SCHEMATIC DIAGRAM | FI | 2017-09-18 | 2017-12-31 | 2018-04-13 | GRT-DS-IP-DT-180097 | FC | 1 | 2018-04-25 | 130034-1 | FC | 1 | A | 2017-09-29 | 2017-11-29
213 | DHI | GRT-CQ02-P0QU-130035 | 130035 | [Sampling System]_O&M MANUAL | FI | 2017-12-17 | 2018-03-31 | 2018-04-02 | GRT-DS-IP-DT-180079 | FC | 0 | 2018-04-13 | 130035-1 | FC | 0 | A | 2017-12-05 | 2018-04-02
214 | DHI | GRT-XG02-P0LDB-130036 | 130036 | [Condensate Filter System]_P&ID | FA | 2017-05-26 | 2017-09-08 | 2018-03-12 | GRT-DS-IP-DT-180065 | FC | 1 | 2018-03-22 | 130036-1 | FC | 1 | A | 2017-05-30 | 2017-11-01
215 | DHI | GRT-XA00-P0LDB-130037 | 130037 | [Condensate Filter System]_GENERAL ARRANGEMENT DRAWING | FA | 2017-05-26 | 2017-09-08 | 2018-03-12 | GRT-DS-IP-DT-180065 | FC | 1 | 2018-03-22 | 130037-1 | FC | 1 | A | 2017-05-30 | 2017-11-01
216 | DHI | GRT-XS00-P0LDB-130038 | 130038 | [Condensate Filter System]_SYSTEM DESCRIPTION | FA | 2017-05-26 | 2017-09-08 | 2017-11-01 | GRT-DS-IP-DT-170434 | FC | 0 | 2018-04-26 | 19-5th DRM | FC | 0 | A | 2017-05-30 | 2017-11-01
217 | DHI | GRT-CC07-P0LDB-130039 | 130039 | [Condensate Filter System]_CALCULATION SHEET | FA | 2017-05-26 | 2017-09-08 | 2017-11-01 | GRT-DS-IP-DT-170434 | FC | 0 | 2018-04-26 | 20-5th DRM | FC | 0 | A | 2017-05-30 | 2017-11-01
218 | DHI | GRT-YD00-P0LDB-130040 | 130040 | [Condensate Filter System]_CONTROL PANEL ARRANGEMENT DRAWING | FA | 2017-06-26 | 2017-10-08 | 2018-04-25 | GRT-DS-IP-DT-180110 | FC | 2 | 2018-04-27 | 130040-2 | FC | 2 | A | 2017-07-13 | 2017-11-30
219 | DHI | GRT-YF02-P0LDB-130041 | 130041 | [Condensate Filter System]_CONTROL CONFIGURATION DIAGRAM | FA | 2017-06-26 | 2017-10-08 | 2017-11-29 | GRT-DS-IP-DT-170489 | FC | 0 | 2018-04-26 | 56-5th DRM | FC | 0 | A | 2017-07-13 | 2017-11-29
220 | DHI | GRT-YL00-P0LDB-130042 | 130042 | [Condensate Filter System]_INSTRUMENT LIST | FI | 2017-06-26 | 2017-10-08 | 2017-11-01 | GRT-DS-IP-DT-170434 | FC | 0 | 2018-04-26 | 21-5th DRM | FC | 0 | A | 2017-07-13 | 2017-11-01
221 | DHI | GRT-XN00-P0LDB-130043 | 130043 | [Condensate Filter System]_VALVE LIST | FI | 2017-06-26 | 2017-10-08 | 2017-11-27 | GRT-DS-IP-DT-170474 | FC | 0 | 2018-04-26 | 57-5th DRM | FC | 0 | A | 2017-07-13 | 2017-11-27
222 | DHI | GRT-XB02-P0LDB-130044 | 130044 | [Condensate Filter System]_FOUNDATION AND LOADING DATA | FI | 2017-06-26 | 2017-10-08 | 2018-03-12 | GRT-DS-IP-DT-180065 | FC | 1 | 2018-03-22 | 130044-1 | FC | 1 | A | 2017-07-13 | 2017-11-01
223 | DHI | GRT-YK10-P0LDB-130045 | 130045 | [Condensate Filter System]_EQUIPMENT ASSEMBLY DRAWING | FI | 2017-06-26 | 2017-10-08 | 2017-12-08 | GRT-DS-IP-DT-170500 | FC | 0 | 2017-12-08 | 130045-0 | FC | 0 | A | 2017-07-13 | 2017-12-08
224 | DHI | GRT-XH01-P0LDB-130046 | 130046 | [Condensate Filter System]_PIPING ARRANGEMENT DRAWING | FI | 2017-06-26 | 2017-10-08 | 2017-11-30 | GRT-DS-IP-DT-170497 | FC | 0 | 2018-04-26 | 58-5th DRM | FC | 0 | A | 2017-07-13 | 2017-11-30
225 | DHI | GRT-YT01-P0LDB-130047 | 130047 | [Condensate Filter System]_TECHNICAL DATASHEET | FA | 2017-07-25 | 2017-11-07 | 2017-11-27 | GRT-DS-IP-DT-170474 | FC | 0 | 2018-04-26 | 59-5th DRM | FC | 0 | A | 2017-07-26 | 2017-11-27
226 | DHI | GRT-YT01-P0LDB-130050 | 130050 | [Condensate Filter System]_VALVE DATA SHEET | FA | 2017-07-25 | 2017-11-07 | 2017-11-27 | GRT-DS-IP-DT-170474 | FC | 0 | 2018-04-26 | 60-5th DRM | FC | 0 | A | 2017-07-26 | 2017-11-27
227 | DHI | GRT-YT01-P0LDB-130051 | 130051 | [Condensate Filter System]_INSTRUMENT DATA SHEET | FA | 2017-07-25 | 2017-11-07 | 2017-11-13 | GRT-DS-IP-DT-170444 | FC | 0 | 2017-11-13 | 130051-0 | FC | 0 | A | 2017-07-26 | 2017-11-13
228 | DHI | GRT-YV02-P0LDB-130052 | 130052 | [Condensate Filter System]_INTERCONNECTION WIRING DIAGRAM | FI | 2017-08-24 | 2017-12-07 | 2018-03-12 | GRT-DS-IP-DT-180065 | FC | 1 | 2018-03-22 | 130052-1 | FC | 1 | A | 2017-09-29 | 2017-12-22
229 | DHI | GRT-YL22-P0LDB-130053 | 130053 | [Condensate Filter System]_NAME PLATE DRAWING | FI | 2017-08-24 | 2017-12-07 | 2018-03-12 | GRT-DS-IP-DT-180065 | FC | 1 | 2018-03-22 | 130053-1 | FC | 1 | A | 2017-09-06 | 2017-11-30
230 | DHI | GRT-YF00-P0LDB-130054 | 130054 | [Condensate Filter System]_CONTROL LOOP & LOGIC DIAGRAM | FI | 2017-08-24 | 2017-12-07 | 2018-03-12 | GRT-DS-IP-DT-180065 | FC | 1 | 2018-03-22 | 130054-1 | FC | 1 | A | 2017-10-13 | 2017-12-22
231 | DHI | GRT-YS01-P0LDB-130055 | 130055 | [Condensate Filter System]_SCHEMATIC DIAGRAM | FI | 2017-08-24 | 2017-12-07 | 2020-01-15 | GRT-DS-IP-DT-200003 | FC | 3 | 2020-01-15 | 130055-3 | FC | 3 | A | 2017-09-29 | 2017-12-22
232 | DHI | GRT-YE00-P0LDB-130056 | 130056 | [Condensate Filter System]_CABLE TRAY LAYOUT DRAWING | FI | 2017-08-24 | 2017-12-07 | 2018-03-12 | GRT-DS-IP-DT-180065 | FC | 1 | 2018-03-22 | 130056-1 | FC | 1 | A | 2017-10-13 | 2017-12-22
233 | DHI | GRT-YK00-P0LDB-130057 | 130057 | [Condensate Filter System]_HOOK UP DRAWING | FI | 2017-08-24 | 2017-12-07 | 2017-11-13 | GRT-DS-IP-DT-170444 | FC | 0 | 2017-11-13 | 130057-0 | FC | 0 | A | 2017-09-06 | 2017-11-13
234 | DHI | GRT-CQ02-P0LDB-130058 | 130058 | [Condensate Filter System]_O&M MANUAL | FI | 2017-11-23 | 2018-03-07 | 2018-03-28 | GRT-DS-IP-DT-180078 | FC | 0 | 2018-04-26 | 123-5th DRM | FC | 0 | A | 2017-12-05 | 2018-03-28
235 | DHI | GRT-FF03-P0SGA-133001 | 133001 | [Fire Fighting System] Water Spray System P&ID for STG Enclosure Inside | FA | 2018-06-05 | 2018-09-07 | 2018-08-02 | GRT-DS-IP-DT-180197 | FC | 0 | 2018-08-10 | 133001-0 | FC | 0 | A | 2018-06-28 | #VALUE!
236 | DHI | GRT-FF01-P0SGA-133002 | 133002 | [Fire Fighting System] Water Spray System Plan for STG Enclosure Inside | FA | 2018-06-15 | 2018-09-14 | 2018-08-02 | GRT-DS-IP-DT-180197 | FC | 0 | 2018-08-10 | 133002-0 | FC | 0 | A | 2018-07-05 | #VALUE!
237 | DHI | GRT-XG11-P0SGA-133003 | 133003 | [Fire Fighting System] Single Line Diagram for STG Enclosure Inside | FA | 2018-06-15 | 2018-09-14 | 2018-08-02 | GRT-DS-IP-DT-180197 | FC | 0 | 2018-08-10 | 133003-0 | FC | 0 | A | #VALUE! | #VALUE!
238 | DHI | GRT-FF02-P0SGA-133004 | 133004 | [Fire Fighting System] Detection and Alarm System Equipment Location Plan for STG Enclosure Inside | FA | 2018-06-15 | 2018-09-14 | 2018-08-16 | GRT-DS-IP-DT-180204 | FC | 0 | 2018-08-30 | 133004-0 | FC | 0 | A | 2018-07-07 | #VALUE!
239 | DHI | GRT-FF05-P0SGA-133005 | 133005 | [Fire Fighting System] Water Spray System Hydraulic Calculation | FA | 2018-06-15 | 2018-09-14 | 2018-08-02 | GRT-DS-IP-DT-180197 | FC | 0 | 2018-08-10 | 133005-0 | FC | 0 | A | 2018-07-08 | #VALUE!
240 | DHI | GRT-XJ00-P0LBA-140001 | 140001 | Piping ISO (Large Bore) - HP Steam | FI | 2017-06-09 | 2017-08-31 | 2020-01-22 | GRT-DS-IP-DT-200006 | FC | 3 | 2020-01-22 | 140001-7 | FC | 3 | A | 2017-06-20 | 2017-12-29
241 | DHI | GRT-XJ00-P0LBA-140002 | 140002 | Piping ISO (Large Bore) - LP Steam | FI | 2017-06-09 | 2017-08-31 | 2020-01-22 | GRT-DS-IP-DT-200006 | FC | 3 | 2020-01-22 | 140002-7 | FC | 3 | A | 2017-06-20 | 2017-12-29
242 | DHI | GRT-XJ00-P0LBG-140003 | 140003 | Piping ISO (Large Bore) - Aux. Steam | FI | 2017-06-16 | 2018-01-31 | 2020-01-22 | GRT-DS-IP-DT-200006 | FC | 3 | 2020-01-22 | 140003-7 | FC | 3 | A | 2017-07-13 | 2018-02-19
243 | DHI | GRT-XJ00-P0LCM-140004 | 140004 | Piping ISO (Large Bore) - Steam drain | FI | 2017-06-09 | 2018-01-31 | 2020-01-22 | GRT-DS-IP-DT-200006 | FC | 2 | 2020-01-22 | 140004-7 | FC | 2 | A | 2017-07-13 | 2018-02-19
244 | DHI | GRT-XJ00-P0LAB-140005 | 140005 | Piping ISO (Large Bore) - Feedwater | FI | 2017-06-16 | 2017-08-31 | 2020-01-22 | GRT-DS-IP-DT-200006 | FC | 3 | 2020-01-22 | 140005-7 | FC | 3 | A | 2017-06-20 | 2017-12-29
245 | DHI | GRT-XJ00-P0LCA-140006 | 140006 | Piping ISO (Large Bore) - Condensate | FI | 2017-06-16 | 2018-01-31 | 2020-01-22 | GRT-DS-IP-DT-200006 | FC | 2 | 2020-01-22 | 140006-7 | FC | 2 | A | 2017-06-20 | 2018-02-19
246 | DHI | GRT-XJ00-P0PAB-140007 | 140007 | Piping ISO (Large Bore) - Aux. cooling water | FI | 2017-06-23 | 2018-01-31 | 2020-01-22 | GRT-DS-IP-DT-200006 | FC | 1 | 2020-01-22 | 140007-7 | FC | 1 | A | 2017-07-13 | 2018-02-19
247 | DHI | GRT-XJ00-P0PGB-140008 | 140008 | Piping ISO (Large Bore) - CCW | FI | 2017-06-23 | 2018-01-31 | 2020-02-07 | GRT-DS-IP-DT-200025 | FC | 2 | 2020-02-07 | 140008-7 | FC | 2 | A | 2017-07-13 | 2018-02-19
248 | DHI | GRT-XJ00-P0SCA-140009 | 140009 | Piping ISO (Large Bore) - Compressed air | FI | 2017-06-30 | 2018-01-31 | 2018-02-19 | GRT-DS-IP-DT-180039 | FC | 0 | 2018-03-01 | 140009-0 | FC | 0 | A | 2017-07-13 | 2018-02-19
249 | DHI | GRT-XJ00-P0MAA-140010 | 140010 | Piping ISO (Large Bore) - ST Misc. | FI | 2017-06-30 | 2018-01-31 | 2018-02-19 | GRT-DS-IP-DT-180039 | FC | 0 | 2018-03-01 | 140010-0 | FC | 0 | A | 2017-07-13 | 2018-02-19
250 | DHI | GRT-XJ00-P0TEM-140011 | 140011 | Piping ISO (Large Bore) - Steam blowing & flushing | FI | 2018-03-30 | 2018-06-01 | 2020-02-07 | GRT-DS-IP-DT-200009 | FC | 1 | 2020-02-07 | 140011-5 | FC | 1 | A | 2018-04-04 | #VALUE!
251 | DHI | GRT-XJ00-P0PAB-140012 | 140012 | Piping ISO (Large Bore) - Cooling water | FI | 2017-08-11 | 2018-01-31 | 2018-02-19 | GRT-DS-IP-DT-180039 | FC | 0 | 2018-03-01 | 140012-0 | FC | 0 | A | 2017-08-15 | 2018-02-19
252 | DHI | GRT-DP00-P0ZEN-141001 | 141001 | WPS&PQR for BOP Piping | FI | 2017-09-15 | 2017-12-15 | 2017-12-22 | GRT-DS-IP-DT-170528 | FC | 0 | 2018-04-26 | 114-5th DRM | FC | 0 | A | 2017-10-30 | 2017-12-22
253 | DHI | GRT-DP00-P0ZEN-141002 | 141002 | Heat treatment procedure for BOP Piping | FI | 2017-09-15 | 2017-12-15 | 2017-12-22 | GRT-DS-IP-DT-170528 | FC | 0 | 2018-04-26 | 115-5th DRM | FC | 0 | A | 2017-10-30 | 2017-12-22
254 | DHI | GRT-QA00-P0ZEN-141003 | 141003 | Welder qualificatoin list for BOP Piping | FI | 2017-09-15 | 2017-12-15 | 2017-12-22 | GRT-DS-IP-DT-170528 | FC | 0 | 2018-04-26 | 116-5th DRM | FC | 0 | A | 2017-10-30 | 2017-12-22
255 | DHI | GRT-DP00-P0ZEN-141004 | 141004 | Repair welding procedure for BOP Piping | FI | 2017-09-15 | 2017-12-15 | 2017-12-22 | GRT-DS-IP-DT-170528 | FC | 0 | 2018-04-26 | 117-5th DRM | FC | 0 | A | 2017-10-30 | 2017-12-22
256 | DHI | GRT-QA00-P0ZEN-141005 | 141005 | Welder consumable control procedure for BOP Piping | FI | 2017-09-15 | 2017-12-15 | 2017-12-22 | GRT-DS-IP-DT-170528 | FC | 0 | 2018-04-26 | 118-5th DRM | FC | 0 | A | 2017-10-30 | 2017-12-22
257 | DHI | GRT-QM03-P0ZEN-141006 | 141006 | RADIOGRAPHIC EXAMINATION PROCEDURE | FA | 2017-10-11 | 2017-11-13 | 2017-11-27 | GRT-DS-IP-DT-170461 | FC | 0 | 2018-04-26 | 77-5th DRM | FC | 0 | A | 2017-10-30 | 2017-11-27
258 | DHI | GRT-QM03-P0ZEN-141007 | 141007 | ULTRASONIC EXAMINATION PROCEDURE | FA | 2017-10-11 | 2017-11-13 | 2017-11-27 | GRT-DS-IP-DT-170461 | FC | 0 | 2018-04-26 | 78-5th DRM | FC | 0 | A | 2017-10-30 | 2017-11-27
259 | DHI | GRT-QM03-P0ZEN-141008 | 141008 | MAGNETIC PARTICLE EXAMINATION PROCEDURE | FA | 2017-10-11 | 2017-11-13 | 2017-11-27 | GRT-DS-IP-DT-170461 | FC | 0 | 2018-04-26 | 79-5th DRM | FC | 0 | A | 2017-10-30 | 2017-11-27
260 | DHI | GRT-QM03-P0ZEN-141009 | 141009 | LIQUID PENETRANT EXAMINATION PROCEDURE | FA | 2017-10-11 | 2017-11-13 | 2017-11-27 | GRT-DS-IP-DT-170461 | FC | 0 | 2018-04-26 | 80-5th DRM | FC | 0 | A | 2017-10-30 | 2017-11-27
261 | DHI | GRT-XJ00-P0LBA-143001 | 143001 | Piping ISO (Small Bore) - HP Steam | FI | 2017-07-07 | 2018-01-31 | 2020-02-07 | GRT-DS-IP-DT-200009 | FC | 2 | 2020-02-07 | 143001-5 | FC | 2 | A | 2017-07-13 | 2017-12-15
262 | DHI | GRT-XJ00-P0LBA-143002 | 143002 | Piping ISO (Small Bore) - LP Steam | FI | 2017-07-07 | 2018-01-31 | 2020-02-07 | GRT-DS-IP-DT-200009 | FC | 2 | 2020-02-07 | 143002-5 | FC | 2 | A | 2017-07-13 | 2017-12-15
263 | DHI | GRT-XJ00-P0LBG-143003 | 143003 | Piping ISO (Small Bore) - Aux. Steam | FI | 2017-07-14 | 2018-01-31 | 2020-02-07 | GRT-DS-IP-DT-200009 | FC | 2 | 2020-02-07 | 143003-5 | FC | 2 | A | 2017-07-19 | 2017-12-15
264 | DHI | GRT-XJ00-P0LCM-143004 | 143004 | Piping ISO (Small Bore) - Steam drain | FI | 2017-07-07 | 2018-01-31 | 2017-12-29 | GRT-DS-IP-DT-170543 | FC | 0 | 2018-04-26 | 127-5th DRM | FC | 0 | A | 2017-07-13 | 2017-12-29
265 | DHI | GRT-XJ00-P0LAB-143005 | 143005 | Piping ISO (Small Bore) - Feedwater | FI | 2017-07-14 | 2018-01-31 | 2020-02-07 | GRT-DS-IP-DT-200009 | FC | 2 | 2020-02-07 | 143005-5 | FC | 2 | A | 2017-07-19 | 2017-12-29
266 | DHI | GRT-XJ00-P0LCA-143006 | 143006 | Piping ISO (Small Bore) - Condensate | FI | 2017-07-14 | 2018-01-31 | 2020-02-07 | GRT-DS-IP-DT-200009 | FC | 3 | 2020-02-07 | 143006-5 | FC | 3 | A | 2017-07-19 | 2018-01-09
267 | DHI | GRT-XJ00-P0PAB-143007 | 143007 | Piping ISO (Small Bore) - Aux. cooling water | FI | 2017-07-21 | 2018-01-31 | 2020-02-07 | GRT-DS-IP-DT-200009 | FC | 3 | 2020-02-07 | 143007-5 | FC | 3 | A | 2017-07-21 | 2018-01-23
268 | DHI | GRT-XJ00-P0PGB-143008 | 143008 | Piping ISO (Small Bore) - CCW | FI | 2017-07-21 | 2018-01-31 | 2020-01-31 | GRT-DS-IP-DT-200023 | FC | 2 | 2020-01-31 | 143008-3 | FC | 2 | A | 2017-07-21 | 2017-12-29
269 | DHI | GRT-XJ00-P0QJA-143009 | 143009 | Piping ISO (Small Bore) - N2 | FI | 2017-07-21 | 2018-01-31 | 2020-01-31 | GRT-DS-IP-DT-200023 | FC | 3 | 2020-01-31 | 143009-3 | FC | 3 | A | 2017-07-21 | 2018-01-23
270 | DHI | GRT-XJ00-P0SCA-143010 | 143010 | Piping ISO (Small Bore) - Compressed air | FI | 2017-07-28 | 2018-01-31 | 2018-04-02 | GRT-DS-IP-DT-180082 | FC | 1 | 2018-04-10 | 143010-1 | FC | 1 | A | 2017-08-01 | 2017-12-18
271 | DHI | GRT-XJ00-P0SCB-143011 | 143011 | Piping ISO (Small Bore) - Service air | FI | 2017-07-28 | 2018-01-31 | 2018-04-02 | GRT-DS-IP-DT-180086 | FC | 1 | 2018-04-06 | 143011-1 | FC | 1 | A | 2017-08-01 | 2017-12-18
272 | DHI | GRT-XJ00-P0QFB-143012 | 143012 | Piping ISO (Small Bore) - Instrument air | FI | 2017-07-28 | 2018-01-31 | 2018-07-26 | GRT-DS-IP-DT-180190 | FC | 2 | 2018-08-02 | 143012-2 | FC | 2 | A | 2017-08-01 | 2018-01-17
273 | DHI | GRT-XJ00-P0MAA-143013 | 143013 | Piping ISO (Small Bore) - ST Misc. | FI | 2017-07-28 | 2018-01-31 | 2020-01-31 | GRT-DS-IP-DT-200023 | FC | 2 | 2020-01-31 | 143013-3 | FC | 2 | A | 2017-08-01 | 2018-01-23
274 | DHI | GRT-XJ00-P0LCW-143014 | 143014 | Piping ISO (Small Bore) - Seal Water | FI | 2017-07-21 | 2018-01-31 | 2020-01-31 | GRT-DS-IP-DT-200023 | FC | 1 | 2020-01-31 | 143014-3 | FC | 1 | A | 2017-07-21 | 2018-01-09
275 | DHI | GRT-XJ00-P0PAB-143015 | 143015 | Piping ISO (Small Bore) - Cooling water | FI | 2017-07-07 | 2018-01-31 | 2020-01-31 | GRT-DS-IP-DT-200023 | FC | 2 | 2020-01-31 | 143015-3 | FC | 2 | A | 2017-07-19 | 2017-12-18
276 | DHI | GRT-XJ00-P0QC-143016 | 143016 | Piping ISO (Small Bore) - Chemical dosing | FI | 2017-07-14 | 2018-01-31 | 2020-01-31 | GRT-DS-IP-DT-200023 | FC | 2 | 2020-01-31 | 143016-2 | FC | 2 | A | 2017-07-19 | 2017-12-29
277 | DHI | GRT-XJ00-P0QUA-143017 | 143017 | Piping ISO (Small Bore) - Sampling | FI | 2017-07-28 | 2018-01-31 | 2020-01-31 | GRT-DS-IP-DT-200023 | FC | 3 | 2020-01-31 | 143017-3 | FC | 3 | A | 2017-08-01 | 2018-01-17
278 | DHI | GRT-XK00-P0LBA-144001 | 144001 | Support DWG (Large Bore) - HP Steam | FI | 2017-08-15 | 2017-11-30 | 2020-02-07 | GRT-DS-IP-DT-200025 | FC | 2 | 2020-02-07 | 144001-7 | FC | 2 | A | 2017-12-18 | 2017-12-29
279 | DHI | GRT-XK00-P0LBA-144002 | 144002 | Support DWG (Large Bore) - LP Steam | FI | 2017-08-15 | 2017-11-30 | 2020-02-07 | GRT-DS-IP-DT-200025 | FC | 3 | 2020-02-07 | 144002-7 | FC | 3 | A | 2017-12-18 | 2017-12-29
280 | DHI | GRT-XK00-P0LBG-144003 | 144003 | Support DWG (Large Bore) - Aux. Steam | FI | 2017-12-31 | 2018-01-30 | 2020-02-07 | GRT-DS-IP-DT-200025 | FC | 4 | 2020-02-07 | 144003-7 | FC | 4 | A | 2017-12-18 | 2018-03-22
281 | DHI | GRT-XK00-P0LCM-144004 | 144004 | Support DWG (Large Bore) - Steam drain | FI | 2017-12-31 | 2018-01-30 | 2018-03-22 | GRT-DS-IP-DT-180040 | FC | 0 | 2018-04-06 | 144004-1 | FC | 0 | B | 2017-12-18 | 2018-03-22
282 | DHI | GRT-XK00-P0LAB-144005 | 144005 | Support DWG (Large Bore) - Feedwater | FI | 2017-08-15 | 2017-11-30 | 2020-02-07 | GRT-DS-IP-DT-200025 | FC | 3 | 2020-02-07 | 144005-7 | FC | 3 | A | 2017-12-18 | 2017-12-29
283 | DHI | GRT-XK00-P0LCA-144006 | 144006 | Support DWG (Large Bore) - Condensate | FI | 2017-12-31 | 2018-01-30 | 2020-02-07 | GRT-DS-IP-DT-200025 | FC | 2 | 2020-02-07 | 144006-7 | FC | 2 | A | 2017-12-18 | 2018-03-22
284 | DHI | GRT-XK00-P0PAB-144007 | 144007 | Support DWG (Large Bore) - Aux. cooling water | FI | 2017-12-31 | 2018-01-30 | 2020-02-07 | GRT-DS-IP-DT-200025 | FC | 1 | 2020-02-07 | 144007-7 | FC | 1 | A | 2017-12-18 | 2018-03-22
285 | DHI | GRT-XK00-P0PGB-144008 | 144008 | Support DWG (Large Bore) - CCW | FI | 2017-12-31 | 2018-01-30 | 2020-02-07 | GRT-DS-IP-DT-200025 | FC | 1 | 2020-02-07 | 144008-7 | FC | 1 | A | 2017-12-18 | 2018-03-22
286 | DHI | GRT-XK00-P0SCA-144009 | 144009 | Support DWG (Large Bore) - Compressed air | FI | 2017-12-31 | 2018-01-30 | 2018-03-22 | GRT-DS-IP-DT-180040 | FC | 0 | 2018-04-06 | 144009-1 | FC | 0 | B | 2017-12-18 | 2018-03-22
287 | DHI | GRT-XK00-P0MAA-144010 | 144010 | Support DWG (Large Bore) - ST Misc. | FI | 2017-12-31 | 2018-01-30 | 2018-09-12 | GRT-DS-IP-DT-180214 | FC | 1 | 2018-09-20 | 144010-2 | FC | 1 | A | 2017-12-18 | 2018-03-22
288 | DHI | GRT-XK00-P0TEM-144011 | 144011 | Support DWG (Large Bore) - Steam blowing | FI | 2018-04-30 | 2018-06-01 | 2020-02-07 | GRT-DS-IP-DT-200025 | FC | 1 | 2020-02-07 | 144011-7 | FC | 1 | A | 2018-07-05 | #VALUE!
289 | DHI | GRT-XK00-P0PAB-144012 | 144012 | Support DWG (Large Bore) - Cooling Water | FI | 2017-12-31 | 2018-01-30 | 2020-02-07 | GRT-DS-IP-DT-200025 | FC | 1 | 2020-02-07 | 144012-7 | FC | 1 | A | 2017-12-18 | 2018-03-22
290 | DHI | GRT-DE00-P0ZEN-144500 | 144500 | [Piping General]_Piping material specification (BOP) | FA | 2017-03-03 | 2017-06-09 | 2017-11-27 | GRT-DS-IP-DT-170475 | FC | 1 | 2018-04-26 | 61-5th DRM | FC | 1 | A | 2017-03-09 | 2017-08-21
291 | DHI | GRT-DE00-P0ZEN-144501 | 144501 | [Piping General]_Piping Insulation Specification (BOP) | FA | 2017-04-07 | 2017-07-07 | 2020-02-07 | GRT-DS-IP-DT-200009 | FC | 1 | 2020-02-07 | 144501-5 | FC | 1 | A | 2017-04-10 | 2017-06-14
292 | DHI | GRT-YT10-P0ZEN-144502 | 144502 | [Piping General]_Pipe Thickness Calculation (BOP) | FA | 2017-03-17 | 2017-06-16 | 2017-11-27 | GRT-DS-IP-DT-170475 | FC | 1 | 2018-04-26 | 62-5th DRM | FC | 1 | A | 2017-03-22 | 2017-08-21
293 | DHI | GRT-XL00-P0ZEN-144503 | 144503 | [Piping General]_Piping Line List (BOP) | FA | 2017-03-31 | 2017-06-30 | 2017-07-31 | GRT-DS-IP-DT-170213 | FC | 0 | 2017-08-25 |  | FC | 0 | A | 2017-04-06 | 2017-07-31
294 | DHI | GRT-XL00-P0ZEN-144504 | 144504 | [Piping General]_Piping Specialty List (BOP) | FA | 2017-03-31 | 2017-06-30 | 2017-07-31 | GRT-DS-IP-DT-170213 | FC | 0 | 2017-08-25 |  | FC | 0 | A | 2017-04-06 | 2017-07-31
295 | DHI | GRT-XN00-P0ZEN-144505 | 144505 | [Piping General]_Manual Valve List (BOP) | FA | 2017-03-31 | 2017-06-30 | 2017-07-31 | GRT-DS-IP-DT-170213 | FC | 0 | 2017-08-25 |  | FC | 0 | A | 2017-04-06 | 2017-07-31
296 | DHI | GRT-XK00-P0ZEN-144511 | 144511 | [Piping General]_Typical Installation Drawing for Pipe Support | FA | 2017-06-15 | 2017-08-18 | 2020-01-31 | GRT-DS-IP-DT-200023 | FC | 1 | 2020-01-31 | 144511-3 | FC | 1 | A | 2017-06-20 | 2017-07-24
297 | DHI | GRT-DF04-P0ZEN-144512 | 144512 | [Piping General]_Stress Analysis Report for HP steam system | FA | 2017-06-23 | 2017-09-15 | 2018-05-16 | GRT-DS-IP-DT-180125 | FC | 1 | 2018-05-16 | 144512-1 | FC | 1 | A | 2017-07-13 | 2017-10-26
298 | DHI | GRT-DF04-P0ZEN-144513 | 144513 | [Piping General]_Stress Analysis Report for LP steam system | FA | 2017-06-23 | 2017-09-15 | 2018-05-16 | GRT-DS-IP-DT-180126 | FC | 1 | 2018-05-16 | 144513-1 | FC | 1 | A | 2017-07-13 | 2017-10-26
299 | DHI | GRT-DF04-P0ZEN-144514 | 144514 | [Piping General]_Stress Analysis Report for Aux.steam system | FA | 2017-06-23 | 2017-09-15 | 2018-05-16 | GRT-DS-IP-DT-180127 | FC | 1 | 2018-05-16 | 144514-1 | FC | 1 | A | 2017-07-13 | 2017-10-26
300 | DHI | GRT-DF04-P0ZEN-144515 | 144515 | [Piping General]_Stress Analysis Report for Feedwater system | FA | 2017-06-23 | 2017-09-15 | 2018-05-16 | GRT-DS-IP-DT-180128 | FC | 1 | 2018-05-16 | 144515-1 | FC | 1 | A | 2017-07-13 | 2017-10-26
301 | DHI | GRT-XH01-P0UMA-144521 | 144521 | [Steam Turbine Building_Piping]_Piping Arrangement | FA | 2017-06-02 | 2017-09-29 | 2018-02-21 | GRT-DS-IP-DT-180045 | FC | 1 | 2018-03-01 | 144521-1 | FC | 1 | A | 2017-06-05 | 2017-07-24
302 | DHI | GRT-XH01-P0UZT-144522 | 144522 | [Pipe Rack_Piping]_Piping Arrangement | FA | 2017-06-02 | 2017-09-29 | 2018-02-21 | GRT-DS-IP-DT-180045 | FC | 1 | 2018-03-01 | 144522-1 | FC | 1 | A | 2017-06-05 | 2017-07-24
303 | DHI | GRT-XH01-P0UTG-144523 | 144523 | [N2 Gas Shelter_Piping]_Piping Arrangement | FA | 2017-06-02 | 2017-09-29 | 2018-02-21 | GRT-DS-IP-DT-180045 | FC | 1 | 2018-03-01 | 144523-1 | FC | 1 | A | 2017-06-05 | 2017-07-24
304 | DHI | GRT-XK00-P0ZEN-144900 | 144900 | Outline Drawing for Piping Manual Ball Valve | FI | 2017-11-15 | 2017-12-01 | 2018-03-21 | GRT-DS-IP-DT-180042 | FC | 1 | 2018-03-27 | 144900-1 | FC | 1 | B | 2017-12-18 | 2017-12-29
305 | DHI | GRT-XK00-P0ZEN-144901 | 144901 | Outline Drawing for Piping Manual Butterfly Valve | FI | 2017-11-15 | 2017-12-01 | 2018-03-21 | GRT-DS-IP-DT-180042 | FC | 1 | 2018-03-27 | 144901-1 | FC | 1 | B | 2017-12-18 | 2017-12-29
306 | DHI | GRT-XK00-P0ZEN-144902 | 144902 | Outline Drawing for Piping HP Manual Casting Valve | FI | 2017-11-15 | 2017-12-01 | 2018-03-21 | GRT-DS-IP-DT-180042 | FC | 1 | 2018-03-27 | 144902-1 | FC | 1 | A | 2017-12-18 | 2017-12-29
307 | DHI | GRT-XK00-P0ZEN-144903 | 144903 | Outline Drawing for Piping LP Manual Casting Valve | FI | 2017-11-15 | 2017-12-01 | 2018-03-21 | GRT-DS-IP-DT-180042 | FC | 1 | 2018-03-27 | 144903-1 | FC | 1 | A | 2017-12-18 | 2017-12-29
308 | DHI | GRT-XK00-P0ZEN-144904 | 144904 | Outline Drawing for Piping HP Manual Forging Valve | FI | 2017-11-15 | 2017-12-01 | 2018-04-13 | GRT-DS-IP-DT-180090 | FC | 2 | 2018-04-27 | 144904-2 | FC | 2 | A | 2017-12-18 | 2017-12-29
309 | DHI | GRT-XK00-P0ZEN-144905 | 144905 | Outline Drawing for Piping LP Manual Forging Valve | FI | 2017-11-15 | 2017-12-01 | 2018-04-13 | GRT-DS-IP-DT-180090 | FC | 2 | 2018-04-27 | 144905-2 | FC | 2 | A | 2017-12-18 | 2017-12-29
310 | DHI | GRT-XW01-P0ZEN-161001 | 161001 | [INC_Plant_Overall_Design]_I&C General Design Criteria | FA | 2017-03-03 | 2017-07-14 | 2020-01-18 | GRT-DS-IP-DT-200016 | FC | 1 | 2020-01-18 | 161001-1 | FC | 1 | A | 2017-03-09 | 2017-07-24
311 | DHI | GRT-MA01-P0ZEN-161002 | 161002 | [INC_Plant_Overall_Design]_Plant Control System Configuration Diagram | FA | 2017-03-31 | 2017-07-14 | 2020-01-18 | GRT-DS-IP-DT-200016 | FC | 1 | 2020-01-18 | 161002-1 | FC | 1 | A | 2017-04-10 | 2017-07-24
312 | DHI | GRT-YU04-P0ZEN-161003 | 161003 | [INC_Plant_Overall_Design]_Plant Control Block Diagram | FA | 2017-03-31 | 2017-07-14 | 2017-07-24 | GRT-DS-IP-DT-170188 | FC | 0 | 2017-07-27 |  | FC | 0 | A | 2017-04-06 | 2017-07-24
313 | DHI | GRT-YF01-P0ZEN-161004 | 161004 | [INC_Plant_Overall_Design]_Plant Protection & Interlock Diagram | FA | 2017-04-07 | 2017-06-30 | 2017-08-23 | GRT-DS-IP-DT-170247 | FC | 0 | 2017-08-23 |  | FC | 0 | A | 2017-04-18 | 2017-08-23
314 | DHI | GRT-MA02-P0ZEN-161006 | 161006 | [INC_Interface]_3rd Party Data-link Interface Concept Diagram | FA | 2017-03-31 | 2017-07-14 | 2020-01-18 | GRT-DS-IP-DT-200008 | FC | 1 | 2020-01-18 | 161006-3 | FC | 1 | A | 2017-04-10 | 2017-10-26
315 | DHI | GRT-YL01-P0ZEN-161101 | 161101 | [INC_DCS_IO]_DCS I/O Database | FA | 2017-04-07 | 2017-06-30 | 2019-10-03 | GRT-DS-IP-DT-190144 | FC | 2 | 2019-10-03 | 161101-3 | FC | 2 | A | 2017-04-18 | 2017-10-13
316 | DHI | GRT-YL01-P0ZEN-161102 | 161102 | [INC_DCS_IO]_3rd Party Data-link Interface Signal Database | FA | 2017-09-15 | 2017-11-03 | 2019-10-25 | GRT-DS-IP-DT-190151 | FC | 2 | 2019-10-25 | 161102-2 | FC | 2 | A | 2017-10-30 | 2017-11-27
317 | DHI | GRT-CV03-P0ZEN-161110 | 161110 | [DCS]_Functional Design Specification for Hardware | FA | 2017-03-31 | 2017-06-30 | 2017-07-27 | GRT-DS-IP-DT-170210 | FC | 0 | 2017-08-03 |  | FC | 0 | A | 2017-05-19 | 2017-07-27
318 | DHI | GRT-CV03-P0ZEN-161111 | 161111 | [DCS]_Functional Design Specification for Software | FA | 2017-03-31 | 2017-06-30 | 2017-09-06 | GRT-DS-IP-DT-170275 | FC | 0 | 2017-09-08 | 161111-0 | FC | 0 | A | 2017-05-19 | 2017-09-06
319 | DHI | GRT-CV03-P0ZEN-161112 | 161112 | [DCS]_Functional Design Specification for Graphic | FA | 2017-04-07 | 2017-07-07 | 2017-11-27 | GRT-DS-IP-DT-170454 | FC | 0 | 2018-04-26 | 24-5th DRM | FC | 0 | A | 2017-05-19 | 2017-11-27
320 | DHI | GRT-YD06-P0ZEN-161113 | 161113 | [INC_Plant_Overall_Design]_DCS Power Distribution Concept Diagram | FA | 2017-03-31 | 2017-06-30 | 2017-09-14 | GRT-DS-IP-DT-170287 | FC | 0 | 2017-09-18 | 161113-0 | FC | 0 | A | 2017-04-18 | 2017-09-14
321 | DHI | GRT-YE03-P0ZEN-161114 | 161114 | [DCS]_Grounding Concept & Drawing | FA | 2017-03-31 | 2017-06-30 | 2017-07-24 | GRT-DS-IP-DT-170182 | FC | 0 | 2017-07-24 |  | FC | 0 | A | 2017-05-19 | 2017-07-24
322 | DHI | GRT-YD06-P0ZEN-161115 | 161115 | [DCS]_Equipment Power Distribution Diagram | FA | 2017-03-31 | 2017-06-30 | 2017-10-30 | GRT-DS-IP-DT-170409 | FC | 0 | 2017-11-02 | 161115-0 | FC | 0 | A | 2017-05-19 | 2017-10-30
323 | DHI | GRT-CV03-P0ZEN-161116 | 161116 | [DCS]_Functional Design Specification for Safety Related System | FA | 2017-04-21 | 2017-06-30 | 2017-10-26 | GRT-DS-IP-DT-170398 | FC | 0 | 2017-11-02 | 161116-0 | FC | 0 | A | 2017-05-19 | 2017-10-26
324 | DHI | GRT-CV03-P0ZEN-161117 | 161117 | [DCS]_Functional Design Specification for Performance Monitoring System | FA | 2017-04-21 | 2017-06-30 | 2017-10-26 | GRT-DS-IP-DT-170402 | FC | 0 | 2017-11-02 | 161117-0 | FC | 0 | A | 2017-05-19 | 2017-10-26
325 | DHI | GRT-MA02-P0ZEN-161121 | 161121 | [DCS]_LAN Configuration Diagram | FA | 2017-03-31 | 2017-06-30 | 2020-01-22 | GRT-DS-IP-DT-200021 | FC | 1 | 2020-01-22 | 161121-3 | FC | 1 | A | 2017-04-10 | 2017-11-01
326 | DHI | GRT-YD07-P0ZEN-161122 | 161122 | [DCS]_IO & Module Allocation | FA | 2017-04-21 | 2017-07-07 | 2019-02-11 | GRT-DS-IP-DT-190021 | FC | 2 | 2019-02-11 | 161122-2 | FC | 2 | A | 2017-05-19 | 2017-07-27
327 | DHI | GRT-YD05-P0ZEN-161123 | 161123 | [DCS]_HMI Graphic Drawing | FA | 2017-09-15 | 2017-11-03 | 2018-08-16 | GRT-DS-IP-DT-180198 | FC | 1 | 2018-09-06 | 161123-1 | FC | 1 | A | 2017-10-13 | 2017-11-27
328 | DHI | GRT-YR05-P0ZEN-161131 | 161131 | [DCS]_Outline & Detail Drawing for Console desk & Computer desk & Printer desk | FA | 2017-04-07 | 2017-07-07 | 2020-01-22 | GRT-DS-IP-DT-200021 | FC | 1 | 2020-01-22 | 161131-3 | FC | 1 | A | 2017-04-18 | 2017-11-27
329 | DHI | GRT-YR05-P0ZEN-161132 | 161132 | [DCS]_Outline & Detail Drawing for LAN Cabinet | FA | 2017-04-07 | 2017-07-07 | 2017-11-27 | GRT-DS-IP-DT-170454 | FC | 0 | 2018-04-26 | 27-5th DRM | FC | 0 | A | 2017-04-18 | 2017-11-27
330 | DHI | GRT-YR05-P0ZEN-161133 | 161133 | [DCS]_Outline & Detail Drawing for Power Distribution Cabinet | FA | 2017-04-07 | 2017-07-07 | 2020-01-22 | GRT-DS-IP-DT-200021 | FC | 1 | 2020-01-22 | 161133-3 | FC | 1 | A | 2017-04-18 | 2017-10-30
331 | DHI | GRT-YR05-P0ZEN-161134 | 161134 | [DCS]_Outline & Detail Drawing for System & Marshalling Cabinet | FA | 2017-04-07 | 2017-07-07 | 2019-02-04 | GRT-DS-IP-DT-190017 | FC | 2 | 2019-02-04 | 161134-2 | FC | 2 | A | 2017-04-18 | 2017-11-27
332 | DHI | GRT-YR05-P0ZEN-161135 | 161135 | [DCS]_Outline & Detail Drawing for Relay Cabinet | FA | 2017-04-07 | 2017-07-07 | 2017-10-30 | GRT-DS-IP-DT-170409 | FC | 0 | 2017-11-02 | 161135-0 | FC | 0 | A | 2017-05-19 | 2017-10-30
333 | DHI | GRT-YR05-P0ZEN-161136 | 161136 | [DCS]_Outline & Detail Drawing for Safety Related System Panel | FA | 2017-04-07 | 2017-07-07 | 2017-11-27 | GRT-DS-IP-DT-170454 | FC | 0 | 2018-04-26 | 29-5th DRM | FC | 0 | A | 2017-04-18 | 2017-11-27
334 | DHI | GRT-YF00-P0ZEN-161201 | 161201 | [INC_Other_Sys_Logic&Loop]_Control Logic Diagram - Symbol & Legend | FA | 2017-04-14 | 2017-07-31 | 2017-07-17 | GRT-DS-IP-DT-170166 | FC | 0 | 2017-07-17 |  | FC | 0 | A | 2017-04-18 | 2017-07-17
335 | DHI | GRT-YF00-P0ZEN-161202 | 161202 | [INC_Other_Sys_Logic&Loop]_Control Logic Diagram - Typical Function | FA | 2017-04-14 | 2017-07-31 | 2018-08-02 | GRT-DS-IP-DT-180175 | FC | 1 | 2018-08-10 | 161202-1 | FC | 1 | A | 2017-04-18 | 2017-09-14
336 | DHI | GRT-YF00-P1LBA-161203 | 161203 | [HP & LP steam system_I&C_Logic]_Control Logic Diagram for BOP | FA | 2017-04-14 | 2017-07-31 | 2018-08-30 | GRT-DS-IP-DT-180212 | FC | 1 | 2018-09-06 | 161203-1 | FC | 1 | A | 2017-05-17 | 2017-09-25
337 | DHI | GRT-YF00-P0LBG-161204 | 161204 | [AUX Steam System_I&C_Logic]_Control Logic Diagram for BOP | FA | 2017-04-14 | 2017-07-31 | 2018-08-30 | GRT-DS-IP-DT-180212 | FC | 1 | 2018-09-06 | 161204-1 | FC | 1 | A | 2017-04-18 | 2017-09-14
338 | DHI | GRT-YF00-P0LA-161205 | 161205 | [Feedwater system_I&C_Logic]_Control Logic Diagram for BOP | FA | 2017-04-28 | 2017-07-31 | 2018-08-16 | GRT-DS-IP-DT-180198 | FC | 1 | 2018-09-06 | 161205-1 | FC | 1 | A | 2017-05-23 | 2017-10-26
339 | DHI | GRT-YF00-P0LC-161206 | 161206 | [Condensate system_I&C_Logic]_Control Logic Diagram for BOP | FA | 2017-04-21 | 2017-07-31 | 2018-09-20 | GRT-DS-IP-DT-180226 | FC | 2 | 2018-09-26 | 161206-2 | FC | 2 | A | 2017-05-19 | 2017-07-31
340 | DHI | GRT-YF00-P0PA-161207 | 161207 | [Aux. Cooling Water System_I&C_Logic]_Control Logic Diagram for BOP | FA | 2017-04-21 | 2017-07-31 | 2019-10-03 | GRT-DS-IP-DT-190144 | FC | 3 | 2019-10-03 | 161207-4 | FC | 3 | A | 2017-05-19 | 2017-10-13
341 | DHI | GRT-YF00-P0PG-161208 | 161208 | [Closed cooling water system_I&C_Logic]_Control Logic Diagram for BOP | FA | 2017-04-21 | 2017-07-31 | 2019-10-03 | GRT-DS-IP-DT-190144 | FC | 3 | 2019-10-03 | 161208-4 | FC | 3 | A | 2017-05-17 | 2017-10-13
342 | DHI | GRT-YF00-P0ZEN-161210 | 161210 | [INC_Other_Sys_Logic&Loop]_Control Logic Diagram for Sampling & Chemical Dosing System | FA | 2017-04-28 | 2017-07-31 | 2017-09-06 | GRT-DS-IP-DT-170283 | FC | 0 | 2017-09-11 | 161210-0 | FC | 0 | B | 2017-05-19 | 2017-09-06
343 | DHI | GRT-YF00-P0ZEN-161211 | 161211 | [INC_Other_Sys_Logic&Loop]_Control Logic Diagram for Interface with other Control System | FA | 2017-04-28 | 2017-07-31 | 2019-09-10 | GRT-DS-IP-DT-190131 | FC | 1 | 2019-09-10 | 161211-1 | FC | 1 | A | 2017-05-19 | 2017-10-13
344 | DHI | GRT-YF00-P0ZEN-161212 | 161212 | [INC_Other_Sys_Logic&Loop]_Control Logic Diagram for Miscellaneous System | FA | 2017-04-28 | 2017-07-31 | 2018-08-16 | GRT-DS-IP-DT-180198 | FC | 1 | 2018-09-06 | 161212-1 | FC | 1 | A | 2017-05-19 | 2017-10-13
345 | DHI | GRT-YF00-P0MAJ-161213 | 161213 | [Condenser Vacuum Pump System _I&C_Logic]_Control Logic Diagram for BOP | FA | 2017-04-28 | 2017-07-31 | 2018-08-24 | GRT-DS-IP-DT-180203 | FC | 1 | 2018-09-06 | 161213-1 | FC | 1 | A | 2017-05-19 | 2017-07-31
346 | DHI | GRT-YF00-P0ZEN-161301 | 161301 | [INC_Other_Sys_Logic&Loop]_Control Loop Diagram - Symbol & Legend | FA | 2017-04-14 | 2017-07-31 | 2017-07-17 | GRT-DS-IP-DT-170166 | FC | 0 | 2017-07-17 |  | FC | 0 | A | 2017-04-18 | 2017-07-17
347 | DHI | GRT-YF00-P0ZEN-161302 | 161302 | [INC_Other_Sys_Logic&Loop]_Control Loop Diagram - Typical Function | FA | 2017-04-14 | 2017-07-31 | 2017-07-17 | GRT-DS-IP-DT-170166 | FC | 0 | 2017-07-17 |  | FC | 0 | A | 2017-04-18 | 2017-07-17
348 | DHI | GRT-YF00-P1LBA-161303 | 161303 | [HP & LP steam system_I&C_Loop]_Control Loop Diagram for BOP | FA | 2017-04-14 | 2017-07-31 | 2018-08-30 | GRT-DS-IP-DT-180212 | FC | 1 | 2018-09-06 | 161303-1 | FC | 1 | A | 2017-05-17 | 2017-09-25
349 | DHI | GRT-YF00-P0LBG-161304 | 161304 | [AUX Steam System_I&C_Loop]_Control Loop Diagram for BOP | FA | 2017-04-14 | 2017-07-31 | 2018-08-30 | GRT-DS-IP-DT-180212 | FC | 1 | 2018-09-06 | 161304-1 | FC | 1 | A | 2017-04-18 | 2017-09-14
350 | DHI | GRT-YF00-P0LA-161305 | 161305 | [Feedwater system_I&C_Loop]_Control Loop Diagram for BOP | FA | 2017-04-28 | 2017-07-31 | 2018-08-16 | GRT-DS-IP-DT-180198 | FC | 1 | 2018-09-06 | 161305-1 | FC | 1 | A | 2017-05-23 | 2017-10-26
351 | DHI | GRT-YF00-P0LC-161306 | 161306 | [Condensate system_I&C_Loop]_Control Loop Diagram for BOP | FA | 2017-04-21 | 2017-07-31 | 2018-08-24 | GRT-DS-IP-DT-180203 | FC | 1 | 2018-09-06 | 161306-1 | FC | 1 | A | 2017-05-19 | 2017-09-14
352 | DHI | GRT-YF00-P0PA-161307 | 161307 | [Aux. Cooling Water System_I&C_Loop]_Control Loop Diagram for BOP | FA | 2017-04-21 | 2017-07-31 | 2018-08-24 | GRT-DS-IP-DT-180203 | FC | 1 | 2018-09-06 | 161307-1 | FC | 1 | A | 2017-05-19 | 2017-10-13
353 | DHI | GRT-YF00-P0PG-161308 | 161308 | [Closed cooling water system_I&C_Loop]_Control Loop Diagram for BOP | FA | 2017-04-21 | 2017-07-31 | 2018-08-24 | GRT-DS-IP-DT-180203 | FC | 1 | 2018-09-06 | 161308-1 | FC | 1 | A | 2017-05-17 | 2017-10-13
354 | DHI | GRT-YF00-P0ZEN-161310 | 161310 | [INC_Other_Sys_Logic&Loop]_Control Loop Diagram for Sampling & Chemical Dosing System | FA | 2017-04-28 | 2017-07-31 | 2017-07-31 | GRT-DS-IP-DT-170218 | FC | 0 | 2017-08-22 |  | FC | 0 | B | 2017-05-19 | 2017-07-31
355 | DHI | GRT-YF00-P0ZEN-161311 | 161311 | [INC_Other_Sys_Logic&Loop]_Control Loop Diagram for Interface with other Control System | FA | 2017-04-28 | 2017-07-31 | 2019-09-10 | GRT-DS-IP-DT-190131 | FC | 1 | 2019-09-10 | 161311-1 | FC | 1 | A | 2017-05-19 | 2017-10-13
356 | DHI | GRT-YF00-P0ZEN-161312 | 161312 | [INC_Other_Sys_Logic&Loop]_Control Loop Diagram for Miscellaneous System | FA | 2017-04-28 | 2017-07-31 | 2018-08-16 | GRT-DS-IP-DT-180198 | FC | 1 | 2018-09-06 | 161312-1 | FC | 1 | A | 2017-05-19 | 2017-10-13
357 | DHI | GRT-YF00-P0MAJ-161313 | 161313 | [Condenser Vacuum Pump System _I&C_Loop]_Control Loop Diagram for BOP | FA | 2017-04-28 | 2017-07-31 | 2018-08-24 | GRT-DS-IP-DT-180203 | FC | 1 | 2018-09-06 | 161313-1 | FC | 1 | A | 2017-05-19 | 2017-07-31
358 | DHI | GRT-YF00-P0ZEN-161401 | 161401 | [INC_PMC]_Plant Master Control Diagram | FA | 2017-07-14 | 2017-10-12 | 2018-07-26 | GRT-DS-IP-DT-180189 | FC | 1 | 2018-08-02 | 161401-1 | FC | 1 | A | 2017-08-01 | 2017-11-27
359 | DHI | GRT-YF00-P0ZEN-161402 | 161402 | [INC_Start&Shutdown Diagram]_Plant Start-up & Shutdown Sequence Diagram - Symbol & Legend | FA | 2017-08-18 | 2017-11-16 | 2017-10-26 | GRT-DS-IP-DT-170368 | FC | 0 | 2017-11-02 | 161402-0 | FC | 0 | A | 2017-09-11 | 2017-10-26
360 | DHI | GRT-YF00-P0ZEN-161403 | 161403 | [INC_Start&Shutdown Diagram]_Plant Start-up & Shutdown Sequence Diagram for Cold Start-up | FA | 2017-08-18 | 2017-11-16 | 2017-10-26 | GRT-DS-IP-DT-170369 | FC | 0 | 2017-11-02 | 161403-0 | FC | 0 | A | 2017-09-20 | 2017-10-26
361 | DHI | GRT-YF00-P0ZEN-161404 | 161404 | [INC_Start&Shutdown Diagram]_Plant Start-up & Shutdown Sequence Diagram for Warm Start-up | FA | 2017-08-18 | 2017-11-16 | 2017-10-26 | GRT-DS-IP-DT-170369 | FC | 0 | 2017-11-02 | 161404-0 | FC | 0 | A | 2017-09-20 | 2017-10-26
362 | DHI | GRT-YF00-P0ZEN-161405 | 161405 | [INC_Start&Shutdown Diagram]_Plant Start-up & Shutdown Sequence Diagram for Hot Start-up | FA | 2017-08-18 | 2017-11-16 | 2017-10-26 | GRT-DS-IP-DT-170369 | FC | 0 | 2017-11-02 | 161405-0 | FC | 0 | A | 2017-09-20 | 2017-10-26
363 | DHI | GRT-YF00-P0ZEN-161406 | 161406 | [INC_Start&Shutdown Diagram]_Plant Start-up & Shutdown Sequence Diagram for Shutdown | FA | 2017-08-18 | 2017-11-16 | 2017-11-27 | GRT-DS-IP-DT-170463 | FC | 0 | 2018-04-26 | 30-5th DRM | FC | 0 | A | 2017-10-30 | 2017-11-27
364 | DHI | GRT-CV03-P0ZEN-162301 | 162301 | [VMS]_Technical Specification & Datasheet for Vibration Monitoring System | FA | 2017-06-09 | 2017-09-15 | 2019-01-21 | GRT-DS-IP-DT-180269 | FC | 1 | 2019-01-21 | 162301-2 | FC | 1 | A | 2017-06-14 | 2017-11-01
365 | DHI | GRT-YS05-P0ZEN-162701 | 162701 | [INC_Design_Criteria_Cable]_Typical I&C Cable Installation Drawing for Field Instrument | FI | 2017-03-17 | 2017-07-31 | 2017-07-17 | GRT-DS-IP-DT-170152 | FC | 0 | 2017-07-17 |  | FC | 0 | A | 2017-03-22 | 2017-07-17
366 | DHI | GRT-YS05-P0ZEN-162702 | 162702 | [INC_Design_Criteria_Cable]_Typical I&C Cable Installation Drawing for Control Valve | FI | 2017-03-17 | 2017-07-31 | 2017-07-17 | GRT-DS-IP-DT-170152 | FC | 0 | 2017-07-17 |  | FC | 0 | A | 2017-03-22 | 2017-07-17
367 | DHI | GRT-YS05-P0ZEN-162703 | 162703 | [INC_Design_Criteria_Cable]_Typical I&C Cable Installation Drawing for MOV | FI | 2017-03-17 | 2017-07-31 | 2017-07-17 | GRT-DS-IP-DT-170152 | FC | 0 | 2017-07-17 |  | FC | 0 | A | 2017-03-22 | 2017-07-17
368 | DHI | GRT-YS05-P0ZEN-162704 | 162704 | [INC_Design_Criteria_Cable]_Typical I&C Cable Installation Drawing for Instrument Rack and Junction Box | FI | 2017-03-17 | 2017-07-31 | 2017-07-17 | GRT-DS-IP-DT-170152 | FC | 0 | 2017-07-17 |  | FC | 0 | A | 2017-03-22 | 2017-07-17
369 | DHI | GRT-YS05-P0ZEN-162705 | 162705 | [INC_Design_Criteria_Cable]_Typical I&C Cable Installation Drawing for Conduit Support | FI | 2017-03-17 | 2017-07-31 | 2017-07-17 | GRT-DS-IP-DT-170152 | FC | 0 | 2017-07-17 |  | FC | 0 | A | 2017-03-22 | 2017-07-17
370 | DHI | GRT-YS00-P0ZEN-163301 | 163301 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram - Index | FA | 2017-03-03 | 2017-05-31 | 2017-06-05 | GRT-DS-IP-DT-170091 | FC | 0 | 2017-06-05 | 163301-0 | FC | 0 | A | 2017-03-22 | 2017-06-05
371 | DHI | GRT-YS00-P0ZEN-163302 | 163302 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Motor Operated Valve (Internal MCC) | FA | 2017-03-03 | 2017-05-31 | 2017-06-05 | GRT-DS-IP-DT-170091 | FC | 0 | 2017-06-05 | 163302-0 | FC | 0 | A | 2017-03-22 | 2017-06-05
372 | DHI | GRT-YS00-P0ZEN-163303 | 163303 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Pneumatic Shut-off Valve (Double Coil SOV) | FA | 2017-03-03 | 2017-05-31 | 2017-06-05 | GRT-DS-IP-DT-170091 | FC | 0 | 2017-06-05 | 163303-0 | FC | 0 | A | 2017-03-22 | 2017-06-05
373 | DHI | GRT-YS00-P0ZEN-163304 | 163304 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Pneumatic Shut-off Valve (Single Coil SOV) | FA | 2017-03-03 | 2017-05-31 | 2017-06-05 | GRT-DS-IP-DT-170091 | FC | 0 | 2017-06-05 | 163304-0 | FC | 0 | A | 2017-03-22 | 2017-06-05
374 | DHI | GRT-YS00-P0ZEN-163305 | 163305 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Modulating Control Actuator | FA | 2017-03-03 | 2017-05-31 | 2017-06-05 | GRT-DS-IP-DT-170091 | FC | 0 | 2017-06-05 | 163305-0 | FC | 0 | A | 2017-03-22 | 2017-06-05
375 | DHI | GRT-YS00-P0ZEN-163306 | 163306 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Analog Input | FA | 2017-03-03 | 2017-05-31 | 2017-06-05 | GRT-DS-IP-DT-170091 | FC | 0 | 2017-06-05 | 163306-0 | FC | 0 | A | 2017-03-22 | 2017-06-05
376 | DHI | GRT-YS00-P0ZEN-163307 | 163307 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Analog Output | FA | 2017-03-03 | 2017-05-31 | 2017-06-05 | GRT-DS-IP-DT-170091 | FC | 0 | 2017-06-05 | 163307-0 | FC | 0 | A | 2017-03-22 | 2017-06-05
377 | DHI | GRT-YS00-P0ZEN-163308 | 163308 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Binary Input | FA | 2017-03-03 | 2017-05-31 | 2017-06-05 | GRT-DS-IP-DT-170091 | FC | 0 | 2017-06-05 | 163308-0 | FC | 0 | A | 2017-03-22 | 2017-06-05
378 | DHI | GRT-YS00-P0ZEN-163309 | 163309 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Binary Output | FA | 2017-03-03 | 2017-05-31 | 2017-06-05 | GRT-DS-IP-DT-170091 | FC | 0 | 2017-06-05 | 163309-0 | FC | 0 | A | 2017-03-22 | 2017-06-05
379 | DHI | GRT-YS00-P0ZEN-163310 | 163310 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Electrical System | FA | 2017-07-21 | 2017-09-30 | 2017-09-06 | GRT-DS-IP-DT-170284 | FC | 0 | 2017-09-12 | 163310-0 | FC | 0 | A | 2017-07-17 | 2017-09-06
380 | DHI | GRT-YL00-P0ZEN-163700 | 163700 | [Field Instruments(DHI)]_Field Instrument List for BOP | FA | 2017-07-19 | 2017-10-31 | 2020-01-21 | GRT-DS-IP-DT-200017 | FC | 2 | 2020-01-21 | 163700-3 | FC | 2 | A | 2017-07-21 | 2017-11-27
381 | DHI | GRT-CV03-P0ZEN-163701 | 163701 | [Field Instruments(DHI)]_Technical Specification & Datasheet for Process Transmitter - BOP | FA | 2017-07-31 | 2017-10-31 | 2020-01-21 | GRT-DS-IP-DT-200017 | FC | 1 | 2020-01-21 | 163701-3 | FC | 1 | A | 2017-08-30 | 2017-11-27
382 | DHI | GRT-CV03-P0ZEN-163702 | 163702 | [Field Instruments(DHI)]_Technical Specification & Datasheet for Local Instrument - BOP | FA | 2017-07-31 | 2017-10-31 | 2018-04-20 | GRT-DS-IP-DT-180107 | FC | 1 | 2018-04-27 | 163702-1 | FC | 1 | A | 2017-08-30 | 2017-11-27
383 | DHI | GRT-CV03-P0ZEN-163703 | 163703 | [Field Instruments(DHI)]_Technical Specification & Datasheet for Flow Element - BOP | FA | 2017-07-31 | 2017-10-31 | 2018-04-02 | GRT-DS-IP-DT-180084 | FC | 1 | 2018-04-06 | 163703-1 | FC | 1 | A | 2017-10-30 | 2017-11-30
384 | DHI | GRT-CV03-P0ZEN-163704 | 163704 | [Control Valves(DHI)]_Technical Specification & Datasheet for Control Valve - BOP | FA | 2017-07-21 | 2017-10-31 | 2018-03-21 | GRT-DS-IP-DT-180072 | FC | 1 | 2018-03-27 | 163704-1 | FC | 1 | A | 2017-08-01 | 2017-11-01
385 | DHI | GRT-CV03-P0ZEN-163705 | 163705 | [Instrument Installation materials(DHI)]_Technical Specification for Instrument Installation Materials | FA | 2017-07-19 | 2017-10-31 | 2017-09-14 | GRT-DS-IP-DT-170291 | FC | 0 | 2017-09-18 | 163705-0 | FC | 0 | A | 2017-07-21 | 2017-09-14
386 | DHI | GRT-CV03-P0ZEN-163706 | 163706 | [Local Boxes(DHI)]_Technical Specification for Junction Box & Racks | FA | 2017-07-25 | 2017-11-05 | 2017-11-29 | GRT-DS-IP-DT-170492 | FC | 1 | 2017-12-18 | 163706-1 | FC | 1 | A | 2017-07-26 | 2017-09-29
387 | DHI | GRT-YK00-P0ZEN-164301 | 164301 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - General Notes | FI | 2017-04-21 | 2017-08-31 | 2020-01-18 | GRT-DS-IP-DT-200007 | FC | 1 | 2020-01-18 | 164301-2 | FC | 1 | A | 2017-05-11 | 2017-09-14
388 | DHI | GRT-YK00-P0ZEN-164302 | 164302 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Symbol & Legend | FI | 2017-04-21 | 2017-08-31 | 2020-01-18 | GRT-DS-IP-DT-200007 | FC | 1 | 2020-01-18 | 164302-2 | FC | 1 | A | 2017-05-11 | 2017-09-14
389 | DHI | GRT-YK00-P0ZEN-164303 | 164303 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Material List | FI | 2017-04-21 | 2017-08-31 | 2020-01-18 | GRT-DS-IP-DT-200007 | FC | 1 | 2020-01-18 | 164303-2 | FC | 1 | A | 2017-05-11 | 2017-09-14
390 | DHI | GRT-YK00-P0ZEN-164304 | 164304 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Pressure Transmitter / Switch | FI | 2017-04-21 | 2017-08-31 | 2020-01-18 | GRT-DS-IP-DT-200007 | FC | 1 | 2020-01-18 | 164304-2 | FC | 1 | A | 2017-05-11 | 2017-09-14
391 | DHI | GRT-YK00-P0ZEN-164305 | 164305 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Diff. Press. Transmitter / Switch | FI | 2017-04-21 | 2017-08-31 | 2020-01-18 | GRT-DS-IP-DT-200007 | FC | 1 | 2020-01-18 | 164305-2 | FC | 1 | A | 2017-05-11 | 2017-09-14
392 | DHI | GRT-YK00-P0ZEN-164306 | 164306 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Flow Transmitter / Switch | FI | 2017-04-21 | 2017-08-31 | 2020-01-18 | GRT-DS-IP-DT-200007 | FC | 1 | 2020-01-18 | 164306-2 | FC | 1 | A | 2017-05-11 | 2017-09-14
393 | DHI | GRT-YK00-P0ZEN-164307 | 164307 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Level Transmitter / Switch | FI | 2017-04-21 | 2017-08-31 | 2020-01-18 | GRT-DS-IP-DT-200007 | FC | 1 | 2020-01-18 | 164307-2 | FC | 1 | A | 2017-05-11 | 2017-09-14
394 | DHI | GRT-YK00-P0ZEN-164308 | 164308 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Pressure Gauge | FI | 2017-04-21 | 2017-08-31 | 2020-01-18 | GRT-DS-IP-DT-200007 | FC | 1 | 2020-01-18 | 164308-2 | FC | 1 | A | 2017-05-11 | 2017-09-14
395 | DHI | GRT-YK00-P0ZEN-164309 | 164309 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Control Valve | FI | 2017-04-21 | 2017-08-31 | 2020-01-18 | GRT-DS-IP-DT-200007 | FC | 1 | 2020-01-18 | 164309-2 | FC | 1 | A | 2017-05-11 | 2017-09-14
396 | DHI | GRT-YK00-P0ZEN-164310 | 164310 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Stanchion & Rack | FI | 2017-04-21 | 2017-08-31 | 2020-01-18 | GRT-DS-IP-DT-200007 | FC | 1 | 2020-01-18 | 164310-2 | FC | 1 | A | 2017-05-11 | 2017-09-14
397 | DHI | GRT-YD08-P0UMA-164311 | 164311 | [Steam Turbine Building_INC_ILD]_BOP_Instrument Location Drawing | FI | 2017-07-25 | 2017-11-05 | 2018-07-26 | GRT-DS-IP-DT-180184 | FC | 1 | 2018-08-02 | 164311-1 | FC | 1 | B | 2017-07-26 | 2017-11-27
398 | DHI | GRT-YK00-P0ZEN-164312 | 164312 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Temp.Transmitter/ Guage/ Test Well | FI | 2017-04-21 | 2017-08-31 | 2020-01-18 | GRT-DS-IP-DT-200007 | FC | 1 | 2020-01-18 | 164312-2 | FC | 1 | A | 2017-05-11 | 2017-09-14
399 | DHI | GRT-XB00-P0MA-200001 | 200001 | [STG]_Foundation - Shape & Anchoring | FI | 2017-02-28 | 2017-07-14 | 2017-06-21 | GRT-DS-IP-DT-170126 | FC | 0 | 2017-06-22 |  | FC | 0 | A | 2017-03-22 | 2017-06-21
400 | DHI | GRT-XB00-P0MA-200002 | 200002 | [STG]_Foundation - Embedded Elements | FI | 2017-02-28 | 2017-07-14 | 2017-08-15 | GRT-DS-IP-DT-170226 | FC | 0 | 2017-08-25 |  | FC | 0 | A | 2017-03-22 | 2017-08-15
401 | DHI | GRT-XB00-P0MA-200003 | 200003 | [STG]_Foundation - Static & Dynamic Calculation | FI | 2017-02-28 | 2017-08-08 | 2017-08-15 | GRT-DS-IP-DT-170226 | FC | 0 | 2017-08-25 |  | FC | 0 | A | 2017-03-22 | 2017-08-15
402 | DHI | GRT-CA03-P0MA-200004 | 200004 | [STG]_Steel structures | FA | 2017-10-25 | 2018-02-24 | 2018-02-08 | GRT-DS-IP-DT-180035 | FC | 0 | 2018-03-01 | 200004-0 | FC | 0 | A | 2017-10-30 | 2018-02-08
403 | DHI | GRT-XG08-P0MA-200005 | 200005 | [STG]_P&I Diagrams | FA | 2017-03-10 | 2017-07-09 | 2019-10-24 | GRT-DS-IP-DT-190149 | FC | 3 | 2019-10-24 | 200005-3 | FC | 3 | A | 2017-03-22 | 2017-09-20
404 | DHI | GRT-YD00-P0MA-200006 | 200006 | [STG]_General Arrangement Drawing | FA | 2017-03-10 | 2017-09-25 | 2019-01-15 | GRT-DS-IP-DT-190004 | FC | 1 | 2019-01-15 | 200006-1 | FC | 1 | A | 2017-03-22 | 2017-09-29
405 | DHI | GRT-XB00-P0MA-200007 | 200007 | [STG]_Foundation load plan | FI | 2017-03-10 | 2017-07-14 | 2017-06-20 | GRT-DS-IP-DT-170122 | FC | 0 | 2017-06-20 |  | FC | 0 | A | 2017-03-22 | 2017-06-20
406 | DHI | GRT-XB00-P0MA-200008 | 200008 | [STG]_Loads plan - Levels | FI | 2017-06-19 | 2017-11-24 | 2019-01-15 | GRT-DS-IP-DT-190004 | FC | 1 | 2019-01-15 | 200008-1 | FC | 1 | A | 2017-06-02 | 2017-12-15
407 | DHI | GRT-XB00-P0MA-200009 | 200009 | [STG]_Lay down plan | FI | 2017-05-21 | 2017-09-20 | 2017-09-29 | GRT-DS-IP-DT-170321 | FC | 0 | 2017-10-02 | 200009-0 | FC | 0 | A | 2017-05-23 | 2017-09-29
408 | DHI | GRT-XV00-P0MA-200010 | 200010 | [STG]_List of pipelines | FI | 2017-05-21 | 2017-08-08 | 2017-08-15 | GRT-DS-IP-DT-170226 | FC | 0 | 2017-08-25 |  | FC | 0 | A | 2017-05-23 | 2017-08-15
409 | DHI | GRT-XN00-P0MA-200011 | 200011 | [STG]_List of valves | FI | 2017-05-21 | 2017-08-08 | 2017-10-26 | GRT-DS-IP-DT-170375 | FC | 0 | 2017-11-02 | 200011-1 | FC | 0 | A | 2017-05-23 | 2017-10-26
410 | DHI | GRT-XV00-P0MA-200012 | 200012 | [STG]_List of equipments | FI | 2017-05-21 | 2017-10-25 | 2017-11-01 | GRT-DS-IP-DT-170419 | FC | 0 | 2017-11-02 | 200012-0 | FC | 0 | A | 2017-05-23 | 2017-11-01
411 | DHI | GRT-XB00-P0MA-200013 | 200013 | [STG]_Allowable loadings and displacements | FI | 2017-03-10 | 2017-10-25 | 2017-10-26 | GRT-DS-IP-DT-170400 | FC | 0 | 2017-11-02 | 200013-0 | FC | 0 | A | 2017-03-22 | 2017-10-26
412 | DHI | GRT-US02-P0MA-200014 | 200014 | [STG]_Detail drawings - piping, components and BOM | FI | 2018-01-22 | 2018-05-22 | 2019-10-24 | GRT-DS-IP-DT-190149 | FC | 2 | 2019-03-03 | 200014-3 | FC | 1 | A | 2018-01-19 | 2018-05-02
413 | DHI | GRT-YD00-P0MA-200017 | 200017 | [STG]_Layout - piping routing - | FI | 2017-05-21 | 2017-10-25 | 2017-11-01 | GRT-DS-IP-DT-170419 | FC | 0 | 2017-11-02 | 200017-0 | FC | 0 | A | 2017-05-23 | 2017-11-01
414 | DHI | GRT-DF04-P0MA-200018 | 200018 | [STG]_Stress analysis of piping | FI | 2017-10-25 | 2018-03-24 | 2018-02-08 | GRT-DS-IP-DT-180035 | FC | 0 | 2018-03-01 | 200018-0 | FC | 0 | A | 2017-10-30 | 2018-02-08
415 | DHI | GRT-YK09-P0MA-200020 | 200020 | [STG]_Functional description | FI | 2017-05-21 | 2017-08-28 | 2017-09-06 | GRT-DS-IP-DT-170277 | FC | 0 | 2017-09-08 | 200020-0 | FC | 0 | A | 2017-05-23 | 2017-09-06
416 | DHI | GRT-YD00-P0MA-200022 | 200022 | [STG]_Steam Turbine Auxiliaries outline drawing | FI | 2017-11-03 | 2018-02-02 | 2018-07-19 | GRT-DS-IP-DT-180178 | FC | 1 | 2018-08-02 | 200022-1 | FC | 1 | A | 2017-11-13 | 2018-02-14
417 | DHI | GRT-YD00-P0MA-200024 | 200024 | [STG]_Generator Specification | FI | 2017-05-14 | 2017-09-13 | 2017-10-26 | GRT-DS-IP-DT-170371 | FC | 0 | 2017-11-02 | 200024-0 | FC | 0 | A | 2017-05-19 | 2017-10-26
418 | DHI | GRT-YK09-P0MA-200025 | 200025 | [STG]_Excitation system | FI | 2017-11-11 | 2018-03-10 | 2019-12-19 | GRT-DS-IP-DT-190182 | FC | 1 | 2019-12-19 | 200025-1 | FC | 1 | A | 2017-10-30 | 2018-01-31
419 | DHI | GRT-YK09-P0MA-200026 | 200026 | [STG]_Line and Neutral Cubicles | FI | 2017-11-11 | 2018-03-10 | 2019-03-29 | GRT-DS-IP-DT-190048 | FC | 2 | 2019-03-29 | 200026-3 | FC | 2 | A | 2017-10-30 | 2018-01-23
420 | DHI | GRT-YK09-P0MA-200027 | 200027 | [STG]_Electrical Protections | FI | 2017-11-11 | 2018-03-10 | 2019-03-29 | GRT-DS-IP-DT-190050 | FC | 2 | 2019-03-29 | 200027-3 | FC | 2 | A | 2017-10-30 | 2018-01-23
421 | DHI | GRT-YK09-P0MA-200028 | 200028 | [STG]_Measuring and Synchronization | FI | 2017-11-11 | 2018-03-10 | 2019-10-23 | GRT-DS-IP-DT-190150 | FC | 1 | 2019-10-23 | 200028-1 | FC | 1 | A | 2017-10-30 | 2018-01-23
422 | DHI | GRT-YK09-P0MA-200029 | 200029 | [STG]_Frequency converter for turning gear | FI | 2017-11-11 | 2018-03-10 | 2019-10-23 | GRT-DS-IP-DT-190150 | FC | 2 | 2019-10-23 | 200029-2 | FC | 2 | A | 2017-10-30 | 2018-02-08
423 | DHI | GRT-YK09-P0MA-200030 | 200030 | [STG]_DC motor starter | FI | 2017-11-11 | 2018-03-10 | 2018-04-17 | GRT-DS-IP-DT-180104 | FC | 1 | 2018-04-27 | 200030-1 | FC | 1 | A | 2017-10-30 | 2018-02-08
424 | DHI | GRT-YK09-P0MA-200032 | 200032 | [STG]_Cabling system | FI | 2017-11-11 | 2018-03-10 | 2018-02-08 | GRT-DS-IP-DT-180035 | FC | 0 | 2018-02-20 | 200032-0 | FC | 0 | A | 2017-10-13 | 2018-02-08
425 | DHI | GRT-YK09-P0MA-200033 | 200033 | [STG]_Electrical system description | FI | 2017-05-14 | 2017-08-13 | 2017-11-01 | GRT-DS-IP-DT-170414 | FC | 0 | 2017-11-02 | 200033-0 | FC | 0 | B | 2017-05-19 | 2017-11-01
426 | DHI | GRT-YK00-P0MA-200034 | 200034 | [STG]_Hook ups | FA | 2017-05-14 | 2017-08-14 | 2019-03-05 | GRT-DS-IP-DT-190037 | FC | 1 | 2019-03-05 | 200034-2 | FC | 1 | A | 2017-05-19 | 2017-08-15
427 | DHI | GRT-YK09-P0MA-200035 | 200035 | [STG]_Instrumentation data sheets | FI | 2017-11-22 | 2018-03-24 | 2018-11-16 | GRT-DS-IP-DT-180242 | FC | 1 | 2018-11-16 | 200035-2 | FC | 1 | A | 2017-11-03 | 2018-03-21
428 | DHI | GRT-YF00-P0MA-200036 | 200036 | [STG]_Consumer schemes | FI | 2017-05-14 | 2017-09-13 | 2017-09-29 | GRT-DS-IP-DT-170327 | FC | 0 | 2017-10-02 | 200036-0 | FC | 0 | A | 2017-05-19 | 2017-09-29
429 | DHI | GRT-YL00-P0MA-200037 | 200037 | [STG]_Measurement list | FI | 2017-05-14 | 2017-09-13 | 2017-09-29 | GRT-DS-IP-DT-170327 | FC | 0 | 2017-10-02 | 200037-0 | FC | 0 | A | 2017-05-19 | 2017-09-29
430 | DHI | GRT-YL19-P0MA-200038 | 200038 | [STG]_Electrical load list | FI | 2017-03-28 | 2017-07-28 | 2017-08-15 | GRT-DS-IP-DT-170226 | FC | 0 | 2017-08-25 |  | FC | 0 | A | 2017-04-18 | 2017-08-15
431 | DHI | GRT-YU03-P0MA-200039 | 200039 | [STG]_Control system architecture | FA | 2017-03-28 | 2017-07-21 | 2017-11-27 | GRT-DS-IP-DT-170467 | FC | 0 | 2018-04-26 | 31-5th DRM | FC | 0 | A | 2017-04-10 | 2017-11-27
432 | DHI | GRT-YK00-P0MA-200040 | 200040 | [STG]_I&C Lay-outs | FI | 2017-05-22 | 2017-09-21 | 2019-01-15 | GRT-DS-IP-DT-190004 | FC | 1 | 2019-01-15 | 200040-1 | FC | 1 | A | 2017-07-13 | 2017-09-29
433 | DHI | GRT-YU03-P0MA-200041 | 200041 | [STG]_Control system function philosophy | FI | 2017-05-22 | 2017-09-21 | 2017-09-29 | GRT-DS-IP-DT-170333 | FC | 0 | 2017-10-02 | 200041-0 | FC | 0 | B | 2017-05-23 | 2017-09-29
434 | DHI | GRT-YU03-P0MA-200043 | 200043 | [STG]_Control system. Hardware specification | FI | 2017-07-22 | 2017-11-21 | 2019-02-11 | GRT-DS-IP-DT-190022 | FC | 2 | 2019-02-11 | 200043-2 | FC | 2 | A | 2017-09-29 | 2017-11-29
435 | DHI | GRT-YF00-P0MA-200044 | 200044 | [STG]_Logic diagrams for control of functional groups | FA | 2017-09-16 | 2017-12-22 | 2017-10-26 | GRT-DS-IP-DT-170406 | FC | 0 | 2017-11-02 | 200044-0 | FC | 0 | B | 2017-09-06 | 2017-10-26
436 | DHI | GRT-YL00-P0MA-200045 | 200045 | [STG]_List of signals | FI | 2017-03-22 | 2017-07-22 | 2017-08-15 | GRT-DS-IP-DT-170226 | FC | 0 | 2017-08-25 |  | FC | 0 | A | 2017-05-19 | 2017-08-15
437 | DHI | GRT-YL21-P0MA-200046 | 200046 | [STG]_Trips & Alarms settings | FI | 2017-09-16 | 2018-01-21 | 2017-10-26 | GRT-DS-IP-DT-170406 | FC | 0 | 2017-11-02 | 200046-0 | FC | 0 | B | 2017-09-06 | 2017-10-26
438 | DHI | GRT-YK08-P0MA-200047 | 200047 | [STG]_HMI design | FI | 2017-09-16 | 2018-01-21 | 2019-01-16 | GRT-DS-IP-DT-190008 | FC | 0 | 2019-01-16 | 200047-1 | FC | 0 | A | 2017-09-06 | 2018-02-08
439 | DHI | GRT-YL00-P0MA-200048 | 200048 | [STG]_I/O list | FI | 2017-11-22 | 2018-03-10 | 2018-03-19 | GRT-DS-IP-DT-180070 | FC | 0 | 2018-03-22 | 200048-1 | FC | 0 | A | 2017-11-29 | 2018-03-19
440 | DHI | GRT-YU03-P0MA-200049 | 200049 | [STG]_Wiring diagrams, Loop diagrams | FI | 2017-11-22 | 2018-03-10 | 2019-12-19 | GRT-DS-IP-DT-190182 | FC | 1 | 2019-12-19 | 200049-1 | FC | 1 | A | 2017-11-03 | #VALUE!
441 | DHI | GRT-YL15-P0MA-200050 | 200050 | [STG]_Cable list | FI | 2017-11-20 | 2018-02-19 | 2018-02-08 | GRT-DS-IP-DT-180035 | FC | 0 | 2018-02-20 | 200050-0 | FC | 0 | A | 2017-11-03 | 2018-02-08
442 | DHI | GRT-YK09-P0MA-200051 | 200051 | [STG]_Operating instructions for the steam turbine and accessories | FI | 2018-02-28 | 2018-05-22 | 2018-04-25 | GRT-DS-IP-DT-180112 | FC | 0 | 2018-05-04 | 200051-2 | FC | 0 | B | 2018-04-02 | 2018-04-25
443 | DHI | GRT-YK09-P0MA-200052 | 200052 | [STG]_Maintenance instructions for the steam turbine and accessories | FI | 2018-02-28 | 2018-05-22 | 2018-08-10 | GRT-DS-IP-DT-180201 | FC | 2 | 2018-08-30 | 200052-4 | FC | 2 | A | 2018-05-16 | 2018-06-05
444 | DHI | GRT-YK09-P0MA-200053 | 200053 | [STG]_Summary Operation and Maintenance instructions | FI | 2018-02-28 | 2018-05-22 | 2018-05-02 | GRT-DS-IP-DT-180108 | FC | 0 | 2018-05-04 | 200053-0 | FC | 0 | B | 2018-04-02 | 2018-05-02
445 | DHI | GRT-YK10-P0MA-200056 | 200056 | [STG]_Initial specification for TG installation | FI | 2018-02-28 | 2018-05-22 | 2018-04-17 | GRT-DS-IP-DT-180105 | FC | 0 | 2018-04-27 | 200056-0 | FC | 0 | B | 2017-05-23 | 2018-04-17
446 | DHI | GRT-YK10-P0MA-200057 | 200057 | [STG]_Instructions for steam turbine assembly | FI | 2018-02-28 | 2018-05-22 | 2018-04-17 | GRT-DS-IP-DT-180104 | FC | 0 | 2018-04-27 | 200057-0 | FC | 0 | B | 2018-03-06 | 2018-04-17
447 | DHI | GRT-YK10-P0MA-200058 | 200058 | [STG]_Main assembly manual | FI | 2018-02-28 | 2018-05-22 | 2018-05-02 | GRT-DS-IP-DT-180108 | FC | 0 | 2018-05-04 | 200058-0 | FC | 0 | B | 2018-04-02 | 2018-05-02
448 | DHI | GRT-YK09-P0MA-200059 | 200059 | [STG]_First commissioning and start-up TG | FI | 2018-02-28 | 2018-05-22 | 2018-08-10 | GRT-DS-IP-DT-180201 | FC | 2 | 2018-08-30 | 200059-4 | FC | 2 | A | 2018-05-16 | 2018-06-05
449 | DHI | GRT-YK10-P0MA-200061 | 200061 | [STG]_Assembly manual for auxiliary equipment | FI | 2018-05-18 | 2018-07-17 | 2018-07-12 | GRT-DS-IP-DT-180167 | FC | 0 | 2018-07-27 | 200061-0 | FC | 0 | A | 2018-05-31 | #VALUE!
450 | DHI | GRT-YK09-P0MA-200062 | 200062 | [STG]_Commissioning manual for auxiliary equipment | FI | 2018-06-20 | 2018-08-20 | 2018-08-24 | GRT-DS-IP-DT-180208 | FC | 0 | 2018-08-30 | 200062-1 | FC | 0 | A | #VALUE! | #VALUE!
451 | DHI | GRT-YK09-P0MA-200063 | 200063 | [STG]_ Elec. Heater panel | FI | 2018-12-10 | 2019-03-11 | 2019-01-21 | GRT-DS-IP-DT-190009 | FC | 0 | 2019-01-21 | 200063-0 | FC | 0 | A | #VALUE! | #VALUE!
452 | DHI | GRT-CQ02-P1H-300001 | 300001 | [HRSG]_INSTALLATION, OPERATION AND MAINTENANCE INSTRUCTION MANUAL | FA | 2018-02-28 | 2018-05-28 | 2018-08-10 | GRT-DS-IP-DT-180200 | FC | 0 | 2018-08-24 | 300001-0 | FC | 0 | A | 2018-03-27 | #VALUE!
453 | DHI | GRT-DF04-P1H-300002 | 300002 | [HRSG]_STRESS ANALYSIS ISOMETRIC DRAWING FOR CRITICAL PIPING | FA | 2017-04-20 | 2017-07-20 | 2017-07-17 | GRT-DS-IP-DT-170164 | FC | 0 | 2017-09-18 | 300002-1 | FC | 0 | B | 2017-06-08 | 2017-07-17
454 | DHI | GRT-DM02-P1H-300005 | 300005 | [HRSG]_GENERAL NOTE FOR STEEL STRUCTURE | FI | 2017-05-20 | 2017-08-20 | 2018-01-09 | GRT-DS-IP-DT-180003 | FC | 1 | 2018-01-24 | 300005-1 | FC | 1 | B | 2017-05-26 | 2017-09-27
455 | DHI | GRT-UE00-P1H-300006 | 300006 | [HRSG]_GENERAL ARRANGEMENT | FA | 2017-03-30 | 2017-06-30 | 2019-09-24 | GRT-DS-IP-DT-190139 | FC | 2 | 2019-09-24 | 300006-2 | FC | 2 | A | 2017-04-06 | 2017-10-26
456 | DHI | GRT-UE00-P1H-300007 | 300007 | [HRSG]_ARRANGEMENT OF CASING & FIELD ERECTION | FI | 2017-04-20 | 2017-07-20 | 2019-04-11 | GRT-DS-IP-DT-190064 | FC | 3 | 2019-04-11 | 300007-3 | FC | 3 | A | 2017-05-19 | 2017-07-24
457 | DHI | GRT-UE00-P1H-300008 | 300008 | [HRSG]_ARRANGEMENT OF INLET DUCT | FI | 2017-04-20 | 2017-07-20 | 2019-08-08 | GRT-DS-IP-DT-190103 | FC | 2 | 2019-08-08 | 300008-3 | FC | 2 | A | 2017-05-19 | 2017-08-24
458 | DHI | GRT-UE00-P1H-300009 | 300009 | [HRSG]_ARRANGEMENT OF MAIN STACK& FIELD ERECTION | FI | 2017-05-20 | 2017-08-20 | 2017-11-01 | GRT-DS-IP-DT-170420 | FC | 0 | 2018-04-26 | 32-5th DRM | FC | 0 | A | 2017-05-23 | 2017-11-01
459 | DHI | GRT-VN03-P1H-300010 | 300010 | [HRSG]_TYPICAL PLATFORM DETAIL FOR STEEL STRUCTURE | FI | 2017-05-20 | 2017-08-20 | 2018-01-09 | GRT-DS-IP-DT-180003 | FC | 1 | 2018-01-24 | 300010-1 | FC | 1 | B | 2017-05-26 | 2017-09-27
460 | DHI | GRT-VN03-P1H-300011 | 300011 | [HRSG]_TYPICAL HANDRAIL DETAIL FOR STEEL STRUCTURE | FI | 2017-05-20 | 2017-08-20 | 2017-07-05 | GRT-DS-IP-DT-170143 | FC | 0 | 2017-07-19 |  | FC | 0 | A | 2017-05-26 | 2017-07-05
461 | DHI | GRT-VN03-P1H-300012 | 300012 | [HRSG]_TYPICAL LADDER DETAIL FOR STEEL STRUCTURE | FI | 2017-05-20 | 2017-08-20 | 2017-08-24 | GRT-DS-IP-DT-170254 | FC | 0 | 2017-08-25 |  | FC | 0 | A | 2017-05-26 | 2017-08-24
462 | DHI | GRT-VN03-P1H-300013 | 300013 | [HRSG]_ARRANGEMENT FOR PLATFORM STRUCTURE | FI | 2017-05-20 | 2017-08-20 | 2018-01-09 | GRT-DS-IP-DT-180003 | FC | 1 | 2018-01-24 | 300013-1 | FC | 1 | B | 2017-05-26 | 2017-11-01
463 | DHI | GRT-XB02-P1H-300014 | 300014 | [HRSG]_COLUMN LOCATION FOR STEEL STRUCTURE AND STACK (WITH PLAN VIEW) | FA | 2017-03-30 | 2017-06-30 | 2017-07-24 | GRT-DS-IP-DT-170185 | FC | 0 | 2017-08-01 |  | FC | 0 | B | 2017-04-06 | 2017-07-24
464 | DHI | GRT-XB02-P1H-300015 | 300015 | [HRSG]_FOUNDATION LOAD TABLE FOR STEEL STRUCTURE AND STACK | FA | 2017-03-30 | 2017-06-30 | 2017-07-24 | GRT-DS-IP-DT-170185 | FC | 0 | 2017-08-01 |  | FC | 0 | B | 2017-04-06 | 2017-07-24
465 | DHI | GRT-XB02-P1H-300016 | 300016 | [HRSG]_BASE PLATE AND ANCHOR BOLTS DETAIL FOR STEEL STRUCTURE | FA | 2017-03-30 | 2017-06-30 | 2017-07-24 | GRT-DS-IP-DT-170185 | FC | 0 | 2017-08-01 |  | FC | 0 | B | 2017-04-06 | 2017-07-24
466 | DHI | GRT-XB02-P1H-300018 | 300018 | [HRSG]_FOUNDATION LOADING & LOCATION DRAWING FOR BLOWDOWN TANK | FA | 2017-03-23 | 2017-07-14 | 2017-07-24 | GRT-DS-IP-DT-170185 | FC | 0 | 2017-08-01 |  | FC | 0 | A | 2017-04-06 | 2017-07-24
467 | DHI | GRT-XG02-P1H-300020 | 300020 | [HRSG]_P&I DIAGRAM | FA | 2017-03-23 | 2017-07-14 | 2019-01-08 | GRT-DS-IP-DT-190002 | FC | 2 | 2019-01-08 | 300020-2 | FC | 2 | A | 2017-04-06 | 2017-09-27
468 | DHI | GRT-XH01-P1H-300021 | 300021 | [HRSG]_PIPE SUPPORT DRAWING FOR EXTERNAL PIPING | FI | 2017-09-20 | 2017-12-20 | 2018-02-14 | GRT-DS-IP-DT-180044 | FC | 1 | 2018-03-01 | 300021-1 | FC | 1 | A | 2017-09-27 | 2017-12-22
469 | DHI | GRT-XH01-P1H-300023 | 300023 | [HRSG]_PIPE SUPPORT DRAWINGS | FI | 2017-08-20 | 2017-12-20 | 2017-12-22 | GRT-DS-IP-DT-170530 | FC | 0 | 2018-04-26 | 92-5th DRM | FC | 0 | A | 2017-08-21 | 2017-12-22
470 | DHI | GRT-XJ00-P1H-300024 | 300024 | [HRSG]_ERECTION ISOMETRIC DRAWING FOR PIPNG FABRICATION STANDARD | FI | 2017-09-20 | 2017-12-20 | 2018-05-24 | GRT-DS-IP-DT-180137 | FC | 1 | 2018-05-25 | 300024-1 | FC | 1 | A | 2017-09-27 | 2017-12-27
471 | DHI | GRT-XL00-P1H-300028 | 300028 | [HRSG]_LINE LIST | FA | 2017-05-20 | 2017-08-20 | 2018-09-12 | GRT-DS-IP-DT-180216 | FC | 1 | 2018-09-20 | 300028-1 | FC | 1 | A | 2017-05-23 | 2017-08-24
472 | DHI | GRT-XN00-P1H-300029 | 300029 | [HRSG]_VALVE LIST | FI | 2017-04-20 | 2017-07-20 | 2018-07-05 | GRT-DS-IP-DT-180160 | FC | 1 | 2018-07-12 | 30029-1 | FC | 1 | A | 2017-05-17 | 2017-08-24
473 | DHI | GRT-XS00-P1H-300031 | 300031 | [HRSG]_SYSTEM DESCRIPTION | FA | 2017-04-20 | 2017-05-20 | 2017-07-05 | GRT-DS-IP-DT-170143 | FC | 0 | 2017-07-19 |  | FC | 0 | B | 2017-05-19 | 2017-07-05
474 | DHI | GRT-XS00-P1H-300032 | 300032 | [HRSG]_BLOWDOWN SYSTEM SUMMARY | FA | 2017-03-23 | 2017-07-14 | 2017-07-17 | GRT-DS-IP-DT-170164 | FC | 0 | 2017-09-18 | 300032-1 | FC | 0 | A | 2017-04-06 | 2017-07-17
475 | DHI | GRT-YB03-P1H-300033 | 300033 | [HRSG]_CABLE CONNECTION DIAGRAM | FA | 2017-08-20 | 2017-11-21 | 2019-05-21 | GRT-DS-IP-DT-190076 | FC | 1 | 2019-05-21 | 300033-1 | FC | 1 | A | 2017-09-14 | 2017-12-15
476 | DHI | GRT-YD00-P1H-300034 | 300034 | [HRSG]_PRESSURE PART ARRANGEMENT | FI | 2017-03-20 | 2017-07-20 | 2017-11-01 | GRT-DS-IP-DT-170420 | FC | 0 | 2018-04-26 | 34-5th DRM | FC | 0 | A | 2017-04-06 | 2017-11-01
477 | DHI | GRT-YD00-P1H-300035 | 300035 | [HRSG]_SPEC. & DRAWING FOR STEAM DRUM | FI | 2017-08-20 | 2017-10-20 | 2017-11-27 | GRT-DS-IP-DT-170486 | FC | 0 | 2017-12-18 | 300035-0 | FC | 0 | A | 2017-08-21 | 2017-11-27
478 | DHI | GRT-YD00-P1H-300036 | 300036 | [HRSG]_EQUIPMENT OUTLINE DRAWING FOR BLOWDOWN TANK | FI | 2017-06-20 | 2017-09-20 | 2017-08-24 | GRT-DS-IP-DT-170256 | FC | 0 | 2017-08-25 |  | FC | 0 | A | 2017-06-21 | 2017-08-24
479 | DHI | GRT-YD00-P1H-300037 | 300037 | [HRSG]_POWER DISTRIBUTION PANEL DRAWINGS | FA | 2017-09-20 | 2017-12-20 | 2019-04-05 | GRT-DS-IP-DT-190061 | FC | 1 | 2019-04-05 | 3000037-1 | FC | 1 | A | 2017-12-13 | 2017-12-27
480 | DHI | GRT-YD00-P1H-300039 | 300039 | [HRSG]_SPEC. & DRAWING FOR SAFETY & RELIEF VALVE | FA | 2017-07-20 | 2017-10-20 | 2017-10-26 | GRT-DS-IP-DT-170387 | FC | 0 | 2017-11-02 | 300039-0 | FC | 0 | A | 2017-07-21 | 2017-10-26
481 | DHI | GRT-YD00-P1H-300040 | 300040 | [HRSG]_SPEC. & DRAWING FOR STACK DAMPER | FA | 2017-07-20 | 2017-10-20 | 2019-04-29 | GRT-DS-IP-DT-190065 | FC | 1 | 2019-04-29 | 300040-1 | FC | 1 | A | 2017-07-21 | 2017-11-01
482 | DHI | GRT-YD00-P1H-300041 | 300041 | [HRSG]_SPEC. & DRAWING FOR SILENCER | FA | 2017-07-20 | 2017-10-20 | 2017-11-01 | GRT-DS-IP-DT-170420 | FC | 0 | 2018-04-26 | 36-5th DRM | FC | 0 | A | 2017-07-21 | 2017-11-01
483 | DHI | GRT-YD04-P1H-300042 | 300042 | [HRSG]_CABLE TRAY & RACEWAY LAYOUT DIAGRAM | FI | 2017-07-20 | 2017-10-20 | 2019-01-15 | GRT-DS-IP-DT-190005 | FC | 2 | 2019-01-15 | 300042-2 | FC | 2 | A | 2017-07-21 | 2017-10-26
484 | DHI | GRT-YF00-P1H-300044 | 300044 | [HRSG]_SEQUENCES & CONTROLS | FA | 2017-06-20 | 2017-09-20 | 2019-01-21 | GRT-DS-IP-DT-180276 | FC | 2 | 2019-01-21 | 300044-2 | FC | 2 | A | 2017-06-21 | 2017-12-27
485 | DHI | GRT-YK01-P1H-300048 | 300048 | [HRSG]_INSTRUMENT INSTALLATION DETAIL DRAWINGS | FA | 2017-07-20 | 2017-10-20 | 2018-11-14 | GRT-DS-IP-DT-180263 | FC | 2 | 2018-11-14 | 300048-2 | FC | 2 | A | 2017-07-21 | 2017-11-01
486 | DHI | GRT-YK09-P1H-300049 | 300049 | [HRSG]_SPECIALTY DRAWING FOR EXTERNAL PIPING | FI | 2017-09-20 | 2017-12-20 | 2017-12-22 | GRT-DS-IP-DT-170530 | FC | 0 | 2018-06-29 | 300049-0 | FC | 0 | A | 2017-09-27 | 2017-12-22
487 | DHI | GRT-YK10-P1H-300050 | 300050 | [HRSG]_MANUAL VALVE ASSEMBLY DRAWING FOR EXTERNAL PIPING | FI | 2017-09-20 | 2017-12-20 | 2018-05-24 | GRT-DS-IP-DT-180137 | FC | 1 | 2018-05-25 | 300050-1 | FC | 1 | A | 2017-09-27 | 2017-12-22
488 | DHI | GRT-YL00-P1H-300051 | 300051 | [HRSG]_INSTRUMENT LIST | FI | 2017-03-20 | 2017-07-20 | 2020-06-30 | GRT-DS-IP-DT-200056 | FC | 2 | [5 empty] | 2017-03-22 | 2017-09-27
489 | DHI | GRT-YL16-P1H-300052 | 300052 | [HRSG]_CABLE SCHEDULE | FA | 2017-08-20 | 2017-11-20 | 2019-08-08 | GRT-DS-IP-DT-190104 | FC | 2 | 2019-08-08 | 300052-2 | FC | 2 | A | 2017-11-02 | 2017-11-27
490 | DHI | GRT-YR01-P1H-300054 | 300054 | [HRSG]_CHEMICAL CLEANING PROCEDURE | FI | 2017-09-20 | 2017-12-20 | 2017-12-22 | GRT-DS-IP-DT-170530 | FC | 0 | 2018-04-26 | 98-5th DRM | FC | 0 | A | 2017-09-27 | 2017-12-22
491 | DHI | GRT-YR01-P1H-300055 | 300055 | [HRSG]_CONSERVATION PROCEDURE | FI | 2017-09-20 | 2017-12-20 | 2017-12-22 | GRT-DS-IP-DT-170530 | FC | 0 | 2018-04-26 | 99-5th DRM | FC | 0 | A | 2017-09-27 | 2017-12-22
492 | DHI | GRT-YT01-P1H-300056 | 300056 | [HRSG]_DATA & BOM OF INSULATION FOR DRUM AND BLOWDOWN TANK | FI | 2017-06-20 | 2017-09-20 | 2017-09-14 | GRT-DS-IP-DT-170279 | FC | 0 | 2017-09-18 | 300056-0 | FC | 0 | A | 2017-07-06 | 2017-09-14
493 | DHI | GRT-YT01-P1H-300057 | 300057 | [HRSG]_DATA & BOM OF INSULATION FOR INTERNAL PIPING | FI | 2017-08-20 | 2017-11-20 | 2017-11-27 | GRT-DS-IP-DT-170486 | FC | 0 | 2017-12-18 | 300057-0 | FC | 0 | A | 2017-08-21 | 2017-11-27
494 | DHI | GRT-YT01-P1H-300058 | 300058 | [HRSG]_PERFORMANCE AND OPERATIONAL DATA | FA | 2017-03-23 | 2017-06-20 | 2017-07-24 | GRT-DS-IP-DT-170185 | FC | 0 | 2017-08-25 |  | FC | 0 | A | 2017-04-06 | 2017-07-24
495 | DHI | GRT-YT01-P1H-300059 | 300059 | [HRSG]_MOV DATASHEET & DRAWINGS | FA | 2017-07-20 | 2017-10-20 | 2018-04-27 | GRT-DS-IP-DT-180117 | FC | 1 | 2018-05-04 | 300059-1 | FC | 1 | B | 2017-07-21 | 2017-11-01
496 | DHI | GRT-YT01-P1H-300060 | 300060 | [HRSG]_CV DATASHEET & DRAWINGS | FA | 2017-07-20 | 2017-10-20 | 2018-05-11 | GRT-DS-IP-DT-180124 | FC | 1 | 2018-05-16 | 300060-1 | FC | 1 | A | 2017-07-21 | 2017-11-01
497 | DHI | GRT-YT01-P1H-300061 | 300061 | [HRSG]_DESH. DATASHEET & DRAWINGS | FA | 2017-07-20 | 2017-10-20 | 2018-04-27 | GRT-DS-IP-DT-180117 | FC | 1 | 2018-05-04 | 300061-1 | FC | 1 | A | 2017-07-21 | 2017-11-01
498 | DHI | GRT-YT01-P1H-300062 | 300062 | [HRSG]_AIRCRAFT WARNING LIGHT DATASHEET & LAYOUT DIAGRAM | FI | 2017-10-20 | 2017-12-20 | 2018-10-26 | GRT-DS-IP-DT-180239 | FC | 2 | 2018-10-26 | 300062-2 | FC | 2 | A | 2017-12-13 | 2017-12-27
499 | DHI | GRT-YT01-P1H-300063 | 300063 | [HRSG]_CEMS DATASHEET & DRAWINGS | FA | 2017-09-20 | 2017-11-20 | 2020-06-30 | GRT-DS-IP-DT-200056 | FC | 3 | [5 empty] | 2017-09-27 | 2017-12-15
500 | DHI | GRT-YT02-P1H-300065 | 300065 | [HRSG]_REMOTE DRUM LEVEL INDICATOR DATASHEET & DRAWINGS | FA | 2017-09-20 | 2017-11-20 | 2017-11-27 | GRT-DS-IP-DT-170486 | FC | 0 | 2017-12-18 | 300065-0 | FC | 0 | A | 2017-09-27 | 2017-11-27
501 | DHI | GRT-YU02-P1H-300066 | 300066 | [HRSG]_ELECTRICAL SINGLE LINE DIAGRAMS | FI | 2017-05-20 | 2017-08-20 | 2018-04-25 | GRT-DS-IP-DT-180113 | FC | 1 | 2018-05-04 | 300066-1 | FC | 1 | A | 2017-05-23 | 2017-07-05
502 | DHI | GRT-DE00-P1H-300067 | 300067 | [HRSG]_PIPING MATERIAL CLASSIFICATION | FA | 2017-06-20 | 2017-09-20 | 2017-09-27 | GRT-DS-IP-DT-170308 | FC | 0 | 2017-10-29 | 300067-0 | FC | 0 | B | 2017-06-21 | 2017-09-27
503 | DHI | GRT-YT01-P1H-300068 | 300068 | [HRSG]_DIVERTER & GUILLOTINE DAMPER DOCUMENT PACKAGE | FA | 2017-08-29 | 2017-09-12 | 2020-06-30 | GRT-DS-IP-DT-200057 | FC | 2 | [5 empty] | 2017-09-14 | 2017-11-27
504 | DHI | GRT-YT01-P1H-300069 | 300069 | [HRSG]_ SPEC. & DRAWING FOR PREHEATER RECIRCULATION PUMP | FA | 2017-08-29 | 2017-11-29 | 2017-11-27 | GRT-DS-IP-DT-170486 | FC | 0 | 2017-12-18 | 300069-0 | FC | 0 | A | 2017-09-14 | 2017-11-27
505 | DHI | GRT-YD00-P1H-300070 | 300070 | [HRSG]_ERECTION ISOMETRIC DRAWING FOR SMALL BORE PIPING | FI | 2018-06-29 | 2018-07-27 | 2019-01-28 | GRT-DS-IP-DT-190012 | FC | 1 | 2019-01-28 | 300070-2 | FC | 1 | A | 2018-07-05 | #VALUE!
506 | DHI | GRT-YD00-P0PGB-400040 | 400040 | Outline Drawing for CCW Heat Exchanger | FA | 2017-03-08 | 2017-08-05 | 2018-04-02 | GRT-DS-IP-DT-180085 | FC | 3 | 2018-04-06 | 400040-3 | FC | 3 | A | 2017-03-22 | 2017-11-01
507 | DHI | GRT-YT10-P0PGB-400050 | 400050 | Thermal Calculation for CCW Heat Exchanger | FA | 2017-10-16 | 2017-12-22 | 2017-12-29 | GRT-DS-IP-DT-170545 | FC | 0 | 2018-04-26 | 134-5th DRM | FC | 0 | A | 2017-11-01 | 2017-12-29
508 | DHI | GRT-YT10-P0PGB-400060 | 400060 | Strength Calculation for CCW Heat Exchanger | FA | 2017-10-16 | 2017-12-22 | 2017-12-22 | GRT-DS-IP-DT-170539 | FC | 0 | 2018-04-26 | 120-5th DRM | FC | 0 | A | 2017-11-01 | 2017-12-22
509 | DHI | GRT-CQ02-P0PGB-400070 | 400070 | Operation and Maintenance Manual for CCW Heat Exchanger | FI | 2018-04-20 | 2018-06-30 | 2018-05-16 | GRT-DS-IP-DT-180129 | FC | 0 | 2018-05-16 | 400070-2 | FC | 0 | A | 2018-04-25 | 2018-05-16
510 | DHI | GRT-YK08-P0MAG-410001 | 410001 | Condenser_General Layout | FA | 2017-02-10 | 2017-05-10 | 2017-12-15 | GRT-DS-IP-DT-170506 | FC | 1 | 2018-04-26 | 102-5th DRM | FC | 1 | A | 2017-03-09 | 2017-09-20
511 | DHI | GRT-YK08-P0MAG-410002 | 410002 | Condenser_General Arrangement | FA | 2017-02-10 | 2017-05-10 | 2017-12-15 | GRT-DS-IP-DT-170506 | FC | 1 | 2018-04-26 | 65-5th DRM | FC | 1 | A | 2017-03-09 | 2017-09-20
512 | DHI | GRT-XL00-P0MAG-410003 | 410003 | Condenser_Connection List | FI | 2017-02-10 | 2017-05-10 | 2017-12-15 | GRT-DS-IP-DT-170506 | FC | 1 | 2018-04-26 | 103-5th DRM | FC | 1 | A | 2017-03-09 | 2017-09-20
513 | DHI | GRT-XL00-P0MAG-410004 | 410004 | Condenser_Connection Detail | FI | 2017-02-10 | 2017-05-10 | 2017-12-15 | GRT-DS-IP-DT-170506 | FC | 1 | 2018-04-26 | 104-5th DRM | FC | 1 | A | 2017-03-09 | 2017-09-20
514 | DHI | GRT-VL00-P0MAG-410005 | 410005 | Condenser_Foundation Assembly | FA | 2017-02-10 | 2017-05-10 | 2017-09-20 | GRT-DS-IP-DT-170298 | FC | 1 | 2017-09-26 | 410005-0 | FC | 1 | A | 2017-03-09 | 2017-05-19
515 | DHI | GRT-VL00-P0MAG-410006 | 410006 | Condenser_Foundation Detail | FA | 2017-02-10 | 2017-05-10 | 2017-05-31 | GRT-DS-IP-DT-170061 | FC | 0 | 2017-05-31 | APPROVED | FC | 0 | A | 2017-03-09 | 2017-05-19
516 | DHI | GRT-YT01-P0MAG-410007 | 410007 | Condenser_Data Sheet | FA | 2017-02-10 | 2017-05-10 | 2017-09-20 | GRT-DS-IP-DT-170298 | FC | 0 | 2017-09-26 | 410007-0 | FC | 0 | A | 2017-03-09 | 2017-09-20
517 | DHI | GRT-YT01-P0MAG-410008 | 410008 | Condenser_Nozzle Force and Moment | FI | 2017-02-10 | 2017-05-10 | 2017-05-31 | GRT-DS-IP-DT-170061 | FC | 0 | 2017-05-31 | APPROVED | FC | 0 | A | 2017-03-09 | 2017-05-19
518 | DHI | GRT-YT01-P0MAG-410009 | 410009 | Condenser_Performance Curves | FI | 2017-02-10 | 2017-05-10 | 2017-05-31 | GRT-DS-IP-DT-170061 | FC | 0 | 2017-05-31 | APPROVED | FC | 0 | A | 2017-03-09 | 2017-05-19
519 | DHI | GRT-YL00-P0MAG-410010 | 410010 | Condenser_Instrument list and Datasheet for Condenser | FA | 2017-07-30 | 2017-08-30 | 2018-01-19 | GRT-DS-IP-DT-180015 | FC | 1 | 2018-04-26 | 124-5th DRM | FC | 1 | A | 2017-12-13 | 2017-12-27
520 | DHI | GRT-CQ02-P0MAG-410011 | 410011 | Condenser_Instruction Manuals for Erection, Installation, Operation and Maintenance | FI | 2017-09-30 | 2017-11-30 | 2020-04-06 | GRT-DS-IP-DT-200035 | DCR | 0DCR2 | 2020-04-09 | 410011-3 | DCR | 0DCR2 | C | 2017-12-13 | 2017-12-27
521 | DHI | GRT-YK08-P0MAG-410012 | 410012 | Transition Piece Assembly between LP TBN and Condenser | FA | 2017-10-13 | 2017-12-30 | 2020-04-06 | GRT-DS-IP-DT-200035 | DCR | 1DCR2 | 2020-03-19 | 410012-2 | DCR | 1DCR1 | C | 2017-10-13 | 2017-12-20
522 | DHI | GRT-YK08-P0LAA-420001 | 420001 | Outline Drawing for Deaerator & Feedwater Storage Tank | FA | 2017-04-28 | 2017-06-29 | 2018-02-08 | GRT-DS-IP-DT-180037 | FC | 2 | 2018-04-26 | 125-5th DRM | FC | 2 | A | 2017-04-10 | 2017-07-18
523 | DHI | GRT-CV03-P0LAA-420002 | 420002 | Datasheet for Deaerator & Feedwater Storage Tank | FA | 2017-04-28 | 2017-06-29 | 2018-02-08 | GRT-DS-IP-DT-180037 | FC | 1 | 2018-04-26 | 126-5th DRM | FC | 1 | A | 2017-04-10 | 2017-07-18
524 | DHI | GRT-CQ02-P0LAA-420003 | 420003 | OPERATING AND MAINTENANCE MANUAL FOR DEAERATOR & FEEDWATER STORAGE TANK | FI | 2018-04-20 | 2018-06-30 | 2018-07-05 | GRT-DS-IP-DT-180164 | FC | 0 | 2018-07-12 | 420003-2 | FC | 0 | A | 2018-04-25 | 2018-05-07
525 | DHI | GRT-YD00-P0LCM-430010 | 430010 | Outline Drawing for Atmospheric Flash Tank | FA | 2017-03-08 | 2017-08-05 | 2017-12-18 | GRT-DS-IP-DT-170524 | FC | 1 | 2018-04-26 | 106-5th DRM | FC | 1 | A | 2017-03-09 | 2017-10-26
526 | DHI | GRT-YD00-P0PGB-430020 | 430020 | Outline Drawing for CCW Chemical Additive Tank | FA | 2017-03-08 | 2017-08-05 | 2017-12-18 | GRT-DS-IP-DT-170523 | FC | 1 | 2018-04-26 | 107-5th DRM | FC | 1 | A | 2017-03-09 | 2017-10-26
527 | DHI | GRT-YD00-P0PGB-430030 | 430030 | Outline Drawing for CCW Expansion Head Tank | FA | 2017-03-08 | 2017-08-05 | 2017-10-26 | GRT-DS-IP-DT-170392 | FC | 0 | 2017-11-02 | 430030-0 | FC | 0 | B | 2017-03-09 | 2017-10-26
528 | DHI | GRT-YT10-P0LCM-430110 | 430110 | Strength Calculation for Atmospheric Flash Tank | FA | 2017-10-20 | 2017-12-22 | 2017-12-29 | GRT-DS-IP-DT-170542 | FC | 0 | 2018-04-26 | 131-5th DRM | FC | 0 | A | 2017-11-01 | 2017-12-29
529 | DHI | GRT-YT10-P0PGB-430120 | 430120 | Strength Calculation for CCW Chemical Additive Tank | FA | 2017-10-20 | 2017-12-22 | 2017-12-29 | GRT-DS-IP-DT-170542 | FC | 0 | 2018-04-26 | 132-5th DRM | FC | 0 | A | 2017-11-01 | 2017-12-29
530 | DHI | GRT-YT10-P0PGB-430130 | 430130 | Strength Calculation for CCW Expansion Head Tank | FA | 2017-10-20 | 2017-12-22 | 2017-12-29 | GRT-DS-IP-DT-170542 | FC | 0 | 2018-04-26 | 133-5th DRM | FC | 0 | A | 2017-11-01 | 2017-12-29
531 | DHI | GRT-XG02-P0PAH-440001 | 440001 | Condenser Tube Cleaning System_P & I Diagram | FA | 2017-04-01 | 2017-10-31 | 2017-10-13 | GRT-DS-IP-DT-170361 | FC | 0 | 2017-10-13 | 440001-0 | FC | 0 | A | 2017-05-17 | 2017-10-13
532 | DHI | GRT-YK08-P0PAH-440002 | 440002 | Condenser Tube Cleaning System_Outline Drawing | FA | 2017-04-01 | 2017-10-31 | 2017-10-13 | GRT-DS-IP-DT-170361 | FC | 0 | 2017-10-13 | 440002-0 | FC | 0 | A | 2017-05-17 | 2017-10-13
533 | DHI | GRT-YK08-P0PAH-440003 | 440003 | Condenser Tube Cleaning System_Outline Drawing for Ball Recirculation unit | FA | 2017-04-01 | 2017-10-31 | 2020-01-22 | GRT-DS-IP-DT-200018 | FC | 1 | 2020-01-22 | 440003-3 | FC | 1 | A | 2017-05-17 | 2017-12-15
534 | DHI | GRT-YF00-P0PAH-440004 | 440004 | Control Logic for CTCS & Debris Filter | FI | 2017-06-01 | 2017-10-31 | 2017-11-13 | GRT-DS-IP-DT-170449 | FC | 0 | 2017-11-13 | 440004-0 | FC | 0 | A | 2017-08-25 | 2017-11-13
535 | DHI | GRT-YV02-P0PAH-440005 | 440005 | Cable Connection/wiring Diagram(for power, control & instrument cable) for CTCS & Debris Filter | FA | 2017-06-01 | 2017-10-31 | 2020-01-22 | GRT-DS-IP-DT-200018 | FC | 2 | 2020-01-22 | 440005-3 | FC | 2 | A | 2017-08-25 | 2017-12-15
536 | DHI | GRT-YB03-P0PAH-440006 | 440006 | Configuration Diagram of Package System for CTCS & Debris Filter | FA | 2017-06-01 | 2017-10-31 | 2018-01-17 | GRT-DS-IP-DT-180009 | FC | 1 | 2018-01-23 | 440006-1 | FC | 1 | A | 2017-08-25 | 2017-12-15
537 | DHI | GRT-YK08-P0PAH-440007 | 440007 | Outline Drawing for Control Panel of CTCS & Debris Filter | FA | 2017-06-01 | 2017-10-31 | 2018-01-17 | GRT-DS-IP-DT-180009 | FC | 1 | 2018-01-23 | 440007-1 | FC | 1 | A | 2017-08-25 | 2017-12-15
538 | DHI | GRT-YT01-P0PAH-440008 | 440008 | Condenser Tube Cleaning System_Technical Data Sheet | FA | 2017-04-01 | 2017-10-31 | 2017-10-13 | GRT-DS-IP-DT-170361 | FC | 0 | 2017-10-13 | 440008-0 | FC | 0 | B | 2017-05-17 | 2017-10-13
539 | DHI | GRT-CQ02-P0PAH-440009 | 440009 | Condenser Tube Cleaning system_Operation & Maintenance Manual | FI | 2018-05-04 | 2018-06-29 | 2018-09-20 | GRT-DS-IP-DT-180219 | FC | 0 | 2018-09-26 | 44009-1 | FC | 0 | A | #VALUE! | #VALUE!
540 | DHI | GRT-XG02-P0PAH-440051 | 440051 | CCW HEX Tube Cleaning System_P & I Diagram | FA | 2017-04-01 | 2017-10-31 | 2017-12-15 | GRT-DS-IP-DT-170508 | FC | 0 | 2018-04-26 | 67-5th DRM | FC | 0 | A | 2017-05-17 | 2017-12-15
541 | DHI | GRT-YK08-P0PAH-440052 | 440052 | CCW HEX Tube Cleaning System_Outline Drawing | FA | 2017-04-01 | 2017-10-31 | 2017-12-15 | GRT-DS-IP-DT-170508 | FC | 0 | 2018-04-26 | 68-5th DRM | FC | 0 | A | 2017-05-17 | 2017-12-15
542 | DHI | GRT-YK08-P0PAH-440053 | 440053 | CCW HEX Tube Cleaning System_Outline Drawing for Ball Recirculation unit | FA | 2017-04-01 | 2017-10-31 | 2017-12-15 | GRT-DS-IP-DT-170508 | FC | 0 | 2018-04-26 | 69-5th DRM | FC | 0 | A | 2017-05-17 | 2017-12-15
543 | DHI | GRT-YF00-P0PAH-440054 | 440054 | CCW HEX Tube Cleaning System_Control Logic | FI | 2017-06-01 | 2017-10-31 | 2017-11-13 | GRT-DS-IP-DT-170451 | FC | 0 | 2017-11-13 | 440054-0 | FC | 0 | A | 2017-08-25 | 2017-11-13
544 | DHI | GRT-YV02-P0PAH-440055 | 440055 | CCW HEX Tube Cleaning System_Cable Connection/wiring Diagram(for power, control & instrument cable) | FA | 2017-06-01 | 2017-10-31 | 2020-01-22 | GRT-DS-IP-DT-200018 | FC | 2 | 2020-01-22 | 440055-3 | FC | 2 | A | 2017-08-25 | 2017-12-15
545 | DHI | GRT-YB03-P0PAH-440056 | 440056 | CCW HEX Tube Cleaning System_Configuration Diagram of Package System | FA | 2017-06-01 | 2017-10-31 | 2018-01-17 | GRT-DS-IP-DT-180010 | FC | 1 | 2018-01-23 | 440056-1 | FC | 1 | A | 2017-08-25 | 2017-12-15
546 | DHI | GRT-YK08-P0PAH-440057 | 440057 | CCW HEX Tube Cleaning System_Outline Drawing for Control Panel | FA | 2017-06-01 | 2017-10-31 | 2018-01-17 | GRT-DS-IP-DT-180010 | FC | 1 | 2018-01-23 | 440057-1 | FC | 1 | A | 2017-08-25 | 2017-12-15
547 | DHI | GRT-YT01-P0PAH-440058 | 440058 | CCW HEX Tube Cleaning System_Technical Data Sheet | FA | 2017-04-01 | 2017-10-31 | 2017-10-13 | GRT-DS-IP-DT-170361 | FC | 0 | 2017-10-13 | 440058-0 | FC | 0 | B | 2017-05-17 | 2017-10-13
548 | DHI | GRT-CQ02-P0PAH-440059 | 440059 | CCW HEX Tube Cleaning system_Operation & Maintenance Manual | FI | 2018-06-30 | 2018-07-31 | 2019-01-24 | GRT-DS-IP-DT-190013 | FC | 0 | 2019-01-24 | 440059-1 | FC | 0 | A | #VALUE! | #VALUE!
549 | DHI | GRT-XG02-P0PBB-440101 | 440101 | Debris Filter_P & I Diagram | FA | 2017-04-01 | 2017-10-31 | 2017-10-13 | GRT-DS-IP-DT-170361 | FC | 0 | 2017-10-13 | 440101-0 | FC | 0 | A | 2017-05-17 | 2017-10-13
550 | DHI | GRT-YK08-P0PBB-440102 | 440102 | Debris Filter_Outline Drawing | FA | 2017-04-01 | 2017-10-31 | 2017-12-15 | GRT-DS-IP-DT-170508 | FC | 0 | 2018-04-26 | 70-5th DRM | FC | 0 | A | 2017-05-17 | 2017-12-15
551 | DHI | GRT-YT01-P0PBB-440103 | 440103 | Debris Filter_Technical Data Sheet | FA | 2017-04-01 | 2017-10-31 | 2017-10-13 | GRT-DS-IP-DT-170361 | FC | 0 | 2017-10-13 | 440103-0 | FC | 0 | B | 2017-05-17 | 2017-10-13
552 | DHI | GRT-CQ02-P0PAH-440104 | 440104 | Debris Filter_Operation & Maintenance Manual | FI | 2018-05-04 | 2018-06-29 | 2018-09-20 | GRT-DS-IP-DT-180219 | FC | 0 | 2018-09-26 | 44104-1 | FC | 0 | A | #VALUE! | #VALUE!
553 | DHI | GRT-YK08-P0MAJ-460100 | 460100 | General Arrangement Drawing For Condenser Vacuum Pump | FA | 2017-06-30 | 2017-09-08 | 2017-12-22 | GRT-DS-IP-DT-170535 | FC | 2 | 2018-04-26 | 109-5th DRM | FC | 2 | A | 2017-07-13 | 2017-09-29
554 | DHI | GRT-XG02-P0MAJ-460101 | 460101 | P & ID For Condenser Vacuum Pump | FA | 2017-06-16 | 2017-09-08 | 2018-01-17 | GRT-DS-IP-DT-180011 | FC | 1 | 2018-04-26 | 128-5th DRM | FC | 1 | A | 2017-06-20 | 2017-09-29
555 | DHI | GRT-YV02-P0MAJ-460102 | 460102 | Wiring Diargam For Condenser Vacuum Pump | FI | 2017-06-30 | 2017-09-08 | 2017-10-26 | GRT-DS-IP-DT-170365 | FC | 0 | 2017-11-02 | 460102-0 | FC | 0 | A | 2017-08-21 | 2017-10-26
556 | DHI | GRT-YB10-P0MAJ-460103 | 460103 | Terminal Box For Condenser Vacuum Pump | FI | 2017-07-07 | 2017-09-08 | 2017-10-26 | GRT-DS-IP-DT-170365 | FC | 0 | 2017-11-02 | 460103-0 | FC | 0 | A | 2017-08-21 | 2017-10-26
557 | DHI | GRT-YT01-P0MAJ-460104 | 460104 | Technical Data Sheet for Condenser Vacuum Pump | FA | 2017-07-21 | 2017-09-08 | 2017-09-29 | GRT-DS-IP-DT-170322 | FC | 0 | 2017-10-02 | 460104-0 | FC | 0 | A | 2017-07-12 | 2017-09-29
558 | DHI | GRT-YT01-P0MAJ-460105 | 460105 | Motor Data sheet and Characteristic Curves and Drawing For CVP | FI | 2017-07-07 | 2017-09-08 | 2017-11-01 | GRT-DS-IP-DT-170396 | FC | 0 | 2017-11-02 | 17.007/E04/PLNE/X/2017 | FI | B | I | 2017-08-07 | 2017-11-01
559 | DHI | GRT-YT01-P0MAJ-460106 | 460106 | Heat Exchanger Drawing and Data Sheet For Condenser Vacuum Pump | FI | 2017-07-07 | 2017-09-08 | 2017-09-29 | GRT-DS-IP-DT-170322 | FC | 0 | 2017-10-02 | 460106-0 | FC | 0 | A | 2017-08-07 | 2017-09-29
560 | DHI | GRT-YL00-P0MAJ-460107 | 460107 | Instrument list For Condenser Vacuum Pump | FA | 2017-07-07 | 2017-09-08 | 2017-10-26 | GRT-DS-IP-DT-170395 | FC | 0 | 2017-11-02 | 460107-0 | FC | 0 | A | 2017-08-30 | 2017-10-26
561 | DHI | GRT-CQ02-P0MAJ-460108 | 460108 | Operation and Maintenance Manuals for Condenser & Water box vacuum pump | FI | 2017-11-10 | 2018-01-20 | 2018-01-17 | GRT-DS-IP-DT-180011 | FC | 0 | 2018-04-26 | 129-5th DRM | FC | 0 | A | 2017-11-13 | 2018-01-17
562 | DHI | GRT-XS00-P0MAJ-460109 | 460109 | Vacuum Pump System Description & Control Philosophy | FA | 2017-07-21 | 2017-09-08 | 2018-04-11 | GRT-DS-IP-DT-180102 | FC | 2 | 2018-04-25 | 460109-2 | FC | 2 | A | 2017-10-30 | 2017-11-27
563 | DHI | GRT-XB02-P0MAJ-460111 | 460111 | Foundation Drawing For Condenser Vacuum Pump | FI | 2017-07-07 | 2017-09-08 | 2017-09-29 | GRT-DS-IP-DT-170331 | FC | 0 | 2017-10-02 | 460111-0 | FC | 0 | A | 2017-08-21 | 2017-09-29
564 | DHI | GRT-XK00-P0MAJ-460112 | 460112 | Outline & Sectional Drawing For Condenser Vacuum Pump | FA | 2017-06-30 | 2017-09-08 | 2017-09-29 | GRT-DS-IP-DT-170322 | FC | 0 | 2017-10-02 | 460112-0 | FC | 0 | A | 2017-07-13 | 2017-09-29
565 | DHI | GRT-XK00-P0MAJ-460113 | 460113 | Tank Drawing For Condenser Vacuum Pump | FI | 2017-08-04 | 2017-09-08 | 2017-12-20 | GRT-DS-IP-DT-170526 | FC | 1 | 2018-04-26 | 110-5th DRM | FC | 1 | A | 2017-09-20 | 2017-11-01
566 | DHI | GRT-XK00-P0MAJ-460114 | 460114 | Baseframe Drawing For Condenser Vacuum Pump | FI | 2017-08-04 | 2017-09-08 | 2017-11-01 | GRT-DS-IP-DT-170393 | FC | 0 | 2017-11-03 | 460114-0 | FC | 0 | A | 2017-09-20 | 2017-11-01
567 | DHI | GRT-YT01-P0MAJ-460115 | 460115 | Recirculation Pump Data Sheet and Characteristic Curves and Drawing For CVP | FI | 2017-07-07 | 2017-09-08 | 2017-12-20 | GRT-DS-IP-DT-170526 | FC | 1 | 2018-04-26 | 111-5th DRM | FC | 1 | A | 2017-08-07 | 2017-11-01
568 | DHI | GRT-XK00-P0MAJ-460116 | 460116 | Name Plate Drawing For Condenser Vacuum Pump | FA | 2017-08-11 | 2017-09-08 | 2017-11-01 | GRT-DS-IP-DT-170393 | FC | 0 | 2017-11-02 | 20.011/E04/PLNE/X/2017 | FA | A | A | 2017-10-13 | 2017-11-01
569 | DHI | GRT-XK00-P0MAJ-460117 | 460117 | Coupling Drawing For Condenser Vacuum Pump | FI | 2017-07-21 | 2017-09-08 | 2017-11-01 | GRT-DS-IP-DT-170393 | FC | 0 | 2017-11-02 | 20.011/E04/PLNE/X/2017 | FI | A | I | 2017-10-13 | 2017-11-01
570 | DHI | GRT-DB00-P0MAJ-460118 | 460118 | Performance Curves For Condenser Vacuum Pump | FA | 2017-06-30 | 2017-09-08 | 2017-09-29 | GRT-DS-IP-DT-170331 | FC | 0 | 2017-10-02 | 460118-0 | FC | 0 | B | 2017-08-21 | 2017-09-29
571 | DHI | GRT-XN00-P0MAJ-460119 | 460119 | Valve and Specialty List For Condenser Vacuum Pump | FI | 2017-07-21 | 2017-09-08 | 2017-09-29 | GRT-DS-IP-DT-170322 | FC | 0 | 2017-10-02 | 460119-0 | FC | 0 | A | 2017-08-30 | 2017-09-29
572 | DHI | GRT-PL03-P0MAJ-460120 | 460120 | Terminal Point List For Condenser Vacuum Pump | FA | 2017-07-07 | 2017-09-08 | 2017-09-29 | GRT-DS-IP-DT-170322 | FC | 0 | 2017-10-02 | 460120-0 | FC | 0 | B | 2017-08-07 | 2017-09-29
573 | DHI | GRT-YL10-P0MAJ-460121 | 460121 | Spare Part List For Condenser Vacuum Pump | FI | 2017-07-14 | 2017-09-08 | 2017-09-06 | GRT-DS-IP-DT-170271 | FC | 0 | 2017-09-08 | 460121-0 | FC | 0 | A | 2017-08-07 | 2017-09-06
574 | DHI | GRT-DA06-P0MAJ-460122 | 460122 | Utility Consumption List For Condenser Vacuum Pump | FA | 2017-08-08 | 2017-11-08 | 2017-09-06 | GRT-DS-IP-DT-170271 | FC | 0 | 2017-09-08 | 460122-0 | FC | 0 | A | 2017-08-07 | 2017-09-06
575 | DHI | GRT-DA06-P0MAJ-460123 | 460123 | Lubricant List For Condenser Vacuum Pump | FI | 2017-07-14 | 2017-09-08 | 2017-09-06 | GRT-DS-IP-DT-170271 | FC | 0 | 2017-09-08 | 460123-0 | FC | 0 | A | 2017-08-07 | 2017-09-06
576 | DHI | GRT-YL00-P0MAJ-460127 | 460127 | Instrument Data sheet For Condenser Vacuum Pump | FI | 2017-07-14 | 2017-09-08 | 2017-09-20 | GRT-DS-IP-DT-170304 | FC | 0 | 2017-09-26 | 460127-0 | FC | 0 | A | 2017-08-07 | 2017-09-20
577 | DHI | GRT-YK08-P0MAJ-460200 | 460200 | General Arrangement Drawing For Water Box Vacuum Pump | FA | 2017-06-30 | 2017-09-08 | 2020-01-18 | GRT-DS-IP-DT-200005 | FC | 2 | 2020-01-18 | 460200-2 | FC | 2 | A | 2017-07-13 | 2017-09-29
578 | DHI | GRT-XG02-P0MAJ-460201 | 460201 | P & ID For Water Box Vacuum Pump | FA | 2017-06-16 | 2017-09-08 | 2018-01-17 | GRT-DS-IP-DT-180011 | FC | 1 | 2018-04-26 | 130-5th DRM | FC | 1 | A | 2017-06-20 | 2017-09-29
579 | DHI | GRT-YV02-P0MAJ-460202 | 460202 | Wiring Diargam For Water Box Vacuum Pump | FI | 2017-06-30 | 2017-09-08 | 2017-10-26 | GRT-DS-IP-DT-170365 | FC | 0 | 2017-11-02 | 460202-0 | FC | 0 | A | 2017-08-21 | 2017-10-26
580 | DHI | GRT-YB10-P0MAJ-460203 | 460203 | Terminal Box For Water Box Vacuum Pump | FI | 2017-07-07 | 2017-09-08 | 2017-10-26 | GRT-DS-IP-DT-170365 | FC | 0 | 2017-11-02 | 460203-0 | FC | 0 | A | 2017-08-21 | 2017-10-26
581 | DHI | GRT-YT01-P0MAJ-460205 | 460205 | Motor Data sheet and Characteristic Curves and Drawing For WBVP | FI | 2017-07-07 | 2017-09-08 | 2017-12-15 | GRT-DS-IP-DT-170507 | FC | 1 | 2018-04-26 | 72-5th DRM | FC | 1 | A | 2017-08-07 | 2017-11-01
582 | DHI | GRT-YT01-P0MAJ-460206 | 460206 | Heat Exchanger Drawing and Data Sheet For Water Box Vacuum Pump | FI | 2017-07-07 | 2017-09-08 | 2017-09-29 | GRT-DS-IP-DT-170322 | FC | 0 | 2017-10-02 | 460206-0 | FC | 0 | A | 2017-08-07 | 2017-09-29
583 | DHI | GRT-YL00-P0MAJ-460207 | 460207 | Instrument list For Water Box Vacuum Pump | FA | 2017-07-07 | 2017-09-08 | 2017-10-26 | GRT-DS-IP-DT-170395 | FC | 0 | 2017-11-02 | 460207-0 | FC | 0 | A | 2017-08-30 | 2017-10-26
584 | DHI | GRT-XB02-P0MAJ-460211 | 460211 | Foundation Drawing For Water Box Vacuum Pump | FI | 2017-07-07 | 2017-09-08 | 2017-11-27 | GRT-DS-IP-DT-170455 | FC | 1 | 2018-04-26 | 73-5th DRM | FC | 1 | A | 2017-08-21 | 2017-09-29
585 | DHI | GRT-XK00-P0MAJ-460212 | 460212 | Outline & Sectional Drawing For Water Box Vacuum Pump | FA | 2017-06-30 | 2017-09-08 | 2017-09-29 | GRT-DS-IP-DT-170322 | FC | 0 | 2017-10-02 | 460212-0 | FC | 0 | A | 2017-07-13 | 2017-09-29
586 | DHI | GRT-XK00-P0MAJ-460213 | 460213 | Tank Drawing For Water Box Vacuum Pump | FI | 2017-08-04 | 2017-09-08 | 2017-12-20 | GRT-DS-IP-DT-170526 | FC | 1 | 2018-04-26 | 112-5th DRM | FC | 1 | A | 2017-09-20 | 2017-11-01
587 | DHI | GRT-XK00-P0MAJ-460214 | 460214 | Baseframe Drawing For Water Box Vacuum Pump | FI | 2017-08-04 | 2017-09-08 | 2017-11-27 | GRT-DS-IP-DT-170455 | FC | 1 | 2018-04-26 | 74-5th DRM | FC | 1 | A | 2017-09-20 | 2017-11-01
588 | DHI | GRT-YT01-P0MAJ-460215 | 460215 | Recirculation Pump Data Sheet and Characteristic Curves and Drawing For WBVP | FI | 2017-07-07 | 2017-09-08 | 2017-11-01 | GRT-DS-IP-DT-170396 | FC | 0 | 2017-11-23 | 23.001/E04/PLNE/X/2017 | FI | B | I | 2017-08-07 | 2017-11-01
589 | DHI | GRT-XK00-P0MAJ-460216 | 460216 | Name Plate Drawing For Water Box Vacuum Pump | FA | 2017-08-11 | 2017-09-08 | 2017-11-01 | GRT-DS-IP-DT-170393 | FC | 0 | 2017-11-02 | 20.011/E04/PLNE/X/2017 | FA | A | A | 2017-10-13 | 2017-11-01
590 | DHI | GRT-XK00-P0MAJ-460217 | 460217 | Coupling Drawing For Water Box Vacuum Pump | FI | 2017-07-21 | 2017-09-08 | 2017-11-01 | GRT-DS-IP-DT-170393 | FC | 0 | 2017-11-02 | 20.011/E04/PLNE/X/2017 | FI | A | I | 2017-10-13 | 2017-11-01
591 | DHI | GRT-DB00-P0MAJ-460218 | 460218 | Performance Curves For Water Box Vacuum Pump | FA | 2017-06-30 | 2017-09-08 | 2017-09-29 | GRT-DS-IP-DT-170331 | FC | 0 | 2017-10-02 | 460218-0 | FC | 0 | B | 2017-08-21 | 2017-09-29
592 | DHI | GRT-XN00-P0MAJ-460219 | 460219 | Valve and Specialty List For Water Box Vacuum Pump | FI | 2017-07-21 | 2017-09-08 | 2017-09-29 | GRT-DS-IP-DT-170322 | FC | 0 | 2017-10-02 | 460219-0 | FC | 0 | A | 2017-08-30 | 2017-09-29
593 | DHI | GRT-PL03-P0MAJ-460220 | 460220 | Terminal Point List For Water Box Vacuum Pump | FA | 2017-07-07 | 2017-09-08 | 2017-09-29 | GRT-DS-IP-DT-170322 | FC | 0 | 2017-10-02 | 460220-0 | FC | 0 | B | 2017-08-07 | 2017-09-29
594 | DHI | GRT-YL10-P0MAJ-460221 | 460221 | Spare Part List For Water Box Vacuum Pump | FI | 2017-07-14 | 2017-09-08 | 2017-09-06 | GRT-DS-IP-DT-170271 | FC | 0 | 2017-09-08 | 460221-0 | FC | 0 | A | 2017-08-07 | 2017-09-06
595 | DHI | GRT-DA06-P0MAJ-460222 | 460222 | Utility Consumption List For Water Box Vacuum Pump | FA | 2017-08-08 | 2017-11-08 | 2017-09-06 | GRT-DS-IP-DT-170271 | FC | 0 | 2017-09-08 | 460222-0 | FC | 0 | A | 2017-08-07 | 2017-09-06
596 | DHI | GRT-DA06-P0MAJ-460223 | 460223 | Lubricant List For Water Box Vacuum Pump | FI | 2017-07-14 | 2017-09-08 | 2017-09-06 | GRT-DS-IP-DT-170271 | FC | 0 | 2017-09-08 | 460223-0 | FC | 0 | A | 2017-08-07 | 2017-09-06
597 | DHI | GRT-YL00-P0MAJ-460227 | 460227 | Instrument Data sheet For Water Box Vacuum Pump | FI | 2017-07-14 | 2017-09-08 | 2017-09-20 | GRT-DS-IP-DT-170304 | FC | 0 | 2017-09-26 | 460227-0 | FC | 0 | A | 2017-08-07 | 2017-09-20
598 | DHI | GRT-DN02-P0ZEN-820001 | 820001 | [Commissioning Program]_Steam Blowing-Out Emergency Response Plan | FI | 2019-12-03 | 2020-03-20 | 2019-12-04 | GRT-DS-IP-DT-190174 | FI | A | 2019-12-28 | 820001-0 | FI | A | I | #VALUE! | #VALUE!
599 | DHI | GRT-DN02-P0ZEN-830000 | 830000 | General Commissioning Procedure | FI | 2018-07-23 | 2018-09-25 | 2019-09-25 | GRT-DS-IP-DT-190141 | FC | 0 | 2019-09-25 | 830000-1 | FC | 0 | A | #VALUE! | #VALUE!
600 | DHI | GRT-DN02-P0LBA-830001 | 830001 | [Commissioning Procedure] HP & LP Steam System | FA | 2018-02-28 | 2018-04-30 | 2019-12-03 | GRT-DS-IP-DT-190173 | FC | 1 | 2019-12-03 | 830001-2 | FC | 1 | A | 2018-03-01 | #VALUE!
601 | DHI | GRT-DN02-P0LBG-830002 | 830002 | [Commissioning Procedure] Auxiliary Steam System | FA | 2018-01-30 | 2018-03-30 | 2019-11-20 | GRT-DS-IP-DT-190155 | FC | 1 | 2019-11-20 | 830002-2 | FC | 1 | A | 2018-02-01 | #VALUE!
602 | DHI | GRT-DN02-P0PC-830003 | 830003 | [Commissioning Procedure] Auxiliary Cooling Water System | FA | 2018-01-30 | 2018-03-30 | 2019-11-20 | GRT-DS-IP-DT-190154 | FC | 1 | 2019-11-20 | 830003-2 | FC | 1 | A | 2018-01-25 | #VALUE!
603 | DHI | GRT-DN02-P0PG-830004 | 830004 | [Commissioning Procedure] Closed Cooling Water system | FA | 2018-01-30 | 2018-03-30 | 2019-11-20 | GRT-DS-IP-DT-190156 | FC | 1 | 2019-11-20 | 840004-2 | FC | 1 | A | 2018-01-25 | #VALUE!
604 | DHI | GRT-DN02-P0LC-830005 | 830005 | [Commissioning Procedure] Condensate System | FA | 2018-01-30 | 2018-03-30 | 2019-12-03 | GRT-DS-IP-DT-190172 | FC | 1 | 2019-12-03 | 830005-2 | FC | 1 | A | 2018-01-25 | #VALUE!
605 | DHI | GRT-DN02-P0LA-830006 | 830006 | [Commissioning Procedure] Feedwater System | FA | 2018-01-30 | 2018-03-30 | 2019-11-25 | GRT-DS-IP-DT-190168 | FC | 1 | 2019-11-25 | 830006-2 | FC | 1 | A | 2018-01-29 | #VALUE!
606 | DHI | GRT-DN02-P0SCA-830007 | 830007 | [Commissioning Procedure] Compressed Air System | FA | 2018-02-28 | 2018-04-30 | 2019-11-21 | GRT-DS-IP-DT-190157 | FC | 1 | 2019-11-21 | 830007-2 | FC | 1 | A | 2018-01-29 | #VALUE!
607 | DHI | GRT-DN02-P0QC-830008 | 830008 | [Commissioning Procedure] Chemical Dosing System | FA | 2018-03-30 | 2018-05-30 | 2019-11-25 | GRT-DS-IP-DT-190164 | FC | 1 | 2019-11-25 | 830008-2 | FC | 1 | A | 2018-03-01 | #VALUE!
608 | DHI | GRT-DN02-P0QU-830009 | 830009 | [Commissioning Procedure] Sampling System | FA | 2018-03-30 | 2018-05-30 | 2019-11-25 | GRT-DS-IP-DT-190165 | FC | 1 | 2019-11-25 | 830009-2 | FC | 1 | A | 2018-03-01 | #VALUE!
609 | DHI | GRT-DN02-P0LBD-830010 | 830010 | [Commissioning Procedure] Condesate Filter System | FA | 2018-02-28 | 2018-04-30 | 2019-11-21 | GRT-DS-IP-DT-190159 | FC | 1 | 2019-11-21 | 830010-2 | FC | 1 | A | 2018-03-01 | #VALUE!
610 | DHI | GRT-DN02-P0MAJ-830011 | 830011 | [Commissioning Procedure] Condenser Vacuum System | FA | 2018-02-28 | 2018-04-30 | 2019-11-22 | GRT-DS-IP-DT-190160 | FC | 1 | 2019-11-22 | 830011-2 | FC | 1 | A | 2018-03-01 | #VALUE!
611 | DHI | GRT-DN02-P1H-830012 | 830012 | [Commissioning Procedure] HRSG | FA | 2018-03-30 | 2018-05-30 | 2019-12-03 | GRT-DS-IP-DT-190175 | FC | 1 | 2019-12-03 | 830012-2 | FC | 1 | A | 2018-04-06 | #VALUE!
612 | DHI | GRT-DN02-P1LBF-830013 | 830013 | [Commissioning Procedure] HRSG Safety Valve Popping Test | FA | 2018-03-30 | 2018-05-30 | 2020-01-04 | GRT-DS-IP-DT-200001 | FC | 2 | 2020-01-04 | 830013-4 | FC | 2 | A | 2018-03-01 | #VALUE!
613 | DHI | GRT-DN02-P0MAJ-830014 | 830014 | [Commissioning Procedure] Water box vacuum | FA | 2018-02-28 | 2018-04-30 | 2019-11-25 | GRT-DS-IP-DT-190167 | FC | 1 | 2019-11-25 | 830014-2 | FC | 1 | A | 2018-03-01 | #VALUE!
614 | DHI | GRT-DN02-P0PAH-830015 | 830015 | [Commissioning Procedure] CTCS / Debris filter | FA | 2018-02-28 | 2018-04-30 | 2019-11-25 | GRT-DS-IP-DT-190166 | FC | 1 | 2019-11-25 | 830015-2 | FC | 1 | A | 2018-03-01 | #VALUE!
615 | DHI | GRT-DN02-P1H-830016 | 830016 | [Commissioning Procedure] CEMS | FA | 2018-03-30 | 2018-05-30 | 2020-05-14 | GRT-DS-IP-DT-200048 | FC | 3 | [5 empty] | 2018-04-06 | #VALUE!
616 | DHI | GRT-DN02-P1H-830017 | 830017 | [Commissioning Procedure]_Bypass Damper | FA | 2019-07-15 | 2019-09-15 | 2019-08-22 | GRT-DS-IP-DT-190108 | FC | 0 | 2019-08-22 | 830017-1 | FC | 0 | A | #VALUE! | #VALUE!
617 | DHI | GRT-DN02-P0MAV-830018 | 830018 | [Commissioning Procedure] STG | FA | 2018-03-30 | 2018-05-30 | 2020-01-31 | GRT-DS-IP-DT-200020 | FC | 2 | 2019-11-28 | 830018-2 | FC | 1 | A | 2018-04-25 | #VALUE!
618 | DHI | GRT-DN02-P1ZEN-830019 | 830019 | [Commissioning Procedure] Disturbance Test | FA | 2018-04-30 | 2018-06-30 | 2020-06-12 | GRT-DS-IP-DT-200052 | FC | 3 | 2020-06-17 | 830016-6 | FC | 3 | A | #VALUE! | #VALUE!
619 | DHI | GRT-DN02-P1ZEN-830020 | 830020 | [Commissioning Procedure] Start-up Test | FA | 2018-04-30 | 2018-06-30 | 2020-07-10 | GRT-DS-IP-DT-200060 | FC | 2 | [5 empty] | #VALUE! | #VALUE!
620 | DHI | GRT-DN02-P1ZEN-830021 | 830021 | [Commissioning Procedure] Load Change Test | FA | 2018-04-30 | 2018-06-30 | 2020-06-15 | GRT-DS-IP-DT-200053 | FC | 4 | 2020-06-17 | 830021-6 | FC | 4 | A | #VALUE! | #VALUE!
621 | DHI | GRT-DN02-P1ZEN-830022 | 830022 | [Commissioning Procedure] Capacity Test | FA | 2018-04-30 | 2018-06-30 | 2019-11-25 | GRT-DS-IP-DT-190163 | FC | 1 | 2019-11-25 | 830022-2 | FC | 1 | A | #VALUE! | #VALUE!
622 | DHI | GRT-DN02-P1ZEN-830023 | 830023 | [Commissioning Procedure]_Fast cut back | FA | 2020-03-17 | 2020-04-17 | 2020-05-08 | GRT-DS-IP-DT-200046 | FC | 0 | 2020-05-08 | 830023-1 | FC | 0 | A | #VALUE! | #VALUE!
623 | DHI | GRT-DN02-P1ZEN-830026 | 830026 | [Commissioning Procedure] Reliability Test | FA | 2018-04-30 | 2018-06-30 | 2019-12-20 | GRT-DS-IP-DT-190183 | FC | 1 | 2019-12-20 | 830026-2 | FC | 1 | A | #VALUE! | #VALUE!
624 | DHI | GRT-DN02-P1ZEN-830027 | 830027 | [Commissioning Procedure] Performance Test | FA | 2018-07-30 | 2018-10-30 | 2019-12-10 | GRT-DS-IP-DT-190179 | FC | 1 | 2019-12-10 | 830027-3 | FC | 1 | A | #VALUE! | #VALUE!
625 | DHI | GRT-DN02-P1ZEN-830028 | 830028 | [Commissioning Procedure] Noise Test | FA | 2018-07-30 | 2018-10-30 | 2019-12-10 | GRT-DS-IP-DT-190178 | FC | 1 | 2019-12-10 | 830028-3 | FC | 1 | A | #VALUE! | #VALUE!
626 | DHI | GRT-DN02-P1ZEN-830024 | 830024 | [Commissioning Procedure]_Load Rejection | FA | 2020-03-20 | 2020-04-20 | 2020-05-06 | GRT-DS-IP-DT-200044 | FC | 0 | 2020-05-06 | 830024-1 | FC | 0 | A | #VALUE! | #VALUE!
627 | DHI | GRT-DN02-P1ZEN-830025 | 830025 | [Commissioning Procedure]_Island operation | FA | 2020-04-24 | 2020-05-22 | 2020-05-06 | GRT-DS-IP-DT-200043 | FC | 0 | 2020-05-06 | 830025-1 | FC | 0 | A | #VALUE! | #VALUE!
628 | PP | GRT-YD00-P0MAG-410103 | 410103 | Cathodic Protection System for Condenser_The Location of Anode (Inlet Waterbox) DCR 0008 | FA | 2019-10-14 | 2019-11-13 | 2019-11-13 | GRT-PP-IP-DT-191482 | FC | 1 | 2019-11-29 | 057/061/GRT/UPR/2019 |  | 1 | A | 2017-09-06 | 2017-10-26
629 | PP | GRT-YD00-P0MAG-410104 | 410104 | Cathodic Protection System for Condenser_The Location of Anode (Outlet Waterbox) DCR 0008 | FA | 2019-10-14 | 2019-11-13 | 2019-11-13 | GRT-PP-IP-DT-191482 | FC | 1 | 2019-11-29 | 057/061/GRT/UPR/2019 |  | 1 | A | 2017-09-06 | 2017-10-26
630 | PP | GRT-DA06-P0ZEN-115001 | 115001 | [Process General] Line List | FA | 2017-04-25 | 2017-05-25 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A | #VALUE! | #VALUE!
631 | PP | GRT-DA06-P0ZEN-115002 | 115002 | [Process General] Equipment list | FA | 2017-04-27 | 2017-05-27 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A | #VALUE! | #VALUE!
632 | PP | GRT-DA06-P0ZEN-115003 | 115003 | [Process General] Tie-In List | FA | 2017-05-02 | 2017-06-01 | 2017-05-02 | GRT-PP-IP-DT-170064 | FI | A | 2017-05-02 | 0002.001/C.1.2.17.01/E04/PLNE/V/2017 | FA | A | I | #VALUE! | #VALUE!
633 | PP | GRT-XG02-P0ZEN-115004 | 115004 | [Process General] Piping and Instrument Diagram (PID) Legends | FA | 2017-02-17 | 2017-03-19 | 2017-02-13 | GRT-PP-IP-DT-170012 | FI | A | 2017-02-03 | 0003.001/ADDONGRT150MW/E04/PLNE/II/2017 | FA | A | I | #VALUE! | #VALUE!
634 | PP | GRT-XG08-P0ZEN-115005 | 115005 | [Process General] Utility Flow Diagram for Sea Water Intake & Circulating Sea Water Cooling System | FA | 2017-04-01 | 2017-05-01 | 2017-09-27 | GRT-PP-IP-DT-170242 | FC | 0 | 2017-09-27 | N.A | FC | 0 | A | #VALUE! | #VALUE!
635 | PP | GRT-XG08-P0ZEN-115006 | 115006 | [Process General] Utility Flow Diagram for Raw Water System | FA | 2017-03-30 | 2017-04-29 | 2017-09-27 | GRT-PP-IP-DT-170242 | FC | 0 | 2017-09-27 | N.A | FC | 0 | A | #VALUE! | #VALUE!
636 | PP | GRT-XG08-P0ZEN-115007 | 115007 | [Process General] Water Balance Calculation | FA | 2017-03-28 | 2017-04-27 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A | #VALUE! | #VALUE!
637 | PP | GRT-XS03-P0ZEN-115008 | 115008 | [Process General] Process Description for BOP | FA | 2017-03-21 | 2017-04-20 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A | #VALUE! | #VALUE!
638 | PP | GRT-XS03-P0ZEN-115009 | 115009 | [Process General] Process Control Philosophy for BOP | FA | 2017-06-12 | 2017-07-12 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A | #VALUE! | #VALUE!
639 | PP | GRT-XW01-P0ZEN-115010 | 115010 | [Process General] Process Design Basis | FA | 2017-02-18 | 2017-03-20 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A | #VALUE! | #VALUE!
640 | PP | GRT-XW01-P0ZEN-115011 | 115011 | [Process General] BEDD | FA | 2017-02-18 | 2017-03-20 | 2017-09-25 | GRT-PP-IP-DT-170239 | FC | 0 | 2017-09-25 | N.A | FC | 0 | A | #VALUE! | #VALUE!
641 | PP | GRT-XW01-P0ZEN-115012 | 115012 | [Process General] Overpressure study | FA | 2017-06-15 | 2017-07-15 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A | #VALUE! | #VALUE!
642 | PP | GRT-XW01-P0ZEN-115013 | 115013 | [Process General] Process Simulation Report | FA | 2017-03-30 | 2017-04-29 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A | #VALUE! | #VALUE!
643 | PP | GRT-XW03-P0ZEN-115014 | 115014 | [Process General] Process Calculation for IA & PA consumption | FA | 2017-06-15 | 2017-07-15 | 2017-11-27 | GRT-PP-IP-DT-170339 | FC | 0 | 2017-11-27 | N.A | FC | 0 | A | #VALUE! | #VALUE!
644 | PP | GRT-XW03-P0ZEN-115015 | 115015 | [Process General] Line Sizing Calculation | FA | 2017-04-14 | 2017-05-14 | 2017-09-25 | GRT-PP-IP-DT-170239 | FC | 0 | 2017-09-25 | N.A | FC | 0 | A | #VALUE! | #VALUE!
645 | PP | GRT-XW03-P0ZEN-115016 | 115016 | [Process General] Hydraulic Calculation | FA | 2017-05-13 | 2017-06-12 | 2017-09-25 | GRT-PP-IP-DT-170239 | FC | 0 | 2017-09-25 | N.A | FC | 0 | A | #VALUE! | #VALUE!
646 | PP | GRT-DP00-P0ZEN-125019 | 125019 | [Mechanical General] Specification for Storage Tank | FA | 2017-02-25 | 2017-03-27 | 2017-05-09 | GRT-PP-IP-DT-170075 | FC | 0 | 2017-05-15 | N.A | FC | 0 | A | #VALUE! | #VALUE!
647 | PP | GRT-DP00-P0ZEN-125020 | 125020 | [Mechanical General] Specification for Centrifugal Pump | FA | 2017-02-25 | 2017-03-27 | 2017-09-06 | GRT-PP-IP-DT-170209 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A | #VALUE! | #VALUE!
648 | PP | GRT-DP00-P0ZEN-125021 | 125021 | [Mechanical General] Specification & Design Criteria for HVAC | FA | 2017-02-25 | 2017-03-27 | 2017-08-07 | GRT-PP-IP-DT-170172 | FC | 0 | 2017-08-07 | N.A | FC | 0 | A | #VALUE! | #VALUE!
649 | PP | GRT-YL19-P0ZEN-125022 | 125022 | [Mechanical General] Power Consumption List | FA | 2017-07-10 | 2017-08-09 | 2017-10-19 | GRT-PP-IP-DT-170276 | FI | B | 2017-10-24 | 0024.001/C.1.2.17.01/E04/PLNE/X/2017 | FA | B | I | #VALUE! | #VALUE!
650 | PP | GRT-CC00-P0ZEN-145023 | 145023 | [Piping General] Plot Plan for BOP | FA | 2017-02-04 | 2017-03-06 | 2017-11-27 | GRT-PP-IP-DT-170339 | FC | 0 | 2017-11-27 | N.A | FC | 0 | A | #VALUE! | #VALUE!
651 | PP | GRT-CC00-P0ZEN-145024 | 145024 | [Piping General] Information Drawing for Loading Data & Local Foundation Water Treatment Area | FA | 2017-06-07 | 2017-07-07 | 2017-06-02 | GRT-PP-IP-DT-170105 | FI | A | 2017-06-12 | 0012.001/C.1.2.17.01/E04/PLNE/VI/2017 | FA | A | I | #VALUE! | #VALUE!
652 | PP | GRT-CC00-P0ZEN-145025 | 145025 | [Piping General] Layout Crossing Road & Electrical Underground | FA | 2017-02-24 | 2017-09-07 | 2017-09-07 | GRT-PP-IP-DT-170212 | FC | 0 | 2017-09-07 | N.A | FC | 0 | A | #VALUE! | #VALUE!
653 | PP | GRT-CC00-P0ZEN-145026 | 145026 | [Piping General] Detail Crossing Road & Electrical Underground | FA | 2017-02-24 | 2017-03-26 | 2017-09-07 | GRT-PP-IP-DT-170212 | FC | 0 | 2017-09-07 | N.A | FC | 0 | A | #VALUE! | #VALUE!
654 | PP | GRT-CC00-P0ZEN-145027 | 145027 | [Piping General] Piping Layout Drawing for Sea Water System | FA | 2017-02-04 | 2017-03-06 | 2017-09-07 | GRT-PP-IP-DT-170212 | FC | 0 | 2017-09-07 | N.A | FC | 0 | A | #VALUE! | #VALUE!
655 | PP | GRT-CC05-P0ZEN-145028 | 145028 | [Piping General] Support Standard Drawing | FA | 2017-03-18 | 2017-04-17 | 2017-05-23 | GRT-PP-IP-DT-170089 | FC | I | 2017-05-29 | 0029.001/C.1.2.17.01/E04/PLNE/V/2017 | FA | I | I | #VALUE! | #VALUE!
656 | PP | GRT-CC07-P0ZEN-145029 | 145029 | [Piping General] Piping Wall Thickness Calculation | FA | 2017-02-10 | 2017-03-12 | 2017-05-22 | GRT-PP-IP-DT-170086 | FC | 0 | 2017-05-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
657 | PP | GRT-CV03-P0ZEN-145030 | 145030 | [Piping General] Piping Design Specification | FA | 2017-03-04 | 2017-04-03 | 2017-08-07 | GRT-PP-IP-DT-170172 | FC | 0 | 2017-08-07 | N.A | FC | 0 | A | #VALUE! | #VALUE!
658 | PP | GRT-DE00-P0ZEN-145031 | 145031 | [Piping General] Piping Fabrication and Installation | FA | 2017-03-15 | 2017-04-14 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A | #VALUE! | #VALUE!
659 | PP | GRT-DE00-P0ZEN-145032 | 145032 | [Piping General] Specification for Wrapping Tape Material | FA | 2017-03-02 | 2017-04-01 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A | #VALUE! | #VALUE!
660 | PP | GRT-DE00-P0ZEN-145033 | 145033 | [Piping General] Piping Material Specification | FA | 2017-02-11 | 2017-03-13 | 2017-12-20 | GRT-PP-IP-DT-170369 | FC | 1 | 2017-12-22 | 0022.001/C.I.2.17.01/E04/PLNE/XII/2017 | FC | 1 | A | #VALUE! | #VALUE!
661 | PP | GRT-DE00-P0ZEN-145034 | 145034 | [Piping General] Specification for Cement Lined for Carbon Stell pipe | FA | 2017-02-23 | 2017-03-25 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A | #VALUE! | #VALUE!
662 | PP | GRT-XJ00-P0ZEN-145035 | 145035 | [Piping General] Isometric Drawing | FA | 2017-06-07 | 2017-07-07 | 2020-05-14 | GRT-PP-IP-DT-201593 (DCR 00054) | FC | 2DCR0 | 2020-06-18 | 024-GRT-M-U-GPE-2020 |  | 2DCR0 | A | #VALUE! | #VALUE!
663 | PP | GRT-XV00-P0ZEN-145036 | 145036 | [Piping General] Pipe Support List | FA | 2017-06-07 | 2017-07-07 | 2019-04-02 | GRT-PP-IP-DT-191115 (DCR 00035) | FC | DCR | 2019-04-24 | 028/061/GRT/UPR/2019 | FC | DCR | B | #VALUE! | #VALUE!
664 | PP | GRT-XN00-P0ZEN-145037 | 145037 | [Piping General] Valve List | FA | 2017-03-11 | 2017-04-10 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 0 | 2017-08-04 | N.A | FC | 0 | A | #VALUE! | #VALUE!
665 | PP | GRT-YT01-P0ZEN-145038 | 145038 | [Piping General] Data Sheet for Valve | FA | 2017-03-18 | 2017-04-17 | 2017-10-12 | GRT-PP-IP-DT-170267 | FC | 0 | 2017-10-12 | N.A | FC | 0 | A | #VALUE! | #VALUE!
666 | PP | GRT-YT01-P0ZEN-145039 | 145039 | [Piping General] Data Sheet for Special Item | FA | 2017-03-18 | 2017-04-17 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A | #VALUE! | #VALUE!
667 | PP | GRT-YE00-P0ZEN-155040 | 155040 | [Electrical General] General Electrical Symbol List | FI | 2017-03-01 | 2017-03-31 | 2017-10-23 | GRT-PP-IP-DT-170282 | FI | B | 2017-10-25 | 0025.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | B | I | #VALUE! | #VALUE!
668 | PP | GRT-YE00-P0ZEN-155041 | 155041 | [Electrical General] Standard Installation Drawing for Electrical | FI | 2017-03-01 | 2017-03-31 | 2017-10-23 | GRT-PP-IP-DT-170282 | FI | B | 2017-10-25 | 0025.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | B | I | #VALUE! | #VALUE!
669 | PP | GRT-YE00-P0ZEN-155042 | 155042 | [Electrical General] General Area Clock System Wiring Layout | FA | 2017-03-15 | 2017-04-14 | 2017-11-20 | GRT-PP-IP-DT-170329 | FC | 0 | 2017-11-21 | N.A | FC | 0 | A | #VALUE! | #VALUE!
670 | PP | GRT-YE00-P0ZEN-155043 | 155043 | [Electrical General] General Area Clock System Wiring Layout | FA | 2017-03-15 | 2017-04-14 | 2017-11-20 | GRT-PP-IP-DT-170329 | FC | 0 | 2017-11-21 | N.A | FC | 0 | A | #VALUE! | #VALUE!
671 | PP | GRT-YE00-P0ZEN-155045 | 155045 | [Electrical General] Cable Tray, Trench and Power Wiring Layout for General Area | FA | 2017-06-10 | 2017-07-10 | 2017-09-08 | GRT-PP-IP-DT-170215 | FC | 1 | 2017-09-08 | N.A | FC | 1 | A | #VALUE! | #VALUE!
672 | PP | GRT-YE06-P0ZEN-155046 | 155046 | [Electrical General] Grounding Wiring Layout for General Area | FA | 2017-03-10 | 2017-04-09 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 1 | 2017-08-22 | N.A | FC | 1 | A | #VALUE! | #VALUE!
673 | PP | GRT-YE06-P0ZEN-155047 | 155047 | [Electrical General] Lightning Protection Layout for General Area | FA | 2017-03-23 | 2017-06-10 | 2017-07-25 | GRT-PP-IP-DT-170155 | FC | 0 | 2017-07-25 | N.A | FC | 0 | A | #VALUE! | #VALUE!
674 | PP | GRT-YL16-P0ZEN-155048 | 155048 | [Electrical General] Power and Control Cable Schedule | FI | 2017-07-14 | 2017-08-13 | 2017-10-23 | GRT-PP-IP-DT-170282 | FI | C | 2017-10-25 | 0025.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | C | I | #VALUE! | #VALUE!
675 | PP | GRT-YQ01-P0ZEN-155049 | 155049 | [Electrical General] Flood Light Wiring Layout for Outfall Area | FA | 2017-07-14 | 2017-08-13 | 2017-07-24 | GRT-PP-IP-DT-170151 | FC | 0 | 2017-07-25 | N.A | FC | 0 | A | #VALUE! | #VALUE!
676 | PP | GRT-YQ01-P0ZEN-155050 | 155050 | [Electrical General] Lighting and Receptacle Panel Schedule and Connection Diagram for Oufall Area | FA | 2017-06-22 | 2017-07-22 | 2017-07-24 | GRT-PP-IP-DT-170151 | FC | 0 | 2017-07-25 | N.A | FC | 0 | A | #VALUE! | #VALUE!
677 | PP | GRT-YR02-P0ZEN-155074 | 155074 | [Electrical General] Datasheet for Electrical Bulk Material | FA | 2017-03-11 | 2017-06-20 | 2017-10-31 | GRT-PP-IP-DT-170301 | FC(D) | C | 2017-11-02 | 0002.001/C.1.2.17.01/E04/PLNE/X/2017 | FA | C | A | #VALUE! | #VALUE!
678 | PP | GRT-YR02-P0ZEN-155073 | 155073 | [Electrical General] Datasheet for Cable Tray & Accessories | FA | 2017-03-11 | 2017-04-10 | 2017-05-26 | GRT-PP-IP-DT-170094 | FC | 0 | 2017-05-26 | N.A | FC | 0 | A | #VALUE! | #VALUE!
679 | PP | GRT-YR02-P0ZEN-155072 | 155072 | [Electrical General] Datasheet for Lighting Fixture & Accessories | FA | 2017-03-11 | 2017-04-10 | 2017-05-26 | GRT-PP-IP-DT-170094 | FC | 0 | 2017-05-26 | N.A | FC | 0 | A | #VALUE! | #VALUE!
680 | PP | GRT-YR02-P0ZEN-155071 | 155071 | [Electrical General] Datasheet for Busduct | FA | 2017-03-11 | 2017-04-10 | 2017-10-31 | GRT-PP-IP-DT-170293 | FC | 0 | 2017-10-31 | N.A | FC | 0 | A | #VALUE! | #VALUE!
681 | PP | GRT-YR02-P0ZEN-155070 | 155070 | [Electrical General] Datasheet for UPS, Battery & Battery Charger | FA | 2017-03-11 | 2017-04-10 | 2019-03-05 | GRT-PP-IP-DT-191041 | FC | 4 | 2019-03-13 | 019/061/GRT/UPR/2019 | FC | 4 | B | #VALUE! | #VALUE!
682 | PP | GRT-YR02-P0ZEN-155069 | 155069 | [Electrical General] Datasheet for Cable and Wire | FA | 2017-03-08 | 2017-04-07 | 2017-11-20 | GRT-PP-IP-DT-170329 | FC | 0 | 2017-11-21 | N.A | FC | 0 | A | #VALUE! | #VALUE!
683 | PP | GRT-YR02-P0ZEN-155068 | 155068 | [Electrical General] Datasheet for Distribution & Lighting Panel | FA | 2017-03-08 | 2017-04-07 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
684 | PP | GRT-YR02-P0ZEN-155067 | 155067 | [Electrical General] Datasheet for Low Voltage Switchgear and MCC | FA | 2017-03-07 | 2017-04-06 | 2017-08-21 | GRT-PP-IP-DT-170187 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
685 | PP | GRT-YR02-P0ZEN-155066 | 155066 | [Electrical General] Datasheet for Medium Voltage Switchgear and MCC | FA | 2017-03-07 | 2017-04-06 | 2017-08-21 | GRT-PP-IP-DT-170187 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
686 | PP | GRT-YR02-P0ZEN-155065 | 155065 | [Electrical General] Datasheet for Auxiliary & Service Transformer | FA | 2017-02-18 | 2017-03-20 | 2017-08-21 | GRT-PP-IP-DT-170187 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
687 | PP | GRT-YR02-P0ZEN-155064 | 155064 | [Electrical General] Datasheet for Main Transformer | FA | 2017-02-18 | 2017-03-20 | 2017-09-14 | GRT-PP-IP-DT-170226 | FC | 0 | 2017-09-14 | N.A | FC | 0 | A | #VALUE! | #VALUE!
688 | PP | GRT-YR02-P0ZEN-155063 | 155063 | [Electrical General] Datasheet for Emergency Diesel Generator | FA | 2017-03-07 | 2017-04-06 | 2017-05-10 | GRT-PP-IP-DT-170077 | FC | 0 | 2017-05-15 | N.A | FC | 0 | A | #VALUE! | #VALUE!
689 | PP | GRT-YR02-P0ZEN-155061 | 155061 | [Electrical General] Specification for Busduct | FA | 2017-03-11 | 2017-04-10 | 2017-05-30 | GRT-PP-IP-DT-170099 | FC | 0 | 2017-05-30 | N.A | FC | 0 | A | #VALUE! | #VALUE!
690 | PP | GRT-YR02-P0ZEN-155060 | 155060 | [Electrical General] Specification for UPS, Battery & Battery Charger | FA | 2017-03-11 | 2017-04-10 | 2017-05-09 | GRT-PP-IP-DT-170075 | FC | 0 | 2017-05-15 | N.A | FC | 0 | A | #VALUE! | #VALUE!
691 | PP | GRT-YR02-P0ZEN-155059 | 155059 | [Electrical General] Specification for Induction Motor | FA | 2017-03-02 | 2017-04-01 | 2017-05-30 | GRT-PP-IP-DT-170099 | FC | 0 | 2017-05-30 | N.A | FC | 0 | A | #VALUE! | #VALUE!
692 | PP | GRT-YR02-P0ZEN-155058 | 155058 | [Electrical General] Specification for Cable and Wire | FA | 2017-03-08 | 2017-04-07 | 2017-05-30 | GRT-PP-IP-DT-170099 | FC | 0 | 2017-05-30 | N.A | FC | 0 | A | #VALUE! | #VALUE!
693 | PP | GRT-YR02-P0ZEN-155057 | 155057 | [Electrical General] Specification for Distribution & Lighting Panel | FA | 2017-03-08 | 2017-04-07 | 2017-06-30 | GRT-PP-IP-DT-170102 | FC | 0 | 2017-06-05 | N.A | FC | 0 | A | #VALUE! | #VALUE!
694 | PP | GRT-YR02-P0ZEN-155056 | 155056 | [Electrical General] Specification for Low Voltage Switchgear and MCC | FA | 2017-03-07 | 2017-04-06 | 2017-05-09 | GRT-PP-IP-DT-170075 | FC | 0 | 2017-05-15 | N.A | FC | 0 | A | #VALUE! | #VALUE!
695 | PP | GRT-YR02-P0ZEN-155055 | 155055 | [Electrical General] Specification for Medium Voltage Switchgear and MCC | FA | 2017-03-07 | 2017-04-06 | 2017-08-21 | GRT-PP-IP-DT-170187 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
696 | PP | GRT-YR02-P0ZEN-155054 | 155054 | [Electrical General] Specification for Auxiliary & Service Transformer | FA | 2017-02-18 | 2017-03-20 | 2017-08-21 | GRT-PP-IP-DT-170187 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
697 | PP | GRT-YR02-P0ZEN-155053 | 155053 | [Electrical General] Specification for Main Transformer | FA | 2017-02-18 | 2017-03-20 | 2017-09-14 | GRT-PP-IP-DT-170226 | FC | 0 | 2017-09-14 | N.A | FC | 0 | A | #VALUE! | #VALUE!
698 | PP | GRT-YR02-P0ZEN-155052 | 155052 | [Electrical General] Specification for Emergency Diesel Generator | FA | 2017-03-07 | 2017-04-06 | 2017-05-10 | GRT-PP-IP-DT-170077 | FC | 0 | 2017-05-15 | N.A | FC | 0 | A | #VALUE! | #VALUE!
699 | PP | GRT-YR02-P0ZEN-155051 | 155051 | [Electrical General] General Specification for Electrical | FA | 2017-03-01 | 2017-03-31 | 2017-09-14 | GRT-PP-IP-DT-170226 | FC | 0 | 2017-09-14 | N.A | FC | 0 | A | #VALUE! | #VALUE!
700 | PP | GRT-YS02-P0ZEN-155075 | 155075 | [Electrical General] Connection Diagram For Power and Control Cable | FI | 2017-06-14 | 2017-07-14 | 2017-10-31 | GRT-PP-IP-DT-170301 | FI | B | 2017-11-02 | 0002.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | B | I | #VALUE! | #VALUE!
701 | PP | GRT-YU01-P0ZEN-155076 | 155076 | [Electrical General] Overall Single Line Diagram for 150 kv | FA | 2017-02-19 | 2017-03-21 | 2017-11-22 | GRT-PP-IP-DT-170334 | FC | 1 | 2017-11-24 | N.A | FC | 1 | A | #VALUE! | #VALUE!
702 | PP | GRT-YU01-P0ZEN-155077 | 155077 | [Electrical General] Single Line Diagram for MV System | FA | 2017-02-25 | 2017-03-27 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A | #VALUE! | #VALUE!
703 | PP | GRT-YU01-P0ZEN-155078 | 155078 | [Electrical General] Single Line Diagram for LV System | FA | 2017-02-25 | 2017-03-27 | 2017-11-20 | GRT-PP-IP-DT-170329 | FC | 1 | 2017-11-21 | N.A | FC | 1 | A | #VALUE! | #VALUE!
704 | PP | GRT-YU01-P0ZEN-155079 | 155079 | [Electrical General] Single Line Diagram for UPS & DC System | FA | 2017-02-28 | 2017-03-30 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
705 | PP | GRT-YU01-P0ZEN-155080 | 155080 | [Electrical General] Single Line Diagram for Protection & Metering System | FA | 2017-03-02 | 2017-04-01 | 2018-06-28 | GRT-PP-IP-DT-180654 | FC | 1 | 2017-07-13 | Comment Sheet IP | FC | 1 | A | #VALUE! | #VALUE!
706 | PP | GRT-XW03-P0ZEN-155081 | 155081 | [Electrical General] Electrical Load Data Calculation | FA | 2017-02-23 | 2017-03-25 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
707 | PP | GRT-XW03-P0ZEN-155082 | 155082 | [Electrical General] Voltage Drop and Power Flow Study | FA | 2017-03-14 | 2017-04-13 | 2017-09-18 | GRT-PP-IP-DT-170230 | FC | 0 | 2017-09-18 | N.A | FC | 0 | A | #VALUE! | #VALUE!
708 | PP | GRT-XW03-P0ZEN-155083 | 155083 | [Electrical General] Short Circuit Calculation | FA | 2017-03-14 | 2017-04-13 | 2017-09-18 | GRT-PP-IP-DT-170230 | FC | 0 | 2017-09-18 | N.A | FC | 0 | A | #VALUE! | #VALUE!
709 | PP | GRT-XW03-P0ZEN-155084 | 155084 | [Electrical General] Protective Relay Coordination Study for MV & LV Switcgear | FA | 2017-06-14 | 2017-07-14 | 2017-10-18 | GRT-PP-IP-DT-170274 | FC(D) | C | 2017-10-23 | 0023.001/C.1.2.15.01/E04/PLNE/X/2017 | FA | C | A | #VALUE! | #VALUE!
710 | PP | GRT-XW03-P0ZEN-155085 | 155085 | [Electrical General] Emergency Diesel Capacity Calculation | FA | 2017-03-15 | 2017-04-14 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A | #VALUE! | #VALUE!
711 | PP | GRT-XW03-P0ZEN-155086 | 155086 | [Electrical General] Transformer Sizing Calculation | FA | 2017-02-18 | 2017-03-20 | 2017-09-18 | GRT-PP-IP-DT-170230 | FC | 0 | 2017-09-18 | N.A | FC | 0 | A | #VALUE! | #VALUE!
712 | PP | GRT-XW03-P0ZEN-155087 | 155087 | [Electrical General] UPS, Battery & Battery Charger Capacity | FA | 2017-03-15 | 2017-04-14 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
713 | PP | GRT-XW03-P0ZEN-155088 | 155088 | [Electrical General] Lighting Illumination Level Calculation | FA | 2017-06-14 | 2017-07-14 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
714 | PP | GRT-XW03-P0ZEN-155089 | 155089 | [Electrical General] Grounding System Calculation | FA | 2017-03-01 | 2017-03-31 | 2017-04-18 | GRT-PP-IP-DT-170048 | FC | 0 | 2017-05-04 | N.A | FA | 0 | A | #VALUE! | #VALUE!
715 | PP | GRT-XW03-P0ZEN-155090 | 155090 | [Electrical General] Lightning Protection System Calculation | FA | 2017-03-16 | 2017-04-15 | 2017-08-23 | GRT-PP-IP-DT-170193 | FC | 0 | 2017-08-23 | N.A | FC | 0 | A | #VALUE! | #VALUE!
716 | PP | GRT-XW03-P0ZEN-155091 | 155091 | [Electrical General] Cable Size Calculation | FA | 2017-03-30 | 2017-04-29 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A | #VALUE! | #VALUE!
717 | PP | GRT-XW03-P0ZEN-155092 | 155092 | [Electrical General] MOTOR STARTING ANALYSIS | FA | 2017-04-01 | 2017-05-01 | 2017-09-22 | GRT-PP-IP-DT-170236 | FC | 0 | 2017-09-25 | N.A | FC | 0 | A | #VALUE! | #VALUE!
718 | PP | GRT-XW03-P0ZEN-155095 | 165095 | [Electrical General] Busduct Sizing Calculation | FA | 2017-03-16 | 2017-04-15 | 2017-05-30 | GRT-PP-IP-DT-170099 | FC | 0 | 2017-05-30 | N.A | FC | 0 | A | #VALUE! | #VALUE!
719 | PP | GRT-XW03-P0ZEN-155096 | 155096 | [Electrical General] Electrical Load List | FA | 2017-02-20 | 2017-03-22 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
720 | PP | GRT-CV03-P0ZEN-165097 | 165097 | [Instrument General] Data Sheet for CCTV Camera | FA | 2017-06-14 | 2017-07-14 | 2019-11-28 | GRT-PP-IP-DT-191509 | FC | 3 | 2019-11-29 | MOM MINI DRM 28-29NOV19 |  | 3 | A | #VALUE! | #VALUE!
721 | PP | GRT-CV03-P0ZEN-165098 | 165098 | [Instrument General] Data Sheet for Telephone System | FA | 2017-06-14 | 2017-07-14 | 2018-01-26 | GRT-PP-IP-DT-180397 | FC | 0 | 2017-09-18 | N.A | FC | 0 | A | #VALUE! | #VALUE!
722 | PP | GRT-CV03-P0ZEN-165099 | 165099 | [Instrument General] Data Sheet for Paging System | FA | 2017-07-19 | 2017-08-18 | 2017-08-08 | GRT-PP-IP-DT-170175 | FC | 0 | 2017-08-08 | N.A | FC | 0 | A | #VALUE! | #VALUE!
723 | PP | GRT-YD00-P0ZEN-165100 | 165100 | [Instrument General] Instrument Layout Keyplan | FA | 2017-09-14 | 2017-06-20 | 2017-09-14 | GRT-PP-IP-DT-170226 | FC | 0 | 2017-09-14 | N.A | FC | 0 | A | #VALUE! | #VALUE!
724 | PP | GRT-YD00-P0ZEN-165101 | 165101 | [Instrument General] Instrument Main Cable Way Layout | FA | 2017-07-19 | 2017-08-18 | 2017-10-04 | GRT-PP-IP-DT-170249 | FC | 0 | 2017-10-04 | N.A | FC | 0 | A | #VALUE! | #VALUE!
725 | PP | GRT-YD00-P0ZEN-165102 | 165102 | [Instrument General] CCTV Location Plan Layout | FA | 2017-09-14 | 2017-07-30 | 2018-02-21 | GRT-PP-IP-DT-180425 | FC | 3 | 2018-02-21 | stempel approved | FC | 3 | A | #VALUE! | #VALUE!
726 | PP | GRT-YD00-P0ZEN-165103 | 165103 | [Instrument General] CCTV Cable Wiring Layout | FA | 2017-10-05 | 2017-07-30 | 2018-02-21 | GRT-PP-IP-DT-180425 | FC | 1 | 2018-02-21 | stempel approved | FC | 1 | A | #VALUE! | #VALUE!
727 | PP | GRT-YD00-P0ZEN-165104 | 165104 | [Instrument General] Telephone Location Plan Layout | FA | 2017-08-08 | 2017-06-20 | 2017-08-08 | GRT-PP-IP-DT-170175 | FC | 0 | 2017-08-08 | N.A | FC | 0 | A | #VALUE! | #VALUE!
728 | PP | GRT-YD00-P0ZEN-165105 | 165105 | [Instrument General] Telephone Cable Wiring Layout | FA | 2017-06-14 | 2017-07-30 | 2017-09-20 | GRT-PP-IP-DT-170232 | FC | 0 | 2017-09-20 | N.A | FC | 0 | A | #VALUE! | #VALUE!
729 | PP | GRT-YD00-P0ZEN-165106 | 165106 | [Instrument General] Paging Location Plan Layout | FA | 2017-06-23 | 2017-07-23 | 2017-09-14 | GRT-PP-IP-DT-170226 | FC | 0 | 2017-09-14 | N.A | FC | 0 | A | #VALUE! | #VALUE!
730 | PP | GRT-YD00-P0ZEN-165107 | 165107 | [Instrument General] Paging Cable Wiring Layout | FA | 2017-07-19 | 2017-08-18 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A | #VALUE! | #VALUE!
731 | PP | GRT-YD00-P0ZEN-165108 | 165108 | [Instrument General] Instrument Grounding Layout | FA | 2017-06-14 | 2017-07-14 | 2017-10-24 | GRT-PP-IP-DT-170286 | FC | 0 | 2017-10-25 | N.A | FC | 0 | A | #VALUE! | #VALUE!
732 | PP | GRT-YD00-P0ZEN-165109 | 165109 | [Instrument General] Instrument Panel Arrangement for BOP | FA | 2017-07-19 | 2017-08-18 | 2019-05-23 | DRM_22-24MAY2019 (DCR 0041) | FC | 2DCR1 | 2019-05-23 | 031/061/GRT/UPR/2018 |  | 2DCR1 | B | #VALUE! | #VALUE!
733 | PP | GRT-YD00-P0ZEN-165110 | 165110 | [Instrument General] Instrument Panel Base Frame & Hole Opening | FA | 2017-07-19 | 2017-08-18 | 2018-01-26 | GRT-PP-IP-DT-180397 | FC | 0 | 2017-08-01 | N.A | FC | 0 | A | #VALUE! | #VALUE!
734 | PP | GRT-YD00-P0ZEN-165111 | 165111 | [Instrument General] Instrument Wiring Layout Inside Control Room | FA | 2017-07-19 | 2017-08-18 | 2018-01-26 | GRT-PP-IC-FCR-00028 | FC | 1FCR3 |  | 0185/SMGRT.IP-TEI/VII/2019 |  | 1FCR3 | A | #VALUE! | #VALUE!
735 | PP | GRT-YF00-P0ZEN-165112 | 165112 | [Instrument General] Instrument Control Logic for Sea Water Intake System | FA | 2017-07-07 | 2017-08-06 | 2018-11-09 | GRT-PP-IP-DT-180849 | FC | 1 | 2018-11-14 | Comment Sheet IP | FC | 1 | A | #VALUE! | #VALUE!
736 | PP | GRT-YL01-P0ZEN-165114 | 165114 | [Instrument General] Instrument Index for BOP | FA | 2017-03-17 | 2017-04-16 | 2017-09-18 | GRT-PP-IP-DT-170230 | FC | 0 | 2017-09-18 | N.A | FC | 0 | A | #VALUE! | #VALUE!
737 | PP | GRT-YL15-P0ZEN-165115 | 165115 | [Instrument General] Instrument Cable Drum Schedule for BOP | FA | 2017-04-29 | 2017-05-29 | 2017-11-03 | GRT-PP-IP-DT-170305 | FC(D) | B | 2017-11-15 | 0015.001/C.1.2.17.01/E04/PLNE/XI/2017 | FA | B | B | #VALUE! | #VALUE!
738 | PP | GRT-YK00-P0ZEN-165116 | 165116 | [Instrument General] Instrument Typical Drawing for Installation | FA | 2017-06-14 | 2017-07-14 | 2017-12-12 | GRT-PP-IP-DT-170355 | FC | 0 | 2017-12-13 | N.A | FC | 0 | A | #VALUE! | #VALUE!
739 | PP | GRT-YK00-P0ZEN-165117 | 165117 | [Instrument General] CCTV Typical Drawing for Installation | FA | 2017-04-22 | 2017-05-22 | 2017-09-14 | GRT-PP-IP-DT-170226 | FC | 0 | 2017-09-14 | N.A | FC | 0 | A | #VALUE! | #VALUE!
740 | PP | GRT-YK00-P0ZEN-165118 | 165118 | [Instrument General] Telephone Typical Drawing for Installation | FA | 2017-04-25 | 2017-05-25 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 0 | 2017-10-17 | N.A | FC | 0 | A | #VALUE! | #VALUE!
741 | PP | GRT-YK00-P0ZEN-165119 | 165119 | [Instrument General] Paging Typical Drawing for Installation | FA | 2017-04-26 | 2017-05-26 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 0 | 2017-10-17 | N.A | FC | 0 | A | #VALUE! | #VALUE!
742 | PP | GRT-YQ07-P0ZEN-165120 | 165120 | [Instrument General] General Specification for Telephone System | FA | 2017-04-17 | 2017-05-17 | 2017-09-25 | GRT-PP-IP-DT-170239 | FC | 0 | 2017-09-25 | N.A | FC | 0 | A | #VALUE! | #VALUE!
743 | PP | GRT-YR04-P0ZEN-165121 | 165121 | [Instrument General] Instrument General Symbol & Index | FA | 2017-02-18 | 2017-03-20 | 2017-02-16 | GRT-PP-IP-DT-170013 | FI | A | 2017-03-27 | 0027.001/ADDONGRT150MW/E04/PLNE/III/2017 | FA | A | I | #VALUE! | #VALUE!
744 | PP | GRT-YR05-P0ZEN-165123 | 165123 | [Instrument General] General Specification for CCTV | FA | 2017-04-16 | 2017-05-16 | 2017-09-25 | GRT-PP-IP-DT-170239 | FC | 0 | 2017-09-25 | N.A | FC | 0 | A | #VALUE! | #VALUE!
745 | PP | GRT-YS01-P0ZEN-165124 | 165124 | [Instrument General] CCTV Block Diagram | FA | 2017-04-22 | 2017-05-22 | 2018-02-21 | GRT-PP-IP-DT-180425 | FC | 3 | 2018-02-21 | stempel approved | FC | 3 | A | #VALUE! | #VALUE!
746 | PP | GRT-YS01-P0ZEN-165125 | 165125 | [Instrument General] Telephone System Block Diagram | FA | 2017-04-25 | 2017-05-25 | 2017-08-08 | GRT-PP-IP-DT-170175 | FC | 0 | 2017-08-08 | N.A | FC | 0 | A | #VALUE! | #VALUE!
747 | PP | GRT-YS01-P0ZEN-165126 | 165126 | [Instrument General] Paging System Block Diagram | FA | 2017-06-14 | 2017-07-14 | 2017-09-18 | GRT-PP-IP-DT-170230 | FC | 0 | 2017-09-18 | N.A | FC | 0 | A | #VALUE! | #VALUE!
748 | PP | GRT-CA07-P0ZEN-175127 | 175127 | [Civil General] Design Specification for Civil and Structural | FA | 2017-02-23 | 2017-03-25 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A | #VALUE! | #VALUE!
749 | PP | GRT-YT01-P0PAC-115136 | 115136 | Sea Water Intake Pump Process Data Sheet | FA | 2017-02-03 | 2017-03-05 | 2017-10-31 | GRT-PP-IP-DT-170293 | FC | 0 | 2017-10-31 | N.A | FC | 0 | A | #VALUE! | #VALUE!
750 | PP | GRT-YT01-P0PAC-115137 | 115137 | [Circulating Water Pump] Sea Water Intake Basin Process Data Sheet | FA | 2017-02-10 | 2017-03-12 | 2017-09-25 | GRT-PP-IP-DT-170239 | FC | 0 | 2017-09-25 | N.A | FC | 0 | A | #VALUE! | #VALUE!
751 | PP | GRT-YD00-P0PAC-125139 | 125139 | [Circulating Water Pump] GA Drawing Stop Log Screen | FA | 2017-07-15 | 2017-08-14 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 1 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 1 | A | #VALUE! | #VALUE!
752 | PP | GRT-YD00-P0PAC-125140 | 125140 | [Circulating Water Pump] GA Drawing Bar Screen | FA | 2017-07-15 | 2017-08-14 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 1 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 1 | A | #VALUE! | #VALUE!
753 | PP | GRT-YD00-P0PAC-125141 | 125141 | [Circulating Water Pump] GA Drawing Travelling Screen | FA | 2017-07-15 | 2017-08-14 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 1 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 1 | A | #VALUE! | #VALUE!
754 | PP | GRT-YT01-P0PAC-125142 | 125142 | [Circulating Water Pump] Mech. Data Sheet for CWP Pump | FA | 2017-02-11 | 2017-03-13 | 2017-05-09 | GRT-PP-IP-DT-170075 | FC | 0 | 2017-05-15 | N.A | FC | 0 | A | #VALUE! | #VALUE!
755 | PP | GRT-CC00-P0PAC-145145 | 145145 | [Circulating Water Pump] Piping Layout Drawing for Sea Water Intake System | FA | 2017-02-03 | 2017-03-05 | 2017-09-07 | GRT-PP-IP-DT-170212 | FC | 0 | 2017-09-07 | N.A | FC | 0 | A | #VALUE! | #VALUE!
756 | PP | GRT-CC00-P0PAC-145146 | 145146 | [Circulating Water Pump] Detail & Section Drawing for Sea Water Intake System | FA | 2017-02-03 | 2017-03-05 | 2017-09-07 | GRT-PP-IP-DT-170212 | FC | 0 | 2017-09-07 | N.A | FC | 0 | A | #VALUE! | #VALUE!
757 | PP | GRT-XW03-P0PAC-155147 | 155147 | [Circulating Water Pump] Electrical Load Data Calculation for Sea Water Intake | FA | 2017-02-03 | 2017-03-05 | 2017-08-23 | GRT-PP-IP-DT-170193 | FC | 0 | 2017-08-23 | N.A | FC | 0 | A | #VALUE! | #VALUE!
758 | PP | GRT-XW03-P0PAC-155148 | 155148 | [Circulating Water Pump] Grounding System Calculation for Sea Water Intake | FA | 2017-02-03 | 2017-03-05 | 2017-08-23 | GRT-PP-IP-DT-170193 | FC | 0 | 2017-08-23 | N.A | FC | 0 | A | #VALUE! | #VALUE!
759 | PP | GRT-XW03-P0PAC-155149 | 155149 | [Circulating Water Pump] Cable Size Calculation for Sea Water Intake | FA | 2017-02-03 | 2017-03-05 | 2017-08-23 | GRT-PP-IP-DT-170193 | FC | 0 | 2017-08-23 | N.A | FC | 0 | A | #VALUE! | #VALUE!
760 | PP | GRT-XW03-P0PAC-155001 | 155001 | [Circulating Water Pump] Lighting Illumination Level Calculation for Sea Water Intake | FA | 2017-02-03 | 2017-03-05 | 2017-08-23 | GRT-PP-IP-DT-170193 | FC | 0 | 2017-08-23 | N.A | FC | 0 | A | #VALUE! | #VALUE!
761 | PP | GRT-YD16-P0PAC-155151 | 155151 | [Circulating Water Pump] Cable Tray and Power Wiring Layout | FA | 2017-02-03 | 2017-03-05 | 2017-08-23 | GRT-PP-IP-DT-170193 | FC | 0 | 2017-08-23 | N.A | FC | 0 | A | #VALUE! | #VALUE!
762 | PP | GRT-YE03-P0PAC-155152 | 155152 | [Circulating Water Pump] Grounding and Lightning Protection Layout | FA | 2017-02-03 | 2017-03-05 | 2017-08-23 | GRT-PP-IP-DT-170193 | FC | 0 | 2017-08-23 | N.A | FC | 0 | A | #VALUE! | #VALUE!
763 | PP | GRT-YQ01-P0PAC-155153 | 155153 | [Circulating Water Pump] Lighting and Receptacle Wiring Layout | FA | 2017-02-03 | 2017-03-05 | 2017-08-23 | GRT-PP-IP-DT-170193 | FC | 0 | 2017-08-23 | N.A | FC | 0 | A | #VALUE! | #VALUE!
764 | PP | GRT-YQ01-P0PAC-155154 | 155154 | [Circulating Water Pump] Lighting and Receptacle Connection Diagram | FA | 2017-02-03 | 2017-03-05 | 2017-08-23 | GRT-PP-IP-DT-170193 | FC | 0 | 2017-08-23 | N.A | FC | 0 | A | #VALUE! | #VALUE!
765 | PP | GRT-CV03-P0PAC-165155 | 165155 | [Circulating Water Pump] Instrument Data Sheet for Circulating Water Pump | FA | 2017-03-11 | 2017-04-10 | 2017-07-24 | GRT-PP-IP-DT-170151 | FC | 0 | 2017-07-25 | N.A | FC | 0 | A | #VALUE! | #VALUE!
766 | PP | GRT-YD00-P0PAC-165156 | 165156 | [Circulating Water Pump] Instrument Main Cable & JB Layout | FA | 2017-03-11 | 2017-04-10 | 2017-07-17 | GRT-PP-IP-DT-170140 | FC | 0 | 2017-07-17 | N.A | FC | 0 | A | #VALUE! | #VALUE!
767 | PP | GRT-YD00-P0PAC-165157 | 165157 | [Circulating Water Pump] Instrument Location Plan Layout | FA | 2017-03-11 | 2017-04-10 | 2017-07-17 | GRT-PP-IP-DT-170140 | FC | 0 | 2017-07-17 | N.A | FC | 0 | A | #VALUE! | #VALUE!
768 | PP | GRT-YD00-P0PAC-165158 | 165158 | [Circulating Water Pump] Instrument Cable Wiring Layout | FA | 2017-03-11 | 2017-04-10 | 2017-07-17 | GRT-PP-IP-DT-170140 | FC | 0 | 2017-07-17 | N.A | FC | 0 | A | #VALUE! | #VALUE!
769 | PP | GRT-YL01-P0PAC-165160 | 165160 | [Circulating Water Pump] I/O List | FA | 2017-03-11 | 2017-04-10 | 2017-11-13 | GRT-PP-IP-DT-170314 | FC | 0 | 2017-11-13 | N.A | FC | 0 | A | #VALUE! | #VALUE!
770 | PP | GRT-YL15-P0PAC-165161 | 165161 | [Circulating Water Pump] Instrument Cable Schedule | FI | 2017-03-11 | 2017-04-10 | 2019-05-26 | GRT-PP-IP-DT-191210 | FC | 0DCR1 |  | 0029.001/C.I.2.17.01/E04/PLNE/V/2019 |  | 0DCR1 | A | #VALUE! | #VALUE!
771 | PP | GRT-YS02-P0PAC-165162 | 165162 | [Circulating Water Pump] Instrument Termination Diagram for Circulating Water Pump | FA | 2017-03-11 | 2017-04-10 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A | #VALUE! | #VALUE!
772 | PP | GRT-CC03-P0PAC-175164 | 175164 | [Circulating Water Pump] Circulating Water Pump Framing Plan | FA | 2017-02-14 | 2017-03-16 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 2 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 2 | A | #VALUE! | #VALUE!
773 | PP | GRT-CC03-P0PAC-175165 | 175165 | [Circulating Water Pump] Circulating Water Pump Section, Slab Schedule and Wall Schedule | FA | 2017-02-14 | 2017-03-16 | 2019-11-29 | MINI DRM 28-29NOV19 | FC | 2 | 2019-11-29 | MOM MINI DRM 28-29NOV19 |  | 2 | A | #VALUE! | #VALUE!
774 | PP | GRT-CC03-P0PAC-175166 | 175166 | [Circulating Water Pump] Circulating Water Pump Sections | FA | 2017-02-14 | 2017-03-16 | 2017-08-22 | GRT-PP-IP-DT-170190 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
775 | PP | GRT-CC03-P0PAC-175167 | 175167 | [Circulating Water Pump] Circulating Water Pump Detail 1 & 2 | FA | 2017-02-14 | 2017-03-16 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A | #VALUE! | #VALUE!
776 | PP | GRT-CC03-P0PAC-175168 | 175168 | [Circulating Water Pump] Circulating Water Pump Detail 3 | FA | 2017-02-14 | 2017-03-16 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A | #VALUE! | #VALUE!
777 | PP | GRT-CC03-P0PAC-175169 | 175169 | [Circulating Water Pump] Circulating Water Pump Detail 4,5 and Suction Chamber | FA | 2017-02-14 | 2017-03-16 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A | #VALUE! | #VALUE!
778 | PP | GRT-CC03-P0PAC-175170(1OF7) | 175170 | [Circulating Water Pump] Circulating Water Pump Stop Log Detail and Section | FA | 2017-02-14 | 2017-03-16 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A | #VALUE! | #VALUE!
779 | PP | GRT-CC03-P0PAC-175170(2OF7) | 175170 | [Circulating Water Pump] Circulating Water Pump Gantry Crane and Traveling Screen Detail | FA | 2017-02-14 | 2017-03-16 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A | #VALUE! | #VALUE!
780 | PP | GRT-CC03-P0PAC-175170(3OF7) | 175170 | [Circulating Water Pump] Circulating Water Pump Bar Screen and Mechanical Rake/Car Detail | FA | 2017-02-14 | 2017-03-16 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A | #VALUE! | #VALUE!
781 | PP | GRT-CC03-P0PAC-175170(4OF7) | 175170 | [Circulating Water Pump] Circulating Water Pump Screen Wash Pumps and Sea Water Feed Pumps Detail | FA | 2017-02-14 | 2017-03-16 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A | #VALUE! | #VALUE!
782 | PP | GRT-CC03-P0PAC-175170(5OF7) | 175170 | [Circulating Water Pump] Circulating Water Pump CWP Pedestal Detail | FA | 2017-02-14 | 2017-03-16 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A | #VALUE! | #VALUE!
783 | PP | GRT-CC03-P0PAC-175170(6OF7) | 175170 | [Circulating Water Pump] Circulating Water Pump Gantry Crane Rail-2 Detail | FA | 2017-02-14 | 2017-03-16 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A | #VALUE! | #VALUE!
784 | PP | GRT-CC03-P0PAC-175170(7OF7) | 175170 | [Circulating Water Pump] Circulating Water Pump Pipe Header Pedestal Detail | FA | 2017-02-14 | 2017-03-16 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A | #VALUE! | #VALUE!
785 | PP | GRT-CC03-P0PAC-175170 | 175170 | [Circulating Water Pump] Circulating Water Pump Pipe Header Pedestal Detail | FA | 2017-02-14 | 2017-03-16 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A | #VALUE! | #VALUE!
786 | PP | GRT-CC07-P0PAC-175174 | 175174 | [Circulating Water Pump] Calculation Sheet for Cooling Water Intake Basin | FA | 2017-02-14 | 2017-03-16 | 2017-10-05 | GRT-PP-IP-DT-170255 | FC | 0 | 2017-10-05 | N.A | FC | 0 | A | #VALUE! | #VALUE!
787 | PP | GRT-CC00-P0PAD-145176 | 145176 | [Circulating Water Pump Outfall] Piping Layout Drawing for Sea Water Outfall | FA | 2017-07-15 | 2017-08-14 | 2017-10-12 | GRT-PP-IP-DT-170267 | FC | 0 | 2017-10-12 | N.A | FC | 0 | A | #VALUE! | #VALUE!
788 | PP | GRT-CC00-P0PAD-145177 | 145177 | [Circulating Water Pump Outfall] Detail & Section Drawing for Sea Water Outfall | FA | 2017-07-07 | 2017-08-06 | 2017-10-12 | GRT-PP-IP-DT-170267 | FC | 0 | 2017-10-12 | N.A | FC | 0 | A | #VALUE! | #VALUE!
789 | PP | GRT-CC07-P0PAD-175178(1OF3) | 175178 | [Circulating Water Pump Outfall] Circulating Water Pump Outfall Plan | FA | 2017-02-11 | 2017-03-13 | 2017-09-13 | GRT-PP-IP-DT-170218 | FC | 1 | 2017-09-18 | N.A | FC | 1 | A | #VALUE! | #VALUE!
790 | PP | GRT-CC07-P0PAD-175178(2OF3) | 175178 | [Circulating Water Pump Outfall] Circulating Water Pump Outfall Section Slab Schedule and Wall Schedule | FA | 2017-02-11 | 2017-03-13 | 2017-09-13 | GRT-PP-IP-DT-170218 | FC | 1 | 2017-09-18 | N.A | FC | 1 | A | #VALUE! | #VALUE!
791 | PP | GRT-CC07-P0PAD-175178(3OF3) | 175178 | [Circulating Water Pump Outfall] Circulating Water Pump Outfall Section and Detail | FA | 2017-02-11 | 2017-03-13 | 2017-09-13 | GRT-PP-IP-DT-170218 | FC | 1 | 2017-09-18 | N.A | FC | 1 | A | #VALUE! | #VALUE!
792 | PP | GRT-CC07-P0PAD-175179(1OF2) | 175179 | [Circulating Water Pump Outfall] Circulating Water Pump Outfall Details | FA | 2017-02-11 | 2017-03-13 | 2017-09-13 | GRT-PP-IP-DT-170218 | FC | 1 | 2017-09-18 | N.A | FC | 1 | A | #VALUE! | #VALUE!
793 | PP | GRT-CC07-P0PAD-175179(2OF2) | 175179 | [Circulating Water Pump Outfall] Circulating Water Pump Outfall Details | FA | 2017-02-11 | 2017-03-13 | 2017-09-13 | GRT-PP-IP-DT-170218 | FC | 1 | 2017-09-18 | N.A | FC | 1 | A | #VALUE! | #VALUE!
794 | PP | GRT-CC07-P0PAD-175180 | 175180 | [Circulating Water Pump Outfall] Calculation Sheet for Circulating Water Pump Outfall | FA | 2017-02-11 | 2017-03-13 | 2017-09-13 | GRT-PP-IP-DT-170218 | FC | 0 | 2017-09-18 | N.A | FC | 0 | A | #VALUE! | #VALUE!
795 | PP | GRT-XG02-P0UGX-115183 | 115183 | [Chlorination System] Piping and instrument diagram (PID) Chlorination System | FA | 2017-06-07 | 2017-07-07 | 2017-12-20 | GRT-PP-IP-DT-170367 | FC | 0 | 2017-12-21 | N.A | FC | 0 | A | #VALUE! | #VALUE!
796 | PP | GRT-XW01-P0UGX-115184 | 115184 | [Chlorination System] Process specification for Chlorination system | FA | 2017-06-07 | 2017-07-07 | 2017-10-31 | GRT-PP-IP-DT-170301 | FC(D) | C | 2017-11-15 | 0015.001/C.1.2.17.01/E04/PLNE/XI/2017 | FA | C | B | #VALUE! | #VALUE!
797 | PP | GRT-CA05-P0UGX-125185 | 125185 | [Chlorination System] Chlorination Plant Building Cold Water Layout & Isometric | FA | 2017-03-11 | 2017-04-10 | 2017-04-07 | GRT-PP-PLN-E-170041 | FC(D) | A | 2017-04-21 | 0021.001/C.1.2.17.01/E04/PLNE/IV/2017 | FA | A | B | #VALUE! | #VALUE!
798 | PP | GRT-CA05-P0UGX-125186 | 125186 | [Chlorination System] Chlorination Plant Building Grey, Black Water Layout & Isometric | FA | 2017-03-11 | 2017-04-10 | 2017-04-07 | GRT-PP-PLN-E-170041 | FC(D) | A | 2017-04-21 | 0021.001/C.1.2.17.01/E04/PLNE/IV/2017 | FA | A | B | #VALUE! | #VALUE!
799 | PP | GRT-HM01-P0UGX-125187 | 125187 | [Chlorination System] Chlorination Plant Building HVAC Flow Schematic Diagram | FA | 2017-03-11 | 2017-04-10 | 2017-08-07 | GRT-PP-IP-DT-170172 | FC | 0 | 2017-08-07 | N.A | FC | 0 | A | #VALUE! | #VALUE!
800 | PP | GRT-HM01-P0UGX-125188 | 125188 | [Chlorination System] Chlorination Plant Building HVAC Ducting Layout | FA | 2017-03-11 | 2017-04-10 | 2017-10-04 | GRT-PP-IP-DT-170249 | FC | 0 | 2017-10-04 | N.A | FC | 0 | A | #VALUE! | #VALUE!
801 | PP | GRT-HM01-P0UGX-125189 | 125189 | [Chlorination System] Chlorination Plant Building HVAC Elevation, Equipment Layout | FA | 2017-03-11 | 2017-04-10 | 2017-10-10 | GRT-PP-IP-DT-170263 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A | #VALUE! | #VALUE!
802 | PP | GRT-HM01-P0UGX-125190 | 125189 | [Chlorination System] Chlorination Plant Building HVAC, Elevation, Section & Detail | FA | 2017-03-11 | 2017-04-10 | 2017-10-10 | GRT-PP-IP-DT-170263 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A | #VALUE! | #VALUE!
803 | PP | GRT-HM05-P0UGX-125191 | 125191 | [Chlorination System] HVAC Calculation for Chlorination Plant Building | FA | 2017-07-07 | 2017-08-06 | 2017-09-06 | GRT-PP-IP-DT-170209 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A | #VALUE! | #VALUE!
804 | PP | GRT-CC00-P0UGX-145192 | 145192 | [Chlorination System] Piping Layout Drawing for Chlorination | FA | 2017-07-15 | 2017-08-14 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A | #VALUE! | #VALUE!
805 | PP | GRT-YD16-P0UGX-155193 | 155193 | [Chlorination System] Cable Tray and Power Wiring Layout | FA | 2017-03-11 | 2017-04-10 | 2017-12-28 | GRT-PP-IP-DT-170376 | FC | 1 | 2017-12-29 | N.A | FC | 1 | A | #VALUE! | #VALUE!
806 | PP | GRT-YE07-P0UGX-155194 | 155194 | [Chlorination System] Grounding Wiring Layout | FA | 2017-03-11 | 2017-04-10 | 2017-09-22 | GRT-PP-IP-DT-170236 | FC | 0 | 2017-09-25 | N.A | FC | 0 | A | #VALUE! | #VALUE!
807 | PP | GRT-YE07-P0UGX-155195 | 155195 | [Chlorination System] Lightning Protection Layout | FA | 2017-03-11 | 2017-04-10 | 2019-09-19 | GRT-PP-IP-DT-191389 (DCR 0040) | FC | 0DCR2 | 2019-09-26 | APPROVED ON SITE (PLN E) |  | 0DCR2 | A | #VALUE! | #VALUE!
808 | PP | GRT-YQ01-P0UGX-155196 | 155196 | [Chlorination System] Lighting and Receptale Wiring Layout | FA | 2017-03-11 | 2017-04-10 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
809 | PP | GRT-YQ01-P0UGX-155197 | 155197 | [Chlorination System] Lighting and Receptacle Panel Schedule and Connection Diagram | FA | 2017-03-11 | 2017-04-10 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
810 | PP | GRT-CA00-P0UGX-175206 | 175206 | [Chlorination System] Chlorination System Architectural Plan, View, Section & Finishing Schedule | FA | 2017-03-04 | 2017-04-03 | 2017-08-24 | GRT-PP-IP-DT-170198 | FC | 0 | 2017-08-25 | N.A | FC | 0 | A | #VALUE! | #VALUE!
811 | PP | GRT-CA00-P0UGX-175207 | 175207 | [Chlorination System] Section, Detail & Finishing Schedule | FA | 2017-06-23 | 2017-07-23 | 2017-08-24 | GRT-PP-IP-DT-170198 | FC | 0 | 2017-08-25 | N.A | FC | 0 | A | #VALUE! | #VALUE!
812 | PP | GRT-CA01-P0UGX-175208 | 175208 | [Chlorination System] Foundation Plan | FA | 2017-06-23 | 2017-07-23 | 2017-08-24 | GRT-PP-IP-DT-170198 | FC | 0 | 2017-08-25 | N.A | FC | 0 | A | #VALUE! | #VALUE!
813 | PP | GRT-CA01-P0UGX-175209 | 175209 | [Chlorination System] Foundation Detail | FA | 2017-06-23 | 2017-07-23 | 2017-08-24 | GRT-PP-IP-DT-170198 | FC | 0 | 2017-08-25 | N.A | FC | 0 | A | #VALUE! | #VALUE!
814 | PP | GRT-CA01-P0UGX-175210 | 175210 | [Chlorination System] Steel Structure Framing Plan | FA | 2017-06-23 | 2017-07-23 | 2017-08-24 | GRT-PP-IP-DT-170198 | FC | 0 | 2017-08-25 | N.A | FC | 0 | A | #VALUE! | #VALUE!
815 | PP | GRT-CA01-P0UGX-175211 | 175211 | [Chlorination System] Steel Structure Framing Elevation and Detail | FA | 2017-06-23 | 2017-07-23 | 2017-08-24 | GRT-PP-IP-DT-170198 | FC | 0 | 2017-08-25 | N.A | FC | 0 | A | #VALUE! | #VALUE!
816 | PP | GRT-CA06-P0UGX-175212 | 175212 | [Chlorination System] Calculation Sheet for Chlorination System Building | FA | 2017-06-23 | 2017-07-23 | 2017-08-24 | GRT-PP-IP-DT-170198 | FC | 0 | 2017-08-25 | N.A | FC | 0 | A | #VALUE! | #VALUE!
817 | PP | GRT-YE00-P1UHA-155213 | 155213 | [HRSG] Cable Tray and Power Wiring Layout | FA | 2017-06-15 | 2017-07-15 | 2017-09-14 | GRT-PP-IP-DT-170226 | FC | 0 | 2017-09-14 | N.A | FC | 0 | A | #VALUE! | #VALUE!
818 | PP | GRT-YE00-P1UHA-155214 | 155214 | [HRSG] Clock System Wiring Layout | FA | 2017-10-31 | 2017-06-20 | 2017-10-31 | GRT-PP-IP-DT-170293 | FC | 0 | 2017-10-31 | N.A | FC | 0 | A | #VALUE! | #VALUE!
819 | PP | GRT-YE06-P1UHA-155215 | 155215 | [HRSG] Grounding Wiring Layout | FA | 2017-06-06 | 2017-06-20 | 2017-06-06 | GRT-PP-IP-DT-170110 | FC | 0 | 2017-06-06 | N.A | FC | 0 | A | #VALUE! | #VALUE!
820 | PP | GRT-YE06-P1UHA-155216 | 155216 | [HRSG] Lightning Protection Layout | FA | 2017-06-15 | 2017-07-15 | 2017-11-22 | GRT-PP-IP-DT-170334 | FC | 0 | 2017-11-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
821 | PP | GRT-YQ01-P1UHA-155217 | 155217 | [HRSG] Lighting and Receptale Wiring Layout | FA | 2017-06-15 | 2017-07-15 | 2017-09-13 | GRT-PP-IP-DT-170218 | FC | 0 | 2017-09-13 | N.A | FC | 0 | A | #VALUE! | #VALUE!
822 | PP | GRT-YQ01-P1UHA-155218 | 155218 | [HRSG] Lighting and Receptacle Panel Schedule and Connection Diagram | FA | 2017-07-12 | 2017-07-12 | 2017-09-13 | GRT-PP-IP-DT-170218 | FC | 0 | 2017-09-13 | N.A | FC | 0 | A | #VALUE! | #VALUE!
823 | PP | GRT-YD00-P1UHA-165219 | 165219 | [HRSG] Instrument Main Cable & JB Layout | FA | 2017-06-15 | 2017-07-15 | 2017-11-03 | GRT-PP-IP-DT-170306 | FC | 0 | 2017-11-03 | N.A | FC | 0 | A | #VALUE! | #VALUE!
824 | PP | GRT-CC03-P1UHA-175220 | 175220 | [HRSG] Foundation Plan | FA | 2017-03-25 | 2017-04-24 | 2017-05-26 | GRT-PP-IP-DT-170094 | FC | 0 | 2017-05-26 | N.A | FC | 0 | A | #VALUE! | #VALUE!
825 | PP | GRT-CC03-P1UHA-175221 | 175221 | [HRSG] Foundation Detail (1/2) | FA | 2017-03-25 | 2017-04-24 | 2017-05-26 | GRT-PP-IP-DT-170094 | FC | 0 | 2017-05-26 | N.A | FC | 0 | A | #VALUE! | #VALUE!
826 | PP | GRT-CC03-P1UHA-175222 | 175222 | [HRSG] Foundation Detail (2/2) | FA | 2017-03-25 | 2017-04-24 | 2017-05-26 | GRT-PP-IP-DT-170094 | FC | 0 | 2017-05-26 | N.A | FC | 0 | A | #VALUE! | #VALUE!
827 | PP | GRT-HM01-P0UMA-125233 | 0.12523 | [STG BUILDING] Steam Turbine Building HVAC Flow Schematic Diagram | FA | 2017-03-11 | 2017-04-10 | 2017-06-16 | GRT-PP-IP-DT-170119 | FC | 0 | 2017-06-16 | N.A | FC | 0 | A | #VALUE! | #VALUE!
828 | PP | GRT-HM01-P0UMA-125234 | 125234 | [STG BUILDING] Steam Turbine Building HVAC Ducting Layout | FA | 2017-03-11 | 2017-04-10 | 2017-03-30 | GRT-PP-IP-DT-170099 | FC | 0 | 2017-03-30 | N.A | FC | 0 | A | #VALUE! | #VALUE!
829 | PP | GRT-HM01-P0UMA-125235 | 125235 | [STG BUILDING] Steam Turbine Building HVAC Equipment Layout | FA | 2017-03-11 | 2017-04-10 | 2019-09-26 | GRT-PP-IP-DT-191407 | FC | 1 | 2019-09-26 | APPROVED ON SITE (PLN E) | FC | 1 | A | #VALUE! | #VALUE!
830 | PP | GRT-HM01-P0UMA-125236 | 125236 | [STG BUILDING] Steam Turbine Building HVAC Elevation, Section & Detail | FA | 2017-03-11 | 2017-04-10 | 2019-09-26 | GRT-PP-IP-DT-191407 | FC | 1 | 2019-09-26 | APPROVED ON SITE (PLN E) | FC | 1 | A | #VALUE! | #VALUE!
831 | PP | GRT-HM05-P0UMA-125237 | 125237 | [STG BUILDING] HVAC Calculation for Steam Turbine Generator Building | FA | 2017-06-20 | 2017-07-20 | 2017-10-04 | GRT-PP-IP-DT-170249 | FC | 0 | 2017-10-04 | N.A | FC | 0 | A | #VALUE! | #VALUE!
832 | PP | GRT-YD16-P0UMA-155238 | 155238 | [STG BUILDING] Cable Tray & Power Wiring Layout | FA | 2017-06-14 | 2017-07-14 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A | #VALUE! | #VALUE!
833 | PP | GRT-YE07-P0UMA-155240 | 155240 | [STG BUILDING] Grounding Wiring Layout | FA | 2017-04-08 | 2017-05-08 | 2017-06-06 | GRT-PP-IP-DT-170110 | FC | 0 | 2017-06-06 | N.A | FC | 0 | A | #VALUE! | #VALUE!
834 | PP | GRT-YE07-P0UMA-155241 | 155241 | [STG BUILDING] Lightning Protection Layout | FA | 2017-04-08 | 2017-05-08 | 2019-09-26 | GRT-PP-IP-DT-191407 (DCR 00052) | FC | 0DCR1 | 2019-09-26 | APPROVED ON SITE (PLN E) | FC | 0DCR1 | A | #VALUE! | #VALUE!
835 | PP | GRT-YQ01-P0UMA-155242 | 155242 | [STG BUILDING] Lighting and Receptacle Wiring Layout | FA | 2017-04-08 | 2017-05-08 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
836 | PP | GRT-YQ01-P0UMA-155243 | 155243 | [STG BUILDING] Lighting and Receptacle Panel Schedule and Connection Diagram | FA | 2017-07-12 | 2017-08-11 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
837 | PP | GRT-YD00-P0UMA-165244 | 165244 | [STG BUILDING] Instrument Main Cable & JB Layout | FA | 2017-07-06 | 2017-08-05 | 2017-12-12 | GRT-PP-IP-DT-170355 | FC | 0 | 2017-12-13 | N.A | FC | 0 | A | #VALUE! | #VALUE!
838 | PP | GRT-CA00-P0UMA-175245 | 175245 | [STG BUILDING] Floor Plan, Roof Plan & Finishing Schedule | FA | 2017-03-04 | 2017-04-03 | 2019-03-15 | GRT-PP-IP-DT-191080 (DCR 00027) | FC | 1 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 1 | B | #VALUE! | #VALUE!
839 | PP | GRT-CA00-P0UMA-175246 | 175246 | [STG BUILDING] Architectural Door & Window Schedule | FA | 2017-06-05 | 2017-07-05 | 2017-11-17 | GRT-PP-IP-DT-170326 | FC | 2 | 2017-11-17 | DRM SEOUL 7-NOVEMBER-2017 | FA | C | A | #VALUE! | #VALUE!
840 | PP | GRT-CA01-P0UMA-175250 | 175250 | [STG BUILDING] Foundation Plan (1/2) | FA | 2017-03-07 | 2017-04-06 | 2017-09-04 | GRT-PP-IP-DT-170206 | FC | 0 | 2017-09-04 | N.A | FC | 0 | A | #VALUE! | #VALUE!
841 | PP | GRT-CA01-P0UMA-175251 | 175251 | [STG BUILDING] Condenser Foundation Detail | FA | 2017-03-07 | 2017-04-06 | 2017-09-04 | GRT-PP-IP-DT-170206 | FC | 0 | 2017-09-04 | N.A | FC | 0 | A | #VALUE! | #VALUE!
842 | PP | GRT-CA01-P0UMA-175252 | 175252 | [STG BUILDING] Basement Floor Plan, El +3.104,EL+2.604, EL.+0.544, EL-0.496, & El-1.150 ( T.O.C ) | FA | 2017-03-07 | 2017-04-06 | 2019-03-15 | GRT-PP-IP-DT-191080 (DCR 00029) | FC | 1 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 1 | A | #VALUE! | #VALUE!
843 | PP | GRT-CA01-P0UMA-175253 | 175253 | [STG BUILDING] Floor Plan EL. +.104 (T.O.C) | FA | 2017-06-05 | 2017-07-05 | 2019-03-15 | GRT-PP-IP-DT-191080 (DCR 00028) | FC | 1 | 2019-03-15 | MINI DRM 13-15MAR2019 | FA | 1 | B | #VALUE! | #VALUE!
844 | PP | GRT-CA01-P0UMA-175254 | 175254 | [STG BUILDING] Foundation Framing Elevation | FA | 2017-03-07 | 2017-04-06 | 2017-09-04 | GRT-PP-IP-DT-170206 | FC | 0 | 2017-09-04 | N.A | FC | 0 | A | #VALUE! | #VALUE!
845 | PP | GRT-CA01-P0UMA-175259 | 175259 | [STG BUILDING] Location Foundation Plant and Detail | FA | 2017-06-05 | 2017-07-05 | 2017-11-21 | GRT-PP-IP-DT-170333 | FC | 0 | 2017-11-27 | 0027.001/C.1.2.17.01/E04/PLNE/XI/2017 | FA | A | A | #VALUE! | #VALUE!
846 | PP | GRT-CA03-P0UMA-175260 | 175260 | [STG BUILDING] Steam Turbine Building Steel Structure Column Layout Plan | FA | 2017-03-07 | 2017-04-06 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 1a | 2017-08-04 | N.A | FC | 1a | A | #VALUE! | #VALUE!
847 | PP | GRT-CA03-P0UMA-175261 | 175261 | [STG BUILDING] Steam Turbine Building Steel Structure Mezzanine Floor El +11.604 (F.F.L) | FA | 2017-03-07 | 2017-04-06 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 1a | 2017-08-04 | N.A | FC | 1a | A | #VALUE! | #VALUE!
848 | PP | GRT-CA03-P0UMA-175262 | 175262 | [STG BUILDING] Steam Turbine Building Steel Structure Operating Floor El +17.104 (F.F.L) | FA | 2017-03-07 | 2017-04-06 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 1a | 2017-08-04 | N.A | FC | 1a | A | #VALUE! | #VALUE!
849 | PP | GRT-CA03-P0UMA-175263 | 175263 | [STG BUILDING] Steam Turbine Building Steel Structure Roof Plan #1 | FA | 2017-03-07 | 2017-04-06 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 1a | 2017-08-04 | N.A | FC | 1a | A | #VALUE! | #VALUE!
850 | PP | GRT-CA03-P0UMA-175264 | 175264 | [STG BUILDING] Steam Turbine Building Steel Structure Runway Girder El +28.604 (T.O.R) | FA | 2017-03-07 | 2017-04-06 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 1a | 2017-08-04 | N.A | FC | 1a | A | #VALUE! | #VALUE!
851 | PP | GRT-CA03-P0UMA-175265 | 175265 | [STG BUILDING] Steam Turbine Building Steel Structure Roof Plan #2 | FA | 2017-03-07 | 2017-04-06 | 2019-03-15 | GRT-PP-IP-DT-191080 (DCR 00034) | FC | 2 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 2 | A | #VALUE! | #VALUE!
852 | PP | GRT-CA03-P0UMA-175266 | 175266 | [STG BUILDING] Steam Turbine Building Steel Structure Framing Elevation Line SA0 & SA | FA | 2017-03-07 | 2017-04-06 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 1a | 2017-08-04 | N.A | FC | 1a | A | #VALUE! | #VALUE!
853 | PP | GRT-CA03-P0UMA-175267 | 175267 | [STG BUILDING] Steam Turbine Building Steel Structure Framing Elevation Line SB, SC & SE | FA | 2017-03-07 | 2017-04-06 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 1a | 2017-08-04 | N.A | FC | 1a | A | #VALUE! | #VALUE!
854 | PP | GRT-CA03-P0UMA-175268 | 175268 | [STG BUILDING] Steam Turbine Building Steel Structure Framing Elevation Line SD & SE | FA | 2017-03-07 | 2017-04-06 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 1a | 2017-08-04 | N.A | FC | 1a | A | #VALUE! | #VALUE!
855 | PP | GRT-CA03-P0UMA-175269 | 175269 | [STG BUILDING] Steam Turbine Building Steel Structure Framing Elevation Line S8, S9 & S10 | FA | 2017-03-07 | 2017-04-06 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 1a | 2017-08-04 | N.A | FC | 1a | A | #VALUE! | #VALUE!
856 | PP | GRT-CA03-P0UMA-175270 | 175270 | [STG BUILDING] Steam Turbine Building Steel Structure Framing Elevation Line S11 & S12 | FA | 2017-03-07 | 2017-04-06 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 1a | 2017-08-04 | N.A | FC | 1a | A | #VALUE! | #VALUE!
857 | PP | GRT-CA06-P0UMA-175271 | 175271 | [STG BUILDING] Calculation Sheet for Steel Structure and Foundation | FA | 2017-03-07 | 2017-04-06 | 2017-10-05 | GRT-PP-IP-DT-170255 | FC | 0 | 2017-10-05 | N.A | FC | 0 | A | #VALUE! | #VALUE!
858 | PP | GRT-CC03-P0UMA-175272 | 175272 | [STG ] Concrete Structure Foundation Plan & Section | FA | 2017-04-08 | 2017-05-08 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A | #VALUE! | #VALUE!
859 | PP | GRT-CC03-P0UMA-175273 | 175273 | [STG BUILDING] Concrete Structure Framing Elevation | FA | 2017-04-08 | 2017-05-08 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A | #VALUE! | #VALUE!
860 | PP | GRT-CC03-P0UMA-175274 | 175274 | [STG BUILDING] Foundation Elevation, Section and Detail (2/2) | FA | 2017-03-07 | 2017-04-06 | 2017-05-12 | GRT-PP-IP-DT-170079 | FC | 0 | 2017-05-19 | 0019.001/C.1.2.17.01/E04/PLNEV/2017 | FA | A | A | #VALUE! | #VALUE!
861 | PP | GRT-CC03-P0UMA-175277(1OF2) | 175277 | [STG ] Concrete structure Insert Plate Plant and Detail | FA | 2017-06-05 | 2017-05-07 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A | #VALUE! | #VALUE!
862 | PP | GRT-CC03-P0UMA-175277(2OF2) | 175277 | [STG ] Concrete structure Insert Plate Plant and Detail | FA | 2017-06-05 | 2017-05-07 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A | #VALUE! | #VALUE!
863 | PP | GRT-CC07-P0UMA-175278 | 175278 | [STG BUILDING] Calculation Sheet for Foundation | FA | 2017-04-08 | 2017-05-08 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A | #VALUE! | #VALUE!
864 | PP | GRT-XG02-P0UGD-115279 | 115279 | [WTP] Piping and instrument diagram (PID) Raw Water System | FA | 2017-02-23 | 2017-03-25 | 2019-01-10 | GRT-PP-IP-DT-190929 | FC | 4 | 2019-01-22 | 004/061/GRT/UPR/2019 | FC | 4 | A | #VALUE! | #VALUE!
865 | PP | GRT-XG02-P0UGD-115280 | 115280 | [WTP] Piping and instrument diagram (PID) Demin Make-up System | FA | 2017-02-23 | 2017-03-25 | 2019-01-10 | GRT-PP-IP-DT-190929 | FC | 4 | 2019-01-22 | 004/061/GRT/UPR/2019 | FC | 4 | A | #VALUE! | #VALUE!
866 | PP | GRT-XG02-P0UGD-115281 | 115281 | [WTP] Piping and instrument diagram (PID) Water Treatment System | FA | 2017-02-21 | 2017-03-23 | 2018-12-20 | GRT-PP-IP-DT-170367 | FC | 0 | 2017-12-21 | N.A | FC | 0 | A | #VALUE! | #VALUE!
867 | PP | GRT-YT01-P0UGD-115282 | 115282 | [WTP] Process data sheet for raw water tank | FA | 2017-02-23 | 2017-03-25 | 2017-10-04 | GRT-PP-IP-DT-170249 | FC | 1 | 2017-10-04 | N.A | FC | 1 | A | #VALUE! | #VALUE!
868 | PP | GRT-YT01-P0UGD-115283 | 115283 | [WTP] Process data sheet for make-up demin water tank | FA | 2017-02-23 | 2017-03-25 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 1 | 2017-10-17 | N.A | FC | 1 | A | #VALUE! | #VALUE!
869 | PP | GRT-YT01-P0UGD-115284 | 115284 | [WTP] Process data sheet for make up demin for closed cooling system pump | FA | 2017-02-23 | 2017-03-25 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
870 | PP | GRT-YT01-P0UGD-115285 | 115285 | [WTP] Process data sheet for Portable Water Pump | FA | 2017-02-23 | 2017-03-25 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
871 | PP | GRT-XG02-P0UGD-115286 | 115286 | [WTP] Piping and instrumentation Diagram for Auxiliary Service Water System | FA | 2017-02-21 | 2017-03-23 | 2017-11-30 | GRT-PP-IP-DT-170343 | FC | 1 | 2017-11-30 | N.A | FC | 1 | A | #VALUE! | #VALUE!
872 | PP | GRT-XG02-P0UGD-115287 | 115287 | [WTP] Piping and instrument diagram (PID) Service Water System | FA | 2017-02-21 | 2017-03-23 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 1 | 2017-10-17 | N.A | FC | 1 | A | #VALUE! | #VALUE!
873 | PP | GRT-YT01-P0UGD-115288 | 115288 | [WTP] Process data sheet for raw water pump | FA | 2017-02-21 | 2017-03-23 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
874 | PP | GRT-YT01-P0UGD-115289 | 115289 | [WTP] Process data sheet for service water pump | FA | 2017-02-23 | 2017-03-25 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
875 | PP | GRT-YT01-P0UGD-115290 | 115290 | [WTP] Process data sheet for sump pumps | FA | 2017-04-06 | 2017-05-06 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
876 | PP | GRT-XG02-P0UGD-115291 | 115291 | [WTP] Piping and Instrumentation Diagram for Interconnecting System | FA | 2017-02-21 | 2017-06-05 | 2017-10-31 | GRT-PP-IP-DT-170293 | FC | 1 | 2017-10-31 | N.A | FC | 1 | A | #VALUE! | #VALUE!
877 | PP | GRT-XW03-P0UGD-115292 | 115292 | [WTP] Process calculation for service water pump | FA | 2017-02-23 | 2017-03-25 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A | #VALUE! | #VALUE!
878 | PP | GRT-XW03-P0UGD-115293 | 115293 | [WTP] Process calculation for sump pumps | FA | 2017-04-06 | 2017-05-06 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A | #VALUE! | #VALUE!
879 | PP | GRT-XW01-P0UGD-115294 | 115294 | [WTP] Process idividual specification for Water treatment system | FA | 2017-02-21 | 2017-03-23 | 2017-11-27 | GRT-PP-IP-DT-170339 | FC | 0 | 2017-11-27 | N.A | FC | 0 | A | #VALUE! | #VALUE!
880 | PP | GRT-XW03-P0UGD-115295 | 115295 | [WTP] Process calculation for raw water tank | FA | 2017-06-10 | 2017-07-10 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
881 | PP | GRT-XW03-P0UGD-115296 | 115296 | [WTP] Process calculation for make-up demin water tank | FA | 2017-02-23 | 2017-03-25 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
882 | PP | GRT-XW03-P0UGD-115297 | 115297 | [WTP] Process calculation for make up demin system pump | FA | 2017-02-23 | 2017-03-25 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
883 | PP | GRT-XW03-P0UGD-115298 | 115298 | [WTP] Process calculation for auxiliary service water pump | FA | 2017-02-23 | 2017-03-25 | 2017-09-27 | GRT-PP-IP-DT-170242 | FC | 1 | 2017-09-27 | N.A | FC | 1 | A | #VALUE! | #VALUE!
884 | PP | GRT-XW03-P0UGD-115299 | 115299 | [WTP] Process calculation for raw water pump | FA | 2017-02-21 | 2017-03-23 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
885 | PP | GRT-YT01-P0UGD-125300 | 125300 | [WTP] Mech. Data Sheet for Make-up Demin Water Tank | FA | 2017-06-23 | 2017-07-23 | 2017-10-06 | GRT-PP-IP-DT-170257 | FC | 0 | 2017-10-06 | N.A | FC | 0 | A | #VALUE! | #VALUE!
886 | PP | GRT-YT01-P0UGD-125301 | 125301 | [WTP] Mech. Data Sheet for Make up Demin for Closed Cooling System Pump | FA | 2017-03-02 | 2017-04-01 | 2017-07-25 | GRT-PP-IP-DT-170154 | FC(D) | B | 2017-08-01 | 0001.001/C.1.2.17.01/E04/PLNE/VIII/2017 | FA | B | B | #VALUE! | #VALUE!
887 | PP | GRT-YT01-P0UGD-125451 | 125451 | [WTP] Mech. Data Sheet for Portable Water Pump | FA | 2017-02-28 | 2017-03-30 | 2017-07-25 | GRT-PP-IP-DT-170154 | FC(D) | B | 2017-08-01 | 0001.001/C.1.2.17.01/E04/PLNE/VIII/2017 | FA | B | B | #VALUE! | #VALUE!
888 | PP | GRT-YT01-P0UGD-125303 | 125303 | [WTP] Mech. Data Sheet for Raw Water Tank | FI | 2017-06-12 | 2017-07-12 | 2017-10-16 | GRT-PP-IP-DT-170270 | FI | A | 2017-10-19 | 019.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I | #VALUE! | #VALUE!
889 | PP | GRT-YT01-P0UGD-125304 | 125304 | [WTP] Mech. Data Sheet for Service Water Pump | FA | 2017-03-02 | 2017-04-01 | 2017-07-25 | GRT-PP-IP-DT-170154 | FC(D) | B | 2017-08-01 | 0001.001/C.1.2.17.01/E04/PLNE/VIII/2017 | FA | B | B | #VALUE! | #VALUE!
890 | PP | GRT-YT01-P0UGD-125305 | 125305 | [WTP] Mech. Data Sheet for Sump Pumps | FA | 2017-04-13 | 2017-05-13 | 2017-07-25 | GRT-PP-IP-DT-170154 | FC(D) | C | 2017-08-01 | 0001.001/C.1.2.17.01/E04/PLNE/VIII/2017 | FA | C | B | #VALUE! | #VALUE!
891 | PP | GRT-CC00-P0UGD-145306 | 145306 | [WTP] Piping Layout Drawing for Water Treatment Area | FA | 2017-02-28 | 2017-03-30 | 2018-02-02 | GRT-PP-IP-DT-180405 | FC | 0 | 2018-02-12 | Comment Sheet IP | FC | 0 | A | #VALUE! | #VALUE!
892 | PP | GRT-CC00-P0UGD-145307 | 145307 | [WTP] Piping Layout Drawing Demin Water Area | FA | 2017-06-23 | 2017-07-23 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A | #VALUE! | #VALUE!
893 | PP | GRT-CC00-P0UGD-145308 | 145308 | [WTP] Piping Layout Drawing Demin to HRSG Area | FA | 2017-03-02 | 2017-04-01 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A | #VALUE! | #VALUE!
894 | PP | GRT-YD16-P0UGD-155309 | 155309 | [WTP] Cable Tray and Power Wiring Layout | FA | 2017-03-22 | 2017-04-21 | 2017-08-21 | GRT-PP-IP-DT-170187 | FC | 1 | 2017-08-22 | N.A | FC | 1 | A | #VALUE! | #VALUE!
895 | PP | GRT-YE07-P0UGD-155310 | 155310 | [WTP] Grounding Wiring Layout | FA | 2017-03-22 | 2017-04-21 | 2017-09-22 | GRT-PP-IP-DT-170236 | FC | 0 | 2017-09-25 | N.A | FC | 0 | A | #VALUE! | #VALUE!
896 | PP | GRT-YE07-P0UGD-155311 | 155311 | [WTP] Lightning Protection Layout | FA | 2017-03-22 | 2017-04-21 | 2019-09-19 | GRT-PP-IP-DT-191389 (DCR 0040) | FC | 0DCR2 | 2019-09-26 | APPROVED ON SITE (PLN E) | FC | 0DCR2 | A | #VALUE! | #VALUE!
897 | PP | GRT-YQ01-P0UGD-155312 | 155312 | [WTP] Lighting and Receptacle Wiring Layout | FA | 2017-03-22 | 2017-04-21 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2019-09-26 | APPROVED ON SITE (PLN E) | FC | 0DCR2 | A | #VALUE! | #VALUE!
898 | PP | GRT-YQ01-P0UGD-155313 | 155313 | [WTP] Lighting and Receptacle Panel Schedule and Connection Diagram | FA | 2017-03-22 | 2017-04-21 | 2017-09-22 | GRT-PP-IP-DT-170236 | FC | 0 | 2017-09-25 | N.A | FC | 0 | A | #VALUE! | #VALUE!
899 | PP | GRT-CV03-P0UGD-165314 | 165314 | [WTP] Instrument Data sheet for Potable Water System | FA | 2017-03-02 | 2017-04-01 | 2018-03-19 | GRT-PP-IP-DT-180471 | FC | 0 | 2018-03-21 | Stempel Approved | FC | 0 | A | #VALUE! | #VALUE!
900 | PP | GRT-CV03-P0UGD-165315 | 165315 | [WTP] Instrument Data Sheet for Raw Water System | FA | 2017-03-02 | 2017-04-01 | 2017-05-10 | GRT-PP-IP-DT-170077 | FC | 0 | 2017-05-15 | N.A | FC | 0 | A | #VALUE! | #VALUE!
901 | PP | GRT-CV03-P0UGD-165316 | 165316 | [WTP] Instrument Data Sheet for Demin Make up System | FA | 2017-03-03 | 2017-04-02 | 2017-11-13 | GRT-PP-IP-DT-170314 | FC | 0 | 2017-11-13 | N.A | FC | 0 | A | #VALUE! | #VALUE!
902 | PP | GRT-CV03-P0UGD-165317 | 165317 | [WTP] Instrument Data Sheet for Service Water System | FA | 2017-06-02 | 2017-07-02 | 2017-10-20 | GRT-PP-IP-DT-170280 | FC | 0 | 2017-10-23 | N.A | FC | 0 | A | #VALUE! | #VALUE!
903 | PP | GRT-YD00-P0UGD-165318 | 165318 | [WTP] Instrument Location Plan Layout for Potable Water System | FA | 2017-03-16 | 2017-04-15 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A | #VALUE! | #VALUE!
904 | PP | GRT-YD00-P0UGD-165319 | 165319 | [WTP] Instrument Main Cable & JB Layout for Potable Water System | FA | 2017-03-22 | 2017-04-21 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A | #VALUE! | #VALUE!
905 | PP | GRT-YD00-P0UGD-165320 | 165320 | [WTP] Instrument Cable Wiring Layout for Raw Water System | FA | 2017-03-29 | 2017-04-28 | 2017-08-01 | GRT-PP-IP-DT-170164 | FC | 0 | 2017-08-01 | N.A | FC | 0 | A | #VALUE! | #VALUE!
906 | PP | GRT-YD00-P0UGD-165321 | 165321 | [WTP] Instrument Location Plan Layout for Raw Water System | FA | 2017-07-07 | 2017-08-06 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A | #VALUE! | #VALUE!
907 | PP | GRT-YD00-P0UGD-165322 | 165322 | [WTP] Instrument Location Plan Layout for Service Water System | FA | 2017-03-16 | 2017-04-15 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A | #VALUE! | #VALUE!
908 | PP | GRT-YD00-P0UGD-165323 | 165323 | [WTP] Instrument Main Cable & JB Layout for Raw Water System | FA | 2017-03-22 | 2017-04-21 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A | #VALUE! | #VALUE!
909 | PP | GRT-YD00-P0UGD-165324 | 165324 | [WTP] Instrument Main Cable & JB Layout for Service Water System | FA | 2017-03-22 | 2017-04-21 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A | #VALUE! | #VALUE!
910 | PP | GRT-YD00-P0UGD-165325 | 165325 | [WTP] Instrument Cable Wiring Layout for Potable Water System | FA | 2017-03-29 | 2017-04-28 | 2017-08-01 | GRT-PP-IP-DT-170164 | FC | 0 | 2017-08-01 | N.A | FC | 0 | A | #VALUE! | #VALUE!
911 | PP | GRT-YD00-P0UGD-165326 | 165326 | [WTP] Instrument Cable Wiring Layout for Water Treatment System | FA | 2017-03-29 | 2017-04-28 | 2017-08-01 | GRT-PP-IP-DT-170164 | FC | 0 | 2017-08-01 | N.A | FC | 0 | A | #VALUE! | #VALUE!
912 | PP | GRT-YD00-P0UGD-165327 | 165327 | [WTP] Instrument Location Plan Layout for Water Treatment System | FA | 2017-03-16 | 2017-04-15 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A | #VALUE! | #VALUE!
913 | PP | GRT-YD00-P0UGD-165328 | 165328 | [WTP] Instrument Main Cable & JB Layout for Water Treatment System | FA | 2017-03-22 | 2017-04-21 | 2017-07-07 | GRT-PP-IP-DT-170133 | FC | 0 | 2017-07-07 | N.A | FC | 0 | A | #VALUE! | #VALUE!
914 | PP | GRT-YL01-P0UGD-165333 | 165333 | [DCS] I/O List for Demin Makeup System | FA | 2017-02-28 | 2017-08-16 | 2017-11-13 | GRT-PP-IP-DT-170314 | FC | 0 | 2017-11-13 | N.A | FC | 0 | A | #VALUE! | #VALUE!
915 | PP | GRT-YL01-P0UGD-165334 | 165334 | [DCS] I/O List for Raw Water System | FA | 2017-02-28 | 2017-03-30 | 2017-11-13 | GRT-PP-IP-DT-170314 | FC | 0 | 2017-11-13 | N.A | FC | 0 | A | #VALUE! | #VALUE!
916 | PP | GRT-YL01-P0UGD-165335 | 165335 | [DCS] I/O List for Service Water System | FA | 2017-02-28 | 2017-03-30 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FA | 0 | A | #VALUE! | #VALUE!
917 | PP | GRT-YL01-P0UGD-165336 | 165336 | [DCS] I/O List for Auxiliary Service Water System | FA | 2017-02-28 | 2017-03-30 | 2017-10-05 | GRT-PP-IP-DT-170254 | FC(D) | C | 2017-10-17 | 0017.001/C.1.2.17.01/E04/PLNE/X/2017 | FA | C | A | #VALUE! | #VALUE!
918 | PP | GRT-YS02-P0UGD-165341 | 165341 | [WTP] Instrument Termination Diagram for Potable Water System | FA | 2017-07-07 | 2017-08-06 | 2017-09-18 | GRT-PP-IP-DT-170230 | FC | 0 | 2017-09-18 | N.A | FC | 0 | A | #VALUE! | #VALUE!
919 | PP | GRT-YS02-P0UGD-165342 | 165342 | [WTP] Instrument Termination Diagram for Raw Water System | FA | 2017-07-07 | 2017-08-06 | 2017-09-28 | GRT-PP-IP-DT-170244 | FC | 0 | 2017-09-28 | N.A | FC | 0 | A | #VALUE! | #VALUE!
920 | PP | GRT-YS02-P0UGD-165343 | 165343 | [WTP] Instrument Termination Diagram for Water Treatment System | FA | 2017-07-07 | 2017-08-06 | 2017-09-28 | GRT-PP-IP-DT-170244 | FC | 0 | 2017-09-28 | N.A | FC | 0 | A | #VALUE! | #VALUE!
921 | PP | GRT-YS02-P0UGD-165344 | 165344 | [WTP] Instrument Termination Diagram for Service Water System | FA | 2017-07-07 | 2017-08-06 | 2017-09-28 | GRT-PP-IP-DT-170244 | FC | 0 | 2017-09-28 | N.A | FC | 0 | A | #VALUE! | #VALUE!
922 | PP | GRT-CA00-P0UGD-175345 | 175345 | [WTP] Water Treatment Plant Architectural Plan, View, Section & Finishing Schedule | FA | 2017-03-15 | 2017-04-14 | 2017-06-05 | GRT-PP-IP-DT-170107 | FC | 0 | 2017-06-05 | N.A | FC | 0 | A | #VALUE! | #VALUE!
923 | PP | GRT-CA00-P0UGD-175346 | 175346 | [WTP] Architectural door & Window key Plant and Schedule | FA | 2017-06-12 | 2017-07-12 | 2017-09-04 | GRT-PP-IP-DT-170206 | FC | 0 | 2017-09-04 | N.A | FC | 0 | A | #VALUE! | #VALUE!
924 | PP | GRT-CA01-P0UGD-175347 | 175347 | [WTP] Foundation Plan | FA | 2017-03-22 | 2017-04-21 | 2017-06-05 | GRT-PP-IP-DT-170107 | FC | 0 | 2017-06-05 | N.A | FC | 0 | A | #VALUE! | #VALUE!
925 | PP | GRT-CA01-P0UGD-175348 | 175348 | [WTP] Concrete Structure Floor Plan, Section & Member Schedule | FA | 2017-03-22 | 2017-04-21 | 2017-07-25 | GRT-PP-IP-DT-170155 | FC | 0 | 2017-07-25 | N.A | FC | 0 | A | #VALUE! | #VALUE!
926 | PP | GRT-CA03-P0UGD-175349 | 175349 | [WTP] Steel Structure Framing Plan | FA | 2017-03-22 | 2017-04-21 | 2017-06-05 | GRT-PP-IP-DT-170107 | FC | 0 | 2017-06-05 | N.A | FC | 0 | A | #VALUE! | #VALUE!
927 | PP | GRT-CA03-P0UGD-175350 | 175350 | [WTP] Steel Structure Framing Elevation and Detail | FA | 2017-06-23 | 2017-07-23 | 2017-06-05 | GRT-PP-IP-DT-170107 | FC | 0 | 2017-06-05 | N.A | FC | 0 | A | #VALUE! | #VALUE!
928 | PP | GRT-CC03-P0UGD-175352 | 175352 | [WTP] Make Up Closed Cooling Foundation | FA | 2017-06-23 | 2017-07-23 | 2018-02-02 | GRT-PP-IP-DT-180405 | FC | 0 | 2018-02-12 | Comment Sheet IP | FC | 0 | B | #VALUE! | #VALUE!
929 | PP | GRT-CC03-P0UGD-175353 | 175353 | [WTP] Make Up Demin for Deaerator Pump Foundation | FA | 2017-06-23 | 2017-07-23 | 2018-12-21 | GRT-PP-IP-DT-180910 | FC | 1 | 2019-01-15 | Comment Sheet IP | FC | 1 | A | #VALUE! | #VALUE!
930 | PP | GRT-CC03-P0UGD-175354 | 175354 | [WTP] Service Water Pump Foundation | FA | 2017-06-23 | 2017-07-23 | 2018-02-02 | GRT-PP-IP-DT-180405 | FC | 0 | 2018-02-12 | Comment Sheet IP | FC | 0 | B | #VALUE! | #VALUE!
931 | PP | GRT-CC03-P0UGD-175355 | 175355 | [WTP] Raw Water Tank Pump Foundation | FA | 2017-06-23 | 2017-07-23 | 2017-12-18 | GRT-PP-IP-DT-180405 | FC | 0 | 2018-02-12 | Comment Sheet IP | FC | 0 | B | #VALUE! | #VALUE!
932 | PP | GRT-CC03-P0UGD-175357 | 175357 | Sum Pit at STG Area Foundation Plan, Section and Detail | FA | 2017-06-23 | 2017-07-23 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A | #VALUE! | #VALUE!
933 | PP | GRT-YD16-P0UAG-155358 | 155358 | [Transformer] Cable Tray and Power Wiring Layout | FA | 2017-06-23 | 2017-07-23 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 1 | 2017-10-24 | N.A | FC | 1 | A | #VALUE! | #VALUE!
934 | PP | GRT-YE06-P0UAG-155359 | 155359 | [Transformer] Grounding Wiring Layout | FA | 2017-06-23 | 2017-07-23 | 2017-08-21 | GRT-PP-IP-DT-170187 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
935 | PP | GRT-YE06-P0UAG-155360 | 155360 | [Transformer] Lightning Protection Layout | FA | 2017-06-23 | 2017-07-23 | 2017-08-21 | GRT-PP-IP-DT-170187 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
936 | PP | GRT-YQ01-P0UAG-155361 | 155361 | [Transformer] Lighting and Receptale Wiring Layout | FA | 2017-06-23 | 2017-07-23 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
937 | PP | GRT-YQ01-P0UAG-155362 | 155362 | [Transformer] Lighting and Receptacle Panel Schedule and Connection Diagram | FA | 2017-06-20 | 2017-07-20 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
938 | PP | GRT-CC03-P0UAG-175363 | 175363 | [Transformer] FOUNDATION PLAN, PLAN EL. +5.672 (T.O.S) SECTION, DETAIL & MEMBER SCHEDULE | FA | 2017-06-20 | 2017-07-20 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 0 | 2017-10-17 | N.A | FC | 0 | A | #VALUE! | #VALUE!
939 | PP | GRT-CC03-P0UAG-175364 | 175364 | [Transformer] Section Detail | FA | 2017-06-20 | 2017-07-20 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 0 | 2017-10-17 | N.A | FC | 0 | A | #VALUE! | #VALUE!
940 | PP | GRT-CC03-P0UAG-175365 | 175365 | [Transformer] Foundation Detail | FA | 2017-06-20 | 2017-07-20 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 0 | 2017-10-17 | N.A | FC | 0 | A | #VALUE! | #VALUE!
941 | PP | GRT-CC07-P0UAG-175366 | 175366 | [Transformer] Calculation Sheet for Foundation | FA | 2017-06-20 | 2017-07-20 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 0 | 2017-10-17 | N.A | FC | 0 | A | #VALUE! | #VALUE!
942 | PP | GRT-YD16-P0UAA-155367 | 155367 | [Switchyard] Cable Tray and Power Wiring Layout | FA | 2017-06-19 | 2017-07-19 | 2017-09-13 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-09-13 | N.A | FC | 0 | A | #VALUE! | #VALUE!
943 | PP | GRT-YQ01-P0UAA-155369 | 155369 | [Switchyard] Lighting and Receptale Wiring Layout | FA | 2017-06-19 | 2017-07-19 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
944 | PP | GRT-YQ01-P0UAA-155370 | 155370 | [Switchyard] Lighting and Receptacle Panel Schedule and Connection Diagram | FA | 2017-06-19 | 2017-07-19 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
945 | PP | GRT-YW06-P0UAA-155371 | 155371 | [Switchyard] Grounding Wiring Layout | FA | 2017-06-23 | 2017-07-23 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A | #VALUE! | #VALUE!
946 | PP | GRT-CC03-P0UAA-175372 | 175372 | [Switchyard] Foundation Layout | FA | 2017-06-23 | 2017-07-23 | 2019-03-15 | GRT-PP-IP-DT-191080 (DCR 00026) | FC | 1 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 1 | A | #VALUE! | #VALUE!
947 | PP | GRT-CC03-P0UAA-175373 | 175373 | [Switchyard] Type 1 Foundation Plan, Section & Detail | FA | 2017-06-23 | 2017-07-23 | 2017-11-30 | GRT-PP-IP-DT-170343 | FC | 0 | 2017-11-30 | N.A | FC | 0 | A | #VALUE! | #VALUE!
948 | PP | GRT-CC07-P0UAA-175376 | 175376 | [Switchyard] Calculation Sheet for Foundation | FA | 2017-07-07 | 2017-07-06 | 2017-11-30 | GRT-PP-IP-DT-170343 | FC | 0 | 2017-11-30 | N.A | FC | 0 | A | #VALUE! | #VALUE!
949 | PP | GRT-CE00-P0SG-115377 | 115377 | [Fire Fighting System] Lay out fire protection equipment | FA | 2017-07-07 | 2017-07-06 | 2019-01-08 | GRT-PP-IP-DT-190925 (DCR0017) | FC | 1 | 2019-01-15 | Comment Sheet IP | FC |  | A | #VALUE! | #VALUE!
950 | PP | GRT-CE00-P0SG-115378 | 115378 | [Fire Fighting System] Escape route lay out | FA | 2017-07-07 | 2017-07-06 | 2017-08-16 | GRT-PP-IP-DT-170183 | FC | 0 | 2017-08-16 | N.A | FC | 0 | A | #VALUE! | #VALUE!
951 | PP | GRT-YT01-P0SG-115379 | 115379 | [Fire Fighting System] Process data sheet for Jockey Pump | FA | 2017-07-07 | 2017-07-06 | 2017-04-18 | GRT-PP-IP-DT-170047 | FC | 0 | 2017-04-21 | 0021.001/C.1.2.17.01/E04/PLNE/IV/2017 | FC | 0 | I | #VALUE! | #VALUE!
952 | PP | GRT-YT01-P0SG-115380 | 115380 | [Fire Fighting System] Process data sheet for Fire Water Pump | FA | 2017-07-07 | 2017-07-06 | 2017-08-16 | GRT-PP-IP-DT-170183 | FC | 0 | 2017-08-16 | N.A | FC | 0 | A | #VALUE! | #VALUE!
953 | PP | GRT-YT01-P0SG-115381 | 115381 | [Fire Fighting System] Datasheet for Fire Protection Equipment | FA | 2017-03-20 | 2017-04-19 | 2017-11-27 | GRT-PP-IP-DT-170339 | FC | 0 | 2017-11-27 | N.A | FC | 0 | A | #VALUE! | #VALUE!
954 | PP | GRT-XG02-P0SG-115382 | 115382 | [Fire Fighting System] Piping & Instrument Diagram for firewater system | FA | 2017-03-20 | 2017-04-19 | 2019-03-15 | GRT-PP-IP-DT-191080 (DCR 00023) | FC | 1 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 1 | A | #VALUE! | #VALUE!
955 | PP | GRT-XG08-P0SG-115383 | 115383 | [Fire Fighting System] Utility Flow Diagram Fire water system | FA | 2017-03-20 | 2017-04-19 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A | #VALUE! | #VALUE!
956 | PP | GRT-XW01-P0SG-115384 | 115384 | [Fire Fighting System] Fire Protection Design Basis | FA | 2017-03-20 | 2017-04-19 | 2017-08-16 | GRT-PP-IP-DT-170183 | FC | 0 | 2017-08-16 | N.A | FC | 0 | A | #VALUE! | #VALUE!
957 | PP | GRT-XW01-P0SG-115385 | 115385 | [Fire Fighting System] Fire Design Basis | FA | 2017-03-20 | 2017-04-19 | 2017-08-16 | GRT-PP-IP-DT-170183 | FC | 0 | 2017-08-16 | N.A | FC | 0 | A | #VALUE! | #VALUE!
958 | PP | GRT-XW01-P0SG-115386 | 115386 | [Fire Fighting System] Specification for Fire Protection Equipment | FA | 2017-03-20 | 2017-04-19 | 2017-08-16 | GRT-PP-IP-DT-170183 | FC | 0 | 2017-08-16 | N.A | FC | 0 | A | #VALUE! | #VALUE!
959 | PP | GRT-XW03-P0SG-115387 | 115387 | [Fire Fighting System] Process Calculation for Jockey Pump | FA | 2017-03-20 | 2017-04-19 | 2017-08-16 | GRT-PP-IP-DT-170183 | FC | 0 | 2017-08-16 | N.A | FC | 0 | A | #VALUE! | #VALUE!
960 | PP | GRT-XW03-P0SG-115388 | 115388 | [Fire Fighting System] Process Calculation for Fire Water Pump | FA | 2017-03-20 | 2017-04-19 | 2017-08-16 | GRT-PP-IP-DT-170183 | FC | 0 | 2017-08-16 | N.A | FC | 0 | A | #VALUE! | #VALUE!
961 | PP | GRT-XW03-P0SG-115389 | 115389 | [Fire Fighting System] Process Calculation for Fire Water Consumption | FA | 2017-03-20 | 2017-04-19 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A | #VALUE! | #VALUE!
962 | PP | GRT-XW03-P0SG-115390 | 115390 | [Fire Fighting System] Fire Water Hydraulic Calculation | FA | 2017-03-20 | 2017-04-19 | 2017-08-16 | GRT-PP-IP-DT-170183 | FC | 0 | 2017-08-16 | N.A | FC | 0 | A | #VALUE! | #VALUE!
963 | PP | GRT-YT01-P0SG-125391 | 125391 | [Fire Fighting System] Mech. Data Sheet for Jockey Pump | FA | 2017-03-27 | 2017-04-26 | 2017-10-06 | GRT-PP-IP-DT-170257 | FC | 0 | 2017-10-06 | N.A | FC | 0 | A | #VALUE! | #VALUE!
964 | PP | GRT-YT01-P0SG-125392 | 125392 | [Fire Fighting System] Mech. Data Sheet for Fire Water Pump | FA | 2017-03-27 | 2017-04-26 | 2017-10-06 | GRT-PP-IP-DT-170257 | FC | 0 | 2017-10-06 | N.A | FC | 0 | A | #VALUE! | #VALUE!
965 | PP | GRT-YD16-P0UGD-155393 | 155393 | [Fire Fighting Shelter] Cable Tray and Power Wiring Layout | FA | 2017-07-14 | 2017-08-13 | 2017-09-08 | GRT-PP-IP-DT-170215 | FC | 0 | 2017-09-08 | N.A | FC | 0 | A | #VALUE! | #VALUE!
966 | PP | GRT-YE07-P0UGD-155394 | 155394 | [Fire Fighting Shelter] Grounding Wiring Layout | FA | 2017-07-14 | 2017-08-13 | 2017-09-08 | GRT-PP-IP-DT-170215 | FC | 0 | 2017-09-08 | N.A | FC | 0 | A | #VALUE! | #VALUE!
967 | PP | GRT-YE07-P0UGD-155395 | 155395 | [Fire Fighting Shelter] Lightning Protection Layout | FA | 2017-07-14 | 2017-08-13 | 2019-09-19 | GRT-PP-IP-DT-191389 (DCR 0040) | FC | 0DCR2 | 2019-09-26 | APPROVED ON SITE (PLN E) | FC |  | A | #VALUE! | #VALUE!
968 | PP | GRT-YQ01-P0UGD-155396 | 155396 | [Fire Fighting Shelter] Lighting and Receptale Wiring Layout | FA | 2017-07-14 | 2017-08-13 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2019-09-26 | APPROVED ON SITE (PLN E) | FC | 0 | A | #VALUE! | #VALUE!
969 | PP | GRT-YQ01-P0UGD-155397 | 155397 | [Fire Fighting Shelter] Lighting and Receptacle Panel Schedule and Connection Diagram | FA | 2017-07-07 | 2017-08-13 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
970 | PP | GRT-CA01-P0UGD-175399 | 175399 | [Fire Fighting Shelter] Foundation, Foundation Plan & Detail | FA | 2017-07-14 | 2017-08-13 | 2019-06-28 | GRT-PP-IP-DT-191235 (DCR 00048) | FC | 1 | 2019-07-19 | 040/061/GRT/UPR/2019 |  | 1 | B | #VALUE! | #VALUE!
971 | PP | GRT-CA03-P0UGD-175400 | 175400 | [Fire Fighting Shelter] Steel Structure Framing Plan & Elevation | FA | 2017-07-14 | 2017-08-13 | 2017-08-08 | GRT-PP-IP-DT-170175 | FC | 0 | 2017-08-08 | N.A | FC | 0 | A | #VALUE! | #VALUE!
972 | PP | GRT-CA06-P0UGD-175401 | 175401 | [Fire Fighting Shelter] Calculation Sheet for Fire Fighting Shelter Stricture and Foundation | FA | 2017-07-14 | 2017-08-13 | 2017-10-05 | GRT-PP-IP-DT-170255 | FC | 0 | 2017-10-05 | N.A | FC | 0 | A | #VALUE! | #VALUE!
973 | PP | GRT-YD16-P0UCA-155408 | 155408 | [Control Building] Cable Tray and Power Wiring Layout | FA | 2017-06-14 | 2017-07-14 | 2017-11-20 | GRT-PP-IP-DT-170329 | FC | 1 | 2017-11-21 | N.A | FC | 1 | A | #VALUE! | #VALUE!
974 | PP | GRT-YE00-P0UCA-155409 | 155409 | [Electrical Room] Clock System Wiring Layout | FA | 2017-06-14 | 2017-07-14 | 2017-10-31 | GRT-PP-IP-DT-170293 | FC | 0 | 2017-10-31 | N.A | FC | 0 | A | #VALUE! | #VALUE!
975 | PP | GRT-YE07-P0UCA-155410 | 155410 | [Electrical Room] Grounding Wiring Layout | FA | 2017-06-14 | 2017-07-14 | 2017-09-18 | GRT-PP-IP-DT-170230 | FC | 0 | 2017-09-18 | N.A | FC | 0 | A | #VALUE! | #VALUE!
976 | PP | GRT-YM02-P0UCA-155411 | 155411 | [Electrical Room] Electrical Equipment Layout | FA | 2017-07-16 | 2017-08-06 | 2019-11-13 | GRT-PP-IP-DT-191482 | FC | 3 | 2019-11-29 | 057/061/GRT/UPR/2019 |  | 3 | A | #VALUE! | #VALUE!
977 | PP | GRT-YM02-P0UCA-155412 | 155412 | Electrical Room Section & Detail Cable Tray Layout | FA | 2017-06-14 | 2017-07-14 | 2017-11-20 | GRT-PP-IP-DT-170329 | FC | 1 | 2017-11-21 | N.A | FC | 1 | A | #VALUE! | #VALUE!
978 | PP | GRT-YD16-P0UBN-155413 | 155413 | [Engine Diesel Generator] Cable Tray and Power Wiring Layout | FA | 2017-06-14 | 2017-07-14 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 1 | 2017-10-24 | N.A | FC | 1 | A | #VALUE! | #VALUE!
979 | PP | GRT-CC07-P0UZA-175420 | 175420 | [Structure for Transport, Trafic & Other Purpose] Calculation for Sheet Pile and Concrete Batter Pile for Thermal Barier | FA | 2017-07-14 | 2017-08-13 | 2017-08-16 | GRT-PP-IP-DT-170183 | FC | 0 | 2017-08-16 | N.A | FC | 0 | A | #VALUE! | #VALUE!
980 | PP | GRT-CC03-P0UZA-175421 | 175421 | [Structure for Transport, Trafic & Other Purpose] Thermal Barrier Pilling Plan and List | FA | 2017-07-14 | 2017-08-13 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 0 | 2017-08-04 | N.A | FC | 0 | A | #VALUE! | #VALUE!
981 | PP | GRT-CC03-P0UZA-175422 | 175422 | [Structure for Transport, Trafic & Other Purpose] Thermal Barrier Layout | FA | 2017-07-14 | 2017-08-13 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 0 | 2017-08-04 | N.A | FC | 0 | A | #VALUE! | #VALUE!
982 | PP | GRT-CC03-P0UZA-175423 | 175423 | [Structure for Transport, Trafic & Other Purpose] Thermal Barrier Cross Section | FA | 2017-07-14 | 2017-08-13 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 0 | 2017-08-04 | N.A | FC | 0 | A | #VALUE! | #VALUE!
983 | PP | GRT-CC03-P0UZA-175424(1OF2) | 175424 | [Structure for Transport, Trafic & Other Purpose] Thermal Barrier Pile Cap, Plan, Long Section and Detail | FA | 2017-02-28 | 2017-03-30 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 0 | 2017-08-04 | N.A | FC | 0 | A | #VALUE! | #VALUE!
984 | PP | GRT-CC03-P0UZA-175424(2OF2) | 175424 | [Structure for Transport, Trafic & Other Purpose] Thermal Barrier Pile Cap Rebar Arrangement and Section | FA | 2017-02-28 | 2017-03-30 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 0 | 2017-08-04 | N.A | FC | 0 | A | #VALUE! | #VALUE!
985 | PP | GRT-CC03-P0UZA-175425 | 175425 | [Structure for Transport, Trafic & Other Purpose] Local Foundation and Pipe Sleeper Foundation Plan and Detail (1/8) | FA | 2017-07-20 | 2017-03-30 | 2019-05-24 | DRM_22-24MAY2019 (DCR 0042) | FC | 1 | 2019-05-24 | DRM_22-24MAY2019 (DCR 0042) | FC | 1 | A | #VALUE! | #VALUE!
986 | PP | GRT-CC03-P0UZA-175426 | 175426 | [Structure for Transport, Trafic & Other Purpose] Local Foundation and Pipe Sleeper Foundation Plan | FA | 2017-07-20 | 2017-03-30 | 2019-05-24 | DRM_22-24MAY2019 (DCR 0042) | FC | 1 | 2019-05-24 | DRM_22-24MAY2019 (DCR 0042) | FC | 1 | A | #VALUE! | #VALUE!
987 | PP | GRT-CC03-P0UZA-175427 | 175427 | [Structure for Transport, Trafic & Other Purpose] Local Foundation and Pipe Sleeper Foundation Plan | FA | 2017-07-20 | 2017-03-30 | 2017-11-22 | GRT-PP-IP-DT-170334 | FC | 0 | 2017-11-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
988 | PP | GRT-CC03-P0UZA-175428 | 175428 | [Structure for Transport, Trafic & Other Purpose] Local Foundation and Pipe Sleeper Foundation Plan | FA | 2017-07-20 | 2017-03-30 | 2017-11-22 | GRT-PP-IP-DT-170334 | FC | 0 | 2017-11-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
989 | PP | GRT-CC07-P0UZA-175429 | 175429 | [Structure for Transport, Trafic & Other Purpose] Local Foundation and Pipe Sleeper Calculation Sheet | FA | 2017-07-30 | 2017-08-19 | 2017-08-18 | GRT-PP-IP-DT-170184 | FC | 0 | 2017-08-22 | 022.001/C.1.2.17.01/E04/PLNE/VIII/2017 | FA | A | B | #VALUE! | #VALUE!
990 | PP | GRT-CC07-P0UZA-175430 | 175430 | [Structure for Transport, Trafic & Other Purpose] CALCULATION SHEET FOR LOCAL FOUNDATION AND PIPE SLEEPER | FA | 2017-07-30 | 2017-08-19 | 2017-11-22 | GRT-PP-IP-DT-170334 | FC | 0 | 2017-11-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
991 | PP | GRT-CC09-P0UZA-175447 | 175447 | [Structure for Transport, Trafic & Other Purpose] Calculation Sheet for Piperack Structure | FA | 2017-07-30 | 2017-08-29 | 2017-08-22 | GRT-PP-IP-DT-170190 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
992 | PP | GRT-CC09-P0UZA-175448(1OF2) | 175448 | [Structure for Transport, Trafic & Other Purpose] Pipe Rack Foundation Plan & Grade Beam Schedule | FA | 2017-07-30 | 2017-08-29 | 2017-08-22 | GRT-PP-IP-DT-170190 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
993 | PP | GRT-CC09-P0UZA-175448(2OF2) | 175448 | [Structure for Transport, Trafic & Other Purpose] Pipe Rack Foundation Detail | FA | 2017-07-30 | 2017-08-29 | 2017-08-22 | GRT-PP-IP-DT-170190 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
994 | PP | GRT-CC09-P0UZA-175449(1OF5) | 175449 | PIPERACK STEEL STRUCTURE COLUMN ARRANGEMENT & MEMBER SCHEDULE | FA | 2017-07-30 | 2017-08-29 | 2019-08-15 | GRT-PP-IP-DT-191312 (DCR 00049) | FC | 1 | 2019-08-22 | 045/061/GRT/UPR/2019 | FC | 1 | B | #VALUE! | #VALUE!
995 | PP | GRT-CC09-P0UZA-175449(2OF5) | 175449 | PIPERACK STEEL STRUCTURE FRAMING PLAN EL. + 10.604 (T.O.S) | FA | 2017-07-30 | 2017-08-29 | 2017-08-22 | GRT-PP-IP-DT-170190 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
996 | PP | GRT-CC09-P0UZA-175449(3OF5) | 175449 | PIPERACK STEEL STRUCTURE FRAMING PLAN EL. + 14.604 (T.O.S) | FA | 2017-07-30 | 2017-08-29 | 2017-08-22 | GRT-PP-IP-DT-170190 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
997 | PP | GRT-CC09-P0UZA-175449(4OF5) | 175449 | PIPERACK STEEL STRUCTURE FRAMING PLAN EL. + 15.604 (T.O.S) | FA | 2017-07-30 | 2017-08-29 | 2017-08-22 | GRT-PP-IP-DT-170190 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
998 | PP | GRT-CC09-P0UZA-175449(5OF5) | 175449 | PIPERACK STEEL STRUCTURE FRAMING PLAN EL. + 17.304 (T.O.S) | FA | 2017-07-30 | 2017-08-29 | 2017-08-22 | GRT-PP-IP-DT-170190 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
999 | PP | GRT-CC09-P0UZA-175450(1OF3) | 175450 | PIPE RACK STEEL STRUCTURE PLAN EL. +19.004(T.O.S) & FRAMING ELEVATION LINE | FA | 2017-05-01 | 2017-05-31 | 2017-08-22 | GRT-PP-IP-DT-170190 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1000 | PP | GRT-CC09-P0UZA-175450(2OF3) | 175450 | PIPE RACK STEEL STRUCTURE ELEVATION LINE SAD -5 & SAD-6 | FA | 2017-05-01 | 2017-05-31 | 2019-09-13 | GRT-PP-IP-DT-191376 (DCR 00050) | FC | 1 | 2019-09-27 | 053/061/GRT/UPR/2019 |  | 1 | A | #VALUE! | #VALUE!
1001 | PP | GRT-CC09-P0UZA-175450(3OF3) | 175450 | PIPE RACK STEEL STRUCTURE ELEVATION LINE S8-A & S8-B | FA | 2017-05-01 | 2017-05-31 | 2019-08-15 | GRT-PP-IP-DT-191312 (DCR 00049) | FC | 1 | 2019-08-22 | 045/061/GRT/UPR/2019 | FC | 1 | B | #VALUE! | #VALUE!
1002 | PP | GRT-CA06-P0UGD-175351 | 175351 | Calculation Sheet for Water Treatment Plant Building Structure and Foundation | FA | 2017-06-05 | 2017-07-05 | 2017-09-04 | GRT-PP-IP-DT-170206 | FC | 0 | 2017-09-04 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1003 | PP | GRT-CA07-P0ZEN-179029 | 179029 | Study Thermal Barrier and Sedimentation | FA | 2017-06-05 | 2017-07-05 | 2017-06-19 | GRT-PP-IP-DT-170123 | FC | 1 | 2017-06-22 | 0022.001/C.1.2.17.01/E04/PLNE/VI/2017 | FC | 1 | I | #VALUE! | #VALUE!
1004 | PP | GRT-CC03-P0UGD-175581 | 175581 | Sump Pit at HRSG Area Foundation Plan, Section and Detail | FA | 2017-10-23 | 2017-10-23 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1005 | PP | GRT-CC07-P0ZEN-175582 | 175582 | Calculation Sheet for Sump Pit | FA | 2017-10-23 | 2017-10-23 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1006 | PP | GRT-CC07-P0UMA-175583 | 175583 | Calculation Sheet for Equipment Foundation on STG Building Grounding Floor | FA | 2017-10-11 | 2017-11-10 | 2017-10-11 | GRT-PP-IP-DT-170264 | FC | 0 | 2017-10-11 | 0017.001/C.1.2.17.01/E04/PLNE/X/2017 | FA | A | A | #VALUE! | #VALUE!
1007 | PP | GRT-CC03-P0UMA-175584 | 175584 | Steam Turbine Building ACW & CCW Foundation Detail | FA | 2017-10-11 | 2017-11-10 | 2017-10-11 | GRT-PP-IP-DT-170264 | FC | 0 | 2017-10-11 | 0017.001/C.1.2.17.01/E04/PLNE/X/2017 | FA | A | A | #VALUE! | #VALUE!
1008 | PP | GRT-CC03-P0UMA-175585 | 175585 | Steam Turbine Building Condenser Vacuum pump & Air Compressore Foundation Detail | FA | 2017-10-11 | 2017-11-10 | 2017-10-11 | GRT-PP-IP-DT-170264 | FC | 0 | 2017-10-11 | 0017.001/C.1.2.17.01/E04/PLNE/X/2017 | FA | A | A | #VALUE! | #VALUE!
1009 | PP | GRT-CC03-P0UMA-175586 | 175586 | Steam Turbine Building Air Dryer & Air Reciver Tank Foundation Detail | FA | 2017-10-11 | 2017-11-10 | 2017-10-11 | GRT-PP-IP-DT-170264 | FC | 0 | 2017-10-11 | 0017.001/C.1.2.17.01/E04/PLNE/X/2017 | FA | A | A | #VALUE! | #VALUE!
1010 | PP | GRT-CC03-P0UMA-175587 | 175587 | Steam Turbine Building HP Feedwater Pump & LP feedwater Pump Foundation Detail | FA | 2017-10-11 | 2017-11-10 | 2017-10-11 | GRT-PP-IP-DT-170264 | FC | 0 | 2017-10-11 | 0017.001/C.1.2.17.01/E04/PLNE/X/2017 | FA | A | A | #VALUE! | #VALUE!
1011 | PP | GRT-CC03-P0UMA-175588 | 175588 | Steam Turbine Building Chemical Dosing System Foundation Detail | FA | 2017-10-11 | 2017-11-10 | 2017-10-11 | GRT-PP-IP-DT-170264 | FC | 0 | 2017-10-11 | 0017.001/C.1.2.17.01/E04/PLNE/X/2017 | FA | A | A | #VALUE! | #VALUE!
1012 | PP | GRT-CC03-P0UMA-175589 | 175589 | Steam Turbine Building Foundation Detail | FA | 2017-10-11 | 2017-11-10 | 2017-10-11 | GRT-PP-IP-DT-170264 | FC | 0 | 2017-10-11 | 0017.001/C.1.2.17.01/E04/PLNE/X/2017 | FA | A | A | #VALUE! | #VALUE!
1013 | PP | GRT-CC03-P0UMA-175590 | 175590 | Steam Turbine Building Foundation Detail | FA | 2017-10-11 | 2017-11-10 | 2017-10-11 | GRT-PP-IP-DT-170264 | FC | 0 | 2017-10-11 | 0017.001/C.1.2.17.01/E04/PLNE/X/2017 | FA | A | B | #VALUE! | #VALUE!
1014 | PP | GRT-CC03-P0UMA-175591 | 175591 | Steam Turbine Building Foundation Detail | FA | 2017-10-11 | 2017-11-10 | 2017-10-11 | GRT-PP-IP-DT-170264 | FC | 0 | 2017-10-11 | 0017.001/C.1.2.17.01/E04/PLNE/X/2017 | FA | A | A | #VALUE! | #VALUE!
1015 | PP | GRT-DN06-P0ZEN-145458 | 145458 | [Piping General] Piping Pressure Test Procedure | FA | 2017-06-05 | 2017-07-05 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1016 | PP | GRT-CC00-P0ZEN-145452 | 145452 | Drawing Index Balance of Plant BOP | FA | 2017-10-09 | 2017-10-09 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1017 | PP | GRT-CC00-P0UMA-145453-1 | 145453 | Piping Layout Drawing Steam Turbine Generator Area | FA | 2017-09-13 | 2017-09-13 | 2017-09-13 | GRT-PP-IP-DT-170218 | FC | 0 | 2017-09-13 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1018 | PP | GRT-CC00-P0UMA-145453-2 | 145453 | Piping Layout Drawing Steam Turbine Generator Area | FA | 2017-09-13 | 2017-09-13 | 2017-09-13 | GRT-PP-IP-DT-170218 | FC | 0 | 2017-09-13 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1019 | PP | GRT-CC00-P1UHA-145454 | 145454 | Piping Layout Drawing for HRSG Area | FA | 2017-10-19 | 2017-10-19 | 2017-10-19 | GRT-PP-IP-DT-170277 | FC | 0 | 2017-10-23 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1020 | PP | GRT-YT001-P0ZEN-145626 | 145626 | Data Sheet for Check Valve | FA | 2017-10-16 | 2017-10-16 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 0 | 2017-10-17 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1021 | PP | GRT-YT001-P0ZEN-145427 | 145427 | General Arrangement for Check Valve | FA | 2017-10-16 | 2017-10-16 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 0 | 2017-10-17 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1022 | PP | GRT-YT001-P0ZEN-145628 | 145628 | Data Sheet for Butterfly MOV Valve | FA | 2017-10-16 | 2017-10-16 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 0 | 2017-10-17 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1023 | PP | GRT-YT001-P0ZEN-145548 | 145548 | General Arrangement Butterfly MOV Valve | FA | 2017-11-20 | 2017-11-20 | 2017-11-20 | GRT-PP-IP-DT-170329 | FC | 0 | 2017-11-21 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1024 | PP | GRT-YT001-P0ZEN-145547 | 145547 | Valve Closing Time Calculation Sheet | FA | 2017-10-16 | 2017-10-16 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 0 | 2017-10-17 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1025 | PP | GRT-HM05-P0UGD-125452 | 125452 | HVAC Calculation for Water Treatment Building | FA | 2017-10-04 | 2017-10-04 | 2017-10-04 | GRT-PP-IP-DT-170249 | FC | 0 | 2017-10-04 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1026 | PP | GRT-YD00-P0GAD-125624 | 125624 | General Arrangement Circulating Water Pump | FA | 2017-11-20 | 2017-11-20 | 2017-11-20 | GRT-PP-IP-DT-170329 | FC | 0 | 2017-11-21 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1027 | PP | GRT-FF01-P0SGC-125440 | 125440 | Water Spray Layout for Transformer | FI | 2017-11-28 | 2017-12-28 | 2019-06-28 | GRT-PP-IP-DT-191236 (DCR 00043) | FC | 0DCR1 | 2019-07-19 | 040/061/GRT/UPR/2019 |  | 0DCR1 | B | #VALUE! | #VALUE!
1028 | PP | GRT-FF03-P0SGM-125442 | 125442 | Fire Suppression/FM/200 Layout | FI | 2017-11-28 | 2017-12-28 | 2017-11-28 | GRT-PP-IP-DT-170342 | FI | A | 2017-12-22 | 0008.001/C.1.2.17.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1029 | PP | GRT-FF04-P0SGM-125443 | 125443 | Fire Suppression/FM/200 Isometric | FI | 2017-11-28 | 2017-12-28 | 2017-11-28 | GRT-PP-IP-DT-170342 | FI | A | 2017-12-22 | 0008.001/C.1.2.17.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1030 | PP | GRT-FF04-P0SGM-125445 | 125445 | Technical Data Sheet FM200 | FI | 2017-11-28 | 2017-12-28 | 2017-11-28 | GRT-PP-IP-DT-170342 | FI | A | 2017-12-22 | 0008.001/C.1.2.17.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1031 | PP | GRT-XW03-P0PAC-115135 | 115135 | [Circulating Water Pump] Process calculation for sea water for closed cooling system booster pump | FA | 2017-02-07 | 2017-03-09 | 2017-09-25 | GRT-PP-IP-DT-170239 | FC | 0 | 2017-09-25 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1032 | PP | GRT-XG02-P0UGD-115469-1 | 115469 | P & ID For Waste Water Transfer System ( 1 of 2 ) | FA | 2017-06-12 | 2017-07-12 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 0 | 2017-10-17 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1033 | PP | GRT-XG02-P0UGD-115469-2 | 115469 | P & ID For Waste Water Transfer System ( 2 of 2 ) | FA | 2017-06-12 | 2017-07-12 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 0 | 2017-10-17 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1034 | PP | GRT-XW03-P1UHA-115456 | 115456 | [WTP] Process calculation for blowdown transfer pump | FA | 2017-08-18 | 2017-08-18 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1035 | PP | GRT-YT01-P1UHA-115457 | 115457 | [WTP] Process data sheet for blowdown transfer pump | FA | 2017-08-18 | 2017-08-18 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1036 | PP | GRTH-YR01-P0ZEN-115017 | 115017 | Procedure for Hazop Study | FI | 2017-06-09 | 2017-07-09 | 2017-06-09 | GRT-PP-IP-DT-170117 | FI | A | 2017-06-16 | 0016.001/C.1.2.17.01/E04/PLNE/VI/2017 | FI | A | I | #VALUE! | #VALUE!
1037 | PP | GRTH-YR01-P0ZEN-115471 | 115471 | Hazop Study Report | FI | 2017-06-12 | 2017-07-12 | 2017-06-09 | GRT-PP-IP-DT-170117 | FI | A | 2017-06-16 | 0016.001/C.1.2.17.01/E04/PLNE/VI/2017 | FI | A | I | #VALUE! | #VALUE!
1038 | PP | GRT-DC01-P0GDN-125913 | 125913 | Data Sheet Sea Water Booster Pump | FI | 2017-09-14 | 2017-10-14 | 2017-09-14 | GRT-PP-IP-DT-170225 | FI | B | 2017-09-20 | 0020.001/C.1.2.17.01/E04/PLNE/IX/2017 | FI | B | A | #VALUE! | #VALUE!
1039 | PP | GRT-DC01-P0GDN-125914 | 125914 | Data Sheet Sea Water Strainer | FI | 2017-09-14 | 2017-10-14 | 2017-09-14 | GRT-PP-IP-DT-170225 | FI | B | 2017-09-20 | 0020.001/C.1.2.17.01/E04/PLNE/IX/2017 | FI | B | A | #VALUE! | #VALUE!
1040 | PP | GRT-DC01-P0GDN-125915 | 125915 | Data Sheet Electrolyzer | FI | 2017-09-14 | 2017-10-14 | 2017-09-14 | GRT-PP-IP-DT-170225 | FI | B | 2017-09-20 | 0020.001/C.1.2.17.01/E04/PLNE/IX/2017 | FI | B | A | #VALUE! | #VALUE!
1041 | PP | GRT-DC01-P0GDN-125916 | 125916 | Data Sheet Acid Cleaning Pump | FI | 2017-09-14 | 2017-10-14 | 2017-09-14 | GRT-PP-IP-DT-170225 | FI | B | 2017-09-20 | 0020.001/C.1.2.17.01/E04/PLNE/IX/2017 | FI | B | A | #VALUE! | #VALUE!
1042 | PP | GRT-DC01-P0GDN-125917 | 125917 | Data Sheet Dilunation air Blower | FI | 2017-09-14 | 2017-10-14 | 2017-09-14 | GRT-PP-IP-DT-170225 | FI | B | 2017-09-20 | 0020.001/C.1.2.17.01/E04/PLNE/IX/2017 | FI | B | A | #VALUE! | #VALUE!
1043 | PP | GRT-DC01-P0GDN-125918 | 125918 | Data Sheet Continuos Dosing Pump | FI | 2017-09-14 | 2017-10-14 | 2017-09-14 | GRT-PP-IP-DT-170225 | FI | B | 2017-09-20 | 0020.001/C.1.2.17.01/E04/PLNE/IX/2017 | FI | B | A | #VALUE! | #VALUE!
1044 | PP | GRT-DC01-P0GDN-125919 | 125919 | Data Sheet Shock DosingPump | FI | 2017-09-14 | 2017-10-14 | 2017-09-14 | GRT-PP-IP-DT-170225 | FI | B | 2017-09-20 | 0020.001/C.1.2.17.01/E04/PLNE/IX/2017 | FI | B | A | #VALUE! | #VALUE!
1045 | PP | GRT-YT02-P0GD-165921 | 165921 | Data sheet Pressure Indicator | FI | 2017-07-21 | 2017-08-20 | 2017-07-21 | GRT-PP-IP-DT-170149 | FI | A | 2017-08-24 | 0024.001/C.1.2.17.01/E04/PLNE/VIII/2017 | FI | A | A | #VALUE! | #VALUE!
1046 | PP | GRT-YT02-P0GD-165922 | 165922 | Data Sheet Flow Transmitter | FI | 2017-07-21 | 2017-08-20 | 2017-07-21 | GRT-PP-IP-DT-170149 | FI | A | 2017-08-24 | 0024.001/C.1.2.17.01/E04/PLNE/VIII/2017 | FI | A | A | #VALUE! | #VALUE!
1047 | PP | GRT-YT02-P0GD-165923 | 165923 | Data Sheet Level Transmitter | FI | 2017-07-21 | 2017-08-20 | 2017-07-21 | GRT-PP-IP-DT-170149 | FI | A | 2017-08-24 | 0024.001/C.1.2.17.01/E04/PLNE/VIII/2017 | FI | A | A | #VALUE! | #VALUE!
1048 | PP | GRT-YT02-P0GD-165924 | 165924 | Data sheet Clorination Analyzer | FI | 2017-07-21 | 2017-08-20 | 2017-07-21 | GRT-PP-IP-DT-170149 | FI | A | 2017-08-24 | 0024.001/C.1.2.17.01/E04/PLNE/VIII/2017 | FI | A | A | #VALUE! | #VALUE!
1049 | PP | GRT-YT02-P0GD-165925 | 165925 | Data Sheet Pressure Switch | FI | 2017-07-21 | 2017-08-20 | 2017-07-21 | GRT-PP-IP-DT-170149 | FI | A | 2017-08-24 | 0024.001/C.1.2.17.01/E04/PLNE/VIII/2017 | FI | A | A | #VALUE! | #VALUE!
1050 | PP | GRT-YT02-P0GD-165926 | 165926 | Data Sheet Pressure Diffrential | FI | 2017-07-21 | 2017-08-20 | 2017-07-21 | GRT-PP-IP-DT-170149 | FI | A | 2017-08-24 | 0024.001/C.1.2.17.01/E04/PLNE/VIII/2017 | FI | A | A | #VALUE! | #VALUE!
1051 | PP | GRT-YT02-P0GD-165927 | 165927 | Data Sheet Flow Indicator | FI | 2017-07-21 | 2017-08-20 | 2017-07-21 | GRT-PP-IP-DT-170149 | FI | A | 2017-08-24 | 0024.001/C.1.2.17.01/E04/PLNE/VIII/2017 | FI | A | A | #VALUE! | #VALUE!
1052 | PP | GRT-YT02-P0GD-165928 | 165928 | Data Sheet Level Switch Electrochlorination | FI | 2017-09-15 | 2017-10-15 | 2017-09-15 | GRT-PP-IP-DT-170227 | FI | B | 2017-10-03 | 0003.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | B | A | #VALUE! | #VALUE!
1053 | PP | GRT-YT02-P0GD-165929 | 165929 | Data Sheet Temperatur Transmitter | FI | 2017-07-21 | 2017-08-20 | 2017-07-21 | GRT-PP-IP-DT-170149 | FI | A | 2017-08-24 | 0024.001/C.1.2.17.01/E04/PLNE/VIII/2017 | FI | A | A | #VALUE! | #VALUE!
1054 | PP | GRT-CC08-P0GAC-135930 | 135930 | Equipment Lay out | FI | 2017-09-14 | 2017-10-14 | 2019-04-25 | GRT-PP-IP-DT-191151 | FI | 0 | 2019-05-09 | 029/061/GRT/UPR/2019 | FI | 0 | A | #VALUE! | #VALUE!
1055 | PP | GRT-XB02-P0GAC-135931 | 135931 | Foundation Layout ELECTROCHLORINATION | FI | 2017-07-21 | 2017-08-20 | 2018-08-30 | GRT-PP-IP-DT-180752 (DCR 00010) | FC | 1 | 2018-09-14 | 14.006/E04/PLNE/IX/2018 |  | 1 | A | #VALUE! | #VALUE!
1056 | PP | GRT-XG07-P0GAC-135936 | 135936 | PFD | FI | 2017-07-21 | 2017-08-20 | 2019-11-29 | MINI DRM 28-29NOV19 | FC | 0 | 2019-11-29 | MOM MINI DRM 28-29NOV19 | FC | 0 | A | #VALUE! | #VALUE!
1057 | PP | GRT-XG02-P0GAC-135937 | 135937 | P & ID | FI | 2017-10-13 | 2017-11-12 | 2019-03-15 | GRT-PP-IP-DT-191080 (DCR 00038) | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1058 | PP | GRT-DC01-P0LDF-125815 | 125815 | DATA SHEET MIXED BED FEED PUMP | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A | #VALUE! | #VALUE!
1059 | PP | GRT-DC01-P0LDH-125816 | 125816 | DATA SHEET AIR BLOWER | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A | #VALUE! | #VALUE!
1060 | PP | GRT-DC01-P0LDP-125817 | 125817 | DATA SHEET REGENERATION PUMP | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A | #VALUE! | #VALUE!
1061 | PP | GRT-DC01-P0LDN-125818 | 125818 | DATA SHEET ACID DOSING PUMP FOR NEUTRALIZING SYSTEM | FI | 2017-10-13 | 2017-11-12 | 2017-10-13 | GRT-PP-IP-DT-170268 | FI | D | 2017-10-19 | 0019.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | D | A | #VALUE! | #VALUE!
1062 | PP | GRT-DC01-P0LDN-125819 | 125819 | DATA SHEET CAUSTIC DOSING PUMP FOR NUTRALIZING SYSTEM | FI | 2017-10-13 | 2017-11-12 | 2017-10-13 | GRT-PP-IP-DT-170268 | FI | D | 2017-10-19 | 0019.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | D | A | #VALUE! | #VALUE!
1063 | PP | GRT-DC01-P0LDR-125820 | 125820 | DATA SHEET NEUTRALIZATION DISCHARGE PUMP | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A | #VALUE! | #VALUE!
1064 | PP | GRT-YT02-P0LD-165822 | 165822 | DATA SHEET PRESSURE INDICATOR | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A | #VALUE! | #VALUE!
1065 | PP | GRT-YT02-P0LD-165823 | 165823 | DATA SHEET FLOW TRANSMITTER | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A | #VALUE! | #VALUE!
1066 | PP | GRT-YT02-P0LD-165824 | 165824 | DATA SHEET PH TRANSMITTER | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A | #VALUE! | #VALUE!
1067 | PP | GRT-YT02-P0LD-165825 | 165825 | DATA SHEET CONDUCTIVITY TRANSMITTER | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A | #VALUE! | #VALUE!
1068 | PP | GRT-YT02-P0LD-165826 | 165826 | DATA SHEET LEVEL SWITCH WTP MIXED BED | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A | #VALUE! | #VALUE!
1069 | PP | GRT-YT02-P0LD-165827 | 165827 | DATA SHEET PRESSURE SWITCH | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A | #VALUE! | #VALUE!
1070 | PP | GRT-YT02-P0LD-165828 | 165828 | DATA SHEET FLOW INDICATOR | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A | #VALUE! | #VALUE!
1071 | PP | GRT-YT02-P0LD-165829 | 165829 | DATA SHEET PRESSURE DIFFERENTIAL SWITCH | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A | #VALUE! | #VALUE!
1072 | PP | GRT-XK58-P0GCK-125830 | 125830 | GENERAL ARRANGEMENT ACID METERING TANK | FI | 2017-09-14 | 2017-10-14 | 2017-09-14 | GRT-PP-IP-DT-170225 | FI | B | 2017-09-20 | 0020.001/C.1.2.17.01/E04/PLNE/IX/2017 | FI | B | A | #VALUE! | #VALUE!
1073 | PP | GRT-XK58-P0GCK-125840 | 125840 | GENERAL ARRANGEMENT NAME PLATE OF TANK | FI | 2017-09-14 | 2017-10-14 | 2017-09-14 | GRT-PP-IP-DT-170225 | FI | B | 2017-09-20 | 0020.001/C.1.2.17.01/E04/PLNE/IX/2017 | FI | B | A | #VALUE! | #VALUE!
1074 | PP | GRT-CC08-P0GCK-135834 | 135834 | EQUIPMENT LAYOUT | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A | #VALUE! | #VALUE!
1075 | PP | GRT-XB02-P0GCK-135835 | 135835 | FOUNDATION LAYOUT | FI | 2017-07-21 | 2017-08-20 | 2017-07-21 | GRT-PP-IP-DT-170149 | FI | A | 2017-08-03 | 0003.001/C.1.2.17.01/E04/PLNE/VIII/2017 | FI | A | I | #VALUE! | #VALUE!
1076 | PP | GRT-XG02-P0GCK-135841 | 135841 | P & ID Mixed BED System | FI | 2017-10-19 | 2017-11-18 | 2019-03-04 | GRT-PP-IP-DT-191030 | FC | 1 | 2019-03-13 | 019/061/GRT/UPR/2019 | FC | 1 | B | #VALUE! | #VALUE!
1077 | PP | GRT-CC07-P0LD-135842 | 135842 | MASS BALANCE Mixed BED System | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A | #VALUE! | #VALUE!
1078 | PP | GRT-YL25-P0LD-165852 | 165852 | MODBUST LIST | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A | #VALUE! | #VALUE!
1079 | PP | GRT-XM01-P0LD-195856 | 195856 | CONTROL PHILOSOPHY | FA | 2017-12-06 | 2018-01-05 | 2018-05-02 | GRT-PP-IP-DT-180561 | FC | 4 |  | 2018-05-18 | FC | 4 | A | #VALUE! | #VALUE!
1080 | PP | GRT-DC01-P0GD-125920 | 125920 | Data Sheet Rectifier | FA | 2017-11-27 | 2017-12-27 | 2019-11-29 | MINI DRM 28-29NOV19 | FC | 0 | 2019-11-29 | MOM MINI DRM 28-29NOV19 | FC | 0 | A | #VALUE! | #VALUE!
1081 | PP | GRT-YL01-P0ZEN-165462 | 165462 | DCS IO List for Electrical Interface System | FA | 2017-10-20 | 2017-08-20 | 2017-10-20 | GRT-PP-IP-DT-170280 | FC | 0 | 2017-10-23 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1082 | PP | GRT-YL01-P0ZEN-165463 | 165463 | DCS IO List for LDC Interface | FA | 2017-10-20 | 2017-08-20 | 2019-03-15 | GRT-PP-IP-DT-191080 (DCR 00036) | FC | 2 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 2 | A | #VALUE! | #VALUE!
1083 | PP | GRT-YL01-P0ZEN-165203 | 165203 | IO List for Package Equipment | FA | 2017-11-21 | 2017-11-21 | 2017-11-21 | GRT-PP-IP-DT-170332 | FC | 0 | 2017-11-21 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1084 | PP | GRT-CV03-P0UGD-165559 | 165559 | Instrument Data Sheet for Waste Water Transfer System | FA | 2017-08-07 | 2017-08-07 | 2017-08-07 | GRT-PP-IP-DT-170172 | FC | 0 | 2017-08-07 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1085 | PP | GRT-YL01-P0UGD-165558 | 165558 | DCS IO List for Waste Water Transfer System | FA | 2017-09-08 | 2017-09-08 | 2017-09-08 | GRT-PP-IP-DT-170215 | FC | 0 | 2017-09-08 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1086 | PP | GRT-YD00-P0UGD-165560 | 165560 | Instrument Loscation Plant Layout for Waste Water Transfer System | FA | 2017-09-28 | 2017-09-28 | 2017-09-28 | GRT-PP-IP-DT-170244 | FC | 0 | 2017-09-28 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1087 | PP | GRT-YS02-P0ZEN-165568 | 165568 | Instrument Termination Dagaram for Waste Water Transfer System | FA | 2017-09-20 | 2017-09-20 | 2017-09-20 | GRT-PP-IP-DT-170232 | FC | 0 | 2017-09-20 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1088 | PP | GRT-YF00-P0ZEN-165568 | 165568 | Instrument Control Loop for Sea Water Intake System | FA | 2017-09-20 | 2017-09-20 | 2019-01-16 | GRT-PP-IP-DT-190939 | FC | 2 | 2019-02-01 | 006/061/GRT/UPR/2019 | FC | 2 | A | #VALUE! | #VALUE!
1089 | PP | GRT-YF00-P0ZEN-165569 | 165569 | Instrument Control Logic for Circulating Sea Water Cooling System | FA | 2017-11-20 | 2017-11-20 | 2017-11-20 | GRT-PP-IP-DT-170329 | FC | 0 | 2017-11-21 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1090 | PP | GRT-YF00-P0ZEN-165570 | 165570 | Instrument Control Logic for Raw Water System | FA | 2017-10-24 | 2017-10-24 | 2017-10-24 | GRT-PP-IP-DT-170286 | FC | 0 | 2017-10-25 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1091 | PP | GRT-YF00-P0ZEN-165571 | 165571 | Instrument Control loop for Raw Water System | FA | 2017-10-24 | 2017-10-24 | 2017-10-24 | GRT-PP-IP-DT-170286 | FC | 0 | 2017-10-25 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1092 | PP | GRT-YF00-P0ZEN-165572 | 165572 | Instrument Control Logic for Demin Make up System | FA | 2017-12-12 | 2017-12-12 | 2017-12-12 | GRT-PP-IP-DT-170355 | FC | 0 | 2017-12-13 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1093 | PP | GRT-YF00-P0ZEN-165573 | 165573 | Instrument Control Loop for Demin Make up System | FA | 2017-12-12 | 2017-12-12 | 2017-12-12 | GRT-PP-IP-DT-170355 | FC | 0 | 2017-12-13 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1094 | PP | GRT-YF00-P0ZEN-165574 | 165574 | INSTRUMENT CONTROL LOGIC FOR AUXILIARY SERVICE WATER SYSTEM | FA | 2017-11-13 | 2017-12-13 | 2018-02-21 | GRT-PP-IP-DT-180425 | FC | 1 | 2018-02-23 | Comment Sheet IP | FC | 1 | A | #VALUE! | #VALUE!
1095 | PP | GRT-YF00-P0ZEN-165575 | 165575 | Instrument Control Logic for Service Water System | FA | 2017-11-03 | 2017-12-03 | 2018-02-21 | GRT-PP-IP-DT-180425 | FC | 0 | 2018-02-23 | Comment Sheet IP | FC | 0 | A | #VALUE! | #VALUE!
1096 | PP | GRT-YF00-P0ZEN-165576 | 165576 | Instrument Control Loop for Waste water Transfer System | FA | 2017-10-24 | 2017-10-24 | 2017-10-24 | GRT-PP-IP-DT-170286 | FC | 0 | 2017-10-25 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1097 | PP | GRT-YF00-P0ZEN-165577 | 165577 | Instrument Control Loop for Waste water Transfer System | FA | 2017-10-24 | 2017-10-24 | 2017-10-24 | GRT-PP-IP-DT-170286 | FC | 0 | 2017-10-25 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1098 | PP | GRT-YF00-P0ZEN-165578 | 165578 | Instrument Control Loop for Electrical | FA | 2017-11-03 | 2017-11-03 | 2017-11-03 | GRT-PP-IP-DT-170306 | FC | 0 | 2017-11-03 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1099 | PP | GRT-YF00-P0ZEN-165579 | 165579 | Instrument Control Logic for Electrical System | FA | 2017-11-03 | 2017-11-03 | 2020-05-11 | GRT-PP-IP-DT-201589 (EMAIL) | FC | 1 |  |  | FC | 0 | A | #VALUE! | #VALUE!
1100 | PP | GRT-YF00-P0ZEN-165580 | 165580 | Instrument Control Loop for Condenser Circulating Sea Water Cooling System | FA | 2017-12-12 | 2017-12-12 | 2017-12-12 | GRT-PP-IP-DT-170355 | FC | 0 | 2017-12-13 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1101 | PP | GRT-YQ05-P0BYA-165651 | 165651 | DCS System Alarm Diagram | FI | 2017-10-26 | 2017-11-25 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | B | #VALUE! | #VALUE!
1102 | PP | GRT-YD07-P0BYA-165652 | 165652 | DCS Input / Output Signal List of DAS | FI | 2017-10-26 | 2017-11-25 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | B | #VALUE! | #VALUE!
1103 | PP | GRT-YD07-P0BYA-165653 | 165653 | DCS Input / Output Signal List of GTC | FI | 2017-10-26 | 2017-11-25 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | B | #VALUE! | #VALUE!
1104 | PP | GRT-YD07-P0BYA-165654 | 165654 | DCS Input / Output Signal List of GWC | FI | 2017-10-26 | 2017-11-25 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | B | #VALUE! | #VALUE!
1105 | PP | GRT-YD07-P0BYA-165655 | 165655 | DCS Input / Output Signal List of SRS | FI | 2017-10-26 | 2017-11-25 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | A | #VALUE! | #VALUE!
1106 | PP | GRT-YD07-P0BYA-165671 | 165671 | DCS Input / Output Signal List of H/W | FI | 2017-10-26 | 2017-11-25 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | A | #VALUE! | #VALUE!
1107 | PP | GRT-YS02-P0BYA-165643 | 165643 | DCS Lan Configuration | FI | 2017-10-31 | 2017-11-30 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | B | #VALUE! | #VALUE!
1108 | PP | GRT-DC01-P0BYA-165644 | 165644 | DCS Hardware Specification | FI | 2017-11-17 | 2017-12-19 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2017-11-15 | 0015.001/C.1.2.17.01/E04/PLNE/XI/2017 | FC | 0 | A | #VALUE! | #VALUE!
1109 | PP | GRT-YR00-P0BYA-165645 | 165645 | DCS Software Specification og GTC | FI | 2017-10-31 | 2017-11-30 | 2017-10-31 | GRT-PP-IP-DT-170301 | FI | A | 2017-11-15 | 0015.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | B | #VALUE! | #VALUE!
1110 | PP | GRT-DC01-P0BYA-165646 | 165646 | DCS SRS Specification of GTC | FI | 2017-10-31 | 2017-11-30 | 2017-10-31 | GRT-PP-IP-DT-170301 | FI | A | 2017-11-15 | 0015.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | B | #VALUE! | #VALUE!
1111 | PP | GRT-YR05-P0BYA-165650 | 165650 | DCS Outline Drawing of SRS | FA | 2017-10-31 | 2017-11-30 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FI | 0 | A | #VALUE! | #VALUE!
1112 | PP | GRT-CV03-P0ZEN-165674 | 165674 | Data Sheet for Waste Water Transfer System | FI | 2017-11-17 | 2017-12-17 | 2017-12-19 | GRT-PP-IP-DT-170326 | FI | A | 2017-11-29 | Comment Sheet IP | FI | A | A | #VALUE! | #VALUE!
1113 | PP | GRT-CV03-P0ZEN-165675 | 165675 | Data Sheet for Service Water System | FI | 2017-11-17 | 2017-12-17 | 2017-11-17 | GRT-PP-IP-DT-170326 | FI | A | 2017-11-29 | Comment Sheet IP | FI | A | A | #VALUE! | #VALUE!
1114 | PP | GRT-CV03-P0ZEN-165676 | 165676 | Data Sheet for Raw Water System | FI | 2017-11-17 | 2017-12-17 | 2017-11-17 | GRT-PP-IP-DT-170326 | FI | A | 2017-11-29 | Comment Sheet IP | FI | A | A | #VALUE! | #VALUE!
1115 | PP | GRT-CV03-P0ZEN-165677 | 165677 | Data Sheet for Portable Water System | FI | 2017-11-17 | 2017-12-17 | 2017-11-17 | GRT-PP-IP-DT-170326 | FI | A | 2017-11-29 | Comment Sheet IP | FI | A | A | #VALUE! | #VALUE!
1116 | PP | GRT-CV03-P0ZEN-165678 | 165678 | Data Sheet for Demin Make up Sysytem | FI | 2017-11-17 | 2017-12-17 | 2017-11-17 | GRT-PP-IP-DT-170326 | FI | A | 2017-11-29 | Comment Sheet IP | FI | A | A | #VALUE! | #VALUE!
1117 | PP | GRT-CV03-P0ZEN-165679 | 165679 | Data Sheet for Circulating Water Pump | FI | 2017-11-17 | 2017-12-17 | 2017-11-17 | GRT-PP-IP-DT-170326 | FI | A | 2017-11-29 | Comment Sheet IP | FI | A | A | #VALUE! | #VALUE!
1118 | PP | GRT-YR05-P0BYA-165647 | 165647 | DCS Outline Drawing of DAS | FA | 2017-11-17 | 2017-12-19 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | A | #VALUE! | #VALUE!
1119 | PP | GRT-YR05-P0BYA-165648 | 165648 | DCS Outline Drawing of GTC | FA | 2017-11-17 | 2017-12-19 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | A | #VALUE! | #VALUE!
1120 | PP | GRT-YR05-P0BYA-165649 | 165649 | DCS Outline Drawing of GWC | FA | 2017-11-17 | 2017-12-19 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | A | #VALUE! | #VALUE!
1121 | PP | GRT-YS01-P0BYA-165656 | 165656 | GTCS-Schematic Diagram of DAS | FA | 2017-12-05 | 2017-12-19 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | B | #VALUE! | #VALUE!
1122 | PP | GRT-YS01-P0BYA-165657 | 165657 | GTCS-Schematic Diagram of GTC | FA | 2017-12-05 | 2017-12-19 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | A | #VALUE! | #VALUE!
1123 | PP | GRT-YS01-P0BYA-165668 | 165668 | GTCS-Spare Part List | FA | 2017-12-05 | 2017-12-19 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | A | #VALUE! | #VALUE!
1124 | PP | GRT-YS01-P0BYA-165658 | 165658 | GTCS-Schematic Diagram of GWC | FA | 2017-12-05 | 2017-12-19 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | A | #VALUE! | #VALUE!
1125 | PP | GRT-YS01-P0BYA-165659 | 165659 | GTCS-Schematic Diagram of SRS | FA | 2017-12-05 | 2017-12-19 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | B | #VALUE! | #VALUE!
1126 | PP | GRT-YF02-P0BYA-165673 | 165673 | GTCS-System Configuration for GTC | FA | 2017-12-18 | 2018-01-17 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 1 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 1 | A | #VALUE! | #VALUE!
1127 | PP | GRT-YR02-P0ZEN-156250 | 156250 | 150KV Grati Switchgear Surge Arrester Technical Particular & Guarantee | FA | 2017-10-05 | 2017-10-05 | 2017-10-05 | GRT-PP-IP-DT-170255 | FC | 0 | 2017-10-05 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1128 | PP | GRT-YR02-P0ZEN-156251 | 156251 | 150KV Grati Switchgear Circuit Breaker Technical Particular & Guarantee | FA | 2017-10-05 | 2017-10-05 | 2017-10-05 | GRT-PP-IP-DT-170255 | FC | 0 | 2017-10-05 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1129 | PP | GRT-YR02-P0ZEN-156252 | 156252 | 150KV Grati Switchgear Current Transfoemer Tecnical Particular & Guarantee | FA | 2017-10-05 | 2017-10-05 | 2017-10-05 | GRT-PP-IP-DT-170255 | FC | 0 | 2017-10-05 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1130 | PP | GRT-YR02-P0ZEN-156253 | 156253 | 150KV Grati Switchgear Disconnector Switch Tecnical Particular & Guarantee | FA | 2017-10-05 | 2017-10-05 | 2017-10-05 | GRT-PP-IP-DT-170255 | FC | 0 | 2017-10-05 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1131 | PP | GRT-YR02-P0ZEN-156254 | 156254 | 150KV Grati Switchgear Capacotator Voltage Transformer Tecnical Particular & Guarantee | FA | 2017-10-05 | 2017-10-05 | 2017-10-05 | GRT-PP-IP-DT-170255 | FC | 0 | 2017-10-05 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1132 | PP | GRT-YR02-P0ZEN-156255 | 156255 | 150 KV Grati Switchgear Disconnector Swich Tecnical Particular & Guarantee | FA | 2017-10-05 | 2017-10-05 | 2017-10-05 | GRT-PP-IP-DT-170255 | FC | 0 | 2017-10-05 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1133 | PP | GRT-YR02-P0AT-156106 | 156106 | Technical Specification UAT 15kV | FI | 2017-10-06 | 2017-11-05 | 2017-10-06 | GRT-PP-IP-DT-170256 | FI | A | 2017-10-09 | 0009.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I | #VALUE! | #VALUE!
1134 | PP | GRT-YR02-P0AT-156117 | 156117 | Technical Specification SST 15kV | FI | 2017-10-06 | 2017-11-05 | 2017-10-06 | GRT-PP-IP-DT-170256 | FI | A | 2017-10-09 | 0009.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I | #VALUE! | #VALUE!
1135 | PP | GRT-YD00-P0AT-156128 | 156128 | General Arrangement Drawing 150/15.75 kV – 250 MVA | FI | 2017-10-06 | 2017-11-05 | 2019-09-26 | GRT-PP-IP-DT-191407 (DCR 0039) | FC | 0FCR2 | 2019-09-26 | APPROVED ON SITE (PLN E) | FC | 0FCR2 | A | #VALUE! | #VALUE!
1136 | PP | GRT-XB02-P0AT-156129 | 156129 | Foundation Drawing 150/15.75 kV – 250 MVA Power Transformer | FI | 2017-10-06 | 2017-11-05 | 2017-10-06 | GRT-PP-IP-DT-170256 | FI | A | 2017-10-09 | 0009.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I | #VALUE! | #VALUE!
1137 | PP | GRT-YS01-P0AT-156130 | 156130 | Rating & Schematic Plate 150/15.75 kV – 250 MVA Power Transformer | FI | 2017-10-06 | 2017-11-05 | 2017-10-06 | GRT-PP-IP-DT-170256 | FI | A | 2017-10-09 | 0009.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I | #VALUE! | #VALUE!
1138 | PP | GRT-CC01-P0AT-156131 | 156131 | Oil Piping & Valve Location Plate 150/15.75 kV – 250 MVA Power Transformer | FI | 2017-10-06 | 2017-11-05 | 2017-10-06 | GRT-PP-IP-DT-170256 | FI | A | 2017-10-09 | 0009.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I | #VALUE! | #VALUE!
1139 | PP | GRT-YS01-P0AT-156132 | 156132 | Schematic Diagram of Contorl Cubicle 150/15.75 kV-250 MVA Power Transformer | FI | 2017-10-19 | 2017-11-18 | 2017-10-19 | GRT-PP-IP-DT-170276 | FI | A | 2017-10-23 | 0023.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I | #VALUE! | #VALUE!
1140 | PP | GRT-YS01-P0AT-156133 | 156133 | Schematic Diagram of Remote Control Panel 150/15.75 kV – 250 MVA Power Transformer | FI | 2017-10-06 | 2017-11-05 | 2017-10-06 | GRT-PP-IP-DT-170256 | FI | A | 2017-10-09 | 0009.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I | #VALUE! | #VALUE!
1141 | PP | GRT-XM00-P0AT-156134 | 156134 | Heaviest Part for Transformer Drawing Plate 150/15.75 kV – 250 MVA Power Transformer | FI | 2017-10-06 | 2017-11-05 | 2017-10-06 | GRT-PP-IP-DT-170256 | FI | A | 2017-10-09 | 0009.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I | #VALUE! | #VALUE!
1142 | PP | GRT-YT01-P0AT-156135 | 156135 | Tecnical Specification (TPG) 150/15.75 kV – 250 MVA Power Transformer | FI | 2017-10-06 | 2017-11-05 | 2017-10-06 | GRT-PP-IP-DT-170256 | FI | A | 2017-10-09 | 0009.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I | #VALUE! | #VALUE!
1143 | PP | GRT-YD00-P0AT-156304 | 156304 | General Arrangement Drawing of 1000 KVA | FI | 2017-10-09 | 2017-11-08 | 2017-10-09 | GRT-PP-IP-DT-170260 | FI | A | 2017-10-17 | 0030.001/C.1.2.17.01/E04/PLNE/V/2017 | FI | A | I | #VALUE! | #VALUE!
1144 | PP | GRT-YD00-P0AT-156305 | 156305 | General Arrangement Drawing of 2000 KVA | FI | 2017-10-09 | 2017-11-08 | 2017-10-09 | GRT-PP-IP-DT-170260 | FI | A | 2017-10-17 | 0030.001/C.1.2.17.01/E04/PLNE/V/2017 | FI | A | I | #VALUE! | #VALUE!
1145 | PP | GRT-YD00-P0AT-156306 | 156306 | General Arrangement Drawing of 3000 KVA | FI | 2017-10-09 | 2017-11-08 | 2017-10-09 | GRT-PP-IP-DT-170260 | FI | A | 2017-10-17 | 0030.001/C.1.2.17.01/E04/PLNE/V/2017 | FI | A | I | #VALUE! | #VALUE!
1146 | PP | GRT-YD00-P0AT-156107 | 156107 | General Arrangement Drawing of Unit Auxiliary Transformer 25MVA | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170274 | FI | A | 2017-10-23 | 0023.001/C.1.2.15.01/E04/PLNE/X/2017 | FI | A | I | #VALUE! | #VALUE!
1147 | PP | GRT-YD00-P0AT-156108 | 156108 | Termination Drawing of Auxiliary Transformer 25MVA | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170274 | FI | A | 2017-10-23 | 0023.001/C.1.2.15.01/E04/PLNE/X/2017 | FI | A | I | #VALUE! | #VALUE!
1148 | PP | GRT-YT01-P0AT-156110 | 156110 | Rating Plate UAT | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170274 | FI | A | 2017-10-23 | 0023.001/C.1.2.15.01/E04/PLNE/X/2017 | FI | A | I | #VALUE! | #VALUE!
1149 | PP | GRT-YD00-P0AT-156118 | 156118 | General Arrangement Drawing of Unit Station Service Transformer 25MVA | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170274 | FI | A | 2017-10-23 | 0023.001/C.1.2.15.01/E04/PLNE/X/2017 | FI | A | I | #VALUE! | #VALUE!
1150 | PP | GRT-YD00-P0AT-156119 | 156119 | Termination drawing of Station Service Transformer 25MVA | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170274 | FI | A | 2017-10-23 | 0023.001/C.1.2.15.01/E04/PLNE/X/2017 | FI | A | I | #VALUE! | #VALUE!
1151 | PP | GRT-YT01-P0AT-156121 | 156121 | Rating Plate SST | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170274 | FI | A | 2017-10-23 | 0023.001/C.1.2.15.01/E04/PLNE/X/2017 | FI | A | I | #VALUE! | #VALUE!
1152 | PP | GRT-YS01-P0AT-156111 | 156111 | Layout and Schematic Diagram for Mashalling Kiosk Transformer 25000KVA 15.75/6.3kV | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170274 | FI | A | 2017-10-23 | 0023.001/C.1.2.15.01/E04/PLNE/X/2017 | FI | A | I | #VALUE! | #VALUE!
1153 | PP | GRT-YV02-P0AT-156114 | 156114 | Layout and Schematic Diagram for Remote Tap Charger Control Panel Transformer 25MVA 15.75/6.3kV | FI | 2017-10-18 | 2017-11-17 | 2019-03-21 | MINI DRM_21MAR2019 | FC | 0 | 2019-03-21 | 021/061/GRT/UPR/2019 | FI | 0 | A | #VALUE! | #VALUE!
1154 | PP | GRT-YS01-P0AT-156122 | 156122 | Layout and Schematic Diagram for Mashalling Kiosk Transformer 25000KVA 15.75/6.3kV | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170274 | FI | A | 2017-10-23 | 0023.001/C.1.2.15.01/E04/PLNE/X/2017 | FI | A | I | #VALUE! | #VALUE!
1155 | PP | GRT-YV02-P0AT-156125 | 156125 | Layout and Schematic Diagram for Remote Tap Charger Control Panel Transformer 25MVA 15.75/6.3kV | FI | 2017-10-18 | 2017-11-17 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FI | 0 | B | #VALUE! | #VALUE!
1156 | PP | GRT-YD00-P0AT-156283 | 156283 | Surge Arrester Drawing of Station Service Transformer 25MVA | FI | 2017-10-19 | 2017-11-18 | 2017-10-19 | GRT-PP-IP-DT-170276 | FI | A | 2017-10-23 | 0023.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I | #VALUE! | #VALUE!
1157 | PP | GRT-YD00-P0AT-156284 | 156284 | NGR Drawing SST & UAT | FI | 2017-10-19 | 2017-11-18 | 2017-10-19 | GRT-PP-IP-DT-170276 | FI | A | 2017-10-23 | 0023.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I | #VALUE! | #VALUE!
1158 | PP | GRTBCP-YD00-P0BBA-156003 | 156003 | General Arrangement MV Switchgear 6,3kV | FI | 2017-10-31 | 2017-11-30 | 2017-10-31 | GRT-PP-IP-DT-170301 | FI | A | 2017-11-02 | 0002.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I | #VALUE! | #VALUE!
1159 | PP | GRTBCP-YD00-P0BBA-156006 | 156006 | Data Sheet MV Switchgear 6,3 kV | FI | 2017-10-31 | 2017-11-30 | 2017-10-31 | GRT-PP-IP-DT-170301 | FI | A | 2017-11-02 | 0002.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I | #VALUE! | #VALUE!
1160 | PP | GRT-DP00-P0MJY-156158 | 156158 | Diesel Genset Specification Sheet | FI | 2017-10-31 | 2017-11-30 | 2019-01-15 | GRT-PP-IP-DT-190930 | FC | 3 | 2019-02-06 | 008/061/GRT/UPR/2019 | FC | 3 | B | #VALUE! | #VALUE!
1161 | PP | GRT-XK00-P0EGB-156154 | 156154 | General Arrangement Daily Tank Drawing | FI | 2017-10-31 | 2017-11-30 | 2018-10-26 | GRT-PP-IP-DT-180831 | FC | 1 | 2018-11-06 | Comment Sheet IP | FC | 1 | B | #VALUE! | #VALUE!
1162 | PP | GRT-YK08-P0MJA-156152 | 156152 | General Arrangement Diesel Genset Drawings | FI | 2017-10-31 | 2017-11-30 | 2019-12-11 | GRT-PP-IP-DT-191520 | FC | 2 |  |  | FC | 2 | A | #VALUE! | #VALUE!
1163 | PP | GRT-YT01-P0MKA-156159 | 156159 | Generator Data Sheets | FI | 2017-12-11 | 2018-01-10 | 2018-03-28 | GRT-PP-IP-DT-180498 | FC | 1 | 2018-04-18 | DRM 5 | FC | 1 | A | #VALUE! | #VALUE!
1164 | PP | GRT-YT01-P0MJA-156160 | 156160 | Diesel Engine Data Sheet | FI | 2017-12-11 | 2018-01-10 | 2018-03-28 | GRT-PP-IP-DT-180498 | FC | 1 | 2018-04-18 | DRM 5 | FC | 1 | A | #VALUE! | #VALUE!
1165 | PP | GRT-YD00-P0BAC-156285 | 156285 | GCB General Arrangement Drawing for FKG 1X | FI | 2017-10-31 | 2017-11-30 | 2017-10-31 | GRT-PP-IP-DT-170301 | FI | A | 2017-11-02 | 0002.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I | #VALUE! | #VALUE!
1166 | PP | GRT-YD00-P0BAC-156286 | 156286 | GCB General Arrangement Drawing for FKG 1X | FI | 2017-10-31 | 2017-11-30 | 2017-10-31 | GRT-PP-IP-DT-170301 | FI | A | 2017-11-02 | 0002.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I | #VALUE! | #VALUE!
1167 | PP | GRTBCP-YD00-P0BBA-156004 | 156004 | Single Line Diagram MV Switchgear 6,3 kV | FI | 2017-10-31 | 2017-11-30 | 2017-10-31 | GRT-PP-IP-DT-170301 | FI | A | 2017-11-02 | 0002.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I | #VALUE! | #VALUE!
1168 | PP | GRT-YD00-P0BVC-156357 | 156357 | General Arrangement UPS System | FI | 2017-11-14 | 2017-12-14 | 2017-11-14 | GRT-PP-IP-DT-170317 | FI | A | 2017-11-21 | 0021.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | I | #VALUE! | #VALUE!
1169 | PP | GRT-YD00-P0BRA-156358 | 156358 | General Arrangement AC Distribution Board 400/230V for UPS System | FI | 2017-11-14 | 2017-12-14 | 2017-11-14 | GRT-PP-IP-DT-170317 | FI | A | 2017-11-21 | 0021.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | I | #VALUE! | #VALUE!
1170 | PP | GRT-YD00-P0BTL-156363 | 156363 | General Arrangement DC System | FI | 2017-11-14 | 2017-12-14 | 2017-11-14 | GRT-PP-IP-DT-170317 | FI | A | 2017-11-21 | 0021.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | I | #VALUE! | #VALUE!
1171 | PP | GRT-YD00-P0BVC-156364 | 156364 | General Arrangement DC Distribution Board 220V for DC System | FI | 2017-11-14 | 2017-12-14 | 2017-11-14 | GRT-PP-IP-DT-170317 | FI | A | 2017-11-21 | 0021.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | I | #VALUE! | #VALUE!
1172 | PP | GRT-YD00-P0BFA-156376 | 156376 | General Arrangement NSPB-A | FA | 2017-11-14 | 2017-12-14 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1173 | PP | GRT-YD00-P0BFA-156379 | 156379 | General Arrangement NSPB-B | FI | 2017-11-14 | 2017-12-14 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1174 | PP | GRT-XW03-P0ZEN-156243 | 156243 | Switchgear Steel Structures SA Support H=2. 1M - IB573 | FA | 2017-11-16 | 2017-12-16 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 2 | 2018-11-05 | Comment Sheet IP | FC | 2 | A | #VALUE! | #VALUE!
1175 | PP | GRT-XW03-P0ZEN-156240 | 156240 | Switchgear Steel Structures CB Support IB562 ( GL314 – TYPE F1 ) | FA | 2017-11-16 | 2017-12-16 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 1 | 2018-11-05 | Comment Sheet IP | FC | 1 | A | #VALUE! | #VALUE!
1176 | PP | GRT-XW03-P0ZEN-156179 | 156179 | 150kV Grati, Switchgear Calculation Note Compatibility CT / Protection (exclude GSUT & SST Area) | FA | 2017-11-16 | 2017-12-16 | 2017-12-18 | GRT-PP-IP-DT-170357 | FC(D) | B | 2017-12-22 | 0022.001/C.1.2.17.01/E04/PLNE/XII/2017 | FA | B | A | #VALUE! | #VALUE!
1177 | PP | GRT-XW03-P0ZEN-156190 | 156190 | 150kV Grati, Switchgear Calculation Steel Structures - Gantries | FA | 2017-11-16 | 2017-12-16 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 2 | 2018-11-05 | Comment Sheet IP | FC | 2 | A | #VALUE! | #VALUE!
1178 | PP | GRT-YT01-P0BAA-156304 | 156304 | Technical Data Sheet for 15.75kV IPBD | FI | 2017-10-09 | 2017-11-08 | 2018-04-09 | GRT-PP-IP-DT-180741 | FC | 1 | 2018-10-05 | Comment Sheet IP | FC | 1 | B | #VALUE! | #VALUE!
1179 | PP | GRT-YK10-P0BAA-156305 | 156305 | Standar Sub-assembly Drawing for 15.75kV IPBD | FI | 2017-10-09 | 2017-11-08 | 2018-04-09 | GRT-PP-IP-DT-180741 | FC | 1 | 2018-10-05 | Comment Sheet IP | FC | 1 | B | #VALUE! | #VALUE!
1180 | PP | GRT-YB10-P0BAA-156314 | 156314 | Terminationn Details of 15.75kV IPBD | FI | 2017-12-13 | 2018-01-12 | 2018-09-04 | GRT-PP-IP-DT-180741 | FC | 1 | 2018-10-05 | Comment Sheet IP | FC | 1 | B | #VALUE! | #VALUE!
1181 | PP | GRT-YK08-P0BAA-156316 | 156316 | GA & Wiring Diagram of Pressurisation Cubicle for 15.75kV IPBD | FI | 2017-12-13 | 2018-01-12 | 2018-04-09 | GRT-PP-IP-DT-180741 | FC | 1 | 2018-10-05 | Comment Sheet IP | FC | 1 | B | #VALUE! | #VALUE!
1182 | PP | GRT-YD00-P0BFA-156123 | 156123 | General Arrangement NSPB-1 | FI | 2017-11-17 | 2017-12-17 | 2017-11-17 | GRT-PP-IP-DT-170326 | FI | A | 2018-10-05 | 0021.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | 1 | I | #VALUE! | #VALUE!
1183 | PP | GRT-YD00-P0BFA-156126 | 156126 | General Arrangement NSPB-2 | FI | 2017-11-17 | 2017-12-17 | 2017-11-17 | GRT-PP-IP-DT-170326 | FI | A | 2018-10-05 | 0021.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | 1 | I | #VALUE! | #VALUE!
1184 | PP | GRT-XW03-P0ZEN-156192 | 156192 | 150kV Grati Switchgear Single Line Diagram Diameter | FA | 2017-11-14 | 2017-12-14 | 2018-05-02 | GRT-PP-IP-DT-180561 | FC | 1 | 2018-05-18 | Comment Sheet IP | FC | 1 | A | #VALUE! | #VALUE!
1185 | PP | GRT-VS02-P0BTL-156359 | 156359 | Battery Rack 2000AH for UPS System | FI | 2017-11-24 | 2017-12-24 | 2018-11-08 | GRT-PP-IP-DT-180852 | FC | 2 | 2018-12-13 | Comment Sheet IP | FC | 2 | B | #VALUE! | #VALUE!
1186 | PP | GRT-VS02-P0BTL-156365 | 156365 | Battery Rack 800AH for DC System | FI | 2017-11-24 | 2017-12-24 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 1 | 2018-11-06 | Comment Sheet IP | FC | 1 | B | #VALUE! | #VALUE!
1187 | PP | GRT-XB02-P0BAA-156313 | 156313 | Layout Foundation Detail of 15. 75kV IPBD | FI | 2017-11-24 | 2017-12-24 | 2018-09-04 | GRT-PP-IP-DT-180741 | FC | 1 | 2018-10-05 | Comment Sheet IP | FC | 1 | B | #VALUE! | #VALUE!
1188 | PP | GRT-YD00-P0BFA-156018 | 156018 | General Arrangement LV Switchgear 1 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1189 | PP | GRT-YD00-P0BFB-156023 | 156023 | General Arrangement LV Switchgear 2 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1190 | PP | GRT-YD00-P0BFC-156028 | 156028 | General Arrangement LV Switchgear 3 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1191 | PP | GRT-YD00-P0BFD-156033 | 156033 | General Arrangement LV Switchgear 4 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1192 | PP | GRT-YD00-P0BJA-156038 | 156038 | General Arrangement STG Unit MCC | FI | 2017-11-24 | 2017-12-24 | 2018-02-02 | GRT-PP-IP-DT-180405 | FC | 0 | 2018-02-12 | Comment Sheet IP | FC | 0 | B | #VALUE! | #VALUE!
1193 | PP | GRT-YD00-P0BJA-156043 | 156043 | General Arrangement STG PDB | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1194 | PP | GRT-YD00-P0BJC-156048 | 156048 | General Arrangement HRSG Unit MCC | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1195 | PP | GRT-YD00-P0BJD-156053 | 156053 | General Arrangement LV Switchgear 3 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1196 | PP | GRT-YD00-P0BJE-156058 | 156058 | General Arrangement Valve PDB | FI | 2017-11-24 | 2017-12-24 | 2019-03-21 | MINI DRM_21MAR2019 | FC | 1 | 2019-03-21 | 021/061/GRT/UPR/2019 | FC | 1 | A | #VALUE! | #VALUE!
1197 | PP | GRT-YD00-P0BJF-156063 | 156063 | General Arrangement BOP Essential MCC | FI | 2017-11-24 | 2017-12-24 | 2019-03-21 | MINI DRM_21MAR2019 | FC | 1 | 2019-03-21 | 021/061/GRT/UPR/2019 | FC | 1 | A | #VALUE! | #VALUE!
1198 | PP | GRT-YD00-P0BJG-156068 | 156068 | General Arrangement Space Heater Panel | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1199 | PP | GRT-YD00-P0BJG-156073 | 156073 | General Arrangement BOP Essential PDB | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1200 | PP | GRT-YD00-P0BJJ-156078 | 156078 | General Arrangement Feeder UPS-01 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1201 | PP | GRT-YD00-P0BJK-156083 | 156083 | General Arrangement Feeder UPS-02 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1202 | PP | GRT-YD00-P0BJL-156088 | 156088 | General Arrangement Feeder Normal Lighting | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1203 | PP | GRT-YD00-P0BJN-156093 | 156093 | General Arrangement HVAC | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1204 | PP | GRT-YT01-P0BJP-156315 | 156315 | Data Sheet HRSG PDB-3 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1205 | PP | GRT-YT01-P0BJ0-156315 | 156315 | Data Sheet HRSG PDB-2 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1206 | PP | GRT-YT01-P0BJN-156310 | 156310 | Data Sheet HRSG PDB-1 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1207 | PP | GRT-YT01-P0BJN-156096 | 156096 | Data Sheet Feeder HVAC | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1208 | PP | GRT-YT01-P0BJL-156091 | 156091 | Data Sheet Feeder Normal Lighting | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1209 | PP | GRT-YT01-P0BJK-156086 | 156086 | Data Sheet Feeder UPS-2 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1210 | PP | GRT-YT01-P0BJJ-156081 | 156081 | Data Sheet Feeder UPS-1 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1211 | PP | GRT-YT01-P0BJH-156076 | 156076 | Data Sheet BOP Essensial PDB | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1212 | PP | GRT-YT01-P0BJG-156071 | 156071 | Data Sheet Space Heater Panel | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1213 | PP | GRT-YT01-P0BJF-156066 | 156066 | Data Sheet BOP Essential MCC | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1214 | PP | GRT-YT01-P0BJE-156061 | 156061 | Data Sheet Valve PDB | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1215 | PP | GRT-YT01-P0BJC-156051 | 156051 | Data Sheet HRSG Unit MCC | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1216 | PP | GRT-YT01-P0BJB-156046 | 156046 | Data Sheet STG PDB | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1217 | PP | GRT-YT01-P0BJA-156041 | 156041 | Data Sheet STG Unit MCC | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1218 | PP | GRT-YT01-P0BFD-156036 | 156036 | Data Sheet LV Switchgear 4 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1219 | PP | GRT-YT01-P0BFC-156031 | 156031 | Data Sheet LV Switchgear 3 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1220 | PP | GRT-YT01-P0BFB-156026 | 156026 | Data Sheet LV Switchgear 2 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1221 | PP | GRT-YT01-P0BFA-156021 | 156021 | Data Sheet LV Switchgear 1 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1222 | PP | GRT-YT01-P0BJP-156317 | 156317 | General Arrangement HRSG PDB-3 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1223 | PP | GRT-YT01-P0BJ0-156312 | 156312 | General Arrangement HRSG PDB-2 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1224 | PP | GRT-YT01-P0BJN-156307 | 156307 | General Arrangement HRSG PDB-1 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1225 | PP | GRT-DD00-P0BAA-156306 | 156306 | Type Test Reports for 15.75kV IPBD | FI | 2017-10-09 | 2017-11-08 | 2017-10-09 | GRT-PP-IP-DT-170260 | FI | A | 2017-10-17 | 0030.001/C.1.2.17.01/E04/PLNE/V/2017 | FI | A | I | #VALUE! | #VALUE!
1226 | PP | GRT-DN03-P0BAA-156308 | 156308 | Site Inspection &Test Plan for 15.75kV IPBD | FI | 2017-12-07 | 2018-01-06 | 2017-12-07 | GRT-PP-IP-DT-170353 | FI | A | 2018-01-08 | 0008.001/C.1.2.17.01/E04/PLNE/XII/2017 | FI | A | I | #VALUE! | #VALUE!
1227 | PP | GRT-YB10-P0UBL-156315 | 156315 | Support Structure Detail of 15.75kV IPBD | FI | 2017-11-24 | 2017-12-24 | 2018-04-09 | GRT-PP-IP-DT-180741 | FC | 1 | 2018-10-05 | Comment Sheet IP | FC | 1 | B | #VALUE! | #VALUE!
1228 | PP | GRT-CC03-P0UGD-175466 | 175466 | Raw Water Tank Concrete Structure Foundation Plan, Detail & Schedule | FA | 2017-09-28 | 2017-09-28 | 2017-09-28 | GRT-PP-IP-DT-170244 | FC | 0 | 2017-09-28 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1229 | PP | GRT-CC03-P0UGD-175468 | 175468 | Make up Demin Water Tank Concrete Structure Foundation Plant, Detail & Schedule | FA | 2017-09-05 | 2017-09-05 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1230 | PP | GRT-CC07-P0UGD-175465 | 175465 | Calculation Sheet for Raw Water Tank Foundation | FA | 2017-09-28 | 2017-09-28 | 2017-09-28 | GRT-PP-IP-DT-170244 | FC | 0 | 2017-09-28 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1231 | PP | GRT-CC07-P0UGD-175467 | 175467 | Calculation Sheet for Make –up Demin Water Tank Foundation | FA | 2017-09-05 | 2017-09-05 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1232 | PP | GRT-CC06-P0UMA-175272 | 175272 | Calculation Sheet for Steam Turbine Building Foundation | FA | 2017-04-08 | 2017-05-08 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1233 | PP | GRT-CC00-P0UGD-175395 | 175395 | Fire Fighting Shelter Architectural Plan, View, Section & Finishing Schedule | FA | 2017-08-09 | 2017-08-09 | 2017-08-09 | GRT-PP-IP-DT-170178 | FC | 0 | 2017-08-09 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1234 | PP | GRT-CA01-P0UGD-175563 | 175563 | Water Treatment Plant Concrete Structure Section and Detail | FA | 2017-09-04 | 2017-09-04 | 2017-09-04 | GRT-PP-IP-DT-170206 | FC | 0 | 2017-09-04 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1235 | PP | GRT-CA01-P0UGD-175564 | 175564 | Water Treatment Plant Concrete Structure Section and Detail | FA | 2017-09-04 | 2017-09-04 | 2017-09-04 | GRT-PP-IP-DT-170206 | FC | 0 | 2017-09-04 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1236 | PP | GRT-CC03-P0UBN-175568 | 175568 | Emergency Diesel Generator Concrete Structure Foundation Plan & Detail | FA | 2017-09-13 | 2017-09-13 | 2019-06-28 | GRT-PP-IP-DT-191235 (DCR 00048) | FC | 1 | 2019-07-19 | 040/061/GRT/UPR/2019 |  | 1 | B | #VALUE! | #VALUE!
1237 | PP | GRT-CC07-P0UBN-175569 | 175569 | Calculation Sheet for EDG Foundation | FA | 2017-09-04 | 2017-09-04 | 2017-09-04 | GRT-PP-IP-DT-170206 | FC | 0 | 2017-09-04 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1238 | PP | GRT-CC03-P0UMA-175596 | 175596 | Calculation Sheet for Underground Facility | FA | 2017-11-21 | 2017-12-21 | 2017-11-21 | GRT-PP-IP-DT-170333 | FC | 1 | 2017-11-21 | 0027.001/C.1.2.17.01/E04/PLNE/XI/2017 | FA | B | A | #VALUE! | #VALUE!
1239 | PP | GRT-CC03-P0UMA-175597 | 175597 | Cable Trench and Duct Bank General Layout | FA | 2017-11-21 | 2017-12-21 | 2017-11-21 | GRT-PP-IP-DT-170333 | FC | 1 | 2017-11-27 | 0027.001/C.1.2.17.01/E04/PLNE/XI/2017 | FA | B | A | #VALUE! | #VALUE!
1240 | PP | GRT-CC03-P0UMA-175598 | 175598 | Cable Trench and Duct Bank Lay out Area 1 | FA | 2017-11-21 | 2017-12-21 | 2017-11-21 | GRT-PP-IP-DT-170333 | FC | 1 | 2017-11-27 | 0027.001/C.1.2.17.01/E04/PLNE/XI/2017 | FA | B | A | #VALUE! | #VALUE!
1241 | PP | GRT-CC03-P0UMA-175599 | 175599 | Cable Trench and Duct Bank Lay out Area 2 | FA | 2017-11-21 | 2017-12-21 | 2017-11-21 | GRT-PP-IP-DT-170333 | FC | 1 | 2017-11-27 | 0027.001/C.1.2.17.01/E04/PLNE/XI/2017 | FA | B | A | #VALUE! | #VALUE!
1242 | PP | GRT-CC03-P0UMA-175600 | 175600 | Cable Trench and Duct Bank Lay out Area 3 | FA | 2017-11-21 | 2017-12-21 | 2017-11-21 | GRT-PP-IP-DT-170333 | FC | 1 | 2017-11-27 | 0027.001/C.1.2.17.01/E04/PLNE/XI/2017 | FA | B | A | #VALUE! | #VALUE!
1243 | PP | GRT-CC03-P0UMA-175601 | 175601 | Cable Trench and Duct Bank Detail | FA | 2017-11-21 | 2017-12-21 | 2018-04-07 | GRT-PP-IP-DT-180524 (EMAIL) | FC | 1 | 2018-04-18 | DRM 5 |  | 1 | A | #VALUE! | #VALUE!
1244 | PP | GRT-CC03-P0UMA-175602 | 175602 | Cable Trench and Duct Bank Detail | FA | 2017-11-21 | 2017-12-21 | 2019-01-08 | GRT-PP-IP-DT-190925 (DCR0015) | FC | 1 | 2019-01-22 | 004/061/GRT/UPR/2019 | FC | 1 | B | #VALUE! | #VALUE!
1245 | PP | GRT-CC03-P0UMA-175603 | 175603 | Cable Pit Foundation Detail | FA | 2017-11-21 | 2017-12-21 | 2017-11-21 | GRT-PP-IP-DT-170333 | FC | 1 | 2017-11-27 | 0027.001/C.1.2.17.01/E04/PLNE/XI/2017 | FA | B | A | #VALUE! | #VALUE!
1246 | PP | GRT-CC03-P0UMA-175604 | 175604 | Culvert Detail, Section & Schedule (1/2) | FA | 2017-11-21 | 2017-12-21 | 2017-11-21 | GRT-PP-IP-DT-170333 | FC | 1 | 2017-11-27 | 0027.001/C.1.2.17.01/E04/PLNE/XI/2017 | FA | B | A | #VALUE! | #VALUE!
1247 | PP | GRT-CC03-P0UMA-175605 | 175605 | Culvert Detail, Section & Schedule (2/2) | FA | 2017-11-21 | 2017-12-21 | 2017-11-21 | GRT-PP-IP-DT-170333 | FC | 1 | 2017-11-27 | 0027.001/C.1.2.17.01/E04/PLNE/XI/2017 | FA | B | A | #VALUE! | #VALUE!
1248 | PP | GRT-CC03-P0UMA-175606 | 175606 | Culvert, Detail & Section | FA | 2017-11-21 | 2017-12-21 | 2017-11-21 | GRT-PP-IP-DT-170333 | FC | 1 | 2017-11-27 | 0027.001/C.1.2.17.01/E04/PLNE/XI/2017 | FA | B | A | #VALUE! | #VALUE!
1249 | PP | GRT-CA00-P0PAC-175607 | 175607 | Calculation Sheet for Intake Electrical Building | FA | 2017-10-23 | 2017-10-23 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1250 | PP | GRT-CA01-P0PAC-175608 | 175608 | Intake Electrical Building Architectural Plan, View, Section, & Finishing Schedule | FA | 2017-10-23 | 2017-10-23 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1251 | PP | GRT-CA01-P0PAC-175609 | 175609 | Intake Electrical Building Foundation, Floor, & Roof Plant, Section, Detail Grade Beam, Slab, & Column Schedule | FA | 2017-10-23 | 2017-10-23 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1252 | PP | GRT-CC07-P0UZEN-175475 | 175475 | Calculation Sheet for Liquefaction potential Check | FA | 2017-09-28 | 2017-09-28 | 2017-09-28 | GRT-PP-IP-DT-170244 | FC | 0 | 2017-09-28 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1253 | PP | GRT-CC04-P1UHA-175617 | 175617 | HRSG Foundation Plan and Section | FA | 2017-12-06 | 2017-12-06 | 2019-03-08 | GRT-PP-IP-DT-191050 | FC | 1 | 2019-04-01 | 024/061/GRT/UPR/2019 | FC | 1 | A | #VALUE! | #VALUE!
1254 | PP | GRT-CC04-P1UHA-175616 | 175616 | HRSG Concrete Layout | FA | 2017-12-06 | 2017-12-06 | 2019-03-08 | GRT-PP-IP-DT-191050 | FC | 1 | 2019-04-01 | 024/061/GRT/UPR/2019 | FC | 1 | A | #VALUE! | #VALUE!
1255 | PP | GRTBCP-YS01-P0BJP-156020 | 156020 | Schematic Diagram LV Switch Gear 1 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B | #VALUE! | #VALUE!
1256 | PP | GRTBCP-YS01-P0BFB-156025 | 156025 | Schematic Diagram LV Switch Gear 2 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B | #VALUE! | #VALUE!
1257 | PP | GRTBCP-YS01-P0BFC-156030 | 156030 | Schematic Diagram LV Switch Gear 3 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 27-Des-17 | Comment Sheet IP | FI | A | I | #VALUE! | #VALUE!
1258 | PP | GRTBCP-YS01-P0BFD-156035 | 156035 | Schematic Diagram LV Switch Gear 4 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B | #VALUE! | #VALUE!
1259 | PP | GRTBCP-YS01-P0BJA-156040 | 156040 | Schematic Diagram STG Unit MCC | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B | #VALUE! | #VALUE!
1260 | PP | GRTBCP-YS01-P0BJB-156045 | 156045 | Schematic Diagram STG PDB | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B | #VALUE! | #VALUE!
1261 | PP | GRTBCP-YS01-P0BJC-156050 | 156050 | Schematic Diagram HRSG Unit MCC | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B | #VALUE! | #VALUE!
1262 | PP | GRTBCP-YS01-P0BJD-156055 | 156055 | Schematic Diagram HRSG PDB | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B | #VALUE! | #VALUE!
1263 | PP | GRTBCP-YS01-P0BJE-156060 | 156060 | Schematic Diagram Valve PDB | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B | #VALUE! | #VALUE!
1264 | PP | GRTBCP-YS01-P0BJF-156065 | 156065 | Schematic Diagram BOP Essential MCC | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B | #VALUE! | #VALUE!
1265 | PP | GRTBCP-YS01-P0BJG-156070 | 156070 | Schematic Diagram Space Heater Panel | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B | #VALUE! | #VALUE!
1266 | PP | GRTBCP-YS01-P0BJH-156075 | 156075 | Schematic Diagram BOP Essential PDB | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B | #VALUE! | #VALUE!
1267 | PP | GRTBCP-YS01-P0BJJ-156080 | 156080 | Schematic Diagram Feeder UPS-01 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B | #VALUE! | #VALUE!
1268 | PP | GRTBCP-YS01-P0BJK-156085 | 156085 | Schematic Diagram Feeder UPS-02 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B | #VALUE! | #VALUE!
1269 | PP | GRTBCP-YS01-P0BJL-156090 | 156090 | Schematic Diagram Feeder Normal Lighting | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B | #VALUE! | #VALUE!
1270 | PP | GRTBCP-YS01-P0BJM-156095 | 156095 | Schematic Diagram Feeder HVAC | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B | #VALUE! | #VALUE!
1271 | PP | GRTBCP-YS01-P0BJN-156398 | 156398 | Schematic Diagram HRSG PDB-01 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B | #VALUE! | #VALUE!
1272 | PP | GRTBCP-YS01-P0BJO-156403 | 156403 | Schematic Diagram HRSG PDB-02 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B | #VALUE! | #VALUE!
1273 | PP | GRTBCP-YS01-P0BJP-156408 | 156408 | Schematic Diagram HRSG PDB-03 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B | #VALUE! | #VALUE!
1274 | PP | GRT-YU01-P0BFA-156019 | 156019 | Single Line Diagram LV Switchgear 1 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I | #VALUE! | #VALUE!
1275 | PP | GRT-YU01-P0BFB-156024 | 156024 | Single Line Diagram LV Switchgear 2 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I | #VALUE! | #VALUE!
1276 | PP | GRT-YU01-P0BFC-156029 | 156029 | Single Line Diagram LV Switchgear 3 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B | #VALUE! | #VALUE!
1277 | PP | GRT-YU01-P0BFD-156034 | 156034 | Single Line Diagram LV Switchgear 4 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I | #VALUE! | #VALUE!
1278 | PP | GRT-YU01-P0BJA-156039 | 156039 | Single Line Diagram STG Unit MCC | FI | 2018-01-26 | 2018-02-25 | 2019-11-07 | GRT-PP-IP-DT-191475 | FC | 1 | 2019-11-21 | 057/061/GRT/UPR/2019 |  | 1 | A | #VALUE! | #VALUE!
1279 | PP | GRT-YU01-P0BJA-156044 | 156044 | Single Line Diagram STG PDB | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I | #VALUE! | #VALUE!
1280 | PP | GRT-YU01-P0BJC-156049 | 156049 | Single Line Diagram HRSG Unit MCC | FI | 2018-01-26 | 2018-02-25 | 2019-11-07 | GRT-PP-IP-DT-191475 | FC | 1 | 2019-11-21 | 057/061/GRT/UPR/2019 |  | 1 | A | #VALUE! | #VALUE!
1281 | PP | GRT-YU01-P0BJP-156054 | 156054 | Single Line Diagram HRSG PDB | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I | #VALUE! | #VALUE!
1282 | PP | GRT-YU01-P0BJE-156059 | 156059 | Single Line Diagram Valve PDB | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I | #VALUE! | #VALUE!
1283 | PP | GRT-YU01-P0BJF-156064 | 156064 | Single Line Diagram BOP Essensial MCC | FI | 2018-01-26 | 2018-02-25 | 2019-11-07 | GRT-PP-IP-DT-191475 | FC | 1 | 2019-11-21 | 057/061/GRT/UPR/2019 |  | 1 | A | #VALUE! | #VALUE!
1284 | PP | GRT-YU01-P0BJG-156069 | 156069 | Single Line Diagram Space Heater Panel | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I | #VALUE! | #VALUE!
1285 | PP | GRT-YU01-P0BJH-156074 | 156074 | Single Line Diagram BOP Essensial PDB | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I | #VALUE! | #VALUE!
1286 | PP | GRT-YU01-P0BJJ-156079 | 156079 | Single Line Diagram Feeder UPS-01 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I | #VALUE! | #VALUE!
1287 | PP | GRT-YU01-P0BJK-156084 | 156084 | Single Line Diagram Feeder UPS-02 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I | #VALUE! | #VALUE!
1288 | PP | GRT-YU01-P0BJL-156089 | 156089 | Single Line Diagram Feeder Normal Lighting | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I | #VALUE! | #VALUE!
1289 | PP | GRT-YU01-P0BJM-156094 | 156094 | Single Line Diagram Feeder HVAC | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I | #VALUE! | #VALUE!
1290 | PP | GRT-YU01-P0BJM-156099 | 156099 | Single Line Diagram Feeder PDB-01 | FI | 2017-12-07 | 2018-01-06 | 2017-12-07 | GRT-PP-IP-DT-170353 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I | #VALUE! | #VALUE!
1291 | PP | GRT-YU01-P0BJO-156104 | 156104 | Single Line Diagram Feeder PDB-02 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I | #VALUE! | #VALUE!
1292 | PP | GRT-YU01-P0BJP-156109 | 156109 | Single Line Diagram Feeder PDB-03 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I | #VALUE! | #VALUE!
1293 | PP | GRT-CC07-PIUHA-175610 | 175610 | Calculation Sheet for Elevator Structure and Foundation | FA | 2018-01-04 | 2018-01-04 | 2018-02-02 | GRT-PP-IP-DT-180405 | FC | 0 | 2018-02-12 | Comment Sheet IP | FC | 0 | A | #VALUE! | #VALUE!
1294 | PP | GRT-CC03-P1UHA-175611 | 175611 | Elevation HRSG Foundation Plan, detail & Section | FA | 2018-01-04 | 2018-01-04 | 2019-01-08 | GRT-PP-IP-DT-190925 (DCR0014) | FC | 2 | 2019-01-22 | 004/061/GRT/UPR/2019 | FC | 2 | B | #VALUE! | #VALUE!
1295 | PP | GRT-CC04-P1UHA-175612 | 175612 | Elevation HRSG Steel Structure Column Arrangement & Member Schedule | FA | 2018-01-04 | 2018-01-04 | 2019-01-08 | GRT-PP-IP-DT-190925 (DCR0014) | FC | 2 | 2019-01-22 | 004/061/GRT/UPR/2019 | FC | 2 | B | #VALUE! | #VALUE!
1296 | PP | GRT-CC04-P1UHA-175613 | 175613 | Elevation HRSG Steel Structure Framing Elevation | FA | 2018-01-04 | 2018-01-04 | 2019-01-08 | GRT-PP-IP-DT-190925 (DCR0014) | FC | 2 | 2019-01-22 | 004/061/GRT/UPR/2019 | FC | 2 | B | #VALUE! | #VALUE!
1297 | PP | GRT-CC04-P1UHA-175614 | 175614 | Elevation HRSG Steel Structure Stairway Detail & Section | FA | 2018-01-04 | 2018-01-04 | 2019-01-08 | GRT-PP-IP-DT-190925 (DCR0014) | FC | 2 | 2019-01-22 | 004/061/GRT/UPR/2019 | FC | 2 | B | #VALUE! | #VALUE!
1298 | PP | GRT-CC04-P1UHA-175615 | 175615 | Elevator HRSG Architectural Plan, Detail, & Finishing Schedule | FA | 2017-12-06 | 2017-12-06 | 2017-12-06 | GRT-PP-IP-DT-170352 | FC | 0 | 2017-12-08 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1299 | PP | GRT-FF01-P0SGA-125501 | 125501 | General Arrangement Drawing Fire Pump | FA | 2017-06-10 | 2017-10-16 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 0 | 2017-10-17 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1300 | PP | GRT-YD00-P0ZEN-120003 | 120003 | General Arrangement Make up Demin Tank Capacity 1000 M3 | FA | 2017-11-09 | 2017-10-10 | 2017-10-10 | GRT-PP-IP-DT-170263 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1301 | PP | GRT-YD00-P0ZEN-120007 | 120007 | Roof Rafter Assembly Section & Detail Make up Demin Tank | FA | 2017-11-09 | 2017-10-10 | 2017-10-10 | GRT-PP-IP-DT-170263 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1302 | PP | GRT-YD00-P0ZEN-120010 | 120010 | Shell Manhole Section & Detail Make Up Demin Tank | FA | 2017-11-09 | 2017-10-10 | 2017-10-10 | GRT-PP-IP-DT-170263 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1303 | PP | GRT-YD00-P0ZEN-120018 | 120018 | Anchor Bolt Arrangemnt Section & Detail Make Up Demin Tank | FA | 2017-11-09 | 2017-10-10 | 2017-10-10 | GRT-PP-IP-DT-170263 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1304 | PP | GRT-YD00-P0ZEN-120004 | 120004 | Shell Plate Arrangement Section & Detail Make up Demin Tank | FA | 2017-11-09 | 2017-10-10 | 2017-10-10 | GRT-PP-IP-DT-170263 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1305 | PP | GRT-YD00-P0ZEN-120005 | 120005 | Bottom Plate Arrangement Section & Detail Make Up Demin Tank | FA | 2017-11-09 | 2017-10-10 | 2017-10-10 | GRT-PP-IP-DT-170263 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1306 | PP | GRT-YD00-P0ZEN-120006 | 120006 | Roof Plate Arrangement Section & Detail Make up Demin Tank | FA | 2017-11-09 | 2017-10-10 | 2017-10-10 | GRT-PP-IP-DT-170263 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1307 | PP | GRT-YD00-P0ZEN-120017 | 120017 | Roof Manhole Section & Detail Make up Demin Tank | FA | 2017-11-09 | 2017-10-10 | 2017-10-10 | GRT-PP-IP-DT-170263 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1308 | PP | GRT-YD00-P0UGD-120032 | 120032 | General Arrangement Drawing | FI | 2017-03-11 | 2017-03-11 | 2017-03-11 | GRT-PP-IP-DT-170305 | FI | A | 2017-11-29 | 0020.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | I | #VALUE! | #VALUE!
1309 | PP | GRT-YD00-P0UGD-120034 | 120034 | Roof Manhole Scetion and Detail | FI | 2017-03-11 | 2017-03-11 | 2017-03-11 | GRT-PP-IP-DT-170305 | FI | A | 2017-11-29 | 0020.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | I | #VALUE! | #VALUE!
1310 | PP | GRT-YD00-P0UGD-120035 | 120035 | Roof Structure Assembling Section & Detail | FI | 2017-03-11 | 2017-03-11 | 2017-03-11 | GRT-PP-IP-DT-170305 | FI | A | 2017-11-29 | 0020.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | I | #VALUE! | #VALUE!
1311 | PP | GRT-XW03-P0UGD-120002 | 120002 | Mechanical Calculation & Orentation | FI | 2017-03-11 | 2017-03-11 | 2017-03-11 | GRT-PP-IP-DT-170305 | FI | A | 2017-11-29 | 0020.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | I | #VALUE! | #VALUE!
1312 | PP | GRT-YD00-P0UGD-120033 | 120033 | Bottom Plate Arrangement Section & Detail | FI | 2017-11-14 | 2017-11-14 | 2017-11-14 | GRT-PP-IP-DT-170305 | FI | A | 2017-11-29 | 0020.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | I | #VALUE! | #VALUE!
1313 | PP | GRT-YD00-P0UGD-120036 | 120036 | Stairway Arrangement | FI | 2017-11-14 | 2017-11-14 | 2017-11-14 | GRT-PP-IP-DT-170317 | FI | A | 2017-11-29 | 0020.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | I | #VALUE! | #VALUE!
1314 | PP | GRT-YD00-P0UGD-120037 | 120037 | Shell Manhole Section & Detail | FI | 2017-11-14 | 2017-11-14 | 2017-11-14 | GRT-PP-IP-DT-170317 | FI | A | 2017-11-29 | 0020.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | I | #VALUE! | #VALUE!
1315 | PP | GRT-YD00-P0UGD-120038 | 120038 | Roof Plate Arrangement Section & Detail | FI | 2017-11-14 | 2017-11-14 | 2017-11-14 | GRT-PP-IP-DT-170317 | FI | A | 2017-11-29 | 0020.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | I | #VALUE! | #VALUE!
1316 | PP | GRT-YD00-P0UGD-120039 | 120039 | Roof Handril Detail | FI | 2017-11-14 | 2017-11-14 | 2017-11-14 | GRT-PP-IP-DT-170317 | FI | A | 2017-11-29 | 0020.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | I | #VALUE! | #VALUE!
1317 | PP | GRT-YT01-P0ZEN-145568 | 145568 | Data Sheet for rubber Expansion Join | FI | 2017-10-20 | 2017-10-20 | 2017-10-20 | GRT-PP-IP-DT-170279 | FI | A | 2017-07-11 | 0024.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I | #VALUE! | #VALUE!
1318 | PP | GRT-UE00-P0ZEN-145571 | 145571 | General Arrangement for Rubber Expansion Joint | FI | 2017-10-20 | 2017-10-20 | 2017-10-20 | GRT-PP-IP-DT-170279 | FI | A | 2017-07-11 | 0024.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I | #VALUE! | #VALUE!
1319 | PP | GRT-PP-KSB-P1702024-ME-002 | ME-002 | Mechanical Data Sheet for CWP Pump | FA | 2017-06-10 | 2017-06-10 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 0 | 2017-10-17 | N.A | FC | 0 | A | #VALUE! | #VALUE!
1320 | PP | GRT - YL16 - P0LD - 155944 | 155944 | Cable Schedule Electrical for EC | FI | 2018-02-02 | 2018-02-16 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1321 | PP | GRT - YL16 - P0LD - 155945 | 155945 | Cable Schedule Instrument for EC | FI | 2018-02-02 | 2018-02-16 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1322 | PP | GRT - YL16 - P0LD - 155848 | 155848 | Cable Schedule Electrical for WTP | FI | 2018-02-02 | 2018-02-16 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1323 | PP | GRT - YL16 - P0LD - 155949 | 155849 | Cable Schedule Instrument for WTP | FI | 2018-02-02 | 2018-02-16 | 2019-01-10 | GRT-PP-IP-DT-190929 (DCR0018) | FC | 0DCR1 | 2019-01-22 | 004/061/GRT/UPR/2019 | FC | DCR | A | #VALUE! | #VALUE!
1324 | PP | GRT - YT01 - P0GCK - 126801 | 126801 | Data Sheet Make Up Demin Water Pump | FI | 2018-02-02 | 2018-02-16 | 2018-02-02 | GRT-PP-IP-DT-180407 | FC | 0 | 2018-02-15 | Comment Sheet IP | FI | 0 | B | #VALUE! | #VALUE!
1325 | PP | GRT - YT01 - P0GCK - 126802 | 126802 | Data Sheet Blow Down Transfer Pump | FI | 2018-02-02 | 2018-02-16 | 2018-02-02 | GRT-PP-IP-DT-180407 | FC | 0 | 2018-02-15 | Comment Sheet IP | FI | 0 | B | #VALUE! | #VALUE!
1326 | PP | GRT - YT01 - P0GCK - 126803 | 126803 | Data Sheet Service Water Pump | FI | 2018-02-02 | 2018-02-16 | 2018-02-02 | GRT-PP-IP-DT-180407 | FC | 0 | 2018-02-15 | Comment Sheet IP | FI | 0 | B | #VALUE! | #VALUE!
1327 | PP | GRT - YT01 - P0GCK - 126804 | 126804 | Data Sheet Auxiliary Service Water Pump | FI | 2018-02-02 | 2018-02-16 | 2018-02-02 | GRT-PP-IP-DT-180407 | FC | 0 | 2018-02-15 | Comment Sheet IP | FI | 0 | B | #VALUE! | #VALUE!
1328 | PP | GRT - YT01 - P0GCK - 126805 | 126805 | Data Sheet Accumulation Sump Pit Pump | FI | 2018-02-02 | 2018-02-16 | 2018-02-02 | GRT-PP-IP-DT-180407 | FC | 0 | 2018-02-15 | Comment Sheet IP | FI | 0 | B | #VALUE! | #VALUE!
1329 | PP | GRT - YT01 - P0GCK - 126806 | 126806 | Data Sheet HRSG Sump Pit Pump | FI | 2018-02-02 | 2018-02-16 | 2018-02-02 | GRT-PP-IP-DT-180407 | FC | 0 | 2018-02-15 | Comment Sheet IP | FI | 0 | B | #VALUE! | #VALUE!
1330 | PP | GRT - YT01 - P0GCK - 126807 | 126807 | Data Sheet CEP Sump Pit Pump | FI | 2018-02-02 | 2018-02-16 | 2018-02-02 | GRT-PP-IP-DT-180407 | FC | 0 | 2018-02-15 | Comment Sheet IP | FI | 0 | B | #VALUE! | #VALUE!
1331 | PP | GRT - YT01 - P0GCK - 126808 | 126808 | Data Sheet Sea Water Drain Pump | FI | 2018-02-02 | 2018-02-16 | 2018-02-02 | GRT-PP-IP-DT-180407 | FC | 0 | 2018-02-15 | Comment Sheet IP | FI | 0 | B | #VALUE! | #VALUE!
1332 | PP | GRT-PP-MAR-0000 | 0000 | Material Approval Painting Raw Tank | FI | 2018-02-02 | 2018-02-16 | 2018-02-02 | GRT-PP-IP-DT-180407 | FI | B | 2018-02-15 | Comment Sheet IP | FA | 0 | B | #VALUE! | #VALUE!
1333 | PP | GRT-XW03-P0ZEN-156273 | 156273 | 150 kV Grati Switchgear Calculation Note High Voltage | FA | 2018-02-05 | 2018-02-19 | 2018-11-08 | GRT-PP-IP-DT-180852 | FC | 1 | 2018-11-14 | Comment Sheet IP | FC | 1 | B | #VALUE! | #VALUE!
1334 | PP | GRT-XW03-P0ZEN-156274 | 156274 | 150 kV Grati Switchgear Calculation Note lightning Arrester Checking | FA | 2018-02-05 | 2018-02-19 | 2018-02-05 | GRT-PP-IP-DT-180408 | FC(D) | A | 2018-02-15 | 0009.001/C.I.2.17.01/E04/PLNE/II/2018 | FA | A | A | #VALUE! | #VALUE!
1335 | PP | GRT-XW03-P0ZEN-156276 | 156276 | 150 kV Grati Switchgear Calculation Note lightning Protection Zone | FA | 2018-02-05 | 2018-02-19 | 2019-03-08 | GRT-PP-IP-DT-191059 | FC | 0 |  | Deem to approved | FC |  | A | #VALUE! | #VALUE!
1336 | PP | GRT-YR02-P0ZEN-156185 | 156185 | Common Switchgear Technical Specification Insulators | FA | 2018-02-05 | 2018-02-19 | 2019-03-08 | GRT-PP-IP-DT-191059 | FC | 0 |  | Deem to approved | FC |  | A | #VALUE! | #VALUE!
1337 | PP | GRT-YR02-P0ZEN-156186 | 156186 | 150 kV Grati Switchgear Technical Soecification Earthing Material | FA | 2018-02-05 | 2018-02-19 | 2019-03-08 | GRT-PP-IP-DT-191059 | FC | 0 |  | Deem to approved | FC |  | A | #VALUE! | #VALUE!
1338 | PP | GRT-YR02-P0ZEN-156187 | 156187 | Common Switchgear Technical Specification Conductor | FA | 2018-02-05 | 2018-02-19 | 2018-02-05 | GRT-PP-IP-DT-180408 | FC(D) | A | 2018-02-15 | 0009.001/C.I.2.17.01/E04/PLNE/II/2018 | FA | A | A | #VALUE! | #VALUE!
1339 | PP | GRT-YR02-P0ZEN-156188 | 156188 | Common Switchgear Technical Specification String Hardware | FA | 2018-02-05 | 2018-02-19 | 2019-03-08 | GRT-PP-IP-DT-191059 | FC | 0 |  | Deem to approved | FC |  | A | #VALUE! | #VALUE!
1340 | PP | GRT-YR02-P0ZEN-156189 | 156189 | Common Switchgear Technical Specification Connector | FA | 2018-02-05 | 2018-02-19 | 2018-05-02 | GRT-PP-IP-DT-180569 | FC | 0 | 2018-05-18 | Comment Sheet IP | FC | 0 | A | #VALUE! | #VALUE!
1341 | PP | GRT-YS01-P0ZEN-156196 | 156196 | 150 kV Grati Switchgear Schematic Diagram Diameter 1 | FA | 2018-02-05 | 2018-02-19 | 2018-02-05 | GRT-PP-IP-DT-180408 | FC(D) | A | 2018-02-15 | 0009.001/C.I.2.17.01/E04/PLNE/II/2018 | FA | A | B | #VALUE! | #VALUE!
1342 | PP | GRTBCP-YS01-P0BBA-156005 | 156005 | Schematic Diagram MV Switchgear 6,3kV | FA | 2018-02-05 | 2018-02-19 | 2018-05-08 | GRT-PP-IP-DT-180574 | FC | 0 | 2018-05-23 | Comment Sheet IP | FC | 0 | A | #VALUE! | #VALUE!
1343 | PP | GRTSCH-YD00-P0BAC-150005 | 150005 | SF6 Pressure Scale | FA | 2018-02-05 | 2018-02-19 | 2018-02-05 | GRT-PP-IP-DT-180408 | FI | A | 2018-02-21 | 0009.001/C.I.2.17.01/E04/PLNE/II/2018 | FA | A | I | #VALUE! | #VALUE!
1344 | PP | GRTSCH-YD00-P0BAC-150004 | 150004 | Name Plate | FA | 2018-02-05 | 2018-02-19 | 2018-02-05 | GRT-PP-IP-DT-180408 | FC(D) | A | 2018-02-21 | Comment Sheet IP | FA | A | B | #VALUE! | #VALUE!
1345 | PP | GRTSCH-YD00-P0BAC-150003 | 150003 | Interlocking Diagram | FA | 2018-02-05 | 2018-02-19 | 2019-11-29 | MINI DRM 28-29NOV19 | FC(D) | B | 2019-11-29 | MOM MINI DRM 28-29NOV19 | FA | B | B | #VALUE! | #VALUE!
1346 | PP | GRTSCH-YS01-P0BAC-150006 | 150006 | Electrical Diagram | FA | 2018-02-05 | 2018-02-19 | 2019-11-29 | MINI DRM 28-29NOV19 | FC(D) | B | 2019-11-29 | MOM MINI DRM 28-29NOV19 | FA | B | B | #VALUE! | #VALUE!
1347 | PP | GRT-YS18-P0BTL-156176 | 156176 | Battery Charger Circuit | FA | 2018-02-05 | 2018-02-19 | 2018-03-28 | GRT-PP-IP-DT-180498 | FC | 0 | 2018-04-18 | DRM 5 | FC | 0 | A | #VALUE! | #VALUE!
1348 | PP | GRT-YT02-P0MJY-156171 | 156171 | Flame and Smoke Detector Specification Sheet | FA | 2018-02-05 | 2018-02-19 | 2019-12-09 | GRT-PP-IP-DT-191518 | FC(D) | C |  |  | FA | C | A | #VALUE! | #VALUE!
1349 | PP | GRT-US02-P0MJY-156156 | 156156 | Local Electrical Panel Bom and Drawing | FA | 2018-02-05 | 2018-02-19 | 2018-05-02 | GRT-PP-IP-DT-180561 | FC | 0 | 2018-05-18 | Comment Sheet IP | FC | 0 | A | #VALUE! | #VALUE!
1350 | PP | GRT-MA01-P0AY-156172 | 156172 | IO List Communication to DCS | FA | 2018-02-05 | 2018-02-19 | 2019-11-29 | GRT-PP-IP-DT-191512 | FC(D) | B | 2019-11-29 | MOM MINI DRM 28-29NOV19 | FA | B | B | #VALUE! | #VALUE!
1351 | PP | GRT-YF01-P0MJ-156169 | 156169 | Termination Diagram for EDG | FA | 2018-02-05 | 2018-02-19 | 2019-11-29 | GRT-PP-IP-DT-191510 | FC | 1 | 2019-11-29 | MOM MINI DRM 28-29NOV19 | FC | 1 | A | #VALUE! | #VALUE!
1352 | PP | GRT-CC04-P0ZEN-156244 | 156244 | Common Switchgear Steel Structure C.V.T. SUPPORT H=2.1m - IB575 | FA | 2018-02-05 | 2018-02-19 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 2 | 2018-11-05 | Comment Sheet IP | FC | 2 | A | #VALUE! | #VALUE!
1353 | PP | GRT-CC04-P0ZEN-156239 | 156239 | Common Switchgear Steel Structure C.T. SUPPORT - H = 4M - IB560 | FA | 2018-02-05 | 2018-02-19 | 2018-10-23 | GRT-PP-IP-DT-180826 | FC | 2 | 2018-12-13 | stempel approved | FC | 2 | A | #VALUE! | #VALUE!
1354 | PP | GRT-CC04-P0ZEN-156241 | 156241 | Common Switchgear Steel Structure 3 Pole Disconnector Support - IB571 (S2DA) | FA | 2018-02-05 | 2018-02-19 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 1 | 2018-11-05 | Comment Sheet IP | FC | 1 | A | #VALUE! | #VALUE!
1355 | PP | GRT-CC04-P0ZEN-156242 | 156242 | Common Switchgear Steel Structure Disconnector Support - IB572 (S2DAT) | FA | 2018-02-05 | 2018-02-19 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 1 | 2018-11-05 | Comment Sheet IP | FC | 1 | A | #VALUE! | #VALUE!
1356 | PP | GRT-CC04-P0ZEN-156247 | 156247 | Common Switchgear Steel Structure CSE SUPPORT - IB583 | FA | 2018-02-05 | 2018-02-19 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 2 | 2018-10-22 | Comment Sheet IP |  | 2 | A | #VALUE! | #VALUE!
1357 | PP | GRT-CC04-P0ZEN-156249 | 156249 | Common Switchgear Steel Structure SA SUPPORT H=4M - IB574 | FA | 2018-02-05 | 2018-02-19 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 1 | 2018-11-05 | Comment Sheet IP | FC | 1 | A | #VALUE! | #VALUE!
1358 | PP | GRT-XW03-P0ZEN-156181 | 156181 | 150 KV Switchgear Calculation Note Battery & Chargear | FA | 2018-02-05 | 2018-02-19 | 2019-03-08 | GRT-PP-IP-DT-191059 | FC | 0 |  | Deem to approved | FC |  | A | #VALUE! | #VALUE!
1359 | PP | GRT-XG11-P0AE-156349 | 156349 | Schematic Line Diagram Cable 150KV | FA | 2018-02-05 | 2018-02-19 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 1 | 2018-10-30 | Comment Sheet IP | FC | 1 | B | #VALUE! | #VALUE!
1360 | PP | GRT-XW03-P0ZEN-156183 | 156183 | 150kV Grati Switchgear Technical Specification Protective Relays | FA | 2018-02-05 | 2018-02-19 | 2018-05-02 | GRT-PP-IP-DT-180569 | FC | 1 | 2018-05-18 | Comment Sheet IP | FC | 1 | I | #VALUE! | #VALUE!
1361 | PP | GRT-XW03-P0ZEN-156184 | 156184 | 150kV Grati Switchgear Technical Specification Low Voltage Cable | FA | 2018-02-05 | 2018-02-19 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 1 | 2018-10-30 | Comment Sheet IP | FC | 1 | A | #VALUE! | #VALUE!
1362 | PP | GRT-XW03-P0ZEN-156193 | 156193 | 150kV Grati Switchgear 110V DC Single Line Diagram | FA | 2018-02-05 | 2018-02-19 | 2018-05-02 | GRT-PP-IP-DT-180561 | FC | 0 | 2018-05-18 | Comment Sheet IP | FC | 0 | A | #VALUE! | #VALUE!
1363 | PP | GRT-XW03-P0ZEN-156209 | 156209 | 150KV Grati Switchgear Outdoor Installation Switchyard Layout | FA | 2018-02-05 | 2018-02-19 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 2 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 2 | A | #VALUE! | #VALUE!
1364 | PP | GRT-XW03-P0ZEN-156195 | 156195 | 150 KV Switchgear Principle Diagram | FA | 2018-02-05 | 2018-02-19 | 2018-05-02 | GRT-PP-IP-DT-180561 | FC | 0 | 2018-05-18 | Comment Sheet IP | FC | 0 | A | #VALUE! | #VALUE!
1365 | PP | GRT-XW03-P0ZEN-156206 | 156206 | 150 KV Switchgear Technical Specification Cable Sealing End (CSE) | FA | 2018-02-05 | 2018-02-19 | 2019-03-08 | GRT-PP-IP-DT-191059 | FC | 0 |  | Deem to approved | FC |  | A | #VALUE! | #VALUE!
1366 | PP | GRT-XW03-P0ZEN-156210 | 156210 | 150kV Grati Switchgear Outdoor Installation Diameter 1 | FA | 2018-02-05 | 2018-02-19 | 2018-05-02 | GRT-PP-IP-DT-180561 | FC | 1 | - | - |  | 1 | A | #VALUE! | #VALUE!
1367 | PP | GRT-XW03-P0ZEN-156211 | 156211 | 150kV Grati Switchgear Outdoor Installation Diameter X | FA | 2018-02-05 | 2018-02-19 | 2018-05-02 | GRT-PP-IP-DT-180561 | FC | 1 | - | - |  | 1 | A | #VALUE! | #VALUE!
1368 | PP | GRT-XW03-P0ZEN-156213 | 156213 | 150kV Grati Switchgear Outdoor Installation Lightning Protection Zone | FA | 2018-02-05 | 2018-02-19 | 2019-03-08 | GRT-PP-IP-DT-191059 | FC | 0 |  | Deem to approved | FC |  | A | #VALUE! | #VALUE!
1369 | PP | GRT-XW03-P0ZEN-156221 | 156221 | 150 KV Switchgear Cable List Diameter 1 | FA | 2018-02-05 | 2018-02-19 | 2019-05-07 | GRT-PP-IP-DT-191180 | FC | 1 | 2019-05-23 | 031/061/GRT/UPR/2018 |  | 1 | A | #VALUE! | #VALUE!
1370 | PP | GRT-XW03-P0ZEN-156222 | 156222 | 150 KV Switchgear Cable List Diameter X | FA | 2018-02-05 | 2018-02-19 | 2019-05-07 | GRT-PP-IP-DT-191180 | FC | 1 | 2019-05-23 | 031/061/GRT/UPR/2018 |  | 1 | A | #VALUE! | #VALUE!
1371 | PP | GRT-XW03-P0ZEN-156226 | 156226 | 150 KV Switchgear Connection Diagram Diameter 1 | FA | 2018-02-05 | 2018-02-19 | 2019-04-02 | GRT-PP-IP-DT-191115 | FC(D) | C | 2019-04-24 | 028/061/GRT/UPR/2019 | FA | C | A | #VALUE! | #VALUE!
1372 | PP | GRT-XW03-P0ZEV-156227 | 156227 | 150 KV Switchgear Connection Diagram Diameter X | FA | 2018-02-05 | 2018-02-19 | 2019-04-02 | GRT-PP-IP-DT-191115 | FC(D) | C | 2019-04-24 | 028/061/GRT/UPR/2019 | FA | C | A | #VALUE! | #VALUE!
1373 | PP | GRT-XW03-P0ZEN-156248 | 156248 | 150 KV Switchgear Earthing And Mounting Principle Drawing | FA | 2018-02-05 | 2018-02-19 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1374 | PP | GRT-YS01-P0ZEN-156197 | 156197 | 150KV GRATI. Switchgear Schematic Diagram Diameter X | FA | 2018-02-05 | 2018-02-19 | 2019-05-24 | DRM_22-24MAY2019 | FC | 0 | 2019-05-24 | DRM_22-24MAY2019 | FC | 0 | A | #VALUE! | #VALUE!
1375 | PP | GRT-CC04-P0ZEN-156232 | 156232 | Common Switchgear Steel Structure Tower Type P1-Bottom Part | FA | 2018-02-05 | 2018-02-19 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 2 | 2018-11-05 | Comment Sheet IP | FC | 2 | A | #VALUE! | #VALUE!
1376 | PP | GRT-CC04-P0ZEN-156233 | 156233 | Common Switchgear Steel Structure Tower Type P1-Top Part | FA | 2018-02-05 | 2018-02-19 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 2 | 2018-11-05 | Comment Sheet IP | FC | 2 | A | #VALUE! | #VALUE!
1377 | PP | GRT-CC04-P0ZEN-156234 | 156234 | Common Switchgear Steel Structure Tower Type P1- Tower Head | FA | 2018-02-05 | 2018-02-19 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 2 | 2018-11-05 | Comment Sheet IP | FC | 2 | A | #VALUE! | #VALUE!
1378 | PP | GRT-CC04-P0ZEN-156236 | 156236 | Common Switchgear Steel Structure Beam Type B1 | FA | 2018-02-05 | 2018-02-19 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 2 | 2018-11-05 | Comment Sheet IP | FC | 2 | A | #VALUE! | #VALUE!
1379 | PP | GRT-CC04-P0ZEN-156238 | 156238 | Common Switchgear Steel Structure Post Insulator Support H=4.5M-IB555 | FA | 2018-02-05 | 2018-02-19 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 1 | 2018-11-05 | Comment Sheet IP | FC | 1 | A | #VALUE! | #VALUE!
1380 | PP | GRT-CC04-P0ZEN-156245 | 156245 | Common Switchgear Steel StructureC.T Support-H=2.1M-IB576 | FA | 2018-02-05 | 2018-02-19 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 2 | 2018-11-05 | Comment Sheet IP | FC | 2 | A | #VALUE! | #VALUE!
1381 | PP | GRT-XA00-P0GCK-106801 | 106801 | GA Drawing Make Up Demin Water Pump | FI | 2018-02-07 | 2018-02-21 | 2018-02-07 | GRT-PP-IP-DT-180414 | FC | 0 | 2018-02-19 | Comment Sheet IP | FC | 0 | B | #VALUE! | #VALUE!
1382 | PP | GRT-XA00-P0GKB-106804 | 106804 | GA Drawing Auxiliary Water Pump | FI | 2018-02-07 | 2018-02-21 | 2018-02-07 | GRT-PP-IP-DT-180414 | FC | 0 | 2018-02-19 | Comment Sheet IP | FC | 0 | B | #VALUE! | #VALUE!
1383 | PP | GRT-XA00-P0LCQ-106800 | 106800 | GA Drawing Sump Pump | FI | 2018-02-07 | 2018-02-21 | 2018-02-07 | GRT-PP-IP-DT-180414 | FC | 0 | 2018-02-19 | Comment Sheet IP | FC | 0 | B | #VALUE! | #VALUE!
1384 | PP | GRT-XA00-P0LCQ-106802 | 106802 | GA Drawing Blow Down Transfer Water Pump | FI | 2018-02-07 | 2018-02-21 | 2018-02-07 | GRT-PP-IP-DT-180414 | FC | 0 | 2018-02-19 | Comment Sheet IP | FC | 0 | B | #VALUE! | #VALUE!
1385 | PP | GRT-XA00-P0PCC-106803 | 106803 | GA Drawing Service Water Pump | FI | 2018-02-07 | 2018-02-21 | 2018-02-07 | GRT-PP-IP-DT-180414 | FC | 0 | 2018-02-19 | Comment Sheet IP | FC | 0 | B | #VALUE! | #VALUE!
1386 | PP | GRT-XW03-P0PCH-156393 | 156393 | TECHNICAL INFORMATION ACWP IMPRESS CURRENT CATHODIC PROTECTION | FA | 2019-10-30 | 2019-11-29 | 2019-11-29 | GRT-PP-IP-DT-191511 | FC | 0 | 2019-11-29 | MOM MINI DRM 28-29NOV19 |  | 0 | A | #VALUE! | #VALUE!
1387 | PP | GRT-XW03-P0PCH-156394 | 156394 | TECHNICAL INFORMATION HEAT EXCHANGER IMPRESS CURRENT CATHODIC PROTECTION | FA | 2019-10-30 | 2019-11-29 | 2019-11-29 | GRT-PP-IP-DT-191511 | FC | 0 | 2019-11-29 | MOM MINI DRM 28-29NOV19 |  | 0 | A | #VALUE! | #VALUE!
1388 | PP | GRT-XW03-YD00-156395 | 156395 | Cathodic Protection System ACWP | FA | 2019-10-30 | 2019-11-29 | 2019-11-29 | Mini DRM 28-29 Nov 2019 | FC | 0 | 2019-11-29 | MoM Mini DRM 28-29 Nov 2019 |  | 0 | A | #VALUE! | #VALUE!
1389 | PP | GRT-YD00-P0PCH-156396 | 156396 | ICCP (IMPRESSED CURRENT CATHODIC PROTECTION) FOR HEAT EXCHANGER | FA | 2019-10-12 | 2019-11-11 | 2019-10-12 | Mini DRM 28-29 Nov 2019 | FC(D) | C |  |  |  |  | A | #VALUE! | #VALUE!
1390 | PP | GRT-XW03-P0ZEN-156275 | 156275 | 150kV Grati Switchgear Calculation Note Compatibility CVT | FA | 2019-10-30 | 2019-11-29 | 2019-11-29 | GRT-PP-IP-DT-191510 | FC | 1 | 2019-11-29 | MOM MINI DRM 28-29NOV19 | FC | 1 | B | #VALUE! | #VALUE!
1391 | PP | GRT-XW03-P0ZEN-156212 | 156212 | 150kV Grati Switchgear Outdoor Installation Busbar-Section | FA | 2018-04-02 | 2018-05-02 | 2018-05-02 | GRT-PP-IP-DT-180561 | FC | 0 | 2018-05-18 | Comment Sheet IP | FC | 0 | A | #VALUE! | #VALUE!
1392 | PP | GRT-YM02-P0ZEN-156207 | 156207 | 150kV Grati Switchgear Indoor Installation Control BLDG Equipment Layout | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 2 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 2 | A | #VALUE! | #VALUE!
1393 | PP | GRT-CA07-P0ZEN-179031 | 179031 | U-Ditch Precast Cable Trench Stability | FA | 2018-04-02 | 2018-05-02 | 2018-05-02 | GRT-PP-IP-DT-180561 | FC | 0 | 2018-05-18 | Comment Sheet IP | FC | 0 | B | #VALUE! | #VALUE!
1394 | PP | GRT-CA07-P0ZEN-179033 | 179033 | ADDITIONAL WINGWALL INTAKE BLOCK 2 STABILITY | FA | 2018-04-02 | 2018-05-02 | 2018-05-02 | GRT-PP-IP-DT-180561 | FC | 0 | 2018-05-18 | Comment Sheet IP | FC | 0 | B | #VALUE! | #VALUE!
1395 | PP | GRT-XW03-P0ZEN-156191 | 156191 | 150KV GRATI SWITCHGEAR CALCULATION NOTE STEEL STRUCTURE – EQUIPMENT SUPPORT | FA | 2018-10-22 | 2018-11-21 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC(D) | B | 2018-11-05 | Comment Sheet IP | FA | B | A | #VALUE! | #VALUE!
1396 | PP | GRT-CA07-P0ZEN-179036 | 179036 | CALCULATION REPORT CABLE TRENCH | FA | 2018-04-18 | 2018-05-18 | 2018-05-18 | GRT-PP-IP-DT-180598 | FC | 0 | 2018-05-23 | Comment Sheet IP | FC | 0 | A | #VALUE! | #VALUE!
1397 | PP | GRT-DD02-P0ZEN-156400 | 156400 | Island Mode Operation (Commissioning Procedure) | FA | 2019-04-03 | 2019-05-03 | 2019-05-03 | GRT-PP-IP-DT-191169 | FC | 0 |  | Deem to approved |  |  | A | #VALUE! | #VALUE!
1398 | PP | GRT-DD02-P0ZEN-156401 | 156401 | Blackout Procedure (Commissioning Procedure) | FA | 2018-09-22 | 2018-10-22 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 0 |  | Deem to approved |  |  | A | #VALUE! | #VALUE!
1399 | PP | GRT-YK08-P0SMM-146538 | 146538 | General Arrangement Rail A75 Overhead Crane | FA | 2018-07-24 | 2018-08-23 | 2018-08-23 | GRT-PP-IP-DT-180740 | FC | 0 | 2018-08-31 | Comment Sheet IP | FC | 0 | A | #VALUE! | #VALUE!
1400 | PP | GRT-YK08-P0SMM-146555 | 146555 | Detail Installation Rail A75 Overhead Crane | FA | 2018-07-24 | 2018-08-23 | 2018-08-23 | GRT-PP-IP-DT-180740 | FC | 0 | 2018-08-31 | Comment Sheet IP | FC | 0 | A | #VALUE! | #VALUE!
1401 | PP | GRT-XW03-P0ZEN-156352 | 156352 | SURGE ARRESTER OUTLINE DRAWING PACKAGE | FA | 2018-12-31 | 2019-01-30 | 2019-01-30 | GRT-PP-IP-DT-190970 | FC | 0 | 2019-02-26 | 10/061/GRT/UPR/2018 | FC | 0 | A | #VALUE! | #VALUE!
1402 | PP | GRT-XW03-P0ZEN-156353 | 156353 | CIRCUIT BREAKER OUTLINE DRAWING PACKAGE | FA | 2019-01-23 | 2019-02-22 | 2019-02-22 | GRT-PP-IP-DT-191010 | FC | 0 |  | Deem to approved | FC |  | A | #VALUE! | #VALUE!
1403 | PP | GRT-XW03-P0ZEN-156354 | 156354 | CURRENT TRANSFORMER OUTLINE DRAWING PACKAGE | FA | 2018-12-31 | 2019-01-30 | 2019-01-30 | GRT-PP-IP-DT-190970 | FC | 0 | 2019-02-26 | 10/061/GRT/UPR/2018 | FC | 0 | A | #VALUE! | #VALUE!
1404 | PP | GRT-XW03-P0ZEN-156355 | 156355 | DISCONNECTOR SWITCH OUTLINE DRAWING PACKAGE | FA | 2019-01-23 | 2019-02-22 | 2019-02-22 | GRT-PP-IP-DT-191010 | FC | 0 |  | Deem to approved | FC |  | A | #VALUE! | #VALUE!
1405 | PP | GRT-XW03-P0ZEN-156356 | 156356 | CAPACITOR VOLTAGE TRANSFORMER OUTLINE DRAWING PACKAGE | FA | 2019-01-23 | 2019-02-22 | 2019-02-22 | GRT-PP-IP-DT-191010 | FC | 0 |  | Deem to approved | FC |  | A | #VALUE! | #VALUE!
1406 | PP | GRT-XW03-P0ZEN-156357 | 156357 | DISCONNECTOR SWITCH with ES OUTLINE DRAWING PACKAGE | FA | 2019-01-23 | 2019-02-22 | 2019-02-22 | GRT-PP-IP-DT-191010 | FC | 0 |  | Deem to approved | FC |  | A | #VALUE! | #VALUE!
1407 | PP | GRT-HM03-P0EBM-135647 | 135647 | HVAC PACKAGE | FA | 2019-03-26 | 2019-04-25 | 2019-04-25 | GRT-PP-IP-DT-191161 | FC | 0 | 2019-05-09 | 029/061/GRT/UPR/2019 | FC | 0 | A | #VALUE! | #VALUE!
1408 | PP | GRT-YS01-POLDY-155853 | 155853 | Schematic Diagram for WTP (Mixed Bed) | FA | 2018-10-10 | 2018-11-09 | 2018-11-09 | GRT-PP-IP-DT-180849 | FC | 0 | 2018-11-09 | Comment Sheet IP | FC | 0 | A | #VALUE! | #VALUE!
1409 | PP | GRTBP-YS00-POGCK-155856 | 155856 | Instrument Connection Diagram for WTP (Mixed Bed) | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 (DCR 00033) | FC | 1 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 1 | A | #VALUE! | #VALUE!
1410 | PP | GRT-YS00-POGCK-155951 | 155951 | ELECTRICAL CONNECTION DIAGRAM FOR EC | FA | 2018-09-25 | 2018-10-25 | 2018-10-25 | GRT-PP-IP-DT-180832 | FC | 0 | 2018-10-25 | Comment Sheet IP | FC | 0 | A | #VALUE! | #VALUE!
1411 | PP | GRT-YS00-POGCK-155952 | 155952 | INSTRUMENT CONNECTION DIAGRAM FOR EC | FA | 2018-10-10 | 2018-11-09 | 2018-11-09 | GRT-PP-IP-DT-180849 | FC | 0 | 2018-11-09 | Comment Sheet IP | FC | 0 | A | #VALUE! | #VALUE!
1412 | PP | GRT-YS01-POGDY-155949 | 155949 | SCHEMATIC DIAGRAM FOR EC | FA | 2018-10-10 | 2018-11-09 | 2018-11-09 | GRT-PP-IP-DT-180849 | FC | 0 | 2018-11-09 | Comment Sheet IP | FC | 0 | A | #VALUE! | #VALUE!
1413 | PP | GRT-YS00-P0GCK-155855 | 155855 | ELECTRICAL CONNECTION DIAGRAM FOR MIXED BED | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1414 | PP | GRT-YD00-P0GD-155839 | 155839 | PANEL ARRANGEMENT (LAYOUT DRAWING) | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | B | #VALUE! | #VALUE!
1415 | PP | GRT-YS01-P0ZEN-156277 | 156277 | 150KV GRATI SWITCHGEAR FRONT AND INTERNAL VIEW ENERGY METER PANEL | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1416 | PP | GRT-YS01-P0ZEN-156278 | 156278 | 150KV GRATI SWITCHGEAR SCHEMATIC DIAGRAM ENERGY METER PANEL | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1417 | PP | GRT-XW03-P0ZEN-156182 | 156182 | 150KV GRATI GENERAL ARRANGEMENT MARSHALLING KIOSK | FA | 2018-10-09 | 2018-11-08 | 2018-11-08 | GRT-PP-IP-DT-180852 | FC | 0 | 2018-11-14 | Comment Sheet IP | FC | 0 | A | #VALUE! | #VALUE!
1418 | PP | GRT-YD00-YM02-156410 | 156410 | GENERAL ARRANGEMENT DIFFERENTIAL PROTECTION OVERALL & UAT SWITCHBOARD | FA | 2018-12-17 | 2019-01-16 | 2019-01-16 | GRT-PP-IP-DT-190931 | FC | 0 | 2019-02-01 | 006/061/GRT/UPR/2019 | FC | 0 | A | #VALUE! | #VALUE!
1419 | PP | GRT-MA01-P0ZEN-165582 | 165582 | SYSTEM CONFIGURATION OF CLOCK SYSTEM | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1420 | PP | GRT-YS02-P0ZEN-165581 | 165581 | [Instrument General] INSTRUMENT TERMINATION DIAGRAM FOR ALL AREA | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | B | #VALUE! | #VALUE!
1421 | PP | GRT-YD00-P0ZEN-165683 | 165683 | GENERAL ARRANGEMENT LOCAL PANEL FIRE FIGTHING | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1422 | PP | GRTBP-YD00-P0GD-155935 | 155935 | PANEL ARRANGEMENT OF ELECTROCHLORINATION | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | B | #VALUE! | #VALUE!
1423 | PP | GRT-YS01-P0ZEN-156358 | 156358 | 150KV GRATI SWITCHGEAR 400/230V AC DISTRIBUTION BOARD | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1424 | PP | GRT-YS01-P0ZEN-156359 | 156359 | 150KV GRT DC DISTRIBUTION BOARD | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1425 | PP | GRT-YT01-P0UZA-156405 | 156405 | CALCULATION CATHODIC PROTECTION FOR THERMAL BARRIER | FA | 2019-01-15 | 2019-02-14 | 2019-01-15 | GRT-PP-IP-DT-190930 | FC(D) | B | 2019-02-08 | 009/061/GRT/UPR/2019 | FA | B | A | #VALUE! | #VALUE!
1426 | PP | GRT-CC03-P0PAD-175181 | 175181 | Outfall Stop Log (include calculation) | FA | 2019-03-10 | 2019-04-09 | 2019-04-09 | GRT-PP-IP-DT-191138 | FC | 0 | 2019-04-24 | 028/061/GRT/UPR/2019 | FC | 0 | A | #VALUE! | #VALUE!
1427 | PP | GRT-CC09-P0UZA-175451 | 175451 | Foundation Support NSPB | FA | 2019-01-20 | 2019-02-19 | 2019-02-19 | GRT-PP-IP-DT-191003 | FC | 0 | 2019-03-04 | 015/061/GRT/UPR/2019 | FC | 0 | A | #VALUE! | #VALUE!
1428 | PP | GRT-CC09-P0UZA-175452 | 175452 | Calculation Sheet for Foundation Support NSPB | FA | 2019-01-20 | 2019-02-19 | 2019-02-19 | GRT-PP-IP-DT-191003 | FC | 0 | 2019-03-04 | 015/061/GRT/UPR/2019 | FC | 0 | A | #VALUE! | #VALUE!
1429 | PP | GRT-CC03-POUMA-175592 | 175592 | Steam Turbine Building Condensate Pump Foundation Detail (include attachment calculation) | FA | 2018-12-25 | 2019-01-24 | 2019-01-24 | GRT-PP-IP-DT-190954 | FC | 0 | 2019-01-24 | 005/061/GRT/UPR/2018 | FC | 0 | A | #VALUE! | #VALUE!
1430 | PP | GRT-CA01-P0UMA-175255 (1 OF 2) | 175255 | Steam Turbine Building Mezzanine Floor Plan El. +11.604 (T.O.C) Slab Schedule and Sections | FA | 2019-01-07 | 2019-02-06 | 2019-02-06 | GRT-PP-IP-DT-190977 | FC | 0 | 2019-02-13 | 011/061/GRT/UPR/2019 | FC | 0 | A | #VALUE! | #VALUE!
1431 | PP | GRT-CA01-P0UMA-175255 (2 OF 2) | 175255 | Steam Turbine Building Lube Oil and Mezzanine Local Platform Foundation Detail | FA | 2019-01-07 | 2019-02-06 | 2019-02-06 | GRT-PP-IP-DT-190977 | FC | 0 | 2019-02-13 | 011/061/GRT/UPR/2019 | FC | 0 | A | #VALUE! | #VALUE!
1432 | PP | GRT-CA01-P0UMA-175256 (1 OF 2) | 175256 | Steam Turbine Building Operating Plan El. +17.054 (T.O.C) Slab Schedule, Section and Details | FA | 2019-01-07 | 2019-02-06 | 2019-02-06 | GRT-PP-IP-DT-190977 | FC | 0 | 2019-02-13 | 011/061/GRT/UPR/2019 | FC | 0 | A | #VALUE! | #VALUE!
1433 | PP | GRT-CA01-P0UMA-175256 (2 OF 2) | 175256 | Steam Turbine Building Operating Local Platform Foundation Detail | FA | 2019-01-07 | 2019-02-06 | 2019-02-06 | GRT-PP-IP-DT-190977 | FC | 0 | 2019-02-13 | 011/061/GRT/UPR/2019 | FC | 0 | A | #VALUE! | #VALUE!
1434 | PP | GRT-YM02-P0UCA-175452 | 175452 | Arrangement Support NSPB (include calculation) | FA | 2019-03-10 | 2019-04-09 | 2019-04-09 | GRT-PP-IP-DT-191138 | FC | 0 | 2019-04-24 | 028/061/GRT/UPR/2019 | FC | 0 | A | #VALUE! | #VALUE!
1435 | PP | GRT-YS00-P0GCK-145938 | 145938 | Layout Busduct Chlorination | FA | 2019-05-27 | 2019-06-26 | 2019-06-26 | GRT-PP-IP-DT-191223 | FC | 0 |  |  |  |  | A | #VALUE! | #VALUE!
1436 | PP | GRT-YE00-P0GAC-145940 | 145940 | Data Sheet Busduct | FA | 2019-02-04 | 2019-03-06 | 2019-03-06 | GRT-PP-IP-DT-191053 | FC | 0 | 2019-03-13 | 019/061/GRT/UPR/2019 | FC | 0 | A | #VALUE! | #VALUE!
1437 | PP | GRT-XW03-P0PAC-156397 | 156397 | Chatodic Protection System for Intake Screen | FA | 2019-11-29 | 2019-12-29 | 2019-11-29 | MINI DRM 28-29NOV19 | FC(D) | B | 2019-11-29 | MOM MINI DRM 28-29NOV19 |  | B | B | #VALUE! | #VALUE!
1438 | PP | GRT-XW03-P0ZEN-156180 | 156180 | 150KV GRT Switchgear Calculation Note Protection Setting | FA | 2019-01-15 | 2019-02-14 | 2019-01-15 | GRT-PP-IP-DT-190930 | FC(D) | A | 2019-02-08 | 009/061/GRT/UPR/2019 | FA | A | B | #VALUE! | #VALUE!
1439 | PP | GRT-YS01-P0ZEN-156198 | 156198 | 150KV GRT General Arrangement Protection Diameter X & 1 Switchboard | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1440 | PP | GRT-YT01-P0UZA-156407 | 156407 | Layout Cathodic Protection for Thermal Barrier | FA | 2019-01-15 | 2019-02-14 | 2019-01-15 | GRT-PP-IP-DT-190930 | FC(D) | A | 2019-02-08 | 009/061/GRT/UPR/2019 | FA | A | A | #VALUE! | #VALUE!
1441 | PP | GRT-YD05-P0GD-165937 | 165937 | HMI GRAPHICS ELECTROCLORINATION | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1442 | PP | GRT-YL01-P0GD-161042 | 161042 | IO LIST FOR EC | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1443 | PP | GRT-YL01-P0LD-165846 | 165846 | IO LIST FOR WTP | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1444 | PP | GRT-YL25-P0GD-165943 | 165943 | MODBUS LIST FOR EC | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | B | #VALUE! | #VALUE!
1445 | PP | GRT-YL25-P0LD-165847 | 165847 | MODBUS LIST FOR WTP | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | B | #VALUE! | #VALUE!
1446 | PP | GRT-YD05-P0LD-135841 | 135841 | HMI GRAPHICS WTP | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 (DCR 00037) | FC | 1 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 1 | A | #VALUE! | #VALUE!
1447 | PP | GRT-YU01-P0ZEN-156411 | 156411 | SINGLE LINE DIAGRAM & LOGIC GT AND UNIT AUXILIARY TRANSFORMER PROTECTION | FA | 2019-01-23 | 2019-02-22 | 2019-02-22 | GRT-PP-IP-DT-191010 | FC | 0 |  | Deem to approved | FC |  | A | #VALUE! | #VALUE!
1448 | PP | GRT-CA01-P0UMA-175257 (1 OF 3) | 175257 | Steam Turbine Building Electrical Room Floor Plan Slab Schedule, Sections and Detail | FA | 2019-01-07 | 2019-02-06 | 2019-02-06 | GRT-PP-IP-DT-190977 | FC | 0 | 2019-02-13 | 011/061/GRT/UPR/2019 | FC | 0 | A | #VALUE! | #VALUE!
1449 | PP | GRT-CA01-P0UMA-175257 (2 OF 3) | 175257 | Steam Turbine Building Deaerator and Battery Room Floor Plan Section and Details | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | MINI DRM_13-15MAR2019 | FC | 1 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 1 | A | #VALUE! | #VALUE!
1450 | PP | GRT-CA01-P0UMA-175257 (3 OF 3) | 175257 | Steam Turbine Building Deaerator Local Platform Foundation Detail | FA | 2019-01-07 | 2019-02-06 | 2019-02-06 | GRT-PP-IP-DT-190977 | FC | 0 | 2019-02-13 | 011/061/GRT/UPR/2019 | FC | 0 | A | #VALUE! | #VALUE!
1451 | PP | GRT-YS18-P0PAC-156398 | 156398 | CIRCUIT AND WIRING DIAGRAM MCC & PLC FOR INTAKE SCREEN | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | B | #VALUE! | #VALUE!
1452 | PP | GRT-YD00-P0GAD-125625 | 125625 | CW PUMP AUXILIARY UNIT PACKAGE | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1453 | PP | GRT-YT01-P0UGD-115853 | 115853 | Process Data Sheet for Aux Service Water Tank | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1454 | PP | GRT-HM01-P0UGD-125453 | 125453 | [WTP] WTP Building HVAC Equipment Layout | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1455 | PP | GRT-HM01-P0UGD-125454 | 125454 | [WTP] WTP Building HVAC Ducting Layout | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1456 | PP | GRT-YM03-P0LD-160040 | 160040 | Instrumnet Arrangement for WTP (MIXED BED) | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1457 | PP | GRT-YM03-P0GD-161036 | 161036 | Instrument Arrangement for Electro Chlorination | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-19080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1458 | PP | GRT-YS01-P0ZEN-156259 | 156259 | Instrument Substation Automation System | FA | 2019-03-08 | 2019-04-07 | 2019-03-08 | GRT-PP-IP-DT-191035 | FC(D) | A |  |  |  | A | A | #VALUE! | #VALUE!
1459 | PP | GRT-YD00-P0ZEN-165690 | 165690 | Panel Arrangement Intake Electrical Building | FA | 2019-05-27 | 2019-06-26 | 2019-06-26 | GRT-PP-IP-DT-191234 (DCR 00047) | FC | 0DCR1 | 2019-07-04 | 037/061/GRT/UPR/2019 |  | 0DCR1 | A | #VALUE! | #VALUE!
1460 | PP | GRT-CV03-P0PAC-165695 | 165695 | INSTRUMENT DATA SHEET FOR CLAW SCREEN | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1461 | PP | GRT-YR02-P0BCA-165703 | 165703 | JUNCTION BOX OUTLINE DRAWING | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1462 | PP | GRT-YR02-P0BCA-165702 | 165702 | MOV OUTLINE DRAWING | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | B | #VALUE! | #VALUE!
1463 | PP | GRT-YR05-P0ZEN-165692 | 165692 | OUTLINE DRAWING FIRE FIGHTING SYSTEM | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1464 | PP | GRT-YS01-P0ZEN-165687 | 165687 | LDC SYSTEM ARCHITECTURE | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1465 | PP | GRT-XG02-P0PAC-115131 | 115131 | Piping & Instrument Diagram for Sea Water Intake | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 (DCR 00024) | FC | 2 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 2 | A | #VALUE! | #VALUE!
1466 | PP | GRT-XG02-P0PAC-115132 | 115132 | Piping & Instrumentation Diagram for Circulating Sea Water Cooling System | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 (DCR 00024) | FC | 2 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 2 | A | #VALUE! | #VALUE!
1467 | PP | GRT-YK00-P0PAC-165689 | 165689 | Hook Up for BOP Area | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1468 | PP | GRT-YR05-P0ZEN-165691 | 165691 | Data Sheet for Fire Alarm System | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1469 | PP | GRT-YR02-P0ZEN-165691 | 165691 | Data Sheet Equipment for Clock System | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1470 | PP | GRT-XK00-P0PAC-126811 | 126811 | Piping & Instrumentation Diagram Intake Screen | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1471 | PP | GRT-YT01-P0GAF-126810 | 126810 | Feed Pump Data Sheet | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1472 | PP | GRT-YD00-P0GAF-126809 | 126809 | Feed Pump Drawing (Arrangement Drawing) | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1473 | PP | GRT-XK00-P0GAC-125950 | 125950 | General Arrangement Aux Service Water Tank | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1474 | PP | GRT-YT01-P0ZEN-165127 | 165127 | Process Data Sheet for Pressure Regulating Valve | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A | #VALUE! | #VALUE!
1475 | PP | GRT-YR02-P0ZEN-156258 | 156258 | 150KV GRATI SWITCHGEAR SYSTEM FUNCTION SPEFICATION | FA | 2019-04-24 | 2019-05-24 | 2019-04-24 | GRT-PP-IP-DT-191158 | FC(D) | A | 2019-05-09 | 029/061/GRT/UPR/2019 | FA | A | B | #VALUE! | #VALUE!
1476 | PP | GRT-XJ00-P0ZEN-145041 | 145041 | CALCULATION SHEET FOR FIRE FIGHTING PIPE SUPPORT | FA | 2019-05-24 | 2019-06-23 | 2019-05-24 | DRM_22-24MAY2019 | FC(D) | B | 2019-05-24 | DRM_22-24MAY2019 |  | B | B | #VALUE! | #VALUE!
1477 | PP | GRT-XW03-P0ZEN-156351 | 156351 | 150KV SWITCHGEAR CABLE TRAY AND WIRING LAYOUT | FA | 2019-02-19 | 2019-03-21 | 2019-03-21 | MINI DRM_21MAR2019 | FC | 0 | 2019-03-21 | MINI DRM_21MAR2019 | FC | 0 | B | #VALUE! | #VALUE!
1478 | PP | GRT-YE07-P0PAC-156415 | 156415 | [Intake Electrical Building] Lightning Protection Layout | FA | 2019-09-19 | 2019-10-19 | 2019-09-19 | GRT-PP-IP-DT-191389 | FC(D) | B | 2019-09-26 | APPROVED ON SITE (PLN E) |  | B | A | #VALUE! | #VALUE!
1479 | PP | GRT-YE07-POPAC-156416 | 156416 | [INTAKE BUIILDING] Lighting Layout & Panel Schedule | FA | 2019-08-06 | 2019-09-05 | 2019-08-06 | GRT-PP-IP-DT-191266 | FC(D) | A | 2019-08-30 | 047/061/GRT/UPR/2019 | FA | A | B | #VALUE! | #VALUE!
1480 | PP | GRT-YL15-P0PAC-165616 | 165616 | TCS Cable Schedule | FA | 2020-08-29 | 2020-09-28 | 2020-08-29 | As-Built | FC | 0 | 2019-11-21 | 057/061/GRT/UPR/2019 |  | B | B | #VALUE! | #VALUE!
1481 | PP | GRT-YD00-P0PUR-156395 | 156395 | ICCP (IMPRESSED CURRENT CATHODIC PROTECTION) FOR AUXILIARY COOLING WATER PUMP | FA | 2019-11-29 | 2019-12-29 | 2019-11-29 | GRT-PP-IP-DT-191511 | FC(D) | B | 2019-11-29 | MOM MINI DRM 28-29NOV19 |  | B | A | #VALUE! | #VALUE!
1482 | PP | GRT-YR02-P0BCA-165707 | 165707 | Wiring Diagram | FA | 2020-01-30 | 2020-02-29 | 2020-01-30 | GRT-PP-IP-DT-201543 | FC(D) | A | 2020-02-03 | 002-GRT-I-U-GPE-2020 |  | A | C | #VALUE! | #VALUE!
1483 | PP | GRT-YR02-P0BCA-165708 | 165708 | Site Acceptance Test (SAT) LDC Panel | FA | 2020-01-30 | 2020-02-29 | 2020-01-30 | GRT-PP-IP-DT-201543 | FC(D) | A | 2020-02-03 | 002-GRT-I-U-GPE-2020 |  | A | C | #VALUE! | #VALUE!
1484 | PP | GRT-YS02-P0PAC-165709 | 165709 | Instrument Interconnection Diagram for TCS System | FA | 2020-08-29 | 2020-09-28 | 2020-08-29 | As-Built | FC | 0 | 2020-02-03 | 002-GRT-I-U-GPE-2020 |  | A | C | #VALUE! | #VALUE!
1485 | PP | GRT-CA01-P0PAC-175182 | 175182 | Architectural Waste Disposal Building Plan, Elevation & Section, Finishing Schedule | FA | 2020-10-15 | 2020-11-14 | 2020-10-15 | As-Built | FC | 0 | 2020-03-16 | 001/061/GRT/UPR/2020 |  | B | C | #VALUE! | #VALUE!
1486 | PP | GRT-CA01-P0PAC-175183 | 175183 | Toilet STG | FA | 2020-10-13 | 2020-11-12 | 2020-10-13 | As-Built | FC | 0 | 2020-03-16 | 001/061/GRT/UPR/2020 |  | B | C | #VALUE! | #VALUE!
1487 | PP | GRT-CC03-P0UGH-175353 (2 OF 2) | 175353 | Shelter for Make Up Demin Water Pump | FA | 2020-02-28 | 2020-03-29 | 2020-02-28 | GRT-PP-IP-DT-201558 | FC(D) | B | 2020-03-16 | 001/061/GRT/UPR/2020 |  | B | C | #VALUE! | #VALUE!
1488 | PP | GRT-YT01-P0SG-115331 | 115331 | Data Sheet Foam Extinguisher | FA | 2020-03-15 | 2020-04-14 | 2020-04-14 | GRT-PP-IP-DT-201577 (EMAIL) | FC | 0
Formulas:
First Actual = CHOOSECOLS(CHOOSEROWS(_xlws.FILTER(표2[],표2[DWG No.]=[Document No],""),1),6)
Final Actual = CHOOSECOLS(CHOOSEROWS(_xlws.FILTER(표2[],(표2[DWG No.]=[Document No])*(ISNUMBER(표2[Rev.])),""),1),6)
First Plan = [Final Plan]-30
First Plan = [Latest Issue to Client]
Final Plan = [Latest Issue to Client]
Final Plan = [First Plan]+30

## Sheet1 (2)
Document Submittal and Comment Status
Document Submittal Log (Prepared by Consortium) | [6 empty] | Comment Status(Prepared by IP)
No. | DT No. | DWG No. | Document Title | Rev. | Date | Review Period | Comment Status | Date2 | Open/Close | Remark
1457 | GRT-DS-IP-DT-170546 | GRT-DS-ME-DCR-0003 | Outline Drawing for CCW Heat Exchanger |  | 2017-01-02 | 387 | APPROVED AS NOTED | 2018-01-24 | Close
1 | GRT-DS-IP-DT-170001 | GRT-DA01-P0ZEN-020001 | DOCUMENT IDENTIFICATION | A | 2017-01-10 | 23 | A | 2017-02-02 | Close
2 | GRT-DS-IP-DT-170001 | GRT-DA01-P0ZEN-020002 | EQUIPMENT AND SYSTEM IDENTIFICATION | A | 2017-01-10 | 23 | A | 2017-02-02 | Close
12 | GRT-DS-IP-DT-170003 | GRT-XG02-P0SC-120001 | [Compressed air system]_P&I DIAGRAM FOR COMPRESSED AIR SYSTEM | A | 2017-02-10 | 55 | B | 2017-04-06 | Close
13 | GRT-DS-IP-DT-170003 | GRT-XG02-P0SC-120002 | [Compressed air system]_P&I DIAGRAM FOR INSTRUMENT AIR SYSTEM | A | 2017-02-10 | 55 | C | 2017-04-06 | Close
14 | GRT-DS-IP-DT-170003 | GRT-XG02-P0SC-120003 | [Compressed air system]_P&I DIAGRAM FOR SERVICE AIR SYSTEM | A | 2017-02-10 | 55 | C | 2017-04-06 | Close
15 | GRT-DS-IP-DT-170004 | GRT-XG05-P0ZEN-110001 | [Plant Overall]_HEAT BALANCE DIAGRAMS | A | 2017-02-10 | 13 | B | 2017-02-23 | Close
16 | GRT-DS-IP-DT-170005 | GRT-UC07-P0ZEN-100001 | PLOT PLAN | A | 2017-02-10 | 11 | C | 2017-02-21 | Close
3 | GRT-DS-IP-DT-170003 | GRT-XG05-P0ZEN-110002 | [Symbol & Legend]_P&I DIAGRAM | A | 2017-02-13 | 52 | I | 2017-04-06 | Close
4 | GRT-DS-IP-DT-170003 | GRT-XG02-P0LBA-110003 | [HP & LP steam system]_P&I DIAGRAM | A | 2017-02-13 | 52 | B | 2017-04-06 | Close
5 | GRT-DS-IP-DT-170003 | GRT-XG02-P0LBG-110004 | [AUX Steam System]_P&I DIAGRAM | A | 2017-02-13 | 52 | B | 2017-04-06 | Close
6 | GRT-DS-IP-DT-170003 | GRT-XG02-P0LCM-110005 | [Steam drain system]_P&ID DIAGRAM | A | 2017-02-13 | 52 | A | 2017-04-06 | Close
7 | GRT-DS-IP-DT-170003 | GRT-XG02-P0LA-110006 | [Feedwater system]_P&I DIAGRAM | A | 2017-02-13 | 52 | C | 2017-04-06 | Close
8 | GRT-DS-IP-DT-170003 | GRT-XG02-P0LC-110007 | [Condensate system]_P&I DIAGRAM | A | 2017-02-13 | 52 | A | 2017-04-06 | Close
9 | GRT-DS-IP-DT-170003 | GRT-XG02-P0PA-110008 | [Aux. Cooling Water System]_P&I DIAGRAM | A | 2017-02-13 | 52 | B | 2017-04-06 | Close
10 | GRT-DS-IP-DT-170003 | GRT-XG02-P0PG-110009 | [Closed cooling water system]_P&I DIAGRAM | A | 2017-02-13 | 52 | B | 2017-04-06 | Close
11 | GRT-DS-IP-DT-170003 | GRT-XG02-P0QJA-110010 | [N2 Gas system]_P&I DIAGRAM | A | 2017-02-13 | 52 | B | 2017-04-06 | Close
17 | GRT-DS-IP-DT-170006 | GRT-XS00-P0SC-120005 | [Compressed air system]_DESIGN CRITERIA FOR COMPRESSED AIR SYSTEM | A | 2017-02-22 | 12 | B | 2017-03-06 | Close
18 | GRT-DS-IP-DT-170006 | GRT-XW03-P0SC-120006 | [Compressed air system]_SIZING CALCULATION_COMPRESSED AIR SYSTEM | A | 2017-02-22 | 12 | C | 2017-03-06 | Close
19 | GRT-DS-IP-DT-170007 | GRT-XW01-P0LBA-110200 | [HP & LP steam system]_DESIGN CRITERIA | A | 2017-03-09 | 89 | B | 2017-06-06 | Close
20 | GRT-DS-IP-DT-170007 | GRT-XW01-P0LBG-110201 | [AUX Steam System]_DESIGN CRITERIA | A | 2017-03-09 | 89 | B | 2017-06-06 | Close
21 | GRT-DS-IP-DT-170007 | GRT-XW01-P0LA-110202 | [Feedwater system]_DESIGN CRITERIA | A | 2017-03-09 | 89 | B | 2017-06-06 | Close
22 | GRT-DS-IP-DT-170007 | GRT-XW01-P0LC-110203 | [Condensate system]_DESIGN CRITERIA | A | 2017-03-09 | 89 | B | 2017-06-06 | Close
23 | GRT-DS-IP-DT-170007 | GRT-XW01-P0PA-110204 | [Aux. Cooling Water System]_DESIGN CRITERIA | A | 2017-03-09 | 43 | B | 2017-04-21 | Close
24 | GRT-DS-IP-DT-170007 | GRT-XW01-P0PG-110205 | [Closed cooling water system]_DESIGN CRITERIA | A | 2017-03-09 | 43 | B | 2017-04-21 | Close
25 | GRT-DS-IP-DT-170007 | GRT-XW01-P0QJA-110206 | [N2 Gas system]_Design Criteria | A | 2017-03-09 | 43 | B | 2017-04-21 | Close
26 | GRT-DS-IP-DT-170008 | GRT-XS00-P0PA-110404 | [Aux. Cooling Water System]_SYSTEM DESCRIPTION | A | 2017-03-09 | 43 | B | 2017-04-21 | Close
27 | GRT-DS-IP-DT-170008 | GRT-XS00-P0PG-110405 | [Closed cooling water system]_SYSTEM DESCRIPTION | A | 2017-03-09 | 43 | B | 2017-04-21 | Close
28 | GRT-DS-IP-DT-170009 | GRT-YD00-P0LCM-430010 | Outline Drawing for Atmospheric Flash Tank | A | 2017-03-09 | 27 | C | 2017-04-05 | Close
29 | GRT-DS-IP-DT-170009 | GRT-YD00-P0PGB-430020 | Outline Drawing for CCW Chemical Additive Tank | A | 2017-03-09 | 27 | C | 2017-04-05 | Close
30 | GRT-DS-IP-DT-170009 | GRT-YD00-P0PGB-430030 | Outline Drawing for CCW Expansion Head Tank | A | 2017-03-09 | 27 | C | 2017-04-05 | Close
31 | GRT-DS-IP-DT-170010 | GRT-DE00-P0ZEN-144500 | [Piping General]_Piping material specification (BOP) | A | 2017-03-09 | 98 | B | 2017-06-15 | Close
32 | GRT-DS-IP-DT-170011 | GRT-XS00-P0LBA-110400 | [HP & LP steam system]_SYSTEM DESCRIPTION | A | 2017-03-09 | 43 | B | 2017-04-21 | Close
33 | GRT-DS-IP-DT-170011 | GRT-XS00-P0LBG-110401 | [AUX Steam System]_SYSTEM DESCRIPTION | A | 2017-03-09 | 43 | B | 2017-04-21 | Close
34 | GRT-DS-IP-DT-170011 | GRT-XS00-P0QJA-110406 | [N2 Gas system]_system description | A | 2017-03-09 | 43 | B | 2017-04-21 | Close
35 | GRT-DS-IP-DT-170012 | GRT-XS00-P0LA-110402 | [Feedwater system]_SYSTEM DESCRIPTION | A | 2017-03-09 | 43 | C | 2017-04-21 | Close
36 | GRT-DS-IP-DT-170012 | GRT-XS00-P0LC-110403 | [Condensate system]_SYSTEM DESCRIPTION | A | 2017-03-09 | 43 | B | 2017-04-21 | Close
37 | GRT-DS-IP-DT-170013 | GRT-YK08-P0MAG-410001 | Condenser_General Layout | A | 2017-03-09 | 29 | I | 2017-04-07 | Close
38 | GRT-DS-IP-DT-170013 | GRT-YK08-P0MAG-410002 | Condenser_General Arrangement | A | 2017-03-09 | 29 | I | 2017-04-07 | Close
39 | GRT-DS-IP-DT-170013 | GRT-XL00-P0MAG-410003 | Condenser_Connection List | A | 2017-03-09 | 29 | B | 2017-04-07 | Close
40 | GRT-DS-IP-DT-170013 | GRT-XL00-P0MAG-410004 | Condenser_Connection Detail | A | 2017-03-09 | 29 | B | 2017-04-07 | Close
41 | GRT-DS-IP-DT-170013 | GRT-VL00-P0MAG-410005 | Condenser_Foundation Assembly | A | 2017-03-09 | 27 | I | 2017-04-05 | Close
42 | GRT-DS-IP-DT-170013 | GRT-VL00-P0MAG-410006 | Condenser_Foundation Detail | A | 2017-03-09 | 27 | I | 2017-04-05 | Close
43 | GRT-DS-IP-DT-170013 | GRT-YT01-P0MAG-410007 | Condenser_Data Sheet | A | 2017-03-09 | 29 | C | 2017-04-07 | Close
44 | GRT-DS-IP-DT-170013 | GRT-YT01-P0MAG-410008 | Condenser_Nozzle Force and Moment | A | 2017-03-09 | 29 | I | 2017-04-07 | Close
45 | GRT-DS-IP-DT-170013 | GRT-YT01-P0MAG-410009 | Condenser_Performance Curves | A | 2017-03-09 | 29 | I | 2017-04-07 | Close
46 | GRT-DS-IP-DT-170014 | GRT-XW01-P0ZEN-161001 | [INC_Plant_Overall_Design]_I&C General Design Criteria | A | 2017-03-09 | 43 | B | 2017-04-21 | Close
47 | GRT-DS-IP-DT-170015 | GRT-XG05-P0ZEN-110001 | [Plant Overall]_HEAT BALANCE DIAGRAMS | B | 2017-03-09 | 27 | C | 2017-04-05 | Close
50 | GRT-DS-IP-DT-170018 | GRT-XG07-P0LBA-110300 | [Steam, Feedwater & Condensate system]_PROCESS FLOW DIAGRAM | A | 2017-03-15 | 50 | C | 2017-05-04 | Close
51 | GRT-DS-IP-DT-170018 | GRT-XG07-P0PA-110304 | [Aux. & Closed Cooling Water System]_PROCESS FLOW DIAGRAM | A | 2017-03-15 | 50 | C | 2017-05-04 | Close
48 | GRT-DS-IP-DT-170016 | GRT-XW03-P0LA-110500 | [BFP_Design]_sizing Calculation | A | 2017-03-22 | 14 | C | 2017-04-05 | Close
49 | GRT-DS-IP-DT-170017 | GRT-XS00-P0SC-120004 | [Compressed air system]_SYSTEM DESCRIPTION FOR COMPRESSED AIR SYSTEM | A | 2017-03-22 | 78 | A | 2017-06-08 | Close
52 | GRT-DS-IP-DT-170019 | GRT-YT10-P0ZEN-144502 | [Piping General]_Pipe Thickness Calculation (BOP) | A | 2017-03-22 | 43 | A | 2017-05-04 | Close
53 | GRT-DS-IP-DT-170020 | GRT-YD00-P0PGB-400040 | Outline Drawing for CCW Heat Exchanger | A | 2017-03-22 | 30 | C | 2017-04-21 | Close
54 | GRT-DS-IP-DT-170021 | GRT-XW03-P0LC-110501 | [CEP_Design]_sizing Calculation | A | 2017-03-22 | 43 | B | 2017-05-04 | Close
55 | GRT-DS-IP-DT-170022 | GRT-YS05-P0ZEN-162701 | [INC_Design_Criteria_Cable]_Typical I&C Cable Installation Drawing for Field Instrument | A | 2017-03-22 | 15 | I | 2017-04-06 | Close
56 | GRT-DS-IP-DT-170022 | GRT-YS05-P0ZEN-162702 | [INC_Design_Criteria_Cable]_Typical I&C Cable Installation Drawing for Control Valve | A | 2017-03-22 | 15 | I | 2017-04-06 | Close
57 | GRT-DS-IP-DT-170022 | GRT-YS05-P0ZEN-162703 | [INC_Design_Criteria_Cable]_Typical I&C Cable Installation Drawing for MOV | A | 2017-03-22 | 15 | I | 2017-04-06 | Close
58 | GRT-DS-IP-DT-170022 | GRT-YS05-P0ZEN-162704 | [INC_Design_Criteria_Cable]_Typical I&C Cable Installation Drawing for Instrument Rack and Junction Box | A | 2017-03-22 | 15 | I | 2017-04-06 | Close
59 | GRT-DS-IP-DT-170022 | GRT-YS05-P0ZEN-162705 | [INC_Design_Criteria_Cable]_Typical I&C Cable Installation Drawing for Conduit Support | A | 2017-03-22 | 15 | I | 2017-04-06 | Close
60 | GRT-DS-IP-DT-170023 | GRT-YS00-P0ZEN-163301 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram - Index | A | 2017-03-22 | 15 | I | 2017-04-06 | Close
61 | GRT-DS-IP-DT-170023 | GRT-YS00-P0ZEN-163302 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Motor Operated Valve (Internal MCC) | A | 2017-03-22 | 15 | I | 2017-04-06 | Close
62 | GRT-DS-IP-DT-170023 | GRT-YS00-P0ZEN-163303 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Pneumatic Shut-off Valve (Double Coil SOV) | A | 2017-03-22 | 15 | I | 2017-04-06 | Close
63 | GRT-DS-IP-DT-170023 | GRT-YS00-P0ZEN-163304 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Pneumatic Shut-off Valve (Single Coil SOV) | A | 2017-03-22 | 15 | I | 2017-04-06 | Close
64 | GRT-DS-IP-DT-170023 | GRT-YS00-P0ZEN-163305 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Modulating Control Actuator | A | 2017-03-22 | 15 | I | 2017-04-06 | Close
65 | GRT-DS-IP-DT-170023 | GRT-YS00-P0ZEN-163306 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Analog Input | A | 2017-03-22 | 15 | I | 2017-04-06 | Close
66 | GRT-DS-IP-DT-170023 | GRT-YS00-P0ZEN-163307 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Analog Output | A | 2017-03-22 | 15 | I | 2017-04-06 | Close
67 | GRT-DS-IP-DT-170023 | GRT-YS00-P0ZEN-163308 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Binary Input | A | 2017-03-22 | 15 | I | 2017-04-06 | Close
68 | GRT-DS-IP-DT-170023 | GRT-YS00-P0ZEN-163309 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Binary Output | A | 2017-03-22 | 15 | I | 2017-04-06 | Close
69 | GRT-DS-IP-DT-170024 | GRT-XB00-P0MA-200002 | [STG]_Foundation - Embedded Elements | A | 2017-03-22 | 30 | I | 2017-04-21 | Close
70 | GRT-DS-IP-DT-170024 | GRT-XB00-P0MA-200003 | [STG]_Foundation - Static & Dynamic Calculation | A | 2017-03-22 | 30 | I | 2017-04-21 | Close
71 | GRT-DS-IP-DT-170024 | GRT-XG08-P0MA-200005 | [STG]_P&I Diagrams | A | 2017-03-22 | 30 | C | 2017-04-21 | Close
72 | GRT-DS-IP-DT-170024 | GRT-YD00-P0MA-200006 | [STG]_General Arrangement Drawing | A | 2017-03-22 | 30 | C | 2017-04-21 | Close
73 | GRT-DS-IP-DT-170024 | GRT-XB00-P0MA-200007 | [STG]_Foundation load plan | A | 2017-03-22 | 30 | I | 2017-04-21 | Close
74 | GRT-DS-IP-DT-170024 | GRT-XB00-P0MA-200013 | [STG]_Allowable loadings and displacements | A | 2017-03-22 | 30 | I | 2017-04-21 | Close
75 | GRT-DS-IP-DT-170025 | GRT-UC07-P0ZEN-100001 | PLOT PLAN | 0 | 2017-03-22 | 30 | B | 2017-04-21 | Close
76 | GRT-DS-IP-DT-170026 | GRT-QM01-P0ZEN-040001 | Shop Inspection and Test Plan for Manufacturing | A | 2017-03-22 | 43 | B | 2017-05-04 | Close
77 | GRT-DS-IP-DT-170027 | GRT-UE00-P0ZEN-100003 | General Arrangement of Steam Turbine Building Ground Floor | A | 2017-03-22 | 15 | C | 2017-04-06 | Close
78 | GRT-DS-IP-DT-170027 | GRT-UE00-P0ZEN-100004 | General Arrangement of Steam Turbine Building Mezzanine Floor | A | 2017-03-22 | 15 | C | 2017-04-06 | Close
79 | GRT-DS-IP-DT-170027 | GRT-UE00-P0ZEN-100005 | General Arrangement of Steam Turbine Building Operating Floor | A | 2017-03-22 | 15 | C | 2017-04-06 | Close
80 | GRT-DS-IP-DT-170027 | GRT-UE00-P0ZEN-100006 | General Arrangement of Steam Turbine Building Deaerator Floor | A | 2017-03-22 | 15 | C | 2017-04-06 | Close
81 | GRT-DS-IP-DT-170027 | GRT-UE00-P0ZEN-100007 | General Arrangement of Steam Turbine Building Basement Floor | A | 2017-03-22 | 15 | C | 2017-04-06 | Close
82 | GRT-DS-IP-DT-170027 | GRT-UE00-P0ZEN-100008 | General Arrangement of Steam Turbine Building Section A-A | A | 2017-03-22 | 15 | C | 2017-04-06 | Close
83 | GRT-DS-IP-DT-170027 | GRT-UE00-P0ZEN-100009 | General Arrangement of Steam Turbine Building Section B-B | A | 2017-03-22 | 15 | C | 2017-04-06 | Close
84 | GRT-DS-IP-DT-170028 | GRT-YL00-P1H-300051 | [HRSG]_INSTRUMENT LIST | A | 2017-03-22 | 15 | I | 2017-04-06 | Close
85 | GRT-DS-IP-DT-170029 | GRT-XB00-P0MA-200001 | [STG]_Foundation - Shape & Anchoring | A | 2017-03-22 | 43 | I | 2017-05-04 | Close
86 | GRT-DS-IP-DT-170030 | GRT-UC08-P0ZEN-100002 | General Arrangement of Power Block | A | 2017-04-06 | 53 | B | 2017-05-29 | Close
87 | GRT-DS-IP-DT-170031 | GRT-XB02-P1H-300018 | [HRSG]_FOUNDATION LOADING & LOCATION DRAWING FOR BLOWDOWN TANK | A | 2017-04-06 | 53 | B | 2017-05-29 | Close
88 | GRT-DS-IP-DT-170031 | GRT-XS00-P1H-300032 | [HRSG]_BLOWDOWN SYSTEM SUMMARY | A | 2017-04-06 | 61 | C | 2017-06-06 | Close
89 | GRT-DS-IP-DT-170031 | GRT-YD00-P1H-300034 | [HRSG]_PRESSURE PART ARRANGEMENT | A | 2017-04-06 | 61 | C | 2017-06-06 | Close
90 | GRT-DS-IP-DT-170031 | GRT-YT01-P1H-300058 | [HRSG]_PERFORMANCE AND OPERATIONAL DATA | A | 2017-04-06 | 61 | C | 2017-06-06 | Close
91 | GRT-DS-IP-DT-170032 | GRT-XG02-P1H-300020 | [HRSG]_P&I DIAGRAM | A | 2017-04-06 | 61 | C | 2017-06-06 | Close
92 | GRT-DS-IP-DT-170033 | GRT-YU04-P0ZEN-161003 | [INC_Plant_Overall_Design]_Plant Control Block Diagram | A | 2017-04-06 | 53 | C | 2017-05-29 | Close
93 | GRT-DS-IP-DT-170034 | GRT-UE00-P1H-300006 | [HRSG]_GENERAL ARRANGEMENT | A | 2017-04-06 | 76 | A | 2017-06-21 | Close
94 | GRT-DS-IP-DT-170034 | GRT-XB02-P1H-300014 | [HRSG]_COLUMN LOCATION FOR STEEL STRUCTURE AND STACK (WITH PLAN VIEW) | A | 2017-04-06 | 69 | B | 2017-06-14 | Close
95 | GRT-DS-IP-DT-170034 | GRT-XB02-P1H-300015 | [HRSG]_FOUNDATION LOAD TABLE FOR STEEL STRUCTURE AND STACK | A | 2017-04-06 | 69 | B | 2017-06-14 | Close
96 | GRT-DS-IP-DT-170034 | GRT-XB02-P1H-300016 | [HRSG]_BASE PLATE AND ANCHOR BOLTS DETAIL FOR STEEL STRUCTURE | A | 2017-04-06 | 69 | B | 2017-06-14 | Close
97 | GRT-DS-IP-DT-170035 | GRT-XL00-P0ZEN-144503 | [Piping General]_Piping Line List (BOP) | A | 2017-04-06 | 53 | C | 2017-05-29 | Close
98 | GRT-DS-IP-DT-170035 | GRT-XL00-P0ZEN-144504 | [Piping General]_Piping Specialty List (BOP) | A | 2017-04-06 | 53 | C | 2017-05-29 | Close
99 | GRT-DS-IP-DT-170035 | GRT-XN00-P0ZEN-144505 | [Piping General]_Manual Valve List (BOP) | A | 2017-04-06 | 53 | C | 2017-05-29 | Close
100 | GRT-DS-IP-DT-170036 | GRT-MA01-P0ZEN-161002 | [INC_Plant_Overall_Design]_Plant Control System Configuration Diagram | A | 2017-04-10 | 49 | C | 2017-05-29 | Close
101 | GRT-DS-IP-DT-170037 | GRT-YK08-P0LAA-420001 | Outline Drawing for Deaerator & Feedwater Storage Tank | A | 2017-04-10 | 49 | C | 2017-05-29 | Close
102 | GRT-DS-IP-DT-170037 | GRT-CV03-P0LAA-420002 | Datasheet for Deaerator & Feedwater Storage Tank | A | 2017-04-10 | 49 | C | 2017-05-29 | Close
103 | GRT-DS-IP-DT-170038 | GRT-XS00-P0SC-120005 | [Compressed air system]_DESIGN CRITERIA FOR COMPRESSED AIR SYSTEM | 0 | 2017-04-10 | 49 | C | 2017-05-29 | Close
104 | GRT-DS-IP-DT-170039 | GRT-MA02-P0ZEN-161006 | [INC_Interface]_3rd Party Data-link Interface Concept Diagram | A | 2017-04-10 | 49 | C | 2017-05-29 | Close
105 | GRT-DS-IP-DT-170039 | GRT-MA02-P0ZEN-161121 | [DCS]_LAN Configuration Diagram | A | 2017-04-10 | 49 | C | 2017-05-29 | Close
106 | GRT-DS-IP-DT-170040 | GRT-DE00-P0ZEN-144501 | [Piping General]_Piping Insulation Specification (BOP) | A | 2017-04-10 | 49 | I | 2017-05-29 | Close
107 | GRT-DS-IP-DT-170041 | GRT-YU03-P0MA-200039 | [STG]_Control system architecture | A | 2017-04-10 | 59 | C | 2017-06-08 | Close
108 | GRT-DS-IP-DT-170042 | GRT-YR01-P0ZEN-110105 | [HP & LP steam system]_Pressure drop calculation | A | 2017-04-10 | 49 | C | 2017-05-29 | Close
109 | GRT-DS-IP-DT-170042 | GRT-CN00-P0ZEN-110106 | [Steam drain system]_Flash tank calculation | A | 2017-04-10 | 49 | C | 2017-05-29 | Close
110 | GRT-DS-IP-DT-170043 | GRT-YF01-P0ZEN-161004 | [INC_Plant_Overall_Design]_Plant Protection & Interlock Diagram | A | 2017-04-18 | 51 | C | 2017-06-08 | Close
111 | GRT-DS-IP-DT-170044 | GRT-YD06-P0ZEN-161113 | [INC_Plant_Overall_Design]_DCS Power Distribution Concept Diagram | A | 2017-04-18 | 48 | C | 2017-06-05 | Close
112 | GRT-DS-IP-DT-170044 | GRT-YR05-P0ZEN-161131 | [DCS]_Outline & Detail Drawing for Console desk & Computer desk & Printer desk | A | 2017-04-18 | 48 | C | 2017-06-05 | Close
113 | GRT-DS-IP-DT-170044 | GRT-YR05-P0ZEN-161132 | [DCS]_Outline & Detail Drawing for LAN Cabinet | A | 2017-04-18 | 48 | C | 2017-06-05 | Close
114 | GRT-DS-IP-DT-170044 | GRT-YR05-P0ZEN-161133 | [DCS]_Outline & Detail Drawing for Power Distribution Cabinet | A | 2017-04-18 | 48 | A | 2017-06-05 | Close
115 | GRT-DS-IP-DT-170044 | GRT-YR05-P0ZEN-161134 | [DCS]_Outline & Detail Drawing for System & Marshalling Cabinet | A | 2017-04-18 | 48 | C | 2017-06-05 | Close
116 | GRT-DS-IP-DT-170044 | GRT-YR05-P0ZEN-161136 | [DCS]_Outline & Detail Drawing for Safety Related System Panel | A | 2017-04-18 | 48 | C | 2017-06-05 | Close
117 | GRT-DS-IP-DT-170044 | GRT-YF00-P0ZEN-161201 | [INC_Other_Sys_Logic&Loop]_Control Logic Diagram - Symbol & Legend | A | 2017-04-18 | 48 | A | 2017-06-05 | Close
118 | GRT-DS-IP-DT-170044 | GRT-YF00-P0ZEN-161202 | [INC_Other_Sys_Logic&Loop]_Control Logic Diagram - Typical Function | A | 2017-04-18 | 48 | C | 2017-06-05 | Close
119 | GRT-DS-IP-DT-170044 | GRT-YF00-P0ZEN-161301 | [INC_Other_Sys_Logic&Loop]_Control Loop Diagram - Symbol & Legend | A | 2017-04-18 | 48 | A | 2017-06-05 | Close
120 | GRT-DS-IP-DT-170044 | GRT-YF00-P0ZEN-161302 | [INC_Other_Sys_Logic&Loop]_Control Loop Diagram - Typical Function | A | 2017-04-18 | 48 | A | 2017-06-05 | Close
121 | GRT-DS-IP-DT-170045 | GRT-YL01-P0ZEN-161101 | [INC_DCS_IO]_DCS I/O Database | A | 2017-04-18 | 42 | C | 2017-05-30 | Close
122 | GRT-DS-IP-DT-170046 | GRT-XW03-P0QJA-111001 | [N2 Gas System_Design]_sizing Calculation | A | 2017-04-18 | 41 | B | 2017-05-29 | Close
123 | GRT-DS-IP-DT-170048 | GRT-DA01-P0ZEN-020001 | DOCUMENT IDENTIFICATION | 0 | 2017-04-18 | 43 | APPROVED | 2017-05-31 | Close
124 | GRT-DS-IP-DT-170048 | GRT-DA01-P0ZEN-020002 | EQUIPMENT AND SYSTEM IDENTIFICATION | 0 | 2017-04-18 | 43 | APPROVED | 2017-05-31 | Close
125 | GRT-DS-IP-DT-170049 | GRT-YL19-P0MA-200038 | [STG]_Electrical load list | A | 2017-04-18 | 51 | C | 2017-06-08 | Close
126 | GRT-DS-IP-DT-170050 | GRT-XW03-P0PCC-113010 | [Aux. Cooling Water Pump_Design]_SIZING CALCULATION FOR AUXILIARY COOLING WATER PUMP | A | 2017-04-18 | 41 | C | 2017-05-29 | Close
127 | GRT-DS-IP-DT-170050 | GRT-XW03-P0PGB-113110 | [CCWP_Design]_SIZING CALCULATION FOR CLOSED COOLING WATER PUMP | A | 2017-04-18 | 41 | C | 2017-05-29 | Close
128 | GRT-DS-IP-DT-170051 | GRT-YF00-P0LBG-161204 | [AUX Steam System_I&C_Logic]_Control Logic Diagram for BOP | A | 2017-04-18 | 42 | C | 2017-05-30 | Close
129 | GRT-DS-IP-DT-170051 | GRT-YF00-P0LBG-161304 | [AUX Steam System_I&C_Loop]_Control Loop Diagram for BOP | A | 2017-04-18 | 42 | C | 2017-05-30 | Close
130 | GRT-DS-IP-DT-170057 | GRT-YK00-P0ZEN-164301 | BOP_Instrument Installation Detail Drawing - General Notes | A | 2017-05-11 | 0 | B | 2017-05-11 | Close
131 | GRT-DS-IP-DT-170057 | GRT-YK00-P0ZEN-164302 | BOP_Instrument Installation Detail Drawing - Symbol & Legend | A | 2017-05-11 | 0 | A | 2017-05-11 | Close
132 | GRT-DS-IP-DT-170057 | GRT-YK00-P0ZEN-164303 | BOP_Instrument Installation Detail Drawing - Material List | A | 2017-05-11 | 0 | A | 2017-05-11 | Close
133 | GRT-DS-IP-DT-170057 | GRT-YK00-P0ZEN-164304 | BOP_Instrument Installation Detail Drawing - Pressure Transmitter / Switch | A | 2017-05-11 | 0 | B | 2017-05-11 | Close
134 | GRT-DS-IP-DT-170057 | GRT-YK00-P0ZEN-164305 | BOP_Instrument Installation Detail Drawing - Diff. Press. Transmitter / Switch | A | 2017-05-11 | 0 | B | 2017-05-11 | Close
135 | GRT-DS-IP-DT-170057 | GRT-YK00-P0ZEN-164306 | BOP_Instrument Installation Detail Drawing - Flow Transmitter / Switch | A | 2017-05-11 | 0 | B | 2017-05-11 | Close
136 | GRT-DS-IP-DT-170057 | GRT-YK00-P0ZEN-164307 | BOP_Instrument Installation Detail Drawing - Level Transmitter / Switch | A | 2017-05-11 | 0 | B | 2017-05-11 | Close
137 | GRT-DS-IP-DT-170057 | GRT-YK00-P0ZEN-164308 | BOP_Instrument Installation Detail Drawing - Pressure Gauge | A | 2017-05-11 | 0 | B | 2017-05-11 | Close
138 | GRT-DS-IP-DT-170057 | GRT-YK00-P0ZEN-164309 | BOP_Instrument Installation Detail Drawing - Control Valve | A | 2017-05-11 | 0 | B | 2017-05-11 | Close
139 | GRT-DS-IP-DT-170057 | GRT-YK00-P0ZEN-164310 | BOP_Instrument Installation Detail Drawing - Stanchion & Rack | A | 2017-05-11 | 0 | B | 2017-05-11 | Close
140 | GRT-DS-IP-DT-170057 | GRT-YK00-P0ZEN-164312 | BOP_Instrument Installation Detail Drawing - Temp.Transmitter/ Guage/ Test Well | A | 2017-05-11 | 0 | B | 2017-05-11 | Close
141 | GRT-DS-IP-DT-170052 | GRT-YF00-P1LBA-161203 | [HP & LP steam system_I&C_Logic]_Control Logic Diagram for BOP | A | 2017-05-17 | 34 | C | 2017-06-20 | Close
142 | GRT-DS-IP-DT-170052 | GRT-YF00-P1LBA-161303 | [HP & LP steam system_I&C_Loop]_Control Loop Diagram for BOP | A | 2017-05-17 | 34 | C | 2017-06-20 | Close
143 | GRT-DS-IP-DT-170053 | GRT-XG02-P0PAH-440001 | Condenser Tube Cleaning System_P & I Diagram | A | 2017-05-17 | 20 | B | 2017-06-06 | Close
144 | GRT-DS-IP-DT-170053 | GRT-YK08-P0PAH-440002 | Condenser Tube Cleaning System_Outline Drawing | A | 2017-05-17 | 20 | B | 2017-06-06 | Close
145 | GRT-DS-IP-DT-170053 | GRT-YK08-P0PAH-440003 | Condenser Tube Cleaning System_Outline Drawing for Ball Recirculation unit | A | 2017-05-17 | 20 | A | 2017-06-06 | Close
146 | GRT-DS-IP-DT-170053 | GRT-YT01-P0PAH-440008 | Condenser Tube Cleaning System_Technical Data Sheet | A | 2017-05-17 | 20 | A | 2017-06-06 | Close
147 | GRT-DS-IP-DT-170053 | GRT-XG02-P0PAH-440051 | CCW HEX Tube Cleaning System_P & I Diagram | A | 2017-05-17 | 20 | B | 2017-06-06 | Close
148 | GRT-DS-IP-DT-170053 | GRT-YK08-P0PAH-440052 | CCW HEX Tube Cleaning System_Outline Drawing | A | 2017-05-17 | 20 | B | 2017-06-06 | Close
149 | GRT-DS-IP-DT-170053 | GRT-YK08-P0PAH-440053 | CCW HEX Tube Cleaning System_Outline Drawing for Ball Recirculation unit | A | 2017-05-17 | 20 | A | 2017-06-06 | Close
150 | GRT-DS-IP-DT-170053 | GRT-YT01-P0PAH-440058 | CCW HEX Tube Cleaning System_Technical Data Sheet | A | 2017-05-17 | 20 | A | 2017-06-06 | Close
151 | GRT-DS-IP-DT-170053 | GRT-XG02-P0PBB-440101 | Debris Filter_P & I Diagram | A | 2017-05-17 | 20 | B | 2017-06-06 | Close
152 | GRT-DS-IP-DT-170053 | GRT-YK08-P0PBB-440102 | Debris Filter_Outline Drawing | A | 2017-05-17 | 20 | B | 2017-06-06 | Close
153 | GRT-DS-IP-DT-170053 | GRT-YT01-P0PBB-440103 | Debris Filter_Technical Data Sheet | A | 2017-05-17 | 20 | A | 2017-06-06 | Close
154 | GRT-DS-IP-DT-170054 | GRT-YF00-P0PG-161208 | [Closed cooling water system_I&C_Logic]_Control Logic Diagram for BOP | A | 2017-05-17 | 51 | C | 2017-07-07 | Close
155 | GRT-DS-IP-DT-170054 | GRT-YF00-P0PG-161308 | [Closed cooling water system_I&C_Loop]_Control Loop Diagram for BOP | A | 2017-05-17 | 51 | C | 2017-07-07 | Close
156 | GRT-DS-IP-DT-170055 | GRT-XN00-P1H-300029 | [HRSG]_VALVE LIST | A | 2017-05-17 | 28 | B | 2017-06-14 | Close
157 | GRT-DS-IP-DT-170056 | GRT-YD00-P0SCA-120007 | [Air Compressor]_AIR COMPRESSOR_GENERAL ARRANGEMENT DRAWING FOR AIR COMPRESSORS PACKAGE | A | 2017-05-17 | 28 | A | 2017-06-14 | Close
158 | GRT-DS-IP-DT-170056 | GRT-XG02-P0SCA-120008 | [Air Compressor]_P&I DIAGRAM FOR AIR COMPRESSOR PACKAGE | A | 2017-05-17 | 28 | C | 2017-06-14 | Close
159 | GRT-DS-IP-DT-170056 | GRT-XW01-P0SCA-120009 | [Air Compressor]_AIR COMPRESSOR SPECIFICATION | A | 2017-05-17 | 28 | A | 2017-06-14 | Close
160 | GRT-DS-IP-DT-170056 | GRT-XW01-P0SCA-120010 | [Air Compressor]_AIR DRYER SPECIFICATION | A | 2017-05-17 | 28 | B | 2017-06-14 | Close
161 | GRT-DS-IP-DT-170056 | GRT-XW01-P0SCA-120011 | [Air Compressor]_AIR RECEIVER SPECIFICATION | A | 2017-05-17 | 28 | A | 2017-06-14 | Close
162 | GRT-DS-IP-DT-170056 | GRT-XW01-P0SCA-120012 | [Air Compressor]_AIR FILTER SPECIFICATION | A | 2017-05-17 | 28 | A | 2017-06-14 | Close
163 | GRT-DS-IP-DT-170058 | GRT-YD00-P0LCB-121001 | [Condensate Extraction Pump]_GENERAL ARRANGEMENT DRAWING | A | 2017-05-19 | 26 | A | 2017-06-14 | Close
164 | GRT-DS-IP-DT-170058 | GRT-XG02-P0LCB-121002 | [Condensate Extraction Pump]_P&I DIAGRAM | A | 2017-05-19 | 26 | A | 2017-06-14 | Close
165 | GRT-DS-IP-DT-170058 | GRT-YT01-P0LCB-121003 | [Condensate Extraction Pump]_DATA SHEET & CHARACTERISTIC CURVE | A | 2017-05-19 | 26 | I | 2017-06-14 | Close
166 | GRT-DS-IP-DT-170058 | GRT-YD00-P0LCB-121008 | [Condensate Extraction Pump]_FOUNDATION DRAWINGS | A | 2017-05-19 | 10 | C | 2017-05-29 | Close
167 | GRT-DS-IP-DT-170059 | GRT-UE00-P1H-300007 | [HRSG]_ARRANGEMENT OF CASING & FIELD ERECTION | A | 2017-05-19 | 26 | I | 2017-06-14 | Close
168 | GRT-DS-IP-DT-170059 | GRT-UE00-P1H-300008 | [HRSG]_ARRANGEMENT OF INLET DUCT | A | 2017-05-19 | 26 | I | 2017-06-14 | Close
169 | GRT-DS-IP-DT-170059 | GRT-XS00-P1H-300031 | [HRSG]_SYSTEM DESCRIPTION | A | 2017-05-19 | 26 | B | 2017-06-14 | Close
170 | GRT-DS-IP-DT-170060 | GRT-CV03-P0ZEN-161110 | [DCS]_Functional Design Specification for Hardware | A | 2017-05-19 | 19 | I | 2017-06-07 | Close
171 | GRT-DS-IP-DT-170060 | GRT-CV03-P0ZEN-161111 | [DCS]_Functional Design Specification for Software | A | 2017-05-19 | 19 | I | 2017-06-07 | Close
172 | GRT-DS-IP-DT-170060 | GRT-YE03-P0ZEN-161114 | [DCS]_Grounding Concept & Drawing | A | 2017-05-19 | 19 | I | 2017-06-07 | Close
173 | GRT-DS-IP-DT-170060 | GRT-YD06-P0ZEN-161115 | [DCS]_Equipment Power Distribution Diagram | A | 2017-05-19 | 19 | I | 2017-06-07 | Close
174 | GRT-DS-IP-DT-170060 | GRT-CV03-P0ZEN-161116 | [DCS]_Functional Design Specification for Safety Related System | A | 2017-05-19 | 19 | I | 2017-06-07 | Close
175 | GRT-DS-IP-DT-170060 | GRT-CV03-P0ZEN-161117 | [DCS]_Functional Design Specification for Performance Monitoring System | A | 2017-05-19 | 19 | I | 2017-06-07 | Close
176 | GRT-DS-IP-DT-170060 | GRT-YD07-P0ZEN-161122 | [DCS]_IO & Module Allocation | A | 2017-05-19 | 19 | I | 2017-06-07 | Close
177 | GRT-DS-IP-DT-170060 | GRT-YR05-P0ZEN-161135 | [DCS]_Outline & Detail Drawing for Relay Cabinet | A | 2017-05-19 | 19 | I | 2017-06-07 | Close
178 | GRT-DS-IP-DT-170060 | GRT-YF00-P0PA-161207 | [Aux. Cooling Water System_I&C_Logic]_Control Logic Diagram for BOP | A | 2017-05-19 | 49 | C | 2017-07-07 | Close
179 | GRT-DS-IP-DT-170060 | GRT-YF00-P0PA-161307 | [Aux. Cooling Water System_I&C_Loop]_Control Loop Diagram for BOP | A | 2017-05-19 | 49 | C | 2017-07-07 | Close
180 | GRT-DS-IP-DT-170061 | GRT-VL00-P0MAG-410005 | Condenser_Foundation Assembly | 0 | 2017-05-19 | 12 | APPROVED | 2017-05-31 | Close
181 | GRT-DS-IP-DT-170061 | GRT-VL00-P0MAG-410006 | Condenser_Foundation Detail | 0 | 2017-05-19 | 12 | APPROVED | 2017-05-31 | Close
182 | GRT-DS-IP-DT-170061 | GRT-YT01-P0MAG-410008 | Condenser_Nozzle Force and Moment | 0 | 2017-05-19 | 12 | APPROVED | 2017-05-31 | Close
183 | GRT-DS-IP-DT-170061 | GRT-YT01-P0MAG-410009 | Condenser_Performance Curves | 0 | 2017-05-19 | 12 | APPROVED | 2017-05-31 | Close
184 | GRT-DS-IP-DT-170062 | GRT-CV03-P0ZEN-161112 | [DCS]_Functional Design Specification for Graphic | A | 2017-05-19 | 32 | C | 2017-06-20 | Close
185 | GRT-DS-IP-DT-170063 | GRT-XB00-P0SCA-120013 | [Air Compressor]_FOUNDATION DRAWINGS | A | 2017-05-19 | 10 | I | 2017-05-29 | Close
186 | GRT-DS-IP-DT-170064 | GRT-YL00-P0MA-200045 | [STG]_List of signals | A | 2017-05-19 | 32 | C | 2017-06-20 | Close
187 | GRT-DS-IP-DT-170065 | GRT-YF00-P0LC-161206 | [Condensate system_I&C_Logic]_Control Logic Diagram for BOP | A | 2017-05-19 | 32 | A | 2017-06-20 | Close
188 | GRT-DS-IP-DT-170065 | GRT-YF00-P0LC-161306 | [Condensate system_I&C_Loop]_Control Loop Diagram for BOP | A | 2017-05-19 | 32 | C | 2017-06-20 | Close
189 | GRT-DS-IP-DT-170066 | GRT-XG02-P0LAC-122001 | [HP Feed Water Pump]_P&I DIAGRAM | A | 2017-05-19 | 129 | DEEMED APPROVAL | 2017-09-25 | Close
190 | GRT-DS-IP-DT-170066 | GRT-YT01-P0LAC-122003 | [HP Feed Water Pump]_DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | A | 2017-05-19 | 129 | DEEMED APPROVAL | 2017-09-25 | Close
191 | GRT-DS-IP-DT-170066 | GRT-YT01-P0LAC-122005 | [HP Feed Water Pump]_DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | A | 2017-05-19 | 129 | DEEMED APPROVAL | 2017-09-25 | Close
192 | GRT-DS-IP-DT-170066 | GRT-XG02-P0LAC-122501 | [LP Feed Water Pump]_P&I DIAGRAM | A | 2017-05-19 | 129 | DEEMED APPROVAL | 2017-09-25 | Close
193 | GRT-DS-IP-DT-170066 | GRT-YT01-P0LAC-122503 | [LP Feed Water Pump]_DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | A | 2017-05-19 | 129 | DEEMED APPROVAL | 2017-09-25 | Close
194 | GRT-DS-IP-DT-170066 | GRT-YT01-P0LAC-122505 | [LP Feed Water Pump]_DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | A | 2017-05-19 | 129 | DEEMED APPROVAL | 2017-09-25 | Close
195 | GRT-DS-IP-DT-170067 | GRT-XW03-P0LA-110500 | [BFP_Design]_sizing Calculation | B | 2017-05-19 | 20 | B | 2017-06-08 | Close
196 | GRT-DS-IP-DT-170068 | GRT-YF00-P0ZEN-161211 | [INC_Other_Sys_Logic&Loop]_Control Logic Diagram for Interface with other Control System | A | 2017-05-19 | 72 | C | 2017-07-30 | Close
197 | GRT-DS-IP-DT-170068 | GRT-YF00-P0ZEN-161212 | [INC_Other_Sys_Logic&Loop]_Control Logic Diagram for Miscellaneous System | A | 2017-05-19 | 72 | C | 2017-07-30 | Close
198 | GRT-DS-IP-DT-170068 | GRT-YF00-P0MAJ-161213 | [Condenser Vacuum Pump System _I&C_Logic]_Control Logic Diagram for BOP | A | 2017-05-19 | 72 | C | 2017-07-30 | Close
199 | GRT-DS-IP-DT-170068 | GRT-YF00-P0ZEN-161311 | [INC_Other_Sys_Logic&Loop]_Control Loop Diagram for Interface with other Control System | A | 2017-05-19 | 72 | C | 2017-07-30 | Close
200 | GRT-DS-IP-DT-170068 | GRT-YF00-P0ZEN-161312 | [INC_Other_Sys_Logic&Loop]_Control Loop Diagram for Miscellaneous System | A | 2017-05-19 | 72 | C | 2017-07-30 | Close
201 | GRT-DS-IP-DT-170068 | GRT-YF00-P0MAJ-161313 | [Condenser Vacuum Pump System _I&C_Loop]_Control Loop Diagram for BOP | A | 2017-05-19 | 72 | C | 2017-07-30 | Close
202 | GRT-DS-IP-DT-170069 | GRT-YF00-P0ZEN-161210 | [INC_Other_Sys_Logic&Loop]_Control Logic Diagram for Sampling & Chemical Dosing System | A | 2017-05-19 | 76 | B | 2017-08-03 | Close
203 | GRT-DS-IP-DT-170069 | GRT-YF00-P0ZEN-161310 | [INC_Other_Sys_Logic&Loop]_Control Loop Diagram for Sampling & Chemical Dosing System | A | 2017-05-19 | 76 | B | 2017-08-03 | Close
204 | GRT-DS-IP-DT-170070 | GRT-XG05-P0ZEN-110001 | [Plant Overall]_HEAT BALANCE DIAGRAMS | C | 2017-05-19 | 26 | B | 2017-06-14 | Close
205 | GRT-DS-IP-DT-170071 | GRT-YD00-P0MA-200024 | [STG]_Generator Specification | A | 2017-05-19 | 18 | I | 2017-06-06 | Close
206 | GRT-DS-IP-DT-170071 | GRT-YK09-P0MA-200033 | [STG]_Electrical system description | A | 2017-05-19 | 18 | B | 2017-06-06 | Close
207 | GRT-DS-IP-DT-170071 | GRT-YK00-P0MA-200034 | [STG]_Hook ups | A | 2017-05-19 | 18 | A | 2017-06-06 | Close
208 | GRT-DS-IP-DT-170071 | GRT-YF00-P0MA-200036 | [STG]_Consumer schemes | A | 2017-05-19 | 18 | I | 2017-06-06 | Close
209 | GRT-DS-IP-DT-170071 | GRT-YL00-P0MA-200037 | [STG]_Measurement list | A | 2017-05-19 | 18 | I | 2017-06-06 | Close
210 | GRT-DS-IP-DT-170072 | GRT-XG02-P0PA-110008 | [Aux. Cooling Water System]_P&I DIAGRAM | B | 2017-05-23 | 45 | B | 2017-07-07 | Close
211 | GRT-DS-IP-DT-170072 | GRT-XG02-P0PG-110009 | [Closed cooling water system]_P&I DIAGRAM | B | 2017-05-23 | 45 | B | 2017-07-07 | Close
212 | GRT-DS-IP-DT-170072 | GRT-XW01-P0PA-110204 | [Aux. Cooling Water System]_DESIGN CRITERIA | B | 2017-05-23 | 45 | A | 2017-07-07 | Close
213 | GRT-DS-IP-DT-170072 | GRT-XW01-P0PG-110205 | [Closed cooling water system]_DESIGN CRITERIA | B | 2017-05-23 | 45 | A | 2017-07-07 | Close
214 | GRT-DS-IP-DT-170072 | GRT-XS00-P0PA-110404 | [Aux. Cooling Water System]_SYSTEM DESCRIPTION | B | 2017-05-23 | 45 | A | 2017-07-07 | Close
215 | GRT-DS-IP-DT-170072 | GRT-XS00-P0PG-110405 | [Closed cooling water system]_SYSTEM DESCRIPTION | B | 2017-05-23 | 45 | A | 2017-07-07 | Close
216 | GRT-DS-IP-DT-170073 | GRT-UE00-P1H-300009 | [HRSG]_ARRANGEMENT OF MAIN STACK& FIELD ERECTION | A | 2017-05-23 | 22 | I | 2017-06-14 | Close
217 | GRT-DS-IP-DT-170073 | GRT-XL00-P1H-300028 | [HRSG]_LINE LIST | A | 2017-05-23 | 22 | A | 2017-06-14 | Close
218 | GRT-DS-IP-DT-170073 | GRT-YU02-P1H-300066 | [HRSG]_ELECTRICAL SINGLE LINE DIAGRAMS | A | 2017-05-23 | 22 | I | 2017-06-14 | Close
219 | GRT-DS-IP-DT-170074 | GRT-YF00-P0LA-161205 | [Feedwater system_I&C_Logic]_Control Logic Diagram for BOP | A | 2017-05-23 | 72 | C | 2017-08-03 | Close
220 | GRT-DS-IP-DT-170074 | GRT-YF00-P0LA-161305 | [Feedwater system_I&C_Loop]_Control Loop Diagram for BOP | A | 2017-05-23 | 72 | C | 2017-08-03 | Close
221 | GRT-DS-IP-DT-170075 | GRT-XB00-P0MA-200001 | [STG]_Foundation - Shape & Anchoring | B | 2017-05-23 | 22 | I | 2017-06-14 | Close
222 | GRT-DS-IP-DT-170075 | GRT-XB00-P0MA-200002 | [STG]_Foundation - Embedded Elements | B | 2017-05-23 | 22 | I | 2017-06-14 | Close
223 | GRT-DS-IP-DT-170075 | GRT-XB00-P0MA-200009 | [STG]_Lay down plan | A | 2017-05-23 | 22 | I | 2017-06-14 | Close
224 | GRT-DS-IP-DT-170075 | GRT-XV00-P0MA-200010 | [STG]_List of pipelines | A | 2017-05-23 | 22 | I | 2017-06-14 | Close
225 | GRT-DS-IP-DT-170075 | GRT-XN00-P0MA-200011 | [STG]_List of valves | A | 2017-05-23 | 22 | I | 2017-06-14 | Close
226 | GRT-DS-IP-DT-170075 | GRT-XV00-P0MA-200012 | [STG]_List of equipments | A | 2017-05-23 | 22 | I | 2017-06-14 | Close
227 | GRT-DS-IP-DT-170075 | GRT-YK09-P0MA-200020 | [STG]_Functional description | A | 2017-05-23 | 8 | I | 2017-05-31 | Close
228 | GRT-DS-IP-DT-170075 | GRT-YK10-P0MA-200056 | [STG]_Initial specification for TG installation | A | 2017-05-23 | 22 | I | 2017-06-14 | Close
229 | GRT-DS-IP-DT-170076 | GRT-XB00-P0MA-200007 | [STG]_Foundation load plan | B | 2017-05-23 | 22 | I | 2017-06-14 | Close
230 | GRT-DS-IP-DT-170076 | GRT-YD00-P0MA-200017 | [STG]_Layout - piping routing - | A | 2017-05-23 | 22 | I | 2017-06-14 | Close
231 | GRT-DS-IP-DT-170076 | GRT-YU03-P0MA-200041 | [STG]_Control system function philosophy | A | 2017-05-23 | 68 | I | 2017-07-30 | Close
232 | GRT-DS-IP-DT-170077 | GRT-YV02-P0SCA-120015 | [Air Compressor]_ELECTRICAL WIRING DIAGRAMS | A | 2017-05-23 | 28 | I | 2017-06-20 | Close
233 | GRT-DS-IP-DT-170077 | GRT-YU03-P0SCA-120016 | [Air Compressor]_ELECTRICAL SCHEMATIC DIAGRAM | A | 2017-05-23 | 28 | I | 2017-06-20 | Close
234 | GRT-DS-IP-DT-170077 | GRT-YF02-P0SCA-120017 | [Air Compressor]_CONTROL DESCRIPTION (PHILOSOPHY) | A | 2017-05-23 | 28 | B | 2017-06-20 | Close
235 | GRT-DS-IP-DT-170078 | GRT-XG02-P0LA-110006 | [Feedwater system]_P&I DIAGRAM | B | 2017-05-23 | 16 | A | 2017-06-08 | Close
236 | GRT-DS-IP-DT-170078 | GRT-XG02-P0LC-110007 | [Condensate system]_P&I DIAGRAM | B | 2017-05-23 | 16 | A | 2017-06-08 | Close
237 | GRT-DS-IP-DT-170078 | GRT-XS00-P0LA-110402 | [Feedwater system]_SYSTEM DESCRIPTION | B | 2017-05-23 | 16 | A | 2017-06-08 | Close
238 | GRT-DS-IP-DT-170078 | GRT-XS00-P0LC-110403 | [Condensate system]_SYSTEM DESCRIPTION | 0 | 2017-05-23 | 24 | APPROVED AS NOTED | 2017-06-16 | Close
239 | GRT-DS-IP-DT-170079 | GRT-DM02-P1H-300005 | [HRSG]_GENERAL NOTE FOR STEEL STRUCTURE | A | 2017-05-26 | 19 | I | 2017-06-14 | Close
240 | GRT-DS-IP-DT-170079 | GRT-VN03-P1H-300010 | [HRSG]_TYPICAL PLATFORM DETAIL FOR STEEL STRUCTURE | A | 2017-05-26 | 19 | I | 2017-06-14 | Close
241 | GRT-DS-IP-DT-170079 | GRT-VN03-P1H-300011 | [HRSG]_TYPICAL HANDRAIL DETAIL FOR STEEL STRUCTURE | A | 2017-05-26 | 19 | I | 2017-06-14 | Close
242 | GRT-DS-IP-DT-170079 | GRT-VN03-P1H-300012 | [HRSG]_TYPICAL LADDER DETAIL FOR STEEL STRUCTURE | A | 2017-05-26 | 19 | I | 2017-06-14 | Close
243 | GRT-DS-IP-DT-170079 | GRT-VN03-P1H-300013 | [HRSG]_ARRANGEMENT FOR PLATFORM STRUCTURE | A | 2017-05-26 | 19 | I | 2017-06-14 | Close
244 | GRT-DS-IP-DT-170080 | GRT-YK09-P0LCB-121004 | [Condensate Extraction Pump]_PUMP SECTIONAL DRAWING | A | 2017-05-26 | 19 | A | 2017-06-14 | Close
245 | GRT-DS-IP-DT-170080 | GRT-YT01-P0LCB-121006 | [Condensate Extraction Pump]_COUPLING SPECIFICATION | A | 2017-05-26 | 19 | I | 2017-06-14 | Close
246 | GRT-DS-IP-DT-170080 | GRT-YM01-P0LCB-121009 | [Condensate Extraction Pump]_MOTOR DATA SHEET & CHARACTERISTIC CURVE | A | 2017-05-26 | 19 | A | 2017-06-14 | Close
247 | GRT-DS-IP-DT-170081 | GRT-XW01-P0QJA-110206 | [N2 Gas system]_Design Criteria | B | 2017-05-26 | 19 | A | 2017-06-14 | Close
248 | GRT-DS-IP-DT-170081 | GRT-XS00-P0LBA-110400 | [HP & LP steam system]_SYSTEM DESCRIPTION | B | 2017-05-26 | 19 | A | 2017-06-14 | Close
249 | GRT-DS-IP-DT-170081 | GRT-XS00-P0LBG-110401 | [AUX Steam System]_SYSTEM DESCRIPTION | B | 2017-05-26 | 19 | A | 2017-06-14 | Close
250 | GRT-DS-IP-DT-170081 | GRT-XS00-P0QJA-110406 | [N2 Gas system]_system description | B | 2017-05-26 | 19 | A | 2017-06-14 | Close
251 | GRT-DS-IP-DT-170084 | GRT-YD00-P0PGB-430030 | OUNLINE DRAWING FOR CCW EXPANSION HEAD TANK | B | 2017-05-26 | 65 | B | 2017-07-30 | Close
252 | GRT-DS-IP-DT-170084 | GRT-YD00-P0PGB-430020 | OUNLINE DRAWING FOR CCW CHEMICAL ADDITIVE TANK | B | 2017-05-26 | 65 | B | 2017-07-30 | Close
253 | GRT-DS-IP-DT-170084 | GRT-YD00-P0LCM-430010 | OUNLINE DRAWING FOR ATMOSPHERIC FLASH TANK | B | 2017-05-26 | 65 | B | 2017-07-30 | Close
254 | GRT-DS-IP-DT-170085 | GRT-XG02-P0LBA-110003 | [HP & LP steam system]_P&I DIAGRAM | B | 2017-05-30 | 15 | A | 2017-06-14 | Close
255 | GRT-DS-IP-DT-170085 | GRT-XG02-P0LBG-110004 | [AUX Steam System]_P&I DIAGRAM | B | 2017-05-30 | 15 | A | 2017-06-14 | Close
256 | GRT-DS-IP-DT-170085 | GRT-XG02-P0LCM-110005 | [Steam drain system]_P&ID DIAGRAM | B | 2017-05-30 | 15 | I | 2017-06-14 | Close
257 | GRT-DS-IP-DT-170085 | GRT-XG02-P0QJA-110010 | [N2 Gas system]_P&I DIAGRAM | B | 2017-05-30 | 15 | A | 2017-06-14 | Close
258 | GRT-DS-IP-DT-170086 | GRT-XG02-P0LDB-130036 | [Condensate Filter System]_P&ID | A | 2017-05-30 | 15 | B | 2017-06-14 | Close
259 | GRT-DS-IP-DT-170086 | GRT-XA00-P0LDB-130037 | [Condensate Filter System]_GENERAL ARRANGEMENT DRAWING | A | 2017-05-30 | 15 | A | 2017-06-14 | Close
260 | GRT-DS-IP-DT-170086 | GRT-XS00-P0LDB-130038 | [Condensate Filter System]_SYSTEM DESCRIPTION | A | 2017-05-30 | 15 | A | 2017-06-14 | Close
261 | GRT-DS-IP-DT-170086 | GRT-CC07-P0LDB-130039 | [Condensate Filter System]_CALCULATION SHEET | A | 2017-05-30 | 15 | A | 2017-06-14 | Close
262 | GRT-DS-IP-DT-170082 | GRT-XG07-P0LBA-110300 | [Steam, Feedwater & condensate system]_PROCESS FLOW DIAGRAM | B | 2017-05-30 | 49 | DEEMED APPROVAL | 2017-07-18 | Close
263 | GRT-DS-IP-DT-170082 | GRT-XG07-P0PA-110304 | [Aux. & closed Cooling Water System]_PROCESS FLOW DIAGRAM | B | 2017-05-30 | 49 | DEEMED APPROVAL | 2017-07-18 | Close
264 | GRT-DS-IP-DT-170082 | GRT-XG02-P0LA-110002 | [Symbol & Legend]_P&I DIAGRAM | 0 | 2017-05-30 | 0 | APPROVED | 2017-05-30 | Close
265 | GRT-DS-IP-DT-170083 | GRT-XN00-P0SCA-120028 | [Air Compressor]_VALVE LIST | A | 2017-05-30 | 87 | A | 2017-08-25 | Close
266 | GRT-DS-IP-DT-170083 | GRT-YL00-P0SCA-120023 | [Air Compressor]_INSTRUMENT LIST | A | 2017-05-30 | 87 | A | 2017-08-25 | Close
267 | GRT-DS-IP-DT-170083 | GRT-CV03-P0SCA-120024 | [Air Compressor]_INSTRUMENT SPECIFICATION | A | 2017-05-30 | 87 | A | 2017-08-25 | Close
268 | GRT-DS-IP-DT-170087 | GRT-YD00-P0LAC-122002 | [HP Feed Water Pump]_GENERAL ARRANGEMENT DRAWING | A | 2017-05-30 | 15 | A | 2017-06-14 | Close
269 | GRT-DS-IP-DT-170087 | GRT-YK10-P0LAC-122004 | [HP Feed Water Pump]_SECTIONAL DRAWING FOR PUMP | A | 2017-05-30 | 15 | A | 2017-06-14 | Close
270 | GRT-DS-IP-DT-170087 | GRT-YD00-P0LAC-122502 | [LP Feed Water Pump]_GENERAL ARRANGEMENT DRAWING | A | 2017-05-30 | 15 | A | 2017-06-14 | Close
271 | GRT-DS-IP-DT-170087 | GRT-YK10-P0LAC-122504 | [LP Feed Water Pump]_SECTIONAL DRAWING FOR PUMP | A | 2017-05-30 | 15 | A | 2017-06-14 | Close
272 | GRT-DS-IP-DT-170088 | GRT-XB02-P1H-300018 | [HRSG]_FOUNDATION LOADING & LOCATION DRAWING FOR BLOWDOWN TANK | B | 2017-06-02 | 52 | DEEMED APPROVAL | 2017-07-24 | Close
273 | GRT-DS-IP-DT-170089 | GRT-XB00-P0MA-200008 | STG Loads plan - Levels | A | 2017-06-02 | 12 | I | 2017-06-14 | Close
274 | GRT-DS-IP-DT-170090 | GRT-QM01-P0ZEN-040001 | Shop Inspection and Test Plan for Manufacturing | B | 2017-06-02 | 12 | C | 2017-06-14 | Close
284 | GRT-DS-IP-DT-170093 | GRT-YL01-P0SCA-120019 | [Air Compressor]_PLC HARDWIRED IO LIST | A | 2017-06-02 | 62 | B | 2017-08-03 | Close
285 | GRT-DS-IP-DT-170093 | GRT-YL01-P0SCA-120020 | [Air Compressor]_DATALINK INTERFACE IO LIST | A | 2017-06-02 | 62 | B | 2017-08-03 | Close
286 | GRT-DS-IP-DT-170094 | GRT-YK08-P0LAA-420001 | Outline Drawing for Deaerator & Feedwater Storage Tank | B | 2017-06-02 | 58 | A | 2017-07-30 | Close
287 | GRT-DS-IP-DT-170094 | GRT-CV03-P0LAA-420002 | Datasheet for Deaerator & Feedwater Storage Tank | B | 2017-06-02 | 58 | A | 2017-07-30 | Close
275 | GRT-DS-IP-DT-170091 | GRT-YS00-P0ZEN-163301 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram - Index | 0 | 2017-06-05 | 0 | APPROVED | 2017-06-05 | Close
276 | GRT-DS-IP-DT-170091 | GRT-YS00-P0ZEN-163302 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Motor Operated Valve (Internal MCC) | 0 | 2017-06-05 | 0 | APPROVED | 2017-06-05 | Close
277 | GRT-DS-IP-DT-170091 | GRT-YS00-P0ZEN-163303 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Pneumatic Shut-off Valve (Double Coil SOV) | 0 | 2017-06-05 | 0 | APPROVED | 2017-06-05 | Close
278 | GRT-DS-IP-DT-170091 | GRT-YS00-P0ZEN-163304 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Pneumatic Shut-off Valve (Single Coil SOV) | 0 | 2017-06-05 | 0 | APPROVED | 2017-06-05 | Close
279 | GRT-DS-IP-DT-170091 | GRT-YS00-P0ZEN-163305 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Modulating Control Actuator | 0 | 2017-06-05 | 0 | APPROVED | 2017-06-05 | Close
280 | GRT-DS-IP-DT-170091 | GRT-YS00-P0ZEN-163306 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Analog Input | 0 | 2017-06-05 | 0 | APPROVED | 2017-06-05 | Close
281 | GRT-DS-IP-DT-170091 | GRT-YS00-P0ZEN-163307 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Analog Output | 0 | 2017-06-05 | 0 | APPROVED | 2017-06-05 | Close
282 | GRT-DS-IP-DT-170091 | GRT-YS00-P0ZEN-163308 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Binary Input | 0 | 2017-06-05 | 0 | APPROVED | 2017-06-05 | Close
283 | GRT-DS-IP-DT-170091 | GRT-YS00-P0ZEN-163309 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Binary Output | 0 | 2017-06-05 | 0 | APPROVED | 2017-06-05 | Close
288 | GRT-DS-IP-DT-170095 | GRT-XH01-P0UMA-144521 | [Steam Turbine Building_Piping]_Piping Arrangement | A | 2017-06-05 | 32 | A | 2017-07-07 | Close
289 | GRT-DS-IP-DT-170095 | GRT-XH01-P0UZT-144522 | [Pipe Rack_Piping]_Piping Arrangement | A | 2017-06-05 | 32 | B | 2017-07-07 | Close
290 | GRT-DS-IP-DT-170095 | GRT-XH01-P0UTG-144523 | [N2 Gas Shelter_Piping]_Piping Arrangement | A | 2017-06-05 | 32 | A | 2017-07-07 | Close
291 | GRT-DS-IP-DT-170096 | GRT-UE00-P0ZEN-100003 | General Arrangement of Steam Turbine Building Ground Floor | B | 2017-06-05 | 15 | C | 2017-06-20 | Close
292 | GRT-DS-IP-DT-170096 | GRT-UE00-P0ZEN-100004 | General Arrangement of Steam Turbine Building Mezzanine Floor | B | 2017-06-05 | 15 | C | 2017-06-20 | Close
293 | GRT-DS-IP-DT-170096 | GRT-UE00-P0ZEN-100005 | General Arrangement of Steam Turbine Building Operating Floor | B | 2017-06-05 | 15 | C | 2017-06-20 | Close
294 | GRT-DS-IP-DT-170096 | GRT-UE00-P0ZEN-100006 | General Arrangement of Steam Turbine Building Deaerator Floor | B | 2017-06-05 | 15 | C | 2017-06-20 | Close
295 | GRT-DS-IP-DT-170096 | GRT-UE00-P0ZEN-100007 | General Arrangement of Steam Turbine Building Basement Floor | B | 2017-06-05 | 15 | C | 2017-06-20 | Close
296 | GRT-DS-IP-DT-170096 | GRT-UE00-P0ZEN-100008 | General Arrangement of Steam Turbine Building Section A-A | B | 2017-06-05 | 15 | C | 2017-06-20 | Close
297 | GRT-DS-IP-DT-170096 | GRT-UE00-P0ZEN-100009 | General Arrangement of Steam Turbine Building Section B-B | B | 2017-06-05 | 15 | A | 2017-06-20 | Close
298 | GRT-DS-IP-DT-170097 | GRT-CN00-P0ZEN-110104 | [Plant Overall]_Hazardous Area Classification | A | 2017-06-05 | 42 | A | 2017-07-17 | Close
299 | GRT-DS-IP-DT-170098 | GRT-YR01-P0ZEN-110105 | [HP & LP steam system]_Pressure drop calculation | B | 2017-06-08 | 28 | B | 2017-07-06 | Close
300 | GRT-DS-IP-DT-170098 | GRT-CN00-P0ZEN-110106 | [Steam drain system]_Flash tank calculation | B | 2017-06-08 | 28 | B | 2017-07-06 | Close
301 | GRT-DS-IP-DT-170098 | GRT-XW03-P0QJA-111001 | [N2 Gas System_Design]_sizing Calculation | B | 2017-06-08 | 28 | B | 2017-07-06 | Close
302 | GRT-DS-IP-DT-170092 | GRT-XW03-P0PCC-113010 | [Aux. Cooling Water Pump_Design]_SIZING CALCULATION FOR AUXILIARY COOLING WATER PUMP | B | 2017-06-08 | 28 | B | 2017-07-06 | Close
303 | GRT-DS-IP-DT-170092 | GRT-XW03-P0PGB-113110 | [CCWP_Design]_SIZING CALCULATION FOR CLOSED COOLING WATER PUMP | B | 2017-06-08 | 28 | B | 2017-07-06 | Close
304 | GRT-DS-IP-DT-170099 | GRT-DF04-P1H-300002 | [HRSG]_STRESS ANALYSIS ISOMETRIC DRAWING FOR CRITICAL PIPING | A | 2017-06-08 | 29 | B | 2017-07-07 | Close
305 | GRT-DS-IP-DT-170100 | GRT-YD00-P0PCC-113001 | [Aux. Cooling Water Pump]_GENERAL ARRANGEMENT DRAWING FOR AUXILIARY COOLING WATER PUMP | A | 2017-06-08 | 39 | A | 2017-07-17 | Close
306 | GRT-DS-IP-DT-170100 | GRT-YT01-P0PCC-113002 | [Aux. Cooling Water Pump]_DATA SHEET FOR AUXILIARY COOLING WATER PUMP | A | 2017-06-08 | 39 | B | 2017-07-17 | Close
307 | GRT-DS-IP-DT-170100 | GRT-YK10-P0PCC-113003 | [Aux. Cooling Water Pump]_Pump Sectional Drawing | A | 2017-06-08 | 39 | A | 2017-07-17 | Close
308 | GRT-DS-IP-DT-170100 | GRT-YD00-P0PGB-113101 | [CCWP ]_GENERAL ARRANGEMENT DRAWING FOR CLOSED COOLING WATER PUMP | A | 2017-06-08 | 39 | A | 2017-07-17 | Close
309 | GRT-DS-IP-DT-170100 | GRT-YT01-P0PGB-113102 | [CCWP ]_DATA SHEET FOR CLOSED COOLING WATER PUMP | A | 2017-06-08 | 39 | B | 2017-07-17 | Close
310 | GRT-DS-IP-DT-170100 | GRT-YK10-P0PGB-113103 | [CCWP ]_Pump Sectional Drawing | A | 2017-06-08 | 39 | A | 2017-07-17 | Close
311 | GRT-DS-IP-DT-170101 | GRT-XW03-P0LC-110501 | [CEP_Design]_sizing Calculation | 0 | 2017-06-08 | 0 | APPROVED | 2017-06-08 | Close
312 | GRT-DS-IP-DT-170102 | GRT-YF00-P0SCA-120021 | [Air Compressor]_CONTROL LOGIC & LOOP DIAGRAM | A | 2017-06-14 | 50 | C | 2017-08-03 | Close
313 | GRT-DS-IP-DT-170102 | GRT-YK00-P0SCA-120025 | [Air Compressor]_INSTRUMENTATION HOOK - UP DRAWING | A | 2017-06-14 | 50 | A | 2017-08-03 | Close
314 | GRT-DS-IP-DT-170102 | GRT-XW01-P0SCA-120029 | [Air Compressor]_VALVE SPECIFICATION | A | 2017-06-14 | 22 | I | 2017-07-06 | Close
315 | GRT-DS-IP-DT-170103 | GRT-CV03-P0ZEN-162301 | [VMS]_Technical Specification & Datasheet for Vibration Monitoring System | A | 2017-06-14 | 72 | B | 2017-08-25 | Close
316 | GRT-DS-IP-DT-170104 | GRT-YT01-P0PCC-113004 | [Aux. Cooling Water Pump]_DATA SHEET FOR AUXILIARY COOLING WATER PUMP MOTOR | A | 2017-06-14 | 22 | B | 2017-07-06 | Close
317 | GRT-DS-IP-DT-170104 | GRT-YD00-P0PCC-113005 | [Aux. Cooling Water Pump]_OUTLINE DRAWING FOR AUXILIARY COOLING WATER PUMP MOTOR | A | 2017-06-14 | 22 | B | 2017-07-06 | Close
318 | GRT-DS-IP-DT-170104 | GRT-YD00-P0PCC-113007 | [Aux. Cooling Water Pump]_MAIN TERMINAL BOX DRAWING FOR AUXILIARY COOLING WATER PUMP MOTOR | A | 2017-06-14 | 22 | A | 2017-07-06 | Close
319 | GRT-DS-IP-DT-170104 | GRT-YT01-P0PGB-113104 | [CCWP ]_DATA SHEET FOR CLOSED COOLING WATER PUMP MOTOR | A | 2017-06-14 | 22 | B | 2017-07-06 | Close
320 | GRT-DS-IP-DT-170104 | GRT-YD00-P0PGB-113105 | [CCWP ]_OUTLINE DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | A | 2017-06-14 | 22 | B | 2017-07-06 | Close
321 | GRT-DS-IP-DT-170104 | GRT-YD00-P0PGB-113107 | [CCWP ]_MAIN TERMINAL BOX DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | A | 2017-06-14 | 22 | A | 2017-07-06 | Close
322 | GRT-DS-IP-DT-170105 | GRT-XG02-P1H-300020 | [HRSG]_P&I DIAGRAM | B | 2017-06-14 | 22 | B | 2017-07-06 | Close
323 | GRT-DS-IP-DT-170105 | GRT-XS00-P1H-300032 | [HRSG]_BLOWDOWN SYSTEM SUMMARY | B | 2017-06-14 | 22 | A | 2017-07-06 | Close
324 | GRT-DS-IP-DT-170105 | GRT-YD00-P1H-300034 | [HRSG]_PRESSURE PART ARRANGEMENT | B | 2017-06-14 | 22 | I | 2017-07-06 | Close
325 | GRT-DS-IP-DT-170106 | GRT-YV02-P0SCA-120022 | [Air Compressor]_I&C WIRING DIAGRAMS | A | 2017-06-14 | 50 | B | 2017-08-03 | Close
326 | GRT-DS-IP-DT-170106 | GRT-YF02-P0SCA-120026 | [Air Compressor]_PLC PANEL DRAWING | A | 2017-06-14 | 50 | C | 2017-08-03 | Close
327 | GRT-DS-IP-DT-170108 | GRT-XW01-P0LBA-110200 | [HP & LP steam system]_DESIGN CRITERIA | B | 2017-06-14 | 22 | A | 2017-07-06 | Close
328 | GRT-DS-IP-DT-170108 | GRT-XW01-P0LBG-110201 | [AUX Steam System]_DESIGN CRITERIA | B | 2017-06-14 | 22 | A | 2017-07-06 | Close
329 | GRT-DS-IP-DT-170109 | GRT-YD00-P0MA-200006 | [STG]_General Arrangement Drawing | B | 2017-06-14 | 22 | A | 2017-07-06 | Close
331 | GRT-DS-IP-DT-170107 | GRT-DE00-P0ZEN-144501 | [Piping General]_Piping Insulation Specification (BOP) | 0 | 2017-06-14 | 2 | APPROVED | 2017-06-16 | Close
334 | GRT-DS-IP-DT-170113 | GRT-XS00-P0SC-120004 | [Compressed air system]_SYSTEM DESCRIPTION FOR COMPRESSED AIR SYSTEM | 0 | 2017-06-14 | 2 | APPROVED | 2017-06-16 | Close
330 | GRT-DS-IP-DT-170110 | GRT-XW01-P0ZEN-161001 | [INC_Plant_Overall_Design]_I&C General Design Criteria | B | 2017-06-20 | 66 | B | 2017-08-25 | Close
332 | GRT-DS-IP-DT-170111 | GRT-MA01-P0ZEN-161002 | [INC_Plant_Overall_Design]_Plant Control System Configuration Diagram | B | 2017-06-20 | 52 | B | 2017-08-11 | Close
333 | GRT-DS-IP-DT-170112 | GRT-YU02-P0SCA-120014 | [Air Compressor]_SINGLE LINE DIAGRAM | A | 2017-06-20 | 27 | B | 2017-07-17 | Close
335 | GRT-DS-IP-DT-170114 | GRT-XG02-P0SC-120001 | [Compressed air system]_P&I DIAGRAM FOR COMPRESSED AIR SYSTEM | B | 2017-06-20 | 40 | B | 2017-07-30 | Close
336 | GRT-DS-IP-DT-170114 | GRT-XG02-P0SC-120002 | [Compressed air system]_P&I DIAGRAM FOR INSTRUMENT AIR SYSTEM | B | 2017-06-20 | 40 | A | 2017-07-30 | Close
337 | GRT-DS-IP-DT-170114 | GRT-XG02-P0SC-120003 | [Compressed air system]_P&I DIAGRAM FOR SERVICE AIR SYSTEM | B | 2017-06-20 | 40 | A | 2017-07-30 | Close
338 | GRT-DS-IP-DT-170115 | GRT-YU04-P0ZEN-161003 | [INC_Plant_Overall_Design]_Plant Control Block Diagram | B | 2017-06-20 | 40 | C | 2017-07-30 | Close
339 | GRT-DS-IP-DT-170116 | GRT-YD00-P0PGB-400040 | Outline Drawing for CCW Heat Exchanger | B | 2017-06-20 | 40 | B | 2017-07-30 | Close
340 | GRT-DS-IP-DT-170117 | GRT-XW03-P0SC-120006 | [Compressed air system]_SIZING CALCULATION_COMPRESSED AIR SYSTEM | B | 2017-06-20 | 34 | B | 2017-07-24 | Close
342 | GRT-DS-IP-DT-170121 | GRT-XG02-P0MAJ-460101 | P & ID For Condenser Vacuum Pump | A | 2017-06-20 | 40 | A | 2017-07-30 | Close
343 | GRT-DS-IP-DT-170121 | GRT-XG02-P0MAJ-460201 | P & ID For Water Box Vacuum Pump | A | 2017-06-20 | 40 | B | 2017-07-30 | Close
344 | GRT-DS-IP-DT-170119 | GRT-MA02-P0ZEN-161006 | [INC_Interface]_3rd Party Data-link Interface Concept Diagram | B | 2017-06-20 | 66 | A | 2017-08-25 | Close
345 | GRT-DS-IP-DT-170120 | GRT-XK00-P0ZEN-144511 | [Piping General]_Typical Installation Drawing for Pipe Support | A | 2017-06-20 | 40 | B | 2017-07-30 | Close
346 | GRT-DS-IP-DT-170120 | GRT-XJ00-P0LBA-140001 | Piping ISO (Large Bore) - HP Steam | A | 2017-06-20 | 40 | I | 2017-07-30 | Close
347 | GRT-DS-IP-DT-170120 | GRT-XJ00-P0LBA-140002 | Piping ISO (Large Bore) - LP Steam | A | 2017-06-20 | 40 | I | 2017-07-30 | Close
348 | GRT-DS-IP-DT-170120 | GRT-XJ00-P0LAB-140005 | Piping ISO (Large Bore) - Feedwater | A | 2017-06-20 | 40 | I | 2017-07-30 | Close
349 | GRT-DS-IP-DT-170120 | GRT-XJ00-P0LCA-140006 | Piping ISO (Large Bore) - Condensate | A | 2017-06-20 | 40 | I | 2017-07-30 | Close
350 | GRT-DS-IP-DT-170122 | GRT-XB00-P0MA-200007 | [STG]_Foundation load plan | 0 | 2017-06-20 | 0 | APPROVED | 2017-06-20 | Close
351 | GRT-DS-IP-DT-170123 | GRT-XW01-P0QJA-110206 | [N2 Gas system]_Design Criteria | 0 | 2017-06-20 | 0 | APPROVED | 2017-06-20 | Close
352 | GRT-DS-IP-DT-170123 | GRT-XS00-P0LBA-110400 | [HP & LP steam system]_SYSTEM DESCRIPTION | 0 | 2017-06-20 | 0 | APPROVED | 2017-06-20 | Close
353 | GRT-DS-IP-DT-170123 | GRT-XS00-P0LBG-110401 | [AUX Steam System]_SYSTEM DESCRIPTION | 0 | 2017-06-20 | 0 | APPROVED | 2017-06-20 | Close
354 | GRT-DS-IP-DT-170123 | GRT-XS00-P0QJA-110406 | [N2 Gas system]_system description | 0 | 2017-06-20 | 0 | APPROVED | 2017-06-20 | Close
355 | GRT-DS-IP-DT-170124 | GRT-YD00-P0SM-123001 | [Crane & Hoist(DHI)]_HOIST_GA DRAWING FOR HOISTS | A | 2017-06-21 | 39 | B | 2017-07-30 | Close
356 | GRT-DS-IP-DT-170124 | GRT-YT01-P0SM-123002 | [Crane & Hoist(DHI)]_HOIST_DATA SHEETS FOR HOISTS | A | 2017-06-21 | 39 | B | 2017-07-30 | Close
357 | GRT-DS-IP-DT-170125 | GRT-YD00-P1H-300036 | [HRSG]_EQUIPMENT OUTLINE DRAWING FOR BLOWDOWN TANK | A | 2017-06-21 | 33 | I | 2017-07-24 | Close
358 | GRT-DS-IP-DT-170125 | GRT-YF00-P1H-300044 | [HRSG]_SEQUENCES & CONTROLS | A | 2017-06-21 | 39 | C | 2017-07-30 | Close
359 | GRT-DS-IP-DT-170125 | GRT-DE00-P1H-300067 | [HRSG]_PIPING MATERIAL CLASSIFICATION | A | 2017-06-21 | 33 | B | 2017-07-24 | Close
360 | GRT-DS-IP-DT-170126 | GRT-XB00-P0MA-200001 | [STG]_Foundation - Shape & Anchoring | 0 | 2017-06-21 | 1 | APPROVED | 2017-06-22 | Close
410 | GRT-DS-IP-DT-170145 | GRT-XG05-P0ZEN-110001 | [Plant Overall]_HEAT BALANCE DIAGRAMS | 0 | 2017-07-04 | 15 | APPROVED AS NOTED | 2017-07-19 | Close
381 | GRT-DS-IP-DT-170135 | GRT-XW01-P0LA-110202 | [Feedwater system]_DESIGN CRITERIA | 0 | 2017-07-05 | 14 | APPROVED AS NOTED | 2017-07-19 | Close
382 | GRT-DS-IP-DT-170135 | GRT-XW01-P0LC-110203 | [Condensate system]_DESIGN CRITERIA | 0 | 2017-07-05 | 14 | APPROVED AS NOTED | 2017-07-19 | Close
402 | GRT-DS-IP-DT-170143 | GRT-VN03-P1H-300011 | [HRSG]_TYPICAL HANDRAIL DETAIL FOR STEEL STRUCTURE | 0 | 2017-07-05 | 14 | APPROVED | 2017-07-19 | Close
403 | GRT-DS-IP-DT-170143 | GRT-XS00-P1H-300031 | [HRSG]_SYSTEM DESCRIPTION | 0 | 2017-07-05 | 14 | APPROVED AS NOTED | 2017-07-19 | Close
404 | GRT-DS-IP-DT-170143 | GRT-YU02-P1H-300066 | [HRSG]_ELECTRICAL SINGLE LINE DIAGRAMS | 0 | 2017-07-05 | 14 | APPROVED | 2017-07-19 | Close
361 | GRT-DS-IP-DT-170128 | GRT-QA00-P0H-040005 | [HRSG]_NDE Procedure for HRSG Heat Exchanger | A | 2017-07-06 | 18 | I | 2017-07-24 | Close
362 | GRT-DS-IP-DT-170128 | GRT-QA00-P0H-040002 | [HRSG]_NDE Procedure for HRSG HP Drum | A | 2017-07-06 | 18 | I | 2017-07-24 | Close
363 | GRT-DS-IP-DT-170128 | GRT-QA00-P0H-040003 | [HRSG]_NDE Procedure for HRSG LP Drum | A | 2017-07-06 | 18 | I | 2017-07-24 | Close
364 | GRT-DS-IP-DT-170128 | GRT-QA00-P0H-040004 | [HRSG]_Heat Treatment Procedure for HRSG Heat Exchanger | A | 2017-07-06 | 18 | I | 2017-07-24 | Close
365 | GRT-DS-IP-DT-170129 | GRT-YD05-P0SCA-120018 | [Air Compressor]_PLC HMI GRAPHICS | A | 2017-07-06 | 36 | A | 2017-08-11 | Close
366 | GRT-DS-IP-DT-170129 | GRT-XF00-P0SCA-120027 | [Air Compressor]_NAME PLATE DRAWING | A | 2017-07-06 | 36 | C | 2017-08-11 | Close
367 | GRT-DS-IP-DT-170130 | GRT-DP00-P0ZEN-070001 | Painting specification | A | 2017-07-06 | 18 | B | 2017-07-24 | Close
368 | GRT-DS-IP-DT-170131 | GRT-YT01-P0LCB-121005 | [Condensate Extraction Pump]_MECHANICAL SEAL SPECIFICATION | A | 2017-07-06 | 18 | B | 2017-07-24 | Close
369 | GRT-DS-IP-DT-170131 | GRT-YT01-P0LCB-121007 | [Condensate Extraction Pump]_SUCTION STRAINER SPECIFICATION | A | 2017-07-06 | 18 | I | 2017-07-24 | Close
370 | GRT-DS-IP-DT-170131 | GRT-YL22-P0LCB-121012 | [Condensate Extraction Pump]_NAME PLATE DRAWING | A | 2017-07-06 | 19 | I | 2017-07-25 | Close
371 | GRT-DS-IP-DT-170132 | GRT-XS00-P0LA-110402 | [Feedwater system]_SYSTEM DESCRIPTION | 0 | 2017-07-06 | 13 | APPROVED | 2017-07-19 | Close
372 | GRT-DS-IP-DT-170127 | GRT-XG02-P0QU-130024 | [Sampling System]_P&ID | A | 2017-07-06 | 24 | B | 2017-07-30 | Close
373 | GRT-DS-IP-DT-170127 | GRT-XA00-P0QU-130025 | [Sampling System]_GENERAL ARRANGEMENT DRAWING | A | 2017-07-06 | 24 | A | 2017-07-30 | Close
374 | GRT-DS-IP-DT-170127 | GRT-XS00-P0QU-130026 | [Sampling System]_SYSTEM DESCRIPTION | A | 2017-07-06 | 24 | B | 2017-07-30 | Close
375 | GRT-DS-IP-DT-170133 | GRT-YT01-P0PGB-113200 | [Blowdown Cooler]_DATA SHEET FOR PLATE TYPE HEAT EXCHANGER | A | 2017-07-06 | 18 | B | 2017-07-24 | Close
376 | GRT-DS-IP-DT-170133 | GRT-YD00-P0PGB-113201 | [Blowdown Cooler]_OUTLINE DRAWING FOR PLATE TYPE HEAT EXCHANGER | A | 2017-07-06 | 18 | B | 2017-07-24 | Close
377 | GRT-DS-IP-DT-170134 | GRT-XV00-P0MA-200010 | [STG]_List of pipelines | B | 2017-07-06 | 40 | DEEMED APPROVAL | 2017-08-15 | Close
378 | GRT-DS-IP-DT-170134 | GRT-XN00-P0MA-200011 | [STG]_List of valves | B | 2017-07-06 | 112 | DEEMED APPROVAL | 2017-10-26 | Close
379 | GRT-DS-IP-DT-170134 | GRT-YK09-P0MA-200020 | [STG]_Functional description | B | 2017-07-06 | 62 | DEEMED APPROVAL | 2017-09-06 | Close
380 | GRT-DS-IP-DT-170134 | GRT-XG08-P0MA-200005 | [STG]_P&I Diagrams | B | 2017-07-06 | 76 | DEEMED APPROVAL | 2017-09-20 | Close
383 | GRT-DS-IP-DT-170137 | GRT-YT01-P1H-300056 | [HRSG]_DATA & BOM OF INSULATION FOR DRUM AND BLOWDOWN TANK | A | 2017-07-06 | 49 | I | 2017-08-24 | Close
384 | GRT-DS-IP-DT-170137 | GRT-YT01-P1H-300058 | [HRSG]_PERFORMANCE AND OPERATIONAL DATA | B | 2017-07-06 | 49 | A | 2017-08-24 | Close
385 | GRT-DS-IP-DT-170138 | GRT-QA00-P0H-040006 | [HRSG]_Shop Quality Manual for HRSG | A | 2017-07-06 | 18 | I | 2017-07-24 | Close
396 | GRT-DS-IP-DT-170139 | GRT-QM01-P0ZEN-040001 | Shop Inspection and Test Plan for Manufacturing | C | 2017-07-12 | 70 | DEEMED APPROVAL | 2017-09-20 | Close
397 | GRT-DS-IP-DT-170140 | GRT-YT01-P0MAJ-460104 | Technical Data Sheet | A | 2017-07-12 | 12 | B | 2017-07-24 | Close
398 | GRT-DS-IP-DT-170141 | GRT-DE00-P0ZEN-144500 | [Piping General]_Piping material specification (BOP) | B | 2017-07-12 | 30 | A | 2017-08-11 | Close
399 | GRT-DS-IP-DT-170141 | GRT-YT10-P0ZEN-144502 | [Piping General]_Pipe Thickness Calculation (BOP) | B | 2017-07-12 | 18 | A | 2017-07-30 | Close
400 | GRT-DS-IP-DT-170142 | GRT-YL00-P0LCB-121010 | [Condensate Extraction Pump]_INSTRUMENT LIST | A | 2017-07-12 | 18 | A | 2017-07-30 | Close
401 | GRT-DS-IP-DT-170142 | GRT-YK00-P0LCB-121011 | [Condensate Extraction Pump]_INSTRUMENTATION HOOK - UP DRAWING | A | 2017-07-12 | 18 | A | 2017-07-30 | Close
405 | GRT-DS-IP-DT-170144 | GRT-YK08-P0MAG-410001 | Condenser_General Layout | B | 2017-07-12 | 70 | DEEMED APPROVAL | 2017-09-20 | Close
406 | GRT-DS-IP-DT-170144 | GRT-YK08-P0MAG-410002 | Condenser_General Arrangement | B | 2017-07-12 | 70 | DEEMED APPROVAL | 2017-09-20 | Close
407 | GRT-DS-IP-DT-170144 | GRT-XL00-P0MAG-410003 | Condenser_Connection List | B | 2017-07-12 | 70 | DEEMED APPROVAL | 2017-09-20 | Close
408 | GRT-DS-IP-DT-170144 | GRT-XL00-P0MAG-410004 | Condenser_Connection Detail | B | 2017-07-12 | 70 | DEEMED APPROVAL | 2017-09-20 | Close
409 | GRT-DS-IP-DT-170144 | GRT-YT01-P0MAG-410007 | Condenser_Data Sheet | B | 2017-07-12 | 70 | DEEMED APPROVAL | 2017-09-20 | Close
386 | GRT-DS-IP-DT-170136 | GRT-XL00-P0ZEN-144503 | [Piping General]_Piping Line List (BOP) | B | 2017-07-13 | 29 | A | 2017-08-11 | Close
387 | GRT-DS-IP-DT-170136 | GRT-XL00-P0ZEN-144504 | [Piping General]_Piping Specialty List (BOP) | B | 2017-07-13 | 29 | A | 2017-08-11 | Close
388 | GRT-DS-IP-DT-170136 | GRT-XN00-P0ZEN-144505 | [Piping General]_Manual Valve List (BOP) | B | 2017-07-13 | 29 | A | 2017-08-11 | Close
389 | GRT-DS-IP-DT-170136 | GRT-DF04-P0ZEN-144512 | [Piping General]_Stress Analysis Report for HP steam system | A | 2017-07-13 | 29 | A | 2017-08-11 | Close
390 | GRT-DS-IP-DT-170136 | GRT-DF04-P0ZEN-144513 | [Piping General]_Stress Analysis Report for LP steam system | A | 2017-07-13 | 29 | A | 2017-08-11 | Close
391 | GRT-DS-IP-DT-170136 | GRT-DF04-P0ZEN-144514 | [Piping General]_Stress Analysis Report for Aux.steam system | A | 2017-07-13 | 29 | A | 2017-08-11 | Close
392 | GRT-DS-IP-DT-170136 | GRT-DF04-P0ZEN-144515 | [Piping General]_Stress Analysis Report for Feedwater system | A | 2017-07-13 | 29 | A | 2017-08-11 | Close
393 | GRT-DS-IP-DT-170136 | GRT-XJ00-P0LBG-140003 | Piping ISO (Large Bore) - Aux. Steam | A | 2017-07-13 | 29 | I | 2017-08-11 | Close
394 | GRT-DS-IP-DT-170136 | GRT-XJ00-P0LCM-140004 | Piping ISO (Large Bore) - Steam drain | A | 2017-07-13 | 29 | I | 2017-08-11 | Close
395 | GRT-DS-IP-DT-170136 | GRT-XJ00-P0PGB-140008 | Piping ISO (Large Bore) - CCW | A | 2017-07-13 | 29 | I | 2017-08-11 | Close
411 | GRT-DS-IP-DT-170146 | GRT-DM02-P1H-300005 | [HRSG]_GENERAL NOTE FOR STEEL STRUCTURE | B | 2017-07-13 | 48 | DEEMED APPROVAL | 2017-08-30 | Close
412 | GRT-DS-IP-DT-170146 | GRT-UE00-P1H-300007 | [HRSG]_ARRANGEMENT OF CASING & FIELD ERECTION | B | 2017-07-13 | 11 | DEEMED APPROVAL | 2017-07-24 | Close
413 | GRT-DS-IP-DT-170146 | GRT-UE00-P1H-300008 | [HRSG]_ARRANGEMENT OF INLET DUCT | B | 2017-07-13 | 8 | DEEMED APPROVAL | 2017-07-21 | Close
414 | GRT-DS-IP-DT-170146 | GRT-UE00-P1H-300009 | [HRSG]_ARRANGEMENT OF MAIN STACK& FIELD ERECTION | B | 2017-07-13 | 48 | DEEMED APPROVAL | 2017-08-30 | Close
415 | GRT-DS-IP-DT-170146 | GRT-VN03-P1H-300010 | [HRSG]_TYPICAL PLATFORM DETAIL FOR STEEL STRUCTURE | B | 2017-07-13 | 48 | DEEMED APPROVAL | 2017-08-30 | Close
416 | GRT-DS-IP-DT-170146 | GRT-VN03-P1H-300012 | [HRSG]_TYPICAL LADDER DETAIL FOR STEEL STRUCTURE | B | 2017-07-13 | 42 | DEEMED APPROVAL | 2017-08-24 | Close
417 | GRT-DS-IP-DT-170146 | GRT-VN03-P1H-300013 | [HRSG]_ARRANGEMENT FOR PLATFORM STRUCTURE | B | 2017-07-13 | 48 | DEEMED APPROVAL | 2017-08-30 | Close
418 | GRT-DS-IP-DT-170146 | GRT-XB02-P1H-300014 | [HRSG]_COLUMN LOCATION FOR STEEL STRUCTURE AND STACK (WITH PLAN VIEW) | B | 2017-07-13 | 11 | DEEMED APPROVAL | 2017-07-24 | Close
419 | GRT-DS-IP-DT-170146 | GRT-XB02-P1H-300015 | [HRSG]_FOUNDATION LOAD TABLE FOR STEEL STRUCTURE AND STACK | B | 2017-07-13 | 11 | DEEMED APPROVAL | 2017-07-24 | Close
420 | GRT-DS-IP-DT-170146 | GRT-XB02-P1H-300016 | [HRSG]_BASE PLATE AND ANCHOR BOLTS DETAIL FOR STEEL STRUCTURE | B | 2017-07-13 | 11 | DEEMED APPROVAL | 2017-07-24 | Close
421 | GRT-DS-IP-DT-170146 | GRT-XN00-P1H-300029 | [HRSG]_VALVE LIST | B | 2017-07-13 | 8 | DEEMED APPROVAL | 2017-07-21 | Close
422 | GRT-DS-IP-DT-170147 | GRT-XJ00-P0PAB-140007 | Piping ISO (Large Bore) - Aux. cooling water | A | 2017-07-13 | 29 | I | 2017-08-11 | Close
423 | GRT-DS-IP-DT-170147 | GRT-XJ00-P0SCA-140009 | Piping ISO (Large Bore) - Compressed air | A | 2017-07-13 | 29 | I | 2017-08-11 | Close
424 | GRT-DS-IP-DT-170147 | GRT-XJ00-P0MAA-140010 | Piping ISO (Large Bore) - ST Misc. | A | 2017-07-13 | 29 | I | 2017-08-11 | Close
425 | GRT-DS-IP-DT-170148 | GRT-YK08-P0MAJ-460100 | General Arrangement Drawing For Condenser Vacuum Pump | A | 2017-07-13 | 29 | B | 2017-08-11 | Close
426 | GRT-DS-IP-DT-170148 | GRT-XK00-P0MAJ-460112 | Outline & Sectional Drawing For Condenser Vacuum Pump | A | 2017-07-13 | 29 | B | 2017-08-11 | Close
427 | GRT-DS-IP-DT-170148 | GRT-YK08-P0MAJ-460200 | General Arrangement Drawing For Water Box Vacuum Pump | A | 2017-07-13 | 29 | B | 2017-08-11 | Close
428 | GRT-DS-IP-DT-170148 | GRT-XK00-P0MAJ-460212 | Outline & Sectional Drawing For Water Box Vacuum Pump | A | 2017-07-13 | 29 | B | 2017-08-11 | Close
436 | GRT-DS-IP-DT-170151 | GRT-XB00-P0MA-200002 | [STG]_Foundation - Embedded Elements | C | 2017-07-13 | 42 | I | 2017-08-24 | Close
437 | GRT-DS-IP-DT-170151 | GRT-YL19-P0MA-200038 | [STG]_Electrical load list | B | 2017-07-13 | 42 | B | 2017-08-24 | Close
438 | GRT-DS-IP-DT-170151 | GRT-YK00-P0MA-200040 | [STG]_I&C Lay-outs | A | 2017-07-13 | 42 | I | 2017-08-24 | Close
444 | GRT-DS-IP-DT-170156 | GRT-XJ00-P0LBA-143001 | Piping ISO (Small Bore) - HP Steam | A | 2017-07-13 | 29 | I | 2017-08-11 | Close
445 | GRT-DS-IP-DT-170156 | GRT-XJ00-P0LBA-143002 | Piping ISO (Small Bore) - LP Steam | A | 2017-07-13 | 29 | I | 2017-08-11 | Close
446 | GRT-DS-IP-DT-170156 | GRT-XJ00-P0LCM-143004 | Piping ISO (Small Bore) - Steam drain | A | 2017-07-13 | 29 | I | 2017-08-11 | Close
450 | GRT-DS-IP-DT-170161 | GRT-XG02-P0QC-130001 | [Chemical Dosing System]_P&ID | A | 2017-07-13 | 29 | B | 2017-08-11 | Close
451 | GRT-DS-IP-DT-170161 | GRT-XA00-P0QC-130002 | [Chemical Dosing System]_GENERAL ARRANGEMENT DRAWING | A | 2017-07-13 | 29 | A | 2017-08-11 | Close
452 | GRT-DS-IP-DT-170161 | GRT-XS00-P0QC-130003 | [Chemical Dosing System]_SYSTEM DESCRIPTION | A | 2017-07-13 | 29 | B | 2017-08-11 | Close
453 | GRT-DS-IP-DT-170161 | GRT-CC07-P0QC-130004 | [Chemical Dosing System]_CALCULATION SHEET | A | 2017-07-13 | 29 | B | 2017-08-11 | Close
454 | GRT-DS-IP-DT-170161 | GRT-YD00-P0QC-130005 | [Chemical Dosing System]_CONTROL PANEL ARRANGEMENT DRAWING | A | 2017-07-13 | 60 | A | 2017-09-11 | Close
455 | GRT-DS-IP-DT-170161 | GRT-YF02-P0QC-130006 | [Chemical Dosing System]_CONTROL CONFIGURATION DIAGRAM | A | 2017-07-13 | 60 | C | 2017-09-11 | Close
456 | GRT-DS-IP-DT-170161 | GRT-YL00-P0QC-130007 | [Chemical Dosing System]_INSTRUMENT LIST | A | 2017-07-13 | 60 | A | 2017-09-11 | Close
457 | GRT-DS-IP-DT-170161 | GRT-XN00-P0QC-130008 | [Chemical Dosing System]_VALVE LIST | A | 2017-07-13 | 29 | I | 2017-08-11 | Close
458 | GRT-DS-IP-DT-170162 | GRT-YF01-P0ZEN-161004 | [INC_Plant_Overall_Design]_Plant Protection & Interlock Diagram | B | 2017-07-13 | 17 | A | 2017-07-30 | Close
459 | GRT-DS-IP-DT-170163 | GRT-YD00-P0LDB-130040 | [Condensate Filter System]_CONTROL PANEL ARRANGEMENT DRAWING | A | 2017-07-13 | 17 | A | 2017-07-30 | Close
460 | GRT-DS-IP-DT-170163 | GRT-YF02-P0LDB-130041 | [Condensate Filter System]_CONTROL CONFIGURATION DIAGRAM | A | 2017-07-13 | 17 | A | 2017-07-30 | Close
461 | GRT-DS-IP-DT-170163 | GRT-YL00-P0LDB-130042 | [Condensate Filter System]_INSTRUMENT LIST | A | 2017-07-13 | 17 | B | 2017-07-30 | Close
462 | GRT-DS-IP-DT-170158 | GRT-XN00-P0LDB-130043 | [Condensate Filter System]_VALVE LIST | A | 2017-07-13 | 29 | I | 2017-08-11 | Close
463 | GRT-DS-IP-DT-170158 | GRT-XB02-P0LDB-130044 | [Condensate Filter System]_FOUNDATION AND LOADING DATA | A | 2017-07-13 | 89 | DEEMED APPROVAL | 2017-10-10 | Close
464 | GRT-DS-IP-DT-170158 | GRT-YK10-P0LDB-130045 | [Condensate Filter System]_EQUIPMENT ASSEMBLY DRAWING | A | 2017-07-13 | 29 | I | 2017-08-11 | Close
465 | GRT-DS-IP-DT-170158 | GRT-XH01-P0LDB-130046 | [Condensate Filter System]_PIPING ARRANGEMENT DRAWING | A | 2017-07-13 | 29 | I | 2017-08-11 | Close
468 | GRT-DS-IP-DT-170165 | GRT-UE00-P1H-300006 | [HRSG]_GENERAL ARRANGEMENT | B | 2017-07-13 | 11 | B | 2017-07-24 | Close
469 | GRT-DS-IP-DT-170165 | GRT-XG02-P1H-300020 | [HRSG]_P&I DIAGRAM | C | 2017-07-13 | 29 | B | 2017-08-11 | Close
470 | GRT-DS-IP-DT-170165 | GRT-YD00-P1H-300034 | [HRSG]_PRESSURE PART ARRANGEMENT | C | 2017-07-13 | 29 | I | 2017-08-11 | Close
474 | GRT-DS-IP-DT-170167 | GRT-YF00-P0ZEN-161202 | [INC_Other_Sys_Logic&Loop]_Control Logic Diagram - Typical Function | B | 2017-07-13 | 63 | DEEMED APPROVAL | 2017-09-14 | Close
475 | GRT-DS-IP-DT-170168 | GRT-YD00-P0LCB-121001 | [Condensate Extraction Pump]_GENERAL ARRANGEMENT DRAWING | B | 2017-07-13 | 29 | A | 2017-08-11 | Close
476 | GRT-DS-IP-DT-170168 | GRT-XG02-P0LCB-121002 | [Condensate Extraction Pump]_P&I DIAGRAM | B | 2017-07-13 | 29 | A | 2017-08-11 | Close
477 | GRT-DS-IP-DT-170168 | GRT-YT01-P0LCB-121003 | [Condensate Extraction Pump]_DATA SHEET & CHARACTERISTIC CURVE | B | 2017-07-13 | 29 | A | 2017-08-11 | Close
478 | GRT-DS-IP-DT-170168 | GRT-YD00-P0LCB-121008 | [Condensate Extraction Pump]_FOUNDATION DRAWINGS | B | 2017-07-13 | 33 | DEEMED APPROVAL | 2017-08-15 | Close
429 | GRT-DS-IP-DT-170149 | GRT-XW01-P0PA-110204 | [Aux. Cooling Water System]_DESIGN CRITERIA | 0 | 2017-07-17 | 2 | APPROVED AS NOTED | 2017-07-19 | Close
430 | GRT-DS-IP-DT-170149 | GRT-XW01-P0PG-110205 | [Closed cooling water system]_DESIGN CRITERIA | 0 | 2017-07-17 | 2 | APPROVED AS NOTED | 2017-07-19 | Close
431 | GRT-DS-IP-DT-170149 | GRT-XS00-P0PA-110404 | [Aux. Cooling Water System]_SYSTEM DESCRIPTION | 0 | 2017-07-17 | 2 | APPROVED AS NOTED | 2017-07-19 | Close
432 | GRT-DS-IP-DT-170149 | GRT-XS00-P0PG-110405 | [Closed cooling water system]_SYSTEM DESCRIPTION | 0 | 2017-07-17 | 2 | APPROVED AS NOTED | 2017-07-19 | Close
439 | GRT-DS-IP-DT-170152 | GRT-YS05-P0ZEN-162701 | [INC_Design_Criteria_Cable]_Typical I&C Cable Installation Drawing for Field Instrument | 0 | 2017-07-17 | 0 | APPROVED AS NOTED | 2017-07-17 | Close
440 | GRT-DS-IP-DT-170152 | GRT-YS05-P0ZEN-162702 | [INC_Design_Criteria_Cable]_Typical I&C Cable Installation Drawing for Control Valve | 0 | 2017-07-17 | 0 | APPROVED AS NOTED | 2017-07-17 | Close
441 | GRT-DS-IP-DT-170152 | GRT-YS05-P0ZEN-162703 | [INC_Design_Criteria_Cable]_Typical I&C Cable Installation Drawing for MOV | 0 | 2017-07-17 | 0 | APPROVED AS NOTED | 2017-07-17 | Close
442 | GRT-DS-IP-DT-170152 | GRT-YS05-P0ZEN-162704 | [INC_Design_Criteria_Cable]_Typical I&C Cable Installation Drawing for Instrument Rack and Junction Box | 0 | 2017-07-17 | 0 | APPROVED AS NOTED | 2017-07-17 | Close
443 | GRT-DS-IP-DT-170152 | GRT-YS05-P0ZEN-162705 | [INC_Design_Criteria_Cable]_Typical I&C Cable Installation Drawing for Conduit Support | 0 | 2017-07-17 | 0 | APPROVED AS NOTED | 2017-07-17 | Close
447 | GRT-DS-IP-DT-170157 | GRT-XW03-P0LA-110500 | [BFP_Design]_sizing Calculation | 0 | 2017-07-17 | 0 | APPROVED AS NOTED | 2017-07-17 | Close
448 | GRT-DS-IP-DT-170159 | GRT-XW01-P0LBA-110200 | [HP & LP steam system]_DESIGN CRITERIA | 0 | 2017-07-17 | 0 | APPROVED | 2017-07-17 | Close
449 | GRT-DS-IP-DT-170159 | GRT-XW01-P0LBG-110201 | [AUX Steam System]_DESIGN CRITERIA | 0 | 2017-07-17 | 0 | APPROVED | 2017-07-17 | Close
466 | GRT-DS-IP-DT-170164 | GRT-DF04-P1H-300002 | [HRSG]_STRESS ANALYSIS ISOMETRIC DRAWING FOR CRITICAL PIPING | 0 | 2017-07-17 | 63 | APPROVED AS NOTED | 2017-09-18 | Close
467 | GRT-DS-IP-DT-170164 | GRT-XS00-P1H-300032 | [HRSG]_BLOWDOWN SYSTEM SUMMARY | 0 | 2017-07-17 | 63 | APPROVED | 2017-09-18 | Close
471 | GRT-DS-IP-DT-170166 | GRT-YF00-P0ZEN-161201 | [INC_Other_Sys_Logic&Loop]_Control Logic Diagram - Symbol & Legend | 0 | 2017-07-17 | 0 | APPROVED | 2017-07-17 | Close
472 | GRT-DS-IP-DT-170166 | GRT-YF00-P0ZEN-161301 | [INC_Other_Sys_Logic&Loop]_Control Loop Diagram - Symbol & Legend | 0 | 2017-07-17 | 0 | APPROVED | 2017-07-17 | Close
473 | GRT-DS-IP-DT-170166 | GRT-YF00-P0ZEN-161302 | [INC_Other_Sys_Logic&Loop]_Control Loop Diagram - Typical Function | 0 | 2017-07-17 | 0 | APPROVED | 2017-07-17 | Close
479 | GRT-DS-IP-DT-170170 | GRT-XG02-P0LBA-110003 | [HP & LP steam system]_P&I DIAGRAM | 0 | 2017-07-17 | 0 | REJECTED | 2017-07-17 | Close
480 | GRT-DS-IP-DT-170170 | GRT-XG02-P0LBG-110004 | [AUX Steam System]_P&I DIAGRAM | 0 | 2017-07-17 | 0 | REJECTED | 2017-07-17 | Close
481 | GRT-DS-IP-DT-170170 | GRT-XG02-P0LCM-110005 | [Steam drain system]_P&ID DIAGRAM | 0 | 2017-07-17 | 0 | REJECTED | 2017-07-17 | Close
482 | GRT-DS-IP-DT-170170 | GRT-XG02-P0QJA-110010 | [N2 Gas system]_P&I DIAGRAM | 0 | 2017-07-17 | 0 | REJECTED | 2017-07-17 | Close
485 | GRT-DS-IP-DT-170172 | GRT-YS00-P0ZEN-163310 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Electrical System | A | 2017-07-17 | 56 | C | 2017-09-11 | Close
433 | GRT-DS-IP-DT-170150 | GRT-XG07-P0PA-110304 | [Aux. & Closed Cooling Water System]_PROCESS FLOW DIAGRAM | C | 2017-07-18 | 37 | A | 2017-08-24 | Close
434 | GRT-DS-IP-DT-170150 | GRT-XW03-P0PCC-113010 | [Aux. Cooling Water Pump_Design]_SIZING CALCULATION FOR AUXILIARY COOLING WATER PUMP | C | 2017-07-18 | 37 | A | 2017-08-24 | Close
435 | GRT-DS-IP-DT-170150 | GRT-XW03-P0PGB-113110 | [CCWP_Design]_SIZING CALCULATION FOR CLOSED COOLING WATER PUMP | C | 2017-07-18 | 37 | A | 2017-08-24 | Close
483 | GRT-DS-IP-DT-170171 | GRT-YL00-P0MA-200045 | [STG]_List of signals | B | 2017-07-18 | 12 | A | 2017-07-30 | Close
484 | GRT-DS-IP-DT-170171 | GRT-XB00-P0MA-200003 | [STG]_Foundation - Static & Dynamic Calculation | B | 2017-07-18 | 6 | I | 2017-07-24 | Close
491 | GRT-DS-IP-DT-170173 | GRT-XG02-P0LA-110006 | [Feedwater system]_P&I DIAGRAM | 0 | 2017-07-18 | 1 | REJECTED | 2017-07-19 | Close
492 | GRT-DS-IP-DT-170173 | GRT-XG02-P0LC-110007 | [Condensate system]_P&I DIAGRAM | 0 | 2017-07-18 | 1 | REJECTED | 2017-07-19 | Close
493 | GRT-DS-IP-DT-170174 | GRT-XG07-P0LBA-110300 | [Steam, Feedwater & Condensate system]_PROCESS FLOW DIAGRAM | 0 | 2017-07-18 | 1 | APPROVED AS NOTED | 2017-07-19 | Close
497 | GRT-DS-IP-DT-170178 | GRT-YK08-P0LAA-420001 | Outline Drawing for Deaerator & Feedwater Storage Tank | 0 | 2017-07-18 | 1 | APPROVED AS NOTED | 2017-07-19 | Close
498 | GRT-DS-IP-DT-170178 | GRT-CV03-P0LAA-420002 | Datasheet for Deaerator & Feedwater Storage Tank | 0 | 2017-07-18 | 1 | APPROVED AS NOTED | 2017-07-19 | Close
486 | GRT-DS-IP-DT-170169 | GRT-XJ00-P0LBG-143003 | Piping ISO (Small Bore) - Aux. Steam | A | 2017-07-19 | 11 | I | 2017-07-30 | Close
487 | GRT-DS-IP-DT-170169 | GRT-XJ00-P0LAB-143005 | Piping ISO (Small Bore) - Feedwater | A | 2017-07-19 | 11 | I | 2017-07-30 | Close
488 | GRT-DS-IP-DT-170169 | GRT-XJ00-P0LCA-143006 | Piping ISO (Small Bore) - Condensate | A | 2017-07-19 | 11 | I | 2017-07-30 | Close
489 | GRT-DS-IP-DT-170169 | GRT-XJ00-P0PAB-143015 | Piping ISO (Small Bore) - Cooling water | A | 2017-07-19 | 11 | I | 2017-07-30 | Close
490 | GRT-DS-IP-DT-170169 | GRT-XJ00-P0QC-143016 | Piping ISO (Small Bore) - Chemical dosing | A | 2017-07-19 | 11 | I | 2017-07-30 | Close
494 | GRT-DS-IP-DT-170175 | GRT-YR01-P0ZEN-110105 | [HP & LP steam system]_Pressure drop calculation | 0 | 2017-07-19 | 0 | APPROVED AS NOTED | 2017-07-19 | Close
495 | GRT-DS-IP-DT-170175 | GRT-CN00-P0ZEN-110106 | [Steam drain system]_Flash tank calculation | 0 | 2017-07-19 | 0 | APPROVED AS NOTED | 2017-07-19 | Close
496 | GRT-DS-IP-DT-170175 | GRT-XW03-P0QJA-111001 | [N2 Gas System_Design]_sizing Calculation | 0 | 2017-07-19 | 0 | APPROVED AS NOTED | 2017-07-19 | Close
499 | GRT-DS-IP-DT-170177 | GRT-CN00-P0ZEN-110100 | [Plant Overall]_OPERATION PHILOSOPHY OF OVERALL PLANT | A | 2017-07-19 | 54 | C | 2017-09-11 | Close
341 | GRT-DS-IP-DT-170118 | GRT-XS00-P0SC-120005 | [Compressed air system]_DESIGN CRITERIA FOR COMPRESSED AIR SYSTEM | 1 | 2017-07-20 | 273 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
503 | GRT-DS-IP-DT-170154 | GRT-CV03-P0ZEN-163705 | [Instrument Installation materials(DHI)]_Technical Specification for Instrument Installation Materials | A | 2017-07-21 | 55 | DEEMED APPROVAL | 2017-09-14 | Close
504 | GRT-DS-IP-DT-170186 | GRT-YL00-P0ZEN-163700 | [Field Instruments(DHI)]_Field Instrument List for BOP | A | 2017-07-21 | 52 | A | 2017-09-11 | Close
505 | GRT-DS-IP-DT-170187 | GRT-YL22-P0PCC-113008 | [Aux. Cooling Water Pump]_NAMEPLATE DRAWING FOR AUXILIARY COOLING WATER PUMP | A | 2017-07-21 | 84 | DEEMED APPROVAL | 2017-10-13 | Close
506 | GRT-DS-IP-DT-170187 | GRT-YL22-P0PGB-113108 | [CCWP ]_NAMEPLATE DRAWING FOR CLOSED COOLING WATER PUMP | A | 2017-07-21 | 84 | DEEMED APPROVAL | 2017-10-13 | Close
510 | GRT-DS-IP-DT-170176 | GRT-XG02-P0PA-110008 | [Aux. Cooling Water System]_P&I DIAGRAM | C | 2017-07-21 | 31 | DEEMED APPROVAL | 2017-08-21 | Close
511 | GRT-DS-IP-DT-170176 | GRT-XG02-P0PG-110009 | [Closed cooling water system]_P&I DIAGRAM | C | 2017-07-21 | 33 | DEEMED APPROVAL | 2017-08-23 | Close
512 | GRT-DS-IP-DT-170183 | GRT-XL00-P1H-300028 | [HRSG]_LINE LIST | B | 2017-07-21 | 13 | A | 2017-08-03 | Close
513 | GRT-DS-IP-DT-170183 | GRT-YD00-P1H-300039 | [HRSG]_SPEC. & DRAWING FOR SAFETY & RELIEF VALVE | A | 2017-07-21 | 13 | B | 2017-08-03 | Close
514 | GRT-DS-IP-DT-170183 | GRT-YD00-P1H-300040 | [HRSG]_SPEC. & DRAWING FOR STACK DAMPER | A | 2017-07-21 | 13 | A | 2017-08-03 | Close
515 | GRT-DS-IP-DT-170183 | GRT-YD00-P1H-300041 | [HRSG]_SPEC. & DRAWING FOR SILENCER | A | 2017-07-21 | 13 | A | 2017-08-03 | Close
516 | GRT-DS-IP-DT-170183 | GRT-YD04-P1H-300042 | [HRSG]_CABLE TRAY & RACEWAY LAYOUT DIAGRAM | A | 2017-07-21 | 13 | I | 2017-08-03 | Close
517 | GRT-DS-IP-DT-170183 | GRT-YK01-P1H-300048 | [HRSG]_INSTRUMENT INSTALLATION DETAIL DRAWINGS | A | 2017-07-21 | 52 | A | 2017-09-11 | Close
518 | GRT-DS-IP-DT-170183 | GRT-YT01-P1H-300059 | [HRSG]_MOV DATASHEET & DRAWINGS | A | 2017-07-21 | 13 | A | 2017-08-03 | Close
519 | GRT-DS-IP-DT-170183 | GRT-YT01-P1H-300060 | [HRSG]_CV DATASHEET & DRAWINGS | A | 2017-07-21 | 13 | A | 2017-08-03 | Close
520 | GRT-DS-IP-DT-170183 | GRT-YT01-P1H-300061 | [HRSG]_DESH. DATASHEET & DRAWINGS | A | 2017-07-21 | 13 | A | 2017-08-03 | Close
521 | GRT-DS-IP-DT-170184 | GRT-UE00-P1H-300008 | [HRSG]_ARRANGEMENT OF INLET DUCT | C | 2017-07-21 | 13 | I | 2017-08-03 | Close
522 | GRT-DS-IP-DT-170184 | GRT-XN00-P1H-300029 | [HRSG]_VALVE LIST | C | 2017-07-21 | 13 | I | 2017-08-03 | Close
529 | GRT-DS-IP-DT-170191 | GRT-XJ00-P0PAB-143007 | Piping ISO (Small Bore) - Aux. cooling water | A | 2017-07-21 | 13 | I | 2017-08-03 | Close
530 | GRT-DS-IP-DT-170191 | GRT-XJ00-P0PGB-143008 | Piping ISO (Small Bore) - CCW | A | 2017-07-21 | 13 | I | 2017-08-03 | Close
531 | GRT-DS-IP-DT-170191 | GRT-XJ00-P0QJA-143009 | Piping ISO (Small Bore) - N2 | A | 2017-07-21 | 13 | I | 2017-08-03 | Close
532 | GRT-DS-IP-DT-170191 | GRT-XJ00-P0LCW-143014 | Piping ISO (Small Bore) - Seal Water | A | 2017-07-21 | 13 | I | 2017-08-03 | Close
533 | GRT-DS-IP-DT-170192 | GRT-YK09-P0LCB-121004 | [Condensate Extraction Pump]_PUMP SECTIONAL DRAWING | B | 2017-07-21 | 13 | A | 2017-08-03 | Close
534 | GRT-DS-IP-DT-170192 | GRT-YT01-P0LCB-121006 | [Condensate Extraction Pump]_COUPLING SPECIFICATION | B | 2017-07-21 | 13 | I | 2017-08-03 | Close
535 | GRT-DS-IP-DT-170193 | GRT-YT01-P0PCC-113002 | [Aux. Cooling Water Pump]_DATA SHEET FOR AUXILIARY | B | 2017-07-21 | 40 | DEEMED APPROVAL | 2017-08-30 | Close
536 | GRT-DS-IP-DT-170193 | GRT-YT01-P0PCC-113004 | [Aux. Cooling Water Pump]_DATA SHEET FOR AUXILIARY COOLING WATER PUMP MOTOR | B | 2017-07-21 | 40 | DEEMED APPROVAL | 2017-08-30 | Close
537 | GRT-DS-IP-DT-170193 | GRT-YD00-P0PCC-113005 | [Aux. Cooling Water Pump]_OUTLINE DRAWING FOR AUXILIARY COOLING WATER PUMP MOTOR | B | 2017-07-21 | 40 | DEEMED APPROVAL | 2017-08-30 | Close
538 | GRT-DS-IP-DT-170193 | GRT-YT01-P0PGB-113102 | [CCWP ]_DATA SHEET FOR CLOSED COOLING WATER PUMP | B | 2017-07-21 | 40 | DEEMED APPROVAL | 2017-08-30 | Close
539 | GRT-DS-IP-DT-170193 | GRT-YT01-P0PGB-113104 | [CCWP ]_DATA SHEET FOR CLOSED COOLING WATER PUMP MOTOR | B | 2017-07-21 | 40 | DEEMED APPROVAL | 2017-08-30 | Close
540 | GRT-DS-IP-DT-170193 | GRT-YD00-P0PGB-113105 | [CCWP ]_OUTLINE DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | B | 2017-07-21 | 40 | DEEMED APPROVAL | 2017-08-30 | Close
500 | GRT-DS-IP-DT-170179 | GRT-XH01-P0UMA-144521 | [Steam Turbine Building_Piping]_Piping Arrangement | 0 | 2017-07-24 | 0 | APPROVED | 2017-07-24 | Close
501 | GRT-DS-IP-DT-170179 | GRT-XH01-P0UTG-144523 | [N2 Gas Shelter_Piping]_Piping Arrangement | 0 | 2017-07-24 | 0 | APPROVED | 2017-07-24 | Close
502 | GRT-DS-IP-DT-170182 | GRT-YE03-P0ZEN-161114 | [DCS]_Grounding Concept & Drawing | 0 | 2017-07-24 | 0 | APPROVED | 2017-07-24 | Close
507 | GRT-DS-IP-DT-170188 | GRT-YU04-P0ZEN-161003 | [INC_Plant_Overall_Design]_Plant Control Block Diagram | 0 | 2017-07-24 | 3 | APPROVED | 2017-07-27 | Close
508 | GRT-DS-IP-DT-170188 | GRT-XW01-P0ZEN-161001 | [INC_Plant_Overall_Design]_I&C General Design Criteria | 0 | 2017-07-24 | 3 | APPROVED AS NOTED | 2017-07-27 | Close
509 | GRT-DS-IP-DT-170189 | GRT-MA01-P0ZEN-161002 | [INC_Plant_Overall_Design]_Plant Control System Configuration Diagram | 0 | 2017-07-24 | 3 | APPROVED | 2017-07-27 | Close
523 | GRT-DS-IP-DT-170185 | GRT-UE00-P1H-300007 | [HRSG]_ARRANGEMENT OF CASING & FIELD ERECTION | 0 | 2017-07-24 | 8 | APPROVED | 2017-08-01 | Close
524 | GRT-DS-IP-DT-170185 | GRT-XB02-P1H-300014 | [HRSG]_COLUMN LOCATION FOR STEEL STRUCTURE AND STACK (WITH PLAN VIEW) | 0 | 2017-07-24 | 8 | APPROVED AS NOTED | 2017-08-01 | Close
525 | GRT-DS-IP-DT-170185 | GRT-XB02-P1H-300015 | [HRSG]_FOUNDATION LOAD TABLE FOR STEEL STRUCTURE AND STACK | 0 | 2017-07-24 | 8 | APPROVED AS NOTED | 2017-08-01 | Close
526 | GRT-DS-IP-DT-170185 | GRT-XB02-P1H-300016 | [HRSG]_BASE PLATE AND ANCHOR BOLTS DETAIL FOR STEEL STRUCTURE | 0 | 2017-07-24 | 8 | APPROVED AS NOTED | 2017-08-01 | Close
527 | GRT-DS-IP-DT-170185 | GRT-XB02-P1H-300018 | [HRSG]_FOUNDATION LOADING & LOCATION DRAWING FOR BLOWDOWN TANK | 0 | 2017-07-24 | 8 | APPROVED | 2017-08-01 | Close
528 | GRT-DS-IP-DT-170185 | GRT-YT01-P1H-300058 | [HRSG]_PERFORMANCE AND OPERATIONAL DATA | 0 | 2017-07-24 | 32 | APPROVED | 2017-08-25 | Close
550 | GRT-DS-IP-DT-170190 | GRT-XK00-P0ZEN-144511 | [Piping General]_Typical Installation Drawing for Pipe Support | 0 | 2017-07-24 | 0 | APPROVED AS NOTED | 2017-07-24 | Close
555 | GRT-DS-IP-DT-170199 | GRT-XH01-P0UZT-144522 | [Pipe rack_Piping]_Piping Arrangement | 0 | 2017-07-24 | 0 | APPROVED AS NOTED | 2017-07-24 | Close
562 | GRT-DS-IP-DT-170202 | GRT-XW03-P0SC-120006 | [Compressed air system]_SIZING CALCULATION_COMPRESSED AIR SYSTEM | 0 | 2017-07-24 | 0 | APPROVED AS NOTED | 2017-07-24 | Close
541 | GRT-DS-IP-DT-170194 | GRT-XN00-P0QU-130029 | [Sampling System]_VALVE LIST | A | 2017-07-26 | 26 | B | 2017-08-21 | Close
542 | GRT-DS-IP-DT-170194 | GRT-YF02-P0QU-130027 | [Sampling System]_CONTROL CONFIGURATION DIAGRAM | A | 2017-07-26 | 47 | C | 2017-09-11 | Close
543 | GRT-DS-IP-DT-170194 | GRT-YL00-P0QU-130028 | [Sampling System]_INSTUMENT LIST | A | 2017-07-26 | 47 | C | 2017-09-11 | Close
544 | GRT-DS-IP-DT-170195 | GRT-YD00-P0PGB-430030 | OUNLINE DRAWING FOR CCW EXPANSION HEAD TANK | C | 2017-07-26 | 26 | B | 2017-08-21 | Close
545 | GRT-DS-IP-DT-170195 | GRT-YD00-P0PGB-430020 | OUNLINE DRAWING FOR CCW CHEMICAL ADDITIVE TANK | C | 2017-07-26 | 26 | B | 2017-08-21 | Close
546 | GRT-DS-IP-DT-170195 | GRT-YD00-P0LCM-430010 | OUNLINE DRAWING FOR ATMOSPHERIC FLASH TANK | C | 2017-07-26 | 26 | B | 2017-08-21 | Close
547 | GRT-DS-IP-DT-170196 | GRT-YD00-P0PGB-400040 | OUTLINE DRAWING FOR CCW HEAT EXCHANGER | C | 2017-07-26 | 26 | B | 2017-08-21 | Close
548 | GRT-DS-IP-DT-170155 | GRT-YD08-P0UMA-164311 | [Steam Turbine Building_INC_ILD]_BOP_Instrument Location Drawing | A | 2017-07-26 | 47 | C | 2017-09-11 | Close
551 | GRT-DS-IP-DT-170180 | GRT-YT01-P0LB-111100 | [Bypass Valve & PRDS]_DATA SHEET FOR BYPASS AND PRDS | A | 2017-07-26 | 26 | B | 2017-08-21 | Close
552 | GRT-DS-IP-DT-170180 | GRT-YK08-P0LB-111101 | [Bypass Valve & PRDS]_OUTLINE DRAWING FOR BYPASS AND PRDS | A | 2017-07-26 | 26 | B | 2017-08-21 | Close
553 | GRT-DS-IP-DT-170180 | GRT-YK09-P0LB-111106 | [Bypass Valve & PRDS]_Sectional drawing | A | 2017-07-26 | 26 | I | 2017-08-21 | Close
554 | GRT-DS-IP-DT-170153 | GRT-CV03-P0ZEN-163706 | [Local Boxes(DHI)]_Technical Specification for Junction Box & Racks | A | 2017-07-26 | 47 | A | 2017-09-11 | Close
556 | GRT-DS-IP-DT-170198 | GRT-XL35-P0LB-111109 | [Bypass Valve & PRDS]_Instrument List & Database Sheet | A | 2017-07-26 | 47 | C | 2017-09-11 | Close
557 | GRT-DS-IP-DT-170198 | GRT-YS18-P0LB-111111 | [Bypass Valve & PRDS]_Pneumatic Diagram | A | 2017-07-26 | 47 | I | 2017-09-11 | Close
558 | GRT-DS-IP-DT-170198 | GRT-YS00-P0LB-111112 | [Bypass Valve & PRDS]_Wiring Diagram | A | 2017-07-26 | 47 | I | 2017-09-11 | Close
559 | GRT-DS-IP-DT-170200 | GRT-XG02-P0SC-120001 | [Compressed air system]_P&I DIAGRAM FOR COMPRESSED AIR SYSTEM | C | 2017-07-26 | 26 | B | 2017-08-21 | Close
560 | GRT-DS-IP-DT-170200 | GRT-XG02-P0SC-120002 | [Compressed air system]_P&I DIAGRAM FOR INSTRUMENT AIR SYSTEM | C | 2017-07-26 | 26 | A | 2017-08-21 | Close
561 | GRT-DS-IP-DT-170200 | GRT-XG02-P0SC-120003 | [Compressed air system]_P&I DIAGRAM FOR SERVICE AIR SYSTEM | C | 2017-07-26 | 26 | A | 2017-08-21 | Close
563 | GRT-DS-IP-DT-170201 | GRT-XG02-P0SCA-120008 | [Air Compressor]_P&I DIAGRAM FOR AIR COMPRESSOR PACKAGE | B | 2017-07-26 | 47 | A | 2017-09-11 | Close
568 | GRT-DS-IP-DT-170205 | GRT-YT01-P0LDB-130047 | [Condensate Filter System]_TECHNICAL DATASHEET | A | 2017-07-26 | 26 | C | 2017-08-21 | Close
569 | GRT-DS-IP-DT-170205 | GRT-YT01-P0LDB-130050 | [Condensate Filter System]_VALVE DATA SHEET | A | 2017-07-26 | 26 | B | 2017-08-21 | Close
570 | GRT-DS-IP-DT-170205 | GRT-YT01-P0LDB-130051 | [Condensate Filter System]_INSTRUMENT DATA SHEET | A | 2017-07-26 | 47 | A | 2017-09-11 | Close
571 | GRT-DS-IP-DT-170206 | GRT-YL01-P0ZEN-161101 | [INC_DCS_IO]_DCS I/O Database | B | 2017-07-26 | 79 | DEEMED APPROVAL | 2017-10-13 | Close
572 | GRT-DS-IP-DT-170207 | GRT-YD06-P0ZEN-161113 | [INC_Plant_Overall_Design]_DCS Power Distribution Concept Diagram | B | 2017-07-26 | 47 | A | 2017-09-11 | Close
573 | GRT-DS-IP-DT-170208 | GRT-MA02-P0ZEN-161121 | [DCS]_LAN Configuration Diagram | B | 2017-07-26 | 47 | A | 2017-09-11 | Close
576 | GRT-DS-IP-DT-170211 | GRT-YK00-P0MA-200034 | [STG]_Hook ups | B | 2017-07-26 | 16 | I | 2017-08-11 | Close
577 | GRT-DS-IP-DT-170211 | GRT-YF00-P0MA-200036 | [STG]_Consumer schemes | B | 2017-07-26 | 16 | I | 2017-08-11 | Close
578 | GRT-DS-IP-DT-170211 | GRT-YL00-P0MA-200037 | [STG]_Measurement list | B | 2017-07-26 | 16 | I | 2017-08-11 | Close
564 | GRT-DS-IP-DT-170203 | GRT-XW01-P0SCA-120009 | [Air Compressor]_AIR COMPRESSOR SPECIFICATION | 0 | 2017-07-27 | 7 | APPROVED | 2017-08-03 | Close
565 | GRT-DS-IP-DT-170203 | GRT-XW01-P0SCA-120010 | [Air Compressor]_AIR DRYER SPECIFICATION | 0 | 2017-07-27 | 7 | APPROVED AS NOTED | 2017-08-03 | Close
566 | GRT-DS-IP-DT-170203 | GRT-XW01-P0SCA-120011 | [Air Compressor]_AIR RECEIVER SPECIFICATION | 0 | 2017-07-27 | 7 | APPROVED | 2017-08-03 | Close
567 | GRT-DS-IP-DT-170203 | GRT-XW01-P0SCA-120012 | [Air Compressor]_AIR FILTER SPECIFICATION | 0 | 2017-07-27 | 7 | APPROVED | 2017-08-03 | Close
574 | GRT-DS-IP-DT-170209 | GRT-YD07-P0ZEN-161122 | [DCS]_IO & Module Allocation | 0 | 2017-07-27 | 7 | APPROVED | 2017-08-03 | Close
575 | GRT-DS-IP-DT-170210 | GRT-CV03-P0ZEN-161110 | [DCS]_Functional Design Specification for Hardware | 0 | 2017-07-27 | 7 | APPROVED | 2017-08-03 | Close
579 | GRT-DS-IP-DT-170212 | GRT-YT02-P0LAC-122006 | [HP Feed Water Pump]_LIST AND DATA SHEET FOR INSTRUMENT | A | 2017-07-28 | 45 | A | 2017-09-11 | Close
580 | GRT-DS-IP-DT-170212 | GRT-YT02-P0LAC-122506 | [LP Feed Water Pump]_LIST AND DATA SHEET FOR INSTRUMENT | A | 2017-07-28 | 45 | A | 2017-09-11 | Close
581 | GRT-DS-IP-DT-170212 | GRT-YL22-P0LAC-122007 | [HP Feed Water Pump]_NAME PLATE DRAWING | A | 2017-07-28 | 24 | A | 2017-08-21 | Close
582 | GRT-DS-IP-DT-170212 | GRT-YL22-P0LAC-122507 | [LP Feed Water Pump]_NAME PLATE DRAWING | A | 2017-07-28 | 24 | A | 2017-08-21 | Close
590 | GRT-DS-IP-DT-170215 | GRT-QA00-P0H-040004 | [HRSG]_Heat Treatment Procedure for HRSG Heat Exchanger | B | 2017-07-28 | 27 | I | 2017-08-24 | Close
591 | GRT-DS-IP-DT-170216 | GRT-YD00-P0SCA-120007 | [Air Compressor]_AIR COMPRESSOR_GENERAL ARRANGEMENT DRAWING FOR AIR COMPRESSORS PACKAGE | B | 2017-07-28 | 27 | B | 2017-08-24 | Close
592 | GRT-DS-IP-DT-170216 | GRT-XB00-P0SCA-120013 | [Air Compressor]_FOUNDATION DRAWINGS | B | 2017-07-28 | 27 | I | 2017-08-24 | Close
610 | GRT-DS-IP-DT-170217 | GRT-YK08-P0LB-111102 | [Bypass Valve & PRDS]_OUTLINE DRAWING FOR HYDRAULIC POWER UNIT | A | 2017-07-28 | 45 | A | 2017-09-11 | Close
611 | GRT-DS-IP-DT-170217 | GRT-YS18-P0LB-111107 | [Bypass Valve & PRDS]_P&ID for HPU | A | 2017-07-28 | 45 | A | 2017-09-11 | Close
612 | GRT-DS-IP-DT-170217 | GRT-YT01-P0LB-111110 | [Bypass Valve & PRDS]_Data Sheet for HPU | A | 2017-07-28 | 45 | A | 2017-09-11 | Close
583 | GRT-DS-IP-DT-170213 | GRT-XL00-P0ZEN-144503 | [Piping General]_Piping Line List (BOP) | 0 | 2017-07-31 | 25 | APPROVED | 2017-08-25 | Close
584 | GRT-DS-IP-DT-170213 | GRT-XL00-P0ZEN-144504 | [Piping General]_Piping Specialty List (BOP) | 0 | 2017-07-31 | 25 | APPROVED | 2017-08-25 | Close
585 | GRT-DS-IP-DT-170213 | GRT-XN00-P0ZEN-144505 | [Piping General]_Manual Valve List (BOP) | 0 | 2017-07-31 | 25 | APPROVED | 2017-08-25 | Close
586 | GRT-DS-IP-DT-170214 | GRT-QA00-P0H-040002 | [HRSG]_NDE Procedure for HRSG HP Drum | 0 | 2017-07-31 | 11 | APPROVED | 2017-08-11 | Close
587 | GRT-DS-IP-DT-170214 | GRT-QA00-P0H-040003 | [HRSG]_NDE Procedure for HRSG LP Drum | 0 | 2017-07-31 | 11 | APPROVED | 2017-08-11 | Close
588 | GRT-DS-IP-DT-170214 | GRT-QA00-P0H-040005 | [HRSG]_NDE Procedure for HRSG Heat Exchanger | 0 | 2017-07-31 | 11 | APPROVED | 2017-08-11 | Close
589 | GRT-DS-IP-DT-170214 | GRT-QA00-P0H-040006 | [HRSG]_Shop Quality Manual for HRSG | 0 | 2017-07-31 | 11 | APPROVED | 2017-08-11 | Close
593 | GRT-DS-IP-DT-170218 | GRT-YF00-P0MAJ-161213 | [Condenser Vacuum Pump System _I&C_Logic]_Control Logic Diagram for BOP | 0 | 2017-07-31 | 25 | APPROVED AS NOTED | 2017-08-25 | Close
594 | GRT-DS-IP-DT-170218 | GRT-YF00-P0ZEN-161310 | [INC_Other_Sys_Logic&Loop]_Control Loop Diagram for Sampling & Chemical Dosing System | 0 | 2017-07-31 | 22 | APPROVED AS NOTED | 2017-08-22 | Close
595 | GRT-DS-IP-DT-170218 | GRT-YF00-P0MAJ-161313 | [Condenser Vacuum Pump System _I&C_Loop]_Control Loop Diagram for BOP | 0 | 2017-07-31 | 25 | APPROVED AS NOTED | 2017-08-25 | Close
596 | GRT-DS-IP-DT-170219 | GRT-YF00-P0LC-161206 | [Condensate system_I&C_Logic]_Control Logic Diagram for BOP | 0 | 2017-07-31 | 22 | APPROVED | 2017-08-22 | Close
549 | GRT-DS-IP-DT-170197 | GRT-CV03-P0ZEN-163704 | [Control Valves(DHI)]_Technical Specification & Datasheet for Control Valve - BOP | A | 2017-08-01 | 41 | A | 2017-09-11 | Close
597 | GRT-DS-IP-DT-170220 | GRT-YF00-P0LC-161306 | [Condensate system_I&C_Loop]_Control Loop Diagram for BOP | B | 2017-08-01 | 41 | A | 2017-09-11 | Close
598 | GRT-DS-IP-DT-170221 | GRT-XJ00-P0SCA-143010 | Piping ISO (Small Bore) - Compressed air | A | 2017-08-01 | 23 | I | 2017-08-24 | Close
599 | GRT-DS-IP-DT-170221 | GRT-XJ00-P0SCB-143011 | Piping ISO (Small Bore) - Service air | A | 2017-08-01 | 23 | I | 2017-08-24 | Close
600 | GRT-DS-IP-DT-170221 | GRT-XJ00-P0QFB-143012 | Piping ISO (Small Bore) - Instrument air | A | 2017-08-01 | 23 | I | 2017-08-24 | Close
601 | GRT-DS-IP-DT-170221 | GRT-XJ00-P0MAA-143013 | Piping ISO (Small Bore) - ST Misc. | A | 2017-08-01 | 23 | I | 2017-08-24 | Close
602 | GRT-DS-IP-DT-170221 | GRT-XJ00-P0QUA-143017 | Piping ISO (Small Bore) - Sampling | A | 2017-08-01 | 23 | I | 2017-08-24 | Close
603 | GRT-DS-IP-DT-170222 | GRT-YF00-P0ZEN-161401 | [INC_PMC]_Plant Master Control Diagram | A | 2017-08-01 | 41 | C | 2017-09-11 | Close
604 | GRT-DS-IP-DT-170223 | GRT-YF00-P1LBA-161203 | [HP & LP steam system_I&C_Logic]_Control Logic Diagram for BOP | B | 2017-08-01 | 41 | A | 2017-09-11 | Close
605 | GRT-DS-IP-DT-170223 | GRT-YF00-P0LBG-161204 | [AUX Steam System_I&C_Logic]_Control Logic Diagram for BOP | B | 2017-08-01 | 41 | A | 2017-09-11 | Close
606 | GRT-DS-IP-DT-170223 | GRT-YF00-P1LBA-161303 | [HP & LP steam system_I&C_Loop]_Control Loop Diagram for BOP | B | 2017-08-01 | 41 | A | 2017-09-11 | Close
607 | GRT-DS-IP-DT-170223 | GRT-YF00-P0LBG-161304 | [AUX Steam System_I&C_Loop]_Control Loop Diagram for BOP | B | 2017-08-01 | 41 | A | 2017-09-11 | Close
608 | GRT-DS-IP-DT-170224 | GRT-DE00-P0ZEN-144500 | [Piping General]_Piping material specification (BOP) | C | 2017-08-01 | 23 | A | 2017-08-24 | Close
609 | GRT-DS-IP-DT-170224 | GRT-YT10-P0ZEN-144502 | [Piping General]_Pipe Thickness Calculation (BOP) | C | 2017-08-01 | 23 | A | 2017-08-24 | Close
613 | GRT-DS-IP-DT-170225 | GRT-YT01-P0MAJ-460105 | Motor Data sheet and Characteristic Curves and Drawing For CVP | A | 2017-08-07 | 17 | C | 2017-08-24 | Close
614 | GRT-DS-IP-DT-170225 | GRT-YT01-P0MAJ-460106 | Heat Exchanger Drawing and Data Sheet For Condenser Vacuum Pump | A | 2017-08-07 | 14 | I | 2017-08-21 | Close
615 | GRT-DS-IP-DT-170225 | GRT-YT01-P0MAJ-460115 | Recirculation Pump Data Sheet and Characteristic Curves and Drawing For CVP | A | 2017-08-07 | 17 | C | 2017-08-24 | Close
616 | GRT-DS-IP-DT-170225 | GRT-PL03-P0MAJ-460120 | Terminal Point List For Condenser Vacuum Pump | A | 2017-08-07 | 14 | B | 2017-08-21 | Close
617 | GRT-DS-IP-DT-170225 | GRT-YL10-P0MAJ-460121 | Spare Part List For Condenser Vacuum Pump | A | 2017-08-07 | 14 | I | 2017-08-21 | Close
618 | GRT-DS-IP-DT-170225 | GRT-DA06-P0MAJ-460123 | Lubricant List For Condenser Vacuum Pump | A | 2017-08-07 | 14 | I | 2017-08-21 | Close
619 | GRT-DS-IP-DT-170225 | GRT-YL00-P0MAJ-460127 | Instrument Data sheet For Condenser Vacuum Pump | A | 2017-08-07 | 35 | A | 2017-09-11 | Close
620 | GRT-DS-IP-DT-170225 | GRT-YT01-P0MAJ-460205 | Motor Data sheet and Characteristic Curves and Drawing For WBVP | A | 2017-08-07 | 17 | C | 2017-08-24 | Close
621 | GRT-DS-IP-DT-170225 | GRT-YT01-P0MAJ-460206 | Heat Exchanger Drawing and Data Sheet For Water Box Vacuum Pump | A | 2017-08-07 | 14 | I | 2017-08-21 | Close
622 | GRT-DS-IP-DT-170225 | GRT-YT01-P0MAJ-460215 | Recirculation Pump Data Sheet and Characteristic Curves and Drawing For WBVP | A | 2017-08-07 | 17 | C | 2017-08-24 | Close
623 | GRT-DS-IP-DT-170225 | GRT-PL03-P0MAJ-460220 | Terminal Point List For Water Box Vacuum Pump | A | 2017-08-07 | 14 | B | 2017-08-21 | Close
624 | GRT-DS-IP-DT-170225 | GRT-YL10-P0MAJ-460221 | Spare Part List For Water Box Vacuum Pump | A | 2017-08-07 | 14 | I | 2017-08-21 | Close
625 | GRT-DS-IP-DT-170225 | GRT-DA06-P0MAJ-460223 | Lubricant List For Water Box Vacuum Pump | A | 2017-08-07 | 14 | I | 2017-08-21 | Close
626 | GRT-DS-IP-DT-170225 | GRT-YL00-P0MAJ-460227 | Instrument Data sheet For Water Box Vacuum Pump | A | 2017-08-07 | 35 | A | 2017-09-11 | Close
627 | GRT-DS-IP-DT-170225 | GRT-DA06-P0MAJ-460122 | Utility Consumption List For Condenser Vacuum Pump | A | 2017-08-07 | 14 | A | 2017-08-21 | Close
628 | GRT-DS-IP-DT-170225 | GRT-DA06-P0MAJ-460222 | Utility Consumption List For Water Box Vacuum Pump | A | 2017-08-07 | 14 | A | 2017-08-21 | Close
629 | GRT-DS-IP-DT-170204 | GRT-XG02-P0PAH-440001 | Condenser Tube Cleaning System_P & I Diagram | B | 2017-08-10 | 14 | A | 2017-08-24 | Close
630 | GRT-DS-IP-DT-170204 | GRT-YK08-P0PAH-440002 | Condenser Tube Cleaning System_Outline Drawing | B | 2017-08-10 | 14 | A | 2017-08-24 | Close
631 | GRT-DS-IP-DT-170204 | GRT-YK08-P0PAH-440003 | Condenser Tube Cleaning System_Outline Drawing for Ball Recirculation unit | B | 2017-08-10 | 14 | A | 2017-08-24 | Close
632 | GRT-DS-IP-DT-170204 | GRT-YT01-P0PAH-440008 | Condenser Tube Cleaning System_Technical Data Sheet | B | 2017-08-10 | 14 | B | 2017-08-24 | Close
633 | GRT-DS-IP-DT-170204 | GRT-XG02-P0PAH-440051 | CCW HEX Tube Cleaning System_P & I Diagram | B | 2017-08-10 | 14 | A | 2017-08-24 | Close
634 | GRT-DS-IP-DT-170204 | GRT-YK08-P0PAH-440052 | CCW HEX Tube Cleaning System_Outline Drawing | B | 2017-08-10 | 14 | A | 2017-08-24 | Close
635 | GRT-DS-IP-DT-170204 | GRT-YK08-P0PAH-440053 | CCW HEX Tube Cleaning System_Outline Drawing for Ball Recirculation unit | B | 2017-08-10 | 14 | A | 2017-08-24 | Close
636 | GRT-DS-IP-DT-170204 | GRT-YT01-P0PAH-440058 | CCW HEX Tube Cleaning System_Technical Data Sheet | B | 2017-08-10 | 14 | B | 2017-08-24 | Close
637 | GRT-DS-IP-DT-170204 | GRT-XG02-P0PBB-440101 | Debris Filter_P & I Diagram | B | 2017-08-10 | 14 | A | 2017-08-24 | Close
638 | GRT-DS-IP-DT-170204 | GRT-YK08-P0PBB-440102 | Debris Filter_Outline Drawing | B | 2017-08-10 | 14 | A | 2017-08-24 | Close
639 | GRT-DS-IP-DT-170204 | GRT-YT01-P0PBB-440103 | Debris Filter_Technical Data Sheet | B | 2017-08-10 | 14 | B | 2017-08-24 | Close
640 | GRT-DS-IP-DT-170226 | GRT-XV00-P0MA-200010 | [STG]_List of pipelines | 0 | 2017-08-15 | 10 | APPROVED | 2017-08-25 | Close
641 | GRT-DS-IP-DT-170226 | GRT-YK00-P0MA-200034 | [STG]_Hook ups | 0 | 2017-08-15 | 10 | APPROVED | 2017-08-25 | Close
642 | GRT-DS-IP-DT-170226 | GRT-YL19-P0MA-200038 | [STG]_Electrical load list | 0 | 2017-08-15 | 10 | APPROVED | 2017-08-25 | Close
643 | GRT-DS-IP-DT-170226 | GRT-YL00-P0MA-200045 | [STG]_List of signals | 0 | 2017-08-15 | 10 | APPROVED | 2017-08-25 | Close
644 | GRT-DS-IP-DT-170226 | GRT-XB00-P0MA-200002 | [STG]_Foundation - Embedded Elements | 0 | 2017-08-15 | 10 | APPROVED | 2017-08-25 | Close
645 | GRT-DS-IP-DT-170226 | GRT-XB00-P0MA-200003 | [STG]_Foundation - Static & Dynamic Calculation | 0 | 2017-08-15 | 10 | APPROVED | 2017-08-25 | Close
646 | GRT-DS-IP-DT-170227 | GRT-UC08-P0ZEN-100002 | General Arrangement of Powerblock | B | 2017-08-15 | 9 | A | 2017-08-24 | Close
647 | GRT-DS-IP-DT-170228 | GRT-UE00-P0ZEN-100003 | General Arrangement of Steam Turbine Building Ground Floor Plan | C | 2017-08-15 | 9 | B | 2017-08-24 | Close
648 | GRT-DS-IP-DT-170228 | GRT-UE00-P0ZEN-100004 | General Arrangement of Steam Turbine Building Mezzanine Floor Plan | C | 2017-08-15 | 9 | A | 2017-08-24 | Close
649 | GRT-DS-IP-DT-170228 | GRT-UE00-P0ZEN-100005 | General Arrangement of Steam Turbine Building Operating Floor Plan | C | 2017-08-15 | 9 | B | 2017-08-24 | Close
650 | GRT-DS-IP-DT-170228 | GRT-UE00-P0ZEN-100006 | General Arrangement of Steam Turbine Building Deaerator Floor Plan | C | 2017-08-15 | 9 | A | 2017-08-24 | Close
651 | GRT-DS-IP-DT-170228 | GRT-UE00-P0ZEN-100007 | General Arrangement of Steam Turbine Building Basement Floor Plan | C | 2017-08-15 | 9 | A | 2017-08-24 | Close
652 | GRT-DS-IP-DT-170228 | GRT-UE00-P0ZEN-100008 | General Arrangement of Steam Turbine Building Section A-A | C | 2017-08-15 | 9 | A | 2017-08-24 | Close
653 | GRT-DS-IP-DT-170228 | GRT-UE00-P0ZEN-100009 | General Arrangement of Steam Turbine Building Section B-B | C | 2017-08-15 | 9 | A | 2017-08-24 | Close
654 | GRT-DS-IP-DT-170229 | GRT-YL22-P0PCC-113009 | [Aux. Cooling Water Pump]_NAMEPLATE DRAWING FOR AUXILIARY COOLING WATER PUMP MOTOR | A | 2017-08-15 | 9 | B | 2017-08-24 | Close
655 | GRT-DS-IP-DT-170229 | GRT-YL22-P0PGB-113109 | [CCWP ]_NAMEPLATE DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | A | 2017-08-15 | 9 | B | 2017-08-24 | Close
656 | GRT-DS-IP-DT-170230 | GRT-XJ00-P0PAB-140012 | Piping ISO (Large Bore) - Cooling water | A | 2017-08-15 | 9 | I | 2017-08-24 | Close
657 | GRT-DS-IP-DT-170231 | GRT-XG02-P0SC-120001 | [Compressed air system]_P&I DIAGRAM FOR COMPRESSED AIR SYSTEM | 0 | 2017-08-15 | 10 | APPROVED AS NOTED | 2017-08-25 | Close
658 | GRT-DS-IP-DT-170231 | GRT-XG02-P0SC-120002 | [Compressed air system]_P&I DIAGRAM FOR INSTRUMENT AIR SYSTEM | 0 | 2017-08-15 | 10 | APPROVED | 2017-08-25 | Close
659 | GRT-DS-IP-DT-170231 | GRT-XG02-P0SC-120003 | [Compressed air system]_P&I DIAGRAM FOR SERVICE AIR SYSTEM | 0 | 2017-08-15 | 10 | APPROVED | 2017-08-25 | Close
660 | GRT-DS-IP-DT-170232 | GRT-YD00-P0SCA-120007 | [Air Compressor]_AIR COMPRESSOR_GENERAL ARRANGEMENT DRAWING FOR AIR COMPRESSORS PACKAGE | 0 | 2017-08-15 | 10 | APPROVED AS NOTED | 2017-08-25 | Close
661 | GRT-DS-IP-DT-170232 | GRT-XG02-P0SCA-120008 | [Air Compressor]_P&I DIAGRAM FOR AIR COMPRESSOR PACKAGE | 0 | 2017-08-15 | 10 | APPROVED AS NOTED | 2017-08-25 | Close
662 | GRT-DS-IP-DT-170232 | GRT-XB00-P0SCA-120013 | [Air Compressor]_FOUNDATION DRAWINGS | 0 | 2017-08-15 | 10 | APPROVED | 2017-08-25 | Close
663 | GRT-DS-IP-DT-170233 | GRT-XG02-P0LCB-121002 | [Condensate Extraction Pump]_P&I DIAGRAM | 0 | 2017-08-15 | 10 | APPROVED | 2017-08-25 | Close
664 | GRT-DS-IP-DT-170233 | GRT-YT01-P0LCB-121003 | [Condensate Extraction Pump]_DATA SHEET & CHARACTERISTIC CURVE | 0 | 2017-08-15 | 10 | APPROVED | 2017-08-25 | Close
665 | GRT-DS-IP-DT-170233 | GRT-YD00-P0LCB-121008 | [Condensate Extraction Pump]_FOUNDATION DRAWINGS | 0 | 2017-08-15 | 10 | APPROVED | 2017-08-25 | Close
666 | GRT-DS-IP-DT-170234 | GRT-YK09-P0LCB-121004 | [Condensate Extraction Pump]_PUMP SECTIONAL DRAWING | 0 | 2017-08-21 | 1 | APPROVED | 2017-08-22 | Close
667 | GRT-DS-IP-DT-170234 | GRT-YT01-P0LCB-121006 | [Condensate Extraction Pump]_COUPLING SPECIFICATION | 0 | 2017-08-21 | 1 | APPROVED | 2017-08-22 | Close
668 | GRT-DS-IP-DT-170235 | GRT-DE00-P0ZEN-144500 | [Piping General]_Piping material specification (BOP) | 0 | 2017-08-21 | 1 | APPROVED | 2017-08-22 | Close
669 | GRT-DS-IP-DT-170235 | GRT-YT10-P0ZEN-144502 | [Piping General]_Pipe Thickness Calculation (BOP) | 0 | 2017-08-21 | 1 | APPROVED | 2017-08-22 | Close
670 | GRT-DS-IP-DT-170236 | GRT-XG02-P0PA-110008 | [Aux. Cooling Water System]_P&I DIAGRAM | 0 | 2017-08-21 | 1 | APPROVED AS NOTED | 2017-08-22 | Close
671 | GRT-DS-IP-DT-170236 | GRT-XG07-P0PA-110304 | [Aux. & Closed Cooling Water System]_PROCESS FLOW DIAGRAM | 0 | 2017-08-21 | 1 | APPROVED AS NOTED | 2017-08-22 | Close
672 | GRT-DS-IP-DT-170236 | GRT-XW03-P0PCC-113010 | [Aux. Cooling Water Pump_Design]_SIZING CALCULATION FOR AUXILIARY COOLING WATER PUMP | 0 | 2017-08-21 | 1 | APPROVED AS NOTED | 2017-08-22 | Close
673 | GRT-DS-IP-DT-170237 | GRT-YD00-P0SM-123001 | [Crane & Hoist(DHI)]_HOIST_GA DRAWING FOR HOISTS | A | 2017-08-21 | 30 | DEEMED APPROVAL | 2017-09-20 | Close
674 | GRT-DS-IP-DT-170237 | GRT-YT01-P0SM-123002 | [Crane & Hoist(DHI)]_HOIST_DATA SHEETS FOR HOISTS | A | 2017-08-21 | 30 | DEEMED APPROVAL | 2017-09-20 | Close
675 | GRT-DS-IP-DT-170238 | GRT-YD00-P0LCB-121001 | [Condensate Extraction Pump]_GENERAL ARRANGEMENT DRAWING | C | 2017-08-21 | 21 | B | 2017-09-11 | Close
676 | GRT-DS-IP-DT-170239 | GRT-YT01-P0PGB-113200 | [Blowdown Cooler]_DATA SHEET FOR PLATE TYPE HEAT EXCHANGER | 0 | 2017-08-21 | 1 | APPROVED AS NOTED | 2017-08-22 | Close
677 | GRT-DS-IP-DT-170240 | GRT-YD00-P0PGB-113201 | [Blowdown Cooler]_OUTLINE DRAWING FOR PLATE TYPE HEAT EXCHANGER | B | 2017-08-21 | 53 | DEEMED APPROVAL | 2017-10-13 | Close
679 | GRT-DS-IP-DT-170242 | GRT-YV02-P0MAJ-460102 | Wiring Diargam For Condenser Vacuum Pump | A | 2017-08-21 | 21 | I | 2017-09-11 | Close
680 | GRT-DS-IP-DT-170242 | GRT-YB10-P0MAJ-460103 | Terminal Box For Condenser Vacuum Pump | A | 2017-08-21 | 21 | B | 2017-09-11 | Close
681 | GRT-DS-IP-DT-170242 | GRT-XB02-P0MAJ-460111 | Foundation Drawing For Condenser Vacuum Pump | A | 2017-08-21 | 39 | DEEMED APPROVAL | 2017-09-29 | Close
682 | GRT-DS-IP-DT-170242 | GRT-DB00-P0MAJ-460118 | Performance Curves For Condenser Vacuum Pump | A | 2017-08-21 | 39 | DEEMED APPROVAL | 2017-09-29 | Close
683 | GRT-DS-IP-DT-170242 | GRT-YV02-P0MAJ-460202 | Wiring Diargam For Water Box Vacuum Pump | A | 2017-08-21 | 21 | I | 2017-09-11 | Close
684 | GRT-DS-IP-DT-170242 | GRT-YB10-P0MAJ-460203 | Terminal Box For Water Box Vacuum Pump | A | 2017-08-21 | 21 | B | 2017-09-11 | Close
685 | GRT-DS-IP-DT-170242 | GRT-XB02-P0MAJ-460211 | Foundation Drawing For Water Box Vacuum Pump | A | 2017-08-21 | 39 | DEEMED APPROVAL | 2017-09-29 | Close
686 | GRT-DS-IP-DT-170242 | GRT-DB00-P0MAJ-460218 | Performance Curves For Water Box Vacuum Pump | A | 2017-08-21 | 39 | DEEMED APPROVAL | 2017-09-29 | Close
687 | GRT-DS-IP-DT-170243 | GRT-XH01-P1H-300023 | [HRSG]_PIPE SUPPORT DRAWINGS | A | 2017-08-21 | 73 | DEEMED APPROVAL | 2017-11-02 | Close
688 | GRT-DS-IP-DT-170243 | GRT-YD00-P1H-300035 | [HRSG]_SPEC. & DRAWING FOR STEAM DRUM | A | 2017-08-21 | 70 | DEEMED APPROVAL | 2017-10-30 | Close
689 | GRT-DS-IP-DT-170243 | GRT-YT01-P1H-300057 | [HRSG]_DATA & BOM OF INSULATION FOR INTERNAL PIPING | A | 2017-08-21 | 73 | DEEMED APPROVAL | 2017-11-02 | Close
690 | GRT-DS-IP-DT-170244 | GRT-YD00-P0QJA-111000 | [N2 Gas System]_General Arrangement Drawing | A | 2017-08-21 | 98 | DEEMED APPROVAL | 2017-11-27 | Close
678 | GRT-DS-IP-DT-170241 | GRT-YT01-P0LCB-121005 | [Condensate Extraction Pump]_MECHANICAL SEAL SPECIFICATION | 0 | 2017-08-23 | 0 | APPROVED AS NOTED | 2017-08-23 | Close
691 | GRT-DS-IP-DT-170245 | GRT-YK00-P0ZEN-164301 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - General Notes | B | 2017-08-23 | 19 | A | 2017-09-11 | Close
692 | GRT-DS-IP-DT-170245 | GRT-YK00-P0ZEN-164302 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Symbol & Legend | B | 2017-08-23 | 19 | A | 2017-09-11 | Close
693 | GRT-DS-IP-DT-170245 | GRT-YK00-P0ZEN-164303 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Material List | B | 2017-08-23 | 19 | A | 2017-09-11 | Close
694 | GRT-DS-IP-DT-170245 | GRT-YK00-P0ZEN-164304 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Pressure Transmitter / Switch | B | 2017-08-23 | 19 | A | 2017-09-11 | Close
695 | GRT-DS-IP-DT-170245 | GRT-YK00-P0ZEN-164305 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Diff. Press. Transmitter / Switch | B | 2017-08-23 | 19 | A | 2017-09-11 | Close
696 | GRT-DS-IP-DT-170245 | GRT-YK00-P0ZEN-164306 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Flow Transmitter / Switch | B | 2017-08-23 | 19 | A | 2017-09-11 | Close
697 | GRT-DS-IP-DT-170245 | GRT-YK00-P0ZEN-164307 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Level Transmitter / Switch | B | 2017-08-23 | 19 | A | 2017-09-11 | Close
698 | GRT-DS-IP-DT-170245 | GRT-YK00-P0ZEN-164308 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Pressure Gauge | B | 2017-08-23 | 19 | A | 2017-09-11 | Close
699 | GRT-DS-IP-DT-170245 | GRT-YK00-P0ZEN-164309 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Control Valve | B | 2017-08-23 | 19 | A | 2017-09-11 | Close
700 | GRT-DS-IP-DT-170245 | GRT-YK00-P0ZEN-164310 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Stanchion & Rack | B | 2017-08-23 | 19 | A | 2017-09-11 | Close
701 | GRT-DS-IP-DT-170245 | GRT-YK00-P0ZEN-164312 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Temp.Transmitter/ Guage/ Test Well | B | 2017-08-23 | 19 | A | 2017-09-11 | Close
702 | GRT-DS-IP-DT-170246 | GRT-XG02-P0PG-110009 | [Closed cooling water system]_P&I DIAGRAM | D | 2017-08-23 | 14 | DEEMED APPROVAL | 2017-09-06 | Close
703 | GRT-DS-IP-DT-170246 | GRT-XW03-P0PGB-113110 | [CCWP_Design]_SIZING CALCULATION FOR CLOSED COOLING WATER PUMP | D | 2017-08-23 | 14 | DEEMED APPROVAL | 2017-09-06 | Close
704 | GRT-DS-IP-DT-170247 | GRT-YF01-P0ZEN-161004 | [INC_Plant_Overall_Design]_Plant Protection & Interlock Diagram | 0 | 2017-08-23 | 0 | APPROVED | 2017-08-23 | Close
706 | GRT-DS-IP-DT-170249 | GRT-YT01-P0QU-130030 | [Sampling System]_TECHNICAL DATASHEET | A | 2017-08-23 | 68 | DEEMED APPROVAL | 2017-10-30 | Close
707 | GRT-DS-IP-DT-170249 | GRT-YT01-P0QU-130031 | [Sampling System]_INSTRUMENT DATA SHEET | A | 2017-08-23 | 19 | A | 2017-09-11 | Close
708 | GRT-DS-IP-DT-170250 | GRT-XH01-P0QC-130011 | [Chemical Dosing System]_PIPING ARRANGEMENT DRAWING | A | 2017-08-23 | 82 | DEEMED APPROVAL | 2017-11-13 | Close
709 | GRT-DS-IP-DT-170250 | GRT-YT01-P0QC-130013 | [Chemical Dosing System]_MOTOR DATA SHEET | A | 2017-08-23 | 19 | A | 2017-09-11 | Close
710 | GRT-DS-IP-DT-170250 | GRT-YT01-P0QC-130014 | [Chemical Dosing System]_PUMP DATA SHEET | A | 2017-08-23 | 14 | DEEMED APPROVAL | 2017-09-06 | Close
711 | GRT-DS-IP-DT-170250 | GRT-YT01-P0QC-130015 | [Chemical Dosing System]_VALVE DATA SHEET | A | 2017-08-23 | 14 | DEEMED APPROVAL | 2017-09-06 | Close
712 | GRT-DS-IP-DT-170250 | GRT-YT01-P0QC-130016 | [Chemical Dosing System]_INSTRUMENT DATA SHEET | A | 2017-08-23 | 19 | A | 2017-09-11 | Close
736 | GRT-DS-IP-DT-170254 | GRT-VN03-P1H-300012 | [HRSG]_TYPICAL LADDER DETAIL FOR STEEL STRUCTURE | 0 | 2017-08-24 | 1 | APPROVED | 2017-08-25 | Close
740 | GRT-DS-IP-DT-170256 | GRT-UE00-P1H-300008 | [HRSG]_ARRANGEMENT OF INLET DUCT | 0 | 2017-08-24 | 1 | APPROVED | 2017-08-25 | Close
741 | GRT-DS-IP-DT-170256 | GRT-XL00-P1H-300028 | [HRSG]_LINE LIST | 0 | 2017-08-24 | 1 | APPROVED AS NOTED | 2017-08-25 | Close
742 | GRT-DS-IP-DT-170256 | GRT-XN00-P1H-300029 | [HRSG]_VALVE LIST | 0 | 2017-08-24 | 1 | APPROVED | 2017-08-25 | Close
743 | GRT-DS-IP-DT-170256 | GRT-YD00-P1H-300036 | [HRSG]_EQUIPMENT OUTLINE DRAWING FOR BLOWDOWN TANK | 0 | 2017-08-24 | 1 | APPROVED | 2017-08-25 | Close
705 | GRT-DS-IP-DT-170248 | GRT-CN00-P0ZEN-110102 | [Plant Overall]_PLANT START - UP AND SHUT - DOWN PROCEDURE | A | 2017-08-25 | 126 | DEEMED APPROVAL | 2017-12-29 | Close
713 | GRT-DS-IP-DT-170251 | GRT-YF00-P0PAH-440004 | Control Logic for CTCS & Debris Filter | A | 2017-08-25 | 17 | A | 2017-09-11 | Close
714 | GRT-DS-IP-DT-170251 | GRT-YV02-P0PAH-440005 | Cable Connection/wiring Diagram(for power, control & instrument cable) for CTCS & Debris Filter | A | 2017-08-25 | 17 | A | 2017-09-11 | Close
715 | GRT-DS-IP-DT-170251 | GRT-YB03-P0PAH-440006 | Configuration Diagram of Package System for CTCS & Debris Filter | A | 2017-08-25 | 17 | A | 2017-09-11 | Close
716 | GRT-DS-IP-DT-170251 | GRT-YK08-P0PAH-440007 | Outline Drawing for Control Panel of CTCS & Debris Filter | A | 2017-08-25 | 17 | A | 2017-09-11 | Close
717 | GRT-DS-IP-DT-170252 | GRT-YF00-P0PAH-440054 | CCW HEX Tube Cleaning System_Control Logic | A | 2017-08-25 | 17 | I | 2017-09-11 | Close
718 | GRT-DS-IP-DT-170252 | GRT-YV02-P0PAH-440055 | CCW HEX Tube Cleaning System_Cable Connection/wiring Diagram(for power, control & instrument cable) | A | 2017-08-25 | 17 | A | 2017-09-11 | Close
719 | GRT-DS-IP-DT-170252 | GRT-YB03-P0PAH-440056 | CCW HEX Tube Cleaning System_Configuration Diagram of Package System | A | 2017-08-25 | 17 | A | 2017-09-11 | Close
720 | GRT-DS-IP-DT-170252 | GRT-YK08-P0PAH-440057 | CCW HEX Tube Cleaning System_Outline Drawing for Control Panel | A | 2017-08-25 | 17 | A | 2017-09-11 | Close
721 | GRT-DS-IP-DT-170257 | GRT-YK08-P0MAJ-460100 | General Arrangement Drawing For Condenser Vacuum Pump | B | 2017-08-30 | 19 | A | 2017-09-18 | Close
722 | GRT-DS-IP-DT-170257 | GRT-XG02-P0MAJ-460101 | P & ID For Condenser Vacuum Pump | B | 2017-08-30 | 19 | B | 2017-09-18 | Close
723 | GRT-DS-IP-DT-170257 | GRT-YT01-P0MAJ-460104 | Technical Data Sheet | B | 2017-08-30 | 19 | A | 2017-09-18 | Close
724 | GRT-DS-IP-DT-170257 | GRT-YL00-P0MAJ-460107 | Instrument list For Condenser Vacuum Pump | A | 2017-08-30 | 19 | A | 2017-09-18 | Close
725 | GRT-DS-IP-DT-170257 | GRT-XK00-P0MAJ-460112 | Outline & Sectional Drawing For Condenser Vacuum Pump | B | 2017-08-30 | 19 | A | 2017-09-18 | Close
726 | GRT-DS-IP-DT-170257 | GRT-XN00-P0MAJ-460119 | Valve and Specialty List For Condenser Vacuum Pump | A | 2017-08-30 | 19 | I | 2017-09-18 | Close
727 | GRT-DS-IP-DT-170257 | GRT-YK08-P0MAJ-460200 | General Arrangement Drawing For Water Box Vacuum Pump | B | 2017-08-30 | 19 | A | 2017-09-18 | Close
728 | GRT-DS-IP-DT-170257 | GRT-XG02-P0MAJ-460201 | P & ID For Water Box Vacuum Pump | B | 2017-08-30 | 19 | B | 2017-09-18 | Close
729 | GRT-DS-IP-DT-170257 | GRT-YL00-P0MAJ-460207 | Instrument list For Water Box Vacuum Pump | A | 2017-08-30 | 19 | A | 2017-09-18 | Close
730 | GRT-DS-IP-DT-170257 | GRT-XK00-P0MAJ-460212 | Outline & Sectional Drawing For Water Box Vacuum Pump | B | 2017-08-30 | 19 | A | 2017-09-18 | Close
731 | GRT-DS-IP-DT-170257 | GRT-XN00-P0MAJ-460219 | Valve and Specialty List For Water Box Vacuum Pump | A | 2017-08-30 | 19 | I | 2017-09-18 | Close
732 | GRT-DS-IP-DT-170253 | GRT-DM02-P1H-300005 | [HRSG]_GENERAL NOTE FOR STEEL STRUCTURE | C | 2017-08-30 | 19 | I | 2017-09-18 | Close
733 | GRT-DS-IP-DT-170253 | GRT-UE00-P1H-300009 | [HRSG]_ARRANGEMENT OF MAIN STACK& FIELD ERECTION | C | 2017-08-30 | 19 | I | 2017-09-18 | Close
734 | GRT-DS-IP-DT-170253 | GRT-VN03-P1H-300010 | [HRSG]_TYPICAL PLATFORM DETAIL FOR STEEL STRUCTURE | C | 2017-08-30 | 19 | I | 2017-09-18 | Close
735 | GRT-DS-IP-DT-170253 | GRT-VN03-P1H-300013 | [HRSG]_ARRANGEMENT FOR PLATFORM STRUCTURE | C | 2017-08-30 | 19 | I | 2017-09-18 | Close
737 | GRT-DS-IP-DT-170255 | GRT-XG02-P1H-300020 | [HRSG]_P&I DIAGRAM | D | 2017-08-30 | 19 | A | 2017-09-18 | Close
738 | GRT-DS-IP-DT-170255 | GRT-YD00-P1H-300034 | [HRSG]_PRESSURE PART ARRANGEMENT | D | 2017-08-30 | 19 | I | 2017-09-18 | Close
739 | GRT-DS-IP-DT-170255 | GRT-YL00-P1H-300051 | [HRSG]_INSTRUMENT LIST | B | 2017-08-30 | 23 | I | 2017-09-22 | Close
744 | GRT-DS-IP-DT-170259 | GRT-YS18-P0LB-111103 | [Bypass Valve & PRDS]_CIRCUIT DIAGRAM FOR HYDRAULIC POWER UNIT | A | 2017-08-30 | 19 | I | 2017-09-18 | Close
745 | GRT-DS-IP-DT-170259 | GRT-XS01-P0LB-111105 | [Bypass Valve & PRDS]_Operating Description for HPU system for Bypass System | A | 2017-08-30 | 19 | I | 2017-09-18 | Close
746 | GRT-DS-IP-DT-170258 | GRT-CV03-P0ZEN-163701 | [Field Instruments(DHI)]_Technical Specification & Datasheet for Process Transmitter - BOP | A | 2017-08-30 | 19 | A | 2017-09-18 | Close
747 | GRT-DS-IP-DT-170258 | GRT-CV03-P0ZEN-163702 | [Field Instruments(DHI)]_Technical Specification & Datasheet for Local Instrument - BOP | A | 2017-08-30 | 19 | A | 2017-09-18 | Close
748 | GRT-DS-IP-DT-170260 | GRT-YK10-P0PCC-113003 | [Aux. Cooling Water Pump]_Pump Sectional Drawing | 0 | 2017-08-30 | 9 | APPROVED | 2017-09-08 | Close
749 | GRT-DS-IP-DT-170260 | GRT-YK10-P0PGB-113103 | [CCWP ]_Pump Sectional Drawing | 0 | 2017-08-30 | 9 | APPROVED | 2017-09-08 | Close
750 | GRT-DS-IP-DT-170261 | GRT-YT01-P0PCC-113002 | [Aux. Cooling Water Pump]_DATA SHEET FOR AUXILIARY COOLING WATER PUMP | 0 | 2017-08-30 | 9 | APPROVED AS NOTED | 2017-09-08 | Close
751 | GRT-DS-IP-DT-170261 | GRT-YT01-P0PCC-113004 | [Aux. Cooling Water Pump]_DATA SHEET FOR AUXILIARY COOLING WATER PUMP MOTOR | 0 | 2017-08-30 | 9 | APPROVED AS NOTED | 2017-09-08 | Close
752 | GRT-DS-IP-DT-170261 | GRT-YD00-P0PCC-113005 | [Aux. Cooling Water Pump]_OUTLINE DRAWING FOR AUXILIARY COOLING WATER PUMP MOTOR | 0 | 2017-08-30 | 9 | APPROVED AS NOTED | 2017-09-08 | Close
753 | GRT-DS-IP-DT-170261 | GRT-YT01-P0PGB-113104 | [CCWP ]_DATA SHEET FOR CLOSED COOLING WATER PUMP MOTOR | 0 | 2017-08-30 | 9 | APPROVED AS NOTED | 2017-09-08 | Close
754 | GRT-DS-IP-DT-170261 | GRT-YD00-P0PGB-113105 | [CCWP ]_OUTLINE DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | 0 | 2017-08-30 | 9 | APPROVED AS NOTED | 2017-09-08 | Close
755 | GRT-DS-IP-DT-170262 | GRT-YD00-P0PCC-113001 | [Aux. Cooling Water Pump]_GENERAL ARRANGEMENT DRAWING FOR AUXILIARY COOLING WATER PUMP | B | 2017-08-30 | 19 | A | 2017-09-18 | Close
756 | GRT-DS-IP-DT-170262 | GRT-YD00-P0PGB-113101 | [CCWP ]_GENERAL ARRANGEMENT DRAWING FOR CLOSED COOLING WATER PUMP | B | 2017-08-30 | 19 | B | 2017-09-18 | Close
757 | GRT-DS-IP-DT-170262 | GRT-YT01-P0PGB-113102 | [CCWP ]_DATA SHEET FOR CLOSED COOLING WATER PUMP | C | 2017-08-30 | 19 | A | 2017-09-18 | Close
758 | GRT-DS-IP-DT-170263 | GRT-XB00-P0MA-200008 | [STG]_Loads plan - Levels | B | 2017-08-30 | 23 | I | 2017-09-22 | Close
759 | GRT-DS-IP-DT-170263 | GRT-YD00-P0MA-200017 | [STG]_Layout - piping routing - | B | 2017-08-30 | 23 | I | 2017-09-22 | Close
760 | GRT-DS-IP-DT-170263 | GRT-YD00-P0MA-200006 | [STG]_General Arrangement Drawing | C | 2017-08-30 | 23 | I | 2017-09-22 | Close
779 | GRT-DS-IP-DT-170267 | GRT-CN00-P0ZEN-110104 | [Plant Overall]_Hazardous Area Classification | 0 | 2017-08-30 | 9 | APPROVED | 2017-09-08 | Close
761 | GRT-DS-IP-DT-170264 | GRT-YK00-P0MA-200040 | [STG]_I&C Lay-outs | B | 2017-09-06 | 12 | A | 2017-09-18 | Close
762 | GRT-DS-IP-DT-170264 | GRT-YU03-P0MA-200041 | [STG]_Control system function philosophy | B | 2017-09-06 | 12 | B | 2017-09-18 | Close
763 | GRT-DS-IP-DT-170264 | GRT-YF00-P0MA-200044 | [STG]_Logic diagrams for control of functional groups | A | 2017-09-06 | 12 | B | 2017-09-18 | Close
764 | GRT-DS-IP-DT-170264 | GRT-YL21-P0MA-200046 | [STG]_Trips & Alarms settings | A | 2017-09-06 | 12 | B | 2017-09-18 | Close
765 | GRT-DS-IP-DT-170264 | GRT-YK08-P0MA-200047 | [STG]_HMI design | A | 2017-09-06 | 12 | B | 2017-09-18 | Close
766 | GRT-DS-IP-DT-170266 | GRT-XB02-P0QC-130009 | [Chemical Dosing System]_FOUNDATION AND LOADING DATA | A | 2017-09-06 | 12 | I | 2017-09-18 | Close
767 | GRT-DS-IP-DT-170266 | GRT-YK10-P0QC-130010 | [Chemical Dosing System]_EQUIPMENT ASSEMBLY DRAWING | A | 2017-09-06 | 12 | I | 2017-09-18 | Close
768 | GRT-DS-IP-DT-170266 | GRT-YT01-P0QC-130012 | [Chemical Dosing System]_TECHNICAL DATASHEET | A | 2017-09-06 | 12 | A | 2017-09-18 | Close
769 | GRT-DS-IP-DT-170265 | GRT-QA00-P0H-040007 | [HRSG]_Welders List for HRSG Heat Exchanger | A | 2017-09-06 | 16 | I | 2017-09-22 | Close
770 | GRT-DS-IP-DT-170265 | GRT-QA00-P0H-040008 | [HRSG]_WPS&PQR for HRSG Heat Exchanger | A | 2017-09-06 | 16 | I | 2017-09-22 | Close
771 | GRT-DS-IP-DT-170265 | GRT-QA00-P0H-040009 | [HRSG]_Welders List for HRSG HP Drum | A | 2017-09-06 | 16 | I | 2017-09-22 | Close
772 | GRT-DS-IP-DT-170265 | GRT-QA00-P0H-040010 | [HRSG]_WPS&PQR for HRSG HP Drum | A | 2017-09-06 | 16 | I | 2017-09-22 | Close
773 | GRT-DS-IP-DT-170265 | GRT-QA00-P0H-040011 | [HRSG]_Welders List for HRSG LP Drum | A | 2017-09-06 | 16 | I | 2017-09-22 | Close
774 | GRT-DS-IP-DT-170265 | GRT-QA00-P0H-040012 | [HRSG]_WPS&PQR for HRSG LP Drum | A | 2017-09-06 | 16 | I | 2017-09-22 | Close
775 | GRT-DS-IP-DT-170265 | GRT-QA00-P0H-040013 | NDE Procedure for HRSG Piping | A | 2017-09-06 | 16 | I | 2017-09-22 | Close
776 | GRT-DS-IP-DT-170265 | GRT-QA00-P0H-040014 | Heat Treatment Procedure for HRSG Piping | A | 2017-09-06 | 16 | I | 2017-09-22 | Close
777 | GRT-DS-IP-DT-170265 | GRT-QA00-P0H-040015 | Welders List for HRSG Piping | A | 2017-09-06 | 16 | I | 2017-09-22 | Close
778 | GRT-DS-IP-DT-170265 | GRT-QA00-P0H-040016 | WPS&PQR for HRSG Piping | A | 2017-09-06 | 16 | I | 2017-09-22 | Close
784 | GRT-DS-IP-DT-170269 | GRT-YT10-P0MAG-410101 | Cathodic Protection System for Condenser_Calculation Sheet | A | 2017-09-06 | 53 | C | 2017-10-29 | Close
785 | GRT-DS-IP-DT-170269 | GRT-YD00-P0MAG-410103 | Cathodic Protection System for Condenser_The Location of Anode (Inlet Waterbox) | A | 2017-09-06 | 53 | C | 2017-10-29 | Close
786 | GRT-DS-IP-DT-170269 | GRT-YD00-P0MAG-410104 | Cathodic Protection System for Condenser_The Location of Anode (Outlet Waterbox) | A | 2017-09-06 | 53 | C | 2017-10-29 | Close
787 | GRT-DS-IP-DT-170270 | GRT-YK08-P0LBG-111300 | [Silencer]_OUTLINE DRAWING FOR SILENCER | A | 2017-09-06 | 16 | B | 2017-09-22 | Close
788 | GRT-DS-IP-DT-170270 | GRT-YT01-P0LBG-111301 | [Silencer]_DATA SHEET FOR SILENCER | A | 2017-09-06 | 16 | B | 2017-09-22 | Close
789 | GRT-DS-IP-DT-170271 | GRT-YL10-P0MAJ-460121 | Spare Part List For Condenser Vacuum Pump | 0 | 2017-09-06 | 2 | APPROVED | 2017-09-08 | Close
790 | GRT-DS-IP-DT-170271 | GRT-DA06-P0MAJ-460123 | Lubricant List For Condenser Vacuum Pump | 0 | 2017-09-06 | 2 | APPROVED | 2017-09-08 | Close
791 | GRT-DS-IP-DT-170271 | GRT-YL10-P0MAJ-460221 | Spare Part List For Water Box Vacuum Pump | 0 | 2017-09-06 | 2 | APPROVED | 2017-09-08 | Close
792 | GRT-DS-IP-DT-170271 | GRT-DA06-P0MAJ-460223 | Lubricant List For Water Box Vacuum Pump | 0 | 2017-09-06 | 2 | APPROVED | 2017-09-08 | Close
793 | GRT-DS-IP-DT-170271 | GRT-DA06-P0MAJ-460122 | Utility Consumption List For Condenser Vacuum Pump | 0 | 2017-09-06 | 2 | APPROVED | 2017-09-08 | Close
794 | GRT-DS-IP-DT-170271 | GRT-DA06-P0MAJ-460222 | Utility Consumption List For Water Box Vacuum Pump | 0 | 2017-09-06 | 2 | APPROVED | 2017-09-08 | Close
795 | GRT-DS-IP-DT-170273 | GRT-YL22-P0LDB-130053 | [Condensate Filter System]_NAME PLATE DRAWING | A | 2017-09-06 | 16 | I | 2017-09-22 | Close
796 | GRT-DS-IP-DT-170273 | GRT-YK00-P0LDB-130057 | [Condensate Filter System]_HOOK UP DRAWING | A | 2017-09-06 | 12 | I | 2017-09-18 | Close
797 | GRT-DS-IP-DT-170274 | GRT-QA00-P0H-040004 | [HRSG]_Heat Treatment Procedure for HRSG Heat Exchanger | 0 | 2017-09-06 | 2 | APPROVED | 2017-09-08 | Close
798 | GRT-DS-IP-DT-170272 | GRT-XG02-P0PG-110009 | [Closed cooling water system]_P&I DIAGRAM | 0 | 2017-09-06 | 2 | APPROVED AS NOTED | 2017-09-08 | Close
799 | GRT-DS-IP-DT-170272 | GRT-XW03-P0PGB-113110 | [CCWP_Design]_SIZING CALCULATION FOR CLOSED COOLING WATER PUMP | 0 | 2017-09-06 | 2 | APPROVED AS NOTED | 2017-09-08 | Close
800 | GRT-DS-IP-DT-170275 | GRT-CV03-P0ZEN-161111 | [DCS]_Functional Design Specification for Software | 0 | 2017-09-06 | 2 | APPROVED | 2017-09-08 | Close
807 | GRT-DS-IP-DT-170277 | GRT-YK09-P0MA-200020 | [STG]_Functional description | 0 | 2017-09-06 | 2 | APPROVED | 2017-09-08 | Close
811 | GRT-DS-IP-DT-170283 | GRT-YF00-P0ZEN-161210 | [INC_Other_Sys_Logic&Loop]_Control Logic Diagram for Sampling & Chemical Dosing System | 0 | 2017-09-06 | 5 | APPROVED AS NOTED | 2017-09-11 | Close
812 | GRT-DS-IP-DT-170284 | GRT-YS00-P0ZEN-163310 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Electrical System | 0 | 2017-09-06 | 5 | APPROVED AS NOTED | 2017-09-11 | Close
801 | GRT-DS-IP-DT-170276 | GRT-YF00-P0PA-161207 | [Aux. Cooling Water System_I&C_Logic]_Control Logic Diagram for BOP | B | 2017-09-11 | 15 | A | 2017-09-26 | Close
802 | GRT-DS-IP-DT-170276 | GRT-YF00-P0PG-161208 | [Closed cooling water system_I&C_Logic]_Control Logic Diagram for BOP | B | 2017-09-11 | 15 | A | 2017-09-26 | Close
803 | GRT-DS-IP-DT-170276 | GRT-YF00-P0ZEN-161211 | [INC_Other_Sys_Logic&Loop]_Control Logic Diagram for Interface with other Control System | B | 2017-09-11 | 15 | A | 2017-09-26 | Close
804 | GRT-DS-IP-DT-170276 | GRT-YF00-P0PA-161307 | [Aux. Cooling Water System_I&C_Loop]_Control Loop Diagram for BOP | B | 2017-09-11 | 15 | A | 2017-09-26 | Close
805 | GRT-DS-IP-DT-170276 | GRT-YF00-P0PG-161308 | [Closed cooling water system_I&C_Loop]_Control Loop Diagram for BOP | B | 2017-09-11 | 15 | A | 2017-09-26 | Close
806 | GRT-DS-IP-DT-170276 | GRT-YF00-P0ZEN-161311 | [INC_Other_Sys_Logic&Loop]_Control Loop Diagram for Interface with other Control System | B | 2017-09-11 | 15 | A | 2017-09-26 | Close
808 | GRT-DS-IP-DT-170281 | GRT-YK10-P0ZEN-113400 | [MOV (Butterfly)(DHI)]_OUTLINE DRAWING FOR MOV (BUTTERFLY) | A | 2017-09-11 | 11 | B | 2017-09-22 | Close
809 | GRT-DS-IP-DT-170281 | GRT-YT01-P0ZEN-113401 | [MOV (Butterfly)(DHI)]_VALVE LIST & DATA SHEET FOR MOV (BUTTERFLY) | A | 2017-09-11 | 11 | B | 2017-09-22 | Close
810 | GRT-DS-IP-DT-170282 | GRT-QA00-P0H-040017 | [HRSG]_Welding Consumable Control Procedure for HRSG Pressure Part | A | 2017-09-11 | 7 | I | 2017-09-18 | Close
813 | GRT-DS-IP-DT-170285 | GRT-YF00-P0ZEN-161402 | [INC_Start&Shutdown Diagram]_Plant Start-up & Shutdown Sequence Diagram - Symbol & Legend | A | 2017-09-11 | 15 | A | 2017-09-26 | Close
780 | GRT-DS-IP-DT-170268 | GRT-DF04-P0ZEN-144512 | [Piping General]_Stress Analysis Report for HP steam system | B | 2017-09-13 | 16 | A | 2017-09-29 | Close
781 | GRT-DS-IP-DT-170268 | GRT-DF04-P0ZEN-144513 | [Piping General]_Stress Analysis Report for LP steam system | B | 2017-09-13 | 16 | A | 2017-09-29 | Close
782 | GRT-DS-IP-DT-170268 | GRT-DF04-P0ZEN-144514 | [Piping General]_Stress Analysis Report for Aux.steam system | B | 2017-09-13 | 16 | A | 2017-09-29 | Close
783 | GRT-DS-IP-DT-170268 | GRT-DF04-P0ZEN-144515 | [Piping General]_Stress Analysis Report for Feedwater system | B | 2017-09-13 | 16 | A | 2017-09-29 | Close
814 | GRT-DS-IP-DT-170278 | GRT-UE00-P1H-300006 | [HRSG]_GENERAL ARRANGEMENT | C | 2017-09-14 | 42 | DEEMED APPROVAL | 2017-10-26 | Close
815 | GRT-DS-IP-DT-170278 | GRT-YB03-P1H-300033 | [HRSG]_CABLE CONNECTION DIAGRAM | A | 2017-09-14 | 30 | A | 2017-10-14 | Close
816 | GRT-DS-IP-DT-170278 | GRT-YT01-P1H-300068 | [HRSG]_DIVERTER & GUILLOTINE DAMPER DOCUMENT PACKAGE | A | 2017-09-14 | 45 | A | 2017-10-29 | Close
817 | GRT-DS-IP-DT-170278 | GRT-YT01-P1H-300069 | [HRSG]_ SPEC. & DRAWING FOR PREHEATER RECIRCULATION PUMP | A | 2017-09-14 | 45 | A | 2017-10-29 | Close
818 | GRT-DS-IP-DT-170279 | GRT-YT01-P1H-300056 | [HRSG]_DATA & BOM OF INSULATION FOR DRUM AND BLOWDOWN TANK | 0 | 2017-09-14 | 4 | APPROVED | 2017-09-18 | Close
819 | GRT-DS-IP-DT-170286 | GRT-YK00-P0ZEN-164301 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - General Notes | 0 | 2017-09-14 | 4 | APPROVED | 2017-09-18 | Close
820 | GRT-DS-IP-DT-170286 | GRT-YK00-P0ZEN-164302 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Symbol & Legend | 0 | 2017-09-14 | 4 | APPROVED | 2017-09-18 | Close
821 | GRT-DS-IP-DT-170286 | GRT-YK00-P0ZEN-164303 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Material List | 0 | 2017-09-14 | 4 | APPROVED | 2017-09-18 | Close
822 | GRT-DS-IP-DT-170286 | GRT-YK00-P0ZEN-164304 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Pressure Transmitter / Switch | 0 | 2017-09-14 | 4 | APPROVED | 2017-09-18 | Close
823 | GRT-DS-IP-DT-170286 | GRT-YK00-P0ZEN-164305 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Diff. Press. Transmitter / Switch | 0 | 2017-09-14 | 4 | APPROVED | 2017-09-18 | Close
824 | GRT-DS-IP-DT-170286 | GRT-YK00-P0ZEN-164306 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Flow Transmitter / Switch | 0 | 2017-09-14 | 4 | APPROVED | 2017-09-18 | Close
825 | GRT-DS-IP-DT-170286 | GRT-YK00-P0ZEN-164307 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Level Transmitter / Switch | 0 | 2017-09-14 | 4 | APPROVED | 2017-09-18 | Close
826 | GRT-DS-IP-DT-170286 | GRT-YK00-P0ZEN-164308 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Pressure Gauge | 0 | 2017-09-14 | 4 | APPROVED | 2017-09-18 | Close
827 | GRT-DS-IP-DT-170286 | GRT-YK00-P0ZEN-164309 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Control Valve | 0 | 2017-09-14 | 4 | APPROVED | 2017-09-18 | Close
828 | GRT-DS-IP-DT-170286 | GRT-YK00-P0ZEN-164310 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Stanchion & Rack | 0 | 2017-09-14 | 4 | APPROVED | 2017-09-18 | Close
829 | GRT-DS-IP-DT-170286 | GRT-YK00-P0ZEN-164312 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Temp.Transmitter/ Guage/ Test Well | 0 | 2017-09-14 | 4 | APPROVED | 2017-09-18 | Close
830 | GRT-DS-IP-DT-170287 | GRT-YD06-P0ZEN-161113 | [INC_Plant_Overall_Design]_DCS Power Distribution Concept Diagram | 0 | 2017-09-14 | 4 | APPROVED | 2017-09-18 | Close
831 | GRT-DS-IP-DT-170287 | GRT-YF00-P0ZEN-161202 | [INC_Other_Sys_Logic&Loop]_Control Logic Diagram - Typical Function | 0 | 2017-09-14 | 4 | APPROVED | 2017-09-18 | Close
832 | GRT-DS-IP-DT-170287 | GRT-YF00-P0LBG-161204 | [AUX Steam System_I&C_Logic]_Control Logic Diagram for BOP | 0 | 2017-09-14 | 4 | APPROVED | 2017-09-18 | Close
833 | GRT-DS-IP-DT-170287 | GRT-YF00-P0LBG-161304 | [AUX Steam System_I&C_Loop]_Control Loop Diagram for BOP | 0 | 2017-09-14 | 4 | APPROVED | 2017-09-18 | Close
834 | GRT-DS-IP-DT-170287 | GRT-YF00-P0LC-161306 | [Condensate system_I&C_Loop]_Control Loop Diagram for BOP | 0 | 2017-09-14 | 4 | APPROVED | 2017-09-18 | Close
835 | GRT-DS-IP-DT-170280 | GRT-XW01-P0SCA-120031 | [Air Compressor]_MAIN MOTOR SPECIFICATION | A | 2017-09-14 | 45 | A | 2017-10-29 | Close
836 | GRT-DS-IP-DT-170288 | GRT-YF00-P0ZEN-161212 | [INC_Other_Sys_Logic&Loop]_Control Logic Diagram for Miscellaneous System | B | 2017-09-14 | 12 | A | 2017-09-26 | Close
837 | GRT-DS-IP-DT-170288 | GRT-YF00-P0ZEN-161312 | [INC_Other_Sys_Logic&Loop]_Control Loop Diagram for Miscellaneous System | B | 2017-09-14 | 12 | A | 2017-09-26 | Close
846 | GRT-DS-IP-DT-170291 | GRT-CV03-P0ZEN-163705 | [Instrument Installation materials(DHI)]_Technical Specification for Instrument Installation Materials | 0 | 2017-09-14 | 45 | A | 2017-10-29 | Close
850 | GRT-DS-IP-DT-170295 | GRT-YT01-P0PGB-113102 | [CCWP ]_DATA SHEET FOR CLOSED COOLING WATER PUMP | 0 | 2017-09-14 | 4 | APPROVED | 2017-09-18 | Close
851 | GRT-DS-IP-DT-170295 | GRT-YD00-P0PGB-113101 | [CCWP ]_GENERAL ARRANGEMENT DRAWING FOR CLOSED COOLING WATER PUMP | 0 | 2017-09-14 | 4 | APPROVED AS NOTED | 2017-09-18 | Close
852 | GRT-DS-IP-DT-170295 | GRT-YD00-P0PCC-113001 | [Aux. Cooling Water Pump]_GENERAL ARRANGEMENT DRAWING FOR AUXILIARY COOLING WATER PUMP | 0 | 2017-09-14 | 4 | APPROVED | 2017-09-18 | Close
838 | GRT-DS-IP-DT-170289 | GRT-XF00-P0SCA-120027 | [Air Compressor]_NAME PLATE DRAWING | B | 2017-09-15 | 25 | A | 2017-10-10 | Close
839 | GRT-DS-IP-DT-170290 | GRT-CQ02-P0SCA-120030 | [Air Compressor]_O & M MANUAL | A | 2017-09-15 | 44 | A | 2017-10-29 | Close
840 | GRT-DS-IP-DT-170292 | GRT-YV02-P0QC-130017 | [Chemical Dosing System]_INTERCONNECTION WIRING DIAGRAM | A | 2017-09-15 | 44 | I | 2017-10-29 | Close
841 | GRT-DS-IP-DT-170292 | GRT-YL22-P0QC-130018 | [Chemical Dosing System]_NAME PLATE DRAWING | A | 2017-09-15 | 44 | I | 2017-10-29 | Close
842 | GRT-DS-IP-DT-170292 | GRT-YF00-P0QC-130019 | [Chemical Dosing System]_CONTROL LOOP & LOGIC DIAGRAM | A | 2017-09-15 | 11 | I | 2017-09-26 | Close
843 | GRT-DS-IP-DT-170292 | GRT-YS01-P0QC-130020 | [Chemical Dosing System]_SCHEMATIC DIAGRAM | A | 2017-09-15 | 44 | I | 2017-10-29 | Close
844 | GRT-DS-IP-DT-170292 | GRT-YE00-P0QC-130021 | [Chemical Dosing System]_CABLE TRAY LAYOUT DRAWING | A | 2017-09-15 | 44 | I | 2017-10-29 | Close
845 | GRT-DS-IP-DT-170292 | GRT-YK00-P0QC-130022 | [Chemical Dosing System]_HOOK UP DRAWING | A | 2017-09-15 | 11 | I | 2017-09-26 | Close
847 | GRT-DS-IP-DT-170294 | GRT-YD00-P0LCB-121001 | [Condensate Extraction Pump]_GENERAL ARRANGEMENT DRAWING | D | 2017-09-15 | 44 | A | 2017-10-29 | Close
848 | GRT-DS-IP-DT-170293 | GRT-YT01-P0ZEN-111201 | [Safety Relief Valve(DHI)]_DATA SHEET FOR SAFETY AND RELIEF VALVE | A | 2017-09-15 | 44 | B | 2017-10-29 | Close
849 | GRT-DS-IP-DT-170293 | GRT-YK08-P0ZEN-111200 | [Safety Relief Valve(DHI)]_OUTLINE DRAWING FOR SAFEY AND RELIEF VALVE | A | 2017-09-15 | 44 | I | 2017-10-29 | Close
853 | GRT-DS-IP-DT-170297 | GRT-YD00-P0SCA-120007 | [Air Compressor]_AIR COMPRESSOR_GENERAL ARRANGEMENT DRAWING FOR AIR COMPRESSORS PACKAGE | 1 | 2017-09-15 | 11 | APPROVED AS NOTED | 2017-09-26 | Close
854 | GRT-DS-IP-DT-170297 | GRT-XB00-P0SCA-120013 | [Air Compressor]_FOUNDATION DRAWINGS | 1 | 2017-09-15 | 11 | APPROVED | 2017-09-26 | Close
855 | GRT-DS-IP-DT-170299 | GRT-YF00-P0ZEN-161405 | [INC_Start&Shutdown Diagram]_Plant Start-up & Shutdown Sequence Diagram for Hot Start-up | A | 2017-09-20 | 24 | A | 2017-10-14 | Close
856 | GRT-DS-IP-DT-170299 | GRT-YF00-P0ZEN-161404 | [INC_Start&Shutdown Diagram]_Plant Start-up & Shutdown Sequence Diagram for Warm Start-up | A | 2017-09-20 | 24 | A | 2017-10-14 | Close
857 | GRT-DS-IP-DT-170299 | GRT-YF00-P0ZEN-161403 | [INC_Start&Shutdown Diagram]_Plant Start-up & Shutdown Sequence Diagram for Cold Start-up | A | 2017-09-20 | 24 | A | 2017-10-14 | Close
858 | GRT-DS-IP-DT-170304 | GRT-YL00-P0MAJ-460227 | Instrument Data sheet For Water Box Vacuum Pump | 0 | 2017-09-20 | 24 | A | 2017-10-14 | Close
859 | GRT-DS-IP-DT-170304 | GRT-YL00-P0MAJ-460127 | Instrument Data sheet For Condenser Vacuum Pump | 0 | 2017-09-20 | 24 | A | 2017-10-14 | Close
860 | GRT-DS-IP-DT-170305 | GRT-XK00-P0MAJ-460214 | Baseframe Drawing For Water Box Vacuum Pump | A | 2017-09-20 | 24 | A | 2017-10-14 | Close
861 | GRT-DS-IP-DT-170305 | GRT-XK00-P0MAJ-460213 | Tank Drawing For Water Box Vacuum Pump | A | 2017-09-20 | 24 | A | 2017-10-14 | Close
862 | GRT-DS-IP-DT-170305 | GRT-XK00-P0MAJ-460114 | Baseframe Drawing For Condenser Vacuum Pump | A | 2017-09-20 | 24 | A | 2017-10-14 | Close
863 | GRT-DS-IP-DT-170305 | GRT-XK00-P0MAJ-460113 | Tank Drawing For Condenser Vacuum Pump | A | 2017-09-20 | 24 | A | 2017-10-14 | Close
864 | GRT-DS-IP-DT-170298 | GRT-YT01-P0MAG-410007 | Condenser_Data Sheet | 0 | 2017-09-20 | 24 | B | 2017-10-14 | Close
865 | GRT-DS-IP-DT-170298 | GRT-YK08-P0MAG-410002 | Condenser_General Arrangement | 0 | 2017-09-20 | 24 | A | 2017-10-14 | Close
866 | GRT-DS-IP-DT-170298 | GRT-YK08-P0MAG-410001 | Condenser_General Layout | 0 | 2017-09-20 | 24 | B | 2017-10-14 | Close
867 | GRT-DS-IP-DT-170298 | GRT-XL00-P0MAG-410004 | Condenser_Connection Detail | 0 | 2017-09-20 | 24 | A | 2017-10-14 | Close
868 | GRT-DS-IP-DT-170298 | GRT-XL00-P0MAG-410003 | Condenser_Connection List | 0 | 2017-09-20 | 24 | A | 2017-10-14 | Close
869 | GRT-DS-IP-DT-170298 | GRT-VL00-P0MAG-410005 | Condenser_Foundation Assembly | 1 | 2017-09-20 | 24 | I | 2017-10-14 | Close
870 | GRT-DS-IP-DT-170300 | GRT-YU02-P0SCA-120014 | [Air Compressor]_SINGLE LINE DIAGRAM | 0 | 2017-09-20 | 24 | A | 2017-10-14 | Close
871 | GRT-DS-IP-DT-170300 | GRT-YL01-P0SCA-120020 | [Air Compressor]_DATALINK INTERFACE IO LIST | 0 | 2017-09-20 | 24 | I | 2017-10-14 | Close
872 | GRT-DS-IP-DT-170300 | GRT-YL01-P0SCA-120019 | [Air Compressor]_PLC HARDWIRED IO LIST | 0 | 2017-09-20 | 24 | I | 2017-10-14 | Close
876 | GRT-DS-IP-DT-170306 | GRT-YT01-P0SM-123002 | [Crane & Hoist(DHI)]_HOIST_DATA SHEETS FOR HOISTS | B | 2017-09-20 | 24 | I | 2017-10-14 | Close
877 | GRT-DS-IP-DT-170306 | GRT-YD00-P0SM-123001 | [Crane & Hoist(DHI)]_HOIST_GA DRAWING FOR HOISTS | B | 2017-09-20 | 24 | B | 2017-10-14 | Close
878 | GRT-DS-IP-DT-170307 | GRT-XG08-P0MA-200005 | [STG]_P&I Diagrams | 0 | 2017-09-20 | 24 | A | 2017-10-14 | Close
883 | GRT-DS-IP-DT-170311 | GRT-QM01-P0ZEN-040001 | Shop Inspection and Test Plan for Manufacturing | 0 | 2017-09-20 | 6 | APPROVED AS NOTED | 2017-09-26 | Close
873 | GRT-DS-IP-DT-170301 | GRT-YL00-P0SCA-120023 | [Air Compressor]_INSTRUMENT LIST | 0 | 2017-09-22 | 22 | I | 2017-10-14 | Close
874 | GRT-DS-IP-DT-170301 | GRT-YK00-P0SCA-120025 | [Air Compressor]_INSTRUMENTATION HOOK - UP DRAWING | 0 | 2017-09-22 | 22 | I | 2017-10-14 | Close
875 | GRT-DS-IP-DT-170301 | GRT-CV03-P0SCA-120024 | [Air Compressor]_INSTRUMENT SPECIFICATION | 0 | 2017-09-22 | 22 | A | 2017-10-14 | Close
879 | GRT-DS-IP-DT-170309 | GRT-YF00-P1LBA-161303 | [HP & LP steam system_I&C_Loop]_Control Loop Diagram for BOP | 0 | 2017-09-25 | 1 | APPROVED | 2017-09-26 | Close
880 | GRT-DS-IP-DT-170309 | GRT-YF00-P1LBA-161203 | [HP & LP steam system_I&C_Logic]_Control Logic Diagram for BOP | 0 | 2017-09-25 | 1 | APPROVED | 2017-09-26 | Close
881 | GRT-DS-IP-DT-170310 | GRT-YF00-P0LA-161205 | [Feedwater system_I&C_Logic]_Control Logic Diagram for BOP | B | 2017-09-25 | 19 | A | 2017-10-14 | Close
882 | GRT-DS-IP-DT-170310 | GRT-YF00-P0LA-161305 | [Feedwater system_I&C_Loop]_Control Loop Diagram for BOP | B | 2017-09-25 | 19 | A | 2017-10-14 | Close
884 | GRT-DS-IP-DT-170312 | GRT-YT01-P0LCB-121007 | [Condensate Extraction Pump]_SUCTION STRAINER SPECIFICATION | B | 2017-09-25 | 15 | I | 2017-10-10 | Close
885 | GRT-DS-IP-DT-170314 | GRT-YD00-P0LAC-122002 | [HP Feed Water Pump]_GENERAL ARRANGEMENT DRAWING | B | 2017-09-25 | 19 | A | 2017-10-14 | Close
886 | GRT-DS-IP-DT-170315 | GRT-YK10-P0LAC-122004 | [HP Feed Water Pump]_SECTIONAL DRAWING FOR PUMP | 0 | 2017-09-25 | 1 | APPROVED AS NOTED | 2017-09-26 | Close
887 | GRT-DS-IP-DT-170316 | GRT-YD00-P0LAC-122502 | [LP Feed Water Pump]_GENERAL ARRANGEMENT DRAWING | B | 2017-09-25 | 19 | A | 2017-10-14 | Close
888 | GRT-DS-IP-DT-170317 | GRT-YK10-P0LAC-122504 | [LP Feed Water Pump]_SECTIONAL DRAWING FOR PUMP | B | 2017-09-25 | 19 | A | 2017-10-14 | Close
889 | GRT-DS-IP-DT-170318 | GRT-YL22-P0LAC-122507 | [LP Feed Water Pump]_NAME PLATE DRAWING | 0 | 2017-09-25 | 1 | APPROVED | 2017-09-26 | Close
890 | GRT-DS-IP-DT-170318 | GRT-YL22-P0LAC-122007 | [HP Feed Water Pump]_NAME PLATE DRAWING | 0 | 2017-09-25 | 1 | APPROVED | 2017-09-26 | Close
891 | GRT-DS-IP-DT-170319 | GRT-YT01-P0LAC-122505 | [LP Feed Water Pump]_DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | B | 2017-09-25 | 19 | A | 2017-10-14 | Close
892 | GRT-DS-IP-DT-170319 | GRT-YT01-P0LAC-122503 | [LP Feed Water Pump]_DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | B | 2017-09-25 | 19 | B | 2017-10-14 | Close
893 | GRT-DS-IP-DT-170319 | GRT-YT01-P0LAC-122005 | [HP Feed Water Pump]_DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | B | 2017-09-25 | 19 | A | 2017-10-14 | Close
894 | GRT-DS-IP-DT-170319 | GRT-YT01-P0LAC-122003 | [HP Feed Water Pump]_DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | B | 2017-09-25 | 19 | B | 2017-10-14 | Close
895 | GRT-DS-IP-DT-170319 | GRT-XG02-P0LAC-122501 | [LP Feed Water Pump]_P&I DIAGRAM | B | 2017-09-25 | 19 | A | 2017-10-14 | Close
896 | GRT-DS-IP-DT-170319 | GRT-XG02-P0LAC-122001 | [HP Feed Water Pump]_P&I DIAGRAM | B | 2017-09-25 | 19 | A | 2017-10-14 | Close
897 | GRT-DS-IP-DT-170303 | GRT-YK10-P1H-300050 | [HRSG]_MANUAL VALVE ASSEMBLY DRAWING FOR EXTERNAL PIPING | A | 2017-09-27 | 17 | I | 2017-10-14 | Close
898 | GRT-DS-IP-DT-170303 | GRT-YT01-P1H-300063 | [HRSG]_CEMS DATASHEET & DRAWINGS | A | 2017-09-27 | 17 | A | 2017-10-14 | Close
899 | GRT-DS-IP-DT-170303 | GRT-XH01-P1H-300021 | [HRSG]_PIPE SUPPORT DRAWING FOR EXTERNAL PIPING | A | 2017-09-27 | 17 | I | 2017-10-14 | Close
900 | GRT-DS-IP-DT-170303 | GRT-YR01-P1H-300055 | [HRSG]_CONSERVATION PROCEDURE | A | 2017-09-27 | 17 | I | 2017-10-14 | Close
901 | GRT-DS-IP-DT-170303 | GRT-YR01-P1H-300054 | [HRSG]_CHEMICAL CLEANING PROCEDURE | A | 2017-09-27 | 17 | I | 2017-10-14 | Close
902 | GRT-DS-IP-DT-170303 | GRT-XJ00-P1H-300024 | [HRSG]_ERECTION ISOMETRIC DRAWING FOR PIPNG FABRICATION STANDARD | A | 2017-09-27 | 17 | I | 2017-10-14 | Close
903 | GRT-DS-IP-DT-170303 | GRT-YT02-P1H-300065 | [HRSG]_REMOTE DRUM LEVEL INDICATOR DATASHEET & DRAWINGS | A | 2017-09-27 | 17 | A | 2017-10-14 | Close
904 | GRT-DS-IP-DT-170303 | GRT-YK09-P1H-300049 | [HRSG]_SPECIALTY DRAWING FOR EXTERNAL PIPING | A | 2017-09-27 | 17 | I | 2017-10-14 | Close
905 | GRT-DS-IP-DT-170308 | GRT-DM02-P1H-300005 | [HRSG]_GENERAL NOTE FOR STEEL STRUCTURE | 0 | 2017-09-27 | 32 | APPROVED | 2017-10-29 | Close
906 | GRT-DS-IP-DT-170308 | GRT-VN03-P1H-300010 | [HRSG]_TYPICAL PLATFORM DETAIL FOR STEEL STRUCTURE | 0 | 2017-09-27 | 32 | APPROVED | 2017-10-29 | Close
907 | GRT-DS-IP-DT-170308 | GRT-XG02-P1H-300020 | [HRSG]_P&I DIAGRAM | 0 | 2017-09-27 | 32 | APPROVED | 2017-10-29 | Close
908 | GRT-DS-IP-DT-170308 | GRT-YL00-P1H-300051 | [HRSG]_INSTRUMENT LIST | 0 | 2017-09-27 | 32 | APPROVED | 2017-10-29 | Close
909 | GRT-DS-IP-DT-170308 | GRT-DE00-P1H-300067 | [HRSG]_PIPING MATERIAL CLASSIFICATION | 0 | 2017-09-27 | 32 | APPROVED AS NOTED | 2017-10-29 | Close
910 | GRT-DS-IP-DT-170320 | GRT-YL22-P0LB-111108 | [Bypass Valve & PRDS]_Name Plate Drawing | A | 2017-09-27 | 17 | B | 2017-10-14 | Close
911 | GRT-DS-IP-DT-170321 | GRT-YK00-P0MA-200040 | [STG]_I&C Lay-outs | 0 | 2017-09-29 | 3 | APPROVED | 2017-10-02 | Close
912 | GRT-DS-IP-DT-170321 | GRT-XB00-P0MA-200009 | [STG]_Lay down plan | 0 | 2017-09-29 | 3 | APPROVED | 2017-10-02 | Close
913 | GRT-DS-IP-DT-170322 | GRT-YT01-P0MAJ-460206 | Heat Exchanger Drawing and Data Sheet For Water Box Vacuum Pump | 0 | 2017-09-29 | 3 | APPROVED | 2017-10-02 | Close
914 | GRT-DS-IP-DT-170322 | GRT-YT01-P0MAJ-460106 | Heat Exchanger Drawing and Data Sheet For Condenser Vacuum Pump | 0 | 2017-09-29 | 3 | APPROVED | 2017-10-02 | Close
915 | GRT-DS-IP-DT-170322 | GRT-YT01-P0MAJ-460104 | Technical Data Sheet | 0 | 2017-09-29 | 3 | APPROVED | 2017-10-02 | Close
916 | GRT-DS-IP-DT-170322 | GRT-XN00-P0MAJ-460219 | Valve and Specialty List For Water Box Vacuum Pump | 0 | 2017-09-29 | 3 | APPROVED | 2017-10-02 | Close
917 | GRT-DS-IP-DT-170322 | GRT-XN00-P0MAJ-460119 | Valve and Specialty List For Condenser Vacuum Pump | 0 | 2017-09-29 | 3 | APPROVED | 2017-10-02 | Close
918 | GRT-DS-IP-DT-170322 | GRT-XK00-P0MAJ-460212 | Outline & Sectional Drawing For Water Box Vacuum Pump | 0 | 2017-09-29 | 3 | APPROVED | 2017-10-02 | Close
919 | GRT-DS-IP-DT-170322 | GRT-XK00-P0MAJ-460112 | Outline & Sectional Drawing For Condenser Vacuum Pump | 0 | 2017-09-29 | 3 | APPROVED | 2017-10-02 | Close
920 | GRT-DS-IP-DT-170322 | GRT-XG02-P0MAJ-460201 | P & ID For Water Box Vacuum Pump | 0 | 2017-09-29 | 3 | APPROVED AS NOTED | 2017-10-02 | Close
921 | GRT-DS-IP-DT-170322 | GRT-XG02-P0MAJ-460101 | P & ID For Condenser Vacuum Pump | 0 | 2017-09-29 | 3 | APPROVED AS NOTED | 2017-10-02 | Close
922 | GRT-DS-IP-DT-170322 | GRT-PL03-P0MAJ-460220 | Terminal Point List For Water Box Vacuum Pump | 0 | 2017-09-29 | 3 | APPROVED AS NOTED | 2017-10-02 | Close
923 | GRT-DS-IP-DT-170322 | GRT-PL03-P0MAJ-460120 | Terminal Point List For Condenser Vacuum Pump | 0 | 2017-09-29 | 3 | APPROVED AS NOTED | 2017-10-02 | Close
924 | GRT-DS-IP-DT-170323 | GRT-QA00-P0H-040017 | [HRSG]_Welding Consumable Control Procedure for HRSG Pressure Part | 0 | 2017-09-29 | 3 | APPROVED | 2017-10-02 | Close
925 | GRT-DS-IP-DT-170325 | GRT-YL00-P0LCB-121010 | [Condensate Extraction Pump]_INSTRUMENT LIST | B | 2017-09-29 | 11 | I | 2017-10-10 | Close
926 | GRT-DS-IP-DT-170325 | GRT-YL22-P0LCB-121012 | [Condensate Extraction Pump]_NAME PLATE DRAWING | B | 2017-09-29 | 11 | I | 2017-10-10 | Close
927 | GRT-DS-IP-DT-170324 | GRT-CV03-P0ZEN-163706 | [Local Boxes(DHI)]_Technical Specification for Junction Box & Racks | 0 | 2017-09-29 | 3 | APPROVED | 2017-10-02 | Close
928 | GRT-DS-IP-DT-170328 | GRT-YF00-P0SCA-120021 | [Air Compressor]_CONTROL LOGIC & LOOP DIAGRAM | B | 2017-09-29 | 15 | A | 2017-10-14 | Close
929 | GRT-DS-IP-DT-170329 | GRT-YF02-P0SCA-120017 | [Air Compressor]_CONTROL DESCRIPTION (PHILOSOPHY) | 0 | 2017-09-29 | 3 | APPROVED AS NOTED | 2017-10-02 | Close
930 | GRT-DS-IP-DT-170331 | GRT-DB00-P0MAJ-460118 | Performance Curves For Condenser Vacuum Pump | 0 | 2017-09-29 | 3 | APPROVED AS NOTED | 2017-10-02 | Close
931 | GRT-DS-IP-DT-170331 | GRT-DB00-P0MAJ-460218 | Performance Curves For Water Box Vacuum Pump | 0 | 2017-09-29 | 3 | APPROVED AS NOTED | 2017-10-02 | Close
932 | GRT-DS-IP-DT-170331 | GRT-XB02-P0MAJ-460111 | Foundation Drawing For Condenser Vacuum Pump | 0 | 2017-09-29 | 3 | APPROVED | 2017-10-02 | Close
933 | GRT-DS-IP-DT-170331 | GRT-XB02-P0MAJ-460211 | Foundation Drawing For Water Box Vacuum Pump | 0 | 2017-09-29 | 3 | APPROVED | 2017-10-02 | Close
934 | GRT-DS-IP-DT-170331 | GRT-YK08-P0MAJ-460100 | General Arrangement Drawing For Condenser Vacuum Pump | 0 | 2017-09-29 | 3 | APPROVED | 2017-10-02 | Close
935 | GRT-DS-IP-DT-170331 | GRT-YK08-P0MAJ-460200 | General Arrangement Drawing For Water Box Vacuum Pump | 0 | 2017-09-29 | 3 | APPROVED | 2017-10-02 | Close
946 | GRT-DS-IP-DT-170326 | GRT-YU03-P0MA-200043 | [STG]_Control system. Hardware specification | A | 2017-09-29 | 11 | I | 2017-10-10 | Close
947 | GRT-DS-IP-DT-170326 | GRT-YD00-P0MA-200024 | [STG]_Generator Specification | B | 2017-09-29 | 11 | I | 2017-10-10 | Close
948 | GRT-DS-IP-DT-170327 | GRT-YL00-P0MA-200037 | [STG]_Measurement list | 0 | 2017-09-29 | 3 | APPROVED | 2017-10-02 | Close
949 | GRT-DS-IP-DT-170327 | GRT-YF00-P0MA-200036 | [STG]_Consumer schemes | 0 | 2017-09-29 | 3 | APPROVED | 2017-10-02 | Close
950 | GRT-DS-IP-DT-170332 | GRT-YV02-P0QU-130032 | [Sampling System]_INTERCONNECTION WIRING DIAGRAM | A | 2017-09-29 | 11 | I | 2017-10-10 | Close
951 | GRT-DS-IP-DT-170332 | GRT-YF00-P0QU-130033 | [Sampling System]_CONTROL LOOP & LOGIC DIAGRAM | A | 2017-09-29 | 11 | I | 2017-10-10 | Close
952 | GRT-DS-IP-DT-170332 | GRT-YS01-P0QU-130034 | [Sampling System]_SCHEMATIC DIAGRAM | A | 2017-09-29 | 11 | I | 2017-10-10 | Close
953 | GRT-DS-IP-DT-170333 | GRT-YD00-P0MA-200006 | [STG]_General Arrangement Drawing | 0 | 2017-09-29 | 3 | APPROVED | 2017-10-02 | Close
954 | GRT-DS-IP-DT-170333 | GRT-YU03-P0MA-200041 | [STG]_Control system function philosophy | 0 | 2017-09-29 | 3 | APPROVED AS NOTED | 2017-10-02 | Close
955 | GRT-DS-IP-DT-170334 | GRT-YV02-P0LDB-130052 | [Condensate Filter System]_INTERCONNECTION WIRING DIAGRAM | A | 2017-09-29 | 14 | DEEMED APPROVAL | 2017-10-13 | Close
956 | GRT-DS-IP-DT-170334 | GRT-YS01-P0LDB-130055 | [Condensate Filter System]_SCHEMATIC DIAGRAM | A | 2017-09-29 | 14 | DEEMED APPROVAL | 2017-10-13 | Close
957 | GRT-DS-IP-DT-170335 | GRT-XS00-P0LDB-130038 | [Condensate Filter System]_SYSTEM DESCRIPTION | B | 2017-10-10 | 23 | A | 2017-11-02 | Close
958 | GRT-DS-IP-DT-170335 | GRT-XG02-P0LDB-130036 | [Condensate Filter System]_P&ID | B | 2017-10-10 | 23 | A | 2017-11-02 | Close
959 | GRT-DS-IP-DT-170335 | GRT-XB02-P0LDB-130044 | [Condensate Filter System]_FOUNDATION AND LOADING DATA | B | 2017-10-10 | 23 | I | 2017-11-02 | Close
960 | GRT-DS-IP-DT-170335 | GRT-XA00-P0LDB-130037 | [Condensate Filter System]_GENERAL ARRANGEMENT DRAWING | B | 2017-10-10 | 23 | B | 2017-11-02 | Close
961 | GRT-DS-IP-DT-170335 | GRT-CC07-P0LDB-130039 | [Condensate Filter System]_CALCULATION SHEET | B | 2017-10-10 | 23 | B | 2017-11-02 | Close
962 | GRT-DS-IP-DT-170337 | GRT-YD00-P0LCB-121014 | [Condensate Extraction Pump]_VFD OUTLINE AND DATA SHEET | A | 2017-10-10 | 22 | DEEMED APPROVAL | 2017-11-01 | Close
963 | GRT-DS-IP-DT-170313 | GRT-YT01-P1H-300061 | [HRSG]_DESH. DATASHEET & DRAWINGS | B | 2017-10-10 | 23 | A | 2017-11-02 | Close
964 | GRT-DS-IP-DT-170313 | GRT-YT01-P1H-300060 | [HRSG]_CV DATASHEET & DRAWINGS | B | 2017-10-10 | 23 | A | 2017-11-02 | Close
965 | GRT-DS-IP-DT-170313 | GRT-YT01-P1H-300059 | [HRSG]_MOV DATASHEET & DRAWINGS | B | 2017-10-10 | 23 | B | 2017-11-02 | Close
966 | GRT-DS-IP-DT-170313 | GRT-UE00-P1H-300009 | [HRSG]_ARRANGEMENT OF MAIN STACK& FIELD ERECTION | D | 2017-10-10 | 23 | I | 2017-11-02 | Close
967 | GRT-DS-IP-DT-170313 | GRT-YK01-P1H-300048 | [HRSG]_INSTRUMENT INSTALLATION DETAIL DRAWINGS | B | 2017-10-10 | 24 | A | 2017-11-03 | Close
968 | GRT-DS-IP-DT-170313 | GRT-VN03-P1H-300013 | [HRSG]_ARRANGEMENT FOR PLATFORM STRUCTURE | D | 2017-10-10 | 22 | DEEMED APPROVAL | 2017-11-01 | Close
969 | GRT-DS-IP-DT-170313 | GRT-YD00-P1H-300041 | [HRSG]_SPEC. & DRAWING FOR SILENCER | B | 2017-10-10 | 23 | A | 2017-11-02 | Close
970 | GRT-DS-IP-DT-170313 | GRT-YD00-P1H-300040 | [HRSG]_SPEC. & DRAWING FOR STACK DAMPER | B | 2017-10-10 | 23 | A | 2017-11-02 | Close
971 | GRT-DS-IP-DT-170313 | GRT-YD00-P1H-300034 | [HRSG]_PRESSURE PART ARRANGEMENT | E | 2017-10-10 | 23 | I | 2017-11-02 | Close
988 | GRT-DS-IP-DT-170346 | GRT-QA00-P0H-040018 | [HRSG]_Welding Consumable Control Procedure for HRSG Piping | A | 2017-10-10 | 23 | I | 2017-11-02 | Close
989 | GRT-DS-IP-DT-170347 | GRT-YT01-P0LDB-130047 | [Condensate Filter System]_TECHNICAL DATASHEET | B | 2017-10-10 | 23 | A | 2017-11-02 | Close
990 | GRT-DS-IP-DT-170347 | GRT-YL00-P0LDB-130042 | [Condensate Filter System]_INSTRUMENT LIST | B | 2017-10-10 | 22 | DEEMED APPROVAL | 2017-11-01 | Close
1001 | GRT-DS-IP-DT-170296 | GRT-CN00-P0ZEN-110100 | [Plant Overall]_OPERATION PHILOSOPHY OF OVERALL PLANT | B | 2017-10-10 | 23 | B | 2017-11-02 | Close
972 | GRT-DS-IP-DT-170336 | GRT-YD00-P0PGB-113201 | [Blowdown Cooler]_OUTLINE DRAWING FOR PLATE TYPE HEAT EXCHANGER | 0 | 2017-10-13 | 0 | APPROVED | 2017-10-13 | Close
973 | GRT-DS-IP-DT-170338 | GRT-YF00-P0PA-161307 | [Aux. Cooling Water System_I&C_Loop]_Control Loop Diagram for BOP | 0 | 2017-10-13 | 0 | APPROVED | 2017-10-13 | Close
974 | GRT-DS-IP-DT-170338 | GRT-YF00-P0PG-161208 | [Closed cooling water system_I&C_Logic]_Control Logic Diagram for BOP | 0 | 2017-10-13 | 0 | APPROVED | 2017-10-13 | Close
975 | GRT-DS-IP-DT-170338 | GRT-YF00-P0PG-161308 | [Closed cooling water system_I&C_Loop]_Control Loop Diagram for BOP | 0 | 2017-10-13 | 0 | APPROVED | 2017-10-13 | Close
976 | GRT-DS-IP-DT-170338 | GRT-YF00-P0ZEN-161211 | [INC_Other_Sys_Logic&Loop]_Control Logic Diagram for Interface with other Control System | 0 | 2017-10-13 | 0 | APPROVED | 2017-10-13 | Close
977 | GRT-DS-IP-DT-170338 | GRT-YF00-P0ZEN-161212 | [INC_Other_Sys_Logic&Loop]_Control Logic Diagram for Miscellaneous System | 0 | 2017-10-13 | 0 | APPROVED | 2017-10-13 | Close
978 | GRT-DS-IP-DT-170338 | GRT-YF00-P0ZEN-161311 | [INC_Other_Sys_Logic&Loop]_Control Loop Diagram for Interface with other Control System | 0 | 2017-10-13 | 0 | APPROVED | 2017-10-13 | Close
979 | GRT-DS-IP-DT-170338 | GRT-YF00-P0ZEN-161312 | [INC_Other_Sys_Logic&Loop]_Control Loop Diagram for Miscellaneous System | 0 | 2017-10-13 | 0 | APPROVED | 2017-10-13 | Close
980 | GRT-DS-IP-DT-170338 | GRT-YF00-P0PA-161207 | [Aux. Cooling Water System_I&C_Logic]_Control Logic Diagram for BOP | 0 | 2017-10-13 | 0 | APPROVED | 2017-10-13 | Close
986 | GRT-DS-IP-DT-170344 | GRT-YK08-P0LB-111101 | [Bypass Valve & PRDS]_OUTLINE DRAWING FOR BYPASS AND PRDS | B | 2017-10-13 | 20 | A | 2017-11-02 | Close
987 | GRT-DS-IP-DT-170345 | GRT-YL01-P0ZEN-161101 | [INC_DCS_IO]_DCS I/O Database | 0 | 2017-10-13 | 0 | APPROVED AS NOTED | 2017-10-13 | Close
991 | GRT-DS-IP-DT-170348 | GRT-CV03-P0ZEN-162301 | [VMS]_Technical Specification & Datasheet for Vibration Monitoring System | B | 2017-10-13 | 21 | A | 2017-11-03 | Close
992 | GRT-DS-IP-DT-170349 | GRT-YK09-P0MA-200032 | [STG]_Cabling system | A | 2017-10-13 | 41 | I | 2017-11-23 | Close
993 | GRT-DS-IP-DT-170350 | GRT-YT01-P0MAJ-460215 | Recirculation Pump Data Sheet and Characteristic Curves and Drawing For WBVP | B | 2017-10-13 | 41 | I | 2017-11-23 | Close
994 | GRT-DS-IP-DT-170350 | GRT-YT01-P0MAJ-460205 | Motor Data sheet and Characteristic Curves and Drawing For WBVP | B | 2017-10-13 | 20 | I | 2017-11-02 | Close
995 | GRT-DS-IP-DT-170350 | GRT-YT01-P0MAJ-460115 | Recirculation Pump Data Sheet and Characteristic Curves and Drawing For CVP | B | 2017-10-13 | 41 | I | 2017-11-23 | Close
996 | GRT-DS-IP-DT-170350 | GRT-YT01-P0MAJ-460105 | Motor Data sheet and Characteristic Curves and Drawing For CVP | B | 2017-10-13 | 20 | I | 2017-11-02 | Close
997 | GRT-DS-IP-DT-170350 | GRT-XK00-P0MAJ-460217 | Coupling Drawing For Water Box Vacuum Pump | A | 2017-10-13 | 20 | I | 2017-11-02 | Close
998 | GRT-DS-IP-DT-170350 | GRT-XK00-P0MAJ-460216 | Name Plate Drawing For Water Box Vacuum Pump | A | 2017-10-13 | 20 | A | 2017-11-02 | Close
999 | GRT-DS-IP-DT-170350 | GRT-XK00-P0MAJ-460117 | Coupling Drawing For Condenser Vacuum Pump | A | 2017-10-13 | 20 | I | 2017-11-02 | Close
1000 | GRT-DS-IP-DT-170350 | GRT-XK00-P0MAJ-460116 | Name Plate Drawing For Condenser Vacuum Pump | A | 2017-10-13 | 20 | A | 2017-11-02 | Close
1002 | GRT-DS-IP-DT-170351 | GRT-YT01-P0LB-111100 | [Bypass Valve & PRDS]_DATA SHEET FOR BYPASS AND PRDS | 0 | 2017-10-13 | 0 | APPROVED AS NOTED | 2017-10-13 | Close
1003 | GRT-DS-IP-DT-170351 | GRT-YK09-P0LB-111106 | [Bypass Valve & PRDS]_Sectional drawing | 0 | 2017-10-13 | 0 | APPROVED | 2017-10-13 | Close
1004 | GRT-DS-IP-DT-170352 | GRT-YD05-P0ZEN-161123 | [DCS]_HMI Graphic Drawing | A | 2017-10-13 | 21 | B | 2017-11-03 | Close
1005 | GRT-DS-IP-DT-170353 | GRT-YF00-P0LDB-130054 | [Condensate Filter System]_CONTROL LOOP & LOGIC DIAGRAM | A | 2017-10-13 | 21 | I | 2017-11-03 | Close
1006 | GRT-DS-IP-DT-170353 | GRT-YE00-P0LDB-130056 | [Condensate Filter System]_CABLE TRAY LAYOUT DRAWING | A | 2017-10-13 | 21 | I | 2017-11-03 | Close
1007 | GRT-DS-IP-DT-170353 | GRT-YT01-P0LDB-130051 | [Condensate Filter System]_INSTRUMENT DATA SHEET | B | 2017-10-13 | 21 | A | 2017-11-03 | Close
1008 | GRT-DS-IP-DT-170354 | GRT-YT01-P0ZEN-111201 | [Safety Relief Valve(DHI)]_DATA SHEET FOR SAFETY AND RELIEF VALVE | 0 | 2017-10-13 | 0 | APPROVED AS NOTED | 2017-10-13 | Close
1009 | GRT-DS-IP-DT-170354 | GRT-YK08-P0ZEN-111200 | [Safety Relief Valve(DHI)]_OUTLINE DRAWING FOR SAFEY AND RELIEF VALVE | 0 | 2017-10-13 | 0 | APPROVED | 2017-10-13 | Close
1010 | GRT-DS-IP-DT-170355 | GRT-YL22-P0PGB-113108 | [CCWP ]_NAMEPLATE DRAWING FOR CLOSED COOLING WATER PUMP | 0 | 2017-10-13 | 0 | APPROVED AS NOTED | 2017-10-13 | Close
1011 | GRT-DS-IP-DT-170355 | GRT-YL22-P0PCC-113008 | [Aux. Cooling Water Pump]_NAMEPLATE DRAWING FOR AUXILIARY COOLING WATER PUMP | 0 | 2017-10-13 | 0 | APPROVED AS NOTED | 2017-10-13 | Close
1012 | GRT-DS-IP-DT-170356 | GRT-YK08-P0MAG-410012 | Transition Piece Assembly between LP TBN and Condenser | A | 2017-10-13 | 20 | A | 2017-11-02 | Close
1013 | GRT-DS-IP-DT-170357 | GRT-YM01-P0LCB-121009 | [Condensate Extraction Pump]_MOTOR DATA SHEET & CHARACTERISTIC CURVE | B | 2017-10-13 | 20 | A | 2017-11-02 | Close
1016 | GRT-DS-IP-DT-170359 | GRT-YD00-P0LAC-122508 | [LP Feed Water Pump]_VFD OUTLINE AND DATA SHEET | A | 2017-10-13 | 21 | I | 2017-11-03 | Close
1021 | GRT-DS-IP-DT-170361 | GRT-XG02-P0PBB-440101 | Debris Filter_P & I Diagram | 0 | 2017-10-13 | 0 | APPROVED | 2017-10-13 | Close
1022 | GRT-DS-IP-DT-170361 | GRT-XG02-P0PAH-440001 | Condenser Tube Cleaning System_P & I Diagram | 0 | 2017-10-13 | 0 | APPROVED | 2017-10-13 | Close
1023 | GRT-DS-IP-DT-170361 | GRT-YT01-P0PBB-440103 | Debris Filter_Technical Data Sheet | 0 | 2017-10-13 | 0 | APPROVED AS NOTED | 2017-10-13 | Close
1024 | GRT-DS-IP-DT-170361 | GRT-YT01-P0PAH-440058 | CCW HEX Tube Cleaning System_Technical Data Sheet | 0 | 2017-10-13 | 0 | APPROVED AS NOTED | 2017-10-13 | Close
1025 | GRT-DS-IP-DT-170361 | GRT-YT01-P0PAH-440008 | Condenser Tube Cleaning System_Technical Data Sheet | 0 | 2017-10-13 | 0 | APPROVED AS NOTED | 2017-10-13 | Close
1026 | GRT-DS-IP-DT-170361 | GRT-YK08-P0PAH-440002 | Condenser Tube Cleaning System_Outline Drawing | 0 | 2017-10-13 | 0 | APPROVED | 2017-10-13 | Close
936 | GRT-DS-IP-DT-170330 | GRT-QA00-P0H-040007 | [HRSG]_Welders List for HRSG Heat Exchanger | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
937 | GRT-DS-IP-DT-170330 | GRT-QA00-P0H-040008 | [HRSG]_WPS&PQR for HRSG Heat Exchanger | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
938 | GRT-DS-IP-DT-170330 | GRT-QA00-P0H-040009 | [HRSG]_Welders List for HRSG HP Drum | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
939 | GRT-DS-IP-DT-170330 | GRT-QA00-P0H-040010 | [HRSG]_WPS&PQR for HRSG HP Drum | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
940 | GRT-DS-IP-DT-170330 | GRT-QA00-P0H-040011 | [HRSG]_Welders List for HRSG LP Drum | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
941 | GRT-DS-IP-DT-170330 | GRT-QA00-P0H-040012 | [HRSG]_WPS&PQR for HRSG LP Drum | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
942 | GRT-DS-IP-DT-170330 | GRT-QA00-P0H-040013 | [HRSG]_NDE Procedure for HRSG Piping | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
943 | GRT-DS-IP-DT-170330 | GRT-QA00-P0H-040014 | [HRSG]_Heat Treatment Procedure for HRSG Piping | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
944 | GRT-DS-IP-DT-170330 | GRT-QA00-P0H-040015 | [HRSG]_Welders List for HRSG Piping | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
945 | GRT-DS-IP-DT-170330 | GRT-QA00-P0H-040016 | [HRSG]_WPS&PQR for HRSG Piping | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
981 | GRT-DS-IP-DT-170339 | GRT-MA02-P0ZEN-161006 | [INC_Interface]_3rd Party Data-link Interface Concept Diagram | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
982 | GRT-DS-IP-DT-170340 | GRT-DF04-P0ZEN-144512 | [Piping General]_Stress Analysis Report for HP steam system | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
983 | GRT-DS-IP-DT-170341 | GRT-DF04-P0ZEN-144513 | [Piping General]_Stress Analysis Report for LP steam system | 0 | 2017-10-26 | 175 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
984 | GRT-DS-IP-DT-170342 | GRT-DF04-P0ZEN-144514 | [Piping General]_Stress Analysis Report for Aux.steam system | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
985 | GRT-DS-IP-DT-170343 | GRT-DF04-P0ZEN-144515 | [Piping General]_Stress Analysis Report for Feedwater system | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1014 | GRT-DS-IP-DT-170358 | GRT-YL22-P0PGB-113109 | [CCWP ]_NAMEPLATE DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1015 | GRT-DS-IP-DT-170358 | GRT-YL22-P0PCC-113009 | [Aux. Cooling Water Pump]_NAMEPLATE DRAWING FOR AUXILIARY COOLING WATER PUMP MOTOR | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1017 | GRT-DS-IP-DT-170360 | GRT-XG02-P0QJA-110010 | [N2 Gas system]_P&I DIAGRAM | 1 | 2017-10-26 | 7 | APPROVED AS NOTED | 2017-11-02 | Close
1018 | GRT-DS-IP-DT-170360 | GRT-XG02-P0LCM-110005 | [Steam drain system]_P&ID DIAGRAM | 1 | 2017-10-26 | 7 | APPROVED AS NOTED | 2017-11-02 | Close
1019 | GRT-DS-IP-DT-170360 | GRT-XG02-P0LBG-110004 | [AUX Steam System]_P&I DIAGRAM | 1 | 2017-10-26 | 7 | APPROVED AS NOTED | 2017-11-02 | Close
1020 | GRT-DS-IP-DT-170360 | GRT-XG02-P0LBA-110003 | [HP & LP steam system]_P&I DIAGRAM | 1 | 2017-10-26 | 7 | APPROVED AS NOTED | 2017-11-02 | Close
1035 | GRT-DS-IP-DT-170365 | GRT-YV02-P0MAJ-460202 | Wiring Diargam For Water Box Vacuum Pump | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1036 | GRT-DS-IP-DT-170365 | GRT-YB10-P0MAJ-460103 | Terminal Box For Condenser Vacuum Pump | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1037 | GRT-DS-IP-DT-170365 | GRT-YB10-P0MAJ-460203 | Terminal Box For Water Box Vacuum Pump | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1038 | GRT-DS-IP-DT-170365 | GRT-YV02-P0MAJ-460102 | Wiring Diargam For Condenser Vacuum Pump | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1039 | GRT-DS-IP-DT-170366 | GRT-XG02-P0LC-110007 | [Condensate system]_P&I DIAGRAM | 1 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1040 | GRT-DS-IP-DT-170366 | GRT-XG02-P0LA-110006 | [Feedwater system]_P&I DIAGRAM | 1 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1046 | GRT-DS-IP-DT-170368 | GRT-YF00-P0ZEN-161402 | [INC_Start&Shutdown Diagram]_Plant Start-up & Shutdown Sequence Diagram - Symbol & Legend | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1047 | GRT-DS-IP-DT-170369 | GRT-YF00-P0ZEN-161405 | [INC_Start&Shutdown Diagram]_Plant Start-up & Shutdown Sequence Diagram for Hot Start-up | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1048 | GRT-DS-IP-DT-170369 | GRT-YF00-P0ZEN-161404 | [INC_Start&Shutdown Diagram]_Plant Start-up & Shutdown Sequence Diagram for Warm Start-up | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1049 | GRT-DS-IP-DT-170369 | GRT-YF00-P0ZEN-161403 | [INC_Start&Shutdown Diagram]_Plant Start-up & Shutdown Sequence Diagram for Cold Start-up | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1052 | GRT-DS-IP-DT-170371 | GRT-YD00-P0MA-200024 | [STG]_Generator Specification | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1053 | GRT-DS-IP-DT-170374 | GRT-YF00-P0LA-161305 | [Feedwater system_I&C_Loop]_Control Loop Diagram for BOP | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1054 | GRT-DS-IP-DT-170374 | GRT-YF00-P0LA-161205 | [Feedwater system_I&C_Logic]_Control Logic Diagram for BOP | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1055 | GRT-DS-IP-DT-170375 | GRT-XN00-P0MA-200011 | [STG]_List of valves | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1056 | GRT-DS-IP-DT-170376 | GRT-YD00-P0LCB-121001 | [Condensate Extraction Pump]_GENERAL ARRANGEMENT DRAWING | 0 | 2017-10-26 | 175 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1057 | GRT-DS-IP-DT-170377 | GRT-QA00-P0H-040005 | [HRSG]_NDE Procedure for HRSG Heat Exchanger | 1 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1058 | GRT-DS-IP-DT-170377 | GRT-QA00-P0H-040004 | [HRSG]_Heat Treatment Procedure for HRSG Heat Exchanger | 1 | 2017-10-26 | 7 | APPROVED AS NOTED | 2017-11-02 | Close
1064 | GRT-DS-IP-DT-170379 | GRT-YT01-P0SM-123002 | [Crane & Hoist(DHI)]_HOIST_DATA SHEETS FOR HOISTS | 0 | 2017-10-26 | 7 | APPROVED AS NOTED | 2017-11-02 | Close
1065 | GRT-DS-IP-DT-170379 | GRT-YD00-P0SM-123001 | [Crane & Hoist(DHI)]_HOIST_GA DRAWING FOR HOISTS | 0 | 2017-10-26 | 7 | APPROVED AS NOTED | 2017-11-02 | Close
1077 | GRT-DS-IP-DT-170383 | GRT-YT01-P0ZEN-113401 | [MOV (Butterfly)(DHI)]_VALVE LIST & DATA SHEET FOR MOV (BUTTERFLY) | 0 | 2017-10-26 | 7 | APPROVED AS NOTED | 2017-11-02 | Close
1078 | GRT-DS-IP-DT-170383 | GRT-YK10-P0ZEN-113400 | [MOV (Butterfly)(DHI)]_OUTLINE DRAWING FOR MOV (BUTTERFLY) | 0 | 2017-10-26 | 7 | APPROVED AS NOTED | 2017-11-02 | Close
1082 | GRT-DS-IP-DT-170387 | GRT-YD00-P1H-300039 | [HRSG]_SPEC. & DRAWING FOR SAFETY & RELIEF VALVE | 0 | 2017-10-26 | 7 | APPROVED AS NOTED | 2017-11-02 | Close
1083 | GRT-DS-IP-DT-170387 | GRT-UE00-P1H-300006 | [HRSG]_GENERAL ARRANGEMENT | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1085 | GRT-DS-IP-DT-170390 | GRT-YD00-P0LCM-430010 | Outline Drawing for Atmospheric Flash Tank | 0 | 2017-10-26 | 7 | APPROVED AS NOTED | 2017-11-02 | Close
1086 | GRT-DS-IP-DT-170391 | GRT-YD00-P0PGB-430020 | Outline Drawing for CCW Chemical Additive Tank | 0 | 2017-10-26 | 7 | APPROVED AS NOTED | 2017-11-02 | Close
1087 | GRT-DS-IP-DT-170392 | GRT-YD00-P0PGB-430030 | Outline Drawing for CCW Expansion Head Tank | 0 | 2017-10-26 | 7 | APPROVED AS NOTED | 2017-11-02 | Close
1088 | GRT-DS-IP-DT-170394 | GRT-YF00-P0SCA-120021 | [Air Compressor]_CONTROL LOGIC & LOOP DIAGRAM | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1089 | GRT-DS-IP-DT-170394 | GRT-XF00-P0SCA-120027 | [Air Compressor]_NAME PLATE DRAWING | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1090 | GRT-DS-IP-DT-170394 | GRT-XN00-P0SCA-120028 | [Air Compressor]_VALVE LIST | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1091 | GRT-DS-IP-DT-170394 | GRT-XW01-P0SCA-120029 | [Air Compressor]_VALVE SPECIFICATION | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1092 | GRT-DS-IP-DT-170394 | GRT-YD05-P0SCA-120018 | [Air Compressor]_PLC HMI GRAPHICS | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1093 | GRT-DS-IP-DT-170394 | GRT-YV02-P0SCA-120022 | [Air Compressor]_I&C WIRING DIAGRAMS | 0 | 2017-10-26 | 7 | APPROVED AS NOTED | 2017-11-02 | Close
1094 | GRT-DS-IP-DT-170394 | GRT-YU03-P0SCA-120016 | [Air Compressor]_ELECTRICAL SCHEMATIC DIAGRAM | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1095 | GRT-DS-IP-DT-170394 | GRT-YV02-P0SCA-120015 | [Air Compressor]_ELECTRICAL WIRING DIAGRAMS | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1096 | GRT-DS-IP-DT-170395 | GRT-YL00-P0MAJ-460107 | Instrument list For Condenser Vacuum Pump | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1097 | GRT-DS-IP-DT-170395 | GRT-YL00-P0MAJ-460207 | Instrument list For Water Box Vacuum Pump | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1098 | GRT-DS-IP-DT-170397 | GRT-YD00-P0MAG-410103 | Cathodic Protection System for Condenser_The Location of Anode (Inlet Waterbox) | 0 | 2017-10-26 | 7 | APPROVED AS NOTED | 2017-11-02 | Close
1099 | GRT-DS-IP-DT-170397 | GRT-YT10-P0MAG-410101 | Cathodic Protection System for Condenser_Calculation Sheet | 0 | 2017-10-26 | 7 | APPROVED AS NOTED | 2017-11-02 | Close
1100 | GRT-DS-IP-DT-170397 | GRT-YD00-P0MAG-410104 | Cathodic Protection System for Condenser_The Location of Anode (Outlet Waterbox) | 0 | 2017-10-26 | 7 | APPROVED AS NOTED | 2017-11-02 | Close
1101 | GRT-DS-IP-DT-170398 | GRT-CV03-P0ZEN-161116 | [DCS]_Functional Design Specification for Safety Related System | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1103 | GRT-DS-IP-DT-170400 | GRT-XB00-P0MA-200013 | [STG]_Allowable loadings and displacements | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1110 | GRT-DS-IP-DT-170402 | GRT-CV03-P0ZEN-161117 | [DCS]_Functional Design Specification for Performance Monitoring System | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1113 | GRT-DS-IP-DT-170405 | GRT-YT02-P0LAC-122506 | [LP Feed Water Pump]_LIST AND DATA SHEET FOR INSTRUMENT | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1114 | GRT-DS-IP-DT-170405 | GRT-YT02-P0LAC-122006 | [HP Feed Water Pump]_LIST AND DATA SHEET FOR INSTRUMENT | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1118 | GRT-DS-IP-DT-170404 | GRT-YD04-P1H-300042 | [HRSG]_CABLE TRAY & RACEWAY LAYOUT DIAGRAM | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1119 | GRT-DS-IP-DT-170406 | GRT-YL21-P0MA-200046 | [STG]_Trips & Alarms settings | 0 | 2017-10-26 | 7 | APPROVED AS NOTED | 2017-11-02 | Close
1120 | GRT-DS-IP-DT-170406 | GRT-YF00-P0MA-200044 | [STG]_Logic diagrams for control of functional groups | 0 | 2017-10-26 | 7 | APPROVED AS NOTED | 2017-11-02 | Close
1127 | GRT-DS-IP-DT-170411 | GRT-YL22-P0LCB-121012 | [Condensate Extraction Pump]_NAME PLATE DRAWING | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1128 | GRT-DS-IP-DT-170411 | GRT-YL00-P0LCB-121010 | [Condensate Extraction Pump]_INSTRUMENT LIST | 0 | 2017-10-26 | 7 | APPROVED | 2017-11-02 | Close
1027 | GRT-DS-IP-DT-170362 | GRT-YK08-P0PBB-440102 | Debris Filter_Outline Drawing | C | 2017-10-30 | 14 | DEEMED APPROVAL | 2017-11-13 | Close
1028 | GRT-DS-IP-DT-170362 | GRT-YK08-P0PAH-440003 | Condenser Tube Cleaning System_Outline Drawing for Ball Recirculation unit | C | 2017-10-30 | 14 | DEEMED APPROVAL | 2017-11-13 | Close
1029 | GRT-DS-IP-DT-170362 | GRT-XG02-P0PAH-440051 | CCW HEX Tube Cleaning System_P & I Diagram | C | 2017-10-30 | 14 | DEEMED APPROVAL | 2017-11-13 | Close
1030 | GRT-DS-IP-DT-170362 | GRT-YK08-P0PAH-440053 | CCW HEX Tube Cleaning System_Outline Drawing for Ball Recirculation unit | C | 2017-10-30 | 14 | DEEMED APPROVAL | 2017-11-13 | Close
1031 | GRT-DS-IP-DT-170362 | GRT-YK08-P0PAH-440052 | CCW HEX Tube Cleaning System_Outline Drawing | C | 2017-10-30 | 14 | DEEMED APPROVAL | 2017-11-13 | Close
1032 | GRT-DS-IP-DT-170363 | GRT-XN00-P0LDB-130043 | [Condensate Filter System]_VALVE LIST | B | 2017-10-30 | 28 | DEEMED APPROVAL | 2017-11-27 | Close
1033 | GRT-DS-IP-DT-170363 | GRT-YT01-P0LDB-130050 | [Condensate Filter System]_VALVE DATA SHEET | B | 2017-10-30 | 28 | DEEMED APPROVAL | 2017-11-27 | Close
1034 | GRT-DS-IP-DT-170364 | GRT-YF02-P0SCA-120026 | [Air Compressor]_PLC PANEL DRAWING | B | 2017-10-30 | 3 | A | 2017-11-02 | Close
1041 | GRT-DS-IP-DT-170367 | GRT-QA00-P0ZEN-141005 | Welder consumable control procedure for BOP Piping | A | 2017-10-30 | 53 | DEEMED APPROVAL | 2017-12-22 | Close
1042 | GRT-DS-IP-DT-170367 | GRT-QA00-P0ZEN-141003 | Welder qualificatoin list for BOP Piping | A | 2017-10-30 | 53 | DEEMED APPROVAL | 2017-12-22 | Close
1043 | GRT-DS-IP-DT-170367 | GRT-DP00-P0ZEN-141004 | Repair welding procedure for BOP Piping | A | 2017-10-30 | 53 | DEEMED APPROVAL | 2017-12-22 | Close
1044 | GRT-DS-IP-DT-170367 | GRT-DP00-P0ZEN-141002 | Heat treatment procedure for BOP Piping | A | 2017-10-30 | 53 | DEEMED APPROVAL | 2017-12-22 | Close
1045 | GRT-DS-IP-DT-170367 | GRT-DP00-P0ZEN-141001 | WPS&PQR for BOP Piping | A | 2017-10-30 | 53 | DEEMED APPROVAL | 2017-12-22 | Close
1050 | GRT-DS-IP-DT-170370 | GRT-XB00-P0MA-200008 | [STG]_Loads plan - Levels | C | 2017-10-30 | 3 | I | 2017-11-02 | Close
1051 | GRT-DS-IP-DT-170372 | GRT-CV03-P0ZEN-163703 | [Field Instruments(DHI)]_Technical Specification & Datasheet for Flow Element - BOP | A | 2017-10-30 | 3 | A | 2017-11-02 | Close
1059 | GRT-DS-IP-DT-170373 | GRT-QM03-P0ZEN-141009 | LIQUID PENETRANT EXAMINATION PROCEDURE | A | 2017-10-30 | 28 | DEEMED APPROVAL | 2017-11-27 | Close
1060 | GRT-DS-IP-DT-170373 | GRT-QM03-P0ZEN-141008 | MAGNETIC PARTICLE EXAMINATION PROCEDURE | A | 2017-10-30 | 28 | DEEMED APPROVAL | 2017-11-27 | Close
1061 | GRT-DS-IP-DT-170373 | GRT-QM03-P0ZEN-141007 | ULTRASONIC EXAMINATION PROCEDURE | A | 2017-10-30 | 28 | DEEMED APPROVAL | 2017-11-27 | Close
1062 | GRT-DS-IP-DT-170373 | GRT-QM03-P0ZEN-141006 | RADIOGRAPHIC EXAMINATION PROCEDURE | A | 2017-10-30 | 28 | DEEMED APPROVAL | 2017-11-27 | Close
1063 | GRT-DS-IP-DT-170378 | GRT-YF00-P0ZEN-161406 | [INC_Start&Shutdown Diagram]_Plant Start-up & Shutdown Sequence Diagram for Shutdown | A | 2017-10-30 | 3 | B | 2017-11-02 | Close
1066 | GRT-DS-IP-DT-170380 | GRT-DF04-P0MA-200018 | [STG]_Stress analysis of piping | A | 2017-10-30 | 94 | DEEMED APPROVAL | 2018-02-01 | Close
1067 | GRT-DS-IP-DT-170380 | GRT-CA03-P0MA-200004 | [STG]_Steel structures | A | 2017-10-30 | 3 | A | 2017-11-02 | Close
1068 | GRT-DS-IP-DT-170381 | GRT-YK09-P0MA-200030 | [STG]_DC motor starter | A | 2017-10-30 | 94 | DEEMED APPROVAL | 2018-02-01 | Close
1069 | GRT-DS-IP-DT-170381 | GRT-YK09-P0MA-200029 | [STG]_Frequency converter for turning gear | A | 2017-10-30 | 94 | DEEMED APPROVAL | 2018-02-01 | Close
1070 | GRT-DS-IP-DT-170381 | GRT-YK09-P0MA-200028 | [STG]_Measuring and Synchronization | A | 2017-10-30 | 81 | DEEMED APPROVAL | 2018-01-19 | Close
1071 | GRT-DS-IP-DT-170381 | GRT-YK09-P0MA-200027 | [STG]_Electrical Protections | A | 2017-10-30 | 81 | DEEMED APPROVAL | 2018-01-19 | Close
1072 | GRT-DS-IP-DT-170381 | GRT-YK09-P0MA-200026 | [STG]_Line and Neutral Cubicles | A | 2017-10-30 | 81 | DEEMED APPROVAL | 2018-01-19 | Close
1073 | GRT-DS-IP-DT-170381 | GRT-YK09-P0MA-200025 | [STG]_Excitation system | A | 2017-10-30 | 84 | DEEMED APPROVAL | 2018-01-22 | Close
1074 | GRT-DS-IP-DT-170382 | GRT-YT01-P0LB-111110 | [Bypass Valve & PRDS]_Data Sheet for HPU | B | 2017-10-30 | 28 | DEEMED APPROVAL | 2017-11-27 | Close
1075 | GRT-DS-IP-DT-170382 | GRT-XS01-P0LB-111105 | [Bypass Valve & PRDS]_Operating Description for HPU system for Bypass System | B | 2017-10-30 | 28 | DEEMED APPROVAL | 2017-11-27 | Close
1076 | GRT-DS-IP-DT-170382 | GRT-XL35-P0LB-111109 | [Bypass Valve & PRDS]_Instrument List & Database Sheet | B | 2017-10-30 | 3 | A | 2017-11-02 | Close
1079 | GRT-DS-IP-DT-170385 | GRT-YS18-P0LB-111107 | [Bypass Valve & PRDS]_P&ID for HPU | B | 2017-10-30 | 3 | A | 2017-11-02 | Close
1080 | GRT-DS-IP-DT-170386 | GRT-YT01-P1H-300068 | [HRSG]_DIVERTER & GUILLOTINE DAMPER DOCUMENT PACKAGE | B | 2017-10-30 | 21 | DEEMED APPROVAL | 2017-11-20 | Close
1081 | GRT-DS-IP-DT-170386 | GRT-YD00-P1H-300035 | [HRSG]_SPEC. & DRAWING FOR STEAM DRUM | B | 2017-10-30 | 14 | DEEMED APPROVAL | 2017-11-13 | Close
1084 | GRT-DS-IP-DT-170388 | GRT-XS00-P0MAJ-460109 | Vacuum Pump System Description & Control Philosophy | A | 2017-10-30 | 3 | B | 2017-11-02 | Close
1102 | GRT-DS-IP-DT-170399 | GRT-YT01-P0LCB-121007 | [Condensate Extraction Pump]_SUCTION STRAINER SPECIFICATION | C | 2017-10-30 | 28 | DEEMED APPROVAL | 2017-11-27 | Close
1104 | GRT-DS-IP-DT-170401 | GRT-YL00-P0QU-130028 | [Sampling System]_INSTRUMENT LIST | B | 2017-10-30 | 3 | APPROVED | 2017-11-02 | Close
1105 | GRT-DS-IP-DT-170401 | GRT-YF02-P0QU-130027 | [Sampling System]_CONTROL CONFIGURATION DIAGRAM | B | 2017-10-30 | 28 | DEEMED APPROVAL | 2017-11-27 | Close
1106 | GRT-DS-IP-DT-170401 | GRT-XS00-P0QU-130026 | [Sampling System]_SYSTEM DESCRIPTION | B | 2017-10-30 | 28 | DEEMED APPROVAL | 2017-11-27 | Close
1107 | GRT-DS-IP-DT-170401 | GRT-XN00-P0QU-130029 | [Sampling System]_VALVE LIST | B | 2017-10-30 | 3 | DEEMED APPROVAL | 2017-11-02 | Close
1108 | GRT-DS-IP-DT-170401 | GRT-XG02-P0QU-130024 | [Sampling System]_P&ID | B | 2017-10-30 | 28 | DEEMED APPROVAL | 2017-11-27 | Close
1109 | GRT-DS-IP-DT-170401 | GRT-XA00-P0QU-130025 | [Sampling System]_GENERAL ARRANGEMENT DRAWING | B | 2017-10-30 | 28 | DEEMED APPROVAL | 2017-11-27 | Close
1111 | GRT-DS-IP-DT-170403 | GRT-YT01-P0QU-130031 | [Sampling System]_INSTRUMENT DATA SHEET | B | 2017-10-30 | 3 | A | 2017-11-02 | Close
1112 | GRT-DS-IP-DT-170403 | GRT-YT01-P0QU-130030 | [Sampling System]_TECHNICAL DATASHEET | B | 2017-10-30 | 28 | DEEMED APPROVAL | 2017-11-27 | Close
1115 | GRT-DS-IP-DT-170407 | GRT-YK10-P0LDB-130045 | [Condensate Filter System]_EQUIPMENT ASSEMBLY DRAWING | B | 2017-10-30 | 14 | DEEMED APPROVAL | 2017-11-13 | Close
1116 | GRT-DS-IP-DT-170407 | GRT-XH01-P0LDB-130046 | [Condensate Filter System]_PIPING ARRANGEMENT DRAWING | B | 2017-10-30 | 14 | DEEMED APPROVAL | 2017-11-13 | Close
1117 | GRT-DS-IP-DT-170384 | GRT-YD08-P0UMA-164311 | [Steam Turbine Building_INC_ILD]_BOP_Instrument Location Drawing | B | 2017-10-30 | 28 | DEEMED APPROVAL | 2017-11-27 | Close
1121 | GRT-DS-IP-DT-170408 | GRT-YL01-P0ZEN-161102 | [INC_DCS_IO]_3rd Party Data-link Interface Signal Database | A | 2017-10-30 | 3 | A | 2017-11-02 | Close
1122 | GRT-DS-IP-DT-170409 | GRT-YR05-P0ZEN-161135 | [DCS]_Outline & Detail Drawing for Relay Cabinet | 0 | 2017-10-30 | 3 | APPROVED | 2017-11-02 | Close
1123 | GRT-DS-IP-DT-170409 | GRT-YR05-P0ZEN-161133 | [DCS]_Outline & Detail Drawing for Power Distribution Cabinet | 0 | 2017-10-30 | 3 | APPROVED | 2017-11-02 | Close
1124 | GRT-DS-IP-DT-170409 | GRT-YD06-P0ZEN-161115 | [DCS]_Equipment Power Distribution Diagram | 0 | 2017-10-30 | 3 | APPROVED | 2017-11-02 | Close
1125 | GRT-DS-IP-DT-170410 | GRT-YR05-P0ZEN-161136 | [DCS]_Outline & Detail Drawing for Safety Related System Panel | B | 2017-10-30 | 3 | A | 2017-11-02 | Close
1126 | GRT-DS-IP-DT-170410 | GRT-YR05-P0ZEN-161132 | [DCS]_Outline & Detail Drawing for LAN Cabinet | B | 2017-10-30 | 3 | A | 2017-11-02 | Close
1129 | GRT-DS-IP-DT-170412 | GRT-YK00-P0LCB-121011 | [Condensate Extraction Pump]_INSTRUMENTATION HOOK - UP DRAWING | B | 2017-10-30 | 3 | I | 2017-11-02 | Close
1130 | GRT-DS-IP-DT-170413 | GRT-YT10-P0PGB-430130 | Strength Calculation for CCW Expansion Head Tank | A | 2017-11-01 | 1 | A | 2017-11-02 | Close
1131 | GRT-DS-IP-DT-170413 | GRT-YT10-P0PGB-430120 | Strength Calculation for CCW Chemical Additive Tank | A | 2017-11-01 | 1 | B | 2017-11-02 | Close
1132 | GRT-DS-IP-DT-170413 | GRT-YT10-P0LCM-430110 | Strength Calculation for Atmospheric Flash Tank | A | 2017-11-01 | 1 | A | 2017-11-02 | Close
1133 | GRT-DS-IP-DT-170414 | GRT-YK09-P0MA-200033 | [STG]_Electrical system description | 0 | 2017-11-01 | 1 | APPROVED AS NOTED | 2017-11-02 | Close
1134 | GRT-DS-IP-DT-170415 | GRT-YU03-P0MA-200039 | [STG]_Control system architecture | B | 2017-11-01 | 47 | B | 2017-12-18 | Close
1135 | GRT-DS-IP-DT-170416 | GRT-YT10-P0PGB-400050 | Thermal Calculation for CCW Heat Exchanger | A | 2017-11-01 | 22 | C | 2017-11-23 | Close
1136 | GRT-DS-IP-DT-170417 | GRT-YT01-P0LAC-122505 | [LP Feed Water Pump]_DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | 0 | 2017-11-01 | 169 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1137 | GRT-DS-IP-DT-170417 | GRT-YT01-P0LAC-122005 | [HP Feed Water Pump]_DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | 0 | 2017-11-01 | 169 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1138 | GRT-DS-IP-DT-170417 | GRT-YK10-P0LAC-122504 | [LP Feed Water Pump]_SECTIONAL DRAWING FOR PUMP | 0 | 2017-11-01 | 169 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1139 | GRT-DS-IP-DT-170417 | GRT-YD00-P0LAC-122502 | [LP Feed Water Pump]_GENERAL ARRANGEMENT DRAWING | 0 | 2017-11-01 | 169 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1140 | GRT-DS-IP-DT-170417 | GRT-YD00-P0LAC-122002 | [HP Feed Water Pump]_GENERAL ARRANGEMENT DRAWING | 0 | 2017-11-01 | 169 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1141 | GRT-DS-IP-DT-170417 | GRT-XG02-P0LAC-122501 | [LP Feed Water Pump]_P&I DIAGRAM | 0 | 2017-11-01 | 169 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1142 | GRT-DS-IP-DT-170417 | GRT-XG02-P0LAC-122001 | [HP Feed Water Pump]_P&I DIAGRAM | 0 | 2017-11-01 | 169 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1143 | GRT-DS-IP-DT-170418 | GRT-YT01-P0ZEN-113301 | [MOV (Gate & Globe)(DHI)]_VALVE LIST & DATA SHEET FOR MOV (G&G) | A | 2017-11-01 | 22 | A | 2017-11-23 | Close
1144 | GRT-DS-IP-DT-170418 | GRT-YK10-P0ZEN-113300 | [MOV (Gate & Globe)(DHI)]_OUTLINE DRAWING FOR MOV (G&G) | A | 2017-11-01 | 22 | A | 2017-11-23 | Close
1145 | GRT-DS-IP-DT-170419 | GRT-YD00-P0MA-200017 | [STG]_Layout - piping routing - | 0 | 2017-11-01 | 1 | APPROVED | 2017-11-02 | Close
1146 | GRT-DS-IP-DT-170419 | GRT-XV00-P0MA-200012 | [STG]_List of equipments | 0 | 2017-11-01 | 1 | APPROVED | 2017-11-02 | Close
1147 | GRT-DS-IP-DT-170420 | GRT-YT01-P1H-300061 | [HRSG]_DESH. DATASHEET & DRAWINGS | 0 | 2017-11-01 | 169 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1148 | GRT-DS-IP-DT-170420 | GRT-YT01-P1H-300060 | [HRSG]_CV DATASHEET & DRAWINGS | 0 | 2017-11-01 | 169 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1149 | GRT-DS-IP-DT-170420 | GRT-YT01-P1H-300059 | [HRSG]_MOV DATASHEET & DRAWINGS | 0 | 2017-11-01 | 169 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1150 | GRT-DS-IP-DT-170420 | GRT-YK01-P1H-300048 | [HRSG]_INSTRUMENT INSTALLATION DETAIL DRAWINGS | 0 | 2017-11-01 | 160 | DEEMED APPROVAL | 2018-04-10 | Close
1151 | GRT-DS-IP-DT-170420 | GRT-YD00-P1H-300041 | [HRSG]_SPEC. & DRAWING FOR SILENCER | 0 | 2017-11-01 | 169 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1152 | GRT-DS-IP-DT-170420 | GRT-YD00-P1H-300040 | [HRSG]_SPEC. & DRAWING FOR STACK DAMPER | 0 | 2017-11-01 | 169 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1153 | GRT-DS-IP-DT-170420 | GRT-YD00-P1H-300034 | [HRSG]_PRESSURE PART ARRANGEMENT | 0 | 2017-11-01 | 169 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1154 | GRT-DS-IP-DT-170420 | GRT-VN03-P1H-300013 | [HRSG]_ARRANGEMENT FOR PLATFORM STRUCTURE | 0 | 2017-11-01 | 14 | DEEMED APPROVAL | 2017-11-15 | Close
1155 | GRT-DS-IP-DT-170420 | GRT-UE00-P1H-300009 | [HRSG]_ARRANGEMENT OF MAIN STACK& FIELD ERECTION | 0 | 2017-11-01 | 169 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1156 | GRT-DS-IP-DT-170422 | GRT-YD00-P0PGB-400040 | Outline Drawing for CCW Heat Exchanger | 0 | 2017-11-01 | 1 | APPROVED AS NOTED | 2017-11-02 | Close
1157 | GRT-DS-IP-DT-170421 | GRT-YL00-P0QC-130007 | [Chemical Dosing System]_INSTRUMENT LIST | 0 | 2017-11-01 | 2 | APPROVED | 2017-11-03 | Close
1158 | GRT-DS-IP-DT-170421 | GRT-CC07-P0QC-130004 | [Chemical Dosing System]_CALCULATION SHEET | 0 | 2017-11-01 | 2 | APPROVED AS NOTED | 2017-11-03 | Close
1159 | GRT-DS-IP-DT-170421 | GRT-XS00-P0QC-130003 | [Chemical Dosing System]_SYSTEM DESCRIPTION | 0 | 2017-11-01 | 2 | APPROVED AS NOTED | 2017-11-03 | Close
1160 | GRT-DS-IP-DT-170421 | GRT-XN00-P0QC-130008 | [Chemical Dosing System]_VALVE LIST | 0 | 2017-11-01 | 2 | APPROVED | 2017-11-03 | Close
1161 | GRT-DS-IP-DT-170421 | GRT-XG02-P0QC-130001 | [Chemical Dosing System]_P&ID | 0 | 2017-11-01 | 2 | APPROVED AS NOTED | 2017-11-03 | Close
1162 | GRT-DS-IP-DT-170421 | GRT-XA00-P0QC-130002 | [Chemical Dosing System]_GENERAL ARRANGEMENT DRAWING | 0 | 2017-11-01 | 2 | APPROVED AS NOTED | 2017-11-03 | Close
1163 | GRT-DS-IP-DT-170421 | GRT-YD00-P0QC-130005 | [Chemical Dosing System]_CONTROL PANEL ARRANGEMENT DRAWING | 0 | 2017-11-01 | 2 | APPROVED | 2017-11-03 | Close
1164 | GRT-DS-IP-DT-170423 | GRT-YR05-P0ZEN-161131 | [DCS]_Outline & Detail Drawing for Console desk & Computer desk & Printer desk | B | 2017-11-01 | 1 | A | 2017-11-02 | Close
1165 | GRT-DS-IP-DT-170423 | GRT-YR05-P0ZEN-161134 | [DCS]_Outline & Detail Drawing for System & Marshalling Cabinet | B | 2017-11-01 | 1 | A | 2017-11-02 | Close
1166 | GRT-DS-IP-DT-170423 | GRT-CV03-P0ZEN-161112 | [DCS]_Functional Design Specification for Graphic | B | 2017-11-01 | 1 | A | 2017-11-02 | Close
1167 | GRT-DS-IP-DT-170424 | GRT-YF02-P0QC-130006 | [Chemical Dosing System]_CONTROL CONFIGURATION DIAGRAM | B | 2017-11-01 | 47 | B | 2017-12-18 | Close
1168 | GRT-DS-IP-DT-170425 | GRT-MA02-P0ZEN-161121 | [DCS]_LAN Configuration Diagram | 0 | 2017-11-01 | 47 | A | 2017-12-18 | Close
1169 | GRT-DS-IP-DT-170426 | GRT-YD00-P0PCC-113007 | [Aux. Cooling Water Pump]_MAIN TERMINAL BOX DRAWING FOR AUXILIARY COOLING WATER PUMP MOTOR | 0 | 2017-11-01 | 1 | APPROVED | 2017-11-02 | Close
1170 | GRT-DS-IP-DT-170427 | GRT-CV03-P0ZEN-163704 | [Control Valves(DHI)]_Technical Specification & Datasheet for Control Valve - BOP | 0 | 2017-11-01 | 1 | APPROVED | 2017-11-02 | Close
1171 | GRT-DS-IP-DT-170429 | GRT-YT10-P0PGB-400060 | Strength Calculation for CCW Heat Exchanger | A | 2017-11-01 | 51 | DEEMED APPROVAL | 2017-12-22 | Close
1172 | GRT-DS-IP-DT-170433 | GRT-CN00-P0ZEN-110100 | [Plant Overall]_OPERATION PHILOSOPHY OF OVERALL PLANT | 0 | 2017-11-01 | 169 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1173 | GRT-DS-IP-DT-170434 | GRT-YL00-P0LDB-130042 | [Condensate Filter System]_INSTRUMENT LIST | 0 | 2017-11-01 | 169 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1174 | GRT-DS-IP-DT-170434 | GRT-XS00-P0LDB-130038 | [Condensate Filter System]_SYSTEM DESCRIPTION | 0 | 2017-11-01 | 169 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1175 | GRT-DS-IP-DT-170434 | GRT-XG02-P0LDB-130036 | [Condensate Filter System]_P&ID | 0 | 2017-11-01 | 127 | DEEMED APPROVAL | 2018-03-08 | Close
1176 | GRT-DS-IP-DT-170434 | GRT-CC07-P0LDB-130039 | [Condensate Filter System]_CALCULATION SHEET | 0 | 2017-11-01 | 169 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1177 | GRT-DS-IP-DT-170393 | GRT-XK00-P0MAJ-460217 | Coupling Drawing For Water Box Vacuum Pump | 0 | 2017-11-01 | 2 | APPROVED | 2017-11-03 | Close
1178 | GRT-DS-IP-DT-170393 | GRT-XK00-P0MAJ-460216 | Name Plate Drawing For Water Box Vacuum Pump | 0 | 2017-11-01 | 2 | APPROVED | 2017-11-03 | Close
1179 | GRT-DS-IP-DT-170393 | GRT-XK00-P0MAJ-460214 | Baseframe Drawing For Water Box Vacuum Pump | 0 | 2017-11-01 | 2 | APPROVED | 2017-11-03 | Close
1180 | GRT-DS-IP-DT-170393 | GRT-XK00-P0MAJ-460213 | Tank Drawing For Water Box Vacuum Pump | 0 | 2017-11-01 | 2 | APPROVED | 2017-11-03 | Close
1181 | GRT-DS-IP-DT-170393 | GRT-XK00-P0MAJ-460117 | Coupling Drawing For Condenser Vacuum Pump | 0 | 2017-11-01 | 2 | APPROVED | 2017-11-03 | Close
1182 | GRT-DS-IP-DT-170393 | GRT-XK00-P0MAJ-460116 | Name Plate Drawing For Condenser Vacuum Pump | 0 | 2017-11-01 | 2 | APPROVED | 2017-11-03 | Close
1183 | GRT-DS-IP-DT-170393 | GRT-XK00-P0MAJ-460114 | Baseframe Drawing For Condenser Vacuum Pump | 0 | 2017-11-01 | 2 | APPROVED | 2017-11-03 | Close
1184 | GRT-DS-IP-DT-170393 | GRT-XK00-P0MAJ-460113 | Tank Drawing For Condenser Vacuum Pump | 0 | 2017-11-01 | 2 | APPROVED | 2017-11-03 | Close
1185 | GRT-DS-IP-DT-170396 | GRT-YT01-P0MAJ-460215 | Recirculation Pump Data Sheet and Characteristic Curves and Drawing For WBVP | 0 | 2017-11-01 | 2 | APPROVED | 2017-11-03 | Close
1186 | GRT-DS-IP-DT-170396 | GRT-YT01-P0MAJ-460205 | Motor Data sheet and Characteristic Curves and Drawing For WBVP | 0 | 2017-11-01 | 14 | DEEMED APPROVAL | 2017-11-15 | Close
1187 | GRT-DS-IP-DT-170396 | GRT-YT01-P0MAJ-460115 | Recirculation Pump Data Sheet and Characteristic Curves and Drawing For CVP | 0 | 2017-11-01 | 2 | APPROVED | 2017-11-03 | Close
1188 | GRT-DS-IP-DT-170396 | GRT-YT01-P0MAJ-460105 | Motor Data sheet and Characteristic Curves and Drawing For CVP | 0 | 2017-11-01 | 2 | APPROVED | 2017-11-03 | Close
1189 | GRT-DS-IP-DT-170430 | GRT-CV03-P0ZEN-162301 | [VMS]_Technical Specification & Datasheet for Vibration Monitoring System | 0 | 2017-11-01 | 1 | APPROVED AS NOTED | 2017-11-02 | Close
1190 | GRT-DS-IP-DT-170436 | GRT-XB02-P0LDB-130044 | [Condensate Filter System]_FOUNDATION AND LOADING DATA | 0 | 2017-11-01 | 2 | APPROVED | 2017-11-03 | Close
1191 | GRT-DS-IP-DT-170436 | GRT-XA00-P0LDB-130037 | [Condensate Filter System]_GENERAL ARRANGEMENT DRAWING | 0 | 2017-11-01 | 2 | APPROVED AS NOTED | 2017-11-03 | Close
1193 | GRT-DS-IP-DT-170431 | GRT-YL22-P0LB-111108 | [Bypass Valve & PRDS]_Name Plate Drawing | 0 | 2017-11-01 | 169 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1194 | GRT-DS-IP-DT-170431 | GRT-YS18-P0LB-111103 | [Bypass Valve & PRDS]_CIRCUIT DIAGRAM FOR HYDRAULIC POWER UNIT | 0 | 2017-11-01 | 169 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1195 | GRT-DS-IP-DT-170440 | GRT-YD00-P0LCB-121014 | [Condensate Extraction Pump]_VFD OUTLINE AND DATA SHEET | 0 | 2017-11-01 | 44 | DEEMED APPROVAL | 2017-12-15 | Close
1201 | GRT-DS-IP-DT-170438 | GRT-XW01-P0SCA-120031 | [Air Compressor]_MAIN MOTOR SPECIFICATION | 0 | 2017-11-01 | 1 | APPROVED | 2017-11-02 | Close
1206 | GRT-DS-IP-DT-170443 | GRT-YT01-P0LCB-121005 | [Condensate Extraction Pump]_MECHANICAL SEAL SPECIFICATION | 1 | 2017-11-01 | 169 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1207 | GRT-DS-IP-DT-170443 | GRT-YT01-P0LCB-121003 | [Condensate Extraction Pump]_DATA SHEET & CHARACTERISTIC CURVE | 1 | 2017-11-01 | 169 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1208 | GRT-DS-IP-DT-170443 | GRT-YM01-P0LCB-121009 | [Condensate Extraction Pump]_MOTOR DATA SHEET & CHARACTERISTIC CURVE | 0 | 2017-11-01 | 169 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1192 | GRT-DS-IP-DT-170437 | GRT-YL22-P0LDB-130053 | [Condensate Filter System]_NAME PLATE DRAWING | B | 2017-11-02 | 21 | I | 2017-11-23 | Close
1202 | GRT-DS-IP-DT-170439 | GRT-YT01-P1H-300069 | [HRSG]_ SPEC. & DRAWING FOR PREHEATER RECIRCULATION PUMP | B | 2017-11-02 | 21 | A | 2017-11-23 | Close
1203 | GRT-DS-IP-DT-170439 | GRT-YT01-P1H-300057 | [HRSG]_DATA & BOM OF INSULATION FOR INTERNAL PIPING | B | 2017-11-02 | 21 | B | 2017-11-23 | Close
1204 | GRT-DS-IP-DT-170439 | GRT-YL16-P1H-300052 | [HRSG]_CABLE SCHEDULE | A | 2017-11-02 | 57 | C | 2017-12-29 | Close
1205 | GRT-DS-IP-DT-170439 | GRT-XH01-P1H-300023 | [HRSG]_PIPE SUPPORT DRAWINGS | B | 2017-11-02 | 21 | I | 2017-11-23 | Close
1196 | GRT-DS-IP-DT-170441 | GRT-YU03-P0MA-200049 | [STG]_Wiring diagrams, Loop diagrams | A | 2017-11-03 | 56 | C | 2017-12-29 | Close
1197 | GRT-DS-IP-DT-170441 | GRT-YU03-P0MA-200043 | [STG]_Control system. Hardware specification | B | 2017-11-03 | 56 | A | 2017-12-29 | Close
1198 | GRT-DS-IP-DT-170441 | GRT-YL15-P0MA-200050 | [STG]_Cable list | A | 2017-11-03 | 56 | A | 2017-12-29 | Close
1199 | GRT-DS-IP-DT-170441 | GRT-YK09-P0MA-200035 | [STG]_Instrumentation data sheets | A | 2017-11-03 | 56 | A | 2017-12-29 | Close
1200 | GRT-DS-IP-DT-170441 | GRT-YK09-P0MA-200032 | [STG]_Cabling system | B | 2017-11-03 | 56 | A | 2017-12-29 | Close
1209 | GRT-DS-IP-DT-170435 | GRT-DS-ME-DCR-0001 | [DCR] Outline Drawing for Deaerator & Feedwater Storage Tank |  | 2017-11-10 | 5 | DEEMED APPROVAL | 2017-11-15 | Close
1210 | GRT-DS-IP-DT-170444 | GRT-YT01-P0LDB-130051 | [Condensate Filter System]_INSTRUMENT DATA SHEET | 0 | 2017-11-13 | 0 | APPROVED | 2017-11-13 | Close
1211 | GRT-DS-IP-DT-170444 | GRT-YK00-P0LDB-130057 | [Condensate Filter System]_HOOK UP DRAWING | 0 | 2017-11-13 | 0 | APPROVED | 2017-11-13 | Close
1215 | GRT-DS-IP-DT-170445 | GRT-YS01-P0QU-130034 | [Sampling System]_SCHEMATIC DIAGRAM | B | 2017-11-13 | 46 | A | 2017-12-29 | Close
1216 | GRT-DS-IP-DT-170446 | GRT-YV02-P0QU-130032 | [Sampling System]_INTERCONNECTION WIRING DIAGRAM | 0 | 2017-11-13 | 0 | APPROVED | 2017-11-13 | Close
1217 | GRT-DS-IP-DT-170446 | GRT-YF00-P0QU-130033 | [Sampling System]_CONTROL LOOP & LOGIC DIAGRAM | 0 | 2017-11-13 | 0 | APPROVED | 2017-11-13 | Close
1218 | GRT-DS-IP-DT-170448 | GRT-YV02-P0PAH-440005 | Cable Connection/wiring Diagram(for power, control & instrument cable) for CTCS & Debris Filter | B | 2017-11-13 | 46 | C | 2017-12-29 | Close
1219 | GRT-DS-IP-DT-170448 | GRT-YK08-P0PAH-440007 | Outline Drawing for Control Panel of CTCS & Debris Filter | B | 2017-11-13 | 46 | C | 2017-12-29 | Close
1220 | GRT-DS-IP-DT-170448 | GRT-YB03-P0PAH-440006 | Configuration Diagram of Package System for CTCS & Debris Filter | B | 2017-11-13 | 46 | C | 2017-12-29 | Close
1221 | GRT-DS-IP-DT-170449 | GRT-YF00-P0PAH-440004 | Control Logic for CTCS & Debris Filter | 0 | 2017-11-13 | 0 | APPROVED | 2017-11-13 | Close
1222 | GRT-DS-IP-DT-170450 | GRT-YV02-P0PAH-440055 | CCW HEX Tube Cleaning System_Cable Connection/wiring Diagram(for power, control & instrument cable) | B | 2017-11-13 | 46 | C | 2017-12-29 | Close
1223 | GRT-DS-IP-DT-170450 | GRT-YK08-P0PAH-440057 | CCW HEX Tube Cleaning System_Outline Drawing for Control Panel | B | 2017-11-13 | 46 | C | 2017-12-29 | Close
1224 | GRT-DS-IP-DT-170450 | GRT-YB03-P0PAH-440056 | CCW HEX Tube Cleaning System_Configuration Diagram of Package System | B | 2017-11-13 | 46 | C | 2017-12-29 | Close
1225 | GRT-DS-IP-DT-170451 | GRT-YF00-P0PAH-440054 | CCW HEX Tube Cleaning System_Control Logic | 0 | 2017-11-13 | 0 | APPROVED | 2017-11-13 | Close
1226 | GRT-DS-IP-DT-170452 | GRT-YT01-P0LAC-122503 | [LP Feed Water Pump]_DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | 0 | 2017-11-13 | 0 | APPROVED AS NOTED | 2017-11-13 | Close
1227 | GRT-DS-IP-DT-170452 | GRT-YT01-P0LAC-122003 | [HP Feed Water Pump]_DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | 0 | 2017-11-13 | 0 | APPROVED AS NOTED | 2017-11-13 | Close
1228 | GRT-DS-IP-DT-170447 | GRT-YV02-P0LDB-130052 | [Condensate Filter System]_INTERCONNECTION WIRING DIAGRAM | B | 2017-11-13 | 46 | A | 2017-12-29 | Close
1229 | GRT-DS-IP-DT-170447 | GRT-YF02-P0LDB-130041 | [Condensate Filter System]_CONTROL CONFIGURATION DIAGRAM | B | 2017-11-13 | 46 | A | 2017-12-29 | Close
1230 | GRT-DS-IP-DT-170453 | GRT-YF00-P0ZEN-161401 | [INC_PMC]_Plant Master Control Diagram | B | 2017-11-13 | 46 | C | 2017-12-29 | Close
1238 | GRT-DS-IP-DT-170457 | GRT-YD00-P0LDB-130040 | [Condensate Filter System]_CONTROL PANEL ARRANGEMENT DRAWING | B | 2017-11-13 | 46 | C | 2017-12-29 | Close
1239 | GRT-DS-IP-DT-170456 | GRT-XB02-P0QC-130009 | [Chemical Dosing System]_FOUNDATION AND LOADING DATA | B | 2017-11-13 | 10 | I | 2017-11-23 | Close
1240 | GRT-DS-IP-DT-170456 | GRT-YF00-P0QC-130019 | [Chemical Dosing System]_CONTROL LOOP & LOGIC DIAGRAM | B | 2017-11-13 | 46 | C | 2017-12-29 | Close
1241 | GRT-DS-IP-DT-170456 | GRT-YK10-P0QC-130010 | [Chemical Dosing System]_EQUIPMENT ASSEMBLY DRAWING | B | 2017-11-13 | 10 | I | 2017-11-23 | Close
1242 | GRT-DS-IP-DT-170456 | GRT-YT01-P0QC-130016 | [Chemical Dosing System]_INSTRUMENT DATA SHEET | B | 2017-11-13 | 46 | C | 2017-12-29 | Close
1243 | GRT-DS-IP-DT-170456 | GRT-YK00-P0QC-130022 | [Chemical Dosing System]_HOOK UP DRAWING | B | 2017-11-13 | 46 | C | 2017-12-29 | Close
1244 | GRT-DS-IP-DT-170458 | GRT-YT01-P0QC-130012 | [Chemical Dosing System]_TECHNICAL DATASHEET | 0 | 2017-11-13 | 0 | APPROVED | 2017-11-13 | Close
1245 | GRT-DS-IP-DT-170458 | GRT-YT01-P0QC-130013 | [Chemical Dosing System]_MOTOR DATA SHEET | 0 | 2017-11-13 | 0 | APPROVED | 2017-11-13 | Close
1246 | GRT-DS-IP-DT-170459 | GRT-YD00-P0MA-200022 | [STG]_Steam Turbine Auxiliaries outline drawing | A | 2017-11-13 | 10 | I | 2017-11-23 | Close
1247 | GRT-DS-IP-DT-170428 | GRT-YD00-P0PGB-113107 | [CCWP ]_MAIN TERMINAL BOX DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | B | 2017-11-13 | 35 | A | 2017-12-18 | Close
1252 | GRT-DS-IP-DT-170462 | GRT-CQ02-P0MAJ-460108 | Operation and Maintenance Manuals | A | 2017-11-13 | 10 | I | 2017-11-23 | Close
1253 | GRT-DS-IP-DT-170464 | GRT-YL22-P0LAC-122008 | [HP Feed Water Pump]_Hydraulic Coupling Data Sheet | A | 2017-11-13 | 57 | B | 2018-01-09 | Close
1212 | GRT-DS-IP-DT-170442 | GRT-YS18-P0LB-111111 | [Bypass Valve & PRDS]_Pneumatic Diagram | B | 2017-11-17 | 42 | B | 2017-12-29 | Close
1213 | GRT-DS-IP-DT-170442 | GRT-YS00-P0LB-111112 | [Bypass Valve & PRDS]_Wiring Diagram | B | 2017-11-17 | 42 | C | 2017-12-29 | Close
1214 | GRT-DS-IP-DT-170442 | GRT-YK08-P0LB-111102 | [Bypass Valve & PRDS]_OUTLINE DRAWING FOR HYDRAULIC POWER UNIT | B | 2017-11-17 | 42 | C | 2017-12-29 | Close
1231 | GRT-DS-IP-DT-170454 | GRT-YL01-P0ZEN-161102 | [INC_DCS_IO]_3rd Party Data-link Interface Signal Database | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1232 | GRT-DS-IP-DT-170454 | GRT-YD05-P0ZEN-161123 | [DCS]_HMI Graphic Drawing | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1233 | GRT-DS-IP-DT-170454 | GRT-YR05-P0ZEN-161136 | [DCS]_Outline & Detail Drawing for Safety Related System Panel | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1234 | GRT-DS-IP-DT-170454 | GRT-YR05-P0ZEN-161134 | [DCS]_Outline & Detail Drawing for System & Marshalling Cabinet | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1235 | GRT-DS-IP-DT-170454 | GRT-YR05-P0ZEN-161132 | [DCS]_Outline & Detail Drawing for LAN Cabinet | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1236 | GRT-DS-IP-DT-170454 | GRT-YR05-P0ZEN-161131 | [DCS]_Outline & Detail Drawing for Console desk & Computer desk & Printer desk | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1237 | GRT-DS-IP-DT-170454 | GRT-CV03-P0ZEN-161112 | [DCS]_Functional Design Specification for Graphic | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1254 | GRT-DS-IP-DT-170465 | GRT-YE00-P0LDB-130056 | [Condensate Filter System]_CABLE TRAY LAYOUT DRAWING | B | 2017-11-27 | 43067 | A | 2017-12-29 | Close
1255 | GRT-DS-IP-DT-170467 | GRT-YU03-P0MA-200039 | [STG]_Control system architecture | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1256 | GRT-DS-IP-DT-170468 | GRT-XS00-P0MAJ-460109 | Vacuum Pump System Description & Control Philosophy | 0 | 2017-11-27 | 134 | DEEMED APPROVAL | 2018-04-10 | Close
1257 | GRT-DS-IP-DT-170469 | GRT-YT01-P0LCB-121007 | [Condensate Extraction Pump]_SUCTION STRAINER SPECIFICATION | 0 | 2017-11-27 | 21 | APPROVED | 2017-12-18 | Close
1258 | GRT-DS-IP-DT-170469 | GRT-YK00-P0LCB-121011 | [Condensate Extraction Pump]_INSTRUMENTATION HOOK - UP DRAWING | 0 | 2017-11-27 | 21 | APPROVED | 2017-12-18 | Close
1259 | GRT-DS-IP-DT-170469 | GRT-XG02-P0LCB-121002 | [Condensate Extraction Pump]_P&I DIAGRAM | 1 | 2017-11-27 | 21 | APPROVED | 2017-12-18 | Close
1260 | GRT-DS-IP-DT-170463 | GRT-YF00-P0ZEN-161406 | [INC_Start&Shutdown Diagram]_Plant Start-up & Shutdown Sequence Diagram for Shutdown | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1261 | GRT-DS-IP-DT-170470 | GRT-YT01-P0QU-130031 | [Sampling System]_INSTRUMENT DATA SHEET | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1262 | GRT-DS-IP-DT-170470 | GRT-YT01-P0QU-130030 | [Sampling System]_TECHNICAL DATASHEET | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1263 | GRT-DS-IP-DT-170470 | GRT-YL00-P0QU-130028 | [Sampling System]_INSTRUMENT LIST | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1264 | GRT-DS-IP-DT-170470 | GRT-YF02-P0QU-130027 | [Sampling System]_CONTROL CONFIGURATION DIAGRAM | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1265 | GRT-DS-IP-DT-170470 | GRT-XS00-P0QU-130026 | [Sampling System]_SYSTEM DESCRIPTION | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1266 | GRT-DS-IP-DT-170470 | GRT-XN00-P0QU-130029 | [Sampling System]_VALVE LIST | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1267 | GRT-DS-IP-DT-170470 | GRT-XG02-P0QU-130024 | [Sampling System]_P&ID | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1268 | GRT-DS-IP-DT-170470 | GRT-XA00-P0QU-130025 | [Sampling System]_GENERAL ARRANGEMENT DRAWING | 0 | 2017-11-27 | 116 | DEEMED APPROVAL | 2018-03-23 | Close
1269 | GRT-DS-IP-DT-170471 | GRT-CV03-P0ZEN-163701 | [Field Instruments(DHI)]_Technical Specification & Datasheet for Process Transmitter - BOP | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1270 | GRT-DS-IP-DT-170472 | GRT-XL35-P0LB-111109 | [Bypass Valve & PRDS]_Instrument List & Database Sheet | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1271 | GRT-DS-IP-DT-170472 | GRT-XS01-P0LB-111105 | [Bypass Valve & PRDS]_Operating Description for HPU system for Bypass System | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1272 | GRT-DS-IP-DT-170472 | GRT-YS18-P0LB-111107 | [Bypass Valve & PRDS]_P&ID for HPU | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1273 | GRT-DS-IP-DT-170472 | GRT-YT01-P0LB-111110 | [Bypass Valve & PRDS]_Data Sheet for HPU | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1274 | GRT-DS-IP-DT-170473 | GRT-YD08-P0UMA-164311 | [Steam Turbine Building_INC_ILD]_BOP_Instrument Location Drawing | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1275 | GRT-DS-IP-DT-170474 | GRT-XN00-P0LDB-130043 | [Condensate Filter System]_VALVE LIST | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1276 | GRT-DS-IP-DT-170474 | GRT-YT01-P0LDB-130047 | [Condensate Filter System]_TECHNICAL DATASHEET | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1277 | GRT-DS-IP-DT-170474 | GRT-YT01-P0LDB-130050 | [Condensate Filter System]_VALVE DATA SHEET | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1278 | GRT-DS-IP-DT-170475 | GRT-YT10-P0ZEN-144502 | [Piping General]_Pipe Thickness Calculation (BOP) | 1 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1279 | GRT-DS-IP-DT-170475 | GRT-DE00-P0ZEN-144500 | [Piping General]_Piping material specification (BOP) | 1 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1280 | GRT-DS-IP-DT-170455 | GRT-YK08-P0MAJ-460200 | General Arrangement Drawing For Water Box Vacuum Pump | 1 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1281 | GRT-DS-IP-DT-170455 | GRT-YK08-P0MAJ-460100 | General Arrangement Drawing For Condenser Vacuum Pump | 1 | 2017-11-27 | 25 | DEEMED APPROVAL | 2017-12-22 | Close
1282 | GRT-DS-IP-DT-170455 | GRT-XK00-P0MAJ-460214 | Baseframe Drawing For Water Box Vacuum Pump | 1 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1283 | GRT-DS-IP-DT-170455 | GRT-XB02-P0MAJ-460211 | Foundation Drawing For Water Box Vacuum Pump | 1 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1284 | GRT-DS-IP-DT-170477 | GRT-YB03-P1H-300033 | [HRSG]_CABLE CONNECTION DIAGRAM | B | 2017-11-27 | 43067 | A | 2017-12-27 | Close
1285 | GRT-DS-IP-DT-170477 | GRT-XH01-P1H-300021 | [HRSG]_PIPE SUPPORT DRAWING FOR EXTERNAL PIPING | B | 2017-11-27 | 43067 | I | 2017-12-27 | Close
1286 | GRT-DS-IP-DT-170461 | GRT-QM03-P0ZEN-141009 | LIQUID PENETRANT EXAMINATION PROCEDURE | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1287 | GRT-DS-IP-DT-170461 | GRT-QM03-P0ZEN-141008 | MAGNETIC PARTICLE EXAMINATION PROCEDURE | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1288 | GRT-DS-IP-DT-170461 | GRT-QM03-P0ZEN-141007 | ULTRASONIC EXAMINATION PROCEDURE | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1289 | GRT-DS-IP-DT-170461 | GRT-QM03-P0ZEN-141006 | RADIOGRAPHIC EXAMINATION PROCEDURE | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1290 | GRT-DS-IP-DT-170479 | GRT-YL00-P0ZEN-163700 | [Field Instruments(DHI)]_Field Instrument List for BOP | 0 | 2017-11-27 | 135 | DEEMED APPROVAL | 2018-04-11 | Close
1292 | GRT-DS-IP-DT-170481 | GRT-YD00-P0PGB-113201 | [Blowdown Cooler]_OUTLINE DRAWING FOR PLATE TYPE HEAT EXCHANGER | 1 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1293 | GRT-DS-IP-DT-170482 | GRT-YD00-P0PGB-113105 | [CCWP ]_OUTLINE DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | 1 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1294 | GRT-DS-IP-DT-170482 | GRT-YD00-P0PCC-113005 | [Aux. Cooling Water Pump]_OUTLINE DRAWING FOR AUXILIARY COOLING WATER PUMP MOTOR | 1 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1295 | GRT-DS-IP-DT-170482 | GRT-XG02-P0PG-110009 | [Closed cooling water system]_P&I DIAGRAM | 1 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1296 | GRT-DS-IP-DT-170483 | GRT-YD00-P0QJA-111000 | [N2 Gas System]_General Arrangement Drawing | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1297 | GRT-DS-IP-DT-170480 | GRT-CV03-P0ZEN-163702 | [Field Instruments(DHI)]_Technical Specification & Datasheet for Local Instrument - BOP | 0 | 2017-11-27 | 121 | DEEMED APPROVAL | 2018-03-28 | Closed
1298 | GRT-DS-IP-DT-170484 | GRT-YF02-P0SCA-120026 | [Air Compressor]_PLC PANEL DRAWING | 0 | 2017-11-27 | 21 | APPROVED AS NOTED | 2017-12-18 | Close
1299 | GRT-DS-IP-DT-170484 | GRT-YD00-P0SCA-120007 | [Air Compressor]_AIR COMPRESSOR_GENERAL ARRANGEMENT DRAWING FOR AIR COMPRESSORS PACKAGE | 2 | 2017-11-27 | 21 | APPROVED AS NOTED | 2017-12-18 | Close
1300 | GRT-DS-IP-DT-170484 | GRT-XG02-P0SC-120003 | [Compressed air system]_P&I DIAGRAM FOR SERVICE AIR SYSTEM | 1 | 2017-11-27 | 21 | APPROVED | 2017-12-18 | Close
1301 | GRT-DS-IP-DT-170484 | GRT-CQ02-P0SCA-120030 | [Air Compressor]_O & M MANUAL | 0 | 2017-11-27 | 21 | APPROVED | 2017-12-18 | Close
1302 | GRT-DS-IP-DT-170389 | GRT-YK08-P0LB-111101 | [Bypass Valve & PRDS]_OUTLINE DRAWING FOR BYPASS AND PRDS | 0 | 2017-11-27 | 143 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1303 | GRT-DS-IP-DT-170486 | GRT-YT02-P1H-300065 | [HRSG]_REMOTE DRUM LEVEL INDICATOR DATASHEET & DRAWINGS | 0 | 2017-11-27 | 21 | APPROVED | 2017-12-18 | Close
1304 | GRT-DS-IP-DT-170486 | GRT-YT01-P1H-300069 | [HRSG]_ SPEC. & DRAWING FOR PREHEATER RECIRCULATION PUMP | 0 | 2017-11-27 | 21 | APPROVED | 2017-12-18 | Close
1305 | GRT-DS-IP-DT-170486 | GRT-YT01-P1H-300068 | [HRSG]_DIVERTER & GUILLOTINE DAMPER DOCUMENT PACKAGE | 0 | 2017-11-27 | 21 | APPROVED | 2017-12-18 | Close
1306 | GRT-DS-IP-DT-170486 | GRT-YT01-P1H-300057 | [HRSG]_DATA & BOM OF INSULATION FOR INTERNAL PIPING | 0 | 2017-11-27 | 21 | APPROVED | 2017-12-18 | Close
1307 | GRT-DS-IP-DT-170486 | GRT-YL16-P1H-300052 | [HRSG]_CABLE SCHEDULE | 0 | 2017-11-27 | 21 | APPROVED AS NOTED | 2017-12-18 | Close
1308 | GRT-DS-IP-DT-170486 | GRT-YD00-P1H-300035 | [HRSG]_SPEC. & DRAWING FOR STEAM DRUM | 0 | 2017-11-27 | 21 | APPROVED | 2017-12-18 | Close
1312 | GRT-DS-IP-DT-170485 | GRT-YF00-P0ZEN-161401 | [INC_PMC]_Plant Master Control Diagram | 0 | 2017-11-27 | 2 | APPROVED AS NOTED | 2017-11-29 | Close
1313 | GRT-DS-IP-DT-170491 | GRT-YL22-P0LAC-122008 | [HP Feed Water Pump]_Hydraulic Coupling Data Sheet | 0 | 2017-11-27 | 2 | APPROVED AS NOTED | 2017-11-29 | Close
1248 | GRT-DS-IP-DT-170460 | GRT-YT01-P1H-300063 | [HRSG]_CEMS DATASHEET & DRAWINGS | B | 2017-11-29 | 43067 | A | 2017-12-27 | Close
1249 | GRT-DS-IP-DT-170460 | GRT-YK10-P1H-300050 | [HRSG]_MANUAL VALVE ASSEMBLY DRAWING FOR EXTERNAL PIPING | B | 2017-11-29 | 43067 | I | 2017-12-27 | Close
1250 | GRT-DS-IP-DT-170460 | GRT-YK09-P1H-300049 | [HRSG]_SPECIALTY DRAWING FOR EXTERNAL PIPING | B | 2017-11-29 | 43067 | I | 2017-12-27 | Close
1251 | GRT-DS-IP-DT-170460 | GRT-XJ00-P1H-300024 | [HRSG]_ERECTION ISOMETRIC DRAWING FOR PIPNG FABRICATION STANDARD | B | 2017-11-29 | 28 | I | 2017-12-27 | Close
1309 | GRT-DS-IP-DT-170487 | GRT-YU03-P0MA-200043 | [STG]_Control system. Hardware specification | 0 | 2017-11-29 | 132 | DEEMED APPROVAL | 2018-04-10 | Close
1310 | GRT-DS-IP-DT-170488 | GRT-YT01-P0ZEN-113301 | [MOV (Gate & Globe)(DHI)]_VALVE LIST & DATA SHEET FOR MOV (G&G) | 0 | 2017-11-29 | 141 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1311 | GRT-DS-IP-DT-170488 | GRT-YK10-P0ZEN-113300 | [MOV (Gate & Globe)(DHI)]_OUTLINE DRAWING FOR MOV (G&G) | 0 | 2017-11-29 | 141 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1314 | GRT-DS-IP-DT-170492 | GRT-CV03-P0ZEN-163706 | [Local Boxes(DHI)]_Technical Specification for Junction Box & Racks | 1 | 2017-11-29 | 19 | APPROVED | 2017-12-18 | Close
1315 | GRT-DS-IP-DT-170493 | GRT-YL00-P0MA-200048 | [STG]_I/O list | A | 2017-11-29 | 28 | I | 2017-12-27 | Close
1316 | GRT-DS-IP-DT-170493 | GRT-XB00-P0MA-200008 | [STG]_Loads plan - Levels | D | 2017-11-29 | 28 | I | 2017-12-27 | Close
1317 | GRT-DS-IP-DT-170490 | GRT-DP00-P0ZEN-070001 | Painting specification | 0 | 2017-11-29 | 141 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1318 | GRT-DS-IP-DT-170489 | GRT-YF02-P0LDB-130041 | [Condensate Filter System]_CONTROL CONFIGURATION DIAGRAM | 0 | 2017-11-29 | 141 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1319 | GRT-DS-IP-DT-170494 | GRT-YD00-P0PGB-113107 | [CCWP ]_MAIN TERMINAL BOX DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | 0 | 2017-11-29 | 141 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1320 | GRT-DS-IP-DT-170495 | GRT-YS01-P0QU-130034 | [Sampling System]_SCHEMATIC DIAGRAM | 0 | 2017-11-29 | 132 | DEEMED APPROVAL | 2018-04-10 | Close
1321 | GRT-DS-IP-DT-170497 | GRT-YL22-P0LDB-130053 | [Condensate Filter System]_NAME PLATE DRAWING | 0 | 2017-11-30 | 98 | DEEMED APPROVAL | 2018-03-08 | Close
1322 | GRT-DS-IP-DT-170497 | GRT-YD00-P0LDB-130040 | [Condensate Filter System]_CONTROL PANEL ARRANGEMENT DRAWING | 0 | 2017-11-30 | 98 | DEEMED APPROVAL | 2018-03-08 | Close
1323 | GRT-DS-IP-DT-170497 | GRT-XH01-P0LDB-130046 | [Condensate Filter System]_PIPING ARRANGEMENT DRAWING | 0 | 2017-11-30 | 140 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1327 | GRT-DS-IP-DT-170496 | GRT-CV03-P0ZEN-163703 | [Field Instruments(DHI)]_Technical Specification & Datasheet for Flow Element - BOP | 0 | 2017-11-30 | 105 | DEEMED APPROVAL | 2018-03-15 | Closed
1328 | GRT-DS-IP-DT-170498 | GRT-YT01-P0QC-130016 | [Chemical Dosing System]_INSTRUMENT DATA SHEET | 0 | 2017-11-30 | 18 | APPROVED | 2017-12-18 | Close
1329 | GRT-DS-IP-DT-170498 | GRT-YT01-P0QC-130015 | [Chemical Dosing System]_VALVE DATA SHEET | 0 | 2017-11-30 | 18 | APPROVED AS NOTED | 2017-12-18 | Close
1330 | GRT-DS-IP-DT-170498 | GRT-YT01-P0QC-130014 | [Chemical Dosing System]_PUMP DATA SHEET | 0 | 2017-11-30 | 18 | APPROVED AS NOTED | 2017-12-18 | Close
1331 | GRT-DS-IP-DT-170498 | GRT-YK10-P0QC-130010 | [Chemical Dosing System]_EQUIPMENT ASSEMBLY DRAWING | 0 | 2017-11-30 | 18 | APPROVED | 2017-12-18 | Close
1332 | GRT-DS-IP-DT-170498 | GRT-YF02-P0QC-130006 | [Chemical Dosing System]_CONTROL CONFIGURATION DIAGRAM | 0 | 2017-11-30 | 18 | APPROVED AS NOTED | 2017-12-18 | Close
1333 | GRT-DS-IP-DT-170498 | GRT-XH01-P0QC-130011 | [Chemical Dosing System]_PIPING ARRANGEMENT DRAWING | 0 | 2017-11-30 | 18 | APPROVED AS NOTED | 2017-12-18 | Close
1334 | GRT-DS-IP-DT-170498 | GRT-XB02-P0QC-130009 | [Chemical Dosing System]_FOUNDATION AND LOADING DATA | 0 | 2017-11-30 | 18 | APPROVED | 2017-12-18 | Close
1324 | GRT-DS-IP-DT-170478 | GRT-YS18-P0LB-111111 | [Bypass Valve & PRDS]_Pneumatic Diagram | 0 | 2017-12-04 | 14 | APPROVED | 2017-12-18 | Close
1325 | GRT-DS-IP-DT-170478 | GRT-YS00-P0LB-111112 | [Bypass Valve & PRDS]_Wiring Diagram | 0 | 2017-12-04 | 14 | APPROVED | 2017-12-18 | Close
1326 | GRT-DS-IP-DT-170478 | GRT-YK08-P0LB-111102 | [Bypass Valve & PRDS]_OUTLINE DRAWING FOR HYDRAULIC POWER UNIT | 0 | 2017-12-04 | 14 | APPROVED | 2017-12-18 | Close
1335 | GRT-DS-IP-DT-170499 | GRT-YS01-P0LDB-130055 | [Condensate Filter System]_SCHEMATIC DIAGRAM | B | 2017-12-05 | 24 | C | 2017-12-29 | Close
1336 | GRT-DS-IP-DT-170499 | GRT-YF00-P0LDB-130054 | [Condensate Filter System]_CONTROL LOOP & LOGIC DIAGRAM | B | 2017-12-05 | 24 | C | 2017-12-29 | Close
1338 | GRT-DS-IP-DT-170501 | GRT-CQ02-P0LDB-130058 | [Condensate Filter System]_O&M MANUAL | A | 2017-12-05 | 108 | DEEMED APPROVAL | 2018-03-23 | Close
1339 | GRT-DS-IP-DT-170502 | GRT-CQ02-P0QU-130035 | [Sampling System]_O&M MANUAL | A | 2017-12-05 | 108 | DEEMED APPROVAL | 2018-03-23 | Close
1337 | GRT-DS-IP-DT-170500 | GRT-YK10-P0LDB-130045 | [Condensate Filter System]_EQUIPMENT ASSEMBLY DRAWING | 0 | 2017-12-08 | 0 | APPROVED | 2017-12-08 | Close
1351 | GRT-DS-IP-DT-170511 | GRT-CQ02-P0MAG-410011 | Condenser_Instruction Manuals for Erection, Installation, Operation and Maintenance | A | 2017-12-13 | 27 | C | 2018-01-09 | Close
1352 | GRT-DS-IP-DT-170512 | GRT-YT01-P1H-300062 | [HRSG]_AIRCRAFT WARNING LIGHT DATASHEET & LAYOUT DIAGRAM | A | 2017-12-13 | 33 | C | 2018-01-15 | Close
1353 | GRT-DS-IP-DT-170512 | GRT-YD00-P1H-300037 | [HRSG]_POWER DISTRIBUTION PANEL DRAWINGS | A | 2017-12-13 | 33 | C | 2018-01-15 | Close
1354 | GRT-DS-IP-DT-170512 | GRT-XJ00-P1H-300024 | [HRSG]_ERECTION ISOMETRIC DRAWING FOR PIPNG FABRICATION STANDARD | C | 2017-12-13 | 33 | B | 2018-01-15 | Close
1355 | GRT-DS-IP-DT-170513 | GRT-YL00-P0MAG-410010 | Condenser_Instrument list and Datasheet for Condenser | A | 2017-12-13 | 27 | B | 2018-01-09 | Close
1340 | GRT-DS-IP-DT-170508 | GRT-YK08-P0PBB-440102 | Debris Filter_Outline Drawing | 0 | 2017-12-15 | 125 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1341 | GRT-DS-IP-DT-170508 | GRT-YK08-P0PAH-440053 | CCW HEX Tube Cleaning System_Outline Drawing for Ball Recirculation unit | 0 | 2017-12-15 | 125 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1342 | GRT-DS-IP-DT-170508 | GRT-YK08-P0PAH-440052 | CCW HEX Tube Cleaning System_Outline Drawing | 0 | 2017-12-15 | 125 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1343 | GRT-DS-IP-DT-170508 | GRT-YK08-P0PAH-440003 | Condenser Tube Cleaning System_Outline Drawing for Ball Recirculation unit | 0 | 2017-12-15 | 125 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1344 | GRT-DS-IP-DT-170508 | GRT-XG02-P0PAH-440051 | CCW HEX Tube Cleaning System_P & I Diagram | 0 | 2017-12-15 | 125 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1345 | GRT-DS-IP-DT-170509 | GRT-YV02-P0PAH-440055 | CCW HEX Tube Cleaning System_Cable Connection/wiring Diagram(for power, control & instrument cable) | 0 | 2017-12-15 | 28 | DEEMED APPROVAL | 2018-01-12 | Closed
1346 | GRT-DS-IP-DT-170509 | GRT-YK08-P0PAH-440057 | CCW HEX Tube Cleaning System_Outline Drawing for Control Panel | 0 | 2017-12-15 | 33 | DEEMED APPROVAL | 2018-01-17 | Closed
1347 | GRT-DS-IP-DT-170509 | GRT-YB03-P0PAH-440056 | CCW HEX Tube Cleaning System_Configuration Diagram of Package System | 0 | 2017-12-15 | 33 | DEEMED APPROVAL | 2018-01-17 | Closed
1348 | GRT-DS-IP-DT-170510 | GRT-YV02-P0PAH-440005 | Cable Connection/wiring Diagram(for power, control & instrument cable) for CTCS & Debris Filter | 0 | 2017-12-15 | 33 | DEEMED APPROVAL | 2018-01-17 | Closed
1349 | GRT-DS-IP-DT-170510 | GRT-YK08-P0PAH-440007 | Outline Drawing for Control Panel of CTCS & Debris Filter | 0 | 2017-12-15 | 33 | DEEMED APPROVAL | 2018-01-17 | Closed
1350 | GRT-DS-IP-DT-170510 | GRT-YB03-P0PAH-440006 | Configuration Diagram of Package System for CTCS & Debris Filter | 0 | 2017-12-15 | 33 | DEEMED APPROVAL | 2018-01-17 | Closed
1356 | GRT-DS-IP-DT-170514 | GRT-YD00-P0LCB-121014 | [Condensate Extraction Pump]_VFD OUTLINE AND DATA SHEET | 1 | 2017-12-15 | 125 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1357 | GRT-DS-IP-DT-170507 | GRT-YT01-P0MAJ-460205 | Motor Data sheet and Characteristic Curves and Drawing For WBVP | 1 | 2017-12-15 | 125 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1358 | GRT-DS-IP-DT-170506 | GRT-YK08-P0MAG-410002 | Condenser_General Arrangement | 1 | 2017-12-15 | 125 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1359 | GRT-DS-IP-DT-170506 | GRT-XL00-P0MAG-410003 | Condenser_Connection List | 1 | 2017-12-15 | 125 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1360 | GRT-DS-IP-DT-170506 | GRT-XL00-P0MAG-410004 | Condenser_Connection Detail | 1 | 2017-12-15 | 125 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1361 | GRT-DS-IP-DT-170506 | GRT-YK08-P0MAG-410001 | Condenser_General Layout | 1 | 2017-12-15 | 125 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1363 | GRT-DS-IP-DT-170517 | GRT-XB00-P0MA-200008 | [STG]_Loads plan - Levels | 0 | 2017-12-15 | 125 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1364 | GRT-DS-IP-DT-170503 | GRT-XJ00-P0LBG-143003 | Piping ISO (Small Bore) - Aux. Steam | 0 | 2017-12-15 | 115 | DEEMED APPROVAL | 2018-04-09 | Close
1365 | GRT-DS-IP-DT-170503 | GRT-XJ00-P0LBA-143002 | Piping ISO (Small Bore) - LP Steam | 0 | 2017-12-15 | 105 | DEEMED APPROVAL | 2018-03-30 | Close
1366 | GRT-DS-IP-DT-170503 | GRT-XJ00-P0LBA-143001 | Piping ISO (Small Bore) - HP Steam | 0 | 2017-12-15 | 105 | DEEMED APPROVAL | 2018-03-30 | Close
1384 | GRT-DS-IP-DT-170518 | GRT-YT01-P1H-300063 | [HRSG]_CEMS DATASHEET & DRAWINGS | 0 | 2017-12-15 | 125 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1385 | GRT-DS-IP-DT-170518 | GRT-YB03-P1H-300033 | [HRSG]_CABLE CONNECTION DIAGRAM | 0 | 2017-12-15 | 125 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1387 | GRT-DS-IP-DT-170520 | GRT-YK08-P0LAA-420001 | Outline Drawing for Deaerator & Feedwater Storage Tank | 1 | 2017-12-15 | 0 | DEEMED APPROVAL | 2017-12-15 | Close
1388 | GRT-DS-IP-DT-170515 | GRT-YT01-P0LB-111100 | [Bypass Valve & PRDS]_DATA SHEET FOR BYPASS AND PRDS | 1 | 2017-12-15 | 125 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1389 | GRT-DS-IP-DT-170515 | GRT-XW01-P0QJA-110206 | [N2 Gas system]_Design Criteria | 1 | 2017-12-15 | 125 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1390 | GRT-DS-IP-DT-170515 | GRT-XS00-P0QJA-110406 | [N2 Gas system]_system description | 1 | 2017-12-15 | 125 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1391 | GRT-DS-IP-DT-170515 | GRT-XG02-P0QJA-110010 | [N2 Gas system]_P&I DIAGRAM | 2 | 2017-12-15 | 125 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1291 | GRT-DS-IP-DT-170476 | GRT-YD00-P0LAC-122508 | [LP Feed Water Pump]_VFD OUTLINE AND DATA SHEET | B | 2017-12-18 | 43067 | C | 2018-01-09 | Close
1367 | GRT-DS-IP-DT-170504 | GRT-XK00-P0PAB-144007 | Support DWG (Large Bore) - Aux. cooling water | A | 2017-12-18 | 28 | B | 2018-01-15 | Close
1368 | GRT-DS-IP-DT-170504 | GRT-XK00-P0PAB-144012 | Support DWG (Large Bore) – Cooling water | A | 2017-12-18 | 28 | B | 2018-01-15 | Close
1369 | GRT-DS-IP-DT-170504 | GRT-XK00-P0LAB-144005 | Support DWG (Large Bore) - Feedwater | A | 2017-12-18 | 28 | B | 2018-01-15 | Close
1370 | GRT-DS-IP-DT-170504 | GRT-XK00-P0LBA-144001 | Support DWG (Large Bore) - HP Steam | A | 2017-12-18 | 28 | B | 2018-01-15 | Close
1371 | GRT-DS-IP-DT-170504 | GRT-XK00-P0LBA-144002 | Support DWG (Large Bore) - LP Steam | A | 2017-12-18 | 28 | B | 2018-01-15 | Close
1372 | GRT-DS-IP-DT-170504 | GRT-XK00-P0LBG-144003 | Support DWG (Large Bore) - Aux. Steam | A | 2017-12-18 | 28 | B | 2018-01-15 | Close
1373 | GRT-DS-IP-DT-170504 | GRT-XK00-P0LCA-144006 | Support DWG (Large Bore) - Condensate | A | 2017-12-18 | 28 | B | 2018-01-15 | Close
1374 | GRT-DS-IP-DT-170504 | GRT-XK00-P0MAA-144010 | Support DWG (Large Bore) - ST Misc. | A | 2017-12-18 | 28 | B | 2018-01-15 | Close
1375 | GRT-DS-IP-DT-170504 | GRT-XK00-P0PGB-144008 | Support DWG (Large Bore) - CCW | A | 2017-12-18 | 28 | B | 2018-01-15 | Close
1376 | GRT-DS-IP-DT-170504 | GRT-XK00-P0SCA-144009 | Support DWG (Large Bore) - Compressed air | A | 2017-12-18 | 28 | B | 2018-01-15 | Close
1377 | GRT-DS-IP-DT-170504 | GRT-XK00-P0LCM-144004 | Support DWG (Large Bore) - Steam drain | A | 2017-12-18 | 28 | B | 2018-01-15 | Close
1378 | GRT-DS-IP-DT-170505 | GRT-XK00-P0ZEN-144905 | Outline Drawing for Piping LP Manual Forging Valve | A | 2017-12-18 | 22 | B | 2018-01-09 | Close
1379 | GRT-DS-IP-DT-170505 | GRT-XK00-P0ZEN-144900 | Outline Drawing for Piping Manual Ball Valve | A | 2017-12-18 | 22 | B | 2018-01-09 | Close
1380 | GRT-DS-IP-DT-170505 | GRT-XK00-P0ZEN-144901 | Outline Drawing for Piping Manual Butterfly Valve | A | 2017-12-18 | 22 | B | 2018-01-09 | Close
1381 | GRT-DS-IP-DT-170505 | GRT-XK00-P0ZEN-144902 | Outline Drawing for Piping HP Manual Casting Valve | A | 2017-12-18 | 22 | B | 2018-01-09 | Close
1382 | GRT-DS-IP-DT-170505 | GRT-XK00-P0ZEN-144903 | Outline Drawing for Piping LP Manual Casting Valve | A | 2017-12-18 | 22 | B | 2018-01-09 | Close
1383 | GRT-DS-IP-DT-170505 | GRT-XK00-P0ZEN-144904 | Outline Drawing for Piping HP Manual Forging Valve | A | 2017-12-18 | 22 | B | 2018-01-09 | Close
1392 | GRT-DS-IP-DT-170521 | GRT-YT10-P0PGB-400050 | Thermal Calculation for CCW Heat Exchanger | B | 2017-12-18 | 22 | C | 2018-01-09 | Close
1393 | GRT-DS-IP-DT-170523 | GRT-YD00-P0PGB-430020 | Outline Drawing for CCW Chemical Additive Tank | 1 | 2017-12-18 | 122 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1394 | GRT-DS-IP-DT-170524 | GRT-YD00-P0LCM-430010 | Outline Drawing for Atmospheric Flash Tank | 1 | 2017-12-18 | 122 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1395 | GRT-DS-IP-DT-170525 | GRT-XJ00-P0SCB-143011 | Piping ISO (Small Bore) - Service air | 0 | 2017-12-18 | 101 | DEEMED APPROVAL | 2018-03-29 | Close
1396 | GRT-DS-IP-DT-170525 | GRT-XJ00-P0SCA-143010 | Piping ISO (Small Bore) - Compressed air | 0 | 2017-12-18 | 98 | DEEMED APPROVAL | 2018-03-26 | Close
1397 | GRT-DS-IP-DT-170525 | GRT-XJ00-P0PAB-143015 | Piping ISO (Small Bore) - Cooling water | 0 | 2017-12-18 | 122 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1386 | GRT-DS-IP-DT-170519 | GRT-YF00-P1H-300044 | [HRSG]_SEQUENCES & CONTROLS | B | 2017-12-19 | 21 | C | 2018-01-09 | Close
1362 | GRT-DS-IP-DT-170516 | GRT-YK08-P0MAG-410012 | Transition Piece Assembly between LP TBN and Condenser | 0 | 2017-12-20 | 120 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1398 | GRT-DS-IP-DT-170522 | GRT-YV02-P0SCA-120022 | [Air Compressor]_I&C WIRING DIAGRAMS | 1 | 2017-12-20 | 120 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1399 | GRT-DS-IP-DT-170526 | GRT-YT01-P0MAJ-460115 | Recirculation Pump Data Sheet and Characteristic Curves and Drawing For CVP | 1 | 2017-12-20 | 120 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1400 | GRT-DS-IP-DT-170526 | GRT-XK00-P0MAJ-460213 | Tank Drawing For Water Box Vacuum Pump | 1 | 2017-12-20 | 120 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1401 | GRT-DS-IP-DT-170526 | GRT-XK00-P0MAJ-460113 | Tank Drawing For Condenser Vacuum Pump | 1 | 2017-12-20 | 120 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1402 | GRT-DS-IP-DT-170528 | GRT-QA00-P0ZEN-141005 | Welder consumable control procedure for BOP Piping | 0 | 2017-12-22 | 118 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1403 | GRT-DS-IP-DT-170528 | GRT-QA00-P0ZEN-141003 | Welder qualificatoin list for BOP Piping | 0 | 2017-12-22 | 118 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1404 | GRT-DS-IP-DT-170528 | GRT-DP00-P0ZEN-141004 | Repair welding procedure for BOP Piping | 0 | 2017-12-22 | 118 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1405 | GRT-DS-IP-DT-170528 | GRT-DP00-P0ZEN-141002 | Heat treatment procedure for BOP Piping | 0 | 2017-12-22 | 118 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1406 | GRT-DS-IP-DT-170528 | GRT-DP00-P0ZEN-141001 | WPS&PQR for BOP Piping | 0 | 2017-12-22 | 118 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1407 | GRT-DS-IP-DT-170529 | GRT-YV02-P0LDB-130052 | [Condensate Filter System]_INTERCONNECTION WIRING DIAGRAM | 0 | 2017-12-22 | 76 | DEEMED APPROVAL | 2018-03-08 | Close
1408 | GRT-DS-IP-DT-170529 | GRT-YS01-P0LDB-130055 | [Condensate Filter System]_SCHEMATIC DIAGRAM | 0 | 2017-12-22 | 76 | DEEMED APPROVAL | 2018-03-08 | Close
1409 | GRT-DS-IP-DT-170529 | GRT-YF00-P0LDB-130054 | [Condensate Filter System]_CONTROL LOOP & LOGIC DIAGRAM | 0 | 2017-12-22 | 76 | DEEMED APPROVAL | 2018-03-08 | Close
1410 | GRT-DS-IP-DT-170529 | GRT-YE00-P0LDB-130056 | [Condensate Filter System]_CABLE TRAY LAYOUT DRAWING | 0 | 2017-12-22 | 76 | DEEMED APPROVAL | 2018-03-08 | Close
1411 | GRT-DS-IP-DT-170530 | GRT-YK09-P1H-300049 | [HRSG]_SPECIALTY DRAWING FOR EXTERNAL PIPING | 0 | 2017-12-22 | 2833
1412 | GRT-DS-IP-DT-170530 | GRT-XH01-P1H-300023 | [HRSG]_PIPE SUPPORT DRAWINGS | 0 | 2017-12-22 | 118 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1413 | GRT-DS-IP-DT-170530 | GRT-YR01-P1H-300055 | [HRSG]_CONSERVATION PROCEDURE | 0 | 2017-12-22 | 118 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1414 | GRT-DS-IP-DT-170530 | GRT-YR01-P1H-300054 | [HRSG]_CHEMICAL CLEANING PROCEDURE | 0 | 2017-12-22 | 118 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1415 | GRT-DS-IP-DT-170530 | GRT-YK10-P1H-300050 | [HRSG]_MANUAL VALVE ASSEMBLY DRAWING FOR EXTERNAL PIPING | 0 | 2017-12-22 | 118 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1416 | GRT-DS-IP-DT-170530 | GRT-XH01-P1H-300021 | [HRSG]_PIPE SUPPORT DRAWING FOR EXTERNAL PIPING | 0 | 2017-12-22 | 54 | DEEMED APPROVAL | 2018-02-14 | Close
1417 | GRT-DS-IP-DT-170535 | GRT-YK08-P0MAJ-460100 | General Arrangement Drawing For Condenser Vacuum Pump | 2 | 2017-12-22 | 118 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1418 | GRT-DS-IP-DT-170538 | GRT-YF00-P0QC-130019 | [Chemical Dosing System]_CONTROL LOOP & LOGIC DIAGRAM | 0 | 2017-12-22 | 67 | DEEMED APPROVAL | 2018-02-27 | Closed
1419 | GRT-DS-IP-DT-170538 | GRT-YE00-P0QC-130021 | [Chemical Dosing System]_CABLE TRAY LAYOUT DRAWING | 0 | 2017-12-22 | 118 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1420 | GRT-DS-IP-DT-170538 | GRT-YV02-P0QC-130017 | [Chemical Dosing System]_INTERCONNECTION WIRING DIAGRAM | 0 | 2017-12-22 | 118 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1421 | GRT-DS-IP-DT-170538 | GRT-YL22-P0QC-130018 | [Chemical Dosing System]_NAME PLATE DRAWING | 0 | 2017-12-22 | 89 | DEEMED APPROVAL | 2018-03-21 | Closed
1422 | GRT-DS-IP-DT-170538 | GRT-YS01-P0QC-130020 | [Chemical Dosing System]_SCHEMATIC DIAGRAM | 0 | 2017-12-22 | 67 | DEEMED APPROVAL | 2018-02-27 | Closed
1423 | GRT-DS-IP-DT-170538 | GRT-YK00-P0QC-130022 | [Chemical Dosing System]_HOOK UP DRAWING | 0 | 2017-12-22 | 63 | DEEMED APPROVAL | 2018-02-23 | Closed
1424 | GRT-DS-IP-DT-170539 | GRT-YT10-P0PGB-400060 | Strength Calculation for CCW Heat Exchanger | 0 | 2017-12-22 | 118 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1425 | GRT-DS-IP-DT-170527 | GRT-YD00-P0LAC-122508 | [LP Feed Water Pump]_VFD OUTLINE AND DATA SHEET | 0 | 2017-12-22 | 118 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1430 | GRT-DS-IP-DT-170432 | GRT-YT01-P0LBG-111301 | [Silencer]_DATA SHEET FOR SILENCER | 0 | 2017-12-22 | 118 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1431 | GRT-DS-IP-DT-170432 | GRT-YK08-P0LBG-111300 | [Silencer]_OUTLINE DRAWING FOR SILENCER | 0 | 2017-12-22 | 118 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1446 | GRT-DS-IP-DT-170540 | GRT-YF02-P0QC-130006 | [Chemical Dosing System]_CONTROL CONFIGURATION DIAGRAM | 1 | 2017-12-22 | 118 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1426 | GRT-DS-IP-DT-170531 | GRT-YT01-P1H-300062 | [HRSG]_AIRCRAFT WARNING LIGHT DATASHEET & LAYOUT DIAGRAM | 0 | 2017-12-27 | 113 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1427 | GRT-DS-IP-DT-170531 | GRT-XJ00-P1H-300024 | [HRSG]_ERECTION ISOMETRIC DRAWING FOR PIPNG FABRICATION STANDARD | 0 | 2017-12-27 | 113 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1428 | GRT-DS-IP-DT-170531 | GRT-YD00-P1H-300037 | [HRSG]_POWER DISTRIBUTION PANEL DRAWINGS | 0 | 2017-12-27 | 113 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1429 | GRT-DS-IP-DT-170531 | GRT-YF00-P1H-300044 | [HRSG]_SEQUENCES & CONTROLS | 0 | 2017-12-27 | 113 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1444 | GRT-DS-IP-DT-170536 | GRT-YL00-P0MAG-410010 | Condenser_Instrument list and Datasheet for Condenser | 0 | 2017-12-27 | 23 | DEEMED APPROVAL | 2018-01-19 | Close
1445 | GRT-DS-IP-DT-170537 | GRT-CQ02-P0MAG-410011 | Condenser_Instruction Manuals for Erection, Installation, Operation and Maintenance | 0 | 2017-12-27 | 113 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1432 | GRT-DS-IP-DT-170532 | GRT-XJ00-P0LAB-140005 | Piping ISO (Large Bore) - Feedwater | 0 | 2017-12-29 | 46 | DEEMED APPROVAL | 2018-02-13 | Close
1433 | GRT-DS-IP-DT-170532 | GRT-XJ00-P0LBA-140001 | Piping ISO (Large Bore) - HP Steam | 0 | 2017-12-29 | 46 | DEEMED APPROVAL | 2018-02-13 | Close
1434 | GRT-DS-IP-DT-170532 | GRT-XJ00-P0LBA-140002 | Piping ISO (Large Bore) - LP Steam | 0 | 2017-12-29 | 46 | DEEMED APPROVAL | 2018-02-13 | Close
1435 | GRT-DS-IP-DT-170533 | GRT-XK00-P0LBA-144002 | Support DWG (Large Bore) - LP Steam | 0 | 2017-12-29 | 83 | DEEMED APPROVAL | 2018-03-22 | Closed
1436 | GRT-DS-IP-DT-170533 | GRT-XK00-P0LAB-144005 | Support DWG (Large Bore) - Feedwater | 0 | 2017-12-29 | 83 | DEEMED APPROVAL | 2018-03-22 | Closed
1437 | GRT-DS-IP-DT-170533 | GRT-XK00-P0LBA-144001 | Support DWG (Large Bore) - HP Steam | 0 | 2017-12-29 | 83 | DEEMED APPROVAL | 2018-03-22 | Closed
1438 | GRT-DS-IP-DT-170534 | GRT-XK00-P0ZEN-144901 | Outline Drawing for Piping Manual Butterfly Valve | 0 | 2017-12-29 | 82 | DEEMED APPROVAL | 2018-03-21 | Close
1439 | GRT-DS-IP-DT-170534 | GRT-XK00-P0ZEN-144902 | Outline Drawing for Piping HP Manual Casting Valve | 0 | 2017-12-29 | 82 | DEEMED APPROVAL | 2018-03-21 | Close
1440 | GRT-DS-IP-DT-170534 | GRT-XK00-P0ZEN-144904 | Outline Drawing for Piping HP Manual Forging Valve | 0 | 2017-12-29 | 82 | DEEMED APPROVAL | 2018-03-21 | Close
1441 | GRT-DS-IP-DT-170534 | GRT-XK00-P0ZEN-144905 | Outline Drawing for Piping LP Manual Forging Valve | 0 | 2017-12-29 | 82 | DEEMED APPROVAL | 2018-03-21 | Close
1442 | GRT-DS-IP-DT-170534 | GRT-XK00-P0ZEN-144903 | Outline Drawing for Piping LP Manual Casting Valve | 0 | 2017-12-29 | 82 | DEEMED APPROVAL | 2018-03-21 | Close
1443 | GRT-DS-IP-DT-170534 | GRT-XK00-P0ZEN-144900 | Outline Drawing for Piping Manual Ball Valve | 0 | 2017-12-29 | 82 | DEEMED APPROVAL | 2018-03-21 | Close
1447 | GRT-DS-IP-DT-170541 | GRT-CN00-P0ZEN-110102 | [Plant Overall]_PLANT START - UP AND SHUT - DOWN PROCEDURE | B | 2017-12-29 | 11 | DEEMED APPROVAL | 2018-01-09 | Close
1448 | GRT-DS-IP-DT-170542 | GRT-YT10-P0PGB-430130 | Strength Calculation for CCW Expansion Head Tank | 0 | 2017-12-29 | 111 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1449 | GRT-DS-IP-DT-170542 | GRT-YT10-P0LCM-430110 | Strength Calculation for Atmospheric Flash Tank | 0 | 2017-12-29 | 111 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1450 | GRT-DS-IP-DT-170542 | GRT-YT10-P0PGB-430120 | Strength Calculation for CCW Chemical Additive Tank | 0 | 2017-12-29 | 111 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1451 | GRT-DS-IP-DT-170543 | GRT-XJ00-P0QC-143016 | Piping ISO (Small Bore) - Chemical dosing | 0 | 2017-12-29 | 96 | DEEMED APPROVAL | 2018-04-04 | Close
1452 | GRT-DS-IP-DT-170543 | GRT-XJ00-P0LAB-143005 | Piping ISO (Small Bore) - Feedwater | 0 | 2017-12-29 | 101 | DEEMED APPROVAL | 2018-04-09 | Close
1453 | GRT-DS-IP-DT-170543 | GRT-XJ00-P0PGB-143008 | Piping ISO (Small Bore) - CCW | 0 | 2017-12-29 | 87 | DEEMED APPROVAL | 2018-03-26 | Close
1454 | GRT-DS-IP-DT-170543 | GRT-XJ00-P0LCM-143004 | Piping ISO (Small Bore) - Steam drain | 0 | 2017-12-29 | 111 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1455 | GRT-DS-IP-DT-170544 | GRT-DS-ME-DCR-0002 | [STG]_P&I Diagrams |  | 2017-12-29 | 17 | C | 2018-01-15 | Close
1456 | GRT-DS-IP-DT-170545 | GRT-YT10-P0PGB-400050 | Thermal Calculation for CCW Heat Exchanger | 0 | 2017-12-29 | 111 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1458 | GRT-DS-IP-DT-180001 | GRT-YL15-P0MA-200050 | [STG]_Cable list | B | 2018-01-05 | 12 | A | 2018-01-17 | Close
1459 | GRT-DS-IP-DT-180001 | GRT-YK09-P0MA-200035 | [STG]_Instrumentation data sheets | B | 2018-01-05 | 12 | B | 2018-01-17 | Close
1460 | GRT-DS-IP-DT-180002 | GRT-QA00-P0H-040018 | [HRSG]_Welding Consumable Control Procedure for HRSG Piping | 0 | 2018-01-06 | 0 | APPROVED | 2018-01-06 | Close
1461 | GRT-DS-IP-DT-180004 | GRT-XG08-P0MA-200005 | [STG]_P&I Diagrams | 1 | 2018-01-06 | 103 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1462 | GRT-DS-IP-DT-180003 | GRT-VN03-P1H-300013 | [HRSG]_ARRANGEMENT FOR PLATFORM STRUCTURE | 1 | 2018-01-09 | 15 | APPROVED AS NOTED | 2018-01-24 | Close
1463 | GRT-DS-IP-DT-180003 | GRT-VN03-P1H-300010 | [HRSG]_TYPICAL PLATFORM DETAIL FOR STEEL STRUCTURE | 1 | 2018-01-09 | 15 | APPROVED AS NOTED | 2018-01-24 | Close
1464 | GRT-DS-IP-DT-180003 | GRT-DM02-P1H-300005 | [HRSG]_GENERAL NOTE FOR STEEL STRUCTURE | 1 | 2018-01-09 | 15 | APPROVED AS NOTED | 2018-01-24 | Close
1465 | GRT-DS-IP-DT-180005 | GRT-XJ00-P0LCW-143014 | Piping ISO (Small Bore) - Seal Water | 0 | 2018-01-09 | 15 | APPROVED AS NOTED | 2018-01-24 | Close
1466 | GRT-DS-IP-DT-180005 | GRT-XJ00-P0LCA-143006 | Piping ISO (Small Bore) - Condensate | 0 | 2018-01-09 | 15 | APPROVED AS NOTED | 2018-01-24 | Close
1467 | GRT-DS-IP-DT-180006 | GRT-CN00-P0ZEN-110102 | [Plant Overall]_PLANT START - UP AND SHUT - DOWN PROCEDURE | 0 | 2018-01-11 | 13 | APPROVED AS NOTED | 2018-01-24 | Close
1468 | GRT-DS-IP-DT-180007 | GRT-XJ00-P0QUA-143017 | Piping ISO (Small Bore) - Sampling | 0 | 2018-01-17 | 7 | APPROVED AS NOTED | 2018-01-24 | Close
1469 | GRT-DS-IP-DT-180007 | GRT-XJ00-P0QFB-143012 | Piping ISO (Small Bore) - Instrument air | 0 | 2018-01-17 | 7 | APPROVED | 2018-01-24 | Close
1470 | GRT-DS-IP-DT-180009 | GRT-YV02-P0PAH-440005 | Cable Connection/wiring Diagram(for power, control & instrument cable) for CTCS & Debris Filter | 1 | 2018-01-17 | 6 | APPROVED | 2018-01-23 | Close
1471 | GRT-DS-IP-DT-180009 | GRT-YK08-P0PAH-440007 | Outline Drawing for Control Panel of CTCS & Debris Filter | 1 | 2018-01-17 | 6 | APPROVED | 2018-01-23 | Close
1472 | GRT-DS-IP-DT-180009 | GRT-YB03-P0PAH-440006 | Configuration Diagram of Package System for CTCS & Debris Filter | 1 | 2018-01-17 | 6 | APPROVED | 2018-01-23 | Close
1473 | GRT-DS-IP-DT-180010 | GRT-YV02-P0PAH-440055 | CCW HEX Tube Cleaning System_Cable Connection/wiring Diagram(for power, control & instrument cable) | 1 | 2018-01-17 | 6 | APPROVED | 2018-01-23 | Close
1474 | GRT-DS-IP-DT-180010 | GRT-YK08-P0PAH-440057 | CCW HEX Tube Cleaning System_Outline Drawing for Control Panel | 1 | 2018-01-17 | 6 | APPROVED | 2018-01-23 | Close
1475 | GRT-DS-IP-DT-180010 | GRT-YB03-P0PAH-440056 | CCW HEX Tube Cleaning System_Configuration Diagram of Package System | 1 | 2018-01-17 | 6 | APPROVED | 2018-01-23 | Close
1476 | GRT-DS-IP-DT-180012 | GRT-DS-ME-DCR-0004 | [HRSG]_P&I DIAGRAM |  | 2018-01-17 | 12 | B | 2018-01-29 | Close
1477 | GRT-DS-IP-DT-180013 | GRT-UE00-P1H-300007 | [HRSG]_ARRANGEMENT OF CASING & FIELD ERECTION | 1 | 2018-01-17 | 7 | APPROVED | 2018-01-24 | Close
1478 | GRT-DS-IP-DT-180011 | GRT-XS00-P0MAJ-460109 | Vacuum Pump System Description & Control Philosophy | 1 | 2018-01-17 | 7 | C | 2018-01-24 | Close
1479 | GRT-DS-IP-DT-180011 | GRT-XG02-P0MAJ-460201 | P & ID For Water Box Vacuum Pump | 1 | 2018-01-17 | 92 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1480 | GRT-DS-IP-DT-180011 | GRT-XG02-P0MAJ-460101 | P & ID For Condenser Vacuum Pump | 1 | 2018-01-17 | 92 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1481 | GRT-DS-IP-DT-180011 | GRT-CQ02-P0MAJ-460108 | Operation and Maintenance Manuals | 0 | 2018-01-17 | 92 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1482 | GRT-DS-IP-DT-180014 | GRT-CQ02-P0QC-130023 | [Chemical Dosing System]_O&M MANUAL | A | 2018-01-17 | 7 | C | 2018-01-24 | Close
1483 | GRT-DS-IP-DT-180015 | GRT-YL00-P0MAG-410010 | Condenser_Instrument list and Datasheet for Condenser | 1 | 2018-01-19 | 90 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1484 | GRT-DS-IP-DT-180016 | GRT-YL00-P0QC-130007 | [Chemical Dosing System]_INSTRUMENT LIST | 1 | 2018-01-19 | 90 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1485 | GRT-DS-IP-DT-180016 | GRT-YK10-P0QC-130010 | [Chemical Dosing System]_EQUIPMENT ASSEMBLY DRAWING | 1 | 2018-01-19 | 5 | APPROVED | 2018-01-24 | Close
1486 | GRT-DS-IP-DT-180016 | GRT-XS00-P0QC-130003 | [Chemical Dosing System]_SYSTEM DESCRIPTION | 1 | 2018-01-19 | 5 | APPROVED | 2018-01-24 | Close
1487 | GRT-DS-IP-DT-180016 | GRT-XH01-P0QC-130011 | [Chemical Dosing System]_PIPING ARRANGEMENT DRAWING | 1 | 2018-01-19 | 5 | APPROVED | 2018-01-24 | Close
1488 | GRT-DS-IP-DT-180016 | GRT-XG02-P0QC-130001 | [Chemical Dosing System]_P&ID | 1 | 2018-01-19 | 5 | APPROVED | 2018-01-24 | Close
1489 | GRT-DS-IP-DT-180016 | GRT-XB02-P0QC-130009 | [Chemical Dosing System]_FOUNDATION AND LOADING DATA | 1 | 2018-01-19 | 10 | APPROVED AS NOTED | 2018-01-29 | Close
1490 | GRT-DS-IP-DT-180016 | GRT-XA00-P0QC-130002 | [Chemical Dosing System]_GENERAL ARRANGEMENT DRAWING | 1 | 2018-01-19 | 5 | APPROVED | 2018-01-24 | Close
1491 | GRT-DS-IP-DT-180017 | GRT-US02-P0MA-200014 | [STG]_Detail drawings - piping, components and BOM | A | 2018-01-19 | 13 | A | 2018-02-01 | Close
1492 | GRT-DS-IP-DT-180019 | GRT-YK09-P0MA-200028 | [STG]_Measuring and Synchronization | 0 | 2018-01-23 | 8 | C | 2018-01-31 | Close
1493 | GRT-DS-IP-DT-180019 | GRT-YK09-P0MA-200027 | [STG]_Electrical Protections | 0 | 2018-01-23 | 8 | C | 2018-01-31 | Close
1494 | GRT-DS-IP-DT-180019 | GRT-YK09-P0MA-200026 | [STG]_Line and Neutral Cubicles | 0 | 2018-01-23 | 8 | C | 2018-01-31 | Close
1495 | GRT-DS-IP-DT-180018 | GRT-UE00-P0ZEN-100009 | General Arrangement of Steam Turbine Building Section B-B | D | 2018-01-23 | 9 | B | 2018-02-01 | Close
1496 | GRT-DS-IP-DT-180018 | GRT-UE00-P0ZEN-100008 | General Arrangement of Steam Turbine Building Section A-A | D | 2018-01-23 | 9 | B | 2018-02-01 | Close
1497 | GRT-DS-IP-DT-180018 | GRT-UE00-P0ZEN-100007 | General Arrangement of Steam Turbine Building Basement Floor | D | 2018-01-23 | 9 | B | 2018-02-01 | Close
1498 | GRT-DS-IP-DT-180018 | GRT-UE00-P0ZEN-100006 | General Arrangement of Steam Turbine Building Deaerator Floor | D | 2018-01-23 | 9 | B | 2018-02-01 | Close
1499 | GRT-DS-IP-DT-180018 | GRT-UE00-P0ZEN-100005 | General Arrangement of Steam Turbine Building Operating Floor | D | 2018-01-23 | 9 | B | 2018-02-01 | Close
1500 | GRT-DS-IP-DT-180018 | GRT-UE00-P0ZEN-100004 | General Arrangement of Steam Turbine Building Mezzanine Floor | D | 2018-01-23 | 9 | B | 2018-02-01 | Close
1501 | GRT-DS-IP-DT-180018 | GRT-UE00-P0ZEN-100003 | General Arrangement of Steam Turbine Building Ground Floor | D | 2018-01-23 | 9 | B | 2018-02-01 | Close
1502 | GRT-DS-IP-DT-180020 | GRT-XJ00-P0QJA-143009 | Piping ISO (Small Bore) - N2 | 0 | 2018-01-23 | 6 | APPROVED AS NOTED | 2018-01-29 | Close
1503 | GRT-DS-IP-DT-180020 | GRT-XJ00-P0PAB-143007 | Piping ISO (Small Bore) - Aux. cooling water | 0 | 2018-01-23 | 6 | APPROVED AS NOTED | 2018-01-29 | Close
1504 | GRT-DS-IP-DT-180020 | GRT-XJ00-P0MAA-143013 | Piping ISO (Small Bore) - ST Misc. | 0 | 2018-01-23 | 6 | APPROVED AS NOTED | 2018-01-29 | Close
1506 | GRT-DS-IP-DT-180022 | GRT-DS-ME-DCR-0005 | [DCR] Change of Deaerator & Feedwater Storage Tank outline drawing |  | 2018-01-25 | 7 | C | 2018-02-01 | Close
1507 | GRT-DS-IP-DT-180023 | GRT-DS-ME-DCR-0006 | [DCR] Hardware specification addition for VMS |  | 2018-01-25 | 7 | C | 2018-02-01 | Close
1508 | GRT-DS-IP-DT-180024 | GRT-YK08-P0MA-200047 | [STG]_HMI design | B | 2018-01-25 | 7 | C | 2018-02-01 | Close
1509 | GRT-DS-IP-DT-180026 | GRT-DN02-P0PC-830003 | [Commissioning Procedure] Auxiliary Cooling Water System | A | 2018-01-25 | 7 | Return | 2018-02-01 | Close | Becuase IP recipient has not been assigned.
1510 | GRT-DS-IP-DT-180027 | GRT-DN02-P0PG-830004 | [Commissioning Procedure] Closed Cooling Water system | A | 2018-01-25 | 7 | Return | 2018-02-01 | Close | Becuase IP recipient has not been assigned.
1511 | GRT-DS-IP-DT-180028 | GRT-DN02-P0LC-830005 | [Commissioning Procedure] Condensate System | A | 2018-01-25 | 7 | Return | 2018-02-01 | Close | Becuase IP recipient has not been assigned.
1513 | GRT-DS-IP-DT-180029 | GRT-DN02-P0SCA-830007 | [Commissioning Procedure] Compressed Air System | A | 2018-01-29 | 3 | Return | 2018-02-01 | Close | Becuase IP recipient has not been assigned.
1514 | GRT-DS-IP-DT-180030 | GRT-DN02-P0LA-830006 | [Commissioning Procedure] Feedwater System | A | 2018-01-29 | 3 | Return | 2018-02-01 | Close | Becuase IP recipient has not been assigned.
1505 | GRT-DS-IP-DT-180021 | GRT-YK09-P0MA-200025 | [STG]_Excitation system | 0 | 2018-01-31 | 19 | C | 2018-02-19 | Close
1516 | GRT-DS-IP-DT-180032 | GRT-DS-ME-DCR-0007 | [DCR] Addition of 1 x 30% Deaerator LCV |  | 2018-01-31 | 21 | C | 2018-02-21 | Close
1517 | GRT-DS-IP-DT-180033 | GRT-YD00-P0MA-200022 | [STG]_Steam Turbine Auxiliaries outline drawing | B | 2018-01-31 | 13 | DEEMED APPROVAL | 2018-02-13 | Close
1515 | GRT-DS-IP-DT-180031 | GRT-DN02-P0LBG-830002 | [Commissioning Procedure] Auxiliary Steam System | A | 2018-02-01 |  | Return | 2018-02-01 | Close | Becuase IP recipient has not been assigned.
1518 | GRT-DS-IP-DT-180035 | GRT-YL15-P0MA-200050 | [STG]_Cable list | 0 | 2018-02-08 | 12 | APPROVED | 2018-02-20 | Close
1519 | GRT-DS-IP-DT-180035 | GRT-YK09-P0MA-200032 | [STG]_Cabling system | 0 | 2018-02-08 | 12 | APPROVED | 2018-02-20 | Close
1520 | GRT-DS-IP-DT-180035 | GRT-YK09-P0MA-200030 | [STG]_DC motor starter | 0 | 2018-02-08 | 12 | APPROVED AS NOTED | 2018-02-20 | Close
1521 | GRT-DS-IP-DT-180035 | GRT-YK09-P0MA-200029 | [STG]_Frequency converter for turning gear | 0 | 2018-02-08 | 12 | C | 2018-02-20 | Close
1522 | GRT-DS-IP-DT-180035 | GRT-DF04-P0MA-200018 | [STG]_Stress analysis of piping | 0 | 2018-02-08 | 21 | APPROVED | 2018-03-01 | Close
1523 | GRT-DS-IP-DT-180035 | GRT-CA03-P0MA-200004 | [STG]_Steel structures | 0 | 2018-02-08 | 21 | APPROVED | 2018-03-01 | Close
1524 | GRT-DS-IP-DT-180037 | GRT-YK08-P0LAA-420001 | Outline Drawing for Deaerator & Feedwater Storage Tank | 2 | 2018-02-08 | 70 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1525 | GRT-DS-IP-DT-180037 | GRT-CV03-P0LAA-420002 | Datasheet for Deaerator & Feedwater Storage Tank | 1 | 2018-02-08 | 70 | DEEMED APPROVAL | 2018-04-19 | Closed | 5th DRM
1526 | GRT-DS-IP-DT-180038 | GRT-YK08-P0MA-200047 | [STG]_HMI design | 0 | 2018-02-08 | 11 | C | 2018-02-19 | Close
1527 | GRT-DS-IP-DT-180041 | GRT-YD00-P0MA-200022 | [STG]_Steam Turbine Auxiliaries outline drawing | 0 | 2018-02-14 | 6 | APPROVED AS NOTED | 2018-02-20 | Close
1540 | GRT-DS-IP-DT-180044 | GRT-XH01-P1H-300021 | [HRSG]_PIPE SUPPORT DRAWING FOR EXTERNAL PIPING | 1 | 2018-02-14 | 15 | APPROVED | 2018-03-01 | Close
1528 | GRT-DS-IP-DT-180039 | GRT-XJ00-P0SCA-140009 | Piping ISO (Large Bore) - Compressed air | 0 | 2018-02-19 | 10 | APPROVED | 2018-03-01 | Close
1529 | GRT-DS-IP-DT-180039 | GRT-XJ00-P0PGB-140008 | Piping ISO (Large Bore) - CCW | 0 | 2018-02-19 | 10 | APPROVED | 2018-03-01 | Close
1530 | GRT-DS-IP-DT-180039 | GRT-XJ00-P0PAB-140012 | Piping ISO (Large Bore) - Cooling water | 0 | 2018-02-19 | 10 | APPROVED | 2018-03-01 | Close
1531 | GRT-DS-IP-DT-180039 | GRT-XJ00-P0PAB-140007 | Piping ISO (Large Bore) - Aux. cooling water | 0 | 2018-02-19 | 10 | APPROVED | 2018-03-01 | Close
1532 | GRT-DS-IP-DT-180039 | GRT-XJ00-P0MAA-140010 | Piping ISO (Large Bore) - ST Misc. | 0 | 2018-02-19 | 10 | APPROVED | 2018-03-01 | Close
1533 | GRT-DS-IP-DT-180039 | GRT-XJ00-P0LCM-140004 | Piping ISO (Large Bore) - Steam drain | 0 | 2018-02-19 | 10 | APPROVED | 2018-03-01 | Close
1534 | GRT-DS-IP-DT-180039 | GRT-XJ00-P0LCA-140006 | Piping ISO (Large Bore) - Condensate | 0 | 2018-02-19 | 10 | APPROVED | 2018-03-01 | Close
1535 | GRT-DS-IP-DT-180039 | GRT-XJ00-P0LBG-140003 | Piping ISO (Large Bore) - Aux. Steam | 0 | 2018-02-19 | 10 | APPROVED | 2018-03-01 | Close
1536 | GRT-DS-IP-DT-180039 | GRT-XJ00-P0LBA-140002 | Piping ISO (Large Bore) - LP Steam | 1 | 2018-02-19 | 10 | APPROVED | 2018-03-01 | Close
1537 | GRT-DS-IP-DT-180039 | GRT-XJ00-P0LBA-140001 | Piping ISO (Large Bore) - HP Steam | 1 | 2018-02-19 | 10 | APPROVED | 2018-03-01 | Close
1538 | GRT-DS-IP-DT-180039 | GRT-XJ00-P0LAB-140005 | Piping ISO (Large Bore) - Feedwater | 1 | 2018-02-19 | 10 | APPROVED | 2018-03-01 | Close
1539 | GRT-DS-IP-DT-180043 | GRT-YD00-P0PGB-400040 | Outline Drawing for CCW Heat Exchanger | 1 | 2018-02-19 | 10 | NOT APPROVED | 2018-03-01 | Close
1541 | GRT-DS-IP-DT-180045 | GRT-XH01-P0UZT-144522 | [Pipe Rack_Piping]_Piping Arrangement | 1 | 2018-02-21 | 8 | APPROVED | 2018-03-01 | Close
1542 | GRT-DS-IP-DT-180045 | GRT-XH01-P0UTG-144523 | [N2 Gas Shelter_Piping]_Piping Arrangement | 1 | 2018-02-21 | 8 | APPROVED | 2018-03-01 | Close
1543 | GRT-DS-IP-DT-180045 | GRT-XH01-P0UMA-144521 | [Steam Turbine Building_Piping]_Piping Arrangement | 1 | 2018-02-21 | 8 | APPROVED | 2018-03-01 | Close
1544 | GRT-DS-IP-DT-180046 | GRT-YT01-P0QC-130016 | [Chemical Dosing System]_INSTRUMENT DATA SHEET | 1 | 2018-02-27 | 2 | APPROVED | 2018-03-01 | Close
1545 | GRT-DS-IP-DT-180046 | GRT-YT01-P0QC-130015 | [Chemical Dosing System]_VALVE DATA SHEET | 1 | 2018-02-27 | 2 | APPROVED | 2018-03-01 | Close
1546 | GRT-DS-IP-DT-180046 | GRT-YS01-P0QC-130020 | [Chemical Dosing System]_SCHEMATIC DIAGRAM | 1 | 2018-02-27 | 2 | APPROVED AS NOTED | 2018-03-01 | Close
1547 | GRT-DS-IP-DT-180046 | GRT-YK00-P0QC-130022 | [Chemical Dosing System]_HOOK UP DRAWING | 1 | 2018-02-27 | 7 | NOT APPROVED | 2018-03-06 | Close
1548 | GRT-DS-IP-DT-180046 | GRT-YF00-P0QC-130019 | [Chemical Dosing System]_CONTROL LOOP & LOGIC DIAGRAM | 1 | 2018-02-27 | 2 | APPROVED | 2018-03-01 | Close
1549 | GRT-DS-IP-DT-180046 | GRT-YD00-P0QC-130005 | [Chemical Dosing System]_CONTROL PANEL ARRANGEMENT DRAWING | 1 | 2018-02-27 | 7 | APPROVED | 2018-03-06 | Close
1550 | GRT-DS-IP-DT-180046 | GRT-XN00-P0QC-130008 | [Chemical Dosing System]_VALVE LIST | 1 | 2018-02-27 | 2 | APPROVED | 2018-03-01 | Close
1551 | GRT-DS-IP-DT-180047 | GRT-DS-ME-DCR-0008 | [DCR] Hardwire specification addition for VMS |  | 2018-02-27 | 13 | APPROVED AS NOTED | 2018-03-12 | Close
1512 | GRT-DS-IP-DT-180025 | GRT-CQ02-P0LCB-121013 | [Condensate Extraction Pump]_O&M MANUAL | A | 2018-03-01 | 12 | APPROVED | 2018-03-13 | Close
1552 | GRT-DS-IP-DT-180048 | GRT-DN02-P0PC-830003 | [Commissioning Procedure] Auxiliary Cooling Water System | A | 2018-03-01 | 12 | APPROVED AS NOTED | 2018-03-13 | Close
1553 | GRT-DS-IP-DT-180049 | GRT-DN02-P0LBG-830002 | [Commissioning Procedure] Auxiliary Steam System | A | 2018-03-01 | 12 | APPROVED AS NOTED | 2018-03-13 | Close
1554 | GRT-DS-IP-DT-180050 | GRT-DN02-P0PG-830004 | [Commissioning Procedure] Closed Cooling Water system | A | 2018-03-01 | 12 | APPROVED AS NOTED | 2018-03-13 | Close
1555 | GRT-DS-IP-DT-180051 | GRT-DN02-P0QC-830008 | [Commissioning Procedure] Chemical Dosing System | A | 2018-03-01 | 12 | APPROVED AS NOTED | 2018-03-13 | Close
1556 | GRT-DS-IP-DT-180052 | GRT-DN02-P0SCA-830007 | [Commissioning Procedure] Compressed Air System | A | 2018-03-01 | 12 | APPROVED AS NOTED | 2018-03-13 | Close
1557 | GRT-DS-IP-DT-180053 | GRT-DN02-P0LC-830005 | [Commissioning Procedure] Condensate System | A | 2018-03-01 | 12 | APPROVED AS NOTED | 2018-03-13 | Close
1558 | GRT-DS-IP-DT-180054 | GRT-DN02-P0LA-830006 | [Commissioning Procedure] Feedwater System | A | 2018-03-01 | 12 | APPROVED AS NOTED | 2018-03-13 | Close
1559 | GRT-DS-IP-DT-180055 | GRT-DN02-P0LBD-830010 | [Commissioning Procedure] Condesate Filter System | A | 2018-03-01 | 12 | APPROVED AS NOTED | 2018-03-13 | Close
1560 | GRT-DS-IP-DT-180056 | GRT-DN02-P0MAJ-830011 | [Commissioning Procedure] Condenser Vacuum System | A | 2018-03-01 | 12 | APPROVED AS NOTED | 2018-03-13 | Close
1561 | GRT-DS-IP-DT-180057 | GRT-DN02-P0LBA-830001 | [Commissioning Procedure] HP & LP Steam System | A | 2018-03-01 | 12 | APPROVED AS NOTED | 2018-03-13 | Close
1562 | GRT-DS-IP-DT-180058 | GRT-DN02-P1LBF-830013 | [Commissioning Procedure] HRSG Safety Valve Popping Test | A | 2018-03-01 | 12 | APPROVED AS NOTED | 2018-03-13 | Close
1563 | GRT-DS-IP-DT-180059 | GRT-DN02-P0MAJ-830014 | [Commissioning Procedure] Water box vacuum | A | 2018-03-01 | 12 | APPROVED AS NOTED | 2018-03-13 | Close
1564 | GRT-DS-IP-DT-180060 | GRT-DN02-P0QU-830009 | [Commissioning Procedure] Sampling System | A | 2018-03-01 | 12 | APPROVED AS NOTED | 2018-03-13 | Close
1565 | GRT-DS-IP-DT-180062 | GRT-DN02-P0PAH-830015 | [Commissioning Procedure] CTCS / Debris filter | A | 2018-03-01 | 12 | APPROVED AS NOTED | 2018-03-13 | Close
1566 | GRT-DS-IP-DT-180063 | GRT-DS-ME-DCR-0009 | [DCR] Addition of 1 x 30% Deaerator LCV |  | 2018-03-01 | 12 | APPROVED | 2018-03-13 | Close
1567 | GRT-DS-IP-DT-180061 | GRT-DS-ME-DCR-0010 | [DCR] Change of piping insulation specification |  | 2018-03-01 | 18 | C | 2018-03-19 | Close
1568 | GRT-DS-IP-DT-180064 | GRT-YK10-P0MA-200057 | [STG]_Instructions for steam turbine assembly | A | 2018-03-06 | 13 | B | 2018-03-19 | Close
1569 | GRT-DS-IP-DT-180064 | GRT-YK08-P0MA-200047 | [STG]_HMI design | C | 2018-03-06 | 6 | B | 2018-03-12 | Close
1570 | GRT-DS-IP-DT-180065 | GRT-YV02-P0LDB-130052 | [Condensate Filter System]_INTERCONNECTION WIRING DIAGRAM | 1 | 2018-03-12 | 7 | APPROVED | 2018-03-19 | Close
1571 | GRT-DS-IP-DT-180065 | GRT-YS01-P0LDB-130055 | [Condensate Filter System]_SCHEMATIC DIAGRAM | 1 | 2018-03-12 | 7 | APPROVED AS NOTED | 2018-03-19 | Close
1572 | GRT-DS-IP-DT-180065 | GRT-YL22-P0LDB-130053 | [Condensate Filter System]_NAME PLATE DRAWING | 1 | 2018-03-12 | 7 | APPROVED | 2018-03-19 | Close
1573 | GRT-DS-IP-DT-180065 | GRT-YF00-P0LDB-130054 | [Condensate Filter System]_CONTROL LOOP & LOGIC DIAGRAM | 1 | 2018-03-12 | 7 | APPROVED | 2018-03-19 | Close
1574 | GRT-DS-IP-DT-180065 | GRT-YE00-P0LDB-130056 | [Condensate Filter System]_CABLE TRAY LAYOUT DRAWING | 1 | 2018-03-12 | 7 | APPROVED | 2018-03-19 | Close
1575 | GRT-DS-IP-DT-180065 | GRT-YD00-P0LDB-130040 | [Condensate Filter System]_CONTROL PANEL ARRANGEMENT DRAWING | 1 | 2018-03-12 | 7 | APPROVED AS NOTED | 2018-03-19 | Close
1576 | GRT-DS-IP-DT-180065 | GRT-XG02-P0LDB-130036 | [Condensate Filter System]_P&ID | 1 | 2018-03-12 | 7 | APPROVED | 2018-03-19 | Close
1577 | GRT-DS-IP-DT-180065 | GRT-XB02-P0LDB-130044 | [Condensate Filter System]_FOUNDATION AND LOADING DATA | 1 | 2018-03-12 | 7 | APPROVED | 2018-03-19 | Close
1578 | GRT-DS-IP-DT-180065 | GRT-XA00-P0LDB-130037 | [Condensate Filter System]_GENERAL ARRANGEMENT DRAWING | 1 | 2018-03-12 | 7 | APPROVED | 2018-03-19 | Close
1579 | GRT-DS-IP-DT-180066 | GRT-YD00-P0PGB-400040 | Outline Drawing for CCW Heat Exchanger | 2 | 2018-03-12 | 7 | APPROVED AS NOTED | 2018-03-19 | Close
1580 | GRT-DS-IP-DT-180067 | GRT-DS-IC-DCR-0011 | [DCR] Revision and Detail Specification for Drawing of Flow Element |  | 2018-03-15 | 6 | B | 2018-03-21 | Close
1581 | GRT-DS-IP-DT-180069 | GRT-YU03-P0MA-200049 | [STG]_Wiring diagrams, Loop diagrams | B | 2018-03-19 | 8 | C | 2018-03-27 | Close
1582 | GRT-DS-IP-DT-180070 | GRT-YL00-P0MA-200048 | [STG]_I/O list | 0 | 2018-03-19 | 1 | APPROVED | 2018-03-20 | Close
1583 | GRT-DS-IP-DT-180068 | GRT-YR01-P0ZEN-110103 | [Plant Overall]_STEAM BLOWING - OUT PROCEDURE | A | 2018-03-19 | 8 | B | 2018-03-27 | Close
1595 | GRT-DS-IP-DT-180042 | GRT-XK00-P0ZEN-144905 | Outline Drawing for Piping LP Manual Forging Valve | 1 | 2018-03-21 | 6 | APPROVED | 2018-03-27 | Close
1596 | GRT-DS-IP-DT-180042 | GRT-XK00-P0ZEN-144900 | Outline Drawing for Piping Manual Ball Valve | 1 | 2018-03-21 | 6 | APPROVED AS NOTED | 2018-03-27 | Close
1597 | GRT-DS-IP-DT-180042 | GRT-XK00-P0ZEN-144901 | Outline Drawing for Piping Manual Butterfly Valve | 1 | 2018-03-21 | 6 | APPROVED AS NOTED | 2018-03-27 | Close
1598 | GRT-DS-IP-DT-180042 | GRT-XK00-P0ZEN-144902 | Outline Drawing for Piping HP Manual Casting Valve | 1 | 2018-03-21 | 6 | APPROVED | 2018-03-27 | Close
1599 | GRT-DS-IP-DT-180042 | GRT-XK00-P0ZEN-144903 | Outline Drawing for Piping LP Manual Casting Valve | 1 | 2018-03-21 | 6 | APPROVED | 2018-03-27 | Close
1600 | GRT-DS-IP-DT-180042 | GRT-XK00-P0ZEN-144904 | Outline Drawing for Piping HP Manual Forging Valve | 1 | 2018-03-21 | 6 | APPROVED | 2018-03-27 | Close
1601 | GRT-DS-IP-DT-180071 | GRT-YK10-P0QC-130010 | [Chemical Dosing System]_EQUIPMENT ASSEMBLY DRAWING | 2 | 2018-03-21 | 6 | APPROVED | 2018-03-27 | Close
1602 | GRT-DS-IP-DT-180071 | GRT-YK00-P0QC-130022 | [Chemical Dosing System]_HOOK UP DRAWING | 2 | 2018-03-21 | 6 | APPROVED | 2018-03-27 | Close
1603 | GRT-DS-IP-DT-180072 | GRT-CV03-P0ZEN-163704 | [Control Valves(DHI)]_Technical Specification & Datasheet for Control Valve - BOP | 1 | 2018-03-21 | 6 | APPROVED | 2018-03-27 | Close
1604 | GRT-DS-IP-DT-180073 | GRT-YK09-P0MA-200035 | [STG]_Instrumentation data sheets | 0 | 2018-03-21 | 7 | NOT APPROVED | 2018-03-28 | Close
1605 | GRT-DS-IP-DT-180074 | GRT-YL22-P0QC-130018 | [Chemical Dosing System]_NAME PLATE DRAWING | 1 | 2018-03-21 | 6 | APPROVED | 2018-03-27 | Close
1584 | GRT-DS-IP-DT-180040 | GRT-XK00-P0PGB-144008 | Support DWG (Large Bore) - CCW | 0 | 2018-03-22 | 13 | APPROVED AS NOTED | 2018-04-04 | Close
1585 | GRT-DS-IP-DT-180040 | GRT-XK00-P0LBA-144001 | Support DWG (Large Bore) - HP Steam | 1 | 2018-03-22 | 13 | APPROVED | 2018-04-04 | Close
1586 | GRT-DS-IP-DT-180040 | GRT-XK00-P0LBA-144002 | Support DWG (Large Bore) - LP Steam | 1 | 2018-03-22 | 13 | APPROVED | 2018-04-04 | Close
1587 | GRT-DS-IP-DT-180040 | GRT-XK00-P0LBG-144003 | Support DWG (Large Bore) - Aux. Steam | 0 | 2018-03-22 | 13 | APPROVED | 2018-04-04 | Close
1588 | GRT-DS-IP-DT-180040 | GRT-XK00-P0LCA-144006 | Support DWG (Large Bore) - Condensate | 0 | 2018-03-22 | 13 | APPROVED AS NOTED | 2018-04-04 | Close
1589 | GRT-DS-IP-DT-180040 | GRT-XK00-P0LCM-144004 | Support DWG (Large Bore) - Steam drain | 0 | 2018-03-22 | 13 | APPROVED AS NOTED | 2018-04-04 | Close
1590 | GRT-DS-IP-DT-180040 | GRT-XK00-P0MAA-144010 | Support DWG (Large Bore) - ST Misc. | 0 | 2018-03-22 | 13 | APPROVED AS NOTED | 2018-04-04 | Close
1591 | GRT-DS-IP-DT-180040 | GRT-XK00-P0LAB-144005 | Support DWG (Large Bore) - Feedwater | 1 | 2018-03-22 | 13 | APPROVED | 2018-04-04 | Close
1592 | GRT-DS-IP-DT-180040 | GRT-XK00-P0PAB-144012 | Support DWG (Large Bore) - Cooling Water | 0 | 2018-03-22 | 13 | APPROVED | 2018-04-04 | Close
1593 | GRT-DS-IP-DT-180040 | GRT-XK00-P0SCA-144009 | Support DWG (Large Bore) - Compressed air | 0 | 2018-03-22 | 13 | APPROVED AS NOTED | 2018-04-04 | Close
1594 | GRT-DS-IP-DT-180040 | GRT-XK00-P0PAB-144007 | Support DWG (Large Bore) - Aux. cooling water | 0 | 2018-03-22 | 13 | APPROVED | 2018-04-04 | Close
1606 | GRT-DS-IP-DT-180075 | GRT-CQ02-P0QC-130023 | [Chemical Dosing System]_O&M MANUAL | B | 2018-03-22 | 6 | B | 2018-03-28 | Close
1607 | GRT-DS-IP-DT-180076 | GRT-CQ02-P1H-300001 | [HRSG]_INSTALLATION, OPERATION AND MAINTENANCE INSTRUCTION MANUAL | A | 2018-03-27 | 17 | B | 2018-04-13 | Close
1608 | GRT-DS-IP-DT-180077 | GRT-DS-IC-DCR-0012 | [DCR] Revision and Detail Specification for Local Instrument (GRT-CV03-P0ZEN-163702) |  | 2018-03-28 | 9 | A | 2018-04-06 | Close
1609 | GRT-DS-IP-DT-180078 | GRT-CQ02-P0LDB-130058 | [Condensate Filter System]_O&M MANUAL | 0 | 2018-03-28 | 26 | APPROVED | 2018-04-23 | Closed | 5th DRM
1610 | GRT-DS-IP-DT-180079 | GRT-XA00-P0QU-130025 | [Sampling System]_GENERAL ARRANGEMENT DRAWING | 1 | 2018-04-02 | 11 | APPROVED | 2018-04-13 | Close
1611 | GRT-DS-IP-DT-180079 | GRT-CQ02-P0QU-130035 | [Sampling System]_O&M MANUAL | 0 | 2018-04-02 | 11 | APPROVED | 2018-04-13 | Close
1612 | GRT-DS-IP-DT-180080 | GRT-UC08-P0ZEN-100002 | General Arrangement of Powerblock | C | 2018-04-02 | 2 | A | 2018-04-04 | Close
1613 | GRT-DS-IP-DT-180081 | GRT-YK09-P0MA-200051 | STG Operating instructions for the steam turbine and accessories | A | 2018-04-02 | 11 | B | 2018-04-13 | Close
1614 | GRT-DS-IP-DT-180081 | GRT-YK09-P0MA-200053 | STG Summary Operation and Maintenance instructions | A | 2018-04-02 | 9 | B | 2018-04-11 | Close
1615 | GRT-DS-IP-DT-180081 | GRT-YK10-P0MA-200058 | STG Main assembly manual | A | 2018-04-02 | 9 | B | 2018-04-11 | Close
1616 | GRT-DS-IP-DT-180082 | GRT-XJ00-P0PGB-143008 | Piping ISO (Small Bore) - CCW | 1 | 2018-04-02 | 4 | APPROVED | 2018-04-06 | Close
1617 | GRT-DS-IP-DT-180082 | GRT-XJ00-P0SCA-143010 | Piping ISO (Small Bore) - Compressed air | 1 | 2018-04-02 | 4 | APPROVED | 2018-04-06 | Close
1618 | GRT-DS-IP-DT-180085 | GRT-YD00-P0PGB-400040 | OUTLINE DRAWING FOR CCW HEAT EXCHANGER | 3 | 2018-04-02 | 4 | APPROVED | 2018-04-06 | Close
1619 | GRT-DS-IP-DT-180084 | GRT-CV03-P0ZEN-163703 | [Field Instruments(DHI)]_Technical Specification & Datasheet for Flow Element-BOP | 1 | 2018-04-02 | 2 | APPROVED | 2018-04-04 | Close
1620 | GRT-DS-IP-DT-180086 | GRT-XJ00-P0SCB-143011 | Piping ISO (Small Bore) - Service air | 1 | 2018-04-02 | 4 | APPROVED | 2018-04-06 | Close
1621 | GRT-DS-IP-DT-180086 | GRT-XJ00-P0QFB-143012 | Piping ISO (Small Bore) - Instrument air | 1 | 2018-04-02 | 4 | APPROVED | 2018-04-06 | Close
1622 | GRT-DS-IP-DT-180088 | GRT-XJ00-P0LBA-143002 | Piping ISO (Small Bore) - LP Steam | 1 | 2018-04-02 | 4 | APPROVED | 2018-04-06 | Close
1623 | GRT-DS-IP-DT-180088 | GRT-XJ00-P0LBA-143001 | Piping ISO (Small Bore) - HP Steam | 1 | 2018-04-02 | 4 | NOT APPROVED | 2018-04-06 | Close
1624 | GRT-DS-IP-DT-180089 | GRT-XJ00-P0TEM-140011 | Piping ISO (Large Bore) - Steam blowing & flushing | A | 2018-04-04 | 21 | C | 2018-04-25 | Close
1625 | GRT-DS-IP-DT-180091 | GRT-XJ00-P0PAB-143007 | Piping ISO (Small Bore) - Aux. cooling water | 1 | 2018-04-04 | 2 | APPROVED | 2018-04-06 | Close
1626 | GRT-DS-IP-DT-180091 | GRT-XJ00-P0QJA-143009 | Piping ISO (Small Bore) - N2 | 1 | 2018-04-04 | 2 | APPROVED | 2018-04-06 | Close
1627 | GRT-DS-IP-DT-180091 | GRT-XJ00-P0MAA-143013 | Piping ISO (Small Bore) - ST Misc. | 1 | 2018-04-04 | 2 | NOT APPROVED | 2018-04-06 | Close
1629 | GRT-DS-IP-DT-180093 | GRT-XJ00-P0QUA-143017 | Piping ISO (Small Bore) - Sampling | 1 | 2018-04-06 | 19 | APPROVED AS NOTED | 2018-04-25 | Close
1630 | GRT-DS-IP-DT-180093 | GRT-XJ00-P0QC-143016 | Piping ISO (Small Bore) - Chemical dosing | 1 | 2018-04-06 | 19 | APPROVED | 2018-04-25 | Close
1631 | GRT-DS-IP-DT-180094 | GRT-DN02-P1H-830016 | [Commissioning Procedure] CEMS | A | 2018-04-06 | 19 | APPROVED | 2018-04-25 | Close
1632 | GRT-DS-IP-DT-180095 | GRT-DN02-P1H-830012 | [Commissioning Procedure] HRSG | A | 2018-04-06 | 19 | APPROVED | 2018-04-25 | Close
1628 | GRT-DS-IP-DT-180092 | GRT-DS-IC-DCR-0013 | [DCR] Revision for Field Instrument List (GRT-YL00-P0ZEN-163700) |  | 2018-04-11 | 14 | B | 2018-04-25 | Close
1633 | GRT-DS-IP-DT-180096 | GRT-DS-ME-DCR-0014 | [DCR] Bypass Valve & PRDS - Revision for IP comment |  | 2018-04-11 | 14 | B | 2018-04-25 | Close
1640 | GRT-DS-IP-DT-180087 | GRT-XK00-P0LBG-144003 | Support DWG (Large Bore) - Aux. Steam | 1 | 2018-04-11 | 14 | APPROVED | 2018-04-25 | Close
1650 | GRT-DS-IP-DT-180102 | GRT-XS00-P0MAJ-460109 | Vacuum Pump System Description & Control Philosophy | 2 | 2018-04-11 | 14 | APPROVED | 2018-04-25 | Close
1651 | GRT-DS-IP-DT-180103 | GRT-DS-IC-DCR-0016 | [DCR] Change HRSG Instrument installation detail drawing (GRT-YK01-P1H-300048) |  | 2018-04-11 | 14 | C | 2018-04-25 | Close
1652 | GRT-DS-IP-DT-180103 | GRT-DS-ME-DCR-0015 | [DCR] Change HRSG P&ID(GRT-XG02-P1H-300020) |  | 2018-04-11 | 14 | A | 2018-04-25 | Close
1634 | GRT-DS-IP-DT-180083 | GRT-XJ00-P0LCM-140004 | Piping ISO (Large Bore) - Steam drain | 1 | 2018-04-13 | 14 | APPROVED AS NOTED | 2018-04-27 | Close
1635 | GRT-DS-IP-DT-180083 | GRT-XJ00-P0LCA-140006 | Piping ISO (Large Bore) - Condensate | 1 | 2018-04-13 | 14 | NOT APPROVED | 2018-04-27 | Close
1636 | GRT-DS-IP-DT-180083 | GRT-XJ00-P0LBG-140003 | Piping ISO (Large Bore) - Aux. Steam | 1 | 2018-04-13 | 14 | APPROVED | 2018-04-27 | Close
1637 | GRT-DS-IP-DT-180083 | GRT-XJ00-P0LBA-140002 | Piping ISO (Large Bore) - LP Steam | 2 | 2018-04-13 | 14 | APPROVED | 2018-04-27 | Close
1638 | GRT-DS-IP-DT-180083 | GRT-XJ00-P0LBA-140001 | Piping ISO (Large Bore) - HP Steam | 2 | 2018-04-13 | 14 | APPROVED AS NOTED | 2018-04-27 | Close
1639 | GRT-DS-IP-DT-180083 | GRT-XJ00-P0LAB-140005 | Piping ISO (Large Bore) - Feedwater | 2 | 2018-04-13 | 14 | NOT APPROVED | 2018-04-27 | Close
1641 | GRT-DS-IP-DT-180090 | GRT-XK00-P0ZEN-144905 | Outline Drawing for Piping LP Manual Forging Valve | 2 | 2018-04-13 | 14 | APPROVED | 2018-04-27 | Close
1642 | GRT-DS-IP-DT-180090 | GRT-XK00-P0ZEN-144904 | Outline Drawing for Piping HP Manual Forging Valve | 2 | 2018-04-13 | 14 | APPROVED | 2018-04-27 | Close
1643 | GRT-DS-IP-DT-180098 | GRT-XJ00-P0LBG-143003 | Piping ISO (Small Bore) - Aux. Steam | 1 | 2018-04-13 | 12 | APPROVED AS NOTED | 2018-04-25 | Close
1644 | GRT-DS-IP-DT-180098 | GRT-XJ00-P0LAB-143005 | Piping ISO (Small Bore) - Feedwater | 1 | 2018-04-13 | 12 | NOT APPROVED | 2018-04-25 | Close
1645 | GRT-DS-IP-DT-180099 | GRT-XJ00-P0LCA-143006 | Piping ISO (Small Bore) - Condensate | 1 | 2018-04-13 | 14 | APPROVED | 2018-04-27 | Close
1647 | GRT-DS-IP-DT-180097 | GRT-YV02-P0QU-130032 | [Sampling System]_INTERCONNECTION WIRING DIAGRAM | 1 | 2018-04-13 | 12 | APPROVED | 2018-04-25 | Close
1648 | GRT-DS-IP-DT-180097 | GRT-YS01-P0QU-130034 | [Sampling System]_SCHEMATIC DIAGRAM | 1 | 2018-04-13 | 12 | APPROVED | 2018-04-25 | Close
1646 | GRT-DS-IP-DT-180100 | GRT-US02-P0MA-200014 | [STG]_Detail drawings - piping, components and BOM | B | 2018-04-17 | 8 | A | 2018-04-25 | Close
1649 | GRT-DS-IP-DT-180101 | GRT-YU03-P0MA-200043 | [STG]_Control system. Hardware specification | 1 | 2018-04-17 | 8 | APPROVED | 2018-04-25 | Close
1653 | GRT-DS-IP-DT-180104 | GRT-YK10-P0MA-200057 | [STG]_Instructions for steam turbine assembly | 0 | 2018-04-17 | 10 | APPROVED AS NOTED | 2018-04-27 | Close
1654 | GRT-DS-IP-DT-180104 | GRT-YK09-P0MA-200030 | [STG]_DC motor starter | 1 | 2018-04-17 | 10 | APPROVED | 2018-04-27 | Close
1655 | GRT-DS-IP-DT-180104 | GRT-YK09-P0MA-200027 | [STG]_Electrical Protections | 1 | 2018-04-17 | 10 | NOT APPROVED | 2018-04-27 | Close
1656 | GRT-DS-IP-DT-180104 | GRT-YK09-P0MA-200026 | [STG]_Line and Neutral Cubicles | 1 | 2018-04-17 | 10 | NOT APPROVED | 2018-04-27 | Close
1657 | GRT-DS-IP-DT-180105 | GRT-YK10-P0MA-200056 | [STG]_Initial specification for TG installation | 0 | 2018-04-17 | 10 | APPROVED AS NOTED | 2018-04-27 | Close
1658 | GRT-DS-IP-DT-180106 | GRT-DS-IC-DCR-0017 | [DCR] Change HRSG Control valve drawings |  | 2018-04-17 | 8 | A | 2018-04-25 | Close
1659 | GRT-DS-IP-DT-180107 | GRT-CV03-P0ZEN-163702 | [Field Instruments(DHI)]_Technical Specification & Datasheet for Local Instrument - BOP | 1 | 2018-04-20 | 5 | APPROVED | 2018-04-25 | Close
1662 | GRT-DS-IP-DT-180109 | GRT-CQ02-P0LCB-121013 | [Condensate Extraction Pump]_O&M MANUAL | 0 | 2018-04-25 | 9 | APPROVED | 2018-05-04 | Close
1663 | GRT-DS-IP-DT-180110 | GRT-YS01-P0LDB-130055 | [Condensate Filter System]_SCHEMATIC DIAGRAM | 2 | 2018-04-25 | 2 | APPROVED AS NOTED | 2018-04-27 | Close
1664 | GRT-DS-IP-DT-180110 | GRT-YD00-P0LDB-130040 | [Condensate Filter System]_CONTROL PANEL ARRANGEMENT DRAWING | 2 | 2018-04-25 | 2 | APPROVED | 2018-04-27 | Close
1665 | GRT-DS-IP-DT-180111 | GRT-DN02-P0MAV-830018 | [Commissioning Procedure]_STG | A | 2018-04-25 | 9 | B | 2018-05-04 | Close
1666 | GRT-DS-IP-DT-180112 | GRT-YK09-P0MA-200051 | [STG]_Operating instructions for the steam turbine and accessories | 0 | 2018-04-25 | 9 | APPROVED AS NOTED | 2018-05-04 | Close
1667 | GRT-DS-IP-DT-180113 | GRT-YU02-P1H-300066 | [HRSG]_ELECTRICAL SINGLE LINE DIAGRAMS | 1 | 2018-04-25 | 9 | APPROVED | 2018-05-04 | Close
1668 | GRT-DS-IP-DT-180113 | GRT-YT01-P1H-300062 | [HRSG]_AIRCRAFT WARNING LIGHT DATASHEET & LAYOUT DIAGRAM | 1 | 2018-04-25 | 9 | APPROVED AS NOTED | 2018-05-04 | Close
1669 | GRT-DS-IP-DT-180113 | GRT-YL16-P1H-300052 | [HRSG]_CABLE SCHEDULE | 1 | 2018-04-25 | 9 | APPROVED AS NOTED | 2018-05-04 | Close
1670 | GRT-DS-IP-DT-180113 | GRT-YD04-P1H-300042 | [HRSG]_CABLE TRAY & RACEWAY LAYOUT DIAGRAM | 1 | 2018-04-25 | 9 | NOT APPROVED | 2018-05-04 | Close
1671 | GRT-DS-IP-DT-180114 | GRT-CQ02-P0PGB-400070 | Operation and Maintenance Manual for CCW Heat Exchanger | A | 2018-04-25 | 9 | A | 2018-05-04 | Close
1672 | GRT-DS-IP-DT-180115 | GRT-CQ02-P0LAA-420003 | OPERATING AND MAINTENANCE MANUAL FOR DEAERATOR & FEEDWATER STORAGE TANK | A | 2018-04-25 | 2 | B | 2018-04-27 | Close
1673 | GRT-DS-IP-DT-180117 | GRT-YT01-P1H-300061 | [HRSG]_DESH. DATASHEET & DRAWINGS | 1 | 2018-04-27 | 7 | APPROVED | 2018-05-04 | Close
1674 | GRT-DS-IP-DT-180117 | GRT-YT01-P1H-300059 | [HRSG]_MOV DATASHEET & DRAWINGS | 1 | 2018-04-27 | 7 | APPROVED AS NOTED | 2018-05-04 | Close
1675 | GRT-DS-IP-DT-180117 | GRT-YF00-P1H-300044 | [HRSG]_SEQUENCES & CONTROLS | 1 | 2018-04-27 | 7 | NOT APPROVED | 2018-05-04 | Close
1676 | GRT-DS-IP-DT-180118 | GRT-CQ02-P0QC-130023 | [Chemical Dosing System]_O&M MANUAL | 0 | 2018-04-27 | 7 | APPROVED AS NOTED | 2018-05-04 | Close
1660 | GRT-DS-IP-DT-180108 | GRT-YK09-P0MA-200053 | STG Summary Operation and Maintenance instructions | 0 | 2018-05-02 | 2 | APPROVED AS NOTED | 2018-05-04 | Close
1661 | GRT-DS-IP-DT-180108 | GRT-YK10-P0MA-200058 | STG Main assembly manual | 0 | 2018-05-02 | 2 | APPROVED AS NOTED | 2018-05-04 | Close
1677 | GRT-DS-IP-DT-180116 | GRT-DS-ME-DCR-0018 | [DCR] Change of piping insulation specification (GRT-DE00-P0ZEN-144501) |  | 2018-05-02 | 14 | Approved | 2018-05-16 | Close
1678 | GRT-DS-IP-DT-180120 | GRT-US02-P0MA-200014 | [STG]_Detail drawings - piping, components and BOM | 0 | 2018-05-02 | 2 | APPROVED | 2018-05-04 | Close
1679 | GRT-DS-IP-DT-180119 | GRT-YL22-P0PGB-113117 | [CCWP]_OPERATION & MAINTENANCE MANUAL | A | 2018-05-04 | 7 | B | 2018-05-11
1680 | GRT-DS-IP-DT-180119 | GRT-YL22-P0PCC-113017 | [ACWP]_OPERATION & MAINTENANCE MANUAL | A | 2018-05-04 | 7 | B | 2018-05-11
1681 | GRT-DS-IP-DT-180119 | GRT-YD00-P0PGB-113205 | [Blowdown Cooler]_INSTALLATION, OPERATION AND MAINTENANCE MANUAL | A | 2018-05-04 | 7 | B | 2018-05-11
1682 | GRT-DS-IP-DT-180121 | GRT-CQ02-P0SM-123003 | [Crane & Hoist(DHI)]_HOIST_O&M MANUAL FOR HOIST | A | 2018-05-04 | 27 | APPROVED | 2018-05-31
1708 | GRT-DS-IP-DT-180164 | GRT-CQ02-P0LAA-420003 | OPERATING AND MAINTENANCE MANUAL FOR DEAERATOR & FEEDWATER STORAGE TANK | 0 | 2018-05-07 | 2697
1689 | GRT-DS-IP-DT-180150 | GRT-CT00-P0QJA-111011 | [N2 GAS SYSTEM]_OPERATION & MAINTENANCE MANUAL | 0 | 2018-05-07 | 2697
1686 | GRT-DS-IP-DT-180124 | GRT-YT01-P1H-300060 | [HRSG]_CV DATASHEET & DRAWINGS | 1 | 2018-05-11 | 5 | Approved | 2018-05-16 | Close
1687 | GRT-DS-IP-DT-180124 | GRT-XG02-P1H-300020 | [HRSG]_P&I DIAGRAM | 1 | 2018-05-11 | 5 | Approved | 2018-05-16 | Close
1683 | GRT-DS-IP-DT-180122 | GRT-DS-IC-DCR-0019 | [DCR] Revision for Instrument Location Drawing (GRT-YD08-P0UMA-164311) | 0DCR1 | 2018-05-14 | 2 | APROVED | 2018-05-16 | Close
1684 | GRT-DS-IP-DT-180123 | GRT-YK09-P0MA-200059 | [STG]_First commissioning and start-up TG | A | 2018-05-16 | 0 | APPROVED | 2018-05-16 | Close
1685 | GRT-DS-IP-DT-180123 | GRT-YK09-P0MA-200052 | [STG]_Maintenance instructions for the steam turbine and accessories | A | 2018-05-16 | 0 | APPROVED AS NOTED | 2018-05-16 | Close
1688 | GRT-DS-IP-DT-180125 | GRT-DF04-P0ZEN-144512 | [Piping General]_Stress Analysis Report for HP steam system | 1 | 2018-05-16 | 0 | A | 2018-05-16 | Close
1689 | GRT-DS-IP-DT-180126 | GRT-DF04-P0ZEN-144513 | [Piping General]_Stress Analysis Report for LP steam system | 1 | 2018-05-16 | 0 | A | 2018-05-16 | Close
1690 | GRT-DS-IP-DT-180127 | GRT-DF04-P0ZEN-144514 | [Piping General]_Stress Analysis Report for Aux.steam system | 1 | 2018-05-16 | 0 | APPROVED | 2018-05-16 | Close
1691 | GRT-DS-IP-DT-180128 | GRT-DF04-P0ZEN-144515 | [Piping General]_Stress Analysis Report for Feedwater system | 1 | 2018-05-16 | 0 | A | 2018-05-16 | Close
1692 | GRT-DS-IP-DT-180129 | GRT-CQ02-P0PGB-400070 | Operation and Maintenance Manual for CCW Heat Exchanger | 0 | 2018-05-16 | 0 | APPROVED | 2018-05-16 | Close
1693 | GRT-DS-IP-DT-180131 | GRT-YD00-P0PCC-113001 | [DCR] ACWP General Arrangement Drawing Update | 0DCR1 | 2018-05-16 | 8 | APPROVED | 2018-05-24 | Close
1694 | GRT-DS-IP-DT-180131 | GRT-YT01-P0PCC-113002 | [DCR] ACWP Data Sheet Update | 0DCR1 | 2018-05-16 | 8 | APPROVED | 2018-05-24 | Close
1695 | GRT-DS-IP-DT-180132 | GRT-DS-ME-DCR-0022 | [DCR] Revision for LP steam system piping support drawings (GRT-XK00-P0LBA-144002) | 0DCR1 | 2018-05-16 | 15 | C | 2018-05-31 | Close
1696 | GRT-DS-IP-DT-180130 | GRT-YR01-P0ZEN-110107 | [Plant Overall]_STEAM FLUSHING - DIAGRAM | A | 2018-05-16 | 15 | B | 2018-05-31 | Close
1697 | GRT-DS-IP-DT-180135 | GRT-XJ00-P0QJA-143009 | Piping ISO (Small Bore) - N2 | 2 | 2018-05-16 | 0 | APPROVED | 2018-05-16 | Close
1698 | GRT-DS-IP-DT-180135 | GRT-XJ00-P0PAB-143015 | Piping ISO (Small Bore) - Cooling Water | 1 | 2018-05-16 | 0 | APPROVED | 2018-05-16 | Close
1699 | GRT-DS-IP-DT-180135 | GRT-XJ00-P0QUA-143017 | Piping ISO (Small Bore) - Sampling | 2 | 2018-05-16 | 2 | APPROVED AS NOTED | 2018-05-18 | Close
1671 | GRT-DS-IP-DT-180134 | GRT-DS-IC-DCR-0023 | [DCR] Revision for Field Instrument List (GRT-YL00-P0ZEN-163700) |  | 2018-05-16 | 14 | APPROVED | 2018-05-30 | Close
1672 | GRT-DS-IP-DT-180137 | GRT-XJ00-P1H-300024 | [HRSG]_ERECTION ISOMETRIC DRAWING FOR PIPNG FABRICATION STANDARD | 1 | 2018-05-24 | 1 | APPROVED | 2018-05-25 | Close
1673 | GRT-DS-IP-DT-180137 | GRT-YK10-P1H-300050 | [HRSG]_MANUAL VALVE ASSEMBLY DRAWING FOR EXTERNAL PIPING | 1 | 2018-05-24 | 1 | APPROVED | 2018-05-25 | Close
1674 | GRT-DS-IP-DT-180138 | GRT-DS-IC-DCR-0024 | [DCR] Modification of HRSG Instrument installation detail drawing (GRT-YK01-P1H-300048) |  | 2018-05-24 | 12 | APPROVED | 2018-06-05 | Close
1670 | GRT-DS-IP-DT-180136 | GRT-YK10-P0MA-200061 | STG Assembly manual for auxiliary equipment | A | 2018-05-31 | 8 | B | 2018-06-08 | Close
1675 | GRT-DS-IP-DT-180139 | GRT-CT-00-P0QJA-111011 | [N2 GAS SYSTEM]_OPERATION & MAINTENANCE MANUAL | A | 2018-05-31 | 5 | B | 2018-06-05 | Close
1676 | GRT-DS-IP-DT-180139 | GRT-CT00-P0LB-111210 | [Bypass]_OPERATION & MAINTENANCE MANUAL | A | 2018-05-31 | 5 | APPROVED | 2018-06-05 | Close
1677 | GRT-DS-IP-DT-180140 | GRT-YR01-P0ZEN-110103 | [Plant Overall]_STEAM BLOWING - OUT PROCEDURE |  | 2018-05-31 | 38 | B | 2018-07-08 | Close
1678 | GRT-DS-IP-DT-180141 | GRT-UE00-P1H-300006 | [HRSG]_GENERAL ARRANGEMENT | 0DCR1 | 2018-05-31 | 38 | A | 2018-07-08 | Close
1679 | GRT-DS-IP-DT-180143 | GRT-YK09-P0MA-200052 | STG Maintenance Instructions for the steam turbine and accessories | 0 | 2018-06-05 | 33 | B | 2018-07-08 | Close
1680 | GRT-DS-IP-DT-180143 | GRT-YK09-P0MA-200059 | STG First Commissioning and Srat-up TG | 0 | 2018-06-05 | 33 |  | 2018-07-08 | Close
1681 | GRT-DS-IP-DT-180144 | GRT-CQ02-P0SM-123003 | [Crane & Hoist(DHI)]_HOIST_O&M MANUAL FOR HOIST | 0 | 2018-06-05 | 33 | A | 2018-07-08 | Close
1682 | GRT-DS-IP-DT-180145 | GRT-CQ02-POPAH-440104 | Debris Filter_Operation & Maintenance Manual | A | 2018-06-05 | 33 | A | 2018-07-08 | Close
1683 | GRT-DS-IP-DT-180145 | GRT-CQ02-P0PAH440009 | Condenser Tube Cleaning System_Operation & Maintenance Manual | A | 2018-06-05 | 33 | A | 2018-07-08 | Close
1684 | GRT-DS-IP-DT-180146 | GRT-FF03-P0SGA-133001 | [Fire Fighting System] Water Spray System P&ID for STG Enclosure Inside | A | 2018-06-28 | 2645
1685 | GRT-DS-IP-DT-180147 | GRT-DS-IC-DCR-0026 | [DCR] Modification of HRSG CEMS Document |  | 2018-06-28 | 2645
1686 | GRT-DS-IP-DT-180148 | GRT-DS-ME-DCR-0027 | [DCR]Bypass Valve & PRDS - Self Revision (GRT-YS18-P0LB-111103, GRT-YK08-P0LB-111101) |  | 2018-06-28 | 2645
1687 | GRT-DS-IP-DT-180149 | GRT-XJ00-P0TEM-140011 | Piping ISO (Large Bore) - Steam blowing & flushing | B | 2018-06-28 | 2645
1688 | GRT-DS-IP-DT-180151 | GRT-DS- ME-DCR-0028 | Revision for CCW system piping fabrication isometric drawings (GRT-XJ00-P0PGB-140008) |  | 2018-06-28 | 2645
1691 | GRT-DS-IP-DT-180152 | GRT-YL22-P0PCC-113017 | [ACWP]_OPERATION & MAINTENANCE MANUAL | 0 | 2018-06-28 | 1 | APPROVED | 2018-06-29 | Close
1692 | GRT-DS-IP-DT-180152 | GRT-YL22-P0PGB-113117 | [CCWP]_OPERATION & MAINTENANCE[CCWP]_OPERATION & MAINTENANCE MANUAL | 0 | 2018-06-28 | 1 | B | 2018-06-29
1693 | GRT-DS-IP-DT-180152 | GRT-YD00-P0PGB-113205 | [Blowdown Cooler]_INSTALLATION, OPERATION AND MAINTENANCE MANUAL | 0 | 2018-06-28 | 1 | APPROVED | 2018-06-29 | Close
1694 | GRT-DS-IP-DT-180156 | GRT-XK00-P0LBA-144002 | Support DWG (Large Bore) - LP Steam | 2 | 2018-06-28 | 1 | APPROVED | 2018-06-29 | Close
1695 | GRT-DS-IP-DT-180154 | GRT-XJ00-P0PGB-140008 | Piping ISO (Large Bore) - CCW | 1 | 2018-06-28 | #VALUE! | APPROVED | 29/60/2018 | Close
1702 | GRT-DS-IP-DT-180153 | GRT-DS-ME-DCR-0029 | [DCR]Revision and new submission for piping support drawings(GRT-XK00-P0LBA-144001,GRT-XK00-P0LAB-144005,GRT-XK00-P0MAA-144010-GRT-XK00-P0LCA-144006-GRT-XK00-P0LBG-144003) |  | 2018-06-28 | 2645
1690 | GRT-DS-IP-DT-180150 | GRT-CT00-P0LB-111210 | [Bypass]_OPERATION & MAINTENANCE | 0 | 2018-07-05 | 2638
1696 | GRT-DS-IP-DT-180155 | GRT-FF01-P0SGA-133002 | [Fire Fighting System] Water Spray System Plan for STG Enclosure Inside | A | 2018-07-05 | 2638
1700 | GRT-DS-IP-DT-180157 | GRT-CQ02-P0LAC-122022 | [HP Feed Water Pump]_Operation & Maintenance manual | A | 2018-07-05 | 2638
1701 | GRT-DS-IP-DT-180157 | GRT-CQ02-P0LAC-122522 | [LP Feed Water Pump]_Operation & Maintenance manual | A | 2018-07-05 | 2638
1703 | GRT-DS-IP-DT-180158 | GRT-CQ02-P1H-300001 | [HRSG]_INSTALLATION, OPERATION AND MAINTENANCE INSTRUCTION MANUAL | B | 2018-07-05 | 2638
1704 | GRT-DS-IP-DT-180160 | GRT-XN00-P1H-300029 | [HRSG]_VALVE LIST | 1 | 2018-07-05 | 2638
1705 | GRT-DS-IP-DT-180163 | GRT-YK09-P0MA-200032 | STG Commissioning manual for auxiliary equipment | A | 2018-07-05 | 2638
1706 | GRT-DS-IP-DT-180162 | GRT-XK00-P0TEM-144011 | Support DWG (Large Bore) - Steam Blowing & Flushing | A | 2018-07-05 | 2638
1707 | GRT-DS-IP-DT-180165 | GRT-DS-EL-DCR-0030 | Revision of HRSG Power Distribution Panel Document (GRT-YD00-P1H-30037) |  | 2018-07-05 | 2638
1709 | GRT-DS-IP-DT-180166 | GRT-YD00-P1H-300070 | [HRSG]_ERECTION ISOMETRIC DRAWING FOR SMALL BORE PIPING | A | 2018-07-05 | 2638
1710 | GRT-DS-IP-DT-180168 | GRT-YU03-P0MA-200049 | STG Wiring diagram, Loop diagrams | C | 2018-07-05
1711 | GRT-DS-IP-DT-180169 | GRT-CT00-P0QJA-111011 | [N2 GAS SYSTEM]_OPERATION & MAINTENANCE MANUAL | 1 | 2018-07-05
1712 | GRT-DS-IP-DT-180170 | GRT-YK09-P0MA-200029 | STG Frequency converter for turning gear | 1 | 2018-07-05
1697 | GRT-DS-IP-DT-180155 | GRT-XG11-0SGA-133003 | [Fire Fighting System] Single Line Diagram for STG Enclosure Inside | A | 2018-07-06 | 2637
1698 | GRT-DS-IP-DT-180155 | GRT-FF02-P0SGA-133004 | [Fire Fighting System] Detection and Alarm System Equipment Location Plan for STG Enclosure Inside | A | 2018-07-07 | 2636
1699 | GRT-DS-IP-DT-180155 | GRT-FF05-P0SGA-133005 | [Fire Fighting System] Water Spray System Hydralic Calculation | A | 2018-07-08 | 2635
1713
1714
1715
1716
1717
Formulas:
Review Period = IF(ISBLANK([Date2]),TODAY()-[Date],[Date2]-[Date])
Note on F479: 박효은(Hyoeun Park) 두산중공업: rejected
Note on H479: 박효은(Hyoeun Park) 두산중공업: FC 리비전 업 시, Self-revision 포함 협의건.
Note on F480: 박효은(Hyoeun Park) 두산중공업: rejected
Note on H480: 박효은(Hyoeun Park) 두산중공업: FC 리비전 업 시, Self-revision 포함 협의건.
Note on F481: 박효은(Hyoeun Park) 두산중공업: rejected
Note on H481: 박효은(Hyoeun Park) 두산중공업: FC 리비전 업 시, Self-revision 포함 협의건.
Note on F482: 박효은(Hyoeun Park) 두산중공업: rejected
Note on H482: 박효은(Hyoeun Park) 두산중공업: FC 리비전 업 시, Self-revision 포함 협의건.
Note on H489: 박효은(Hyoeun Park) 두산중공업: FC 리비전 업 시, Self-revision 포함 협의건.
Note on H490: 박효은(Hyoeun Park) 두산중공업: FC 리비전 업 시, Self-revision 포함 협의건.
Note on F503: 박효은(Hyoeun Park) 두산중공업: -REMINDER 중 PLNE document control 이 status 보고 예정. (7/20/by email)

## Sheet1 (hidden)
156284
156132