## EDL+VDL
| * Note - EPC will submit on ThinkProject(TP) only the documents listed in the MDL. EPC can not upload any documents on TP unless it is listed in the MDL. - This Engineering MDL will be used as part of Project MDL(Doc No. XXX ) along with the MDLs from other departments. - The Project MDL must be used exclusively for document uploads on TP database, which will serve as the reference for all types of reporting. - The submission dates for documents in TP must be aligned with the Primavera software program of the project schedule. - Since the package vendor has not yet been finalized, the following Vendor Document will be updated as per progress is updated. | [15 empty] | Class 1 Issue For Approval | [11 empty] | Class 2 Issue for Information
No. | P6 Activity ID | Issued by | Document Number | Document Description | Plant | Department | Discipline (DCC A1) | Common document of Rumah and Nairyah | Sub-Discipline | WBS Category | Document Owner (This column will be deleted) | System(APEX Code) | Class / Purpose | IFD/IFC/IFP | Actual Rev Status | Step | Issue for Approval (1st issue) |  |  |  | Approved with comments and issue to Owner |  |  |  | Final approval and issue to Owner (IFC) |  |  |  | IFI |  |  |  | Estimated Manhours | Document Weight | PROGRESS |  |  | TOTAL FLOAT |  | TO be reviewed by |  |  |  | TOP No.
[16 empty] | Cumm | 45% |  |  |  | 80% |  |  |  | 100% |  |  |  | 100% | [5 empty] | Baseline | Forecast | Actual | Baseline | Actual | ACWA PC | OE | NOMAC | CTS
[16 empty] | Partial | 45% |  |  |  | 35% |  |  |  | 20% |  |  |  | 100%
[17 empty] | Baseline | Forecast | Actual | variance | Baseline | Forecast | Actual | variance | Baseline | Forecast | Actual | variance | Baseline | Forecast | Actual | variance | [12 empty] | Engineering Type | Sub Discipline | Work Flow | OE Review (Yes/No) | O&M Review (Yes/NO) | SPPC (Off Taker) Submission (Yes/No) | SPPC (Off Taker) Submission (C1,C2,C3,C4) | For interfacing parties (SEC, Aramco,NWC) | SEC-NG Department | NOC | Open/Combine Cycle (Open/Combine/Partial)
1 | Later | S&L | SAU4005-G000-___-&ABD-00001 | Document Numbering Procedure | A1 | Engineering | A-Overall management | Yes | GENERAL | GENERAL | Common |  | IFA | IFD |  |  | 2025-02-14 |  |  |  | 2025-03-06 |  |  |  | 2025-04-11 | [7 empty] | 1000 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
2 | Later | S&L | SAU4005-G000-___-&ABD-00002 | Plant Tagging Procedure | A1 | Engineering | A-Overall management | Yes | GENERAL | MECHANICAL | Common |  | IFA | IFD |  |  | 2025-02-14 |  |  |  | 2025-03-06 |  |  |  | 2025-04-11 | [7 empty] | 1000 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C1 | NO |  | NO | Common
3 | Later | S&L | SAU4005-G000-___-&ABD-00003 | Document Management Plan | A1 | Engineering | A-Overall management | Yes | GENERAL | GENERAL | Common |  | IFA | IFD |  |  | 2025-02-14 |  |  |  | 2025-03-06 |  |  |  | 2025-04-11 | [7 empty] | 1000 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
4 | Later | S&L | SAU4005-G000-___-&AAB-00338 | Master Deliverable List | A1 | Engineering | A-Overall management | Yes | GENERAL | GENERAL | Common |  | IFA | IFD |  |  | 2025-02-21 |  |  |  | 2025-03-13 |  |  |  | 2025-04-18 | [7 empty] | 1000 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1 | NO |  | NO | Common
5 | Later | S&L | SAU4005-G000-___-&MDB-00004 | Design Criteria Document for Mechanical | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFD |  |  | 2025-03-14 |  |  |  | 2025-04-03 |  |  |  | 2025-05-09 | [7 empty] | 991 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1 | NO |  | NO | Common
6 | Later | S&L | SAU4005-G000-SA_-&MDB-00005 | Design Criteria Document for Heating, Ventilation and Air Conditioning System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-03-05 |  |  |  | 2025-03-31 |  |  |  | 2026-06-04 | [7 empty] | 139 | [13 empty] | WF Transmittal DI-EPC-ACWA |  | YES | NO | C1 | NO |  | NO
7 | Later | S&L | SAU4005-G000-XGA-&MDB-00006 | Design Criteria for Fire Detection & Protection System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-04-04 |  |  |  | 2025-04-24 |  |  |  | 2026-06-04 | [7 empty] | 188 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES
8 | Later | S&L | SAU4005-G000-___-&MDB-00460 | Basic Engineering Design Criteria Document | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFD |  |  | 2025-03-11 |  |  |  | 2025-03-31 |  |  |  | 2025-05-06 | [7 empty] | 910 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
9 | Later | S&L | SAU4005-G000-___-&MDD-00461 | Plant Performance Correction Curve | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | Common |  | IFA | IFD |  |  | 2026-11-25 |  |  |  | 2026-12-15 |  |  |  | 2027-01-20 | [7 empty] | 696 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES
10 | Later | S&L | SAU4005-G000-___-&MDD-00462 | Plant Degradation Curve | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | Common |  | IFA | IFD |  |  | 2026-11-25 |  |  |  | 2026-12-15 |  |  |  | 2027-01-20 | [7 empty] | 411 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES
11 | Later | S&L | SAU4005-G000-H__-&MFB-00007 | Heat Balance Diagram | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-06-17 |  |  |  | 2025-07-07 |  |  |  | 2025-08-12 | [7 empty] | 1943 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1,C2 | NO |  | NO | Common
12 | Later | S&L | SAU4005-G000-G__-&MFB-00008 | Water Balance Diagram | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-03-11 |  |  |  | 2025-03-31 |  |  |  | 2025-12-30 | [7 empty] | 463 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1,C2 | NWC |  | NO | Common
13 | Later | S&L | SAU4005-G000-LA_-&MED-00009 | Calculation for Feed Water System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-07-17 |  |  |  | 2025-08-06 |  |  |  | 2025-09-11 | [7 empty] | 586 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Combine
14 | Later | S&L | SAU4005-G000-QCA-&MED-00011 | Calculation for Power Cycle Chemical Feed System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-04-29 |  |  |  | 2025-05-19 |  |  |  | 2026-02-10 | [7 empty] | 674 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
15 | Later | S&L | SAU4005-G000-LAH-&MED-00012 | Calculation for Steam drain and Vents | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-05-05 |  |  |  | 2025-05-25 |  |  |  | 2025-06-30 | [7 empty] | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Combine
16 | Later | S&L | SAU4005-G000-EG_-&MED-00013 | Calculation for Fuel oil System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-04-15 |  |  |  | 2025-05-05 |  |  |  | 2025-11-19 | [7 empty] | 463 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | ARAMCO |  | NO | Open
17 | Later | S&L | SAU4005-G000-EK_-&MED-00014 | Calculation for Fuel Gas System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-02-13 |  |  |  | 2025-03-05 |  |  |  | 2025-11-15 | [7 empty] | 589 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | ARAMCO |  | NO | Open
18 | Later | S&L | SAU4005-G000-GH_-&MED-00015 | Calculation for Service water system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-06-17 |  |  |  | 2025-07-07 |  |  |  | 2025-12-05 | [7 empty] | 680 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
19 | Later | S&L | SAU4005-G000-GK_-&MED-00016 | Calculation for Potable water system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-07-02 |  |  |  | 2025-07-22 |  |  |  | 2025-12-05 | [7 empty] | 680 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
20 | Later | S&L | SAU4005-G000-QEA-&MED-00017 | Calculation for Compressed Air System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-06-11 |  |  |  | 2025-07-01 |  |  |  | 2025-12-03 | [7 empty] | 680 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
21 | Later | S&L | SAU4005-G000-G__-&MED-00018 | Calculation for Service Water (Treated Waste Water) System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-05-17 |  |  |  | 2025-06-06 |  |  |  | 2025-12-05 | [7 empty] | 680 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
22 | Later | S&L | SAU4005-G000-GHC-&MED-00019 | Calculation for DM Water Distribution system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-05-23 |  |  |  | 2025-06-12 |  |  |  | 2025-12-05 | [7 empty] | 680 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NWC |  | NO | Common
23 | Later | S&L | SAU4005-G000-LBA-&MED-00021 | Calculation for High Pressure (HP) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-13 |  |  |  | 2025-04-02 |  |  |  | 2025-05-08 | [7 empty] | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Combine
24 | Later | S&L | SAU4005-G000-LBB-&MED-00022 | Calculation for Hot Reheat (HRH) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-13 |  |  |  | 2025-04-02 |  |  |  | 2025-05-08 | [7 empty] | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Combine
25 | Later | S&L | SAU4005-G000-LBC-&MED-00023 | Calculation for Cold Reheat (CRH) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-13 |  |  |  | 2025-04-02 |  |  |  | 2025-05-08 | [7 empty] | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Combine
26 | Later | S&L | SAU4005-G000-LBD-&MED-00024 | Calculation for Low Pressure (LP) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-13 |  |  |  | 2025-04-02 |  |  |  | 2025-05-08 | [7 empty] | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Combine
27 | Later | S&L | SAU4005-G000-LBG-&MED-00025 | Calculation for Auxiliary Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-13 |  |  |  | 2025-04-02 |  |  |  | 2025-05-08 | [7 empty] | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Combine
28 | Later | S&L | SAU4005-G000-LC_-&MED-00026 | Calculation for Condensate System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2026-03-12 |  |  |  | 2026-04-01 |  |  |  | 2026-05-07 | [7 empty] | 541 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
29 | Later | S&L | SAU4005-G000-PG_-&MED-00027 | Calculation for Closed Circuit Cooling Water System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-05-08 |  |  |  | 2025-05-28 |  |  |  | 2026-02-14 | [7 empty] | 683 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
30 | Later | S&L | SAU4005-G000-GMA-&MED-00028 | Calculation for Plant Drain System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-10-30 |  |  |  | 2025-11-19 |  |  |  | 2026-01-08 | [7 empty] | 680 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
31 | Later | S&L | SAU4005-G000-QJ_-&MED-00029 | Calculation for Industrial Gas System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-09-02 |  |  |  | 2025-09-22 |  |  |  | 2025-11-05 | [7 empty] | 330 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
32 | Later | S&L | SAU4005-G000-___-&MED-00033 | Insulation calculation | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | Common |  | IFA | IFD |  |  | 2025-11-13 |  |  |  | 2025-12-03 |  |  |  | 2026-01-08 | [7 empty] | 162 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
33 | Later | S&L | SAU4005-G000-SA_-&MED-00360 | HVAC sizing calculation for STG Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-12-05 |  |  |  | 2025-12-25 |  |  |  | 2026-05-11 | [7 empty] | 304 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO
34 | Later | S&L | SAU4005-G000-SA_-&MED-00361 | HVAC sizing calculation for Main Electrical & Control Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-08-06 |  |  |  | 2025-08-26 |  |  |  | 2026-06-05 | [7 empty] | 304 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO
35 | Later | S&L | SAU4005-G000-SA_-&MED-00362 | HVAC sizing calculation for Administration & Social Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-06-27 |  |  |  | 2025-07-17 |  |  |  | 2025-08-21 | [7 empty] | 304 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO
36 | Later | S&L | SAU4005-G000-SA_-&MED-00363 | HVAC sizing calculation for Security and Control center | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2026-06-04 |  |  |  | 2026-06-24 |  |  |  | 2026-07-29 | [7 empty] | 308 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
37 | Later | S&L | SAU4005-G000-SA_-&MED-00364 | HVAC sizing calculation for Workshop and Warehouse Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-08-30 |  |  |  | 2025-09-19 |  |  |  | 2026-05-29 | [7 empty] | 308 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
38 | Later | S&L | SAU4005-G000-SA_-&MED-00365 | HVAC sizing calculation for Water and Effluent treatment System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-10-23 |  |  |  | 2025-11-12 |  |  |  | 2026-02-25 | [7 empty] | 249 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
39 | Later | S&L | SAU4005-G000-SA_-&MED-00367 | HVAC sizing calculation for Unit MV/LV Electrical Switchgear building - 11, 12, 13 | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-08-14 |  |  |  | 2025-09-03 |  |  |  | 2026-05-12 | [7 empty] | 236 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO
40 | Later | S&L | SAU4005-G000-SA_-&MED-00368 | HVAC sizing calculation for GT Package MCC / Control room - 11, 12, 13 | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-08-14 |  |  |  | 2025-09-03 |  |  |  | 2025-10-08 | [7 empty] | 236 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO
41 | Later | S&L | SAU4005-G000-SA_-&MED-00370 | HVAC sizing calculation for BOP Electrical Switchgear Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2026-01-23 |  |  |  | 2026-02-12 |  |  |  | 2026-03-19 | [7 empty] | 236 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
42 | Later | S&L | SAU4005-G000-SA_-&MED-00372 | HVAC sizing calculation for Fire Station Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2026-01-09 |  |  |  | 2026-01-29 |  |  |  | 2026-05-12 | [7 empty] | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
43 | Later | S&L | SAU4005-G000-SA_-&MED-00374 | HVAC sizing calculation for Hydrogen Generation Plant including Electrical Room | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2026-03-14 |  |  |  | 2026-04-03 |  |  |  | 2026-05-08 | [7 empty] | 249 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
44 | Later | S&L | SAU4005-G000-SA_-&MED-00375 | HVAC sizing calculation for Electrical Switchgear Building for Fuel Gas | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2026-04-04 |  |  |  | 2026-04-24 |  |  |  | 2026-05-29 | [7 empty] | 249 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
45 | Later | S&L | SAU4005-G000-SA_-&MED-00376 | HVAC sizing calculation for Search Facility & Visitors Centre | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2026-04-14 |  |  |  | 2026-05-04 |  |  |  | 2026-06-08 | [7 empty] | 249 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
46 | Later | S&L | SAU4005-G000-SA_-&MED-00377 | HVAC sizing calculation for Main Gate House | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2026-04-14 |  |  |  | 2026-05-04 |  |  |  | 2026-02-19 | [7 empty] | 249 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
47 | Later | S&L | SAU4005-G000-SA_-&MED-00380 | HVAC sizing calculation for STG Electrical Switchgear Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2026-05-19 |  |  |  | 2026-06-08 |  |  |  | 2026-07-13 | [7 empty] | 249 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO
48 | Later | S&L | SAU4005-G000-SA_-&MED-00440 | HVAC sizing calculation for Electrical building for Water and Effluent treatment System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2026-04-14 |  |  |  | 2026-05-04 |  |  |  | 2026-06-08 | [7 empty] | 249 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
49 | Later | S&L | SAU4005-G000-___-&MFB-00034 | P&ID for Index, Legends & Symbols | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | Common |  | IFA | IFD |  |  | 2025-04-15 |  |  |  | 2025-05-05 |  |  |  | 2025-06-10 | [7 empty] | 269 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
50 | Later | S&L | SAU4005-G000-EK_-&MFB-00035 | P&ID for Fuel gas system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-06-12 |  |  |  | 2025-07-02 |  |  |  | 2025-12-04 | [7 empty] | 683 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | Aramco |  | NO | Open
51 | Later | S&L | SAU4005-G000-GH_-&MFB-00036 | P&ID for Service water system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-07-24 |  |  |  | 2025-08-13 |  |  |  | 2026-01-02 | [7 empty] | 823 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
52 | Later | S&L | SAU4005-G000-GK_-&MFB-00037 | P&ID for Potable water system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-08-07 |  |  |  | 2025-08-27 |  |  |  | 2026-01-02 | [7 empty] | 810 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
53 | Later | S&L | SAU4005-G000-QEA-&MFB-00038 | P&ID for Compressed Air System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-07-18 |  |  |  | 2025-08-07 |  |  |  | 2025-12-31 | [7 empty] | 852 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
54 | Later | S&L | SAU4005-G000-G__-&MFB-00039 | P&ID for Service Water (Treated Waste Water) System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-05-17 |  |  |  | 2025-06-06 |  |  |  | 2025-12-29 | [7 empty] | 819 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NWC |  | NO | Common
55 | Later | S&L | SAU4005-G000-GHC-&MFB-00040 | P&ID for DM Water Distribution System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-07-07 |  |  |  | 2025-07-27 |  |  |  | 2026-01-02 | [7 empty] | 852 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
56 | Later | S&L | SAU4005-G000-MB_-&MFB-00041 | P&ID for Gas Turbine Interconnecting Piping System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | Common |  | IFA | IFD |  |  | 2025-08-15 |  |  |  | 2025-09-04 |  |  |  | 2025-10-10 | [7 empty] | 862 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
57 | Later | S&L | SAU4005-G000-LBA-&MFB-00043 | P&ID for High Pressure (HP) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-23 |  |  |  | 2025-04-12 |  |  |  | 2025-05-18 | [7 empty] | 547 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Combine
58 | Later | S&L | SAU4005-G000-LBC-&MFB-00044 | P&ID for Cold Reheat (CRH) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-23 |  |  |  | 2025-04-12 |  |  |  | 2025-05-18 | [7 empty] | 547 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Combine
59 | Later | S&L | SAU4005-G000-LBB-&MFB-00045 | P&ID for Hot Reheat (HRH) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-23 |  |  |  | 2025-04-12 |  |  |  | 2025-05-18 | [7 empty] | 547 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Combine
60 | Later | S&L | SAU4005-G000-LBD-&MFB-00046 | P&ID for Low Pressure (LP) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-23 |  |  |  | 2025-04-12 |  |  |  | 2025-05-18 | [7 empty] | 547 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Combine
61 | Later | S&L | SAU4005-G000-LBG-&MFB-00047 | P&ID for Auxiliary Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-23 |  |  |  | 2025-04-12 |  |  |  | 2025-05-18 | [7 empty] | 547 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Combine
62 | Later | S&L | SAU4005-G000-LAB-&MFB-00048 | P&ID for Feed Water System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-16 |  |  |  | 2025-04-05 |  |  |  | 2025-05-11 | [7 empty] | 683 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Combine
63 | Later | S&L | SAU4005-G000-LC_-&MFB-00049 | P&ID for Condensate System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-16 |  |  |  | 2025-04-05 |  |  |  | 2025-05-11 | [7 empty] | 596 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C2 | NO |  | NO | Combine
64 | Later | S&L | SAU4005-G000-PG_-&MFB-00050 | P&ID for Closed Circuit Cooling Water System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-06-20 |  |  |  | 2025-07-10 |  |  |  | 2026-03-10 | [7 empty] | 683 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Common
65 | Later | S&L | SAU4005-G000-QCA-&MFB-00051 | P&ID for Chemical Feed System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-05-08 |  |  |  | 2025-05-28 |  |  |  | 2025-12-15 | [7 empty] | 622 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
66 | Later | S&L | SAU4005-G000-QU_-&MFB-00052 | P&ID for Process Sampling System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-06-27 |  |  |  | 2025-07-17 |  |  |  | 2026-04-18 | [7 empty] | 292 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
67 | Later | S&L | SAU4005-G000-QJA-&MFB-00053 | P&ID for Industrial Gas System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-10-13 |  |  |  | 2025-11-02 |  |  |  | 2026-01-27 | [7 empty] | 292 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
68 | Later | S&L | SAU4005-G000-LBW-&MFB-00054 | P&ID for STG Interconnecting Piping System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-07-29 12:00 |  |  |  | 2025-08-18 12:00 |  |  |  | 2025-09-23 12:00 | [7 empty] | 622 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
69 | Later | S&L | SAU4005-G000-EG_-&MFB-00055 | P&ID for Fuel oil System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-05-15 |  |  |  | 2025-06-04 |  |  |  | 2025-12-11 | [7 empty] | 547 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Open
70 | Later | S&L | SAU4005-G000-LCM-&MFB-00056 | P&ID for Steam Vents & Drains System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-05-05 |  |  |  | 2025-05-25 |  |  |  | 2025-06-30 | [7 empty] | 781 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Combine
71 | Later | S&L | SAU4005-G000-GMA-&MFB-00057 | P&ID for Plant Drain System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-11-28 |  |  |  | 2025-12-18 |  |  |  | 2026-05-04 | [7 empty] | 528 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Common
72 | Later | S&L | SAU4005-G000-SA_-&MFB-00381 | Air Flow Diagram of HVAC system for STG Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFC |  |  | 2025-12-19 |  |  |  | 2026-01-08 |  |  |  | 2026-02-12 | [7 empty] | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
73 | Later | S&L | SAU4005-G000-SA_-&MFB-00382 | Air Flow Diagram of HVAC system for Main Electrical & Control Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFC |  |  | 2025-08-18 |  |  |  | 2025-09-07 |  |  |  | 2025-10-12 | [7 empty] | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
74 | Later | S&L | SAU4005-G000-SA_-&MFB-00383 | Air Flow Diagram of HVAC system for Administration & Social Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFC |  |  | 2025-10-28 |  |  |  | 2025-11-17 |  |  |  | 2025-12-22 | [7 empty] | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
75 | Later | S&L | SAU4005-G000-SA_-&MFB-00384 | Air Flow Diagram of HVAC system for Security and Control center | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFC |  |  | 2026-07-08 |  |  |  | 2026-07-28 |  |  |  | 2026-09-01 | [7 empty] | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
76 | Later | S&L | SAU4005-G000-SA_-&MFB-00385 | Air Flow Diagram of HVAC system for Workshop and Warehouse Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFC |  |  | 2025-09-17 |  |  |  | 2025-10-08 |  |  |  | 2025-11-12 | [7 empty] | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
77 | Later | S&L | SAU4005-G000-SA_-&MFB-00386 | Air Flow Diagram of HVAC system for Water and Effluent treatment System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFC |  |  | 2025-11-10 |  |  |  | 2025-10-13 |  |  |  | 2025-12-22 | [7 empty] | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
78 | Later | S&L | SAU4005-G000-SA_-&MFB-00388 | Air Flow Diagram of HVAC system for Unit MV/LV Electrical Switchgear building - 11, 12, 13 | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFC |  |  | 2025-09-20 |  |  |  | 2025-10-13 |  |  |  | 2025-11-17 | [7 empty] | 211 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
79 | Later | S&L | SAU4005-G000-SA_-&MFB-00389 | Air Flow Diagram of HVAC system for GT Package MCC / Control room - 11, 12, 13 | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFC |  |  | 2025-09-20 |  |  |  | 2025-10-13 |  |  |  | 2025-11-17 | [7 empty] | 211 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
80 | Later | S&L | SAU4005-G000-SA_-&MFB-00391 | Air Flow Diagram of HVAC system for BOP Electrical Switchgear Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFC |  |  | 2026-02-26 |  |  |  | 2026-03-18 |  |  |  | 2026-04-22 | [7 empty] | 211 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
81 | Later | S&L | SAU4005-G000-SA_-&MFB-00393 | Air Flow Diagram of HVAC system for Fire Station Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFC |  |  | 2026-02-17 |  |  |  | 2026-03-09 |  |  |  | 2026-04-13 | [7 empty] | 211 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
82 | Later | S&L | SAU4005-G000-SA_-&MFB-00395 | Air Flow Diagram of HVAC system for Hydrogen Generation Plant including Electrical Room | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFC |  |  | 2026-04-13 |  |  |  | 2026-05-03 |  |  |  | 2026-06-07 | [7 empty] | 211 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
83 | Later | S&L | SAU4005-G000-SA_-&MFB-00396 | Air Flow Diagram of HVAC system for Electrical Switchgear Building for Fuel Gas | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFC |  |  | 2026-05-13 |  |  |  | 2026-06-02 |  |  |  | 2026-07-07 | [7 empty] | 211 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
84 | Later | S&L | SAU4005-G000-SA_-&MFB-00397 | Air Flow Diagram of HVAC system for Search Facility & Visitors Centre | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFC |  |  | 2026-05-14 |  |  |  | 2026-06-03 |  |  |  | 2026-07-08 | [7 empty] | 211 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
85 | Later | S&L | SAU4005-G000-SA_-&MFB-00398 | Air Flow Diagram of HVAC system for Main Gate House | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFC |  |  | 2026-04-14 |  |  |  | 2026-05-04 |  |  |  | 2026-06-08 | [7 empty] | 211 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
86 | Later | S&L | SAU4005-G000-SA_-&MFB-00401 | Air Flow Diagram of HVAC system for STG and Auxiliary Boiler Electrical Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFC |  |  | 2026-06-04 |  |  |  | 2026-06-24 |  |  |  | 2026-07-29 | [7 empty] | 211 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
87 | Later | S&L | SAU4005-G000-SA_-&MFB-00441 | Air Flow Diagram of HVAC system for Electrical building for Water and Effluent treatment System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFC |  |  | 2026-04-10 |  |  |  | 2026-04-30 |  |  |  | 2026-06-04 | [7 empty] | 211 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
88 | Later | S&L | SAU4005-G000-EK_-&MDB-00060 | System Description for Fuel gas system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-07-28 |  |  |  | 2025-08-17 |  |  |  | 2025-12-10 | [7 empty] | 292 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | ARAMCO |  | NO | Open
89 | Later | S&L | SAU4005-G000-EG_-&MDB-00061 | System Description for Fuel oil system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-06-10 |  |  |  | 2025-06-30 |  |  |  | 2025-12-16 | [7 empty] | 308 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | ARAMCO |  | NO | Open
90 | Later | S&L | SAU4005-G000-GH_-&MDB-00062 | System Description for Service water system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-09-02 |  |  |  | 2025-09-22 |  |  |  | 2026-01-08 | [7 empty] | 324 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
91 | Later | S&L | SAU4005-G000-GK_-&MDB-00063 | System Description for Potable water system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-09-19 |  |  |  | 2025-10-13 |  |  |  | 2026-01-08 | [7 empty] | 340 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
92 | Later | S&L | SAU4005-G000-QEA-&MDB-00064 | System Description for Compressed Air System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-08-16 |  |  |  | 2025-09-05 |  |  |  | 2026-01-05 | [7 empty] | 308 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
93 | Later | S&L | SAU4005-G000-G__-&MDB-00065 | System Description for Service Water (Treated Waste Water) System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-08-30 |  |  |  | 2025-09-19 |  |  |  | 2026-01-01 | [7 empty] | 308 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
94 | Later | S&L | SAU4005-G000-GHC-&MDB-00066 | System Description for DM Water Distribution System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-08-04 |  |  |  | 2025-08-24 |  |  |  | 2026-01-08 | [7 empty] | 308 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
95 | Later | S&L | SAU4005-G000-LB_-&MDB-00067 | System Description for Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-23 |  |  |  | 2025-04-12 |  |  |  | 2025-05-18 | [7 empty] | 347 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Combine
96 | Later | S&L | SAU4005-G000-LAB-&MDB-00069 | System Description for Feed Water System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-16 |  |  |  | 2025-04-05 |  |  |  | 2025-05-11 | [7 empty] | 347 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Combine
97 | Later | S&L | SAU4005-G000-LC_-&MDB-00070 | System Description for Condensate System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-16 |  |  |  | 2025-04-05 |  |  |  | 2025-05-11 | [7 empty] | 347 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
98 | Later | S&L | SAU4005-G000-PG_-&MDB-00071 | System Description for Closed Circuit Cooling Water System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-08-05 |  |  |  | 2025-08-25 |  |  |  | 2026-03-16 | [7 empty] | 308 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
99 | Later | S&L | SAU4005-G000-GMA-&MDB-00072 | System Description for Plant Drain System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2026-02-26 |  |  |  | 2026-03-18 |  |  |  | 2026-05-26 | [7 empty] | 308 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Common
100 | Later | S&L | SAU4005-G000-QJA-&MDB-00073 | System Description for Industrial Gas System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-11-25 |  |  |  | 2025-12-15 |  |  |  | 2026-02-23 | [7 empty] | 194 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
101 | Later | S&L | SAU4005-G000-SA_-&MDB-00339 | System Description for HVAC System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2026-06-17 |  |  |  | 2026-07-07 |  |  |  | 2026-08-11 | [7 empty] | 421 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
102 | Later | S&L | SAU4005-G000-___-&BPC-00074 | Equipment list | A1 | Engineering | B-Overall technology | Yes | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFD |  |  | 2025-10-24 |  |  |  | 2025-11-13 |  |  |  | 2025-12-19 | [7 empty] | 674 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
103 | Later | S&L | SAU4005-G000-___-&MPA-00075 | Valve list | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFP |  |  | 2025-11-16 |  |  |  | 2025-12-06 |  |  |  | 2026-01-11 | [7 empty] | 674 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
104 | Later | S&L | SAU4005-G000-___-&MPB-00076 | Specialties list | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFI | IFP | [14 empty] | 2026-09-26 |  |  |  | 674 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
105 | Later | S&L | SAU4005-G000-___-&MMB-00077 | Pipe Line List | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFC |  |  | 2025-11-10 |  |  |  | 2025-11-30 |  |  |  | 2026-01-05 | [7 empty] | 674 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
106 | Later | S&L | SAU4005-G000-___-&BPL-00078 | Terminal Point List | A1 | Engineering | B-Overall technology | No | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFD |  |  | 2025-03-11 |  |  |  | 2025-03-31 |  |  |  | 2025-05-06 | [7 empty] | 463 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C1 | SEC, Aramco,NWC | S1,S2,S3,S4,S5,S6,S7,S8,S9,S10,S11 | NO | Common
107 | Later | S&L | SAU4005-G000-U__-&BTL-00079 | Plot Plan | A1 | Engineering | B-Overall technology | No | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFC |  |  | 2025-02-20 |  |  |  | 2025-03-12 |  |  |  | 2025-04-17 | [7 empty] | 3054 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1 | SEC, Aramco,NWC | S2,S8 | Yes | Common
108 | Later | S&L | SAU4005-G000-UM_-&MLD-00080 | General Arrangement of GT & HRSG Area | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFC |  |  | 2025-03-11 |  |  |  | 2025-03-31 |  |  |  | 2025-05-06 | [7 empty] | 1182 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C2 | NO |  | NO | Common
109 | Later | S&L | SAU4005-G000-UST-&MLH-00082 | General Arrangement of Workshop and Warehouse Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-05-09 |  |  |  | 2025-05-29 |  |  |  | 2026-04-08 | [7 empty] | 1004 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
110 | Later | S&L | SAU4005-G000-USU-&MLD-00083 | General Arrangement of Chemical Storage Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-09-15 |  |  |  | 2025-10-05 |  |  |  | 2026-01-30 | [7 empty] | 991 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
111 | Later | S&L | SAU4005-G000-UEN-&MLD-00084 | General Arrangement of Fuel Gas Area | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-07-22 |  |  |  | 2025-08-11 |  |  |  | 2026-02-05 | [7 empty] | 1092 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Open
112 | Later | S&L | SAU4005-G000-USC-&MLH-00085 | General Arrangement of Air Compressor Shed | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-04-28 |  |  |  | 2025-05-18 |  |  |  | 2025-12-31 | [7 empty] | 991 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
113 | Later | S&L | SAU4005-G000-UTG-&MLH-00086 | General Arrangement of Hydrogen Generation Plant including Electrical Room | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-07-31 |  |  |  | 2025-08-20 |  |  |  | 2026-05-12 | [7 empty] | 709 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
114 | Later | S&L | SAU4005-G000-MA_-&MLH-00087 | General Arrangement of Steam Turbine Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-04-23 |  |  |  | 2025-05-13 |  |  |  | 2026-03-21 | [7 empty] | 897 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C2 | NO |  | NO | Combine
115 | Later | S&L | SAU4005-G000-ULA-&MLD-00088 | General Arrangement of Boiler Feed Pump Area | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFC |  |  | 2025-06-09 |  |  |  | 2025-06-29 |  |  |  | 2025-08-04 | [7 empty] | 998 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Combine
116 | Later | S&L | SAU4005-G000-USG-&MLH-00090 | General Arrangement of Fire Water Pump House | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-05-14 |  |  |  | 2025-06-03 |  |  |  | 2026-03-09 | [7 empty] | 956 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
117 | Later | S&L | SAU4005-G000-URC-&MLD-00340 | General Arrangement of ACC Area | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFC |  |  | 2025-06-04 |  |  |  | 2025-06-24 |  |  |  | 2025-07-30 | [7 empty] | 875 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C2 | NO |  | NO | Combine
118 | Later | S&L | SAU4005-G000-UEM-&MLD-00345 | General Arrangemenmt of Fuel Oil Area | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-07-03 |  |  |  | 2025-07-23 |  |  |  | 2025-12-23 | [7 empty] | 1027 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Open
119 | Later | S&L | SAU4005-G000-UGD-&MTL-00359 | General Arrangement of DM and Service Water Pump Shed | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-05-12 |  |  |  | 2025-06-01 |  |  |  | 2025-07-06 | [7 empty] | 499 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
120 | Later | S&L | SAU4005-G000-UGA-&MTL-00356 | General Arrangement of Service water (Treated wastewater) Area | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-05-10 |  |  |  | 2025-05-30 |  |  |  | 2025-07-04 | [7 empty] | 509 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO
121 | Later | S&L | SAU4005-G000-UTG-&MTL-00357 | General Arrangement of Gas Cylinder Storage Shed | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-05-20 |  |  |  | 2025-06-09 |  |  |  | 2025-07-14 | [7 empty] | 509 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO
122 | Later | S&L | SAU4005-G000-SA_-&MLH-00093 | HVAC Layout for Steam Turbine Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-01-17 |  |  |  | 2026-02-07 |  |  |  | 2026-03-15 | [7 empty] | 437 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
123 | Later | S&L | SAU4005-G000-SA_-&MLH-00094 | HVAC Layout for Main Electrical & Control Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-10-24 |  |  |  | 2025-11-13 |  |  |  | 2026-06-03 | [7 empty] | 434 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
124 | Later | S&L | SAU4005-G000-SA_-&MLH-00096 | HVAC Layout for Administration & Social Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-11-04 |  |  |  | 2025-11-24 |  |  |  | 2025-12-29 | [7 empty] | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
125 | Later | S&L | SAU4005-G000-SA_-&MLH-00097 | HVAC Layout for Security and Control center | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-10-29 |  |  |  | 2025-11-18 |  |  |  | 2025-12-23 | [7 empty] | 288 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
126 | Later | S&L | SAU4005-G000-SA_-&MLH-00098 | HVAC Layout for Workshop and Warehouse Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-11-01 |  |  |  | 2025-11-21 |  |  |  | 2026-05-29 | [7 empty] | 389 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
127 | Later | S&L | SAU4005-G000-SA_-&MLH-00099 | HVAC Layout for Water and Effluent treatment System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-11-24 |  |  |  | 2025-11-25 |  |  |  | 2026-02-23 | [7 empty] | 389 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
128 | Later | S&L | SAU4005-G000-SA_-&MLH-00103 | HVAC Layout for GT Package MCC / Control room - 11, 12, 13 | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-01-23 |  |  |  | 2026-02-12 |  |  |  | 2026-07-15 | [7 empty] | 389 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
129 | Later | S&L | SAU4005-G000-SA_-&MLH-00104 | HVAC Layout for Fuel Gas Electrical Switchgear Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-04-07 |  |  |  | 2026-04-27 |  |  |  | 2026-08-04 | [7 empty] | 223 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
130 | Later | S&L | SAU4005-G000-SA_-&MLH-00106 | HVAC Layout for Hydrogen Generation Plant including Electrical Room | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-02-13 |  |  |  | 2026-03-05 |  |  |  | 2026-06-04 | [7 empty] | 288 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
131 | Later | S&L | SAU4005-G000-SA_-&MLH-00107 | HVAC Layout for Fire Station Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-01-29 |  |  |  | 2026-02-18 |  |  |  | 2026-05-12 | [7 empty] | 165 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
132 | Later | S&L | SAU4005-G000-SA_-&MLH-00109 | HVAC Layout for Unit MV/LV Electrical Switchgear building-11, 12, 13 | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-02-11 |  |  |  | 2026-03-03 |  |  |  | 2026-08-05 | [7 empty] | 288 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
133 | Later | S&L | SAU4005-G000-SA_-&MLH-00110 | HVAC Layout for STG and Auxiliary Boiler Electrical Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-05-15 |  |  |  | 2026-06-04 |  |  |  | 2026-07-09 | [7 empty] | 223 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
134 | Later | S&L | SAU4005-G000-SA_-&MLH-00112 | HVAC Layout for Main Gate House | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-01-14 |  |  |  | 2026-02-03 |  |  |  | 2026-03-10 | [7 empty] | 223 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
135 | Later | S&L | SAU4005-G000-SA_-&MLH-00113 | HVAC Layout for BOP Electrical Switchgear Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-02-02 |  |  |  | 2026-02-22 |  |  |  | 2026-03-29 | [7 empty] | 288 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
136 | Later | S&L | SAU4005-G000-SA_-&MLH-00116 | HVAC Layout for Search Facility & Vendor Center | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-11-06 |  |  |  | 2025-11-26 |  |  |  | 2026-04-03 | [7 empty] | 288 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
137 | Later | S&L | SAU4005-G000-SA_-&MLH-00423 | HVAC Standard Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-07-15 |  |  |  | 2025-08-04 |  |  |  | 2025-09-08 | [7 empty] | 133 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO
138 | Later | S&L | SAU4005-G000-SA_-&MLH-00442 | HVAC Layout for Electrical building for Water and Effluent treatment System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-02-14 |  |  |  | 2026-03-06 |  |  |  | 2026-04-10 | [7 empty] | 249 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
139 | Later | S&L | SAU4005-G000-EK_-&MDA-00119 | LB Isometrics Drawing for Fuel gas system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-02-05 |  |  |  | 1976 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Open
140 | Later | S&L | SAU4005-G000-GH_-&MDA-00120 | LB Isometrics Drawing for Service water system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-04-18 |  |  |  | 1328 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
141 | Later | S&L | SAU4005-G000-GK_-&MDA-00121 | LB Isometrics Drawing for Potable water system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-08 |  |  |  | 1328 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
142 | Later | S&L | SAU4005-G000-QEA-&MDA-00122 | LB Isometrics Drawing for Compressed Air System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-02-14 |  |  |  | 1490 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
143 | Later | S&L | SAU4005-G000-G__-&MDA-00123 | LB Isometrics Drawing for Service Water (Treated Waste Water) System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-05 |  |  |  | 1490 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
144 | Later | S&L | SAU4005-G000-GHC-&MDA-00124 | LB Isometrics Drawing for DM Water Distribution System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-04-24 |  |  |  | 1328 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
145 | Later | S&L | SAU4005-G000-MB_-&MDA-00125 | LB Isometrics Drawing for Gas Turbine Interconnecting Piping System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | Common |  | IFI | IFC | [14 empty] | 2026-04-02 |  |  |  | 1328 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
146 | Later | S&L | SAU4005-G000-LBA-&MDA-00127 | LB Isometrics Drawing for High Pressure (HP) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFA | IFC |  |  | 2026-01-20 |  |  |  | 2026-02-09 |  |  |  | 2026-03-17 | [7 empty] | 2947 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
147 | Later | S&L | SAU4005-G000-LBC-&MDA-00128 | LB Isometrics Drawing for Cold Reheat (CRH) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFA | IFC |  |  | 2026-02-09 |  |  |  | 2026-03-01 |  |  |  | 2026-04-06 | [7 empty] | 2947 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
148 | Later | S&L | SAU4005-G000-LBB-&MDA-00129 | LB Isometrics Drawing for Hot Reheat (HRH) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFA | IFC |  |  | 2026-03-01 |  |  |  | 2026-03-21 |  |  |  | 2026-04-26 | [7 empty] | 3919 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
149 | Later | S&L | SAU4005-G000-LBD-&MDA-00130 | LB Isometrics Drawing for Low Pressure (LP) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFA | IFC |  |  | 2026-03-14 |  |  |  | 2026-04-03 |  |  |  | 2026-05-09 | [7 empty] | 2947 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
150 | Later | S&L | SAU4005-G000-LBG-&MDA-00131 | LB Isometrics Drawing for Auxiliary Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [14 empty] | 2026-03-27 |  |  |  | 2462 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
151 | Later | S&L | SAU4005-G000-LAB-&MDA-00132 | LB Isometrics Drawing for Feed Water System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [14 empty] | 2026-04-04 |  |  |  | 1976 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
152 | Later | S&L | SAU4005-G000-LC_-&MDA-00133 | LB Isometrics Drawing for Condensate System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [14 empty] | 2026-05-19 |  |  |  | 2624 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
153 | Later | S&L | SAU4005-G000-PG_-&MDA-00134 | LB Isometrics Drawing for Closed Circuit Cooling Water System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-04-04 |  |  |  | 1328 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
154 | Later | S&L | SAU4005-G000-QCA-&MDA-00135 | LB Isometrics Drawing for Chemical Feed System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-26 |  |  |  | 1328 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
155 | Later | S&L | SAU4005-G000-EG_-&MDA-00136 | LB Isometrics Drawing for Fuel oil System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-19 |  |  |  | 1490 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
156 | Later | S&L | SAU4005-G000-LBH-&MDA-00137 | LB Isometrics Drawing for Steam Vents & Drains System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [14 empty] | 2026-06-07 |  |  |  | 1652 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
157 | Later | S&L | SAU4005-G000-GMA-&MDA-00138 | LB Isometrics Drawing for Plant Drain System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-12-18 |  |  |  | 1166 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
158 | Later | S&L | SAU4005-G000-MA_-&MDA-00464 | LB Isometrics Drawing for STG Interconnecting System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [14 empty] | 2026-04-30 |  |  |  | 1900 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
159 | Later | S&L | SAU4005-G000-LBA-&MDA-00147 | SB Isometrics Drawing for High Pressure (HP) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [14 empty] | 2026-04-24 |  |  |  | 1166 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
160 | Later | S&L | SAU4005-G000-LBC-&MDA-00148 | SB Isometrics Drawing for Cold Reheat (CRH) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [14 empty] | 2026-05-19 |  |  |  | 1166 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
161 | Later | S&L | SAU4005-G000-LBB-&MDA-00149 | SB Isometrics Drawing for Hot Reheat (HRH) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [14 empty] | 2026-05-30 |  |  |  | 1166 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
162 | Later | S&L | SAU4005-G000-LBD-&MDA-00150 | SB Isometrics Drawing for Low Pressure (LP) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [14 empty] | 2026-06-13 |  |  |  | 1166 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
163 | Later | S&L | SAU4005-G000-LBG-&MDA-00151 | SB Isometrics Drawing for Auxiliary Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [14 empty] | 2026-06-26 |  |  |  | 1166 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
164 | Later | S&L | SAU4005-G000-LAB-&MDA-00152 | SB Isometrics Drawing for Feed Water System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [14 empty] | 2026-06-30 |  |  |  | 1166 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
165 | Later | S&L | SAU4005-G000-LBW-&MDA-00158 | SB Isometrics Drawing for STG Interconnecting System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [14 empty] | 2026-09-30 |  |  |  | 1166 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
166 | Later | S&L | SAU4005-G000-LBH-&MDA-00160 | SB Isometrics Drawing for Steam Vents & Drains System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [14 empty] | 2026-09-05 |  |  |  | 1166 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
167 | Later | S&L | SAU4005-G000-GH_-&MDA-00438 | SB Isometrics Drawing for Service water system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-04-24 |  |  |  | 875 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
168 | Later | S&L | SAU4005-G000-GK_-&MDA-00439 | SB Isometrics Drawing for Potable Water System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-07-06 |  |  |  | 810 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
169 | Later | S&L | SAU4005-G000-EK_-&MDA-00444 | SB Isometrics Drawing for Fuel gas system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-05-13 |  |  |  | 907 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
170 | Later | S&L | SAU4005-G000-QEA-&MDA-00445 | SB Isometrics Drawing for Compressed Air System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-05-06 |  |  |  | 891 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
171 | Later | S&L | SAU4005-G000-G__-&MDA-00446 | SB Isometrics Drawing for Service Water (Treated Waste Water) System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-07-03 |  |  |  | 777 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
172 | Later | S&L | SAU4005-G000-GHC-&MDA-00447 | SB Isometrics Drawing for DM Water Distribution System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-05-25 |  |  |  | 891 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
173 | Later | S&L | SAU4005-G000-MB_-&MDA-00448 | SB Isometrics Drawing for Gas Turbine Interconnecting Piping System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | Common |  | IFI | IFC | [14 empty] | 2026-04-16 |  |  |  | 875 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
174 | Later | S&L | SAU4005-G000-GMA-&MDA-00449 | SB Isometrics Drawing for Plant Drain System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [14 empty] | 2027-01-19 |  |  |  | 810 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
175 | Later | S&L | SAU4005-G000-PG_-&MDA-00450 | SB Isometrics Drawing for Closed Circuit Cooling Water System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-26 |  |  |  | 794 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
176 | Later | S&L | SAU4005-G000-EG_-&MDA-00451 | SB Isometrics Drawing for Fuel oil System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-02-14 |  |  |  | 810 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
177 | Later | S&L | SAU4005-G000-QCA-&MDA-00452 | SB Isometrics Drawing for Chemical Feed System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-05-15 |  |  |  | 680 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
178 | Later | S&L | SAU4005-G000-LC_-&MDA-00453 | SB Isometrics Drawing for Condensate System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-05-13 |  |  |  | 680 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Combine
179 | Later | S&L | SAU4005-G000-LBA-&MDD-00162 | Stress Analysis for High Pressure (HP) and Cold Reheat (CRH) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | DOOSAN |  | IFA | IFD |  |  | 2026-02-19 |  |  |  | 2026-03-11 |  |  |  | 2026-04-16 | [7 empty] | 3919 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
180 | Later | S&L | SAU4005-G000-LBB-&MDD-00164 | Stress Analysis for Hot Reheat (HRH) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | DOOSAN |  | IFA | IFD |  |  | 2026-03-29 |  |  |  | 2026-04-18 |  |  |  | 2026-05-24 | [7 empty] | 3595 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
181 | Later | S&L | SAU4005-G000-LBD-&MDD-00165 | Stress Analysis for Low Pressure (LP) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | DOOSAN |  | IFA | IFD |  |  | 2026-04-11 |  |  |  | 2026-05-01 |  |  |  | 2026-06-06 | [7 empty] | 2947 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
182 | Later | S&L | SAU4005-G000-LBG-&MDD-00166 | Stress Analysis for Auxiliary Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | DOOSAN |  | IFA | IFD |  |  | 2025-10-29 16:30 |  |  |  | 2025-11-18 16:30 |  |  |  | 2025-12-24 16:30 | [7 empty] | 2624 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
183 | Later | S&L | SAU4005-G000-LAB-&MDD-00167 | Stress Analysis for Feed Water System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | DOOSAN |  | IFA | IFD |  |  | 2026-05-03 |  |  |  | 2026-05-23 |  |  |  | 2026-06-28 | [7 empty] | 3109 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
184 | Later | S&L | SAU4005-G000-LBH-&MDD-00169 | Stress Analysis for STG Drains & Vents System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | DOOSAN |  | IFA | IFD |  |  | 2026-07-25 |  |  |  | 2026-08-14 |  |  |  | 2026-09-19 | [7 empty] | 2624 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
185 | Later | S&L | SAU4005-G000-EK_-&MDD-00170 | Stress Analysis for Fuel Gas system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFD |  |  | 2026-03-03 |  |  |  | 2026-03-23 |  |  |  | 2026-04-27 | [7 empty] | 1004 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
186 | Later | S&L | SAU4005-G000-EK_-&MDA-00171 | Piping Support Schedule for Fuel gas system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFD | [14 empty] | 2026-03-10 |  |  |  | 1004 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
187 | Later | S&L | SAU4005-G000-GH_-&MDA-00172 | Piping Support Schedule for Service water system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFD | [14 empty] | 2026-06-05 |  |  |  | 842 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
188 | Later | S&L | SAU4005-G000-GK_-&MDA-00173 | Piping Support Schedule for Potable water system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFD | [14 empty] | 2026-07-13 |  |  |  | 842 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
189 | Later | S&L | SAU4005-G000-QEA-&MDA-00174 | Piping Support Schedule for Compressed Air System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFD | [14 empty] | 2026-04-02 |  |  |  | 842 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
190 | Later | S&L | SAU4005-G000-G__-&MDA-00175 | Piping Support Schedule for Service water (Treated Waste Water) System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFD | [14 empty] | 2026-07-03 |  |  |  | 680 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
191 | Later | S&L | SAU4005-G000-GHC-&MDA-00176 | Piping Support Schedule for DM Water Distribution System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFD | [14 empty] | 2026-05-16 |  |  |  | 842 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
192 | Later | S&L | SAU4005-G000-LBA-&MDA-00178 | Piping Support for High Pressure (HP) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFA | IFC |  |  | 2026-07-25 |  |  |  | 2026-08-14 |  |  |  | 2026-09-19 | [7 empty] | 1490 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
193 | Later | S&L | SAU4005-G000-LBC-&MDA-00179 | Piping Support for Cold Reheat (CRH) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFA | IFC |  |  | 2026-07-25 |  |  |  | 2026-08-14 |  |  |  | 2026-09-19 | [7 empty] | 1490 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
194 | Later | S&L | SAU4005-G000-LBB-&MDA-00180 | Piping Support for Hot Reheat (HRH) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFA | IFC |  |  | 2026-07-25 |  |  |  | 2026-08-14 |  |  |  | 2026-09-19 | [7 empty] | 1490 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
195 | Later | S&L | SAU4005-G000-LBD-&MDA-00181 | Piping Support for Low Pressure (LP) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFA | IFC |  |  | 2026-08-03 |  |  |  | 2026-08-23 |  |  |  | 2026-09-28 | [7 empty] | 1490 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
196 | Later | S&L | SAU4005-G000-LBG-&MDA-00182 | Piping Support for Auxiliary Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [14 empty] | 2026-08-18 |  |  |  | 1328 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
197 | Later | S&L | SAU4005-G000-LAB-&MDA-00183 | Piping Support for Feed Water System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [14 empty] | 2026-08-18 |  |  |  | 1328 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
198 | Later | S&L | SAU4005-G000-LC_-&MDA-00184 | Piping Support Schedule for Condensate System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [14 empty] | 2026-09-03 |  |  |  | 1166 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
199 | Later | S&L | SAU4005-G000-EG_-&MDA-00185 | Piping Support Schedule for Fuel oil System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFD | [14 empty] | 2026-04-08 |  |  |  | 680 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
200 | Later | S&L | SAU4005-G000-PG_-&MDA-00186 | Piping Support Schedule for Closed Circuit Cooling Water System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFD | [14 empty] | 2026-04-24 |  |  |  | 1004 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
201 | Later | S&L | SAU4005-G000-QC_-&MDA-00187 | Piping Support Schedule for Chemical Feed System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFD | [14 empty] | 2026-09-04 |  |  |  | 680 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
202 | Later | S&L | SAU4005-G000-QJA-&MDA-00189 | Piping Support Schedule for Industrial Gas System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFD | [14 empty] | 2026-09-24 |  |  |  | 680 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
203 | Later | S&L | SAU4005-G000-LBW-&MDA-00190 | Piping Support Schedule for STG Interconnecting System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [14 empty] | 2026-11-08 |  |  |  | 1166 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
204 | Later | S&L | SAU4005-G000-LBH-&MDA-00191 | Piping Support for Steam Vents & Drains System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [14 empty] | 2026-11-15 |  |  |  | 1166 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
205 | Later | S&L | SAU4005-G000-GMA-&MDA-00192 | Piping Support Schedule for Plant Drain System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFD | [14 empty] | 2027-01-05 |  |  |  | 680 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
206 | Later | S&L | SAU4005-G000-MB_-&MDA-00465 | Piping Support Schedule for GTG Interconnecting System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | Common |  | IFI | IFC | [14 empty] | 2026-11-20 |  |  |  | 1900 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
207 | Later | S&L | SAU4005-G000-___-&BTA-00202 | 3D Model Concept | A1 | Engineering | B-Overall technology | Yes | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFD |  |  | 2025-03-27 |  |  |  | 2025-04-16 |  |  |  | 2025-05-22 | [7 empty] | 515 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C1 | NO |  | NO | Common
208 | Later | S&L | SAU4005-G000-___-&BTB-00354 | 3D Model | A1 | Engineering | B-Overall technology | No | PIPING&PLANT DESIGN | PIPING | Common |  | IFA | IFD |  |  | 2025-05-12 |  |  |  | 2025-06-01 |  |  |  | 2025-07-07 | [7 empty] | 3600 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C3 | NO |  | NO | Common
209 | Later | S&L | SAU4005-G000-___-&BDD-00203 | Hazardous Area Classification | A1 | Engineering | B-Overall technology | Yes | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFD |  |  | 2026-07-29 |  |  |  | 2026-08-18 |  |  |  | 2026-09-23 | [7 empty] | 1338 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
210 | Later | S&L | SAU4005-G000-___-&BDC-00204 | Plant Operation and Control Philosophy | A1 | Engineering | B-Overall technology | Yes | MECH&PROCESS&WTP | PROCESS | Common |  | IFA | IFD |  |  | 2026-08-29 |  |  |  | 2026-09-18 |  |  |  | 2026-10-24 | [7 empty] | 1607 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Common
211 | Later | S&L | SAU4005-G000-___-&MDD-00205 | Piping and Valve Design Table Report | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | Common |  | IFA | IFD |  |  | 2025-07-30 |  |  |  | 2025-08-19 |  |  |  | 2025-09-24 | [7 empty] | 1315 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
212 | Later | S&L | SAU4005-G000-___-&MTA-00207 | Piping and Support General notes | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | Common |  | IFI | IFC | [14 empty] | 2026-07-25 |  |  |  | 1156 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
213 | Later | S&L | SAU4005-G000-MB_-&MEC-00294 | Technical Specifications for Gas Turbine, Generator & Auxiliaries | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | DOOSAN |  | IFI | IFP | [14 empty] | 2025-05-19 |  |  |  | 2000 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | YES
214 | Later | S&L | SAU4005-G000-MA_-&MEC-00208 | Technical Specifications for Steam Turbine and Generator | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | DOOSAN |  | IFI | IFP | [14 empty] | 2025-07-15 |  |  |  | 2000 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | YES
215 | Later | S&L | SAU4005-G000-HA_-&MEC-00209 | Technical Specifications for HRSG and Bypass Stack | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | DOOSAN |  | IFI | IFP | [14 empty] | 2025-05-06 |  |  |  | 2000 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | YES
216 | Later | S&L | SAU4005-G000-___-&MEC-00210 | Technical Specifications for Misc. sump pumps | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-12-18 |  |  |  | 2026-01-07 |  |  |  | 2026-02-11 | [7 empty] | 635 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO
217 | Later | S&L | SAU4005-G000-MAN-&MEC-00211 | Technical Specifications for Steam Bypass system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | DOOSAN |  | IFA | IFP |  |  | 2025-08-08 17:30 |  |  |  | 2025-08-28 17:30 |  |  |  | 2025-10-03 17:30 | [7 empty] | 428 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
218 | Later | S&L | SAU4005-G000-___-&MEC-00212 | Technical Specifications for GRP Piping | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFA | IFP |  |  | 2025-07-24 |  |  |  | 2025-08-13 |  |  |  | 2025-09-17 | [7 empty] | 619 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
219 | Later | S&L | SAU4005-G000-QJ_-&MEC-00213 | Technical Specifications for Industrial Gas System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-09-04 |  |  |  | 2025-09-24 |  |  |  | 2025-10-29 | [7 empty] | 256 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
220 | Later | S&L | SAU4005-G000-QJ_-&MEC-00214 | Technical Specifications for Hydrogen Generation Plant | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-07-09 |  |  |  | 2025-07-29 |  |  |  | 2025-09-02 | [7 empty] | 256 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
221 | Later | S&L | SAU4005-G000-___-&MEC-00215 | Technical Specifications for Field Fabricated Tank | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-05-21 |  |  |  | 2025-06-10 |  |  |  | 2025-07-15 | [7 empty] | 602 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
222 | Later | S&L | SAU4005-G000-___-&MEC-00216 | Technical Specifications for Shop fabricated Tank | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFP |  |  | 2025-08-21 17:30 |  |  |  | 2025-09-10 17:30 |  |  |  | 2025-10-16 17:30 | [7 empty] | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
223 | Later | S&L | SAU4005-G000-G__-&MEC-00217 | Technical Specifications for Water and Effluent Treatment System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-05-12 |  |  |  | 2025-06-01 |  |  |  | 2025-07-06 | [7 empty] | 1033 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NWC |  | NO | Common
224 | Later | S&L | SAU4005-G000-EK_-&MEC-00219 | Technical Specifications for Fuel Gas Conditioning System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-02-25 |  |  |  | 2025-03-17 |  |  |  | 2025-04-21 | [7 empty] | 476 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | ARAMCO |  | NO | Open
225 | Later | S&L | SAU4005-G000-PG_-&MEC-00220 | Technical Specifications for CCCW heat exchanger (Fin Fan Cooler) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-05-22 |  |  |  | 2025-06-11 |  |  |  | 2025-07-16 | [7 empty] | 683 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
226 | Later | S&L | SAU4005-G000-___-&MEC-00223 | Technical Specifications for Miscellaneous Horizontal pump | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFP |  |  | 2025-06-25 |  |  |  | 2025-07-15 |  |  |  | 2025-08-20 | [7 empty] | 528 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
227 | Later | S&L | SAU4005-G000-___-&MEC-00224 | Technical Specifications for Miscellaneous Vertical pump | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-07-30 |  |  |  | 2025-08-19 |  |  |  | 2025-09-23 | [7 empty] | 528 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
228 | Later | S&L | SAU4005-G000-STG-&MEC-00225 | Technical Specifications for Laboratory Equipment | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2026-03-11 |  |  |  | 2026-03-31 |  |  |  | 2026-05-05 | [7 empty] | 188 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
229 | Later | S&L | SAU4005-G000-SM_-&MEC-00226 | Technical Specifications for Cranes & Hoists | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-10-14 |  |  |  | 2025-11-03 |  |  |  | 2025-12-08 | [7 empty] | 217 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
230 | Later | S&L | SAU4005-G000-QEA-&MEC-00228 | Technical Specifications for Compressed Air System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-06-06 |  |  |  | 2025-06-26 |  |  |  | 2025-07-31 | [7 empty] | 761 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
231 | Later | S&L | SAU4005-G000-EK_-&MEC-00229 | Technical Specifications for Fuel Gas Compressors | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-03-04 |  |  |  | 2025-03-24 |  |  |  | 2025-04-28 | [7 empty] | 641 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C1,C2 | NO |  | NO | Open
232 | Later | S&L | SAU4005-G000-L__-&MEC-00230 | Technical Specifications for Power Cycle Pumps (BFP,CEP) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | DOOSAN |  | IFA | IFP |  |  | 2025-02-27 |  |  |  | 2025-03-19 |  |  |  | 2025-04-24 | [7 empty] | 1555 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
233 | Later | S&L | SAU4005-G000-QC_-&MEC-00232 | Technical Specifications for Chemical Feed System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-07-17 |  |  |  | 2025-08-06 |  |  |  | 2025-09-10 | [7 empty] | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
234 | Later | S&L | SAU4005-G000-___-&MEC-00234 | Technical Specifications for Safety valve | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFP |  |  | 2025-11-13 11:30 |  |  |  | 2025-12-03 11:30 |  |  |  | 2026-01-08 11:30 | [7 empty] | 113 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
235 | Later | S&L | SAU4005-G000-QH_-&MEC-00235 | Technical Specifications for Auxiliary Boiler | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-05-17 |  |  |  | 2025-06-06 |  |  |  | 2025-07-11 | [7 empty] | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
236 | Later | S&L | SAU4005-G000-SA_-&MEC-00236 | Technical Specifications for HVAC System - Air Conditioner Units | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-10-27 |  |  |  | 2025-11-16 |  |  |  | 2025-12-21 | [7 empty] | 525 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
237 | Later | S&L | SAU4005-G000-SA_-&MEC-00237 | Technical Specifications for HVAC System Fans | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-10-24 |  |  |  | 2025-11-13 |  |  |  | 2025-12-18 | [7 empty] | 525 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
238 | Later | S&L | SAU4005-G000-SA_-&MEC-00238 | Technical Specifications for HVAC Ducting and Accessories | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2026-01-23 |  |  |  | 2026-02-12 |  |  |  | 2026-03-19 | [7 empty] | 301 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
239 | Later | S&L | SAU4005-G000-___-&MEC-00239 | Technical Specifications for Pipe Hangers & Supports | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFP |  |  | 2025-07-07 |  |  |  | 2025-07-27 |  |  |  | 2025-09-01 | [7 empty] | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
240 | Later | S&L | SAU4005-G000-___-&MEC-00240 | Technical Specifications for Power Cycle Valves | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | DOOSAN |  | IFA | IFP |  |  | 2025-07-27 06:00 |  |  |  | 2025-08-16 06:00 |  |  |  | 2025-09-21 06:00 | [7 empty] | 674 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
241 | Later | S&L | SAU4005-G000-___-&MEC-00241 | Technical Specifications for Low Pressure Valves | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFP |  |  | 2025-11-18 17:30 |  |  |  | 2025-12-08 17:30 |  |  |  | 2026-01-13 17:30 | [7 empty] | 609 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
242 | Later | S&L | SAU4005-G000-___-&MEC-00242 | Technical Specifications for Butterfly Valves | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-12-01 |  |  |  | 2025-12-21 |  |  |  | 2026-01-25 | [7 empty] | 609 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
243 | Later | S&L | SAU4005-G000-___-&MEC-00243 | Technical Specifications for Piping Specialties | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | PIPING&PLANT DESIGN | PIPING | Common |  | IFA | IFP |  |  | 2025-09-26 06:00 |  |  |  | 2025-10-16 06:00 |  |  |  | 2025-11-21 06:00 | [7 empty] | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
244 | Later | S&L | SAU4005-G000-GR_-&MEC-00244 | Technical Specifications for Sewage Treatment Plant | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2026-05-05 |  |  |  | 2026-05-25 |  |  |  | 2026-06-29 | [7 empty] | 256 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
245 | Later | S&L | SAU4005-G000-GNB-&MEC-00245 | Technical Specifications for Oil Water Separator | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-11-05 |  |  |  | 2025-11-25 |  |  |  | 2025-12-30 | [7 empty] | 227 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
246 | Later | S&L | SAU4005-G000-___-&MEC-00247 | Technical Specifications for Alloy Piping | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | PIPING&PLANT DESIGN | PIPING | Common |  | IFA | IFP |  |  | 2026-03-22 |  |  |  | 2026-04-11 |  |  |  | 2026-05-17 | [7 empty] | 194 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
247 | Later | S&L | SAU4005-G000-XTA-&MEC-00248 | Technical Specifications for Painting and Coating | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFP |  |  | 2025-02-16 |  |  |  | 2025-03-08 |  |  |  | 2025-04-13 | [7 empty] | 547 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
248 | Later | S&L | SAU4005-G000-___-&MEC-00249 | Technical Specifications for Thermal Insulation | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFP |  |  | 2025-12-17 15:30 |  |  |  | 2026-01-06 15:30 |  |  |  | 2026-02-11 15:30 | [7 empty] | 194 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
249 | Later | S&L | SAU4005-G000-PA_-&MEC-00251 | Technical Specifications for Air Cooled Condenser | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | DOOSAN |  | IFA | IFP |  |  | 2025-04-10 |  |  |  | 2025-04-30 |  |  |  | 2025-06-05 | [7 empty] | 638 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1,C2 | NO |  | NO | Combine
250 | Later | S&L | SAU4005-G000-SM_-&MEC-00252 | Technical Specifications for STG Building Overhead Crane | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-03-01 |  |  |  | 2025-03-21 |  |  |  | 2025-04-25 | [7 empty] | 496 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
251 | Later | S&L | SAU4005-G000-PG_-&MEC-00403 | Technical Specifications for Closed Circuit Cooling Water Pumps | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-06-19 |  |  |  | 2025-07-09 |  |  |  | 2025-08-13 | [7 empty] | 227 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO
252 | Later | S&L | SAU4005-G000-EG_-&MEC-00404 | Technical Specifications for Fuel Oil System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-09-08 |  |  |  | 2025-09-28 |  |  |  | 2025-11-02 | [7 empty] | 259 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO
253 | Later | S&L | SAU4005-G000-LC_-&MEC-00433 | Technical Specification for Cartridge Filter | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-09-02 |  |  |  | 2025-09-22 |  |  |  | 2025-10-27 | [7 empty] | 130 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO
254 | Later | S&L | SAU4005-G000-___-&MEC-00434 | Technical Specification for HAZID , Hazop and SIL | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFP |  |  | 2025-09-12 |  |  |  | 2025-10-02 |  |  |  | 2025-11-07 | [7 empty] | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
255 | Later | S&L | SAU4005-G000-PG_-&MEC-00435 | Technical Specification for Plates type Heatexchanger | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-10-31 |  |  |  | 2025-11-20 |  |  |  | 2025-12-25 | [7 empty] | 162 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
256 | Later | S&L | SAU4005-P000-LB_-&MEC-00436 | Technical Specifications for Silencer | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFP |  |  | 2025-10-22 |  |  |  | 2025-11-11 |  |  |  | 2025-12-17 | [7 empty] | 130 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO
257 | Later | S&L | SAU4005-G000-LCM-&MEC-00472 | Technical Specifications for Atmospheric Flash Tank Transfer Pumps | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | DOOSAN |  | IFA | IFP |  |  | 2025-06-25 |  |  |  | 2025-07-15 |  |  |  | 2025-08-20 | [7 empty] | 528 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
258 | Later | S&L | SAU4005-G000-B__-&EDB-00500 | Electrical Design Criteria Document | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFA | IFD |  |  | 2025-03-13 |  |  |  | 2025-04-02 |  |  |  | 2025-05-08 | [7 empty] | 764 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1 | NO |  | NO | Common
259 | Later | S&L | SAU4005-G000-B__-&EFA-00501 | Overall Key Single Line Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-03-20 |  |  |  | 2025-04-09 |  |  |  | 2026-07-16 | [7 empty] | 434 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1,C4 | SEC | S1,S2,S3,S4,S5,S6,S7,S8,S9,S10,S11 | Yes | Common
260 | Later | S&L | SAU4005-G000-B__-&EFA-00502 | Single Line Diagram of Relay & Metering Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-05-02 |  |  |  | 2025-05-22 |  |  |  | 2026-08-14 | [7 empty] | 434 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1,C2,C4 | SEC | S1,S2,S3,S4,S5,S6,S7,S8,S9,S10,S11 | Yes | Common
261 | Later | S&L | SAU4005-G000-B__-&EFA-00503 | Single Line Diagram of MV Switchgear | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-05-19 |  |  |  | 2025-06-08 |  |  |  | 2026-08-14 | [7 empty] | 343 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1,C2,C4 | SEC | S1,S2,S3,S4,S5 | Yes | Common
262 | Later | S&L | SAU4005-G000-B__-&EFA-00504 | Single Line Diagram of DC & UPS System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-09-26 |  |  |  | 2025-10-16 |  |  |  | 2026-09-07 | [7 empty] | 343 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C2 | NO |  | NO | Common
263 | Later | S&L | SAU4005-G000-B__-&EFA-00676 | Single Line Diagram of LV Switchgear | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-10-06 |  |  |  | 2025-10-26 |  |  |  | 2026-08-14 | [7 empty] | 343 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Common
264 | Later | S&L | SAU4005-G000-B__-&EFA-00677 | Single Line Diagram of BSEDG | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | DOOSAN |  | IFA | IFP |  |  | 2025-08-31 |  |  |  | 2025-09-20 |  |  |  | 2025-10-26 | [7 empty] | 343 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C2 | NO |  | NO | Common
265 | Later | S&L | SAU4005-G000-CEJ-&EEC-00678 | Technical specification for Fault Monitoring System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA |  |  |  | 2025-12-15 |  |  |  | 2026-01-04 |  |  |  | 2026-02-08 | [21 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES |  |  |  |  | Common
266 | Later | S&L | SAU4005-G000-B__-&EEC-00679 | Technical specification for Cathodic Protection system | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA |  |  |  | 2025-12-06 |  |  |  | 2025-12-26 |  |  |  | 2026-01-30 | [21 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO |  |  |  |  | Open
267 | Later | S&L | SAU4005-G000-B__-&EEC-00680 | Technical specification for EHV Cable | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA |  |  |  | 2025-11-09 |  |  |  | 2025-11-29 |  |  |  | 2026-01-03 | [21 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO |  |  |  |  | Common
268 | Later | S&L | SAU4005-G000-B__-&EDD-00505 | Load Flow Study of Power Plant | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-16 |  |  |  | 2026-01-05 |  |  |  | 2026-08-14 | [7 empty] | 1095 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1,C2,C4 | SEC | S1,S2,S3,S4,S5,S6 | NO | Common
269 | Later | S&L | SAU4005-G000-B__-&EDD-00506 | Transient Analysis of Power Plant | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-18 |  |  |  | 2026-03-10 |  |  |  | 2026-09-14 | [7 empty] | 1095 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1,C2,C4 | SEC | S1,S2,S3,S4,S5,S6 | NO | Common
270 | Later | S&L | SAU4005-G000-B__-&EDD-00507 | Motor Starting Study of Power Plant | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-25 |  |  |  | 2026-01-14 |  |  |  | 2026-08-24 | [7 empty] | 1095 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Common
271 | Later | S&L | SAU4005-G000-B__-&EDD-00508 | Short Circuit Study of Power Plant | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-16 |  |  |  | 2026-01-05 |  |  |  | 2026-08-14 | [7 empty] | 1095 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1,C2,C4 | SEC | S1,S2,S3,S4,S5,S6 | NO | Common
272 | Later | S&L | SAU4005-G000-B__-&EED-00509 | Relay Setting Calculation of Power Plant | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2026-08-29 |  |  |  | 2026-09-18 |  |  |  | 2027-01-01 | [7 empty] | 2300 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C1,C2,C4 | SEC | S1,S2,S3,S4,S5,S6 | NO | Common
273 | Later | S&L | SAU4005-G000-BAT-&EED-00510 | Sizing Calculation for Generator Transformer | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-05-08 |  |  |  | 2025-05-28 |  |  |  | 2025-09-26 | [7 empty] | 690 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1,C2,C4 | SEC | S1 | NO | Common
274 | Later | S&L | SAU4005-G000-BAC-&EED-00511 | Sizing Calculation for Generator Circuit Breaker | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-05-02 |  |  |  | 2025-05-22 |  |  |  | 2025-10-30 | [7 empty] | 651 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
275 | Later | S&L | SAU4005-G000-BAA-&EED-00512 | Sizing Calculation for Iso Phase Bus duct | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-05-02 |  |  |  | 2025-05-22 |  |  |  | 2026-02-25 | [7 empty] | 651 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
276 | Later | S&L | SAU4005-G000-BBT-&EED-00513 | Sizing Calculation for Unit Auxiliary Transformer | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-07-16 |  |  |  | 2025-08-05 |  |  |  | 2026-01-30 | [7 empty] | 965 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Common
277 | Later | S&L | SAU4005-G000-BFT-&EED-00514 | Sizing Calculation for LV Auxiliary Transformer | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-06-10 |  |  |  | 2025-06-30 |  |  |  | 2025-12-24 | [7 empty] | 807 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
278 | Later | S&L | SAU4005-G000-BBA-&EED-00515 | Sizing Calculation for MV Power Cable | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-09-01 |  |  |  | 2025-09-21 |  |  |  | 2026-02-25 | [7 empty] | 651 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | SEC | S1 | NO | Common
279 | Later | S&L | SAU4005-G000-BFA-&EED-00516 | Sizing Calculation for LV Power Cable (sample) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-09-12 |  |  |  | 2025-10-02 |  |  |  | 2026-02-25 | [7 empty] | 651 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
280 | Later | S&L | SAU4005-G000-BUA-&EED-00517 | Sizing Calculation for DC System (Load Duty Cycle) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-08-12 |  |  |  | 2025-09-01 |  |  |  | 2026-08-14 | [7 empty] | 651 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Common
281 | Later | S&L | SAU4005-G000-BR_-&EED-00518 | Sizing Calculation for UPS System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-08-21 |  |  |  | 2025-09-10 |  |  |  | 2026-03-05 | [7 empty] | 761 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
282 | Later | S&L | SAU4005-G000-MJ_-&EED-00519 | Sizing Calculation for BSEDG | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | DOOSAN |  | IFA | IFD |  |  | 2025-03-25 |  |  |  | 2025-04-14 |  |  |  | 2025-05-20 | [7 empty] | 651 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
283 | Later | S&L | SAU4005-G000-BAU-&EED-00520 | Sizing Calculation for Grounding System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-06-18 |  |  |  | 2025-07-08 |  |  |  | 2026-05-02 | [7 empty] | 492 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1 | SEC | S1 | NO | Common
284 | Later | S&L | SAU4005-G000-BAU-&EED-00521 | Sizing Calculation for Lightning Protection System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-09-08 |  |  |  | 2025-09-28 |  |  |  | 2026-01-09 | [7 empty] | 492 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
285 | Later | S&L | SAU4005-G000-BMA-&EED-00522 | Sizing Calculation for Current Transformer | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-08-22 |  |  |  | 2025-09-11 |  |  |  | 2026-09-07 | [7 empty] | 492 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Common
286 | Later | S&L | SAU4005-G000-B__-&EED-00523 | Indoor Lighting Calculation | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-05 |  |  |  | 2025-12-25 |  |  |  | 2026-06-04 | [7 empty] | 645 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Common
287 | Later | S&L | SAU4005-G000-B__-&EED-00524 | Outdoor Lighting Calculation | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2026-01-28 |  |  |  | 2026-02-17 |  |  |  | 2026-05-02 | [7 empty] | 645 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Common
288 | Later | S&L | SAU4005-G000-BUA-&EED-00719 | Sizing Calculation for 125V DC System (Load Duty Cycle) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-10-30 |  |  |  | 2025-11-19 |  |  |  | 2025-12-24 | [7 empty] | 230 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
289 | Later | S&L | SAU4005-G000-UAA-&ELD-00525 | General Arrangement of EHV Cable corridor (upto plant boundary) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-05-14 |  |  |  | 2025-06-03 |  |  |  | 2026-01-03 | [7 empty] | 2267 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1,C2,C4 | SEC | S1,S2,S8 | NO | Common
290 | Later | S&L | SAU4005-G000-UBF-&ELD-00526 | General Arrangement of Transformer Yard Area | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-08-21 |  |  |  | 2025-09-10 |  |  |  | 2026-05-11 | [7 empty] | 1898 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C2 | NO |  | NO | Common
291 | Later | S&L | SAU4005-G000-UBA-&ELH-00527 | Equipment Layout for GT Package MCC / Control room - 11, 12, 13 | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFA | IFC |  |  | 2025-07-02 |  |  |  | 2025-07-22 |  |  |  | 2025-08-27 | [7 empty] | 2267 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Open
292 | Later | S&L | SAU4005-G000-UCA-&ELH-00528 | Equipment Layout for Main Electrical & Control Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-05-26 |  |  |  | 2025-06-15 |  |  |  | 2026-04-16 | [7 empty] | 2666 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Common
293 | Later | S&L | SAU4005-G000-UBA-&ELH-00529 | Equipment Layout for Unit MV/LV Electrical Switchgear building-11, 12, 13 | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFA | IFC |  |  | 2025-08-18 |  |  |  | 2025-09-07 |  |  |  | 2025-10-13 | [7 empty] | 1762 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Combine
294 | Later | S&L | SAU4005-G000-UBA-&ELH-00530 | Equipment Layout for STG and Auxiliary Boiler Electrical Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFA | IFC |  |  | 2025-08-11 |  |  |  | 2025-08-31 |  |  |  | 2025-10-06 | [7 empty] | 1500 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Combine
295 | Later | S&L | SAU4005-G000-UBA-&ELH-00722 | Equipment Layout for BOP Electrical Switchgear Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-12-09 |  |  |  | 2025-12-29 |  |  |  | 2026-02-02 | [7 empty] | 858 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES |  |  |  |  | Open
296 | Later | S&L | SAU4005-G000-B__-&EMA-00533 | Cable Interconnection document for GT & Auxiliaries (Termination details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFI | IFC | [14 empty] | 2026-05-08 |  |  |  | 1814 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
297 | Later | S&L | SAU4005-G000-B__-&EMA-00692 | Cable Interconnection document for ST & Auxiliaries (Termination details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFI | IFC | [14 empty] | 2026-05-28 |  |  |  | 1817 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
298 | Later | S&L | SAU4005-G000-B__-&EMA-00693 | Cable Interconnection document for HRSG and Auxiliaries (Termination details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFI | IFC | [14 empty] | 2026-06-30 |  |  |  | 1817 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
299 | Later | S&L | SAU4005-G000-B__-&EMA-00694 | Cable Interconnection document for BOP (Termination details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-10-07 |  |  |  | 1817 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
300 | Later | S&L | SAU4005-G000-B__-&EMA-00695 | Cable Interconnection document for Electrical Auxiliaries System (Termination details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-11-30 |  |  |  | 1817 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
301 | Later | S&L | SAU4005-G000-B__-&EMA-00696 | Cable Interconnection document for DC System (Termination details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-12-24 |  |  |  | 1817 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
302 | Later | S&L | SAU4005-G000-B__-&EMA-00697 | Cable Interconnection document for UPS System (Termination details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [14 empty] | 2027-01-16 |  |  |  | 1814 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
303 | Later | S&L | SAU4005-G000-B__-&EMA-00534 | Cable Schedule document for GT & Auxiliaries (Routing details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFI | IFD | [14 empty] | 2026-05-30 |  |  |  | 1733 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
304 | Later | S&L | SAU4005-G000-B__-&EMA-00698 | Cable Schedule document for ST & Auxiliaries (Routing details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFI | IFD | [14 empty] | 2026-06-29 |  |  |  | 1733 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
305 | Later | S&L | SAU4005-G000-B__-&EMA-00699 | Cable Schedule document for HRSG and Auxiliaries (Routing details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFI | IFD | [14 empty] | 2026-07-24 |  |  |  | 1733 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
306 | Later | S&L | SAU4005-G000-B__-&EMA-00700 | Cable Schedule document for BOP (Routing details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFD | [14 empty] | 2026-10-28 |  |  |  | 1765 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
307 | Later | S&L | SAU4005-G000-B__-&EMA-00701 | Cable Schedule document for Electrical Auxiliaries System (Routing details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFD | [14 empty] | 2026-11-23 |  |  |  | 1765 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
308 | Later | S&L | SAU4005-G000-B__-&EMA-00702 | Cable Schedule document for DC System (Routing details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFD | [14 empty] | 2026-12-15 |  |  |  | 1765 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
309 | Later | S&L | SAU4005-G000-B__-&EMA-00703 | Cable Schedule document for UPS System (Routing details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFD | [14 empty] | 2027-01-05 |  |  |  | 1765 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
310 | Later | S&L | SAU4005-G000-B__-&EMA-00704 | Cable Schedule document for CNI Cables (Routing details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFI | IFD | [14 empty] | 2026-10-10 |  |  |  | 1785 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
311 | Later | S&L | SAU4005-G000-B__-&ELD-00535 | General Notes & Details of Cable Raceway and Equipment Installation | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-05-09 |  |  |  | 2025-05-29 |  |  |  | 2025-07-04 | [7 empty] | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
312 | Later | S&L | SAU4005-G000-UZT-&ELD-00536 | Cable Raceway Layout for Overall Plant Outdoor Raceway | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | Common |  | IFA | IFC |  |  | 2026-01-21 |  |  |  | 2026-02-10 |  |  |  | 2026-03-18 | [7 empty] | 541 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
313 | Later | S&L | SAU4005-G000-UM_-&ELD-00537 | Cable Raceway Layout for GTG Area | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFA | IFC |  |  | 2025-09-29 |  |  |  | 2025-10-19 |  |  |  | 2025-11-24 | [7 empty] | 573 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
314 | Later | S&L | SAU4005-G000-UMA-&ELH-00538 | Cable Raceway Layout for STG Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFA | IFC |  |  | 2026-04-14 |  |  |  | 2026-05-04 |  |  |  | 2026-06-09 | [7 empty] | 424 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
315 | Later | S&L | SAU4005-G000-USU-&ELH-00539 | Cable Raceway Layout for Chemical Storage Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-04-13 |  |  |  | 2026-05-03 |  |  |  | 2026-06-07 | [7 empty] | 424 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
316 | Later | S&L | SAU4005-G000-USC-&ELH-00540 | Cable Raceway Layout for Air Compressor Shed | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-01-08 |  |  |  | 424 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
317 | Later | S&L | SAU4005-G000-URX-&ELH-00541 | Cable Raceway Layout for Fin Fan Cooler, CCCW Area and Fin Fan Cooler Electrical Container | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-02-06 |  |  |  | 363 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
318 | Later | S&L | SAU4005-G000-UBA-&ELH-00542 | Cable Raceway Layout for STG and Auxiliary Boiler Electrical Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFI | IFC | [14 empty] | 2026-03-02 |  |  |  | 363 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
319 | Later | S&L | SAU4005-G000-UER-&ELH-00543 | Cable Raceway Layout for Fuel Gas Area and GBC Building including Electrical Room | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-01-07 |  |  |  | 2026-01-27 |  |  |  | 2026-03-23 | [7 empty] | 363 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
320 | Later | S&L | SAU4005-G000-UEJ-&ELH-00544 | Cable Raceway Layout for Fuel Oil Area , Pump Shed and Electrical Container | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-02 |  |  |  | 363 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
321 | Later | S&L | SAU4005-G000-UBF-&ELD-00545 | Cable Raceway Layout for Transformer Area | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-01-21 |  |  |  | 2026-02-10 |  |  |  | 2026-06-04 | [7 empty] | 363 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
322 | Later | S&L | SAU4005-G000-UBA-&ELH-00546 | Cable Raceway Layout for ACC Electrical Container | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFA | IFC |  |  | 2025-12-17 |  |  |  | 2026-01-06 |  |  |  | 2026-02-11 | [7 empty] | 363 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
323 | Later | S&L | SAU4005-G000-UBA-&ELH-00547 | Cable Raceway Layout for GT Package MCC / Control room - 11, 12, 13 | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFA | IFC |  |  | 2025-09-22 |  |  |  | 2025-10-12 |  |  |  | 2025-11-17 | [7 empty] | 363 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
324 | Later | S&L | SAU4005-G000-UCA-&ELH-00548 | Cable Raceway Layout for Main Electrical & Control Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFA | IFC |  |  | 2025-09-15 |  |  |  | 2025-10-05 |  |  |  | 2025-11-10 | [7 empty] | 363 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
325 | Later | S&L | SAU4005-G000-UST-&ELH-00549 | Cable Raceway Layout for Workshop and Warehouse Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-12-22 |  |  |  | 363 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
326 | Later | S&L | SAU4005-G000-UG_-&ELH-00550 | Cable Raceway Layout for Water and Effluent treatment building including Electrical Room | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-12-02 |  |  |  | 2025-12-22 |  |  |  | 2026-03-23 | [7 empty] | 363 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
327 | Later | S&L | SAU4005-G000-UTG-&ELH-00551 | Cable Raceway Layout for Hydrogen Generation Plant including Electrical Room | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-11-07 |  |  |  | 2025-11-27 |  |  |  | 2026-06-11 | [7 empty] | 363 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
328 | Later | S&L | SAU4005-G000-UGA-&ELH-00552 | Cable Raceway Layout for Raw Water Transfer Pumps and Chlorination Shed | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-03-16 |  |  |  | 2026-04-05 |  |  |  | 2026-05-10 | [7 empty] | 363 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
329 | Later | S&L | SAU4005-G000-USG-&ELH-00554 | Cable Raceway Layout for Fire Water Pump and Service water pump Shed | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-01-08 |  |  |  | 2026-01-28 |  |  |  | 2026-04-03 | [7 empty] | 363 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
330 | Later | S&L | SAU4005-G000-UBA-&ELH-00555 | Cable Raceway Layout for BFP VFD Container | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFI | IFC | [14 empty] | 2025-11-12 |  |  |  | 363 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
331 | Later | S&L | SAU4005-G000-UBA-&ELH-00556 | Cable Raceway Layout for BSEDG Electrical Container | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFA | IFC |  |  | 2026-01-29 |  |  |  | 2026-02-18 |  |  |  | 2026-03-26 | [7 empty] | 363 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
332 | Later | S&L | SAU4005-G000-UBA-&ELH-00557 | Cable Raceway Layout for Unit MV/LV Electrical Switchgear building-11, 12, 13 | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFA | IFC |  |  | 2026-04-01 |  |  |  | 2026-04-21 |  |  |  | 2026-05-27 | [7 empty] | 363 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
333 | Later | S&L | SAU4005-G000-UGD-&ELH-00558 | Cable Raceway Layout for DM water forwarding Pump Shed | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-12-09 |  |  |  | 363 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
334 | Later | S&L | SAU4005-G000-UBA-&ELH-00559 | Cable Raceway Layout for BOP Electrical Switchgear Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-01-29 |  |  |  | 2026-02-18 |  |  |  | 2026-03-25 | [7 empty] | 363 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
335 | Later | S&L | SAU4005-G000-UYC-&ELH-00562 | Cable Raceway Layout for Administration & Social Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-03-10 |  |  |  | 2026-03-30 |  |  |  | 2026-05-04 | [7 empty] | 363 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
336 | Later | S&L | SAU4005-G000-UHA-&ELH-00854 | Cable Raceway Layout for HRSG Electrical Container | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFA | IFC |  |  | 2026-06-24 |  |  |  | 2026-07-14 |  |  |  | 2026-08-19 | [7 empty] | 1500 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
337 | Later | S&L | SAU4005-G000-B__-&ELD-00564 | General Notes & Details of Lighting System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-04-25 |  |  |  | 2025-05-15 |  |  |  | 2025-06-22 | [7 empty] | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
338 | Later | S&L | SAU4005-G000-UM_-&ELD-00565 | Lighting Layout for GTG Area | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-03-09 |  |  |  | 2026-03-29 |  |  |  | 2026-06-30 | [7 empty] | 476 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
339 | Later | S&L | SAU4005-G000-UMA-&ELH-00566 | Lighting Layout for STG Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-03-12 |  |  |  | 2026-04-01 |  |  |  | 2026-06-30 | [7 empty] | 476 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
340 | Later | S&L | SAU4005-G000-USU-&ELH-00567 | Lighting Layout for Chemical Storage Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-06-03 |  |  |  | 2026-06-23 |  |  |  | 2026-07-28 | [7 empty] | 476 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
341 | Later | S&L | SAU4005-G000-USC-&ELH-00568 | Lighting Layout for Air Compressor Shed | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-10 |  |  |  | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
342 | Later | S&L | SAU4005-G000-URX-&ELH-00569 | Lighting Layout for Fin Fan Cooler & CCCW Area | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-03 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
343 | Later | S&L | SAU4005-G000-UBA-&ELH-00570 | Lighting Layout for STG and Auxiliary Boiler Electrical Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-09 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
344 | Later | S&L | SAU4005-G000-UER-&ELH-00571 | Lighting Layout for Fuel Gas Area and GBC Building including Electrical Room | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-16 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
345 | Later | S&L | SAU4005-G000-UEJ-&ELH-00572 | Lighting Layout for Fuel Oil Area and Pump Shed | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-04-14 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
346 | Later | S&L | SAU4005-G000-UBF-&ELD-00573 | Lighting Layout for Transformer Area | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-05-05 |  |  |  | 2026-05-25 |  |  |  | 2026-06-30 | [7 empty] | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
347 | Later | S&L | SAU4005-G000-UBA-&ELH-00575 | Lighting Layout for GT Package MCC / Control room - 11, 12, 13 | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-01-29 |  |  |  | 2026-02-18 |  |  |  | 2026-06-30 | [7 empty] | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
348 | Later | S&L | SAU4005-G000-UCA-&ELH-00576 | Lighting Layout for Main Electrical & Control Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-02-06 |  |  |  | 2026-02-26 |  |  |  | 2026-06-30 | [7 empty] | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
349 | Later | S&L | SAU4005-G000-UST-&ELH-00577 | Lighting Layout for Workshop and Warehouse Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-03-13 |  |  |  | 2026-04-02 |  |  |  | 2026-06-30 | [7 empty] | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
350 | Later | S&L | SAU4005-G000-UG_-&ELH-00578 | Lighting Layout for Water and Effluent treatment building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-04-16 |  |  |  | 2026-05-06 |  |  |  | 2026-06-30 | [7 empty] | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
351 | Later | S&L | SAU4005-G000-UTG-&ELH-00579 | Lighting Layout for Hydrogen Generation Plant including Electrical Room | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-02-28 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
352 | Later | S&L | SAU4005-G000-UGA-&ELH-00580 | Lighting Layout for Raw Water Transfer Pumps and Chlorination Shed | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-05-25 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
353 | Later | S&L | SAU4005-G000-USG-&ELH-00582 | Lighting Layout for Fire Water Pump and Service water pump Shed | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-03-23 |  |  |  | 2026-04-12 |  |  |  | 2026-06-30 | [7 empty] | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
354 | Later | S&L | SAU4005-G000-UBA-&ELH-00585 | Lighting Layout for Unit MV/LV Electrical Switchgear building-11, 12, 13 | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-04-21 |  |  |  | 2026-05-11 |  |  |  | 2026-06-30 | [7 empty] | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
355 | Later | S&L | SAU4005-G000-UGD-&ELH-00586 | Lighting Layout for DM water forwarding Pump Shed | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-04-01 |  |  |  | 2026-04-21 |  |  |  | 2026-06-10 | [7 empty] | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
356 | Later | S&L | SAU4005-G000-UBA-&ELH-00587 | Lighting Layout for BOP Electrical Switchgear Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-04-21 |  |  |  | 2026-05-11 |  |  |  | 2026-07-06 | [7 empty] | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
357 | Later | S&L | SAU4005-G000-UYC-&ELH-00590 | Lighting Layout for Administration & Social Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-03-25 |  |  |  | 2026-04-14 |  |  |  | 2026-06-30 | [7 empty] | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
358 | Later | S&L | SAU4005-G000-UZA-&ELH-00858 | Outdoor Lighting Layout for Access Road | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-12-10 |  |  |  | 2025-12-30 |  |  |  | 2026-02-03 | [7 empty] | 1200 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
359 | Later | S&L | SAU4005-G000-UZT-&ELH-00859 | Lighting Layout for Outdoor areas | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-04-20 |  |  |  | 2026-05-10 |  |  |  | 2026-06-14 | [7 empty] | 1200 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
360 | Later | S&L | SAU4005-G000-B__-&ELD-00592 | General Notes & Details of Grounding System and Lightning Protection System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-06-25 |  |  |  | 2025-07-15 |  |  |  | 2026-05-28 | [7 empty] | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
361 | Later | S&L | SAU4005-G000-UM_-&ELD-00593 | Grounding & Lightning Protection Layout for GTG Area | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-09-30 |  |  |  | 2025-10-20 |  |  |  | 2026-05-28 | [7 empty] | 476 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Open
362 | Later | S&L | SAU4005-G000-UMA-&ELH-00594 | Grounding & Lightning Protection Layout for STG Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-10-24 |  |  |  | 2025-11-13 |  |  |  | 2026-05-28 | [7 empty] | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
363 | Later | S&L | SAU4005-G000-USU-&ELH-00595 | Grounding & Lightning Protection Layout for Chemical Storage Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-12-15 |  |  |  | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
364 | Later | S&L | SAU4005-G000-USC-&ELH-00596 | Grounding & Lightning Protection Layout for Air Compressor Shed | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-12-20 |  |  |  | 2026-01-09 |  |  |  | 2026-05-28 | [7 empty] | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
365 | Later | S&L | SAU4005-G000-URX-&ELH-00597 | Grounding & Lightning Protection Layout for Fin Fan Cooler & CCCW Area | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-01-02 |  |  |  | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
366 | Later | S&L | SAU4005-G000-UBA-&ELH-00598 | Grounding & Lightning Protection Layout for STG and Auxiliary Boiler Electrical Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-01-07 |  |  |  | 2026-01-27 |  |  |  | 2026-05-28 | [7 empty] | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
367 | Later | S&L | SAU4005-G000-UER-&ELH-00599 | Grounding & Lightning Protection Layout for Fuel Gas Area and GBC Building including Electrical Room | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-12-23 |  |  |  | 2026-01-27 |  |  |  | 2026-05-28 | [7 empty] | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
368 | Later | S&L | SAU4005-G000-UEJ-&ELH-00600 | Grounding & Lightning Protection Layout for Fuel Oil Area and Pump Shed | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-06-02 |  |  |  | 2026-06-22 |  |  |  | 2026-07-27 | [7 empty] | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
369 | Later | S&L | SAU4005-G000-UBF-&ELD-00601 | Grounding & Lightning Protection Layout for Transformer Area | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-03-09 |  |  |  | 2026-03-29 |  |  |  | 2026-06-04 | [7 empty] | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
370 | Later | S&L | SAU4005-G000-UBA-&ELH-00603 | Grounding & Lightning Protection Layout for GT Package MCC / Control room - 11, 12, 13 | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-10-17 |  |  |  | 2025-11-06 |  |  |  | 2026-05-28 | [7 empty] | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
371 | Later | S&L | SAU4005-G000-UCA-&ELH-00604 | Grounding & Lightning Protection Layout for Main Electrical & Control Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-10-23 |  |  |  | 2025-11-12 |  |  |  | 2026-05-28 | [7 empty] | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
372 | Later | S&L | SAU4005-G000-UST-&ELH-00605 | Grounding and Lightning Protection Layout for Workshop and Warehouse Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-11-12 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
373 | Later | S&L | SAU4005-G000-UG_-&ELH-00606 | Grounding & Lightning Protection Layout for Water and Effluent treatment building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-12-27 |  |  |  | 2026-04-13 |  |  |  | 2026-05-28 | [7 empty] | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
374 | Later | S&L | SAU4005-G000-UTG-&ELH-00607 | Grounding & Lightning Protection Layout for Hydrogen Generation Plant including Electrical Room | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-03-14 |  |  |  | 2026-04-13 |  |  |  | 2026-06-05 | [7 empty] | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
375 | Later | S&L | SAU4005-G000-UGA-&ELH-00608 | Grounding & Lightning Protection Layout for Raw Water Transfer Pumps and Chlorination Shed | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-04-21 |  |  |  | 2026-05-22 |  |  |  | 2026-06-26 | [7 empty] | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
376 | Later | S&L | SAU4005-G000-USG-&ELH-00610 | Grounding & Lightning Protection Layout for Fire Water Pump and Service water pump Shed | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-02-23 |  |  |  | 2025-09-23 |  |  |  | 2026-05-28 | [7 empty] | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
377 | Later | S&L | SAU4005-G000-UBA-&ELH-00613 | Grounding & Lightning Protection Layout for Unit MV/LV Electrical Switchgear building-11, 12, 13 | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-01-29 |  |  |  | 2026-03-02 |  |  |  | 2026-05-28 | [7 empty] | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
378 | Later | S&L | SAU4005-G000-UGD-&ELH-00614 | Grounding & Lightning Protection Layout for DM water forwarding Pump Shed | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-01-29 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
379 | Later | S&L | SAU4005-G000-UBA-&ELH-00615 | Grounding & Lightning Protection Layout for BOP Electrical Switchgear Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-05-29 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
380 | Later | S&L | SAU4005-G000-UYC-&ELH-00618 | Grounding & Lightning Protection Layout for Administration & Social Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-01-29 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
381 | Later | S&L | SAU4005-G000-B__-&ELD-00708 | Overall Grounding Layout | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-07-18 |  |  |  | 2025-08-07 |  |  |  | 2026-05-04 | [7 empty] | 334 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
382 | Later | S&L | SAU4005-G000-B__-&EFB-00710 | 380 KV Substation Interface Block Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2026-03-11 |  |  |  | 2026-03-31 |  |  |  | 2026-05-05 | [7 empty] | 123 | [13 empty] | WF Transmittal DI-EPC-ACWA |  | NO | NO | NO | NO |  | NO
383 | Later | S&L | SAU4005-G000-B__-&EFB-00718 | Common Interlock Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2026-06-06 |  |  |  | 2026-06-26 |  |  |  | 2026-07-31 | [7 empty] | 292 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
384 | Later | S&L | SAU4005-G000-B__-&EDC-00720 | Electrical operation philosophy | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2026-08-17 |  |  |  | 2026-09-06 |  |  |  | 2026-10-11 | [7 empty] | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Common
385 | Later | S&L | SAU4005-G000-B__-&ELD-00721 | Overall Lightning Protection Layout | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-12-29 |  |  |  | 2026-01-18 |  |  |  | 2026-05-04 | [7 empty] | 162 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Common
386 | Later | S&L | SAU4005-G000-BAT-&EEC-00728 | Technical Specification for Generator Transformer | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-04-30 |  |  |  | 2025-05-20 |  |  |  | 2025-06-24 | [7 empty] | 567 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1,C1 | SEC | S1 | NO | Common
387 | Later | S&L | SAU4005-G000-BAC-&EEC-00630 | Technical Specification for Generator Circuit Breaker | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-06-04 |  |  |  | 2025-06-24 |  |  |  | 2025-07-29 | [7 empty] | 567 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
388 | Later | S&L | SAU4005-G000-BAA-&EEC-00631 | Technical Specification for Isolated Phase Bus duct | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-06-04 |  |  |  | 2025-06-24 |  |  |  | 2025-07-29 | [7 empty] | 385 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
389 | Later | S&L | SAU4005-G000-BBT-&EEC-00632 | Technical Specification for Unit Auxiliary Transformer and NGR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-08-21 |  |  |  | 2025-09-10 |  |  |  | 2025-10-15 | [7 empty] | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
390 | Later | S&L | SAU4005-G000-BBA-&EEC-00633 | Technical Specification for MV Switchgear | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-08-28 |  |  |  | 2025-09-17 |  |  |  | 2025-10-22 | [7 empty] | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
391 | Later | S&L | SAU4005-G000-BFT-&EEC-00634 | Technical Specification for LV Auxiliary Transformers | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-07-17 |  |  |  | 2025-08-06 |  |  |  | 2025-09-10 | [7 empty] | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
392 | Later | S&L | SAU4005-G000-BF_-&EEC-00635 | Technical Specification for Non Segregated Phase Bus duct | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-08-05 |  |  |  | 2025-09-23 |  |  |  | 2025-10-28 | [7 empty] | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
393 | Later | S&L | SAU4005-G000-BHA-&EEC-00636 | Technical Specification for LV Switchgear | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-10-23 |  |  |  | 2025-11-12 |  |  |  | 2025-12-17 | [7 empty] | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
394 | Later | S&L | SAU4005-G000-MJ_-&EEC-00637 | Technical Specification for BSEDG | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | DOOSAN |  | IFA | IFP |  |  | 2025-03-16 |  |  |  | 2025-04-05 |  |  |  | 2025-05-11 | [7 empty] | 298 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
395 | Later | S&L | SAU4005-G000-BUA-&EEC-00638 | Technical Specification for Battery | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-09-17 |  |  |  | 2025-10-07 |  |  |  | 2025-11-11 | [7 empty] | 236 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
396 | Later | S&L | SAU4005-G000-BR_-&EEC-00639 | Technical Specification for UPS System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-10-03 |  |  |  | 2025-10-23 |  |  |  | 2025-11-27 | [7 empty] | 236 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Common
397 | Later | S&L | SAU4005-G000-AR_-&EEC-00640 | Technical Specification for Protection Panels | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-10-16 |  |  |  | 2025-11-05 |  |  |  | 2025-12-10 | [7 empty] | 236 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1 | SEC | S2,S3 | NO | Common
398 | Later | S&L | SAU4005-G000-C__-&EEC-00641 | Technical Specification for Plant Communication System (Turnkey Package) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-10-15 |  |  |  | 2025-11-04 |  |  |  | 2025-12-09 | [7 empty] | 236 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
399 | Later | S&L | SAU4005-G000-C__-&EEC-00681 | Technical specification for Interface & Telecommunication Panels between Plant and S/S | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-11-19 |  |  |  | 2025-12-09 |  |  |  | 2026-01-13 | [7 empty] | 236 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1 | SEC | S1,S2,S3,S4,S5,S7,S9,S10,S11 | NO | Common
400 | Later | S&L | SAU4005-G000-BBA-&EEC-00706 | Technical specification for MV VFD | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | DOOSAN |  | IFA | IFP |  |  | 2025-08-08 |  |  |  | 2025-08-28 |  |  |  | 2025-10-03 | [7 empty] | 259 | [13 empty] | WF Transmittal DI-EPC-ACWA |  | NO | YES | NO | NO |  | NO
401 | Later | S&L | SAU4005-G000-BUA-&EEC-00709 | Technical Specification for Battery Charger | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-11-05 |  |  |  | 2025-11-25 |  |  |  | 2025-12-30 | [7 empty] | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
402 | Later | S&L | SAU4005-G000-B__-&EEC-00711 | Technical Specification for Heat Tracing System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-12-14 |  |  |  | 2026-01-03 |  |  |  | 2026-02-07 | [7 empty] | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
403 | Later | S&L | SAU4005-G000-B__-&EEC-00713 | Technical Specification for MV Cable | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-11-11 |  |  |  | 2025-12-01 |  |  |  | 2026-01-05 | [7 empty] | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO
404 | Later | S&L | SAU4005-G000-B__-&EEC-00714 | Technical Specification for LV Cable | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-12-01 |  |  |  | 2025-12-21 |  |  |  | 2026-01-25 | [7 empty] | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO
405 | Later | S&L | SAU4005-G000-B__-&EEC-00723 | Technical Specification for Control Cable | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-11-12 |  |  |  | 2025-12-02 |  |  |  | 2026-01-06 | [7 empty] | 194 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
406 | Later | S&L | SAU4005-G000-B__-&EEC-00724 | Technical Specification for Cable Termination Material | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | Common |  | IFA | IFP |  |  | 2026-05-20 |  |  |  | 2026-06-09 |  |  |  | 2026-07-15 | [7 empty] | 130 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
407 | Later | S&L | SAU4005-G000-B__-&EEC-00855 | Technical Specification for Electrical Container | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-12-16 |  |  |  | 2026-01-05 |  |  |  | 2026-02-09 | [7 empty] | 1500 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
408 | Later | S&L | SAU4005-G000-C__-&EDB-00750 | Design Criteria Documents of Control & Instrumentation | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | Common |  | IFA | IFD |  |  | 2025-03-20 |  |  |  | 2025-04-09 |  |  |  | 2025-05-15 | [7 empty] | 233 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1 | NO |  | NO | Common
409 | Later | S&L | SAU4005-G000-CJ_-&EFF-00751 | Plant Control System Architecture Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | Common |  | IFA | IFD |  |  | 2025-02-20 |  |  |  | 2025-03-12 |  |  |  | 2025-04-17 | [7 empty] | 279 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1 | NO |  | NO | Common
410 | Later | S&L | SAU4005-G000-UCA-&ELH-00752 | Central Control Room Layout | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | Common |  | IFA | IFC |  |  | 2025-05-10 |  |  |  | 2025-05-30 |  |  |  | 2025-07-05 | [7 empty] | 797 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C2 | NO |  | NO | Common
411 | Later | S&L | SAU4005-G000-C__-&ELD-00753 | Instrument Installation & Hook Up Drawings | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | Common |  | IFA | IFC |  |  | 2025-04-27 |  |  |  | 2025-05-17 |  |  |  | 2025-06-22 | [7 empty] | 641 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
412 | Later | S&L | SAU4005-G000-C__-&ELD-00754 | Instrument/Junction Box Location Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | I&C&DCS | Instrumentation & Control | Common |  | IFA | IFC |  |  | 2026-07-25 |  |  |  | 2026-08-14 |  |  |  | 2026-09-19 | [7 empty] | 641 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
413 | Later | S&L | SAU4005-G000-EK_-&EFF-00755 | Logic Diagram for Fuel Gas Compressor System Interface | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFC |  |  | 2025-12-06 |  |  |  | 2025-12-26 |  |  |  | 2026-01-30 | [7 empty] | 431 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
414 | Later | S&L | SAU4005-G000-GHC-&EFF-00756 | Logic Diagram for DM Water Distribution System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFC |  |  | 2026-02-23 |  |  |  | 2026-03-15 |  |  |  | 2026-04-19 | [7 empty] | 431 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
415 | Later | S&L | SAU4005-G000-GK_-&EFF-00757 | Logic Diagram for Potable Water System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFC |  |  | 2026-01-29 |  |  |  | 2026-02-18 |  |  |  | 2026-03-25 | [7 empty] | 431 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
416 | Later | S&L | SAU4005-G000-GH_-&EFF-00758 | Logic Diagram for Service water system | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFC |  |  | 2026-02-04 |  |  |  | 2026-02-24 |  |  |  | 2026-03-31 | [7 empty] | 431 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
417 | Later | S&L | SAU4005-G000-MB_-&EFF-00759 | Logic Diagram for Gas Turbine, Generator & Auxiliaries Interface | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFC |  |  | 2025-08-22 |  |  |  | 2025-09-11 |  |  |  | 2025-10-17 | [7 empty] | 496 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
418 | Later | S&L | SAU4005-G000-MA_-&EFF-00760 | Logic Diagram for Steam Turbine, Generator & Auxiliaries Interface | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFC |  |  | 2025-09-29 |  |  |  | 2025-10-19 |  |  |  | 2025-11-24 |  |  |  | 2025-12-22 |  |  |  | 496 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
419 | Later | S&L | SAU4005-G000-GB_-&EFF-00761 | Logic Diagram for Water and Effluent treatment building Interface | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFC |  |  | 2026-02-25 |  |  |  | 2026-03-17 |  |  |  | 2026-04-21 | [7 empty] | 463 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
420 | Later | S&L | SAU4005-G000-SA_-&EFF-00762 | Logic Diagram for HVAC Interface | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFC |  |  | 2026-04-15 |  |  |  | 2026-05-05 |  |  |  | 2026-06-09 | [7 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
421 | Later | S&L | SAU4005-G000-C__-&EFF-00763 | Logic Diagram for Plant Startup Logic | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFC |  |  | 2026-05-12 14:30 |  |  |  | 2026-06-01 14:30 |  |  |  | 2026-07-07 14:30 | [7 empty] | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
422 | Later | S&L | SAU4005-G000-C__-&EFF-00764 | Logic Diagram for Plant Shutdown Logic | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFC |  |  | 2026-05-21 10:00 |  |  |  | 2026-06-10 10:00 |  |  |  | 2026-07-16 10:00 | [7 empty] | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
423 | Later | S&L | SAU4005-G000-C__-&EFF-00765 | Logic Diagram for AGC Logic | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFC |  |  | 2026-06-24 17:00 |  |  |  | 2026-07-14 17:00 |  |  |  | 2026-08-19 17:00 | [7 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
424 | Later | S&L | SAU4005-G000-C__-&EFF-00766 | Master Logic Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFD |  |  | 2025-07-28 16:00 |  |  |  | 2025-08-17 16:00 |  |  |  | 2025-09-22 16:00 | [7 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
425 | Later | S&L | SAU4005-G000-QU_-&EFF-00768 | Logic Diagram for Sampling System Interface | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFC |  |  | 2026-04-13 |  |  |  | 2026-05-03 |  |  |  | 2026-06-07 | [7 empty] | 382 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
426 | Later | S&L | SAU4005-G000-QCA-&EFF-00769 | Logic Diagram for Chemical Feed System Interface | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFC |  |  | 2026-04-01 |  |  |  | 2026-04-21 |  |  |  | 2026-05-26 | [7 empty] | 382 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
427 | Later | S&L | SAU4005-G000-QEA-&EFF-00770 | Logic Diagram for Compressed Air System Interface | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFC |  |  | 2026-02-10 |  |  |  | 2026-03-02 |  |  |  | 2026-04-06 | [7 empty] | 382 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
428 | Later | S&L | SAU4005-G000-QH_-&EFF-00771 | Logic Diagram for Auxiliary Boiler system Interface | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFC |  |  | 2026-03-27 |  |  |  | 2026-04-16 |  |  |  | 2026-05-21 | [7 empty] | 382 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
429 | Later | S&L | SAU4005-G000-LAB-&EFF-00772 | Logic Diagram for Feed Water System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFC |  |  | 2025-08-16 15:00 |  |  |  | 2025-09-05 15:00 |  |  |  | 2025-10-11 15:00 | [7 empty] | 382 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
430 | Later | S&L | SAU4005-G000-LC_-&EFF-00773 | Logic Diagram for Condensate System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFC |  |  | 2025-10-08 09:00 |  |  |  | 2025-10-28 09:00 |  |  |  | 2025-12-03 09:00 | [7 empty] | 382 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
431 | Later | S&L | SAU4005-G000-LBA-&EFF-00774 | Logic Diagram for HP Steam System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFC |  |  | 2025-11-23 |  |  |  | 2025-12-13 |  |  |  | 2026-01-18 | [7 empty] | 366 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
432 | Later | S&L | SAU4005-G000-LBD-&EFF-00775 | Logic Diagram for LP Steam System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFC |  |  | 2025-11-29 |  |  |  | 2025-12-19 |  |  |  | 2026-01-24 | [7 empty] | 366 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
433 | Later | S&L | SAU4005-G000-LBC-&EFF-00776 | Logic Diagram for Cold Reheat System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFC |  |  | 2025-12-04 |  |  |  | 2025-12-24 |  |  |  | 2026-01-29 | [7 empty] | 366 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
434 | Later | S&L | SAU4005-G000-LBB-&EFF-00777 | Logic Diagram for Hot Reheat System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFC |  |  | 2025-12-06 |  |  |  | 2025-12-26 |  |  |  | 2026-01-31 | [7 empty] | 366 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
435 | Later | S&L | SAU4005-G000-LBG-&EFF-00778 | Logic Diagram for Auxiliary Steam System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFC |  |  | 2025-12-27 |  |  |  | 2026-01-16 |  |  |  | 2026-02-21 | [7 empty] | 366 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
436 | Later | S&L | SAU4005-G000-LBH-&EFF-00779 | Logic Diagram for STG Drains & Vents System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFC |  |  | 2025-12-22 |  |  |  | 2026-01-11 |  |  |  | 2026-02-16 | [7 empty] | 366 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
437 | Later | S&L | SAU4005-G000-CYV-&EDD-00830 | Plant Settlement System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFD |  |  | 2026-03-06 |  |  |  | 2026-03-26 |  |  |  | 2026-04-30 | [7 empty] | 317 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1,C1 | SEC, Aramco,NWC | S1,S7,S11 | YES
438 | Later | S&L | SAU4005-G000-C__-&EDB-00831 | DCS Graphic Philosophy | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFD |  |  | 2026-09-09 |  |  |  | 2026-09-29 |  |  |  | 2026-11-04 | [7 empty] | 317 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
439 | Later | S&L | SAU4005-G000-C__-&EFF-00850 | Logic Diagram for Electrical System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFC |  |  | 2026-02-06 |  |  |  | 2026-02-26 |  |  |  | 2026-04-02 | [7 empty] | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
440 | Later | S&L | SAU4005-G000-C__-&EFF-00851 | Logic Diagram for Miscellaneous System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | Common |  | IFA | IFC |  |  | 2026-05-12 |  |  |  | 2026-05-26 |  |  |  | 2026-07-03 | [7 empty] | 292 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
441 | Later | S&L | SAU4005-G000-C__-&EFF-00853 | Logic diagram for Closed Circuit Cooling Water System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | Common |  | IFA | IFC |  |  | 2026-03-31 |  |  |  | 2026-04-20 |  |  |  | 2026-05-26 | [7 empty] | 500 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
442 | Later | S&L | SAU4005-G000-C__-&EMA-00780 | I & C cable interconnection document for Combined Cycle Misc. System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFI | IFC | [14 empty] | 2026-09-29 |  |  |  | 852 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
443 | Later | S&L | SAU4005-G000-C__-&EMA-00781 | I & C cable interconnection document for HRSG and Auxiliaries | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFI | IFC | [14 empty] | 2026-07-30 |  |  |  | 674 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
444 | Later | S&L | SAU4005-G000-C__-&EMA-00782 | I & C cable interconnection document for GT Interface | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFI | IFC | [14 empty] | 2026-03-15 |  |  |  | 674 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
445 | Later | S&L | SAU4005-G000-C__-&EMA-00783 | I & C cable interconnection document for Service Water, Raw Water & Potable Water Distribution System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-10 |  |  |  | 674 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
446 | Later | S&L | SAU4005-G000-C__-&EMA-00832 | I & C cable interconnection document for ST Interface | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFI | IFC | [14 empty] | 2026-08-29 |  |  |  | 405 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
447 | Later | S&L | SAU4005-G000-C__-&EMA-00833 | I & C cable interconnection document for Fuel Oil System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-07-14 |  |  |  | 405 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
448 | Later | S&L | SAU4005-G000-C__-&EMA-00834 | I & C cable interconnection document for Fuel Gas System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-11 |  |  |  | 405 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
449 | Later | S&L | SAU4005-G000-C__-&EMA-00835 | I & C cable interconnection document for Fire Protection System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-09-30 |  |  |  | 259 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
450 | Later | S&L | SAU4005-G000-C__-&EMA-00836 | I & C cable interconnection document for Fin Fan Cooler System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-07-08 |  |  |  | 405 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
451 | Later | S&L | SAU4005-G000-C__-&EMA-00837 | I & C cable interconnection document for Compressed Air System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-02 |  |  |  | 324 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
452 | Later | S&L | SAU4005-G000-C__-&EMA-00838 | I & C cable interconnection document - WTP & ETP DCS Interface | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-07-04 |  |  |  | 324 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
453 | Later | S&L | SAU4005-G000-C__-&EMA-00839 | I & C cable interconnection document for Air Cooled Condenser | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFI | IFC | [14 empty] | 2026-08-29 |  |  |  | 405 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
454 | Later | S&L | SAU4005-G000-C__-&EMA-00842 | I & C cable interconnection document - CCCW System & Demineralized Water Distribution | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-31 |  |  |  | 405 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
455 | Later | S&L | SAU4005-G000-C__-&EMA-00843 | I & C cable interconnection document - Condensate System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFI | IFC | [14 empty] | 2026-06-14 |  |  |  | 168 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
456 | Later | S&L | SAU4005-G000-C__-&EMA-00844 | I & C cable interconnection document - Feedwater System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFI | IFC | [14 empty] | 2026-06-29 |  |  |  | 168 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
457 | Later | S&L | SAU4005-G000-C__-&EMA-00845 | I & C cable interconnection document - Auxiliary Steam System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFI | IFC | [14 empty] | 2026-07-24 |  |  |  | 168 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
458 | Later | S&L | SAU4005-G000-C__-&EMA-00846 | I & C cable interconnection document - Steam & Bypass System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFI | IFC | [14 empty] | 2026-07-12 |  |  |  | 168 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
459 | Later | S&L | SAU4005-G000-C__-&EPA-00784 | Instrument List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | I&C&DCS | Instrumentation & Control | Common |  | IFA | IFD |  |  | 2025-11-09 |  |  |  | 2025-11-29 |  |  |  | 2026-01-04 | [7 empty] | 658 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
460 | Later | S&L | SAU4005-G000-C__-&EPB-00785 | DCS I/O List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | I&C&DCS | Instrumentation & Control | Common |  | IFA | IFP |  |  | 2025-11-19 |  |  |  | 2025-12-09 |  |  |  | 2026-01-14 | [7 empty] | 658 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
461 | Later | S&L | SAU4005-G000-C__-&EPB-00847 | Signal Exchange List between IPP and GIS Substation | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | Common |  | IFA | IFD |  |  | 2025-11-07 |  |  |  | 2025-11-27 |  |  |  | 2026-01-02 | [7 empty] | 372 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO |  |  |  |  | Open
462 | Later | S&L | SAU4005-G000-C__-&EEC-00789 | Technical Specifications for DCS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFP |  |  | 2025-08-11 14:00 |  |  |  | 2025-08-31 14:00 |  |  |  | 2025-10-06 14:00 | [7 empty] | 845 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
463 | Later | S&L | SAU4005-G000-C__-&EEC-00790 | Technical Specifications for Field Instruments | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | I&C&DCS | Instrumentation & Control | Common |  | IFA | IFP |  |  | 2025-11-06 |  |  |  | 2025-11-26 |  |  |  | 2026-01-01 | [7 empty] | 836 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Common
464 | Later | S&L | SAU4005-G000-C__-&EEC-00791 | Technical Specifications for Pneumatic On/Off & Modulating Control Valves and Accessories | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | I&C&DCS | Instrumentation & Control | Common |  | IFA | IFP |  |  | 2025-10-10 17:30 |  |  |  | 2025-10-30 17:30 |  |  |  | 2025-12-05 17:30 | [7 empty] | 479 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
465 | Later | S&L | SAU4005-G000-C__-&EEC-00792 | Technical Specifications for SWAS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFP |  |  | 2025-09-19 |  |  |  | 2025-10-09 |  |  |  | 2025-11-13 | [7 empty] | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
466 | Later | S&L | SAU4005-G000-C__-&EEC-00794 | Technical Specifications for Vibration measurement system | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFP |  |  | 2025-06-24 |  |  |  | 2025-07-14 |  |  |  | 2025-08-19 | [7 empty] | 500 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
467 | Later | S&L | SAU4005-G000-C__-&EEC-00795 | Technical Specifications for Weather Station | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFP |  |  | 2025-12-29 |  |  |  | 2026-01-18 |  |  |  | 2026-02-22 | [7 empty] | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Common
468 | Later | S&L | SAU4005-G000-C__-&EEC-00796 | Technical Specifications for I & C Cable | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | I&C&DCS | Instrumentation & Control | Common |  | IFA | IFP |  |  | 2025-06-06 |  |  |  | 2025-06-26 |  |  |  | 2025-08-01 | [7 empty] | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
469 | Later | S&L | SAU4005-G000-C__-&EEC-00799 | Technical Specifications for Junction Box & Transmitter rack | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | I&C&DCS | Instrumentation & Control | Common |  | IFA | IFP |  |  | 2025-12-06 |  |  |  | 2025-12-26 |  |  |  | 2026-01-31 | [7 empty] | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
470 | Later | S&L | SAU4005-G000-C__-&EEC-00800 | Technical Specifications for Plant Security System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFP |  |  | 2025-11-06 |  |  |  | 2025-11-26 |  |  |  | 2025-12-31 | [7 empty] | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
471 | Later | S&L | SAU4005-G000-C__-&EEC-00841 | Technical Specifications for Plant Settlement System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFP |  |  | 2025-09-20 |  |  |  | 2025-10-13 |  |  |  | 2025-11-17 | [7 empty] | 434 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Common
472 | Later | S&L | SAU4005-G000-C__-&EEC-00849 | Technical Specification of CCTV | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFP |  |  | 2025-09-29 |  |  |  | 2025-10-19 |  |  |  | 2025-11-23 | [7 empty] | 211 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
473 | Later | S&L | SAU4005-G000-UER-&ELH-00862 | Equipment Layout For Gas Booster Electrical Switchgear Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-10-20 |  |  |  | 2025-11-09 |  |  |  | 2025-12-17 | [21 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | RESPECTIVE EM
474 | Later | S&L | SAU4005-G000-UYC-&ELH-00863 | Equipment Layout For Administration Electrical Room | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-09-20 |  |  |  | 2025-10-10 |  |  |  | 2025-11-17 | [21 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | RESPECTIVE EM
475 | Later | S&L | SAU4005-G000-U__-&CDB-00900 | Design Criteria Document for Civil, Structural, Architectural works | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-03-04 |  |  |  | 2025-03-29 |  |  |  | 2025-06-24 | [7 empty] | 726 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1 | NO |  | NO | Common
476 | Later | S&L | SAU4005-G000-U__-&CTA-00901 | Steel Standard drawings | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-04-03 |  |  |  | 2025-04-23 |  |  |  | 2025-07-29 | [7 empty] | 470 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
477 | Later | S&L | SAU4005-G000-U__-&CTA-00910 | Concrete standard drawings | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-04-03 |  |  |  | 2025-04-23 |  |  |  | 2025-07-29 | [7 empty] | 389 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
478 | Later | S&L | SAU4005-G000-U__-&CTA-00917 | Architectural Standard drawings | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-04-03 |  |  |  | 2025-04-23 |  |  |  | 2025-07-29 | [7 empty] | 470 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
479 | Later | S&L | SAU4005-G000-U__-&CTL-00926 | Site Grading - Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-05-14 |  |  |  | 2025-06-03 |  |  |  | 2025-07-08 | [7 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C1 | SEC | S1 | NO | Common
480 | Later | S&L | SAU4005-G000-GU_-&CED-00927 | Storm Water Drainage network Design calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-09-17 |  |  |  | 2025-10-07 |  |  |  | 2026-01-17 | [7 empty] | 609 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
481 | Later | S&L | SAU4005-G000-UGH-&CTB-00928 | Storm Water Drainage network - Layout and details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-09-02 |  |  |  | 2025-09-22 |  |  |  | 2026-01-17 | [7 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Common
482 | Later | S&L | SAU4005-G000-GT_-&CED-00929 | Evaporation Pond for Process Water - Design calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-08-01 |  |  |  | 2025-08-21 |  |  |  | 2026-01-07 | [7 empty] | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
483 | Later | S&L | SAU4005-G000-UGX-&CTB-00930 | Evaporation Pond for Process Water - Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-07-21 |  |  |  | 2025-08-10 |  |  |  | 2026-01-07 | [7 empty] | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
484 | Later | S&L | SAU4005-G000-GU_-&CED-00931 | Evaporation Pond for Storm Water - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-07-21 |  |  |  | 2025-08-10 |  |  |  | 2025-09-14 | [7 empty] | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
485 | Later | S&L | SAU4005-G000-UGH-&CTB-00932 | Evaporation Pond for Storm Water - Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-07-21 |  |  |  | 2025-08-10 |  |  |  | 2025-09-14 | [7 empty] | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
486 | Later | S&L | SAU4005-G000-UMB-&CED-00933 | Gas Turbine, Generator Unit-11, 12 & 13 Foundation - Design Calculation - Static & Dyanamic Analysis | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-08-01 |  |  |  | 2025-08-21 |  |  |  | 2025-12-25 | [7 empty] | 680 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Open
487 | Later | S&L | SAU4005-G000-UMB-&CLB-00934 | Gas Turbine, Generator & Auxiliaries Area - Overall Foundation Layout | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-12-12 |  |  |  | 2026-01-01 |  |  |  | 2026-02-05 | [7 empty] | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
488 | Later | S&L | SAU4005-G000-UMB-&CLB-00935 | Gas Turbine, Generator Unit-11, 12 & 13 Foundation Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-07-31 |  |  |  | 2025-08-20 |  |  |  | 2025-09-24 | [7 empty] | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
489 | Later | S&L | SAU4005-G000-UMB-&CLB-00936 | Gas Turbine, Generator Unit-11, 12 & 13 Foundation RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-08-01 |  |  |  | 2025-08-21 |  |  |  | 2026-01-19 | [7 empty] | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
490 | Later | S&L | SAU4005-G000-UMB-&CLB-00937 | Gas Turbine, Generator Unit-11, 12 & 13 Foundation Embedment Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-07-31 |  |  |  | 2025-08-20 |  |  |  | 2025-09-24 | [7 empty] | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
491 | Later | S&L | SAU4005-G000-UMB-&CTB-00938 | Gas Turbine, Generator & Auxiliaries Area Unit-11, 12 & 13 - Miscellaneous Platform details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-11-20 |  |  |  | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
492 | Later | S&L | SAU4005-G000-UMB-&CLB-00939 | Gas Turbine, Generator & Auxiliaries Area Unit-11, 12 & 13 - Miscellaneous foundation details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-11-20 |  |  |  | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
493 | Later | S&L | SAU4005-G000-UMB-&CED-01392 | Gas Turbine, Generator -11, 12 & 13 - Design calculation - RC Design | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-09-30 |  |  |  | 2025-10-20 |  |  |  | 2026-02-02 | [7 empty] | 680 | [13 empty] | WF Transmittal DI-EPC-ACWA |  | NO | NO | NO | NO |  | NO
494 | Later | S&L | SAU4005-G000-UMA-&CED-00940 | Steam Turbine, Generator Foundation - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-06 |  |  |  | 2026-02-26 |  |  |  | 2026-04-02 | [7 empty] | 871 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
495 | Later | S&L | SAU4005-G000-UMA-&CLB-00941 | Steam Turbine, Generator Foundation Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-12-29 |  |  |  | 2026-01-18 |  |  |  | 2026-04-20 | [7 empty] | 372 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
496 | Later | S&L | SAU4005-G000-UMA-&CLB-00942 | Steam Turbine, Generator Foundation RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-01-24 |  |  |  | 372 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
497 | Later | S&L | SAU4005-G000-UMA-&CLB-00943 | Steam Turbine, Generator Foundation Embedment Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-01-24 |  |  |  | 372 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
498 | Later | S&L | SAU4005-G000-UMA-&CED-00944 | STG Building Foundation - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-04-06 |  |  |  | 2026-04-26 |  |  |  | 2026-05-31 | [7 empty] | 1150 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
499 | Later | S&L | SAU4005-G000-UMA-&CED-00945 | STG Building Superstructure - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-13 |  |  |  | 2026-03-05 |  |  |  | 2026-06-04 | [7 empty] | 372 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
500 | Later | S&L | SAU4005-G000-UMA-&CED-00946 | STG Building Purlin and Girt - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-06 |  |  |  | 2026-02-26 |  |  |  | 2026-04-02 | [7 empty] | 372 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
501 | Later | S&L | SAU4005-G000-UMA-&CLH-00947 | STG Building - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-11-15 |  |  |  | 2025-12-05 |  |  |  | 2026-04-15 | [7 empty] | 1134 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
502 | Later | S&L | SAU4005-G000-UMA-&CLB-00948 | STG Building - Foundation& Pier Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-04-06 |  |  |  | 2026-04-26 |  |  |  | 2026-06-19 | [7 empty] | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
503 | Later | S&L | SAU4005-G000-UMA-&CLB-00949 | STG Building - Foundation& Pier RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-04-06 |  |  |  | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
504 | Later | S&L | SAU4005-G000-UMA-&CLH-00950 | STG Building - Grade Beam Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-02-06 |  |  |  | 2026-02-26 |  |  |  | 2026-06-04 | [7 empty] | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
505 | Later | S&L | SAU4005-G000-UMA-&CLH-00951 | STG Building - Base Plate Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-01-27 |  |  |  | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
506 | Later | S&L | SAU4005-G000-UMA-&CLH-00952 | STG Building - Framing Elevations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-02-06 |  |  |  | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
507 | Later | S&L | SAU4005-G000-UMA-&CLH-00953 | STG Building - Operation Floor Framing Plan and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-02-06 |  |  |  | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
508 | Later | S&L | SAU4005-G000-UMA-&CLH-00954 | STG Building - Crane Girder Layout & Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-01-27 |  |  |  | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
509 | Later | S&L | SAU4005-G000-UMA-&CLH-00955 | STG Building - Miscellaneous platforms -Layout & Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-03-18 |  |  |  | 2026-04-07 |  |  |  | 2026-06-10 | [7 empty] | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
510 | Later | S&L | SAU4005-G000-UMA-&CLH-00956 | STG Building - Roof Framing Plan and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-19 |  |  |  | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
511 | Later | S&L | SAU4005-G000-UMA-&CLH-00957 | STG Building - Purlin Plan and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-19 |  |  |  | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
512 | Later | S&L | SAU4005-G000-UMA-&CLH-00958 | STG Building - Girt Elevations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-19 |  |  |  | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
513 | Later | S&L | SAU4005-G000-UMA-&CLH-00959 | STG Building - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-18 |  |  |  | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
514 | Later | S&L | SAU4005-G000-UMA-&CLH-00960 | STG Building - Staircases Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-18 |  |  |  | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
515 | Later | S&L | SAU4005-G000-URC-&CED-00961 | ACC Foundation - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-08-16 |  |  |  | 2025-09-05 |  |  |  | 2025-10-10 | [7 empty] | 836 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
516 | Later | S&L | SAU4005-G000-URC-&CLB-00962 | ACC Foundation& Pier - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-08-16 |  |  |  | 2025-09-05 |  |  |  | 2025-10-10 | [7 empty] | 664 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
517 | Later | S&L | SAU4005-G000-UGA-&CED-00963 | Filtered Water & UF Water Storage Tank Foundation - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-03 |  |  |  | 2025-12-23 |  |  |  | 2026-01-27 | [7 empty] | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
518 | Later | S&L | SAU4005-G000-UGA-&CLB-00964 | Filtered Water & UF Water Storage Tank Foundation - Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-12-16 |  |  |  | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
519 | Later | S&L | SAU4005-G000-URX-&CED-00965 | Fin Fan Cooler CCCW system - Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-02 |  |  |  | 2025-12-22 |  |  |  | 2026-01-26 | [7 empty] | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
520 | Later | S&L | SAU4005-G000-URX-&CLB-00966 | Fin Fan Cooler CCCW system - Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-12-11 |  |  |  | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
521 | Later | S&L | SAU4005-G000-URX-&CED-00967 | Fin Fan Cooler (GBC Area) Foundation - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-02 |  |  |  | 2025-12-22 |  |  |  | 2026-01-26 | [7 empty] | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
522 | Later | S&L | SAU4005-G000-URX-&CLB-00968 | Fin Fan Cooler (GBC Area) Foundation layout and RC details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-12-11 |  |  |  | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
523 | Later | S&L | SAU4005-G000-UCA-&CED-00969 | Main Electrical & Control Building - Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-08-02 |  |  |  | 2025-08-22 |  |  |  | 2025-09-26 | [7 empty] | 687 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
524 | Later | S&L | SAU4005-G000-UCA-&CED-00970 | Main Electrical & Control Building - Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-08-02 |  |  |  | 2025-08-22 |  |  |  | 2025-09-26 | [7 empty] | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
525 | Later | S&L | SAU4005-G000-UCA-&CLH-00971 | Main Electrical & Control Building - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-07-15 |  |  |  | 2025-08-04 |  |  |  | 2026-05-12 | [7 empty] | 891 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
526 | Later | S&L | SAU4005-G000-UCA-&CLH-00972 | Main Electrical & Control Building - Toilet and False ceiling Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-09-23 |  |  |  | 360 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
527 | Later | S&L | SAU4005-G000-UCA-&CLB-00973 | Main Electrical & Control Building - Foundation and Column Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-08-02 |  |  |  | 360 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
528 | Later | S&L | SAU4005-G000-UCA-&CTL-00974 | Main Electrical & Control Building - Grade Beam Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-08-02 |  |  |  | 360 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
529 | Later | S&L | SAU4005-G000-UCA-&CTL-00975 | Main Electrical & Control Building - First Floor Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-09-04 |  |  |  | 360 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
530 | Later | S&L | SAU4005-G000-UCA-&CTL-00976 | Main Electrical & Control Building - Second Floor Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-09-04 |  |  |  | 360 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
531 | Later | S&L | SAU4005-G000-UCA-&CTL-00977 | Main Electrical & Control Building - Roof Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-09-04 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
532 | Later | S&L | SAU4005-G000-UCA-&CTL-00978 | Main Electrical & Control Building - Staircase -1 Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-09-24 |  |  |  | 360 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
533 | Later | S&L | SAU4005-G000-UCA-&CTL-00979 | Main Electrical & Control Building - Staircase -2 Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-01-24 |  |  |  | 360 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
534 | Later | S&L | SAU4005-G000-UCA-&CTL-00980 | Main Electrical & Control Building - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-05 |  |  |  | 360 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
535 | Later | S&L | SAU4005-G000-UHA-&CED-00988 | HRSG Unit - 11, 12 & 13 Foundation - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-07-31 |  |  |  | 2025-08-20 |  |  |  | 2025-09-24 | [7 empty] | 1011 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
536 | Later | S&L | SAU4005-G000-UHA-&CLB-00989 | HRSG Unit - 11, 12 & 13 Foundation - Layout and details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-07-18 |  |  |  | 2025-08-07 |  |  |  | 2025-09-11 | [7 empty] | 615 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
537 | Later | S&L | SAU4005-G000-UHA-&CLB-00990 | HRSG Unit - 11, 12 & 13 Foundation - RC details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-07-30 |  |  |  | 615 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
538 | Later | S&L | SAU4005-G000-UHA-&CLB-00991 | HRSG Unit - 11, 12 & 13 Miscellaneous Foundation - Layout and RC details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-11-15 |  |  |  | 615 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
539 | Later | S&L | SAU4005-G000-UYC-&CED-00992 | Administration & Social Building - Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-08-16 |  |  |  | 2025-09-05 |  |  |  | 2025-10-18 | [7 empty] | 249 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
540 | Later | S&L | SAU4005-G000-UYC-&CED-00993 | Administration & Social Building - Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-08-16 |  |  |  | 2025-09-05 |  |  |  | 2025-10-18 | [7 empty] | 249 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
541 | Later | S&L | SAU4005-G000-UYC-&CLH-00994 | Administration & Social Building - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-05-08 |  |  |  | 2025-05-28 |  |  |  | 2025-10-13 | [7 empty] | 654 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
542 | Later | S&L | SAU4005-G000-UYC-&CLH-00995 | Administration & Social Building - False ceiling Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-06-07 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
543 | Later | S&L | SAU4005-G000-UYC-&CLB-00996 | Administration & Social Building - Foundation & Column Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-08-16 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
544 | Later | S&L | SAU4005-G000-UYC-&CTL-00997 | Administration & Social Building - First Floor Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-08-16 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
545 | Later | S&L | SAU4005-G000-UYC-&CTL-00998 | Administration & Social Building - Roof Slabs Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-08-16 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
546 | Later | S&L | SAU4005-G000-UYC-&CTL-00999 | Administration & Social Building - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-08-16 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
547 | Later | S&L | SAU4005-G000-UYC-&CTL-01000 | Administration & Social Building - Staircases-1 Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-10-10 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
548 | Later | S&L | SAU4005-G000-UYC-&CTL-01001 | Administration & Social Building - Staircases-2 Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-10-10 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
549 | Later | S&L | SAU4005-G000-UYF-&CED-01002 | Security and Control center - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-05-12 |  |  |  | 2026-06-01 |  |  |  | 2026-07-06 | [7 empty] | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
550 | Later | S&L | SAU4005-G000-UYF-&CLH-01003 | Security and Control center - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-07-22 |  |  |  | 2025-08-11 |  |  |  | 2025-11-26 | [7 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
551 | Later | S&L | SAU4005-G000-UYF-&CLH-01004 | Security and Control center - Toilet and False ceiling Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-02-23 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
552 | Later | S&L | SAU4005-G000-UYF-&CLB-01005 | Security and Control center - Foundation and Column Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-05-26 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
553 | Later | S&L | SAU4005-G000-UYF-&CLH-01006 | Security and Control center - Roof Slabs Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-30 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
554 | Later | S&L | SAU4005-G000-UYF-&CLH-01007 | Security and Control center - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-08-04 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
555 | Later | S&L | SAU4005-G000-UST-&CED-01010 | Workshop and Warehouse Building - Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-09-02 |  |  |  | 2025-09-22 |  |  |  | 2026-05-11 | [7 empty] | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
556 | Later | S&L | SAU4005-G000-UST-&CED-01011 | Workshop and Warehouse Building - Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-10-09 |  |  |  | 2025-10-29 |  |  |  | 2026-05-11 | [7 empty] | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
557 | Later | S&L | SAU4005-G000-UST-&CLH-01012 | Workshop and Warehouse Building - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-07-16 |  |  |  | 2025-08-05 |  |  |  | 2026-05-04 | [7 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
558 | Later | S&L | SAU4005-G000-UST-&CLH-01013 | Workshop and Warehouse Building - Toilet and False ceiling Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-11-20 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
559 | Later | S&L | SAU4005-G000-UST-&CLB-01014 | Workshop and Warehouse Building - Foundation and Pier Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-10-09 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
560 | Later | S&L | SAU4005-G000-UST-&CTL-01015 | Workshop and Warehouse Building - Grade Beam Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-11-17 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
561 | Later | S&L | SAU4005-G000-UST-&CTB-01016 | Workshop and Warehouse Building - Base Plate and Framing Plan, Elevations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-12-23 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
562 | Later | S&L | SAU4005-G000-UST-&CTB-01491 | Workshop and Warehouse Building - Crane Girder Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-05-13 |  |  |  | 500 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
563 | Later | S&L | SAU4005-G000-UST-&CTB-01017 | Workshop and Warehouse Building - Purlin Plan and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-01-20 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
564 | Later | S&L | SAU4005-G000-UST-&CTB-01018 | Workshop and Warehouse Building - Girt Elevations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-01-21 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
565 | Later | S&L | SAU4005-G000-UST-&CTL-01019 | Workshop and Warehouse Building - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-12-29 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
566 | Later | S&L | SAU4005-G000-UGG-&CED-01020 | Potable Water Unloading Area - Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-06-01 |  |  |  | 2026-06-21 |  |  |  | 2026-07-26 | [7 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
567 | Later | S&L | SAU4005-G000-UGG-&CTL-01021 | Potable Water Unloading Area - Layout and RC details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-11 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
568 | Later | S&L | SAU4005-G000-UAG-&CLB-01023 | Transformer Yard Area - Miscellaneous foundations -Layout | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-24 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
569 | Later | S&L | SAU4005-G000-UAG-&CLB-01024 | Transformer Yard Area - Miscellaneous foundations -RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-24 |  |  |  | 285 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
570 | Later | S&L | SAU4005-G000-UBB-&CED-01025 | Generator Circuit Breaker Unit - 11, 12 & 13 - Supporting structure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-06-25 |  |  |  | 2026-07-15 |  |  |  | 2026-08-19 | [7 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
571 | Later | S&L | SAU4005-G000-UBB-&CLB-01026 | Generator Circuit Breaker Unit - 11, 12 & 13 - Supporting structure Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-10-13 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
572 | Later | S&L | SAU4005-G000-UBB-&CTB-01027 | Generator Circuit Breaker Unit - 11, 12 & 13 - Supporting structure Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-07-29 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
573 | Later | S&L | SAU4005-G000-UHX-&CTL-01032 | CEMS Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-24 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
574 | Later | S&L | SAU4005-G000-UQA-&CLB-01033 | CCCW Pumps - Foundation Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-12-01 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
575 | Later | S&L | SAU4005-G000-U__-&CLB-01034 | Miscellaneous Equipment Foundations within Plant boundary - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-05-16 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
576 | Later | S&L | SAU4005-G000-UEN-&CLB-01036 | Fuel Gas Regulating station foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-10-31 |  |  |  | 2025-11-20 |  |  |  | 2025-12-25 | [7 empty] | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
577 | Later | S&L | SAU4005-G000-ULA-&CED-01037 | Feed Water Pumps - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-04-07 |  |  |  | 2026-04-27 |  |  |  | 2026-06-01 | [7 empty] | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
578 | Later | S&L | SAU4005-G000-ULA-&CLB-01038 | Feed Water Pumps - Over all Foundation Layout | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-04-18 |  |  |  | 2026-05-08 |  |  |  | 2026-06-12 | [7 empty] | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
579 | Later | S&L | SAU4005-G000-ULA-&CLB-01039 | Feed Water Pumps - Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-05-25 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
580 | Later | S&L | SAU4005-G000-ULC-&CLB-01040 | Condensate Water Pumps Foundation - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-12-24 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
581 | Later | S&L | SAU4005-G000-ULC-&CLB-01041 | Condensate receiving tank foundation layout and RC details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-12-31 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
582 | Later | S&L | SAU4005-G000-ULC-&CTL-01042 | Condensate receiving pump skids layout and RC details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-01-03 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
583 | Later | S&L | SAU4005-G000-ULC-&CED-01043 | Flash Tanks / Boiler Blow Off Tanks Foundation - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-04-16 |  |  |  | 2026-05-06 |  |  |  | 2026-06-10 | [7 empty] | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
584 | Later | S&L | SAU4005-G000-ULC-&CLB-01044 | Flash Tanks / Boiler Blow Off Tanks Foundation - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-04-16 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
585 | Later | S&L | SAU4005-G000-ULC-&CTL-01045 | Condensate receiver drain tank sump - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-01-27 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
586 | Later | S&L | SAU4005-G000-USG-&CED-01047 | Fire Water Pump House - Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-30 |  |  |  | 2025-12-20 |  |  |  | 2026-04-06 | [7 empty] | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
587 | Later | S&L | SAU4005-G000-USG-&CLH-01048 | Fire Water Pump House - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-09-30 |  |  |  | 2025-10-20 |  |  |  | 2026-04-04 | [7 empty] | 547 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
588 | Later | S&L | SAU4005-G000-USG-&CLB-01049 | Fire Water Pump House - Foundation & Pier Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-11-30 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
589 | Later | S&L | SAU4005-G000-USG-&CTB-01050 | Fire Water Pump House - Superstructure Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-11-30 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
590 | Later | S&L | SAU4005-G000-USG-&CTL-01051 | Fire Water Pump House - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-12-31 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
591 | Later | S&L | SAU4005-G000-USC-&CED-01052 | Air Compressor Shed - Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-10-24 |  |  |  | 2025-11-13 |  |  |  | 2026-01-05 | [7 empty] | 453 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
592 | Later | S&L | SAU4005-G000-USC-&CLH-01053 | Air Compressor Shed - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-08-02 |  |  |  | 2025-08-22 |  |  |  | 2026-01-28 | [7 empty] | 713 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
593 | Later | S&L | SAU4005-G000-USC-&CLB-01054 | Air Compressor Shed - Foundation & Pier - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-11-04 |  |  |  | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
594 | Later | S&L | SAU4005-G000-USC-&CTB-01055 | Air Compressor Shed - Superstructure Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-11-05 |  |  |  | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
595 | Later | S&L | SAU4005-G000-USC-&CTL-01056 | Air Compressor Shed - Grade Slab - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-02-04 |  |  |  | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
596 | Later | S&L | SAU4005-G000-USC-&CTL-01058 | Drain Oil Tank - Layout and RC Detail | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-10-08 |  |  |  | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
597 | Later | S&L | SAU4005-G000-UTG-&CED-01059 | Cylinder Storage Shed - Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-12-09 |  |  |  | 2026-12-29 |  |  |  | 2027-02-02 | [7 empty] | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
598 | Later | S&L | SAU4005-G000-UTG-&CLH-01060 | Cylinder Storage Shed - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-05-12 |  |  |  | 547 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
599 | Later | S&L | SAU4005-G000-UTG-&CLB-01061 | Cylinder Storage Shed - Foundation & Pier Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-12-23 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
600 | Later | S&L | SAU4005-G000-UTG-&CTB-01062 | Cylinder Storage Shed - Superstructure Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2027-01-22 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
601 | Later | S&L | SAU4005-G000-UTG-&CTL-01063 | Cylinder Storage Shed - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2027-03-08 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
602 | Later | S&L | SAU4005-G000-UGD-&CED-01064 | Water and Effluent treatment building - Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-02 |  |  |  | 2025-12-22 |  |  |  | 2026-01-26 | [7 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
603 | Later | S&L | SAU4005-G000-UGD-&CED-01065 | Water and Effluent treatment building - Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-01-07 |  |  |  | 2026-01-27 |  |  |  | 2026-03-03 | [7 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
604 | Later | S&L | SAU4005-G000-UGD-&CLH-01066 | Water and Effluent treatment building - Architectural Layout & Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-09-19 |  |  |  | 2025-10-15 |  |  |  | 2026-01-30 | [7 empty] | 745 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
605 | Later | S&L | SAU4005-G000-UGD-&CLB-01067 | Water and Effluent treatment building - Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-12-02 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
606 | Later | S&L | SAU4005-G000-UGD-&CTL-01068 | Water and Effluent treatment building - Crane Girder Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-01-31 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
607 | Later | S&L | SAU4005-G000-UGD-&CTL-01069 | Water and Effluent treatment building - Framing Plan and Elevation Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-01-31 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
608 | Later | S&L | SAU4005-G000-UGD-&CTL-01070 | Water and Effluent treatment building - Side Runner and Purlin Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-02-23 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
609 | Later | S&L | SAU4005-G000-UGD-&CTL-01071 | Water and Effluent treatment building - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-18 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
610 | Later | S&L | SAU4005-G000-UGD-&CED-01072 | DM Water storage tank Foundation - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-01-18 |  |  |  | 2026-02-07 |  |  |  | 2026-03-14 | [7 empty] | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
611 | Later | S&L | SAU4005-G000-UGD-&CLB-01073 | DM Water storage tank Foundation - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-01-18 |  |  |  | 2026-02-07 |  |  |  | 2026-03-14 | [7 empty] | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
612 | Later | S&L | SAU4005-G000-UGF-&CED-01074 | Service and Fire Water Tank foundation - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-09 |  |  |  | 2025-12-29 |  |  |  | 2026-02-02 | [7 empty] | 512 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
613 | Later | S&L | SAU4005-G000-UGF-&CLB-01075 | Service and Fire Water Tank foundation - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-12-09 |  |  |  | 2025-12-29 |  |  |  | 2026-02-02 | [7 empty] | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
614 | Later | S&L | SAU4005-G000-UZT-&CED-01076 | Pipe Rack PR-01 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-10-29 |  |  |  | 2025-11-18 |  |  |  | 2026-01-19 | [7 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
615 | Later | S&L | SAU4005-G000-UZT-&CED-01077 | Pipe Rack PR-01 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-09-20 |  |  |  | 2025-10-10 |  |  |  | 2025-11-14 | [7 empty] | 599 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
616 | Later | S&L | SAU4005-G000-UZT-&CLB-01078 | Pipe Rack PR-01 : Foundation Pier Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-11-10 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
617 | Later | S&L | SAU4005-G000-UZT-&CTB-01079 | Pipe Rack PR-01 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-09-20 |  |  |  | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
618 | Later | S&L | SAU4005-G000-UZT-&CED-01080 | Pipe Rack PR-02 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-17 |  |  |  | 2025-12-07 |  |  |  | 2026-01-11 | [7 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
619 | Later | S&L | SAU4005-G000-UZT-&CED-01081 | Pipe Rack PR-02 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-09-20 |  |  |  | 2025-10-10 |  |  |  | 2025-11-14 | [7 empty] | 599 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
620 | Later | S&L | SAU4005-G000-UZT-&CLB-01082 | Pipe Rack PR-02 : Foundation Pier Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-11-28 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
621 | Later | S&L | SAU4005-G000-UZT-&CTB-01083 | Pipe Rack PR-02 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-09-20 |  |  |  | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
622 | Later | S&L | SAU4005-G000-UZT-&CED-01084 | Pipe Rack PR-03 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-04 |  |  |  | 2025-11-24 |  |  |  | 2025-12-29 | [7 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
623 | Later | S&L | SAU4005-G000-UZT-&CED-01085 | Pipe Rack PR-03 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-10-20 |  |  |  | 2025-11-09 |  |  |  | 2025-12-14 | [7 empty] | 599 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
624 | Later | S&L | SAU4005-G000-UZT-&CLB-01086 | Pipe Rack PR-03 : Foundation Pier Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-11-04 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
625 | Later | S&L | SAU4005-G000-UZT-&CTB-01087 | Pipe Rack PR-03 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-10-27 |  |  |  | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
626 | Later | S&L | SAU4005-G000-UZT-&CED-01088 | Pipe Rack PR-04 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-12 |  |  |  | 2026-01-01 |  |  |  | 2026-02-05 | [7 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
627 | Later | S&L | SAU4005-G000-UZT-&CED-01089 | Pipe Rack PR-04 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-09-30 |  |  |  | 2025-10-20 |  |  |  | 2025-12-19 | [7 empty] | 599 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
628 | Later | S&L | SAU4005-G000-UZT-&CLB-01090 | Pipe Rack PR-04 : Foundation Pier Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-12-26 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
629 | Later | S&L | SAU4005-G000-UZT-&CTB-01091 | Pipe Rack PR-04 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-10-27 |  |  |  | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
630 | Later | S&L | SAU4005-G000-UZT-&CED-01092 | Pipe sleeper - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-12 |  |  |  | 2026-01-01 |  |  |  | 2026-02-05 | [7 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
631 | Later | S&L | SAU4005-G000-UZT-&CTB-01093 | Pipe sleeper Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-12-25 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
632 | Later | S&L | SAU4005-G000-UZT-&CED-01394 | Pipe Rack PR-05 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-20 |  |  |  | 2025-12-10 |  |  |  | 2026-01-14 | [7 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
633 | Later | S&L | SAU4005-G000-UZT-&CED-01395 | Pipe Rack PR-05 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-10-23 |  |  |  | 2025-11-12 |  |  |  | 2025-12-17 | [7 empty] | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
634 | Later | S&L | SAU4005-G000-UZT-&CLB-01396 | Pipe Rack PR-05 : Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-11-20 |  |  |  | 434 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
635 | Later | S&L | SAU4005-G000-UZT-&CTB-01397 | Pipe Rack PR-05 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-10-23 |  |  |  | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
636 | Later | S&L | SAU4005-G000-UZT-&CED-01398 | Pipe Rack PR-06 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-20 |  |  |  | 2025-12-10 |  |  |  | 2026-01-14 | [7 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
637 | Later | S&L | SAU4005-G000-UZT-&CED-01399 | Pipe Rack PR-06 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-10-23 |  |  |  | 2025-11-12 |  |  |  | 2025-12-17 | [7 empty] | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
638 | Later | S&L | SAU4005-G000-UZT-&CLB-01400 | Pipe Rack PR-06 : Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-11-20 |  |  |  | 434 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
639 | Later | S&L | SAU4005-G000-UZT-&CTB-01401 | Pipe Rack PR-06 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-10-23 |  |  |  | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
640 | Later | S&L | SAU4005-G000-UZT-&CED-01402 | Pipe Rack PR-07 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-20 |  |  |  | 2025-12-10 |  |  |  | 2026-01-14 | [7 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
641 | Later | S&L | SAU4005-G000-UZT-&CED-01403 | Pipe Rack PR-07 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-10-23 |  |  |  | 2025-11-12 |  |  |  | 2025-12-17 | [7 empty] | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
642 | Later | S&L | SAU4005-G000-UZT-&CLB-01404 | Pipe Rack PR-07 : Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-11-20 |  |  |  | 434 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
643 | Later | S&L | SAU4005-G000-UZT-&CTB-01405 | Pipe Rack PR-07 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-10-23 |  |  |  | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
644 | Later | S&L | SAU4005-G000-UZT-&CED-01497 | Pipe Rack PR-08 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-29 |  |  |  | 2026-01-18 |  |  |  | 2026-02-22 | [7 empty] | 500 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
645 | Later | S&L | SAU4005-G000-UZT-&CED-01498 | Pipe Rack PR-08 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-20 |  |  |  | 2025-12-10 |  |  |  | 2026-01-14 | [7 empty] | 550 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
646 | Later | S&L | SAU4005-G000-UZT-&CLB-01499 | Pipe Rack PR-08 : Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-12-29 |  |  |  | 450 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
647 | Later | S&L | SAU4005-G000-UZT-&CTB-01500 | Pipe Rack PR-08 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-11-20 |  |  |  | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
648 | Later | S&L | SAU4005-G000-UZT-&CED-01410 | Pipe Rack PR-09 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-25 |  |  |  | 2026-01-14 |  |  |  | 2026-02-18 | [7 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
649 | Later | S&L | SAU4005-G000-UZT-&CED-01411 | Pipe Rack PR-09 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-19 |  |  |  | 2026-01-08 |  |  |  | 2026-02-12 | [7 empty] | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
650 | Later | S&L | SAU4005-G000-UZT-&CLB-01412 | Pipe Rack PR-09 : Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-12-25 |  |  |  | 434 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
651 | Later | S&L | SAU4005-G000-UZT-&CTB-01413 | Pipe Rack PR-09 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-12-19 |  |  |  | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
652 | Later | S&L | SAU4005-G000-UZT-&CED-01414 | Pipe Rack PR-10 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-25 |  |  |  | 2026-01-14 |  |  |  | 2026-02-18 | [7 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
653 | Later | S&L | SAU4005-G000-UZT-&CED-01415 | Pipe Rack PR-10 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-19 |  |  |  | 2026-01-08 |  |  |  | 2026-02-12 | [7 empty] | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
654 | Later | S&L | SAU4005-G000-UZT-&CLB-01416 | Pipe Rack PR-10 : Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-12-25 |  |  |  | 444 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
655 | Later | S&L | SAU4005-G000-UZT-&CTB-01417 | Pipe Rack PR-10 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-12-19 |  |  |  | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
656 | Later | S&L | SAU4005-G000-UZT-&CED-01418 | Pipe Rack PR-11 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-04-13 |  |  |  | 2026-05-03 |  |  |  | 2026-06-07 | [7 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
657 | Later | S&L | SAU4005-G000-UZT-&CED-01419 | Pipe Rack PR-11 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-03-29 |  |  |  | 2026-04-18 |  |  |  | 2026-05-23 | [7 empty] | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
658 | Later | S&L | SAU4005-G000-UZT-&CLB-01420 | Pipe Rack PR-11 : Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-04-13 |  |  |  | 434 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
659 | Later | S&L | SAU4005-G000-UZT-&CTB-01421 | Pipe Rack PR-11 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-29 |  |  |  | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
660 | Later | S&L | SAU4005-G000-UZT-&CED-01422 | Pipe Rack PR-12 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-03-14 |  |  |  | 2026-04-03 |  |  |  | 2026-05-08 | [7 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
661 | Later | S&L | SAU4005-G000-UZT-&CED-01423 | Pipe Rack PR-12 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-03-01 |  |  |  | 2026-03-21 |  |  |  | 2026-04-25 | [7 empty] | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
662 | Later | S&L | SAU4005-G000-UZT-&CLB-01424 | Pipe Rack PR-12 : Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-14 |  |  |  | 434 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
663 | Later | S&L | SAU4005-G000-UZT-&CTB-01425 | Pipe Rack PR-12 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-01 |  |  |  | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
664 | Later | S&L | SAU4005-G000-UZT-&CED-01440 | Pipe Rack PR-13 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-04-03 |  |  |  | 2026-04-23 |  |  |  | 2026-05-28 | [7 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
665 | Later | S&L | SAU4005-G000-UZT-&CED-01441 | Pipe Rack PR-13 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-03-14 |  |  |  | 2026-04-03 |  |  |  | 2026-05-08 | [7 empty] | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
666 | Later | S&L | SAU4005-G000-UZT-&CLB-01442 | Pipe Rack PR-13 : Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-04-03 |  |  |  | 434 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
667 | Later | S&L | SAU4005-G000-UZT-&CTB-01443 | Pipe Rack PR-13 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-14 |  |  |  | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
668 | Later | S&L | SAU4005-G000-UZT-&CED-01426 | Cable Rack CR-01 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-09 |  |  |  | 2026-03-01 |  |  |  | 2026-04-05 | [7 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
669 | Later | S&L | SAU4005-G000-UZT-&CED-01427 | Cable Rack CR-01 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-01-12 |  |  |  | 2026-02-01 |  |  |  | 2026-03-08 | [7 empty] | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
670 | Later | S&L | SAU4005-G000-UZT-&CLB-01428 | Cable Rack CR-01 : Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-02-09 |  |  |  | 434 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
671 | Later | S&L | SAU4005-G000-UZT-&CTB-01429 | Cable Rack CR-01 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-01-12 |  |  |  | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
672 | Later | S&L | SAU4005-G000-UZT-&CED-01430 | Cable Rack CR-02 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-09 |  |  |  | 2026-03-01 |  |  |  | 2026-04-05 | [7 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
673 | Later | S&L | SAU4005-G000-UZT-&CED-01431 | Cable Rack CR-02 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-01-12 |  |  |  | 2026-02-01 |  |  |  | 2026-03-08 | [7 empty] | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
674 | Later | S&L | SAU4005-G000-UZT-&CLB-01432 | Cable Rack CR-02 : Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-02-09 |  |  |  | 434 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
675 | Later | S&L | SAU4005-G000-UZT-&CTB-01433 | Cable Rack CR-02 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-01-12 |  |  |  | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
676 | Later | S&L | SAU4005-G000-U__-&CED-01094 | Miscellaneous Sumps and Pits Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-09-08 |  |  |  | 2026-09-28 |  |  |  | 2026-12-04 | [7 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
677 | Later | S&L | SAU4005-G000-U__-&CTB-01095 | Miscellaneous Sumps and Pits Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-09-21 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
678 | Later | S&L | SAU4005-G000-UGE-&CED-01489 | Neutralisation pits Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-08-17 |  |  |  | 2026-09-06 |  |  |  | 2026-10-11 | [7 empty] | 500 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
679 | Later | S&L | SAU4005-G000-UGE-&CTB-01096 | Neutralisation pits for DM Plant Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-01-12 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
680 | Later | S&L | SAU4005-G000-UTS-&CTB-01097 | Chemical Storage Building Pits Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2027-01-02 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
681 | Later | S&L | SAU4005-G000-UTS-&CED-01098 | Chemical Storage Building for Water and Effluent Treatment System - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-07-22 |  |  |  | 2026-08-11 |  |  |  | 2026-09-15 | [7 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
682 | Later | S&L | SAU4005-G000-UTS-&CLH-01099 | Chemical Storage Building for Water and Effluent Treatment System - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-14 |  |  |  | 641 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
683 | Later | S&L | SAU4005-G000-UTS-&CLB-01100 | Chemical Storage Building for Water and Effluent Treatment System - Foundation & Column Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-10-16 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
684 | Later | S&L | SAU4005-G000-UTS-&CTL-01102 | Chemical Storage Building for Water and Effluent Treatment System - Roof Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-05-20 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
685 | Later | S&L | SAU4005-G000-UTS-&CTL-01103 | Chemical Storage Building for Water and Effluent Treatment System - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-08 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
686 | Later | S&L | SAU4005-G000-UGV-&CED-01110 | Sewage Treatment Plant Area - Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-06-24 |  |  |  | 2026-07-14 |  |  |  | 2026-08-18 | [7 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
687 | Later | S&L | SAU4005-G000-UGV-&CLB-01111 | Sewage Treatment Plant Area - Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-07-22 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
688 | Later | S&L | SAU4005-G000-UGX-&CED-01112 | Oil Water Separator (underground tank) Foundation - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-04-03 |  |  |  | 2026-04-23 |  |  |  | 2026-05-28 | [7 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
689 | Later | S&L | SAU4005-G000-UGX-&CLB-01113 | Oil Water Separator (underground tank) Foundation - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-04-16 |  |  |  | 2026-05-06 |  |  |  | 2026-06-10 | [7 empty] | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
690 | Later | S&L | SAU4005-G000-UER-&CED-01119 | Fuel Gas Compressor Foundation - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-18 |  |  |  | 2025-12-08 |  |  |  | 2026-01-12 | [7 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
691 | Later | S&L | SAU4005-G000-UER-&CLB-01120 | Fuel Gas Compressor Foundation - RC details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-11-18 |  |  |  | 2025-12-08 |  |  |  | 2026-01-12 | [7 empty] | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
692 | Later | S&L | SAU4005-G000-UZA-&CED-01122 | Roads - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-08-04 |  |  |  | 2025-08-24 |  |  |  | 2025-09-28 | [7 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
693 | Later | S&L | SAU4005-G000-UZA-&CTL-01123 | Roads & Surfacing - Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-08-18 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C1 | NO |  | Yes | Common
694 | Later | S&L | SAU4005-G000-UZA-&CED-01124 | Culvert, Retaining Walls and Road Crossings - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-10-20 |  |  |  | 2025-11-09 |  |  |  | 2025-12-14 | [7 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
695 | Later | S&L | SAU4005-G000-UZA-&CTL-01125 | Culvert, Retaining Walls and Road Crossings - Layout and RC details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-11-04 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
696 | Later | S&L | SAU4005-G000-UZA-&CED-01126 | Process / Oily Water Drainage - Crossings Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-04-06 |  |  |  | 2026-04-26 |  |  |  | 2026-06-12 | [7 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Common
697 | Later | S&L | SAU4005-G000-UGX-&CTL-01127 | Process / Oily Water Drainage - Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-04-18 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
698 | Later | S&L | SAU4005-G000-UZT-&CTB-01128 | Pipe/Cable Trench - Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-01-22 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
699 | Later | S&L | SAU4005-G000-UZJ-&CTL-01129 | Boundary Wall/Fencing - Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-10-14 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C1 | SEC | S1 | NO | Common
700 | Later | S&L | SAU4005-G000-UGF-&CLB-01130 | DV Shed - Foundation Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-08-12 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
701 | Later | S&L | SAU4005-G000-UZT-&CTL-01131 | Duct Bank - Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-05-26 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
702 | Later | S&L | SAU4005-G000-UMB-&CTL-01133 | GT & HRSG area Pavements - Layout & Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-10-20 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
703 | Later | S&L | SAU4005-G000-URC-&CTL-01134 | ACC area Pavements - Layout & Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-04-10 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
704 | Later | S&L | SAU4005-G000-U__-&CTL-01135 | BOP area Pavements - Layout & Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-07-07 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
705 | Later | S&L | SAU4005-G000-U__-&CTL-01136 | Misc Area Pavements - Layout & Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-08-24 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
706 | Later | S&L | SAU4005-G000-U__-&CTL-01389 | Property Line Storm Water Interface | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-08-25 |  |  |  | 201 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C1 | SEC | S1,S2,S5,S8 | NO
707 | Later | S&L | SAU4005-G000-UZA-&CTB-01391 | Road Cross Section Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-08-25 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA |  | NO | NO | NO | NO |  | NO
708 | Later | S&L | SAU4005-G000-UGV-&CED-01137 | Sanitary System - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-06-24 |  |  |  | 2026-07-14 |  |  |  | 2026-08-18 | [7 empty] | 450 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
709 | Later | S&L | SAU4005-G000-UGV-&CTB-01138 | Sanitary System - Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-07-09 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
710 | Later | S&L | SAU4005-G000-URC-&CED-01139 | ACC Duct Foundation - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-01-01 |  |  |  | 2026-01-21 |  |  |  | 2026-02-25 | [7 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
711 | Later | S&L | SAU4005-G000-URC-&CTB-01140 | ACC Duct Foundation - Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-01-13 |  |  |  | 2026-02-02 |  |  |  | 2026-03-09 | [7 empty] | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
712 | Later | S&L | SAU4005-G000-UGV-&CED-01141 | Lifting Station - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-10-22 |  |  |  | 2026-11-11 |  |  |  | 2026-12-16 | [7 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
713 | Later | S&L | SAU4005-G000-UGV-&CTB-01142 | Lifting Station - Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-11-06 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
714 | Later | S&L | SAU4005-G000-UZD-&CTL-01143 | Car Parking Area (Open) - Paving Layout & Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-08-10 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
715 | Later | S&L | SAU4005-G000-UZD-&CED-01144 | Car Parking Shed - Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFD | [14 empty] | 2026-05-18 |  |  |  | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
716 | Later | S&L | SAU4005-G000-UZD-&CTB-01145 | Car Parking Shed - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-04-10 |  |  |  | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
717 | Later | S&L | SAU4005-G000-UZD-&CLB-01146 | Car Parking Shed - Foundation & Pier- Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-05-30 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
718 | Later | S&L | SAU4005-G000-UZD-&CTB-01147 | Car Parking Shed - Superstructure Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-07-04 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
719 | Later | S&L | SAU4005-G000-UZD-&CTL-01148 | Car Parking Shed - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-08-10 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
720 | Later | S&L | SAU4005-G000-UTH-&CED-01149 | Auxiliary boiler - Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-19 |  |  |  | 2026-01-08 |  |  |  | 2026-03-13 | [7 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
721 | Later | S&L | SAU4005-G000-UTH-&CLB-01150 | Auxiliary boiler - Foundation Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-01-01 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
722 | Later | S&L | SAU4005-G000-UMB-&CED-01151 | GT Bypass Stack Unit - 11, 12 & 13 Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-09-05 |  |  |  | 2025-09-25 |  |  |  | 2025-10-30 | [7 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
723 | Later | S&L | SAU4005-G000-UMB-&CLB-01152 | GT Bypass Stack Unit - 11, 12 & 13 Foundation Layout & Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-09-17 |  |  |  | 2025-10-07 |  |  |  | 2025-11-11 | [7 empty] | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
724 | Later | S&L | SAU4005-G000-U__-&CLB-01153 | Power Cycle Chemical Dosing Container - Foundation Layout and RC details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-07-02 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
725 | Later | S&L | SAU4005-G000-U__-&CLB-01154 | SWAS - Foundation Layout and RC details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-07-27 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
726 | Later | S&L | SAU4005-G000-UBF-&CED-01162 | GT Unit - 11, 12 & 13 Generator Step-Up Transformer Foundation - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-01 |  |  |  | 2025-11-21 |  |  |  | 2025-12-26 | [7 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
727 | Later | S&L | SAU4005-G000-UBF-&CLB-01163 | GT Unit - 11, 12 & 13 Generator Step-Up Transformer Foundation - Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-11-01 |  |  |  | 2025-11-21 |  |  |  | 2025-12-26 | [7 empty] | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
728 | Later | S&L | SAU4005-G000-UBF-&CED-01164 | Unit Auxiliary, Excitation and Isolation Transformer Foundation - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-23 |  |  |  | 2026-01-12 |  |  |  | 2026-02-16 | [7 empty] | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
729 | Later | S&L | SAU4005-G000-UBF-&CLB-01165 | Unit Auxiliary, Excitation and Isolation Foundation - Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-01-02 |  |  |  | 2026-01-22 |  |  |  | 2026-02-26 | [7 empty] | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
730 | Later | S&L | SAU4005-G000-UBH-&CED-01166 | GT Unit - 11, 12 & 13 & 4 Transformer Oil Collection Pits - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-06-16 |  |  |  | 2026-07-06 |  |  |  | 2026-08-25 | [7 empty] | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
731 | Later | S&L | SAU4005-G000-UBH-&CTL-01167 | GT Unit - 11, 12 & 13 & 4 Transformer Oil Collection Pits - Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-29 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
732 | Later | S&L | SAU4005-G000-UBH-&CED-01168 | ST Transformer Oil Collection Pit - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-08-20 |  |  |  | 2026-09-09 |  |  |  | 2026-10-17 | [7 empty] | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
733 | Later | S&L | SAU4005-G000-UBH-&CTL-01169 | ST Transformer Oil Collection Pit - Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-09-03 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
734 | Later | S&L | SAU4005-G000-UBF-&CED-01170 | ST-Generator Step-Up Transformer Foundation - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-17 |  |  |  | 2026-01-06 |  |  |  | 2026-02-10 | [7 empty] | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
735 | Later | S&L | SAU4005-G000-UBF-&CLB-01171 | ST-Generator Step-Up Transformer Foundation - Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-12-24 |  |  |  | 2026-01-13 |  |  |  | 2026-02-17 | [7 empty] | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
736 | Later | S&L | SAU4005-G000-UBF-&CED-01174 | GT- TRANSFORMER AREA - IPBD Supports, paving, rail foundation Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-07-01 |  |  |  | 2026-07-21 |  |  |  | 2026-08-25 | [7 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
737 | Later | S&L | SAU4005-G000-UBF-&CLB-01175 | GT- TRANSFORMER AREA - IPBD Supports, paving, rail foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-07-13 |  |  |  | 207 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
738 | Later | S&L | SAU4005-G000-UBF-&CED-01176 | ST- TRANSFORMER AREA - IPBD Supports, paving, rail foundation Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-07-14 |  |  |  | 2026-08-03 |  |  |  | 2026-09-07 | [7 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
739 | Later | S&L | SAU4005-G000-UBF-&CLB-01177 | ST- TRANSFORMER AREA - IPBD Supports, paving, rail foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-07-24 |  |  |  | 207 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
740 | Later | S&L | SAU4005-G000-UBA-&CED-01178 | STG and Auxiliary Boiler Electrical Building - Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-05-07 |  |  |  | 2026-05-27 |  |  |  | 2026-07-01 | [7 empty] | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
741 | Later | S&L | SAU4005-G000-UBA-&CED-01179 | STG and Auxiliary Boiler Electrical Building - Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-06-10 |  |  |  | 2026-06-30 |  |  |  | 2026-08-04 | [7 empty] | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
742 | Later | S&L | SAU4005-G000-UBA-&CTB-01180 | STG and Auxiliary Boiler Electrical Building - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-04-21 |  |  |  | 2026-05-11 |  |  |  | 2026-06-15 | [7 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
743 | Later | S&L | SAU4005-G000-UBA-&CLB-01182 | STG and Auxiliary Boiler Electrical Building - Foundation and Column Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-05-20 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
744 | Later | S&L | SAU4005-G000-UBA-&CTL-01183 | STG and Auxiliary Boiler Electrical Building - Grade Beam Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-08 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
745 | Later | S&L | SAU4005-G000-UBA-&CTL-01184 | STG and Auxiliary Boiler Electrical Building - Roof Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-11 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
746 | Later | S&L | SAU4005-G000-UBA-&CTL-01185 | STG and Auxiliary Boiler Electrical Building - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-07-01 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
747 | Later | S&L | SAU4005-G000-UBA-&CED-01186 | GT Package MCC / Control room - 11, 12, 13 - Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-25 |  |  |  | 2025-12-15 |  |  |  | 2026-06-05 | [7 empty] | 528 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
748 | Later | S&L | SAU4005-G000-UBA-&CED-01187 | GT Package MCC / Control room - 11, 12, 13 - Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-01-01 |  |  |  | 2026-01-21 |  |  |  | 2026-06-29 | [7 empty] | 528 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
749 | Later | S&L | SAU4005-G000-UBA-&CTB-01188 | GT Package MCC / Control room - 11, 12, 13 - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-10-17 |  |  |  | 2025-11-06 |  |  |  | 2026-05-13 | [7 empty] | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Open
750 | Later | S&L | SAU4005-G000-UBA-&CTB-01189 | GT Package MCC / Control room - 11, 12, 13 - Toilet and False ceiling Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-12-16 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
751 | Later | S&L | SAU4005-G000-UBA-&CLB-01190 | GT Package MCC / Control room - 11, 12, 13 - Foundation and Column Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-10 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
752 | Later | S&L | SAU4005-G000-UBA-&CTL-01191 | GT Package MCC / Control room - 11, 12, 13 - Grade Beam Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-01-01 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
753 | Later | S&L | SAU4005-G000-UBA-&CTL-01192 | GT Package MCC / Control room - 11, 12, 13 - Roof Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-01-01 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
754 | Later | S&L | SAU4005-G000-UBA-&CTL-01193 | GT Package MCC / Control room - 11, 12, 13 - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-07-04 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
755 | Later | S&L | SAU4005-G000-UBA-&CTL-01201 | ACC Electrical Container - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-08-18 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
756 | Later | S&L | SAU4005-G000-UBA-&CED-01202 | Unit MV/LV Electrical Switchgear building-11, 12, 13 - Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-03-14 |  |  |  | 2026-04-03 |  |  |  | 2026-07-20 | [7 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
757 | Later | S&L | SAU4005-G000-UBA-&CED-01203 | Unit MV/LV Electrical Switchgear building-11, 12, 13 - Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-03-27 |  |  |  | 2026-04-16 |  |  |  | 2026-07-27 | [7 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
758 | Later | S&L | SAU4005-G000-UBA-&CTB-01204 | Unit MV/LV Electrical Switchgear building-11, 12, 13 - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-11-17 |  |  |  | 2025-12-07 |  |  |  | 2026-07-14 | [7 empty] | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
759 | Later | S&L | SAU4005-G000-UBA-&CTB-01205 | Unit MV/LV Electrical Switchgear building-11, 12, 13 - False ceiling Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-04-17 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
760 | Later | S&L | SAU4005-G000-UBA-&CLB-01206 | Unit MV/LV Electrical Switchgear building-11, 12, 13 - Foundation and Column Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-12-03 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
761 | Later | S&L | SAU4005-G000-UBA-&CTL-01207 | Unit MV/LV Electrical Switchgear building-11, 12, 13 - Grade Beam Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-04-03 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
762 | Later | S&L | SAU4005-G000-UBA-&CTL-01208 | Unit MV/LV Electrical Switchgear building-11, 12, 13 - Roof Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-04-03 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
763 | Later | S&L | SAU4005-G000-UBA-&CTL-01209 | Unit MV/LV Electrical Switchgear building-11, 12, 13 - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-12 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
764 | Later | S&L | SAU4005-G000-UGA-&CED-01212 | Waste Water Collecion Pit Foundation - Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-30 |  |  |  | 2025-12-20 |  |  |  | 2026-01-24 | [7 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
765 | Later | S&L | SAU4005-G000-UGA-&CLB-01213 | Waste Water Collecion Pit Foundation - Layout & Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-11-30 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
766 | Later | S&L | SAU4005-G000-UYP-&CED-01214 | Fire Station Building - Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-03-18 |  |  |  | 2026-04-07 |  |  |  | 2026-05-12 | [7 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
767 | Later | S&L | SAU4005-G000-UYP-&CTB-01215 | Fire Station Building - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-10-27 |  |  |  | 2025-11-16 |  |  |  | 2026-04-16 | [7 empty] | 560 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
768 | Later | S&L | SAU4005-G000-UYP-&CTB-01216 | Fire Station Building - False ceiling Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-26 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
769 | Later | S&L | SAU4005-G000-UYP-&CLB-01217 | Fire Station Building - Foundation & Column - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-27 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
770 | Later | S&L | SAU4005-G000-UYP-&CTL-01218 | Fire Station Building - Grade beams Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-05-13 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
771 | Later | S&L | SAU4005-G000-UYP-&CTL-01219 | Fire Station Building - Roof Slabs Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-26 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
772 | Later | S&L | SAU4005-G000-UYP-&CTL-01220 | Fire Station Building - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-12 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
773 | Later | S&L | SAU4005-G000-UGA-&CED-01221 | Raw water Buffer Storage Tank with Unloading Area - Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-06 |  |  |  | 2025-11-26 |  |  |  | 2025-12-31 | [7 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
774 | Later | S&L | SAU4005-G000-UGA-&CTB-01222 | Raw water Buffer Storage Tank with Unloading Area - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-11-18 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
775 | Later | S&L | SAU4005-G000-UGD-&CED-01223 | DM and Service Water Pump Shed - Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-01-13 |  |  |  | 2026-02-02 |  |  |  | 2026-03-09 | [7 empty] | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
776 | Later | S&L | SAU4005-G000-UGD-&CTB-01224 | DM and Service Water Pump Shed - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-10-16 |  |  |  | 2025-11-05 |  |  |  | 2026-01-30 | [7 empty] | 547 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
777 | Later | S&L | SAU4005-G000-UGD-&CLB-01225 | DM and Service Water Pump Shed - Foundation & Pier Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-01-13 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
778 | Later | S&L | SAU4005-G000-UGD-&CTB-01226 | DM and Service Water Pump Shed - Superstructure Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-12-19 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
779 | Later | S&L | SAU4005-G000-UGD-&CTL-01227 | DM and Service Water Pump Shed - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-05-01 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
780 | Later | S&L | SAU4005-G000-UGD-&CED-01490 | Treated Water Storage Tank - Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-08-06 |  |  |  | 2026-08-26 |  |  |  | 2026-09-30 | [7 empty] | 500 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
781 | Later | S&L | SAU4005-G000-UGD-&CTB-01228 | Treated Water Storage Tank - Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-12-10 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
782 | Later | S&L | SAU4005-G000-UGA-&CLB-01239 | Centrifuge Foundation - Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-09-18 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | NO | NO | NO | NO | NO |  | NO
783 | Later | S&L | SAU4005-G000-UBN-&CED-01240 | BSEDG Foundation - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-10-06 |  |  |  | 2025-10-26 |  |  |  | 2025-11-30 | [7 empty] | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
784 | Later | S&L | SAU4005-G000-UBN-&CLB-01243 | BSEDG Foundation - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-10-15 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
785 | Later | S&L | SAU4005-G000-UBN-&CTL-01247 | BSEDG Area - Grade slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-10-18 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
786 | Later | S&L | SAU4005-G000-UBN-&CLB-01249 | BSEDG Area Miscellaneous Equipment foundations - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-11-24 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
787 | Later | S&L | SAU4005-G000-UBA-&CED-01252 | BOP Electrical Switchgear Building - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-03-06 |  |  |  | 2026-03-26 |  |  |  | 2026-04-30 | [7 empty] | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
788 | Later | S&L | SAU4005-G000-UBA-&CTB-01253 | BOP Electrical Switchgear Building - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-12-22 |  |  |  | 2026-01-11 |  |  |  | 2026-02-15 | [7 empty] | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
789 | Later | S&L | SAU4005-G000-UBA-&CTB-01254 | BOP Electrical Switchgear Building - Toilet and False ceiling Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-04-16 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | NO | NO | NO | NO | NO |  | NO
790 | Later | S&L | SAU4005-G000-UBA-&CLB-01255 | BOP Electrical Switchgear Building - Foundation & Column- Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-10-12 |  |  |  | 2026-11-01 |  |  |  | 2026-12-06 | [7 empty] | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
791 | Later | S&L | SAU4005-G000-UBA-&CTL-01256 | BOP Electrical Switchgear Building - Grade Beam Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-04-15 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
792 | Later | S&L | SAU4005-G000-UBA-&CTL-01257 | BOP Electrical Switchgear Building - Roof Slabs Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-05-19 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
793 | Later | S&L | SAU4005-G000-UBA-&CTL-01258 | BOP Electrical Switchgear Building - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-05 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
794 | Later | S&L | SAU4005-G000-UEL-&CED-01259 | Fuel Oil pump Shed - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-15 |  |  |  | 2026-01-04 |  |  |  | 2026-02-08 | [7 empty] | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
795 | Later | S&L | SAU4005-G000-UEL-&CTB-01260 | Fuel Oil pump Shed - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-08-28 |  |  |  | 547 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Open
796 | Later | S&L | SAU4005-G000-UEL-&CLB-01261 | Fuel Oil Pump Shed - Foundation & Pier Layout and RC details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-12-15 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
797 | Later | S&L | SAU4005-G000-UEL-&CTB-01262 | Fuel Oil Pump Shed - Superstructure details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-01-19 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
798 | Later | S&L | SAU4005-G000-UEL-&CTL-01263 | Fuel Oil Pump Shed - Grade Slab Layout and RC details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-05-16 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
799 | Later | S&L | SAU4005-G000-UEN-&CTL-01264 | Fuel Gas Conditioning Area - Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-10-08 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
800 | Later | S&L | SAU4005-G000-UBA-&CTL-01270 | Electrical Container for Fuel Oil Area - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-12 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
801 | Later | S&L | SAU4005-G000-UTG-&CED-01271 | Hydrogen Generation Plant including Electrical Room - Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-17 |  |  |  | 2026-03-09 |  |  |  | 2026-04-13 | [7 empty] | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
802 | Later | S&L | SAU4005-G000-UTG-&CED-01272 | Hydrogen Generation Plant including Electrical Room - Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-17 |  |  |  | 2026-03-09 |  |  |  | 2026-04-13 | [7 empty] | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
803 | Later | S&L | SAU4005-G000-UTG-&CTB-01273 | Hydrogen Generation Plant including Electrical Room - Architectural Drawings | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-02-17 |  |  |  | 2026-03-09 |  |  |  | 2026-04-13 | [7 empty] | 547 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
804 | Later | S&L | SAU4005-G000-UTG-&CLB-01274 | Hydrogen Generation Plant including Electrical Room - Foundation & Pier Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-02-17 |  |  |  | 2026-03-09 |  |  |  | 2026-04-13 | [7 empty] | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
805 | Later | S&L | SAU4005-G000-UTG-&CTB-01275 | Hydrogen Generation Plant including Electrical Room - Base Plate and Framing Plan, Elevations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-05-04 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
806 | Later | S&L | SAU4005-G000-UTG-&CTB-01276 | Hydrogen Generation Plant including Electrical Room - Purlin Plan and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-05-21 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
807 | Later | S&L | SAU4005-G000-UTG-&CTB-01277 | Hydrogen Generation Plant including Electrical Room - Girt Elevations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-05-21 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | NO | NO | NO | NO | NO |  | NO
808 | Later | S&L | SAU4005-G000-UTG-&CTL-01278 | Hydrogen Generation Plant including Electrical Room - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-30 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
809 | Later | S&L | SAU4005-G000-UBA-&CED-01279 | Electrical Switchgear Building for Fuel Gas - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-03-07 |  |  |  | 2026-03-27 |  |  |  | 2026-05-11 | [7 empty] | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
810 | Later | S&L | SAU4005-G000-UBA-&CTB-01280 | Electrical Switchgear Building for Fuel Gas Area - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-02-20 |  |  |  | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
811 | Later | S&L | SAU4005-G000-UBA-&CLB-01282 | Electrical Switchgear Building for Fuel Gas Area - Foundation & Column Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-06 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
812 | Later | S&L | SAU4005-G000-UBA-&CTL-01283 | Electrical Switchgear Building for Fuel Gas Area - Grade Beam Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-25 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
813 | Later | S&L | SAU4005-G000-UBA-&CTL-01284 | Electrical Switchgear Building for Fuel Gas Area - Roof Slabs Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-25 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
814 | Later | S&L | SAU4005-G000-UBA-&CTL-01285 | Electrical Switchgear Building for Fuel Gas Area - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-12 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
815 | Later | S&L | SAU4005-G000-UBA-&CTL-01306 | BSEDG Electrical Container - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-12 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
816 | Later | S&L | SAU4005-G000-UEJ-&CED-01327 | Fuel Oil Storage Tank Foundation - Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-30 |  |  |  | 2025-12-20 |  |  |  | 2026-01-24 | [7 empty] | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
817 | Later | S&L | SAU4005-G000-UEJ-&CLB-01328 | Fuel Oil Storage Tank Foundation - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-11-30 |  |  |  | 2025-12-20 |  |  |  | 2026-01-24 | [7 empty] | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
818 | Later | S&L | SAU4005-G000-UEJ-&CTL-01329 | Fuel Oil Storage Tank With Dyke Area - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-01-16 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
819 | Later | S&L | SAU4005-G000-UEJ-&CTL-01330 | Fuel Oil Unloading Area - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-26 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
820 | Later | S&L | SAU4005-G000-UYF-&CED-01331 | Search Facility & Visitors Center - Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-05-28 |  |  |  | 2026-06-17 |  |  |  | 2026-07-22 | [7 empty] | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
821 | Later | S&L | SAU4005-G000-UYF-&CTB-01332 | Search Facility & Visitors Center - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-09-19 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
822 | Later | S&L | SAU4005-G000-UYF-&CTB-01333 | Search Facility & Visitors Center - Toilet and False ceiling Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-11 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
823 | Later | S&L | SAU4005-G000-UYF-&CLB-01334 | Search Facility & Visitors Center - Foundation & Column Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-05-28 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
824 | Later | S&L | SAU4005-G000-UYF-&CTL-01335 | Search Facility & Visitors Center - Grade Beam Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-07-01 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
825 | Later | S&L | SAU4005-G000-UYF-&CTL-01336 | Search Facility & Visitors Center - Roof Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-08-06 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
826 | Later | S&L | SAU4005-G000-UYF-&CTL-01337 | Search Facility & Visitors Center - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-08-29 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
827 | Later | S&L | SAU4005-G000-UYE-&CED-01338 | Main Gate - Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-06-02 |  |  |  | 2026-06-22 |  |  |  | 2026-07-27 | [7 empty] | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
828 | Later | S&L | SAU4005-G000-UYE-&CTB-01339 | Main Gate House including Sunshade - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-08-16 |  |  |  | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
829 | Later | S&L | SAU4005-G000-UYE-&CLB-01340 | Main Gate - Foundation and Pier Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-15 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
830 | Later | S&L | SAU4005-G000-UYE-&CTB-01341 | Main Gate - Superstructure Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-07-18 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
831 | Later | S&L | SAU4005-G000-UYE-&CED-01342 | Main Gate House Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-06-02 |  |  |  | 2026-06-22 |  |  |  | 2026-08-10 | [7 empty] | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
832 | Later | S&L | SAU4005-G000-UYE-&CLB-01343 | Main Gate House - Foundation and Column Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-15 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
833 | Later | S&L | SAU4005-G000-UYE-&CTL-01344 | Main Gate House - Roof Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-07-18 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
834 | Later | S&L | SAU4005-G000-UGN-&CED-01350 | Clarifier Unit - 1 & 2 - Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-06-24 |  |  |  | 2026-07-14 |  |  |  | 2026-08-18 | [7 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
835 | Later | S&L | SAU4005-G000-UGN-&CTB-01351 | Clarifier Unit - 1 & 2 - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-07-06 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
836 | Later | S&L | SAU4005-G000-UGN-&CED-01352 | Clarifier Water Storage Tank - Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-07-27 |  |  |  | 2026-08-16 |  |  |  | 2026-09-20 | [7 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
837 | Later | S&L | SAU4005-G000-UGN-&CTB-01353 | Clarifier Water Storage Tank - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-08-06 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
838 | Later | S&L | SAU4005-G000-UGX-&CED-01354 | Ammonia Storage area - Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-01-22 |  |  |  | 2026-02-11 |  |  |  | 2026-04-16 | [7 empty] | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
839 | Later | S&L | SAU4005-G000-UGX-&CTL-01355 | Ammonia Storage area - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-02-05 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
840 | Later | S&L | SAU4005-G000-UBE-&CED-01434 | MV/LV ACC Transformer - Foundation Design Calulation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-03-23 |  |  |  | 2026-04-12 |  |  |  | 2026-05-17 | [7 empty] | 207 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
841 | Later | S&L | SAU4005-G000-UBE-&CLB-01435 | MV/LV ACC Transformer - Foundation Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-04-30 |  |  |  | 136 | [13 empty] | WF Transmittal DI-EPC-ACWA | NO | NO | NO | NO | NO |  | NO
842 | Later | S&L | SAU4005-G000-UBE-&CED-01436 | MV/MV BOP Area Transformer - Foundation Design Calulation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-03-30 |  |  |  | 2026-04-19 |  |  |  | 2026-05-24 | [7 empty] | 207 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
843 | Later | S&L | SAU4005-G000-UBE-&CLB-01437 | MV/MV BOP Area Transformer Foundation - Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-05-13 |  |  |  | 136 | [13 empty] | WF Transmittal DI-EPC-ACWA | NO | NO | NO | NO | NO |  | NO
844 | Later | S&L | SAU4005-G000-UBE-&CED-01438 | Fuel Gas Area Transformer Foundation - Design Calulation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-01-22 |  |  |  | 2026-02-11 |  |  |  | 2026-03-18 | [7 empty] | 207 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
845 | Later | S&L | SAU4005-G000-UBE-&CLB-01439 | Fuel Gas Area Transformer Foundation - Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-13 |  |  |  | 136 | [13 empty] | WF Transmittal DI-EPC-ACWA | NO | NO | NO | NO | NO |  | NO
846 | Later | S&L | SAU4005-G000-UM_-&CED-01451 | GTG Intake Structure Foundation Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-10-24 |  |  |  | 2025-11-13 |  |  |  | 2026-05-04 | [7 empty] | 389 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
847 | Later | S&L | SAU4005-G000-UM_-&CTB-01452 | GTG Intake Structure Foundation Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-12-15 |  |  |  | 2026-01-04 |  |  |  | 2026-02-08 | [7 empty] | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
848 | Later | S&L | SAU4005-G000-UB_-&CTB-01455 | EHV Cable Trench RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-12-18 |  |  |  | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
849 | Later | S&L | SAU4005-G000-UYF-&CTL-01457 | Security and Control center - Wet area details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-08-01 |  |  |  | 233 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Common
850 | Later | S&L | SAU4005-G000-UYF-&CTL-01458 | Search facility & Visitor's centre - Wet area details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-09-18 |  |  |  | 233 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Common
851 | Later | S&L | SAU4005-G000-UYC-&CTL-01459 | Administration & Social Building - Wet area details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-01-07 |  |  |  | 233 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Common
852 | Later | S&L | SAU4005-G000-UYP-&CTL-01460 | Fire Brigade Building - Wet area details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-10 |  |  |  | 233 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Common
853 | Later | S&L | SAU4005-G000-UST-&CTL-01461 | Workshop and Warehouse Building - Wet area details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2025-12-19 |  |  |  | 233 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Common
854 | Later | S&L | SAU4005-G000-UCA-&CTL-01462 | Main Electrical & Control Building - Wet area details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-01-27 |  |  |  | 233 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
855 | Later | S&L | SAU4005-G000-UGD-&CTL-01463 | DM plant laboratory - Wet area details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-05-30 |  |  |  | 233 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
856 | Later | S&L | SAU4005-G000-UBA-&CED-01319 | MCC Room for Water and Effluent treatment building - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-05-01 |  |  |  | 2026-05-21 |  |  |  | 2026-06-25 | [7 empty] | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
857 | Later | S&L | SAU4005-G000-UBA-&CTB-01320 | MCC Room for Water and Effluent treatment building - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-02-28 |  |  |  | 2026-03-20 |  |  |  | 2026-04-24 | [7 empty] | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
858 | Later | S&L | SAU4005-G000-UBA-&CTB-01485 | MCC Room for Water and Effluent treatment building - False Ceiling Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-04-21 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
859 | Later | S&L | SAU4005-G000-UBA-&CLB-01321 | MCC Room for Water and Effluent treatment building - Foundation and Column Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-05-21 |  |  |  | 2026-06-10 |  |  |  | 2026-07-18 | [7 empty] | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
860 | Later | S&L | SAU4005-G000-UBA-&CTL-01322 | MCC Room for Water and Effluent treatment building - Grade Beam Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-08 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
861 | Later | S&L | SAU4005-G000-UBA-&CTL-01323 | MCC Room for Water and Effluent treatment building - Roof Slabs Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-08 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
862 | Later | S&L | SAU4005-G000-UBA-&CTL-01324 | MCC Room for Water and Effluent treatment building - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-08 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
863 | Later | S&L | SAU4005-G000-UBA-&CTL-01477 | Fin Fan Cooler Electrical Container - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-05-30 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
864 | Later | S&L | SAU4005-G000-AS_-&CED-01478 | SPVT Cubicle - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-06-17 |  |  |  | 2026-07-07 |  |  |  | 2026-08-11 | [7 empty] | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
865 | Later | S&L | SAU4005-G000-AS_-&CLB-01479 | SPVT Cubicle - Foundation and Column Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-07-18 |  |  |  | 285 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
866 | Later | S&L | SAU4005-G000-UYX-&CTL-01480 | Atmospheric Flash Tank Pit Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-06-12 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
867 | Later | S&L | SAU4005-G000-GM_-&CED-01481 | Outside Plant Peripherial Drain Design calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-06-30 |  |  |  | 2026-07-20 |  |  |  | 2026-08-24 | [7 empty] | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
868 | Later | S&L | SAU4005-G000-GM_-&CLB-01482 | Outside Plant Peripherial Drain - Layout and details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-08-20 |  |  |  | 285 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
869 | Later | S&L | SAU4005-G000-UYX-&CTL-01483 | Sound Barrier Fence Wall - Layout and RC details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-07-14 |  |  |  | 2026-08-03 |  |  |  | 2026-09-07 | [7 empty] | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
870 | Later | S&L | SAU4005-G000-___-&CEC-01385 | Technical Specification for Topography Survey | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-03-04 |  |  |  | 2025-03-24 |  |  |  | 2025-04-28 | [7 empty] | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
871 | Later | S&L | SAU4005-G000-___-&CEC-01386 | Technical Specification for Geotechnical Investigations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-03-04 |  |  |  | 2025-03-24 |  |  |  | 2025-04-28 | [7 empty] | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C1 | NO |  | NO | Common
872 | Later | S&L | SAU4005-G000-___-&CEC-01387 | Technical Specification for General Civil Works | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-05-21 |  |  |  | 2025-06-10 |  |  |  | 2025-07-15 | [7 empty] | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
873 | Later | S&L | SAU4005-G000-___-&CEC-01390 | Technical Specification for Structural Steel | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-06-25 |  |  |  | 2025-07-15 |  |  |  | 2025-08-19 | [7 empty] | 246 | [13 empty] | WF Transmittal DI-EPC-ACWA |  | YES | NO | NO | NO |  | NO
874 | Later | S&L | SAU4005-G000-___-&CEC-01393 | Technical Specification for Architectural Works | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-07-21 |  |  |  | 2025-08-10 |  |  |  | 2025-09-14 | [7 empty] | 246 | [13 empty] | WF Transmittal DI-EPC-ACWA |  | NO | NO | NO | NO |  | NO
875 | Later | S&L | SAU4005-G000-___-&EDD-00732 | Harmonic Studies | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFD | [14 empty] | 2025-10-09 |  |  |  | 615 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | SEC | S1,S2 | NO | Common
876 | Later | S&L | SAU4005-G000-___-&EDD-00690 | Arc Flash Study | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-24 |  |  |  | 2025-12-14 |  |  |  | 2026-01-18 | [7 empty] | 463 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
877 | Later | S&L | SAU4005-G000-A__-&EDD-00691 | Grid Code Impact Study | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-01 |  |  |  | 2025-11-21 |  |  |  | 2025-12-26 | [7 empty] | 282 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | SEC | S1,S2,S6 | NO | Common
878 | Later | S&L | SAU4005-G000-___-&CDD-01388 | Flooding Protection Study | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-05-08 |  |  |  | 2025-05-28 |  |  |  | 2026-05-22 | [7 empty] | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Common
879 | Later | S&L | SAU4005-G000-___-&MDD-00342 | Near Field Noise Study Report | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-20 |  |  |  | 2025-12-10 |  |  |  | 2026-02-12 | [7 empty] | 1500 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Common
880 | Later | S&L | SAU4005-G000-___-&EDD-00712 | Insulation Coordination Study | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2026-01-13 |  |  |  | 2026-02-02 |  |  |  | 2026-03-09 | [7 empty] | 1600 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO
881 | Later | S&L | SAU4005-G000-___-&MDC-00458 | HAZID Study Report | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | Common |  | IFA | IFD |  |  | 2026-04-19 |  |  |  | 2026-05-09 |  |  |  | 2026-06-14 | [7 empty] | 1500 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
882 | Later | S&L | SAU4005-G000-___-&MDD-00343 | HAZOP Study Report | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | Common |  | IFA | IFD |  |  | 2026-04-19 |  |  |  | 2026-05-09 |  |  |  | 2026-06-14 | [7 empty] | 1500 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
883 | Later | S&L | SAU4005-G000-___-&MDC-00459 | SIL Study Report | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | Common |  | IFA | IFD |  |  | 2026-04-19 |  |  |  | 2026-05-09 |  |  |  | 2026-06-14 | [7 empty] | 1600 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Common
884 | Later | S&L | SAU4005-G000-___-&MDD-00466 | RAM Study | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFD |  |  | 2026-05-05 |  |  |  | 2026-05-25 |  |  |  | 2026-06-29 | [7 empty] | 1500 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
885 | Later | S&L | SAU4005-G000-UZA-&CED-01492 | Access road - Design calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-04-13 |  |  |  | 2026-05-03 |  |  |  | 2026-06-07 | [7 empty] | 1800 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
886 | Later | S&L | SAU4005-G000-UZA-&CTL-01493 | Access Road - Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-04-13 |  |  |  | 2026-05-03 |  |  |  | 2026-06-07 | [7 empty] | 1900 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
887 | Later | S&L | SAU4005-G000-GM_-&CTL-01494 | Plant outside drain channel drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-11-18 |  |  |  | 2026-12-08 |  |  |  | 2027-01-12 | [7 empty] | 1600 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
888 | Later | S&L | SAU4005-G000-UM_-&CED-01495 | GTG Intake Platform Superstructure - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-11-08 |  |  |  | 2026-11-28 |  |  |  | 2027-01-02 | [7 empty] | 1600 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
889 | Later | S&L | SAU4005-G000-UM_-&CLH-01496 | GTG Intake Platform - Framing and Elevations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-11-08 |  |  |  | 1600 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
890 | Later | S&L | SAU4005-G000-UHA-&CTL-01501 | HRSG MCC Container_Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-04-15 |  |  |  | 1800 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
891 | Later | S&L | SAU4005-G000-___-&ABB-00010 | Project Design Management Plan | A1 | Engineering | A-Overall management | Yes | GENERAL | GENERAL | Common |  | IFA | IFD |  |  | 2025-04-27 |  |  |  | 2025-05-17 |  |  |  | 2025-06-22 | [7 empty] | 1479 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
892 | Later | S&L | SAU4005-G000-___-&PFB-91000 | Process Flow Diagram | A1 | Engineering | A-Overall management | Yes | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFI | IFD | [14 empty] | 2026-06-30 |  |  |  | 1479 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
893 | LATER | DE(STG) | SAU4005-G010-MAA-&MDB-04004 | ST(V) - STEAM TURBINE FOUNDATION DESIGN CRITERIA | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-07-01 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
894 | LATER | DE(STG) | SAU4005-G010-MAA-&MLB-04005 | ST(V) - STEAM TURBINE FOUNDATION LOADING DATA | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-07-01 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
895 | LATER | DE(STG) | SAU4005-G010-MAA-&MDD-04030 | ST(V) - STEAM TURBINE OUTPUT CORRECTION FOR VARIOUS CONDITIONS(THERMAL KIT) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-07-31 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
896 | LATER | DE(STG) | SAU4005-G010-MAV-&MDB-04061 | ST(V) - FLOW DIAGRAM - LUBE OIL CONDITIONER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-07-31 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
897 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04210 | ST(V) - ASSEMBLY OF STEAM TURBINE EXHAUST HOOD (LP OUTER CASING) TO CONDENSER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-07-31 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
898 | LATER | DE(STG) | SAU4005-G010-MAA-&MDB-04211 | ST(V) - STEAM TURBINE CONDENSER DESIGN RECOMMENDATIONS | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-07-31 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
899 | LATER | DE(STG) | SAU4005-G010-MAC-&MTC-04218 | ST(V) - WPS/PQR FOR LP CASING FOR STG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-08-07 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
900 | LATER | DE(STG) | SAU4005-G010-MKA-&MTC-04220 | ST(V) - WPS/PQR FOR STATOR FRAME FOR STG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-08-07 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
901 | LATER | DE(STG) | SAU4005-G010-MKA-&MTC-04221 | ST(V) - WPS/PQR FOR END SHIELD FOR STG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-08-07 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
902 | LATER | DE(STG) | SAU4005-G010-MAA-&MDC-04222 | ST(V) - PAINTING SPECIFICATION FOR STG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-08-07 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
903 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04002 | ST(V) - TURBINE MAJOR COMPONENTS LAYDOWN AREA | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-08-21 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
904 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04000 | ST(V) - OUTLINE - STEAM TURBINE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-06-20 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO | NO | NO
905 | LATER | DE(STG) | SAU4005-G010-MKA-&MLU-04001 | ST(V) - OUTLINE - GENERATOR MECHANICAL | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-07-11 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO | NO | NO
906 | LATER | DE(STG) | SAU4005-G010-MKA-&MLU-04003 | ST(V) - GENERATOR COMONENT LAYDOWN AREA | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-08-28 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
907 | LATER | DE(STG) | SAU4005-G010-MKA-&MLB-04006 | ST(V) - GENERATOR FOUNDATION LOADING DATA | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-07-01 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
908 | LATER | DE(STG) | SAU4005-G010-MAA-&MLB-04009 | ST(V) - FOUNDATION INTERFACE FOR STEAM TURBINE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-07-01 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
909 | LATER | DE(STG) | SAU4005-G010-MKA-&MLB-04010 | ST(V) - GENERATOR FOUNDATION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-07-11 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
910 | LATER | DE(STG) | SAU4005-G010-MAY-&EPC-04011 | ST(V) - STG ELECTRICAL LOAD LIST | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-08-28 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
911 | LATER | DE(STG) | SAU4005-G010-MAX-&MPC-04012 | ST(V) - UTILITY CONSUMPTION LIST | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-08-28 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
912 | LATER | DE(STG) | SAU4005-G010-MAX-&MDD-04023 | ST(V) - VALVE CHARACTERISTIC CURVE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-08-28 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
913 | LATER | DE(STG) | SAU4005-G010-MAX-&MFB-04033 | ST(V) - P&ID - TURBINE HYDRAULIC FLUID SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-06-30 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | YES | C2 | NO
914 | LATER | DE(STG) | SAU4005-G010-MAX-&MFB-04035 | ST(V) - P&ID - INSTRUMENT AIR SYSTEM FOR STG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-07-29 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | YES | NO | NO
915 | LATER | DE(STG) | SAU4005-G010-MAA-&MFB-04036 | ST(V) - P&ID - STEAM SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-07-29 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | YES | C2 | NO
916 | LATER | DE(STG) | SAU4005-G010-MKG-&MFB-04053 | ST(V) - P&ID - H2 COOLER VENT, DRAIN | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-06-30 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | YES | NO | NO
917 | LATER | DE(STG) | SAU4005-G010-MKW-&MFB-04054 | ST(V) - P&ID - GENERATOR SHAFT SEAL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-06-30 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | YES | NO | NO
918 | LATER | DE(STG) | SAU4005-G010-MKG-&MFB-04055 | ST(V) - P&ID - H2 & CO2 CONTROL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-06-30 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | YES | NO | NO
919 | LATER | DE(STG) | SAU4005-G010-MKU-&MFB-04056 | ST(V) - P&ID - STATOR WINDING LIQUID COOLING SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-06-30 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | YES | NO | NO
920 | LATER | DE(STG) | SAU4005-G010-MAV-&MFB-04070 | ST(V) - P&ID - JACKING OIL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-07-18 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | YES | NO | NO
921 | LATER | DE(STG) | SAU4005-G010-MAV-&MFB-04071 | ST(V) - P&ID - LUBE OIL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-07-18 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | YES | NO | NO
922 | LATER | DE(STG) | SAU4005-G010-MKA-&MLD-04103 | ST(V) - GENERATOR PIPING CONNECTION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-08-28 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
923 | LATER | DE(STG) | SAU4005-G010-MKB-&ELU-04109 | ST(V) - GENERATOR ELECTRICAL CONDUIT LAYOUT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-07-01 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
924 | LATER | DE(STG) | SAU4005-G010-MKB-&ELU-04110 | ST(V) - GENERATOR ELECTRICAL OUTLINE | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-07-01 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
925 | LATER | DE(STG) | SAU4005-G010-MAA-&MPA-04191 | ST(V) - PIPING MATERIAL CLASSES FOR STEAM TURBINE & GENERATOR SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-08-28 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
926 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04209 | ST(V) - STEAM TURBINE OUTLINE 3D MODEL FOR INTERFACE CHECK | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-08-28 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
927 | LATER | DE(STG) | SAU4005-G010-MAA-&MEC-04240 | ST(V) - STEAM TURBINE NOISE TEST PROCEDURE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-09-18 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
928 | LATER | DE(STG) | SAU4005-G010-MAA-&MDD-04028 | ST(V) - NOZZLE MOVEMENT & ALLOWABLE PIPE LOAD | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-08-09 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
929 | LATER | DE(STG) | SAU4005-G010-MKC-&ELU-04090 | ST(V) - OUTLINE - EXCITATION SYSTEM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-09-30 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
930 | LATER | DE(STG) | SAU4005-G010-MAX-&MPA-04206 | ST(V) - MANUAL VALVE LIST FOR STG PIPING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-10-09 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
931 | LATER | DE(STG) | SAU4005-G010-LBR-&MLU-04230 | ST(V) - OUTLINE - DYNAMIC SEPARATOR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-10-09 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
932 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04007 | ST(V) - ARRANGEMENT OF GROUT PADS & FOUNDATION PLATES - STEAM TURBINE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-07-01 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
933 | LATER | DE(STG) | SAU4005-G010-MKA-&MLU-04008 | ST(V) - ARRANGEMENT OF GROUT PADS & FOUNDATION PLATES - GENERATOR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-07-01 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
934 | LATER | DE(STG) | SAU4005-G010-MAX-&MLU-04032 | ST(V) - OUTLINE - HYDRAULIC POWER UNIT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-08-23 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
935 | LATER | DE(STG) | SAU4005-G010-MKG-&MLU-04043 | ST(V) - OUTLINE - CO2 BOTTLE MANIFOLD FOR GENERATOR GAS CONTROL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-08-22 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
936 | LATER | DE(STG) | SAU4005-G010-MKW-&MLU-04044 | ST(V) - OUTLINE - FLOAT TRAP | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-08-22 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
937 | LATER | DE(STG) | SAU4005-G010-MKG-&MLU-04045 | ST(V) - OUTLINE - GAS CONTROL VALVE STATION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-08-22 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
938 | LATER | DE(STG) | SAU4005-G010-MKG-&MLU-04046 | ST(V) - OUTLINE - H2 BOTTLE MANIFOLD FOR GENERATOR GAS CONTROL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-08-22 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
939 | LATER | DE(STG) | SAU4005-G010-MKG-&MLU-04047 | ST(V) - OUTLINE - HYDROGEN CONTROL CABINET | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-08-22 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
940 | LATER | DE(STG) | SAU4005-G010-MKG-&MLU-04048 | ST(V) - OUTLINE - HYDROGEN GAS DRYER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-08-22 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
941 | LATER | DE(STG) | SAU4005-G010-MKW-&MLU-04049 | ST(V) - OUTLINE - HYDROGEN SEAL OIL UNIT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-08-22 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
942 | LATER | DE(STG) | SAU4005-G010-MKW-&MLU-04050 | ST(V) - OUTLINE - LIQUID LEVEL DETECTOR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-08-22 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
943 | LATER | DE(STG) | SAU4005-G010-MKU-&MLU-04051 | ST(V) - OUTLINE - STATOR WINDING WATER COOLING UNIT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-08-22 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
944 | LATER | DE(STG) | SAU4005-G010-MAV-&MLU-04064 | ST(V) - OUTLINE - JACKING OIL DISTRIBUTION MANIFOLD | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-07-18 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
945 | LATER | DE(STG) | SAU4005-G010-MAV-&MLU-04065 | ST(V) - OUTLINE - JACKING OIL PUMP UNIT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-07-18 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
946 | LATER | DE(STG) | SAU4005-G010-MAV-&MLU-04066 | ST(V) - OUTLINE - LUBE OIL CONDITIONER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-07-18 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
947 | LATER | DE(STG) | SAU4005-G010-MAV-&MLU-04067 | ST(V) - OUTLINE - LUBE OIL TANK | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-07-18 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
948 | LATER | DE(STG) | SAU4005-G010-MAV-&MLU-04068 | ST(V) - OUTLINE - MIST ELIMINATOR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-07-18 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
949 | LATER | DE(STG) | SAU4005-G010-MAG-&MLU-04074 | ST(V) - OUTLINE - GLAND STEAM CONDENSER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-09-23 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
950 | LATER | DE(STG) | SAU4005-G010-MAY-&ELD-04077 | ST(V) - STEAM TURBINE CONDUIT LOCATION DRAWING | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-07-13 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
951 | LATER | DE(STG) | SAU4005-G010-MKY-&EFA-04089 | ST(V) - SINGLE LINE DIAGRAM(INCLUDING ST GENERATOR CONTROL & PROTECTION, SUPPLY SCOPE) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-08-30 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
952 | LATER | DE(STG) | SAU4005-G010-MKC-&EDB-04091 | ST(V) - ELEMENTARY DIAGRAM FOR EXCITATION SYSTEM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-10-31 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
953 | LATER | DE(STG) | SAU4005-G010-MAY-&EDD-04097 | ST(V) - CONFIGURATION - TCS(SYSTEM CONFIGURATION - STG TCS / TPS ) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-09-23 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
954 | LATER | DE(STG) | SAU4005-G010-MAY-&EDC-04100 | ST(V) - RECOMMENDED CONTROL CIRCUIT - STG MCC | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-09-23 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
955 | LATER | DE(STG) | SAU4005-G010-MAY-&EFF-04102 | ST(V) - STG TRIP/PROTECTION DIAGRAM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-09-23 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
956 | LATER | DE(STG) | SAU4005-G010-MAA-&MPC-04113 | ST(V) - TERMINAL POINT LIST OF TURBINE SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-09-23 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
957 | LATER | DE(STG) | SAU4005-G010-MAG-&MFB-04162 | ST(V) - P&ID - GLAND STEAM CONDENSER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-10-23 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | YES | NO | NO | NO
958 | LATER | DE(STG) | SAU4005-G010-MAA-&MPA-04190 | ST(V) - TURBINE PIPING INSULATION SPECIFICATION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-11-06 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
959 | LATER | DE(STG) | SAU4005-G010-MAA-&MDB-04212 | ST(V) - INSULATION INSTALLATION PROCEDURE – HIP TURBINE & VALVE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-11-06 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
960 | LATER | DE(STG) | SAU4005-G010-MAA-&MEC-04232 | ST(V) - ST_STEAM PURITY LIMITS REQUIRED DURING OPERATION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-06-09 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
961 | LATER | DE(STG) | SAU4005-G010-MKB-&ELU-04111 | ST(V) - NEUTRAL TIE & ENCLOSURE ASSEMBLY | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-09-04 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
962 | LATER | DE(STG) | SAU4005-G010-MKA-&ELU-04178 | ST(V) - GENERATOR ON LINE MONITORING SYSTEM LAYOUT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-12-04 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
963 | LATER | DE(STG) | SAU4005-G010-MKA-&MLU-04192 | ST(V) - BRUSH HOLDER RIGGING ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-12-04 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
964 | LATER | DE(STG) | SAU4005-G010-MAX-&MDB-04239 | ST(V) - STEAM BLOWING PROCEDURE FOR STEAM SEAL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-12-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
965 | LATER | DE(STG) | SAU4005-G010-MAA-&MQA-04306 | ST(V) - NDE PROCEDURE FOR GENERAL MATERIAL | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-12-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
966 | LATER | DE(STG) | SAU4005-G010-MAA-&MQA-04307 | ST(V) - NDE PROCEDURE FOR GENERAL WELD | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-12-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
967 | LATER | DE(STG) | SAU4005-G010-MAA-&MQA-04308 | ST(V) - NDE PROCEDURE FOR PIPING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-12-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
968 | LATER | DE(STG) | SAU4005-G010-MAA-&MQA-04309 | ST(V) - NDE PROCEDURE FOR PRESSURE VESSEL | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-12-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
969 | LATER | DE(STG) | SAU4005-G010-MAA-&MQA-04310 | ST(V) - NDE PROCEDURE FOR VALVE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-12-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
970 | LATER | DE(STG) | SAU4005-G010-MAA-&MQA-04311 | ST(V) - NDE PROCEDURE FOR STEEL STRUCTURE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-12-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
971 | LATER | DE(STG) | SAU4005-G010-MAA-&MLD-04018 | ST(V) - HP CASING PIPING CONNECTION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-01-15 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
972 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04019 | ST(V) - HP CASING STUDS ARRANGEMENT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-01-15 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
973 | LATER | DE(STG) | SAU4005-G010-MAX-&MMB-04034 | ST(V) - WIRING DIAGRAM - HYDRAULIC POWER UNIT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-11-16 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
974 | LATER | DE(STG) | SAU4005-G010-MAX-&MDB-04037 | ST(V) - SYSTEM DESCRIPTION - STEAM SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-12-16 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO | NO | NO
975 | LATER | DE(STG) | SAU4005-G010-MAX-&MDA-04038 | ST(V) - LP STOP & CONTROL VALVE DATA SHEET AND OUTLINE FOR STG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-01-15 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
976 | LATER | DE(STG) | SAU4005-G010-MAX-&MDA-04039 | ST(V) - MOTOR OPERATED VALVE DATA SHEET AND OUTLINE FOR STG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-01-15 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
977 | LATER | DE(STG) | SAU4005-G010-MAX-&MDA-04040 | ST(V) - AIR OPERATED VALVE DATA SHEET AND OUTLINE FOR STG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-12-16 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
978 | LATER | DE(STG) | SAU4005-G010-MAA-&MDA-04041 | ST(V) - NON-RETURN VALVE DATA SHEET AND OUTLINE FOR CRH | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-01-15 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
979 | LATER | DE(STG) | SAU4005-G010-MKW-&EDA-04042 | ST(V) - PUMP & MOTOR DATA SHEET - HYDROGEN SEAL OIL SYSTEM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-11-16 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
980 | LATER | DE(STG) | SAU4005-G010-MKU-&EDA-04052 | ST(V) - PUMP & MOTOR DATA SHEET - STATOR WATER COOLING SYSTEM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-11-16 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
981 | LATER | DE(STG) | SAU4005-G010-MKF-&MDB-04058 | ST(V) - SYSTEM DESCRIPTION - GEN STATOR WINDING LIQUID COOLING SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-07-04 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO | NO | NO
982 | LATER | DE(STG) | SAU4005-G010-MKG-&MDB-04059 | ST(V) - SYSTEM DESCRIPTION - GENERATOR GAS(H2&CO2) CONTROL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-07-04 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO | NO | NO
983 | LATER | DE(STG) | SAU4005-G010-MKW-&MDB-04060 | ST(V) - SYSTEM DESCRIPTION - GENERATOR HYDROGEN SEAL OIL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-07-04 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO | NO | NO
984 | LATER | DE(STG) | SAU4005-G010-MAV-&EDA-04062 | ST(V) - PUMP & MOTOR DATA SHEET - LUBE OIL CONDITIONER | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-07-18 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
985 | LATER | DE(STG) | SAU4005-G010-MAV-&EDA-04069 | ST(V) - PUMP & MOTOR DATA SHEET - LUBE OIL TANK | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-07-18 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
986 | LATER | DE(STG) | SAU4005-G010-MAV-&MDB-04072 | ST(V) - SYSTEM DESCRIPTION - LUBE OIL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-07-18 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO | NO | NO
987 | LATER | DE(STG) | SAU4005-G010-MAG-&EDA-04073 | ST(V) - BLOWER & MOTOR DATA SHEET - GLAND STEAM CONDENSER | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-12-16 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
988 | LATER | DE(STG) | SAU4005-G010-MAY-&MLD-04075 | ST(V) - HOOK-UP DRAWING - STEAM TURBINE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-12-16 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
989 | LATER | DE(STG) | SAU4005-G010-MAY-&ELU-04095 | ST(V) - OUTLINE - STG TCS / TPS CABINET TCS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-12-16 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
990 | LATER | DE(STG) | SAU4005-G010-MAY-&EPC-04099 | ST(V) - I/O LIST - STG TCS / TPS (HARDWIRED & SOFT SIGNAL) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-12-16 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
991 | LATER | DE(STG) | SAU4005-G010-MKG-&MLU-04107 | ST(V) - OUTLINE - HYDROGEN COOLER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-06-16 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
992 | LATER | DE(STG) | SAU4005-G010-MAL-&MDB-04165 | ST(V) - STEAM DRAIN RECOMMENDATIONS FOR STEAM TURBINE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-01-15 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
993 | LATER | DE(STG) | SAU4005-G010-MKA-&MDB-04208 | ST(V) - ST GENERATOR NAME PLATE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-01-15 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
994 | LATER | DE(STG) | SAU4005-G010-MKC-&EFB-04226 | ST(V) - BLOCK DIAGRAM_COMPLETE EXCITATION SYSTEM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-01-15 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
995 | LATER | DE(STG) | SAU4005-G010-MAA-&MLD-04228 | ST(V) - IP CASING PIPING CONNECTION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-01-15 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
996 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04229 | ST(V) - IP CASING STUDS ARRANGEMENT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-01-15 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
997 | LATER | DE(STG) | SAU4005-G010-MAA-&MDB-04013 | ST(V) - STEAM BLOWING REQUIREMENT - STEAM TURBINE | A1 | COMMISSIONING | M-Mechanical engineering (normally including process engineering) | YES | COMMISSIONING |  | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-02-12 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
998 | LATER | DE(STG) | SAU4005-G010-MAA-&MDD-04014 | ST(V) - STEAM TURBINE STARTUP & SHUTDOWN CURVES | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-09-30 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
999 | LATER | DE(STG) | SAU4005-G010-MAK-&MLU-04022 | ST(V) - OUTLINE – TURNING GEAR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-09-30 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1000 | LATER | DE(STG) | SAU4005-G010-MAK-&EFF-04024 | ST(V) - WIRING SCHEMATIC - TURNING GEAR PANEL | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-09-30 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1001 | LATER | DE(STG) | SAU4005-G010-MAX-&MLU-04025 | ST(V) - OUTLINE - HPV (HIGH PRESSURE VALVE) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-09-30 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1002 | LATER | DE(STG) | SAU4005-G010-MAX-&MLU-04026 | ST(V) - OUTLINE - IPV (INTERMEDIATE PRESSURE VALVE) | A1 |  | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-09-30 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1003 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04029 | ST(V) - LIFTING ARRANGEMENT - STEAM TURBINE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-10-10 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1004 | LATER | DE(STG) | SAU4005-G010-MKY-&EED-04082 | ST(V) - PROTECTIVE RELAY SETTING(ST GENERATOR PROTECTION, EXCITER TRANSFORMER RELAY SETTING CALCULATION) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-12-31 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1005 | LATER | DE(STG) | SAU4005-G010-MAY-&ELU-04092 | ST(V) - CABINET INTERNAL ARRANGEMENT DRAWING - STG TCS / TPS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-01-13 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1006 | LATER | DE(STG) | SAU4005-G010-MAY-&ELU-04096 | ST(V) - OUTLINE - STG VMS CABINET | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-01-13 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1007 | LATER | DE(STG) | SAU4005-G010-MAA-&MDD-04163 | ST(V) - STEAM TURBINE START-UP & SHUTDOWN PROCEDURE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-02-12 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1008 | LATER | DE(STG) | SAU4005-G010-MAY-&EPC-04168 | ST(V) - INSTRUMENT LIST FOR STEAM TURBINE | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-02-12 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1009 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04242 | ST(V) - STEAM TURBINE SXD(SHELL EXPANSION DETECTOR) MOUNT ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-02-19 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1010 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04243 | ST(V) - STEAM TURBINE FOUNDATION ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-02-19 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1011 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04244 | ST(V) - STEAM TURBINE CONNECTING MEMBER ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-02-19 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1012 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04245 | ST(V) - STEAM TURBINE COUPLING GUARD ASSEMBLY - HP/IP PEDESTAL | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-02-19 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1013 | LATER | DE(STG) | SAU4005-G010-MAC-&MLU-04246 | ST(V) - STEAM TURBINE COUPLING GUARD ASSEMBLY - LP PEDESTAL | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-02-19 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1014 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04247 | ST(V) - STEAM TURBINE SPEED PICKUP/ECCENTRICITY ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-02-19 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1015 | LATER | DE(STG) | SAU4005-G010-MAC-&MLU-04248 | ST(V) - STEAM TURBINE RXD MOUNT ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-02-19 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1016 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04249 | ST(V) - STEAM TURBINE HP FRONT PEDESTAL ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-02-19 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1017 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04250 | ST(V) - STEAM TURBINE HP/IP MIDDLE PEDESTAL ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-02-19 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1018 | LATER | DE(STG) | SAU4005-G010-MAB-&MLU-04251 | ST(V) - STEAM TURBINE IP REAR PEDESTAL ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-02-19 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1019 | LATER | DE(STG) | SAU4005-G010-MAC-&MLU-04252 | ST(V) - STEAM TURBINE LPA REAR PEDESTAL ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-02-19 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1020 | LATER | DE(STG) | SAU4005-G010-MAC-&MLU-04253 | ST(V) - STEAM TURBINE LPB REAR PEDESTAL ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-02-19 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1021 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04254 | ST(V) - STEAM TURBINE OIL DEFLECTOR ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-02-19 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1022 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04255 | ST(V) - STEAM TURBINE BEARING JACKING OIL TUBING PEDESTAL ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-02-19 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1023 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04256 | ST(V) - STEAM TURBINE PEDESTAL KEY IDENTIFICATION LIST | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-02-19 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1024 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04257 | ST(V) - STEAM TURBINE EARTH(GROUND) PAD LOCATION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-02-19 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1025 | LATER | DE(STG) | SAU4005-G010-MAY-&MLU-04258 | ST(V) - STEAM TURBINE INSTRUMENT LOCATION DRAWING FOR INSTALLATION - PEDESTAL | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-02-19 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1026 | LATER | DE(STG) | SAU4005-G010-MAB-&MLU-04259 | ST(V) - STEAM TURBINE CROSSOVER PIPE OUTLINE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-02-19 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1027 | LATER | DE(STG) | SAU4005-G010-MAB-&MLU-04260 | ST(V) - HEAT RETENTION MATERIAL - CROSSOVER PIPE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-02-19 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1028 | LATER | DE(STG) | SAU4005-G010-MAY-&EMB-04093 | ST(V) - CABINET INTERNAL WIRING - STG TCS / TPS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-02-10 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1029 | LATER | DE(STG) | SAU4005-G010-MAY-&EMB-04094 | ST(V) - CABINET INTERNAL WIRING - STG VMS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-02-10 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1030 | LATER | DE(STG) | SAU4005-G010-MAY-&EPC-04101 | ST(V) - SIGNAL INTERFACE LIST BETWEEN STG TCS /TPS & DCS (HARDWIRED & SOFT SIGNAL) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-02-10 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1031 | LATER | DE(STG) | SAU4005-G010-MAA-&MDA-04184 | ST(V) - PIPING ISOMETRIC DRAWING OF STEAM SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-03-12 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1032 | LATER | DE(STG) | SAU4005-G010-MAW-&MDA-04185 | ST(V) - PIPING ISOMETRIC DRAWING OF LUBRICATING OIL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-03-12 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1033 | LATER | DE(STG) | SAU4005-G010-MKG-&MDA-04186 | ST(V) - PIPING ISOMETRIC DRAWING OF GEN GAS CONTROL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-03-12 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1034 | LATER | DE(STG) | SAU4005-G010-MKW-&MDA-04187 | ST(V) - PIPING ISOMETRIC DRAWING OF HYDROGEN SEAL OIL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-03-12 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1035 | LATER | DE(STG) | SAU4005-G010-MKU-&MDA-04188 | ST(V) - PIPING ISOMETRIC DRAWING OF GEN STATOR WINDING LIQUID COOLING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-03-12 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1036 | LATER | DE(STG) | SAU4005-G010-MAX-&MDA-04189 | ST(V) - PIPING ISOMETRIC DRAWING OF HYDROLIC FLUID PIPING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-03-12 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1037 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04173 | ST(V) - PIPING ARRANGEMENT OF STEAM SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-03-26 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1038 | LATER | DE(STG) | SAU4005-G010-MAV-&MLU-04174 | ST(V) - PIPING ARRANGEMENT OF LUBRICATING OIL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-03-26 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1039 | LATER | DE(STG) | SAU4005-G010-MKG-&MLU-04175 | ST(V) - PIPING ARRANGEMENT OF GEN GAS CONTROL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-03-26 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1040 | LATER | DE(STG) | SAU4005-G010-MKW-&MLU-04176 | ST(V) - PIPING ARRANGEMENT OF HYDROGEN SEAL OIL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-03-26 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1041 | LATER | DE(STG) | SAU4005-G010-MKU-&MLU-04177 | ST(V) - PIPING ARRANGEMENT OF GEN STATOR WINDING LIQUID COOLING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-03-26 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1042 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04204 | ST(V) - TURBINE OPENING INFORMATION FOR STG PIPING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-03-26 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1043 | LATER | DE(STG) | SAU4005-G010-MAW-&MLU-04241 | ST(V) - OUTLINE - DE-HUMIDIFICATION UNIT FOR STG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-03-03 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1044 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04261 | ST(V) - HP INNER CASING ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1045 | LATER | DE(STG) | SAU4005-G010-MAB-&MLU-04262 | ST(V) - IP INNER CASING ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1046 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04263 | ST(V) - HP OUTER CASING ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1047 | LATER | DE(STG) | SAU4005-G010-MAB-&MLU-04264 | ST(V) - IP OUTER CASING ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1048 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04265 | ST(V) - HP-IP KEY IDENTIFICATION LIST | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1049 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04266 | ST(V) - THERMOCOUPLE HOLDER ASSEMBLY (HP INLET) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1050 | LATER | DE(STG) | SAU4005-G010-MAB-&MLU-04267 | ST(V) - THERMOCOUPLE HOLDER ASSEMBLY (IP INLET) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1051 | LATER | DE(STG) | SAU4005-G010-MAC-&MLU-04268 | ST(V) - TURBINE CASING WELD PREPERATION INFORMATION - CUSTOMER CONNECTION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1052 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04269 | ST(V) - N2 RETURN PIPE ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1053 | LATER | DE(STG) | SAU4005-G010-MAB-&MLU-04270 | ST(V) - IP FRONT GLAND ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1054 | LATER | DE(STG) | SAU4005-G010-MAB-&MLU-04271 | ST(V) - IP REAR GLAND ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1055 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04272 | ST(V) - HP FRONT GLAND ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1056 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04273 | ST(V) - HP INNER GLAND ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1057 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04274 | ST(V) - HP REAR GLAND ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1058 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04275 | ST(V) - HP CASING INSTRUMENT LOCATION DRAWING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1059 | LATER | DE(STG) | SAU4005-G010-MAB-&MLU-04276 | ST(V) - IP CASING INSTRUMENT LOCATION DRAWING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1060 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04277 | ST(V) - HP CASING MAIN ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1061 | LATER | DE(STG) | SAU4005-G010-MAB-&MLU-04278 | ST(V) - IP CASING MAIN ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1062 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04281 | ST(V) - STEAM TURBINE HPV SUPPORT ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1063 | LATER | DE(STG) | SAU4005-G010-MAB-&MLU-04282 | ST(V) - STEAM TURBINE IPV SUPPORT ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1064 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04283 | ST(V) - STEAM TURBINE HPV ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1065 | LATER | DE(STG) | SAU4005-G010-MAB-&MLU-04284 | ST(V) - STEAM TURBINE IPV ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1066 | LATER | DE(STG) | SAU4005-G010-MAX-&MLU-04285 | ST(V) - STEAM TURBINE VALVE WELD PREPARATIONS INFORMATION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1067 | LATER | DE(STG) | SAU4005-G010-MAX-&MLU-04286 | ST(V) - ST_HEAT RETENTION MATERIAL_HP/IP VALVES | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1068 | LATER | DE(STG) | SAU4005-G010-MAA-&MFB-04287 | ST(V) - TURBINE SUPERVISORY INSTRUMENT DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-04-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1069 | LATER | DE(STG) | SAU4005-G010-MAW-&MLD-04196 | ST(V) - HANGER & SUPPORT DRAWING FOR TURBINE STEAM SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-09 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1070 | LATER | DE(STG) | SAU4005-G010-MAV-&MLD-04197 | ST(V) - HANGER & SUPPORT DRAWING FOR TURBINE LUBRICATING OIL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-09 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1071 | LATER | DE(STG) | SAU4005-G010-MKG-&MLD-04198 | ST(V) - HANGER & SUPPORT DRAWING FOR GEN GAS CONTROL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-09 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1072 | LATER | DE(STG) | SAU4005-G010-MKW-&MLD-04199 | ST(V) - HANGER & SUPPORT DRAWING FOR HYDROGEN SEAL OIL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-09 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1073 | LATER | DE(STG) | SAU4005-G010-MKU-&MLD-04200 | ST(V) - HANGER & SUPPORT DRAWING FOR GEN STATOR WINDING LIQUID COOLING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-09 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1074 | LATER | DE(STG) | SAU4005-G010-MAL-&MLD-04201 | ST(V) - HANGER & SUPPORT DRAWING FOR SMALL BORE PIPING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-09 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1075 | LATER | DE(STG) | SAU4005-G010-MKA-&MLU-04207 | ST(V) - GENERATOR FIELD ASSEMBLY AND DISASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-09 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1076 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04279 | ST(V) - HEAT RETENTION MATERIAL - HP/IP TURBINE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-16 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1077 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04280 | ST(V) - HORIZONTAL AND VERTICAL JOINT STUD TIGHTENING_HIP CASING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-16 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1078 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04182 | ST(V) - ARRANGEMENT-TURBINE LAGGING SUPPORT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-23 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1079 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04183 | ST(V) - OUTLINE-STEAM TURBINE ENCLOSURE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-03-24 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1080 | LATER | DE(STG) | SAU4005-G010-MAY-&EMB-04076 | ST(V) - INTERCONNECTION WIRING DIAGRAM - STEAM TURBINE | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-07 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1081 | LATER | DE(STG) | SAU4005-G010-MAY-&ELU-04098 | ST(V) - HMI GRAPHIC - STG TCS / TPS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-04-07 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1082 | LATER | DE(STG) | SAU4005-G010-MAY-&ELU-04169 | ST(V) - INSTRUMENT CABINET DRAWING FOR STEAM TURBINE | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-05-07 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1083 | LATER | DE(STG) | SAU4005-G010-MAY-&EDA-04170 | ST(V) - INSTRUMENT DATASHEET FOR LOCAL INSTRUMENT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-05-07 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1084 | LATER | DE(STG) | SAU4005-G010-MAY-&ELU-04172 | ST(V) - CONDUIT ARRANGEMENT DRAWING FOR STEAM TURBINE | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-04-07 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1085 | LATER | DE(STG) | SAU4005-G010-MAC-&MLU-04238 | ST(V) - ST_OUTLINE DRAWING_LP GLAND PACKING RING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-05-07 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1086 | LATER | DE(STG) | SAU4005-G010-MAB-&MLU-04237 | ST(V) - ST_OUTLINE DRAWING_IP GLAND PACKING RING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-03-31 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1087 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04236 | ST(V) - ST_OUTLINE DRAWING_HP GLAND PACKING RING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-03-31 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1088 | LATER | DE(STG) | SAU4005-G010-MAC-&MLU-04239 | ST(V) - ST_OUTLINE DRAWING_LP DIAPHRAGM PACKING RING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-03-31 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1089 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04233 | ST(V) - ST_ASSEMBLY DRAWING_DIAPHRAGM SUPPORT BAR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-05-07 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1090 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04234 | ST(V) - ST_ASSEMBLY DRAWING_PACKING RING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-05-07 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1091 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04235 | ST(V) - ST_ASSEMBLY DRAWING_DIAPHRAGM BOLT TORQUE TIGHTING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-05-07 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1092 | LATER | DE(STG) | SAU4005-G010-MAD-&MLU-04304 | ST(V) - STEAM TURBINE JOURNAL BEARING ASSY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-05-07 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1093 | LATER | DE(STG) | SAU4005-G010-MAD-&MLU-04305 | ST(V) - STEAM TURBINE THRUST BEARING ASSY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-05-07 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1094 | LATER | DE(STG) | SAU4005-G010-MAY-&ELD-04171 | ST(V) - INSTRUMENT LOCATION DRAWING FOR STEAM TURBINE | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-06-04 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1095 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04288 | ST(V) - STEAM TURBINE LP OUTER CASING ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-06-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1096 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04289 | ST(V) - STEAM TURBINE LP INNER CASING ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-06-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1097 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04290 | ST(V) - STEAM TURBINE LP CASING BOLT ARRANGEMENT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-06-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1098 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04291 | ST(V) - STEAM TURBINE LP CASING END GIB & KEY ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-06-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1099 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04292 | ST(V) - STEAM TURBINE LP DEFLECTOR(STEAM GUIDE) ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-06-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1100 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04293 | ST(V) - STEAM TURBINE LP INNER CASINGSHIELDING HORIZONTAL JOINT ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-06-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1101 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04294 | ST(V) - STEAM TURBINE LP PACKING GLAND ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-06-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1102 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04295 | ST(V) - STEAM TURBINE LP PACKING CASING ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-06-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1103 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04296 | ST(V) - STEAM TURBINE LP RELIEF DIAPHRAGM ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-06-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1104 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04297 | ST(V) - STEAM TURBINE LP WATER COOLING SPRAY ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-06-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1105 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04298 | ST(V) - STEAM TURBINE VSL PIPING ASSY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-06-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1106 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04299 | ST(V) - STEAM TURBINE PERFORMANCE TEST PIPING FOR LP EXHAUST PRESSURE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-06-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1107 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04300 | ST(V) - STEAM TURBINE LP CONDENSERSEAL BELLOWS ASSY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-06-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1108 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04301 | ST(V) - STEAM TURBINE LP PIPING CONNECTION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-06-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1109 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04302 | ST(V) - STEAM TURBINE INSTRUMENT LOCATION DRAWING FOR INSTALLATION - LP CASING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-06-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1110 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04303 | ST(V) - STEAM TURBINE LP KEY IDENTIFICATION LIST | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-06-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1111 | LATER | DE(STG) | SAU4005-G010-MAD-&MLU-04015 | ST(V) - BEARING ALIGNMENT DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-07-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1112 | LATER | DE(STG) | SAU4005-G010-MAA-&MDA-04016 | ST(V) - CLEARANCE MEASUREMENT DATA(HP/IP) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-07-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1113 | LATER | DE(STG) | SAU4005-G010-MKA-&MLD-04105 | ST(V) - GENERATOR FIELD CLEARANCE DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-07-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1114 | LATER | DE(STG) | SAU4005-G010-MKA-&MLU-04312 | ST(V) - GENERATOR BEARING ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-07-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1115 | LATER | DE(STG) | SAU4005-G010-MAA-&MDD-04313 | ST(V) - PIPING STRESS ANALYSIS REPORT FOR STG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-07-02 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1116 | LATER | DE(STG) | SAU4005-G010-MAC-&MDA-04017 | ST(V) - CLEARANCE MEASUREMENT DATA(LP) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-07-30 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1117 | LATER | DE(STG) | SAU4005-G010-MAA-&MEC-04027 | ST(V) - CRANE & HOIST REQUIREMENTS STG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-08-09 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1118 | LATER | DE(STG) | SAU4005-G010-MAV-&MLU-04202 | ST(V) - OUTLINE DRAWING FOR BEARING DRAIN ENLARGEMENT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-12-31 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1119 | LATER | DE(STG) | SAU4005-G010-MKW-&MLU-04203 | ST(V) - OUTLINE DRAWING FOR SEAL OIL DRAIN ENLARGEMENT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-12-31 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1120 | LATER | DE(STG) | SAU4005-G010-MAA-&MPC-04205 | ST(V) - LINE LIST FOR STG PIPING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-08-27 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1121 | LATER | DE(STG) | SAU4005-G010-MAX-&MLU-04020 | ST(V) - BLOWDOWN COVER OUTLINE - HPV (HIGH PRESSURE VALVE) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-10-01 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1122 | LATER | DE(STG) | SAU4005-G010-MAX-&MLU-04021 | ST(V) - BLOWDOWN COVER OUTLINE - IPV (INTERMEDIATE PRESSURE VALVE) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2026-10-01 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1123 | LATER | DE(STG) | SAU4005-G010-MKC-&ELU-04078 | ST(V) - OUTLINE - ST EXCITATION TRANSFORMER | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-10-31 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1124 | LATER | DE(STG) | SAU4005-G010-MKY-&ELU-04079 | ST(V) - OUTLINE - ST GENERATOR PROTECTION RELAY PANEL | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-10-31 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1125 | LATER | DE(STG) | SAU4005-G010-MKY-&ELU-04080 | ST(V) - OUTLINE - ST NGR & NGTR PANEL | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-10-31 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1126 | LATER | DE(STG) | SAU4005-G010-MKY-&ELU-04081 | ST(V) - OUTLINE & DETAIL DRAWINGS - ST AC/DC BUSDUCT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-10-31 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1127 | LATER | DE(STG) | SAU4005-G010-MAV-&EFF-04083 | ST(V) - SCHEMATIC DIAGRAM - ST EBOP DC MOTOR STARTER PANEL | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-10-31 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1128 | LATER | DE(STG) | SAU4005-G010-MAW-&EFF-04084 | ST(V) - SCHEMATIC DIAGRAM - ST ESOP DC MOTOR STARTER PANEL | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-10-31 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1129 | LATER | DE(STG) | SAU4005-G010-MKC-&EFF-04085 | ST(V) - SCHEMATIC DIAGRAMS - ST EXCITATION TRANSFORMER | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-10-31 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1130 | LATER | DE(STG) | SAU4005-G010-MKY-&EFF-04086 | ST(V) - SCHEMATIC DIAGRAMS - ST GEN SYNCHRONIZING & METERING PANEL | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-10-31 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1131 | LATER | DE(STG) | SAU4005-G010-MKY-&EFF-04087 | ST(V) - SCHEMATIC DIAGRAMS - ST GENERATOR PROTECTION RELAY PANEL | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-10-31 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1132 | LATER | DE(STG) | SAU4005-G010-MKY-&EFF-04088 | ST(V) - SCHEMATIC DIAGRAMS - ST NGR & NGTR PANEL | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFC | [14 empty] | 2025-10-31 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1133 | LATER | DE(STG) | SAU4005-G010-MAA-&MDC-04117 | ST(V) - O&M MANUAL - STEAM TURBINE & AUXILIARIES | A1 | COMMISSIONING | M-Mechanical engineering (normally including process engineering) | YES | COMMISSIONING |  | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-10-01 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1134 | LATER | DE(STG) | SAU4005-G010-MKA-&MDC-04118 | ST(V) - O&M MANUAL - GENERATOR & AUXILIARIES | A1 | COMMISSIONING | M-Mechanical engineering (normally including process engineering) | YES | COMMISSIONING |  | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-10-01 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1135 | LATER | DE(STG) | SAU4005-G010-MKC-&EDD-04225 | ST(V) - PSS STUDY REPORT_EXCITATION SYSTEM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-11-01 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | YES | NO | SEC
1136 | LATER | DE(STG) | SAU4005-G010-MAA-&MDA-04031 | ST(V) - TECHNICAL DATA SHEET - STEAM TURBINE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFA | IFD |  |  | 2025-08-28 |  |  |  | 2025-09-17 |  |  |  | 2025-10-23 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | YES | C2 | NO
1137 | LATER | DE(STG) | SAU4005-G010-MKA-&MDA-04108 | ST(V) - GENERATOR DATA SHEET AND CHARACTERISTIC CURVES | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFA | IFC |  |  | 2025-06-16 |  |  |  | 2025-09-17 |  |  |  | 2025-10-23 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | YES | C2 | NO
1138 | LATER | DE(STG) | SAU4005-G010-MAA-&MDD-04302 | ST(V) - HAZARDOUS AREA CLASSIFICATION FOR STG PACKAGES | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | COMMISSIONING |  | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1139 | LATER | DE(STG) | SAU4005-G010-MKB-&ELU-04112 | ST(V) - GENERATOR CURRENT TRANSFORMER ASSEMBLY | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-11-04 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1140 | LATER | MHDB | SAU4005-G011-H__-&MDD-04803 | HRSG(V) - Design Life Analysis Report | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1141 | LATER | DE(STG) | SAU4005-G010-MKA-&ELU-04179 | ST(V) - GENERATOR SHAFT GROUNDING BRUSH RIGGING ASSEMBLY | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-11-04 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1142 | LATER | DE(STG) | SAU4005-G010-MAA-&MDB-04231 | ST(V) - SYSTEM DESCRIPTION - FORCED COOLING AIR SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-07-08 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
1143 | LATER | MHDB | SAU4005-G011-H__-&MDA-04804 | HRSG(V) - Degradation Curve | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-05-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1144 | LATER | MHDB | SAU4005-G011-H__-&MDA-04805 | HRSG(V) - Start-up Curve | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-05-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1145 | LATER | MHDB | SAU4005-G011-H__-&MDA-04806 | HRSG(V) - Design Report for Insulation (HRSG Internal) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-05-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1146 | LATER | MHDB | SAU4005-G011-H__-&MDD-04807 | HRSG(V) - Design Report for Insulation of Piping and Equipments (HRSG External) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-05-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1147 | LATER | MHDB | SAU4005-G011-H__-&MDA-04809 | HRSG(V) - Design Report for Noise Protection (Silencer Caluculation) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-05-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1148 | LATER | MHDB | SAU4005-G011-CJF-&MDB-04811 | HRSG(V) - System Description | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-05-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1149 | LATER | MHDB | SAU4005-G011-HAB-&MFB-04812 | HRSG(V) - P&I Diagram | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFC |  |  | 2025-04-29 |  |  |  | 2025-05-19 |  |  |  | 2025-06-24 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1150 | LATER | MHDB | SAU4005-G011-H__-&MDB-04813 | HRSG(V) - HRSG Blowdown System Summary | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-04-29 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1151 | LATER | MHDB | SAU4005-G011-UHB-&MED-04814 | HRSG(V) - Strength Calculation for HRSG Steel Structure | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1152 | LATER | MHDB | SAU4005-G011-UHB-&MED-04815 | HRSG(V) - Strength Calculation Report for HRSG Stack | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1153 | LATER | MHDB | SAU4005-G011-HAA-&MED-04816 | HRSG(V) - ASME Strength Calculation Sheet for Drum (with Deaerator) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1154 | LATER | MHDB | SAU4005-G011-HAA-&MED-04817 | HRSG(V) - ASME Strength Calculation Sheet for Blowdown Tank | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1155 | LATER | MHDB | SAU4005-G011-HAA-&MED-04818 | HRSG(V) - ASME Strength Calculation Sheets for Header | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1156 | LATER | MHDB | SAU4005-G011-HAA-&MED-04819 | HRSG(V) - ASME Strength Calculation for Link | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1157 | LATER | MHDB | SAU4005-G011-HAA-&MED-04820 | HRSG(V) - ASME Strength Calculation for Tube | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-06-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1158 | LATER | MHDB | SAU4005-G011-HAA-&MTL-04821 | HRSG(V) - Pressure Part Arrangement | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFC |  |  | 2025-06-15 |  |  |  | 2025-07-05 |  |  |  | 2025-08-10 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1159 | LATER | MHDB | SAU4005-G011-HAA-&MDD-04822 | HRSG(V) - Assembly Drawing of Steam Drum | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1160 | LATER | MHDB | SAU4005-G011-HAA-&MDD-04823 | HRSG(V) - Detail of External Attachment of Steam Drum | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1161 | LATER | MHDB | SAU4005-G011-HAA-&MDD-04824 | HRSG(V) - Internal Assembly Drawing of Steam Drum | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1162 | LATER | MHDB | SAU4005-G011-HAA-&MDD-04825 | HRSG(V) - HP Steam Drum Name Plate Detail | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-10-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1163 | LATER | MHDB | SAU4005-G011-HAA-&MLU-04826 | HRSG(V) - Typical Drawing for Drum Insulation | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-10-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1164 | LATER | MHDB | SAU4005-G011-HAA-&MLB-04827 | HRSG(V) - Foundation Loading & Location Drawing for Blowdown Tank | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-05-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1165 | LATER | MHDB | SAU4005-G011-HAA-&MLU-04828 | HRSG(V) - Equipment Outline Drawing for Blowdown Tank | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1166 | LATER | MHDB | SAU4005-G011-HAA-&MLU-04829 | HRSG(V) - Link Assembly Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-11-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1167 | LATER | MHDB | SAU4005-G011-HAN-&MLU-04830 | HRSG(V) - Vent & Drain Line (Module /Field weld) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-11-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1168 | LATER | MHDB | SAU4005-G011-H__-&MDA-04831 | HRSG(V) - Data & BOM of Insulation for Piping | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-12-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1169 | LATER | MHDB | SAU4005-G011-H__-&MDA-04832 | HRSG(V) - Calculation of each Drum Volume | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-05-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1170 | LATER | MHDB | SAU4005-G011-H__-&MDD-04835 | HRSG(V) - HRSG CFD Report | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFC |  |  | 2025-06-30 |  |  |  | 2025-07-20 |  |  |  | 2025-08-09 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1171 | LATER | MHDB | SAU4005-G011-HAX-&MDA-04837 | HRSG(V) - Desuperheater Data Sheet & Drawings | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1172 | LATER | MHDB | SAU4005-G011-LCQ-&MDA-04838 | HRSG(V) - Spec. & Drawing for Blowdown Tank Pump | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1173 | LATER | MHDB | SAU4005-G011-LBF-&MDA-04839 | HRSG(V) - Spec. & Drawing for Safety & Relief Valve | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1174 | LATER | MHDB | SAU4005-G011-HNE-&MDA-04840 | HRSG(V) - Spec. & Drawing for Stack Damper | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1175 | LATER | MHDB | SAU4005-G011-LBF-&MDA-04841 | HRSG(V) - Spec. & Drawing for Vent Silencer | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1176 | LATER | MHDB | SAU4005-G011-HAA-&MLU-04842 | HRSG(V) - Spec. & Drawing for Deaerator | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1177 | LATER | MHDB | SAU4005-G011-HNE-&MDA-04843 | HRSG(V) - Spec. & Drawing for Stack Silencer | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1178 | LATER | MHDB | SAU4005-G011-HAY-&MDA-04844 | HRSG(V) - Spec. & Drawing for Boiler Stress Evaluator System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1179 | LATER | MHDB | SAU4005-G011-H__-&MFB-04845 | HRSG(V) - P&ID for Diverter & Guillotine Damper | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFC |  |  | 2025-07-02 |  |  |  | 2025-07-22 |  |  |  | 2025-08-27 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1180 | LATER | MHDB | SAU4005-G011-H__-&MDB-04846 | HRSG(V) - System Description for Diverter & Guillotine Damper | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-06-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1181 | LATER | MHDB | SAU4005-G011-H__-&MLB-04847 | HRSG(V) - Foundation Drawing including Loading Data for Diverter & Guillotine Damper | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-06-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1182 | LATER | MHDB | SAU4005-G011-H__-&MLB-04848 | HRSG(V) - Fan Skid Drawing including Foundation and Loading Data with specification for Diverter & Guillotine Damper | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-05-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1183 | LATER | MHDB | SAU4005-G011-H__-&MDB-04850 | HRSG(V) - HPU Specification & Drawing for Diverter & Guillotine Damper | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-05-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1184 | LATER | MHDB | SAU4005-G011-H__-&MDB-04851 | HRSG(V) - Hoist Specification & Drawing for Diverter & Guillotine Damper | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-31 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1185 | LATER | MHDB | SAU4005-G011-H__-&MDB-04852 | HRSG(V) - Platform for Access Door for Diverter Damper | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1186 | LATER | MHDB | SAU4005-G011-SMH-&MDA-04853 | HRSG(V) - Spec. & Drawing for Hoist | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1187 | LATER | MHDB | SAU4005-G011-LCP-&MDA-04854 | HRSG(V) - Spec. & Drawing for Recirculation Pump | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1188 | LATER | MHDB | SAU4005-G011-UHB-&MTL-04855 | HRSG(V) - Non-Metallic Expansion Joint | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1189 | LATER | MHDB | SAU4005-G011-H__-&MTB-04856 | HRSG(V) - Name Plate Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFP |  |  | 2025-08-14 |  |  |  | 2025-09-03 |  |  |  | 2025-10-09 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1190 | LATER | MHDB | SAU4005-G011-UHB-&CTL-04858 | HRSG(V) - Foundation Load Table for HRSG Steel Structure and Stack | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-05-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1191 | LATER | MHDB | SAU4005-G011-UHB-&CTL-04859 | HRSG(V) - Base Plate and Anchor Bolts Detail for HRSG (Steel Structure) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-05-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1192 | LATER | MHDB | SAU4005-G011-UHB-&CTL-04860 | HRSG(V) - Base Plate and Anchor Bolts Detail for HRSG Auxiliary Steel Structure | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-05-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1193 | LATER | MHDB | SAU4005-G011-UHB-&MDB-04861 | HRSG(V) - General Note for HRSG Steel Structure | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1194 | LATER | MHDB | SAU4005-G011-UHB-&MTL-04862 | HRSG(V) - Typical Platform Detail for HRSG Steel Structure | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1195 | LATER | MHDB | SAU4005-G011-UHB-&MTL-04863 | HRSG(V) - Typical Handrail Detail for HRSG Steel Structure | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1196 | LATER | MHDB | SAU4005-G011-UHB-&MTL-04864 | HRSG(V) - Typical Ladder Detail for HRSG Steel Structure | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1197 | LATER | MHDB | SAU4005-G011-UHB-&MTL-04865 | HRSG(V) - Arrangement for HRSG Platform Structure | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1198 | LATER | MHDB | SAU4005-G011-UHB-&MTL-04866 | HRSG(V) - Arrangement for HRSG Canpoy Structure | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFC |  |  | 2025-07-15 |  |  |  | 2025-08-04 |  |  |  | 2025-08-24 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1199 | LATER | MHDB | SAU4005-G011-UHA-&MLH-04867 | HRSG(V) - General Arrangement | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFC |  |  | 2025-04-29 |  |  |  | 2025-05-19 |  |  |  | 2025-06-08 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1200 | LATER | MHDB | SAU4005-G011-UHB-&MTL-04868 | HRSG(V) - Arrangement of Casing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-06-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1201 | LATER | MHDB | SAU4005-G011-UHB-&MTL-04869 | HRSG(V) - Arrangement of Inlet Duct | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFC |  |  | 2025-06-30 |  |  |  | 2025-07-20 |  |  |  | 2025-08-09 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1202 | LATER | MHDB | SAU4005-G011-UHB-&MTL-04870 | HRSG(V) - Arrangement of Main Stack | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFC |  |  | 2025-06-30 |  |  |  | 2025-07-20 |  |  |  | 2025-08-09 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1203 | LATER | MHDB | SAU4005-G011-UHB-&MTL-04871 | HRSG(V) - Arrangement of Bypass Stack | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFC |  |  | 2025-04-29 |  |  |  | 2025-05-19 |  |  |  | 2025-06-08 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1204 | LATER | MHDB | SAU4005-G011-UHB-&MTL-04872 | HRSG(V) - General Arrangement Drawing for Diverter & Guillotine Damper | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFC |  |  | 2025-06-15 |  |  |  | 2025-07-05 |  |  |  | 2025-07-25 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1205 | LATER | MHDB | SAU4005-G011-HA_-&MDA-04874 | HRSG(V) - Stress Analysis Isometric Drawing for Critical Piping | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1206 | LATER | MHDB | SAU4005-G011-HA_-&MDA-04875 | HRSG(V) - Erection Isometric Drawing for PIPNG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1207 | LATER | MHDB | SAU4005-G011-HB_-&MDA-04876 | HRSG(V) - Pipe Support Drawing for Piping (Large Bore / Small Bore) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-11-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1208 | LATER | MHDB | SAU4005-G011-HB_-&MDA-04877 | HRSG(V) - Typical Support Drawing for Small Bore Piping | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-11-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1209 | LATER | MHDB | SAU4005-G011-HA_-&MTL-04878 | HRSG(V) - Large Bore Piping Arrangement of HRSG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-11-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1210 | LATER | MHDB | SAU4005-G011-HA_-&MPA-04879 | HRSG(V) - Manual Valve List and ASSEMBLY Drawing for HRSG Piping | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1211 | LATER | MHDB | SAU4005-G011-HA_-&MPA-04880 | HRSG(V) - Specialty List and Drawing for HRSG Piping | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1212 | LATER | MHDB | SAU4005-G011-HA_-&MEC-04881 | HRSG(V) - Piping Material Classification (for HRSG) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1213 | LATER | MHDB | SAU4005-G011-HA_-&MEC-04882 | HRSG(V) - Piping Insulation Specification | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFp | [14 empty] | 2025-11-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1214 | LATER | MHDB | SAU4005-G011-HA_-&MPD-04883 | HRSG(V) - Line List | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-06-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1215 | LATER | MHDB | SAU4005-G011-HA_-&MPL-04885 | HRSG(V) - Terminal Point List | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-06-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1216 | LATER | MHDB | SAU4005-G011-HYA-&EDB-04886 | HRSG(V) - Control Description | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFA | IFC |  |  | 2025-06-15 |  |  |  | 2025-07-05 |  |  |  | 2025-07-25 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1217 | LATER | MHDB | SAU4005-G011-HYA-&EFB-04887 | HRSG(V) - System Configuration Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1218 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04890 | HRSG(V) - MOV List | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-06-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1219 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04891 | HRSG(V) - Control Valve List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-06-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1220 | LATER | MHDB | SAU4005-G011-HYA-&EPC-04892 | HRSG(V) - Instrument List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-06-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1221 | LATER | MHDB | SAU4005-G011-HYA-&EFF-04893 | HRSG(V) - Control Logic Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1222 | LATER | MHDB | SAU4005-G011-HYA-&EFF-04894 | HRSG(V) - Control Loop Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1223 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04895 | HRSG(V) - MOV Data Sheet/Drawings | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1224 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04896 | HRSG(V) - Control Valve Data Sheet/Drawings | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFA | IFC |  |  | 2025-09-14 |  |  |  | 2025-10-04 |  |  |  | 2025-10-24 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1225 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04897 | HRSG(V) - Field Instrument Data Sheet/Drawings(Include below) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1226 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04898 | HRSG(V) - Drum Level Gauge Datasheet/Drawings | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1227 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04899 | HRSG(V) - Flow Element Datasheet and Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-10-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1228 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04900 | HRSG(V) - Level Switch Datasheet and Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1229 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04901 | HRSG(V) - Local Gauge and Temp. Element Specification | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1230 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04902 | HRSG(V) - Transmiter Speicification | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1231 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04903 | HRSG(V) - Remote Drum Level Indicator Datasheet/Drawings | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFA | IFC |  |  | 2025-09-14 |  |  |  | 2025-10-04 |  |  |  | 2025-10-24 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1232 | LATER | MHDB | SAU4005-G011-HYA-&EMA-04904 | HRSG(V) - Wiring Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1233 | LATER | MHDB | SAU4005-G011-HYA-&EMB-04905 | HRSG(V) - Interccnnection Wiring Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1234 | LATER | MHDB | SAU4005-G011-HYA-&EFP-04906 | HRSG(V) - DCS I/O List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-06-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1235 | LATER | MHDB | SAU4005-G011-HYA-&EFP-04907 | HRSG(V) - Alarm Set Point List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-05-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1236 | LATER | MHDB | SAU4005-G011-HYA-&EEC-04908 | HRSG(V) - Utility Consumption List | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-04-29 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1237 | LATER | MHDB | SAU4005-G011-HYA-&EFF-04910 | HRSG(V) - Start-up & Shut-down Sequence Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1238 | LATER | MHDB | SAU4005-G011-HYA-&EEC-04911 | HRSG(V) - Aircraft Warning Light Data sheet / layout diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1239 | LATER | MHDB | SAU4005-G011-HYA-&ELD-04912 | HRSG(V) - Instrument Location & Conduit Plan Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1240 | LATER | MHDB | SAU4005-G011-HYA-&ELD-04913 | HRSG(V) - Instrument Catalog & installation Detail Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1241 | LATER | MHDB | SAU4005-G011-HYA-&ELD-04914 | HRSG(V) - Instrument Installation Detail Drawings | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-06-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1242 | LATER | MHDB | SAU4005-G011-HYA-&ELU-04915 | HRSG(V) - Local Panel Assembly Drawing for Diverter & Guillotine Damper | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-31 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1243 | LATER | MHDB | SAU4005-G011-HYA-&EMA-04916 | HRSG(V) - Instrument Hook-up for Diverter & Guillotine Damper | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1244 | LATER | MHDB | SAU4005-G011-HYA-&EMA-04917 | HRSG(V) - Wiring and Terminal Connection Diagram for Diverter & Guillotine Damper | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1245 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04918 | HRSG(V) - Valve List for Diverter & Guillotine Damper | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-31 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1246 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04919 | HRSG(V) - Instrument List for Diverter & Guillotine Damper | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-31 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1247 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04920 | HRSG(V) - Instrument Data Sheet for Diverter & Guillotine Damper | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1248 | LATER | MHDB | SAU4005-G011-HYA-&EFQ-04921 | HRSG(V) - Alarm and Trip Setting List for Diverter & Guillotine Damper | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-31 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1249 | LATER | MHDB | SAU4005-G011-HYA-&EFF-04922 | HRSG(V) - Control Logic Diagram for Diverter & Guillotine Damper | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-31 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1250 | LATER | MHDB | SAU4005-G011-HYA-&EDB-04923 | HRSG(V) - Control Configurtion for Diverter Damper | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1251 | LATER | MHDB | SAU4005-G011-HYA-&EDB-04924 | HRSG(V) - PLC Specificatoin for Diverter Damper | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1252 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04925 | HRSG(V) - PLC I/O List for Diverter Damper (include Datalink IO list) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1253 | LATER | MHDB | SAU4005-G011-HYA-&EFC-04926 | HRSG(V) - PLC HMI Drawing for Diverter Damper | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1254 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04927 | HRSG(V) - Control Cabinet Drawing for Diverter Damper (include Schematic and Wiring Diagram) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1255 | LATER | MHDB | SAU4005-G011-HNE-&EDA-04929 | HRSG(V) - SPEC. & Drawing for CEMS | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1256 | LATER | MHDB | SAU4005-G011-HNE-&ELU-04930 | HRSG(V) - Foundation drawing for CEMS Room | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-06-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1257 | LATER | MHDB | SAU4005-G011-HYA-&ELU-04931 | HRSG(V) - General Arrangement drawing for CEMS Room | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-06-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1258 | LATER | MHDB | SAU4005-G011-HYA-&ELB-04932 | HRSG(V) - Nozzle Orientation and Cable Route Drawing for CEMS | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1259 | LATER | MHDB | SAU4005-G011-HYA-&EDB-04933 | HRSG(V) - Equipment Specification for CEMS | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1260 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04934 | HRSG(V) - Instrument List and Data Sheet for CEMS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1261 | LATER | MHDB | SAU4005-G011-HYA-&EDB-04935 | HRSG(V) - Contol Configuration for CEMS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1262 | LATER | MHDB | SAU4005-G011-HYA-&EFQ-04936 | HRSG(V) - Alarm and Trip Setting List for for CEMS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1263 | LATER | MHDB | SAU4005-G011-HYA-&EMA-04937 | HRSG(V) - Wiring and Terminal Connection Diagram for CEMS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1264 | LATER | MHDB | SAU4005-G011-HYA-&ELB-04938 | HRSG(V) - Earthing Concept | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-04-29 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1265 | LATER | MHDB | SAU4005-G011-HYA-&EPC-04939 | HRSG(V) - Electrical Load List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-04-29 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1266 | LATER | MHDB | SAU4005-G011-HYA-&ELD-04940 | HRSG(V) - Grounding and Lightning Plan Diagrams | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1267 | LATER | MHDB | SAU4005-G011-HYA-&EFA-04941 | HRSG(V) - Electrical Single Line Diagrams | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFA | IFC |  |  | 2025-05-15 |  |  |  | 2025-06-04 |  |  |  | 2025-06-24 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1268 | LATER | MHDB | SAU4005-G011-HYA-&EEC-04942 | HRSG(V) - Power Distribution Panel Drawings | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1269 | LATER | MHDB | SAU4005-G011-HYA-&EEC-04943 | HRSG(V) - Lighting Plan Diagrams | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1270 | LATER | MHDB | SAU4005-G011-HYA-&EEC-04944 | HRSG(V) - Lighting and Small Power Distribution Panel Drawings | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1271 | LATER | MHDB | SAU4005-G011-HYA-&EEC-04945 | HRSG(V) - Junction Box/Cabinet Layout and Stanchion Layout Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1272 | LATER | MHDB | SAU4005-G011-HYA-&EED-04946 | HRSG(V) - Cable Schedule | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1273 | LATER | MHDB | SAU4005-G011-HNE-&EMA-04947 | HRSG(V) - Cable Connection Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1274 | LATER | MHDB | SAU4005-G011-HYA-&ELD-04948 | HRSG(V) - Cable Tray & Raceway Layout Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1275 | LATER | MHDB | SAU4005-G011-HYA-&EEC-04949 | HRSG(V) - CABLE SPECIFICATION | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1276 | LATER | MHDB | SAU4005-G011-HYA-&EDB-04952 | HRSG(V) - Conduit Plan | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1277 | LATER | MHDB | SAU4005-G011-HYA-&EMA-04953 | HRSG(V) - Single Line Diagram for Diverter & Guillotine Damper | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1278 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04954 | HRSG(V) - Cable Schedule for Diverter & Guillotine Damper | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1279 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04955 | HRSG(V) - Motor Data Sheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1280 | LATER | MHDB | SAU4005-G011-HYA-&EDB-04956 | HRSG(V) - Motor Terminal Limit Curve | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1281 | LATER | MHDB | SAU4005-G011-HYA-&ETA-04957 | HRSG(V) - Motor Terminal Box Detail Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1282 | LATER | MHDB | SAU4005-G011-HNY-&MFQ-04958 | HRSG(V) - Alarm and Trip Setting List for SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1283 | LATER | MHDB | SAU4005-G011-HNY-&MMB-04959 | HRSG(V) - Cable Interconnection Diagram for SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1284 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04960 | HRSG(V) - Cable List for SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1285 | LATER | MHDB | SAU4005-G011-HNY-&MLU-04961 | HRSG(V) - Cable Tray & Conduit Drawing for SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1286 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04962 | HRSG(V) - Control Logic & Loop for SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1287 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04963 | HRSG(V) - Control Valve Data Sheet & Drawings for SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-31 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1288 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04964 | HRSG(V) - Catalyst Data Sheet & Drawings for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1289 | LATER | MHDB | SAU4005-G011-HNY-&MED-04965 | HRSG(V) - Equipment Calculation Sheet for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1290 | LATER | MHDB | SAU4005-G011-HNY-&MLU-04966 | HRSG(V) - General Arrangement Drawing of Ammonia Storage Area for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFC |  |  | 2025-07-15 |  |  |  | 2025-08-04 |  |  |  | 2025-08-24 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1291 | LATER | MHDB | SAU4005-G011-HNY-&MLU-04967 | HRSG(V) - General arrangement Drawing of Internal Part for SCR (with AIG and Catalyst Frame & Sealing Arrangement) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-06-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1292 | LATER | MHDB | SAU4005-G011-HNY-&MLU-04968 | HRSG(V) - Dilution Tank Drawing for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1293 | LATER | MHDB | SAU4005-G011-HNY-&MLU-04969 | HRSG(V) - Vaporizer Arrangement Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1294 | LATER | MHDB | SAU4005-G011-HNY-&MLU-04970 | HRSG(V) - Ammonia Distribution Header Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1295 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04971 | HRSG(V) - Hot Gas Circulation Fan Data Sheet and Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1296 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04972 | HRSG(V) - Ammonia Supply Pump Data Sheet and Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1297 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04973 | HRSG(V) - Ammonia Unloading Pump Data Sheet and Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1298 | LATER | MHDB | SAU4005-G011-HNY-&MLD-04974 | HRSG(V) - Instrument Hook-up for SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1299 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04975 | HRSG(V) - Instrument Data Sheet for SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1300 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04976 | HRSG(V) - Instrument List for SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1301 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04977 | HRSG(V) - INSTRUMENT LOCATION FOR SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1302 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04978 | HRSG(V) - SPECIAL ITEM LIST AND DRAWING FOR SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1303 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04979 | HRSG(V) - Piping Isometric Drawing for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-31 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1304 | LATER | MHDB | SAU4005-G011-HNY-&MLU-04980 | HRSG(V) - Piping Layout Drawing for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-31 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1305 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04981 | HRSG(V) - Piping Support Drawing for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-31 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1306 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04982 | HRSG(V) - Line List for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-31 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1307 | LATER | MHDB | SAU4005-G011-HNY-&MFB-04983 | HRSG(V) - P&ID for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFC |  |  | 2025-07-15 |  |  |  | 2025-08-04 |  |  |  | 2025-09-09 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1308 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04984 | HRSG(V) - Junction Box Drawing for SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1309 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04985 | HRSG(V) - Local Panel Drawing for SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1310 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04987 | HRSG(V) - Electrical and I&c BOM for SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1311 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04988 | HRSG(V) - Process Mass Balance for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1312 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04989 | HRSG(V) - System Description for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFC |  |  | 2025-07-15 |  |  |  | 2025-08-04 |  |  |  | 2025-08-24 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1313 | LATER | MHDB | SAU4005-G011-HNY-&MDB-04990 | HRSG(V) - Technical Specification for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1314 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04991 | HRSG(V) - Valve List for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1315 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04992 | HRSG(V) - Valve Drawing for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1316 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04993 | HRSG(V) - SPEC. & Drawing of Analyzer for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1317 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04994 | HRSG(V) - CFD Report for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-31 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1318 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04998 | HRSG(V) - I/O List for SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1319 | LATER | MHDB | SAU4005-G011-HHA-&MFQ-05000 | HRSG(V) - Alarm and Trip Setting List for Duct Burner | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1320 | LATER | MHDB | SAU4005-G011-HHA-&MMB-05001 | HRSG(V) - Cable Interconnection Diagram for Duct Burner | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-07-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1321 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05002 | HRSG(V) - Cable List for Duct Burner | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-07-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1322 | LATER | MHDB | SAU4005-G011-HHA-&MTA-05003 | HRSG(V) - Cable Tray & Conduit Drawing for Duct Burner | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-07-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1323 | LATER | MHDB | SAU4005-G011-HHA-&MMB-05004 | HRSG(V) - Control Logic & Loop for Duct Burner | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-07-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1324 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05005 | HRSG(V) - Control Valve Data Sheet & Drawings for Duct Burner | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-07-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1325 | LATER | MHDB | SAU4005-G011-HHA-&MFB-05006 | HRSG(V) - P&ID for Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFC |  |  | 2025-09-30 |  |  |  | 2025-10-20 |  |  |  | 2025-11-09 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1326 | LATER | MHDB | SAU4005-G011-HHA-&MDB-05007 | HRSG(V) - System Description for Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-07-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1327 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05008 | HRSG(V) - General Arrangement for Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFC |  |  | 2025-07-30 |  |  |  | 2025-08-19 |  |  |  | 2025-09-08 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1328 | LATER | MHDB | SAU4005-G011-HHA-&MLB-05009 | HRSG(V) - Foundation Drawing for Duct Burner | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-06-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1329 | LATER | MHDB | SAU4005-G011-HHA-&MLU-05010 | HRSG(V) - Fuel Gas Skid Arrangement Drawing for Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFC |  |  | 2025-07-30 |  |  |  | 2025-08-19 |  |  |  | 2025-09-08 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1330 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05012 | HRSG(V) - Cooling Air Fan Data Sheet for Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-31 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1331 | LATER | MHDB | SAU4005-G011-HHA-&MLD-05013 | HRSG(V) - Instrument Hook-up for Duct Burner | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-07-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1332 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05014 | HRSG(V) - Instrument Data Sheet for Duct Burner | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-07-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1333 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05015 | HRSG(V) - Instrument List for Duct Burner | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-07-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1334 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05016 | HRSG(V) - Piping Isometric Drawing for Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-07-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1335 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05017 | HRSG(V) - Piping Layout Drawing for Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-07-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1336 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05018 | HRSG(V) - Piping Support Drawing for Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-07-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1337 | LATER | MHDB | SAU4005-G011-HHA-&MLU-05020 | HRSG(V) - Junction Box Drawing for Duct Burner | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-07-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1338 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05021 | HRSG(V) - Local Panel / Control Panel Drawing for Duct Burner | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-07-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1339 | LATER | MHDB | SAU4005-G011-HHA-&MDB-05022 | HRSG(V) - Technical Specification for Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-07-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1340 | LATER | MHDB | SAU4005-G011-HHA-&MFF-05023 | HRSG(V) - BMS Control Logic Diagram & Flow Chart | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-07-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1341 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05024 | HRSG(V) - BMS Cause and Effect Chart | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-07-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1342 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05025 | HRSG(V) - BMS Control Narrative | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-07-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1343 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05026 | HRSG(V) - BMS Communication List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-07-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1344 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05027 | HRSG(V) - BMS HMI Graphic | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-07-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1345 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05028 | HRSG(V) - BMS TMR Configuration | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-07-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1346 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05029 | HRSG(V) - I/O List for DUCT BURNER | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-07-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1347 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05030 | HRSG(V) - Valve List for Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-07-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1348 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05031 | HRSG(V) - Valve Drawing for Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-07-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1349 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05032 | HRSG(V) - SPEC. & Drawing of Flame Scanner for Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-07-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1350 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05033 | HRSG(V) - SPEC. & Drawing of Ignition Burner for Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-07-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1351 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05034 | HRSG(V) - Hazardous Area Classification Specification & Drawing for Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-07-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1352 | LATER | MHDB | SAU4005-G011-QLA-&MDA-05054 | HRSG(V) - Water Quality Standard | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-04-29 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1353 | LATER | MHDB | SAU4005-G011-HNY-&MDA-05058 | HRSG(V) - Material Safety Data Sheet for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1354 | LATER | MHDB | SAU4005-G011-H__-&MDA-05061 | HRSG(V) - Stack size calculation | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1355 | LATER | MHDB | SAU4005-G011-H__-&MED-05063 | HRSG(V) - Blowdown tank size calculation sheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1356 | LATER | MHDB | SAU4005-G011-CJA-&MFB-05067 | HRSG(V) - Operation Flow Chart | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-12-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1357 | LATER | MHDB | SAU4005-G011-___-&BAB-05068 | HRSG(V) - Equipment List | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-06-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1358 | LATER | MHDB | SAU4005-G011-HAA-&MTC-05071 | HRSG(V) - Internal Tray Enclosure Detail for Deaerator | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1359 | LATER | MHDB | SAU4005-G011-HAA-&MTC-05072 | HRSG(V) - Internal Spray Header Detail for Deaerator | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1360 | LATER | MHDB | SAU4005-G011-HAA-&MTC-05073 | HRSG(V) - Name Plate Detail for Deaerator | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1361 | LATER | MHDB | SAU4005-G011-HAA-&MED-05074 | HRSG(V) - Strength Calculation for Deaerator | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1362 | LATER | MHDB | SAU4005-G011-UHB-&MDD-05076 | HRSG(V) - Field Bolt and Weld List | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-12-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1363 | LATER | MHDB | SAU4005-G011-UHB-&MTL-05077 | HRSG(V) - Stair Arrangement for HRSG Steel Structure | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1364 | LATER | MHDB | SAU4005-G011-UHB-&MTL-05078 | HRSG(V) - Plan View at T.O.P for HRSG Steel Structure | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-10-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1365 | LATER | MHDB | SAU4005-G011-UHB-&MTL-05079 | HRSG(V) - Plan View at T.O.P & BD Tank & Drum Support Detail for HRSG Steel Structure | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-10-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1366 | LATER | MHDB | SAU4005-G011-UHB-&MTL-05080 | HRSG(V) - Section Detail for HRSG Steel Structure | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1367 | LATER | MHDB | SAU4005-G011-UHB-&MTL-05081 | HRSG(V) - Girth Line & Roof Purlin Plan for HRSG Steel Structure | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1368 | LATER | MHDB | SAU4005-G011-UHB-&MTL-05082 | HRSG(V) - Section & Detail for HRSG Steel Structure | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1369 | LATER | MHDB | SAU4005-G011-HBB-&MTL-05083 | HRSG(V) - Wall Panel Elevations for HRSG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1370 | LATER | MHDB | SAU4005-G011-UHB-&MTL-05084 | HRSG(V) - Trolley Detail for Harp | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1371 | LATER | MHDB | SAU4005-G011-UHB-&MTL-05085 | HRSG(V) - Arrangement of Casing Flow Baffle | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-11-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1372 | LATER | MHDB | SAU4005-G011-LAE-&MDA-05088 | HRSG(V) - Attemperator Data Sheet and Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1373 | LATER | MHDB | SAU4005-G011-SND-&MDA-05089 | HRSG(V) - Elevator Data Sheet and Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-10-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1374 | LATER | MHDB | SAU4005-G011-QMA-&MDA-05090 | HRSG(V) - Dehumidifier Data Sheet and Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-10-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1375 | LATER | MHDB | SAU4005-G011-HNY-&MLU-05091 | HRSG(V) - Ammonia Storage Tank Capacity Calculation for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-07-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1376 | LATER | MHDB | SAU4005-G011-HNY-&MLU-05092 | HRSG(V) - AIG, Catalyst Frame & Sealing Arrangement Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-31 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1377 | LATER | MHDB | SAU4005-G011-HNY-&MDA-05093 | HRSG(V) - SCR Performance Summary | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-31 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1378 | LATER | MHDB | SAU4005-G011-HNY-&MDA-05094 | HRSG(V) - System Configuration for SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1379 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05095 | HRSG(V) - Duct Burner System Configuration | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1380 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05096 | HRSG(V) - BMS IO List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-05-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1381 | LATER | MHDB | SAU4005-G011-HNY-&MDA-05097 | HRSG(V) - Ammonia Pump Sizing Calculation for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1382 | LATER | MHDB | SAU4005-G011-HA_-&MPA-05098 | HRSG(V) - Strainer List & Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1383 | LATER | MHDB | SAU4005-G011-HAA-&MDD-05099 | HRSG(V) - HP Steam Drum Insulation Details | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1384 | LATER | MHDB | SAU4005-G011-UHB-&MPD-05100 | HRSG(V) - Field Welding List for EXP Piping(LB) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-12-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1385 | LATER | MHDB | SAU4005-G011-UHB-&MTL-05101 | HRSG(V) - Outside Insulation & Lagging for HRSG Main Stack | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-12-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1386 | LATER | MHDB | SAU4005-G011-HNY-&MDA-05102 | HRSG(V) - Lighting System for SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1387 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05103 | HRSG(V) - BMS Control Panel Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1388 | LATER | MHDB | SAU4005-G011-UHB-&MED-05104 | HRSG(V) - Strength Calculation for Lifting Device | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-10-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1389 | LATER | MHDB | SAU4005-G011-HYA-&EFB-05105 | HRSG(V) - Cable Block Diagram for HRSG | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-09-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1390 | LATER | MHDB | SAU4005-G011-HNE-&EPC-05106 | HRSG(V) - CEMS Electrical Load List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1391 | LATER | MHDB | SAU4005-G011-HNE-&EFB-05107 | HRSG(V) - CEMS P&ID | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFC |  |  | 2025-09-30 |  |  |  | 2025-10-20 |  |  |  | 2025-11-09 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1392 | LATER | MHDB | SAU4005-G011-HNE-&EFA-05108 | HRSG(V) - CEMS Network Architecture | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1393 | LATER | MHDB | SAU4005-G011-HNE-&EDB-05109 | HRSG(V) - CEMS System structure Diagram | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1394 | LATER | MHDB | SAU4005-G011-HNE-&ETB-05110 | HRSG(V) - CEMS Flange Installation Diagram | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1395 | LATER | MHDB | SAU4005-G011-HNE-&ELU-05111 | HRSG(V) - General Arrangement Drawing for Analyzer Cabinet. | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFC |  |  | 2025-09-30 |  |  |  | 2025-10-20 |  |  |  | 2025-11-09 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1396 | LATER | MHDB | SAU4005-G011-HNE-&EPA-05112 | HRSG(V) - CEMS Cable list | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1397 | LATER | MHDB | SAU4005-G011-HNE-&EFP-05115 | HRSG(V) - CEMS I/O Signals exchange List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1398 | LATER | MHDB | SAU4005-G011-HNE-&EFB-05117 | HRSG(V) - CEMS Single Line Diagram for Power Distribution | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1399 | LATER | MHDB | SAU4005-G011-UHB-&MTL-05121 | HRSG(V) - Platform Detail for HRSG Main Stack | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-08-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1400 | LATER | MHDB | SAU4005-G011-UHB-&MTL-05122 | HRSG(V) - Embedded Material Calculation for HRSG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFC | [14 empty] | 2025-05-08 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1401 | LATER | MHDB | SAU4005-G011-HB_-&MEC-05070 | HRSG(V) - STEEL STRUCTURE MATERIAL SPECIFICATION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-07-03 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1402 | LATER | MPW | SAU4005-G000-___-&BBD-03041 | GT(V) - PLANT IDENTIFICATION NUMBERING SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1403 | LATER | MPW | SAU4005-G000-___-&MEC-03040 | GT(V) - PAINTING SPECIFICATION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1404 | LATER | MPW | SAU4005-G011-MBN-&MTA-03045 | GT(V) - OUTLINE OF GT FUEL OIL & FLOW DIVIDER UNIT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1405 | LATER | MPW | SAU4005-G011-MBP-&MTA-03044 | GT(V) - OUTLINE OF FUEL GAS UNIT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1406 | LATER | MPW | SAU4005-G011-MBL-&MTL-03046 | GT(V) - GENERAL ARRANGEMENT OF GT AIR INTAKE SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1407 | LATER | MPW | SAU4005-G011-MBR-&MTL-03047 | GT(V) - GENERAL ARRANGEMENT OF GT EXHAUST SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1408 | LATER | MPW | SAU4005-G000-___-&MPD-03043 | GT(V) - EQUIPMENT LIST | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1409 | LATER | MPW | SAU4005-G000-___-&BBD-03042 | GT(V) - LIST OF APPLICABLE UNIT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1410 | LATER | MPW | SAU4005-G000-___-&MFB-03039 | GT(V) - P&I DIAGRAM LEGEND | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1411 | LATER | MPW | SAU4005-G011-MBV-&MFB-03000 | GT(V) - LUBE OIL SYSTEM P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-28 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1412 | LATER | MPW | SAU4005-G011-MBN-&MFB-03004 | GT(V) - FUEL OIL SYSTEM P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-28 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1413 | LATER | MPW | SAU4005-G011-MBP-&MFB-03009 | GT(V) - FUEL GAS SYSTEM P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-28 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1414 | LATER | MPW | SAU4005-G011-MBP-&MFB-03016 | GT(V) - FUEL GAS SYSTEM(FUEL GAS FLOW METER) P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1415 | LATER | MPW | SAU4005-G011-MBP-&MFB-03017 | GT(V) - FUEL GAS SYSTEM(FUEL GAS LAST CHANCE FILTER) P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1416 | LATER | MPW | SAU4005-G000-MBP-&MFB-03037 | GT(V) - FUEL GAS SYSTEM(FUEL GAS CALORIE METER) P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1417 | LATER | MPW | SAU4005-G011-MBH-&MFB-03018 | GT(V) - AIR AND FLUE GAS SYSTEM P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-28 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1418 | LATER | MPW | SAU4005-G011-SDD-&MFB-03024 | GT(V) - GT WASHING & DRAIN SYSTEM P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-28 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1419 | LATER | MPW | SAU4005-G011-MBA-&MFB-03026 | GT(V) - PROTECTION SYSTEM P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1420 | LATER | MPW | SAU4005-G011-QFF-&MFB-03029 | GT(V) - GT CASING COOLING AIR SYSTEM P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1421 | LATER | MPW | SAU4005-G011-QFF-&MFB-03027 | GT(V) - GT INSTRUMENT AIR SYSTEM P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-28 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1422 | LATER | MPW | SAU4005-G011-SDD-&MFB-03038 | GT(V) - GT INLET AIR COOLING(HIGH FOGGING)SYSTEM P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1423 | LATER | MPW | SAU4005-G011-QEE-&MFB-03030 | GT(V) - GT PURGE AIR SYSTEM P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1424 | LATER | MPW | SAU4005-G011-MBU-&MFB-03031 | GT(V) - GT WATER INJECTION SYSTEM P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-28 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1425 | LATER | MPW | SAU4005-G011-PGG-&MFB-03033 | GT(V) - COOLING WATER SYSTEM FOR GT P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1426 | LATER | MPW | SAU4005-G011-LAB-&MFB-03034 | GT(V) - GT FUEL GAS HEATER & GT COOLING AIR COOLER SYSTEM P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1427 | LATER | MPW | SAU4005-G011-MBH-&MFB-03035 | GT(V) - ENHANCED COOLING AIR SYSTEM P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-28 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1428 | LATER | MPW | SAU4005-G011-MB_-&MTA-03053 | GT(V) - PIPING TERMINAL POINTS FOR GAS TURBINE PACKAGE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1429 | LATER | MPW | SAU4005-G000-CJP-&EFB-03058 | GT(V) - TYPICAL LOGIC DIAGRAM FOR AUXILIARIES (GT PORTION) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1430 | LATER | MPW | SAU4005-G000-CAA-&EFE-03059 | GT(V) - GENERAL DESCRIPTION OF GT UNIT INTERLOCK | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1431 | LATER | MPW | SAU4005-G000-CAA-&EFB-03061 | GT(V) - GAS TURBINE UNIT INTERLOCK DIAGRAM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1432 | LATER | MPW | SAU4005-G000-CJP-&EFB-03062 | GT(V) - GAS TURBINE GOVERNOR CONTROL DIAGRAM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1433 | LATER | MPW | SAU4005-G000-___-&MTL-03067 | GT(V) - OVERHAUL PARTS DRAWING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1434 | LATER | MPW | SAU4005-G000-___-&BBD-03051 | GT(V) - UTILITY LIST | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1435 | LATER | MPW | SAU4005-G011-BFJ-&EFS-03050 | GT(V) - KEY SINGLE LINE DIAGRAM FOR GT AUXILIARIES | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1436 | LATER | MPW | SAU4005-G011-BFJ-&EFF-03101 | GT(V) - TYPICAL SCHEMATIC DIAGRAM FOR ELECTRICAL PANEL | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1437 | LATER | MPW | SAU4005-G011-BFJ-&EFB-03102 | GT(V) - LOGIC DIAGRAM FOR ELECTRICAL CONTROL SYSTEM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1438 | LATER | MPW | SAU4005-G000-MB_-&MDA-03103 | GT(V) - DESIGN NOTE FOR GT FOUNDATION | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1439 | LATER | MPW | SAU4005-G000-CJP-&EFE-03060 | GT(V) - DESCRIPTION OF GAS TURBINE CONTROL | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-04-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1440 | LATER | MPW | SAU4005-G011-MB_-&MTA-03065 | GT(V) - ROUTE PLAN OF PIPING AROUND FUEL OIL & FLOW DIVIDER UNIT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-05-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1441 | LATER | MPW | SAU4005-G011-MB_-&MTA-03064 | GT(V) - ARRANGEMENT OF PLATFORM AROUND GAS TURBINE & GENERATOR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-05-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1442 | LATER | MPW | SAU4005-G011-MB_-&MTA-03055 | GT(V) - ARRANGEMENT OF PLATFORM AROUND GT LUBE OIL RESERVOIR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-05-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1443 | LATER | MPW | SAU4005-G011-SGJ-&MTA-03138 | GT(V) - BASIC DESIGN OF FIRE PROTECTION SYSTEM IN GAS TURBINE PACKAGE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1444 | LATER | MPW | SAU4005-G011-MB_-&MTA-03066 | GT(V) - ARRANGEMENT OF GAS TURBINE, GENERATOR & AUXILIARY EQUIPMENT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-05-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1445 | LATER | MPW | SAU4005-G011-MB_-&MTA-03189 | GT(V) - TURBINE & GENERATOR FOUNDATION DRAWINGS | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-05-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1446 | LATER | MPW | SAU4005-G011-MB_-&MTA-03104 | GT(V) - AUXILIARY EQUIPMENT FOUNDATION DRAWINGS | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-05-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1447 | LATER | MPW | SAU4005-G011-MB_-&MTA-03105 | GT(V) - AROUND GT UNIT FOUNDATION DRAWINGS | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-05-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1448 | LATER | MPW | SAU4005-G000-___-&MMA-03205 | GT(V) - CONTRACT INTERFACE LIST | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1449 | LATER | MPW | SAU4005-G000-___-&MEC-03206 | GT(V) - WASTE WATER LIST | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1450 | LATER | MPW | SAU4005-G000-___-&EEC-03214 | GT(V) - HEAT LOAD LIST | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1451 | LATER | MPW | SAU4005-G011-___-&BDB-03135 | GT(V) - HAZARDOUS AREA CLASSIFICATION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1452 | LATER | MPW | SAU4005-G011-LAB-&MDB-03056 | GT(V) - DESIGN PHILOSOPHY FOR TCA COOLER FEEDWATER SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-16 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1453 | LATER | MPW | SAU4005-G011-LAB-&MDB-03057 | GT(V) - DESIGN PHILOSOPHY FOR FGH FEED WATER SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1454 | LATER | MPW | SAU4005-G000-CRV-&EDB-03258 | GT(V) - CONTROL SYSTEM CONFIGURATION | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-05-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1455 | LATER | MPW | SAU4005-G000-CJP-&EFA-03274 | GT(V) - HARDWARE SPECIFICATION OF CONTROL SYSTEM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1456 | LATER | MPW | SAU4005-G011-BJF-&EPC-03052 | GT(V) - ELECTRICAL LOAD LIST | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1457 | LATER | MPW | SAU4005-G011-BFJ-&EFS-03199 | GT(V) - SINGLE LINE DIAGRAM FOR MOTOR CONTROL CENTER | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-05-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1458 | LATER | MPW | SAU4005-G011-BTA-&EFS-03191 | GT(V) - SINGLE LINE DIAGRAM FOR DC SYSTEM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-05-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1459 | LATER | MPW | SAU4005-G011-BJA-&EFS-03196 | GT(V) - SINGLE LINE DIAGRAM FOR AC DISTRIBUTION PANEL | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-05-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1460 | LATER | MPW | SAU4005-G011-MB_-&MTA-03179 | GT(V) - OUTLINE OF GT TURNING DEVICE ENCLOSURE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-05-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1461 | LATER | MPW | SAU4005-G000-CJP-&EED-03276 | GT(V) - OUTLINE OF GT CONTROL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-05-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1462 | LATER | MPW | SAU4005-G000-CAA-&EED-03296 | GT(V) - OUTLINE OF SAFETY PLC PANEL | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-05-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1463 | LATER | MPW | SAU4005-G000-CWQ-&EED-03255 | GT(V) - OUTLINE OF CPFA SERVER CABINET | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-05-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1464 | LATER | MPW | SAU4005-G011-MBP-&MDA-03110 | GT(V) - GT FUEL GAS HEATER SECTIONAL ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-05-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1465 | LATER | MPW | SAU4005-G011-MBH-&MDA-03119 | GT(V) - GT COOLING AIR COOLER SECTIONAL ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-05-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1466 | LATER | MPW | SAU4005-G011-MBR-&MTA-03154 | GT(V) - TERMINAL FLANGE OF GT EXHAUST DUCT & HRSG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-05-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1467 | LATER | MPW | SAU4005-G000-CAA-&EFA-03295 | GT(V) - SPECIFICATION OF SAFETY PLC | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-05 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1468 | LATER | MPW | SAU4005-G000-CMB-&EFA-03260 | GT(V) - SPECIFICATION OF COMMUNICATION CABLE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-05 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1469 | LATER | MPW | SAU4005-G000-CMB-&EFA-03261 | GT(V) - SPECIFICATION OF OPC COMMUNICATION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-05 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1470 | LATER | MPW | SAU4005-G000-CJP-&EFA-03275 | GT(V) - SPECIFICATION OF A-CPFM/CPFM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-05 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1471 | LATER | MPW | SAU4005-G000-___-&BDD-03247 | GT(V) - HAZOP STUDY REPORT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFA | IFD |  |  | 2025-06-11 |  |  |  | 2025-07-01 |  |  |  | 2025-08-06 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
1472 | LATER | MPW | SAU4005-G000-___-&BDD-03248 | GT(V) - SIL STUDY REPORT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFA | IFD |  |  | 2025-06-11 |  |  |  | 2025-07-01 |  |  |  | 2025-08-06 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
1473 | LATER | MPW | SAU4005-G000-___-&EEC-03213 | GT(V) - MOTOR LIST | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-11 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1474 | LATER | MPW | SAU4005-G000-MBA-&CTB-03303 | GT(V) - ARRANGEMENT OF TEMPLATE DWG FOR GT POWER TRAIN | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-06-18 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1475 | LATER | MPW | SAU4005-G011-___-&MDA-03122 | GT(V) - PNEUMATIC CONTROL VALVE DWG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-06-18 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1476 | LATER | MPW | SAU4005-G011-MBP-&MDA-03157 | GT(V) - ELECTRIC CONTROL VALVE DWG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-06-18 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1477 | LATER | MPW | SAU4005-G011-MBN-&MDA-03161 | GT(V) - GT FLOW DIVIDER DWG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-06-18 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1478 | LATER | MPW | SAU4005-G011-MBN-&MDA-03162 | GT(V) - MAIN FUEL OIL PUMP DWG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-06-18 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1479 | LATER | MPW | SAU4005-G011-MBU-&MDA-03152 | GT(V) - WATER INJECTION PUMP DWG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-06-18 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1480 | LATER | MPW | SAU4005-G011-QEE-&MDA-03141 | GT(V) - PURGE AIR COMPRESSOR(MECHANICAL) DWG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-06-18 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1481 | LATER | MPW | SAU4005-G011-QEE-&MDA-03142 | GT(V) - PURGE AIR RECEIVER DWG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-06-18 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1482 | LATER | MPW | SAU4005-G011-MBH-&MDA-03174 | GT(V) - GT ENHANCED COOLING AIR COMPRESSOR(MECHANICAL) DWG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-06-18 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1483 | LATER | MPW | SAU4005-G011-MBP-&MDA-03158 | GT(V) - GT FUEL GAS LAST CHNACE FILTER DWG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-06-18 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1484 | LATER | MPW | SAU4005-G011-___-&MPC-03107 | GT(V) - VALVE LIST FOR HEAT EXCHANGER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-18 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1485 | LATER | MPW | SAU4005-G000-___-&MEC-03207 | GT(V) - Thermal Insulation Specification | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-18 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1486 | LATER | MPW | SAU4005-G011-BFJ-&EED-03200 | GT(V) - STUDY OF ELECTRICAL CONSUMPTION AND BUS CAPACITY FOR MCC | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1487 | LATER | MPW | SAU4005-G011-BTA-&EED-03192 | GT(V) - STUDY OF DC SYSTEM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1488 | LATER | MPW | SAU4005-G011-MBR-&MTA-03153 | GT(V) - LOADING DATA OF GT EXHAUST SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1489 | LATER | MPW | SAU4005-G011-MBR-&MTA-03155 | GT(V) - FOUNDATION OUTLINE OF GT EXHAUST DUCT | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-06-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1490 | LATER | MPW | SAU4005-G011-MBR-&MTA-03156 | GT(V) - ARRANGEMENT OF EARTH TERMINAL AROUND GT EXHAUST SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-06-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1491 | LATER | MPW | SAU4005-G011-MBL-&MTA-03165 | GT(V) - LOADING DATA OF GT AIR INTAKE SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-02 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1492 | LATER | MPW | SAU4005-G011-MBL-&MTA-03168 | GT(V) - FOUNDATION OUTLINE OF GT AIR INTAKE SYSTEM | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-07-02 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1493 | LATER | MPW | SAU4005-G000-CMB-&EFA-03262 | GT(V) - SPECIFICATION OF SECURITY CONTROL SYSTEM(NPP) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-02 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1494 | LATER | MPW | SAU4005-G011-MB_-&MTA-03180 | GT(V) - ROUTE PLAN OF PIPING AROUND GT UNIT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-07-09 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1495 | LATER | MPW | SAU4005-G011-MB_-&MTA-03183 | GT(V) - ROUTE PLAN OF GAS TURBINE COOLING AIR PIPING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-07-09 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1496 | LATER | MPW | SAU4005-G011-MB_-&MTA-03184 | GT(V) - ROUTE PLAN OF PRESSURE PIPING FOR EXHAUST DUCT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-07-09 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1497 | LATER | MPW | SAU4005-G011-MB_-&MTA-03185 | GT(V) - ROUTE PLAN OF EXHAUST DUCT DRAIN PIPING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-07-09 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1498 | LATER | MPW | SAU4005-G011-MB_-&MTA-03186 | GT(V) - ROUTE PLAN OF GT CASING COOLING AIR PIPING (LOCAL) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-07-09 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1499 | LATER | MPW | SAU4005-G011-MB_-&MTA-03187 | GT(V) - ROUTE PLAN OF 4S COOLING AIR PIPING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-07-09 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1500 | LATER | MPW | SAU4005-G011-___-&MDB-03121 | GT(V) - SYSTEM DESCRIPTION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-09 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1501 | LATER | MPW | SAU4005-G011-QFF-&MDB-03140 | GT(V) - DESIGN PHILOSOPHY FOR EMERGENCY AIR SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-09 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1502 | LATER | MPW | SAU4005-G000-CFA-&EEC-03279 | GT(V) - SPECIFICATION OF SPEED PICK UP | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-09 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1503 | LATER | MPW | SAU4005-G000-CFA-&EEC-03280 | GT(V) - SPECIFICATION OF PRESSURE TRANSMITTER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-09 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1504 | LATER | MPW | SAU4005-G000-CFA-&EEC-03283 | GT(V) - SPECIFICATION OF FUEL GAS FLOW METER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-09 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1505 | LATER | MPW | SAU4005-G000-CFA-&EEC-03287 | GT(V) - SPECIFICATION OF PRESSURE GAUGE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-09 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1506 | LATER | MPW | SAU4005-G000-CFA-&EEC-03289 | GT(V) - SPECIFICATION OF SOLENOID VALVE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-09 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1507 | LATER | MPW | SAU4005-G000-CJP-&EFB-03273 | GT(V) - GAS TURBINE GENERAL LOGIC DIAGRAM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-07-16 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1508 | LATER | MPW | SAU4005-G011-MBV-&MDA-03112 | GT(V) - GT LUBE OIL COOLER SECTIONAL ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-07-16 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1509 | LATER | MPW | SAU4005-G011-BJA-&EDB-03198 | GT(V) - SPECIFICATION OF AC/DC DISTRIBUTION PANEL | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1510 | LATER | MPW | SAU4005-G000-___-&CTC-03216 | GT(V) - OUTLINE OF TERMINAL BOX (FUEL UNIT) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-07-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1511 | LATER | MPW | SAU4005-G011-QEE-&EDA-03143 | GT(V) - PURGE AIR COMPRESSOR(ELECTRICAL) DWG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-07-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1512 | LATER | MPW | SAU4005-G011-MBH-&EDA-03175 | GT(V) - GT ENHANCED COOLING AIR COMPRESSOR(ELECTRICAL) DWG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-07-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1513 | LATER | MPW | SAU4005-G011-SDD-&MDA-03139 | GT(V) - COMPRESSOR WASHING DEVICE DWG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-07-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1514 | LATER | MPW | SAU4005-G000-CAA-&EFS-03294 | GT(V) - SCHEMATIC DIAGRAM OF SAFETY PLC PANEL | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-07-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1515 | LATER | MPW | SAU4005-G000-CMB-&EED-03263 | GT(V) - OUTLINE OF NPP PANEL | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-07-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1516 | LATER | MPW | SAU4005-G000-CFA-&EEC-03278 | GT(V) - SPECIFICATION OF VIBRATION MONITORING INSTRUMENT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1517 | LATER | MPW | SAU4005-G000-CFA-&EEC-03281 | GT(V) - SPECIFICATION OF LEVEL TRANSMITTER | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1518 | LATER | MPW | SAU4005-G000-CFA-&EEC-03282 | GT(V) - SPECIFICATION OF FUEL OIL FLOW METER | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1519 | LATER | MPW | SAU4005-G000-CFA-&EEC-03284 | GT(V) - SPECIFICATION OF TEMPERATURE MEASURING INSTRUMENT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1520 | LATER | MPW | SAU4005-G000-CFA-&EEC-03285 | GT(V) - SPECIFICATION OF FLOW ELEMENT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1521 | LATER | MPW | SAU4005-G000-CFA-&EEC-03290 | GT(V) - SPECIFICATION OF AMBIENT TEMPERATURE & HUMIDITY MEASURING INSTRUMENT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1522 | LATER | MPW | SAU4005-G000-CFA-&EEC-03291 | GT(V) - SPECIFICATION OF GAS DETECTOR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1523 | LATER | MPW | SAU4005-G000-CFA-&EEC-03292 | GT(V) - SPECIFICATION OF CPFM SENSOR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1524 | LATER | MPW | SAU4005-G000-CFA-&EEC-03293 | GT(V) - SPECIFICATION OF CALORIE METER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1525 | LATER | MPW | SAU4005-G011-MBH-&MDA-03108 | GT(V) - TURBINE COOLING AIR COOLER WITH FUEL GAS HEATER(Air Cooled Type) SECTIONAL ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-07-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1526 | LATER | MPW | SAU4005-G011-MBH-&MDA-03109 | GT(V) - ENHANCED COOLING AIR COOLER SECTIONAL ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-07-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1527 | LATER | MPW | SAU4005-G011-MBP-&MTA-03111 | GT(V) - INSTRUMENT PIPING FOR GT FUEL GAS HEATER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-07-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1528 | LATER | MPW | SAU4005-G011-MBV-&MDA-03113 | GT(V) - THREE WAY VALVE SECTIONAL ASSEMBLY (FOR GT LUBE OIL COOLER) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-07-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1529 | LATER | MPW | SAU4005-G011-MBV-&MTA-03114 | GT(V) - THREE WAY VALVE INSTALLATION DRAWING (FOR GT LUBE OIL COOLER) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-07-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1530 | LATER | MPW | SAU4005-G011-MBH-&MTA-03115 | GT(V) - INSTRUMENT PIPING FOR 2C COOLER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-07-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1531 | LATER | MPW | SAU4005-G011-MBH-&MDA-03116 | GT(V) - 2C COOLER SECTIONAL ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-07-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1532 | LATER | MPW | SAU4005-G011-MBH-&MDA-03117 | GT(V) - 4S COOLER SECTIONAL ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-07-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1533 | LATER | MPW | SAU4005-G011-QEE-&MDA-03118 | GT(V) - GT PURGE AIR COOLER SECTIONAL ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-07-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1534 | LATER | MPW | SAU4005-G011-MBH-&MTA-03120 | GT(V) - GT COOLING AIR COOLER INSTRUMENT PIPING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-07-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1535 | LATER | MPW | SAU4005-G011-SGJ-&MTA-03136 | GT(V) - CO2 FIRE FIGHTING SYSTEM (MECHANICAL) DRAWING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-08-13 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1536 | LATER | MPW | SAU4005-G011-SGJ-&MTA-03137 | GT(V) - CO2 FIRE FIGHTING SYSTEM (ELECTRICAL) DRAWING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-08-13 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1537 | LATER | MPW | SAU4005-G000-CJP-&EFP-03270 | GT(V) - DCS-GTC INTERFACE LIST(HARD-WIRED) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-08-13 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
1538 | LATER | MPW | SAU4005-G000-CFA-&EPB-03299 | GT(V) - INSTRUMENT LIST | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-08-13 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1539 | LATER | MPW | SAU4005-G011-MBA-&MLU-03177 | GT(V) - OUTLINE DRAWING OF LOW VOLTAGE MOTOR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-08-13 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1540 | LATER | MPW | SAU4005-G011-MBV-&MLU-03150 | GT(V) - OUTLINE DRAWING OF DC MOTOR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-08-13 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1541 | LATER | MPW | SAU4005-G011-BFJ-&EDB-03202 | GT(V) - SPECIFICATION OF MOTOR CONTROL CENTER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-08-13 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1542 | LATER | MPW | SAU4005-G011-BTA-&EDB-03194 | GT(V) - SPECIFICATION OF DC SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-08-13 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1543 | LATER | MPW | SAU4005-G011-MBL-&MTA-03166 | GT(V) - OUTLINE DRAWING OF GT AIR INTAKE FILTER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-08-29 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1544 | LATER | MPW | SAU4005-G011-MBL-&MTA-03170 | GT(V) - ARRANGEMENT OF EARTH TERMINAL AROUND GT AIR INTAKE SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-08-29 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1545 | LATER | MPW | SAU4005-G011-MBL-&MTA-03171 | GT(V) - OUTLINE DRAWING OF FOGGING SYSTEM PUMP SKID | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-08-29 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1546 | LATER | MPW | SAU4005-G011-MBL-&MTA-03172 | GT(V) - ROUTE PLAN OF FOGGING SYSTEM PIPING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-08-29 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1547 | LATER | MPW | SAU4005-G000-___-&CTA-03219 | GT(V) - OUTLINE OF INSTRUMENT MOUNTING SUPPORT (FUEL UNIT) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-08-29 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1548 | LATER | MPW | SAU4005-G000-___-&CMB-03236 | GT(V) - WIRING DIAGRAM OF TERMINAL BOX (FUEL UNIT) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-08-29 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1549 | LATER | MPW | SAU4005-G000-___-&CPA-03234 | GT(V) - CABLE LIST (FUEL UNIT) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-08-29 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1550 | LATER | MPW | SAU4005-G011-MBV-&MTA-03149 | GT(V) - OUTLINE OF LUBE OIL RESERVOIR UNIT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-08-29 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1551 | LATER | MPW | SAU4005-G011-MB_-&MTA-03181 | GT(V) - VALVE LIST FOR GAS TURBINE PART | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-08-29 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1552 | LATER | MPW | SAU4005-G000-___-&CEC-03238 | GT(V) - SPECIFICATION OF INSTRUMENT CABLE | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-09-03 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1553 | LATER | MPW | SAU4005-G000-___-&CTA-03222 | GT(V) - ARRANGEMENT OF CONDUIT PIPING FOR FUEL UNIT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-09-03 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1554 | LATER | MPW | SAU4005-G000-___-&CTA-03223 | GT(V) - ARRANGEMENT OF CONDUIT PIPING FOR LIGHTING & FIRE FIGHTING SYSTEM (FUEL UNIT) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-09-03 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1555 | LATER | MPW | SAU4005-G000-CJP-&EFS-03269 | GT(V) - SCHEMATIC DIAGRAM OF GT CONTROL SYSTEM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-09-03 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1556 | LATER | MPW | SAU4005-G000-CMB-&EFS-03259 | GT(V) - SCHEMATIC DIAGRAM OF NPP | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-09-03 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1557 | LATER | MPW | SAU4005-G000-MBA-&MDB-03297 | GT(V) - GAS TURBINE LONGITUDINAL SECT ASS'Y | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-09-03 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1558 | LATER | MPW | SAU4005-G000-CJP-&EEC-03277 | GT(V) - SPECIFICATION OF GT OPS SCREENS | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-09-03 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1559 | LATER | MPW | SAU4005-G011-MBL-&MTA-03163 | GT(V) - GT CASING COOLING FAN DWG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-09-03 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1560 | LATER | MPW | SAU4005-G011-MBL-&MTA-03167 | GT(V) - TECHNICAL SPECIFICATION OF GT AIR INTAKE FILTER SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-09-03 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
1561 | LATER | MPW | SAU4005-G011-BLA-&ELU-03195 | GT(V) - OUTLINE DRAWING OF WALL MOUNT RECEPTACLE FOR GT BOLT HEATER RECEPTACLE BOX | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-09-17 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1562 | LATER | MPW | SAU4005-G011-MBN-&MTA-03159 | GT(V) - FUEL OIL DRAIN PUMP & TANK UNIT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-09-24 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1563 | LATER | MPW | SAU4005-G000-___-&CTA-03220 | GT(V) - IMPULSE PIPING DRAWING (FUEL UNIT) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1564 | LATER | MPW | SAU4005-G000-___-&CTA-03221 | GT(V) - SUPPLY & CONTROL AIR TUBING DRAWING (FUEL UNIT) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1565 | LATER | MPW | SAU4005-G000-___-&CTA-03224 | GT(V) - CONDUIT DIAGRAM (FUEL UNIT) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1566 | LATER | MPW | SAU4005-G000-___-&CEC-03239 | GT(V) - SPECIFICATION OF LIGHTING FIXTURES | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-09-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1567 | LATER | MPW | SAU4005-G000-___-&CMB-03237 | GT(V) - WIRING DIAGRAM OF TERMINAL BOX | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-10-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1568 | LATER | MPW | SAU4005-G000-___-&CPA-03235 | GT(V) - CABLE LIST | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-10-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1569 | LATER | MPW | SAU4005-G000-CWQ-&EFS-03253 | GT(V) - SCHEMATIC DIAGRAM OF CPFA SERVER CABINET | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-10-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1570 | LATER | MPW | SAU4005-G011-MBV-&MTA-03148 | GT(V) - GT LUBE OIL MIST SEPARATOR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-10-15 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1571 | LATER | MPW | SAU4005-G011-MBL-&ETA-03173 | GT(V) - LOCAL CONTROL PANEL, LOGIC & WIRING DIAGRAM OF GT AIR INTAKE FILTER | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-10-22 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1572 | LATER | MPW | SAU4005-G011-BVR-&EDB-03190 | GT(V) - SPECIFICATION OF DC STARTER PANEL | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-10-22 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1573 | LATER | MPW | SAU4005-G000-___-&CTC-03217 | GT(V) - OUTLINE OF TERMINAL BOX | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-10-29 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1574 | LATER | MPW | SAU4005-G000-CJP-&EFC-03272 | GT(V) - PLAN OF OPS SCREENS | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-10-29 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1575 | LATER | MPW | SAU4005-G011-MBV-&MTA-03144 | GT(V) - GT MAIN LUBE OIL PUMP | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-11-19 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1576 | LATER | MPW | SAU4005-G011-MBV-&MTA-03145 | GT(V) - GT EMERGENCY LUBE OIL PUMP | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-11-19 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1577 | LATER | MPW | SAU4005-G011-MBV-&MTA-03146 | GT(V) - GT LUBE OIL FILTER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-11-19 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1578 | LATER | MPW | SAU4005-G011-MBV-&MTA-03147 | GT(V) - GT LUBE OIL ACCUMULATOR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-11-19 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1579 | LATER | MPW | SAU4005-G011-MBL-&MTA-03164 | GT(V) - GAS TURBINE PACKAGE VENTILATION FAN | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-11-19 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1580 | LATER | MPW | SAU4005-G000-___-&CTC-03218 | GT(V) - OUTLINE OF INSTRUMENT PANEL | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-11-26 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1581 | LATER | MPW | SAU4005-G000-___-&CTA-03225 | GT(V) - OUTLINE OF INSTRUMENT MOUNTING SUPPORT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-11-26 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1582 | LATER | MPW | SAU4005-G000-___-&CTA-03226 | GT(V) - IMPULSE PIPING DRAWING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-11-26 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1583 | LATER | MPW | SAU4005-G000-___-&CTA-03227 | GT(V) - SUPPLY & CONTROL AIR TUBING DRAWING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-11-26 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1584 | LATER | MPW | SAU4005-G000-___-&CTA-03229 | GT(V) - ARRANGEMENT OF CONDUIT PIPING FOR LIGHTING & FIRE FIGHTING SYSTEM (GT PACKAGE INTERNAL) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-11-26 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1585 | LATER | MPW | SAU4005-G000-___-&CTL-03215 | GT(V) - LOCATION OF DETECTION POINT & INSTRUMENT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-11-26 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1586 | LATER | MPW | SAU4005-G000-___-&CEC-03240 | GT(V) - SPECIFICATION OF HEAT TRACE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-12-03 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1587 | LATER | MPW | SAU4005-G000-___-&CTA-03228 | GT(V) - ARRANGEMENT OF CONDUIT PIPING (GT PACKAGE INTERNAL) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-12-10 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1588 | LATER | MPW | SAU4005-G011-___-&BFQ-03129 | GT(V) - CONTROL SETTING FOR GT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-12-10 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1589 | LATER | MPW | SAU4005-G000-___-&CTA-03231 | GT(V) - ARRANGEMENT OF CONDUIT PIPING (AROUND LUBE OIL UNIT) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-12-17 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1590 | LATER | MPW | SAU4005-G000-___-&CTA-03232 | GT(V) - ARRANGEMENT OF CONDUIT PIPING (AROUND EXHAUST GAS DUCT) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-12-17 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1591 | LATER | MPW | SAU4005-G000-___-&CTA-03230 | GT(V) - CONDUIT DIAGRAM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFC | [14 empty] | 2026-01-12 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1592 | LATER | MPW | SAU4005-G011-MB_-&MTA-03182 | GT(V) - OUTLINE DRAWING OF VALVES FOR GAS TURBINE PART | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2026-01-12 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1593 | LATER | MPW | SAU4005-G000-CJP-&EFT-03266 | GT(V) - IDOL LOGIC DIAGRAM OF FUNCTION MODULE | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFC | [14 empty] | 2026-02-04 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1594 | LATER | MPW | SAU4005-G000-CJP-&EFT-03267 | GT(V) - CPFM LOGIC DIAGRAM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFC | [14 empty] | 2026-02-04 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1595 | LATER | MPW | SAU4005-G000-CJP-&EFT-03268 | GT(V) - CPFM GRAPHIC SCREEN | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFD | [14 empty] | 2026-02-04 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1596 | LATER | MPW | SAU4005-G011-MBA-&MTA-03176 | GT(V) - GAS TURBINE NAME PLATE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFA | IFC |  |  | 2026-02-11 |  |  |  | 2026-03-03 |  |  |  | 2026-04-08 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1597 | LATER | MPW | SAU4005-G000-CKN-&EFA-03264 | GT(V) - HARDWARE SPECIFICATION OF OPERATION AND MAINTENANCE TOOL | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1598 | LATER | MPW | SAU4005-G000-CKN-&EFA-03265 | GT(V) - SPECIFICATION OF OPERATION AND MAINTENANCE TOOL | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-14 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1599 | LATER | MPW | SAU4005-G011-MPA-&CLB-03506 | GT(V) - GENERATOR FOUNDATION EMBEDDED METALS LAYOUT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-04-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1600 | LATER | MPW | SAU4005-G000-MKA-&MDA-03511 | GT(V) - GENERATOR FOUNDATION BOLT ARRANGEMENT (FOR GAS TURBINE) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-04-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1601 | LATER | MPW | SAU4005-G000-MKA-&MDA-03509 | GT(V) - GENERATOR LOAD ON FOUNDATION (FOR GAS TURBINE) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-04-23 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1602 | LATER | MPW | SAU4005-G000-MK_-&BAB-03526 | GT(V) - PAINTING COLOR LIST FOR GTG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1603 | LATER | MPW | SAU4005-G000-MK_-&BAC-03527 | GT(V) - PAINTING PROCEDURE FOR GTG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1604 | LATER | MPW | SAU4005-G000-MK_-&EDA-03544 | GT(V) - GENERAL SPECIFICATION OF ELECTRICAL CONTROL PANELS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-05-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1605 | LATER | MPW | SAU4005-G000-MK_-&EFA-03528 | GT(V) - SINGLE LINE DIAGRAM GENERATOR CIRCUIT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-05-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1606 | LATER | MPW | SAU4005-G000-MKA-&EDA-03507 | GT(V) - GENERATOR TECHNICAL DATA SHEET | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-05-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1607 | LATER | MPW | SAU4005-G000-MKA-&MDA-03508 | GT(V) - GENERATOR OUTLINE | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-05-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1608 | LATER | MPW | SAU4005-G000-MKA-&MDA-03510 | GT(V) - GENERATOR TERMINAL AND C.T. ASSEMBLY | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-05-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1609 | LATER | MPW | SAU4005-G000-MKA-&MDA-03512 | GT(V) - GENERATOR FIELD LEADS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFC | [14 empty] | 2025-05-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1610 | LATER | MPW | SAU4005-G000-MKA-&MDA-03513 | GT(V) - GENERATOR GROUT RETAINER ARRANGEMENT | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1611 | LATER | MPW | SAU4005-G000-MKA-&MDA-03517 | GT(V) - GENERATOR METHOD OF MOUNTING | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1612 | LATER | MPW | SAU4005-G000-MKA-&MDA-03523 | GT(V) - GENERATOR ANCHOR BLOCK ARRANGEMENT | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1613 | LATER | MPW | SAU4005-G000-MKA-&MDA-03524 | GT(V) - GENERATOR COOLING WATER PIPING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1614 | LATER | MPW | SAU4005-G000-MKG-&MFB-03504 | GT(V) - GENERATOR H2 & CO2 GAS SUPPLY SYSTEM DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1615 | LATER | MPW | SAU4005-G011-MKG-&MFB-03503 | GT(V) - GENERATOR COOLING WATER DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1616 | LATER | MPW | SAU4005-G011-MKG-&MFB-03505 | GT(V) - GENERATOR H2 & CO2 GAS DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1617 | LATER | MPW | SAU4005-G011-MKV-&MFB-03502 | GT(V) - GENERATOR JACKING OIL DIAGRAM FOR GT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1618 | LATER | MPW | SAU4005-G011-MKW-&MFB-03501 | GT(V) - GENERATOR SEAL OIL DIAGRAM FOR GT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-30 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1619 | LATER | MPW | SAU4005-G000-MBA-&CDC-03304 | GT(V) - INSTALLATION PROCEDUDRE FOR THE ANCHOR BOLT & TEMPLATE FOR GT POWER TRAIN | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-20 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1620 | LATER | SPGDC | SAU4005-G104-MAG-&MFE-07302 | ACC(V) - Functional Description | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-08-28 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO | NO | NO |  | NO
1621 | LATER | SPGDC | SAU4005-G104-MAG-&MFB-07303 | ACC(V) - P&I Diagram_Steam & Condensate System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFA | IFD |  |  | 2025-06-28 |  |  |  | 2025-07-18 |  |  |  | 2025-08-23 | [19 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO | NO | NO |  | NO
1622 | LATER | SPGDC | SAU4005-G104-MAG-&MFB-07304 | ACC(V) - P&I Diagram_Air take-off & Cleaning System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFA | IFD |  |  | 2025-06-28 |  |  |  | 2025-07-18 |  |  |  | 2025-08-23 | [19 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO | NO | NO |  | NO
1623 | LATER | SPGDC | SAU4005-G104-MAG-&MED-07308 | ACC(V) - Noise Calculation | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-12-15 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1624 | LATER | SPGDC | SAU4005-G104-MAG-&MDD-07309 | ACC(V) - CFD Analysis Report | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-09-26 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1625 | LATER | SPGDC | SAU4005-G104-MAG-&MPC-07310 | ACC(V) - Terminal Point List | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-08-11 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1626 | LATER | SPGDC | SAU4005-G104-MAG-&MTL-07320 | ACC(V) - General Arrangement | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFA | IFC |  |  | 2025-06-28 |  |  |  | 2025-07-18 |  |  |  | 2025-08-23 | [19 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO | NO | NO |  | NO
1627 | LATER | SPGDC | SAU4005-G104-MAG-&CLB-07321 | ACC(V) - Anchorage / Foundation Loading | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-07-08 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1628 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07322 | ACC(V) - Datasheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFA | IFD |  |  | 2025-07-28 |  |  |  | 2025-08-17 |  |  |  | 2025-09-22 | [19 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1629 | LATER | SPGDC | SAU4005-G104-MAG-&MDD-07323 | ACC(V) - Performance Curve | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-07-28 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1630 | LATER | SPGDC | SAU4005-G104-MAG-&MPB-07324 | ACC(V) - Valve List | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-08-25 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1631 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07325 | ACC(V) - Fan Datasheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFA | IFD |  |  | 2025-07-08 |  |  |  | 2025-07-28 |  |  |  | 2025-09-02 | [19 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1632 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07326 | ACC(V) - Fan Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-10-26 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1633 | LATER | SPGDC | SAU4005-G104-MAG-&EDA-07327 | ACC(V) - Fan Motor Datasheet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-07-18 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1634 | LATER | SPGDC | SAU4005-G104-MAG-&EDA-07328 | ACC(V) - Fan Motor Outline Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-11-25 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1635 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07329 | ACC(V) - Gearbox Datasheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-07-18 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1636 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07330 | ACC(V) - Gearbox Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-11-25 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1637 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07331 | ACC(V) - Steam Jet Air Ejector Datasheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-08-07 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1638 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07332 | ACC(V) - Steam Jet Air Ejector Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-11-25 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1639 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07333 | ACC(V) - Vacuum Pump Datasheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-08-07 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1640 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07334 | ACC(V) - Vacuum Pump Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-11-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1641 | LATER | SPGDC | SAU4005-G104-MAG-&EDA-07335 | ACC(V) - Vacuum Pump Motor Datasheet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-08-07 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1642 | LATER | SPGDC | SAU4005-G104-MAG-&EDA-07336 | ACC(V) - Vacuum Pump Motor Outline & Terminal Box Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-11-25 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1643 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07337 | ACC(V) - Cleaning Water Pump Datasheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-09-06 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1644 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07338 | ACC(V) - Cleaning Water Pump Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2026-01-04 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1645 | LATER | SPGDC | SAU4005-G104-MAG-&EDA-07339 | ACC(V) - Cleaning Water Pump Motor Datasheet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-09-06 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1646 | LATER | SPGDC | SAU4005-G104-MAG-&EDA-07340 | ACC(V) - Cleaning Water Pump Motor Outline & Terminal Box Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2026-01-04 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1647 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07341 | ACC(V) - Drain Pump Datasheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-08-07 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1648 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07342 | ACC(V) - Drain Pump Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-11-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1649 | LATER | SPGDC | SAU4005-G104-MAG-&EDA-07343 | ACC(V) - Drain Pump Motor Datasheet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-08-07 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1650 | LATER | SPGDC | SAU4005-G104-MAG-&EDA-07344 | ACC(V) - Drain Pump Motor Outline & Terminal Box Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-11-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1651 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07345 | ACC(V) - Electrical Lifting Hoist Datasheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-09-06 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1652 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07346 | ACC(V) - Electrical Lifting Hoist Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2026-01-04 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1653 | LATER | SPGDC | SAU4005-G104-MAG-&EDA-07347 | ACC(V) - Electrical Lifting Hoist Motor Datasheet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-09-06 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1654 | LATER | SPGDC | SAU4005-G104-MAG-&EDA-07348 | ACC(V) - Electrical Lifting Hoist Motor Outline & Terminal Box Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2026-01-04 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1655 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07349 | ACC(V) - Condensate Collecting Tank Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-10-26 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1656 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07350 | ACC(V) - Flash Tank Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-10-26 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1657 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07351 | ACC(V) - Tube Bundle Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-07-13 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1658 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07352 | ACC(V) - Expansion Joint Datasheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-09-06 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1659 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07353 | ACC(V) - Expansion Joint Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2026-01-04 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1660 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07354 | ACC(V) - Rupture Disc Datasheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-11-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1661 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07355 | ACC(V) - Rupture Disc Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-12-15 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1662 | LATER | SPGDC | SAU4005-G104-MAG-&MED-07356 | ACC(V) - Vacuum Breaker Valve Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-11-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1663 | LATER | SPGDC | SAU4005-G104-MAG-&MPD-07357 | ACC(V) - Equipment List | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-07-18 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1664 | LATER | SPGDC | SAU4005-G104-MAG-&CTS-07358 | ACC(V) - Steel Structure Drawing (Erection Drawing) | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-09-26 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1665 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07363 | ACC(V) - Piping Arrangement Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-11-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1666 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07364 | ACC(V) - Piping Isometric Drawring - Mixed Bundles Air Take Off Lines | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-11-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1667 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07365 | ACC(V) - Piping Isometric Drawring - Main Condensate Lines | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-11-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1668 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07366 | ACC(V) - Piping Isometric Drawring - Condensate Tank Drain Lines | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-11-25 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1669 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07367 | ACC(V) - Piping Isometric Drawring - Drain Pump Lines | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-11-25 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1670 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07368 | ACC(V) - Piping Isometric Drawring - Drain Tank, Flash Tank, and Vacuum Unit Drain Lines | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-11-25 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1671 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07369 | ACC(V) - Piping Isometric Drawring - Air Take Off Holding Lines | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-11-25 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1672 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07370 | ACC(V) - Piping Isometric Drawring - Equalising Lines | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-11-25 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1673 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07371 | ACC(V) - Duct Arrangement Drawing & Support Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-09-26 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1674 | LATER | SPGDC | SAU4005-G104-MAG-&MPD-07374 | ACC(V) - Pipe Line List | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-08-25 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1675 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07375 | ACC(V) - Piping Support Drawing - Cleaning Lines & Site Routing Lines | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-12-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1676 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07376 | ACC(V) - Piping Support Drawing - Main Condensate Lines | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-12-25 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1677 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07377 | ACC(V) - Piping Support Drawing - Condensate Tank Drain Lines | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-12-25 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1678 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07378 | ACC(V) - Piping Support Drawing - Drain Pump Lines | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-12-25 | [15 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1679 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07379 | ACC(V) - Piping Support Drawing - Drain Tank, Flash Tank, and Vacuum Unit Drain Lines | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-12-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1680 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07380 | ACC(V) - Piping Support Drawing - Air Take Off Holding Lines | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-12-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1681 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07381 | ACC(V) - Piping Support Drawing - Equalising Lines | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-12-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1682 | LATER | SPGDC | SAU4005-G104-MAG-&MPA-07382 | ACC(V) - Insulation Specification | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-09-26 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1683 | LATER | SPGDC | SAU4005-G104-MAG-&MED-07383 | ACC(V) - Flexibility Analysis for Steam Exhaust Ducting | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-09-26 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1684 | LATER | SPGDC | SAU4005-G104-MAG-&EFF-07384 | ACC(V) - Control Logic Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | MECHANICAL | DOOSAN | ACC | IFA | IFD |  |  | 2025-10-26 |  |  |  | 2025-11-15 |  |  |  | 2025-12-21 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1685 | LATER | SPGDC | SAU4005-G104-MAG-&EPD-07385 | ACC(V) - Instrument List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-08-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1686 | LATER | SPGDC | SAU4005-G104-MAG-&EDA-07386 | ACC(V) - Instrument Datasheet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-09-08 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1687 | LATER | SPGDC | SAU4005-G104-MAG-&ELD-07387 | ACC(V) - Instrument Hook-up Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-10-26 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1688 | LATER | SPGDC | SAU4005-G104-MAG-&ELD-07388 | ACC(V) - Wiring Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2026-01-24 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1689 | LATER | SPGDC | SAU4005-G104-MAG-&ELD-07389 | ACC(V) - Electrical and I&C Item (Terminal Box, Junction Box, Instrument) Layout Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2026-01-24 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1690 | LATER | SPGDC | SAU4005-G104-MAG-&EDA-07390 | ACC(V) - Junction Box Outline Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2026-01-24 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1691 | LATER | SPGDC | SAU4005-G104-MAG-&ELD-07391 | ACC(V) - Lighting and Small Power Layout & Specification | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2026-01-24 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1692 | LATER | SPGDC | SAU4005-G104-MAG-&ELD-07392 | ACC(V) - Cable Raceway Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-11-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1693 | LATER | SPGDC | SAU4005-G104-MAG-&ELD-07393 | ACC(V) - Earthing Layout Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFC | [14 empty] | 2025-11-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1694 | LATER | SPGDC | SAU4005-G104-MAG-&EEC-07394 | ACC(V) - Elec. Load list | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-07-28 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1695 | LATER | SPGDC | SAU4005-G104-MAG-&EMA-07395 | ACC(V) - Power Supply Distribution Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-10-26 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1696 | LATER | SPGDC | SAU4005-G104-MAG-&EPF-07397 | ACC(V) - Hardwired IO list | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-12-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1697 | LATER | SPGDC | SAU4005-G104-MAG-&EPD-09400 | ACC(V) - Drive list (MOVs, Motors, Control valves, Solenoid valves, etc..) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2026-01-24 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1698 | LATER | SPGDC | SAU4005-G104-MAG-&EPD-09401 | ACC(V) - Cable Schedule | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-11-25 | [17 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1699 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09624 | BFP(V) - Piping detailed drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFA | IFC |  |  | 2025-08-10 |  |  |  | 2025-08-30 |  |  |  | 2025-10-05 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1700 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09625 | BFP(V) - Coupling Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFD | [14 empty] | 2025-07-17 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1701 | LATER | Hyosung | SAU4005-G011-LAC-&MFB-09634 | BFP(V) - Instrument Hookup drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFC | [14 empty] | 2025-09-12 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1702 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09622 | BFP(V) - Instrument data sheets | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFA | IFD |  |  | 2025-08-29 |  |  |  | 2025-09-18 |  |  |  | 2025-10-24 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1703 | LATER | Hyosung | SAU4005-G011-LAC-&MGD-09650 | BFP(V) - Instrument list | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFD | [14 empty] | 2025-08-29 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1704 | LATER | Hyosung | SAU4005-G011-LAC-&MGD-09655 | BFP(V) - Complete Valve list & Valve datasheet. | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFA | IFD |  |  | 2025-08-15 |  |  |  | 2025-09-04 |  |  |  | 2025-10-10 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1705 | LATER | Hyosung | SAU4005-G011-LAC-&MMB-09640 | BFP(V) - Instrumentation wiring diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFA | IFC |  |  | 2025-08-10 |  |  |  | 2025-08-30 |  |  |  | 2025-10-05 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1706 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09616 | BFP(V) - Lubrication oil system data sheets | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFA | IFD |  |  | 2025-07-17 |  |  |  | 2025-08-06 |  |  |  | 2025-09-11 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1707 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09615 | BFP(V) - Lubrication oil system nameplate drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFD | [14 empty] | 2025-07-17 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1708 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09614 | BFP(V) - Lubrication oil system general arrangement drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFA | IFD |  |  | 2025-07-21 |  |  |  | 2025-08-10 |  |  |  | 2025-09-15 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1709 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09605 | BFP(V) - General Arrangement drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFA | IFC |  |  | 2025-06-20 |  |  |  | 2025-07-10 |  |  |  | 2025-08-15 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1710 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09609 | BFP(V) - Motor general arrangement drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFD | [14 empty] | 2025-08-01 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1711 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09608 | BFP(V) - Motor data sheets | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFA | IFD |  |  | 2025-08-01 |  |  |  | 2025-08-21 |  |  |  | 2025-09-26 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1712 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09611 | BFP(V) - Motor nameplate drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFA | IFD |  |  | 2025-08-01 |  |  |  | 2025-08-21 |  |  |  | 2025-09-26 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1713 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09612 | BFP(V) - Motor performance curves | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFD | [14 empty] | 2025-08-01 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1714 | LATER | Hyosung | SAU4005-G011-LAC-&ELU-09684 | BFP(V) - I&C Junction Box & Outline Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFD | [14 empty] | 2025-08-15 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1715 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09606 | BFP(V) - Pump data sheets | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFA | IFD |  |  | 2025-06-20 |  |  |  | 2025-07-10 |  |  |  | 2025-08-15 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1716 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09607 | BFP(V) - Pump performance curves | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFD | [14 empty] | 2025-06-20 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1717 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09610 | BFP(V) - Pump nameplate drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFD | [14 empty] | 2025-06-20 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1718 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09613 | BFP(V) - Pump sectional drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFD | [14 empty] | 2025-06-20 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1719 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09618 | BFP(V) - Mechanical seal general arrangement drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFD | [14 empty] | 2025-08-29 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1720 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09695 | BFP(V) - Cooler Specification | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFD | [14 empty] | 2025-08-29 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1721 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09617 | BFP(V) - Suction strainer data sheets | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFA | IFD |  |  | 2025-08-29 |  |  |  | 2025-09-18 |  |  |  | 2025-10-24 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1722 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09619 | BFP(V) - Suction strainer general arrangement drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFD | [14 empty] | 2025-08-29 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1723 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09696 | BFP(V) - Orifice Drawing & Data sheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFA | IFD |  |  | 2025-10-09 |  |  |  | 2025-10-29 |  |  |  | 2025-12-04 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1724 | LATER | Hyosung | SAU4005-G011-LAC-&MEC-09698 | BFP(V) - Thermal insulation specification | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFP | [14 empty] | 2025-08-29 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1725 | LATER | Hyosung | SAU4005-G011-LAC-&ELU-09699 | BFP(V) - Diagram of LPBS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFC | [14 empty] | 2025-08-15 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1726 | LATER | Hyosung | SAU4005-G011-LAC-&ELU-09700 | BFP(V) - LPBS Specification | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFD | [14 empty] | 2025-08-15 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1727 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09701 | BFP(V) - Sound Enclosure Specification & Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFP | [14 empty] | 2025-08-15 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1728 | LATER | Hyosung | SAU4005-G011-LAC-&MFB-09632 | BFP(V) - Pump Piping & instrumentation diagram | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFA | IFC |  |  | 2025-06-20 |  |  |  | 2025-07-10 |  |  |  | 2025-08-15 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1729 | LATER | Hyosung | SAU4005-G011-LAC-&MDD-09698 | BFP(V) - Wake frequency calculation | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFD | [14 empty] | 2025-08-15 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1730 | LATER | Hyosung | SAU4005-G000-LCB-&MDF-09500 | CEP(V) - Performance Curve | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFD | [14 empty] | 2025-06-20 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1731 | LATER | Hyosung | SAU4005-G000-LCB-&MDA-09501 | CEP(V) - Datasheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFA | IFD |  |  | 2025-06-20 |  |  |  | 2025-07-10 |  |  |  | 2025-08-15 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1732 | LATER | Hyosung | SAU4005-G000-LCB-&MLU-09502 | CEP(V) - General Arrangement Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFA | IFC |  |  | 2025-06-20 |  |  |  | 2025-07-10 |  |  |  | 2025-08-15 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1733 | LATER | Hyosung | SAU4005-G000-LCB-&MFB-09503 | CEP(V) - Piping & Instrument Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFA | IFC |  |  | 2025-06-20 |  |  |  | 2025-07-10 |  |  |  | 2025-08-15 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1734 | LATER | Hyosung | SAU4005-G000-LCB-&MLU-09504 | CEP(V) - Pump Section Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFD | [14 empty] | 2025-06-20 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1735 | LATER | Hyosung | SAU4005-G000-LCB-&MLU-09505 | CEP(V) - Pump Mechenical. Seal Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFD | [14 empty] | 2025-08-29 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1736 | LATER | Hyosung | SAU4005-G000-LCB-&MDA-09506 | CEP(V) - Pump Nameplate Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFD | [14 empty] | 2025-07-17 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1737 | LATER | Hyosung | SAU4005-G000-LCB-&MEC-09547 | CEP(V) - Thermal insulation specification | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFP | [14 empty] | 2025-08-29 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1738 | LATER | Hyosung | SAU4005-G000-LCB-&EEC-09509 | CEP(V) - Instrument List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFD | [14 empty] | 2025-08-29 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1739 | LATER | Hyosung | SAU4005-G000-LCB-&MFB-09549 | CEP(V) - Instrument Hookup drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFC | [14 empty] | 2025-09-12 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1740 | LATER | Hyosung | SAU4005-G000-LCB-&EEC-09510 | CEP(V) - I/O List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFD | [14 empty] | 2025-08-15 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1741 | LATER | Hyosung | SAU4005-G000-LCB-&ELU-09550 | CEP(V) - I&C Junction Box & Outline Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFD | [14 empty] | 2025-08-15 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1742 | LATER | Hyosung | SAU4005-G000-LCB-&EDA-09511 | CEP(V) - Motor Data Sheet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFA | IFD |  |  | 2025-08-01 |  |  |  | 2025-08-21 |  |  |  | 2025-09-26 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1743 | LATER | Hyosung | SAU4005-G000-LCB-&EDF-09512 | CEP(V) - Motor Performance Curve | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFD | [14 empty] | 2025-08-01 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1744 | LATER | Hyosung | SAU4005-G000-LCB-&ELU-09513 | CEP(V) - Motor Outline Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFD | [14 empty] | 2025-08-01 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1745 | LATER | Hyosung | SAU4005-G000-LCB-&EDA-09514 | CEP(V) - Motor Terminal Box Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFD | [14 empty] | 2025-08-15 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1746 | LATER | Hyosung | SAU4005-G000-LCB-&MDA-09524 | CEP(V) - Motor Nameplate Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFA | IFD |  |  | 2025-08-01 |  |  |  | 2025-08-21 |  |  |  | 2025-09-26 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1747 | LATER | Hyosung | SAU4005-G000-LCB-&MEC-09525 | CEP(V) - Valve List & Datasheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFA | IFD |  |  | 2025-08-15 |  |  |  | 2025-09-04 |  |  |  | 2025-10-10 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1748 | LATER | Hyosung | SAU4005-G000-LCB-&MEC-09526 | CEP(V) - Strainer Technical Documents | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFP | [14 empty] | 2025-08-15 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1749 | LATER | Hyosung | SAU4005-G000-LCB-&MEC-09528 | CEP(V) - Coupling Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFD | [14 empty] | 2025-07-17 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1750 | LATER | Hyosung | SAU4005-G000-LCB-&ELU-09537 | CEP(V) - Diagram of LPBS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFC | [14 empty] | 2025-08-01 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1751 | LATER | Hyosung | SAU4005-G000-LCB-NMLU-09548 | CEP(V) - Aux. Piping Arrangement Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFC |  |  | 2025-08-15 |  |  |  | 2025-09-04 |  |  |  | 2025-10-10 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1752 | LATER | Hyosung | SAU4005-G000-LCB-NEEC-09555 | CEP(V) - LPBS Specification | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFD | [14 empty] | 2025-08-01 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1753 | LATER | Hyosung | SAU4005-G000-LCB-NMMB-09540 | CEP(V) - Pipe Line List | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFD | [14 empty] | 2025-07-17 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1754 | LATER | Hyosung | SAU4005-G000-LCB-&MDA-09567 | CEP(V) - Instrument Data Sheets | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFA | IFD |  |  | 2025-08-07 |  |  |  | 2025-08-27 |  |  |  | 2025-10-02 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
1755 | LATER | LATER | SAU4005-G010-ACA-&MDA-09801 | GSP(V) - Motor Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECHANICAL | MECHANICAL | DOOSAN | GSP | IFI | IFD | [14 empty] | 2025-10-15 | [15 empty] | DE | MECHANICAL | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO | YES | NO | NO |  | NO
1756 | LATER | LATER | SAU4005-G010-ACA-&MDA-09802 | GSP(V) - Motor Terminal Box Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECHANICAL | MECHANICAL | DOOSAN | GSP | IFI | IFD | [14 empty] | 2025-11-15 | [15 empty] | DE | MECHANICAL | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO | YES | NO | NO |  | NO
1757 | LATER | LATER | SAU4005-G010-ACA-&MDA-09803 | GSP(V) - Pump Section Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECHANICAL | MECHANICAL | DOOSAN | GSP | IFI | IFD | [14 empty] | 2025-11-15 | [15 empty] | DE | MECHANICAL | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO | YES | NO | NO |  | NO
1758 | LATER | LATER | SAU4005-G010-ACA-&MDA-09804 | GSP(V) - Nameplate Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECHANICAL | MECHANICAL | DOOSAN | GSP | IFI | IFD | [14 empty] | 2025-11-15 | [15 empty] | DE | MECHANICAL | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO | YES | NO | NO |  | NO
1759 | LATER | LATER | SAU4005-G010-ACA-&MDA-09805 | GSP(V) - Tagplate Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECHANICAL | MECHANICAL | DOOSAN | GSP | IFI | IFD | [14 empty] | 2025-11-15 | [15 empty] | DE | MECHANICAL | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO | YES | NO | NO |  | NO
1760 | LATER | LATER | SAU4005-G010-ACA-&MPC-09808 | GSP(V) - Valve List | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECHANICAL | MECHANICAL | DOOSAN | GSP | IFI | IFD | [14 empty] | 2025-11-15 | [15 empty] | DE | MECHANICAL | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO | YES | NO | NO |  | NO
1761 | LATER | LATER | SAU4005-G010-ACA-&EPC-09809 | GSP(V) - Instrument List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | GSP | IFI | IFD | [14 empty] | 2025-11-15 | [15 empty] | DE | I&C | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO | YES | NO | NO |  | NO
1762 | LATER | LATER | SAU4005-G010-ACA-&MDA-09810 | GSP(V) - Instrument Hook up Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | GSP | IFI | IFD | [14 empty] | 2025-12-15 | [15 empty] | DE | I&C | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO | YES | NO | NO |  | NO
1763 | LATER | LATER | SAU4005-G119-ACA-&MDA-09800 | GSP(V) - Pump Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECHANICAL | MECHANICAL | DOOSAN | GSP | IFA | IFD |  |  | 2025-10-15 |  |  |  | 2025-11-04 |  |  |  | 2025-12-10 | [19 empty] | DE | MECHANICAL | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO | YES | NO | NO |  | NO
1764 | LATER | LATER | SAU4005-G119-ACA-&MDA-09806 | GSP(V) - Pump Data Sheet with Performance Curve | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECHANICAL | MECHANICAL | DOOSAN | GSP | IFA | IFD |  |  | 2025-10-15 |  |  |  | 2025-11-04 |  |  |  | 2025-12-10 | [19 empty] | DE | MECHANICAL | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO | YES | NO | NO |  | NO
1765 | LATER | LATER | SAU4005-G119-ACA-&EDA-09807 | GSP(V) - Motor Data Sheet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GSP | IFA | IFD |  |  | 2025-10-15 |  |  |  | 2025-11-04 |  |  |  | 2025-12-10 | [19 empty] | DE | ELECTRICAL | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO | YES | NO | NO |  | NO
1766 | LATER | Emerson | SAU4005-G180-C__-&EFE-25001 | DCS(V) - Functional Design Specification for Hardware | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFA | IFD |  |  | 2025-07-16 |  |  |  | 2025-08-05 |  |  |  | 2025-09-10 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1767 | LATER | Emerson | SAU4005-G180-C__-&EFE-25002 | DCS(V) - Functional Design Specification for Software | A1 | Engineering | B-Overall technology | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFA | IFD |  |  | 2025-07-16 |  |  |  | 2025-08-05 |  |  |  | 2025-09-10 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1768 | LATER | Emerson | SAU4005-G180-C__-&EFE-25003 | DCS(V) - Functional Design Specification for Graphic | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFA | IFD |  |  | 2025-07-16 |  |  |  | 2025-08-05 |  |  |  | 2025-09-10 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1769 | LATER | Emerson | SAU4005-G180-C__-&EFE-25004 | DCS(V) - Functional Design Specification for Safety Related System | A1 | Engineering | B-Overall technology | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFA | IFD |  |  | 2025-09-11 |  |  |  | 2025-10-01 |  |  |  | 2025-11-06 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1770 | LATER | Emerson | SAU4005-G180-C__-&EFE-25005 | DCS(V) - Functional Design Specification for Cyber Security and Network | A1 | Engineering | A-Overall management | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFA | IFD |  |  | 2025-07-16 |  |  |  | 2025-08-05 |  |  |  | 2025-09-10 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO | NO | NO |  | NO
1771 | LATER | Emerson | SAU4005-G180-C__-&EFE-25006 | DCS(V) - Functional Design Specification for Plant Performance Monitoring System | A1 | Engineering | B-Overall technology | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFA | IFD |  |  | 2025-10-29 |  |  |  | 2025-11-18 |  |  |  | 2025-12-24 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1772 | LATER | Emerson | SAU4005-G180-C__-&EFE-25007 | DCS(V) - Datasheet & Drawing for Time Synchronization | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFA | IFD |  |  | 2025-08-27 |  |  |  | 2025-09-16 |  |  |  | 2025-10-22 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1773 | LATER | Emerson | SAU4005-G180-C__-&EFE-25008 | DCS(V) - Datasheet & Drawings for Large Screen Display | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFA | IFD |  |  | 2025-08-27 |  |  |  | 2025-09-16 |  |  |  | 2025-10-22 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1774 | LATER | Emerson | SAU4005-G180-C__-&EFA-25009 | DCS(V) - LAN Configuration Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFI | IFD | [14 empty] | 2025-07-30 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1775 | LATER | Emerson | SAU4005-G180-C__-&ELD-25010 | DCS(V) - Grounding Detail Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFI | IFC | [14 empty] | 2025-11-16 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1776 | LATER | Emerson | SAU4005-G180-C__-&ELU-25011 | DCS(V) - Typical Outline Drawing for Cabinet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFI | IFD | [14 empty] | 2025-07-30 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1777 | LATER | Emerson | SAU4005-G180-C__-&ELU-25012 | DCS(V) - Outline & Detail Drawing for System and Marshalling Cabinet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFI | IFD | [14 empty] | 2025-10-29 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1778 | LATER | Emerson | SAU4005-G180-C__-&ELU-25013 | DCS(V) - Outline & Detail Drawing for LAN/Server Cabinet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFI | IFD | [14 empty] | 2025-10-29 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1779 | LATER | Emerson | SAU4005-G180-C__-&ELU-25014 | DCS(V) - Outline & Detail Drawing for Power Distribution Cabinet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFI | IFD | [14 empty] | 2025-10-29 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1780 | LATER | Emerson | SAU4005-G180-C__-&ELU-25015 | DCS(V) - Outline & Detail Drawing for Relay Cabinet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFI | IFD | [14 empty] | 2025-10-29 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1781 | LATER | Emerson | SAU4005-G180-C__-&ELU-25016 | DCS(V) - Outline & Detail Drawing for Console Desk with EPB Station | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFI | IFD | [14 empty] | 2025-10-29 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1782 | LATER | Emerson | SAU4005-G180-C__-&ELU-25017 | DCS(V) - Outline & Detail Drawing for Provision Cabinet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFI | IFD | [14 empty] | 2025-10-29 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1783 | LATER | Emerson | SAU4005-G180-C__-&ELU-25018 | DCS(V) - Outline & Detail Drawing for Safety Related System Cabinet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFI | IFD | [14 empty] | 2025-10-29 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1784 | LATER | Emerson | SAU4005-G180-C__-&EFC-25019 | DCS(V) - HMI Graphic Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFA | IFD |  |  | 2026-03-30 |  |  |  | 2026-04-19 |  |  |  | 2026-05-25 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1785 | LATER | Emerson | SAU4005-G180-C__-&EFP-25020 | DCS(V) - IO & Module Allocation | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFI | IFD | [14 empty] | 2025-11-29 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1786 | LATER | Emerson | SAU4005-G180-C__-&EMA-25021 | DCS(V) - Internal Interconnection Wiring Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFI | IFD | [14 empty] | 2026-02-28 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1787 | LATER | Emerson | SAU4005-G180-C__-&EMB-25022 | DCS(V) - Cable List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFI | IFC | [14 empty] | 2026-03-30 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1788 | LATER | Emerson | SAU4005-G180-C__-&BQA-25025 | DCS(V) - SAT Procedure | A1 | Commissioning | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFA | IFC |  |  | 2026-03-30 |  |  |  | 2026-04-19 |  |  |  | 2026-05-25 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1789 | LATER | Emerson | SAU4005-G180-C__-&EFE-25028 | DCS(V) - Functional Design Specification for Field Instrument Management System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFA | IFD |  |  | 2025-08-27 |  |  |  | 2025-09-16 |  |  |  | 2025-10-22 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1790 | LATER | Emerson | SAU4005-G180-C__-&EFE-25029 | DCS(V) - Functional Design Specification for Remote Monitoring System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFA | IFD |  |  | 2025-08-27 |  |  |  | 2025-09-16 |  |  |  | 2025-10-22 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1791 | LATER | Emerson | SAU4005-G180-C__-&EFE-25105 | DCS(V) - 3rd Party Datalink Specification(OPC, IEC, Modbus) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFA | IFD |  |  | 2025-08-27 |  |  |  | 2025-09-16 |  |  |  | 2025-10-22 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
1792 | LATER | LATER | SAU4005-G185-C__-&EDA-22800 | VMS(V) - Datasheet & Vender Print | A1 | EN-Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | VMS | IFA | IFD |  |  | 2025-10-30 | [7 empty] | 2025-12-30 | [20 empty] | I&C&DCS | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1793 | LATER | LATER | SAU4005-G185-C__-&EFA-22801 | VMS(V) - System Configuration | A1 | EN-Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | VMS | IFI | IFD | [14 empty] | 2025-10-30 | [16 empty] | I&C&DCS | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
1794 | LATER | SWT | SAU4005-G158-XKA-&EDA-21001 | BSEDG(V) - Control cabinet layout of DG | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-09-11
1795 | LATER | SWT | SAU4005-G158-XKA-&EEC-21002 | BSEDG(V) - Cable schedule | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-09-11
1796 | LATER | SWT | SAU4005-G158-XKA-&EFB-21003 | BSEDG(V) - Wiring diagrams | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-10-23
1797 | LATER | SWT | SAU4005-G158-XKA-&ELU-21004 | BSEDG(V) - General Arrangement | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | GENERAL | GENERAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-07-31
1798 | LATER | SWT | SAU4005-G158-XKA-&EFB-21005 | BSEDG(V) - P&ID(FUEL OIL SYSTEM, LUBE OIL SYSTEM, COOLING WATER SYSTEM, AIR INTAKE & EXHAUST SYSTEM ) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECHANICAL | MECHANICAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-07-03
1799 | LATER | SWT | SAU4005-G158-XKA-&EEC-21006 | BSEDG(V) - Electrical load list | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-07-31
1800 | LATER | SWT | SAU4005-G158-XKA-&EPF-21007 | BSEDG(V) - PLC IO List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-10-23
1801 | LATER | SWT | SAU4005-G158-XKA-&EDA-21008 | BSEDG(V) - Datasheet for DG | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | GENERAL | GENERAL | DOOSAN | BSDG | IFA | IFC |  |  | 2025-07-03 |  |  |  | 2025-08-07 |  |  |  | 2025-09-11
1802 | LATER | SWT | SAU4005-G158-XKA-&EDB-21009 | BSEDG(V) - Control System Configuration | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-10-23
1803 | LATER | SWT | SAU4005-G158-XKA-&EDA-21010 | BSEDG(V) - Nameplate drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECHANICAL | MECHANICAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-10-23
1804 | LATER | SWT | SAU4005-G158-XKA-&EDA-21011 | BSEDG(V) - Technical specification for Panel /SWGR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-10-23
1805 | LATER | SWT | SAU4005-G158-XKA-&EFB-21012 | BSEDG(V) - Single Line Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | BSDG | IFA | IFC |  |  | 2025-08-14 |  |  |  | 2025-09-18 |  |  |  | 2025-10-23
1806 | LATER | SWT | SAU4005-G158-XKA-&EFB-21013 | BSEDG(V) - Schematic Diagram for SWGR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | BSDG | IFA | IFC |  |  | 2025-08-14 |  |  |  | 2025-09-18 |  |  |  | 2025-10-23
1807 | LATER | SWT | SAU4005-G158-XKA-&EDB-21014 | BSEDG(V) - Operation philosophy and System description | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | GENERAL | GENERAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-07-31
1808 | LATER | SWT | SAU4005-G158-XKA-&ELD-21015 | BSEDG(V) - Earthing terminal point drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-10-23
1809 | LATER | SWT | SAU4005-G158-XKA-&ELB-21016 | BSEDG(V) - Foundation drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | CIVIL | CIVIL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-09-25
1810 | LATER | SWT | SAU4005-G158-XKA-&ELD-21017 | BSEDG(V) - Piping Arrangement Drawing (FUEL OIL SYSTEM, LUBE OIL SYSTEM, COOLING WATER SYSTEM, AIR INTAKE & EXHAUST SYSTEM ) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECHANICAL | MECHANICAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-09-25
1811 | LATER | SWT | SAU4005-G158-XKA-&ELD-21018 | BSEDG(V) - Piping ISOMETRIC Drawing (FUEL OIL SYSTEM, LUBE OIL SYSTEM, COOLING WATER SYSTEM, AIR INTAKE & EXHAUST SYSTEM ) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECHANICAL | MECHANICAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-10-23
1812 | LATER | SWT | SAU4005-G158-XKA-&EDC-21021 | BSEDG(V) - O&M Manual | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | GENERAL | GENERAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2026-01-20
1813 | LATER | SWT | SAU4005-G158-XKA-&EDC-21022 | BSEDG(V) - Commissioning procedure | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | GENERAL | GENERAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2026-01-20
1814 | LATER | SWT | SAU4005-G158-XKA-&EDC-21023 | BSEDG(V) - Installation and Erection Manual | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | GENERAL | GENERAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-10-23
1815 | LATER | SWT | SAU4005-G158-XKA-&EBF-21024 | BSEDG(V) - Master Supply List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | GENERAL | GENERAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2026-01-20
1816 | LATER | SWT | SAU4005-G158-XKA-&EPA-21025 | BSEDG(V) - Chemical list and supplier list | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | GENERAL | GENERAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2026-03-17
1817 | LATER | SWT | SAU4005-G158-XKA-&EDA-21026 | BSEDG(V) - Outline Drawing for DG | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | GENERAL | GENERAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2026-03-17
1818 | LATER | SWT | SAU4005-G158-XKA-&EEC-21027 | BSEDG(V) - PIPE LINE LIST | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECHANICAL | MECHANICAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-07-03
1819 | LATER | SWT | SAU4005-G158-XKA-&ELD-21028 | BSEDG(V) - ACCESS PLATFORM DRAWING | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECHANICAL | MECHANICAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-08-28
1820 | LATER | SWT | SAU4005-G158-XKA-&EEC-21029 | BSEDG(V) - VALVE LIST | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECHANICAL | MECHANICAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-09-25
1821 | LATER | SWT | SAU4005-G158-XKA-&EED-21030 | BSEDG(V) - HVAC CALCULATION | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECHANICAL | MECHANICAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-08-28
1822 | LATER | SWT | SAU4005-G158-XKA-&EPL-21031 | BSEDG(V) - Terminal Point List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECHANICAL | MECHANICAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-07-03
1823 | LATER | SWT | SAU4005-G158-XKA-&EFC-21032 | BSEDG(V) - PLC HMI graphic | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-07-03
1824 | LATER | SWT | SAU4005-G158-XKA-&ELD-21033 | BSEDG(V) - PLC/DCS/MCC Arrangement/Layout Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-07-17
1825 | LATER | SWT | SAU4005-G158-XKA-&ELD-21034 | BSEDG(V) - Cabinet / Panel terminal Block details | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-07-17
1826 | LATER | SWT | SAU4005-G158-XKA-&EDA-21035 | BSEDG(V) - PLC Specification | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-08-28
1827 | LATER | SWT | SAU4005-G158-XKA-&EPF-21036 | BSEDG(V) - Datalink IO List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-10-23
1828 | LATER | SWT | SAU4005-G158-XKA-&ELD-21037 | BSEDG(V) - Hook Up Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-10-23
1829 | LATER | SWT | SAU4005-G158-XKA-&EFE-21038 | BSEDG(V) - Functional Description | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-07-17
1830 | LATER | SWT | SAU4005-G158-XKA-&EEC-21039 | BSEDG(V) - Instrument List & Data Sheet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-07-31
1831 | LATER | SWT | SAU4005-G158-XKA-&EEC-21041 | BSEDG(V) - Instrument Installation Detail Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-10-23
1832 | LATER | SWT | SAU4005-G158-XKA-&EPL-21042 | BSEDG(V) - Instrument Location Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-10-23
1833 | LATER | SWT | SAU4005-G158-XKA-&EDD-21043 | BSEDG(V) - Protection relay setting report | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-10-23
1834 | LATER | SWT | SAU4005-G158-XKA-&ELD-21044 | BSEDG(V) - Cable raceway drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-08-14
1835 | LATER | SWT | SAU4005-G158-XKA-&EED-21045 | BSEDG(V) - DC System calculation | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-09-25
1836 | LATER | SWT | SAU4005-G158-XKA-&ETB-21046 | BSEDG(V) - 3D Modeling | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | GENERAL | GENERAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-08-28
1837 | LATER | SWT | SAU4005-G158-XKA-&EED-21047 | BSEDG(V) - Fuel Oil Storage Tank Sizing Calculation | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECHANICAL | MECHANICAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2026-04-14
1838 | LATER | SWT | SAU4005-G158-XKA-&EQB-21048 | BSEDG(V) - Hazardous Area Classification | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECHANICAL | MECHANICAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-06-19
1839 | LATER | SWT | SAU4005-G158-XKA-&EMB-21049 | BSEDG(V) - Instrument Cable Schedule | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-10-23
1840 | LATER | SWT | SAU4005-G158-XKA-&EMA-21050 | BSEDG(V) - I&C cable interconnection list | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-10-23
1841 | LATER | SWT | SAU4005-G158-XKA-&EMA-21051 | BSEDG(V) - Cable interconnection diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-09-25
1842 | LATER | SWT | SAU4005-G158-XKA-&EDD-21052 | BSEDG(V) - Vibration Guarantee Data | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | GENERAL | GENERAL | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-09-25
1843 | LATER | SWT | SAU4005-G158-XKA-&EFF-21053 | BSEDG(V) - Control Logic & Loop Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFA | IFC |  |  | 2025-07-03 |  |  |  | 2025-08-07 |  |  |  | 2025-09-11
1844 | LATER | SWT | SAU4005-G158-MJ_-&EQC-21029 | BSDG(V) - Emergency Diesel Generator - Factory Inspection Test Plan | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | Electrical | Electrical | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-10-22 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1845 | LATER | SWT | SAU4005-G158-MJ_-&EQA-21040 | BSDG(V) - Emergency Diesel Generator - Factory Procedures | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | Electrical | Electrical | DOOSAN | BSDG | IFI | IFC | [14 empty] | 2025-10-22 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
1846 | LATER | Later | SAU4005-G131-MAN-&MDA-11502 | Bypass Valve & PRDS(V) - Sectional Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | PROCESS | IFI | IFC | [30 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1847 | LATER | Later | SAU4005-G131-MAN-&EMA-11503 | Bypass Valve & PRDS(V) - Wiring Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | PROCESS | IFI | IFC | [30 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1848 | LATER | Later | SAU4005-G131-MAN-&MFB-11504 | Bypass Valve & PRDS(V) - Pneumatic Diagram | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | PROCESS | IFI | IFC | [30 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1849 | LATER | Later | SAU4005-G131-MAN-&MDC-11511 | Bypass Valve & PRDS(V) - Operation & Maintenance Manual | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | PROCESS | IFI | IFC | [30 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1850 | LATER | Later | SAU4005-G127-LBG-&MDC-11162 | Safety Relief Valves(V) - Operation & Maintenance Manual | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | PROCESS | IFI | IFC | [30 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1851 | LATER | Later | SAU4005-G128-LB-&MDC-11262 | Motor Operated Valve for Steam and Water(V) - Operation & Maintenance Manual | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | PROCESS | IFI | IFC | [30 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1852 | LATER | Later | SAU4005-G127-LBG-&MDC-11172 | Silencer(V) - Operation & Maintenance Manual | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | PROCESS | IFI | IFC | [30 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1853 | LATER | Later | SAU4005-G131-MAN-&MDA-11500 | Bypass Valve & PRDS(V) - Data Sheet and Charateristic Curves | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | PROCESS | IFA | IFD | [30 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1854 | LATER | Later | SAU4005-G131-MAN-&MDA-11501 | Bypass Valve & PRDS(V) - Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | PROCESS | IFA | IFC | [30 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1855 | LATER | Later | SAU4005-G127-LBG-&MDA-11160 | Safety Relief Valves(V) - Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | PROCESS | IFA | IFC | [30 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1856 | LATER | Later | SAU4005-G127-LBG-&MDA-11161 | Safety Relief Valves(V) - Data Sheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | PROCESS | IFA | IFD | [30 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1857 | LATER | Later | SAU4005-G128-LB-&MDA-11260 | Motor Operated Valve for Steam and Water(V) - Data Sheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | PROCESS | IFA | IFD | [30 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1858 | LATER | Later | SAU4005-G128-LB-&MDA-11261 | Motor Operated Valve for Steam and Water(V) - Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | PROCESS | IFA | IFC | [30 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1859 | LATER | Later | SAU4005-G127-LBG-&MDA-11170 | Silencer(V) - Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | PROCESS | IFA | IFC | [30 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1860 | LATER | Later | SAU4005-G127-LBG-&MDA-11171 | Silencer(V) - Data Sheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | PROCESS | IFA | IFD | [30 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
1861 | LATER | Later | SAU4005-G108-LB-&MDA-07760 | Atm Flash Tank(V) - Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | PROCESS | IFA | IFC | [30 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
Formulas:
Baseline = [Issue for Approval (1st issue)]+20
Final approval and issue to Owner (IFC) = [Baseline]+38

## others
| * Note - EPC will submit on ThinkProject(TP) only the documents listed in the MDL. EPC can not upload any documents on TP unless it is listed in the MDL. - This Engineering MDL will be used as part of Project MDL(Doc No. XXX ) along with the MDLs from other departments. - The Project MDL must be used exclusively for document uploads on TP database, which will serve as the reference for all types of reporting. - The submission dates for documents in TP must be aligned with the Primavera software program of the project schedule. - Since the package vendor has not yet been finalized, the following Vendor Document will be updated as per progress is updated. | [14 empty] | Class 1 Issue For Approval | [11 empty] | Class 2 Issue for Information
No. | P6 Activity ID | Issued by | Document Number | Document Description | Plant | Department | Discipline (DCC A1) | Common document of Nairyah and Nairyah | Sub-Discipline | WBS Category | System(APEX Code) | Class / Purpose | IFD / IFC / IFP | Actual Rev Status | Step | Issue for Approval (1st issue) |  |  |  | Approved with comments and issue to Owner |  |  |  | Final approval and issue to Owner (IFC) |  |  |  | IFI |  |  |  | Estimated Manhours | Document Weight | PROGRESS |  |  | TOTAL FLOAT |  | TO be reviewed by |  |  |  | TOP No.
[15 empty] | Cumm | 45% |  |  |  | 80% |  |  |  | 100% |  |  |  | 100% | [5 empty] | Baseline | Forecast | Actual | Baseline | Actual | ACWA PC | OE | NOMAC | CTS
[15 empty] | Partial | 45% |  |  |  | 35% |  |  |  | 20% |  |  |  | 100%
[16 empty] | Baseline | Forecast | Actual | variance | Baseline | Forecast | Actual | variance | Baseline | Forecast | Actual | variance | Baseline | Forecast | Actual | variance | [12 empty] | Engineering Type | Sub Discipline | Work Flow | OE Review (Yes/No) | O&M Review (Yes/NO) | SPPC (Off Taker) Submission (Yes/No) | SPPC (Off Taker) Submission (C1,C2,C3,C4) | For interfacing parties (SEC, Aramco,NWC) | SEC-NG Department | NOC | Open/Combine Cycle (Open/Combine/Partial) | ACWA ENGINEERING MGR OWN
1 | N/A | DE | SAU4005-G000-___-&ABB-02003 | Weekly Progress Report on 14th February 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-02-17 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
2 | N/A | DE | SAU4005-G000-___-&ABB-02004 | Weekly Progress Report on 21st February 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-02-24 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
3 | N/A | DE | SAU4005-G000-___-&ABB-02005 | Weekly Progress Report on 28th February 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-03-03 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
4 | N/A | DE | SAU4005-G000-___-&ABB-02007 | Weekly Progress Report on 7th March 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-03-10 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
5 | N/A | DE | SAU4005-G000-___-&ABB-02008 | Weekly Progress Report on 14th March 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-03-17 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
6 | N/A | DE | SAU4005-G000-___-&ABB-02009 | Weekly Progress Report on 28th Mar 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-03-24 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
7 | N/A | DE | SAU4005-G000-___-&ABB-02010 | Weekly Progress Report on 28th Mar 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-03-31 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
8 | N/A | DE | SAU4005-G000-___-&ABB-02012 | Weekly Progress Report on 4th April 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-04-07 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
9 | N/A | DE | SAU4005-G000-___-&ABB-02013 | Weekly Progress Report on 11th April 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-04-14 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
10 | N/A | DE | SAU4005-G000-___-&ABB-02014 | Weekly Progress Report on 18th April 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-04-21 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
11 | N/A | DE | SAU4005-G000-___-&ABB-02015 | Weekly Progress Report on 25th April 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-04-28 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
12 | N/A | DE | SAU4005-G000-___-&ABB-02017 | Weekly Progress Report on 2nd May 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-05-05 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
13 | N/A | DE | SAU4005-G000-___-&ABB-02018 | Weekly Progress Report on 9th May 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-05-12 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
14 | N/A | DE | SAU4005-G000-___-&ABB-02019 | Weekly Progress Report on 16th May 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-05-19 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
15 | N/A | DE | SAU4005-G000-___-&ABB-02020 | Weekly Progress Report on 23rd May 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-05-26 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
16 | N/A | DE | SAU4005-G000-___-&ABB-02021 | Weekly Progress Report on 30th May 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-06-02 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
17 | N/A | DE | SAU4005-G000-___-&ABB-02022 | Weekly Progress Report on 6th June 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-06-09 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
18 | N/A | DE | SAU4005-G000-___-&ABB-02023 | Weekly Progress Report on 13th June 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-06-16 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
19 | N/A | DE | SAU4005-G000-___-&ABB-02024 | Weekly Progress Report on 20th June 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-06-23 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
20 | N/A | DE | SAU4005-G000-___-&ABB-02025 | Weekly Progress Report on 27th June 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-06-30 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
21 | N/A | DE | SAU4005-G000-___-&ABB-02026 | Weekly Progress Report on 4th July 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-07-07 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
22 | N/A | DE | SAU4005-G000-___-&ABB-02027 | Weekly Progress Report on 11th July 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-07-14 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
23 | N/A | DE | SAU4005-G000-___-&ABB-02028 | Weekly Progress Report on 18th July 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-07-21 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
24 | N/A | DE | SAU4005-G000-___-&ABB-02029 | Weekly Progress Report on 25th July 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-07-28 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
25 | N/A | DE | SAU4005-G000-___-&ABB-02030 | Weekly Progress Report on 1st August 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-08-04 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
26 | N/A | DE | SAU4005-G000-___-&ABB-02031 | Weekly Progress Report on 8th August 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-08-11 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
27 | N/A | DE | SAU4005-G000-___-&ABB-02032 | Weekly Progress Report on 15th August 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-08-18 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
28 | N/A | DE | SAU4005-G000-___-&ABB-02033 | Weekly Progress Report on 22nd August 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-08-25 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
29 | N/A | DE | SAU4005-G000-___-&ABB-02034 | Weekly Progress Report on 29th August 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-09-01 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
30 | N/A | DE | SAU4005-G000-___-&ABB-02035 | Weekly Progress Report on 5th September 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-09-08 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
31 | N/A | DE | SAU4005-G000-___-&ABB-02036 | Weekly Progress Report on 12th September 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-09-15 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
32 | N/A | DE | SAU4005-G000-___-&ABB-02037 | Weekly Progress Report on 19th September 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-09-22 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
33 | N/A | DE | SAU4005-G000-___-&ABB-02038 | Weekly Progress Report on 26th September 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-09-29 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
34 | N/A | DE | SAU4005-G000-___-&ABB-02039 | Weekly Progress Report on 3rd October 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-10-06 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
35 | N/A | DE | SAU4005-G000-___-&ABB-02040 | Weekly Progress Report on 10th October 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-10-13 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
36 | N/A | DE | SAU4005-G000-___-&ABB-02041 | Weekly Progress Report on 17th October 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-10-20 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
37 | N/A | DE | SAU4005-G000-___-&ABB-02042 | Weekly Progress Report on 24th October 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-10-27 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
38 | N/A | DE | SAU4005-G000-___-&ABB-02043 | Weekly Progress Report on 31st October 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-11-03 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
39 | N/A | DE | SAU4005-G000-___-&ABB-02044 | Weekly Progress Report on 7th November 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-11-10 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
40 | N/A | DE | SAU4005-G000-___-&ABB-02045 | Weekly Progress Report on 14th November 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-11-17 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
41 | N/A | DE | SAU4005-G000-___-&ABB-02046 | Weekly Progress Report on 21st November 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-11-24 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
42 | N/A | DE | SAU4005-G000-___-&ABB-02047 | Weekly Progress Report on 28th November 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-12-01 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
43 | N/A | DE | SAU4005-G000-___-&ABB-02048 | Weekly Progress Report on 5th December 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-12-08 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
44 | N/A | DE | SAU4005-G000-___-&ABB-02049 | Weekly Progress Report on 12th December 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-12-15 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
45 | N/A | DE | SAU4005-G000-___-&ABB-02050 | Weekly Progress Report on 19th December 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-12-22 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
46 | N/A | DE | SAU4005-G000-___-&ABB-02051 | Weekly Progress Report on 26th December 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-12-29 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
47 | N/A | DE | SAU4005-G000-___-&ABB-02052 | Weekly Progress Report on 2nd January 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-01-05 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
48 | N/A | DE | SAU4005-G000-___-&ABB-02053 | Weekly Progress Report on 9th January 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-01-12 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
49 | N/A | DE | SAU4005-G000-___-&ABB-02054 | Weekly Progress Report on 16th January 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-01-19 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
50 | N/A | DE | SAU4005-G000-___-&ABB-02055 | Weekly Progress Report on 23rd January 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-01-26 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
51 | N/A | DE | SAU4005-G000-___-&ABB-02056 | Weekly Progress Report on 30th January 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-02-02 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
52 | N/A | DE | SAU4005-G000-___-&ABB-02057 | Weekly Progress Report on 6th February 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-02-09 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
53 | N/A | DE | SAU4005-G000-___-&ABB-02058 | Weekly Progress Report on 13th February 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-02-16 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
54 | N/A | DE | SAU4005-G000-___-&ABB-02059 | Weekly Progress Report on 20th February 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-02-23 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
55 | N/A | DE | SAU4005-G000-___-&ABB-02060 | Weekly Progress Report on 27th February 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-03-02 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
56 | N/A | DE | SAU4005-G000-___-&ABB-02061 | Weekly Progress Report on 6th March 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-03-09 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
57 | N/A | DE | SAU4005-G000-___-&ABB-02062 | Weekly Progress Report on 13th March 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-03-16 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
58 | N/A | DE | SAU4005-G000-___-&ABB-02063 | Weekly Progress Report on 20th March 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-03-23 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
59 | N/A | DE | SAU4005-G000-___-&ABB-02064 | Weekly Progress Report on 27th March 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-03-30 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
60 | N/A | DE | SAU4005-G000-___-&ABB-02065 | Weekly Progress Report on 3rd April 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-04-06 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
61 | N/A | DE | SAU4005-G000-___-&ABB-02066 | Weekly Progress Report on 10th April 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-04-13 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
62 | N/A | DE | SAU4005-G000-___-&ABB-02067 | Weekly Progress Report on 17th April 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-04-20 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
63 | N/A | DE | SAU4005-G000-___-&ABB-02068 | Weekly Progress Report on 24th April 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-04-27 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
64 | N/A | DE | SAU4005-G000-___-&ABB-02069 | Weekly Progress Report on 1st May 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-05-04 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
65 | N/A | DE | SAU4005-G000-___-&ABB-02070 | Weekly Progress Report on 8th May 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-05-11 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
66 | N/A | DE | SAU4005-G000-___-&ABB-02071 | Weekly Progress Report on 15th May 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-05-18 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
67 | N/A | DE | SAU4005-G000-___-&ABB-02072 | Weekly Progress Report on 22nd May 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-05-25 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
68 | N/A | DE | SAU4005-G000-___-&ABB-02073 | Weekly Progress Report on 29th May 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-06-01 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
69 | N/A | DE | SAU4005-G000-___-&ABB-02074 | Weekly Progress Report on 5th June 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-06-08 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
70 | N/A | DE | SAU4005-G000-___-&ABB-02075 | Weekly Progress Report on 12th June 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-06-15 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
71 | N/A | DE | SAU4005-G000-___-&ABB-02076 | Weekly Progress Report on 19th June 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-06-22 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
72 | N/A | DE | SAU4005-G000-___-&ABB-02077 | Weekly Progress Report on 26th June 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-06-29 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
73 | N/A | DE | SAU4005-G000-___-&ABB-02078 | Weekly Progress Report on 3rd July 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-07-06 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
74 | N/A | DE | SAU4005-G000-___-&ABB-02079 | Weekly Progress Report on 10th July 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-07-13 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
75 | N/A | DE | SAU4005-G000-___-&ABB-02080 | Weekly Progress Report on 17th July 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-07-20 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
76 | N/A | DE | SAU4005-G000-___-&ABB-02081 | Weekly Progress Report on 24th July 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-07-27 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
77 | N/A | DE | SAU4005-G000-___-&ABB-02082 | Weekly Progress Report on 31st July 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-08-03 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
78 | N/A | DE | SAU4005-G000-___-&ABB-02083 | Weekly Progress Report on 7th August 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-08-10 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
79 | N/A | DE | SAU4005-G000-___-&ABB-02084 | Weekly Progress Report on 14th August 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-08-17 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
80 | N/A | DE | SAU4005-G000-___-&ABB-02085 | Weekly Progress Report on 21st August 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-08-24 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
81 | N/A | DE | SAU4005-G000-___-&ABB-02086 | Weekly Progress Report on 28th August 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-08-31 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
82 | N/A | DE | SAU4005-G000-___-&ABB-02087 | Weekly Progress Report on 4th September 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-09-07 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
83 | N/A | DE | SAU4005-G000-___-&ABB-02088 | Weekly Progress Report on 11th September 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-09-14 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
84 | N/A | DE | SAU4005-G000-___-&ABB-02089 | Weekly Progress Report on 18th September 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-09-21 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
85 | N/A | DE | SAU4005-G000-___-&ABB-02090 | Weekly Progress Report on 25th September 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-09-28 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
86 | N/A | DE | SAU4005-G000-___-&ABB-02091 | Weekly Progress Report on 2nd October 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-10-05 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
87 | N/A | DE | SAU4005-G000-___-&ABB-02092 | Weekly Progress Report on 9th October 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-10-12 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
88 | N/A | DE | SAU4005-G000-___-&ABB-02093 | Weekly Progress Report on 16th October 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-10-19 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
89 | N/A | DE | SAU4005-G000-___-&ABB-02094 | Weekly Progress Report on 23rd October 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-10-26 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
90 | N/A | DE | SAU4005-G000-___-&ABB-02095 | Weekly Progress Report on 30th October 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-11-02 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
91 | N/A | DE | SAU4005-G000-___-&ABB-02096 | Weekly Progress Report on 6th November 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-11-09 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
92 | N/A | DE | SAU4005-G000-___-&ABB-02097 | Weekly Progress Report on 13th November 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-11-16 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
93 | N/A | DE | SAU4005-G000-___-&ABB-02098 | Weekly Progress Report on 20th November 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-11-23 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
94 | N/A | DE | SAU4005-G000-___-&ABB-02099 | Weekly Progress Report on 27th November 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-11-30 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
95 | N/A | DE | SAU4005-G000-___-&ABB-02100 | Weekly Progress Report on 4th December 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-12-07 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
96 | N/A | DE | SAU4005-G000-___-&ABB-02101 | Weekly Progress Report on 11th December 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-12-14 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
97 | N/A | DE | SAU4005-G000-___-&ABB-02102 | Weekly Progress Report on 18th December 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-12-21 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
98 | N/A | DE | SAU4005-G000-___-&ABB-02103 | Weekly Progress Report on 25th December 2026 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2026-12-28 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
99 | N/A | DE | SAU4005-G000-___-&ABB-02104 | Weekly Progress Report on 1st January 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-01-04 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
100 | N/A | DE | SAU4005-G000-___-&ABB-02105 | Weekly Progress Report on 8th January 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-01-11 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
101 | N/A | DE | SAU4005-G000-___-&ABB-02106 | Weekly Progress Report on 15th January 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-01-18 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
102 | N/A | DE | SAU4005-G000-___-&ABB-02107 | Weekly Progress Report on 22nd January 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-01-25 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
103 | N/A | DE | SAU4005-G000-___-&ABB-02108 | Weekly Progress Report on 29th January 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-02-01 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
104 | N/A | DE | SAU4005-G000-___-&ABB-02109 | Weekly Progress Report on 5th February 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-02-08 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
105 | N/A | DE | SAU4005-G000-___-&ABB-02110 | Weekly Progress Report on 12th February 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-02-15 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
106 | N/A | DE | SAU4005-G000-___-&ABB-02111 | Weekly Progress Report on 19th February 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-02-22 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
107 | N/A | DE | SAU4005-G000-___-&ABB-02112 | Weekly Progress Report on 26th February 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-03-01 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
108 | N/A | DE | SAU4005-G000-___-&ABB-02113 | Weekly Progress Report on 5th March 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-03-08 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
109 | N/A | DE | SAU4005-G000-___-&ABB-02114 | Weekly Progress Report on 12th March 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-03-15 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
110 | N/A | DE | SAU4005-G000-___-&ABB-02115 | Weekly Progress Report on 19th March 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-03-22 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
111 | N/A | DE | SAU4005-G000-___-&ABB-02116 | Weekly Progress Report on 26th March 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-03-29 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
112 | N/A | DE | SAU4005-G000-___-&ABB-02117 | Weekly Progress Report on 2nd April 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-04-05 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
113 | N/A | DE | SAU4005-G000-___-&ABB-02118 | Weekly Progress Report on 9th April 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-04-12 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
114 | N/A | DE | SAU4005-G000-___-&ABB-02119 | Weekly Progress Report on 16th April 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-04-19 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
115 | N/A | DE | SAU4005-G000-___-&ABB-02120 | Weekly Progress Report on 23rd April 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-04-26 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
116 | N/A | DE | SAU4005-G000-___-&ABB-02121 | Weekly Progress Report on 30th April 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-05-03 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
117 | N/A | DE | SAU4005-G000-___-&ABB-02122 | Weekly Progress Report on 7th May 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-05-10 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
118 | N/A | DE | SAU4005-G000-___-&ABB-02123 | Weekly Progress Report on 14th May 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-05-17 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
119 | N/A | DE | SAU4005-G000-___-&ABB-02124 | Weekly Progress Report on 21st May 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-05-24 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
120 | N/A | DE | SAU4005-G000-___-&ABB-02125 | Weekly Progress Report on 28th May 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-05-31 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
121 | N/A | DE | SAU4005-G000-___-&ABB-02126 | Weekly Progress Report on 4th June 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-06-07 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
122 | N/A | DE | SAU4005-G000-___-&ABB-02127 | Weekly Progress Report on 11th June 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-06-14 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
123 | N/A | DE | SAU4005-G000-___-&ABB-02128 | Weekly Progress Report on 18th June 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-06-21 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
124 | N/A | DE | SAU4005-G000-___-&ABB-02129 | Weekly Progress Report on 25th June 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-06-28 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
125 | N/A | DE | SAU4005-G000-___-&ABB-02130 | Weekly Progress Report on 2nd July 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-07-05 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
126 | N/A | DE | SAU4005-G000-___-&ABB-02131 | Weekly Progress Report on 9th July 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-07-12 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
127 | N/A | DE | SAU4005-G000-___-&ABB-02132 | Weekly Progress Report on 16th July 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-07-19 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
128 | N/A | DE | SAU4005-G000-___-&ABB-02133 | Weekly Progress Report on 23rd July 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-07-26 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
129 | N/A | DE | SAU4005-G000-___-&ABB-02134 | Weekly Progress Report on 30th July 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-08-02 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
130 | N/A | DE | SAU4005-G000-___-&ABB-02135 | Weekly Progress Report on 6th August 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-08-09 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
131 | N/A | DE | SAU4005-G000-___-&ABB-02136 | Weekly Progress Report on 13th August 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-08-16 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
132 | N/A | DE | SAU4005-G000-___-&ABB-02137 | Weekly Progress Report on 20th August 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-08-23 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
133 | N/A | DE | SAU4005-G000-___-&ABB-02138 | Weekly Progress Report on 27th August 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-08-30 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
134 | N/A | DE | SAU4005-G000-___-&ABB-02139 | Weekly Progress Report on 3rd September 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-09-06 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
135 | N/A | DE | SAU4005-G000-___-&ABB-02140 | Weekly Progress Report on 10th September 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-09-13 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
136 | N/A | DE | SAU4005-G000-___-&ABB-02141 | Weekly Progress Report on 17th September 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-09-20 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
137 | N/A | DE | SAU4005-G000-___-&ABB-02142 | Weekly Progress Report on 24th September 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-09-27 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
138 | N/A | DE | SAU4005-G000-___-&ABB-02143 | Weekly Progress Report on 1st October 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-10-04 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
139 | N/A | DE | SAU4005-G000-___-&ABB-02144 | Weekly Progress Report on 8th October 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-10-11 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
140 | N/A | DE | SAU4005-G000-___-&ABB-02145 | Weekly Progress Report on 15th October 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-10-18 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
141 | N/A | DE | SAU4005-G000-___-&ABB-02146 | Weekly Progress Report on 22nd October 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-10-25 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
142 | N/A | DE | SAU4005-G000-___-&ABB-02147 | Weekly Progress Report on 29th October 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-11-01 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
143 | N/A | DE | SAU4005-G000-___-&ABB-02148 | Weekly Progress Report on 5th November 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-11-08 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
144 | N/A | DE | SAU4005-G000-___-&ABB-02149 | Weekly Progress Report on 12th November 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-11-15 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
145 | N/A | DE | SAU4005-G000-___-&ABB-02150 | Weekly Progress Report on 19th November 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-11-22 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
146 | N/A | DE | SAU4005-G000-___-&ABB-02151 | Weekly Progress Report on 26th November 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-11-29 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
147 | N/A | DE | SAU4005-G000-___-&ABB-02152 | Weekly Progress Report on 3rd December 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-12-06 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
148 | N/A | DE | SAU4005-G000-___-&ABB-02153 | Weekly Progress Report on 10th December 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-12-13 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
149 | N/A | DE | SAU4005-G000-___-&ABB-02154 | Weekly Progress Report on 17th December 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-12-20 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
150 | N/A | DE | SAU4005-G000-___-&ABB-02155 | Weekly Progress Report on 24th December 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2027-12-27 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
151 | N/A | DE | SAU4005-G000-___-&ABB-02156 | Weekly Progress Report on 31st December 2027 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2028-01-03 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
152 | N/A | DE | SAU4005-G000-___-&ABB-02157 | Weekly Progress Report on 7th January 2028 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2028-01-10 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
153 | N/A | DE | SAU4005-G000-___-&ABB-02158 | Weekly Progress Report on 14th January 2028 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2028-01-17 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
154 | N/A | DE | SAU4005-G000-___-&ABB-02159 | Weekly Progress Report on 21st January 2028 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2028-01-24 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
155 | N/A | DE | SAU4005-G000-___-&ABB-02160 | Weekly Progress Report on 28th January 2028 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2028-01-31 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
156 | N/A | DE | SAU4005-G000-___-&ABB-02161 | Weekly Progress Report on 4th February 2028 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2028-02-07 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
157 | N/A | DE | SAU4005-G000-___-&ABB-02162 | Weekly Progress Report on 11th February 2028 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2028-02-14 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
158 | N/A | DE | SAU4005-G000-___-&ABB-02163 | Weekly Progress Report on 18th February 2028 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2028-02-21 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
159 | N/A | DE | SAU4005-G000-___-&ABB-02164 | Weekly Progress Report on 25th February 2028 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2028-02-28 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
160 | N/A | DE | SAU4005-G000-___-&ABB-02165 | Weekly Progress Report on 3rd March 2028 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2028-03-06 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
161 | N/A | DE | SAU4005-G000-___-&ABB-02166 | Weekly Progress Report on 10th March 2028 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2028-03-13 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
162 | N/A | DE | SAU4005-G000-___-&ABB-02167 | Weekly Progress Report on 17th March 2028 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2028-03-20 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
163 | N/A | DE | SAU4005-G000-___-&ABB-02168 | Weekly Progress Report on 24th March 2028 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2028-03-27 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
164 | N/A | DE | SAU4005-G000-___-&ABB-02169 | Weekly Progress Report on 31st March 2028 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2028-04-03 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
165 | N/A | DE | SAU4005-G000-___-&ABB-02170 | Weekly Progress Report on 7th April 2028 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2028-04-10 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
166 | N/A | DE | SAU4005-G000-___-&ABB-02171 | Weekly Progress Report on 14th April 2028 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2028-04-17 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
167 | N/A | DE | SAU4005-G000-___-&ABB-02172 | Weekly Progress Report on 21st April 2028 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2028-04-24 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
168 | N/A | DE | SAU4005-G000-___-&ABB-02173 | Weekly Progress Report on 28th April 2028 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2028-05-01 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
169 | N/A | DE | SAU4005-G000-___-&ABB-02174 | Weekly Progress Report on 5th May 2028 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2028-05-08 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
170 | N/A | DE | SAU4005-G000-___-&ABB-02175 | Weekly Progress Report on 12th May 2028 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2028-05-15 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
171 | N/A | DE | SAU4005-G000-___-&ABB-02176 | Weekly Progress Report on 19th May 2028 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2028-05-22 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
172 | N/A | DE | SAU4005-G000-___-&ABB-02177 | Weekly Progress Report on 26th May 2028 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2028-05-29 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
173 | N/A | DE | SAU4005-G000-___-&ABB-02178 | Weekly Progress Report on 2nd June 2028 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2028-06-05 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
174 | N/A | DE | SAU4005-G000-___-&ABB-02001 | LNTP Monthly Report for January 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-02-05 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
175 | N/A | DE | SAU4005-G000-___-&ABB-02006 | LNTP Monthly Report for February 2025 | A1 | Planning | A-Overall management | No | GENERAL | GENERAL |  | IFI | IFD | [14 empty] | 2025-03-05 | [17 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
176 | N/A | DE | SAU4005-G000-___-&ABB-02011 | Monthly Progress Report in March 2025 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2025-04-05 |  |  |  | 2025-04-25 |  |  |  | 2025-05-31 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
177 | N/A | DE | SAU4005-G000-___-&ABB-02016 | Monthly Progress Report in April 2025 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2025-05-05 |  |  |  | 2025-05-25 |  |  |  | 2025-06-30 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
178 | N/A | DE | SAU4005-G000-___-&ABB-02201 | Monthly Progress Report in May 2025 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2025-06-05 |  |  |  | 2025-06-25 |  |  |  | 2025-07-31 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
179 | N/A | DE | SAU4005-G000-___-&ABB-02202 | Monthly Progress Report in June 2025 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2025-07-05 |  |  |  | 2025-07-25 |  |  |  | 2025-08-30 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
180 | N/A | DE | SAU4005-G000-___-&ABB-02203 | Monthly Progress Report in July 2025 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2025-08-05 |  |  |  | 2025-08-25 |  |  |  | 2025-09-30 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
181 | N/A | DE | SAU4005-G000-___-&ABB-02204 | Monthly Progress Report in August 2025 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2025-09-05 |  |  |  | 2025-09-25 |  |  |  | 2025-10-31 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
182 | N/A | DE | SAU4005-G000-___-&ABB-02205 | Monthly Progress Report in September 2025 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2025-10-05 |  |  |  | 2025-10-25 |  |  |  | 2025-11-30 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
183 | N/A | DE | SAU4005-G000-___-&ABB-02206 | Monthly Progress Report in October 2025 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2025-11-05 |  |  |  | 2025-11-25 |  |  |  | 2025-12-31 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
184 | N/A | DE | SAU4005-G000-___-&ABB-02207 | Monthly Progress Report in November 2025 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2025-12-05 |  |  |  | 2025-12-25 |  |  |  | 2026-01-30 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
185 | N/A | DE | SAU4005-G000-___-&ABB-02208 | Monthly Progress Report in December 2025 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2026-01-05 |  |  |  | 2026-01-25 |  |  |  | 2026-03-02 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
186 | N/A | DE | SAU4005-G000-___-&ABB-02209 | Monthly Progress Report in January 2026 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2026-02-05 |  |  |  | 2026-02-25 |  |  |  | 2026-04-02 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
187 | N/A | DE | SAU4005-G000-___-&ABB-02210 | Monthly Progress Report in February 2026 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2026-03-05 |  |  |  | 2026-03-25 |  |  |  | 2026-04-30 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
188 | N/A | DE | SAU4005-G000-___-&ABB-02211 | Monthly Progress Report in March 2026 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2026-04-05 |  |  |  | 2026-04-25 |  |  |  | 2026-05-31 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
189 | N/A | DE | SAU4005-G000-___-&ABB-02212 | Monthly Progress Report in April 2026 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2026-05-05 |  |  |  | 2026-05-25 |  |  |  | 2026-06-30 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
190 | N/A | DE | SAU4005-G000-___-&ABB-02213 | Monthly Progress Report in May 2026 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2026-06-05 |  |  |  | 2026-06-25 |  |  |  | 2026-07-31 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
191 | N/A | DE | SAU4005-G000-___-&ABB-02214 | Monthly Progress Report in June 2026 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2026-07-05 |  |  |  | 2026-07-25 |  |  |  | 2026-08-30 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
192 | N/A | DE | SAU4005-G000-___-&ABB-02215 | Monthly Progress Report in July 2026 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2026-08-05 |  |  |  | 2026-08-25 |  |  |  | 2026-09-30 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
193 | N/A | DE | SAU4005-G000-___-&ABB-02216 | Monthly Progress Report in August 2026 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2026-09-05 |  |  |  | 2026-09-25 |  |  |  | 2026-10-31 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
194 | N/A | DE | SAU4005-G000-___-&ABB-02217 | Monthly Progress Report in September 2026 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2026-10-05 |  |  |  | 2026-10-25 |  |  |  | 2026-11-30 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
195 | N/A | DE | SAU4005-G000-___-&ABB-02218 | Monthly Progress Report in October 2026 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2026-11-05 |  |  |  | 2026-11-25 |  |  |  | 2026-12-31 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
196 | N/A | DE | SAU4005-G000-___-&ABB-02219 | Monthly Progress Report in November 2026 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2026-12-05 |  |  |  | 2026-12-25 |  |  |  | 2027-01-30 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
197 | N/A | DE | SAU4005-G000-___-&ABB-02220 | Monthly Progress Report in December 2026 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2027-01-05 |  |  |  | 2027-01-25 |  |  |  | 2027-03-02 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
198 | N/A | DE | SAU4005-G000-___-&ABB-02221 | Monthly Progress Report in January 2027 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2027-02-05 |  |  |  | 2027-02-25 |  |  |  | 2027-04-02 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
199 | N/A | DE | SAU4005-G000-___-&ABB-02222 | Monthly Progress Report in February 2027 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2027-03-05 |  |  |  | 2027-03-25 |  |  |  | 2027-04-30 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
200 | N/A | DE | SAU4005-G000-___-&ABB-02223 | Monthly Progress Report in March 2027 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2027-04-05 |  |  |  | 2027-04-25 |  |  |  | 2027-05-31 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
201 | N/A | DE | SAU4005-G000-___-&ABB-02224 | Monthly Progress Report in April 2027 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2027-05-05 |  |  |  | 2027-05-25 |  |  |  | 2027-06-30 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
202 | N/A | DE | SAU4005-G000-___-&ABB-02225 | Monthly Progress Report in May 2027 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2027-06-05 |  |  |  | 2027-06-25 |  |  |  | 2027-07-31 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
203 | N/A | DE | SAU4005-G000-___-&ABB-02226 | Monthly Progress Report in June 2027 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2027-07-05 |  |  |  | 2027-07-25 |  |  |  | 2027-08-30 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
204 | N/A | DE | SAU4005-G000-___-&ABB-02227 | Monthly Progress Report in July 2027 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2027-08-05 |  |  |  | 2027-08-25 |  |  |  | 2027-09-30 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
205 | N/A | DE | SAU4005-G000-___-&ABB-02228 | Monthly Progress Report in August 2027 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2027-09-05 |  |  |  | 2027-09-25 |  |  |  | 2027-10-31 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
206 | N/A | DE | SAU4005-G000-___-&ABB-02229 | Monthly Progress Report in September 2027 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2027-10-05 |  |  |  | 2027-10-25 |  |  |  | 2027-11-30 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
207 | N/A | DE | SAU4005-G000-___-&ABB-02230 | Monthly Progress Report in October 2027 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2027-11-05 |  |  |  | 2027-11-25 |  |  |  | 2027-12-31 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
208 | N/A | DE | SAU4005-G000-___-&ABB-02231 | Monthly Progress Report in November 2027 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2027-12-05 |  |  |  | 2027-12-25 |  |  |  | 2028-01-30 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
209 | N/A | DE | SAU4005-G000-___-&ABB-02232 | Monthly Progress Report in December 2027 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2028-01-05 |  |  |  | 2028-01-25 |  |  |  | 2028-03-01 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
210 | N/A | DE | SAU4005-G000-___-&ABB-02233 | Monthly Progress Report in January 2028 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2028-02-05 |  |  |  | 2028-02-25 |  |  |  | 2028-04-01 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
211 | N/A | DE | SAU4005-G000-___-&ABB-02234 | Monthly Progress Report in February 2028 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2028-03-05 |  |  |  | 2028-03-25 |  |  |  | 2028-04-30 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
212 | N/A | DE | SAU4005-G000-___-&ABB-02235 | Monthly Progress Report in March 2028 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2028-04-05 |  |  |  | 2028-04-25 |  |  |  | 2028-05-31 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
213 | N/A | DE | SAU4005-G000-___-&ABB-02236 | Monthly Progress Report in April 2028 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2028-05-05 |  |  |  | 2028-05-25 |  |  |  | 2028-06-30 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
214 | N/A | DE | SAU4005-G000-___-&ABB-02237 | Monthly Progress Report in May 2028 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2028-06-05 |  |  |  | 2028-06-25 |  |  |  | 2028-07-31 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
215 | N/A | DE | SAU4005-G000-___-&ABB-02238 | Monthly Progress Report in June 2028 | A1 | Project Management | A-Overall management | No | GENERAL | GENERAL |  | IFA | IFD |  |  | 2028-07-05 |  |  |  | 2028-07-25 |  |  |  | 2028-08-30 | [21 empty] | WF Transmittal DI-EPC-ACWA | Yes | Yes | No | No | No
216 | N/A | DE | SAU4005-G000-ZEN-&AQA-02101 | Gas Turbine Package - Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFA | IFP
217 | N/A | DE | SAU4005-G000-ZEN-&AQA-02102 | HRSG- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFA | IFP
218 | N/A | DE | SAU4005-G000-ZEN-&AQA-02103 | Bypass & PRDS- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFA | IFP
219 | N/A | DE | SAU4005-G000-ZEN-&AQA-02104 | BSDG- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
220 | N/A | DE | SAU4005-G000-ZEN-&AQA-02105 | MOV (Butterfly)- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
221 | N/A | DE | SAU4005-G000-ZEN-&AQA-02106 | MOV (Casting & Forging)- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
222 | N/A | DE | SAU4005-G000-ZEN-&AQA-02107 | Safety-Relief Valve- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
223 | N/A | DE | SAU4005-G000-ZEN-&AQA-02108 | Silencer- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
224 | N/A | DE | SAU4005-G000-ZEN-&AQA-02109 | Shop Tank- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
225 | N/A | DE | SAU4005-G000-ZEN-&AQA-02110 | HP/IP BFP - Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFA | IFP
226 | N/A | DE | SAU4005-G000-ZEN-&AQA-02111 | VFD (for HP/IP BFP)- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
227 | N/A | DE | SAU4005-G000-ZEN-&AQA-02112 | CEP- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFA | IFP
228 | N/A | DE | SAU4005-G000-ZEN-&AQA-02113 | Air Cooled Condensate System- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFA | IFP
229 | N/A | DE | SAU4005-G000-ZEN-&AQA-02114 | Atmosphere Flash Tank Drain Pump- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
230 | N/A | DE | SAU4005-G000-ZEN-&AQA-02115 | Piping Spool- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
231 | N/A | DE | SAU4005-G000-ZEN-&AQA-02116 | Small bore Piping - Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
232 | N/A | DE | SAU4005-G000-ZEN-&AQA-02117 | Small bore Fitting- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
233 | N/A | DE | SAU4005-G000-ZEN-&AQA-02118 | Small bore Flange- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
234 | N/A | DE | SAU4005-G000-ZEN-&AQA-02119 | Manual Valve - Casting- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
235 | N/A | DE | SAU4005-G000-ZEN-&AQA-02120 | Manual Valve - Forging- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
236 | N/A | DE | SAU4005-G000-ZEN-&AQA-02121 | Specialty Item - Trap- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
237 | N/A | DE | SAU4005-G000-ZEN-&AQA-02122 | Specialty Item - Strainer- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
238 | N/A | DE | SAU4005-G000-ZEN-&AQA-02123 | Specialty Item - Expansion Joint- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
239 | N/A | DE | SAU4005-G000-ZEN-&AQA-02124 | Hanger & Support- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
240 | N/A | DE | SAU4005-G000-ZEN-&AQA-02125 | Insulation - Mineral wool- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
241 | N/A | DE | SAU4005-G000-ZEN-&AQA-02126 | Insulation - Lagging Material- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
242 | N/A | DE | SAU4005-G000-ZEN-&AQA-02127 | Insulation - Accessory- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
243 | N/A | DE | SAU4005-G000-ZEN-&AQA-02128 | DCS- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
244 | N/A | DE | SAU4005-G000-ZEN-&AQA-02129 | Control valves- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
245 | N/A | DE | SAU4005-G000-ZEN-&AQA-02130 | Process Transmitter- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
246 | N/A | DE | SAU4005-G000-ZEN-&AQA-02131 | Local Instrument- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
247 | N/A | DE | SAU4005-G000-ZEN-&AQA-02132 | Flow element- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
248 | N/A | DE | SAU4005-G000-ZEN-&AQA-02133 | Instrument Installation Material- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
249 | N/A | DE | SAU4005-G000-ZEN-&AQA-02134 | Instrument Rack and Junction Box- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
250 | N/A | DE | SAU4005-G000-ZEN-&AQA-02135 | I&C Cable- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
251 | N/A | DE | SAU4005-G000-ZEN-&AQA-02137 | VMS for BFP- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFI | IFP
252 | N/A | DE | SAU4005-G000-ZEN-&AQA-02138 | Steam Turbine and Generator- Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFA | IFP
253 | N/A | DE | SAU4005-G000-ZEN-&AQA-02139 | Reserve for STG | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFA | IFP
254 | N/A | DE | SAU4005-G000-ZEN-&AQA-02140 | Gas Turbine Generator Package - Inspection Test Plan | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFA | IFP
255 | N/A | DE | SAU4005-G000-ZEN-&AQA-02201 | Gas Turbine and Generator- Factory Test Procedure | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFA | IFP
256 | N/A | DE | SAU4005-G000-ZEN-&AQA-02202 | HRSG- Factory Test Procedure | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFA | IFP
257 | N/A | DE | SAU4005-G000-ZEN-&AQA-02203 | Bypass & PRDS- Factory Test Procedure | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFA | IFP
258 | N/A | DE | SAU4005-G000-ZEN-&AQA-02210 | HP/IP BFP- Factory Test Procedure | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFA | IFP
259 | N/A | DE | SAU4005-G000-ZEN-&AQA-02212 | CEP- Factory Test Procedure | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFA | IFP
260 | N/A | DE | SAU4005-G000-ZEN-&AQA-02213 | Air Cooled Condensate System- Factory Test Procedure | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFA | IFP
261 | N/A | DE | SAU4005-G000-ZEN-&AQA-02238 | Steam Turbine and Generator- Factory Test Procedure | A1 | QAQC | A-Overall management | Yes | Quality Management Documents | Quality |  | IFA | IFP
262 | N/A | DE | SAU4005-G000-ZEN-&AQC-90101 | Gas Turbine and Generator- Notice Of Inspection | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
263 | N/A | DE | SAU4005-G000-ZEN-&AQC-90201 | HRSG- Notice Of Inspection | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
264 | N/A | DE | SAU4005-G000-ZEN-&AQC-90301 | Bypass & PRDS- Notice Of Inspection | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
265 | N/A | DE | SAU4005-G000-ZEN-&AQC-90401 | HP/IP BFP- Notice Of Inspection | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
266 | N/A | DE | SAU4005-G000-ZEN-&AQC-90501 | CEP- Notice Of Inspection | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
267 | N/A | DE | SAU4005-G000-ZEN-&AQC-90601 | Air Cooled Condensate System- Notice Of Inspection | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
268 | N/A | DE | SAU4005-G000-ZEN-&AQC-90701 | Steam Turbine and Generator- Notice Of Inspection | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
269 | N/A | DE | SAU4005-G001-ZEN-&AQC-02101 | Gas Turbine and Generator- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
270 | N/A | DE | SAU4005-G001-ZEN-&AQC-02102 | HRSG- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
271 | N/A | DE | SAU4005-G000-ZEN-&AQC-02103 | Bypass & PRDS- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
272 | N/A | DE | SAU4005-G000-ZEN-&AQC-02104 | BSDG- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
273 | N/A | DE | SAU4005-G000-ZEN-&AQC-02105 | MOV (Butterfly)- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
274 | N/A | DE | SAU4005-G000-ZEN-&AQC-02106 | MOV (Casting & Forging)- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
275 | N/A | DE | SAU4005-G000-ZEN-&AQC-02107 | Safety-Relief Valve- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
276 | N/A | DE | SAU4005-G000-ZEN-&AQC-02108 | Silencer- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
277 | N/A | DE | SAU4005-G000-ZEN-&AQC-02109 | Shop Tank- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
278 | N/A | DE | SAU4005-G000-ZEN-&AQC-02110 | HP/IP BFP - EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
279 | N/A | DE | SAU4005-G000-ZEN-&AQC-02111 | VFD (for HP/IP BFP)- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
280 | N/A | DE | SAU4005-G000-ZEN-&AQC-02112 | CEP- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
281 | N/A | DE | SAU4005-G000-ZEN-&AQC-02113 | Air Cooled Condensate System- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
282 | N/A | DE | SAU4005-G000-ZEN-&AQC-02114 | Atmosphere Flash Tank Drain Pump- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
283 | N/A | DE | SAU4005-G000-ZEN-&AQC-02115 | Piping Spool- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
284 | N/A | DE | SAU4005-G000-ZEN-&AQC-02116 | Small bore Piping - EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
285 | N/A | DE | SAU4005-G000-ZEN-&AQC-02117 | Small bore Fitting- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
286 | N/A | DE | SAU4005-G000-ZEN-&AQC-02118 | Small bore Flange- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
287 | N/A | DE | SAU4005-G000-ZEN-&AQC-02119 | Manual Valve - Casting- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
288 | N/A | DE | SAU4005-G000-ZEN-&AQC-02120 | Manual Valve - Forging- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
289 | N/A | DE | SAU4005-G000-ZEN-&AQC-02121 | Specialty Item - Trap- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
290 | N/A | DE | SAU4005-G000-ZEN-&AQC-02122 | Specialty Item - Strainer- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
291 | N/A | DE | SAU4005-G000-ZEN-&AQC-02123 | Specialty Item - Expansion Joint- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
292 | N/A | DE | SAU4005-G000-ZEN-&AQC-02124 | Hanger & Support- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
293 | N/A | DE | SAU4005-G000-ZEN-&AQC-02125 | Insulation - Mineral wool- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
294 | N/A | DE | SAU4005-G000-ZEN-&AQC-02126 | Insulation - Lagging Material- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
295 | N/A | DE | SAU4005-G000-ZEN-&AQC-02127 | Insulation - Accessory- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
296 | N/A | DE | SAU4005-G000-ZEN-&AQC-02128 | DCS- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
297 | N/A | DE | SAU4005-G000-ZEN-&AQC-02129 | Control valves- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
298 | N/A | DE | SAU4005-G000-ZEN-&AQC-02130 | Process Transmitter- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
299 | N/A | DE | SAU4005-G000-ZEN-&AQC-02131 | Local Instrument- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
300 | N/A | DE | SAU4005-G000-ZEN-&AQC-02132 | Flow element- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
301 | N/A | DE | SAU4005-G000-ZEN-&AQC-02133 | Instrument Installation Material- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
302 | N/A | DE | SAU4005-G000-ZEN-&AQC-02134 | Instrument Rack and Junction Box- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
303 | N/A | DE | SAU4005-G000-ZEN-&AQC-02135 | I&C Cable- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
304 | N/A | DE | SAU4005-G000-ZEN-&AQC-02137 | VMS for BFP- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
305 | N/A | DE | SAU4005-G000-ZEN-&AQC-02138 | Steam Turbine and Generator- EOMR | A1 | QAQC | A-Overall management | Yes | Quality Verfying Documents | Quality |  | IFI | IFP
306 | N/A | S3 | SAU4005-G000-ZEN-&CBG-02500 | MOS For Earth Works | A1 | CIVIL | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
307 | N/A | S3 | SAU4005-G000-ZEN-&CBG-02501 | MOS For Concrete Works | A1 | CIVIL | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
308 | N/A | S3 | SAU4005-G000-ZEN-&CBG-02502 | MOS For Masonry and Block Works | A1 | CIVIL | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
309 | N/A | S3 | SAU4005-G000-ZEN-&CBG-02503 | MOS For Painting Works | A1 | CIVIL | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
310 | N/A | S3 | SAU4005-G000-ZEN-&CBG-02504 | MOS for false ceiling works | A1 | CIVIL | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
311 | N/A | S3 | SAU4005-G000-ZEN-&CBG-02505 | MOS For all kinds of floor works | A1 | CIVIL | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
312 | N/A | S3 | SAU4005-G000-ZEN-&CBG-02506 | MOS For Door And Windows Installation Works | A1 | CIVIL | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
313 | N/A | S3 | SAU4005-G000-ZEN-&CBG-02507 | MOS For roof water-proofing and insulation works | A1 | CIVIL | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
314 | N/A | S3 | SAU4005-G000-ZEN-&CBG-02508 | MOS For Construction Of Road Works | A1 | CIVIL | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
315 | N/A | S3 | SAU4005-G000-ZEN-&CBG-02509 | MOS For Fence Installation Works | A1 | CIVIL | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
316 | N/A | S3 | SAU4005-G000-ZEN-&CBG-02510 | MOS for underground pipeline work | A1 | CIVIL | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
317 | N/A | S3 | SAU4005-G000-ZEN-&CBG-02511 | MOS for evaporation ponds work | A1 | CIVIL | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
318 | N/A | S3 | SAU4005-G000-ZEN-&EBG-02500 | Method Statement For Instrument Installation | A1 | E&I | E-Electrotechnology (including control, information and communication techniques) |  |  |  |  | IFI | IFC
319 | N/A | S3 | SAU4005-G000-ZEN-&EBG-02501 | Method Statement For Instrument Testing and Loop checking during commissioning | A1 | E&I | E-Electrotechnology (including control, information and communication techniques) |  |  |  |  | IFI | IFC
320 | N/A | S3 | SAU4005-G000-ZEN-&EBG-02502 | Method Statement for heat tracing cable installation | A1 | E&I | E-Electrotechnology (including control, information and communication techniques) |  |  |  |  | IFI | IFC
321 | N/A | S3 | SAU4005-G000-ZEN-&EBG-02503 | Method Statement For Junction Box, Cabinet and Panel Installation | A1 | E&I | E-Electrotechnology (including control, information and communication techniques) |  |  |  |  | IFI | IFC
322 | N/A | S3 | SAU4005-G000-ZEN-&EBG-02504 | Method Statement For Instrument Tubing Installation | A1 | E&I | E-Electrotechnology (including control, information and communication techniques) |  |  |  |  | IFI | IFC
323 | N/A | S3 | SAU4005-G000-ZEN-&EBG-02505 | Method statement for inspection and commissioning fire fighting system | A1 | E&I | E-Electrotechnology (including control, information and communication techniques) |  |  |  |  | IFI | IFC
324 | N/A | S3 | SAU4005-G000-ZEN-&EBG-02506 | Method Statement For CCTV & Access Control System device Installation | A1 | E&I | E-Electrotechnology (including control, information and communication techniques) |  |  |  |  | IFI | IFC
325 | N/A | S3 | SAU4005-G000-ZEN-&EBG-02507 | Method Statement For I&C Cable Pulling And Termination | A1 | E&I | E-Electrotechnology (including control, information and communication techniques) |  |  |  |  | IFI | IFC
326 | N/A | S3 | SAU4005-G000-ZEN-&EBG-02508 | Method Statement For I&C cable conduit and cable tray installation | A1 | E&I | E-Electrotechnology (including control, information and communication techniques) |  |  |  |  | IFI | IFC
327 | N/A | S3 | SAU4005-G000-ZEN-&EBG-02509 | Method Statement For I&C Fireproof sealing | A1 | E&I | E-Electrotechnology (including control, information and communication techniques) |  |  |  |  | IFI | IFC
328 | N/A | S3 | SAU4005-G000-ZEN-&CBG-02511 | Method Statement For Steel Structure Erection | A1 | machinery | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
329 | N/A | S3 | SAU4005-G000-ZEN-&CBG-02512 | Method Statement For Installation Crane And Hoist | A1 | machinery | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
330 | N/A | S3 | SAU4005-G000-ZEN-&CBG-02513 | Method Statement For Roof And Wall Cladding Installation | A1 | machinery | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
331 | N/A | S3 | SAU4005-G000-ZEN-&CBG-02514 | Method Statement For TransFormer Unload In Place | A1 | machinery | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
332 | N/A | S3 | SAU4005-G000-ZEN-&MBG-02500 | Method Statement For HRSG installation | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
333 | N/A | S3 | SAU4005-G000-ZEN-&MBG-02501 | Method Statement For Bypass stack installation | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
334 | N/A | S3 | SAU4005-G000-ZEN-&MBG-02502 | Method Statement For GT&GTG and Auxiliary module installation | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
335 | N/A | S3 | SAU4005-G000-ZEN-&MBG-02503 | Method Statement For For Static equipment installation | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
336 | N/A | S3 | SAU4005-G000-ZEN-&MBG-02504 | Method Statement For Piping installation (Including hydro/pneumatic test and flushing/blowing ) | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
337 | N/A | S3 | SAU4005-G000-ZEN-&MBG-02505 | Method Statement For Rotating equipment installation | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
338 | N/A | S3 | SAU4005-G000-ZEN-&MBG-02506 | Method Statement For ACC installation | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
339 | N/A | S3 | SAU4005-G000-ZEN-&MBG-02507 | Method Statement For ST&STG and Auxiliary module installation | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
340 | N/A | S3 | SAU4005-G000-ZEN-&MBG-02508 | Method Statement For GRP piping installation | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
341 | N/A | S3 | SAU4005-G000-ZEN-&MBG-02509 | Method Statement For PVC/CPVC/UPVC/HDPE pipe installation | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
342 | N/A | S3 | SAU4005-G000-ZEN-&MBG-02510 | Method Statement For GT&GTG oil system flushing | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
343 | N/A | S3 | SAU4005-G000-ZEN-&MBG-02511 | Method Statement For ST&STG Lube oil system flushing | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
344 | N/A | S3 | SAU4005-G000-ZEN-&MBG-02512 | Method Statement For ST Hydraulic oil system flushing | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
345 | N/A | S3 | SAU4005-G000-ZEN-&MBG-02513 | Method Statement For BFWP oil system flushing | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
346 | N/A | S3 | SAU4005-G000-ZEN-&MBG-02514 | Method Statement For Tank Installation | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
347 | N/A | S3 | SAU4005-G000-ZEN-&MBG-02515 | Method Statement For Fire Fighting system installation | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
348 | N/A | S3 | SAU4005-G000-ZEN-&MBG-02516 | Method Statement For HRSG pressure test | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
349 | N/A | S3 | SAU4005-G000-ZEN-&MBG-02517 | Method Statement For HRSG chemical cleaning and blowing | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
350 | N/A | S3 | SAU4005-G000-ZEN-&MBG-02518 | Method Statement For GT&GTG Lifting Work | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
351 | N/A | S3 | SAU4005-G000-ZEN-&MBG-02519 | Method Statement For ST&STG Lifting Work | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
352 | N/A | S3 | SAU4005-G000-ZEN-&MBG-02520 | Method Statement For Painting and Coating Work | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
353 | N/A | S3 | SAU4005-G000-ZEN-&MBG-02521 | Method Statement For Insulation and Cladding work | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
354 | N/A | S3 | SAU4005-G000-ZEN-&MBG-02522 | Method Statement For STG Insulation and Cladding work | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
355 | N/A | S3 | SAU4005-G000-ZEN-&MBG-02523 | Method Statement For Steam Blow | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
356 | N/A | S3 | SAU4005-G000-ZEN-&CQA-02500 | ITP For Earth Works | A1 | Civil | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
357 | N/A | S3 | SAU4005-G000-ZEN-&CQA-02501 | ITP For Concrete Works | A1 | Civil | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
358 | N/A | S3 | SAU4005-G000-ZEN-&CQA-02502 | The ITP For Masonry and Block Works | A1 | Civil | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
359 | N/A | S3 | SAU4005-G000-ZEN-&CQA-02503 | ITP For Painting Works | A1 | Civil | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
360 | N/A | S3 | SAU4005-G000-ZEN-&CQA-02504 | ITP for false ceiling works | A1 | Civil | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
361 | N/A | S3 | SAU4005-G000-ZEN-&CQA-02505 | ITP For all kinds of floor works | A1 | Civil | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
362 | N/A | S3 | SAU4005-G000-ZEN-&CQA-02506 | ITP For Door And Windows Installation Works | A1 | Civil | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
363 | N/A | S3 | SAU4005-G000-ZEN-&CQA-02507 | ITP For roof water-proofing and insulation works | A1 | Civil | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
364 | N/A | S3 | SAU4005-G000-ZEN-&CQA-02508 | ITP For Construction Of Road Works | A1 | Civil | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
365 | N/A | S3 | SAU4005-G000-ZEN-&CQA-02509 | ITP For Fence Installation Works | A1 | Civil | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
366 | N/A | S3 | SAU4005-G000-ZEN-&CQA-02510 | ITP for underground pipeline work | A1 | Civil | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
367 | N/A | S3 | SAU4005-G000-ZEN-&CQA-02511 | ITP for evaporation ponds work | A1 | Civil | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
368 | N/A | S3 | SAU4005-G000-ZEN-&EQA-02500 | ITP For 380kV cable laying and termination | A1 | E&I | E-Electrotechnology (including control, information and communication techniques) |  |  |  |  | IFI | IFC
369 | N/A | S3 | SAU4005-G000-ZEN-&EQA-02501 | ITP For HV transFormer installation | A1 | E&I | E-Electrotechnology (including control, information and communication techniques) |  |  |  |  | IFI | IFC
370 | N/A | S3 | SAU4005-G000-ZEN-&EQA-02502 | ITP For Generator &GCB & IPB installation | A1 | E&I | E-Electrotechnology (including control, information and communication techniques) |  |  |  |  | IFI | IFC
371 | N/A | S3 | SAU4005-G000-ZEN-&EQA-02503 | ITP For Electrical and Instrument panel installation | A1 | E&I | E-Electrotechnology (including control, information and communication techniques) |  |  |  |  | IFI | IFC
372 | N/A | S3 | SAU4005-G000-ZEN-&EQA-02504 | ITP For UPS&DC&Battery installation | A1 | E&I | E-Electrotechnology (including control, information and communication techniques) |  |  |  |  | IFI | IFC
373 | N/A | S3 | SAU4005-G000-ZEN-&EQA-02505 | ITP For MV/LV transFormer installation | A1 | E&I | E-Electrotechnology (including control, information and communication techniques) |  |  |  |  | IFI | IFC
374 | N/A | S3 | SAU4005-G000-ZEN-&EQA-02506 | ITP For Lighting and small power installation | A1 | E&I | E-Electrotechnology (including control, information and communication techniques) |  |  |  |  | IFI | IFC
375 | N/A | S3 | SAU4005-G000-ZEN-&EQA-02507 | ITP For Cable tray and conduit installation | A1 | E&I | E-Electrotechnology (including control, information and communication techniques) |  |  |  |  | IFI | IFC
376 | N/A | S3 | SAU4005-G000-ZEN-&EQA-02508 | ITP For Electrical and Instrument cable laying and termination | A1 | E&I | E-Electrotechnology (including control, information and communication techniques) |  |  |  |  | IFI | IFC
377 | N/A | S3 | SAU4005-G000-ZEN-&EQA-02509 | ITP For Grounding & Lightning protection system Installation | A1 | E&I | E-Electrotechnology (including control, information and communication techniques) |  |  |  |  | IFI | IFC
378 | N/A | S3 | SAU4005-G000-ZEN-&EQA-02510 | ITP For Catholic protection system installation | A1 | E&I | E-Electrotechnology (including control, information and communication techniques) |  |  |  |  | IFI | IFC
379 | N/A | S3 | SAU4005-G000-ZEN-&EQA-02511 | ITP For DCS Energyed | A1 | E&I | E-Electrotechnology (including control, information and communication techniques) |  |  |  |  | IFI | IFC
380 | N/A | S3 | SAU4005-G000-ZEN-&EQA-02512 | ITP For Installation of Instrument Piping | A1 | E&I | E-Electrotechnology (including control, information and communication techniques) |  |  |  |  | IFI | IFC
381 | N/A | S3 | SAU4005-G000-ZEN-&EQA-02513 | ITP For Instrument installation | A1 | E&I | E-Electrotechnology (including control, information and communication techniques) |  |  |  |  | IFI | IFC
382 | N/A | S3 | SAU4005-G000-ZEN-&EQA-02514 | ITP For instrument calibration | A1 | E&I | E-Electrotechnology (including control, information and communication techniques) |  |  |  |  | IFI | IFC
383 | N/A | S3 | SAU4005-G000-ZEN-&EQA-02515 | ITP For HVAC | A1 | E&I | E-Electrotechnology (including control, information and communication techniques) |  |  |  |  | IFI | IFC
384 | N/A | S3 | SAU4005-G000-ZEN-&EQA-02516 | ITP For Loopcheck | A1 | E&I | E-Electrotechnology (including control, information and communication techniques) |  |  |  |  | IFI | IFC
385 | N/A | S3 | SAU4005-G000-ZEN-&MQA-02500 | ITP For HRSG installation and pressure test | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
386 | N/A | S3 | SAU4005-G000-ZEN-&MQA-02501 | ITP For By pass stack installation | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
387 | N/A | S3 | SAU4005-G000-ZEN-&MQA-02502 | ITP For GT&GTG and Auxiliary Module installation | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
388 | N/A | S3 | SAU4005-G000-ZEN-&MQA-02503 | ITP For Static equipment installation | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
389 | N/A | S3 | SAU4005-G000-ZEN-&MQA-02504 | ITP For Piping installation (Including hydro/pneumatic test and flushing/blowing ) | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
390 | N/A | S3 | SAU4005-G000-ZEN-&MQA-02505 | ITP For Rotating equipment installation | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
391 | N/A | S3 | SAU4005-G000-ZEN-&MQA-02506 | ITP For ACC installation | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
392 | N/A | S3 | SAU4005-G000-ZEN-&MQA-02507 | ITP For ST&STG and Auxiliary module installation | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
393 | N/A | S3 | SAU4005-G000-ZEN-&MQA-02508 | ITP For GRP piping installation | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
394 | N/A | S3 | SAU4005-G000-ZEN-&MQA-02509 | ITP For PVC/CPVC/UPVC/HDPE pipe installation | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
395 | N/A | S3 | SAU4005-G000-ZEN-&MQA-02510 | ITP For Tank installation | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
396 | N/A | S3 | SAU4005-G000-ZEN-&MQA-02511 | ITP For Fire Fighting system installation | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
397 | N/A | S3 | SAU4005-G000-ZEN-&MQA-02512 | ITP For HRSG chemical cleaning and blowing | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
398 | N/A | S3 | SAU4005-G000-ZEN-&MQA-02513 | ITP For Painting and Coating | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
399 | N/A | S3 | SAU4005-G000-ZEN-&MQA-02514 | ITP For Insulation and Cladding | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
400 | N/A | S3 | SAU4005-G000-ZEN-&CQA-02512 | ITP For Steel Structure Erection | A1 | Civil | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
401 | N/A | S3 | SAU4005-G000-ZEN-&MQA-02515 | ITP For Cranes And Hoists Erection | A1 | Mechanical | M-Mechanical engineering (normally including process engineering) |  |  |  |  | IFI | IFC
402 | N/A | S3 | SAU4005-G000-ZEN-&CQA-02513 | ITP For Cladding Installation | A1 | Civil | C-Construction engineering (building construction and civil engineering) |  |  |  |  | IFI | IFC
403 | N/A | S3 | SAU4005-G000-___-&AAC-02001 | Project Management Plan | A1 | Construction | A-Overall management |  |  |  |  | IFI | IFD
404 | N/A | S3 | SAU4005-G000-___-&AQA-02501 | Project Quality Management Plan | A1 | QA/QC | A-Overall management |  |  |  |  | IFI | IFD
405 | N/A | S3 |  | Project Design Management Plan | A1 | Engineering | [5 empty] | IFI | IFD
406 | N/A | S3 | SAU4005-G000-___-&AAC-02503 | Project Coordination Plan | A1 | Construction | A-Overall management |  |  |  |  | IFI | IFD
407 | N/A | S3 | SAU4005-G000-___-&AAC-02504 | Project Procurement and Subcontracting Management Plan | A1 | Logistics | A-Overall management |  |  |  |  | IFI | IFD
408 | N/A | S3 | SAU4005-G000-___-&ABF-02004 | Project Logistics and Traffic Management Plan | A1 | Logistics | A-Overall management |  |  |  |  | IFI | IFD
409 | N/A | S3 | SAU4005-G000-___-&AAC-02505 | Project Employee and Industrial Relations Management Plan | A1 | Admin&HR | A-Overall management |  |  |  |  | IFI | IFD
410 | N/A | S3 | SAU4005-G000-___-&ABD-00003 | Project communication and Document Management Plan (Think Project) | A1 | QA/QC | A-Overall management |  |  |  |  | IFI | IFD
411 | N/A | S3 | SAU4005-G000-___-&AAC-02501 | Project Control Management Plan | A1 | Construction | A-Overall management |  |  |  |  | IFI | IFD
412 | N/A | S3 | SAU4005-G000-___-&AAC-02506 | Project Stakeholder Management Plan | A1 | Admin&HR | A-Overall management |  |  |  |  | IFI | IFD
413 | N/A | S3 | SAU4005-G000-___-&AAC-02500 | Project Construction Management Plan | A1 | Construction | A-Overall management |  |  |  |  | IFI | IFD
414 | N/A | S3 | SAU4005-G000-___-&AAC-02502 | Project Completion Management Plan | A1 | Construction | A-Overall management |  |  |  |  | IFI | IFD
415 | N/A | S3 | SAU4005-G000-___-&AAC-02507 | Risk management plan | A1 | Commercial | A-Overall management |  |  |  |  | IFI | IFD
416 | N/A | S3 | SAU4005-G000-___-&AAC-02508 | Transportation management plan | A1 | Admin&HR | A-Overall management |  |  |  |  | IFI | IFD
417 | N/A | S3 | SAU4005-G000-___-&ABB-00010 | ENGINEERING & DESIGN MANAGEMENT PLAN | A1 | Engineering | A-Overall management |  |  |  |  | IFI | IFD
418 | N/A | S3 | SAU4005-G000-___-&AEA-02503 | Construction Environmental And Social Management Plan | A1 | HSE | A-Overall management |  |  |  |  | IFI | IFD
419 | N/A | S3 | SAU4005-G000-___-&ABD-02500 | Project Communication Procedure | A1 | QA/QC | A-Overall management |  |  |  |  | IFI | IFC
420 | N/A | S3 | SAU4005-G000-___-&AQA-02502 | Non Conformance Procedure | A1 | QA/QC | A-Overall management |  |  |  |  | IFI | IFC
421 | N/A | S3 | SAU4005-G000-___-&AAC-02024 | Draft Local Content Plan | A1 | Commercial | A-Overall management |  |  |  |  | IFI | IFC
422 | N/A | S3 | SAU4005-G000-___-&ABA-02025 | The updated list of Subcontractors and [Major Equipment] suppliers | A1 | Commercial | A-Overall management |  |  |  |  | IFI | IFC
423 | N/A | S3 | SAU4005-G000-___-&ABB-02006 | Turnover to Owner Plan (Owner’s construction site facilities) | A1 | Construction | A-Overall management |  |  |  |  | IFI | IFC
424 | N/A | S3 | SAU4005-G000-___-&ABG-02001 | Health, Safety and Environmental Plan | A1 | HSE | A-Overall management |  |  |  |  | IFI | IFC
425 | N/A | S3 | SAU4005-G000-___-&ABG-02002 | Permit To Work Procedure | A1 | HSE | A-Overall management |  |  |  |  | IFI | IFC
426 | N/A | S3 | SAU4005-G000-___-&ABG-02005 | Colour Code Procedure | A1 | HSE | A-Overall management |  |  |  |  | IFI | IFC
427 | N/A | S3 | SAU4005-G000-___-&ABF-02027 | Reception, Handling and Storing of materials and equipment plan | A1 | Logistics | A-Overall management |  |  |  |  | IFI | IFC
428 | N/A | S3 | SAU4005-G000-___-&AQA-02503 | System Audit and Supervision Management Procedure | A1 | QA/QC | A-Overall management |  |  |  |  | IFI | IFC
429 | N/A | S3 | SAU4005-G000-___-&AQA-02504 | Site inspection and test plan procedure | A1 | QA/QC | A-Overall management |  |  |  |  | IFI | IFC
430 | N/A | S3 | SAU4005-G000-___-&AQA-02505 | Project Punch list Procedure | A1 | QA/QC | A-Overall management |  |  |  |  | IFI | IFC
431 | N/A | S3 | SAU4005-G000-___-&ABG-02503 | Chance Find Procedure | A1 | HSE | A-Overall management |  |  |  |  | IFI | IFC
432 | N/A | S3 | SAU4005-G000-___-&ABG-02504 | Hand and Power Tools Procedure | A1 | HSE | A-Overall management |  |  |  |  | IFI | IFC
433 | N/A | S3 | SAU4005-G000-___-&ABG-02506 | Hearing Conservation Procedure | A1 | HSE | A-Overall management |  |  |  |  | IFI | IFC
434 | N/A | S3 | SAU4005-G000-___-&ABG-02507 | Hot Work Procedure | A1 | HSE | A-Overall management |  |  |  |  | IFI | IFC
435 | N/A | S3 | SAU4005-G000-___-&ABG-02509 | Working at Height Procedure | A1 | HSE | A-Overall management |  |  |  |  | IFI | IFC
436 | N/A | S3 | SAU4005-G000-___-&ABS-02502 | Emergency Response Plan | A1 | HSE | A-Overall management |  |  |  |  | IFI | IFC
437 | N/A | S3 | SAU4005-G000-___-&AQA-02506 | Project Quality objectives KPI's | A1 | QA/QC | A-Overall management |  |  |  |  | IFI | IFC
438 | N/A | S3 | SAU4005-G000-___-&ABS-02503 | Spill Prevention And Emergency Preparedness Plan | A1 | HSE | A-Overall management |  |  |  |  | IFI | IFC
439 | N/A | S3 | SAU4005-G000-___-&ABS-02504 | Fire Prevention and Protection Procedure | A1 | HSE | A-Overall management |  |  |  |  | IFI | IFC
440 | N/A | S3 | SAU4005-G000-___-&ABT-02501 | HSE Training Awareness Competence Procedure | A1 | HSE | A-Overall management |  |  |  |  | IFI | IFC
441 | N/A | S3 | SAU4005-G000-___-&AEA-02501 | HSE Discipline Procedure | A1 | HSE | A-Overall management |  |  |  |  | IFI | IFC
442 | N/A | S3 | SAU4005-G000-___-&ABH-02091 | Field Design Change Management Procedure | A1 | Construction | A-Overall management |  |  |  |  | IFI | IFC
443 | N/A | S3 | SAU4005-G000-___-&AQA-02507 | Welding Material Quality Control Procedure | A1 | Welding | A-Overall management |  |  |  |  | IFI | IFC
444 | N/A | S3 | SAU4005-G000-___-&AQA-02508 | Welder Test Management Procedure | A1 | Welding | A-Overall management |  |  |  |  | IFI | IFC
445 | N/A | S3 | SAU4005-G000-___-&AQA-02509 | Welding Quality control Procedure | A1 | Welding | A-Overall management |  |  |  |  | IFI | IFC
446 | N/A | S3 | SAU4005-G000-___-&AQA-02510 | Welder Test Management Procedure | A1 | Welding | A-Overall management |  |  |  |  | IFI | IFC
447 | N/A | S3 | SAU4005-G000-___-&AQA-02511 | Heat Treatment Control Procedure | A1 | Welding | A-Overall management |  |  |  |  | IFI | IFC
448 | N/A | S3 | SAU4005-G000-___-&AQA-02512 | Welding Repair quanlity control procedure | A1 | Welding | A-Overall management |  |  |  |  | IFI | IFC
449 | N/A | S3 | SAU4005-G000-___-&AQA-02513 | Visual Examination Control Procedure | A1 | Welding | A-Overall management |  |  |  |  | IFI | IFC
450 | N/A | S3 | SAU4005-G000-___-&AQA-02100 | Project Quality Plan For GT & GTG Installation | A1 | Mechanical | A-Overall management |  |  |  |  | IFI | IFC
451 | N/A | S3 | SAU4005-G000-___-&AEA-02502 | Behavioural Safety Procedure | A1 | HSE | A-Overall management |  |  |  |  | IFI | IFC
452 | N/A | S3 | SAU4005-G000-___-&AEA-02504 | Legal Compliance Procedure | A1 | HSE | A-Overall management |  |  |  |  | IFI | IFC
453 | N/A | S3 | SAU4005-G000-___-&ALB-02501 | Excavation and Trenching Procedure | A1 | HSE | A-Overall management |  |  |  |  | IFI | IFC
454 | N/A | S3 | SAU4005-G000-___-&AQB-02501 | Risk Assessment Procedure | A1 | HSE | A-Overall management |  |  |  |  | IFI | IFC
455 | N/A | S3 | SAU4005-G000-___-&AQB-02502 | Grievance Procedure | A1 | HSE | A-Overall management |  |  |  |  | IFI | IFC
456 | N/A | S3 | SAU4005-G000-___-&AQB-02503 | Health Safety Security & Environment Risk Register | A1 | HSE | A-Overall management |  |  |  |  | IFI | IFC
457 | N/A | S3 | SAU4005-G000-___-&AQB-02504 | HSE Audit Procedure | A1 | HSE | A-Overall management |  |  |  |  | IFI | IFC
458 | N/A | S3 | SAU4005-G000-___-&AQB-02505 | HSE Document Recordkeeping | A1 | HSE | A-Overall management |  |  |  |  | IFI | IFC
459 | N/A | S3 | SAU4005-G000-___-&AQB-02506 | HSE Meeting Procedure | A1 | HSE | A-Overall management |  |  |  |  | IFI | IFC
460 | N/A | S3 | SAU4005-G000-___-&AQB-02507 | Lifting and Rigging Equipment Procedure | A1 | HSE | A-Overall management |  |  |  |  | IFI | IFC
461 | N/A | S3 | SAU4005-G000-___-&AQB-02509 | Temporary Electrical Work Procedure | A1 | HSE | A-Overall management |  |  |  |  | IFI | IFC
462 | N/A | S3 | SAU4005-G000-___-&AQB-02510 | Warehouse HSE Procedure | A1 | HSE | A-Overall management |  |  |  |  | IFI | IFC
463 | N/A | S3 | SAU4005-G000-___-&AQB-02511 | Accident Reporting & Investigation Procedure | A1 | HSE | A-Overall management |  |  |  |  | IFI | IFC
464 | LATER | DE(STG) | SAU4005-G010-MAA-&MDC-04223 | ST(V) - PACKING PROCEDURE FOR STG | A1 | LOGISTICS | M-Mechanical engineering (normally including process engineering) | YES | LOGISTICS |  |  | IFI | IFD | [30 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO
465 | LATER | DE(STG) | SAU4005-G010-MKA-&MTL-04104 | ST(V) - SHIPPING DIMENSIONS - GENERATOR STATOR | A1 | LOGISTICS | M-Mechanical engineering (normally including process engineering) | YES | LOGISTICS |  |  | IFI | IFC | [14 empty] | 2026-01-15 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO
466 | LATER | DE(STG) | SAU4005-G010-MKA-&MTL-04106 | ST(V) - SHIPPING DIMENSIONS - GENERATOR ROTOR | A1 | LOGISTICS | M-Mechanical engineering (normally including process engineering) | YES | LOGISTICS |  |  | IFI | IFC | [14 empty] | 2026-01-15 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO
467 | LATER | DE(STG) | SAU4005-G010-MAA-&MDC-04114 | ST(V) - ERECTION MANUAL - STEAM TURBINE | A1 | CONSTRUCTION | M-Mechanical engineering (normally including process engineering) | YES | CONSTRUCTION |  |  | IFI | IFC | [14 empty] | 2026-06-04 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO
468 | LATER | DE(STG) | SAU4005-G010-MKA-&MDC-04115 | ST(V) - ERECTION MANUAL - GENERATOR | A1 | CONSTRUCTION | M-Mechanical engineering (normally including process engineering) | YES | CONSTRUCTION |  |  | IFI | IFC | [14 empty] | 2026-06-04 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO
469 | LATER | DE(STG) | SAU4005-G010-MAA-&MPC-04217 | ST(V) - SPECIAL TOOL LIST FOR STG AND AUXILIARIES | A1 | Procurement | M-Mechanical engineering (normally including process engineering) | YES | PROCUREMENT |  |  | IFA | IFD |  |  | 2026-07-02 |  |  |  | 2026-07-22 |  |  |  | 2026-08-27 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO
470 | LATER | DE(STG) | SAU4005-G010-MAA-&ABA-04213 | ST(V) - SUB-VENDOR LIST | A1 | Procurement | A-Overall management | YES | PROCUREMENT |  |  | IFI | IFD | [14 empty] | 2026-07-30 | [15 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO
471 | LATER | DE(STG) | SAU4005-G010-MAA-&MPB-04214 | ST(V) - START-UP SPARE PARTS LIST FOR STG AND AUXILIARIES | A1 | Procurement | M-Mechanical engineering (normally including process engineering) | YES | PROCUREMENT |  |  | IFA | IFD |  |  | 2026-07-02 |  |  |  | 2026-07-22 |  |  |  | 2026-08-27 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO
472 | LATER | DE(STG) | SAU4005-G010-MAA-&MPB-04215 | ST(V) - MANDATORY SPARE PARTS LIST FOR STG AND AUXILIARIES | A1 | Procurement | M-Mechanical engineering (normally including process engineering) | YES | PROCUREMENT |  |  | IFA | IFD |  |  | 2026-07-02 |  |  |  | 2026-07-22 |  |  |  | 2026-08-27 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO
473 | LATER | DE(STG) | SAU4005-G010-MAA-&MPB-04216 | ST(V) - RECOMMENDED SPARE PARTS LIST FOR STG AND AUXILIARIES | A1 | Procurement | M-Mechanical engineering (normally including process engineering) | YES | PROCUREMENT |  |  | IFA | IFD |  |  | 2026-10-01 |  |  |  | 2026-10-21 |  |  |  | 2026-11-26 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO

## KPIs
Engineering Progress Overview KPI's
|  |  |  | Issue For Approval (IFA) | [13 empty] | IFI |  |  |  | OVERALL
| Area | Plant | Discipline | Plan first Issue for Approval (BASELINE ) | Actual first submitted for Approval | Variance (Submitted) | Plan Approved AWC (BASELINE ) | AWC Actual | Variance (Approved) | Plan FINAL APPROVAL (BASELINE) | Actual FINAL APPROVAL | UNDER REVIEW | REJECTED | SUBMITTAL PENDING | RESPONSE PENDING FROM OWNER | RESPONSE PENDING FROM EPC | Total Documents | Plan Submitted (BASELINE SCHEDULE) | SUBMITTED | Variance (Submitted) | Total Documents | Plan Submitted (BASELINE SCHEDULE) | SUBMITTED | Variance (Submitted) | Total Documents
|  | RO (A001) | CIV | 32 | 22 | -10 | 11 | 6 | -5 | 8 |  | 1 | 6 | 0 | 1 | 14 | 305 | 8 | 8 | 0 | 8 | 40 | 30 | -10 | 313
|  |  | ELE | 22 | 7 | -15 | 12 | 2 | -10 | 2 | 1 | 0 | 2 | 0 | 0 | 4 | 87 | 20 | 13 | -7 | 50 | 42 | 20 | -22 | 137
|  |  | GEN | 10 | 10 | 0 | 7 | 1 | -6 | 8 | 0 | 0 | 1 | 0 | 0 | 9 | 15 | 2 | 2 | 0 | 3 | 12 | 12 | 0 | 18
|  |  | HYD | 7 | 2 | -5 | 2 | 0 | -2 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 9 | 0 | 0 | 0 | 0 | 7 | 2 | -5 | 9
|  |  | I&C | 5 | 0 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 2 | 0 | -2 | 7 | 7 | 0 | -7 | 24
|  |  | MEC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 16 | 1 | 33 | 15 | 16 | 1 | 33
|  |  | PIP | 6 | 5 | -1 | 6 | 0 | -6 | 2 | 0 | 0 | 3 | 0 | 0 | 5 | 18 | 5 | 4 | -1 | 10 | 11 | 9 | -2 | 28
|  |  | PRO | 21 | 17 | -4 | 13 | 0 | -13 | 6 | 0 | 4 | 7 | 0 | 4 | 13 | 21 | 1 | 1 | 0 | 2 | 22 | 18 | -4 | 23
|  |  | 3D Model | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 4
|  |  | FF | 4 | 0 | -4 | 1 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 6 | 4 | 0 | -4 | 10
|  |  | HVAC | 4 | 2 | -2 | 2 | 0 | -2 | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 4 | 1 | 1 | 0 | 1 | 5 | 3 | -2 | 5
|  |  | TOTAL - RO Plant | 113 | 67 | -46 | 54 | 10 | -14 | 28 | 2 | 7 | 20 | 0 | 7 | 48 | 484 | 54 | 45 | -9 | 120 | 167 | 112 | -55 | 604
|  | PV (G00x) | CIV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17
|  |  | ELE | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 27 | 0 | 0 | 0 | 15 | 0 | 1 | 1 | 42
|  |  | GEN | 1 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | -1 | 2
|  |  | I&C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 15
|  |  | MEC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 12
|  |  | TOTAL - PV Plant | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 65 | 0 | 0 | 0 | 23 | 1 | 1 | 0 | 88
|  | Marine ( | CIV | 16 | 14 | -2 | 9 | 0 | -4 | 4 | 1 | 4 | 5 | 0 | 4 | 9 | 17 | 0 | 0 | 0 | 0 | 16 | 14 | -2 | 17
|  |  | GEN | 3 | 3 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 3
|  |  | HYD | 4 | 4 | 0 | 4 | 0 | -2 | 2 | 0 | 1 | 1 | 0 | 1 | 3 | 4 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 4
|  |  | MEC | 2 | 3 | 1 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 2 | 3 | 1 | 1 | 0 | 1 | 3 | 4 | 1 | 4
|  |  | TOTAL - Marine | 25 | 24 | -1 | 18 | 0 | -6 | 10 | 2 | 5 | 7 | 0 | 5 | 17 | 27 | 1 | 1 | 0 | 1 | 26 | 25 | -1 | 28
Overall Toal
Overall Summary
| Purpose | Total | Cumulative |  |  | Last Week (reported) |  |  | Current Week (actual) |  |  | Next Week
|  |  | Planned | Issued | Gap | Planned | Issued | Gap | Planned | Issued | Gap | Plan
| FA | 982 | 403 | 329 | -74 | 107 | 18 | -89 | 107 | 18 | -89 | 22
| FC | 900 | 119 | 94 | -25 | 49 | 2 | -47 | 49 | 2 | -47 | 26
| FI | 642 | 74 | 40 | -34 | 52 | 5 | -47 | 52 | 5 | -47 | 6
| TOTAL | 2524 | 596 | 463 | -133 | 208 | 25 | -183 | 208 | 25 | -183 | 54
| Discipline | Cumulative |  |  |  | Last Week (reported) |  |  |  | Current Week (Actual) |  |  |  | Next Week (forecast)
|  | Baseline | Plan | Actual | Gap | Baseline | Plan | Actual | Gap | Baseline | Plan | Actual | Gap | Baseline | Plan | Gap
| GENERAL | 10.31% |  | 10.06% | -0.251% | 0% |  | 0% | 0% | 0% |  | 0% | 0% | 0% |  | 0%
| PROCESS | 80.82% |  | 77.13% | -3.687% | 1.802% |  | 0.8986% | -0.9036% | 1.802% |  | 0.8986% | -0.9036% | 1.802% |  | -0.9036%
| CIVIL | 14.6% |  | 16.31% | 1.706% | 0.6161% |  | 0.7468% | 0.1307% | 0.6161% |  | 0.7468% | 0.1307% | 0.6161% |  | 0.1307%
| S&A | 23.35% |  | 10.38% | -12.96% | 0.5632% |  | 0.1438% | -0.4194% | 0.5632% |  | 0.1438% | -0.4194% | 0.5632% |  | -0.4194%
| MECHANICAL | 21.14% |  | 19.17% | -1.973% | 2.183% |  | 0.04156% | -2.141% | 2.183% |  | 0.04156% | -2.141% | 2.183% |  | -2.141%
| PIPING | 33.31% |  | 33.82% | 0.5109% | 2.918% |  | 0.6403% | -2.277% | 2.918% |  | 0.6403% | -2.277% | 2.918% |  | -2.277%
| ELECTRICAL | 16.45% |  | 13.82% | -2.63% | 3.384% |  | 1.807% | -1.577% | 3.384% |  | 1.807% | -1.577% | 3.384% |  | -1.577%
| I&C | 11.32% |  | 15.23% | 3.91% | 0.4461% |  | 0.4386% | -0.007488% | 0.4461% |  | 0.4386% | -0.007488% | 0.4461% |  | -0.007488%
| TOTAL | #REF! |  | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! |  | #REF!
KPI's Format to be followed
Engineering Codification as per Project Management Speficiation requirements
Zone and Systems to be definied as per Project technology and with agreement with Owner
Overall Summary to be agreed with Project Company
TO BE DEFINED
Systems and disciplines TO BE DEFINED
and agreed with Owner

## Sheet1
SAU4005-G000-UMB-&CLB-00936 | IFI |  | Class 1 Issue For Approval
SAU4005-G000-UMB-&CTB-00938 | IFI | Document Number | Issue for Approval (1st issue)
SAU4005-G000-UMB-&CLB-00939 | IFI |  | 45%
SAU4005-G000-UMA-&CLB-00942 | IFI |  | 45%
SAU4005-G000-UMA-&CLB-00943 | IFI |  | Baseline
SAU4005-G000-UMA-&CLB-00949 | IFI | SAU4005-G000-UMB-&CTB-00938 | 2025-11-20
SAU4005-G000-UMA-&CLH-00951 | IFI | SAU4005-G000-UMB-&CLB-00939 | 2025-11-20
SAU4005-G000-UMA-&CLH-00952 | IFI | SAU4005-G000-UMA-&CLB-00942 | 2026-01-24
SAU4005-G000-UMA-&CLH-00953 | IFI | SAU4005-G000-UMA-&CLB-00943 | 2026-01-24
SAU4005-G000-UMA-&CLH-00954 | IFI | SAU4005-G000-UMA-&CLB-00949 | 2026-04-06
SAU4005-G000-UMA-&CLH-00957 | IFI | SAU4005-G000-UMA-&CLH-00951 | 2026-01-27
SAU4005-G000-UMA-&CLH-00958 | IFI | SAU4005-G000-UMA-&CLH-00952 | 2026-02-06
SAU4005-G000-UMA-&CLH-00959 | IFI | SAU4005-G000-UMA-&CLH-00953 | 2026-02-06
SAU4005-G000-UMA-&CLH-00960 | IFI | SAU4005-G000-UMA-&CLH-00954 | 2026-01-27
SAU4005-G000-UGA-&CLB-00964 | IFI | SAU4005-G000-UMA-&CLH-00957 | 2026-03-19
SAU4005-G000-URX-&CLB-00966 | IFI | SAU4005-G000-UMA-&CLH-00958 | 2026-03-19 | 2026-01-08
SAU4005-G000-URX-&CLB-00968 | IFI | SAU4005-G000-UMA-&CLH-00959 | 2026-03-18 | 2026-02-06
SAU4005-G000-UCA-&CLH-00972 | IFI | SAU4005-G000-UMA-&CLH-00960 | 2026-03-18 | 2026-03-02
SAU4005-G000-UCA-&CLB-00973 | IFI | SAU4005-G000-UGA-&CLB-00964 | 2025-12-16 | 2025-12-22
SAU4005-G000-UCA-&CTL-00974 | IFI | SAU4005-G000-URX-&CLB-00966 | 2025-12-11 | 2025-12-09
SAU4005-G000-UCA-&CTL-00975 | IFI | SAU4005-G000-URX-&CLB-00968 | 2025-12-11 | 2026-03-10
SAU4005-G000-UCA-&CTL-00976 | IFI | SAU4005-G000-UCA-&CLH-00972 | 2025-09-23 | 2026-03-03
SAU4005-G000-UCA-&CTL-00978 | IFI | SAU4005-G000-UCA-&CLB-00973 | 2025-08-02 | 2026-06-09
SAU4005-G000-UCA-&CTL-00979 | IFI | SAU4005-G000-UCA-&CTL-00974 | 2025-08-02 | 2026-03-16
SAU4005-G000-UCA-&CTL-00980 | IFI | SAU4005-G000-UCA-&CTL-00975 | 2025-09-04 | 2026-04-14
SAU4005-G000-UHA-&CLB-00990 | IFI | SAU4005-G000-UCA-&CTL-00976 | 2025-09-04 | 2026-02-28
SAU4005-G000-UHA-&CLB-00991 | IFI | SAU4005-G000-UCA-&CTL-00978 | 2025-09-24 | 2026-05-25
SAU4005-G000-UYC-&CLH-00995 | IFI | SAU4005-G000-UCA-&CTL-00979 | 2026-01-24 | 2025-12-15
SAU4005-G000-UYC-&CLB-00996 | IFI | SAU4005-G000-UCA-&CTL-00980 | 2026-06-05 | 2026-01-02
SAU4005-G000-UYC-&CTL-00997 | IFI | SAU4005-G000-UHA-&CLB-00990 | 2025-07-30 | 2025-11-12
SAU4005-G000-UYC-&CTL-00999 | IFI | SAU4005-G000-UHA-&CLB-00991 | 2025-11-15 | 2026-01-29
SAU4005-G000-UYC-&CTL-01000 | IFI | SAU4005-G000-UYC-&CLH-00995 | 2025-06-07 | 2026-05-29
SAU4005-G000-UYC-&CTL-01001 | IFI | SAU4005-G000-UYC-&CLB-00996 | 2025-08-16 | 2026-01-29
SAU4005-G000-UYF-&CLB-01005 | IFI | SAU4005-G000-UYC-&CTL-00997 | 2025-08-16
SAU4005-G000-UST-&CLH-01013 | IFI | SAU4005-G000-UYC-&CTL-00999 | 2025-08-16
SAU4005-G000-UST-&CLB-01014 | IFI | SAU4005-G000-UYC-&CTL-01000 | 2025-10-10
SAU4005-G000-UST-&CTL-01015 | IFI | SAU4005-G000-UYC-&CTL-01001 | 2025-10-10
SAU4005-G000-UST-&CTB-01016 | IFI | SAU4005-G000-UYF-&CLB-01005 | 2026-05-26
SAU4005-G000-UST-&CTB-01491 | IFI | SAU4005-G000-UST-&CLH-01013 | 2025-11-20
SAU4005-G000-UST-&CTB-01017 | IFI | SAU4005-G000-UST-&CLB-01014 | 2025-10-09
SAU4005-G000-UST-&CTB-01018 | IFI | SAU4005-G000-UST-&CTL-01015 | 2025-11-17
SAU4005-G000-UST-&CTL-01019 | IFI | SAU4005-G000-UST-&CTB-01016 | 2025-12-23
SAU4005-G000-UGG-&CTL-01021 | IFI | SAU4005-G000-UST-&CTB-01491 | 2026-05-13
SAU4005-G000-UAG-&CLB-01023 | IFI | SAU4005-G000-UST-&CTB-01017 | 2026-01-20
SAU4005-G000-UAG-&CLB-01024 | IFI | SAU4005-G000-UST-&CTB-01018 | 2026-01-21
SAU4005-G000-UBB-&CLB-01026 | IFI | SAU4005-G000-UST-&CTL-01019 | 2025-12-29
SAU4005-G000-UBB-&CTB-01027 | IFI | SAU4005-G000-UGG-&CTL-01021 | 2026-06-11
SAU4005-G000-UHX-&CTL-01032 | IFI | SAU4005-G000-UAG-&CLB-01023 | 2026-03-24
SAU4005-G000-UQA-&CLB-01033 | IFI | SAU4005-G000-UAG-&CLB-01024 | 2026-03-24
SAU4005-G000-U__-&CLB-01034 | IFI | SAU4005-G000-UBB-&CLB-01026 | 2026-10-13
SAU4005-G000-ULA-&CLB-01039 | IFI | SAU4005-G000-UBB-&CTB-01027 | 2026-07-29
SAU4005-G000-ULC-&CLB-01040 | IFI | SAU4005-G000-UHX-&CTL-01032 | 2026-06-24
SAU4005-G000-ULC-&CLB-01041 | IFI | SAU4005-G000-UQA-&CLB-01033 | 2025-12-01
SAU4005-G000-ULC-&CTL-01042 | IFI | SAU4005-G000-U__-&CLB-01034 | 2026-05-16
SAU4005-G000-ULC-&CLB-01044 | IFI | SAU4005-G000-ULA-&CLB-01039 | 2026-05-25
SAU4005-G000-ULC-&CTL-01045 | IFI | SAU4005-G000-ULC-&CLB-01040 | 2025-12-24
SAU4005-G000-USG-&CLB-01049 | IFI | SAU4005-G000-ULC-&CLB-01041 | 2025-12-31
SAU4005-G000-USG-&CTB-01050 | IFI | SAU4005-G000-ULC-&CTL-01042 | 2026-01-03
SAU4005-G000-USC-&CLB-01054 | IFI | SAU4005-G000-ULC-&CLB-01044 | 2026-04-16
SAU4005-G000-USC-&CTB-01055 | IFI | SAU4005-G000-ULC-&CTL-01045 | 2026-01-27
SAU4005-G000-USC-&CTL-01056 | IFI | SAU4005-G000-USG-&CLB-01049 | 2025-11-30
SAU4005-G000-USC-&CTL-01058 | IFI | SAU4005-G000-USG-&CTB-01050 | 2025-11-30
SAU4005-G000-UTG-&CLH-01060 | IFI | SAU4005-G000-USC-&CLB-01054 | 2025-11-04
SAU4005-G000-UTG-&CLB-01061 | IFI | SAU4005-G000-USC-&CTB-01055 | 2025-11-05
SAU4005-G000-UTG-&CTB-01062 | IFI | SAU4005-G000-USC-&CTL-01056
SAU4005-G000-UGD-&CLB-01067 | IFI | SAU4005-G000-USC-&CTL-01058 | 2026-10-08
SAU4005-G000-UGD-&CTL-01068 | IFI | SAU4005-G000-UTG-&CLH-01060 | 2026-05-12
SAU4005-G000-UGD-&CTL-01069 | IFI | SAU4005-G000-UTG-&CLB-01061 | 2026-12-23
SAU4005-G000-UGD-&CTL-01070 | IFI | SAU4005-G000-UTG-&CTB-01062 | 2027-01-22
SAU4005-G000-UZT-&CLB-01078 | IFI | SAU4005-G000-UGD-&CLB-01067 | 2025-12-02
SAU4005-G000-UZT-&CLB-01082 | IFI | SAU4005-G000-UGD-&CTL-01068 | 2026-01-31
SAU4005-G000-UZT-&CLB-01086 | IFI | SAU4005-G000-UGD-&CTL-01069 | 2026-01-31
SAU4005-G000-UZT-&CLB-01090 | IFI | SAU4005-G000-UGD-&CTL-01070 | 2026-02-23
SAU4005-G000-UZT-&CLB-01396 | IFI | SAU4005-G000-UZT-&CLB-01078 | 2025-11-10
SAU4005-G000-UZT-&CLB-01400 | IFI | SAU4005-G000-UZT-&CLB-01082 | 2025-11-28
SAU4005-G000-UZT-&CLB-01404 | IFI | SAU4005-G000-UZT-&CLB-01086 | 2025-11-04
SAU4005-G000-UZT-&CLB-01499 | IFI | SAU4005-G000-UZT-&CLB-01090 | 2025-12-26
SAU4005-G000-UZT-&CTB-01500 | IFI | SAU4005-G000-UZT-&CLB-01396 | 2025-11-20
SAU4005-G000-UZT-&CLB-01412 | IFI | SAU4005-G000-UZT-&CLB-01400 | 2025-11-20
SAU4005-G000-UZT-&CLB-01416 | IFI | SAU4005-G000-UZT-&CLB-01404 | 2025-11-20
SAU4005-G000-UZT-&CLB-01420 | IFI | SAU4005-G000-UZT-&CLB-01499 | 2025-12-29
SAU4005-G000-UZT-&CLB-01424 | IFI | SAU4005-G000-UZT-&CTB-01500 | 2025-11-20
SAU4005-G000-UZT-&CLB-01442 | IFI | SAU4005-G000-UZT-&CLB-01412 | 2025-12-25
SAU4005-G000-UZT-&CLB-01428 | IFI | SAU4005-G000-UZT-&CLB-01416 | 2025-12-25
SAU4005-G000-UZT-&CLB-01432 | IFI | SAU4005-G000-UZT-&CLB-01420 | 2026-04-13
SAU4005-G000-UTS-&CLH-01099 | IFI | SAU4005-G000-UZT-&CLB-01424 | 2026-03-14
SAU4005-G000-UTS-&CLB-01100 | IFI | SAU4005-G000-UZT-&CLB-01442 | 2026-04-03
SAU4005-G000-UGV-&CLB-01111 | IFI | SAU4005-G000-UZT-&CLB-01428 | 2026-02-09
SAU4005-G000-UGF-&CLB-01130 | IFI | SAU4005-G000-UZT-&CLB-01432 | 2026-02-09
SAU4005-G000-UZD-&CED-01144 | IFI | SAU4005-G000-UTS-&CLH-01099 | 2026-03-14
SAU4005-G000-UZD-&CTB-01145 | IFI | SAU4005-G000-UTS-&CLB-01100 | 2026-10-16
SAU4005-G000-UTH-&CLB-01150 | IFI | SAU4005-G000-UGV-&CLB-01111 | 2026-07-22
SAU4005-G000-U__-&CLB-01153 | IFI | SAU4005-G000-UGF-&CLB-01130 | 2026-08-12
SAU4005-G000-UBF-&CLB-01175 | IFI | SAU4005-G000-UZD-&CED-01144 | 2026-05-18
SAU4005-G000-UBF-&CLB-01177 | IFI | SAU4005-G000-UZD-&CTB-01145 | 2026-04-10
SAU4005-G000-UBA-&CLB-01182 | IFI | SAU4005-G000-UTH-&CLB-01150 | 2026-01-01
SAU4005-G000-UBA-&CLB-01190 | IFI | SAU4005-G000-U__-&CLB-01153 | 2026-07-02
SAU4005-G000-UBA-&CLB-01206 | IFI | SAU4005-G000-UBF-&CLB-01175 | 2026-07-13
SAU4005-G000-UGA-&CLB-01213 | IFI | SAU4005-G000-UBF-&CLB-01177 | 2026-07-24
SAU4005-G000-UYP-&CLB-01217 | IFI | SAU4005-G000-UBA-&CLB-01182 | 2026-05-20
SAU4005-G000-UGD-&CLB-01225 | IFI | SAU4005-G000-UBA-&CLB-01190 | 2026-06-10
SAU4005-G000-UGA-&CLB-01239 | IFI | SAU4005-G000-UBA-&CLB-01206 | 2025-12-03
SAU4005-G000-UBN-&CLB-01243 | IFI | SAU4005-G000-UGA-&CLB-01213 | 2025-11-30
SAU4005-G000-UBN-&CLB-01249 | IFI | SAU4005-G000-UYP-&CLB-01217 | 2026-03-27
SAU4005-G000-UEL-&CTB-01260 | IFI | SAU4005-G000-UGD-&CLB-01225 | 2026-01-13
SAU4005-G000-UEL-&CLB-01261 | IFI | SAU4005-G000-UGA-&CLB-01239 | 2026-09-18
SAU4005-G000-UBA-&CTB-01280 | IFI | SAU4005-G000-UBN-&CLB-01243 | 2025-10-15
SAU4005-G000-UBA-&CLB-01282 | IFI | SAU4005-G000-UBN-&CLB-01249 | 2025-11-24
SAU4005-G000-UYF-&CTB-01332 | IFI | SAU4005-G000-UEL-&CTB-01260 | 2025-08-28
SAU4005-G000-UYE-&CTB-01339 | IFI | SAU4005-G000-UEL-&CLB-01261 | 2025-12-15
SAU4005-G000-UBE-&CLB-01435 | IFI | SAU4005-G000-UBA-&CTB-01280 | 2026-02-20
SAU4005-G000-UBE-&CLB-01437 | IFI | SAU4005-G000-UBA-&CLB-01282 | 2026-03-06
SAU4005-G000-UBE-&CLB-01439 | IFI | SAU4005-G000-UYF-&CTB-01332 | 2025-09-19
SAU4005-G000-UBA-&CTB-01485 | IFI | SAU4005-G000-UYE-&CTB-01339 | 2025-08-16
SAU4005-G000-AS_-&CLB-01479 | IFI | SAU4005-G000-UBE-&CLB-01435 | 2026-04-30
SAU4005-G000-UYX-&CTL-01480 | IFI | SAU4005-G000-UBE-&CLB-01437 | 2026-05-13
SAU4005-G000-GM_-&CLB-01482 | IFI | SAU4005-G000-UBE-&CLB-01439 | 2026-03-13
SAU4005-G000-UM_-&CLH-01496 | IFI | SAU4005-G000-UBA-&CTB-01485 | 2026-04-21
|  | SAU4005-G000-AS_-&CLB-01479 | 2026-07-18
|  | SAU4005-G000-UYX-&CTL-01480 | 2026-06-12
|  | SAU4005-G000-GM_-&CLB-01482 | 2026-08-20
|  | SAU4005-G000-UM_-&CLH-01496 | 2026-11-08

## Legend & Codes used
1. Column 'AT': Classifies whether each document is required for submission to SPPC with a 'Yes' or 'No'
2. Column 'AU': Categorizes all documents required for submission to SPPC into the four specified categories within the MDL:
| Code In MDL | Four category documents
| C1 | Documents to be submitted prior to closing date
| C2 | Documents and/or software to be submitted After Closing date
| C3 | Documents to be submitted prior to site construction
| C4 | Documents to be submitted during site construction
3. Column 'AV': Classifies documents required for submission to SPPC and specifies the interfacing parties (SEC, Aramco, NWC,…etc)
4. Column 'AW': Classifies documents required for submission to SEC-NG for each department as per received transmittal form from SPPC
SPPC PROJECT'S SUBMITTAL/TRANSMITTAL
|  |  |  | Code In MDL |  | Code In MDL
|  |  | Project Execution (SPPC) | S1 | Safety & Environmental Prev. (ISCEPDV)
|  |  | Support Facility Projects Div (PRCSFDV) |  | Telecom Maintenance (CATCDV)
|  |  | Engineering & Design (EGDCADV) | S2 | Field Op & Supp Survey (SSRFODV)
|  |  | Protection Eng Division (PTECADV) | S3 | O&M Al Kharj (SSROPDV)
|  |  | Protection Testing Div. (SSRPTDV) | S4 | Commissioning Services Div. (CSVCADV)
|  |  | Substations Div, Riyadh (SSRSSDV) | S5 | Project Technical Support Division
|  |  | Network Planning Div. (COA) | S6 | SCADA Division – COA (CASDDV) | S10
|  |  | Lines & Telecom Proj Div (PRCLTDV) | S7 | Prequalification & Support Facilities Div. (STDSFDV)
|  |  | Under Ground Cable Div. (LNRGCDV) | S8 | Project Quality Monitoring Division
|  |  | Control Support Div. (OPCCSDV) | S9 | Telecom Technical support Div. (TLCSVDV) | S11
5. Column 'AX': Classifies documents required for submission to IPP-2