## EDL+VDL
|  |  | * Note - EPC will submit on ThinkProject(TP) only the documents listed in the MDL. EPC can not upload any documents on TP unless it is listed in the MDL. - This Engineering MDL will be used as part of Project MDL(Doc No. XXX ) along with the MDLs from other departments. - The Project MDL must be used exclusively for document uploads on TP database, which will serve as the reference for all types of reporting. - The submission dates for documents in TP must be aligned with the Primavera software program of the project schedule. - Since the package vendor has not yet been finalized, the following Vendor Document will be updated as per progress is updated. | [15 empty] | Class 1 Issue For Approval | [11 empty] | Class 2 Issue for Information |  |  |  | Class 3 Issue for Construction |  |  |  | Cutoff Date | 2026-06-12
|  | No. | P6 Activity ID | Issued by | Document Number | Document Description | Plant | Department | Discipline (DCC A1) | Common document of Rumah and Nairyah | Sub-Discipline | WBS Category | Document Owner (This column will be deleted) | System(APEX Code) | Class / Purpose | IFD/IFC/IFP | Actual Rev Status | Step | Issue for Approval (1st issue) |  |  |  | Approved with comments and issue to Owner |  |  |  | Final approval and issue to Owner (IFC) |  |  |  | IFI |  |  |  | IFC |  |  |  | Estimated Manhours | Document Weight | PROGRESS |  |  | TOTAL FLOAT |  | TO be reviewed by |  |  |  | TOP No.
[18 empty] | Cumm | 45% |  |  |  | 80% |  |  |  | 100% |  |  |  | 100% |  |  |  | - | [5 empty] | Baseline | Forecast | Actual | Baseline | Actual | ACWA PC | OE | NOMAC | CTS
[18 empty] | Partial | 45% |  |  |  | 35% |  |  |  | 20% |  |  |  | 100% |  |  |  | -
| Remark | [17 empty] | Baseline L3(Rev.B) | Forecast | Actual | variance | Baseline L3(Rev.B) | Forecast | Actual | variance | Baseline L3(Rev.B) | Forecast | Actual | variance | Baseline L3(Rev.B) | Forecast | Actual | variance | IFC - BL L3 | Forecast | IFC - Actual | IFC - variance | [12 empty] | Engineering Type | Sub Discipline | Work Flow | OE Review (Yes/No) | O&M Review (Yes/NO) | SPPC (Off Taker) Submission (Yes/No) | SPPC (Off Taker) Submission (C1,C2,C3,C4) | For interfacing parties (SEC, Aramco,NWC) | SEC-NG Department | NOC | Open/Combine Cycle (Open/Combine/Partial)
|  | 1 | Later | S&L | SAU4005-G000-___-&ABD-00001 | Document Numbering Procedure | A1 | Engineering | A-Overall management | Yes | GENERAL | GENERAL | Common |  | IFA | IFD |  |  | 2025-02-14 |  | 2025-01-23 |  | 2025-03-06 |  | 2025-02-07 |  | 2025-04-11 |  | 2025-03-22 | [9 empty] | 1000 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 2 | Later | S&L | SAU4005-G000-___-&ABD-00002 | Plant Tagging Procedure | A1 | Engineering | A-Overall management | Yes | GENERAL | MECHANICAL | Common |  | IFA | IFD |  |  | 2025-02-14 |  | 2025-01-24 |  | 2025-03-06 |  | 2025-02-16 |  | 2025-04-11 |  | 2025-03-04 | [9 empty] | 1000 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C1 | NO |  | NO | Common
|  | 3 | Later | S&L | SAU4005-G000-___-&ABD-00003 | Document Management Plan | A1 | Engineering | A-Overall management | Yes | GENERAL | GENERAL | Common |  | IFA | IFD |  |  | 2025-02-14 |  | 2025-01-24 |  | 2025-03-06 |  | 2025-02-16 |  | 2025-04-11 |  | 2025-04-14 | [9 empty] | 1000 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 4 | Later | S&L | SAU4005-G000-___-&AAB-00338 | Master Deliverable List | A1 | Engineering | A-Overall management | Yes | GENERAL | GENERAL | Common |  | IFA | IFD |  |  | 2025-02-21 |  | 2025-01-27 |  | 2025-03-13 |  | 2025-03-13 |  | 2025-04-18 |  | 0 | [9 empty] | 1000 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1 | NO |  | NO | Common
|  | 5 | Later | S&L | SAU4005-G000-___-&MDB-00004 | Design Criteria Document for Mechanical | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFD |  |  | 2025-03-14 |  | 2025-02-25 |  | 2025-04-03 |  | 2025-03-07 |  | 2025-05-09 |  | 2025-07-30 | [9 empty] | 991 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1 | NO |  | NO | Common
|  | 6 | Later | S&L | SAU4005-G000-SA_-&MDB-00005 | Design Criteria Document for Heating, Ventilation and Air Conditioning System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-03-12 |  | 2025-02-25 |  | 2025-03-31 |  | 2025-03-07 |  | 2026-03-06 |  | 0 | [9 empty] | 139 | [13 empty] | WF Transmittal DI-EPC-ACWA |  | YES | NO | C1 | NO |  | NO
|  | 8 | Later | S&L | SAU4005-G000-___-&MDB-00460 | Basic Engineering Design Criteria Document | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFD |  |  | 2025-03-11 |  | 2025-02-19 |  | 2025-03-31 |  | 2025-03-30 |  | 2025-05-06 |  | 2025-04-23 | [9 empty] | 910 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
|  | 9 | Later | S&L | SAU4005-G000-___-&MDD-00461 | Plant Performance Correction Curve | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | Common |  | IFA | IFD |  |  | 2026-11-25 |  |  |  | 2026-12-15 |  |  |  | 2027-01-20 | [11 empty] | 696 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES
|  | 10 | Later | S&L | SAU4005-G000-___-&MDD-00462 | Plant Degradation Curve | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | Common |  | IFA | IFD |  |  | 2026-11-25 |  |  |  | 2026-12-15 |  |  |  | 2027-01-20 | [11 empty] | 411 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES
|  | 11 | Later | S&L | SAU4005-G000-H__-&MFB-00007 | Heat Balance Diagram | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-06-17 |  | 2025-01-24 |  | 2025-07-07 |  | 2025-02-19 |  | 2025-08-12 |  | 0 | [9 empty] | 1943 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1,C2 | NO |  | NO | Common
|  | 12 | Later | S&L | SAU4005-G000-G__-&MFB-00008 | Water Balance Diagram | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-03-17 |  | 2025-04-16 |  | 2025-04-04 |  | 2025-06-03 |  | 2026-01-06 |  | 2025-11-19 | [9 empty] | 463 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1,C2 | NWC |  | NO | Common
|  | 13 | Later | S&L | SAU4005-G000-LA_-&MED-00009 | Calculation for Feed Water System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-07-17 |  | 2025-02-28 |  | 2025-08-06 |  | 2025-03-15 |  | 2025-09-15 |  | 2025-09-16 | [9 empty] | 586 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Combine
|  | 14 | Later | S&L | SAU4005-G000-QCA-&MED-00011 | Calculation for Power Cycle Chemical Feed System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-04-29 |  | 2025-04-15 |  | 2025-05-19 |  | 2025-04-30 |  | 2026-01-23 |  | 2025-07-28 | [9 empty] | 674 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
|  | 15 | Later | S&L | SAU4005-G000-LAH-&MED-00012 | Calculation for Steam drain and Vents | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-05-05 |  | 2025-04-30 |  | 2025-05-23 |  | 2025-05-14 |  | 2025-07-03 |  | 2025-08-19 | [9 empty] | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Combine
|  | 16 | Later | S&L | SAU4005-G000-EG_-&MED-00013 | Calculation for Fuel oil System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-04-10 |  | 2025-04-09 |  | 2025-04-29 |  | 2025-04-24 |  | 2025-10-15 |  | 2025-08-24 | [9 empty] | 463 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | ARAMCO |  | NO | Open
|  | 17 | Later | S&L | SAU4005-G000-EK_-&MED-00014 | Calculation for Fuel Gas System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-01-27 |  | 2025-02-17 |  | 2025-02-17 |  | 2025-05-05 |  | 2025-10-10 |  | 2025-08-07 | [9 empty] | 589 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | ARAMCO |  | NO | Open
|  | 18 | Later | S&L | SAU4005-G000-GH_-&MED-00015 | Calculation for Service water system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-06-24 |  | 2025-04-25 |  | 2025-07-11 |  | 2025-05-07 |  | 2025-12-15 |  | 0 | [9 empty] | 680 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 19 | Later | S&L | SAU4005-G000-GK_-&MED-00016 | Calculation for Potable water system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-07-07 |  | 2025-06-20 |  | 2025-07-25 |  | 2025-05-07 |  | 2025-12-15 |  | 2025-09-28 | [9 empty] | 680 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 20 | Later | S&L | SAU4005-G000-QEA-&MED-00017 | Calculation for Compressed Air System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-06-11 |  | 2025-04-21 |  | 2025-07-01 |  | 2025-06-12 |  | 2025-11-19 |  | 2025-11-30 | [9 empty] | 680 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
|  | 21 | Later | S&L | SAU4005-G000-G__-&MED-00018 | Calculation for Service Water (Treated Waste Water) System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-05-27 |  | 2025-04-16 |  | 2025-06-16 |  | 2025-04-30 |  | 2025-12-15 |  | 2025-08-18 | [9 empty] | 680 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
|  | 22 | Later | S&L | SAU4005-G000-GHC-&MED-00019 | Calculation for DM Water Distribution system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-05-28 |  | 2025-04-15 |  | 2025-06-17 |  | 2025-03-14 |  | 2025-12-15 |  | 2025-08-18 | [9 empty] | 680 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NWC |  | NO | Common
|  | 23 | Later | S&L | SAU4005-G000-LBA-&MED-00021 | Calculation for High Pressure (HP) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-13 |  | 2025-02-28 |  | 2025-04-02 |  | 2025-03-12 |  | 2025-05-08 |  | 2025-06-30 | [9 empty] | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Combine
|  | 24 | Later | S&L | SAU4005-G000-LBB-&MED-00022 | Calculation for Hot Reheat (HRH) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-13 |  | 2025-02-28 |  | 2025-04-02 |  | 2025-03-12 |  | 2025-05-12 |  | 2025-07-04 | [9 empty] | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Combine
|  | 25 | Later | S&L | SAU4005-G000-LBC-&MED-00023 | Calculation for Cold Reheat (CRH) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-13 |  | 2025-03-02 |  | 2025-04-02 |  | 2025-03-12 |  | 2025-05-12 |  | 2025-06-23 | [9 empty] | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Combine
|  | 26 | Later | S&L | SAU4005-G000-LBD-&MED-00024 | Calculation for Low Pressure (LP) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-13 |  | 2025-02-28 |  | 2025-04-02 |  | 2025-03-12 |  | 2025-05-12 |  | 2025-07-07 | [9 empty] | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Combine
|  | 27 | Later | S&L | SAU4005-G000-LBG-&MED-00025 | Calculation for Auxiliary Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-13 |  | 2025-03-10 |  | 2025-04-02 |  | 2025-03-22 |  | 2025-05-12 |  | 2025-08-24 | [9 empty] | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Combine
|  | 28 | Later | S&L | SAU4005-G000-LC_-&MED-00026 | Calculation for Condensate System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-06-13 |  | 2025-03-02 |  | 2025-07-03 |  | 2025-03-15 |  | 2025-10-23 |  | 2025-08-24 | [9 empty] | 541 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
|  | 29 | Later | S&L | SAU4005-G000-PG_-&MED-00027 | Calculation for Closed Circuit Cooling Water System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-05-14 |  | 2025-04-03 |  | 2025-06-03 |  | 2025-04-18 |  | 2026-01-30 |  | 2025-08-07 | [9 empty] | 683 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
|  | 30 | Later | S&L | SAU4005-G000-GMA-&MED-00028 | Calculation for Plant Drain System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-08-13 |  | 2025-08-05 |  | 2025-09-04 |  | 2025-08-26 |  | 2025-12-17 |  | 2025-09-26 | [9 empty] | 680 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 31 | Later | S&L | SAU4005-G000-QJ_-&MED-00029 | Calculation for Industrial Gas System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-08-14 |  | 2025-07-27 |  | 2025-09-05 |  | 2025-06-09 |  | 2025-10-07 |  | 2025-09-26 | [9 empty] | 330 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 32 | Later | S&L | SAU4005-G000-___-&MED-00033 | Calculation for Thermal Insulation | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | Common |  | IFA | IFD |  |  | 2025-11-10 |  | 2025-04-23 |  | 2025-12-01 |  | 2025-05-06 |  | 2026-01-08 |  | 2025-07-04 | [9 empty] | 162 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 33 | Later | S&L | SAU4005-G000-SA_-&MED-00360 | HVAC sizing calculation for STG Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2026-01-05 |  | 2025-04-29 |  | 2026-01-27 |  | 2025-03-12 |  | 2026-03-19 |  | 2025-08-06 | [9 empty] | 304 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO
|  | 34 | Later | S&L | SAU4005-G000-SA_-&MED-00361 | HVAC sizing calculation for Main Electrical & Control Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-07-18 |  | 2025-06-21 |  | 2025-08-07 |  | 2025-03-12 |  | 2026-04-08 |  | 2025-09-03 | [9 empty] | 304 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO
|  | 35 | Later | S&L | SAU4005-G000-SA_-&MED-00362 | HVAC sizing calculation for Administration & Social Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-07-07 |  | 2025-05-09 |  | 2025-07-25 |  | 2025-05-27 |  | 2025-08-25 |  | 2025-06-26 | [9 empty] | 304 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO
|  | 36 | Later | S&L | SAU4005-G000-SA_-&MED-00363 | HVAC sizing calculation for Security and Control center | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2026-07-10 |  | 2025-12-25 |  | 2026-07-30 |  | 2026-01-14 |  | 2026-08-27 |  | 2026-02-24 | [9 empty] | 308 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
|  | 37 | Later | S&L | SAU4005-G000-SA_-&MED-00364 | HVAC sizing calculation for Workshop and Warehouse Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-08-19 |  | 2025-05-20 |  | 2025-09-09 |  | 2025-06-03 |  | 2025-10-14 |  | 2025-09-16 | [9 empty] | 308 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
|  | 38 | Later | S&L | SAU4005-G000-SA_-&MED-00365 | HVAC sizing calculation for Water and Effluent treatment System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-12-11 |  | 2025-06-25 |  | 2025-12-31 |  | 2025-03-12 |  | 2026-03-10 |  | 2025-12-18 | [9 empty] | 249 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
|  | 39 | Later | S&L | SAU4005-G000-SA_-&MED-00367 | HVAC sizing calculation for Unit MV/LV Electrical Switchgear building - 11, 12, 13 | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-09-11 |  | 2025-06-06 |  | 2025-10-06 |  | 2025-06-24 |  | 2026-03-26 |  | 2025-07-29 | [9 empty] | 236 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO
|  | 40 | Later | S&L | SAU4005-G000-SA_-&MED-00368 | HVAC sizing calculation for GT Package MCC / Control room - 11, 12, 13 | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-08-11 |  | 2025-06-25 |  | 2025-09-02 |  | 2025-07-09 |  | 2025-10-03 |  | 2025-09-28 | [9 empty] | 236 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO
|  | 41 | Later | S&L | SAU4005-G000-SA_-&MED-00370 | HVAC sizing calculation for BOP Electrical Switchgear Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2026-01-15 |  | 2025-10-13 |  | 2026-02-05 |  | 2025-03-12 |  | 2026-03-06 |  | 2025-11-19 | [9 empty] | 236 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
|  | 42 | Later | S&L | SAU4005-G000-SA_-&MED-00372 | HVAC sizing calculation for Fire Station Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2026-01-29 |  | 2025-06-13 |  | 2026-02-18 |  | 2025-07-01 |  | 2026-03-19 |  | 2025-07-29 | [9 empty] | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
|  | 43 | Later | S&L | SAU4005-G000-SA_-&MED-00374 | HVAC sizing calculation for Hydrogen Generation Plant including Electrical Room | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2026-05-21 |  | 2025-10-13 |  | 2026-06-10 |  | 2025-03-12 |  | 2026-07-08 |  | 2025-11-18 | [9 empty] | 249 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
|  | 44 | Later | S&L | SAU4005-G000-SA_-&MED-00375 | HVAC sizing calculation for Electrical Switchgear Building for Fuel Gas | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2026-04-07 |  | 2025-10-19 |  | 2026-04-27 |  | 2025-11-04 |  | 2026-05-25 |  | 2025-12-28 | [9 empty] | 249 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
|  | 45 | Later | S&L | SAU4005-G000-SA_-&MED-00376 | HVAC sizing calculation for Search Facility & Visitors Centre | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2026-07-14 |  | 2025-12-20 |  | 2026-08-03 |  | 2025-11-30 |  | 2026-09-01 |  | 2026-01-12 | [9 empty] | 249 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
|  | 46 | Later | S&L | SAU4005-G000-SA_-&MED-00377 | HVAC sizing calculation for Main Gate House | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2026-07-29 |  | 2025-11-25 |  | 2026-08-18 |  | 2026-01-04 |  | 2026-09-17 |  | 2026-01-21 | [9 empty] | 249 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
|  | 47 | Later | S&L | SAU4005-G000-SA_-&MED-00380 | HVAC sizing calculation for STG and Auxiliary Boiler Electrical Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2026-06-08 |  | 2025-06-29 |  | 2026-06-26 |  | 2025-05-02 |  | 2026-07-24 |  | 2025-07-29 | [9 empty] | 249 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO
|  | 48 | Later | S&L | SAU4005-G000-SA_-&MED-00440 | HVAC sizing calculation for Electrical building for Water and Effluent treatment System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2026-04-21 |  | 2025-11-15 |  | 2026-05-11 |  | 2025-12-01 |  | 2026-06-08 |  | 2025-12-28 | [9 empty] | 249 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
|  | 49 | Later | S&L | SAU4005-G000-___-&MFB-00034 | P&ID for Index, Legends & Symbols | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | Common |  | IFA | IFD |  |  | 2025-04-15 |  | 2025-03-11 |  | 2025-05-05 |  | 0 |  | 2025-06-10 |  | 2025-03-22 | [9 empty] | 269 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 50 | Later | S&L | SAU4005-G000-EK_-&MFB-00035 | P&ID for Fuel gas system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-05-29 |  | 2025-05-01 |  | 2025-06-17 |  | 2025-05-15 |  | 2025-11-03 |  | 0 | [9 empty] | 683 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | Aramco |  | NO | Open
|  | 51 | Later | S&L | SAU4005-G000-GH_-&MFB-00036 | P&ID for Service water system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-06-17 |  | 2025-05-07 |  | 2025-07-07 |  | 2025-05-20 |  | 2026-01-12 |  | 2025-07-23 | [9 empty] | 823 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
|  | 52 | Later | S&L | SAU4005-G000-GK_-&MFB-00037 | P&ID for Potable water system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-06-16 |  | 2025-06-23 |  | 2025-07-04 |  | 2025-05-07 |  | 2026-01-12 |  | 2025-12-07 | [9 empty] | 810 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
|  | 53 | Later | S&L | SAU4005-G000-QEA-&MFB-00038 | P&ID for Compressed Air System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-06-18 |  | 2025-05-29 |  | 2025-07-07 |  | 2025-06-12 |  | 2025-12-17 |  | 2025-12-04 | [9 empty] | 852 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
|  | 54 | Later | S&L | SAU4005-G000-G__-&MFB-00039 | P&ID for Service Water (Treated Waste Water) System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-05-27 |  | 2025-04-14 |  | 2025-06-16 |  | 2025-04-29 |  | 2026-01-06 |  | 2025-08-18 | [9 empty] | 819 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NWC |  | NO | Common
|  | 55 | Later | S&L | SAU4005-G000-GHC-&MFB-00040 | P&ID for DM Water Distribution System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-07-08 |  | 2025-05-06 |  | 2025-07-28 |  | 2025-03-14 |  | 2026-01-12 |  | 2025-09-26 | [9 empty] | 852 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
|  | 56 | Later | S&L | SAU4005-G000-MB_-&MFB-00041 | P&ID for Gas Turbine Interconnecting Piping System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | Common |  | IFA | IFD |  |  | 2025-08-18 |  | 2025-09-18 |  | 2025-09-05 |  | 2025-10-02 |  | 2025-10-10 |  | 2026-04-26 | [9 empty] | 862 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
|  | 57 | Later | S&L | SAU4005-G000-LBA-&MFB-00043 | P&ID for High Pressure (HP) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-24 |  | 2025-02-28 |  | 2025-04-11 |  | 2025-03-12 |  | 2025-05-19 |  | 2025-08-19 | [9 empty] | 547 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Combine
|  | 58 | Later | S&L | SAU4005-G000-LBC-&MFB-00044 | P&ID for Cold Reheat (CRH) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-24 |  | 2025-03-02 |  | 2025-04-11 |  | 2025-03-10 |  | 2025-05-19 |  | 2025-08-19 | [9 empty] | 547 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Combine
|  | 59 | Later | S&L | SAU4005-G000-LBB-&MFB-00045 | P&ID for Hot Reheat (HRH) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-24 |  | 2025-02-28 |  | 2025-04-11 |  | 2025-03-11 |  | 2025-05-19 |  | 2025-08-19 | [9 empty] | 547 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Combine
|  | 60 | Later | S&L | SAU4005-G000-LBD-&MFB-00046 | P&ID for Low Pressure (LP) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-24 |  | 2025-02-28 |  | 2025-04-11 |  | 2025-03-11 |  | 2025-05-19 |  | 2025-08-19 | [9 empty] | 547 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Combine
|  | 61 | Later | S&L | SAU4005-G000-LBG-&MFB-00047 | P&ID for Auxiliary Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-24 |  | 2025-03-10 |  | 2025-04-11 |  | 2025-03-22 |  | 2025-05-19 |  | 2026-03-29 | [9 empty] | 547 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Combine
|  | 62 | Later | S&L | SAU4005-G000-LAB-&MFB-00048 | P&ID for Feed Water System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-17 |  | 2025-03-02 |  | 2025-04-04 |  | 2025-03-10 |  | 2025-05-12 |  | 2025-08-20 | [9 empty] | 683 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Combine
|  | 63 | Later | S&L | SAU4005-G000-LC_-&MFB-00049 | P&ID for Condensate System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-17 |  | 2025-03-02 |  | 2025-04-04 |  | 2025-03-10 |  | 2025-05-12 |  | 2025-08-21 | [9 empty] | 596 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C2 | NO |  | NO | Combine
|  | 64 | Later | S&L | SAU4005-G000-PG_-&MFB-00050 | P&ID for Closed Circuit Cooling Water System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-06-27 |  | 2025-05-08 |  | 2025-07-17 |  | 2025-05-20 |  | 2026-02-23 |  | 2026-03-15 | [9 empty] | 683 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Common
|  | 65 | Later | S&L | SAU4005-G000-QCA-&MFB-00051 | P&ID for Chemical Feed System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-05-08 |  | 2025-04-08 |  | 2025-05-28 |  | 2025-04-20 |  | 2025-12-09 |  | 2026-01-22 | [9 empty] | 622 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
|  | 66 | Later | S&L | SAU4005-G000-QU_-&MFB-00052 | P&ID for Process Sampling System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-07-04 |  | 2025-03-28 |  | 2025-07-25 |  | 2025-04-08 |  | 2026-01-27 |  | 2025-05-27 | [9 empty] | 292 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 67 | Later | S&L | SAU4005-G000-QJA-&MFB-00053 | P&ID for Industrial Gas System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-09-22 |  | 2025-07-31 |  | 2025-10-14 |  | 2025-09-09 |  | 2026-01-02 |  | 2025-12-04 | [9 empty] | 292 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 68 | Later | S&L | SAU4005-G000-LBW-&MFB-00054 | P&ID for STG Interconnecting Piping System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-07-29 |  | 2025-09-18 |  | 2025-08-19 |  | 2025-10-02 |  | 2025-09-25 |  | 2025-10-22 | [9 empty] | 622 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
|  | 69 | Later | S&L | SAU4005-G000-EG_-&MFB-00055 | P&ID for Fuel oil System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-05-09 |  | 2025-04-11 |  | 2025-05-29 |  | 2025-04-29 |  | 2025-11-12 |  | 2025-07-01 | [9 empty] | 547 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Open
|  | 70 | Later | S&L | SAU4005-G000-LCM-&MFB-00056 | P&ID for Steam Vents & Drains System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-05-05 |  | 2025-04-30 |  | 2025-05-23 |  | 2025-05-13 |  | 2025-08-08 |  | 2025-08-19 | [9 empty] | 781 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Combine
|  | 71 | Later | S&L | SAU4005-G000-GMA-&MFB-00057 | P&ID for Plant Drain System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-09-16 |  | 2025-08-03 |  | 2025-10-07 |  | 2025-08-18 |  | 2026-03-18 |  | 2025-10-09 | [9 empty] | 528 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Common
| Design Purpose Changed | 72 | Later | S&L | SAU4005-G000-SA_-&MFB-00381 | Air Flow Diagram of HVAC system for STG Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-12-31 |  | 2025-05-07 |  | 2026-01-21 |  | 2025-05-20 |  | 2026-02-19 |  | 2025-05-29 | [5 empty] | 2026-02-19 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
| Design Purpose Changed | 73 | Later | S&L | SAU4005-G000-SA_-&MFB-00382 | Air Flow Diagram of HVAC system for Main Electrical & Control Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-07-31 |  | 2025-07-14 |  | 2025-08-21 |  | 2025-07-28 |  | 2025-09-19 |  | 2025-08-12 | [5 empty] | 2025-09-19 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
| Design Purpose Changed | 74 | Later | S&L | SAU4005-G000-SA_-&MFB-00383 | Air Flow Diagram of HVAC system for Administration & Social Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-12-31 |  | 2025-05-06 |  | 2026-01-21 |  | 2025-05-19 |  | 2026-02-19 |  | 2025-06-09 | [5 empty] | 2026-02-19 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
| Design Purpose Changed | 75 | Later | S&L | SAU4005-G000-SA_-&MFB-00384 | Air Flow Diagram of HVAC system for Security and Control center | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2026-08-18 |  | 2026-03-27 |  | 2026-09-08 |  | 2026-04-12 |  | 2026-10-07 |  | 2026-04-26 | [5 empty] | 2026-10-07 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
| Design Purpose Changed | 76 | Later | S&L | SAU4005-G000-SA_-&MFB-00385 | Air Flow Diagram of HVAC system for Workshop and Warehouse Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-09-04 |  | 2025-06-06 |  | 2025-09-24 |  | 2025-06-24 |  | 2025-10-29 |  | 2025-09-16 | [5 empty] | 2025-10-29 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
| Design Purpose Changed | 77 | Later | S&L | SAU4005-G000-SA_-&MFB-00386 | Air Flow Diagram of HVAC system for Water and Effluent treatment System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-12-30 |  | 2025-06-29 |  | 2026-01-20 |  | 2025-07-10 |  | 2026-02-18 |  | 2026-03-10 | [5 empty] | 2026-02-18 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
| Design Purpose Changed | 78 | Later | S&L | SAU4005-G000-SA_-&MFB-00388 | Air Flow Diagram of HVAC system for Unit MV/LV Electrical Switchgear building - 11, 12, 13 | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-08-21 |  | 2025-06-13 |  | 2025-09-11 |  | 2025-04-21 |  | 2025-10-14 |  | 2025-08-04 | [5 empty] | 2025-10-14 |  |  |  | 211 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
| Design Purpose Changed | 79 | Later | S&L | SAU4005-G000-SA_-&MFB-00389 | Air Flow Diagram of HVAC system for GT Package MCC / Control room - 11, 12, 13 | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-09-24 |  | 2025-09-17 |  | 2025-10-17 |  | 2025-10-02 |  | 2025-11-18 |  | 2026-01-11 | [5 empty] | 2025-11-18 |  |  |  | 211 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
| Design Purpose Changed | 80 | Later | S&L | SAU4005-G000-SA_-&MFB-00391 | Air Flow Diagram of HVAC system for BOP Electrical Switchgear Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-12-31 |  | 2025-11-20 |  | 2026-01-21 |  | 2025-06-24 |  | 2026-02-19 |  | 2026-01-11 | [5 empty] | 2026-02-19 |  |  |  | 211 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
| Design Purpose Changed | 81 | Later | S&L | SAU4005-G000-SA_-&MFB-00393 | Air Flow Diagram of HVAC system for Fire Station Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2026-03-11 |  | 2025-06-13 |  | 2026-03-31 |  | 2025-06-27 |  | 2026-04-28 |  | 2025-07-11 | [5 empty] | 2026-04-28 |  |  |  | 211 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
| Design Purpose Changed | 82 | Later | S&L | SAU4005-G000-SA_-&MFB-00395 | Air Flow Diagram of HVAC system for Hydrogen Generation Plant including Electrical Room | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2026-06-30 |  | 2025-12-08 |  | 2026-07-20 |  | 2025-12-21 |  | 2026-08-17 |  | 2026-01-13 | [5 empty] | 2026-08-17 |  |  |  | 211 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
| Design Purpose Changed | 83 | Later | S&L | SAU4005-G000-SA_-&MFB-00396 | Air Flow Diagram of HVAC system for Electrical Switchgear Building for Fuel Gas | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2026-05-19 |  | 2025-12-08 |  | 2026-06-08 |  | 2025-12-21 |  | 2026-07-06 |  | 2026-01-11 | [5 empty] | 2026-07-06 |  |  |  | 211 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
| Design Purpose Changed | 84 | Later | S&L | SAU4005-G000-SA_-&MFB-00397 | Air Flow Diagram of HVAC system for Search Facility & Visitors Centre | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2027-01-06 |  | 2025-12-24 |  | 2027-01-28 |  | 2025-10-02 |  | 2027-02-25 |  | 2026-01-25 | [5 empty] | 2027-02-25 |  |  |  | 211 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
| Design Purpose Changed | 85 | Later | S&L | SAU4005-G000-SA_-&MFB-00398 | Air Flow Diagram of HVAC system for Main Gate House | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2027-01-22 |  | 2025-12-27 |  | 2027-02-12 |  | 0 |  | 2027-03-12 |  | 2026-01-11 | [5 empty] | 2027-03-12 |  |  |  | 211 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
| Design Purpose Changed | 86 | Later | S&L | SAU4005-G000-SA_-&MFB-00401 | Air Flow Diagram of HVAC system for STG and Auxiliary Boiler Electrical Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2026-05-26 |  | 2025-07-16 |  | 2026-06-15 |  | 2025-07-28 |  | 2026-07-13 |  | 2025-08-12 | [5 empty] | 2026-07-13 |  |  |  | 211 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
| Design Purpose Changed | 87 | Later | S&L | SAU4005-G000-SA_-&MFB-00441 | Air Flow Diagram of HVAC system for Electrical building for Water and Effluent treatment System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2026-03-12 |  | 2025-11-25 |  | 2026-04-01 |  | 2025-12-24 |  | 2026-04-29 |  | 2026-01-11 | [5 empty] | 2026-04-29 |  |  |  | 211 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
|  | 88 | Later | S&L | SAU4005-G000-EK_-&MDB-00060 | System Description for Fuel gas system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-07-14 |  | 2025-05-05 |  | 2025-07-30 |  | 2025-05-19 |  | 2025-11-10 |  | 2025-08-12 | [9 empty] | 292 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | ARAMCO |  | NO | Open
|  | 89 | Later | S&L | SAU4005-G000-EG_-&MDB-00061 | System Description for Fuel oil system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-06-06 |  | 2025-04-09 |  | 2025-06-30 |  | 2025-04-24 |  | 2025-11-17 |  | 2025-06-06 | [9 empty] | 308 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | ARAMCO |  | NO | Open
|  | 90 | Later | S&L | SAU4005-G000-GH_-&MDB-00062 | System Description for Service water system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-07-23 |  | 2025-06-06 |  | 2025-08-14 |  | 2025-05-02 |  | 2026-01-20 |  | 2025-07-29 | [9 empty] | 324 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
|  | 91 | Later | S&L | SAU4005-G000-GK_-&MDB-00063 | System Description for Potable water system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-07-25 |  | 2025-07-15 |  | 2025-08-18 |  | 2025-07-08 |  | 2026-01-20 |  | 2025-08-18 | [9 empty] | 340 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
|  | 92 | Later | S&L | SAU4005-G000-QEA-&MDB-00064 | System Description for Compressed Air System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-07-17 |  | 2025-06-09 |  | 2025-08-07 |  | 2025-09-02 |  | 2025-12-24 |  | 2025-12-04 | [9 empty] | 308 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
|  | 93 | Later | S&L | SAU4005-G000-G__-&MDB-00065 | System Description for Service Water (Treated Waste Water) System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-09-30 |  | 2025-06-04 |  | 2025-10-28 |  | 2025-06-18 |  | 2026-01-12 |  | 2025-07-28 | [9 empty] | 308 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
|  | 94 | Later | S&L | SAU4005-G000-GHC-&MDB-00066 | System Description for DM Water Distribution System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-08-05 |  | 2025-05-16 |  | 2025-08-25 |  | 2025-05-30 |  | 2026-01-20 |  | 2025-08-18 | [9 empty] | 308 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
|  | 95 | Later | S&L | SAU4005-G000-LB_-&MDB-00067 | System Description for Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-24 |  | 2025-03-05 |  | 2025-04-11 |  | 2025-03-18 |  | 2025-05-19 |  | 2025-12-24 | [9 empty] | 347 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Combine
|  | 96 | Later | S&L | SAU4005-G000-LAB-&MDB-00069 | System Description for Feed Water System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-17 |  | 2025-02-28 |  | 2025-04-04 |  | 2025-03-14 |  | 2025-05-12 |  | 2025-10-02 | [9 empty] | 347 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Combine
|  | 97 | Later | S&L | SAU4005-G000-LC_-&MDB-00070 | System Description for Condensate System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | DOOSAN |  | IFA | IFD |  |  | 2025-03-17 |  | 2025-03-02 |  | 2025-04-04 |  | 2025-03-17 |  | 2025-05-12 |  | 2025-08-24 | [9 empty] | 347 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
|  | 98 | Later | S&L | SAU4005-G000-PG_-&MDB-00071 | System Description for Closed Circuit Cooling Water System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-08-12 |  | 2025-05-28 |  | 2025-09-02 |  | 2025-06-10 |  | 2026-03-02 |  | 2026-02-09 | [9 empty] | 308 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
|  | 99 | Later | S&L | SAU4005-G000-GMA-&MDB-00072 | System Description for Plant Drain System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-12-25 |  | 2025-12-19 |  | 2026-01-15 |  | 2026-01-21 |  | 2026-04-10 |  | 2026-04-05 | [9 empty] | 308 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Common
|  | 100 | Later | S&L | SAU4005-G000-QJA-&MDB-00073 | System Description for Industrial Gas System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-11-10 |  | 2025-08-13 |  | 2025-11-27 |  | 2025-05-12 |  | 2026-02-03 |  | 2025-09-21 | [9 empty] | 194 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 101 | Later | S&L | SAU4005-G000-SA_-&MDB-00339 | System Description for HVAC System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2026-07-08 |  | 2025-11-12 |  | 2026-07-28 |  | 2025-11-30 |  | 2026-08-25 |  | 2025-12-29 | [9 empty] | 421 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 102 | Later | S&L | SAU4005-G000-___-&BPC-00074 | Equipment list | A1 | Engineering | B-Overall technology | Yes | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFD |  |  | 2025-10-24 |  | 2025-10-27 |  | 2025-11-13 |  | 2025-11-12 |  | 2025-12-19 |  | 0 | [9 empty] | 674 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 103 | Later | S&L | SAU4005-G000-___-&MPA-00075 | Valve list | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFP |  |  | 2025-11-17 |  | 2025-09-23 |  | 2025-12-05 |  | 2025-10-08 |  | 2026-01-12 |  | 2025-10-27 | [9 empty] | 674 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 104 | Later | S&L | SAU4005-G000-___-&MPB-00076 | Specialties list | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFI | IFP | [10 empty] | 2026-10-22 |  |  |  | 2026-08-27 | [7 empty] | 674 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
| purpose changed | 105 | Later | S&L | SAU4005-G000-___-&MMB-00077 | Pipe Line List | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFD |  |  | 2025-11-10 |  | 2025-09-01 |  | 2025-11-28 |  | 2025-09-21 |  | 2026-04-05 |  | 2025-11-04 | [9 empty] | 674 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 106 | Later | S&L | SAU4005-G000-___-&BPL-00078 | Terminal Point List | A1 | Engineering | B-Overall technology | No | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFD |  |  | 2025-03-11 |  | 2025-01-24 |  | 2025-03-31 |  | 2025-03-22 |  | 2025-05-06 |  | 0 | [9 empty] | 463 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C1 | SEC, Aramco,NWC | S1,S2,S3,S4,S5,S6,S7,S8,S9,S10,S11 | NO | Common
|  | 107 | Later | S&L | SAU4005-G000-U__-&BTL-00079 | Plot Plan | A1 | Engineering | B-Overall technology | No | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFC |  |  | 2025-02-20 |  | 2025-02-06 |  | 2025-03-13 |  | 2025-03-04 |  | 2026-07-02 |  | 0 | [5 empty] | 2026-07-02 |  |  |  | 3054 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1 | SEC, Aramco,NWC | S2,S8 | Yes | Common
|  | 108 | Later | S&L | SAU4005-G000-UM_-&MLD-00080 | General Arrangement of GT & HRSG Area | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFC |  |  | 2025-03-11 |  | 2025-02-28 |  | 2025-03-31 |  | 2025-03-14 |  | 2026-07-28 |  | 2025-10-07 | [5 empty] | 2026-07-28 |  |  |  | 1182 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C2 | NO |  | NO | Common
|  | 109 | Later | S&L | SAU4005-G000-UST-&MLH-00082 | General Arrangement of Workshop and Warehouse Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-06-06 |  | 2025-04-06 |  | 2025-06-27 |  | 2025-04-22 |  | 2025-07-18 |  | 0 | [5 empty] | 2025-07-18 |  |  |  | 1004 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 111 | Later | S&L | SAU4005-G000-UEN-&MLD-00084 | General Arrangement of Fuel Gas Area | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-06-23 |  | 2025-06-13 |  | 2025-07-14 |  | 2025-03-07 |  | 2025-12-31 |  | 0 | [5 empty] | 2025-12-31 |  |  |  | 1092 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Open
|  | 112 | Later | S&L | SAU4005-G000-USC-&MLH-00085 | General Arrangement of Air Compressor Shed | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-04-29 |  | 2025-04-17 |  | 2025-05-16 |  | 2025-05-02 |  | 2025-12-17 |  | 2025-11-18 | [5 empty] | 2025-12-17 |  |  |  | 991 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
|  | 113 | Later | S&L | SAU4005-G000-UTG-&MLH-00086 | General Arrangement of Hydrogen Generation Plant including Electrical Room | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-06-19 |  | 2025-06-15 |  | 2025-07-08 |  | 2025-07-01 |  | 2026-01-13 |  | 2026-04-21 | [5 empty] | 2026-01-13 |  |  |  | 709 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 114 | Later | S&L | SAU4005-G000-MA_-&MLH-00087 | General Arrangement of Steam Turbine Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-04-02 |  | 2025-03-04 |  | 2025-04-22 |  | 2025-03-17 |  | 2026-01-23 |  | 2025-06-09 | [5 empty] | 2026-01-23 |  |  |  | 897 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C2 | NO |  | NO | Combine
|  | 115 | Later | S&L | SAU4005-G000-ULA-&MLD-00088 | General Arrangement of Boiler Feed Pump Area | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFC |  |  | 2025-09-02 |  | 2025-04-28 |  | 2025-09-22 |  | 2025-05-30 |  | 2026-03-22 |  | 2025-06-10 | [5 empty] | 2026-03-22 |  |  |  | 998 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Combine
|  | 116 | Later | S&L | SAU4005-G000-USG-&MLH-00090 | General Arrangement of Fire Water Pump House | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-05-13 |  | 2025-04-25 |  | 2025-05-30 |  | 2025-09-26 |  | 2025-06-23 |  | 2026-04-16 | [5 empty] | 2025-06-23 |  |  |  | 956 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
|  | 117 | Later | S&L | SAU4005-G000-URC-&MLD-00340 | General Arrangement of ACC Area | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFC |  |  | 2025-06-04 |  | 2025-05-16 |  | 2025-06-24 |  | 2025-05-30 |  | 2026-01-26 |  | 2026-02-16 | [5 empty] | 2026-01-26 |  |  |  | 875 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C2 | NO |  | NO | Combine
|  | 118 | Later | S&L | SAU4005-G000-UEM-&MLD-00345 | General Arrangemenmt of Fuel Oil Area | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-07-02 |  | 2025-05-01 |  | 2025-07-22 |  | 2025-05-15 |  | 2025-12-05 |  | 2025-12-07 | [5 empty] | 2025-12-05 |  |  |  | 1027 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Open
|  | 119 | Later | S&L | SAU4005-G000-UGD-&MTL-00359 | General Arrangement of DM and Service Water Pump Shed | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-05-19 |  | 2025-05-06 |  | 2025-06-06 |  | 2025-05-19 |  | 2025-07-04 |  | 2025-09-26 | [5 empty] | 2025-07-04 |  |  |  | 499 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 120 | Later | S&L | SAU4005-G000-UGA-&MTL-00356 | General Arrangement of Service water (Treated wastewater) Area | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-05-16 |  | 2025-05-20 |  | 2025-06-05 |  | 2025-07-01 |  | 2025-07-03 |  | 2025-09-26 | [5 empty] | 2025-07-03 |  |  |  | 509 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO
|  | 122 | Later | S&L | SAU4005-G000-SA_-&MLH-00093 | HVAC Layout for Steam Turbine Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-04-01 |  | 2025-12-15 |  | 2026-04-22 |  | 2025-12-18 |  | 2026-07-21 |  | 0 | [5 empty] | 2026-07-21 |  |  |  | 437 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 123 | Later | S&L | SAU4005-G000-SA_-&MLH-00094 | HVAC Layout for Main Electrical & Control Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-10-06 |  | 2025-07-19 |  | 2025-10-27 |  | 2025-08-04 |  | 2026-04-06 |  | 2025-12-23 | [5 empty] | 2026-04-06 |  |  |  | 434 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 124 | Later | S&L | SAU4005-G000-SA_-&MLH-00096 | HVAC Layout for Administration & Social Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-12-16 |  | 2025-07-06 |  | 2026-01-02 |  | 2025-07-21 |  | 2026-01-30 |  | 2026-03-31 | [5 empty] | 2026-01-30 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 125 | Later | S&L | SAU4005-G000-SA_-&MLH-00097 | HVAC Layout for Security and Control center | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-03-31 |  | 2026-01-13 |  | 2026-04-21 |  | 2026-02-01 |  | 2026-05-13 |  | 2026-03-05 | [5 empty] | 2026-05-13 |  |  |  | 288 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 126 | Later | S&L | SAU4005-G000-SA_-&MLH-00098 | HVAC Layout for Workshop and Warehouse Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-12-19 |  | 2025-11-12 |  | 2026-01-09 |  | 2025-11-26 |  | 2026-02-09 |  | 2026-02-18 | [5 empty] | 2026-02-09 |  |  |  | 389 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 127 | Later | S&L | SAU4005-G000-SA_-&MLH-00099 | HVAC Layout for Water and Effluent treatment System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-12-02 |  | 2025-11-11 |  | 2025-12-17 |  | 2025-07-21 |  | 2026-03-03 |  | 2026-01-11 | [5 empty] | 2026-03-03 |  |  |  | 389 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 128 | Later | S&L | SAU4005-G000-SA_-&MLH-00103 | HVAC Layout for GT Package MCC / Control room - 11, 12, 13 | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-03-02 |  | 2025-10-02 |  | 2026-03-25 |  | 2025-10-14 |  | 2026-06-30 |  | 2026-03-03 | [5 empty] | 2026-06-30 |  |  |  | 389 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 129 | Later | S&L | SAU4005-G000-SA_-&MLH-00104 | HVAC Layout for Fuel Gas Electrical Switchgear Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-03-26 |  | 2026-02-23 |  | 2026-04-14 |  | 2026-03-05 |  | 2026-07-21 |  | 2026-03-10 | [5 empty] | 2026-07-21 |  |  |  | 223 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 130 | Later | S&L | SAU4005-G000-SA_-&MLH-00106 | HVAC Layout for Hydrogen Generation Plant including Electrical Room | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-02-13 |  | 2026-02-23 |  | 2026-03-05 |  | 2026-03-10 |  | 2026-04-03 |  | 2026-04-12 | [5 empty] | 2026-04-03 |  |  |  | 288 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 131 | Later | S&L | SAU4005-G000-SA_-&MLH-00107 | HVAC Layout for Fire Station Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-02-17 |  | 2025-07-06 |  | 2026-03-05 |  | 2025-07-21 |  | 2026-03-31 |  | 2025-09-02 | [5 empty] | 2026-03-31 |  |  |  | 165 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 132 | Later | S&L | SAU4005-G000-SA_-&MLH-00109 | HVAC Layout for Unit MV/LV Electrical Switchgear building-11, 12, 13 | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-02-12 |  | 2025-08-27 |  | 2026-03-06 |  | 2025-07-21 |  | 2026-07-14 |  | 2025-11-19 | [5 empty] | 2026-07-14 |  |  |  | 288 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
|  | 133 | Later | S&L | SAU4005-G000-SA_-&MLH-00110 | HVAC Layout for STG and Auxiliary Boiler Electrical Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-05-28 |  | 2026-01-30 |  | 2026-06-15 |  | 2026-02-12 |  | 2026-07-10 |  | 2026-03-29 | [5 empty] | 2026-07-10 |  |  |  | 223 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
|  | 134 | Later | S&L | SAU4005-G000-SA_-&MLH-00112 | HVAC Layout for Main Gate House | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-02-26 |  | 2026-01-22 |  | 2026-03-20 |  | 2025-11-26 |  | 2026-04-14 |  | 2026-02-18 | [5 empty] | 2026-04-14 |  |  |  | 223 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 135 | Later | S&L | SAU4005-G000-SA_-&MLH-00113 | HVAC Layout for BOP Electrical Switchgear Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-02-23 |  | 2025-12-03 |  | 2026-03-13 |  | 2025-07-21 |  | 2026-04-06 |  | 2026-01-11 | [5 empty] | 2026-04-06 |  |  |  | 288 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 136 | Later | S&L | SAU4005-G000-SA_-&MLH-00116 | HVAC Layout for Search Facility & Vendor Center | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-11-17 |  | 2026-01-04 |  | 2025-12-08 |  | 2026-01-21 |  | 2026-04-30 |  | 0 | [5 empty] | 2026-04-30 |  |  |  | 288 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 137 | Later | S&L | SAU4005-G000-SA_-&MLH-00423 | HVAC Standard Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-07-18 |  | 2025-07-06 |  | 2025-08-07 |  | 2025-07-21 |  | 2025-09-08 |  | 2025-09-02 | [9 empty] | 133 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO
|  | 138 | Later | S&L | SAU4005-G000-SA_-&MLH-00442 | HVAC Layout for Electrical building for Water and Effluent treatment System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-03-20 |  | 2025-11-25 |  | 2026-04-09 |  | 2025-12-18 |  | 2026-05-07 |  | 2026-02-09 | [5 empty] | 2026-05-07 |  |  |  | 249 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
|  | 139 | Later | S&L | SAU4005-G000-EK_-&MDA-00119 | LB Isometrics Drawing for Fuel gas system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-03-18 |  |  |  | 2026-01-28 |  | 2026-01-15 |  | 2026-03-18 |  |  |  | 1976 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Open
|  | 140 | Later | S&L | SAU4005-G000-GH_-&MDA-00120 | LB Isometrics Drawing for Service water system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-06-24 |  |  |  | 2026-05-07 |  | 2025-12-17 |  | 2026-06-24 |  |  |  | 1328 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 141 | Later | S&L | SAU4005-G000-GK_-&MDA-00121 | LB Isometrics Drawing for Potable water system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-08-18 |  |  |  | 2026-06-30 |  | 2025-11-27 |  | 2026-08-18 |  |  |  | 1328 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 142 | Later | S&L | SAU4005-G000-QEA-&MDA-00122 | LB Isometrics Drawing for Compressed Air System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-03-03 |  |  |  | 2026-01-12 |  | 2025-12-31 |  | 2026-03-03 |  |  |  | 1490 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 143 | Later | S&L | SAU4005-G000-G__-&MDA-00123 | LB Isometrics Drawing for Service Water (Treated Waste Water) System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-08-25 |  |  |  | 2026-07-01 |  | 2025-12-17 |  | 2026-08-25 |  |  |  | 1490 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 144 | Later | S&L | SAU4005-G000-GHC-&MDA-00124 | LB Isometrics Drawing for DM Water Distribution System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-07-03 |  |  |  | 2026-05-18 |  | 2026-02-19 |  | 2026-07-03 |  |  |  | 1328 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 145 | Later | S&L | SAU4005-G000-MB_-&MDA-00125 | LB Isometrics Drawing for Gas Turbine Interconnecting Piping System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | Common |  | IFI | IFC | [10 empty] | 2026-05-20 |  |  |  | 2026-04-02 |  | 2026-02-21 |  | 2026-05-20 |  |  |  | 1328 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 146 | Later | S&L | SAU4005-G000-LBA-&MDA-00127 | LB Isometrics Drawing for High Pressure (HP) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFA | IFC |  |  | 2026-01-20 |  | 2025-10-28 |  | 2026-02-10 |  | 2025-11-16 |  | 2026-06-17 |  | 2026-03-02 | [5 empty] | 2026-06-17 |  |  |  | 2947 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 147 | Later | S&L | SAU4005-G000-LBC-&MDA-00128 | LB Isometrics Drawing for Cold Reheat (CRH) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFA | IFC |  |  | 2026-02-09 |  | 2025-10-28 |  | 2026-02-27 |  | 2025-11-16 |  | 2026-07-09 |  | 2026-03-02 | [5 empty] | 2026-07-09 |  |  |  | 2947 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 148 | Later | S&L | SAU4005-G000-LBB-&MDA-00129 | LB Isometrics Drawing for Hot Reheat (HRH) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFA | IFC |  |  | 2026-03-02 |  | 2025-10-28 |  | 2026-03-23 |  | 2025-11-16 |  | 2026-08-03 |  | 2026-01-15 | [5 empty] | 2026-08-03 |  |  |  | 3919 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 149 | Later | S&L | SAU4005-G000-LBD-&MDA-00130 | LB Isometrics Drawing for Low Pressure (LP) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFA | IFC |  |  | 2026-03-16 |  | 2025-10-28 |  | 2026-04-03 |  | 2025-11-16 |  | 2026-08-16 |  | 2026-04-05 | [5 empty] | 2026-08-16 |  |  |  | 2947 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 150 | Later | S&L | SAU4005-G000-LBG-&MDA-00131 | LB Isometrics Drawing for Auxiliary Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [10 empty] | 2026-04-28 |  |  |  | 2026-03-24 |  | 2026-02-12 |  | 2026-04-28 |  |  |  | 2462 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 151 | Later | S&L | SAU4005-G000-LAB-&MDA-00132 | LB Isometrics Drawing for Feed Water System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [10 empty] | 2026-05-26 |  |  |  | 2026-04-06 |  | 2026-04-21 |  | 2026-05-26 |  |  |  | 1976 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 152 | Later | S&L | SAU4005-G000-LC_-&MDA-00133 | LB Isometrics Drawing for Condensate System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [10 empty] | 2026-07-06 |  |  |  | 2026-05-15 |  | 2026-03-24 |  | 2026-07-06 |  |  |  | 2624 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 153 | Later | S&L | SAU4005-G000-PG_-&MDA-00134 | LB Isometrics Drawing for Closed Circuit Cooling Water System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-03-26 |  |  |  | 2026-03-19 |  | 2026-01-16 |  | 2026-03-26 |  |  |  | 1328 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 154 | Later | S&L | SAU4005-G000-QCA-&MDA-00135 | LB Isometrics Drawing for Chemical Feed System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-08-11 |  |  |  | 2026-06-24 |  | 2026-01-24 |  | 2026-08-11 |  |  |  | 1328 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 155 | Later | S&L | SAU4005-G000-EG_-&MDA-00136 | LB Isometrics Drawing for Fuel oil System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-03-09 |  |  |  | 2026-03-05 |  | 2026-01-15 |  | 2026-03-09 |  |  |  | 1490 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 156 | Later | S&L | SAU4005-G000-LBH-&MDA-00137 | LB Isometrics Drawing for Steam Vents & Drains System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [10 empty] | 2026-07-22 |  |  |  | 2026-06-04 |  | 2026-05-07 |  | 2026-07-22 |  |  |  | 1652 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 157 | Later | S&L | SAU4005-G000-GMA-&MDA-00138 | LB Isometrics Drawing for Plant Drain System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-10-08 |  |  |  | 2026-08-20 |  | 2025-11-27 |  | 2026-10-08 |  |  |  | 1166 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 158 | Later | S&L | SAU4005-G000-MA_-&MDA-00464 | LB Isometrics Drawing for STG Interconnecting System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [10 empty] | 2026-05-07 |  |  |  | 2026-04-30 |  | 2026-05-22 |  | 2026-05-07 |  |  |  | 1900 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
|  | 159 | Later | S&L | SAU4005-G000-LBA-&MDA-00147 | SB Isometrics Drawing for High Pressure (HP) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [10 empty] | 2026-05-25 |  |  |  | 2026-04-24 |  | 2026-04-02 |  | 2026-05-25 |  |  |  | 1166 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 160 | Later | S&L | SAU4005-G000-LBC-&MDA-00148 | SB Isometrics Drawing for Cold Reheat (CRH) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [10 empty] | 2026-06-23 |  |  |  | 2026-05-19 |  | 2026-04-06 |  | 2026-06-23 |  |  |  | 1166 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 161 | Later | S&L | SAU4005-G000-LBB-&MDA-00149 | SB Isometrics Drawing for Hot Reheat (HRH) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [10 empty] | 2026-06-03 |  |  |  | 2026-06-01 |  | 2026-05-08 |  | 2026-06-03 |  |  |  | 1166 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 163 | Later | S&L | SAU4005-G000-LBG-&MDA-00151 | SB Isometrics Drawing for Auxiliary Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [10 empty] | 2026-08-11 |  |  |  | 2026-06-23 |  | 2026-05-07 |  | 2026-08-11 |  |  |  | 1166 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 164 | Later | S&L | SAU4005-G000-LAB-&MDA-00152 | SB Isometrics Drawing for Feed Water System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [10 empty] | 2026-08-11 |  |  |  | 2026-06-30 |  | 2026-05-18 |  | 2026-08-11 |  |  |  | 1166 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 165 | Later | S&L | SAU4005-G000-LBW-&MDA-00158 | SB Isometrics Drawing for STG Interconnecting System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [10 empty] | 2026-10-06 |  |  |  | 2026-09-30 |  |  |  | 2026-10-06 |  |  |  | 1166 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 166 | Later | S&L | SAU4005-G000-LBH-&MDA-00160 | SB Isometrics Drawing for Steam Vents & Drains System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [10 empty] | 2026-10-08 |  |  |  | 2026-09-03 |  | 2026-06-09 |  | 2026-10-08 |  |  |  | 1166 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 167 | Later | S&L | SAU4005-G000-GH_-&MDA-00438 | SB Isometrics Drawing for Service water system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-05-27 |  |  |  | 2026-05-20 |  | 2026-04-16 |  | 2026-05-27 |  |  |  | 875 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
|  | 168 | Later | S&L | SAU4005-G000-GK_-&MDA-00439 | SB Isometrics Drawing for Potable Water System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-08-10 |  |  |  | 2026-08-03 |  | 2026-04-16 |  | 2026-08-10 |  |  |  | 810 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
|  | 169 | Later | S&L | SAU4005-G000-EK_-&MDA-00444 | SB Isometrics Drawing for Fuel gas system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-02-05 |  |  |  | 2026-01-29 |  | 2026-04-01 |  | 2026-02-05 |  |  |  | 907 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
|  | 170 | Later | S&L | SAU4005-G000-QEA-&MDA-00445 | SB Isometrics Drawing for Compressed Air System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-03-24 |  |  |  | 2026-03-17 |  | 2026-04-03 |  | 2026-03-24 |  |  |  | 891 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
|  | 172 | Later | S&L | SAU4005-G000-GHC-&MDA-00447 | SB Isometrics Drawing for DM Water Distribution System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-06-25 |  |  |  | 2026-06-18 |  | 2026-03-29 |  | 2026-06-25 |  |  |  | 891 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
|  | 173 | Later | S&L | SAU4005-G000-MB_-&MDA-00448 | SB Isometrics Drawing for Gas Turbine Interconnecting Piping System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | Common |  | IFI | IFC | [10 empty] | 2026-04-23 |  |  |  | 2026-04-16 |  | 2026-04-01 |  | 2026-04-23 |  |  |  | 875 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
|  | 175 | Later | S&L | SAU4005-G000-PG_-&MDA-00450 | SB Isometrics Drawing for Closed Circuit Cooling Water System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-05-11 |  |  |  | 2026-05-04 |  | 2026-03-24 |  | 2026-05-11 |  |  |  | 794 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
|  | 176 | Later | S&L | SAU4005-G000-EG_-&MDA-00451 | SB Isometrics Drawing for Fuel oil System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-03-24 |  |  |  | 2026-03-17 |  | 2026-03-19 |  | 2026-03-24 |  |  |  | 810 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
|  | 177 | Later | S&L | SAU4005-G000-QCA-&MDA-00452 | SB Isometrics Drawing for Chemical Feed System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-13 |  |  |  | 2026-04-06 |  | 2026-03-31 |  | 2026-04-13 |  |  |  | 680 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
| Document Owner changed | 178 | Later | S&L | SAU4005-G000-LC_-&MDA-00453 | SB Isometrics Drawing for Condensate System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [10 empty] | 2026-06-01 |  |  |  | 2026-05-25 |  | 2026-05-15 |  | 2026-06-01 |  |  |  | 680 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Combine
|  | 179 | Later | S&L | SAU4005-G000-LBA-&MDD-00162 | Stress Analysis for High Pressure (HP) and Cold Reheat (CRH) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | DOOSAN |  | IFA | IFD |  |  | 2026-02-19 |  | 2025-11-05 |  | 2026-03-12 |  | 2026-03-15 |  | 2026-04-17 |  | 2026-05-06 | [9 empty] | 3919 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 180 | Later | S&L | SAU4005-G000-LBB-&MDD-00164 | Stress Analysis for Hot Reheat (HRH) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | DOOSAN |  | IFA | IFD |  |  | 2026-03-30 |  | 2025-12-03 |  | 2026-04-17 |  | 2026-04-05 |  | 2026-05-25 |  | 2026-05-06 | [9 empty] | 3595 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 181 | Later | S&L | SAU4005-G000-LBD-&MDD-00165 | Stress Analysis for Low Pressure (LP) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | DOOSAN |  | IFA | IFD |  |  | 2026-04-13 |  | 2025-11-05 |  | 2026-05-01 |  | 2026-04-05 |  | 2026-06-08 |  | 2026-05-21 | [9 empty] | 2947 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 183 | Later | S&L | SAU4005-G000-LAB-&MDD-00167 | Stress Analysis for Feed Water System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | DOOSAN |  | IFA | IFD |  |  | 2026-05-04 |  | 2026-05-06 |  | 2026-05-22 |  | 0 |  | 2026-06-29 |  | 0 | [9 empty] | 3109 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 184 | Later | S&L | SAU4005-G000-LBH-&MDD-00169 | Stress Analysis for STG Drains & Vents System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | DOOSAN |  | IFA | IFD |  |  | 2026-07-27 |  | 2026-05-06 |  | 2026-08-14 |  | 0 |  | 2026-09-23 |  | 0 | [9 empty] | 2624 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 186 | Later | S&L | SAU4005-G000-EK_-&MDA-00171 | Piping Support Schedule for Fuel gas system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFD | [10 empty] | 2026-04-28 |  |  |  | 2026-03-03 |  | 2026-02-18 | [5 empty] | 1004 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 187 | Later | S&L | SAU4005-G000-GH_-&MDA-00172 | Piping Support Schedule for Service water system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFD | [10 empty] | 2026-08-21 |  |  |  | 2026-06-26 |  | 2026-03-20 | [5 empty] | 842 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 188 | Later | S&L | SAU4005-G000-GK_-&MDA-00173 | Piping Support Schedule for Potable water system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFD | [10 empty] | 2026-10-01 |  |  |  | 2026-08-06 |  | 2026-04-01 | [5 empty] | 842 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 189 | Later | S&L | SAU4005-G000-QEA-&MDA-00174 | Piping Support Schedule for Compressed Air System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFD | [10 empty] | 2026-04-27 |  |  |  | 2026-03-02 |  | 2026-02-01 | [5 empty] | 842 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 190 | Later | S&L | SAU4005-G000-G__-&MDA-00175 | Piping Support Schedule for Service water (Treated Waste Water) System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFD | [10 empty] | 2026-09-23 |  |  |  | 2026-07-29 |  | 2025-12-31 | [5 empty] | 680 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 191 | Later | S&L | SAU4005-G000-GHC-&MDA-00176 | Piping Support Schedule for DM Water Distribution System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFD | [10 empty] | 2026-07-31 |  |  |  | 2026-06-05 |  | 2026-02-11 | [5 empty] | 842 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 192 | Later | S&L | SAU4005-G000-LBA-&MDA-00178 | Piping Support for High Pressure (HP) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFA | IFC |  |  | 2026-07-27 |  | 2026-02-11 |  | 2026-08-14 |  | 2026-03-08 |  | 2026-12-24 |  | 2026-04-02 | [5 empty] | 2026-12-24 |  |  |  | 1490 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 193 | Later | S&L | SAU4005-G000-LBC-&MDA-00179 | Piping Support for Cold Reheat (CRH) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFA | IFC |  |  | 2026-07-27 |  | 2026-02-11 |  | 2026-08-14 |  | 2026-03-10 |  | 2026-12-24 |  | 0 | [5 empty] | 2026-12-24 |  |  |  | 1490 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 194 | Later | S&L | SAU4005-G000-LBB-&MDA-00180 | Piping Support for Hot Reheat (HRH) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFA | IFC |  |  | 2026-07-27 |  | 2026-03-06 |  | 2026-08-14 |  | 2026-03-29 |  | 2026-12-28 |  | 0 | [5 empty] | 2026-12-28 |  |  |  | 1490 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 195 | Later | S&L | SAU4005-G000-LBD-&MDA-00181 | Piping Support for Low Pressure (LP) Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFA | IFC |  |  | 2026-08-03 |  | 2026-03-24 |  | 2026-08-21 |  | 2026-04-12 |  | 2027-01-04 |  | 0 | [5 empty] | 2027-01-04 |  |  |  | 1490 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 196 | Later | S&L | SAU4005-G000-LBG-&MDA-00182 | Piping Support for Auxiliary Steam System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [10 empty] | 2026-08-20 |  |  |  | 2026-08-13 |  | 2026-04-07 |  | 2026-08-20 |  |  |  | 1328 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 197 | Later | S&L | SAU4005-G000-LAB-&MDA-00183 | Piping Support for Feed Water System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [10 empty] | 2026-08-24 |  |  |  | 2026-08-18 |  | 2026-05-12 |  | 2026-08-24 |  |  |  | 1328 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 198 | Later | S&L | SAU4005-G000-LC_-&MDA-00184 | Piping Support Schedule for Condensate System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [10 empty] | 2026-09-07 |  |  |  | 2026-09-01 |  | 2026-04-07 |  | 2026-09-07 |  |  |  | 1166 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 199 | Later | S&L | SAU4005-G000-EG_-&MDA-00185 | Piping Support Schedule for Fuel oil System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFD | [10 empty] | 2026-05-20 |  |  |  | 2026-03-25 |  | 2026-02-01 | [5 empty] | 680 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 200 | Later | S&L | SAU4005-G000-PG_-&MDA-00186 | Piping Support Schedule for Closed Circuit Cooling Water System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFD | [10 empty] | 2026-06-04 |  |  |  | 2026-04-09 |  | 2026-02-01 | [5 empty] | 1004 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 203 | Later | S&L | SAU4005-G000-LBW-&MDA-00190 | Piping Support Schedule for STG Interconnecting System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [10 empty] | 2026-11-13 |  |  |  | 2026-11-06 |  |  |  | 2026-11-13 |  |  |  | 1166 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 204 | Later | S&L | SAU4005-G000-LBH-&MDA-00191 | Piping Support for Steam Vents & Drains System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [10 empty] | 2026-11-19 |  |  |  | 2026-11-12 |  | 2026-05-12 |  | 2026-11-19 |  |  |  | 1166 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 205 | Later | S&L | SAU4005-G000-GMA-&MDA-00192 | Piping Support Schedule for Plant Drain System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFI | IFD | [10 empty] | 2026-11-04 |  |  |  | 2026-09-09 |  | 2026-03-20 | [5 empty] | 680 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 206 | Later | S&L | SAU4005-G000-MB_-&MDA-00465 | Piping Support Schedule for GTG Interconnecting System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | Common |  | IFI | IFC | [10 empty] | 2027-04-14 |  |  |  | 2027-04-07 |  | 2026-03-09 |  | 2027-04-14 |  |  |  | 1900 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
|  | 207 | Later | S&L | SAU4005-G000-___-&BTA-00202 | 3D Model Concept | A1 | Engineering | B-Overall technology | Yes | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFD |  |  | 2025-03-27 |  | 2025-03-07 |  | 2025-04-16 |  | 2025-03-20 |  | 2025-05-26 |  | 2025-04-08 | [9 empty] | 515 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C1 | NO |  | NO | Common
|  | 208 | Later | S&L | SAU4005-G000-___-&BTB-00354 | 3D Model | A1 | Engineering | B-Overall technology | No | PIPING&PLANT DESIGN | PIPING | Common |  | IFA | IFD |  |  |  |  | 2025-04-25 |  |  |  | 2025-08-25 |  | 2025-07-07 |  | 0 | [9 empty] | 3600 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C3 | NO |  | NO | Common
|  | 209 | Later | S&L | SAU4005-G000-___-&BDD-00203 | Hazardous Area Classification | A1 | Engineering | B-Overall technology | Yes | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFD |  |  | 2026-10-01 |  | 2025-07-16 |  | 2026-10-23 |  | 2025-08-03 |  | 2026-11-30 |  | 0 | [9 empty] | 1338 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 210 | Later | S&L | SAU4005-G000-___-&BDC-00204 | Plant Operation and Control Philosophy | A1 | Engineering | B-Overall technology | Yes | MECH&PROCESS&WTP | PROCESS | Common |  | IFA | IFD |  |  | 2027-02-02 |  |  |  | 2027-02-22 |  |  |  | 2027-03-31 | [11 empty] | 1607 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Common
|  | 211 | Later | S&L | SAU4005-G000-___-&MDD-00205 | Piping and Valve Design Table Report | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | PIPING&PLANT DESIGN | PIPING | Common |  | IFA | IFD |  |  | 2025-08-07 |  | 2025-07-17 |  | 2025-08-29 |  | 2025-07-31 |  | 2025-10-09 |  | 2025-08-31 | [9 empty] | 1315 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 213 | Later | S&L | SAU4005-G000-MB_-&MEC-00294 | Technical Specifications for Gas Turbine, Generator & Auxiliaries | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | DOOSAN |  | IFI | IFP | [10 empty] | 2025-07-14 |  |  |  | 2025-05-19 |  | 2025-04-15 | [5 empty] | 2000 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | YES
|  | 214 | Later | S&L | SAU4005-G000-MA_-&MEC-00208 | Technical Specifications for Steam Turbine and Generator | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | DOOSAN |  | IFI | IFP | [10 empty] | 2025-09-09 |  |  |  | 2025-07-15 |  | 2025-06-05 | [5 empty] | 2000 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | YES
|  | 215 | Later | S&L | SAU4005-G000-HA_-&MEC-00209 | Technical Specifications for HRSG and Bypass Stack | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | DOOSAN |  | IFI | IFP | [10 empty] | 2025-07-01 |  |  |  | 2025-05-06 |  | 2025-04-16 | [5 empty] | 2000 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | YES
|  | 216 | Later | S&L | SAU4005-G000-___-&MEC-00210 | Technical Specifications for Misc. sump pumps | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-11-03 |  | 2025-10-14 |  | 2025-11-21 |  | 2025-10-30 |  | 2025-11-28 |  | 2025-12-02 | [9 empty] | 635 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO
|  | 217 | Later | S&L | SAU4005-G000-MAN-&MEC-00211 | Technical Specifications for Steam Bypass system | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | DOOSAN |  | IFA | IFP |  |  | 2025-08-08 |  | 2025-08-22 |  | 2025-09-01 |  | 2025-09-07 |  | 2025-10-10 |  | 2025-10-22 | [9 empty] | 428 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
|  | 218 | Later | S&L | SAU4005-G000-___-&MEC-00212 | Technical Specifications for GRP Piping | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | PIPING&PLANT DESIGN | PIPING | SEPCOIII |  | IFA | IFP |  |  | 2025-08-08 |  | 2025-05-14 |  | 2025-09-01 |  | 2025-05-29 |  | 2025-09-08 |  | 2025-06-12 | [9 empty] | 619 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 219 | Later | S&L | SAU4005-G000-QJ_-&MEC-00213 | Technical Specifications for Industrial Gas System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-08-19 |  | 2025-07-29 |  | 2025-09-09 |  | 2025-03-12 |  | 2025-09-16 |  | 2025-09-26 | [9 empty] | 256 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 220 | Later | S&L | SAU4005-G000-QJ_-&MEC-00214 | Technical Specifications for Hydrogen Generation Plant | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-07-15 |  | 2025-06-04 |  | 2025-08-04 |  | 2025-06-19 |  | 2025-08-11 |  | 2025-08-12 | [9 empty] | 256 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 221 | Later | S&L | SAU4005-G000-___-&MEC-00215 | Technical Specifications for Field Fabricated Tank | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-05-28 |  | 2025-04-14 |  | 2025-06-17 |  | 2025-04-29 |  | 2025-06-24 |  | 0 | [9 empty] | 602 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 222 | Later | S&L | SAU4005-G000-___-&MEC-00216 | Technical Specifications for Shop fabricated Tank | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFP |  |  | 2025-08-21 |  | 2025-07-24 |  | 2025-09-11 |  | 2025-08-11 |  | 2025-10-16 |  | 2025-08-24 | [9 empty] | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 223 | Later | S&L | SAU4005-G000-G__-&MEC-00217 | Technical Specifications for Water and Effluent Treatment System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-05-19 |  | 2025-04-08 |  | 2025-06-06 |  | 2025-05-30 |  | 2025-06-13 |  | 2025-07-28 | [9 empty] | 1033 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NWC |  | NO | Common
|  | 224 | Later | S&L | SAU4005-G000-EK_-&MEC-00219 | Technical Specifications for Fuel Gas Conditioning System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-02-07 |  | 2025-02-17 |  | 2025-02-27 |  | 2025-03-23 |  | 2025-03-06 |  | 2025-07-01 | [9 empty] | 476 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | ARAMCO |  | NO | Open
|  | 225 | Later | S&L | SAU4005-G000-PG_-&MEC-00220 | Technical Specifications for CCCW heat exchanger (Fin Fan Cooler) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-05-27 |  | 2025-04-20 |  | 2025-06-16 |  | 2025-05-05 |  | 2025-06-23 |  | 2025-06-10 | [9 empty] | 683 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 226 | Later | S&L | SAU4005-G000-___-&MEC-00223 | Technical Specifications for Miscellaneous Horizontal pump | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFP |  |  | 2025-06-04 |  | 2025-05-23 |  | 2025-06-24 |  | 2025-06-06 |  | 2025-07-30 |  | 2025-07-10 | [9 empty] | 528 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 227 | Later | S&L | SAU4005-G000-___-&MEC-00224 | Technical Specifications for Miscellaneous Vertical pump | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-07-02 |  | 2025-06-09 |  | 2025-07-22 |  | 2025-06-24 |  | 2025-07-29 |  | 2025-07-29 | [9 empty] | 528 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 228 | Later | S&L | SAU4005-G000-STG-&MEC-00225 | Technical Specifications for Laboratory Equipment | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2026-01-12 |  | 2025-12-01 |  | 2026-02-03 |  | 2025-12-21 |  | 2026-02-10 |  | 0 | [9 empty] | 188 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 229 | Later | S&L | SAU4005-G000-SM_-&MEC-00226 | Technical Specifications for Cranes & Hoists | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-11-25 |  | 2025-09-08 |  | 2025-12-15 |  | 2025-09-24 |  | 2025-12-22 |  | 2025-11-30 | [9 empty] | 217 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 230 | Later | S&L | SAU4005-G000-QEA-&MEC-00228 | Technical Specifications for Compressed Air System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-05-29 |  | 2025-04-17 |  | 2025-06-18 |  | 2025-05-02 |  | 2025-06-25 |  | 2025-07-28 | [9 empty] | 761 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 231 | Later | S&L | SAU4005-G000-EK_-&MEC-00229 | Technical Specifications for Fuel Gas Compressors | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-01-24 |  | 2025-02-16 |  | 2025-02-13 |  | 2025-03-07 |  | 2025-02-20 |  | 2025-06-03 | [9 empty] | 641 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C1,C2 | NO |  | NO | Open
|  | 232 | Later | S&L | SAU4005-G000-L__-&MEC-00230 | Technical Specifications for Power Cycle Pumps (BFP,CEP) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | DOOSAN |  | IFA | IFP |  |  | 2025-02-27 |  | 2025-01-24 |  | 2025-03-19 |  | 2025-03-18 |  | 2025-04-24 |  | 2025-04-22 | [9 empty] | 1555 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
|  | 233 | Later | S&L | SAU4005-G000-QC_-&MEC-00232 | Technical Specifications for Chemical Feed System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-07-17 |  | 2025-05-28 |  | 2025-08-06 |  | 2025-06-10 |  | 2025-08-13 |  | 2025-07-25 | [9 empty] | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
|  | 234 | Later | S&L | SAU4005-G000-___-&MEC-00234 | Technical Specifications for Safety valve | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFP |  |  | 2025-11-13 |  | 2025-07-15 |  | 2025-12-03 |  | 2025-08-21 |  | 2026-01-08 |  | 2025-09-21 | [9 empty] | 113 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 235 | Later | S&L | SAU4005-G000-QH_-&MEC-00235 | Technical Specifications for Auxiliary Boiler | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-04-22 |  | 2025-03-28 |  | 2025-05-12 |  | 2025-04-11 |  | 2025-05-19 |  | 2025-05-29 | [9 empty] | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
|  | 236 | Later | S&L | SAU4005-G000-SA_-&MEC-00236 | Technical Specifications for HVAC System - Air Conditioner Units | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-09-10 |  | 2025-08-31 |  | 2025-10-03 |  | 2025-09-16 |  | 2025-10-10 |  | 0 | [9 empty] | 525 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 237 | Later | S&L | SAU4005-G000-SA_-&MEC-00237 | Technical Specifications for HVAC System Fans | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-09-09 |  | 2025-09-01 |  | 2025-09-30 |  | 2025-10-12 |  | 2025-10-09 |  | 2025-11-20 | [9 empty] | 525 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 238 | Later | S&L | SAU4005-G000-SA_-&MEC-00238 | Technical Specifications for HVAC Ducting and Accessories | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-12-18 |  | 2025-09-27 |  | 2026-01-07 |  | 2025-10-21 |  | 2026-01-15 |  | 2025-11-20 | [9 empty] | 301 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 239 | Later | S&L | SAU4005-G000-___-&MEC-00239 | Technical Specifications for Pipe Hangers & Supports | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFP |  |  | 2025-09-10 |  | 2025-06-17 |  | 2025-10-03 |  | 2025-07-01 |  | 2025-11-07 |  | 2025-07-31 | [9 empty] | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 240 | Later | S&L | SAU4005-G000-___-&MEC-00240 | Technical Specifications for Power Cycle Valves | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | DOOSAN |  | IFA | IFP |  |  | 2025-07-31 |  | 2025-07-24 |  | 2025-08-21 |  | 2025-08-11 |  | 2025-09-24 |  | 2025-08-29 | [9 empty] | 674 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
|  | 242 | Later | S&L | SAU4005-G000-___-&MEC-00242 | Technical Specifications for Butterfly Valves | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-11-24 |  | 2025-09-07 |  | 2025-12-12 |  | 2025-09-24 |  | 2025-12-19 |  | 2025-10-14 | [9 empty] | 609 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 243 | Later | S&L | SAU4005-G000-___-&MEC-00243 | Technical Specifications for Piping Specialties | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | PIPING&PLANT DESIGN | PIPING | Common |  | IFA | IFP |  |  | 2025-09-26 |  | 2025-09-09 |  | 2025-10-23 |  | 2025-10-14 |  | 2025-11-28 |  | 2025-10-27 | [9 empty] | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 244 | Later | S&L | SAU4005-G000-GR_-&MEC-00244 | Technical Specifications for Sewage Treatment Plant | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-11-18 |  | 2025-12-01 |  | 2025-12-08 |  | 0 |  | 2025-12-15 |  | 2026-02-18 | [9 empty] | 256 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 245 | Later | S&L | SAU4005-G000-GNB-&MEC-00245 | Technical Specifications for Oil Water Separator | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-08-29 |  | 2025-08-06 |  | 2025-09-18 |  | 2025-08-26 |  | 2025-09-25 |  | 2025-09-09 | [9 empty] | 227 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 246 | Later | S&L | SAU4005-G000-___-&MEC-00247 | Technical Specifications for Alloy Piping | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | PIPING&PLANT DESIGN | PIPING | Common |  | IFA | IFP |  |  | 2026-03-18 |  | 2025-07-15 |  | 2026-04-08 |  | 2025-07-29 |  | 2026-05-14 |  | 2025-08-15 | [9 empty] | 194 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 247 | Later | S&L | SAU4005-G000-XTA-&MEC-00248 | Technical Specifications for Painting and Coating | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFP |  |  | 2025-02-17 |  | 2025-01-27 |  | 2025-03-10 |  | 2025-02-19 |  | 2025-04-15 |  | 2026-02-17 | [9 empty] | 547 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 248 | Later | S&L | SAU4005-G000-___-&MEC-00249 | Technical Specifications for Thermal Insulation | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFP |  |  | 2025-12-17 |  | 2025-02-18 |  | 2026-01-06 |  | 2025-03-30 |  | 2026-02-13 |  | 2026-02-01 | [9 empty] | 194 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 249 | Later | S&L | SAU4005-G000-PA_-&MEC-00251 | Technical Specifications for Air Cooled Condenser | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | DOOSAN |  | IFA | IFP |  |  | 2025-04-10 |  | 2025-01-24 |  | 2025-04-30 |  | 2025-04-01 |  | 2025-06-05 |  | 2025-07-01 | [9 empty] | 638 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1,C2 | NO |  | NO | Combine
|  | 250 | Later | S&L | SAU4005-G000-SM_-&MEC-00252 | Technical Specifications for STG Building Overhead Crane | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-02-21 |  | 2025-03-06 |  | 2025-03-13 |  | 0 |  | 2025-03-20 |  | 2025-04-17 | [9 empty] | 496 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
|  | 251 | Later | S&L | SAU4005-G000-PG_-&MEC-00403 | Technical Specifications for Closed Circuit Cooling Water Pumps | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-06-23 |  | 2025-05-13 |  | 2025-07-11 |  | 2025-05-27 |  | 2025-07-18 |  | 2025-06-10 | [9 empty] | 227 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO
|  | 252 | Later | S&L | SAU4005-G000-EG_-&MEC-00404 | Technical Specifications for Fuel Oil System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-07-23 |  | 2025-06-27 |  | 2025-08-12 |  | 2025-04-29 |  | 2025-08-20 |  | 2025-07-30 | [9 empty] | 259 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO
|  | 253 | Later | S&L | SAU4005-G000-LC_-&MEC-00433 | Technical Specification for Cartridge Filter | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-08-29 |  | 2025-07-29 |  | 2025-09-18 |  | 2025-08-12 |  | 2025-09-25 |  | 2025-08-27 | [9 empty] | 130 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO
|  | 254 | Later | S&L | SAU4005-G000-___-&MEC-00434 | Technical Specification for HAZID , Hazop and SIL | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | Common |  | IFA | IFP |  |  | 2025-09-12 |  | 2025-08-08 |  | 2025-10-07 |  | 2025-08-29 |  | 2025-11-14 |  | 2025-09-17 | [9 empty] | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 255 | Later | S&L | SAU4005-G000-PG_-&MEC-00435 | Technical Specification for Plates type Heatexchanger | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-11-25 |  | 2025-09-06 |  | 2025-12-15 |  | 2025-09-23 |  | 2025-12-22 |  | 2025-10-12 | [9 empty] | 162 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
|  | 256 | Later | S&L | SAU4005-G000-LB_-&MEC-00436 | Technical Specifications for Silencer | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | DOOSAN |  | IFA | IFP |  |  | 2025-10-20 |  | 2025-07-25 |  | 2025-11-11 |  | 2025-08-27 |  | 2025-12-17 |  | 2025-09-11 | [9 empty] | 130 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO
|  | 257 | Later | S&L | SAU4005-G000-LCM-&MEC-00472 | Technical Specification For Atmospheric Flash Tank Transfer Pumps | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | DOOSAN |  | IFA | IFP |  |  | 2025-06-25 |  | 2025-05-27 |  | 2025-07-15 |  | 2025-06-09 |  | 2025-08-20 |  | 2025-06-26 | [9 empty] | 528 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 258 | Later | S&L | SAU4005-G000-B__-&EDB-00500 | Electrical Design Criteria Document | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFA | IFD |  |  | 2025-03-13 |  | 2025-02-28 |  | 2025-04-02 |  | 2025-03-12 |  | 2025-05-08 |  | 2025-11-02 | [9 empty] | 764 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1 | NO |  | NO | Common
|  | 259 | Later | S&L | SAU4005-G000-B__-&EFA-00501 | Overall Key Single Line Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-03-27 |  | 2025-03-02 |  | 2025-04-16 |  | 2025-03-13 |  | 2026-05-22 |  | 2026-04-12 | [9 empty] | 434 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1,C4 | SEC | S1,S2,S3,S4,S5,S6,S7,S8,S9,S10,S11 | Yes | Common
|  | 260 | Later | S&L | SAU4005-G000-B__-&EFA-00502 | Single Line Diagram of Relay & Metering Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-05-01 |  | 2025-04-07 |  | 2025-05-22 |  | 2025-08-26 |  | 2026-06-22 |  | 0 | [9 empty] | 434 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1,C2,C4 | SEC | S1,S2,S3,S4,S5,S6,S7,S8,S9,S10,S11 | Yes | Common
|  | 261 | Later | S&L | SAU4005-G000-B__-&EFA-00503 | Single Line Diagram of MV Switchgear | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-05-28 |  | 2025-04-02 |  | 2025-06-17 |  | 2025-04-21 |  | 2026-06-22 |  | 2025-06-10 | [9 empty] | 343 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1,C2,C4 | SEC | S1,S2,S3,S4,S5 | Yes | Common
|  | 262 | Later | S&L | SAU4005-G000-B__-&EFA-00504 | Single Line Diagram of DC & UPS System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-09-05 |  | 2025-07-19 |  | 2025-09-24 |  | 2025-08-04 |  | 2026-07-14 |  | 2026-01-08 | [9 empty] | 343 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C2 | NO |  | NO | Common
|  | 263 | Later | S&L | SAU4005-G000-B__-&EFA-00676 | Single Line Diagram of LV Switchgear | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-09-15 |  | 2025-07-08 |  | 2025-10-07 |  | 2025-08-19 |  | 2026-06-22 |  | 2025-09-16 | [9 empty] | 343 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Common
|  | 264 | Later | S&L | SAU4005-G000-B__-&EFA-00677 | Single Line Diagram of BSEDG | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | DOOSAN |  | IFA | IFD |  |  | 2025-09-01 |  | 2025-08-26 |  | 2025-09-19 |  | 2025-10-30 |  | 2025-11-03 |  | 0 | [9 empty] | 343 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C2 | NO |  | NO | Common
|  | 265 | Later | S&L | SAU4005-G000-CEJ-&EEC-00678 | Technical specification for Fault Monitoring System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-11-24 |  | 2025-09-23 |  | 2025-12-12 |  | 2025-09-16 |  | 2025-12-19 |  | 2025-12-08 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES |  |  |  |  | Common
|  | 266 | Later | S&L | SAU4005-G000-B__-&EEC-00679 | Technical specification for Cathodic Protection system | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-07-01 |  | 2025-04-29 |  | 2025-07-21 |  | 2025-05-12 |  | 2025-07-28 |  | 2025-10-09 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 267 | Later | S&L | SAU4005-G000-B__-&EEC-00680 | Technical specification for EHV Cable | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-08-18 |  | 2025-07-04 |  | 2025-09-08 |  | 2025-07-17 |  | 2025-09-15 |  | 2025-07-29 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO |  |  |  |  | Common
|  | 268 | Later | S&L | SAU4005-G000-B__-&EDD-00505 | Load Flow Study of Power Plant | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-03 |  | 2025-09-23 |  | 2025-12-23 |  | 2025-10-08 |  | 2026-06-22 |  | 2026-06-01 | [9 empty] | 1095 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1,C2,C4 | SEC | S1,S2,S3,S4,S5,S6 | NO | Common
|  | 269 | Later | S&L | SAU4005-G000-B__-&EDD-00506 | Transient Analysis of Power Plant | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-06 |  | 2026-05-28 |  | 2026-02-25 |  | 0 |  | 2026-07-20 |  | 0 | [9 empty] | 1095 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1,C2,C4 | SEC | S1,S2,S3,S4,S5,S6 | NO | Common
|  | 270 | Later | S&L | SAU4005-G000-B__-&EDD-00507 | Motor Starting Study of Power Plant | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-15 |  | 2025-09-23 |  | 2026-01-02 |  | 2025-10-15 |  | 2026-06-30 |  | 0 | [9 empty] | 1095 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Common
|  | 271 | Later | S&L | SAU4005-G000-B__-&EDD-00508 | Short Circuit Study of Power Plant | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-03 |  | 2025-09-23 |  | 2025-12-23 |  | 2025-10-23 |  | 2026-06-22 |  | 2026-04-28 | [9 empty] | 1095 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1,C2,C4 | SEC | S1,S2,S3,S4,S5,S6 | NO | Common
|  | 272 | Later | S&L | SAU4005-G000-B__-&EED-00509 | Relay Setting Calculation of Power Plant | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2026-06-29 |  |  |  | 2026-07-20 |  |  |  | 2026-11-13 | [11 empty] | 2300 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C1,C2,C4 | SEC | S1,S2,S3,S4,S5,S6 | NO | Common
|  | 273 | Later | S&L | SAU4005-G000-BAT-&EED-00510 | Sizing Calculation for Generator Transformer | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-06-06 |  | 2025-04-04 |  | 2025-06-30 |  | 2025-04-20 |  | 2025-08-22 |  | 2025-11-04 | [9 empty] | 690 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1,C2,C4 | SEC | S1 | NO | Common
|  | 274 | Later | S&L | SAU4005-G000-BAC-&EED-00511 | Sizing Calculation for Generator Circuit Breaker | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-04-15 |  | 2025-04-07 |  | 2025-05-06 |  | 2025-04-20 |  | 2025-09-22 |  | 2025-12-25 | [9 empty] | 651 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
|  | 275 | Later | S&L | SAU4005-G000-BAA-&EED-00512 | Sizing Calculation for Iso Phase Bus duct | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-05-01 |  | 2025-04-10 |  | 2025-05-22 |  | 2025-04-20 |  | 2026-02-26 |  | 2025-10-14 | [9 empty] | 651 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
|  | 276 | Later | S&L | SAU4005-G000-BBT-&EED-00513 | Sizing Calculation for Unit Auxiliary Transformer | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-06-26 |  | 2025-05-29 |  | 2025-07-15 |  | 2025-06-09 |  | 2026-02-02 |  | 2026-01-04 | [9 empty] | 965 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Common
|  | 277 | Later | S&L | SAU4005-G000-BFT-&EED-00514 | Sizing Calculation for LV Auxiliary Transformer | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-06-12 |  | 2025-05-30 |  | 2025-07-01 |  | 2025-07-15 |  | 2026-01-19 |  | 2025-10-26 | [9 empty] | 807 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 278 | Later | S&L | SAU4005-G000-BBA-&EED-00515 | Sizing Calculation for MV Power Cable | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-08-04 |  | 2025-09-23 |  | 2025-08-25 |  | 2025-10-12 |  | 2026-02-26 |  | 2025-12-25 | [9 empty] | 651 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | SEC | S1 | NO | Common
|  | 279 | Later | S&L | SAU4005-G000-BFA-&EED-00516 | Sizing Calculation for LV Power Cable (sample) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-08-25 |  | 2025-06-13 |  | 2025-09-15 |  | 2025-07-01 |  | 2026-02-26 |  | 2025-07-22 | [9 empty] | 651 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 280 | Later | S&L | SAU4005-G000-BUA-&EED-00517 | Sizing Calculation for DC System (Load Duty Cycle) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-08-13 |  | 2025-07-13 |  | 2025-09-04 |  | 2025-06-09 |  | 2026-06-22 |  | 2025-12-04 | [9 empty] | 651 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Common
|  | 281 | Later | S&L | SAU4005-G000-BR_-&EED-00518 | Sizing Calculation for UPS System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-08-05 |  | 2025-07-08 |  | 2025-08-28 |  | 2025-06-09 |  | 2026-02-02 |  | 2025-10-13 | [9 empty] | 761 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 282 | Later | S&L | SAU4005-G000-MJ_-&EED-00519 | Sizing Calculation for BSEDG | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | DOOSAN |  | IFA | IFD |  |  | 2025-03-25 |  | 2025-03-13 |  | 2025-04-14 |  | 2025-03-22 |  | 2025-05-22 |  | 2026-02-18 | [9 empty] | 651 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
|  | 283 | Later | S&L | SAU4005-G000-BAU-&EED-00520 | Sizing Calculation for Grounding System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-06-20 |  | 2025-05-19 |  | 2025-07-09 |  | 2025-06-02 |  | 2026-04-29 |  | 2025-09-07 | [9 empty] | 492 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1 | SEC | S1 | NO | Common
|  | 284 | Later | S&L | SAU4005-G000-BAU-&EED-00521 | Sizing Calculation for Lightning Protection System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-09-22 |  | 2025-07-13 |  | 2025-10-17 |  | 2025-08-11 |  | 2026-02-05 |  | 2025-12-29 | [9 empty] | 492 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 285 | Later | S&L | SAU4005-G000-BMA-&EED-00522 | Sizing Calculation for Current Transformer | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-08-11 |  | 2025-07-28 |  | 2025-08-28 |  | 2025-07-31 |  | 2026-07-16 |  | 2025-08-24 | [9 empty] | 492 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Common
|  | 286 | Later | S&L | SAU4005-G000-B__-&EED-00523 | Indoor Lighting Calculation | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-10 |  | 2025-10-09 |  | 2025-12-30 |  | 2025-10-26 |  | 2026-04-28 |  | 0 | [9 empty] | 645 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Common
|  | 287 | Later | S&L | SAU4005-G000-B__-&EED-00524 | Outdoor Lighting Calculation | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-03 |  | 2025-10-11 |  | 2026-02-23 |  | 0 |  | 2026-05-25 |  | 0 | [9 empty] | 645 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Common
|  | 288 | Later | S&L | SAU4005-G000-BUA-&EED-00719 | Sizing Calculation for 125V DC System (Load Duty Cycle) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-11 |  | 2025-08-12 |  | 2025-12-01 |  | 2025-09-16 |  | 2025-12-29 |  | 2025-11-26 | [9 empty] | 230 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
|  | 289 | Later | S&L | SAU4005-G000-UAA-&ELD-00525 | General Arrangement of EHV Cable corridor (upto plant boundary) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-05-14 |  | 2025-04-03 |  | 2025-06-03 |  | 2025-04-18 |  | 2025-12-26 |  | 0 | [5 empty] | 2025-12-26 |  |  |  | 2267 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1,C2,C4 | SEC | S1,S2,S8 | NO | Common
|  | 290 | Later | S&L | SAU4005-G000-UBF-&ELD-00526 | General Arrangement of Transformer Yard Area | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-07-31 |  | 2025-07-26 |  | 2025-08-21 |  | 2025-09-28 |  | 2026-04-29 |  | 2025-11-19 | [5 empty] | 2026-04-29 |  |  |  | 1898 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C2 | NO |  | NO | Common
|  | 291 | Later | S&L | SAU4005-G000-UBA-&ELH-00527 | Equipment Layout for GT Package MCC / Control room - 11, 12, 13 | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFA | IFC |  |  | 2025-07-02 |  | 2025-06-12 |  | 2025-08-05 |  | 2025-06-27 |  | 2026-04-13 |  | 2026-04-19 | [5 empty] | 2026-04-13 |  |  |  | 2267 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Open
|  | 292 | Later | S&L | SAU4005-G000-UCA-&ELH-00528 | Equipment Layout for Main Electrical & Control Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-04-30 |  | 2025-05-05 |  | 2025-05-22 |  | 2025-05-14 |  | 2026-02-12 |  | 2025-08-18 | [5 empty] | 2026-02-12 |  |  |  | 2666 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Common
|  | 293 | Later | S&L | SAU4005-G000-UBA-&ELH-00529 | Equipment Layout for Unit MV/LV Electrical Switchgear building-11, 12, 13 | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFA | IFC |  |  | 2025-08-18 |  | 2025-06-20 |  | 2025-09-08 |  | 2025-06-18 |  | 2026-05-26 |  | 2025-09-07 | [5 empty] | 2026-05-26 |  |  |  | 1762 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C2 | NO |  | NO | Combine
|  | 294 | Later | S&L | SAU4005-G000-UBA-&ELH-00530 | Equipment Layout for STG and Auxiliary Boiler Electrical Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFA | IFC |  |  | 2025-08-12 |  | 2025-06-13 |  | 2025-09-03 |  | 2025-06-27 |  | 2026-05-13 |  | 2025-09-28 | [5 empty] | 2026-05-13 |  |  |  | 1500 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Combine
|  | 295 | Later | S&L | SAU4005-G000-UBA-&ELH-00722 | Equipment Layout for BOP-1 Electrical Switchgear Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-11-26 |  | 2025-08-14 |  | 2025-12-16 |  | 0 |  | 2026-01-13 |  | 2025-10-12 | [5 empty] | 2026-01-13 |  |  |  | 858 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES |  |  |  |  | Open
|  | 296 | Later | S&L | SAU4005-G000-B__-&EMA-00533 | Cable Interconnection document for GT & Auxiliaries (Termination details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-08-19 |  |  |  | 2026-06-03 |  |  |  | 2026-08-19 |  |  |  | 1814 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 297 | Later | S&L | SAU4005-G000-B__-&EMA-00692 | Cable Interconnection document for ST & Auxiliaries (Termination details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFI | IFC | [10 empty] | 2026-06-30 |  |  |  | 2026-06-23 |  |  |  | 2026-06-30 |  |  |  | 1817 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 298 | Later | S&L | SAU4005-G000-B__-&EMA-00693 | Cable Interconnection document for HRSG and Auxiliaries (Termination details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-07-31 |  |  |  | 2026-07-24 |  |  |  | 2026-07-31 |  |  |  | 1817 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 299 | Later | S&L | SAU4005-G000-B__-&EMA-00694 | Cable Interconnection document for BOP (Termination details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-08-24 |  |  |  | 2026-08-17 |  |  |  | 2026-08-24 |  |  |  | 1817 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 300 | Later | S&L | SAU4005-G000-B__-&EMA-00695 | Cable Interconnection document for Electrical Auxiliaries System (Termination details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-10-08 |  |  |  | 2026-10-05 |  |  |  | 2026-10-08 |  |  |  | 1817 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 301 | Later | S&L | SAU4005-G000-B__-&EMA-00696 | Cable Interconnection document for DC System (Termination details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-07-09 |  |  |  | 2026-07-03 |  |  |  | 2026-07-09 |  |  |  | 1817 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 302 | Later | S&L | SAU4005-G000-B__-&EMA-00697 | Cable Interconnection document for UPS System (Termination details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-07-03 |  |  |  | 2026-06-25 |  |  |  | 2026-07-03 |  |  |  | 1814 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 303 | Later | S&L | SAU4005-G000-B__-&EMA-00534 | Cable Schedule document for GT & Auxiliaries (Routing details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFD | [10 empty] | 2026-08-20 |  |  |  | 2026-06-25 | [7 empty] | 1733 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 304 | Later | S&L | SAU4005-G000-B__-&EMA-00698 | Cable Schedule document for ST & Auxiliaries (Routing details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFI | IFD | [10 empty] | 2026-09-17 |  |  |  | 2026-07-23 | [7 empty] | 1733 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 305 | Later | S&L | SAU4005-G000-B__-&EMA-00699 | Cable Schedule document for HRSG and Auxiliaries (Routing details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFD | [10 empty] | 2026-10-14 |  |  |  | 2026-08-19 | [7 empty] | 1733 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 306 | Later | S&L | SAU4005-G000-B__-&EMA-00700 | Cable Schedule document for BOP (Routing details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFD | [10 empty] | 2026-11-02 |  |  |  | 2026-09-07 | [7 empty] | 1765 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 307 | Later | S&L | SAU4005-G000-B__-&EMA-00701 | Cable Schedule document for Electrical Auxiliaries System (Routing details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFD | [10 empty] | 2026-11-24 |  |  |  | 2026-09-29 | [7 empty] | 1765 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 308 | Later | S&L | SAU4005-G000-B__-&EMA-00702 | Cable Schedule document for DC System (Routing details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFD | [10 empty] | 2026-12-18 |  |  |  | 2026-10-23 | [7 empty] | 1765 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 309 | Later | S&L | SAU4005-G000-B__-&EMA-00703 | Cable Schedule document for UPS System (Routing details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFD | [10 empty] | 2027-01-13 |  |  |  | 2026-11-18 | [7 empty] | 1765 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 310 | Later | S&L | SAU4005-G000-B__-&EMA-00704 | Cable Schedule document for CNI Cables (Routing details in Excel File) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFI | IFD | [10 empty] | 2027-01-12 |  |  |  | 2026-11-17 | [7 empty] | 1785 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 311 | Later | S&L | SAU4005-G000-B__-&ELD-00535 | General Notes & Details of Cable Raceway and Equipment Installation | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-05-09 |  | 2025-04-08 |  | 2025-05-29 |  | 2025-04-23 |  | 2025-07-04 |  | 2025-12-24 | [5 empty] | 2025-07-04 |  |  |  | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 312 | Later | S&L | SAU4005-G000-UZT-&ELD-00536 | Cable Raceway Layout for Overall Plant Outdoor Raceway | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-01-21 |  | 2025-12-08 |  | 2026-02-11 |  | 2025-12-30 |  | 2026-03-20 |  | 2026-02-24 | [5 empty] | 2026-03-20 |  |  |  | 541 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 313 | Later | S&L | SAU4005-G000-UM_-&ELD-00537 | Cable Raceway Layout for GTG Area | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFA | IFC |  |  | 2025-09-30 |  | 2025-09-01 |  | 2025-10-24 |  | 2025-03-12 |  | 2026-03-01 |  | 2026-01-19 | [5 empty] | 2026-03-01 |  |  |  | 573 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 314 | Later | S&L | SAU4005-G000-UMA-&ELH-00538 | Cable Raceway Layout for STG Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFA | IFC |  |  | 2026-05-01 |  | 2025-12-09 |  | 2026-05-21 |  | 2025-12-28 |  | 2026-09-24 |  | 2026-01-21 | [5 empty] | 2026-09-24 |  |  |  | 424 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 316 | Later | S&L | SAU4005-G000-USC-&ELH-00540 | Cable Raceway Layout for Air Compressor Shed | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-03-27 |  |  |  | 2025-12-30 |  | 2025-08-30 |  | 2026-03-27 |  |  |  | 363 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 317 | Later | S&L | SAU4005-G000-URX-&ELH-00541 | Cable Raceway Layout for Fin Fan Cooler, CCCW Area and Fin Fan Cooler Electrical Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-03-27 |  |  |  | 2026-01-30 |  | 2025-10-16 |  | 2026-06-04 |  |  |  | 363 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 318 | Later | S&L | SAU4005-G000-UBA-&ELH-00542 | Cable Raceway Layout for STG and Auxiliary Boiler Electrical Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFI | IFC | [10 empty] | 2026-06-04 |  |  |  | 2026-03-25 |  | 2025-12-04 |  | 2026-03-27 |  |  |  | 363 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 319 | Later | S&L | SAU4005-G000-UER-&ELH-00543 | Cable Raceway Layout for Fuel Gas Area and GBC Building including Electrical Room | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-01-01 |  | 2025-10-16 |  | 2026-01-22 |  | 2025-11-02 |  | 2026-03-27 |  | 2026-01-21 | [5 empty] | 2026-06-05 |  |  |  | 363 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 320 | Later | S&L | SAU4005-G000-UEJ-&ELH-00544 | Cable Raceway Layout for Fuel Oil Area , Pump Shed and E-House | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-06-05 |  |  |  | 2026-04-20 |  | 2025-11-14 |  | 2026-05-14 |  |  |  | 363 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 322 | Later | S&L | SAU4005-G000-UBA-&ELH-00546 | Cable Raceway Layout for ACC Electrical Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFA | IFC |  |  | 2025-12-17 |  | 2025-11-17 |  | 2026-01-06 |  | 2025-12-04 |  | 2026-05-14 |  | 2026-01-19 | [5 empty] | 2026-06-21 |  |  |  | 363 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 323 | Later | S&L | SAU4005-G000-UBA-&ELH-00547 | Cable Raceway Layout for GT Package MCC / Control room - 11, 12, 13 | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFA | IFC |  |  | 2025-09-22 |  | 2025-10-02 |  | 2025-10-15 |  | 0 |  | 2026-05-21 |  | 2025-12-22 | [5 empty] | 2026-03-27 |  |  |  | 363 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 324 | Later | S&L | SAU4005-G000-UCA-&ELH-00548 | Cable Raceway Layout for Main Electrical & Control Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFA | IFC |  |  | 2025-09-15 |  | 2025-08-05 |  | 2025-10-08 |  | 2025-08-18 |  | 2026-06-21 |  | 2025-12-29 | [5 empty] | 2026-03-27 |  |  |  | 363 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 325 | Later | S&L | SAU4005-G000-UST-&ELH-00549 | Cable Raceway Layout for Workshop and Warehouse Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-03-27 |  |  |  | 2025-12-09 |  | 2025-09-23 |  | 2026-04-06 |  |  |  | 363 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
|  | 329 | Later | S&L | SAU4005-G000-USG-&ELH-00554 | Cable Raceway Layout for Fire Water Pump and Service water pump Shed | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-12-17 |  | 2025-10-28 |  | 2026-01-06 |  | 2026-01-04 |  | 2026-03-27 |  | 2026-02-16 | [5 empty] | 2026-04-22 |  |  |  | 363 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 330 | Later | S&L | SAU4005-G000-UBA-&ELH-00555 | Cable Raceway Layout for BOP-2 E-House | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-06 |  |  |  | 2026-02-03 |  | 2025-09-28 |  | 2027-01-25 |  |  |  | 1500 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
|  | 332 | Later | S&L | SAU4005-G000-UBA-&ELH-00557 | Cable Raceway Layout for Unit MV/LV Electrical Switchgear building-11, 12, 13 | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFA | IFC |  |  | 2026-04-01 |  | 2025-08-01 |  | 2026-04-21 |  | 2025-08-18 |  | 2026-08-25 |  | 2025-12-23 | [5 empty] | 2026-06-22 |  |  |  | 476 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 333 | Later | S&L | SAU4005-G000-UGD-&ELH-00558 | Cable Raceway Layout for DM water forwarding Pump Shed | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-03-27 |  |  |  | 2025-11-25 |  | 2025-10-04 |  | 2026-06-22 |  |  |  | 476 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 334 | Later | S&L | SAU4005-G000-UBA-&ELH-00559 | Cable Raceway Layout for BOP-1 Electrical Switchgear Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-12-31 |  | 2025-10-09 |  | 2026-01-21 |  | 2025-12-22 |  | 2026-03-27 |  | 2026-02-01 | [5 empty] | 2026-07-01 |  |  |  | 476 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 335 | Later | S&L | SAU4005-G000-UYC-&ELH-00562 | Cable Raceway Layout for Administration & Social Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-03-05 |  | 2025-09-23 |  | 2026-03-25 |  | 2025-10-07 |  | 2026-04-22 |  | 2026-02-15 | [5 empty] | 2026-06-22 |  |  |  | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 336 | Later | S&L | SAU4005-G000-UHA-&ELH-00854 | Cable Raceway Layout for HRSG E-House | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | Common |  | IFA | IFC |  |  | 2026-08-26 |  | 2025-10-13 |  | 2026-09-17 |  | 2025-10-26 |  | 2027-01-25 |  | 2025-11-17 | [5 empty] | 2026-06-22 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 337 | Later | S&L | SAU4005-G000-B__-&ELD-00564 | General Notes & Details of Lighting System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-02-24 |  | 2025-04-08 |  | 2026-03-17 |  | 2025-04-24 |  | 2026-06-22 |  | 2025-11-20 | [5 empty] | 2026-06-22 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 338 | Later | S&L | SAU4005-G000-UM_-&ELD-00565 | Lighting Layout for GTG Area | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-03-16 |  | 2025-10-16 |  | 2026-04-03 |  | 2025-12-30 |  | 2026-06-22 |  | 2026-05-21 | [5 empty] | 2026-06-22 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 339 | Later | S&L | SAU4005-G000-UMA-&ELH-00566 | Lighting Layout for STG Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-04-10 |  | 2026-01-21 |  | 2026-04-30 |  | 2026-02-05 |  | 2026-06-22 |  | 2026-03-10 | [5 empty] | 2026-06-22 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 340 | Later | S&L | SAU4005-G000-USU-&ELH-00567 | Lighting Layout for Chemical Storage Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-05-19 |  | 2026-03-27 |  | 2026-06-08 |  | 2026-04-06 |  | 2026-07-01 |  | 2026-05-06 | [5 empty] | 2026-07-01 |  |  |  | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 341 | Later | S&L | SAU4005-G000-USC-&ELH-00568 | Lighting Layout for Air Compressor Shed | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-06-22 |  |  |  | 2026-03-20 |  | 2025-10-16 |  | 2026-06-22 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 342 | Later | S&L | SAU4005-G000-URX-&ELH-00569 | Lighting Layout for Fin Fan Cooler & CCCW Area | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-06-22 |  |  |  | 2026-03-09 |  | 2026-01-02 |  | 2026-06-22 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 343 | Later | S&L | SAU4005-G000-UBA-&ELH-00570 | Lighting Layout for STG and Auxiliary Boiler Electrical Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-08-12 |  |  |  | 2026-06-25 |  | 2026-01-29 |  | 2026-08-12 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 344 | Later | S&L | SAU4005-G000-UER-&ELH-00571 | Lighting Layout for Fuel Gas Area and GBC Building including Electrical Room | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-06-22 |  |  |  | 2026-03-26 |  | 2026-03-13 |  | 2026-06-22 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 345 | Later | S&L | SAU4005-G000-UEJ-&ELH-00572 | Lighting Layout for Fuel Oil Area and Pump Shed | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-07-20 |  |  |  | 2026-04-23 |  | 2026-01-21 |  | 2026-07-20 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 346 | Later | S&L | SAU4005-G000-UBF-&ELD-00573 | Lighting Layout for Transformer Area | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-05-19 |  | 2025-11-02 |  | 2026-06-08 |  | 2025-11-20 |  | 2026-07-06 |  | 2026-05-21 | [5 empty] | 2026-07-06 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 347 | Later | S&L | SAU4005-G000-UBA-&ELH-00575 | Lighting Layout for GT Package MCC / Control room - 11, 12, 13 | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-02-16 |  | 2025-10-09 |  | 2026-03-09 |  | 2025-10-30 |  | 2026-06-22 |  | 2026-05-03 | [5 empty] | 2026-06-22 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 348 | Later | S&L | SAU4005-G000-UCA-&ELH-00576 | Lighting Layout for Main Electrical & Control Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-03-05 |  | 2025-10-09 |  | 2026-03-25 |  | 2025-10-30 |  | 2026-06-22 |  | 2026-05-21 | [5 empty] | 2026-06-22 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 349 | Later | S&L | SAU4005-G000-UST-&ELH-00577 | Lighting Layout for Workshop and Warehouse Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-03-26 |  | 2026-01-17 |  | 2026-04-15 |  | 2026-01-22 |  | 2026-06-22 |  | 2026-05-03 | [5 empty] | 2026-06-22 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 350 | Later | S&L | SAU4005-G000-UG_-&ELH-00578 | Lighting Layout for Water and Effluent treatment building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-04-17 |  | 2026-01-29 |  | 2026-05-07 |  | 2026-02-18 |  | 2026-06-22 |  | 2026-03-15 | [5 empty] | 2026-06-22 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 351 | Later | S&L | SAU4005-G000-UTG-&ELH-00579 | Lighting Layout for Hydrogen Generation Plant including Electrical Room | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-06-22 |  |  |  | 2026-04-13 |  | 2026-03-13 |  | 2026-06-22 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 353 | Later | S&L | SAU4005-G000-USG-&ELH-00582 | Lighting Layout for Fire Water Pump and Service water pump Shed | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-06-01 |  | 2026-01-21 |  | 2026-06-19 |  | 2026-02-05 |  | 2026-07-17 |  | 2026-05-03 | [5 empty] | 2026-07-17 |  |  |  | 1200 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
|  | 354 | Later | S&L | SAU4005-G000-UBA-&ELH-00585 | Lighting Layout for Unit MV/LV Electrical Switchgear building-11, 12, 13 | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-04-28 |  | 2025-11-02 |  | 2026-05-18 |  | 2025-11-20 |  | 2026-06-22 |  | 2026-06-07 | [5 empty] | 2026-06-22 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 355 | Later | S&L | SAU4005-G000-UGD-&ELH-00586 | Lighting Layout for DM water forwarding Pump Shed | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-04-15 |  | 2026-01-29 |  | 2026-05-05 |  | 2026-02-05 |  | 2026-06-22 |  | 2026-03-15 | [5 empty] | 2026-06-22 |  |  |  | 476 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Open
|  | 356 | Later | S&L | SAU4005-G000-UBA-&ELH-00587 | Lighting Layout for BOP Electrical Switchgear Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-05-06 |  | 2026-01-02 |  | 2026-05-26 |  | 2026-01-19 |  | 2026-07-20 |  | 2026-05-12 | [5 empty] | 2026-07-20 |  |  |  | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 357 | Later | S&L | SAU4005-G000-UYC-&ELH-00590 | Lighting Layout for Administration & Social Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-04-09 |  | 2025-10-09 |  | 2026-04-29 |  | 2025-10-30 |  | 2026-05-27 |  | 2026-02-18 | [5 empty] | 2026-05-27 |  |  |  | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 358 | Later | S&L | SAU4005-G000-UZA-&ELH-00858 | Outdoor Lighting Layout for Access Road | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-08-12 |  | 2025-10-14 |  | 2026-09-02 |  | 2026-04-02 |  | 2026-10-01 |  | 0 | [5 empty] | 2026-10-01 |  |  |  | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 359 | Later | S&L | SAU4005-G000-UZT-&ELH-00859 | Lighting Layout for Outdoor areas | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-10-09 |  | 2026-04-11 |  | 2026-11-02 |  | 2026-05-06 |  | 2026-12-02 |  | 0 | [5 empty] | 2026-12-02 |  |  |  | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 360 | Later | S&L | SAU4005-G000-B__-&ELD-00592 | General Notes & Details of Grounding System and Lightning Protection System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-06-27 |  | 2025-04-08 |  | 2025-07-17 |  | 2025-04-24 |  | 2026-05-27 |  | 2025-08-11 | [9 empty] | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 361 | Later | S&L | SAU4005-G000-UM_-&ELD-00593 | Grounding & Lightning Protection Layout for GTG Area | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-10-16 |  | 2025-07-19 |  | 2025-11-07 |  | 2025-07-27 |  | 2026-05-27 |  | 2025-08-26 | [5 empty] | 2026-05-27 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 362 | Later | S&L | SAU4005-G000-UMA-&ELH-00594 | Grounding Protection Layout for STG Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-02-26 |  | 2025-12-24 |  | 2026-03-19 |  | 2026-01-08 |  | 2026-05-27 |  | 2026-01-19 | [5 empty] | 2026-05-27 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 363 | Later | S&L | SAU4005-G000-USU-&ELH-00595 | Grounding Protection Layout for Chemical Storage Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-05-27 |  |  |  | 2026-01-02 |  | 2025-11-30 |  | 2026-05-27 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 364 | Later | S&L | SAU4005-G000-USC-&ELH-00596 | Grounding Protection Layout for Air Compressor Shed | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-12-02 |  | 2025-10-29 |  | 2025-12-22 |  | 2025-11-18 |  | 2026-05-27 |  | 2025-12-04 | [5 empty] | 2026-05-27 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 365 | Later | S&L | SAU4005-G000-URX-&ELH-00597 | Grounding Protection Layout for Fin Fan Cooler & CCCW Area | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-05-27 |  |  |  | 2026-01-28 |  | 2025-11-12 |  | 2026-05-27 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 366 | Later | S&L | SAU4005-G000-UBA-&ELH-00598 | Grounding Protection Layout for STG and Auxiliary Boiler Electrical Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-02-02 |  | 2025-12-24 |  | 2026-02-20 |  | 2025-07-17 |  | 2026-05-27 |  | 2026-01-19 | [5 empty] | 2026-05-27 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 367 | Later | S&L | SAU4005-G000-UER-&ELH-00599 | Grounding Protection Layout for Fuel Gas Area and GBC Building including Electrical Room | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-01-07 |  | 2025-10-16 |  | 2026-02-13 |  | 2025-07-17 |  | 2026-05-27 |  | 2026-02-16 | [5 empty] | 2026-05-27 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 368 | Later | S&L | SAU4005-G000-UEJ-&ELH-00600 | Grounding Protection Layout for Fuel Oil Area and Pump Shed | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-05-07 |  | 2025-09-29 |  | 2026-05-27 |  | 2025-10-16 |  | 2026-06-24 |  | 2025-11-20 | [5 empty] | 2026-06-24 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 369 | Later | S&L | SAU4005-G000-UBF-&ELD-00601 | Grounding Protection Layout for Transformer Area | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-03-20 |  | 2025-11-30 |  | 2026-04-09 |  | 2025-12-23 |  | 2026-05-27 |  | 2026-05-06 | [5 empty] | 2026-05-27 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 370 | Later | S&L | SAU4005-G000-UBA-&ELH-00603 | Grounding Protection Layout for GT Package MCC / Control room - 11, 12, 13 | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-11-06 |  | 2025-08-19 |  | 2025-11-26 |  | 2025-10-09 |  | 2026-05-27 |  | 2025-10-27 | [5 empty] | 2026-05-27 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 371 | Later | S&L | SAU4005-G000-UCA-&ELH-00604 | Grounding & Lightning Protection Layout for Main Electrical & Control Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-11-11 |  | 2025-07-11 |  | 2025-12-01 |  | 2025-07-27 |  | 2026-05-27 |  | 2025-09-02 | [5 empty] | 2026-05-27 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 372 | Later | S&L | SAU4005-G000-UST-&ELH-00605 | Grounding and Lightning Protection Layout for Workshop and Warehouse Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-05-27 |  |  |  | 2025-12-02 |  | 2025-07-13 |  | 2026-05-27 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 373 | Later | S&L | SAU4005-G000-UG_-&ELH-00606 | Grounding Protection Layout for Water and Effluent treatment building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-01-05 |  | 2025-11-19 |  | 2026-01-27 |  | 2025-12-07 |  | 2026-05-27 |  | 2025-12-30 | [5 empty] | 2026-05-27 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 374 | Later | S&L | SAU4005-G000-UTG-&ELH-00607 | Grounding Protection Layout for Hydrogen Generation Plant including Electrical Room | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-04-15 |  | 2025-11-30 |  | 2026-05-20 |  | 2025-12-23 |  | 2026-06-17 |  | 2026-01-06 | [5 empty] | 2026-06-17 |  |  |  | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 375 | Later | S&L | SAU4005-G000-UGA-&ELH-00608 | Grounding Protection Layout for Raw Water Transfer Pumps and Chlorination Shed | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-04-17 |  | 2025-11-06 |  | 2026-05-22 |  | 2025-11-20 |  | 2026-06-19 |  | 2025-12-04 | [5 empty] | 2026-06-19 |  |  |  | 334 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 376 | Later | S&L | SAU4005-G000-USG-&ELH-00610 | Grounding & Lightning Protection Layout for Fire Water Pump and Service water pump Shed | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-03-25 |  | 2025-07-10 |  | 2026-04-14 |  | 2025-03-10 |  | 2026-05-27 |  | 2025-09-07 | [5 empty] | 2026-05-27 |  |  |  | 123 | [13 empty] | WF Transmittal DI-EPC-ACWA |  | NO | NO | NO | NO |  | NO
|  | 377 | Later | S&L | SAU4005-G000-UBA-&ELH-00613 | Grounding Protection Layout for Unit MV/LV Electrical Switchgear building-11, 12, 13 | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-02-25 |  | 2025-11-13 |  | 2026-04-02 |  | 2025-10-16 |  | 2026-05-27 |  | 2026-05-06 | [5 empty] | 2026-05-27 |  |  |  | 292 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
|  | 378 | Later | S&L | SAU4005-G000-UGD-&ELH-00614 | Grounding Protection Layout for DM water forwarding Pump Shed | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-05-27 |  |  |  | 2026-02-25 |  | 2025-09-29 |  | 2026-05-27 |  |  |  | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Common
|  | 379 | Later | S&L | SAU4005-G000-UBA-&ELH-00615 | Grounding Protection Layout for BOP Electrical Switchgear Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-08-21 |  |  |  | 2026-07-06 |  | 2025-12-23 |  | 2026-08-21 |  |  |  | 162 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Common
|  | 380 | Later | S&L | SAU4005-G000-UYC-&ELH-00618 | Grounding & Lightning Protection Layout for Administration & Social Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-06-15 |  |  |  | 2026-02-26 |  | 2025-07-17 |  | 2026-06-15 |  |  |  | 567 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1,C1 | SEC | S1 | NO | Common
|  | 381 | Later | S&L | SAU4005-G000-B__-&ELD-00708 | Overall Grounding Layout | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-07-24 |  | 2025-08-09 |  | 2025-08-13 |  | 2025-08-11 |  | 2026-05-01 |  | 2025-09-16 | [5 empty] | 2026-05-01 |  |  |  | 567 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
|  | 382 | Later | S&L | SAU4005-G000-B__-&EFB-00710 | 380 KV Substation Interface Block Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-24 |  | 2025-10-06 |  | 2026-03-17 |  | 2025-10-22 |  | 2026-04-14 |  | 0 | [9 empty] | 385 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
|  | 383 | Later | S&L | SAU4005-G000-B__-&EFB-00718 | Common Interlock Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2026-07-03 |  |  |  | 2026-07-23 |  |  |  | 2026-08-20 | [11 empty] | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
|  | 384 | Later | S&L | SAU4005-G000-B__-&EDC-00720 | Electrical operation philosophy | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2026-10-12 |  |  |  | 2026-11-03 |  |  |  | 2026-12-03 | [11 empty] | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
|  | 385 | Later | S&L | SAU4005-G000-B__-&ELD-00721 | Overall Lightning Protection Layout | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-01-23 |  | 2025-11-30 |  | 2026-02-13 |  | 2025-08-11 |  | 2026-05-01 |  | 2026-05-06 | [5 empty] | 2026-05-01 |  |  |  | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 386 | Later | S&L | SAU4005-G000-BAT-&EEC-00728 | Technical Specification for Generator Transformer | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-04-30 |  | 2025-03-10 |  | 2025-05-20 |  | 2025-03-17 |  | 2025-06-24 |  | 2025-09-02 | [9 empty] | 266 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
|  | 387 | Later | S&L | SAU4005-G000-BAC-&EEC-00630 | Technical Specification for Generator Circuit Breaker | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-05-16 |  | 2025-04-08 |  | 2025-06-05 |  | 2025-04-20 |  | 2025-06-12 |  | 2025-12-08 | [9 empty] | 298 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
|  | 388 | Later | S&L | SAU4005-G000-BAA-&EEC-00631 | Technical Specification for Isolated Phase Bus duct | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-06-03 |  | 2025-04-08 |  | 2025-06-23 |  | 2025-04-29 |  | 2025-06-30 |  | 2025-05-14 | [9 empty] | 236 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 389 | Later | S&L | SAU4005-G000-BBT-&EEC-00632 | Technical Specification for Unit Auxiliary Transformer and NGR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-07-22 |  | 2025-05-29 |  | 2025-08-11 |  | 2025-06-09 |  | 2025-08-19 |  | 2025-09-02 | [9 empty] | 236 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Common
|  | 390 | Later | S&L | SAU4005-G000-BBA-&EEC-00633 | Technical Specification for MV Switchgear | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-06-25 |  | 2025-05-25 |  | 2025-07-15 |  | 2025-06-09 |  | 2025-07-22 |  | 2025-10-15 | [9 empty] | 236 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1 | SEC | S2,S3 | NO | Common
|  | 391 | Later | S&L | SAU4005-G000-BFT-&EEC-00634 | Technical Specification for Auxiliary Distribution Transformers | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-07-07 |  | 2025-05-16 |  | 2025-07-25 |  | 2025-08-06 |  | 2025-08-01 |  | 2025-12-01 | [9 empty] | 236 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 393 | Later | S&L | SAU4005-G000-BHA-&EEC-00636 | Technical Specification for LV Switchgear | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-08-28 |  | 2025-07-10 |  | 2025-09-17 |  | 2025-07-24 |  | 2025-09-24 |  | 2025-12-25 | [9 empty] | 259 | [13 empty] | WF Transmittal DI-EPC-ACWA |  | NO | YES | NO | NO |  | NO
|  | 394 | Later | S&L | SAU4005-G000-MJ_-&EEC-00637 | Technical Specification for BSEDG | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | DOOSAN |  | IFA | IFP |  |  | 2025-03-17 |  | 2025-01-24 |  | 2025-04-04 |  | 2025-03-22 |  | 2025-05-12 |  | 2025-08-24 | [9 empty] | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
|  | 395 | Later | S&L | SAU4005-G000-BUA-&EEC-00638 | Technical Specification for Battery | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-09-09 |  | 2025-07-10 |  | 2025-09-30 |  | 0 |  | 2025-10-09 |  | 2025-09-16 | [9 empty] | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 396 | Later | S&L | SAU4005-G000-BR_-&EEC-00639 | Technical Specification for UPS System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-09-09 |  | 2025-07-19 |  | 2025-09-30 |  | 2025-08-04 |  | 2025-10-09 |  | 2025-11-20 | [9 empty] | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO
|  | 397 | Later | S&L | SAU4005-G000-AR_-&EEC-00640 | Technical Specification for Protection Panels | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-08-29 |  | 2025-07-23 |  | 2025-09-18 |  | 2025-08-06 |  | 2025-09-25 |  | 2025-10-07 | [9 empty] | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO
|  | 398 | Later | S&L | SAU4005-G000-C__-&EEC-00641 | Technical Specification for Plant Communication System (Turnkey Package) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-11-03 |  | 2025-08-13 |  | 2025-11-21 |  | 2025-07-31 |  | 2025-11-28 |  | 2025-10-26 | [9 empty] | 194 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
|  | 399 | Later | S&L | SAU4005-G000-C__-&EEC-00681 | Technical specification for Telecommunication Panels between Plant and S/S | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-10-30 |  | 2025-08-20 |  | 2025-11-19 |  | 2025-09-02 |  | 2025-11-26 |  | 0 | [9 empty] | 1500 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
|  | 400 | Later | S&L | SAU4005-G000-BBA-&EEC-00706 | Technical specification for MV VFD | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | DOOSAN |  | IFA | IFP |  |  | 2025-08-08 |  | 2025-06-20 |  | 2025-09-01 |  | 2025-07-04 |  | 2025-10-10 |  | 2025-09-21 | [9 empty] | 233 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1 | NO |  | NO | Common
|  | 401 | Later | S&L | SAU4005-G000-BUA-&EEC-00709 | Technical Specification for Battery Charger | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-10-16 |  | 2025-07-19 |  | 2025-11-07 |  | 2025-07-31 |  | 2025-11-14 |  | 2025-12-02 | [9 empty] | 279 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1 | NO |  | NO | Common
|  | 402 | Later | S&L | SAU4005-G000-B__-&EEC-00711 | Technical Specification for Heat Tracing System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-12-22 |  | 2026-01-21 |  | 2026-01-09 |  | 2026-02-09 |  | 2026-01-19 |  | 2026-04-12 | [9 empty] | 797 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C2 | NO |  | NO | Common
|  | 403 | Later | S&L | SAU4005-G000-B__-&EEC-00713 | Technical Specification for MV Cable | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-10-28 |  | 2025-08-23 |  | 2025-11-17 |  | 2025-09-04 |  | 2025-11-24 |  | 2025-11-19 | [9 empty] | 641 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 404 | Later | S&L | SAU4005-G000-B__-&EEC-00714 | Technical Specification for LV Cable | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-10-23 |  | 2025-08-11 |  | 2025-11-12 |  | 2025-08-24 |  | 2025-11-19 |  | 2025-10-16 | [9 empty] | 641 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 405 | Later | S&L | SAU4005-G000-B__-&EEC-00723 | Technical Specification for Control Cable | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-10-30 |  | 2025-08-09 |  | 2025-11-19 |  | 2025-08-25 |  | 2025-11-26 |  | 2026-02-16 | [9 empty] | 431 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 407 | Later | S&L | SAU4005-G000-B__-&EEC-00855 | Technical Specification for Electrical Container | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-12-29 |  | 2025-07-26 |  | 2026-01-19 |  | 2025-08-08 |  | 2026-01-27 |  | 0 | [9 empty] | 431 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 408 | Later | S&L | SAU4005-G000-C__-&EDB-00750 | Design Criteria Documents of Control & Instrumentation | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | Common |  | IFA | IFD |  |  | 2025-03-20 |  | 2025-02-27 |  | 2025-04-09 |  | 2025-03-13 |  | 2025-05-15 |  | 2025-11-20 | [9 empty] | 431 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 409 | Later | S&L | SAU4005-G000-CJ_-&EFF-00751 | Plant Control System Architecture Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | Common |  | IFA | IFD |  |  | 2025-02-20 |  | 2025-01-24 |  | 2025-03-12 |  | 2025-02-20 |  | 2025-04-17 |  | 2025-06-18 | [9 empty] | 496 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 410 | Later | S&L | SAU4005-G000-UCA-&ELH-00752 | Central Control Room Layout | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | Common |  | IFA | IFC |  |  | 2025-05-12 |  | 2025-04-23 |  | 2025-06-04 |  | 2025-05-07 |  | 2025-12-28 |  | 0 | [5 empty] | 2025-12-28 |  |  |  | 496 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 411 | Later | S&L | SAU4005-G000-C__-&ELD-00753 | Instrument Installation & Hook Up Drawings | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | Common |  | IFA | IFC |  |  | 2025-04-28 |  | 2025-03-18 |  | 2025-05-16 |  | 2025-03-28 |  | 2025-12-20 |  | 2025-05-20 | [5 empty] | 2025-12-20 |  |  |  | 463 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 412 | Later | S&L | SAU4005-G000-C__-&ELD-00754 | Instrument/Junction Box Location Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | I&C&DCS | Instrumentation & Control | Common |  | IFA | IFC |  |  | 2026-08-20 |  |  |  | 2026-09-10 |  |  |  | 2027-01-18 | [7 empty] | 2027-01-18 |  |  |  | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 413 | Later | S&L | SAU4005-G000-EK_-&EFF-00755 | Logic Diagram for Fuel Gas Compressor System Interface | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFC |  |  | 2025-11-17 |  | 2025-11-06 |  | 2025-12-05 |  | 2025-11-23 |  | 2026-01-06 |  | 2026-05-21 | [5 empty] | 2026-01-06 |  |  |  | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 414 | Later | S&L | SAU4005-G000-GHC-&EFF-00756 | Logic Diagram for DM Water Distribution System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFC |  |  | 2026-03-03 |  | 2025-12-25 |  | 2026-03-24 |  | 2025-11-24 |  | 2026-04-20 |  | 2026-04-02 | [5 empty] | 2026-04-20 |  |  |  | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 415 | Later | S&L | SAU4005-G000-GK_-&EFF-00757 | Logic Diagram for Potable Water System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFC |  |  | 2026-02-05 |  | 2025-12-26 |  | 2026-02-25 |  | 2026-01-07 |  | 2026-03-24 |  | 2026-05-12 | [5 empty] | 2026-03-24 |  |  |  | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 416 | Later | S&L | SAU4005-G000-GH_-&EFF-00758 | Logic Diagram for Service water system | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFC |  |  | 2026-02-13 |  | 2025-12-26 |  | 2026-03-06 |  | 2026-01-07 |  | 2026-04-01 |  | 2026-03-29 | [5 empty] | 2026-04-01 |  |  |  | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 417 | Later | S&L | SAU4005-G000-MB_-&EFF-00759 | Logic Diagram for Gas Turbine, Generator & Auxiliaries Interface | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFC |  |  | 2025-11-20 |  | 2026-01-26 |  | 2025-09-12 |  | 2026-01-21 |  | 2026-03-01 |  | 2026-05-21 | [5 empty] | 2026-03-01 |  |  |  | 382 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 418 | Later | S&L | SAU4005-G000-MA_-&EFF-00760 | Logic Diagram for Steam Turbine, Generator & Auxiliaries Interface | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFC |  |  | 2025-12-29 |  | 2025-11-28 |  | 2025-10-24 |  | 2025-12-14 |  | 2026-04-05 |  | 2026-04-02 | [5 empty] | 2026-04-05 |  |  |  | 382 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 419 | Later | S&L | SAU4005-G000-GB_-&EFF-00761 | Logic Diagram for Water and Effluent treatment building Interface | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFC |  |  | 2026-03-06 |  | 2026-03-12 |  | 2026-03-26 |  | 2026-04-02 |  | 2026-05-01 |  | 2026-05-06 | [5 empty] | 2026-05-01 |  |  |  | 382 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 421 | Later | S&L | SAU4005-G000-C__-&EFF-00763 | Logic Diagram for Plant Startup Logic | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFC |  |  | 2026-05-12 |  | 2026-03-10 |  | 2026-06-01 |  | 0 |  | 2026-10-05 |  | 0 | [5 empty] | 2026-10-05 |  |  |  | 382 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 422 | Later | S&L | SAU4005-G000-C__-&EFF-00764 | Logic Diagram for Plant Shutdown Logic | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFC |  |  | 2026-05-21 |  | 2026-03-10 |  | 2026-06-10 |  | 0 |  | 2026-10-14 |  | 0 | [5 empty] | 2026-10-14 |  |  |  | 382 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 423 | Later | S&L | SAU4005-G000-C__-&EFF-00765 | Logic Diagram for AGC Logic | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFC |  |  | 2026-06-24 |  | 2026-06-09 |  | 2026-07-14 |  | 0 |  | 2026-11-17 |  | 0 | [5 empty] | 2026-11-17 |  |  |  | 366 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 424 | Later | S&L | SAU4005-G000-C__-&EFF-00766 | Master Logic Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFD |  |  | 2025-07-28 |  | 2025-06-04 |  | 2025-08-18 |  | 2025-06-18 |  | 2025-09-24 |  | 2026-04-02 | [9 empty] | 366 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 426 | Later | S&L | SAU4005-G000-QCA-&EFF-00769 | Logic Diagram for Chemical Feed System Interface | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFC |  |  | 2026-03-17 |  | 2026-03-20 |  | 2026-04-06 |  | 2026-04-02 |  | 2026-06-15 |  | 2026-05-06 | [5 empty] | 2026-06-15 |  |  |  | 366 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 428 | Later | S&L | SAU4005-G000-QH_-&EFF-00771 | Logic Diagram for Auxiliary Boiler system Interface | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFC |  |  | 2026-02-20 |  | 2025-12-25 |  | 2026-03-12 |  | 2026-04-02 |  | 2026-04-17 |  | 2026-05-06 | [5 empty] | 2026-04-17 |  |  |  | 366 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 429 | Later | S&L | SAU4005-G000-LAB-&EFF-00772 | Logic Diagram for Feed Water System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFC |  |  | 2025-11-16 |  | 2025-12-10 |  | 2025-09-08 |  | 2025-12-23 |  | 2026-01-22 |  | 2026-03-29 | [5 empty] | 2026-01-22 |  |  |  | 317 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1,C1 | SEC, Aramco,NWC | S1,S7,S11 | YES
|  | 430 | Later | S&L | SAU4005-G000-LC_-&EFF-00773 | Logic Diagram for Condensate System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFC |  |  | 2026-01-06 |  | 2025-12-12 |  | 2025-10-30 |  | 2025-12-23 |  | 2026-03-15 |  | 2026-02-05 | [5 empty] | 2026-03-15 |  |  |  | 317 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
|  | 431 | Later | S&L | SAU4005-G000-LBA-&EFF-00774 | Logic Diagram for HP Steam System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFC |  |  | 2026-02-22 |  | 2026-01-09 |  | 2025-12-12 |  | 2026-01-29 |  | 2026-04-28 |  | 2026-04-26 | [5 empty] | 2026-04-28 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
|  | 432 | Later | S&L | SAU4005-G000-LBD-&EFF-00775 | Logic Diagram for LP Steam System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFC |  |  | 2026-03-01 |  | 2026-01-06 |  | 2025-12-19 |  | 2026-01-21 |  | 2026-05-04 |  | 2026-05-21 | [5 empty] | 2026-05-04 |  |  |  | 292 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
|  | 433 | Later | S&L | SAU4005-G000-LBC-&EFF-00776 | Logic Diagram for Cold Reheat System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFC |  |  | 2026-03-04 |  | 2026-01-06 |  | 2025-12-24 |  | 2026-01-29 |  | 2026-05-18 |  | 2026-04-26 | [5 empty] | 2026-05-18 |  |  |  | 500 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 434 | Later | S&L | SAU4005-G000-LBB-&EFF-00777 | Logic Diagram for Hot Reheat System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFC |  |  | 2026-03-08 |  | 2026-01-09 |  | 2025-12-26 |  | 2026-01-29 |  | 2026-05-18 |  | 2026-04-26 | [5 empty] | 2026-05-18 |  |  |  | 852 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 435 | Later | S&L | SAU4005-G000-LBG-&EFF-00778 | Logic Diagram for Auxiliary Steam System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFC |  |  | 2026-03-25 |  | 2026-01-23 |  | 2026-01-15 |  | 2026-02-09 |  | 2026-05-25 |  | 2026-04-26 | [5 empty] | 2026-05-25 |  |  |  | 674 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 436 | Later | S&L | SAU4005-G000-LBH-&EFF-00779 | Logic Diagram for STG Drains & Vents System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFC |  |  | 2025-12-22 |  | 2025-10-21 |  | 2026-01-09 |  | 2025-11-06 |  | 2026-05-21 |  | 2026-05-21 | [5 empty] | 2026-05-21 |  |  |  | 674 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 437 | Later | S&L | SAU4005-G000-CYV-&EDD-00830 | Plant Settlement System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFD |  |  | 2026-01-02 |  | 2026-01-29 |  | 2026-01-23 |  | 0 |  | 2026-02-23 |  | 0 | [9 empty] | 674 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 438 | Later | S&L | SAU4005-G000-C__-&EDB-00831 | DCS Graphic Philosophy | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFD |  |  | 2026-09-09 |  | 2025-06-04 |  | 2026-09-30 |  | 2025-06-18 |  | 2026-11-11 |  | 2025-09-08 | [9 empty] | 405 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
|  | 439 | Later | S&L | SAU4005-G000-C__-&EFF-00850 | Logic Diagram for Electrical System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFC |  |  | 2025-07-16 |  | 2025-12-25 |  | 2025-08-05 |  | 2026-04-02 |  | 2025-09-12 |  | 2026-05-20 | [5 empty] | 2025-09-12 |  |  |  | 405 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
| add again | 440 | Later | S&L | SAU4005-G000-QJ_-&EFF-00851 | Logic Diagram for Miscellaneous System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFC |  |  | 2026-05-11 |  | 2026-04-22 |  | 2026-05-29 |  | 2026-05-07 |  | 2026-10-06 |  | 0 | [5 empty] | 2026-10-06 |  |  |  | 405 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
|  | 441 | Later | S&L | SAU4005-G000-C__-&EFF-00853 | Logic diagram for Closed Circuit Cooling Water System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFC |  |  | 2026-03-30 |  | 2025-11-06 |  | 2026-04-17 |  | 2025-11-24 |  | 2026-05-27 |  | 2026-04-02 | [5 empty] | 2026-05-27 |  |  |  | 259 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
|  | 442 | Later | S&L | SAU4005-G000-C__-&EMA-00780 | I & C cable interconnection document for Combined Cycle Misc. System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFI | IFC | [10 empty] | 2026-10-02 |  |  |  | 2026-09-29 |  |  |  | 2026-10-02 |  |  |  | 405 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
|  | 443 | Later | S&L | SAU4005-G000-C__-&EMA-00781 | I & C cable interconnection document for HRSG and Auxiliaries | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFI | IFC | [10 empty] | 2026-11-03 |  |  |  | 2026-07-30 |  |  |  | 2026-11-03 |  |  |  | 324 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
|  | 444 | Later | S&L | SAU4005-G000-C__-&EMA-00782 | I & C cable interconnection document for GT Interface | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFI | IFC | [10 empty] | 2026-06-12 |  |  |  | 2026-03-16 |  | 2026-04-02 |  | 2026-06-12 |  |  |  | 324 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
|  | 445 | Later | S&L | SAU4005-G000-C__-&EMA-00783 | I & C cable interconnection document for Service Water, Raw Water & Potable Water Distribution System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-06-04 |  |  |  | 2026-01-27 |  | 2026-04-23 |  | 2026-06-04 |  |  |  | 405 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
|  | 446 | Later | S&L | SAU4005-G000-C__-&EMA-00832 | I & C cable interconnection document for ST Interface | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFI | IFC | [10 empty] | 2026-09-07 |  |  |  | 2026-08-31 |  |  |  | 2026-09-07 |  |  |  | 405 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
|  | 447 | Later | S&L | SAU4005-G000-C__-&EMA-00833 | I & C cable interconnection document for Fuel Oil System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-07-03 |  |  |  | 2026-06-26 |  |  |  | 2026-07-03 |  |  |  | 168 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
|  | 448 | Later | S&L | SAU4005-G000-C__-&EMA-00834 | I & C cable interconnection document for Fuel Gas System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-06-12 |  |  |  | 2026-06-05 |  |  |  | 2026-06-12 |  |  |  | 168 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
|  | 449 | Later | S&L | SAU4005-G000-C__-&EMA-00835 | I & C cable interconnection document for Fire Protection System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-10-15 |  |  |  | 2026-10-08 |  |  |  | 2026-10-15 |  |  |  | 168 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
|  | 450 | Later | S&L | SAU4005-G000-C__-&EMA-00836 | I & C cable interconnection document for Fin Fan Cooler System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-07-28 |  |  |  | 2026-07-21 |  | 2026-05-06 |  | 2026-07-28 |  |  |  | 168 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
|  | 451 | Later | S&L | SAU4005-G000-C__-&EMA-00837 | I & C cable interconnection document for Compressed Air System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-06-05 |  |  |  | 2026-05-29 |  | 2026-05-06 |  | 2026-06-05 |  |  |  | 658 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 452 | Later | S&L | SAU4005-G000-C__-&EMA-00838 | I & C cable interconnection document - WTP & ETP DCS Interface | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-07-27 |  |  |  | 2026-07-20 |  |  |  | 2026-07-27 |  |  |  | 658 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 453 | Later | S&L | SAU4005-G000-C__-&EMA-00839 | I & C cable interconnection document for Air Cooled Condenser | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFI | IFC | [10 empty] | 2026-09-07 |  |  |  | 2026-08-31 |  |  |  | 2026-09-07 |  |  |  | 372 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 454 | Later | S&L | SAU4005-G000-C__-&EMA-00842 | I & C cable interconnection document - CCCW System & Demineralized Water Distribution | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-17 |  |  |  | 2026-04-10 |  | 2026-04-23 |  | 2026-04-17 |  |  |  | 845 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
|  | 455 | Later | S&L | SAU4005-G000-C__-&EMA-00843 | I & C cable interconnection document - Condensate System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFI | IFC | [10 empty] | 2026-06-22 |  |  |  | 2026-06-15 |  | 2026-05-07 |  | 2026-06-22 |  |  |  | 836 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Common
|  | 456 | Later | S&L | SAU4005-G000-C__-&EMA-00844 | I & C cable interconnection document - Feedwater System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFI | IFC | [10 empty] | 2026-07-06 |  |  |  | 2026-06-29 |  |  |  | 2026-07-06 |  |  |  | 479 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 457 | Later | S&L | SAU4005-G000-C__-&EMA-00845 | I & C cable interconnection document - Auxiliary Steam System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFI | IFC | [10 empty] | 2026-07-31 |  |  |  | 2026-07-24 |  |  |  | 2026-07-31 |  |  |  | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 458 | Later | S&L | SAU4005-G000-C__-&EMA-00846 | I & C cable interconnection document - Steam & Bypass System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFI | IFC | [10 empty] | 2026-07-20 |  |  |  | 2026-07-13 |  |  |  | 2026-07-20 |  |  |  | 500 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO
|  | 459 | Later | S&L | SAU4005-G000-C__-&EPA-00784 | Instrument List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | I&C&DCS | Instrumentation & Control | Common |  | IFA | IFD |  |  | 2025-11-10 |  | 2025-10-15 |  | 2025-11-28 |  | 0 |  | 2026-01-05 |  | 2025-11-02 | [9 empty] | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Common
|  | 460 | Later | S&L | SAU4005-G000-C__-&EPB-00785 | DCS I/O List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | I&C&DCS | Instrumentation & Control | Common |  | IFA | IFP |  |  | 2025-11-19 |  | 2025-12-04 |  | 2025-12-09 |  | 0 |  | 2026-08-19 |  | 2025-12-21 | [9 empty] | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 461 | Later | S&L | SAU4005-G000-C__-&EPB-00847 | Signal Exchange List between IPP and GIS Substation | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFD |  |  | 2026-02-05 |  | 2026-01-18 |  | 2026-02-25 |  | 2026-02-04 |  | 2026-04-01 |  | 2026-05-06 | [9 empty] | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 462 | Later | S&L | SAU4005-G000-C__-&EEC-00789 | Technical Specifications for DCS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFP |  |  | 2025-08-11 |  | 2025-04-28 |  | 2025-09-01 |  | 2025-05-13 |  | 2025-10-10 |  | 2025-11-12 | [9 empty] | 434 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Common
|  | 463 | Later | S&L | SAU4005-G000-C__-&EEC-00790 | Technical Specifications for Field Instruments | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | I&C&DCS | Instrumentation & Control | Common |  | IFA | IFP |  |  | 2025-11-20 |  | 2025-10-15 |  | 2025-12-10 |  | 2025-10-29 |  | 2026-01-19 |  | 2026-02-15 | [9 empty] | 211 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 464 | Later | S&L | SAU4005-G000-C__-&EEC-00791 | Technical Specifications for Pneumatic On/Off & Modulating Control Valves and Accessories | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | I&C&DCS | Instrumentation & Control | Common |  | IFA | IFP |  |  | 2025-10-10 |  | 2025-10-17 |  | 2025-11-03 |  | 2025-11-04 |  | 2025-12-09 |  | 2025-12-09 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | RESPECTIVE EM
|  | 465 | Later | S&L | SAU4005-G000-C__-&EEC-00792 | Technical Specifications for SWAS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFP |  |  | 2025-09-03 |  | 2025-07-28 |  | 2025-09-23 |  | 2025-08-12 |  | 2025-10-03 |  | 2025-10-15 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | RESPECTIVE EM
|  | 466 | Later | S&L | SAU4005-G000-C__-&EEC-00794 | Technical Specifications for Vibration measurement system | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | I&C&DCS | Instrumentation & Control | DOOSAN |  | IFA | IFP |  |  | 2025-09-30 |  | 2025-04-25 |  | 2025-10-24 |  | 2025-05-09 |  | 2025-12-01 |  | 2025-05-20 | [9 empty] | 726 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | C1 | NO |  | NO | Common
|  | 467 | Later | S&L | SAU4005-G000-C__-&EEC-00795 | Technical Specifications for Weather Station | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFP |  |  | 2025-12-25 |  | 2025-10-24 |  | 2026-01-15 |  | 2025-11-11 |  | 2026-01-22 |  | 2026-03-29 | [9 empty] | 470 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 468 | Later | S&L | SAU4005-G000-C__-&EEC-00796 | Technical Specifications for I & C Cable | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | I&C&DCS | Instrumentation & Control | Common |  | IFA | IFP |  |  | 2025-06-09 |  | 2025-05-08 |  | 2025-06-27 |  | 2025-05-20 |  | 2025-08-04 |  | 2025-10-05 | [9 empty] | 389 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 469 | Later | S&L | SAU4005-G000-C__-&EEC-00799 | Technical Specifications for Junction Box & Transmitter rack | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | I&C&DCS | Instrumentation & Control | Common |  | IFA | IFP |  |  | 2025-12-08 |  | 2025-10-13 |  | 2025-12-26 |  | 2025-10-22 |  | 2026-02-04 |  | 2026-02-09 | [9 empty] | 470 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 471 | Later | S&L | SAU4005-G000-C__-&EEC-00841 | Technical Specifications for Plant Settlement System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFP |  |  | 2025-08-19 |  | 2025-09-07 |  | 2025-09-09 |  | 2025-09-26 |  | 2025-09-16 |  | 2025-12-23 | [9 empty] | 609 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 472 | Later | S&L | SAU4005-G000-C__-&EEC-00849 | Technical Specification of CCTV | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | I&C&DCS | Instrumentation & Control | SEPCOIII |  | IFA | IFP |  |  | 2025-09-05 |  | 2025-06-26 |  | 2025-09-25 |  | 2025-07-10 |  | 2025-10-07 |  | 2025-09-21 | [9 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Common
|  | 473 | Later | S&L | SAU4005-G000-UER-&ELH-00862 | Equipment Layout for Fuel Gas Electrical Switchgear Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-10-20 |  | 2025-08-12 |  | 2025-11-09 |  | 2025-08-27 |  | 2025-12-17 |  | 2025-12-17 | [9 empty] | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
|  | 474 | Later | S&L | SAU4005-G000-UYC-&ELH-00863 | Equipment Layout for Administration Electrical Switchgear building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-09-20 |  | 2025-08-19 |  | 2025-10-10 |  | 2025-09-02 |  | 2025-11-17 |  | 2026-02-16 | [9 empty] | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 475 | Later | S&L | SAU4005-G000-U__-&CDB-00900 | Design Criteria Document for Civil, Structural, Architectural works | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-03-03 |  | 2025-02-24 |  | 2025-03-28 |  | 2025-06-09 |  | 2025-07-02 |  | 2025-08-04 | [9 empty] | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 476 | Later | S&L | SAU4005-G000-U__-&CTA-00901 | Steel Standard drawings | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-04-02 |  | 2025-02-20 |  | 2025-04-22 |  | 2025-03-07 |  | 2025-08-08 |  | 2025-05-09 | [9 empty] | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | NO |  | NO | Common
|  | 477 | Later | S&L | SAU4005-G000-U__-&CTA-00910 | Concrete standard drawings | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-04-02 |  | 2025-02-25 |  | 2025-04-22 |  | 2025-03-28 |  | 2025-08-08 |  | 2025-08-04 | [9 empty] | 680 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Open
|  | 478 | Later | S&L | SAU4005-G000-U__-&CTA-00917 | Architectural Standard drawings | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-04-02 |  | 2025-02-25 |  | 2025-04-22 |  | 2025-03-07 |  | 2025-08-08 |  | 2025-05-12 | [9 empty] | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 479 | Later | S&L | SAU4005-G000-U__-&CTL-00926 | Site Grading - Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-05-19 |  | 2025-03-02 |  | 2025-06-06 |  | 2025-03-13 |  | 2025-07-01 |  | 0 | [5 empty] | 2025-07-01 |  |  |  | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 480 | Later | S&L | SAU4005-G000-GU_-&CED-00927 | Storm Water Drainage network Design calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-10-10 |  | 2025-08-22 |  | 2025-11-03 |  | 2025-10-19 |  | 2026-02-19 |  | 2026-01-15 | [9 empty] | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 481 | Later | S&L | SAU4005-G000-UGH-&CTB-00928 | Storm Water Drainage network - Layout and details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-09-02 |  | 2025-08-15 |  | 2025-09-22 |  | 2025-10-22 |  | 2026-01-17 |  | 2026-02-02 | [5 empty] | 2026-01-17 |  |  |  | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 482 | Later | S&L | SAU4005-G000-GT_-&CED-00929 | Evaporation Pond for Process Water - Design calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-08-13 |  | 2025-06-24 |  | 2025-09-04 |  | 2025-07-09 |  | 2026-02-09 |  | 0 | [9 empty] | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 483 | Later | S&L | SAU4005-G000-UGX-&CTB-00930 | Evaporation Pond for Process Water - Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-07-31 |  | 2025-06-24 |  | 2025-08-21 |  | 2025-07-09 |  | 2026-02-09 |  | 0 | [5 empty] | 2026-02-09 |  |  |  | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 484 | Later | S&L | SAU4005-G000-GU_-&CED-00931 | Evaporation Pond for Storm Water - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-07-31 |  | 2025-07-08 |  | 2025-08-21 |  | 2025-07-09 |  | 2025-09-18 |  | 2026-03-29 | [9 empty] | 680 | [13 empty] | WF Transmittal DI-EPC-ACWA |  | NO | NO | NO | NO |  | NO
|  | 485 | Later | S&L | SAU4005-G000-UGH-&CTB-00932 | Evaporation Pond for Storm Water - Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-07-31 |  | 2025-07-08 |  | 2025-08-21 |  | 2025-07-08 |  | 2025-09-18 |  | 0 | [5 empty] | 2025-09-18 |  |  |  | 871 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 486 | Later | S&L | SAU4005-G000-UMB-&CED-00933 | Gas Turbine, Generator Unit-11, 12 & 13 Foundation - Design Calculation - Static & Dyanamic Analysis | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-08-04 |  | 2025-06-13 |  | 2025-08-21 |  | 2025-06-26 |  | 2025-12-29 |  | 2025-07-29 | [9 empty] | 372 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 487 | Later | S&L | SAU4005-G000-UMB-&CLB-00934 | Gas Turbine, Generator & Auxiliaries Area - Overall Foundation Layout | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-12-15 |  | 2025-10-11 |  | 2026-01-04 |  | 2025-10-23 |  | 2026-02-09 |  | 2025-12-08 | [5 empty] | 2026-02-09 |  |  |  | 372 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 488 | Later | S&L | SAU4005-G000-UMB-&CLB-00935 | Gas Turbine, Generator Unit-11, 12 & 13 Foundation Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-08-01 |  | 2025-06-13 |  | 2025-08-22 |  | 2025-06-26 |  | 2025-09-18 |  | 2025-07-31 | [5 empty] | 2025-09-18 |  |  |  | 372 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 489 | Later | S&L | SAU4005-G000-UMB-&CLB-00936 | Gas Turbine, Generator Unit-11, 12 & 13 Foundation RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-08-04 |  | 2025-06-13 |  | 2025-08-25 |  | 2025-06-26 |  | 2026-01-22 |  | 2025-08-03 | [5 empty] | 2026-01-22 |  |  |  | 1150 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 490 | Later | S&L | SAU4005-G000-UMB-&CLB-00937 | Gas Turbine, Generator Unit-11, 12 & 13 Foundation Embedment Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-08-01 |  | 2025-06-13 |  | 2025-08-21 |  | 2025-06-26 |  | 2025-09-23 |  | 2025-07-10 | [5 empty] | 2025-09-23 |  |  |  | 372 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 491 | Later | S&L | SAU4005-G000-UMB-&CTB-00938 | Gas Turbine, Generator & Auxiliaries Area Unit-11, 12 & 13 - Miscellaneous Platform details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-12-01 |  |  |  | 2025-11-25 |  | 2025-10-14 |  | 2025-12-01 |  |  |  | 372 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 493 | Later | S&L | SAU4005-G000-UMB-&CED-01392 | Gas Turbine, Generator -11, 12 & 13 - Design calculation - RC Design | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-10-09 |  | 2025-06-13 |  | 2025-10-31 |  | 2025-07-01 |  | 2026-01-30 |  | 2025-08-04 | [5 empty] | 2026-01-30 |  |  |  | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 494 | Later | S&L | SAU4005-G000-UMA-&CED-00940 | Steam Turbine, Generator Foundation - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-03-25 |  | 2025-12-24 |  | 2026-04-10 |  | 2026-01-08 |  | 2026-05-08 |  | 2026-02-18 | [9 empty] | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 495 | Later | S&L | SAU4005-G000-UMA-&CLB-00941 | Steam Turbine, Generator Foundation Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-12-25 |  | 2025-12-24 |  | 2026-01-15 |  | 2026-01-08 |  | 2026-02-13 |  | 2026-02-19 | [5 empty] | 2026-02-13 |  |  |  | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 496 | Later | S&L | SAU4005-G000-UMA-&CLB-00942 | Steam Turbine, Generator Foundation RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-06-04 |  |  |  | 2026-02-23 |  | 2025-12-24 |  | 2026-06-04 |  |  |  | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 497 | Later | S&L | SAU4005-G000-UMA-&CLB-00943 | Steam Turbine, Generator Foundation Embedment Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-06-29 |  |  |  | 2026-03-16 |  | 2025-12-24 |  | 2026-06-29 |  |  |  | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 498 | Later | S&L | SAU4005-G000-UMA-&CED-00944 | STG Building Foundation - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-17 |  | 2026-01-14 |  | 2026-03-10 |  | 2026-01-21 |  | 2026-04-06 |  | 2026-02-01 | [9 empty] | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 499 | Later | S&L | SAU4005-G000-UMA-&CED-00945 | STG Building Superstructure - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-16 |  | 2025-12-26 |  | 2026-03-09 |  | 2026-01-11 |  | 2026-04-21 |  | 2026-02-04 | [9 empty] | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 500 | Later | S&L | SAU4005-G000-UMA-&CED-00946 | STG Building Purlin and Girt - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-16 |  | 2025-12-26 |  | 2026-03-09 |  | 2026-01-11 |  | 2026-04-02 |  | 2026-02-04 | [9 empty] | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 501 | Later | S&L | SAU4005-G000-UMA-&CLH-00947 | STG Building - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-12-11 |  | 2025-09-05 |  | 2025-12-31 |  | 2025-09-21 |  | 2026-02-18 |  | 2026-04-26 | [5 empty] | 2026-02-18 |  |  |  | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 502 | Later | S&L | SAU4005-G000-UMA-&CLB-00948 | STG Building - Foundation& Pier Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-02-17 |  | 2026-01-14 |  | 2026-03-10 |  | 2026-01-21 |  | 2026-04-29 |  | 0 | [5 empty] | 2026-04-29 |  |  |  | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 505 | Later | S&L | SAU4005-G000-UMA-&CLH-00951 | STG Building - Base Plate Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-14 |  |  |  | 2026-02-04 |  | 2025-12-26 |  | 2026-04-14 |  |  |  | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 506 | Later | S&L | SAU4005-G000-UMA-&CLH-00952 | STG Building - Framing Elevations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-05-19 |  |  |  | 2026-02-16 |  | 2025-12-26 |  | 2026-05-19 |  |  |  | 836 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 507 | Later | S&L | SAU4005-G000-UMA-&CLH-00953 | STG Building - Operation Floor Framing Plan and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-05-19 |  |  |  | 2026-02-16 |  | 2025-12-26 |  | 2026-05-19 |  |  |  | 664 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 508 | Later | S&L | SAU4005-G000-UMA-&CLH-00954 | STG Building - Crane Girder Layout & Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-21 |  |  |  | 2026-02-04 |  | 2025-12-26 |  | 2026-04-21 |  |  |  | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 509 | Later | S&L | SAU4005-G000-UMA-&CLH-00955 | STG Building - Miscellaneous platforms -Layout & Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-03-26 |  | 2025-12-26 |  | 2026-04-15 |  | 2026-01-11 |  | 2026-05-11 |  | 2026-01-12 | [5 empty] | 2026-05-11 |  |  |  | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 510 | Later | S&L | SAU4005-G000-UMA-&CLH-00956 | STG Building - Roof Framing Plan and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-06-12 |  |  |  | 2026-03-26 |  | 2025-12-26 |  | 2026-06-12 |  |  |  | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 511 | Later | S&L | SAU4005-G000-UMA-&CLH-00957 | STG Building - Purlin Plan and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-05-13 |  |  |  | 2026-03-26 |  | 2025-12-26 |  | 2026-05-13 |  |  |  | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 512 | Later | S&L | SAU4005-G000-UMA-&CLH-00958 | STG Building - Girt Elevations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-05-11 |  |  |  | 2026-03-26 |  | 2025-12-26 |  | 2026-05-11 |  |  |  | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
|  | 513 | Later | S&L | SAU4005-G000-UMA-&CLH-00959 | STG Building - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-05-18 |  |  |  | 2026-03-26 |  |  |  | 2026-05-18 |  |  |  | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
|  | 514 | Later | S&L | SAU4005-G000-UMA-&CLH-00960 | STG Building - Staircases Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-05-11 |  |  |  | 2026-03-26 |  | 2025-12-26 |  | 2026-05-11 |  |  |  | 687 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 515 | Later | S&L | SAU4005-G000-URC-&CED-00961 | ACC Foundation - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-09-10 |  | 2025-08-20 |  | 2025-10-03 |  | 2025-08-31 |  | 2025-10-31 |  | 2025-10-12 | [9 empty] | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 516 | Later | S&L | SAU4005-G000-URC-&CLB-00962 | ACC Foundation& Pier - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-09-18 |  | 2025-08-20 |  | 2025-10-08 |  | 2025-08-31 |  | 2025-10-31 |  | 2025-09-26 | [5 empty] | 2025-10-31 |  |  |  | 891 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 517 | Later | S&L | SAU4005-G000-UGA-&CED-00963 | Water & Waste Water Storage Tank Foundation - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-03 |  | 2025-12-13 |  | 2025-12-23 |  | 2025-12-28 |  | 2026-01-27 |  | 2026-01-19 | [9 empty] | 360 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 518 | Later | S&L | SAU4005-G000-UGA-&CLB-00964 | Water & Waste Water Storage Tank Foundation - Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-01-27 |  |  |  | 2025-12-22 |  | 2025-12-13 |  | 2026-01-27 |  |  |  | 360 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 519 | Later | S&L | SAU4005-G000-URX-&CED-00965 | Fin Fan Cooler CCCW system - Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-01-06 |  | 2025-11-09 |  | 2026-01-28 |  | 2025-11-18 |  | 2026-02-24 |  | 2025-11-23 | [9 empty] | 360 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 520 | Later | S&L | SAU4005-G000-URX-&CLB-00966 | Fin Fan Cooler CCCW system - Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-02-24 |  |  |  | 2026-01-16 |  | 2025-11-09 |  | 2026-02-24 |  |  |  | 360 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 521 | Later | S&L | SAU4005-G000-URX-&CED-00967 | Fin Fan Cooler (GBC Area) Foundation - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-05 |  | 2025-10-29 |  | 2025-12-25 |  | 0 |  | 2026-01-22 |  | 2025-11-17 | [9 empty] | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 522 | Later | S&L | SAU4005-G000-URX-&CLB-00968 | Fin Fan Cooler (GBC Area) Foundation layout and RC details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-01-22 |  |  |  | 2025-12-16 |  | 2025-10-29 |  | 2026-01-22 |  |  |  | 360 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 523 | Later | S&L | SAU4005-G000-UCA-&CED-00969 | Main Electrical & Control Building - Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-07-11 |  | 2025-07-24 |  | 2025-07-31 |  | 2025-03-10 |  | 2025-08-29 |  | 2025-08-12 | [9 empty] | 360 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 524 | Later | S&L | SAU4005-G000-UCA-&CED-00970 | Main Electrical & Control Building - Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-07-11 |  | 2025-09-05 |  | 2025-07-31 |  | 2025-09-21 |  | 2025-09-05 |  | 2025-10-15 | [9 empty] | 360 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 525 | Later | S&L | SAU4005-G000-UCA-&CLH-00971 | Main Electrical & Control Building - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-06-24 |  | 2025-06-13 |  | 2025-07-15 |  | 2025-07-01 |  | 2026-03-11 |  | 0 | [5 empty] | 2026-03-11 |  |  |  | 1011 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
|  | 526 | Later | S&L | SAU4005-G000-UCA-&CLH-00972 | Main Electrical & Control Building - Toilet and False ceiling Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-29 |  |  |  | 2025-09-05 |  | 2025-06-13 |  | 2026-04-29 |  |  |  | 615 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 527 | Later | S&L | SAU4005-G000-UCA-&CLB-00973 | Main Electrical & Control Building - Foundation and Column Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-08-29 |  |  |  | 2025-07-11 |  | 2025-07-24 |  | 2025-08-29 |  |  |  | 615 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 528 | Later | S&L | SAU4005-G000-UCA-&CTL-00974 | Main Electrical & Control Building - Grade Beam Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-09-12 |  |  |  | 2025-07-11 |  | 2025-07-24 |  | 2025-09-12 |  |  |  | 249 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 529 | Later | S&L | SAU4005-G000-UCA-&CTL-00975 | Main Electrical & Control Building - First Floor Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-10-13 |  |  |  | 2025-08-22 |  | 2025-09-05 |  | 2025-10-13 |  |  |  | 249 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 531 | Later | S&L | SAU4005-G000-UCA-&CTL-00977 | Main Electrical & Control Building - Roof Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-09-25 |  |  |  | 2025-08-08 |  | 2025-09-05 |  | 2025-09-25 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 532 | Later | S&L | SAU4005-G000-UCA-&CTL-00978 | Main Electrical & Control Building - Staircase -1 Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-02-09 |  |  |  | 2025-12-23 |  | 2025-09-05 |  | 2026-02-09 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 533 | Later | S&L | SAU4005-G000-UCA-&CTL-00979 | Main Electrical & Control Building - Staircase -2 Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-02-16 |  |  |  | 2025-10-28 |  | 2025-09-05 |  | 2026-02-16 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 534 | Later | S&L | SAU4005-G000-UCA-&CTL-00980 | Main Electrical & Control Building - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-06-09 |  |  |  | 2026-04-03 |  | 2025-10-17 |  | 2026-06-09 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 535 | Later | S&L | SAU4005-G000-UHA-&CED-00988 | HRSG Unit - 11, 12 & 13 Foundation - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-08-01 |  | 2025-07-16 |  | 2025-08-22 |  | 2025-07-25 |  | 2025-09-17 |  | 2025-08-08 | [9 empty] | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 536 | Later | S&L | SAU4005-G000-UHA-&CLB-00989 | HRSG Unit - 11, 12 & 13 Foundation - Layout and details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-07-21 |  | 2025-07-16 |  | 2025-08-08 |  | 2025-07-27 |  | 2025-09-17 |  | 0 | [5 empty] | 2025-09-17 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 537 | Later | S&L | SAU4005-G000-UHA-&CLB-00990 | HRSG Unit - 11, 12 & 13 Foundation - RC details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-09-17 |  |  |  | 2025-07-31 |  | 2025-07-17 |  | 2025-09-17 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 539 | Later | S&L | SAU4005-G000-UYC-&CED-00992 | Administration & Social Building - Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-09-12 |  | 2025-06-10 |  | 2025-10-07 |  | 2025-06-24 |  | 2025-11-07 |  | 2025-07-15 | [9 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 540 | Later | S&L | SAU4005-G000-UYC-&CED-00993 | Administration & Social Building - Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-09-12 |  | 2025-06-20 |  | 2025-10-07 |  | 2025-07-07 |  | 2025-11-07 |  | 2025-08-07 | [9 empty] | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 541 | Later | S&L | SAU4005-G000-UYC-&CLH-00994 | Administration & Social Building - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-05-30 |  | 2025-04-02 |  | 2025-06-20 |  | 2025-04-16 |  | 2025-10-31 |  | 0 | [5 empty] | 2025-10-31 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 542 | Later | S&L | SAU4005-G000-UYC-&CLH-00995 | Administration & Social Building - False ceiling Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-11-06 |  |  |  | 2025-07-02 |  | 2025-04-02 |  | 2025-11-06 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 543 | Later | S&L | SAU4005-G000-UYC-&CLB-00996 | Administration & Social Building - Foundation & Column Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-11-07 |  |  |  | 2025-09-12 |  | 2025-06-10 |  | 2025-11-07 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 544 | Later | S&L | SAU4005-G000-UYC-&CTL-00997 | Administration & Social Building - First Floor Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-11-14 |  |  |  | 2025-09-12 |  | 2025-06-20 |  | 2025-11-14 |  |  |  | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 545 | Later | S&L | SAU4005-G000-UYC-&CTL-00998 | Administration & Social Building - Roof Slabs Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-11-14 |  |  |  | 2025-09-12 |  | 2025-06-20 |  | 2025-11-14 |  |  |  | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 546 | Later | S&L | SAU4005-G000-UYC-&CTL-00999 | Administration & Social Building - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-11-21 |  |  |  | 2025-09-12 |  | 2025-06-20 |  | 2025-11-21 |  |  |  | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 547 | Later | S&L | SAU4005-G000-UYC-&CTL-01000 | Administration & Social Building - Staircases-1 Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-12-24 |  |  |  | 2025-11-10 |  | 2025-06-20 |  | 2025-12-24 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 548 | Later | S&L | SAU4005-G000-UYC-&CTL-01001 | Administration & Social Building - Staircases-2 Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-12-31 |  |  |  | 2025-11-10 |  | 2025-06-20 |  | 2025-12-31 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
| Issuer changed | 549 | Later | SAIS | SAU4005-G000-UYF-&CED-01002 | Security and Control center - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-05-12 |  | 2026-04-17 |  | 2026-06-01 |  | 2026-04-21 |  | 2026-06-25 |  | 2026-04-28 | [9 empty] | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
| Issuer changed | 550 | Later | SAIS | SAU4005-G000-UYF-&CLH-01003 | Security and Control center - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-11-20 |  | 2026-02-25 |  | 2025-12-09 |  | 2026-03-10 |  | 2026-04-02 |  | 0 | [5 empty] | 2026-04-02 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
| Issuer changed | 551 | Later | SAIS | SAU4005-G000-UYF-&CLH-01004 | Security and Control center - Toilet and False ceiling Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-05-14 |  |  |  | 2026-05-08 |  | 2026-02-25 |  | 2026-05-14 |  |  |  | 500 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
| Issuer changed | 552 | Later | SAIS | SAU4005-G000-UYF-&CLB-01005 | Security and Control center - Foundation and Column Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-06-25 |  |  |  | 2026-05-26 |  | 2026-04-17 |  | 2026-06-25 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 553 | Later | S&L | SAU4005-G000-UYF-&CLH-01006 | Security and Control center - Roof Slabs Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-08-07 |  |  |  | 2026-08-04 |  | 2026-04-17 |  | 2026-08-07 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 554 | Later | S&L | SAU4005-G000-UYF-&CLH-01007 | Security and Control center - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-09-17 |  |  |  | 2026-09-10 |  | 2026-05-22 |  | 2026-09-17 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 555 | Later | S&L | SAU4005-G000-UST-&CED-01010 | Workshop and Warehouse Building - Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-09-12 |  | 2025-09-07 |  | 2025-10-07 |  | 2025-10-02 |  | 2025-11-05 |  | 2025-11-09 | [9 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 556 | Later | S&L | SAU4005-G000-UST-&CED-01011 | Workshop and Warehouse Building - Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-10-20 |  | 2025-11-02 |  | 2025-11-11 |  | 2025-11-20 |  | 2025-12-08 |  | 2025-12-28 | [9 empty] | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 557 | Later | S&L | SAU4005-G000-UST-&CLH-01012 | Workshop and Warehouse Building - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-07-24 |  | 2025-06-05 |  | 2025-08-13 |  | 2025-06-19 |  | 2025-09-11 |  | 0 | [5 empty] | 2025-09-11 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 558 | Later | S&L | SAU4005-G000-UST-&CLH-01013 | Workshop and Warehouse Building - Toilet and False ceiling Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-01-28 |  |  |  | 2025-12-10 |  | 2025-06-05 |  | 2026-01-28 |  |  |  | 285 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 559 | Later | S&L | SAU4005-G000-UST-&CLB-01014 | Workshop and Warehouse Building - Foundation and Pier Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-12-08 |  |  |  | 2025-10-20 |  | 2025-09-07 |  | 2025-12-08 |  |  |  | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 560 | Later | S&L | SAU4005-G000-UST-&CTL-01015 | Workshop and Warehouse Building - Grade Beam Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-01-09 |  |  |  | 2025-11-26 |  | 2025-09-07 |  | 2026-01-09 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 561 | Later | S&L | SAU4005-G000-UST-&CTB-01016 | Workshop and Warehouse Building - Base Plate and Framing Plan, Elevations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-02-19 |  |  |  | 2026-01-01 |  | 2025-11-02 |  | 2026-02-19 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 562 | Later | S&L | SAU4005-G000-UST-&CTB-01491 | Workshop and Warehouse Building - Crane Girder Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-07-31 |  |  |  | 2026-06-15 |  | 2025-11-02 |  | 2026-07-31 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 563 | Later | S&L | SAU4005-G000-UST-&CTB-01017 | Workshop and Warehouse Building - Purlin Plan and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-03-19 |  |  |  | 2026-01-30 |  | 2025-11-02 |  | 2026-03-19 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 564 | Later | S&L | SAU4005-G000-UST-&CTB-01018 | Workshop and Warehouse Building - Girt Elevations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-03-20 |  |  |  | 2026-02-02 |  | 2025-11-02 |  | 2026-03-20 |  |  |  | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 565 | Later | S&L | SAU4005-G000-UST-&CTL-01019 | Workshop and Warehouse Building - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-05-01 |  |  |  | 2026-01-06 |  | 2025-09-16 |  | 2026-05-01 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 566 | Later | S&L | SAU4005-G000-UGG-&CED-01020 | Potable Water Unloading Area - Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-06-22 |  | 2026-03-27 |  | 2026-07-10 |  | 2026-04-02 |  | 2026-08-06 |  | 2026-04-15 | [9 empty] | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 567 | Later | S&L | SAU4005-G000-UGG-&CTL-01021 | Potable Water Unloading Area - Layout and RC details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-08-06 |  |  |  | 2026-07-03 |  | 2026-03-27 |  | 2026-08-06 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 570 | Later | S&L | SAU4005-G000-UBB-&CED-01025 | Generator Circuit Breaker Unit - 11, 12 & 13 - Supporting structure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-12-17 |  | 2025-10-01 |  | 2026-01-06 |  | 2025-10-14 |  | 2026-02-03 |  | 2025-12-07 | [5 empty] | 2026-02-03 |  |  |  | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 572 | Later | S&L | SAU4005-G000-UBB-&CTB-01027 | Generator Circuit Breaker Unit - 11, 12 & 13 - Supporting structure Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-02-03 |  |  |  | 2026-01-22 |  | 2025-10-01 |  | 2026-02-03 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 573 | Later | S&L | SAU4005-G000-UHX-&CTL-01032 | CEMS Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-08-05 |  |  |  | 2026-07-29 |  | 2026-01-07 |  | 2026-08-05 |  |  |  | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 574 | Later | S&L | SAU4005-G000-UQA-&CLB-01033 | CCCW Pumps - Foundation Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-01-07 |  |  |  | 2026-01-01 |  | 2025-10-04 |  | 2026-01-07 |  |  |  | 547 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 575 | Later | S&L | SAU4005-G000-U__-&CLB-01034 | Miscellaneous Equipment Foundations within Plant boundary - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-06-10 |  |  |  | 2026-06-05 |  | 2026-04-02 |  | 2026-06-10 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 577 | Later | S&L | SAU4005-G000-ULA-&CED-01037 | Feed Water Pumps - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-14 |  | 2026-04-03 |  | 2025-12-04 |  | 2026-04-13 |  | 2025-12-31 |  | 0 | [9 empty] | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 579 | Later | S&L | SAU4005-G000-ULA-&CLB-01039 | Feed Water Pumps - Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-06-16 |  |  |  | 2026-06-09 |  | 2026-04-03 |  | 2026-06-16 |  |  |  | 713 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 580 | Later | S&L | SAU4005-G000-ULC-&CLB-01040 | Condensate Water Pumps Foundation - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-01-12 |  |  |  | 2026-01-07 |  | 2026-01-29 |  | 2026-01-12 |  |  |  | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 585 | Later | S&L | SAU4005-G000-ULC-&CTL-01045 | Condensate receiver drain tank sump - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-02-27 |  |  |  | 2026-02-20 |  | 2026-02-09 |  | 2026-02-27 |  |  |  | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 586 | Later | S&L | SAU4005-G000-USG-&CED-01047 | Fire Water Pump House - Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-03-20 |  | 2025-11-20 |  | 2026-04-09 |  | 2025-12-23 |  | 2026-05-11 |  | 2026-01-07 | [9 empty] | 745 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 587 | Later | S&L | SAU4005-G000-USG-&CLH-01048 | Fire Water Pump House - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-01-02 |  | 2025-10-02 |  | 2026-01-23 |  | 2026-01-04 |  | 2026-02-19 |  | 2026-02-04 | [5 empty] | 2026-02-19 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 588 | Later | S&L | SAU4005-G000-USG-&CLB-01049 | Fire Water Pump House - Foundation & Pier Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-05-18 |  |  |  | 2026-03-20 |  | 2025-11-27 |  | 2026-05-18 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 589 | Later | S&L | SAU4005-G000-USG-&CTB-01050 | Fire Water Pump House - Superstructure Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-14 |  |  |  | 2026-04-06 |  | 2025-11-20 |  | 2026-04-14 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
|  | 590 | Later | S&L | SAU4005-G000-USG-&CTL-01051 | Fire Water Pump House - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-17 |  |  |  | 2025-12-31 |  | 2026-01-22 |  | 2026-04-17 |  |  |  | 353 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 591 | Later | S&L | SAU4005-G000-USC-&CED-01052 | Air Compressor Shed - Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-11-19 |  | 2025-09-26 |  | 2025-12-09 |  | 2025-11-20 |  | 2026-01-05 |  | 2025-11-26 | [5 empty] | 2026-01-05 |  |  |  | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 592 | Later | S&L | SAU4005-G000-USC-&CLH-01053 | Air Compressor Shed - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-09-08 |  | 2025-08-25 |  | 2025-09-26 |  | 2025-09-23 |  | 2026-01-13 |  | 2025-12-04 | [5 empty] | 2026-01-13 |  |  |  | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 593 | Later | S&L | SAU4005-G000-USC-&CLB-01054 | Air Compressor Shed - Foundation & Pier - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-01-05 |  |  |  | 2025-11-28 |  | 2025-10-01 |  | 2026-01-05 |  |  |  | 512 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 594 | Later | S&L | SAU4005-G000-USC-&CTB-01055 | Air Compressor Shed - Superstructure Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-01-12 |  |  |  | 2026-01-05 |  | 2025-09-26 |  | 2026-01-12 |  |  |  | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 595 | Later | S&L | SAU4005-G000-USC-&CTL-01056 | Air Compressor Shed - Grade Slab - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-03-17 |  |  |  | 2026-01-20 |  | 2025-11-04 |  | 2026-03-17 |  |  |  | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 602 | Later | S&L | SAU4005-G000-UGD-&CED-01064 | Water and Effluent treatment building - Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-28 |  | 2025-10-07 |  | 2025-12-18 |  | 2025-10-23 |  | 2026-01-15 |  | 2025-11-19 | [9 empty] | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 603 | Later | S&L | SAU4005-G000-UGD-&CED-01065 | Water and Effluent treatment building - Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-01-02 |  | 2025-10-02 |  | 2026-01-23 |  | 2025-10-14 |  | 2026-02-02 |  | 2025-12-08 | [9 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 604 | Later | S&L | SAU4005-G000-UGD-&CLH-01066 | Water and Effluent treatment building - Architectural Layout & Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-09-15 |  | 2025-09-11 |  | 2025-10-13 |  | 2025-11-24 |  | 2026-02-09 |  | 2026-04-12 | [5 empty] | 2026-02-09 |  |  |  | 599 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 605 | Later | S&L | SAU4005-G000-UGD-&CLB-01067 | Water and Effluent treatment building - Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-01-21 |  |  |  | 2025-11-28 |  | 2025-10-07 |  | 2026-01-21 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 607 | Later | S&L | SAU4005-G000-UGD-&CTL-01069 | Water and Effluent treatment building - Framing Plan and Elevation Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-02-02 |  |  |  | 2026-01-27 |  | 2025-10-02 |  | 2026-02-02 |  |  |  | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 608 | Later | S&L | SAU4005-G000-UGD-&CTL-01070 | Water and Effluent treatment building - Side Runner and Purlin Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-02-20 |  |  |  | 2026-02-18 |  | 2025-10-02 |  | 2026-02-20 |  |  |  | 599 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 609 | Later | S&L | SAU4005-G000-UGD-&CTL-01071 | Water and Effluent treatment building - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-03-17 |  |  |  | 2026-03-13 |  | 2025-10-16 |  | 2026-03-17 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 610 | Later | S&L | SAU4005-G000-UGD-&CED-01072 | DM Water storage tank Foundation - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-09-05 |  | 2025-09-03 |  | 2025-09-25 |  | 2025-09-16 |  | 2025-10-15 |  | 2025-10-07 | [9 empty] | 356 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 611 | Later | S&L | SAU4005-G000-UGD-&CLB-01073 | DM Water storage tank Foundation - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-09-17 |  | 2025-09-03 |  | 2025-10-07 |  | 2025-09-16 |  | 2025-10-15 |  | 2025-10-07 | [5 empty] | 2025-10-15 |  |  |  | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 612 | Later | S&L | SAU4005-G000-UGF-&CED-01074 | Service and Fire Water Tank foundation - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-28 |  | 2025-09-03 |  | 2025-12-18 |  | 2025-09-16 |  | 2026-01-13 |  | 0 | [9 empty] | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 613 | Later | S&L | SAU4005-G000-UGF-&CLB-01075 | Service and Fire Water Tank foundation - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-12-10 |  | 2025-09-03 |  | 2025-12-30 |  | 2025-09-16 |  | 2026-01-13 |  | 0 | [5 empty] | 2026-01-13 |  |  |  | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 614 | Later | S&L | SAU4005-G000-UZT-&CED-01076 | Pipe Rack PR-01 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-10-29 |  | 2025-09-19 |  | 2025-11-18 |  | 2025-09-26 |  | 2026-01-19 |  | 2025-11-18 | [9 empty] | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 615 | Later | S&L | SAU4005-G000-UZT-&CED-01077 | Pipe Rack PR-01 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-09-20 |  | 2025-08-31 |  | 2025-10-10 |  | 2025-09-11 |  | 2025-11-14 |  | 2025-11-18 | [9 empty] | 434 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 616 | Later | S&L | SAU4005-G000-UZT-&CLB-01078 | Pipe Rack PR-01 : Foundation Pier Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-01-28 |  |  |  | 2025-11-10 |  | 2025-09-19 |  | 2026-01-28 |  |  |  | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 617 | Later | S&L | SAU4005-G000-UZT-&CTB-01079 | Pipe Rack PR-01 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-09-25 |  |  |  | 2025-09-23 |  | 2025-08-31 |  | 2025-09-25 |  |  |  | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 618 | Later | S&L | SAU4005-G000-UZT-&CED-01080 | Pipe Rack PR-02 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-17 |  | 2025-11-25 |  | 2025-12-07 |  | 2025-11-30 |  | 2026-01-11 |  | 2025-12-21 | [9 empty] | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 619 | Later | S&L | SAU4005-G000-UZT-&CED-01081 | Pipe Rack PR-02 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-09-20 |  | 2025-10-27 |  | 2025-10-10 |  | 2025-10-29 |  | 2025-11-14 |  | 2025-12-11 | [9 empty] | 434 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 620 | Later | S&L | SAU4005-G000-UZT-&CLB-01082 | Pipe Rack PR-02 : Foundation Pier Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-12-31 |  |  |  | 2025-12-01 |  | 2025-11-25 |  | 2025-12-31 |  |  |  | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 621 | Later | S&L | SAU4005-G000-UZT-&CTB-01083 | Pipe Rack PR-02 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-10-16 |  |  |  | 2025-09-18 |  | 2025-10-27 |  | 2025-10-16 |  |  |  | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 622 | Later | S&L | SAU4005-G000-UZT-&CED-01084 | Pipe Rack PR-03 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-04 |  | 2025-12-08 |  | 2025-11-24 |  | 2025-12-21 |  | 2025-12-29 |  | 2025-12-28 | [9 empty] | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 623 | Later | S&L | SAU4005-G000-UZT-&CED-01085 | Pipe Rack PR-03 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-10-20 |  | 2025-10-27 |  | 2025-11-09 |  | 2025-11-04 |  | 2025-12-14 |  | 2025-12-09 | [9 empty] | 434 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 624 | Later | S&L | SAU4005-G000-UZT-&CLB-01086 | Pipe Rack PR-03 : Foundation Pier Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-12-15 |  |  |  | 2025-11-05 |  | 2025-12-08 |  | 2025-12-15 |  |  |  | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 625 | Later | S&L | SAU4005-G000-UZT-&CTB-01087 | Pipe Rack PR-03 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-12-08 |  |  |  | 2025-10-27 |  | 2025-10-27 |  | 2025-12-08 |  |  |  | 500 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
|  | 626 | Later | S&L | SAU4005-G000-UZT-&CED-01088 | Pipe Rack PR-04 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-12 |  | 2025-10-26 |  | 2026-01-01 |  | 2025-10-29 |  | 2026-02-05 |  | 2025-12-01 | [9 empty] | 550 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
|  | 627 | Later | S&L | SAU4005-G000-UZT-&CED-01089 | Pipe Rack PR-04 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-09-30 |  | 2025-09-28 |  | 2025-10-20 |  | 2025-09-21 |  | 2025-12-19 |  | 2025-11-26 | [9 empty] | 450 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
|  | 628 | Later | S&L | SAU4005-G000-UZT-&CLB-01090 | Pipe Rack PR-04 : Foundation Pier Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-01-29 |  |  |  | 2025-12-26 |  | 2025-10-26 |  | 2026-01-29 |  |  |  | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
|  | 629 | Later | S&L | SAU4005-G000-UZT-&CTB-01091 | Pipe Rack PR-04 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-12-26 |  |  |  | 2025-10-16 |  | 2025-09-28 |  | 2025-12-26 |  |  |  | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 631 | Later | S&L | SAU4005-G000-UZT-&CTB-01093 | Pipe sleeper SL-01 Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-01-29 |  |  |  | 2025-12-25 |  | 2025-12-30 |  | 2026-01-29 |  |  |  | 434 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 632 | Later | S&L | SAU4005-G000-UZT-&CED-01394 | Pipe Rack PR-05 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-15 |  | 2025-10-29 |  | 2026-01-02 |  | 2025-11-17 |  | 2026-02-03 |  | 2025-11-26 | [9 empty] | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 633 | Later | S&L | SAU4005-G000-UZT-&CED-01395 | Pipe Rack PR-05 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-10-20 |  | 2025-09-28 |  | 2025-11-11 |  | 2025-09-21 |  | 2025-12-09 |  | 2025-11-26 | [9 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 634 | Later | S&L | SAU4005-G000-UZT-&CLB-01396 | Pipe Rack PR-05 : Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-01-01 |  |  |  | 2025-12-12 |  | 2025-10-29 |  | 2026-01-01 |  |  |  | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 635 | Later | S&L | SAU4005-G000-UZT-&CTB-01397 | Pipe Rack PR-05 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-11-11 |  |  |  | 2025-10-20 |  | 2025-09-28 |  | 2025-11-11 |  |  |  | 444 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 636 | Later | S&L | SAU4005-G000-UZT-&CED-01398 | Pipe Rack PR-06 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-10-20 |  | 2025-09-19 |  | 2025-11-11 |  | 2025-09-26 |  | 2025-12-09 |  | 2025-11-18 | [9 empty] | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 637 | Later | S&L | SAU4005-G000-UZT-&CED-01399 | Pipe Rack PR-06 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-09-17 |  | 2025-08-31 |  | 2025-10-10 |  | 2025-09-11 |  | 2025-11-11 |  | 2025-12-08 | [9 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 638 | Later | S&L | SAU4005-G000-UZT-&CLB-01400 | Pipe Rack PR-06 : Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-11-11 |  |  |  | 2025-10-20 |  | 2025-09-19 |  | 2025-11-11 |  |  |  | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 639 | Later | S&L | SAU4005-G000-UZT-&CTB-01401 | Pipe Rack PR-06 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-10-10 |  |  |  | 2025-09-17 |  | 2025-08-31 |  | 2025-10-10 |  |  |  | 434 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 640 | Later | S&L | SAU4005-G000-UZT-&CED-01402 | Pipe Rack PR-07 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-11 |  | 2025-12-26 |  | 2026-03-03 |  | 2026-01-07 |  | 2026-04-01 |  | 2026-01-19 | [9 empty] | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 641 | Later | S&L | SAU4005-G000-UZT-&CED-01403 | Pipe Rack PR-07 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-10-29 |  | 2025-11-09 |  | 2025-11-18 |  | 2025-11-18 |  | 2025-12-16 |  | 2025-12-14 | [9 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 642 | Later | S&L | SAU4005-G000-UZT-&CLB-01404 | Pipe Rack PR-07 : Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-03-03 |  |  |  | 2026-02-11 |  | 2025-12-26 |  | 2026-03-03 |  |  |  | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 643 | Later | S&L | SAU4005-G000-UZT-&CTB-01405 | Pipe Rack PR-07 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-12-09 |  |  |  | 2025-11-19 |  | 2025-11-09 |  | 2025-12-09 |  |  |  | 434 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 644 | Later | S&L | SAU4005-G000-UZT-&CED-01497 | Pipe Rack PR-08 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-03-06 |  | 2025-12-25 |  | 2026-03-26 |  | 2025-12-30 |  | 2026-04-23 |  | 2026-01-08 | [9 empty] | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 645 | Later | S&L | SAU4005-G000-UZT-&CED-01498 | Pipe Rack PR-08 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-02 |  | 2025-12-08 |  | 2025-12-22 |  | 2025-12-23 |  | 2026-01-20 |  | 2025-12-28 | [9 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 646 | Later | S&L | SAU4005-G000-UZT-&CLB-01499 | Pipe Rack PR-08 : Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-15 |  |  |  | 2026-03-06 |  | 2025-12-25 |  | 2026-04-15 |  |  |  | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 647 | Later | S&L | SAU4005-G000-UZT-&CTB-01500 | Pipe Rack PR-08 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-12-22 |  |  |  | 2025-12-02 |  | 2025-12-08 |  | 2025-12-22 |  |  |  | 434 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 648 | Later | S&L | SAU4005-G000-UZT-&CED-01410 | Pipe Rack PR-09 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-01-22 |  | 2025-11-26 |  | 2026-02-12 |  | 2025-11-30 |  | 2026-03-13 |  | 2025-12-11 | [9 empty] | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 649 | Later | S&L | SAU4005-G000-UZT-&CED-01411 | Pipe Rack PR-09 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-10 |  | 2025-10-17 |  | 2025-12-30 |  | 2025-10-17 |  | 2026-01-29 |  | 2025-12-09 | [9 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 650 | Later | S&L | SAU4005-G000-UZT-&CLB-01412 | Pipe Rack PR-09 : Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-02-12 |  |  |  | 2026-01-22 |  | 2025-11-26 |  | 2026-02-12 |  |  |  | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 651 | Later | S&L | SAU4005-G000-UZT-&CTB-01413 | Pipe Rack PR-09 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-12-30 |  |  |  | 2025-12-10 |  | 2025-10-17 |  | 2025-12-30 |  |  |  | 434 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 652 | Later | S&L | SAU4005-G000-UZT-&CED-01414 | Pipe Rack PR-10 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-01-22 |  | 2025-11-27 |  | 2026-02-12 |  | 2025-12-09 |  | 2026-03-13 |  | 2025-12-21 | [9 empty] | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 653 | Later | S&L | SAU4005-G000-UZT-&CED-01415 | Pipe Rack PR-10 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-10 |  | 2025-10-27 |  | 2025-12-30 |  | 2025-11-09 |  | 2026-01-29 |  | 2025-12-11 | [9 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 654 | Later | S&L | SAU4005-G000-UZT-&CLB-01416 | Pipe Rack PR-10 : Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-02-12 |  |  |  | 2026-01-22 |  | 2025-11-27 |  | 2026-02-12 |  |  |  | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 655 | Later | S&L | SAU4005-G000-UZT-&CTB-01417 | Pipe Rack PR-10 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-12-30 |  |  |  | 2025-12-10 |  | 2025-10-27 |  | 2025-12-30 |  |  |  | 434 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 656 | Later | S&L | SAU4005-G000-UZT-&CED-01418 | Pipe Rack PR-11 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-10 |  | 2026-04-23 |  | 2026-03-02 |  | 2026-04-26 |  | 2026-03-31 |  | 2026-05-06 | [9 empty] | 327 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | No | NO
|  | 657 | Later | S&L | SAU4005-G000-UZT-&CED-01419 | Pipe Rack PR-11 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-14 |  | 2026-04-09 |  | 2025-12-04 |  | 2026-04-16 |  | 2026-01-01 |  | 2026-04-28 | [9 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 658 | Later | S&L | SAU4005-G000-UZT-&CLB-01420 | Pipe Rack PR-11 : Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-05-26 |  |  |  | 2026-05-06 |  | 2026-04-23 |  | 2026-05-26 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 659 | Later | S&L | SAU4005-G000-UZT-&CTB-01421 | Pipe Rack PR-11 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-12-04 |  |  |  | 2025-11-14 |  | 2026-04-16 |  | 2025-12-04 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 660 | Later | S&L | SAU4005-G000-UZT-&CED-01422 | Pipe Rack PR-12 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-04-28 |  | 2026-02-22 |  | 2026-05-18 |  | 2026-03-02 |  | 2026-06-15 |  | 0 | [9 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 661 | Later | S&L | SAU4005-G000-UZT-&CED-01423 | Pipe Rack PR-12 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-13 |  | 2026-01-29 |  | 2025-12-03 |  | 2026-02-04 |  | 2025-12-31 |  | 0 | [9 empty] | 641 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 662 | Later | S&L | SAU4005-G000-UZT-&CLB-01424 | Pipe Rack PR-12 : Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-05-18 |  |  |  | 2026-04-28 |  | 2026-02-22 |  | 2026-05-18 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 663 | Later | S&L | SAU4005-G000-UZT-&CTB-01425 | Pipe Rack PR-12 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-01-15 |  |  |  | 2025-12-25 |  | 2026-01-29 |  | 2026-01-15 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 664 | Later | S&L | SAU4005-G000-UZT-&CED-01440 | Pipe Rack PR-13 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-05-19 |  | 2026-04-12 |  | 2026-06-08 |  | 2026-04-19 |  | 2026-07-06 |  | 0 | [9 empty] | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 665 | Later | S&L | SAU4005-G000-UZT-&CED-01441 | Pipe Rack PR-13 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-25 |  | 2026-03-10 |  | 2025-12-15 |  | 2026-03-15 |  | 2026-01-12 |  | 0 | [9 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 666 | Later | S&L | SAU4005-G000-UZT-&CLB-01442 | Pipe Rack PR-13 : Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-06-11 |  |  |  | 2026-05-22 |  | 2026-04-12 |  | 2026-06-11 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 667 | Later | S&L | SAU4005-G000-UZT-&CTB-01443 | Pipe Rack PR-13 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-12-29 |  |  |  | 2025-12-09 |  | 2026-03-10 |  | 2025-12-29 |  |  |  | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 668 | Later | S&L | SAU4005-G000-UZT-&CED-01426 | Cable Rack CR-01 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-18 |  | 2025-11-11 |  | 2026-03-11 |  | 2025-11-20 |  | 2026-04-08 |  | 2025-11-26 | [9 empty] | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 669 | Later | S&L | SAU4005-G000-UZT-&CED-01427 | Cable Rack CR-01 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-01-20 |  | 2025-10-02 |  | 2026-02-10 |  | 2025-09-11 |  | 2026-03-11 |  | 2025-11-24 | [9 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 670 | Later | S&L | SAU4005-G000-UZT-&CLB-01428 | Cable Rack CR-01 : Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-03-11 |  |  |  | 2026-02-18 |  | 2025-11-11 |  | 2026-03-11 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 671 | Later | S&L | SAU4005-G000-UZT-&CTB-01429 | Cable Rack CR-01 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-02-10 |  |  |  | 2026-01-20 |  | 2025-10-02 |  | 2026-02-10 |  |  |  | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 672 | Later | S&L | SAU4005-G000-UZT-&CED-01430 | Cable Rack CR-02 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-18 |  | 2025-10-26 |  | 2026-03-11 |  | 2025-11-04 |  | 2026-04-08 |  | 2025-11-24 | [9 empty] | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C1 | NO |  | Yes | Common
|  | 673 | Later | S&L | SAU4005-G000-UZT-&CED-01431 | Cable Rack CR-02 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-01-20 |  | 2025-10-02 |  | 2026-02-10 |  | 2025-09-11 |  | 2026-03-11 |  | 2025-11-24 | [9 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Common
|  | 674 | Later | S&L | SAU4005-G000-UZT-&CLB-01432 | Cable Rack CR-02 : Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-03-11 |  |  |  | 2026-02-18 |  | 2025-10-26 |  | 2026-03-11 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 675 | Later | S&L | SAU4005-G000-UZT-&CTB-01433 | Cable Rack CR-02 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-02-10 |  |  |  | 2026-01-20 |  | 2025-10-02 |  | 2026-02-10 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 676 | Later | S&L | SAU4005-G000-U__-&CED-01094 | Miscellaneous Sumps and Pits Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-08-14 |  | 2026-03-09 |  | 2026-09-04 |  | 2026-03-29 |  | 2026-11-19 |  | 2026-05-10 | [9 empty] | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C1 | SEC | S1 | NO | Common
|  | 677 | Later | S&L | SAU4005-G000-U__-&CTB-01095 | Miscellaneous Sumps and Pits Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-11-19 |  |  |  | 2026-08-27 |  | 2026-03-09 |  | 2026-11-19 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 681 | Later | S&L | SAU4005-G000-UTS-&CED-01098 | Chemical Storage Building for Water and Effluent Treatment System - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-03-17 |  | 2026-02-12 |  | 2026-04-06 |  | 2026-02-24 |  | 2026-05-04 |  | 2026-05-06 | [9 empty] | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 682 | Later | S&L | SAU4005-G000-UTS-&CLH-01099 | Chemical Storage Building for Water and Effluent Treatment System - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-03-10 |  |  |  | 2026-01-08 |  | 2026-01-19 |  | 2026-03-10 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 683 | Later | S&L | SAU4005-G000-UTS-&CLB-01100 | Chemical Storage Building for Water and Effluent Treatment System - Foundation & Column Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-02 |  |  |  | 2026-03-26 |  | 2026-02-12 |  | 2026-04-02 |  |  |  | 201 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C1 | SEC | S1,S2,S5,S8 | NO
|  | 684 | Later | S&L | SAU4005-G000-UTS-&CTL-01102 | Chemical Storage Building for Water and Effluent Treatment System - Roof Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-22 |  |  |  | 2026-04-15 |  | 2026-02-12 |  | 2026-04-22 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA |  | NO | NO | NO | NO |  | NO
|  | 685 | Later | S&L | SAU4005-G000-UTS-&CTL-01103 | Chemical Storage Building for Water and Effluent Treatment System - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-05-15 |  |  |  | 2026-05-08 |  | 2026-04-24 |  | 2026-05-15 |  |  |  | 450 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 686 | Later | S&L | SAU4005-G000-UGV-&CED-01110 | Sewage Treatment Plant Area - Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-19 |  | 2026-05-20 |  | 2026-03-12 |  | 0 |  | 2026-04-08 |  | 0 | [9 empty] | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 687 | Later | S&L | SAU4005-G000-UGV-&CLB-01111 | Sewage Treatment Plant Area - Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-09 |  |  |  | 2026-04-02 |  | 2026-05-20 |  | 2026-04-09 |  |  |  | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 689 | Later | S&L | SAU4005-G000-UGX-&CLB-01113 | Oil Water Separator (underground tank) Foundation - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-02-25 |  | 2026-03-10 |  | 2026-03-17 |  | 2026-04-15 |  | 2026-04-22 |  | 0 | [5 empty] | 2026-04-22 |  |  |  | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 690 | Later | S&L | SAU4005-G000-UER-&CED-01119 | Fuel Gas Compressor Foundation - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-10-13 |  | 2025-09-05 |  | 2025-11-04 |  | 2025-10-12 |  | 2025-12-02 |  | 2025-11-09 | [9 empty] | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 691 | Later | S&L | SAU4005-G000-UER-&CLB-01120 | Fuel Gas Compressor Foundation - RC details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-10-13 |  | 2025-09-05 |  | 2025-11-02 |  | 2025-10-12 |  | 2025-11-04 |  | 2025-11-09 | [5 empty] | 2025-11-04 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 692 | Later | S&L | SAU4005-G000-UZA-&CED-01122 | Roads - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-08-07 |  | 2025-07-03 |  | 2025-08-29 |  | 2025-07-17 |  | 2025-09-24 |  | 2025-07-31 | [9 empty] | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 693 | Later | S&L | SAU4005-G000-UZA-&CTL-01123 | Roads & Surfacing - Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-09-24 |  |  |  | 2025-08-20 |  | 2025-07-07 |  | 2025-09-24 |  |  |  | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 696 | Later | S&L | SAU4005-G000-UZA-&CED-01126 | Process / Oily Water Drainage - Crossings Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-01-22 |  | 2025-12-04 |  | 2026-02-12 |  | 2025-12-21 |  | 2026-04-22 |  | 2026-03-15 | [5 empty] | 2026-04-22 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 697 | Later | S&L | SAU4005-G000-UGX-&CTL-01127 | Process / Oily Water Drainage - Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-02-12 |  |  |  | 2026-02-05 |  | 2025-12-04 |  | 2026-02-12 |  |  |  | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 699 | Later | S&L | SAU4005-G000-UZJ-&CTL-01129 | Boundary Wall/Fencing - Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-12-04 |  |  |  | 2026-12-01 |  |  |  | 2026-12-04 |  |  |  | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 700 | Later | S&L | SAU4005-G000-UGF-&CLB-01130 | DV Shed - Foundation Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-09-11 |  |  |  | 2026-09-08 |  |  |  | 2026-09-11 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 701 | Later | S&L | SAU4005-G000-UZT-&CTL-01131 | Duct Bank - Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-07-06 |  |  |  | 2026-06-30 |  | 2025-10-09 |  | 2026-07-06 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 702 | Later | S&L | SAU4005-G000-UMB-&CTL-01133 | GT & HRSG area Pavements - Layout & Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-12-18 |  |  |  | 2026-12-10 |  | 2026-02-11 |  | 2026-12-18 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 706 | Later | S&L | SAU4005-G000-U__-&CTL-01389 | Property Line Storm Water Interface | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-10-03 |  |  |  | 2025-09-10 |  | 2025-06-12 |  | 2025-10-03 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 707 | Later | S&L | SAU4005-G000-UZA-&CTB-01391 | Road Cross Section Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-10-03 |  |  |  | 2025-09-10 |  | 2025-07-03 |  | 2025-10-03 |  |  |  | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 708 | Later | S&L | SAU4005-G000-UGV-&CED-01137 | Sanitary System - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-04-24 |  | 2025-12-22 |  | 2026-05-14 |  | 2026-01-04 |  | 2026-06-10 |  | 2026-03-15 | [9 empty] | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 709 | Later | S&L | SAU4005-G000-UGV-&CTB-01138 | Sanitary System - Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-06-10 |  |  |  | 2026-05-11 |  | 2025-12-19 |  | 2026-06-10 |  |  |  | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 710 | Later | S&L | SAU4005-G000-URC-&CED-01139 | ACC Duct Foundation - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-01-07 |  | 2026-01-07 |  | 2026-01-29 |  | 2026-01-14 |  | 2026-02-25 |  | 2026-01-19 | [9 empty] | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 711 | Later | S&L | SAU4005-G000-URC-&CTB-01140 | ACC Duct Foundation - Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-01-21 |  | 2026-01-07 |  | 2026-02-10 |  | 2026-01-14 |  | 2026-02-25 |  | 2026-01-19 | [5 empty] | 2026-02-25 |  |  |  | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 712 | Later | S&L | SAU4005-G000-UGV-&CED-01141 | Lifting Station - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-08-20 |  | 2026-05-14 |  | 2026-09-10 |  | 2026-05-21 |  | 2026-10-07 |  | 0 | [9 empty] | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 713 | Later | S&L | SAU4005-G000-UGV-&CTB-01142 | Lifting Station - Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-12-07 |  |  |  | 2026-12-01 |  | 2026-05-14 |  | 2026-12-07 |  |  |  | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 714 | Later | S&L | SAU4005-G000-UZD-&CTL-01143 | Car Parking Area (Open) - Paving Layout & Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-10-14 |  |  |  | 2026-09-14 |  |  |  | 2026-10-14 |  |  |  | 207 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
| ISSUER CHANGED | 715 | Later | S3 SITE | SAU4005-G000-UZD-&CED-01144 | Car Parking Shed - Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFD | [10 empty] | 2026-09-30 |  |  |  | 2026-06-19 | [7 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
| ISSUER CHANGED | 716 | Later | S3 SITE | SAU4005-G000-UZD-&CTB-01145 | Car Parking Shed - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-09-23 |  |  |  | 2026-05-14 |  |  |  | 2026-09-23 |  |  |  | 207 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
| ISSUER CHANGED | 717 | Later | S3 SITE | SAU4005-G000-UZD-&CLB-01146 | Car Parking Shed - Foundation & Pier- Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-09-30 |  |  |  | 2026-07-03 |  |  |  | 2026-09-30 |  |  |  | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 719 | Later | S&L | SAU4005-G000-UZD-&CTL-01148 | Car Parking Shed - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-10-14 |  |  |  | 2026-09-14 |  |  |  | 2026-10-14 |  |  |  | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
|  | 720 | Later | S&L | SAU4005-G000-UTH-&CED-01149 | Auxiliary boiler - Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-17 |  | 2026-01-07 |  | 2025-12-05 |  | 2026-01-14 |  | 2026-02-16 |  | 2026-02-01 | [9 empty] | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
|  | 721 | Later | S&L | SAU4005-G000-UTH-&CLB-01150 | Auxiliary boiler - Foundation Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-03-31 |  |  |  | 2026-01-08 |  | 2026-01-07 |  | 2026-03-31 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
|  | 722 | Later | S&L | SAU4005-G000-UMB-&CED-01151 | GT Bypass Stack Unit - 11, 12 & 13 Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-09-08 |  | 2025-07-23 |  | 2025-09-26 |  | 2025-08-03 |  | 2025-10-30 |  | 2025-09-11 | [9 empty] | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
|  | 723 | Later | S&L | SAU4005-G000-UMB-&CLB-01152 | GT Bypass Stack Unit - 11, 12 & 13 Foundation Layout & Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-09-18 |  | 2025-07-23 |  | 2025-10-08 |  | 2025-08-05 |  | 2025-10-30 |  | 2025-09-21 | [5 empty] | 2025-10-30 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
|  | 726 | Later | S&L | SAU4005-G000-UBF-&CED-01162 | GT Unit - 11, 12 & 13 Generator Step-Up Transformer Foundation - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-09-22 |  | 2025-12-11 |  | 2025-10-15 |  | 2025-12-21 |  | 2025-11-13 |  | 2026-02-01 | [9 empty] | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Open
|  | 727 | Later | S&L | SAU4005-G000-UBF-&CLB-01163 | GT Unit - 11, 12 & 13 Generator Step-Up Transformer Foundation - Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-10-29 |  | 2025-12-11 |  | 2025-11-18 |  | 2025-12-21 |  | 2025-12-15 |  | 2026-02-01 | [5 empty] | 2025-12-15 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 732 | Later | S&L | SAU4005-G000-UBH-&CED-01168 | ST Transformer Oil Collection Pit - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-08-12 |  | 2025-11-19 |  | 2026-09-02 |  | 2025-11-26 |  | 2026-10-14 |  | 2025-12-09 | [9 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 733 | Later | S&L | SAU4005-G000-UBH-&CTL-01169 | ST Transformer Oil Collection Pit - Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-09-02 |  |  |  | 2026-08-26 |  | 2025-11-19 |  | 2026-09-02 |  |  |  | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 734 | Later | S&L | SAU4005-G000-UBF-&CED-01170 | ST-Generator Step-Up Transformer Foundation - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-18 |  | 2025-12-16 |  | 2025-12-08 |  | 2025-12-23 |  | 2026-01-02 |  | 2026-01-25 | [9 empty] | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Combine
|  | 735 | Later | S&L | SAU4005-G000-UBF-&CLB-01171 | ST-Generator Step-Up Transformer Foundation - Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-11-26 |  | 2025-12-16 |  | 2025-12-16 |  | 2025-12-23 |  | 2026-01-21 |  | 2026-01-25 | [5 empty] | 2026-01-21 |  |  |  | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 738 | Later | S&L | SAU4005-G000-UBF-&CED-01176 | ST- TRANSFORMER AREA - IPBD Supports, paving, rail foundation Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-07-31 |  | 2026-01-10 |  | 2026-08-20 |  | 2026-01-19 |  | 2026-09-18 |  | 2026-02-09 | [9 empty] | 272 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 739 | Later | S&L | SAU4005-G000-UBF-&CLB-01177 | ST- TRANSFORMER AREA - IPBD Supports, paving, rail foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-09-18 |  |  |  | 2026-08-12 |  | 2026-01-10 |  | 2026-09-18 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 740 | Later | S&L | SAU4005-G000-UBA-&CED-01178 | STG and Auxiliary Boiler Electrical Building - Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-05-21 |  | 2026-01-17 |  | 2026-06-10 |  | 2026-01-25 |  | 2026-07-06 |  | 2026-02-24 | [9 empty] | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
|  | 742 | Later | S&L | SAU4005-G000-UBA-&CTB-01180 | STG and Auxiliary Boiler Electrical Building - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-05-05 |  | 2025-12-15 |  | 2026-05-22 |  | 2025-12-29 |  | 2026-06-17 |  | 2026-01-06 | [5 empty] | 2026-06-17 |  |  |  | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 743 | Later | S&L | SAU4005-G000-UBA-&CLB-01182 | STG and Auxiliary Boiler Electrical Building - Foundation and Column Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-07-06 |  |  |  | 2026-06-03 |  | 2026-01-17 |  | 2026-07-06 |  |  |  | 560 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 744 | Later | S&L | SAU4005-G000-UBA-&CTL-01183 | STG and Auxiliary Boiler Electrical Building - Grade Beam Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-07-10 |  |  |  | 2026-06-23 |  | 2026-01-17 |  | 2026-07-10 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 745 | Later | S&L | SAU4005-G000-UBA-&CTL-01184 | STG and Auxiliary Boiler Electrical Building - Roof Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-07-10 |  |  |  | 2026-06-25 |  | 2026-01-17 |  | 2026-07-10 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 746 | Later | S&L | SAU4005-G000-UBA-&CTL-01185 | STG and Auxiliary Boiler Electrical Building - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-07-22 |  |  |  | 2026-07-15 |  | 2026-05-08 |  | 2026-07-22 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 747 | Later | S&L | SAU4005-G000-UBA-&CED-01186 | GT Package MCC / Control room - 11, 12, 13 - Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-25 |  | 2025-08-26 |  | 2026-01-15 |  | 2025-09-08 |  | 2026-04-06 |  | 2025-10-02 | [9 empty] | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 748 | Later | S&L | SAU4005-G000-UBA-&CED-01187 | GT Package MCC / Control room - 11, 12, 13 - Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-03 |  | 2025-09-24 |  | 2026-02-23 |  | 2025-10-05 |  | 2026-04-28 |  | 2025-12-14 | [9 empty] | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 749 | Later | S&L | SAU4005-G000-UBA-&CTB-01188 | GT Package MCC / Control room - 11, 12, 13 - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-11-19 |  | 2025-07-24 |  | 2025-12-08 |  | 2025-08-12 |  | 2026-03-12 |  | 2025-10-09 | [5 empty] | 2026-03-12 |  |  |  | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 751 | Later | S&L | SAU4005-G000-UBA-&CLB-01190 | GT Package MCC / Control room - 11, 12, 13 - Foundation and Column Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-02-01 |  |  |  | 2026-01-01 |  | 2025-08-26 |  | 2026-02-01 |  |  |  | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 752 | Later | S&L | SAU4005-G000-UBA-&CTL-01191 | GT Package MCC / Control room - 11, 12, 13 - Grade Beam Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-07 |  |  |  | 2026-02-03 |  | 2025-09-24 |  | 2026-04-07 |  |  |  | 547 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 753 | Later | S&L | SAU4005-G000-UBA-&CTL-01192 | GT Package MCC / Control room - 11, 12, 13 - Roof Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-07 |  |  |  | 2026-02-03 |  | 2025-09-24 |  | 2026-04-07 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 754 | Later | S&L | SAU4005-G000-UBA-&CTL-01193 | GT Package MCC / Control room - 11, 12, 13 - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-05-12 |  |  |  | 2026-05-05 |  | 2026-01-21 |  | 2026-05-12 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 755 | Later | S&L | SAU4005-G000-UBA-&CTL-01201 | ACC Electrical Switchgear Building - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-08-10 |  |  |  | 2026-08-04 |  | 2026-05-17 |  | 2026-08-10 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 756 | Later | S&L | SAU4005-G000-UBA-&CED-01202 | Unit MV/LV Electrical Switchgear building-11, 12, 13 - Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-20 |  | 2025-10-28 |  | 2026-03-13 |  | 2025-11-04 |  | 2026-06-26 |  | 2025-12-01 | [9 empty] | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 757 | Later | S&L | SAU4005-G000-UBA-&CED-01203 | Unit MV/LV Electrical Switchgear building-11, 12, 13 - Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-05-28 |  | 2025-10-19 |  | 2026-06-17 |  | 2025-11-04 |  | 2026-07-13 |  | 2025-12-14 | [9 empty] | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | NO | NO | NO | NO | NO |  | NO
|  | 758 | Later | S&L | SAU4005-G000-UBA-&CTB-01204 | Unit MV/LV Electrical Switchgear building-11, 12, 13 - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-11-12 |  | 2025-08-12 |  | 2025-11-28 |  | 2025-08-26 |  | 2026-06-19 |  | 2025-10-17 | [5 empty] | 2026-06-19 |  |  |  | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 759 | Later | S&L | SAU4005-G000-UBA-&CTB-01205 | Unit MV/LV Electrical Switchgear building-11, 12, 13 - False ceiling Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-06-24 |  |  |  | 2026-04-24 |  | 2025-08-12 |  | 2026-06-24 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 760 | Later | S&L | SAU4005-G000-UBA-&CLB-01206 | Unit MV/LV Electrical Switchgear building-11, 12, 13 - Foundation and Column Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-05 |  |  |  | 2026-03-05 |  | 2025-10-28 |  | 2026-04-05 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 761 | Later | S&L | SAU4005-G000-UBA-&CTL-01207 | Unit MV/LV Electrical Switchgear building-11, 12, 13 - Grade Beam Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-07-07 |  |  |  | 2026-03-24 |  | 2025-10-28 |  | 2026-07-07 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 762 | Later | S&L | SAU4005-G000-UBA-&CTL-01208 | Unit MV/LV Electrical Switchgear building-11, 12, 13 - Roof Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-07-07 |  |  |  | 2026-04-10 |  | 2025-10-28 |  | 2026-07-07 |  |  |  | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 763 | Later | S&L | SAU4005-G000-UBA-&CTL-01209 | Unit MV/LV Electrical Switchgear building-11, 12, 13 - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-07-13 |  |  |  | 2026-04-29 |  | 2025-11-15 |  | 2026-07-13 |  |  |  | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 765 | Later | S&L | SAU4005-G000-UGA-&CLB-01213 | Pre-Treatment Facilities (DAF - Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-12-30 |  |  |  | 2025-12-24 |  | 2025-12-20 |  | 2025-12-30 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 766 | Later | S&L | SAU4005-G000-UYP-&CED-01214 | Fire Station Building - Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-01-28 |  | 2026-03-09 |  | 2026-02-17 |  | 2026-03-15 |  | 2026-03-16 |  | 2026-04-12 | [9 empty] | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 767 | Later | S&L | SAU4005-G000-UYP-&CTB-01215 | Fire Station Building - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-08-28 |  | 2025-05-14 |  | 2025-09-18 |  | 2025-05-27 |  | 2026-02-12 |  | 0 | [5 empty] | 2026-02-12 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 768 | Later | S&L | SAU4005-G000-UYP-&CTB-01216 | Fire Station Building - False ceiling Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-02-17 |  |  |  | 2026-01-06 |  | 2025-05-14 |  | 2026-02-17 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 769 | Later | S&L | SAU4005-G000-UYP-&CLB-01217 | Fire Station Building - Foundation & Column - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-03-25 |  |  |  | 2026-03-17 |  | 2026-03-09 |  | 2026-03-25 |  |  |  | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 770 | Later | S&L | SAU4005-G000-UYP-&CTL-01218 | Fire Station Building - Grade beams Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-05-18 |  |  |  | 2026-04-30 |  | 2026-03-09 |  | 2026-05-18 |  |  |  | 547 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Open
|  | 771 | Later | S&L | SAU4005-G000-UYP-&CTL-01219 | Fire Station Building - Roof Slabs Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-06-23 |  |  |  | 2026-06-16 |  | 2026-03-09 |  | 2026-06-23 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 772 | Later | S&L | SAU4005-G000-UYP-&CTL-01220 | Fire Station Building - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-06-29 |  |  |  | 2026-04-13 |  | 2026-03-27 |  | 2026-06-29 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 773 | Later | S&L | SAU4005-G000-UGA-&CED-01221 | Raw water Buffer Storage Tank with Unloading Area - Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-26 |  | 2025-10-09 |  | 2025-12-16 |  | 2025-10-15 |  | 2026-01-09 |  | 0 | [9 empty] | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 774 | Later | S&L | SAU4005-G000-UGA-&CTB-01222 | Raw water Buffer Storage Tank with Unloading Area - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-01-09 |  |  |  | 2025-12-08 |  | 2025-10-09 |  | 2026-01-09 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 775 | Later | S&L | SAU4005-G000-UGD-&CED-01223 | DM and Service Water Pump Shed - Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-14 |  | 2025-11-14 |  | 2025-12-04 |  | 2025-11-26 |  | 2026-02-16 |  | 2025-12-03 | [9 empty] | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 776 | Later | S&L | SAU4005-G000-UGD-&CTB-01224 | DM and Service Water Pump Shed - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-10-10 |  | 2025-10-04 |  | 2025-10-28 |  | 2025-10-14 |  | 2026-02-09 |  | 2026-02-24 | [5 empty] | 2026-02-09 |  |  |  | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 777 | Later | S&L | SAU4005-G000-UGD-&CLB-01225 | DM and Service Water Pump Shed - Foundation & Pier Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-02-16 |  |  |  | 2025-12-26 |  | 2026-01-06 |  | 2026-02-16 |  |  |  | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 778 | Later | S&L | SAU4005-G000-UGD-&CTB-01226 | DM and Service Water Pump Shed - Superstructure Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-02-18 |  |  |  | 2026-01-22 |  | 2025-11-14 |  | 2026-02-18 |  |  |  | 547 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 779 | Later | S&L | SAU4005-G000-UGD-&CTL-01227 | DM and Service Water Pump Shed - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-29 |  |  |  | 2026-04-23 |  | 2026-02-10 |  | 2026-04-29 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
| DCC CHANGED | 781 | Later | S&L | SAU4005-G000-UGD-&CED-01228 | Sludge Handling Facilities – Sub structure Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-12-31 |  |  |  | 2025-12-24 |  | 2025-12-07 |  | 2025-12-31 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 783 | Later | S&L | SAU4005-G000-UBN-&CED-01240 | BSEDG Foundation - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-10-06 |  | 2025-09-09 |  | 2025-10-28 |  | 2025-09-26 |  | 2025-11-24 |  | 2026-03-15 | [9 empty] | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 784 | Later | S&L | SAU4005-G000-UBN-&CLB-01243 | BSEDG Foundation - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-11-24 |  |  |  | 2025-10-16 |  | 2025-09-09 |  | 2025-11-24 |  |  |  | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 785 | Later | S&L | SAU4005-G000-UBN-&CTL-01247 | BSEDG Area - Grade slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-11-25 |  |  |  | 2025-10-17 |  | 2025-09-26 |  | 2025-11-25 |  |  |  | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 786 | Later | S&L | SAU4005-G000-UBN-&CLB-01249 | BSEDG Area Miscellaneous Equipment foundations - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-01-20 |  |  |  | 2025-12-29 |  | 2026-01-31 |  | 2026-01-20 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 787 | Later | S&L | SAU4005-G000-UBA-&CED-01252 | BOP Electrical Switchgear Building - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-11 |  | 2026-01-08 |  | 2026-03-03 |  | 2026-01-18 |  | 2026-03-27 |  | 2026-03-03 | [9 empty] | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 788 | Later | S&L | SAU4005-G000-UBA-&CTB-01253 | BOP Electrical Switchgear Building - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-01-09 |  | 2025-11-07 |  | 2026-02-02 |  | 2025-11-24 |  | 2026-02-27 |  | 2026-01-21 | [5 empty] | 2026-02-27 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 789 | Later | S&L | SAU4005-G000-UBA-&CTB-01254 | BOP Electrical Switchgear Building - Toilet and False ceiling Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-05-15 |  |  |  | 2026-05-13 |  | 2025-11-07 |  | 2026-05-15 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 790 | Later | S&L | SAU4005-G000-UBA-&CLB-01255 | BOP Electrical Switchgear Building - Foundation & Column- Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-02-23 |  | 2026-01-08 |  | 2026-03-15 |  | 2026-01-18 |  | 2026-04-20 |  | 2026-01-25 | [5 empty] | 2026-04-20 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 791 | Later | S&L | SAU4005-G000-UBA-&CTL-01256 | BOP Electrical Switchgear Building - Grade Beam Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-03-31 |  |  |  | 2026-03-25 |  | 2026-01-08 |  | 2026-03-31 |  |  |  | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 792 | Later | S&L | SAU4005-G000-UBA-&CTL-01257 | BOP Electrical Switchgear Building - Roof Slabs Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-05-05 |  |  |  | 2026-04-29 |  | 2026-01-08 |  | 2026-05-05 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 793 | Later | S&L | SAU4005-G000-UBA-&CTL-01258 | BOP Electrical Switchgear Building - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-05-21 |  |  |  | 2026-05-14 |  | 2026-03-22 |  | 2026-05-21 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 794 | Later | S&L | SAU4005-G000-UEL-&CED-01259 | Fuel Oil pump Shed - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-19 |  | 2025-10-14 |  | 2026-01-08 |  | 2025-10-21 |  | 2026-02-04 |  | 2025-11-26 | [9 empty] | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Open
|  | 795 | Later | S&L | SAU4005-G000-UEL-&CTB-01260 | Fuel Oil pump Shed - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-10-27 |  |  |  | 2025-09-04 |  | 2025-10-11 |  | 2025-10-27 |  |  |  | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 796 | Later | S&L | SAU4005-G000-UEL-&CLB-01261 | Fuel Oil Pump Shed - Foundation & Pier Layout and RC details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-02-06 |  |  |  | 2025-12-19 |  | 2025-11-11 |  | 2026-02-06 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 797 | Later | S&L | SAU4005-G000-UEL-&CTB-01262 | Fuel Oil Pump Shed - Superstructure details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-02-12 |  |  |  | 2025-12-15 |  | 2025-10-14 |  | 2026-02-12 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 798 | Later | S&L | SAU4005-G000-UEL-&CTL-01263 | Fuel Oil Pump Shed - Grade Slab Layout and RC details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-29 |  |  |  | 2026-04-22 |  | 2026-01-09 |  | 2026-04-29 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 799 | Later | S&L | SAU4005-G000-UEN-&CTL-01264 | Fuel Gas Conditioning Area - Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-10-13 |  |  |  | 2025-10-08 |  | 2025-10-07 |  | 2025-10-13 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 800 | Later | S&L | SAU4005-G000-UBA-&CTL-01270 | Electrical Container for Fuel Oil Area - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-17 |  |  |  | 2026-04-13 |  | 2026-05-09 |  | 2026-04-17 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 802 | Later | S&L | SAU4005-G000-UTG-&CED-01272 | Hydrogen Generation Plant including Electrical Room - Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-25 |  | 2026-02-13 |  | 2026-03-18 |  | 2026-02-24 |  | 2026-04-13 |  | 2026-04-12 | [9 empty] | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 803 | Later | S&L | SAU4005-G000-UTG-&CTB-01273 | Hydrogen Generation Plant including Electrical Room - Architectural Drawings | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-01-30 |  | 2026-02-05 |  | 2026-02-19 |  | 2026-02-18 |  | 2026-03-17 |  | 0 | [5 empty] | 2026-03-17 |  |  |  | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 804 | Later | S&L | SAU4005-G000-UTG-&CLB-01274 | Hydrogen Generation Plant including Electrical Room - Foundation & Pier Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-02-25 |  | 2026-02-13 |  | 2026-03-17 |  | 2026-02-24 |  | 2026-04-20 |  | 0 | [5 empty] | 2026-04-20 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 805 | Later | S&L | SAU4005-G000-UTG-&CTB-01275 | Hydrogen Generation Plant including Electrical Room - Base Plate and Framing Plan, Elevations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-05-04 |  |  |  | 2026-04-29 |  | 2025-11-06 |  | 2026-05-04 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 808 | Later | S&L | SAU4005-G000-UTG-&CTL-01278 | Hydrogen Generation Plant including Electrical Room - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-05-28 |  |  |  | 2026-03-31 |  | 2026-05-16 |  | 2026-05-28 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 809 | Later | S&L | SAU4005-G000-UBA-&CED-01279 | Electrical Switchgear Building for Fuel Gas - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-03 |  | 2026-01-23 |  | 2026-02-23 |  | 2026-02-04 |  | 2026-04-17 |  | 2026-04-13 | [9 empty] | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 810 | Later | S&L | SAU4005-G000-UBA-&CTB-01280 | Electrical Switchgear Building for Fuel Gas Area - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-03-25 |  |  |  | 2026-02-06 |  | 2025-12-19 |  | 2026-03-25 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 811 | Later | S&L | SAU4005-G000-UBA-&CLB-01282 | Electrical Switchgear Building for Fuel Gas Area - Foundation & Column Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-02-06 |  |  |  | 2026-02-02 |  | 2026-01-23 |  | 2026-02-06 |  |  |  | 415 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 812 | Later | S&L | SAU4005-G000-UBA-&CTL-01283 | Electrical Switchgear Building for Fuel Gas Area - Grade Beam Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-02-24 |  |  |  | 2026-02-20 |  | 2026-01-23 |  | 2026-02-24 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 813 | Later | S&L | SAU4005-G000-UBA-&CTL-01284 | Electrical Switchgear Building for Fuel Gas Area - Roof Slabs Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-02-24 |  |  |  | 2026-02-20 |  | 2026-01-23 |  | 2026-02-24 |  |  |  | 447 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 814 | Later | S&L | SAU4005-G000-UBA-&CTL-01285 | Electrical Switchgear Building for Fuel Gas Area - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-17 |  |  |  | 2026-04-13 |  | 2026-02-27 |  | 2026-04-17 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Combine
|  | 816 | Later | S&L | SAU4005-G000-UEJ-&CED-01327 | Fuel Oil Storage Tank Foundation - Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-10-15 |  | 2025-07-31 |  | 2025-11-06 |  | 2025-08-13 |  | 2025-12-11 |  | 0 | [9 empty] | 136 | [13 empty] | WF Transmittal DI-EPC-ACWA | NO | NO | NO | NO | NO |  | NO
|  | 817 | Later | S&L | SAU4005-G000-UEJ-&CLB-01328 | Fuel Oil Storage Tank Foundation - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-10-30 |  | 2025-07-31 |  | 2025-11-19 |  | 2025-08-13 |  | 2025-12-11 |  | 0 | [5 empty] | 2025-12-11 |  |  |  | 207 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
|  | 818 | Later | S&L | SAU4005-G000-UEJ-&CTL-01329 | Fuel Oil Storage Tank With Dyke Area - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-02-11 |  |  |  | 2026-02-06 |  | 2025-08-12 |  | 2026-02-11 |  |  |  | 136 | [13 empty] | WF Transmittal DI-EPC-ACWA | NO | NO | NO | NO | NO |  | NO
|  | 819 | Later | S&L | SAU4005-G000-UEJ-&CTL-01330 | Fuel Oil Unloading Area - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-21 |  |  |  | 2026-04-15 |  | 2026-01-13 |  | 2026-04-21 |  |  |  | 207 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
| ISSUER CHANGED | 820 | Later | SAIS | SAU4005-G000-UYF-&CED-01331 | Search Facility & Visitors Center - Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-07-01 |  | 2026-04-19 |  | 2026-07-21 |  | 2026-04-26 |  | 2026-08-12 |  | 2026-05-20 | [9 empty] | 136 | [13 empty] | WF Transmittal DI-EPC-ACWA | NO | NO | NO | NO | NO |  | NO
|  | 821 | Later | S&L | SAU4005-G000-UYF-&CTB-01332 | Search Facility & Visitors Center - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-02 |  |  |  | 2025-10-03 |  | 2026-02-25 |  | 2026-04-02 |  |  |  | 389 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
|  | 822 | Later | S&L | SAU4005-G000-UYF-&CTB-01333 | Search Facility & Visitors Center - Toilet and False ceiling Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-07-23 |  |  |  | 2026-07-17 |  | 2026-01-23 |  | 2026-07-23 |  |  |  | 243 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
| ISSUER CHANGED | 823 | Later | SAIS | SAU4005-G000-UYF-&CLB-01334 | Search Facility & Visitors Center - Foundation & Column Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-08-19 |  |  |  | 2026-07-01 |  | 2026-04-19 |  | 2026-08-19 |  |  |  | 518 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Open
|  | 824 | Later | S&L | SAU4005-G000-UYF-&CTL-01335 | Search Facility & Visitors Center - Grade Beam Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-08-26 |  |  |  | 2026-08-04 |  | 2026-04-19 |  | 2026-08-26 |  |  |  | 233 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Common
|  | 825 | Later | S&L | SAU4005-G000-UYF-&CTL-01336 | Search Facility & Visitors Center - Roof Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-09-18 |  |  |  | 2026-09-10 |  | 2026-04-19 |  | 2026-09-18 |  |  |  | 233 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Common
|  | 826 | Later | S&L | SAU4005-G000-UYF-&CTL-01337 | Search Facility & Visitors Center - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-10-09 |  |  |  | 2026-10-02 |  | 2026-05-22 |  | 2026-10-09 |  |  |  | 233 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Common
|  | 828 | Later | S&L | SAU4005-G000-UYE-&CTB-01339 | Main Gate House including Sunshade - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-02-17 |  |  |  | 2025-08-25 |  | 2026-02-11 |  | 2026-02-17 |  |  |  | 233 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO |  |  |  |  | Common
| ISSUER CHANGED | 831 | Later | SAIS | SAU4005-G000-UYE-&CED-01342 | Main Gate House Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-07-06 |  | 2026-04-01 |  | 2026-07-24 |  | 2026-04-12 |  | 2026-09-18 |  | 2026-04-26 | [9 empty] | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
| ISSUER CHANGED | 832 | Later | SAIS | SAU4005-G000-UYE-&CLB-01343 | Main Gate House - Foundation and Column Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-09-18 |  |  |  | 2026-07-16 |  | 2026-04-01 |  | 2026-09-18 |  |  |  | 418 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
|  | 833 | Later | S&L | SAU4005-G000-UYE-&CTL-01344 | Main Gate House - Roof Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-09-23 |  |  |  | 2026-08-19 |  | 2026-04-01 |  | 2026-09-23 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
|  | 836 | Later | S&L | SAU4005-G000-UGN-&CED-01352 | Sludge Thickener - Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-09-02 |  | 2025-12-08 |  | 2026-09-23 |  | 2025-12-23 |  | 2026-10-22 |  | 2026-01-08 | [9 empty] | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
|  | 837 | Later | S&L | SAU4005-G000-UGN-&CTB-01353 | Sludge Thickener- Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-10-22 |  |  |  | 2026-09-14 |  | 2025-12-08 |  | 2026-10-22 |  |  |  | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
|  | 838 | Later | S&L | SAU4005-G000-UGX-&CED-01354 | Ammonia Storage area - Design Calculations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-28 |  | 2025-10-01 |  | 2025-12-18 |  | 2025-10-16 |  | 2026-04-29 |  | 2025-11-12 | [9 empty] | 275 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
|  | 839 | Later | S&L | SAU4005-G000-UGX-&CTL-01355 | Ammonia Storage area - Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-29 |  |  |  | 2025-12-11 |  | 2025-10-01 |  | 2026-04-29 |  |  |  | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
|  | 846 | Later | S&L | SAU4005-G000-UM_-&CED-01451 | GTG Intake Structure Foundation Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-06 |  | 2025-09-23 |  | 2025-11-26 |  | 2025-10-02 |  | 2026-05-01 |  | 2025-11-17 | [9 empty] | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | C1 | NO |  | NO | Common
|  | 847 | Later | S&L | SAU4005-G000-UM_-&CTB-01452 | GTG Intake Structure Foundation Layout & RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-01-01 |  | 2025-09-23 |  | 2026-01-21 |  | 2025-10-02 |  | 2026-02-26 |  | 2025-11-17 | [5 empty] | 2026-02-26 |  |  |  | 350 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 848 | Later | S&L | SAU4005-G000-UB_-&CTB-01455 | EHV Cable Trench RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-12-26 |  |  |  | 2025-12-08 |  | 2026-03-05 |  | 2025-12-26 |  |  |  | 246 | [13 empty] | WF Transmittal DI-EPC-ACWA |  | YES | NO | NO | NO |  | NO
| ISSUER CHANGED | 849 | Later | SAIS | SAU4005-G000-UYF-&CTL-01457 | Security and Control center - Wet area details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-09-01 |  |  |  | 2026-08-11 |  | 2026-03-18 |  | 2026-09-01 |  |  |  | 246 | [13 empty] | WF Transmittal DI-EPC-ACWA |  | NO | NO | NO | NO |  | NO
| ISSUER CHANGED | 850 | Later | SAIS | SAU4005-G000-UYF-&CTL-01458 | Search facility & Visitor's centre - Wet area details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-11-27 |  |  |  | 2026-11-05 |  | 2026-03-27 |  | 2026-11-27 |  |  |  | 615 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | SEC | S1,S2 | NO | Common
|  | 851 | Later | S&L | SAU4005-G000-UYC-&CTL-01459 | Administration & Social Building - Wet area details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-03-13 |  |  |  | 2026-02-20 |  | 2025-11-22 |  | 2026-03-13 |  |  |  | 463 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO | NO |  | NO | Common
|  | 852 | Later | S&L | SAU4005-G000-UYP-&CTL-01460 | Fire Brigade Building - Wet area details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-07-08 |  |  |  | 2026-06-18 |  | 2025-07-15 |  | 2026-07-08 |  |  |  | 282 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | NO | SEC | S1,S2,S6 | NO | Common
|  | 853 | Later | S&L | SAU4005-G000-UST-&CTL-01461 | Workshop and Warehouse Building - Wet area details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-02-18 |  |  |  | 2026-01-29 |  | 2025-08-31 |  | 2026-02-18 |  |  |  | 460 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Common
|  | 854 | Later | S&L | SAU4005-G000-UCA-&CTL-01462 | Main Electrical & Control Building - Wet area details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-02-12 |  |  |  | 2026-01-22 |  | 2025-11-18 |  | 2026-02-12 |  |  |  | 1500 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | YES | NO | NO |  | NO | Common
|  | 856 | Later | S&L | SAU4005-G000-UBA-&CED-01319 | MCC Room for Water and Effluent treatment building - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-11 |  | 2025-11-26 |  | 2025-12-31 |  | 2025-12-07 |  | 2026-05-01 |  | 2026-01-08 | [9 empty] | 1500 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
|  | 857 | Later | S&L | SAU4005-G000-UBA-&CTB-01320 | MCC Room for Water and Effluent treatment building - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-12-18 |  | 2025-11-01 |  | 2026-01-07 |  | 2026-01-07 |  | 2026-02-06 |  | 2026-01-18 | [5 empty] | 2026-02-06 |  |  |  | 1500 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO | NO | NO |  | NO | Common
|  | 859 | Later | S&L | SAU4005-G000-UBA-&CLB-01321 | MCC Room for Water and Effluent treatment building - Foundation and Column Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-12-29 |  | 2025-11-26 |  | 2026-02-04 |  | 2025-12-07 |  | 2026-03-12 |  | 2025-12-23 | [5 empty] | 2026-03-12 |  |  |  | 1500 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
|  | 860 | Later | S&L | SAU4005-G000-UBA-&CTL-01322 | MCC Room for Water and Effluent treatment building - Grade Beam Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-03-24 |  |  |  | 2026-03-02 |  | 2025-11-26 |  | 2026-03-24 |  |  |  | 1800 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
|  | 861 | Later | S&L | SAU4005-G000-UBA-&CTL-01323 | MCC Room for Water and Effluent treatment building - Roof Slabs Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-09 |  |  |  | 2026-03-20 |  | 2025-11-26 |  | 2026-04-09 |  |  |  | 1900 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
|  | 862 | Later | S&L | SAU4005-G000-UBA-&CTL-01324 | MCC Room for Water and Effluent treatment building - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-03-26 |  |  |  | 2026-03-06 |  | 2026-03-18 |  | 2026-03-26 |  |  |  | 1600 | [13 empty] | WF Transmittal DI-EPC-ACWA |  |  | NO
|  | 867 | Later | S&L | SAU4005-G000-GM_-&CED-01481 | Outside Plant Peripherial Drain Design calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-07-30 |  |  |  | 2026-08-19 |  |  |  | 2026-09-18 | [25 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | YES
|  | 868 | Later | S&L | SAU4005-G000-GM_-&CLB-01482 | Outside Plant Peripherial Drain - Layout and details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-10-16 |  |  |  | 2026-09-28 |  |  |  | 2026-10-16 | [17 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | YES
|  | 869 | Later | S&L | SAU4005-G000-UYX-&CTL-01483 | Sound Barrier Fence Wall - Layout and RC details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-08-13 |  |  |  | 2026-09-02 |  |  |  | 2026-10-08 | [7 empty] | 2026-10-08 | [17 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | YES
|  | 870 | Later | S&L | SAU4005-G000-___-&CEC-01385 | Technical Specification for Topography Survey | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-03-07 |  | 2025-01-27 |  | 2025-03-28 |  | 2025-02-19 |  | 2025-04-04 |  | 2025-05-19 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | YES
|  | 871 | Later | S&L | SAU4005-G000-___-&CEC-01386 | Technical Specification for Geotechnical Investigations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-02-10 |  | 2025-01-27 |  | 2025-03-03 |  | 2025-03-06 |  | 2025-03-10 |  | 2025-07-09 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | YES
|  | 872 | Later | S&L | SAU4005-G000-___-&CEC-01387 | Technical Specification for General Civil Works | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-06-23 |  | 2025-03-28 |  | 2025-07-14 |  | 2025-04-30 |  | 2025-07-21 |  | 2025-05-09 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | YES
|  | 873 | Later | S&L | SAU4005-G000-___-&CEC-01390 | Technical Specification for Structural Steel | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-07-29 |  | 2025-06-03 |  | 2025-08-19 |  | 2025-06-17 |  | 2025-08-26 |  | 2025-07-11 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | YES
|  | 874 | Later | S&L | SAU4005-G000-___-&CEC-01393 | Technical Specification for Architectural Works | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-08-28 |  | 2025-07-31 |  | 2025-09-17 |  | 2025-08-15 |  | 2025-09-24 |  | 2025-09-07 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | YES
|  | 875 | Later | S&L | SAU4005-G000-___-&EDD-00732 | Harmonic Studies | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFI | IFD | [10 empty] | 2025-10-28 |  |  |  | 2025-09-02 |  | 2026-02-06 | [19 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | YES
|  | 876 | Later | S&L | SAU4005-G000-___-&EDD-00690 | Arc Flash Study | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-10-10 |  | 2025-10-04 |  | 2025-11-03 |  | 2025-10-23 |  | 2025-11-28 |  | 0 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | YES
|  | 878 | Later | S&L | SAU4005-G000-___-&CDD-01388 | Flooding Protection Study | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | No | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-05-05 |  | 2025-02-24 |  | 2025-05-23 |  | 2026-03-26 |  | 2026-05-22 |  | 0 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | YES
|  | 879 | Later | S&L | SAU4005-G000-___-&MDD-00342 | Near Field Noise Study Report | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-10-09 |  | 2025-12-16 |  | 2025-10-31 |  | 2026-01-08 |  | 2026-01-08 |  | 0 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | YES
|  | 880 | Later | S&L | SAU4005-G000-___-&EDD-00712 | Insulation Coordination Study | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-10-23 |  | 2026-01-02 |  | 2025-11-12 |  | 0 |  | 2025-12-10 |  | 0 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | YES
|  | 881 | Later | S&L | SAU4005-G000-___-&MDC-00458 | HAZID Study Report | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | Common |  | IFA | IFD |  |  | 2025-11-18 |  | 2025-09-15 |  | 2025-12-09 |  | 2025-10-02 |  | 2026-01-13 |  | 2026-01-04 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | YES
|  | 882 | Later | S&L | SAU4005-G000-___-&MDD-00343 | HAZOP Study Report | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | Common |  | IFA | IFD |  |  | 2026-04-19 |  | 2026-05-20 |  | 2026-05-09 |  | 0 |  | 2026-06-14 |  | 0 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | YES
|  | 883 | Later | S&L | SAU4005-G000-___-&MDC-00459 | SIL Study Report | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | PROCESS | Common |  | IFA | IFD |  |  | 2026-05-18 |  | 2026-05-18 |  | 2026-06-08 |  | 0 |  | 2026-07-13 |  | 0 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | YES
|  | 884 | Later | S&L | SAU4005-G000-___-&MDD-00466 | RAM Study | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFD |  |  | 2026-03-26 |  |  |  | 2026-04-15 |  |  |  | 2026-05-13 | [25 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | YES
|  | 885 | Later | S&L | SAU4005-G000-UZA-&CED-01492 | Access road - Design calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-04-02 |  | 2026-03-28 |  | 2026-04-22 |  | 2026-04-12 |  | 2026-05-20 |  | 2026-04-26 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | YES | YES
|  | 886 | Later | S&L | SAU4005-G000-UZA-&CTL-01493 | Access Road - Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-04-13 |  | 2026-03-28 |  | 2026-05-01 |  | 2026-04-12 |  | 2026-05-29 |  | 0 | [5 empty] | 2026-05-29 |  |  |  | 200 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO |  |  | NO | open
|  | 888 | Later | S&L | SAU4005-G000-UM_-&CED-01495 | GTG Intake Platform Superstructure - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-02-09 |  | 2025-09-07 |  | 2026-02-27 |  | 2025-09-21 |  | 2026-03-30 |  | 2025-11-20 | [5 empty] | 2026-03-30 |  |  |  | 200 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO |  |  | NO | open
|  | 889 | Later | S&L | SAU4005-G000-UM_-&CLH-01496 | GTG Intake Platform - Framing and Elevations | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-06-29 |  |  |  | 2026-05-12 |  | 2025-09-07 |  | 2026-06-29 |  |  |  | 400 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO |  |  | NO | open
|  | 890 | Later | S&L | SAU4005-G000-UHA-&CTL-01501 | HRSG MCC Container_Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-06-10 |  |  |  | 2026-04-15 |  | 2026-04-07 |  | 2026-06-10 |  |  |  | 485 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO |  |  | NO | open
|  | 913 | Later | S&L | SAU4005-G000-URX-&ELH-00864 | Equipment Layout for Fin Fan Cooler Electrical Switchgear Building | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2025-09-28 |  | 2025-08-12 |  | 2025-10-26 |  | 2025-08-27 |  | 2025-11-23 |  | 2025-09-11 | [5 empty] | 2025-11-23 |  |  |  | 485 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO |  |  | NO | open
|  | 914 | Later | S&L | SAU4005-G000-UYP-&ELH-00865 | Cable Raceway Layout for Fire Station Building | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2025-12-19 |  |  |  | 2025-10-01 |  | 2025-08-17 |  | 2025-12-19 |  |  |  | 485 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO |  |  | NO | open
|  | 915 | Later | S&L | SAU4005-G000-EG_-&EEC-00866 | Technical Specification for Heaters | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFP |  |  | 2025-10-22 |  | 2025-09-07 |  | 2025-11-19 |  | 2025-09-24 |  | 2025-12-17 |  | 2025-10-22 | [9 empty] | 485 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO |  |  | NO | open
|  | 916 | Later | S&L | SAU4005-G000-UZT-&CED-01503 | Pipe Rack PR-16 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-01-15 |  | 2025-12-26 |  | 2026-02-12 |  | 2026-01-07 |  | 2026-03-12 |  | 2026-01-21 | [9 empty] | 485 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO |  |  | NO | open
|  | 917 | Later | S&L | SAU4005-G000-UZT-&CED-01504 | Pipe Rack PR-16 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-01-15 |  | 2025-11-18 |  | 2026-02-12 |  | 2025-11-23 |  | 2026-03-12 |  | 2025-12-02 | [9 empty] | 485 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO |  |  | NO | open
|  | 918 | Later | S&L | SAU4005-G000-UZT-&CLB-01505 | Pipe Rack PR-16 : Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-12 |  |  |  | 2026-02-15 |  | 2025-12-26 |  | 2026-04-12 |  |  |  | 200 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO |  |  | NO | open
|  | 919 | Later | S&L | SAU4005-G000-UZT-&CTB-01506 | Pipe Rack PR-16 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-03-12 |  |  |  | 2026-01-15 |  | 2025-11-18 |  | 2026-03-12 |  |  |  | 485 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO |  |  | NO | open
|  | 920 | Later | S&L | SAU4005-G000-UZT-&CED-01507 | Pipe Rack PR-17 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-03-20 |  | 2026-02-18 |  | 2026-04-17 |  | 2026-02-24 |  | 2026-05-15 |  | 2026-03-03 | [9 empty] | 485 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO |  |  | NO | open
|  | 921 | Later | S&L | SAU4005-G000-UZT-&CED-01508 | Pipe Rack PR-17 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-20 |  | 2026-01-15 |  | 2026-03-20 |  | 2026-01-18 |  | 2026-04-17 |  | 2026-02-04 | [9 empty] | 485 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO |  |  | NO | open
|  | 922 | Later | S&L | SAU4005-G000-UZT-&CLB-01509 | Pipe Rack PR-17 : Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-05-15 |  |  |  | 2026-03-20 |  | 2026-02-18 |  | 2026-05-15 |  |  |  | 485 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO |  |  | NO | open
|  | 923 | Later | S&L | SAU4005-G000-UZT-&CTB-01510 | Pipe Rack PR-17 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-02-14 |  |  |  | 2025-12-20 |  | 2026-01-15 |  | 2026-02-14 |  |  |  | 200 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO |  |  | NO | open
|  | 924 | Later | S&L | SAU4005-G000-UZT-&CED-01511 | Pipe Rack PR-18 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-03-20 |  | 2025-12-30 |  | 2026-04-17 |  | 2026-01-11 |  | 2026-05-15 |  | 2026-01-18 | [9 empty] | 485 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO |  |  | NO | open
|  | 925 | Later | S&L | SAU4005-G000-UZT-&CED-01512 | Pipe Rack PR-18 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-20 |  | 2025-12-12 |  | 2026-03-20 |  | 2025-12-21 |  | 2026-04-17 |  | 2025-12-28 | [9 empty] | 485 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO |  |  | NO | open
|  | 926 | Later | S&L | SAU4005-G000-UZT-&CLB-01513 | Pipe Rack PR-18 : Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-05-15 |  |  |  | 2026-03-20 |  | 2025-12-30 |  | 2026-05-15 |  |  |  | 485 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO |  |  | NO | open
|  | 927 | Later | S&L | SAU4005-G000-UZT-&CTB-01514 | Pipe Rack PR-18 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-17 |  |  |  | 2026-02-20 |  | 2025-12-12 |  | 2026-04-17 |  |  |  | 485 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO |  |  | NO | open
|  | 929 | Later | S&L | SAU4005-G000-UZT-&CTB-01516 | Pipe sleeper SL-02 Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-17 |  |  |  | 2026-02-20 |  | 2026-01-05 |  | 2026-04-17 |  |  |  | 485 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO |  |  | NO | open
|  | 931 | Later | S&L | SAU4005-G000-UZT-&CTB-01518 | Pipe sleeper SL-03 Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-17 |  |  |  | 2026-02-20 |  | 2026-01-03 |  | 2026-04-17 |  |  |  | 485 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO |  |  | NO | open
|  | 933 | Later | S&L | SAU4005-G000-UZT-&CTB-01522 | Pipe sleeper SL-05 Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-17 |  |  |  | 2026-02-20 |  | 2026-01-24 |  | 2026-04-17 |  |  |  | 485 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO |  |  | NO | open
|  | 936 | Later | S&L | SAU4005-G000-UBA-&CTL-01525 | GT Package MCC / Control room - 11, 12, 13 - Staircase-1 Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-01-19 |  |  |  | 2025-11-24 |  | 2025-09-24 |  | 2026-01-19 |  |  |  | 485 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO |  |  | NO | open
|  | 937 | Later | S&L | SAU4005-G000-UBA-&CTL-01526 | GT Package MCC / Control room - 11, 12, 13 - Staircase-2 Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-06-23 |  |  |  | 2026-04-28 |  | 2025-11-23 |  | 2026-06-23 |  |  |  | 485 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO |  |  | NO | open
|  | 938 | Later | S&L | SAU4005-G000-UBA-&CTL-01527 | Unit MV/LV Electrical Switchgear building-11, 12, 13- First Floor Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-07-25 |  |  |  | 2026-05-30 |  | 2025-10-28 |  | 2026-07-25 |  |  |  | 485 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO |  |  | NO | open
|  | 939 | Later | S&L | SAU4005-G000-UBA-&CTL-01528 | BOP-2 Switchgear E-House - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-11-19 |  |  |  | 2026-09-24 |  | 2026-05-13 |  | 2026-11-19 |  |  |  | 200 | [13 empty] | WF Transmittal DI-EPC-ACWA | YES | NO | NO | NO |  |  | NO | open
|  | 941 | Later | S&L | SAU4005-G000-UYX-&CED-01530 | FOAM TANK SHELTER - Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFD | [10 empty] | 2026-12-19 |  |  |  | 2026-10-24 |  | 2026-02-02 | [5 empty] | 485
|  | 942 | Later | S&L | SAU4005-G000-UYX-&CTL-01531 | FOAM TANK SHELTER - Superstructure layout and details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-12-19 |  |  |  | 2026-10-24 |  | 2026-02-02 |  | 2026-12-19
| PURPOSE CHANGED | 943 | Later | S&L | SAU4005-G000-UYX-&CED-01532 | FOAM TANK SHELTER - Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-26 |  | 2026-02-18 |  | 2026-03-16 |  | 2026-03-02 |  | 2026-04-22 |  | 2026-03-15
|  | 944 | Later | S&L | SAU4005-G000-UYX-&CTL-01533 | FOAM TANK SHELTER - Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-12-19 |  |  |  | 2026-10-24 |  | 2026-02-18 |  | 2026-12-19
|  | 945 | Later | S&L | SAU4005-G000-UYX-&MED-00478 | Calculation for TCA & FGH Vacuum Flash Tank | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-11-17 |  | 2025-10-14 |  | 2025-12-15 |  | 2025-11-04 |  | 2026-01-12 |  | 0
|  | 946 | Later | S&L | SAU4005-G000-UZT-&CED-01534 | Pipe Rack PR-15 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-19 |  | 2025-12-22 |  | 2026-03-19 |  | 2025-12-30 |  | 2026-04-16 |  | 2026-01-08
|  | 947 | Later | S&L | SAU4005-G000-UZT-&CED-01535 | Pipe Rack PR-15 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-01-19 |  | 2025-12-12 |  | 2026-02-16 |  | 2025-12-21 |  | 2026-03-16 |  | 2025-12-28
|  | 948 | Later | S&L | SAU4005-G000-UZT-&CLB-01536 | Pipe Rack PR-15 : Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-16 |  |  |  | 2026-02-19 |  | 2025-12-22 |  | 2026-04-16
|  | 949 | Later | S&L | SAU4005-G000-UZT-&CTB-01537 | Pipe Rack PR-15 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-03-16 |  |  |  | 2026-01-19 |  | 2025-12-12 |  | 2026-03-16
|  | 950 | Later | S&L | SAU4005-G000-SA_-&MED-00371 | HVAC sizing calculation for ACC Electrical Switchgear Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | PROCESS | SEPCOIII |  | IFA | IFD |  |  | 2025-11-26 |  | 2025-10-13 |  | 2025-12-24 |  | 2025-03-12 |  | 2026-01-21 |  | 2026-01-27
|  | 951 | Later | S&L | SAU4005-G000-SA_-&MFB-00392 | Air Flow Diagram of HVAC system for ACC Electrical Switchgear Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-05 |  | 2025-11-20 |  | 2026-03-05 |  | 0 |  | 2026-04-02 |  | 2025-12-23
|  | 952 | Later | S&L | SAU4005-G000-SA_-&MLH-00108 | HVAC Layout for ACC Electrical Switchgear Room | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-02-10 |  | 2025-12-25 |  | 2026-03-10 |  | 2025-12-18 |  | 2026-04-07 |  | 2026-03-29 | [5 empty] | 2026-04-07
|  | 953 | Later | S&L | SAU4005-G000-UBA-&ELH-00574 | Lighting Layout for ACC Electrical Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-06-24 |  | 2026-01-30 |  | 2026-07-22 |  | 2026-02-16 |  | 2026-08-19 |  | 2026-03-15 | [5 empty] | 2026-08-19
|  | 955 | Later | S&L | SAU4005-G000-UBA-&CED-01195 | ACC Electrical Switchgear Building - Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-10-22 |  | 2026-01-30 |  | 2026-11-19 |  | 2026-02-05 |  | 2026-12-17 |  | 2026-03-29
|  | 956 | Later | S&L | SAU4005-G000-UBA-&CTB-01196 | ACC Electrical Switchgear Building - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-10-22 |  | 2025-12-08 |  | 2026-11-19 |  | 2025-12-23 |  | 2026-12-17 |  | 2026-01-08 | [5 empty] | 2026-12-17
|  | 957 | Later | S&L | SAU4005-G000-UBA-&CLB-01198 | ACC Electrical Switchgear Building - Foundation and Column Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-12-17 |  |  |  | 2026-10-22 |  | 2026-01-30 |  | 2026-12-17
|  | 958 | Later | S&L | SAU4005-G000-UBA-&CTL-01199 | ACC Electrical Switchgear Building - Grade Beam Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-12-17 |  |  |  | 2026-10-22 |  | 2026-01-30 |  | 2026-12-17
|  | 959 | Later | S&L | SAU4005-G000-UBA-&CTL-01200 | ACC Electrical Switchgear Building - Roof Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-12-17 |  |  |  | 2026-10-22 |  | 2026-01-30 |  | 2026-12-17
|  | 960 | Later | S&L | SAU4005-G000-UBA-&CED-01472 | Electrical Switchgear Building for Fin Fan Cooler Area - Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-11-15 |  | 2025-11-22 |  | 2026-12-13 |  | 2025-12-07 |  | 2027-01-10 |  | 2025-12-23
|  | 961 | Later | S&L | SAU4005-G000-UBA-&CTB-01473 | Electrical Switchgear Building for Fin Fan Cooler Area - Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2027-01-10 |  |  |  | 2026-11-15 |  | 2025-10-15 |  | 2027-01-10
|  | 962 | Later | S&L | SAU4005-G000-UBA-&CTB-01486 | Electrical Switchgear Building for Fin Fan Cooler Area - False Ceiling Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2027-01-10 |  |  |  | 2026-11-15 |  | 2025-10-15 |  | 2027-01-10
|  | 963 | Later | S&L | SAU4005-G000-UBA-&CLB-01474 | Electrical Switchgear Building for Fin Fan Cooler Area - Foundation and Column Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2027-01-10 |  |  |  | 2026-11-15 |  | 2025-11-22 |  | 2027-01-10
|  | 964 | Later | S&L | SAU4005-G000-UBA-&CTL-01475 | Electrical Switchgear Building for Fin Fan Cooler Area - Grade Beam Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2027-01-10 |  |  |  | 2026-11-15 |  | 2025-11-22 |  | 2027-01-10
|  | 965 | Later | S&L | SAU4005-G000-UBA-&CTL-01476 | Electrical Switchgear Building for Fin Fan Cooler Area - Roof Slabs Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2027-01-10 |  |  |  | 2026-11-15 |  | 2025-11-18 |  | 2027-01-10
|  | 966 | Later | S&L | SAU4005-G000-URX-&MED-00475 | HVAC sizing calculation for Fin Fan Cooler Electrical Switchgear Building | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-10-22 |  | 2025-08-22 |  | 2025-11-19 |  | 2025-09-07 |  | 2025-12-17 |  | 2025-09-26
|  | 967 | Later | S&L | SAU4005-G000-URX-&MFB-00476 | Air Flow Diagram of HVAC system for Fin Fan Cooler Electrical Switchgear Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-15 |  | 2025-12-08 |  | 2026-03-15 |  | 2025-12-22 |  | 2026-04-12 |  | 2026-01-11
|  | 968 | Later | S&L | SAU4005-G000-URX-&MLH-00477 | HVAC Layout for Fin Fan Cooler Electrical Switchgear Building | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFC |  |  | 2026-02-25 |  | 2025-12-03 |  | 2026-03-25 |  | 2025-12-22 |  | 2026-04-22 |  | 2026-01-25 | [5 empty] | 2026-04-22
|  | 969 | Later | S&L | SAU4005-G000-___-&MBD-00474 | METHODOLOGY OF CALCULATION UNVERIFIED TO VERIFIED INPUTS | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | COMMON |  | IFA | IFD |  |  | 2026-04-28 |  | 2025-09-17 |  | 2026-05-18 |  | 2025-09-30 |  | 2026-06-23 |  | 0
|  | 970 | Later | S&L | SAU4005-G000-UBA-&ELH-00602 | Grounding Protection Layout for ACC Electrical Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-02-15 |  | 2025-10-04 |  | 2026-03-07 |  | 2025-07-17 |  | 2026-04-12 |  | 2025-11-04 | [5 empty] | 2026-04-12
|  | 971 | Later | S&L | SAU4005-G000-UG_-&MLD-00081 | General Arrangement of Water and Effluent treatment System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFP |  |  | 2025-06-28 |  | 2025-07-06 |  | 2025-08-12 |  | 0 |  | 2025-08-23 |  | 2026-05-05
|  | 972 | Later | S&L | SAU4005-G000-UBA-&ELH-00531 | Equipment Layout for ACC Electrical Container | A1 | Engineering | e-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2025-10-20 |  | 2025-08-15 |  | 2025-11-09 |  | 2025-08-31 |  | 2026-03-15 |  | 2025-12-09 | [5 empty] | 2026-03-15
|  | 975 | Later | S&L | SAU4005-G000-UGA-&CLB-01231 | Sludge Handling Facilities- Foundation & Pier Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-17 |  |  |  | 2026-02-20 |  | 2025-12-07 |  | 2026-04-17
|  | 976 | Later | S&L | SAU4005-G000-UGA-&CTL-01232 | Sludge Handling Facilities- Superstructure Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-03-02 |  |  |  | 2026-01-05 |  | 2026-01-02 |  | 2026-03-02
|  | 977 | Later | S&L | SAU4005-G000-UGA-&CTL-01233 | Sludge Handling Facilities- Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [10 empty] | 2026-04-17 |  |  |  | 2026-02-20 |  | 2026-01-02 |  | 2026-04-17
| New Added | 978 | Later | S&L | SAU4005-G000-UBA-&ELH-00612 | Grounding Protection Layout for BSEDG Building including Electrical Room | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-03-25 |  | 2025-10-08 |  | 2026-04-14 |  | 2025-10-16 |  | 2026-05-20 |  | 2025-11-09 | [5 empty] | 2026-05-27 | [17 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 979 | Later | S&L | SAU4005-G000-UZT-&CED-01444 | Pipe Rack PR-14 : Foundation Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-14 |  | 2025-12-04 |  | 2026-03-06 |  | 2025-12-14 |  | 2026-04-11 |  | 2025-12-21 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 980 | Later | S&L | SAU4005-G000-UZT-&CED-01445 | Pipe Rack PR-14 : Superstructure Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-01-29 |  | 2025-10-16 |  | 2026-02-18 |  | 2025-10-27 |  | 2026-03-26 |  | 2025-12-11 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 981 | Later | S&L | SAU4005-G000-UZT-&CLB-01446 | Pipe Rack PR-14 : Foundation Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFD | [14 empty] | 2026-02-14 |  | 2025-12-04 | [19 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 982 | Later | S&L | SAU4005-G000-UZT-&CTB-01447 | Pipe Rack PR-14 : Structural Layout and Details of Superstructure | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFD | [14 empty] | 2026-01-29 |  | 2025-10-16 | [19 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 983 | Later | S&L | SAU4005-G000-UBA-&CTL-01502 | GT Package MCC / Control room - 11, 12, 13 - First Floor Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFD | [14 empty] | 2025-10-12 |  | 2025-09-24 | [19 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 984 | Later | S&L | SAU4005-G000-UZT-&CTB-01520 | FUEL GAS BUFFER AREA FOUNDATION LAYOUT AND RC DETAILS | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFD | [14 empty] | 2025-12-25 |  | 2026-01-02 | [19 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 985 | Later | S&L | SAU4005-G000-UM_-&CTB-01456 | GT Area Pipe Trench Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-02-05 |  | 2025-11-30 | [19 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 987 | Later | S&L | SAU4005-G000-UGF-&MLH-00483 | HVAC Layout for Fire Water Pump House | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFD |  |  | 2026-01-19 |  | 2025-12-20 |  | 2026-02-08 |  | 2025-12-22 |  | 2026-03-16 |  | 2026-01-21 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 988 | Later | S&L | SAU4005-G000-SA_-&MED-00379 | HVAC SIZING CALCULATION FOR FIRE WATER PUMP HOUSE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-14 |  | 2025-11-14 |  | 2026-01-03 |  | 2025-11-30 |  | 2026-02-08 |  | 2025-12-28 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 989 | Later | S&L | SAU4005-G000-UEJ-&ELH-00868 | Cable raceway layout for Fuel Connection Facility | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2026-07-15 |  | 2026-05-30 |  | 2026-08-04 |  | 0 |  | 2026-09-09 |  | 0 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 990 | Later | S&L | SAU4005-G000-UBL-&CTB-01538 | IPBD ST Unit - 10 : Support Structure Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFD | [14 empty] | 2026-01-21 |  | 2025-12-22 | [19 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 991 | Later | S&L | SAU4005-G000-UBL-&CTB-01539 | IPBD GT Unit - 11, 12, & 13 : Support Structure Layout and Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2025-12-30 |  | 2025-11-30 |  | 2026-01-19 |  | 2025-12-09 |  | 2026-02-24 |  | 2026-01-08 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 992 | Later | S&L | SAU4005-G000-UER-&CTL-01121 | Fuel Gas Compressor Area - Grade Slab Layout and RC Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-07-15 |  | 2026-03-05 |  | 2026-08-04 |  | 2026-03-29 |  | 2026-09-09 |  | 0 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 993 | Later | S&L | SAU4005-G000-B__-&EFF-00873 | 380kV Protection Logic Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-02 |  | 2026-01-03 |  | 2026-02-22 |  | 0 |  | 2026-03-30 |  | 2026-01-19 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 994 | Later | S&L | SAU4005-G000-C__-&EPB-00874 | LDC/CRCC SIGNAL EXCHANGE LIST | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFD |  |  | 2026-02-02 |  | 2026-01-03 |  | 2026-02-22 |  | 0 |  | 2026-03-30 |  | 2026-02-01 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 995 | Later | S&L | SAU4005-G000-UBA-&CTB-01540 | Electrical Switchgear Building for Fuel Gas Area – False Ceiling Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFD | [14 empty] | 2026-01-18 |  | 2025-12-19 | [19 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 996 | Later | S&L | SAU4005-G000-SA_-&MFB-00400 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR FIRE WATER PUMP HOUSE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFD |  |  | 2026-01-07 |  | 2025-12-08 |  | 2026-01-27 |  | 2025-12-22 |  | 2026-03-04 |  | 2026-01-12 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 997 | Later | S&L | SAU4005-G000-UTS-&CTL-01541 | Chemical Storage Building for Water and Effluent Treatment System – Structural Layout and Details (Shed) | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFD | [14 empty] | 2026-01-30 |  | 2025-12-31 | [19 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 998 | Later | S&L | SAU4005-G000-SA_-&MED-00484 | HVAC SIZING CALCULATION FOR CHEMICAL STORAGE BUILDING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFD |  |  | 2026-07-15 |  | 2026-01-24 |  | 2026-08-04 |  | 2026-02-05 |  | 2026-09-09 |  | 2026-02-24 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 999 | Later | S&L | SAU4005-G000-SA_-&MLH-00485 | HVAC LAYOUT FOR CHEMICAL STORAGE BUILDING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFD |  |  | 2026-07-15 |  | 2026-02-23 |  | 2026-08-04 |  | 2026-03-10 |  | 2026-09-09 |  | 0 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1000 | Later | S&L | SAU4005-G000-SA_-&MFB-00486 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR CHEMICAL STORAGE BUILDING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | MECHANICAL | SEPCOIII |  | IFA | IFD |  |  | 2026-07-15 |  | 2026-02-08 |  | 2026-08-04 |  | 2026-02-24 |  | 2026-09-09 |  | 2026-03-10 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1001 | Later | S&L | SAU4005-G000-UMA-&CED-01542 | STEAM TURBINE GENERATOR FOUNDATION - RC DESIGN | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-01-23 |  | 2025-12-24 |  | 2026-02-12 |  | 2026-01-08 |  | 2026-03-20 |  | 2026-02-19 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1002 | Later | S&L | SAU4005-G000-G__-&CTB-01543 | Sludge Dewatering Shed - Superstructure Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFD | [14 empty] | 2026-01-18 |  | 2025-12-19 | [19 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1003 | Later | S&L | SAU4005-G000-UY_-&CTB-01544 | Support Building – Architectural Drawing | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFD | [14 empty] | 2026-01-30 |  | 2025-12-31 | [19 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1004 | Later | S&L | SAU4005-G000-UY_-&CTL-01545 | Support Building – Wet Area Details | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFD | [14 empty] | 2026-07-15 |  | 2026-03-27 | [19 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1005 | Later | S&L | SAU4005-G000-UY_-&CLB-01546 | Support Building – Foundation – Layout and RC details. | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFD | [14 empty] | 2026-07-15 |  | 2026-04-21 | [19 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1006 | Later | S&L | SAU4005-G000-UY_-&CTB-01547 | Support Building – Super Structure – Layout and RC details. | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFD | [14 empty] | 2026-07-15 |  | 2026-04-21 | [19 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1007 | Later | S&L | SAU4005-G000-UY_-&CED-01548 | Support Building – Design Calculation | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-07-15 |  | 2026-04-21 |  | 2026-08-04 |  | 2026-04-26 |  | 2026-09-09 |  | 2026-04-28 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1008 | Later | S&L | SAU4005-G000-USU-&ELH-00589 | Lighting Layout for WTP & ETP Electrical Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-07-15 |  | 2026-01-29 |  | 2026-08-04 |  | 2026-02-16 |  | 2026-09-09 |  | 2026-03-12 | [5 empty] | 2026-09-16 | [17 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1009 | Later | S&L | SAU4005-G000-SA_-&MED-00487 | HVAC Sizing Calculation For EHV CABLE CORRIDOR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII |  | IFA | IFD |  |  | 2026-07-15 |  | 2026-03-09 |  | 2026-08-04 |  | 2026-05-07 |  | 2026-09-09 |  | 0 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| DCC CHANGED | 1010 | Later | S&L | SAU4005-G000-SA_-&MFB-00488 | Air Flow Diagram of HVAC system for EHV CABLE CORRIDOR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII |  | IFA | IFD |  |  | 2026-07-15 |  | 2026-04-09 |  | 2026-08-04 |  | 2026-05-03 |  | 2026-09-09 |  | 2026-05-14 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| DCC CHANGED | 1011 | Later | S&L | SAU4005-G000-SA_-&MLH-00489 | HVAC Layout for EHV CABLE CORRIDOR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII |  | IFA | IFC |  |  | 2026-07-15 |  | 2026-05-25 |  | 2026-08-04 |  | 0 |  | 2026-09-09 |  | 0 | [5 empty] | 2026-09-16 | [17 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1012 | Later | S&L | SAU4005-G000-UQA-&CLB-01549 | CCCW EXPANSION TANK SUPPORTING STRUCTURE FOUNDATION LAYOUT & RC DETAILS | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-07-15 |  | 2026-02-18 |  | 2026-07-22 | [17 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1013 | Later | S&L | SAU4005-G000-UQA-&CTL-01550 | CCCW EXPANSION TANK SUPERSTRUCTURE LAYOUT DETAILS | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-01 |  | 2026-01-30 |  | 2026-03-08 | [17 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1014 | Later | S&L | SAU4005-G000-UBA-&CTL-01551 | UNIT MV/LV ELECTRICAL SWITCHGEAR BUILDING (UNIT #11, #12 & #13) STRUCTURAL DETAILS FOR STEEL STAIRCASE | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-02-15 |  | 2026-01-16 |  | 2026-02-22 | [17 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1015 | Later | S&L | SAU4005-G000-UTS-&CTL-01552 | CHEMICAL STORAGE BUILDING FOR WATER AND EFFLUENT TREATMENT SYSTEM – FALSE CEILING DETAILS | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-02-18 |  | 2026-01-19 |  | 2026-02-25 | [17 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1016 | Later | S&L | SAU4005-G000-UTS-&CTL-01553 | CHEMICAL STORAGE BUILDING FOR WATER AND EFFLUENT TREATMENT SYSTEM – WET AREA DETAILS | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-15 |  | 2026-03-20 |  | 2026-03-22 | [17 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1017 | Later | S&L | SAU4005-G000-U__-&CTB-01554 | OVER WATCH – ARCHITECTURAL DRAWING | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-02-15 |  | 2026-01-16 |  | 2026-02-22 | [17 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1018 | Later | S&L | SAU4005-G000-U__-&CTB-01555 | OVER WATCH – SUPER STRUCTURE DRAWING | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-04-19 |  | 2026-04-03 |  | 2026-04-26 | [17 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1019 | Later | S&L | SAU4005-G000-U__-&CLB-01556 | OVER WATCH – FOUNDATION LAYOUT AND RC DTAILS | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-05-15 |  | 2026-04-28 |  | 2026-05-22 | [17 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1020 | Later | S&L | SAU4005-G000-UYF-&CTB-01557 | PRELIMINARY INSPECTION CHECKPOINT (PIC) SECURITY SYSTEM - ARCHITECTURAL DRAWING | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-04 |  | 2026-02-02 |  | 2026-03-11 | [17 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1021 | Later | S&L | SAU4005-G000-UYF-&CTL-01558 | PRELIMINARY INSPECTION CHECKPOINT (PIC) SECURITY SYSTEM – STRUCTURAL DRAWING | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-05-15 |  | 2026-04-22 |  | 2026-05-22 | [17 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1022 | Later | S&L | SAU4005-G000-ULC-&CED-01559 | HRSG BLOWDOWN STORAGE TANK AREA - FOUNDATION DESIGN CALCULATION | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFA | IFD |  |  | 2026-03-04 |  | 2026-03-04 |  | 2026-03-24 |  | 2026-03-10 |  | 2026-04-29 |  | 2026-05-10 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1023 | Later | S&L | SAU4005-G000-ULC-&CLB-01560 | HRSG BLOWDOWN STORAGE TANK AREA - LAYOUT AND RC DETAILS | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-04 |  | 2026-03-04 |  | 2026-03-11 | [17 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1024 | Later | S&L | SAU4005-G000-SA_-&MED-00490 | HVAC Sizing Calculation For Support Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII |  | IFA | IFC |  |  | 2026-07-15 |  | 2026-03-16 |  | 2026-08-04 |  | 2026-01-29 |  | 2026-09-09 |  | 2026-04-23 | [5 empty] | 2026-09-16 | [17 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| DCC CHANGED | 1025 | Later | S&L | SAU4005-G000-SA_-&MFB-00491 | Air Flow Diagram of HVAC system for Support Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII |  | IFA | IFC |  |  | 2026-07-15 |  | 2026-04-15 |  | 2026-08-04 |  | 2026-04-26 |  | 2026-09-09 |  | 0 | [5 empty] | 2026-09-16 | [17 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| DCC CHANGED | 1026 | Later | S&L | SAU4005-G000-SA_-&MLH-00492 | HVAC Layout for Support Building | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII |  | IFA | IFC |  |  | 2026-03-22 |  | 2026-04-20 |  | 2026-04-11 |  | 2026-05-06 |  | 2026-05-17 |  | 0 | [5 empty] | 2026-05-24 | [17 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1027 | Later | S&L | SAU4005-G000-QJA-&MDA-00493 | SB Isometrics Drawing for Industrial Gas System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-07-15 |  | 2026-04-01 |  | 2026-07-22 | [17 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1028 | Later | S&L | SAU4005-G000-UYP-&ELH-00875 | Lighting Layout for Fire Station Building | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | ELECTRICAL | SEPCOIII |  | IFA | IFC |  |  | 2026-02-28 |  | 2026-01-29 |  | 2026-03-20 |  | 2026-02-16 |  | 2026-04-25 |  | 2026-03-15 | [5 empty] | 2026-05-02 | [17 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1029 | Later | S&L | SAU4005-G000-UGF-&CTL-01561 | FIRE HYDRANT VALVE PIT - TYPICAL RC DETAILS | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-07-15 |  | 2026-02-27 |  | 2026-07-22 | [17 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1030 | Later | S&L | SAU4005-G000-UBA-&CTL-01562 | ELECTRICAL SWITCHGEAR BUILDING FOR FUEL GAS AREA- STRUCTURAL DETAILS FOR STEEL STAIRCASE | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-30 |  | 2026-03-27 |  | 2026-04-06 | [17 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1031 | Later | S&L | SAU4005-G000-UBA-&CTL-01563 | MCC Room for Water and Effluent treatment building - STRUCTURAL DETAILS FOR STEEL STAIRCASE | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | SEPCOIII |  | IFI | IFC | [14 empty] | 2026-03-30 |  | 2026-03-19 |  | 2026-04-06 | [17 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1032 | Later | S&L | SAU4005-G000-UYF-&MFB-00496 | Air Flow Diagram of HVAC system for PRELIMINARY INSPECTION CHECKPOINT (PIC) SECURITY SYSTEM ROOM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII |  | IFA | IFD |  |  | 2026-07-15 |  | 2026-04-15 |  | 2026-08-04 |  | 2026-04-26 |  | 2026-09-09 |  | 0 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1033 | Later | S&L | SAU4005-G000-STA-&MEC-00227 | Technical Specifications for Workshop equipment | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII |  | IFA | IFD |  |  | 2025-11-10 |  | 2025-11-03 |  | 2025-11-30 |  | 2025-11-18 |  | 2025-12-09 |  | 2025-12-14 | [23 empty] | WF Transmittal DI-EPC-ACWA | YES | YES | NO
| New Added | 1034 | Later | S&L | SAU4005-G000-MB_-&MDA-00188 | PIPING SUPPORT SCHEDULE FOR SB GTG INTERCONNECTING SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | COMMON |  | IFI | IFC | [10 empty] | 2027-04-17 |  |  |  | 2027-04-14 |  | 2026-04-30
| New Added | 1035 | Later | S&L | SAU4005-G000-LBA-&MDA-01701 | SB PIPING SUPPORT FOR HIGH PRESSURE (HP) STEAM SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [14 empty] | 2026-05-19 |  | 2026-05-12
| New Added | 1036 | Later | S&L | SAU4005-G000-LBC-&MDA-01702 | SB PIPING SUPPORT FOR COLD RE-HEAT (CRH) STEAM SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN |  | IFI | IFC | [14 empty] | 2026-05-19 |  | 2026-05-12
|  | 1037 | LATER | DE(STG) | SAU4005-G010-MAA-&MDB-04004 | ST(V) - STEAM TURBINE FOUNDATION DESIGN CRITERIA | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-07-01 |  | 2025-09-25 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1038 | LATER | DE(STG) | SAU4005-G010-MAA-&MLB-04005 | ST(V) - STEAM TURBINE FOUNDATION LOADING DATA | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-07-01 |  | 2025-09-25 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1039 | LATER | DE(STG) | SAU4005-G010-MAA-&MDD-04030 | ST(V) - STEAM TURBINE OUTPUT CORRECTION FOR VARIOUS CONDITIONS(THERMAL KIT) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-07-31 |  | 2025-09-02 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1040 | LATER | DE(STG) | SAU4005-G010-MAV-&MFB-04061 | ST(V) - FLOW DIAGRAM - LUBE OIL CONDITIONER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-07-31 |  | 2025-12-04 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1041 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04210 | ST(V) - ASSEMBLY OF STEAM TURBINE EXHAUST HOOD (LP OUTER CASING) TO CONDENSER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-07-31 |  | 2025-09-30 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1042 | LATER | DE(STG) | SAU4005-G010-MAA-&MDB-04211 | ST(V) - STEAM TURBINE CONDENSER DESIGN RECOMMENDATIONS | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-07-31 |  | 2025-09-30 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1043 | LATER | DE(STG) | SAU4005-G010-MAC-&MTC-04218 | ST(V) - WPS/PQR FOR LP CASING FOR STG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-08-07 |  | 2025-11-07 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1044 | LATER | DE(STG) | SAU4005-G010-MKA-&MTC-04220 | ST(V) - WPS/PQR FOR STATOR FRAME FOR STG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-08-07 |  | 2025-09-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1045 | LATER | DE(STG) | SAU4005-G010-MKA-&MTC-04221 | ST(V) - WPS/PQR FOR END SHIELD FOR STG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-08-07 |  | 2025-09-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1046 | LATER | DE(STG) | SAU4005-G010-MAA-&MDC-04222 | ST(V) - PAINTING SPECIFICATION FOR STG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-08-07 |  | 2025-11-05 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1047 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04002 | ST(V) - TURBINE MAJOR COMPONENTS LAYDOWN AREA | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-08-21 |  | 2025-09-18 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1048 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04000 | ST(V) - OUTLINE - STEAM TURBINE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-06-20 |  | 2025-10-27 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO | NO | NO
|  | 1049 | LATER | DE(STG) | SAU4005-G010-MKA-&MLU-04001 | ST(V) - OUTLINE - GENERATOR MECHANICAL | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-07-11 |  | 2025-09-17 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO | NO | NO
|  | 1050 | LATER | DE(STG) | SAU4005-G010-MKA-&MLU-04003 | ST(V) - GENERATOR COMONENT LAYDOWN AREA | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-08-28 |  | 2025-09-17 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1051 | LATER | DE(STG) | SAU4005-G010-MKA-&MLB-04006 | ST(V) - GENERATOR FOUNDATION LOADING DATA | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-07-01 |  | 2025-09-17 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1052 | LATER | DE(STG) | SAU4005-G010-MAA-&MLB-04009 | ST(V) - FOUNDATION INTERFACE FOR STEAM TURBINE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-07-01 |  | 2025-09-11 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1053 | LATER | DE(STG) | SAU4005-G010-MKA-&MLB-04010 | ST(V) - GENERATOR FOUNDATION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-07-11 |  | 2025-09-17 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1054 | LATER | DE(STG) | SAU4005-G010-MAY-&EPC-04011 | ST(V) - STG ELECTRICAL LOAD LIST | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-08-28 |  | 2025-09-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1055 | LATER | DE(STG) | SAU4005-G010-MAX-&MPC-04012 | ST(V) - UTILITY CONSUMPTION LIST | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-08-28 |  | 2025-07-21 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1056 | LATER | DE(STG) | SAU4005-G010-MAX-&MDD-04023 | ST(V) - VALVE CHARACTERISTIC CURVE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-08-28 |  | 2025-09-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1057 | LATER | DE(STG) | SAU4005-G010-MAX-&MFB-04033 | ST(V) - P&ID - TURBINE HYDRAULIC FLUID SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFA | IFD |  |  | 2025-06-30 |  | 2025-10-02 |  | 2025-07-20 |  | 0 |  | 2025-08-25 |  | 2025-10-16 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | YES | C2 | NO
|  | 1058 | LATER | DE(STG) | SAU4005-G010-MAX-&MFB-04035 | ST(V) - P&ID - INSTRUMENT AIR SYSTEM FOR STG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFA | IFD |  |  | 2025-07-29 |  | 2025-09-26 |  | 2025-08-18 |  | 2025-10-09 |  | 2025-09-23 |  | 2026-03-10 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | YES | NO | NO
|  | 1059 | LATER | DE(STG) | SAU4005-G010-MAA-&MFB-04036 | ST(V) - P&ID - STEAM SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFA | IFD |  |  | 2025-07-29 |  | 2025-09-26 |  | 2025-08-18 |  | 2025-10-09 |  | 2025-09-23 |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | YES | C2 | NO
|  | 1060 | LATER | DE(STG) | SAU4005-G010-MKG-&MFB-04053 | ST(V) - P&ID - H2 COOLER VENT, DRAIN | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFA | IFD |  |  | 2025-06-30 |  | 2025-10-17 |  | 2025-07-20 |  | 0 |  | 2025-08-25 |  | 2025-11-05 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | YES | NO | NO
|  | 1061 | LATER | DE(STG) | SAU4005-G010-MKW-&MFB-04054 | ST(V) - P&ID - GENERATOR SHAFT SEAL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFA | IFD |  |  | 2025-06-30 |  | 2025-10-20 |  | 2025-07-20 |  | 0 |  | 2025-08-25 |  | 2025-11-04 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | YES | NO | NO
|  | 1062 | LATER | DE(STG) | SAU4005-G010-MKG-&MFB-04055 | ST(V) - P&ID - H2 & CO2 CONTROL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFA | IFD |  |  | 2025-06-30 |  | 2025-10-17 |  | 2025-07-20 |  | 0 |  | 2025-08-25 |  | 2025-11-05 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | YES | NO | NO
|  | 1063 | LATER | DE(STG) | SAU4005-G010-MKU-&MFB-04056 | ST(V) - P&ID - STATOR WINDING LIQUID COOLING SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFA | IFD |  |  | 2025-06-30 |  | 2025-10-20 |  | 2025-07-20 |  | 0 |  | 2025-08-25 |  | 2025-11-06 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | YES | NO | NO
|  | 1064 | LATER | DE(STG) | SAU4005-G010-MAV-&MFB-04070 | ST(V) - P&ID - JACKING OIL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFA | IFD |  |  | 2025-07-18 |  | 2025-10-15 |  | 2025-08-07 |  | 2025-11-05 |  | 2025-09-12 |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | YES | NO | NO
|  | 1065 | LATER | DE(STG) | SAU4005-G010-MAV-&MFB-04071 | ST(V) - P&ID - LUBE OIL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFA | IFD |  |  | 2025-07-18 |  | 2025-10-17 |  | 2025-08-07 |  | 2025-11-12 |  | 2025-09-12 |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | YES | NO | NO
|  | 1066 | LATER | DE(STG) | SAU4005-G010-MKA-&MLD-04103 | ST(V) - GENERATOR PIPING CONNECTION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-08-28 |  | 2025-09-17 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1067 | LATER | DE(STG) | SAU4005-G010-MKB-&ELU-04109 | ST(V) - GENERATOR ELECTRICAL CONDUIT LAYOUT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-07-01 |  | 2025-09-23 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1068 | LATER | DE(STG) | SAU4005-G010-MKB-&ELU-04110 | ST(V) - GENERATOR ELECTRICAL OUTLINE | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-07-01 |  | 2025-09-17 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1069 | LATER | DE(STG) | SAU4005-G010-MAA-&MPA-04191 | ST(V) - PIPING MATERIAL CLASSES FOR STEAM TURBINE & GENERATOR SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-08-28 |  | 2025-09-30 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1070 | LATER | DE(STG) | SAU4005-G010-MAA-&MEC-04240 | ST(V) - STEAM TURBINE NOISE TEST PROCEDURE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-09-18 |  | 2025-10-22 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1071 | LATER | DE(STG) | SAU4005-G010-MAA-&MDD-04028 | ST(V) - NOZZLE MOVEMENT & ALLOWABLE PIPE LOAD | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-08-09 |  | 2025-09-18 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1072 | LATER | DE(STG) | SAU4005-G010-MKC-&ELU-04090 | ST(V) - OUTLINE - EXCITATION SYSTEM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-09-30 |  | 2025-10-31 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1073 | LATER | DE(STG) | SAU4005-G010-MAX-&MPA-04206 | ST(V) - MANUAL VALVE LIST FOR STG PIPING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-10-09 |  | 2025-11-14 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1075 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04007 | ST(V) - ARRANGEMENT OF GROUT PADS & FOUNDATION PLATES - STEAM TURBINE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-07-01 |  | 2025-09-25 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1076 | LATER | DE(STG) | SAU4005-G010-MKA-&MLU-04008 | ST(V) - ARRANGEMENT OF GROUT PADS & FOUNDATION PLATES - GENERATOR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-07-01 |  | 2025-09-17 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1077 | LATER | DE(STG) | SAU4005-G010-MAX-&MLU-04032 | ST(V) - OUTLINE - HYDRAULIC POWER UNIT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-08-23 |  | 2025-10-02 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1078 | LATER | DE(STG) | SAU4005-G010-MKG-&MLU-04043 | ST(V) - OUTLINE - CO2 BOTTLE MANIFOLD FOR GENERATOR GAS CONTROL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-08-22 |  | 2025-10-27 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1079 | LATER | DE(STG) | SAU4005-G010-MKW-&MLU-04044 | ST(V) - OUTLINE - FLOAT TRAP | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-08-22 |  | 2025-10-27 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1080 | LATER | DE(STG) | SAU4005-G010-MKG-&MLU-04045 | ST(V) - OUTLINE - GAS CONTROL VALVE STATION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-08-22 |  | 2025-10-27 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1081 | LATER | DE(STG) | SAU4005-G010-MKG-&MLU-04046 | ST(V) - OUTLINE - H2 BOTTLE MANIFOLD FOR GENERATOR GAS CONTROL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-08-22 |  | 2025-10-27 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1082 | LATER | DE(STG) | SAU4005-G010-MKG-&MLU-04047 | ST(V) - OUTLINE - HYDROGEN CONTROL CABINET | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-08-22 |  | 2025-10-27 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1083 | LATER | DE(STG) | SAU4005-G010-MKG-&MLU-04048 | ST(V) - OUTLINE - HYDROGEN GAS DRYER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-08-22 |  | 2025-10-27 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1084 | LATER | DE(STG) | SAU4005-G010-MKW-&MLU-04049 | ST(V) - OUTLINE - HYDROGEN SEAL OIL UNIT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-08-22 |  | 2025-10-27 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1085 | LATER | DE(STG) | SAU4005-G010-MKW-&MLU-04050 | ST(V) - OUTLINE - LIQUID LEVEL DETECTOR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-08-22 |  | 2025-10-27 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1086 | LATER | DE(STG) | SAU4005-G010-MKU-&MLU-04051 | ST(V) - OUTLINE - STATOR WINDING WATER COOLING UNIT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-08-22 |  | 2025-10-27 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1087 | LATER | DE(STG) | SAU4005-G010-MAV-&MLU-04064 | ST(V) - OUTLINE - JACKING OIL DISTRIBUTION MANIFOLD | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-07-18 |  | 2025-10-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1088 | LATER | DE(STG) | SAU4005-G010-MAV-&MLU-04065 | ST(V) - OUTLINE - JACKING OIL PUMP UNIT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-07-18 |  | 2025-10-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1089 | LATER | DE(STG) | SAU4005-G010-MAV-&MLU-04066 | ST(V) - OUTLINE - LUBE OIL CONDITIONER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-07-18 |  | 2025-10-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1090 | LATER | DE(STG) | SAU4005-G010-MAV-&MLU-04067 | ST(V) - OUTLINE - LUBE OIL TANK | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-07-18 |  | 2025-10-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1091 | LATER | DE(STG) | SAU4005-G010-MAV-&MLU-04068 | ST(V) - OUTLINE - MIST ELIMINATOR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-07-18 |  | 2025-10-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1092 | LATER | DE(STG) | SAU4005-G010-MAG-&MLU-04074 | ST(V) - OUTLINE - GLAND STEAM CONDENSER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-09-23 |  | 2025-09-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1093 | LATER | DE(STG) | SAU4005-G010-MAY-&ELD-04077 | ST(V) - STEAM TURBINE CONDUIT LOCATION DRAWING | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-07-13 |  | 2025-09-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1094 | LATER | DE(STG) | SAU4005-G010-MKY-&EFA-04089 | ST(V) - SINGLE LINE DIAGRAM(INCLUDING ST GENERATOR CONTROL & PROTECTION, SUPPLY SCOPE) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-08-30 |  | 2025-09-18 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1095 | LATER | DE(STG) | SAU4005-G010-MKC-&EDB-04091 | ST(V) - ELEMENTARY DIAGRAM FOR EXCITATION SYSTEM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-10-31 |  | 2025-12-09 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1096 | LATER | DE(STG) | SAU4005-G010-MAY-&EDD-04097 | ST(V) - CONFIGURATION - TCS(SYSTEM CONFIGURATION - STG TCS / TPS ) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-09-23 |  | 2025-11-27 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1097 | LATER | DE(STG) | SAU4005-G010-MAY-&EDC-04100 | ST(V) - RECOMMENDED CONTROL CIRCUIT - STG MCC | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-09-23 |  | 2025-11-27 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1098 | LATER | DE(STG) | SAU4005-G010-MAY-&EFF-04102 | ST(V) - STG TRIP/PROTECTION DIAGRAM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-09-23 |  | 2025-11-27 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
| NEW | 1099 | LATER | DE(STG) | SAU4005-G010-MKA-&MDA-04104 | ST(V) - SHIPPING DIMENSIONS - GENERATOR STATOR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | [15 empty] | 2026-01-15 |  | 2026-02-02
|  | 1100 | LATER | DE(STG) | SAU4005-G010-MAA-&MPC-04113 | ST(V) - TERMINAL POINT LIST OF TURBINE SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-09-23 |  | 2026-02-05 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1101 | LATER | DE(STG) | SAU4005-G010-MAG-&MFB-04162 | ST(V) - P&ID - GLAND STEAM CONDENSER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFA | IFD |  |  | 2025-10-23 |  | 2025-10-27 |  | 2025-11-12 |  | 2025-11-11 |  | 2025-12-18 |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | YES | NO | NO | NO
|  | 1102 | LATER | DE(STG) | SAU4005-G010-MAA-&MPA-04190 | ST(V) - TURBINE PIPING INSULATION SPECIFICATION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-11-06 |  | 2025-12-05 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1103 | LATER | DE(STG) | SAU4005-G010-MAA-&MDB-04212 | ST(V) - INSULATION INSTALLATION PROCEDURE – HIP TURBINE & VALVE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-11-06 |  | 2025-11-26 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1104 | LATER | DE(STG) | SAU4005-G010-MAA-&MEC-04232 | ST(V) - ST_STEAM PURITY LIMITS REQUIRED DURING OPERATION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-06-09 |  | 2025-09-03 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1105 | LATER | DE(STG) | SAU4005-G010-MKB-&ELU-04111 | ST(V) - NEUTRAL TIE & ENCLOSURE ASSEMBLY | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-09-04 |  | 2025-09-17 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1106 | LATER | DE(STG) | SAU4005-G010-MKA-&ELU-04178 | ST(V) - GENERATOR ON LINE MONITORING SYSTEM LAYOUT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-12-04 |  | 2026-03-03 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1107 | LATER | DE(STG) | SAU4005-G010-MKA-&MLU-04192 | ST(V) - BRUSH HOLDER RIGGING ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-12-04 |  | 2026-04-06 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1108 | LATER | DE(STG) | SAU4005-G010-MAX-&MDB-04116 | ST(V) - STEAM BLOWING PROCEDURE FOR STEAM SEAL SYSTEM | A1 | Quality | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-12-25 |  | 2026-01-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1109 | LATER | DE(STG) | SAU4005-G010-MAA-&MQA-04306 | ST(V) - NDE PROCEDURE FOR GENERAL MATERIAL | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-12-25 |  | 2025-09-17 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1110 | LATER | DE(STG) | SAU4005-G010-MAA-&MQA-04307 | ST(V) - NDE PROCEDURE FOR GENERAL WELD | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-12-25 |  | 2025-09-17 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1111 | LATER | DE(STG) | SAU4005-G010-MAA-&MQA-04308 | ST(V) - NDE PROCEDURE FOR PIPING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-12-25 |  | 2025-09-17 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1112 | LATER | DE(STG) | SAU4005-G010-MAA-&MQA-04309 | ST(V) - NDE PROCEDURE FOR PRESSURE VESSEL | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-12-25 |  | 2025-09-17 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1113 | LATER | DE(STG) | SAU4005-G010-MAA-&MQA-04310 | ST(V) - NDE PROCEDURE FOR VALVE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-12-25 |  | 2025-09-17 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1114 | LATER | DE(STG) | SAU4005-G010-MAA-&MQA-04311 | ST(V) - NDE PROCEDURE FOR STEEL STRUCTURE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-12-25 |  | 2025-09-17 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1115 | LATER | DE(STG) | SAU4005-G010-MAA-&MLD-04018 | ST(V) - HP CASING PIPING CONNECTION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-01-15 |  | 2026-01-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1116 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04019 | ST(V) - HP CASING STUDS ARRANGEMENT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-01-15 |  | 2026-01-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1117 | LATER | DE(STG) | SAU4005-G010-MAX-&MMB-04034 | ST(V) - WIRING DIAGRAM - HYDRAULIC POWER UNIT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-11-16 |  | 2025-12-04 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1118 | LATER | DE(STG) | SAU4005-G010-MAX-&MDB-04037 | ST(V) - SYSTEM DESCRIPTION - STEAM SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-12-16 |  | 2025-12-18 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO | NO | NO
|  | 1119 | LATER | DE(STG) | SAU4005-G010-MAX-&MDA-04038 | ST(V) - LP STOP & CONTROL VALVE DATA SHEET AND OUTLINE FOR STG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-01-15 |  | 2026-01-20 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1120 | LATER | DE(STG) | SAU4005-G010-MAX-&MDA-04039 | ST(V) - MOTOR OPERATED VALVE DATA SHEET AND OUTLINE FOR STG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-01-15 |  | 2026-01-20 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1121 | LATER | DE(STG) | SAU4005-G010-MAX-&MDA-04040 | ST(V) - AIR OPERATED VALVE DATA SHEET AND OUTLINE FOR STG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-12-16 |  | 2026-01-23 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1122 | LATER | DE(STG) | SAU4005-G010-MAA-&MDA-04041 | ST(V) - NON-RETURN VALVE DATA SHEET AND OUTLINE FOR CRH | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-01-15 |  | 2026-01-20 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1123 | LATER | DE(STG) | SAU4005-G010-MKW-&EDA-04042 | ST(V) - PUMP & MOTOR DATA SHEET - HYDROGEN SEAL OIL SYSTEM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-11-16 |  | 2025-12-03 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1124 | LATER | DE(STG) | SAU4005-G010-MKU-&EDA-04052 | ST(V) - PUMP & MOTOR DATA SHEET - STATOR WATER COOLING SYSTEM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-11-16 |  | 2025-12-03 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1125 | LATER | DE(STG) | SAU4005-G010-MKF-&MDB-04058 | ST(V) - SYSTEM DESCRIPTION - GEN STATOR WINDING LIQUID COOLING SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-07-04 |  | 2025-11-13 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO | NO | NO
|  | 1126 | LATER | DE(STG) | SAU4005-G010-MKG-&MDB-04059 | ST(V) - SYSTEM DESCRIPTION - GENERATOR GAS(H2&CO2) CONTROL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-07-04 |  | 2025-11-14 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO | NO | NO
|  | 1127 | LATER | DE(STG) | SAU4005-G010-MKW-&MDB-04060 | ST(V) - SYSTEM DESCRIPTION - GENERATOR HYDROGEN SEAL OIL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-07-04 |  | 2025-11-14 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO | NO | NO
|  | 1128 | LATER | DE(STG) | SAU4005-G010-MAV-&EDA-04062 | ST(V) - PUMP & MOTOR DATA SHEET - LUBE OIL CONDITIONER | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-11-15 |  | 2025-12-01 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1129 | LATER | DE(STG) | SAU4005-G010-MAV-&EDA-04069 | ST(V) - PUMP & MOTOR DATA SHEET - LUBE OIL TANK | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-11-15 |  | 2025-11-19 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1130 | LATER | DE(STG) | SAU4005-G010-MAV-&MDB-04072 | ST(V) - SYSTEM DESCRIPTION - LUBE OIL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-07-18 |  | 2025-10-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO | NO | NO
|  | 1131 | LATER | DE(STG) | SAU4005-G010-MAG-&EDA-04073 | ST(V) - BLOWER & MOTOR DATA SHEET - GLAND STEAM CONDENSER | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-12-16 |  | 2026-03-12 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1132 | LATER | DE(STG) | SAU4005-G010-MAY-&MLD-04075 | ST(V) - HOOK-UP DRAWING - STEAM TURBINE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-12-16 |  | 2026-01-14 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1133 | LATER | DE(STG) | SAU4005-G010-MAY-&ELU-04095 | ST(V) - OUTLINE - STG TCS / TPS CABINET TCS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-12-16 |  | 2025-12-29 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1134 | LATER | DE(STG) | SAU4005-G010-MAY-&EPC-04099 | ST(V) - I/O LIST - STG TCS / TPS (HARDWIRED & SOFT SIGNAL) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-12-16 |  | 2025-09-23 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1135 | LATER | DE(STG) | SAU4005-G010-MKG-&MLU-04107 | ST(V) - OUTLINE - HYDROGEN COOLER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-06-16 |  | 2025-08-07 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1136 | LATER | DE(STG) | SAU4005-G010-MAL-&MDB-04165 | ST(V) - STEAM DRAIN RECOMMENDATIONS FOR STEAM TURBINE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-01-15 |  | 2026-01-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1137 | LATER | DE(STG) | SAU4005-G010-MKA-&MDB-04208 | ST(V) - ST GENERATOR NAME PLATE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-01-15 |  | 2026-01-23 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1138 | LATER | DE(STG) | SAU4005-G010-MKC-&EFB-04226 | ST(V) - BLOCK DIAGRAM_COMPLETE EXCITATION SYSTEM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-01-15 |  | 2026-01-06 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1139 | LATER | DE(STG) | SAU4005-G010-MAA-&MLD-04228 | ST(V) - IP CASING PIPING CONNECTION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-01-15 |  | 2026-01-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1140 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04229 | ST(V) - IP CASING STUDS ARRANGEMENT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-01-15 |  | 2026-01-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1141 | LATER | DE(STG) | SAU4005-G010-MAA-&MDB-04013 | ST(V) - STEAM BLOWING REQUIREMENT - STEAM TURBINE | A1 | COMMISSIONING | M-Mechanical engineering (normally including process engineering) | YES | COMMISSIONING | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-02-12 |  | 2026-02-26 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1142 | LATER | DE(STG) | SAU4005-G010-MAA-&MDD-04014 | ST(V) - STEAM TURBINE STARTUP & SHUTDOWN CURVES | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-09-30 |  | 2025-10-21 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1143 | LATER | DE(STG) | SAU4005-G010-MAK-&MLU-04022 | ST(V) - OUTLINE – TURNING GEAR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-09-30 |  | 2025-09-17 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1144 | LATER | DE(STG) | SAU4005-G010-MAK-&EFF-04024 | ST(V) - WIRING SCHEMATIC - TURNING GEAR PANEL | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-09-30 |  | 2025-11-07 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1145 | LATER | DE(STG) | SAU4005-G010-MAX-&MLU-04025 | ST(V) - OUTLINE - HPV (HIGH PRESSURE VALVE) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-09-30 |  | 2025-09-17 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1146 | LATER | DE(STG) | SAU4005-G010-MAX-&MLU-04026 | ST(V) - OUTLINE - IPV (INTERMEDIATE PRESSURE VALVE) | A1 |  | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-09-30 |  | 2025-09-17 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1147 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04029 | ST(V) - LIFTING ARRANGEMENT - STEAM TURBINE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-11-30 |  | 2025-12-05 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1148 | LATER | DE(STG) | SAU4005-G010-MKY-&EED-04082 | ST(V) - PROTECTIVE RELAY SETTING(ST GENERATOR PROTECTION, EXCITER TRANSFORMER RELAY SETTING CALCULATION) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-12-31 |  | 2025-12-18 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1149 | LATER | DE(STG) | SAU4005-G010-MAY-&ELU-04092 | ST(V) - CABINET INTERNAL ARRANGEMENT DRAWING - STG TCS / TPS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-01-13 |  | 2026-02-24 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1150 | LATER | DE(STG) | SAU4005-G010-MAY-&ELU-04096 | ST(V) - OUTLINE - STG VMS CABINET | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-01-13 |  | 2026-04-10 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1151 | LATER | DE(STG) | SAU4005-G010-MAA-&MDD-04163 | ST(V) - STEAM TURBINE START-UP & SHUTDOWN PROCEDURE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-02-12 |  | 2026-02-27 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1152 | LATER | DE(STG) | SAU4005-G010-MAY-&EPC-04168 | ST(V) - INSTRUMENT LIST FOR STEAM TURBINE | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-02-12 |  | 2026-02-13 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1153 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04242 | ST(V) - STEAM TURBINE SXD(SHELL EXPANSION DETECTOR) MOUNT ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-02-19 |  | 2026-04-01 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1154 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04243 | ST(V) - STEAM TURBINE FOUNDATION ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-02-19 |  | 2026-04-01 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1155 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04244 | ST(V) - STEAM TURBINE CONNECTING MEMBER ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-02-19 |  | 2026-04-01 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1156 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04245 | ST(V) - STEAM TURBINE COUPLING GUARD ASSEMBLY - HP/IP PEDESTAL | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-02-19 |  | 2026-04-01 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1157 | LATER | DE(STG) | SAU4005-G010-MAC-&MLU-04246 | ST(V) - STEAM TURBINE COUPLING GUARD ASSEMBLY - LP PEDESTAL | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-02-19 |  | 2026-04-01 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1158 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04247 | ST(V) - STEAM TURBINE SPEED PICKUP/ECCENTRICITY ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-02-19 |  | 2026-04-01 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1159 | LATER | DE(STG) | SAU4005-G010-MAC-&MLU-04248 | ST(V) - STEAM TURBINE RXD MOUNT ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-02-19 |  | 2026-04-01 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1160 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04249 | ST(V) - STEAM TURBINE HP FRONT PEDESTAL ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-02-19 |  | 2026-04-02 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1161 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04250 | ST(V) - STEAM TURBINE HP/IP MIDDLE PEDESTAL ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-02-19 |  | 2026-04-02 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1162 | LATER | DE(STG) | SAU4005-G010-MAB-&MLU-04251 | ST(V) - STEAM TURBINE IP REAR PEDESTAL ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-02-19 |  | 2026-04-02 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1163 | LATER | DE(STG) | SAU4005-G010-MAC-&MLU-04252 | ST(V) - STEAM TURBINE LPA REAR PEDESTAL ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-02-19 |  | 2026-04-02 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1164 | LATER | DE(STG) | SAU4005-G010-MAC-&MLU-04253 | ST(V) - STEAM TURBINE LPB REAR PEDESTAL ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-02-19 |  | 2026-04-02 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1165 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04254 | ST(V) - STEAM TURBINE OIL DEFLECTOR ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-02-19 |  | 2026-04-01 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1166 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04255 | ST(V) - STEAM TURBINE BEARING JACKING OIL TUBING PEDESTAL ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-02-19 |  | 2026-04-01 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1167 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04256 | ST(V) - STEAM TURBINE PEDESTAL KEY IDENTIFICATION LIST | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-02-19 |  | 2026-04-01 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1168 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04257 | ST(V) - STEAM TURBINE EARTH(GROUND) PAD LOCATION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-02-19 |  | 2026-04-01 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1169 | LATER | DE(STG) | SAU4005-G010-MAY-&MLU-04258 | ST(V) - STEAM TURBINE INSTRUMENT LOCATION DRAWING FOR INSTALLATION - PEDESTAL | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-02-19 |  | 2026-04-02 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1170 | LATER | DE(STG) | SAU4005-G010-MAB-&MLU-04259 | ST(V) - STEAM TURBINE CROSSOVER PIPE OUTLINE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-02-19 |  | 2026-03-31 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1171 | LATER | DE(STG) | SAU4005-G010-MAB-&MLU-04260 | ST(V) - HEAT RETENTION MATERIAL - CROSSOVER PIPE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-02-19 |  | 2026-04-08 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1172 | LATER | DE(STG) | SAU4005-G010-MAY-&EMB-04093 | ST(V) - CABINET INTERNAL WIRING - STG TCS / TPS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-02-10 |  | 2026-03-27 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1173 | LATER | DE(STG) | SAU4005-G010-MAY-&EMB-04094 | ST(V) - CABINET INTERNAL WIRING - STG VMS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-02-10 |  | 2026-04-10 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1174 | LATER | DE(STG) | SAU4005-G010-MAY-&EPC-04101 | ST(V) - SIGNAL INTERFACE LIST BETWEEN STG TCS /TPS & DCS (HARDWIRED & SOFT SIGNAL) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-02-10 |  | 2026-02-12 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1175 | LATER | DE(STG) | SAU4005-G010-MAA-&MDA-04184 | ST(V) - PIPING ISOMETRIC DRAWING OF STEAM SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-03-12 |  | 2026-04-06 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1176 | LATER | DE(STG) | SAU4005-G010-MAW-&MDA-04185 | ST(V) - PIPING ISOMETRIC DRAWING OF LUBRICATING OIL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-03-12 |  | 2026-04-06 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1177 | LATER | DE(STG) | SAU4005-G010-MKG-&MDA-04186 | ST(V) - PIPING ISOMETRIC DRAWING OF GEN GAS CONTROL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-03-12 |  | 2026-04-06 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1178 | LATER | DE(STG) | SAU4005-G010-MKW-&MDA-04187 | ST(V) - PIPING ISOMETRIC DRAWING OF HYDROGEN SEAL OIL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-03-12 |  | 2026-04-06 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1179 | LATER | DE(STG) | SAU4005-G010-MKU-&MDA-04188 | ST(V) - PIPING ISOMETRIC DRAWING OF GEN STATOR WINDING LIQUID COOLING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-03-12 |  | 2026-04-06 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1180 | LATER | DE(STG) | SAU4005-G010-MAX-&MDA-04189 | ST(V) - PIPING ISOMETRIC DRAWING OF HYDROLIC FLUID PIPING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-03-12 |  | 2026-04-06 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1181 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04173 | ST(V) - PIPING ARRANGEMENT OF STEAM SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-03-26 |  | 2026-04-29 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1182 | LATER | DE(STG) | SAU4005-G010-MAV-&MLU-04174 | ST(V) - PIPING ARRANGEMENT OF LUBRICATING OIL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-03-26 |  | 2026-04-29 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1183 | LATER | DE(STG) | SAU4005-G010-MKG-&MLU-04175 | ST(V) - PIPING ARRANGEMENT OF GEN GAS CONTROL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-03-26 |  | 2026-04-29 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1184 | LATER | DE(STG) | SAU4005-G010-MKW-&MLU-04176 | ST(V) - PIPING ARRANGEMENT OF HYDROGEN SEAL OIL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-03-26 |  | 2026-04-29 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1185 | LATER | DE(STG) | SAU4005-G010-MKU-&MLU-04177 | ST(V) - PIPING ARRANGEMENT OF GEN STATOR WINDING LIQUID COOLING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-03-26 |  | 2026-04-29 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1186 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04204 | ST(V) - TURBINE OPENING INFORMATION FOR STG PIPING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-03-26 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1187 | LATER | DE(STG) | SAU4005-G010-MAW-&MLU-04241 | ST(V) - OUTLINE - DE-HUMIDIFICATION UNIT FOR STG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-03-03 |  | 2026-03-03 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1188 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04261 | ST(V) - HP INNER CASING ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-02 |  | 2026-04-02 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1189 | LATER | DE(STG) | SAU4005-G010-MAB-&MLU-04262 | ST(V) - IP INNER CASING ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-02 |  | 2026-04-02 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1190 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04263 | ST(V) - HP OUTER CASING ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-02 |  | 2026-04-02 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1191 | LATER | DE(STG) | SAU4005-G010-MAB-&MLU-04264 | ST(V) - IP OUTER CASING ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-02 |  | 2026-04-02 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1192 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04265 | ST(V) - HP-IP KEY IDENTIFICATION LIST | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-02 |  | 2026-04-02 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1193 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04266 | ST(V) - THERMOCOUPLE HOLDER ASSEMBLY (HP INLET) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-02 |  | 2026-04-02 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1194 | LATER | DE(STG) | SAU4005-G010-MAB-&MLU-04267 | ST(V) - THERMOCOUPLE HOLDER ASSEMBLY (IP INLET) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-02 |  | 2026-04-02 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1195 | LATER | DE(STG) | SAU4005-G010-MAC-&MLU-04268 | ST(V) - TURBINE CASING WELD PREPERATION INFORMATION - CUSTOMER CONNECTION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-02 |  | 2026-04-02 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1196 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04269 | ST(V) - N2 RETURN PIPE ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-02 |  | 2026-04-02 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1197 | LATER | DE(STG) | SAU4005-G010-MAB-&MLU-04270 | ST(V) - IP FRONT GLAND ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-02 |  | 2026-04-02 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1198 | LATER | DE(STG) | SAU4005-G010-MAB-&MLU-04271 | ST(V) - IP REAR GLAND ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-02 |  | 2026-04-02 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1199 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04272 | ST(V) - HP FRONT GLAND ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-02 |  | 2026-04-02 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1200 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04273 | ST(V) - HP INNER GLAND ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-02 |  | 2026-04-02 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1201 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04274 | ST(V) - HP REAR GLAND ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-02 |  | 2026-04-02 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1202 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04275 | ST(V) - HP CASING INSTRUMENT LOCATION DRAWING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-02 |  | 2026-04-02 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1203 | LATER | DE(STG) | SAU4005-G010-MAB-&MLU-04276 | ST(V) - IP CASING INSTRUMENT LOCATION DRAWING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-02 |  | 2026-04-02 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1204 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04277 | ST(V) - HP CASING MAIN ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-02 |  | 2026-04-02 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1205 | LATER | DE(STG) | SAU4005-G010-MAB-&MLU-04278 | ST(V) - IP CASING MAIN ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-02 |  | 2026-04-02 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1206 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04281 | ST(V) - STEAM TURBINE HPV SUPPORT ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-02 |  | 2026-06-09 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1207 | LATER | DE(STG) | SAU4005-G010-MAB-&MLU-04282 | ST(V) - STEAM TURBINE IPV SUPPORT ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-02 |  | 2026-06-09 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1208 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04283 | ST(V) - STEAM TURBINE HPV ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-02 |  | 2026-04-06 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1209 | LATER | DE(STG) | SAU4005-G010-MAB-&MLU-04284 | ST(V) - STEAM TURBINE IPV ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-02 |  | 2026-04-06 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1210 | LATER | DE(STG) | SAU4005-G010-MAX-&MLU-04285 | ST(V) - STEAM TURBINE VALVE WELD PREPARATIONS INFORMATION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-02 |  | 2026-04-06 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1211 | LATER | DE(STG) | SAU4005-G010-MAX-&MLU-04286 | ST(V) - ST_HEAT RETENTION MATERIAL_HP/IP VALVES | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-02 |  | 2026-04-06 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1212 | LATER | DE(STG) | SAU4005-G010-MAA-&MFB-04287 | ST(V) - TURBINE SUPERVISORY INSTRUMENT DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-04-02 |  | 2026-02-24 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1213 | LATER | DE(STG) | SAU4005-G010-MAW-&MLD-04196 | ST(V) - HANGER & SUPPORT DRAWING FOR TURBINE STEAM SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-09 |  | 2026-05-13 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1214 | LATER | DE(STG) | SAU4005-G010-MAV-&MLD-04197 | ST(V) - HANGER & SUPPORT DRAWING FOR TURBINE LUBRICATING OIL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-09 |  | 2026-05-13 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1215 | LATER | DE(STG) | SAU4005-G010-MKG-&MLD-04198 | ST(V) - HANGER & SUPPORT DRAWING FOR GEN GAS CONTROL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-09 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1216 | LATER | DE(STG) | SAU4005-G010-MKW-&MLD-04199 | ST(V) - HANGER & SUPPORT DRAWING FOR HYDROGEN SEAL OIL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-09 |  | 2026-05-13 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1217 | LATER | DE(STG) | SAU4005-G010-MKU-&MLD-04200 | ST(V) - HANGER & SUPPORT DRAWING FOR GEN STATOR WINDING LIQUID COOLING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-09 |  | 2026-05-13 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1218 | LATER | DE(STG) | SAU4005-G010-MAL-&MLD-04201 | ST(V) - HANGER & SUPPORT DRAWING FOR SMALL BORE PIPING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-09 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1219 | LATER | DE(STG) | SAU4005-G010-MKA-&MLU-04207 | ST(V) - GENERATOR FIELD ASSEMBLY AND DISASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-09 |  | 2026-04-10 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1220 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04279 | ST(V) - HEAT RETENTION MATERIAL - HP/IP TURBINE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-16 |  | 2026-04-02 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1221 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04280 | ST(V) - HORIZONTAL AND VERTICAL JOINT STUD TIGHTENING_HIP CASING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-16 |  | 2026-04-02 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1222 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04182 | ST(V) - ARRANGEMENT-TURBINE LAGGING SUPPORT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-23 |  | 2026-03-27 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1223 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04183 | ST(V) - OUTLINE-STEAM TURBINE ENCLOSURE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-03-24 |  | 2026-03-27 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1224 | LATER | DE(STG) | SAU4005-G010-MAY-&EMB-04076 | ST(V) - INTERCONNECTION WIRING DIAGRAM - STEAM TURBINE | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-07 |  | 2026-04-10 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
| DCC changed | 1225 | LATER | DE(STG) | SAU4005-G010-MAY-&EFC-04098 | ST(V) - HMI GRAPHIC - STG TCS / TPS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-04-07 |  | 2026-04-08 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1226 | LATER | DE(STG) | SAU4005-G010-MAY-&ELU-04169 | ST(V) - INSTRUMENT CABINET DRAWING FOR STEAM TURBINE | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-05-07 |  | 2026-04-24 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1227 | LATER | DE(STG) | SAU4005-G010-MAY-&EDA-04170 | ST(V) - INSTRUMENT DATASHEET FOR LOCAL INSTRUMENT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-05-07 |  | 2026-04-01 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1228 | LATER | DE(STG) | SAU4005-G010-MAY-&ELU-04172 | ST(V) - CONDUIT ARRANGEMENT DRAWING FOR STEAM TURBINE | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-04-07 |  | 2026-04-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1229 | LATER | DE(STG) | SAU4005-G010-MAC-&MLU-04238 | ST(V) - ST_OUTLINE DRAWING_LP GLAND PACKING RING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-05-07 |  | 2026-04-01 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1230 | LATER | DE(STG) | SAU4005-G010-MAB-&MLU-04237 | ST(V) - ST_OUTLINE DRAWING_IP GLAND PACKING RING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-03-31 |  | 2026-04-01 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1231 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04236 | ST(V) - ST_OUTLINE DRAWING_HP GLAND PACKING RING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-03-31 |  | 2026-04-01 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1232 | LATER | DE(STG) | SAU4005-G010-MAC-&MLU-04239 | ST(V) - ST_OUTLINE DRAWING_LP DIAPHRAGM PACKING RING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-03-31 |  | 2026-04-01 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1233 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04233 | ST(V) - ST_ASSEMBLY DRAWING_DIAPHRAGM SUPPORT BAR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-05-07 |  | 2026-04-01 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1234 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04234 | ST(V) - ST_ASSEMBLY DRAWING_PACKING RING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-05-07 |  | 2026-04-01 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1235 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04235 | ST(V) - ST_ASSEMBLY DRAWING_DIAPHRAGM BOLT TORQUE TIGHTING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-05-07 |  | 2026-04-01 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1236 | LATER | DE(STG) | SAU4005-G010-MAD-&MLU-04304 | ST(V) - STEAM TURBINE JOURNAL BEARING ASSY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-05-07 |  | 2026-01-09 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1237 | LATER | DE(STG) | SAU4005-G010-MAD-&MLU-04305 | ST(V) - STEAM TURBINE THRUST BEARING ASSY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-05-07 |  | 2026-01-09 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1238 | LATER | DE(STG) | SAU4005-G010-MAY-&ELD-04171 | ST(V) - INSTRUMENT LOCATION DRAWING FOR STEAM TURBINE | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-06-04 |  | 2026-02-13 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1239 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04288 | ST(V) - STEAM TURBINE LP OUTER CASING ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-06-25 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1240 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04289 | ST(V) - STEAM TURBINE LP INNER CASING ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-06-25 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1241 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04290 | ST(V) - STEAM TURBINE LP CASING BOLT ARRANGEMENT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-06-25 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1242 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04291 | ST(V) - STEAM TURBINE LP CASING END GIB & KEY ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-06-25 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1243 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04292 | ST(V) - STEAM TURBINE LP DEFLECTOR(STEAM GUIDE) ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-06-25 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1244 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04293 | ST(V) - STEAM TURBINE LP INNER CASINGSHIELDING HORIZONTAL JOINT ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-06-25 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1245 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04294 | ST(V) - STEAM TURBINE LP PACKING GLAND ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-06-25 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1246 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04295 | ST(V) - STEAM TURBINE LP PACKING CASING ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-06-25 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1247 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04296 | ST(V) - STEAM TURBINE LP RELIEF DIAPHRAGM ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-06-25 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1248 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04297 | ST(V) - STEAM TURBINE LP WATER COOLING SPRAY ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-06-25 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1249 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04298 | ST(V) - STEAM TURBINE VSL PIPING ASSY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-06-25 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1250 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04299 | ST(V) - STEAM TURBINE PERFORMANCE TEST PIPING FOR LP EXHAUST PRESSURE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-06-25 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1251 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04300 | ST(V) - STEAM TURBINE LP CONDENSERSEAL BELLOWS ASSY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-06-25 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1252 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04301 | ST(V) - STEAM TURBINE LP PIPING CONNECTION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-06-25 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1253 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04302 | ST(V) - STEAM TURBINE INSTRUMENT LOCATION DRAWING FOR INSTALLATION - LP CASING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-06-25 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1254 | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04303 | ST(V) - STEAM TURBINE LP KEY IDENTIFICATION LIST | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-06-25 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1255 | LATER | DE(STG) | SAU4005-G010-MAD-&MLU-04015 | ST(V) - BEARING ALIGNMENT DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-07-02 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1256 | LATER | DE(STG) | SAU4005-G010-MAA-&MDA-04016 | ST(V) - CLEARANCE MEASUREMENT DATA(HP/IP) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-07-02 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1257 | LATER | DE(STG) | SAU4005-G010-MKA-&MLD-04105 | ST(V) - GENERATOR FIELD CLEARANCE DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-07-02 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1258 | LATER | DE(STG) | SAU4005-G010-MKA-&MLU-04312 | ST(V) - GENERATOR BEARING ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-07-02 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1259 | LATER | DE(STG) | SAU4005-G010-MAA-&MDD-04313 | ST(V) - PIPING STRESS ANALYSIS REPORT FOR STG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-07-02 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1260 | LATER | DE(STG) | SAU4005-G010-MAC-&MDA-04017 | ST(V) - CLEARANCE MEASUREMENT DATA(LP) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-07-30 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1261 | LATER | DE(STG) | SAU4005-G010-MAA-&MEC-04027 | ST(V) - CRANE & HOIST REQUIREMENTS STG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-08-09 |  | 2025-09-25 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1262 | LATER | DE(STG) | SAU4005-G010-MAV-&MLU-04202 | ST(V) - OUTLINE DRAWING FOR BEARING DRAIN ENLARGEMENT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-12-31 |  | 2026-01-14 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1263 | LATER | DE(STG) | SAU4005-G010-MKW-&MLU-04203 | ST(V) - OUTLINE DRAWING FOR SEAL OIL DRAIN ENLARGEMENT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-12-31 |  | 2026-01-14 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1264 | LATER | DE(STG) | SAU4005-G010-MAA-&MPC-04205 | ST(V) - LINE LIST FOR STG PIPING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-08-27 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1265 | LATER | DE(STG) | SAU4005-G010-MAX-&MLU-04020 | ST(V) - BLOWDOWN COVER OUTLINE - HPV (HIGH PRESSURE VALVE) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-10-01 |  | 2026-04-10 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1266 | LATER | DE(STG) | SAU4005-G010-MAX-&MLU-04021 | ST(V) - BLOWDOWN COVER OUTLINE - IPV (INTERMEDIATE PRESSURE VALVE) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2026-10-01 |  | 2026-04-10 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1267 | LATER | DE(STG) | SAU4005-G010-MKC-&ELU-04078 | ST(V) - OUTLINE - ST EXCITATION TRANSFORMER | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-09-12 |  | 2025-09-18 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1268 | LATER | DE(STG) | SAU4005-G010-MKY-&ELU-04079 | ST(V) - OUTLINE - ST GENERATOR PROTECTION RELAY PANEL | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-10-31 |  | 2025-12-05 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1269 | LATER | DE(STG) | SAU4005-G010-MKY-&ELU-04080 | ST(V) - OUTLINE - ST NGR & NGTR PANEL | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-10-31 |  | 2025-12-18 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1270 | LATER | DE(STG) | SAU4005-G010-MKY-&ELU-04081 | ST(V) - OUTLINE & DETAIL DRAWINGS - ST AC/DC BUSDUCT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-10-31 |  | 2025-12-09 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1271 | LATER | DE(STG) | SAU4005-G010-MAV-&EFF-04083 | ST(V) - SCHEMATIC DIAGRAM - ST EBOP DC MOTOR STARTER PANEL | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-10-31 |  | 2025-12-18 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1272 | LATER | DE(STG) | SAU4005-G010-MAW-&EFF-04084 | ST(V) - SCHEMATIC DIAGRAM - ST ESOP DC MOTOR STARTER PANEL | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-10-31 |  | 2025-12-18 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1273 | LATER | DE(STG) | SAU4005-G010-MKC-&EFF-04085 | ST(V) - SCHEMATIC DIAGRAMS - ST EXCITATION TRANSFORMER | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-10-31 |  | 2025-11-26 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1274 | LATER | DE(STG) | SAU4005-G010-MKY-&EFF-04086 | ST(V) - SCHEMATIC DIAGRAMS - ST GEN SYNCHRONIZING & METERING PANEL | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-10-31 |  | 2025-12-05 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1275 | LATER | DE(STG) | SAU4005-G010-MKY-&EFF-04087 | ST(V) - SCHEMATIC DIAGRAMS - ST GENERATOR PROTECTION RELAY PANEL | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-10-31 |  | 2025-12-18 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1276 | LATER | DE(STG) | SAU4005-G010-MKY-&EFF-04088 | ST(V) - SCHEMATIC DIAGRAMS - ST NGR & NGTR PANEL | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-10-31 |  | 2025-12-12 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1277 | LATER | DE(STG) | SAU4005-G010-MAA-&MDC-04117 | ST(V) - O&M MANUAL - STEAM TURBINE & AUXILIARIES | A1 | COMMISSIONING | M-Mechanical engineering (normally including process engineering) | YES | COMMISSIONING | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-10-01 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1278 | LATER | DE(STG) | SAU4005-G010-MKA-&MDC-04118 | ST(V) - O&M MANUAL - GENERATOR & AUXILIARIES | A1 | COMMISSIONING | M-Mechanical engineering (normally including process engineering) | YES | COMMISSIONING | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-10-01 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO
|  | 1279 | LATER | DE(STG) | SAU4005-G010-MKC-&EDD-04225 | ST(V) - PSS STUDY REPORT_EXCITATION SYSTEM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2027-11-01 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | YES | NO | SEC
|  | 1280 | LATER | DE(STG) | SAU4005-G010-MAA-&MDA-04031 | ST(V) - TECHNICAL DATA SHEET - STEAM TURBINE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-08-28 |  | 2025-09-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | YES | C2 | NO
|  | 1281 | LATER | DE(STG) | SAU4005-G010-MKA-&MDA-04108 | ST(V) - GENERATOR DATA SHEET AND CHARACTERISTIC CURVES | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFA | IFP |  |  | 2025-06-16 |  | 2025-10-01 |  | 2025-09-17 |  | 2025-10-22 |  | 2025-10-23 |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | YES | C2 | NO
|  | 1282 | LATER | DE(STG) | SAU4005-G010-MAA-&MDD-04120 | ST(V) - HAZARDOUS AREA CLASSIFICATION FOR STG PACKAGES | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | COMMISSIONING |  | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-04-25 |  | 2026-04-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1283 | LATER | DE(STG) | SAU4005-G010-MKB-&ELU-04112 | ST(V) - GENERATOR CURRENT TRANSFORMER ASSEMBLY | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-11-04 |  | 2025-11-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1284 | LATER | DE(STG) | SAU4005-G010-MKA-&ELU-04179 | ST(V) - GENERATOR SHAFT GROUNDING BRUSH RIGGING ASSEMBLY | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-11-04 |  | 2026-01-23 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1285 | LATER | DE(STG) | SAU4005-G010-MAA-&MDB-04231 | ST(V) - SYSTEM DESCRIPTION - FORCED COOLING AIR SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-07-08 |  | 2025-07-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1286 | LATER | DE(STG) | SAU4005-G010-MAX-&MDB-04057 | ST(V) - SYSTEM DESCRIPTION - HYDRAULIC POWER UNIT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-08-22 |  | 2025-09-17 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1287 | LATER | DE(STG) | SAU4005-G010-MAV-&EDA-04063 | ST(V) - PUMP & MOTOR DATA SHEET - JACKING OIL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-11-15 |  | 2026-01-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1288 | LATER | DE(STG) | SAU4005-G010-MAX-&EDA-04435 | ST(V) - PUMP & MOTOR DATA SHEET - HYDRAULIC POWER UNIT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFP | [14 empty] | 2025-11-15 |  | 2025-12-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1289 | LATER | DE(STG) | SAU4005-G010-MAA-&EPC-04314 | ST(V) – CABLE LIST - STEAM TURBINE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-12-31 |  | 2026-01-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1290 | LATER | DE(STG) | SAU4005-G010-MAV-&MDB-04121 | ST(V) - SYSTEM DESCRIPTION - JACKING OIL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-10-30 |  | 2025-11-12 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
|  | 1291 | LATER | DE(STG) | SAU4005-G010-MAK-&MDA-04122 | ST(V) - MOTOR DATA SHEET - ST TURNING GEAR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2025-10-31 |  | 2025-11-12 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | NO | NO | NO | NO | NO
| NEW | 1292 | LATER | DE(STG) | SAU4005-G010-MAY-&EFF-04123 | ST(V) - STEAM TURBINE CONTROL LOGIC DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | COMMISSIONING | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-01-30 |  | 2026-04-08
| NEW | 1293 | LATER | DE(STG) | SAU4005-G010-MAY-&EDD-04124 | ST(V) - STCS ALARM LIST | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | COMMISSIONING | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-01-30 |  | 2026-03-31
| NEW | 1294 | LATER | DE(STG) | SAU4005-G010-MAA-&MDA-04320 | ST(V) - NOISE DATA FOR STG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | COMMISSIONING | MECHANICAL | DOOSAN | STG | IFI | IFD | [14 empty] | 2026-01-30 |  | 2026-01-16
| NEW | 1295 | LATER | DE(STG) | SAU4005-G010-MAA-&MPD-04326 | ST(V) - EQUIPMENT LIST - STEAM TURBINE GENERATOR & AUXILIARIES | A1 | Engineering |  |  |  |  | DOOSAN | STG | IFI | [15 empty] | 2026-03-03 |  | 2026-03-03
| NEW | 1296 | LATER | DE(STG) | SAU4005-G010-MAV-&ELU-04125 | ST(V) - DATA SHEET – MOBILE OIL PURIFIER | A1 | Engineering |  |  |  |  | DOOSAN | STG | IFI | [15 empty] | 2026-05-29
| NEW | 1297 | LATER | DE(STG) | SAU4005-G010-MAV-&ELU-04126 | ST(V) - OUTLINE – MOBILE OIL PURIFIER | A1 | Engineering |  |  |  |  | DOOSAN | STG | IFI | [15 empty] | 2026-05-29
| DCC changed | 1298 | LATER | DE(STG) | SAU4005-G010-MKA-&MDA-04106 | ST(V) - SHIPPING DIMENSIONS - GENERATOR ROTOR | A1 | Engineering |  |  |  |  | DOOSAN | STG | IFI | [15 empty] | 2026-01-15 |  | 2026-04-09
| NEW |  | LATER | DE(STG) | SAU4005-G010-MAA-&MLU-04127 | ST(V) - STEAM TURBINE NAME PLATE | A1 | Engineering |  |  |  |  | DOOSAN | STG | IFI | [15 empty] | 2026-06-10
| NEW |  | LATER | DE(STG) | SAU4005-G010-MAG-&EDA-04128 | ST(V) - INSTRUMENT DATASHEET - GLAND STEAM CONDENSER | A1 | Engineering |  |  |  |  | DOOSAN | STG | IFI | [15 empty] | 2026-06-01 |  | 2026-06-02
|  | 1299 | LATER | MHDB | SAU4005-G011-H__-&MDD-04803 | HRSG(V) - Design Life Analysis Report | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2026-01-13 |  | 2025-12-23 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1300 | LATER | MHDB | SAU4005-G011-H__-&MDA-04804 | HRSG(V) - Degradation Curve | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-06-14 |  | 2025-04-15 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1301 | LATER | MHDB | SAU4005-G011-H__-&MDA-04805 | HRSG(V) - Start-up Curve | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-06-14 |  | 2025-05-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1302 | LATER | MHDB | SAU4005-G011-H__-&MDA-04806 | HRSG(V) - Design Report for Insulation (HRSG Internal) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-06-14 |  | 2025-05-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1303 | LATER | MHDB | SAU4005-G011-H__-&MDD-04807 | HRSG(V) - Design Report for Insulation of Piping and Equipments (HRSG External) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-06-14 |  | 2025-05-08 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1304 | LATER | MHDB | SAU4005-G011-H__-&MDA-04809 | HRSG(V) - Design Report for Noise Protection (Silencer Caluculation) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-06-14 |  | 2025-05-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1305 | LATER | MHDB | SAU4005-G011-CJF-&MDB-04811 | HRSG(V) - System Description | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-06-14 |  | 2025-05-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1306 | LATER | MHDB | SAU4005-G011-HAB-&MFB-04812 | HRSG(V) - P&I Diagram | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFD |  |  | 2025-05-29 |  | 2025-04-29 |  | 2025-05-19 |  | 2025-07-28 |  | 2025-06-24 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1307 | LATER | MHDB | SAU4005-G011-H__-&MDB-04813 | HRSG(V) - HRSG Blowdown System Summary | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-05-29 |  | 2025-04-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1308 | LATER | MHDB | SAU4005-G011-UHB-&MED-04814 | HRSG(V) - Strength Calculation for HRSG Steel Structure | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-13 |  | 2025-10-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1309 | LATER | MHDB | SAU4005-G011-UHB-&MED-04815 | HRSG(V) - Strength Calculation Report for HRSG Stack | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-13 |  | 2025-10-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1310 | LATER | MHDB | SAU4005-G011-HAA-&MED-04816 | HRSG(V) - ASME Strength Calculation Sheet for Drum (with Deaerator) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-09-13 |  | 2025-07-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1311 | LATER | MHDB | SAU4005-G011-HAA-&MED-04817 | HRSG(V) - ASME Strength Calculation Sheet for Blowdown Tank | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-09-13 |  | 2025-08-20 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1312 | LATER | MHDB | SAU4005-G011-HAA-&MED-04818 | HRSG(V) - ASME Strength Calculation Sheets for Header | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-14 |  | 2025-06-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1313 | LATER | MHDB | SAU4005-G011-HAA-&MED-04819 | HRSG(V) - ASME Strength Calculation for Link | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-14 |  | 2025-07-15 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1314 | LATER | MHDB | SAU4005-G011-HAA-&MED-04820 | HRSG(V) - ASME Strength Calculation for Tube | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-07-30 |  | 2025-06-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
| Document number changed | 1315 | LATER | MHDB | SAU4005-G011-UHA-&MLH-04821 | HRSG(V) - Pressure Part Arrangement | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFP |  |  | 2025-07-15 |  | 2026-03-27 |  | 2025-07-05 |  | 2026-02-18 |  | 2025-08-10 |  | 2026-04-13 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1316 | LATER | MHDB | SAU4005-G011-HAA-&MDD-04822 | HRSG(V) - Assembly Drawing of Steam Drum | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-13 |  | 2025-09-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1317 | LATER | MHDB | SAU4005-G011-HAA-&MDD-04823 | HRSG(V) - Detail of External Attachment of Steam Drum | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-13 |  | 2025-10-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1318 | LATER | MHDB | SAU4005-G011-HAA-&MDD-04824 | HRSG(V) - Internal Assembly Drawing of Steam Drum | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-13 |  | 2025-10-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1319 | LATER | MHDB | SAU4005-G011-HAA-&MDD-04825 | HRSG(V) - HP Steam Drum Name Plate Detail | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-12-15 |  | 2025-09-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1320 | LATER | MHDB | SAU4005-G011-HAA-&MLU-04826 | HRSG(V) - Typical Drawing for Drum Insulation | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-12-15 |  | 2025-09-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1321 | LATER | MHDB | SAU4005-G011-HAA-&MLB-04827 | HRSG(V) - Foundation Loading & Location Drawing for Blowdown Tank | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-06-14 |  | 2025-04-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1322 | LATER | MHDB | SAU4005-G011-HAA-&MLU-04828 | HRSG(V) - Equipment Outline Drawing for Blowdown Tank | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-13 |  | 2025-08-20 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1323 | LATER | MHDB | SAU4005-G011-HAA-&MLU-04829 | HRSG(V) - Link Assembly Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-12-15 |  | 2025-11-13 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1324 | LATER | MHDB | SAU4005-G011-HAN-&MLU-04830 | HRSG(V) - Vent & Drain Line (Module /Field weld) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-12-14 |  | 2025-10-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1325 | LATER | MHDB | SAU4005-G011-H__-&MDA-04831 | HRSG(V) - Data & BOM of Insulation for Piping | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2026-01-14 |  | 2025-11-06 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1326 | LATER | MHDB | SAU4005-G011-H__-&MDA-04832 | HRSG(V) - Calculation of each Drum Volume | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-06-14 |  | 2025-05-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1327 | LATER | MHDB | SAU4005-G011-H__-&MDD-04835 | HRSG(V) - HRSG CFD Report | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFD |  |  | 2025-07-30 |  | 2025-08-14 |  | 2025-07-20 |  | 2025-08-31 |  | 2025-08-09 |  | 2026-01-04 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1328 | LATER | MHDB | SAU4005-G011-HAX-&MDA-04837 | HRSG(V) - Desuperheater Data Sheet & Drawings | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-13 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1329 | LATER | MHDB | SAU4005-G011-LCQ-&MDA-04838 | HRSG(V) - Spec. & Drawing for Blowdown Tank Pump | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-13 |  | 2025-10-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1330 | LATER | MHDB | SAU4005-G011-LBF-&MDA-04839 | HRSG(V) - Spec. & Drawing for Safety & Relief Valve | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-13 |  | 2025-08-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1331 | LATER | MHDB | SAU4005-G011-HNE-&MDA-04840 | HRSG(V) - Spec. & Drawing for Stack Damper | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-13 |  | 2025-10-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1332 | LATER | MHDB | SAU4005-G011-LBF-&MDA-04841 | HRSG(V) - Spec. & Drawing for Vent Silencer | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-14 |  | 2025-08-13 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1333 | LATER | MHDB | SAU4005-G011-HAA-&MLU-04842 | HRSG(V) - Spec. & Drawing for Deaerator | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-14 |  | 2025-07-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1334 | LATER | MHDB | SAU4005-G011-HNE-&MDA-04843 | HRSG(V) - Spec. & Drawing for Stack Silencer | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-14 |  | 2025-08-13 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1335 | LATER | MHDB | SAU4005-G011-HAY-&MDA-04844 | HRSG(V) - Spec. & Drawing for Boiler Stress Evaluator System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-13 |  | 2025-11-11 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1336 | LATER | MHDB | SAU4005-G011-H__-&MFB-04845 | HRSG(V) - P&ID for Diverter & Guillotine Damper | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFD |  |  | 2025-08-01 |  | 2025-07-03 |  | 2025-07-22 |  | 2025-07-17 |  | 2025-08-27 |  | 2025-12-25 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1337 | LATER | MHDB | SAU4005-G011-H__-&MDB-04846 | HRSG(V) - System Description for Diverter & Guillotine Damper | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-07-15 |  | 2025-06-10 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1338 | LATER | MHDB | SAU4005-G011-H__-&MLB-04847 | HRSG(V) - Foundation Drawing including Loading Data for Diverter & Guillotine Damper | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-07-15 |  | 2025-06-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1339 | LATER | MHDB | SAU4005-G011-H__-&MLB-04848 | HRSG(V) - Fan Skid Drawing including Foundation and Loading Data with specification for Diverter & Guillotine Damper | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-06-14 |  | 2025-04-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1340 | LATER | MHDB | SAU4005-G011-H__-&MDB-04850 | HRSG(V) - HPU Specification & Drawing for Diverter & Guillotine Damper | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-06-14 |  | 2025-05-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1341 | LATER | MHDB | SAU4005-G011-H__-&MDB-04851 | HRSG(V) - Hoist Specification & Drawing for Diverter & Guillotine Damper | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-30 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1342 | LATER | MHDB | SAU4005-G011-H__-&MDB-04852 | HRSG(V) - Platform for Access Door for Diverter Damper | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-13 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1343 | LATER | MHDB | SAU4005-G011-SMH-&MDA-04853 | HRSG(V) - Spec. & Drawing for Hoist | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-13 |  | 2025-10-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1344 | LATER | MHDB | SAU4005-G011-LCP-&MDA-04854 | HRSG(V) - Spec. & Drawing for Recirculation Pump | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-14 |  | 2025-08-13 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1345 | LATER | MHDB | SAU4005-G011-UHB-&MTL-04855 | HRSG(V) - Non-Metallic Expansion Joint | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-14 |  | 2025-08-13 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1346 | LATER | MHDB | SAU4005-G011-H__-&MTB-04856 | HRSG(V) - Name Plate Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFP |  |  | 2025-09-13 |  | 2025-08-22 |  | 2025-09-03 |  | 2025-07-28 |  | 2025-10-09 |  | 2025-10-30 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1347 | LATER | MHDB | SAU4005-G011-UHB-&CTL-04858 | HRSG(V) - Foundation Load Table for HRSG Steel Structure and Stack | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-06-14 |  | 2025-04-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1348 | LATER | MHDB | SAU4005-G011-UHB-&CTL-04859 | HRSG(V) - Base Plate and Anchor Bolts Detail for HRSG (Steel Structure) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-06-29 |  | 2025-04-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1349 | LATER | MHDB | SAU4005-G011-UHB-&CTL-04860 | HRSG(V) - Base Plate and Anchor Bolts Detail for HRSG Auxiliary Steel Structure | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-06-13 |  | 2025-05-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1350 | LATER | MHDB | SAU4005-G011-UHB-&MTL-04862 | HRSG(V) - Typical Platform Detail for HRSG Steel Structure | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-14 |  | 2025-07-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1351 | LATER | MHDB | SAU4005-G011-UHB-&MTL-04863 | HRSG(V) - Typical Handrail Detail for HRSG Steel Structure | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-14 |  | 2025-07-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1352 | LATER | MHDB | SAU4005-G011-UHB-&MTL-04864 | HRSG(V) - Typical Ladder Detail for HRSG Steel Structure | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-14 |  | 2025-07-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1353 | LATER | MHDB | SAU4005-G011-UHB-&MTL-04865 | HRSG(V) - Arrangement for HRSG Platform Structure | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-14 |  | 2025-07-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1354 | LATER | MHDB | SAU4005-G011-UHB-&MTL-04866 | HRSG(V) - Arrangement for HRSG Canpoy Structure | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFP |  |  | 2025-08-14 |  | 2025-08-14 |  | 2025-08-04 |  | 2025-07-28 |  | 2025-08-24 |  | 2025-12-08 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1355 | LATER | MHDB | SAU4005-G011-UHA-&MLH-04867 | HRSG(V) - General Arrangement | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFP |  |  | 2025-05-29 |  | 2025-05-12 |  | 2025-05-19 |  | 2025-11-27 |  | 2025-06-08 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1356 | LATER | MHDB | SAU4005-G011-UHB-&MTL-04868 | HRSG(V) - Arrangement of Casing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-07-30 |  | 2025-07-15 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1357 | LATER | MHDB | SAU4005-G011-UHB-&MTL-04869 | HRSG(V) - Arrangement of Inlet Duct | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFP |  |  | 2025-07-30 |  | 2025-07-15 |  | 2025-07-20 |  | 2025-07-28 |  | 2025-08-09 |  | 2025-10-30 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1358 | LATER | MHDB | SAU4005-G011-UHB-&MTL-04870 | HRSG(V) - Arrangement of Main Stack | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFP |  |  | 2025-07-30 |  | 2025-07-15 |  | 2025-07-20 |  | 2025-07-28 |  | 2025-08-09 |  | 2025-12-08 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1359 | LATER | MHDB | SAU4005-G011-UHB-&MTL-04871 | HRSG(V) - Arrangement of Bypass Stack | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFP |  |  | 2025-05-29 |  | 2025-06-17 |  | 2025-05-19 |  | 2025-07-01 |  | 2025-06-08 |  | 2025-12-07 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1360 | LATER | MHDB | SAU4005-G011-UHB-&MTL-04872 | HRSG(V) - General Arrangement Drawing for Diverter & Guillotine Damper | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFP |  |  | 2025-07-15 |  | 2025-07-15 |  | 2025-07-05 |  | 2025-07-29 |  | 2025-07-25 |  | 2025-12-04 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1361 | LATER | MHDB | SAU4005-G011-HA_-&MDA-04874 | HRSG(V) - Stress Analysis Isometric Drawing for Critical Piping | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-13 |  | 2025-09-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1362 | LATER | MHDB | SAU4005-G011-HA_-&MDA-04875 | HRSG(V) - Erection Isometric Drawing for PIPNG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-13 |  | 2025-09-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1363 | LATER | MHDB | SAU4005-G011-HB_-&MDA-04876 | HRSG(V) - Pipe Support Drawing for Piping (Large Bore / Small Bore) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2026-01-13 |  | 2025-12-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1364 | LATER | MHDB | SAU4005-G011-HB_-&MDA-04877 | HRSG(V) - Typical Support Drawing for Small Bore Piping | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2026-01-13 |  | 2025-09-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1365 | LATER | MHDB | SAU4005-G011-HA_-&MTL-04878 | HRSG(V) - Large Bore Piping Arrangement of HRSG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2026-01-13 |  | 2025-11-06 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1366 | LATER | MHDB | SAU4005-G011-HA_-&MPA-04879 | HRSG(V) - Manual Valve List and ASSEMBLY Drawing for HRSG Piping | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2026-01-13 |  | 2025-10-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1367 | LATER | MHDB | SAU4005-G011-HA_-&MPA-04880 | HRSG(V) - Specialty List and Drawing for HRSG Piping | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2026-01-13 |  | 2025-10-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1368 | LATER | MHDB | SAU4005-G011-HA_-&MEC-04881 | HRSG(V) - Piping Material Classification (for HRSG) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-13 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1370 | LATER | MHDB | SAU4005-G011-HA_-&MPD-04883 | HRSG(V) - Line List | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-07-30 |  | 2025-07-15 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1371 | LATER | MHDB | SAU4005-G011-HA_-&MPL-04885 | HRSG(V) - Terminal Point List | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-07-15 |  | 2025-06-10 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1372 | LATER | MHDB | SAU4005-G011-HYA-&EDB-04886 | HRSG(V) - Control Description | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFA | IFD |  |  | 2025-07-15 |  | 2025-06-10 |  | 2025-07-05 |  | 0 |  | 2025-07-25 |  | 2025-11-23 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1373 | LATER | MHDB | SAU4005-G011-HYA-&EFB-04887 | HRSG(V) - System Configuration Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-14 |  | 2025-07-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1374 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04890 | HRSG(V) - MOV List | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-07-30 |  | 2025-07-15 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1375 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04891 | HRSG(V) - Control Valve List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-07-30 |  | 2025-07-15 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1376 | LATER | MHDB | SAU4005-G011-HYA-&EPC-04892 | HRSG(V) - Instrument List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-07-14 |  | 2025-07-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1377 | LATER | MHDB | SAU4005-G011-HYA-&EFF-04893 | HRSG(V) - Control Logic Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-09-13 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1378 | LATER | MHDB | SAU4005-G011-HYA-&EFF-04894 | HRSG(V) - Control Loop Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-09-13 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1379 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04895 | HRSG(V) - MOV Data Sheet/Drawings | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-13 |  | 2025-10-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1380 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04896 | HRSG(V) - Control Valve Data Sheet/Drawings | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFA | IFD |  |  | 2025-11-13 |  | 2025-09-26 |  | 2025-11-03 |  | 0 |  | 2025-12-09 |  | 2025-10-12 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1381 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04898 | HRSG(V) - Drum Level Gauge Datasheet/Drawings | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-13 |  | 2025-09-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1382 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04899 | HRSG(V) - Flow Element Datasheet and Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-12-15 |  | 2025-10-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1383 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04901 | HRSG(V) - Local Gauge and Temp. Element Specification | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-13 |  | 2025-10-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1384 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04902 | HRSG(V) - Transmiter Speicification | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-13 |  | 2025-10-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1385 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04903 | HRSG(V) - Remote Drum Level Indicator Datasheet/Drawings | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFA | IFD |  |  | 2025-11-13 |  | 2025-11-11 |  | 2025-11-03 |  | 2025-07-28 |  | 2025-12-09 |  | 2026-03-23 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1386 | LATER | MHDB | SAU4005-G011-HYA-&EMA-04904 | HRSG(V) - Wiring Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-13 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1387 | LATER | MHDB | SAU4005-G011-HYA-&EMB-04905 | HRSG(V) - I&C Cable schedule | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-13 |  | 2025-09-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1388 | LATER | MHDB | SAU4005-G011-HYA-&EFP-04906 | HRSG(V) - DCS I/O List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-07-15 |  | 2025-06-10 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1389 | LATER | MHDB | SAU4005-G011-HYA-&EFP-04907 | HRSG(V) - Alarm Set Point List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-06-14 |  | 2025-05-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1390 | LATER | MHDB | SAU4005-G011-HYA-&EEC-04908 | HRSG(V) - Utility Consumption List | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-05-29 |  | 2025-04-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1391 | LATER | MHDB | SAU4005-G011-HYA-&EFF-04910 | HRSG(V) - Start-up & Shut-down Sequence Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-13 |  | 2025-09-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1392 | LATER | MHDB | SAU4005-G011-HYA-&EEC-04911 | HRSG(V) - Aircraft Warning Light Data sheet / layout diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-13 |  | 2025-11-10 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1393 | LATER | MHDB | SAU4005-G011-HYA-&ELD-04912 | HRSG(V) - Instrument Location & Conduit Plan Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-13 |  | 2025-11-13 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1394 | LATER | MHDB | SAU4005-G011-HYA-&ELD-04914 | HRSG(V) - Instrument Installation Detail Drawings | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-07-15 |  | 2025-06-10 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1395 | LATER | MHDB | SAU4005-G011-HYA-&ELU-04915 | HRSG(V) - Local Panel Assembly Drawing for Diverter & Guillotine Damper | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-30 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1396 | LATER | MHDB | SAU4005-G011-HYA-&EMA-04916 | HRSG(V) - Instrument Hook-up for Diverter & Guillotine Damper | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-13 |  | 2025-10-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1397 | LATER | MHDB | SAU4005-G011-HYA-&EMA-04917 | HRSG(V) - Wiring and Terminal Connection Diagram for Diverter & Guillotine Damper | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-13 |  | 2025-11-11 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1398 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04918 | HRSG(V) - Valve List for Diverter & Guillotine Damper | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-30 |  | 2025-08-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1399 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04919 | HRSG(V) - Instrument List for Diverter & Guillotine Damper | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-30 |  | 2025-08-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1400 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04920 | HRSG(V) - Instrument Data Sheet for Diverter & Guillotine Damper | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-13 |  | 2025-09-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1401 | LATER | MHDB | SAU4005-G011-HYA-&EFQ-04921 | HRSG(V) - Alarm and Trip Setting List for Diverter & Guillotine Damper | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-09-30 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1402 | LATER | MHDB | SAU4005-G011-HYA-&EFF-04922 | HRSG(V) - Control Logic Diagram for Diverter & Guillotine Damper | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-09-30 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1403 | LATER | MHDB | SAU4005-G011-HYA-&EDB-04923 | HRSG(V) - Control Configurtion for Diverter Damper | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-09-14 |  | 2025-08-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1404 | LATER | MHDB | SAU4005-G011-HYA-&EDB-04924 | HRSG(V) - PLC Specificatoin for Diverter Damper | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-14 |  | 2025-07-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1405 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04925 | HRSG(V) - PLC I/O List for Diverter Damper (include Datalink IO list) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-09-14 |  | 2025-08-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1406 | LATER | MHDB | SAU4005-G011-HYA-&EFC-04926 | HRSG(V) - PLC HMI Drawing for Diverter Damper | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-14 |  | 2025-07-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1407 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04927 | HRSG(V) - Control Cabinet Drawing for Diverter Damper (include Schematic and Wiring Diagram) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-13 |  | 2025-09-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1408 | LATER | MHDB | SAU4005-G011-HNE-&EDA-04929 | HRSG(V) - SPEC. & Drawing for CEMS | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-13 |  | 2025-11-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1409 | LATER | MHDB | SAU4005-G011-HNE-&ELU-04930 | HRSG(V) - Foundation drawing for CEMS Room | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-07-14 |  | 2025-05-27 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1410 | LATER | MHDB | SAU4005-G011-HYA-&ELU-04931 | HRSG(V) - General Arrangement drawing for CEMS Room | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-07-14 |  | 2025-05-27 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1411 | LATER | MHDB | SAU4005-G011-HYA-&ELB-04932 | HRSG(V) - Nozzle Orientation and Cable Route Drawing for CEMS | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-13 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1412 | LATER | MHDB | SAU4005-G011-HYA-&EDB-04933 | HRSG(V) - Equipment Specification for CEMS | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-13 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1413 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04934 | HRSG(V) - Instrument List and Data Sheet for CEMS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-09-13 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1414 | LATER | MHDB | SAU4005-G011-HYA-&EDB-04935 | HRSG(V) - Contol Configuration for CEMS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-09-13 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1415 | LATER | MHDB | SAU4005-G011-HYA-&EFQ-04936 | HRSG(V) - Alarm and Trip Setting List for for CEMS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-09-13 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1416 | LATER | MHDB | SAU4005-G011-HYA-&EMA-04937 | HRSG(V) - Wiring and Terminal Connection Diagram for CEMS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-13 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1417 | LATER | MHDB | SAU4005-G011-HYA-&ELB-04938 | HRSG(V) - Earthing Concept | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-05-29 |  | 2025-04-10 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1418 | LATER | MHDB | SAU4005-G011-HYA-&EPC-04939 | HRSG(V) - Electrical Load List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-05-29 |  | 2025-04-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1419 | LATER | MHDB | SAU4005-G011-HYA-&ELD-04940 | HRSG(V) - Grounding and Lightning Plan Diagrams | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-14 |  | 2025-07-17 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1420 | LATER | MHDB | SAU4005-G011-HYA-&EFA-04941 | HRSG(V) - Electrical Single Line Diagrams | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFA | IFD |  |  | 2025-06-14 |  | 2025-05-22 |  | 2025-06-04 |  | 2025-08-31 |  | 2025-06-24 |  | 2026-02-04 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1421 | LATER | MHDB | SAU4005-G011-HYA-&EEC-04942 | HRSG(V) - Power Distribution Panel Drawings | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-13 |  | 2025-08-20 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1422 | LATER | MHDB | SAU4005-G011-HYA-&EEC-04943 | HRSG(V) - Lighting Plan Diagrams | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-09-13 |  | 2025-08-20 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1423 | LATER | MHDB | SAU4005-G011-HYA-&EEC-04944 | HRSG(V) - Lighting and Small Power Distribution Panel Drawings | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-13 |  | 2025-08-20 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1424 | LATER | MHDB | SAU4005-G011-HYA-&EEC-04945 | HRSG(V) - Junction Box/Cabinet Layout and Stanchion Layout Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-13 |  | 2025-08-20 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1425 | LATER | MHDB | SAU4005-G011-HYA-&EED-04946 | HRSG(V) - Power Cable Schedule | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-13 |  | 2025-08-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1426 | LATER | MHDB | SAU4005-G011-HNE-&EMA-04947 | HRSG(V) - Power Cable Connection Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-13 |  | 2025-08-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1427 | LATER | MHDB | SAU4005-G011-HYA-&ELD-04948 | HRSG(V) - Cable Tray & Raceway Layout Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-13 |  | 2025-08-20 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1428 | LATER | MHDB | SAU4005-G011-HYA-&EEC-04949 | HRSG(V) - CABLE SPECIFICATION | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-13 |  | 2025-08-20 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1429 | LATER | MHDB | SAU4005-G011-HYA-&EDB-04952 | HRSG(V) - Conduit Plan | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-13 |  | 2025-08-20 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1430 | LATER | MHDB | SAU4005-G011-HYA-&EMA-04953 | HRSG(V) - Single Line Diagram for Diverter & Guillotine Damper | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-09-14 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1431 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04954 | HRSG(V) - Cable Schedule for Diverter & Guillotine Damper | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-14 |  | 2025-08-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1432 | LATER | MHDB | SAU4005-G011-HNY-&MFQ-04958 | HRSG(V) - Alarm and Trip Setting List for SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-09-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1433 | LATER | MHDB | SAU4005-G011-HNY-&MMB-04959 | HRSG(V) - Cable Interconnection Diagram for SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-29 |  | 2025-09-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1434 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04960 | HRSG(V) - Cable List for SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-29 |  | 2025-09-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1435 | LATER | MHDB | SAU4005-G011-HNY-&MLU-04961 | HRSG(V) - Cable Tray & Conduit Drawing for SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-29 |  | 2025-11-10 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1436 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04962 | HRSG(V) - Control Logic & Loop for SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-10-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1437 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04963 | HRSG(V) - Control Valve Data Sheet & Drawings for SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-13 |  | 2025-10-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1438 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04964 | HRSG(V) - Catalyst Data Sheet & Drawings for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-29 |  | 2025-11-06 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1439 | LATER | MHDB | SAU4005-G011-HNY-&MED-04965 | HRSG(V) - Equipment Calculation Sheet for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-14 |  | 2025-07-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1440 | LATER | MHDB | SAU4005-G011-HNY-&MLU-04966 | HRSG(V) - General Arrangement Drawing of Ammonia Storage Area for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFP |  |  | 2025-08-14 |  | 2025-08-13 |  | 2025-08-04 |  | 2025-07-28 |  | 2025-08-24 |  | 2025-12-24 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1441 | LATER | MHDB | SAU4005-G011-HNY-&MLU-04967 | HRSG(V) - General arrangement Drawing of Internal Part for SCR (with AIG and Catalyst Frame & Sealing Arrangement) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-07-15 |  | 2025-06-11 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1442 | LATER | MHDB | SAU4005-G011-HNY-&MLU-04968 | HRSG(V) - Dilution Tank Drawing for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-14 |  | 2025-07-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1443 | LATER | MHDB | SAU4005-G011-HNY-&MLU-04969 | HRSG(V) - Vaporizer Arrangement Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-14 |  | 2025-07-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1444 | LATER | MHDB | SAU4005-G011-HNY-&MLU-04970 | HRSG(V) - Ammonia Distribution Header Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-14 |  | 2025-08-19 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1445 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04971 | HRSG(V) - Hot Gas Circulation Fan Data Sheet and Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-14 |  | 2025-08-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1446 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04972 | HRSG(V) - Ammonia Supply Pump Data Sheet and Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-14 |  | 2025-08-13 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1447 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04973 | HRSG(V) - Ammonia Unloading Pump Data Sheet and Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-14 |  | 2025-08-13 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1448 | LATER | MHDB | SAU4005-G011-HNY-&MLD-04974 | HRSG(V) - Instrument Hook-up for SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-29 |  | 2025-09-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1449 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04975 | HRSG(V) - Instrument Data Sheet for SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-10-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1450 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04976 | HRSG(V) - Instrument List for SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-29 |  | 2025-10-23 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1451 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04977 | HRSG(V) - INSTRUMENT LOCATION FOR SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-29 |  | 2025-10-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1452 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04978 | HRSG(V) - SPECIAL ITEM LIST AND DRAWING FOR SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-29 |  | 2025-09-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1453 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04979 | HRSG(V) - Piping Isometric Drawing for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-13 |  | 2025-09-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1454 | LATER | MHDB | SAU4005-G011-HNY-&MLU-04980 | HRSG(V) - Piping Layout Drawing for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-13 |  | 2025-09-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1455 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04981 | HRSG(V) - Piping Support Drawing for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-13 |  | 2025-09-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1456 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04982 | HRSG(V) - Line List for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-30 |  | 2025-08-13 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1457 | LATER | MHDB | SAU4005-G011-HNY-&MFB-04983 | HRSG(V) - P&ID for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFD |  |  | 2025-08-14 |  | 2025-05-23 |  | 2025-08-04 |  | 2025-06-09 |  | 2025-09-09 |  | 2026-01-04 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1458 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04984 | HRSG(V) - Junction Box Drawing for SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-29 |  | 2025-09-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1459 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04985 | HRSG(V) - Local Panel Drawing for SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-29 |  | 2025-09-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1460 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04987 | HRSG(V) - Electrical and I&c BOM for SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-29 |  | 2025-10-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1461 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04988 | HRSG(V) - Process Mass Balance for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-14 |  | 2025-07-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1462 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04989 | HRSG(V) - System Description for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFD |  |  | 2025-08-14 |  | 2025-07-21 |  | 2025-08-04 |  | 2025-08-05 |  | 2025-08-24 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1463 | LATER | MHDB | SAU4005-G011-HNY-&MDB-04990 | HRSG(V) - Technical Specification for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-14 |  | 2025-07-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1464 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04991 | HRSG(V) - Valve List for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-14 |  | 2025-07-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1465 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04992 | HRSG(V) - Valve Drawing for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-13 |  | 2025-11-13 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1466 | LATER | MHDB | SAU4005-G011-HNE-&EDA-04993 | HRSG(V) - SPEC. & Drawing of Analyzer for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-29 |  | 2026-03-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1467 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04994 | HRSG(V) - CFD Report for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-13 |  | 2025-10-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1468 | LATER | MHDB | SAU4005-G011-HNY-&MDA-04998 | HRSG(V) - I/O List for SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-14 |  | 2025-07-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1469 | LATER | MHDB | SAU4005-G011-HHA-&MFQ-05000 | HRSG(V) - Alarm and Trip Setting List for Duct Burner | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-14 |  | 2025-06-10 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1470 | LATER | MHDB | SAU4005-G011-HHA-&MMB-05001 | HRSG(V) - Cable Interconnection Diagram for Duct Burner | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-29 |  | 2025-08-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1471 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05002 | HRSG(V) - Cable List for Duct Burner | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-29 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1472 | LATER | MHDB | SAU4005-G011-HHA-&MTA-05003 | HRSG(V) - Cable Tray & Conduit Drawing for Duct Burner | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-29 |  | 2025-08-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1473 | LATER | MHDB | SAU4005-G011-HHA-&MMB-05004 | HRSG(V) - Control Logic & Loop for Duct Burner | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-29 |  | 2025-07-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1474 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05005 | HRSG(V) - Control Valve Data Sheet & Drawings for Duct Burner | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-29 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1475 | LATER | MHDB | SAU4005-G011-HHA-&MFB-05006 | HRSG(V) - P&ID for Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFD |  |  | 2025-11-29 |  | 2025-09-16 |  | 2025-11-19 |  | 2025-10-01 |  | 2025-12-25 |  | 2026-03-15 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1476 | LATER | MHDB | SAU4005-G011-HHA-&MDB-05007 | HRSG(V) - System Description for Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-29 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1477 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05008 | HRSG(V) - General Arrangement for Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFP |  |  | 2025-08-29 |  | 2025-08-21 |  | 2025-08-19 |  | 2025-07-28 |  | 2025-09-08 |  | 2025-12-07 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1478 | LATER | MHDB | SAU4005-G011-HHA-&MLB-05009 | HRSG(V) - Foundation Drawing for Duct Burner | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-07-14 |  | 2025-04-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1479 | LATER | MHDB | SAU4005-G011-HHA-&MLU-05010 | HRSG(V) - Fuel Gas Skid Arrangement Drawing for Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFP |  |  | 2025-08-29 |  | 2025-08-25 |  | 2025-08-19 |  | 2025-07-28 |  | 2025-09-08 |  | 2026-03-15 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1480 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05012 | HRSG(V) - Cooling Air Fan Data Sheet for Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-30 |  | 2025-08-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1481 | LATER | MHDB | SAU4005-G011-HHA-&MLD-05013 | HRSG(V) - Instrument Hook-up for Duct Burner | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-29 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1482 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05014 | HRSG(V) - Instrument Data Sheet for Duct Burner | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-29 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1483 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05015 | HRSG(V) - Instrument List for Duct Burner | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-29 |  | 2025-08-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1484 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05016 | HRSG(V) - Piping Isometric Drawing for Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-29 |  | 2025-08-08 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1485 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05017 | HRSG(V) - Piping Layout Drawing for Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-29 |  | 2025-06-12 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1486 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05018 | HRSG(V) - Piping Support Drawing for Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-29 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1487 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05019 | HRSG(V) - Line List for Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-17 |  | 2025-07-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1488 | LATER | MHDB | SAU4005-G011-HHA-&MLU-05020 | HRSG(V) - Junction Box Drawing for Duct Burner | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-29 |  | 2025-08-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1489 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05021 | HRSG(V) - Local Panel / Control Panel Drawing for Duct Burner | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-29 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1490 | LATER | MHDB | SAU4005-G011-HHA-&MDB-05022 | HRSG(V) - Technical Specification for Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-29 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1491 | LATER | MHDB | SAU4005-G011-HHA-&MFF-05023 | HRSG(V) - BMS Control Logic Diagram & Flow Chart | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-29 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1492 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05024 | HRSG(V) - BMS Cause and Effect Chart | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-29 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1493 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05025 | HRSG(V) - BMS Control Narrative | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-29 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1494 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05026 | HRSG(V) - BMS Communication List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-29 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1495 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05027 | HRSG(V) - BMS HMI Graphic | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-29 |  | 2025-07-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1496 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05028 | HRSG(V) - BMS TMR Configuration | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-29 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1497 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05029 | HRSG(V) - I/O List for DUCT BURNER | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-29 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1498 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05030 | HRSG(V) - Valve List for Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-29 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1499 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05031 | HRSG(V) - Valve Drawing for Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-29 |  | 2025-07-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1500 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05032 | HRSG(V) - SPEC. & Drawing of Flame Scanner for Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-29 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1501 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05033 | HRSG(V) - SPEC. & Drawing of Ignition Burner for Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-29 |  | 2025-08-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1502 | LATER | MHDB | SAU4005-G011-ZEN-&MDC-05040 | HRSG(V) - HRSG_Painting Specification | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-10-02 |  | 2025-09-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1503 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05034 | HRSG(V) - Hazardous Area Classification Specification & Drawing for Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-08-29 |  | 2025-08-11 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1504 | LATER | MHDB | SAU4005-G011-QLA-&MDA-05054 | HRSG(V) - Water Quality Standard | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-05-29 |  | 2025-04-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1505 | LATER | MHDB | SAU4005-G011-HNY-&MDA-05058 | HRSG(V) - Material Safety Data Sheet for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2026-01-13 |  | 2025-10-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1506 | LATER | MHDB | SAU4005-G011-H__-&MDA-05061 | HRSG(V) - Stack size calculation | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2026-01-13 |  | 2025-10-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1507 | LATER | MHDB | SAU4005-G011-H__-&MED-05063 | HRSG(V) - Blowdown tank size calculation sheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-12-14 |  | 2025-08-20 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1509 | LATER | MHDB | SAU4005-G011-___-&BAB-05068 | HRSG(V) - Equipment List | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-07-15 |  | 2025-06-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1510 | LATER | MHDB | SAU4005-G011-HAA-&MTC-05071 | HRSG(V) - Internal Tray Enclosure Detail for Deaerator | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-13 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1511 | LATER | MHDB | SAU4005-G011-HAA-&MTC-05072 | HRSG(V) - Internal Spray Header Detail for Deaerator | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-09-13 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1512 | LATER | MHDB | SAU4005-G011-HAA-&MED-05074 | HRSG(V) - Strength Calculation for Deaerator | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-09-13 |  | 2025-08-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1514 | LATER | MHDB | SAU4005-G011-UHB-&MTL-05085 | HRSG(V) - Arrangement of Casing Flow Baffle | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2026-01-13 |  | 2025-09-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1516 | LATER | MHDB | SAU4005-G011-SND-&MDA-05089 | HRSG(V) - Elevator Data Sheet and Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-12-15 |  | 2025-10-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1517 | LATER | MHDB | SAU4005-G011-QMA-&MDA-05090 | HRSG(V) - Dehumidifier Data Sheet and Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-12-15 |  | 2025-10-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1518 | LATER | MHDB | SAU4005-G011-HNY-&MLU-05092 | HRSG(V) - AIG, Catalyst Frame & Sealing Arrangement Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-13 |  | 2025-11-10 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1519 | LATER | MHDB | SAU4005-G011-HNY-&MDA-05093 | HRSG(V) - SCR Performance Summary | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-13 |  | 2025-09-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1520 | LATER | MHDB | SAU4005-G011-HHA-&MDA-05096 | HRSG(V) - BMS IO List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-06-14 |  | 2025-06-10 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1522 | LATER | MHDB | SAU4005-G011-UHB-&MTL-05101 | HRSG(V) - Outside Insulation & Lagging for HRSG Main Stack | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2026-01-14 |  | 2025-11-06 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
| DCC changed | 1523 | LATER | MHDB | SAU4005-G011-HNY-&EDA-05102 | HRSG(V) - Lighting System for SCR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-29 |  | 2026-04-23 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1525 | LATER | MHDB | SAU4005-G011-UHB-&MED-05104 | HRSG(V) - Strength Calculation for Lifting Device | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-12-15 |  | 2025-09-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1526 | LATER | MHDB | SAU4005-G011-HYA-&EFB-05105 | HRSG(V) - Cable Block Diagram for HRSG | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-13 |  | 2025-10-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1527 | LATER | MHDB | SAU4005-G011-HNE-&EPC-05106 | HRSG(V) - CEMS Electrical Load List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-11-10 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1528 | LATER | MHDB | SAU4005-G011-HNE-&EFB-05107 | HRSG(V) - CEMS P&ID | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFD |  |  | 2025-11-29 |  | 2025-09-26 |  | 2025-11-19 |  | 2025-09-03 |  | 2025-12-25 |  | 2025-11-16 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1529 | LATER | MHDB | SAU4005-G011-HNE-&EFA-05108 | HRSG(V) - CEMS Network Architecture | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-09-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1530 | LATER | MHDB | SAU4005-G011-HNE-&EDB-05109 | HRSG(V) - CEMS System structure Diagram | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-09-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1531 | LATER | MHDB | SAU4005-G011-HNE-&ETB-05110 | HRSG(V) - CEMS Flange Installation Diagram | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-09-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1532 | LATER | MHDB | SAU4005-G011-HNE-&ELU-05111 | HRSG(V) - General Arrangement Drawing for Analyzer Cabinet. | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFA | IFP |  |  | 2025-11-29 |  | 2025-09-26 |  | 2025-11-19 |  | 2025-10-09 |  | 2025-12-25 |  | 2025-11-19 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1533 | LATER | MHDB | SAU4005-G011-HNE-&EPA-05112 | HRSG(V) - CEMS Cable list | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-11-29 |  | 2025-09-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1534 | LATER | MHDB | SAU4005-G011-HNE-&EFP-05115 | HRSG(V) - CEMS I/O Signals exchange List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-09-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1535 | LATER | MHDB | SAU4005-G011-HNE-&EFB-05117 | HRSG(V) - CEMS Single Line Diagram for Power Distribution | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-09-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1536 | LATER | MHDB | SAU4005-G011-UHB-&MTL-05122 | HRSG(V) - Embedded Material Calculation for HRSG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFP | [14 empty] | 2025-06-07 |  | 2025-05-09 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1537 | LATER | MHDB | SAU4005-G011-HB_-&MEC-05070 | HRSG(V) - STEEL STRUCTURE MATERIAL SPECIFICATION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-08-02 |  | 2025-06-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1538 | LATER | MHDB | SAU4005-G011-UHB-&MTL-05123 | HRSG(V) - Embedded Material Calculation for Bypass Stack | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-09-05 |  | 2025-07-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1539 | LATER | MHDB | SAU4005-G011-H__-&MDA-05127 | HRSG(V) - Dispersion Study | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-10-25 |  | 2025-09-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1540 | LATER | MHDB | SAU4005-G011-UHB-&MDB-04861 | HRSG(V) - General NOTE For HRSG Steel Structure | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-21 |  | 2025-10-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1541 | LATER | MHDB | SAU4005-G011-HYA-&EDA-04955 | HRSG(V) - Motor Data Sheet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-21 |  | 2025-10-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1542 | LATER | MHDB | SAU4005-G011-HNY-&MLU-05128 | HRSG(V) - Assembly Drawing for Ammonia Unloading Area Shed | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-21 |  | 2025-10-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1543 | LATER | MHDB | SAU4005-G011-HNY-&MLU-05129 | HRSG(V) - Measurement Socket Drawing for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-21 |  | 2025-10-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1544 | LATER | MHDB | SAU4005-G011-HNY-&MLU-05130 | HRSG(V) - Metal Parts for SCR Piping Insulation | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-21 |  | 2025-10-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1545 | LATER | MHDB | SAU4005-G011-HNY-&MLU-05131 | HRSG(V) - Piping Insulation Drawing for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-21 |  | 2025-10-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1546 | LATER | MHDB | SAU4005-G011-HNY-&MLU-05132 | HRSG(V) - Metal Parts for SCR Equipment Insulation | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-21 |  | 2025-10-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1547 | LATER | MHDB | SAU4005-G011-HNY-&MLU-05133 | HRSG(V) - Equipment Insulation Drawing for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-21 |  | 2025-10-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1548 | LATER | MHDB | SAU4005-G011-HNY-&MLU-05135 | HRSG(V) - Grounding and Lightning Drawing for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-21 |  | 2025-10-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1549 | LATER | MHDB | SAU4005-G011-HYA-&ELD-05136 | HRSG(V) - Grounding and Lightning Drawing for Bypass Stack | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-11-21 |  | 2025-10-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1550 | LATER | MHDB | SAU4005-G011-HHA-&MDD-05035 | HRSG(V) - CFD Report For Duct Burner | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-12-28 |  | 2025-11-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1551 | LATER | MHDB | SAU4005-G011-UHB-&MTL-05138 | HRSG(V) - METALLIC EXPANSION JOINT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2025-12-28 |  | 2025-11-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1552 | LATER | MHDB | SAU4005-G011-UHB-&MTL-05139 | HRSG(V) - Non-Metallic Expansion Joint for Piping | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2026-02-06 |  | 2026-01-07
| NEW | 1553 | LATER | MHDB | SAU4005-G011-H__-&MDD-04884 | HRSG(V) - FEM Analysis | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2026-02-13 |  | 2026-02-25
| NEW | 1554 | LATER | MHDB | SAU4005-G011-HNY-&MDA-05147 | HRSG(V) – Hot Gas Circulation Fan VFD Drawing for SCR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2026-02-13 |  | 2026-01-29
| NEW | 1555 | LATER | MHDB | SAU4005-G011-H__-&MDD-05141 | HRSG(V) – HP, RH Section Dissimilar Metal Weld Analysis Report | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2026-02-13 |  | 2026-01-29
| NEW | 1556 | LATER | MHDB | SAU4005-G011-HYA-&MDA-05151 | HRSG(V) - Manual Valve Data Sheet and Drawings | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2026-03-11 |  | 2026-03-10
| NEW | 1562 | LATER | MHDB | SAU4005-G011-HYA-&EDA-05137 | HRSG(V) - Main Steam Valve Data Sheet and Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2026-03-11 |  | 2026-03-10
| NEW | 1563 | LATER | MHDB | SAU4005-G011-HYA-&EEC-05153 | HRSG(V) - Lighting Plan Diagrams for Bypass Stack | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | DOOSAN | HRSG | IFI | IFD | [14 empty] | 2026-03-18 |  | 2026-03-16
|  | 1564 | LATER | MPW | SAU4005-G000-___-&BBD-03041 | GT(V) - PLANT IDENTIFICATION NUMBERING SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-25 |  | 2025-07-02 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA
|  | 1565 | LATER | MPW | SAU4005-G000-___-&MEC-03040 | GT(V) - PAINTING SPECIFICATION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-25 |  | 2025-07-02 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1566 | LATER | MPW | SAU4005-G011-MBN-&MTA-03045 | GT(V) - OUTLINE OF GT FUEL OIL & FLOW DIVIDER UNIT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-25 |  | 2025-04-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1567 | LATER | MPW | SAU4005-G011-MBP-&MTA-03044 | GT(V) - OUTLINE OF FUEL GAS UNIT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-25 |  | 2025-05-08 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1568 | LATER | MPW | SAU4005-G011-MBL-&MTL-03046 | GT(V) - GENERAL ARRANGEMENT OF GT AIR INTAKE SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-25 |  | 2025-04-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1569 | LATER | MPW | SAU4005-G011-MBR-&MTL-03047 | GT(V) - GENERAL ARRANGEMENT OF GT EXHAUST SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-25 |  | 2025-04-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1570 | LATER | MPW | SAU4005-G000-___-&MPD-03043 | GT(V) - EQUIPMENT LIST | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-25 |  | 2025-07-02 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1571 | LATER | MPW | SAU4005-G000-___-&BBD-03042 | GT(V) - LIST OF APPLICABLE UNIT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-25 |  | 2025-07-02 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1572 | LATER | MPW | SAU4005-G000-___-&MFB-03039 | GT(V) - P&I DIAGRAM LEGEND | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-25 |  | 2025-07-02 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1573 | LATER | MPW | SAU4005-G011-MBV-&MFB-03000 | GT(V) - LUBE OIL SYSTEM P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-28 |  | 2025-04-28 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1574 | LATER | MPW | SAU4005-G011-MBN-&MFB-03004 | GT(V) - FUEL OIL SYSTEM P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-28 |  | 2025-04-28 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1575 | LATER | MPW | SAU4005-G011-MBP-&MFB-03009 | GT(V) - FUEL GAS SYSTEM P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-28 |  | 2025-04-28 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1576 | LATER | MPW | SAU4005-G011-MBP-&MFB-03016 | GT(V) - FUEL GAS SYSTEM(FUEL GAS FLOW METER) P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-25 |  | 2025-04-28 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1577 | LATER | MPW | SAU4005-G011-MBP-&MFB-03017 | GT(V) - FUEL GAS SYSTEM(FUEL GAS LAST CHANCE FILTER) P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-25 |  | 2025-04-28 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1578 | LATER | MPW | SAU4005-G000-MBP-&MFB-03037 | GT(V) - FUEL GAS SYSTEM(FUEL GAS CALORIE METER) P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-25 |  | 2025-04-28 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1579 | LATER | MPW | SAU4005-G011-MBH-&MFB-03018 | GT(V) - AIR AND FLUE GAS SYSTEM P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-28 |  | 2025-04-28 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1580 | LATER | MPW | SAU4005-G011-SDD-&MFB-03024 | GT(V) - GT WASHING & DRAIN SYSTEM P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-28 |  | 2025-04-28 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1581 | LATER | MPW | SAU4005-G011-MBA-&MFB-03026 | GT(V) - PROTECTION SYSTEM P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-25 |  | 2025-04-28 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1582 | LATER | MPW | SAU4005-G011-QFF-&MFB-03029 | GT(V) - GT CASING COOLING AIR SYSTEM P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-25 |  | 2025-04-28 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1583 | LATER | MPW | SAU4005-G011-QFF-&MFB-03027 | GT(V) - GT INSTRUMENT AIR SYSTEM P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-28 |  | 2025-04-28 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1584 | LATER | MPW | SAU4005-G011-SDD-&MFB-03038 | GT(V) - GT INLET AIR COOLING(HIGH FOGGING)SYSTEM P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-25 |  | 2025-04-28 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1585 | LATER | MPW | SAU4005-G011-QEE-&MFB-03030 | GT(V) - GT PURGE AIR SYSTEM P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-25 |  | 2025-04-28 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1586 | LATER | MPW | SAU4005-G011-MBU-&MFB-03031 | GT(V) - GT WATER INJECTION SYSTEM P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-28 |  | 2025-04-28 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1587 | LATER | MPW | SAU4005-G011-PGG-&MFB-03033 | GT(V) - COOLING WATER SYSTEM FOR GT P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-25 |  | 2025-04-28 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1588 | LATER | MPW | SAU4005-G011-LAB-&MFB-03034 | GT(V) - GT FUEL GAS HEATER & GT COOLING AIR COOLER SYSTEM P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-25 |  | 2025-04-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1589 | LATER | MPW | SAU4005-G011-MBH-&MFB-03035 | GT(V) - ENHANCED COOLING AIR SYSTEM P&I DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-28 |  | 2025-04-28 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1590 | LATER | MPW | SAU4005-G011-MB_-&MTA-03053 | GT(V) - PIPING TERMINAL POINTS FOR GAS TURBINE PACKAGE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-25 |  | 2025-04-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1591 | LATER | MPW | SAU4005-G000-CJP-&EFB-03058 | GT(V) - TYPICAL LOGIC DIAGRAM FOR AUXILIARIES (GT PORTION) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-25 |  | 2025-05-08 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1592 | LATER | MPW | SAU4005-G000-CAA-&EFE-03059 | GT(V) - GENERAL DESCRIPTION OF GT UNIT INTERLOCK | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-25 |  | 2025-04-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1593 | LATER | MPW | SAU4005-G000-CAA-&EFB-03061 | GT(V) - GAS TURBINE UNIT INTERLOCK DIAGRAM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-25 |  | 2025-04-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1594 | LATER | MPW | SAU4005-G000-CJP-&EFB-03062 | GT(V) - GAS TURBINE GOVERNOR CONTROL DIAGRAM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-25 |  | 2025-04-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1595 | LATER | MPW | SAU4005-G000-___-&MTL-03067 | GT(V) - OVERHAUL PARTS DRAWING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-25 |  | 2025-06-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1596 | LATER | MPW | SAU4005-G000-___-&BBD-03051 | GT(V) - UTILITY LIST | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-25 |  | 2025-07-02 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1597 | LATER | MPW | SAU4005-G011-BFJ-&EFS-03050 | GT(V) - KEY SINGLE LINE DIAGRAM FOR GT AUXILIARIES | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-25 |  | 2025-04-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1598 | LATER | MPW | SAU4005-G011-BFJ-&EFF-03101 | GT(V) - TYPICAL SCHEMATIC DIAGRAM FOR ELECTRICAL PANEL | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-25 |  | 2025-04-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1599 | LATER | MPW | SAU4005-G011-BFJ-&EFB-03102 | GT(V) - LOGIC DIAGRAM FOR ELECTRICAL CONTROL SYSTEM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-05-25 |  | 2025-04-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1600 | LATER | MPW | SAU4005-G000-MB_-&MDA-03103 | GT(V) - DESIGN NOTE FOR GT FOUNDATION | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-25 |  | 2025-04-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1601 | LATER | MPW | SAU4005-G000-CJP-&EFE-03060 | GT(V) - DESCRIPTION OF GAS TURBINE CONTROL | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-25 |  | 2025-04-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1602 | LATER | MPW | SAU4005-G011-MB_-&MTA-03065 | GT(V) - ROUTE PLAN OF PIPING AROUND FUEL OIL & FLOW DIVIDER UNIT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-06-13 |  | 2025-05-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1603 | LATER | MPW | SAU4005-G011-MB_-&MTA-03064 | GT(V) - ARRANGEMENT OF PLATFORM AROUND GAS TURBINE & GENERATOR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-06-13 |  | 2025-06-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1604 | LATER | MPW | SAU4005-G011-MB_-&MTA-03055 | GT(V) - ARRANGEMENT OF PLATFORM AROUND GT LUBE OIL RESERVOIR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-06-13 |  | 2025-06-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1605 | LATER | MPW | SAU4005-G011-SGJ-&MTA-03138 | GT(V) - BASIC DESIGN OF FIRE PROTECTION SYSTEM IN GAS TURBINE PACKAGE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-13 |  | 2025-05-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1606 | LATER | MPW | SAU4005-G011-MB_-&MTA-03066 | GT(V) - ARRANGEMENT OF GAS TURBINE, GENERATOR & AUXILIARY EQUIPMENT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-06-13 |  | 2025-05-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1607 | LATER | MPW | SAU4005-G011-MB_-&MTA-03189 | GT(V) - TURBINE & GENERATOR FOUNDATION DRAWINGS | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-06-13 |  | 2025-04-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1608 | LATER | MPW | SAU4005-G011-MB_-&MTA-03104 | GT(V) - AUXILIARY EQUIPMENT FOUNDATION DRAWINGS | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-06-13 |  | 2025-04-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1609 | LATER | MPW | SAU4005-G011-MB_-&MTA-03105 | GT(V) - AROUND GT UNIT FOUNDATION DRAWINGS | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-06-13 |  | 2025-04-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1610 | LATER | MPW | SAU4005-G000-___-&MMA-03205 | GT(V) - CONTRACT INTERFACE LIST | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-13 |  | 2025-07-02 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1611 | LATER | MPW | SAU4005-G000-___-&MEC-03206 | GT(V) - WASTE WATER LIST | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-13 |  | 2025-07-02 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1612 | LATER | MPW | SAU4005-G000-___-&EEC-03214 | GT(V) - HEAT LOAD LIST | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-13 |  | 2025-07-02 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1613 | LATER | MPW | SAU4005-G011-___-&BDB-03135 | GT(V) - HAZARDOUS AREA CLASSIFICATION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-13 |  | 2025-07-02 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1614 | LATER | MPW | SAU4005-G011-LAB-&MDB-03056 | GT(V) - DESIGN PHILOSOPHY FOR TCA COOLER FEEDWATER SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-08-15 |  | 2025-07-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1615 | LATER | MPW | SAU4005-G011-LAB-&MDB-03057 | GT(V) - DESIGN PHILOSOPHY FOR FGH FEED WATER SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-13 |  | 2025-05-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1616 | LATER | MPW | SAU4005-G000-CRV-&EDB-03258 | GT(V) - CONTROL SYSTEM CONFIGURATION | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-06-13 |  | 2025-05-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1617 | LATER | MPW | SAU4005-G000-CJP-&EFA-03274 | GT(V) - HARDWARE SPECIFICATION OF CONTROL SYSTEM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-13 |  | 2025-04-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1618 | LATER | MPW | SAU4005-G011-BJF-&EPC-03052 | GT(V) - ELECTRICAL LOAD LIST | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-13 |  | 2025-05-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1619 | LATER | MPW | SAU4005-G011-BFJ-&EFS-03199 | GT(V) - SINGLE LINE DIAGRAM FOR MOTOR CONTROL CENTER | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-06-13 |  | 2025-05-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1620 | LATER | MPW | SAU4005-G011-BTA-&EFS-03191 | GT(V) - SINGLE LINE DIAGRAM FOR DC SYSTEM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-06-13 |  | 2025-05-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1621 | LATER | MPW | SAU4005-G011-BJA-&EFS-03196 | GT(V) - SINGLE LINE DIAGRAM FOR AC DISTRIBUTION PANEL | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-06-13 |  | 2025-05-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1622 | LATER | MPW | SAU4005-G011-MB_-&MTA-03179 | GT(V) - OUTLINE OF GT TURNING DEVICE ENCLOSURE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-06-13 |  | 2025-05-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1623 | LATER | MPW | SAU4005-G000-CJP-&ELU-03276 | GT(V) - OUTLINE OF GT CONTROL SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-06-22 |  | 2025-12-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1624 | LATER | MPW | SAU4005-G000-CAA-&EED-03296 | GT(V) - OUTLINE OF SAFETY PLC PANEL | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-06-22 |  | 2025-05-20 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1625 | LATER | MPW | SAU4005-G000-CWQ-&EED-03255 | GT(V) - OUTLINE OF CPFA SERVER CABINET | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-06-22 |  | 2025-05-20 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1626 | LATER | MPW | SAU4005-G011-MBP-&MDA-03110 | GT(V) - GT FUEL GAS HEATER SECTIONAL ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-06-29 |  | 2025-06-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1627 | LATER | MPW | SAU4005-G011-MBH-&MDA-03119 | GT(V) - GT COOLING AIR COOLER SECTIONAL ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-06-29 |  | 2025-06-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1628 | LATER | MPW | SAU4005-G011-MBR-&MTA-03154 | GT(V) - TERMINAL FLANGE OF GT EXHAUST DUCT & HRSG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-06-29 |  | 2025-06-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1629 | LATER | MPW | SAU4005-G000-CAA-&EFE-03295 | GT(V) - SPECIFICATION OF SAFETY PLC | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-05 |  | 2025-12-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1630 | LATER | MPW | SAU4005-G000-CMB-&EFA-03260 | GT(V) - SPECIFICATION OF COMMUNICATION CABLE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-05 |  | 2025-06-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1631 | LATER | MPW | SAU4005-G000-CMB-&EFA-03261 | GT(V) - SPECIFICATION OF OPC COMMUNICATION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-05 |  | 2025-06-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1632 | LATER | MPW | SAU4005-G000-CJP-&EFA-03275 | GT(V) - SPECIFICATION OF A-CPFM/CPFM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-05 |  | 2025-05-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1633 | LATER | MPW | SAU4005-G000-___-&BDD-03247 | GT(V) - HAZOP STUDY REPORT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-11 |  | 2025-06-11 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 1634 | LATER | MPW | SAU4005-G000-___-&BDD-03248 | GT(V) - SIL STUDY REPORT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-11 |  | 2025-06-11 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 1635 | LATER | MPW | SAU4005-G000-___-&EEC-03213 | GT(V) - MOTOR LIST | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-11 |  | 2025-06-11 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1636 | LATER | MPW | SAU4005-G000-MBA-&CTB-03303 | GT(V) - ARRANGEMENT OF TEMPLATE DWG FOR GT POWER TRAIN | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-07-18 |  | 2025-06-10 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1637 | LATER | MPW | SAU4005-G011-___-&MDA-03122 | GT(V) - PNEUMATIC CONTROL VALVE DWG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-07-18 |  | 2025-06-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1638 | LATER | MPW | SAU4005-G011-MBP-&MDA-03157 | GT(V) - ELECTRIC CONTROL VALVE DWG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-07-18 |  | 2025-06-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1639 | LATER | MPW | SAU4005-G011-MBN-&MDA-03161 | GT(V) - GT FLOW DIVIDER DWG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-07-18 |  | 2025-06-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1640 | LATER | MPW | SAU4005-G011-MBN-&MDA-03162 | GT(V) - MAIN FUEL OIL PUMP DWG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-07-18 |  | 2025-06-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1641 | LATER | MPW | SAU4005-G011-MBU-&MDA-03152 | GT(V) - WATER INJECTION PUMP DWG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-07-18 |  | 2025-06-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1642 | LATER | MPW | SAU4005-G011-QEE-&MDA-03141 | GT(V) - PURGE AIR COMPRESSOR(MECHANICAL) DWG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-07-18 |  | 2025-06-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1643 | LATER | MPW | SAU4005-G011-QEE-&MDA-03142 | GT(V) - PURGE AIR RECEIVER DWG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-07-18 |  | 2025-06-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1644 | LATER | MPW | SAU4005-G011-MBH-&MDA-03174 | GT(V) - GT ENHANCED COOLING AIR COMPRESSOR(MECHANICAL) DWG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-07-18 |  | 2025-06-19 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1645 | LATER | MPW | SAU4005-G011-MBP-&MDA-03158 | GT(V) - GT FUEL GAS LAST CHNACE FILTER DWG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-07-18 |  | 2025-06-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1646 | LATER | MPW | SAU4005-G011-___-&MPC-03107 | GT(V) - VALVE LIST FOR HEAT EXCHANGER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-18 |  | 2025-06-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1647 | LATER | MPW | SAU4005-G000-___-&MEC-03207 | GT(V) - Thermal Insulation Specification | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-18 |  | 2025-06-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1648 | LATER | MPW | SAU4005-G011-BFJ-&EED-03200 | GT(V) - STUDY OF ELECTRICAL CONSUMPTION AND BUS CAPACITY FOR MCC | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-06-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1649 | LATER | MPW | SAU4005-G011-BTA-&EED-03192 | GT(V) - STUDY OF DC SYSTEM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-06-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1650 | LATER | MPW | SAU4005-G011-MBR-&MTA-03153 | GT(V) - LOADING DATA OF GT EXHAUST SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-06-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1651 | LATER | MPW | SAU4005-G011-MBR-&MTA-03155 | GT(V) - FOUNDATION OUTLINE OF GT EXHAUST DUCT | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-07-25 |  | 2025-04-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1652 | LATER | MPW | SAU4005-G011-MBR-&MTA-03156 | GT(V) - ARRANGEMENT OF EARTH TERMINAL AROUND GT EXHAUST SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-07-25 |  | 2025-06-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1653 | LATER | MPW | SAU4005-G011-MBL-&MTA-03165 | GT(V) - LOADING DATA OF GT AIR INTAKE SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-08-01 |  | 2025-07-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1654 | LATER | MPW | SAU4005-G011-MBL-&MTA-03168 | GT(V) - FOUNDATION OUTLINE OF GT AIR INTAKE SYSTEM | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-08-01 |  | 2025-07-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1655 | LATER | MPW | SAU4005-G000-CMB-&EFE-03262 | GT(V) - SPECIFICATION OF SECURITY CONTROL SYSTEM(NPP) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-08-01 |  | 2025-12-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1656 | LATER | MPW | SAU4005-G011-MB_-&MTA-03180 | GT(V) - ROUTE PLAN OF PIPING AROUND GT UNIT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-08-08 |  | 2025-07-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1657 | LATER | MPW | SAU4005-G011-MB_-&MTA-03183 | GT(V) - ROUTE PLAN OF GAS TURBINE COOLING AIR PIPING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-08-08 |  | 2025-07-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1658 | LATER | MPW | SAU4005-G011-MB_-&MTA-03184 | GT(V) - ROUTE PLAN OF PRESSURE PIPING FOR EXHAUST DUCT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-08-08 |  | 2025-07-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1659 | LATER | MPW | SAU4005-G011-MB_-&MTA-03185 | GT(V) - ROUTE PLAN OF EXHAUST DUCT DRAIN PIPING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-08-08 |  | 2025-07-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1660 | LATER | MPW | SAU4005-G011-MB_-&MTA-03186 | GT(V) - ROUTE PLAN OF GT CASING COOLING AIR PIPING (LOCAL) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-08-08 |  | 2025-07-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1661 | LATER | MPW | SAU4005-G011-MB_-&MTA-03187 | GT(V) - ROUTE PLAN OF 4S COOLING AIR PIPING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-08-08 |  | 2025-07-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1662 | LATER | MPW | SAU4005-G011-___-&MDB-03121 | GT(V) - SYSTEM DESCRIPTION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-08-08 |  | 2025-07-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1663 | LATER | MPW | SAU4005-G011-QFF-&MDB-03140 | GT(V) - DESIGN PHILOSOPHY FOR EMERGENCY AIR SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-08-08 |  | 2025-07-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1664 | LATER | MPW | SAU4005-G000-CFA-&EEC-03279 | GT(V) - SPECIFICATION OF SPEED PICK UP | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-08-08 |  | 2025-07-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1665 | LATER | MPW | SAU4005-G000-CFA-&EEC-03280 | GT(V) - SPECIFICATION OF PRESSURE TRANSMITTER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-08-08 |  | 2025-07-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1666 | LATER | MPW | SAU4005-G000-CFA-&EEC-03283 | GT(V) - SPECIFICATION OF FUEL GAS FLOW METER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-08-08 |  | 2025-07-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1667 | LATER | MPW | SAU4005-G000-CFA-&EEC-03287 | GT(V) - SPECIFICATION OF PRESSURE GAUGE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-08-08 |  | 2025-07-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1668 | LATER | MPW | SAU4005-G000-CFA-&EEC-03289 | GT(V) - SPECIFICATION OF SOLENOID VALVE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-08-08 |  | 2025-07-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1669 | LATER | MPW | SAU4005-G000-CJP-&EFB-03273 | GT(V) - GAS TURBINE GENERAL LOGIC DIAGRAM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-08-15 |  | 2025-07-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1670 | LATER | MPW | SAU4005-G011-MBV-&MDA-03112 | GT(V) - GT LUBE OIL COOLER SECTIONAL ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-08-15 |  | 2025-07-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1671 | LATER | MPW | SAU4005-G011-BJA-&EDB-03198 | GT(V) - SPECIFICATION OF AC/DC DISTRIBUTION PANEL | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-08-22 |  | 2025-07-17 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1672 | LATER | MPW | SAU4005-G000-___-&CTC-03216 | GT(V) - OUTLINE OF TERMINAL BOX (FUEL UNIT) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-08-22 |  | 2025-07-17 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1673 | LATER | MPW | SAU4005-G011-QEE-&EDA-03143 | GT(V) - PURGE AIR COMPRESSOR(ELECTRICAL) DWG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-08-22 |  | 2025-08-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1674 | LATER | MPW | SAU4005-G011-MBH-&EDA-03175 | GT(V) - GT ENHANCED COOLING AIR COMPRESSOR(ELECTRICAL) DWG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-08-22 |  | 2025-07-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1675 | LATER | MPW | SAU4005-G011-SDD-&MDA-03139 | GT(V) - COMPRESSOR WASHING DEVICE DWG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-08-22 |  | 2025-07-17 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1676 | LATER | MPW | SAU4005-G000-CAA-&EFS-03294 | GT(V) - SCHEMATIC DIAGRAM OF SAFETY PLC PANEL | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-08-22 |  | 2025-08-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1677 | LATER | MPW | SAU4005-G000-CMB-&EED-03263 | GT(V) - OUTLINE OF NPP PANEL | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-08-22 |  | 2025-07-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1678 | LATER | MPW | SAU4005-G000-CFA-&EEC-03278 | GT(V) - SPECIFICATION OF VIBRATION MONITORING INSTRUMENT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-08-22 |  | 2025-07-17 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1679 | LATER | MPW | SAU4005-G000-CFA-&EEC-03281 | GT(V) - SPECIFICATION OF LEVEL TRANSMITTER | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-08-22 |  | 2025-07-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1680 | LATER | MPW | SAU4005-G000-CFA-&EEC-03282 | GT(V) - SPECIFICATION OF FUEL OIL FLOW METER | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-08-22 |  | 2025-07-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1681 | LATER | MPW | SAU4005-G000-CFA-&EEC-03284 | GT(V) - SPECIFICATION OF TEMPERATURE MEASURING INSTRUMENT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-08-22 |  | 2025-07-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1682 | LATER | MPW | SAU4005-G000-CFA-&EEC-03285 | GT(V) - SPECIFICATION OF FLOW ELEMENT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-08-22 |  | 2025-07-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1683 | LATER | MPW | SAU4005-G000-CFA-&EEC-03290 | GT(V) - SPECIFICATION OF AMBIENT TEMPERATURE & HUMIDITY MEASURING INSTRUMENT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-08-22 |  | 2025-07-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1684 | LATER | MPW | SAU4005-G000-CFA-&EEC-03291 | GT(V) - SPECIFICATION OF GAS DETECTOR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-08-22 |  | 2025-07-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1685 | LATER | MPW | SAU4005-G000-CFA-&EEC-03292 | GT(V) - SPECIFICATION OF CPFM SENSOR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-08-22 |  | 2025-07-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1686 | LATER | MPW | SAU4005-G000-CFA-&EEC-03293 | GT(V) - SPECIFICATION OF CALORIE METER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-08-22 |  | 2025-07-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1687 | LATER | MPW | SAU4005-G011-MBH-&MDA-03108 | GT(V) - GT COOLING AIR COOLER WITH GT FUEL GAS HEATER SECTIONAL ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-08-22 |  | 2025-07-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1688 | LATER | MPW | SAU4005-G011-MBH-&MDA-03109 | GT(V) - ENHANCED COOLING AIR COOLER SECTIONAL ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-08-22 |  | 2025-07-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1689 | LATER | MPW | SAU4005-G011-MBP-&MTA-03111 | GT(V) - INSTRUMENT PIPING FOR GT FUEL GAS HEATER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-08-22 |  | 2025-07-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1690 | LATER | MPW | SAU4005-G011-MBV-&MDA-03113 | GT(V) - THREE WAY VALVE SECTIONAL ASSEMBLY (FOR GT LUBE OIL COOLER) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-08-22 |  | 2025-07-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1691 | LATER | MPW | SAU4005-G011-MBV-&MTA-03114 | GT(V) - THREE WAY VALVE INSTALLATION DRAWING (FOR GT LUBE OIL COOLER) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-08-22 |  | 2025-07-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1692 | LATER | MPW | SAU4005-G011-MBH-&MTA-03115 | GT(V) - INSTRUMENT PIPING FOR 2C COOLER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-08-22 |  | 2025-07-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1693 | LATER | MPW | SAU4005-G011-MBH-&MDA-03116 | GT(V) - 2C COOLER SECTIONAL ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-08-22 |  | 2025-07-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1694 | LATER | MPW | SAU4005-G011-MBH-&MDA-03117 | GT(V) - 4S COOLER SECTIONAL ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-08-22 |  | 2025-07-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1695 | LATER | MPW | SAU4005-G011-QEE-&MDA-03118 | GT(V) - GT PURGE AIR COOLER SECTIONAL ASSEMBLY | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-08-22 |  | 2025-07-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1696 | LATER | MPW | SAU4005-G011-MBH-&MTA-03120 | GT(V) - GT COOLING AIR COOLER INSTRUMENT PIPING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-08-22 |  | 2025-07-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1697 | LATER | MPW | SAU4005-G011-SGJ-&MTA-03136 | GT(V) - FM200 FIRE FIGHTING SYSTEM (MECHANICAL) DRAWING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-09-12 |  | 2025-08-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1698 | LATER | MPW | SAU4005-G011-SGJ-&MTA-03137 | GT(V) - FM200 FIRE FIGHTING SYSTEM (ELECTRICAL) DRAWING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-09-12 |  | 2025-08-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1699 | LATER | MPW | SAU4005-G000-CJP-&EFP-03270 | GT(V) - DCS-GTC INTERFACE LIST(HARD-WIRED) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-09-12 |  | 2025-08-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 1700 | LATER | MPW | SAU4005-G000-CFA-&EPB-03299 | GT(V) - INSTRUMENT LIST | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-09-12 |  | 2025-08-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1701 | LATER | MPW | SAU4005-G011-MBA-&MLU-03177 | GT(V) - OUTLINE DRAWING OF LOW VOLTAGE MOTOR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-09-12 |  | 2025-08-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1702 | LATER | MPW | SAU4005-G011-MBV-&MLU-03150 | GT(V) - OUTLINE DRAWING OF DC MOTOR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-09-12 |  | 2025-08-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1703 | LATER | MPW | SAU4005-G011-BFJ-&EDB-03202 | GT(V) - SPECIFICATION OF MOTOR CONTROL CENTER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-09-12 |  | 2025-08-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1704 | LATER | MPW | SAU4005-G011-BTA-&EDB-03194 | GT(V) - SPECIFICATION OF DC SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-09-12 |  | 2025-08-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1705 | LATER | MPW | SAU4005-G011-MBL-&MTA-03166 | GT(V) - OUTLINE DRAWING OF GT AIR INTAKE FILTER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-09-28 |  | 2025-09-02 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1706 | LATER | MPW | SAU4005-G011-MBL-&MTA-03170 | GT(V) - ARRANGEMENT OF EARTH TERMINAL AROUND GT AIR INTAKE SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-09-28 |  | 2025-09-02 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1707 | LATER | MPW | SAU4005-G011-MBL-&MTA-03171 | GT(V) - OUTLINE DRAWING OF WET COMPRESSION SYSTEM PUMP SKID | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-10-23 |  | 2025-09-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1708 | LATER | MPW | SAU4005-G011-MBL-&MTA-03172 | GT(V) - ROUTE PLAN OF WET COMPRESSION SYSTEM PIPING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-10-23 |  | 2025-09-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1709 | LATER | MPW | SAU4005-G000-___-&CTA-03219 | GT(V) - OUTLINE OF INSTRUMENT MOUNTING SUPPORT (FUEL UNIT) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-09-28 |  | 2025-09-02 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1710 | LATER | MPW | SAU4005-G000-___-&CMB-03236 | GT(V) - WIRING DIAGRAM OF TERMINAL BOX (FUEL UNIT) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-09-28 |  | 2025-09-02 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1711 | LATER | MPW | SAU4005-G000-___-&CPA-03234 | GT(V) - CABLE LIST (FUEL UNIT) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-09-28 |  | 2025-09-02 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1712 | LATER | MPW | SAU4005-G011-MBV-&MTA-03149 | GT(V) - OUTLINE OF LUBE OIL RESERVOIR UNIT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-09-28 |  | 2025-09-02 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1713 | LATER | MPW | SAU4005-G011-MB_-&MTA-03181 | GT(V) - VALVE LIST FOR GAS TURBINE PART | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-10-23 |  | 2025-10-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1714 | LATER | MPW | SAU4005-G000-___-&CEC-03238 | GT(V) - SPECIFICATION OF INSTRUMENT CABLE | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-10-03 |  | 2025-09-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1715 | LATER | MPW | SAU4005-G000-___-&CTA-03222 | GT(V) - ARRANGEMENT OF CONDUIT PIPING FOR FUEL UNIT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-22 |  | 2026-01-08 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1716 | LATER | MPW | SAU4005-G000-___-&CTA-03223 | GT(V) - ARRANGEMENT OF CONDUIT PIPING FOR LIGHTING & FIRE FIGHTING SYSTEM (FUEL UNIT) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-22 |  | 2026-01-08 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1717 | LATER | MPW | SAU4005-G000-CJP-&EFS-03269 | GT(V) - SCHEMATIC DIAGRAM OF GT CONTROL SYSTEM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-10-03 |  | 2025-09-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1718 | LATER | MPW | SAU4005-G000-CMB-&EFS-03259 | GT(V) - SCHEMATIC DIAGRAM OF NPP | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-10-03 |  | 2025-09-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1719 | LATER | MPW | SAU4005-G000-MBA-&MDB-03297 | GT(V) - GAS TURBINE LONGITUDINAL SECT ASS'Y | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-10-03 |  | 2025-09-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1720 | LATER | MPW | SAU4005-G000-CJP-&EEC-03277 | GT(V) - SPECIFICATION OF GT OPS SCREENS | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-10-03 |  | 2025-04-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1721 | LATER | MPW | SAU4005-G011-MBL-&MTA-03163 | GT(V) - GT CASING COOLING FAN DWG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-10-03 |  | 2025-09-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1722 | LATER | MPW | SAU4005-G011-MBL-&MTA-03167 | GT(V) - TECHNICAL SPECIFICATION OF GT AIR INTAKE FILTER SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-10-03 |  | 2025-09-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | YES
|  | 1723 | LATER | MPW | SAU4005-G011-BLA-&ELU-03195 | GT(V) - OUTLINE DRAWING OF WALL MOUNT RECEPTACLE FOR GT BOLT HEATER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-10-17 |  | 2025-09-11 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1724 | LATER | MPW | SAU4005-G011-MBN-&MTA-03159 | GT(V) - FUEL OIL DRAIN PUMP & TANK UNIT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-10-24 |  | 2025-09-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1725 | LATER | MPW | SAU4005-G000-___-&CTA-03220 | GT(V) - IMPULSE PIPING DRAWING (FUEL UNIT) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-16 |  | 2026-01-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1726 | LATER | MPW | SAU4005-G000-___-&CTA-03221 | GT(V) - SUPPLY & CONTROL AIR TUBING DRAWING (FUEL UNIT) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-16 |  | 2026-01-08 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1727 | LATER | MPW | SAU4005-G000-___-&CTA-03224 | GT(V) - CONDUIT DIAGRAM (FUEL UNIT) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-22 |  | 2026-01-08 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1728 | LATER | MPW | SAU4005-G000-___-&CEC-03239 | GT(V) - SPECIFICATION OF LIGHTING FIXTURES | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-10-30 |  | 2025-06-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1729 | LATER | MPW | SAU4005-G000-___-&CMB-03237 | GT(V) - WIRING DIAGRAM OF TERMINAL BOX | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-11-14 |  | 2025-10-01 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1730 | LATER | MPW | SAU4005-G000-___-&CPA-03235 | GT(V) - CABLE LIST | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-11-14 |  | 2025-10-01 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1731 | LATER | MPW | SAU4005-G000-CWQ-&EFS-03253 | GT(V) - SCHEMATIC DIAGRAM OF CPFA SERVER CABINET | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-11-14 |  | 2025-10-01 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1732 | LATER | MPW | SAU4005-G011-MBV-&MTA-03148 | GT(V) - GT LUBE OIL MIST SEPARATOR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-11-14 |  | 2025-10-01 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1733 | LATER | MPW | SAU4005-G011-MBL-&ETA-03173 | GT(V) - LOCAL CONTROL PANEL, LOGIC & WIRING DIAGRAM OF GT AIR INTAKE FILTER | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-11-21 |  | 2025-10-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1734 | LATER | MPW | SAU4005-G011-BVR-&EDB-03190 | GT(V) - SPECIFICATION OF DC STARTER PANEL | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-11-21 |  | 2025-10-27 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1735 | LATER | MPW | SAU4005-G000-___-&CTC-03217 | GT(V) - OUTLINE OF TERMINAL BOX | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-11-28 |  | 2025-10-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1736 | LATER | MPW | SAU4005-G000-CJP-&EFC-03272 | GT(V) - PLAN OF OPS SCREENS | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-11-28 |  | 2025-10-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1737 | LATER | MPW | SAU4005-G011-MBV-&MTA-03144 | GT(V) - GT MAIN LUBE OIL PUMP | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-12-19 |  | 2025-10-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1738 | LATER | MPW | SAU4005-G011-MBV-&MTA-03145 | GT(V) - GT EMERGENCY LUBE OIL PUMP | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-12-19 |  | 2025-10-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1739 | LATER | MPW | SAU4005-G011-MBV-&MTA-03146 | GT(V) - GT LUBE OIL FILTER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-12-19 |  | 2025-10-01 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1740 | LATER | MPW | SAU4005-G011-MBV-&MTA-03147 | GT(V) - GT LUBE OIL ACCUMULATOR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-12-19 |  | 2025-11-20 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1741 | LATER | MPW | SAU4005-G011-MBL-&MTA-03164 | GT(V) - GAS TURBINE PACKAGE VENTILATION FAN | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-12-19 |  | 2025-11-06 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1742 | LATER | MPW | SAU4005-G000-___-&CTC-03218 | GT(V) - OUTLINE OF INSTRUMENT PANEL | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-12-26 |  | 2025-11-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1743 | LATER | MPW | SAU4005-G000-___-&CTA-03225 | GT(V) - OUTLINE OF INSTRUMENT MOUNTING SUPPORT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-03-13 |  | 2026-03-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1744 | LATER | MPW | SAU4005-G000-___-&CTA-03226 | GT(V) - IMPULSE PIPING DRAWING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-03-13 |  | 2026-03-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1745 | LATER | MPW | SAU4005-G000-___-&CTA-03227 | GT(V) - SUPPLY & CONTROL AIR TUBING DRAWING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-03-13 |  | 2026-03-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1746 | LATER | MPW | SAU4005-G000-___-&CTA-03229 | GT(V) - ARRANGEMENT OF CONDUIT PIPING FOR LIGHTING & FIRE FIGHTING SYSTEM (GT PACKAGE INTERNAL) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-03-13 |  | 2026-03-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1747 | LATER | MPW | SAU4005-G000-___-&CTL-03215 | GT(V) - LOCATION OF DETECTION POINT & INSTRUMENT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-12-26 |  | 2025-11-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1748 | LATER | MPW | SAU4005-G000-___-&CEC-03240 | GT(V) - SPECIFICATION OF HEAT TRACE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2026-03-13 |  | 2026-03-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1749 | LATER | MPW | SAU4005-G000-___-&CTA-03228 | GT(V) - ARRANGEMENT OF CONDUIT PIPING (GT PACKAGE INTERNAL) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-03-13 |  | 2026-03-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1750 | LATER | MPW | SAU4005-G011-___-&BFQ-03129 | GT(V) - CONTROL SETTING FOR GT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFD | [14 empty] | 2026-04-22 |  | 2026-04-20 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1751 | LATER | MPW | SAU4005-G000-___-&CTA-03231 | GT(V) - ARRANGEMENT OF CONDUIT PIPING (AROUND LUBE OIL UNIT) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-16 |  | 2026-01-08 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1752 | LATER | MPW | SAU4005-G000-___-&CTA-03232 | GT(V) - ARRANGEMENT OF CONDUIT PIPING (AROUND EXHAUST GAS DUCT) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-16 |  | 2026-01-08 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1753 | LATER | MPW | SAU4005-G000-___-&CTA-03230 | GT(V) - CONDUIT DIAGRAM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-03-13 |  | 2026-03-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1754 | LATER | MPW | SAU4005-G011-MB_-&MTA-03182 | GT(V) - OUTLINE DRAWING OF VALVES FOR GAS TURBINE PART | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-02-11 |  | 2026-01-08 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1755 | LATER | MPW | SAU4005-G000-CJP-&EFT-03266 | GT(V) - IDOL LOGIC DIAGRAM OF FUNCTION MODULE | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-03-06 |  | 2026-01-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1756 | LATER | MPW | SAU4005-G000-CJP-&EFT-03267 | GT(V) - CPFM LOGIC DIAGRAM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-03-06 |  | 2026-01-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1757 | LATER | MPW | SAU4005-G000-CJP-&EFT-03268 | GT(V) - CPFM GRAPHIC SCREEN | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFD | [14 empty] | 2026-03-06 |  | 2026-01-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1759 | LATER | MPW | SAU4005-G000-CKN-&EFA-03264 | GT(V) - HARDWARE SPECIFICATION OF OPERATION AND MAINTENANCE TOOL | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-13 |  | 2025-05-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1760 | LATER | MPW | SAU4005-G000-CKN-&EFA-03265 | GT(V) - SPECIFICATION OF OPERATION AND MAINTENANCE TOOL | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-13 |  | 2025-05-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1761 | LATER | MPW | SAU4005-G011-MPA-&CLB-03506 | GT(V) - GENERATOR FOUNDATION EMBEDDED METALS LAYOUT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-23 |  | 2025-04-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1762 | LATER | MPW | SAU4005-G000-MKA-&MDA-03511 | GT(V) - GENERATOR FOUNDATION BOLT ARRANGEMENT (FOR GAS TURBINE) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-23 |  | 2025-04-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1763 | LATER | MPW | SAU4005-G000-MKA-&MDA-03509 | GT(V) - GENERATOR LOAD ON FOUNDATION (FOR GAS TURBINE) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-05-23 |  | 2025-04-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1764 | LATER | MPW | SAU4005-G000-MK_-&BAB-03526 | GT(V) - PAINTING COLOR LIST FOR GTG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-29 |  | 2025-06-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1765 | LATER | MPW | SAU4005-G000-MK_-&BAC-03527 | GT(V) - PAINTING PROCEDURE FOR GTG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-29 |  | 2025-06-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1766 | LATER | MPW | SAU4005-G000-MK_-&EDA-03544 | GT(V) - GENERAL SPECIFICATION OF ELECTRICAL CONTROL PANELS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-06-29 |  | 2025-06-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1767 | LATER | MPW | SAU4005-G000-MK_-&EFA-03528 | GT(V) - SINGLE LINE DIAGRAM GENERATOR CIRCUIT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-06-29 |  | 2025-06-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1768 | LATER | MPW | SAU4005-G000-MKA-&EDA-03507 | GT(V) - GENERATOR TECHNICAL DATA SHEET | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-06-29 |  | 2025-06-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1769 | LATER | MPW | SAU4005-G000-MKA-&MDA-03508 | GT(V) - GENERATOR OUTLINE | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-06-29 |  | 2025-06-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1770 | LATER | MPW | SAU4005-G000-MKA-&MDA-03510 | GT(V) - GENERATOR TERMINAL AND C.T. ASSEMBLY | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-06-29 |  | 2025-06-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1771 | LATER | MPW | SAU4005-G000-MKA-&MDA-03512 | GT(V) - GENERATOR FIELD LEADS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-06-29 |  | 2025-06-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1772 | LATER | MPW | SAU4005-G000-MKA-&MDA-03513 | GT(V) - GENERATOR GROUT RETAINER ARRANGEMENT | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-29 |  | 2025-06-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1773 | LATER | MPW | SAU4005-G000-MKA-&MDA-03517 | GT(V) - GENERATOR METHOD OF MOUNTING | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-29 |  | 2025-06-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1774 | LATER | MPW | SAU4005-G000-MKA-&MDA-03523 | GT(V) - GENERATOR ANCHOR BLOCK ARRANGEMENT | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-29 |  | 2025-06-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1775 | LATER | MPW | SAU4005-G000-MKA-&MDA-03524 | GT(V) - GENERATOR COOLING WATER PIPING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-29 |  | 2025-06-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1776 | LATER | MPW | SAU4005-G000-MKG-&MFB-03504 | GT(V) - GENERATOR H2 & CO2 GAS SUPPLY SYSTEM DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-29 |  | 2025-06-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1777 | LATER | MPW | SAU4005-G011-MKG-&MFB-03503 | GT(V) - GENERATOR COOLING WATER DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-29 |  | 2025-06-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1778 | LATER | MPW | SAU4005-G011-MKG-&MFB-03505 | GT(V) - GENERATOR H2 & CO2 GAS DIAGRAM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-29 |  | 2025-06-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1779 | LATER | MPW | SAU4005-G011-MKV-&MFB-03502 | GT(V) - GENERATOR JACKING OIL DIAGRAM FOR GT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-29 |  | 2025-06-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1780 | LATER | MPW | SAU4005-G011-MKW-&MFB-03501 | GT(V) - GENERATOR SEAL OIL DIAGRAM FOR GT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-06-29 |  | 2025-06-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1781 | LATER | MPW | SAU4005-G000-MBA-&CDC-03304 | GT(V) - INSTALLATION PROCEDUDRE FOR THE ANCHOR BOLT & TEMPLATE FOR GT POWER TRAIN | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-07-20 |  | 2025-06-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1782 | LATER | MPW | SAU4005-G011-MB_-&MTA-03106 | GT(V) - LIFTING PROCEDURE FOR GT ROTOR & GT AUXILIARY EQUIPMENT | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | CIVIL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-06-29 |  | 2025-05-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1783 | LATER | MPW | SAU4005-G000-MK_-&EAB-03537 | GT(V) - SIGNAL INTERFACE LIST AND APPLICABLE DATA | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-09-28 |  | 2025-09-02 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1784 | LATER | MPW | SAU4005-G000-MKA-&MDA-03516 | GT(V) - GENERATOR GROUND CONNECTION TERMINALS ARRANGEMENT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-09-28 |  | 2025-09-02 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1785 | LATER | MPW | SAU4005-G000-MKC-&ELD-03625 | GT(V) - EMBEDDED METAL ARRANGEMENT OF EXCITATION BUSDUCT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-09-28 |  | 2025-09-02 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1786 | LATER | MPW | SAU4005-G000-MK_-&EFF-03551 | GT(V) - LOGIC DIAGRAM OF SFC SELECTION | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-10-11 |  | 2025-09-11 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1787 | LATER | MPW | SAU4005-G000-MKW-&EEC-03636 | GT(V) - TYPE TEST REPORT FOR GENERATOR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2025-10-11 |  | 2025-09-11 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1788 | LATER | MPW | SAU4005-G011-MB_-&MTA-03054 | GT(V) - PIPING TERMINAL POINTS FOR GT FUEL OIL & GT FLOW DIVIDER UNIT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-10-12 |  | 2025-09-15 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1789 | LATER | MPW | SAU4005-G000-MKC-&EDA-03624 | GT(V) - SECTION VIEW AND SPECIFICATION OF EXCITATION BUSDUCT FOR GTG | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-10-19 |  | 2025-09-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1790 | LATER | MPW | SAU4005-G011-MBH-&MDA-03334 | GT(V) - MOTOR OPERATED VALVE DWG FOR GT COOLING AIR LINE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-11-14 |  | 2025-10-01 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1791 | LATER | MPW | SAU4005-G011-MBH-&MTA-03338 | GT(V) - ROUTE PLAN OF GAS TURBINE ENHANCED COOLING AIR PURGE PIPING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-11-19 |  | 2025-10-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1792 | LATER | MPW | SAU4005-G011-MBH-&MTA-03332 | GT(V) - ROUTE PLAN OF GAS TURBINE ENHANCED COOLING AIR PIPING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-11-19 |  | 2025-10-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1793 | LATER | MPW | SAU4005-G000-MK_-&EFA-03529 | GT(V) - SINGLE LINE DIAGRAM FOR SFC CIRCUIT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-12-31 |  | 2025-12-01 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1794 | LATER | MPW | SAU4005-G000-MK_-&EFB-03530 | GT(V) - TRIP LOGIC DIAGRAM UNIT GENERATOR FOR GT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-12-31 |  | 2025-12-01 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1795 | LATER | MPW | SAU4005-G000-MK_-&EFF-03549 | GT(V) - LOGIC DIAGRAM OF GENERATOR CONTROL FOR GT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-12-31 |  | 2025-12-01 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1796 | LATER | MPW | SAU4005-G000-MKA-&MDA-03519 | GT(V) - GENERATOR INSTRUMENT WIRING ARRANGEMENT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-12-31 |  | 2025-12-01 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1797 | LATER | MPW | SAU4005-G000-MKA-&MDA-03522 | GT(V) - GENERATOR RATING NAME PLATE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-12-31 |  | 2025-12-01 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1798 | LATER | MPW | SAU4005-G011-___-&BDC-03134 | GT(V) - OPERATING PROCEDURE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-12-31 |  | 2025-12-01 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1799 | LATER | MPW | SAU4005-G011-MBL-&MTA-03169 | GT(V) - CHANGEOUT PROCEDURE OF FILTER ELEMENT FOR GT AIR INTAKE SYSTEM | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-12-31 |  | 2025-12-01 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1800 | LATER | MPW | SAU4005-G011-PGG-&MDA-03335 | GT(V) - COOLING TOWER DWG FOR GT HP PURGE AIR COMPRESSOR | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2025-12-31 |  | 2025-12-01 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1801 | LATER | MPW | SAU4005-G000-MK_-&EAB-03555 | GT(V) - INSTRUMENT LIST FOR GTG | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-04 |  | 2025-12-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1802 | LATER | MPW | SAU4005-G000-MKE-&EDA-03539 | GT(V) - SFC TRANSFORMER DRAWINGS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-04 |  | 2025-12-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1803 | LATER | MPW | SAU4005-G000-MKE-&EDA-03566 | GT(V) - OUTLINE OF STATIC FREQUENCY CONVERTER | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-04 |  | 2025-12-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1804 | LATER | MPW | SAU4005-G000-MKE-&EDA-03570 | GT(V) - SFC START-UP SWITCHING CUBICLE OUTLINE | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-04 |  | 2025-12-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1805 | LATER | MPW | SAU4005-G000-MKE-&EFS-03567 | GT(V) - SCHEMATIC DIAGRAM AND SPECIFICATION FOR STATIC FREQUENCY CONVERTER | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-04 |  | 2025-12-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1806 | LATER | MPW | SAU4005-G000-MKY-&EDA-03548 | GT(V) - OUTLINE DRAWING OF SFC SWITCH CIRCUIT CONTROL PANEL | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-04 |  | 2025-12-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1807 | LATER | MPW | SAU4005-G011-MKY-&EDA-03569 | GT(V) - GENERATOR NEUTRAL GROUNDING CUBICLE OUTLINE | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-04 |  | 2025-12-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1808 | LATER | MPW | SAU4005-G011-MBV-&MTA-03345 | GT(V) - GT LUBE OIL LEVEL GAUGE WITH LEVEL SWITCH | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-04 |  | 2025-12-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1809 | LATER | MPW | SAU4005-G000-MKG-&EFB-03689 | GT(V) - GENERATOR AUX. TERMINAL BLOCK ARRANGEMENT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-18 |  | 2025-12-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1811 | LATER | MPW | SAU4005-G000-MK_-&ELD-03632 | GT(V) - GENERATOR ELECTRICAL EQUIPMENT GENERAL ARRANGEMENT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-18 |  | 2025-12-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1812 | LATER | MPW | SAU4005-G000-MKY-&EDA-03545 | GT(V) - OUTLINE DRAWING OF GENERATOR PROTECTION RELAY PANEL | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-18 |  | 2025-12-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1813 | LATER | MPW | SAU4005-G000-MKY-&EDA-03546 | GT(V) - OUTLINE DRAWING OF GENERATOR CONTROL PANEL | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-18 |  | 2025-12-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1814 | LATER | MPW | SAU4005-G000-MKY-&EDA-03547 | GT(V) - OUTLINE DRAWING OF SEAL OIL CONTROL PANEL | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-18 |  | 2025-12-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1815 | LATER | MPW | SAU4005-G000-MKC-&ELD-03626 | GT(V) - ROUTE ARRANGEMENT AND INTERFACE DRAWING OF EXCITATION BUSDUCT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-18 |  | 2025-12-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1816 | LATER | MPW | SAU4005-G011-MKG-&MDA-03691 | GT(V) - GENERATOR AUX. EQUIPMENT OUTLINE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-18 |  | 2025-12-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1817 | LATER | MPW | SAU4005-G000-MKA-&MDA-03525 | GT(V) - GENERATOR MONITORING PANEL OUTLINE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-18 |  | 2025-12-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1818 | LATER | MPW | SAU4005-G000-MKC-&EDA-03541 | GT(V) - EXCITATION TRANSFORMER DRAWINGS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-18 |  | 2025-12-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1819 | LATER | MPW | SAU4005-G000-MKC-&EDA-03560 | GT(V) - EXCITATION CUBICLE OUTLINE | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-18 |  | 2025-12-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1820 | LATER | MPW | SAU4005-G000-MKC-&EDA-03561 | GT(V) - AVR CUBICLE OUTLINE | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-18 |  | 2025-12-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1821 | LATER | MPW | SAU4005-G000-MKC-&EFS-03563 | GT(V) - SPECIFICATION AND SCHEMATIC DIAGRAM EXCITATION SYSTEM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-18 |  | 2025-12-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1822 | LATER | MPW | SAU4005-G011-MBL-&ETA-03344 | GT(V) - ELECTRIAL DRAWINGS OF WET COMPRESSION SYSTEM | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-18 |  | 2025-12-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1823 | LATER | MPW | SAU4005-G011-MKG-&MDA-03531 | GT(V) - GENERATOR PIPING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-18 |  | 2025-12-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1824 | LATER | MPW | SAU4005-G011-AB_-&MTA-03343 | GT(V) - GT FO UNIT VENTILATION FAN | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-18 |  | 2025-12-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1825 | LATER | MPW | SAU4005-G011-MB_-&CTC-03514 | GT(V) - GAS TURBINE NAME PLATE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-01-18 |  | 2025-12-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
| NEW | 1826 | LATER | MPW | SAU4005-G000-CWQ-&ELU-03254 | GT(V) - OUTLINE OF LOCAL OPS DESK | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-02-12 |  | 2026-02-24
| NEW | 1827 | LATER | MPW | SAU4005-G000-CWA-&ELU-03257 | GT(V) - OUTLINE OF CCR DESK | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-02-12 |  | 2026-02-24
| NEW | 1828 | LATER | MPW | SAU4005-G000-CWQ-&EFS-03252 | GT(V) - SCHEMATIC DIAGRAM OF LOCAL OPS DESK | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-02-12 |  | 2026-02-12
| NEW | 1829 | LATER | MPW | SAU4005-G000-CWA-&EFS-03256 | GT(V) - SCHEMATIC DIAGRAM OF CCR DESK | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-02-12 |  | 2026-02-12
| NEW | 1830 | LATER | MPW | SAU4005-G000-MKG-&MDB-03733 | GT(V) - GENERATOR H2 & CO2 GAS SYSTEM DESCRIPTION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-03-13 |  | 2026-03-11
| NEW | 1831 | LATER | MPW | SAU4005-G000-MKW-&MDB-03732 | GT(V) - GENERATOR SEAL OIL SYSTEM DESCRIPTION | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-03-13 |  | 2026-03-11
| NEW | 1832 | LATER | MPW | SAU4005-G000-MKY-&EFS-03552 | GT(V) - SCHEMATIC DIAGRAM OF GENERATOR CONTROL AND PROTECTION CIRCUIT | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-03-13 |  | 2026-03-05
| NEW | 1833 | LATER | MPW | SAU4005-G000-MKY-&EFS-03553 | GT(V) - SCHEMATIC DIAGRAM OF GENERATOR AUXILIARIES | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-03-13 |  | 2026-03-05
| NEW | 1834 | LATER | MPW | SAU4005-G000-MKY-&EFS-03554 | GT(V) - SCHEMATIC DIAGRAM OF SFC SWITCH CIRCUIT CONTROL | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-03-13 |  | 2026-03-05
| NEW | 1835 | LATER | MPW | SAU4005-G011-___-&DEC-03126 | GT(V) - BLADE WASHING PROCEDURE | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-03-13 |  | 2026-03-05
| NEW | 1836 | LATER | MPW | SAU4005-G011-___-&MDA-03532 | GT(V) - MOBILE AIR DRYER | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFP | [14 empty] | 2026-03-13 |  | 2026-03-05
| NEW | 1837 | LATER | MPW | SAU4005-G000-MKW-&BPD-03734 | GT(V) - LUBRICANT OIL LIST FOR GENERATOR AUXILIARY EQUIPMENT | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2026-04-22 |  | 2026-04-20
| NEW | 1838 | LATER | MPW | SAU4005-G000-MKC-&EFB-03562 | GT(V) - TRANSFER FUNCTION DIAGRAM OF EXCITATION SYSTEM FOR GTG | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | GTG | IFI | IFD | [14 empty] | 2026-05-13 |  | 2026-05-13
|  | 1839 | LATER | SPGDC | SAU4005-G104-MAG-&MFE-07302 | ACC(V) - Functional Description | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-09-27 |  | 2025-12-02 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO | NO | NO |  | NO
|  | 1840 | LATER | SPGDC | SAU4005-G104-MAG-&MFB-07303 | ACC(V) - P&I Diagram_Steam & Condensate System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFA | IFD |  |  | 2025-07-28 |  | 2025-07-24 |  | 2025-07-18 |  | 2025-08-11 |  | 2025-08-23 |  | 2025-12-03 | [21 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO | NO | NO |  | NO
|  | 1841 | LATER | SPGDC | SAU4005-G104-MAG-&MFB-07304 | ACC(V) - P&I Diagram_Air take-off & Cleaning System | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFA | IFD |  |  | 2025-07-28 |  | 2025-07-24 |  | 2025-07-18 |  | 2025-09-16 |  | 2025-08-23 |  | 2025-11-04 | [21 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO | NO | NO |  | NO
|  | 1842 | LATER | SPGDC | SAU4005-G104-MAG-&MED-07308 | ACC(V) - Noise Calculation | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2026-01-14 |  | 2025-12-16 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1843 | LATER | SPGDC | SAU4005-G104-MAG-&MDD-07309 | ACC(V) - CFD Analysis Report | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-10-26 |  | 2025-09-26 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1844 | LATER | SPGDC | SAU4005-G104-MAG-&MPC-07310 | ACC(V) - Terminal Point List | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-09-10 |  | 2025-10-16 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1845 | LATER | SPGDC | SAU4005-G104-MAG-&MTL-07320 | ACC(V) - General Arrangement | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFA | IFP |  |  | 2025-07-28 |  | 2025-07-09 |  | 2025-07-18 |  | 2025-07-23 |  | 2025-08-23 |  | 2025-11-26 | [21 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO | NO | NO |  | NO
|  | 1846 | LATER | SPGDC | SAU4005-G104-MAG-&CLB-07321 | ACC(V) - Anchorage / Foundation Loading | A1 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2025-12-30 |  | 2025-07-14 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1847 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07322 | ACC(V) - Datasheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFA | IFD |  |  | 2025-08-27 |  | 2025-07-14 |  | 2025-08-17 |  | 2025-09-10 |  | 2025-09-22 |  | 2025-12-04 | [21 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1848 | LATER | SPGDC | SAU4005-G104-MAG-&MDD-07323 | ACC(V) - Performance Curve | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-08-27 |  | 2025-07-14 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1849 | LATER | SPGDC | SAU4005-G104-MAG-&MPB-07324 | ACC(V) - Valve List | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-09-24 |  | 2025-10-16 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1850 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07325 | ACC(V) - Fan Datasheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFA | IFD |  |  | 2025-11-25 |  | 2025-07-24 |  | 2025-11-15 |  | 2025-08-11 |  | 2025-12-21 |  | 2025-11-12 | [21 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1851 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07326 | ACC(V) - Fan Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2025-11-25 |  | 2025-11-11 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1852 | LATER | SPGDC | SAU4005-G104-MAG-&EDA-07327 | ACC(V) - Fan Motor Datasheet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-12-25 |  | 2025-11-26 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1853 | LATER | SPGDC | SAU4005-G104-MAG-&EDA-07328 | ACC(V) - Fan Motor Outline Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2025-12-25 |  | 2025-11-26 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1854 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07329 | ACC(V) - Gearbox Datasheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-12-25 |  | 2025-11-12 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1855 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07330 | ACC(V) - Gearbox Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2025-12-25 |  | 2025-11-12 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1856 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07331 | ACC(V) - Steam Jet Air Ejector Datasheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-12-25 |  | 2025-11-26 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1857 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07332 | ACC(V) - Steam Jet Air Ejector Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2025-12-25 |  | 2025-12-02 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1858 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07333 | ACC(V) - Vacuum Pump Datasheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2026-02-08 |  | 2026-02-26 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1859 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07334 | ACC(V) - Vacuum Pump Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2026-02-08 |  | 2026-03-26 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1860 | LATER | SPGDC | SAU4005-G104-MAG-&EDA-07335 | ACC(V) - Vacuum Pump Motor Datasheet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-12-25 |  | 2025-11-27 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1861 | LATER | SPGDC | SAU4005-G104-MAG-&EDA-07336 | ACC(V) - Vacuum Pump Motor Outline & Terminal Box Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2025-12-25 |  | 2025-11-27 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1862 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07337 | ACC(V) - Cleaning Water Pump Datasheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2026-02-03 |  | 2026-06-01 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1863 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07338 | ACC(V) - Cleaning Water Pump Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2026-02-03 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1864 | LATER | SPGDC | SAU4005-G104-MAG-&EDA-07339 | ACC(V) - Cleaning Water Pump Motor Datasheet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2026-02-03 |  | 2026-06-09 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1865 | LATER | SPGDC | SAU4005-G104-MAG-&EDA-07340 | ACC(V) - Cleaning Water Pump Motor Outline & Terminal Box Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2026-02-03 |  | 2026-06-09 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1866 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07341 | ACC(V) - Drain Pump Datasheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2026-02-08 |  | 2026-04-30 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1867 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07342 | ACC(V) - Drain Pump Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2026-02-08 |  | 2026-04-30 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1868 | LATER | SPGDC | SAU4005-G104-MAG-&EDA-07343 | ACC(V) - Drain Pump Motor Datasheet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2026-02-08 |  | 2026-05-06 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1869 | LATER | SPGDC | SAU4005-G104-MAG-&EDA-07344 | ACC(V) - Drain Pump Motor Outline & Terminal Box Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2026-02-08 |  | 2026-05-06 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1870 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07345 | ACC(V) - Electrical Lifting Hoist Datasheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2026-02-03 |  | 2025-12-16 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1871 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07346 | ACC(V) - Electrical Lifting Hoist Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2026-02-03 |  | 2025-12-16 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1872 | LATER | SPGDC | SAU4005-G104-MAG-&EDA-07347 | ACC(V) - Electrical Lifting Hoist Motor Datasheet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2026-02-03 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1873 | LATER | SPGDC | SAU4005-G104-MAG-&EDA-07348 | ACC(V) - Electrical Lifting Hoist Motor Outline & Terminal Box Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2026-02-03 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1874 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07349 | ACC(V) - Condensate Collecting Tank Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2025-11-25 |  | 2025-09-30 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1875 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07350 | ACC(V) - Flash Tank Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2025-11-25 |  | 2025-11-18 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1876 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-09404 | ACC(V) - Drain Tank Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2026-01-17 |  | 2025-12-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1877 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07351 | ACC(V) - Tube Bundle Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2025-08-12 |  | 2025-07-14 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1878 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07352 | ACC(V) - Expansion Joint Datasheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2026-02-03 |  | 2026-02-26 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1879 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07353 | ACC(V) - Expansion Joint Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2026-02-03 |  | 2026-02-26 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1880 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07354 | ACC(V) - Rupture Disc Datasheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2026-01-14 |  | 2025-12-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1881 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07355 | ACC(V) - Rupture Disc Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2026-01-14 |  | 2025-12-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1882 | LATER | SPGDC | SAU4005-G104-MAG-&MDA-07356 | ACC(V) - Vacuum Breaker Valve Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2025-12-25 |  | 2025-11-27 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1883 | LATER | SPGDC | SAU4005-G104-MAG-&MPD-07357 | ACC(V) - Equipment List | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-08-17 |  | 2025-07-24 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1885 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07363 | ACC(V) - Piping Arrangement Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2026-03-02 |  | 2026-04-30 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1886 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07364 | ACC(V) - Piping Isometric Drawring - Mixed Bundles Air Take Off Lines | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2026-03-02 |  | 2026-03-12 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1887 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07365 | ACC(V) - Piping Isometric Drawring - Main Condensate Lines | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2026-03-02 |  | 2026-03-12 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1888 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07366 | ACC(V) - Piping Isometric Drawring - Condensate Tank Drain Lines | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2026-03-02 |  | 2026-03-12 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1889 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07367 | ACC(V) - Piping Isometric Drawring - Drain Pump Lines | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2026-03-02 |  | 2026-03-12 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1890 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07368 | ACC(V) - Piping Isometric Drawring - Drain Tank, Flash Tank, and Vacuum Unit Drain Lines | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2026-03-02 |  | 2026-03-12 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1891 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07369 | ACC(V) - Piping Isometric Drawring - Air Take Off Holding Lines | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2026-03-02 |  | 2026-03-12 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1892 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07370 | ACC(V) - Piping Isometric Drawring - Equalising Lines | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2026-03-02 |  | 2026-03-12 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1893 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07371 | ACC(V) - Duct Arrangement Drawing & Support Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2025-10-26 |  | 2025-09-24 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1894 | LATER | SPGDC | SAU4005-G104-MAG-&MPD-07374 | ACC(V) - Pipe Line List | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-09-24 |  | 2025-10-16 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1895 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07375 | ACC(V) - Piping Support Drawing - Cleaning Lines & Site Routing Lines | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2026-03-29 |  | 2026-03-12 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1896 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07376 | ACC(V) - Piping Support Drawing - Main Condensate Lines | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2026-03-29 |  | 2026-03-12 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1897 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07377 | ACC(V) - Piping Support Drawing - Condensate Tank Drain Lines | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2026-03-29 |  | 2026-03-12 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1898 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07378 | ACC(V) - Piping Support Drawing - Drain Pump Lines | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2026-03-29 |  | 2026-03-12 | [17 empty] | BE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1899 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07379 | ACC(V) - Piping Support Drawing - Drain Tank, Flash Tank, and Vacuum Unit Drain Lines | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2026-03-29 |  | 2026-03-13 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1900 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07380 | ACC(V) - Piping Support Drawing - Air Take Off Holding Lines | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2026-03-29 |  | 2026-03-13 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1901 | LATER | SPGDC | SAU4005-G104-MAG-&MMB-07381 | ACC(V) - Piping Support Drawing - Equalising Lines | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2026-03-29 |  | 2026-03-13 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
| DCC changed | 1902 | LATER | SPGDC | SAU4005-G104-MAG-&MEC-07382 | ACC(V) - Insulation Specification | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2026-03-02 |  | 2026-04-15 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1903 | LATER | SPGDC | SAU4005-G104-MAG-&MED-07383 | ACC(V) - Flexibility Analysis for Steam Exhaust Ducting | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-10-26 |  | 2025-09-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1904 | LATER | SPGDC | SAU4005-G104-MAG-&EFF-07384 | ACC(V) - Control Logic Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | MECHANICAL | DOOSAN | ACC | IFA | IFD |  |  | 2026-02-15 |  | 2026-04-10 |  | 2026-02-05 |  | 2025-10-14 |  | 2026-03-13 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1905 | LATER | SPGDC | SAU4005-G104-MAG-&EPD-07385 | ACC(V) - Instrument List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-09-24 |  | 2025-09-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1906 | LATER | SPGDC | SAU4005-G104-MAG-&EDA-07386 | ACC(V) - Instrument Datasheet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-10-08 |  | 2025-09-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1907 | LATER | SPGDC | SAU4005-G104-MAG-&ELD-07387 | ACC(V) - Instrument Hook-up Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2025-11-25 |  | 2025-09-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1908 | LATER | SPGDC | SAU4005-G104-MAG-&ELD-07388 | ACC(V) - Wiring Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2026-02-23 |  | 2026-01-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1909 | LATER | SPGDC | SAU4005-G104-MAG-&ELD-07389 | ACC(V) - Electrical and I&C Item (Terminal Box, Junction Box, Instrument) Layout Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2026-02-23 |  | 2025-10-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1910 | LATER | SPGDC | SAU4005-G104-MAG-&EDA-07390 | ACC(V) - Junction Box Outline Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2026-02-23 |  | 2026-01-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1911 | LATER | SPGDC | SAU4005-G104-MAG-&ELD-07391 | ACC(V) - Lighting and Small Power Layout & Specification | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2026-02-23 |  | 2026-01-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1912 | LATER | SPGDC | SAU4005-G104-MAG-&ELD-07392 | ACC(V) - Cable Raceway Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2025-12-25 |  | 2025-10-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1913 | LATER | SPGDC | SAU4005-G104-MAG-&ELD-07393 | ACC(V) - Earthing Layout Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFP | [14 empty] | 2025-12-25 |  | 2025-10-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1914 | LATER | SPGDC | SAU4005-G104-MAG-&EEC-07394 | ACC(V) - Elec. Load list | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-08-27 |  | 2025-08-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1915 | LATER | SPGDC | SAU4005-G104-MAG-&EMA-07395 | ACC(V) - Power Supply Distribution Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-11-25 |  | 2025-10-31 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1916 | LATER | SPGDC | SAU4005-G104-MAG-&EPF-07397 | ACC(V) - Hardwired IO list | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2026-01-24 |  | 2025-12-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1917 | LATER | SPGDC | SAU4005-G104-MAG-&EPD-09400 | ACC(V) - Drive list (MOVs, Motors, Control valves, Solenoid valves, etc..) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2026-02-23 |  | 2026-02-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 1918 | LATER | SPGDC | SAU4005-G104-MAG-&EPD-09401 | ACC(V) - Cable Schedule | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | MECHANICAL | DOOSAN | ACC | IFI | IFD | [14 empty] | 2025-12-25 |  | 2025-11-27 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
| Purpose changed | 1919 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09624 | BFP(V) - Piping detailed drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFP | [6 empty] | 2025-08-30 |  |  |  | 2025-12-26 |  |  |  | 2025-09-09 |  | 2025-10-01 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1920 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09625 | BFP(V) - Coupling Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFD | [14 empty] | 2025-09-07 |  | 2025-08-21 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1921 | LATER | Hyosung | SAU4005-G011-LAC-&MFB-09634 | BFP(V) - Instrument Hookup drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFP | [14 empty] | 2025-11-01 |  | 2025-10-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1922 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09622 | BFP(V) - Instrument data sheets | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFA | IFD |  |  | 2025-10-12 |  | 2025-09-30 |  | 2025-09-18 |  | 2025-07-22 |  | 2025-12-26 |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1923 | LATER | Hyosung | SAU4005-G011-LAC-&MPD-09650 | BFP(V) - Instrument list | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFD | [14 empty] | 2025-09-28 |  | 2025-08-13 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1924 | LATER | Hyosung | SAU4005-G011-LAC-&MPD-09655 | BFP(V) - Complete Valve list & Valve datasheet. | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFA | IFD |  |  | 2025-10-12 |  | 2025-09-11 |  | 2025-09-04 |  | 0 |  | 2025-12-30 |  | 2025-09-26 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1925 | LATER | Hyosung | SAU4005-G011-LAC-&MMB-09640 | BFP(V) - Instrumentation wiring diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFA | IFP |  |  | 2025-09-09 |  | 2025-08-21 |  | 2025-08-30 |  | 2025-09-08 |  | 2025-11-30 |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1926 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09616 | BFP(V) - Lubrication oil system data sheets | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFA | IFD |  |  | 2025-09-07 |  | 2025-08-20 |  | 2025-08-28 |  | 2025-09-16 |  | 2025-11-30 |  | 2025-09-03 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1927 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09615 | BFP(V) - Lubrication oil system nameplate drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFD | [14 empty] | 2025-09-07 |  | 2025-08-21 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1928 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09614 | BFP(V) - Lubrication oil system general arrangement drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFA | IFD |  |  | 2025-08-20 |  | 2025-07-07 |  | 2025-08-10 |  | 2025-07-23 |  | 2025-10-31 |  | 2025-12-17 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1929 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09605 | BFP(V) - General Arrangement drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFA | IFP |  |  | 2025-07-20 |  | 2025-06-24 |  | 2025-07-10 |  | 2025-07-09 |  | 2025-10-31 |  | 2025-10-05 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1930 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09609 | BFP(V) - Motor general arrangement drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFD | [14 empty] | 2025-09-07 |  | 2025-08-13 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1931 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09608 | BFP(V) - Motor data sheets | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFA | IFD |  |  | 2025-09-07 |  | 2025-08-25 |  | 2025-08-28 |  | 2025-07-22 |  | 2025-11-30 |  | 2026-01-08 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1932 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09611 | BFP(V) - Motor nameplate drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFA | IFD |  |  | 2025-09-07 |  | 2025-08-22 |  | 2025-08-28 |  | 2025-07-22 |  | 2025-11-30 |  | 2026-01-21 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1933 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09612 | BFP(V) - Motor performance curves | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFD | [14 empty] | 2025-09-07 |  | 2025-08-28 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1934 | LATER | Hyosung | SAU4005-G011-LAC-&ELU-09684 | BFP(V) - I&C Junction Box & Outline Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFD | [14 empty] | 2025-10-12 |  | 2025-09-12 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1935 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09606 | BFP(V) - Pump data sheets | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFA | IFD |  |  | 2025-07-20 |  | 2025-07-07 |  | 2025-07-10 |  | 2025-07-22 |  | 2025-10-31 |  | 2025-10-08 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1936 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09607 | BFP(V) - Pump performance curves | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFD | [14 empty] | 2025-07-20 |  | 2025-07-07 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1937 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09610 | BFP(V) - Pump nameplate drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFD | [14 empty] | 2025-07-20 |  | 2025-07-07 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1938 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09613 | BFP(V) - Pump sectional drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFD | [14 empty] | 2025-07-20 |  | 2025-07-07 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1939 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09618 | BFP(V) - Mechanical seal general arrangement drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFD | [14 empty] | 2025-09-28 |  | 2025-09-03 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1940 | LATER | Hyosung | SAU4005-G011-LAC-&MEC-09695 | BFP(V) - Cooler Specification | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFD | [14 empty] | 2025-09-28 |  | 2025-09-03 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1941 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09617 | BFP(V) - Suction strainer data sheets | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFA | IFD |  |  | 2025-09-28 |  | 2025-09-03 |  | 2025-09-18 |  | 2025-09-16 |  | 2025-10-24 |  | 2025-10-02 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1942 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09619 | BFP(V) - Suction strainer general arrangement drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFD | [14 empty] | 2025-09-28 |  | 2025-09-03 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1943 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09696 | BFP(V) - Orifice Drawing & Data sheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFA | IFD |  |  | 2025-11-18 |  | 2025-09-26 |  | 2025-10-29 |  | 2025-09-16 |  | 2025-12-26 |  | 2025-10-09 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1944 | LATER | Hyosung | SAU4005-G011-LAC-&MEC-09698 | BFP(V) - Thermal insulation specification | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFP | [14 empty] | 2025-09-28 |  | 2025-08-13 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1945 | LATER | Hyosung | SAU4005-G011-LAC-&ELU-09699 | BFP(V) - Diagram of LPBS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFP | [14 empty] | 2025-09-14 |  | 2025-08-14 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1946 | LATER | Hyosung | SAU4005-G011-LAC-&EEC-09700 | BFP(V) - LPBS Specification | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFD | [14 empty] | 2025-09-14 |  | 2025-08-14 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1947 | LATER | Hyosung | SAU4005-G011-LAC-&MDA-09701 | BFP(V) - Sound Enclosure Specification & Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFP | [14 empty] | 2025-09-14 |  | 2025-08-13 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1948 | LATER | Hyosung | SAU4005-G011-LAC-&MFB-09632 | BFP(V) - Pump Piping & instrumentation diagram | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFA | IFP |  |  | 2025-07-20 |  | 2025-06-24 |  | 2025-07-10 |  | 2025-07-09 |  | 2025-10-31 |  | 2025-10-07 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1949 | LATER | Hyosung | SAU4005-G011-LAC-&EFP-09682 | BFP(V) - DCS Interface I/C List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFI | IFD | [14 empty] | 2025-10-12 |  | 2025-09-09 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1950 | LATER | Hyosung | SAU4005-G011-LAC-&MMB-09644 | BFP(V) - Motor wiring diagram and main terminal box | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | Boiler Feed Pump | IFA | IFD |  |  | 2026-01-24 |  | 2025-12-09 |  | 2025-02-09 |  | 2025-12-23 |  | 2026-01-25 |  | 2026-04-16 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 1951 | LATER | Hyosung | SAU4005-G000-LCB-&MDF-09500 | CEP(V) - Performance Curve | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFD | [14 empty] | 2025-07-20 |  | 2025-06-24 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1952 | LATER | Hyosung | SAU4005-G000-LCB-&MDA-09501 | CEP(V) - Datasheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFA | IFD |  |  | 2025-07-20 |  | 2025-06-24 |  | 2025-07-10 |  | 2025-07-09 |  | 2025-08-15 |  | 2025-08-27 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1953 | LATER | Hyosung | SAU4005-G000-LCB-&MLU-09502 | CEP(V) - General Arrangement Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFA | IFP |  |  | 2025-07-20 |  | 2025-06-24 |  | 2025-07-10 |  | 2025-07-08 |  | 2025-10-31 |  | 2025-10-22 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1954 | LATER | Hyosung | SAU4005-G000-LCB-&MFB-09503 | CEP(V) - Piping & Instrument Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFA | IFP |  |  | 2025-07-20 |  | 2025-06-24 |  | 2025-07-10 |  | 2025-12-23 |  | 2025-10-31 |  | 2025-07-04 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1955 | LATER | Hyosung | SAU4005-G000-LCB-&MLU-09504 | CEP(V) - Pump Section Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFD | [14 empty] | 2025-07-20 |  | 2025-07-07 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1956 | LATER | Hyosung | SAU4005-G000-LCB-&MLU-09505 | CEP(V) - Pump Mechenical. Seal Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFD | [14 empty] | 2025-09-28 |  | 2025-09-09 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1957 | LATER | Hyosung | SAU4005-G000-LCB-&MDA-09506 | CEP(V) - Pump Nameplate Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFD | [14 empty] | 2025-09-07 |  | 2025-08-14 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1958 | LATER | Hyosung | SAU4005-G000-LCB-&MEC-09547 | CEP(V) - Thermal insulation specification | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFP | [14 empty] | 2025-09-28 |  | 2025-08-13 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1959 | LATER | Hyosung | SAU4005-G000-LCB-&EEC-09509 | CEP(V) - Instrument List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFD | [14 empty] | 2025-09-28 |  | 2025-08-13 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1960 | LATER | Hyosung | SAU4005-G000-LCB-&MFB-09549 | CEP(V) - Instrument Hookup drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFP | [14 empty] | 2025-11-01 |  | 2025-10-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1961 | LATER | Hyosung | SAU4005-G000-LCB-&EEC-09510 | CEP(V) - I/O List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFD | [14 empty] | 2025-10-12 |  | 2025-09-09 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1962 | LATER | Hyosung | SAU4005-G000-LCB-&ELU-09550 | CEP(V) - I&C Junction Box & Outline Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFD | [14 empty] | 2025-10-12 |  | 2025-09-12 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1963 | LATER | Hyosung | SAU4005-G000-LCB-&EDA-09511 | CEP(V) - Motor Data Sheet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFA | IFD |  |  | 2025-09-07 |  | 2025-08-26 |  | 2025-08-28 |  | 2025-09-10 |  | 2025-11-30 |  | 2026-04-13 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1964 | LATER | Hyosung | SAU4005-G000-LCB-&EDF-09512 | CEP(V) - Motor Performance Curve | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFD | [14 empty] | 2025-09-07 |  | 2025-08-22 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1965 | LATER | Hyosung | SAU4005-G000-LCB-&ELU-09513 | CEP(V) - Motor Outline Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFD | [14 empty] | 2025-09-07 |  | 2025-08-22 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1966 | LATER | Hyosung | SAU4005-G000-LCB-&EDA-09514 | CEP(V) - Motor Terminal Box Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFD | [14 empty] | 2025-09-14 |  | 2025-08-22 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1967 | LATER | Hyosung | SAU4005-G000-LCB-&MDA-09524 | CEP(V) - Motor Nameplate Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFA | IFD |  |  | 2025-09-07 |  | 2025-08-22 |  | 2025-08-28 |  | 2025-09-07 |  | 2025-11-30 |  | 2026-01-14 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1968 | LATER | Hyosung | SAU4005-G000-LCB-&MEC-09525 | CEP(V) - Valve List & Datasheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFA | IFD |  |  | 2025-10-12 |  | 2025-09-11 |  | 2025-09-04 |  | 0 |  | 2025-11-30 |  | 2025-09-26 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1969 | LATER | Hyosung | SAU4005-G000-LCB-&MEC-09526 | CEP(V) - Strainer Technical Documents | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFP | [14 empty] | 2025-10-12 |  | 2025-09-12 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1970 | LATER | Hyosung | SAU4005-G000-LCB-&MEC-09528 | CEP(V) - Coupling Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFD | [14 empty] | 2025-09-07 |  | 2025-08-21 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1971 | LATER | Hyosung | SAU4005-G000-LCB-&ELU-09537 | CEP(V) - Diagram of LPBS | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFP | [14 empty] | 2025-09-07 |  | 2025-08-14 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1972 | LATER | Hyosung | SAU4005-G000-LCB-&MLU-09548 | CEP(V) - Aux. Piping Arrangement Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFP | [14 empty] | 2025-10-12 |  | 2025-09-11 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1973 | LATER | Hyosung | SAU4005-G000-LCB-&EEC-09555 | CEP(V) - LPBS Specification | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFI | IFD | [14 empty] | 2025-09-07 |  | 2025-08-14 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1974 | LATER | Hyosung | SAU4005-G000-LCB-&MDA-09567 | CEP(V) - Instrument Data Sheets | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFA | IFD |  |  | 2025-11-01 |  | 2025-09-30 |  | 2025-09-27 |  | 2025-10-12 |  | 2025-12-16 |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO | NO
|  | 1975 | LATER | Hyosung | SAU4005-G000-LCB-&EDB-09536 | CEP(V) - Pump Wiring Diagram | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECHANICAL | MECHANICAL | DOOSAN | CEP | IFA | IFD |  |  | 2025-11-01 |  | 2025-09-30 |  | 2025-11-10 |  | 2025-10-12 |  | 2025-12-16 |  | 0
|  | 1976 | LATER | ShinShin | SAU4005-G142-ACA-&MDA-12801 | FTTP(V) - Motor Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECHANICAL | MECHANICAL | DOOSAN | FTTP | IFI | IFD | [14 empty] | 2026-02-08 |  | 2026-02-02 | [17 empty] | DE | MECHANICAL | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO | YES | NO | NO |  | NO
|  | 1977 | LATER | ShinShin | SAU4005-G142-ACA-&MDA-12802 | FTTP(V) - Steam Drain Motor Terminal Box Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECHANICAL | MECHANICAL | DOOSAN | FTTP | IFI | IFD | [14 empty] | 2026-02-22 |  | 2026-02-02 | [17 empty] | DE | MECHANICAL | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO | YES | NO | NO |  | NO
|  | 1978 | LATER | ShinShin | SAU4005-G142-ACA-&MDA-12803 | FTTP(V) - Steam Drain Pump Section Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECHANICAL | MECHANICAL | DOOSAN | FTTP | IFI | IFD | [14 empty] | 2026-03-01 |  | 2026-02-02 | [17 empty] | DE | MECHANICAL | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO | YES | NO | NO |  | NO
|  | 1979 | LATER | ShinShin | SAU4005-G142-ACA-&MDA-12804 | FTTP(V) - Steam Drain Pump Nameplate Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECHANICAL | MECHANICAL | DOOSAN | FTTP | IFA | IFD |  |  | 2026-03-08 |  | 2026-02-02 |  | 2026-03-23 |  | 2026-02-18 |  | 2026-05-06 |  | 2026-04-02 | [21 empty] | DE | MECHANICAL | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO | YES | NO | NO |  | NO
|  | 1981 | LATER | ShinShin | SAU4005-G142-ACA-&EPC-12807 | FTTP(V) - Instrument list & datasheet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | FTTP | IFI | IFD | [14 empty] | 2026-03-08 |  | 2026-02-03 | [17 empty] | DE | I&C | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO | YES | NO | NO |  | NO
|  | 1982 | LATER | ShinShin | SAU4005-G142-ACA-&MDA-12800 | FTTP(V) - Pump Outline Drawing (with foundation loading data) | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECHANICAL | MECHANICAL | DOOSAN | FTTP | IFA | IFD |  |  | 2026-02-08 |  | 2026-02-02 |  | 2026-02-23 |  | 2026-02-18 |  | 2026-04-09 |  | 2026-03-29 | [21 empty] | DE | MECHANICAL | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO | YES | NO | NO |  | NO
|  | 1983 | LATER | ShinShin | SAU4005-G142-ACA-&MDA-12805 | FTTP(V) - Pump Data Sheet with Performance Curve | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECHANICAL | MECHANICAL | DOOSAN | FTTP | IFA | IFD |  |  | 2026-02-08 |  | 2026-02-02 |  | 2026-02-23 |  | 2026-02-18 |  | 2026-04-09 |  | 2026-03-29 | [21 empty] | DE | MECHANICAL | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO | YES | NO | NO |  | NO
|  | 1984 | LATER | ShinShin | SAU4005-G142-ACA-&EDA-12806 | FTTP(V) - Motor Data Sheet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | FTTP | IFA | IFD |  |  | 2026-02-22 |  | 2026-02-02 |  | 2026-03-09 |  | 2026-02-05 |  | 2026-04-23 |  | 2026-03-29 | [21 empty] | DE | ELECTRICAL | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO | YES | NO | NO |  | NO
|  | 1985 | LATER | ShinShin | SAU4005-G142-ACA-&ADC-12808 | FTTP(V) - O&M and start up commissioning manuals of pumps & motors | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECHANICAL | MECHANICAL | DOOSAN | FTTP | IFI | IFD | [14 empty] | 2026-07-18 | [19 empty] | DE | MECHANICAL | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO | YES | NO | NO
|  | 1986 | LATER | Emerson | SAU4005-G180-C__-&EFE-25001 | DCS(V) - Functional Design Specification for Hardware | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFA | IFD |  |  | 2025-08-15 |  | 2025-07-25 |  | 2025-08-05 |  | 2025-08-11 |  | 2025-09-10 |  | 2025-12-09 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1987 | LATER | Emerson | SAU4005-G180-C__-&EFE-25002 | DCS(V) - Functional Design Specification for Software | A1 | Engineering | B-Overall technology | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFA | IFD |  |  | 2025-08-15 |  | 2025-07-25 |  | 2025-08-05 |  | 2025-08-11 |  | 2025-09-10 |  | 2026-03-15 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1988 | LATER | Emerson | SAU4005-G180-C__-&EFE-25003 | DCS(V) - Functional Design Specification for Graphic | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFA | IFD |  |  | 2025-08-15 |  | 2025-07-25 |  | 2025-08-05 |  | 2025-08-07 |  | 2025-09-10 |  | 2026-01-15 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1989 | LATER | Emerson | SAU4005-G180-C__-&EFE-25004 | DCS(V) - Functional Design Specification for Safety Related System | A1 | Engineering | B-Overall technology | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFA | IFD |  |  | 2025-10-11 |  | 2025-09-01 |  | 2025-10-01 |  | 2025-09-16 |  | 2025-11-06 |  | 2025-11-19 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1990 | LATER | Emerson | SAU4005-G180-C__-&EFE-25005 | DCS(V) - Functional Design Specification for Cyber Security and Network | A1 | Engineering | A-Overall management | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFA | IFD |  |  | 2025-08-15 |  | 2025-07-25 |  | 2025-08-05 |  | 2025-08-07 |  | 2025-09-10 |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO | NO | NO |  | NO
|  | 1991 | LATER | Emerson | SAU4005-G180-C__-&EFE-25006 | DCS(V) - Functional Design Specification for Plant Performance Monitoring System | A1 | Engineering | B-Overall technology | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFA | IFD |  |  | 2025-11-28 |  | 2025-09-26 |  | 2025-11-18 |  | 2025-08-11 |  | 2025-12-24 |  | 2026-01-21 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1992 | LATER | Emerson | SAU4005-G180-C__-&EFE-25007 | DCS(V) - Datasheet & Drawing for Time Synchronization | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFA | IFD |  |  | 2025-09-26 |  | 2025-08-18 |  | 2025-09-16 |  | 2025-08-11 |  | 2025-10-22 |  | 2025-11-04 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1993 | LATER | Emerson | SAU4005-G180-C__-&EFE-25008 | DCS(V) - Datasheet & Drawings for Large Screen Display | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFA | IFD |  |  | 2025-09-26 |  | 2025-08-18 |  | 2025-09-16 |  | 2025-08-11 |  | 2025-10-22 |  | 2025-11-06 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1994 | LATER | Emerson | SAU4005-G180-C__-&EFA-25009 | DCS(V) - LAN Configuration Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFI | IFD | [14 empty] | 2025-08-29 |  | 2025-08-07 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1995 | LATER | Emerson | SAU4005-G180-C__-&ELD-25010 | DCS(V) - Grounding Detail Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFI | IFP | [14 empty] | 2025-12-16 |  | 2025-11-25 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1996 | LATER | Emerson | SAU4005-G180-C__-&ELU-25011 | DCS(V) - Typical Outline Drawing for Cabinet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFI | IFD | [14 empty] | 2025-08-29 |  | 2025-08-07 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1997 | LATER | Emerson | SAU4005-G180-C__-&ELU-25012 | DCS(V) - Outline & Detail Drawing for System and Marshalling Cabinet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFI | IFD | [14 empty] | 2025-11-28 |  | 2025-10-21 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1998 | LATER | Emerson | SAU4005-G180-C__-&ELU-25013 | DCS(V) - Outline & Detail Drawing for LAN/Server Cabinet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFI | IFD | [14 empty] | 2025-11-28 |  | 2025-10-21 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 1999 | LATER | Emerson | SAU4005-G180-C__-&ELU-25014 | DCS(V) - Outline & Detail Drawing for Power Distribution Cabinet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFI | IFD | [14 empty] | 2025-11-28 |  | 2025-10-21 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2000 | LATER | Emerson | SAU4005-G180-C__-&ELU-25015 | DCS(V) - Outline & Detail Drawing for Relay Cabinet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFI | IFD | [14 empty] | 2025-11-28 |  | 2025-10-21 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2001 | LATER | Emerson | SAU4005-G180-C__-&ELU-25016 | DCS(V) - Outline & Detail Drawing for Console Desk with EPB Station | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFI | IFD | [14 empty] | 2025-11-28 |  | 2025-11-10 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2002 | LATER | Emerson | SAU4005-G180-C__-&ELU-25017 | DCS(V) - Outline & Detail Drawing for Provision Cabinet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFI | IFD | [14 empty] | 2025-11-28 |  | 2025-10-21 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2003 | LATER | Emerson | SAU4005-G180-C__-&ELU-25018 | DCS(V) - Outline & Detail Drawing for Safety Related System Cabinet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFI | IFD | [14 empty] | 2025-11-28 |  | 2025-10-22 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2004 | LATER | Emerson | SAU4005-G180-C__-&EFC-25019 | DCS(V) - HMI Graphic Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFA | IFD |  |  | 2026-04-29 |  | 2026-06-09 |  | 2026-04-19 |  | 0 |  | 2026-05-25 |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2005 | LATER | Emerson | SAU4005-G180-C__-&EFP-25020 | DCS(V) - IO & Module Allocation | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFI | IFD | [14 empty] | 2025-12-29 |  | 2025-12-15 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2006 | LATER | Emerson | SAU4005-G180-C__-&EMA-25021 | DCS(V) - Internal Interconnection Wiring Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFI | IFD | [14 empty] | 2026-03-30 |  | 2026-03-26 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2007 | LATER | Emerson | SAU4005-G180-C__-&EMB-25022 | DCS(V) - Cable List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFI | IFP | [14 empty] | 2026-04-29 |  | 2026-06-04 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2009 | LATER | Emerson | SAU4005-G180-C__-&EFE-25028 | DCS(V) - Functional Design Specification for Field Instrument Management System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFA | IFD |  |  | 2025-09-26 |  | 2025-08-13 |  | 2025-09-16 |  | 2025-08-07 |  | 2025-10-22 |  | 2025-10-14 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2010 | LATER | Emerson | SAU4005-G180-C__-&EFE-25029 | DCS(V) - Functional Design Specification for Remote Monitoring System | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFA | IFD |  |  | 2025-09-26 |  | 2025-09-16 |  | 2025-09-16 |  | 2025-08-07 |  | 2025-10-22 |  | 2026-01-04 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2011 | LATER | Emerson | SAU4005-G180-C__-&EFE-25105 | DCS(V) - 3rd Party Datalink Specification(OPC, IEC, Modbus) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFA | IFD |  |  | 2025-09-26 |  | 2025-08-25 |  | 2025-09-16 |  | 2025-08-11 |  | 2025-10-22 |  | 2025-10-13 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2012 | LATER | Emerson | SAU4005-G180-C__-&EFE-25023 | DCS(V) - Datasheet & Drawings for CCR Emergency Push Button | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFA | IFD |  |  | 2025-11-26 |  | 2025-09-23 |  |  |  | 2025-08-11 |  |  |  | 2025-11-04 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2013 | LATER | Emerson | SAU4005-G180-C__-&ELD-25104 | DCS(V) - Grounding Concept & Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & control | DOOSAN | DCS | IFI | IFD | [14 empty] | 2025-12-30 |  | 2025-11-12 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2014 | LATER | NADA | SAU4005-G185-C__-&EDA-22800 | VMS(V) - Datasheet & Vender Print | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | Instrumentation & control | DOOSAN | VMS | IFA | IFD |  |  | 2025-11-29 |  | 2025-09-26 |  | 2025-11-19 |  | 2025-10-12 |  | 2025-12-30 |  | 2025-11-26 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2015 | LATER | NADA | SAU4005-G185-C__-&EFA-22801 | VMS(V) - System Configuration | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | Instrumentation & control | DOOSAN | VMS | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-09-26 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
| NEW | 2016 | LATER | LS Cable | SAU4005-G188-___-&EEC-26001 | I&C Cable(V) – Technical Specification | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | Instrumentation & control | DOOSAN | I&C Cable | IFA | IFP |  |  | 2026-01-19 |  | 2026-01-14 |  | 2026-01-09 |  | 2026-02-01 |  | 2026-02-14 |  | 2026-03-29 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
| NEW | 2017 | LATER | Emerson Saudi Arabia | SAU4005-G187-___-&EEC-25901 | Pneumatic Control Valve(V) - Technical Specification & Datasheet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | Instrumentation & control | DOOSAN | Pneumatic Control Valve | IFA | IFD |  |  | 2026-03-30 |  | 2026-04-20 |  | 2026-04-19 |  | 0 |  | 2026-05-25 |  | 2026-05-06 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
| NEW | 2018 | LATER | Dongjin | SAU4005-G188-___-&EEC-26011 | I&C Cable Termination Materials(V) – Technical Specification | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | Instrumentation & control | DOOSAN | I&C Cable Termination | IFA | IFP |  |  | 2026-02-27 |  | 2026-02-11 |  | 2026-03-19 |  | 0 |  | 2026-04-24 |  | 2026-03-02 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
| NEW | 2019 | LATER | HY-LOK CORPORATION | SAU4005-G193-___-&EEC-26811 | Instrument Installation Material(V) – Technical Specification | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | Instrumentation & control | DOOSAN | Instrument Hook-up | IFA | IFP |  |  |  |  | 2026-04-13 |  |  |  | 0 |  |  |  | 2026-04-28 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
| NEW | 2020 | LATER | WINNERS INTECH | SAU4005-G191-___-&EEC-26410 | Process Transmitters(V) - Technical Specification & Datasheet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | Instrumentation & control | DOOSAN | Field Instrument | IFA | IFP |  |  | 2026-03-30 |  | 2026-03-19 |  | 2026-04-19 |  | 2026-04-12 |  | 2026-05-25 |  | 0
| NEW | 2021 | LATER | SEOJIN PROCESS | SAU4005-G191-___-&EEC-26420 | Local Instruments(V) - Technical Specification & Datasheet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | Instrumentation & control | DOOSAN | Field Instrument | IFA | IFP |  |  | 2026-03-30 |  | 2026-03-19 |  | 2026-04-19 |  | 2026-04-06 |  | 2026-05-25 |  | 0
| NEW | 2022 | LATER | EPC | SAU4005-G000-___-&EFF-02000 | Cyber Security Integrated Configuration | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | Instrumentation & control | COMMON | I&C Cable Termination | IFI | IFD | [14 empty] | 2026-02-27 |  | 2026-02-04 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
| NEW | 2023 | LATER | ESAK Co. Ltd | SAU4005-G191-___-&EEC-26430 | Flow Elements (V) - Technical Specification & Datasheet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | Instrumentation & control | DOOSAN | Field Instrument | IFA | IFP |  |  | 2026-03-30 |  | 2026-03-20 |  | 2026-04-19 |  | 2026-02-05 |  | 2026-05-25 |  | 0
| NEW | 2024 | LATER | UNITECKOREA | SAU4005-G193-___-&EEC-26801 | JUNCTION BOX & TRANSMITTER RACK(V) – Technical Specification | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | Instrumentation & control | DOOSAN | Local Box | IFA | IFP |  |  | 2026-03-30 |  | 2026-03-24 |  | 2026-04-19 |  | 0 |  | 2026-05-25 |  | 2026-04-13
|  | 2025 | LATER | SWT | SAU4005-G158-XKA-&EDA-21001 | BSEDG(V) - Control cabinet layout of DG | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | [15 empty] | 2025-09-25 |  | 2025-10-17
| title changed | 2026 | LATER | SWT | SAU4005-G158-XKA-&EEC-21002 | BSEDG(V) - Electrical Cable schedule | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2025-10-18 |  | 2025-10-17 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2028 | LATER | SWT | SAU4005-G158-XKA-&ELU-21004 | BSEDG(V) - General Arrangement | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | GENERAL | GENERAL | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2025-10-15 |  | 2025-09-22 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2029 | LATER | SWT | SAU4005-G158-XKA-&EFB-21005 | BSEDG(V) - P&ID(FUEL OIL SYSTEM, LUBE OIL SYSTEM, COOLING WATER SYSTEM, AIR INTAKE & EXHAUST SYSTEM ) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECHANICAL | MECHANICAL | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2025-10-30 |  | 2025-10-24 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2030 | LATER | SWT | SAU4005-G158-XKA-&EEC-21006 | BSEDG(V) - Electrical load list | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2025-10-18 |  | 2025-10-17 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2031 | LATER | SWT | SAU4005-G158-XKA-&EPF-21007 | BSEDG(V) - PLC IO List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2025-11-22 |  | 2025-10-24 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2032 | LATER | SWT | SAU4005-G158-XKA-&EDA-21008 | BSEDG(V) - Datasheet for DG | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | GENERAL | GENERAL | DOOSAN | BSDG | IFA | IFP |  |  | 2025-10-17 |  | 2025-09-22 |  | 2025-10-07 |  | 2025-12-23 |  | 2025-11-12 |  | 2026-02-18 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2033 | LATER | SWT | SAU4005-G158-XKA-&EDB-21009 | BSEDG(V) - Control System Configuration | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2026-01-15 |  | 2025-12-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2034 | LATER | SWT | SAU4005-G158-XKA-&EDA-21010 | BSEDG(V) - Nameplate drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECHANICAL | MECHANICAL | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2026-01-15 |  | 2025-12-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2035 | LATER | SWT | SAU4005-G158-XKA-&EDA-21011 | BSEDG(V) - Technical specification for Panel /SWGR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2025-11-22 |  | 2025-10-17 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2036 | LATER | SWT | SAU4005-G158-XKA-&EFB-21012 | BSEDG(V) - Single Line Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | BSDG | IFA | IFP |  |  | 2025-10-17 |  | 2025-12-23 |  | 2025-10-07 |  | 2026-01-15 |  | 2025-11-12 |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2037 | LATER | SWT | SAU4005-G158-XKA-&EFB-21013 | BSEDG(V) - Schematic Diagram for SWGR | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | BSDG | IFA | IFP |  |  | 2025-10-24 |  | 2025-10-17 |  | 2025-10-14 |  | 2025-11-04 |  | 2025-11-19 |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2038 | LATER | SWT | SAU4005-G158-XKA-&EDB-21014 | BSEDG(V) - Operation philosophy and System description | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | GENERAL | GENERAL | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2025-11-29 |  | 2025-10-24 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2041 | LATER | SWT | SAU4005-G158-XKA-&ELD-21017 | BSEDG(V) - Piping Arrangement Drawing (FUEL OIL SYSTEM, LUBE OIL SYSTEM, COOLING WATER SYSTEM, AIR INTAKE & EXHAUST SYSTEM ) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECHANICAL | MECHANICAL | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2026-01-25 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2042 | LATER | SWT | SAU4005-G158-XKA-&ELD-21018 | BSEDG(V) - Piping ISOMETRIC Drawing (FUEL OIL SYSTEM, LUBE OIL SYSTEM, COOLING WATER SYSTEM, AIR INTAKE & EXHAUST SYSTEM ) | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECHANICAL | MECHANICAL | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2026-02-19 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2047 | LATER | SWT | SAU4005-G158-XKA-&EPA-21025 | BSEDG(V) - Chemical list and supplier list | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | GENERAL | GENERAL | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2026-04-02 |  | 2025-09-19 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2048 | LATER | SWT | SAU4005-G158-XKA-&EDA-21026 | BSEDG(V) - Outline Drawing for DG | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | GENERAL | GENERAL | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2025-10-15 |  | 2025-09-22 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2049 | LATER | SWT | SAU4005-G158-XKA-&EEC-21027 | BSEDG(V) - PIPE LINE LIST | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECHANICAL | MECHANICAL | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2026-01-25 |  | 2026-01-08 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2051 | LATER | SWT | SAU4005-G158-XKA-&EEC-21029 | BSEDG(V) - VALVE LIST | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECHANICAL | MECHANICAL | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2026-01-25 |  | 2026-01-08 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2052 | LATER | SWT | SAU4005-G158-XKA-&EED-21030 | BSEDG(V) - HVAC CALCULATION | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECHANICAL | MECHANICAL | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2025-10-18 |  | 2025-10-01 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2053 | LATER | SWT | SAU4005-G158-XKA-&EPL-21031 | BSEDG(V) - Terminal Point List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECHANICAL | MECHANICAL | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2025-10-30 |  | 2025-10-24 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2054 | LATER | SWT | SAU4005-G158-XKA-&EFC-21032 | BSEDG(V) - PLC HMI graphic | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2025-10-18 |  | 2025-09-19 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2055 | LATER | SWT | SAU4005-G158-XKA-&ELD-21033 | BSEDG(V) - PLC/DCS/MCC Arrangement/Layout Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2025-10-18 |  | 2025-09-22 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2056 | LATER | SWT | SAU4005-G158-XKA-&ELD-21034 | BSEDG(V) - Cabinet / Panel terminal Block details | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2025-10-18 |  | 2025-10-24 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2057 | LATER | SWT | SAU4005-G158-XKA-&EDA-21035 | BSEDG(V) - PLC Specification | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2026-01-15 |  | 2025-12-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2058 | LATER | SWT | SAU4005-G158-XKA-&EPF-21036 | BSEDG(V) - Datalink IO List | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2026-01-18 |  | 2026-01-08 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2059 | LATER | SWT | SAU4005-G158-XKA-&ELD-21037 | BSEDG(V) - Hook Up Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2026-02-19 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2060 | LATER | SWT | SAU4005-G158-XKA-&EFE-21038 | BSEDG(V) - Functional Description | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2026-01-25 |  | 2025-12-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2061 | LATER | SWT | SAU4005-G158-XKA-&EEC-21039 | BSEDG(V) - Instrument List & Data Sheet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2026-01-25 |  | 2026-05-07 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2062 | LATER | SWT | SAU4005-G158-XKA-&EEC-21041 | BSEDG(V) - Instrument Installation Detail Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2026-01-25 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2063 | LATER | SWT | SAU4005-G158-XKA-&EPL-21042 | BSEDG(V) - Instrument Location Drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2026-01-25 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2064 | LATER | SWT | SAU4005-G158-XKA-&EDD-21043 | BSEDG(V) - Protection relay setting report | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2025-11-22 |  | 2026-03-12 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2066 | LATER | SWT | SAU4005-G158-XKA-&EED-21045 | BSEDG(V) - DC System calculation | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2025-10-25 |  | 2025-10-17 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2068 | LATER | SWT | SAU4005-G158-XKA-&EED-21047 | BSEDG(V) - Fuel Oil Storage Tank Sizing Calculation | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECHANICAL | MECHANICAL | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2025-10-18 |  | 2025-09-19 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2070 | LATER | SWT | SAU4005-G158-XKA-&EMB-21049 | BSEDG(V) - Instrument Cable Schedule | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2026-01-15 |  | 2025-12-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2071 | LATER | SWT | SAU4005-G158-XKA-&EMA-21050 | BSEDG(V) - I&C cable interconnection list | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2026-02-19 |  | 2026-05-26 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
| title changed | 2072 | LATER | SWT | SAU4005-G158-XKA-&EMA-21051 | BSEDG(V) - Electrical Cable interconnection diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2025-10-25 |  | 2026-03-12 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2073 | LATER | SWT | SAU4005-G158-XKA-&EDD-21052 | BSEDG(V) - Vibration Guarantee Data | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | GENERAL | GENERAL | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2025-10-15 |  | 2025-09-19 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2074 | LATER | SWT | SAU4005-G158-XKA-&EFF-21053 | BSEDG(V) - Control Logic & Loop Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFA | IFP |  |  | 2026-01-15 |  | 2025-12-16 |  | 2025-12-30 |  | 2026-01-11 |  | 2026-01-30 |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
|  | 2075 | LATER | SWT | SAU4005-G158-XKA-&EDA-21054 | BSEDG(V) - CONTAINER DATA SHEET | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | I&C | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2026-01-16 |  | 2025-12-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO | NO | NO |  | NO
| NEW | 2076 | LATER | SWT | SAU4005-G158-XKA-&EFB-21061 | BSEDG(V) - Layout diagram& secondary schematic diagram& data sheet of AC load power cabinet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2026-07-15 |  | 2026-03-20
| NEW | 2077 | LATER | SWT | SAU4005-G158-XKA-&EFB-21057 | BSEDG(V) - LAYOUT DIAGRAM & SECONDARY SCHEMATIC DIAGRAM & DATA SHEET OF DC LOAD POWER CABINET | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2026-07-15 |  | 2026-03-27
| NEW |  | LATER | SWT | SAU4005-G158-XKA-&EFB-21063 | BSEDG(V) - NGR Panel – Outline drawing, Schematic drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | BSDG | IFI | IFP | [14 empty] | 2026-08-09
| dcc changed | 2078 | LATER | WOOSUNG FLOWTEC | SAU4005-G123-___-&MDA-10400 | STRAINER(V) - GA DRAWING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | STRAINER | IFI | [15 empty] | 2026-08-05 |  | 2026-05-11 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES
| NEW | 2079 | LATER | WOOSUNG FLOWTEC | SAU4005-G123-___-&MED-10401 | STRAINER(V) - CACULATION SHEET | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | STRAINER | IFI | [15 empty] | 2026-08-05 |  | 2026-05-11 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES
| DOCUMENT CODE CHANGED | 2080 | LATER | SPIRAX SARCO | SAU4005-G123-___-&MDA-10420 | TRAP(V) - PRODUCT DRAWING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | TRAP | IFI | [15 empty] | 2026-08-05 |  | 2026-05-20 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES
| NEW | 2081 | LATER | SPIRAX SARCO | SAU4005-G123-___-&MED-10421 | TRAP(V) - CACULATION SHEET | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | TRAP | IFI | [15 empty] | 2026-08-05 |  | 2026-05-20 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES
| DOCUMENT CODE CHANGED | 2082 | LATER | KJS INTERVALVE | SAU4005-G128-___-&MDA-11200 | Manual Casting Valve(V) - MANUFACTURING DWG | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | Manual Casting Valve | IFI | [15 empty] | 2026-08-05 |  | 2026-05-22 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES
| NEW | 2083 | LATER | HK Metal | SAU4005-G123-___-&MED-10440 | RESTRICTION ORIFICE (V) - CALCULATION SHEET | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | RESTRICTION ORIFICE | IFI | [15 empty] | 2026-08-05 |  | 2026-05-29
| DOCUMENT CODE CHANGED | 2084 | LATER | HK Metal | SAU4005-G123-___-&MDA-10441 | RESTRICTION ORIFICE (V) - DRAWING | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | RESTRICTION ORIFICE | IFI | [15 empty] | 2026-08-05 |  | 2026-05-29
| NEW | 2085 | LATER | DONG EUN VALVE | SAU4005-G123-___-&MDA-11300 | Manual Forging Valve(V) - OUTLINE DRAWINGS | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | Manual Forging Valve | IFI | [15 empty] | 2026-08-05
| dcc changed | 2086 | LATER | YongKwang | SAU4005-G123-___-&MDA-10460 | Expansion Joint(V) - Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | Expansion Joint | IFI | [15 empty] | 2026-07-06 |  | 2026-05-11
| NEW | 2087 | LATER | YongKwang | SAU4005-G123-___-&MED-10461 | Expansion Joint(V) - Calculation sheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | PIPING | DOOSAN | Expansion Joint | IFI | [15 empty] | 2026-07-06 |  | 2026-05-08
| NEW | 2088 | LATER | IMI | SAU4005-G131-MAN-&MDA-11500 | Bypass Valve & PRDS(V) - Data Sheet and Charateristic Curves | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | Bypass Valve & PRDS | IFA | IFD |  |  | 2026-03-20 |  | 2026-04-09 |  | 2026-04-10 |  | 2026-05-03 |  | 2026-06-18 |  | 0
| NEW | 2089 | LATER | IMI | SAU4005-G131-MAN-&MDA-11501 | Bypass Valve & PRDS(V) - Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | Bypass Valve & PRDS | IFA | IFP |  |  | 2026-03-20 |  | 2026-04-17 |  | 2026-04-10 |  | 2026-05-03 |  | 2026-06-18 |  | 0
|  | 2097 | LATER | IMEC | SAU4005-G127-LBG-&MDA-11160 | Safety Relief Valves(V) - Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | Safety Relief Valves | IFA | IFP |  |  | 2026-03-31 |  | 2026-04-01 |  | 2026-04-21 |  | 0 |  | 2026-06-29 |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 2098 | LATER | IMEC | SAU4005-G127-LBG-&MDA-11161 | Safety Relief Valves(V) - Data Sheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | Safety Relief Valves | IFA | IFD |  |  | 2026-03-31 |  | 2026-04-01 |  | 2026-04-21 |  | 0 |  |  |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 2099 | LATER | Samshin | SAU4005-G128-LBA-&MDA-11260 | Motor Operated Valve for Power Cycle(V) - Data Sheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | Motor Operated Valve | IFA | IFD |  |  | 2026-05-07 |  | 2026-05-20 |  | 2026-05-28 |  | 0 |  |  |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 2100 | LATER | Samshin | SAU4005-G128-LBA-&MDA-11261 | Motor Operated Valve for Power Cycle(V) - Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | Motor Operated Valve | IFA | IFP |  |  | 2026-05-07 |  | 2026-05-20 |  | 2026-05-28 |  | 0 |  | 2026-08-05 |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
| DOCUMENT CODE CHANGED | 2101 | LATER | Samshin | SAU4005-G128-LBA-&EFS-11265 | Motor Operated Valve for Power Cycle(V) - Schematic & Wiring Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | Motor Operated Valve | IFI | IFD | [14 empty] | 2026-05-07 |  | 2026-06-04 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
| DOCUMENT CODE CHANGED | 2102 | LATER | NRTec | SAU4005-G195-LBG-&MDA-11170 | Silencer(V) - Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | Silencer | IFA | IFP |  |  | 2026-03-16 |  | 2026-03-12 |  | 2026-04-06 |  | 2026-04-12 |  | 2026-06-14 |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
| DOCUMENT CODE CHANGED | 2103 | LATER | NRTec | SAU4005-G195-LBG-&MDA-11171 | Silencer(V) - Data Sheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | Silencer | IFA | IFD |  |  | 2026-03-16 |  | 2026-03-12 |  | 2026-04-06 |  | 2026-04-12 |  |  |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
|  | 2104 | LATER | AGMF | SAU4005-G108-LBA-&MDA-07760 | Atmospheric Flash Tank (V) - Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | Shop Fabricated Tank | IFA | IFP |  |  | 2026-05-01 |  | 2026-05-26 |  | 2026-05-22 |  | 0 |  | 2026-07-30 |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
| NEW | 2105 | LATER | AGMF | SAU4005-G108-LBA-&MDA-07761 | Atmospheric Flash Tank (V) - Valve list, Outline drawing and Data sheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | Shop Fabricated Tank | IFI | IFD | [14 empty] | 2026-05-13 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
| NEW | 2106 | LATER | AGMF | SAU4005-G108-LBA-&EEC-07762 | Atmospheric Flash Tank (V) - Instrument List and Data sheet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | Shop Fabricated Tank | IFI | IFD | [14 empty] | 2026-05-27 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
| NEW | 2107 | LATER | AGMF | SAU4005-G108-LBA-&MDA-07770 | TCA and FGH Vacuum Flash Tank (V) - Outline Drawing | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | Shop Fabricated Tank | IFA | IFP |  |  | 2026-05-01 |  | 2026-05-26 |  | 2026-05-22 |  | 0 |  | 2026-07-30 |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
| NEW | 2108 | LATER | AGMF | SAU4005-G108-LBA-&MDA-07771 | TCA and FGH Vacuum Flash Tank (V) - Valve list, Outline drawing and Data sheet | A1 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | MECHANICAL | DOOSAN | Shop Fabricated Tank | IFI | IFD | [14 empty] | 2026-05-27 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
| NEW | 2109 | LATER | AGMF | SAU4005-G108-LBA-&EEC-07772 | TCA and FGH Vacuum Flash Tank (V) - Instrument List and Data sheet | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation & Control | DOOSAN | Shop Fabricated Tank | IFI | IFD | [34 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA |  |  | NO
| NEW | 2110 | LATER | BORRI | SAU4005-G160-BRU-&EDA-22100 | UPS system for GT Package(V) - Technical Datasheet & Sizing calculation | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | UPS system for GT Package | IFA |  |  |  | 2026-06-16 |  | 2026-03-17 |  | 2026-09-16 |  | 2026-03-25 |  | 2026-09-16 |  | 2026-04-26
| NEW | 2111 | LATER | BORRI | SAU4005-G160-BRU-&EFA-22102 | UPS system for GT Package(V) - Single line diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | UPS system for GT Package | IFA |  |  |  | 2026-06-16 |  | 2026-03-17 |  | 2026-09-16 |  | 2026-03-25 |  | 2026-09-16 |  | 2026-04-26
| NEW | 2112 | LATER | BORRI | SAU4005-G160-BRU-&ELU-22103 | UPS system for GT Package(V) - General Arrangement diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | UPS system for GT Package | IFA |  |  |  | 2026-06-16 |  | 2026-03-17 |  | 2026-09-16 |  | 2026-01-15 |  | 2026-09-16 |  | 2026-04-26
| NEW | 2114 | LATER | BORRI | SAU4005-G160-BRU-&ELU-22104 | UPS system for GT Package(V) - Battery Rack and layout arrangement diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | UPS system for GT Package | IFA |  |  |  | 2026-06-30 |  | 2026-03-19 |  | 2026-09-30 |  | 2026-03-25 |  | 2026-09-30 |  | 0
| NEW | 2115 | LATER | BORRI | SAU4005-G160-BRU-&EFF-22105 | UPS system for GT Package(V) - Schematic Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | UPS system for GT Package | IFI | [15 empty] | 2026-07-16 |  | 2026-03-19
| NEW | 2116 | LATER | Innomotics | SAU4005-G192-BBA-&EEC-26600 | MV VFD(V) - Technical Specification | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | MV VFD | IFA |  |  |  | 2026-06-30 |  | 2026-04-15 |  | 2026-09-30 |  | 2026-04-26 |  | 2026-09-30 |  | 0
| dcc changed | 2117 | LATER | Innomotics | SAU4005-G192-BBA-&ELU-26601 | MV VFD(V) - Outline drawing | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | MV VFD | IFA |  |  |  | 2026-06-30 |  | 2026-04-16 |  | 2026-09-30 |  | 2026-04-26 |  | 2026-09-30 |  | 0
| NEW | 2118 | LATER | Innomotics | SAU4005-G192-BBA-&EFS-26602 | MV VFD(V) - Schematic and Wiring Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | MV VFD | IFI | [15 empty] | 2026-07-16 |  | 2026-04-15
| dcc changed | 2119 | LATER | Innomotics | SAU4005-G192-BBA-&EFA-26603 | MV VFD(V) - Single Line Diagram | A1 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | ELECTRICAL | DOOSAN | MV VFD | IFA |  |  |  | 2026-06-30 |  | 2026-04-16 |  | 2026-09-30 |  | 2026-04-26 |  | 2026-09-30 |  | 0
|  | 2121 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&MDA-06600 | Fuel Gas Compressor-(V) Data Sheet | G101 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Gas Compressor | IFA | IFD |  |  | 2025-07-15 |  | 2025-08-21 |  | 2025-08-04 |  | 2025-11-11 |  | 2025-09-09 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2122 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&MDC-06610 | Fuel Gas Compressor-(V) Installation,Operation and maintenance manual | G101 | Operation & Maintenacne | M-Mechanical engineering (normally including process engineering) | NO | O&M | General | SEPCOIII | Fuel Gas Compressor | IFI | IFC | [14 empty] | 2026-05-11 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2123 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&MEC-06620 | Fuel Gas Compressor-(V) Utility List | G101 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | GENERAL | General | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2025-07-13 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2124 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&MFB-06630 | Fuel Gas Compressor-(V) P & ID | G101 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Process | SEPCOIII | Fuel Gas Compressor | IFA | IFD |  |  | 2025-07-30 |  | 2025-08-04 |  | 2025-08-19 |  | 2025-09-07 |  | 2025-09-24 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| dcc changed | 2125 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&CLB-06640 | Fuel Gas Compressor-(V) Foundation Load Condition | G101 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2025-08-18 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2126 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&MLU-06650 | Fuel Gas Compressor-(V) General Arrangement | G101 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Fuel Gas Compressor | IFA | IFD |  |  | 2025-08-18 |  | 2025-08-04 |  | 2025-09-07 |  | 2025-10-15 |  | 2025-10-13 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2129 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&MLU-06653 | Fuel Gas Compressor-(V) Nitrogen Generator General Arrangement | G101 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | General | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2025-11-28 |  | 2025-08-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2130 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&MLU-06654 | Fuel Gas Compressor-(V) Interconnection piping ISO drawing between FGBC SKID and Fin Fan | G101 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | General | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2025-12-22 |  | 2026-01-08 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2131 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&MLU-06655 | Fuel Gas Compressor-(V) Interconnection piping supports drawing between FGBC SKID and Fin Fan | G101 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | General | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2025-12-22 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2132 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&MPB-06660 | Fuel Gas Compressor-(V) KKS List | G101 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | GENERAL | General | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2025-09-01 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2134 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&MLU-06657 | Fuel Gas Compressor-(V) Pressure Safty Valve Drawing | G101 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | PIPING&PLANT DESIGN | Piping | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2026-01-05 |  | 2025-11-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2135 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&MDA-06609 | Fuel Gas Compressor-(V) Pressure Safty Valve Datasheet | G101 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | PIPING&PLANT DESIGN | Piping | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2025-11-28 |  | 2025-11-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2136 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&MLU-06658 | Fuel Gas Compressor-(V) Pressure Relief Valve Drawing | G101 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | PIPING&PLANT DESIGN | Piping | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2026-01-05 |  | 2025-11-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2137 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&MDA-06602 | Fuel Gas Compressor-(V) Pressure Relief Valve Datasheet | G101 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | PIPING&PLANT DESIGN | Piping | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2025-11-28 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2138 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&MLU-06659 | Fuel Gas Compressor-(V) Gas Isolation Valve Drawing | G101 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | PIPING&PLANT DESIGN | Piping | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2026-01-05 |  | 2025-11-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2139 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&MDA-06603 | Fuel Gas Compressor-(V) Gas Isolation Valve Datasheet | G101 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | PIPING&PLANT DESIGN | Piping | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2025-11-28 |  | 2025-11-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2140 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&MLU-06690 | Fuel Gas Compressor-(V) Surge Control Valve Drawing | G101 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | PIPING&PLANT DESIGN | Piping | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2026-01-05 |  | 2025-11-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2141 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&MDA-06604 | Fuel Gas Compressor-(V) Surge Control Valve Datasheet | G101 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | PIPING&PLANT DESIGN | Piping | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2025-11-28 |  | 2025-11-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2142 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&MLU-06691 | Fuel Gas Compressor-(V) Vent Valve Drawing | G101 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | PIPING&PLANT DESIGN | Piping | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2026-01-05 |  | 2025-11-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2143 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&MDA-06605 | Fuel Gas Compressor-(V) Vent Valve Datasheet | G101 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | PIPING&PLANT DESIGN | Piping | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2025-11-28 |  | 2025-11-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2144 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&MTB-06670 | Fuel Gas Compressor-(V) 3d Model of compressor, coolers, noise hood & N2 generation | G101 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | PIPING&PLANT DESIGN | Piping | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2025-08-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2145 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&MPB-06661 | Fuel Gas Compressor-(V) Equipment List | G101 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | GENERAL | General | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2025-09-01 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2146 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&MPB-06662 | Fuel Gas Compressor-(V) Piping Line List | G101 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | GENERAL | General | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2025-11-28 |  | 2026-01-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2147 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&MLU-06692 | Fuel Gas Compressor-(V) Interconnection piping & ISO drawing for Nitrogen generation plant. | G101 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | PIPING&PLANT DESIGN | Piping | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2025-12-22 |  | 2026-03-31 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2149 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&MDA-06608 | Fuel Gas Compressor-(V) Curve | G101 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2025-08-18 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2150 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&MDA-06607 | Fuel Gas Compressor-(V) Nameplate | G101 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | GENERAL | General | SEPCOIII | Fuel Gas Compressor | IFA | IFD |  |  | 2026-01-05 |  | 2026-01-04 |  | 2026-01-25 |  | 2026-01-19 |  | 2026-03-02 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| dcc changed | 2151 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&ELD-06693 | Fuel Gas Compressor-(V) Cable tray layout drawing | G101 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | GENERAL | General | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2026-01-05 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2152 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&EDA-06701 | Fuel Gas Compressor-(V) Main Motor data sheet | G101 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fuel Gas Compressor | IFA | IFD |  |  | 2025-09-15 |  | 2025-09-25 |  | 2025-10-05 |  | 2025-10-14 |  | 2025-11-10 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2153 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&EDA-06702 | Fuel Gas Compressor-(V) Main motor curves | G101 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fuel Gas Compressor | IFA | IFD |  |  | 2025-09-15 |  | 2025-09-25 |  | 2025-10-05 |  | 0 |  | 2025-11-10 |  | 2025-10-12 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2154 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&EEC-06710 | Fuel Gas Compressor-(V) Electrical Load list | G101 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2025-07-13 |  | 2025-08-11 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2155 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&ELU-06720 | Fuel Gas Compressor-(V) Main Motor Outline drawing | G101 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fuel Gas Compressor | IFA | IFD |  |  | 2025-09-15 |  | 2025-09-25 |  | 2025-10-05 |  | 2025-10-12 |  | 2025-11-10 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2156 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&ELU-06721 | Fuel Gas Compressor-(V) Main Motor terminal box outline drawing | G101 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | GENERAL | General | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2025-09-15 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2157 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&ELU-06722 | Fuel Gas Compressor-(V) Main Motor Nameplate drawing | G101 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | NO | GENERAL | General | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2025-09-15 |  | 2025-09-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2158 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&ELU-06723 | Fuel Gas Compressor-(V) Soft starter Outline | G101 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | GENERAL | General | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2025-09-15 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2159 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&EDB-06800 | Fuel Gas Compressor-(V) Control system architecture | G101 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2026-01-05 |  | 2025-11-17 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| dcc changed | 2160 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&EPC-06810 | Fuel Gas Compressor-(V) Instruments list | G101 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Fuel Gas Compressor | IFA | IFD |  |  | 2026-01-05 |  | 2026-04-29 |  | 2026-01-25 |  | 0 |  | 2026-03-02 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2161 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&EMA-06820 | Fuel Gas Compressor-(V) Terminal Designations | G101 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2026-01-05 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2162 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&EMA-06821 | Fuel Gas Compressor-(V) System Operation & Control Philosophy | G101 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Fuel Gas Compressor | IFA | IFD |  |  | 2026-01-05 |  | 2025-11-05 |  | 2026-01-25 |  | 2025-11-24 |  | 2026-03-02 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| dcc changed | 2163 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&EMB-06822 | Fuel Gas Compressor-(V) Cable list | G101 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2026-01-05 |  | 2026-04-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2164 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&EFP-06830 | Fuel Gas Compressor-(V) I/O list | G101 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2025-08-10 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2165 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&ELU-06840 | Fuel Gas Compressor-(V) Control Panel dimensional drawings | G101 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2026-01-05 |  | 2025-11-17 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2166 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&EDA-06801 | Fuel Gas Compressor-(V) PLC Specification & Datasheet along with Catalogue | G101 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2026-01-05 |  | 2025-12-15 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2167 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&EFF-06860 | Fuel Gas Compressor-(V) Control Loop & Logic Diagram (in SAMA Format) | G101 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Fuel Gas Compressor | IFA | IFD |  |  | 2026-01-05 |  | 2026-02-09 |  | 2026-01-25 |  | 0 |  | 2026-03-02 |  | 2026-05-21 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| dcc changed | 2168 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&DDC-06823 | Fuel Gas Compressor-(V) Instrument Installation Hook-up Drawing | G101 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2026-01-05 |  | 2026-03-17 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| dcc changed | 2169 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&EFC-06850 | Fuel Gas Compressor-(V) PLC HMI Graphic Display | G101 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2026-01-05 |  | 2026-03-17 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2170 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&EMA-06824 | Fuel Gas Compressor-(V) Master Wiring Drawing | G101 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2026-01-05 |  | 2026-01-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| dcc changed | 2171 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&EQC-06811 | Fuel Gas Compressor-(V) PLC FAT/SAT Procedure | G101 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2026-01-05 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| dcc changed | 2172 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&EFF-06825 | Fuel Gas Compressor-(V) Cause and effect Matrix. | G101 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2026-01-05 |  | 2026-03-17 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2173 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&EMA-06826 | Fuel Gas Compressor-(V) Vibration Monitoring System Specification | G101 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2026-01-05 |  | 2025-12-15 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2174 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&BBF-06900 | Fuel Gas Compressor-(V) Packing List | G101 | Construction | B-Overall technology | NO | COMMISSIONING | General | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2026-05-25 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2175 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&BQA-06901 | Fuel Gas Compressor-(V) Inspection & Test Plan (ITP) | G101 | QA/QC | B-Overall technology | YES | QA/QC | General | SEPCOIII | Fuel Gas Compressor | IFA | IFD |  |  | 2025-08-18 |  | 2025-09-09 |  | 2025-09-07 |  | 0 |  | 2025-10-13 |  | 2025-12-07 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2176 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&BQA-06902 | Fuel Gas Compressor-(V) Mechnical test Procedure | G101 | QA/QC | B-Overall technology | YES | QA/QC | General | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2025-08-18 |  | 2025-09-09 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2177 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&BQA-06903 | Fuel Gas Compressor-(V) Painting procedure and Surface preparation & coating specification | G101 | QA/QC | B-Overall technology | YES | QA/QC | General | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2025-08-18 |  | 2025-10-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2178 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&BQA-06904 | Fuel Gas Compressor-(V) Main motor Painting procedure | G101 | QA/QC | B-Overall technology | YES | QA/QC | General | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2025-08-18 |  | 2025-10-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2179 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&BQA-06905 | Fuel Gas Compressor-(V) EOMR | G101 | QA/QC | B-Overall technology | NO | QA/QC | General | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2026-05-11 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2180 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&BQA-06907 | Fuel Gas Compressor-(V) Mechnical test Report | G101 | QA/QC | B-Overall technology | NO | QA/QC | General | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2026-05-25 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Open
|  | 2181 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&BTL-06908 | Fuel Gas Compressor-(V) Hazardous Area Classification Drawing | G101 | HSE | B-Overall technology | YES | GENERAL | General | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2026-11-14 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2182 | LATER | Ingersoll Rand | SAU4005-G101-EKH-&BQB-06909 | Fuel Gas Compressor-(V) HAZOP Risk Assessment | G101 | HSE | B-Overall technology | YES | GENERAL | General | SEPCOIII | Fuel Gas Compressor | IFI | IFD | [14 empty] | 2026-05-25 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2183 | LATER | ENERGAS | SAU4005-G102-EK_-&CLB-07000 | Fuel Gas conditioning system(V)- Foundation load and anchorage details | G102 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | Mechanical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-08-19 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2184 | LATER | ENERGAS | SAU4005-G102-EK_-&CLB-07001 | Fuel Gas conditioning system(V)- Grounding and earthing details | G102 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | ELECTRICAL | Electrical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-08-12 |  | 2025-09-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2185 | LATER | ENERGAS | SAU4005-G102-EK_-&ELU-07002 | Fuel Gas conditioning system(V)- LCP, PDB and Junction Box GA | G102 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-08-26 |  |  |  | 2025-09-15 |  |  |  | 2025-10-21 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2186 | LATER | ENERGAS | SAU4005-G102-EK_-&ETL-07003 | Fuel Gas conditioning system(V)- Cable trays Layout Drawing | G102 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-08-26 |  | 2025-09-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2187 | LATER | ENERGAS | SAU4005-G102-EK_-&EFB-07004 | Fuel Gas conditioning system(V)- Electrical devices Wiring Diagrams | G102 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-08-26 |  | 2025-09-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2188 | LATER | ENERGAS | SAU4005-G102-EK_-&EFB-07005 | Fuel Gas conditioning system(V)- Electrical Cable Schedule | G102 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-08-26 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2189 | LATER | ENERGAS | SAU4005-G102-EK_-&EFB-07006 | Fuel Gas conditioning system(V)- Single Line Diagram | G102 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-07-15 |  | 2025-09-25 |  | 2025-08-04 |  | 0 |  | 2025-09-09 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Open
|  | 2190 | LATER | ENERGAS | SAU4005-G102-EK_-&ETL-07007 | Fuel Gas conditioning system(V)- Lighting layout drawing | G102 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-08-26 |  | 2025-09-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2191 | LATER | ENERGAS | SAU4005-G102-EK_-&EFB-07008 | Fuel Gas conditioning system(V)- Electrical load list | G102 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-07-15 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2192 | LATER | ENERGAS | SAU4005-G102-EK_-&ECA-07009 | Fuel Gas conditioning system(V)- Illumination calculation | G102 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-08-26 |  |  |  | 2025-09-15 |  |  |  | 2025-10-21 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2193 | LATER | ENERGAS | SAU4005-G102-EK_-&MPC-07010 | Fuel Gas conditioning system(V)- Terminal Point List | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | GENERAL | General | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-08-26 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2194 | LATER | ENERGAS | SAU4005-G102-EK_-&MDB-07011 | Fuel Gas conditioning system(V)- Description & Control & Operation philosophy | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | GENERAL | General | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-08-26 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2196 | LATER | ENERGAS | SAU4005-G102-EK_-&MAB-07013 | Fuel Gas conditioning system(V)- Document list | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | GENERAL | General | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-08-26 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2197 | LATER | ENERGAS | SAU4005-G102-EK_-&MFE-07014 | Fuel Gas conditioning system(V)- Functional Description | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | GENERAL | General | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-08-26 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2198 | LATER | ENERGAS | SAU4005-G102-EK_-&EFB-07015 | Fuel Gas conditioning system(V)- I&C and control cabinet general arrangements diagram | G102 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Electrical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-09-23 |  | 2025-09-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2199 | LATER | ENERGAS | SAU4005-G102-EK_-&ELU-07016 | Fuel Gas conditioning system(V)- Instrument Location Plan | G102 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Electrical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-09-23 |  | 2025-11-20 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2200 | LATER | ENERGAS | SAU4005-G102-EK_-&EEC-07017 | Fuel Gas conditioning system(V)- Instrument List & Datasheet with catalogue | G102 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Electrical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-10-07 |  |  |  | 2025-10-27 |  |  |  | 2025-12-02 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2201 | LATER | ENERGAS | SAU4005-G102-EK_-&ECA-07019 | Fuel Gas conditioning system(V)- Thermowell calculation sheet | G102 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Electrical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-09-09 |  | 2025-09-17 |  | 2025-09-29 |  | 0 |  | 2025-11-04 |  | 2025-11-09 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2202 | LATER | ENERGAS | SAU4005-G102-EK_-&EFB-07020 | Fuel Gas conditioning system(V)- Instrument Hookup drawing | G102 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Electrical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-08-12 |  | 2025-09-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2203 | LATER | ENERGAS | SAU4005-G102-EK_-&EEC-07021 | Fuel Gas conditioning system(V)- IO List | G102 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Electrical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-08-12 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2204 | LATER | ENERGAS | SAU4005-G102-EK_-&EFB-07022 | Fuel Gas conditioning system(V)- Control Architecture drawing | G102 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Electrical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-06-24 |  | 2025-09-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2205 | LATER | ENERGAS | SAU4005-G102-EK_-&EFF-07023 | Fuel Gas conditioning system(V)- Control Loop & Logic Diagram (SAMA Format) | G102 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Electrical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-08-26 |  | 2025-09-25 |  | 2025-09-15 |  | 2025-08-26 |  | 2025-10-21 |  | 2026-02-05 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | YES |  |  |  |  | Open
|  | 2206 | LATER | ENERGAS | SAU4005-G102-EK_-&EFF-07024 | Fuel Gas conditioning system(V)- Junction Box Wiring Diagram | G102 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Electrical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-09-09 |  | 2025-09-17 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2207 | LATER | ENERGAS | SAU4005-G102-EK_-&EFT-07025 | Fuel Gas conditioning system(V)- List of software | G102 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Electrical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-08-26 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2208 | LATER | ENERGAS | SAU4005-G102-EK_-&MDA-07026 | Fuel Gas conditioning system(V)- Condensate Tank Data sheet | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-08-12 |  | 2025-08-05 |  | 2025-09-01 |  | 2025-08-27 |  | 2025-10-07 |  | 2025-12-04 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2209 | LATER | ENERGAS | SAU4005-G102-EK_-&MDA-07027 | Fuel Gas conditioning system(V)- Filters separator Data sheet | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-08-12 |  | 2025-08-05 |  | 2025-09-01 |  | 2025-08-27 |  | 2025-10-07 |  | 2025-11-20 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2210 | LATER | ENERGAS | SAU4005-G102-EK_-&MDA-07028 | Fuel Gas conditioning system(V)- KOD Data sheet | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-08-12 |  | 2025-08-05 |  | 2025-09-01 |  | 2025-08-27 |  | 2025-10-07 |  | 2025-11-20 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2211 | LATER | ENERGAS | SAU4005-G102-EK_-&MEC-07029 | Fuel Gas conditioning system(V)- Surface Preparation & CoatingSpecifications. | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-08-12 |  | 2025-08-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2212 | LATER | ENERGAS | SAU4005-G102-EK_-&MDA-07030 | Fuel Gas conditioning system(V)- Water Bath Heaters Skid Data sheet | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-08-12 |  | 2025-08-05 |  | 2025-09-01 |  | 2025-08-27 |  | 2025-10-07 |  | 2025-12-14 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2213 | LATER | ENERGAS | SAU4005-G102-EK_-&MEC-07031 | Fuel Gas conditioning system(V)- Insulation Specification | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-07-29 |  | 2025-12-11 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2215 | LATER | ENERGAS | SAU4005-G102-EK_-&EDA-07033 | Fuel Gas conditioning system(V)- Flowmeter Data Sheet | G102 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-08-12 |  | 2025-10-24 |  | 2025-09-01 |  | 2025-12-14 |  | 2025-10-07 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | YES |  |  |  |  | Open
|  | 2216 | LATER | ENERGAS | SAU4005-G102-EK_-&MFB-07034 | Fuel Gas conditioning system(V)- Hazardous area drawing | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-08-12 |  | 2025-09-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2217 | LATER | ENERGAS | SAU4005-G102-EK_-&MLU-07035 | Fuel Gas conditioning system(V)- General Arrangement & Layout drawings | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-08-12 |  | 2025-08-01 |  | 2025-09-01 |  | 2025-09-26 |  | 2025-10-07 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | YES |  |  |  |  | Open
|  | 2218 | LATER | ENERGAS | SAU4005-G102-EK_-&EDA-07036 | Fuel Gas conditioning system(V)- Gas Chromatograph Data Sheet | G102 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-08-12 |  |  |  | 2025-09-01 |  |  |  | 2025-10-07 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | YES |  |  |  |  | Open
|  | 2219 | LATER | ENERGAS | SAU4005-G102-EK_-&MDA-07037 | Fuel Gas conditioning system(V)- List of Specialties such as relief valves, silencers, etc | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-09-09 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2220 | LATER | ENERGAS | SAU4005-G102-EK_-&MDA-07038 | Fuel Gas conditioning system(V)- Cold Vent Stack Data sheet | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-08-26 |  | 2025-12-23 |  | 2025-09-15 |  | 2025-09-21 |  | 2025-10-21 |  | 2026-01-22 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2221 | LATER | ENERGAS | SAU4005-G102-EK_-&MCA-07039 | Fuel Gas conditioning system(V)- Sizing Calculation For Cold Vent Stack | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-08-26 |  | 2025-09-17 |  | 2025-09-15 |  | 2025-11-18 |  | 2025-10-21 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2223 | LATER | ENERGAS | SAU4005-G102-EK_-&MTB-07041 | Fuel Gas conditioning system(V)- 3D Model | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-09-09 |  | 2025-10-10 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2224 | LATER | ENERGAS | SAU4005-G102-EK_-&MFB-07042 | Fuel Gas conditioning system(V)- Nameplate drawing | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-07-15 |  | 2025-12-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2225 | LATER | ENERGAS | SAU4005-G102-EK_-&MPD-07043 | Fuel Gas conditioning system(V)- Equipment List. | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-08-12 |  | 2026-01-15 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2226 | LATER | ENERGAS | SAU4005-G102-EK_-&MPD-07044 | Fuel Gas conditioning system(V)- Valve List | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-08-12 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2227 | LATER | ENERGAS | SAU4005-G102-EK_-&MPD-07045 | Fuel Gas conditioning system(V)- Line List | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-08-12 |  | 2026-01-15 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2228 | LATER | ENERGAS | SAU4005-G102-EK_-&MDA-07046 | Fuel Gas conditioning system(V)- ESDV Skid Data sheet | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-08-12 |  |  |  | 2025-09-01 |  |  |  | 2025-10-07 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2229 | LATER | ENERGAS | SAU4005-G102-EK_-&MPD-07047 | Fuel Gas conditioning system(V)- Utility list | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-08-12 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2230 | LATER | ENERGAS | SAU4005-G102-EK_-&MFB-07048 | Fuel Gas conditioning system(V)- P&ID | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-07-15 |  | 2025-08-04 |  | 2025-08-04 |  | 2025-08-24 |  | 2025-09-09 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | YES |  |  |  |  | Open
|  | 2231 | LATER | ENERGAS | SAU4005-G102-EK_-&MCA-07049 | Fuel Gas conditioning system(V)- Pipe Sizing & Pressure Drop Calculation for all the skid and interconnecting piping | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-08-12 |  | 2025-10-13 |  | 2025-09-01 |  | 2025-11-18 |  | 2025-10-07 |  | 2026-05-12 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2232 | LATER | ENERGAS | SAU4005-G102-EK_-&MDA-07050 | Fuel Gas conditioning system(V)- PRS Skid 2 x 100% for HRSG Data sheet | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-08-12 |  |  |  | 2025-09-01 |  |  |  | 2025-10-07 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2233 | LATER | ENERGAS | SAU4005-G102-EK_-&MDA-07051 | Fuel Gas conditioning system(V)- commom PRS Skid 3 x 50% for GT #11 to GT #13 Data sheet | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-08-12 |  |  |  | 2025-09-01 |  |  |  | 2025-10-07 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
| DOCUMENT CODE CHANGED | 2234 | LATER | ENERGAS | SAU4005-G000-ZEN-&AQA-02600 | Fuel Gas conditioning system(V)- Meter Calibration certificate | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2026-01-14 |  | 2025-06-19 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
| DOCUMENT CODE CHANGED | 2235 | LATER | ENERGAS | SAU4005-G000-ZEN-&AQA-02512 | Fuel Gas conditioning system(V)- FAT ITP for Fuel Gas conditioning system(V)- | G102 | QA/QC | A-Overall management | YES | QA/QC | General | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-12-29 |  | 2025-08-21 |  | 2026-01-18 |  | 2025-08-21 |  | 2026-02-23 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | YES |  |  |  |  | Open
|  | 2236 | LATER | ENERGAS | SAU4005-G102-EK_-&AFB-07054 | Fuel Gas conditioning system(V)- Test procedure for Fuel Gas conditioning system(V)- | G102 | QA/QC | A-Overall management | YES | QA/QC | General | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-11-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2237 | LATER | ENERGAS | SAU4005-G102-EK_-&AFB-07055 | Fuel Gas conditioning system(V)- End of manufacture | G102 | QA/QC | A-Overall management | YES | QA/QC | General | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2026-02-28 |  |  |  | 2026-03-20 |  |  |  | 2026-04-25 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2238 | LATER | ENERGAS | SAU4005-G102-EK_-&AQC-07056 | Fuel Gas conditioning system(V)- Factory Acceptance Test Results Report-Quality document | G102 | QA/QC | A-Overall management | YES | QA/QC | General | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2026-01-29 |  |  |  | 2026-02-18 |  |  |  | 2026-03-26 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2239 | LATER | ENERGAS | SAU4005-G102-EK_-&MDC-07057 | Fuel Gas conditioning system(V)- O&M | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-11-29 |  |  |  | 2025-12-19 |  |  |  | 2026-01-24 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | YES |  |  |  |  | Open
|  | 2240 | LATER | ENERGAS | SAU4005-G102-EK_-&EFQ-07058 | Fuel Gas conditioning system(V)- Setpoint and alarm list | G102 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Electrical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-10-07 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2241 | LATER | ENERGAS | SAU4005-G102-EK_-&ETC-07059 | Fuel Gas conditioning system(V)- Erection, Commissioning, Startup, and Shutdown Manual | G102 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-12-29 |  |  |  | 2026-01-18 |  |  |  | 2026-02-23 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2242 | LATER | ENERGAS | SAU4005-G102-EK_-&MDD-07060 | Fuel Gas conditioning system(V)- Pump and motor curves | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-09-17 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2243 | LATER | ENERGAS | SAU4005-G102-EK_-&MDA-07061 | Fuel Gas conditioning system(V)- Data sheet of Pump Motor | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | ELECTRICAL | Electrical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-10-07 |  | 2025-09-17 |  | 2025-10-27 |  | 2025-10-02 |  | 2025-12-02 |  | 2026-04-13 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2244 | LATER | ENERGAS | SAU4005-G102-EK_-&MFB-07063 | Fuel Gas conditioning system(V)- Dispersion study of cold vent stack | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-10-07 |  | 2025-10-31 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2245 | LATER | ENERGAS | SAU4005-G102-EK_-&MFB-07064 | Fuel Gas conditioning system(V)- Nameplate drawings for units | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-12-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2247 | LATER | ENERGAS | SAU4005-G102-EK_-&MCA-07066 | Fuel Gas conditioning system(V)- Stress Calculation - main pipeline | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-11-07 |  | 2026-04-21 |  | 2025-11-27 |  | 2026-05-14 |  | 2026-01-02 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2249 | LATER | ENERGAS | SAU4005-G102-EK_-&MTL-07068 | Fuel Gas conditioning system(V)- Lifting Arrangement | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-11-29 |  | 2026-02-11 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2250 | LATER | ENERGAS | SAU4005-G102-EK_-&MDA-07069 | Fuel Gas conditioning system(V)- Pressure Safety Valve Data Sheet | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-11-07 |  | 2025-10-22 |  | 2025-11-27 |  | 2025-11-06 |  | 2026-01-02 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | YES |  |  |  |  | Open
| dcc changed | 2251 | LATER | ENERGAS | SAU4005-G102-EK_-&MTL-07070 | Fuel Gas conditioning system(V)- Gas Leak Detection System arrangement drawings | G102 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-11-07 |  | 2025-09-17 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2252 | LATER | ENERGAS | SAU4005-G102-EK_-&MCA-07071 | Fuel Gas conditioning system(V)- Calculation for temperature drop in the all PRCS skid due to joule-thomson effect. | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-11-29 |  |  |  | 2025-12-19 |  |  |  | 2026-01-24 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2253 | LATER | ENERGAS | SAU4005-G102-EK_-&AFB-07072 | Fuel Gas conditioning system(V)- Hydrostatic Test Procedures | G102 | QA/QC | A-Overall management | YES | QA/QC | General | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-11-07 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2254 | LATER | ENERGAS | SAU4005-G102-EK_-&MPB-07073 | Fuel Gas conditioning system(V)- Spare Parts & Special Tools List. | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-11-07 |  | 2025-12-23 |  | 2025-11-27 |  | 2026-01-08 |  | 2026-01-02 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2255 | LATER | ENERGAS | SAU4005-G102-EK_-&MTC-07074 | Fuel Gas conditioning system(V)- WPS | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFI | IFD | [14 empty] | 2025-11-07 |  | 2025-11-06 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2257 | LATER | ENERGAS | SAU4005-G102-EK_-&MQC-07076 | Fuel Gas conditioning system(V)- hydraulic test report and final inspection report | G102 | QA/QC | M-Mechanical engineering (normally including process engineering) | YES | QA/QC | General | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-12-29 |  |  |  | 2026-01-18 |  |  |  | 2026-02-23 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | YES |  |  |  |  | Open
|  | 2258 | LATER | ENERGAS | SAU4005-G102-EK_-&MCA-07077 | Fuel Gas conditioning system(V)- HRSG & Aux. boiler PRCS calculation | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-11-07 |  | 2025-09-17 |  | 2025-11-27 |  | 2025-10-05 |  | 2026-01-02 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2259 | LATER | ENERGAS | SAU4005-G102-EK_-&MCA-07078 | Fuel Gas conditioning system(V)- common GT PRCS calculation | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-11-07 |  | 2025-09-17 |  | 2025-11-27 |  | 2025-10-05 |  | 2026-01-02 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | NO |  |  |  |  | Open
|  | 2260 | LATER | ENERGAS | SAU4005-G102-EK_-&MDA-07079 | Fuel Gas conditioning system(V)- Fuel Gas Dew point Datasheet | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-11-07 |  | 2025-10-23 |  | 2025-11-27 |  | 2025-11-09 |  | 2026-01-02 |  | 2026-04-28 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | YES | YES |  |  |  |  | Open
|  | 2261 | LATER | ENERGAS | SAU4005-G102-EK_-&MDA-07080 | Fuel Gas conditioning system(V)- KOD outline drawing | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-08-12 |  |  |  | 2025-09-01 |  |  |  | 2025-10-07 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Open
|  | 2262 | LATER | ENERGAS | SAU4005-G102-EK_-&MDA-07081 | Fuel Gas conditioning system(V)- KOD calculation sheet | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-08-12 |  |  |  | 2025-09-01 |  |  |  | 2025-10-07 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Open
|  | 2263 | LATER | ENERGAS | SAU4005-G102-EK_-&MDA-07082 | Fuel Gas conditioning system(V)- Filters separator outline drawing | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-08-12 |  |  |  | 2025-09-01 |  |  |  | 2025-10-07 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Open
|  | 2264 | LATER | ENERGAS | SAU4005-G102-EK_-&MDA-07083 | Fuel Gas conditioning system(V)- Filters separator calculation sheet | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-08-12 |  |  |  | 2025-09-01 |  |  |  | 2025-10-07 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Open
|  | 2265 | LATER | ENERGAS | SAU4005-G102-EK_-&MDA-07084 | Fuel Gas conditioning system(V)- Condensate Tank outline drawing | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-08-12 |  |  |  | 2025-09-01 |  |  |  | 2025-10-07 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Open
|  | 2266 | LATER | ENERGAS | SAU4005-G102-EK_-&MDA-07085 | Fuel Gas conditioning system(V)- Condensate Tank calculation sheet | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-08-12 |  |  |  | 2025-09-01 |  |  |  | 2025-10-07 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Open
|  | 2267 | LATER | ENERGAS | SAU4005-G102-EK_-&MDA-07086 | Fuel Gas conditioning system(V)- Water Bath Heaters Skid outline drawing | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-08-12 |  |  |  | 2025-09-01 |  |  |  | 2025-10-07 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Open
|  | 2268 | LATER | ENERGAS | SAU4005-G102-EK_-&MDA-07087 | Fuel Gas conditioning system(V)- Water Bath Heaters Skid calculation sheet | G102 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel gas conditioning system | IFA | IFD |  |  | 2025-08-12 |  |  |  | 2025-09-01 |  |  |  | 2025-10-07 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Open
|  | 2270 | LATER | PERIC | SAU4005-G106-QJC-&MFB-07502 | Hydrogen Generation Plant(V)-PI&D Drawing for Hydrogen generation plant | G106 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Hydrogen Generation Plant | IFA | IFD |  |  | 2025-10-16 |  | 2025-09-05 |  | 2025-11-05 |  | 2025-10-06 |  | 2025-12-11 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2271 | LATER | PERIC | SAU4005-G106-QJC-&MTL-07503 | Hydrogen Generation Plant(V)-General Arrangement Drawing for Hydrogen generation plant | G106 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Hydrogen Generation Plant | IFA | IFD |  |  | 2025-10-30 |  | 2025-09-07 |  | 2025-11-19 |  | 2025-10-06 |  | 2025-12-25 |  | 2026-01-07 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2272 | LATER | PERIC | SAU4005-G106-QJC-&ELH-07504 | Hydrogen Generation Plant(V)-Earthing position diagram for Hydrogen generation plant | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | Electrical | Electrical | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-10-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2273 | LATER | PERIC | SAU4005-G106-QJC-&MTC-07505 | Hydrogen Generation Plant(V)-Pressure vessels diagram for Hydrogen generation plant | G106 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-13 |  | 2025-10-31 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2274 | LATER | PERIC | SAU4005-G106-QJC-&EPB-07506 | Hydrogen Generation Plant(V)-IO List for Hydrogen generation plant | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-13 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2275 | LATER | PERIC | SAU4005-G106-QJC-&MMB-07507 | Hydrogen Generation Plant(V)-Pipeline List for Hydrogen generation plant | G106 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2276 | LATER | PERIC | SAU4005-G106-QJC-&MPA-07508 | Hydrogen Generation Plant(V)-Valves List for Hydrogen generation plant | G106 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-13 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2277 | LATER | PERIC | SAU4005-G106-QJC-&EMA-07509 | Hydrogen Generation Plant(V)-Control Cable list for Hydrogen generation plant | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2025-10-23 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2278 | LATER | PERIC | SAU4005-G106-QJC-&EMA-07510 | Hydrogen Generation Plant(V)-Power Cable list for Hydrogen generation plant | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | Electrical | Electrical | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2025-09-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2279 | LATER | PERIC | SAU4005-G106-QJC-&EPC-07511 | Hydrogen Generation Plant(V)-Electrical loads list for Hydrogen generation plant | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | Electrical | Electrical | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-10-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2280 | LATER | PERIC | SAU4005-G106-QJC-&BDC-07512 | Hydrogen Generation Plant(V)-O&M Manual for Hydrogen generation plant | G106 | Operation & Maintenacne | A-Overall management | YES | General | General | SEPCOIII | Hydrogen Generation Plant | IFI | IFC | [14 empty] | 2025-10-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2281 | LATER | PERIC | SAU4005-G106-QJC-&CLB-07513 | Hydrogen Generation Plant(V)-Civil engineering drawing along with Loads | G106 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Hydrogen Generation Plant | IFA | IFD |  |  | 2025-10-30 |  | 2025-09-08 |  | 2025-11-19 |  | 0 |  | 2025-12-25 |  | 2025-11-20 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2282 | LATER | PERIC | SAU4005-G106-QJC-&EFF-07514 | Hydrogen Generation Plant(V)-Control System Configuration (System Architecture) of PLC | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-13 |  | 2025-09-11 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2283 | LATER | PERIC | SAU4005-G106-QJC-&EPB-07515 | Hydrogen Generation Plant(V)-Hardwire I/O Signal List (Package PLC to Main Plant DCS) | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Hydrogen Generation Plant | IFA | IFD |  |  | 2025-11-13 |  | 2025-09-12 |  | 2025-12-03 |  | 2025-09-26 |  | 2026-01-08 |  | 2026-02-09 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2284 | LATER | PERIC | SAU4005-G106-QJC-&EFP-07516 | Hydrogen Generation Plant(V)-Communication Signal List | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-13 |  | 2025-12-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2285 | LATER | PERIC | SAU4005-G106-QJC-&EFQ-07517 | Hydrogen Generation Plant(V)-Alarm and Set Point List | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-13 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2286 | LATER | PERIC | SAU4005-G106-QJC-&ELD-07518 | Hydrogen Generation Plant(V)-Cable Tray Design Specification and Routing Drawing | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2026-03-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2287 | LATER | PERIC | SAU4005-G106-QJC-&ECG-07519 | Hydrogen Generation Plant(V)-Based on Area classificaton all instruments, JBs, etc's., certification | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2026-01-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2288 | LATER | PERIC | SAU4005-G106-QJC-&BDA-07520 | Hydrogen Generation Plant(V)-Equipment data sheets | G106 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Hydrogen Generation Plant | IFA | IFD |  |  | 2025-11-13 |  | 2025-10-01 |  | 2025-12-03 |  | 2025-10-06 |  | 2026-01-08 |  | 2026-02-16 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2289 | LATER | PERIC | SAU4005-G106-QJC-&PPC-07521 | Hydrogen Generation Plant(V)-Equipment list | G106 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-10-30 |  | 2026-01-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2290 | LATER | PERIC | SAU4005-G106-QJC-&PPC-07522 | Hydrogen Generation Plant(V)-Chemicals & Consumables list | G106 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-10-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2291 | LATER | PERIC | SAU4005-G106-QJC-&PPC-07523 | Hydrogen Generation Plant(V)-Utility List | G106 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-10-30 |  | 2025-09-10 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2292 | LATER | PERIC | SAU4005-G106-QJC-&PPB-07524 | Hydrogen Generation Plant(V)-Spares Part List | G106 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2293 | LATER | PERIC | SAU4005-G106-QJC-&PPB-07525 | Hydrogen Generation Plant(V)-Special tools list | G106 | Project Management | C-Construction engineering (building construction and civil engineering) | YES | PIPING&PLANT DESIGN | PIPING | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2026-04-06 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2294 | LATER | PERIC | SAU4005-G106-QJC-&MDA-07526 | Hydrogen Generation Plant(V)-Piping arrangement drawing | G106 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2026-01-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2295 | LATER | PERIC | SAU4005-G106-QJC-&MDA-07527 | Hydrogen Generation Plant(V)-Piping Support drawing | G106 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2026-01-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2296 | LATER | PERIC | SAU4005-G106-QJC-&BBF-07528 | Hydrogen Generation Plant(V)-Packing and shipping instructions | G106 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2026-02-19 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2297 | LATER | PERIC | SAU4005-G106-QJC-&PPA-07529 | Hydrogen Generation Plant(V)-Hazard area classification drawing | G106 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Hydrogen Generation Plant | IFA | IFD |  |  | 2025-11-13 |  | 2025-09-24 |  | 2025-12-03 |  | 2025-10-09 |  | 2026-01-08 |  | 2026-03-29 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2298 | LATER | PERIC | SAU4005-G106-QJC-&MTB-07530 | Hydrogen Generation Plant(V)-3D Model | G106 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2026-02-28 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2299 | LATER | PERIC | SAU4005-G106-QJC-&AQA-07531 | Hydrogen Generation Plant(V)-FAT for hydrogen generation plant | G106 | Engineering | A-Overall management | YES | General | General | SEPCOIII | Hydrogen Generation Plant | IFA | IFD |  |  | 2025-11-27 |  | 2025-11-07 |  | 2025-12-17 |  | 2025-11-23 |  | 2026-01-22 |  | 2026-01-04 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2300 | LATER | PERIC | SAU4005-G106-QJC-&EPA-07532 | Hydrogen Generation Plant(V)-Instrument List | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2025-10-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2301 | LATER | PERIC | SAU4005-G106-QJC-&ELD-07533 | Hydrogen Generation Plant(V)-Instrument GA drawings | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2025-09-28 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2302 | LATER | PERIC | SAU4005-G106-QJC-&ELD-07534 | Hydrogen Generation Plant(V)-Instrument hook-up drawing in Purchaser's format | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2025-12-10 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2303 | LATER | PERIC | SAU4005-G106-QJC-&ELD-07535 | Hydrogen Generation Plant(V)-JB/Rack/Air header etc., Location Drawings | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2025-12-31 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2304 | LATER | PERIC | SAU4005-G106-QJC-&ECG-07536 | Hydrogen Generation Plant(V)-Calibration Certificates | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2026-02-19 |  | 2026-01-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2305 | LATER | PERIC | SAU4005-G106-QJC-&EPB-07537 | Hydrogen Generation Plant(V)-Soft Signal List | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2025-12-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2306 | LATER | PERIC | SAU4005-G106-QJC-&ELD-07538 | Hydrogen Generation Plant(V)-Gas Leak Detection system arrangement Drawing | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2025-11-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2308 | LATER | PERIC | SAU4005-G106-QJC-&EFF-07540 | Hydrogen Generation Plant(V)-Hydrogen Generation Plant --Control Logic Diagram & Narratives | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2025-11-23 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2309 | LATER | PERIC | SAU4005-G106-QJC-&EDA-07541 | Hydrogen Generation Plant(V)-Data sheets of all C&I items / equipment / cables in Purchaser format giving offered make and model no. along with catalogues and technical literature of C&I items | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Hydrogen Generation Plant | IFA | IFD |  |  | 2025-12-25 |  | 2025-12-03 |  | 2026-01-14 |  | 2025-12-30 |  | 2026-02-19 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2311 | LATER | PERIC | SAU4005-G106-QJC-&EDA-07543 | Hydrogen Generation Plant(V)-Motor Data Sheet | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | Electrical | Electrical | SEPCOIII | Hydrogen Generation Plant | IFA | IFD |  |  | 2025-10-30 |  | 2025-11-06 |  | 2025-11-19 |  | 2026-01-19 |  | 2025-12-25 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2312 | LATER | PERIC | SAU4005-G106-QJC-&ELU-07544 | Hydrogen Generation Plant(V)-Motor GA Drawing and Performance Curve | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | Electrical | Electrical | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-10-30 |  | 2026-01-12 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2313 | LATER | PERIC | SAU4005-G106-QJC-&EMB-07545 | Hydrogen Generation Plant(V)-Motor Electrical Wiring and Nameplate Details | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | Electrical | Electrical | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-10-30 |  | 2026-03-20 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2314 | LATER | PERIC | SAU4005-G106-QJC-&DQA-07546 | Hydrogen Generation Plant(V)-Motor Test Report | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | Electrical | Electrical | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2026-03-20 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2315 | LATER | PERIC | SAU4005-G106-QJC-&MDB-07547 | Hydrogen Generation Plant(V)-Equipment cross-section drawing | G106 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2025-10-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2316 | LATER | PERIC | SAU4005-G106-QJC-&PPA-07548 | Hydrogen Generation Plant(V)-Hazardous material list | G106 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-10-30 |  | 2025-09-10 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2317 | LATER | PERIC | SAU4005-G106-QJC-&MEC-07549 | Hydrogen Generation Plant(V)-Piping material specification | G106 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-10-30 |  | 2026-04-01 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2320 | LATER | PERIC | SAU4005-G106-QJC-&MDA-07552 | Hydrogen Generation Plant(V)-Isometric drawing for piping within Vendor Scope | G106 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2026-01-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2321 | LATER | PERIC | SAU4005-G106-QJC-&BDB-07553 | Hydrogen Generation Plant(V)-Nameplate Drawing | G106 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2025-11-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2322 | LATER | PERIC | SAU4005-G106-QJC-&BFE-07554 | Hydrogen Generation Plant(V)-System Functional Description | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2025-11-19 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2323 | LATER | PERIC | SAU4005-G106-QJC-&BPL-07555 | Hydrogen Generation Plant(V)-Terminal Point List | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2025-11-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2324 | LATER | PERIC | SAU4005-G106-QJC-&EFF-07556 | Hydrogen Generation Plant(V)-Cause and effect Diagram | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2025-11-23 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2326 | LATER | PERIC | SAU4005-G106-QJC-&ELU-07558 | Hydrogen Generation Plant(V)-Control Panel GA/IA Layout Drawing along with BOM | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2025-11-06 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2327 | LATER | PERIC | SAU4005-G106-QJC-&EMB-07559 | Hydrogen Generation Plant(V)-Control Panel Internal Wiring & Schematic Drawing | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2025-12-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2328 | LATER | PERIC | SAU4005-G106-QJC-&EDA-07560 | Hydrogen Generation Plant(V)-Junction Box Data sheet & GA drawings | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2025-12-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2329 | LATER | PERIC | SAU4005-G106-QJC-&EPC-07561 | Hydrogen Generation Plant(V)-Junction Box Schedule | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2025-12-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| dcc changed | 2330 | LATER | PERIC | SAU4005-G106-QJC-&EMB-07562 | Hydrogen Generation Plant(V)-I&C cable interconnection panel to panel | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2026-03-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| dcc changed | 2331 | LATER | PERIC | SAU4005-G106-QJC-&EMB-07563 | Hydrogen Generation Plant(V)-I&C cable interconnection JB to panel | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2026-03-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2332 | LATER | PERIC | SAU4005-G106-QJC-&EDA-07564 | Hydrogen Generation Plant(V)-I&C Cable Datasheet | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2025-12-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2333 | LATER | PERIC | SAU4005-G106-QJC-&EDA-07565 | Hydrogen Generation Plant(V)-PLC Specification & Datasheet along with Catalogue | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2025-10-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2334 | LATER | PERIC | SAU4005-G106-QJC-&EFC-07566 | Hydrogen Generation Plant(V)-DCS graphics screen | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2336 | LATER | PERIC | SAU4005-G106-QJC-&ELU-07568 | Hydrogen Generation Plant(V)-GA and Datasheet of Local Emergency Push Button Station(LPBS) | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | Electrical | Electrical | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2025-11-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2337 | LATER | PERIC | SAU4005-G106-QJC-&EDA-07569 | Hydrogen Generation Plant(V)-GA and Datasheet of Rectifier Unit | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | Electrical | Electrical | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2025-10-01 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2338 | LATER | PERIC | SAU4005-G106-QJC-&EPA-07570 | Hydrogen Generation Plant(V)-Electrical Equipment BOQ | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | Electrical | Electrical | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2025-11-20 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2339 | LATER | PERIC | SAU4005-G106-QJC-&ELU-07571 | Hydrogen Generation Plant(V)-GA drawing and Data sheet for MCC panels, PDB, Junction Box, LCP and other electrical equipment | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | Electrical | Electrical | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2025-10-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2340 | LATER | PERIC | SAU4005-G106-QJC-&EFA-07572 | Hydrogen Generation Plant(V)-SLD and Schematic diagram for Hydrogen generation plant with scope marking | G106 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | Electrical | Electrical | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 |  | 2025-10-01 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2342 | LATER | PERIC | SAU4005-G106-QJC-&EDD-07574 | Hydrogen Generation Plant(V)-Plant performance curves | G106 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-11-27 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2343 | LATER | PERIC | SAU4005-G106-QJC-&BQA-07575 | Hydrogen Generation Plant(V)-ITP for hydrogen generation plant | G106 | Engineering | A-Overall management | YES | General | General | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-12-14 |  | 2025-09-10 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2344 | LATER | PERIC | SAU4005-G106-QJC-&BQA-07576 | Hydrogen Generation Plant(V)-EOMR for hydrogen generation plant | G106 | Engineering | A-Overall management | YES | General | General | SEPCOIII | Hydrogen Generation Plant | IFI | IFD | [14 empty] | 2025-12-14 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2345 | LATER | LANPEC | SAU4005-G107-EGB-&MTC-07601 | Field Erected Tank(V)-General Arrangement Drawing of Fuel Oil Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFA | IFD |  |  | 2025-07-25 |  | 2025-07-16 |  | 2025-08-14 |  | 2025-08-20 |  | 2025-09-19 |  | 2025-11-09 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2346 | LATER | LANPEC | SAU4005-G107-EGB-&MTC-07602 | Field Erected Tank(V)-Bottom Plate Drawing of Fuel Oil Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-07-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2347 | LATER | LANPEC | SAU4005-G107-EGB-&MTC-07603 | Field Erected Tank(V)-Sheel Drawing of Fuel Oil Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-07-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2348 | LATER | LANPEC | SAU4005-G107-EGB-&MTC-07604 | Field Erected Tank(V)-Dome Roof Drawing of Fuel Oil Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-07-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2349 | LATER | LANPEC | SAU4005-G107-EGB-&MTC-07605 | Field Erected Tank(V)-Accessories Drawing of Fuel Oil Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-07-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2350 | LATER | LANPEC | SAU4005-G107-EGB-&MTC-07606 | Field Erected Tank(V)-Roof Platform Drawing of Fuel Oil Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-07-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2351 | LATER | LANPEC | SAU4005-G107-EGB-&MTC-07607 | Field Erected Tank(V)-Stairs Drawing of Fuel Oil Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-07-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2352 | LATER | LANPEC | SAU4005-G107-EGB-&MTC-07608 | Field Erected Tank(V)-Manhole M4 Drawing of Fuel Oil Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-07-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2353 | LATER | LANPEC | SAU4005-G107-EGB-&MTC-07609 | Field Erected Tank(V)-Manhole M1 Drawing of Fuel Oil Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-07-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2354 | LATER | LANPEC | SAU4005-G107-EGB-&MTC-07610 | Field Erected Tank(V)-Name Plate, Grounding Plates & Security Door Drawing of Fuel Oil Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFA | IFD |  |  | 2025-07-25 |  | 2025-07-29 |  | 2025-08-14 |  | 2025-08-20 |  | 2025-09-19 |  | 2025-11-09 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2355 | LATER | LANPEC | SAU4005-G107-EGB-&MED-07611 | Field Erected Tank(V)-Fuel Oil Storage Tank Calculations 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-14 |  | 2025-07-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2356 | LATER | LANPEC | SAU4005-G107-GHC-&MTC-07612 | Field Erected Tank(V)-General Arrangement Drawing of DM Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFA | IFD |  |  | 2025-07-25 |  | 2025-07-16 |  | 2025-08-14 |  | 2025-08-20 |  | 2025-09-19 |  | 2025-11-09 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2357 | LATER | LANPEC | SAU4005-G107-GHC-&MTC-07613 | Field Erected Tank(V)-Bottom Plate Drawing of DM Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-07-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2358 | LATER | LANPEC | SAU4005-G107-GHC-&MTC-07614 | Field Erected Tank(V)-Sheel Drawing of DM Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-07-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2359 | LATER | LANPEC | SAU4005-G107-GHC-&MTC-07615 | Field Erected Tank(V)-Dome Roof Drawing of DM Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-07-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2360 | LATER | LANPEC | SAU4005-G107-GHC-&MTC-07616 | Field Erected Tank(V)-Accessories Drawing of DM Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-07-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2361 | LATER | LANPEC | SAU4005-G107-GHC-&MTC-07617 | Field Erected Tank(V)-Roof Platform Drawing of DM Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-07-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2362 | LATER | LANPEC | SAU4005-G107-GHC-&MTC-07618 | Field Erected Tank(V)-Stairs Drawing of DM Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-07-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2363 | LATER | LANPEC | SAU4005-G107-GHC-&MTC-07619 | Field Erected Tank(V)-Manhole M2 Drawing of DM Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-08-09 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2364 | LATER | LANPEC | SAU4005-G107-GHC-&MTC-07620 | Field Erected Tank(V)-Manhole M1 Drawing of DM Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-07-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2365 | LATER | LANPEC | SAU4005-G107-GHC-&MTC-07621 | Field Erected Tank(V)-Name Plate, Grounding Plates & Security Door Drawing of DM Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFA | IFD |  |  | 2025-07-25 |  | 2025-07-29 |  | 2025-08-14 |  | 2025-08-24 |  | 2025-09-19 |  | 2025-11-09 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2366 | LATER | LANPEC | SAU4005-G107-GHC-&MED-07622 | Field Erected Tank(V)-DM Water Storage Tank Calculations 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-14 |  | 2025-07-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2367 | LATER | LANPEC | SAU4005-G107-GHD-&MTC-07623 | Field Erected Tank(V)-General Arrangement Drawing of Service Cum Fire Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFA | IFD |  |  | 2025-07-25 |  | 2025-07-16 |  | 2025-08-14 |  | 2025-08-20 |  | 2025-09-19 |  | 2025-11-09 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2368 | LATER | LANPEC | SAU4005-G107-GHD-&MTC-07624 | Field Erected Tank(V)-Bottom Plate Drawing of Service Cum Fire Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-07-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2369 | LATER | LANPEC | SAU4005-G107-GHD-&MTC-07625 | Field Erected Tank(V)-Sheel Drawing of Service Cum Fire Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-07-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2370 | LATER | LANPEC | SAU4005-G107-GHD-&MTC-07626 | Field Erected Tank(V)-Dome Roof Drawing of Service Cum Fire Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2371 | LATER | LANPEC | SAU4005-G107-GHD-&MTC-07627 | Field Erected Tank(V)-Accessories Drawing of Service Cum Fire Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2372 | LATER | LANPEC | SAU4005-G107-GHD-&MTC-07628 | Field Erected Tank(V)-Roof Platform Drawing of Service Cum Fire Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2373 | LATER | LANPEC | SAU4005-G107-GHD-&MTC-07629 | Field Erected Tank(V)-Stairs Drawing of Service Cum Fire Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2374 | LATER | LANPEC | SAU4005-G107-GHD-&MTC-07630 | Field Erected Tank(V)-Manhole M2 Drawing of Service Cum Fire Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-11-02 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2375 | LATER | LANPEC | SAU4005-G107-GHD-&MTC-07631 | Field Erected Tank(V)-Manhole M1 Drawing of Service Cum Fire Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2376 | LATER | LANPEC | SAU4005-G107-GHD-&MTC-07632 | Field Erected Tank(V)-Name Plate, Grounding Plates & Security Door Drawing of Service Cum Fire Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFA | IFD |  |  | 2025-07-25 |  | 2025-07-29 |  | 2025-08-14 |  | 2025-08-15 |  | 2025-09-19 |  | 2025-11-12 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
| dcc changed | 2377 | LATER | LANPEC | SAU4005-G107-GHD-&MED-07633 | Field Erected Tank(V)-Service Cum Fire Water Storage Tank Calculations 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-14 |  | 2025-07-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2378 | LATER | LANPEC | SAU4005-G107-GMG-&MTC-07634 | Field Erected Tank(V)-General Arrangement Drawing of HRSG Blow Down Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFA | IFD |  |  | 2025-07-25 |  | 2025-07-16 |  | 2025-08-14 |  | 2025-08-20 |  | 2025-09-19 |  | 2025-11-18 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2379 | LATER | LANPEC | SAU4005-G107-GMG-&MTC-07635 | Field Erected Tank(V)-Bottom Plate Drawing of HRSG Blow Down Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-07-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2380 | LATER | LANPEC | SAU4005-G107-GMG-&MTC-07636 | Field Erected Tank(V)-Sheel Drawing of HRSG Blow Down Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-07-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2381 | LATER | LANPEC | SAU4005-G107-GMG-&MTC-07637 | Field Erected Tank(V)-Cone Roof Drawing of HRSG Blow Down Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-11-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2382 | LATER | LANPEC | SAU4005-G107-GMG-&MTC-07638 | Field Erected Tank(V)-Accessories Drawing of HRSG Blow Down Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-07-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2383 | LATER | LANPEC | SAU4005-G107-GMG-&MTC-07639 | Field Erected Tank(V)-Roof Platform Drawing of HRSG Blow Down Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-07-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2384 | LATER | LANPEC | SAU4005-G107-GMG-&MTC-07640 | Field Erected Tank(V)-Stairs Drawing of HRSG Blow Down Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-07-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2385 | LATER | LANPEC | SAU4005-G107-GMG-&MTC-07641 | Field Erected Tank(V)-Manhole M2 Drawing of HRSG Blow Down Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-11-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2386 | LATER | LANPEC | SAU4005-G107-GMG-&MTC-07642 | Field Erected Tank(V)-Manhole M1 Drawing of HRSG Blow Down Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-07-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2387 | LATER | LANPEC | SAU4005-G107-GMG-&MTC-07643 | Field Erected Tank(V)-Name Plate, Grounding Plates & Security Door Drawing of HRSG Blow Down Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFA | IFD |  |  | 2025-07-25 |  | 2025-07-29 |  | 2025-08-14 |  | 2025-08-24 |  | 2025-09-19 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2388 | LATER | LANPEC | SAU4005-G107-GMG-&MED-07644 | Field Erected Tank(V)-HRSG Blow Down Water Storage Tank Calculations 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-14 |  | 2025-07-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2389 | LATER | LANPEC | SAU4005-G107-HSJ-&MTC-07645 | Field Erected Tank(V)-General Arrangement Drawing of Amonia Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFA | IFD |  |  | 2025-07-25 |  | 2025-07-16 |  | 2025-08-14 |  | 2025-08-20 |  | 2025-09-19 |  | 2025-11-09 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2390 | LATER | LANPEC | SAU4005-G107-HSJ-&MTC-07646 | Field Erected Tank(V)-Bottom Plate Drawing of Amonia Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-08-09 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2391 | LATER | LANPEC | SAU4005-G107-HSJ-&MTC-07647 | Field Erected Tank(V)-Sheel Drawing of Amonia Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-08-09 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2392 | LATER | LANPEC | SAU4005-G107-HSJ-&MTC-07648 | Field Erected Tank(V)-Dome Roof Drawing of Amonia Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-08-09 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2393 | LATER | LANPEC | SAU4005-G107-HSJ-&MTC-07649 | Field Erected Tank(V)-Accessories Drawing of Amonia Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-08-09 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2394 | LATER | LANPEC | SAU4005-G107-HSJ-&MTC-07650 | Field Erected Tank(V)-Roof Platform Drawing of Amonia Storage Tankk 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-08-09 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2395 | LATER | LANPEC | SAU4005-G107-HSJ-&MTC-07651 | Field Erected Tank(V)-Stairs Drawing of Amonia Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-08-09 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2396 | LATER | LANPEC | SAU4005-G107-HSJ-&MTC-07652 | Field Erected Tank(V)-Manhole M2 Drawing of Amonia Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-11-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2397 | LATER | LANPEC | SAU4005-G107-HSJ-&MTC-07653 | Field Erected Tank(V)-Manhole M1 Drawing of Amonia Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-25 |  | 2025-08-09 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2398 | LATER | LANPEC | SAU4005-G107-HSJ-&MTC-07654 | Field Erected Tank(V)-Name Plate, Grounding Plates & Security Door Drawing of Amonia Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFA | IFD |  |  | 2025-07-25 |  | 2025-08-09 |  | 2025-08-14 |  | 2025-08-20 |  | 2025-09-19 |  | 2025-11-18 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2399 | LATER | LANPEC | SAU4005-G107-HSJ-&MED-07655 | Field Erected Tank(V)-Amonia Storage Tank Calculations 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | IFD | [14 empty] | 2025-07-14 |  | 2025-07-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2400 | LATER | LANPEC | SAU4005-G107-EGB-&MTC-07656 | Field Erected Tank(V)-Fuel Oil Storage Tank foundationload data 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFA | IFD |  |  | 2025-07-25 |  |  |  | 2025-08-14 |  |  |  | 2025-09-19 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2401 | LATER | LANPEC | SAU4005-G107-GHC-&MTC-07657 | Field Erected Tank(V)-DM Water Storage Tank foundationload data 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFA | IFD |  |  | 2025-07-25 |  |  |  | 2025-08-14 |  |  |  | 2025-09-19 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2402 | LATER | LANPEC | SAU4005-G107-GHD-&MTC-07658 | Field Erected Tank(V)-Service Cum Fire Water Storage Tank foundationload data 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFA | IFD |  |  | 2025-07-25 |  |  |  | 2025-08-14 |  |  |  | 2025-09-19 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2403 | LATER | LANPEC | SAU4005-G107-GMG-&MTC-07659 | Field Erected Tank(V)-HRSG Blow Down Water Storage Tank foundationload data 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFA | IFD |  |  | 2025-07-25 |  |  |  | 2025-08-14 |  |  |  | 2025-09-19 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2404 | LATER | LANPEC | SAU4005-G107-HSJ-&MTC-07660 | Field Erected Tank(V)-Amonia Storage Tank foundationload data 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFA | IFD |  |  | 2025-07-25 |  |  |  | 2025-08-14 |  |  |  | 2025-09-19 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
| NEW | 2405 | LATER | LANPEC | SAU4005-G107-EGB-&MDA-07661 | FFT(V)-FLAME ARRESTOR Data Sheet of Fuel Oil Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | [15 empty] | 2026-01-08 |  | 2026-02-06 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2406 | LATER | LANPEC | SAU4005-G107-EGB-&MDA-07662 | FFT(V)-LEVEL INDICATOR Data Sheet of Fuel Oil Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | [15 empty] | 2026-01-08 |  | 2026-02-06 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2407 | LATER | LANPEC | SAU4005-G107-EGB-&MDA-07663 | FFT(V)-HEATERS Data Sheet of Fuel Oil Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | [15 empty] | 2026-01-08 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2408 | LATER | LANPEC | SAU4005-G107-EGB-&MDA-07664 | FFT(V)-FLOATING SUCTION Data Sheet of Fuel Oil Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | [15 empty] | 2026-01-08 |  | 2026-02-06 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2409 | LATER | LANPEC | SAU4005-G107-GHC-&MDA-07665 | FFT(V)-CO₂ ABSORBER DATA Sheet of DM Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | [15 empty] | 2026-01-08 |  | 2026-02-06 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2410 | LATER | LANPEC | SAU4005-G107-GHC-&MDA-07666 | FFT(V)-BREATHER VALVE Data Sheet of DM Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | [15 empty] | 2026-01-08 |  | 2026-02-06 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2411 | LATER | LANPEC | SAU4005-G107-GHC-&MDA-07667 | FFT(V)-LEVEL INDICATOR Data Sheet of DM Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | [15 empty] | 2026-01-08 |  | 2026-02-06 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2412 | LATER | LANPEC | SAU4005-G107-GHD-&MDA-07668 | FFT(V)-LEVEL INDICATOR Data Sheet of Service Cum Fire Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | [15 empty] | 2026-01-08 |  | 2026-02-06 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2413 | LATER | LANPEC | SAU4005-G107-GMG-&MDA-07669 | FFT(V)-LEVEL INDICATOR Data Sheet of HRSG Blow Down Water Storage Tank 1 & 2 | G107 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Field Erected Tanks | IFI | [15 empty] | 2026-01-08 |  | 2026-02-06 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2414 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&AAB-07800 | WTP&ETP(V)_EDL | G109 | Engineering | A-Overall management | NO | GENERAL | General | SEPCOIII | WTP&ETP | IFI | IFD | [16 empty] | 2025-11-05 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2415 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&PFB-07801 | WTP&ETP(V)_P&ID | G109 | Engineering | P-Process engineering (only if separation from M is required) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-09-15 |  |  |  | 2025-10-28 |  |  |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2416 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MTL-07802 | WTP&ETP(V)_GA | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-01 |  |  |  | 2025-10-23 |  |  |  | 2026-02-18 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2417 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MTL-07803 | WTP&ETP(V)_Layout drawing of WTP&ETP Building | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-07-24 |  |  |  | 2025-10-23 |  |  |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2418 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MTL-07804 | WTP&ETP(V)_Layout drawing of Outdoor RCC tank | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-09-22 |  |  |  | 2025-10-23 |  |  |  | 2025-11-30 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2419 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MTL-07805 | WTP&ETP(V)_Layout drawing of Thickener | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-09-18 |  |  |  | 2025-09-26 |  |  |  | 2025-10-05 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2420 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MTL-07806 | WTP&ETP(V)_Layout drawing of sludge dewatering system | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-09-22 |  |  |  | 2025-10-06 |  |  |  | 2025-10-30 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2421 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MTL-07807 | WTP&ETP(V)_Layout drawing of Outdoor water Tank | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-01 |  |  |  | 2025-09-26 |  |  |  | 2025-11-19 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2422 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MTL-07808 | WTP&ETP(V)_Layout drawing of Electric Building | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-10 |  |  |  | 2025-10-23 |  |  |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2423 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MTL-07809 | WTP&ETP(V)_Pipeline layout drawings for WTP&ETP | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2026-01-18 |  |  |  | 2025-11-09 |  |  |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2424 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07810 | WTP&ETP(V)_Outline drawing of Raw water chemical dosing system (NaOCl) | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-09-29 |  |  |  | 2025-10-06 |  |  |  | 2026-03-15 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2425 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07811 | WTP&ETP(V)_Outline drawing of FeCl3 Dosing system | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-09-29 |  |  |  | 2025-10-23 |  |  |  | 2026-01-11 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2426 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07812 | WTP&ETP(V)_Outline drawing of PAM Dosing system | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-09-29 |  |  |  | 2025-10-06 |  |  |  | 2026-01-15 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2427 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07813 | WTP&ETP(V)_Outline drawing of NaOH Dosing system | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-01 |  |  |  | 2025-10-29 |  |  |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2428 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07814 | WTP&ETP(V)_Outline drawing of HCl Dosing system | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-01 |  |  |  | 2025-10-23 |  |  |  | 2026-01-15 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2429 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07815 | WTP&ETP(V)_Outline drawing of NaOCl Dosing system | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-01 |  |  |  | 2025-10-29 |  |  |  | 2026-01-15 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2430 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07816 | WTP&ETP(V)_Outline drawing of Na2CO3 Dosing system | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-01 |  |  |  | 2025-10-27 |  |  |  | 2026-01-15 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2431 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07817 | WTP&ETP(V)_Outline drawing of Anti-oxidation bactericide Dosing system | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-01 |  |  |  | 2025-10-29 |  |  |  | 2026-01-15 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2432 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07818 | WTP&ETP(V)_Outline drawing of Sodium meta bi sulfate Dosing system | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-01 |  |  |  | 2025-10-29 |  |  |  | 2026-01-15 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2433 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07819 | WTP&ETP(V)_Outline drawing of Anti scalant Dosing system | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-01 |  |  |  | 2025-10-29 |  |  |  | 2026-01-11 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2434 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07820 | WTP&ETP(V)_Outline drawing of Calcium bicarbonate Dosing system | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-01 |  |  |  | 2025-10-29 |  |  |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2435 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07821 | WTP&ETP(V)_Outline drawing of Chlorination Dosing system | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-10 |  |  |  | 2025-10-06 |  |  |  | 2026-03-15 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2436 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07822 | WTP&ETP(V)_Outline drawing of NaOCl Storage tank | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-16 |  |  |  | 2025-10-29 |  |  |  | 2025-12-18 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2437 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07823 | WTP&ETP(V)_Outline drawing of HCl Storage tank | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-16 |  |  |  | 2025-10-29 |  |  |  | 2025-12-18 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2438 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07824 | WTP&ETP(V)_Outline drawing of NaOH Storage tank | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-16 |  |  |  | 2025-10-29 |  |  |  | 2025-12-18 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2439 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07825 | WTP&ETP(V)_Outline drawing of FeCl3 Storage tank | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-17 |  |  |  | 2025-10-29 |  |  |  | 2025-12-18 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2440 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07826 | WTP&ETP(V)_Outline drawing of Anti scalant Storage tank | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-17 |  |  |  | 2025-10-29 |  |  |  | 2025-12-18 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2441 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07827 | WTP&ETP(V)_Outline drawing of DAF | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD | [34 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2442 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07828 | WTP&ETP(V)_Outline drawing of DMF | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-10 |  |  |  | 2025-10-29 |  |  |  | 2025-12-18 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2443 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07829 | WTP&ETP(V)_Outline drawing of UF pre filter | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-01 |  |  |  | 2025-10-29 |  |  |  | 2025-12-11 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2444 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07830 | WTP&ETP(V)_Outline drawing of UF | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-01 |  |  |  | 2025-10-27 |  |  |  | 2025-12-03 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2445 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07831 | WTP&ETP(V)_Outline drawing of 1st pass RO | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-01 |  |  |  | 2025-10-27 |  |  |  | 2025-12-03 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2446 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07832 | WTP&ETP(V)_Outline drawing of 2nd pass RO | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-01 |  |  |  | 2025-10-27 |  |  |  | 2025-12-07 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2447 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07833 | WTP&ETP(V)_Outline drawing of EDI | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-01 |  |  |  | 2025-10-27 |  |  |  | 2025-12-28 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2448 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07834 | WTP&ETP(V)_Outline drawing of 1st Pass RO permeate water tank | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-16 |  |  |  | 2025-10-29 |  |  |  | 2025-12-18 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2449 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07835 | WTP&ETP(V)_Outline drawing of 2nd Pass RO permeate water tank | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-16 |  |  |  | 2025-10-29 |  |  |  | 2025-12-18 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2450 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07836 | WTP&ETP(V)_Outline drawing of ETP storage tank | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-16 |  |  |  | 2025-10-29 |  |  |  | 2025-12-17 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2451 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07837 | WTP&ETP(V)_Outline drawing of ETP RO | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-01 |  |  |  | 2025-10-27 |  |  |  | 2025-12-17 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2452 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07838 | WTP&ETP(V)_Outline drawing of Fiter press | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-19 |  |  |  | 2025-10-06 |  |  |  | 2025-12-18 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2453 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07839 | WTP&ETP(V)_Outline drawing of Sludge silo | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-20 |  |  |  | 2025-10-06 |  |  |  | 2025-12-17 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2454 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07840 | WTP&ETP(V)_Outline drawing of Air Blowers | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-16 |  |  |  | 2025-10-30 |  |  |  | 2025-11-18 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2455 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07841 | WTP&ETP(V)_Outline drawing of Acid mist absorber | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-16 |  |  |  | 2025-10-30 |  |  |  | 2025-11-19 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2456 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07842 | WTP&ETP(V)_Outline drawing of Safety shower | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-16 |  |  |  | 2025-10-30 |  |  |  | 2025-11-19 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2457 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07843 | WTP&ETP(V)_Outline drawing of Air storage tank | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-10 |  |  |  | 2025-10-29 |  |  |  | 2025-12-24 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2458 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07844 | WTP&ETP(V)_Outline drawing of Pipeline mixer | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-16 |  |  |  | 2025-10-30 |  |  |  | 2025-11-19 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2459 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07845 | WTP&ETP(V)_Outline drawing of High pressure pump | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-19 |  |  |  | 2025-10-29 |  |  |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2460 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07846 | WTP&ETP(V)_Outline drawing of Self priming pump | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-19 |  |  |  | 2025-10-29 |  |  |  | 2025-11-18 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2461 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07847 | WTP&ETP(V)_Outline drawing of Centrifugal pump | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-22 |  |  |  | 2025-11-06 |  |  |  | 2025-11-30 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2462 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07848 | WTP&ETP(V)_Outline drawing of Magnetic pump | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-22 |  |  |  | 2025-11-09 |  |  |  | 2025-12-03 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2463 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07849 | WTP&ETP(V)_Outline drawing of Screw pump | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-22 |  |  |  | 2025-10-27 |  |  |  | 2025-12-03 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2464 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07850 | WTP&ETP(V)_Outline drawing of Gate | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-16 |  |  |  | 2025-10-30 |  |  |  | 2025-11-18 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2465 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07851 | WTP&ETP(V)_Outline drawing of UF CIP system | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-16 |  |  |  | 2025-10-30 |  |  |  | 2025-12-03 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2466 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07852 | WTP&ETP(V)_Outline drawing of RO&EDI CIP system | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-16 |  |  |  | 2025-10-30 |  |  |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2467 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07853 | WTP&ETP(V)_Data sheet | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-30 |  |  |  | 2025-10-28 |  |  |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2468 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07854 | WTP&ETP(V)_Piping Isometric drawings | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFI | IFD | [16 empty] | 2025-11-25 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2469 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDA-07855 | WTP&ETP(V)_Nameplate drawing | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-11-10 |  |  |  | 0 |  |  |  | 2025-11-23 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2470 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MED-07856 | WTP&ETP(V)_Process calculation | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-09-18 |  |  |  | 2025-09-26 |  |  |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2471 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MED-07857 | WTP&ETP(V)_Mass balance diagram | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-09-24 |  |  |  | 0 |  |  |  | 2025-12-23 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2472 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MED-07858 | WTP&ETP(V)_Hydraulic flow diagram | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFI | IFD | [16 empty] | 2025-11-03 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2473 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MDC-07859 | WTP&ETP(V)_O&M manual | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFI | IFD | [34 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2474 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MEC-07860 | WTP&ETP(V)_Paint procedure | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-27 |  |  |  | 2025-10-23 |  |  |  | 2026-02-26 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2475 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MPC-07861 | WTP&ETP(V)_Valve list | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFI | IFD | [16 empty] | 2025-12-10 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2476 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MPD-07862 | WTP&ETP(V)_Equipment list | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFI | IFD | [16 empty] | 2025-11-05 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2477 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MPD-07863 | WTP&ETP(V)_Piping line list | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFI | IFD | [16 empty] | 2025-11-05 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2478 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MPD-07864 | WTP&ETP(V)_Utility and Load List | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFI | IFD | [16 empty] | 2025-11-05 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2479 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MPD-07865 | WTP&ETP(V)_Chemicals & Consumables list | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFI | IFD | [16 empty] | 2025-11-05 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2480 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MTB-07866 | WTP&ETP(V)_3D Model | G109 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFI | IFD | [16 empty] | 2025-11-18 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2481 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EPD-07867 | WTP&ETP(V)_Instrument List | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | I&C&DCS | Instrumentation and Control | SEPCOIII | WTP&ETP | IFI | IFD | [16 empty] | 2025-10-22 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2482 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EDA-07868 | WTP&ETP(V)_Instrument Datasheet | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | I&C&DCS | Instrumentation and Control | SEPCOIII | WTP&ETP | IFI | IFD | [16 empty] | 2025-10-29 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2483 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EDC-07869 | WTP&ETP(V)_Hook up drawing | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | I&C&DCS | Instrumentation and Control | SEPCOIII | WTP&ETP | IFI | IFD | [16 empty] | 2025-11-03 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2484 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&ELD-07870 | WTP&ETP(V)_Instrument/JB location drawing | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | I&C&DCS | Instrumentation and Control | SEPCOIII | WTP&ETP | IFI | IFD | [16 empty] | 2025-11-03 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2485 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFE-07871 | WTP&ETP(V)_Control philosophy | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | I&C&DCS | Instrumentation and Control | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-11-05 |  |  |  | 2026-02-16 |  |  |  | 2026-04-02 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2486 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFC-07872 | WTP&ETP(V)_HMI graphics | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | I&C&DCS | Instrumentation and Control | SEPCOIII | WTP&ETP | IFI | IFD | [16 empty] | 2025-11-05 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2487 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFC-07873 | WTP&ETP(V)_PLC Datasheet along with Catalogue | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | I&C&DCS | Instrumentation and Control | SEPCOIII | WTP&ETP | IFA | IFD | [34 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2488 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFF-07874 | WTP&ETP(V)_Control Loop & Logic Diagram | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | I&C&DCS | Instrumentation and Control | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-11-05 |  |  |  | 0 |  |  |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2489 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFP-07875 | WTP&ETP(V)_DCS I/O List | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | I&C&DCS | Instrumentation and Control | SEPCOIII | WTP&ETP | IFI | IFD | [16 empty] | 2025-10-19 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2490 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFP-07876 | WTP&ETP(V)_PLC I/O List | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | I&C&DCS | Instrumentation and Control | SEPCOIII | WTP&ETP | IFI | IFD | [16 empty] | 2025-11-05 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2491 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFP-07877 | WTP&ETP(V)_Communicated signal list | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | I&C&DCS | Instrumentation and Control | SEPCOIII | WTP&ETP | IFI | IFD | [16 empty] | 2025-11-05 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2492 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EMA-07878 | WTP&ETP(V)_Interconnection wiring diagram | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | I&C&DCS | Instrumentation and Control | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-29 |  |  |  | 2025-11-19 |  |  |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2493 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EEC-07879 | WTP&ETP(V)_Electric load list | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFI | IFD | [16 empty] | 2025-10-16 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2494 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EMB-07880 | WTP&ETP(V)_Cable Schedule for WTP&ETP | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFI | IFD | [16 empty] | 2025-11-10 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2495 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&ETL-07881 | WTP&ETP(V)_Electrical Equipment Layout drawing | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-11-10 |  |  |  | 2025-11-23 |  |  |  | 2026-01-19 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2496 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&ETL-07882 | WTP&ETP(V)_Cable raceway layout | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-11-10 |  |  |  | 2025-10-23 |  |  |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2497 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07883 | WTP&ETP(V)_Electrical schematic diagram of LV control cabinet | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-09-14 |  |  |  | 2025-09-26 |  |  |  | 2025-10-27 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2498 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07884 | WTP&ETP(V)_Electrical schematic diagram of button box | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-11-05 |  |  |  | 2025-11-20 |  |  |  | 2025-12-09 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2499 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07885 | WTP&ETP(V)_Electrical schematic diagram of Control box for inlet valve of DAF | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-19 |  |  |  | 0 |  |  |  | 2025-10-27 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2500 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07886 | WTP&ETP(V)_Electrical schematic diagram of DMF control box | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-19 |  |  |  | 0 |  |  |  | 2025-10-27 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2501 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07887 | WTP&ETP(V)_Electrical schematic diagram of UF pre filter control box | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-19 |  |  |  | 0 |  |  |  | 2025-10-27 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2502 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07888 | WTP&ETP(V)_Electrical schematic diagram of UF control box | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-19 |  |  |  | 0 |  |  |  | 2025-10-27 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2503 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07889 | WTP&ETP(V)_Electrical schematic diagram of 1st pass RO control box | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-19 |  |  |  | 0 |  |  |  | 2025-10-27 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2504 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07890 | WTP&ETP(V)_Electrical schematic diagram of the control box for the service water tank inlet valve | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-19 |  |  |  | 0 |  |  |  | 2025-10-27 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2505 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07891 | WTP&ETP(V)_Electrical schematic diagram of RO washing pump reflux valve control box | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-19 |  |  |  | 0 |  |  |  | 2025-10-27 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2506 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07892 | WTP&ETP(V)_Electrical schematic diagram of 2nd pass RO control box | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-19 |  |  |  | 0 |  |  |  | 2025-10-27 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2507 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07893 | WTP&ETP(V)_Electrical schematic diagram of EDI control cabinet | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-19 |  |  |  | 0 |  |  |  | 2025-10-27 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2508 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07894 | WTP&ETP(V)_Electrical schematic diagram of ETP RO control box | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-19 |  |  |  | 0 |  |  |  | 2025-10-27 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2509 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07895 | WTP&ETP(V)_Electrical schematic diagram of pneumatic valve control box for sludge thickener | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-19 |  |  |  | 0 |  |  |  | 2025-10-27 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2510 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07896 | WTP&ETP(V)_Electrical schematic diagram of sludge silo control box | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-09-14 |  |  |  | 2025-09-30 |  |  |  | 2026-02-18 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2511 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07897 | WTP&ETP(V)_Electrical schematic diagram of UF CIP control box | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-19 |  |  |  | 0 |  |  |  | 2025-10-27 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2512 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07898 | WTP&ETP(V)_Electrical schematic diagram of RO/EDI CIP control box | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-10-19 |  |  |  | 0 |  |  |  | 2025-10-27 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2513 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07899 | WTP&ETP(V)_Electrical schematic diagram of Raw water chemical dosing control box | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-09-14 |  |  |  | 2025-09-26 |  |  |  | 2025-10-27 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2514 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07900 | WTP&ETP(V)_Electrical schematic diagram of NaClO Dosing system control box | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-09-14 |  |  |  | 2025-09-26 |  |  |  | 2025-10-27 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2515 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07901 | WTP&ETP(V)_Electrical schematic diagram of FeCL3 Dosing system control box | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-09-14 |  |  |  | 2025-09-26 |  |  |  | 2025-10-27 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2516 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07902 | WTP&ETP(V)_Electrical schematic diagram of Na2CO3 Dosing system control box | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-09-14 |  |  |  | 2025-09-26 |  |  |  | 2025-10-27 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 2517 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07903 | WTP&ETP(V)_Electrical schematic diagram of PAM Dosing system control box | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-09-14 |  |  |  | 2025-09-26 |  |  |  | 2025-10-27 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
|  | 2518 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07904 | WTP&ETP(V)_Electrical schematic diagram of HCL Dosing system control box | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-09-14 |  |  |  | 2025-09-26 |  |  |  | 2025-10-27 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2519 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07905 | WTP&ETP(V)_Electrical schematic diagram of SMBS Dosing system control box | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-09-14 |  |  |  | 2025-09-26 |  |  |  | 2025-10-27 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2520 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07906 | WTP&ETP(V)_Electrical schematic diagram of Anti scalant Dosing system control box | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-09-14 |  |  |  | 2025-09-26 |  |  |  | 2025-10-27 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2521 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07907 | WTP&ETP(V)_Electrical schematic diagram of NaOH Dosing system control box | G109 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFC |  |  |  |  | 2025-09-14 |  |  |  | 2025-09-26 |  |  |  | 2025-10-27 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2522 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07908 | WTP&ETP(V)_Electrical schematic diagram of Ca(HCO3)2 Dosing system control box |  | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-09-14 |  |  |  | 2025-09-26 |  |  |  | 2025-10-27 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2523 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07909 | WTP&ETP(V)_Electrical schematic diagram of Non-Oxidizing Biocide dosing system) control box |  | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-09-14 |  |  |  | 2025-09-26 |  |  |  | 2025-10-27 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2524 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07910 | WTP&ETP(V)_Electrical schematic diagram of Magnetic pump control box |  | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-09-14 |  |  |  | 2025-09-26 |  |  |  | 2025-10-27 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2525 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07911 | WTP&ETP(V)_Electrical schematic diagram of PLC control cabinet including the wiring diagram of I&C cables |  | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-11-05 |  |  |  | 0 |  |  |  | 2025-11-20 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2526 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EPD-07912 | WTP&ETP(V)_Junction Box/Local Panel List |  | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFI | IFD | [16 empty] | 2025-11-06 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2527 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MQC-07913 | WTP&ETP(V)_ITP |  | QA/QC | M-Mechanical engineering (normally including process engineering) | NO | QA/QC | General | SEPCOIII | WTP&ETP | IFA | IFD | [36 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2528 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MQC-07914 | WTP&ETP(V)_Test procedure |  | QA/QC | M-Mechanical engineering (normally including process engineering) | NO | QA/QC | General | SEPCOIII | WTP&ETP | IFI | IFD | [16 empty] | 2025-09-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2529 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MPB-07917 | WTP&ETP(V)_Special tools list |  | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFI | IFD | [16 empty] | 2026-01-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2530 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MPB-07916 | WTP&ETP(V)_Startup, 2-Year Spares List |  | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFA | IFD | [36 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2531 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07915 | WTP&ETP(V)_Motor GA & Datasheet include MOV GA and data sheet |  | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFI | IFD | [14 empty] | 2025-10-21 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2532 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MPL-07918 | WTP&ETP(V)_TP list |  | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | WTP&ETP | IFI | IFD | [14 empty] | 2025-10-21 |  | 2025-11-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2533 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&MQC-07919 | WTP&ETP(V)_End of manufacturing report |  | Engineering | M-Mechanical engineering (normally including process engineering) | NO | QA/QC | General | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2026-03-29 |  |  |  | 2026-05-14 |  |  |  | 0 |  | 2025-10-21 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2534 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07920 | WTP&ETP(V)_Electrical schematic diagram of Bleaching powder Dosing system control box |  | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2025-09-14 |  |  |  | 2025-09-26 |  |  |  | 2025-10-27 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2535 | LATER | JIANGSU TIANMA | SAU4005-G109-G__-&EFS-07921 | WTP&ETP(V)_Training Materials |  | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | WTP&ETP | IFA | IFD |  |  |  |  | 2026-01-18 |  |  |  | 2026-02-09 |  |  |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2536 | LATER | JIANGSU TIANMA | SAU4005-G114-GNB-&AAB-08801 | OWS(V)_Engineering Master Document List (MDL) of Oil Water Separator | G114 | Project Management | A-Overall management | YES | GENERAL | General | SEPCOIII | OWS | IFI | IFD | [14 empty] | 2025-11-16 |  | 2026-02-09 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2537 | LATER | JIANGSU TIANMA | SAU4005-G114-GNB-&EFB-08802 | OWS(V)_P&ID of Oil Water Separator | G114 | Engineering | P-Process engineering (only if separation from M is required) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | OWS | IFA | IFD |  |  | 2025-12-12 |  | 2025-12-16 |  | 2026-01-01 |  | 2026-01-21 |  | 2026-02-06 |  | 2026-04-28 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2538 | LATER | JIANGSU TIANMA | SAU4005-G114-GNB-&MTL-08803 | OWS(V)_General arrangement of Oil Water Separator | G114 | Construction | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | OWS | IFA | IFC |  |  | 2025-12-19 |  | 2026-01-06 |  | 2026-01-08 |  | 2025-12-30 |  | 2026-02-13 |  | 2026-02-16 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2539 | LATER | JIANGSU TIANMA | SAU4005-G114-GNB-&MTL-08804 | OWS(V)_Oil Water Separator piping layout | G114 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | OWS | IFA | IFC |  |  | 2025-12-26 |  | 2026-04-02 |  | 2026-01-15 |  | 2026-01-21 |  | 2026-02-20 |  | 2026-04-28 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2540 | LATER | JIANGSU TIANMA | SAU4005-G114-GNB-&MDA-08805 | OWS(V)_Oil Water Separator GA | G114 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | OWS | IFA | IFC |  |  | 2025-12-13 |  | 2025-12-16 |  | 2026-01-02 |  | 2025-12-30 |  | 2026-02-07 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2541 | LATER | JIANGSU TIANMA | SAU4005-G114-GNB-&MDA-08806 | OWS(V)_Oil lift pump GA | G114 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | OWS | IFA | IFC |  |  | 2025-12-14 |  | 2025-12-16 |  | 2026-01-03 |  | 2025-12-30 |  | 2026-02-08 |  | 2026-05-12 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2542 | LATER | JIANGSU TIANMA | SAU4005-G114-GNB-&MDA-08807 | OWS(V)_GA of Oil storage tank | G114 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | OWS | IFA | IFC |  |  | 2025-12-15 |  | 2025-12-16 |  | 2026-01-04 |  | 2025-12-30 |  | 2026-02-09 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2543 | LATER | JIANGSU TIANMA | SAU4005-G114-GNB-&MDA-08808 | OWS(V)_GA of Sludge storage tank | G114 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | OWS | IFA | IFC |  |  | 2025-12-15 |  | 2025-12-16 |  | 2026-01-04 |  | 2025-12-30 |  | 2026-02-09 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2544 | LATER | JIANGSU TIANMA | SAU4005-G114-GNB-&MDA-08809 | OWS(V)_GA of Oil skimmer | G114 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | OWS | IFA | IFC |  |  | 2025-12-14 |  | 2026-01-06 |  | 2026-01-03 |  | 2025-12-30 |  | 2026-02-08 |  | 2026-01-21 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2545 | LATER | JIANGSU TIANMA | SAU4005-G114-GNB-&MPD-08810 | OWS(V)_Equipment list of Oil Water Separator | G114 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | OWS | IFI | IFD | [14 empty] | 2025-12-08 |  | 2025-12-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2546 | LATER | JIANGSU TIANMA | SAU4005-G114-GNB-&MEB-08811 | OWS(V)_Valve list of Oil Water Separator | G114 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | OWS | IFI | IFD | [14 empty] | 2025-12-19 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2547 | LATER | JIANGSU TIANMA | SAU4005-G114-GNB-&BFE-08812 | OWS(V)_Functional Description of Oil Water Separator(control philoshopy,List of alarms and signals) | G114 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | OWS | IFI | IFD | [14 empty] | 2026-01-04 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2548 | LATER | JIANGSU TIANMA | SAU4005-G114-GNB-&BFF-08813 | OWS(V)_Logic diagram of Oil Water Separator | G114 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | OWS | IFA | IFD |  |  | 2026-01-08 |  | 2026-04-01 |  | 2026-01-28 |  | 2026-01-21 |  | 2026-03-05 |  | 2026-04-28 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2549 | LATER | JIANGSU TIANMA | SAU4005-G114-GNB-&EDC-08814 | OWS(V)_Instrument List of Oil Water Separator | G114 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | I&C&DCS | Instrumentation and Control | SEPCOIII | OWS | IFI | IFD | [14 empty] | 2025-12-19 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2550 | LATER | JIANGSU TIANMA | SAU4005-G114-GNB-&EDA-08815 | OWS(V)_Instrument datasheet of Oil Water Separator | G114 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | OWS | IFI | IFD | [14 empty] | 2025-12-20 |  | 2025-12-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2551 | LATER | JIANGSU TIANMA | SAU4005-G114-GNB-&EDC-08816 | OWS(V)_Loop drawing and hookup for instrument of Oil Water Separator | G114 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | OWS | IFI | IFC | [14 empty] | 2025-12-21 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2552 | LATER | JIANGSU TIANMA | SAU4005-G114-GNB-&EFP-08817 | OWS(V)_I/O list of Oil Water Separator | G114 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | I&C&DCS | Instrumentation and Control | SEPCOIII | OWS | IFI | IFD | [14 empty] | 2025-12-13 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2553 | LATER | JIANGSU TIANMA | SAU4005-G114-GNB-&EMB-08818 | OWS(V)_Cable list of Oil Water Separator | G114 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | OWS | IFI | IFD | [14 empty] | 2025-12-27 |  | 2026-02-09 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2554 | LATER | JIANGSU TIANMA | SAU4005-G114-GNB-&EEC-08819 | OWS(V)_Electrical Load List of Oil Water Separator | G114 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | OWS | IFI | IFD | [14 empty] | 2025-12-08 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2555 | LATER | JIANGSU TIANMA | SAU4005-G114-GNB-&EFS-08820 | OWS(V)_Electrical control and schematic drawings of Oil Water Separator | G114 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | OWS | IFA | IFD |  |  | 2025-12-15 |  | 2026-01-27 |  | 2026-01-04 |  | 2025-12-30 |  | 2026-02-09 |  | 2026-04-02 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2556 | LATER | JIANGSU TIANMA | SAU4005-G114-GNB-&MDA-08821 | OWS(V)_Nameplate drawing of Oil Water Separator | G114 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | OWS | IFA | IFC |  |  | 2025-12-27 |  |  |  | 2026-01-16 |  |  |  | 2026-02-21 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2557 | LATER | JIANGSU TIANMA | SAU4005-G114-GNB-&MTB-08822 | OWS(V)_3D model of Oil Water Separator | G114 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | OWS | IFI | IFC | [14 empty] | 2026-03-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2558 | LATER | JIANGSU TIANMA | SAU4005-G114-GNB-&BDA-08823 | OWS(V)_Technical datasheet of Oil Water Separator | G114 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | OWS | IFA | IFC |  |  | 2025-12-08 |  | 2025-12-30 |  | 2025-12-28 |  | 2026-01-21 |  | 2026-02-02 |  | 2026-04-28 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2559 | LATER | JIANGSU TIANMA | SAU4005-G114-GNB-&MEC-08824 | OWS(V)_Painting procedures of Oil Water Separator | G114 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | OWS | IFA | IFC |  |  | 2025-12-29 |  | 2025-12-30 |  | 2026-01-18 |  | 2026-01-21 |  | 2026-02-23 |  | 2026-05-04 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2560 | LATER | JIANGSU TIANMA | SAU4005-G000-ZEN-&AQA-02617 | OWS(V)_Inspection and test plan of Oil Water Separator | G114 | Planning | M-Mechanical engineering (normally including process engineering) | YES | QA/QC | General | SEPCOIII | OWS | IFA | IFD |  |  | 2025-12-08 |  |  |  | 2025-12-28 |  |  |  | 2026-02-02 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2561 | LATER | JIANGSU TIANMA | SAU4005-G114-GNB-&BDC-08826 | OWS(V)_Installation, Maintenance operating instructions manual of Oil Water Separator | G114 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | OWS | IFI | IFD | [14 empty] | 2026-01-01 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2562 | LATER | JIANGSU TIANMA | SAU4005-G000-ZEN-&AQA-02528 | OWS(V)_Oil Water Separator test procedure | G114 | QA/QC | M-Mechanical engineering (normally including process engineering) | YES | QA/QC | General | SEPCOIII | OWS | IFI | IFD | [14 empty] | 2026-01-03 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| PURPOSE CHANGED | 2563 | LATER | JIANGSU TIANMA | SAU4005-G114-GNB-&MQC-08828 | OWS(V)_Oil Water Separator Quality Document | G114 | QA/QC | M-Mechanical engineering (normally including process engineering) | YES | QA/QC | General | SEPCOIII | OWS | IFI | IFD | [14 empty] | 2026-04-16 |  | 2026-03-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2564 | LATER | JIANGSU TIANMA | SAU4005-G114-GNB-&MTL-08829 | OWS(V)_Cable race way layout | G114 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | OWS | IFA | IFC |  |  | 2026-01-04 |  | 2026-04-08 |  | 2026-01-24 |  | 2026-01-21 |  | 2026-03-01 |  | 2026-05-06 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2565 | LATER | JIANGSU TIANMA | SAU4005-G114-GNB-&MQC-08825 | OWS_Inspection and test plan of Oil Water Separator | G114 | QA/QC | M-Mechanical engineering (normally including process engineering) | YES | QA/QC | General | SEPCOIII | OWS | IFA | IFD |  |  | 2025-12-08 |  | 2025-12-30 |  | 2025-12-28 |  | 2026-02-09 |  | 2026-02-02 |  | 2026-03-23 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2566 | LATER | JIANGSU TIANMA | SAU4005-G114-GNB-&MQC-08827 | OWS_Oil Water Separator test procedure | G114 | QA/QC | M-Mechanical engineering (normally including process engineering) | YES | QA/QC | General | SEPCOIII | OWS | IFI | IFD | [10 empty] | 2026-01-03 | [5 empty] | 2025-12-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2571 | LATER | SPX | SAU4005-G110-PGB-&MLU-08201 | Fin Fan Cooler(V)-General Arrangement Drawing | G110 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fin Fan Cooler | IFA | IFD |  |  | 2025-10-06 |  |  |  | 2025-10-26 |  |  |  | 2025-12-01 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2572 | LATER | SPX | SAU4005-G110-PGB-&MLU-08206 | Fin Fan Cooler(V)-Foundation Loading Anchorage | G110 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fin Fan Cooler | IFA | IFD |  |  | 2025-10-19 |  |  |  | 2025-11-08 |  |  |  | 2025-12-14 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2573 | LATER | SPX | SAU4005-G110-PGB-&MTC-08204 | Fin Fan Cooler(V)-Bundle Detail Drawing | G110 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2025-10-15 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2574 | LATER | SPX | SAU4005-G110-PGB-&MTC-08213 | Fin Fan Cooler(V)-Front Plug Header Drawing | G110 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2025-10-15 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2575 | LATER | SPX | SAU4005-G110-PGB-&MTC-08214 | Fin Fan Cooler(V)-Rear Plug Header Drawing | G110 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2025-10-15 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2576 | LATER | SPX | SAU4005-G110-PGB-&MTC-08207 | Fin Fan Cooler(V)-Name Plate Drawings | G110 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2025-11-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2577 | LATER | SPX | SAU4005-G110-PGB-&MLU-08208 | Fin Fan Cooler(V)-Erection Drawing - Steel Structure | G110 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2579 | LATER | SPX | SAU4005-G110-PGB-&MLU-08210 | Fin Fan Cooler(V)-Isometric Water lines | G110 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2026-01-29 |  | 2026-01-23 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2580 | LATER | SPX | SAU4005-G110-PGB-&MED-08205 | Fin Fan Cooler(V)-Mechanical Calculations For Pressure Parts | G110 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2025-10-12 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2581 | LATER | SPX | SAU4005-G110-PGB-&MLU-08211 | Fin Fan Cooler(V)-Piping Genaral Layout | G110 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | Piping | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2026-01-29 |  | 2025-11-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2582 | LATER | SPX | SAU4005-G110-PGB-&MED-08212 | Fin Fan Cooler(V)-Bill of Material for Piping | G110 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | Piping | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2583 | LATER | SPX | SAU4005-G110-PGB-&MDA-08202 | Fin Fan Cooler(V)-Air Cooler Data Sheet | G110 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fin Fan Cooler | IFA | IFD |  |  | 2025-09-24 |  | 2025-08-11 |  | 2025-10-14 |  | 0 |  | 2025-11-19 |  | 2025-09-26 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2584 | LATER | SPX | SAU4005-G110-PGB-&MDA-08215 | Fin Fan Cooler(V)-Fans Data Sheet | G110 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fin Fan Cooler | IFA | IFD |  |  | 2025-09-24 |  | 2025-10-20 |  | 2025-10-14 |  | 2025-08-27 |  | 2025-11-19 |  | 2025-12-01 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2585 | LATER | SPX | SAU4005-G110-PGB-&MDA-08216 | Fin Fan Cooler(V)-Gear Box Data Sheet | G110 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-10-20 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| dcc changed | 2586 | LATER | SPX | SAU4005-G110-PGB-&MDB-08217 | Fin Fan Cooler(V)-System Operation & Control Logic Description | G110 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2587 | LATER | SPX | SAU4005-G110-PGB-&MFB-08203 | Fin Fan Cooler(V)-P&ID | G110 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fin Fan Cooler | IFA | IFD |  |  | 2025-10-07 |  | 2025-08-11 |  | 2025-10-27 |  | 2025-08-31 |  | 2025-12-02 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2588 | LATER | SPX | SAU4005-G110-PGB-&EDA-08282 | Fin Fan Cooler(V)-Motor Data Sheet & Motor Outline Drawing | G110 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2025-11-17 |  | 2025-10-27 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2589 | LATER | SPX | SAU4005-G110-PGB-&EMA-08283 | Fin Fan Cooler(V)-Junction Box Outline Drawing and Interconnection Wiring Diagram | G110 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2025-11-17 |  | 2025-12-01 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2590 | LATER | SPX | SAU4005-G110-PGB-&EMB-08284 | Fin Fan Cooler(V)-Instrument Location & Cable Tray Layout Drawing | G110 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2025-11-17 |  | 2025-11-12 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2591 | LATER | SPX | SAU4005-G110-PGB-&ELU-08285 | Fin Fan Cooler(V)-Local Control Station Drawing | G110 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2025-11-20 |  | 2025-10-27 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2592 | LATER | SPX | SAU4005-G110-PGB-&EPC-08286 | Fin Fan Cooler(V)-Instrument Cable List | G110 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2025-11-17 |  | 2025-12-01 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2593 | LATER | SPX | SAU4005-G110-PGB-&EPC-08281 | Fin Fan Cooler(V)-I/O List | G110 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2025-09-24 |  | 2025-11-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2594 | LATER | SPX | SAU4005-G110-PGB-&ELD-08287 | Fin Fan Cooler(V)-Lightning Protection & Earthing | G110 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2025-11-17 |  | 2025-11-10 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2595 | LATER | SPX | SAU4005-G110-PGB-&ELD-08288 | Fin Fan Cooler(V)-Lighting Layout Drawing | G110 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2025-10-21 |  | 2025-09-17 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2596 | LATER | SPX | SAU4005-G110-PGB-&MDA-08218 | Fin Fan Cooler(V)-List of Specialties | G110 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | Electrical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-11-23 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2597 | LATER | SPX | SAU4005-G110-PGB-&MDA-08219 | Fin Fan Cooler(V)-Lubricant List | G110 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2026-01-29 |  | 2026-02-19 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2598 | LATER | SPX | SAU4005-G110-PGB-&MDA-08220 | Fin Fan Cooler(V)-Utility Consumption List | G110 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2025-10-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2599 | LATER | SPX | SAU4005-G110-PGB-&ELD-08289 | Fin Fan Cooler(V)-Instrument Hook-up Drawing With BOM | G110 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2025-10-21 |  | 2025-12-01 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2600 | LATER | SPX | SAU4005-G110-PGB-&EEC-08290 | Fin Fan Cooler(V)-Instrument Data Sheet Along With Catalouge(including Vibration Switches) | G110 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2025-11-17 |  | 2026-02-09 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2601 | LATER | SPX | SAU4005-G110-PGB-&EPA-08291 | Fin Fan Cooler(V)-Bill of Material For All Electrical Equipments | G110 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2025-11-17 |  | 2025-12-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2602 | LATER | SPX | SAU4005-G110-PGB-&EPD-08292 | Fin Fan Cooler(V)-Instrument List | G110 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2025-11-17 |  | 2025-12-01 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2603 | LATER | SPX | SAU4005-G110-PGB-&EEC-08280 | Fin Fan Cooler(V)-Complete Electrical Load List. | G110 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2025-10-05 |  | 2025-10-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2604 | LATER | SPX | SAU4005-G110-PGB-&EPD-08293 | Fin Fan Cooler(V)-Schematic Diagram | G110 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2025-11-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2606 | LATER | SPX | SAU4005-G110-PGB-&ELD-08294 | Fin Fan Cooler(V)-Scheme Drawings | G110 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2025-11-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2608 | LATER | SPX | SAU4005-G110-PGB-&AQC-08256 | Fin Fan Cooler(V)-Inspection and Test Plan | G110 | QA/QC | A-Overall management | YES | QA/QC | General | SEPCOIII | Fin Fan Cooler | IFA | IFD |  |  | 2025-10-20 |  | 2025-08-25 |  | 2025-11-09 |  | 2025-11-20 |  | 2025-12-15 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| dcc changed | 2614 | LATER | SPX | SAU4005-G110-PGB-&MDC-08262 | Fin Fan Cooler(V)-Painting, Galvanizing and Protection Specification | G110 | QA/QC | A-Overall management | YES | QA/QC | General | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2025-12-30 |  | 2025-12-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2617 | LATER | SPX | SAU4005-G110-PGB-&ADC-08265 | Fin Fan Cooler(V)-Installation,Operation and Maintenance Manual | G110 | Operation & Maintenacne | A-Overall management | YES | GENERAL | General | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2025-10-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2618 | LATER | SPX | SAU4005-G110-PGB-&APB-08221 | Fin Fan Cooler(V)-Spare Parts for Commissioning and Start-up | G110 | Commissioning | A-Overall management | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2619 | LATER | SPX | SAU4005-G110-PGB-&APB-08222 | Fin Fan Cooler(V)-Two-Years Operation Spare Parts List | G110 | Commissioning | A-Overall management | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2620 | LATER | SPX | SAU4005-G110-PGB-&APB-08223 | Fin Fan Cooler(V)-Special Tools List | G110 | Commissioning | A-Overall management | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2621 | LATER | SPX | SAU4005-G110-PGB-&AAB-08266 | Fin Fan Cooler(V)-Manufacturing Data Book Index | G110 | QA/QC | A-Overall management | YES | QA/QC | General | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2026-02-14 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2622 | LATER | SPX | SAU4005-G110-PGB-&AQA-08267 | Fin Fan Cooler(V)-Manufacturing Data Book (MDB) | G110 | QA/QC | A-Overall management | YES | QA/QC | General | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2026-03-17 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| dcc changed | 2623 | LATER | SPX | SAU4005-G110-PGB-&APA-08224 | Fin Fan Cooler(V)-Completed Bill of Materials for All Equipment(Main Equipment List) | G110 | Engineering | A-Overall management | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2026-03-27 |  | 2026-02-06 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2624 | LATER | SPX | SAU4005-G110-PGB-&MDA-08225 | Fin Fan Cooler(V)-Piping List | G110 | Engineering | A-Overall management | YES | PIPING&PLANT DESIGN | Piping | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2026-01-29 |  | 2025-11-28 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2626 | LATER | SPX | SAU4005-G110-PGB-&MDA-08227 | Fin Fan Cooler(V)-3D Model (Progressively with physical design submittals) | G110 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2026-03-27 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2628 | LATER | SPX | SAU4005-G110-PGB-&ADC-08228 | Fin Fan Cooler(V)-Performance Correction Curves | G110 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2026-01-29 |  | 2026-02-06 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES
| NEW | 2629 | LATER | SPX | SAU4005-G110-PGB-&MDA-08229 | Fin Fan Cooler(V)-Relief Valve Set Point List | G110 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES
| NEW | 2630 | LATER | SPX | SAU4005-G110-PGB-&MDA-08230 | Fin Fan Cooler(V)-Piping Line List | G110 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | Mechanical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2026-01-29 |  | 2026-02-09 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES
| NEW | 2632 | LATER | SPX | SAU4005-G110-PGB-&MDA-08232 | Fin Fan Cooler(V)-Maintenance Checkoff List | G110 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2026-01-29 |  | 2026-02-09 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES
| NEW | 2633 | LATER | SPX | SAU4005-G110-PGB-&ADC-08233 | Fin Fan Cooler(V)-Preservation Procedure | G110 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2026-01-29 |  | 2026-02-09 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES
| NEW | 2634 | LATER | SPX | SAU4005-G110-PGB-&AQA-08247 | Fin Fan Cooler(V)-Cleaning Procedure of Tube Bundle Internal | G110 | QA/QC | A-Overall management | YES | QA/QC | General | SEPCOIII | Fin Fan Cooler | IFI | IFD | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES
| NEW | 2635 | LATER | SPX | SAU4005-G110-ZEN-&AQA-02518 | Fin Fan Cooler(V) -FAT Test Procedure | G110 | QA/QC | A-Overall management | YES | QA/QC | General | SEPCOIII | Fin Fan Cooler | IFA | IFD |  |  | 2026-02-28 |  | 2025-12-29 |  | 2026-03-17 |  | 2026-01-11 |  | 2026-04-23 |  | 2026-01-13 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 2636 | LATER | SPX | SAU4005-G110-PGB-&EFF-08295 | Fin Fan Cooler(V)-Control Loop & Logic Diagram | G110 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fin Fan Cooler | IFA | IFD |  |  | 2026-04-20 |  | 2026-04-10 |  | 2026-05-10 |  | 2026-05-12 |  | 2026-06-15 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2638 | LATER | HBC | SAU4005-G111-QEA-&MFB-08301 | Compressed air(V)-Piping and instrument(P&ID) drawings | G111 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Compressed Air | IFA | IFD |  |  | 2025-08-09 |  | 2025-08-13 |  | 2025-08-29 |  | 2025-09-02 |  | 2025-10-04 |  | 2025-11-20 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Open
|  | 2639 | LATER | HBC | SAU4005-G111-QEA-&MTL-08302 | Compressed air(V)-Outline drawing of service air receiver | G111 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Compressed Air | IFA | IFD |  |  | 2025-08-02 |  | 2025-08-19 |  | 2025-08-22 |  | 2025-09-02 |  | 2025-09-27 |  | 2025-10-22 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2640 | LATER | HBC | SAU4005-G111-QEA-&MTL-08303 | Compressed air(V)-Outline drawing of instrument air receiver | G111 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Compressed Air | IFA | IFD |  |  | 2025-08-02 |  | 2025-08-19 |  | 2025-08-22 |  | 2025-09-02 |  | 2025-09-27 |  | 2025-10-22 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2641 | LATER | HBC | SAU4005-G111-QEA-&MPD-08304 | Compressed air(V)-Piping line list | G111 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Compressed Air | IFI | IFD | [14 empty] | 2025-08-30 |  | 2025-08-23 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2642 | LATER | HBC | SAU4005-G111-QEA-&MPD-08305 | Compressed air(V)-Valve list | G111 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Compressed Air | IFI | IFD | [14 empty] | 2025-08-30 |  | 2025-08-23 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2643 | LATER | HBC | SAU4005-G111-QEA-&MTB-08306 | Compressed air(V)-Nameplate drawings | G111 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Compressed Air | IFI | IFD | [14 empty] | 2025-08-30 |  | 2025-08-19 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2644 | LATER | HBC | SAU4005-G111-QEA-&MFP-08307 | Compressed air(V)- Lubrication list & First Fill details | G111 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Compressed Air | IFI | IFD | [14 empty] | 2025-08-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2645 | LATER | HBC | SAU4005-G111-QEA-&MDA-08308 | Compressed air(V)-Equipment & component datasheet | G111 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Compressed Air | IFI | IFD | [14 empty] | 2025-08-02 |  | 2025-08-13 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2646 | LATER | HBC | SAU4005-G111-QEA-&MTL-08309 | Compressed air(V)-General Arrangement (GA) drawings | G111 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Compressed Air | IFA | IFD |  |  | 2025-08-02 |  | 2025-08-13 |  | 2025-08-22 |  | 2025-09-02 |  | 2025-09-27 |  | 2025-10-26 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Open
|  | 2647 | LATER | HBC | SAU4005-G111-QEA-&MTB-08310 | Compressed air(V)-Piping Isometric drawings | G111 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Compressed Air | IFI | IFD | [14 empty] | 2025-08-02 |  | 2025-10-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2648 | LATER | HBC | SAU4005-G111-QEA-&MTL-08311 | Compressed air(V)-Outline drawing of compressor | G111 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Compressed Air | IFA | IFD |  |  | 2025-08-02 |  | 2025-09-25 |  | 2025-08-22 |  | 2025-09-02 |  | 2025-09-27 |  | 2025-11-20 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2649 | LATER | HBC | SAU4005-G111-QEA-&MTL-08312 | Compressed air(V)-Outline drawing of refrigerated air chiller | G111 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Compressed Air | IFA | IFD |  |  | 2025-08-02 |  | 2025-09-18 |  | 2025-08-22 |  | 2025-09-02 |  | 2025-09-27 |  | 2025-11-20 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2650 | LATER | HBC | SAU4005-G111-QEA-&MFP-08313 | Compressed air(V)- Terminal Point List | G111 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Compressed Air | IFI | IFD | [14 empty] | 2025-08-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2651 | LATER | HBC | SAU4005-G111-QEA-&MTL-08314 | Compressed air(V)-Outline drawing of air dryer | G111 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Compressed Air | IFA | IFD |  |  | 2025-08-02 |  | 2025-09-25 |  | 2025-08-22 |  | 2025-09-02 |  | 2025-09-27 |  | 2025-11-09 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2652 | LATER | HBC | SAU4005-G111-QEA-&MTL-08315 | Compressed air(V)-Outline drawing of service air filter | G111 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Compressed Air | IFA | IFD |  |  | 2025-08-02 |  | 2025-09-18 |  | 2025-08-22 |  | 0 |  | 2025-09-27 |  | 2025-10-02 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2653 | LATER | HBC | SAU4005-G111-QEA-&MPD-08316 | Compressed air(V)-Equipment list | G111 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Compressed Air | IFI | IFD | [14 empty] | 2025-08-30 |  | 2025-08-13 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2654 | LATER | HBC | SAU4005-G111-QEA-&MQA-08317 | Compressed air(V)-Painting procedure | G111 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | QA/QC | Mechanical | SEPCOIII | Compressed Air | IFI | IFD | [14 empty] | 2025-08-30 |  | 2025-08-19 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2655 | LATER | HBC | SAU4005-G111-QEA-&MTB-08318 | Compressed air(V)-3D Model | G111 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Compressed Air | IFI | IFD | [14 empty] | 2025-09-13 |  | 2025-09-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2656 | LATER | HBC | SAU4005-G111-QEA-&MTB-08319 | Compressed air(V)-Piping GA drawings | G111 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Compressed Air | IFI | IFD | [14 empty] | 2025-08-30 |  | 2025-09-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2657 | LATER | HBC | SAU4005-G111-QEA-&CTL-08320 | Compressed air(V)-Equipment foundation load data and Civil assignment drawing | G111 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Compressed Air | IFI | IFD | [14 empty] | 2025-08-02 |  | 2025-08-19 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2658 | LATER | HBC | SAU4005-G111-QEA-&BDC-08321 | Compressed air(V)-Catalogs document | G111 | Engineering | B-Overall technology | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Compressed Air | IFI | IFD | [14 empty] | 2025-09-13 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2660 | LATER | HBC | SAU4005-G111-QEA-&MQA-08323 | Compressed air(V)-SAT Procedure | G111 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | QA/QC | Process | SEPCOIII | Compressed Air | IFI | IFP | [14 empty] | 2025-09-13 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2661 | LATER | HBC | SAU4005-G111-QEA-&ETL-08324 | Compressed air(V)-Earthing layout | G111 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Compressed Air | IFI | IFD | [14 empty] | 2025-08-16 |  | 2025-09-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2662 | LATER | HBC | SAU4005-G111-QEA-&EDA-08325 | Compressed air(V)-Motor Data Sheet and Curves | G111 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Compressed Air | IFI | IFD | [14 empty] | 2025-09-29 |  | 2025-09-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2663 | LATER | HBC | SAU4005-G111-QEA-&EEC-08326 | Compressed air(V)-Electrical load list | G111 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Compressed Air | IFI | IFD | [14 empty] | 2025-08-09 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2664 | LATER | HBC | SAU4005-G111-QEA-&EFP-08327 | Compressed air(V)-Setpoint and alarm list | G111 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Compressed Air | IFI | IFD | [14 empty] | 2025-08-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2665 | LATER | HBC | SAU4005-G111-QEA-&EFF-08328 | Compressed air(V)-Single line diagram | G111 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Compressed Air | IFI | IFD | [14 empty] | 2025-08-16 |  | 2025-09-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2666 | LATER | HBC | SAU4005-G111-QEA-&EFP-08329 | Compressed air(V)-Communication Signal List | G111 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Compressed Air | IFI | IFD | [14 empty] | 2025-09-19 |  | 2025-09-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2667 | LATER | HBC | SAU4005-G111-QEA-&EFA-08330 | Compressed air(V)-System Configuration Diagram | G111 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Compressed Air | IFA | IFD |  |  | 2025-08-02 |  | 2025-09-18 |  | 2025-08-22 |  | 2025-09-02 |  | 2025-09-27 |  | 2026-05-06 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
| PURPOSE CHANGED | 2668 | LATER | HBC | SAU4005-G111-QEA-&EDA-08331 | Compressed air(V)-Instrument List with Data Sheet | G111 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Compressed Air | IFA | IFD |  |  | 2025-09-13 |  | 2025-09-18 |  | 2025-10-03 |  | 2025-09-02 |  | 2025-11-09 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2669 | LATER | HBC | SAU4005-G111-QEA-&EMA-08332 | Compressed air(V)-Instrument hookup drawings | G111 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Compressed Air | IFI | IFD | [14 empty] | 2025-08-30 |  | 2025-09-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2670 | LATER | HBC | SAU4005-G111-QEA-&EFF-08333 | Compressed air(V)-GAD and wiring diagram of Local control panel for refrigerant dryer | G111 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Compressed Air | IFI | IFD | [14 empty] | 2025-08-30 |  | 2025-09-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2671 | LATER | HBC | SAU4005-G111-QEA-&EFF-08334 | Compressed air(V)-GAD and wiring diagram of Local control panel for Air Dryer | G111 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Compressed Air | IFI | IFD | [14 empty] | 2025-08-30 |  | 2025-09-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2672 | LATER | HBC | SAU4005-G111-QEA-&EFF-08335 | Compressed air(V)-GAD and wiring diagram of Local control panel for Air Compressor | G111 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Compressed Air | IFI | IFD | [14 empty] | 2025-09-13 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2673 | LATER | HBC | SAU4005-G111-QEA-&EFP-08336 | Compressed air(V)-Hard wired I/O List | G111 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Compressed Air | IFI | IFD | [14 empty] | 2025-08-09 |  | 2025-09-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2674 | LATER | HBC | SAU4005-G111-QEA-&EFF-08337 | Compressed air(V)-Control logic diagram | G111 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Compressed Air | IFA | IFD |  |  | 2025-08-30 |  |  |  | 2025-09-19 |  |  |  | 2025-10-25 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2675 | LATER | HBC | SAU4005-G111-QEA-&EAC-08338 | Compressed air(V)-System Operation & Control Description | G111 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Compressed Air | IFA | IFD |  |  | 2025-08-30 |  | 2025-09-16 |  | 2025-09-19 |  | 2025-09-02 |  | 2025-10-25 |  | 2026-01-08 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Open
|  | 2676 | LATER | HBC | SAU4005-G111-QEA-&ETL-08339 | Compressed air(V)-Instrument/JB Location Drawing | G111 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Compressed Air | IFI | IFD | [14 empty] | 2025-09-13 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
|  | 2677 | LATER | HBC | SAU4005-G111-QEA-&EDA-08340 | Compressed air(V)-MOV List & Datasheet along with Catalogue | G111 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Compressed Air | IFI | IFD | [14 empty] | 2025-09-13 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
| NEW ADDED | 2678 | LATER | HBC | SAU4005-G111-QEA-&MQA-08343 | Compressed air(V)-End of Manufacturing Record for Air Compressor System Equipment | G111 | QA/QC | m-Mechanical engineering (normally including process engineering) | YES | QA/QC | General | SEPCOIII | Compressed Air | IFI | IFD | [14 empty] | 2026-05-15 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 2679 | LATER | HBC | SAU4005-G111-QEA-&MQA-08344 | Compressed air(V)-O&M Manuals | G111 | QA/QC | m-Mechanical engineering (normally including process engineering) | YES | QA/QC | General | SEPCOIII | Compressed Air | IFI | IFD | [14 empty] | 2026-05-15 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2681 | LATER | CHUANRUN | SAU4005-G113-QH_-&MLU-08502 | Auxiliary Boiler(V)- General Arrangement Drawing | G113 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Auxiliary Boiler | IFI | IFD | [14 empty] | 2025-09-23 |  | 2025-09-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2682 | LATER | CHUANRUN | SAU4005-G113-QH_-&APB-08503 | Aux Boiler(V)-Spare Parts list and consumables (commissioning and 2 years operation) | G113 | Project Management | A-Overall management | YES | GENERAL | General | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-09-23 |  | 2026-04-02 |  | 2025-10-13 |  | 2026-05-06 |  | 2025-11-18 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2683 | LATER | CHUANRUN | SAU4005-G113-QH_-&APB-08504 | Aux Boiler(V)-Special tools list and manual | G113 | Project Management | A-Overall management | YES | GENERAL | General | SEPCOIII | Auxiliary Boiler | IFA | IFP |  |  | 2025-09-23 |  | 2026-04-02 |  | 2025-10-13 |  | 2026-05-06 |  | 2025-11-18 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2684 | LATER | CHUANRUN | SAU4005-G113-QH_-&ADC-08505 | Aux Boiler(V)-Installation instruction manual | G113 | Project Management | A-Overall management | YES | GENERAL | General | SEPCOIII | Auxiliary Boiler | IFA | IFP |  |  | 2026-03-31 |  | 2026-03-11 |  | 2026-04-20 |  | 2025-10-12 |  | 2026-05-26 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2686 | LATER | CHUANRUN | SAU4005-G113-QH_-&MDA-08507 | Aux Boiler(V)-Performance data | G113 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-09-09 |  |  |  | 2025-09-29 |  |  |  | 2025-11-04 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2687 | LATER | CHUANRUN | SAU4005-G113-QH_-&MDB-08508 | Aux Boiler(V)-System description | G113 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-09-23 |  |  |  | 2025-10-13 |  |  |  | 2025-11-18 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2688 | LATER | CHUANRUN | SAU4005-G113-QH_-&MDA-08509 | Aux Boiler(V)-Equipment list | G113 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-09-23 |  |  |  | 2025-10-13 |  |  |  | 2025-11-18 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2689 | LATER | CHUANRUN | SAU4005-G113-QH_-&MLB-08510 | Aux Boiler(V)-Foundation drawing | G113 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-10-02 |  |  |  | 2025-10-22 |  |  |  | 2025-11-27 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2690 | LATER | CHUANRUN | SAU4005-G113-QH_-&MFB-08511 | Aux Boiler(V)-Process and instrument diagram drawing | G113 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-09-23 |  | 2025-09-10 |  | 2025-10-13 |  | 2025-10-12 |  | 2025-11-18 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2691 | LATER | CHUANRUN | SAU4005-G113-QH_-&MPL-08512 | Aux Boiler(V)-Terminal points list and drawing including, at least, exact location, process data (design and operation values -pressure, temperature, flow-), dimensions, material and characteristics | G113 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-09-30 |  |  |  | 2025-10-20 |  |  |  | 2025-11-25 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2692 | LATER | CHUANRUN | SAU4005-G113-QH_-&MLD-08513 | Aux Boiler(V)-Pipe support drawing | G113 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | Piping | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-12-30 |  | 2025-12-11 |  | 2026-01-19 |  | 2025-10-12 |  | 2026-02-24 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2693 | LATER | CHUANRUN | SAU4005-G113-QH_-&MBD-08514 | Aux Boiler(V)-Start-up and shut-down curve | G113 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Auxiliary Boiler | IFI | IFD | [14 empty] | 2025-12-30 |  | 2025-12-12 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2694 | LATER | CHUANRUN | SAU4005-G113-QH_-&MPC-08515 | Aux Boiler(V)-List of valves and accessories | G113 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | Piping | SEPCOIII | Auxiliary Boiler | IFI | IFD | [14 empty] | 2025-10-21 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2695 | LATER | CHUANRUN | SAU4005-G113-QH_-&MDC-08516 | Aux Boiler(V)-List of consumers and consumables, including lubricant and lube oil consumers, and utility consumption list. | G113 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-12-02 |  | 2025-12-05 |  | 2025-12-22 |  | 0 |  | 2026-01-27 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2696 | LATER | CHUANRUN | SAU4005-G113-QH_-&MTB-08517 | Aux Boiler(V)-Large bore piping isometrics drawing | G113 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | Piping | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-12-02 |  | 2025-12-04 |  | 2025-12-22 |  | 0 |  | 2026-01-27 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2697 | LATER | CHUANRUN | SAU4005-G113-QH_-&MTB-08518 | Aux Boiler(V)-Small bore piping isometrics drawing | G113 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | Piping | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-12-30 |  | 2025-12-11 |  | 2026-01-19 |  | 0 |  | 2026-02-24 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2698 | LATER | CHUANRUN | SAU4005-G113-QH_-&MLD-08519 | Aux Boiler(V)-Piping arrangement drawing of large bore and small bore | G113 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | Piping | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-11-04 |  | 2025-10-13 |  | 2025-11-24 |  | 0 |  | 2025-12-30 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2699 | LATER | CHUANRUN | SAU4005-G113-QH_-&MED-08520 | Aux Boiler(V)-Complete mechanical calculations | G113 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-11-04 |  | 2025-10-30 |  | 2025-11-24 |  | 2025-09-07 |  | 2025-12-30 |  | 2026-03-02 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2700 | LATER | CHUANRUN | SAU4005-G113-QH_-&MLD-08521 | Aux Boiler(V)-Hazardous Areas drawings | G113 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-10-21 |  | 2025-09-08 |  | 2025-11-10 |  | 0 |  | 2025-12-16 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2701 | LATER | CHUANRUN | SAU4005-G113-QH_-&MTB-08522 | Aux Boiler(V)-Nameplate drawings | G113 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-12-30 |  | 2025-10-30 |  | 2026-01-19 |  | 2025-09-07 |  | 2026-02-24 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2702 | LATER | CHUANRUN | SAU4005-G113-QH_-&MTB-08523 | Aux Boiler(V)-Lifting plan, lifting drawings (including mass, center of gravity and lifting lugs layout) | G113 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-12-16 |  | 2025-10-31 |  | 2026-01-05 |  | 0 |  | 2026-02-10 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2703 | LATER | CHUANRUN | SAU4005-G113-QH_-&MDB-08524 | Aux Boiler(V)-Coating and painting procedure | G113 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-12-02 |  | 2025-12-17 |  | 2025-12-22 |  | 2025-09-08 |  | 2026-01-27 |  | 2026-02-16 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2704 | LATER | CHUANRUN | SAU4005-G113-QH_-&EDC-08525 | Aux Boiler(V)-Electrical Load list | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-09-08 |  | 2025-10-30 |  | 2025-09-28 |  | 0 |  | 2025-11-03 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2705 | LATER | CHUANRUN | SAU4005-G113-QH_-&EMA-08526 | Aux Boiler(V)-Connections diagrams of the terminal boxes | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-11-04 |  | 2025-12-03 |  | 2025-11-24 |  | 0 |  | 2025-12-30 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2706 | LATER | CHUANRUN | SAU4005-G113-QH_-&EDA-08527 | Aux Boiler(V)-Motor data sheet | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-12-02 |  | 2025-10-13 |  | 2025-12-22 |  | 2025-09-08 |  | 2026-01-27 |  | 2026-03-02 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2707 | LATER | CHUANRUN | SAU4005-G113-QH_-&EMA-08528 | Aux Boiler(V)-External Connection Diagrams | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-11-04 |  | 2025-11-13 |  | 2025-11-24 |  | 2025-09-08 |  | 2025-12-30 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2708 | LATER | CHUANRUN | SAU4005-G113-QH_-&ETB-08529 | Aux Boiler(V)-Motor and all junction boxes drawings | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-11-04 |  | 2025-12-22 |  | 2025-11-24 |  | 2025-09-08 |  | 2025-12-30 |  | 2026-03-31 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2709 | LATER | CHUANRUN | SAU4005-G113-QH_-&ETB-08530 | Aux Boiler(V)-Wiring diagrams | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-11-04 |  | 2025-10-08 |  | 2025-11-24 |  | 2025-10-27 |  | 2025-12-30 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2710 | LATER | CHUANRUN | SAU4005-G113-QH_-&EMA-08531 | Aux Boiler(V)-Location & size of conduit connections | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-11-04 |  | 2025-12-19 |  | 2025-11-24 |  | 2025-09-08 |  | 2025-12-30 |  | 2026-02-24 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2711 | LATER | CHUANRUN | SAU4005-G113-QH_-&ELH-08532 | Aux Boiler(V)-Earthing connection details for construction and equipment’s | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-11-04 |  | 2025-10-27 |  | 2025-11-24 |  | 0 |  | 2025-12-30 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2712 | LATER | CHUANRUN | SAU4005-G113-QH_-&ETC-08533 | Aux Boiler(V)-Local distribution panel outline drawings | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-11-04 |  |  |  | 2025-11-24 |  |  |  | 2025-12-30 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2713 | LATER | CHUANRUN | SAU4005-G113-QH_-&EED-08534 | Aux Boiler(V)-Lighting and small power layout including Illumination calculation. | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Auxiliary Boiler | IFI | IFD | [14 empty] | 2025-11-25 |  | 2025-12-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2714 | LATER | CHUANRUN | SAU4005-G113-QH_-&EPC-08535 | Aux Boiler(V)-Power cable schedule | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Auxiliary Boiler | IFI | IFD | [14 empty] | 2025-11-25 |  | 2025-11-09 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2715 | LATER | CHUANRUN | SAU4005-G113-QH_-&EED-08536 | Aux Boiler(V)-Bill of material for electrical equipments. | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Auxiliary Boiler | IFI | IFD | [14 empty] | 2025-12-09 |  | 2025-12-11 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
| dcc changed | 2717 | LATER | CHUANRUN | SAU4005-G113-QH_-&EEC-08538 | Aux Boiler(V)-Instruments list | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Auxiliary Boiler | IFI | IFD | [14 empty] | 2025-12-02 |  | 2026-01-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2718 | LATER | CHUANRUN | SAU4005-G113-QH_-&EDA-08539 | Aux Boiler(V)-Instruments data sheets along with Catalogue | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Auxiliary Boiler | IFI | IFD | [14 empty] | 2025-12-02 |  | 2026-01-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2719 | LATER | CHUANRUN | SAU4005-G113-QH_-&ELD-08540 | Aux Boiler(V)-Instrument Installation Hook-up Drawing | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Auxiliary Boiler | IFI | IFD | [14 empty] | 2025-12-02 |  | 2025-10-15 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2720 | LATER | CHUANRUN | SAU4005-G113-QH_-&ETB-08541 | Aux Boiler(V)-Instruments/Junction boxes layout drawings | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Auxiliary Boiler | IFI | IFD | [14 empty] | 2025-12-02 |  | 2026-01-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
| dcc changed | 2721 | LATER | CHUANRUN | SAU4005-G113-QH_-&EMB-08542 | Aux Boiler(V)-I&C Cable Interconnection Drawing | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Auxiliary Boiler | IFI | IFD | [14 empty] | 2025-12-02 |  | 2026-02-20 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2722 | LATER | CHUANRUN | SAU4005-G113-QH_-&EDC-08543 | Aux Boiler(V)-Instrumentation O&M Manuals | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Auxiliary Boiler | IFI | IFD | [14 empty] | 2025-12-02 |  | 2025-12-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2723 | LATER | CHUANRUN | SAU4005-G113-QH_-&EFP-08544 | Aux Boiler(V)-Control System I/O List(Hardwired & Soft) | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Auxiliary Boiler | IFI | IFD | [14 empty] | 2025-11-18 |  | 2025-10-01 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2724 | LATER | CHUANRUN | SAU4005-G113-QH_-&EPC-08545 | Aux Boiler(V)-I&C Cable Schedule | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-11-18 |  |  |  | 2025-12-08 |  |  |  | 2026-01-13 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2725 | LATER | CHUANRUN | SAU4005-G113-QH_-&ETB-08546 | Aux Boiler(V)-I&C Cable Raceway Drawing | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-11-18 |  | 2025-10-13 |  | 2025-12-08 |  | 0 |  | 2026-01-13 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2726 | LATER | CHUANRUN | SAU4005-G113-QH_-&ETA-08547 | Aux Boiler(V)-Control Panel GA/IA Layout Drawing along with BOM | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-11-18 |  | 2025-12-15 |  | 2025-12-08 |  | 2025-10-29 |  | 2026-01-13 |  | 2026-02-16 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2727 | LATER | CHUANRUN | SAU4005-G113-QH_-&EED-08548 | Aux Boiler(V)-Control System Configuration (System Architecture) of PLC | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-09-13 |  | 2025-10-25 |  | 2025-10-03 |  | 2025-09-08 |  | 2025-11-08 |  | 2026-02-18 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2728 | LATER | CHUANRUN | SAU4005-G113-QH_-&EFP-08549 | Aux Boiler(V)-Hardwire I/O Signal List (Package PLC to Main Plant DCS) | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-09-12 |  | 2025-11-18 |  | 2025-10-02 |  | 0 |  | 2025-11-07 |  | 2025-12-07 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2729 | LATER | CHUANRUN | SAU4005-G113-QH_-&ETA-08550 | Aux Boiler(V)-Control Loop & Logic Diagram (in SAMA Format) | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Auxiliary Boiler | IFI | IFD | [14 empty] | 2025-12-01 |  | 2025-12-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2730 | LATER | CHUANRUN | SAU4005-G113-QH_-&EDA-08551 | Aux Boiler(V)-Cause & Effect Matrix | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Auxiliary Boiler | IFI | IFD | [14 empty] | 2025-12-01 |  | 2025-10-01 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2731 | LATER | CHUANRUN | SAU4005-G113-QH_-&EDA-08552 | Aux Boiler(V)-Alarm & Setpoint List | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Auxiliary Boiler | IFI | IFD | [14 empty] | 2025-11-17 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2732 | LATER | CHUANRUN | SAU4005-G113-QH_-&ETB-08553 | Aux Boiler(V)-Control Panel Internal Wiring & Schematic Drawing | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Auxiliary Boiler | IFI | IFD | [14 empty] | 2025-11-24 |  | 2025-12-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2733 | LATER | CHUANRUN | SAU4005-G113-QH_-&ETB-08554 | Aux Boiler(V)-PLC HMI Graphic | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Auxiliary Boiler | IFI | IFD | [14 empty] | 2025-11-17 |  | 2025-12-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2734 | LATER | CHUANRUN | SAU4005-G113-QH_-&EDC-08555 | Aux Boiler(V)-Control Philosphy | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Auxiliary Boiler | IFI | IFD | [14 empty] | 2025-12-01 |  | 2025-11-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2735 | LATER | CHUANRUN | SAU4005-G113-QH_-&EDC-08556 | Aux Boiler(V)-PLC Specification & Datasheet along with Catalogue | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Auxiliary Boiler | IFI | IFD | [14 empty] | 2025-12-01 |  | 2025-10-13 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2736 | LATER | CHUANRUN | SAU4005-G113-QH_-&ELD-08557 | Aux Boiler(V)-Instrument/JB Location Drawing | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Auxiliary Boiler | IFI | IFD | [14 empty] | 2025-12-01 |  | 2025-12-19 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2737 | LATER | CHUANRUN | SAU4005-G113-QH_-&EDA-08558 | Aux Boiler(V)-I&C Cable Datasheet | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Auxiliary Boiler | IFI | IFD | [14 empty] | 2025-12-01 |  | 2025-10-17 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
| dcc changed | 2738 | LATER | CHUANRUN | SAU4005-G113-QH_-&EEC-08559 | Aux Boiler(V)-Control Valve List & Datasheet along with Catalogue (If Applicable) | G113 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Auxiliary Boiler | IFI | IFD | [14 empty] | 2025-12-01 |  | 2026-01-09 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2739 | LATER | CHUANRUN | SAU4005-G113-QH_-&AQC-08560 | Aux Boiler(V)-FAT/SAT Procedure | G113 | QA/QC | A-Overall management | YES | QA/QC | General | SEPCOIII | Auxiliary Boiler | IFI | IFP | [14 empty] | 2025-12-01 |  | 2025-11-17 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2740 | LATER | CHUANRUN | SAU4005-G113-QH_-&AQA-08561 | Aux Boiler_Quality Management Program | G113 | QA/QC | A-Overall management | YES | QA/QC | General | SEPCOIII | Auxiliary Boiler | IFI | IFP | [14 empty] | 2025-10-07 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2741 | LATER | CHUANRUN | SAU4005-G113-QH_-&AQC-08562 | Aux Boiler(V)-Inspection & Test Plan (ITP) | G113 | QA/QC | A-Overall management | YES | QA/QC | General | SEPCOIII | Auxiliary Boiler | IFA | IFP |  |  | 2025-10-21 |  |  |  | 2025-11-10 |  |  |  | 2025-12-16 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2742 | LATER | CHUANRUN | SAU4005-G113-QH_-&AQC-08563 | Aux Boiler(V)-Hydrostatic Test report and certificate | G113 | QA/QC | A-Overall management | YES | QA/QC | General | SEPCOIII | Auxiliary Boiler | IFA | IFP |  |  | 2026-03-31 |  |  |  | 2026-04-20 |  |  |  | 2026-05-26 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2743 | LATER | CHUANRUN | SAU4005-G113-QH_-&AQC-08564 | Aux Boiler(V)-Performance test Procedure | G113 | QA/QC | A-Overall management | YES | QA/QC | General | SEPCOIII | Auxiliary Boiler | IFA | IFP |  |  | 2026-03-31 |  |  |  | 2026-04-20 |  |  |  | 2026-05-26 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2744 | LATER | CHUANRUN | SAU4005-G113-QH_-&AQC-08565 | Aux Boiler(V)-Performance test report | G113 | QA/QC | A-Overall management | YES | QA/QC | General | SEPCOIII | Auxiliary Boiler | IFA | IFP |  |  | 2026-06-07 |  |  |  | 2026-06-27 |  |  |  | 2026-08-02 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2745 | LATER | CHUANRUN | SAU4005-G113-QH_-&MTC-08566 | Aux Boiler(V)-Welding Procedures | G113 | Construction | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | General | SEPCOIII | Auxiliary Boiler | IFI | IFP | [14 empty] | 2025-12-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2748 | LATER | CHUANRUN | SAU4005-G113-QH_-&ABF-08569 | Aux Boiler(V)-Packaging & Shipping Instructions | G113 | QA/QC | A-Overall management | YES | QA/QC | General | SEPCOIII | Auxiliary Boiler | IFI | IFP | [14 empty] | 2025-12-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2749 | LATER | CHUANRUN | SAU4005-G113-QH_-&MDA-08570 | Aux Boiler(V)-Cleaning specification | G113 | QA/QC | M-Mechanical engineering (normally including process engineering) | YES | QA/QC | General | SEPCOIII | Auxiliary Boiler | IFI | IFC | [14 empty] | 2025-09-23 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2751 | LATER | CHUANRUN | SAU4005-G113-QH_-&ADC-08572 | Aux Boiler(V)-Noise Datasheets / guarantees | G113 | HSE | A-Overall management | YES | QA/QC | General | SEPCOIII | Auxiliary Boiler | IFI | IFD | [14 empty] | 2025-09-23 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2752 | LATER | CHUANRUN | SAU4005-G113-QH_-&MTB-08573 | Aux Boiler(V)-3D Model | G113 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | PIPING&PLANT DESIGN | Piping | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-10-07 |  |  |  | 2025-10-27 |  |  |  | 2025-12-02 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES |  |  |  |  | Combine
|  | 2753 | LATER | CHUANRUN | SAU4005-G113-QH_-&ETB-08574 | Aux Boiler(V)-single line drawing | G113 | Engineering | e-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Auxiliary Boiler | IFA | IFD |  |  | 2025-10-21 |  | 2025-09-02 |  | 2025-11-10 |  | 2025-09-16 |  | 2025-12-16 |  | 2026-02-01 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2755 | LATER | NUCLEON | SAU4005-G115-SMM-&MDA-08901 | STG Overhead Crane-(V) General Arrangement (GA) drawing | G115 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STG Building Overhead Crane | IFA | IFD |  |  | 2025-09-04 |  | 2025-08-24 |  | 2025-09-24 |  | 2025-10-22 |  | 2025-10-30 |  | 2026-01-21 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2756 | LATER | NUCLEON | SAU4005-G115-SMM-&MDA-08902 | STG Overhead Crane-(V) Datasheet | G115 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STG Building Overhead Crane | IFA | IFD |  |  | 2025-09-04 |  | 2025-08-24 |  | 2025-09-24 |  | 2025-10-30 |  | 2025-10-30 |  | 2026-01-22 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2757 | LATER | NUCLEON | SAU4005-G115-SMM-&ETL-08903 | STG Overhead Crane-(V) Electrical system layout diagram and Cable layout | G115 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | STG Building Overhead Crane | IFA | IFD |  |  | 2025-09-04 |  | 2025-10-09 |  | 2025-09-24 |  | 2025-10-30 |  | 2025-10-30 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2758 | LATER | NUCLEON | SAU4005-G115-SMM-&EFF-08904 | STG Overhead Crane-(V) Electrical control schematic diagram | G115 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | STG Building Overhead Crane | IFA | IFD |  |  | 2025-09-04 |  | 2025-10-09 |  | 2025-09-24 |  | 2025-10-30 |  | 2025-10-30 |  | 2026-01-07 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2759 | LATER | NUCLEON | SAU4005-G115-SMM-&ADC-08905 | STG Overhead Crane-(V) Installation, Operation, and Maintenance Manuals | G115 | Operation & Maintenacne | A-Overall management | YES | O&M | General | SEPCOIII | STG Building Overhead Crane | IFI | IFP | [14 empty] | 2025-09-04 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2760 | LATER | NUCLEON | SAU4005-G115-SMM-&MTB-08906 | STG Overhead Crane-(V) 3D Model | G115 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STG Building Overhead Crane | IFI | IFD | [14 empty] | 2025-11-04 |  | 2025-10-11 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2761 | LATER | NUCLEON | SAU4005-G115-SMM-&AQA-08907 | STG Overhead Crane-(V) Inspection and Test Plan | G115 | QA/QC | A-Overall management | YES | QA/QC | General | SEPCOIII | STG Building Overhead Crane | IFA | IFP |  |  | 2025-09-04 |  |  |  | 2025-09-24 |  |  |  | 2025-10-30 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2762 | LATER | NUCLEON | SAU4005-G115-SMM-&AQA-08908 | STG Overhead Crane-(V) FAT Procedure | G115 | QA/QC | A-Overall management | YES | QA/QC | General | SEPCOIII | STG Building Overhead Crane | IFA | IFP |  |  | 2025-09-04 |  |  |  | 2025-09-24 |  |  |  | 2025-10-30 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2763 | LATER | NUCLEON | SAU4005-G115-SMM-&AQC-08909 | STG Overhead Crane-(V) FAT Report | G115 | QA/QC | A-Overall management | YES | QA/QC | General | SEPCOIII | STG Building Overhead Crane | IFA | IFP |  |  | 2026-01-09 |  |  |  | 2026-01-29 |  |  |  | 2026-03-06 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2764 | LATER | NUCLEON | SAU4005-G115-SMM-&AQC-08910 | STG Overhead Crane-(V) End of Manufacturing Record | G115 | QA/QC | A-Overall management | NO | QA/QC | General | SEPCOIII | STG Building Overhead Crane | IFA | IFP |  |  | 2026-01-09 |  |  |  | 2026-01-29 |  |  |  | 2026-03-06 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2765 | LATER | NUCLEON | SAU4005-G115-SMM-&ELD-08911 | STG Overhead Crane-(V) Busbar installation drawing | G115 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | STG Building Overhead Crane | IFA | IFD |  |  | 2025-09-04 |  | 2025-10-09 |  | 2025-09-24 |  | 2025-10-23 |  | 2025-10-30 |  | 2026-01-22 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2766 | LATER | NUCLEON | SAU4005-G115-SMM-&MED-08912 | STG Overhead Crane-(V) Calculation sheet | G115 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STG Building Overhead Crane | IFA | IFD |  |  | 2025-09-04 |  |  |  | 2025-09-24 |  |  |  | 2025-10-30 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2767 | LATER | NUCLEON | SAU4005-G115-SMM-&MDA-08913 | STG Overhead Crane-(V) Mechanical detail drawing | G115 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STG Building Overhead Crane | IFI | IFD | [14 empty] | 2025-09-04 |  | 2025-10-09 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2768 | LATER | NUCLEON | SAU4005-G115-SMM-&MDA-08914 | STG Overhead Crane-(V) Motor data sheet | G115 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STG Building Overhead Crane | IFI | IFD | [14 empty] | 2025-09-04 |  | 2025-10-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2770 | LATER | NUCLEON | SAU4005-G115-SMM-&ABF-08916 | STG Overhead Crane-(V) Storage and handling procedure | G115 | Engineering | A-Overall management | YES | GENERAL | General | SEPCOIII | STG Building Overhead Crane | IFI | IFP | [14 empty] | 2025-11-04 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2771 | LATER | NUCLEON | SAU4005-G115-SMM-&BDC-08917 | STG Overhead Crane-(V) Training manual | G115 | Operation & Maintenacne | B-Overall technology | YES | O&M | General | SEPCOIII | STG Building Overhead Crane | IFI | IFP | [14 empty] | 2025-09-04 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2772 | LATER | NUCLEON | SAU4005-G115-SMM-&ABF-08918 | STG Overhead Crane-(V) Packing list | G115 | Engineering | A-Overall management | NO | GENERAL | General | SEPCOIII | STG Building Overhead Crane | IFI | IFP | [14 empty] | 2025-09-04 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2773 | LATER | NUCLEON | SAU4005-G115-SMM-&CLD-08919 | STG Overhead Crane-(V) Rail fixing arrangement | G115 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | STG Building Overhead Crane | IFA | IFD |  |  | 2025-09-04 |  | 2025-10-24 |  | 2025-09-24 |  | 0 |  | 2025-10-30 |  | 2025-11-09 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
i | NEW | 2774 | LATER | NUCLEON | SAU4005-G115-SMM-&AQA-08920 | STG Overhead Crane(V)-Painting Procedure | G115 | QA/QC | A-Overall management | YES | QA/QC | General | SEPCOIII | STG Building Overhead Crane | IFI | [15 empty] | 2026-02-24 |  | 2026-01-19 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO
| NEW | 2775 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09001 | Cranes and Hoists(V)-Technical Datasheet for Crane | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-10 |  | 2026-02-06 |  | 2026-01-30 |  | 2026-05-21 |  | 2026-03-07 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO
| NEW | 2776 | LATER | NUCLEON | SAU4005-G116-SMO-&MED-09002 | Cranes and Hoists(V)-Mechanism Sizing Calculation | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFI | IFC | [14 empty] | 2026-01-10 |  | 2026-03-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
| dcc changed | 2777 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09003 | Cranes and Hoists(V)-Nameplate | G116 | Engineering | B-Overall technology | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-04-16 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO
| NEW | 2778 | LATER | NUCLEON | SAU4005-G116-SMO-&ADC-09004 | Cranes and Hoists(V)-Installation, Operation, and Maintenance Manuals | G116 | Operation & Maintenacne | A-Overall management | YES | O&M | General | SEPCOIII | Cranes & Hoists | IFI | IFC | [14 empty] | 2026-01-10 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
| NEW | 2779 | LATER | NUCLEON | SAU4005-G116-SMO-&MTB-09005 | Cranes and Hoists(V)-3D Model | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFI | IFC | [14 empty] | 2026-02-20 |  | 2026-04-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
| NEW | 2780 | LATER | NUCLEON | SAU4005-G116-SMO-&EFF-09006 | Cranes and Hoists(V)-Electrical Schematic Diagram | G116 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Cranes & Hoists | IFI | IFC | [14 empty] | 2026-02-20 |  | 2026-04-13 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
| NEW | 2781 | LATER | NUCLEON | SAU4005-G116-SMO-&ETL-09007 | Cranes and Hoists(V)-Control cabin layout | G116 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Cranes & Hoists | IFI | IFC | [14 empty] | 2026-02-20 |  | 2026-03-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
| NEW | 2782 | LATER | NUCLEON | SAU4005-G116-SMO-&ETL-09008 | Cranes and Hoists(V)-Control Panel GA & Specification | G116 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Cranes & Hoists | IFI | IFC | [14 empty] | 2026-02-20 |  | 2026-03-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
| NEW | 2783 | LATER | NUCLEON | SAU4005-G116-SMO-&ELD-09009 | Cranes and Hoists(V)-DSL fixing arrangement | G116 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Cranes & Hoists | IFI | IFC | [14 empty] | 2026-02-20 |  | 2026-02-06 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
| dcc changed | 2784 | LATER | NUCLEON | SAU4005-G116-SMO-&EEC-09010 | Cranes and Hoists(V)-Load List | G116 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Cranes & Hoists | IFI | IFC | [14 empty] | 2026-02-20 |  | 2026-04-08 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
| NEW | 2785 | LATER | NUCLEON | SAU4005-G116-SMO-&EED-09011 | Cranes and Hoists(V)-DSL busbar sizing calculation & Voltage drop calculation | G116 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Cranes & Hoists | IFI | IFC | [14 empty] | 2026-02-20 |  | 2026-02-06 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
| NEW | 2786 | LATER | NUCLEON | SAU4005-G116-SMO-&EEC-09012 | Cranes and Hoists(V)-VFD Specification details | G116 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Cranes & Hoists | IFI | IFC | [14 empty] | 2026-02-20 |  | 2026-02-06 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
| NEW | 2787 | LATER | NUCLEON | SAU4005-G116-SMO-&ABE-09013 | Cranes and Hoists(V)-Manufacturing schedule | G116 | Planning | A-Overall management | YES | MECH&PROCESS&WTP | General | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-02-20 |  |  |  | 2026-03-12 |  |  |  | 2026-04-17 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO
| NEW | 2788 | LATER | NUCLEON | SAU4005-G116-SMO-&AQA-09014 | Cranes and Hoists(V)-Shop Performance Test Procedure | G116 | QA/QC | A-Overall management | YES | QA/QC | General | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-02-20 |  | 2026-03-02 |  | 2026-03-12 |  | 2026-04-23 |  | 2026-04-17 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO
| NEW | 2789 | LATER | NUCLEON | SAU4005-G116-SMO-&AQA-09015 | Cranes and Hoists(V)-NDE testing procedures | G116 | QA/QC | A-Overall management | YES | QA/QC | General | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-02-20 |  |  |  | 2026-03-12 |  |  |  | 2026-04-17 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO
| NEW | 2790 | LATER | NUCLEON | SAU4005-G116-SMO-&MEC-09016 | Cranes and Hoists(V)-Surface preparation and painting, coating system specifications | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-02-20 |  | 2026-04-03 |  | 2026-03-12 |  | 2026-02-11 |  | 2026-04-17 |  | 2026-04-26 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO
| NEW | 2791 | LATER | NUCLEON | SAU4005-G116-SMO-&MTC-09017 | Cranes and Hoists(V)-Welding procedures and welding procedure qualification | G116 | QA/QC | M-Mechanical engineering (normally including process engineering) | YES | QA/QC | General | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-02-20 |  |  |  | 2026-03-12 |  |  |  | 2026-04-17 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO
| NEW | 2792 | LATER | NUCLEON | SAU4005-G116-SMO-&AQA-09018 | Cranes and Hoists(V)-Auxiliary Cranes and Hoists Inspection and Test Plan | G116 | QA/QC | A-Overall management | YES | QA/QC | General | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-02-20 |  | 2026-03-02 |  | 2026-03-12 |  | 0 |  | 2026-04-17 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO
| NEW | 2793 | LATER | NUCLEON | SAU4005-G116-SMO-&AQC-09019 | Cranes and Hoists(V)-Manufacture recording book | G116 | QA/QC | A-Overall management | YES | QA/QC | General | SEPCOIII | Cranes & Hoists | IFI | IFC | [14 empty] | 2026-02-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO | NO
| NEW | 2794 | LATER | NUCLEON | SAU4005-G116-SMO-&CLD-09020 | Cranes and Hoists(V)-Rail fixing Arrangement for WORKSHOP | G116 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-06 |  | 2026-02-09 |  | 2026-03-03 |  | 2026-03-17 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO
| NEW | 2795 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09021 | Cranes and Hoists(V)-GA drawing of WTP/ETP BUILDING | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 2026-03-29 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO
| NEW | 2796 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09022 | Cranes and Hoists(V)-GA drawing of WORKSHOP | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO
| NEW | 2797 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09023 | Cranes and Hoists(V)-GA drawing of FUEL OIL PUMP SHED | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 2026-05-06 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO
| NEW | 2798 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09024 | Cranes and Hoists(V)-GA drawing of AIR COMPRESSOR SHED | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES | NO
| NEW | 2799 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09025 | Cranes and Hoists(V)-GA drawing of WTP/ETP BUILDING | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 2026-03-29 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2800 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09026 | Cranes and Hoists(V)-GA drawing of WTP/ETP Building-(Filter Press Area) | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 2026-05-06 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2801 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09027 | Cranes and Hoists(V)-GA drawing of WTP/ETP Building-(Storage Tank Area) | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2802 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09028 | Cranes and Hoists(V)-GA drawing of FIRE WATER PUMP SHELTER | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2803 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09029 | Cranes and Hoists(V)-GA drawing of SERVICE WATER (TREATED WASTE WATER) PUMP AREA | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 2026-03-29 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2804 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09030 | Cranes and Hoists(V)-GA drawing of DM AND SERVICE WATER PUMP SHED | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 2026-03-29 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2805 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09031 | Cranes and Hoists(V)-GA drawing of BOILER FEED PUMP AREA | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2806 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09032 | Cranes and Hoists(V)-GA drawing of GENERATOR CIRCUIT BREAKER | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 2026-03-29 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2807 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09033 | Cranes and Hoists(V)-GA drawing of MAIN ELECTRICAL CONTROL BUILDING | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 2026-03-23 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2808 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09034 | Cranes and Hoists(V)-GA drawing of Hoist-1 for GT # 11,12 & 13 FOR GENERATOR BEARING SHIELD REMOVAL (TURBINE SIDE) | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 2026-03-23 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2809 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09035 | Cranes and Hoists(V)-GA drawing of Hoist-3 for GT # 11,12 & 13 FOR GENERATOR Slip Ring Removal | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 2026-03-23 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2810 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09036 | Cranes and Hoists(V)-GA drawing of Hoist-4 for GT # 11,12 & 13 Lube Oil Skid area | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2811 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09037 | Cranes and Hoists(V)-GA drawing of HOIST FOR HP BYPASS VALVE | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 2026-05-06 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2812 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09038 | Cranes and Hoists(V)-GA drawing of HOIST FOR HR BYPASS VALVE | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 2026-05-03 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2813 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09039 | Cranes and Hoists(V)-GA drawing of HOIST FOR LP BYPASS VALVE | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 2026-05-06 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2814 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09040 | Cranes and Hoists(V)-GA drawing of MISC. AREA | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2815 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09041 | Cranes and Hoists(V)-GA drawing of MAIN ELECTRICAL & CONTROL BUILDING | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 2026-03-23 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2816 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09042 | Cranes and Hoists(V)-GA drawing of MV/LV ELECTRICAL SWITCHGEAR BUILDING | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 2026-03-23 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2817 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09043 | Cranes and Hoists(V)-GA drawing of GT MCC | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 2026-03-23 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2818 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09044 | Cranes and Hoists(V)-GA drawing of WORKSHOP & WARE HOUSE | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 2026-03-23 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2819 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09045 | Cranes and Hoists(V)-GA drawing of ADMINISTRATION & SOCIAL BUILDING | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 2026-03-29 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2820 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09046 | Cranes and Hoists(V)-GA drawing of FUEL GAS ELECTRICAL SWITCHGEAR BUILDING | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 2026-03-29 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2821 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09047 | Cranes and Hoists(V)-GA drawing of SEARCH FACILITY & VISITORS CENTER | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 2026-03-29 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2822 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09048 | Cranes and Hoists(V)-GA drawing of SECURITY CONTROL CENTER | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 2026-03-23 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2823 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09049 | Cranes and Hoists(V)-GA drawing of WATER TREATMENT CHEMICAL AND LABORATORY BUILDING | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 2026-03-23 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2824 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09050 | Cranes and Hoists(V)-GA drawing of WATER MISC (STG, ETP, HGD) (HOLD) | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 2026-03-23 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2825 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09051 | Cranes and Hoists(V)-GA drawing of Filter Seperator | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 2026-03-23 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2826 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09052 | Cranes and Hoists(V)-GA drawing of WTP Area | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-01-20 |  | 2026-02-01 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-03-17 |  | 2026-03-23 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2827 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09053 | Cranes & Hoists(V)-GA drawing of Hoist-2 for GT # 11,12 & 13 FOR GENERATOR COOLER REMOVAL | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-03-15 |  | 2026-02-06 |  | 2026-04-04 |  | 2026-02-11 |  | 2026-05-10 |  | 2026-03-23 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 2828 | LATER | NUCLEON | SAU4005-G116-SMO-&MDA-09054 | Cranes & Hoists(V)-GA drawing of BFP MV BFD | G116 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cranes & Hoists | IFA | IFC |  |  | 2026-03-15 |  | 2026-03-06 |  | 2026-04-04 |  | 2026-02-11 |  | 2026-05-10 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2830 | LATER | ZWL | SAU4005-G119-GAF-&MDA-09801 | Horizontal Pump(V)-Pump GA drawing | G119 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Horizontal Pump | IFA | IFD |  |  | 2025-10-18 |  | 2025-08-22 |  | 2025-11-07 |  | 2025-09-02 |  | 2025-12-13 |  | 2025-10-22 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2831 | LATER | ZWL | SAU4005-G119-GAF-&EDA-09802 | Horizontal Pump(V)-Motor GA drawing | G119 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Horizontal Pump | IFA | IFD |  |  | 2025-10-18 |  | 2025-08-29 |  | 2025-11-07 |  | 2025-09-16 |  | 2025-12-13 |  | 2025-10-14 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2832 | LATER | ZWL | SAU4005-G119-GAF-&MDB-09803 | Horizontal Pump(V)-Pump performance curve | G119 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Horizontal Pump | IFA | IFD |  |  | 2025-10-18 |  | 2025-08-22 |  | 2025-11-07 |  | 2025-09-16 |  | 2025-12-13 |  | 2025-10-22 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2833 | LATER | ZWL | SAU4005-G119-GAF-&MDA-09804 | Horizontal Pump(V)-Nameplate drawing | G119 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Horizontal Pump | IFA | IFD |  |  | 2025-10-18 |  | 2025-09-24 |  | 2025-11-07 |  | 2025-10-09 |  | 2025-12-13 |  | 2026-01-28 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2834 | LATER | ZWL | SAU4005-G119-GAF-&MDA-09805 | Horizontal Pump(V)-Pump Data sheet | G119 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Horizontal Pump | IFA | IFD |  |  | 2025-10-18 |  | 2025-09-07 |  | 2025-11-07 |  | 2025-10-09 |  | 2025-12-13 |  | 2025-12-14 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2835 | LATER | ZWL | SAU4005-G119-GAF-&MPB-09806 | Horizontal Pump(V)-Pump Cross-sectional drawings and bill of materials | G119 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Horizontal Pump | IFI | IFD | [14 empty] | 2025-10-18 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2836 | LATER | ZWL | SAU4005-G119-GAF-&MDA-09807 | Horizontal Pump(V)-Pump Shaft seal and coupling drawings | G119 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Horizontal Pump | IFI | IFD | [14 empty] | 2025-11-01 |  | 2025-10-12 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2837 | LATER | ZWL | SAU4005-G119-GAF-&EDA-09808 | Horizontal Pump(V)-Motor Data sheet | G119 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Horizontal Pump | IFA | IFD |  |  | 2025-11-01 |  | 2025-09-07 |  | 2025-11-21 |  | 2025-10-09 |  | 2025-12-27 |  | 2025-12-09 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2838 | LATER | ZWL | SAU4005-G119-GAF-&EEC-09809 | Horizontal Pump(V)-Electrical Load List | G119 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Horizontal Pump | IFA | IFD |  |  | 2025-10-18 |  |  |  | 2025-11-07 |  |  |  | 2025-12-13 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2839 | LATER | ZWL | SAU4005-G119-GAF-&EFP-09810 | Horizontal Pump(V)-IO List | G119 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Horizontal Pump | IFA | IFD |  |  | 2025-10-18 |  | 2025-12-23 |  | 2025-11-07 |  | 0 |  | 2025-12-13 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2840 | LATER | ZWL | SAU4005-G119-GAF-&APB-09811 | Horizontal Pump(V)-Spare parts list ( commissioning and 2 years operation and special tool list (if applicable) ) | G119 | Engineering | A-Overall management | YES | GENERAL | General | SEPCOIII | Horizontal Pump | IFI | IFD | [14 empty] | 2025-11-01 |  | 2026-04-10 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2841 | LATER | ZWL | SAU4005-G119-GAF-&APB-09812 | Horizontal Pump(V)-Lubricants list First Fill details | G119 | Engineering | A-Overall management | YES | GENERAL | General | SEPCOIII | Horizontal Pump | IFI | IFD | [14 empty] | 2025-11-01 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2842 | LATER | ZWL | SAU4005-G119-GAF-&APB-09813 | Horizontal Pump(V)-Chemicals Consumables list | G119 | Engineering | A-Overall management | YES | GENERAL | General | SEPCOIII | Horizontal Pump | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-12-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2843 | LATER | ZWL | SAU4005-G119-GAF-&MDC-09814 | Horizontal Pump(V)-OM and start up commissioning manuals of pumps | G119 | Operation & Maintenacne | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Horizontal Pump | IFI | IFD | [14 empty] | 2025-11-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2844 | LATER | ZWL | SAU4005-G119-GAF-&EDC-09815 | Horizontal Pump(V)-OM and start up commissioning manuals of motors | G119 | Operation & Maintenacne | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Horizontal Pump | IFA | IFD |  |  | 2025-11-29 |  |  |  | 2025-12-19 |  |  |  | 2026-01-24 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2845 | LATER | ZWL | SAU4005-G119-GAF-&ADC-09816 | Horizontal Pump(V)-Surface preparation & coating Procedure | G119 | Engineering | A-Overall management | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Horizontal Pump | IFI | IFD | [14 empty] | 2025-11-01 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2846 | LATER | ZWL | SAU4005-G119-GAF-&MDA-09818 | Horizontal Pump(V)-Valve List & Valve GA | G119 | Project Management | A-Overall management | YES | GENERAL | General | SEPCOIII | Horizontal Pump | IFA | IFD |  |  | 2025-11-01 |  |  |  | 2025-11-21 |  |  |  | 2025-12-27 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2847 | LATER | ZWL | SAU4005-G119-GAF-&EEC-09819 | Horizontal Pump(V)-Instrument list | G119 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Horizontal Pump | IFA | IFD |  |  | 2025-11-01 |  | 2025-11-28 |  | 2025-11-21 |  | 2025-10-14 |  | 2025-12-27 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2852 | LATER | ZWL | SAU4005-G119-GAF-&BQC-09824 | Horizontal Pump(V)-Type test reports/as-built information | G119 | QA/QC | B-Overall technology | YES | QA/QC | General | SEPCOIII | Horizontal Pump | IFI | IFD | [14 empty] | 2026-03-21 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2854 | LATER | ZWL | SAU4005-G119-GAF-&EDA-09826 | Horizontal Pump(V)-Outline Diagram and Technical details of Junction Box | G119 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | GENERAL | General | SEPCOIII | Horizontal Pump | IFA | IFD |  |  | 2025-11-01 |  | 2025-09-15 |  | 2025-11-21 |  | 2025-10-02 |  | 2025-12-27 |  | 2025-11-09 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2855 | LATER | ZWL | SAU4005-G119-GAF-&EDA-09827 | Horizontal Pump(V)-Internal wiring diagrams up to Junction Box | G119 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Horizontal Pump | IFA | IFD |  |  | 2025-11-01 |  | 2025-11-01 |  | 2025-11-21 |  | 2025-10-02 |  | 2025-12-27 |  | 2025-11-20 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2856 | LATER | ZWL | SAU4005-G119-GAF-&ADC-09828 | Horizontal Pump(V)-Instrumentation O&M Manuals | G119 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Horizontal Pump | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-09-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2857 | LATER | ZWL | SAU4005-G119-GAF-&EDA-09829 | Horizontal Pump(V)-Electrical schematic diagram (SLD) | G119 | Operation & Maintenacne | A-Overall management | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Horizontal Pump | IFA | IFD |  |  | 2025-11-01 |  | 2025-09-24 |  | 2025-11-21 |  | 2025-10-14 |  | 2025-12-27 |  | 2025-12-29 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2858 | LATER | ZWL | SAU4005-G119-GAF-&EDA-09830 | Horizontal Pump(V)-LCP of Potable Water Unloading Pump(V)- motor Electrical schematic diagram & GAD | G119 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Horizontal Pump | IFA | IFD |  |  | 2025-10-18 |  | 2025-09-15 |  | 2025-11-07 |  | 0 |  | 2025-12-13 |  | 2025-10-09 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2859 | LATER | ZWL | SAU4005-G119-GAF-&MLD-09831 | Horizontal Pump(V)-P&I Diagram | G119 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Horizontal Pump | IFA | IFD |  |  | 2025-10-18 |  | 2025-10-14 |  | 2025-11-07 |  | 2025-10-12 |  | 2025-12-13 |  | 2026-01-08 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2860 | LATER | ZWL | SAU4005-G119-GAF-&MDC-09832 | Horizontal Pump(V)-Noise Datasheets / guarantees | G119 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Horizontal Pump | IFA | IFD |  |  | 2025-11-01 |  | 2025-11-17 |  | 2025-11-21 |  | 2025-10-09 |  | 2025-12-27 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2861 | LATER | ZWL | SAU4005-G119-GAF-&APC-09833 | Horizontal Pump(V)-Packing List of the Proposed Equipment | G119 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Horizontal Pump | IFI | IFD | [14 empty] | 2025-11-01 |  | 2025-10-31 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2862 | LATER | ZWL | SAU4005-G119-GAF-&MDA-09834 | Horizontal Pump(V)-Strainer GA drawing | G119 | Engineering | A-Overall management | YES | GENERAL | General | SEPCOIII | Horizontal Pump | IFI | IFD | [14 empty] | 2025-11-01 |  | 2025-09-15 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2864 | LATER | ZWL | SAU4005-G120-GAF-&MDA-10102 | Vertical Pump(V)-Pump GA drawing | G120 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | ELECTRICAL | Mechanical | SEPCOIII | Vertical Pump | IFA | IFD |  |  | 2025-10-18 |  | 2025-08-26 |  | 2025-11-07 |  | 2025-09-10 |  | 2025-12-13 |  | 2025-10-22 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2865 | LATER | ZWL | SAU4005-G120-GAF-&EDA-10103 | Vertical Pump(V)-Motor GA drawing, | G120 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | Electrical | SEPCOIII | Vertical Pump | IFA | IFD |  |  | 2025-10-18 |  |  |  | 2025-11-07 |  |  |  | 2025-12-13 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2866 | LATER | ZWL | SAU4005-G120-GAF-&MDB-10104 | Vertical Pump(V)-Pump performance curve | G120 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Vertical Pump | IFA | IFD |  |  | 2025-10-18 |  | 2025-09-08 |  | 2025-11-07 |  | 2025-09-10 |  | 2025-12-13 |  | 2025-10-27 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2867 | LATER | ZWL | SAU4005-G120-GAF-&MDA-10105 | Vertical Pump(V)-Nameplate drawing | G120 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Vertical Pump | IFA | IFD |  |  | 2025-10-18 |  | 2025-09-29 |  | 2025-11-07 |  | 0 |  | 2025-12-13 |  | 2025-10-15 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2868 | LATER | ZWL | SAU4005-G120-GAF-&MDA-10106 | Vertical Pump(V)-Pump Data sheet | G120 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Vertical Pump | IFA | IFD |  |  | 2025-10-18 |  | 2025-09-08 |  | 2025-11-07 |  | 2025-09-23 |  | 2025-12-13 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2869 | LATER | ZWL | SAU4005-G120-GAF-&MPB-10107 | Vertical Pump(V)-Pump Cross-sectional drawings and bill of materials | G120 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Vertical Pump | IFI | IFD | [14 empty] | 2025-11-01 |  | 2025-09-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2870 | LATER | ZWL | SAU4005-G120-GAF-&MDA-10108 | Vertical Pump(V)-Pump Shaft seal and coupling drawings | G120 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | ELECTRICAL | Mechanical | SEPCOIII | Vertical Pump | IFI | IFD | [14 empty] | 2025-11-01 |  | 2025-10-12 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2871 | LATER | ZWL | SAU4005-G120-GAF-&EDA-10109 | Vertical Pump(V)-Motor Data sheet | G120 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Vertical Pump | IFA | IFD |  |  | 2025-10-18 |  | 2025-10-24 |  | 2025-11-07 |  | 2025-09-10 |  | 2025-12-13 |  | 2025-12-30 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2872 | LATER | ZWL | SAU4005-G120-GAF-&EEC-10110 | Vertical Pump(V)-Electrical Load List | G120 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Vertical Pump | IFA | IFD |  |  | 2025-10-18 |  |  |  | 2025-11-07 |  |  |  | 2025-12-13 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2874 | LATER | ZWL | SAU4005-G120-GAF-&APB-10112 | Vertical Pump(V)-Spare parts list ( commissioning and 2 years operation and special tool list (if applicable) ) | G120 | Engineering | A-Overall management | YES | GENERAL | General | SEPCOIII | Vertical Pump | IFI | IFD | [14 empty] | 2025-11-01 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2875 | LATER | ZWL | SAU4005-G120-GAF-&APB-10113 | Vertical Pump(V)-Lubricants list First Fill details | G120 | Engineering | A-Overall management | YES | GENERAL | General | SEPCOIII | Vertical Pump | IFI | IFD | [14 empty] | 2025-11-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2876 | LATER | ZWL | SAU4005-G120-GAF-&APB-10114 | Vertical Pump(V)-Chemicals Consumables list | G120 | Engineering | A-Overall management | YES | MECH&PROCESS&WTP | General | SEPCOIII | Vertical Pump | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-12-09 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2877 | LATER | ZWL | SAU4005-G120-GAF-&MDC-10115 | Vertical Pump(V)-OM and start up commissioning manuals of pumps | G120 | Operation & Maintenacne | M-Mechanical engineering (normally including process engineering) | YES | ELECTRICAL | Mechanical | SEPCOIII | Vertical Pump | IFI | IFD | [14 empty] | 2025-11-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2878 | LATER | ZWL | SAU4005-G120-GAF-&EDC-10116 | Vertical Pump(V)-OM and start up commissioning manuals of motors | G120 | Operation & Maintenacne | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | Electrical | SEPCOIII | Vertical Pump | IFI | IFD | [14 empty] | 2025-11-01 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2879 | LATER | ZWL | SAU4005-G120-GAF-&ADC-10117 | Vertical Pump(V)-Surface preparation & coating Procedure | G120 | Engineering | A-Overall management | YES | GENERAL | Mechanical | SEPCOIII | Vertical Pump | IFA | IFD |  |  | 2025-11-01 |  | 2026-01-23 |  | 2025-11-21 |  | 2025-09-10 |  | 2025-12-27 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2880 | LATER | ZWL | SAU4005-G120-GAF-&EEC-10120 | Vertical Pump(V)-Instrument list | G120 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | Electrical | SEPCOIII | Vertical Pump | IFA | IFD |  |  | 2025-11-01 |  | 2025-10-31 |  | 2025-11-21 |  | 0 |  | 2025-12-27 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2885 | LATER | ZWL | SAU4005-G120-GAF-&BQC-10125 | Vertical Pump(V)-Type test reports/as-built information | G120 | QA/QC | B-Overall technology | YES | GENERAL | General | SEPCOIII | Vertical Pump | IFI | IFD | [14 empty] | 2025-11-01 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2887 | LATER | ZWL | SAU4005-G120-GAF-&EDA-10127 | Vertical Pump(V)-Outline Diagram and Technical details of Junction Box | G120 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Vertical Pump | IFA | IFD |  |  | 2025-11-29 |  | 2025-11-01 |  | 2025-11-21 |  | 0 |  | 2025-12-27 |  | 2025-11-20 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2891 | LATER | ZWL | SAU4005-G120-GAF-&MLD-10131 | Vertical Pump(V)-P&I Diagram | G120 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Vertical Pump | IFA | IFD |  |  | 2025-11-01 |  | 2025-09-24 |  | 2025-11-21 |  | 2025-09-10 |  | 2025-12-27 |  | 2026-01-25 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2892 | LATER | ZWL | SAU4005-G120-GAF-&MDC-10132 | Vertical Pump(V)-Noise Datasheets / guarantees | G120 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Vertical Pump | IFI | IFD | [14 empty] | 2025-11-01 |  | 2025-10-31 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2893 | LATER | ZWL | SAU4005-G120-GAF-&APC-10133 | Vertical Pump(V)-Packing List of the Proposed Equipment | G120 | Engineering | A-Overall management | YES | GENERAL | General | SEPCOIII | Vertical Pump | IFI | IFD | [14 empty] | 2025-11-01 |  | 2025-10-31 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2899 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&BPB-12406 | CCCW (V)-Spare Parts list and consumables (commissioning and 2 years operation) | G137 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | GENERAL | GENERAL | SEPCOIII | CCCW | IFI | IFD | [14 empty] | 2025-10-30 |  | 2025-10-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2901 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&BDC-12408 | CCCW (V)-O&M Manuals, and start/up commissioning manuals | G137 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | GENERAL | GENERAL | SEPCOIII | CCCW | IFI | IFD | [14 empty] | 2025-12-30 |  | 2025-12-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2902 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&BDA-12409 | CCCW (V)-Nameplate drawings | G137 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | GENERAL | GENERAL | SEPCOIII | CCCW | IFI | IFD | [14 empty] | 2025-12-30 |  | 2026-01-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2903 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&BDC-12410 | CCCW (V)-Field Installation/Erection Instructions/Procedure | G137 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | GENERAL | GENERAL | SEPCOIII | CCCW | IFI | IFD | [14 empty] | 2025-12-30 |  | 2026-01-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2907 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&AAB-12414 | CCCW (V)-General Arrangement drawing | G137 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | CCCW | IFA | IFD |  |  | 2025-10-30 |  | 2025-08-26 |  | 2025-11-19 |  | 2025-09-08 |  | 2025-12-25 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2908 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&MDA-12415 | CCCW (V)-Cross-sectional drawings and bill of materials | G137 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | CCCW | IFI | IFD | [14 empty] | 2025-10-30 |  | 2025-10-11 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2909 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&MDA-12416 | CCCW (V)-Shaft seal and coupling drawings, including bill of materials | G137 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | CCCW | IFI | IFD | [14 empty] | 2025-10-30 |  | 2025-11-10 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2910 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&AAB-12417 | CCCW (V)-Foundation load and anchorage details | G137 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | CCCW | IFA | IFD |  |  | 2025-10-30 |  | 2025-10-24 |  | 2025-11-19 |  | 0 |  | 2025-12-25 |  | 2025-11-09 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2911 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&MDA-12418 | CCCW (V)-Pump Data Sheets | G137 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | CCCW | IFA | IFD |  |  | 2025-10-30 |  | 2025-08-26 |  | 2025-11-19 |  | 2025-09-08 |  | 2025-12-25 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2912 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&MDF-12419 | CCCW (V)-Pump Performance Curves | G137 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | CCCW | IFA | IFD |  |  | 2025-10-30 |  |  |  | 2025-11-19 |  |  |  | 2025-12-25 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2913 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&MFB-12420 | CCCW (V)-P&I Diagram | G137 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | CCCW | IFA | IFD |  |  | 2025-10-30 |  |  |  | 2025-11-19 |  |  |  | 2025-12-25 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2914 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&MDB-12421 | CCCW (V)-System / Equipment Design Description | G137 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | CCCW | IFI | IFD | [14 empty] | 2025-10-30 |  | 2025-11-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2915 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&MPB-12422 | CCCW (V)-Valve List | G137 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | CCCW | IFI | IFD | [14 empty] | 2025-10-30 |  | 2025-10-27 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2916 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&MPB-12423 | CCCW (V)-Utility Consumpation and Load List, i.e. power/water/air/oil,etc., in excel/pdf Version | G137 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | CCCW | IFI | IFD | [14 empty] | 2025-10-30 |  | 2025-10-31 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2917 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&MDC-12424 | CCCW (V)-Site lay down area requirements | G137 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | CCCW | IFI | IFD | [14 empty] | 2025-10-30 |  | 2025-10-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2919 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&MCA-12426 | CCCW (V)-Mechanical calculations | G137 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | CCCW | IFA | IFD |  |  | 2025-10-30 |  | 2025-11-24 |  | 2025-11-19 |  | 2025-12-09 |  | 2025-12-25 |  | 2026-04-13 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2920 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&EDA-12427 | CCCW (V)-Motor outline & cross section | G137 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII | CCCW | IFA | IFD |  |  | 2025-10-30 |  |  |  | 2025-11-19 |  |  |  | 2025-12-25 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2921 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&EDA-12428 | CCCW (V)-Motor data sheets | G137 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII | CCCW | IFA | IFD |  |  | 2025-10-30 |  | 2025-08-28 |  | 2025-11-19 |  | 2025-09-16 |  | 2025-12-25 |  | 2026-04-12 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2922 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&EDA-12429 | CCCW (V)-Characteristic Curves: (motor performance) | G137 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII | CCCW | IFA | IFD |  |  | 2025-10-30 |  |  |  | 2025-11-19 |  |  |  | 2025-12-25 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2923 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&EEC-12430 | CCCW (V)-Elementary Diagrams | G137 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII | CCCW | IFA | IFD |  |  | 2025-10-30 |  | 2025-12-26 |  | 2025-11-19 |  | 0 |  | 2025-12-25 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| SUBMISSION PLAN CHANGED | 2924 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&EEC-12431 | CCCW (V)-Connections diagrams of the terminal boxes & Motor Accessary Terminal Box Assembly Drawing | G137 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII | CCCW | IFA | IFD |  |  | 2026-08-14 |  |  |  | 2026-09-03 |  |  |  | 2026-10-09 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2926 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&EEC-12433 | CCCW (V)-Stator winding connections diagrams operation. | G137 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII | CCCW | IFA | IFD |  |  | 2025-10-30 |  | 2025-09-29 |  | 2025-11-19 |  | 2025-09-16 |  | 2025-12-25 |  | 2025-10-14 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2927 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&EDC-12434 | CCCW (V)-Wiring Diagrams | G137 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII | CCCW | IFA | IFD |  |  | 2025-10-30 |  |  |  | 2025-11-19 |  |  |  | 2025-12-25 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2929 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&EEC-12436 | CCCW (V)-Electrical Load List | G137 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII | CCCW | IFA | IFD |  |  | 2025-10-30 |  | 2025-09-29 |  | 2025-11-19 |  | 2025-09-16 |  | 2025-12-25 |  | 2026-04-28 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2930 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&EEC-12437 | CCCW (V)-Motor Heater Terminal Box Assembly Drawing | G137 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | ELECTRICAL | ELECTRICAL | SEPCOIII | CCCW | IFA | IFD |  |  | 2025-10-30 |  | 2025-09-29 |  | 2025-11-19 |  | 2025-09-16 |  | 2025-12-25 |  | 2026-03-31 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2931 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&EPB-12438 | CCCW (V)-Final Bill of Quantity (BOQ) for Instrumentation Items | G137 | Logistics | M-Mechanical engineering (normally including process engineering) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | CCCW | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-12-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2932 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&EDC-12439 | CCCW (V)-Instruments list | G137 | Logistics | M-Mechanical engineering (normally including process engineering) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | CCCW | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-12-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2933 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&EDC-12440 | CCCW (V)-Instruments data sheets along with Catalogues | G137 | Logistics | M-Mechanical engineering (normally including process engineering) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | CCCW | IFA | IFD |  |  | 2025-11-29 |  | 2025-12-30 |  | 2025-12-19 |  | 2026-01-19 |  | 2026-01-24 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2934 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&EMA-12441 | CCCW (V)-Instrument hook-up drawing in Purchaser's format | G137 | Logistics | M-Mechanical engineering (normally including process engineering) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | CCCW | IFI | IFD | [14 empty] | 2025-11-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2935 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&EFP-12442 | CCCW (V)-I/O list along with List of Alarms | G137 | Logistics | M-Mechanical engineering (normally including process engineering) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | CCCW | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-12-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2936 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&EDC-12443 | CCCW (V)-Internal wiring diagrams up to junction boxes | G137 | Logistics | M-Mechanical engineering (normally including process engineering) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | CCCW | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-12-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2937 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&EFE-12444 | CCCW (V)-Control philosophy | G137 | Logistics | M-Mechanical engineering (normally including process engineering) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | CCCW | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-12-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2938 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&EDC-12445 | CCCW (V)-Instrumentation O&M Manuals | G137 | Logistics | M-Mechanical engineering (normally including process engineering) | Yes | General | Instrumentation and Control | SEPCOIII | CCCW | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-12-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2939 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&MDA-12446 | CCCW (V)-Noise Datasheets / guarantees | G137 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | CCCW | IFI | IFD | [14 empty] | 2025-10-30 |  | 2025-10-31 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2940 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&MQA-12447 | CCCW (V)-Quality Management Program | G137 | QA/QC | M-Mechanical engineering (normally including process engineering) | Yes | General | GENERAL | SEPCOIII | CCCW | IFI | IFD | [14 empty] | 2025-10-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2941 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&MQA-12448 | CCCW (V)-Inspection & Test Plan (ITP) | G137 | QA/QC | M-Mechanical engineering (normally including process engineering) | Yes | General | GENERAL | SEPCOIII | CCCW | IFA | IFD |  |  | 2025-10-30 |  | 2025-09-23 |  | 2025-11-19 |  | 0 |  | 2025-12-25 |  | 2026-01-11 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2942 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&MQA-12449 | CCCW (V)-Hydrostatic Test report and certificate | G137 | QA/QC | M-Mechanical engineering (normally including process engineering) | Yes | General | GENERAL | SEPCOIII | CCCW | IFA | IFD |  |  | 2025-12-30 |  |  |  | 2026-01-19 |  |  |  | 2026-02-24 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2943 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&MQC-12450 | CCCW (V)-Performance test Procedure | G137 | QA/QC | M-Mechanical engineering (normally including process engineering) | Yes | General | GENERAL | SEPCOIII | CCCW | IFA | IFD |  |  | 2025-12-30 |  | 2026-01-24 |  | 2026-01-19 |  | 2026-01-27 |  | 2026-02-24 |  | 2026-04-19 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2944 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&MQA-12451 | CCCW (V)-Performance test report | G137 | QA/QC | M-Mechanical engineering (normally including process engineering) | Yes | General | GENERAL | SEPCOIII | CCCW | IFA | IFD |  |  | 2025-12-30 |  |  |  | 2026-01-19 |  |  |  | 2026-02-24 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 2946 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&MQC-12453 | CCCW (V)-Site test procedures | G137 | QA/QC | M-Mechanical engineering (normally including process engineering) | Yes | General | GENERAL | SEPCOIII | CCCW | IFI | IFD | [14 empty] | 2025-12-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2947 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&MBF-12454 | CCCW (V)-Packaging & Shipping Instructions | G137 | QA/QC | M-Mechanical engineering (normally including process engineering) | Yes | General | GENERAL | SEPCOIII | CCCW | IFI | IFD | [14 empty] | 2025-12-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2948 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&MTC-12455 | CCCW (V)-Erection procedure and drawings. | G137 | QA/QC | M-Mechanical engineering (normally including process engineering) | Yes | General | GENERAL | SEPCOIII | CCCW | IFI | IFD | [14 empty] | 2025-12-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2949 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&MQA-12456 | CCCW (V)-Cleaning specification | G137 | QA/QC | M-Mechanical engineering (normally including process engineering) | Yes | General | GENERAL | SEPCOIII | CCCW | IFI | IFD | [14 empty] | 2026-01-29 |  | 2026-02-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| dcc changed | 2950 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&MQA-12457 | CCCW (V)-Surface preparation & coating Procedure | G137 | QA/QC | M-Mechanical engineering (normally including process engineering) | Yes | General | GENERAL | SEPCOIII | CCCW | IFI | IFD | [14 empty] | 2026-01-29 |  | 2026-03-27 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 2951 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&MQC-12458 | CCCW (V)-Packing List of the Proposed Equipment | G137 | QA/QC | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | CCCW | IFI | IFD | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 2952 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&AAB-12459 | CCCW (V)-General arrangement drawing of Strainer with counter flange | G137 | Engineering | A-Overall management | Yes | General | GENERAL | SEPCOIII | CCCW | IFA | IFD |  |  | 2025-11-14 |  | 2025-10-16 |  | 2025-12-04 |  | 0 |  | 2026-01-09 |  | 2025-10-30
| NEW | 2953 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&MDA-12460 | CCCW (V)-Strainer Data sheet | G137 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | CCCW | IFA | IFD |  |  | 2025-11-14 |  | 2025-10-31 |  | 2025-12-04 |  | 2025-11-18 |  | 2026-01-09 |  | 0
| NEW | 2954 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&MDA-12461 | CCCW (V)-Lifting drawing | G137 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | CCCW | IFI | IFD | [16 empty] | 2025-10-11
| NEW | 2955 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&ETL-12462 | CCCW (V)-Electrical equipment layout drawing | G137 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | ELECTRICAL | Electrical | SEPCOIII | CCCW | IFI | IFD | [16 empty] | 2025-10-11
| NEW | 2956 | LATER | CHANGSHA PUMP | SAU4005-G137-PGA-&EMA-12465 | CCCW (V)-Junction box outline & Internal junction box wiring diagram | G137 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | ELECTRICAL | SEPCOIII | CCCW | IFI | IFD | [16 empty] | 2025-12-30
|  | 2958 | LATER | SHENGDA | SAU4005-G140-EGA-&MLU-12501 | Fuel Oil System(V)-General Arrangement Drawing for Fuel Oil Unloading Pump Skid | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFA | IFC |  |  | 2025-11-20 |  | 2025-09-24 |  | 2025-12-10 |  | 2025-10-09 |  | 2026-01-15 |  | 2025-11-18 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2959 | LATER | SHENGDA | SAU4005-G140-EGA-&MFB-12502 | Fuel Oil System(V)-PID drawing for Fuel Oil Unlaoding Pump | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFA | IFD |  |  | 2025-11-20 |  | 2025-09-21 |  | 2025-12-10 |  | 2025-10-06 |  | 2026-01-15 |  | 2025-11-20 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2960 | LATER | SHENGDA | SAU4005-G140-EGA-&MLB-12503 | Fuel Oil System(V)-Foundation Drawing for Fuel Oil Unloading Pump Skid | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFI | IFC | [14 empty] | 2025-11-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2961 | LATER | SHENGDA | SAU4005-G140-EGA-&MDA-12504 | Fuel Oil System(V)-Datasheet for Fuel Oil Unloading Pump Skid | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFA | IFD |  |  | 2025-11-20 |  |  |  | 2025-12-10 |  |  |  | 2026-01-15 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2962 | LATER | SHENGDA | SAU4005-G140-EGA-&MDB-12505 | Fuel Oil System(V)-Sectional drawing for Basket Filter for Fuel Oil Unloading Pump Skid | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFI | IFP | [14 empty] | 2025-11-29 |  | 2025-11-12 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2963 | LATER | SHENGDA | SAU4005-G140-EGA-&MDB-12506 | Fuel Oil System(V)-Sectional drawing for Fuel Oil Unloading Pump | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFI | IFP | [14 empty] | 2025-11-29 |  | 2025-12-23 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2964 | LATER | SHENGDA | SAU4005-G140-EGA-&MDD-12507 | Fuel Oil System(V)-Performance Curve drawing for Fuel Oil Unloading Pump | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFI | IFD | [14 empty] | 2025-11-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2965 | LATER | SHENGDA | SAU4005-G140-EGA-&ELU-12508 | Fuel Oil System(V)-Outline drawing for LCP of Fuel Oil Unloading Pump Skid | G140 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fuel Oil Syestem | IFA | IFD |  |  | 2025-11-20 |  |  |  | 2025-12-10 |  |  |  | 2026-01-15 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2966 | LATER | SHENGDA | SAU4005-G140-EGA-&EMA-12509 | Fuel Oil System(V)-Electrical schematic diagram for LCP of Fuel Oil Unloading Pump Skid | G140 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fuel Oil Syestem | IFA | IFD |  |  | 2025-11-20 |  |  |  | 2025-12-10 |  |  |  | 2026-01-15 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2967 | LATER | SHENGDA | SAU4005-G140-EGA-&EDA-12510 | Fuel Oil System(V)-Motor Datasheet for Fuel Oil Unloading Pump | G140 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fuel Oil Syestem | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-09-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2968 | LATER | SHENGDA | SAU4005-G140-EGA-&ELU-12511 | Fuel Oil System(V)-Motor Outline drawing for Fuel Oil Unloading Pump | G140 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fuel Oil Syestem | IFA | IFD |  |  | 2025-11-29 |  | 2025-09-29 |  | 2025-12-19 |  | 2025-10-14 |  | 2026-01-24 |  | 2025-11-04 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2969 | LATER | SHENGDA | SAU4005-G140-EGC-&MLU-12512 | Fuel Oil System(V)-General Arrangement Drawing for Fuel Oil Transfer Pump skid | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFA | IFC |  |  | 2025-11-20 |  | 2025-09-29 |  | 2025-12-10 |  | 2025-10-09 |  | 2026-01-15 |  | 2025-11-18 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2970 | LATER | SHENGDA | SAU4005-G140-EGC-&MFB-12513 | Fuel Oil System(V)-PID drawing for Fuel Oil Transfer Pump skid | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFA | IFD |  |  | 2025-11-20 |  | 2025-10-03 |  | 2025-12-10 |  | 2025-10-06 |  | 2026-01-15 |  | 2025-11-19 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2971 | LATER | SHENGDA | SAU4005-G140-EGC-&MLB-12514 | Fuel Oil System(V)-Foundation Drawing for Fuel Oil Transfer Pump skid | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFI | IFC | [14 empty] | 2025-11-20 |  | 2025-09-27 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2972 | LATER | SHENGDA | SAU4005-G140-EGC-&MDA-12515 | Fuel Oil System(V)-Datasheet for Fuel Oil Transfer Pump Skid | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFA | IFD |  |  | 2025-11-20 |  | 2025-10-03 |  | 2025-12-10 |  | 2025-10-12 |  | 2026-01-15 |  | 2025-11-06 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2973 | LATER | SHENGDA | SAU4005-G140-EGC-&MDB-12516 | Fuel Oil System(V)-Sectional drawing for Basket Filter for Fuel Oil Transfer Pump skid | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFI | IFP | [14 empty] | 2025-11-29 |  | 2025-11-12 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2974 | LATER | SHENGDA | SAU4005-G140-EGC-&MDB-12517 | Fuel Oil System(V)-Sectional drawing for Fuel Oil Transfer Pump | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFI | IFP | [14 empty] | 2025-11-29 |  | 2025-12-23 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2975 | LATER | SHENGDA | SAU4005-G140-EGC-&MDD-12518 | Fuel Oil System(V)-Performance Curve drawing for Fuel Oil Transfer Pump | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFI | IFD | [14 empty] | 2025-11-20 |  | 2025-09-27 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2976 | LATER | SHENGDA | SAU4005-G140-EGC-&EDA-12519 | Fuel Oil System(V)-Motor Datasheet for Fuel Oil Transfer Pump | G140 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fuel Oil Syestem | IFA | IFD |  |  | 2025-11-29 |  | 2025-09-29 |  | 2025-12-19 |  | 2025-10-12 |  | 2026-01-24 |  | 2025-11-04 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2977 | LATER | SHENGDA | SAU4005-G140-EGC-&ELU-12520 | Fuel Oil System(V)-Motor Outline drawing for Fuel Oil Transfer Pump | G140 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fuel Oil Syestem | IFA | IFD |  |  | 2025-11-29 |  | 2025-09-29 |  | 2025-12-19 |  | 2025-10-16 |  | 2026-01-24 |  | 2025-11-04 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2978 | LATER | SHENGDA | SAU4005-G140-EGD-&MLU-12521 | Fuel Oil System(V)-General Arrangement Drawing for BSEDG/Fire pump Fuel Oil Forwarding Pump Skid | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFA | IFC |  |  | 2025-11-20 |  | 2025-09-26 |  | 2025-12-10 |  | 2025-10-09 |  | 2026-01-15 |  | 2025-12-09 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2979 | LATER | SHENGDA | SAU4005-G140-EGD-&MFB-12522 | Fuel Oil System(V)-PID for BSEDG/Fire pump Fuel Oil Forwarding Pump Skid | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFA | IFD |  |  | 2025-11-20 |  | 2025-09-25 |  | 2025-12-10 |  | 2025-10-06 |  | 2026-01-15 |  | 2025-11-20 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2980 | LATER | SHENGDA | SAU4005-G140-EGD-&MLB-12523 | Fuel Oil System(V)-Foundation Drawing BSEDG/Fire pump Fuel Oil Forwarding Pump Skid | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFI | IFC | [14 empty] | 2025-11-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2981 | LATER | SHENGDA | SAU4005-G140-EGD-&MDA-12524 | Fuel Oil System(V)-Datasheet for BSEDG/Fire pump Fuel Oil forwarding Pump Skid | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFA | IFD |  |  | 2025-11-20 |  | 2025-09-25 |  | 2025-12-10 |  | 0 |  | 2026-01-15 |  | 2025-10-16 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2982 | LATER | SHENGDA | SAU4005-G140-EGD-&MDB-12525 | Fuel Oil System(V)-Sectional drawing for Basket Filter for BSEDG/Fire pump Fuel Oil Forwarding Pump Skid | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFI | IFP | [14 empty] | 2025-11-29 |  | 2025-11-12 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2983 | LATER | SHENGDA | SAU4005-G140-EGD-&MDB-12526 | Fuel Oil System(V)-Sectional drawing for BSEDG/Fire pump Fuel Oil Forwarding Pump | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFI | IFP | [14 empty] | 2025-11-29 |  | 2025-11-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2984 | LATER | SHENGDA | SAU4005-G140-EGD-&MDD-12527 | Fuel Oil System(V)-Performance Curve Drawing for BSEDG/Fire pump Fuel Oil Forwarding Pump | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFI | IFD | [14 empty] | 2025-11-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2985 | LATER | SHENGDA | SAU4005-G140-EGD-&EDA-12528 | Fuel Oil System(V)-Motor Datasheet for BSEDG/Fire pump Fuel Oil Forwarding Pump | G140 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fuel Oil Syestem | IFA | IFD |  |  | 2025-11-29 |  | 2025-09-29 |  | 2025-12-19 |  | 2025-10-12 |  | 2026-01-24 |  | 2025-11-04 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2986 | LATER | SHENGDA | SAU4005-G140-EGD-&ELU-12529 | Fuel Oil System(V)-Motor Outline Drawing for BSEDG/Fire pump Fuel Oil Forwarding Pump | G140 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fuel Oil Syestem | IFA | IFD |  |  | 2025-11-29 |  | 2025-10-02 |  | 2025-12-19 |  | 2025-10-16 |  | 2026-01-24 |  | 2025-11-06 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2987 | LATER | SHENGDA | SAU4005-G140-EGA-&MFB-12530 | Fuel Oil System(V)-PID for Coalescer Filter | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFA | IFD |  |  | 2025-11-20 |  | 2025-09-22 |  | 2025-12-10 |  | 2025-10-06 |  | 2026-01-15 |  | 2025-10-22 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2988 | LATER | SHENGDA | SAU4005-G140-EGA-&MDA-12531 | Fuel Oil System(V)-Datasheet for Coalescer Filter | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFA | IFD |  |  | 2025-11-20 |  |  |  | 2025-12-10 |  |  |  | 2026-01-15 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2989 | LATER | SHENGDA | SAU4005-G140-EGA-&MLU-12532 | Fuel Oil System(V)-Outline Drawing for Coalescer Filter | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFA | IFC |  |  | 2025-11-20 |  | 2025-09-21 |  | 2025-12-10 |  | 2025-10-05 |  | 2026-01-15 |  | 2025-11-20 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2990 | LATER | SHENGDA | SAU4005-G140-EGA-&MDB-12533 | Fuel Oil System(V)-Sectional Drawing for Coalescer Filter | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFI | IFP | [14 empty] | 2025-11-29 |  | 2025-11-11 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2991 | LATER | SHENGDA | SAU4005-G140-EGA-&MLB-12534 | Fuel Oil System(V)-Foundation drawing for Coalescer Filter | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFI | IFC | [14 empty] | 2025-11-29 |  | 2025-09-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2992 | LATER | SHENGDA | SAU4005-G140-EG_-&MDB-12535 | Fuel Oil System(V)-Nameplate of pump skids | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-12-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2993 | LATER | SHENGDA | SAU4005-G140-EGA-&MDB-12536 | Fuel Oil System(V)-Nameplate of Coalescer Filter | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-11-11 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2994 | LATER | SHENGDA | SAU4005-G140-EG_-&MPC-12537 | Fuel Oil System(V)-Fuel Oil System Utility list | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-11-11 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2995 | LATER | SHENGDA | SAU4005-G140-EG_-&EFP-12538 | Fuel Oil System(V)-IO List for Fuel Oil System | G140 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Fuel Oil Syestem | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-10-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2996 | LATER | SHENGDA | SAU4005-G140-EG_-&EMB-12539 | Fuel Oil System(V)-Fuel oil unloading skid Cable list | G140 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fuel Oil Syestem | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-11-08 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2997 | LATER | SHENGDA | SAU4005-G140-EG_-&EEC-12540 | Fuel Oil System(V)-Fuel Oil System Electrical Load List | G140 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Fuel Oil Syestem | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-10-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2998 | LATER | SHENGDA | SAU4005-G140-EG_-&MEC-12541 | Fuel Oil System(V)-Instrument List and datasheet for Fuel Oil System | G140 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Fuel Oil Syestem | IFI | IFD | [14 empty] | 2025-12-15 |  | 2025-10-31 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 2999 | LATER | SHENGDA | SAU4005-G140-EG_-&EDA-12542 | Fuel Oil System(V)-I &C Cable Datasheet | G140 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Fuel Oil Syestem | IFI | IFD | [14 empty] | 2025-12-15 |  | 2025-12-27 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3001 | LATER | SHENGDA | SAU4005-G140-EG_-&EMB-12544 | Fuel Oil System(V)-I&C Cable Interconnection Drawing | G140 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Fuel Oil Syestem | IFI | IFD | [14 empty] | 2025-12-15 |  | 2025-12-27 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| dcc changed | 3002 | LATER | SHENGDA | SAU4005-G140-EG_-&EMA-12545 | Fuel Oil System(V)-Instrument Installation Hook-up Drawing | G140 | Engineering | C-Construction engineering (building construction and civil engineering) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Fuel Oil Syestem | IFI | IFD | [14 empty] | 2025-12-15 |  | 2026-02-09 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3003 | LATER | SHENGDA | SAU4005-G140-EG_-&MDB-12546 | Fuel Oil System(V)-Fuel oil Paint plan | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-11-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3004 | LATER | SHENGDA | SAU4005-G140-EG_-&MPD-12547 | Fuel Oil System(V)-Fuel oil Valve List | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-11-11 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3005 | LATER | SHENGDA | SAU4005-G140-EG_-&MTB-12548 | Fuel Oil System(V)-Fuel oil 3D model | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFI | IFD | [14 empty] | 2026-02-09 |  | 2025-12-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3006 | LATER | SHENGDA | SAU4005-G140-EG_-&MQA-12549 | Fuel Oil System(V)-Inspection and Test Plan | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFA | IFD |  |  | 2025-11-20 | [33 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3007 | LATER | SHENGDA | SAU4005-G140-EG_-&MQA-12550 | Fuel Oil System(V)-Hydrostatic Test Procedure | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFI | IFD | [14 empty] | 2025-11-29 |  | 2025-10-31 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3009 | LATER | SHENGDA | SAU4005-G140-EG_-&MDC-12552 | Fuel Oil System(V)-Instruction manual (including product catalog,installation,operation, Maintenacne etc.) | G140 | Operation & Maintenacne | B-Overall technology | YES | O&M | Mechanical | SEPCOIII | Fuel Oil Syestem | IFI | IFC | [14 empty] | 2026-02-09 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3010 | LATER | SHENGDA | SAU4005-G140-EG_-&MAC-12553 | Fuel Oil System(V)-End Of Manufacturing Report | G140 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Syestem | IFI | IFD | [14 empty] | 2025-11-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3011 | LATER | BAOBIAN | SAU4005-G150-BAT-&EDA-20001 | GSUT(V)-Technical Data Sheet (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFA | IFD |  |  | 2025-09-04 |  | 2025-09-16 |  | 2025-09-24 |  | 2025-11-09 |  | 2025-10-30 |  | 2026-03-15 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3012 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20002 | GSUT(V)-Outline drawing (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFA | IFD |  |  | 2025-09-14 |  | 2025-09-24 |  | 2025-10-04 |  | 2025-11-09 |  | 2025-11-09 |  | 2026-02-01 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3013 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20003 | GSUT(V)-HV Bushing (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [6 empty] | 2025-08-29 |  |  |  | 2025-10-04 |  |  |  | 2025-08-09 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3014 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20004 | GSUT(V)-LV Bushing (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [6 empty] | 2025-08-29 |  |  |  | 2025-10-04 |  |  |  | 2025-08-09 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3015 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20005 | GSUT(V)-HV Neutral Bushing (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [6 empty] | 2025-08-29 |  |  |  | 2025-10-04 |  |  |  | 2025-08-09 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3016 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20006 | GSUT(V)-OIL PUMP drawing (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [6 empty] | 2025-09-19 |  |  |  | 2025-10-25 |  |  |  | 2025-08-30 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3017 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20007 | GSUT(V)-Gas relay drawing (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [6 empty] | 2025-08-29 |  |  |  | 2025-10-04 |  |  |  | 2025-08-09 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3018 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20008 | GSUT(V)-Foundation drawing (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [6 empty] | 2025-09-19 |  |  |  | 2025-10-25 |  |  |  | 2025-08-30 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3019 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20010 | GSUT(V)-Nameplate drawing (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFA | IFD |  |  | 2025-09-14 |  | 2025-09-16 |  | 2025-09-19 |  | 2025-11-09 |  | 2025-10-25 |  | 2026-01-19 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3020 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20012 | GSUT(V)-Transportation drawing (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [6 empty] | 2025-10-04 |  |  |  | 2025-11-09 |  |  |  | 2025-09-14 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3021 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20013 | GSUT(V)-Neutral/resistance cabinet drawing (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [6 empty] | 2025-10-09 |  |  |  | 2025-11-14 |  |  |  | 2025-09-14 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3022 | LATER | BAOBIAN | SAU4005-G150-BAT-&EDA-20014 | GSUT(V)-Technical Data (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFA | IFD |  |  | 2025-09-19 |  | 2025-09-16 |  | 2025-10-04 |  | 2025-11-09 |  | 2025-11-09 |  | 2026-03-15 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3023 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20015 | GSUT(V)-Outline drawing (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFA | IFD |  |  | 2025-09-30 |  | 2025-09-24 |  | 2025-10-04 |  | 2025-10-12 |  | 2025-11-09 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3024 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20016 | GSUT(V)-HV Bushing (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD |  |  | 2025-08-09 |  |  |  | 2025-10-09 |  |  |  | 2025-11-14 | [5 empty] | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3025 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20017 | GSUT(V)-LV Bushing (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD |  |  | 2025-08-09 |  |  |  | 2025-10-20 |  |  |  | 2025-11-25 | [5 empty] | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3026 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20018 | GSUT(V)-HV Neutral Bushing (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD |  |  | 2025-08-09 |  |  |  | 2025-08-29 |  |  |  | 2025-10-04 | [5 empty] | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3027 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20019 | GSUT(V)-OIL PUMP drawing (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD |  |  | 2025-08-30 |  |  |  | 2025-08-29 |  |  |  | 2025-10-04 | [5 empty] | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3028 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20020 | GSUT(V)-Gas relay drawing (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD |  |  | 2025-08-09 |  |  |  | 2025-08-29 |  |  |  | 2025-10-04 | [5 empty] | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3029 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20021 | GSUT(V)-Foundation drawing (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFA | IFD |  |  | 2025-09-14 |  | 2025-10-25 |  | 2025-09-19 |  | 2025-11-09 |  | 2025-10-25 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3030 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20023 | GSUT(V)-Nameplate drawing (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFA | IFD |  |  | 2025-09-30 |  | 2025-09-16 |  | 2025-08-29 |  | 2025-11-12 |  | 2025-10-04 |  | 2026-02-05 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3031 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20025 | GSUT(V)-Transportation drawing (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [6 empty] | 2025-10-04 |  |  |  | 2025-11-09 |  |  |  | 2025-10-05 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3032 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20026 | GSUT(V)-Neutral/resistance cabinet drawing (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [6 empty] | 2025-10-04 |  |  |  | 2025-11-09 |  |  |  | 2025-09-30 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3033 | LATER | BAOBIAN | SAU4005-G150-BAT-&EDA-20027 | GSUT(V)-CURRENT TRANSFORMERS CURVES & DATA SHEET (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [6 empty] | 2025-10-20 |  |  |  | 2025-11-25 |  |  |  | 2025-10-20 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3034 | LATER | BAOBIAN | SAU4005-G150-BAT-&EDA-20028 | GSUT(V)-DIGITAL IMPACT RECORDER DATA SHEET AND CATALOGUES (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [6 empty] | 2025-10-25 |  |  |  | 2025-11-30 |  |  |  | 2025-09-19 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3036 | LATER | BAOBIAN | SAU4005-G150-BAT-&EDA-20030 | GSUT(V)-Transformer BILL OF MATERIALS (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [6 empty] | 2025-10-20 |  |  |  | 2025-11-25 |  |  |  | 2025-09-19 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3037 | LATER | BAOBIAN | SAU4005-G150-BAT-&EDF-20031 | GSUT(V)-RANSFORMER CURVES (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [6 empty] | 2025-09-29 |  |  |  | 2025-11-04 |  |  |  | 2025-09-19 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
|  | 3038 | LATER | BAOBIAN | SAU4005-G150-BAT-&EEC-20032 | GSUT(V)-CORROSIVE PROTECTION SPECIFICATION (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [6 empty] | 2025-10-09 | [7 empty] | 2025-09-14 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3039 | LATER | BAOBIAN | SAU4005-G150-BAT-&EED-20033 | GSUT(V)-SHORT CIRCUIT CALCULATION (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFA | IFD |  |  | 2025-09-14 |  | 2025-09-16 |  | 2025-10-09 |  | 2025-10-12 |  |  |  | 2026-01-19 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3041 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20035 | GSUT(V)-DGA CATALOGUE, DESCRIPTIONS, CONNECTIONS (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [6 empty] | 2025-12-13 |  |  |  | 2026-01-18 |  |  |  | 2025-09-14 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3042 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20036 | GSUT(V)-CONSERVATOR DIMENSIONS AND DETAILS (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [6 empty] | 2025-11-03 | [7 empty] | 2025-09-24 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3044 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20038 | GSUT(V)-OLTC AND MOTOR DRIVE DATA AND SCHEMATICS (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [6 empty] | 2025-11-03 | [7 empty] | 2025-09-09 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3045 | LATER | BAOBIAN | SAU4005-G150-BAT-&EMA-20039 | GSUT(V)-HOT SPOT WINDING TEMPERATURE GRADIENT SETTINGS (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [14 empty] | 2025-09-19 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3046 | LATER | BAOBIAN | SAU4005-G150-BAT-&EPC-20040 | GSUT(V)-AC/DC POWER CONSUMPTION LOAD LIST (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [14 empty] | 2025-09-24 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3047 | LATER | BAOBIAN | SAU4005-G150-BAT-&EPC-20041 | GSUT(V)-SPECIAL TOOLS AND RECOMMENDED SPARE PARTS (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFA | IFD |  |  | 2025-09-14 |  | 2025-10-25 |  |  |  | 2025-11-09 |  |  |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3048 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20042 | GSUT(V)-General Arrangement drawings of marshalling box, cooler control cabinet, and remote tap changer control panel (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [14 empty] | 2025-09-19 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3049 | LATER | BAOBIAN | SAU4005-G150-BAT-&EMA-20043 | GSUT(V)-Schematic diagram showing internal wiring within marshalling box along with terminal details for external cable connections (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [14 empty] | 2025-09-19 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3050 | LATER | BAOBIAN | SAU4005-G150-BAT-&EMA-20044 | GSUT(V)-Schematic diagram showing internal wiring within cooler control cabinet along with terminal details for external cable connections (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [14 empty] | 2025-09-19 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3051 | LATER | BAOBIAN | SAU4005-G150-BAT-&EMA-20045 | GSUT(V)-Cable interconnection list for cables between two Vendor supplied equipment (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [14 empty] | 2025-09-24 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3052 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20046 | GSUT(V)-Catalogues of all bought out items (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [14 empty] | 2025-10-09 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3053 | LATER | BAOBIAN | SAU4005-G150-BAT-&EBD-20047 | GSUT(V)-Manufacturing & Inspection Schedule (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [14 empty] | 2025-11-23 |  | 2025-12-15 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| dcc changed | 3054 | LATER | BAOBIAN | SAU4005-G150-BAT-&EQA-20048 | GSUT(V)-Quality Assurance Plan (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [14 empty] | 2025-09-24 |  | 2026-01-10 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3055 | LATER | BAOBIAN | SAU4005-G150-BAT-&EDC-20049 | GSUT(V)-Erection and Commissioning Manual (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [14 empty] | 2026-01-19 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3056 | LATER | BAOBIAN | SAU4005-G150-BAT-&EQC-20050 | GSUT(V)-Performance Test Procedure (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [14 empty] | 2026-01-19 |  | 2026-01-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3057 | LATER | BAOBIAN | SAU4005-G150-BAT-&EQC-20051 | GSUT(V)-Type test report (GT) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFA | IFD |  |  | 2025-04-19 |  | 2025-12-27 |  |  |  | 2025-11-09 |  |  |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3058 | LATER | BAOBIAN | SAU4005-G150-BAT-&EDA-20052 | GSUT(V)-CURRENT TRANSFORMERS CURVES & DATA SHEET (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [14 empty] | 2025-12-24 |  | 2025-11-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3059 | LATER | BAOBIAN | SAU4005-G150-BAT-&EDA-20053 | GSUT(V)-DIGITAL IMPACT RECORDER DATA SHEET AND CATALOGUES (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [14 empty] | 2025-09-19 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3061 | LATER | BAOBIAN | SAU4005-G150-BAT-&EDA-20055 | GSUT(V)-Transformer BILL OF MATERIALS (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [14 empty] | 2025-10-19 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3062 | LATER | BAOBIAN | SAU4005-G150-BAT-&EDF-20056 | GSUT(V)-TRANSFORMER CURVES (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [14 empty] | 2025-10-19 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3063 | LATER | BAOBIAN | SAU4005-G150-BAT-&EEC-20057 | GSUT(V)-CORROSIVE PROTECTION SPECIFICATION (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [14 empty] | 2025-11-23 |  | 2025-11-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3064 | LATER | BAOBIAN | SAU4005-G150-BAT-&EED-20058 | GSUT(V)-SHORT CIRCUIT CALCULATION (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFA | IFD |  |  | 2025-11-23 |  | 2025-09-16 |  |  |  | 2025-10-12 |  |  |  | 2026-01-19 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3066 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20060 | GSUT(V)-DGA CATALOGUE, DESCRIPTIONS, CONNECTIONS (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [14 empty] | 2025-09-14 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3067 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20061 | GSUT(V)-CONSERVATOR DIMENSIONS AND DETAILS (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [14 empty] | 2025-10-24 |  | 2025-11-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3069 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20063 | GSUT(V)-OLTC AND MOTOR DRIVE DATA AND SCHEMATICS (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [14 empty] | 2025-10-09 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3070 | LATER | BAOBIAN | SAU4005-G150-BAT-&EMA-20064 | GSUT(V)-HOT SPOT WINDING TEMPERATURE GRADIENT SETTINGS (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [14 empty] | 2025-10-14 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3071 | LATER | BAOBIAN | SAU4005-G150-BAT-&EPC-20065 | GSUT(V)-AC/DC POWER CONSUMPTION LOAD LIST (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [14 empty] | 2025-10-24 |  | 2025-09-17 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3072 | LATER | BAOBIAN | SAU4005-G150-BAT-&EPC-20066 | GSUT(V)-SPECIAL TOOLS AND RECOMMENDED SPARE PARTS (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFA | IFD |  |  | 2025-09-14 |  | 2025-10-25 |  |  |  | 2025-11-09 |  |  |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3073 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20067 | GSUT(V)-General Arrangement drawings of marshalling box, cooler control cabinet, and remote tap changer control panel (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [14 empty] | 2025-10-14 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3074 | LATER | BAOBIAN | SAU4005-G150-BAT-&EMA-20068 | GSUT(V)-Schematic diagram showing internal wiring within marshalling box along with terminal details for external cable connections (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [14 empty] | 2025-10-14 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3075 | LATER | BAOBIAN | SAU4005-G150-BAT-&EMA-20069 | GSUT(V)-Schematic diagram showing internal wiring within cooler control cabinet along with terminal details for external cable connections (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [14 empty] | 2025-10-14 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3077 | LATER | BAOBIAN | SAU4005-G150-BAT-&ELU-20071 | GSUT(V)-Catalogues of all bought out items (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [14 empty] | 2025-10-24 |  | 2025-12-20 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3078 | LATER | BAOBIAN | SAU4005-G150-BAT-&EBD-20072 | GSUT(V)-Manufacturing & Inspection Schedule (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [14 empty] | 2025-11-13 |  | 2025-12-09 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| dcc changed | 3079 | LATER | BAOBIAN | SAU4005-G150-BAT-&EQA-20073 | GSUT(V)-Quality Assurance Plan (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [14 empty] | 2025-10-24 |  | 2026-01-10 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3080 | LATER | BAOBIAN | SAU4005-G150-BAT-&EDC-20074 | GSUT(V)-Erection and Commissioning Manual (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [14 empty] | 2026-01-29 |  | 2025-12-01 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3081 | LATER | BAOBIAN | SAU4005-G150-BAT-&EQC-20075 | GSUT(V)-Performance Test Procedure (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFI | IFD | [14 empty] | 2026-01-29 |  | 2026-01-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3082 | LATER | BAOBIAN | SAU4005-G150-BAT-&EQC-20076 | GSUT(V)-Type test report (ST) | G150 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | GSUT | IFA | IFD |  |  | 2025-05-20 | [33 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3083 | LATER | Tbea Shenyang | SAU4005-G151-BBT-&EDA-20200 | UAT (V)- Data Sheet | G151 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UAT | IFA | IFD |  |  | 2025-09-25 |  | 2025-09-24 |  | 2025-10-15 |  | 2025-11-20 |  | 2025-11-20 |  | 2026-01-19 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES | NO
|  | 3084 | LATER | Tbea Shenyang | SAU4005-G151-BBT-&EED-20201 | UAT (V)-Short Circuit Calculation | G151 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UAT | IFI | IFD | [14 empty] | 2025-09-25 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES | NO
|  | 3085 | LATER | Tbea Shenyang | SAU4005-G151-BBT-&EDF-20202 | UAT (V)-Transformer Curves | G151 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UAT | IFI | IFD | [14 empty] | 2025-09-25 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES | NO
|  | 3086 | LATER | Tbea Shenyang | SAU4005-G151-BBT-&EDA-20203 | UAT (V)-NGR Drawing and Datasheet | G151 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UAT | IFI | IFD | [14 empty] | 2025-09-25 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES | NO
|  | 3087 | LATER | Tbea Shenyang | SAU4005-G151-BBT-&EQC-20204 | UAT (V)-OLTC Selection and Type Test Report | G151 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UAT | IFI | IFD | [14 empty] | 2025-09-25 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES | NO
|  | 3088 | LATER | Tbea Shenyang | SAU4005-G151-BBT-&ELU-20205 | UAT (V)-Outline Drawing | G151 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UAT | IFI | IFD | [14 empty] | 2025-09-25 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES | NO
|  | 3089 | LATER | Tbea Shenyang | SAU4005-G151-BBT-&ELU-20206 | UAT (V)-Foundation Drawing | G151 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UAT | IFI | IFD | [14 empty] | 2025-09-25 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES | NO
|  | 3090 | LATER | Tbea Shenyang | SAU4005-G151-BBT-&ELU-20207 | UAT (V)-Bushing Drawing | G151 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UAT | IFI | IFD | [14 empty] | 2025-09-25 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES | NO
|  | 3091 | LATER | Tbea Shenyang | SAU4005-G151-BBT-&EFP-20208 | UAT (V)-I/O Signal Exchange List | G151 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UAT | IFI | IFD | [14 empty] | 2025-09-25 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES | NO
|  | 3092 | LATER | Tbea Shenyang | SAU4005-G151-BBT-&EFF-20209 | UAT (V)-OLTC Drawing and Schematic | G151 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UAT | IFI | IFD | [14 empty] | 2025-09-25 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES | NO
|  | 3093 | LATER | Tbea Shenyang | SAU4005-G151-BBT-&ELU-20210 | UAT (V)-Rating Plate | G151 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UAT | IFA | IFD |  |  | 2025-09-25 |  | 2025-10-25 |  | 2025-10-15 |  | 2025-11-30 |  | 2025-11-20 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES | NO
|  | 3094 | LATER | Tbea Shenyang | SAU4005-G151-BBT-&ELU-20211 | UAT (V)-Valve Plate | G151 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UAT | IFI | IFD | [14 empty] | 2025-09-25 |  | 2025-09-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES | NO
|  | 3095 | LATER | Tbea Shenyang | SAU4005-G151-BBT-&ELU-20212 | UAT (V)-Main Accessories & Valves Marking Plates | G151 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UAT | IFI | IFD | [14 empty] | 2025-09-25 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES | NO
|  | 3096 | LATER | Tbea Shenyang | SAU4005-G151-BBT-&EDC-20213 | UAT (V)-Operation and Maintenance Manual | G151 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UAT | IFI | IFD | [14 empty] | 2025-09-25 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES | NO
|  | 3097 | LATER | Tbea Shenyang | SAU4005-G151-BBT-&EQC-20214 | UAT (V)-Inspection Test Plan | G151 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UAT | IFA | IFD |  |  | 2025-10-25 |  |  |  | 2025-11-14 |  |  |  | 2025-12-20 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES | NO
|  | 3098 | LATER | Tbea Shenyang | SAU4005-G151-BBT-&EQC-20215 | UAT (V)-Factory Acceptance Test Procedure | G151 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UAT | IFI | IFD | [14 empty] | 2025-10-25 |  | 2025-10-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES | NO
|  | 3099 | LATER | Tbea Shenyang | SAU4005-G151-BBT-&EDC-20216 | UAT (V)-Coating System Procedure | G151 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UAT | IFI | IFD | [14 empty] | 2025-09-25 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES | NO
|  | 3100 | LATER | Tbea Shenyang | SAU4005-G151-BBT-&EFF-20217 | UAT (V)-Control And Auxiliary Wiring and Schematic | G151 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UAT | IFI | IFD | [14 empty] | 2025-09-25 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES | NO
|  | 3101 | LATER | Tbea Shenyang | SAU4005-G151-BBT-&EPC-20218 | UAT (V)-AC/DC Power Consumption Load List | G151 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UAT | IFI | IFD | [14 empty] | 2025-09-25 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES | NO
|  | 3102 | LATER | Tbea Shenyang | SAU4005-G151-BBT-&EDA-20219 | UAT (V)-Bushing CT Excitation Curves & Data Sheet | G151 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UAT | IFI | IFD | [14 empty] | 2025-09-25 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES | NO
|  | 3103 | LATER | Tbea Shenyang | SAU4005-G151-BBT-&ELU-20220 | UAT (V)-Transport Dimensions | G151 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UAT | IFI | IFD | [14 empty] | 2025-09-25 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES | NO
|  | 3104 | LATER | Tbea Shenyang | SAU4005-G151-BBT-&EPB-20221 | UAT (V)-Spare Parts | G151 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UAT | IFI | IFD | [14 empty] | 2025-09-29 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES | NO
| dcc changed | 3105 | LATER | Tbea Shenyang | SAU4005-G151-BBT-&EED-20222 | UAT (V)-Seismic Calculation | G151 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UAT | IFI | IFD | [14 empty] | 2025-09-29 |  | 2026-01-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES | NO
|  | 3106 | LATER | Tbea Shenyang | SAU4005-G151-BBT-&EFF-20223 | UAT (V)-RTCC Cabinet Drawings | G151 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UAT | IFI | IFD | [14 empty] | 2025-10-01 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES | NO
|  | 3107 | LATER | Tbea Shenyang | SAU4005-G151-BBT-&ETB-20224 | UAT (V)-3D Model | G151 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UAT | IFI | IFD | [14 empty] | 2025-09-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES | NO
|  | 3108 | LATER | Tbea Shenyang | SAU4005-G151-BBT-&EFF-20225 | UAT (V)-Online Transformer condition monitoring & DGA documents. | G151 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UAT | IFI | IFD | [14 empty] | 2025-09-25 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES | NO
|  | 3109 | LATER | JST | SAU4005-G152-BFT-&EDA-20300 | LV Dry Type Transformer Technical Data Sheet | G152 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | LV Transformer | IFA | IFD |  |  | 2025-09-16 |  | 2025-10-25 |  | 2025-10-06 |  | 2026-01-27 |  | 2025-11-11 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3110 | LATER | JST | SAU4005-G152-BFT-&ELU-20301 | LV Dry Type Transformer Outline Drawing | G152 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | LV Transformer | IFI | IFD | [14 empty] | 2025-09-19 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3111 | LATER | JST | SAU4005-G152-BFT-&EDB-20302 | LV Dry Type Transformer Nameplates | G152 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | LV Transformer | IFA | IFD |  |  | 2025-09-19 |  | 2025-10-25 |  | 2025-10-09 |  | 2026-01-27 |  | 2025-11-14 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3112 | LATER | JST | SAU4005-G152-BFT-&ELU-20303 | LV Dry Type Transformer Foundation Drawing | G152 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | LV Transformer | IFI | IFD | [14 empty] | 2025-09-16 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3113 | LATER | JST | SAU4005-G152-BFT-&EPC-20304 | LV Dry Type Transformer AC/DC Power Consumption Load List | G152 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | LV Transformer | IFI | IFD | [14 empty] | 2025-09-21 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3114 | LATER | JST | SAU4005-G152-BFT-&EFF-20305 | LV Dry Type Transformer Control and Auxiliary Wiring, and Schematic | G152 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | LV Transformer | IFI | IFD | [14 empty] | 2025-09-27 |  | 2025-11-08 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3115 | LATER | JST | SAU4005-G152-BFT-&ELU-20306 | LV Dry Type Transformer Inspection & Test Plan (ITP) | G152 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | LV Transformer | IFA | IFD |  |  | 2025-10-26 |  | 2025-10-16 |  | 2025-11-15 |  | 2026-01-18 |  | 2025-12-21 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3116 | LATER | JST | SAU4005-G152-BFT-&EQC-20307 | LV Dry Type Transformer Factory Test Procedure | G152 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | LV Transformer | IFI | IFD | [14 empty] | 2025-10-26 |  | 2025-10-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| dcc changed | 3117 | LATER | JST | SAU4005-G152-BFT-&EPB-20308 | LV Dry Type Transformer Spare Parts | G152 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | LV Transformer | IFA | IFD |  |  | 2025-09-29 |  |  |  | 2025-10-19 |  |  |  | 2025-11-24 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3118 | LATER | JST | SAU4005-G152-BFT-&ELU-20309 | LV Dry Type Transformer Neutral Point CT Excitation Curves | G152 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | LV Transformer | IFI | IFD | [14 empty] | 2025-10-26 |  | 2026-02-13 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| dcc changed | 3119 | LATER | JST | SAU4005-G152-BFT-&EED-20310 | LV Dry Type Transformer(V)-Calculation of the thermal ability to withstand short-circuit | G152 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | LV Transformer | IFI | IFD | [14 empty] | 2025-10-26 |  | 2026-02-28 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3120 | LATER | JST | SAU4005-G152-BFT-&ELU-20311 | LV Dry Type Transformer(V)-List with ratings/ranges & makes of all bought out items | G152 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | LV Transformer | IFI | IFD | [14 empty] | 2025-10-26 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3121 | LATER | JST | SAU4005-G152-BFT-&ELU-20312 | LV Dry Type Transformer(V)-O&M Manuals, start/up commissioning manuals and Field Installation/Erection Instructions/Procedure | G152 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | LV Transformer | IFI | IFD | [14 empty] | 2025-10-26 |  | 2026-03-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3122 | LATER | HITACHI | SAU4005-G153-BAC-&ELU-20400 | GCB (V)-Outline Drawing (GT) | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFA | IFP |  |  | 2025-08-29 |  | 2025-10-25 |  | 2025-09-18 |  | 0 |  | 2025-10-24 |  | 2025-12-23 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3123 | LATER | HITACHI | SAU4005-G153-BAC-&ELU-20401 | GCB (V)-Outline Drawing (ST) | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFA | IFP |  |  | 2025-08-29 |  | 2025-10-25 |  | 2025-09-18 |  | 0 |  | 2025-10-24 |  | 2025-11-24 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3124 | LATER | HITACHI | SAU4005-G153-BAC-&ELU-20402 | GCB (V)-Scale of Pressure (GT) | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFI | IFP | [14 empty] | 2026-01-29 |  | 2025-12-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3125 | LATER | HITACHI | SAU4005-G153-BAC-&ELU-20403 | GCB (V)-Scale of Pressure (ST) | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFI | IFP | [14 empty] | 2026-01-29 |  | 2025-11-13 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3126 | LATER | HITACHI | SAU4005-G153-BAC-&EPC-20404 | GCB (V)-Special tools | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFI | IFP | [14 empty] | 2025-09-29 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3127 | LATER | HITACHI | SAU4005-G153-BAC-&EQC-20405 | GCB (V)-Factory Acceptance Test Procedures (GT) | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFI | IFP | [14 empty] | 2026-01-29 |  | 2025-10-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3128 | LATER | HITACHI | SAU4005-G153-BAC-&EQC-20406 | GCB (V)-Factory Acceptance Test Procedures (ST) | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFI | IFP | [14 empty] | 2026-01-29 |  | 2025-11-08 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3129 | LATER | HITACHI | SAU4005-G153-BAC-&EQC-20407 | GCB (V)-Factory Acceptance Test Results Report (GT) | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFI | IFP | [14 empty] | 2026-06-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3130 | LATER | HITACHI | SAU4005-G153-BAC-&EQC-20408 | GCB (V)-Factory Acceptance Test Results Report (ST) | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFI | IFP | [14 empty] | 2026-07-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3131 | LATER | HITACHI | SAU4005-G153-BAC-&EDC-20409 | GCB (V)-Cleaning and Painting Procedure | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFI | IFP | [14 empty] | 2025-11-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3132 | LATER | HITACHI | SAU4005-G153-BAC-&EDB-20410 | GCB (V)-Nameplate Drawing (GT) | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFI | IFP | [14 empty] | 2026-06-29 |  | 2025-09-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3133 | LATER | HITACHI | SAU4005-G153-BAC-&EDB-20411 | GCB (V)-Nameplate Drawing (ST) | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFI | IFP | [14 empty] | 2026-07-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3134 | LATER | HITACHI | SAU4005-G153-BAC-&EDC-20412 | GCB (V)-Operation and Maintenance Manual (GT) | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFI | IFP | [14 empty] | 2025-09-29 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3135 | LATER | HITACHI | SAU4005-G153-BAC-&EDC-20413 | GCB (V)-Operation and Maintenance Manual (ST) | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFI | IFP | [14 empty] | 2025-09-29 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3136 | LATER | HITACHI | SAU4005-G153-BAC-&EQC-20414 | GCB (V)-Inspection Test Plan | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFA | IFP |  |  | 2026-01-29 |  |  |  | 2026-02-18 |  |  |  | 2026-03-26 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3137 | LATER | HITACHI | SAU4005-G153-BAC-&EDA-20415 | GCB (V)-Technical Data Sheet | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFI | IFP | [14 empty] | 2025-10-30 |  | 2025-09-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3138 | LATER | HITACHI | SAU4005-G153-BAC-&EPC-20416 | GCB (V)-AC/DC Power Consumption Load List | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFI | IFP | [14 empty] | 2025-08-29 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3139 | LATER | HITACHI | SAU4005-G153-BAC-&EED-20417 | GCB (V)-Heat Dissipation | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFI | IFP | [14 empty] | 2026-01-29 |  | 2025-11-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3140 | LATER | HITACHI | SAU4005-G153-BAC-&EDF-20418 | GCB (V)-Capability Curve | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFI | IFP | [14 empty] | 2026-01-29 |  | 2025-12-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| dcc changed | 3141 | LATER | HITACHI | SAU4005-G153-BAC-&EQA-20419 | GCB (V)-Site Test Procedures | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFI | IFP | [14 empty] | 2025-09-29 |  | 2026-01-12 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3142 | LATER | HITACHI | SAU4005-G153-BAC-&EMA-20420 | GCB (V)-Schematic and wiring Diagram (GT) | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFA | IFP |  |  | 2025-08-29 |  | 2025-09-29 |  | 2025-09-18 |  | 2025-10-22 |  | 2025-10-24 |  | 2026-04-28 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3143 | LATER | HITACHI | SAU4005-G153-BAC-&EMA-20421 | GCB (V)-Schematic and wiring Diagram (ST) | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFA | IFP |  |  | 2025-08-29 |  | 2025-09-29 |  | 2025-09-18 |  | 2025-10-22 |  | 2025-10-24 |  | 2026-04-28 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| dcc changed | 3144 | LATER | HITACHI | SAU4005-G153-BAC-&EBF-20422 | GCB (V)-Packing Procedures | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFI | IFP | [14 empty] | 2025-09-29 |  | 2026-01-12 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3145 | LATER | HITACHI | SAU4005-G153-BAC-&ETB-20423 | GCB (V)-3D Modelling (GT) | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFA | IFP |  |  | 2025-09-29 |  | 2025-10-25 |  | 2025-10-19 |  | 0 |  | 2025-11-24 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3146 | LATER | HITACHI | SAU4005-G153-BAC-&ETB-20424 | GCB (V)-3D Modelling (ST) | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFA | IFP |  |  | 2025-09-29 |  | 2025-10-25 |  | 2025-10-19 |  | 0 |  | 2025-11-24 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3147 | LATER | HITACHI | SAU4005-G153-BAC-&EQC-20425 | GCB (V)-Type Tests Reports (GT) | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFI | IFP | [14 empty] | 2026-06-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3148 | LATER | HITACHI | SAU4005-G153-BAC-&EQC-20426 | GCB (V)-Type Tests Reports (ST) | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFI | IFP | [14 empty] | 2026-07-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3149 | LATER | HITACHI | SAU4005-G153-BAC-&EEB-20427 | GCB (V)-Calculation as per IEC/IEEE 62271-37-013 (GT) | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFI | IFP | [14 empty] | 2025-11-29 |  | 2025-09-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3150 | LATER | HITACHI | SAU4005-G153-BAC-&EEB-20428 | GCB (V)-Calculation as per IEC/IEEE 62271-37-013 (ST) | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFI | IFP | [14 empty] | 2025-11-29 |  | 2025-09-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| dcc changed | 3151 | LATER | HITACHI | SAU4005-G153-BAC-&EED-20429 | GCB (V)-Sizing calculation of SA Arrestor (GT) | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFI | IFP | [14 empty] | 2025-11-29 |  | 2026-01-12 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| dcc changed | 3152 | LATER | HITACHI | SAU4005-G153-BAC-&EED-20430 | GCB (V)-Sizing calculation of SA Arrestor (ST) | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFI | IFP | [14 empty] | 2025-11-29 |  | 2026-01-12 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3153 | LATER | HITACHI | SAU4005-G153-BAC-&EQA-20431 | GCB (V)-Quality Assurance Plan | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFA | IFP |  |  | 2026-01-29 |  | 2025-11-13 |  | 2026-02-18 |  | 2025-10-22 |  | 2026-03-26 |  | 2026-02-24 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3154 | LATER | HITACHI | SAU4005-G153-BAC-&EDC-20432 | GCB (V)-Erection and Commissioning Manual(GT) | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFI | IFP | [14 empty] | 2025-09-29 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3155 | LATER | HITACHI | SAU4005-G153-BAC-&EDC-20433 | GCB (V)-Erection and Commissioning Manual (ST) | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFI | IFP | [14 empty] | 2025-09-29 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3156 | LATER | HITACHI | SAU4005-G153-BAC-&EEC-20434 | GCB (V)-TRV Study and calculation (GT) | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFI | IFP | [14 empty] | 2026-01-29 |  | 2025-12-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3157 | LATER | HITACHI | SAU4005-G153-BAC-&EEC-20435 | GCB (V)-TRV Study and calculation (ST) | G153 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Generator Circuit Breaker | IFI | IFP | [14 empty] | 2026-01-29 |  | 2025-12-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
|  | 3158 | LATER | ARFA | SAU4005-G154-BAA-&EDA-20500 | IPBD (V)-TECHNICAL DATASHEET (GT&ST) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-09-19 |  | 2025-10-25 |  |  |  | 2025-12-03 |  |  |  | 2026-02-01 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3159 | LATER | ARFA | SAU4005-G154-BAA-&EDA-20501 | IPBD (V)-SUPPORTS LOCATIONS AND LOADING DATA (GT) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-10-20 |  | 2025-10-25 |  | 2025-11-09 |  | 2026-01-08 |  | 2025-12-15 |  | 2026-05-06 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3160 | LATER | ARFA | SAU4005-G154-BAA-&EDA-20502 | IPBD (V)-SUPPORTS LOCATIONS AND LOADING DATA (ST) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-10-20 |  | 2025-10-25 |  | 2025-11-09 |  | 2026-01-08 |  | 2025-12-15 |  | 2026-05-06 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3161 | LATER | ARFA | SAU4005-G154-BAA-&EDD-20503 | IPBD (V)-OVER TEMPERATURE AND LOSSES MECHANICAL CALCULATION REPORT (GT) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-09-19 |  | 2025-10-25 |  |  |  | 2025-12-14 |  |  |  | 2025-12-28 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3162 | LATER | ARFA | SAU4005-G154-BAA-&EDD-20504 | IPBD (V)-OVER TEMPERATURE AND LOSSES MECHANICAL CALCULATION REPORT (ST) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-09-19 |  | 2025-10-25 |  |  |  | 2025-12-14 |  |  |  | 2025-12-28 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3163 | LATER | ARFA | SAU4005-G154-BAA-&ELU-20505 | IPBD (V)-OUTLINE DRAWING (GT) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-09-04 |  | 2025-10-25 |  | 2025-09-24 |  | 2025-12-03 |  | 2025-10-30 |  | 2026-01-21 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3164 | LATER | ARFA | SAU4005-G154-BAA-&ELU-20506 | IPBD (V)-OUTLINE DRAWING (ST) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-09-04 |  | 2025-10-25 |  | 2025-09-24 |  | 2025-12-03 |  | 2025-10-30 |  | 2026-01-21 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3165 | LATER | ARFA | SAU4005-G154-BAA-&ELU-20507 | IPBD (V)-GROUNDING LAYOUT AND DETAILS (GT) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-09-19 |  | 2025-10-25 |  |  |  | 0 |  |  |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3166 | LATER | ARFA | SAU4005-G154-BAA-&ELU-20508 | IPBD (V)-GROUNDING LAYOUT AND DETAILS (ST) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-09-19 |  | 2025-10-25 |  |  |  | 0 |  |  |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3167 | LATER | ARFA | SAU4005-G154-BAA-&EFE-20509 | IPBD (V)-TEMPERATURE CONTROL WIRING DIAGRAM (GT) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-09-19 |  | 2025-10-25 |  | 2025-10-09 |  | 2026-01-21 |  | 2025-11-14 |  | 2026-03-23 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3168 | LATER | ARFA | SAU4005-G154-BAA-&EFE-20510 | IPBD (V)-TEMPERATURE CONTROL WIRING DIAGRAM (ST) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-09-19 |  | 2025-10-25 |  | 2025-10-09 |  | 2025-12-03 |  | 2025-11-14 |  | 2026-03-23 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3169 | LATER | ARFA | SAU4005-G154-BAA-&EMA-20511 | IPBD (V)-CONNECTION TO AUXILIARY TRANSFORMER (GT) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-10-15 |  | 2025-11-15 |  | 2025-11-04 |  | 2025-12-03 |  | 2025-12-10 |  | 2026-02-23 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3170 | LATER | ARFA | SAU4005-G154-BAA-&EMA-20512 | IPBD (V)-CONNECTION TO GENERATOR (GT) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-10-15 |  | 2025-11-15 |  | 2025-11-04 |  | 2025-12-14 |  | 2025-12-10 |  | 2025-12-29 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3171 | LATER | ARFA | SAU4005-G154-BAA-&EMA-20513 | IPBD (V)-CONNECTION TO MAIN TRANSFORMER (GT) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-10-15 |  | 2025-11-15 |  | 2025-11-04 |  | 2025-12-14 |  | 2025-12-10 |  | 2025-12-29 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3172 | LATER | ARFA | SAU4005-G154-BAA-&EMA-20514 | IPBD (V)-CONNECTION TO GENERATOR CIRCUIT BREAKER (GT) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-10-15 |  | 2025-11-15 |  | 2025-11-04 |  | 2025-12-14 |  | 2025-12-10 |  | 2025-12-29 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3173 | LATER | ARFA | SAU4005-G154-BAA-&EMA-20515 | IPBD (V)-CONNECTION TO SAVT CUBICLE (GT) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-10-15 |  | 2025-12-02 |  | 2025-11-04 |  | 2025-12-03 |  | 2025-12-10 |  | 2026-02-23 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3174 | LATER | ARFA | SAU4005-G154-BAA-&ELU-20516 | IPBD (V)-SUPPORT STEEL STRUCTURE (GT) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-10-15 |  | 2025-12-02 |  | 2025-11-04 |  | 0 |  | 2025-12-10 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3175 | LATER | ARFA | SAU4005-G154-BAA-&ELU-20517 | IPBD (V)-SHORT CIRCUIT TEST DEVICE (GT) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-10-15 |  | 2025-10-25 |  | 2025-11-04 |  | 0 |  | 2025-12-10 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3176 | LATER | ARFA | SAU4005-G154-BAA-&ELU-20518 | IPBD (V)-SUNSHINE PROOF ASSEMBLY (GT) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-10-20 |  | 2025-11-15 |  | 2025-11-09 |  | 2025-12-03 |  | 2025-12-15 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3177 | LATER | ARFA | SAU4005-G154-BAA-&EMA-20519 | IPBD (V)-CONNECTION TO MAIN TRANSFORMER (ST) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-10-15 |  | 2025-11-15 |  | 2025-11-04 |  | 2025-12-14 |  | 2025-12-10 |  | 2025-12-29 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3178 | LATER | ARFA | SAU4005-G154-BAA-&EMA-20520 | IPBD (V)-CONNECTION TO GENERATOR CIRCUIT BREAKER (ST) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-10-15 |  | 2025-11-15 |  | 2025-11-04 |  | 2025-12-14 |  | 2025-12-10 |  | 2025-12-29 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3179 | LATER | ARFA | SAU4005-G154-BAA-&EMA-20521 | IPBD (V)-CONNECTION TO GENERATOR (ST) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-10-15 |  | 2025-11-15 |  | 2025-11-04 |  | 2025-12-14 |  | 2025-12-10 |  | 2025-12-29 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3180 | LATER | ARFA | SAU4005-G154-BAA-&EMA-20522 | IPBD (V)-CONNECTION TO SAVT CUBICLE (ST) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-10-15 |  | 2025-12-02 |  | 2025-11-04 |  | 2025-12-03 |  | 2025-12-10 |  | 2026-02-23 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3181 | LATER | ARFA | SAU4005-G154-BAA-&EMA-20523 | IPBD (V)-CONNECTION TO EXCITATION TRANSFORMER (ST) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-10-15 |  | 2025-12-02 |  | 2025-11-04 |  | 2025-12-14 |  | 2025-12-10 |  | 2025-12-29 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3182 | LATER | ARFA | SAU4005-G154-BAA-&ELU-20524 | IPBD (V)-SUPPORT STEEL STRUCTURE (ST) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-10-20 |  | 2025-12-02 |  | 2025-11-09 |  | 0 |  | 2025-12-15 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3183 | LATER | ARFA | SAU4005-G154-BAA-&ELU-20525 | IPBD (V)-SHORT CIRCUIT TEST DEVICE (ST) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-10-15 |  | 2025-10-25 |  | 2025-11-04 |  | 0 |  | 2025-12-10 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3184 | LATER | ARFA | SAU4005-G154-BAA-&ELU-20526 | IPBD (V)-SUNSHINE PROOF ASSEMBLY (ST) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-10-20 |  | 2025-11-15 |  | 2025-11-09 |  | 2025-12-03 |  | 2025-12-15 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3185 | LATER | ARFA | SAU4005-G154-BAA-&EPA-20527 | IPBD (V)-MATERIAL LIST (GT) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFI | IFD | [14 empty] | 2025-10-20 |  | 2026-01-13 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3186 | LATER | ARFA | SAU4005-G154-BAA-&EPA-20528 | IPBD (V)-MATERIAL LIST (ST) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFI | IFD | [14 empty] | 2025-09-19 |  | 2026-03-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3187 | LATER | ARFA | SAU4005-G154-BAA-&ELU-20529 | IPBD (V)-SAVT DRAWING (GT) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-09-19 |  | 2025-12-02 |  | 2025-10-09 |  | 0 |  | 2025-11-14 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3188 | LATER | ARFA | SAU4005-G154-BAA-&ELU-20530 | IPBD (V)-SAVT DRAWING (ST) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-09-19 |  | 2025-12-02 |  | 2025-10-09 |  | 0 |  | 2025-11-14 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3189 | LATER | ARFA | SAU4005-G154-BAA-&ELU-20531 | IPBD (V)-DRY AIR PRESSURIZATION SYSTEM (GT&ST) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-09-19 |  | 2025-10-25 |  | 2025-10-09 |  | 2025-12-03 |  | 2025-11-14 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3190 | LATER | ARFA | SAU4005-G154-BAA-&ELU-20532 | IPBD (V)-MOBILE HOT AIR MAINTENANCE SYSTEM (GT&ST) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-09-19 |  | 2025-10-25 |  | 2025-10-09 |  | 2026-01-08 |  | 2025-11-14 |  | 2026-03-31 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3191 | LATER | ARFA | SAU4005-G154-BAA-&EDB-20533 | IPBD (V)-NAMEPLATE DRAWING (GT&ST) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 1916-11-14 |  | 2025-10-25 |  |  |  | 2026-01-08 |  |  |  | 2026-02-01 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3192 | LATER | ARFA | SAU4005-G154-BAA-&ELU-20534 | IPBD (V)-IPB TYPICAL DETAILS (GT) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-09-19 |  | 2025-10-25 |  |  |  | 0 |  |  |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3193 | LATER | ARFA | SAU4005-G154-BAA-&ELU-20535 | IPBD (V)-IPB TYPICAL DETAILS (ST) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-09-19 |  | 2025-10-25 |  |  |  | 0 |  |  |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3194 | LATER | ARFA | SAU4005-G154-BAA-&EDC-20536 | IPBD (V)-O&M Manuals (GT&ST) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-09-19 |  | 2025-10-25 |  |  |  | 0 |  |  |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3195 | LATER | ARFA | SAU4005-G154-BAA-&EQC-20537 | IPBD (V)-Inspection & Test Plan (ITP)(GT&ST) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-09-09 | [33 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3196 | LATER | ARFA | SAU4005-G154-BAA-&EQC-20538 | IPBD (V)-FAT Procedure (GT&ST) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-09-09 |  | 2025-09-09 |  |  |  | 2026-01-04 |  |  |  | 2026-02-05 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3197 | LATER | ARFA | SAU4005-G154-BAA-&EQC-20539 | IPBD (V)-FAT report (GT&ST) | G154 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | IPBD(ACC) | IFA | IFD |  |  | 2025-09-09 | [33 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3198 | LATER | BAOJI | SAU4005-G155-BBA-&EAB-20600 | MV Switchgear(V)-Document List | G155 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | MV Switchgear | IFI | IFD | [14 empty] | 2025-09-04 |  | 2026-01-09 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3199 | LATER | BAOJI | SAU4005-G155-BBA-&EDA-20601 | MV Switchgear(V)-Technical Data Sheet | G155 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | MV Switchgear | IFA | IFD |  |  | 2025-09-29 |  | 2025-09-30 |  |  |  | 2025-12-21 |  |  |  | 2026-02-04 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3200 | LATER | BAOJI | SAU4005-G155-BBA-&ELB-20602 | MV Switchgear(V)-foundation & structure layout drawing | G155 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | MV Switchgear | IFI | IFD | [14 empty] | 2025-09-14 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3201 | LATER | BAOJI | SAU4005-G155-BBA-&ELU-20603 | MV Switchgear(V)-General Arrangement drawing | G155 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | MV Switchgear | IFA | IFD |  |  | 2025-09-04 |  | 2025-10-25 |  |  |  | 2026-01-04 |  |  |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3202 | LATER | BAOJI | SAU4005-G155-BBA-&EFF-20604 | MV Switchgear(V)-Single Line Diagram | G155 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | MV Switchgear | IFA | IFD |  |  | 2025-09-04 |  | 2025-09-30 |  | 2025-09-24 |  | 2025-10-17 |  | 2025-10-30 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3203 | LATER | BAOJI | SAU4005-G155-BBA-&EFF-20605 | MV Switchgear(V)-Schematic Diagram | G155 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | MV Switchgear | IFA | IFD |  |  | 2025-09-24 |  | 2025-09-30 |  | 2025-10-14 |  | 2025-10-22 |  | 2025-11-19 |  | 2026-01-19 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3204 | LATER | BAOJI | SAU4005-G155-BBA-&EFF-20606 | MV Switchgear(V)-Mechanical Interlock Schematic Diagram | G155 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | MV Switchgear | IFI | IFD | [14 empty] | 2025-09-14 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3205 | LATER | BAOJI | SAU4005-G155-BBA-&EFF-20607 | MV Switchgear(V)-HSBT Schematic & Wiring Diagram | G155 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | MV Switchgear | IFI | IFD | [14 empty] | 2025-09-19 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| dcc changed | 3206 | LATER | BAOJI | SAU4005-G155-BBA-&EDB-20608 | MV Switchgear(V)-Name Plate drawing | G155 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | MV Switchgear | IFA | IFD |  |  | 2025-09-24 |  | 2026-02-14 |  |  |  | 2026-02-24 |  |  |  | 2026-03-09 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3207 | LATER | BAOJI | SAU4005-G155-BBA-&EFF-20609 | MV Switchgear(V)-Wiring Diagram | G155 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | MV Switchgear | IFI | IFD | [14 empty] | 2025-09-29 |  | 2025-12-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3208 | LATER | BAOJI | SAU4005-G155-BBA-&EQC-20610 | MV Switchgear(V)-Type Test Certificate | G155 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | MV Switchgear | IFA | IFD |  |  | 2025-12-31 | [33 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3209 | LATER | BAOJI | SAU4005-G155-BBA-&EDA-20611 | MV Switchgear(V)-Current transformers catalogue and VA characteristic curves | G155 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | MV Switchgear | IFI | IFD | [14 empty] | 2025-09-29 |  | 2026-01-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3210 | LATER | BAOJI | SAU4005-G155-BBA-&EED-20612 | MV Switchgear(V)-Current transformers calculation | G155 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | MV Switchgear | IFA | IFD |  |  | 2025-09-14 | [33 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3211 | LATER | BAOJI | SAU4005-G155-BBA-&EED-20613 | MV Switchgear(V)-Busbar sizing calculation | G155 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | MV Switchgear | IFI | IFD | [14 empty] | 2025-09-14 |  | 2025-12-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3212 | LATER | BAOJI | SAU4005-G155-BBA-&EDC-20614 | MV Switchgear(V)-Protection relay Catalogue | G155 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | MV Switchgear | IFI | IFD | [14 empty] | 2025-09-09 |  | 2025-10-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3213 | LATER | BAOJI | SAU4005-G155-BBA-&EED-20615 | MV Switchgear(V)-DC & AC Electrical load list & Panel Heat Load dissipation | G155 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | MV Switchgear | IFI | IFC | [14 empty] | 2025-09-14 |  | 2025-11-27 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3214 | LATER | BAOJI | SAU4005-G155-BBA-&EQC-20616 | MV Switchgear(V)-FAT ITP & TEST Procedure | G155 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | YES | QA/QC | Electrical | SEPCOIII | MV Switchgear | IFA | IFD |  |  | 2025-09-19 |  | 2025-10-16 |  |  |  | 2025-12-23 |  |  |  | 2026-01-18 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3215 | LATER | BAOJI | SAU4005-G155-BBA-&EQA-20617 | MV Switchgear(V)-Factory Acceptance Test Results Report | G155 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | YES | QA/QC | Electrical | SEPCOIII | MV Switchgear | IFA | IFD |  |  | 2025-09-19 | [33 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3216 | LATER | BAOJI | SAU4005-G155-BBA-&EFP-20618 | MV Switchgear(V)-I/O List | G155 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | MV Switchgear | IFI | IFD | [14 empty] | 2025-09-29 |  | 2026-04-01 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3217 | LATER | BAOJI | SAU4005-G155-BBA-&EDE-20619 | MV Switchgear(V)-Installation O&M, Instruction Catalogue | G155 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | MV Switchgear | IFA | IFD |  |  | 2025-10-30 |  | 2026-01-09 |  |  |  | 0 |  |  |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3218 | LATER | BAOJI | SAU4005-G155-BBA-&EBF-20620 | MV Switchgear(V)-Packing List | G155 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | MV Switchgear | IFI | IFD | [14 empty] | 2026-01-14 |  | 2026-02-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3219 | LATER | BAOJI | SAU4005-G155-BBA-&EBB-20621 | MV Swtichgear(V)-End of Manufacturing Report | G155 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | MV Switchgear | IFA | IFD |  |  | 2026-01-14 |  | 2026-05-13 |  |  |  | 0 |  |  |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3220 | LATER | BAOJI | SAU4005-G155-BBA-&EAB-20622 | MV Swtichgear(V)-Spare Parts & Special Tools List | G155 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | MV Switchgear | IFA | IFD |  |  | 2026-01-14 | [33 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3221 | LATER | NCS | SAU4005-G164-PUR-&EPA-21801 | Cathodic Protection (V)-Material list for outside the bottom of the tank | G164 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Cathodic Protection System | IFI | IFC | [14 empty] | 2025-08-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3222 | LATER | NCS | SAU4005-G164-PUR-&EEC-21802 | Cathodic Protection (V)-Flexible anode arrangement diagram for outside the bottom of the tank | G164 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Cathodic Protection System | IFI | IFC | [14 empty] | 2025-08-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3223 | LATER | NCS | SAU4005-G164-PUR-&EEC-21803 | Cathodic Protection (V)-Reference electrode arrangement diagramfor outside the bottom of the tank | G164 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Cathodic Protection System | IFI | IFC | [14 empty] | 2025-08-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3224 | LATER | NCS | SAU4005-G164-PUR-&EMA-21804 | Cathodic Protection (V)-Wiring drawing for outside the bottom of the tank | G164 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Cathodic Protection System | IFI | IFC | [14 empty] | 2025-08-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3225 | LATER | NCS | SAU4005-G164-PUR-&EEC-21805 | Cathodic Protection (V)-Installation diagram of cathode and zero position test points for outside the bottom of the tank | G164 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Cathodic Protection System | IFI | IFC | [14 empty] | 2025-08-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3226 | LATER | NCS | SAU4005-G164-PUR-&EEC-21806 | Cathodic Protection (V)-Junction box for outside the bottom of the tank | G164 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Cathodic Protection System | IFI | IFC | [14 empty] | 2025-08-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3227 | LATER | NCS | SAU4005-G164-PUR-&EEC-21807 | Cathodic Protection (V)-Test station for outside the bottom of the tank | G164 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Cathodic Protection System | IFI | IFC | [14 empty] | 2025-08-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3228 | LATER | NCS | SAU4005-G164-PUR-&EEC-21808 | Cathodic Protection (V)-PCR for outside the bottom of the tank | G164 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Cathodic Protection System | IFI | IFC | [14 empty] | 2025-08-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3229 | LATER | NCS | SAU4005-G164-PUR-&EEC-21809 | Cathodic Protection (V)-Transfomer rectifier for outside the bottom of the tank | G164 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Cathodic Protection System | IFI | IFC | [14 empty] | 2025-08-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3230 | LATER | NCS | SAU4005-G164-PUR-&EMA-21810 | Cathodic Protection (V)-Transformer rectifier schematic diagram for outside the bottom of the tank | G164 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Cathodic Protection System | IFI | IFC | [14 empty] | 2025-08-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3231 | LATER | NCS | SAU4005-G164-PUR-&EPA-21811 | Cathodic Protection (V)-Material list for UG pipe | G164 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Cathodic Protection System | IFI | IFC | [14 empty] | 2025-08-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3232 | LATER | NCS | SAU4005-G164-PUR-&EMA-21812 | Cathodic Protection (V)-Schematic diagram of MMO anode and test station distribution for UG pipe | G164 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Cathodic Protection System | IFI | IFC | [14 empty] | 2025-08-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3233 | LATER | NCS | SAU4005-G164-PUR-&EEC-21813 | Cathodic Protection (V)-Test station for UG pipe | G164 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Cathodic Protection System | IFI | IFC | [14 empty] | 2025-08-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3234 | LATER | NCS | SAU4005-G164-PUR-&EEC-21814 | Cathodic Protection (V)-Installation diagram of cathode and zero position test points for UG pipe | G164 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Cathodic Protection System | IFI | IFC | [14 empty] | 2025-08-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3235 | LATER | NCS | SAU4005-G164-PUR-&EEC-21815 | Cathodic Protection (V)-Installation diagram of spark gaps for UG pipe | G164 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Cathodic Protection System | IFI | IFC | [14 empty] | 2025-08-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3236 | LATER | NCS | SAU4005-G164-PUR-&EMA-21816 | Cathodic Protection (V)-Wiring Diagram for UG pipe | G164 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Cathodic Protection System | IFI | IFC | [14 empty] | 2025-08-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3237 | LATER | NCS | SAU4005-G164-PUR-&EEC-21817 | Cathodic Protection (V)-Transfomer rectifier for UG pipe | G164 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Cathodic Protection System | IFI | IFC | [14 empty] | 2025-08-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3238 | LATER | NCS | SAU4005-G164-PUR-&EMA-21818 | Cathodic Protection (V)-Transformer rectifier schematic diagram for UG pipe | G164 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Cathodic Protection System | IFI | IFC | [14 empty] | 2025-08-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
|  | 3239 | LATER | NCS | SAU4005-G164-PUR-&EED-21819 | Cathodic Protection (V)-Calculation sheet | G164 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Cathodic Protection System | IFA | IFC |  |  | 2025-08-20 |  |  |  | 2025-09-09 |  |  |  | 2025-10-15 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3240 | LATER | JIANGSU TONGYUAN | SAU4005-G105-QJA-&BDA-07401 | Industrial Gas System (H₂, N₂ & CO₂)（V）-Data Sheet | G105 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECHANICAL | MECHANICAL | SEPCOIII | Industrial Gas System | IFA | IFD |  |  | 2025-12-30 |  | 2025-11-06 |  | 2026-01-19 |  | 2025-11-20 |  | 2026-02-24 |  | 2026-03-29 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
| NEW | 3241 | LATER | JIANGSU TONGYUAN | SAU4005-G105-QJA-&BDA-07402 | Industrial Gas System (H₂, N₂ & CO₂)（V）-Cylinder Data Sheet | G105 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECHANICAL | MECHANICAL | SEPCOIII | Industrial Gas System | IFI | IFD | [14 empty] | 2025-12-30 |  | 2025-11-06 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
| NEW | 3242 | LATER | JIANGSU TONGYUAN | SAU4005-G105-QJA-&PFB-07403 | Industrial Gas System (H₂, N₂ & CO₂)（V）-P&ID | G105 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECHANICAL | MECHANICAL | SEPCOIII | Industrial Gas System | IFA | IFD |  |  | 2025-12-30 |  | 2025-11-06 |  | 2026-01-19 |  | 2025-11-23 |  | 2026-02-24 |  | 2026-01-25 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
| NEW | 3243 | LATER | JIANGSU TONGYUAN | SAU4005-G105-QJA-&MLU-07404 | Industrial Gas System (H₂, N₂ & CO₂)（V）-GA | G105 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECHANICAL | MECHANICAL | SEPCOIII | Industrial Gas System | IFA | IFD |  |  | 2026-01-09 |  | 2025-11-24 |  | 2026-01-29 |  | 2025-12-07 |  | 2026-03-06 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
| NEW | 3244 | LATER | JIANGSU TONGYUAN | SAU4005-G105-QJA-&BTA-07405 | Industrial Gas System (H₂, N₂ & CO₂)（V）-Name Plate Drawing | G105 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECHANICAL | MECHANICAL | SEPCOIII | Industrial Gas System | IFI | IFD | [14 empty] | 2026-01-14 |  | 2026-02-02 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
| NEW | 3245 | LATER | JIANGSU TONGYUAN | SAU4005-G105-QJA-&AQC-07406 | Industrial Gas System (H₂, N₂ & CO₂)（V）-Inspection and Test Plan | G105 | QA/QC | A-Overall management | YES | QA/QC | QUALITY | SEPCOIII | Industrial Gas System | IFA | IFD |  |  | 2025-12-30 |  |  |  | 2026-01-19 |  |  |  | 2026-02-24 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
| NEW | 3246 | LATER | JIANGSU TONGYUAN | SAU4005-G105-QJA-&AQC-07407 | Industrial Gas System (H₂, N₂ & CO₂)（V）-Test Procedure | G105 | QA/QC | A-Overall management | YES | QA/QC | QUALITY | SEPCOIII | Industrial Gas System | IFA | IFD |  |  | 2025-12-30 |  | 2025-11-18 |  | 2026-01-19 |  | 0 |  | 2026-02-24 |  | 2026-01-25 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
| NEW | 3247 | LATER | JIANGSU TONGYUAN | SAU4005-G105-QJA-&AQA-07408 | Industrial Gas System (H₂, N₂ & CO₂)（V）-Pickling and Passivation Procedure | G105 | QA/QC | A-Overall management | YES | QA/QC | QUALITY | SEPCOIII | Industrial Gas System | IFA | IFD |  |  | 2025-12-30 |  | 2025-12-14 |  | 2026-01-19 |  | 2026-01-04 |  | 2026-02-24 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
| NEW | 3248 | LATER | JIANGSU TONGYUAN | SAU4005-G105-QJA-&AQA-07409 | Industrial Gas System (H₂, N₂ & CO₂)（V）-Final quality document | G105 | QA/QC | A-Overall management | YES | QA/QC | QUALITY | SEPCOIII | Industrial Gas System | IFI | IFD | [14 empty] | 2026-02-28 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
| dcc changed | 3249 | LATER | JIANGSU TONGYUAN | SAU4005-G105-QJA-&MQA-07410 | Industrial Gas System (H₂, N₂ & CO₂)（V）-Painting Procedure | G105 | Engineering | B-Overall technology | YES | Insulation & Painting | MECHANICAL | SEPCOIII | Industrial Gas System | IFA | IFD |  |  | 2026-01-04 |  |  |  | 2026-01-24 |  |  |  | 2026-03-01 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
| NEW | 3250 | LATER | JIANGSU TONGYUAN | SAU4005-G105-QJA-&EPC-07411 | Industrial Gas System (H₂, N₂ & CO₂)（V）-Instrument list | G105 | I&C | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | MECHANICAL | SEPCOIII | Industrial Gas System | IFA | IFD |  |  | 2025-12-29 |  | 2026-01-15 |  | 2026-01-18 |  | 2026-02-04 |  | 2026-02-23 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO |  |  |  |  | Open
| NEW | 3251 | LATER | JIANGSU TONGYUAN | SAU4005-G105-QJA-&EDA-07412 | Industrial Gas System (H₂, N₂ & CO₂)（V）-Instrument datasheet | G105 | I&C | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | MECHANICAL | SEPCOIII | Industrial Gas System | IFA | IFD |  |  | 2026-01-04 |  | 2026-01-21 |  | 2026-01-24 |  | 2026-02-04 |  | 2026-03-01 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3252 | LATER | JIANGSU TONGYUAN | SAU4005-G105-QJA-&ETA-07413 | Industrial Gas System (H₂, N₂ & CO₂)（V）-HOOKUP DRAWING | G105 | I&C | E-Electrotechnology (including control, information and communication techniques) | YES | I&C | MECHANICAL | SEPCOIII | Industrial Gas System | IFA | IFD |  |  | 2026-01-04 |  | 2026-01-21 |  | 2026-01-24 |  | 2026-02-04 |  | 2026-03-01 |  | 2026-04-28 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3253 | LATER | JIANGSU TONGYUAN | SAU4005-G169-HHZ-&MDA-22312 | Instrument Air Heater (V)-Data Sheet | G169 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Instrument Air Heater | IFA | IFD |  |  | 2026-03-15 |  | 2026-02-09 |  | 2026-04-04 |  | 2026-03-05 |  | 2026-05-10 |  | 2026-03-29 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3254 | LATER | JIANGSU TONGYUAN | SAU4005-G169-HHZ-&MTA-22313 | Instrument Air Heater (V)- GA drawing | G169 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Instrument Air Heater | IFA | IFD |  |  | 2026-03-15 |  | 2026-02-09 |  | 2026-04-04 |  | 2026-03-05 |  | 2026-05-10 |  | 2026-03-29 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3255 | LATER | JIANGSU TONGYUAN | SAU4005-G169-HHZ-&ETA-22314 | Instrument Air Heater (V)-Control panel GA drawing | G169 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Instrument Air Heater | IFA | IFD |  |  | 2026-03-15 |  | 2026-02-09 |  | 2026-04-04 |  | 2026-03-05 |  | 2026-05-10 |  | 2026-03-31 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3256 | LATER | JIANGSU TONGYUAN | SAU4005-G169-HHZ-&EFP-22315 | Instrument Air Heater (V)-IO list | G169 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Instrument Air Heater | IFI | IFD | [14 empty] | 2026-03-15 |  | 2026-03-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3257 | LATER | JIANGSU TONGYUAN | SAU4005-G169-HHZ-&EEC-22316 | Instrument Air Heater (V)-Electric load list | G169 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Instrument Air Heater | IFI | IFD | [14 empty] | 2026-03-15 |  | 2026-03-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| PURPOSE CHANGED | 3258 | LATER | JIANGSU TONGYUAN | SAU4005-G169-HHZ-&EFF-22317 | Instrument Air Heater (V)-Control philosophy | G169 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Instrument Air Heater | IFA | IFD |  |  | 2026-03-15 |  | 2026-03-13 |  | 2026-04-05 |  | 2026-03-05 |  | 2026-05-11 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| dcc changed | 3259 | LATER | JIANGSU TONGYUAN | SAU4005-G169-HHZ-&MQA-22318 | Instrument Air Heater (V)-Painting Procudure | G169 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Instrument Air Heater | IFI | IFD | [14 empty] | 2026-03-15 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3260 | LATER | JIANGSU TONGYUAN | SAU4005-G169-HHZ-&AQA-22319 | Instrument Air Heater (V)-Test Procedures | G169 | QA/QC | QA/QC | YES | QA/QC | General | SEPCOIII | Instrument Air Heater | IFI | IFD | [14 empty] | 2026-03-15 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3261 | LATER | JIANGSU TONGYUAN | SAU4005-G169-HHZ-&AQA-22320 | Instrument Air Heater (V)-ITP | G169 | QA/QC | QA/QC | YES | QA/QC | General | SEPCOIII | Instrument Air Heater | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3262 | LATER | JIANGSU TONGYUAN | SAU4005-G169-HHZ-&AQA-22321 | Instrument Air Heater (V)-Final quality document | G169 | QA/QC | QA/QC | YES | QA/QC | General | SEPCOIII | Instrument Air Heater | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| dcc changed | 3263 | LATER | JIANGSU TONGYUAN | SAU4005-G169-HHZ-&EDA-22322 | Instrument Air Heater (V)-Nameplate | G169 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Instrument Air Heater | IFA | IFD |  |  | 2026-03-15 |  | 2026-04-22 |  | 2026-04-04 |  | 0 |  | 2026-05-10 |  | 2026-04-26 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3264 | LATER | JIANGSU TONGYUAN | SAU4005-G169-HHZ-&MEC-22323 | Instrument Air Heater（V）-Thermal insulation document | G169 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Instrument Air Heater | IFI | IFD |  |  | 2026-04-20 |  |  |  | 2026-05-10 |  |  |  | 2026-06-16 | [5 empty] | 2026-04-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3265 | LATER | JIANGSU TONGYUAN | SAU4005-G169-HHZ-&MDA-22301 | Fuel Oil tank Heater (V)-Data Sheet | G169 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Tank Heater | IFA | IFD |  |  | 2026-03-15 |  | 2026-02-09 |  | 2026-04-04 |  | 2026-03-05 |  | 2026-05-10 |  | 2026-03-29 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3266 | LATER | JIANGSU TONGYUAN | SAU4005-G169-HHZ-&MTA-22302 | Fuel Oil tank Heater (V)- GA drawing | G169 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Tank Heater | IFA | IFD |  |  | 2026-03-15 |  | 2026-02-09 |  | 2026-04-04 |  | 2026-03-05 |  | 2026-05-10 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3267 | LATER | JIANGSU TONGYUAN | SAU4005-G169-HHZ-&ETA-22303 | Fuel Oil tank Heater (V)-Control panel GA drawing | G169 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Fuel Oil Tank Heater | IFA | IFD |  |  | 2026-03-15 |  | 2026-02-09 |  | 2026-04-04 |  | 2026-03-05 |  | 2026-05-10 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3268 | LATER | JIANGSU TONGYUAN | SAU4005-G169-HHZ-&EFP-22304 | Fuel Oil tank Heater (V)-IO list | G169 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Fuel Oil Tank Heater | IFI | IFD | [14 empty] | 2026-03-15 |  | 2026-03-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3269 | LATER | JIANGSU TONGYUAN | SAU4005-G169-HHZ-&EEC-22305 | Fuel Oil tank Heater (V)-Electric load list | G169 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Fuel Oil Tank Heater | IFI | IFD | [14 empty] | 2026-03-15 |  | 2026-03-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3270 | LATER | JIANGSU TONGYUAN | SAU4005-G169-HHZ-&EFF-22306 | Fuel Oil tank Heater (V)-Control philosophy | G169 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Fuel Oil Tank Heater | IFI | IFD | [14 empty] | 2026-03-15 |  | 2026-02-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3271 | LATER | JIANGSU TONGYUAN | SAU4005-G169-HHZ-&MDC-22307 | Fuel Oil tank Heater (V)-Painting Procudure | G169 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Tank Heater | IFI | IFD | [14 empty] | 2026-03-15 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3272 | LATER | JIANGSU TONGYUAN | SAU4005-G169-HHZ-&AQA-22308 | Fuel Oil tank Heater (V)-Test Procedures | G169 | QA/QC | A-Overall management | NO | QA/QC | General | SEPCOIII | Fuel Oil Tank Heater | IFI | IFD | [14 empty] | 2026-03-15 |  | 2026-03-12 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3273 | LATER | JIANGSU TONGYUAN | SAU4005-G169-HHZ-&AQA-22309 | Fuel Oil tank Heater (V)-ITP | G169 | QA/QC | A-Overall management | NO | QA/QC | General | SEPCOIII | Fuel Oil Tank Heater | IFA | IFD |  |  | 2026-03-15 |  | 2026-02-09 |  | 2026-04-04 |  | 2026-03-08 |  | 2026-05-10 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3274 | LATER | JIANGSU TONGYUAN | SAU4005-G169-HHZ-&AQA-22310 | Fuel Oil tank Heater (V)-Final quality document | G169 | QA/QC | A-Overall management | NO | QA/QC | General | SEPCOIII | Fuel Oil Tank Heater | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| dcc changed | 3275 | LATER | JIANGSU TONGYUAN | SAU4005-G169-HHZ-&EDA-22311 | Fuel Oil tank Heater (V)-Nameplate | G169 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Fuel Oil Tank Heater | IFA | IFD |  |  | 2026-03-15 |  | 2026-04-22 |  | 2026-04-04 |  | 0 |  | 2026-05-10 |  | 2026-04-26 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3276 | LATER | JIANGSU TONGYUAN | SAU4005-G169-HHZ-&BDA-22324 | Fuel oil tank heater（V）-Chemical list | G169 | Operation & Maintenacne | B-Overall technology | NO | O&M | General | SEPCOIII | Fuel Oil Tank Heater | IFI | IFD | [14 empty] | 2026-04-20 |  | 2026-04-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3278 | LATER | SHANDONG JIRONG | SAU4005-G108-STA-&MDA-07701 | SHOP FABRICATED TANK (V)-DATA SHEET FOR SHOP FABRICATED TANK | G108 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SHOP FABRICATED TANK | IFA | IFD |  |  | 2025-12-30 |  | 2025-11-04 |  | 2026-01-19 |  | 2025-11-17 |  | 2026-02-24 |  | 2026-05-14 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3279 | LATER | SHANDONG JIRONG | SAU4005-G108-STA-&MLU-07702 | SHOP FABRICATED TANK (V)-GA DRAWING FOR CCCW EXPANSION TANK | G108 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SHOP FABRICATED TANK | IFA | IFD |  |  | 2025-12-30 |  | 2025-10-27 |  | 2026-01-19 |  | 2025-11-09 |  | 2026-02-24 |  | 2026-04-02 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3280 | LATER | SHANDONG JIRONG | SAU4005-G108-STA-&MLU-07703 | SHOP FABRICATED TANK (V)-GA DRAWING FOR CHEMICAL NEWITIVE TANK | G108 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SHOP FABRICATED TANK | IFA | IFD |  |  | 2025-12-30 |  | 2025-10-27 |  | 2026-01-19 |  | 2025-11-09 |  | 2026-02-24 |  | 2026-04-02 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3281 | LATER | SHANDONG JIRONG | SAU4005-G108-STA-&MLU-07704 | SHOP FABRICATED TANK (V)-GA DRAWING FOR POTABLE WATER STORAGE TANK | G108 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SHOP FABRICATED TANK | IFA | IFD |  |  | 2025-12-30 |  | 2025-10-27 |  | 2026-01-19 |  | 2025-11-09 |  | 2026-02-24 |  | 2026-01-13 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3282 | LATER | SHANDONG JIRONG | SAU4005-G108-STA-&MLU-07705 | SHOP FABRICATED TANK (V)-GA DRAWING FOR POTABLE WATER OVERHEAD TANK | G108 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SHOP FABRICATED TANK | IFA | IFD |  |  | 2025-12-30 |  | 2025-10-27 |  | 2026-01-19 |  | 2025-11-09 |  | 2026-02-24 |  | 2026-04-28 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3283 | LATER | SHANDONG JIRONG | SAU4005-G108-STA-&MLU-07706 | SHOP FABRICATED TANK (V)-GA DRAWING FOR PUMP HOUSE AREA FUELOIL DRAIN TANK | G108 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SHOP FABRICATED TANK | IFA | IFD |  |  | 2025-12-30 |  | 2025-10-27 |  | 2026-01-19 |  | 2025-11-09 |  | 2026-02-24 |  | 0 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3284 | LATER | SHANDONG JIRONG | SAU4005-G108-STA-&MLU-07707 | SHOP FABRICATED TANK (V)-GA DRAWING FOR PLUSE AIR ACCUMULATOR | G108 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SHOP FABRICATED TANK | IFA | IFD |  |  | 2025-12-30 |  | 2025-10-27 |  | 2026-01-19 |  | 2025-11-09 |  | 2026-02-24 |  | 2026-04-02 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3286 | LATER | SHANDONG JIRONG | SAU4005-G108-STA-&MPD-07709 | SHOP FABRICATED TANK (V)-VALVE LIST FOR SHOP FABRICATED TANK | G108 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SHOP FABRICATED TANK | IFI | IFD | [14 empty] | 2026-01-30 |  | 2026-02-09 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3287 | LATER | SHANDONG JIRONG | SAU4005-G108-STA-&MDB-07710 | SHOP FABRICATED TANK (V)-PAINT SCHEME FOR SHOP FABRICATED TANK | G108 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SHOP FABRICATED TANK | IFI | IFD | [14 empty] | 2026-01-30 |  | 2026-01-24 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3288 | LATER | SHANDONG JIRONG | SAU4005-G108-STA-&MQA-07711 | SHOP FABRICATED TANK (V)-INSPECTION AND TEST PLAN FOR SHOP FABRICATED TANK | G108 | QA/QC | A-Overall management | YES | QA/QC | General | SEPCOIII | SHOP FABRICATED TANK | IFA | IFD |  |  | 2026-01-30 |  | 2025-11-07 |  | 2026-02-19 |  | 2025-12-14 |  | 2026-03-27 |  | 2026-01-25 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3289 | LATER | SHANDONG JIRONG | SAU4005-G108-STA-&MEC-07712 | SHOP FABRICATED TANK (V)-HYDROSTATIC TEST PROCEDURE FOR SHOP FABRICATED TANK | G108 | QA/QC | A-Overall management | YES | QA/QC | General | SEPCOIII | SHOP FABRICATED TANK | IFI | IFD | [14 empty] | 2026-01-30 |  | 2025-11-08 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3290 | LATER | SHANDONG JIRONG | SAU4005-G108-STA-&MED-07713 | SHOP FABRICATED TANK (V)-CALCULATION SHEET FOR SHOP FABRICATED TANK | G108 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SHOP FABRICATED TANK | IFA | IFD |  |  | 2026-01-30 |  | 2026-02-09 |  | 2026-02-19 |  | 2026-02-24 |  | 2026-03-27 |  | 2026-03-15 | [21 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3291 | LATER | SHANDONG JIRONG | SAU4005-G108-STA-&MTC-07714 | SHOP FABRICATED TANK (V)-NAMEPLATE DRAWING FOR SHOP FABRICATED TANK | G108 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SHOP FABRICATED TANK | IFA | IFD |  |  |  |  | 2026-02-09 |  |  |  | 2025-11-09 |  |  |  | 2026-04-28 |  | 2026-01-30 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3292 | LATER | SHANDONG JIRONG | SAU4005-G108-STA-&MLU-07715 | SHOP FABRICATED TANK (V)-ASSEMBLY DRAWING FOR CCCW EXPANSION TANK | G108 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SHOP FABRICATED TANK | IFI | IFC | [14 empty] | 2026-03-30 |  | 2026-04-19 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3293 | LATER | SHANDONG JIRONG | SAU4005-G108-STA-&MLU-07716 | SHOP FABRICATED TANK (V)-ASSEMBLY DRAWING FOR CHEMICAL NEWITIVE TANK | G108 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SHOP FABRICATED TANK | IFI | IFC | [14 empty] | 2026-03-30 |  | 2026-04-19 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3294 | LATER | SHANDONG JIRONG | SAU4005-G108-STA-&MLU-07717 | SHOP FABRICATED TANK (V)-ASSEMBLY DRAWING FOR POTABLE WATER STORAGE TANK | G108 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SHOP FABRICATED TANK | IFI | IFC | [14 empty] | 2026-03-30 |  | 2026-05-07 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3295 | LATER | SHANDONG JIRONG | SAU4005-G108-STA-&MLU-07718 | SHOP FABRICATED TANK (V)-ASSEMBLY DRAWING FOR POTABLE WATER OVERHEAD TANK | G108 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SHOP FABRICATED TANK | IFI | IFC | [14 empty] | 2026-03-30 |  | 2026-05-07 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3296 | LATER | SHANDONG JIRONG | SAU4005-G108-STA-&MLU-07719 | SHOP FABRICATED TANK (V)-ASSEMBLY DRAWING FOR FOPH FUELOIL DRAIN TANK | G108 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SHOP FABRICATED TANK | IFI | IFC | [14 empty] | 2026-03-30 |  | 2026-05-07 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3297 | LATER | SHANDONG JIRONG | SAU4005-G108-STA-&MLU-07720 | SHOP FABRICATED TANK (V)-ASSEMBLY DRAWING FOR PULSE AIR ACCUMULATOR | G108 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SHOP FABRICATED TANK | IFI | IFC | [14 empty] | 2026-03-30 |  | 2026-04-19 | [17 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3299 | LATER | SHANDONG JIRONG | SAU4005-G108-STA-&MDC-07722 | SHOP FABRICATED TANK (V)-O&M MANUAL FOR SHOP FABRICATED TANK | G108 | Operation & Maintenacne | B-Overall technology | YES | O&M | Mechanical | SEPCOIII | SHOP FABRICATED TANK | IFI | IFD | [14 empty] | 2026-03-30 | [19 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3300 | LATER | SHANDONG JIRONG | SAU4005-G108-STA-&MQC-07723 | SHOP FABRICATED TANK (V)-END OF MANUFACTURING RECORD FOR SHOP FABRICATED TANK | G108 | QA/QC | A-Overall management | YES | QA/QC | General | SEPCOIII | SHOP FABRICATED TANK | IFA | IFD |  |  | 2026-05-30 |  |  |  | 2026-06-19 |  |  |  | 2026-07-25 | [23 empty] | DE |  | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3301 | LATER | SPEC | SAU4005-G112-QC_-&MDA-08401 | Chemical Feed System(V)-Datasheet for chemical dosing system | G112 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Chemical Feed System | IFA | IFD |  |  | 2025-12-21 |  | 2025-10-21 |  | 2026-01-10 |  | 2025-11-06 |  | 2026-02-15 |  | 2025-11-20 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3302 | LATER | SPEC | SAU4005-G112-QC_-&MFB-08402 | Chemical Feed System(V)-PI&D Drawing for chemical dosing system | G112 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Chemical Feed System | IFA | IFD |  |  | 2025-11-22 |  | 2025-10-07 |  | 2025-12-12 |  | 2025-10-30 |  | 2026-01-17 |  | 2026-04-05 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3303 | LATER | SPEC | SAU4005-G112-QC_-&MTL-08403 | Chemical Feed System(V)-General Arrange Drawing for chemical dosing system | G112 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Chemical Feed System | IFA | IFD |  |  | 2025-11-22 |  | 2025-10-13 |  | 2025-12-12 |  | 0 |  | 2026-01-17 |  | 2025-11-04 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3304 | LATER | SPEC | SAU4005-G112-QC_-&EDA-08404 | Chemical Feed System(V)-Electrical loads list for Chemical Dosing System | G112 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2025-11-22 |  | 2025-10-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3305 | LATER | SPEC | SAU4005-G112-QC_-&EFP-08405 | Chemical Feed System(V)-IO List for chemical dosing system | G112 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | I&C&DCS | Electrical | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2025-12-07 |  | 2025-10-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3306 | LATER | SPEC | SAU4005-G112-QC_-&ELU-08406 | Chemical Feed System(V)-Control panel Drawings for chemical dosing system | G112 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2025-12-21 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3307 | LATER | SPEC | SAU4005-G112-QC_-&MTB-08407 | Chemical Feed System(V)-3D Model for chemical dosing system | G112 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2026-01-24 |  | 2026-02-02 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3308 | LATER | SPEC | SAU4005-G112-QC_-&MEC-08408 | Chemical Feed System(V)-Factory inspection and Test Procedure for chemical dosing system | G112 | QA/QC | A-Overall management | NO | QA/QC | General | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2025-12-21 |  | 2025-11-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3309 | LATER | SPEC | SAU4005-G112-QC_-&MPB-08409 | Chemical Feed System(V)-Nameplate Drawing for chemical dosing system | G112 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2025-12-21 |  | 2025-10-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3310 | LATER | SPEC | SAU4005-G112-QC_-&MDC-08410 | Chemical Feed System(V)-O&M Manua for chemical dosing system | G112 | Operation & Maintenacne | B-Overall technology | NO | GENERAL | General | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2026-04-08 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3311 | LATER | SPEC | SAU4005-G112-QC_-&MDA-08411 | Chemical Feed System(V)-Manufacturer Data Book for chemical dosing system | G112 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2025-12-21 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3312 | LATER | SPEC | SAU4005-G112-QC_-&MPB-08412 | Chemical Feed System(V)-Spares and special tool list for chemical dosing system | G112 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2025-12-21 |  | 2026-04-06 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3313 | LATER | SPEC | SAU4005-G112-QC_-&EEC-08413 | Chemical Feed System(V)-Instrument list for chemical dosing system | G112 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | I&C&DCS | Instrumentation and Control | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2025-12-07 |  | 2025-10-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3314 | LATER | SPEC | SAU4005-G112-QC_-&EDA-08414 | Chemical Feed System(V)-Instrument Datasheet &drawing for chemical dosing system | G112 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | I&C&DCS | Instrumentation and Control | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2025-12-21 |  | 2026-03-02 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3315 | LATER | SPEC | SAU4005-G112-QC_-&EFF-08415 | Chemical Feed System(V)-Control logic diagram for chemical dosing system | G112 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | I&C&DCS | Instrumentation and Control | SEPCOIII | Chemical Feed System | IFA | IFD |  |  | 2025-12-21 |  | 2025-11-28 |  | 2026-01-10 |  | 2025-12-09 |  | 2026-02-15 |  | 2026-05-10 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3316 | LATER | SPEC | SAU4005-G112-QC_-&MPB-08416 | Chemical Feed System(V)-Valves List for chemical dosing system | G112 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2025-12-07 |  | 2025-10-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3317 | LATER | SPEC | SAU4005-G112-QC_-&EEC-08417 | Chemical Feed System(V)-Motor datasheet & curves for chemical dosing system | G112 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Electrical | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2025-11-14 |  | 2025-10-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3318 | LATER | SPEC | SAU4005-G112-QC_-&BDB-08418 | Chemical Feed System(V)-System Functional Description for Chemical Dosing System | G112 | Engineering | B-Overall technology | NO | GENERAL | General | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2026-02-11 |  | 2026-03-27 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| dcc changed | 3319 | LATER | SPEC | SAU4005-G112-QC_-&AQA-08419 | Chemical Feed System(V)-Painting Scheme for chemical dosing system | G112 | Construction | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2025-12-21 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3320 | LATER | SPEC | SAU4005-G112-QC_-&BEC-08421 | Chemical Feed System(V)-Inspection and Test Plan for chemical dosing system | G112 | QA/QC | A-Overall management | NO | QA/QC | General | SEPCOIII | Chemical Feed System | IFA | IFD |  |  | 2025-12-21 |  | 2025-10-15 |  | 2026-01-10 |  | 2025-10-23 |  | 2026-02-15 |  | 2025-12-30 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3321 | LATER | SPEC | SAU4005-G112-QC_-&BDA-08422 | Chemical Feed System(V)-Utility consumption list for chemical dosing system | G112 | Operation & Maintenacne | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2025-12-21 |  | 2026-03-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3322 | LATER | SPEC | SAU4005-G112-QC_-&BPB-08423 | Chemical Feed System(V)-Equipment list for chemical dosing system | G112 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2026-01-24 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3323 | LATER | SPEC | SAU4005-G112-QC_-&BPA-08424 | Chemical Feed System(V)-Consumable and lubricant list for chemical dosing system | G112 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2025-12-21 |  | 2026-04-10 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3324 | LATER | SPEC | SAU4005-G112-QC_-&MLB-08425 | Chemical Feed System(V)-Foundation and Loading drawing for chemical dosing system | G112 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2025-11-22 |  | 2025-10-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3325 | LATER | SPEC | SAU4005-G112-QC_-&EFS-08426 | Chemical Feed System(V)-Single Line diagram for chemical dosing system | G112 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Chemical Feed System | IFA | IFD |  |  | 2025-11-22 |  | 2025-10-29 |  | 2025-12-12 |  | 2025-10-29 |  | 2026-01-17 |  | 2025-12-09 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3326 | LATER | SPEC | SAU4005-G112-QC_-&MLD-08427 | Chemical Feed System(V)-Grounding and Lightning Drawing for chemical dosing system | G112 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2025-12-21 |  | 2026-01-15 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3327 | LATER | SPEC | SAU4005-G112-QC_-&MMB-08428 | Chemical Feed System(V)-Cable list for chemical dosing system | G112 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2026-01-24 |  | 2026-02-09 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3328 | LATER | SPEC | SAU4005-G112-QC_-&MLU-08429 | Chemical Feed System(V)-Lighting Drawing for chemical dosing system | G112 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2026-01-24 |  | 2026-02-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3329 | LATER | SPEC | SAU4005-G112-QC_-&MMA-08430 | Chemical Feed System(V)-Terminal Point List for chemical dosing system | G112 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2025-11-22 |  | 2025-10-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3330 | LATER | SPEC | SAU4005-G112-QC_-&MMB-08431 | Chemical Feed System(V)-Pipeline List for chemical dosing system | G112 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2025-12-07 |  | 2025-10-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3331 | LATER | SPEC | SAU4005-G112-QC_-&MLU-08432 | Chemical Feed System(V)-Motor ,MOV General Arrange Dra for chemical dosing system | G112 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2026-01-24 |  | 2026-02-06 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3332 | LATER | SPEC | SAU4005-G112-QC_-&EMB-08433 | Chemical Feed System(V)-Cable raceway layout for chemical dosing system | G112 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2025-12-07 |  | 2025-10-23 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3333 | LATER | SPEC | SAU4005-G112-QC_-&EFP-08434 | Chemical Feed System(V)-DCS Interface I/O list for chemical dosing system | G112 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2025-12-07 |  | 2025-10-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3334 | LATER | SPEC | SAU4005-G112-QC_-&MPA-08435 | Chemical Feed System(V)-Chemical and consumable list of chemical dosing system | G112 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2025-12-21 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3335 | LATER | SPEC | SAU4005-G112-QC_-&MPA-08436 | Chemical Feed System(V)-Specialty list of chemical dosing system | G112 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2026-01-03 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3336 | LATER | SPEC | SAU4005-G112-QC_-&MWT-08437 | Chemical Feed System(V)-Chemical cleaning procedures and recommendations, waste water quality etc.of chemical dosing system | G112 | Engineering | A-Overall management | NO | QA/QC | General | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2026-01-03 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3337 | LATER | SPEC | SAU4005-G112-QC_-&MQC-08438 | Chemical Feed System(V)-Hydrotest certificate of chemical dosing system | G112 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Process | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2026-04-01 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3338 | LATER | SPEC | SAU4005-G112-QC_-&MBB-08439 | Chemical Feed System(V)-End of Manufacturing Report of chemical dosing system | G112 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Process | SEPCOIII | Chemical Feed System | IFI | IFD | [14 empty] | 2026-05-15 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
i | NEW | 3339 | LATER | SPEC | SAU4005-G181-QU_-&MDA-25201 | SWAS(V)-Datasheet for sampling system | G181 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SWAS | IFA | IFD |  |  | 2025-12-21 |  | 2025-10-18 |  | 2026-01-10 |  | 2025-12-21 |  | 2026-02-15 |  | 2026-01-22 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3340 | LATER | SPEC | SAU4005-G181-QU_-&MFB-25202 | SWAS(V)-PI&D Drawing for sampling system | G181 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SWAS | IFA | IFD |  |  | 2025-11-22 |  | 2025-09-25 |  | 2025-12-12 |  | 2025-11-02 |  | 2026-01-17 |  | 2026-03-15 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3341 | LATER | SPEC | SAU4005-G181-QU_-&MTL-25203 | SWAS(V)-General Arrange Drawing for sampling system | G181 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SWAS | IFA | IFD |  |  | 2025-11-22 |  | 2025-09-25 |  | 2025-12-12 |  | 2025-11-02 |  | 2026-01-17 |  | 2026-01-21 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3342 | LATER | SPEC | SAU4005-G181-QU_-&EDA-25204 | SWAS(V)-Electrical loads list for sampling system | G181 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2025-11-22 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3343 | LATER | SPEC | SAU4005-G181-QU_-&EFP-25205 | SWAS(V)-IO List for sampling system | G181 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | I&C&DCS | Electrical | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2025-12-07 |  | 2025-10-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3344 | LATER | SPEC | SAU4005-G181-QU_-&ELU-25206 | SWAS(V)-Control panel Drawings for sampling system | G181 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2025-12-21 |  | 2026-01-15 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3345 | LATER | SPEC | SAU4005-G181-QU_-&MTB-25207 | SWAS(V)-3D Model for sampling system | G181 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2026-01-24 |  | 2026-02-02 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3346 | LATER | SPEC | SAU4005-G181-QU_-&MEC-25208 | SWAS(V)-Factory inspection and Test Procedure for sampling system | G181 | QA/QC | A-Overall management | NO | QA/QC | General | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2025-12-21 |  | 2025-11-17 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3347 | LATER | SPEC | SAU4005-G181-QU_-&MPB-25209 | SWAS(V)-Nameplate Drawing for sampling system | G181 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2025-12-21 |  | 2025-10-10 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3348 | LATER | SPEC | SAU4005-G181-QU_-&MDC-25210 | SWAS(V)-O&M Manua for sampling system | G181 | Operation & Maintenacne | B-Overall technology | NO | GENERAL | General | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2026-04-08 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3349 | LATER | SPEC | SAU4005-G181-QU_-&MDA-25211 | SWAS(V)-Manufacturer Data Book for sampling system | G181 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2025-12-21 |  | 2025-12-31 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3350 | LATER | SPEC | SAU4005-G181-QU_-&MPB-25212 | SWAS(V)-Spares and special tool list for sampling system | G181 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2025-12-21 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3351 | LATER | SPEC | SAU4005-G181-QU_-&EEC-25213 | SWAS(V)-Instrument list for sampling system | G181 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | I&C&DCS | Instrumentation and Control | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2025-12-07 |  | 2025-10-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3352 | LATER | SPEC | SAU4005-G181-QU_-&EDA-25214 | SWAS(V)-Instrument Datasheet &drawing for sampling system | G181 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | I&C&DCS | Instrumentation and Control | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2025-12-21 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3353 | LATER | SPEC | SAU4005-G181-QU_-&EFF-25215 | SWAS(V)-Control logic diagram for sampling system | G181 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | I&C&DCS | Instrumentation and Control | SEPCOIII | SWAS | IFA | IFD |  |  | 2025-12-21 |  | 2026-01-01 |  | 2026-01-10 |  | 2025-11-02 |  | 2026-02-15 |  | 2026-04-13 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3354 | LATER | SPEC | SAU4005-G181-QU_-&MPB-25216 | SWAS(V)-Valves List for sampling system | G181 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2025-12-07 |  | 2025-10-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| dcc changed | 3355 | LATER | SPEC | SAU4005-G181-QU_-&EDA-25217 | SWAS(V)-Motor datasheet & curves for sampling system | G181 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Electrical | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2026-01-24 |  | 2026-04-01 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3356 | LATER | SPEC | SAU4005-G181-QU_-&BDB-25218 | SWAS(V)-System Functional Description for sampling system | G181 | Engineering | B-Overall technology | NO | GENERAL | General | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2026-04-08 |  | 2026-04-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| dcc changed | 3357 | LATER | SPEC | SAU4005-G181-QU_-&AQA-25219 | SWAS(V)-Painting Scheme for sampling system | G181 | Construction | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2025-12-21 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3358 | LATER | SPEC | SAU4005-G181-QU_-&BEC-25221 | SWAS(V)-Inspection and Test Plan for sampling system | G181 | QA/QC | A-Overall management | NO | QA/QC | General | SEPCOIII | SWAS | IFA | IFD |  |  | 2025-12-21 |  | 2025-10-14 |  | 2026-01-10 |  | 2025-12-14 |  | 2026-02-15 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3359 | LATER | SPEC | SAU4005-G181-QU_-&BDA-25222 | SWAS(V)-Utility consumption list for sampling system | G181 | Operation & Maintenacne | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2025-12-21 |  | 2025-10-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3360 | LATER | SPEC | SAU4005-G181-QU_-&BPB-25223 | SWAS(V)-Equipment list for sampling system | G181 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2026-01-24 |  | 2025-12-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3361 | LATER | SPEC | SAU4005-G181-QU_-&BPA-25224 | SWAS(V)-Consumable and lubricant list for sampling system | G181 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2025-12-21 |  | 2025-11-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3362 | LATER | SPEC | SAU4005-G181-QU_-&MLB-25225 | SWAS(V)-Foundation and Loading drawing for sampling system | G181 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2025-11-22 |  | 2025-09-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3363 | LATER | SPEC | SAU4005-G181-QU_-&EFS-25226 | SWAS(V)-Single Line diagram for sampling system | G181 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | SWAS | IFA | IFD |  |  | 2025-11-22 |  | 2025-09-26 |  | 2025-12-12 |  | 2025-10-05 |  | 2026-01-17 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3364 | LATER | SPEC | SAU4005-G181-QU_-&MLD-25227 | SWAS(V)-Grounding and Lightning Drawing for sampling system | G181 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2025-12-21 |  | 2026-01-15 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3365 | LATER | SPEC | SAU4005-G181-QU_-&MMB-25228 | SWAS(V)-Cable list for sampling system | G181 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2026-01-24 |  | 2026-02-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3366 | LATER | SPEC | SAU4005-G181-QU_-&MLU-25229 | SWAS(V)-Lighting Drawing for sampling system | G181 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2026-01-24 |  | 2026-02-02 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3367 | LATER | SPEC | SAU4005-G181-QU_-&MMA-25230 | SWAS(V)-Terminal Point List for sampling system | G181 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2025-11-22 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3368 | LATER | SPEC | SAU4005-G181-QU_-&MMB-25231 | SWAS(V)-Pipeline List for sampling system | G181 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2025-12-07 |  | 2025-10-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3369 | LATER | SPEC | SAU4005-G181-QU_-&MLU-25233 | SWAS(V)-Motor ,MOV General Arrange Dra for sampling system | G181 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2026-01-24 |  | 2026-03-23 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3370 | LATER | SPEC | SAU4005-G181-QU_-&EMB-25234 | SWAS(V)-Cable raceway layout for sampling system | G181 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2025-12-07 |  | 2025-10-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3371 | LATER | SPEC | SAU4005-G181-QU_-&MPA-25236 | SWAS(V)-Chemical and consumable list of sampling system | G181 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2025-12-21 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3372 | LATER | SPEC | SAU4005-G181-QU_-&MPA-25237 | SWAS(V)-Specialty list of sampling system | G181 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2025-11-03 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3373 | LATER | SPEC | SAU4005-G181-QU_-&MWT-25238 | SWAS(V)-Chemical cleaning procedures and recommendations, waste water quality etc.of sampling system | G181 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2026-01-03 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3374 | LATER | SPEC | SAU4005-G181-QU_-&MQC-25239 | SWAS(V)-Hydrotest certificate of sampling system | G181 | Engineering | B-Overall technology | NO | QA/QC | General | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2026-05-02 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3375 | LATER | SPEC | SAU4005-G181-QU_-&MED-25240 | SWAS(V)-Chiller Capacity Calculation / Cooling Water Calculation Sheet of sampling system | G181 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Process | SEPCOIII | SWAS | IFA | IFD |  |  | 2025-12-21 |  | 2025-11-13 |  | 2026-01-10 |  | 2025-11-27 |  | 2026-02-15 |  | 2026-02-01 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3376 | LATER | SPEC | SAU4005-G181-QU_-&MFE-25241 | SWAS(V)-Chiller drawings related document of sampling system | G181 | Engineering | B-Overall technology | NO | GENERAL | General | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2025-12-07 |  | 2025-10-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW | 3377 | LATER | SPEC | SAU4005-G181-QU_-&MTL-25242 | SWAS(V)-Isntallation Drawing of sampling system | G181 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2025-12-21 |  | 2025-12-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA |  | YES | YES
| NEW ADDED | 3378 | LATER | SPEC | SAU4005-G181-QU_-&MBB-25243 | SWAS(V)-End of Manufacturing Report of sampling system | G181 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | SWAS | IFI | IFD | [14 empty] | 2026-05-15 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| PURPOSE CHANGED | 3379 | LATER | PENTAX | SAU4005-G121-GAF-&BDA-10200 | Miscellaneous Sump Pumps(V)-MDL | G121 | Project Management |  | YES | GENERAL | General | SEPCOIII | Miscellaneous Sump Pumps | IFA | IFD |  |  | 2026-01-20 |  |  |  | 2026-02-10 |  |  |  | 2026-03-16 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3380 | LATER | PENTAX | SAU4005-G121-GAF-&MDA-10201 | Miscellaneous Sump Pumps(V))-Pump GA drawing | G121 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Miscellaneous Sump Pumps | IFA | IFD |  |  | 2026-01-24 |  | 2026-03-04 |  | 2026-02-13 |  | 2026-03-29 |  | 2026-03-21 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3381 | LATER | PENTAX | SAU4005-G121-GAF-&EDA-10202 | Miscellaneous Sump Pumps(V))-Motor GA drawing | G121 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Miscellaneous Sump Pumps | IFA | IFD |  |  | 2026-01-30 |  | 2026-03-29 |  | 2026-02-19 |  | 2026-04-15 |  | 2026-03-27 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3382 | LATER | PENTAX | SAU4005-G121-GAF-&MDA-10203 | Miscellaneous Sump Pumps(V))-Pump performance curve & Miscellaneous Sump Pumps(V)- Pump Datasheet | G121 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Miscellaneous Sump Pumps | IFA | IFD |  |  | 2026-01-27 |  | 2026-03-24 |  | 2026-02-16 |  | 2026-04-15 |  | 2026-03-24 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3383 | LATER | PENTAX | SAU4005-G121-GAF-&MDA-10204 | Miscellaneous Sump Pumps(V))-Nameplate drawing | G121 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Miscellaneous Sump Pumps | IFA | IFD |  |  | 2026-02-28 |  | 2026-04-29 |  | 2026-03-20 |  | 2026-05-17 |  | 2026-04-25 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3384 | LATER | PENTAX | SAU4005-G121-GAF-&MPB-10205 | Miscellaneous Sump Pumps(V))-Pump Cross-sectional drawings and bill of materials | G121 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Miscellaneous Sump Pumps | IFI | IFD | [14 empty] | 2026-02-28 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3385 | LATER | PENTAX | SAU4005-G121-GAF-&MDA-10206 | Miscellaneous Sump Pumps(V))-Pump Shaft seal and coupling drawings | G121 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Miscellaneous Sump Pumps | IFI | IFD | [14 empty] | 2026-02-28 |  | 2026-03-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3386 | LATER | PENTAX | SAU4005-G121-GAF-&EDA-10207 | Miscellaneous Sump Pumps(V))-Motor Data sheet, Performance curve | G121 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Miscellaneous Sump Pumps | IFA | IFD |  |  | 2026-02-07 |  | 2026-04-08 |  | 2026-02-27 |  | 2026-04-15 |  | 2026-04-04 |  | 2026-05-12 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3387 | LATER | PENTAX | SAU4005-G121-GAF-&EEC-10208 | Miscellaneous Sump Pumps(V))-Electrical Load List | G121 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Miscellaneous Sump Pumps | IFA | IFD |  |  | 2026-01-27 |  | 2026-03-13 |  | 2026-02-16 |  | 0 |  | 2026-03-24 |  | 2026-03-29 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3388 | LATER | PENTAX | SAU4005-G121-GAF-&EFP-10209 | Miscellaneous Sump Pumps(V))-DCS IO List | G121 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Miscellaneous Sump Pumps | IFA | IFD |  |  | 2026-02-07 |  | 2026-03-29 |  | 2026-02-27 |  | 0 |  | 2026-04-04 |  | 2026-04-28 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3389 | LATER | PENTAX | SAU4005-G121-GAF-&APB-10210 | Miscellaneous Sump Pumps(V))-Spare parts list ( commissioning and 2 years operation and special tool list ) | G121 | Engineering |  | YES | GENERAL | General | SEPCOIII | Miscellaneous Sump Pumps | IFI | IFD | [14 empty] | 2026-03-10 |  | 2026-03-13 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3390 | LATER | PENTAX | SAU4005-G121-GAF-&APB-10211 | Miscellaneous Sump Pumps(V))-Lubricants list First Fill details | G121 | Engineering |  | YES | GENERAL | General | SEPCOIII | Miscellaneous Sump Pumps | IFI | IFD | [14 empty] | 2026-03-10 |  | 2026-03-13 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3391 | LATER | PENTAX | SAU4005-G121-GAF-&APB-10212 | Miscellaneous Sump Pumps(V))-Chemicals Consumables list | G121 | Engineering |  | YES | GENERAL | General | SEPCOIII | Miscellaneous Sump Pumps | IFI | IFD | [14 empty] | 2026-03-10 |  | 2026-03-13 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3392 | LATER | PENTAX | SAU4005-G121-GAF-&MDC-10213 | Miscellaneous Sump Pumps(V))-OM and start up commissioning manuals of pumps | G121 | Operation & Maintenacne | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Miscellaneous Sump Pumps | IFI | IFD | [14 empty] | 2026-05-10 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| SUBMISSION PLAN CHANGED | 3393 | LATER | PENTAX | SAU4005-G121-GAF-&EDC-10214 | Miscellaneous Sump Pumps(V))-OM and start up commissioning manuals of motors | G121 | Operation & Maintenacne | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Miscellaneous Sump Pumps | IFI | IFD | [14 empty] | 2026-08-14 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| dcc changed | 3394 | LATER | PENTAX | SAU4005-G121-GAF-&AQA-10215 | Miscellaneous Sump Pumps(V))-Surface preparation & coating Procedure | G121 | Engineering |  | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Miscellaneous Sump Pumps | IFA | IFD |  |  | 2026-03-10 |  |  |  | 2026-03-30 |  |  |  | 2026-05-05 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3395 | LATER | PENTAX | SAU4005-G121-GAF-&EEC-10216 | Miscellaneous Sump Pumps(V))-Instrument list & Datasheet | G121 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Miscellaneous Sump Pumps | IFI | IFD | [14 empty] | 2026-03-10 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3396 | LATER | PENTAX | SAU4005-G121-GAF-&ELD-10217 | Miscellaneous Sump Pumps(V))-Instrument hook-up drawing | G121 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Miscellaneous Sump Pumps | IFI | IFD | [14 empty] | 2026-04-10 |  | 2026-04-08 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3397 | LATER | PENTAX | SAU4005-G121-GAF-&AQA-10218 | Miscellaneous Sump Pumps(V))-ITP (Factory Inspection and Test Plan) | G121 | QA/QC |  | YES | QA/QC | General | SEPCOIII | Miscellaneous Sump Pumps | IFA | IFD |  |  | 2026-05-10 |  | 2026-03-20 |  | 2026-05-30 |  | 2026-05-04 |  | 2026-07-05 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3398 | LATER | PENTAX | SAU4005-G121-GAF-&AQA-10219 | Miscellaneous Sump Pumps(V))-Test procedure | G121 | QA/QC |  | YES | QA/QC | General | SEPCOIII | Miscellaneous Sump Pumps | IFA | IFD |  |  | 2026-05-10 |  | 2026-03-20 |  | 2026-05-30 |  | 0 |  | 2026-07-05 |  | 2026-04-19 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3399 | LATER | PENTAX | SAU4005-G121-GAF-&AQA-10220 | Miscellaneous Sump Pumps(V))-Type test reports/as-built information | G121 | QA/QC |  | YES | QA/QC | General | SEPCOIII | Miscellaneous Sump Pumps | IFI | IFD | [14 empty] | 2026-05-10 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3400 | LATER | PENTAX | SAU4005-G121-GAF-&EFS-10221 | Miscellaneous Sump Pumps(V))-Local control panel Schematic and terminal Diagram | G121 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Miscellaneous Sump Pumps | IFI | IFD | [14 empty] | 2026-02-28 |  | 2026-03-13 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3401 | LATER | PENTAX | SAU4005-G121-GAF-&EDA-10222 | Miscellaneous Sump Pumps(V))-Local control panel GA drawing | G121 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Miscellaneous Sump Pumps | IFI | IFD | [14 empty] | 2026-02-28 |  | 2026-03-13 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| SUBMISSION PLAN CHANGED | 3402 | LATER | PENTAX | SAU4005-G121-GAF-&EFS-10223 | Miscellaneous Sump Pumps(V))-Electrical Schematic Diagram (SLD) | G121 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Miscellaneous Sump Pumps | IFA | IFD |  |  | 2026-08-14 |  |  |  | 2026-09-03 |  |  |  | 2026-10-09 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| SUBMISSION PLAN CHANGED | 3403 | LATER | PENTAX | SAU4005-G121-GAF-&EPC-10224 | Miscellaneous Sump Pumps(V))-Final Bill of Quantity (BOQ) for Electrical Items | G121 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Miscellaneous Sump Pumps | IFI | IFD | [14 empty] | 2026-08-14 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3404 | LATER | PENTAX | SAU4005-G121-GAF-&EFB-10225 | Miscellaneous Sump Pumps(V))-P&I Diagram | G121 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Miscellaneous Sump Pumps | IFI | IFD | [14 empty] | 2026-03-10 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3405 | LATER | PENTAX | SAU4005-G121-GAF-&MDC-10226 | Miscellaneous Sump Pumps(V))-Noise Datasheets / guarantees | G121 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Miscellaneous Sump Pumps | IFI | IFD | [14 empty] | 2026-03-10 |  | 2026-03-13 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3406 | LATER | PENTAX | SAU4005-G121-GAF-&APC-10227 | Miscellaneous Sump Pumps(V))-Packing List of the Proposed Equipment | G121 | Logistics | M-Mechanical engineering (normally including process engineering) | YES | O&M | General | SEPCOIII | Miscellaneous Sump Pumps | IFI | IFD | [14 empty] | 2026-03-10 |  | 2026-03-13 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3407 | LATER | BAOCHENG | SAU4005-G123-ZEN-&MBC-10400 | Piping Specialties(V)-VDL | G123 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Piping Specialties | IFI | IFD | [14 empty] | 2026-02-21 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3408 | LATER | BAOCHENG | SAU4005-G123-ZEN-&MBC-10401 | Piping Specialties(V)-Sight Flow Glass GA Drawings | G123 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Piping Specialties | IFA | IFD |  |  | 2026-02-21 |  |  |  | 2026-03-13 |  |  |  | 2026-04-20 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3409 | LATER | BAOCHENG | SAU4005-G123-ZEN-&MBC-10402 | Piping Specialties(V)-Accumulator Tank GA Drawings | G123 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Piping Specialties | IFA | IFD |  |  | 2026-02-21 |  |  |  | 2026-03-13 |  |  |  | 2026-04-20 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3410 | LATER | BAOCHENG | SAU4005-G123-ZEN-&MBC-10403 | Piping Specialties(V)-Spectacle Flange GA Drawings | G123 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Piping Specialties | IFA | IFD |  |  | 2026-02-21 |  |  |  | 2026-03-13 |  |  |  | 2026-04-20 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3411 | LATER | BAOCHENG | SAU4005-G123-ZEN-&MBC-10404 | Piping Specialties(V)-Insulation Gasket Kit GA Drawings | G123 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Piping Specialties | IFA | IFD |  |  | 2026-02-21 |  |  |  | 2026-03-13 |  |  |  | 2026-04-20 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3412 | LATER | BAOCHENG | SAU4005-G123-ZEN-&MLU-10405 | Piping Specialties(V)-Trap Assembly GA Drawings | G123 | QA/QC | M-Mechanical engineering (normally including process engineering) | NO | QA/QC | GENERAL | SEPCOIII | Piping Specialties | IFI | [15 empty] | 2026-01-25 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3413 | LATER | BAOCHENG | SAU4005-G123-ZEN-&MLU-10406 | Piping Specialties(V)-EWSS GA Drawings | G123 | QA/QC | M-Mechanical engineering (normally including process engineering) | NO | QA/QC | GENERAL | SEPCOIII | Piping Specialties | IFI | [15 empty] | 2026-01-25 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3414 | LATER | BAOCHENG | SAU4005-G123-ZEN-&MLU-10407 | Piping Specialties(V)-Accumulator Tank GA Drawings | G123 | QA/QC | M-Mechanical engineering (normally including process engineering) | NO | QA/QC | GENERAL | SEPCOIII | Piping Specialties | IFI | [15 empty] | 2026-01-25 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3415 | LATER | BAOCHENG | SAU4005-G123-ZEN-&MLU-10408 | Piping Specialties(V)-Strainer GA Drawings | G123 | QA/QC | M-Mechanical engineering (normally including process engineering) | NO | QA/QC | GENERAL | SEPCOIII | Piping Specialties | IFI | [15 empty] | 2026-01-25 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3416 | LATER | BAOCHENG | SAU4005-G123-ZEN-&MLU-10409 | Piping Specialties(V)-Expansion Joint GA Drawings | G123 | QA/QC | M-Mechanical engineering (normally including process engineering) | NO | QA/QC | GENERAL | SEPCOIII | Piping Specialties | IFI | [15 empty] | 2026-01-25 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3417 | LATER | BAOCHENG | SAU4005-G123-ZEN-&MQA-10410 | Piping Specialties(V)-Inspection & Test Plan (ITP) | G123 | QA/QC | M-Mechanical engineering (normally including process engineering) | NO | QA/QC | GENERAL | SEPCOIII | Piping Specialties | IFA | [15 empty] | 2026-01-25 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3418 | LATER | DIAMOND | SAU4005-G123-ZEN-&MLU-10415 | Piping Specialties(V)-Flame arrestor GA Drawings | G123 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Piping Specialties | IFI | IFP | [14 empty] | 2026-07-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3419 | LATER | DIAMOND | SAU4005-G123-ZEN-&MLU-10416 | Piping Specialties(V)-Restriction Oriface GA Drawings | G123 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Piping Specialties | IFI | IFP | [14 empty] | 2026-07-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3420 | LATER | DIAMOND | SAU4005-G123-ZEN-&MLU-10417 | Piping Specialties(V)-Self-Regulating Valve GA Drawings | G123 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Piping Specialties | IFI | IFP | [14 empty] | 2026-07-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3421 | LATER | DIAMOND | SAU4005-G123-ZEN-&MLU-10418 | Piping Specialties(V)-Flexible Hose GA Drawings | G123 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Piping Specialties | IFI | IFP | [14 empty] | 2026-07-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3422 | LATER | LIANG GU | SAU4005-G127-ZEN-&MAB-11100 | Safety valve- MDL | G127 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Safety Valve | IFI | IFP | [14 empty] | 2026-01-07 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3423 | LATER | LIANG GU | SAU4005-G127-ZEN-&MLU-11101 | Safety valve- GA Drawings | G127 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Safety Valve | IFI | IFP | [14 empty] | 2026-01-09 |  | 2026-04-09 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3424 | LATER | LIANG GU | SAU4005-G127-ZEN-&MQA-11102 | Safety valve - Inspection & Test Plan (ITP) | G127 | QA/QC | M-Mechanical engineering (normally including process engineering) | NO | QA/QC | General | SEPCOIII | Safety Valve | IFA | IFP |  |  | 2026-01-14 |  |  |  | 2026-02-03 |  |  |  | 2026-03-11 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3425 | LATER | LIANG GU | SAU4005-G127-ZEN-&MQC-11103 | Safety valve- Testing Procedure | G127 | QA/QC | M-Mechanical engineering (normally including process engineering) | NO | QA/QC | General | SEPCOIII | Safety Valve | IFI | IFP | [14 empty] | 2026-04-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3426 | LATER | NANTONG | SAU4005-G129-ZEN-&MAB-11310 | Motor Operated Ball Valve & Globe Valve(V)- MDL | G129 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Motor Operated Ball Valve | IFI | IFP | [14 empty] | 2026-01-03 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3427 | LATER | NANTONG | SAU4005-G129-ZEN-&MLU-11311 | Motor Operated Ball Valve & Globe Valve(V)- GA Drawings | G129 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Motor Operated Ball Valve | IFI | IFP | [14 empty] | 2026-01-30 |  | 2026-01-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3428 | LATER | NANTONG | SAU4005-G129-ZEN-&MQA-11312 | Motor Operated Ball Valve & Globe Valve(V)- Inspection & Test Plan (ITP) | G129 | QA/QC | M-Mechanical engineering (normally including process engineering) | NO | QA/QC | General | SEPCOIII | Motor Operated Ball Valve | IFA | IFP |  |  | 2026-02-14 |  |  |  | 2026-03-06 |  |  |  | 2026-04-11 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3429 | LATER | NANTONG | SAU4005-G129-ZEN-&MQA-11313 | Motor Operated Ball Valve & Globe Valve(V)- Testing Procedure | G129 | QA/QC | M-Mechanical engineering (normally including process engineering) | NO | QA/QC | General | SEPCOIII | Motor Operated Ball Valve | IFI | IFP | [14 empty] | 2026-01-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3430 | LATER | NANTONG | SAU4005-G129-ZEN-&EDA-11314 | MO Ball & Globe Valve- Electrical Load List | G129 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Motor Operated Ball Valve | IFI | IFD | [14 empty] | 2026-02-28 |  | 2026-02-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3431 | LATER | NANTONG | SAU4005-G129-ZEN-&EDB-11315 | MO Ball & Globe Valve- Electrical Control & Schematic Drawings | G129 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Motor Operated Ball Valve | IFI | IFD | [14 empty] | 2026-02-28 |  | 2026-02-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3432 | LATER | NANTONG | SAU4005-G129-ZEN-&EDA-11316 | MO Ball & Globe Valve-Technical Datasheet For Actuator | G129 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Motor Operated Ball Valve | IFI | IFD | [14 empty] | 2026-02-28 |  | 2026-02-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3433 | LATER | NANTONG | SAU4005-G130-ZEN-&MAB-11410 | Motor Operated Butterfly Valve(V)- MDL | G130 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Butterfly Valve | IFI | IFP | [14 empty] | 2026-01-03 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3434 | LATER | NANTONG | SAU4005-G130-ZEN-&MLU-11411 | Motor Operated Butterfly Valve(V) - GA Drawings | G130 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Butterfly Valve | IFI | IFP | [14 empty] | 2026-01-30 |  | 2026-01-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3435 | LATER | NANTONG | SAU4005-G130-ZEN-&MQA-11412 | Butterfly Valve(V)- Inspection & Test Plan (ITP) | G130 | QA/QC | M-Mechanical engineering (normally including process engineering) | NO | QA/QC | General | SEPCOIII | Butterfly Valve | IFA | IFP |  |  | 2026-02-14 |  |  |  | 2026-03-06 |  |  |  | 2026-04-11 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3436 | LATER | NANTONG | SAU4005-G130-ZEN-&MQA-11413 | Butterfly Valve (V)- Testing Procedure | G130 | QA/QC | M-Mechanical engineering (normally including process engineering) | NO | QA/QC | General | SEPCOIII | Butterfly Valve | IFI | IFP | [14 empty] | 2026-01-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3437 | LATER | NANTONG | SAU4005-G130-ZEN-&EDA-11414 | MO Butterfly Valve- Electrical Load List | G130 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Butterfly Valve | IFI | IFD | [14 empty] | 2026-02-28 |  | 2026-02-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3438 | LATER | NANTONG | SAU4005-G130-ZEN-&EDB-11415 | MO Butterfly Valve-Electrical Control & Schematic Drawings | G130 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Butterfly Valve | IFI | IFD | [14 empty] | 2026-02-28 |  | 2026-02-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3439 | LATER | NANTONG | SAU4005-G130-ZEN-&EDA-11416 | MO Butterfly Valve-Technical Datasheet For Actuator | G130 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Butterfly Valve | IFI | IFD | [14 empty] | 2026-02-28 |  | 2026-02-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3440 | LATER | PETRA | SAU4005-G132-SA_-&MEC-11601 | PACKAGED A/C UNIT (V)- TECHNICAL SUBMITTAL OF Main Electrical & Control Building (1A, 1B, 5A) | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2026-01-03 |  | 2026-01-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3441 | LATER | PETRA | SAU4005-G132-SA_-&MEC-11602 | PACKAGED A/C UNIT (V)- TECHNICAL SUBMITTAL OF STG-Excitation System AVR Room (1C) | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2026-01-03 |  | 2026-01-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3442 | LATER | PETRA | SAU4005-G132-SA_-&MEC-11603 | PACKAGED A/C UNIT (V)- TECHNICAL SUBMITTAL OF Workshop & Storage Building (1D, 1E) | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2026-01-03 |  | 2026-01-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3443 | LATER | PETRA | SAU4005-G132-SA_-&MEC-11604 | PACKAGED A/C UNIT (V)- TECHNICAL SUBMITTAL OF Unit MV/LV Electrical SWGR Building-11,12 & 13 (1F) | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2026-01-03 |  | 2025-12-11 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3444 | LATER | PETRA | SAU4005-G132-SA_-&MEC-11605 | PACKAGED A/C UNIT (V)- TECHNICAL SUBMITTAL OF Fin Fan Cooler Electrical SWGR Building (1G) | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2026-01-03 |  | 2026-01-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3445 | LATER | PETRA | SAU4005-G132-SA_-&MEC-11606 | PACKAGED A/C UNIT (V)- TECHNICAL SUBMITTAL OF ACC Electrical SWGR Building-1 & 2 (1H) | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2026-01-05 |  | 2026-01-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3446 | LATER | PETRA | SAU4005-G132-SA_-&MEC-11607 | PACKAGED A/C UNIT (V)- TECHNICAL SUBMITTAL OF Fire Station Building (1I) | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2026-01-03 |  | 2026-01-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3447 | LATER | PETRA | SAU4005-G132-SA_-&MEC-11608 | PACKAGED A/C UNIT (V)- TECHNICAL SUBMITTAL OF STG & Auxiliary Boiler Electrical Building (1J) | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2026-01-03 |  | 2026-01-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3449 | LATER | PETRA | SAU4005-G132-SA_-&MEC-11610 | PACKAGED A/C UNIT (V)- TECHNICAL SUBMITTAL OF Admin Building (1L, 5B) | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2025-12-27 |  | 2026-01-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3450 | LATER | PETRA | SAU4005-G132-SA_-&MEC-11611 | PACKAGED A/C UNIT (V)- TECHNICAL SUBMITTAL OF GT Package MCC and Control Room-11, 12, 13 (1M) | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2026-01-03 |  | 2026-01-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3451 | LATER | PETRA | SAU4005-G132-SA_-&MEC-11612 | PACKAGED A/C UNIT (V)- TECHNICAL SUBMITTAL OF BOP Electrical SWGR Building (1N) | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2026-01-05 |  | 2026-01-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3452 | LATER | PETRA | SAU4005-G132-SA_-&MEC-11613 | PACKAGED A/C UNIT (V)- TECHNICAL SUBMITTAL OF Electrical SWGR Building for Fuel GAS Area (1O, 1P) | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2026-01-17 |  | 2026-03-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3453 | LATER | PETRA | SAU4005-G132-SA_-&MEC-11614 | PACKAGED A/C UNIT (V)- TECHNICAL SUBMITTAL OF Electrical SWGR Building for Water Treatment Area (1Q) | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2026-01-21 |  | 2026-01-23 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3454 | LATER | PETRA | SAU4005-G132-SA_-&MEC-11615 | PACKAGED A/C UNIT (V)- TECHNICAL SUBMITTAL OF Search Facility & Visitor Center (1R) | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2026-01-14 |  | 2026-01-23 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3455 | LATER | PETRA | SAU4005-G132-SA_-&MEC-11616 | PACKAGED A/C UNIT (V)- TECHNICAL SUBMITTAL OF Chemical Building for WTP & ETP - Lab & Office Area (1S) | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2026-01-14 |  | 2026-03-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3456 | LATER | PETRA | SAU4005-G132-SA_-&MEC-11617 | PACKAGED A/C UNIT (V)- TECHNICAL SUBMITTAL OF Hydrogen Generation Plant & Switchgear Building - Rectifying Room and Electrical & Control Room (1T) | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2026-01-03 |  | 2026-01-21 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3457 | LATER | PETRA | SAU4005-G132-SA_-&MEC-11618 | PACKAGED A/C UNIT (V)- TECHNICAL SUBMITTAL OF Security Control Center (1U) | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2026-01-19 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3458 | LATER | PETRA | SAU4005-G132-SA_-&MEC-11620 | HVAC SYSTEM (V)- TECHNICAL SUBMITTAL OF HEAT PUMP TYPE SPLIT AC UNIT | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2026-01-01 |  | 2026-03-09 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3459 | LATER | PETRA | SAU4005-G132-SA_-&MEC-11623 | HVAC SYSTEM (V)- TECHNICAL SUBMITTAL OF Potable Humidifier Unit (V) | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2026-01-09 |  | 2026-03-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3460 | LATER | PETRA | SAU4005-G132-SA_-&MEC-11625 | HVAC SYSTEM (V)- TECHNICAL SUBMITTAL OF ADMIN BUILDING (VRF) | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2026-01-19 |  | 2026-03-09 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3461 | LATER | PETRA | SAU4005-G132-SA_-&MEC-11626 | HVAC SYSTEM (V)- TECHNICAL SUBMITTAL OF Unit Heater | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2025-12-31 |  | 2026-03-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3462 | LATER | PETRA | SAU4005-G132-SA_-&MDB-11653 | HVAC SYSTEMS (V)- Name plate of (PACU / FANS / VRF / SAC) | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2025-12-27 |  | 2026-04-06 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3463 | LATER | PETRA | SAU4005-G132-SA_-&MDC-11654 | HVAC SYSTEMS (V)-INSTALLATION, OPERATION & MAINTENANCE MANUAL (PACU / FANS / VRF SYSTEM / SAC) | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2025-12-27 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| dcc changed | 3464 | LATER | PETRA | SAU4005-G132-SA_-&MFB-11655 | PACKAGED A/C UNIT (V)- REFRIGERANT CIRCUIT DIAGRAM | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2026-01-21 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3465 | LATER | PETRA | SAU4005-G132-SA_-&EPC-11656 | HVAC SYSTEMS (V)- Electrical load list (i.e. including PACKAGED A/C UNIT, Fans, Split AC unit(SAC), VRF system) | G132 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2026-01-26 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3466 | LATER | PETRA | SAU4005-G132-SA_-&EMB-11657 | HVAC SYSTEMS (V)- WIRING DIAGRAM and dimensional layout for electrical panels with cable entry details and grouping details | G132 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2026-01-22 |  | 2026-04-06 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3467 | LATER | PETRA | SAU4005-G132-SA_-&EFA-11658 | HVAC SYSTEMS (V)- Single Line Diagram | G132 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | HVAC System | IFA | IFC |  |  | 2026-01-17 |  | 2026-04-09 |  | 2026-02-06 |  | 2026-04-19 |  | 2026-03-14 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3471 | LATER | PETRA | SAU4005-G000-SA_-&CQA-11662 | HVAC SYSTEMS (V)- Inspection & Test Plan (ITP) | G000 | ENGINEERING | C-Construction engineering (building construction and civil engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFA | IFC |  |  | 2025-12-27 |  | 2026-01-12 |  | 2026-01-16 |  | 2026-02-09 |  | 2026-02-21 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3472 | LATER | PETRA | SAU4005-G132-SA_-&MQA-11663 | HVAC SYSTEMS (V)- Quality Management Program | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2025-12-31 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3473 | LATER | PETRA | SAU4005-G132-SA_-&ABF-11664 | HVAC SYSTEMS (V)- Packing List of the Proposed Equipment | G132 | ENGINEERING | A-Overall management | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2025-12-31 |  | 2026-03-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3474 | LATER | PETRA | SAU4005-G132-SA_-&ABF-11665 | HVAC SYSTEMS (V)- Packing procedure | G132 | ENGINEERING | A-Overall management | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2026-01-01 |  | 2026-03-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3475 | LATER | PETRA | SAU4005-G132-SA_-&MEC-11666 | HVAC SYSTEMS (V)- Surface preparation & coating Procedure | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2026-01-01 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3476 | LATER | PETRA | SAU4005-G132-SA_-&MQC-11667 | HVAC SYSTEMS (V)- Warranty Certificate Form | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2026-01-01 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3477 | LATER | PETRA | SAU4005-G132-SA_-&MQA-11668 | HVAC SYSTEMS (V)- Shop Test Procedures | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2026-01-02 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3478 | LATER | PETRA | SAU4005-G132-SA_-&MQA-11669 | HVAC SYSTEMS (V)- Site test procedures | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2026-01-02 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3479 | LATER | PETRA | SAU4005-G132-SA_-&MPB-11670 | HVAC SYSTEMS (V)- Recommended Spare Parts list and consumables (commissioning and 2 years operation) | G132 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | HVAC System | IFI | IFC | [14 empty] | 2026-01-14 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3480 | LATER | PETRA | SAU4005-G133-SA_-&MEC-11630 | FANS (V)- TECHNICAL SUBMITTAL OF Main Electrical & Control Building (1A, 1B, 1C, 1D, 1E, 1F, 1J, 1H) | G133 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | FANS | IFI | IFC | [14 empty] | 2026-01-03 |  | 2025-12-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3481 | LATER | PETRA | SAU4005-G133-SA_-&MEC-11631 | FANS (V)- TECHNICAL SUBMITTAL OF Admin Building (2A, 2B, 2C, 2D, 2E, 2F, 2G, 2H, 2I, 2J, 2K, 2L, 2M) | G133 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | FANS | IFI | IFC | [14 empty] | 2026-01-03 |  | 2025-12-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3482 | LATER | PETRA | SAU4005-G133-SA_-&MEC-11632 | FANS (V)- TECHNICAL SUBMITTAL OF Unit MV/LV Electrical Switchgear Building (3A, 3B, 3C) | G133 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | FANS | IFI | IFC | [14 empty] | 2026-01-03 |  | 2025-12-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3483 | LATER | PETRA | SAU4005-G133-SA_-&MEC-11633 | FANS (V)- TECHNICAL SUBMITTAL OF GT Package MCC Control Room (4A, 4B, 4C, 4D, 4E, 4F, 4G, 4H, 4I) | G133 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | FANS | IFI | IFC | [14 empty] | 2026-01-03 |  | 2025-12-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3484 | LATER | PETRA | SAU4005-G133-SA_-&MEC-11634 | FANS (V)- TECHNICAL SUBMITTAL OF Fin Fan Cooler Electrical Switchgear Building (5A) | G133 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | FANS | IFI | IFC | [14 empty] | 2026-01-03 |  | 2026-01-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3485 | LATER | PETRA | SAU4005-G133-SA_-&MEC-11635 | FANS (V)- TECHNICAL SUBMITTAL OF ACC Electrical Switchgear Building (7A, 7B) | G133 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | FANS | IFI | IFC | [14 empty] | 2026-01-03 |  | 2026-01-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3486 | LATER | PETRA | SAU4005-G133-SA_-&MEC-11636 | FANS (V)- TECHNICAL SUBMITTAL OF STG Hall (8A, 8B, 8C) | G133 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | FANS | IFI | IFC | [14 empty] | 2026-01-03 |  | 2026-04-12 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3487 | LATER | PETRA | SAU4005-G133-SA_-&MEC-11637 | FANS (V)- TECHNICAL SUBMITTAL OF STG and Auxiliary Boiler Electrical Switchgear Building (9A) | G133 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | FANS | IFA | IFC |  |  | 2026-01-03 |  | 2026-03-09 |  | 2026-01-23 |  | 2026-01-08 |  | 2026-02-28 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3488 | LATER | PETRA | SAU4005-G133-SA_-&MEC-11638 | FANS (V)- TECHNICAL SUBMITTAL OF Water and Effluent Treatment Building (10A, 10B, 10C, 10E) | G133 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | FANS | IFA | IFC |  |  | 2026-01-03 |  | 2026-03-30 |  | 2026-01-23 |  | 0 |  | 2026-02-28 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3489 | LATER | PETRA | SAU4005-G133-SA_-&MEC-11639 | FANS (V)- TECHNICAL SUBMITTAL OF BOP Electrical Switchgear Building (12A) | G133 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | FANS | IFA | IFC |  |  | 2026-01-03 |  | 2026-03-09 |  | 2026-01-23 |  | 2026-01-14 |  | 2026-02-28 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3491 | LATER | PETRA | SAU4005-G133-SA_-&MEC-11641 | FANS (V)- TECHNICAL SUBMITTAL OF Fire Water Pump House (14A, 14B) | G133 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | FANS | IFA | IFC |  |  | 2026-01-03 |  | 2026-03-30 |  | 2026-01-23 |  | 0 |  | 2026-02-28 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3492 | LATER | PETRA | SAU4005-G133-SA_-&MEC-11642 | FANS (V)- TECHNICAL SUBMITTAL OF Search Facility & visitor Center (15A, 15B) | G133 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | FANS | IFA | IFC |  |  | 2026-01-03 |  | 2026-01-25 |  | 2026-01-23 |  | 0 |  | 2026-02-28 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3493 | LATER | PETRA | SAU4005-G133-SA_-&MEC-11643 | FANS (V)- TECHNICAL SUBMITTAL OF Workshop & Warehouse Building (17A, 17B, 17C, 17D, 17E, 17F, 17G) | G133 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | FANS | IFA | IFC |  |  | 2026-01-03 |  | 2026-03-09 |  | 2026-01-23 |  | 2026-01-14 |  | 2026-02-28 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3494 | LATER | PETRA | SAU4005-G133-SA_-&MEC-11644 | FANS (V)- TECHNICAL SUBMITTAL OF Fire Station Building (18A, 18B, 18C, 18D) | G133 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | FANS | IFA | IFC |  |  | 2026-01-03 |  | 2026-03-09 |  | 2026-01-23 |  | 0 |  | 2026-02-28 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3495 | LATER | PETRA | SAU4005-G133-SA_-&MEC-11645 | FANS (V)- TECHNICAL SUBMITTAL OF Electical SWGR Building for Fuel GAS & OIL Area (19A, 20A) | G133 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | FANS | IFA | IFC |  |  | 2026-01-03 |  | 2026-03-30 |  | 2026-01-23 |  | 0 |  | 2026-02-28 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3496 | LATER | PETRA | SAU4005-G133-SA_-&MEC-11646 | FANS (V)- TECHNICAL SUBMITTAL OF Chemical Building for WTP & ETP (22A, 22B, 22C, 22D, 22E, 22F, 22G, 22H, 22I) | G133 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | FANS | IFA | IFC |  |  | 2026-01-03 |  |  |  | 2026-01-23 |  |  |  | 2026-02-28 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3497 | LATER | PETRA | SAU4005-G133-SA_-&MEC-11647 | FANS (V)- TECHNICAL SUBMITTAL OF Hydrogen Generation Plant & Switchgear Building (23A, 23B, 23C, 23D) | G133 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | FANS | IFA | IFC |  |  | 2026-01-03 |  | 2026-04-05 |  | 2026-01-23 |  | 0 |  | 2026-02-28 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3498 | LATER | PETRA | SAU4005-G133-SA_-&MEC-11648 | FANS (V)- TECHNICAL SUBMITTAL OF Security Control Center (24A, 24B, 24C, 24D) | G133 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | FANS | IFA | IFC |  |  | 2026-01-03 |  | 2026-03-30 |  | 2026-01-23 |  | 0 |  | 2026-02-28 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3499 | LATER | PETRA | SAU4005-G133-SA_-&MEC-11649 | FANS (V)- TECHNICAL SUBMITTAL OF EHV Cable Corridor (25A, 25B) | G133 | ENGINEERING | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | FANS | IFA | IFC |  |  | 2026-01-03 |  |  |  | 2026-01-23 |  |  |  | 2026-02-28 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3500 | LATER | AHYN | SAU4005-G184-STG-&AAB-25500 | Laboratory equipment (V)_EDL | G184 | Project Management | A-Overall management | YES | GENERAL | General | SEPCOIII | Laboratory Equipment | IFI | IFD | [14 empty] | 2026-05-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3501 | LATER | AHYN | SAU4005-G184-STG-&EEC-25501 | Laboratory equipment (V)_List of electrical load | G184 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Laboratory Equipment | IFI | IFD | [14 empty] | 2026-05-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3502 | LATER | AHYN | SAU4005-G184-STG-&MTL-25502 | Laboratory equipment (V)_GA drawings | G184 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Laboratory Equipment | IFA | IFD |  |  | 2026-05-20 |  | 2026-04-23 |  | 2026-06-09 |  | 0 |  | 2026-07-15 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3503 | LATER | AHYN | SAU4005-G184-STG-&MDA-25503 | Laboratory equipment (V)_Datasheet | G184 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Laboratory Equipment | IFA | IFD |  |  | 2026-05-20 |  |  |  | 2026-06-09 |  |  |  | 2026-07-15 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3504 | LATER | AHYN | SAU4005-G184-STG-&MDC-25504 | Laboratory equipment (V)_OM manu | G184 | Quality Assurance/Quality Control Supply | M-Mechanical engineering (normally including process engineering) | YES | QA/QC | General | SEPCOIII | Laboratory Equipment | IFI | IFD | [14 empty] | 2026-05-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3505 | LATER | AHYN | SAU4005-G184-STG-&AQA-25505 | Laboratory equipment (V)_Inspection and test plan | G184 | Quality Assurance/Quality Control Supply | A-Overall management | YES | QA/QC | General | SEPCOIII | Laboratory Equipment | IFA | IFD |  |  | 2026-05-20 |  |  |  | 2026-06-09 |  |  |  | 2026-07-15 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3506 | LATER | AHYN | SAU4005-G184-STG-&MQC-25506 | Laboratory equipment (V)_FAT program | G184 | Quality Assurance/Quality Control Supply | M-Mechanical engineering (normally including process engineering) | YES | QA/QC | General | SEPCOIII | Laboratory Equipment | IFI | IFD | [14 empty] | 2026-05-06 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3507 | LATER | AHYN | SAU4005-G184-STG-&MQC-25507 | Laboratory equipment (V)_FAT report | G184 | Quality Assurance/Quality Control Supply | M-Mechanical engineering (normally including process engineering) | YES | QA/QC | General | SEPCOIII | Laboratory Equipment | IFI | IFD | [14 empty] | 2026-05-06 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3508 | LATER | AHYN | SAU4005-G184-STG-&MQC-25508 | Laboratory equipment (V)_Manufacturing completion report | G184 | Quality Assurance/Quality Control Supply | M-Mechanical engineering (normally including process engineering) | YES | QA/QC | General | SEPCOIII | Laboratory Equipment | IFI | IFD | [14 empty] | 2026-05-06 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3484 | LATER | PETRA | SAU4005-G185-SA_-&EFF-11671 | HVAC CONTROL SYSTEM (V)- Architecture diagram of HVAC System | G185 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | HVAC Control System | IFI | IFC | [14 empty] | 2026-01-30 |  | 2026-03-25 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3485 | LATER | PETRA | SAU4005-G185-SA_-&EPA-11672 | HVAC CONTROL SYSTEM (V)- Final Bill of Quantity (BOQ) for Instrumentation Items | G185 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | HVAC Control System | IFI | IFC | [14 empty] | 2026-01-30 |  | 2026-04-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3486 | LATER | PETRA | SAU4005-G185-SA_-&EPC-11673 | HVAC CONTROL SYSTEM (V)- Instruments list | G185 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | HVAC Control System | IFI | IFC | [14 empty] | 2026-01-30 |  | 2026-04-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3487 | LATER | PETRA | SAU4005-G185-SA_-&EDA-11674 | HVAC CONTROL SYSTEM (V)- Instruments data sheets along with Catalogues | G185 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | HVAC Control System | IFA | IFC |  |  | 2026-01-30 |  | 2026-03-28 |  | 2026-02-19 |  | 2026-04-13 |  | 2026-03-27 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3488 | LATER | PETRA | SAU4005-G185-SA_-&ELD-11675 | HVAC CONTROL SYSTEM (V)- Instrument hook-up drawing | G185 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | HVAC Control System | IFI | IFC | [14 empty] | 2026-01-30 |  | 2026-04-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3489 | LATER | PETRA | SAU4005-G185-SA_-&EFP-11676 | HVAC CONTROL SYSTEM (V)- I/O list along with List of alarms | G185 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | HVAC Control System | IFI | IFC | [14 empty] | 2026-01-30 |  | 2026-04-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
i | NEW | 3490 | LATER | PETRA | SAU4005-G185-SA_-&EDA-11677 | HVAC CONTROL SYSTEM (V)- Instrumentation cable list, schedule (Will be submitted separately for each building) | G185 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | HVAC Control System | IFI | IFC | [14 empty] | 2026-01-30 |  | 2026-04-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3491 | LATER | PETRA | SAU4005-G185-SA_-&ETB-11678 | HVAC CONTROL SYSTEM (V)- GA, wiring and termination details of HVAC LCP | G185 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | HVAC Control System | IFI | IFC | [14 empty] | 2026-01-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3492 | LATER | PETRA | SAU4005-G185-SA_-&EMB-11679 | HVAC CONTROL SYSTEM (V)- Interconnection wiring diagram (Will be submitted separately for each building) | G185 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | HVAC Control System | IFI | IFC | [14 empty] | 2026-01-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3493 | LATER | PETRA | SAU4005-G185-SA_-&EMB-11680 | HVAC CONTROL SYSTEM (V)- Control logic & loop diagram of HVAC LCP | G185 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | HVAC Control System | IFA | IFC |  |  | 2026-01-30 |  |  |  | 2026-02-19 |  |  |  | 2026-03-27 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3494 | LATER | PETRA | SAU4005-G185-SA_-&ETB-11681 | HVAC CONTROL SYSTEM (V)- HVAC Interface Drawing with Fire Fighting/DCS | G185 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | HVAC Control System | IFA | IFC |  |  | 2026-01-30 |  |  |  | 2026-02-19 |  |  |  | 2026-03-27 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3495 | LATER | PETRA | SAU4005-G185-SA_-&EDC-11682 | HVAC CONTROL SYSTEM (V)- Instrument O&M Manuals | G185 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | HVAC Control System | IFI | IFC | [14 empty] | 2026-01-30 |  | 2026-04-22 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3496 | LATER | PETRA | SAU4005-G185-SA_-&ELD-11683 | HVAC CONTROL SYSTEM (V)- Instrument installation / mounting details | G185 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | HVAC Control System | IFA | IFC |  |  | 2026-01-30 |  | 2026-04-22 |  | 2026-02-19 |  | 0 |  | 2026-03-27 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3497 | LATER | PETRA | SAU4005-G185-SA_-&EDA-11684 | HVAC CONTROL SYSTEM (V)- Printer & workstation Datasheet | G185 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | HVAC Control System | IFA | IFC |  |  | 2026-01-30 |  |  |  | 2026-02-19 |  |  |  | 2026-03-27 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3498 | LATER | PETRA | SAU4005-G185-SA_-&ETB-11685 | HVAC CONTROL SYSTEM (V)- Local control panel/ddc dimensional layout | G185 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | HVAC Control System | IFI | IFC | [14 empty] | 2026-01-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3499 | LATER | PETRA | SAU4005-G185-SA_-&EDA-11686 | HVAC CONTROL SYSTEM (V)- Local control panel/ddc componet datasheet | G185 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | HVAC Control System | IFA | IFC |  |  | 2026-01-30 |  | 2026-03-26 |  | 2026-02-19 |  | 0 |  | 2026-03-27 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3500 | LATER | PETRA | SAU4005-G185-SA_-&ETL-11687 | HVAC CONTROL SYSTEM (V)- Cable raceway layout drawing | G185 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | HVAC Control System | IFA | IFC |  |  | 2026-01-30 |  |  |  | 2026-02-19 |  |  |  | 2026-03-27 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3501 | LATER | PETRA | SAU4005-G185-SA_-&ETL-11688 | HVAC CONTROL SYSTEM (V)- Grounding layout drawing (WIRING DIAGRAM and dimensional layout for electrical panels) | G185 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | HVAC Control System | IFA | IFC |  |  | 2026-01-30 |  |  |  | 2026-02-19 |  |  |  | 2026-03-27 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3502 | LATER | PETRA | SAU4005-G185-SA_-&EDA-11689 | HVAC CONTROL SYSTEM (V)- HVAC DDC Cabinet Datasheet | G185 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | HVAC Control System | IFA | IFC |  |  | 2026-01-30 |  | 2026-03-25 |  | 2026-02-19 |  | 2026-04-13 |  | 2026-03-27 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3503 | LATER | PETRA | SAU4005-G185-SA_-&EFP-11690 | HVAC CONTROL SYSTEM (V)- HVAC Communication Signals | G185 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | HVAC Control System | IFA | IFC |  |  | 2026-01-30 |  | 2026-04-22 |  | 2026-02-19 |  | 0 |  | 2026-03-27 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3504 | LATER | PETRA | SAU4005-G185-SA_-&EMB-11691 | HVAC CONTROL SYSTEM (V)- HVAC Workstation HMI | G185 | ENGINEERING | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | HVAC Control System | IFI | IFC | [14 empty] | 2026-01-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3505 | LATER | JIANGSU JUNDE | SAU4005-G138-GBB-&PFB-12601 | Cartridge Filter(V)-P＆ID | G138 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Process | SEPCOIII | Cartridge Filter | IFA | IFD |  |  | 2025-12-17 |  | 2025-10-24 |  | 2026-01-06 |  | 2025-11-09 |  | 2026-02-11 |  | 2025-12-03 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3506 | LATER | JIANGSU JUNDE | SAU4005-G138-GBB-&MEC-12602 | Cartridge Filte(V)-Nameplate drawings for all equipment's | G138 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cartridge Filter | IFA | IFD |  |  | 2025-12-30 |  | 2025-11-25 |  | 2026-01-19 |  | 2025-11-09 |  | 2026-02-24 |  | 2025-12-07 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3507 | LATER | JIANGSU JUNDE | SAU4005-G138-GBB-&MED-12603 | Cartridge Filte(V)-Strength Calculations | G138 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cartridge Filter | IFA | IFD |  |  | 2026-01-05 |  |  |  | 2026-01-25 |  |  |  | 2026-03-02 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3508 | LATER | JIANGSU JUNDE | SAU4005-G138-GBB-&MEC-12604 | Cartridge Filte(V)-General Arrangement Drawing | G138 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cartridge Filter | IFA | IFD |  |  | 2025-12-30 |  | 2025-10-31 |  | 2026-01-19 |  | 0 |  | 2026-02-24 |  | 2025-11-09 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3509 | LATER | JIANGSU JUNDE | SAU4005-G138-GBB-&CLB-12605 | Cartridge Filte(V)-Foundation load and anchorage | G138 | Construction | C-Construction engineering (building construction and civil engineering) | Yes | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Cartridge Filter | IFI | IFD | [14 empty] | 2025-12-30 |  | 2025-12-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3510 | LATER | JIANGSU JUNDE | SAU4005-G138-GBB-&MDA-12606 | Cartridge Filte(V)-Equipment Data Sheets | G138 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cartridge Filter | IFI | IFD | [14 empty] | 2025-12-21 |  | 2025-10-23 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3511 | LATER | JIANGSU JUNDE | SAU4005-G138-GBB-&MPD-12607 | Cartridge Filte(V)-Valve List | G138 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cartridge Filter | IFI | IFD | [14 empty] | 2025-12-21 |  | 2025-10-24 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| DCC CHANGED | 3512 | LATER | JIANGSU JUNDE | SAU4005-G138-GBB-&MTB-12608 | Cartridge Filte(V)-3D Model of cartridge filter | G138 | Engineering | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Cartridge Filter | IFI | IFD | [14 empty] | 2026-02-28 |  | 2026-02-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3513 | LATER | JIANGSU JUNDE | SAU4005-G138-GBB-&EPD-12609 | Cartridge Filte(V)-Instruments list | G138 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | Cartridge Filter | IFI | IFD | [14 empty] | 2025-12-24 |  | 2025-10-31 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3514 | LATER | JIANGSU JUNDE | SAU4005-G138-GBB-&EDA-12610 | Cartridge Filte(V)-Instruments data sheets | G138 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | Cartridge Filter | IFA | IFD |  |  | 2026-01-05 |  | 2025-10-31 |  | 2026-01-25 |  | 2025-11-16 |  | 2026-03-02 |  | 2025-12-23 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3515 | LATER | JIANGSU JUNDE | SAU4005-G138-GBB-&EMB-12611 | Cartridge Filte(V)-Instrument hook-up drawing in Purchaser's format | G138 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | Cartridge Filter | IFA | IFD |  |  | 2027-01-05 |  | 2025-10-31 |  | 2027-01-25 |  | 2025-11-20 |  | 2027-03-02 |  | 2025-12-02 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3516 | LATER | JIANGSU JUNDE | SAU4005-G138-GBB-&EFQ-12612 | Cartridge Filte(V)-I/O list along with List of Alarms | G138 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | Cartridge Filter | IFA | IFD |  |  | 2028-01-05 |  | 2025-10-31 |  | 2028-01-25 |  | 0 |  | 2028-03-01 |  | 2025-11-09 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3517 | LATER | JIANGSU JUNDE | SAU4005-G138-GBB-&MQA-12613 | Cartridge Filte(V)-Quality Management Program | G138 | QA/QC | M-Mechanical engineering (normally including process engineering) | Yes | QA/QC | General | SEPCOIII | Cartridge Filter | IFI | IFD | [14 empty] | 2025-12-24 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3518 | LATER | JIANGSU JUNDE | SAU4005-G138-GBB-&MQA-12614 | Cartridge Filte(V)-Inspection & Test Plan (ITP) | G138 | QA/QC | M-Mechanical engineering (normally including process engineering) | Yes | QA/QC | General | SEPCOIII | Cartridge Filter | IFA | IFD |  |  | 2025-12-30 |  |  |  | 2026-01-19 |  |  |  | 2026-02-24 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3519 | LATER | JIANGSU JUNDE | SAU4005-G138-GBB-&MQC-12615 | Cartridge Filte(V)-Hydrostatic Test report and certificate | G138 | QA/QC | M-Mechanical engineering (normally including process engineering) | Yes | QA/QC | General | SEPCOIII | Cartridge Filter | IFA | IFC |  |  | 2026-06-01 |  |  |  | 2026-06-21 |  |  |  | 2026-07-27 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3520 | LATER | JIANGSU JUNDE | SAU4005-G138-GBB-&MQA-12616 | Cartridge Filte(V)-Welding Procedures | G138 | QA/QC | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | General | SEPCOIII | Cartridge Filter | IFI | IFD | [14 empty] | 2025-12-24 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3521 | LATER | JIANGSU JUNDE | SAU4005-G138-GBB-&MQA-12617 | Cartridge Filte(V)-Surface preparation & coating Procedure | G138 | QA/QC | M-Mechanical engineering (normally including process engineering) | Yes | QA/QC | General | SEPCOIII | Cartridge Filter | IFI | IFD | [14 empty] | 2026-02-28 |  | 2026-03-18 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3522 | LATER | JIANGSU JUNDE | SAU4005-G138-GBB-&MQA-12618 | Cartridge Filter(V)-Hydrostatic Test Procedure | G138 | QA/QC | M-Mechanical engineering (normally including process engineering) | Yes | MECH&PROCESS&WTP | General | SEPCOIII | Cartridge Filter | IFA | IFD |  |  | 2025-12-28 |  | 2025-12-04 |  | 2026-01-08 |  | 2026-01-11 |  | 2026-02-14 |  | 2026-02-09 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3523 | LATER | INNOGREEN | SAU4005-G139-GMD-&AAB-08700 | STP(V)_EDL | G139 | Project Management | A-Overall management | NO | GENERAL | General | SEPCOIII | STP | IFI | IFD | [14 empty] | 2026-04-11 |  | 2026-04-06 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3524 | LATER | INNOGREEN | SAU4005-G139-GMD-&PFB-08701 | STP(V)_P&ID | G139 | Engineering | B-Overall technology | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STP | IFA | IFD |  |  | 2026-04-12 |  | 2026-04-06 |  | 2026-05-02 |  | 2026-04-19 |  | 2026-06-07 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3525 | LATER | INNOGREEN | SAU4005-G139-GMD-&MTL-08702 | STP(V)_GA | G139 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STP | IFA | IFD |  |  | 2026-04-12 |  | 2026-03-20 |  | 2026-05-02 |  | 2026-04-19 |  | 2026-06-07 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3526 | LATER | INNOGREEN | SAU4005-G139-GMD-&MDA-08703 | STP(V)_Outline drawing of Fan | G139 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STP | IFA | IFD |  |  | 2026-05-02 |  | 2026-04-13 |  | 2026-05-22 |  | 2026-04-19 |  | 2026-06-27 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3527 | LATER | INNOGREEN | SAU4005-G139-GMD-&MDA-08704 | STP(V)_Outline drawing of Filter | G139 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STP | IFA | IFD |  |  | 2026-05-02 |  | 2026-04-13 |  | 2026-05-22 |  | 2026-04-19 |  | 2026-06-27 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3528 | LATER | INNOGREEN | SAU4005-G139-GMD-&MDA-08705 | STP(V)_Outline drawing of Pump | G139 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STP | IFA | IFD |  |  | 2026-05-02 |  | 2026-04-13 |  | 2026-05-22 |  | 2026-04-19 |  | 2026-06-27 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| DCC CHANGED | 3529 | LATER | INNOGREEN | SAU4005-G139-GMD-&AQA-08706 | STP(V)_Inspection and Test Plan | G139 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STP | IFA | IFD |  |  | 2026-05-02 |  |  |  | 2026-05-22 |  |  |  | 2026-06-27 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3530 | LATER | INNOGREEN | SAU4005-G139-GMD-&MPD-08707 | STP(V)_Equipment list | G139 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STP | IFA | IFD |  |  | 2026-05-02 |  |  |  | 2026-05-22 |  |  |  | 2026-06-27 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3531 | LATER | INNOGREEN | SAU4005-G139-GMD-&MPD-08708 | STP(V)_instrument List | G139 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STP | IFA | IFD |  |  | 2026-05-02 |  |  |  | 2026-05-22 |  |  |  | 2026-06-27 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3532 | LATER | INNOGREEN | SAU4005-G139-GMD-&MDA-08709 | STP(V)_Nameplate drawing | G139 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STP | IFA | IFD |  |  | 2026-05-02 |  |  |  | 2026-05-22 |  |  |  | 2026-06-27 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3533 | LATER | INNOGREEN | SAU4005-G139-GMD-&EMA-08710 | STP(V)_External Pipe Interface Diagram | G139 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STP | IFA | IFD |  |  | 2026-05-02 |  |  |  | 2026-05-22 |  |  |  | 2026-06-27 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3534 | LATER | INNOGREEN | SAU4005-G139-GMD-&MDC-08711 | STP(V)_O&M manual | G139 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STP | IFA | IFD |  |  | 2026-05-02 |  |  |  | 2026-05-22 |  |  |  | 2026-06-27 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3535 | LATER | INNOGREEN | SAU4005-G139-GMD-&MDB-08712 | STP(V)_System Control Description | G139 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STP | IFA | IFD |  |  | 2026-05-02 |  |  |  | 2026-05-22 |  |  |  | 2026-06-27 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3536 | LATER | INNOGREEN | SAU4005-G139-GMD-&EFS-08713 | STP(V)_Electrical Schematic Diagram of Electrical Equipment | G139 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STP | IFA | IFD |  |  | 2026-05-02 |  | 2026-05-12 |  | 2026-05-22 |  | 2026-05-21 |  | 2026-06-27 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3537 | LATER | INNOGREEN | SAU4005-G139-GMD-&EFS-08714 | STP(V)_Electrical Schematic Diagram of Instrumentation Control Box | G139 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STP | IFA | IFD |  |  | 2026-05-02 |  |  |  | 2026-05-22 |  |  |  | 2026-06-27 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3538 | LATER | INNOGREEN | SAU4005-G139-GMD-&MDA-08715 | STP(V)_Datashteet | G139 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STP | IFA | IFD |  |  | 2026-05-02 |  |  |  | 2026-05-22 |  |  |  | 2026-06-27 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3539 | LATER | INNOGREEN | SAU4005-G139-GMD-&MED-08716 | STP(V)_Process calculation | G139 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STP | IFA | IFD |  |  | 2026-05-02 |  |  |  | 2026-05-22 |  |  |  | 2026-06-27 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| DCC CHANGED | 3540 | LATER | INNOGREEN | SAU4005-G139-GMD-&MQA-08717 | STP(V)_Paint procedure | G139 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STP | IFA | IFD |  |  | 2026-05-02 |  |  |  | 2026-05-22 |  |  |  | 2026-06-27 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3541 | LATER | INNOGREEN | SAU4005-G139-GMD-&MPD-08718 | STP(V)_Valve list | G139 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STP | IFA | IFD |  |  | 2026-05-02 |  |  |  | 2026-05-22 |  |  |  | 2026-06-27 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3542 | LATER | INNOGREEN | SAU4005-G139-GMD-&MTB-08719 | STP(V)_3D Model | G139 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STP | IFA | IFD |  |  | 2026-05-02 |  |  |  | 2026-05-22 |  |  |  | 2026-06-27 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW ADDED | 3543 | LATER | INNOGREEN | SAU4005-G139-GMD-&AQA-08728 | STP(V)_Test procedure | G139 | Engineering | A-Overall Management | No | QA/QC | GENERAL | SEPCOIII | STP | IFA | IFD |  |  | 2026-05-15 |  |  |  | 2026-06-05 |  |  |  | 2026-07-11 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW ADDED | 3544 | Later | INNOGREEN | SAU4005-G139-GMD-&ETL-08720 | STP(V)_Cable raceway layout | G139 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | Electrical | SEPCOIII | STP | IFI | IFD | [14 empty] | 2026-06-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW ADDED | 3545 | Later | INNOGREEN | SAU4005-G139-GMD-&EMB-08721 | STP(V)_Cable schedule | G139 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | Electrical | SEPCOIII | STP | IFI | IFD | [14 empty] | 2026-06-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW ADDED | 3546 | Later | INNOGREEN | SAU4005-G139-GMD-&EEC-08722 | STP(V)_Electric load list | G139 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | Electrical | SEPCOIII | STP | IFI | IFD | [14 empty] | 2026-06-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW ADDED | 3547 | Later | INNOGREEN | SAU4005-G139-GMD-&MDA-08723 | STP(V)_GA of chemical dosing skid | G139 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STP | IFI | IFD | [14 empty] | 2026-06-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW ADDED | 3548 | Later | INNOGREEN | SAU4005-G139-GMD-&MPD-08724 | STP(V)_chemical and consumable list | G139 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STP | IFI | IFD | [14 empty] | 2026-06-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW ADDED | 3549 | Later | INNOGREEN | SAU4005-G139-GMD-&MTL-08725 | STP(V)_STP Piping Layout | G139 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STP | IFI | IFD | [14 empty] | 2026-06-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW ADDED | 3550 | Later | INNOGREEN | SAU4005-G139-GMD-&MED-08726 | STP(V)_Hydraulic flow diagram | G139 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STP | IFI | IFD | [14 empty] | 2026-06-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW ADDED | 3551 | Later | INNOGREEN | SAU4005-G139-GMD-&MPB-08727 | STP(V)_Startup, 2-Year Spares, and Insurance Spares List | G139 | Engineering | M-Mechanical engineering (normally including process engineering) | No | MECH&PROCESS&WTP | Mechanical | SEPCOIII | STP | IFI | IFD | [14 empty] | 2026-06-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW ADDED | 3552 | Later | INNOGREEN | SAU4005-G139-GMD-&ELD-08730 | STP(V)_Instrument Hook up diagram | G139 | Engineering | E-Electrotechnology (including control, information and communication techniques) | No | ELECTRICAL | Electrical | SEPCOIII | STP | IFI | IFD | [14 empty] | 2026-06-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3553 | LATER | BEIJING HUAEN | SAU4005-G141-PG_-&MLU-12700 | Plate heat exchanger(V)-GA drawing | G141 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Plate Heat Exchanger | IFA | IFD |  |  | 2025-12-25 |  | 2025-11-28 |  | 2026-01-14 |  | 2025-12-21 |  | 2026-02-01 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3554 | LATER | BEIJING HUAEN | SAU4005-G141-PG_-&MLU-12701 | Plate heat exchanger(V)-3D modle | G141 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Plate Heat Exchanger | IFI | IFD | [14 empty] | 2026-01-04 |  | 2025-12-23 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3555 | LATER | BEIJING HUAEN | SAU4005-G141-PG_-&MQA-12702 | Plate heat exchanger(V)-Inspection & Test Plan (ITP) | G141 | QA/QC | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | General | SEPCOIII | Plate Heat Exchanger | IFA | IFD |  |  | 2026-03-01 |  | 2025-11-25 |  | 2026-03-19 |  | 2026-01-11 |  | 2026-02-09 |  | 2026-02-16 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3556 | LATER | BEIJING HUAEN | SAU4005-G141-PG_-&MQA-12703 | Plate heat exchanger(V)-Shop Test Procedures | G141 | QA/QC | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | General | SEPCOIII | Plate Heat Exchanger | IFI | IFD | [14 empty] | 2026-02-09 |  | 2026-01-23 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3557 | LATER | BEIJING HUAEN | SAU4005-G141-PG_-&MDA-12704 | Plate heat exchanger(V)-Datesheet | G141 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Plate Heat Exchanger | IFA | IFD |  |  | 2025-12-25 |  | 2025-11-26 |  | 2026-01-14 |  | 2025-12-11 |  | 2026-02-01 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3559 | LATER | BEIJING HUAEN | SAU4005-G141-PG_-&MDA-12706 | Plate heat exchanger(V)-Nameplate drawing | G141 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Plate Heat Exchanger | IFA | IFD |  |  | 2026-01-09 |  | 2026-01-09 |  | 2026-01-29 |  | 0 |  | 2026-02-16 |  | 2026-01-21 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3560 | LATER | DAQO | SAU4005-G157-BHA-&EDA-20801 | LV SWGR(V) Technical Data Sheet | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | LV SWGR | IFA | IFD |  |  | 2025-12-10 |  | 2026-04-16 |  | 2025-12-30 |  | 2026-05-06 |  | 2026-02-04 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| SUBMISSION PLAN CHANGED | 3561 | LATER | DAQO | SAU4005-G157-BHA-&ELU-20802 | LV SWGR(V) Foundation drawings | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | LV SWGR | IFI | IFD | [14 empty] | 2026-08-14 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| DCC CHANGED | 3562 | LATER | DAQO | SAU4005-G157-BHA-&EFA-20803 | LV SWGR(V) Single line Drawing for UNIT PMCC | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | LV SWGR | IFA | IFD |  |  | 2025-12-20 |  | 2026-04-23 |  | 2026-01-09 |  | 2026-05-03 |  | 2026-02-14 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| DCC CHANGED | 3563 | LATER | DAQO | SAU4005-G157-BHA-&EFA-20804 | LV SWGR(V) Single line Drawing for ACC PMCC | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | LV SWGR | IFA | IFD |  |  | 2025-12-20 |  | 2026-04-23 |  | 2026-01-09 |  | 2026-05-03 |  | 2026-02-14 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3564 | LATER | DAQO | SAU4005-G157-BHA-&EFF-20805 | LV SWGR(V) Single line Drawing for Other PMCC | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | LV SWGR | IFA | IFD |  |  | 2025-12-20 |  |  |  | 2026-01-09 |  |  |  | 2026-02-14 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3565 | LATER | DAQO | SAU4005-G157-BHA-&EFF-20806 | LV SWGR(V) Single line Drawing for ACB incoming | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | LV SWGR | IFA | IFD |  |  | 2025-12-30 |  |  |  | 2026-01-19 |  |  |  | 2026-02-24 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3566 | LATER | DAQO | SAU4005-G157-BHA-&EFF-20807 | LV SWGR(V) Single line Drawing for MCCB incoming | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | LV SWGR | IFA | IFD |  |  | 2025-12-30 |  |  |  | 2026-01-19 |  |  |  | 2026-02-24 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3567 | LATER | DAQO | SAU4005-G157-BHA-&EFF-20808 | LV SWGR(V) Single line Drawing for emergancy board | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | LV SWGR | IFA | IFD |  |  | 2025-12-30 |  |  |  | 2026-01-19 |  |  |  | 2026-02-24 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| DCC CHANGED | 3568 | LATER | DAQO | SAU4005-G157-BHA-&EFA-20809 | LV SWGR(V) Single line Drawing for other DB | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | LV SWGR | IFA | IFD |  |  | 2026-01-09 |  | 2026-04-23 |  | 2026-01-29 |  | 2026-05-03 |  | 2026-03-06 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| SUBMISSION PLAN CHANGED | 3569 | LATER | DAQO | SAU4005-G157-BHA-&EFF-20810 | LV SWGR(V) Single line Drawing for MVCD and MFD | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | LV SWGR | IFA | IFD |  |  | 2026-08-14 |  |  |  | 2026-09-03 |  |  |  | 2026-10-09 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| SUBMISSION PLAN CHANGED | 3570 | LATER | DAQO | SAU4005-G157-BHA-&EED-20811 | LV SWGR(V) DC load list | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | LV SWGR | IFI | IFD | [14 empty] | 2026-08-14 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3571 | LATER | DAQO | SAU4005-G157-BHA-&EFF-20812 | LV SWGR(V) Schematic diagrams | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | LV SWGR | IFI | IFD | [14 empty] | 2025-12-30 |  | 2026-04-06 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| SUBMISSION PLAN CHANGED | 3572 | LATER | DAQO | SAU4005-G157-BHA-&ELU-20813 | LV SWGR(V) Outline drawings | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | LV SWGR | IFA | IFD |  |  | 2026-08-14 |  |  |  | 2026-09-03 |  |  |  | 2026-10-09 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3573 | LATER | DAQO | SAU4005-G157-BHA-&EDB-20814 | LV SWGR(V) Name Plate drawing | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | LV SWGR | IFA | IFD |  |  | 2025-12-15 |  |  |  | 2026-01-04 |  |  |  | 2026-02-09 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3574 | LATER | DAQO | SAU4005-G157-BHA-&EDC-20815 | LV SWGR(V) Cleaning and painting procedure | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | LV SWGR | IFI | IFD | [14 empty] | 2025-12-10 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3575 | LATER | DAQO | SAU4005-G157-BHA-&EQC-20816 | LV SWGR(V) Type Test Certificate | G157 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | YES | QA/QC | Electrical | SEPCOIII | LV SWGR | IFA | IFD |  |  | 2025-12-30 |  |  |  | 2026-01-19 |  |  |  | 2026-02-24 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| SUBMISSION PLAN CHANGED | 3576 | LATER | DAQO | SAU4005-G157-BHA-&EDC-20817 | LV SWGR(V) Installation O&M, Instruction manuals | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | LV SWGR | IFI | IFD | [14 empty] | 2026-08-14 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3577 | LATER | DAQO | SAU4005-G157-BHA-&EQA-20818 | LV SWGR(V) FAT Procedure (Inspection Test Plan) | G157 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | YES | QA/QC | Electrical | SEPCOIII | LV SWGR | IFA | IFD |  |  | 2026-01-29 |  | 2026-01-04 |  | 2026-02-18 |  | 0 |  | 2026-03-26 |  | 2026-01-29 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3578 | LATER | DAQO | SAU4005-G157-BHA-&EQC-20819 | LV SWGR(V) FAT Report | G157 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | NO | QA/QC | Electrical | SEPCOIII | LV SWGR | IFA | IFD |  |  | 2025-03-30 |  |  |  | 2025-04-19 |  |  |  | 2025-05-25 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| SUBMISSION PLAN CHANGED | 3579 | LATER | DAQO | SAU4005-G157-BHA-&EPB-20820 | LV SWGR(V) Supplier Recommended Spare Parts list | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | LV SWGR | IFA | IFD |  |  | 2026-08-14 |  |  |  | 2026-09-03 |  |  |  | 2026-10-09 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3580 | LATER | DAQO | SAU4005-G157-BHA-&EBF-20821 | LV SWGR(V) Packing List | G157 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | YES | QA/QC | Electrical | SEPCOIII | LV SWGR | IFI | IFD | [14 empty] | 2025-03-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| SUBMISSION PLAN CHANGED | 3581 | LATER | DAQO | SAU4005-G157-BHA-&EDC-20822 | LV SWGR(V) Relay catalogues and Manuals. | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | LV SWGR | IFI | IFD | [14 empty] | 2026-08-14 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| SUBMISSION PLAN CHANGED | 3582 | LATER | DAQO | SAU4005-G157-BHA-&EED-20823 | LV SWGR(V) Heat Dissipation data | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | LV SWGR | IFI | IFD | [14 empty] | 2026-08-14 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| SUBMISSION PLAN CHANGED | 3583 | LATER | DAQO | SAU4005-G157-BHA-&EED-20824 | E-house(V) Structural Drawings | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | LV SWGR | IFI | IFD | [14 empty] | 2026-08-14 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3584 | LATER | DAQO | SAU4005-G157-BHA-&EED-20825 | E-house(V) Electrical Drawings | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | LV SWGR | IFI | IFD | [14 empty] | 2025-12-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3585 | LATER | DAQO | SAU4005-G157-BHA-&EED-20826 | E-house HVAC Sizing Calculation | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | E HOUSE | IFA |  |  |  | 2026-04-25 |  |  |  | 2026-05-15 |  |  |  | 2026-06-20 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3586 | LATER | DAQO | SAU4005-G157-BHA-&EDB-20827 | E-house Nameplate Drawing | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | E HOUSE | IFI |  |  |  | 2026-04-25 |  |  |  | 2026-05-15 |  |  |  | 2026-06-20 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3587 | LATER | DAQO | SAU4005-G157-BHA-&EEC-20828 | E-house Painting Procedure | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | E HOUSE | IFA | [15 empty] | 2026-04-25 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3588 | LATER | DAQO | SAU4005-G157-BHA-&EDA-20829 | E-house Datasheet | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | E HOUSE | IFI |  |  |  | 2026-04-25 |  |  |  | 2026-05-15 |  |  |  | 2026-06-20 | [5 empty] | 2026-04-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3589 | LATER | DAQO | SAU4005-G157-BHA-&EEC-20830 | E-house Electrical Load List | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | E HOUSE | IFI | [15 empty] | 2026-04-25 |  | 2026-04-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3590 | LATER | DAQO | SAU4005-G157-BHA-&ELH-20831 | E-house Cable Raceway Drawing | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | E HOUSE | IFI | [15 empty] | 2026-04-25 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3591 | LATER | DAQO | SAU4005-G157-BHA-&ELH-20832 | E-house Earthing System Drawing& Lightning Protection Drawing | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | E HOUSE | IFA | [5 empty] | 2026-04-30 |  |  |  | 2026-05-21 |  |  |  | 0 |  | 2026-04-25 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3592 | LATER | DAQO | SAU4005-G157-BHA-&EED-20833 | E-house Lighting Calculation | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | E HOUSE | IFI |  |  |  | 2026-04-25 |  |  |  | 2026-05-15 |  |  |  | 2026-06-20 | [5 empty] | 2026-04-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3593 | LATER | DAQO | SAU4005-G157-BHA-&EDC-20834 | E-house O&M Manual | G157 | Operation & maintenance | E-Electrotechnology (including control, information and communication techniques) | YES | O&M | Electrical | SEPCOIII | E HOUSE | IFI | [15 empty] | 2026-04-25 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3594 | LATER | DAQO | SAU4005-G157-BHA-&EDC-20835 | E-house Installation and Erection Manual | G157 | Construction | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | E HOUSE | IFI | [15 empty] | 2026-04-25 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3595 | LATER | DAQO | SAU4005-G157-BHA-&EQA-20836 | E-house Inspection and Test Plan | G157 | Construction | E-Electrotechnology (including control, information and communication techniques) | YES | QA/QC | Electrical | SEPCOIII | E HOUSE | IFA | [15 empty] | 2026-04-25 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3596 | LATER | DAQO | SAU4005-G157-BHA-&EED-20837 | E-house Structure Calculation | G157 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | E HOUSE | IFA |  |  |  | 2026-04-25 |  |  |  | 2026-05-15 |  |  |  | 2026-06-20 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3597 | LATER | DAQO | SAU4005-G157-BHA-&EQC-20838 | E-house (V)- Type Test Report | G157 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | NO | QA/QC | General | SEPCOIII | E HOUSE | IFA | IFD |  |  | 2026-05-15 |  | 2026-04-30 |  | 2026-06-05 |  | 2026-06-07 |  | 2026-07-11 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3598 | LATER | BORRI | SAU4005-G159-BRU-&EFA-21100 | 125V DC System (V) - Single Line Diagram | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 125V DC System | IFA | IFD |  |  | 2025-12-12 |  | 2025-12-17 |  | 2026-01-01 |  | 2026-01-04 |  | 2026-02-06 |  | 2026-04-28 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3599 | LATER | BORRI | SAU4005-G159-BRU-&ELU-21101 | 125V DC System (V) - General Arrangement Layout Drawing | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 125V DC System | IFA | IFD |  |  | 2025-12-12 |  | 2025-12-17 |  | 2026-01-01 |  | 2026-01-04 |  | 2026-02-06 |  | 2026-01-19 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3600 | LATER | BORRI | SAU4005-G159-BRU-&EFF-21102 | 125V DC System (V) - Schematic Diagram | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 125V DC System | IFI | IFD | [14 empty] | 2025-12-12 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3601 | LATER | BORRI | SAU4005-G159-BRU-&EFA-21103 | 125V DC System (V) - Battery Rack and General Arrangement Layout Drawing | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 125V DC System | IFA | IFD |  |  | 2025-12-20 |  | 2025-12-16 |  | 2026-01-09 |  | 2026-01-04 |  | 2026-02-14 |  | 2026-03-10 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3602 | LATER | BORRI | SAU4005-G159-BUA-&EDA-21104 | 125V DC System (V) - Technical Datasheet (Charger) | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 125V DC System | IFA | IFD |  |  | 2025-11-19 |  | 2025-12-16 |  | 2025-12-09 |  | 2026-01-04 |  | 2026-01-14 |  | 2026-05-21 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3603 | LATER | BORRI | SAU4005-G159-BUA-&EDA-21105 | 125V DC System (V) - Technical Datasheet (Battery) | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 125V DC System | IFA | IFD |  |  | 2025-11-19 |  | 2025-12-16 |  | 2025-12-09 |  | 2026-01-04 |  | 2026-01-14 |  | 2026-03-23 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3604 | LATER | BORRI | SAU4005-G159-BRU-&EFA-21106 | 125V DC System (V) - DC Distribution Board Single Line Diagram | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 125V DC System | IFA | IFD |  |  | 2025-12-12 |  | 2026-01-03 |  | 2026-01-01 |  | 2026-01-19 |  | 2026-02-06 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3605 | LATER | BORRI | SAU4005-G159-BUA-&EFA-21107 | 125V DC System (V) - DC Distribution Board General Arrangement Layout Drawing | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 125V DC System | IFA | IFD |  |  | 2025-12-12 |  | 2026-01-03 |  | 2026-01-01 |  | 2026-01-19 |  | 2026-02-06 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3606 | LATER | BORRI | SAU4005-G159-BUA-&EFF-21108 | 125V DC System (V) - DC Distribution Board - Schematic Diagram | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 125V DC System | IFI | IFD | [14 empty] | 2025-12-12 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3607 | LATER | BORRI | SAU4005-G159-BRU-&EED-21109 | 125V DC System (V) - Battery Sizing Calculation | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 125V DC System | IFA | IFD |  |  | 2025-11-19 |  | 2025-12-16 |  | 2025-12-09 |  | 2026-01-04 |  | 2026-01-14 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3608 | LATER | BORRI | SAU4005-G159-BRU-&EDE-21110 | 125V DC System (V) - Catalogues | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 125V DC System | IFI | IFD | [14 empty] | 2025-11-19 |  | 2025-12-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| SUBMISSION PLAN CHANGED | 3609 | LATER | BORRI | SAU4005-G159-BRU-&EQA-21111 | 125V DC System (V) - Inspection Test Plan | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 125V DC System | IFA | IFD |  |  | 2026-08-14 |  |  |  | 2026-09-03 |  |  |  | 2026-10-09 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3610 | LATER | BORRI | SAU4005-G159-BRU-&EQC-21112 | 125V DC System (V) - FAT Procedures | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 125V DC System | IFA | IFD |  |  | 2025-12-12 |  | 2026-01-16 |  | 2026-01-01 |  | 2026-03-08 |  | 2026-02-06 |  | 2026-04-12 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| SUBMISSION PLAN CHANGED | 3611 | LATER | BORRI | SAU4005-G159-BRU-&EQC-21113 | 125V DC System (V) - FAT Report | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 125V DC System | IFA | IFD |  |  | 2026-08-14 |  |  |  | 2026-09-03 |  |  |  | 2026-10-09 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3612 | LATER | BORRI | SAU4005-G159-BRU-&EQA-21114 | 125V DC System (V) - Painting Procedure | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 125V DC System | IFI | IFD | [14 empty] | 2025-11-26 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3613 | LATER | BORRI | SAU4005-G159-BRU-&EPB-21115 | 125V DC System (V) - Spare parts list | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 125V DC System | IFA | IFD |  |  | 2026-01-14 |  | 2026-03-30 |  | 2026-02-03 |  | 2026-04-06 |  | 2026-03-11 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3614 | LATER | BORRI | SAU4005-G159-BRU-&EDC-21116 | 125V DC System (V) - Packing, Shipping and Handling Procedure | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 125V DC System | IFI | IFD | [14 empty] | 2026-01-14 |  | 2025-12-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3615 | LATER | BORRI | SAU4005-G159-BRU-&EDC-21117 | 125V DC System (V) - Operation and Maintenance Manuals | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 125V DC System | IFI | IFD | [14 empty] | 2026-01-14 |  | 2025-12-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3616 | LATER | BORRI | SAU4005-G159-BRU-&EED-21118 | 125V DC System (V) - Heat Dissipation Calculation | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 125V DC System | IFA | IFD |  |  | 2025-11-21 |  | 2025-12-16 |  | 2025-12-11 |  | 2026-01-04 |  | 2026-01-16 |  | 2026-03-10 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3617 | LATER | BORRI | SAU4005-G159-BRU-&EPC-21119 | 125V DC System (V) - Special Tool List | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 125V DC System | IFA | IFD |  |  | 2025-11-26 |  |  |  | 2025-12-16 |  |  |  | 2026-01-21 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3618 | LATER | BORRI | SAU4005-G159-BRU-&EQC-21120 | 125V DC System (V) - Type Test Report | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 125V DC System | IFA | IFD |  |  | 2025-11-19 |  |  |  | 2025-12-09 |  |  |  | 2026-01-14 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3619 | LATER | BORRI | SAU4005-G159-BUA-&ELU-21121 | 220V DC System(V) - Heat Dissipation Calculation | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 220V DC System | IFA | IFD |  |  | 2025-12-07 |  |  |  | 2025-12-27 |  |  |  | 2026-02-01 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3620 | LATER | BORRI | SAU4005-G159-BRU-&EDA-21122 | 220V DC System(V) - Technical Datasheet | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 220V DC System | IFA | IFD |  |  | 2025-12-07 |  | 2026-01-04 |  | 2025-12-27 |  | 2026-01-14 |  | 2026-02-01 |  | 2026-03-10 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3621 | LATER | BORRI | SAU4005-G159-BRU-&EED-21123 | 220V DC System(V) - Sizing Calculations | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 220V DC System | IFA | IFD |  |  | 2025-12-07 |  | 2026-01-25 |  | 2025-12-27 |  | 2026-02-04 |  | 2026-02-01 |  | 2026-03-10 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3622 | LATER | BORRI | SAU4005-G159-BUA-&ELU-21124 | 220V DC System(V) - Spare Parts list | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 220V DC System | IFA | IFD |  |  | 2025-12-07 |  |  |  | 2025-12-27 |  |  |  | 2026-02-01 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3623 | LATER | BORRI | SAU4005-G159-BRU-&EFA-21125 | 220V DC System(V) - Single Line Diagram | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 220V DC System | IFA | IFD |  |  | 2025-12-07 |  | 2025-12-31 |  | 2025-12-27 |  | 2026-01-15 |  | 2026-02-01 |  | 2026-02-01 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3624 | LATER | BORRI | SAU4005-G159-BRU-&ELU-21126 | 220V DC System(V) - General Arrangement Drawing | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 220V DC System | IFA | IFD |  |  | 2025-12-07 |  | 2025-12-31 |  | 2025-12-27 |  | 2026-01-15 |  | 2026-02-01 |  | 2026-05-20 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3625 | LATER | BORRI | SAU4005-G159-BRU-&EFF-21127 | 220V DC System(V) - Electrical Wiring Diagram | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 220V DC System | IFI | IFD | [14 empty] | 2025-12-07 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3626 | LATER | BORRI | SAU4005-G159-BRU-&EPC-21128 | 220V DC System(V) - Special Tools list | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 220V DC System | IFA | IFD |  |  | 2025-12-07 |  | 2026-01-25 |  | 2025-12-27 |  | 0 |  | 2026-02-01 |  | 2026-02-12 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| SUBMISSION PLAN CHANGED | 3627 | LATER | BORRI | SAU4005-G159-BRU-&EQA-21129 | 220V DC System(V) - FAT Procedure | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 220V DC System | IFA | IFD |  |  | 2026-08-14 |  |  |  | 2026-09-03 |  |  |  | 2026-10-09 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| SUBMISSION PLAN CHANGED | 3628 | LATER | BORRI | SAU4005-G159-BRU-&EQC-21130 | 220V DC System(V) - Inspection and Test Plan | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 220V DC System | IFA | IFD |  |  | 2026-08-14 |  |  |  | 2026-09-03 |  |  |  | 2026-10-09 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| SUBMISSION PLAN CHANGED | 3629 | LATER | BORRI | SAU4005-G159-BRU-&EQC-21131 | 220V DC System(V) - FAT Report | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 220V DC System | IFA | IFD |  |  | 2026-08-14 |  |  |  | 2026-09-03 |  |  |  | 2026-10-09 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| SUBMISSION PLAN CHANGED | 3630 | LATER | BORRI | SAU4005-G159-BRU-&EDC-21132 | 220V DC System(V) - Operation & Maintenance Manual | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 220V DC System | IFI | IFD | [14 empty] | 2026-08-14 |  | 2026-05-15 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3631 | LATER | BORRI | SAU4005-G159-BRU-&EEC-21133 | 220V DC System(V) - Painting Specification | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 220V DC System | IFI | IFD | [14 empty] | 2025-12-07 |  | 2026-03-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3632 | LATER | BORRI | SAU4005-G159-BRU-&EFA-21134 | 220V DC System(V) - DC Distribution Board Single Line Diagram | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 220V DC System | IFA | IFD |  |  | 2025-12-07 |  | 2025-12-31 |  | 2025-12-27 |  | 2026-01-15 |  | 2026-02-01 |  | 2026-03-29 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3633 | LATER | BORRI | SAU4005-G159-BRU-&ELU-21135 | 220V DC System(V) - DC Distribution Board General Arrangement Drawing | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 220V DC System | IFA | IFD |  |  | 2025-12-07 |  | 2025-12-31 |  | 2025-12-27 |  | 2026-01-15 |  | 2026-02-01 |  | 2026-05-06 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| SUBMISSION PLAN CHANGED | 3634 | LATER | BORRI | SAU4005-G159-BRU-&EFF-21136 | 220V DC System(V) -DC Distribution Board Schematic Diagram | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 220V DC System | IFI | IFD | [14 empty] | 2026-08-14 |  | 2026-04-15 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| SUBMISSION PLAN CHANGED | 3635 | LATER | BORRI | SAU4005-G159-BRU-&EDC-21137 | 220V DC System(V) -DC Distribution Board Erection Manual | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 220V DC System | IFI | IFD | [14 empty] | 2026-08-14 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3636 | LATER | BORRI | SAU4005-G160-BRU-&EFA-21200 | UPS System(V) - Single Line Diagram | G160 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UPS System | IFA | IFD |  |  | 2025-12-07 |  | 2026-01-04 |  | 2025-12-27 |  | 2026-01-15 |  | 2026-02-01 |  | 2026-03-31 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3637 | LATER | BORRI | SAU4005-G160-BRU-&ELU-21201 | UPS System(V) - General Arrangement Drawing | G160 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UPS System | IFA | IFD |  |  | 2025-12-07 |  | 2026-01-04 |  | 2025-12-27 |  | 2026-01-18 |  | 2026-02-01 |  | 2026-04-28 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3638 | LATER | BORRI | SAU4005-G160-BRU-&EFF-21202 | UPS System(V) - Electrical Wiring Diagram | G160 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UPS System | IFI | IFD | [14 empty] | 2025-12-07 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3639 | LATER | BORRI | SAU4005-G160-BRU-&EDA-21203 | UPS System(V) - Technical Datasheet | G160 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UPS System | IFA | IFD |  |  | 2025-12-07 |  | 2026-01-04 |  | 2025-12-27 |  | 2026-01-18 |  | 2026-02-01 |  | 2026-03-31 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| SUBMISSION PLAN CHANGED | 3640 | LATER | BORRI | SAU4005-G160-BRU-&EED-21204 | UPS System(V) - Loads Profile and Inverter Sizing Calculations | G160 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UPS System | IFA | IFD |  |  | 2026-08-14 |  |  |  | 2026-09-03 |  |  |  | 2026-10-09 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| SUBMISSION PLAN CHANGED | 3641 | LATER | BORRI | SAU4005-G160-BRU-&EED-21205 | UPS System(V) - Short Circuit Calculations | G160 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UPS System | IFA | IFD |  |  | 2026-08-14 |  |  |  | 2026-09-03 |  |  |  | 2026-10-09 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3642 | LATER | BORRI | SAU4005-G160-BRU-&EPB-21206 | UPS System(V) - Spare Parts list | G160 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UPS System | IFA | IFD |  |  | 2025-12-07 |  | 2026-01-25 |  | 2025-12-27 |  | 2026-02-11 |  | 2026-02-01 |  | 2026-03-10 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3643 | LATER | BORRI | SAU4005-G160-BRU-&EPC-21207 | UPS System(V) - Special Tools list | G160 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UPS System | IFA | IFD |  |  | 2025-12-07 |  | 2026-01-25 |  | 2025-12-27 |  | 2026-02-15 |  | 2026-02-01 |  | 2026-03-10 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3644 | LATER | BORRI | SAU4005-G160-BRU-&EQA-21208 | UPS System(V) - FAT Procedure | G160 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UPS System | IFA | IFD |  |  | 2025-12-07 |  | 2026-02-25 |  | 2025-12-27 |  | 0 |  | 2026-02-01 |  | 2026-03-15 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3645 | LATER | BORRI | SAU4005-G160-BRU-&EQA-21209 | UPS System(V) - Inspection and Test Plan | G160 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UPS System | IFA | IFD |  |  | 2025-12-07 |  | 2026-02-25 |  | 2025-12-27 |  | 2026-03-15 |  | 2026-02-01 |  | 2026-04-12 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| SUBMISSION PLAN CHANGED | 3646 | LATER | BORRI | SAU4005-G160-BRU-&EQC-21210 | UPS System(V) - FAT Report | G160 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UPS System | IFA | IFD |  |  | 2026-08-14 |  |  |  | 2026-09-03 |  |  |  | 2026-10-09 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3647 | LATER | BORRI | SAU4005-G160-BRU-&EED-21211 | UPS System(V) - Heat Dissipation Calculation | G160 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UPS System | IFA | IFD |  |  | 2025-12-07 |  |  |  | 2025-12-27 |  |  |  | 2026-02-01 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| SUBMISSION PLAN CHANGED | 3648 | LATER | BORRI | SAU4005-G160-BRU-&EDC-21212 | UPS System(V) - Operation & Maintenance Manual | G160 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UPS System | IFI | IFD | [14 empty] | 2026-08-14 |  | 2026-05-16 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3649 | LATER | BORRI | SAU4005-G160-BRU-&EEC-21213 | UPS System(V) - Painting Specification | G160 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UPS System | IFI | IFD | [14 empty] | 2025-12-07 |  | 2026-03-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3650 | LATER | BORRI | SAU4005-G160-BRU-&ELU-21214 | UPS System(V) - UPS Distribution Board General Arrangement Drawing | G160 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UPS System | IFA | IFD |  |  | 2025-12-07 |  | 2026-01-04 |  | 2025-12-27 |  | 2026-01-15 |  | 2026-02-01 |  | 2026-04-28 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3651 | LATER | BORRI | SAU4005-G160-BRU-&EFA-21215 | UPS System(V) - UPS Distribution Board Single Line Diagram | G160 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UPS System | IFA | IFD |  |  | 2025-12-07 |  | 2026-01-04 |  | 2025-12-27 |  | 2026-01-18 |  | 2026-02-01 |  | 2026-03-31 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| SUBMISSION PLAN CHANGED | 3652 | LATER | BORRI | SAU4005-G160-BRU-&EFF-21216 | UPS System(V) - UPS Distribution Board Schematic Diagram | G160 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UPS System | IFI | IFD | [14 empty] | 2026-08-14 |  | 2026-04-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| SUBMISSION PLAN CHANGED | 3653 | LATER | BORRI | SAU4005-G160-BRU-&EEC-21217 | UPS System(V) - UPS Distribution Board Heat Dissipation Calculations | G160 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | UPS System | IFA | IFD |  |  | 2026-08-14 |  |  |  | 2026-09-03 |  |  |  | 2026-10-09 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3654 | LATER | YIJIEHONGLI | SAU4005-G159-BUA-&EDA-21180 | 220V Battery(V) - Technical Data Sheet | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 220V Battery | IFA | IFD |  |  | 2025-11-30 |  | 2026-02-05 |  | 2025-12-20 |  | 2026-01-12 |  | 2026-01-25 |  | 2026-02-23 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3655 | LATER | YIJIEHONGLI | SAU4005-G159-BUA-&ELU-21181 | 220V Battery(V) - General Arrangement Drawing | G159 | Construction | E-Electrotechnology (including control, information and communication techniques) | YES | PIPING&PLANT DESIGN | Electrical | SEPCOIII | 220V Battery | IFA | IFD |  |  | 2025-12-07 |  | 2025-12-28 |  | 2025-12-27 |  | 2026-01-12 |  | 2026-02-01 |  | 2026-02-04 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3656 | LATER | YIJIEHONGLI | SAU4005-G159-BUA-&EED-21182 | 220V Battery(V) - Battery Sizing Calculations | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 220V Battery | IFI | IFD | [14 empty] | 2025-11-30 |  | 2025-12-28 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3657 | LATER | YIJIEHONGLI | SAU4005-G159-BUA-&EFA-21183 | 220V Battery(V) - Single Line Diagram | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 220V Battery | IFA | IFD |  |  | 2025-11-30 |  | 2025-12-28 |  | 2025-12-20 |  | 0 |  | 2026-01-25 |  | 2026-01-12 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3658 | LATER | YIJIEHONGLI | SAU4005-G159-BUA-&ELU-21184 | 220V Battery(V) - Foundation / Fixing detail drawing showing layout plan | G159 | Construction | E-Electrotechnology (including control, information and communication techniques) | YES | CIVIL&STRUCTURE&ARCHITECTURAL | Electrical | SEPCOIII | 220V Battery | IFA | IFD |  |  | 2025-12-07 |  | 2025-12-28 |  | 2025-12-27 |  | 0 |  | 2026-02-01 |  | 2026-01-12 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3659 | LATER | YIJIEHONGLI | SAU4005-G159-BUA-&EQA-21185 | 220V Battery(V) - Inspection and Test Plan | G159 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | YES | QA/QC | General | SEPCOIII | 220V Battery | IFA | IFD |  |  | 2025-11-30 |  | 2025-12-27 |  | 2025-12-20 |  | 2026-01-28 |  | 2026-01-25 |  | 2026-03-15 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3660 | LATER | YIJIEHONGLI | SAU4005-G159-BUA-&EQC-21186 | 220V Battery(V) - Type Test certificate | G159 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | YES | QA/QC | General | SEPCOIII | 220V Battery | IFA | IFD |  |  | 2025-11-30 |  |  |  | 2025-12-20 |  |  |  | 2026-01-25 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3661 | LATER | YIJIEHONGLI | SAU4005-G159-BUA-&EDC-21187 | 220V Battery(V) - Installation Operation and Maintenance Manual | G159 | Operation & Maintenacne | E-Electrotechnology (including control, information and communication techniques) | YES | O&M | Electrical | SEPCOIII | 220V Battery | IFI | IFD | [14 empty] | 2025-11-30 |  | 2025-12-28 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3662 | LATER | YIJIEHONGLI | SAU4005-G159-BUA-&EED-21188 | 220V Battery(V) - Heat Dissipation Calculation | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 220V Battery | IFA | IFD |  |  | 2025-11-30 |  |  |  | 2025-12-20 |  |  |  | 2026-01-25 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3663 | LATER | YIJIEHONGLI | SAU4005-G159-BUA-&EED-21189 | 220V Battery(V) - Short Circuit Calculations | G159 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | 220V Battery | IFA | IFD |  |  | 2025-11-30 |  | 2025-12-28 |  | 2025-12-20 |  | 2026-01-12 |  | 2026-01-25 |  | 2026-01-15 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3664 | LATER | YIJIEHONGLI | SAU4005-G159-BUA-&ELU-21190 | 220V Battery(V) - Battery Catalogue | G159 | Commissioning | E-Electrotechnology (including control, information and communication techniques) | YES | COMMISSIONING | Instrumentation and Control | SEPCOIII | 220V Battery | IFI | IFD | [14 empty] | 2025-11-30 |  | 2025-12-28 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3665 | LATER | YIJIEHONGLI | SAU4005-G159-BUA-&ELU-21191 | 220V Battery(V) - FAT Test Procedure | G159 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | YES | QA/QC | General | SEPCOIII | 220V Battery | IFA | IFD |  |  | 2025-11-30 |  |  |  | 2025-12-20 |  |  |  | 2026-01-25 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3666 | LATER | YIJIEHONGLI | SAU4005-G162-CMB-&EAB-21500 | Cyber Security System(V)-MDL | G162 | EN | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Plant Communication | IFI | IFD | [14 empty] | 2026-03-10 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3667 | LATER | YIJIEHONGLI | SAU4005-G162-CMB-&EPC-21501 | Cyber Security System(V) -Electrical Load List | G162 | EN | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Plant Communication | IFI | IFD | [14 empty] | 2026-03-12 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3668 | LATER | YIJIEHONGLI | SAU4005-G162-CMB-&EDA-21502 | Cyber Security System (V)- Data Sheets | G162 | EN | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Plant Communication | IFA | IFD |  |  | 2026-03-11 |  |  |  | 2026-03-31 |  |  |  | 2026-05-06 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3669 | LATER | YIJIEHONGLI | SAU4005-G162-CMB-&EDB-21503 | Cyber Security System (V) -Network Architecture | G162 | EN | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Plant Communication | IFA | IFD |  |  | 2026-03-13 |  | 2026-03-28 |  | 2026-04-02 |  | 0 |  | 2026-05-08 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3670 | LATER | YIJIEHONGLI | SAU4005-G162-CMB-&EDA-21504 | Cyber Security System(V) - Cabinet Outline Drawing | G162 | EN | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Plant Communication | IFI | IFD | [14 empty] | 2026-03-14 |  | 2026-04-12 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3671 | LATER | YIJIEHONGLI | SAU4005-G162-CMB-&EPA-21505 | Cyber Security System(V) - Bill of Material | G162 | EN | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Plant Communication | IFI | IFD | [14 empty] | 2026-04-19 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3672 | LATER | YIJIEHONGLI | SAU4005-G162-CMB-&ELU-21506 | Cyber Security System (V)- Cabinet Arrangement & Internal Wiring Drawings | G162 | EN | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Plant Communication | IFI | IFD | [14 empty] | 2026-04-24 |  | 2026-04-14 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3673 | LATER | YIJIEHONGLI | SAU4005-G162-CMB-&EPA-21507 | Cyber Security System(V)- Cable list | G162 | EN | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Plant Communication | IFI | IFD | [14 empty] | 2026-05-01 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3674 | LATER | YIJIEHONGLI | SAU4005-G162-CMB-&EPB-21508 | Cyber Security System(V)- Spare Parts List | G162 | OM | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Plant Communication | IFI | IFD | [14 empty] | 2026-04-19 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3675 | LATER | YIJIEHONGLI | SAU4005-G162-CMB-&EQA-21509 | Cyber Security System (V)- FAT Procedure | G162 | CS | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Plant Communication | IFA | IFD |  |  | 2026-04-14 |  | 2026-03-27 |  | 2026-05-04 |  | 2026-06-07 |  | 2026-06-09 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3676 | LATER | YIJIEHONGLI | SAU4005-G162-CMB-&EQA-21510 | Cyber Security System (V)- Factory Inspection and Test Plan | G162 | CS | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Plant Communication | IFA | IFD |  |  | 2026-04-14 |  | 2026-03-27 |  | 2026-05-04 |  | 2026-06-07 |  | 2026-06-09 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3677 | LATER | YIJIEHONGLI | SAU4005-G162-CMB-&EQA-21511 | Cyber Security System (V)- FAT Reports | G162 | CS | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Plant Communication | IFA | IFD |  |  | 2026-10-05 |  |  |  | 2026-10-25 |  |  |  | 2026-11-30 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3678 | LATER | YIJIEHONGLI | SAU4005-G162-CMB-&EQA-21512 | Cyber Security System(V)-SAT Procedure | G162 | CS | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Plant Communication | IFA | IFD |  |  | 2026-04-19 |  |  |  | 2026-05-09 |  |  |  | 2026-06-14 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3679 | LATER | YIJIEHONGLI | SAU4005-G162-CMB-&EDC-21513 | Cyber Security System(V)-Operation and Maintenance Manual | G162 | OM | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Plant Communication | IFI | IFD | [14 empty] | 2026-09-19 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3680 | LATER | YIJIEHONGLI | SAU4005-G162-CYA-&EDA-21400 | Plant Communication (V)-Communication System Data Sheets | G162 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Plant Communication | IFA | IFD |  |  | 2026-03-07 |  | 2026-03-10 |  | 2026-03-27 |  | 0 |  | 2026-05-02 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3681 | LATER | YIJIEHONGLI | SAU4005-G162-CYA-&EFA-21401 | Plant Communication (V)-Communication System Network Architecture | G162 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Plant Communication | IFI | IFD | [14 empty] | 2026-03-12 |  | 2026-04-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3682 | LATER | YIJIEHONGLI | SAU4005-G162-CYA-&ELU-21402 | Plant Communication (V)-Communication System Cabinet Assembly Diagram | G162 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Plant Communication | IFI | IFD | [14 empty] | 2026-04-09 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3683 | LATER | YIJIEHONGLI | SAU4005-G162-CYA-&ELU-21403 | Plant Communication (V)-Communication System Arrangement Drawing | G162 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Plant Communication | IFA | IFD |  |  | 2026-03-12 |  |  |  | 2026-04-01 |  |  |  | 2026-05-07 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3684 | LATER | YIJIEHONGLI | SAU4005-G162-CYA-&EDA-21404 | Plant Communication (V)-Communication System Nameplate Drawing | G162 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Plant Communication | IFI | IFD |  |  | 2026-04-09 |  |  |  | 2026-04-29 |  |  |  | 2026-06-04 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3685 | LATER | YIJIEHONGLI | SAU4005-G162-CYA-&EDA-21405 | Plant Communication (V)-Communication System Cable Data Sheets | G162 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Plant Communication | IFA | IFD |  |  | 2026-03-12 |  |  |  | 2026-04-01 |  |  |  | 2026-05-07 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3686 | LATER | YIJIEHONGLI | SAU4005-G162-CYA-&EPA-21406 | Plant Communication (V)-Communication System Cable Schedule and Interconnection Details | G162 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Plant Communication | IFI | IFD | [14 empty] | 2026-04-09 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3687 | LATER | YIJIEHONGLI | SAU4005-G162-CYA-&EPA-21407 | Plant Communication (V)-Communication System Equipment List | G162 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Plant Communication | IFI | IFD | [14 empty] | 2026-04-09 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3688 | LATER | YIJIEHONGLI | SAU4005-G162-CYA-&EPC-21408 | Plant Communication (V)-Communication System Electrical Load List | G162 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Plant Communication | IFI | IFD | [14 empty] | 2026-04-29 |  | 2026-03-12 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3689 | LATER | YIJIEHONGLI | SAU4005-G162-CYA-&EQA-21409 | Plant Communication (V)-Communication System - Inspection and Test Plan | G162 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | YES | QA/QC | General | SEPCOIII | Plant Communication | IFA | IFD |  |  | 2026-04-29 |  |  |  | 2026-05-19 |  |  |  | 2026-06-24 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3690 | LATER | YIJIEHONGLI | SAU4005-G162-CYA-&EQA21410 | Plant Communication (V)-Communication System - FAT Reports | G162 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | NO | QA/QC | General | SEPCOIII | Plant Communication | IFA | IFD |  |  | 2026-04-29 |  |  |  | 2026-05-19 |  |  |  | 2026-06-24 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3691 | LATER | YIJIEHONGLI | SAU4005-G162-CYA-&EFE-21411 | Plant Communication (V)-Functional Description of the Plant Communication System | G162 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Plant Communication | IFI | IFD | [14 empty] | 2026-03-12 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3692 | LATER | YIJIEHONGLI | SAU4005-G162-CYA-&ELD-21412 | Plant Communication (V)-Communication System Typical Installation Drawing | G162 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Plant Communication | IFI | IFD | [14 empty] | 2026-04-15 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3693 | LATER | YIJIEHONGLI | SAU4005-G162-CYA-&EDC-21413 | Plant Communication (V)-Communication System Operation and Maintenance Manual | G162 | Operation & Maintenacne | E-Electrotechnology (including control, information and communication techniques) | YES | O&M | Electrical | SEPCOIII | Plant Communication | IFI | IFD | [14 empty] | 2026-05-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3694 | LATER | YIJIEHONGLI | SAU4005-G162-CYA-&EPB-21414 | Plant Communication (V)-Communication System Start-Up & Commissioning Spare parts and Special Tools List | G162 | Operation & Maintenacne | E-Electrotechnology (including control, information and communication techniques) | YES | O&M | Electrical | SEPCOIII | Plant Communication | IFA | IFD |  |  | 2026-03-14 |  | 2026-04-29 |  | 2026-04-03 |  | 0 |  | 2026-05-09 |  | 2026-05-20 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3695 | LATER | YIJIEHONGLI | SAU4005-G162-CYA-&EPA-21415 | Plant Communication (V)-Communication System – BOM (Bill of Material) | G162 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Plant Communication | IFI | IFD | [14 empty] | 2026-03-14 |  | 2026-04-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3696 | LATER | SHANDONG HUANING | SAU4005-G170-BY_-&EFF-22401 | Heat Tracing(V) - Standard schematic wiring diagram | G170 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Heat Tracing | IFI | IFD | [14 empty] | 2026-12-05 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3697 | LATER | SHANDONG HUANING | SAU4005-G170-BY_-&EDC-22402 | Heat Tracing(V) - O&M Manual | G170 | Operation & maintenance | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Heat Tracing | IFI | IFD | [14 empty] | 2026-12-05 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3698 | LATER | SHANDONG HUANING | SAU4005-G170-BY_-&EFF-22403 | Heat Tracing(V) - Logic diagram | G170 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Heat Tracing | IFI | IFD | [14 empty] | 2026-12-05 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3699 | LATER | SHANDONG HUANING | SAU4005-G170-BY_-&EEC-22404 | Heat Tracing(V) - Load list | G170 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Heat Tracing | IFI | IFD | [14 empty] | 2026-12-05 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3700 | LATER | SHANDONG HUANING | SAU4005-G170-BY_-&EDA-22405 | Heat Tracing(V) - Data sheet | G170 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Heat Tracing | IFA | IFD |  |  | 2026-12-05 |  |  |  | 2026-12-25 |  |  |  | 2027-01-31 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3701 | LATER | SHANDONG HUANING | SAU4005-G170-BY_-&EDA-22406 | Heat Tracing(V) - Rating Plate | G170 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Heat Tracing | IFA | IFD |  |  | 2026-12-05 |  |  |  | 2026-12-25 |  |  |  | 2027-01-31 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3702 | LATER | SHANDONG HUANING | SAU4005-G170-BY_-&EQA-22407 | Heat Tracing(V) - Inspection Test Plan | G170 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Heat Tracing | IFA | IFP |  |  | 2026-12-05 |  |  |  | 2026-12-25 |  |  |  | 2027-01-31 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3703 | LATER | SHANDONG HUANING | SAU4005-G170-BY_-&EQC-22408 | Heat Tracing(V) - Factory Acceptance Test Results Report | G170 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Heat Tracing | IFA | IFP |  |  | 2026-12-05 |  |  |  | 2026-12-25 |  |  |  | 2027-01-31 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3704 | LATER | SHANDONG HUANING | SAU4005-G170-BY_-&EPB-22409 | Heat Tracing(V) - Spare Parts | G170 | Operation & maintenance | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Heat Tracing | IFA | IFD |  |  | 2026-12-05 |  |  |  | 2026-12-25 |  |  |  | 2027-01-31 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| purpose changed | 3657 | LATER | YIJIEHONGLI | SAU4005-G171-CYP-&EAB-22500 | CCTV (V)MDL | G171 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | CCTV | IFA | IFD |  |  | 2025-11-30 |  | 2025-12-12 |  | 2025-12-20 |  | 2026-01-21 |  | 2026-01-25 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3658 | LATER | YIJIEHONGLI | SAU4005-G171-CYP-&EDB-22501 | CCTV (V)System Network Architecture | G171 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | CCTV | IFA | IFD |  |  | 2026-01-19 |  | 2025-12-12 |  | 2026-02-08 |  | 2026-01-21 |  | 2026-03-16 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3659 | LATER | YIJIEHONGLI | SAU4005-G171-CYP-&ELD-22502 | CCTV (V)Equipment Arrangement Drawing | G171 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | I&C&DCS | Instrumentation and Control | SEPCOIII | CCTV | IFA | IFC |  |  | 2026-01-19 |  |  |  | 2026-02-08 |  |  |  | 2026-03-16 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3660 | LATER | YIJIEHONGLI | SAU4005-G171-CYP-&EPD-22503 | CCTV (V)Equipment List | G171 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | I&C&DCS | Instrumentation and Control | SEPCOIII | CCTV | IFI | IFD | [14 empty] | 2026-01-19 |  | 2026-01-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3661 | LATER | YIJIEHONGLI | SAU4005-G171-CYP-&EMB-22504 | CCTV (V)Cable List | G171 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | I&C&DCS | Instrumentation and Control | SEPCOIII | CCTV | IFI | IFC | [14 empty] | 2026-02-21 |  | 2026-03-12 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3662 | LATER | YIJIEHONGLI | SAU4005-G171-CYP-&EDA-22505 | CCTV (V)Equipments Datasheet & Catalogues | G171 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | CCTV | IFA | IFD |  |  | 2025-12-27 |  | 2025-12-12 |  | 2026-01-16 |  | 2026-01-21 |  | 2026-02-21 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3663 | LATER | YIJIEHONGLI | SAU4005-G171-CYP-&EED-22506 | CCTV (V)Electrical Load List and Heat Load Calculation | G171 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | I&C&DCS | Instrumentation and Control | SEPCOIII | CCTV | IFI | IFD | [14 empty] | 2025-12-27 |  | 2026-03-12 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3664 | LATER | YIJIEHONGLI | SAU4005-G171-CYP-&EPA-22507 | CCTV (V)Bill of Material | G171 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | I&C&DCS | Instrumentation and Control | SEPCOIII | CCTV | IFI | IFD | [14 empty] | 2026-01-23 |  | 2026-01-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3665 | LATER | YIJIEHONGLI | SAU4005-G171-CYP-&ELD-22508 | CCTV (V)Installation Drawing | G171 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | CCTV | IFI | IFD | [14 empty] | 2026-01-19 |  | 2026-01-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3666 | LATER | YIJIEHONGLI | SAU4005-G171-CYP-&EMA-22509 | CCTV (V)Local Junction Box GA & Wiring Diagram | G171 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | I&C&DCS | Instrumentation and Control | SEPCOIII | CCTV | IFI | IFC | [14 empty] | 2026-01-23 |  | 2026-01-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3667 | LATER | YIJIEHONGLI | SAU4005-G171-CYP-&EMA-22510 | CCTV (V)Panel GA & Wiring Diagram | G171 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | I&C&DCS | Instrumentation and Control | SEPCOIII | CCTV | IFI | IFC | [14 empty] | 2026-01-23 |  | 2026-01-30 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3668 | LATER | YIJIEHONGLI | SAU4005-G171-CYP-&EQA-22511 | CCTV (V)FAT Procedure | G171 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | CCTV | IFI | IFD | [14 empty] | 2026-02-14 |  | 2026-01-12 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3669 | LATER | YIJIEHONGLI | SAU4005-G171-CYP-&EQA-22512 | CCTV (V)ITP Procedure | G171 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | CCTV | IFI | IFD | [14 empty] | 2025-12-27 |  | 2026-01-12 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3670 | LATER | YIJIEHONGLI | SAU4005-G171-CYP-&EDC-22513 | CCTV (V)Operation and maintenance manual | G171 | Operation & Maintenacne | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | CCTV | IFI | IFD | [14 empty] | 2026-02-11 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3671 | LATER | SCHNEIDER | SAU4005-G161-AR_-&ELU-21300 | Protection Panel (V)-General Arrangement Drawing- Protection Panel | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2025-12-30 |  | 2026-02-24 |  | 2026-01-19 |  | 0 |  | 2026-02-24 |  | 2026-03-10 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3672 | LATER | SCHNEIDER | SAU4005-G161-AQ_-&ELU-21301 | Protection Panel (V)-General Arrangement Drawing- Tariff Metering Panel | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2025-12-30 |  | 2026-03-31 |  | 2026-01-19 |  | 0 |  | 2026-02-24 |  | 2026-04-26 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3673 | LATER | SCHNEIDER | SAU4005-G161-AR_-&EFF-21302 | Protection Panel (V)-Schematic Drawing -GSUT PROTECTION PANEL | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFI | IFD | [14 empty] | 2026-01-30 |  | 2026-03-10 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3674 | LATER | SCHNEIDER | SAU4005-G161-AR_-&EFF-21303 | Protection Panel (V)-Schematic Drawing -OVERALL DIFFERENTIAL PROTECTION PANEL | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFI | IFD | [14 empty] | 2026-01-30 |  | 2026-03-10 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3675 | LATER | SCHNEIDER | SAU4005-G161-AR_-&EFF-21304 | Protection Panel (V)-Schematic Drawing -UAT PROTECTION PANEL | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFI | IFD | [14 empty] | 2026-01-30 |  | 2026-03-10 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3676 | LATER | SCHNEIDER | SAU4005-G161-AQ_-&EFF-21305 | Protection Panel (V)-Schematic Drawing -GSUT MAIN AND CEHCK METERING PANEL | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFI | IFD | [14 empty] | 2026-01-30 |  | 2026-03-10 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3678 | LATER | SCHNEIDER | SAU4005-G161-AR_-&EDA-21307 | Protection Panel (V)-Technical Datasheet for Protection Relays and Meters | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2025-12-15 |  |  |  | 2026-01-04 |  |  |  | 2026-02-09 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3679 | LATER | SCHNEIDER | SAU4005-G161-AR_-&EFP-21308 | Protection Panel (V)-GSUT and UAT Protection and Metering Relay List | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFI | IFD | [14 empty] | 2025-12-16 |  | 2026-05-02 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3680 | LATER | SCHNEIDER | SAU4005-G161-AR_-&EDE-21309 | Protection Panel (V)-Technical Catalogues for Protection Relays and Meters | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFI | IFD | [14 empty] | 2025-12-17 |  | 2026-03-31 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3681 | LATER | SCHNEIDER | SAU4005-G161-AR_-&AQC-21310 | Protection Panel (V)-Type Test Reports for Protection Relays and Meters | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | QA/QC | General | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2025-12-18 |  |  |  | 2026-01-07 |  |  |  | 2026-02-12 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3682 | LATER | SCHNEIDER | SAU4005-G161-AR_-&EPA-21311 | Protection Panel (V)-GSUT and UAT Protection and Metering Panel List | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFI | IFD | [14 empty] | 2025-12-30 |  | 2026-02-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3683 | LATER | SCHNEIDER | SAU4005-G161-AR_-&EFP-21312 | Protection Panel (V)-GSUT and UAT Protection and Metering Signal List | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFI | IFD | [14 empty] | 2026-02-14 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3684 | LATER | SCHNEIDER | SAU4005-G161-AR_-&EPC-21313 | Protection Panel (V)-Load List and Heat Dissipation for Protection and Metering Panels | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFI | IFD | [14 empty] | 2026-01-14 |  | 2026-02-26 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3685 | LATER | SCHNEIDER | SAU4005-G161-AR_-&AQA-21314 | Protection Panel (V)-FAT Procedures for Protection and Metering Panels | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | QA/QC | General | SEPCOIII | Protection Panel | IFI | IFD | [14 empty] | 2026-02-14 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3686 | LATER | SCHNEIDER | SAU4005-G161-AR_-&AQC-21315 | Protection Panel (V)-FAT Report for Protection and Metering Panels | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | QA/QC | General | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-02-14 |  |  |  | 2026-03-06 |  |  |  | 2026-04-11 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3687 | LATER | SCHNEIDER | SAU4005-G161-AR_-&ADC-21316 | Protection Panel (V)-SAT Procedures for Protection and Metering Panels | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | QA/QC | General | SEPCOIII | Protection Panel | IFI | IFD | [14 empty] | 2026-02-14 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3688 | LATER | SCHNEIDER | SAU4005-G161-AR_-&MDC-21317 | Protection Panel (V)-Painting Procedure for Protection and Metering Panels | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Protection Panel | IFI | IFD | [14 empty] | 2026-02-15 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3689 | LATER | SCHNEIDER | SAU4005-G161-AR_-&APB-21318 | Protection Panel (V)-Recommend Spare Parts for Protection and Metering Panels | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | GENERAL | General | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-01-14 |  |  |  | 2026-02-03 |  |  |  | 2026-03-11 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3690 | LATER | SCHNEIDER | SAU4005-G161-AR_-&APC-21319 | Protection Panel (V)-Recommend Special Tools List for Protection and Metering Panels | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | GENERAL | General | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-01-14 |  |  |  | 2026-02-03 |  |  |  | 2026-03-11 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3691 | LATER | SCHNEIDER | SAU4005-G161-AR_-&ADC-21320 | Protection Panel (V)-Operation and Maintenance Manuals for Protection Relays and Meters | G161 | Commissioning | E-Electrotechnology (including control, information and communication techniques) | YES | COMMISSIONING | General | SEPCOIII | Protection Panel | IFI | IFD | [14 empty] | 2026-01-14 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3692 | LATER | SCHNEIDER | SAU4005-G161-AR_-&AQC-21321 | Protection Panel (V)-FAT ITP FOR Protection and Metering Panels | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | QA/QC | General | SEPCOIII | Protection Panel | IFI | IFD | [14 empty] | 2026-01-14 |  | 2025-12-04 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3693 | LATER | SCHNEIDER | SAU4005-G161-AR_-&ELU-21322 | Protection Panel (V)-Interface panel general arrangement drawings | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-01-30 |  | 2026-03-31 |  | 2026-02-19 |  | 2026-05-12 |  | 2026-03-27 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3694 | LATER | SCHNEIDER | SAU4005-G161-AR_-&EPC-21323 | Protection Panel (V)-Interface panel load list and heat dissipation data | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFI | IFD | [14 empty] | 2026-01-30 |  | 2026-03-05 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3695 | LATER | SCHNEIDER | SAU4005-G161-AR_-&AQC-21324 | Protection Panel (V)-End of Manufacturing Record for Protection Panels | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | QA/QC | General | SEPCOIII | Protection Panel | IFI | IFD | [14 empty] | 2026-04-09 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3696 | LATER | SIEMENS | SAU4005-G161-AR_-&EPD-21340 | Protection Panel (V)-PROTECTION PANEL LIST (BSP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFI | IFP | [14 empty] | 2026-03-15 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3697 | LATER | SIEMENS | SAU4005-G161-ARE-&EPD-21341 | Protection Panel (V)-PROTECTION RELAY LIST (BSP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFI | IFP | [14 empty] | 2026-03-15 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3698 | LATER | SIEMENS | SAU4005-G161-ARE-&EED-21342 | Protection Panel (V)-PROTECTION AC LOAD CALCULATION (BSP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3699 | LATER | SIEMENS | SAU4005-G161-ARE-&EED-21343 | Protection Panel (V)-PROTECTION DC LOAD CALCULATION (BSP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3700 | LATER | SIEMENS | SAU4005-G161-ARE-&EED-21344 | Protection Panel (V)-PROTECTION HEAT DISSIPATION CALCULATION (BSP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3701 | LATER | SIEMENS | SAU4005-G161-ARE-&EFF-21345 | Protection Panel (V)-380KV CABLE DIFFERENTIAL(GT-11) PROTN.PANEL-MAIN-1,=8C.C16A+R1 (BSP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3702 | LATER | SIEMENS | SAU4005-G161-ARE-&EFF-21346 | Protection Panel (V)-380KV CABLE DIFFERENTIAL(GT-11) PROTN.PANEL-MAIN-2,=8C.C16A+R2 (BSP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3703 | LATER | SIEMENS | SAU4005-G161-ARE-&EFF-21347 | Protection Panel (V)-380KV CABLE BACKUP(GT-11) PROTN.PANEL,=8C.C16A+R3 (BSP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3704 | LATER | SIEMENS | SAU4005-G161-ARE-&EFF-21348 | Protection Panel (V)-380KV CABLE DIFFERENTIAL(GT-12) PROTN.PANEL-MAIN-1,=8C.C22C+R1 (BSP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3705 | LATER | SIEMENS | SAU4005-G161-ARE-&EFF-21349 | Protection Panel (V)-380KV CABLE DIFFERENTIAL(GT-12) PROTN.PANEL-MAIN-2,=8C.C22C+R2 (BSP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3706 | LATER | SIEMENS | SAU4005-G161-ARE-&EFF-21350 | Protection Panel (V)-380KV CABLE BACKUP(GT-12) PROTN.PANEL,=8C.C22C+R3 (BSP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3707 | LATER | SIEMENS | SAU4005-G161-ARE-&EFF-21351 | Protection Panel (V)-380KV CABLE DIFFERENTIAL(GT-13) PROTN.PANEL-MAIN-1,=8C.C18C+R1 (BSP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3708 | LATER | SIEMENS | SAU4005-G161-ARE-&EFF-21352 | Protection Panel (V)-380KV CABLE DIFFERENTIAL(GT-13) PROTN.PANEL-MAIN-2,=8C.C18C+R2 (BSP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3709 | LATER | SIEMENS | SAU4005-G161-ARE-&EFF-21353 | Protection Panel (V)-380KV CABLE BACKUP(GT-13) PROTN.PANEL,=8C.C18C+R3 (BSP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3710 | LATER | SIEMENS | SAU4005-G161-ARE-&EFF-21354 | Protection Panel (V)-380KV CABLE DIFFERENTIAL(ST-10) PROTN.PANEL-MAIN-1,=8C.C20A+R1 (BSP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3711 | LATER | SIEMENS | SAU4005-G161-ARE-&EFF-21355 | Protection Panel (V)-380KV CABLE DIFFERENTIAL(ST-10) PROTN.PANEL-MAIN-2,=8C.C20A+R2 (BSP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3712 | LATER | SIEMENS | SAU4005-G161-ARE-&EFF-21356 | Protection Panel (V)-380KV CABLE BACKUP(ST-10) PROTN.PANEL,=8C.C20A+R3 (BSP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3713 | LATER | SIEMENS | SAU4005-G161-ARE-&EPD-21357 | Protection Panel (V)-PANEL LIST LAN (BSP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFI | IFP | [14 empty] | 2026-03-15 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3714 | LATER | SIEMENS | SAU4005-G161-AY_-&EPA-21358 | Protection Panel (V)-LAN MATERIAL LIST (BSP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFI | IFP | [14 empty] | 2026-03-15 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3715 | LATER | SIEMENS | SAU4005-G161-ARE-&EPD-21359 | Protection Panel (V)-AC/DC LOAD AND HEAT DISSIPATION LAN (BSP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFI | IFD | [14 empty] | 2026-03-15 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3716 | LATER | SIEMENS | SAU4005-G161-ARE-&EFB-21360 | Protection Panel (V)-INTERFACING ARCHITECTURE LAN (BSP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFI | IFD | [14 empty] | 2026-03-15 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3717 | LATER | SIEMENS | SAU4005-G161-AY_-&ELU-21361 | Protection Panel (V)-LAN PANEL GENERAL LAYOUT (BSP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3718 | LATER | SIEMENS | SAU4005-G161-AY_-&EFF-21362 | Protection Panel (V)-ETHERNET SWITCH PANEL,LAN-A_ +SLA-1 (BSP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3719 | LATER | SIEMENS | SAU4005-G161-AY_-&EFF-21363 | Protection Panel (V)-ETHERNET SWITCH PANEL,LAN-B_+SLB-1 (BSP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3720 | LATER | SIEMENS | SAU4005-G161-AY_-&EFF-21364 | Protection Panel (V)-SAS COMMON ALARM PANEL, +SCP1 (BSP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3721 | LATER | SIEMENS | SAU4005-G161-ARE-&EPD-21365 | Protection Panel (V)-FO Details From Relays & LAN SWITCH (BSP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFI | IFD | [14 empty] | 2026-03-15 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3722 | LATER | SIEMENS | SAU4005-G161-ARE-&EPD-21366 | Protection Panel (V)-PROTECTION PANEL LIST (IPP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFI | IFP | [14 empty] | 2026-03-15 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3723 | LATER | SIEMENS | SAU4005-G161-ARE-&EED-21367 | Protection Panel (V)-PROTECTION AC LOAD CALCULATION (IPP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3724 | LATER | SIEMENS | SAU4005-G161-ARE-&EED-21368 | Protection Panel (V)-PROTECTION DC LOAD CALCULATION (IPP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3725 | LATER | SIEMENS | SAU4005-G161-ARE-&EED-21369 | Protection Panel (V)-PROTECTION HEAT DISSIPATION CALCULATION (IPP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3726 | LATER | SIEMENS | SAU4005-G161-ARE-&EFF-21370 | Protection Panel (V)-380KV CABLE DIFFERENTIAL(GT-11) PROTN.PANEL-MAIN-1,=11ARA01+R1 (IPP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3727 | LATER | SIEMENS | SAU4005-G161-ARE-&EFF-21371 | Protection Panel (V)-380KV CABLE DIFFERENTIAL(GT-11) PROTN.PANEL-MAIN-2,=11ARA01+R2 (IPP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3728 | LATER | SIEMENS | SAU4005-G161-ARE-&EFF-21372 | Protection Panel (V)-380KV CABLE DIFFERENTIAL(GT-12) PROTN.PANEL-MAIN-1,=12ARA01+R1 (IPP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3729 | LATER | SIEMENS | SAU4005-G161-ARE-&EFF-21373 | Protection Panel (V)-380KV CABLE DIFFERENTIAL(GT-12) PROTN.PANEL-MAIN-2,=12ARA01+R2 (IPP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3730 | LATER | SIEMENS | SAU4005-G161-ARE-&EFF-21374 | Protection Panel (V)-380KV CABLE DIFFERENTIAL(GT-13) PROTN.PANEL-MAIN-1,=13ARA01+R1 (IPP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3731 | LATER | SIEMENS | SAU4005-G161-ARE-&EFF-21375 | Protection Panel (V)-380KV CABLE DIFFERENTIAL(GT-13) PROTN.PANEL-MAIN-2,=13ARA01+R2 (IPP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3732 | LATER | SIEMENS | SAU4005-G161-ARE-&EFF-21376 | Protection Panel (V)-380KV CABLE DIFFERENTIAL(ST-10) PROTN.PANEL-MAIN-1,=10ARA01+R1 (IPP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3733 | LATER | SIEMENS | SAU4005-G161-ARE-&EFF-21377 | Protection Panel (V)-380KV CABLE DIFFERENTIAL(ST-10) PROTN.PANEL-MAIN-2,=10ARA01+R2 (IPP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3734 | LATER | SIEMENS | SAU4005-G161-ARE-&EPD-21378 | Protection Panel (V)-FO Details From Relays & LAN SWITCH (IPP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFI | IFD | [14 empty] | 2026-03-15 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3735 | LATER | SIEMENS | SAU4005-G161-ARE-&EPD-21379 | Protection Panel (V)-PANEL LIST LAN (IPP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFI | IFP | [14 empty] | 2026-03-15 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3736 | LATER | SIEMENS | SAU4005-G161-AY_-&EPA-21380 | Protection Panel (V)-LAN MATERIAL LIST (IPP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFI | IFP | [14 empty] | 2026-03-15 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3737 | LATER | SIEMENS | SAU4005-G161-ARE-&EPD-21381 | Protection Panel (V)-AC/DC LOAD AND HEAT DISSIPATION LAN (IPP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFI | IFD | [14 empty] | 2026-03-15 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3738 | LATER | SIEMENS | SAU4005-G161-ARE-&EFB-21382 | Protection Panel (V)-INTERFACING ARCHITECTURE LAN (IPP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFI | IFD | [14 empty] | 2026-03-15 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3739 | LATER | SIEMENS | SAU4005-G161-AY_-&ELU-21383 | Protection Panel (V)-LAN PANEL GENERAL LAYOUT (IPP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3740 | LATER | SIEMENS | SAU4005-G161-AY_-&EFF-21384 | Protection Panel (V)-ETHERNET SWITCH PANEL,LAN-A/B-1, +SLA/B1 (IPP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3741 | LATER | SIEMENS | SAU4005-G161-AY_-&EFF-21385 | Protection Panel (V)-ETHERNET SWITCH PANEL,LAN-A/B-2, +SLA/B2 (IPP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3742 | LATER | SIEMENS | SAU4005-G161-AY_-&EFF-21386 | Protection Panel (V)-ETHERNET SWITCH PANEL,LAN-A/B-3, +SLA/B3 (IPP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3743 | LATER | SIEMENS | SAU4005-G161-AY_-&EFF-21387 | Protection Panel (V)-ETHERNET SWITCH PANEL,LAN-A/B-4, +SLA/B4 (IPP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3744 | LATER | SIEMENS | SAU4005-G161-AY_-&EFF-21388 | Protection Panel (V)-ETHERNET SWITCH PANEL,LAN-A/B-5, +SLA/B5 (IPP) | G161 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | Protection Panel | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3745 | LATER | SIEMENS | SAU4005-G161-ARE-&EQA-21389 | Protection Panel (V)-Inspection and test plan | G161 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | NO | QA/QC | General | SEPCOIII | Protection Panel | IFA | IFP |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3746 | LATER | SIEMENS | SAU4005-G161-ARE-&EQA-21390 | Protection Panel (V)-FAT procedure | G161 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | NO | QA/QC | General | SEPCOIII | Protection Panel | IFI | IFP | [14 empty] | 2026-03-15 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3747 | LATER | SIEMENS | SAU4005-G163-AY_-&EMA-21648 | Telecommunication Panel (V)-LAN PANEL GENERAL DOCUMENTS-1 | G163 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | Electrical | ELECTRICAL | SEPCOIII | Telecommunication Panel | IFI | IFD | [14 empty] | 2026-02-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3748 | LATER | SIEMENS | SAU4005-G163-AY_-&EMA-21649 | Telecommunication Panel (V)-LAN PANEL GENERAL DOCUMENTS-2 | G163 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | Electrical | ELECTRICAL | SEPCOIII | Telecommunication Panel | IFI | IFD | [14 empty] | 2026-02-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3749 | LATER | SIEMENS | SAU4005-G163-AY_-&EMA-21650 | Telecommunication Panel (V)- PANEL GENERAL DOCUMENT | G163 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | Electrical | ELECTRICAL | SEPCOIII | Telecommunication Panel | IFI | IFD | [14 empty] | 2026-02-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3750 | LATER | SIEMENS | SAU4005-G163-AY_-&EFE-21651 | Telecommunication Panel (V)-NARRATIVE OF WORK | G163 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | Electrical | ELECTRICAL | SEPCOIII | Telecommunication Panel | IFI | IFD | [14 empty] | 2026-02-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3751 | LATER | SIEMENS | SAU4005-G163-AY_-&EMA-21652 | Telecommunication Panel (V)-DRAWING CONTROL SHEET | G163 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | Electrical | ELECTRICAL | SEPCOIII | Telecommunication Panel | IFI | IFD | [14 empty] | 2026-02-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3752 | LATER | SIEMENS | SAU4005-G163-AY_-&EFB-21653 | Telecommunication Panel (V)-RTU BLOCK DIAGRAM | G163 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | Electrical | ELECTRICAL | SEPCOIII | Telecommunication Panel | IFI | IFD | [14 empty] | 2026-02-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3753 | LATER | SIEMENS | SAU4005-G163-AY_-&ELU-21654 | Telecommunication Panel (V)-GENERAL ARRANGEMENT | G163 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | Electrical | ELECTRICAL | SEPCOIII | Telecommunication Panel | IFA | IFD |  |  | 2026-02-20 |  |  |  | 2026-03-12 |  |  |  | 2026-04-17 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3754 | LATER | SIEMENS | SAU4005-G163-AY_-&EPC-21655 | Telecommunication Panel (V)-RTU CONFIGURATION TOOLS | G163 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | Electrical | ELECTRICAL | SEPCOIII | Telecommunication Panel | IFA | IFD |  |  | 2026-02-20 |  |  |  | 2026-03-12 |  |  |  | 2026-04-17 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3755 | LATER | SIEMENS | SAU4005-G163-AY_-&EED-21656 | Telecommunication Panel (V)-RTU POWER CONSUMPTION CALCULATION | G163 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | Electrical | ELECTRICAL | SEPCOIII | Telecommunication Panel | IFA | IFD |  |  | 2026-02-20 |  |  |  | 2026-03-12 |  |  |  | 2026-04-17 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3756 | LATER | SIEMENS | SAU4005-G163-AY_-&EQA-21657 | Telecommunication Panel (V)-FAT PROCEDURE | G163 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | Electrical | ELECTRICAL | SEPCOIII | Telecommunication Panel | IFI | IFD | [14 empty] | 2026-02-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3757 | LATER | SIEMENS | SAU4005-G163-AY_-&EQA-21658 | Telecommunication Panel (V)-SAT PROCEDURE | G163 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | Electrical | ELECTRICAL | SEPCOIII | Telecommunication Panel | IFI | IFD | [14 empty] | 2026-02-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3758 | LATER | SIEMENS | SAU4005-G163-AY_-&EDA-21659 | Telecommunication Panel (V)-RTU DATA SHEET | G163 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | Electrical | ELECTRICAL | SEPCOIII | Telecommunication Panel | IFA | IFD |  |  | 2026-02-20 |  |  |  | 2026-03-12 |  |  |  | 2026-04-17 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3759 | LATER | SIEMENS | SAU4005-G163-AY_-&EMB-21660 | Telecommunication Panel (V)-CABLE LIST | G163 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | Electrical | ELECTRICAL | SEPCOIII | Telecommunication Panel | IFI | IFD | [14 empty] | 2026-02-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3760 | LATER | SIEMENS | SAU4005-G163-AY_-&EMA-21661 | Telecommunication Panel (V)-INTERFACE PANEL | G163 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | Electrical | ELECTRICAL | SEPCOIII | Telecommunication Panel | IFI | IFD | [14 empty] | 2026-02-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3761 | LATER | SIEMENS | SAU4005-G163-AY_-&EFF-21662 | Telecommunication Panel (V)-CIRCUIT DIAGRAM | G163 | Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | Electrical | ELECTRICAL | SEPCOIII | Telecommunication Panel | IFI | IFD | [14 empty] | 2026-02-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3762 | LATER | SIEMENS FMS | SAU4005-G165-CEJ-&EMA-21900 | FMS (V)-UNIT 10 FAULT RECORD PANEL | G165 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | FMS | IFI | IFD | [14 empty] | 2026-03-15 |  | 2026-02-02 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3763 | LATER | SIEMENS FMS | SAU4005-G165-CEJ-&EMA-21901 | FMS (V)-UNIT 11 FAULT RECORD PANEL 1 | G165 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | FMS | IFI | IFD | [14 empty] | 2026-03-15 |  | 2026-02-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3769 | LATER | SIEMENS FMS | SAU4005-G165-CEJ-&EMA-21907 | FMS (V)-FAULT RECORD PANEL | G165 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | FMS | IFI | IFD | [14 empty] | 2026-03-15 |  | 2026-02-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3770 | LATER | SIEMENS FMS | SAU4005-G165-CEJ-&EMA-21908 | FMS (V)-BSDG FAULT RECORD PANEL 1 | G165 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | FMS | IFI | IFD | [14 empty] | 2026-03-15 |  | 2026-02-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3771 | LATER | SIEMENS FMS | SAU4005-G165-CEJ-&EMA-21909 | FMS (V)-BSDG FAULT RECORD PANEL 2 | G165 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | FMS | IFI | IFD | [14 empty] | 2026-03-15 |  | 2026-02-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3772 | LATER | SIEMENS FMS | SAU4005-G165-CEJ-&EMA-21910 | FMS (V)-400V FIN FAN FAULT RECORD PANEL | G165 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | FMS | IFI | IFD | [14 empty] | 2026-03-15 |  | 2026-02-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3773 | LATER | SIEMENS FMS | SAU4005-G165-CEJ-&EMA-21911 | FMS (V)-400V ADMIN FAULT RECORD PANEL | G165 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | FMS | IFI | IFD | [14 empty] | 2026-03-15 |  | 2026-02-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3774 | LATER | SIEMENS FMS | SAU4005-G165-CEJ-&EMA-21912 | FMS (V)-400V BOP FAULT RECORD PANEL | G165 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | FMS | IFI | IFD | [14 empty] | 2026-03-15 |  | 2026-02-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3775 | LATER | SIEMENS FMS | SAU4005-G165-CEJ-&EMA-21913 | FMS (V)-400V GAS FAULT RECORD PANEL | G165 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | FMS | IFI | IFD | [14 empty] | 2026-03-15 |  | 2026-02-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3776 | LATER | SIEMENS FMS | SAU4005-G165-CEJ-&EMA-21914 | FMS (V)-600V ACC FAULT RECORD PANEL | G165 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | FMS | IFI | IFD | [14 empty] | 2026-03-15 |  | 2026-02-02 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3777 | LATER | SIEMENS FMS | SAU4005-G165-CEJ-&EFA-21915 | FMS (V)-NETWORK INTERFACE & SERVER PANEL | G165 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | FMS | IFI | IFD | [14 empty] | 2026-03-15 |  | 2026-02-03 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3778 | LATER | SIEMENS FMS | SAU4005-G165-CEJ-&EQA-21916 | FMS (V)-ITP | G165 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | YES | QA/QC | General | SEPCOIII | FMS | IFA | IFD |  |  | 2026-03-15 |  |  |  | 2026-04-04 |  |  |  | 2026-05-10 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| DCC CHANGED | 3779 | LATER | SIEMENS FMS | SAU4005-G165-CEJ-&EQC-21917 | FMS (V)-FAT | G165 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | YES | QA/QC | General | SEPCOIII | FMS | IFA | IFD |  |  | 2026-03-15 |  | 2026-04-02 |  | 2026-04-04 |  | 2026-04-21 |  | 2026-05-10 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3780 | LATER | JEDDAH CABLES | SAU4005-G168-ACA-&EED-22200 | EHV CABLES (V)-Ampacity calculations for EHV cable | G168 | EN-Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | EHV CABLES | IFA | IFD |  |  | 2026-03-24 |  |  |  | 2026-04-13 |  |  |  | 2026-05-19 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3781 | LATER | JEDDAH CABLES | SAU4005-G168-ACA-&EED-22201 | EHV CABLES (V)-Induced Voltage Calculation for EHV cable | G168 | EN-Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | EHV CABLES | IFA | IFD |  |  | 2026-01-29 |  |  |  | 2026-02-18 |  |  |  | 2026-03-26 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3782 | LATER | JEDDAH CABLES | SAU4005-G168-ACA-&EDD-22202 | EHV CABLES (V)-Cable connection module for transformer and GIS sides | G168 | EN-Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | EHV CABLES | IFI | IFD | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3783 | LATER | JEDDAH CABLES | SAU4005-G168-ACA-&EDD-22203 | EHV CABLES (V)-Technical Submittal for Link Boxes | G168 | EN-Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | EHV CABLES | IFI | IFD | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3784 | LATER | JEDDAH CABLES | SAU4005-G168-ACA-&EDD-22204 | EHV CABLES (V)-JCC SINGLE CORE BONDING 1X500 CABLE | G168 | EN-Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | EHV CABLES | IFI | IFD | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3785 | LATER | JEDDAH CABLES | SAU4005-G168-ACA-&EDD-22205 | EHV CABLES (V)-JCC EARTHING 1X500 CABLE | G168 | EN-Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | EHV CABLES | IFI | IFD | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3786 | LATER | JEDDAH CABLES | SAU4005-G168-ACA-&EDD-22206 | EHV CABLES (V)-JCC 380kV EHV POWER CABLE | G168 | EN-Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | ELECTRICAL | Electrical | SEPCOIII | EHV CABLES | IFI | IFD | [14 empty] | 2026-02-02 |  | 2026-02-12 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3787 | LATER | JEDDAH CABLES | SAU4005-G168-ACA-&EQA-22207 | EHV CABLES (V)-EHV Cable Inspection and Test Plan | G168 | QA-Quality Assurance/Quality Control Supply | E-Electrotechnology (including control, information and communication techniques) | YES | QA/QC | General | SEPCOIII | EHV CABLES | IFA | IFP |  |  | 2026-02-02 |  | 2026-02-12 |  | 2026-02-22 |  | 0 |  | 2026-03-30 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| DCC CHANGED | 3788 | LATER | JEDDAH CABLES | SAU4005-G168-ACA-&EQC-22208 | EHV CABLES (V)-EHV Cable FAT Procedure | G168 | QA-Quality Assurance/Quality Control Supply | E-Electrotechnology (including control, information and communication techniques) | YES | QA/QC | General | SEPCOIII | EHV CABLES | IFI | IFP | [14 empty] | 2026-02-02 |  | 2026-05-06 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3789 | LATER | JEDDAH CABLES | SAU4005-G168-ACA-&EQC-22209 | EHV CABLES (V)-EHV Cable Type Test Certificate | G168 | QA-Quality Assurance/Quality Control Supply | E-Electrotechnology (including control, information and communication techniques) | YES | QA/QC | General | SEPCOIII | EHV CABLES | IFA | IFP |  |  | 2026-02-02 |  |  |  | 2026-02-22 |  |  |  | 2026-03-30 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3790 | LATER | JEDDAH CABLES | SAU4005-G168-ACA-&EQA-22210 | EHV CABLES (V)-EHV Cable End of Manufacturing Report | G168 | QA-Quality Assurance/Quality Control Supply | E-Electrotechnology (including control, information and communication techniques) | YES | QA/QC | General | SEPCOIII | EHV CABLES | IFI | IFP | [14 empty] | 2026-03-01 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3791 | LATER | JEDDAH CABLES | SAU4005-G168-ACA-&EDD-22211 | EHV CABLES (V)-Conductor and Shield size selection based on Voltage drop restrictions , short circuit current and duration | G168 | EN-Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | EHV CABLES | IFI | IFD | [14 empty] | 2026-03-01 |  | 2026-02-13 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3792 | LATER | JEDDAH CABLES | SAU4005-G168-ACA-&EQA-22212 | EHV CABLES (V)-Quality Dossier | G168 | QA-Quality Assurance/Quality Control Supply | E-Electrotechnology (including control, information and communication techniques) | YES | QA/QC | General | SEPCOIII | EHV CABLES | IFI | IFP | [14 empty] | 2026-03-01 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3793 | LATER | JEDDAH CABLES | SAU4005-G168-ACA-&EQA-22213 | EHV CABLES (V)-EHV Cable accessories Inspection and Test Plan | G168 | QA-Quality Assurance/Quality Control Supply | E-Electrotechnology (including control, information and communication techniques) | YES | QA/QC | General | SEPCOIII | EHV CABLES | IFA | IFP |  |  | 2026-03-01 |  |  |  | 2026-03-21 |  |  |  | 2026-04-26 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3794 | LATER | JEDDAH CABLES | SAU4005-G168-ACA-&EED-22214 | EHV CABLES (V)-Short circuit calculation for conductor | G168 | EN-Engineering | E-Electrotechnology (including control, information and communication techniques) | NO | ELECTRICAL | Electrical | SEPCOIII | EHV CABLES | IFA | IFD |  |  | 2026-03-01 |  | 2026-02-13 |  | 2026-03-21 |  | 2026-02-26 |  | 2026-04-26 |  | 2026-05-20 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | YES
| NEW | 3795 | LATER | BML | SAU4005-G175-AQA-&EAB-22900 | PSS(V)-PSS Master document list | G175 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | PSS | IFA | IFD |  |  | 2026-02-15 |  |  |  | 2026-03-07 |  |  |  | 2026-04-12 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3796 | LATER | BML | SAU4005-G175-AQA-&EIP-22900 | PSS(V)-BASE DESIGN FOR MDA & PSS PANELS | G175 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | PSS | IFA | IFD |  |  | 2026-02-19 |  |  |  | 2026-03-11 |  |  |  | 2026-04-16 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3797 | LATER | BML | SAU4005-G175-AQA-&EIP-22901 | PSS(V)-BASE DESIGN FOR DATALOGGER PANELS | G175 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | PSS | IFA | IFD |  |  | 2026-02-20 |  |  |  | 2026-03-12 |  |  |  | 2026-04-17 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3798 | LATER | BML | SAU4005-G175-AQA-&EFF-22913 | PSS(V)-STRUCTURE ARCHITECTURE OF SETTLEMENT SYSTEM | G175 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | PSS | IFA | IFD |  |  | 2026-02-21 |  | 2026-03-23 |  | 2026-03-13 |  | 0 |  | 2026-04-18 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3799 | LATER | BML | SAU4005-G175-AQA-&EDA-22902 | PSS(V)-DETAIL DESIGN FOR CORE MDA PANEL | G175 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | PSS | IFA | IFC |  |  | 2026-03-17 |  |  |  | 2026-04-06 |  |  |  | 2026-05-12 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3800 | LATER | BML | SAU4005-G175-AQA-&EDA-22903 | PSS(V)-DETAIL DESIGN FOR SECONDARY MDA & PSS PANEL | G175 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | PSS | IFA | IFC |  |  | 2026-03-17 |  |  |  | 2026-04-06 |  |  |  | 2026-05-12 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3801 | LATER | BML | SAU4005-G175-AQA-&EDA-22904 | PSS(V)-DETAIL DESIGN FOR DATALOGGER PANELS | G175 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | PSS | IFA | IFC |  |  | 2026-03-17 |  |  |  | 2026-04-06 |  |  |  | 2026-05-12 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3802 | LATER | BML | SAU4005-G175-AQA-&EFP-22905 | PSS(V)-FUNCTIONAL DESIGN SPECIFICATION (FDS) FOR MDA SYSTEM | G175 | Engineering | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | PSS | IFA | IFD |  |  | 2026-04-22 |  |  |  | 2026-05-12 |  |  |  | 2026-06-17 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3803 | LATER | BML | SAU4005-G175-AQA-&EQA-22907 | PSS(V)-FAT PROCEDURE FOR CORE MDA PANEL | G175 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | PSS | IFA | IFD |  |  | 2026-05-05 |  |  |  | 2026-05-25 |  |  |  | 2026-06-30 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3804 | LATER | BML | SAU4005-G175-AQA-&EQA-22908 | PSS(V)-FAT PROCEDURE FOR SECONDARY MDA & PSS PANEL | G175 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | PSS | IFA | IFD |  |  | 2026-05-05 |  |  |  | 2026-05-25 |  |  |  | 2026-06-30 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3805 | LATER | BML | SAU4005-G175-AQA-&EQA-22909 | PSS(V)-FAT PROCEDURE FOR DATALOGGER PANELS | G175 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | PSS | IFA | IFD |  |  | 2026-05-05 |  |  |  | 2026-05-25 |  |  |  | 2026-06-30 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3806 | LATER | BML | SAU4005-G175-AQA-&BQC-22922 | PSS(V)-ITP FOR CORE MDA PANEL | G175 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | PSS | IFA | IFD |  |  | 2026-05-05 |  |  |  | 2026-05-25 |  |  |  | 2026-06-30 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3807 | LATER | BML | SAU4005-G175-AQA-&BQC-22923 | PSS(V)-ITP FOR SECONDARY MDA & PSS PANEL | G175 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | PSS | IFA | IFD |  |  | 2026-05-05 |  |  |  | 2026-05-25 |  |  |  | 2026-06-30 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3808 | LATER | BML | SAU4005-G175-AQA-&BQC-22924 | PSS(V)-ITP FOR DATALOGGER PANELS | G175 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | PSS | IFA | IFD |  |  | 2026-05-05 |  |  |  | 2026-05-25 |  |  |  | 2026-06-30 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3809 | LATER | BML | SAU4005-G175-AQA-&BQC-22915 | PSS(V)-FAT REPORT FOR CORE MDA PANEL | G175 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | PSS | IFA | IFD |  |  | 2026-09-19 |  |  |  | 2026-10-09 |  |  |  | 2026-11-14 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3810 | LATER | BML | SAU4005-G175-AQA-&BQC-22916 | PSS(V)-FAT REPORT FOR SECONDARY MDA & PSS PANEL | G175 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | PSS | IFA | IFD |  |  | 2026-09-19 |  |  |  | 2026-10-09 |  |  |  | 2026-11-14 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3811 | LATER | BML | SAU4005-G175-AQA-&BQC-22917 | PSS(V)-FAT REPORT FOR DATALOGGER PANELS | G175 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | PSS | IFA | IFD |  |  | 2026-09-19 |  |  |  | 2026-10-09 |  |  |  | 2026-11-14 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3812 | LATER | BML | SAU4005-G175-AQA-&EA-22910 | PSS(V)-SAT PROCEDURE FOR CORE MDA PANEL | G175 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | PSS | IFA | IFD |  |  | 2026-05-31 |  |  |  | 2026-06-20 |  |  |  | 2026-07-26 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3813 | LATER | BML | SAU4005-G175-AQA-&EQA-22911 | PSS(V)-SAT PROCEDURE FOR SECONDARY MDA & PSS PANEL | G175 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | PSS | IFA | IFD |  |  | 2026-05-31 |  |  |  | 2026-06-20 |  |  |  | 2026-07-26 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3814 | LATER | BML | SAU4005-G175-AQA-&EQA-22912 | PSS(V)-SAT PROCEDURE FOR DATALOGGER PANELS | G175 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | PSS | IFA | IFD |  |  | 2026-05-31 |  |  |  | 2026-06-20 |  |  |  | 2026-07-26 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3815 | LATER | BML | SAU4005-G175-AQA-&BQC-22918 | PSS(V)-SAT REPORT FOR CORE MDA PANEL | G175 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | PSS | IFA | IFD |  |  | 2027-01-12 |  |  |  | 2027-02-01 |  |  |  | 2027-03-09 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3816 | LATER | BML | SAU4005-G175-AQA-&BQC-22919 | PSS(V)-SAT REPORT FOR SECONDARY MDA & PSS PANEL | G175 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | PSS | IFA | IFD |  |  | 2027-01-12 |  |  |  | 2027-02-01 |  |  |  | 2027-03-09 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3817 | LATER | BML | SAU4005-G175-AQA-&BQC-22920 | PSS(V)-SAT REPORT FOR DATALOGGER PANELS | G175 | QA/QC | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | PSS | IFA | IFD |  |  | 2027-01-12 |  |  |  | 2027-02-01 |  |  |  | 2027-03-09 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3818 | LATER | BML | SAU4005-G175-AQA-&EDE-22921 | PSS(V)-O&M MANUAL FOR SETTLEMENT SYSTEM | G175 | Operation & Maintenacne | E-Electrotechnology (including control, information and communication techniques) | Yes | I&C&DCS | Instrumentation and Control | SEPCOIII | PSS | IFI | IFC | [14 empty] | 2027-01-12 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3819 | LATER | SUZHOU DELAN | SAU4005-G187-ZEN-&MDA-25801 | Control and on off Valves（V）-GA Drawings | G187 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Control and on off Valves | IFA | IFD |  |  | 2026-01-20 |  |  |  | 2026-02-09 |  |  |  | 2026-03-17 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3820 | LATER | SUZHOU DELAN | SAU4005-G187-ZEN-&MDA-25802 | Control and on off Valves（V）-Data Sheets | G187 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Control and on off Valves | IFA | IFD |  |  | 2026-01-20 |  |  |  | 2026-02-09 |  |  |  | 2026-03-17 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3821 | LATER | SUZHOU DELAN | SAU4005-G187-ZEN-&MDA-25803 | Control and on off Valves（V）-Wiring drawing | G187 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Control and on off Valves | IFI | IFD | [14 empty] | 2026-01-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3822 | LATER | SUZHOU DELAN | SAU4005-G187-ZEN-&MQA-25804 | Control and on off Valves（V）-Inspection & Test Plan (ITP) | G187 | QA/QC | QA/QC | YES | QA/QC | General | SEPCOIII | Control and on off Valves | IFA | IFD |  |  | 2026-01-20 |  | 2026-01-26 |  | 2026-02-09 |  | 0 |  | 2026-03-17 |  | 2026-03-29 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3823 | LATER | SUZHOU DELAN | SAU4005-G187-ZEN-&MEC-25805 | Control and on off Valves（V）-Testing Procedure | G187 | QA/QC | QA/QC | YES | QA/QC | General | SEPCOIII | Control and on off Valves | IFI | IFD | [14 empty] | 2026-01-20 |  | 2026-01-27 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| DCC CHANGED | 3824 | LATER | SUZHOU DELAN | SAU4005-G187-ZEN-&MQA-25806 | Control and on off Valves（V）-Painting Procedure | G187 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Control and on off Valves | IFA | IFD |  |  | 2026-01-20 |  |  |  | 2026-02-09 |  |  |  | 2026-03-17 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3825 | LATER | SUZHOU DELAN | SAU4005-G187-ZEN-&MEC-25807 | Control and on off Valves（V）-Material Test Certificates | G187 | QA/QC | QA/QC | YES | QA/QC | General | SEPCOIII | Control and on off Valves | IFI | IFD | [14 empty] | 2026-01-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3826 | LATER | SUZHOU DELAN | SAU4005-G187-ZEN-&MDC-25808 | Control and on off Valves（V）-O & M Manual | G187 | QA/QC | QA/QC | YES | O&M | General | SEPCOIII | Control and on off Valves | IFI | IFC | [14 empty] | 2026-01-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3827 | LATER | SUZHOU DELAN | SAU4005-G187-ZEN-&MDA-25809 | Control and on off Valves（V）-Actuator sizing calculation | G187 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Control and on off Valves | IFI | IFD | [14 empty] | 2026-01-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3828 | LATER | SUZHOU DELAN | SAU4005-G187-ZEN-&MPD-25810 | Control and on off Valves（V）-Valve List | G187 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Control and on off Valves | IFI | IFD | [14 empty] | 2026-01-20 |  | 2025-12-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3829 | LATER | SUZHOU DELAN | SAU4005-G187-ZEN-&MDC-25811 | Control and on off Valves（V）-Nameplate Drawing | G187 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Control and on off Valves | IFI | IFD | [14 empty] | 2026-01-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3830 | LATER | SUZHOU DELAN | SAU4005-G187-ZEN-&MEC-25812 | Control and on off Valves（V）-Calibration Test Certificate | G187 | QA/QC | QA/QC | YES | QA/QC | General | SEPCOIII | Control and on off Valves | IFI | IFD | [14 empty] | 2026-01-20 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3831 | LATER | SUZHOU DELAN | SAU4005-G187-ZEN-&MDA-25813 | Control and on off Valves（V）-Terminal Box Outline Diagram | G187 | Engineering | M-Mechanical engineering (normally including process engineering) | YES | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Control and on off Valves | IFI | IFD | [14 empty] | 2026-01-20 |  | 2025-12-29 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3832 | LATER | CHUAN YI | SAU4005-G191-C__-&EBA-26300 | Field Instrument(V)-MDL | G191 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFI | IFD | [14 empty] | 2026-01-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3833 | LATER | CHUAN YI | SAU4005-G191-C__-&EDA-26301 | Field Instrument(V)-Datesheet for Level Transmitter | G191 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFA | IFD |  |  | 2026-02-19 |  | 2026-01-23 |  | 2026-03-11 |  | 2026-02-09 |  | 2026-04-15 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3834 | LATER | CHUAN YI | SAU4005-G191-C__-&EDA-26302 | Field Instrument(V)-Datesheet for Flow Orifice | G191 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFA | IFD |  |  | 2026-02-09 |  | 2026-02-25 |  | 2026-03-01 |  | 2026-02-05 |  | 2026-04-05 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3835 | LATER | CHUAN YI | SAU4005-G191-C__-&EDA-26303 | Field Instrument(V)-Datesheet for Flow Transmitter | G191 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFA | IFD |  |  | 2026-02-19 |  | 2026-01-20 |  | 2026-03-11 |  | 2026-02-05 |  | 2026-04-15 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3836 | LATER | CHUAN YI | SAU4005-G191-C__-&EDA-26304 | Field Instrument(V)-Datesheet for Temperature Transmitter& Temperature Indicator | G191 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFA | IFD |  |  | 2026-02-09 |  | 2026-01-23 |  | 2026-03-01 |  | 2026-02-05 |  | 2026-04-05 |  | 2026-05-10 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3837 | LATER | CHUAN YI | SAU4005-G191-C__-&EDA-26332 | Field Instrument(V)-Thermowell Wake frequency Calculation for Thermowell | G191 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFI | IFD | [14 empty] | 2026-02-10 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3838 | LATER | CHUAN YI | SAU4005-G191-C__-&EDA-26305 | Field Instrument(V)-Datesheet for Level Indicator | G191 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFA | IFD |  |  | 2026-02-19 |  | 2026-02-09 |  | 2026-03-11 |  | 2026-02-24 |  | 2026-04-15 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3839 | LATER | CHUAN YI | SAU4005-G191-C__-&EDA-26306 | Field Instrument(V)-Datesheet for Pressure Gauge | G191 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFA | IFD |  |  | 2026-02-19 |  | 2026-01-23 |  | 2026-03-11 |  | 2026-02-05 |  | 2026-04-15 |  | 2026-03-29 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3840 | LATER | CHUAN YI | SAU4005-G191-C__-&EDA-26307 | Field Instrument(V)-Datesheet for Analyzer | G191 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFA | IFD |  |  | 2026-02-09 |  | 2026-01-19 |  | 2026-03-01 |  | 0 |  | 2026-04-05 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3841 | LATER | CHUAN YI | SAU4005-G191-C__-&EDA-26308 | Field Instrument(V)-Datesheet for Pressure &Pressure Differential Transmitter | G191 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFA | IFD |  |  | 2026-02-09 |  | 2026-02-25 |  | 2026-03-01 |  | 2026-03-15 |  | 2026-04-05 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3842 | LATER | CHUAN YI | SAU4005-G191-C__-&EDA-26309 | Field Instrument(V)-Datesheet for Pressure Switch | G191 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFA | IFD |  |  | 2026-02-19 |  | 2026-01-23 |  | 2026-03-11 |  | 2026-02-05 |  | 2026-04-15 |  | 2026-05-06 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3843 | LATER | CHUAN YI | SAU4005-G191-C__-&EDA-26310 | Field Instrument(V)-Datesheet for Flow Switch | G191 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFA | IFD |  |  | 2026-02-19 |  | 2026-01-20 |  | 2026-03-11 |  | 2026-02-05 |  | 2026-04-15 |  | 2026-05-03 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3844 | LATER | CHUAN YI | SAU4005-G191-C__-&EDA-26311 | Field Instrument(V)-Datesheet for Junction Box | G191 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFA | IFD |  |  | 2026-02-09 |  | 2026-01-20 |  | 2026-03-01 |  | 0 |  | 2026-04-05 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3845 | LATER | CHUAN YI | SAU4005-G191-C__-&EDA-26312 | Field Instrument(V)-Junction Box GA & layout drawings | G191 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFI | IFD | [14 empty] | 2026-02-09 |  | 2026-01-20 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3846 | LATER | CHUAN YI | SAU4005-G191-C__-&EDA-26313 | Field Instrument(V)-Complete BOQ for Field instruments and its accessories | G191 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFI | IFD | [14 empty] | 2026-02-19 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3847 | LATER | CHUAN YI | SAU4005-G191-C__-&EDA-26314 | IField Instrument(V)-nstruments list for Weather Sataion | G191 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFI | IFD | [14 empty] | 2026-02-09 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3848 | LATER | CHUAN YI | SAU4005-G191-C__-&EDA-26315 | Field Instrument(V)-Hook-up´s details of Weather Sataion | G191 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFI | IFD | [14 empty] | 2026-02-19 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3849 | LATER | CHUAN YI | SAU4005-G191-C__-&EDA-26316 | Field Instrument(V)-GA & layout drawings for Weather Sataion | G191 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFI | IFD | [14 empty] | 2026-02-09 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3850 | LATER | CHUAN YI | SAU4005-G191-C__-&EDA-26317 | Field Instrument(V)-Wiring diagrams for Weather Sataion | G191 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFI | IFD | [14 empty] | 2026-02-19 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3851 | LATER | CHUAN YI | SAU4005-G191-C__-&EDA-26318 | Field Instrument(V)-List of signals and alarms (I/O list) for Weather Sataion | G191 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFI | IFD | [14 empty] | 2026-02-09 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3852 | LATER | CHUAN YI | SAU4005-G191-C__-&EDA-26319 | Field Instrument(V)-Cable list for Weather Sataion | G191 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFI | IFD | [14 empty] | 2026-02-19 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3853 | LATER | CHUAN YI | SAU4005-G191-C__-&EDA-26320 | Field Instrument(V)-UPS & Non-UPS load list for Weather Sataion | G191 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFI | IFD | [14 empty] | 2026-02-09 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3854 | LATER | CHUAN YI | SAU4005-G191-C__-&EDA-26321 | IField Instrument(V)-nstallation & Foundation drawings for Weather Sataion | G191 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFI | IFD | [14 empty] | 2026-02-09 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3855 | LATER | CHUAN YI | SAU4005-G191-C__-&BDC-26322 | Field Instrument(V)-Manual for Level Transmitter | G191 | Operation & Maintenance | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFI | IFD | [14 empty] | 2026-02-19 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3856 | LATER | CHUAN YI | SAU4005-G191-C__-&BDC-26323 | Field Instrument(V)-Manual for Flow Orifice | G191 | Operation & Maintenance | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFI | IFD | [14 empty] | 2026-02-19 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3857 | LATER | CHUAN YI | SAU4005-G191-C__-&BDC-26324 | Field Instrument(V)-Manual for Flow Transmitter | G191 | Operation & Maintenance | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFI | IFD | [14 empty] | 2026-02-19 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3858 | LATER | CHUAN YI | SAU4005-G191-C__-&BDC-26325 | Field Instrument(V)-Manual for Temperature Transmitter& Temperature Indicato | G191 | Operation & Maintenance | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFI | IFD | [14 empty] | 2026-02-19 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3859 | LATER | CHUAN YI | SAU4005-G191-C__-&BDC-26326 | Field Instrument(V)-Manual for Level Indicator | G191 | Operation & Maintenance | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFI | IFD | [14 empty] | 2026-02-19 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3860 | LATER | CHUAN YI | SAU4005-G191-C__-&BDC-26327 | Field Instrument(V)-Manual for Pressure Gauge | G191 | Operation & Maintenance | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFI | IFD | [14 empty] | 2026-02-19 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3861 | LATER | CHUAN YI | SAU4005-G191-C__-&BDC-26328 | Field Instrument(V)-Manual for Analyzer | G191 | Operation & Maintenance | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFI | IFD | [14 empty] | 2026-02-19 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3862 | LATER | CHUAN YI | SAU4005-G191-C__-&BDC-26329 | Field Instrument(V)-Manual for Pressure &Pressure Differential Transmitter | G191 | Operation & Maintenance | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFI | IFD | [14 empty] | 2026-02-19 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3863 | LATER | CHUAN YI | SAU4005-G191-C__-&BDC-26330 | Field Instrument(V)-Manual for Pressure Switch | G191 | Operation & Maintenance | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFI | IFD | [14 empty] | 2026-02-19 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3864 | LATER | CHUAN YI | SAU4005-G191-C__-&BDC-26331 | Field Instrument(V)-Manual for Flow Switch | G191 | Operation & Maintenance | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFI | IFD | [14 empty] | 2026-02-19 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3865 | LATER | CHUAN YI | SAU4005-G191-C__-&BDC-26332 | Field Instrument(V)-Manual for Weather station | G191 | Operation & Maintenance | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFI | IFD | [14 empty] | 2026-02-19 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3866 | LATER | CHUAN YI | SAU4005-G191-C__-&AQA-26333 | IField Instrument(V)-TP for Field Instrument | G191 | QA/QC | A-Overall Management | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFA | IFC |  |  | 2026-02-19 |  | 2026-01-20 |  | 2026-03-11 |  | 0 |  | 2026-04-15 |  | 2026-04-12 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3867 | LATER | CHUAN YI | SAU4005-G191-C__-&AQA-26329 | Field Instrument(V)-FAT Report for Instrument package | G191 | QA/QC | A-Overall Management | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFA | IFC |  |  | 2026-04-19 |  |  |  | 2026-05-09 |  |  |  | 2026-06-13 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3868 | LATER | CHUAN YI | SAU4005-G191-C__-&AQA-26334 | Field Instrument(V)-Test Procedure for Instrument package | G191 | Operation & Maintenance | A-Overall Management | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFA | IFC |  |  | 2026-02-19 |  | 2026-01-20 |  | 2026-03-11 |  | 2026-03-12 |  | 2026-04-15 |  | 2026-03-26 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3869 | LATER | CHUAN YI | SAU4005-G191-C__-&AQA-26335 | Field Instrument(V)-Complete BOQ for Field instruments and its accessories | G191 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFI | IFD | [14 empty] | 2026-03-12 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3870 | LATER | CHUAN YI | SAU4005-G191-C__-&EDA-26336 | Field Instrument(V)-Datesheet for Weather Sataion | G191 | Engineering | E-Electrotechnology (including control, information and communication techniques) | YES | I&C&DCS | Instrumentation and Control | SEPCOIII | Field Instrument | IFA | IFD |  |  | 2026-03-15 |  | 2026-03-04 |  | 2026-04-05 |  | 2026-03-29 |  | 2026-05-11 |  | 2026-04-26 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | Yes | Yes | NO
| NEW | 3871 | LATER | Beijingkaitong | SAU4005-G201-ZEN-&MLU-10430 | Piping Specialties(V)-MDL | G201 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Piping Specialties | IFI | [15 empty] | 2026-01-25 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3872 | LATER | Beijingkaitong | SAU4005-G201-ZEN-&MLU-10431 | Piping Specialties(V)-SIGHT FLOW INDICATOR GA Drawings | G201 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Piping Specialties | IFA |  |  |  | 2026-01-25 |  |  |  | 2026-02-14 |  |  |  | 2026-03-22 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3873 | LATER | Beijingkaitong | SAU4005-G201-ZEN-&MLU-10432 | Piping Specialties(V)-STRAINER Gl41P-150LB GA Drawings | G201 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Piping Specialties | IFA |  |  |  | 2026-01-25 |  |  |  | 2026-02-14 |  |  |  | 2026-03-22 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3874 | LATER | Beijingkaitong | SAU4005-G201-ZEN-&MLU-10433 | Piping Specialties(V)-STRAINER Gl41P-150LBPL GA Drawings | G201 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Piping Specialties | IFA |  |  |  | 2026-01-25 |  |  |  | 2026-02-14 |  |  |  | 2026-03-22 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3875 | LATER | Beijingkaitong | SAU4005-G201-ZEN-&MLU-10434 | Piping Specialties(V)-Espansion Joint（DN125-DN500） GA Drawings | G201 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Piping Specialties | IFA |  |  |  | 2026-01-25 |  |  |  | 2026-02-14 |  |  |  | 2026-03-22 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3876 | LATER | Beijingkaitong | SAU4005-G201-ZEN-&MLU-10435 | Piping Specialties(V)-Espansion Joint（DN800） GA Drawings | G201 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | MECH&PROCESS&WTP | Mechanical | SEPCOIII | Piping Specialties | IFA |  |  |  | 2026-01-25 |  |  |  | 2026-02-14 |  |  |  | 2026-03-22 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3877 | LATER | MAJD | SAU4005-G280-ZEN-&MQA-03601 | Steel Structure (V)- PAINTING PROCEDURE | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | GENERAL | General | SEPCOIII | Steel Structure | IFA | IFD |  |  | 2026-01-29 |  | 2025-11-02 |  | 2026-02-18 |  | 2025-12-09 |  | 2026-03-26 |  | 2026-01-14 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3878 | LATER | MAJD | SAU4005-G280-ZEN-&MEC-03602 | Steel Structure (V)- WELDING PROCEDURE | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | GENERAL | General | SEPCOIII | Steel Structure | IFA | IFD |  |  | 2026-03-22 |  |  |  | 2026-04-11 |  |  |  | 2026-05-17 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3879 | LATER | MAJD | SAU4005-G280-ZEN-&MQA-03603 | Steel Structure (V)- INSPECTION AND TEST PLAN | G280 | QA/QC | M-Mechanical engineering (normally including process engineering) | NO | QA/QC | General | SEPCOIII | Steel Structure | IFA | IFD |  |  | 2026-01-29 |  | 2025-11-24 |  | 2026-02-18 |  | 2025-12-11 |  | 2026-03-26 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3880 | LATER | MAJD | SAU4005-G280-ZEN-&MQA-03604 | Steel Structure (V)- NDT PROCEDURE | G280 | QA/QC | M-Mechanical engineering (normally including process engineering) | NO | QA/QC | General | SEPCOIII | Steel Structure | IFA | IFD |  |  | 2026-01-29 |  | 2025-12-10 |  | 2026-02-18 |  | 2026-01-25 |  | 2026-03-26 |  | 0 | [23 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3881 | LATER | MAJD | SAU4005-G280-ZEN-&MQC-03605 | Steel Structure (V)- REPORT FOR 1st BATCH | G280 | QA/QC | M-Mechanical engineering (normally including process engineering) | NO | QA/QC | General | SEPCOIII | Steel Structure | IFA | IFD |  |  | 2026-03-22 |  |  |  | 2026-04-11 |  |  |  | 2026-05-17 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3882 | LATER | MAJD | SAU4005-G280-ZEN-&MQC-03606 | Steel Structure (V)- REPORT FOR 2nd BATCH | G280 | QA/QC | M-Mechanical engineering (normally including process engineering) | NO | QA/QC | General | SEPCOIII | Steel Structure | IFA | IFD |  |  | 2026-03-22 |  |  |  | 2026-04-11 |  |  |  | 2026-05-17 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3883 | LATER | MAJD | SAU4005-G280-ZEN-&MQC-03607 | Steel Structure (V)- REPORT FOR 3rd BATCH | G280 | QA/QC | M-Mechanical engineering (normally including process engineering) | NO | QA/QC | General | SEPCOIII | Steel Structure | IFA | IFD |  |  | 2026-03-22 |  |  |  | 2026-04-11 |  |  |  | 2026-05-17 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3884 | LATER | MAJD | SAU4005-G280-ZEN-&MQC-03608 | Steel Structure (V)- REPORT FOR 4th BATCH | G280 | QA/QC | M-Mechanical engineering (normally including process engineering) | NO | QA/QC | General | SEPCOIII | Steel Structure | IFA | IFD |  |  | 2026-03-22 |  |  |  | 2026-04-11 |  |  |  | 2026-05-17 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3885 | LATER | MAJD | SAU4005-G280-ZEN-&MQC-03609 | Steel Structure (V)- REPORT FOR 5th BATCH | G280 | QA/QC | M-Mechanical engineering (normally including process engineering) | NO | QA/QC | General | SEPCOIII | Steel Structure | IFA | IFD |  |  | 2026-03-22 |  |  |  | 2026-04-11 |  |  |  | 2026-05-17 | [25 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3886 | LATER | MAJD | SAU4005-G280-UZT-&CTB-02003 | Pipe Rack-01(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3887 | LATER | MAJD | SAU4005-G280-UZT-&CTB-02004 | Pipe Rack-06(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3888 | LATER | MAJD | SAU4005-G280-UM_-&CLH-02005 | GTG Intake Platform Superstructure(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3889 | LATER | MAJD | SAU4005-G280-UCA-&CTL-02006 | MAIN ELECTRICAL & CONTROL BUILDING STAIRCASE -2(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3890 | LATER | MAJD | SAU4005-G280-USC-&CTB-02007 | AIR COMPRESSOR SHED(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3891 | LATER | MAJD | SAU4005-G280-UZT-&CTB-02008 | Pipe Rack-04(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3892 | LATER | MAJD | SAU4005-G280-UZT-&CTB-02009 | Pipe Rack-05(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3893 | LATER | MAJD | SAU4005-G280-UBB-&CTB-02010 | GENERATOR CIRCUIT BREAKER UNIT - 11, 12 & 13SUPPORTING STRUCTURE DETAILS(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3894 | LATER | MAJD | SAU4005-G280-UZT-&CTB-02011 | CABLE RACK CR-01(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3895 | LATER | MAJD | SAU4005-G280-UZT-&CTB-02012 | CABLE RACK CR-02(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3896 | LATER | MAJD | SAU4005-G280-UGD-&CTL-02013 | WATER AND EFFLUENT TREATMENT BUILDING(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3897 | LATER | MAJD | SAU4005-G280-UMB-&CTB-02014 | GAS TURBINE, GENERATOR & AUXILIARIES AREA UNIT-11, 12 & 13 - MISC. PLATFORM(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3898 | LATER | MAJD | SAU4005-G280-UGA-&CTB-02015 | Raw water Buffer Storage Tank with Unloading Area(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3899 | LATER | MAJD | SAU4005-G280-UEL-&CTB-02016 | FUEL OIL PUMP SHED(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3900 | LATER | MAJD | SAU4005-G280-UZT-&CTB-02017 | PIPE RACK PR-14(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3901 | LATER | MAJD | SAU4005-G280-UZT-&CTB-02018 | PIPE RACK PR-09(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3902 | LATER | MAJD | SAU4005-G280-UZT-&CTB-02019 | PIPE RACK PR-02(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3903 | LATER | MAJD | SAU4005-G280-UZT-&CTB-02020 | PIPE RACK PR-03(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3904 | LATER | MAJD | SAU4005-G280-UZT-&CTB-02021 | PIPE RACK PR-10(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3905 | LATER | MAJD | SAU4005-G280-UST-&CTB-02022 | WORKSHOP AND WAREHOUSE BUILDING(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3906 | LATER | MAJD | SAU4005-G280-UTG-&CTB-02023 | HYDROGEN CYLINDER STORAGE SHED(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3907 | LATER | MAJD | SAU4005-G280-UZT-&CTB-02024 | PIPE RACK PR-07(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3908 | LATER | MAJD | SAU4005-G280-UGD-&CTB-02025 | DM AND SERVICE WATER PUMP SHED(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3909 | LATER | MAJD | SAU4005-G280-UZT-&CTB-02026 | PIPE RACK PR-16(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3910 | LATER | MAJD | SAU4005-G280-USG-&CTB-02027 | FIRE WATER PUMP HOUSE(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3911 | LATER | MAJD | SAU4005-G280-UBA-&CTL-02028 | GT PACKAGE MCC/CONTROL ROOM -11,12,13 STAIRCASE-2(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3912 | LATER | MAJD | SAU4005-G280-UBL-&CTB-02029 | IPBD GT Unit - 11, 12, & 13：SUPPORT STRUCTURE(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-01-29 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3913 | LATER | MAJD | SAU4005-G280-UZT-&CTB-02030 | PIPE RACK PR-15(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-03-10 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3914 | LATER | MAJD | SAU4005-G280-UZT-&CTB-02031 | PIPE RACK PR-18(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-03-10 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3915 | LATER | MAJD | SAU4005-G280-UBL-&CTB-02032 | ST-10 IPBD SUPPORT STRUCTURE(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-03-10 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3916 | LATER | MAJD | SAU4005-G280-UZT-&CTB-02033 | PIPE RACK PR-08(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-03-10 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3917 | LATER | MAJD | SAU4005-G280-G__-&CTB-02034 | SLUDGE DEWATERING SHED(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-03-10 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3918 | LATER | MAJD | SAU4005-G280-UBF-&CLB-02035 | ST-GENERATOR STEP-UP TRANSFORMER(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-03-10 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3919 | LATER | MAJD | SAU4005-G280-UZT-&CED-02036 | PIPE SLEEPER SL-01(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-03-10 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3920 | LATER | MAJD | SAU4005-G280-UZT-&CTB-02037 | PIPE SLEEPER SL-03(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-03-10 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3921 | LATER | MAJD | SAU4005-G280-UMA-&CED-02038 | STG BUILDING(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-03-10 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3922 | LATER | MAJD | SAU4005-G280-UTS-&CTL-02039 | CHEMICAL STORAGE BUILDING (V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-03-10 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3923 | LATER | MAJD | SAU4005-G280-UZT-&CTB-02040 | PIPE SLEEPER SL-02(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-03-10 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3924 | LATER | MAJD | SAU4005-G280-UZT-&CTB-02041 | PIPE RACK PR-17(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-03-10 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3925 | LATER | MAJD | SAU4005-G280-UBA-&CTL-02042 | UNIT MV/LV ELECTRICAL SWITCHGEAR BUILDING (UNIT #11, #12 & #13)(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-03-10 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3926 | LATER | MAJD | SAU4005-G280-UZT-&CTB-02043 | PIPE RACK PR-12(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-03-10 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3927 | LATER | MAJD | SAU4005-G280-UZT-&CTB-02044 | PIPE SLEEPER SL-05(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-03-10 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW | 3928 | LATER | MAJD | SAU4005-G280-UYX-&CTL-02045 | foam tank shelter(V)-Wrok shop drawing | G280 | Engineering | M-Mechanical engineering (normally including process engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-03-10 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3929 | LATER | TSSC | SAU4005-G280-UGD-&CTB-02500 | Steel Structure （V）-Water and Effluent treatment building Cladding Shop Drawing | G280 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-04-30 |  | 2026-04-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3930 | LATER | TSSC | SAU4005-G280-UEL-&CTB-02501 | Steel Structure （V）-Fuel Oil Pump Shed Cladding Shop Drawing | G280 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-04-30 |  | 2026-04-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3931 | LATER | TSSC | SAU4005-G280-USC-&CTB-02502 | Steel Structure （V）-Air Compressor Building Cladding Shop Drawing | G280 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-07-30 |  | 2026-04-07 | [19 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3932 | LATER | TSSC | SAU4005-G280-UTS-&CTB-02503 | Steel Structure （V）-Chemical Storage Building Cladding Shop Drawing | G280 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-07-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3933 | LATER | TSSC | SAU4005-G280-UMA-&CTB-02504 | Steel Structure （V）-STG Building Cladding Shop Drawing | G280 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-07-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3934 | LATER | TSSC | SAU4005-G280-UST-&CTB-02505 | Steel Structure （V）-Workshop and Warehouse Building Cladding Shop Drawing | G280 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-07-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3935 | LATER | TSSC | SAU4005-G280-USG-&CTB-02506 | Steel Structure （V）-Fire Water Pump House Cladding Shop Drawing | G280 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-07-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3936 | LATER | TSSC | SAU4005-G280-UZD-&CTB-02507 | Steel Structure （V）-Car Parking Shed Cladding Shop Drawing | G280 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-07-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3937 | LATER | TSSC | SAU4005-G280-UYP-&CTB-02508 | Steel Structure （V）-Fire Station Building Cladding Shop Drawing | G280 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-07-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3938 | LATER | TSSC | SAU4005-G280-UGA-&CTB-02509 | Steel Structure （V）-GT MCC Roof GCB Shed Cladding Shop Drawing | G280 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-05-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3939 | LATER | TSSC | SAU4005-G280-UGD-&CTB-02510 | Steel Structure （V）-DM and Service Water Pump Shed Cladding Shop Drawing | G280 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-05-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3940 | LATER | TSSC | SAU4005-G280-UTM-&CTB-02511 | Steel Structure （V）-Hydrogen Generation Plant including Electrical Room Cladding Shop Drawing | G280 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-07-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3941 | LATER | TSSC | SAU4005-G280-UYE-&CTB-02512 | Steel Structure （V）-Main Gate House including Sunshade Cladding Shop Drawing | G280 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-07-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3942 | LATER | TSSC | SAU4005-G280-UGQ-&CTB-02513 | Steel Structure （V）-Sludge Dewatering Shed Cladding Shop Drawing | G280 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-05-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3943 | LATER | TSSC | SAU4005-G280-UYX-&CTB-02514 | Steel Structure （V）-Foam Tank Shelter Cladding Shop Drawing | G280 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-05-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO
| NEW ADDED | 3944 | LATER | TSSC | SAU4005-G280-UYE-&CTB-02515 | Steel Structure （V）-Over Watch Cladding Shop Drawing | G280 | Engineering | C-Construction engineering (building construction and civil engineering) | NO | CIVIL&STRUCTURE&ARCHITECTURAL | Civil | SEPCOIII | Steel Structure | IFI | IFC | [14 empty] | 2026-07-30 | [21 empty] | WF Transmittal Vendor-DI&EPC-ACWA | YES | YES | NO